## Perf Targets - DO NOT EDIT
DCAS Six-Month Performance Targets and Numbers of Provisional Appointments To Be Eliminated
6-Month | Number of Provisional Appointments To Be Reduced, By Action Category+
Benchmarks
| Jurisdiction Classification |  |  | Position Classification
Plan Year | Temporary Title Codes | Non-competitive, Exempt, Labor Requests | Titles With Few Incumbents | Broadbanding | Consolidation | Competitive Appointments To Be Made from Eligible Lists | TA/TBTA Transfer | Target Number of Provisionals To Be Reduced
0.5 |  | 2320 |  |  | 84 |  |  | 2404
1 |  | 469 |  |  | 92 |  |  | 561
1.5 | 1171 | 2222 |  |  | 50 |  |  | 3443
2 |  | 316 |  |  | 20 | 6740 |  | 7076
2.5 |  | 790 |  |  | 77 |  |  | 867
3 |  |  |  | 1 |  | 7651 |  | 7652
3.5 | 62 | 516 | [5 empty] | 578
4 |  |  |  |  | 9 | 3104 |  | 3113
4.5 | 392 | 1595 | [5 empty] | 1987
5 |  |  | 987 |  |  | 1588 | 4072 | 6647
Totals @ End | 1625 | 8228 | 987 | 1 | 332 | 19083 | 4072 | 34328
+Adjustment for Multiple Actions has been omitted. The final Action used to reduce the provisional appointment should be reported as the resolution method for the provisional appointment.
Total # of Competitive Class Employees as of 5/31/08 |  |  | 196648
Total # of Provisional Employees as of 5/31/08 |  |  | 37797

## JC Provs
THESE TWO COLUMNS ARE NOT SET TO PRINT |  | DCAS Progress Report
Jurisdictional Classification Actions and Provisional Appointments Resolved Through Jurisdictional Classification
Report Date: 4/30/09
[7 empty] | Number of Provisionals Resolved By |  |  |  |  | Unresolved Titles
Jurisdictional Classification Category
Title Code Subject To Action This Reporting Period | Title Categories Subject To Action This Reporting Period | Titles Subject To Action This Reporting Period | Date Public Hearing Held | Date Resolution Submitted to SCSC | Code for Action Comments | Number of Provisionals Serving In Title | Temporary Title Codes | Non-competitive, Exempt, Labor Requests | Titles With Few Incumbents | Total Provisionals Resolved Per Title | Total Provisionials Remaining Per Title (if any) | Will The Position Be Competitively Examined? (Y/N) | Scheduled Date of Examination
|  | Executive Program Specialist | 2008-12-16 | 2009-02-12 |  | 0 |  |  |  | 0 | 0 | N
|  | Strategic Initiative Specialist | 2008-12-16 | 2009-02-12 |  | 0 |  |  |  | 0 | 0 | N
|  | Confidential Strategy Planner | 2008-12-16 | 2009-02-12 |  | 0 |  |  |  | 0 | 0 | N
52015 |  | Mortuary Technician | n/a | n/a | PC | 40 |  | Reclass to Labor |  | 0 | 40 | N
31621 |  | Inspector (Cement Test) | n/a | n/a |  | 0 |  |  | Delete Vacant Title | 0 | 0 | n/a | n/a
56067 |  | Comprehensive Health Coord. | n/a | n/a |  | 0 |  |  | Delete Vacant Title | 0 | 0 | n/a | n/a
56066 |  | Asst.Comprehensive Health Coord | n/a | n/a |  | 0 |  |  | Delete Vacant Title | 0 | 0 | n/a | n/a
56068 |  | Sr Comprehensive Health Coord | n/a | n/a |  | 0 |  |  | Delete Vacant Title | 0 | 0 | n/a | n/a
51452 |  | Administrator of Youth Svces | n/a | n/a |  | 0 |  |  | Delete Vacant Title | 0 | 0 | n/a | n/a
51450 |  | Admin of YS (Research) | n/a | n/a |  | 0 |  |  | Delete Vacant Title | 0 | 0 | n/a | n/a
51448 |  | Asst Admin of YS | n/a | n/a |  | 0 |  |  | Delete Vacant Title | 0 | 0 | n/a | n/a
51442 |  | Asst Supvr of YS | n/a | n/a |  | 0 |  |  | Delete Vacant Title | 0 | 0 | n/a | n/a
51440 |  | Asst Supvr of YS (Research) | n/a | n/a |  | 0 |  |  | Delete Vacant Title | 0 | 0 | n/a | n/a
51436 |  | Asst YS Specialist | n/a | n/a |  | 0 |  |  | Delete Vacant Title | 0 | 0 | n/a | n/a
51444 |  | Supervisor of YS | n/a | n/a |  | 0 |  |  | Delete Vacant Title | 0 | 0 | n/a | n/a
51446 |  | Supervisor of YS (Research) | n/a | n/a |  | 0 |  |  | Delete Vacant Title | 0 | 0 | n/a | n/a
51438 |  | Youth Services Specialist | n/a | n/a |  | 0 |  |  | Delete Vacant Title | 0 | 0 | n/a | n/a
12616 |  | Training Development Spec Trainee | n/a | n/a |  | 0 |  |  | Delete Vacant Title | 0 | 0 | n/a | n/a
10302 |  | *Word Processor | n/a | n/a |  | 0 |  |  | Delete Vacant Title | 0 | 0 | n/a | n/a
31271 |  | Reg Director (Pest Control) | n/a | n/a | PN | 3 |  | Reclass to Existing NC Title |  | 0 | 3 | N
56093 |  | Community Liaison Worker | n/a | n/a | PN | 160 |  | Reclass to Existing NC Title |  | 0 | 160 | N
56092 |  | Asst Comm Liaison Worker | n/a | n/a | PN | 49 |  | Reclass to Existing NC Title |  | 0 | 49 | N
56094 |  | Senior Comm Liaison Worker | n/a | n/a | PN | 118 |  | Reclass to Existing NC Title |  | 0 | 118 | N
56095 |  | Principal Comm Liaison Worker | n/a | n/a | PN | 123 |  | Reclass to Existing NC Title |  | 0 | 123 | N
56091 |  | Comm.Liaison Trainee | n/a | n/a | PU | 0 |  |  | Delete Vacant Title | 0 | 0 | n/a | n/a
|  | TOTALS |  |  |  | 493 | 0 | 0 | 0 | 0 | 493
*If the total number of resolved provisional appointments is less than the number of provisional appointments scheduled for resolution in the performance targets, an explanation of the reasons why the target has not been met, and a schedule for resolution of the provisional appointments is needed under separate cover.
Code for Action Comments
PC - Pending: Awaiting Union Certification
PN - Pending: Reclassification to an Existing Non-Competitive Title
PU - Pending Union Discussions
DP - Implementation Delayed for Payroll Actions

## PC Provs
THESE TWO COLUMNS ARE NOT SET TO PRINT |  | DCAS Progress Report
Position Classification Actions and Provisional Appointments Resolved Through Position Classification
Report Date: 4/30/09
No. of Provisionals Resolved
By Position Classification
Title Code Subject To Action This Reporting Period | Title Categories Subject To Action This Reporting Period | Titles Subject To Action This Reporting Period | Date Action Began | Date Action Was Finalized | Code for Action Comments | Number of Provisionals Serving In Title | Broadbanding | Consolidation | Total Provisionals Resolved Per Title | Total Provisionals Remaining Per Title (if any)
56093 |  | Community Liaison Worker |  |  | PU | 160 |  |  | 0 | 160
56092 |  | Asst Comm Liaison Worker |  |  | PU | 49 |  |  | 0 | 49
56094 |  | Senior Comm Liaison Worker |  |  | PU | 118 |  |  | 0 | 118
56095 |  | Principal Comm Liaison Worker |  |  | PU | 123 |  |  | 0 | 123
91569 |  | Second Mate |  |  | PC | 5 |  |  | 0 | 5
91526 |  | Chief Mate |  |  | PC | 0 |  |  | 0 | 0
06252 |  | Third Mate |  |  | PC | 4 |  |  | 0 | 4
40510 |  | Accountant |  |  | DP | 153 |  |  | 0 | 153
40517 |  | Associate Accountant |  |  | DP | 4 |  |  | 0 | 4
40526 |  | Bookkeeper |  |  | DP | 127 |  |  | 0 | 127
40527 |  | Associate Bookkeeper |  |  | DP | 121 |  |  | 0 | 121
60860 |  | Business Promotion Coordinator |  |  | DP | 37 |  |  | 0 | 37
60861 |  | Associate Bus. Prom. Coordinator |  |  | DP | 23 |  |  | 0 | 23
40502 |  | Management Auditor |  |  | DP | 110 |  |  | 0 | 110
40503 |  | Associate Management Auditor |  |  | DP | 0 |  |  | 0 | 0
52016 |  | Senior Mortuary Technician |  |  | PC | 17 |  |  | 0 | 17
52017 |  | Principal Mortuary Technician |  |  | PC | 6 |  |  | 0 | 6
52085 |  | Asst. Coord. of Mortuary Services |  |  | PC | 3 |  |  | 0 | 3
52090 |  | Coord. of Mortuary Services |  |  | PC | 1 |  |  | 0 | 1
|  | TOTALS |  |  |  |  | 0 | 0 | 0 | 1061
*If the total number of resolved provisional appointments is less than the number of provisional appointments scheduled for resolution in the performance targets
an explanation of the reasons why the target has not been met, and a schedule for resolution of the provisional appointments is needed under separate cover.
Code for Action Comments
PC - Pending: Awaiting Union Certification
PN - Pending: Reclassification to an Existing Non-Competitive Title
PU - Pending Union Discussions
DP - Implementation Delayed for Payroll Actions

## Comp Appts.
THESE COLUMNS ARE NOT SET TO PRINT |  | DCAS Progress Report
Examinations, Eligible Lists & Provisionals Resolved Through Competitive Means
Report Date: 4/30/09
[5 empty] | Examination Scheduling and Administration |  |  | Eligible List Administration
Title Code Subject To Action This Reporting Period | Title Categories Subject To Action This Reporting Period | Titles Scheduled and/or Subject To Action This Reporting Period | Number of Provisionals Serving In Title | No. of Appointments Made ** | Scheduled Date of Examination | Date Examination Was Held | Date Examination Was Completed | Date Eligible List Established | Date(s) Certified | No. of Eligibles on List at Establishment | No. of Eligibles Remaining on List | Code for Action Comments | Total Provisionals Remaining Per Title (if any) +
21215 |  | ARCHITECT | 42 | 0 |  |  | 2009-01-28 | 2009-03-25 | 2009-03-26 | 98 | 98 | D | 44
71682 |  | ASSOCIATE SANITATION ENFORCEMENT AGENT | 13 | 0 | 2008-12-20 | 2008-12-20 |  |  |  |  | 0 |  | 13
91203 |  | BUS OPERATOR | 0 | 0 |  |  | 2009-03-04 |  |  | 3757 |  | E | 0
70365 |  | CAPTAIN (FIRE) | 0 | 0 | 2008-12-06 | 2008-12-06 | [5 empty] | E | 0
52304 |  | CASEWORKER | 273 | 7 | 2008-12-01 | 2008-12-01 |  |  |  |  | 73 | A | 71
52366 |  | CHILD PROTECTIVE SPECIALIST | 1254 | 311 |  |  | 2009-02-18 | 2009-02-18 | 2/20/09 - 3/26/09 | 386 | 192 | B | 834
52370 |  | CHILD WELFARE SPECIALIST SUPERVISOR | 25 | 0 | 2009-01-31 | 2009-01-31 |  |  |  |  | 0 |  | 23
20215 |  | CIVIL ENGINEER | 90 | 0 |  |  | 2009-02-11 |  |  | 165 | 165 |  | 90
10050 |  | COMPUTER SYSTEMS MANAGER | 848 | 90 |  |  | 2009-01-07 | 2009-01-07 | 1/9/09 - 3/31/09 | 270 | 104 | D | 789
91207 |  | CONDUCTOR | 0 | 0 | 2008-12-06 | 2008-12-06 | [5 empty] | E | 0
34202 |  | CONSTRUCTION PROJECT MANAGER | 161 | 0 | 2009-03-28 | 2009-03-28 |  |  |  |  | 0 |  | 189
70410 |  | CORRECTION OFFICER | 0 | 0 |  |  | 2009-01-21 | 2009-01-21 |  | 1714 |  | E | 0
91898 |  | DISPATCHER (SURFACE TRANSPORTATION) | 0 | 0 |  |  | 2009-02-25 | 2009-02-25 | 2009-02-26 | 1017 |  | E | 0
92010 |  | DOCKBUILDER | 9 | 1 |  |  | 2009-02-11 | 2009-02-11 | 2/17/09 - 2/20/09 | 21 | 20 |  | 8
53053 |  | EMERGENCY MEDICAL SPECIALIST-EMT | 735 | 342 |  |  | 2008-12-10 | 2008-12-10 | 2009-03-18 | 761 | 284 | B | 389
53054 |  | EMERGENCY MEDICAL SPECIALIST-PARAMEDIC | 328 | 93 |  |  | 2009-01-14 | 2009-01-14 | 1/26/09 - 3/16/09 | 133 | 44 | B | 276
70811 |  | ENVIRONMENTAL POLICE OFFICER | 0 | 0 | 2009-01-02 | 2009-01-02 | [5 empty] | E | 0
71022 |  | EVIDENCE AND PROPERTY CONTROL SPECIALIST | 67 | 0 | 2009-02-21 | 2009-02-21 |  |  |  |  | 0 |  | 64
31661 |  | FIRE PROTECTION INSPECTOR | 15 | 0 | 2009-01-24 | 2009-01-24 |  |  |  |  | 2 | A, G | 18
91619 |  | HEATING PLANT TECHNICIAN (HOUSING AUTHORITY) | 170 | 42 |  |  | 2009-01-21 | 2009-01-21 | 2009-01-28 | 44 | 2 | G | 121
31670 |  | INSPECTOR (HOUSING) | 213 | 0 |  |  | 2009-01-14 | 2009-01-14 | 1/27/09 - 3/9/09 | 191 | 191 |  | 208
52314 |  | JOB OPPORTUNITY SPECIALIST | 660 | 0 | 2009-01-24 | 2009-01-24 |  |  |  |  | 0 |  | 694
21315 |  | LANDSCAPE ARCHITECT | 11 | 0 |  |  | 2009-03-04 |  |  | 12 | 12 |  | 10
91885 |  | MAINTENANCE SUPERVISOR (STORES) | 0 | 4 | 2009-02-07 | 2009-02-07 | [5 empty] | E | 0
91893 |  | MAINTENANCE SUPERVISOR (SURFACE) | 0 | 3 | 2009-01-10 | 2009-01-10 | [5 empty] | E | 0
91894 |  | MAINTENANCE SUPERVISOR (TELEPHONES) | 6 | 0 | 2008-12-20 | 2008-12-20 |  |  |  |  | 0 |  | 9
91897 |  | MAINTENANCE SUPERVISOR (VENTILATION AND DRAINAGE) | 0 | 2 |  |  | 2008-12-03 | 2008-12-03 | 1/8/09 - 2/19/09 | 19 | 17 | A | 1
40502 |  | MANAGEMENT AUDITOR | 90 | 0 | 2008-12-13 | 2008-12-13 |  |  |  |  | 0 |  | 110
20415 |  | MECHANICAL ENGINEER | 42 | 7 |  |  | 2009-02-04 | 2009-02-04 | 2/12/09 - 3/31/09 | 81 | 66 |  | 36
90728 |  | MECHANICAL MAINTAINER - GROUP C | 6 | 0 | 2009-03-09 | 2009-03-09 |  |  |  |  | 1 | A, G | 6
70210 |  | POLICE OFFICER | 0 | 1 |  |  | 12/24/2008 - 1/9/2009 | 12/24/2008 - 1/9/2009 | 2009-01-14 | 8230 |  | E | 0
91736 |  | POWER CABLE MAINTAINER | 40 | 1 |  |  | 2009-01-14 | 2009-01-14 | 2009-01-27 | 1 | 0 |  | 42
91738 |  | POWER MAINTAINER, GROUP B | 24 | 23 |  |  | 2009-01-21 | 2009-01-21 | 2009-01-28 | 28 | 2 | G | 8
51810 |  | PROBATION OFFICER | 27 | 0 | 2008-12-13 | 2008-12-13 |  |  |  |  | 9 | A | 30
92050 |  | REVENUE EQUIPMENT MAINTAINER | 0 | 0 | 2008-12-20 | 2008-12-20 | [5 empty] | E | 0
60817 |  | SCHOOL SAFETY AGENT | 133 | 0 | 2008-12-20 | 2008-12-20 |  |  |  |  | 78 | A | 308
90767 |  | SENIOR SEWAGE TREATMENT WORKER | 89 | 0 |  |  | 2009-01-28 | 2009-01-28 | 2009-02-02 | 241 | 241 |  | 87
70235 |  | SERGEANT (POLICE) | 0 | 58 | 2009-02-07 | 2009-02-07 | [5 empty] | E | 0
90739 |  | SEWAGE TREATMENT WORKER | 248 | 1 | 2009-02-21 | 2009-02-21 |  |  |  |  | 0 |  | 260
92025 |  | SHIP CARPENTER | 6 | 0 |  |  | 2009-02-18 |  |  | 9 | 9 |  | 6
91741 |  | SIGNAL MAINTAINER | 18 | 0 | 2009-01-13 | 2009-01-13 |  |  |  |  | 27 | A | 16
30315 |  | SUPERVISING DEPUTY SHERIFF-AL I ((ONLY)) | 0 | 1 |  |  | 2008-12-24 | 2008-12-24 | 2009-01-06 | 14 |  | E | 0
71060 |  | SUPERVISING FIRE ALARM DISPATCHER | 8 | 0 | 2008-12-20 | 2008-12-20 |  |  |  |  | 0 |  | 12
71013 |  | SUPERVISING POLICE COMMUNICATIONS TECHNICIAN | 13 | 0 |  |  | 2009-02-11 | 2009-02-11 | 2009-02-18 | 47 | 47 |  | 11
52311 |  | SUPERVISOR I (SOCIAL SERVICES) | 158 | 0 | 2009-01-31 | 2009-01-31 |  |  |  |  | 0 |  | 162
52631 |  | SUPERVISOR I (SOCIAL WORK) | 31 | 0 | 2009-01-31 | 2009-01-31 |  |  |  |  | 0 |  | 31
12204 |  | SUPERVISOR OF HOUSING STOCK WORKERS | 4 | 0 | 2008-12-13 | 2008-12-13 |  |  |  |  | 0 |  | 4
11704 |  | SUPERVISOR OF OFFICE MACHINE OPERATIONS | 41 | 0 | 2009-02-28 | 2009-02-28 |  |  |  |  | 0 |  | 40
12202 |  | SUPERVISOR OF STOCK WORKERS | 84 | 0 | 2008-12-13 | 2008-12-13 |  |  |  |  | 0 |  | 84
91801 |  | TRACK EQUIPMENT MAINTAINER | 17 | 0 | 2009-03-10 | 2009-03-10 |  |  |  |  | 1 | A, G | 16
71651 |  | TRAFFIC ENFORCEMENT AGENT | 724 | 0 | 2008-12-01 | 2008-12-01 |  |  |  |  | 203 | A | 521
[12 empty] | TOTAL | 5641
*If the total number of resolved provisional appointments is less than the number of provisional appointments scheduled for resolution in the performance targets, an
explanation of the reasons why the target has not been met, and a schedule for resolution of the provisional appointments is needed under separate cover.
+ This cannot be a formula since appointments are made for a variety of different reasons, not always to replace provisionals.
**Appointments made may include filling vacancies as well as replacing provisionals.
Code for Action Comments
A - Eligibles remaining on lists established prior to the reporting period.
B - Multiple lists were established; some lists were established prior to the reporting period.
C - This is a promo only list; appointments were made in agencies with no lists.
D - Provisional appointments were made prior to list establishment.
E - "No. of Eligibles Remaining on List" is not reported as no provisionals were serving during the reporting period.
F - Multiple lists established; Old List is non-viable; New List recently established.
G - List is currently non-viable.
H - Data Error Being Investigated.
I - Provisionals Resolved after 03/31/09 Charter.

## TA_TBTA Transfer
DCAS Progress Report
Summary of Progress to Secure TA/TBTA Transfer Legislation
Report Date: 4/30/09
Date Action Occurred | Action Description
2009-02-20 | DCAS discussed with TA the terms regarding their use of the DCAS databases.
2009-03-05 | DCAS met with TA to discuss technical issues related to the option of using our systems.
2009-03-26 | DCAS met with TA to review TA's proposed targets for the divestiture.