## Sheet1 (hidden)
Work Completed
A | B | C | C1 | C2 | D | E | F | G | H | I | J
ITEM NO. | UNFORMAT CODE | DESCRIPTION OF WORK |  |  | Schedule of Value (SOV) | From Previous Application | This Pay Period [F] - [G] | Total Value of Materials Presently Stored (not included in G or H) | Total Completed | % Complete [H]/[[D] | Balance to Finish [D] - [H]
|  |  |  | TOTALS: | 2747095 | 163141.1505 | 38927.1737 | 52500 | 254568.3242 | 9.267% | 2301326.6758
1 |  | General Requirements |  |  | 105000 | 26077 | 2758.6164 | 0 | 28835.6164 | 27.46% | 76164.3836
2 | Z70 | Mobilization *3 |  |  | 25000 | 25000 | 0 | 0 | 25000 | 100% | 0
3 | Z30 | Supervision/Project Coordination *1 |  |  | 50000 | 85 | 2312.2603 | 0 | 2397.2603 | 4.795% | 47602.7397
4 | Z60 | Submittals & Shop drawings*1 |  |  | 7000 | 200 | 135.6164 | 0 | 335.6164 | 4.795% | 6664.3836
5 | Z50 | Permits & Fees*1 |  |  | 1000 | 35 | 12.9452 | 0 | 47.9452 | 4.795% | 952.0548
6 | Z60 | Health & Safety*1 |  |  | 1000 | 25 | 22.9452 | 0 | 47.9452 | 4.795% | 952.0548
7 | Z60 | Waste Management* |  |  | 20000 | 700 | 258.9041 | 0 | 958.9041 | 4.795% | 19041.0959
8 | Z70 | Site Cleaning*1 |  |  | 1000 | 32 | 15.9452 | 0 | 47.9452 | 4.795% | 952.0548
9 |  | General Requirements/ Unit Price Work | Unit Price | Total Qty | 214125 | 6506.1707 | 14405.8164 | 0 | 20911.987 | 9.766% | 193213.013
10 | Z40 | Temporary Electrical Service*2 | 53.9957 | 463 | 25000 | 291.5533 | 2408.2307 | 0 | 2699.784 | 10.8% | 22300.216
11 | Z40 | Temporary Heat*2 | 39.9568 | 463 | 18500 | 200 | 199.568 | 0 | 399.568 | 2.16% | 18100.432
12 | Z40 | Field Office*2 | 158.5313 | 463 | 73400 | 5000 | 2926.5659 | 0 | 7926.5659 | 10.8% | 65473.4341
13 | Z40 | Rodent & Insect Control*2 | 9.7192 | 463 | 4500 | 52.4796 | 433.4815 | 0 | 485.9611 | 10.8% | 4014.0389
14 | Z30 | Security Guards*2 | 138.9309 | 463 | 64325 | 750.1668 | 6196.3775 | 0 | 6946.5443 | 10.8% | 57378.4557
15 | Z40 | Sidewalk Sheds*2 | 61.3391 | 463 | 28400 | 211.9709 | 2241.5928 | 0 | 2453.5637 | 8.639% | 25946.4363
16 |  | Site Preparation |  |  | 526000 | 109750 | 6250 | 0 | 116000 | 22.05% | 410000
17 | F10 | Special Construction Segments |  |  | 50000 | 0 | 0 | 0 | 0 | 0% | 50000
18 | F20 | Facility Hazardous Remediation |  |  | 75000 | 75000 | 0 | 0 | 75000 | 100% | 0
19 | F30 | Demolition Existing Building |  |  | 25000 | 6250 | 6250 | 0 | 12500 | 50% | 12500
20 | G10 | Site Element Demolition & Relocation |  |  | 18500 | 18500 | 0 | 0 | 18500 | 100% | 0
21 | G10 | Site Eartwork & Excavation |  |  | 67000 | 0 | 0 | 0 | 0 | 0% | 67000
22 | G20 | Site Improvements |  |  | 99000 | 0 | 0 | 0 | 0 | 0% | 99000
23 | G10 | Erosion & Sediment Control Measures |  |  | 10000 | 10000 | 0 | 0 | 10000 | 100% | 0
24 | G30 | Site Mechanical Utilities |  |  | 68500 | 0 | 0 | 0 | 0 | 0% | 68500
25 | G40 | Electrical Site Improvements |  |  | 76500 | 0 | 0 | 0 | 0 | 0% | 76500
26 | G50 | Site Communication |  |  | 8500 | 0 | 0 | 0 | 0 | 0% | 8500
27 | G90 | Miscellaneous Site Construction |  |  | 28000 | 0 | 0 | 0 | 0 | 0% | 28000
28 |  | Foundation |  |  | 100100 | 0 | 0 | 0 | 0 | 0% | 100100
29 | A10 | Foundation Formwork |  |  | 36000 | 0 | 0 | 0 | 0 | 0% | 36000
30 | A10 | Foundation Rebar |  |  | 14400 | 0 | 0 | 0 | 0 | 0% | 14400
31 | A10 | Foundation Concrete |  |  | 6000 | 0 | 0 | 0 | 0 | 0% | 6000
32 | A20 | Subgrade Enclosures |  |  | 11500 | 0 | 0 | 0 | 0 | 0% | 11500
33 | A40 | Slab-On-Grade Construction |  |  | 26700 | 0 | 0 | 0 | 0 | 0% | 26700
34 | A60 | Site Water & Gas Mitigation |  |  | 2000 | 0 | 0 | 0 | 0 | 0% | 2000
35 | A90 | Substructure Related Activities |  |  | 3500 | 0 | 0 | 0 | 0 | 0% | 3500
36 |  | Building Construction |  |  | 324500 | 0 | 0 | 0 | 0 | 0% | 324500
37 | B10 | Superstructure |  |  | 197500 | 0 | 0 | 0 | 0 | 0% | 197500
38 | B20 | Exterior Vertical Enclosures |  |  | 2500 | 0 | 0 | 0 | 0 | 0% | 2500
39 | B20 | Framing |  |  | 19500 | 0 | 0 | 0 | 0 | 0% | 19500
40 | B20 | Exterior Doors |  |  | 26000 | 0 | 0 | 0 | 0 | 0% | 26000
41 | B20 | Exterior Windows |  |  | 40500 | 0 | 0 | 0 | 0 | 0% | 40500
42 | B20 | Insulation |  |  | 2700 | 0 | 0 | 0 | 0 | 0% | 2700
43 | B30 | Roofing |  |  | 35800 | 0 | 0 | 0 | 0 | 0% | 35800
44 |  | Interior Construction |  |  | 341100 | 0 | 0 | 0 | 0 | 0% | 341100
45 | C10 | Interior Walls |  |  | 45000 | 0 | 0 | 0 | 0 | 0% | 45000
46 | C10 | Drywall |  |  | 38000 | 0 | 0 | 0 | 0 | 0% | 38000
47 | C10 | Interior Doors, Frames & Hardware |  |  | 23600 | 0 | 0 | 0 | 0 | 0% | 23600
48 | C10 | Kitchen & Toilet Cabinets |  |  | 21300 | 0 | 0 | 0 | 0 | 0% | 21300
49 | C10 | Stair Construction |  |  | 18700 | 0 | 0 | 0 | 0 | 0% | 18700
50 | C10 | Flooring Construction |  |  | 120000 | 0 | 0 | 0 | 0 | 0% | 120000
51 | C10 | Ceilings Construction |  |  | 40000 | 0 | 0 | 0 | 0 | 0% | 40000
52 | C20 | Painting & Wall Finishes |  |  | 34500 | 0 | 0 | 0 | 0 | 0% | 34500
53 |  | Fire Protection & Safety |  |  | 98500 | 0 | 0 | 0 | 0 | 0% | 98500
54 | C10 | Exit Signages |  |  | 5500 | 0 | 0 | 0 | 0 | 0% | 5500
55 | D40 | Fire Suppression System |  |  | 84500 | 0 | 0 | 0 | 0 | 0% | 84500
56 | D50 | Emergency Lightings |  |  | 8500 | 0 | 0 | 0 | 0 | 0% | 8500
57 |  | Plumbing Fixture Installation |  |  | 91600 | 0 | 0 | 0 | 0 | 0% | 91600
58 | D20 | Sinks, Toilets & Showers |  |  | 8500 | 0 | 0 | 0 | 0 | 0% | 8500
59 | D20 | Domestic Water Supply Connection |  |  | 13400 | 0 | 0 | 0 | 0 | 0% | 13400
60 | D20 | Sanitary Waste & Drainage Lines Connection |  |  | 32900 | 0 | 0 | 0 | 0 | 0% | 32900
61 | G30 | Site Water Supply Connection |  |  | 36800 | 0 | 0 | 0 | 0 | 0% | 36800
62 |  | Electrical Fixture Installation |  |  | 103120 | 0 | 0 | 0 | 0 | 0% | 103120
63 | D50 | Electric Panel |  |  | 9750 | 0 | 0 | 0 | 0 | 0% | 9750
64 | D50 | Light Fixtures, Switches & Outlets |  |  | 20000 | 0 | 0 | 0 | 0 | 0% | 20000
65 | D50 | Electrical Wiring Connection |  |  | 31850 | 0 | 0 | 0 | 0 | 0% | 31850
66 | D60 | Communication |  |  | 31520 | 0 | 0 | 0 | 0 | 0% | 31520
67 | D70 | Electrical Safety & Security |  |  | 8500 | 0 | 0 | 0 | 0 | 0% | 8500
68 | D80 | Integrated Automation |  |  | 1500 | 0 | 0 | 0 | 0 | 0% | 1500
69 |  | HVAC Installation |  |  | 54750 | 0 | 0 | 0 | 0 | 0% | 54750
70 | D30 | Hot Water Boiler |  |  | 6950 | 0 | 0 | 0 | 0 | 0% | 6950
71 | D30 | Cooling Units Installation |  |  | 3700 | 0 | 0 | 0 | 0 | 0% | 3700
72 | D30 | Heating Units Installation |  |  | 28900 | 0 | 0 | 0 | 0 | 0% | 28900
73 | D30 | HVAC Building Management System |  |  | 15200 | 0 | 0 | 0 | 0 | 0% | 15200
74 |  | Conveyance Installation |  |  | 100000 | 0 | 0 | 0 | 0 | 0% | 100000
75 | D10 | Elevator System Installation |  |  | 100000 | 0 | 0 | 0 | 0 | 0% | 100000
76 |  | Equipment & Furnishings |  |  | 5000 | 0 | 0 | 2000 | 2000 | 40% | 3000
77 | E10 | Equipment |  |  | 2500 | 0 | 0 | 1000 | 1000 | 40% | 1500
78 | E20 | Furnishings |  |  | 2500 | 0 | 0 | 1000 | 1000 | 40% | 1500
79 |  | Landscaping & Exterior Works |  |  | 185900 | 0 | 0 | 50500 | 50500 | 27.17% | 135400
80 | D20 | Wastewater & Stormwater Conveyance System |  |  | 32400 | 0 | 0 | 0 | 0 | 0% | 32400
81 | D30 | Fuel Tank |  |  | 3500 | 0 | 0 | 500 | 500 | 14.29% | 3000
82 | D50 | Generators |  |  | 65000 | 0 | 0 | 50000 | 50000 | 76.92% | 15000
83 | F10 | Special Structure Construction |  |  | 28500 | 0 | 0 | 0 | 0 | 0% | 28500
84 | G20 | Landscaping |  |  | 8400 | 0 | 0 | 0 | 0 | 0% | 8400
85 | G20 | Entryways, Sidewalks, Walkways & Access Compliance with ADA |  |  | 28500 | 0 | 0 | 0 | 0 | 0% | 28500
86 | G40 | Exterior Electrical & Signage Installation |  |  | 19600 | 0 | 0 | 0 | 0 | 0% | 19600
87 |  | Testing & Commissioning |  |  | 6000 | 0 | 0 | 0 | 0 | 0% | 6000
88 | Z70 | Testing & Commissioning Conveyance Installation |  |  | 1000 | 0 | 0 | 0 | 0 | 0% | 1000
89 | Z70 | Testing & Commissioning Plumbing Installation |  |  | 1000 | 0 | 0 | 0 | 0 | 0% | 1000
90 | Z70 | Testing & Commissioning Fuel Tank & Generators |  |  | 1000 | 0 | 0 | 0 | 0 | 0% | 1000
91 | Z70 | Testing & Commissioning HVAC Installation |  |  | 1000 | 0 | 0 | 0 | 0 | 0% | 1000
92 | Z70 | Testing & Commissioning Fire Protection |  |  | 1000 | 0 | 0 | 0 | 0 | 0% | 1000
93 | Z70 | Testing & Commissioning Electrical Installation |  |  | 1000 | 0 | 0 | 0 | 0 | 0% | 1000
94 |  | Operations & Maintenance Manual |  |  | 1000 | 0 | 0 | 0 | 0 | 0% | 1000
95 | Z60 | Operations & Maintenance Manual Submission |  |  | 1000 | 0 | 0 | 0 | 0 | 0% | 1000
96 |  | Final Inspections & Certifications |  |  | 5000 | 0 | 0 | 0 | 0 | 0% | 5000
97 | Z70 | Final Inspections & Walkthrough |  |  | 1000 | 0 | 0 | 0 | 0 | 0% | 1000
98 | Z70 | Punchlist Items |  |  | 2000 | 0 | 0 | 0 | 0 | 0% | 2000
99 | Z70 | Certificate of Occupancy |  |  | 2000 | 0 | 0 | 0 | 0 | 0% | 2000
100 |  | Final Walkthrough & Handover |  |  | 27000 | 0 | 0 | 0 | 0 | 0% | 27000
101 | Z70 | Final Walkthrough |  |  | 1000 | 0 | 0 | 0 | 0 | 0% | 1000
102 | Z70 | Signoff |  |  | 25000 | 0 | 0 | 0 | 0 | 0% | 25000
103 | Z70 | Handover |  |  | 1000 | 0 | 0 | 0 | 0 | 0% | 1000
104 |  | Unit Price Work | Unit Price | Total Qty | 76000 | 20807.9799 | 15512.7408 | 0 | 36320.7207 | 47.79% | 39679.2793
105 | W10 | Work Item 01*2 | 270.2703 | 37 | 10000 | 1643.5354 | 2410.5186 | 0 | 4054.0541 | 40.54% | 5945.9459
106 | W10 | Work Item 02*2 | 880 | 25 | 22000 | 3520 | 5280 | 0 | 8800 | 40% | 13200
107 | W10 | Work Item 03*2 | 293.3333 | 75 | 22000 | 1564.4444 | 4302.2222 | 0 | 5866.6667 | 26.67% | 16133.3333
108 | W10 | Work Item 04*2 | 1466.6667 | 15 | 22000 | 14080 | 3520 | 0 | 17600 | 80% | 4400
109 |  | Contract Allowances |  |  | 191200 | 0 | 0 | 0 | 0 | 0% | 191200
110 | W10 | Allowance 01 - Price Adjustment Allowance: Asphalt, Fuel, or Steel Products |  |  | 65000 | 0 | 0 | 0 | 0 | 0% | 65000
111 | W10 | Allowance 02 - EWA (Expanded Work Allowance) |  |  | 10000 | 0 | 0 | 0 | 0 | 0% | 10000
112 | W10 | Allowance 03 - Excavation and Disposal of Potentially Contaminated Soils |  |  | 95000 | 0 | 0 | 0 | 0 | 0% | 95000
113 | W10 | Allowance 04 - GC Allowance for Incidental Asbestos Abatement |  |  | 12000 | 0 | 0 | 0 | 0 | 0% | 12000
114 | W10 | Allowance 05 - Lead Remediation |  |  | 9200 | 0 | 0 | 0 | 0 | 0% | 9200
115 |  | Change Orders |  |  | 191200 | 0 | 0 | 0 | 0 | 0% | 0
116 | CO001 | Change Order 001 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0
117 | CO002 | Change Order 002 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0
118 | CO003 | Change Order 003 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0
119 | CO004 | Change Order 004 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0
120 |  | Totals: |  |  | 2555895 | 163141.1505 | 38927.1737 | 52500 | 254568.3242 | 9.96% | 2301326.6758
[9 empty] | Retainage 5%* [H] |  | 115066.3338

## Blank Sub (hidden)
Work Completed
A | B | C | C1 | C2 | D | E | F | G | H | I | J
ITEM NO. | UNFORMAT CODE | DESCRIPTION OF WORK | Lump Sum or Unit Cost | Total Qty (Unit Cost Items) | Total Schedule of Value (SOV) | From Previous Application | This Pay Period [F] - [G] | Total Value of Materials Presently Stored (not included in G or H) |  | % Complete [H]/[[D] | Balance to Finish [D] - [H]
Total Completed
|  |  |  | TOTALS: | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  | General Requirements |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
1 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  | General Requirements/ Unit Price Work | Unit Price | Total Qty | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  | Site Preparation |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  | Foundation |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  | Building Construction |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  | Interior Construction |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  | Fire Protection & Safety |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  | Plumbing Fixture Installation |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
24 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  | Electrical Fixture Installation |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
26 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  | HVAC Installation |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
28 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
29 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
30 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  | Conveyance Installation |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
31 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  | Equipment & Furnishings |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
32 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
33 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  | Landscaping & Exterior Works |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
34 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
35 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
36 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  | Testing & Commissioning |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
37 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
38 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  | Operations & Maintenance Manual |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
39 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  | Final Inspections & Certifications |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
40 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
41 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
42 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  | Final Walkthrough & Handover |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
43 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
44 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
45 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  | Unit Price Work | Unit Price | Total Qty | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
46 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
47 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
48 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
49 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  | Contract Allowances |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
50 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
51 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
52 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  | Change Orders |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
53 | CO001 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0
54 | CO002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0
54 | CO003 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0
|  | Totals: |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
[9 empty] | Retainage 5%* [H] |  | 0

## Payment Detail
#VALUE! | [8 empty] | Payment Detail
Project ID | Contract Registration Number |  | Work Order Number |  |  |  | Change Order Number
Project Address
Payment Number | Project Number |  | Payment Period From |  |  |  | Payment Period To |  |  | Submission Date
(Columns A through D determined by agreed upon SOV) |  |  |  |  | Work Completed
A | B | C1 | C2 | D | E | F | G | H | I | J | K
ITEM NO. | DESCRIPTION OF WORK | Total Qty (Unit Cost Items) | Lump Sum or Unit Cost | Total Schedule of Value (SOV) | From Previous Application | This Pay Period | Total Earned | Total Value of Materials Presently Stored (not included in E or F) | Total Completed and Stored to Date col. [G] + [H] | % Complete col. [I] / [D] | Balance to Finish col. [D] - [I]
col. [E] + [F]
Total Completed and Stored to Date [G] + [H]
|  |  | Totals: | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
#DIV/0!
#DIV/0!
#DIV/0!
|  | Total Qty | Unit Cost | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | #DIV/0! | 0
0
0
0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  | Total Qty | Unit Cost | 0 |  | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | #DIV/0! | 0
0
0
0
0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
[6 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Totals: |  |  | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
CM/REI | [9 empty] | Retainage 5%* col. [G] | 0
| Title |  | Signature |  | Date (MM/DD/YY)
DDC PM/EIC
| Title |  | Signature |  | Date (MM/DD/YY)

## Payment Summary and Certificati
#VALUE! |  |  |  | Payment Summary and Certification
0 |  | 0 | 0 |  | 0
Project ID | Contract Registration Number |  | Work Order Number |  | Change Order Number
0
Project Address
0 |  | 0 | 0 |  | 0 | 0
Payment Number | Project Number |  | Payment Period From |  | Payment Period To | Submission Date
1. TOTAL COMPLETED & STORED (Column I on Payment Detail / Line (A) From Totals Report): | [6 empty] | 0
2. RETAINAGE/STORED MATERIALS WITHHOLDING:
2A. |  | % of Completed Work (Column G on Payment Detail / Line (B1) on Totals Report, except where variable) |  |  |  | 0
2B. |  | % of Stored Material (Column h on Stored Materials Summary) |  |  |  | 0
2C. | Total Retainage/Withholding (Line 2A+2B) | [5 empty] | 0
3. Total Completed & Stored Less Retainage/Withholding ((Line 1) - (Line 2C)) | [6 empty] | 0
Contractor's Certificate
The undersigned Contractor certifies that all items, units, quantities and prices of work and material shown on this estimate are correct; that all work has been performed and material supplied in full accordance with the terms and conditions of the Contract between the Department of Design and Construction of the City of New York and ___________________________(Contractor) dated , 20 , and all authorized changes thereto; that all Contract reports are attached; that all outstanding claims for labor, materials and equipment for the performance of said Contract have been paid in full in accordance with the requirements of said Contract, except the outstanding claims listed in the attached sheet, “Certificate of Contractor to the Comptroller”; that the above is a true and correct statement of the contract account up to and including the last day of the period covered by this estimate and that no part of the “Current Payment Due” has been received.
Print Name |  | Title |  | Federal Taxpayer I.D Number
Signature |  |  |  | Invoice Date (MM/DD/YY)
DDC Project Manager Certificate
I certify that I have verified this estimate and that to the best of my knowledge and belief it is a true and correct statement of the work performed and materials supplied by the Contractor and that all work and material included in this estimate has been inspected by me or my duly authorized assistants and has been found to comply with the terms and conditions of the corresponding construction contract documents and authorized changes thereto. I further certify that I have verified that certificates of non-discrimination have been obtained from the Contractor and all Subcontractors who performed any work covered by this payment and that the Subcontractor’s Payment Form, if applicable to this payment, has been obtained.
NTP Date
Contract Time |  |  | Time Consumed to Date
Time Elapsed | 0% |  | Work Completed (%) |  | #DIV/0!
CM/REI (if applicable)
| Print Name |  | Title | Signature |  | Date (MM/DD/YY)
DDC PM/EIC
| Print Name |  | Title | Signature |  | Date (MM/DD/YY)
Formulas:
Change Order Number = IF([Contract Registration Number, row above]="","",TODAY()-[Contract Registration Number, row above])

## Stored Materials Summary
Stored Materials Summary
0 |  | 0 |  | 0 |  | 0
Project ID |  | Contract Registration Number |  | Work Order Number |  | Change Order Number
0
Project Address
0 |  | 0 |  | 0 |  | 0 | 0
Payment Number |  | Project Number |  | Payment Period From |  | Payment Period To | Submission Date
Table I:
|  |  |  | Quantities |  | Values
a | b | c | d | e | f | g | h
Item Number/Budget Line | Item Description and Units | Stored at the End of Last Period | Newly Stored This Period | Installed This Period ≤ col. [d] | Stored On and Off Site at the End of This Period col. [c] + [d] - [e] | Unit Cost | Total Cost Stored On and Off Site col. [f] x [g]
0
0
0
0
0
0
0
0
Total
|  |  |  | (A) Value of material in storage at the end of this period. (Col. h Total) |  |  | 0
|  |  |  | (B) Less value of materials lost, missing or rejected. (See Table II below) |  |  | 0
|  |  |  | (C) Net value of materials in storage at the end of this period. (A - B) |  |  | 0
(D) Percentage payable under contract. (See Contract Specifications)
|  |  |  | Amount due for materials in storage. (C x D) |  |  | 0
Table II:
Material or Equipment Lost, Missing, or Rejected at the Time Inspection was Made.
Item Number/Budget Line | Item Description and Units | Invoice Number |  | Vendor |  |  | Requistioned Amount
[6 empty] | Total | 0
This above materials or equipment is stored at the location(s) indicated above and I have inspected the above materials or equipment while at the location(s) specificed and I find that:
(I) The materials or equipent stored is the same as indicated on paid invoiced submitted to the Department of Design and Construction for payment of such materials or equipment.
(II) The quantities of materials or equipment in storage is the same as indicated under Column f, except as indicated above in Table II.
(III) The material or equipment in storage is tagged "Property of the City of New York".
Contractor's Representative
| Print Name | Title |  | Signature |  | Date (MM/DD/YY)
CM/REI
| Print Name | Title |  | Signature |  | Date (MM/DD/YY)
DDC PM/EIC
| Print Name | Title |  | Signature |  | Date (MM/DD/YY)

## Deduction Report
Deduction Report
0 |  |  | 0 |  |  | 0 |  | 0
Project ID |  |  | Contract Registration Number |  |  | Work Order Number |  | Change Order Number
0
Project Address
0 |  |  | 0 |  |  | 0 |  | 0 | 0
Payment Number |  |  | Project Number |  |  | Payment Period From |  | Payment Period To | Submission Date
PM/EIC Deduction/Restoration Approved Report
Item Number/Budget Line | Uniformat Code | Item Description | Reason for Deduction (Include all typs of deductions-detailed below) | Temporary or Permanent Deduction? | Deduction Amount | Payment # Deduction Taken | Deduction Amount Restoration | Payment # Restoration | Deduction Remaining
[6 empty] | # |  | # | 0
[6 empty] | # |  | # | 0
[6 empty] | # |  | # | 0
[6 empty] | # |  | # | 0
[6 empty] | # |  | # | 0
[6 empty] | # |  | # | 0
[6 empty] | # |  | # | 0
[6 empty] | # |  | # | 0
[6 empty] | # |  | # | 0
[6 empty] | # |  | # | 0
[6 empty] | # |  | # | 0
[6 empty] | # |  | # | 0
[6 empty] | # |  | # | 0
[6 empty] | # |  | # | 0
[6 empty] | # |  | # | 0
[8 empty] | Total | 0
Prepard by CM/REI
|  | Print Name | Title |  |  | Signature |  | Date (MM/DD/YY)
Checked by DDC PM/EIC
|  | Print Name | Title |  |  | Signature |  | Date (MM/DD/YY)

## 125% Item Justification
125% Item Justification Report for Overruns
0 |  | 0 | [7 empty] | 0 |  |  |  | 0
Project ID |  | Contract Registration Number | [7 empty] | Work Order Number |  |  |  | Change Order Number
0
Project Address
0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  |  | 0
Payment Number |  | Project Number |  |  |  |  | Payment Period From |  |  | Payment Period To |  |  |  | Submission Date
Item Number/Budget Line | Item Description | Bid-Line | Unit | Bid Quantity | Quantity-to-Date |  | Estimated Final |  | Price Bid vs. Eng. Estimate |  |  | Average Price Next 2 Bidders | Cost of Not Renegotiating (See Note 1) | Accepted Price (See Note 3) | Reason Code (See Note 2) | Contractor’s Initials | Comments/Reasons for Overrun
[5 empty] | Amount | % of Bid Qty | Amount | % of Bid Qty | Eng. Est Price | Bid Price | Bid as % EE
0
0
0
0
0
0
0
0
0
0
Prepard by CM/REI
| Print Name |  |  | Title |  |  | Signature |  |  |  | Date (MM/DD/YY)
Checked by DDC PM/EIC
| Print Name |  |  | Title |  |  | Signature |  |  |  | Date (MM/DD/YY)
Accepted by Contractor
| Print Name |  |  | Title |  |  | Signature |  |  |  | Date (MM/DD/YY)
Notes: | 1. If Bid is = or < Engineer’s Estimate, Bid Price is acceptable. If not, Cost of Not Renegotiating = [ (Estimated Final Quantity - (125% x Bid Quantity)) x (Bid Price - Engineer’s Estimated Price) ] If <= 0, then Bid Price is the Accepted Price.
2.Reason Codes (select one): a) <=EE: Less than or equal to Engineer’s Estimate; b) <AVG2: Less than the Average of the Next Two Bidders; c) INC: Incidental Cost (defined as Overrun Value <= $2000 AND Bid Price < 120% of EE Price); d) T&M: based on T&M. Not withstanding the arithmetic that may generate any of the above reason codes, the acceptance of any bid and/or renegotiated price must be reasonable in the judgment of the RE and the EIC.
3.Contractor’s Initials and Signature at Bottom Required if any Accepted Price is less than the Bid Price. An Accepted Price is either a Renegotiated Unit Price or the Accepted Original Unit Bid Price.
*** If Contractor and Agency cannot agree on an Accepted Price, Contractor agrees to perform the Additional Work on Time and Material basis pursuant to Article 26 but in no event at a price higher than the Bid Price. In this case, enter “T&M” into the Accepted Price Column for that Item. Payment will be made pursuant to Article 26 of the Agreement.