## Slide 1
HWMWTCB7 – Reconstruction of Trinity Place
NTP: September 18, 2023
Original Contract Amount: $18,903,881.37
Current Contract Amount: $18,903,881.37
Supervision : NV5
Contractor: MFM Contracting Corp
Projected Completion Date: 09/27/29
% of Work Completed: 33%
Original Completion Date: 9/16/27
% of Time Elapsed: 60.62 %

## Slide 2
Projected Completion Date: 09/27/29
% of Work Completed: 33%
HWMWTCB7 – Reconstruction of Trinity Place
Traffic signals & Streetlights
Installation of New 9” Concrete Road Base with 3” Asphalt
Replace 150 L.F. of 15” Combined sewers
ConEd and ECS Private upgrade Work under Joint Bid
Scope of Work:
Four (4) Blocks Full Roadway Reconstruction
New Granite Curbs and Sidewalks
ADA Compliant Ramps
Catch Basins
Water main upgrade (added scope)
Steam main upgrade (added scope)
Wayfinding Sign, leaning bars and benches

## Slide 3
Projected Completion Date: 09/27/29
% of Work Completed: 33%
HWMWTCB7 – Reconstruction of Trinity Place (work completed)
Trinity Pl between Morris St and Edgar St
New 20” ductile Iron watermain
16”Steam main repair

## Slide 4
Projected Completion Date: 01/17/29
% of Work Completed: 31%
HWMWTCB7 – Reconstruction of Trinity Place
MPT Set up:
Morris Street between Broadway & Trinity Place
Full Roadway closure, 24/7
Both sidewalks accessible 24/7

## Slide 5
Projected Completion Date: 09/17/29
% of Work Completed: 33%
HWMWTCB7 – Reconstruction of Trinity Place
Mass excavation for ConEd utilities Upgrade at Morris Street & Trinity Place
New electric steel conduits on Morris Street

## Slide 6
Projected Completion Date: 09/27/29
% of Work Completed: 33%
HWMWTCB7 – Reconstruction of Trinity Place
Rector Street Closure for ConEd & ECS Utilities Upgrade
Rector St. between Trinity Pl & Broadway
Full Roadway closure, 24/7
South sidewalk open 24/7
Access for businesses maintained
at all times.

## Slide 7
Projected Completion Date: 09/27/29
% of Work Completed: 33%
HWMWTCB7 – Reconstruction of Trinity Place
Damaged sewer manhole to be replaced
New 4” gas pipes
Rector Street Between and Trinity Pl & Broadway
New sewer manhole

## Slide 8
Projected Completion Date: 09/27/29
% of Work Completed: 33%
HWMWTCB7 – Reconstruction of Trinity Place
Rector Street Between and Trinity Pl & Broadway
Steam leak
Steam leak is delaying
the gas upgrade work

## Slide 9
Projected Completion Date: 09/27/29
% of Work Completed: 33%
HWMWTCB7 – Reconstruction of Trinity Place
Utilities relocation for catch basin & Hydrant installation
Trinity Pl between Exchange Alley & Rector St
MPT Set Up at Exchange Alley &Trinity Pl
Utilities Relocation prior to new catch basin and
hydrant installation

## Slide 10
Projected Completion Date: 09/27/29
% of Work Completed: 33%
HWMWTCB7 – Reconstruction of Trinity Place
86 Trinity Place
Sewer plans

## Slide 11
Projected Completion Date: 09/27/29
% of Work Completed: 33%
HWMWTCB7 – Reconstruction of Trinity Place
86 Trinity Place
Sewer Trench in front
of 86 Trinity Place

## Slide 12
Projected Completion Date: 09/27/29
% of Work Completed: 33%
HWMWTCB7 – Reconstruction of Trinity Place
Design of modified scaffolding

## Slide 13
Projected Completion Date: 09/27/29
% of Work Completed: 33%
HWMWTCB7 – Reconstruction of Trinity Place
86 Trinity Place
New scaffolding looking north
(Incomplete)
Sheeting design

## Slide 14
Thank You!