## SubmissionChecklist
Submission Checklist: Cover sheet for Estimate Submittals to allow estimators to confirm that required elements of the estimate are included, and to allow for formatted DDC review of packages
Revision 16. Date August 24, 2021. This is a version controlled document. Printed copies are not controlled
Cost Estimate Submission Checklist
Project ID:
Project Name:
Checklist Item | Reference | Included (Y/N) | For DDC Use
Estimating Workshop Minutes of Meeting 1
Construction Work Cost Summary Worksheet
Detailed Worksheets
Hard Cost Detail Worksheet (Level 1)
Hard Cost Detail Worksheet (Level 2)
Hard Cost Itemized General Requirements Worksheet
Bid Contingency Worksheet
Construction Contract Allowance Worksheet
Basis of Estimate
Report
Project Complexity Report
Project Type Report
1. Minutes of Meeting shall include all decisions made relevant to basis of estimate
Note:
Shaded cell is where data must be entered

## CostSummary
Construction Cost Summary: This template provides a summary of cost information in standardized format.
Project ID: |  | Construction Work Cost Summary
Line Item | Description | Calculation | Cost
A | Hard Cost Summary | see Detail Sheet | 0
B | General Conditions | Included in Hard Cost, General Requirements (Division 1)
C | Design Contingency | see Basis of Estimate
D | Overhead and Profit | see Basis of Estimate
E | Cost Escalation | see Basis of Estimate
F | Subtotal | Sum (A thru E) | 0
G | Bid Contingency | see Detail Sheet | 0
H | Construction Contract Allowance | see Detail Sheet | 0
I | Estimated Construction Cost at Award | F+G+H | 0
J | Construction Contingency | see Basis of Estimate
K | Estimated Construction Cost at Completion | I+J | 0
Note:
Shaded cell is where data must be entered

## HardCostDetailLevel1
Hard Cost Detail Level 1: This form summarizes cost estimate information by CSI Division in Master Format. This form also provides a summary of the detailed information from the Hard Cost Detail Level 2 tab.
Project ID: |  |  |  |  | Hard Cost Estimate (Level 1)
CSI Division: |  | Total cost |  |  | Total Cost
|  | Material: | Labor: | Equipment:
DIVISION 01 - GENERAL REQUIREMENTS
DIVISION 02 - EXISTING CONDITIONS |  | 0 | 0 | 0 | 0
DIVISION 03 - CONCRETE |  | 0 | 0 | 0 | 0
DIVISION 04 - MASONRY |  | 0 | 0 | 0 | 0
DIVISION 05 - METALS |  | 0 | 0 | 0 | 0
DIVISION 06 - WOOD, PLASTICS, COMPOSITES |  | 0 | 0 | 0 | 0
DIVISION 07 - THERMAL AND MOISTURE PROTECTION |  | 0 | 0 | 0 | 0
DIVISION 08 - OPENINGS |  | 0 | 0 | 0 | 0
DIVISION 09 - FINISHES |  | 0 | 0 | 0 | 0
DIVISION 10 - SPECIALTIES |  | 0 | 0 | 0 | 0
DIVISION 11 - EQUIPMENT |  | 0 | 0 | 0 | 0
DIVISION 12 - FURNISHINGS |  | 0 | 0 | 0 | 0
DIVISION 13 - SPECIAL CONSTRUCTION |  | 0 | 0 | 0 | 0
DIVISION 14 - CONVEYING EQUIPMENT |  | 0 | 0 | 0 | 0
DIVISION 21 - FIRE SUPPRESSION |  | 0 | 0 | 0 | 0
DIVISION 22 - PLUMBING |  | 0 | 0 | 0 | 0
DIVISION 23 - HEATING, VENTILATING, AND AIR CONDITIONING (HVAC) |  | 0 | 0 | 0 | 0
DIVISION 25 - INTEGRATED AUTOMATION |  | 0 | 0 | 0 | 0
DIVISION 26 - ELECTRICAL |  | 0 | 0 | 0 | 0
DIVISION 27 - COMMUNICATIONS |  | 0 | 0 | 0 | 0
DIVISION 28 - ELECTRONIC SAFETY AND SECURITY |  | 0 | 0 | 0 | 0
DIVISION 31 - EARTHWORK |  | 0 | 0 | 0 | 0
DIVISION 32 - EXTERIOR IMPROVEMENTS |  | 0 | 0 | 0 | 0
DIVISION 33 - UTILITIES |  | 0 | 0 | 0 | 0
DIVISION 34 - TRANSPORTATION |  | 0 | 0 | 0 | 0
DIVISION 35 - WATERWAY AND MARINE CONSTRUCTION |  | 0 | 0 | 0 | 0
DIVISION 40 - PROCESS INTEGRATION |  | 0 | 0 | 0 | 0
DIVISION 41 - MATERIAL PROCESSING AND HANDLING EQUIPMENT |  | 0 | 0 | 0 | 0
DIVISION 42 - PROCESS HEATING, COOLING, AND DRYING EQUIPMENT |  | 0 | 0 | 0 | 0
DIVISION 43 - PROCESS GAS AND LIQUID HANDLING, PURIFICATION AND STORAGE EQUIPMENT |  | 0 | 0 | 0 | 0
DIVISION 44 - POLLUTION AND WASTE CONTROL EQUIPMENT |  | 0 | 0 | 0 | 0
DIVISION 45 - INDUSTRY-SPECIFIC MANUFACTURING EQUIPMENT |  | 0 | 0 | 0 | 0
DIVISION 46 - WATER AND WASTEWATER EQUIPMENT |  | 0 | 0 | 0 | 0
DIVISION 48 - ELECTRICAL POWER GENERATION |  | 0 | 0 | 0 | 0
| Hard Cost: | 0 | 0 | 0 | 0
| Hard Cost Summary(Including General Requirement): |  |  |  | 0

## HardCostDetailLevel2
Hard Cost Detail Level 2: This template provides a detailed takeoff for cost estimate in CSI Master Format.
Project ID: | [19 empty] | Hard Cost Estimate (Level 2)
No. | Sub Work (*) | CSI Division: | CSI Sub Division: | RSMeans 12-digit item code: | Vendor Quote (Yes/ No): | Description: | Qty | Unit: | Material $: |  | Labor $: |  |  |  |  | Equipment $: |  | Total $: |  | DDC COMMENTS:
[9 empty] | U/Cost: | T/Cost: | U/Time: | T/Time: | Wage: | U/Cost: | T/Cost: | U/Cost: | T/Cost: | U/Cost: | T/Cost:
DIVISION 01 - GENERAL REQUIREMENTS
[6 empty] | Total from HardCostGeneralRequirements | [12 empty] | 0
|  |  | DIVISION 01 - GENERAL REQUIREMENTS |  |  | SUB TOTAL
DIVISION 02 - EXISTING CONDITIONS
copy above cell and insert copied cell above the row
|  |  | DIVISION 02 - EXISTING CONDITIONS |  |  | SUB TOTAL
DIVISION 03 - CONCRETE
copy above cell and insert copied cell above the row
|  |  | DIVISION 03 - CONCRETE |  |  | SUB TOTAL
DIVISION 04 - MASONRY
copy above cell and insert copied cell above the row
|  |  | DIVISION 04 - MASONRY |  |  | SUB TOTAL
DIVISION 05 - METALS
copy above cell and insert copied cell above the row
|  |  | DIVISION 05 - METALS |  |  | SUB TOTAL
DIVISION 06 - WOOD, PLASTICS, COMPOSITES
copy above cell and insert copied cell above the row
|  |  | DIVISION 06 - WOOD, PLASTICS, COMPOSITES |  |  | SUB TOTAL
DIVISION 07 - THERMAL AND MOISTURE PROTECTION
copy above cell and insert copied cell above the row
|  |  | DIVISION 07 - THERMAL AND MOISTURE PROTECTION |  |  | SUB TOTAL
DIVISION 08 - OPENINGS
copy above cell and insert copied cell above the row
|  |  | DIVISION 08 - OPENINGS |  |  | SUB TOTAL
DIVISION 09 - FINISHES
copy above cell and insert copied cell above the row
|  |  | DIVISION 09 - FINISHES |  |  | SUB TOTAL
DIVISION 10 - SPECIALTIES
copy above cell and insert copied cell above the row
|  |  | DIVISION 10 - SPECIALTIES |  |  | SUB TOTAL
DIVISION 11 - EQUIPMENT
copy above cell and insert copied cell above the row
|  |  | DIVISION 11 - EQUIPMENT |  |  | SUB TOTAL
DIVISION 12 - FURNISHINGS
copy above cell and insert copied cell above the row
|  |  | DIVISION 12 - FURNISHINGS |  |  | SUB TOTAL
DIVISION 13 - SPECIAL CONSTRUCTION
copy above cell and insert copied cell above the row
|  |  | DIVISION 13 - SPECIAL CONSTRUCTION |  |  | SUB TOTAL
DIVISION 14 - CONVEYING EQUIPMENT
copy above cell and insert copied cell above the row
|  |  | DIVISION 14 - CONVEYING EQUIPMENT |  |  | SUB TOTAL
DIVISION 21 - FIRE SUPPRESSION
copy above cell and insert copied cell above the row
|  |  | DIVISION 21 - FIRE SUPPRESSION |  |  | SUB TOTAL
DIVISION 22 - PLUMBING
copy above cell and insert copied cell above the row
|  |  | DIVISION 22 - PLUMBING |  |  | SUB TOTAL
DIVISION 23 - HEATING, VENTILATING, AND AIR CONDITIONING (HVAC)
copy above cell and insert copied cell above the row
|  |  | DIVISION 23 - HEATING, VENTILATING, AND AIR CONDITIONING (HVAC) |  |  | SUB TOTAL
DIVISION 25 - INTEGRATED AUTOMATION
copy above cell and insert copied cell above the row
|  |  | DIVISION 25 - INTEGRATED AUTOMATION |  |  | SUB TOTAL
DIVISION 26 - ELECTRICAL
copy above cell and insert copied cell above the row
|  |  | DIVISION 26 - ELECTRICAL |  |  | SUB TOTAL
DIVISION 27 - COMMUNICATIONS
copy above cell and insert copied cell above the row
|  |  | DIVISION 27 - COMMUNICATIONS |  |  | SUB TOTAL
DIVISION 28 - ELECTRONIC SAFETY AND SECURITY
copy above cell and insert copied cell above the row
|  |  | DIVISION 28 - ELECTRONIC SAFETY AND SECURITY |  |  | SUB TOTAL
DIVISION 31 - EARTHWORK
copy above cell and insert copied cell above the row
|  |  | DIVISION 31 - EARTHWORK |  |  | SUB TOTAL
DIVISION 32 - EXTERIOR IMPROVEMENTS
copy above cell and insert copied cell above the row
|  |  | DIVISION 32 - EXTERIOR IMPROVEMENTS |  |  | SUB TOTAL
DIVISION 33 - UTILITIES
copy above cell and insert copied cell above the row
|  |  | DIVISION 33 - UTILITIES |  |  | SUB TOTAL
DIVISION 34 - TRANSPORTATION
copy above cell and insert copied cell above the row
|  |  | DIVISION 34 - TRANSPORTATION |  |  | SUB TOTAL
DIVISION 35 - WATERWAY AND MARINE CONSTRUCTION
copy above cell and insert copied cell above the row
|  |  | DIVISION 35 - WATERWAY AND MARINE CONSTRUCTION |  |  | SUB TOTAL
DIVISION 40 - PROCESS INTEGRATION
copy above cell and insert copied cell above the row
|  |  | DIVISION 40 - PROCESS INTEGRATION |  |  | SUB TOTAL
DIVISION 41 - MATERIAL PROCESSING AND HANDLING EQUIPMENT
copy above cell and insert copied cell above the row
|  |  | DIVISION 41 - MATERIAL PROCESSING AND HANDLING EQUIPMENT |  |  | SUB TOTAL
DIVISION 42 - PROCESS HEATING, COOLING, AND DRYING EQUIPMENT
copy above cell and insert copied cell above the row
|  |  | DIVISION 42 - PROCESS HEATING, COOLING, AND DRYING EQUIPMENT |  |  | SUB TOTAL
DIVISION 43 - PROCESS GAS AND LIQUID HANDLING, PURIFICATION AND STORAGE EQUIPMENT
copy above cell and insert copied cell above the row
|  |  | DIVISION 43 - PROCESS GAS AND LIQUID HANDLING, PURIFICATION AND STORAGE EQUIPMENT |  |  | SUB TOTAL
DIVISION 44 - POLLUTION AND WASTE CONTROL EQUIPMENT
copy above cell and insert copied cell above the row
|  |  | DIVISION 44 - POLLUTION AND WASTE CONTROL EQUIPMENT |  |  | SUB TOTAL
DIVISION 45 - INDUSTRY-SPECIFIC MANUFACTURING EQUIPMENT
copy above cell and insert copied cell above the row
|  |  | DIVISION 45 - INDUSTRY-SPECIFIC MANUFACTURING EQUIPMENT |  |  | SUB TOTAL
DIVISION 46 - WATER AND WASTEWATER EQUIPMENT
copy above cell and insert copied cell above the row
|  |  | DIVISION 46 - WATER AND WASTEWATER EQUIPMENT |  |  | SUB TOTAL
DIVISION 48 - ELECTRICAL POWER GENERATION
copy above cell and insert copied cell above the row
|  |  | DIVISION 48 - ELECTRICAL POWER GENERATION |  |  | SUB TOTAL
[6 empty] | Hard Cost: |  |  |  | 0 |  |  |  |  | 0 |  | 0 |  | 0
[6 empty] | Hard Cost Summary(Including General Requirement): | [12 empty] | 0
Note:
1. Bidders' total material,labor, and equipment costs are fully-loaded with markups
2. Quanity includes expected material wastage
3. (*) Identify possible Sub Contract Work items
4. Shaded cell is where data must be entered

## HardCostGeneralRequirements
Hard Cost General Requirements: This is a itemized approach for estimating general requirements. Add cost to applicable items. Ignore items not applicable. Add other items, if needed.
Project ID: | [7 empty] | Division 1 General Requirements
(include all General Conditions)
Item# |  |  | Description | Qty | Unit | Unit Cost | Total Cost | DDC COMMENTS:
1 | BOND | [5 empty] | 0
| 1.1 | Performance Bond
| 1.2 | Payment Bond
2 | INSURANCE | [5 empty] | 0
| 2.1 | Liability
| 2.2 | Disability
| 2.3 | Builders Risk
| 2.4 | Auto Liability
| 2.5 | Asbestos Liability
| 2.6 | Railroad or other agency protection
3 | CONSTRUCTION MANAGEMENT (by CONTRACTOR) | [5 empty] | 0
| 3.1 | Supervision / Project Coordination |  |  |  |  | 0
|  | 3.101 | Project Executive
|  | 3.102 | Project Manager
|  | 3.103 | Assistant Project Manager
|  | 3.104 | Project Accountant
|  | 3.105 | Project Administration
|  | 3.106 | Project Superintendent
|  | 3.107 | Project Superintendent- MEP
|  | 3.108 | Assistant Super
|  | 3.109 | Office Engineer
|  | 3.110 | Assistant Project Engineer
|  | 3.111 | Scheduler
|  | 3.112 | QA/QC Engineer
|  | 3.113 | Shop Stewards-15 Days per Work Month
Numbering item when Insert a row above
| 3.2 | Safety Personnel |  |  |  |  | 0
|  | 3.201 | Licensed Site Safety Manager- Either mentioned in specifications or DOB Requirements based on height of the building more than 6 floors ht.
|  | 3.202 | Site Safety Manager- 40 hrs. Trained
|  | 3.203 | Fire watch
|  | 3.204 | Security - 24/7
Numbering item when Insert a row above
| 3.3 | Maintenance & Protection of Traffic |  |  |  |  | 0
|  | 3.301 | Traffic Control - Flagger- During material Delivery and Disposal
Numbering item when Insert a row above
4 | TEMPORARY FACILITIES AND CONTROLS | [5 empty] | 0
| 4.1 | Temporary Utilities |  |  |  |  | 0
|  | 4.1.01 | Temporary Electricity
|  | 4.1.02 | Temporary Fuel Oil
|  | 4.1.03 | Temporary Heating, Cooling, And Ventilating
|  | 4.1.04 | Temporary Lighting
|  | 4.1.05 | Temporary Telephone
|  | 4.1.06 | Temporary Water
|  | 4.1.07 | Temporary Construction or silt fences'
Numbering item when Insert a row above
| 4.2 | Construction Facilities |  |  |  |  | 0
|  | 4.201 | (GC) Trailer Office & Equipment
|  | 4.202 | (CM) Trailer Office & Equipment
|  | 4.203 | Office Supply
|  | 4.204 | Phone / Fax / Internet
|  | 4.205 | Electric Hookup & Usage
|  | 4.206 | Water Hookup & Usage
|  | 4.207 | Office Drinking Water
|  | 4.208 | Toilets/Sanitary Service
|  | 4.209 | Janitorial Service
|  | 4.210 | Heat / Winter Protection
|  | 4.211 | Enclosure
|  | 4.212 | Fire Extinguishers
|  | 4.213 | Arrange pick up for tools and equipment to deliver at Jobsite
|  | 4.214 | Staging area - Set Up, Maintain and Remove (e.g. 25' x 25' with 8 ht. chain-link fence, double gate, lock and Trailer)
Numbering item when Insert a row above
| 4.3 | Temporary Construction |  |  |  |  | 0
|  | 4.301 | Temporary Bridges
|  | 4.302 | Temporary Decking
|  | 4.303 | Temporary Ramps
Numbering item when Insert a row above
| 4.4 | Vehicular Access And Parking |  |  |  |  | 0
|  | 4.401 | Access Roads
|  | 4.402 | Parking Areas
|  | 4.403 | Temporary Roads
Numbering item when Insert a row above
| 4.5 | Construction Aids |  |  |  |  | 0
|  | 4.501 | Sidewalk sheds- Drawings, Permits, Setup, install and dismantle
|  | 4.502 | Sidewalk sheds- Rental after 3 months of installation
|  | 4.503 | Chute - Rental, Installation and removal
|  | 4.504 | Hoists - Rental, Installation and removal
|  | 4.505 | Tower Crane
|  | 4.506 | Elevators
|  | 4.507 | Temporary scaffolds and platforms Hoists-Setup and remove
|  | 4.508 | Temporary scaffolds and platforms Hoists- Rental after 3 months of installation
|  | 4.509 | Floor Protection - Temporary scaffolds and platforms, Hoists Setup and remove
|  | 4.510 | Dewatering
Numbering item when Insert a row above
| 4.6 | Temporary Barriers And Enclosures |  |  |  |  | 0
|  | 4.601 | Barricades
|  | 4.602 | Dust Barriers
|  | 4.603 | Fences
|  | 4.604 | Pollution Control
|  | 4.605 | Protective Walkways
|  | 4.606 | Security Measures
|  | 4.607 | Tree And Plant Protection
|  | 4.608 | Protection of adjacent work area including Properties, utilities or equipment etc.
Numbering item when Insert a row above
| 4.7 | Temporary Controls |  |  |  |  | 0
|  | 4.701 | Erosion And Sediment Control
|  | 4.702 | Pest Control
|  | 4.703 | Rodent Control
Numbering item when Insert a row above
| 4.8 | Project Sign |  |  |  |  | 0
|  | 4.801 | Project Main sign
|  | 4.802 | Project Specific Identification
Numbering item when Insert a row above
| 4.9 | Phasing |  |  |  |  | 0
|  | 4.901 | Project Phasing
Numbering item when Insert a row above
| 4.10 | Swing Space |  |  |  |  | 0
|  | 4.10.01 | Project Swing Space
Numbering item when Insert a row above
5 | PROJECT START-UP | [5 empty] | 0
| 5.1 | Permits / Fees |  |  |  |  | 0
|  | 5.101 | DEP, DOT, DOB Permits
|  | 5.102 | Expediter Fees
|  | 5.103 | Scaffold / Rigger Licenses
Numbering item when Insert a row above
| 5.2 | SURVEYING |  |  |  |  | 0
|  | 5.201 | Building Layout Survey
|  | 5.202 | Foundation Survey
|  | 5.203 | Geotechnical requirements
|  | 5.204 | Steel Survey
|  | 5.205 | Final Survey
Numbering item when Insert a row above
| 5.3 | Facility Decommissioning |  |  |  |  | 0
|  | 5.301 | Decommissioning Systems and Equipment
|  | 5.302 | Facility Demolition and Removal
|  | 5.303 | Protection of Deactivated Facilities
Numbering item when Insert a row above
6 | PROJECT EXECUTION | [5 empty] | 0
| 6.1 | Documentation & Records |  |  |  |  | 0
|  | 6.101 | Construction Drawings Blue Prints
|  | 6.102 | Pre construction Photographs
|  | 6.103 | Progressive Photographs
|  | 6.104 | Baseline Schedule
|  | 6.105 | CPM Scheduling- Monthly Updates after Baseline Approval
|  | 6.106 | BIM Implementation
|  | 6.107 | LEED related Reports
Numbering item when Insert a row above
| 6.2 | Shop Drawings / Submittals |  |  |  |  | 0
|  | 6.201 | Division 02 Sitework
|  | 6.202 | Division 03 Concrete
|  | 6.203 | Division 04 Masonry
|  | 6.204 | Division 05 Metals
|  | 6.205 | Division 06 Wood & Plastic
|  | 6.206 | Division 07 Thermal & Moisture Protection
|  | 6.207 | Division 08 Doors & Windows
|  | 6.208 | Division 09 Finishes
|  | 6.209 | Division 10 Equipment
|  | 6.210 | Division 11 Furnishings
|  | 6.211 | Division 14 Conveying System
|  | 6.212 | Division 21 Fire Suppression
|  | 6.213 | Division 22 Plumbing
|  | 6.214 | Division 23 HVAC
|  | 6.215 | Division 26 Electrical
Numbering item when Insert a row above
| 6.3 | Safety |  |  |  |  | 0
|  | 6.301 | Cost of site Safety Plans
|  | 6.301 | Cost of Safety meetings ( 1 hr. per week)- 1% of labor hours
|  | 6.301 | PPE or medical monitoring for “regular” workers (e.g., due to exposure to lead dust, silica dust exposure, etc.).
|  | 6.301 | Noise abatement
|  | 6.301 | Vibration monitoring (coordinate with Division 31)
Numbering item when Insert a row above
| 6.4 | Quality Assurance |  |  |  |  | 0
|  | 6.401 | Quality Plan
|  | 6.402 | Mockups
|  | 6.403 | Inspection
|  | 6.404 | Testing
Numbering item when Insert a row above
| 6.5 | Cleaning and Waste Management |  |  |  |  | 0
|  | 6.501 | Waste Management (Including LEED requirements)
|  | 6.502 | Dumpsters and Trash removals
|  | 6.503 | Snow Removal
|  | 6.504 | Daily Cleaning
|  | 6.505 | General Cleanup (Office/Trailer)
|  | 6.506 | Site Cleanup
|  | 6.507 | Yard / offsite maintenance
Numbering item when Insert a row above
| 6.6 | Project Logistic |  |  |  |  | 0
|  | 6.601 | Tolls
|  | 6.602 | Parking
|  | 6.603 | Delivery
Numbering item when Insert a row above
7 | COMMISSIONING AND CLOSEOUT (by CONTRACTOR) | [5 empty] | 0
| 7.1 | Equipment Startup |  |  |  |  | 0
|  | 7.101 | Equipment Testing
|  | 7.102 | Equipment Startup
Numbering item when Insert a row above
| 7.2 | Commissioning |  |  |  |  | 0
|  | 7.201 | Commissioning
|  | 7.202 | Testing, Adjusting and Balancing
|  | 7.203 | LEED Commissioning
Numbering item when Insert a row above
| 7.3 | Closeout |  |  |  |  | 0
|  | 7.301 | Punchlist
|  | 7.302 | As-Builts / Closeout Documents
|  | 7.303 | O&M Manuals and Presentation
|  | 7.304 | Warranty
|  | 7.305 | Final Cleaning
Numbering item when Insert a row above
| 7.4 | Demobilization |  |  |  |  | 0
|  | 7.401 | Demobilization
Numbering item when Insert a row above
|  |  | Total: |  |  |  | 0
Special Notes:
1 | Labor Cost shall account for productivity losses related to project field conditions, phasing requirements in landmark or historical properties, workers compensation cost, payroll taxes and PLA requirements.
2 | Asbestos abatement work is not part of Division 1. Asbestos abatement work is part of Division 2 which shall include Asbestos work plan, DOI Notification, DEP Notification, All abatement work, Removal and Disposal of HAZMAT.
3 | Shaded cell is where data must be entered, which items are applicable to the contract documents.

## BidContingency
Hard Cost Bid Contingency: This is a formatted approach for estimating the impact of contractor’s bids. The total cost from this spreadsheet is incoporated into “Construction Cost Summary” tab.
Note: Use estimator judgment if this is required. Adjust or add other items if needed.
Project ID: |  |  |  | Bid Contingency
Item# | Description | Total Cost | Justification | DDC COMMENTS:
1 | Bid Contingency (Risk)
Premium Time
Unforeseen delays and weather conditions
MWBE Contractor purchasing
Buy America
One year warranty Inspection and Repair
Insert row above
| Total Bid Contingency: | 0
Note:
Shaded cell is where data must be entered

## ContractAllowance
Construction Contract Allowance: This form lists any allowance Listing of any allowance bidders are required to add to their bids. Two categories can be considered: allowances for areas of work where definitive cost information is not available at time of bid (e.g., possible fees from Con Edison or NYC Parks), and allowances for costs likely to occur from differing site conditions, (e.g., actual physical condition materially different from the scope definition or an unknown condition that are normally encountered.)
Project ID: |  |  |  | Construction Contract Allowance
Item # | Description | Total Cost | Justification | DDC COMMENTS:
copy above cell and insert copied cell above the row
| Total: | 0
Note:
Shaded cell is where data must be entered

## BasisOfEstimate
BOE: Estimators, use this template to develop the Basis of Estimate (BOE).
Project ID: |  |  | BOE: Basis of Estimate
PROJECT NAME:
DDC PROJECT MANAGER NAME:
ANTICIPATED CONSTRUCTION START DATE:
ANTICIPATED CONSTRUCTION COMPLECTION DATE:
NAME OF THE DESIGN CONSULTANT SERVICES:
NAME OF THE CONSTRUCTION MANAGEMENT SERVICES:
NAME OF THE DESIGN BUILD CONSULTANT:
NAME OF THE COST ESTIMATING COMPANY:
CONSULTANT COST ESTIMATE SUBMISSION DATE:
PHASE OF COST ESTIMATE SUBMISSION:
DDC REVIEW DATE:
SECTION | Justification |  | DDC Comments | Guideline (All content below may not be necessary for some projects, but a complete BOE should include as much applicable information as possible.)
1 Purpose
Write a brief description of the project that includes the project type, location, and overall timing.
2 Scope
The DDC Project Manager (PM) provides this formal project scope description. A semi-detailed description of the project for each major segment should be provided, identifying any major pieces of equipment or components, and the primary trades involved in the project.
3 Methodology
The methodology includes documentation of approved workbreakdown structure, cost resources, historical data, project benchmarking, and man-hours used to prepare the estimate.
4 Estimate Classification
Define the AACE Estimate Classification along with the reasons or justification used in selection of the estimate classification.
5 Design Basis
NYC DDC standards will typically specify the technical and project information required for the classification of the estimate being prepared. The estimator will identify the types and status of engineering and design deliverables that were provided to prepare the estimate. This includes any design basis assumptions, as well as an assessment of the level of scope definition and the relationship to the published deliverable scope. If any element of the design does not meet DD-level specifications, the estimator should indicate this on the BOE. Design Basis should also include relevant information from design gap analysis.
6 Planning Basis
Provide a rough schedule outline including: a. Work time assumptions, such as hours per day, days per week, shifts per day, and overtime pay requirements b. Building occupancy expectations, including whether the building will be vacated during renovation or remain in operation c. Overall project schedule and key milestones (Construction Start and End Dates) d. Assumptions regarding constructability, modularization, or use of specialized construction equipment. e. Restrictions on mobilization that could delay project start f. Risks to productivity estimates that might increase durations
7 Cost Basis
Describe the methods and sources used for determining all material, labor and subcontract pricing. Identify the following: a. Pricing sources for all major equipment, such as vendor quotes and historical data b. Bulk material and commodity pricing sources, including any discount strategies c. The pricing source for all labor hours, and all labor productivity adjustments. Provide appropriate detail if productivities vary by trade and/or location within the project. d. All wage rates used, including crew/craft rates, craft mix, and other factors. Identify all items included in all-in rates, if used. Verify use of appropriate NYC union rates. e. Pricing source and methodology for shipping/freight, taxes, and duties f. Confirm that subcontractor indirects cost are included in the hard cost. That includes subcontractor markups for shop drawings, submittals, operations and maintenance manuals, and occupant training. g. Describe the methods and sources used for determining all indirect costs and markup. h. Confirm that majority of the work will be subcontracted.
8 Overhead and Profit
Describe the methods and sources used for determining bidder's overhead and profit. Document your analysis of market conditions and how it affected estimated profit.
9 Escalation
Identify escalation percentage used and the number of years is applied to. Identify any factors leading to the identified escalation rate.
10 Allowances
Describe any allowances that will be established for the bid documents, along with a description of the basis of the value established for each allowance.
11 Assumptions
The design consultant should provide information on assumptions that should be used by both the design consultant’s estimator and by the CM’s estimator. The BOE should provide the information from the design consultant, along with amplifying or conflicting information developed by the estimator, such as whether an adequate labor supply is available, adequate funding is available, etc. All assumptions should be documented, regardless of the anticipated impact at the time of estimate preparation.
12 Exclusions
Provide a list of the work/materials that are not included in the cost estimate, but that are required to make a complete and usable facility. Use the information provided by the design consultant, along with any other additional exclusions assumed by the estimator. Examples may include asbestos abatement, removal of hazardous wastes, land acquisition, taxes, financing costs, etc.
13 Exceptions
Provide a listing of all anomalies or variances to the estimator’s organizational standards for estimating.
14 Risks and Opportunities
Identify areas of the estimate containing significant risk or opportunity. Describe a formal risk analysis study that has been prepared (e.g. methodology or technique). The risk analysis report should be provided as an attachment to the BOE.
15 Contingencies
Contingencies are cost elements used to cover uncertainty and variability, and unforeseeable elements of cost within the defined project scope. Break down contingencies into Design Contingency, Construction Contingency, and Bid Contingency. The amount of contingency should be identified, as well as the method used to determine the contingency amount. If risk analysis techniques were used in estimating the contingency amount, identify the associated confidence level. Contingency excludes changes in project scope and unforeseen major events (such as earthquakes, prolonged labor strikes, etc.).
16 Reconciliation
Provide an overview of the major differences between the current estimate and the last published estimate prepared for this project that resulted from the reconciliation effort for the last submission. Explain any differences as well as the cumulative impact to the total budget.
17 Benchmarking
Document any comparisons of overall estimate metrics, ratios, and factors with similar projects, historical data, and industry data.
18 Estimate Quality Assurance
Identify all estimate reviews that have taken place to date, and any additional reviews that are proposed.
19 Estimating Team
| COST ESTIMATOR (GC) NAME: | Email: |  | Identify all members of the estimating team, including roles and responsibilities.
| COST ESTIMATOR (MECHANICAL) NAME: | Email:
| COST ESTIMATOR (PLUMBING) NAME: | Email:
| COST ESTIMATOR (ELECTRICAL) NAME: | Email:
20 Design Consulant Team
| PROJECT MANAGER (ARCHITECTURAL): | Email: |  | Identify all members of the Design Consultant team, including roles and responsibilities.
| ENGINEER (STRUCTURAL): | Email:
| ENGINEER (MECH & PLUMBING): | Email:
| ENGINEER (ELECTRICAL): | Email:
Note:
Shaded cell is where data must be entered
Note on E7: mm/dd/yyyy
Note on E8: mm/dd/yyyy
Note on E13: mm/dd/yyyy
Note on E15: mm/dd/yyyy

## ProjectTypeReport
Project Type Report: This is the standard format for collecting estimate information by project type. This allows DDC to improve internal tools for parametic estimating.
Project ID: |  |  |  |  | Project Type Report
Estimator prepares the Project Type Report based on data abstracted from the detailed cost estimate. Estimator shall determine applicable project type. A project can either be new construction, major rehabiliaton/renovation, or a combination of systems such as facade, fire alarm upgrade and/or replacement. A new constrution or major rehabiliation/renovation projects do not need to be broken further into systems. For applicable project types, estimator determines total quantities and total cost to allow for unit cost calculation.
ITEM# | PROJECT TYPES |  | UNITS OF MEASUREMENTS | QTY. | COST
(A) | NEW CONSTRUCTION:
| Demolition of existing building; design and construction of a new facility. |  | SF
(B) | MAJOR REHABILITATION/ RENOVATION:
| Provide rehabilitation of facility which can includes architectural, mechanical, electrical, plumbing, structural and landscaping. |  | SF
(C) | EXTERIOR RENOVATION | Façade:
|  | Façade restoration, which includes masonry pointing and replacement of deteriorated units and restoration of architectural metal elements. May include a fire escape upgrade and various historical restorations. | SF
Roof Replacement:
|  | Remove, and replace the existing roofing system, restorations to the parapet wall, Replacement of roof drains, Repair and /or replacement of existing dunnage supports for HVAC equipment’s. Associated water damage repair. | SF
Window Replacement:
|  | Replacement of exterior windows and related associated work | # of Windows
(D) | INTERIOR RENOVATION | Interior Fit-out:
|  | Modification of interior work includes common areas, bathroom & kitchen/ pantry to incorporate ADA compliance, ceiling, interior doors, and painting. | SF
Fire Alarm Upgrade and/or Replacement:
|  | Installation of New fire Alarm system with control panel, remote annunciation, peripheral devices. | SF
Fire Sprinkler Upgrade and/or Replacement:
|  | Installation of new wet /Dry sprinkler system. Upgrade/Install Stand pipe system. | SF
Electrical Upgrade and/or Replacement:
|  | Provide an energy efficient upgrade for the facility. New LED lighting to be provided as well as the associated lighting controls. New retrofit kits are to be mounted within the existing recessed ceiling light fixture housings. Each retrofit kit covers the existing ceiling aperture and includes integral LEDs, diffuser lens, driver, and an occupancy/motion sensor. May include Replacement of distribution panels, feeders etc. | SF
HVAC Upgrade and/or Replacement:
|  | Provide cooling units based on area and occupancy factor. Provide heating units measured in BTU based on occupancy factor. HVAC Replacement and Installation of BMS (Building Management System), Provide a complete electrical design system required for the Heating Ventilating Unit replacement, and the replacement of the associated exhaust fans which include power requirements, heat and smoke detectors and carbon monoxide and electrical demolition and removals of existing equipment as required. | Tons/MBH/BTU
Conveyance Upgrade and/or Replacement:
|  | Remove and replace the existing elevator system. | #of Stops
Boiler Upgrade and/or Replacement:
|  | Remove and dispose Existing Boiler which includes Provide a new gas-fired, hot water boiler, install new circulating pumps expansion tank, air separator and all other heating system accessory equipment required to be connected to the existing supply and return piping and terminal equipment distribution systems and associated auxiliary equipment, Replacement of Chimney liner and control system. | MBH
Plumbing Upgrade and/or Replacement:
|  | Replacement of bathroom and kitchen fixtures, Hot/Cold Water piping, sanitary vent and waste piping. | SF
(E) | MISC. | Site Work:
|  | Associated landscape architecture such as design and layout of permeable and non-permeable pavement system, site engineering of drainage improvements, Installation of pedestrian yard lightings for safety and security measures, design and installation of irrigation system. | SF
Structural Work – Steel
|  | Assembly of steel components into a frame on site. This involves lifting and placing components into position, then connecting them together by bolting and/ or site welding. | Tons
Structural Work – Concrete
|  | Used for new/repair of existing foundations, building floors, slab on grade, exterior concrete site work, and custom machine base foundations and pits. | CY
Fuel Tank:
|  | Environmental remediation of existing fuel oil storage tank, Removal of containerized chemicals, environmental waste transportation and disposition and related work. Furnish and install new fuel tank with all associate piping, equipment and controls. | Gal
Resiliency/ Elevated System or Utilities:
|  | Design and install a new waste water and Strom water conveyance system. | SF
Generators:
|  | Removal and replacement of generators and associated accessories. | KW
Others:
|  | Special construction work not described any of above category. | SF, LF, EA, Acre, etc.
|  |  |  | Grand Total | 0
Note:
Shaded cell is where data must be entered

## ProjectComplexity
Project Complexity: Estimators, use this template to summarize project complexity factors. This form accompanies the BOE.
Project ID: | Project Complexity
Description | *Yes/No
Occupied: |  | Will the property be occupied during construction?
Building Year Built: |  | What year was the building built?
Adverse Subsurface Condition: |  | Is there an adverse subsurface condition (e.g. rock, high groundwater table, contaminated soil)?
Phased: |  | Will construction be sequenced into multiple phases requiring move management and/or temporary relocations? This may include a construction phase plan (CPP) to record arrangements for managing significant health and safety risks associated with the construction of the project and is the basis for communicating those arrangements to those involved in the construction phase. It outlines the health and safety arrangements and site rules considering any industrial activities taking place on site, and, where applicable, must include specific measures concerning any work involving the risks
Swing Space: |  | Is a swing space required? DDC and Sponsor Agency coordinate at project initiation to define whether swing space is required, and whether the project scope and budget will include work to provide swing space. The impact will vary based on the complexity or if leasing or improvements are required. Impacts will be alleviated if a separate team develops this concurrent to the main design package.
Site Density & Logistics: |  | Will workers need to be bussed to the site, will just-in-time delivery be required due to lack of storage/laydown areas, etc.?
LEED: |  | Is the job subject to any LEED certification (Leadership in Energy and Environmental Design)? (Choose Level) Levels of Certification: 0) Not Required 1) Silver 2) Gold 3) Platinum
Landmark: |  | Is the job subject to Landmark Preservation requirement? The New York City Landmarks Preservation Commission defines a landmark as a building, property or object that has a special character or special historical or aesthetic interest or value as part of the development, heritage, or cultural characteristics of the city, state, or nation.
Leased |  | Is this property leased? Leased means written or implied contract by which an owner (the lessor) of a specific asset (such as a parcel of land, building, equipment, or machinery) grants a second party (the lessee) the right to its exclusive possession and use for a specific period and under specified conditions
Sitework: |  | Does the job involve sitework? Sitework is part of a construction project that is not part of a building or house's physical structure. This usually includes grading, excavation, construction and installation of septic tanks and filtration systems, driveways and other utilities
Wicks Law: |  | Is Wicks Law applicable for this job? The Wicks Law requires that government agencies in New York State (except some state and local authorities, which are exempt) directly hire separate contractors for general construction, plumbing, electrical work, and heating and ventilation
PLA: |  | Is this a PLA job? Project Labor Agreement (PLA), also known as a Community Workforce Agreement, is a pre-hire collective bargaining agreement with one or more labor organizations that establishes the terms and conditions of employment for a specific construction project
Lead/Asbestos: |  | Does the job involve lead/asbestos abatement? The term ' asbestos abatement' is used to refer to procedures used to control fiber release from asbestos-containing materials in a building, or to remove them entirely, including removal, encapsulation, repair, enclosure, encasement, and operations and maintenance programs. Lead abatement is an activity to reduce levels of lead, particularly in the home environment, generally to permanently eliminate lead-based paint hazards, in order to reduce or eliminate incidents of lead poisoning
HAZMAT: |  | Does the project involve substances in quantities or forms that may pose a reasonable risk to health, property, or the environment? HAZMAT (Hazardous materials) include such substances as toxic chemicals, fuels, nuclear waste products, and biological, chemical, and radiological agents.
Unique Safety Requirements: |  | Are there any Unique Safety Requirements (e.g. work in lead-contaminated environment, impact of new OSHA Silica rules, sidewalk bridging/scaffolding, requirement for major crane event(s), etc.)? Consider known issues at time of project initiation.
ULURP/EAS: |  | Is the land use subject to the ULURP review? ULURP is the Uniform Land Use Review Procedure is a standardized procedure whereby applications affecting the land use of the city are publicly reviewed. An Environmental Assessment Statement (EAS) is intended to assist in identifying the potential impacts a project may have on the environment and whether such impacts are significant and adverse.
Demolition: |  | Does the job involve deconstruction, which involves taking a building apart while carefully preserving valuable elements for reuse purposes? or Does it require science and engineering in safely and efficiently tearing down of the building and other man-made structures?
PQL: |  | Does the job involve only Pre-Qualified List of contractors? (List maintained by ACCO used for professional contracts procurements)
* Select appropriate One in each line item (Yes/No) except cell 8 and 13.Refer the each shaded cell comments
Note:
Shaded cell is where data must be entered

## Defintitions
Term | Definition
Design contingency | Design contingency is a budget used during the design phase of the project to cover the cost of design parameters and requirements that become known as the design develops. Design contingency depends directly on the level of project definition and design maturity. The contingency amount typically starts out as 10-15% at the start of design and is reduced as the design progresses. Better-defined projects may allow lower contingency. No design contingency is carried in the project budget after design has been completed.
General Requirements | General requirements budget includes general contractors' project-specific costs that are not direct construction costs (i.e., field labor, material and equipment costs) but are associated with the specific project. It includes all general condition items typically identified in the contract (i.e. contractor’s field staff, bonds and insurance, field trailers, security fencing, photocopy, phone, office supplies, etc.) These are cost specifically called for in Division 1 of the contract that are unique to the project.
Overhead and Profit | The overhead and profit budget reflect the bidder’s cost of home office operations and profit. Overhead cost does not include overhead costs assignable directly to the project carried out and included under general requirements. Overhead and profit is variable and dependent upon market conditions.
Escalation | The cost escalation estimate accounts for an increase in the cost of equipment, material, labor, etc. over that specified in the estimate due to continuing price level changes over time and includes inflation. Escalation is typically applied to mid-point of construction based on an annual escalation rate, compounded annually. The annual escalation rate is determined by the estimator based on reference to various economics publications and requires frequent reassessment.
Bid Contingency | Bid contingency estimate accounts for the successful bidder’s risk exposure during construction not captured elsewhere. It reflects the bidder’s perception of risk associated with the project, including risk transferred to the contractor per DDC’s contract terms and conditions.
Contract Allowance | Contract Allowance estimate is an amount that bidders will be directed to include in their bids. Contract Allowance covers the cost of known but undefined contract work requirements, e.g., possible fees from Con Edison or NYC Parks. It also covers anticipated actual field condition normally encountered that is materially different from the scope definition and specific areas of work difficult to quantify at time of bid, e.g., asbestos abatement. Do not use a contract allowance for something that can be designed and documented in the bid documents. The Contract allowance is not intended for scope changes. These costs will need to be estimated by the DDC and supplied to the designer for inclusion in the bid documents . Include any expected field conditions changes not captured under contract allowance in the construction contingency.
Construction Contingency | Construction contingency estimate budgets for anticipated cost growth in a construction project after bid due to field changes and design consultant errors and omissions. This amount should also be adjusted to address the cost of unforeseen changes that were not addressed by a contract allowance.

## csi
DIVISION 00 - PROCUREMENT AND CONTRACTING REQUIREMENTS
DIVISION 01 - GENERAL REQUIREMENTS
DIVISION 02 - EXISTING CONDITIONS
DIVISION 03 - CONCRETE
DIVISION 04 - MASONRY
DIVISION 05 - METALS
DIVISION 06 - WOOD, PLASTICS, COMPOSITES
DIVISION 07 - THERMAL AND MOISTURE PROTECTION
DIVISION 08 - OPENINGS
DIVISION 09 - FINISHES
DIVISION 10 - SPECIALTIES
DIVISION 11 - EQUIPMENT
DIVISION 12 - FURNISHINGS
DIVISION 13 - SPECIAL CONSTRUCTION
DIVISION 14 - CONVEYING EQUIPMENT
DIVISION 21 - FIRE SUPPRESSION
DIVISION 22 - PLUMBING
DIVISION 23 - HEATING, VENTILATING, AND AIR CONDITIONING (HVAC)
DIVISION 25 - INTEGRATED AUTOMATION
DIVISION 26 - ELECTRICAL
DIVISION 27 - COMMUNICATIONS
DIVISION 28 - ELECTRONIC SAFETY AND SECURITY
DIVISION 31 - EARTHWORK
DIVISION 32 - EXTERIOR IMPROVEMENTS
DIVISION 33 - UTILITIES
DIVISION 34 - TRANSPORTATION
DIVISION 35 - WATERWAY AND MARINE CONSTRUCTION
DIVISION 40 - PROCESS INTEGRATION
DIVISION 41 - MATERIAL PROCESSING AND HANDLING EQUIPMENT
DIVISION 42 - PROCESS HEATING, COOLING, AND DRYING EQUIPMENT
DIVISION 43 - PROCESS GAS AND LIQUID HANDLING, PURIFICATION AND STORAGE EQUIPMENT
DIVISION 44 - POLLUTION AND WASTE CONTROL EQUIPMENT
DIVISION 45 - INDUSTRY-SPECIFIC MANUFACTURING EQUIPMENT
DIVISION 46 - WATER AND WASTEWATER EQUIPMENT
DIVISION 48 - ELECTRICAL POWER GENERATION
UNIT | ABBREVIATION
ACRE | ACRE
BAG | BAG
BCY | BANK CUBIC YARD
BF | BOARD FEET
C | HUNDRED
C FL | HUNDRED SQUARE FEET PER FLOOR
CAR | CAR
CCF | HUNDRED CUBIC FEET
CF | CUBIC FEET
CLF | HUNDRED LINEAR FEET
CRT | CATHODE RAY TUBE
CSF | HUNDRED SQUARE FEET
CWT | 100 POUNDS
CY | CUBIC YARD
DAY | DAY
DOOR | DOOR
DRUM | DRUM
EA | EACH
ECY | EMBANKMENT CUBIC YARDS
FACE | FACE
FLGH | FLIGHT
FLR | FLOOR
FXTR | FIXTURE
GAL | GALLON
HDR | HEADER
HOR | HORIZONTAL
HR | HOUR
INCH | INCH
JACK | JACK
JOB | JOB
KIP | 1000 POUNDS
KW | KILOWATT
LANE | LANE
LB | POUND
LCY | LOOSE CUBIC YARD
LEAF | LEAF
LF | LINEAR FEET
M | THOUSAND
MBF | THOUSAND BOARD FEET
MCFM | THOUSAND CUBIC FEET PER MINUTE
MILE | MILE
MLF | THOUSAND LINEAR FEET
MO | MONTH
MOVE | MOVE
MSF | THOUSAND SQUARE FEET
NAME | NAME
NOSE | NOSE
OPNG | OPENING
OTLT | OUTLETS
PAIR | PAIR
PLAN | PLAN
PNT | POINT
POOL | POOL
PR | PAIR
PRJC | PROJECT
PRSN | PERSON
QT | QUART
RISR | RISER
ROLL | ROLL
ROOM | ROOM
RSR | RISER
SCTN | SECTION
SEAT | SEAT
SET | SET
SF | SQUARE FOOT
SFCA | SQUARE FOOT CONTACT AREA
SGNL | SIGNAL
SHAD | SHADE
SHLF | SHELF
SPKR | SPEAKER
SQ | HUNDRED SQUARE FEET
STDN | STUDENT
STG | STAGING
STLL | STALL
STOP | STOP
STTN | STATION
SURF | SURFACE
SY | SQUARE YARD
SYST | SYSTEM
TN/D | TON/DAY
TON | TON
TONC | TON AC
TOTL | TOTAL
TRD | TREAD
TRSS | TRUSS
VLF | VERTICAL LINEAR FOOT
WALL | WALL
WEEK | WEEK
ACRE | ACRE
BAG | BAG
BCY | BANK CUBIC YARD
BF | BOARD FEET
C | HUNDRED
C FL | HUNDRED SQUARE FEET PER FLOOR
CAR | CAR
CCF | HUNDRED CUBIC FEET
CF | CUBIC FEET
CLF | HUNDRED LINEAR FEET
CRT | CATHODE RAY TUBE
CSF | HUNDRED SQUARE FEET
CWT | 100 POUNDS
CY | CUBIC YARD
DAY | DAY
DOOR | DOOR
DRUM | DRUM
EA | EACH
ECY | EMBANKMENT CUBIC YARDS
FACE | FACE
FLGH | FLIGHT
FLR | FLOOR
FXTR | FIXTURE
GAL | GALLON
HDR | HEADER
HOR | HORIZONTAL
HR | HOUR
INCH | INCH
JACK | JACK
JOB | JOB
KIP | 1000 POUNDS
KW | KILOWATT
LANE | LANE
LB | POUND
LCY | LOOSE CUBIC YARD
LEAF | LEAF
LF | LINEAR FEET
LS | LUMP SUM
M | THOUSAND
MBF | THOUSAND BOARD FEET
MCFM | THOUSAND CUBIC FEET PER MINUTE
MILE | MILE
MLF | THOUSAND LINEAR FEET
MO | MONTH
MOVE | MOVE
MSF | THOUSAND SQUARE FEET
NAME | NAME
NOSE | NOSE
OPNG | OPENING
OTLT | OUTLETS
PAIR | PAIR
PLAN | PLAN
PNT | POINT
POOL | POOL
PR | PAIR
PRJC | PROJECT
PRSN | PERSON
QT | QUART
RISR | RISER
ROLL | ROLL
ROOM | ROOM
RSR | RISER
SCTN | SECTION
SEAT | SEAT
SET | SET
SF | SQUARE FOOT
SFCA | SQUARE FOOT CONTACT AREA
SGNL | SIGNAL
SHAD | SHADE
SHLF | SHELF
SPKR | SPEAKER
SQ | HUNDRED SQUARE FEET
STDN | STUDENT
STG | STAGING
STLL | STALL
STOP | STOP
STTN | STATION
SURF | SURFACE
SY | SQUARE YARD
SYST | SYSTEM
TN/D | TON/DAY
TON | TON
TONC | TON AC
TOTL | TOTAL
TRD | TREAD
TRSS | TRUSS
VLF | VERTICAL LINEAR FOOT
WALL | WALL
WEEK | WEEK

## csi-sub
MasterFormat ® Numbers & Titles
2016-04-01
00 00 00 Procurement and Contracting Requirements
00 01 01 Project Title Page
00 01 03 Project Directory
00 01 05 Certifications Page
00 01 07 Seals Page
00 01 10 Table of Contents
00 01 15 List of Drawing Sheets
00 01 20 List of Schedules
00 10 00 Solicitation
00 11 00 Advertisements and Invitations
00 11 13 Advertisement for Bids
00 11 15 Advertisement for Prequalification of Bidders
00 11 16 Invitation to Bid
00 11 19 Request for Proposal
00 11 53 Request for Qualifications
00 20 00 Instructions for Procurement
00 21 00 Instructions
00 21 13 Instructions to Bidders
00 21 16 Instructions to Proposers
00 22 00 Supplementary Instructions
00 22 13 Supplementary Instructions to Bidders
00 22 16 Supplementary Instructions to Proposers
00 23 00 Procurement Definitions
00 24 00 Procurement Scopes
00 24 13 Scopes of Bids
00 24 13.13 Scopes of Bids (Multiple Contracts)
00 24 13.16 Scopes of Bids (Multiple-Prime Contract)
00 24 16 Scopes of Proposals
00 24 16.13 Scopes of Proposals (Multiple Contracts)
00 24 16.16 Scopes of Proposals (Multiple-Prime Contract)
00 25 00 Procurement Meetings
00 25 13 Pre-Bid Meetings
00 25 16 Pre-Proposal Meetings
00 26 00 Procurement Substitution Procedures
00 30 00 Available Information
00 31 00 Available Project Information
00 31 13 Preliminary Schedules
00 31 13.13 Preliminary Project Schedule
00 31 13.16 Preliminary Construction Schedule
00 31 13.23 Preliminary Project Phases
00 31 13.26 Preliminary Project Sequencing
00 31 13.33 Preliminary Project Milestones
00 31 16 Project Budget Information
00 31 19 Existing Condition Information
00 31 19.13 Movement and Vibration Information
00 31 19.16 Acoustic Information
00 31 19.19 Traffic Information
00 31 19.23 Existing Structural Information
00 31 21 Survey Information
00 31 21.13 Site Survey Information
00 31 21.16 Measured Drawing Information
00 31 21.19 Photographic Information
00 31 24 Environmental Assessment Information
00 31 24.13 Soil Contamination Report
00 31 24.23 Environmental Impact Study Report
00 31 24.26 Environmental Impact Report Evaluation
00 31 24.29 Record of Environmental Impact Decision
00 31 24.33 Environmental Impact Mitigation Report
00 31 25 Existing Material Information
00 31 25.16 Existing Concrete Information
00 31 25.19 Existing Masonry Information
00 31 25.23 Existing Metals Information
00 31 25.26 Existing Wood, Plastics, and Composites Information
00 31 25.29 Existing Thermal and Moisture Protection Information
00 31 26 Existing Hazardous Material Information
00 31 26.23 Existing Asbestos Information
00 31 26.26 Existing Lead Information
00 31 26.29 Existing Polychlorinate Biphenyl Information
00 31 26.33 Existing Mold Information
00 31 26.36 Existing Hazardous Waste Drum Information
00 31 31 Geophysical Data
00 31 31.13 Seismic Investigations Information
00 31 31.16 Gravity Investigations Information
00 31 31.19 Magnetic Investigations Information
00 31 31.23 Electromagnetic Investigations Information
00 31 31.26 Electrical Resistivity Investigations Information
00 31 31.29 Magnetotelluric Investigations Information
00 31 32 Geotechnical Data
00 31 32.13 Subsurface Drilling and Sampling Information
00 31 32.16 Material Testing Information
00 31 32.19 Exploratory Excavation Information
00 31 32.23 Geotechnical Monitoring Information
00 31 43 Permit Application
00 31 46 Permits
00 40 00 Procurement Forms and Supplements
00 41 00 Bid Forms
00 41 13 Bid Form - Stipulated Sum (Single-Prime Contract)
00 41 16 Bid Form - Stipulated Sum (Multiple-Prime Contract)
00 41 23 Bid Form - Construction Management (Single-Prime Contract)
00 41 26 Bid Form - Construction Management (Multiple-Prime Contract)
00 41 33 Bid Form - Cost-Plus-Fee (Single-Prime Contract)
00 41 36 Bid Form - Cost-Plus-Fee (Multiple-Prime Contract)
00 41 43 Bid Form - Unit Price (Single-Prime Contract)
00 41 46 Bid Form - Unit Price (Multiple-Prime Contract)
00 41 53 Bid Form - Design/Build (Single-Prime Contract)
00 41 56 Bid Form - Design/Build (Multiple-Prime Contract)
00 41 63 Bid Form - Purchase Contract
00 42 00 Proposal Forms
00 42 13 Proposal Form - Stipulated Sum (Single-Prime Contract)
00 42 16 Proposal Form - Stipulated Sum (Multiple-Prime Contract)
00 42 23 Proposal Form - Construction Management (Single-Prime Contract)
00 42 26 Proposal Form - Construction Management (Multiple-Prime Contract)
00 42 33 Proposal Form - Cost-Plus-Fee (Single-Prime Contract)
00 42 36 Proposal Form - Cost-Plus-Fee (Multiple-Prime Contract)
00 42 43 Proposal Form - Unit Price (Single-Prime Contract)
00 42 46 Proposal Form - Unit Price (Multiple-Prime Contract)
00 42 53 Proposal Form - Design/Build (Single-Prime Contract)
00 42 56 Proposal Form - Design/Build (Multiple-Prime Contract)
00 42 63 Proposal Form - Purchase Contract
00 42 73 Proposal Form - Performance Contract
00 43 00 Procurement Form Supplements
00 43 13 Bid Security Form
00 43 21 Allowance Form
00 43 22 Unit Prices Form
00 43 23 Alternates Form
00 43 25 Substitution Request Form (During Procurement)
00 43 26 Estimated Quantities Form
00 43 27 Separate Prices Break-Out Form
00 43 28 Tax Rebate Form
00 43 33 Proposed Products Form
00 43 36 Proposed Subcontractors Form
00 43 39 Minority Business Enterprise Statement of Intent Form
00 43 43 Wage Rates Form
00 43 73 Proposed Schedule of Values Form
00 43 83 Proposed Construction Schedule Form
00 43 86 Proposed Work Plan Schedule Form
00 43 93 Bid Submittal Checklist
00 45 00 Representations and Certifications
00 45 13 Bidder's Qualifications
00 45 16 Proposer's Qualifications
00 45 19 Non-Collusion Affidavit
00 45 23 Statement of Disposal Facility
00 45 26 Workers Compensation Certificate Schedule
00 45 33 Non-Segregated Facilities Affidavit
00 45 36 Equal Employment Opportunity Affidavit
00 45 39 Minority Business Enterprise Affidavit
00 45 43 Corporate Resolutions
00 45 46 Governmental Certifications
00 50 00 Contracting Forms and Supplements
00 51 00 Notice of Award
00 52 00 Agreement Forms
00 52 13 Agreement Form - Stipulated Sum (design/bid/build or design/negotiate/build)
00 52 14 Subcontract Form - Stipulated Sum (design/bid/build or design/negotiate/build)
00 52 16 Agreement Form - Cost-Plus (design/bid/build or design/negotiate/build)
00 52 17 Subcontract Form - Cost-Plus (design/bid/build or design/negotiate/build)
00 52 23 Agreement Form - Construction Manager as Agent or Advisor - Stipulated Sum
00 52 24 Subcontract Form - Construction Manager as Agent or Adviser - Stipulated Sum
00 52 26 Agreement Form - Construction Manager as Agent or Adviser - Cost-Plus
00 52 27 Subcontract Form - Construction Manager as Agent or Adviser - Cost-Plus
00 52 33 Agreement Form - Construction Manager at Risk - Stipulated Sum
00 52 34 Subcontract Form - Construction Manager at Risk - Stipulated Sum
00 52 36 Agreement Form - Construction Manager at Risk - Cost-Plus
00 52 37 Subcontract Form - Construction Manager at Risk - Cost-Plus
00 52 51 Public-Private Partnership Agreement
00 52 52 Agreement for Preliminary Services - Owner-Design/Builder
00 52 53 Agreement Form - Owner-Design/Builder - Stipulated Sum
00 52 54 Subcontract Form - Design/Build - Stipulated Sum
00 52 56 Agreement Form - Owner-Design/Builder - Cost-Plus
00 52 57 Subcontract Form - Design/Build - Cost-Plus
00 52 63 Agreement Form - Purchase - Stipulated Price
00 52 73 Agreement Form - Performance Contract
00 52 93 Multi-Party Agreement Form - Integrated Project Delivery
00 52 96 Agreement between Single-Purpose Entity and Owner - Integrated Project Delivery
00 52 97 Agreement between Single-Purpose Entity and Non-Owner - Integrated Project Delivery
00 52 98 Agreement between Single-Purpose Entity and Consultant - Integrated Project Delivery
00 54 00 Agreement Form Supplements
00 54 13 Supplementary Scope Statement
00 54 21 Allowances Schedule
00 54 22 Unit Prices Schedule
00 54 33 Digital/Electronic Data Protocol Exhibit
00 54 36 Building Information Modeling Exhibit
00 55 00 Notice to Proceed
00 60 00 Project Forms
00 61 00 Bond Forms
00 61 13 Performance and Payment Bond Form
00 61 13.13 Performance Bond Form
00 61 13.16 Payment Bond Form
00 61 16 Lien Bond Form
00 61 19 Maintenance Bond Form
00 61 23 Retainage Bond Form
00 61 26 Special Bond Form
00 62 00 Certificates and Other Forms
00 62 11 Submittal Transmittal Form
00 62 16 Certificate of Insurance Form
00 62 19 Infection Control Form
00 62 23 Construction Waste Diversion Form
00 62 33 Products Form
00 62 34 Recycled Content of Materials Form
00 62 39 Minority Business Enterprise Certification Form
00 62 73 Schedule of Values Form
00 62 76 Application for Payment Form
00 62 76.13 Sales Tax Form
00 62 76.16 Consent of Surety to Reduction of Retainage Form
00 62 79 Stored Material Form
00 62 83 Construction Schedule Form
00 62 86 Work Plan Schedule Form
00 62 89 Construction Equipment Form
00 63 00 Clarification and Modification Forms
00 63 13 Request for Interpretation Form
00 63 19 Clarification Form
00 63 25 Substitution Request Form (During Construction)
00 63 33 Supplemental Instruction Form
00 63 36 Field Order Form
00 63 43 Written Amendment Form
00 63 46 Construction Change Directive Form
00 63 49 Work Change Directive Form
00 63 53 Request for Proposal Form
00 63 54 Proposal Worksheet Summary Form
00 63 55 Proposal Worksheet Detail Form
00 63 57 Change Order Request Form
00 63 63 Change Order Form
00 65 00 Closeout Forms
00 65 13 Certificate of Compliance Form
00 65 16 Certificate of Substantial Completion Form
00 65 19 Certificate of Completion Form
00 65 19.13 Affidavit of Payment of Debts and Claims Form
00 65 19.16 Affidavit of Release of Liens Form
00 65 19.19 Consent of Surety to Final Payment Form
00 65 19.23 Acceptance Certificate Form
00 65 19.26 Final Settlement Certificate Form
00 65 36 Warranty Form
00 65 73 Statutory Declaration Form
00 70 00 Conditions of the Contract
00 71 00 Contracting Definitions
00 72 00 General Conditions
00 72 13 General Conditions - Stipulated Sum (Single-Prime Contract)
00 72 16 General Conditions - Stipulated Sum (Multiple-Prime Contract)
00 72 23 General Conditions - Construction Management (Single-Prime Contract)
00 72 26 General Conditions - Construction Management (Multiple-Prime Contract)
00 72 33 General Conditions - Cost Plus-Fee (Single-Prime Contract)
00 72 36 General Conditions - Cost-Plus-Fee (Multiple-Prime Contract)
00 72 43 General Conditions - Unit Price (Single-Prime Contract)
00 72 46 General Conditions - Unit Price (Multiple-Prime Contract)
00 72 53 General Conditions - Design/Build (Single-Prime Contract)
00 72 56 General Conditions - Design/Build (Multiple-Prime Contract)
00 72 73 General Conditions - Performance Contract
00 72 95 General Conditions - Integrated Project Delivery
00 73 00 Supplementary Conditions
00 73 16 Insurance Requirements
00 73 19 Health and Safety Requirements
00 73 23 Purchase Contracts
00 73 26 Assigned Contracts
00 73 33 Non-Segregated Facilities Requirements
00 73 36 Equal Employment Opportunity Requirements
00 73 39 Minority Business Enterprise Requirements
00 73 43 Wage Rate Requirements
00 73 46 Wage Determination Schedule
00 73 49 Labor Stabilization Agreement
00 73 53 Anti-Pollution Measures
00 73 63 Security Requirements
00 73 73 Statutory Requirements
00 73 83 Dispute Resolution
00 90 00 Revisions, Clarifications, and Modifications
00 91 00 Precontract Revisions
00 91 13 Addenda
00 91 16 Bid Revisions
00 91 19 Proposal Revisions
00 93 00 Record Clarifications and Proposals
00 93 13 Record Requests for Interpretation
00 93 19 Record Clarification Notices
00 93 53 Record Proposal Requests
00 93 54 Record Proposal Worksheet Summaries
00 93 57 Record Change Order Requests
00 94 00 Record Modifications
00 94 33 Record Minor Changes in the Work
00 94 36 Record Supplemental Instructions
00 94 39 Record Field Orders
00 94 43 Record Amendments
00 94 46 Record Construction Change Directives
00 94 49 Record Work Change Directives
00 94 63 Record Change Orders
01 00 00 General Requirements
01 10 00 Summary
01 11 00 Summary of Work
01 11 13 Work Covered by Contract Documents
01 11 16 Work by Owner
01 11 19 Purchase Contracts
01 12 00 Multiple Contract Summary
01 12 13 Summary of Contracts
01 12 16 Work Sequence
01 12 19 Contract Interface
01 14 00 Work Restrictions
01 14 13 Access to Site
01 14 16 Coordination with Occupants
01 14 19 Use of Site
01 14 33 Work in Rights-of-Way
01 18 00 Project Utility Sources
01 18 13 Utility Service Connections
01 20 00 Price and Payment Procedures
01 21 00 Allowances
01 21 13 Cash Allowances
01 21 16 Contingency Allowances
01 21 19 Testing and Inspecting Allowances
01 21 23 Installation Allowances
01 21 26 Product Allowances
01 21 29 Quantity Allowances
01 21 43 Time Allowances
01 22 00 Unit Prices
01 22 13 Unit Price Measurement
01 22 16 Unit Price Payment
01 23 00 Alternates
01 24 00 Value Analysis
01 24 13 Value Engineering
01 25 00 Substitution Procedures
01 25 13 Product Substitution Procedures
01 25 16 Execution Substitution Procedures
01 26 00 Contract Modification Procedures
01 26 13 Requests for Interpretation
01 26 19 Clarification Notices
01 26 33 Minor Changes in the Work
01 26 36 Supplemental Instructions
01 26 39 Field Orders
01 26 43 Amendments
01 26 46 Construction Change Directives
01 26 49 Work Change Directives
01 26 53 Proposal Requests
01 26 54 Proposal Worksheet Summaries
01 26 57 Change Order Requests
01 26 63 Change Orders
01 29 00 Payment Procedures
01 29 73 Schedule of Values
01 29 76 Progress Payment Procedures
01 29 83 Payment Procedures for Testing Laboratory Services
01 30 00 Administrative Requirements
01 31 00 Project Management and Coordination
01 31 13 Project Coordination
01 31 14 Facility Services Coordination
01 31 16 Multiple Contract Coordination
01 31 19 Project Meetings
01 31 19.13 Preconstruction Meetings
01 31 19.16 Site Mobilization Meetings
01 31 19.23 Progress Meetings
01 31 19.33 Preinstallation Meetings
01 31 23 Project Web Site
01 31 26 Electronic Communication Protocols
01 32 00 Construction Progress Documentation
01 32 13 Scheduling of Work
01 32 16 Construction Progress Schedule
01 32 16.13 Network Analysis Schedules
01 32 19 Submittals Schedule
01 32 23 Survey and Layout Data
01 32 26 Construction Progress Reporting
01 32 29 Periodic Work Observation
01 32 33 Photographic Documentation
01 32 36 Video Monitoring and Documentation
01 32 43 Purchase Order Tracking
01 33 00 Submittal Procedures
01 33 13 Certificates
01 33 16 Design Data
01 33 19 Field Test Reporting
01 33 23 Shop Drawings, Product Data, and Samples
01 33 26 Source Quality Control Reporting
01 33 29 Sustainable Design Reporting
01 33 29.01 Material Cost Summary Form
01 33 29.02 Wood-Containing Product List
01 33 29.03 Metal-Containing Product List
01 33 29.04 Material Content Form
01 33 29.05 New Product Source Form
01 33 29.06 Reused Product Form
01 33 29.07 Prohibited Content Installer Certification
01 35 00 Special Procedures
01 35 03 Conservation Treatment Procedures
01 35 13 Special Project Procedures
01 35 13.13 Special Project Procedures for Airport Facilities
01 35 13.16 Special Project Procedures for Detention Facilities
01 35 13.19 Special Project Procedures for Healthcare Facilities
01 35 13.26 Special Project Procedures for Clean Rooms
01 35 13.43 Special Project Procedures for Contaminated Sites
01 35 16 Alteration Project Procedures
01 35 23 Owner Safety Requirements
01 35 26 Governmental Safety Requirements
01 35 29 Health, Safety, and Emergency Response Procedures
01 35 29.13 Health, Safety, and Emergency Response Procedures for Contaminated Sites
01 35 33 Infection Control Procedures
01 35 43 Environmental Procedures
01 35 43.13 Environmental Procedures for Hazardous Materials
01 35 43.16 Environmental Procedures for Toxic Materials
01 35 46 Indoor Air Quality Procedures
01 35 53 Security Procedures
01 35 63 Sustainability Certification Project Requirements
01 35 66 Sustainability Certification Project Procedures
01 35 73 Delegated Design Procedures
01 35 91 Period Treatment Procedures
01 40 00 Quality Requirements
01 41 00 Regulatory Requirements
01 41 13 Codes
01 41 16 Laws
01 41 19 Rules
01 41 23 Fees
01 41 26 Permit Requirements
01 42 00 References
01 42 13 Abbreviations and Acronyms
01 42 16 Definitions
01 42 19 Reference Standards
01 43 00 Quality Assurance
01 43 13 Manufacturer Qualifications
01 43 16 Supplier Qualifications
01 43 19 Fabricator Qualifications
01 43 23 Installer Qualifications
01 43 26 Testing and Inspecting Agency Qualifications
01 43 29 Code-Required Special Inspector Qualifications
01 43 33 Manufacturer's Field Services
01 43 36 Field Samples
01 43 39 Mockups
01 45 00 Quality Control
01 45 13 Source Quality Control Procedures
01 45 16 Field Quality Control Procedures
01 45 16.13 Contractor Quality Control
01 45 23 Testing and Inspecting Services
01 45 26 Plant Inspection Procedures
01 45 29 Testing Laboratory Services
01 45 33 Code-Required Special Inspections and Procedures
01 50 00 Temporary Facilities and Controls
01 51 00 Temporary Utilities
01 51 13 Temporary Electricity
01 51 16 Temporary Fire Protection
01 51 19 Temporary Fuel Oil
01 51 23 Temporary Heating, Cooling, and Ventilating
01 51 26 Temporary Lighting
01 51 29 Temporary Natural-Gas
01 51 33 Temporary Telecommunications
01 51 36 Temporary Water
01 52 00 Construction Facilities
01 52 13 Field Offices and Sheds
01 52 16 First Aid Facilities
01 52 19 Sanitary Facilities
01 53 00 Temporary Construction
01 53 13 Temporary Bridges
01 53 16 Temporary Decking
01 53 19 Temporary Overpasses
01 53 23 Temporary Ramps
01 53 26 Temporary Runarounds
01 54 00 Construction Aids
01 54 13 Temporary Elevators
01 54 16 Temporary Hoists
01 54 19 Temporary Cranes
01 54 23 Temporary Scaffolding and Platforms
01 54 26 Temporary Swing Staging
01 55 00 Vehicular Access and Parking
01 55 13 Temporary Access Roads
01 55 16 Haul Routes
01 55 19 Temporary Parking Areas
01 55 23 Temporary Roads
01 55 26 Traffic Control
01 55 29 Staging Areas
01 56 00 Temporary Barriers and Enclosures
01 56 13 Temporary Air Barriers
01 56 16 Temporary Dust Barriers
01 56 19 Temporary Noise Barriers
01 56 23 Temporary Barricades
01 56 26 Temporary Fencing
01 56 29 Temporary Protective Walkways
01 56 33 Temporary Security Barriers
01 56 36 Temporary Security Enclosures
01 56 39 Temporary Tree and Plant Protection
01 57 00 Temporary Controls
01 57 13 Temporary Erosion and Sediment Control
01 57 16 Temporary Pest Control
01 57 19 Temporary Environmental Controls
01 57 23 Temporary Storm Water Pollution Control
01 57 26 Site Watering for Dust Control
01 58 00 Project Identification
01 58 13 Temporary Project Signage
01 58 16 Temporary Interior Signage
01 60 00 Product Requirements
01 61 00 Common Product Requirements
01 61 13 Software Licensing Requirements
01 62 00 Product Options
01 64 00 Owner-Furnished Products
01 65 00 Product Delivery Requirements
01 66 00 Product Storage and Handling Requirements
01 66 13 Product Storage and Handling Requirements for Hazardous Materials
01 66 16 Product Storage and Handling Requirements for Toxic Materials
01 70 00 Execution and Closeout Requirements
01 71 00 Examination and Preparation
01 71 13 Mobilization
01 71 16 Acceptance of Conditions
01 71 23 Field Engineering
01 71 23.13 Construction Layout
01 71 23.16 Construction Surveying
01 71 33 Protection of Adjacent Construction
01 71 36 Non-Destructive Concrete Examination
01 73 00 Execution
01 73 13 Application
01 73 16 Erection
01 73 19 Installation
01 73 23 Bracing and Anchoring
01 73 26 Existing Products
01 73 29 Cutting and Patching
01 74 00 Cleaning and Waste Management
01 74 13 Progress Cleaning
01 74 16 Site Maintenance
01 74 19 Construction Waste Management and Disposal
01 74 23 Final Cleaning
01 75 00 Starting and Adjusting
01 75 13 Checkout Procedures
01 75 16 Startup Procedures
01 76 00 Protecting Installed Construction
01 77 00 Closeout Procedures
01 77 13 Preliminary Closeout Reviews
01 77 16 Final Closeout Review
01 77 19 Closeout Requirements
01 78 00 Closeout Submittals
01 78 13 Completion and Correction List
01 78 19 Maintenance Contracts
01 78 23 Operation and Maintenance Data
01 78 23.13 Operation Data
01 78 23.16 Maintenance Data
01 78 23.19 Preventative Maintenance Instructions
01 78 29 Final Site Survey
01 78 33 Bonds
01 78 36 Warranties
01 78 39 Project Record Documents
01 78 43 Spare Parts
01 78 46 Extra Stock Materials
01 78 53 Sustainable Design Closeout Documentation
01 79 00 Demonstration and Training
01 80 00 Performance Requirements
01 81 00 Facility Performance Requirements
01 81 13 Sustainable Design Requirements
01 81 16 Facility Environmental Requirements
01 81 19 Indoor Air Quality Requirements
01 82 00 Facility Substructure Performance Requirements
01 82 13 Foundation Performance Requirements
01 82 16 Basement Construction Performance Requirements
01 83 00 Facility Shell Performance Requirements
01 83 13 Superstructure Performance Requirements
01 83 16 Exterior Enclosure Performance Requirements
01 83 19 Roofing Performance Requirements
01 84 00 Interiors Performance Requirements
01 84 13 Interior Construction Performance Requirements
01 84 16 Stairways Performance Requirements
01 84 19 Interior Finishes Performance Requirements
01 85 00 Conveying Equipment Performance Requirements
01 86 00 Facility Services Performance Requirements
01 86 13 Fire Suppression Performance Requirements
01 86 16 Plumbing Performance Requirements
01 86 19 HVAC Performance Requirements
01 86 23 Integrated Automation Performance Requirements
01 86 26 Electrical Performance Requirements
01 86 29 Communications Performance Requirements
01 86 33 Electronic Safety and Security Performance Requirements
01 87 00 Equipment and Furnishings Performance Requirements
01 87 13 Equipment Performance Requirements
01 87 16 Furnishings Performance Requirements
01 88 00 Other Facility Construction Performance Requirements
01 88 13 Special Construction Performance Requirements
01 88 16 Selective Construction Performance Requirements
01 89 00 Site Construction Performance Requirements
01 89 13 Site Preparation Performance Requirements
01 89 16 Site Improvements Performance Requirements
01 89 19 Site Plumbing Utilities Performance Requirements
01 89 23 Site HVAC Utilities Performance Requirements
01 89 26 Site Electrical Utilities Performance Requirements
01 89 29 Other Site Construction Performance Requirements
01 90 00 Life Cycle Activities
01 91 00 Commissioning
01 91 13 General Commissioning Requirements
01 91 16 Facility Substructure Commissioning
01 91 16.13 Foundation Commissioning
01 91 16.53 Basement Construction Commissioning
01 91 19 Facility Shell Commissioning
01 91 19.13 Superstructure Commissioning
01 91 19.43 Exterior Enclosure Commissioning
01 91 19.73 Roofing Commissioning
01 91 23 Interiors Commissioning
01 91 23.13 Interior Construction Commissioning
01 91 23.43 Stairways Commissioning
01 91 23.73 Interior Finishes Commissioning
01 92 00 Facility Operation
01 92 13 Facility Operation Procedures
01 93 00 Facility Maintenance
01 93 13 Facility Maintenance Procedures
01 93 16 Recycling Programs
01 94 00 Facility Decommissioning
01 94 13 Facility Decommissioning Procedures
02 00 00 Existing Conditions
02 01 00 Maintenance of Existing Conditions
02 01 50 Maintenance of Site Remediation
02 01 65 Maintenance of Underground Storage Tank Removal
02 01 80 Maintenance of Facility Remediation
02 01 86 Maintenance of Hazardous Waste Drum Handling
02 03 00 Conservation Treatment for Existing Period Conditions
02 03 01 Maintenance of Existing Period Conditions
02 03 01.19 Mothballing Period Structures
02 03 41 Selective Demolition for Period Structures
02 03 42 Removal and Salvage of Period Construction Materials
02 03 43 Period Structure Relocating
02 03 44 Shoring and Support of Period Structures
02 05 00 Common Work Results for Existing Conditions
02 05 19 Geosynthetics for Existing Conditions
02 05 19.13 Geotextiles for Existing Conditions
02 05 19.16 Geomembranes for Existing Conditions
02 05 19.19 Geogrids for Existing Conditions
02 06 00 Schedules for Existing Conditions
02 06 13 Geotechnical Baseline Report
02 06 14 Geotechnical Data Report
02 06 30 Schedules for Subsurface Investigations
02 06 30.13 Boring or Test Pit Log Schedule
02 06 50 Schedules for Site Remediation
02 06 65 Schedules for Underground Storage Tank Removal
02 06 80 Schedules for Facility Remediation
02 06 86 Schedules for Hazardous Waste Drum Handling
02 08 00 Commissioning of Existing Conditions
02 20 00 Assessment
02 21 00 Surveys
02 21 13 Site Surveys
02 21 13.13 Boundary and Survey Markers
02 21 13.23 Archeological and Historic Surveys
02 21 16 Measured Drawings
02 22 00 Existing Conditions Assessment
02 22 13 Movement and Vibration Assessment
02 22 16 Acoustic Assessment
02 22 19 Traffic Assessment
02 22 23 Accessibility Assessment
02 24 00 Environmental Assessment
02 24 13 Natural Environment Assessment
02 24 13.13 Air Assessment
02 24 13.43 Water Assessment
02 24 13.73 Land Assessment
02 24 23 Chemical Sampling and Analysis of Soils
02 24 43 Transboundary and Global Environmental Aspects Assessment
02 25 00 Existing Material Assessment
02 25 16 Existing Concrete Assessment
02 25 16.13 Concrete Assessment Drilling
02 25 19 Existing Masonry Assessment
02 25 19.13 Masonry Assessment Drilling
02 25 23 Existing Metals Assessment
02 25 23.13 Welding Investigations
02 25 26 Existing Wood, Plastics, and Composites Assessment
02 25 29 Existing Thermal and Moisture Protection Assessment
02 25 29.13 Waterproofing Investigations
02 25 29.23 Roofing Investigations
02 26 00 Hazardous Material Assessment
02 26 23 Asbestos Assessment
02 26 26 Lead Assessment
02 26 29 Polychlorinated Biphenyl Assessment
02 26 33 Biological Assessment
02 26 33.13 Mold Assessment
02 26 36 Hazardous Waste Drum Assessment
02 30 00 Subsurface Investigation
02 31 00 Geophysical Investigations
02 31 13 Seismic Investigations
02 31 16 Gravity Investigations
02 31 19 Magnetic Investigations
02 31 23 Electromagnetic Investigations
02 31 26 Electrical Resistivity Investigations
02 31 29 Magnetotelluric Investigations
02 32 00 Geotechnical Investigations
02 32 13 Subsurface Drilling and Sampling
02 32 16 Material Testing
02 32 19 Exploratory Excavations
02 32 23 Geotechnical Monitoring Before Construction
02 32 23.13 Groundwater Monitoring Before Construction
02 40 00 Demolition and Structure Moving
02 41 00 Demolition
02 41 13 Selective Site Demolition
02 41 13.13 Paving Removal
02 41 13.23 Utility Line Removal
02 41 13.33 Railtrack Removal
02 41 16 Structure Demolition
02 41 16.13 Building Demolition
02 41 16.23 Tower Demolition
02 41 16.33 Bridge Demolition
02 41 16.43 Dam Demolition
02 41 19 Selective Demolition
02 41 19.13 Selective Building Demolition
02 41 19.16 Selective Interior Demolition
02 41 19.19 Selective Facility Services Demolition
02 41 19.33 Selective Bridge Demolition
02 42 00 Removal and Salvage of Construction Materials
02 42 13 Deconstruction of Structures
02 42 13.13 Deconstruction of Buildings
02 43 00 Structure Moving
02 43 13 Structure Relocation
02 43 13.13 Building Relocation
02 43 16 Structure Raising
02 43 16.13 Building Raising
02 50 00 Site Remediation
02 51 00 Physical Decontamination
02 51 13 Coagulation and Flocculation Decontamination
02 51 16 Reverse-Osmosis Decontamination
02 51 19 Solidification and Stabilization Decontamination
02 51 23 Mechanical Filtration Decontamination
02 51 26 Radioactive Decontamination
02 51 29 Surface Cleaning Decontamination
02 51 29.13 High-Pressure Water Cleaning Decontamination
02 51 29.16 Vacuum Sweeping Cleaning Decontamination
02 51 33 Surface Removal Decontamination
02 51 33.13 Surface Removal Decontamination by Grinding
02 51 33.16 Surface Removal Decontamination by Sand Blasting
02 51 33.19 Surface Removal Decontamination by Ultrasound
02 52 00 Chemical Decontamination
02 52 13 Chemical Precipitation Decontamination
02 52 16 Ion Change Decontamination
02 52 19 Neutralization Decontamination
02 53 00 Thermal Decontamination
02 53 13 Incineration Decontamination
02 53 13.13 Remediation of Contaminated Soils and Sludges by Incineration
02 53 16 Thermal Desorption Decontamination
02 53 16.13 Remediation of Contaminated Soils by Thermal Desorption
02 53 19 Vitrification Decontamination
02 54 00 Biological Decontamination
02 54 13 Aerobic Processes Decontamination
02 54 16 Anaerobic Processes Decontamination
02 54 19 Bioremediation Decontamination
02 54 19.13 Bioremediation Using Landfarming
02 54 19.16 Bioremediation of Soils Using Windrow Composting
02 54 19.19 Bioremediation Using Bacteria Injection
02 54 23 Soil Washing through Separation/Solubilization
02 54 26 Organic Decontamination
02 55 00 Remediation Soil Stabilization
02 56 00 Site Containment
02 56 13 Waste Containment
02 56 13.13 Geomembrane Waste Containment
02 56 19 Gas Containment
02 56 19.13 Fluid-Applied Gas Barrier
02 57 00 Sinkhole Remediation
02 57 13 Sinkhole Remediation by Grouting
02 57 13.13 Sinkhole Remediation by Compaction Grouting
02 57 13.16 Sinkhole Remediation by Cap Grouting
02 57 16 Sinkhole Remediation by Backfilling
02 58 00 Snow Control
02 58 13 Snow Fencing
02 58 16 Snow Avalanche Control
02 60 00 Contaminated Site Material Removal
02 61 00 Removal and Disposal of Contaminated Soils
02 61 13 Excavation and Handling of Contaminated Material
02 61 23 Removal and Disposal of Polychlorinate Biphenyl Contaminated Soils
02 61 26 Removal and Disposal of Asbestos Contaminated Soils
02 61 29 Removal and Disposal of Organically Contaminated Soils
02 62 00 Hazardous Waste Recovery Processes
02 62 13 Air and Steam Stripping
02 62 16 Soil Vapor Extraction
02 62 19 Soil Washing and Flushing
02 65 00 Underground Storage Tank Removal
02 70 00 Water Remediation
02 71 00 Groundwater Treatment
02 72 00 Water Decontamination
02 72 13 Chemical Water Decontamination
02 72 16 Biological Water Decontamination
02 72 19 Electrolysis Water Decontamination
02 80 00 Facility Remediation
02 81 00 Transportation and Disposal of Hazardous Materials
02 82 00 Asbestos Remediation
02 82 13 Asbestos Abatement
02 82 13.13 Glovebag Asbestos Abatement
02 82 13.16 Precautions for Asbestos Abatement
02 82 13.19 Asbestos Floor Tile and Mastic Abatement
02 82 13.33 Asbestos Abatement for Utilities
02 82 16 Engineering Control of Asbestos Containing Materials
02 82 33 Removal and Disposal of Asbestos Containing Materials
02 83 00 Lead Remediation
02 83 13 Lead Hazard Control Activities
02 83 19 Lead-Based Paint Remediation
02 83 19.13 Lead-Based Paint Abatement
02 83 33 Removal and Disposal of Material Containing Lead
02 83 33.13 Lead-Based Paint Removal and Disposal
02 84 00 Polychlorinate Biphenyl Remediation
02 84 16 Handling of Lighting Ballasts and Lamps Containing PCBs and Mercury
02 84 33 Removal and Disposal of Polychlorinate Biphenyls
02 86 00 Hazardous Waste Drum Handling
02 87 00 Biohazard Remediation
02 87 13 Mold Remediation
02 87 13.13 Precautions for Mold Remediation
02 87 13.16 Mold Remediation Preparation and Containment
02 87 13.19 Mold Remediation Clearance Air Sampling
02 87 13.33 Removal and Disposal of Materials with Mold
02 87 16 Excrement Removal
02 87 16.13 Bird Excrement Removal
02 87 16.16 Rodent Excrement Removal
03 00 00 Concrete
03 01 00 Maintenance of Concrete
03 01 10 Maintenance of Concrete Forming and Accessories
03 01 20 Maintenance of Concrete Reinforcing
03 01 23 Maintenance of Stressing Tendons
03 01 30 Maintenance of Cast-in-Place Concrete
03 01 30.51 Cleaning of Cast-in-Place Concrete
03 01 30.61 Resurfacing of Cast-in-Place Concrete
03 01 30.71 Rehabilitation of Cast-in-Place Concrete
03 01 30.72 Strengthening of Cast-in-Place Concrete
03 01 40 Maintenance of Precast Concrete
03 01 40.51 Cleaning of Precast Concrete
03 01 40.61 Resurfacing of Precast Concrete
03 01 40.71 Rehabilitation of Precast Concrete
03 01 40.72 Strengthening of Precast Concrete
03 01 50 Maintenance of Cast Decks and Underlayment
03 01 50.51 Cleaning Cast Decks and Underlayment
03 01 50.61 Resurfacing of Cast Decks and Underlayment
03 01 50.71 Rehabilitation of Cast Decks and Underlayment
03 01 50.72 Strengthening of Cast Decks and Underlayment
03 01 60 Maintenance of Grouting
03 01 70 Maintenance of Mass Concrete
03 01 80 Maintenance of Concrete Cutting and Boring
03 03 00 Conservation Treatment for Period Concrete
03 03 30 Conservation Treatment for Period Cast-in-Place Concrete
03 03 31 Conservation Treatment for Period Structural Concrete
03 03 33 Conservation Treatment for Period Architectural Concrete
03 05 00 Common Work Results for Concrete
03 05 05 Selective Demolition for Concrete
03 06 00 Schedules for Concrete
03 06 10 Schedules for Concrete Forming and Accessories
03 06 20 Schedules for Concrete Reinforcing
03 06 20.13 Concrete Beam Reinforcing Schedule
03 06 20.16 Concrete Slab Reinforcing Schedule
03 06 30 Schedules for Cast-in-Place Concrete
03 06 30.13 Concrete Footing Schedule
03 06 30.16 Concrete Column Schedule
03 06 30.19 Concrete Slab Schedule
03 06 30.23 Concrete Shaft Schedule
03 06 30.26 Concrete Beam Schedule
03 06 40 Schedules for Precast Concrete
03 06 40.13 Precast Concrete Panel Schedule
03 06 50 Schedules for Cast Decks and Underlayment
03 06 60 Schedules for Grouting
03 06 70 Schedules for Mass Concrete
03 06 80 Schedules for Concrete Cutting and Boring
03 08 00 Commissioning of Concrete
03 10 00 Concrete Forming and Accessories
03 11 00 Concrete Forming
03 11 13 Structural Cast-in-Place Concrete Forming
03 11 13.13 Concrete Slip Forming
03 11 13.16 Concrete Shoring
03 11 13.19 Falsework
03 11 16 Architectural Cast-in Place Concrete Forming
03 11 16.13 Concrete Form Liners
03 11 19 Insulating Concrete Forming
03 11 23 Permanent Stair Forming
03 11 26 Permanent Tier Forming
03 15 00 Concrete Accessories
03 15 13 Waterstops
03 15 13.13 Non-Expanding Waterstops
03 15 13.16 Expanding Waterstops
03 15 13.19 Combination Expanding and Injection Hose Waterstops
03 15 13.21 Injection Hose Waterstops
03 15 16 Concrete Construction Joints
03 15 19 Cast-In Concrete Anchors
03 15 21 Termite Barrier
03 20 00 Concrete Reinforcing
03 21 00 Reinforcement Bars
03 21 11 Plain Steel Reinforcement Bars
03 21 13 Galvanized Reinforcement Steel Bars
03 21 16 Epoxy-Coated Reinforcement Steel Bars
03 21 19 Stainless Steel Reinforcement Bars
03 21 21 Composite Reinforcement Bars
03 21 21.11 Glass Fiber-Reinforced Polymer Reinforcement Bars
03 21 21.13 Organic Fiber-Reinforced Polymer Reinforcement Bars
03 21 21.16 Carbon Fiber-Reinforced Polymer Reinforcement Bars
03 22 00 Fabric and Grid Reinforcing
03 22 13 Galvanized Welded Wire Fabric Reinforcing
03 22 16 Epoxy-Coated Welded Wire Fabric Reinforcing
03 22 19 Composite Grid Reinforcing
03 23 00 Stressed Tendon Reinforcing
03 24 00 Fibrous Reinforcing
03 25 00 Composite Reinforcing
03 25 13 Glass Fiber-Reinforced Polymer Reinforcing
03 25 16 Organic Fiber-Reinforced Polymer Reinforcing
03 25 19 Carbon Fiber-Reinforced Polymer Reinforcing
03 30 00 Cast-in-Place Concrete
03 30 53 Miscellaneous Cast-in-Place Concrete
03 31 00 Structural Concrete
03 31 13 Heavyweight Structural Concrete
03 31 16 Lightweight Structural Concrete
03 31 19 Shrinkage-Compensating Structural Concrete
03 31 23 High-Performance Structural Concrete
03 31 24 Ultra High-Performance Structural Concrete
03 31 26 Self-Compacting Concrete
03 33 00 Architectural Concrete
03 33 13 Heavyweight Architectural Concrete
03 33 16 Lightweight Architectural Concrete
03 34 00 Low Density Concrete
03 35 00 Concrete Finishing
03 35 13 High-Tolerance Concrete Floor Finishing
03 35 16 Heavy-Duty Concrete Floor Finishing
03 35 19 Colored Concrete Finishing
03 35 23 Exposed Aggregate Concrete Finishing
03 35 26 Grooved Concrete Surface Finishing
03 35 29 Tooled Concrete Finishing
03 35 33 Stamped Concrete Finishing
03 35 43 Polished Concrete Finishing
03 35 43.13 Polished and Dyed Concrete Finishing
03 35 43.16 Polished and Stained Concrete Finishing
03 35 46 Concrete Topical Treatments
03 37 00 Specialty Placed Concrete
03 37 13 Shotcrete
03 37 16 Pumped Concrete
03 37 19 Pneumatically Placed Concrete
03 37 23 Roller-Compacted Concrete
03 37 26 Underwater Placed Concrete
03 38 00 Post-Tensioned Concrete
03 38 13 Post-Tensioned Concrete Preparation
03 38 16 Unbonded Post-Tensioned Concrete
03 38 19 Bonded Post-Tensioned Concrete
03 39 00 Concrete Curing
03 39 13 Water Concrete Curing
03 39 16 Sand Concrete Curing
03 39 23 Membrane Concrete Curing
03 39 23.13 Chemical Compound Membrane Concrete Curing
03 39 23.23 Sheet Membrane Concrete Curing
03 40 00 Precast Concrete
03 41 00 Precast Structural Concrete
03 41 13 Precast Concrete Hollow Core Planks
03 41 16 Precast Concrete Slabs
03 41 23 Precast Concrete Stairs
03 41 33 Precast Structural Pretensioned Concrete
03 41 36 Precast Structural Post-Tensioned Concrete
03 45 00 Precast Architectural Concrete
03 45 13 Faced Architectural Precast Concrete
03 45 33 Precast Architectural Pretensioned Concrete
03 45 36 Precast Architectural Post-Tensioned Concrete
03 47 00 Site-Cast Concrete
03 47 13 Tilt-Up Concrete
03 47 16 Lift-Slab Concrete
03 48 00 Precast Concrete Specialties
03 48 13 Precast Concrete Bollards
03 48 13.11 Precast Concrete Security Bollards
03 48 16 Precast Concrete Splash Blocks
03 48 19 Precast Concrete Stair Treads
03 48 26 Precast Concrete Parking Bumpers
03 48 33 Precast Pre-Framed Concrete Panels
03 48 43 Precast Concrete Trim
03 49 00 Glass-Fiber-Reinforced Concrete
03 49 13 Glass-Fiber-Reinforced Concrete Column Covers
03 49 16 Glass-Fiber-Reinforced Concrete Spandrels
03 49 43 Glass-Fiber-Reinforced Concrete Trim
03 50 00 Cast Decks and Underlayment
03 51 00 Cast Roof Decks
03 51 13 Cementitious Wood Fiber Decks
03 51 16 Gypsum Concrete Roof Decks
03 52 00 Lightweight Concrete Roof Insulation
03 52 13 Composite Concrete Roof Insulation
03 52 16 Lightweight Insulating Concrete
03 52 16.13 Lightweight Cellular Insulating Concrete
03 52 16.16 Lightweight Aggregate Insulating Concrete
03 53 00 Concrete Topping
03 53 13 Emery-Aggregate Concrete Topping
03 53 16 Iron-Aggregate Concrete Topping
03 53 19 Concrete Overlayment
03 54 00 Cast Underlayment
03 54 13 Gypsum Cement Underlayment
03 54 16 Hydraulic Cement Underlayment
03 60 00 Grouting
03 61 00 Cementitious Grouting
03 61 13 Dry-Pack Grouting
03 62 00 Non-Shrink Grouting
03 62 13 Non-Metallic Non-Shrink Grouting
03 62 16 Metallic Non-Shrink Grouting
03 63 00 Epoxy Grouting
03 64 00 Injection Grouting
03 64 23 Epoxy Injection Grouting
03 70 00 Mass Concrete
03 71 00 Mass Concrete for Raft Foundations
03 72 00 Mass Concrete for Dams
03 80 00 Concrete Cutting and Boring
03 81 00 Concrete Cutting
03 81 13 Flat Concrete Sawing
03 81 16 Track Mounted Concrete Wall Sawing
03 81 19 Wire Concrete Wall Sawing
03 81 23 Hand Concrete Wall Sawing
03 81 26 Chain Concrete Wall Sawing
03 82 00 Concrete Boring
03 82 13 Concrete Core Drilling
04 00 00 Masonry
04 01 00 Maintenance of Masonry
04 01 20 Maintenance of Unit Masonry
04 01 20.41 Unit Masonry Stabilization
04 01 20.51 Unit Masonry Maintenance
04 01 20.52 Unit Masonry Cleaning
04 01 20.91 Unit Masonry Restoration
04 01 20.93 Testing and Sampling Brick Units for Restoration
04 01 40 Maintenance of Stone Assemblies
04 01 40.51 Stone Maintenance
04 01 40.52 Stone Cleaning
04 01 40.91 Stone Restoration
04 01 50 Maintenance of Refractory Masonry
04 01 60 Maintenance of Corrosion-Resistant Masonry
04 01 70 Maintenance of Manufactured Masonry
04 03 00 Conservation Treatment for Period Masonry
04 03 01 Maintenance for Period Masonry
04 03 01.13 Period Masonry Cleaning
04 03 05 Common Work Results for Period Masonry
04 03 05.13 Period Masonry Mortaring
04 03 05.16 Period Masonry Grouting
04 03 05.19 Period Masonry Anchorage and Reinforcing
04 03 21 Conservation Treatment for Period Clay Unit Masonry
04 03 21.19 Clay Brick Conservation Treatment
04 03 21.21 Terra Cotta Conservation Treatment
04 03 21.23 Fiance Block Conservation Treatment
04 03 22 Conservation Treatment for Period Concrete Unit Masonry
04 03 24 Conservation Treatment for Period Adobe Unit Masonry
04 03 43 Conservation Treatment for Period Stone Masonry
04 05 00 Common Work Results for Masonry
04 05 05 Selective Demolition for Masonry
04 05 13 Masonry Mortaring
04 05 13.16 Chemical-Resistant Masonry Mortaring
04 05 13.19 Epoxy Masonry Mortaring
04 05 13.23 Surface Bonding Masonry Mortaring
04 05 13.26 Engineered Masonry Mortaring
04 05 13.29 Refractory Masonry Mortaring
04 05 13.91 Masonry Restoration Mortaring
04 05 16 Masonry Grouting
04 05 16.16 Chemical-Resistant Masonry Grouting
04 05 16.26 Engineered Masonry Grouting
04 05 19 Masonry Anchorage and Reinforcing
04 05 19.13 Continuous Joint Reinforcing
04 05 19.16 Masonry Anchors
04 05 19.26 Masonry Reinforcing Bars
04 05 19.29 Stone Anchors
04 05 21 Masonry Strengthening
04 05 23 Masonry Accessories
04 05 23.13 Masonry Control and Expansion Joints
04 05 23.16 Masonry Embedded Flashing
04 05 23.19 Masonry Cavity Drainage, Weepholes, and Vents
04 06 00 Schedules for Masonry
04 06 20 Schedules for Unit Masonry
04 06 20.13 Masonry Unit Schedule
04 06 40 Schedules for Stone Assemblies
04 06 50 Schedules for Refractory Masonry
04 06 60 Schedules for Corrosion-Resistant Masonry
04 06 70 Schedules for Manufactured Masonry
04 08 00 Commissioning of Masonry
04 20 00 Unit Masonry
04 21 00 Clay Unit Masonry
04 21 13 Brick Masonry
04 21 13.13 Brick Veneer Masonry
04 21 13.23 Surface-Bonded Brick Masonry
04 21 16 Ceramic Glazed Clay Masonry
04 21 19 Clay Tile Masonry
04 21 23 Structural Clay Tile Masonry
04 21 26 Glazed Structural Clay Tile Masonry
04 21 29 Terra Cotta Masonry
04 22 00 Concrete Unit Masonry
04 22 00.13 Concrete Unit Veneer Masonry
04 22 00.16 Surface-Bonded Concrete Unit Masonry
04 22 19 Insulated Concrete Unit Masonry
04 22 23 Architectural Concrete Unit Masonry
04 22 23.13 Exposed Aggregate Concrete Unit Masonry
04 22 23.16 Fluted Concrete Unit Masonry
04 22 23.19 Molded-Face Concrete Unit Masonry
04 22 23.23 Prefaced Concrete Unit Masonry
04 22 23.26 Sound-Absorbing Concrete Unit Masonry
04 22 23.29 Split-Face Concrete Unit Masonry
04 22 26 Autoclaved Aerated Concrete Unit Masonry
04 22 33 Interlocking Concrete Unit Masonry
04 23 00 Glass Unit Masonry
04 23 13 Vertical Glass Unit Masonry
04 23 16 Glass Unit Masonry Floors
04 23 19 Glass Unit Masonry Skylights
04 24 00 Adobe Unit Masonry
04 24 13 Site-Cast Adobe Unit Masonry
04 24 16 Manufactured Adobe Unit Masonry
04 25 00 Unit Masonry Panels
04 25 13 Metal-Supported Unit Masonry Panels
04 26 00 Single-Wythe Unit Masonry
04 26 13 Masonry Veneer
04 27 00 Multiple-Wythe Unit Masonry
04 27 13 Composite Unit Masonry
04 27 23 Cavity Wall Unit Masonry
04 28 00 Concrete Form Masonry Units
04 28 13 Dry-Stacked, Concrete-Filled Masonry Units
04 28 23 Mortar-Set, Concrete-Filled Masonry Units
04 29 00 Engineered Unit Masonry
04 40 00 Stone Assemblies
04 41 00 Dry-Placed Stone
04 42 00 Exterior Stone Cladding
04 42 13 Masonry-Supported Stone Cladding
04 42 16 Steel-Stud-Supported Stone Cladding
04 42 19 Strongback-Frame-Supported Stone Cladding
04 42 23 Truss-Supported Stone Cladding
04 42 26 Grid-System-Supported Stone Cladding
04 42 43 Stone Panels for Curtain Walls
04 43 00 Stone Masonry
04 43 13 Stone Masonry Veneer
04 43 13.13 Anchored Stone Masonry Veneer
04 43 13.16 Adhered Stone Masonry Veneer
04 43 16 Stone Fabrications
04 50 00 Refractory Masonry
04 51 00 Flue Liner Masonry
04 52 00 Combustion Chamber Masonry
04 53 00 Castable Refractory Masonry
04 54 00 Refractory Brick Masonry
04 57 00 Masonry Fireplaces
04 57 33 Modular Masonry Fireplaces
04 60 00 Corrosion-Resistant Masonry
04 61 00 Chemical-Resistant Brick Masonry
04 62 00 Vitrified Clay Liner Plate
04 70 00 Manufactured Masonry
04 71 00 Manufactured Brick Masonry
04 71 13 Calcium Silicate Manufactured Brick Masonry
04 72 00 Cast Stone Masonry
04 73 00 Manufactured Stone Masonry
04 73 13 Calcium Silicate Manufactured Stone Masonry
05 00 00 Metals
05 01 00 Maintenance of Metals
05 01 10 Maintenance of Structural Metal Framing
05 01 20 Maintenance of Metal Joists
05 01 30 Maintenance of Metal Decking
05 01 40 Maintenance of Cold-Formed Metal Framing
05 01 50 Maintenance of Metal Fabrications
05 01 70 Maintenance of Decorative Metal
05 01 70.91 Historic Treatment of Decorative Metal
05 03 00 Conservation Treatment for Period Metals
05 03 12 Conservation Treatment for Period Structural Steel
05 03 12.13 Conservation Treatment for Period Architecturally Exposed Steel
05 03 12.23 Conservation Treatment for Period Structural Steel for Buildings
05 03 51 Conservation Treatment for Period Metal Stairs
05 03 58 Conservation Treatment for Period Column Covers
05 03 70 Conservation Treatment for Period Decorative Metal
05 03 71 Conservation Treatment for Period Decorative Metal Stairs
05 03 73 Conservation Treatment for Period Decorative Metal Railings
05 03 75 Conservation Treatment for Period Decorative Formed Metal
05 03 76 Conservation Treatment for Period Decorative Forged Metal
05 05 00 Common Work Results for Metals
05 05 05 Selective Demolition for Metals
05 05 13 Shop-Applied Coatings for Metal
05 05 19 Post-Installed Concrete Anchors
05 05 23 Metal Fastenings
05 05 53 Security Metal Fastenings
05 06 00 Schedules for Metals
05 06 10 Schedules for Structural Metal Framing
05 06 10.13 Steel Column Schedule
05 06 10.16 Steel Beam Schedule
05 06 20 Schedules for Metal Joists
05 06 20.13 Steel Joist Schedule
05 06 30 Schedules for Metal Decking
05 06 40 Schedules for Cold-Formed Metal Framing
05 06 50 Schedules for Metal Fabrications
05 06 70 Schedules for Decorative Metal
05 08 00 Commissioning of Metals
05 10 00 Structural Metal Framing
05 12 00 Structural Steel Framing
05 12 13 Architecturally-Exposed Structural Steel Framing
05 12 16 Fabricated Fireproofed Steel Columns
05 12 19 Buckling Restrained Braces
05 12 23 Structural Steel for Buildings
05 12 33 Structural Steel for Bridges
05 13 00 Structural Stainless-Steel Framing
05 14 00 Structural Aluminum Framing
05 14 13 Architecturally-Exposed Structural Aluminum Framing
05 15 00 Wire Rope Assemblies
05 15 13 Aluminum Wire Rope Assemblies
05 15 16 Steel Wire Rope Assemblies
05 15 19 Stainless-Steel Wire Rope Assemblies
05 16 00 Structural Cabling
05 16 13 Cable Bow Truss Assemblies
05 16 33 Bridge Cabling
05 17 00 Structural Rod Assemblies
05 19 00 Tension Rod and Cable Truss Assemblies
05 19 13 Façade Support Truss Assemblies
05 19 19 Canopy Support Truss Assemblies
05 20 00 Metal Joists
05 21 00 Steel Joist Framing
05 21 13 Deep Longspan Steel Joist Framing
05 21 16 Longspan Steel Joist Framing
05 21 19 Open Web Steel Joist Framing
05 21 23 Steel Joist Girder Framing
05 25 00 Aluminum Joist Framing
05 30 00 Metal Decking
05 31 00 Steel Decking
05 31 13 Steel Floor Decking
05 31 23 Steel Roof Decking
05 31 33 Steel Form Decking
05 33 00 Aluminum Decking
05 33 13 Aluminum Floor Decking
05 33 23 Aluminum Roof Decking
05 34 00 Acoustical Metal Decking
05 35 00 Raceway Decking Assemblies
05 36 00 Composite Metal Decking
05 36 13 Composite Steel Plate and Elastomer Decking
05 40 00 Cold-Formed Metal Framing
05 41 00 Structural Metal Stud Framing
05 42 00 Cold-Formed Metal Joist Framing
05 42 13 Cold-Formed Metal Floor Joist Framing
05 42 23 Cold-Formed Metal Roof Joist Framing
05 43 00 Slotted Channel Framing
05 44 00 Cold-Formed Metal Trusses
05 44 13 Cold-Formed Metal Roof Trusses
05 45 00 Metal Support Assemblies
05 45 13 Mechanical Metal Supports
05 45 16 Electrical Metal Supports
05 45 19 Communications Metal Supports
05 45 23 Healthcare Metal Supports
05 50 00 Metal Fabrications
05 51 00 Metal Stairs
05 51 13 Metal Pan Stairs
05 51 16 Metal Floor Plate Stairs
05 51 17 Alternating Tread Stairs
05 51 19 Metal Grating Stairs
05 51 23 Metal Fire Escapes
05 51 33 Metal Ladders
05 51 33.13 Vertical Metal Ladders
05 51 33.16 Inclined Metal Ladders
05 51 33.23 Alternating Tread Ladders
05 51 36 Metal Walkways
05 51 36.13 Metal Catwalks
05 51 36.16 Metal Ramps
05 51 36.19 Metal Platforms
05 52 00 Metal Railings
05 52 13 Pipe and Tube Railings
05 53 00 Metal Gratings
05 53 13 Bar Gratings
05 53 16 Plank Gratings
05 53 19 Expanded Metal Gratings
05 54 00 Metal Floor Plates
05 55 00 Metal Stair Treads and Nosings
05 55 13 Metal Stair Treads
05 55 16 Metal Stair Nosings
05 56 00 Metal Castings
05 58 00 Formed Metal Fabrications
05 58 13 Column Covers
05 58 16 Formed Metal Enclosures
05 58 19 Heating/Cooling Unit Covers
05 58 23 Formed Metal Guards
05 59 00 Metal Specialties
05 59 13 Metal Balconies
05 59 63 Detention Enclosures
05 70 00 Decorative Metal
05 71 00 Decorative Metal Stairs
05 71 13 Fabricated Metal Spiral Stairs
05 73 00 Decorative Metal Railings
05 73 13 Glazed Decorative Metal Railings
05 73 16 Wire Rope Decorative Metal Railings
05 74 00 Decorative Metal Castings
05 75 00 Decorative Formed Metal
05 76 00 Decorative Forged Metal
05 77 00 Decorative Extruded Metal
06 00 00 Wood, Plastics, and Composites
06 01 00 Maintenance of Wood, Plastics, and Composites
06 01 10 Maintenance of Rough Carpentry
06 01 10.71 Rough Carpentry Rehabilitation
06 01 10.91 Rough Carpentry Restoration
06 01 10.92 Rough Carpentry Preservation
06 01 20 Maintenance of Finish Carpentry
06 01 20.71 Finish Carpentry Rehabilitation
06 01 20.91 Finish Carpentry Restoration
06 01 20.92 Finish Carpentry Preservation
06 01 40 Maintenance of Architectural Woodwork
06 01 40.51 Architectural Woodwork Cleaning
06 01 40.61 Architectural Woodwork Refinishing
06 01 40.91 Architectural Woodwork Restoration
06 01 50 Maintenance of Structural Plastics
06 01 60 Maintenance of Plastic Fabrications
06 01 60.51 Plastic Cleaning
06 01 60.71 Plastic Rehabilitation
06 01 60.91 Plastic Restoration
06 01 60.92 Plastic Preservation
06 01 70 Maintenance of Structural Composites
06 01 80 Maintenance of Composite Assemblies
06 01 80.51 Composite Cleaning
06 01 80.71 Composite Rehabilitation
06 01 80.91 Composite Restoration
06 01 80.92 Composite Preservation
06 03 00 Conservation Treatment for Period Wood
06 03 01 Maintenance for Period Wood
06 03 01.31 Period Wood Storage and Protection
06 03 05 Common Work Results for Period Wood
06 03 05.73 Long-term Period Wood Treatment
06 03 05.74 Eradication of Insects in Period Wood
06 03 05.75 Antiseptic Treatment of Period Wood
06 03 13 Conservation Treatment of Period Log Construction
06 03 13.23 Conservation Treatment for Period Heavy Timber
06 03 20 Conservation Treatment for Period Finish Carpentry
06 03 20.13 Period Exterior Finish Carpentry
06 03 20.23 Period Interior Finish Carpentry
06 03 40 Conservation Treatment for Period Architectural Woodwork
06 03 40.13 Period Exterior Architectural Woodwork
06 03 40.23 Period Interior Architectural Woodwork
06 05 00 Common Work Results for Wood, Plastics, and Composites
06 05 05 Selective Demolition for Wood, Plastics, and Composites
06 05 23 Wood, Plastic, and Composite Fastenings
06 05 73 Wood Treatment
06 05 73.13 Fire-Retardant Wood Treatment
06 05 73.33 Preservative Wood Treatment
06 05 73.91 Long-Term Wood Treatment
06 05 73.93 Eradication of Insects in Wood
06 05 73.96 Antiseptic Treatment of Wood
06 05 83 Shop-Applied Wood Coatings
06 06 00 Schedules for Wood, Plastics, and Composites
06 06 10 Schedules for Rough Carpentry
06 06 10.13 Nailing Schedule
06 06 10.16 Wood Beam Schedule
06 06 10.19 Plywood Shear Wall Schedule
06 06 10.23 Plywood Web Joist Schedule
06 06 10.26 Wood Truss Schedule
06 06 20 Schedules for Finish Carpentry
06 06 40 Schedules for Architectural Woodwork
06 06 50 Schedules for Structural Plastics
06 06 60 Schedules for Plastic Fabrications
06 06 70 Schedules for Structural Composites
06 06 80 Schedules for Composite Assemblies
06 08 00 Commissioning of Wood, Plastics, and Composites
06 10 00 Rough Carpentry
06 10 53 Miscellaneous Rough Carpentry
06 10 63 Exterior Rough Carpentry
06 11 00 Wood Framing
06 11 13 Engineered Wood Products
06 11 16 Mechanically Graded Lumber
06 12 00 Structural Panels
06 12 13 Cementitious Reinforced Panels
06 12 16 Stressed Skin Panels
06 13 00 Heavy Timber Construction
06 13 13 Log Construction
06 13 13.91 Period Horizontal Log Work
06 13 16 Pole Construction
06 13 23 Heavy Timber Framing
06 13 26 Heavy Timber Trusses
06 13 33 Heavy Timber Pier Construction
06 14 00 Treated Wood Foundations
06 15 00 Wood Decking
06 15 13 Wood Floor Decking
06 15 13.91 Carvel Planking
06 15 16 Wood Roof Decking
06 15 19 Timber Decking
06 15 23 Laminated Wood Decking
06 15 33 Wood Patio Decking
06 16 00 Sheathing
06 16 13 Insulating Sheathing
06 16 23 Subflooring
06 16 26 Underlayment
06 16 33 Wood Board Sheathing
06 16 36 Wood Panel Product Sheathing
06 16 43 Gypsum Sheathing
06 16 53 Moisture-Resistant Sheathing Board
06 16 63 Cementitious Sheathing
06 17 00 Shop-Fabricated Structural Wood
06 17 13 Laminated Veneer Lumber
06 17 19 Cross-Laminated Timber
06 17 23 Parallel Strand Lumber
06 17 33 Wood I-Joists
06 17 36 Metal-Web Wood Joists
06 17 43 Rim Boards
06 17 53 Shop-Fabricated Wood Trusses
06 18 00 Glued-Laminated Construction
06 18 13 Glued-Laminated Beams
06 18 16 Glued-Laminated Columns
06 20 00 Finish Carpentry
06 20 13 Exterior Finish Carpentry
06 20 23 Interior Finish Carpentry
06 22 00 Millwork
06 22 13 Standard Pattern Wood Trim
06 25 00 Prefinished Paneling
06 25 13 Prefinished Hardboard Paneling
06 25 16 Prefinished Plywood Paneling
06 26 00 Board Paneling
06 26 13 Profile Board Paneling
06 40 00 Architectural Woodwork
06 40 13 Exterior Architectural Woodwork
06 40 23 Interior Architectural Woodwork
06 41 00 Architectural Wood Casework
06 41 13 Wood-Veneer-Faced Architectural Cabinets
06 41 16 Plastic-Laminate-Clad Architectural Cabinets
06 41 93 Cabinet and Drawer Hardware
06 42 00 Wood Paneling
06 42 13 Wood Board Paneling
06 42 14 Stile and Rail Wood Paneling
06 42 16 Flush Wood Paneling
06 42 19 Plastic-Laminate-Faced Wood Paneling
06 43 00 Wood Stairs and Railings
06 43 13 Wood Stairs
06 43 16 Wood Railings
06 44 00 Ornamental Woodwork
06 44 13 Wood Turnings
06 44 16 Wood Pilasters
06 44 19 Wood Grilles
06 44 23 Wood Corbels
06 44 26 Wood Cupolas
06 44 29 Wood Finials
06 44 33 Wood Mantels
06 44 36 Wood Pediment Heads
06 44 39 Wood Posts and Columns
06 46 00 Wood Trim
06 46 13 Wood Door and Window Casings
06 46 16 Wood Aprons
06 46 19 Wood Base and Shoe Moldings
06 46 23 Wood Chair Rails
06 46 26 Wood Cornices
06 46 29 Wood Fasciae and Soffits
06 46 33 Wood Stops, Stools, and Sills
06 46 91 Splicing of Wooden Components
06 48 00 Wood Frames
06 48 13 Exterior Wood Door Frames
06 48 16 Interior Wood Door Frames
06 48 19 Ornamental Wood Frames
06 48 23 Stick-Built Wood Windows
06 48 26 Wood-Veneer Frames
06 49 00 Wood Screens and Shutters
06 49 13 Wood Screens
06 49 16 Wood Blinds
06 49 19 Wood Shutters
06 50 00 Structural Plastics
06 51 00 Structural Plastic Shapes and Plates
06 51 13 Plastic Lumber
06 52 00 Plastic Structural Assemblies
06 53 00 Plastic Decking
06 53 13 Solid Plastic Decking
06 60 00 Plastic Fabrications
06 61 00 Cast Polymer Fabrications
06 61 13 Simulated Stone Fabrications
06 61 16 Solid Surfacing Fabrications
06 63 00 Plastic Railings
06 64 00 Plastic Paneling
06 64 13 Plastic Lattice Paneling
06 65 00 Plastic Trim
06 66 00 Custom Ornamental Simulated Woodwork
06 70 00 Structural Composites
06 71 00 Structural Composite Shapes and Plates
06 71 13 Composite Lumber
06 72 00 Composite Structural Assemblies
06 72 13 Composite Joist Assemblies
06 72 23 Composite Stair Assemblies
06 73 00 Composite Decking
06 73 13 Composite Structural Decking
06 74 00 Composite Gratings
06 74 13 Fiberglass Reinforced Gratings
06 80 00 Composite Fabrications
06 81 00 Composite Railings
06 81 13 Glass-Fiber-Reinforced Plastic Railings
06 82 00 Composite Trim
06 83 00 Composite Paneling
06 83 13 Resin Composite Paneling
06 83 16 Fiberglass Reinforced Paneling
07 00 00 Thermal and Moisture Protection
07 01 00 Operation and Maintenance of Thermal and Moisture Protection
07 01 10 Maintenance of Dampproofing and Waterproofing
07 01 10.81 Waterproofing Replacement
07 01 20 Maintenance of Thermal Protection
07 01 30 Maintenance of Steep Slope Roofing
07 01 40 Maintenance of Roofing and Siding Panels
07 01 50 Maintenance of Membrane Roofing
07 01 50.13 Roof Moisture Survey
07 01 50.16 Roof Maintenance Program
07 01 50.19 Preparation for Re-Roofing
07 01 50.23 Roof Removal
07 01 50.61 Roof Re-Coating
07 01 50.81 Roof Replacement
07 01 50.91 Roofing Restoration
07 01 60 Maintenance of Flashing and Sheet Metal
07 01 60.71 Flashing and Sheet Metal Rehabilitation
07 01 60.91 Flashing and Sheet Metal Restoration
07 01 60.92 Flashing and Sheet Metal Preservation
07 01 70 Operation and Maintenance of Roof Specialties and Accessories
07 01 80 Maintenance of Fire and Smoke Protection
07 01 90 Maintenance of Joint Protection
07 01 90.71 Joint Sealant Rehabilitation
07 01 90.81 Joint Sealant Replacement
07 03 00 Conservation Treatment for Period Roofing
07 03 30 Conservation Treatment for Period Steep Slope Roofing
07 03 30.13 Conservation Treatment for Period Canvas Roofing
07 03 30.16 Conservation Treatment for Period Board Roofing
07 03 31 Conservation Treatment for Period Shingles and Shakes
07 03 31.16 Conservation Treatment for Period Metal Shingles
07 03 31.26 Conservation Treatment for Period Slate Shingles
07 03 31.29 Conservation Treatment for Period Wood Shingles and Shakes
07 03 32 Conservation Treatment for Period Roof Tiles
07 03 32.13 Conservation Treatment for Period Clay Roof Tiles
07 03 32.16 Conservation Treatment for Period Concrete Roof Tiles
07 03 32.19 Conservation Treatment for Period Metal Roof Tiles
07 03 33 Conservation Treatment for Period Natural Roof Coverings
07 03 33.13 Conservation Treatment for Period Sod Roofing
07 03 40 Conservation Treatment for Period Roofing and Siding Panels
07 03 41 Conservative Treatment for Period Roof Panels
07 03 41.13 Conservation Treatment for Period Metal Roof Panels
07 03 41.23 Conservation Treatment for Period Wood Roof Panels
07 03 46 Conservation Treatment for Period Wood Siding
07 03 60 Conservation Treatment of Period Flashing and Sheet Metal
07 03 61 Conservation Treatment for Period Sheet Metal Roofing
07 03 61.13 Conservation Treatment for Period Standing Seam Sheet Metal Roofing
07 03 61.16 Conservation Treatment for Period Batten Seam Sheet Metal Roofing
07 03 61.19 Conservation Treatment for Period Flat Seam Sheet Metal Roofing
07 05 00 Common Work Results for Thermal and Moisture Protection
07 05 05 Selective Demolition for Thermal and Moisture Protection
07 05 43 Cladding Support Systems
07 05 53 Fire and Smoke Assembly Identification
07 06 00 Schedules for Thermal and Moisture Protection
07 06 10 Schedules for Dampproofing and Waterproofing
07 06 20 Schedules for Thermal Protection
07 06 30 Schedules for Steep Slope Roofing
07 06 40 Schedules for Roofing and Siding Panels
07 06 50 Schedules for Membrane Roofing
07 06 60 Schedules for Flashing and Sheet Metal
07 06 70 Schedules for Roof Specialties and Accessories
07 06 80 Schedules for Fire and Smoke Protection
07 06 80.13 Fireproofing Schedule
07 06 80.16 Firestopping Schedule
07 06 90 Schedules for Joint Protection
07 06 90.13 Joint Sealant Schedule
07 08 00 Commissioning of Thermal and Moisture Protection
07 10 00 Dampproofing and Waterproofing
07 11 00 Dampproofing
07 11 13 Bituminous Dampproofing
07 11 16 Cementitious Dampproofing
07 11 19 Sheet Dampproofing
07 12 00 Built-Up Bituminous Waterproofing
07 12 13 Built-Up Asphalt Waterproofing
07 12 16 Built-Up Coal Tar Waterproofing
07 13 00 Sheet Waterproofing
07 13 13 Bituminous Sheet Waterproofing
07 13 26 Self-Adhering Sheet Waterproofing
07 13 52 Modified Bituminous Sheet Waterproofing
07 13 53 Elastomeric Sheet Waterproofing
07 13 54 Thermoplastic Sheet Waterproofing
07 14 00 Fluid-Applied Waterproofing
07 14 13 Hot Fluid-Applied Rubberized Asphalt Waterproofing
07 14 14 Hot Fluid-Applied Polyurea Waterproofing
07 14 16 Cold Fluid-Applied Waterproofing
07 15 00 Sheet Metal Waterproofing
07 15 13 Sheet Lead Waterproofing
07 16 00 Cementitious and Reactive Waterproofing
07 16 13 Polymer Modified Cement Waterproofing
07 16 16 Crystalline Waterproofing
07 16 19 Metal Oxide Waterproofing
07 17 00 Bentonite Waterproofing
07 17 13 Bentonite Panel Waterproofing
07 17 16 Bentonite Composite Sheet Waterproofing
07 18 00 Traffic Coatings
07 18 13 Pedestrian Traffic Coatings
07 18 16 Vehicular Traffic Coatings
07 19 00 Water Repellents
07 19 13 Acrylic Water Repellents
07 19 16 Silane Water Repellents
07 19 19 Silicone Water Repellents
07 19 23 Siloxane Water Repellents
07 19 26 Stearate Water Repellents
07 19 29 Penetrating Polyester Water Repellents
07 20 00 Thermal Protection
07 21 00 Thermal Insulation
07 21 13 Board Insulation
07 21 13.13 Foam Board Insulation
07 21 13.16 Fibrous Board Insulation
07 21 13.19 Mineral Board Insulation
07 21 16 Blanket Insulation
07 21 19 Foamed-In-Place Insulation
07 21 23 Loose-Fill Insulation
07 21 26 Blown Insulation
07 21 29 Sprayed Insulation
07 21 53 Reflective Insulation
07 22 00 Roof and Deck Insulation
07 22 13 Asphaltic Perlite Concrete Deck
07 22 16 Roof Board Insulation
07 24 00 Exterior Insulation and Finish Systems
07 24 13 Polymer-Based Exterior Insulation and Finish System
07 24 16 Polymer-Modified Exterior Insulation and Finish System
07 24 19 Water-Drainage Exterior Insulation and Finish System
07 24 23 Direct-Applied Finish Systems
07 25 00 Weather Barriers
07 26 00 Vapor Retarders
07 26 13 Above-Grade Vapor Retarders
07 26 16 Below-Grade Vapor Retarders
07 26 23 Below-Grade Gas Retarders
07 27 00 Air Barriers
07 27 13 Modified Bituminous Sheet Air Barriers
07 27 16 Sheet Metal Membrane Air Barriers
07 27 19 Plastic Sheet Air Barriers
07 27 23 Board Product Air Barriers
07 27 26 Fluid-Applied Membrane Air Barriers
07 27 36 Sprayed Foam Air Barrier
07 30 00 Steep Slope Roofing
07 30 91 Canvas Roofing
07 31 00 Shingles and Shakes
07 31 13 Asphalt Shingles
07 31 13.13 Fiberglass-Reinforced Asphalt Shingles
07 31 16 Metal Shingles
07 31 19 Mineral-Fiber Cement Shingles
07 31 23 Porcelain Enamel Shingles
07 31 26 Slate Shingles
07 31 29 Wood Shingles and Shakes
07 31 29.13 Wood Shingles
07 31 29.16 Wood Shakes
07 31 33 Composite Rubber Shingles
07 31 53 Plastic Shakes
07 32 00 Roof Tiles
07 32 13 Clay Roof Tiles
07 32 14 Ceramic and Porcelain Roof Tiles
07 32 16 Concrete Roof Tiles
07 32 19 Metal Roof Tiles
07 32 23 Mineral-Fiber Cement Roof Tiles
07 32 26 Plastic Roof Tiles
07 32 29 Rubber Tiles/Panels
07 33 00 Natural Roof Coverings
07 33 13 Sod Roofing
07 33 16 Thatched Roofing
07 33 63 Vegetated Steep-Slope Roofing
07 40 00 Roofing and Siding Panels
07 41 00 Roof Panels
07 41 13 Metal Roof Panels
07 41 16 Insulated Metal Roof Panels
07 41 23 Wood Roof Panels
07 41 33 Plastic Roof Panels
07 41 43 Composite Roof Panels
07 41 63 Fabricated Roof Panel Assemblies
07 42 00 Wall Panels
07 42 13 Metal Wall Panels
07 42 13.13 Formed Metal Wall Panels
07 42 13.16 Metal Plate Wall Panels
07 42 13.19 Insulated Metal Wall Panels
07 42 13.23 Metal Composite Material Wall Panels
07 42 23 Wood Wall Panels
07 42 26 Tile Wall Panels
07 42 29 Terra Cotta Wall Panels
07 42 33 Plastic Wall Panels
07 42 43 Composite Wall Panels
07 42 46 Cementitious Wall Panels
07 42 63 Fabricated Wall Panel Assemblies
07 42 93 Soffit Panels
07 44 00 Faced Panels
07 44 13 Aggregate Coated Panels
07 44 16 Porcelain Enameled Faced Panels
07 44 19 Tile-Faced Panels
07 44 23 Ceramic-Tile-Faced Panels
07 44 33 Metal Faced Panels
07 44 53 Glass-Fiber-Reinforced Cementitious Panels
07 44 56 Mineral-Fiber-Reinforced Cementitious Panels
07 44 63 Fabricated Faced Panel Assemblies
07 46 00 Siding
07 46 16 Aluminum Siding
07 46 19 Steel Siding
07 46 21 Zinc Siding
07 46 23 Wood Siding
07 46 24 Wood Shingle and Shake Siding
07 46 24.13 Wood Shingle Siding
07 46 24.16 Wood Shake Siding
07 46 26 Hardboard Siding
07 46 29 Plywood Siding
07 46 33 Plastic Siding
07 46 43 Composition Siding
07 46 46 Fiber-Cement Siding
07 46 63 Fabricated Panel Assemblies with Siding
07 50 00 Membrane Roofing
07 51 00 Built-Up Bituminous Roofing
07 51 13 Built-Up Asphalt Roofing
07 51 13.13 Cold-Applied Built-Up Asphalt Roofing
07 51 16 Built-Up Coal Tar Roofing
07 51 23 Glass-Fiber-Reinforced Asphalt Emulsion Roofing
07 52 00 Modified Bituminous Membrane Roofing
07 52 13 Atactic-Polypropylene-Modified Bituminous Membrane Roofing
07 52 13.11 Cold Adhesive Applied Atactic-Polypropylene-Modified Bituminous Membrane Roofing
07 52 13.13 Torch-Applied Atactic-Polypropylene-Modified Bituminous Membrane Roofing
07 52 13.14 Mechanically Fastened Atactic-Polypropylene-Modified Bituminous Membrane Roofing
07 52 16 Styrene-Butadiene-Styrene Modified Bituminous Membrane Roofing
07 52 16.11 Cold Adhesive Styrene-Butadiene-Styrene Modified Bituminous Membrane Roofing
07 52 16.12 Hot-Mopped Styrene-Butadiene-Styrene Modified Bituminous Membrane Roofing
07 52 16.13 Torch-Applied Styrene-Butadiene-Styrene Modified Bituminous Membrane Roofing
07 52 16.14 Mechanically Fastened Styrene-Butadiene-Styrene Modified Bituminous Membrane Roofing
07 53 00 Elastomeric Membrane Roofing
07 53 13 Chlorinated-Polyethylene Roofing
07 53 16 Chlorosulfonate-Polyethylene Roofing
07 53 23 Ethylene-Propylene-Diene-Monomer Roofing
07 53 29 Polyisobutylene Roofing
07 54 00 Thermoplastic Membrane Roofing
07 54 13 Copolymer-Alloy Roofing
07 54 16 Ketone Ethylene Ester Roofing
07 54 19 Polyvinyl-Chloride Roofing
07 54 23 Thermoplastic-Polyolefin Roofing
07 54 26 Nitrile-Butadiene-Polymer Roofing
07 55 00 Protected Membrane Roofing
07 55 51 Built-Up Bituminous Protected Membrane Roofing
07 55 52 Modified Bituminous Protected Membrane Roofing
07 55 53 Elastomeric Protected Membrane Roofing
07 55 54 Thermoplastic Protected Membrane Roofing
07 55 56 Fluid-Applied Protected Membrane Roofing
07 55 56.13 Hot-Applied Rubberized Asphalt Protected Membrane Roofing
07 55 63 Vegetated Protected Membrane Roofing
07 56 00 Fluid-Applied Roofing
07 57 00 Coated Foamed Roofing
07 57 13 Sprayed Polyurethane Foam Roofing
07 58 00 Roll Roofing
07 60 00 Flashing and Sheet Metal
07 61 00 Sheet Metal Roofing
07 61 13 Standing Seam Sheet Metal Roofing
07 61 16 Batten Seam Sheet Metal Roofing
07 61 19 Flat Seam Sheet Metal Roofing
07 62 00 Sheet Metal Flashing and Trim
07 63 00 Sheet Metal Roofing Specialties
07 64 00 Sheet Metal Wall Cladding
07 64 13 Standing Seam Sheet Metal Wall Cladding
07 64 16 Batten Seam Sheet Metal Wall Cladding
07 64 19 Flat Seam Sheet Metal Wall Cladding
07 65 00 Flexible Flashing
07 65 13 Laminated Sheet Flashing
07 65 16 Modified Bituminous Sheet Flashing
07 65 19 Plastic Sheet Flashing
07 65 23 Rubber Sheet Flashing
07 65 26 Self-Adhering Sheet Flashing
07 70 00 Roof and Wall Specialties and Accessories
07 71 00 Roof Specialties
07 71 13 Manufactured Copings
07 71 16 Manufactured Counterflashing Systems
07 71 19 Manufactured Gravel Stops and Fasciae
07 71 23 Manufactured Gutters and Downspouts
07 71 23.13 Gutter Debris Guards
07 71 26 Reglets
07 71 29 Manufactured Roof Expansion Joints
07 71 33 Manufactured Scuppers
07 72 00 Roof Accessories
07 72 13 Manufactured Curbs
07 72 23 Relief Vents
07 72 26 Ridge Vents
07 72 33 Roof Hatches
07 72 36 Smoke Vents
07 72 39 Operable Roof Vents
07 72 43 Roof Walk Boards
07 72 46 Roof Walkways
07 72 53 Snow Guards
07 72 63 Waste Containment Assemblies
07 72 73 Vegetated Roof Systems
07 76 00 Roof Pavers
07 76 13 Roof Ballast Pavers
07 76 16 Roof Decking Pavers
07 77 00 Wall Specialties
07 80 00 Fire and Smoke Protection
07 81 00 Applied Fireproofing
07 81 13 Cement Aggregate Fireproofing
07 81 16 Cementitious Fireproofing
07 81 19 Foamed Magnesium-Oxychloride Fireproofing
07 81 23 Intumescent Fireproofing
07 81 26 Magnesium Cement Fireproofing
07 81 29 Mineral-Fiber Cementitious Fireproofing
07 81 33 Mineral-Fiber Fireproofing
07 82 00 Board Fireproofing
07 82 13 Calcium-Silicate Board Fireproofing
07 82 16 Slag-Fiber Board Fireproofing
07 84 00 Firestopping
07 84 13 Penetration Firestopping
07 84 13.13 Penetration Firestopping Mortars
07 84 13.16 Penetration Firestopping Devices
07 84 43 Joint Firestopping
07 84 53 Building Perimeter Firestopping
07 86 00 Smoke Seals
07 87 00 Smoke Containment Barriers
07 90 00 Joint Protection
07 91 00 Preformed Joint Seals
07 91 13 Compression Seals
07 91 16 Joint Gaskets
07 91 23 Backer Rods
07 91 26 Joint Fillers
07 92 00 Joint Sealants
07 92 13 Elastomeric Joint Sealants
07 92 16 Rigid Joint Sealants
07 92 19 Acoustical Joint Sealants
07 95 00 Expansion Control
07 95 13 Expansion Joint Cover Assemblies
07 95 13.13 Interior Expansion Joint Cover Assemblies
07 95 13.16 Exterior Expansion Joint Cover Assemblies
07 95 13.19 Parking Deck Expansion Joint Cover Assemblies
07 95 53 Joint Slide Bearings
07 95 63 Bridge Expansion Joint Cover Assemblies
08 00 00 Openings
08 01 00 Operation and Maintenance of Openings
08 01 10 Operation and Maintenance of Doors and Frames
08 01 11 Operation and Maintenance of Metal Doors and Frames
08 01 14 Operation and Maintenance of Wood Doors
08 01 15 Operation and Maintenance of Plastic Doors
08 01 16 Operation and Maintenance of Composite Doors
08 01 17 Operation and Maintenance of Integrated Door Opening Assemblies
08 01 30 Operation and Maintenance of Specialty Doors and Frames
08 01 32 Operation and Maintenance of Sliding Glass Doors
08 01 33 Operation and Maintenance of Coiling Doors and Grilles
08 01 34 Operation and Maintenance of Special Function Doors
08 01 35 Operation and Maintenance of Folding Doors and Grilles
08 01 36 Operation and Maintenance of Panel Doors
08 01 39 Operation and Maintenance of Traffic Doors
08 01 40 Operation and Maintenance of Entrances, Storefronts, and Curtain Walls
08 01 41 Operation and Maintenance of Entrances
08 01 42 Operation and Maintenance of Storefronts
08 01 44 Operation and Maintenance of Curtain Walls
08 01 50 Operation and Maintenance of Windows
08 01 51 Operation and Maintenance of Metal Windows
08 01 52 Operation and Maintenance of Wood Windows
08 01 52.61 Wood Window Repairs
08 01 52.71 Wood Window Rehabilitation
08 01 52.81 Wood Window Replacement
08 01 52.91 Wood Window Restoration
08 01 52.93 Historic Treatment of Wood Windows
08 01 53 Operation and Maintenance of Plastic Windows
08 01 54 Operation and Maintenance of Composite Windows
08 01 56 Operation and Maintenance of Special Function Windows
08 01 60 Operation and Maintenance of Skylights and Roof Windows
08 01 61 Operation and Maintenance of Roof Windows
08 01 62 Operation and Maintenance of Unit Skylights
08 01 63 Operation and Maintenance of Metal-Framed Skylights
08 01 64 Operation and Maintenance of Plastic-Framed Skylights
08 01 70 Operation and Maintenance of Hardware
08 01 71 Operation and Maintenance of Door Hardware
08 01 74 Operation and Maintenance of Access Control Hardware
08 01 75 Operation and Maintenance of Window Hardware
08 01 80 Maintenance of Glazing
08 01 81 Maintenance of Glass Glazing
08 01 84 Maintenance of Plastic Glazing
08 01 88 Maintenance of Special Function Glazing
08 01 90 Operation and Maintenance of Louvers and Vents
08 01 91 Operation and Maintenance of Louvers
08 01 92 Operation and Maintenance of Louvered Equipment Enclosures
08 01 95 Operation and Maintenance of Vents
08 03 00 Conservation Treatment for Period Openings
08 03 11 Conservation Treatment for Period Metal Doors and Frames
08 03 11.23 Conservation Treatment for Period Bronze Doors and Frames
08 03 14 Conservation Treatment for Period Wood Doors
08 03 14.23 Conservation Treatment for Period Metal-Faced Wood Doors
08 03 14.33 Conservation Treatment for Period Stile and Rail Wood Doors
08 03 30 Conservation Treatment for Period Specialty Doors and Frames
08 03 34 Conservation Treatment for Period Special Function Doors
08 03 34.59 Conservation Treatment for Period Vault Doors
08 03 50 Conservation Treatment for Period Windows
08 03 51 Conservation Treatment for Period Metal Windows
08 03 51.16 Conservation Treatment for Period Bronze Windows
08 03 51.23 Conservation Treatment for Period Steel Windows
08 03 52 Conservation Treatment for Period Wood Windows
08 03 70 Conservation Treatment for Period Hardware
08 03 71 Conservation Treatment for Period Door Hardware
08 03 75 Conservation Treatment for Period Window Hardware
08 03 90 Conservation Treatment for Period Louvers and Vents
08 03 91 Conservation Treatment for Period Louvers
08 03 95 Conservation Treatment for Period Vents
08 05 00 Common Work Results for Openings
08 05 05 Selective Demolition for Openings
08 06 00 Schedules for Openings
08 06 10 Door Schedule
08 06 10.13 Door Type Schedule
08 06 10.16 Frame Type Schedule
08 06 40 Schedules for Entrances, Storefronts, and Curtain Walls
08 06 41 Entrance Schedule
08 06 42 Storefront Schedule
08 06 50 Window Schedule
08 06 60 Skylight Schedule
08 06 70 Hardware Schedule
08 06 71 Door Hardware Schedule
08 06 80 Glazing Schedule
08 06 90 Louver and Vent Schedule
08 08 00 Commissioning of Openings
08 10 00 Doors and Frames
08 11 00 Metal Doors and Frames
08 11 13 Hollow Metal Doors and Frames
08 11 13.13 Standard Hollow Metal Doors and Frames
08 11 13.16 Custom Hollow Metal Doors and Frames
08 11 16 Aluminum Doors and Frames
08 11 19 Stainless-Steel Doors and Frames
08 11 23 Bronze Doors and Frames
08 11 63 Metal Screen and Storm Doors and Frames
08 11 63.13 Steel Screen and Storm Doors and Frames
08 11 63.23 Aluminum Screen and Storm Doors and Frames
08 11 66 Metal Screen Doors and Frames
08 11 66.13 Steel Screen Doors and Frames
08 11 66.23 Aluminum Screen Doors and Frames
08 11 69 Metal Storm Doors and Frames
08 11 69.13 Steel Storm Doors and Frames
08 11 69.23 Aluminum Storm Doors and Frames
08 11 73 Sliding Metal Fire Doors
08 11 74 Sliding Metal Grilles
08 12 00 Metal Frames
08 12 13 Hollow Metal Frames
08 12 13.13 Standard Hollow Metal Frames
08 12 13.53 Custom Hollow Metal Frames
08 12 16 Aluminum Frames
08 12 19 Stainless-Steel Frames
08 12 23 Bronze Frames
08 13 00 Metal Doors
08 13 13 Hollow Metal Doors
08 13 13.13 Standard Hollow Metal Doors
08 13 13.53 Custom Hollow Metal Doors
08 13 16 Aluminum Doors
08 13 16.13 Aluminum Terrace Doors
08 13 19 Stainless-Steel Doors
08 13 23 Bronze Doors
08 13 73 Sliding Metal Doors
08 13 76 Bifolding Metal Doors
08 14 00 Wood Doors
08 14 13 Carved Wood Doors
08 14 16 Flush Wood Doors
08 14 23 Clad Wood Doors
08 14 23.13 Metal-Faced Wood Doors
08 14 23.16 Plastic-Laminate-Faced Wood Doors
08 14 23.17 Plastic-Faced Wood Doors
08 14 23.19 Molded-Hardboard-Faced Wood Doors
08 14 29 Prefinished Wood Doors
08 14 33 Stile and Rail Wood Doors
08 14 33.13 Wood Terrace Doors
08 14 66 Wood Screen Doors
08 14 69 Wood Storm Doors
08 14 73 Sliding Wood Doors
08 14 76 Bifolding Wood Doors
08 15 00 Plastic Doors
08 15 13 Laminated Plastic Doors
08 15 16 Solid Plastic Doors
08 15 66 Plastic Screen Doors
08 15 69 Plastic Storm Doors
08 15 73 Sliding Plastic Doors
08 15 76 Bifolding Plastic Doors
08 16 00 Composite Doors
08 16 13 Fiberglass Doors
08 16 73 Sliding Composite Doors
08 16 76 Bifolding Composite Doors
08 17 00 Integrated Door Opening Assemblies
08 17 13 Integrated Metal Door Opening Assemblies
08 17 23 Integrated Wood Door Opening Assemblies
08 17 33 Integrated Plastic Door Opening Assemblies
08 17 43 Integrated Composite Door Opening Assemblies
08 30 00 Specialty Doors and Frames
08 31 00 Access Doors and Panels
08 31 13 Access Doors and Frames
08 31 13.53 Security Access Doors and Frames
08 31 16 Access Panels and Frames
08 32 00 Sliding Glass Doors
08 32 13 Sliding Aluminum-Framed Glass Doors
08 32 16 Sliding Plastic-Framed Glass Doors
08 32 19 Sliding Wood-Framed Glass Doors
08 33 00 Coiling Doors and Grilles
08 33 13 Coiling Counter Doors
08 33 16 Coiling Counter Grilles
08 33 23 Overhead Coiling Doors
08 33 23.13 Overhead Rapid Coiling Doors
08 33 26 Overhead Coiling Grilles
08 33 33 Side Coiling Doors
08 33 36 Side Coiling Grilles
08 33 43 Overhead Coiling Smoke Curtains
08 33 44 Overhead Coiling Fire Curtains
08 34 00 Special Function Doors
08 34 13 Cold Storage Doors
08 34 16 Hangar Doors
08 34 19 Industrial Doors
08 34 33 Lightproof Doors
08 34 36 Darkroom Doors
08 34 46 Radio-Frequency-Interference Shielding Doors
08 34 49 Radiation Shielding Doors and Frames
08 34 49.13 Neutron Shielding Doors and Frames
08 34 53 Security Doors and Frames
08 34 56 Security Gates
08 34 58 File Room Doors and Frames
08 34 59 Vault Doors and Day Gates
08 34 73 Sound Control Door Assemblies
08 34 73.13 Metal Sound Control Door Assemblies
08 34 73.16 Wood Sound Control Door Assemblies
08 35 00 Folding Doors and Grilles
08 35 13 Folding Doors
08 35 13.13 Accordion Folding Doors
08 35 13.23 Accordion Folding Fire Doors
08 35 13.33 Panel Folding Doors
08 35 16 Folding Grilles
08 35 16.13 Accordion Folding Grilles
08 36 00 Panel Doors
08 36 13 Sectional Doors
08 36 16 Single-Panel Doors
08 36 19 Multi-Leaf Vertical Lift Doors
08 36 23 Telescoping Vertical Lift Doors
08 38 00 Traffic Doors
08 38 13 Flexible Strip Doors
08 38 16 Flexible Traffic Doors
08 38 19 Rigid Traffic Doors
08 39 00 Pressure-Resistant Doors
08 39 13 Airtight Doors
08 39 19 Watertight Doors
08 39 53 Blast-Resistant Doors
08 40 00 Entrances, Storefronts, and Curtain Walls
08 41 00 Entrances and Storefronts
08 41 13 Aluminum-Framed Entrances and Storefronts
08 41 13.13 Fire-Rated Aluminum-Framed Entrances and Storefronts
08 41 16 Bronze-Framed Entrances and Storefronts
08 41 19 Stainless-Steel-Framed Entrances and Storefronts
08 41 23 Steel-Framed Entrances and Storefronts
08 41 26 All-Glass Entrances and Storefronts
08 41 26.13 Point Supported All-Glass Storefronts
08 42 00 Entrances
08 42 13 Aluminum-Framed Entrances
08 42 26 All-Glass Entrances
08 42 29 Automatic Entrances
08 42 29.13 Folding Automatic Entrances
08 42 29.23 Sliding Automatic Entrances
08 42 29.33 Swinging Automatic Entrances
08 42 33 Revolving Door Entrances
08 42 33.13 Security Revolving Door Entrances
08 42 36 Balanced Door Entrances
08 42 39 Pressure-Resistant Entrances
08 42 43 Intensive Care Unit/Critical Care Unit Entrances
08 43 00 Storefronts
08 43 11 Timber-Framed Storefronts
08 43 13 Aluminum-Framed Storefronts
08 43 13.13 Fire-Rated Aluminum Storefronts
08 43 16 Bronze-Framed Storefronts
08 43 19 Stainless-Steel-Framed Storefronts
08 43 23 Steel-Framed Storefronts
08 43 26 All-Glass Storefronts
08 43 27 Channel Glass Storefronts
08 43 29 Sliding Storefronts
08 44 00 Curtain Wall and Glazed Assemblies
08 44 11 Glazed Timber Curtain Walls
08 44 12 Glazed Composite Curtain Wall
08 44 12.13 Glazed Fiberglass Curtain Wall
08 44 13 Glazed Aluminum Curtain Walls
08 44 16 Glazed Bronze Curtain Walls
08 44 18 Glazed Steel Curtain Walls
08 44 19 Glazed Stainless-Steel Curtain Walls
08 44 23 Structural Sealant Glazed Curtain Walls
08 44 26 Structural Glass Curtain Walls
08 44 26.13 Glass Framed Point Supported Glass Curtain Walls
08 44 26.16 Metal Framed Point Supported Glass Curtain Walls
08 44 26.23 Cable Framed Point Supported Glass Curtain Walls
08 44 33 Sloped Glazing Assemblies
08 45 00 Translucent Wall and Roof Assemblies
08 45 13 Structured-Polycarbonate-Panel Assemblies
08 45 23 Fiberglass-Sandwich-Panel Assemblies
08 46 00 Window Wall Assemblies
08 50 00 Windows
08 51 00 Metal Windows
08 51 13 Aluminum Windows
08 51 16 Bronze Windows
08 51 19 Stainless-Steel Windows
08 51 23 Steel Windows
08 51 23.13 Hot-Rolled Steel Windows
08 51 23.23 Cold-Rolled Steel Windows
08 51 66 Metal Window Screens
08 51 69 Metal Storm Windows
08 52 00 Wood Windows
08 52 13 Metal-Clad Wood Windows
08 52 16 Plastic-Clad Wood Windows
08 52 66 Wood Window Screens
08 52 69 Wood Storm Windows
08 53 00 Plastic Windows
08 53 13 Vinyl Windows
08 53 66 Vinyl Window Screens
08 53 69 Vinyl Storm Windows
08 54 00 Composite Windows
08 54 13 Fiberglass Windows
08 54 66 Fiberglass Window Screens
08 54 69 Fiberglass Storm Windows
08 55 00 Pressure-Resistant Windows
08 55 13 Tornado-Resistant Windows
08 55 23 Blast-Resistant Windows
08 56 00 Special Function Windows
08 56 19 Pass Windows
08 56 46 Radio-Frequency-Interference Shielding Windows
08 56 49 Radiation Shielding Windows
08 56 53 Security Windows
08 56 56 Security Window Screens
08 56 59 Service and Teller Window Units
08 56 73 Sound Control Windows
08 56 88 Interior Insulating Windows
08 60 00 Roof Windows and Skylights
08 61 00 Roof Windows
08 61 13 Metal Roof Windows
08 61 16 Wood Roof Windows
08 62 00 Unit Skylights
08 62 13 Domed Unit Skylights
08 62 16 Pyramidal Unit Skylights
08 62 19 Vaulted Unit Skylights
08 62 23 Tubular Skylights
08 63 00 Metal-Framed Skylights
08 63 13 Domed Metal-Framed Skylights
08 63 16 Pyramidal Metal-Framed Skylights
08 63 19 Vaulted Metal-Framed Skylights
08 63 23 Ridge Metal-Framed Skylights
08 63 53 Motorized Metal-Framed Skylights
08 64 00 Plastic-Framed Skylights
08 65 00 Glazed Canopies
08 65 13 Suspended Glazed Canopies
08 67 00 Skylight Protection and Screens
08 70 00 Hardware
08 71 00 Door Hardware
08 71 13 Automatic Door Operators
08 71 53 Security Door Hardware
08 75 00 Window Hardware
08 75 13 Automatic Window Equipment
08 75 16 Window Operators
08 78 00 Special Function Hardware
08 79 00 Hardware Accessories
08 79 13 Key Storage Equipment
08 80 00 Glazing
08 81 00 Glass Glazing
08 81 13 Decorative Glass Glazing
08 81 23 Exterior Glass Glazing
08 81 26 Interior Glass Glazing
08 83 00 Mirrors
08 83 13 Mirrored Glass Glazing
08 83 16 Mirrored Plastic Glazing
08 84 00 Plastic Glazing
08 84 13 Decorative Plastic Glazing
08 85 00 Glazing Accessories
08 87 00 Glazing Surface Films
08 87 13 Solar Control Films
08 87 23 Safety and Security Films
08 87 23.13 Safety Films
08 87 23.16 Security Films
08 87 26 Bird Control Film
08 87 33 Decorative Films
08 88 00 Special Function Glazing
08 88 13 Fire-Resistant Glazing
08 88 19 Hurricane-Resistant Glazing
08 88 23 Cable Suspended Glazing
08 88 33 Transparent Mirrored Glazing
08 88 36 Switchable Glass
08 88 36.16 Electronically Controlled Switchable Glass
08 88 39 Pressure-Resistant Glazing
08 88 49 Radiation-Resistant Glazing
08 88 53 Security Glazing
08 88 56 Ballistics-Resistant Glazing
08 90 00 Louvers and Vents
08 91 00 Louvers
08 91 13 Motorized Wall Louvers
08 91 16 Operable Wall Louvers
08 91 19 Fixed Louvers
08 91 26 Door Louvers
08 92 00 Louvered Equipment Enclosures
08 95 00 Vents
08 95 13 Soffit Vents
08 95 16 Wall Vents
08 95 33 Explosion Vents
08 95 43 Flood Vents
09 00 00 Finishes
09 01 00 Maintenance of Finishes
09 01 20 Maintenance of Plaster and Gypsum Board
09 01 20.91 Plaster Restoration
09 01 30 Maintenance of Tiling
09 01 30.91 Tile Restoration
09 01 50 Maintenance of Ceilings
09 01 50.91 Ceiling Restoration
09 01 60 Maintenance of Flooring
09 01 60.91 Flooring Restoration
09 01 70 Maintenance of Wall Finishes
09 01 70.91 Wall Finish Restoration
09 01 80 Maintenance of Acoustic Treatment
09 01 90 Maintenance of Painting and Coating
09 01 90.51 Paint Cleaning
09 01 90.52 Maintenance Repainting
09 01 90.53 Maintenance Coatings
09 01 90.61 Repainting
09 01 90.91 Paint Restoration
09 01 90.92 Coating Restoration
09 01 90.93 Paint Preservation
09 03 00 Conservation Treatment of Period Finishes
09 03 21 Conservation Treatment for Period Plaster Assemblies
09 03 25 Conservation Treatment for Period Plastering
09 03 25.23 Conservation Treatment for Period Lime-Based Plaster
09 03 30 Conservation Treatment for Period Tile
09 03 50 Conservation Treatment for Period Ceilings
09 03 51 Conservation Treatment for Period Suspended Ceilings
09 03 56 Conservation Treatment for Textured Ceilings
09 03 56.16 Conservation Treatment for Period Metal-Panel Textured Ceilings
09 03 60 Conservation Treatment for Period Flooring
09 03 63 Conservation Treatment for Period Masonry Flooring
09 03 63.13 Conservation Treatment for Period Brick Flooring
09 03 63.40 Conservation Treatment for Period Stone Flooring
09 03 64 Conservation Treatment for Period Wood Flooring
09 03 64.29 Conservation Treatment for Period Wood Strip and Plank Flooring
09 03 65 Conservation Treatment for Period Resilient Flooring
09 03 65.16 Conservation Treatment for Period Resilient Sheet Flooring
09 03 66 Conservation Treatment for Period Terrazzo Flooring
09 03 70 Conservation Treatment for Period Wall Finishes
09 03 72 Conservation Treatment for Period Wall Coverings
09 03 90 Conservation Treatment for Period Painting and Coating
09 03 91 Conservation Treatment for Period Painted Surfaces
09 03 91.13 Conservation Treatment for Period Exterior Painting
09 03 91.23 Conservation Treatment for Period Interior Painting
09 05 00 Common Work Results for Finishes
09 05 05 Selective Demolition for Finishes
09 05 13 Common Finishes
09 05 61 Common Work Results for Flooring Preparation
09 05 61.13 Moisture Vapor Emission Control
09 05 71 Acoustic Underlayment
09 06 00 Schedules for Finishes
09 06 00.13 Room Finish Schedule
09 06 20 Schedules for Plaster and Gypsum Board
09 06 30 Schedules for Tiling
09 06 50 Schedules for Ceilings
09 06 60 Schedules for Flooring
09 06 70 Schedules for Wall Finishes
09 06 80 Schedules for Acoustical Treatment
09 06 90 Schedules for Painting and Coating
09 06 90.13 Paint Schedule
09 08 00 Commissioning of Finishes
09 20 00 Plaster and Gypsum Board
09 21 00 Plaster and Gypsum Board Assemblies
09 21 13 Plaster Assemblies
09 21 16 Gypsum Board Assemblies
09 21 16.23 Gypsum Board Shaft Wall Assemblies
09 21 16.33 Gypsum Board Area Separation Wall Assemblies
09 22 00 Supports for Plaster and Gypsum Board
09 22 13 Metal Furring
09 22 13.13 Metal Channel Furring
09 22 13.23 Resilient Channel Furring
09 22 16 Non-Structural Metal Framing
09 22 16.13 Non-Structural Metal Stud Framing
09 22 26 Suspension Systems
09 22 26.23 Metal Suspension Systems
09 22 26.33 Plastic Suspension Systems
09 22 36 Lath
09 22 36.13 Gypsum Lath
09 22 36.23 Metal Lath
09 22 39 Veneer Plaster Base
09 23 00 Gypsum Plastering
09 23 13 Acoustical Gypsum Plastering
09 23 82 Fireproof Gypsum Plastering
09 24 00 Cement Plastering
09 24 13 Adobe Finish
09 24 23 Cement Stucco
09 24 33 Cement Parging
09 25 00 Other Plastering
09 25 13 Acrylic Plastering
09 25 13.13 Acrylic Plaster Finish
09 25 23 Lime Based Plastering
09 25 26 Natural Clay Plastering
09 26 00 Veneer Plastering
09 26 13 Gypsum Veneer Plastering
09 27 00 Plaster Fabrications
09 27 13 Glass-Fiber-Reinforced Gypsum Fabrications
09 27 23 Simulated Plaster Fabrications
09 28 00 Backing Boards and Underlayments
09 28 13 Cementitious Backing Boards
09 28 16 Glass-Mat Faced Gypsum Backing Boards
09 28 19 Fibered Gypsum Backing Boards
09 29 00 Gypsum Board
09 29 82 Gypsum Board Fireproofing
09 30 00 Tiling
09 30 13 Ceramic Tiling
09 30 16 Quarry Tiling
09 30 19 Paver Tiling
09 30 23 Glass Mosaic Tiling
09 30 26 Plastic Tiling
09 30 29 Metal Tiling
09 30 33 Stone Tiling
09 30 36 Concrete Tiling
09 30 39 Brick Tiling
09 31 00 Thin-Set Tiling
09 31 13 Thin-Set Ceramic Tiling
09 31 16 Thin-Set Quarry Tiling
09 31 19 Thin-Set Paver Tiling
09 31 23 Thin-Set Glass Mosaic Tiling
09 31 26 Thin-Set Plastic Tiling
09 31 29 Thin-Set Metal Tiling
09 31 33 Thin-Set Stone Tiling
09 31 36 Thin-Set Concrete Tiling
09 32 00 Mortar-Bed Tiling
09 32 13 Mortar-Bed Ceramic Tiling
09 32 16 Mortar-Bed Quarry Tiling
09 32 19 Mortar-Bed Paver Tiling
09 32 23 Mortar-Bed Glass Mosaic Tiling
09 32 26 Mortar-Bed Plastic Tiling
09 32 29 Mortar-Bed Metal Tiling
09 32 33 Mortar-Bed Stone Tiling
09 32 36 Mortar-Bed Concrete Tiling
09 33 00 Conductive Tiling
09 33 13 Conductive Ceramic Tiling
09 33 16 Conductive Quarry Tiling
09 33 19 Conductive Paver Tiling
09 33 23 Conductive Glass Mosaic Tiling
09 33 26 Conductive Plastic Tiling
09 33 29 Conductive Metal Tiling
09 33 33 Conductive Stone Tiling
09 33 36 Conductive Concrete Tiling
09 34 00 Waterproofing-Membrane Tiling
09 34 13 Waterproofing-Membrane Ceramic Tiling
09 34 16 Waterproofing-Membrane Quarry Tiling
09 34 19 Waterproofing-Membrane Paver Tiling
09 34 23 Waterproofing-Membrane Glass Mosaic Tiling
09 34 26 Waterproofing-Membrane Plastic Tiling
09 34 29 Waterproofing-Membrane Metal Tiling
09 34 33 Waterproofing-Membrane Stone Tiling
09 34 36 Waterproofing-Membrane Concrete Tiling
09 35 00 Chemical-Resistant Tiling
09 35 13 Chemical-Resistant Ceramic Tiling
09 35 16 Chemical-Resistant Quarry Tiling
09 35 19 Chemical-Resistant Paver Tiling
09 35 23 Chemical-Resistant Glass Mosaic Tiling
09 35 26 Chemical-Resistant Plastic Tiling
09 35 29 Chemical-Resistant Metal Tiling
09 35 33 Chemical-Resistant Stone Tiling
09 35 36 Chemical-Resistant Concrete Tiling
09 50 00 Ceilings
09 51 00 Acoustical Ceilings
09 51 13 Acoustical Panel Ceilings
09 51 14 Acoustical Fabric-Faced Panel Ceilings
09 51 23 Acoustical Tile Ceilings
09 51 26 Acoustical Wood Ceilings
09 51 33 Acoustical Metal Pan Ceilings
09 51 33.13 Acoustical Snap-in Metal Pan Ceilings
09 51 53 Direct-Applied Acoustical Ceilings
09 53 00 Acoustical Ceiling Suspension Assemblies
09 53 13 Curved Profile Ceiling Suspension Assemblies
09 53 23 Metal Acoustical Ceiling Suspension Assemblies
09 53 33 Plastic Acoustical Ceiling Suspension Assemblies
09 54 00 Specialty Ceilings
09 54 13 Open Metal Mesh Ceilings
09 54 16 Luminous Ceilings
09 54 19 Mirror Panel Ceilings
09 54 23 Linear Metal Ceilings
09 54 26 Suspended Wood Ceilings
09 54 29 Suspended Plastic Ceilings
09 54 33 Decorative Panel Ceilings
09 54 36 Suspended Decorative Grids
09 54 43 Stretched-Fabric Ceiling Systems
09 54 46 Fabric-Wrapped Ceiling Panels
09 54 53 Fiberglass Reinforced Panel Ceilings
09 56 00 Textured Ceilings
09 56 13 Gypsum-Panel Textured Ceilings
09 56 16 Metal-Panel Textured Ceilings
09 57 00 Special Function Ceilings
09 57 53 Security Ceiling Assemblies
09 58 00 Integrated Ceiling Assemblies
09 60 00 Flooring
09 61 00 Flooring Treatment
09 61 13 Slip-Resistant Flooring Treatment
09 61 19 Concrete Floor Staining
09 61 36 Static-Resistant Flooring Treatment
09 62 00 Specialty Flooring
09 62 13 Asphaltic Plank Flooring
09 62 19 Laminate Flooring
09 62 23 Bamboo Flooring
09 62 26 Leather Flooring
09 62 29 Cork Flooring
09 62 35 Acid-Resistant Flooring
09 62 48 Acoustic Flooring
09 62 53 Synthetic Turf Flooring
09 62 63 Metal Flooring
09 62 63.13 Aluminum Flooring
09 62 63.16 Stainless Steel Flooring
09 62 83 Structural Glass Flooring
09 63 00 Masonry Flooring
09 63 13 Brick Flooring
09 63 13.35 Chemical-Resistant Brick Flooring
09 63 40 Stone Flooring
09 63 43 Composition Stone Flooring
09 64 00 Wood Flooring
09 64 16 Wood Block Flooring
09 64 19 Wood Composition Flooring
09 64 23 Wood Parquet Flooring
09 64 23.13 Acrylic-Impregnated Wood Parquet Flooring
09 64 29 Wood Strip and Plank Flooring
09 64 33 Laminated Wood Flooring
09 64 53 Resilient Wood Flooring Assemblies
09 64 66 Wood Athletic Flooring
09 65 00 Resilient Flooring
09 65 13 Resilient Base and Accessories
09 65 13.13 Resilient Base
09 65 13.23 Resilient Stair Treads and Risers
09 65 13.26 Resilient Stair Nosings
09 65 13.33 Resilient Accessories
09 65 13.36 Resilient Carpet Transitions
09 65 16 Resilient Sheet Flooring
09 65 16.23 Vinyl Sheet Flooring
09 65 16.33 Rubber Sheet Flooring
09 65 16.43 PVC-Free Sheet Flooring
09 65 19 Resilient Tile Flooring
09 65 19.19 Vinyl Composition Tile Flooring
09 65 19.23 Vinyl Tile Flooring
09 65 19.33 Rubber Tile Flooring
09 65 19.43 Polyester Composition Tile Flooring
09 65 33 Conductive Resilient Flooring
09 65 36 Static-Control Resilient Flooring
09 65 36.13 Static-Dissipative Resilient Flooring
09 65 36.16 Static-Resistant Resilient Flooring
09 65 43 Linoleum Flooring
09 65 66 Resilient Athletic Flooring
09 66 00 Terrazzo Flooring
09 66 13 Portland Cement Terrazzo Flooring
09 66 13.13 Sand Cushion Terrazzo Flooring
09 66 13.16 Monolithic Terrazzo Flooring
09 66 13.19 Bonded Terrazzo Flooring
09 66 13.23 Palladina Terrazzo Flooring
09 66 13.26 Rustic Terrazzo Flooring
09 66 13.33 Structural Terrazzo Flooring
09 66 16 Terrazzo Floor Tile
09 66 16.13 Portland Cement Terrazzo Floor Tile
09 66 16.16 Plastic-Matrix Terrazzo Floor Tile
09 66 23 Resinous Matrix Terrazzo Flooring
09 66 23.13 Polyacrylate Modified Cementitious Terrazzo Flooring
09 66 23.16 Epoxy-Resin Terrazzo Flooring
09 66 23.19 Polyester-Resin Terrazzo Flooring
09 66 33 Conductive Terrazzo Flooring
09 66 33.13 Conductive Epoxy-Resin Terrazzo
09 66 33.16 Conductive Polyester-Resin Terrazzo Flooring
09 66 33.19 Conductive Plastic-Matrix Terrazzo Flooring
09 67 00 Fluid-Applied Flooring
09 67 13 Elastomeric Liquid Flooring
09 67 13.33 Conductive Elastomeric Liquid Flooring
09 67 16 Epoxy-Marble Chip Flooring
09 67 19 Magnesium-Oxychloride Flooring
09 67 23 Resinous Flooring
09 67 26 Quartz Flooring
09 67 66 Fluid-Applied Athletic Flooring
09 68 00 Carpeting
09 68 13 Tile Carpeting
09 68 16 Sheet Carpeting
09 69 00 Access Flooring
09 69 13 Rigid-Grid Access Flooring
09 69 16 Snap-on Stringer Access Flooring
09 69 19 Stringerless Access Flooring
09 69 33 Low-Profile Fixed Height Access Flooring
09 69 53 Access Flooring Accessories
09 69 56 Access Flooring Stairs and Stringers
09 70 00 Wall Finishes
09 72 00 Wall Coverings
09 72 13 Cork Wall Coverings
09 72 16 Vinyl-Coated Fabric Wall Coverings
09 72 16.13 Flexible Vinyl Wall Coverings
09 72 16.16 Rigid-Sheet Vinyl Wall Coverings
09 72 19 Textile Wall Coverings
09 72 23 Wallpapering
09 73 00 Wall Carpeting
09 74 00 Flexible Wood Sheets
09 74 13 Wood Wall Coverings
09 74 16 Flexible Wood Veneers
09 75 00 Stone Facing
09 75 13 Stone Wall Facing
09 75 19 Stone Trim
09 75 19.13 Stone Base
09 75 19.23 Stone Window Stools
09 75 23 Simulated Stone Wall Facing
09 76 00 Plastic Blocks
09 77 00 Special Wall Surfacing
09 77 13 Stretched-Fabric Wall Systems
09 77 23 Fabric-Wrapped Panels
09 77 33 Terrazzo Wall Finish
09 77 53 Vegetated Wall Systems
09 78 00 Interior Wall Paneling
09 78 13 Metal Interior Wall Paneling
09 78 16 Stone-Faced Interior Wall Paneling
09 78 19 Cementitious Interior Wall Paneling
09 78 23 Phenolic Interior Wall Paneling
09 80 00 Acoustic Treatment
09 81 00 Acoustic Insulation
09 81 13 Acoustic Board Insulation
09 81 16 Acoustic Blanket Insulation
09 81 29 Sprayed Acoustic Insulation
09 83 00 Acoustic Finishes
09 83 13 Acoustic Wall Coating
09 83 16 Acoustic Ceiling Coating
09 83 22 Acoustic Drapery
09 84 00 Acoustic Room Components
09 84 13 Fixed Sound-Absorptive Panels
09 84 14 Acoustic Stretched-Fabric Wall Systems
09 84 16 Fixed Sound-Reflective Panels
09 84 23 Moveable Sound-Absorptive Panels
09 84 26 Moveable Sound-Reflective Panels
09 84 33 Sound-Absorbing Wall Units
09 84 36 Sound-Absorbing Ceiling Units
09 90 00 Painting and Coating
09 91 00 Painting
09 91 13 Exterior Painting
09 91 23 Interior Painting
09 93 00 Staining and Transparent Finishing
09 93 13 Exterior Staining and Finishing
09 93 13.13 Exterior Staining
09 93 13.53 Exterior Finishing
09 93 23 Interior Staining and Finishing
09 93 23.13 Interior Staining
09 93 23.53 Interior Finishing
09 94 00 Decorative Finishing
09 94 13 Textured Finishing
09 94 16 Faux Finishing
09 94 19 Multicolor Interior Finishing
09 94 23 Gilding
09 96 00 High-Performance Coatings
09 96 13 Abrasion-Resistant Coatings
09 96 23 Graffiti-Resistant Coatings
09 96 26 Marine Coatings
09 96 33 High-Temperature-Resistant Coatings
09 96 35 Chemical-Resistant Coatings
09 96 43 Fire-Retardant Coatings
09 96 46 Intumescent Painting
09 96 53 Elastomeric Coatings
09 96 56 Epoxy Coatings
09 96 59 High-Build Glazed Coatings
09 96 63 Textured Plastic Coatings
09 96 66 Aggregate Wall Coatings
09 97 00 Special Coatings
09 97 13 Steel Coatings
09 97 13.13 Interior Steel Coatings
09 97 13.23 Exterior Steel Coatings
09 97 13.24 Steel Water Storage Tank Painting
09 97 23 Concrete and Masonry Coatings
09 97 23.24 Concrete Water Storage Tank Painting
09 97 26 Cementitious Coatings
09 97 26.13 Interior Cementitious Coatings
09 97 26.23 Exterior Cementitious Coatings
09 97 35 Dry Erase Coatings
10 00 00 Specialties
10 01 00 Operation and Maintenance of Specialties
10 01 10 Operation and Maintenance of Information Specialties
10 01 20 Operation and Maintenance of Interior Specialties
10 01 30 Operation and Maintenance of Fireplaces and Stoves
10 01 40 Operation and Maintenance of Safety Specialties
10 01 50 Operation and Maintenance of Storage Specialties
10 01 70 Operation and Maintenance of Exterior Specialties
10 01 80 Operation and Maintenance of Other Specialties
10 05 00 Common Work Results for Specialties
10 05 05 Selective Demolition for Specialties
10 06 00 Schedules for Specialties
10 06 10 Schedules for Information Specialties
10 06 10.13 Exterior Signage Schedule
10 06 10.16 Interior Signage Schedule
10 06 20 Schedules for Interior Specialties
10 06 20.13 Toilet, Bath, and Laundry Accessory Schedule
10 06 30 Schedules for Fireplaces and Stoves
10 06 40 Schedules for Safety Specialties
10 06 50 Schedules for Storage Specialties
10 06 70 Schedules for Exterior Specialties
10 06 80 Schedules for Other Specialties
10 08 00 Commissioning of Specialties
10 10 00 Information Specialties
10 11 00 Visual Display Units
10 11 13 Chalkboards
10 11 13.13 Fixed Chalkboards
10 11 13.23 Modular-Support-Mounted Chalkboards
10 11 13.33 Rail-Mounted Chalkboards
10 11 13.43 Portable Chalkboards
10 11 16 Markerboards
10 11 16.13 Fixed Markerboards
10 11 16.23 Modular-Support-Mounted Markerboards
10 11 16.33 Rail-Mounted Markerboards
10 11 16.43 Portable Markerboards
10 11 16.53 Electronic Markerboards
10 11 23 Tackboards
10 11 23.13 Fixed Tackboards
10 11 23.23 Modular-Support-Mounted Tackboards
10 11 23.33 Rail-Mounted Tackboards
10 11 23.43 Portable Tackboards
10 11 33 Sliding Visual Display Units
10 11 33.13 Horizontal-Sliding Visual Display Units
10 11 33.23 Vertical-Sliding Visual Display Units
10 11 36 Visual Display Conference Units
10 11 39 Visual Display Rails
10 11 43 Visual Display Wall Panels
10 11 46 Visual Display Fabrics
10 12 00 Display Cases
10 13 00 Directories
10 13 13 Electronic Directories
10 13 23 Illuminated Directories
10 14 00 Signage
10 14 16 Plaques
10 14 19 Dimensional Letter Signage
10 14 23 Panel Signage
10 14 23.13 Engraved Panel Signage
10 14 26 Post and Panel/Pylon Signage
10 14 33 Illuminated Panel Signage
10 14 43 Photoluminescent Signage
10 14 53 Traffic Signage
10 14 53.13 Transportation Reference Markers
10 14 63 Electronic Message Signage
10 14 64 Audible Signage
10 14 66 Floating Signage
10 14 67 Tactile Signage
10 17 00 Telephone Specialties
10 17 13 Telephone Directory Units
10 17 16 Telephone Enclosures
10 17 16.13 Telephone Stalls
10 17 16.16 Telephone Alcoves
10 17 19 Telephone Shelving
10 18 00 Informational Kiosks
10 20 00 Interior Specialties
10 21 00 Compartments and Cubicles
10 21 13 Toilet Compartments
10 21 13.13 Metal Toilet Compartments
10 21 13.14 Stainless-Steel Toilet Compartments
10 21 13.16 Plastic-Laminate-Clad Toilet Compartments
10 21 13.17 Phenolic-Core Toilet Compartments
10 21 13.19 Plastic Toilet Compartments
10 21 13.23 Particleboard Toilet Compartments
10 21 13.40 Stone Toilet Compartments
10 21 16 Shower and Dressing Compartments
10 21 16.13 Metal Shower and Dressing Compartments
10 21 16.14 Stainless-Steel Shower and Dressing Compartments
10 21 16.16 Plastic-Laminate-Clad Shower and Dressing Compartments
10 21 16.17 Phenolic-Core Shower and Dressing Compartments
10 21 16.19 Plastic Shower and Dressing Compartments
10 21 16.23 Particleboard Shower and Dressing Compartments
10 21 16.40 Stone Shower and Dressing Compartments
10 21 23 Cubicle Curtains and Track
10 21 23.13 Cubicle Curtains
10 21 23.16 Cubicle Track and Hardware
10 21 26 Room Darkening Curtains and Tracks
10 22 00 Partitions
10 22 13 Wire Mesh Partitions
10 22 14 Expanded Metal Partitions
10 22 16 Folding Gates
10 22 19 Demountable Partitions
10 22 19.13 Demountable Metal Partitions
10 22 19.23 Demountable Wood Partitions
10 22 19.33 Demountable Plastic Partitions
10 22 19.43 Demountable Composite Partitions
10 22 19.53 Demountable Gypsum Partitions
10 22 23 Portable Partitions, Screens, and Panels
10 22 23.13 Wall Screens
10 22 23.23 Movable Panel Systems
10 22 33 Accordion Folding Partitions
10 22 36 Coiling Partitions
10 22 39 Folding Panel Partitions
10 22 39.13 Folding Glass-Panel Partitions
10 22 43 Sliding Partitions
10 25 00 Service Walls
10 25 13 Patient Bed Service Walls
10 25 16 Modular Service Walls
10 26 00 Wall and Door Protection
10 26 13 Corner Guards
10 26 16 Bumper Guards
10 26 16.13 Bumper Rails
10 26 16.16 Protective Corridor Handrails
10 26 23 Protective Wall Covering
10 26 23.13 Impact Resistant Wall Protection
10 26 23.16 Fiberglass Reinforced Protective Wall Covering
10 26 33 Door and Frame Protection
10 26 41 Bullet Resistant Panels
10 28 00 Toilet, Bath, and Laundry Accessories
10 28 13 Toilet Accessories
10 28 13.13 Commercial Toilet Accessories
10 28 13.19 Healthcare Toilet Accessories
10 28 13.53 Security Toilet Accessories
10 28 13.63 Detention Toilet Accessories
10 28 16 Bath Accessories
10 28 16.13 Residential Bath Accessories
10 28 19 Tub and Shower Enclosures
10 28 19.16 Shower Doors
10 28 19.19 Tub Doors
10 28 23 Laundry Accessories
10 28 23.13 Built-In Ironing Boards
10 28 23.16 Clothes Drying Racks
10 28 26 Hygiene and Custodial Accessories
10 30 00 Fireplaces and Stoves
10 31 00 Manufactured Fireplaces
10 31 13 Manufactured Fireplace Chimneys
10 31 16 Manufactured Fireplace Forms
10 32 00 Fireplace Specialties
10 32 13 Fireplace Dampers
10 32 16 Fireplace Inserts
10 32 19 Fireplace Screens
10 32 23 Fireplace Doors
10 32 26 Fireplace Water Heaters
10 35 00 Stoves
10 35 13 Heating Stoves
10 35 23 Cooking Stoves
10 40 00 Safety Specialties
10 41 00 Emergency Access and Information Cabinets
10 41 13 Fire Department Plan Cabinets
10 41 16 Emergency Key Cabinets
10 43 00 Emergency Aid Specialties
10 43 13 Defibrillator Cabinets
10 43 16 First Aid Cabinets
10 43 21 Accessibility Evacuation Chairs
10 43 31 Respiration Equipment
10 43 33 Breathing Air Replenishment Systems
10 44 00 Fire Protection Specialties
10 44 13 Fire Protection Cabinets
10 44 13.53 Security Fire Extinguisher Cabinets
10 44 16 Fire Extinguishers
10 44 16.13 Portable Fire Extinguishers
10 44 16.16 Wheeled Fire Extinguisher Units
10 44 19 Fire Blankets
10 44 43 Fire Extinguisher Accessories
10 45 00 Photoluminescent Exit Specialties
10 50 00 Storage Specialties
10 51 00 Lockers
10 51 13 Metal Lockers
10 51 13.13 Coin-Operated Metal Lockers
10 51 16 Wood Lockers
10 51 23 Plastic-Laminate-Clad Lockers
10 51 26 Plastic Lockers
10 51 26.13 Recycled Plastic Lockers
10 51 29 Phenolic Lockers
10 51 33 Glass Lockers
10 51 43 Wire Mesh Storage Lockers
10 51 53 Locker Room Benches
10 55 00 Postal Specialties
10 55 13 Central Mail Delivery Boxes
10 55 13.13 Cluster Box Units
10 55 16 Mail Collection Boxes
10 55 19 Receiving Boxes
10 55 23 Mail Boxes
10 55 23.13 Apartment Mail Boxes
10 55 23.16 Mail Box Directories
10 55 23.19 Mail Box Key Keepers
10 55 26 Parcel Lockers
10 55 33 Data Distribution Boxes
10 55 36 Package Depositories
10 55 91 Mail Chutes
10 56 00 Storage Assemblies
10 56 13 Metal Storage Shelving
10 56 13.13 End-Panel-Support Metal Storage Shelving
10 56 13.16 Post-and-Shelf Metal Storage Shelving
10 56 13.19 Post-and-Beam Metal Storage Shelving
10 56 13.23 Cantilever Metal Storage Shelving
10 56 16 Fabricated Wood Storage Shelving
10 56 17 Wall-Mounted Standards and Shelving
10 56 19 Plastic Storage Shelving
10 56 19.13 Recycled Plastic Storage Shelving
10 56 23 Wire Storage Shelving
10 56 26 Mobile Storage Shelving
10 56 26.13 Manual Mobile Storage Shelving
10 56 26.23 Motorized Mobile Storage Shelving
10 56 29 Storage Racks
10 56 29.13 Flow Storage Racks
10 56 29.16 Pallet Storage Racks
10 56 29.19 Movable-Shelf Storage Racks
10 56 29.23 Stacker Storage Racks
10 56 29.26 Cantilever Storage Racks
10 56 29.29 Drive-In Storage Racks
10 56 29.33 Drive-Through Storage Racks
10 56 29.43 Wine Storage Racks
10 56 33 Mercantile Storage Assemblies
10 57 00 Wardrobe and Closet Specialties
10 57 13 Hat and Coat Racks
10 57 16 Boot Racks
10 57 23 Closet and Utility Shelving
10 57 23.13 Wire Closet and Utility Shelving
10 57 23.16 Plastic-Laminate-Clad Closet and Utility Shelving
10 57 23.19 Wood Closet and Utility Shelving
10 57 33 Closet and Utility Shelving Hardware
10 57 36 Closet Doors
10 57 36.13 Sliding Closet Doors
10 57 36.16 Bifold Closet Doors
10 70 00 Exterior Specialties
10 71 00 Exterior Protection
10 71 13 Exterior Sun Control Devices
10 71 13.13 Exterior Shutters
10 71 13.19 Rolling Exterior Shutters
10 71 13.23 Coiling Exterior Shutters
10 71 13.26 Decorative Exterior Shutters
10 71 13.29 Side-Hinged Exterior Shutters
10 71 13.43 Fixed Sun Screens
10 71 13.53 Exterior Daylighting Devices
10 71 16 Storm Panels
10 71 16.13 Demountable Storm Panels
10 71 16.16 Movable Storm Panels
10 71 19 Flood Barriers
10 71 19.16 Removable Flood Barriers
10 73 00 Protective Covers
10 73 13 Awnings
10 73 13.13 Metal Awnings
10 73 13.23 Fabric Awnings
10 73 13.36 Point Supported Glass Awnings
10 73 16 Canopies
10 73 16.13 Metal Canopies
10 73 16.23 Fabric Canopies
10 73 16.33 Glazed Canopies
10 73 16.36 Point Supported Glass Canopies
10 73 23 Car Shelters
10 73 26 Walkway Coverings
10 73 26.13 Metal Walkway Coverings
10 73 26.23 Fabric Walkway Coverings
10 73 26.33 Glazed Walkway Coverings
10 73 26.36 Point Supported Glass Walkway Coverings
10 73 33 Marquees
10 73 43 Transportation Stop Shelters
10 74 00 Manufactured Exterior Specialties
10 74 13 Exterior Clocks
10 74 23 Cupolas
10 74 26 Spires
10 74 29 Steeples
10 74 33 Weathervanes
10 74 43 Below-Grade Egress Assemblies
10 74 46 Window Wells
10 75 00 Flagpoles
10 75 13 Automatic Flagpoles
10 75 16 Ground-Set Flagpoles
10 75 19 Nautical Flagpoles
10 75 23 Wall-Mounted Flagpoles
10 75 26 Roof-Mounted Flagpoles
10 75 29 Plaza-Mounted Flagpoles
10 80 00 Other Specialties
10 81 00 Pest Control Devices
10 81 13 Bird Control Devices
10 81 16 Insect Control Devices
10 81 19 Rodent Control Devices
10 82 00 Grilles and Screens
10 82 13 Exterior Grilles and Screens
10 82 19 Exterior Sound Screens
10 82 23 Interior Grilles and Screens
10 83 00 Flags and Banners
10 83 13 Flags
10 83 16 Banners
10 84 00 Gas Lighting
10 84 13 Exterior Gas Lighting
10 84 16 Interior Gas Lighting
10 86 00 Security Mirrors and Domes
10 88 00 Scales
11 00 00 Equipment
11 01 00 Operation and Maintenance of Equipment
11 01 10 Operation and Maintenance of Vehicle and Pedestrian Equipment
11 01 20 Operation and Maintenance of Commercial Equipment
11 01 30 Operation and Maintenance of Residential Equipment
11 01 40 Operation and Maintenance of Foodservice Equipment
11 01 50 Operation and Maintenance of Educational and Scientific Equipment
11 01 56 Operation and Maintenance of Observatory Equipment
11 01 60 Operation and Maintenance of Entertainment and Recreation Equipment
11 01 70 Operation and Maintenance of Healthcare Equipment
11 01 80 Operation and Maintenance of Facility Maintenance and Operation Equipment
11 01 90 Operation and Maintenance of Other Equipment
11 05 00 Common Work Results for Equipment
11 05 05 Selective Demolition for Equipment
11 05 13 Common Motor Requirements for Equipment
11 06 00 Schedules for Equipment
11 06 10 Schedules for Vehicle and Pedestrian Equipment
11 06 20 Schedules for Commercial Equipment
11 06 30 Schedules for Residential Equipment
11 06 40 Schedules for Foodservice Equipment
11 06 40.13 Foodservice Equipment Schedule
11 06 50 Schedules for Educational and Scientific Equipment
11 06 60 Schedules for Entertainment and Recreation Equipment
11 06 70 Schedules for Healthcare Equipment
11 06 70.13 Healthcare Equipment Schedule
11 06 80 Schedules for Facility Maintenance and Operation Equipment
11 06 90 Schedules for Other Equipment
11 06 90.11 Schedules for Detention Equipment
11 08 00 Commissioning of Equipment
11 10 00 Vehicle and Pedestrian Equipment
11 11 00 Vehicle Service Equipment
11 11 13 Compressed-Air Vehicle Service Equipment
11 11 19 Vehicle Lubrication Equipment
11 11 23 Tire-Changing Equipment
11 11 26 Vehicle-Washing Equipment
11 11 36 Vehicle Charging Equipment
11 11 36.13 Commercial Electric Vehicle Charging Unit
11 11 36.16 Residential Electric Vehicle Charging Unit
11 12 00 Parking Control Equipment
11 12 13 Parking Key and Card Control Units
11 12 16 Parking Ticket Dispensers
11 12 23 Parking Meters
11 12 26 Parking Fee Collection Equipment
11 12 26.13 Parking Fee Coin Collection Equipment
11 12 33 Parking Gates
11 12 33.13 Lift Arm Parking Gates
11 12 33.16 Sliding Parking Gates
11 12 33.19 Swinging Parking Gates
11 13 00 Loading Dock Equipment
11 13 13 Loading Dock Bumpers
11 13 16 Loading Dock Seals and Shelters
11 13 16.13 Loading Dock Seals
11 13 16.23 Loading Dock Shelters
11 13 16.33 Loading Dock Rail Shelters
11 13 19 Stationary Loading Dock Equipment
11 13 19.13 Loading Dock Levelers
11 13 19.23 Stationary Loading Dock Lifts
11 13 19.26 Loading Dock Truck Lifts
11 13 19.33 Loading Dock Truck Restraints
11 13 23 Portable Dock Equipment
11 13 23.13 Portable Dock Lifts
11 13 23.16 Portable Dock Ramps
11 13 23.19 Portable Dock Bridges
11 13 23.23 Portable Dock Platforms
11 13 26 Loading Dock Lights
11 14 00 Pedestrian Control Equipment
11 14 13 Pedestrian Gates
11 14 13.16 Rotary Gates
11 14 13.19 Turnstiles
11 14 16 Pedestrian Control Devices
11 14 19 Portable Posts and Railings
11 14 26 Pedestrian Fare Collection Equipment
11 14 26.13 Pedestrian Coin Fare Collection Equipment
11 14 43 Pedestrian Detection Equipment
11 14 43.13 Electronic Detection and Counting Systems
11 14 53 Pedestrian Security Equipment
11 15 00 Security Control Equipment
11 20 00 Commercial Equipment
11 21 00 Retail and Service Equipment
11 21 13 Cash Registers and Checking Equipment
11 21 23 Vending Equipment
11 21 23.13 Merchandise Vending Machines
11 21 23.16 Reverse Vending Machines
11 21 23.19 Video Rental Vending Machines
11 21 23.36 Token Vending Machines
11 21 24 Money Changing Machines
11 21 33 Checkroom Equipment
11 21 43 Weighing and Wrapping Equipment
11 21 53 Barber and Beauty Shop Equipment
11 21 63 Refrigerated Display Equipment
11 21 73 Commercial Laundry and Dry Cleaning Equipment
11 21 73.13 Dry Cleaning Equipment
11 21 73.16 Drying and Conditioning Equipment
11 21 73.19 Finishing Equipment
11 21 73.23 Commercial Ironing Equipment
11 21 73.26 Commercial Washers and Extractors
11 21 73.33 Coin-Operated Laundry Equipment
11 21 73.43 Hanging Garment Conveyors
11 21 83 Photo Processing Equipment
11 22 00 Banking Equipment
11 22 13 Vault Equipment
11 22 13.13 Safe Deposit Boxes
11 22 13.16 Safes
11 22 13.23 Vault Ventilators
11 22 13.26 Time Capsules
11 22 16 Teller and Service Equipment
11 22 16.13 Teller Equipment Systems
11 22 16.16 Automatic Banking Systems
11 22 16.19 Money Handling Equipment
11 22 16.23 Money Depositories
11 22 16.26 Money Cart Pass-Through
11 22 16.29 Package Transfer Units
11 22 16.33 Deal Trays
11 25 00 Hospitality Equipment
11 25 13 Registration Equipment
11 28 00 Office Equipment
11 28 13 Computers
11 28 16 Printers
11 28 23 Copiers
11 29 00 Postal, Packaging, and Shipping Equipment
11 29 23 Packaging Equipment
11 29 33 Shipping Equipment
11 29 55 Postal Equipment
11 30 00 Residential Equipment
11 30 13 Residential Appliances
11 30 13.13 Residential Kitchen Appliances
11 30 13.23 Residential Laundry Appliances
11 30 33 Retractable Stairs
11 30 34 Residential Ceiling Fans
11 32 00 Unit Kitchens
11 32 13 Metal Unit Kitchens
11 32 16 Wood Unit Kitchens
11 32 19 Plastic-Laminate-Clad Unit Kitchens
11 40 00 Foodservice Equipment
11 41 00 Foodservice Storage Equipment
11 41 13 Refrigerated Food Storage Cases
11 41 23 Walk-In Coolers
11 41 26 Walk-In Freezers
11 41 33 Foodservice Shelving
11 42 00 Food Preparation Equipment
11 42 13 Food Preparation Appliances
11 42 16 Food Preparation Surfaces
11 43 00 Food Delivery Carts and Conveyors
11 43 13 Food Delivery Carts
11 43 16 Food Delivery Conveyors
11 44 00 Food Cooking Equipment
11 44 13 Commercial Ranges
11 44 16 Commercial Ovens
11 46 00 Food Dispensing Equipment
11 46 13 Bar Equipment
11 46 16 Service Line Equipment
11 46 19 Soda Fountain Equipment
11 46 23 Coffee and Espresso Equipment
11 46 83 Ice Machines
11 48 00 Foodservice Cleaning and Disposal Equipment
11 48 13 Commercial Dishwashers
11 50 00 Educational and Scientific Equipment
11 51 00 Library Equipment
11 51 13 Automated Book Storage and Retrieval Systems
11 51 16 Book Depositories
11 51 19 Book Theft Protection Equipment
11 51 23 Library Stack Systems
11 51 23.13 Metal Library Shelving
11 52 00 Audio-Visual Equipment
11 52 13 Projection Screens
11 52 13.13 Fixed Projection Screens
11 52 13.16 Portable Projection Screens
11 52 13.19 Rear Projection Screens
11 52 16 Projectors
11 52 16.13 Movie Projectors
11 52 16.16 Slide Projectors
11 52 16.19 Overhead Projectors
11 52 16.23 Opaque Projectors
11 52 16.26 Video Projectors
11 52 19 Players and Recorders
11 52 23 Audio-Visual Equipment Supports
11 53 00 Laboratory Equipment
11 53 13 Laboratory Fume Hoods
11 53 13.13 Recirculating Laboratory Fume Hoods
11 53 16 Laboratory Incubators
11 53 17 Laboratory Equipment Washers
11 53 19 Laboratory Sterilizers
11 53 23 Laboratory Refrigerators
11 53 26 Laboratory Freezers
11 53 29 Laboratory Controlled-Environment Cabinets
11 53 33 Emergency Safety Appliances
11 53 43 Service Fittings and Accessories
11 53 53 Biological Safety Cabinets
11 55 00 Planetarium Equipment
11 55 13 Planetarium Projectors
11 55 16 Planetarium Pendulums
11 56 00 Observatory Equipment
11 56 13 Telescopes
11 56 16 Telescope Mounts
11 56 19 Telescope Drive Mechanisms
11 56 23 Telescope Domes
11 57 00 Vocational Shop Equipment
11 59 00 Exhibit Equipment
11 60 00 Entertainment and Recreation Equipment
11 61 00 Broadcast, Theater, and Stage Equipment
11 61 13 Acoustical Shells
11 61 23 Folding and Portable Stages
11 61 33 Rigging Systems and Controls
11 61 33.11 Lighting Rigging Systems
11 61 33.16 Scenery Rigging Systems
11 61 33.19 Curtain Systems
11 61 43 Stage Curtains
11 62 00 Musical Equipment
11 62 13 Bells
11 62 16 Carillons
11 62 19 Organs
11 66 00 Athletic Equipment
11 66 13 Exercise Equipment
11 66 23 Gymnasium Equipment
11 66 23.13 Basketball Equipment
11 66 23.23 Volleyball Equipment
11 66 23.33 Interior Tennis Equipment
11 66 23.43 Interior Track and Field Equipment
11 66 23.53 Wall Padding
11 66 23.56 Mat Storage
11 66 43 Interior Scoreboards
11 66 53 Gymnasium Dividers
11 66 53.13 Batting/Golf Cages
11 67 00 Recreational Equipment
11 67 13 Bowling Alley Equipment
11 67 23 Shooting Range Equipment
11 67 33 Climbing Walls
11 67 43 Table Games Equipment
11 67 43.13 Pool Tables
11 67 43.23 Ping-Pong Tables
11 67 53 Game Room Equipment
11 67 53.13 Video Games
11 67 53.23 Pinball Machines
11 68 00 Play Field Equipment and Structures
11 68 13 Playground Equipment
11 68 16 Play Structures
11 68 23 Exterior Court Athletic Equipment
11 68 23.13 Exterior Basketball Equipment
11 68 23.23 Exterior Volleyball Equipment
11 68 23.33 Tennis Equipment
11 68 33 Athletic Field Equipment
11 68 33.13 Football Field Equipment
11 68 33.23 Soccer and Field Hockey Equipment
11 68 33.33 Baseball Field Equipment
11 68 33.43 Track and Field Equipment
11 68 43 Exterior Scoreboards
11 70 00 Healthcare Equipment
11 71 00 Medical Sterilizing Equipment
11 72 00 Examination and Treatment Equipment
11 72 13 Examination Equipment
11 72 53 Treatment Equipment
11 73 00 Patient Care Equipment
11 73 13 Psychiatric Seclusion Room Padding
11 74 00 Dental Equipment
11 75 00 Optical Equipment
11 76 00 Operating Room Equipment
11 77 00 Radiology Equipment
11 78 00 Mortuary Equipment
11 78 13 Mortuary Refrigerators
11 78 16 Crematorium Equipment
11 78 19 Mortuary Lifts
11 79 00 Therapy Equipment
11 80 00 Facility Maintenance and Operation Equipment
11 81 00 Facility Maintenance Equipment
11 81 13 Floor and Wall Cleaning Equipment
11 81 16 Housekeeping Carts
11 81 19 Vacuum Cleaning Systems
11 81 23 Façade Access Equipment
11 81 23.13 Window Washing Systems
11 81 29 Facility Fall Protection
11 82 00 Facility Solid Waste Handling Equipment
11 82 13 Solid Waste Bins
11 82 19 Packaged Incinerators
11 82 23 Recycling Equipment
11 82 26 Facility Waste Compactors
11 82 29 Composting Equipment
11 82 33 Facility Waste Shredders
11 82 36 Facility Waste Balers
11 90 00 Other Equipment
11 91 00 Religious Equipment
11 91 13 Baptisteries
11 92 00 Agricultural Equipment
11 92 13 Milkers
11 92 16 Stock Feeders
11 92 19 Stock Waterers
11 92 23 Agricultural Waste Clean-Up Equipment
11 93 00 Horticultural Equipment
11 93 13 Hydroponic Growing Systems
11 93 16 Seeders
11 93 19 Transplanters
11 93 23 Potting Machines
11 93 26 Flat Fillers
11 93 29 Baggers
11 93 33 Soil Mixers
11 94 00 Veterinary Equipment
11 95 00 Arts and Crafts Equipment
11 95 13 Kilns
11 97 00 Security Equipment
11 97 13 Deal Drawers
11 97 16 Gun Ports
11 97 23 Valuable Material Storage
11 98 00 Detention Equipment
11 98 11 Detention Equipment General Requirements
11 98 12 Detention Doors and Frames
11 98 13 Detention Pass-Through Doors
11 98 14 Detention Door Hardware
11 98 16 Detention Equipment Fasteners
11 98 19 Detention Room Padding
11 98 21 Detention Windows
11 98 23 Detention Window Screens
12 00 00 Furnishings
12 01 00 Operation and Maintenance of Furnishings
12 01 10 Operation and Maintenance of Art
12 01 20 Operation and Maintenance of Window Treatments
12 01 30 Operation and Maintenance of Casework
12 01 40 Operation and Maintenance of Furnishings and Accessories
12 01 50 Operation and Maintenance of Furniture
12 01 60 Operation and Maintenance of Multiple Seating
12 01 90 Operation and Maintenance of Other Furnishings
12 05 00 Common Work Results for Furnishings
12 05 05 Selective Demolition for Furnishings
12 05 13 Fabrics
12 06 00 Schedules for Furnishings
12 06 10 Schedules for Art
12 06 20 Schedules for Window Treatments
12 06 20.13 Window Treatment Schedule
12 06 30 Schedules for Casework
12 06 30.13 Manufactured Casework Schedule
12 06 40 Schedules for Furnishings and Accessories
12 06 40.13 Furnishings Schedule
12 06 50 Schedules for Furniture
12 06 60 Schedules for Multiple Seating
12 06 90 Schedules for Other Furnishings
12 08 00 Commissioning of Furnishings
12 10 00 Art
12 11 00 Murals
12 11 13 Photo Murals
12 11 16 Sculptured Brick Panels
12 11 23 Brick Murals
12 11 26 Ceramic Tile Murals
12 11 33 Trompe l'oeil
12 12 00 Wall Decorations
12 12 13 Commissioned Paintings
12 12 16 Framed Paintings
12 12 19 Framed Prints
12 12 23 Tapestries
12 12 26 Wall Hangings
12 14 00 Sculptures
12 14 13 Carved Sculpture
12 14 16 Cast Sculpture
12 14 19 Constructed Sculpture
12 14 23 Relief Art
12 17 00 Art Glass
12 17 13 Etched Glass
12 17 16 Stained Glass
12 19 00 Religious Art
12 20 00 Window Treatments
12 21 00 Window Blinds
12 21 13 Wood Blinds
12 21 13.13 Metal Horizontal Louver Blinds
12 21 13.23 Wood Horizontal Louver Blinds
12 21 13.33 Plastic Horizontal Louver Blinds
12 21 16 Vertical Louver Blinds
12 21 16.13 Metal Vertical Louver Blinds
12 21 16.23 Wood Vertical Louver Blinds
12 21 16.33 Plastic Vertical Louver Blinds
12 21 23 Roll-Down Blinds
12 21 26 Black-Out Blinds
12 22 00 Curtains and Drapes
12 22 13 Draperies
12 22 16 Drapery Track and Accessories
12 23 00 Interior Shutters
12 23 13 Wood Interior Shutters
12 24 00 Window Shades
12 24 13 Roller Window Shades
12 24 16 Pleated Window Shades
12 24 16.13 Z-Pleated Window Shades
12 24 16.16 Cellular Shades
12 24 16.19 Roman Shades
12 25 00 Window Treatment Operating Hardware
12 25 09 Window Treatment Control System
12 25 13 Motorized Drapery Rods
12 26 00 Interior Daylighting Devices
12 30 00 Casework
12 31 00 Manufactured Metal Casework
12 31 16 Manufactured Metal Sandwich Panel Casework
12 32 00 Manufactured Wood Casework
12 32 13 Manufactured Wood-Veneer-Faced Casework
12 32 16 Manufactured Plastic-Laminate-Clad Casework
12 34 00 Manufactured Plastic Casework
12 34 16 Manufactured Solid-Plastic Casework
12 34 19 Manufactured Solid Surface Casework
12 35 00 Specialty Casework
12 35 17 Bank Casework
12 35 25 Hospitality Casework
12 35 30 Residential Casework
12 35 30.13 Kitchen Casework
12 35 30.23 Bathroom Casework
12 35 30.43 Dormitory Casework
12 35 33 Utility Room Casework
12 35 36 Mailroom Casework
12 35 39 Commercial Kitchen Casework
12 35 50 Educational/Library Casework
12 35 50.13 Educational Casework
12 35 50.53 Library Casework
12 35 50.56 Built-In Study Carrels
12 35 53 Laboratory Casework
12 35 53.13 Metal Laboratory Casework
12 35 53.16 Plastic-Laminate-Clad Laboratory Casework
12 35 53.19 Wood Laboratory Casework
12 35 53.23 Solid-Plastic Laboratory Casework
12 35 59 Display Casework
12 35 70 Healthcare Casework
12 35 70.13 Hospital Casework
12 35 70.16 Nurse Station Casework
12 35 70.19 Exam Room Casework
12 35 70.74 Dental Casework
12 35 83 Performing Arts Casework
12 35 91 Religious Casework
12 36 00 Countertops
12 36 13 Concrete Countertops
12 36 16 Metal Countertops
12 36 19 Wood Countertops
12 36 23 Plastic Countertops
12 36 23.13 Plastic-Laminate-Clad Countertops
12 36 26 Glass Countertops
12 36 40 Stone Countertops
12 36 53 Laboratory Countertops
12 36 61 Simulated Stone Countertops
12 36 61.13 Cultured Marble Countertops
12 36 61.16 Solid Surfacing Countertops
12 36 61.19 Quartz Agglomerate Countertops
12 36 71 Paper-Composite Countertops
12 40 00 Furnishings and Accessories
12 41 00 Office Accessories
12 41 13 Desk Accessories
12 42 00 Table Accessories
12 42 13 Ceramics
12 42 16 Flatware
12 42 16.13 Silverware
12 42 19 Hollowware
12 42 23 Glassware
12 42 26 Table Linens
12 42 26.13 Napery
12 43 00 Portable Lamps
12 43 13 Lamps
12 43 13.13 Desk Lamps
12 43 13.16 Table Lamps
12 43 13.19 Floor Lamps
12 44 00 Bath Furnishings
12 44 13 Bath Linens
12 44 13.13 Bath Mats
12 44 13.16 Bath Towels
12 44 16 Shower Curtains
12 45 00 Bedroom Furnishings
12 45 13 Bed Linens
12 45 13.13 Blankets
12 45 13.16 Comforters
12 45 16 Pillows
12 46 00 Furnishing Accessories
12 46 13 Ash Receptacles
12 46 16 Bowls
12 46 19 Clocks
12 46 23 Decorative Crafts
12 46 26 Decorative Screens
12 46 29 Vases
12 46 33 Waste Receptacles
12 48 00 Rugs and Mats
12 48 13 Entrance Floor Mats and Frames
12 48 13.13 Entrance Floor Mats
12 48 13.16 Entrance Floor Mat Frames
12 48 16 Entrance Floor Grilles
12 48 19 Entrance Floor Gratings
12 48 23 Entrance Floor Grids
12 48 26 Entrance Tile
12 48 43 Floor Mats
12 48 43.13 Chair Mats
12 48 43.23 Anti-Fatigue Floor Mats
12 48 43.26 Fall-Cushioning Floor Mats
12 48 53 Rugs
12 48 53.13 Runners
12 48 53.16 Oriental Rugs
12 50 00 Furniture
12 51 00 Office Furniture
12 51 16 Case Goods
12 51 16.13 Metal Case Goods
12 51 16.16 Wood Case Goods
12 51 16.19 Plastic-Laminate-Clad Case Goods
12 51 19 Filing Cabinets
12 51 19.13 Lateral Filing Cabinets
12 51 19.16 Vertical Filing Cabinets
12 51 23 Office Tables
12 51 83 Custom Office Furniture
12 52 00 Seating
12 52 13 Chairs
12 52 19 Upholstered Seating
12 52 23 Office Seating
12 52 70 Healthcare Seating
12 52 83 Custom Seating
12 53 00 Retail Furniture
12 53 83 Custom Retail Furniture
12 54 00 Hospitality Furniture
12 54 13 Hotel and Motel Furniture
12 54 16 Restaurant Furniture
12 54 83 Custom Hospitality Furniture
12 55 00 Detention Furniture
12 55 13 Detention Bunks
12 55 16 Detention Desks
12 55 19 Detention Stools
12 55 23 Detention Tables
12 55 26 Detention Safety Clothes Hooks
12 55 83 Custom Detention Furniture
12 55 86 Detention Control Room Furniture
12 56 00 Institutional Furniture
12 56 23 Religious Furniture
12 56 33 Classroom Furniture
12 56 33.13 Fixed Classroom Tables
12 56 33.23 Classroom Computer Furniture
12 56 39 Lecterns
12 56 43 Dormitory Furniture
12 56 51 Library Furniture
12 56 51.13 Book Shelves
12 56 51.16 Study Carrels
12 56 51.19 Index Card File Cabinets
12 56 52 Audio-Visual Furniture
12 56 53 Laboratory Furniture
12 56 70 Healthcare Furniture
12 56 83 Custom Institutional Furniture
12 56 86 Institutional Control Room Furniture
12 57 00 Industrial Furniture
12 57 13 Welding Benches
12 57 16 Welding Screens
12 57 19 Laser Containment Screens
12 57 83 Custom Industrial Furniture
12 57 86 Industrial Control Room Furniture
12 58 00 Residential Furniture
12 58 13 Couches and Loveseats
12 58 13.13 Futons
12 58 16 Residential Chairs
12 58 16.13 Reclining Chairs
12 58 19 Dining Tables and Chairs
12 58 23 Coffee Tables
12 58 26 Entertainment Centers
12 58 29 Beds
12 58 29.13 Daybeds
12 58 33 Dressers
12 58 33.13 Armoires
12 58 36 Nightstands
12 58 83 Custom Residential Furniture
12 59 00 Systems Furniture
12 59 13 Panel-Hung Component System Furniture
12 59 16 Free-Standing Component System Furniture
12 59 19 Beam System Furniture
12 59 23 Desk System Furniture
12 59 83 Custom Systems Furniture
12 60 00 Multiple Seating
12 61 00 Fixed Audience Seating
12 61 13 Upholstered Audience Seating
12 61 16 Molded-Plastic Audience Seating
12 62 00 Portable Audience Seating
12 62 13 Folding Chairs
12 62 16 Interlocking Chairs
12 62 19 Stacking Chairs
12 62 23 Portable Bleachers
12 63 00 Stadium and Arena Seating
12 63 13 Stadium and Arena Bench Seating
12 63 23 Stadium and Arena Seats
12 64 00 Booths and Tables
12 65 00 Multiple-Use Fixed Seating
12 66 00 Telescoping Stands
12 66 13 Telescoping Bleachers
12 66 23 Telescoping Chair Platforms
12 67 00 Pews and Benches
12 67 13 Pews
12 67 23 Benches
12 68 00 Seat and Table Assemblies
12 68 13 Pedestal Tablet Arm Chairs
12 90 00 Other Furnishings
12 92 00 Interior Planters and Artificial Plants
12 92 13 Interior Artificial Plants
12 92 33 Interior Planters
12 92 43 Interior Landscaping Accessories
12 93 00 Interior Public Space Furnishings
12 93 13 Bicycle Racks
12 93 14 Bicycle Lockers
12 93 23 Trash and Litter Receptacles
13 00 00 Special Construction
13 01 00 Operation and Maintenance of Special Construction
13 01 10 Operation and Maintenance of Special Facility Components
13 01 11 Operation and Maintenance of Swimming Pools
13 01 12 Operation and Maintenance of Fountains
13 01 13 Operation and Maintenance of Aquariums
13 01 14 Operation and Maintenance of Amusement Park Structures and Equipment
13 01 18 Operation and Maintenance of Ice Rinks
13 01 20 Operation and Maintenance of Special Purpose Rooms
13 01 21 Operation and Maintenance of Controlled Environment Rooms
13 01 23 Operation and Maintenance of Planetariums
13 01 30 Operation and Maintenance of Special Structures
13 01 40 Operation and Maintenance of Integrated Construction
13 01 49 Operation and Maintenance of Radiation Protection
13 01 50 Operation and Maintenance of Special Instrumentation
13 01 51 Operation and Maintenance of Stress Instrumentation
13 01 52 Operation and Maintenance of Seismic Instrumentation
13 01 53 Operation and Maintenance of Meteorological Instrumentation
13 05 00 Common Work Results for Special Construction
13 05 05 Selective Demolition for Special Construction
13 06 00 Schedules for Special Construction
13 06 10 Schedules for Special Facility Components
13 06 20 Schedules for Special Purpose Rooms
13 06 30 Schedules for Special Structures
13 06 40 Schedules for Integrated Construction
13 06 50 Schedules for Special Instrumentation
13 08 00 Commissioning of Special Construction
13 08 10 Commissioning of Special Facility Components
13 08 11 Commissioning of Swimming Pools
13 08 12 Commissioning of Fountains
13 08 13 Commissioning of Aquariums
13 08 14 Commissioning of Amusement Park Structures and Equipment
13 08 18 Commissioning of Ice Rinks
13 08 20 Commissioning of Special Purpose Rooms
13 08 21 Commissioning of Controlled Environment Rooms
13 08 23 Commissioning of Planetariums
13 08 30 Commissioning of Special Structures
13 08 40 Commissioning of Integrated Construction
13 08 50 Commissioning of Special Instrumentation
13 10 00 Special Facility Components
13 11 00 Swimming Pools
13 11 13 Below-Grade Swimming Pools
13 11 23 On-Grade Swimming Pools
13 11 33 Elevated Swimming Pools
13 11 43 Recirculating Gutter Systems
13 11 46 Swimming Pool Accessories
13 11 49 Swimming Pool Cleaning Equipment
13 11 53 Movable Pool Bulkheads
13 11 56 Movable Pool Floors
13 12 00 Fountains
13 12 13 Exterior Fountains
13 12 23 Interior Fountains
13 13 00 Aquariums
13 14 00 Amusement Park Structures and Equipment
13 14 13 Water Slides
13 14 16 Wave Generating Equipment
13 14 23 Amusement Park Rides
13 15 00 Specialty Element Construction
13 17 00 Tubs and Pools
13 17 13 Hot Tubs
13 17 23 Therapeutic Pools
13 17 33 Whirlpool Tubs
13 18 00 Ice Rinks
13 18 13 Ice Rink Floor Systems
13 18 16 Ice Rink Dasher Boards
13 19 00 Kennels and Animal Shelters
13 19 13 Kennel Enclosures and Gates
13 19 16 Kennel Feeding Devices
13 19 19 Animal Washing Tubs
13 20 00 Special Purpose Rooms
13 21 00 Controlled Environment Rooms
13 21 13 Clean Rooms
13 21 16 Hyperbaric Rooms
13 21 23 Insulated Rooms
13 21 26 Cold Storage Rooms
13 21 26.13 Walk-in Coolers
13 21 26.16 Walk-in Freezers
13 21 29 Constant Temperature Rooms
13 21 48 Sound-Conditioned Rooms
13 22 00 Office Shelters and Booths
13 23 00 Planetariums
13 24 00 Special Activity Rooms
13 24 16 Saunas
13 24 26 Steam Baths
13 24 66 Athletic Rooms
13 26 00 Fabricated Rooms
13 26 13 Storm Shelter Rooms
13 27 00 Vaults
13 27 16 Modular Fire Vaults
13 27 53 Security Vaults
13 27 53.13 Modular Concrete Security Vaults
13 27 53.16 Modular Metal-Clad Laminated Security Vaults
13 28 00 Athletic and Recreational Special Construction
13 28 13 Indoor Soccer Boards
13 28 16 Safety Netting
13 28 19 Arena Football Boards
13 28 26 Floor Sockets
13 28 33 Athletic and Recreational Court Walls
13 28 66 Demountable Athletic Surfaces
13 30 00 Special Structures
13 31 00 Fabric Structures
13 31 13 Air-Supported Fabric Structures
13 31 13.13 Single-Walled Air-Supported Structures
13 31 13.16 Multiple-Walled Air-Supported Structures
13 31 23 Tensioned Fabric Structures
13 31 33 Framed Fabric Structures
13 32 00 Space Frames
13 32 13 Metal Space Frames
13 32 23 Wood Space Frames
13 33 00 Geodesic Structures
13 33 13 Geodesic Domes
13 34 00 Fabricated Engineered Structures
13 34 13 Glazed Structures
13 34 13.13 Greenhouses
13 34 13.16 Solariums
13 34 13.19 Swimming Pool Enclosures
13 34 13.23 Sunrooms
13 34 13.26 Conservatories
13 34 16 Grandstands and Bleachers
13 34 16.13 Grandstands
13 34 16.53 Bleachers
13 34 18 Post Frame Building Systems
13 34 19 Metal Building Systems
13 34 23 Fabricated Structures
13 34 23.13 Portable and Mobile Buildings
13 34 23.14 Fabricated Classroom Buildings
13 34 23.16 Fabricated Control Booths
13 34 23.19 Fabricated Dome Structures
13 34 23.23 Fabricated Substation Control Rooms
13 34 56 Observatories
13 35 00 Rammed Earth Construction
13 35 13 Rammed Earth Walls
13 35 13.13 Traditional Rammed Earth Walls
13 35 13.23 Stabilized Insulated Rammed Earth Walls
13 36 00 Towers
13 36 13 Metal Towers
13 36 13.13 Steel Towers
13 36 23 Wood Towers
13 40 00 Integrated Construction
13 42 00 Building Modules
13 42 13 Bathroom Unit Modules
13 42 25 Hospitality Unit Modules
13 42 33 Apartment Unit Modules
13 42 43 Dormitory Unit Modules
13 42 46 Education Unit Modules
13 42 63 Detention Cell Modules
13 42 63.13 Precast-Concrete Detention Cell Modules
13 42 63.16 Steel Detention Cell Modules
13 44 00 Modular Mezzanines
13 47 00 Facility Protection
13 47 13 Cathodic Protection
13 47 13.13 Cathodic Protection for Underground and Submerged Piping
13 47 13.16 Cathodic Protection for Underground Storage Tanks
13 47 13.19 Cathodic Protection for Concrete Reinforcing
13 48 00 Sound, Vibration, and Seismic Control
13 48 13 Manufactured Sound and Vibration Control Components
13 48 23 Fabricated Sound and Vibration Control Assemblies
13 48 53 Manufactured Seismic Control Components
13 48 63 Fabricated Seismic Control Assemblies
13 49 00 Radiation Protection
13 49 13 Integrated X-Ray Shielding Assemblies
13 49 16 Modular X-Ray Shielding Rooms
13 49 23 Integrated RFI/EMI Shielding Assemblies
13 49 26 Modular RFI/EMI Shielding Rooms
13 50 00 Special Instrumentation
13 51 00 Stress Instrumentation
13 52 00 Seismic Instrumentation
13 53 00 Meteorological Instrumentation
13 53 13 Solar Instrumentation
13 53 23 Wind Instrumentation
14 00 00 Conveying Equipment
14 01 00 Operation and Maintenance of Conveying Equipment
14 01 10 Operation and Maintenance of Dumbwaiters
14 01 10.71 Dumbwaiter Rehabilitation
14 01 20 Operation and Maintenance of Elevators
14 01 20.71 Elevator Rehabilitation
14 01 30 Operation and Maintenance of Escalators and Moving Walks
14 01 30.71 Escalators and Moving Walks Rehabilitation
14 01 40 Operation and Maintenance of Lifts
14 01 40.71 Lift Rehabilitation
14 01 70 Operation and Maintenance of Turntables
14 01 80 Operation and Maintenance of Scaffolding
14 01 90 Operation and Maintenance of Other Conveying Equipment
14 05 00 Common Work Results for Conveying Equipment
14 05 05 Selective Demolition for Conveying Equipment
14 06 00 Schedules for Conveying Equipment
14 06 10 Schedules for Dumbwaiters
14 06 20 Schedules for Elevators
14 06 20.13 Elevator Equipment Schedule
14 06 30 Schedules for Escalators and Moving Walks
14 06 40 Schedules for Lifts
14 06 40.13 Lift Schedule
14 06 70 Schedules for Turntables
14 06 80 Schedules for Scaffolding
14 06 90 Schedules for Other Conveying Equipment
14 08 00 Commissioning of Conveying Equipment
14 08 10 Commissioning of Dumbwaiters
14 08 20 Commissioning of Elevators
14 08 30 Commissioning of Escalators and Moving Walks
14 08 40 Commissioning of Lifts
14 08 70 Commissioning of Turntables
14 08 80 Commissioning of Scaffolding
14 10 00 Dumbwaiters
14 11 00 Manual Dumbwaiters
14 12 00 Electric Dumbwaiters
14 14 00 Hydraulic Dumbwaiters
14 20 00 Elevators
14 21 00 Electric Traction Elevators
14 21 13 Electric Traction Freight Elevators
14 21 23 Electric Traction Passenger Elevators
14 21 23.13 Machine Room Electric Traction Passenger Elevators
14 21 23.16 Machine Room-Less Electric Traction Passenger Elevators
14 21 33 Electric Traction Residential Elevators
14 21 43 Electric Traction Service Elevators
14 24 00 Hydraulic Elevators
14 24 13 Hydraulic Freight Elevators
14 24 23 Hydraulic Passenger Elevators
14 24 33 Hydraulic Residential Elevators
14 24 43 Hydraulic Service Elevators
14 26 00 Limited-Use/Limited-Application Elevators
14 27 00 Custom Elevator Cabs and Doors
14 27 13 Custom Elevator Cab Finishes
14 27 16 Custom Elevator Doors
14 28 00 Elevator Equipment and Controls
14 28 16 Elevator Controls
14 28 19 Elevator Equipment
14 28 19.13 Elevator Safety Equipment
14 28 19.16 Elevator Hoistway Equipment
14 30 00 Escalators and Moving Walks
14 31 00 Escalators
14 32 00 Moving Walks
14 33 00 Moving Ramps
14 33 13 Motorized Ramps
14 33 16 Powered Ramps
14 40 00 Lifts
14 41 00 People Lifts
14 41 13 Counterbalanced People Lifts
14 41 16 Endless-Belt People Lifts
14 41 19 Stairway Chairlifts
14 42 00 Wheelchair Lifts
14 42 13 Inclined Wheelchair Lifts
14 42 16 Vertical Wheelchair Lifts
14 43 00 Platform Lifts
14 43 13 Orchestra Lifts
14 43 16 Stage Lifts
14 44 00 Sidewalk Lifts
14 45 00 Vehicle Lifts
14 45 13 Vehicle Service Lifts
14 45 23 Vehicle Parking Lifts
14 46 00 Material Lifts
14 70 00 Turntables
14 71 00 Industrial Turntables
14 71 11 Vehicle Turntables
14 72 00 Hospitality Turntables
14 72 25 Restaurant Turntables
14 73 00 Exhibit Turntables
14 73 59 Display Turntables
14 74 00 Entertainment Turntables
14 74 61 Stage Turntables
14 80 00 Scaffolding
14 81 00 Suspended Scaffolding
14 81 13 Beam Scaffolding
14 81 16 Carriage Scaffolding
14 81 19 Hook Scaffolding
14 82 00 Rope Climbers
14 82 13 Manual Rope Climbers
14 82 16 Powered Rope Climbers
14 83 00 Elevating Platforms
14 83 13 Telescoping Platform Lifts
14 83 13.13 Electric and Battery Telescoping Platform Lifts
14 83 13.16 Pneumatic Telescoping Platform Lifts
14 83 16 Scissor Lift Platforms
14 83 19 Multi-Axis Platform Lifts
14 84 00 Powered Scaffolding
14 84 13 Window Washing Scaffolding
14 84 23 Window Washing Hoists
14 90 00 Other Conveying Equipment
14 91 00 Facility Chutes
14 91 13 Coal Chutes
14 91 23 Escape Chutes
14 91 33 Laundry and Linen Chutes
14 91 82 Trash Chutes
14 92 00 Pneumatic Tube Systems
14 93 00 Slide Pole Systems
14 93 13 Firehouse Slide Poles
21 00 00 Fire Suppression
21 01 00 Operation and Maintenance of Fire Suppression
21 01 10 Operation and Maintenance of Water-Based Fire-Suppression Systems
21 01 20 Operation and Maintenance of Fire-Extinguishing Systems
21 01 30 Operation and Maintenance of Fire-Suppression Equipment
21 05 00 Common Work Results for Fire Suppression
21 05 05 Selective Demolition for Fire Suppression
21 05 13 Common Motor Requirements for Fire-Suppression Equipment
21 05 16 Expansion Fittings and Loops for Fire-Suppression Piping
21 05 17 Sleeves and Sleeve Seals for Fire-Suppression Piping
21 05 19 Meters and Gages for Fire-Suppression Systems
21 05 23 General-Duty Valves for Water-Based Fire-Suppression Piping
21 05 29 Hangers and Supports for Fire-Suppression Piping and Equipment
21 05 33 Heat Tracing for Fire-Suppression Piping
21 05 48 Vibration and Seismic Controls for Fire-Suppression Piping and Equipment
21 05 48.13 Vibration Controls for Fire-Suppresion Piping and Equipment
21 05 53 Identification for Fire-Suppression Piping and Equipment
21 06 00 Schedules for Fire Suppression
21 06 10 Schedules for Water-Based Fire-Suppression Systems
21 06 20 Schedules for Fire-Extinguishing Systems
21 06 30 Schedules for Fire-Suppression Equipment
21 07 00 Fire Suppression Systems Insulation
21 07 16 Fire-Suppression Equipment Insulation
21 07 19 Fire-Suppression Piping Insulation
21 08 00 Commissioning of Fire Suppression
21 09 00 Instrumentation and Control for Fire-Suppression Systems
21 10 00 Water-Based Fire-Suppression Systems
21 11 00 Facility Fire-Suppression Water-Service Piping
21 11 16 Facility Fire Hydrants
21 11 19 Fire-Department Connections
21 12 00 Fire-Suppression Standpipes
21 12 13 Fire-Suppression Hoses and Nozzles
21 12 16 Fire-Suppression Hose Reels
21 12 19 Fire-Suppression Hose Racks
21 12 23 Fire-Suppression Hose Valves
21 13 00 Fire-Suppression Sprinkler Systems
21 13 13 Wet-Pipe Sprinkler Systems
21 13 16 Dry-Pipe Sprinkler Systems
21 13 19 Preaction Sprinkler Systems
21 13 23 Combined Dry-Pipe and Preaction Sprinkler Systems
21 13 26 Deluge Fire-Suppression Sprinkler Systems
21 13 29 Water Spray Fixed Systems
21 13 36 Antifreeze Sprinkler Systems
21 13 39 Foam-Water Systems
21 16 00 Fire-Suppression Pressure Maintenance Pumps
21 20 00 Fire-Extinguishing Systems
21 21 00 Carbon-Dioxide Fire-Extinguishing Systems
21 21 13 Carbon-Dioxide Fire-Extinguishing Piping
21 21 13.13 High-Pressure, Carbon-Dioxide Fire-Extinguishing Systems
21 21 13.16 Low-Pressure, Carbon-Dioxide Fire-Extinguishing Systems
21 21 16 Carbon-Dioxide Fire-Extinguishing Equipment
21 22 00 Clean-Agent Fire-Extinguishing Systems
21 22 13 Clean-Agent Fire-Extinguishing Piping
21 22 16 Clean-Agent Fire-Extinguishing Equipment
21 23 00 Wet-Chemical Fire-Extinguishing Systems
21 23 13 Wet-Chemical Fire-Extinguishing Piping
21 23 16 Wet-Chemical Fire-Extinguishing Equipment
21 24 00 Dry-Chemical Fire-Extinguishing Systems
21 24 13 Dry-Chemical Fire-Extinguishing Piping
21 24 16 Dry-Chemical Fire-Extinguishing Equipment
21 30 00 Fire Pumps
21 31 00 Centrifugal Fire Pumps
21 31 13 Electric-Drive, Centrifugal Fire Pumps
21 31 16 Diesel-Drive, Centrifugal Fire Pumps
21 32 00 Vertical-Turbine Fire Pumps
21 32 13 Electric-Drive, Vertical-Turbine Fire Pumps
21 32 16 Diesel-Drive, Vertical-Turbine Fire Pumps
21 33 00 Positive-Displacement Fire Pumps
21 33 13 Electric-Drive, Positive-Displacement Fire Pumps
21 33 16 Diesel-Drive, Positive-Displacement Fire Pumps
21 34 00 Fire Pump Accessories
21 34 13 Pressure Maintenance Pumps
21 40 00 Fire-Suppression Water Storage
21 41 00 Storage Tanks for Fire-Suppression Water
21 41 13 Pressurized Storage Tanks for Fire-Suppression Water
21 41 16 Elevated Storage Tanks for Fire-Suppression Water
21 41 19 Roof-Mounted Storage Tanks for Fire-Suppression Water
21 41 23 Ground Suction Storage Tanks for Fire-Suppression Water
21 41 26 Underground Storage Tanks for Fire-Suppression Water
21 41 29 Storage Tanks for Fire-Suppression Water Additives
22 00 00 Plumbing
22 01 00 Operation and Maintenance of Plumbing
22 01 10 Operation and Maintenance of Plumbing Piping and Pumps
22 01 10.16 Video Piping Inspections
22 01 10.51 Plumbing Piping Cleaning
22 01 10.61 Plumbing Piping Repairs
22 01 10.62 Plumbing Piping Relining
22 01 30 Operation and Maintenance of Plumbing Equipment
22 01 40 Operation and Maintenance of Plumbing Fixtures
22 01 50 Operation and Maintenance of Pool and Fountain Plumbing Systems
22 01 60 Operation and Maintenance of Laboratory and Healthcare Systems
22 05 00 Common Work Results for Plumbing
22 05 05 Selective Demolition for Plumbing
22 05 13 Common Motor Requirements for Plumbing Equipment
22 05 16 Expansion Fittings and Loops for Plumbing Piping
22 05 17 Sleeves and Sleeve Seals for Plumbing Piping
22 05 19 Meters and Gages for Plumbing Piping
22 05 23 General-Duty Valves for Plumbing Piping
22 05 29 Hangers and Supports for Plumbing Piping and Equipment
22 05 33 Heat Tracing for Plumbing Piping
22 05 48 Vibration and Seismic Controls for Plumbing Piping and Equipment
22 05 48.13 Vibration Controls for Plumbing Piping and Equipment
22 05 53 Identification for Plumbing Piping and Equipment
22 05 73 Facility Drainage Manholes
22 05 76 Facility Drainage Piping Cleanouts
22 06 00 Schedules for Plumbing
22 06 10 Schedules for Plumbing Piping and Pumps
22 06 10.13 Plumbing Pump Schedule
22 06 12 Schedules for Facility Potable Water Storage
22 06 15 Schedules for General Service Compressed-Air Equipment
22 06 30 Schedules for Plumbing Equipment
22 06 30.13 Domestic Water Heater Schedule
22 06 40 Schedules for Plumbing Fixtures
22 06 40.13 Plumbing Fixture Schedule
22 06 50 Schedules for Pool and Fountain Plumbing Systems
22 06 60 Schedules for Laboratory and Healthcare Systems
22 07 00 Plumbing Insulation
22 07 16 Plumbing Equipment Insulation
22 07 19 Plumbing Piping Insulation
22 08 00 Commissioning of Plumbing
22 09 00 Instrumentation and Control for Plumbing
22 09 63 Medical Gas Alarms
22 10 00 Plumbing Piping
22 11 00 Facility Water Distribution
22 11 13 Facility Water Distribution Piping
22 11 16 Domestic Water Piping
22 11 17 Gray-Water Piping
22 11 19 Domestic Water Piping Specialties
22 11 23 Domestic Water Pumps
22 11 23.13 Domestic-Water Packaged Booster Pumps
22 11 23.23 Domestic-Water In-Line Pumps
22 11 23.26 Close-Coupled, Horizontally Mounted, In-Line Centrifugal Domestic-Water Pumps
22 11 23.29 Close-Coupled, Vertically Mounted, In-Line Centrifugal Domestic-Water Pumps
22 11 23.33 Separately Coupled, In-Line Centrifugal Domestic-Water Pumps
22 11 23.36 Separately Coupled, Horizontally Mounted, In-Line Centrifugal Domestic-Water Pumps
22 11 23.43 Domestic-Water, Base-Mounted Pumps
22 11 63 Gray-Water Pumps
22 12 00 Facility Potable-Water Storage Tanks
22 12 13 Facility Roof-Mounted, Potable-Water Storage Tanks
22 12 16 Facility Elevated, Potable-Water Storage Tanks
22 12 19 Facility Ground-Mounted, Potable-Water Storage Tanks
22 12 21 Facility Underground Potable-Water Storage Tanks
22 12 23 Facility Indoor Potable-Water Storage Tanks
22 12 23.13 Facility Steel, Indoor Potable-Water Storage Pressure Tanks
22 12 23.16 Facility Steel, Indoor Potable-Water Storage Non-Pressure Tanks
22 12 23.23 Facility Plastic, Indoor Potable-Water Storage Pressure Tanks
22 12 23.26 Facility Plastic, Indoor Potable-Water Storage Non-Pressure Tanks
22 13 00 Facility Sanitary Sewerage
22 13 13 Facility Sanitary Sewers
22 13 16 Sanitary Waste and Vent Piping
22 13 19 Sanitary Waste Piping Specialties
22 13 19.13 Sanitary Drains
22 13 19.23 Fats, Oils, and Grease Disposal Systems
22 13 19.26 Grease Removal Devices
22 13 19.33 Backwater Valves
22 13 19.36 Air-Admittance Valves
22 13 23 Sanitary Waste Interceptors
22 13 26 Sanitary Waste Separators
22 13 29 Sanitary Sewerage Pumps
22 13 29.13 Wet-Pit-Mounted, Vertical Sewerage Pumps
22 13 29.16 Submersible Sewerage Pumps
22 13 29.23 Sewerage Pump Reverse-Flow Assemblies
22 13 29.33 Sewerage Pump Basins and Pits
22 13 33 Packaged, Submersible Sewerage Pump Units
22 13 36 Packaged, Wastewater Pump Units
22 13 43 Facility Packaged Sewage Pumping Stations
22 13 43.13 Facility Dry-Well Packaged Sewage Pumping Stations
22 13 43.16 Facility Wet-Well Packaged Sewage Pumping Stations
22 13 63 Facility Gray Water Tanks
22 14 00 Facility Storm Drainage
22 14 13 Facility Storm Drainage Piping
22 14 16 Rainwater Leaders
22 14 19 Sump Pump Discharge Piping
22 14 23 Storm Drainage Piping Specialties
22 14 26 Facility Storm Drains
22 14 26.13 Roof Drains
22 14 26.16 Facility Area Drains
22 14 26.19 Facility Trench Drains
22 14 29 Sump Pumps
22 14 29.13 Wet-Pit-Mounted, Vertical Sump Pumps
22 14 29.16 Submersible Sump Pumps
22 14 29.19 Sump-Pump Basins and Pits
22 14 33 Packaged, Pedestal Drainage Pump Units
22 14 36 Packaged, Submersible, Drainage Pump Units
22 14 53 Rainwater Storage Tanks
22 14 63 Facility Storm-Water Retention Tanks
22 15 00 General Service Compressed-Air Systems
22 15 13 General Service Compressed-Air Piping
22 15 16 General Service Compressed-Air Valves
22 15 19 General Service Packaged Air Compressors and Receivers
22 15 19.13 General Service Packaged Reciprocating Air Compressors
22 15 19.16 General Service Packaged Liquid-Ring Air Compressors
22 15 19.19 General Service Packaged Rotary-Screw Air Compressors
22 15 19.23 General Service Packaged Sliding-Vane Air Compressors
22 30 00 Plumbing Equipment
22 31 00 Domestic Water Softeners
22 31 13 Residential Domestic Water Softeners
22 31 16 Commercial Domestic Water Softeners
22 32 00 Domestic Water Filtration Equipment
22 32 13 Domestic-Water Bag-Type Filters
22 32 16 Domestic-Water Freestanding Cartridge Filters
22 32 19 Domestic-Water Off-Floor Cartridge Filters
22 32 23 Domestic-Water Carbon Filters
22 32 26 Domestic-Water Sand Filters
22 32 26.13 Domestic-Water Circulating Sand Filters
22 32 26.16 Domestic-Water Multimedia Sand Filters
22 32 26.19 Domestic-Water Greensand Filters
22 33 00 Electric Domestic Water Heaters
22 33 13 Instantaneous Electric Domestic Water Heaters
22 33 13.13 Flow-Control, Instantaneous Electric Domestic Water Heaters
22 33 13.16 Thermostat-Control, Instantaneous Electric Domestic Water Heaters
22 33 30 Residential, Electric Domestic Water Heaters
22 33 30.13 Residential, Small-Capacity Electric Domestic Water Heaters
22 33 30.16 Residential, Storage Electric Domestic Water Heaters
22 33 30.23 Residential, Collector-to-Tank, Solar-Electric Domestic Water Heaters
22 33 30.26 Residential, Collector-to-Tank, Heat-Exchanger-Coil, Solar-Electric Domestic Water Heaters
22 33 33 Light-Commercial Electric Domestic Water Heaters
22 33 36 Commercial Domestic Water Electric Booster Heaters
22 33 36.13 Commercial Domestic Water Electric Booster Heaters
22 33 36.16 Commercial Storage Electric Domestic Water Heaters
22 34 00 Fuel-Fired Domestic Water Heaters
22 34 13 Instantaneous, Tankless, Gas Domestic Water Heaters
22 34 30 Residential Gas Domestic Water Heaters
22 34 30.13 Residential, Atmospheric, Gas Domestic Water Heaters
22 34 30.16 Residential, Direct-Vent, Gas Domestic Water Heaters
22 34 30.19 Residential, Power-Vent, Gas Domestic Water Heaters
22 34 36 Commercial Gas Domestic Water Heaters
22 34 36.13 Commercial, Atmospheric, Gas Domestic Water Heaters
22 34 36.16 Commercial, Power-Burner, Gas Domestic Water Heaters
22 34 36.19 Commercial, Power-Vent, Gas Domestic Water Heaters
22 34 36.23 Commercial, High-Efficiency, Gas Domestic Water Heaters
22 34 36.26 Commercial, Coil-Type, Finned-Tube, Gas Domestic Water Heaters
22 34 36.29 Commercial, Grid-Type, Finned-Tube, Gas Domestic Water Heaters
22 34 46 Oil-Fired Domestic Water Heaters
22 34 46.13 Large-Capacity, Oil-Fired Domestic Water Heaters
22 34 56 Dual-Fuel-Fired Domestic Water Heaters
22 35 00 Domestic Water Heat Exchangers
22 35 13 Instantaneous Domestic Water Heat Exchangers
22 35 13.13 Heating-Fluid-in-Coil, Instantaneous Domestic Water Heat Exchangers
22 35 13.16 Domestic-Water-in-Coil, Instantaneous Domestic Water Heat Exchangers
22 35 13.19 Heating-Fluid-in-U-Tube-Coil, Instantaneous Domestic Water Heat Exchangers
22 35 23 Circulating, Domestic Water Heat Exchangers
22 35 23.13 Circulating, Compact Domestic Water Heat Exchangers
22 35 23.16 Circulating, Storage Domestic Water Heat Exchangers
22 35 29 Noncirculating, Domestic Water Heat Exchangers
22 35 29.13 Noncirculating, Compact Domestic Water Heat Exchangers
22 35 29.16 Noncirculating, Storage Domestic Water Heat Exchangers
22 35 36 Domestic Water Brazed-Plate Heat Exchangers
22 35 39 Domestic Water Frame-and-Plate Heat Exchangers
22 35 43 Domestic Water Heat Reclaimers
22 36 00 Domestic Water Preheaters
22 36 13 Solar Domestic Water Preheaters
22 36 23 Geothermal Domestic Water Preheaters
22 40 00 Plumbing Fixtures
22 41 00 Residential Plumbing Fixtures
22 41 13 Residential Water Closets, Urinals, and Bidets
22 41 13.13 Residential Water Closets
22 41 13.16 Residential Urinals
22 41 13.19 Residential Bidets
22 41 16 Residential Lavatories and Sinks
22 41 16.13 Residential Lavatories
22 41 16.16 Residential Sinks
22 41 19 Residential Bathtubs
22 41 23 Residential Showers
22 41 26 Residential Disposers
22 41 36 Residential Laundry Trays
22 41 39 Residential Faucets, Supplies, and Trim
22 42 00 Commercial Plumbing Fixtures
22 42 13 Commercial Water Closets, Urinals, and Bidets
22 42 13.13 Commercial Water Closets
22 42 13.16 Commercial Urinals
22 42 16 Commercial Lavatories and Sinks
22 42 16.13 Commercial Lavatories
22 42 16.16 Commercial Sinks
22 42 19 Commercial Bathtubs
22 42 23 Commercial Showers
22 42 26 Commercial Disposers
22 42 29 Shampoo Bowls
22 42 33 Wash Fountains
22 42 36 Commercial Laundry Trays
22 42 39 Commercial Faucets, Supplies, and Trim
22 42 43 Flushometers
22 43 00 Healthcare Plumbing Fixtures
22 43 13 Healthcare Water Closets
22 43 16 Healthcare Sinks
22 43 19 Healthcare Bathtubs
22 43 23 Healthcare Showers
22 43 39 Healthcare Faucets
22 43 43 Healthcare Plumbing Fixture Flushometers
22 45 00 Emergency Plumbing Fixtures
22 45 13 Emergency Showers
22 45 16 Eyewash Equipment
22 45 19 Self-Contained Eyewash Equipment
22 45 23 Personal Eyewash Equipment
22 45 26 Eye/Face Wash Equipment
22 45 29 Hand-Held Emergency Drench Hoses
22 45 33 Combination Emergency Fixture Units
22 45 36 Emergency Fixture Water-Tempering Equipment
22 46 00 Security Plumbing Fixtures
22 46 13 Security Water Closets and Urinals
22 46 13.13 Security Water Closets
22 46 13.16 Security Urinals
22 46 16 Security Lavatories and Sinks
22 46 16.13 Security Lavatories
22 46 16.16 Security Sinks
22 46 19 Security Showers
22 46 39 Security Faucets, Supplies, and Trim
22 46 43 Security Plumbing Fixture Flushometers
22 46 53 Security Plumbing Fixture Supports
22 47 00 Drinking Fountains and Water Coolers
22 47 13 Drinking Fountains
22 47 16 Pressure Water Coolers
22 47 19 Water-Station Water Coolers
22 47 23 Remote Water Coolers
22 50 00 Pool and Fountain Plumbing Systems
22 51 00 Swimming Pool Plumbing Systems
22 51 13 Swimming Pool Piping
22 51 16 Swimming Pool Pumps
22 51 19 Swimming Pool Water Treatment Equipment
22 51 23 Swimming Pool Equipment Controls
22 52 00 Fountain Plumbing Systems
22 52 13 Fountain Piping
22 52 16 Fountain Pumps
22 52 19 Fountain Water Treatment Equipment
22 52 23 Fountain Equipment Controls
22 60 00 Gas and Vacuum Systems for Laboratory and Healthcare Facilities
22 61 00 Compressed-Air Systems for Laboratory and Healthcare Facilities
22 61 13 Compressed-Air Piping for Laboratory and Healthcare Facilities
22 61 13.53 Laboratory Compressed-Air Piping
22 61 13.70 Healthcare Compressed-Air Piping
22 61 13.74 Dental Compressed-Air Piping
22 61 19 Compressed-Air Equipment for Laboratory and Healthcare Facilities
22 61 19.53 Laboratory Compressed-Air Equipment
22 61 19.70 Healthcare Compressed-Air Equipment
22 61 19.74 Dental Compressed-Air Equipment
22 62 00 Vacuum Systems for Laboratory and Healthcare Facilities
22 62 13 Vacuum Piping for Laboratory and Healthcare Facilities
22 62 13.53 Laboratory Vacuum Piping
22 62 13.70 Healthcare, Surgical Vacuum Piping
22 62 13.74 Dental Vacuum Piping
22 62 19 Vacuum Equipment for Laboratory and Healthcare Facilities
22 62 19.53 Laboratory Vacuum Equipment
22 62 19.70 Healthcare Vacuum Equipment
22 62 19.74 Dental Vacuum and Evacuation Equipment
22 62 23 Waste Anesthesia-Gas Piping
22 63 00 Gas Systems for Laboratory and Healthcare Facilities
22 63 13 Gas Piping for Laboratory and Healthcare Facilities
22 63 13.53 Laboratory Gas Piping
22 63 13.70 Healthcare Gas Piping
22 63 19 Gas Storage Tanks for Laboratory and Healthcare Facilities
22 63 19.53 Laboratory Gas Storage Tanks
22 63 19.70 Healthcare Gas Storage Tanks
22 66 00 Chemical-Waste Systems for Laboratory and Healthcare Facilities
22 66 53 Laboratory Chemical-Waste and Vent Piping
22 66 70 Healthcare Chemical-Waste and Vent Piping
22 66 83 Chemical-Waste Tanks
22 66 83.13 Chemical-Waste Dilution Tanks
22 66 83.16 Chemical-Waste Neutralization Tanks
22 67 00 Processed Water Systems for Laboratory and Healthcare Facilities
22 67 13 Processed Water Piping for Laboratory and Healthcare Facilities
22 67 13.13 Distilled-Water Piping
22 67 13.16 Reverse-Osmosis Water Piping
22 67 13.19 Deionized-Water Piping
22 67 19 Processed Water Equipment for Laboratory and Healthcare Facilities
22 67 19.13 Distilled-Water Equipment
22 67 19.16 Reverse-Osmosis Water Equipment
22 67 19.19 Deionized-Water Equipment
23 00 00 Heating, Ventilating, and Air Conditioning (HVAC)
23 01 00 Operation and Maintenance of HVAC Systems
23 01 10 Operation and Maintenance of Facility Fuel Systems
23 01 20 Operation and Maintenance of HVAC Piping and Pumps
23 01 30 Operation and Maintenance of HVAC Air Distribution
23 01 30.51 HVAC Air-Distribution System Cleaning
23 01 50 Operation and Maintenance of Central Heating Equipment
23 01 60 Operation and Maintenance of Central Cooling Equipment
23 01 60.71 Refrigerant Recovery/Recycling
23 01 70 Operation and Maintenance of Central HVAC Equipment
23 01 80 Operation and Maintenance of Decentralized HVAC Equipment
23 01 90 Diagnostic Systems for HVAC
23 05 00 Common Work Results for HVAC
23 05 05 Selective Demolition for Heating, Ventilating, and Air Conditioning (HVAC)
23 05 13 Common Motor Requirements for HVAC Equipment
23 05 16 Expansion Fittings and Loops for HVAC Piping
23 05 17 Sleeves and Sleeve Seals for HVAC Piping
23 05 19 Meters and Gages for HVAC Piping
23 05 23 General-Duty Valves for HVAC Piping
23 05 29 Hangers and Supports for HVAC Piping and Equipment
23 05 33 Heat Tracing for HVAC Piping
23 05 48 Vibration and Seismic Controls for HVAC
23 05 48.13 Vibration Controls for HVAC
23 05 53 Identification for HVAC Piping and Equipment
23 05 63 Anti-Microbial Coatings for HVAC Ducts and Equipment
23 05 66 Anti-Microbial Ultraviolet Emitters for HVAC Ducts and Equipment
23 05 93 Testing, Adjusting, and Balancing for HVAC
23 06 00 Schedules for HVAC
23 06 10 Schedules for Facility Fuel Service Systems
23 06 20 Schedules for HVAC Piping and Pumps
23 06 20.13 Hydronic Pump Schedule
23 06 30 Schedules for HVAC Air Distribution
23 06 30.13 HVAC Fan Schedule
23 06 30.16 Air Terminal Unit Schedule
23 06 30.19 Air Outlet and Inlet Schedule
23 06 30.23 HVAC Air Cleaning Device Schedule
23 06 50 Schedules for Central Heating Equipment
23 06 50.13 Heating Boiler Schedule
23 06 60 Schedules for Central Cooling Equipment
23 06 60.13 Refrigerant Condenser Schedule
23 06 60.16 Packaged Water Chiller Schedule
23 06 70 Schedules for Central HVAC Equipment
23 06 70.13 Indoor, Central-Station Air-Handling Unit Schedule
23 06 70.16 Packaged Outdoor HVAC Equipment Schedule
23 06 80 Schedules for Decentralized HVAC Equipment
23 06 80.13 Decentralized Unitary HVAC Equipment Schedule
23 06 80.16 Convection Heating and Cooling Unit Schedule
23 06 80.19 Radiant Heating Unit Schedule
23 07 00 HVAC Insulation
23 07 13 Duct Insulation
23 07 16 HVAC Equipment Insulation
23 07 19 HVAC Piping Insulation
23 08 00 Commissioning of HVAC
23 09 00 Instrumentation and Control for HVAC
23 09 13 Instrumentation and Control Devices for HVAC
23 09 13.13 Actuators and Operators
23 09 13.23 Sensors and Transmitters
23 09 13.33 Control Valves
23 09 13.43 Control Dampers
23 09 23 Direct-Digital Control System for HVAC
23 09 23.11 Control Valves
23 09 23.12 Control Dampers
23 09 23.13 Energy Meters
23 09 23.14 Flow Instruments
23 09 23.16 Gas Instruments
23 09 23.17 Level Instruments
23 09 23.18 Leak Detection Instruments
23 09 23.19 Moisture Instruments
23 09 23.21 Motion Instruments
23 09 23.22 Position Instruments
23 09 23.23 Pressure Instruments
23 09 23.24 Speed Instruments
23 09 23.27 Temperature Instruments
23 09 23.33 Vibration Instruments
23 09 23.43 Weather Stations
23 09 33 Electric and Electronic Control System for HVAC
23 09 43 Pneumatic Control System for HVAC
23 09 53 Pneumatic and Electric Control System for HVAC
23 09 93 Sequence of Operations for HVAC Controls
23 09 93.11 Sequence of Operation for HVAC DDC
23 10 00 Facility Fuel Systems
23 11 00 Facility Fuel Piping
23 11 13 Facility Fuel-Oil Piping
23 11 16 Facility Gasoline Piping
23 11 23 Facility Natural-Gas Piping
23 11 26 Facility Liquefied-Petroleum Gas Piping
23 12 00 Facility Fuel Pumps
23 12 13 Facility Fuel-Oil Pumps
23 12 16 Facility Gasoline Dispensing Pumps
23 12 26 Facility Liquefied-Petroleum Gas Pumps
23 13 00 Facility Fuel-Storage Tanks
23 13 13 Facility Underground Fuel-Oil, Storage Tanks
23 13 13.13 Double-Wall Steel, Underground Fuel-Oil, Storage Tanks
23 13 13.16 Composite, Steel, Underground Fuel-Oil, Storage Tanks
23 13 13.19 Jacketed, Steel, Underground Fuel-Oil, Storage Tanks
23 13 13.23 Glass-Fiber-Reinforced-Plastic, Underground Fuel-Oil, Storage Tanks
23 13 13.33 Fuel-Oil Storage Tank Pumps
23 13 23 Facility Aboveground Fuel-Oil, Storage Tanks
23 13 23.13 Vertical, Steel, Aboveground Fuel-Oil, Storage Tanks
23 13 23.16 Horizontal, Steel, Aboveground Fuel-Oil, Storage Tanks
23 13 23.19 Containment-Dike, Steel, Aboveground Fuel-Oil, Storage Tanks
23 13 23.23 Insulated, Steel, Aboveground Fuel-Oil, Storage Tanks
23 13 23.26 Concrete-Vaulted, Steel, Aboveground Fuel-Oil, Storage Tanks
23 13 26 Facility Aboveground Liquefied-Petroleum Gas Storage Tanks
23 20 00 HVAC Piping and Pumps
23 21 00 Hydronic Piping and Pumps
23 21 13 Hydronic Piping
23 21 13.13 Underground Hydronic Piping
23 21 13.23 Aboveground Hydronic Piping
23 21 13.33 Ground-Loop Heat-Pump Piping
23 21 16 Hydronic Piping Specialties
23 21 23 Hydronic Pumps
23 21 23.13 In-Line Centrifugal Hydronic Pumps
23 21 23.16 Base-Mounted, Centrifugal Hydronic Pumps
23 21 23.19 Vertical-Mounted, Double-Suction Centrifugal Hydronic Pumps
23 21 23.23 Vertical-Turbine Hydronic Pumps
23 21 29 Automatic Condensate Pump Units
23 22 00 Steam and Condensate Piping and Pumps
23 22 13 Steam and Condensate Heating Piping
23 22 13.13 Underground Steam and Condensate Heating Piping
23 22 13.23 Aboveground Steam and Condensate Heating Piping
23 22 16 Steam and Condensate Heating Piping Specialties
23 22 23 Steam Condensate Pumps
23 22 23.13 Electric-Driven Steam Condensate Pumps
23 22 23.23 Pressure-Powered Steam Condensate Pumps
23 23 00 Refrigerant Piping
23 23 13 Refrigerant Piping Valves
23 23 16 Refrigerant Piping Specialties
23 23 19 Refrigerant Safety Relief Valve Discharge Piping
23 23 23 Refrigerants
23 24 00 Internal-Combustion Engine Piping
23 24 13 Internal-Combustion Engine Remote-Radiator Coolant Piping
23 24 16 Internal-Combustion Engine Exhaust Piping
23 25 00 HVAC Water Treatment
23 25 13 Water Treatment for Closed-Loop Hydronic Systems
23 25 16 Water Treatment for Open Hydronic Systems
23 25 19 Water Treatment for Steam System Feedwater
23 25 23 Water Treatment for Humidification Steam System Feedwater
23 25 33 HVAC Makeup-Water Filtration Equipment
23 30 00 HVAC Air Distribution
23 31 00 HVAC Ducts and Casings
23 31 13 Metal Ducts
23 31 13.13 Rectangular Metal Ducts
23 31 13.16 Round and Flat-Oval Spiral Ducts
23 31 13.19 Metal Duct Fittings
23 31 16 Nonmetal Ducts
23 31 16.13 Fibrous-Glass Ducts
23 31 16.16 Thermoset Fiberglass-Reinforced Plastic Ducts
23 31 16.19 PVC Ducts
23 31 16.26 Concrete Ducts
23 31 19 HVAC Casings
23 32 00 Air Plenums and Chases
23 32 13 Fabricated, Metal Air Plenums
23 32 33 Air-Distribution Ceiling Plenums
23 32 36 Air-Distribution Floor Plenums
23 32 39 Air-Distribution Wall Plenums
23 32 43 Air-Distribution Chases Formed by General Construction
23 32 48 Acoustical Air Plenums
23 33 00 Air Duct Accessories
23 33 13 Dampers
23 33 13.13 Volume-Control Dampers
23 33 13.16 Fire Dampers
23 33 13.19 Smoke-Control Dampers
23 33 13.23 Backdraft Dampers
23 33 19 Duct Silencers
23 33 23 Turning Vanes
23 33 33 Duct-Mounting Access Doors
23 33 38 Duct Security Bars
23 33 43 Flexible Connectors
23 33 46 Flexible Ducts
23 33 53 Duct Liners
23 34 00 HVAC Fans
23 34 13 Axial HVAC Fans
23 34 16 Centrifugal HVAC Fans
23 34 23 HVAC Power Ventilators
23 34 33 Air Curtains
23 34 39 High-Volume, Low-Speed Propeller Fans
23 35 00 Special Exhaust Systems
23 35 13 Dust Collection Systems
23 35 13.13 Sawdust Collection Systems
23 35 16 Engine Exhaust Systems
23 35 16.13 Positive-Pressure Engine Exhaust Systems
23 35 16.16 Mechanical Engine Exhaust Systems
23 35 33 Listed Kitchen Ventilation Exhaust System
23 36 00 Air Terminal Units
23 36 13 Constant-Air-Volume Units
23 36 16 Variable-Air-Volume Units
23 37 00 Air Outlets and Inlets
23 37 13 Diffusers, Registers, and Grilles
23 37 13.43 Security Registers and Grilles
23 37 16 Fabric Air Distribution Devices
23 37 23 HVAC Gravity Ventilators
23 37 23.13 HVAC Gravity Dome Ventilators
23 37 23.16 HVAC Gravity Louvered-Penthouse Ventilators
23 37 23.19 HVAC Gravity Upblast Ventilators
23 38 00 Ventilation Hoods
23 38 13 Commercial-Kitchen Hoods
23 38 13.13 Listed Commercial-Kitchen Hoods
23 38 13.16 Standard Commercial-Kitchen Hoods
23 38 16 Fume Hoods
23 40 00 HVAC Air Cleaning Devices
23 41 00 Particulate Air Filtration
23 41 13 Panel Air Filters
23 41 16 Renewable-Media Air Filters
23 41 19 Washable Air Filters
23 41 23 Extended Surface Filters
23 41 33 High-Efficiency Particulate Filtration
23 41 43 Ultra-Low Penetration Filtration
23 41 46 Super Ultra-Low Penetration Filtration
23 42 00 Gas-Phase Air Filtration
23 42 13 Activated-Carbon Air Filtration
23 42 16 Chemically-Impregnated Adsorption Air Filtration
23 42 19 Catalytic-Adsorption Air Filtration
23 43 00 Electronic Air Cleaners
23 43 13 Washable Electronic Air Cleaners
23 43 16 Agglomerator Electronic Air Cleaners
23 43 23 Self-Contained Electronic Air Cleaners
23 50 00 Central Heating Equipment
23 51 00 Breechings, Chimneys, and Stacks
23 51 13 Draft Control Devices
23 51 13.11 Draft Control Fans
23 51 13.13 Draft-Induction Fans
23 51 13.16 Vent Dampers
23 51 13.19 Barometric Dampers
23 51 16 Fabricated Breechings and Accessories
23 51 19 Fabricated Stacks
23 51 23 Gas Vents
23 51 33 Insulated Sectional Chimneys
23 51 43 Flue-Gas Filtration Equipment
23 51 43.13 Gaseous Filtration
23 51 43.16 Particulate Filtration
23 52 00 Heating Boilers
23 52 13 Electric Boilers
23 52 16 Condensing Boilers
23 52 16.13 Stainless-Steel Condensing Boilers
23 52 16.16 Aluminum Condensing Boilers
23 52 17 Low Mass Boilers
23 52 19 Pulse Combustion Boilers
23 52 23 Cast-Iron Boilers
23 52 33 Water-Tube Boilers
23 52 33.13 Finned Water-Tube Boilers
23 52 33.14 Flexible Water-Tube Boilers
23 52 33.16 Steel Water-Tube Boilers
23 52 33.19 Copper Water-Tube Boilers
23 52 39 Fire-Tube Boilers
23 52 39.13 Scotch Marine Boilers
23 52 39.16 Steel Fire-Tube Boilers
23 52 83 Boiler Blowdown Systems
23 53 00 Heating Boiler Feedwater Equipment
23 53 13 Boiler Feedwater Pumps
23 53 16 Deaerators
23 54 00 Furnaces
23 54 13 Electric-Resistance Furnaces
23 54 16 Fuel-Fired Furnaces
23 54 16.13 Gas-Fired Furnaces
23 54 16.16 Oil-Fired Furnaces
23 55 00 Fuel-Fired Heaters
23 55 13 Fuel-Fired Duct Heaters
23 55 13.13 Oil-Fired Duct Heaters
23 55 13.16 Gas-Fired Duct Heaters
23 55 23 Gas-Fired Radiant Heaters
23 55 23.13 Low-Intensity Gas-Fired Radiant Heaters
23 55 23.16 High-Intensity Gas-Fired Radiant Heaters
23 55 33 Fuel-Fired Unit Heaters
23 55 33.13 Oil-Fired Unit Heaters
23 55 33.16 Gas-Fired Unit Heaters
23 56 00 Solar Energy Heating Equipment
23 56 13 Heating Solar Collectors
23 56 13.13 Heating Solar Flat-Plate Collectors
23 56 13.16 Heating Solar Concentrating Collectors
23 56 13.19 Heating Solar Vacuum-Tube Collectors
23 56 16 Packaged Solar Heating Equipment
23 56 23 Solar Air-Heating Panels
23 57 00 Heat Exchangers for HVAC
23 57 13 Steam-to-Steam Heat Exchangers
23 57 16 Steam-to-Water Heat Exchangers
23 57 19 Liquid-to-Liquid Heat Exchangers
23 57 19.13 Plate-Type, Liquid-to-Liquid Heat Exchangers
23 57 19.16 Shell-Type, Liquid-to-Liquid Heat Exchangers
23 57 33 Direct Geoexchange Heat Exchangers
23 60 00 Central Cooling Equipment
23 61 00 Refrigerant Compressors
23 61 13 Centrifugal Refrigerant Compressors
23 61 13.13 Non-Condensable Gas Purge Equipment
23 61 16 Reciprocating Refrigerant Compressors
23 61 19 Scroll Refrigerant Compressors
23 61 23 Rotary-Screw Refrigerant Compressors
23 62 00 Packaged Compressor and Condenser Units
23 62 13 Packaged Air-Cooled Refrigerant Compressor and Condenser Units
23 62 23 Packaged Water-Cooled Refrigerant Compressor and Condenser Units
23 62 46 Packaged Variable-Refrigerant-Flow Air-Conditioning Systems
23 63 00 Refrigerant Condensers
23 63 13 Air-Cooled Refrigerant Condensers
23 63 23 Water-Cooled Refrigerant Condensers
23 63 33 Evaporative Refrigerant Condensers
23 64 00 Packaged Water Chillers
23 64 13 Absorption Water Chillers
23 64 13.13 Direct-Fired Absorption Water Chillers
23 64 13.16 Indirect-Fired Absorption Water Chillers
23 64 16 Centrifugal Water Chillers
23 64 16.13 Air-Cooled Centrifugal Water Chillers
23 64 16.16 Water-Cooled Centrifugal Water Chillers
23 64 19 Reciprocating Water Chillers
23 64 23 Scroll Water Chillers
23 64 23.13 Air-Cooled Scroll Water Chillers
23 64 23.16 Water-Cooled Scroll Water Chillers
23 64 26 Rotary-Screw Water Chillers
23 64 26.13 Air-Cooled, Rotary-Screw Water Chillers
23 64 26.16 Water-Cooled, Rotary-Screw Water Chillers
23 64 33 Modular Water Chillers
23 64 33.13 Air-Cooled, Modular Water Chillers
23 64 33.16 Water-Cooled, Modular Water Chillers
23 65 00 Cooling Towers
23 65 13 Forced-Draft Cooling Towers
23 65 13.13 Open-Circuit, Forced-Draft Cooling Towers
23 65 13.16 Closed-Circuit, Forced-Draft Cooling Towers
23 65 14 Induced-Draft Cooling Towers
23 65 14.13 Open-Circuit, Induced-Draft Counterflow Cooling Towers
23 65 14.14 Open-Circuit, Induced-Draft Crossflow Cooling Towers
23 65 14.16 Closed-Circuit, Induced-Draft Counterflow Cooling Towers
23 65 14.17 Closed-Circuit, Induced-Draft Combined-Flow Cooling Towers
23 65 16 Natural-Draft Cooling Towers
23 65 23 Field-Erected Cooling Towers
23 65 33 Liquid Coolers
23 70 00 Central HVAC Equipment
23 71 00 Thermal Storage
23 71 13 Thermal Heat Storage
23 71 13.13 Room Storage Heaters for Thermal Storage
23 71 13.16 Heat-Pump Boosters for Thermal Storage
23 71 13.19 Central Furnace Heat-Storage Units
23 71 13.23 Pressurized-Water Thermal Storage Tanks
23 71 16 Chilled-Water Thermal Storage
23 71 19 Ice Storage
23 71 19.13 Internal Ice-on-Coil Thermal Storage
23 71 19.16 External Ice-on-Coil Thermal Storage
23 71 19.19 Encapsulated-Ice Thermal Storage
23 71 19.23 Ice-Harvesting Thermal Storage
23 71 19.26 Ice-Slurry Thermal Storage
23 72 00 Air-to-Air Energy Recovery Equipment
23 72 13 Heat-Wheel Air-to-Air Energy-Recovery Equipment
23 72 16 Heat-Pipe Air-to-Air Energy-Recovery Equipment
23 72 19 Fixed-Plate Air-to-Air Energy-Recovery Equipment
23 72 23 Packaged Air-to-Air Energy-Recovery Units
23 73 00 Indoor Central-Station Air-Handling Units
23 73 13 Modular Indoor Central-Station Air-Handling Units
23 73 23 Custom Indoor Central-Station Air-Handling Units
23 73 33 Indoor Indirect Fuel-Fired Heating and Ventilating Units
23 73 33.13 Indoor Indirect Oil-Fired Heating and Ventilating Units
23 73 33.16 Indoor Indirect Gas-Fired Heating and Ventilating Units
23 73 39 Indoor, Direct Gas-Fired Heating and Ventilating Units
23 74 00 Packaged Outdoor HVAC Equipment
23 74 13 Packaged, Outdoor, Central-Station Air-Handling Units
23 74 16 Packaged Rooftop Air-Conditioning Units
23 74 16.11 Packaged, Small-Capacity, Rooftop Air-Conditioning Units
23 74 16.12 Packaged, Intermediate-Capacity, Rooftop Air-Conditioning Units
23 74 16.13 Packaged, Large-Capacity, Rooftop Air-Conditioning Units
23 74 23 Packaged, Outdoor, Heating-Only Makeup-Air Units
23 74 23.13 Packaged, Direct-Fired, Outdoor, Heating-Only Makeup-Air Units
23 74 23.16 Packaged, Indirect-Fired, Outdoor, Heating-Only Makeup-Air Units
23 74 33 Dedicated Outdoor-Air Units
23 75 00 Custom-Packaged Outdoor HVAC Equipment
23 75 13 Custom-Packaged, Outdoor, Central-Station Air-Handling Units
23 75 16 Custom-Packaged, Rooftop Air-Conditioning Units
23 75 23 Custom-Packaged, Outdoor, Heating and Ventilating Makeup-Air Units
23 75 33 Custom-Packaged, Outdoor, Heating and Cooling Makeup Air- Conditioners
23 76 00 Evaporative Air-Cooling Equipment
23 76 13 Direct Evaporative Air Coolers
23 76 16 Indirect Evaporative Air Coolers
23 76 19 Combined Direct and Indirect Evaporative Air Coolers
23 80 00 Decentralized HVAC Equipment
23 81 00 Decentralized Unitary HVAC Equipment
23 81 13 Packaged Terminal Air-Conditioners
23 81 13.11 Packaged Terminal Air-Conditioners, Through-Wall Units
23 81 13.12 Packaged Terminal Air-Conditioners, Freestanding Units
23 81 13.13 Packaged Terminal Air-Conditioners, Outdoor, Wall-Mounted Units
23 81 16 Room Air-Conditioners
23 81 19 Self-Contained Air-Conditioners
23 81 19.13 Small-Capacity Self-Contained Air-Conditioners
23 81 19.16 Large-Capacity Self-Contained Air-Conditioners
23 81 23 Computer-Room Air-Conditioners
23 81 23.11 Small-Capacity, Computer-Room Air-Conditioners, Floor Mounted Units
23 81 23.12 Large-Capacity, Computer-Room Air-Conditioners, Floor-Mounted Units
23 81 23.13 Computer-Room Air-Conditioners, Ceiling Mounted Units
23 81 23.14 Computer-Room Air-Conditioners, Console Units
23 81 23.16 Computer-Room Air-Conditioners, Rack Mounted, Space-Cooling Units
23 81 23.18 Computer-Room, Rack-Cooling Equipment
23 81 26 Split-System Air-Conditioners
23 81 26.13 Small-Capacity Split-System Air-Conditioners
23 81 26.16 Large-Capacity Split-System Air-Conditioners
23 81 29 Variable Refrigerant Flow HVAC Systems
23 81 43 Air-Source Unitary Heat Pumps
23 81 46 Water-Source Unitary Heat Pumps
23 81 49 Ground-Source Unitary Heat Pumps
23 82 00 Convection Heating and Cooling Units
23 82 13 Valance Heating and Cooling Units
23 82 14 Chilled Beams
23 82 16 Air Coils
23 82 16.11 Hydronic Air Coils
23 82 16.12 Steam Air Coils
23 82 16.13 Refrigerant Air Coils
23 82 16.14 Electric-Resistance Air Coils
23 82 19 Fan Coil Units
23 82 23 Unit Ventilators
23 82 26 Induction Units
23 82 29 Radiators
23 82 33 Convectors
23 82 36 Finned-Tube Radiation Heaters
23 82 39 Unit Heaters
23 82 39.13 Cabinet Unit Heaters
23 82 39.16 Propeller Unit Heaters
23 82 39.19 Wall and Ceiling Unit Heaters
23 82 41 Water-to-Water Heat Pumps
23 83 00 Radiant Heating Units
23 83 13 Radiant-Heating Electric Cables
23 83 13.16 Radiant-Heating Electric Mats
23 83 16 Radiant-Heating Hydronic Piping
23 83 23 Radiant-Heating Electric Panels
23 83 33 Electric Radiant Heaters
23 84 00 Humidity Control Equipment
23 84 13 Humidifiers
23 84 13.13 Heated-Pan Humidifiers
23 84 13.16 Wetted-Element Humidifiers
23 84 13.19 Atomizing Humidifiers
23 84 13.23 Direct-Steam-Injection Humidifiers
23 84 13.26 Jacketed, Steam Humidifiers
23 84 13.29 Self-Contained Steam Humidifiers
23 84 13.33 Portable Humidifiers
23 84 16 Mechanical Dehumidification Units
23 84 16.13 Outdoor, Mechanical Dehumidification Units
23 84 16.16 Indoor, Mechanical Dehumidification Units
23 84 16.33 Portable Dehumidifiers
23 84 19 Desiccant Dehumidification Units
25 00 00 Integrated Automation
25 01 00 Operation and Maintenance of Integrated Automation
25 01 10 Operation and Maintenance of Integrated Automation Network Equipment
25 01 20 Operation and Maintenance of Integrated Equipment
25 01 30 Operation and Maintenance of Integrated Automation Instrumentation and Terminal Devices
25 01 90 Diagnostic Systems for Integrated Automation
25 05 00 Common Work Results for Integrated Automation
25 05 05 Selective Demolition for Integrated Automation
25 05 13 Conductors and Cables for Integrated Automation
25 05 26 Grounding and Bonding for Integrated Automation
25 05 28 Pathways for Integrated Automation
25 05 28.29 Hangers and Supports for Integrated Automation
25 05 28.33 Conduits and Backboxes for Integrated Automation
25 05 28.36 Cable Trays for Integrated Automation
25 05 28.39 Surface Raceways for Integrated Automation
25 05 48 Vibration and Seismic Controls for Integrated Automation
25 05 53 Identification for Integrated Automation
25 06 00 Schedules for Integrated Automation
25 06 11 Schedules for Integrated Automation Network
25 06 12 Schedules for Integrated Automation Network Gateways
25 06 13 Schedules for Integrated Automation Control and Monitoring Network
25 06 14 Schedules for Integrated Automation Local Control Units
25 06 30 Schedules for Integrated Automation Instrumentation and Terminal Devices
25 08 00 Commissioning of Integrated Automation
25 10 00 Integrated Automation Network Equipment
25 11 00 Integrated Automation Network Devices
25 11 13 Integrated Automation Network Servers
25 11 16 Integrated Automation Network Routers, Bridges, Switches, Hubs, and Modems
25 11 19 Integrated Automation Network Operator Workstations
25 12 00 Integrated Automation Network Gateways
25 12 13 Hardwired Integration Network Gateways
25 12 16 Direct-Protocol Integration Network Gateways
25 12 19 Neutral-Protocol Integration Network Gateways
25 12 23 Client-Server Information/Database Integration Network Gateways
25 13 00 Integrated Automation Control and Monitoring Network
25 13 13 Integrated Automation Control and Monitoring Network Supervisory Control
25 13 16 Integrated Automation Control and Monitoring Network Integration Panels
25 13 19 Integrated Automation Control and Monitoring Network Interoperability
25 14 00 Integrated Automation Local Control Units
25 14 13 Integrated Automation Remote Control Panels
25 14 16 Integrated Automation Application-Specific Control Panels
25 14 19 Integrated Automation Terminal Control Units
25 14 23 Integrated Automation Field Equipment Panels
25 15 00 Integrated Automation Software
25 15 13 Integrated Automation Software for Network Gateways
25 15 16 Integrated Automation Software for Control and Monitoring Networks
25 15 19 Integrated Automation Software for Local Control Units
25 30 00 Integrated Automation Instrumentation and Terminal Devices
25 31 00 Integrated Automation Instrumentation and Terminal Devices for Facility Equipment
25 32 00 Integrated Automation Instrumentation and Terminal Devices for Conveying Equipment
25 33 00 Integrated Automation Instrumentation and Terminal Devices for Fire-Suppression Systems
25 34 00 Integrated Automation Instrumentation and Terminal Devices for Plumbing
25 35 00 Integrated Automation Instrumentation and Terminal Devices for HVAC
25 35 13 Integrated Automation Actuators and Operators
25 35 16 Integrated Automation Sensors and Transmitters
25 35 19 Integrated Automation Control Valves
25 35 23 Integrated Automation Control Dampers
25 35 26 Integrated Automation Compressed Air Supply
25 36 00 Integrated Automation Instrumentation and Terminal Devices for Electrical Systems
25 36 13 Integrated Automation Power Meters
25 36 16 Integrated Automation KW Transducers
25 36 19 Integrated Automation Current Sensors
25 36 23 Integrated Automation Battery Monitors
25 36 26 Integrated Automation Lighting Relays
25 36 29 Integrated Automation UPS Monitors
25 37 00 Integrated Automation Instrumentation and Terminal Devices for Communications Systems
25 38 00 Integrated Automation Instrumentation and Terminal Devices for Electronic Safety and Security Systems
25 50 00 Integrated Automation Facility Controls
25 51 00 Integrated Automation Control of Facility Equipment
25 52 00 Integrated Automation Control of Conveying Equipment
25 53 00 Integrated Automation Control of Fire-Suppression Systems
25 54 00 Integrated Automation Control of Plumbing
25 55 00 Integrated Automation Control of HVAC
25 56 00 Integrated Automation Control of Electrical Systems
25 57 00 Integrated Automation Control of Communications Systems
25 58 00 Integrated Automation Control of Electronic Safety and Security Systems
25 90 00 Integrated Automation Control Sequences
25 91 00 Integrated Automation Control Sequences for Facility Equipment
25 92 00 Integrated Automation Control Sequences for Conveying Equipment
25 93 00 Integrated Automation Control Sequences for Fire- Suppression Systems
25 94 00 Integrated Automation Control Sequences for Plumbing
25 95 00 Integrated Automation Control Sequences for HVAC
25 96 00 Integrated Automation Control Sequences for Electrical Systems
25 97 00 Integrated Automation Control Sequences for Communications Systems
25 98 00 Integrated Automation Control Sequences for Electronic Safety and Security Systems
26 00 00 Electrical
26 01 00 Operation and Maintenance of Electrical Systems
26 01 10 Operation and Maintenance of Medium-Voltage Electrical Distribution
26 01 20 Operation and Maintenance of Low-Voltage Electrical Distribution
26 01 26 Maintenance Testing of Electrical Systems
26 01 30 Operation and Maintenance of Facility Electrical Power Generating and Storing Equipment
26 01 40 Operation and Maintenance of Electrical Protection Systems
26 01 40.13 Operation and Maintenance of Lightning Protection Systems
26 01 50 Operation and Maintenance of Lighting
26 01 50.51 Luminaire Relamping
26 01 50.81 Luminaire Replacement
26 05 00 Common Work Results for Electrical
26 05 05 Selective Demolition for Electrical
26 05 13 Medium-Voltage Cables
26 05 13.13 Medium-Voltage Open Conductors
26 05 13.16 Medium-Voltage, Single- and Multi-Conductor Cables
26 05 19 Low-Voltage Electrical Power Conductors and Cables
26 05 19.13 Undercarpet Electrical Power Cables
26 05 19.23 Manufactured Wiring Assemblies
26 05 23 Control-Voltage Electrical Power Cables
26 05 26 Grounding and Bonding for Electrical Systems
26 05 29 Hangers and Supports for Electrical Systems
26 05 33 Raceway and Boxes for Electrical Systems
26 05 33.13 Conduit for Electrical Systems
26 05 33.16 Boxes for Electrical Systems
26 05 33.23 Surface raceways for Electrical Systems
26 05 36 Cable Trays for Electrical Systems
26 05 39 Underfloor Raceways for Electrical Systems
26 05 43 Underground Ducts and Raceways for Electrical Systems
26 05 44 Sleeves and Sleeve Seals for Electrical Raceways and Cabling
26 05 46 Poles for Electrical Systems
26 05 48 Vibration and Seismic Controls for Electrical Systems
26 05 48.16 Seismic Controls for Electrical Systems
26 05 53 Identification for Electrical Systems
26 05 73 Power System Studies
26 05 73.13 Short-Circuit Studies
26 05 73.16 Coordination Studies
26 05 73.19 Arc-Flash Hazard Analysis
26 05 73.23 Load Flow Studies
26 05 73.26 Stability Studies
26 05 73.29 Harmonic-Analysis Studies
26 05 76 Photometric Studies
26 05 83 Wiring Connections
26 06 00 Schedules for Electrical
26 06 10 Schedules for Medium-Voltage Electrical Distribution
26 06 20 Schedules for Low-Voltage Electrical Distribution
26 06 20.13 Electrical Switchboard Schedule
26 06 20.16 Electrical Panelboard Schedule
26 06 20.19 Electrical Motor-Control Center Schedule
26 06 20.23 Electrical Circuit Schedule
26 06 20.26 Wiring Device Schedule
26 06 30 Schedules for Facility Electrical Power Generating and Storing Equipment
26 06 40 Schedules for Electrical Protection Systems
26 06 50 Schedules for Lighting
26 06 50.13 Lighting Panelboard Schedule
26 06 50.16 Lighting Fixture Schedule
26 08 00 Commissioning of Electrical Systems
26 09 00 Instrumentation and Control for Electrical Systems
26 09 13 Electrical Power Monitoring
26 09 15 Peak Load Controllers
26 09 16 Electrical Controls and Relays
26 09 17 Programmable Controllers
26 09 19 Enclosed Contactors
26 09 23 Lighting Control Devices
26 09 26 Lighting Control Panelboards
26 09 33 Central Dimming Controls
26 09 33.13 Multichannel Remote-Controlled Dimmers
26 09 33.16 Remote-Controlled Dimming Stations
26 09 36 Modular Dimming Controls
26 09 36.13 Manual Modular Dimming Controls
26 09 36.16 Integrated Multipreset Modular Dimming Controls
26 09 36.19 Standalone Multipreset Modular Dimming
26 09 43 Network Lighting Controls
26 09 43.13 Digital-Network Lighting Controls
26 09 43.16 Addressable Luminaire Lighting Controls
26 09 43.19 Wireless Network Lighting Controls
26 09 43.23 Relay-Based Lighting Controls
26 09 61 Theatrical Lighting Controls
26 10 00 Medium-Voltage Electrical Distribution
26 11 00 Substations
26 11 13 Primary Unit Substations
26 11 16 Secondary Unit Substations
26 11 16.11 Secondary Unit Substations with Switchgear Secondary
26 11 16.12 Secondary Unit Substations with Switchboard Secondary
26 11 16.13 Secondary Unit Substations with Motor Control Center Secondary
26 12 00 Medium-Voltage Transformers
26 12 13 Liquid-Filled, Medium-Voltage Transformers
26 12 16 Dry-Type, Medium-Voltage Transformers
26 12 19 Pad-Mounted, Liquid-Filled, Medium-Voltage Transformers
26 13 00 Medium-Voltage Switchgear
26 13 13 Medium-Voltage Circuit Breaker Switchgear
26 13 16 Medium-Voltage Fusible Interrupter Switchgear
26 13 19 Medium-Voltage Vacuum Interrupter Switchgear
26 13 23 Medium-Voltage Metal-Enclosed Switchgear
26 13 26 Medium-Voltage Metal-Clad Switchgear
26 13 29 Medium-Voltage Compartmentalized Switchgear
26 15 00 Medium-Voltage Enclosed Bus Assemblies
26 15 13 Medium-Voltage Busways
26 15 16 Medium-Voltage Cablebus
26 16 00 Medium-Voltage Metering
26 18 00 Medium-Voltage Circuit Protection Devices
26 18 13 Medium-Voltage Cutouts
26 18 16 Medium-Voltage Fuses
26 18 19 Medium-Voltage Lightning Arresters
26 18 23 Medium-Voltage Surge Arresters
26 18 26 Medium-Voltage Reclosers
26 18 29 Medium-Voltage Enclosed Bus
26 18 33 Medium-Voltage Enclosed Fuse Cutouts
26 18 36 Medium-Voltage Enclosed Fuses
26 18 39 Medium-Voltage Motor Controllers
26 20 00 Low-Voltage Electrical Distribution
26 21 00 Low-Voltage Electrical Service Entrance
26 21 13 Low-Voltage Overhead Electrical Service Entrance
26 21 16 Low-Voltage Underground Electrical Service Entrance
26 22 00 Low-Voltage Transformers
26 22 13 Low-Voltage Distribution Transformers
26 22 16 Low-Voltage Buck-Boost Transformers
26 22 17 Low-Voltage Transformers for Nonlinear Loads
26 22 18 Low-Voltage Transformers for Load Centers
26 22 19 Control and Signal Transformers
26 23 00 Low-Voltage Switchgear
26 23 13 Paralleling Low-Voltage Switchgear
26 24 00 Switchboards and Panelboards
26 24 13 Switchboards
26 24 16 Panelboards
26 24 16.16 Electronically Operated Circuit-Breaker Panelboards
26 24 19 Motor-Control Centers
26 25 00 Low-Voltage Enclosed Bus Assemblies
26 25 13 Low-Voltage Busways
26 25 16 Low-Voltage Cablebus Systems
26 27 00 Low-Voltage Distribution Equipment
26 27 13 Electricity Metering
26 27 16 Electrical Cabinets and Enclosures
26 27 19 Multi-Outlet Assemblies
26 27 23 Indoor Service Poles
26 27 26 Wiring Devices
26 27 33 Power Distribution Units
26 27 73 Door Chimes
26 28 00 Low-Voltage Circuit Protective Devices
26 28 13 Fuses
26 28 16 Enclosed Switches and Circuit Breakers
26 28 16.13 Enclosed Circuit Breakers
26 28 16.16 Enclosed Switches
26 29 00 Low-Voltage Controllers
26 29 13 Enclosed Controllers
26 29 13.13 Across-the-Line Motor Controllers
26 29 13.16 Reduced-Voltage Motor Controllers
26 29 23 Variable-Frequency Motor Controllers
26 29 33 Controllers for Fire Pump Drivers
26 29 33.13 Full-Service Controllers for Fire Pump Electric-Motor Drivers
26 29 33.16 Limited-Service Controllers for Fire Pump Electric-Motor Drivers
26 29 33.19 Controllers for Fire Pump Diesel Engine Drivers
26 30 00 Facility Electrical Power Generating and Storing Equipment
26 31 00 Photovoltaic Collectors
26 32 00 Packaged Generator Assemblies
26 32 13 Engine Generators
26 32 13.13 Diesel-Engine-Driven Generator Sets
26 32 13.16 Gas-Engine-Driven Generator Sets
26 32 13.26 Gas-Turbine Engine-Driven Generators
26 32 16 Steam-Turbine Generators
26 32 19 Hydro-Turbine Generators
26 32 23 Wind Energy Equipment
26 32 23.13 Horizontal-Axis Wind Turbines
26 32 23.16 Vertical-Axis Wind Turbines
26 32 26 Frequency Changers
26 32 29 Rotary Converters
26 32 33 Rotary Uninterruptible Power Units
26 32 36 Resistive Load Banks
26 33 00 Battery Equipment
26 33 13 Batteries
26 33 16 Battery Racks
26 33 19 Battery Units
26 33 23 Central Battery Equipment
26 33 23.13 Central Battery Equipment for Emergency Lighting
26 33 33 Static Power Converters
26 33 43 Battery Chargers
26 33 46 Battery Monitoring
26 33 53 Static Uninterruptible Power Supply
26 35 00 Power Filters and Conditioners
26 35 13 Capacitors
26 35 16 Chokes and Inductors
26 35 23 Electromagnetic-Interference Filters
26 35 26 Harmonic Filters
26 35 33 Power Factor Correction Equipment
26 35 33.13 Medium-Voltage Power Factor Correction Equipment
26 35 33.16 Low-Voltage Power Factor Correction Equipment
26 35 36 Slip Controllers
26 35 43 Static-Frequency Converters
26 35 46 Radio-Frequency-Interference Filters
26 35 53 Voltage Regulators
26 36 00 Transfer Switches
26 36 13 Manual Transfer Switches
26 36 23 Automatic Transfer Switches
26 40 00 Electrical Protection
26 41 00 Facility Lightning Protection
26 41 13 Lightning Protection for Structures
26 41 13.13 Lightning Protection for Buildings
26 41 16 Lightning Prevention and Dissipation
26 41 19 Early Streamer Emission Lightning Protection
26 41 23 Lightning Protection Surge Arresters and Suppressors
26 43 00 Surge Protective Devices
26 43 13 Surge Protective Devices for Low-Voltage Electrical Power Circuits
26 50 00 Lighting
26 51 00 Interior Lighting
26 51 13 Incandescent Interior Lighting
26 51 16 Fluorescent Interior Lighting
26 51 19 LED Interior Lighting
26 51 23 HID Interior Lighting
26 52 00 Safety Lighting
26 52 13 Emergency and Exit Lighting
26 52 13.13 Emergency Lighting
26 52 13.16 Exit Signs
26 54 00 Classified Location Lighting
26 54 13 Incandescent Classified Location Lighting
26 54 16 Fluorescent Classified Location Lighting
26 54 19 LED Classified Location Lighting
26 55 00 Special Purpose Lighting
26 55 23 Outline Lighting
26 55 29 Underwater Lighting
26 55 33 Hazard Warning Lighting
26 55 36 Obstruction Lighting
26 55 39 Helipad Lighting
26 55 53 Security Lighting
26 55 59 Display Lighting
26 55 61 Theatrical Lighting
26 55 63 Detention Lighting
26 55 68 Athletic Field Lighting
26 55 70 Healthcare Lighting
26 55 83 Broadcast Lighting
26 56 00 Exterior Lighting
26 56 13 Lighting Poles and Standards
26 56 17 Fluorescent Exterior Lighting
26 56 18 Incandescent Exterior Lighting
26 56 19 LED Exterior Lighting
26 56 21 HID Exterior Lighting
27 00 00 Communications
27 01 00 Operation and Maintenance of Communications Systems
27 01 10 Operation and Maintenance of Structured Cabling and Enclosures
27 01 20 Operation and Maintenance of Data Communications
27 01 30 Operation and Maintenance of Voice Communications
27 01 40 Operation and Maintenance of Audio-Video Communications
27 01 50 Operation and Maintenance of Distributed Communications and Monitoring
27 05 00 Common Work Results for Communications
27 05 05 Selective Demolition for Communications
27 05 11 Cameras for Audio-Visual Systems
27 05 13 Communications Services
27 05 13.13 Dialtone Services
27 05 13.23 T1 Services
27 05 13.33 DSL Services
27 05 13.43 Cable Services
27 05 13.53 Satellite Services
27 05 26 Grounding and Bonding for Communications Systems
27 05 28 Pathways for Communications Systems
27 05 29 Hangers and Supports for Communications Systems
27 05 33 Conduits and Backboxes for Communications Systems
27 05 36 Cable Trays for Communications Systems
27 05 39 Surface Raceways for Communications Systems
27 05 43 Underground Ducts and Raceways for Communications Systems
27 05 44 Sleeves and Sleeve Seals for Communications Pathways and Cabling
27 05 46 Utility Poles for Communications Systems
27 05 48 Vibration and Seismic Controls for Communications Systems
27 05 48.16 Seismic Controls for Communications Systems
27 05 53 Identification for Communications Systems
27 06 00 Schedules for Communications
27 06 10 Schedules for Structured Cabling and Enclosures
27 06 20 Schedules for Data Communications
27 06 30 Schedules for Voice Communications
27 06 40 Schedules for Audio-Video Communications
27 06 50 Schedules for Distributed Communications and Monitoring
27 08 00 Commissioning of Communications
27 10 00 Structured Cabling
27 11 00 Communications Equipment Room Fittings
27 11 13 Communications Entrance Protection
27 11 16 Communications Cabinets, Racks, Frames, and Enclosures
27 11 19 Communications Termination Blocks and Patch Panels
27 11 23 Communications Cable Management and Ladder Rack
27 11 26 Communications Rack Mounted Power Protection and Power Strips
27 13 00 Communications Backbone Cabling
27 13 13 Communications Copper Backbone Cabling
27 13 13.13 Communications Copper Cable Splicing and Terminations
27 13 23 Communications Optical Fiber Backbone Cabling
27 13 23.13 Communications Optical Fiber Splicing and Terminations
27 13 33 Communications Coaxial Backbone Cabling
27 13 33.13 Communications Coaxial Splicing and Terminations
27 13 43 Communications Services Cabling
27 13 43.13 Dialtone Services Cabling
27 13 43.23 T1 Services Cabling
27 13 43.33 DSL Services Cabling
27 13 43.43 Cable Services Cabling
27 13 43.53 Satellite Services Cabling
27 15 00 Communications Horizontal Cabling
27 15 01 Communications Horizontal Cabling Applications
27 15 01.11 Conductors and Cables for Electronic Safety and Security
27 15 01.13 Video Surveillance Communications Conductors and Cables
27 15 01.15 Access Control Communications Conductors and Cables
27 15 01.16 Voice Communications Horizontal Cabling
27 15 01.17 Intrusion Detection Communications Conductors and Cables
27 15 01.19 Fire Alarm Communications Conductors and Cables
27 15 01.23 Audio-Video Communications Horizontal Cabling
27 15 01.39 Patient Monitoring and Telemetry Communications Horizontal Cabling
27 15 01.43 Nurse Call and Intercom Communications Horizontal Cabling
27 15 01.46 Paging Communications Horizontal Cabling
27 15 01.49 Intermediate Frequency/Radio Frequency Communications Horizontal Cabling
27 15 01.53 Antennas Communications Horizontal Cabling
27 15 13 Communications Copper Horizontal Cabling
27 15 23 Communications Optical Fiber Horizontal Cabling
27 15 33 Communications Coaxial Horizontal Cabling
27 15 43 Communications Faceplates and Connectors
27 16 00 Communications Connecting Cords, Devices, and Adapters
27 16 13 Communications Custom Cable Assemblies
27 16 16 Communications Media Converters, Adapters, and Transceivers
27 16 19 Communications Patch Cords, Station Cords, and Cross Connect Wire
27 20 00 Data Communications
27 21 00 Data Communications Network Equipment
27 21 13 Data Communications Firewalls
27 21 16 Data Communications Routers, CSU/DSU, Multiplexers, Codecs, and Modems
27 21 26 Data Communications Network Management
27 21 29 Data Communications Switches and Hubs
27 21 33 Data Communications Wireless Access Points
27 22 00 Data Communications Hardware
27 22 13 Data Communications Mainframes
27 22 16 Data Communications Storage and Backup
27 22 19 Data Communications Servers
27 22 23 Data Communications Desktops
27 22 26 Data Communications Laptops
27 22 29 Data Communications Handhelds
27 24 00 Data Communications Peripheral Data Equipment
27 24 13 Printers
27 24 16 Scanners
27 24 19 External Drives
27 24 23 Audio-Video Devices
27 24 26 Virtual Reality Equipment
27 24 29 Disaster Recovery Equipment
27 25 00 Data Communications Software
27 25 13 Virus Protection Software
27 25 16 Application Suites
27 25 19 Email Software
27 25 23 Graphics/Multimedia Software
27 25 26 Customer Relationship Management Software
27 25 29 Operating System Software
27 25 33 Database Software
27 25 37 Virtual Private Network Software
27 25 39 Internet Conferencing Software
27 26 00 Data Communications Programming and Integration Services
27 26 13 Web Development
27 26 16 Database Development
27 26 19 Application Development
27 26 23 Network Integration Requirements
27 26 26 Data Communications Integration Requirements
27 30 00 Voice Communications
27 31 00 Voice Communications Switching and Routing Equipment
27 31 13 PBX/ Key Systems
27 31 23 Internet Protocol Voice Switches
27 32 00 Voice Communications Terminal Equipment
27 32 13 Telephone Sets
27 32 16 Wireless Transceivers
27 32 23 Elevator Telephones
27 32 26 Ring-Down Emergency Telephones
27 32 29 Facsimiles and Modems
27 32 36 TTY Equipment
27 32 43 Radio Communications Equipment
27 33 00 Voice Communications Messaging
27 33 16 Voice Mail and Auto Attendant
27 33 23 Interactive Voice Response
27 33 26 Facsimile Servers
27 34 00 Call Accounting
27 34 13 Toll Fraud Equipment and Software
27 34 16 Telemanagement Software
27 35 00 Call Management
27 35 13 Digital Voice Announcers
27 35 16 Automatic Call Distributors
27 35 19 Call Status and Management Displays
27 35 23 Dedicated 911 Systems
27 40 00 Audio-Video Communications
27 41 00 Audio-Video Systems
27 41 13 Architecturally Integrated Audio-Video Equipment
27 41 16 Integrated Audio-Video Systems and Equipment
27 41 16.25 Integrated Audio-Video Systems and Equipment for Restaurants and Bars
27 41 16.28 Integrated Audio-Video Systems and Equipment for Conference Rooms
27 41 16.29 Integrated Audio-Video Systems and Equipment for Board Rooms
27 41 16.51 Integrated Audio-Video Systems and Equipment for Classrooms
27 41 16.52 Integrated Audio-Video Systems and Equipment for Religious Facilities
27 41 16.61 Integrated Audio-Video Systems and Equipment for Theaters
27 41 16.62 Integrated Audio-Video Systems and Equipment for Auditoriums
27 41 16.63 Integrated Audio-Video Systems and Equipment for Stadiums and Arenas
27 41 19 Portable Audio-Video Equipment
27 41 23 Audio-Video Accessories
27 41 33 Master Antenna Television Systems
27 41 43 Audio-Video Conferencing
27 42 00 Electronic Digital Systems
27 42 13 Point of Sale Systems
27 42 16 Transportation Information Display Systems
27 42 19 Public Information Systems
27 50 00 Distributed Communications and Monitoring Systems
27 51 00 Distributed Audio-Video Communications Systems
27 51 13 Paging Systems
27 51 13.13 Overhead Paging Systems
27 51 16 Public Address Systems
27 51 19 Sound Masking Systems
27 51 23 Intercommunications and Program Systems
27 51 23.20 Commercial Intercommunications and Program Systems
27 51 23.30 Residential Intercommunications and Program Systems
27 51 23.50 Educational Intercommunications and Program Systems
27 51 23.63 Detention Intercommunications and Program Systems
27 51 23.70 Healthcare Intercommunications and Program Systems
27 51 26 Assistive Listening Systems
27 51 29 Emergency Communications Systems
27 52 00 Healthcare Communications and Monitoring Systems
27 52 13 Patient Monitoring and Telemetry Systems
27 52 16 Telemedicine Systems
27 52 19 Healthcare Imaging Systems
27 52 23 Nurse Call/Code Blue Systems
27 53 00 Distributed Systems
27 53 13 Clock Systems
27 53 13.13 Wireless Clock Systems
27 53 16 Infrared and Radio Frequency Tracking Systems
27 53 19 Internal Cellular, Paging, and Antenna Systems
28 00 00 Electronic Safety and Security
28 01 00 Operation and Maintenance of Electronic Safety and Security
28 01 10 Operation and Maintenance of Access Control
28 01 10.51 Maintenance and Administration of Access Control
28 01 10.71 Revisions and Upgrades of Access Control
28 01 20 Operation and Maintenance of Video Surveillance
28 01 20.51 Maintenance and Administration of Video Surveillance
28 01 20.71 Revisions and Upgrades of Video Surveillance
28 01 30 Operation and Maintenance of Security Detection, Alarm, and Monitoring
28 01 30.51 Maintenance and Administration of Security Detection, Alarm, and Monitoring
28 01 30.71 Revisions and Upgrades of Security Detection, Alarm, and Monitoring
28 01 50 Operation and Maintenance of Specialized Systems
28 01 50.51 Maintenance and Administration of Specialized Systems
28 01 50.71 Revisions and Upgrades of Specialized Systems
28 01 60 Operation and Maintenance of Mass Notification
28 01 60.51 Maintenance and Administration of Mass Notification
28 01 60.71 Revisions and Upgrades of Mass Notification
28 01 70 Operation and Maintenance of Life Safety
28 01 70.51 Maintenance and Administration of Life Safety
28 01 70.71 Revisions and Upgrades of Life Safety
28 01 80 Operation and Maintenance of Fire Detection and Alarm
28 01 80.51 Maintenance and Administration of Fire Detection and Alarm
28 01 80.71 Revisions and Upgrades of Fire Detection and Alarm
28 05 00 Common Work Results for Electronic Safety and Security
28 05 07 Power Sources for Electronic Safety and Security
28 05 07.11 Power Sources for Access Control
28 05 07.13 Power Sources for Video Surveillance
28 05 07.15 Power Sources for Intrusion Detection
28 05 07.17 Power Sources for Fire Detection and Alarm
28 05 07.19 Solar Power Sources for Electronic Safety and Security
28 05 07.21 Poe Power Sources for Electronic Safety and Security
28 05 07.23 Uninterruptible Power Supply
28 05 07.25 Power Source Monitoring
28 05 07.27 Power Source Monitoring Appliances
28 05 07.29 Power Source Monitoring Software
28 05 09 Surge Protection for Electronic Safety and Security
28 05 09.11 Surge Protection for Access Control
28 05 09.13 Surge Protection for Video Surveillance
28 05 09.15 Surge Protection for Intrusion Detection
28 05 09.17 Surge Protection for Fire Detection and Alarm
28 05 11 Cyber Security Requirements for Electronic Safety and Security
28 05 13 Servers, Workstations and Storage for Electronic Safety and Security
28 05 13.11 General Requirements for Servers, Workstations and Storage
28 05 15 Servers for Electronic Safety and Security
28 05 17 Workstations for Electronic Safety and Security
28 05 19 Storage Appliances for Electronic Safety and Security
28 05 19.11 Digital Video Recorders
28 05 19.13 Hybrid Digital Video Recorders
28 05 19.15 Network Video Recorders
28 05 21 Network Attached Storage for Electronic Safety and Security
28 05 23 Storage Area Network for Electronic Safety and Security
28 05 25 Cloud Based Storage for Electronic Safety and Security
28 05 27 Archival Systems for Electronic Safety and Security
28 05 27.11 Digital Tape Storage
28 05 27.13 Storage Media
28 05 29 Storage Management Software for Electronic Safety and Security
28 05 31 Communications Equipment for Electronic Safety and Security
28 05 33 Safety and Security Network Communications Equipment
28 05 33.11 Security Data Communications Firewalls
28 05 33.13 Security Data Communications Routers
28 05 33.15 Security Data Communications Power-Over-Ethernet Switches
28 05 33.17 Security Data Communications Non-Power-Over-Ethernet Switches
28 05 33.19 Security Data Communications Media Converters
28 05 35 Security Data Communications Wireless Transmission Equipment
28 05 35.11 Microwave Transmission Equipment
28 05 37 Security Voice Communications -Distributed Antenna System
28 05 37.11 Bi-Directional Amplifiers
28 05 37.13 Repeaters
28 05 37.15 Remote Repeaters
28 05 39 Antennas
28 05 39.11 Donor Antennas
28 05 39.13 Multi-Band Antennas
28 05 39.15 Band Specific Antennas
28 05 39.17 Radiating Coaxial Cable
28 05 39.19 Other Antennas
28 05 41 Signal Controllers
28 05 41.11 Splitters
28 05 41.13 Directional Couplers
28 05 43 Security Voice Communications Private Mobile Radio System
28 05 43.11 Base Station
28 05 43.13 Handheld Radio
28 05 45 Systems Integration and Interconnection Requirements
28 05 45.11 Mechanical
28 05 45.13 Electrical
28 05 45.15 Information
28 05 48 Vibration and Seismic Controls for Electronic Safety and Security
28 05 53 Identification for Electronic Safety and Security
28 06 00 Schedules for Electronic Safety and Security
28 06 10 Schedules for Access Control
28 06 20 Schedules for Video Surveillance
28 06 30 Schedules for Security Detection, Alarm, and Monitoring
28 06 40 Schedules for Detention Monitoring and Control
28 06 50 Schedules for Information Management and Display
28 06 60 Schedules for Mass Notification
28 06 70 Schedules for Life Safety
28 06 80 Schedules for Fire Detection and Alarm
28 08 00 Commissioning of Electronic Safety and Security
28 08 11 Testing for Baseline Performance Criteria
28 10 00 Access Control
28 11 00 Access Control Global Applications
28 12 01 General Requirements for Access Control Systems
28 13 00 Access Control Software and Database Management
28 13 11 Access Control Software
28 13 11.11 Access Control Operating Systems
28 13 11.13 Access Control Application Services
28 13 11.15 Access Control Mobile Applications
28 13 13 Access Control Software Interfaces
28 14 00 Access Control System Hardware
28 14 11 Access Control Network Controllers
28 14 13 Access Control Door Controllers
28 14 15 Access Control Inputs and Outputs
28 14 17 Access Control Printers and Encoders
28 14 19 Access Control Enclosures
28 15 00 Access Control Hardware Devices
28 15 11 Integrated Credential Readers and Field Entry Management
28 15 11.11 Standard Card Readers
28 15 11.13 Keypads
28 15 11.15 Biometric Identity Devices
28 15 11.17 Combination Reader Devices
28 15 13 Access Control Credentials
28 15 13.11 Access Control Cards
28 15 13.13 Wireless Key Fobs
28 15 15 Electrified Locking Devices & Accessories
28 15 15.11 Direct Interface Integrated Locking Devices
28 15 15.13 Wireless Integrated Locking Devices
28 15 15.15 Intelligent Ethernet Integrated Locking Devices
28 15 15.17 Status Monitoring and Egress Devices
28 15 17 Egress Management Devices
28 15 17.11 Magnetic Lock Delayed Egress Devices
28 15 17.13 Panic Hardware Delayed Egress Devices
28 15 19 Access Control Remote Devices
28 15 19.11 Smart Phone Interface Requirements
28 15 19.13 Wireless Access Control Devices
28 15 21 Telephone Entry Systems
28 15 23 Intercom Entry Systems
28 15 23.11 Audio Intercom (Analog)
28 15 23.13 Audio Video Intercom (Analog)
28 15 23.15 Audio Intercom (IP)
28 15 23.17 Audio Video Intercom (IP)
28 15 25 Electronic Key Management Systems
28 15 27 Access Control Electronic Turnstiles & Mobility Systems
28 16 00 Access Control Interfaces
28 16 11 Access Control Interfaces to Access Control Hardware
28 16 13 Access Control Interfaces to Intrusion Detection
28 16 15 Access Control Interfaces to Video Surveillance
28 16 17 Access Control Interfaces to Fire Alarm
28 16 19 Access Control Interfaces to Enterprise Software
28 16 21 Access Control Interfaces to Mechanical Systems
28 16 23 Access Control Interfaces to Electrical Systems
28 16 25 Access Control Interfaces to Electronic Key Management System
28 16 27 Access Control Interfaces to Elevator Controls
28 16 29 Access Control Interfaces to Parking Equipment
28 16 31 Access Control Interfaces to Perimeter Security Systems
28 17 00 Access Control Identification Management Systems
28 17 11 Visitor Management Systems
28 17 13 Self Check In and Kiosk Visitor Systems
28 17 15 Contractor & Vendor Management Systems
28 17 17 Mobile Access Identification Management Systems
28 18 00 Security Access Detection Equipment
28 18 11 Security Access Metal Detectors
28 18 13 Security Access X-Ray Equipment
28 18 15 Security Access Explosive Detection Equipment
28 18 17 Security Access Sniffing Equipment
28 19 00 Access Control Vehicle Identification Systems
28 19 11 Loading Dock Access Management Systems
28 19 13 Parking Garage Access Management Systems
28 19 15 Perimeter Vehicle Access Management Systems
28 20 00 Video Surveillance
28 21 00 Surveillance Cameras
28 21 11 Analog Camera
28 21 13 IP Cameras
28 21 13.11 Panoramic IP Cameras
28 21 15 Specialty Cameras
28 21 17 Camera Housings
28 21 19 Camera Mounts
28 21 21 Illuminators
28 23 00 Video Management System
28 23 11 Video Management System Analytics
28 23 13 Video Management System Interfaces
28 25 00 Video Surveillance Positioning Equipment
28 27 00 Video Surveillance Sensors
28 30 00 Security Detection, Alarm, and Monitoring
28 31 00 Intrusion Detection
28 31 11 Building Intrusion Detection
28 31 11.11 Building Intrusion Detection Control, Gui, and Logic Systems
28 31 11.13 Building Intrusion Detection Remote Devices and Sensors
28 31 21 Area and Perimeter Intrusion Detection
28 31 21.11 Fiber Optic Area and Perimeter Security Systems
28 31 21.13 Microwave Area and Perimeter Security Systems
28 31 21.15 Integrated Video Area and Perimeter Security Systems
28 31 21.17 Fixed Optical Beam Area and Perimeter Security Systems
28 31 21.19 Lidar Area and Perimeter Security Systems
28 31 21.21 Coaxial Area and Perimeter Security Systems
28 31 21.23 Area and Perimeter Intrusion Detection Devices and Sensors
28 31 31 Intrusion Detection Interfaces
28 31 31.11 Intrusion Detection Interfaces to Security Monitoring and Control
28 31 31.13 Intrusion Detection Interfaces to Access Control System
28 31 31.15 Intrusion Detection Interfaces to Video Surveillance
28 31 31.17 Intrusion Detection Interfaces to Information Management and Presentation
28 31 31.19 Intrusion Detection Interfaces to Mass Notification
28 31 31.21 Intrusion Detection Interfaces to Life Safety
28 31 31.23 Intrusion Detection Interfaces to Fire Alarm
28 31 31.25 Intrusion Detection Interfaces to Temperature Controls
28 33 00 Security Monitoring and Control
28 33 11 Electronic Structural Monitoring Systems
28 33 13 Security Operations and Monitoring Center
28 33 15 Security Monitoring and Control Software
28 33 17 Security Monitoring and Control Services
28 35 00 Tracking Systems
28 35 11 Asset Tracking Systems
28 35 11.11 Rf Asset Tracking Systems
28 35 11.13 GPS Asset Tracking Systems
28 35 11.15 Cellular Asset Tracking Systems
28 35 13 Personnel Tracking Systems
28 35 13.11 Rf Personnel Tracking Systems
28 35 13.13 GPS Personnel Tracking Systems
28 35 13.15 Cellular Personnel Tracking Systems
28 37 00 Audio Monitoring
28 37 11 Audio Monitoring Devices
28 40 00 Life Safety
28 41 00 Radiation Detection and Alarm
28 41 11 Radiation Detection and Alarm Control, Gui, and Logic Systems
28 41 13 Radiation Detection and Alarm Integrated Audio Evacuation Systems
28 41 15 Radiation Detection Sensors
28 41 17 Radiation Dosimeters
28 42 00 Gas Detection and Alarm
28 42 11 Gas Detection and Alarm Control, Gui, and Logic Systems
28 42 13 Gas Detection and Alarm Integrated Audio Evacuation Systems
28 42 15 Gas Detection Sensors
28 43 00 Fuel Oil Detection and Alarm
28 43 11 Fuel Oil Detection and Alarm Control, Gui, and Logic Systems
28 43 13 Fuel Oil Detection and Alarm Integrated Audio Evacuation Systems
28 43 15 Fuel Oil Detection Sensors
28 44 00 Refrigerant Detection and Alarm
28 44 11 Refrigerant Detection and Alarm Control, Gui, and Logic Systems
28 44 13 Refrigerant Detection and Alarm Integrated Audio Evacuation Systems
28 44 15 Refrigerant Detection Sensors
28 45 00 Water Detection and Alarm
28 45 11 Water Detection and Alarm Control, Gui, and Logic Systems
28 45 13 Water Detection Sensors
28 45 15 Building Envelope Water Detection and Alarm
28 46 00 Fire Detection and Alarm
28 46 10 Detection and Initiation
28 46 11 Fire Sensors and Detectors
28 46 11.11 Linear Heat Detection Sensors
28 46 11.13 Spot-Type Heat Detection Sensors
28 46 11.15 Duct Smoke Detection Sensors
28 46 11.17 Beam Smoke Detection Sensors
28 46 11.19 Video Smoke Detection Sensors
28 46 11.21 Carbon-Monoxide Detection Sensors
28 46 11.23 Combination Sensors
28 46 11.25 Air Sampling Systems
28 46 11.27 Other Sensors
28 46 12 Other Initiating Devices
28 46 12.11 Fire Alarm Pull Stations
28 46 12.13 Fire Alarm Level Detector Switches
28 46 12.15 Fire Alarm Flow Switches
28 46 12.17 Fire Alarm Pressure Sensors
28 46 12.19 Sprinkler Supervisory Devices
28 46 20 Fire Alarm
28 46 21.11 Addressable Fire-Alarm Systems
28 46 21.13 Conventional Fire-Alarm Systems
28 46 21.15 Protected Premise Systems
28 46 21.17 Proprietary Systems
28 46 21.19 Central Station Systems
28 46 21.21 Remote Station Systems
28 46 21.23 Public Emergency Alarm Reporting Systems
28 46 22 Network Command Centers, Printers and Peripherals for Fire Systems
28 46 23 Fire Alarm Notification Appliances
28 46 23.11 Fire Alarm Horns and Strobes
28 46 23.13 Fire Alarm Speakers
28 46 23.15 Fire Alarm Low Frequency Sounders
28 46 23.17 Wide Band Sounders
28 46 24 Fire Detection and Alarm Emergency Control Function Interfaces
28 46 24.11 Fire Detection and Alarm Interfaces to Remote Monitoring
28 46 24.13 Fire Detection and Alarm Interfaces to Access Control Hardware
28 46 24.15 Fire Detection and Alarm Interfaces to Access Control System
28 46 24.17 Fire Detection and Alarm Interfaces to Intrusion Detection
28 46 24.19 Fire Detection and Alarm Interfaces to Video Surveillance
28 46 24.21 Fire Detection and Alarm Interfaces to Elevator Control
28 46 24.23 Other Fire Detection and Alarm Interfaces
28 47 00 Mass Notification
28 47 11 General Requirements for Mass Notification
28 47 13 Mass Notification Software
28 47 15 Mass Notification Control Panels
28 47 17 Notification Devices and Methods
28 47 17.11 Notification Appliances and Methods Indoors
28 47 17.13 Notification Appliances and Methods Outdoors
28 47 17.15 Notification Appliances and Methods Distributed Recipient
28 47 17.17 Notification Appliances and Methods Public Methods
28 47 21 Mass Notification System Interfaces
28 47 21.11 Notification Interfaces to Access Control Systems
28 47 21.13 Notification Interfaces to Video Surveillance Systems
28 47 21.15 Notification Interfaces to Security Detection, Alarm, and Monitoring
28 47 21.17 Notification Interfaces to Security Monitoring and Control
28 47 21.19 Notification Interfaces to Life Safety Systems
28 47 21.21 Notification Interfaces to Fire Detection and Alarm
28 47 21.23 Notification Interfaces to Detention Systems
28 47 21.25 Notification Interfaces to Emergency Response Systems
28 47 21.27 Notification Interfaces to Network and Facilities Monitoring
28 47 21.29 Notification Interfaces to Web Intelligence
28 47 21.31 Notification Interfaces to Traffic Management and Monitoring Systems
28 47 21.33 Notification Interfaces to Smart Phones
28 47 21.35 Notification Interfaces to Other External Subsystems
28 48 00 Emergency Response Systems
28 48 23 Computer Aided Dispatch
28 49 00 Electronic Personal Protection Systems
28 49 11 Electronic Personal Safety Detection Systems
28 49 13 Electronic Personal Safety Alarm Annunciation and Control Systems
28 49 15 Electronic Personal Safety Interfaces to Remote Monitoring
28 49 17 Electronic Personal Safety Emergency Aid Devices
28 50 00 Specialized Systems
28 51 00 Information Management & Presentation
28 51 11 Information Management & Presentation Architecture
28 51 13 Data and Information Management
28 51 15 Information Interfaces to Connected Subsystems
28 51 15.11 Information Interfaces to Access Control Systems
28 51 15.13 Information Interfaces to Video Surveillance Systems
28 51 15.15 Information Interfaces to Security Detection, Alarm, and Monitoring
28 51 15.17 Information Interfaces to Security Monitoring and Control
28 51 15.19 Information Interfaces to Mass Notification Systems
28 51 15.21 Information Interfaces to Life Safety Systems
28 51 15.23 Information Interfaces to Fire Detection and Alarm
28 51 15.25 Information Interfaces to Detention Systems
28 51 15.27 Information Interfaces to Emergency Response Systems
28 51 15.29 Information Interfaces to License Plate Recognition Systems
28 51 15.31 Information Interfaces to Facial Recognition Systems
28 51 15.33 Information Interfaces to Remote Data Structures
28 51 15.35 Information Interfaces to Network and Facilities Monitoring
28 51 15.37 Information Interfaces to Crowd Sourcing
28 51 15.39 Information Interfaces to Web Intelligence
28 51 15.41 Information Interfaces to Traffic Management and Monitoring Systems
28 51 15.43 Information Interfaces to Environmental Monitoring Systems
28 51 15.45 Information Interfaces to Directly Connected Sensors
28 51 15.47 Information Interfaces to Other Safety and Security Subsystems
28 51 15.49 Information Interfaces to Other External Subsystems
28 51 17 Data Presentation
28 51 17.11 Maps
28 51 17.13 Visualization
28 51 17.15 Events/Alarms/Incidents
28 51 17.17 Video Workspace
28 51 17.19 Dispatch/Notification
28 51 17.21 Review and Investigation
28 51 17.23 Reporting
28 51 19 Control Room and Monitoring Equipment
28 51 19.11 Display/Workstations
28 51 19.13 Video Walls
28 51 19.15 Audio Equipment
28 51 19.17 Remote Displays
28 52 00 Detention Security Systems
28 52 11 Detention Monitoring and Control Systems
28 52 13 Detention Interfaces to Connected Subsystems
28 52 13.11 Detention Interfaces to Access Control Systems
28 52 13.13 Detention Interfaces to Video Surveillance Systems
28 52 13.15 Detention Interfaces to Security Detention, Alarm, and Monitoring
28 52 13.17 Detention Interfaces to Security Monitoring and Control
28 52 13.19 Detention Interfaces to Duress Alarm Systems
28 52 13.21 Detention Interfaces to Distributed Television Systems
28 52 13.23 Detention Interfaces to Perimeter Security Systems
28 52 15 Video Support Systems for Detention
28 52 15.11 Video Interrogation System
28 52 15.13 Video Arraignment System
28 52 15.15 Video Visitation System
31 00 00 Earthwork
31 01 00 Maintenance of Earthwork
31 01 10 Maintenance of Clearing
31 01 20 Maintenance of Earth Moving
31 01 40 Maintenance of Shoring and Underpinning
31 01 50 Maintenance of Excavation Support and Protection
31 01 60 Maintenance of Special Foundations and Load Bearing Elements
31 01 62 Maintenance of Driven Piles
31 01 62.61 Driven Pile Repairs
31 01 63 Maintenance of Bored and Augered Piles
31 01 63.61 Bored and Augered Pile Repairs
31 01 70 Maintenance of Tunneling and Mining
31 01 70.61 Tunnel Leak Repairs
31 05 00 Common Work Results for Earthwork
31 05 05 Selective Demolition for Earthwork
31 05 13 Soils for Earthwork
31 05 16 Aggregates for Earthwork
31 05 19 Geosynthetics for Earthwork
31 05 19.13 Geotextiles for Earthwork
31 05 19.16 Geomembranes for Earthwork
31 05 19.19 Geogrids for Earthwork
31 05 19.23 Geosynthetic Clay Liners
31 05 19.26 Geocomposites
31 05 19.29 Geonets
31 05 23 Cement and Concrete for Earthwork
31 06 00 Schedules for Earthwork
31 06 10 Schedules for Clearing
31 06 20 Schedules for Earth Moving
31 06 20.13 Trench Dimension Schedule
31 06 20.16 Backfill Material Schedule
31 06 40 Schedules for Shoring and Underpinning
31 06 50 Schedules for Excavation Support and Protection
31 06 60 Schedules for Special Foundations and Load Bearing Elements
31 06 60.13 Driven Pile Schedule
31 06 60.16 Caisson Schedule
31 06 70 Schedules for Tunneling and Mining
31 08 00 Commissioning of Earthwork
31 08 13 Pile Load Testing
31 08 13.13 Dynamic Pile Load Testing
31 08 13.16 Static Pile Load Testing
31 09 00 Geotechnical Instrumentation and Monitoring of Earthwork
31 09 13 Geotechnical Instrumentation and Monitoring
31 09 13.13 Groundwater Monitoring During Construction
31 09 16 Foundation Performance Instrumentation
31 09 16.26 Bored and Augered Pile Load Tests
31 10 00 Site Clearing
31 11 00 Clearing and Grubbing
31 12 00 Selective Clearing
31 13 00 Selective Tree and Shrub Removal and Trimming
31 13 13 Selective Tree and Shrub Removal
31 13 16 Selective Tree and Shrub Trimming
31 14 00 Earth Stripping and Stockpiling
31 14 13 Soil Stripping and Stockpiling
31 14 13.13 Soil Stripping
31 14 13.16 Soil Stockpiling
31 14 13.23 Topsoil Stripping and Stockpiling
31 14 16 Sod Stripping and Stockpiling
31 14 16.13 Sod Stripping
31 14 16.16 Sod Stockpiling
31 20 00 Earth Moving
31 21 00 Off-Gassing Mitigation
31 21 13 Radon Mitigation
31 21 13.13 Radon Venting
31 21 16 Methane Mitigation
31 21 16.13 Methane Venting
31 22 00 Grading
31 22 13 Rough Grading
31 22 16 Fine Grading
31 22 16.13 Roadway Subgrade Reshaping
31 22 19 Finish Grading
31 22 19.13 Spreading and Grading Topsoil
31 23 00 Excavation and Fill
31 23 13 Subgrade Preparation
31 23 16 Excavation
31 23 16.13 Trenching
31 23 16.16 Structural Excavation for Minor Structures
31 23 16.26 Rock Removal
31 23 19 Dewatering
31 23 23 Fill
31 23 23.13 Backfill
31 23 23.23 Compaction
31 23 23.33 Flowable Fill
31 23 23.43 Geofoam
31 23 33 Trenching and Backfilling
31 24 00 Embankments
31 24 13 Roadway Embankments
31 24 16 Railway Embankments
31 25 00 Erosion and Sedimentation Controls
31 25 14 Stabilization Measures for Erosion and Sedimentation Control
31 25 14.13 Hydraulically-Applied Erosion Control
31 25 14.16 Rolled Erosion Control Mats and Blankets
31 25 24 Structural Measures for Erosion and Sedimentation Control
31 25 24.13 Rock Barriers
31 25 34 Retention Measures for Erosion and Sedimentation Controls
31 25 34.13 Rock Basins
31 30 00 Earthwork Methods
31 31 00 Soil Treatment
31 31 13 Rodent Control
31 31 13.16 Rodent Control Bait Systems
31 31 13.19 Rodent Control Traps
31 31 13.23 Rodent Control Electronic Systems
31 31 13.26 Rodent Control Repellants
31 31 16 Termite Control
31 31 16.13 Chemical Termite Control
31 31 16.16 Termite Control Bait Systems
31 31 16.19 Termite Control Barriers
31 31 19 Vegetation Control
31 31 19.13 Chemical Vegetation Control
31 31 33 Sanitary Vacuum System Piping
31 32 00 Soil Stabilization
31 32 13 Soil Mixing Stabilization
31 32 13.13 Asphalt Soil Stabilization
31 32 13.16 Cement Soil Stabilization
31 32 13.19 Lime Soil Stabilization
31 32 13.23 Fly-Ash Soil Stabilization
31 32 13.26 Lime-Fly-Ash Soil Stabilization
31 32 16 Chemical Treatment Soil Stabilization
31 32 16.13 Polymer Emulsion Soil Stabilization
31 32 17 Water Injection Soil Stabilization
31 32 19 Geosynthetic Soil Stabilization and Layer Separation
31 32 19.13 Geogrid Soil Stabilization
31 32 19.16 Geotextile Soil Stabilization
31 32 19.19 Geogrid Layer Separation
31 32 19.23 Geotextile Layer Separation
31 32 23 Pressure Grouting Soil Stabilization
31 32 23.13 Cementitious Pressure Grouting Soil Stabilization
31 32 23.16 Chemical Pressure Grouting Soil Stabilization
31 32 33 Shotcrete Soil Slope Stabilization
31 32 36 Soil Nailing
31 32 36.13 Driven Soil Nailing
31 32 36.16 Grouted Soil Nailing
31 32 36.19 Corrosion-Protected Soil Nailing
31 32 36.23 Jet-Grouted Soil Nailing
31 32 36.26 Launched Soil Nailing
31 33 00 Rock Stabilization
31 33 13 Rock Bolting and Grouting
31 33 23 Rock Slope Netting
31 33 26 Rock Slope Wire Mesh
31 33 33 Shotcrete Rock Slope Stabilization
31 33 43 Vegetated Rock Slope Stabilization
31 34 00 Soil Reinforcement
31 34 19 Geosynthetic Soil Reinforcement
31 34 19.13 Geogrid Soil Reinforcement
31 34 19.16 Geotextile Soil Reinforcement
31 34 23 Fiber Soil Reinforcement
31 34 23.13 Geosynthetic Fiber Soil Reinforcement
31 35 00 Slope Protection
31 35 19 Geosynthetic Slope Protection
31 35 19.13 Geogrid Slope Protection
31 35 19.16 Geotextile Slope Protection
31 35 19.19 Slope Protection with Mulch Control Netting
31 35 23 Slope Protection with Slope Paving
31 35 23.13 Cast-In-Place Concrete Slope Paving
31 35 23.16 Precast Concrete Slope Paving
31 35 23.19 Concrete Unit Masonry Slope Paving
31 35 26 Containment Barriers
31 35 26.13 Clay Containment Barriers
31 35 26.16 Geomembrane Containment Barriers
31 35 26.23 Bentonite Slurry Trench
31 36 00 Gabions
31 36 13 Gabion Boxes
31 36 19 Gabion Mattresses
31 36 19.13 Vegetated Gabion Mattresses
31 37 00 Riprap
31 37 13 Machined Riprap
31 37 16 Non-Machined Riprap
31 37 16.13 Rubble-Stone Riprap
31 37 16.16 Concrete Unit Masonry Riprap
31 37 16.19 Sacked Sand-Cement Riprap
31 40 00 Shoring and Underpinning
31 41 00 Shoring
31 41 13 Timber Shoring
31 41 16 Sheet Piling
31 41 16.13 Steel Sheet Piling
31 41 16.16 Plastic Sheet Piling
31 41 19 Metal Hydraulic Shoring
31 41 19.13 Aluminum Hydraulic Shoring
31 41 23 Pneumatic Shoring
31 41 33 Trench Shielding
31 43 00 Concrete Raising
31 43 13 Pressure Grouting
31 43 13.13 Concrete Pressure Grouting
31 43 13.16 Polyurethane Pressure Grouting
31 43 16 Compaction Grouting
31 43 19 Mechanical Jacking
31 45 00 Vibroflotation and Densification
31 45 13 Vibroflotation
31 45 16 Densification
31 46 00 Needle Beams
31 46 13 Cantilever Needle Beams
31 48 00 Underpinning
31 48 13 Underpinning Piers
31 48 19 Bracket Piers
31 48 23 Jacked Piers
31 48 33 Micropile Underpinning
31 50 00 Excavation Support and Protection
31 51 00 Anchor Tiebacks
31 51 13 Excavation Soil Anchors
31 51 16 Excavation Rock Anchors
31 52 00 Cofferdams
31 52 13 Sheet Piling Cofferdams
31 52 16 Timber Cofferdams
31 52 19 Precast Concrete Cofferdams
31 53 00 Cribbing and Walers
31 53 13 Timber Cribwork
31 54 00 Ground Freezing
31 56 00 Slurry Walls
31 56 13 Bentonite Slurry Walls
31 56 13.13 Soil-Bentonite Slurry Walls
31 56 13.16 Cement-Bentonite Slurry Walls
31 56 13.19 Slag-Cement-Bentonite Slurry Walls
31 56 13.23 Soil-Cement-Bentonite Slurry Walls
31 56 13.26 Pozzolan-Bentonite Slurry Walls
31 56 13.29 Organically-Modified Bentonite Slurry Walls
31 56 16 Attipulgite Slurry Walls
31 56 16.13 Soil-Attipulgite Slurry Walls
31 56 19 Slurry-Geomembrane Composite Slurry Walls
31 56 23 Lean Concrete Slurry Walls
31 56 26 Bio-Polymer Trench Drain
31 60 00 Special Foundations and Load-Bearing Elements
31 62 00 Driven Piles
31 62 13 Concrete Piles
31 62 13.13 Cast-in-Place Concrete Piles
31 62 13.16 Concrete Displacement Piles
31 62 13.19 Precast Concrete Piles
31 62 13.23 Prestressed Concrete Piles
31 62 13.26 Pressure-Injected Footings
31 62 16 Steel Piles
31 62 16.13 Sheet Steel Piles
31 62 16.16 Steel H Piles
31 62 16.19 Unfilled Tubular Steel Piles
31 62 19 Timber Piles
31 62 23 Composite Piles
31 62 23.13 Concrete-Filled Steel Piles
31 62 23.16 Wood and Cast-In-Place Concrete Piles
31 63 00 Bored Piles
31 63 13 Bored and Augered Test Piles
31 63 16 Auger Cast Grout Piles
31 63 19 Bored and Socketed Piles
31 63 19.13 Rock Sockets for Piles
31 63 23 Bored Concrete Piles
31 63 23.13 Bored and Belled Concrete Piles
31 63 23.16 Bored Friction Concrete Piles
31 63 26 Drilled Caissons
31 63 26.13 Fixed End Caisson Piles
31 63 26.16 Concrete Caissons for Marine Construction
31 63 29 Drilled Concrete Piers and Shafts
31 63 29.13 Uncased Drilled Concrete Piers
31 63 29.16 Cased Drilled Concrete Piers
31 63 33 Drilled Micropiles
31 64 00 Caissons
31 64 13 Box Caissons
31 64 16 Excavated Caissons
31 64 19 Floating Caissons
31 64 23 Open Caissons
31 64 26 Pneumatic Caissons
31 64 29 Sheeted Caissons
31 66 00 Special Foundations
31 66 13 Special Piles
31 66 13.13 Rammed Aggregate Piles
31 66 15 Helical Foundation Piles
31 66 16 Special Foundation Walls
31 66 16.13 Anchored Foundation Walls
31 66 16.23 Concrete Cribbing Foundation Walls
31 66 16.26 Metal Cribbing Foundation Walls
31 66 16.33 Manufactured Modular Foundation Walls
31 66 16.43 Mechanically Stabilized Earth Foundation Walls
31 66 16.46 Slurry Diaphragm Foundation Walls
31 66 16.53 Soldier-Beam Foundation Walls
31 66 16.56 Permanently-Anchored Soldier-Beam Foundation Walls
31 66 19 Refrigerated Foundations
31 68 00 Foundation Anchors
31 68 13 Rock Foundation Anchors
31 68 16 Helical Foundation Anchors
31 70 00 Tunneling and Mining
31 71 00 Tunnel Excavation
31 71 13 Shield Driving Tunnel Excavation
31 71 16 Tunnel Excavation by Drilling and Blasting
31 71 19 Tunnel Excavation by Tunnel Boring Machine
31 71 23 Tunneling by Cut and Cover
31 72 00 Tunnel Support Systems
31 72 13 Rock Reinforcement and Initial Support
31 72 16 Steel Ribs and Lagging
31 73 00 Tunnel Grouting
31 73 13 Cement Tunnel Grouting
31 73 16 Chemical Tunnel Grouting
31 74 00 Tunnel Construction
31 74 13 Cast-in-Place Concrete Tunnel Lining
31 74 16 Precast Concrete Tunnel Lining
31 74 19 Shotcrete Tunnel Lining
31 75 00 Shaft Construction
31 75 13 Cast-in-Place Concrete Shaft Lining
31 75 16 Precast Concrete Shaft Lining
31 77 00 Submersible Tube Tunnels
31 77 13 Trench Excavation for Submerged Tunnels
31 77 16 Tube Construction (Outfitting Tunnel Tubes)
31 77 19 Floating and Laying Submerged Tunnels
32 00 00 Exterior Improvements
32 01 00 Operation and Maintenance of Exterior Improvements
32 01 11 Paving Cleaning
32 01 11.51 Rubber and Paint Removal from Paving
32 01 11.52 Rubber Removal from Paving
32 01 11.53 Paint Removal from Paving
32 01 13 Flexible Paving Surface Treatment
32 01 13.61 Slurry Seal (Latex Modified)
32 01 13.62 Asphalt Surface Treatment
32 01 16 Flexible Paving Rehabilitation
32 01 16.71 Cold Milling Asphalt Paving
32 01 16.72 Asphalt Paving Reuse
32 01 16.73 In Place Cold Reused Asphalt Paving
32 01 16.74 In Place Hot Reused Asphalt Paving
32 01 16.75 Heater Scarifying of Asphalt Paving
32 01 17 Flexible Paving Repair
32 01 17.61 Sealing Cracks in Asphalt Paving
32 01 17.62 Stress-Absorbing Membrane Interlayer
32 01 19 Rigid Paving Surface Treatment
32 01 19.61 Sealing of Joints in Rigid Paving
32 01 19.62 Patching of Rigid Paving
32 01 23 Base Course Reconditioning
32 01 26 Rigid Paving Rehabilitation
32 01 26.71 Grooving of Concrete Paving
32 01 26.72 Grinding of Concrete Paving
32 01 26.73 Milling of Concrete Paving
32 01 26.74 Concrete Overlays
32 01 26.75 Concrete Paving Reuse
32 01 29 Rigid Paving Repair
32 01 29.61 Partial Depth Patching of Rigid Paving
32 01 29.62 Concrete Paving Raising
32 01 29.63 Subsealing and Stabilization
32 01 30 Operation and Maintenance of Site Improvements
32 01 30.13 Snow Removal
32 01 80 Operation and Maintenance of Irrigation
32 01 90 Operation and Maintenance of Planting
32 01 90.13 Fertilizing
32 01 90.16 Amending Soils
32 01 90.19 Mowing
32 01 90.23 Pruning
32 01 90.26 Watering
32 01 90.29 Topsoil Preservation
32 01 90.33 Tree and Shrub Preservation
32 05 00 Common Work Results for Exterior Improvements
32 05 05 Selective Demolition for Exterior Improvements
32 05 13 Soils for Exterior Improvements
32 05 16 Aggregates for Exterior Improvements
32 05 19 Geosynthetics for Exterior Improvements
32 05 19.13 Geotextiles for Exterior Improvements
32 05 19.16 Geomembranes for Exterior Improvements
32 05 19.19 Geogrids for Exterior Improvements
32 05 23 Cement and Concrete for Exterior Improvements
32 05 33 Common Work Results for Planting
32 06 00 Schedules for Exterior Improvements
32 06 10 Schedules for Bases, Ballasts, and Paving
32 06 10.13 Pedestrian Walkway Schedule
32 06 30 Schedules for Site Improvements
32 06 30.13 Retaining Wall Schedule
32 06 80 Schedules for Irrigation
32 06 80.13 Irrigation Piping Schedule
32 06 90 Schedules for Planting
32 06 90.13 Planting Schedule
32 08 00 Commissioning of Exterior Improvements
32 10 00 Bases, Ballasts, and Paving
32 11 00 Base Courses
32 11 13 Subgrade Modifications
32 11 13.13 Lime-Treated Subgrades
32 11 13.16 Bituminous-Treated Subgrades
32 11 16 Subbase Courses
32 11 16.13 Sand-Clay Subbase Courses
32 11 16.16 Aggregate Subbase Courses
32 11 23 Aggregate Base Courses
32 11 23.13 Sand-Clay Base Courses
32 11 23.23 Base Course Drainage Layers
32 11 26 Asphaltic Base Courses
32 11 26.13 Plant Mix Asphaltic Base Courses
32 11 26.16 Road Mix Asphaltic Base Courses
32 11 26.19 Bituminous-Stabilized Base Courses
32 11 29 Lime Treated Base Courses
32 11 29.13 Lime-Fly Ash-Treated Base Courses
32 11 33 Cement-Treated Base Courses
32 11 33.13 Portland Cement-Stabilized Base Courses
32 11 36 Concrete Base Courses
32 11 36.11 Soil-Cement Concrete Base Courses
32 11 36.13 Lean Concrete Base Courses
32 11 36.16 Plain Cement Concrete Base Courses
32 11 36.19 Hydraulic Cement Concrete Base Courses
32 11 39 Shell Base Course
32 12 00 Flexible Paving
32 12 13 Preparatory Coats
32 12 13.13 Tack Coats
32 12 13.16 Asphaltic Tack Coats
32 12 13.19 Prime Coats
32 12 13.23 Asphaltic Prime Coats
32 12 16 Asphalt Paving
32 12 16.13 Plant-Mix Asphalt Paving
32 12 16.16 Road-Mix Asphalt Paving
32 12 16.19 Cold-Mix Asphalt Paving
32 12 16.23 Reinforced Asphalt Paving
32 12 16.26 Fiber-Modified Asphalt Paving
32 12 16.29 Polymer-Modified Asphalt Paving
32 12 16.33 Granulated Rubber-Modified Asphalt Paving
32 12 16.36 Athletic Asphalt Paving
32 12 19 Asphalt Paving Wearing Courses
32 12 19.13 Road-Mix Asphalt Paving Wearing Courses
32 12 19.16 Resin-Modified Asphalt Paving Wearing Courses
32 12 19.19 Porous Friction Asphalt Paving Wearing Courses
32 12 33 Flexible Paving Surface Treatments
32 12 36 Seal Coats
32 12 36.13 Asphaltic Seal and Fog Coats
32 12 36.16 Coal Tar Seal Coats
32 12 36.19 Coal Tar Seal Coats with Unvulcanized Rubber
32 12 36.23 Fuel-Resistant Sealers
32 12 43 Porous Flexible Paving
32 12 73 Asphalt Paving Joint Sealants
32 13 00 Rigid Paving
32 13 13 Concrete Paving
32 13 13.13 Exposed Aggregate Concrete Paving
32 13 13.16 Power-Compacted Concrete Paving
32 13 13.17 Roller-Compacted Concrete Paving
32 13 13.19 Prestressed Concrete Paving
32 13 13.23 Concrete Paving Surface Treatment
32 13 13.26 Stained Concrete Paving
32 13 13.33 Plain Concrete Paving
32 13 16 Decorative Concrete Paving
32 13 16.13 Patterned Concrete Paving
32 13 16.19 Imprinted Concrete Paving
32 13 16.23 Stamped Concrete Paving
32 13 43 Pervious Concrete Paving
32 13 73 Concrete Paving Joint Sealants
32 13 73.13 Fuel-Resistant Concrete Paving Joint Sealants
32 13 73.16 Field-Molded Concrete Paving Joint Sealants
32 13 73.19 Compression Concrete Paving Joint Sealants
32 14 00 Unit Paving
32 14 13 Precast Concrete Unit Paving
32 14 13.13 Interlocking Precast Concrete Unit Paving
32 14 13.16 Precast Concrete Unit Paving Slabs
32 14 13.19 Porous Precast Concrete Unit Paving
32 14 16 Brick Unit Paving
32 14 23 Asphalt Unit Paving
32 14 26 Wood Paving
32 14 29 Rubber Paving
32 14 33 Plastic Paving
32 14 33.13 Permeable Plastic Paving
32 14 40 Stone Paving
32 14 43 Porous Unit Paving
32 15 00 Aggregate Surfacing
32 15 13 Cinder Surfacing
32 15 40 Crushed Stone Surfacing
32 15 50 Aggregate-Turf Pavement
32 16 00 Curbs, Gutters, Sidewalks, and Driveways
32 16 13 Curbs and Gutters
32 16 13.13 Cast-In-Place Concrete Curbs and Gutters
32 16 13.16 Steel Faced Curbs
32 16 13.23 Precast Concrete Curbs and Gutters
32 16 13.33 Asphalt Curbs
32 16 13.43 Stone Curbs
32 16 23 Sidewalks
32 16 33 Driveways
32 17 00 Paving Specialties
32 17 13 Parking Bumpers
32 17 13.13 Metal Parking Bumpers
32 17 13.16 Plastic Parking Bumpers
32 17 13.19 Precast Concrete Parking Bumpers
32 17 13.23 Rubber Parking Bumpers
32 17 13.26 Wood Parking Bumpers
32 17 16 Manufactured Traffic-Calming Devices
32 17 23 Pavement Markings
32 17 23.13 Painted Pavement Markings
32 17 23.23 Raised Pavement Markings
32 17 23.33 Plastic Pavement Markings
32 17 26 Tactile Warning Surfacing
32 17 29 Pavement Embedded Warning Lights
32 17 43 Pavement Snow Melting Systems
32 18 00 Athletic and Recreational Surfacing
32 18 13 Synthetic Grass Surfacing
32 18 16 Synthetic Resilient Surfacing
32 18 16.13 Playground Protective Surfacing
32 18 23 Athletic Surfacing
32 18 23.13 Baseball Field Surfacing
32 18 23.16 Natural Baseball Field Surfacing
32 18 23.19 Synthetic Baseball Field Surfacing
32 18 23.23 Field Sport Surfacing
32 18 23.26 Natural Field Sport Surfacing
32 18 23.29 Synthetic Field Sport Surfacing
32 18 23.33 Running Track Surfacing
32 18 23.36 Natural Running Track Surfacing
32 18 23.39 Synthetic Running Track Surfacing
32 18 23.43 Recreational Court Surfacing
32 18 23.53 Tennis Court Surfacing
32 18 23.56 Natural Tennis Court Surfacing
32 18 23.59 Synthetic Tennis Court Surfacing
32 18 23.63 Equestrian Surfacing
32 30 00 Site Improvements
32 31 00 Fences and Gates
32 31 11 Gate Operators
32 31 13 Chain Link Fences and Gates
32 31 13.23 Recreational Court Fences and Gates
32 31 13.26 Tennis Court Fences and Gates
32 31 13.29 Tennis Court Wind Breaker
32 31 13.33 Chain Link Backstops
32 31 13.53 High-Security Chain Link Fences and Gates
32 31 16 Welded Wire Fences and Gates
32 31 17 Expanded Metal Fences and Gates
32 31 19 Decorative Metal Fences and Gates
32 31 19.53 Decorative Metal Security Fences and Gates
32 31 23 Plastic Fences and Gates
32 31 26 Wire Fences and Gates
32 31 26.11 Wire Fences with Wood Posts
32 31 26.13 Wire Fences with Steel Posts
32 31 29 Wood Fences and Gates
32 31 32 Composite Fences and Gates
32 31 53 Cattle Guards
32 31 56 Wild Life Deterrent Fence
32 32 00 Retaining Walls
32 32 13 Cast-in-Place Concrete Retaining Walls
32 32 16 Precast Concrete Retaining Walls
32 32 19 Unit Masonry Retaining Walls
32 32 23 Segmental Retaining Walls
32 32 23.13 Segmental Concrete Unit Masonry Retaining Walls
32 32 23.16 Manufactured Modular Walls
32 32 26 Metal Crib Retaining Walls
32 32 29 Timber Retaining Walls
32 32 34 Reinforced Soil Retaining Walls
32 32 36 Gabion Retaining Walls
32 32 43 Soldier-Beam Retaining Walls
32 32 53 Stone Retaining Walls
32 33 00 Site Furnishings
32 33 13 Site Bicycle Racks
32 33 14 Site Bicycle Lockers
32 33 23 Site Trash and Litter Receptacles
32 33 33 Site Manufactured Planters
32 33 43 Site Seating and Tables
32 33 43.13 Site Seating
32 33 43.53 Site Tables
32 34 00 Fabricated Bridges
32 34 13 Fabricated Pedestrian Bridges
32 34 23 Fabricated Roadway Bridges
32 34 33 Fabricated Railway Bridges
32 35 00 Screening Devices
32 35 13 Screens and Louvers
32 35 16 Sound Barriers
32 35 23 Fire Barriers
32 35 26 Blast Barriers
32 39 00 Manufactured Site Specialties
32 39 13 Manufactured Metal Bollards
32 39 13.11 Manufactured Metal Security Bollards
32 39 16 Manufactured Fire Pits
32 39 33 Artificial Rock Fabrications
32 70 00 Wetlands
32 71 00 Constructed Wetlands
32 72 00 Wetlands Restoration
32 80 00 Irrigation
32 81 00 Irrigation Components
32 81 13 Irrigation Intake Screens
32 82 00 Irrigation Pumps
32 84 00 Planting Irrigation
32 84 13 Drip Irrigation
32 84 23 Underground Sprinklers
32 86 00 Agricultural Irrigation
32 90 00 Planting
32 91 00 Planting Preparation
32 91 13 Soil Preparation
32 91 13.13 Hydro-Punching
32 91 13.16 Mulching
32 91 13.19 Planting Soil Mixing
32 91 13.23 Structural Soil Mixing
32 91 13.26 Planting Beds
32 91 16 Planting Soil Stabilization
32 91 16.13 Blanket Planting Soil Stabilization
32 91 16.16 Mat Planting Soil Stabilization
32 91 16.19 Netting Planting Soil Stabilization
32 91 19 Landscape Grading
32 91 19.13 Topsoil Placement and Grading
32 92 00 Turf and Grasses
32 92 13 Hydro-Mulching
32 92 16 Plugging
32 92 19 Seeding
32 92 19.13 Mechanical Seeding
32 92 19.16 Hydraulic Seeding
32 92 23 Sodding
32 92 26 Sprigging
32 92 26.13 Stolonizing
32 93 00 Plants
32 93 13 Ground Covers
32 93 23 Plants and Bulbs
32 93 33 Shrubs
32 93 43 Trees
32 93 93 Exterior Artificial Plants
32 94 00 Planting Accessories
32 94 13 Landscape Edging
32 94 16 Landscape Timbers
32 94 19 Landscape Surfacing
32 94 33 Planters
32 94 43 Tree Grates
32 94 46 Tree Grids
32 95 00 Exterior Planting Support Structures
32 96 00 Transplanting
32 96 13 Ground Cover Transplanting
32 96 23 Plant and Bulb Transplanting
32 96 33 Shrub Transplanting
32 96 43 Tree Transplanting
33 00 00 Utilities
33 01 00 Operation and Maintenance of Utilities
33 01 10 Operation and Maintenance of Water Utilities
33 01 10.51 Water Utility Intake Cleaning and Maintenance
33 01 10.52 Reservoir Maintenance
33 01 10.53 Flushing of Water Utility Piping
33 01 10.54 Cleaning of Water Utility Piping
33 01 10.56 Cleaning of Water Utility Storage Tanks
33 01 10.57 Disinfection of Water Supply Wells
33 01 10.58 Disinfection of Water Utility Piping Systems
33 01 10.59 Disinfection of Water Utility Storage Tanks
33 01 10.81 Water Supply Well Abandonment
33 01 10.91 Rehabilitation of Water Supply Wells
33 01 10.92 Redevelopment of Water Supply Wells
33 01 12 Inspection and Testing of Water Utilities
33 01 12.11 Leakage Detection
33 01 12.13 Electrical Continuity Testing
33 01 30 Operation and Maintenance of Sewer Utilities
33 01 30.11 Television Inspection of Sewers
33 01 30.13 Dye Testing of Sewers
33 01 30.16 Smoke Testing
33 01 30.23 Pipe Bursting
33 01 30.41 Cleaning of Sewers
33 01 30.42 Cleaning of Manholes
33 01 30.43 Removal of Protruding Service Connection
33 01 30.44 Chemical Treatment of Roots in Sewer Lines
33 01 30.61 Packer Injection Grouting
33 01 30.72 Cured-in-place Pipe Lining
33 01 30.73 Cured-in-Place Point Repair
33 01 30.74 Cured-in-Place Lateral Lining
33 01 30.77 Cured-in-Place Lateral Shortliners
33 01 30.79 Fold-and-Form Pipe Lining
33 01 30.81 Manhole Rehabilitation
33 01 30.82 Epoxy Lining for Concrete Manholes
33 01 30.84 Manhole Inserts
33 01 30.86 Manhole Rim Adjustment
33 01 34 Operation and Maintenance of Onsite Wastewater Disposal Systems
33 01 34.13 Septic Tank Solids Removal
33 01 34.14 Septic Tank Maintenance
33 01 34.19 Septic Tank Abandonment
33 01 34.33 Maintenance of Onsite Sand Filters
33 01 50 Operation and Maintenance of Hydrocarbon Utilities
33 01 50.53 Cleaning of Hydrocarbon Conveyance Piping
33 01 50.56 Cleaning of Hydrocarbon Storage Tanks
33 01 50.73 Relining of Hydrocarbon Conveyance Piping
33 01 50.76 Relining of Steel Hydrocarbon Storage Tanks
33 01 50.81 Hydrocarbon Well Abandonment
33 01 50.91 Rehabilitation of Hydrocarbon Wells
33 01 60 Operation and Maintenance of Hydronic and Steam Energy Utilities
33 01 70 Operation and Maintenance of Electrical Utilities
33 01 70.51 Electrical Utility Visual Inspection
33 01 70.52 Electrical Utility Thermographic Surveys
33 01 70.53 Electrical Utility Insulation Testing
33 01 70.54 Electrical Utility Insulating Oil/Fluid Analysis
33 01 80 Operation and Maintenance of Communications Utilities
33 01 80.51 Communication Utility Visual Inspection
33 01 80.52 Communication Utility Thermographic Surveys
33 05 00 Common Work Results for Utilities
33 05 05 Buried Piping Installation
33 05 05.11 Installing Bell-and-Spigot Joints
33 05 05.13 Installing Push-on Joints
33 05 05.15 Installing Butt-and-Strap Joints
33 05 05.16 Installing Mechanical Joints
33 05 05.18 Installing Restrained Joints
33 05 05.19 Fusing Joints
33 05 05.31 Hydrostatic Testing
33 05 05.33 Infiltration and Exfiltration Testing
33 05 05.36 Vacuum Testing
33 05 05.41 Air Testing
33 05 05.43 Mandrel Testing
33 05 05.46 Lamp Testing
33 05 07 Trenchless Installation of Utility Piping
33 05 07.13 Utility Directional Drilling
33 05 07.23 Utility Boring and Jacking
33 05 07.24 Casing Piping for Utility Jacking
33 05 07.33 Tunnelling
33 05 07.36 Microtunnelling
33 05 07.43 Utility Impact Moling
33 05 07.53 Cable Trenching and Plowing
33 05 09 Piping Specials for Utilities
33 05 09.13 Couplings for Utility Piping
33 05 09.23 Adapters for Utility Piping
33 05 09.33 Thrust Restraint for Utility Piping
33 05 09.43 Tappling Sleeves and Saddles for Utility Piping
33 05 11 Aluminum Utility Pipe
33 05 12 Brass Utility Pipe
33 05 16 Cast-Iron Utility Pipe
33 05 17 Copper Utility Pipe and Tubing
33 05 19 Ductile-Iron Utility Pipe
33 05 21 High-Alloy Nickel Utility Pipe and Tubing
33 05 23 Stainless Steel Utility Pipe and Tubing
33 05 23.13 Duplex and Super-Duplex Stainless Steel Utility Pipe
33 05 23.23 300- and 400-Series Stainless Steel Utility Pipe
33 05 23.33 Special-Fabrication Stainless Steel Utility Pipe and Tubing
33 05 24 Steel Utility Pipe
33 05 24.13 Steel Pipe and Tubing for Air and Gas Service
33 05 24.23 Steel Pipe for Water Service
33 05 24.26 Steel Pipe and Tubing for Utility Liquid Service
33 05 24.33 Steel Pipe for Bulk Materials Conveyance
33 05 27 Corrugated Metal Utility Pipe
33 05 27.13 Corrugated Metal Culvert Pipe
33 05 27.23 Corrugated Metal Slotted Pipe
33 05 27.33 Corrugated Metal Culvert Arch Pipe
33 05 31 Thermoplastic Utility Pipe
33 05 31.11 Polyvinyl Chloride Gravity Sewer Pipe
33 05 31.13 Polyvinyl Chloride Pressure Pipe
33 05 31.16 Polyvinyl Chloride Pressure Pipe for Water Transmission and Distribution (AWWA C900 and AWWA C905)
33 05 31.19 Fusible Polyvinyl Chloride Pipe
33 05 31.21 Ribbed Polyvinyl Chloride Gravity Pipe
33 05 31.23 Dual-Wall Polyvinyl Chloride Profile Pipe
33 05 31.26 Polyvinyl Chloride Sleeve Pipe
33 05 31.27 Polyvinyl Chloride Perforated Drainage Pipe
33 05 31.29 Polyvinyl Chloride Electrical Duct
33 05 31.33 ABS Utility Pipe
33 05 33 Polyethylene Utility Pipe
33 05 33.13 Corrugated-Wall, Smooth Interior HDPE Gravity Pipe
33 05 33.23 Polyethylene Pressure Pipe and Tubing (AWWA C901 and AWWA C906)
33 05 33.33 Corrugated, Perforated HDPE Drainage Pipe
33 05 33.36 Corrugated, Non-Perforated HDPE Drainage Pipe
33 05 33.53 HDPE Gas Utility Pipe
33 05 33.56 Medium-Density Polyethylene Gas Utility Pipe
33 05 33.63 HDPE Communication Duct
33 05 36 Fiberglass-Reinforced Plastic Utility Pipe
33 05 36.13 Fiberglass-Reinforced Plastic Pipe for Utility Air, Gas, and Odor Service
33 05 36.23 Fiberglass-Reinforced Plastic Pipe for Utility Liquid Service
33 05 36.33 Fiberglass-Reinforced Plastic Pipe for Electrical Service
33 05 37 Centrifugally Cast Fiberglass-Reinforced Polymer Mortar Utility Pipe
33 05 39 Concrete Pipe
33 05 39.11 Concrete Pressure Pipe, Steel-Cylinder Type (AWWA C300)
33 05 39.13 Prestressed Concrete Pressure Pipe, Steel-Cylinder Type (AWWA C301)
33 05 39.16 Reinforced Concrete Pressure Pipe, Non-cylinder Type (AWWA C302)
33 05 39.17 Concrete Pressure Pipe, Bar-Wrapped Steel-Cylinder Type (AWWA C303)
33 05 39.23 Reinforced Concrete Low-Head Pressure Utility Pipe
33 05 39.33 Non-Reinforced Concrete Sewer and Culvert Pipe
33 05 39.36 Non-Reinforced Concrete Irrigation and Drainage Pipe
33 05 39.41 Reinforced Concrete Pipe for Sewers and Culverts
33 05 39.43 Perforated Concrete Utility Pipe
33 05 39.46 Reinforced Concrete Elliptical Pipe for Sewers and Culverts
33 05 39.49 Reinforced Concrete Box Sections for Sewers and Culverts
33 05 39.63 Concrete Pipe Closures
33 05 39.66 Concrete Pipe Thrust Restraints
33 05 39.69 Concrete Pipe Wall Fittings
33 05 41 Vitrified Clay Utility Pipe
33 05 43 Ceramic Drainage Tile
33 05 46 Asbestos Cement Utility Pipe
33 05 61 Concrete Manholes
33 05 63 Concrete Vaults and Chambers
33 05 66 Concrete Distribution Chambers
33 05 69 Concrete Trenchways
33 05 71 Cleanouts
33 05 73 Polyethylene Manholes
33 05 76 Fiberglass Manholes
33 05 77 Fiberglass Metering Manholes
33 05 81 Metallic Castings for Utility Structures
33 05 83 Non-Metallic Accessories for Utility Structures
33 05 93 Common Motor Requirements for Utilities
33 05 96 Vibration and Seismic Controls for Utilities
33 05 97 Identification and Signage for Utilities
33 05 97.13 Signage for Utilities
33 05 97.16 Markers for Utility Identification
33 05 97.23 Underground Utility Warning Tape
33 05 97.33 Utility Identification Flags
33 06 00 Schedules for Utilities
33 06 05 Schedules for Utility Piping
33 06 10 Schedules for Water Utilities
33 06 30 Schedules for Sanitray Sewerage Utiltiies
33 06 40 Schedules for Stormwater Utilities
33 06 40.13 Stormwater Drainage System Schedules
33 06 50 Schedules for Hydrocarbon Utilities
33 06 60 Schedules for Hydronic and Steam Energy Utilities
33 06 70 Schedules for Electrical Utilities
33 06 80 Schedules for Communications Utilities
33 08 00 Commissioning of Utilities
33 08 10 Commissioning of Water Utilities
33 08 30 Commissioning of Sanitary Sewerage Utilities
33 08 40 Commissioning of Stormwater Utilities
33 08 50 Commissioning of Hydrocarbon Utilities
33 08 60 Commissioning of Hydronic and Steam Energy Utilities
33 08 70 Commissioning of Electrical Utilities
33 08 80 Commissioning of Communications Utilities
33 09 00 Instrumentation and Control for Utilities
33 09 01 Utility Meter Registers
33 09 01.13 Mechanical Registers
33 09 01.23 Pulse Registers
33 09 01.33 Encoder Registers
33 09 02 Touch-based Utility Meter Reading Equipment
33 09 03 Handheld Radio Frequency Utility Meter Reading Equipment
33 09 04 Mobile Radio Frequency Utility Meter Reading Equipment
33 09 05 Fixed-Network Radio Frequency Utility Meter Reading Equipment
33 09 06 Satellite Radio Frequency Utility Meter Reading Equipment
33 09 07 Power Line Communication Utility Meter Reading Equipment
33 09 08 Wireless Local Area Network Utility Meter Reading Equipment
33 09 09 Meter Data Acquisition and Hosting Software
33 09 10 Instrumentation and Control for Water Utilities
33 09 30 Instrumentation and Control for Sanitary Sewerage Utilities
33 09 40 Instrumentation and Control for Stormwater Utilities
33 09 50 Instrumentation and Control for Hydrocarbon Utilities
33 09 53 Leak Detection for Hydrocarbon Systems
33 09 60 Instrumentation and Control for Hydronic and Steam Energy Utilities
33 09 70 Instrumentation and Control for Electrical Utilities
33 09 80 Instrumentation and Control for Communications Utilities
33 10 00 Water Utilities
33 11 00 Groundwater Sources
33 11 11 Test Wells
33 11 13 Potable Water Supply Wells
33 11 16 Irrigation Wells
33 11 19 Aquifer Recharging Wells
33 11 33 Vertically Suspended Dry-Location Centrifugal Well Pumps
33 11 36 Submersible Centrifugal Well Pumps
33 11 39 Jet-Type Well Pumps
33 11 53 Monitoring Wells
33 12 00 Surface Water Sources
33 12 11 Intake Structure Systems
33 12 13 Intake Cribs
33 12 16 Intake Drop and Riser Shafts
33 12 31 Reservoir Weight-tensioned, Defined Sump Floating Covers
33 12 31.13 Reservoir Weight-tensioned, Defined Sump Polyethylene-reinforced Floating Covers
33 12 31.23 Reservoir Weight-tensioned, Defined Sump Polypropylene-reinforced Floating Covers
33 12 33 Reservoir Mechanically-tensioned Floating Covers
33 12 33.13 Reservoir Mechanically-tensioned Polyethylene-reinforced Floating Covers
33 12 33.23 Reservoir Mechanically-tensioned Polypropylene-reinforced Floating Covers
33 12 36 Reservoir Short-term Floating Covers
33 12 39 Reservoir Ball Floating Covers
33 12 43 Floats for Reservoir Floating Covers
33 12 46 Appurtenances for Reservoir Floating Covers
33 12 53 Reservoir Flexible Baffle Curtains
33 14 00 Water Utility Transmission and Distribution
33 14 11 Water Utility Transmission Piping
33 14 13 Public Water Utility Distribution Piping
33 14 16 Site Water Utility Distribution Piping
33 14 17 Site Water Utility Service Laterals
33 14 19 Valves and Hydrants for Water Utility Service
33 14 23 Enclosures for Water Utility Piping and Valves
33 14 23.11 Heated, Insulated Aluminum Enclosures for Water Utility Piping and Valves
33 14 23.13 Heated, Insulated Fiberglass Enclosures for Water Utility Piping and Valves
33 14 23.16 Unheated, Insulated Aluminum Enclosures for Water Utility Piping and Valves
33 14 23.17 Unheated, Insulated Fiberglass Enclosures for Water Utility Piping and Valves
33 14 23.23 Fiberglass Artificial Rock Enclosures for Water Utility Piping and Valves
33 14 23.26 Plastic Artificial Rock Enclosures for Water Utility Piping and Valves
33 14 23.33 Enclosures for Water Utility Air Valves
33 14 43 Packaged Pumping Systems for Water Utility Service
33 16 00 Water Utility Storage Tanks
33 16 11 Elevated Composite Water Storage Tanks
33 16 13 Elevated Pillar-Type Steel Water Storage Tanks
33 16 16 Multi-Column Elevated Steel Water Storage Tanks
33 16 19 Elevated Spheroid Steel Water Storage Tanks
33 16 23 Ground-Level Steel Water Storage Tanks
33 16 31 Ground-Level AWWA D110 Type I Prestressed Concrete Water Storage Tanks
33 16 32 Ground-Level AWWA D110 Type II Prestressed Concrete Water Storage Tanks
33 16 33 Ground-Level AWWA D110 Type III Prestressed Concrete Water Storage Tanks
33 16 36 Ground-Level Reinforced Concrete Water Storage Tanks
33 16 53 Ground-Level Metal Water Storage Cisterns
33 16 56 Ground-Level Plastic Water Storage Cisterns
33 16 61 Underground Concrete Water Storage Cisterns
33 16 63 Underground Non-Metallic Water Storage Cisterns
33 16 66 Underground Plastic Modular Water Storage Cisterns
33 16 93 Water Storage Tank Interior Curtain Walls
33 16 96 Water Storage Tank Appurtenances
33 19 00 Water Utility Metering Equipment
33 19 13 Positive Displacement Water Meters
33 19 13.13 Oscillating Piston Water Meters
33 19 13.23 Nutating Disc Water Meters
33 19 16 Velocity-Type Water Meters
33 19 16.13 Single-Jet Water Meters
33 19 16.16 Multi-Jet Water Meters
33 19 16.23 Turbine Water Meters
33 19 16.26 Fire-Type Turbine Water Meters
33 19 16.29 Portable Fire Hydrant-Type Turbine Water Meters
33 19 16.33 Propeller Water Meters
33 19 19 Compound Water Meters
33 19 23 Magnetic Water Meters
33 19 26 Ultrasonic Water Meters
33 19 29 Pre-paid Water Meters
33 30 00 Sanitary Sewerage
33 31 00 Sanitary Sewerage Piping
33 31 11 Public Sanitary Sewerage Gravity Piping
33 31 13 Site Sanitary Sewerage Gravity Piping
33 31 16 Site Sanitary Sewerage Gravity Service Laterals
33 31 19 Small-Diameter Sanitary Sewerage Gravity Piping
33 31 23 Sanitary Sewerage Force Main Piping
33 31 26 Sanitary Pressure Sewer Piping
33 31 29 STEP System Piping
33 32 00 Sanitary Sewerage Equipment
33 32 11 Field-Erected Wastewater Pumping Stations
33 32 13 Packaged Wastewater Pumping Stations
33 32 16 Packaged Wastewater Grinder Pump Assemblies
33 32 19 Septic Tank Effluent Pumps
33 32 26 Pneumatic Sewage Ejectors
33 32 33 Wastewater Collection Vacuum Stations
33 32 36 Pneumatic Wastewater Vacuum Valve Sumps
33 34 00 Onsite Wastewater Disposal
33 34 13 Septic Tanks
33 34 13.13 Concrete Septic Tanks
33 34 13.23 Fiberglass Septic Tanks
33 34 13.33 Polyethylene Septic Tanks
33 34 16 Septic Tank Effluent Filters
33 34 16.13 Septic Tank Gravity Effluent Filters
33 34 16.16 Septic Tank Pressurized Effluent Filters
33 34 19 Septic Tank Accessories
33 34 23 Onsite Aerobic Equipment
33 34 33 Onsite Intermittent Wastewater Filtration Systems
33 34 36 Onsite Recirculating Wastewater Filtration Systems
33 34 51 Drainage Field System
33 34 53 Distribution Chambers
33 34 53.13 Drainage Field Concrete Distribution Chambers
33 34 53.23 Drainage Field Fiberglass Distribution Chambers
33 34 53.33 Drainage Field Polyethylene Distribution Chambers
33 34 56 Drainage Field Dosing Chambers
33 34 57 Drainage Field Infiltration Chambers
33 36 00 Wastewater Utility Storage Tanks
33 36 23 Ground-Level Steel Wastewater Storage Tanks
33 36 31 Ground-Level AWWA D110 Type I Prestressed Concrete Wastewater Storage Tanks
33 36 32 Ground-Level AWWA D110 Type II Prestressed Concrete Wastewater Storage Tanks
33 36 33 Ground-Level AWWA D110 Type III Prestressed Concrete Wastewater Storage Tanks
33 36 36 Ground-Level Reinforced Concrete Wastewater Storage Tanks
33 36 43 Underground Reinforced Concrete Wastewater Storage Tanks
33 36 53 Wastewater Storage Tunnel Systems
33 37 00 Overflow Control
33 37 13 Bending Weirs
33 37 16 Spring-loaded Weirs
33 37 23 Flow Regulators
33 37 33 Swirl Concentrators
33 37 36 Vortex-Type Hydrodynamic Separators
33 37 43 Netting Systems
33 37 46 End-of-Pipe In-water Storage Systems
33 40 00 Stormwater Utilities
33 41 00 Subdrainage
33 41 13 Foundation Drainage
33 41 13.13 Foundation Drainage Piping
33 41 13.16 Geocomposite Foundation Drainage
33 41 16 Subdrainage Piping
33 41 16.16 Geocomposite Subdrainage
33 41 16.19 Pipe Underdrains
33 41 19 Underslab Drainage
33 41 19.13 Underslab Drainage Piping
33 41 19.16 Geocomposite Underslab Drainage
33 41 23 Drainage Layers
33 41 23.16 Gravel Drainage Layers
33 41 23.19 Geosynthetic Drainage Layers
33 41 33 Retaining Wall Drainage
33 41 43 Synthetic-Media French Drains
33 42 00 Stormwater Conveyance
33 42 11 Stormwater Gravity Piping
33 42 13 Stormwater Culverts
33 42 16 Stormwater Force Main Piping
33 42 23 Headwalls and Endwalls for Stormwater Piping
33 42 26 End Sections for Stormwater Piping
33 42 26.11 Aluminum End Sections for Stormwater Piping
33 42 26.13 Steel End Sections for Stormwater Piping
33 42 26.16 Corrugated Metal End Sections for Stormwater Piping
33 42 26.23 Concrete End Sections for Stormwater Piping
33 42 31 Stormwater Area Drains and Inlets
33 42 33 Stormwater Curbside Drains and Inlets
33 42 36 Stormwater Trench Drains
33 42 41 Gratings and Frames for Stormwater Drainage Inlets
33 42 41.11 Aluminum Gratings and Frames for Stormwater Drainage inlets
33 42 41.21 Brass Gratings and Frames for Stormwater Drainage inlets
33 42 41.31 Cast-Iron Gratings and Frames for Stormwater Drainage Inlets
33 42 41.41 Chrome Gratings and Frames for Stormwater Drainage inlets
33 42 41.51 Steel Gratings and Frames for Stormwater Drainage Inlets
33 42 41.61 Fiberglass Gratings and Frames for Stormwater Drainage Inlets
33 44 00 Stormwater Utility Equipment
33 44 11 Field-Erected Stormwater Pumping Stations
33 44 13 Packaged Stormwater Pumping Stations
33 44 21 Stormwater Downspout Filters
33 44 23 Inline Stormwater Filters
33 44 26 Stormwater Catch Basin Insert Filters
33 44 27 Stormwater Trench Drain Insert Filters
33 44 31 Stormwater Membrane Filtration
33 44 33 Stormwater Trash and Debris Guards
33 44 36 Oil and Stormwater Separators
33 44 43 Vortex-Type Hydrodynamic Separators
33 44 53 Stormwater Area Drainage Pop-up Relief Valves
33 46 00 Stormwater Management
33 46 11 Stormwater Ponds
33 46 11.13 Stormwater Detention Ponds
33 46 11.23 Stormwater Retention Ponds
33 46 11.33 Fire Protection Ponds
33 46 11.43 Cooling Water Ponds
33 46 16 Outlet Structures for Stormwater Ponds
33 46 16.13 Stormwater Pond Concrete Outlet Structures
33 46 16.23 Stormwater Pond Fiberglass Outlet Structures
33 46 23 Modular Buried Stormwater Storage Units
33 46 39 Rain Barrels
33 46 53 Stormwater Leaching Pits
33 46 56 Tree Box Filters
33 46 59 Concrete Modular Biofiltration Cells
33 46 63 Swale Protection Prefilters
33 50 00 Hydrocarbon Utilities
33 51 00 Hydrocarbon Sources
33 51 13 Appraisal Wells for Liquid Hydrocarbons
33 51 16 Appraisal Wells for Gaseous Hydrocarbons
33 51 23 Production Wells for Liquid Hydrocarbons
33 51 26 Production Wells for Gaseous Hydrocarbons
33 51 33 Liquid Injection Wells
33 51 36 Gas Injection Wells
33 51 39 Monitoring Wells
33 51 53 Reciprocating Pumpjack
33 51 56 Submersible Liquid Hydrocarbon Pumps
33 52 00 Hydrocarbon Transmission and Distribution
33 52 13 Liquid Hydrocarbon Piping
33 52 16 Gas Hydrocarbon Piping
33 52 16.13 Steel Natural Gas Piping
33 52 16.23 Medium Density Polyethylene Piping for Natural Gas
33 52 16.26 High Density Polyethylene Piping for Natural Gas
33 52 19 Hydrocarbon Piping Handling
33 52 19.13 Hydrocarbon Piping Stringing, Storing, and Stacking
33 52 23 Hydrocarbon Piping Welding
33 52 23.13 Liquid Hydrocarbon Piping Welding
33 52 23.16 Gas Hydrocarbon Piping Welding
33 52 26 Hydrocarbon Piping Pigging
33 52 26.13 Hydrocarbon Piping Pig Launchers
33 52 26.16 Hydrocarbon Piping Pig Receivers
33 52 26.23 Pigs for Hydrocarbon Piping
33 53 00 Hydrocarbon Utility Pressure Regulation
33 53 13 Liquid Hydrocarbon Pressure Regulation
33 53 16 Gas Hydrocarbon Pressure Regulation
33 54 00 Hydrocarbon Utility Safety Equipment
33 54 13 Liquid Hydrocarbon Leak Detection Equipment
33 54 16 Gas Hydrocarbon Leak Detection Equipment
33 54 23 Hydrocarbon Pipeline Venting
33 54 23.13 Liquid Hydrocarbon Pipeline Venting
33 54 23.16 Gas Hydrocarbon Pipeline Venting
33 56 00 Hydrocarbon Storage
33 56 13 Aboveground Hydrocarbon Storage Tanks
33 56 21 Ground-Level Fixed Roof Hydrocarbon Storage Tanks
33 56 21.13 Double-Wall Ground-Level Fixed Roof Metallic Hydrocarbon Storage Tanks
33 56 21.16 Single-Wall Ground-Level Fixed Roof Metallic Hydrocarbon Storage Tanks
33 56 21.23 Single-Wall Ground-Level Fixed Roof Non-Metallic Hydrocarbon Storage Tanks
33 56 21.26 Double-Wall Ground-Level Fixed Roof Non-Metallic Hydrocarbon Storage Tanks
33 56 23 Ground-Level External Floating Roof Hydrocarbon Storage Tanks
33 56 26 Ground-Level Internal Floating Roof Hydrocarbon Storage Tanks
33 56 33 Underground Hydrocarbon Storage
33 56 33.13 Double-Wall Metallic Underground Hydrocarbon Storage Tanks
33 56 33.23 Single-Wall Metallic Underground Hydrocarbon Storage Tanks
33 56 33.26 Single-Wall Non-Metallic Underground Hydrocarbon Storage Tanks
33 56 33.29 Double-Wall Non-Metallic Underground Hydrocarbon Storage Tanks
33 56 33.43 Underground Hydrocarbon Storage Caverns
33 56 43 Aviation Fuel Storage Tanks
33 56 43.13 Ground-Level Aviation Fuel Storage Tanks
33 56 43.53 Underground Aviation Fuel Storage Tanks
33 56 53 Compressed Gaseous Hydrocarbon Storage Tanks
33 56 60 Moveable Hydrocarbon Storage Tanks
33 56 93 Hydrocarbon Tank Linings
33 56 96 Hydrocarbon Storage Tank Appurtenances
33 57 00 Bulk Hydrocarbons Receiving/Dispensing Equipment
33 59 00 Hydrocarbon Utility Metering
33 59 11 Diaphragm/Bellows Hydrocarbons Meters
33 59 13 Hydrocarbons Rotary Meters
33 59 16 Hydrocarbons Turbine Meters
33 59 19 Hydrocarbons Orifice Meters
33 59 23 Hydrocarbons Ultrasonic Flow Meters
33 59 26 Hydrocarbons Coriolis Meters
33 59 43 Liquid Hydrocarbon Sampling and Quality Analysis Instrumentation
33 59 46 Gas Hydrocarbon Sampling and Quality Analysis Instrumentation
33 60 00 Hydronic and Steam Energy Utilities
33 61 00 Hydronic Energy Distribution
33 61 13 Buried Hydronic Energy Distribution
33 61 23 Ground-Level Hydronic Energy Distribution
33 61 27 Prefabricated Energy Distribution
33 61 29 Pre-Engineered, Field-Assembled Energy Distribution
33 61 33 Hydronic Energy Distribution Metering
33 63 00 Steam Energy Distribution
33 63 13 Underground Steam and Condensate Distribution Piping
33 63 13.13 Shallow-Trench Steam Distribution Piping
33 63 13.16 Utilidor Steam Distribution Piping
33 63 23 Ground-Level Steam and Condensate Distribution Piping
33 63 33 Steam Energy Distribution Metering
33 70 00 Electrical Utilities
33 71 00 Electrical Utility Transmission and Distribution
33 71 13 Electrical Utility Towers
33 71 13.13 Precast Concrete Electrical Utility Towers
33 71 13.23 Steel Electrical Utility Towers
33 71 13.33 Wood Electrical Utility Towers
33 71 16 Electrical Poles
33 71 16.13 Precast Concrete Electrical Utility Poles
33 71 16.23 Steel Electrical Utility Poles
33 71 16.33 Wood Electrical Utility Poles
33 71 19 Electrical Underground Ducts, Ductbanks,and Manholes
33 71 19.13 Electrical Manholes and Handholes
33 71 19.23 Trenched Electrical Underground Duct and Ductbanks
33 71 19.33 Trenchless Electrical Underground Duct and Ductbanks
33 71 23 Insulators and Fittings
33 71 23.13 Suspension Insulators
33 71 23.16 Post Insulators
33 71 23.23 Potheads
33 71 26 Transmission and Distribution Equipment
33 71 26.13 Capacitor Banks
33 71 26.16 Coupling Capacitors
33 71 26.23 Current Transformers
33 71 26.26 Potential Transformers
33 71 36 Extra-High-Voltage Transmission Wiring
33 71 36.13 Overhead Extra-High-Voltage Transmission Wiring
33 71 39 High-Voltage Transmission Wiring
33 71 39.13 Overhead High-Voltage Transmission Wiring
33 71 39.23 Underground High-Voltage Transmission Wiring
33 71 39.33 Underwater High-Voltage Transmission Wiring
33 71 49 Medium-Voltage Transmission Wiring
33 71 49.13 Overhead Medium-Voltage Transmission Wiring
33 71 49.23 Underground Medium-Voltage Transmission Wiring
33 71 49.33 Underwater Medium-Voltage Transmission Wiring
33 71 53 Direct-Current Transmission
33 71 73 Electrical Utility Services
33 71 83 Transmission and Distribution Specialties
33 72 00 Utility Substations
33 72 13 Deadend Structures
33 72 23 Structural Bus Supports
33 72 23.13 Bus Support Insulators
33 72 26 Substation Bus Assemblies
33 72 26.13 Aluminum Substation Bus Assemblies
33 72 26.16 Copper Substation Bus Assemblies
33 72 33 Control House Equipment
33 72 33.13 Relays
33 72 33.16 Substation Control Panels
33 72 33.23 Power-Line Carriers
33 72 33.26 Substation Metering
33 72 33.43 Substation DC Supply
33 72 43 Substation Control Wiring
33 72 53 Shunt Reactors
33 72 63 Substation Disconnect Switches
33 72 63.13 Vertical Break Disconnect Switches
33 72 63.16 Double End Break Disconnect Switches
33 72 63.19 Double End Break "Vee" Disconnect Switches
33 72 63.21 Center Break Disconnect Switches
33 72 63.23 Center Break "Vee" Disconnect Switches
33 72 63.26 Single Side Break Disconnect Switches
33 72 63.27 Vertical Reach Disconnect Switches
33 72 63.29 Grounding for Substation Disconnect Switches
33 72 63.31 Hook Sticks
33 73 00 Utility Transformers
33 73 13 Liquid-Filled Utility Transformers
33 73 23 Dry-Type Utility Transformers
33 74 00 Extra High Voltage (EHV) Switchgear and protection devices
33 74 13 Air EHV Circuit Breaker
33 74 16 Oil EHV Circuit Breaker
33 74 19 Gas EHV Circuit Breaker
33 74 30 EHV Disconnect switch
33 74 36 EHV Utility Fuses
33 74 39 EHV Surge Arresters
33 74 40 EHV Rod Gap
33 74 43 EVH Shunt Reactors
33 74 43.13 EHV Shunt Reactor Banks
33 74 43.16 EHV Current Limiting Reactors
33 75 00 High-Voltage Switchgear and Protection Devices
33 75 13 Air High-Voltage Circuit Breaker
33 75 16 Oil High-Voltage Circuit Breaker
33 75 19 Gas High-Voltage Circuit Breaker
33 75 23 Vacuum High-Voltage Circuit Breaker
33 75 30 High-Voltage Disconnect Switch
33 75 36 High-Voltage Utility Fuses
33 75 39 High-Voltage Surge Arresters
33 75 40 High-Voltage Rod Gap
33 77 00 Medium-Voltage Utility Switchgear and Protection Devices
33 77 13 Air Medium-Voltage Circuit Breaker
33 77 16 Oil Medium-Voltage Circuit Breaker
33 77 19 Gas Medium-Voltage Circuit Breaker
33 77 23 Vacuum Medium-Voltage Circuit Breaker
33 77 26 Medium-Voltage Utility Fusible Interrupter Switchgear
33 77 30 Medium-Voltage Disconnect Switch
33 77 33 Medium-Voltage Utility Cutouts
33 77 36 Medium-Voltage Utility Fuses
33 77 39 Medium-Voltage Utility Surge Arresters
33 77 40 Medium-Voltage Rod Gap
33 77 53 Medium-Voltage Utility Reclosers
33 78 00 Substation Converter Stations
33 79 00 Site Grounding
33 79 13 Site Improvement Grounding
33 79 13.13 Fence Grounding
33 79 16 Tower Grounding
33 79 16.13 Communications Tower Grounding
33 79 16.16 Antenna Tower Grounding
33 79 19 Utilities Grounding
33 79 19.13 Electrical Utilities Grounding
33 79 19.16 Communications Utilities Grounding
33 79 23 Utility Substation Grounding
33 79 83 Site Grounding Conductors
33 79 93 Site Lightning Protection
33 79 93.13 Lightning Arrestors
33 79 93.16 Lightning Strike Counters
33 79 93.19 Lightning Strike Warning Devices
33 80 00 Communications Utilities
33 81 00 Communications Structures
33 81 13 Monopole Communications Towers
33 81 16 Lattice Communications Towers
33 81 19 Guyed Communications Towers
33 81 21 Concealed Communications Towers
33 81 23 Broadcast Communications Towers
33 81 27 Aerial Cable Installation Hardware
33 81 29 Communications Vaults, Pedestals, and Enclosures
33 81 63 Cell Site Shelter Equipment
33 81 63.16 DC Rectifiers
33 81 63.19 Backup Batteries
33 81 63.23 Baseband Microwave Processing
33 81 63.26 Base Station Transceivers
33 81 63.43 Remote Monitoring
33 82 00 Communications Transmission and Distribution
33 82 13 Copper Communications Transmission and Distribution Cabling
33 82 13.13 Copper Splicing and Terminations
33 82 23 Optical Fiber Communications Transmission and Distribution Cabling
33 82 23.13 Optical Fiber Splicing and Terminations
33 82 33 Coaxial Communications Transmission and Distribution Cabling
33 82 33.13 Coaxial Splicing and Terminations
33 82 43 Grounding and Bonding for Communications Transmission and Distribution
33 82 46 Cable Pressurization Equipment
33 82 53 Cleaning, Lubrication, and Restoration Chemicals
33 82 63 Shelter Equipment
33 82 63.13 Transceivers
33 82 63.16 Control Panels
33 82 63.23 Power-Line Carriers
33 82 63.43 Backup Batteries
33 83 00 Wireless Communications Transmission and Distribution
33 83 13 Laser Transmitters and Receivers
33 83 16 Microwave Transmitters and Receivers
33 83 17 Microwave Antennas
33 83 17.13 Microwave Waveguides
33 83 19 Infrared Transmitters and Receivers
33 83 23 Radio Antennas
34 00 00 Transportation
34 01 00 Operation and Maintenance of Transportation
34 01 13 Operation and Maintenance of Roadways
34 01 23 Operation and Maintenance of Railways
34 01 23.13 Track Removal and Salvage
34 01 23.81 Track Crosstie Replacement
34 01 33 Operation and Maintenance of Airfields
34 01 43 Operation and Maintenance of Bridges
34 05 00 Common Work Results for Transportation
34 05 05 Selective Demolition for Transportation
34 05 13 Common Work Results for Roadways
34 05 23 Common Work Results for Railways
34 05 33 Common Work Results for Airports
34 05 43 Common Work Results for Bridges
34 06 00 Schedules for Transportation
34 06 13 Schedules for Roadways
34 06 23 Schedules for Railways
34 06 33 Schedules for Airfields
34 06 43 Schedules for Bridges
34 08 00 Commissioning of Transportation
34 08 13 Commissioning of Roadways
34 08 23 Commissioning of Railways
34 08 33 Commissioning of Airfields
34 08 43 Commissioning of Bridges
34 10 00 Guideways/Railways
34 11 00 Rail Tracks
34 11 13 Track Rails
34 11 13.13 Light Rail Track
34 11 13.23 Heavy Rail Track
34 11 16 Welded Track Rails
34 11 16.13 In-Track Butt-Welded Track Rail
34 11 16.16 Pressure-Welded Track Rail
34 11 16.19 Thermite-Welded Track Rail
34 11 19 Track Rail Joints
34 11 23 Special Trackwork
34 11 23.13 Ballasted Special Track Rail
34 11 23.16 Direct-Fixation Track
34 11 23.23 Running Rail
34 11 23.26 Precurved Running Rail
34 11 26 Ballasted Track Rail
34 11 26.13 Track Rail Ballast
34 11 26.16 Track Rail Subballast
34 11 29 Embedded Track Rail
34 11 33 Track Cross Ties
34 11 33.13 Concrete Track Cross Ties
34 11 33.16 Timber Track Cross Ties
34 11 33.19 Resilient Track Cross Ties
34 11 36 Track Rail Fasteners
34 11 36.13 Direct-Fixation Fasteners
34 11 39 Track Collector Pans
34 11 39.13 Fiberglass Track Collector Pans
34 11 93 Track Appurtenances and Accessories
34 12 00 Monorails
34 12 13 Elevated Monorails
34 12 16 On-Grade Monorails
34 12 19 Below-Grade Monorails
34 12 23 Maglev Monorail
34 12 63 Monorail Track
34 13 00 Funiculars
34 13 13 Inclined Railway
34 14 00 Cable Transportation
34 14 13 Aerial Tramways
34 14 19 Gondolas
34 14 26 Funitels
34 14 33 Chairlifts
34 14 39 Surface Lifts
34 14 46 Ropeway Tows
34 14 53 Cable Car Systems
34 20 00 Traction Power
34 21 00 Traction Power Distribution
34 21 13 High Power Static Frequency Converters
34 21 16 Traction Power Substations
34 21 16.13 AC Traction Power Substations
34 21 16.16 DC Traction Power Substations
34 21 19 Traction Power Switchgear
34 21 19.13 AC Traction Power Switchgear
34 21 19.16 DC Traction Power Switchgear
34 21 19.23 Frequency Changer
34 21 23 Traction Power Transformer-Rectifier Units
34 23 00 Overhead Traction Power
34 23 13 Traction Power Poles
34 23 16 Overhead Cable Suspension
34 23 23 Overhead Traction Power Cables
34 24 00 Third Rail Traction Power
34 24 13 Bottom-Contact Third Rail
34 24 16 Side-Contact Third Rail
34 24 19 Top-Contact Third Rail
34 40 00 Transportation Signaling and Control Equipment
34 41 00 Roadway Signaling and Control Equipment
34 41 13 Traffic Signals
34 41 16 Traffic Control Equipment
34 41 23 Roadway Monitoring Equipment
34 41 33 In Roadway Warning Lights
34 42 00 Railway Signaling and Control Equipment
34 42 13 Railway Signals
34 42 13.13 General Railway Signal Requirements
34 42 13.16 Signal Solid State Coded Track Circuits
34 42 16 Train Control Wires and Cables
34 42 19 Vital Interlocking Logic Controllers
34 42 23 Railway Control Equipment
34 42 23.13 Mainline Train Control Room Equipment
34 42 23.16 Yard Train Control Room Equipment
34 42 23.19 Integrated Control Equipment
34 42 23.23 Interlocking Railway Control Equipment
34 42 26 Rail Network Equipment
34 42 29 Station Agent Equipment
34 42 33 Yard Management Equipment
34 42 36 Supervisory Control and Data Acquisition
34 43 00 Airfield Signaling and Control Equipment
34 43 13 Airfield Signals and Lighting
34 43 13.09 Airport Rotating Beacons
34 43 13.10 Hazard Beacons
34 43 13.11 Airport Beacon Towers
34 43 13.12 Airport Obstruction Lights
34 43 13.13 Airfield Runway Identification Lights
34 43 13.16 Airfield Runway and Taxiway Inset Lighting
34 43 13.19 Adhesive for Inset Lighting & Wiring
34 43 13.23 Airfield Short-Approach Lighting Equipment
34 43 13.26 Airfield Omni-Directional-Approach Lighting Equipment
34 43 13.29 Airfield Low-Intensity-Approach Lighting Equipment
34 43 13.33 Airfield High-Intensity-Approach Lighting Equipment
34 43 13.36 Airfield Precision-Approach Path Indicator Equipment
34 43 16 Airfield Landing Equipment
34 43 16.13 Microwave Airfield Landing Equipment
34 43 16.16 Instrument Airfield Landing Equipment
34 43 16.19 Airfield Visual-Approach Slope Indicator Equipment
34 43 19 Airfield Traffic Control Tower Equipment
34 43 23 Weather Observation Equipment
34 43 23.13 Automatic Weather Observation Equipment
34 43 23.16 Airfield Wind Cones
34 43 26 Airfield Control Equipment
34 43 26.13 Airfield Lighting Control Equipment
34 43 26.16 Airfield Lighting PLC Control Equipment
34 43 26.19 Airfield Lighting Regulator Assembly
34 48 00 Bridge Signaling and Control Equipment
34 48 13 Operating Bridge Signals
34 48 16 Operating Bridge Control Equipment
34 50 00 Transportation Fare Collection Equipment
34 52 00 Vehicle Fare Collection
34 52 16 Vehicle Ticketing Equipment
34 52 16.13 Vehicle Ticket Vending Machines
34 52 26 Vehicle Fare Collection Equipment
34 52 26.13 Vehicle Coin Fare Collection Equipment
34 52 26.16 Vehicle Electronic Fare Collection Equipment
34 52 33 Vehicle Fare Gates
34 54 00 Passenger Fare Collection
34 54 16 Passenger Ticketing Equipment
34 54 16.13 Passenger Ticket Vending Machines
34 54 16.16 Passenger Addfare Machines
34 54 16.23 Passenger Intermodal Transfer Machines
34 54 26 Passenger Fare Collection Equipment
34 54 26.13 Passenger Coin Fare Collection Equipment
34 54 26.16 Passenger Electronic Fare Collection Equipment
34 54 33 Passenger Fare Gates
34 70 00 Transportation Construction and Equipment
34 71 00 Roadway Construction
34 71 13 Vehicle Barriers
34 71 13.13 Vehicle Median Barriers
34 71 13.16 Vehicle Crash Barriers
34 71 13.19 Vehicle Traffic Barriers
34 71 13.26 Vehicle Guide Rails
34 71 13.29 Vehicle Barrier Fenders
34 71 16 Impact Attenuating Devices
34 71 19 Vehicle Delineators
34 71 19.13 Fixed Vehicle Delineators
34 71 19.16 Flexible Vehicle Delineators
34 72 00 Railway Construction
34 72 13 Railway Line
34 72 16 Railway Siding
34 73 00 Airfield Construction
34 73 13 Aircraft Tiedowns
34 73 16 Airfield Grounding
34 73 16.13 Aircraft Static Grounding
34 73 19 Jet Blast Barriers
34 73 23 Manufactured Airfield Control Towers
34 73 26 Manufactured Helipads
34 75 00 Roadway Equipment
34 75 13 Operable Roadway Equipment
34 75 13.13 Active Vehicle Barriers
34 76 00 Railway Equipment
34 76 13 Roadway Crossing Control Equipment
34 77 00 Transportation Equipment
34 77 13 Passenger Boarding Bridges
34 77 13.13 Fixed Aircraft Passenger Boarding Bridges
34 77 13.16 Movable Aircraft Passenger Boarding Bridges
34 77 13.23 Ship Passenger Boarding Bridges
34 77 33 Baggage Scanning Equipment
34 77 36 Baggage Scales
34 77 39 Baggage Conveying Equipment
34 78 00 Weighing Equipment
34 78 13 Truck Scales
34 78 16 Weighbridges
34 78 23 Railroad Car Scales
34 78 33 Crane Scales
34 80 00 Bridges
34 81 00 Bridge Machinery
34 81 13 Single-Swing Bridge Machinery
34 81 16 Double-Swing Bridge Machinery
34 81 19 Cantilever Bridge Machinery
34 81 23 Lift Bridge Machinery
34 81 26 Sliding Bridge Machinery
34 81 29 Pontoon Bridge Machinery
34 81 32 Bascule Bridge Machinery
34 82 00 Bridge Specialties
34 82 13 Bridge Vibration Dampers
34 82 13.13 Visco Elastic Bridge Vibration Dampers
34 82 13.16 Tuned-Mass Bridge Vibration Dampers
34 82 19 Bridge Pier Protection
34 82 19.13 Bridge Pier Ice Shields
35 00 00 Waterway and Marine Construction
35 01 00 Operation and Maintenance of Waterway and Marine Construction
35 01 30 Operation and Maintenance of Coastal Construction
35 01 40 Operation and Maintenance of Waterway Construction
35 01 40.51 Waterway Dredging
35 01 40.92 Preservation of Water Courses
35 01 50 Operation and Maintenance of Marine Construction
35 01 50.51 Marine Dredging
35 01 50.71 Channel Excavation, Cleaning and Deepening
35 01 70 Operation and Maintenance of Dams
35 05 00 Common Work Results for Waterway and Marine Construction
35 05 05 Selective Demolition for Waterway and Marine Construction
35 05 30 Common Work Results for Coastal Construction
35 05 40 Common Work Results for Waterway Construction
35 05 50 Common Work Results for Marine Construction
35 05 70 Common Work Results for Dams
35 06 00 Schedules for Waterway and Marine Construction
35 06 30 Schedules for Coastal Construction
35 06 40 Schedules for Waterway Construction
35 06 50 Schedules for Marine Construction
35 06 70 Schedules for Dams
35 08 00 Commissioning of Waterway and Marine Construction
35 08 30 Commissioning of Coastal Construction
35 08 40 Commissioning of Waterway Construction
35 08 50 Commissioning of Marine Construction
35 08 70 Commissioning of Dams
35 10 00 Waterway and Marine Signaling and Control Equipment
35 11 00 Signaling and Control Equipment for Waterways
35 11 13 Signaling Equipment for Waterways
35 11 53 Control Equipment for Waterways
35 12 00 Marine Signaling and Control Equipment
35 12 13 Marine Signaling Equipment
35 12 13.13 Lighthouse Equipment
35 12 33 Marine Navigation Equipment
35 12 53 Marine Control Equipment
35 13 00 Signaling and Control Equipment for Dams
35 13 13 Signaling Equipment for Dams
35 13 53 Control Equipment for Dams
35 20 00 Waterway and Marine Construction and Equipment
35 21 00 General Fabrications for Waterways
35 21 13 Hydraulic Bifurcation Panels
35 21 16 Hydraulic Bulkheads
35 21 19 Hydraulic Manifolds
35 21 23 Penstocks
35 21 33 Trash Racks
35 21 36 Debris Cages
35 22 00 Hydraulic Gates
35 22 13 Spillway Crest Gates
35 22 19 Hydraulic Head Gates
35 22 26 Sluice Gates
35 22 33 Miter Gates
35 22 39 Sector Gates
35 22 46 Tainter Gates
35 22 53 Vertical Lift Hydraulic Gates
35 22 59 Hydraulic Closure Gates
35 22 63 Through-Levee Access Gates
35 24 00 Dredging
35 24 13 Suction Dredging
35 24 13.11 Training Suction Dredging
35 24 13.13 Cutter Suction Dredging
35 24 13.16 Auger Suction Dredging
35 24 13.23 Jet-Lift Dredging
35 24 13.26 Air-Lift Dredging
35 24 21 Bucket Dredging
35 24 23 Clamshell Dredging
35 24 26 Backhoe/Dipper Dredging
35 24 33 Water Injection Dredging
35 24 36 Pneumatic Dredging
35 24 43 Bed-Levelling Dredging
35 24 46 Krabbelaar Dredging
35 24 53 Waterway Snag Removal
35 30 00 Coastal Construction
35 31 00 Shoreline Protection
35 31 16 Seawalls
35 31 16.13 Concrete Seawalls
35 31 16.16 Segmental Seawalls
35 31 16.19 Steel Sheet Piling Seawalls
35 31 16.23 Timber Seawalls
35 31 16.40 Stone Seawalls
35 31 19 Revetments
35 31 19.13 Sacked Cement-Sand Revetments
35 31 19.16 Concrete Unit Masonry Revetments
35 31 19.36 Gabion Revetments
35 31 19.40 Stone Revetments
35 31 23 Breakwaters
35 31 23.13 Rubble Mound Breakwaters
35 31 23.16 Precast Breakwater Modules
35 31 26 Jetties
35 31 26.13 Concrete Jetties
35 31 26.16 Concrete Unit Masonry Jetties
35 31 26.36 Gabion Jetties
35 31 26.40 Stone Jetties
35 31 29 Groins
35 31 29.13 Concrete Groins
35 31 29.16 Concrete Unit Masonry Groins
35 31 29.26 Steel Groins
35 31 29.36 Gabion Groins
35 31 29.40 Stone Groins
35 32 00 Artificial Reefs
35 32 13 Scrap Material Artificial Reefs
35 32 13.13 Scrap Concrete Artificial Reefs
35 32 13.19 Scrap Steel Artificial Reefs
35 32 13.33 Sunken Ship Artificial Reefs
35 32 16 Constructed Artificial Reefs
35 32 16.13 Constructed Concrete Artificial Reefs
35 32 16.19 Constructed Steel Artificial Reefs
35 40 00 Waterway Construction and Equipment
35 41 00 Levees
35 41 13 Landside Levee Berms
35 41 13.13 Stability Landside Levee Berms
35 41 13.16 Seepage Landside Levee Berms
35 41 16 Levee Cutoff Trenches
35 41 19 Levee Relief Wells
35 42 00 Waterway Bank Protection
35 42 13 Piling Bank Protection
35 42 13.19 Steel Sheet Piling Bank Protection
35 42 13.23 Timber Piling Bank Protection
35 42 13.26 Plastic Piling Bank Protection
35 42 29 Grout-Bag Bank Protection
35 42 34 Soil Reinforcement Bank Protection
35 42 35 Slope Protection Bank Protection
35 42 36 Gabion Bank Protection
35 42 37 Riprap Bank Protection
35 42 53 Wall Bank Protection
35 42 53.16 Concrete Unit Masonry Wall Bank Protection
35 42 53.19 Segmental Wall Bank Protection
35 42 53.40 Stone Wall Bank Protection
35 43 00 Waterway Scour Protection
35 43 29 Grout-Bag Scour Protection
35 43 34 Soil Reinforcement Scour Protection
35 43 35 Slope Protection Scour Protection
35 43 36 Gabion Scour Protection
35 43 37 Riprap Scour Protection
35 43 53 Wall Scour Protection
35 43 53.13 Concrete Unit Masonry Wall Scour Protection
35 43 53.16 Segmental Wall Scour Protection
35 43 53.40 Stone Wall Scour Protection
35 49 00 Waterway Structures
35 49 13 Floodwalls
35 49 13.13 Concrete Floodwalls
35 49 13.16 Masonry Floodwalls
35 49 23 Waterway Locks
35 49 23.13 Concrete Waterway Locks
35 49 23.23 Piling Waterway Locks
35 49 26 Floodgate Machinery
35 50 00 Marine Construction and Equipment
35 51 00 Floating Construction
35 51 13 Floating Piers
35 51 13.23 Floating Wood Piers
35 51 13.26 Floating Plastic Piers
35 51 23 Pontoons
35 52 00 Offshore Platform Construction
35 52 13 Fixed Offshore Platform Construction
35 52 23 Semi-Submersible Offshore Platform Construction
35 52 33 Floating Offshore Platform Construction
35 53 00 Underwater Construction
35 53 23 Underwater Harbor Deepening
35 53 33 Underwater Pipeline Construction
35 53 43 Underwater Foundation Construction
35 53 53 Underwater Structures Construction
35 53 63 Underwater Waterproofing
35 59 00 Marine Specialties
35 59 13 Marine Fenders
35 59 13.13 Prestressed Concrete Marine Fender Piling
35 59 13.16 Resilient Foam-Filled Marine Fenders
35 59 13.19 Rubber Marine Fenders
35 59 23 Buoys
35 59 23.13 Mooring Buoys
35 59 23.16 Anchor Pendant Buoys
35 59 23.19 Navigation Buoys
35 59 29 Mooring Devices
35 59 29.13 Quick-Release Mooring Hooks
35 59 29.16 Laser Docking Systems
35 59 29.19 Capstans
35 59 33 Marine Bollards and Cleats
35 59 33.13 Cast-Steel Marine Bollards and Cleats
35 59 33.16 Cast-Iron Marine Bollards and Cleats
35 59 33.19 Stainless-Steel Marine Bollards and Cleats
35 59 33.23 Plastic Marine Bollards and Cleats
35 59 93 Marine Chain and Accessories
35 59 93.13 Marine Chain
35 59 93.16 Marine Shackles
35 59 93.19 Marine Chain Tensioners
35 70 00 Dam Construction and Equipment
35 71 00 Gravity Dams
35 71 13 Concrete Gravity Dams
35 71 16 Masonry Gravity Dams
35 71 19 Rockfill Gravity Dams
35 72 00 Arch Dams
35 72 13 Concrete Arch Dams
35 73 00 Embankment Dams
35 73 13 Earth Embankment Dam
35 73 16 Rock Embankment Dams
35 74 00 Buttress Dams
35 74 13 Concrete Buttress Dams
35 79 00 Auxiliary Dam Structures
35 79 13 Fish Ladders
35 79 13.13 Concrete Fish Ladders
40 00 00 Process Interconnections
40 01 00 Operation and Maintenance of Process Interconnections
40 01 10 Operation and Maintenance of Gas and Vapor Process Piping
40 01 20 Operation and Maintenance of Liquids Process Piping
40 01 30 Operation and Maintenance of Solid and Mixed Materials Piping and Chutes
40 01 40 Operation and Maintenance of Process Piping and Equipment Protection
40 01 60 Operation and Maintenance of Process Control and Process Facility Enterprise Management Systems
40 01 70 Operation and Maintenance of Instrumentation for Process Systems
40 01 90 Operation and Maintenance of Primary Control Devices
40 05 00 Common Work Results for Process Interconnections
40 05 05 Exposed Piping Installation
40 05 06 Couplings, Adapters, and Specials for Process Piping
40 05 07 Hangers and Supports for Process Piping
40 05 09 Wall Pipes, Floor Pipes, and Pipe Sleeves
40 05 11 Aluminum Process Pipe
40 05 12 Brass Process Pipe
40 05 13 Bronze Process Pipe
40 05 17 Copper Process Pipe and Tubing
40 05 19 Ductile Iron Process Pipe
40 05 21 High-Alloy Nickel Process Pipe and Tubing
40 05 23 Stainless Steel Process Pipe and Tubing
40 05 23.13 Duplex and Super-Duplex Stainless Steel Process Pipe
40 05 23.23 300- and 400-Series Stainless Steel Process Pipe
40 05 23.33 Special-Fabrication Stainless Steel Process Pipe and Tubing
40 05 24 Steel Process Pipe
40 05 24.13 Steel Pipe and Tubing for Air and Gas Service
40 05 24.23 Steel Pipe for Water Service
40 05 24.26 Steel Pipe and Tubing for Process Liquid Service
40 05 24.33 Steel Pipe for Bulk Materials Conveyance
40 05 26 Other Metals Process Pipe
40 05 26.13 Titanium Process Pipe
40 05 26.23 Tantalum Process Pipe
40 05 26.33 Zirconium Process Pipe
40 05 31 Thermoplastic Process Pipe
40 05 31.13 Polyvinyl Chloride Process Pipe
40 05 31.23 Chlorinated Polyvinyl Chloride Process Pipe
40 05 31.33 ABS Process Pipe
40 05 31.43 Polypropylene Process Pipe
40 05 31.53 PVDF Process Pipe
40 05 31.63 High-Purity Plastic Process Pipe
40 05 31.83 Flexible Plastic Tubing
40 05 33 High-Density Polyethylene Process Pipe
40 05 36 Fiberglass-Reinforced Plastic Process Pipe
40 05 36.13 Fiberglass-Reinforced Plastic Pipe for Process Air, Gas, and Odor Service
40 05 36.23 Fiberglass-Reinforced Plastic Pipe for Process Liquid Service
40 05 37 Centrifugally Cast Fiberglass-Reinforced Polymer Mortar Process Pipe
40 05 38 PTFE Process Pipe
40 05 39 Concrete Pipe
40 05 39.13 Concrete Pressure Water Pipe
40 05 39.23 Concrete Gravity and Drainage Process Pipe
40 05 51 Common Requirements for Process Valves
40 05 53 Process Valves Four-inch Diameter and Larger
40 05 56 Process Valves, Smaller than Four-inch Diameter
40 05 57 Actuators for Process Valves and Gates
40 05 57.13 Manual Actuators
40 05 57.23 Electric Motor Actuators
40 05 57.33 Hydraulic Cylinder Actuators
40 05 57.43 Hydraulic Actuator Systems
40 05 57.53 Pneumatic Actuators
40 05 59 Hydraulic Gates
40 05 59.13 Stop Plates
40 05 59.16 Stop Logs
40 05 59.21 Aluminum Slide Gates
40 05 59.23 Stainless Steel Slide Gates
40 05 59.26 Fiberglass-Reinforced Plastic Slide Gates
40 05 59.33 Cast Iron Slide Gates
40 05 59.43 Butterfly Gates
40 05 61 Gate Valves
40 05 61.13 Solid Wedge Metal-Seated Gate Valves
40 05 61.16 Double Disc Metal-Seated Gate Valves
40 05 61.23 Resilient-Seated Gate Valves
40 05 61.43 Knife Gate Valves
40 05 62 Plug Valves
40 05 62.13 Eccentric Plug Valves for Gas Service
40 05 62.16 Eccentric Plug Valves for Liquid Service
40 05 63 Ball Valves
40 05 63.13 AWWA Metal-Seated Ball Valves
40 05 63.16 AWWA Resilient-Seated Ball Valves
40 05 63.33 Metallic Ball Valves
40 05 63.43 Plastic Ball Valves
40 05 64 Butterfly Valves
40 05 64.13 Metal-Seated Butterfly Valves
40 05 64.16 AWWA Resilient-Seated Butterfly Valves
40 05 64.23 Metallic Industrial Butterfly Valves
40 05 64.26 Plastic Industrial Butterfly Valves
40 05 64.33 Butterfly Valves in Air or Gas Service
40 05 64.36 High-Performance Butterfly Valves in Air or Gas Service
40 05 64.43 Dampers for Corrosive Gas Service
40 05 65 Valves for Pump Control and Check Service
40 05 65.11 Angle Valves
40 05 65.13 Cone Valves
40 05 65.16 Globe Valves
40 05 65.23 Swing Check Valves
40 05 65.26 Tilting Disc Check Valves
40 05 65.29 Double-Disk Check Valves
40 05 67 Specialized Pressure and Flow-Control Valves
40 05 67.13 Reduced-Pressure Zone Backflow Preventers for Process Service
40 05 67.16 Double Check Valve Assembly Backflow Preventers for Process Service
40 05 67.23 Pressure Vacuum Breaker Backflow Preventers
40 05 67.26 Atmospheric Vacuum Breaker Backflow Preventers
40 05 67.29 Hose Connection Vacuum Breaker Backflow Preventers
40 05 67.33 Backpressure Valves
40 05 67.36 Pressure-Regulating Valves
40 05 67.39 Pressure-Relief Valves
40 05 67.41 Direct-Acting Surge Relief Valves for Water Service
40 05 67.43 Pilot-Operated Surge Relief Valves for Water Service
40 05 67.44 Pilot-Operated Surge Arrestor Valves for Water Service
40 05 67.46 Electronic Surge Anticipator Valves for Water Service
40 05 67.47 Surge Relief Valves for Wastewater Service
40 05 67.49 Electronic Surge Anticipator Valves for Wastewater Service
40 05 71 Solids Handling Valves
40 05 71.13 Duckbill Check Valves
40 05 71.16 Flap Gates
40 05 71.23 Mud Valves
40 05 71.33 Telescoping Valves
40 05 73 Special-Application Process Valves
40 05 73.13 Altitude Valves
40 05 73.16 Float Valves
40 05 73.23 Anti-Cavitation Valves
40 05 74 Flexible-Closure Valves
40 05 74.13 Diaphragm Valves
40 05 74.23 Pinch Valves
40 05 76 Hot-Tapping Valves and Appurtenances
40 05 76.13 Tapping Sleeves and Valves
40 05 76.16 Tapping Machines
40 05 76.23 Line Stops
40 05 78 Air Valves for Water and Wastewater Service
40 05 78.11 Air Release Valves for Water Service
40 05 78.13 Air/Vacuum Valves for Water Service
40 05 78.16 Vacuum-Breaking Valves for Water Service
40 05 78.19 Combination Air Valves for Water Service
40 05 78.21 Air Release Valves for Wastewater Service
40 05 78.23 Air/Vacuum Valves for Wastewater Service
40 05 78.26 Vacuum-Breaking Valves for Wastewater Service
40 05 78.29 Combination Air Valves for Wastewater Service
40 05 81 Hydrants and Hose Bibbs for Process Service
40 05 81.13 Fire Hydrants
40 05 81.23 Yard Hydrants
40 05 81.26 Freeze-Proof Yard Hydrants
40 05 81.33 Hose Bibbs
40 05 82 Solenoid Valves for Process Service
40 05 89 Valve Accessories
40 05 89.13 Basket Strainers for Process Service
40 05 89.23 Needle Valves
40 05 89.33 Quick-Connect Couplers
40 05 93 Common Motor Requirements for Process Equipment
40 05 96 Vibration and Seismic Controls for Process Equipment
40 05 97 Identification for Process Equipment
40 06 00 Schedules for Process Interconnections
40 06 10 Schedules for Gas and Vapor Process Piping and Ductwork
40 06 20 Schedules for Liquids Process Piping
40 06 30 Schedules for Solid and Mixed Materials Piping and Chutes
40 06 40 Schedules for Process Piping and Equipment Protection
40 06 60 Schedules for Process Control and Process Facility Enterprise Management Systems
40 06 70 Schedules of Instrumentation for Process Systems
40 06 90 Schedules for Primary Control Devices
40 10 00 Gas and Vapor Process Piping and Ductwork
40 11 00 Steam Process Piping
40 11 13 Low-Pressure Steam Process Piping
40 11 16 Intermediate-Pressure Steam Process Piping
40 11 19 High-Pressure Steam Process Piping
40 11 23 Condensate Process Piping for Process Applications
40 12 00 Compressed Air Process Piping
40 12 13 Compressed Air Process Piping for Breathing Service
40 12 23 Low-Pressure Compressed Air Process Piping
40 12 53 High-Pressure Compressed Air Process Piping
40 13 00 Process Ductwork
40 15 00 Combustion System Gas Piping
40 15 13 Combustion Air Piping
40 15 16 Oxygen Combustion System Gas Piping
40 15 19 Flue-Gas Combustion System Piping
40 15 23 Exothermic-Gas Combustion System Piping
40 15 26 Endothermic-Gas Combustion System Piping
40 15 29 Dissociated-Ammonia-Gas Combustion System Piping
40 16 00 Specialty and High-Purity Gases Piping
40 16 13 Ammonia Gas Piping
40 16 16 Boron Gas Piping
40 16 17 Chlorine Gas Piping
40 16 26 Diborane Gas Piping
40 16 29 Fluorine Gas Piping
40 16 33 Hydrogen Sulfide Gas Piping
40 16 36 Nitrous-Oxide Gas Process Piping
40 16 37 Oxygen Gas Process Piping
40 16 39 Ozone Gas Process Piping
40 16 43 Phosphine Gas Piping
40 16 46 Silane Gas Piping
40 16 49 Sulfur-Dioxide Gas Piping
40 16 53 Specialty Gas Mixtures Piping
40 16 56 High-Purity Gas Piping Components
40 17 00 Welding and Cutting Gases Piping
40 17 13 Acetylene Welding and Cutting Piping
40 17 16 Acetylene-Hydrogen Mix Welding and Cutting Piping
40 17 19 Methylacetylene-Propadiene Welding and Cutting Piping
40 17 23 Oxygen Welding and Cutting Piping
40 17 26 Inert Gas Welding and Cutting Piping
40 18 00 Vacuum Systems Process Piping
40 18 13 Low-Vacuum Systems Process Piping
40 18 23 Chlorine Gas Vacuum System Piping
40 18 53 High-Vacuum Systems Process Piping
40 20 00 Liquids Process Piping
40 21 00 Liquid Fuel Process Piping
40 21 13 Bio Fuels Process Piping
40 21 13.13 Bioalcohols Process Piping
40 21 13.23 Biodiesel Fuel Process Piping
40 21 13.26 Green Diesel Fuel Process Piping
40 21 13.33 Biomass-to-Liquid (BTL) Fuel Process Piping
40 21 13.43 Gas-to-Liquid (GTL) Fuel Process Piping
40 21 16 Gasoline Process Piping
40 21 19 Diesel Process Piping
40 21 23 Fuel-Oils Process Piping
40 21 23.13 No. 1 Fuel-Oil Process Piping
40 21 23.23 No. 2 Fuel-Oil Process Piping
40 21 23.26 Kerosene Process Piping
40 21 23.29 Tar Fuels Process Piping
40 21 23.43 No. 4 Fuel-Oil Process Piping
40 21 23.53 No. 5 Fuel-Oil Process Piping
40 21 23.63 No. 6 Fuel-Oil Process Piping
40 22 00 Petroleum Products Piping
40 22 10 Heavy-Fractions Petroleum Products Piping
40 22 13 Liquefied Petroleum Gas (LPG) Process Piping
40 22 16 Lubricating Oils Process Piping
40 22 23 Petrochemicals Process Piping
40 22 50 Light-Fractions Petroleum Products Piping
40 23 00 Water and Wastewater Process Piping
40 23 13 Deionized Water Process Piping
40 23 16 Distilled-Water Process Piping
40 23 19 Non-Potable Plant Water Process Piping
40 23 23 Potable Water Process Piping
40 23 29 Recirculated Water Process Piping
40 23 33 Reverse-Osmosis Water Process Piping
40 23 40 Sanitary Wastewater Process Piping
40 23 41 Grit Process Piping
40 23 43 Scum and Floatables Process Piping
40 23 44 Primary Sludge Process Piping
40 23 46 Waste Sludge Process Piping
40 23 48 Thickened Sludge Process Piping
40 24 00 Specialty Liquid Chemicals Piping
40 24 13 Alcohol Piping
40 24 14 Liquid Chlorine and Sodium Hypochlorite Piping
40 24 16 Gel Piping
40 24 19 Slurries Process Piping
40 24 23 Thixotropic Liquid Piping
40 25 00 Liquid Acids and Bases Piping
40 25 10 Liquid Acids Piping
40 25 50 Liquid Bases Piping
40 26 00 Liquid Polymer Piping
40 30 00 Solid and Mixed Materials Piping and Chutes
40 32 00 Bulk Materials Piping and Chutes
40 32 10 Abrasive Materials Piping and Chutes
40 32 50 Nonabrasive Materials Piping and Chutes
40 33 00 Bulk Materials Valves
40 33 13 Airlock Bulk Materials Valves
40 33 16 Blind Bulk Materials Valves
40 33 26 Diverter Bulk Materials Valves
40 33 29 Double or Single Dump Bulk Materials Valves
40 33 39 Swing Bulk Materials Valves
40 33 43 Specialty Bulk Materials Valves
40 34 00 Pneumatic Conveying Lines
40 34 10 Dense Phase Pneumatic Conveying Lines
40 34 50 Dilute Phase Pneumatic Conveying Lines
40 40 00 Process Piping and Equipment Protection
40 41 00 Process Piping and Equipment Heat Tracing
40 41 13 Process Piping Heat Tracing
40 41 13.13 Process Piping Electrical Resistance Heat Tracing
40 41 13.16 Process Piping Electrical Conductance Heat Tracing
40 41 13.19 Process Piping Gas Heat Tracing
40 41 13.23 Process Piping Steam Heat Tracing
40 41 13.26 Process Piping Thermal Fluids Heat Tracing
40 41 23 Process Equipment Heat Tracing
40 41 23.13 Process Equipment Electrical Resistance Heat Tracing
40 41 23.16 Process Equipment Electrical Conductance Heat Tracing
40 41 23.19 Process Equipment Gas Heat Tracing
40 41 23.23 Process Equipment Steam Heat Tracing
40 41 23.26 Process Equipment Thermal Fluids Heat Tracing
40 42 00 Process Piping and Equipment Insulation
40 42 13 Process Piping Insulation
40 42 13.13 Cryogenic Temperature Process Piping Insulation
40 42 13.16 Low Temperature Process Piping Insulation
40 42 13.19 Intermediate Temperature Process Piping Insulation
40 42 13.23 High Temperature Process Piping Insulation
40 42 13.26 Process Piping Insulation for Specialty Applications
40 42 23 Process Equipment Insulation
40 42 23.13 Cryogenic Temperature Process Equipment Insulation
40 42 23.16 Low Temperature Process Equipment Insulation
40 42 23.19 Intermediate Temperature Process Equipment Insulation
40 42 23.23 High Temperature Process Equipment Insulation
40 42 23.26 Process Equipment Insulation for Specialty Applications
40 46 00 Process Corrosion Protection
40 46 16 Coatings and Wrappings for Process Corrosion Protection
40 46 42 Cathodic Process Corrosion Protection
40 47 00 Refractories
40 47 13 Silica Refractories
40 47 16 Alumina Refractories
40 47 19 Carbon and Graphite Refractories
40 47 23 Castable Refractories
40 47 26 Rammed Refractories
40 47 29 Refractory Concrete
40 60 00 Process Control and Enterprise Management Systems
40 61 00 Process Control and Enterprise Management Systems General Provisions
40 61 13 Process Control System General Provisions
40 61 16 Enterprise Management System General Provisions
40 61 21 Process Control System Testing
40 61 26 Process Control System Training
40 61 93 Process Control System Input/Output List
40 61 96 Process Control Descriptions
40 62 00 Computer System Hardware and Ancillaries
40 62 13 Server Computers
40 62 16 Operator Workstation Computers
40 62 19 Industrial Computers
40 62 21 Desktop Computers
40 62 23 Mobile Computers
40 62 26 Laptop Computers
40 62 29 Tablet Computers and Mobile Devices
40 62 33 Printers
40 62 43 Large Display Screens
40 62 63 Operator Interface Terminals (OIT)
40 63 00 Control System Equipment
40 63 13 Distributed Process Control Systems
40 63 43 Programmable Logic Controllers
40 63 83 Remote Terminal Units
40 66 00 Network and Communication Equipment
40 66 13 Switches and Routers
40 66 16 Firewall Hardware
40 66 19 Media Converters
40 66 23 Frame Relay Equipment
40 66 26 Device Network Equipment
40 66 33 Metallic and Fiber-Optic Communication Cabling and Connectors
40 66 36 Process Instrumentation Networks
40 66 43 Wireless Network Systems
40 66 53 Multiple Address Radio Equipment
40 66 56 Point-to-Point Radio Equipment
40 66 63 Antennas
40 66 66 Monopoles and Towers
40 66 73 Satellite Communication Equipment
40 67 00 Control System Equipment Panels and Racks
40 67 13 Computer Equipment Racks
40 67 16 Free-Standing Panels
40 67 19 Wall-Mounted Panels
40 67 23 Control System Consoles
40 67 33 Panel Wiring
40 67 63 Control Panel-Mounted Uninterruptible Power Supply
40 68 00 Process Control Software
40 68 13 Process Control (HMI) Software
40 68 23 Reporting Software
40 68 26 Online Performance Monitoring Systems Software
40 68 33 Maintenance Management Software
40 68 36 Laboratory Information System Software
40 68 39 Energy Management Software
40 68 43 Load Management Software
40 68 63 Configuration of HMI Software
40 68 66 Programming of Controller Software
40 68 93 Computer Operating Systems Software
40 69 00 Packaged Control Systems
40 69 13 Control System Simulators
40 69 23 Burner Management Systems
40 69 26 Safety Instrumented Control Systems
40 69 33 Fire and Gas Monitoring/Protection Systems for Industrial Applications
40 70 00 Instrumentation for Process Systems
40 71 00 Flow Measurement
40 71 13 Magnetic Flow Meters
40 71 13.13 Inline Magnetic Flow Meters
40 71 13.23 Insertion-Type Magnetic Flow Meters
40 71 23 Differential Pressure-Type Flow Meters
40 71 23.13 Venturi Flow Meters
40 71 23.16 Flow Tubes
40 71 23.19 Flow Nozzle-Type Flow Meters
40 71 23.23 Orifice Plate Flow Meters
40 71 23.26 Integral Orifice Flow Meters
40 71 23.29 Orifice Meter Runs
40 71 23.33 Elbow Flow Meters
40 71 23.36 Pitot Tube and Averaging Pitot Flow Meters
40 71 23.39 V-Cone Flow Meters
40 71 23.43 Differential Pressure-Type Flow Transmitters
40 71 23.46 Flow Computers
40 71 33 Propeller Flow Meters
40 71 36 Turbine Flow Meters
40 71 43 Variable Area Flow Meters
40 71 46 Target Flow Meters
40 71 49 Vortex-Shedding Flow Meters
40 71 53 Positive Displacement Flow Meters
40 71 63 Doppler Flow Meters
40 71 66 Transit Time Flow Meters
40 71 69 Open Channel Flow Meters
40 71 73 Coriolis Flow Meters
40 71 76 Thermal Flow Meters
40 71 79 Flow Switches
40 71 83 Sight Flow Indicators
40 71 86 Flow Metering Weirs
40 72 00 Level Measurement
40 72 13 Ultrasonic Level Meters (Continuous and Point-Type)
40 72 23 Radar Level Meters
40 72 26 Laser Level Meters
40 72 29 Nuclear Level Meters
40 72 33 Capacitance Type Level Meters (Continuous and Point Type)
40 72 36 RF Admittance Level Meters (Continuous and Point Type)
40 72 43 Pressure and Differential Pressure Type Level Meters
40 72 46 Bubbler Systems
40 72 53 Magnetic and Magnetostrictive Level Meters
40 72 63 Displacement-Type Level Meters
40 72 73 Sight Level Gauges
40 72 76 Level Switches
40 72 83 Leak Detection Systems
40 73 00 Pressure, Strain, and Force Measurement
40 73 13 Pressure and Differential Pressure Gauges
40 73 16 Manometers
40 73 23 Absolute-Pressure Transmitters
40 73 26 Gauge-Pressure Transmitters
40 73 29 Differential Pressure Transmitters
40 73 33 Multi-Variable Pressure/Temperature Transmitters
40 73 36 Pressure and Differential Pressure Switches
40 73 43 Force Measurement Devices
40 73 46 Load Cells
40 73 53 Torque Measurement Devices
40 73 63 Diaphragm Seals
40 74 00 Temperature Measurement
40 74 13 Resistance Temperature Devices
40 74 16 Thermocouples
40 74 23 Radiation Pyrometers
40 74 33 Thermistors
40 74 36 Diode Temperature Measurement Devices
40 74 43 Bimetallic Thermometers
40 74 46 Fluid Expansion Thermometers
40 74 49 Change-of-State Temperature Measurement Devices
40 74 53 Cryogenic Temperature Sensors
40 74 63 Temperature Transmitters
40 74 66 Temperature Switches
40 74 69 Thermowells, Protection Tubes, and Test Thermowells
40 75 00 Process Liquid Analytical Measurement
40 75 05 Multi-Parameter Analyzer Systems
40 75 13 pH/ORP Analyzers
40 75 16 Conductivity Analyzers
40 75 19 Moisture Analyzers
40 75 21 Chlorine Analyzers
40 75 21.13 Free-Chlorine Analyzers
40 75 21.23 Residual-Chlorine Analyzers
40 75 23 Chlorine Dioxide Analyzer
40 75 26 Dissolved Chlorine Dioxide Analyzers
40 75 29 Dissolved Ammonia Analyzers
40 75 33 Fluoride Analyzers
40 75 43 Dissolved Oxygen Analyzers
40 75 46 Dissolved Ozone Analyzers
40 75 53 Turbidity Analyzers
40 75 56 Suspended Solids/Sludge Density Analyzers
40 75 59 Liquid Density Analyzers
40 75 63 Monochloramine Analyzers
40 75 66 Nitrogen Analyzers
40 75 69 Phosphorous Analyzers
40 75 73 Particle Counters
40 75 76 Total Organic Carbon Analyzers
40 75 79 Total Organics Analyzers
40 75 83 Hardness Analyzers
40 75 86 Alkalinity Analyzer
40 76 00 Process Gas Analytical Measurement
40 76 05 Continuous Emissions Monitoring Systems
40 76 13 Oxygen Gas Analyzers
40 76 16 Ozone Analyzers
40 76 23 Combustible Gas Monitors
40 76 26 Chlorine Gas Analyzers
40 76 29 Ammonia Gas Analyzers
40 76 33 Hydrogen Sulfide Monitors
40 76 36 Sulfur Dioxide Analyzers
40 76 39 Carbon Dioxide Analyzers
40 76 43 Carbon Monoxide Analyzers
40 76 53 Dewpoint/Moisture Analyzers
40 76 56 Gas Density Analyzers
40 76 63 Flue Gas Analyzers
40 76 66 NO/NOX Analyzers
40 76 73 Hydrocarbon Analyzers
40 76 76 Gas Chromatograph Analyzers
40 76 79 Vapor Pressure Analyzers
40 76 83 Mass Spectrometers
40 77 00 Position and Motion Measurement
40 77 13 Acceleration Measurement Devices
40 77 16 Proximity Measurement Devices
40 77 19 Vibration Velocity Measurement Devices
40 77 23 Vibration Monitoring Systems
40 77 26 Position, Speed, and Motion Measurement Devices
40 78 00 Panel Mounted Instruments
40 78 13 Indicators and Meters
40 78 16 Indicating Lights
40 78 19 Switches and Push Buttons
40 78 23 Potentiometers and Manual Controllers
40 78 26 Chart Recorders
40 78 33 Annunciators
40 78 43 Single-Loop Controllers
40 78 53 Relays
40 78 56 Isolators, Intrinsically-Safe Barriers, and Surge Suppressors
40 78 59 Power Supplies
40 78 63 Alarm Dialers
40 79 00 Miscellaneous Instruments, Calibration Equipment, Instrument Valves, and Fittings
40 79 13 Nuclear Mass-Measuring Scales
40 79 23 Instrument Calibration Equipment
40 79 26 Instrument Programming Equipment
40 79 33 Current-to-Pressure Converters
40 79 36 Voltage-to-Pressure Converters
40 79 39 Signal Conditioners and Converters
40 79 43 Deadweight Testers
40 79 46 Flame Scanners
40 79 63 Instrument Tubing
40 79 66 Instrument Valve Manifolds, Valves, and Fittings
40 80 00 Commissioning of Process Systems
40 90 00 Primary Control Devices
40 91 00 Primary Control Valves
40 91 13 Electrically-Operated Primary Control Valves
40 91 16 Hydraulically-Operated Primary Control Valves
40 91 19 Pneumatically-Operated Primary Control Valves
40 91 23 Solenoid Primary Control Valves
40 91 26 Specialty Primary Control Valves
40 92 00 Self-Contained Flow Controllers
40 93 00 Linear Actuators and Positioners
40 94 00 Self-Contained Pressure Regulators
40 95 00 Rotary Actuators
40 96 00 Saturable Core Reactors
40 97 00 Variable Frequency Drives
41 00 00 Material Processing and Handling Equipment
41 01 00 Operation and Maintenance of Material Processing and Handling Equipment
41 01 52 Operation and Maintenance of Bulk Materials Storage
41 01 52.13 Storage Bin and Hopper Cleaning
41 01 52.16 Silo Cleaning
41 05 00 Common Work Results for Material Processing and Handling Equipment
41 05 05 Selective Demolition for Material Processing and Handling Equipment
41 06 00 Schedules for Material Processing and Handling Equipment
41 06 10 Schedules for Bulk Material Processing Equipment
41 06 20 Schedules for Piece Material Handling Equipment
41 06 30 Schedules for Manufacturing Equipment
41 06 40 Schedules for Container Processing and Packaging
41 06 50 Schedules for Material Storage
41 06 60 Schedules for Mobile Plant Equipment
41 08 00 Commissioning of Material Processing and Handling Equipment
41 08 10 Commissioning of Bulk Material Processing Equipment
41 08 20 Commissioning of Piece Material Handling Equipment
41 08 30 Commissioning of Manufacturing Equipment
41 08 40 Commissioning of Container Processing and Packaging
41 08 50 Commissioning of Material Storage
41 08 60 Commissioning of Mobile Plant Equipment
41 10 00 Bulk Material Processing Equipment
41 11 00 Bulk Material Sizing Equipment
41 11 13 Bulk Material Agglomerators
41 11 16 Bulk Material Air Mill Classifiers
41 11 19 Bulk Material Centrifuges
41 11 23 Bulk Material Crushers
41 11 26 Bulk Material Cyclones
41 11 29 Bulk Material Fluid Bed Separators
41 11 33 Bulk Material Grinders
41 11 36 Bulk Material Homogenizers
41 11 39 Bulk Material Lump Breakers
41 11 43 Bulk Material Mills
41 11 46 Bulk Material Pulverizers
41 11 49 Bulk Material Screens
41 11 53 Bulk Material Shredders
41 11 56 Bulk Material Sieves
41 12 00 Bulk Material Conveying Equipment
41 12 13 Bulk Material Conveyors
41 12 13.13 Airslide Bulk Material Conveyors
41 12 13.16 Auger Bulk Material Conveyors
41 12 13.19 Belt Bulk Material Conveyors
41 12 13.23 Container Bulk Material Conveyors
41 12 13.26 Drag Chain Bulk Material Conveyors
41 12 13.29 Hopper Bulk Material Conveyors
41 12 13.33 Reciprocating Bulk Material Conveyors
41 12 13.36 Screw Bulk Material Conveyors
41 12 13.39 Stacking and Reclaim Bulk Material Conveyors
41 12 13.43 Trough Bulk Material Conveyors
41 12 13.46 Tube Bulk Material Conveyors
41 12 13.49 Vibratory Bulk Material Conveyors
41 12 13.53 Weigh-Belt Bulk Material Conveyors
41 12 16 Bucket Elevators
41 12 19 Pneumatic Conveyors
41 12 19.13 Dense Phase Pneumatic Conveyors
41 12 19.16 Dilute Phase Pneumatic Conveyors
41 13 00 Bulk Material Feeders
41 13 13 Bin Activators/Live Bin Bottoms
41 13 23 Feeders
41 13 23.13 Airlock Bulk Material Feeders
41 13 23.16 Apron Bulk Material Feeders
41 13 23.19 Rotary-Valve Bulk Material Feeders
41 13 23.23 Screw Bulk Material Feeders
41 13 23.26 Vibratory Bulk Material Feeders
41 13 23.29 Volumetric Bulk Material Feeders
41 13 23.33 Weigh Bulk Material Feeders
41 14 00 Batching Equipment
41 14 13 Bag-Handling Batching Equipment
41 14 16 Batch Cars/Transports
41 14 19 Batch Hoppers
41 14 23 Bulk Bag-Handling Batching Equipment
41 14 26 Blenders
41 14 29 Drum-Handling Batching Equipment
41 14 33 Mixers
41 14 36 Weigh Scales
41 20 00 Piece Material Handling Equipment
41 21 00 Conveyors
41 21 13 Automatic Guided Vehicle Systems
41 21 23 Piece Material Conveyors
41 21 23.13 Belt Piece Material Conveyors
41 21 23.16 Container Piece Material Conveyors
41 21 23.19 Drag-Chain Piece Material Conveyors
41 21 23.23 Hopper Piece Material Conveyors
41 21 23.26 Monorail Piece Material Conveyors
41 21 23.29 Power and Free Piece Material Conveyors
41 21 23.33 Reciprocating Piece Material Conveyors
41 21 23.36 Roller Piece Material Conveyors
41 21 23.39 Vibratory Piece Material Conveyors
41 21 23.43 Walking-Beam Piece Material Conveyors
41 21 23.46 Weigh-Belt Piece Material Conveyors
41 21 23.53 Postal Conveyors
41 21 26 Piece Material Diverter Gates
41 21 29 Piece Material Gravity Slides
41 21 33 Piece Material Transfer Cars
41 21 36 Piece Material Turntables
41 21 39 Piece Material Feeders
41 21 39.13 Piece Material Vibratory Feeders
41 22 00 Cranes and Hoists
41 22 13 Cranes
41 22 13.13 Bridge Cranes
41 22 13.16 Gantry Cranes
41 22 13.19 Jib Cranes
41 22 13.23 Mobile Cranes
41 22 13.26 Tower Cranes
41 22 13.29 Specialty Cranes
41 22 23 Hoists
41 22 23.13 Fixed Hoists
41 22 23.16 Portable Hoists
41 22 23.19 Monorail Hoists
41 22 23.23 Specialty Hoists
41 22 33 Derricks
41 23 00 Lifting Devices
41 23 13 Clamps
41 23 16 Grabs
41 23 19 Hooks
41 23 23 Lifts
41 23 26 Slings
41 23 29 Spreader Bars/Beams
41 23 33 Tongs
41 24 00 Specialty Material Handling Equipment
41 24 13 Aeration Devices
41 24 16 Bin Vibrators
41 24 19 Dehydrators
41 24 23 Hydrators
41 24 26 Hydraulic Power Systems
41 24 29 Lubrication Systems
41 24 33 Magnetic Separators
41 24 36 Metal Detectors
41 24 39 Railcar Movers
41 24 43 Turnheads/Distributors
41 24 46 Sorting Machines
41 24 46.13 Postal Sorting Machines
41 30 00 Manufacturing Equipment
41 31 00 Manufacturing Lines and Equipment
41 31 13 Manufacturing Lines
41 31 13.13 Assembly Lines
41 31 13.16 Casting Lines
41 31 13.19 Coating Lines
41 31 13.23 Converting Lines
41 31 13.26 Disassembly Lines
41 31 13.29 Extrusion Lines
41 31 13.33 Machining Lines
41 31 13.36 Molding Lines
41 31 13.39 Finishing/Painting Lines
41 31 13.43 Painting Lines
41 31 13.46 Pickling Lines
41 31 13.49 Plating Lines
41 31 13.53 Polishing Lines
41 31 13.56 Press Lines
41 31 13.59 Rolling/Calendaring Lines
41 31 13.63 Web Processing Lines
41 31 16 Pick and Place Systems
41 31 19 Manufacturing-Line Robots
41 31 23 Specialty Assembly Machines
41 32 00 Forming Equipment
41 32 13 Bending Equipment
41 32 16 Blow-Molding Equipment
41 32 19 Brake-Forming Equipment
41 32 23 Cold-Forming Equipment
41 32 26 Die-Casting Equipment
41 32 29 Drawing Equipment
41 32 33 Electroforming Equipment
41 32 36 Forging Equipment
41 32 39 Extruding Equipment
41 32 43 Metal-Spinning Equipment
41 32 46 Piercing Equipment
41 32 49 Powder Metal-Forming Equipment
41 32 53 Pressing Equipment
41 32 56 Roll-Forming Equipment
41 32 59 Shearing Equipment
41 32 63 Spinning Equipment
41 32 66 Stretching/Leveling Equipment
41 32 69 Swaging Equipment
41 33 00 Machining Equipment
41 33 13 Automatic Screw Machining Equipment
41 33 16 Boring Equipment
41 33 19 Broaching Equipment
41 33 23 Drilling Equipment
41 33 26 Electro-Discharge Machining Equipment
41 33 29 Grinding Equipment
41 33 33 Hobbing Equipment
41 33 36 Lapping Equipment
41 33 39 Lathe Equipment
41 33 43 Leveling Equipment
41 33 46 Machining Center Equipment
41 33 53 Milling Equipment
41 33 53.13 Horizontal Milling Equipment
41 33 53.16 Vertical Milling Equipment
41 33 60 Multi-Axis Machine Equipment
41 33 63 Planing Equipment
41 33 66 Reaming Equipment
41 33 69 Routing Equipment
41 33 73 Sawing Equipment
41 33 76 Shaping Equipment
41 33 79 Threading Equipment
41 34 00 Finishing Equipment
41 34 13 Anodizing Equipment
41 34 16 Barrel Tumbling Equipment
41 34 23 Coating Equipment
41 34 23.13 Diffusion Coating Equipment
41 34 23.16 Dipping Coating Equipment
41 34 23.19 Film Coating Equipment
41 34 23.23 Phosphatizing Coating Equipment
41 34 23.26 Plasma Coating Equipment
41 34 23.29 Hardface Welding Coating Equipment
41 34 23.33 Spray Painting Booth
41 34 26 Deburring Equipment
41 34 36 Electroplating Equipment
41 34 46 Grinding Equipment
41 34 49 Honing Equipment
41 34 53 Lapping Equipment
41 34 56 Shot Peening Equipment
41 34 59 Superfinishing/Polishing Equipment
41 35 00 Dies and Molds
41 35 13 Dies
41 35 13.13 Drawing Dies
41 35 13.16 Extrusion Dies
41 35 13.19 Press Dies
41 35 13.23 Rotary Dies
41 35 13.26 Rule Dies
41 35 33 Molds
41 36 00 Assembly and Testing Equipment
41 36 13 Applicators
41 36 13.13 Adhesive Applicators
41 36 13.16 Lubricant Applicators
41 36 13.19 Sealer Applicators
41 36 16 Fixtures and Jigs
41 36 19 Joining Equipment
41 36 19.13 Adhesive Joining Equipment
41 36 19.16 Arc-Welding Equipment
41 36 19.19 Brazing Equipment
41 36 19.23 Resistance-Welding Equipment
41 36 19.26 Riveting Equipment
41 36 19.29 Sintering Equipment
41 36 19.33 Soldering Equipment
41 36 23 Cutting Equipment
41 36 23.13 Cutting Torches
41 36 23.16 High-Pressure Water Cutting Equipment
41 36 23.19 Laser Cutting Equipment
41 36 23.23 Plasma Cutting Equipment
41 36 26 Process Tools
41 36 26.13 Air Process Tools
41 36 26.16 Electric Process Tools
41 36 26.19 Hydraulic Process Tools
41 36 26.23 Manual Process Tools
41 36 29 Manufacturing Measurement and Testing Equipment
41 36 29.13 Gages, Rules, and Blocks
41 36 29.16 Penetrant Measurement and Testing Equipment
41 36 29.19 Laser Measurement and Testing Equipment
41 36 29.23 Magnaflux Measurement and Testing Equipment
41 36 29.26 Optical Comparators
41 36 29.29 Profilometers
41 36 29.33 Radiograph Measurement and Testing Equipment
41 36 29.36 Surface Tables
41 36 29.39 Ultrasonic Measurement and Testing Equipment
41 36 29.43 Test Weigh Scales
41 40 00 Container Processing and Packaging
41 41 00 Container Filling and Sealing
41 41 13 Bulk Container Fillers/Packers
41 41 16 Container Cappers
41 41 19 Container Fillers
41 41 19.13 Bag Fillers
41 41 19.16 Box Fillers
41 41 19.19 Bottle Fillers
41 41 23 Container Sealers
41 42 00 Container Packing Equipment
41 42 13 Box Packing Equipment
41 42 13.13 Box Makers
41 42 13.16 Box Packers
41 42 16 Bulk Material Loaders
41 42 16.13 Container Bulk Material Loaders
41 42 16.23 Truck Bulk Material Loaders
41 42 16.26 Railcar Bulk Material Loaders
41 42 16.29 Ship Bulk Material Loaders
41 42 16.33 Barge Bulk Material Loaders
41 42 19 Carton Packers
41 42 23 Carton Sealers
41 42 26 Carton Shrink Wrappers
41 42 29 Carton Stackers
41 43 00 Shipping Packaging
41 43 13 Banding/Strapping Equipment
41 43 16 Barcode Equipment
41 43 16.13 Barcode Readers
41 43 16.16 Barcode Printers
41 43 19 Labeling Equipment
41 43 23 Pallet Stacking/Wrapping Equipment
41 50 00 Material Storage
41 51 00 Automatic Material Storage
41 51 13 Automatic Storage/Automatic Retrieval Systems
41 52 00 Bulk Material Storage
41 52 16.13 Concrete Flat-Bottom Silos
41 52 16.16 Concrete Masonry Flat-Bottom Silos
41 52 16.23 Concrete Cone-Bottom Silos
41 52 16.26 Concrete Masonry Cone-Bottom Silos
41 52 16.29 Steel Cone-Bottom Silos
41 52 19 Bulk Materials Storage Tanks
41 52 19.13 Stationary Bulk Materials Storage Tanks
41 52 19.33 Mobile Bulk Materials Storage Tanks
41 52 41 Pneumatic, Block-Distributed Materials Fluidizing System for Flat-Bottom Bins and Silos
41 52 43 Aerated Trough Materials Fluidizing System for Flat-Bottom Bins and Silos
41 52 46 Pad-Mounted Aerated Disc Materials Fluidizing System for Cone-Bottom Bins and Silos
41 53 00 Storage Equipment and Systems
41 53 13 Storage Cabinets
41 53 16 Container Storage Systems
41 53 19 Flat Files
41 53 23 Storage Racks
41 53 23.13 Mobile Storage Racks
41 53 26 Mezzanine Storage Systems
41 60 00 Mobile Plant Equipment
41 61 00 Mobile Earth Moving Equipment
41 61 13 Backhoes
41 61 16 Bulldozers
41 61 19 Compactors
41 61 23 Excavators
41 61 26 Graders
41 61 29 Payloaders
41 61 33 Trenchers
41 62 00 Trucks
41 62 13 Cement Mixer Trucks
41 62 16 Dump Trucks
41 62 19 Flatbed Trucks
41 62 23 Forklift Trucks
41 62 26 Pickup Trucks
41 62 29 Tank Trucks
41 63 00 General Vehicles
41 63 13 Bicycles
41 63 16 Carts
41 63 19 Maintenance Vehicles
41 63 23 Utility Vehicles
41 63 26 Vans
41 63 29 Wagons
41 64 00 Rail Vehicles
41 64 13 Locomotives
41 64 13.13 Diesel Locomotives
41 64 13.23 Electric Locomotives
41 64 16 Mobile Railcar Movers
41 65 00 Mobile Support Equipment
41 65 13 Mobile Air Compressors
41 65 16 Mobile Generators
41 65 19 Mobile Welders
41 66 00 Miscellaneous Mobile Equipment
41 66 13 Mobile Boring and Drilling Rigs
41 66 16 Mobile Lifts and Cherrypickers
41 66 19 Mobile Paving Equipment
41 66 23 Mobile Sweepers/Vacuums
41 67 00 Plant Maintenance Equipment
41 67 13 Plant Lube Oil System
41 67 16 Plant Fall Protection Equipment
41 67 19 Plant Safety Equipment
41 67 23 Plant Maintenance Tools
41 67 26 Plant Maintenance Washing Equipment
42 00 00 Process Heating, Cooling, and Drying Equipment
42 01 00 Operation and Maintenance of Process Heating, Cooling, and Drying Equipment
42 01 10 Operation and Maintenance of Process Heating Equipment
42 01 20 Operation and Maintenance of Process Cooling Equipment
42 01 30 Operation and Maintenance of Process Drying Equipment
42 05 00 Common Work Results for Process Heating, Cooling, and Drying Equipment
42 05 05 Selective Demolition for Process Heating, Cooling, and Drying Equipment
42 06 00 Schedules for Process Heating, Cooling, and Drying Equipment
42 06 10 Schedules for Process Heating Equipment
42 06 20 Schedules for Process Cooling Equipment
42 06 30 Schedules for Process Drying Equipment
42 08 00 Commissioning of Process Heating, Cooling, and Drying Equipment
42 08 10 Commissioning of Heating Equipment
42 08 20 Commissioning of Cooling Equipment
42 08 30 Commissioning of Drying Equipment
42 10 00 Process Heating Equipment
42 11 00 Process Boilers
42 11 13 Low-Pressure Process Boilers
42 11 16 Intermediate-Pressure Process Boilers
42 11 19 High-Pressure Process Boilers
42 11 23 Specialty Process Boilers
42 12 00 Process Heaters
42 12 13 Electric Process Heaters
42 12 16 Fuel-Fired Process Heaters
42 12 19 Thermoelectric Process Heaters
42 12 23 Solar Process Heaters
42 12 26 Specialty Process Heaters
42 13 00 Industrial Heat Exchangers and Recuperators
42 13 13 Industrial Gas-to-Gas Heat Exchangers
42 13 16 Industrial Liquid-to-Gas/Gas-to-Liquid Heat Exchangers
42 13 19 Industrial Liquid-to-Liquid Heat Exchangers
42 13 23 Industrial Gas Radiation Heat Exchangers
42 13 26 Industrial Solar Radiation Heat Exchangers
42 14 00 Industrial Furnaces
42 14 13 Annealing Furnaces
42 14 16 Atmosphere Generators
42 14 19 Industrial Baking Furnaces
42 14 23 Industrial Brazing Furnaces
42 14 26 Industrial Calcining Furnaces
42 14 29 Industrial Heat-Treating Furnaces
42 14 33 Industrial Melting Furnaces
42 14 33.13 Ceramics and Glass Melting Furnaces
42 14 33.16 Ferrous Melting Furnaces
42 14 33.19 Non-Ferrous Melting Furnaces
42 14 36 Primary Refining Furnaces
42 14 43 Reactor Furnaces
42 14 46 Industrial Reheat Furnaces
42 14 53 Industrial Sintering Furnaces
42 14 56 Industrial Vacuum Furnaces
42 15 00 Industrial Ovens
42 15 13 Industrial Drying Ovens
42 15 16 Industrial Curing Ovens
42 15 19 Industrial Specialty Ovens
42 20 00 Process Cooling Equipment
42 21 00 Process Cooling Towers
42 21 13 Open-Circuit Process Cooling Towers
42 21 16 Closed-Circuit Process Cooling Towers
42 22 00 Process Chillers and Coolers
42 22 13 Centrifugal Process Chillers and Coolers
42 22 16 Reciprocating Process Chillers and Coolers
42 22 19 Refrigerant Process Chillers and Coolers
42 22 23 Rotary Process Chillers and Coolers
42 22 26 Thermoelectric Process Chillers and Coolers
42 23 00 Process Condensers and Evaporators
42 23 13 Process Condensers
42 23 16 Process Cooling Evaporators
42 23 19 Process Humidifiers
42 30 00 Process Drying Equipment
42 31 00 Gas Dryers and Dehumidifiers
42 31 13 Drying Evaporators
42 31 16 Desiccant Equipment
42 31 19 Regenerative Dryers
42 31 23 Refrigerant Dryers
42 32 00 Material Dryers
42 32 13 Centrifugal Material Dryers
42 32 16 Conveyor Material Dryers
42 32 19 Flash Material Dryers
42 32 23 Fluid-Bed Material Dryers
42 32 26 Material Roasters
42 32 29 Rotary-Kiln Material Dryers
42 32 33 Spray Material Dryers
42 32 36 Tower Material Dryers
42 32 39 Vacuum Material Dryers
42 32 43 Specialty Material Dryers
43 00 00 Process Gas and Liquid Handling, Purification, and Storage Equipment
43 01 00 Operation and Maintenance of Process Gas and Liquid Handling, Purification, and Storage Equipment
43 01 10 Operation and Maintenance of Gas Handling Equipment
43 01 10.13 Gas Blowers Maintenance and Rehabilitation
43 01 10.16 Gas Compressors Maintenance and Rehabilitation
43 01 20 Operation and Maintenance of Liquid Handling Equipment
43 01 20.13 Liquid Pumps Maintenance and Rehabilitation
43 01 20.16 Liquid Process Equipment Maintenance and Rehabilitation
43 01 30 Operation and Maintenance of Gas and Liquid Hi-Purification Equipment
43 01 40 Operation and Maintenance of Gas and Liquid Storage
43 01 40.13 Non-pressurized Tanks Cleaning, Maintenance, and Rehabilitation
43 01 40.16 Pressurized Tanks Cleaning, Maintenance, and Rehabilitation
43 05 00 Common Work Results for Process Gas and Liquid Handling, Purification, and Storage Equipment
43 05 05 Selective Demolition for Process Gas and Liquid Handling, Purification, and Storage Equipment.
43 05 10 Common Work Results for Gas Handling Equipment
43 05 20 Common Work Results for Liquid Handling Equipment
43 05 30 Common Work Results for Gas and Liquid Hi-Purification Equipment
43 05 40 Common Work Results for Gas and Liquid Storage
43 06 00 Schedules for Process Gas and Liquid Handling, Purification, and Storage Equipment
43 06 10 Schedules for Gas Handling Equipment
43 06 20 Schedules for Liquid Handling Equipment
43 06 30 Schedules for Gas and Liquid Hi-Purification Equipment
43 06 40 Schedules for Gas and Liquid Storage
43 08 00 Commissioning of Process Gas and Liquid Handling, Purification, and Storage Equipment
43 08 10 Commissioning of Gas Handling Equipment
43 08 20 Commissioning of Liquid Handling Equipment
43 08 30 Commissioning of Gas and Liquid Purification Equipment
43 08 40 Commissioning of Gas and Liquid Storage
43 10 00 Gas Handling Equipment
43 11 00 Gas Fans, Blowers, Pumps and Boosters
43 11 11 Direct Drive Single Stage Centrifugal Blowers
43 11 12 Integrally Geared Single Stage Centrifugal Blowers
43 11 13 Separately Geared Single Stage Centrifugal Blowers
43 11 14 Direct Drive Integral Shaft Single Stage Centrifugal Blowers
43 11 17 Horizontally Split Multistage Centrifugal Blowers
43 11 18 Vertically Split Multistage Centrifugal Blowers
43 11 19 Centrifugal Fans
43 11 23 Axial Blowers
43 11 26 Axial Fans
43 11 31 Rotary Helical Screw Blowers
43 11 33 Rotary Lobe Blowers
43 11 34 Regenerative Rotary Blowers
43 11 36 Rotary Vane Blowers
43 11 41 Gas-handling Venturi Jet Pumps
43 11 43 Gas-handling Vacuum Pumps
43 11 46 Gas Boosters
43 12 00 Gas Compressors
43 12 11 Centrifugal Compressors
43 12 13 Diagonal or Mixed-flow Compressors
43 12 16 Axial-flow Compressors
43 12 33 Single-acting Reciprocating Compressors
43 12 34 Double-acting Reciprocating Compressors
43 12 37 Diaphragm Reciprocating Compressors
43 12 51 Rotary Screw Compressors
43 12 53 Rotary Vane Compressors
43 12 56 Rotary Liquid-ring Compressors
43 12 57 Rotary Scroll Compressors
43 13 00 Gas Process Equipment
43 13 13 Gas Blenders
43 13 19 Gas Mixers
43 13 23 Gas Pressure Regulators
43 13 31 Gas Separation Equipment
43 13 33 Gas Dehydration Equipment
43 13 36 Combined Gas Separation and Dehydration Equipment
43 13 39 Gas Recovery and Condensing Equipment
43 13 43 Waste Gas Burner System
43 13 46 Gas Control and Safety Equipment
43 15 00 Process Air and Gas Filters
43 15 13 Blower Intake and Turbine Air Filters
43 15 13.13 Static Prefilters
43 15 13.16 Static Final Filters
43 15 13.19 Static HEPA Filters
43 15 13.23 Pulse Filters
43 15 33 Grease Filters
43 15 43 Mist Eliminators
43 15 63 High-temperature Air Filters
43 15 73 Multiple-application Air Filters
43 15 73.11 Air Filter Media
43 15 73.12 Permanent Washable Filters
43 15 73.13 Poly-ring Air Filters
43 15 73.15 Rigid Cell Filters
43 15 73.17 Automatic Roll-type Air Filters
43 15 76 Chemical Media for Air and Gas Filters
43 20 00 Liquid Handling Equipment
43 22 00 Liquid Process Equipment
43 22 13 Liquid Aeration Devices
43 22 16 Liquid Agitators
43 22 19 Liquid Blenders
43 22 23 Liquid Centrifuges
43 22 26 Liquid Deaerators
43 22 29 Drum Handling Liquid Process Equipment
43 22 33 Liquid Emulsifiers
43 22 36 Liquid Evaporators
43 22 39 Liquid Feeders
43 22 56 Liquid Process Mixers
43 22 59 Liquid Process Pressure Regulators
43 22 63 Liquid Separation Towers
43 22 66 Liquid Weigh Systems
43 22 69 Liquid Grease Receiving and Dewatering Systems
43 22 73 Liquid Fillers
43 22 76 Liquid Screeners
43 22 79 Liquid Clarifiers
43 22 83 Liquid Classifiers
43 22 86 Liquid Homogenizers
43 22 89 Liquid Presses
43 22 96 Liquid Versators
43 22 99 Liquid Votators
43 23 00 Dry Location Liquid Pumps
43 23 13 Overhung Horizontal Centrifugal Pumps
43 23 13.13 Overhung Flexibly-coupled Horizontal Axial Flow Centrifugal Pumps
43 23 13.14 Overhung Flexibly-coupled Horizontal Frame-mounted Centrifugal Pumps
43 23 13.17 Overhung Flexibly-coupled Horizontal Foot-mounted Centrifugal Pumps
43 23 13.19 Overhung Flexibly-coupled Horizontal Foot-mounted Self-priming Centrifugal Pumps
43 23 13.21 Overhung Flexibly-coupled Horizontal Centerline-mounted Centrifugal Pumps
43 23 13.23 Overhung Flexibly-coupled, Magnetic Drive, Sealless Horizontal Centrifugal Pumps
43 23 13.24 Overhung Close-coupled High-speed Integral Gear Centrifugal Pumps
43 23 13.27 Overhung Close-coupled Horizontal Centrifugal Pumps
43 23 13.29 Overhung Close-coupled Sealless with Canned Motor Horizontal Centrifugal Pumps
43 23 21 Between-Bearings Impeller Centrifugal Pumps
43 23 21.13 Between-bearings Impeller, One- and Two-stage Axially-split Centrifugal Pumps
43 23 21.14 Between-bearings Impeller, One- and Two-stage, Radially-split Centrifugal Pumps
43 23 21.17 Between-bearings Impeller, Multiple-stage, Axially-split Centrifugal Pumps
43 23 21.19 Between-bearings Impeller, Multiple-stage, Radially-split Centrifugal Pumps
43 23 21.21 Between-bearings Impeller, Multiple-stage, Radially-split, Single Casing Centrifugal Pumps
43 23 21.23 Between-bearings Impeller, Multiple-stage, Radially-split, Double Casing Centrifugal Pumps
43 23 31 Vertical Centrifugal Pumps
43 23 31.13 Overhung Flexibly-coupled Vertical Centrifugal Pumps
43 23 31.14 Overhung Flexibly-coupled Vertical Inline Centrifugal Pumps
43 23 31.17 Overhung Flexibly-coupled Vertical End-suction Centrifugal Pumps
43 23 31.19 Overhung Flexibly-coupled, Magnetic Drive, Sealless Vertical Centrifugal Pumps
43 23 31.21 Overhung Close-coupled Vertical Inline Centrifugal Pumps
43 23 31.23 Overhung Close-coupled Vertical End Suction Centrifugal Pumps
43 23 31.24 Overhung Close-coupled Sealless with Canned Motor Vertical Centrifugal Pumps
43 23 31.27 Overhung Rigidly-coupled Vertical Inline Centrifugal Pumps
43 23 31.29 Overhung Close-coupled Vertical Centrifugal Pumps
43 23 51 Vane Pumps
43 23 53 Piston Pumps
43 23 53.13 Piston Axial Rotary Pumps
43 23 53.23 Piston Radial Rotary Pumps
43 23 53.33 Circumferential Single-Piston Rotary Pumps
43 23 53.36 Circumferential Multiple-Piston Rotary Pumps
43 23 54 Flexible Member Pumps
43 23 54.13 Flexible Tube Rotary Pumps
43 23 54.23 Flexible Vane Rotary Pumps
43 23 54.33 Flexible Liner Rotary Pumps
43 23 56 Gear Pumps
43 23 56.13 External Gear Rotary Pumps
43 23 56.23 Internal Gear Rotary Pumps
43 23 57 Progressing Cavity Pumps
43 23 58 Lobe Pumps
43 23 58.13 Single-Lobe Rotary Pumps
43 23 58.23 Multiple-Lobe Rotary Pumps
43 23 59 Screw Pumps
43 23 59.13 Single-Screw Rotary Pumps
43 23 59.23 Multiple-Screw Rotary Pumps
43 23 71 Air-Operated Diaphragm Reciprocating Pumps
43 23 71.13 Air-Operated Diaphragm Simplex Single-Acting Reciprocating Pumps
43 23 71.23 Air-Operated Diaphragm Simplex Double-Acting Reciprocating Pumps
43 23 71.33 Air-Operated Diaphragm Duplex Single-acting Reciprocating Pumps
43 23 71.43 Air-Operated Diaphragm Duplex Double-acting Reciprocating Pumps
43 23 72 Air-Operated Bellows Reciprocating Pumps
43 23 72.13 Air-Operated Bellows Simplex Single-Acting Reciprocating Pumps
43 23 72.23 Air-Operated Bellows Simplex Double-Acting Reciprocating Pumps
43 23 72.33 Air-Operated Bellows Duplex Single-Acting Reciprocating Pumps
43 23 72.43 Air-Operated Bellows Duplex Double-Acting Reciprocating Pumps
43 23 73 Air-Operated Piston Reciprocating Pumps
43 23 73.13 Air-Operated Piston Simplex Single-Acting Reciprocating Pumps
43 23 73.23 Air-Operated Piston Simplex Double-Acting Reciprocating Pumps
43 23 73.33 Air-Operated Piston Duplex Single-Acting Reciprocating Pumps
43 23 73.43 Air-Operated Piston Duplex Double-Acting Reciprocating Pumps
43 23 74 Steam Horizontal Reciprocating Pumps
43 23 74.13 Steam Horizontal Double-Acting Piston Simplex Reciprocating Pumps
43 23 74.23 Steam Horizontal Double-Acting Piston Duplex Reciprocating Pumps
43 23 74.33 Steam Horizontal Double-Acting Plunger Simplex Reciprocating Pumps
43 23 74.43 Steam Horizontal Double-Acting Plunger Duplex Reciprocating Pumps
43 23 75 Steam Vertical Reciprocating Pumps
43 23 75.13 Steam Vertical Double-Acting Piston Simplex Reciprocating Pumps
43 23 75.23 Steam Vertical Double-Acting Piston Duplex Reciprocating Pumps
43 23 75.33 Steam Vertical Double-Acting Plunger Simplex Reciprocating Pumps
43 23 75.43 Steam Vertical Double-acting Plunger Duplex Reciprocating Pumps
43 23 76 Power Horizontal Reciprocating Pumps
43 23 76.11 Power Horizontal Single-Acting Piston Simplex Reciprocating Pumps
43 23 76.12 Power Horizontal Single-Acting Piston Duplex Reciprocating Pumps
43 23 76.13 Power Horizontal Single-Acting Piston Multiplex Reciprocating Pumps
43 23 76.21 Power Horizontal Single-Acting Plunger Simplex Reciprocating Pumps
43 23 76.22 Power Horizontal Single-Acting Plunger Duplex Reciprocating Pumps
43 23 76.23 Power Horizontal Single-Acting Plunger Multiplex Reciprocating Pumps
43 23 76.31 Power Horizontal Double-Acting Piston Simplex Reciprocating Pumps
43 23 76.32 Power Horizontal Double-Acting Piston Duplex Reciprocating Pumps
43 23 76.33 Power Horizontal Double-Acting Piston Multiplex Reciprocating Pumps
43 23 76.41 Power Horizontal Double-Acting Plunger Simplex Reciprocating Pumps
43 23 76.42 Power Horizontal Double-Acting Plunger Duplex Reciprocating Pumps
43 23 76.43 Power Horizontal Double-Acting Plunger Multiplex Reciprocating Pumps
43 23 77 Power Vertical Reciprocating Pumps
43 23 77.11 Power Vertical Single-Acting Piston Simplex Reciprocating Pumps
43 23 77.12 Power Vertical Single-Acting Piston Duplex Reciprocating Pumps
43 23 77.13 Power Vertical Single-Acting Piston Multiplex Reciprocating Pumps
43 23 77.21 Power Vertical Single-Acting Plunger Simplex Reciprocating Pumps
43 23 77.22 Power Vertical Single-Acting Plunger Duplex Reciprocating Pumps
43 23 77.23 Power Vertical Single-Acting Plunger Multiplex Reciprocating Pumps
43 23 77.31 Power Vertical Double-Acting Piston Simplex Reciprocating Pumps
43 23 77.32 Power Vertical Double-Acting Piston Duplex Reciprocating Pumps
43 23 77.33 Power Vertical Double-Acting Piston Multiplex Reciprocating Pumps
43 23 77.41 Power Vertical Double-Acting Plunger Simplex Reciprocating Pumps
43 23 77.42 Power Vertical Double-Acting Plunger Duplex Reciprocating Pumps
43 23 77.43 Power Vertical Double-Acting Plunger Multiplex Reciprocating Pumps
43 23 78 Controlled Volume Horizontal Reciprocating Pumps
43 23 78.11 Controlled Volume Horizontal Packed Plunger Simplex Reciprocating Pumps
43 23 78.12 Controlled Volume Horizontal Packed Plunger Duplex Reciprocating Pumps
43 23 78.13 Controlled Volume Horizontal Packed Plunger Multiplex Reciprocating Pumps
43 23 78.21 Controlled Volume Horizontal Packed Piston Simplex Reciprocating Pumps
43 23 78.22 Controlled Volume Horizontal Packed Piston Duplex Reciprocating Pumps
43 23 78.23 Controlled Volume Horizontal Packed Piston Multiplex Reciprocating Pumps
43 23 78.31 Controlled Volume Horizontal Mechanically-Coupled Diaphragm Simplex Reciprocating Pumps
43 23 78.32 Controlled Volume Horizontal Mechanically-Coupled Diaphragm Duplex Reciprocating Pumps
43 23 78.33 Controlled Volume Horizontal Mechanically-Coupled Diaphragm Multiplex Reciprocating Pumps
43 23 78.34 Controlled Volume Horizontal Hydraulically-Coupled Diaphragm Simplex Reciprocating Pumps
43 23 78.35 Controlled Volume Horizontal Hydraulically-Coupled Diaphragm Duplex Reciprocating Pumps
43 23 78.36 Controlled Volume Horizontal Hydraulically-Coupled Diaphragm Multiplex Reciprocating Pumps
43 23 79 Controlled Volume Vertical Reciprocating Pumps
43 23 79.11 Controlled Volume Vertical Packed Plunger Simplex Reciprocating Pumps
43 23 79.12 Controlled Volume Vertical Packed Plunger Duplex Reciprocating Pumps
43 23 79.13 Controlled Volume Vertical Packed Plunger Multiplex Reciprocating Pumps
43 23 79.21 Controlled Volume Vertical Packed Piston Simplex Reciprocating Pumps
43 23 79.22 Controlled Volume Vertical Packed Piston Duplex Reciprocating Pumps
43 23 79.23 Controlled Volume Vertical Packed Piston Multiplex Reciprocating Pumps
43 23 79.31 Controlled Volume Vertical Mechanically-Coupled Diaphragm Simplex Reciprocating Pumps
43 23 79.32 Controlled Volume Vertical Mechanically-Coupled Diaphragm Duplex Reciprocating Pumps
43 23 79.33 Controlled Volume Vertical Mechanically-Coupled Diaphragm Multiplex Reciprocating Pumps
43 23 79.34 Controlled Volume Vertical Hydraulically-Coupled Diaphragm Simplex Reciprocating Pumps
43 23 79.35 Controlled Volume Vertical Hydraulically-Coupled Diaphragm Duplex Reciprocating Pumps
43 23 79.36 Controlled Volume Vertical Hydraulically-Coupled Diaphragm Multiplex Reciprocating Pumps
43 24 00 Suspended Liquid Pumps
43 24 11 Vertically Suspended Single-Casing Submersible Centrifugal Pumps
43 24 13 Vertically Suspended Single-Casing Discharge-through-column Centrifugal Pumps
43 24 13.13 Vertically Suspended Single-Casing Discharge-through-column Diffuser Centrifugal Pumps
43 24 13.23 Vertically Suspended Single-Casing Discharge-through-column Volute Centrifugal Pumps
43 24 13.33 Vertically Suspended Single-Casing Discharge-through-column Axial Flow Centrifugal Pumps
43 24 16 Vertically Suspended Single-casing Separate Discharge (Sump) Centrifugal Pumps
43 24 16.13 Vertically Suspended Single-Casing Separate Discharge (Sump) Line Shaft Centrifugal Pumps
43 24 16.23 Vertically Suspended Single-Casing Separate Discharge (Sump) Cantilever Centrifugal Pumps
43 24 21 Vertically Suspended Double-Casing Centrifugal Pumps
43 24 21.13 Vertically Suspended Double-Casing Diffuser Centrifugal Pumps
43 24 21.23 Vertically Suspended Double-Casing Volute Centrifugal Pumps
43 24 26 Vertically Suspended Inline Casing Diffuser Centrifugal Pumps
43 24 41 Archimedes Screw Pumps
43 24 41.13 Positive-Displacement Inclined Open Archimedes Screw-type Pumps
43 24 41.23 Positive-Displacement Inclined Closed-casing Archimedes Screw-type Pumps
43 25 00 Submersible/Immersible Liquid Pumps
43 25 13 Overhung Close-Coupled Submersible Centrifugal Pumps
43 25 13.13 Overhung Close-Coupled Submersible Diffuser Centrifugal Pumps
43 25 13.23 Overhung Close-Coupled Submersible Volute Centrifugal Pumps
43 25 50 Positive Displacement Submersible Liquid Pumps
43 26 00 Specialized Liquid Pumps
43 26 13 Submersible Grinder Pumps
43 26 30 Regenerative Centrifugal Pumps
43 26 30.13 Overhung Impeller Regenerative Turbine Pumps
43 26 30.21 Overhung Impeller Single-Stage Regenerative Turbine Pumps
43 26 30.23 Overhung Impeller Two-Stage Regenerative Turbine Pumps
43 26 30.26 Between-Bearings Impeller Regenerative Turbine Pumps
43 26 30.27 Between-Bearings Impeller Single-Stage Regenerative Turbine Pumps
43 26 30.29 Between-Bearings Impeller Two-Stage Regenerative Turbine Pumps
43 26 40 Regenerative Turbine Pumps
43 26 60 Regenerative Vacuum Pumps
43 26 70 Rotating-Case Pumps
43 27 00 Process Liquid Filters
43 27 13 Cyclonic Liquid Filters
43 27 16 Centrifugal Horizontal Pressure Leaf Liquid Filters
43 27 19 Press Liquid Filters
43 27 23 Liquid Bag Filters
43 27 33 Mechanically Cleaned Liquid Filters
43 27 43 Tubular Backwashing Liquid Filters
43 27 53 Vacuum Belt Liquid Filters
43 27 63 Woven Media Liquid Filters
43 27 63.13 Disc Liquid Filters
43 27 63.23 Rotating Drum Liquid Filters
43 27 63.33 Layer Liquid Filters
43 27 63.43 Candle Liquid Filters
43 27 63.53 Vertical Leaf Liquid Filters
43 27 73 Nonwoven Media Liquid Filters
43 27 73.13 Surface Liquid Filters
43 27 73.23 Depth Liquid Filters
43 30 00 Gas and Liquid Purification Equipment
43 31 00 Gas and Liquid Purification Filtration Equipment
43 31 13 Gas and Liquid Purification Filters
43 31 13.13 Activated Carbon-Gas and Liquid Purification Filters
43 31 13.16 Gas and Liquid Purification Filter Presses
43 31 13.19 High-Purity Cartridge Gas and Liquid Purification Filters
43 31 13.23 Membrane Diaphragm Gas and Liquid Purification Filters
43 31 13.26 Multimedia Gas and Liquid Purification Filters
43 31 13.29 Pretreatment Cartridge Gas and Liquid Purification Filters
43 31 13.33 Ultrafilter Units
43 32 00 Gas and Liquid Purification Process Equipment
43 32 13 Gas and Liquid Purification Process Beds
43 32 13.13 Anion-Gas and Liquid Purification Process Beds
43 32 13.16 Cation-Gas and Liquid Purification Process Beds
43 32 23 Gas and Liquid Purification Process Clarifier Systems
43 32 26 Gas and Liquid Purification Decarbonators
43 32 29 Electronic Deionization Purification Units
43 32 33 External Regeneration Systems
43 32 36 Mixed-Bed Ion-Exchange Vessels
43 32 39 Gas and Liquid Purification Mixed Beds
43 32 39.13 Externally Regenerable Gas and Liquid Purification Mixed Beds
43 32 39.16 In-Situ Regenerable Gas and Liquid Purification Mixed Beds
43 32 53 Packed-Bed Ion-Exchange Vessels
43 32 56 Reverse-Osmosis Purification Units
43 32 59 Gas and Liquid Purification Scrubbers
43 32 63 Ultraviolet Sterilizers
43 32 66 Vacuum Degasifiers
43 32 69 Chemical Feed Systems
43 32 73 Ozonation Equipment
43 32 76 Chlorination Equipment
43 40 00 Gas and Liquid Storage
43 41 00 Non-pressurized Tanks and Vessels
43 41 11 Bolted Steel Tanks
43 41 13 Welded Steel Tanks
43 41 13.13 Glass-lined Welded Steel Tanks
43 41 13.23 Rubber-lined Welded Steel Tanks
43 41 13.33 Epoxy-lined Welded Steel Tanks
43 41 13.43 Ceramic-lined Welded Steel Tanks
43 41 23 Stainless Steel Tanks
43 41 26 Aluminum Tanks
43 41 31 Metallic Specialty Tanks
43 41 41 Polyvinyl Chloride Tanks
43 41 43 Polyethylene Tanks
43 41 45 Fiberglass Reinforced Plastic Tanks
43 41 53 Wood Stave Tanks
43 41 63 Precast Concrete Tanks
43 41 73 Ceramic Tanks
43 41 83 Non-metallic Specialty Tanks
43 42 00 Pressurized Tanks and Vessels
43 42 11 Cast Iron Pressure Tanks
43 42 13 Ductile Iron Pressure Tanks
43 42 21 Welded Steel Pressure Tanks
43 42 23 Glass-lined Steel Pressure Tanks
43 42 26 Welded Steel Gas Storage Sphere
43 42 33 Stainless Steel Pressure Tanks
43 42 36 Aluminum Pressure Tanks
43 42 41 Metallic Specialty Pressure Tanks
43 42 53 Fiberglass Reinforced Plastic Pressure Tanks
43 42 83 Non-metallic Specialty Pressure Tanks
44 00 00 Pollution and Waste Control Equipment
44 01 00 Operation and Maintenance of Pollution and Waste Control Equipment
44 01 10 Operation and Maintenance of Air Pollution Control
44 01 20 Operation and Maintenance of Noise Pollution Control
44 01 30 Operation and Maintenance of Odor Control Equipment
44 01 40 Operation and Maintenance of Water Pollution Control Equipment
44 01 50 Operation and Maintenance of Solid Waste Control and Reuse
44 01 60 Operation and Maintenance of Waste Thermal Processing Equipment
44 05 00 Common Work Results for Pollution and Waste Control Equipment
44 05 05 Selective Demolition for Pollution and Waste Control Equipment
44 06 00 Schedules for Pollution and Waste Control Equipment
44 06 10 Schedules for Air Pollution Control
44 06 20 Schedules for Noise Pollution Control
44 06 30 Schedules for Odor Control Equipment
44 06 40 Schedules for Water Pollution Control Equipment
44 06 50 Schedules for Solid Waste Control and Reuse
44 06 60 Schedules for Waste Thermal Processing Equipment
44 08 00 Commissioning of Pollution and Waste Control Equipment
44 08 10 Commissioning of Air Pollution Control
44 08 20 Commissioning of Noise Pollution Control
44 08 30 Commissioning of Odor Control Equipment
44 08 40 Commissioning Water Pollution Control Equipment
44 08 50 Commissioning Solid Waste Control and Reuse
44 08 60 Commissioning of Waste Thermal Processing Equipment
44 10 00 Air Pollution Control
44 11 00 Particulate Control Equipment
44 11 13 Fugitive Dust Control
44 11 16 Fugitive Dust Barrier Systems
44 11 19 Atmospheric Air Quality Monitoring Equipment
44 11 20 Gravitational Separators
44 11 31 Venturi Scrubbing Equipment
44 11 33 Spray Tower/Chamber Scrubbing Equipment
44 11 36 Cyclone Scrubbing Equipment
44 11 51 Pulse Jet Fabric Filtration Equipment
44 11 53 Reverse Flow Fabric Filtration Equipment
44 11 54 Shake/Deflate Fabric Filtration Equipment
44 11 56 Cartridge Filtration Equipment
44 11 59 Disposable Dry Filtration Equipment
44 11 71 Cyclone Dust Collection Equipment
44 11 73 Multicylone Dust Collection Equipment
44 11 76 Mist Elimination Equipment
44 11 93 Wet Electrostatic Precipitator Equipment
44 11 96 Dry Plate Electrostatic Precipitator Equipment
44 13 00 Gaseous Air Pollution Control Equipment
44 13 11 Spray Tower/Chamber Absorption Equipment
44 13 13 Packed Tower/Chamber Absorption Equipment
44 13 14 Tray Tower Absorption Equipment
44 13 16 Jet Bubbling Reactor Equipment
44 13 17 Venturi Absorption Equipment
44 13 20 Vacuum Extraction Systems
44 13 31 Powdered Injection Adsorption Equipment
44 13 33 Fluidized Bed Adsorption Equipment
44 13 34 Fixed Bed Adsorption Equipment
44 13 36 Rotary Bed Adsorption Equipment
44 13 39 Radial Bed Adsorption Equipment
44 13 51 Thermal Oxidation Equipment
44 13 53 Catalytic Oxidation Equipment
44 13 56 Flare Oxidation Equipment
44 13 59 Claus Sulfur Recovery Equipment
44 13 71 Thermal Reduction Equipment
44 13 73 Catalytic Reduction Equipment
44 13 76 Non-catalytic Reduction Equipment
44 13 77 Selective Non-catalytic Reduction Equipment
44 13 81 Condensation Systems
44 13 83 Contact Condensing Equipment
44 13 86 Solvent Recovery Equipment
44 13 91 Biofilter Media
44 13 93 Fixed Bed Biofilter Equipment
44 13 96 Fixed Bed Biotrickling Filter Equipment
44 13 97 Fixed Bed Bioscrubbing Equipment
44 20 00 Noise Pollution Control
44 21 00 Noise Pollution Control Equipment
44 21 13 Fixed Noise Abatement Barriers
44 21 16 Flexible Noise Abatement Barriers
44 21 19 Portable Noise Abatement Barriers
44 21 23 Noise Pollution Silencers
44 21 26 Frequency Cancellers
44 30 00 Odor Control
44 31 00 Odor Treatment Equipment
44 31 11 Wet Chemical Packed Tower Odor Control Equipment
44 31 13 Chemical Mist System Odor Control Equipment
44 31 16 Activated Carbon Adsorption Odor Control Equipment
44 31 19 Packaged Odor Control Systems
44 31 21 Odor Control Biofilters
44 31 28 Odor Control Biofilter Aeration Floor
44 31 29 Odor Control Biofilter Media
44 31 31 Odor Control Biotrickling Filter Equipment
44 31 33 Odor Control Bioscrubbing Equipment
44 31 41 Odor Control Vapor Combustion Equipment
44 31 83 Adjusting and Balancing Odor Control Systems
44 32 00 Odor Dispersing and Masking/Counteracting Equipment
44 32 13 Odor Dispersing Exhaust Stacks
44 32 13.13 Fan-equipped Odor Dispersing Exhaust Stacks
44 32 23 Odor Masking/Counteracting Equipment
44 40 00 Water Pollution Control Equipment
44 41 00 Water Pollution Containment and Cleanup Equipment
44 41 13 Spill Cleanup
44 41 21 Containment Booms
44 41 23 Marine Spill Accessories
44 41 31 Spill Decks
44 41 32 Drum Containment Units
44 41 33 Containment Pallets
44 41 34 Prefabricated Spill Containment Curbing
44 41 36 Prefabricated Spill Containment Berms
44 41 37 Prefabricated Berms for Tank Containment
44 41 41 Collapsible Storage Tanks
44 50 00 Solid Waste Control and Reuse
44 51 00 Solid Waste Collection, Transfer, and Hauling Equipment
44 51 13 Solid Waste Portable Containers
44 51 16 Solid Waste Stationary Containers
44 51 23 Solid Waste Transfer Trailers
44 53 00 Solid Waste Processing Equipment
44 53 11 Live-floor Storage Bins
44 53 13 Refuse Cranes and Accessories
44 53 16 Solid Waste Screens
44 53 21 Car Crushers
44 53 23 Shears and Guillotines
44 53 26 Shredders and Grinders
44 53 27 Perforators
44 53 31 Bag Breakers
44 53 33 Granulators
44 53 36 Crumb Rubber Systems
44 53 39 Briquetters
44 53 41 Vibratory Table Separation Equipment
44 53 43 Ferrous Metals Separation Equipment
44 53 44 Eddy Current Separators
44 53 46 Single-stream Materials Separation Equipment
44 53 49 Ballistic Separators
44 53 51 Air Classifying Equipment
44 53 52 Air Knives
44 53 53 Optical Sorting Equipment
44 53 56 Packaged Sorting Stations
44 53 59 Packaged Reclaimer Stations
44 53 61 Solid Waste Compactors
44 53 63 Solid Waste Baling Equipment
44 53 64 Bagging Equipment
44 53 66 Wrappers
44 53 73 Solid Waste Liquid Extraction Equipment
44 55 00 Composting Equipment
44 55 11 Electromechanical Composters
44 55 13 Compost Screening Equipment
44 55 16 Compost Shredding Equipment
44 55 23 Compost Pile Turning Equipment
44 55 26 Compost Mixing and Blending Equipment
44 55 33 In-vessel Composing Equipment
44 55 43 Compost Pad System
44 55 73 Compost Liquid Extraction Equipment
44 60 00 Waste Thermal Processing Equipment
44 61 00 Waste-to-Energy Plants
44 61 13 Waste Receiving, Management, and Feed Equipment
44 61 16 Mass Burn Combustion Equipment
44 61 23 Refuse-derived Fuel Feed Equipment
44 61 26 Refuse-derived Fuel Combustion Equipment
44 61 29 Modular Combustion System Equipment
44 61 31 Ash Handling Equipment
44 61 33 Post-combustion Ferrous Metals Recovery Equipment
44 61 36 Post-combustion Non-ferrous Metals Recovery Equipment
44 62 00 Fluidized Bed Combustion Equipment
44 63 00 Rotary Kiln Incinerators
44 64 00 Gasification Equipment
44 64 13 Counter-current Fixed Bed Gasification Equipment
44 64 23 Co-current Fixed Bed Gasification Equipment
44 64 33 Fluidized Bed Gasification Equipment
44 64 43 Entrained Flow Gasification Equipment
44 64 53 Plasma Arc Gasification Equipment
44 65 00 Pyrolysis Equipment
44 66 00 Hazardous Waste and Medical Waste Incinerators
44 67 00 Heat Recovery Equipment for Waste Thermal Processing
44 68 00 Synthesis Gas Cleanup and Handling Equipment
45 00 00 Industry-Specific Manufacturing Equipment
45 05 00 Common Work Results for Industry-Specific Manufacturing Equipment
45 05 05 Selective Demolition for Industry-Specific Manufacturing Equipment
45 08 00 Commissioning of Industry-Specific Manufacturing Equipment
45 11 00 Oil and Gas Extraction Equipment
45 11 01 Operation and Maintenance of Oil and Gas Extraction Equipment
45 11 06 Schedules for Oil and Gas Extraction Equipment
45 11 10 User-Defined Oil and Gas Extraction Equipment
45 12 00 User-Defined Oil and Gas Extraction Equipment
45 13 00 Mining Machinery and Equipment
45 13 01 Operation and Maintenance of Mining Machinery and Equipment
45 13 06 Schedules for Mining Machinery and Equipment
45 13 10 User-Defined Mining Machinery and Equipment
45 14 00 User-Defined Mining Machinery and Equipment
45 15 00 Food Manufacturing Equipment
45 15 01 Operation and Maintenance of Food Manufacturing Equipment
45 15 06 Schedules for Food Manufacturing Equipment
45 15 10 User-Defined Food Manufacturing Equipment
45 16 00 User-Defined Food Manufacturing Equipment
45 17 00 Beverage and Tobacco Manufacturing Equipment
45 17 01 Operation and Maintenance of Beverage and Tobacco Manufacturing Equipment
45 17 06 Schedules for Beverage and Tobacco Manufacturing Equipment
45 17 10 User-Defined Beverage and Tobacco Manufacturing Equipment
45 18 00 User-Defined Beverage and Tobacco Manufacturing Equipment
45 19 00 Textiles and Apparel Manufacturing Equipment
45 19 01 Operation and Maintenance of Textiles and Apparel Manufacturing Equipment
45 19 06 Schedules for Textiles and Apparel Manufacturing Equipment
45 19 10 User-Defined Textiles and Apparel Manufacturing Equipment
45 20 00 User-Defined Textiles and Apparel Manufacturing Equipment
45 21 00 Leather and Allied Product Manufacturing Equipment
45 21 01 Operation and Maintenance of Leather and Allied Product Manufacturing Equipment
45 21 06 Schedules for Leather and Allied Product Manufacturing Equipment
45 21 10 User-Defined Leather and Allied Product Manufacturing Equipment
45 22 00 User-Defined Leather and Allied Product Manufacturing Equipment
45 23 00 Wood Product Manufacturing Equipment
45 23 01 Operation and Maintenance of Wood Product Manufacturing Equipment
45 23 06 Schedules for Wood Product Manufacturing Equipment
45 23 10 User-Defined Wood Product Manufacturing Equipment
45 24 00 User-Defined Wood Product Manufacturing Equipment
45 25 00 Paper Manufacturing Equipment
45 25 01 Operation and Maintenance of Paper Manufacturing Equipment
45 25 06 Schedules for Paper Manufacturing Equipment
45 25 10 User-Defined Paper Manufacturing Equipment
45 26 00 User-Defined Paper Manufacturing Equipment
45 27 00 Printing and Related Manufacturing Equipment
45 27 01 Operation and Maintenance of Printing and Related Manufacturing Equipment
45 27 06 Schedules for Printing and Related Manufacturing Equipment
45 27 10 User-Defined Printing and Related Manufacturing Equipment
45 28 00 User-Defined Printing and Related Manufacturing Equipment
45 29 00 Petroleum and Coal Products Manufacturing Equipment
45 29 01 Operation and Maintenance of Petroleum and Coal Products Manufacturing Equipment
45 29 06 Schedules for Petroleum and Coal Products Manufacturing Equipment
45 29 10 User-Defined Petroleum and Coal Products Manufacturing Equipment
45 30 00 User-Defined Petroleum and Coal Products Manufacturing Equipment
45 31 00 Chemical Manufacturing Equipment
45 31 01 Operation and Maintenance of Chemical Manufacturing Equipment
45 31 06 Schedules for Chemical Manufacturing Equipment
45 31 10 User-Defined Chemical Manufacturing Equipment
45 32 00 User-Defined Chemical Manufacturing Equipment
45 33 00 Plastics and Rubber Manufacturing Equipment
45 33 01 Operation and Maintenance of Plastics and Rubber Manufacturing Equipment
45 33 06 Schedules for Plastics and Rubber Manufacturing Equipment
45 33 10 User-Defined Plastics and Rubber Manufacturing Equipment
45 34 00 User-Defined Plastics and Rubber Manufacturing Equipment
45 35 00 Nonmetallic Mineral Product Manufacturing Equipment
45 35 01 Operation and Maintenance of Nonmetallic Mineral Product Manufacturing Equipment
45 35 06 Schedules for Nonmetallic Mineral Product Manufacturing Equipment
45 35 10 User-Defined Nonmetallic Mineral Product Manufacturing Equipment
45 36 00 User-Defined Nonmetallic Mineral Product Manufacturing Equipment
45 37 00 Primary Metal Manufacturing Equipment
45 37 01 Operation and Maintenance of Primary Metal Manufacturing Equipment
45 37 06 Schedules for Primary Metal Manufacturing Equipment
45 37 10 User-Defined Primary Metal Manufacturing Equipment
45 38 00 User-Defined Primary Metal Manufacturing Equipment
45 39 00 Fabricated Metal Product Manufacturing Equipment
45 39 01 Operation and Maintenance of Fabricated Metal Product Manufacturing Equipment
45 39 06 Schedules for Fabricated Metal Product Manufacturing Equipment
45 39 10 User-Defined Fabricated Metal Product Manufacturing Equipment
45 40 00 User-Defined Fabricated Metal Product Manufacturing Equipment
45 41 00 Machinery Manufacturing Equipment
45 41 01 Operation and Maintenance of Machinery Manufacturing Equipment
45 41 06 Schedules for Machinery Manufacturing Equipment
45 41 10 User-Defined Machinery Manufacturing Equipment
45 42 00 User-Defined Machinery Manufacturing Equipment
45 43 00 Computer and Electronic Product Manufacturing Equipment
45 43 01 Operation and Maintenance of Computer and Electronic Product Manufacturing Equipment
45 43 06 Schedules for Computer and Electronic Product Manufacturing Equipment
45 43 10 User-Defined Computer and Electronic Product Manufacturing Equipment
45 44 00 User-Defined Computer and Electronic Product Manufacturing Equipment
45 45 00 Electrical Equipment, Appliance, and Component Manufacturing Equipment
45 45 01 Operation and Maintenance of Electrical Equipment, Appliance, and Component Manufacturing Equipment
45 45 06 Schedules for Electrical Equipment, Appliance, and Component Manufacturing Equipment
45 45 10 User-Defined Electrical Equipment, Appliance, and Component Manufacturing Equipment
45 46 00 User-Defined Electrical Equipment, Appliance, and Component Manufacturing Equipment
45 47 00 Transportation Manufacturing Equipment
45 47 01 Operation and Maintenance of Transportation Manufacturing Equipment
45 47 06 Schedules for Transportation Manufacturing Equipment
45 47 10 User-Defined Transportation Manufacturing Equipment
45 48 00 User-Defined Transportation Manufacturing Equipment
45 49 00 Furniture and Related Product Manufacturing Equipment
45 49 01 Operation and Maintenance of Furniture and Related Product Manufacturing Equipment
45 49 06 Schedules for Furniture and Related Product Manufacturing Equipment
45 49 10 User-Defined Furniture and Related Product Manufacturing Equipment
45 50 00 User-Defined Furniture and Related Product Manufacturing Equipment
45 52 00 User-Defined Other Manufacturing Equipment
45 53 00 Biopharmaceutical Manufacturing Equipment
46 00 00 Water and Wastewater Equipment
46 01 00 Operation and Maintenance of Water and Wastewater Equipment
46 01 07 Operation and Maintenance of Packaged Treatment Equipment
46 01 20 Operation and Maintenance of Preliminary Treatment Equipment
46 01 30 Operation and Maintenance of Chemical Feed Equipment
46 01 40 Operation and Maintenance of Clarification and Mixing Equipment
46 01 50 Operation and Maintenance of Secondary Treatment Equipment
46 01 60 Operation and Maintenance of Advanced Treatment Equipment
46 01 70 Operation and Maintenance of Residuals Handling and Treatment
46 05 00 Common Work Results for Water and Wastewater Equipment
46 05 05 Selective Demolition for Water and Wastewater Equipment
46 06 00 Schedules for Water and Wastewater Equipment
46 06 07 Schedules for Packaged Treatment Equipment
46 06 20 Schedules for Preliminary Treatment Equipment
46 06 30 Schedules for Chemical Feed Equipment
46 06 40 Schedules for Clarification and Mixing Equipment
46 06 50 Schedules for Secondary Treatment Equipment
46 06 60 Schedules for Advanced Treatment Equipment
46 06 70 Schedules for Residuals Handling and Treatment
46 07 00 Packaged Water and Wastewater Treatment Equipment
46 07 13 Packaged Water Treatment Equipment
46 07 53 Packaged Wastewater Treatment Equipment
46 08 00 Commissioning of Water and Wastewater Equipment
46 08 07 Commissioning of Packaged Treatment Equipment
46 08 20 Commissioning of Preliminary Treatment Equipment
46 08 30 Commissioning of Chemical Feed Equipment
46 08 40 Commissioning of Clarification and Mixing Equipment
46 08 50 Commissioning of Secondary Treatment Equipment
46 08 60 Commissioning of Advanced Treatment Equipment
46 08 70 Commissioning of Residuals Handling and Treatment
46 20 00 Water and Wastewater Preliminary Treatment Equipment
46 21 00 Screening Equipment
46 21 11 Climber-type Bar Screens
46 21 13 Chain-and-Rake Bar Screens
46 21 16 Flexible Rake Bar Screens
46 21 17 Catenary Bar Screens
46 21 19 Continuous Belt Screens
46 21 23 Cylindrical Bar Screens
46 21 26 Step Screens
46 21 33 Rotary Drum Screens
46 21 39 Spiral Screens
46 21 43 Band Screens
46 21 46 Disc Screens
46 21 51 Traveling Water Screens
46 21 53 Perforated Plate Screens
46 21 56 Wedge Wire Screens
46 21 57 Element Screens
46 21 71 Trash Raking Equipment
46 21 73 Screenings Washing and Compacting Equipment
46 21 76 Vacuum Screenings Conveying Equipment
46 21 79 Screenings Storage Containers
46 21 83 Septage Receiving Equipment
46 23 00 Grit Removal and Handling Equipment
46 23 13 Chain-and-Bucket Grit Removal Equipment
46 23 16 Chain-and-Flight Grit Removal Equipment
46 23 23 Vortex Grit Removal Equipment
46 23 27 Cyclone Degritters
46 23 33 Aerated Grit Removal Equipment
46 23 43 Inline Baffled Grit Removal Equipment
46 23 53 Traveling Bridge Grit Removal Equipment
46 23 63 Grit Classifying and Washing Equipment
46 23 66 Grit Storage Containers
46 24 00 Grinding and Shredding Equipment
46 24 13 Macerators
46 24 16 Comminutors
46 24 23 Inline Grinders
46 24 33 Open-channel Grinders
46 24 36 Modular Grinding-Screening-Compacting Equipment
46 25 00 Oil and Grease Separation and Removal Equipment
46 25 13 Coalescing Oil-Water Separators
46 25 16 API Oil-Water Separators
46 25 23 Grease Traps
46 25 33 Dissolved Air Flotation Grease and Oil Separation Equipment
46 25 41 Helical Scum Skimming and Removal Equipment
46 25 43 Tipping Trough Scum Skimming and Removal Equipment
46 25 46 Chain and Flight Scum Collection and Removal Equipment
46 25 47 Floating Scum Skimming and Removal Equipment
46 30 00 Water and Wastewater Chemical Feed Equipment
46 31 00 Gas Chemical Feed Equipment
46 31 11 Chlorine Gas Feed Equipment
46 31 13 Sulfur Dioxide Gas Feed Equipment
46 31 16 Ammonia Gas Feed Equipment
46 31 23 Gas Storage, Weighing, and Leak Detection Equipment
46 31 26 Emergency Gas Treatment Systems
46 31 33 Chlorine Dioxide Reactors
46 31 43 Carbon Dioxide Gas Feed Equipment
46 31 53 Ozone Generating and Feed Equipment
46 31 56 Liquid Oxygen Storage and Feed Equipment
46 31 59 Cleaning Requirements for Oxygen Service
46 31 83 Gas Chemical Feed Accessories and Safety Equipment
46 33 00 Liquid Chemical Feed Equipment
46 33 13 Sodium Hypochlorite Generating Equipment
46 33 23 Liquid Chemical Weighing Equipment
46 33 33 Polymer Blending and Feed Equipment
46 33 41 Liquid Chemical Feed System Coordination and Integration
46 33 42 Diaphragm-type Metering Pumps
46 33 44 Peristaltic Metering Pumps
46 33 46 Progressing Cavity Metering Pumps
46 33 48 Lobe Metering Pumps
46 33 53 Drum Pumps
46 33 66 Liquid Chemical Transfer Pumps
46 33 73 Liquid Chemical Diffusers
46 33 83 Liquid Chemical Feed Accessories and Safety Equipment
46 36 00 Dry Chemical Feed Equipment
46 36 11 Dry Chemical Feed System Coordination and Integration
46 36 13 Storage Silos
46 36 23 Dry Chemical Weighing Equipment
46 36 33 Volumetric Feed Equipment
46 36 36 Gravimetric Feed Equipment
46 36 43 Lime Slaking Equipment
46 36 53 Chemical Tablet Feeding Equipment
46 36 83 Dry Chemical Feed Accessories and Safety Equipment
46 40 00 Water and Wastewater Clarification and Mixing Equipment
46 41 00 Mixing Equipment
46 41 11 Rapid Mixers
46 41 13 Inline Blender-type Rapid Mixers
46 41 16 Induction-type Rapid Mixing Equipment
46 41 17 Inline Static Mixers
46 41 21 Jet Mixing Equipment
46 41 23 Submersible Mixers
46 41 26 Floating Mechanical Mixers
46 41 27 Paddle Mixers
46 41 29 Pin Mixers
46 41 31 Vertical Reel Flocculation Equipment
46 41 33 Horizontal Reel Flocculation Equipment
46 41 34 Vertical Turbine Flocculation Equipment
46 41 36 Walking-beam Flocculation Equipment
46 41 38 Horizontal Oscillating Flocculation Equipment
46 41 41 Top-entering Tank Mixers
46 41 43 Side-entry Tank Mixers
46 41 46 Portable Tank Mixers
46 43 00 Clarifier Equipment
46 43 11 Chain-and-Flight Clarifier Equipment
46 43 14 Traveling Bridge Clarifier Equipment
46 43 16 Differential Head Clarifier Equipment
46 43 18 Oscillating Scraper-type Clarifier Equipment
46 43 21 Circular Clarifier Equipment
46 43 53 Solids Contact Clarifier Equipment
46 43 61 Flocculating Clarifier, Pulsating Sludge Blanket Type
46 43 63 Dissolved Air Flotation Equipment for Water Treatment
46 43 66 Ballasted High-rate Clarifier Equipment
46 43 67 High rate Clarification/Thickening Equipment
46 43 73 Tube Settlers
46 43 76 Inclined Plate Settlers
46 46 00 Sediment Removal Equipment
46 46 13 Tipping Sediment Flushing Tanks
46 46 16 Flushing Gates
46 46 23 Water Cannon
46 46 26 Nozzle Systems
46 50 00 Water and Wastewater Secondary Treatment Equipment
46 51 00 Air and Gas Diffusion Equipment
46 51 11 Fixed Mechanical Aerators
46 51 13 Floating Mechanical Aerators
46 51 16 Submersible Aspirating Aerator Equipment
46 51 17 Jet Aeration Equipment
46 51 21 Coarse Bubble Diffusers
46 51 23 Swing-type Channel Aeration Equipment
46 51 26 Shear Box Diffusers
46 51 31 Flexible Membrane Tube Diffusers
46 51 33 Flexible Membrane Disc Diffusers
46 51 36 Ceramic Disc Fine Bubble Diffusers
46 51 43 Floating Membrane Diffusers
46 51 46 Membrane Diffusers
46 51 53 Cascading Aerators
46 51 63 Pure-oxygen Generating Equipment
46 53 00 Biological Treatment Systems
46 53 13 Rotating Biological Contactors
46 53 23 Trickling Filter Rotary Distributor Equipment
46 53 24 Trickling Filter Media
46 53 26 Bio-towers
46 53 33 Moving-bed Biological Reactors
46 53 36 Integrated Fixed-film Activated Sludge Equipment
46 53 41 Intermittent Sand Filters for Wastewater Treatment
46 53 43 Deep-bed Denitrification Filters
46 53 46 Biologically Activated Filters
46 53 49 Membrane Biological Reactors
46 53 53 Sequencing Batch Reactors
46 53 61 Oxidation Ditch Equipment
46 53 63 Vertical Loop Reactors
46 60 00 Water and Wastewater Advanced Treatment Equipment
46 61 00 Filtration Equipment
46 61 13 Filter Media
46 61 16 Filter Surface Wash Agitators
46 61 17 Filter Air Scour Equipment
46 61 19 Wash Water Troughs
46 61 21 Pressure Filters
46 61 23 Gravity Filters
46 61 26 High-rate Sand Filters
46 61 29 Traveling Bridge Filters
46 61 33 Microfiltration and Ultrafiltration Membrane Equipment
46 61 41 Disc Cloth Filters
46 61 43 Rotary Drum Cloth Filters
46 61 46 Automatic Backwash Cloth Filter Equipment
46 61 53 Cartridge Filters
46 61 63 Bag Filters
46 61 73 Automatic Straining Equipment
46 63 00 Demineralization Equipment
46 63 11 Ion-exchange Vessel Media
46 63 13 Mixed Bed Ion-exchange Vessel Systems
46 63 16 Packed Bed Ion-exchange Vessel Systems
46 63 17 Electrodialysis Reversal Equipment
46 63 23 Reverse-Osmosis and Nanofiltration Membrane Equipment
46 63 31 Multiple-effect Distillation Equipment
46 63 32 Water Vapor Compression Distillation Equipment
46 63 33 Desalination Mechanical Vapor Compression Equipment
46 63 34 Desalination Thermal Vapor Compression Equipment
46 63 36 Desalination Multi-stage Flash Equipment
46 63 41 Desalination Falling Film Evaporators
46 63 43 Desalination Rising Film Evaporators
46 63 53 Desalination Forced-circulation Crystallizing Equipment
46 63 63 Desalination Spray Dry Evaporation Equipment
46 63 73 Demineralization Energy Recovery Equipment
46 66 00 Ultraviolet Equipment
46 66 13 Closed-vessel Low-pressure/Low-intensity Ultraviolet Treatment Equipment
46 66 16 Closed-vessel Low-pressure/High-intensity Ultraviolet Treatment Equipment
46 66 23 Closed-vessel Medium-pressure Ultraviolet Treatment Equipment
46 66 53 Open-channel Low-pressure/Low-intensity Ultraviolet Treatment Equipment
46 66 56 Open-channel Low-pressure/High-intensity Ultraviolet Treatment Equipment
46 66 63 Open-channel Medium-pressure Ultraviolet Treatment Equipment
46 70 00 Water and Wastewater Residuals Handling and Treatment
46 71 00 Residuals Thickening Equipment
46 71 13 Circular Gravity Thickeners
46 71 16 Gravity Belt Thickeners
46 71 23 Dissolved Air Flotation Thickening Equipment
46 71 33 Rotary Drum Thickening Equipment
46 71 36 Centrifuge Thickening Equipment
46 71 43 Disc Thickeners
46 71 46 Thickening Screw Press
46 71 53 Scum Concentrator Equipment
46 73 00 Residuals Stabilization
46 73 11 Radial Beam Fixed Digester Covers
46 73 12 Dual Deck Truss-type Fixed Digester Covers
46 73 14 Radial Beam Floating Digester Covers
46 73 16 Dual Deck Truss-type Floating Digester Covers
46 73 17 Radial Beam Floating Gas-holding Digester Covers
46 73 18 Dual Deck Truss-type Floating Gas-holding Digester Covers
46 73 19 Digester Appurtenances
46 73 21 Aerobic Digester Aeration Equipment
46 73 24 Autothermal Thermophilic Aerobic Digestion Equipment
46 73 26 Egg-shaped Digesters
46 73 31 External Draft Tube Digester Mixing System
46 73 32 Internal Draft Tube Digester Mixing System
46 73 33 Confined Gas Mixing System
46 73 34 Unconfined Gas Mixing System
46 73 41 Digester Heating Equipment
46 73 63 Residuals Pasteurization Equipment
46 76 00 Residuals Dewatering Equipment
46 76 13 Vacuum Filters
46 76 21 Belt Filter Presses
46 76 23 Plate-and-Frame Filter Presses
46 76 26 Rotary Presses
46 76 27 Screw Presses
46 76 33 Dewatering Centrifuges
46 76 53 Belt Dryers
46 76 60 Direct-heat Residuals Drying Equipment
46 76 70 Indirect-heat Residuals Drying Equipment
46 78 00 Thermal Treatment of Residuals
46 78 13 Multiple-hearth Sludge Incinerators
46 78 23 Fluidized-bed Sludge Incinerators
46 78 33 Ash Handling Equipment
46 78 41 Recuperative Air Preheating Equipment
46 78 46 Regenerative Thermal Oxidizers
46 78 47 Waste Heat Recovery Boilers
46 78 49 Waste Heat Recovery Heat Exchangers
46 78 73 Thermal Oxidation Equipment
48 00 00 Electrical Power Generation
48 01 00 Operation and Maintenance for Electrical Power Generation
48 01 10 Operation and Maintenance of Electrical Power Generation Equipment
48 01 70 Operation and Maintenance of Electrical Power Generation Testing
48 05 00 Common Work Results for Electrical Power Generation
48 05 05 Selective Demolition for Electrical Power Generation
48 06 00 Schedules for Electrical Power Generation
48 06 10 Schedules for Electrical Power Generation Equipment
48 06 70 Schedules for Electrical Power Generation Testing
48 08 00 Commissioning of Electrical Power Generation
48 09 00 Instrumentation and Control for Electrical Power Generation
48 10 00 Electrical Power Generation Equipment
48 11 00 Fossil Fuel Plant Electrical Power Generation Equipment
48 11 13 Fossil Fuel Electrical Power Plant Boilers
48 11 16 Fossil Fuel Electrical Power Plant Condensers
48 11 19 Fossil Fuel Electrical Power Plant Steam Turbines
48 11 23 Fossil Fuel Electrical Power Plant Gas Turbines
48 11 26 Fossil Fuel Electrical Power Plant Generators
48 12 00 Nuclear Fuel Plant Electrical Power Generation Equipment
48 12 13 Nuclear Fuel Reactors
48 12 13.13 Nuclear Fuel Fission Reactors
48 12 13.16 Nuclear Fuel Fusion Reactors
48 12 23 Nuclear Fuel Electrical Power Plant Steam Generators
48 12 26 Nuclear Fuel Electrical Power Plant Condensers
48 12 29 Nuclear Fuel Electrical Power Plant Turbines
48 12 33 Nuclear Fuel Electrical Power Generators
48 13 00 Hydroelectric Plant Electrical Power Generation Equipment
48 13 13 Hydroelectric Power Plant Water Turbines
48 13 16 Hydroelectric Power Plant Electrical Power Generators
48 14 00 Solar Energy Electrical Power Generation Equipment
48 14 13 Solar Energy Collectors
48 14 13.13 Amorphous Solar Energy Collectors
48 14 13.16 Plate Cell Solar Energy Collectors
48 14 13.19 Vacuum Tube Solar Energy Collectors
48 15 00 Wind Energy Electrical Power Generation Equipment
48 15 13 Wind Turbines
48 15 16 Wind Energy Electrical Power Generators
48 16 00 Geothermal Energy Electrical Power Generation Equipment
48 16 13 Geothermal Energy Heat Pumps
48 16 16 Geothermal Energy Condensers
48 16 19 Geothermal Energy Steam Turbines
48 16 23 Geothermal Energy Electrical Power Generators
48 17 00 Electrochemical Energy Electrical Power Generation Equipment
48 17 13 Electrical Power Generation Batteries
48 18 00 Fuel Cell Electrical Power Generation Equipment
48 18 13 Electrical Power Generation Fuel Cells
48 18 16 Hydrogen Control Equipment
48 19 00 Electrical Power Control Equipment
48 19 13 Electrical Power Generation Battery Charging Equipment
48 19 16 Electrical Power Generation Inverters
48 19 19 Electrical Power Generation Solar Tracking Equipment
48 19 23 Electrical Power Generation Transformers
48 19 26 Electrical Power Generation Voltage Regulators
48 30 00 Combined Heat and Power Generation
48 31 00 Combustion Combined Heat and Power Generation
48 31 13 Natural Gas-Fueled Combined Heat and Power Generation
48 31 16 Biomass-Fueled Combined Heat and Power Generation
48 70 00 Electrical Power Generation Testing
48 71 00 Electrical Power Generation Test Equipment
48 71 13 Electrical Power Generation Corona Test Equipment
48 71 16 Electrical Power Generation Current Test Equipment
48 71 19 Electrical Power Generation Power Test Equipment
48 71 23 Electrical Power Generation Resistance Test Equipment
48 71 26 Electrical Power Generation Voltage Test Equipment