TIMELINE 2010-2011

October 2010 – January 2011

- Follow up with businesses to enroll and advance them in EcoBizNYC program

- Evaluate program by surveying businesses and interns, and continue to restructure program

- Improve web resources for participating businesses and update program description on website

- Develop workshops for 2011 with increased focus on stewardship component

- Plan outreach and workshops for business owners with LES BID and Chinatown Partnership

- Recruit 10 college interns for winter and summer semesters

- Outreach to schools and after school programs for Street Tree Stewardship Program

January/February 2011

- Start Trainings for college interns

March – December 2011

- Conduct community workshops

- Start outreach to businesses in settlement area as well as expanded area with newly trained interns

- Award 10 businesses the sustainability grants for achieving recommendations and distribute stickers

- Update information on business status/improvement online

- Recruit 10 college interns for summer and fall semesters

March 2011

- Enroll 20 local youth in Street Tree Stewardship program and start training

April 2011

- Kick off Street Tree Stewardship Program on Arbor Day, April 29, 2011 with press event

- Survey settlement area for empty street tree planting sites and recommend to Million TreesNYC

August – November 2011

- Get 50 street trees planted and focus stewardship effort on newly planted trees