## Sheet1
PUB_DATE | BORO | MANAGING_AGCY_CD | MANAGING_AGCY | PPROJECT_ID | PROJECT_DESCR | SEQ_NUMBER | TASK_DESCRIPTION | ORIG_START_DATE | ORIG_END_DATE | TASK_START_DATE | TASK_END_DATE
20231026 | CITYWIDE | 042 | CITY UNIVERSITY | CA002-023 | Health, Safety and ADA Projects | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | CITYWIDE | 042 | CITY UNIVERSITY | CA002-023 | Health, Safety and ADA Projects | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | CITYWIDE | 042 | CITY UNIVERSITY | CA002-023 | Health, Safety and ADA Projects | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | CITYWIDE | 042 | CITY UNIVERSITY | CA002-023 | Health, Safety and ADA Projects | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | CITYWIDE | 042 | CITY UNIVERSITY | CA002-023 | Health, Safety and ADA Projects | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | CITYWIDE | 042 | CITY UNIVERSITY | CA002-023 | Health, Safety and ADA Projects | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | CITYWIDE | 042 | CITY UNIVERSITY | CA002-023 | Health, Safety and ADA Projects | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | CITYWIDE | 042 | CITY UNIVERSITY | CA002-023 | Health, Safety and ADA Projects | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | CITYWIDE | 042 | CITY UNIVERSITY | CA002-023 | Health, Safety and ADA Projects | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | CITYWIDE | 042 | CITY UNIVERSITY | CA002-023 | Health, Safety and ADA Projects | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2029
20231026 | CITYWIDE | 042 | CITY UNIVERSITY | CA202-006 | ADA Compliance | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2006 | Sep 2006 | Jun 2006 | Sep 2006
20231026 | CITYWIDE | 042 | CITY UNIVERSITY | CA202-006 | ADA Compliance | 5 | CONSTRUCTION TO 25% | Sep 2006 | Jan 2007 | Sep 2006 | Jan 2007
20231026 | CITYWIDE | 042 | CITY UNIVERSITY | CA202-006 | ADA Compliance | 6 | CONSTRUCTION TO 50% | Jan 2007 | May 2007 | Jan 2007 | May 2007
20231026 | CITYWIDE | 042 | CITY UNIVERSITY | CA202-006 | ADA Compliance | 7 | CONSTRUCTION TO 75% | May 2007 | Sep 2007 | May 2007 | Sep 2007
20231026 | CITYWIDE | 042 | CITY UNIVERSITY | CA202-006 | ADA Compliance | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2007 | Dec 2007 | Sep 2007 | Dec 2007
20231026 | CITYWIDE | 042 | CITY UNIVERSITY | CA202-006 | ADA Compliance | 9 | SUBSTANTIAL COMPLETION | Dec 2007 | Feb 2008 | Dec 2007 | Feb 2008
20231026 | CITYWIDE | 042 | CITY UNIVERSITY | CA202-006 | ADA Compliance | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2008 | Mar 2008 | Feb 2008 | Mar 2008
20231026 | CITYWIDE | 042 | CITY UNIVERSITY | CA207-006 | CUNY Incubator Network | 1 | DEVELOP SCOPE | May 2009 | Aug 2009 | Jul 2021 | Sep 2021
20231026 | CITYWIDE | 042 | CITY UNIVERSITY | CA207-006 | CUNY Incubator Network | 2 | PRELIMINARY DESIGN | Aug 2009 | Dec 2009 | Sep 2021 | Jan 2022
20231026 | CITYWIDE | 042 | CITY UNIVERSITY | CA207-006 | CUNY Incubator Network | 3 | FINAL DESIGN | Dec 2009 | Jun 2010 | Jan 2022 | Jul 2022
20231026 | CITYWIDE | 042 | CITY UNIVERSITY | CA207-006 | CUNY Incubator Network | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2010 | Sep 2010 | Jul 2022 | Oct 2022
20231026 | CITYWIDE | 042 | CITY UNIVERSITY | CA207-006 | CUNY Incubator Network | 5 | CONSTRUCTION TO 25% | Sep 2010 | Jan 2011 | Oct 2022 | Feb 2023
20231026 | CITYWIDE | 042 | CITY UNIVERSITY | CA207-006 | CUNY Incubator Network | 6 | CONSTRUCTION TO 50% | Jan 2011 | May 2011 | Feb 2023 | Jun 2023
20231026 | CITYWIDE | 042 | CITY UNIVERSITY | CA207-006 | CUNY Incubator Network | 7 | CONSTRUCTION TO 75% | May 2011 | Sep 2011 | Jun 2023 | Oct 2023
20231026 | CITYWIDE | 042 | CITY UNIVERSITY | CA207-006 | CUNY Incubator Network | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2011 | Dec 2011 | Oct 2023 | Jan 2024
20231026 | CITYWIDE | 042 | CITY UNIVERSITY | CA207-006 | CUNY Incubator Network | 9 | SUBSTANTIAL COMPLETION | Dec 2011 | Feb 2012 | Jan 2024 | Mar 2024
20231026 | CITYWIDE | 042 | CITY UNIVERSITY | CA207-006 | CUNY Incubator Network | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2012 | Mar 2012 | Mar 2024 | Aug 2028
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79-ADA | ADA COMPLIANCE RENOVATIONS AT NYPD PRECINCTS | 1 | DESIGN | Jul 2020 | Jan 2021 | Jul 2020 | Jan 2021
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79-ADA | ADA COMPLIANCE RENOVATIONS AT NYPD PRECINCTS | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2021 | Apr 2021 | Jan 2021 | Apr 2021
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79-ADA | ADA COMPLIANCE RENOVATIONS AT NYPD PRECINCTS | 3 | CONSTRUCTION | Apr 2021 | Apr 2022 | Apr 2021 | Apr 2022
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79-ADA | ADA COMPLIANCE RENOVATIONS AT NYPD PRECINCTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2022 | Oct 2022 | Apr 2022 | Oct 2027
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79-ADA2 | ADA COMPLIANCE HUB RENOVATIONS AT NYPD PRECINCTS | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79-ADA2 | ADA COMPLIANCE HUB RENOVATIONS AT NYPD PRECINCTS | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79-ADA2 | ADA COMPLIANCE HUB RENOVATIONS AT NYPD PRECINCTS | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79-ADA2 | ADA COMPLIANCE HUB RENOVATIONS AT NYPD PRECINCTS | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79-ADA2 | ADA COMPLIANCE HUB RENOVATIONS AT NYPD PRECINCTS | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79-ADA2 | ADA COMPLIANCE HUB RENOVATIONS AT NYPD PRECINCTS | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79-ADA2 | ADA COMPLIANCE HUB RENOVATIONS AT NYPD PRECINCTS | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79-ADA2 | ADA COMPLIANCE HUB RENOVATIONS AT NYPD PRECINCTS | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79-ADA2 | ADA COMPLIANCE HUB RENOVATIONS AT NYPD PRECINCTS | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79-ADA2 | ADA COMPLIANCE HUB RENOVATIONS AT NYPD PRECINCTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BATH | CITYWIDE BATHROOM RENOVATION | 1 | DEVELOP SCOPE | Feb 2015 | May 2015 | Feb 2015 | May 2015
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BATH | CITYWIDE BATHROOM RENOVATION | 2 | PRELIMINARY DESIGN | May 2015 | Sep 2015 | May 2015 | Sep 2015
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BATH | CITYWIDE BATHROOM RENOVATION | 3 | FINAL DESIGN | Sep 2015 | Mar 2016 | Sep 2015 | Mar 2016
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BATH | CITYWIDE BATHROOM RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2016 | Jun 2016 | Mar 2016 | Jun 2016
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BATH | CITYWIDE BATHROOM RENOVATION | 5 | CONSTRUCTION TO 25% | Jun 2016 | Oct 2016 | Jun 2016 | Oct 2016
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BATH | CITYWIDE BATHROOM RENOVATION | 6 | CONSTRUCTION TO 50% | Oct 2016 | Jan 2017 | Oct 2016 | Jan 2017
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BATH | CITYWIDE BATHROOM RENOVATION | 7 | CONSTRUCTION TO 75% | Jan 2017 | May 2017 | Jan 2017 | May 2024
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BATH | CITYWIDE BATHROOM RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | May 2017 | Aug 2017 | May 2024 | Aug 2024
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BATH | CITYWIDE BATHROOM RENOVATION | 9 | SUBSTANTIAL COMPLETION | Aug 2017 | Oct 2017 | Aug 2024 | Oct 2024
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BATH | CITYWIDE BATHROOM RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2017 | Nov 2017 | Oct 2024 | Nov 2027
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHI | BOILER REPLACEMENT AT 68TH, 76TH AND 102ND PCTS | 1 | DEVELOP SCOPE | Jun 2014 | Sep 2014 | Jun 2014 | Sep 2014
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHI | BOILER REPLACEMENT AT 68TH, 76TH AND 102ND PCTS | 2 | PRELIMINARY DESIGN | Sep 2014 | Jan 2015 | Sep 2014 | Jan 2015
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHI | BOILER REPLACEMENT AT 68TH, 76TH AND 102ND PCTS | 3 | FINAL DESIGN | Jan 2015 | Jul 2015 | Jan 2015 | Jul 2015
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHI | BOILER REPLACEMENT AT 68TH, 76TH AND 102ND PCTS | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Oct 2015 | Jul 2015 | Oct 2015
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHI | BOILER REPLACEMENT AT 68TH, 76TH AND 102ND PCTS | 5 | CONSTRUCTION TO 25% | Oct 2015 | Feb 2016 | Oct 2015 | Feb 2016
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHI | BOILER REPLACEMENT AT 68TH, 76TH AND 102ND PCTS | 6 | CONSTRUCTION TO 50% | Feb 2016 | Jun 2016 | Feb 2016 | Jun 2016
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHI | BOILER REPLACEMENT AT 68TH, 76TH AND 102ND PCTS | 7 | CONSTRUCTION TO 75% | Jun 2016 | Oct 2016 | Jun 2016 | Oct 2020
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHI | BOILER REPLACEMENT AT 68TH, 76TH AND 102ND PCTS | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2016 | Jan 2017 | Oct 2020 | Jan 2021
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHI | BOILER REPLACEMENT AT 68TH, 76TH AND 102ND PCTS | 9 | SUBSTANTIAL COMPLETION | Jan 2017 | Mar 2017 | Jan 2021 | Mar 2021
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHI | BOILER REPLACEMENT AT 68TH, 76TH AND 102ND PCTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Apr 2017 | Mar 2021 | Jun 2028
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHY | BOILERS AT 26TH, 42ND & 46TH PRECINCTS | 1 | DEVELOP SCOPE | Jun 2014 | Sep 2014 | Jun 2014 | Sep 2014
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHY | BOILERS AT 26TH, 42ND & 46TH PRECINCTS | 2 | PRELIMINARY DESIGN | Sep 2014 | Jan 2015 | Sep 2014 | Jan 2015
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHY | BOILERS AT 26TH, 42ND & 46TH PRECINCTS | 3 | FINAL DESIGN | Jan 2015 | Jul 2015 | Jan 2015 | Jul 2015
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHY | BOILERS AT 26TH, 42ND & 46TH PRECINCTS | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Oct 2015 | Jul 2015 | Oct 2015
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHY | BOILERS AT 26TH, 42ND & 46TH PRECINCTS | 5 | CONSTRUCTION TO 25% | Oct 2015 | Feb 2016 | Oct 2015 | Feb 2016
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHY | BOILERS AT 26TH, 42ND & 46TH PRECINCTS | 6 | CONSTRUCTION TO 50% | Feb 2016 | Jun 2016 | Feb 2016 | Jun 2016
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHY | BOILERS AT 26TH, 42ND & 46TH PRECINCTS | 7 | CONSTRUCTION TO 75% | Jun 2016 | Oct 2016 | Jun 2016 | Oct 2023
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHY | BOILERS AT 26TH, 42ND & 46TH PRECINCTS | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2016 | Jan 2017 | Oct 2023 | Jan 2024
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHY | BOILERS AT 26TH, 42ND & 46TH PRECINCTS | 9 | SUBSTANTIAL COMPLETION | Jan 2017 | Mar 2017 | Jan 2024 | Mar 2024
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHY | BOILERS AT 26TH, 42ND & 46TH PRECINCTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Apr 2017 | Mar 2024 | Apr 2024
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAJZ | 49TH & 115TH & MTN PCT HVAC REPLACEMENT | 1 | DESIGN | Dec 2019 | Jun 2020 | Dec 2019 | Jun 2020
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAJZ | 49TH & 115TH & MTN PCT HVAC REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAJZ | 49TH & 115TH & MTN PCT HVAC REPLACEMENT | 3 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAJZ | 49TH & 115TH & MTN PCT HVAC REPLACEMENT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Mar 2022 | Sep 2021 | Mar 2025
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKI | BOILERS AT MTS, HWY 3, 75 & 77 PRECINCTS | 1 | DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKI | BOILERS AT MTS, HWY 3, 75 & 77 PRECINCTS | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKI | BOILERS AT MTS, HWY 3, 75 & 77 PRECINCTS | 3 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKI | BOILERS AT MTS, HWY 3, 75 & 77 PRECINCTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Mar 2023 | Sep 2022 | Sep 2025
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKM | PSA4 HVAC | 1 | DEVELOP SCOPE | Dec 2020 | Mar 2021 | Dec 2020 | Mar 2021
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKM | PSA4 HVAC | 2 | PRELIMINARY DESIGN | Mar 2021 | Jul 2021 | Mar 2021 | Jul 2021
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKM | PSA4 HVAC | 3 | FINAL DESIGN | Jul 2021 | Nov 2021 | Jul 2021 | Nov 2021
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKM | PSA4 HVAC | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2021 | May 2022 | Nov 2021 | May 2022
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKM | PSA4 HVAC | 5 | CONSTRUCTION TO 25% | May 2022 | Aug 2022 | May 2022 | Aug 2022
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKM | PSA4 HVAC | 6 | CONSTRUCTION TO 50% | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKM | PSA4 HVAC | 7 | CONSTRUCTION TO 75% | Dec 2022 | Apr 2023 | Dec 2022 | Apr 2023
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKM | PSA4 HVAC | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2023 | Jul 2023 | Apr 2023 | Jul 2023
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKM | PSA4 HVAC | 9 | SUBSTANTIAL COMPLETION | Jul 2023 | Sep 2023 | Jul 2023 | Sep 2023
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKM | PSA4 HVAC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Oct 2023 | Sep 2023 | Jun 2027
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKN | BOILERS REPLACEMENT AT BMS & SRG4 | 1 | DEVELOP SCOPE | Dec 2020 | Mar 2021 | Dec 2020 | Mar 2021
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKN | BOILERS REPLACEMENT AT BMS & SRG4 | 2 | PRELIMINARY DESIGN | Mar 2021 | Jul 2021 | Mar 2021 | Jul 2021
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKN | BOILERS REPLACEMENT AT BMS & SRG4 | 3 | FINAL DESIGN | Jul 2021 | Nov 2021 | Jul 2021 | Nov 2021
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKN | BOILERS REPLACEMENT AT BMS & SRG4 | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2021 | May 2022 | Nov 2021 | May 2022
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKN | BOILERS REPLACEMENT AT BMS & SRG4 | 5 | CONSTRUCTION TO 25% | May 2022 | Aug 2022 | May 2022 | Aug 2022
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKN | BOILERS REPLACEMENT AT BMS & SRG4 | 6 | CONSTRUCTION TO 50% | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKN | BOILERS REPLACEMENT AT BMS & SRG4 | 7 | CONSTRUCTION TO 75% | Dec 2022 | Apr 2023 | Dec 2022 | Apr 2023
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKN | BOILERS REPLACEMENT AT BMS & SRG4 | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2023 | Jul 2023 | Apr 2023 | Jul 2023
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKN | BOILERS REPLACEMENT AT BMS & SRG4 | 9 | SUBSTANTIAL COMPLETION | Jul 2023 | Sep 2023 | Jul 2023 | Sep 2023
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKN | BOILERS REPLACEMENT AT BMS & SRG4 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Oct 2023 | Sep 2023 | Jun 2027
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMALC | BOILERS REPLACEMENT AT 52 & 108 PCT | 1 | DESIGN | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMALC | BOILERS REPLACEMENT AT 52 & 108 PCT | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2021 | Mar 2022 | Dec 2021 | Mar 2022
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMALC | BOILERS REPLACEMENT AT 52 & 108 PCT | 3 | CONSTRUCTION | Mar 2022 | Mar 2023 | Mar 2022 | Mar 2023
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMALC | BOILERS REPLACEMENT AT 52 & 108 PCT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Sep 2023 | Mar 2023 | Sep 2027
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMALE | Electric Upgrade and Generator at the 68, 108, and 120 Pct | 1 | DESIGN | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMALE | Electric Upgrade and Generator at the 68, 108, and 120 Pct | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2021 | Mar 2022 | Dec 2021 | Mar 2022
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMALE | Electric Upgrade and Generator at the 68, 108, and 120 Pct | 3 | CONSTRUCTION | Mar 2022 | Mar 2023 | Mar 2022 | Mar 2023
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMALE | Electric Upgrade and Generator at the 68, 108, and 120 Pct | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Sep 2023 | Mar 2023 | Sep 2027
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMALF | MULTI-YEAR PAVING AT VARIOUS NYPD PRECINCTS | 1 | DESIGN | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMALF | MULTI-YEAR PAVING AT VARIOUS NYPD PRECINCTS | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2021 | Mar 2022 | Dec 2021 | Mar 2022
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMALF | MULTI-YEAR PAVING AT VARIOUS NYPD PRECINCTS | 3 | CONSTRUCTION | Mar 2022 | Mar 2023 | Mar 2022 | Mar 2023
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMALF | MULTI-YEAR PAVING AT VARIOUS NYPD PRECINCTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Sep 2023 | Mar 2023 | Jun 2028
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMALG | 101ST AND 103RD PRECINCT ROOF AND FACADE | 1 | DESIGN | Dec 2021 | Jun 2022 | Dec 2021 | Jun 2022
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMALG | 101ST AND 103RD PRECINCT ROOF AND FACADE | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMALG | 101ST AND 103RD PRECINCT ROOF AND FACADE | 3 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMALG | 101ST AND 103RD PRECINCT ROOF AND FACADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Mar 2024 | Sep 2023 | Jun 2031
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79CWAC | CITYWIDE HVAC PROGRAM | 1 | DESIGN | Jul 2016 | Dec 2016 | Jun 2018 | Nov 2018
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79CWAC | CITYWIDE HVAC PROGRAM | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2016 | Mar 2017 | Nov 2018 | Feb 2019
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79CWAC | CITYWIDE HVAC PROGRAM | 3 | CONSTRUCTION | Mar 2017 | Mar 2018 | Feb 2019 | Feb 2022
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79CWAC | CITYWIDE HVAC PROGRAM | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2018 | Sep 2018 | Feb 2022 | Aug 2022
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79-GEN | PRECINCT GENERATORS LIFE CYCLE REPLACEMENTS | 1 | DESIGN | Dec 2021 | Jun 2022 | Dec 2021 | Jun 2022
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79-GEN | PRECINCT GENERATORS LIFE CYCLE REPLACEMENTS | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79-GEN | PRECINCT GENERATORS LIFE CYCLE REPLACEMENTS | 3 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79-GEN | PRECINCT GENERATORS LIFE CYCLE REPLACEMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Mar 2024 | Sep 2023 | Jun 2029
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79LOCK | CITYWIDE LOCKER ROOM RENOVATION | 1 | DEVELOP SCOPE | Apr 2017 | Jul 2017 | Apr 2017 | Jul 2017
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79LOCK | CITYWIDE LOCKER ROOM RENOVATION | 2 | PRELIMINARY DESIGN | Jul 2017 | Nov 2017 | Jul 2017 | Nov 2017
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79LOCK | CITYWIDE LOCKER ROOM RENOVATION | 3 | FINAL DESIGN | Nov 2017 | May 2018 | Nov 2017 | May 2018
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79LOCK | CITYWIDE LOCKER ROOM RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | May 2018 | Aug 2018 | May 2018 | Aug 2018
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79LOCK | CITYWIDE LOCKER ROOM RENOVATION | 5 | CONSTRUCTION TO 25% | Aug 2018 | Dec 2018 | Aug 2018 | Dec 2018
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79LOCK | CITYWIDE LOCKER ROOM RENOVATION | 6 | CONSTRUCTION TO 50% | Dec 2018 | Apr 2019 | Dec 2018 | Apr 2019
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79LOCK | CITYWIDE LOCKER ROOM RENOVATION | 7 | CONSTRUCTION TO 75% | Apr 2019 | Aug 2019 | Apr 2019 | Aug 2024
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79LOCK | CITYWIDE LOCKER ROOM RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | Aug 2019 | Nov 2019 | Aug 2024 | Nov 2024
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79LOCK | CITYWIDE LOCKER ROOM RENOVATION | 9 | SUBSTANTIAL COMPLETION | Nov 2019 | Jan 2020 | Nov 2024 | Jan 2025
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79LOCK | CITYWIDE LOCKER ROOM RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2020 | Feb 2020 | Jan 2025 | Feb 2028
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | SANDCONDT | ELECTRICAL CONDUIT REPLACEMENT (SANDY) | 1 | DEVELOP SCOPE | Feb 2015 | May 2015 | Jan 2019 | Apr 2022
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | SANDCONDT | ELECTRICAL CONDUIT REPLACEMENT (SANDY) | 2 | PRELIMINARY DESIGN | May 2015 | Sep 2015 | Apr 2022 | Aug 2022
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | SANDCONDT | ELECTRICAL CONDUIT REPLACEMENT (SANDY) | 3 | FINAL DESIGN | Sep 2015 | Jan 2016 | Aug 2022 | Dec 2022
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | SANDCONDT | ELECTRICAL CONDUIT REPLACEMENT (SANDY) | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2016 | Jul 2016 | Dec 2022 | Jun 2023
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | SANDCONDT | ELECTRICAL CONDUIT REPLACEMENT (SANDY) | 5 | CONSTRUCTION TO 25% | Jul 2016 | Oct 2016 | Jun 2023 | Oct 2023
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | SANDCONDT | ELECTRICAL CONDUIT REPLACEMENT (SANDY) | 6 | CONSTRUCTION TO 50% | Nov 2016 | Feb 2017 | Oct 2023 | Feb 2024
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | SANDCONDT | ELECTRICAL CONDUIT REPLACEMENT (SANDY) | 7 | CONSTRUCTION TO 75% | Mar 2017 | Jun 2017 | Feb 2024 | Jun 2024
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | SANDCONDT | ELECTRICAL CONDUIT REPLACEMENT (SANDY) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2017 | Sep 2017 | Jun 2024 | Sep 2024
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | SANDCONDT | ELECTRICAL CONDUIT REPLACEMENT (SANDY) | 9 | SUBSTANTIAL COMPLETION | Sep 2017 | Nov 2017 | Sep 2024 | Nov 2024
20231026 | CITYWIDE | 056 | POLICE DEPARTMENT | SANDCONDT | ELECTRICAL CONDUIT REPLACEMENT (SANDY) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | Dec 2017 | Nov 2024 | Dec 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175CHILL | Chiller replacement at Bronx and Queens CO s | 1 | DESIGN | Nov 2022 | Apr 2023 | Nov 2022 | Apr 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175CHILL | Chiller replacement at Bronx and Queens CO s | 2 | CONSTRUCTION | Apr 2023 | Apr 2024 | Apr 2023 | Apr 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175CHILL | Chiller replacement at Bronx and Queens CO s | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2024 | Jul 2024 | Apr 2024 | Jul 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175CHLL2 | Chiller replacement at Manhattan CO | 1 | DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175CHLL2 | Chiller replacement at Manhattan CO | 2 | CONSTRUCTION | Jul 2024 | Jul 2025 | Jul 2024 | Jul 2025
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175CHLL2 | Chiller replacement at Manhattan CO | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175DW211 | Door widening and retaining wall reconstruction - EC211 | 1 | DESIGN | Jul 2021 | Jan 2022 | Jul 2021 | Jan 2022
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175DW211 | Door widening and retaining wall reconstruction - EC211 | 2 | CONSTRUCTION | Jan 2022 | Jan 2023 | Jan 2022 | Jan 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175DW211 | Door widening and retaining wall reconstruction - EC211 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2023 | Apr 2023 | Jan 2023 | Jun 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175EC287 | Engine Company 287 | 1 | DESIGN | Feb 2022 | Aug 2022 | Feb 2022 | Aug 2022
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175EC287 | Engine Company 287 | 2 | CONSTRUCTION | Aug 2022 | Aug 2023 | Aug 2022 | Aug 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175EC287 | Engine Company 287 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2023 | Nov 2023 | Aug 2023 | Nov 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175EMS4M | MULTI COMPONENT RENOVATIONS - EMS 4 | 1 | DESIGN | Aug 2017 | Jan 2018 | Aug 2017 | Jan 2019
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175EMS4M | MULTI COMPONENT RENOVATIONS - EMS 4 | 2 | CONSTRUCTION | Jan 2018 | Jan 2019 | Jan 2019 | Jan 2020
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175EMS4M | MULTI COMPONENT RENOVATIONS - EMS 4 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2019 | Apr 2019 | Jan 2020 | Nov 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175EMS58 | EMS 58 Construction | 1 | DESIGN | May 2023 | Nov 2023 | May 2023 | Nov 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175EMS58 | EMS 58 Construction | 2 | CONSTRUCTION | Nov 2023 | Nov 2024 | Nov 2023 | Nov 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175EMS58 | EMS 58 Construction | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2024 | Feb 2025 | Nov 2024 | Feb 2025
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175-ES55 | EMS Station 55 | 1 | DESIGN | Jun 2025 | Dec 2025 | Jun 2025 | Dec 2025
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175-ES55 | EMS Station 55 | 2 | CONSTRUCTION | Dec 2025 | Dec 2026 | Dec 2025 | Dec 2026
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175-ES55 | EMS Station 55 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2026 | Mar 2027 | Dec 2026 | Mar 2027
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175FE163 | APPARATUS FLOOR - EC163 | 1 | DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175FE163 | APPARATUS FLOOR - EC163 | 2 | CONSTRUCTION | Jul 2023 | Jul 2024 | Jul 2023 | Jul 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175FE163 | APPARATUS FLOOR - EC163 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175FE221 | APPARATUS FLOOR - EC221 | 1 | DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175FE221 | APPARATUS FLOOR - EC221 | 2 | CONSTRUCTION | Jul 2023 | Jul 2024 | Jul 2023 | Jul 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175FE221 | APPARATUS FLOOR - EC221 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175FE260 | APPARATUS FLOOR - EC260 | 1 | DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175FE260 | APPARATUS FLOOR - EC260 | 2 | CONSTRUCTION | Jul 2023 | Jul 2024 | Jul 2023 | Jul 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175FE260 | APPARATUS FLOOR - EC260 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175FE294 | APPARATUS FLOOR - EC294 | 1 | DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175FE294 | APPARATUS FLOOR - EC294 | 2 | CONSTRUCTION | Jul 2023 | Jul 2024 | Jul 2023 | Jul 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175FE294 | APPARATUS FLOOR - EC294 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175FE295 | APPARATUS FLOOR - EC295 | 1 | DESIGN | Jul 2024 | Jan 2025 | Jul 2024 | Jan 2025
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175FE295 | APPARATUS FLOOR - EC295 | 2 | CONSTRUCTION | Jan 2025 | Jan 2026 | Jan 2025 | Jan 2026
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175FE295 | APPARATUS FLOOR - EC295 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2026 | Apr 2026 | Jan 2026 | Apr 2026
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175FEC52 | Flood Mitigation Site Drainage - EC52 | 1 | DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175FEC52 | Flood Mitigation Site Drainage - EC52 | 2 | CONSTRUCTION | Jul 2022 | Jul 2023 | Jul 2022 | Jul 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175FEC52 | Flood Mitigation Site Drainage - EC52 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175FTANK | Fleet Tank Room | 1 | DESIGN | Mar 2023 | Sep 2023 | Mar 2023 | Sep 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175FTANK | Fleet Tank Room | 2 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175FTANK | Fleet Tank Room | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175M9EWF | Marine 9 East Wave Fence Attenuator | 1 | DESIGN | Jun 2024 | Dec 2024 | Jun 2024 | Dec 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175M9EWF | Marine 9 East Wave Fence Attenuator | 2 | CONSTRUCTION | Dec 2024 | Dec 2025 | Dec 2024 | Dec 2025
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175M9EWF | Marine 9 East Wave Fence Attenuator | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2025 | Mar 2026 | Dec 2025 | Mar 2026
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175MARN4 | Marine 4 Pier Renovation | 1 | DESIGN | May 2023 | Nov 2023 | May 2023 | Nov 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175MARN4 | Marine 4 Pier Renovation | 2 | CONSTRUCTION | Nov 2023 | Nov 2024 | Nov 2023 | Nov 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175MARN4 | Marine 4 Pier Renovation | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2024 | Feb 2025 | Nov 2024 | Feb 2025
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175MC153 | MULTI COMPONENT RENOVATIONS - EC153 | 1 | DESIGN | Feb 2018 | Aug 2018 | Jun 2020 | Nov 2020
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175MC153 | MULTI COMPONENT RENOVATIONS - EC153 | 2 | CONSTRUCTION | Aug 2018 | Aug 2019 | Dec 2020 | Nov 2021
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175MC153 | MULTI COMPONENT RENOVATIONS - EC153 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2019 | Nov 2019 | Dec 2021 | Dec 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175MC288 | MULTI-COMPONENT RENOVATIONS - SQ288 | 1 | DESIGN | Mar 2023 | Sep 2023 | Mar 2023 | Sep 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175MC288 | MULTI-COMPONENT RENOVATIONS - SQ288 | 2 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175MC288 | MULTI-COMPONENT RENOVATIONS - SQ288 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175MR1WF | Marine 1 Wave Fence Attentuator | 1 | DESIGN | Jun 2025 | Dec 2025 | Jun 2025 | Dec 2025
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175MR1WF | Marine 1 Wave Fence Attentuator | 2 | CONSTRUCTION | Dec 2025 | Dec 2026 | Dec 2025 | Dec 2026
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175MR1WF | Marine 1 Wave Fence Attentuator | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2026 | Mar 2027 | Dec 2026 | Mar 2027
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175RFMR9 | Marine 9 Roof Renovation | 1 | DESIGN | Jun 2024 | Dec 2024 | Jun 2024 | Dec 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175RFMR9 | Marine 9 Roof Renovation | 2 | CONSTRUCTION | Dec 2024 | Dec 2025 | Dec 2024 | Dec 2025
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175RFMR9 | Marine 9 Roof Renovation | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2025 | Mar 2026 | Dec 2025 | Mar 2026
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175SPACE | R&T (Fleet) Space at 58-80 Borden Avenue | 1 | DESIGN | Mar 2024 | Sep 2024 | Mar 2024 | Sep 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175SPACE | R&T (Fleet) Space at 58-80 Borden Avenue | 2 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175SPACE | R&T (Fleet) Space at 58-80 Borden Avenue | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175WPE46 | Roof and Waterproofing Project - EC46 | 1 | DESIGN | Nov 2017 | May 2018 | Nov 2017 | May 2018
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175WPE46 | Roof and Waterproofing Project - EC46 | 2 | CONSTRUCTION | May 2018 | May 2019 | May 2018 | May 2019
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175WPE46 | Roof and Waterproofing Project - EC46 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | May 2019 | Aug 2019 | May 2019 | Jun 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175WU299 | Cellar Reconstruction - EC299 | 1 | DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175WU299 | Cellar Reconstruction - EC299 | 2 | CONSTRUCTION | Jul 2020 | Jul 2021 | Jul 2020 | Jul 2021
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F175WU299 | Cellar Reconstruction - EC299 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Oct 2021 | Jul 2021 | Jun 2025
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F1GAZ2401 | Gazebo-Manhole project on Kings Hway & Ryder St in Brooklyn | 1 | CONSTRUCTION | Dec 2023 | Dec 2024 | Dec 2023 | Dec 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F1GAZ2401 | Gazebo-Manhole project on Kings Hway & Ryder St in Brooklyn | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2024 | Mar 2025 | Dec 2024 | Mar 2025
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F204FT317 | Fort Totten Building # 317 Demolition | 1 | DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F204FT317 | Fort Totten Building # 317 Demolition | 2 | CONSTRUCTION | Jun 2024 | Jun 2025 | Jun 2024 | Jun 2025
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F204FT317 | Fort Totten Building # 317 Demolition | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F204FTBLD | Fort Totten Buildings 322 and 323 | 1 | DESIGN | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F204FTBLD | Fort Totten Buildings 322 and 323 | 2 | CONSTRUCTION | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F204FTBLD | Fort Totten Buildings 322 and 323 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Mar 2024 | Dec 2023 | Mar 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F204HZTAC | HazTac Trailer Replacement | 1 | CONSTRUCTION | May 2022 | May 2023 | May 2022 | May 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F204HZTAC | HazTac Trailer Replacement | 2 | PUNCHLIST COMPLETE, JOB CLOSED | May 2023 | Aug 2023 | May 2023 | Aug 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F204RDWSH | Randall's Bunker Gear Laundry | 1 | DESIGN | Aug 2021 | Feb 2022 | Aug 2021 | Feb 2022
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F204RDWSH | Randall's Bunker Gear Laundry | 2 | CONSTRUCTION | Feb 2022 | Feb 2023 | Feb 2022 | Feb 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F204RDWSH | Randall's Bunker Gear Laundry | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | May 2023 | Feb 2023 | Jun 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F204RF333 | Roofing replacement at Fort Totten Building # 333 | 1 | CONSTRUCTION | Apr 2022 | Apr 2023 | Apr 2022 | Apr 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F204RF333 | Roofing replacement at Fort Totten Building # 333 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2023 | Jul 2023 | Apr 2023 | Jul 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F204SHADE | Randall's Island Shade Structure | 1 | DESIGN | Sep 2022 | Mar 2023 | Sep 2022 | Mar 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F204SHADE | Randall's Island Shade Structure | 2 | CONSTRUCTION | Mar 2023 | Mar 2024 | Mar 2023 | Mar 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F204SHADE | Randall's Island Shade Structure | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Jun 2024 | Mar 2024 | Dec 2027
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F204TRAN1 | Randall's Island Utility Upgrade | 1 | DESIGN | Oct 2022 | Apr 2023 | Oct 2022 | Apr 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F204TRAN1 | Randall's Island Utility Upgrade | 2 | CONSTRUCTION | Apr 2023 | Apr 2024 | Apr 2023 | Apr 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F204TRAN1 | Randall's Island Utility Upgrade | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2024 | Jul 2026 | Apr 2024 | Jul 2026
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F204TRAN2 | FORT TOTTEN EVOC COURSE RENOVATION (Bldg #137 & Bldg# 138) | 1 | DESIGN | Oct 2022 | Apr 2023 | Oct 2022 | Apr 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F204TRAN2 | FORT TOTTEN EVOC COURSE RENOVATION (Bldg #137 & Bldg# 138) | 2 | CONSTRUCTION | Apr 2023 | Apr 2024 | Apr 2023 | Apr 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F204TRAN2 | FORT TOTTEN EVOC COURSE RENOVATION (Bldg #137 & Bldg# 138) | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2024 | Jul 2026 | Apr 2024 | Jul 2026
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F204TRAN3 | Fort Totten Building 318/332 Renovations | 1 | DESIGN | Sep 2022 | Mar 2023 | Sep 2022 | Mar 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F204TRAN3 | Fort Totten Building 318/332 Renovations | 2 | CONSTRUCTION | Mar 2023 | Mar 2024 | Mar 2023 | Mar 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F204TRAN3 | Fort Totten Building 318/332 Renovations | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Jun 2027 | Mar 2024 | Jun 2027
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F212-COOL | Power and Cooling for Data Center 11 MetroTech | 1 | CONSTRUCTION | Jun 2020 | Jun 2021 | Jun 2020 | Jun 2021
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | F212-COOL | Power and Cooling for Data Center 11 MetroTech | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2021 | Sep 2021 | Jun 2021 | Oct 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175D155 | Door Replacement - EC155 | 1 | CONSTRUCTION | Feb 2022 | Feb 2023 | Feb 2022 | Feb 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175D155 | Door Replacement - EC155 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | May 2023 | Feb 2023 | Jun 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175D158 | Door Replacement - EC158 | 1 | CONSTRUCTION | Feb 2022 | Feb 2023 | Feb 2022 | Feb 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175D158 | Door Replacement - EC158 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | May 2023 | Feb 2023 | Jun 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175D161 | Door Replacement - EC161 | 1 | CONSTRUCTION | Feb 2022 | Feb 2023 | Feb 2022 | Feb 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175D161 | Door Replacement - EC161 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | May 2023 | Feb 2023 | Jun 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175D255 | Door Replacement - EC255 | 1 | CONSTRUCTION | Feb 2022 | Feb 2023 | Feb 2022 | Feb 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175D255 | Door Replacement - EC255 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | May 2023 | Feb 2023 | Jun 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175DES8 | Door Replacement - EMS 8 | 1 | CONSTRUCTION | Feb 2022 | Feb 2023 | Feb 2022 | Feb 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175DES8 | Door Replacement - EMS 8 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | May 2023 | Feb 2023 | Jun 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175DR44 | DOOR REPLACEMENT - EC44 | 2 | CONSTRUCTION | Apr 2022 | Apr 2023 | Jun 2021 | Jun 2022
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175DR44 | DOOR REPLACEMENT - EC44 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2023 | Jul 2023 | Jun 2022 | Sep 2022
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175E287 | Door Replacement - EC287 | 1 | CONSTRUCTION | Jun 2022 | Jun 2023 | Jun 2022 | Jun 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175E287 | Door Replacement - EC287 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175G153 | GENERATOR - EC153 | 1 | DESIGN | Feb 2023 | Aug 2023 | Feb 2023 | Aug 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175G153 | GENERATOR - EC153 | 2 | CONSTRUCTION | Aug 2023 | Aug 2024 | Aug 2023 | Aug 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175G153 | GENERATOR - EC153 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2024 | Nov 2024 | Aug 2024 | Nov 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175G157 | Generator - EC157 | 1 | DESIGN | Nov 2020 | May 2021 | Nov 2020 | May 2021
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175G157 | Generator - EC157 | 2 | CONSTRUCTION | May 2021 | May 2022 | May 2021 | May 2022
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175G157 | Generator - EC157 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | May 2022 | Nov 2023 | May 2022 | Nov 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175G158 | Generator - EC158 | 1 | DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175G158 | Generator - EC158 | 2 | CONSTRUCTION | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175G158 | Generator - EC158 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Sep 2022 | Jun 2022 | Jun 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175G246 | GENERATOR - EC246 | 1 | DESIGN | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175G246 | GENERATOR - EC246 | 2 | CONSTRUCTION | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175G246 | GENERATOR - EC246 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175G254 | GENERATOR - EC254 | 1 | DESIGN | Sep 2023 | Mar 2024 | Sep 2023 | Mar 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175G254 | GENERATOR - EC254 | 2 | CONSTRUCTION | Mar 2024 | Mar 2025 | Mar 2024 | Mar 2025
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175G254 | GENERATOR - EC254 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Jun 2025 | Mar 2025 | Jun 2025
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175G295 | GENERATOR - EC295 | 1 | DESIGN | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175G295 | GENERATOR - EC295 | 2 | CONSTRUCTION | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175G295 | GENERATOR - EC295 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175G307 | GENERATOR - EC307 | 1 | DESIGN | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175G307 | GENERATOR - EC307 | 2 | CONSTRUCTION | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175G307 | GENERATOR - EC307 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175GE16 | GENERATOR - EC16 | 1 | DESIGN | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175GE16 | GENERATOR - EC16 | 2 | CONSTRUCTION | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175GE16 | GENERATOR - EC16 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175GE40 | GENERATOR - EC40 | 1 | DESIGN | Sep 2023 | Mar 2024 | Sep 2023 | Mar 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175GE40 | GENERATOR - EC40 | 2 | CONSTRUCTION | Mar 2024 | Mar 2025 | Mar 2024 | Mar 2025
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175GE40 | GENERATOR - EC40 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Jun 2025 | Mar 2025 | Jun 2025
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175GE74 | GENERATOR - EC74 | 1 | DESIGN | Feb 2023 | Aug 2023 | Feb 2023 | Aug 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175GE74 | GENERATOR - EC74 | 2 | CONSTRUCTION | Aug 2023 | Aug 2024 | Aug 2023 | Aug 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175GE74 | GENERATOR - EC74 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2024 | Nov 2024 | Aug 2024 | Nov 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175GE89 | GENERATOR - EC89 | 1 | DESIGN | Nov 2022 | May 2023 | Nov 2022 | May 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175GE89 | GENERATOR - EC89 | 2 | CONSTRUCTION | May 2023 | May 2024 | May 2023 | May 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175GE89 | GENERATOR - EC89 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Aug 2024 | May 2024 | Aug 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175GE96 | GENERATOR - EC96 | 1 | DESIGN | Feb 2023 | Aug 2023 | Feb 2023 | Aug 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175GE96 | GENERATOR - EC96 | 2 | CONSTRUCTION | Aug 2023 | Aug 2024 | Aug 2023 | Aug 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175GE96 | GENERATOR - EC96 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2024 | Nov 2024 | Aug 2024 | Nov 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175K221 | KITCHENT RENOVATION - EC221 | 1 | DESIGN | Feb 2023 | Aug 2023 | Feb 2023 | Aug 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175K221 | KITCHENT RENOVATION - EC221 | 2 | CONSTRUCTION | Aug 2023 | Aug 2024 | Aug 2023 | Aug 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175K221 | KITCHENT RENOVATION - EC221 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2024 | Nov 2024 | Aug 2024 | Nov 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175K316 | KITCHENT RENOVATION - EC316 | 1 | CONSTRUCTION | Aug 2023 | Aug 2024 | Aug 2023 | Aug 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175K316 | KITCHENT RENOVATION - EC316 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2024 | Nov 2024 | Aug 2024 | Nov 2024
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175KT96 | KITCHEN - EC96 | 1 | DESIGN | Oct 2021 | Apr 2022 | Oct 2021 | Apr 2022
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175KT96 | KITCHEN - EC96 | 2 | CONSTRUCTION | Apr 2022 | Apr 2023 | Apr 2022 | Apr 2023
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175KT96 | KITCHEN - EC96 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2023 | Jul 2023 | Apr 2023 | Jun 2029
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | SANDHM265 | HURRICANE SANDY HAZMAT MITIGATION-EC265 | 1 | DESIGN | Apr 2016 | Oct 2016 | Apr 2017 | Oct 2017
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | SANDHM265 | HURRICANE SANDY HAZMAT MITIGATION-EC265 | 2 | CONSTRUCTION | Oct 2016 | Oct 2017 | Oct 2017 | Oct 2018
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | SANDHM265 | HURRICANE SANDY HAZMAT MITIGATION-EC265 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2017 | Jan 2018 | Oct 2018 | Mar 2025
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | SANDHM266 | HURRICANE SANDY HAZMAT MITIGATION - EC266 | 1 | DESIGN | Mar 2016 | Sep 2016 | Mar 2017 | Sep 2017
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | SANDHM266 | HURRICANE SANDY HAZMAT MITIGATION - EC266 | 2 | CONSTRUCTION | Sep 2016 | Sep 2017 | Sep 2017 | Sep 2018
20231026 | CITYWIDE | 057 | FIRE DEPARTMENT | SANDHM266 | HURRICANE SANDY HAZMAT MITIGATION - EC266 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2017 | Dec 2017 | Sep 2018 | Oct 2025
20231026 | CITYWIDE | 068 | ADMIN FOR CHILDREN'S SERVICES | ACSPDF | Renovation projects for field offices | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jun 2020 | Sep 2020
20231026 | CITYWIDE | 068 | ADMIN FOR CHILDREN'S SERVICES | ACSPDF | Renovation projects for field offices | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Sep 2020 | Jan 2021
20231026 | CITYWIDE | 068 | ADMIN FOR CHILDREN'S SERVICES | ACSPDF | Renovation projects for field offices | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2021 | Jul 2021
20231026 | CITYWIDE | 068 | ADMIN FOR CHILDREN'S SERVICES | ACSPDF | Renovation projects for field offices | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2021 | Oct 2021
20231026 | CITYWIDE | 068 | ADMIN FOR CHILDREN'S SERVICES | ACSPDF | Renovation projects for field offices | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2021 | Feb 2022
20231026 | CITYWIDE | 068 | ADMIN FOR CHILDREN'S SERVICES | ACSPDF | Renovation projects for field offices | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2022 | Jun 2022
20231026 | CITYWIDE | 068 | ADMIN FOR CHILDREN'S SERVICES | ACSPDF | Renovation projects for field offices | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2022 | Oct 2022
20231026 | CITYWIDE | 068 | ADMIN FOR CHILDREN'S SERVICES | ACSPDF | Renovation projects for field offices | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2026 | Jan 2027
20231026 | CITYWIDE | 068 | ADMIN FOR CHILDREN'S SERVICES | ACSPDF | Renovation projects for field offices | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2023 | Jan 2027 | Mar 2027
20231026 | CITYWIDE | 068 | ADMIN FOR CHILDREN'S SERVICES | ACSPDF | Renovation projects for field offices | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2027 | Apr 2027
20231026 | CITYWIDE | 071 | DEPT OF HOMELESS SERVICES | HRCN100VA | Volunteers of America | 1 | DESIGN | Aug 2014 | Nov 2014 | Jan 2025 | Jun 2025
20231026 | CITYWIDE | 071 | DEPT OF HOMELESS SERVICES | HRCN100VA | Volunteers of America | 2 | CONSTRUCTION | Nov 2014 | Mar 2015 | Jun 2025 | Jun 2027
20231026 | CITYWIDE | 071 | DEPT OF HOMELESS SERVICES | HRCN100VA | Volunteers of America | 3 | FINAL DESIGN | Mar 2015 | Jul 2015 | Jun 2025 | Jun 2027
20231026 | CITYWIDE | 071 | DEPT OF HOMELESS SERVICES | HRCN100VA | Volunteers of America | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Jan 2016 | Jun 2025 | Jun 2027
20231026 | CITYWIDE | 071 | DEPT OF HOMELESS SERVICES | HRCN100VA | Volunteers of America | 5 | CONSTRUCTION TO 25% | Jan 2016 | May 2016 | Jun 2025 | Jun 2027
20231026 | CITYWIDE | 071 | DEPT OF HOMELESS SERVICES | HRCN100VA | Volunteers of America | 6 | CONSTRUCTION TO 50% | May 2016 | Sep 2016 | Jun 2025 | Jun 2027
20231026 | CITYWIDE | 071 | DEPT OF HOMELESS SERVICES | HRCN100VA | Volunteers of America | 7 | CONSTRUCTION TO 75% | Sep 2016 | Jan 2017 | Jun 2025 | Jun 2027
20231026 | CITYWIDE | 071 | DEPT OF HOMELESS SERVICES | HRCN100VA | Volunteers of America | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2017 | Apr 2017 | Jun 2025 | Jun 2027
20231026 | CITYWIDE | 071 | DEPT OF HOMELESS SERVICES | HRCN100VA | Volunteers of America | 9 | SUBSTANTIAL COMPLETION | Apr 2017 | May 2017 | Jun 2025 | Jun 2027
20231026 | CITYWIDE | 071 | DEPT OF HOMELESS SERVICES | HRCN100VA | Volunteers of America | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2017 | Jun 2017 | Jun 2025 | Jun 2027
20231026 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C75GENREP | Installation of Replacement Generators RNDC, EMTC,GMDC,RMSC | 1 | DESIGN | Jul 2014 | Aug 2014 | Jul 2014 | Aug 2014
20231026 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C75GENREP | Installation of Replacement Generators RNDC, EMTC,GMDC,RMSC | 2 | BID AWARD AND REGISTER CONTRCT | Aug 2014 | Nov 2014 | Aug 2014 | Nov 2014
20231026 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C75GENREP | Installation of Replacement Generators RNDC, EMTC,GMDC,RMSC | 3 | CONSTRUCTION | Nov 2014 | May 2015 | Nov 2014 | May 2015
20231026 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C75GENREP | Installation of Replacement Generators RNDC, EMTC,GMDC,RMSC | 4 | ORIGINAL EQUIP & FURNISHING | May 2015 | Aug 2015 | May 2015 | Aug 2015
20231026 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C75GENREP | Installation of Replacement Generators RNDC, EMTC,GMDC,RMSC | 5 | SUBSTANTIAL COMPLETION | Aug 2015 | Sep 2015 | Aug 2015 | Sep 2015
20231026 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C75GENREP | Installation of Replacement Generators RNDC, EMTC,GMDC,RMSC | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2015 | Oct 2015 | Sep 2015 | Jun 2029
20231026 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C-75MISC | MISC INFRASTRUCTURE RECON | 1 | DEVELOP SCOPE | Jun 2008 | Jun 2010 | Jun 2008 | Jun 2010
20231026 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C-75MISC | MISC INFRASTRUCTURE RECON | 2 | PRELIMINARY DESIGN | Jun 2010 | Jun 2012 | Jun 2010 | Jun 2012
20231026 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C-75MISC | MISC INFRASTRUCTURE RECON | 3 | FINAL DESIGN | Jun 2012 | Jun 2014 | Jun 2012 | Jun 2014
20231026 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C-75MISC | MISC INFRASTRUCTURE RECON | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2014 | Jun 2016 | Jun 2014 | Jun 2016
20231026 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C-75MISC | MISC INFRASTRUCTURE RECON | 5 | CONSTRUCTION TO 25% | Jun 2016 | Jun 2018 | Jun 2016 | Jun 2018
20231026 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C-75MISC | MISC INFRASTRUCTURE RECON | 6 | CONSTRUCTION TO 50% | Jun 2018 | Jun 2020 | Jun 2018 | Jun 2020
20231026 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C-75MISC | MISC INFRASTRUCTURE RECON | 7 | CONSTRUCTION TO 75% | Jun 2020 | Jun 2022 | Jun 2020 | Jun 2022
20231026 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C-75MISC | MISC INFRASTRUCTURE RECON | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2022 | Jun 2024 | Jun 2022 | Jun 2024
20231026 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C-75MISC | MISC INFRASTRUCTURE RECON | 9 | SUBSTANTIAL COMPLETION | Jun 2024 | Jun 2026 | Jun 2024 | Jun 2026
20231026 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C-75MISC | MISC INFRASTRUCTURE RECON | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2033
20231026 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C75POWRF | Replace 5 and 27 KV Feeders | 1 | DESIGN | Dec 2015 | Sep 2016 | Jun 2018 | Apr 2019
20231026 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C75POWRF | Replace 5 and 27 KV Feeders | 2 | BID AWARD AND REGISTER CONTRCT | Oct 2016 | Sep 2017 | Apr 2019 | Mar 2020
20231026 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C75POWRF | Replace 5 and 27 KV Feeders | 3 | CONSTRUCTION TO 75% | Oct 2017 | May 2019 | Apr 2020 | Jan 2021
20231026 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C75POWRF | Replace 5 and 27 KV Feeders | 4 | SUBSTANTIAL COMPLETION | May 2019 | Sep 2019 | Jan 2021 | Dec 2024
20231026 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C75POWRF | Replace 5 and 27 KV Feeders | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Nov 2019 | Jan 2025 | May 2032
20231026 | CITYWIDE | 096 | HUMAN RESOURCES ADMINISTRATION | HR25EFOY | HRA FACILITIES & EQUIPMENT OUTYEARS FOR UPGRADES | 1 | DEVELOP SCOPE | Jan 2008 | Mar 2008 | Jul 2026 | Sep 2026
20231026 | CITYWIDE | 096 | HUMAN RESOURCES ADMINISTRATION | HR25EFOY | HRA FACILITIES & EQUIPMENT OUTYEARS FOR UPGRADES | 2 | PRELIMINARY DESIGN | Mar 2008 | Jul 2008 | Sep 2026 | Jan 2027
20231026 | CITYWIDE | 096 | HUMAN RESOURCES ADMINISTRATION | HR25EFOY | HRA FACILITIES & EQUIPMENT OUTYEARS FOR UPGRADES | 3 | FINAL DESIGN | Jul 2008 | Jan 2009 | Jan 2027 | Jul 2027
20231026 | CITYWIDE | 096 | HUMAN RESOURCES ADMINISTRATION | HR25EFOY | HRA FACILITIES & EQUIPMENT OUTYEARS FOR UPGRADES | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2009 | Apr 2009 | Jul 2027 | Oct 2027
20231026 | CITYWIDE | 096 | HUMAN RESOURCES ADMINISTRATION | HR25EFOY | HRA FACILITIES & EQUIPMENT OUTYEARS FOR UPGRADES | 5 | CONSTRUCTION TO 25% | Apr 2009 | Aug 2009 | Oct 2027 | Feb 2028
20231026 | CITYWIDE | 096 | HUMAN RESOURCES ADMINISTRATION | HR25EFOY | HRA FACILITIES & EQUIPMENT OUTYEARS FOR UPGRADES | 6 | CONSTRUCTION TO 50% | Aug 2009 | Dec 2009 | Feb 2028 | Jun 2028
20231026 | CITYWIDE | 096 | HUMAN RESOURCES ADMINISTRATION | HR25EFOY | HRA FACILITIES & EQUIPMENT OUTYEARS FOR UPGRADES | 7 | CONSTRUCTION TO 75% | Dec 2009 | Apr 2010 | Jun 2028 | Oct 2028
20231026 | CITYWIDE | 096 | HUMAN RESOURCES ADMINISTRATION | HR25EFOY | HRA FACILITIES & EQUIPMENT OUTYEARS FOR UPGRADES | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2010 | Jul 2010 | Oct 2028 | Jan 2029
20231026 | CITYWIDE | 096 | HUMAN RESOURCES ADMINISTRATION | HR25EFOY | HRA FACILITIES & EQUIPMENT OUTYEARS FOR UPGRADES | 9 | SUBSTANTIAL COMPLETION | Jul 2010 | Sep 2010 | Jan 2029 | Mar 2029
20231026 | CITYWIDE | 096 | HUMAN RESOURCES ADMINISTRATION | HR25EFOY | HRA FACILITIES & EQUIPMENT OUTYEARS FOR UPGRADES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2010 | Oct 2010 | Mar 2029 | Apr 2029
20231026 | CITYWIDE | 125 | DEPARTMENT FOR THE AGING | AGVARSRCT | REHABILITATION OF VARIOUS SENIOR CENTERS | 1 | DEVELOP SCOPE | Jan 2002 | Mar 2002 | Jan 2027 | Mar 2027
20231026 | CITYWIDE | 125 | DEPARTMENT FOR THE AGING | AGVARSRCT | REHABILITATION OF VARIOUS SENIOR CENTERS | 2 | PRELIMINARY DESIGN | Apr 2002 | Jul 2002 | Apr 2027 | Jul 2027
20231026 | CITYWIDE | 125 | DEPARTMENT FOR THE AGING | AGVARSRCT | REHABILITATION OF VARIOUS SENIOR CENTERS | 3 | FINAL DESIGN | Jul 2002 | Jan 2003 | Jul 2027 | Jan 2028
20231026 | CITYWIDE | 125 | DEPARTMENT FOR THE AGING | AGVARSRCT | REHABILITATION OF VARIOUS SENIOR CENTERS | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2003 | Apr 2003 | Jan 2028 | Apr 2028
20231026 | CITYWIDE | 125 | DEPARTMENT FOR THE AGING | AGVARSRCT | REHABILITATION OF VARIOUS SENIOR CENTERS | 5 | CONSTRUCTION TO 25% | Apr 2003 | Aug 2003 | Apr 2028 | Aug 2028
20231026 | CITYWIDE | 125 | DEPARTMENT FOR THE AGING | AGVARSRCT | REHABILITATION OF VARIOUS SENIOR CENTERS | 6 | CONSTRUCTION TO 50% | Aug 2003 | Dec 2003 | Aug 2028 | Dec 2028
20231026 | CITYWIDE | 125 | DEPARTMENT FOR THE AGING | AGVARSRCT | REHABILITATION OF VARIOUS SENIOR CENTERS | 7 | CONSTRUCTION TO 75% | Dec 2003 | Apr 2004 | Dec 2028 | Apr 2029
20231026 | CITYWIDE | 125 | DEPARTMENT FOR THE AGING | AGVARSRCT | REHABILITATION OF VARIOUS SENIOR CENTERS | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2004 | Jul 2004 | Apr 2029 | Jul 2029
20231026 | CITYWIDE | 125 | DEPARTMENT FOR THE AGING | AGVARSRCT | REHABILITATION OF VARIOUS SENIOR CENTERS | 9 | SUBSTANTIAL COMPLETION | Jul 2004 | Sep 2004 | Jul 2029 | Sep 2029
20231026 | CITYWIDE | 125 | DEPARTMENT FOR THE AGING | AGVARSRCT | REHABILITATION OF VARIOUS SENIOR CENTERS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2004 | Oct 2004 | Sep 2029 | Oct 2029
20231026 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467-EMR | DCA - EMERGENCY CAPITAL FUND FOR DCA | 1 | DESIGN | Apr 2015 | Oct 2015 | Jun 2025 | Sep 2025
20231026 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467-EMR | DCA - EMERGENCY CAPITAL FUND FOR DCA | 2 | BID AWARD AND REGISTER CONTRCT | Oct 2015 | Jan 2016 | Sep 2025 | Sep 2026
20231026 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467-EMR | DCA - EMERGENCY CAPITAL FUND FOR DCA | 3 | CONSTRUCTION | Jan 2016 | Jan 2017 | Sep 2026 | Sep 2027
20231026 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467-EMR | DCA - EMERGENCY CAPITAL FUND FOR DCA | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2017 | Jul 2017 | Sep 2026 | Sep 2027
20231026 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501CRTY | MoMA PS1 - Courtyard Access Renovation | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2025 | Sep 2025
20231026 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501CRTY | MoMA PS1 - Courtyard Access Renovation | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2025 | Jan 2026
20231026 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501CRTY | MoMA PS1 - Courtyard Access Renovation | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2026 | Jul 2026
20231026 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501CRTY | MoMA PS1 - Courtyard Access Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2026 | Oct 2026
20231026 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501CRTY | MoMA PS1 - Courtyard Access Renovation | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2026 | Feb 2027
20231026 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501CRTY | MoMA PS1 - Courtyard Access Renovation | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2027 | Jun 2027
20231026 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501CRTY | MoMA PS1 - Courtyard Access Renovation | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2027 | Oct 2027
20231026 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501CRTY | MoMA PS1 - Courtyard Access Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2027 | Jan 2028
20231026 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501CRTY | MoMA PS1 - Courtyard Access Renovation | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2028 | Mar 2028
20231026 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501CRTY | MoMA PS1 - Courtyard Access Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2028 | Apr 2028
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSBARGE | New York City Ferry Barges | 1 | DESIGN | Jan 2016 | Jun 2018 | Jan 2016 | Jun 2018
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSBARGE | New York City Ferry Barges | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Jun 2018 | Jul 2018 | Jun 2018
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSBARGE | New York City Ferry Barges | 3 | CONSTRUCTION | Jul 2018 | Jun 2021 | Jul 2018 | Jun 2025
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSBARGE | New York City Ferry Barges | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2021 | Jun 2021 | Jul 2025 | Jun 2025
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSBARGE | New York City Ferry Barges | 5 | SUBSTANTIAL COMPLETION | Jul 2021 | Jun 2021 | Jul 2025 | Jun 2025
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSBARGE | New York City Ferry Barges | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Jul 2021 | Jul 2025 | Jul 2025
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSFERRY | New York City Ferry - Ferry Purchase and Upgrade | 1 | DESIGN | Jul 2016 | Jul 2016 | Mar 2019 | Apr 2019
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSFERRY | New York City Ferry - Ferry Purchase and Upgrade | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Apr 2019 | Apr 2019
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSFERRY | New York City Ferry - Ferry Purchase and Upgrade | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Apr 2019 | May 2019
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSFERRY | New York City Ferry - Ferry Purchase and Upgrade | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Jun 2019 | Jun 2019
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSFERRY | New York City Ferry - Ferry Purchase and Upgrade | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Jun 2019 | Jun 2019
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSFERRY | New York City Ferry - Ferry Purchase and Upgrade | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2016 | Jun 2019 | Jun 2026
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFNEIG-H | Neighborhood Fund - Hold | 1 | DESIGN | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFNEIG-H | Neighborhood Fund - Hold | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Aug 2021 | Jul 2021 | Aug 2021
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFNEIG-H | Neighborhood Fund - Hold | 3 | CONSTRUCTION | Aug 2021 | Sep 2021 | Aug 2021 | Sep 2021
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFNEIG-H | Neighborhood Fund - Hold | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Sep 2021 | Sep 2021 | Sep 2021
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFNEIG-H | Neighborhood Fund - Hold | 5 | SUBSTANTIAL COMPLETION | Sep 2021 | Oct 2021 | Sep 2021 | Oct 2021
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFNEIG-H | Neighborhood Fund - Hold | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2021 | Oct 2033 | Oct 2021 | Oct 2033
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFRANEIG | Neighborhood Fund | 1 | DESIGN | Jul 2016 | Jul 2016 | Jul 2016 | Apr 2024
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFRANEIG | Neighborhood Fund | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Apr 2024 | Apr 2024
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFRANEIG | Neighborhood Fund | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Apr 2024 | May 2024
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFRANEIG | Neighborhood Fund | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Jun 2024 | Jun 2024
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFRANEIG | Neighborhood Fund | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Jun 2024 | Jun 2024
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFRANEIG | Neighborhood Fund | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2016 | Jun 2024 | Jun 2029
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFRASEED | SEED Fund Lump Sum | 1 | DESIGN | Jul 2028 | Jul 2028 | Jul 2028 | Jul 2028
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFRASEED | SEED Fund Lump Sum | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2028 | Aug 2028 | Jul 2028 | Aug 2028
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFRASEED | SEED Fund Lump Sum | 3 | CONSTRUCTION | Aug 2028 | Sep 2028 | Aug 2028 | Sep 2028
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFRASEED | SEED Fund Lump Sum | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2028 | Sep 2028 | Sep 2028 | Sep 2028
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFRASEED | SEED Fund Lump Sum | 5 | SUBSTANTIAL COMPLETION | Sep 2028 | Oct 2028 | Sep 2028 | Oct 2028
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFRASEED | SEED Fund Lump Sum | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2028 | Jun 2030 | Oct 2028 | Jun 2030
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | LOWMANHUD | East River Waterfront | 1 | DESIGN | Jan 2005 | Jan 2005 | Aug 2012 | Aug 2014
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | LOWMANHUD | East River Waterfront | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2005 | Feb 2007 | Aug 2014 | May 2016
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | LOWMANHUD | East River Waterfront | 3 | CONSTRUCTION | Feb 2007 | Feb 2007 | Jun 2010 | Jun 2011
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | LOWMANHUD | East River Waterfront | 4 | ORIGINAL EQUIP & FURNISHING | Feb 2007 | Feb 2007 | Jul 2011 | Jun 2011
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | LOWMANHUD | East River Waterfront | 5 | SUBSTANTIAL COMPLETION | Feb 2007 | Feb 2007 | Jul 2011 | Jun 2011
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | LOWMANHUD | East River Waterfront | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2007 | Feb 2007 | May 2014 | Jun 2029
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | NRELUMP | Lump Sum - Asset Management | 1 | DESIGN | Jul 2000 | Jul 2000 | Jul 2000 | Jul 2000
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | NRELUMP | Lump Sum - Asset Management | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2000 | Aug 2000 | Jul 2000 | Aug 2000
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | NRELUMP | Lump Sum - Asset Management | 3 | CONSTRUCTION | Aug 2000 | Jul 2007 | Aug 2000 | Jul 2029
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | NRELUMP | Lump Sum - Asset Management | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2007 | Jul 2007 | Jul 2029 | Jul 2029
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | NRELUMP | Lump Sum - Asset Management | 5 | SUBSTANTIAL COMPLETION | Jul 2007 | Jul 2007 | Jul 2029 | Jul 2029
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | NRELUMP | Lump Sum - Asset Management | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2007 | Jul 2007 | Jul 2029 | Jul 2029
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | RS-PH1 | Raise Shoreline- Phase 1 | 1 | DESIGN | Aug 2019 | Sep 2019 | Aug 2019 | Sep 2019
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | RS-PH1 | Raise Shoreline- Phase 1 | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Oct 2019 | Sep 2019 | Oct 2019
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | RS-PH1 | Raise Shoreline- Phase 1 | 3 | CONSTRUCTION | Oct 2019 | Nov 2019 | Oct 2019 | Nov 2019
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | RS-PH1 | Raise Shoreline- Phase 1 | 4 | ORIGINAL EQUIP & FURNISHING | Nov 2019 | Nov 2019 | Nov 2019 | Nov 2019
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | RS-PH1 | Raise Shoreline- Phase 1 | 5 | SUBSTANTIAL COMPLETION | Nov 2019 | Dec 2019 | Nov 2019 | Dec 2019
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | RS-PH1 | Raise Shoreline- Phase 1 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2025
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | TENANTIMP | Tenant Improvement Fund | 1 | DESIGN | Jul 2017 | Jul 2017 | Mar 2020 | Apr 2020
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | TENANTIMP | Tenant Improvement Fund | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Aug 2017 | Apr 2020 | Apr 2020
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | TENANTIMP | Tenant Improvement Fund | 3 | CONSTRUCTION | Aug 2017 | Sep 2017 | Apr 2020 | May 2020
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | TENANTIMP | Tenant Improvement Fund | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Sep 2017 | Jun 2020 | Jun 2020
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | TENANTIMP | Tenant Improvement Fund | 5 | SUBSTANTIAL COMPLETION | Sep 2017 | Oct 2017 | Jun 2020 | Jun 2020
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | TENANTIMP | Tenant Improvement Fund | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2017 | Oct 2017 | Jun 2020 | Jun 2031
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | WATERLUMP | Lump Sum - Waterfront Improvements | 1 | DESIGN | Jan 2005 | Jan 2005 | Jan 2005 | Jan 2005
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | WATERLUMP | Lump Sum - Waterfront Improvements | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2005 | Feb 2005 | Jan 2005 | Feb 2005
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | WATERLUMP | Lump Sum - Waterfront Improvements | 3 | CONSTRUCTION | Feb 2005 | Jun 2008 | Feb 2005 | Jun 2025
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | WATERLUMP | Lump Sum - Waterfront Improvements | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2008 | Jun 2008 | Jul 2025 | Jun 2025
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | WATERLUMP | Lump Sum - Waterfront Improvements | 5 | SUBSTANTIAL COMPLETION | Jul 2008 | Jun 2008 | Jul 2025 | Jun 2025
20231026 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | WATERLUMP | Lump Sum - Waterfront Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2008 | Jul 2008 | Jul 2025 | Jul 2025
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | CLB-CLINT | Cloudburst project at NYCHA Clinton Houses | 1 | DEVELOP SCOPE | Jun 2027 | Mar 2028 | Jun 2027 | Mar 2028
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | CLB-CLINT | Cloudburst project at NYCHA Clinton Houses | 2 | PRELIMINARY DESIGN | Mar 2028 | Mar 2029 | Mar 2028 | Mar 2029
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | CLB-CLINT | Cloudburst project at NYCHA Clinton Houses | 3 | FINAL DESIGN | Mar 2029 | Sep 2030 | Mar 2029 | Sep 2030
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | CLB-CLINT | Cloudburst project at NYCHA Clinton Houses | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2030 | Jun 2031 | Sep 2030 | Jun 2031
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | CLB-CLINT | Cloudburst project at NYCHA Clinton Houses | 5 | CONSTRUCTION TO 25% | Jun 2031 | Jun 2032 | Jun 2031 | Jun 2032
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | CLB-CLINT | Cloudburst project at NYCHA Clinton Houses | 6 | CONSTRUCTION TO 50% | Jun 2032 | May 2033 | Jun 2032 | May 2033
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | CLB-CLINT | Cloudburst project at NYCHA Clinton Houses | 7 | CONSTRUCTION TO 75% | May 2033 | May 2034 | May 2033 | May 2034
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | CLB-CLINT | Cloudburst project at NYCHA Clinton Houses | 8 | ORIGINAL EQUIP & FURNISHING | May 2034 | Feb 2035 | May 2034 | Feb 2035
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | CLB-CLINT | Cloudburst project at NYCHA Clinton Houses | 9 | SUBSTANTIAL COMPLETION | Feb 2035 | Aug 2035 | Feb 2035 | Aug 2035
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | CLB-CLINT | Cloudburst project at NYCHA Clinton Houses | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2035 | Nov 2035 | Aug 2035 | Nov 2035
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM11IHWH | INSTANTANEOUS HOT WATER HEATERS | 1 | DESIGN | Jan 2011 | Jun 2011 | Dec 2017 | Apr 2018
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM11IHWH | INSTANTANEOUS HOT WATER HEATERS | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2011 | Nov 2011 | May 2018 | Dec 2020
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM11IHWH | INSTANTANEOUS HOT WATER HEATERS | 3 | CONSTRUCTION | Nov 2011 | Nov 2012 | Jan 2020 | Sep 2022
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM11IHWH | INSTANTANEOUS HOT WATER HEATERS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2012 | May 2013 | Jan 2020 | Sep 2022
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM11IHWH | INSTANTANEOUS HOT WATER HEATERS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2012 | May 2013 | Sep 2022 | Apr 2023
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13GCON | GENERAL CONSTRUCTION CITYWIDE | 1 | DESIGN | Jun 2013 | Nov 2013 | Jun 2013 | Nov 2013
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13GCON | GENERAL CONSTRUCTION CITYWIDE | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2013 | Apr 2014 | Nov 2013 | May 2014
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13GCON | GENERAL CONSTRUCTION CITYWIDE | 3 | CONSTRUCTION | Apr 2014 | Apr 2015 | May 2014 | May 2015
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13GCON | GENERAL CONSTRUCTION CITYWIDE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2015 | Oct 2015 | May 2014 | May 2015
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13GCON | GENERAL CONSTRUCTION CITYWIDE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2015 | Oct 2015 | May 2015 | Jan 2027
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13VAEL | CITYWIDE ELEVATOR REPAIRS | 1 | DESIGN | Aug 2012 | Feb 2013 | Dec 2012 | Feb 2014
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13VAEL | CITYWIDE ELEVATOR REPAIRS | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2013 | Jul 2013 | Feb 2014 | Jul 2014
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13VAEL | CITYWIDE ELEVATOR REPAIRS | 3 | CONSTRUCTION | Jul 2013 | Jul 2014 | Aug 2014 | Jul 2015
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13VAEL | CITYWIDE ELEVATOR REPAIRS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2014 | Dec 2014 | Aug 2014 | Jul 2015
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13VAEL | CITYWIDE ELEVATOR REPAIRS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2014 | Dec 2014 | Aug 2015 | Jan 2031
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM14VAUP | Major Renovations-Brickwork and Roofs at Sotomayer Houses | 1 | DESIGN | Jan 2014 | Jun 2014 | Aug 2012 | Jul 2014
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM14VAUP | Major Renovations-Brickwork and Roofs at Sotomayer Houses | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2014 | Nov 2014 | Aug 2014 | May 2015
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM14VAUP | Major Renovations-Brickwork and Roofs at Sotomayer Houses | 3 | CONSTRUCTION | Nov 2014 | Nov 2015 | Jun 2015 | Aug 2019
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM14VAUP | Major Renovations-Brickwork and Roofs at Sotomayer Houses | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2015 | May 2016 | Jun 2015 | Aug 2019
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM14VAUP | Major Renovations-Brickwork and Roofs at Sotomayer Houses | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2015 | May 2016 | Aug 2019 | Mar 2024
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM15HMLS | HOMELESS INITIATIVE | 1 | DESIGN | Oct 2015 | Mar 2016 | Oct 2015 | May 2016
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM15HMLS | HOMELESS INITIATIVE | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2016 | Aug 2016 | May 2016 | Nov 2016
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM15HMLS | HOMELESS INITIATIVE | 3 | CONSTRUCTION | Aug 2016 | Aug 2017 | Nov 2016 | Nov 2019
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM15HMLS | HOMELESS INITIATIVE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2017 | Feb 2018 | Nov 2016 | Nov 2019
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM15HMLS | HOMELESS INITIATIVE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2017 | Feb 2018 | Nov 2019 | Jun 2023
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SLVA | SECURITY INITIATIVES - LIGHTING AT VARIOUS DEVELOPMENTS | 1 | DESIGN | Jan 2015 | Jun 2015 | Jan 2015 | Jun 2015
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SLVA | SECURITY INITIATIVES - LIGHTING AT VARIOUS DEVELOPMENTS | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Nov 2015 | Jul 2015 | Nov 2015
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SLVA | SECURITY INITIATIVES - LIGHTING AT VARIOUS DEVELOPMENTS | 3 | CONSTRUCTION | Nov 2015 | Nov 2016 | Nov 2015 | Nov 2016
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SLVA | SECURITY INITIATIVES - LIGHTING AT VARIOUS DEVELOPMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2016 | May 2017 | Nov 2015 | Nov 2016
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SLVA | SECURITY INITIATIVES - LIGHTING AT VARIOUS DEVELOPMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2016 | May 2017 | Nov 2016 | Apr 2026
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM16FACD | BUILDING FACADES | 1 | DESIGN | Feb 2015 | Aug 2015 | Sep 2015 | Oct 2015
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM16FACD | BUILDING FACADES | 2 | BID AWARD AND REGISTER CONTRCT | Aug 2015 | Jan 2016 | Oct 2015 | Apr 2016
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM16FACD | BUILDING FACADES | 3 | CONSTRUCTION | Jan 2016 | Jan 2017 | Apr 2016 | Jan 2019
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM16FACD | BUILDING FACADES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2017 | Jun 2017 | Apr 2016 | Jan 2019
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM16FACD | BUILDING FACADES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2017 | Jun 2017 | Jan 2019 | Jul 2026
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM16MRVR | ROOF WORK TO PREVENT MOLD AT VARIOUS DEVELOPMENTS | 1 | DESIGN | Apr 2014 | Oct 2014 | Apr 2014 | Oct 2014
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM16MRVR | ROOF WORK TO PREVENT MOLD AT VARIOUS DEVELOPMENTS | 2 | BID AWARD AND REGISTER CONTRCT | Oct 2014 | May 2015 | Oct 2014 | May 2015
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM16MRVR | ROOF WORK TO PREVENT MOLD AT VARIOUS DEVELOPMENTS | 3 | CONSTRUCTION | May 2015 | Dec 2020 | May 2015 | Dec 2020
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM16MRVR | ROOF WORK TO PREVENT MOLD AT VARIOUS DEVELOPMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2021 | Jun 2021 | May 2015 | Dec 2020
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM16MRVR | ROOF WORK TO PREVENT MOLD AT VARIOUS DEVELOPMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2021 | Jun 2021 | Jan 2021 | Dec 2026
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BOIL | MOBLE BOILERS AT VARIOUS NYCHA DEVELOPMENTS | 1 | DESIGN | Jan 2018 | Jun 2018 | Jan 2018 | Jun 2018
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BOIL | MOBLE BOILERS AT VARIOUS NYCHA DEVELOPMENTS | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BOIL | MOBLE BOILERS AT VARIOUS NYCHA DEVELOPMENTS | 3 | CONSTRUCTION | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BOIL | MOBLE BOILERS AT VARIOUS NYCHA DEVELOPMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2018 | Dec 2019
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BOIL | MOBLE BOILERS AT VARIOUS NYCHA DEVELOPMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2019 | Dec 2030
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDCH | CITY HEATING PLANT SCOPE CHANGE | 1 | DESIGN | Jun 2022 | Nov 2022 | Jun 2022 | Nov 2022
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDCH | CITY HEATING PLANT SCOPE CHANGE | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2022 | May 2023 | Nov 2022 | May 2023
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDCH | CITY HEATING PLANT SCOPE CHANGE | 3 | CONSTRUCTION | May 2023 | May 2024 | May 2023 | May 2024
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDCH | CITY HEATING PLANT SCOPE CHANGE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2023 | May 2024
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDCH | CITY HEATING PLANT SCOPE CHANGE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDCP | BUILDING IMPROVEMENTS | 1 | DESIGN | Feb 2018 | Aug 2018 | May 2022 | Nov 2022
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDCP | BUILDING IMPROVEMENTS | 2 | BID AWARD AND REGISTER CONTRCT | Aug 2018 | Jan 2019 | Nov 2022 | May 2023
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDCP | BUILDING IMPROVEMENTS | 3 | CONSTRUCTION | Jan 2019 | Jan 2020 | May 2023 | May 2024
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDCP | BUILDING IMPROVEMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2020 | Jul 2020 | May 2023 | May 2024
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDCP | BUILDING IMPROVEMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2020 | Jul 2020 | May 2024 | May 2026
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDEE | ELEVATOR ESCALATION COST | 1 | DESIGN | Jun 2022 | Nov 2022 | Jun 2022 | Nov 2022
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDEE | ELEVATOR ESCALATION COST | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2022 | May 2023 | Nov 2022 | May 2023
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDEE | ELEVATOR ESCALATION COST | 3 | CONSTRUCTION | May 2023 | May 2024 | May 2023 | May 2024
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDEE | ELEVATOR ESCALATION COST | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2023 | May 2024
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDEE | ELEVATOR ESCALATION COST | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDLC | LEAD ABATEMENT & COMP APRROACH TO MOLD | 1 | DESIGN | Jun 2022 | Nov 2022 | Jun 2022 | Nov 2022
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDLC | LEAD ABATEMENT & COMP APRROACH TO MOLD | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2022 | May 2023 | Nov 2022 | May 2023
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDLC | LEAD ABATEMENT & COMP APRROACH TO MOLD | 3 | CONSTRUCTION | May 2023 | May 2024 | May 2023 | May 2024
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDLC | LEAD ABATEMENT & COMP APRROACH TO MOLD | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2023 | May 2024
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDLC | LEAD ABATEMENT & COMP APRROACH TO MOLD | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDLP | LEAD ABATEMENT (PHASED PROGRAM) | 1 | DESIGN | Jun 2022 | Nov 2022 | Jun 2022 | Nov 2022
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDLP | LEAD ABATEMENT (PHASED PROGRAM) | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2022 | May 2023 | Nov 2022 | May 2023
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDLP | LEAD ABATEMENT (PHASED PROGRAM) | 3 | CONSTRUCTION | May 2023 | May 2024 | May 2023 | May 2024
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDLP | LEAD ABATEMENT (PHASED PROGRAM) | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2023 | May 2024
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDLP | LEAD ABATEMENT (PHASED PROGRAM) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDWM | WASTE MANAGEMENT | 1 | DESIGN | Jun 2022 | Nov 2022 | Jun 2022 | Nov 2022
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDWM | WASTE MANAGEMENT | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2022 | May 2023 | Nov 2022 | May 2023
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDWM | WASTE MANAGEMENT | 3 | CONSTRUCTION | May 2023 | May 2024 | May 2023 | May 2024
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDWM | WASTE MANAGEMENT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2023 | May 2024
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDWM | WASTE MANAGEMENT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CSVA | CONCRETE SLABS AT VARIOUS DEVELOPMENTS | 1 | DESIGN | Mar 2017 | Feb 2018 | Mar 2017 | Feb 2018
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CSVA | CONCRETE SLABS AT VARIOUS DEVELOPMENTS | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2018 | Jun 2018 | Feb 2018 | Jun 2018
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CSVA | CONCRETE SLABS AT VARIOUS DEVELOPMENTS | 3 | CONSTRUCTION | Jun 2018 | Jun 2021 | Jun 2018 | Jun 2021
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CSVA | CONCRETE SLABS AT VARIOUS DEVELOPMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2021 | Dec 2021 | Jun 2018 | Jun 2021
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CSVA | CONCRETE SLABS AT VARIOUS DEVELOPMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2021 | Dec 2021 | Jun 2021 | Jun 2031
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HEAT | HEATING SYSTEM IMPROVEMENTS AT NYCHA DEVELOPMENTS CITYWIDE | 1 | DESIGN | Feb 2018 | Sep 2018 | Feb 2018 | Sep 2018
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HEAT | HEATING SYSTEM IMPROVEMENTS AT NYCHA DEVELOPMENTS CITYWIDE | 2 | BID AWARD AND REGISTER CONTRCT | Oct 2018 | Jul 2019 | Oct 2018 | Jul 2019
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HEAT | HEATING SYSTEM IMPROVEMENTS AT NYCHA DEVELOPMENTS CITYWIDE | 3 | CONSTRUCTION | Aug 2019 | Jul 2020 | Aug 2019 | Jul 2020
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HEAT | HEATING SYSTEM IMPROVEMENTS AT NYCHA DEVELOPMENTS CITYWIDE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Jan 2021 | Aug 2019 | Jul 2020
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HEAT | HEATING SYSTEM IMPROVEMENTS AT NYCHA DEVELOPMENTS CITYWIDE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Jan 2021 | Jul 2020 | Jul 2030
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18IHWH | INSTANTANEOUS HOT WATER HEATERS | 1 | DESIGN | Jun 2018 | Nov 2018 | Jun 2018 | Nov 2018
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18IHWH | INSTANTANEOUS HOT WATER HEATERS | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2018 | Apr 2019 | Nov 2018 | Apr 2019
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18IHWH | INSTANTANEOUS HOT WATER HEATERS | 3 | CONSTRUCTION | Apr 2019 | Apr 2020 | Apr 2019 | Apr 2020
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18IHWH | INSTANTANEOUS HOT WATER HEATERS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2020 | Oct 2020 | Apr 2019 | Apr 2020
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18IHWH | INSTANTANEOUS HOT WATER HEATERS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2020 | Oct 2020 | Apr 2020 | Apr 2025
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PNAP | Gas Risers | 1 | DESIGN | Jan 2018 | Jun 2018 | Jan 2018 | Jun 2018
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PNAP | Gas Risers | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PNAP | Gas Risers | 3 | CONSTRUCTION | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PNAP | Gas Risers | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2018 | Dec 2019
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PNAP | Gas Risers | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2019 | Dec 2030
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RAEX | EXTERNAL COMPACTORS-BULK CRUSHERS | 1 | DESIGN | Jan 2018 | Jun 2018 | Jan 2018 | Jun 2018
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RAEX | EXTERNAL COMPACTORS-BULK CRUSHERS | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RAEX | EXTERNAL COMPACTORS-BULK CRUSHERS | 3 | CONSTRUCTION | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RAEX | EXTERNAL COMPACTORS-BULK CRUSHERS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2018 | Dec 2019
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RAEX | EXTERNAL COMPACTORS-BULK CRUSHERS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2019 | Dec 2026
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RSPL | Citywide Gas Risers, Steam Distribution, Condensate Lines | 1 | DESIGN | Jan 2018 | Jun 2018 | Jan 2018 | Jun 2018
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RSPL | Citywide Gas Risers, Steam Distribution, Condensate Lines | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RSPL | Citywide Gas Risers, Steam Distribution, Condensate Lines | 3 | CONSTRUCTION | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2020
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RSPL | Citywide Gas Risers, Steam Distribution, Condensate Lines | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2018 | Dec 2020
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RSPL | Citywide Gas Risers, Steam Distribution, Condensate Lines | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2020 | Dec 2024
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DGV2 | DIGITAL VAN | 1 | DESIGN | Jan 2018 | Jun 2018 | Jan 2018 | Jun 2018
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DGV2 | DIGITAL VAN | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DGV2 | DIGITAL VAN | 3 | CONSTRUCTION | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DGV2 | DIGITAL VAN | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2018 | Dec 2019
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DGV2 | DIGITAL VAN | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2019 | Dec 2022
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MOCJ | Installation of LED Exterior Lighting Citywide | 1 | DESIGN | Jan 2018 | Jun 2018 | Jan 2018 | Jun 2018
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MOCJ | Installation of LED Exterior Lighting Citywide | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MOCJ | Installation of LED Exterior Lighting Citywide | 3 | CONSTRUCTION | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MOCJ | Installation of LED Exterior Lighting Citywide | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2018 | Dec 2019
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MOCJ | Installation of LED Exterior Lighting Citywide | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2019 | Mar 2028
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20DMSC | SENIOR CENTER RENOVATION- DYCKMAN AND MARBLE HILL | 1 | DESIGN | Sep 2019 | Feb 2020 | Sep 2019 | Feb 2020
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20DMSC | SENIOR CENTER RENOVATION- DYCKMAN AND MARBLE HILL | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Aug 2020 | Feb 2020 | Aug 2020
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20DMSC | SENIOR CENTER RENOVATION- DYCKMAN AND MARBLE HILL | 3 | CONSTRUCTION | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20DMSC | SENIOR CENTER RENOVATION- DYCKMAN AND MARBLE HILL | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2020 | Aug 2021
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20DMSC | SENIOR CENTER RENOVATION- DYCKMAN AND MARBLE HILL | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2021 | Oct 2023
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ECFL | ELLIOTT CHELSEA AND FULTON LIGHTING FOR PARKS | 1 | DESIGN | Sep 2019 | Feb 2020 | Sep 2019 | Feb 2020
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ECFL | ELLIOTT CHELSEA AND FULTON LIGHTING FOR PARKS | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Aug 2020 | Feb 2020 | Aug 2020
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ECFL | ELLIOTT CHELSEA AND FULTON LIGHTING FOR PARKS | 3 | CONSTRUCTION | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ECFL | ELLIOTT CHELSEA AND FULTON LIGHTING FOR PARKS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2020 | Aug 2021
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ECFL | ELLIOTT CHELSEA AND FULTON LIGHTING FOR PARKS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2021 | Feb 2024
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20QWGR | BEAUTIFICATION OF QUEENSBRIDGE HOUSES AND WOODSIDE HOUSES | 1 | DESIGN | Sep 2019 | Feb 2020 | Sep 2019 | Feb 2020
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20QWGR | BEAUTIFICATION OF QUEENSBRIDGE HOUSES AND WOODSIDE HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Aug 2020 | Feb 2020 | Aug 2020
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20QWGR | BEAUTIFICATION OF QUEENSBRIDGE HOUSES AND WOODSIDE HOUSES | 3 | CONSTRUCTION | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20QWGR | BEAUTIFICATION OF QUEENSBRIDGE HOUSES AND WOODSIDE HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2020 | Aug 2021
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20QWGR | BEAUTIFICATION OF QUEENSBRIDGE HOUSES AND WOODSIDE HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2021 | Aug 2024
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WMEX | WASTE MANAGEMENT EXTERIOR COMPACTORS | 1 | DESIGN | Sep 2019 | Feb 2020 | Oct 2020 | Mar 2021
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WMEX | WASTE MANAGEMENT EXTERIOR COMPACTORS | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Aug 2020 | Mar 2021 | Sep 2021
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WMEX | WASTE MANAGEMENT EXTERIOR COMPACTORS | 3 | CONSTRUCTION | Aug 2020 | Aug 2021 | Sep 2021 | Sep 2022
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WMEX | WASTE MANAGEMENT EXTERIOR COMPACTORS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Sep 2021 | Sep 2022
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WMEX | WASTE MANAGEMENT EXTERIOR COMPACTORS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Sep 2022 | Sep 2025
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MCCT | MARCY HOUSES COMMUNITY CENTER TECHNOLOGY UPGRADES | 1 | DESIGN | Jan 2022 | Jun 2022 | Jan 2022 | Jun 2022
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MCCT | MARCY HOUSES COMMUNITY CENTER TECHNOLOGY UPGRADES | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MCCT | MARCY HOUSES COMMUNITY CENTER TECHNOLOGY UPGRADES | 3 | CONSTRUCTION | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MCCT | MARCY HOUSES COMMUNITY CENTER TECHNOLOGY UPGRADES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jun 2024 | Dec 2022 | Dec 2023
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MCCT | MARCY HOUSES COMMUNITY CENTER TECHNOLOGY UPGRADES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM21UWMS | UPGRADED WASTE MANAGEMENT SYSTEM FOR NYCHA PROJECT | 1 | DESIGN | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM21UWMS | UPGRADED WASTE MANAGEMENT SYSTEM FOR NYCHA PROJECT | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM21UWMS | UPGRADED WASTE MANAGEMENT SYSTEM FOR NYCHA PROJECT | 3 | CONSTRUCTION | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM21UWMS | UPGRADED WASTE MANAGEMENT SYSTEM FOR NYCHA PROJECT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2021 | Jun 2022
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM21UWMS | UPGRADED WASTE MANAGEMENT SYSTEM FOR NYCHA PROJECT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM22FACD | BUILDING FACADES | 1 | DESIGN | Jun 2022 | Nov 2022 | Jun 2022 | Nov 2022
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM22FACD | BUILDING FACADES | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2022 | May 2023 | Nov 2022 | May 2023
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM22FACD | BUILDING FACADES | 3 | CONSTRUCTION | May 2023 | May 2024 | May 2023 | May 2024
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM22FACD | BUILDING FACADES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2023 | May 2024
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM22FACD | BUILDING FACADES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM22GISW | GREEN INFRASTRUCTURE AND STORM WATER MANAGEMENT | 1 | DESIGN | Jan 2022 | Jun 2022 | Jan 2022 | Jun 2022
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM22GISW | GREEN INFRASTRUCTURE AND STORM WATER MANAGEMENT | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM22GISW | GREEN INFRASTRUCTURE AND STORM WATER MANAGEMENT | 3 | CONSTRUCTION | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM22GISW | GREEN INFRASTRUCTURE AND STORM WATER MANAGEMENT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jun 2024 | Dec 2022 | Dec 2023
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM22GISW | GREEN INFRASTRUCTURE AND STORM WATER MANAGEMENT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM22GOGR | GOWANUS AND WYCKOFF STATE OF GOOD REPAIR | 1 | DESIGN | Sep 2022 | Feb 2023 | Sep 2022 | Feb 2023
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM22GOGR | GOWANUS AND WYCKOFF STATE OF GOOD REPAIR | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2023 | Aug 2023 | Feb 2023 | Aug 2023
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM22GOGR | GOWANUS AND WYCKOFF STATE OF GOOD REPAIR | 3 | CONSTRUCTION | Aug 2023 | Aug 2024 | Aug 2023 | Aug 2024
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM22GOGR | GOWANUS AND WYCKOFF STATE OF GOOD REPAIR | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2024 | Feb 2025 | Aug 2023 | Aug 2024
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM22GOGR | GOWANUS AND WYCKOFF STATE OF GOOD REPAIR | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM23SCCM | General Construction | 1 | DESIGN | Jun 2024 | Dec 2024 | Jun 2024 | Dec 2024
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM23SCCM | General Construction | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM23SCCM | General Construction | 3 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM23SCCM | General Construction | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Dec 2026 | Jun 2025 | Jun 2026
20231026 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM23SCCM | General Construction | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Dec 2026 | Jun 2026 | Dec 2026
20231026 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CMESECURE | OCME - Agency-wide Physical Security System Upgrades | 1 | DESIGN | Sep 2020 | Mar 2021 | Sep 2023 | Nov 2023
20231026 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CMESECURE | OCME - Agency-wide Physical Security System Upgrades | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2021 | Sep 2021 | Nov 2023 | Dec 2023
20231026 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CMESECURE | OCME - Agency-wide Physical Security System Upgrades | 3 | CONSTRUCTION | Sep 2021 | May 2022 | Dec 2023 | May 2025
20231026 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CMESECURE | OCME - Agency-wide Physical Security System Upgrades | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2022 | Jun 2022 | May 2025 | Jun 2025
20231026 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82VCLIN | EMERGENCY FUNDING FOR VARIOUS CLINICS | 1 | DEVELOP SCOPE | Sep 2005 | Dec 2005 | Jun 2021 | Nov 2021
20231026 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82VCLIN | EMERGENCY FUNDING FOR VARIOUS CLINICS | 2 | PRELIMINARY DESIGN | Dec 2005 | Apr 2006 | Nov 2021 | Dec 2030
20231026 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82VCLIN | EMERGENCY FUNDING FOR VARIOUS CLINICS | 3 | FINAL DESIGN | Apr 2006 | Oct 2006 | Jan 2031 | Jun 2031
20231026 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82VCLIN | EMERGENCY FUNDING FOR VARIOUS CLINICS | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2006 | Jan 2007 | Jan 2031 | Jun 2031
20231026 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82VCLIN | EMERGENCY FUNDING FOR VARIOUS CLINICS | 5 | CONSTRUCTION TO 25% | Jan 2007 | May 2007 | Jan 2031 | Jun 2031
20231026 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82VCLIN | EMERGENCY FUNDING FOR VARIOUS CLINICS | 6 | CONSTRUCTION TO 50% | May 2007 | Sep 2007 | Jan 2031 | Jun 2031
20231026 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82VCLIN | EMERGENCY FUNDING FOR VARIOUS CLINICS | 7 | CONSTRUCTION TO 75% | Sep 2007 | Jan 2008 | Jan 2031 | Jun 2031
20231026 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82VCLIN | EMERGENCY FUNDING FOR VARIOUS CLINICS | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2008 | Apr 2008 | Jan 2031 | Jun 2031
20231026 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82VCLIN | EMERGENCY FUNDING FOR VARIOUS CLINICS | 9 | SUBSTANTIAL COMPLETION | Apr 2008 | May 2008 | Jan 2031 | Jun 2031
20231026 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82VCLIN | EMERGENCY FUNDING FOR VARIOUS CLINICS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2008 | Jun 2008 | Jan 2031 | Jun 2031
20231026 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 02201601 | HHC PRIMARY HEALTH CLINICS | 1 | DESIGN | Dec 2020 | May 2022 | Jan 2026 | Jul 2035
20231026 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 02201602 | UPGRADE IDF AND MDF ROOMS (LAN ENVIRONMENTALS) | 1 | DESIGN | Nov 2017 | Apr 2019 | Dec 2024 | May 2026
20231026 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 02201602 | UPGRADE IDF AND MDF ROOMS (LAN ENVIRONMENTALS) | 2 | CONSTRUCTION | Apr 2019 | Apr 2021 | May 2026 | May 2028
20231026 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 02201602 | UPGRADE IDF AND MDF ROOMS (LAN ENVIRONMENTALS) | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2021 | Jun 2021 | May 2028 | Jul 2028
20231026 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 02202101 | SYSTEM WIDE ELEVATOR DOOR LOCK MONITORING | 1 | DESIGN | Mar 2020 | Jul 2021 | Mar 2020 | Jul 2021
20231026 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 02202101 | SYSTEM WIDE ELEVATOR DOOR LOCK MONITORING | 2 | CONSTRUCTION | Jul 2021 | Jul 2023 | Jul 2021 | Jul 2023
20231026 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 02202101 | SYSTEM WIDE ELEVATOR DOOR LOCK MONITORING | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2029
20231026 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 022021PM | PM/CM Services | 1 | DESIGN | Mar 2021 | Jul 2022 | Jul 2023 | Jul 2023
20231026 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 022021PM | PM/CM Services | 2 | CONSTRUCTION | Jul 2022 | Jul 2024 | Jul 2023 | Jul 2025
20231026 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 022021PM | PM/CM Services | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2024 | Oct 2024 | Jul 2025 | Jun 2027
20231026 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 26202341 | Coney Island: Purchase new Patient Transportation Bus | 1 | DESIGN | Sep 2022 | Mar 2023 | Sep 2022 | Mar 2023
20231026 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 26202341 | Coney Island: Purchase new Patient Transportation Bus | 2 | CONSTRUCTION | Mar 2023 | Dec 2023 | Mar 2023 | Dec 2023
20231026 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | SANDNEW | MISC CORPORATE-WIDE RECONSTRUCTION AS A RESULT OF SANDY | 1 | DESIGN | May 2021 | Sep 2022 | Jul 2021 | Nov 2022
20231026 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | SANDNEW | MISC CORPORATE-WIDE RECONSTRUCTION AS A RESULT OF SANDY | 2 | CONSTRUCTION | Sep 2022 | Sep 2024 | Nov 2022 | Nov 2024
20231026 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | SANDNEW | MISC CORPORATE-WIDE RECONSTRUCTION AS A RESULT OF SANDY | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Jun 2027 | Nov 2024 | Aug 2027
20231026 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | WFF-HHC | HHC Fixture Replacement in City-owned Hospitals | 1 | DEVELOP SCOPE | Jun 2020 | Oct 2020 | Jun 2020 | Oct 2020
20231026 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | WFF-HHC | HHC Fixture Replacement in City-owned Hospitals | 2 | PRELIMINARY DESIGN | Oct 2020 | Apr 2021 | Oct 2020 | Apr 2021
20231026 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | WFF-HHC | HHC Fixture Replacement in City-owned Hospitals | 3 | FINAL DESIGN | Apr 2021 | Oct 2022 | Apr 2021 | Oct 2022
20231026 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | WFF-HHC | HHC Fixture Replacement in City-owned Hospitals | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2022 | Apr 2023 | Oct 2022 | Apr 2023
20231026 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | WFF-HHC | HHC Fixture Replacement in City-owned Hospitals | 5 | CONSTRUCTION TO 25% | Apr 2023 | Jan 2024 | Apr 2023 | Jan 2024
20231026 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | WFF-HHC | HHC Fixture Replacement in City-owned Hospitals | 6 | CONSTRUCTION TO 50% | Jan 2024 | Oct 2024 | Jan 2024 | Oct 2024
20231026 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | WFF-HHC | HHC Fixture Replacement in City-owned Hospitals | 7 | CONSTRUCTION TO 75% | Oct 2024 | Jul 2025 | Oct 2024 | Jul 2025
20231026 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | WFF-HHC | HHC Fixture Replacement in City-owned Hospitals | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | WFF-HHC | HHC Fixture Replacement in City-owned Hospitals | 9 | SUBSTANTIAL COMPLETION | Oct 2025 | Dec 2025 | Oct 2025 | Dec 2025
20231026 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | WFF-HHC | HHC Fixture Replacement in City-owned Hospitals | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2025 | Mar 2026 | Dec 2025 | Mar 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP503 | DEP: Cannonsville Hydroelectric Plant | 1 | DEVELOP SCOPE | Jan 2023 | Sep 2023 | Jan 2023 | Sep 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP503 | DEP: Cannonsville Hydroelectric Plant | 2 | PRELIMINARY DESIGN | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP503 | DEP: Cannonsville Hydroelectric Plant | 3 | FINAL DESIGN | Sep 2024 | Mar 2026 | Sep 2024 | Mar 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP503 | DEP: Cannonsville Hydroelectric Plant | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2026 | Dec 2026 | Mar 2026 | Dec 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP503 | DEP: Cannonsville Hydroelectric Plant | 5 | CONSTRUCTION TO 25% | Dec 2026 | Dec 2027 | Dec 2026 | Dec 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP503 | DEP: Cannonsville Hydroelectric Plant | 6 | CONSTRUCTION TO 50% | Dec 2027 | Nov 2028 | Dec 2027 | Nov 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP503 | DEP: Cannonsville Hydroelectric Plant | 7 | CONSTRUCTION TO 75% | Nov 2028 | Nov 2029 | Nov 2028 | Nov 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP503 | DEP: Cannonsville Hydroelectric Plant | 8 | ORIGINAL EQUIP & FURNISHING | Nov 2029 | Aug 2030 | Nov 2029 | Aug 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP503 | DEP: Cannonsville Hydroelectric Plant | 9 | SUBSTANTIAL COMPLETION | Aug 2030 | Feb 2031 | Aug 2030 | Feb 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP503 | DEP: Cannonsville Hydroelectric Plant | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2031 | May 2031 | Feb 2031 | May 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP701 | DEP- DEMAND CONTROLLED VENTILATION UPGRADE | 1 | DEVELOP SCOPE | Jul 2019 | Jun 2020 | Jul 2022 | Jun 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AGRI-18 | FAD 18-22 WAP AND FORESTRY | 1 | DEVELOP SCOPE | Jun 2018 | Mar 2019 | Jun 2018 | Mar 2019
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AGRI-18 | FAD 18-22 WAP AND FORESTRY | 2 | PRELIMINARY DESIGN | Mar 2019 | Mar 2020 | Mar 2019 | Mar 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AGRI-18 | FAD 18-22 WAP AND FORESTRY | 3 | FINAL DESIGN | Mar 2020 | Aug 2021 | Mar 2020 | Aug 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AGRI-18 | FAD 18-22 WAP AND FORESTRY | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2021 | May 2022 | Aug 2021 | May 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AGRI-18 | FAD 18-22 WAP AND FORESTRY | 5 | CONSTRUCTION TO 25% | May 2022 | May 2023 | May 2022 | May 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AGRI-18 | FAD 18-22 WAP AND FORESTRY | 6 | CONSTRUCTION TO 50% | May 2023 | May 2024 | May 2023 | May 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AGRI-18 | FAD 18-22 WAP AND FORESTRY | 7 | CONSTRUCTION TO 75% | May 2024 | May 2025 | May 2024 | May 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AGRI-18 | FAD 18-22 WAP AND FORESTRY | 8 | ORIGINAL EQUIP & FURNISHING | May 2025 | Feb 2026 | May 2025 | Feb 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AGRI-18 | FAD 18-22 WAP AND FORESTRY | 9 | SUBSTANTIAL COMPLETION | Feb 2026 | Aug 2026 | Feb 2026 | Aug 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AGRI-18 | FAD 18-22 WAP AND FORESTRY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2026 | Oct 2026 | Aug 2026 | Oct 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON2 | Air Monitoring Analysis | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Aug 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON2 | Air Monitoring Analysis | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON2 | Air Monitoring Analysis | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON2 | Air Monitoring Analysis | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON2 | Air Monitoring Analysis | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON2 | Air Monitoring Analysis | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2022 | May 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON2 | Air Monitoring Analysis | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2022 | Sep 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON2 | Air Monitoring Analysis | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON2 | Air Monitoring Analysis | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2022 | Feb 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON2 | Air Monitoring Analysis | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Feb 2023 | Mar 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON2 | Air Monitoring Analysis | 11 | PRE-CONSTRUCTION MOBILIZATION | Mar 2023 | Mar 2024 | Mar 2023 | Mar 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON2 | Air Monitoring Analysis | 12 | ON-SITE CONSTRUCTION MANAGEMEN | Mar 2024 | Feb 2030 | Mar 2024 | Feb 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON2 | Air Monitoring Analysis | 13 | POST-CONSTRUCTION CLOSE-OUT | Feb 2030 | Feb 2031 | Feb 2030 | Feb 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ASB-REM | Asbestos Removal | 1 | DEVELOP SCOPE | Mar 2013 | Jun 2013 | Aug 2014 | Dec 2014
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ASB-REM | Asbestos Removal | 2 | PRELIMINARY DESIGN | Jun 2013 | Oct 2013 | Dec 2014 | Jun 2015
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ASB-REM | Asbestos Removal | 3 | FINAL DESIGN | Oct 2013 | Apr 2014 | Jun 2015 | Dec 2016
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ASB-REM | Asbestos Removal | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2014 | Jul 2014 | Dec 2016 | Jun 2017
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ASB-REM | Asbestos Removal | 5 | CONSTRUCTION TO 25% | Jul 2014 | Nov 2014 | Jun 2017 | Mar 2018
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ASB-REM | Asbestos Removal | 6 | CONSTRUCTION TO 50% | Nov 2014 | Mar 2015 | Mar 2018 | Jan 2019
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ASB-REM | Asbestos Removal | 7 | CONSTRUCTION TO 75% | Mar 2015 | Jul 2015 | Jan 2019 | Oct 2019
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ASB-REM | Asbestos Removal | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2015 | Oct 2015 | Oct 2019 | Jan 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ASB-REM | Asbestos Removal | 9 | SUBSTANTIAL COMPLETION | Oct 2015 | Dec 2015 | Jan 2020 | Mar 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ASB-REM | Asbestos Removal | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2015 | Jan 2016 | Mar 2020 | Jun 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ASB-REM | Asbestos Removal | 11 | PRE-CONSTRUCTION MOBILIZATION | Dec 2015 | Jan 2016 | Jun 2020 | May 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ASB-REM | Asbestos Removal | 12 | ON-SITE CONSTRUCTION MANAGEMEN | Dec 2015 | Jan 2016 | Jun 2021 | Apr 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ASB-REM | Asbestos Removal | 13 | POST-CONSTRUCTION CLOSE-OUT | Dec 2015 | Jan 2016 | May 2027 | Apr 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | BEDC-JOCS | JOB ORDER CONTRACTING WORK TO SUPPLEMENT BEDC CAPITAL CONSTR | 1 | DEVELOP SCOPE | Jun 2020 | Feb 2021 | Jun 2020 | Feb 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | BEDC-JOCS | JOB ORDER CONTRACTING WORK TO SUPPLEMENT BEDC CAPITAL CONSTR | 2 | PRELIMINARY DESIGN | Feb 2021 | Feb 2022 | Feb 2021 | Feb 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | BEDC-JOCS | JOB ORDER CONTRACTING WORK TO SUPPLEMENT BEDC CAPITAL CONSTR | 3 | FINAL DESIGN | Feb 2022 | Aug 2023 | Feb 2022 | Aug 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | BEDC-JOCS | JOB ORDER CONTRACTING WORK TO SUPPLEMENT BEDC CAPITAL CONSTR | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2023 | May 2024 | Aug 2023 | May 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | BEDC-JOCS | JOB ORDER CONTRACTING WORK TO SUPPLEMENT BEDC CAPITAL CONSTR | 5 | CONSTRUCTION TO 25% | May 2024 | May 2025 | May 2024 | May 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | BEDC-JOCS | JOB ORDER CONTRACTING WORK TO SUPPLEMENT BEDC CAPITAL CONSTR | 6 | CONSTRUCTION TO 50% | May 2025 | Apr 2026 | May 2025 | Apr 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | BEDC-JOCS | JOB ORDER CONTRACTING WORK TO SUPPLEMENT BEDC CAPITAL CONSTR | 7 | CONSTRUCTION TO 75% | May 2026 | Apr 2027 | May 2026 | Apr 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | BEDC-JOCS | JOB ORDER CONTRACTING WORK TO SUPPLEMENT BEDC CAPITAL CONSTR | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2027 | Jan 2028 | Apr 2027 | Jan 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | BEDC-JOCS | JOB ORDER CONTRACTING WORK TO SUPPLEMENT BEDC CAPITAL CONSTR | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Jul 2032 | Jan 2028 | Jul 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | BEDC-JOCS | JOB ORDER CONTRACTING WORK TO SUPPLEMENT BEDC CAPITAL CONSTR | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2032 | Oct 2032 | Jul 2032 | Oct 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C519 | MODIFICATION OF CHAMBERS AT HILLVIEW | 1 | DEVELOP SCOPE | May 1996 | Feb 1997 | Jun 2007 | Feb 2008
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C519 | MODIFICATION OF CHAMBERS AT HILLVIEW | 2 | PRELIMINARY DESIGN | Feb 1997 | Feb 1998 | Feb 2008 | Feb 2009
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C519 | MODIFICATION OF CHAMBERS AT HILLVIEW | 3 | FINAL DESIGN | Feb 1998 | Jul 1999 | Feb 2009 | Aug 2010
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C519 | MODIFICATION OF CHAMBERS AT HILLVIEW | 4 | BID AWARD AND REGISTER CONTRCT | Jul 1999 | Apr 2000 | Aug 2010 | May 2011
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C519 | MODIFICATION OF CHAMBERS AT HILLVIEW | 5 | CONSTRUCTION TO 25% | Apr 2000 | Apr 2001 | May 2011 | May 2012
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C519 | MODIFICATION OF CHAMBERS AT HILLVIEW | 6 | CONSTRUCTION TO 50% | Apr 2001 | Apr 2002 | May 2012 | Apr 2013
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C519 | MODIFICATION OF CHAMBERS AT HILLVIEW | 7 | CONSTRUCTION TO 75% | Apr 2002 | Apr 2003 | Apr 2013 | Apr 2014
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C519 | MODIFICATION OF CHAMBERS AT HILLVIEW | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2003 | Jan 2004 | Apr 2014 | Jan 2015
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C519 | MODIFICATION OF CHAMBERS AT HILLVIEW | 9 | SUBSTANTIAL COMPLETION | Jan 2004 | Jul 2004 | Jan 2015 | Jul 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C519 | MODIFICATION OF CHAMBERS AT HILLVIEW | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2004 | Sep 2004 | Jul 2027 | Oct 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAN-HYDRO | Development of Hydroelectric Cannonsville Dam. incl P'wrhse | 1 | DEVELOP SCOPE | Jun 2018 | Feb 2019 | Jun 2021 | Feb 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAN-HYDRO | Development of Hydroelectric Cannonsville Dam. incl P'wrhse | 2 | PRELIMINARY DESIGN | Feb 2019 | Feb 2020 | Feb 2022 | Feb 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAN-HYDRO | Development of Hydroelectric Cannonsville Dam. incl P'wrhse | 3 | FINAL DESIGN | Feb 2020 | Aug 2021 | Feb 2023 | Aug 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAN-HYDRO | Development of Hydroelectric Cannonsville Dam. incl P'wrhse | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2021 | May 2022 | Aug 2024 | May 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAN-HYDRO | Development of Hydroelectric Cannonsville Dam. incl P'wrhse | 5 | CONSTRUCTION TO 25% | May 2022 | May 2023 | May 2025 | May 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAN-HYDRO | Development of Hydroelectric Cannonsville Dam. incl P'wrhse | 6 | CONSTRUCTION TO 50% | May 2023 | Apr 2024 | May 2026 | Apr 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAN-HYDRO | Development of Hydroelectric Cannonsville Dam. incl P'wrhse | 7 | CONSTRUCTION TO 75% | Apr 2024 | Apr 2025 | May 2027 | Apr 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAN-HYDRO | Development of Hydroelectric Cannonsville Dam. incl P'wrhse | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2025 | Jan 2026 | Apr 2028 | Jan 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAN-HYDRO | Development of Hydroelectric Cannonsville Dam. incl P'wrhse | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Jul 2026 | Jan 2029 | Jul 2033
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAN-HYDRO | Development of Hydroelectric Cannonsville Dam. incl P'wrhse | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2026 | Oct 2026 | Jul 2033 | Oct 2033
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-212 | SCHOHARIE RESERVOIR/GILBOA DAM AND INTAKE/OUTLET CHAMBER | 1 | DEVELOP SCOPE | Mar 2004 | Dec 2004 | May 2015 | Feb 2016
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-212 | SCHOHARIE RESERVOIR/GILBOA DAM AND INTAKE/OUTLET CHAMBER | 2 | PRELIMINARY DESIGN | Dec 2004 | Dec 2005 | Feb 2016 | Feb 2017
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-212 | SCHOHARIE RESERVOIR/GILBOA DAM AND INTAKE/OUTLET CHAMBER | 3 | FINAL DESIGN | Dec 2005 | May 2007 | Feb 2017 | Aug 2018
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-212 | SCHOHARIE RESERVOIR/GILBOA DAM AND INTAKE/OUTLET CHAMBER | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2007 | Feb 2008 | Aug 2018 | Apr 2019
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-212 | SCHOHARIE RESERVOIR/GILBOA DAM AND INTAKE/OUTLET CHAMBER | 5 | CONSTRUCTION TO 25% | Feb 2008 | Feb 2009 | May 2019 | Apr 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-212 | SCHOHARIE RESERVOIR/GILBOA DAM AND INTAKE/OUTLET CHAMBER | 6 | CONSTRUCTION TO 50% | Feb 2009 | Feb 2010 | Apr 2020 | Apr 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-212 | SCHOHARIE RESERVOIR/GILBOA DAM AND INTAKE/OUTLET CHAMBER | 7 | CONSTRUCTION TO 75% | Feb 2010 | Feb 2011 | Apr 2021 | Apr 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-212 | SCHOHARIE RESERVOIR/GILBOA DAM AND INTAKE/OUTLET CHAMBER | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2011 | Nov 2011 | Apr 2022 | Jan 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-212 | SCHOHARIE RESERVOIR/GILBOA DAM AND INTAKE/OUTLET CHAMBER | 9 | SUBSTANTIAL COMPLETION | Nov 2011 | May 2012 | Jan 2023 | Jul 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-212 | SCHOHARIE RESERVOIR/GILBOA DAM AND INTAKE/OUTLET CHAMBER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2012 | Aug 2012 | Jul 2031 | Oct 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-213 | ASHOKAN RESERVOIR/OLIVE BRIDGE DAM & UPPER/LOWER OUTLET& SCR | 1 | DEVELOP SCOPE | Jun 2008 | Mar 2009 | Jun 2008 | Mar 2009
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-213 | ASHOKAN RESERVOIR/OLIVE BRIDGE DAM & UPPER/LOWER OUTLET& SCR | 2 | PRELIMINARY DESIGN | Mar 2009 | Mar 2010 | Mar 2009 | Mar 2010
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-213 | ASHOKAN RESERVOIR/OLIVE BRIDGE DAM & UPPER/LOWER OUTLET& SCR | 3 | FINAL DESIGN | Mar 2010 | Aug 2011 | Mar 2010 | Aug 2011
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-213 | ASHOKAN RESERVOIR/OLIVE BRIDGE DAM & UPPER/LOWER OUTLET& SCR | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2011 | May 2012 | Aug 2011 | May 2012
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-213 | ASHOKAN RESERVOIR/OLIVE BRIDGE DAM & UPPER/LOWER OUTLET& SCR | 5 | CONSTRUCTION TO 25% | May 2012 | May 2013 | May 2012 | May 2013
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-213 | ASHOKAN RESERVOIR/OLIVE BRIDGE DAM & UPPER/LOWER OUTLET& SCR | 6 | CONSTRUCTION TO 50% | May 2013 | May 2014 | May 2013 | May 2014
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-213 | ASHOKAN RESERVOIR/OLIVE BRIDGE DAM & UPPER/LOWER OUTLET& SCR | 7 | CONSTRUCTION TO 75% | May 2014 | May 2015 | May 2014 | May 2015
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-213 | ASHOKAN RESERVOIR/OLIVE BRIDGE DAM & UPPER/LOWER OUTLET& SCR | 8 | ORIGINAL EQUIP & FURNISHING | May 2015 | Feb 2016 | May 2015 | Feb 2016
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-213 | ASHOKAN RESERVOIR/OLIVE BRIDGE DAM & UPPER/LOWER OUTLET& SCR | 9 | SUBSTANTIAL COMPLETION | Feb 2016 | Aug 2016 | Feb 2016 | Jul 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-213 | ASHOKAN RESERVOIR/OLIVE BRIDGE DAM & UPPER/LOWER OUTLET& SCR | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2016 | Oct 2016 | Jul 2028 | Oct 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-252 | REPLACEMENT OF ESOPUS AND ROUTE 28A RAILROAD BRIDGES | 1 | DEVELOP SCOPE | Dec 2008 | Sep 2009 | Jul 2017 | Mar 2018
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-252 | REPLACEMENT OF ESOPUS AND ROUTE 28A RAILROAD BRIDGES | 2 | PRELIMINARY DESIGN | Sep 2009 | Sep 2010 | Mar 2018 | Mar 2019
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-252 | REPLACEMENT OF ESOPUS AND ROUTE 28A RAILROAD BRIDGES | 3 | FINAL DESIGN | Sep 2010 | Feb 2012 | Mar 2019 | Sep 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-252 | REPLACEMENT OF ESOPUS AND ROUTE 28A RAILROAD BRIDGES | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2012 | Nov 2012 | Sep 2020 | Jun 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-252 | REPLACEMENT OF ESOPUS AND ROUTE 28A RAILROAD BRIDGES | 5 | CONSTRUCTION TO 25% | Nov 2012 | Nov 2013 | Jun 2021 | Jun 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-252 | REPLACEMENT OF ESOPUS AND ROUTE 28A RAILROAD BRIDGES | 6 | CONSTRUCTION TO 50% | Nov 2013 | Nov 2014 | Jun 2022 | May 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-252 | REPLACEMENT OF ESOPUS AND ROUTE 28A RAILROAD BRIDGES | 7 | CONSTRUCTION TO 75% | Nov 2014 | Nov 2015 | May 2023 | May 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-252 | REPLACEMENT OF ESOPUS AND ROUTE 28A RAILROAD BRIDGES | 8 | ORIGINAL EQUIP & FURNISHING | Nov 2015 | Aug 2016 | May 2024 | Feb 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-252 | REPLACEMENT OF ESOPUS AND ROUTE 28A RAILROAD BRIDGES | 9 | SUBSTANTIAL COMPLETION | Aug 2016 | Jan 2017 | Feb 2025 | Aug 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-252 | REPLACEMENT OF ESOPUS AND ROUTE 28A RAILROAD BRIDGES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2017 | May 2017 | Aug 2025 | Nov 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-367 | Reconstruction of Roads at Ashokan Reservoir | 1 | DEVELOP SCOPE | Jun 2023 | Feb 2024 | Jun 2023 | Feb 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-367 | Reconstruction of Roads at Ashokan Reservoir | 2 | PRELIMINARY DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-367 | Reconstruction of Roads at Ashokan Reservoir | 3 | FINAL DESIGN | Feb 2025 | Aug 2026 | Feb 2025 | Aug 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-367 | Reconstruction of Roads at Ashokan Reservoir | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2026 | May 2027 | Aug 2026 | May 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-367 | Reconstruction of Roads at Ashokan Reservoir | 5 | CONSTRUCTION TO 25% | May 2027 | May 2028 | May 2027 | May 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-367 | Reconstruction of Roads at Ashokan Reservoir | 6 | CONSTRUCTION TO 50% | May 2028 | Apr 2029 | May 2028 | Apr 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-367 | Reconstruction of Roads at Ashokan Reservoir | 7 | CONSTRUCTION TO 75% | Apr 2029 | Apr 2030 | Apr 2029 | Apr 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-367 | Reconstruction of Roads at Ashokan Reservoir | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2030 | Jan 2031 | Apr 2030 | Jan 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-367 | Reconstruction of Roads at Ashokan Reservoir | 9 | SUBSTANTIAL COMPLETION | Jan 2031 | Jul 2031 | Jan 2031 | Jul 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-367 | Reconstruction of Roads at Ashokan Reservoir | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2031 | Oct 2031 | Jul 2031 | Oct 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-379 | Bureau of Police & Security Academy Renovation, Kingston | 1 | DEVELOP SCOPE | Jul 2017 | Mar 2018 | Jul 2017 | Mar 2018
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-379 | Bureau of Police & Security Academy Renovation, Kingston | 2 | PRELIMINARY DESIGN | Mar 2018 | Mar 2019 | Mar 2018 | Mar 2019
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-379 | Bureau of Police & Security Academy Renovation, Kingston | 3 | FINAL DESIGN | Mar 2019 | Sep 2020 | Mar 2019 | Sep 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-379 | Bureau of Police & Security Academy Renovation, Kingston | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2020 | Jun 2021 | Sep 2020 | Jun 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-379 | Bureau of Police & Security Academy Renovation, Kingston | 5 | CONSTRUCTION TO 25% | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-379 | Bureau of Police & Security Academy Renovation, Kingston | 6 | CONSTRUCTION TO 50% | Jun 2022 | May 2023 | Jun 2022 | May 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-379 | Bureau of Police & Security Academy Renovation, Kingston | 7 | CONSTRUCTION TO 75% | May 2023 | May 2024 | May 2023 | May 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-379 | Bureau of Police & Security Academy Renovation, Kingston | 8 | ORIGINAL EQUIP & FURNISHING | May 2024 | Feb 2025 | May 2024 | Feb 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-379 | Bureau of Police & Security Academy Renovation, Kingston | 9 | SUBSTANTIAL COMPLETION | Feb 2025 | Aug 2025 | Feb 2025 | Aug 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-379 | Bureau of Police & Security Academy Renovation, Kingston | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2025 | Nov 2025 | Aug 2025 | Nov 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-390 | Schoharie Reservoir road improvement- NYS Rt. 990V | 1 | DEVELOP SCOPE | Feb 2010 | May 2010 | Jun 2011 | Mar 2012
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-390 | Schoharie Reservoir road improvement- NYS Rt. 990V | 2 | PRELIMINARY DESIGN | May 2010 | Aug 2010 | Mar 2012 | Mar 2013
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-390 | Schoharie Reservoir road improvement- NYS Rt. 990V | 3 | FINAL DESIGN | Aug 2010 | Feb 2011 | Mar 2013 | Sep 2014
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-390 | Schoharie Reservoir road improvement- NYS Rt. 990V | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2011 | May 2011 | Sep 2014 | Jun 2015
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-390 | Schoharie Reservoir road improvement- NYS Rt. 990V | 5 | CONSTRUCTION TO 25% | May 2011 | Sep 2011 | Jun 2015 | Jun 2016
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-390 | Schoharie Reservoir road improvement- NYS Rt. 990V | 6 | CONSTRUCTION TO 50% | Sep 2011 | Jan 2012 | Jun 2016 | May 2017
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-390 | Schoharie Reservoir road improvement- NYS Rt. 990V | 7 | CONSTRUCTION TO 75% | Jan 2012 | May 2012 | May 2017 | May 2018
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-390 | Schoharie Reservoir road improvement- NYS Rt. 990V | 8 | ORIGINAL EQUIP & FURNISHING | May 2012 | Aug 2012 | May 2018 | Feb 2019
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-390 | Schoharie Reservoir road improvement- NYS Rt. 990V | 9 | SUBSTANTIAL COMPLETION | Aug 2012 | Oct 2012 | Feb 2019 | Aug 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-390 | Schoharie Reservoir road improvement- NYS Rt. 990V | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2012 | Nov 2012 | Aug 2027 | Nov 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-399 | CA Hudson River Drainage Chamber | 1 | DEVELOP SCOPE | Mar 2011 | Nov 2011 | Mar 2011 | Nov 2011
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-399 | CA Hudson River Drainage Chamber | 2 | PRELIMINARY DESIGN | Nov 2011 | Nov 2012 | Nov 2011 | Nov 2012
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-399 | CA Hudson River Drainage Chamber | 3 | FINAL DESIGN | Nov 2012 | May 2014 | Nov 2012 | May 2014
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-399 | CA Hudson River Drainage Chamber | 4 | BID AWARD AND REGISTER CONTRCT | May 2014 | Feb 2015 | May 2014 | Feb 2015
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-399 | CA Hudson River Drainage Chamber | 5 | CONSTRUCTION TO 25% | Feb 2015 | Feb 2016 | Feb 2015 | Feb 2016
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-399 | CA Hudson River Drainage Chamber | 6 | CONSTRUCTION TO 50% | Feb 2016 | Jan 2017 | Feb 2016 | Jan 2017
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-399 | CA Hudson River Drainage Chamber | 7 | CONSTRUCTION TO 75% | Jan 2017 | Jan 2018 | Jan 2017 | Jan 2018
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-399 | CA Hudson River Drainage Chamber | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2018 | Oct 2018 | Jan 2018 | Oct 2018
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-399 | CA Hudson River Drainage Chamber | 9 | SUBSTANTIAL COMPLETION | Oct 2018 | Apr 2019 | Oct 2018 | Apr 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-399 | CA Hudson River Drainage Chamber | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2019 | Jul 2019 | Apr 2027 | Jul 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-427 | POOR FARM ARCH BRIDGE RECONSTRUCTION | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Sep 2022 | Dec 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-427 | POOR FARM ARCH BRIDGE RECONSTRUCTION | 2 | PRELIMINARY DESIGN | Sep 2015 | Jan 2016 | Dec 2022 | Apr 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-427 | POOR FARM ARCH BRIDGE RECONSTRUCTION | 3 | FINAL DESIGN | Jan 2016 | Jul 2016 | Apr 2023 | Oct 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-427 | POOR FARM ARCH BRIDGE RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Oct 2016 | Oct 2023 | Jan 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-427 | POOR FARM ARCH BRIDGE RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | Oct 2016 | Feb 2017 | Jan 2024 | May 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-427 | POOR FARM ARCH BRIDGE RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | Feb 2017 | Jun 2017 | May 2024 | Sep 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-427 | POOR FARM ARCH BRIDGE RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | Jun 2017 | Oct 2017 | Sep 2024 | Jan 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-427 | POOR FARM ARCH BRIDGE RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2017 | Jan 2018 | Jan 2025 | Apr 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-427 | POOR FARM ARCH BRIDGE RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | Jan 2018 | Mar 2018 | Apr 2025 | Jun 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-427 | POOR FARM ARCH BRIDGE RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2018 | Apr 2018 | Jun 2025 | Jul 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-431 | CATSKILL AQUEDUCT RECONST.-KENSICO TO HILVIEW | 1 | DEVELOP SCOPE | Jun 2015 | Sep 2015 | Jun 2015 | Mar 2016
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-431 | CATSKILL AQUEDUCT RECONST.-KENSICO TO HILVIEW | 2 | PRELIMINARY DESIGN | Sep 2015 | Jan 2016 | Mar 2016 | Mar 2017
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-431 | CATSKILL AQUEDUCT RECONST.-KENSICO TO HILVIEW | 3 | FINAL DESIGN | Jan 2016 | Jul 2016 | Mar 2017 | Sep 2018
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-431 | CATSKILL AQUEDUCT RECONST.-KENSICO TO HILVIEW | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Oct 2016 | Sep 2018 | Jun 2019
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-431 | CATSKILL AQUEDUCT RECONST.-KENSICO TO HILVIEW | 5 | CONSTRUCTION TO 25% | Oct 2016 | Feb 2017 | Jun 2019 | Jun 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-431 | CATSKILL AQUEDUCT RECONST.-KENSICO TO HILVIEW | 6 | CONSTRUCTION TO 50% | Feb 2017 | Jun 2017 | Jun 2020 | May 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-431 | CATSKILL AQUEDUCT RECONST.-KENSICO TO HILVIEW | 7 | CONSTRUCTION TO 75% | Jun 2017 | Oct 2017 | May 2021 | May 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-431 | CATSKILL AQUEDUCT RECONST.-KENSICO TO HILVIEW | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2017 | Jan 2018 | May 2022 | Feb 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-431 | CATSKILL AQUEDUCT RECONST.-KENSICO TO HILVIEW | 9 | SUBSTANTIAL COMPLETION | Jan 2018 | Mar 2018 | Feb 2023 | Aug 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-431 | CATSKILL AQUEDUCT RECONST.-KENSICO TO HILVIEW | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2018 | Apr 2018 | Aug 2031 | Nov 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-452 | WOH Catskill Acqueduct Chambers Rehab & Restoration | 1 | DEVELOP SCOPE | Jul 2019 | Mar 2020 | Jul 2019 | Mar 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-452 | WOH Catskill Acqueduct Chambers Rehab & Restoration | 2 | PRELIMINARY DESIGN | Mar 2020 | Mar 2021 | Mar 2020 | Mar 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-452 | WOH Catskill Acqueduct Chambers Rehab & Restoration | 3 | FINAL DESIGN | Mar 2021 | Sep 2022 | Mar 2021 | Sep 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-452 | WOH Catskill Acqueduct Chambers Rehab & Restoration | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2022 | Jun 2023 | Sep 2022 | Jun 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-452 | WOH Catskill Acqueduct Chambers Rehab & Restoration | 5 | CONSTRUCTION TO 25% | Jun 2023 | Jun 2024 | Jun 2023 | Jun 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-452 | WOH Catskill Acqueduct Chambers Rehab & Restoration | 6 | CONSTRUCTION TO 50% | Jun 2024 | May 2025 | Jun 2024 | May 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-452 | WOH Catskill Acqueduct Chambers Rehab & Restoration | 7 | CONSTRUCTION TO 75% | May 2025 | May 2026 | May 2025 | May 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-452 | WOH Catskill Acqueduct Chambers Rehab & Restoration | 8 | ORIGINAL EQUIP & FURNISHING | May 2026 | Feb 2027 | May 2026 | Feb 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-452 | WOH Catskill Acqueduct Chambers Rehab & Restoration | 9 | SUBSTANTIAL COMPLETION | Feb 2027 | Aug 2027 | Feb 2027 | Aug 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-452 | WOH Catskill Acqueduct Chambers Rehab & Restoration | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2027 | Nov 2027 | Aug 2027 | Nov 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-454 | Reconstruction of Grand Gorge & Tannersville WWTPs | 1 | DEVELOP SCOPE | Jun 2018 | Mar 2019 | Jun 2018 | Mar 2019
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-454 | Reconstruction of Grand Gorge & Tannersville WWTPs | 2 | PRELIMINARY DESIGN | Mar 2019 | Mar 2020 | Mar 2019 | Mar 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-454 | Reconstruction of Grand Gorge & Tannersville WWTPs | 3 | FINAL DESIGN | Mar 2020 | Sep 2021 | Mar 2020 | Sep 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-454 | Reconstruction of Grand Gorge & Tannersville WWTPs | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2021 | Jun 2022 | Sep 2021 | Jun 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-454 | Reconstruction of Grand Gorge & Tannersville WWTPs | 5 | CONSTRUCTION TO 25% | Jun 2022 | Jun 2023 | Jun 2022 | Jun 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-454 | Reconstruction of Grand Gorge & Tannersville WWTPs | 6 | CONSTRUCTION TO 50% | Jun 2023 | May 2024 | Jun 2023 | May 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-454 | Reconstruction of Grand Gorge & Tannersville WWTPs | 7 | CONSTRUCTION TO 75% | May 2024 | May 2025 | May 2024 | May 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-454 | Reconstruction of Grand Gorge & Tannersville WWTPs | 8 | ORIGINAL EQUIP & FURNISHING | May 2025 | Feb 2026 | May 2025 | Feb 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-454 | Reconstruction of Grand Gorge & Tannersville WWTPs | 9 | SUBSTANTIAL COMPLETION | Feb 2026 | Aug 2026 | Feb 2026 | Aug 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-454 | Reconstruction of Grand Gorge & Tannersville WWTPs | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2026 | Nov 2026 | Aug 2026 | Nov 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-475 | GILBOA HLO | 1 | DEVELOP SCOPE | Jun 2019 | Mar 2020 | Jun 2019 | Mar 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-475 | GILBOA HLO | 2 | PRELIMINARY DESIGN | Mar 2020 | Mar 2021 | Mar 2020 | Mar 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-475 | GILBOA HLO | 3 | FINAL DESIGN | Mar 2021 | Sep 2022 | Mar 2021 | Sep 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-475 | GILBOA HLO | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2022 | Jun 2023 | Sep 2022 | Jun 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-475 | GILBOA HLO | 5 | CONSTRUCTION TO 25% | Jun 2023 | Jun 2024 | Jun 2023 | Jun 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-475 | GILBOA HLO | 6 | CONSTRUCTION TO 50% | Jun 2024 | May 2025 | Jun 2024 | May 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-475 | GILBOA HLO | 7 | CONSTRUCTION TO 75% | May 2025 | May 2026 | May 2025 | May 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-475 | GILBOA HLO | 8 | ORIGINAL EQUIP & FURNISHING | May 2026 | Feb 2027 | May 2026 | Feb 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-475 | GILBOA HLO | 9 | SUBSTANTIAL COMPLETION | Feb 2027 | Aug 2027 | Feb 2027 | Aug 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-475 | GILBOA HLO | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2027 | Nov 2027 | Aug 2027 | Nov 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-477 | Catskill Acqueduct Pressure Tunnels | 1 | DEVELOP SCOPE | Jun 2019 | Feb 2020 | Jun 2019 | Feb 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-477 | Catskill Acqueduct Pressure Tunnels | 2 | PRELIMINARY DESIGN | Feb 2020 | Feb 2021 | Feb 2020 | Feb 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-477 | Catskill Acqueduct Pressure Tunnels | 3 | FINAL DESIGN | Feb 2021 | Aug 2022 | Feb 2021 | Aug 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-477 | Catskill Acqueduct Pressure Tunnels | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2022 | May 2023 | Aug 2022 | May 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-477 | Catskill Acqueduct Pressure Tunnels | 5 | CONSTRUCTION TO 25% | May 2023 | May 2024 | May 2023 | May 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-477 | Catskill Acqueduct Pressure Tunnels | 6 | CONSTRUCTION TO 50% | May 2024 | Apr 2025 | May 2024 | Apr 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-477 | Catskill Acqueduct Pressure Tunnels | 7 | CONSTRUCTION TO 75% | Apr 2025 | Apr 2026 | Apr 2025 | Apr 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-477 | Catskill Acqueduct Pressure Tunnels | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2026 | Jan 2027 | Apr 2026 | Jan 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-477 | Catskill Acqueduct Pressure Tunnels | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Jul 2027 | Jan 2027 | Jul 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-477 | Catskill Acqueduct Pressure Tunnels | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2027 | Oct 2027 | Jul 2027 | Oct 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-506 | Watershed WRRFs RBC Replacement | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Feb 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-506 | Watershed WRRFs RBC Replacement | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Feb 2024 | Feb 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-506 | Watershed WRRFs RBC Replacement | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Feb 2025 | Aug 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-506 | Watershed WRRFs RBC Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Aug 2026 | May 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-506 | Watershed WRRFs RBC Replacement | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | May 2027 | May 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-506 | Watershed WRRFs RBC Replacement | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | May 2028 | Apr 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-506 | Watershed WRRFs RBC Replacement | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | Apr 2029 | Apr 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-506 | Watershed WRRFs RBC Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Apr 2030 | Jan 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-506 | Watershed WRRFs RBC Replacement | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Jan 2031 | Jul 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-506 | Watershed WRRFs RBC Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Jul 2031 | Oct 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-507 | Watershed WRRFS Microfiltration and Plant Upgrades | 1 | DEVELOP SCOPE | Jun 2022 | Feb 2023 | Jun 2022 | Feb 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-507 | Watershed WRRFS Microfiltration and Plant Upgrades | 2 | PRELIMINARY DESIGN | Feb 2023 | Feb 2024 | Feb 2023 | Feb 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-507 | Watershed WRRFS Microfiltration and Plant Upgrades | 3 | FINAL DESIGN | Feb 2024 | Aug 2025 | Feb 2024 | Aug 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-507 | Watershed WRRFS Microfiltration and Plant Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2025 | May 2026 | Aug 2025 | May 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-507 | Watershed WRRFS Microfiltration and Plant Upgrades | 5 | CONSTRUCTION TO 25% | May 2026 | May 2027 | May 2026 | May 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-507 | Watershed WRRFS Microfiltration and Plant Upgrades | 6 | CONSTRUCTION TO 50% | May 2027 | Apr 2028 | May 2027 | Apr 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-507 | Watershed WRRFS Microfiltration and Plant Upgrades | 7 | CONSTRUCTION TO 75% | Apr 2028 | Apr 2029 | Apr 2028 | Apr 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-507 | Watershed WRRFS Microfiltration and Plant Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2029 | Jan 2030 | Apr 2029 | Jan 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-507 | Watershed WRRFS Microfiltration and Plant Upgrades | 9 | SUBSTANTIAL COMPLETION | Jan 2030 | Jul 2030 | Jan 2030 | Jul 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-507 | Watershed WRRFS Microfiltration and Plant Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2030 | Oct 2030 | Jul 2030 | Oct 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-508 | DR-30 Culvert Repair & Embankment Stabilization | 1 | DEVELOP SCOPE | Jul 2019 | Mar 2020 | Jul 2019 | Mar 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-508 | DR-30 Culvert Repair & Embankment Stabilization | 2 | PRELIMINARY DESIGN | Mar 2020 | Mar 2021 | Mar 2020 | Mar 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-508 | DR-30 Culvert Repair & Embankment Stabilization | 3 | FINAL DESIGN | Mar 2021 | Sep 2022 | Mar 2021 | Sep 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-508 | DR-30 Culvert Repair & Embankment Stabilization | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2022 | Jun 2023 | Sep 2022 | Jun 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-508 | DR-30 Culvert Repair & Embankment Stabilization | 5 | CONSTRUCTION TO 25% | Jun 2023 | Jun 2024 | Jun 2023 | Jun 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-508 | DR-30 Culvert Repair & Embankment Stabilization | 6 | CONSTRUCTION TO 50% | Jun 2024 | May 2025 | Jun 2024 | May 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-508 | DR-30 Culvert Repair & Embankment Stabilization | 7 | CONSTRUCTION TO 75% | May 2025 | May 2026 | May 2025 | May 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-508 | DR-30 Culvert Repair & Embankment Stabilization | 8 | ORIGINAL EQUIP & FURNISHING | May 2026 | Feb 2027 | May 2026 | Feb 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-508 | DR-30 Culvert Repair & Embankment Stabilization | 9 | SUBSTANTIAL COMPLETION | Feb 2027 | Aug 2027 | Feb 2027 | Aug 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-508 | DR-30 Culvert Repair & Embankment Stabilization | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2027 | Nov 2027 | Aug 2027 | Nov 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-511 | Tannersville WWTP Collection System Repairs | 1 | DEVELOP SCOPE | Jun 2021 | Feb 2022 | Jul 2023 | Apr 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-511 | Tannersville WWTP Collection System Repairs | 2 | PRELIMINARY DESIGN | Feb 2022 | Feb 2023 | Apr 2024 | Apr 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-511 | Tannersville WWTP Collection System Repairs | 3 | FINAL DESIGN | Feb 2023 | Aug 2024 | Apr 2025 | Sep 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-511 | Tannersville WWTP Collection System Repairs | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2024 | May 2025 | Sep 2026 | Jun 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-511 | Tannersville WWTP Collection System Repairs | 5 | CONSTRUCTION TO 25% | May 2025 | May 2026 | Jun 2027 | Jun 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-511 | Tannersville WWTP Collection System Repairs | 6 | CONSTRUCTION TO 50% | May 2026 | Apr 2027 | Jun 2028 | Jun 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-511 | Tannersville WWTP Collection System Repairs | 7 | CONSTRUCTION TO 75% | May 2027 | Apr 2028 | Jun 2029 | Jun 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-511 | Tannersville WWTP Collection System Repairs | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2028 | Jan 2029 | Jun 2030 | Mar 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-511 | Tannersville WWTP Collection System Repairs | 9 | SUBSTANTIAL COMPLETION | Jan 2029 | Jul 2037 | Mar 2031 | Sep 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-511 | Tannersville WWTP Collection System Repairs | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2037 | Oct 2037 | Sep 2031 | Dec 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-515 | Hudson River Drainage Chmb Bridge IGA | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-515 | Hudson River Drainage Chmb Bridge IGA | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-515 | Hudson River Drainage Chmb Bridge IGA | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-515 | Hudson River Drainage Chmb Bridge IGA | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-515 | Hudson River Drainage Chmb Bridge IGA | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-515 | Hudson River Drainage Chmb Bridge IGA | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-515 | Hudson River Drainage Chmb Bridge IGA | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-515 | Hudson River Drainage Chmb Bridge IGA | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-515 | Hudson River Drainage Chmb Bridge IGA | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-515 | Hudson River Drainage Chmb Bridge IGA | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-521 | Ashokan Fleet Garage Floor | 1 | DEVELOP SCOPE | Dec 2022 | Feb 2023 | Dec 2022 | Feb 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-521 | Ashokan Fleet Garage Floor | 2 | PRELIMINARY DESIGN | Mar 2023 | Jun 2023 | Mar 2023 | Jun 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-521 | Ashokan Fleet Garage Floor | 3 | FINAL DESIGN | Jun 2023 | Dec 2023 | Jun 2023 | Dec 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-521 | Ashokan Fleet Garage Floor | 4 | BID AWARD AND REGISTER CONTRCT | Dec 2023 | Mar 2024 | Dec 2023 | Mar 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-521 | Ashokan Fleet Garage Floor | 5 | CONSTRUCTION TO 25% | Mar 2024 | Jul 2024 | Mar 2024 | Jul 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-521 | Ashokan Fleet Garage Floor | 6 | CONSTRUCTION TO 50% | Jul 2024 | Nov 2024 | Jul 2024 | Nov 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-521 | Ashokan Fleet Garage Floor | 7 | CONSTRUCTION TO 75% | Nov 2024 | Mar 2025 | Nov 2024 | Mar 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-521 | Ashokan Fleet Garage Floor | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2025 | Jun 2025 | Mar 2025 | Jun 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-521 | Ashokan Fleet Garage Floor | 9 | SUBSTANTIAL COMPLETION | Jun 2025 | Aug 2025 | Jun 2025 | Aug 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-521 | Ashokan Fleet Garage Floor | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2025 | Sep 2025 | Aug 2025 | Sep 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-523 | Walkill Blow off Valves | 1 | DEVELOP SCOPE | Jan 2022 | Apr 2022 | Jun 2020 | Feb 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-523 | Walkill Blow off Valves | 2 | PRELIMINARY DESIGN | Apr 2022 | Jul 2022 | Feb 2021 | Feb 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-523 | Walkill Blow off Valves | 3 | FINAL DESIGN | Jul 2022 | Jan 2023 | Feb 2022 | Aug 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-523 | Walkill Blow off Valves | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2023 | Apr 2023 | Aug 2023 | May 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-523 | Walkill Blow off Valves | 5 | CONSTRUCTION TO 25% | Apr 2023 | Aug 2023 | May 2024 | May 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-523 | Walkill Blow off Valves | 6 | CONSTRUCTION TO 50% | Aug 2023 | Dec 2023 | May 2025 | Apr 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-523 | Walkill Blow off Valves | 7 | CONSTRUCTION TO 75% | Dec 2023 | Apr 2024 | May 2026 | Apr 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-523 | Walkill Blow off Valves | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2024 | Jul 2024 | Apr 2027 | Jan 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-523 | Walkill Blow off Valves | 9 | SUBSTANTIAL COMPLETION | Jul 2024 | Sep 2024 | Jan 2028 | Jul 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-523 | Walkill Blow off Valves | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Oct 2024 | Jul 2032 | Oct 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-OPTIM | To Increase the Capacity of Upper Catskill Aqueduct | 1 | DEVELOP SCOPE | Jan 2011 | Dec 2011 | Jan 2011 | Sep 2011
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-OPTIM | To Increase the Capacity of Upper Catskill Aqueduct | 2 | PRELIMINARY DESIGN | Jan 2012 | May 2012 | Sep 2011 | Sep 2012
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-OPTIM | To Increase the Capacity of Upper Catskill Aqueduct | 3 | FINAL DESIGN | May 2012 | Dec 2012 | Sep 2012 | Mar 2014
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-OPTIM | To Increase the Capacity of Upper Catskill Aqueduct | 4 | BID AWARD AND REGISTER CONTRCT | Dec 2012 | Sep 2013 | Mar 2014 | Dec 2014
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-OPTIM | To Increase the Capacity of Upper Catskill Aqueduct | 5 | CONSTRUCTION TO 25% | Sep 2013 | Mar 2014 | Dec 2014 | Dec 2015
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-OPTIM | To Increase the Capacity of Upper Catskill Aqueduct | 6 | CONSTRUCTION TO 50% | Mar 2014 | Dec 2014 | Dec 2015 | Nov 2016
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-OPTIM | To Increase the Capacity of Upper Catskill Aqueduct | 7 | CONSTRUCTION TO 75% | Dec 2014 | Mar 2015 | Nov 2016 | Nov 2017
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-OPTIM | To Increase the Capacity of Upper Catskill Aqueduct | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2015 | Jun 2015 | Nov 2017 | Aug 2018
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-OPTIM | To Increase the Capacity of Upper Catskill Aqueduct | 9 | SUBSTANTIAL COMPLETION | Jun 2015 | Sep 2015 | Aug 2018 | Feb 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-OPTIM | To Increase the Capacity of Upper Catskill Aqueduct | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2015 | Dec 2015 | Feb 2027 | May 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-MRX24 | Replacng substandard catch basins with upgraded design CW | 1 | DEVELOP SCOPE | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-MRX24 | Replacng substandard catch basins with upgraded design CW | 2 | PRELIMINARY DESIGN | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-MRX24 | Replacng substandard catch basins with upgraded design CW | 3 | FINAL DESIGN | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-MRX24 | Replacng substandard catch basins with upgraded design CW | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2024 | Feb 2025 | Nov 2024 | Feb 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-MRX24 | Replacng substandard catch basins with upgraded design CW | 5 | CONSTRUCTION TO 25% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-MRX24 | Replacng substandard catch basins with upgraded design CW | 6 | CONSTRUCTION TO 50% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-MRX24 | Replacng substandard catch basins with upgraded design CW | 7 | CONSTRUCTION TO 75% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-MRX24 | Replacng substandard catch basins with upgraded design CW | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2026 | May 2026 | Feb 2026 | May 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-MRX24 | Replacng substandard catch basins with upgraded design CW | 9 | SUBSTANTIAL COMPLETION | May 2026 | Jul 2026 | May 2026 | Jul 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-MRX24 | Replacng substandard catch basins with upgraded design CW | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2026 | Aug 2026 | Jul 2026 | Aug 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CFP-PMCS | Croton Filtration Process Monitoring & Control System | 1 | DEVELOP SCOPE | Dec 2022 | Feb 2023 | Dec 2022 | Feb 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CFP-PMCS | Croton Filtration Process Monitoring & Control System | 2 | PRELIMINARY DESIGN | Mar 2023 | Jun 2023 | Mar 2023 | Jun 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CFP-PMCS | Croton Filtration Process Monitoring & Control System | 3 | FINAL DESIGN | Jun 2023 | Dec 2023 | Jun 2023 | Dec 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CFP-PMCS | Croton Filtration Process Monitoring & Control System | 4 | BID AWARD AND REGISTER CONTRCT | Dec 2023 | Mar 2024 | Dec 2023 | Mar 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CFP-PMCS | Croton Filtration Process Monitoring & Control System | 5 | CONSTRUCTION TO 25% | Mar 2024 | Jul 2024 | Mar 2024 | Jul 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CFP-PMCS | Croton Filtration Process Monitoring & Control System | 6 | CONSTRUCTION TO 50% | Jul 2024 | Nov 2024 | Jul 2024 | Nov 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CFP-PMCS | Croton Filtration Process Monitoring & Control System | 7 | CONSTRUCTION TO 75% | Nov 2024 | Mar 2025 | Nov 2024 | Mar 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CFP-PMCS | Croton Filtration Process Monitoring & Control System | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2025 | Jun 2025 | Mar 2025 | Jun 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CFP-PMCS | Croton Filtration Process Monitoring & Control System | 9 | SUBSTANTIAL COMPLETION | Jun 2025 | Aug 2025 | Jun 2025 | Aug 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CFP-PMCS | Croton Filtration Process Monitoring & Control System | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2025 | Sep 2025 | Aug 2025 | Sep 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CLBRSTROW | CONSTRUCTION OF RIGHT-OF-WAY CLOUDBURST NEIGHBORHOODS | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CLBRSTROW | CONSTRUCTION OF RIGHT-OF-WAY CLOUDBURST NEIGHBORHOODS | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CLBRSTROW | CONSTRUCTION OF RIGHT-OF-WAY CLOUDBURST NEIGHBORHOODS | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CLBRSTROW | CONSTRUCTION OF RIGHT-OF-WAY CLOUDBURST NEIGHBORHOODS | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CLBRSTROW | CONSTRUCTION OF RIGHT-OF-WAY CLOUDBURST NEIGHBORHOODS | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CLBRSTROW | CONSTRUCTION OF RIGHT-OF-WAY CLOUDBURST NEIGHBORHOODS | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CLBRSTROW | CONSTRUCTION OF RIGHT-OF-WAY CLOUDBURST NEIGHBORHOODS | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | May 2024 | Sep 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CLBRSTROW | CONSTRUCTION OF RIGHT-OF-WAY CLOUDBURST NEIGHBORHOODS | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CLBRSTROW | CONSTRUCTION OF RIGHT-OF-WAY CLOUDBURST NEIGHBORHOODS | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Dec 2024 | Feb 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CLBRSTROW | CONSTRUCTION OF RIGHT-OF-WAY CLOUDBURST NEIGHBORHOODS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Mar 2025 | Feb 2025 | Mar 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CLBRSTROW | CONSTRUCTION OF RIGHT-OF-WAY CLOUDBURST NEIGHBORHOODS | 11 | DEVELOP SCOPE | Feb 2025 | Mar 2025 | Mar 2025 | Dec 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CLBRSTROW | CONSTRUCTION OF RIGHT-OF-WAY CLOUDBURST NEIGHBORHOODS | 12 | PRELIMINARY DESIGN | Feb 2025 | Mar 2025 | Dec 2025 | Dec 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CLBRSTROW | CONSTRUCTION OF RIGHT-OF-WAY CLOUDBURST NEIGHBORHOODS | 13 | FINAL DESIGN | Feb 2025 | Mar 2025 | Dec 2026 | May 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CLBRSTROW | CONSTRUCTION OF RIGHT-OF-WAY CLOUDBURST NEIGHBORHOODS | 14 | BID AWARD AND REGISTER CONTRCT | Feb 2025 | Mar 2025 | May 2028 | Feb 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CLBRSTROW | CONSTRUCTION OF RIGHT-OF-WAY CLOUDBURST NEIGHBORHOODS | 15 | CONSTRUCTION TO 25% | Feb 2025 | Mar 2025 | Feb 2029 | Feb 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CLBRSTROW | CONSTRUCTION OF RIGHT-OF-WAY CLOUDBURST NEIGHBORHOODS | 16 | CONSTRUCTION TO 50% | Feb 2025 | Mar 2025 | Feb 2030 | Feb 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CLBRSTROW | CONSTRUCTION OF RIGHT-OF-WAY CLOUDBURST NEIGHBORHOODS | 17 | CONSTRUCTION TO 75% | Feb 2025 | Mar 2025 | Feb 2031 | Feb 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CLBRSTROW | CONSTRUCTION OF RIGHT-OF-WAY CLOUDBURST NEIGHBORHOODS | 18 | ORIGINAL EQUIP & FURNISHING | Feb 2025 | Mar 2025 | Feb 2032 | Nov 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CLBRSTROW | CONSTRUCTION OF RIGHT-OF-WAY CLOUDBURST NEIGHBORHOODS | 19 | SUBSTANTIAL COMPLETION | Feb 2025 | Mar 2025 | Nov 2032 | May 2033
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CLBRSTROW | CONSTRUCTION OF RIGHT-OF-WAY CLOUDBURST NEIGHBORHOODS | 20 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Mar 2025 | May 2033 | Aug 2033
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208B | NEW CROTON DAM RECONSTRUCTION | 1 | DEVELOP SCOPE | Jul 2016 | Sep 2016 | Jul 2016 | Mar 2017
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208B | NEW CROTON DAM RECONSTRUCTION | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Mar 2017 | Mar 2018
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208B | NEW CROTON DAM RECONSTRUCTION | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Mar 2018 | Sep 2019
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208B | NEW CROTON DAM RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Sep 2019 | Jun 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208B | NEW CROTON DAM RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Jun 2020 | Jun 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208B | NEW CROTON DAM RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Jun 2021 | May 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208B | NEW CROTON DAM RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | May 2022 | May 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208B | NEW CROTON DAM RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | May 2023 | Feb 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208B | NEW CROTON DAM RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Feb 2024 | Aug 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208B | NEW CROTON DAM RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Aug 2028 | Nov 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-410 | NEW CROTON LAKE GATE HOUSE HVAC REHABILITATION | 1 | DEVELOP SCOPE | Dec 2007 | Mar 2008 | Aug 2024 | Nov 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-410 | NEW CROTON LAKE GATE HOUSE HVAC REHABILITATION | 2 | PRELIMINARY DESIGN | Mar 2008 | Jul 2008 | Nov 2024 | Mar 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-410 | NEW CROTON LAKE GATE HOUSE HVAC REHABILITATION | 3 | FINAL DESIGN | Jul 2008 | Jan 2009 | Mar 2025 | Sep 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-410 | NEW CROTON LAKE GATE HOUSE HVAC REHABILITATION | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2009 | Apr 2009 | Sep 2025 | Dec 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-410 | NEW CROTON LAKE GATE HOUSE HVAC REHABILITATION | 5 | CONSTRUCTION TO 25% | Apr 2009 | Aug 2009 | Dec 2025 | Apr 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-410 | NEW CROTON LAKE GATE HOUSE HVAC REHABILITATION | 6 | CONSTRUCTION TO 50% | Aug 2009 | Dec 2009 | Apr 2026 | Aug 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-410 | NEW CROTON LAKE GATE HOUSE HVAC REHABILITATION | 7 | CONSTRUCTION TO 75% | Dec 2009 | Apr 2010 | Aug 2026 | Dec 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-410 | NEW CROTON LAKE GATE HOUSE HVAC REHABILITATION | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2010 | Jul 2010 | Dec 2026 | Mar 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-410 | NEW CROTON LAKE GATE HOUSE HVAC REHABILITATION | 9 | SUBSTANTIAL COMPLETION | Jul 2010 | Aug 2010 | Mar 2027 | May 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-410 | NEW CROTON LAKE GATE HOUSE HVAC REHABILITATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2010 | Sep 2010 | May 2027 | Jun 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-452 | WWTP - CYCLICAL EQUIPMENT REPLACEMENT | 1 | DEVELOP SCOPE | Aug 2009 | Nov 2009 | Jun 2008 | Mar 2009
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-452 | WWTP - CYCLICAL EQUIPMENT REPLACEMENT | 2 | PRELIMINARY DESIGN | Nov 2009 | Mar 2010 | Mar 2009 | Mar 2010
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-452 | WWTP - CYCLICAL EQUIPMENT REPLACEMENT | 3 | FINAL DESIGN | Mar 2010 | Sep 2010 | Mar 2010 | Sep 2011
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-452 | WWTP - CYCLICAL EQUIPMENT REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2010 | Dec 2010 | Sep 2011 | Jun 2012
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-452 | WWTP - CYCLICAL EQUIPMENT REPLACEMENT | 5 | CONSTRUCTION TO 25% | Dec 2010 | Apr 2011 | Jun 2012 | Jun 2013
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-452 | WWTP - CYCLICAL EQUIPMENT REPLACEMENT | 6 | CONSTRUCTION TO 50% | Apr 2011 | Aug 2011 | Jun 2013 | May 2014
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-452 | WWTP - CYCLICAL EQUIPMENT REPLACEMENT | 7 | CONSTRUCTION TO 75% | Aug 2011 | Dec 2011 | May 2014 | May 2015
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-452 | WWTP - CYCLICAL EQUIPMENT REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2011 | Mar 2012 | May 2015 | Feb 2016
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-452 | WWTP - CYCLICAL EQUIPMENT REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | Mar 2012 | Apr 2012 | Feb 2016 | Aug 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-452 | WWTP - CYCLICAL EQUIPMENT REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2012 | May 2012 | Aug 2028 | Nov 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-497 | Aqueduct Erosion Restoration at EOH | 2 | PRELIMINARY DESIGN | Oct 2009 | Feb 2010 | Mar 2019 | Mar 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-497 | Aqueduct Erosion Restoration at EOH | 3 | FINAL DESIGN | Feb 2010 | Aug 2010 | Mar 2020 | Sep 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-497 | Aqueduct Erosion Restoration at EOH | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2010 | Nov 2010 | Sep 2021 | Jun 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-497 | Aqueduct Erosion Restoration at EOH | 5 | CONSTRUCTION TO 25% | Nov 2010 | Mar 2011 | Jun 2022 | Jun 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-497 | Aqueduct Erosion Restoration at EOH | 6 | CONSTRUCTION TO 50% | Mar 2011 | Jul 2011 | Jun 2023 | May 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-497 | Aqueduct Erosion Restoration at EOH | 7 | CONSTRUCTION TO 75% | Jul 2011 | Nov 2011 | May 2024 | May 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-497 | Aqueduct Erosion Restoration at EOH | 8 | ORIGINAL EQUIP & FURNISHING | Nov 2011 | Feb 2012 | May 2025 | Feb 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-497 | Aqueduct Erosion Restoration at EOH | 9 | SUBSTANTIAL COMPLETION | Feb 2012 | Apr 2012 | Feb 2026 | Aug 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-497 | Aqueduct Erosion Restoration at EOH | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2012 | May 2012 | Aug 2026 | Nov 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-502 | Road Improvement due to Kensico Dam Road Closure | 1 | DEVELOP SCOPE | Sep 2009 | Nov 2009 | Sep 2009 | May 2010
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-502 | Road Improvement due to Kensico Dam Road Closure | 2 | PRELIMINARY DESIGN | Nov 2009 | Mar 2010 | May 2010 | May 2011
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-502 | Road Improvement due to Kensico Dam Road Closure | 3 | FINAL DESIGN | Mar 2010 | Sep 2010 | May 2011 | Nov 2012
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-502 | Road Improvement due to Kensico Dam Road Closure | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2010 | Dec 2010 | Nov 2012 | Aug 2013
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-502 | Road Improvement due to Kensico Dam Road Closure | 5 | CONSTRUCTION TO 25% | Dec 2010 | Apr 2011 | Aug 2013 | Aug 2014
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-502 | Road Improvement due to Kensico Dam Road Closure | 6 | CONSTRUCTION TO 50% | Apr 2011 | Aug 2011 | Aug 2014 | Jul 2015
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-502 | Road Improvement due to Kensico Dam Road Closure | 7 | CONSTRUCTION TO 75% | Aug 2011 | Dec 2011 | Aug 2015 | Jul 2016
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-502 | Road Improvement due to Kensico Dam Road Closure | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2011 | Mar 2012 | Jul 2016 | Apr 2017
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-502 | Road Improvement due to Kensico Dam Road Closure | 9 | SUBSTANTIAL COMPLETION | Mar 2012 | May 2012 | Apr 2017 | Oct 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-502 | Road Improvement due to Kensico Dam Road Closure | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2012 | Jun 2012 | Oct 2025 | Jan 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-509 | Arcady Road Reconstruction | 1 | DEVELOP SCOPE | Jul 2016 | Mar 2017 | Jun 2019 | Feb 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-509 | Arcady Road Reconstruction | 2 | PRELIMINARY DESIGN | Mar 2017 | Mar 2018 | Feb 2020 | Feb 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-509 | Arcady Road Reconstruction | 3 | FINAL DESIGN | Mar 2018 | Sep 2019 | Feb 2021 | Aug 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-509 | Arcady Road Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Jun 2020 | Aug 2022 | May 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-509 | Arcady Road Reconstruction | 5 | CONSTRUCTION TO 25% | Jun 2020 | Jun 2021 | May 2023 | May 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-509 | Arcady Road Reconstruction | 6 | CONSTRUCTION TO 50% | Jun 2021 | May 2022 | May 2024 | Apr 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-509 | Arcady Road Reconstruction | 7 | CONSTRUCTION TO 75% | May 2022 | May 2023 | Apr 2025 | Apr 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-509 | Arcady Road Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | May 2023 | Feb 2024 | Apr 2026 | Jan 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-509 | Arcady Road Reconstruction | 9 | SUBSTANTIAL COMPLETION | Feb 2024 | Aug 2024 | Jan 2027 | Jul 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-509 | Arcady Road Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2024 | Nov 2024 | Jul 2031 | Oct 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-530 | Removal and reconstruction of DEP bridges, upstate watershed | 1 | DEVELOP SCOPE | Jul 2016 | Sep 2016 | Jul 2016 | Mar 2017
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-530 | Removal and reconstruction of DEP bridges, upstate watershed | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Mar 2017 | Mar 2018
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-530 | Removal and reconstruction of DEP bridges, upstate watershed | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Mar 2018 | Sep 2019
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-530 | Removal and reconstruction of DEP bridges, upstate watershed | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Sep 2019 | Jun 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-530 | Removal and reconstruction of DEP bridges, upstate watershed | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Jun 2020 | Jun 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-530 | Removal and reconstruction of DEP bridges, upstate watershed | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Jun 2021 | May 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-530 | Removal and reconstruction of DEP bridges, upstate watershed | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | May 2022 | May 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-530 | Removal and reconstruction of DEP bridges, upstate watershed | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | May 2023 | Feb 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-530 | Removal and reconstruction of DEP bridges, upstate watershed | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Feb 2024 | Aug 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-530 | Removal and reconstruction of DEP bridges, upstate watershed | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Aug 2028 | Nov 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-534 | WEST BRANCH AUXILIARY DAM-CREEP REMEDIATION | 1 | DEVELOP SCOPE | Jul 2017 | Sep 2017 | Jul 2017 | Mar 2018
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-534 | WEST BRANCH AUXILIARY DAM-CREEP REMEDIATION | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Mar 2018 | Mar 2019
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-534 | WEST BRANCH AUXILIARY DAM-CREEP REMEDIATION | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Mar 2019 | Sep 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-534 | WEST BRANCH AUXILIARY DAM-CREEP REMEDIATION | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Sep 2020 | Jun 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-534 | WEST BRANCH AUXILIARY DAM-CREEP REMEDIATION | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Jun 2021 | Jun 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-534 | WEST BRANCH AUXILIARY DAM-CREEP REMEDIATION | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Jun 2022 | May 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-534 | WEST BRANCH AUXILIARY DAM-CREEP REMEDIATION | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | May 2023 | May 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-534 | WEST BRANCH AUXILIARY DAM-CREEP REMEDIATION | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | May 2024 | Feb 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-534 | WEST BRANCH AUXILIARY DAM-CREEP REMEDIATION | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Feb 2025 | Nov 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-534 | WEST BRANCH AUXILIARY DAM-CREEP REMEDIATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Nov 2025 | Feb 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-536 | EOH Dam Facing | 1 | DEVELOP SCOPE | Jul 2017 | Sep 2017 | Jul 2017 | Mar 2018
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-536 | EOH Dam Facing | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Mar 2018 | Mar 2019
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-536 | EOH Dam Facing | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Mar 2019 | Sep 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-536 | EOH Dam Facing | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Sep 2020 | Jun 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-536 | EOH Dam Facing | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Jun 2021 | Jun 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-536 | EOH Dam Facing | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Jun 2022 | May 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-536 | EOH Dam Facing | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | May 2023 | May 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-536 | EOH Dam Facing | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | May 2024 | Feb 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-536 | EOH Dam Facing | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Feb 2025 | Aug 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-536 | EOH Dam Facing | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Aug 2029 | Nov 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-552 | Shaft 18 Traveling Screens & Other Work | 1 | DEVELOP SCOPE | Jun 2020 | Mar 2021 | Jun 2020 | Mar 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-552 | Shaft 18 Traveling Screens & Other Work | 2 | PRELIMINARY DESIGN | Mar 2021 | Mar 2022 | Mar 2021 | Mar 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-552 | Shaft 18 Traveling Screens & Other Work | 3 | FINAL DESIGN | Mar 2022 | Sep 2023 | Mar 2022 | Sep 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-552 | Shaft 18 Traveling Screens & Other Work | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2023 | Jun 2024 | Sep 2023 | Jun 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-552 | Shaft 18 Traveling Screens & Other Work | 5 | CONSTRUCTION TO 25% | Jun 2024 | Jun 2025 | Jun 2024 | Jun 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-552 | Shaft 18 Traveling Screens & Other Work | 6 | CONSTRUCTION TO 50% | Jun 2025 | May 2026 | Jun 2025 | May 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-552 | Shaft 18 Traveling Screens & Other Work | 7 | CONSTRUCTION TO 75% | May 2026 | May 2027 | May 2026 | May 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-552 | Shaft 18 Traveling Screens & Other Work | 8 | ORIGINAL EQUIP & FURNISHING | May 2027 | Feb 2028 | May 2027 | Feb 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-552 | Shaft 18 Traveling Screens & Other Work | 9 | SUBSTANTIAL COMPLETION | Feb 2028 | Aug 2028 | Feb 2028 | Aug 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-552 | Shaft 18 Traveling Screens & Other Work | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2028 | Nov 2028 | Aug 2028 | Nov 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-553B | Class C regulated dams | 1 | DEVELOP SCOPE | Jun 2024 | Feb 2025 | Jun 2024 | Feb 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-553B | Class C regulated dams | 2 | PRELIMINARY DESIGN | Feb 2025 | Feb 2026 | Feb 2025 | Feb 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-553B | Class C regulated dams | 3 | FINAL DESIGN | Feb 2026 | Aug 2027 | Feb 2026 | Aug 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-553B | Class C regulated dams | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2027 | May 2028 | Aug 2027 | May 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-553B | Class C regulated dams | 5 | CONSTRUCTION TO 25% | May 2028 | May 2029 | May 2028 | May 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-553B | Class C regulated dams | 6 | CONSTRUCTION TO 50% | May 2029 | Apr 2030 | May 2029 | Apr 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-553B | Class C regulated dams | 7 | CONSTRUCTION TO 75% | May 2030 | Apr 2031 | May 2030 | Apr 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-553B | Class C regulated dams | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2031 | Jan 2032 | Apr 2031 | Jan 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-553B | Class C regulated dams | 9 | SUBSTANTIAL COMPLETION | Jan 2032 | Jul 2032 | Jan 2032 | Jul 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-553B | Class C regulated dams | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2032 | Oct 2032 | Jul 2032 | Oct 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-557 | Kensico Waterfowl Facility Construction & Paving | 1 | DEVELOP SCOPE | Jun 2019 | Aug 2019 | Jan 2022 | Apr 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-557 | Kensico Waterfowl Facility Construction & Paving | 2 | PRELIMINARY DESIGN | Aug 2019 | Dec 2019 | Apr 2022 | Jul 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-557 | Kensico Waterfowl Facility Construction & Paving | 3 | FINAL DESIGN | Dec 2019 | Jun 2020 | Jul 2022 | Jan 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-557 | Kensico Waterfowl Facility Construction & Paving | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Sep 2020 | Jan 2023 | Apr 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-557 | Kensico Waterfowl Facility Construction & Paving | 5 | CONSTRUCTION TO 25% | Sep 2020 | Jan 2021 | Apr 2023 | Aug 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-557 | Kensico Waterfowl Facility Construction & Paving | 6 | CONSTRUCTION TO 50% | Jan 2021 | May 2021 | Aug 2023 | Dec 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-557 | Kensico Waterfowl Facility Construction & Paving | 7 | CONSTRUCTION TO 75% | May 2021 | Sep 2021 | Dec 2023 | Apr 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-557 | Kensico Waterfowl Facility Construction & Paving | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Dec 2021 | Apr 2024 | Jul 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-557 | Kensico Waterfowl Facility Construction & Paving | 9 | SUBSTANTIAL COMPLETION | Dec 2021 | Feb 2022 | Jul 2024 | Sep 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-557 | Kensico Waterfowl Facility Construction & Paving | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2022 | Mar 2022 | Sep 2024 | Oct 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-558 | Aqueduct Restoration at Lake Street - EOH | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2021 | Mar 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-558 | Aqueduct Restoration at Lake Street - EOH | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Mar 2022 | Mar 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-558 | Aqueduct Restoration at Lake Street - EOH | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Mar 2023 | Sep 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-558 | Aqueduct Restoration at Lake Street - EOH | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Sep 2024 | Jun 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-558 | Aqueduct Restoration at Lake Street - EOH | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Jun 2025 | Jun 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-558 | Aqueduct Restoration at Lake Street - EOH | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Jun 2026 | May 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-558 | Aqueduct Restoration at Lake Street - EOH | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | May 2027 | May 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-558 | Aqueduct Restoration at Lake Street - EOH | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | May 2028 | Feb 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-558 | Aqueduct Restoration at Lake Street - EOH | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Feb 2029 | Aug 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-558 | Aqueduct Restoration at Lake Street - EOH | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Aug 2029 | Nov 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-559 | MAHOPAC WTP Upgrades | 1 | DEVELOP SCOPE | Jun 2020 | Mar 2021 | Jun 2020 | Mar 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-559 | MAHOPAC WTP Upgrades | 2 | PRELIMINARY DESIGN | Mar 2021 | Mar 2022 | Mar 2021 | Mar 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-559 | MAHOPAC WTP Upgrades | 3 | FINAL DESIGN | Mar 2022 | Sep 2023 | Mar 2022 | Sep 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-559 | MAHOPAC WTP Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2023 | Jun 2024 | Sep 2023 | Jun 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-559 | MAHOPAC WTP Upgrades | 5 | CONSTRUCTION TO 25% | Jun 2024 | Jun 2025 | Jun 2024 | Jun 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-559 | MAHOPAC WTP Upgrades | 6 | CONSTRUCTION TO 50% | Jun 2025 | May 2026 | Jun 2025 | May 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-559 | MAHOPAC WTP Upgrades | 7 | CONSTRUCTION TO 75% | May 2026 | May 2027 | May 2026 | May 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-559 | MAHOPAC WTP Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | May 2027 | Feb 2028 | May 2027 | Feb 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-559 | MAHOPAC WTP Upgrades | 9 | SUBSTANTIAL COMPLETION | Feb 2028 | Aug 2028 | Feb 2028 | Aug 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-559 | MAHOPAC WTP Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2028 | Nov 2028 | Aug 2028 | Nov 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-569 | HIGHLANDS CONSOLIDATED FACILITY | 1 | DEVELOP SCOPE | Jul 2023 | Mar 2024 | Jul 2023 | Mar 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-569 | HIGHLANDS CONSOLIDATED FACILITY | 2 | PRELIMINARY DESIGN | Mar 2024 | Mar 2025 | Mar 2024 | Mar 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-569 | HIGHLANDS CONSOLIDATED FACILITY | 3 | FINAL DESIGN | Mar 2025 | Sep 2026 | Mar 2025 | Sep 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-569 | HIGHLANDS CONSOLIDATED FACILITY | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2026 | Jun 2027 | Sep 2026 | Jun 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-569 | HIGHLANDS CONSOLIDATED FACILITY | 5 | CONSTRUCTION TO 25% | Jun 2027 | Jun 2028 | Jun 2027 | Jun 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-569 | HIGHLANDS CONSOLIDATED FACILITY | 6 | CONSTRUCTION TO 50% | Jun 2028 | May 2029 | Jun 2028 | May 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-569 | HIGHLANDS CONSOLIDATED FACILITY | 7 | CONSTRUCTION TO 75% | May 2029 | May 2030 | May 2029 | May 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-569 | HIGHLANDS CONSOLIDATED FACILITY | 8 | ORIGINAL EQUIP & FURNISHING | May 2030 | Feb 2031 | May 2030 | Feb 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-569 | HIGHLANDS CONSOLIDATED FACILITY | 9 | SUBSTANTIAL COMPLETION | Feb 2031 | Aug 2031 | Feb 2031 | Aug 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-569 | HIGHLANDS CONSOLIDATED FACILITY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2031 | Nov 2031 | Aug 2031 | Nov 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-570 | Dunwoodie Field Operations Shop | 1 | DEVELOP SCOPE | Jan 2020 | Mar 2020 | Jul 2023 | Sep 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-570 | Dunwoodie Field Operations Shop | 2 | PRELIMINARY DESIGN | Mar 2020 | Jul 2020 | Sep 2023 | Jan 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-570 | Dunwoodie Field Operations Shop | 3 | FINAL DESIGN | Jul 2020 | Jan 2021 | Jan 2024 | Jul 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-570 | Dunwoodie Field Operations Shop | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2021 | Apr 2021 | Jul 2024 | Oct 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-570 | Dunwoodie Field Operations Shop | 5 | CONSTRUCTION TO 25% | Apr 2021 | Aug 2021 | Oct 2024 | Feb 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-570 | Dunwoodie Field Operations Shop | 6 | CONSTRUCTION TO 50% | Aug 2021 | Dec 2021 | Feb 2025 | Jun 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-570 | Dunwoodie Field Operations Shop | 7 | CONSTRUCTION TO 75% | Dec 2021 | Apr 2022 | Jun 2025 | Oct 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-570 | Dunwoodie Field Operations Shop | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2022 | Jul 2022 | Oct 2025 | Jan 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-570 | Dunwoodie Field Operations Shop | 9 | SUBSTANTIAL COMPLETION | Jul 2022 | Sep 2022 | Jan 2026 | Mar 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-570 | Dunwoodie Field Operations Shop | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Oct 2022 | Mar 2026 | Apr 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-586 | Amawalk Dam Improvements | 1 | DEVELOP SCOPE | Sep 2022 | Nov 2022 | Sep 2022 | May 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-586 | Amawalk Dam Improvements | 2 | PRELIMINARY DESIGN | Nov 2022 | Mar 2023 | May 2023 | May 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-586 | Amawalk Dam Improvements | 3 | FINAL DESIGN | Mar 2023 | Sep 2023 | May 2024 | Nov 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-586 | Amawalk Dam Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2023 | Dec 2023 | Nov 2025 | Aug 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-586 | Amawalk Dam Improvements | 5 | CONSTRUCTION TO 25% | Dec 2023 | Apr 2024 | Aug 2026 | Aug 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-586 | Amawalk Dam Improvements | 6 | CONSTRUCTION TO 50% | Apr 2024 | Aug 2024 | Aug 2027 | Jul 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-586 | Amawalk Dam Improvements | 7 | CONSTRUCTION TO 75% | Aug 2024 | Dec 2024 | Jul 2028 | Jul 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-586 | Amawalk Dam Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2024 | Mar 2025 | Jul 2029 | Apr 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-586 | Amawalk Dam Improvements | 9 | SUBSTANTIAL COMPLETION | Mar 2025 | May 2025 | Apr 2030 | Oct 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-586 | Amawalk Dam Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2025 | Jun 2025 | Oct 2030 | Jan 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-587 | DAM STABILITY IMPROVEMENTS | 1 | DEVELOP SCOPE | Jun 2022 | Feb 2023 | Jun 2022 | Feb 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-587 | DAM STABILITY IMPROVEMENTS | 2 | PRELIMINARY DESIGN | Feb 2023 | Feb 2024 | Feb 2023 | Feb 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-587 | DAM STABILITY IMPROVEMENTS | 3 | FINAL DESIGN | Feb 2024 | Aug 2025 | Feb 2024 | Aug 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-587 | DAM STABILITY IMPROVEMENTS | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2025 | May 2026 | Aug 2025 | May 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-587 | DAM STABILITY IMPROVEMENTS | 5 | CONSTRUCTION TO 25% | May 2026 | May 2027 | May 2026 | May 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-587 | DAM STABILITY IMPROVEMENTS | 6 | CONSTRUCTION TO 50% | May 2027 | Apr 2028 | May 2027 | Apr 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-587 | DAM STABILITY IMPROVEMENTS | 7 | CONSTRUCTION TO 75% | Apr 2028 | Apr 2029 | Apr 2028 | Apr 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-587 | DAM STABILITY IMPROVEMENTS | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2029 | Jan 2030 | Apr 2029 | Jan 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-587 | DAM STABILITY IMPROVEMENTS | 9 | SUBSTANTIAL COMPLETION | Jan 2030 | Jul 2030 | Jan 2030 | Jul 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-587 | DAM STABILITY IMPROVEMENTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2030 | Oct 2030 | Jul 2030 | Oct 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-589 | EASTVIEW MAINTENANCE SHOP | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2025 | Aug 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-589 | EASTVIEW MAINTENANCE SHOP | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2025 | Dec 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-589 | EASTVIEW MAINTENANCE SHOP | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2025 | Jun 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-589 | EASTVIEW MAINTENANCE SHOP | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2026 | Sep 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-589 | EASTVIEW MAINTENANCE SHOP | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | Sep 2026 | Jan 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-589 | EASTVIEW MAINTENANCE SHOP | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | Jan 2027 | May 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-589 | EASTVIEW MAINTENANCE SHOP | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | May 2027 | Sep 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-589 | EASTVIEW MAINTENANCE SHOP | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Sep 2027 | Dec 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-589 | EASTVIEW MAINTENANCE SHOP | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Dec 2027 | Feb 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-589 | EASTVIEW MAINTENANCE SHOP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Mar 2025 | Feb 2028 | Mar 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-594 | UV FOUNDATION DRAIN MH PHASE 2 | 1 | DEVELOP SCOPE | Jun 2019 | Aug 2019 | Jan 2023 | Mar 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-594 | UV FOUNDATION DRAIN MH PHASE 2 | 2 | PRELIMINARY DESIGN | Aug 2019 | Dec 2019 | Apr 2023 | Jul 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-594 | UV FOUNDATION DRAIN MH PHASE 2 | 3 | FINAL DESIGN | Dec 2019 | Jun 2020 | Jul 2023 | Jan 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-594 | UV FOUNDATION DRAIN MH PHASE 2 | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Sep 2020 | Jan 2024 | Apr 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-594 | UV FOUNDATION DRAIN MH PHASE 2 | 5 | CONSTRUCTION TO 25% | Sep 2020 | Jan 2021 | Apr 2024 | Aug 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-594 | UV FOUNDATION DRAIN MH PHASE 2 | 6 | CONSTRUCTION TO 50% | Jan 2021 | May 2021 | Aug 2024 | Dec 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-594 | UV FOUNDATION DRAIN MH PHASE 2 | 7 | CONSTRUCTION TO 75% | May 2021 | Sep 2021 | Dec 2024 | Apr 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-594 | UV FOUNDATION DRAIN MH PHASE 2 | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Dec 2021 | Apr 2025 | Jul 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-594 | UV FOUNDATION DRAIN MH PHASE 2 | 9 | SUBSTANTIAL COMPLETION | Dec 2021 | Feb 2022 | Jul 2025 | Sep 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-594 | UV FOUNDATION DRAIN MH PHASE 2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2022 | Mar 2022 | Sep 2025 | Oct 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-607 | Shaft 17 Elevator Replacement | 1 | DEVELOP SCOPE | Mar 2019 | Jun 2019 | Mar 2024 | Jun 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-607 | Shaft 17 Elevator Replacement | 2 | PRELIMINARY DESIGN | Jun 2019 | Oct 2019 | Jun 2024 | Oct 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-607 | Shaft 17 Elevator Replacement | 3 | FINAL DESIGN | Oct 2019 | Apr 2020 | Oct 2024 | Apr 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-607 | Shaft 17 Elevator Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2020 | Jul 2020 | Apr 2025 | Jul 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-607 | Shaft 17 Elevator Replacement | 5 | CONSTRUCTION TO 25% | Jul 2020 | Nov 2020 | Jul 2025 | Nov 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-607 | Shaft 17 Elevator Replacement | 6 | CONSTRUCTION TO 50% | Nov 2020 | Mar 2021 | Nov 2025 | Mar 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-607 | Shaft 17 Elevator Replacement | 7 | CONSTRUCTION TO 75% | Mar 2021 | Jul 2021 | Mar 2026 | Jun 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-607 | Shaft 17 Elevator Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2021 | Oct 2021 | Jun 2026 | Sep 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-607 | Shaft 17 Elevator Replacement | 9 | SUBSTANTIAL COMPLETION | Oct 2021 | Dec 2021 | Sep 2026 | Nov 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-607 | Shaft 17 Elevator Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2021 | Jan 2022 | Nov 2026 | Dec 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-611 | BWS Emergency Services Contract | 1 | DEVELOP SCOPE | Jun 2020 | Feb 2021 | Jan 2023 | Sep 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-611 | BWS Emergency Services Contract | 2 | PRELIMINARY DESIGN | Feb 2021 | Feb 2022 | Sep 2023 | Sep 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-611 | BWS Emergency Services Contract | 3 | FINAL DESIGN | Feb 2022 | Aug 2023 | Sep 2024 | Mar 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-611 | BWS Emergency Services Contract | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2023 | May 2024 | Mar 2026 | Dec 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-611 | BWS Emergency Services Contract | 5 | CONSTRUCTION TO 25% | May 2024 | May 2025 | Dec 2026 | Dec 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-611 | BWS Emergency Services Contract | 6 | CONSTRUCTION TO 50% | May 2025 | Apr 2026 | Dec 2027 | Nov 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-611 | BWS Emergency Services Contract | 7 | CONSTRUCTION TO 75% | May 2026 | Apr 2027 | Nov 2028 | Nov 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-611 | BWS Emergency Services Contract | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2027 | Jan 2028 | Nov 2029 | Aug 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-611 | BWS Emergency Services Contract | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Jul 2028 | Aug 2030 | Feb 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-611 | BWS Emergency Services Contract | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2028 | Oct 2028 | Feb 2031 | May 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-624 | Conversion of Kensico Lab to EOH Operations HQ | 1 | DEVELOP SCOPE | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-624 | Conversion of Kensico Lab to EOH Operations HQ | 2 | PRELIMINARY DESIGN | Apr 2022 | Jul 2022 | Apr 2022 | Jul 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-624 | Conversion of Kensico Lab to EOH Operations HQ | 3 | FINAL DESIGN | Jul 2022 | Jan 2023 | Jul 2022 | Jan 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-624 | Conversion of Kensico Lab to EOH Operations HQ | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2023 | Apr 2023 | Jan 2023 | Apr 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-624 | Conversion of Kensico Lab to EOH Operations HQ | 5 | CONSTRUCTION TO 25% | Apr 2023 | Aug 2023 | Apr 2023 | Aug 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-624 | Conversion of Kensico Lab to EOH Operations HQ | 6 | CONSTRUCTION TO 50% | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-624 | Conversion of Kensico Lab to EOH Operations HQ | 7 | CONSTRUCTION TO 75% | Dec 2023 | Apr 2024 | Dec 2023 | Apr 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-624 | Conversion of Kensico Lab to EOH Operations HQ | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2024 | Jul 2024 | Apr 2024 | Jul 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-624 | Conversion of Kensico Lab to EOH Operations HQ | 9 | SUBSTANTIAL COMPLETION | Jul 2024 | Sep 2024 | Jul 2024 | Sep 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-624 | Conversion of Kensico Lab to EOH Operations HQ | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Oct 2024 | Sep 2024 | Oct 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-636 | Hillview South Connecting Conduit Repair | 1 | DEVELOP SCOPE | Jan 2024 | Sep 2024 | Jan 2024 | Sep 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-636 | Hillview South Connecting Conduit Repair | 2 | PRELIMINARY DESIGN | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-636 | Hillview South Connecting Conduit Repair | 3 | FINAL DESIGN | Sep 2025 | Mar 2027 | Sep 2025 | Mar 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-636 | Hillview South Connecting Conduit Repair | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2027 | Dec 2027 | Mar 2027 | Dec 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-636 | Hillview South Connecting Conduit Repair | 5 | CONSTRUCTION TO 25% | Dec 2027 | Dec 2028 | Dec 2027 | Dec 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-636 | Hillview South Connecting Conduit Repair | 6 | CONSTRUCTION TO 50% | Dec 2028 | Nov 2029 | Dec 2028 | Nov 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-636 | Hillview South Connecting Conduit Repair | 7 | CONSTRUCTION TO 75% | Nov 2029 | Nov 2030 | Nov 2029 | Nov 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-636 | Hillview South Connecting Conduit Repair | 8 | ORIGINAL EQUIP & FURNISHING | Nov 2030 | Aug 2031 | Nov 2030 | Aug 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-636 | Hillview South Connecting Conduit Repair | 9 | SUBSTANTIAL COMPLETION | Aug 2031 | Feb 2032 | Aug 2031 | Feb 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-636 | Hillview South Connecting Conduit Repair | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2032 | May 2032 | Feb 2032 | May 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-644 | Cross River Inlet Bridge Rehabilitation | 1 | DEVELOP SCOPE | Jul 2024 | Mar 2025 | Jul 2024 | Mar 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-644 | Cross River Inlet Bridge Rehabilitation | 2 | PRELIMINARY DESIGN | Mar 2025 | Mar 2026 | Mar 2025 | Mar 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-644 | Cross River Inlet Bridge Rehabilitation | 3 | FINAL DESIGN | Mar 2026 | Sep 2027 | Mar 2026 | Sep 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-644 | Cross River Inlet Bridge Rehabilitation | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2027 | Jun 2028 | Sep 2027 | Jun 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-644 | Cross River Inlet Bridge Rehabilitation | 5 | CONSTRUCTION TO 25% | Jun 2028 | Jun 2029 | Jun 2028 | Jun 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-644 | Cross River Inlet Bridge Rehabilitation | 6 | CONSTRUCTION TO 50% | Jun 2029 | May 2030 | Jun 2029 | May 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-644 | Cross River Inlet Bridge Rehabilitation | 7 | CONSTRUCTION TO 75% | May 2030 | May 2031 | May 2030 | May 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-644 | Cross River Inlet Bridge Rehabilitation | 8 | ORIGINAL EQUIP & FURNISHING | May 2031 | Feb 2032 | May 2031 | Feb 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-644 | Cross River Inlet Bridge Rehabilitation | 9 | SUBSTANTIAL COMPLETION | Feb 2032 | Aug 2032 | Feb 2032 | Aug 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-644 | Cross River Inlet Bridge Rehabilitation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2032 | Nov 2032 | Aug 2032 | Nov 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-UPGRD | UPGRADES AT CSO FACILITIES | 1 | DEVELOP SCOPE | Jun 2021 | Feb 2022 | Jun 2021 | Feb 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-UPGRD | UPGRADES AT CSO FACILITIES | 2 | PRELIMINARY DESIGN | Feb 2022 | Feb 2023 | Feb 2022 | Feb 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-UPGRD | UPGRADES AT CSO FACILITIES | 3 | FINAL DESIGN | Feb 2023 | Aug 2024 | Feb 2023 | Aug 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-UPGRD | UPGRADES AT CSO FACILITIES | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2024 | May 2025 | Aug 2024 | May 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-UPGRD | UPGRADES AT CSO FACILITIES | 5 | CONSTRUCTION TO 25% | May 2025 | May 2026 | May 2025 | May 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-UPGRD | UPGRADES AT CSO FACILITIES | 6 | CONSTRUCTION TO 50% | May 2026 | Apr 2027 | May 2026 | Apr 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-UPGRD | UPGRADES AT CSO FACILITIES | 7 | CONSTRUCTION TO 75% | May 2027 | Apr 2028 | May 2027 | Apr 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-UPGRD | UPGRADES AT CSO FACILITIES | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2028 | Jan 2029 | Apr 2028 | Jan 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-UPGRD | UPGRADES AT CSO FACILITIES | 9 | SUBSTANTIAL COMPLETION | Jan 2029 | Jul 2029 | Jan 2029 | Jul 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-UPGRD | UPGRADES AT CSO FACILITIES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2029 | Oct 2029 | Jul 2029 | Oct 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT3CORR | Repairs & Remediate Corrosion Issues - CT 3 | 1 | DEVELOP SCOPE | Aug 2017 | Oct 2017 | Jul 2016 | Mar 2017
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT3CORR | Repairs & Remediate Corrosion Issues - CT 3 | 2 | PRELIMINARY DESIGN | Oct 2017 | Feb 2018 | Mar 2017 | Mar 2018
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT3CORR | Repairs & Remediate Corrosion Issues - CT 3 | 3 | FINAL DESIGN | Feb 2018 | Aug 2018 | Mar 2018 | Sep 2019
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT3CORR | Repairs & Remediate Corrosion Issues - CT 3 | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2018 | Nov 2018 | Sep 2019 | Jun 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT3CORR | Repairs & Remediate Corrosion Issues - CT 3 | 5 | CONSTRUCTION TO 25% | Nov 2018 | Mar 2019 | Jun 2020 | Jun 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT3CORR | Repairs & Remediate Corrosion Issues - CT 3 | 6 | CONSTRUCTION TO 50% | Mar 2019 | Jul 2019 | Jun 2021 | May 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT3CORR | Repairs & Remediate Corrosion Issues - CT 3 | 7 | CONSTRUCTION TO 75% | Jul 2019 | Nov 2019 | May 2022 | May 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT3CORR | Repairs & Remediate Corrosion Issues - CT 3 | 8 | ORIGINAL EQUIP & FURNISHING | Nov 2019 | Feb 2020 | May 2023 | Feb 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT3CORR | Repairs & Remediate Corrosion Issues - CT 3 | 9 | SUBSTANTIAL COMPLETION | Feb 2020 | Apr 2020 | Feb 2024 | Aug 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT3CORR | Repairs & Remediate Corrosion Issues - CT 3 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2020 | May 2020 | Aug 2028 | Nov 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-194 | Merriman Dam Spillway | 1 | DEVELOP SCOPE | Jun 2008 | Mar 2009 | Jun 2015 | Mar 2016
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-194 | Merriman Dam Spillway | 2 | PRELIMINARY DESIGN | Mar 2009 | Mar 2010 | Mar 2016 | Mar 2017
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-194 | Merriman Dam Spillway | 3 | FINAL DESIGN | Mar 2010 | Aug 2011 | Mar 2017 | Aug 2018
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-194 | Merriman Dam Spillway | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2011 | May 2012 | Aug 2018 | May 2019
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-194 | Merriman Dam Spillway | 5 | CONSTRUCTION TO 25% | May 2012 | May 2013 | May 2019 | May 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-194 | Merriman Dam Spillway | 6 | CONSTRUCTION TO 50% | May 2013 | May 2014 | May 2020 | May 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-194 | Merriman Dam Spillway | 7 | CONSTRUCTION TO 75% | May 2014 | May 2015 | May 2021 | May 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-194 | Merriman Dam Spillway | 8 | ORIGINAL EQUIP & FURNISHING | May 2015 | Feb 2016 | May 2022 | Feb 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-194 | Merriman Dam Spillway | 9 | SUBSTANTIAL COMPLETION | Feb 2016 | Aug 2016 | Feb 2023 | Jul 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-194 | Merriman Dam Spillway | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2016 | Oct 2016 | Jul 2031 | Oct 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-359V | Shaft 4 Gate Valve Replacements | 1 | DEVELOP SCOPE | Jun 2020 | Feb 2021 | Jun 2020 | Feb 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-359V | Shaft 4 Gate Valve Replacements | 2 | PRELIMINARY DESIGN | Feb 2021 | Feb 2022 | Feb 2021 | Feb 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-359V | Shaft 4 Gate Valve Replacements | 3 | FINAL DESIGN | Feb 2022 | Aug 2023 | Feb 2022 | Aug 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-359V | Shaft 4 Gate Valve Replacements | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2023 | May 2024 | Aug 2023 | May 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-359V | Shaft 4 Gate Valve Replacements | 5 | CONSTRUCTION TO 25% | May 2024 | May 2025 | May 2024 | May 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-359V | Shaft 4 Gate Valve Replacements | 6 | CONSTRUCTION TO 50% | May 2025 | Apr 2026 | May 2025 | Apr 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-359V | Shaft 4 Gate Valve Replacements | 7 | CONSTRUCTION TO 75% | May 2026 | Apr 2027 | May 2026 | Apr 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-359V | Shaft 4 Gate Valve Replacements | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2027 | Jan 2028 | Apr 2027 | Jan 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-359V | Shaft 4 Gate Valve Replacements | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Jul 2028 | Jan 2028 | Jul 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-359V | Shaft 4 Gate Valve Replacements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2028 | Oct 2028 | Jul 2028 | Oct 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-397 | Riser Valve Control Mechanism at DA Chambers | 1 | DEVELOP SCOPE | Jun 2020 | Feb 2021 | Jun 2020 | Feb 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-397 | Riser Valve Control Mechanism at DA Chambers | 2 | PRELIMINARY DESIGN | Feb 2021 | Feb 2022 | Feb 2021 | Feb 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-397 | Riser Valve Control Mechanism at DA Chambers | 3 | FINAL DESIGN | Feb 2022 | Aug 2023 | Feb 2022 | Aug 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-397 | Riser Valve Control Mechanism at DA Chambers | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2023 | May 2024 | Aug 2023 | May 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-397 | Riser Valve Control Mechanism at DA Chambers | 5 | CONSTRUCTION TO 25% | May 2024 | May 2025 | May 2024 | May 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-397 | Riser Valve Control Mechanism at DA Chambers | 6 | CONSTRUCTION TO 50% | May 2025 | Apr 2026 | May 2025 | Apr 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-397 | Riser Valve Control Mechanism at DA Chambers | 7 | CONSTRUCTION TO 75% | May 2026 | Apr 2027 | May 2026 | Apr 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-397 | Riser Valve Control Mechanism at DA Chambers | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2027 | Jan 2028 | Apr 2027 | Jan 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-397 | Riser Valve Control Mechanism at DA Chambers | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Jul 2028 | Jan 2028 | Jul 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-397 | Riser Valve Control Mechanism at DA Chambers | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2028 | Oct 2028 | Jul 2028 | Oct 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-450 | Downsville Water Connection | 1 | DEVELOP SCOPE | Jun 2021 | Feb 2022 | Jun 2021 | Feb 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-450 | Downsville Water Connection | 2 | PRELIMINARY DESIGN | Feb 2022 | Feb 2023 | Feb 2022 | Feb 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-450 | Downsville Water Connection | 3 | FINAL DESIGN | Feb 2023 | Aug 2024 | Feb 2023 | Aug 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-450 | Downsville Water Connection | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2024 | May 2025 | Aug 2024 | May 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-450 | Downsville Water Connection | 5 | CONSTRUCTION TO 25% | May 2025 | May 2026 | May 2025 | May 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-450 | Downsville Water Connection | 6 | CONSTRUCTION TO 50% | May 2026 | Apr 2027 | May 2026 | Apr 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-450 | Downsville Water Connection | 7 | CONSTRUCTION TO 75% | May 2027 | Apr 2028 | May 2027 | Apr 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-450 | Downsville Water Connection | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2028 | Jan 2029 | Apr 2028 | Jan 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-450 | Downsville Water Connection | 9 | SUBSTANTIAL COMPLETION | Jan 2029 | Jul 2029 | Jan 2029 | Jul 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-450 | Downsville Water Connection | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2029 | Oct 2029 | Jul 2029 | Oct 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-457 | Route 55A reconstruction and paving | 1 | DEVELOP SCOPE | Jul 2022 | Mar 2023 | Jul 2022 | Mar 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-457 | Route 55A reconstruction and paving | 2 | PRELIMINARY DESIGN | Mar 2023 | Mar 2024 | Mar 2023 | Mar 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-457 | Route 55A reconstruction and paving | 3 | FINAL DESIGN | Mar 2024 | Sep 2025 | Mar 2024 | Sep 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-457 | Route 55A reconstruction and paving | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2025 | Jun 2026 | Sep 2025 | Jun 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-457 | Route 55A reconstruction and paving | 5 | CONSTRUCTION TO 25% | Jun 2026 | Jun 2027 | Jun 2026 | Jun 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-457 | Route 55A reconstruction and paving | 6 | CONSTRUCTION TO 50% | Jun 2027 | May 2028 | Jun 2027 | May 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-457 | Route 55A reconstruction and paving | 7 | CONSTRUCTION TO 75% | May 2028 | May 2029 | May 2028 | May 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-457 | Route 55A reconstruction and paving | 8 | ORIGINAL EQUIP & FURNISHING | May 2029 | Feb 2030 | May 2029 | Feb 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-457 | Route 55A reconstruction and paving | 9 | SUBSTANTIAL COMPLETION | Feb 2030 | Aug 2030 | Feb 2030 | Aug 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-457 | Route 55A reconstruction and paving | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2030 | Nov 2030 | Aug 2030 | Nov 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-DRA | DELAWARE-RONDOUT AQUEDUCT (PARALLEL TUNNEL TO RWBT) | 1 | DEVELOP SCOPE | Sep 2008 | May 2009 | Jun 2016 | Feb 2017
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-DRA | DELAWARE-RONDOUT AQUEDUCT (PARALLEL TUNNEL TO RWBT) | 2 | PRELIMINARY DESIGN | May 2009 | May 2010 | Feb 2017 | Feb 2018
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-DRA | DELAWARE-RONDOUT AQUEDUCT (PARALLEL TUNNEL TO RWBT) | 3 | FINAL DESIGN | May 2010 | Nov 2011 | Feb 2018 | Aug 2019
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-DRA | DELAWARE-RONDOUT AQUEDUCT (PARALLEL TUNNEL TO RWBT) | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2011 | Aug 2012 | Aug 2019 | May 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-DRA | DELAWARE-RONDOUT AQUEDUCT (PARALLEL TUNNEL TO RWBT) | 5 | CONSTRUCTION TO 25% | Aug 2012 | Aug 2013 | May 2020 | May 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-DRA | DELAWARE-RONDOUT AQUEDUCT (PARALLEL TUNNEL TO RWBT) | 6 | CONSTRUCTION TO 50% | Aug 2013 | Jul 2014 | May 2021 | Apr 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-DRA | DELAWARE-RONDOUT AQUEDUCT (PARALLEL TUNNEL TO RWBT) | 7 | CONSTRUCTION TO 75% | Aug 2014 | Jul 2015 | May 2022 | Apr 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-DRA | DELAWARE-RONDOUT AQUEDUCT (PARALLEL TUNNEL TO RWBT) | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2015 | Apr 2016 | Apr 2023 | Jan 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-DRA | DELAWARE-RONDOUT AQUEDUCT (PARALLEL TUNNEL TO RWBT) | 9 | SUBSTANTIAL COMPLETION | Apr 2016 | Oct 2024 | Jan 2024 | Jul 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-DRA | DELAWARE-RONDOUT AQUEDUCT (PARALLEL TUNNEL TO RWBT) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2024 | Jan 2025 | Jul 2032 | Oct 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | 1 | DEVELOP SCOPE | Jun 2025 | Sep 2025 | Jan 2023 | Apr 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | 2 | PRELIMINARY DESIGN | Sep 2025 | Mar 2026 | May 2023 | Oct 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | 3 | FINAL DESIGN | Mar 2026 | Sep 2027 | Oct 2023 | Apr 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2027 | Mar 2028 | Apr 2025 | Oct 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | 5 | CONSTRUCTION TO 25% | Mar 2028 | Dec 2028 | Oct 2025 | Aug 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | 6 | CONSTRUCTION TO 50% | Jan 2029 | Oct 2029 | Jan 2029 | Oct 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | 7 | CONSTRUCTION TO 75% | Oct 2029 | Jul 2030 | Oct 2029 | Jul 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2030 | Oct 2030 | Jul 2030 | Oct 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | 9 | SUBSTANTIAL COMPLETION | Oct 2030 | Dec 2030 | Oct 2030 | Dec 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2030 | Mar 2031 | Dec 2030 | Mar 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | 11 | DEVELOP SCOPE | Dec 2030 | Mar 2031 | Mar 2031 | Jun 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | 12 | PRELIMINARY DESIGN | Dec 2030 | Mar 2031 | Jun 2031 | Oct 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | 13 | FINAL DESIGN | Dec 2030 | Mar 2031 | Oct 2031 | Apr 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | 14 | BID AWARD AND REGISTER CONTRCT | Dec 2030 | Mar 2031 | Apr 2032 | Jul 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | 15 | CONSTRUCTION TO 25% | Dec 2030 | Mar 2031 | Jul 2032 | Oct 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | 16 | CONSTRUCTION TO 50% | Dec 2030 | Mar 2031 | Nov 2032 | Feb 2033
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | 17 | CONSTRUCTION TO 75% | Dec 2030 | Mar 2031 | Mar 2033 | Jun 2033
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | 18 | ORIGINAL EQUIP & FURNISHING | Dec 2030 | Mar 2031 | Jun 2033 | Sep 2033
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | 19 | SUBSTANTIAL COMPLETION | Dec 2030 | Mar 2031 | Sep 2033 | Nov 2033
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | 20 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2030 | Mar 2031 | Nov 2033 | Dec 2033
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | 21 | DEVELOP SCOPE | Dec 2030 | Mar 2031 | Dec 2033 | Apr 2034
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | 22 | PRELIMINARY DESIGN | Dec 2030 | Mar 2031 | Apr 2034 | Oct 2034
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | 23 | FINAL DESIGN | Dec 2030 | Mar 2031 | Oct 2034 | Apr 2036
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | 24 | BID AWARD AND REGISTER CONTRCT | Dec 2030 | Mar 2031 | Apr 2036 | Oct 2036
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | 25 | CONSTRUCTION TO 25% | Dec 2030 | Mar 2031 | Oct 2036 | Jul 2037
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | 26 | CONSTRUCTION TO 50% | Dec 2030 | Mar 2031 | Jul 2037 | May 2038
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | 27 | CONSTRUCTION TO 75% | Dec 2030 | Mar 2031 | May 2038 | Feb 2039
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | 28 | ORIGINAL EQUIP & FURNISHING | Dec 2030 | Mar 2031 | Feb 2039 | May 2039
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | 29 | SUBSTANTIAL COMPLETION | Dec 2030 | Mar 2031 | May 2039 | Jul 2039
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | 30 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2030 | Mar 2031 | Jul 2039 | Oct 2039
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-GUN25 | Emergency Guniting of Sewers, Citywide | 1 | DEVELOP SCOPE | Jan 2023 | Apr 2023 | Jan 2023 | Apr 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-GUN25 | Emergency Guniting of Sewers, Citywide | 2 | PRELIMINARY DESIGN | Apr 2023 | Aug 2023 | Apr 2023 | Aug 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-GUN25 | Emergency Guniting of Sewers, Citywide | 3 | FINAL DESIGN | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-GUN25 | Emergency Guniting of Sewers, Citywide | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2024 | May 2024 | Feb 2024 | May 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-GUN25 | Emergency Guniting of Sewers, Citywide | 5 | CONSTRUCTION TO 25% | May 2024 | Aug 2024 | May 2024 | Aug 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-GUN25 | Emergency Guniting of Sewers, Citywide | 6 | CONSTRUCTION TO 50% | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-GUN25 | Emergency Guniting of Sewers, Citywide | 7 | CONSTRUCTION TO 75% | Dec 2024 | Apr 2025 | Dec 2024 | Apr 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-GUN25 | Emergency Guniting of Sewers, Citywide | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2025 | Jul 2025 | Apr 2025 | Jul 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-GUN25 | Emergency Guniting of Sewers, Citywide | 9 | SUBSTANTIAL COMPLETION | Jul 2025 | Sep 2025 | Jul 2025 | Sep 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-GUN25 | Emergency Guniting of Sewers, Citywide | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Oct 2025 | Sep 2025 | Oct 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC25KR | Emergency Sewer Lining Contract, Brooklyn and Staten Island | 1 | DEVELOP SCOPE | Jan 2023 | Apr 2023 | Jan 2023 | Apr 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC25KR | Emergency Sewer Lining Contract, Brooklyn and Staten Island | 2 | PRELIMINARY DESIGN | Apr 2023 | Aug 2023 | Apr 2023 | Aug 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC25KR | Emergency Sewer Lining Contract, Brooklyn and Staten Island | 3 | FINAL DESIGN | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC25KR | Emergency Sewer Lining Contract, Brooklyn and Staten Island | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2024 | May 2024 | Feb 2024 | May 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC25KR | Emergency Sewer Lining Contract, Brooklyn and Staten Island | 5 | CONSTRUCTION TO 25% | May 2024 | Aug 2024 | May 2024 | Aug 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC25KR | Emergency Sewer Lining Contract, Brooklyn and Staten Island | 6 | CONSTRUCTION TO 50% | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC25KR | Emergency Sewer Lining Contract, Brooklyn and Staten Island | 7 | CONSTRUCTION TO 75% | Dec 2024 | Apr 2025 | Dec 2024 | Apr 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC25KR | Emergency Sewer Lining Contract, Brooklyn and Staten Island | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2025 | Jul 2025 | Apr 2025 | Jul 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC25KR | Emergency Sewer Lining Contract, Brooklyn and Staten Island | 9 | SUBSTANTIAL COMPLETION | Jul 2025 | Sep 2025 | Jul 2025 | Sep 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC25KR | Emergency Sewer Lining Contract, Brooklyn and Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Oct 2025 | Sep 2025 | Oct 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC25QX | Emergency Sewer Lining Contract, Queens and Bronx | 1 | DEVELOP SCOPE | Jan 2023 | Apr 2023 | Jan 2023 | Apr 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC25QX | Emergency Sewer Lining Contract, Queens and Bronx | 2 | PRELIMINARY DESIGN | Apr 2023 | Aug 2023 | Apr 2023 | Aug 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC25QX | Emergency Sewer Lining Contract, Queens and Bronx | 3 | FINAL DESIGN | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC25QX | Emergency Sewer Lining Contract, Queens and Bronx | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2024 | May 2024 | Feb 2024 | May 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC25QX | Emergency Sewer Lining Contract, Queens and Bronx | 5 | CONSTRUCTION TO 25% | May 2024 | Aug 2024 | May 2024 | Aug 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC25QX | Emergency Sewer Lining Contract, Queens and Bronx | 6 | CONSTRUCTION TO 50% | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC25QX | Emergency Sewer Lining Contract, Queens and Bronx | 7 | CONSTRUCTION TO 75% | Dec 2024 | Apr 2025 | Dec 2024 | Apr 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC25QX | Emergency Sewer Lining Contract, Queens and Bronx | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2025 | Jul 2025 | Apr 2025 | Jul 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC25QX | Emergency Sewer Lining Contract, Queens and Bronx | 9 | SUBSTANTIAL COMPLETION | Jul 2025 | Sep 2025 | Jul 2025 | Sep 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC25QX | Emergency Sewer Lining Contract, Queens and Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Oct 2025 | Sep 2025 | Oct 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEC25 | Emergency Reconstruction of Sewers, Citywide | 1 | DEVELOP SCOPE | Jan 2023 | Apr 2023 | Jan 2023 | Apr 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEC25 | Emergency Reconstruction of Sewers, Citywide | 2 | PRELIMINARY DESIGN | Apr 2023 | Aug 2023 | Apr 2023 | Aug 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEC25 | Emergency Reconstruction of Sewers, Citywide | 3 | FINAL DESIGN | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEC25 | Emergency Reconstruction of Sewers, Citywide | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2024 | May 2024 | Feb 2024 | May 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEC25 | Emergency Reconstruction of Sewers, Citywide | 5 | CONSTRUCTION TO 25% | May 2024 | Aug 2024 | May 2024 | Aug 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEC25 | Emergency Reconstruction of Sewers, Citywide | 6 | CONSTRUCTION TO 50% | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEC25 | Emergency Reconstruction of Sewers, Citywide | 7 | CONSTRUCTION TO 75% | Dec 2024 | Apr 2025 | Dec 2024 | Apr 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEC25 | Emergency Reconstruction of Sewers, Citywide | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2025 | Jul 2025 | Apr 2025 | Jul 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEC25 | Emergency Reconstruction of Sewers, Citywide | 9 | SUBSTANTIAL COMPLETION | Jul 2025 | Sep 2025 | Jul 2025 | Sep 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEC25 | Emergency Reconstruction of Sewers, Citywide | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Oct 2025 | Sep 2025 | Oct 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-WMC25 | Citywide Emergency Reconstruction of Water Mains | 1 | DEVELOP SCOPE | Jan 2023 | Apr 2023 | Jan 2023 | Apr 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-WMC25 | Citywide Emergency Reconstruction of Water Mains | 2 | PRELIMINARY DESIGN | Apr 2023 | Aug 2023 | Apr 2023 | Aug 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-WMC25 | Citywide Emergency Reconstruction of Water Mains | 3 | FINAL DESIGN | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-WMC25 | Citywide Emergency Reconstruction of Water Mains | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2024 | May 2024 | Feb 2024 | May 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-WMC25 | Citywide Emergency Reconstruction of Water Mains | 5 | CONSTRUCTION TO 25% | May 2024 | Aug 2024 | May 2024 | Aug 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-WMC25 | Citywide Emergency Reconstruction of Water Mains | 6 | CONSTRUCTION TO 50% | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-WMC25 | Citywide Emergency Reconstruction of Water Mains | 7 | CONSTRUCTION TO 75% | Dec 2024 | Apr 2025 | Dec 2024 | Apr 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-WMC25 | Citywide Emergency Reconstruction of Water Mains | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2025 | Jul 2025 | Apr 2025 | Jul 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-WMC25 | Citywide Emergency Reconstruction of Water Mains | 9 | SUBSTANTIAL COMPLETION | Jul 2025 | Sep 2025 | Jul 2025 | Sep 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-WMC25 | Citywide Emergency Reconstruction of Water Mains | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Oct 2025 | Sep 2025 | Oct 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FMC-LEAD | LEAD PAINT ABATEMENT & REMOVAL | 1 | DEVELOP SCOPE | Oct 2010 | Feb 2011 | Oct 2018 | Feb 2019
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FMC-LEAD | LEAD PAINT ABATEMENT & REMOVAL | 2 | PRELIMINARY DESIGN | Feb 2011 | Aug 2011 | Feb 2019 | Aug 2019
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FMC-LEAD | LEAD PAINT ABATEMENT & REMOVAL | 3 | FINAL DESIGN | Aug 2011 | Feb 2013 | Aug 2019 | Feb 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FMC-LEAD | LEAD PAINT ABATEMENT & REMOVAL | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2013 | Aug 2013 | Feb 2021 | Aug 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FMC-LEAD | LEAD PAINT ABATEMENT & REMOVAL | 5 | CONSTRUCTION TO 25% | Aug 2013 | May 2014 | Aug 2021 | May 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FMC-LEAD | LEAD PAINT ABATEMENT & REMOVAL | 6 | CONSTRUCTION TO 50% | Jun 2014 | Mar 2015 | Jun 2022 | Mar 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FMC-LEAD | LEAD PAINT ABATEMENT & REMOVAL | 7 | CONSTRUCTION TO 75% | Mar 2015 | Dec 2015 | Mar 2023 | Dec 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FMC-LEAD | LEAD PAINT ABATEMENT & REMOVAL | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2015 | Mar 2016 | Dec 2024 | Mar 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FMC-LEAD | LEAD PAINT ABATEMENT & REMOVAL | 9 | SUBSTANTIAL COMPLETION | Mar 2016 | May 2016 | Mar 2025 | May 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FMC-LEAD | LEAD PAINT ABATEMENT & REMOVAL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2016 | Aug 2016 | May 2025 | Aug 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CON-AS | GI - DPR ONSITE GREEN INFRASTRUCTURE ASPHALT | 1 | FINAL DESIGN | May 2022 | Oct 2023 | May 2022 | Oct 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CON-AS | GI - DPR ONSITE GREEN INFRASTRUCTURE ASPHALT | 2 | CONSTRUCTION TO 25% | Oct 2023 | Jun 2024 | Oct 2023 | Jun 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CON-AS | GI - DPR ONSITE GREEN INFRASTRUCTURE ASPHALT | 3 | CONSTRUCTION TO 50% | Jun 2024 | Feb 2025 | Jun 2024 | Feb 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CON-AS | GI - DPR ONSITE GREEN INFRASTRUCTURE ASPHALT | 4 | CONSTRUCTION TO 75% | Feb 2025 | Oct 2025 | Feb 2025 | Oct 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-3 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 1 | FINAL DESIGN | Jun 2024 | Dec 2025 | Jun 2024 | Dec 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-3 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 2 | CONSTRUCTION TO 25% | Dec 2025 | Aug 2026 | Dec 2025 | Aug 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-3 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 3 | CONSTRUCTION TO 50% | Aug 2026 | Apr 2027 | Aug 2026 | Apr 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-3 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 4 | CONSTRUCTION TO 75% | Apr 2027 | Dec 2027 | Apr 2027 | Dec 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-4 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 1 | FINAL DESIGN | Jun 2024 | Dec 2025 | Jun 2024 | Dec 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-4 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 2 | CONSTRUCTION TO 25% | Dec 2025 | Aug 2026 | Dec 2025 | Aug 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-4 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 3 | CONSTRUCTION TO 50% | Aug 2026 | Apr 2027 | Aug 2026 | Apr 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-4 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 4 | CONSTRUCTION TO 75% | Apr 2027 | Dec 2027 | Apr 2027 | Dec 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-5 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 1 | FINAL DESIGN | Jul 2024 | Dec 2025 | Jul 2024 | Dec 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-5 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 2 | CONSTRUCTION TO 25% | Dec 2025 | Aug 2026 | Dec 2025 | Aug 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-5 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 3 | CONSTRUCTION TO 50% | Aug 2026 | Apr 2027 | Aug 2026 | Apr 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-5 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 4 | CONSTRUCTION TO 75% | Apr 2027 | Dec 2027 | Apr 2027 | Dec 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-6 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 1 | DEVELOP SCOPE | Jan 2024 | Sep 2024 | Jan 2024 | Sep 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-6 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 2 | PRELIMINARY DESIGN | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-6 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 3 | FINAL DESIGN | Sep 2025 | Mar 2027 | Sep 2025 | Mar 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-6 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2027 | Dec 2027 | Mar 2027 | Dec 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-6 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 5 | CONSTRUCTION TO 25% | Dec 2027 | Dec 2028 | Dec 2027 | Dec 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-6 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 6 | CONSTRUCTION TO 50% | Dec 2028 | Nov 2029 | Dec 2028 | Nov 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-6 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 7 | CONSTRUCTION TO 75% | Nov 2029 | Nov 2030 | Nov 2029 | Nov 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-6 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 8 | ORIGINAL EQUIP & FURNISHING | Nov 2030 | Aug 2031 | Nov 2030 | Aug 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-6 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 9 | SUBSTANTIAL COMPLETION | Aug 2031 | Feb 2032 | Aug 2031 | Feb 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-6 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2032 | May 2032 | Feb 2032 | May 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-7 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 1 | FINAL DESIGN | Jun 2025 | Nov 2026 | Jun 2025 | Nov 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-7 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 2 | CONSTRUCTION TO 25% | Nov 2026 | Jul 2027 | Nov 2026 | Jul 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-7 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 3 | CONSTRUCTION TO 50% | Jul 2027 | Mar 2028 | Jul 2027 | Mar 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-7 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | 4 | CONSTRUCTION TO 75% | Mar 2028 | Nov 2028 | Mar 2028 | Nov 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | 1 | DEVELOP SCOPE | Oct 2011 | Dec 2011 | Jan 2011 | Oct 2011
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | 2 | PRELIMINARY DESIGN | Dec 2011 | Apr 2012 | Oct 2011 | Oct 2012
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | 3 | FINAL DESIGN | Apr 2012 | Oct 2012 | Oct 2012 | Apr 2014
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2012 | Jan 2013 | Apr 2014 | Jan 2015
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | 5 | CONSTRUCTION TO 25% | Jan 2013 | May 2013 | Jan 2015 | Jan 2016
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | 6 | CONSTRUCTION TO 50% | May 2013 | Sep 2013 | Jan 2016 | Dec 2016
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | 7 | CONSTRUCTION TO 75% | Sep 2013 | Jan 2014 | Dec 2016 | Dec 2017
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2014 | Apr 2014 | Dec 2017 | Sep 2018
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | 9 | SUBSTANTIAL COMPLETION | Apr 2014 | Jun 2014 | Sep 2018 | Mar 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2014 | Jul 2014 | Mar 2023 | Jun 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | 11 | DEVELOP SCOPE | Jun 2014 | Jul 2014 | Jun 2023 | Mar 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | 12 | PRELIMINARY DESIGN | Jun 2014 | Jul 2014 | Mar 2024 | Mar 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | 13 | FINAL DESIGN | Jun 2014 | Jul 2014 | Mar 2025 | Aug 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | 14 | BID AWARD AND REGISTER CONTRCT | Jun 2014 | Jul 2014 | Aug 2026 | May 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | 15 | CONSTRUCTION TO 25% | Jun 2014 | Jul 2014 | May 2027 | May 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | 16 | CONSTRUCTION TO 50% | Jun 2014 | Jul 2014 | May 2028 | May 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | 17 | CONSTRUCTION TO 75% | Jun 2014 | Jul 2014 | May 2029 | May 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | 18 | ORIGINAL EQUIP & FURNISHING | Jun 2014 | Jul 2014 | May 2030 | Feb 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | 19 | SUBSTANTIAL COMPLETION | Jun 2014 | Jul 2014 | Feb 2031 | Jul 2039
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | 20 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2014 | Jul 2014 | Aug 2039 | Oct 2039
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-HPD | GI - FUNDING FOR HPD GREEN INFRASTRUCTURE PROJECTS | 1 | DEVELOP SCOPE | Nov 2011 | Jan 2012 | Nov 2022 | Jan 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-HPD | GI - FUNDING FOR HPD GREEN INFRASTRUCTURE PROJECTS | 2 | PRELIMINARY DESIGN | Jan 2012 | May 2012 | Jan 2023 | May 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-HPD | GI - FUNDING FOR HPD GREEN INFRASTRUCTURE PROJECTS | 3 | FINAL DESIGN | May 2012 | Nov 2012 | May 2023 | Nov 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-HPD | GI - FUNDING FOR HPD GREEN INFRASTRUCTURE PROJECTS | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2012 | Feb 2013 | Nov 2023 | Feb 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-HPD | GI - FUNDING FOR HPD GREEN INFRASTRUCTURE PROJECTS | 5 | CONSTRUCTION TO 25% | Feb 2013 | Jun 2013 | Feb 2024 | Jun 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-HPD | GI - FUNDING FOR HPD GREEN INFRASTRUCTURE PROJECTS | 6 | CONSTRUCTION TO 50% | Jun 2013 | Oct 2013 | Jun 2024 | Oct 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-HPD | GI - FUNDING FOR HPD GREEN INFRASTRUCTURE PROJECTS | 7 | CONSTRUCTION TO 75% | Oct 2013 | Feb 2014 | Oct 2024 | Feb 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-HPD | GI - FUNDING FOR HPD GREEN INFRASTRUCTURE PROJECTS | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2014 | May 2014 | Feb 2025 | May 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-HPD | GI - FUNDING FOR HPD GREEN INFRASTRUCTURE PROJECTS | 9 | SUBSTANTIAL COMPLETION | May 2014 | Jul 2014 | May 2025 | Jul 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-HPD | GI - FUNDING FOR HPD GREEN INFRASTRUCTURE PROJECTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2014 | Aug 2014 | Jul 2025 | Aug 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | HVR-500 | Hillview Police Precinct | 1 | DEVELOP SCOPE | Jun 2021 | Feb 2022 | Jun 2021 | Feb 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | HVR-500 | Hillview Police Precinct | 2 | PRELIMINARY DESIGN | Feb 2022 | Feb 2023 | Feb 2022 | Feb 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | HVR-500 | Hillview Police Precinct | 3 | FINAL DESIGN | Feb 2023 | Aug 2024 | Feb 2023 | Aug 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | HVR-500 | Hillview Police Precinct | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2024 | May 2025 | Aug 2024 | May 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | HVR-500 | Hillview Police Precinct | 5 | CONSTRUCTION TO 25% | May 2025 | May 2026 | May 2025 | May 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | HVR-500 | Hillview Police Precinct | 6 | CONSTRUCTION TO 50% | May 2026 | Apr 2027 | May 2026 | Apr 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | HVR-500 | Hillview Police Precinct | 7 | CONSTRUCTION TO 75% | May 2027 | Apr 2028 | May 2027 | Apr 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | HVR-500 | Hillview Police Precinct | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2028 | Jan 2029 | Apr 2028 | Jan 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | HVR-500 | Hillview Police Precinct | 9 | SUBSTANTIAL COMPLETION | Jan 2029 | Jul 2029 | Jan 2029 | Jul 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | HVR-500 | Hillview Police Precinct | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2029 | Oct 2029 | Jul 2029 | Oct 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | IN-CITYLS | Agency Proposed Outyear Projects | 1 | DEVELOP SCOPE | Aug 2030 | Nov 2030 | Aug 2030 | Nov 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | IN-CITYLS | Agency Proposed Outyear Projects | 2 | PRELIMINARY DESIGN | Nov 2030 | Mar 2031 | Nov 2030 | Mar 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | IN-CITYLS | Agency Proposed Outyear Projects | 3 | FINAL DESIGN | Mar 2031 | Sep 2031 | Mar 2031 | Sep 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | IN-CITYLS | Agency Proposed Outyear Projects | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2031 | Dec 2031 | Sep 2031 | Dec 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | IN-CITYLS | Agency Proposed Outyear Projects | 5 | CONSTRUCTION TO 25% | Dec 2031 | Apr 2032 | Dec 2031 | Apr 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | IN-CITYLS | Agency Proposed Outyear Projects | 6 | CONSTRUCTION TO 50% | Apr 2032 | Aug 2032 | Apr 2032 | Aug 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | IN-CITYLS | Agency Proposed Outyear Projects | 7 | CONSTRUCTION TO 75% | Aug 2032 | Dec 2032 | Aug 2032 | Dec 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | IN-CITYLS | Agency Proposed Outyear Projects | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2032 | Mar 2033 | Dec 2032 | Mar 2033
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | IN-CITYLS | Agency Proposed Outyear Projects | 9 | SUBSTANTIAL COMPLETION | Mar 2033 | May 2033 | Mar 2033 | May 2033
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | IN-CITYLS | Agency Proposed Outyear Projects | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2033 | Jun 2033 | May 2033 | Jun 2033
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JFK-12 | WATER METER INSTALLATION AT JFK AIRPORT | 1 | PRE-CONSTRUCTION MOBILIZATION | Jul 2016 | Jun 2017 | Jul 2016 | Jun 2017
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JFK-12 | WATER METER INSTALLATION AT JFK AIRPORT | 2 | ON-SITE CONSTRUCTION MANAGEMEN | Jun 2017 | May 2023 | Jun 2017 | May 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JFK-12 | WATER METER INSTALLATION AT JFK AIRPORT | 3 | POST-CONSTRUCTION CLOSE-OUT | May 2023 | May 2024 | May 2023 | May 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15BWS | Facilities Improvement Program | 1 | DEVELOP SCOPE | Jan 2015 | Mar 2015
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15BWS | Facilities Improvement Program | 2 | PRELIMINARY DESIGN | Apr 2015 | Jul 2015
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15BWS | Facilities Improvement Program | 3 | FINAL DESIGN | Jul 2015 | Jan 2016
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15BWS | Facilities Improvement Program | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2016 | Apr 2016
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15BWS | Facilities Improvement Program | 5 | CONSTRUCTION TO 25% | Apr 2016 | Aug 2016
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15BWS | Facilities Improvement Program | 6 | CONSTRUCTION TO 50% | Aug 2016 | Dec 2016
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15BWS | Facilities Improvement Program | 7 | CONSTRUCTION TO 75% | Dec 2016 | Apr 2017
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15BWS | Facilities Improvement Program | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2017 | Jul 2017
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15BWS | Facilities Improvement Program | 9 | SUBSTANTIAL COMPLETION | Jul 2017 | Sep 2017
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15BWS | Facilities Improvement Program | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2017 | Oct 2017
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 1 | DEVELOP SCOPE | Jun 2015 | Sep 2015 | Jun 2015 | Sep 2015
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 2 | PRELIMINARY DESIGN | Sep 2015 | Jan 2016 | Sep 2015 | Jan 2016
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 3 | FINAL DESIGN | Jan 2016 | Jul 2016 | Jan 2016 | Jul 2016
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Oct 2016 | Jul 2016 | Oct 2016
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 5 | CONSTRUCTION TO 25% | Oct 2016 | Feb 2017 | Oct 2016 | Feb 2017
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 6 | CONSTRUCTION TO 50% | Feb 2017 | Jun 2017 | Feb 2017 | Jun 2017
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 7 | CONSTRUCTION TO 75% | Jun 2017 | Oct 2017 | Jun 2017 | Oct 2017
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2017 | Jan 2018 | Oct 2017 | Jan 2018
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 9 | SUBSTANTIAL COMPLETION | Jan 2018 | Mar 2018 | Jan 2018 | Mar 2018
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2018 | Apr 2018 | Mar 2018 | Apr 2018
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-22-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 1 | FINAL DESIGN | Jun 2022 | Nov 2023 | Jun 2022 | Nov 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-22-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 2 | CONSTRUCTION TO 25% | Nov 2023 | Jul 2024 | Nov 2023 | Jul 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-22-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 3 | CONSTRUCTION TO 50% | Jul 2024 | Mar 2025 | Jul 2024 | Mar 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-22-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 4 | CONSTRUCTION TO 75% | Mar 2025 | Nov 2025 | Mar 2025 | Nov 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-24-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 1 | FINAL DESIGN | Jun 2024 | Nov 2025 | Jun 2024 | Nov 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-24-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 2 | CONSTRUCTION TO 25% | Nov 2025 | Jul 2026 | Nov 2025 | Jul 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-24-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 3 | CONSTRUCTION TO 50% | Jul 2026 | Mar 2027 | Jul 2026 | Mar 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-24-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 4 | CONSTRUCTION TO 75% | Mar 2027 | Nov 2027 | Mar 2027 | Nov 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-25-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 1 | FINAL DESIGN | Jun 2025 | Nov 2026 | Jun 2025 | Nov 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-25-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 2 | CONSTRUCTION TO 25% | Nov 2026 | Jul 2027 | Nov 2026 | Jul 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-25-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 3 | CONSTRUCTION TO 50% | Jul 2027 | Mar 2028 | Jul 2027 | Mar 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-25-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 4 | CONSTRUCTION TO 75% | Mar 2028 | Nov 2028 | Mar 2028 | Nov 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-26-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 1 | FINAL DESIGN | Jun 2026 | Nov 2027 | Jun 2026 | Nov 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-26-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 2 | CONSTRUCTION TO 25% | Nov 2027 | Jul 2028 | Nov 2027 | Jul 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-26-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 3 | CONSTRUCTION TO 50% | Jul 2028 | Mar 2029 | Jul 2028 | Mar 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-26-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 4 | CONSTRUCTION TO 75% | Mar 2029 | Nov 2029 | Mar 2029 | Nov 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-27-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 1 | FINAL DESIGN | Jun 2027 | Nov 2028 | Jun 2027 | Nov 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-27-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 2 | CONSTRUCTION TO 25% | Nov 2028 | Jul 2029 | Nov 2028 | Jul 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-27-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 3 | CONSTRUCTION TO 50% | Jul 2029 | Mar 2030 | Jul 2029 | Mar 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-27-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 4 | CONSTRUCTION TO 75% | Mar 2030 | Nov 2030 | Mar 2030 | Nov 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-28-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 1 | FINAL DESIGN | Jul 2027 | Dec 2028 | Jul 2027 | Dec 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-28-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 2 | CONSTRUCTION TO 25% | Dec 2028 | Aug 2029 | Dec 2028 | Aug 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-28-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 3 | CONSTRUCTION TO 50% | Aug 2029 | Apr 2030 | Aug 2029 | Apr 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-28-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 4 | CONSTRUCTION TO 75% | Apr 2030 | Dec 2030 | Apr 2030 | Dec 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-29-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 1 | FINAL DESIGN | Jul 2028 | Dec 2029 | May 2028 | Oct 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-29-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 2 | CONSTRUCTION TO 25% | Dec 2029 | Aug 2030 | Oct 2029 | Jun 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-29-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 3 | CONSTRUCTION TO 50% | Aug 2030 | Apr 2031 | Jun 2030 | Feb 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-29-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 4 | CONSTRUCTION TO 75% | Apr 2031 | Dec 2031 | Feb 2031 | Oct 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-30-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 1 | FINAL DESIGN | Jun 2030 | Nov 2031 | Jun 2030 | Nov 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-30-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 2 | CONSTRUCTION TO 25% | Nov 2031 | Jul 2032 | Nov 2031 | Jul 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-30-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 3 | CONSTRUCTION TO 50% | Jul 2032 | Mar 2033 | Jul 2032 | Mar 2033
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-30-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 4 | CONSTRUCTION TO 75% | Mar 2033 | Nov 2033 | Mar 2033 | Nov 2033
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-31-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 1 | FINAL DESIGN | Jun 2031 | Nov 2032 | Jun 2031 | Nov 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-31-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 2 | CONSTRUCTION TO 25% | Nov 2032 | Jul 2033 | Nov 2032 | Jul 2033
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-31-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 3 | CONSTRUCTION TO 50% | Jul 2033 | Mar 2034 | Jul 2033 | Mar 2034
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-31-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 4 | CONSTRUCTION TO 75% | Mar 2034 | Nov 2034 | Mar 2034 | Nov 2034
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWS | BWS JOC Contracts (E-O-H & W-O-H) | 1 | DEVELOP SCOPE | Mar 2012 | Nov 2012 | Mar 2016 | Dec 2016
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWS | BWS JOC Contracts (E-O-H & W-O-H) | 2 | PRELIMINARY DESIGN | Nov 2012 | Nov 2013 | Dec 2016 | Dec 2017
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWS | BWS JOC Contracts (E-O-H & W-O-H) | 3 | FINAL DESIGN | Nov 2013 | May 2015 | Dec 2017 | May 2019
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWS | BWS JOC Contracts (E-O-H & W-O-H) | 4 | BID AWARD AND REGISTER CONTRCT | May 2015 | Feb 2016 | May 2019 | Feb 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWS | BWS JOC Contracts (E-O-H & W-O-H) | 5 | CONSTRUCTION TO 25% | Feb 2016 | Feb 2017 | Feb 2020 | Feb 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWS | BWS JOC Contracts (E-O-H & W-O-H) | 6 | CONSTRUCTION TO 50% | Feb 2017 | Jan 2018 | Feb 2021 | Feb 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWS | BWS JOC Contracts (E-O-H & W-O-H) | 7 | CONSTRUCTION TO 75% | Jan 2018 | Jan 2019 | Feb 2022 | Feb 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWS | BWS JOC Contracts (E-O-H & W-O-H) | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2019 | Oct 2019 | Feb 2023 | Oct 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWS | BWS JOC Contracts (E-O-H & W-O-H) | 9 | SUBSTANTIAL COMPLETION | Oct 2019 | Apr 2020 | Nov 2023 | Apr 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWS | BWS JOC Contracts (E-O-H & W-O-H) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2020 | Jul 2020 | Apr 2029 | Jul 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWSO | BWSO Facilities Improvement Program | 1 | DEVELOP SCOPE | Jun 2019 | Feb 2020 | Jun 2019 | Feb 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWSO | BWSO Facilities Improvement Program | 2 | PRELIMINARY DESIGN | Feb 2020 | Feb 2021 | Feb 2020 | Feb 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWSO | BWSO Facilities Improvement Program | 3 | FINAL DESIGN | Feb 2021 | Aug 2022 | Feb 2021 | Aug 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWSO | BWSO Facilities Improvement Program | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2022 | May 2023 | Aug 2022 | May 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWSO | BWSO Facilities Improvement Program | 5 | CONSTRUCTION TO 25% | May 2023 | May 2024 | May 2023 | May 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWSO | BWSO Facilities Improvement Program | 6 | CONSTRUCTION TO 50% | May 2024 | Apr 2025 | May 2024 | Apr 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWSO | BWSO Facilities Improvement Program | 7 | CONSTRUCTION TO 75% | Apr 2025 | Apr 2026 | Apr 2025 | Apr 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWSO | BWSO Facilities Improvement Program | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2026 | Jan 2027 | Apr 2026 | Jan 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWSO | BWSO Facilities Improvement Program | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Jul 2027 | Jan 2027 | Jul 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWSO | BWSO Facilities Improvement Program | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2027 | Oct 2027 | Jul 2027 | Oct 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC4 | Job Order Contract 2 - CIitywide | 1 | DEVELOP SCOPE | Jul 2016 | Oct 2016 | Aug 2018 | Dec 2018
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC4 | Job Order Contract 2 - CIitywide | 2 | PRELIMINARY DESIGN | Oct 2016 | Apr 2017 | Dec 2018 | Jun 2019
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC4 | Job Order Contract 2 - CIitywide | 3 | FINAL DESIGN | Apr 2017 | Oct 2018 | Jun 2019 | Dec 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC4 | Job Order Contract 2 - CIitywide | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2018 | Apr 2019 | Dec 2020 | Jun 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC4 | Job Order Contract 2 - CIitywide | 5 | CONSTRUCTION TO 25% | Apr 2019 | Jan 2020 | Jun 2021 | Mar 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC4 | Job Order Contract 2 - CIitywide | 6 | CONSTRUCTION TO 50% | Feb 2020 | Nov 2020 | Mar 2022 | Dec 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC4 | Job Order Contract 2 - CIitywide | 7 | CONSTRUCTION TO 75% | Nov 2020 | Aug 2021 | Dec 2022 | Oct 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC4 | Job Order Contract 2 - CIitywide | 8 | ORIGINAL EQUIP & FURNISHING | Aug 2021 | Nov 2021 | Oct 2023 | Jan 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC4 | Job Order Contract 2 - CIitywide | 9 | SUBSTANTIAL COMPLETION | Nov 2021 | Jan 2022 | Jan 2024 | Mar 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC4 | Job Order Contract 2 - CIitywide | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2022 | Apr 2022 | Mar 2024 | Jun 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC6 | FMC Facilities Improvement Program | 1 | DEVELOP SCOPE | Jan 2021 | Apr 2021 | Jan 2021 | Apr 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC6 | FMC Facilities Improvement Program | 2 | PRELIMINARY DESIGN | May 2021 | Oct 2021 | May 2021 | Oct 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC6 | FMC Facilities Improvement Program | 3 | FINAL DESIGN | Oct 2021 | Apr 2023 | Oct 2021 | Apr 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC6 | FMC Facilities Improvement Program | 4 | BID AWARD AND REGISTER CONTRCT | May 2023 | Oct 2023 | May 2023 | Oct 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC6 | FMC Facilities Improvement Program | 5 | CONSTRUCTION TO 25% | Oct 2023 | Aug 2024 | Oct 2023 | Aug 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC6 | FMC Facilities Improvement Program | 6 | CONSTRUCTION TO 50% | Aug 2024 | May 2025 | Aug 2024 | May 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC6 | FMC Facilities Improvement Program | 7 | CONSTRUCTION TO 75% | May 2025 | Feb 2026 | May 2025 | Feb 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC6 | FMC Facilities Improvement Program | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2026 | May 2026 | Feb 2026 | May 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC6 | FMC Facilities Improvement Program | 9 | SUBSTANTIAL COMPLETION | May 2026 | Jul 2026 | May 2026 | Jul 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC6 | FMC Facilities Improvement Program | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2026 | Oct 2026 | Jul 2026 | Oct 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | 1 | DEVELOP SCOPE | Jan 2021 | Apr 2021 | Jan 2021 | Apr 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | 2 | PRELIMINARY DESIGN | May 2021 | Oct 2021 | May 2021 | Oct 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | 3 | FINAL DESIGN | Oct 2021 | Apr 2023 | Oct 2021 | Apr 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | 4 | BID AWARD AND REGISTER CONTRCT | May 2023 | Oct 2023 | May 2023 | Oct 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | 5 | CONSTRUCTION TO 25% | Oct 2023 | Aug 2024 | Oct 2023 | Aug 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | 6 | CONSTRUCTION TO 50% | Aug 2024 | May 2025 | Aug 2024 | May 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | 7 | CONSTRUCTION TO 75% | May 2025 | Feb 2026 | May 2025 | Feb 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2026 | May 2026 | Feb 2026 | May 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | 9 | SUBSTANTIAL COMPLETION | May 2026 | Jul 2026 | May 2026 | Jul 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2026 | Oct 2026 | Jul 2026 | Oct 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | 11 | DEVELOP SCOPE | Jul 2026 | Oct 2026 | Oct 2026 | Jan 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | 12 | PRELIMINARY DESIGN | Jul 2026 | Oct 2026 | Jan 2027 | May 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | 13 | FINAL DESIGN | Jul 2026 | Oct 2026 | May 2027 | Nov 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | 14 | BID AWARD AND REGISTER CONTRCT | Jul 2026 | Oct 2026 | Nov 2027 | Feb 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | 15 | CONSTRUCTION TO 25% | Jul 2026 | Oct 2026 | Feb 2028 | Jun 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | 16 | CONSTRUCTION TO 50% | Jul 2026 | Oct 2026 | Jun 2028 | Sep 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | 17 | CONSTRUCTION TO 75% | Jul 2026 | Oct 2026 | Oct 2028 | Jan 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | 18 | ORIGINAL EQUIP & FURNISHING | Jul 2026 | Oct 2026 | Jan 2029 | Apr 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | 19 | SUBSTANTIAL COMPLETION | Jul 2026 | Oct 2026 | Apr 2029 | Jun 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | 20 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2026 | Oct 2026 | Jun 2029 | Jul 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | 1 | DEVELOP SCOPE | Jan 2023 | Apr 2023 | Jan 2031 | Apr 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | 2 | PRELIMINARY DESIGN | May 2023 | Oct 2023 | May 2031 | Oct 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | 3 | FINAL DESIGN | Oct 2023 | Apr 2025 | Oct 2031 | Apr 2033
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2025 | Oct 2025 | Apr 2033 | Oct 2033
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | 5 | CONSTRUCTION TO 25% | Oct 2025 | Aug 2026 | Oct 2033 | Aug 2034
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | 6 | CONSTRUCTION TO 50% | Aug 2026 | May 2027 | Aug 2034 | May 2035
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | 7 | CONSTRUCTION TO 75% | May 2027 | Feb 2028 | May 2035 | Feb 2036
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2028 | May 2028 | Feb 2036 | May 2036
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | 9 | SUBSTANTIAL COMPLETION | May 2028 | Jul 2028 | May 2036 | Jul 2036
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2028 | Oct 2028 | Jul 2036 | Oct 2036
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | 11 | DEVELOP SCOPE | Jul 2028 | Oct 2028 | Oct 2036 | Jan 2037
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | 12 | PRELIMINARY DESIGN | Jul 2028 | Oct 2028 | Jan 2037 | May 2037
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | 13 | FINAL DESIGN | Jul 2028 | Oct 2028 | May 2037 | Nov 2037
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | 14 | BID AWARD AND REGISTER CONTRCT | Jul 2028 | Oct 2028 | Nov 2037 | Feb 2038
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | 15 | CONSTRUCTION TO 25% | Jul 2028 | Oct 2028 | Feb 2038 | Jun 2038
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | 16 | CONSTRUCTION TO 50% | Jul 2028 | Oct 2028 | Jun 2038 | Sep 2038
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | 17 | CONSTRUCTION TO 75% | Jul 2028 | Oct 2028 | Oct 2038 | Jan 2039
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | 18 | ORIGINAL EQUIP & FURNISHING | Jul 2028 | Oct 2028 | Jan 2039 | Apr 2039
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | 19 | SUBSTANTIAL COMPLETION | Jul 2028 | Oct 2028 | Apr 2039 | Jun 2039
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | 20 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2028 | Oct 2028 | Jun 2039 | Jul 2039
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | 1 | DEVELOP SCOPE | Jan 2023 | Apr 2023 | Jan 2033 | Apr 2033
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | 2 | PRELIMINARY DESIGN | May 2023 | Oct 2023 | May 2033 | Oct 2033
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | 3 | FINAL DESIGN | Oct 2023 | Apr 2025 | Oct 2033 | Apr 2035
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2025 | Oct 2025 | May 2035 | Oct 2035
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | 5 | CONSTRUCTION TO 25% | Oct 2025 | Aug 2026 | Oct 2035 | Aug 2036
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | 6 | CONSTRUCTION TO 50% | Aug 2026 | May 2027 | Aug 2036 | May 2037
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | 7 | CONSTRUCTION TO 75% | May 2027 | Feb 2028 | May 2037 | Feb 2038
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2028 | May 2028 | Feb 2038 | May 2038
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | 9 | SUBSTANTIAL COMPLETION | May 2028 | Jul 2028 | May 2038 | Jul 2038
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2028 | Oct 2028 | Jul 2038 | Oct 2038
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | 11 | DEVELOP SCOPE | Jul 2028 | Oct 2028 | Oct 2038 | Jan 2039
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | 12 | PRELIMINARY DESIGN | Jul 2028 | Oct 2028 | Jan 2039 | May 2039
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | 13 | FINAL DESIGN | Jul 2028 | Oct 2028 | May 2039 | Nov 2039
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | 14 | BID AWARD AND REGISTER CONTRCT | Jul 2028 | Oct 2028 | Nov 2039 | Feb 2040
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | 15 | CONSTRUCTION TO 25% | Jul 2028 | Oct 2028 | Feb 2040 | Jun 2040
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | 16 | CONSTRUCTION TO 50% | Jul 2028 | Oct 2028 | Jun 2040 | Sep 2040
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | 17 | CONSTRUCTION TO 75% | Jul 2028 | Oct 2028 | Oct 2040 | Jan 2041
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | 18 | ORIGINAL EQUIP & FURNISHING | Jul 2028 | Oct 2028 | Jan 2041 | Apr 2041
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | 19 | SUBSTANTIAL COMPLETION | Jul 2028 | Oct 2028 | Apr 2041 | Jun 2041
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | 20 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2028 | Oct 2028 | Jun 2041 | Jul 2041
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-WSO20 | BWSO Facilities Improvement Program Citywide | 1 | DEVELOP SCOPE | Jun 2021 | Aug 2021 | Jun 2021 | Aug 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-WSO20 | BWSO Facilities Improvement Program Citywide | 2 | PRELIMINARY DESIGN | Aug 2021 | Dec 2021 | Aug 2021 | Dec 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-WSO20 | BWSO Facilities Improvement Program Citywide | 3 | FINAL DESIGN | Dec 2021 | Jun 2022 | Dec 2021 | Jun 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-WSO20 | BWSO Facilities Improvement Program Citywide | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-WSO20 | BWSO Facilities Improvement Program Citywide | 5 | CONSTRUCTION TO 25% | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-WSO20 | BWSO Facilities Improvement Program Citywide | 6 | CONSTRUCTION TO 50% | Jan 2023 | May 2023 | Jan 2023 | May 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-WSO20 | BWSO Facilities Improvement Program Citywide | 7 | CONSTRUCTION TO 75% | May 2023 | Sep 2023 | May 2023 | Sep 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-WSO20 | BWSO Facilities Improvement Program Citywide | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Dec 2023 | Sep 2023 | Dec 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-WSO20 | BWSO Facilities Improvement Program Citywide | 9 | SUBSTANTIAL COMPLETION | Dec 2023 | Feb 2024 | Dec 2023 | Feb 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-WSO20 | BWSO Facilities Improvement Program Citywide | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2024 | Mar 2024 | Feb 2024 | Mar 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-WSO24 | BWSO Facilities Improvement Program Citywide | 1 | DEVELOP SCOPE | Aug 2023 | May 2024 | Aug 2023 | May 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JPSCOMPEH | JEROME PS ELECTRIC & HYDRAULIC SVC REPLAMNT | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jun 2018 | Mar 2019
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JPSCOMPEH | JEROME PS ELECTRIC & HYDRAULIC SVC REPLAMNT | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Mar 2019 | Mar 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JPSCOMPEH | JEROME PS ELECTRIC & HYDRAULIC SVC REPLAMNT | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Mar 2020 | Sep 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JPSCOMPEH | JEROME PS ELECTRIC & HYDRAULIC SVC REPLAMNT | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Sep 2021 | Jun 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JPSCOMPEH | JEROME PS ELECTRIC & HYDRAULIC SVC REPLAMNT | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Jun 2022 | Jun 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JPSCOMPEH | JEROME PS ELECTRIC & HYDRAULIC SVC REPLAMNT | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Jun 2023 | May 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JPSCOMPEH | JEROME PS ELECTRIC & HYDRAULIC SVC REPLAMNT | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | May 2024 | May 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JPSCOMPEH | JEROME PS ELECTRIC & HYDRAULIC SVC REPLAMNT | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | May 2025 | Feb 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JPSCOMPEH | JEROME PS ELECTRIC & HYDRAULIC SVC REPLAMNT | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Feb 2026 | Aug 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JPSCOMPEH | JEROME PS ELECTRIC & HYDRAULIC SVC REPLAMNT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Aug 2026 | Nov 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | KENS-EAST | KENSICO-EASTVIEW CONNECTION TUNNEL | 1 | DEVELOP SCOPE | Jul 2016 | Mar 2017 | Jul 2016 | Mar 2017
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | KENS-EAST | KENSICO-EASTVIEW CONNECTION TUNNEL | 2 | PRELIMINARY DESIGN | Mar 2017 | Mar 2018 | Mar 2017 | Mar 2018
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | KENS-EAST | KENSICO-EASTVIEW CONNECTION TUNNEL | 3 | FINAL DESIGN | Mar 2018 | Sep 2019 | Mar 2018 | Sep 2019
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | KENS-EAST | KENSICO-EASTVIEW CONNECTION TUNNEL | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Jun 2020 | Sep 2019 | Jun 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | KENS-EAST | KENSICO-EASTVIEW CONNECTION TUNNEL | 5 | CONSTRUCTION TO 25% | Jun 2020 | Jun 2021 | Jun 2020 | Jun 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | KENS-EAST | KENSICO-EASTVIEW CONNECTION TUNNEL | 6 | CONSTRUCTION TO 50% | Jun 2021 | May 2022 | Jun 2021 | May 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | KENS-EAST | KENSICO-EASTVIEW CONNECTION TUNNEL | 7 | CONSTRUCTION TO 75% | May 2022 | May 2023 | May 2022 | May 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | KENS-EAST | KENSICO-EASTVIEW CONNECTION TUNNEL | 8 | ORIGINAL EQUIP & FURNISHING | May 2023 | Feb 2024 | May 2023 | Feb 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | KENS-EAST | KENSICO-EASTVIEW CONNECTION TUNNEL | 9 | SUBSTANTIAL COMPLETION | Feb 2024 | Aug 2024 | Feb 2024 | Aug 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | KENS-EAST | KENSICO-EASTVIEW CONNECTION TUNNEL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2024 | Nov 2024 | Aug 2032 | Nov 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | LFK-RELO | Lefrak Relocation | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Aug 2020 | Dec 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | LFK-RELO | Lefrak Relocation | 2 | PRELIMINARY DESIGN | Sep 2016 | Mar 2017 | Dec 2020 | Jun 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | LFK-RELO | Lefrak Relocation | 3 | FINAL DESIGN | Mar 2017 | Sep 2018 | Jun 2021 | Dec 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | LFK-RELO | Lefrak Relocation | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2018 | Mar 2019 | Dec 2022 | Jun 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | LFK-RELO | Lefrak Relocation | 5 | CONSTRUCTION TO 25% | Mar 2019 | Jan 2020 | Jun 2023 | Mar 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | LFK-RELO | Lefrak Relocation | 6 | CONSTRUCTION TO 50% | Jan 2020 | Oct 2020 | Mar 2024 | Dec 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | LFK-RELO | Lefrak Relocation | 7 | CONSTRUCTION TO 75% | Oct 2020 | Jul 2021 | Dec 2024 | Oct 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | LFK-RELO | Lefrak Relocation | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2021 | Oct 2021 | Oct 2025 | Jan 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | LFK-RELO | Lefrak Relocation | 9 | SUBSTANTIAL COMPLETION | Oct 2021 | Dec 2021 | Jan 2026 | Mar 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | LFK-RELO | Lefrak Relocation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2021 | Mar 2022 | Mar 2026 | Jun 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MONIT-13 | FAD 13-17 Monitoring | 1 | DEVELOP SCOPE | Jan 2013 | Dec 2022 | Jan 2011 | Dec 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MONIT-18 | FAD MONITORING | 1 | DEVELOP SCOPE | Jul 2022 | Jun 2032 | Jul 2022 | Jun 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-GRANT | GREEN INFRASTRUCTURE GRANT PROGRAM - MS4 PROJECTS | 1 | DEVELOP SCOPE | Jun 2025 | Aug 2025 | Jun 2025 | Aug 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-GRANT | GREEN INFRASTRUCTURE GRANT PROGRAM - MS4 PROJECTS | 2 | PRELIMINARY DESIGN | Aug 2025 | Dec 2025 | Aug 2025 | Dec 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-GRANT | GREEN INFRASTRUCTURE GRANT PROGRAM - MS4 PROJECTS | 3 | FINAL DESIGN | Dec 2025 | Jun 2026 | Dec 2025 | Jun 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-GRANT | GREEN INFRASTRUCTURE GRANT PROGRAM - MS4 PROJECTS | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2026 | Sep 2026 | Jun 2026 | Sep 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-GRANT | GREEN INFRASTRUCTURE GRANT PROGRAM - MS4 PROJECTS | 5 | CONSTRUCTION TO 25% | Sep 2026 | Jan 2027 | Sep 2026 | Jan 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-GRANT | GREEN INFRASTRUCTURE GRANT PROGRAM - MS4 PROJECTS | 6 | CONSTRUCTION TO 50% | Jan 2027 | May 2027 | Jan 2027 | May 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-GRANT | GREEN INFRASTRUCTURE GRANT PROGRAM - MS4 PROJECTS | 7 | CONSTRUCTION TO 75% | May 2027 | Sep 2027 | May 2027 | Sep 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-GRANT | GREEN INFRASTRUCTURE GRANT PROGRAM - MS4 PROJECTS | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2027 | Dec 2027 | Sep 2027 | Dec 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-GRANT | GREEN INFRASTRUCTURE GRANT PROGRAM - MS4 PROJECTS | 9 | SUBSTANTIAL COMPLETION | Dec 2027 | Feb 2028 | Dec 2027 | Feb 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-GRANT | GREEN INFRASTRUCTURE GRANT PROGRAM - MS4 PROJECTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2028 | Mar 2028 | Feb 2028 | Mar 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-STORM | MS4 CITYWIDE STORMWATER MANAGEMENT PROGRAM | 1 | DEVELOP SCOPE | Dec 2017 | Aug 2018 | Dec 2017 | Aug 2018
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-STORM | MS4 CITYWIDE STORMWATER MANAGEMENT PROGRAM | 2 | PRELIMINARY DESIGN | Aug 2018 | Aug 2019 | Aug 2018 | Aug 2019
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-STORM | MS4 CITYWIDE STORMWATER MANAGEMENT PROGRAM | 3 | FINAL DESIGN | Aug 2019 | Feb 2021 | Aug 2019 | Feb 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-STORM | MS4 CITYWIDE STORMWATER MANAGEMENT PROGRAM | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2021 | Nov 2021 | Feb 2021 | Nov 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-STORM | MS4 CITYWIDE STORMWATER MANAGEMENT PROGRAM | 5 | CONSTRUCTION TO 25% | Nov 2021 | Nov 2022 | Nov 2021 | Nov 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-STORM | MS4 CITYWIDE STORMWATER MANAGEMENT PROGRAM | 6 | CONSTRUCTION TO 50% | Nov 2022 | Oct 2023 | Nov 2022 | Oct 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-STORM | MS4 CITYWIDE STORMWATER MANAGEMENT PROGRAM | 7 | CONSTRUCTION TO 75% | Oct 2023 | Oct 2024 | Oct 2023 | Oct 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-STORM | MS4 CITYWIDE STORMWATER MANAGEMENT PROGRAM | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jul 2025 | Oct 2024 | Jul 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-STORM | MS4 CITYWIDE STORMWATER MANAGEMENT PROGRAM | 9 | SUBSTANTIAL COMPLETION | Jul 2025 | Jan 2030 | Jul 2025 | Jan 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-STORM | MS4 CITYWIDE STORMWATER MANAGEMENT PROGRAM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2030 | Apr 2030 | Jan 2030 | Apr 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | NYSDOTBRG | NYS DOT Bridges El Grant, Jesup, Nelson, Depot, Boston Road | 1 | DEVELOP SCOPE | Jun 2019 | Aug 2019 | Oct 2024 | Dec 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | NYSDOTBRG | NYS DOT Bridges El Grant, Jesup, Nelson, Depot, Boston Road | 2 | PRELIMINARY DESIGN | Aug 2019 | Dec 2019 | Dec 2024 | Apr 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | NYSDOTBRG | NYS DOT Bridges El Grant, Jesup, Nelson, Depot, Boston Road | 3 | FINAL DESIGN | Dec 2019 | Jun 2020 | Apr 2025 | Oct 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | NYSDOTBRG | NYS DOT Bridges El Grant, Jesup, Nelson, Depot, Boston Road | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Sep 2020 | Oct 2025 | Jan 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | NYSDOTBRG | NYS DOT Bridges El Grant, Jesup, Nelson, Depot, Boston Road | 5 | CONSTRUCTION TO 25% | Sep 2020 | Jan 2021 | Jan 2026 | May 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | NYSDOTBRG | NYS DOT Bridges El Grant, Jesup, Nelson, Depot, Boston Road | 6 | CONSTRUCTION TO 50% | Jan 2021 | May 2021 | May 2026 | Sep 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | NYSDOTBRG | NYS DOT Bridges El Grant, Jesup, Nelson, Depot, Boston Road | 7 | CONSTRUCTION TO 75% | May 2021 | Sep 2021 | Sep 2026 | Jan 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | NYSDOTBRG | NYS DOT Bridges El Grant, Jesup, Nelson, Depot, Boston Road | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Dec 2021 | Jan 2027 | Apr 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | NYSDOTBRG | NYS DOT Bridges El Grant, Jesup, Nelson, Depot, Boston Road | 9 | SUBSTANTIAL COMPLETION | Dec 2021 | Feb 2022 | Apr 2027 | Jun 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | NYSDOTBRG | NYS DOT Bridges El Grant, Jesup, Nelson, Depot, Boston Road | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2022 | Mar 2022 | Jun 2027 | Jul 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PJ-PLNT | RECONSTRUCTION OF PORT JERVIS WPCP, DEL | 1 | DEVELOP SCOPE | Nov 2003 | Aug 2004 | Jun 2012 | Feb 2013
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PJ-PLNT | RECONSTRUCTION OF PORT JERVIS WPCP, DEL | 2 | PRELIMINARY DESIGN | Aug 2004 | Aug 2005 | Feb 2013 | Feb 2014
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PJ-PLNT | RECONSTRUCTION OF PORT JERVIS WPCP, DEL | 3 | FINAL DESIGN | Aug 2005 | Jan 2007 | Feb 2014 | Aug 2015
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PJ-PLNT | RECONSTRUCTION OF PORT JERVIS WPCP, DEL | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2007 | Oct 2007 | Aug 2015 | May 2016
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PJ-PLNT | RECONSTRUCTION OF PORT JERVIS WPCP, DEL | 5 | CONSTRUCTION TO 25% | Oct 2007 | Oct 2008 | May 2016 | May 2017
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PJ-PLNT | RECONSTRUCTION OF PORT JERVIS WPCP, DEL | 6 | CONSTRUCTION TO 50% | Oct 2008 | Oct 2009 | May 2017 | Apr 2018
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PJ-PLNT | RECONSTRUCTION OF PORT JERVIS WPCP, DEL | 7 | CONSTRUCTION TO 75% | Oct 2009 | Oct 2010 | May 2018 | Apr 2019
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PJ-PLNT | RECONSTRUCTION OF PORT JERVIS WPCP, DEL | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2010 | Jul 2011 | Apr 2019 | Jan 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PJ-PLNT | RECONSTRUCTION OF PORT JERVIS WPCP, DEL | 9 | SUBSTANTIAL COMPLETION | Jul 2011 | Dec 2011 | Jan 2020 | Jul 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PJ-PLNT | RECONSTRUCTION OF PORT JERVIS WPCP, DEL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2011 | Mar 2012 | Jul 2032 | Oct 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS179 | REHAB 179 ST PS/CONST MULTIPLE PS IN TOWER AREA | 1 | DEVELOP SCOPE | Jun 2020 | Feb 2021 | Jun 2020 | Feb 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS179 | REHAB 179 ST PS/CONST MULTIPLE PS IN TOWER AREA | 2 | PRELIMINARY DESIGN | Feb 2021 | Feb 2022 | Feb 2021 | Feb 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS179 | REHAB 179 ST PS/CONST MULTIPLE PS IN TOWER AREA | 3 | FINAL DESIGN | Feb 2022 | Aug 2023 | Feb 2022 | Aug 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS179 | REHAB 179 ST PS/CONST MULTIPLE PS IN TOWER AREA | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2023 | May 2024 | Aug 2023 | May 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS179 | REHAB 179 ST PS/CONST MULTIPLE PS IN TOWER AREA | 5 | CONSTRUCTION TO 25% | May 2024 | May 2025 | May 2024 | May 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS179 | REHAB 179 ST PS/CONST MULTIPLE PS IN TOWER AREA | 6 | CONSTRUCTION TO 50% | May 2025 | Apr 2026 | May 2025 | Apr 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS179 | REHAB 179 ST PS/CONST MULTIPLE PS IN TOWER AREA | 7 | CONSTRUCTION TO 75% | May 2026 | Apr 2027 | May 2026 | Apr 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS179 | REHAB 179 ST PS/CONST MULTIPLE PS IN TOWER AREA | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2027 | Jan 2028 | Apr 2027 | Jan 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS179 | REHAB 179 ST PS/CONST MULTIPLE PS IN TOWER AREA | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Jul 2028 | Jan 2028 | Jul 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS179 | REHAB 179 ST PS/CONST MULTIPLE PS IN TOWER AREA | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2028 | Oct 2028 | Jul 2028 | Oct 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-FORCEM | Rehabilitation of Forcemains Systemwide | 1 | DEVELOP SCOPE | Jan 2021 | Oct 2021 | Jan 2021 | Oct 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-FORCEM | Rehabilitation of Forcemains Systemwide | 2 | PRELIMINARY DESIGN | Oct 2021 | Oct 2022 | Oct 2021 | Oct 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-FORCEM | Rehabilitation of Forcemains Systemwide | 3 | FINAL DESIGN | Oct 2022 | Mar 2024 | Oct 2022 | Mar 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-FORCEM | Rehabilitation of Forcemains Systemwide | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2024 | Dec 2024 | Mar 2024 | Dec 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-FORCEM | Rehabilitation of Forcemains Systemwide | 5 | CONSTRUCTION TO 25% | Dec 2024 | Dec 2025 | Dec 2024 | Dec 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-FORCEM | Rehabilitation of Forcemains Systemwide | 6 | CONSTRUCTION TO 50% | Dec 2025 | Dec 2026 | Dec 2025 | Dec 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-FORCEM | Rehabilitation of Forcemains Systemwide | 7 | CONSTRUCTION TO 75% | Dec 2026 | Dec 2027 | Dec 2026 | Dec 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-FORCEM | Rehabilitation of Forcemains Systemwide | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2027 | Sep 2028 | Dec 2027 | Sep 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-FORCEM | Rehabilitation of Forcemains Systemwide | 9 | SUBSTANTIAL COMPLETION | Sep 2028 | Mar 2029 | Sep 2028 | Mar 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-FORCEM | Rehabilitation of Forcemains Systemwide | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2029 | Jun 2029 | Mar 2029 | Jun 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-117-L | INSTALLATION OF DISTRIBUTED CONTROL SYSTEMS @ VARIOUS WWTPS | 1 | DEVELOP SCOPE | Mar 2019 | May 2019 | Jun 2029 | Aug 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-117-L | INSTALLATION OF DISTRIBUTED CONTROL SYSTEMS @ VARIOUS WWTPS | 2 | PRELIMINARY DESIGN | May 2019 | Sep 2019 | Aug 2029 | Dec 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-117-L | INSTALLATION OF DISTRIBUTED CONTROL SYSTEMS @ VARIOUS WWTPS | 3 | FINAL DESIGN | Sep 2019 | Mar 2020 | Dec 2029 | Jun 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-117-L | INSTALLATION OF DISTRIBUTED CONTROL SYSTEMS @ VARIOUS WWTPS | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Jun 2020 | Jun 2030 | Sep 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-117-L | INSTALLATION OF DISTRIBUTED CONTROL SYSTEMS @ VARIOUS WWTPS | 5 | CONSTRUCTION TO 25% | Jun 2020 | Oct 2020 | Sep 2030 | Jan 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-117-L | INSTALLATION OF DISTRIBUTED CONTROL SYSTEMS @ VARIOUS WWTPS | 6 | CONSTRUCTION TO 50% | Oct 2020 | Feb 2021 | Jan 2031 | May 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-117-L | INSTALLATION OF DISTRIBUTED CONTROL SYSTEMS @ VARIOUS WWTPS | 7 | CONSTRUCTION TO 75% | Feb 2021 | Jun 2021 | May 2031 | Sep 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-117-L | INSTALLATION OF DISTRIBUTED CONTROL SYSTEMS @ VARIOUS WWTPS | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2021 | Sep 2021 | Sep 2031 | Dec 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-117-L | INSTALLATION OF DISTRIBUTED CONTROL SYSTEMS @ VARIOUS WWTPS | 9 | SUBSTANTIAL COMPLETION | Sep 2021 | Nov 2021 | Dec 2031 | Feb 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-117-L | INSTALLATION OF DISTRIBUTED CONTROL SYSTEMS @ VARIOUS WWTPS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2021 | Dec 2021 | Feb 2032 | Mar 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-CBS | REPLACEMENT OF CHEMICAL BULK STORAGE TANKS PLANT- WIDE | 1 | DEVELOP SCOPE | Jun 2019 | Aug 2019 | Jun 2019 | Feb 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-CBS | REPLACEMENT OF CHEMICAL BULK STORAGE TANKS PLANT- WIDE | 2 | PRELIMINARY DESIGN | Aug 2019 | Dec 2019 | Feb 2020 | Feb 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-CBS | REPLACEMENT OF CHEMICAL BULK STORAGE TANKS PLANT- WIDE | 3 | FINAL DESIGN | Dec 2019 | Jun 2020 | Feb 2021 | Aug 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-CBS | REPLACEMENT OF CHEMICAL BULK STORAGE TANKS PLANT- WIDE | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Sep 2020 | Aug 2022 | May 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-CBS | REPLACEMENT OF CHEMICAL BULK STORAGE TANKS PLANT- WIDE | 5 | CONSTRUCTION TO 25% | Sep 2020 | Jan 2021 | May 2023 | May 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-CBS | REPLACEMENT OF CHEMICAL BULK STORAGE TANKS PLANT- WIDE | 6 | CONSTRUCTION TO 50% | Jan 2021 | May 2021 | May 2024 | Apr 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-CBS | REPLACEMENT OF CHEMICAL BULK STORAGE TANKS PLANT- WIDE | 7 | CONSTRUCTION TO 75% | May 2021 | Sep 2021 | Apr 2025 | Apr 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-CBS | REPLACEMENT OF CHEMICAL BULK STORAGE TANKS PLANT- WIDE | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Dec 2021 | Apr 2026 | Jan 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-CBS | REPLACEMENT OF CHEMICAL BULK STORAGE TANKS PLANT- WIDE | 9 | SUBSTANTIAL COMPLETION | Dec 2021 | Feb 2022 | Jan 2027 | Jul 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-CBS | REPLACEMENT OF CHEMICAL BULK STORAGE TANKS PLANT- WIDE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2022 | Mar 2022 | Jul 2031 | Oct 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-FOAM | Replacement of Spread Foam Insulation over Digester & Thicke | 1 | FINAL DESIGN | Jun 2025 | Nov 2026 | Jun 2025 | Nov 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-FOAM | Replacement of Spread Foam Insulation over Digester & Thicke | 2 | CONSTRUCTION TO 25% | Nov 2026 | Jul 2027 | Nov 2026 | Jul 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-FOAM | Replacement of Spread Foam Insulation over Digester & Thicke | 3 | CONSTRUCTION TO 50% | Jul 2027 | Mar 2028 | Jul 2027 | Mar 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-FOAM | Replacement of Spread Foam Insulation over Digester & Thicke | 4 | CONSTRUCTION TO 75% | Mar 2028 | Nov 2028 | Mar 2028 | Nov 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-SCADA | Installation of New SCADA System at Various DEP Facilities | 1 | DEVELOP SCOPE | Jun 2023 | Feb 2024 | Jun 2023 | Feb 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-SCADA | Installation of New SCADA System at Various DEP Facilities | 2 | PRELIMINARY DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-SCADA | Installation of New SCADA System at Various DEP Facilities | 3 | FINAL DESIGN | Feb 2025 | Aug 2026 | Feb 2025 | Aug 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-SCADA | Installation of New SCADA System at Various DEP Facilities | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2026 | May 2027 | Aug 2026 | May 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-SCADA | Installation of New SCADA System at Various DEP Facilities | 5 | CONSTRUCTION TO 25% | May 2027 | May 2028 | May 2027 | May 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-SCADA | Installation of New SCADA System at Various DEP Facilities | 6 | CONSTRUCTION TO 50% | May 2028 | Apr 2029 | May 2028 | Apr 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-SCADA | Installation of New SCADA System at Various DEP Facilities | 7 | CONSTRUCTION TO 75% | Apr 2029 | Apr 2030 | Apr 2029 | Apr 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-SCADA | Installation of New SCADA System at Various DEP Facilities | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2030 | Jan 2031 | Apr 2030 | Jan 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-SCADA | Installation of New SCADA System at Various DEP Facilities | 9 | SUBSTANTIAL COMPLETION | Jan 2031 | Jul 2035 | Jan 2031 | Jul 2035
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-SCADA | Installation of New SCADA System at Various DEP Facilities | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2035 | Oct 2035 | Jul 2035 | Oct 2035
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RESAMSAF | DESIGN & CM FOR DAM SAFETY CONSTRUCTION | 1 | DEVELOP SCOPE | Jun 2013 | Mar 2014 | Jun 2013 | Mar 2014
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RESAMSAF | DESIGN & CM FOR DAM SAFETY CONSTRUCTION | 2 | PRELIMINARY DESIGN | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2015
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RESAMSAF | DESIGN & CM FOR DAM SAFETY CONSTRUCTION | 3 | FINAL DESIGN | Mar 2015 | Sep 2016 | Mar 2015 | Sep 2016
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RESAMSAF | DESIGN & CM FOR DAM SAFETY CONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2016 | Jun 2017 | Sep 2016 | Jun 2017
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RESAMSAF | DESIGN & CM FOR DAM SAFETY CONSTRUCTION | 5 | CONSTRUCTION TO 25% | Jun 2017 | Jun 2018 | Jun 2017 | Jun 2018
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RESAMSAF | DESIGN & CM FOR DAM SAFETY CONSTRUCTION | 6 | CONSTRUCTION TO 50% | Jun 2018 | May 2019 | Jun 2018 | May 2019
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RESAMSAF | DESIGN & CM FOR DAM SAFETY CONSTRUCTION | 7 | CONSTRUCTION TO 75% | May 2019 | May 2020 | May 2019 | May 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RESAMSAF | DESIGN & CM FOR DAM SAFETY CONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | May 2020 | Feb 2021 | May 2020 | Feb 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RESAMSAF | DESIGN & CM FOR DAM SAFETY CONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | Feb 2021 | Aug 2021 | Feb 2021 | Aug 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RESAMSAF | DESIGN & CM FOR DAM SAFETY CONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Nov 2021 | Aug 2029 | Nov 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RIDGEPIPE | RIDGEWOOD RESERVOIR PIPE ABANDONMENT | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2024 | Aug 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RIDGEPIPE | RIDGEWOOD RESERVOIR PIPE ABANDONMENT | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2024 | Dec 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RIDGEPIPE | RIDGEWOOD RESERVOIR PIPE ABANDONMENT | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2024 | Jun 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RIDGEPIPE | RIDGEWOOD RESERVOIR PIPE ABANDONMENT | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2025 | Sep 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RIDGEPIPE | RIDGEWOOD RESERVOIR PIPE ABANDONMENT | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2025 | Jan 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RIDGEPIPE | RIDGEWOOD RESERVOIR PIPE ABANDONMENT | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2026 | May 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RIDGEPIPE | RIDGEWOOD RESERVOIR PIPE ABANDONMENT | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2026 | Sep 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RIDGEPIPE | RIDGEWOOD RESERVOIR PIPE ABANDONMENT | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2026 | Dec 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RIDGEPIPE | RIDGEWOOD RESERVOIR PIPE ABANDONMENT | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2026 | Feb 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RIDGEPIPE | RIDGEWOOD RESERVOIR PIPE ABANDONMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Feb 2027 | Mar 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RLCY-WWT | FLOODWATER RESILIENCY AT BWT FACILITES | 1 | DEVELOP SCOPE | Jun 2017 | Feb 2018 | Jun 2017 | Feb 2018
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RLCY-WWT | FLOODWATER RESILIENCY AT BWT FACILITES | 2 | PRELIMINARY DESIGN | Feb 2018 | Feb 2019 | Feb 2018 | Feb 2019
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RLCY-WWT | FLOODWATER RESILIENCY AT BWT FACILITES | 3 | FINAL DESIGN | Feb 2019 | Aug 2020 | Feb 2019 | Aug 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RLCY-WWT | FLOODWATER RESILIENCY AT BWT FACILITES | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2020 | May 2021 | Aug 2020 | May 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RLCY-WWT | FLOODWATER RESILIENCY AT BWT FACILITES | 5 | CONSTRUCTION TO 25% | May 2021 | May 2022 | May 2021 | May 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RLCY-WWT | FLOODWATER RESILIENCY AT BWT FACILITES | 6 | CONSTRUCTION TO 50% | May 2022 | Apr 2023 | May 2022 | Apr 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RLCY-WWT | FLOODWATER RESILIENCY AT BWT FACILITES | 7 | CONSTRUCTION TO 75% | May 2023 | Apr 2024 | May 2023 | Apr 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RLCY-WWT | FLOODWATER RESILIENCY AT BWT FACILITES | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2024 | Jan 2025 | Apr 2024 | Jan 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RLCY-WWT | FLOODWATER RESILIENCY AT BWT FACILITES | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RLCY-WWT | FLOODWATER RESILIENCY AT BWT FACILITES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Oct 2025 | Jul 2029 | Oct 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDHILLV | HILLVIEW RESERVOIR SECURITY FENCE IMPROVEMENTS | 1 | DEVELOP SCOPE | Jun 2017 | Oct 2017 | Jun 2018 | Oct 2018
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDHILLV | HILLVIEW RESERVOIR SECURITY FENCE IMPROVEMENTS | 2 | PRELIMINARY DESIGN | Oct 2017 | Apr 2018 | Oct 2018 | Apr 2019
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDHILLV | HILLVIEW RESERVOIR SECURITY FENCE IMPROVEMENTS | 3 | FINAL DESIGN | Apr 2018 | Oct 2019 | Apr 2019 | Oct 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDHILLV | HILLVIEW RESERVOIR SECURITY FENCE IMPROVEMENTS | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2019 | Apr 2020 | Oct 2020 | Apr 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDHILLV | HILLVIEW RESERVOIR SECURITY FENCE IMPROVEMENTS | 5 | CONSTRUCTION TO 25% | Apr 2020 | Jan 2021 | Apr 2021 | Jan 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDHILLV | HILLVIEW RESERVOIR SECURITY FENCE IMPROVEMENTS | 6 | CONSTRUCTION TO 50% | Jan 2021 | Nov 2021 | Jan 2022 | Nov 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDHILLV | HILLVIEW RESERVOIR SECURITY FENCE IMPROVEMENTS | 7 | CONSTRUCTION TO 75% | Nov 2021 | Aug 2022 | Nov 2022 | Aug 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDHILLV | HILLVIEW RESERVOIR SECURITY FENCE IMPROVEMENTS | 8 | ORIGINAL EQUIP & FURNISHING | Aug 2022 | Nov 2022 | Aug 2023 | Nov 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDHILLV | HILLVIEW RESERVOIR SECURITY FENCE IMPROVEMENTS | 9 | SUBSTANTIAL COMPLETION | Nov 2022 | Jan 2023 | Nov 2023 | Jan 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDHILLV | HILLVIEW RESERVOIR SECURITY FENCE IMPROVEMENTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2023 | Apr 2023 | Jan 2024 | Apr 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDPUMP | RECONS OF VARIOUS PUMPING STATIONS DUE TO HURRICANE SANDY | 1 | DEVELOP SCOPE | Oct 2012 | Dec 2012 | Oct 2012 | Jun 2013
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDPUMP | RECONS OF VARIOUS PUMPING STATIONS DUE TO HURRICANE SANDY | 2 | PRELIMINARY DESIGN | Dec 2012 | Apr 2013 | Jun 2013 | Jun 2014
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDPUMP | RECONS OF VARIOUS PUMPING STATIONS DUE TO HURRICANE SANDY | 3 | FINAL DESIGN | Apr 2013 | Oct 2013 | Jun 2014 | Dec 2015
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDPUMP | RECONS OF VARIOUS PUMPING STATIONS DUE TO HURRICANE SANDY | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2013 | Jan 2014 | Dec 2015 | Sep 2016
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDPUMP | RECONS OF VARIOUS PUMPING STATIONS DUE TO HURRICANE SANDY | 5 | CONSTRUCTION TO 25% | Jan 2014 | May 2014 | Sep 2016 | Sep 2017
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDPUMP | RECONS OF VARIOUS PUMPING STATIONS DUE TO HURRICANE SANDY | 6 | CONSTRUCTION TO 50% | May 2014 | Sep 2014 | Sep 2017 | Aug 2018
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDPUMP | RECONS OF VARIOUS PUMPING STATIONS DUE TO HURRICANE SANDY | 7 | CONSTRUCTION TO 75% | Sep 2014 | Jan 2015 | Aug 2018 | Aug 2019
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDPUMP | RECONS OF VARIOUS PUMPING STATIONS DUE TO HURRICANE SANDY | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2015 | Apr 2015 | Aug 2019 | May 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDPUMP | RECONS OF VARIOUS PUMPING STATIONS DUE TO HURRICANE SANDY | 9 | SUBSTANTIAL COMPLETION | Apr 2015 | Jun 2015 | May 2020 | Nov 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDPUMP | RECONS OF VARIOUS PUMPING STATIONS DUE TO HURRICANE SANDY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2015 | Jul 2015 | Nov 2028 | Feb 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWM | RECONS OF WATER MAINS CITYWIDE DUE TO HURRICANE SANDY | 1 | DEVELOP SCOPE | Jun 2019 | Aug 2019 | Jun 2026 | Aug 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWM | RECONS OF WATER MAINS CITYWIDE DUE TO HURRICANE SANDY | 2 | PRELIMINARY DESIGN | Aug 2019 | Dec 2019 | Aug 2026 | Dec 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWM | RECONS OF WATER MAINS CITYWIDE DUE TO HURRICANE SANDY | 3 | FINAL DESIGN | Dec 2019 | Jun 2020 | Dec 2026 | Jun 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWM | RECONS OF WATER MAINS CITYWIDE DUE TO HURRICANE SANDY | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Sep 2020 | Jun 2027 | Sep 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWM | RECONS OF WATER MAINS CITYWIDE DUE TO HURRICANE SANDY | 5 | CONSTRUCTION TO 25% | Sep 2020 | Jan 2021 | Sep 2027 | Jan 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWM | RECONS OF WATER MAINS CITYWIDE DUE TO HURRICANE SANDY | 6 | CONSTRUCTION TO 50% | Jan 2021 | May 2021 | Jan 2028 | May 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWM | RECONS OF WATER MAINS CITYWIDE DUE TO HURRICANE SANDY | 7 | CONSTRUCTION TO 75% | May 2021 | Sep 2021 | May 2028 | Sep 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWM | RECONS OF WATER MAINS CITYWIDE DUE TO HURRICANE SANDY | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Dec 2021 | Sep 2028 | Dec 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWM | RECONS OF WATER MAINS CITYWIDE DUE TO HURRICANE SANDY | 9 | SUBSTANTIAL COMPLETION | Dec 2021 | Feb 2022 | Dec 2028 | Feb 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWM | RECONS OF WATER MAINS CITYWIDE DUE TO HURRICANE SANDY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2022 | Mar 2022 | Feb 2029 | Mar 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWPCPS | RECONS OF WPCPS AND PUMPING STATIONS DUE TO HURRICANE SANDY | 1 | DEVELOP SCOPE | Dec 2015 | Aug 2016 | Dec 2015 | Aug 2016
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWPCPS | RECONS OF WPCPS AND PUMPING STATIONS DUE TO HURRICANE SANDY | 2 | PRELIMINARY DESIGN | Aug 2016 | Aug 2017 | Aug 2016 | Aug 2017
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWPCPS | RECONS OF WPCPS AND PUMPING STATIONS DUE TO HURRICANE SANDY | 3 | FINAL DESIGN | Aug 2017 | Feb 2019 | Aug 2017 | Feb 2019
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWPCPS | RECONS OF WPCPS AND PUMPING STATIONS DUE TO HURRICANE SANDY | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2019 | Nov 2019 | Feb 2019 | Nov 2019
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWPCPS | RECONS OF WPCPS AND PUMPING STATIONS DUE TO HURRICANE SANDY | 5 | CONSTRUCTION TO 25% | Nov 2019 | Nov 2020 | Nov 2019 | Nov 2020
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWPCPS | RECONS OF WPCPS AND PUMPING STATIONS DUE TO HURRICANE SANDY | 6 | CONSTRUCTION TO 50% | Nov 2020 | Oct 2021 | Nov 2020 | Oct 2021
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWPCPS | RECONS OF WPCPS AND PUMPING STATIONS DUE TO HURRICANE SANDY | 7 | CONSTRUCTION TO 75% | Oct 2021 | Oct 2022 | Oct 2021 | Oct 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWPCPS | RECONS OF WPCPS AND PUMPING STATIONS DUE TO HURRICANE SANDY | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jul 2023 | Oct 2022 | Jul 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWPCPS | RECONS OF WPCPS AND PUMPING STATIONS DUE TO HURRICANE SANDY | 9 | SUBSTANTIAL COMPLETION | Jul 2023 | Jan 2024 | Jul 2023 | Jan 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWPCPS | RECONS OF WPCPS AND PUMPING STATIONS DUE TO HURRICANE SANDY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2024 | Apr 2024 | Jan 2028 | Apr 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SEBLMX25 | Critical SE Deficiencies to be addressed for EC backlog, CW | 1 | DEVELOP SCOPE | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SEBLMX25 | Critical SE Deficiencies to be addressed for EC backlog, CW | 2 | PRELIMINARY DESIGN | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SEBLMX25 | Critical SE Deficiencies to be addressed for EC backlog, CW | 3 | FINAL DESIGN | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SEBLMX25 | Critical SE Deficiencies to be addressed for EC backlog, CW | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2024 | Feb 2025 | Nov 2024 | Feb 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SEBLMX25 | Critical SE Deficiencies to be addressed for EC backlog, CW | 5 | CONSTRUCTION TO 25% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SEBLMX25 | Critical SE Deficiencies to be addressed for EC backlog, CW | 6 | CONSTRUCTION TO 50% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SEBLMX25 | Critical SE Deficiencies to be addressed for EC backlog, CW | 7 | CONSTRUCTION TO 75% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SEBLMX25 | Critical SE Deficiencies to be addressed for EC backlog, CW | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2026 | May 2026 | Feb 2026 | May 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SEBLMX25 | Critical SE Deficiencies to be addressed for EC backlog, CW | 9 | SUBSTANTIAL COMPLETION | May 2026 | Jul 2026 | May 2026 | Jul 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SEBLMX25 | Critical SE Deficiencies to be addressed for EC backlog, CW | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2026 | Aug 2026 | Jul 2026 | Aug 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | STMEOH-18 | FAD 18-22 STORMWATER MGMT. (EOH) | 1 | DEVELOP SCOPE | Dec 2019 | Nov 2029 | Dec 2019 | Nov 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | STMWOH-18 | FAD 18-22 STORMWATER MGMT. (WOH) | 1 | DEVELOP SCOPE | Dec 2018 | Nov 2028 | Dec 2018 | Nov 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | STRREST24 | Street Restoration for roadway settlement & caveins Citywide | 1 | DEVELOP SCOPE | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | STRREST24 | Street Restoration for roadway settlement & caveins Citywide | 2 | PRELIMINARY DESIGN | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | STRREST24 | Street Restoration for roadway settlement & caveins Citywide | 3 | FINAL DESIGN | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | STRREST24 | Street Restoration for roadway settlement & caveins Citywide | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2024 | Feb 2025 | Nov 2024 | Feb 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | STRREST24 | Street Restoration for roadway settlement & caveins Citywide | 5 | CONSTRUCTION TO 25% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | STRREST24 | Street Restoration for roadway settlement & caveins Citywide | 6 | CONSTRUCTION TO 50% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | STRREST24 | Street Restoration for roadway settlement & caveins Citywide | 7 | CONSTRUCTION TO 75% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | STRREST24 | Street Restoration for roadway settlement & caveins Citywide | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2026 | May 2026 | Feb 2026 | May 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | STRREST24 | Street Restoration for roadway settlement & caveins Citywide | 9 | SUBSTANTIAL COMPLETION | May 2026 | Jul 2026 | May 2026 | Jul 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | STRREST24 | Street Restoration for roadway settlement & caveins Citywide | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2026 | Aug 2026 | Jul 2026 | Aug 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | UTIUTIL | UTILITY RELOCATION FOR SE AND WM PROJECTS | 1 | BID AWARD AND REGISTER CONTRCT | Jul 2006 | Jun 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | UTIUTIL | UTILITY RELOCATION FOR SE AND WM PROJECTS | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2006 | Jun 2025 | May 2004 | May 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WCR-GRANT | Water Conservation and Reuse Grant Pilot Program | 1 | DEVELOP SCOPE | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WCR-GRANT | Water Conservation and Reuse Grant Pilot Program | 2 | PRELIMINARY DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WCR-GRANT | Water Conservation and Reuse Grant Pilot Program | 3 | FINAL DESIGN | Jul 2022 | Jan 2024 | Jul 2022 | Jan 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WCR-GRANT | Water Conservation and Reuse Grant Pilot Program | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WCR-GRANT | Water Conservation and Reuse Grant Pilot Program | 5 | CONSTRUCTION TO 25% | Jul 2024 | May 2025 | Jul 2024 | May 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WCR-GRANT | Water Conservation and Reuse Grant Pilot Program | 6 | CONSTRUCTION TO 50% | May 2025 | Feb 2026 | May 2025 | Feb 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WCR-GRANT | Water Conservation and Reuse Grant Pilot Program | 7 | CONSTRUCTION TO 75% | Feb 2026 | Nov 2026 | Feb 2026 | Nov 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WCR-GRANT | Water Conservation and Reuse Grant Pilot Program | 8 | ORIGINAL EQUIP & FURNISHING | Nov 2026 | Feb 2027 | Nov 2026 | Feb 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WCR-GRANT | Water Conservation and Reuse Grant Pilot Program | 9 | SUBSTANTIAL COMPLETION | Feb 2027 | Apr 2027 | Feb 2027 | Apr 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WCR-GRANT | Water Conservation and Reuse Grant Pilot Program | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2027 | Jul 2027 | Apr 2027 | Jul 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFINSP-SP | CITYWIDE WATERFRONT INSPECTIONS AT VARIOUS WPCPS | 1 | DEVELOP SCOPE | Jun 2019 | Aug 2019 | Nov 2022 | Jan 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFINSP-SP | CITYWIDE WATERFRONT INSPECTIONS AT VARIOUS WPCPS | 2 | PRELIMINARY DESIGN | Aug 2019 | Dec 2019 | Jan 2023 | May 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFINSP-SP | CITYWIDE WATERFRONT INSPECTIONS AT VARIOUS WPCPS | 3 | FINAL DESIGN | Dec 2019 | Jun 2020 | May 2023 | Nov 2023
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFINSP-SP | CITYWIDE WATERFRONT INSPECTIONS AT VARIOUS WPCPS | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Sep 2020 | Nov 2023 | Feb 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFINSP-SP | CITYWIDE WATERFRONT INSPECTIONS AT VARIOUS WPCPS | 5 | CONSTRUCTION TO 25% | Sep 2020 | Jan 2021 | Feb 2024 | Jun 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFINSP-SP | CITYWIDE WATERFRONT INSPECTIONS AT VARIOUS WPCPS | 6 | CONSTRUCTION TO 50% | Jan 2021 | May 2021 | Jun 2024 | Oct 2024
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFINSP-SP | CITYWIDE WATERFRONT INSPECTIONS AT VARIOUS WPCPS | 7 | CONSTRUCTION TO 75% | May 2021 | Sep 2021 | Oct 2024 | Feb 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFINSP-SP | CITYWIDE WATERFRONT INSPECTIONS AT VARIOUS WPCPS | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Dec 2021 | Feb 2025 | May 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFINSP-SP | CITYWIDE WATERFRONT INSPECTIONS AT VARIOUS WPCPS | 9 | SUBSTANTIAL COMPLETION | Dec 2021 | Feb 2022 | May 2025 | Jul 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFINSP-SP | CITYWIDE WATERFRONT INSPECTIONS AT VARIOUS WPCPS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2022 | Mar 2022 | Jul 2025 | Aug 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WSRRF-102 | Upgrade Grand Gorge,T'ville, G'ville and Pine Hill WSRRF's | 1 | DEVELOP SCOPE | Jul 2024 | Mar 2025 | Jul 2024 | Mar 2025
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WSRRF-102 | Upgrade Grand Gorge,T'ville, G'ville and Pine Hill WSRRF's | 2 | PRELIMINARY DESIGN | Mar 2025 | Mar 2026 | Mar 2025 | Mar 2026
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WSRRF-102 | Upgrade Grand Gorge,T'ville, G'ville and Pine Hill WSRRF's | 3 | FINAL DESIGN | Mar 2026 | Sep 2027 | Mar 2026 | Sep 2027
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WSRRF-102 | Upgrade Grand Gorge,T'ville, G'ville and Pine Hill WSRRF's | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2027 | Jun 2028 | Sep 2027 | Jun 2028
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WSRRF-102 | Upgrade Grand Gorge,T'ville, G'ville and Pine Hill WSRRF's | 5 | CONSTRUCTION TO 25% | Jun 2028 | Jun 2029 | Jun 2028 | Jun 2029
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WSRRF-102 | Upgrade Grand Gorge,T'ville, G'ville and Pine Hill WSRRF's | 6 | CONSTRUCTION TO 50% | Jun 2029 | May 2030 | Jun 2029 | May 2030
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WSRRF-102 | Upgrade Grand Gorge,T'ville, G'ville and Pine Hill WSRRF's | 7 | CONSTRUCTION TO 75% | May 2030 | May 2031 | May 2030 | May 2031
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WSRRF-102 | Upgrade Grand Gorge,T'ville, G'ville and Pine Hill WSRRF's | 8 | ORIGINAL EQUIP & FURNISHING | May 2031 | Feb 2032 | May 2031 | Feb 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WSRRF-102 | Upgrade Grand Gorge,T'ville, G'ville and Pine Hill WSRRF's | 9 | SUBSTANTIAL COMPLETION | Feb 2032 | Aug 2032 | Feb 2032 | Aug 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WSRRF-102 | Upgrade Grand Gorge,T'ville, G'ville and Pine Hill WSRRF's | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2032 | Nov 2032 | Aug 2032 | Nov 2032
20231026 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WWMGT-18 | FAD 18-22 COMMUNITY WASTEWATER MGMT. | 1 | DEVELOP SCOPE | May 2019 | Apr 2029 | May 2019 | Apr 2029
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-281D | CITYWIDE Female Locker Rooms | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-281D | CITYWIDE Female Locker Rooms | 2 | PRELIMINARY DESIGN | Sep 2015 | Mar 2016 | Sep 2015 | Mar 2016
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-281D | CITYWIDE Female Locker Rooms | 3 | FINAL DESIGN | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-281D | CITYWIDE Female Locker Rooms | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2017 | Mar 2018 | Mar 2017 | Mar 2018
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-281D | CITYWIDE Female Locker Rooms | 5 | CONSTRUCTION TO 25% | Mar 2018 | Mar 2019 | Mar 2018 | Mar 2019
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-281D | CITYWIDE Female Locker Rooms | 6 | CONSTRUCTION TO 50% | Mar 2019 | Mar 2020 | Mar 2019 | Mar 2020
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-281D | CITYWIDE Female Locker Rooms | 7 | CONSTRUCTION TO 75% | Mar 2020 | Mar 2021 | Mar 2020 | Mar 2021
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-281D | CITYWIDE Female Locker Rooms | 8 | SUBSTANTIAL COMPLETION | Mar 2021 | May 2023 | Mar 2021 | May 2023
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-281D | CITYWIDE Female Locker Rooms | 9 | PUNCHLIST COMPLETE, JOB CLOSED | May 2023 | Jul 2025 | May 2023 | Jul 2025
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366D | Construct/Reconstruct composting sites Citywide | 1 | DEVELOP SCOPE | May 2014 | Jul 2014 | May 2014 | Jul 2014
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366D | Construct/Reconstruct composting sites Citywide | 2 | PRELIMINARY DESIGN | Jul 2014 | Jan 2015 | Jul 2014 | Jan 2015
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366D | Construct/Reconstruct composting sites Citywide | 3 | FINAL DESIGN | Jan 2015 | Jan 2016 | Jan 2015 | Jan 2016
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366D | Construct/Reconstruct composting sites Citywide | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2016 | Jan 2017 | Jan 2016 | Jan 2017
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366D | Construct/Reconstruct composting sites Citywide | 5 | CONSTRUCTION TO 25% | Jan 2017 | Jan 2018 | Jan 2017 | Jan 2023
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366D | Construct/Reconstruct composting sites Citywide | 6 | CONSTRUCTION TO 50% | Jan 2018 | Jan 2019 | Jan 2023 | Jan 2024
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366D | Construct/Reconstruct composting sites Citywide | 7 | CONSTRUCTION TO 75% | Jan 2019 | Jan 2020 | Jan 2024 | Jan 2025
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366D | Construct/Reconstruct composting sites Citywide | 8 | SUBSTANTIAL COMPLETION | Jan 2020 | Jan 2021 | Jan 2025 | Jan 2026
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366D | Construct/Reconstruct composting sites Citywide | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2021 | Jan 2022 | Jan 2026 | Jan 2027
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366F | BROOKLYN Greenpoint Community Composting | 1 | DEVELOP SCOPE | Mar 2021 | Apr 2021 | Mar 2021 | Nov 2021
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366F | BROOKLYN Greenpoint Community Composting | 2 | PRELIMINARY DESIGN | Apr 2021 | Jun 2021 | Nov 2021 | Jul 2022
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366F | BROOKLYN Greenpoint Community Composting | 3 | FINAL DESIGN | Jun 2021 | Aug 2021 | Jul 2022 | Sep 2022
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366F | BROOKLYN Greenpoint Community Composting | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2021 | Nov 2021 | Sep 2022 | Dec 2022
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366F | BROOKLYN Greenpoint Community Composting | 5 | CONSTRUCTION TO 25% | Nov 2021 | May 2022 | Dec 2022 | Mar 2023
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366F | BROOKLYN Greenpoint Community Composting | 6 | CONSTRUCTION TO 50% | May 2022 | Nov 2022 | Mar 2023 | Jun 2023
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366F | BROOKLYN Greenpoint Community Composting | 7 | CONSTRUCTION TO 75% | Nov 2022 | May 2023 | Jun 2023 | Sep 2023
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366F | BROOKLYN Greenpoint Community Composting | 8 | SUBSTANTIAL COMPLETION | May 2023 | May 2024 | Sep 2023 | May 2024
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366F | BROOKLYN Greenpoint Community Composting | 9 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | May 2025 | May 2024 | May 2025
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-439 | DSNY FACILITY REHAB, CITYWIDE | 1 | DEVELOP SCOPE | Jul 2016 | Sep 2016 | Jul 2016 | Sep 2016
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-439 | DSNY FACILITY REHAB, CITYWIDE | 2 | PRELIMINARY DESIGN | Sep 2016 | Sep 2016 | Sep 2016 | Sep 2018
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-439 | DSNY FACILITY REHAB, CITYWIDE | 3 | FINAL DESIGN | Dec 2016 | Apr 2017 | Jan 2022 | Jan 2023
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-439 | DSNY FACILITY REHAB, CITYWIDE | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2017 | Apr 2018 | Jan 2023 | Jan 2024
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-439 | DSNY FACILITY REHAB, CITYWIDE | 5 | CONSTRUCTION TO 25% | Apr 2018 | Apr 2019 | Jan 2024 | Jan 2025
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-439 | DSNY FACILITY REHAB, CITYWIDE | 6 | CONSTRUCTION TO 50% | Apr 2019 | Apr 2020 | Jan 2025 | Jan 2027
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-439 | DSNY FACILITY REHAB, CITYWIDE | 7 | CONSTRUCTION TO 75% | Apr 2020 | Apr 2021 | Jan 2027 | Jan 2029
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-439 | DSNY FACILITY REHAB, CITYWIDE | 8 | SUBSTANTIAL COMPLETION | Apr 2021 | Jul 2023 | Jan 2028 | Apr 2030
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-439 | DSNY FACILITY REHAB, CITYWIDE | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2023 | Feb 2025 | Apr 2030 | Nov 2031
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S216-240 | DSNY PIER WORK RECONSTRUCTION CITYWIDE | 1 | DEVELOP SCOPE | Jan 2021 | Jun 2021 | Jan 2021 | Jun 2021
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S216-240 | DSNY PIER WORK RECONSTRUCTION CITYWIDE | 2 | PRELIMINARY DESIGN | Jun 2021 | Dec 2021 | Jun 2021 | Dec 2021
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S216-240 | DSNY PIER WORK RECONSTRUCTION CITYWIDE | 3 | FINAL DESIGN | Dec 2021 | Jun 2022 | Dec 2021 | Jun 2022
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S216-240 | DSNY PIER WORK RECONSTRUCTION CITYWIDE | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Jul 2024 | Jun 2022 | Jul 2024
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S216-240 | DSNY PIER WORK RECONSTRUCTION CITYWIDE | 5 | CONSTRUCTION TO 25% | Jul 2024 | Aug 2026 | Jul 2024 | Aug 2026
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S216-240 | DSNY PIER WORK RECONSTRUCTION CITYWIDE | 6 | CONSTRUCTION TO 50% | Aug 2026 | Aug 2028 | Aug 2026 | Aug 2028
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S216-240 | DSNY PIER WORK RECONSTRUCTION CITYWIDE | 7 | CONSTRUCTION TO 75% | Aug 2028 | Sep 2030 | Aug 2028 | Sep 2030
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S216-240 | DSNY PIER WORK RECONSTRUCTION CITYWIDE | 8 | SUBSTANTIAL COMPLETION | Sep 2030 | Feb 2031 | Sep 2030 | Feb 2031
20231026 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S216-240 | DSNY PIER WORK RECONSTRUCTION CITYWIDE | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2031 | May 2031 | Feb 2031 | May 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BIKE2030 | BIKE NETWORK DEVELOPMENT 2030 | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2008 | Jun 2008 | Jun 2016 | Jul 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BIKE2030 | BIKE NETWORK DEVELOPMENT 2030 | 2 | CONSTRUCTION START | Jul 2008 | Aug 2008 | Jul 2025 | Aug 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BIKE2030 | BIKE NETWORK DEVELOPMENT 2030 | 3 | CONSTRUCTION COMPLETION | Aug 2008 | Mar 2010 | Aug 2026 | Jun 2032
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC231F | QUEENSBORO BRIDGE #10 OVER EAST RIVER | 1 | DEVELOP SCOPE | Jun 2015 | Jun 2016 | Apr 2020 | Apr 2020
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC231F | QUEENSBORO BRIDGE #10 OVER EAST RIVER | 2 | DESIGN START | Jun 2016 | Jun 2020 | Apr 2016 | Jan 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC231F | QUEENSBORO BRIDGE #10 OVER EAST RIVER | 3 | CONSTRUCTION START | Jun 2020 | Jun 2022 | Jul 2018 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC253D | WILLIAMSBURG BRIDGE MISC REPAIRS AND PAINTING FY20 | 1 | DEVELOP SCOPE | Jul 2016 | Jun 2017 | Aug 2016 | Aug 2016
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC253D | WILLIAMSBURG BRIDGE MISC REPAIRS AND PAINTING FY20 | 2 | DESIGN START | Jul 2017 | Jun 2021 | Aug 2018 | May 2020
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC253D | WILLIAMSBURG BRIDGE MISC REPAIRS AND PAINTING FY20 | 3 | CONSTRUCTION START | Jun 2021 | Jun 2023 | Jul 2022 | Jul 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC270D | BROOKLYN BRIDGE REHABILITATION OF APPOACH ARCHES FY19 | 1 | DEVELOP SCOPE | Jun 2019 | Jun 2020 | May 2017 | Jul 2017
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC270D | BROOKLYN BRIDGE REHABILITATION OF APPOACH ARCHES FY19 | 2 | DESIGN START | Jun 2020 | Jun 2024 | Apr 2016 | Aug 2018
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC270D | BROOKLYN BRIDGE REHABILITATION OF APPOACH ARCHES FY19 | 3 | CONSTRUCTION START | Jun 2024 | Jun 2026 | Sep 2019 | Jun 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRCHAZMIG | HAZARD MITIGATION (EAST RIVER BRIDGES - CITYWIDE) | 1 | DEVELOP SCOPE | Jul 2009 | Jun 2010 | Jun 2018 | Jun 2019
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRCHAZMIG | HAZARD MITIGATION (EAST RIVER BRIDGES - CITYWIDE) | 2 | DESIGN START | Jul 2010 | Jun 2014 | Jun 2019 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRCHAZMIG | HAZARD MITIGATION (EAST RIVER BRIDGES - CITYWIDE) | 3 | CONSTRUCTION START | Jun 2014 | Jun 2016 | Jun 2023 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRKA24039 | GRAND STREET/ NEWTON CREEK BIN: 2240390 | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Feb 2018 | Mar 2018
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRKA24039 | GRAND STREET/ NEWTON CREEK BIN: 2240390 | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Jul 2019 | Oct 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRKA24039 | GRAND STREET/ NEWTON CREEK BIN: 2240390 | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Oct 2021 | Aug 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRKA24039 | GRAND STREET/ NEWTON CREEK BIN: 2240390 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2023 | Mar 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRKA24039 | GRAND STREET/ NEWTON CREEK BIN: 2240390 | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Apr 2024 | Jan 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRKA24039 | GRAND STREET/ NEWTON CREEK BIN: 2240390 | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Jan 2025 | Nov 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRKA24039 | GRAND STREET/ NEWTON CREEK BIN: 2240390 | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Nov 2025 | Aug 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRKA24039 | GRAND STREET/ NEWTON CREEK BIN: 2240390 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Aug 2026 | Nov 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRKA24039 | GRAND STREET/ NEWTON CREEK BIN: 2240390 | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Sep 2027 | Sep 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRKA24039 | GRAND STREET/ NEWTON CREEK BIN: 2240390 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Sep 2027 | Dec 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRX287S | MACOMBS DAM BRIDGE - REHAB OF FENDER SYSTEM & 155TH VIA | 1 | DEVELOP SCOPE | Jul 2009 | Jun 2010 | Jun 2022 | Jun 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRX287S | MACOMBS DAM BRIDGE - REHAB OF FENDER SYSTEM & 155TH VIA | 2 | DESIGN START | Jul 2010 | Jun 2014 | Jul 2022 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRX287S | MACOMBS DAM BRIDGE - REHAB OF FENDER SYSTEM & 155TH VIA | 3 | CONSTRUCTION START | Jun 2014 | Jun 2016 | Jul 2023 | Jun 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BUSLANSY3 | PURCHASE & INSTALL BUS LANE PHOTO ENFORCEMENT SYSTEM | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Jun 2021 | Jun 2028 | Jun 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BUSLANSY3 | PURCHASE & INSTALL BUS LANE PHOTO ENFORCEMENT SYSTEM | 2 | CONSTRUCTION START | Jul 2021 | Aug 2021 | Jul 2028 | Aug 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BUSLANSY3 | PURCHASE & INSTALL BUS LANE PHOTO ENFORCEMENT SYSTEM | 3 | CONSTRUCTION COMPLETION | Aug 2021 | Mar 2023 | Aug 2028 | Mar 2033
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BUSLANSY4 | Bus Lane Cameras System- CW- Streets Plan | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Jun 2023 | Jun 2024 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BUSLANSY4 | Bus Lane Cameras System- CW- Streets Plan | 2 | CONSTRUCTION START | Jul 2023 | Aug 2023 | Jul 2024 | Aug 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BUSLANSY4 | Bus Lane Cameras System- CW- Streets Plan | 3 | CONSTRUCTION COMPLETION | Aug 2023 | Mar 2025 | Aug 2024 | Mar 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5447 | MISCELLANEOUS UPGRADES TO FERRYBOATS | 1 | DEVELOP SCOPE | Jun 2008 | Jun 2009 | Jun 2025 | Jun 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5447 | MISCELLANEOUS UPGRADES TO FERRYBOATS | 2 | DESIGN START | Jun 2009 | Jun 2011 | Jun 2026 | Jun 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5447 | MISCELLANEOUS UPGRADES TO FERRYBOATS | 3 | CONSTRUCTION START | Jun 2011 | Jun 2013 | Jun 2028 | Jun 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5586 | REPLACEMENT OF COSGROVE FERRY BOAT | 1 | DEVELOP SCOPE | Jul 2006 | Jun 2007 | Jul 2017 | Jun 2018
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5586 | REPLACEMENT OF COSGROVE FERRY BOAT | 2 | DESIGN START | Jul 2007 | Jun 2009 | Jul 2018 | Jun 2020
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5586 | REPLACEMENT OF COSGROVE FERRY BOAT | 3 | CONSTRUCTION START | Jun 2009 | Jun 2011 | Jul 2020 | Jun 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5589AUS | DRYDOCK AUSTEN CLASS FERRY BOATS | 1 | DEVELOP SCOPE | Jun 2011 | Jun 2012 | Jun 2020 | Jun 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5589AUS | DRYDOCK AUSTEN CLASS FERRY BOATS | 2 | DESIGN START | Jun 2012 | Jun 2014 | Jun 2021 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5589AUS | DRYDOCK AUSTEN CLASS FERRY BOATS | 3 | CONSTRUCTION START | Jun 2014 | Jun 2016 | Jun 2023 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5BARBERI | Drydocking and Reconstructtion of Barberi Class Ferryboats | 1 | DEVELOP SCOPE | Jun 2010 | Jun 2011 | Jun 2016 | Jun 2017
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5BARBERI | Drydocking and Reconstructtion of Barberi Class Ferryboats | 2 | DESIGN START | Jun 2011 | Jun 2013 | Jun 2017 | Jun 2019
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5BARBERI | Drydocking and Reconstructtion of Barberi Class Ferryboats | 3 | CONSTRUCTION START | Jun 2013 | Jun 2015 | Jun 2019 | Jun 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | CONG2030 | CONGESTED CORRIDORS/ GROWTH AREAS | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2008 | Jun 2008 | Jun 2014 | Jun 2014
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | CONG2030 | CONGESTED CORRIDORS/ GROWTH AREAS | 2 | CONSTRUCTION START | Jul 2008 | Aug 2008 | Jul 2014 | Aug 2014
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | CONG2030 | CONGESTED CORRIDORS/ GROWTH AREAS | 3 | CONSTRUCTION COMPLETION | Aug 2008 | Mar 2010 | Aug 2014 | Jun 2033
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FACLUMP | LUMP SUM FOR FACILITIES | 1 | DEVELOP SCOPE | Jun 2010 | May 2011
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FACLUMP | LUMP SUM FOR FACILITIES | 2 | DESIGN START | Jun 2011 | May 2015 | Jun 2022 | May 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FACLUMP | LUMP SUM FOR FACILITIES | 3 | CONSTRUCTION START | May 2015 | May 2017 | Jun 2023 | May 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FACLUMP | LUMP SUM FOR FACILITIES | 5 | CONSTRUCTION START | May 2015 | May 2017 | May 2027 | May 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FARRSLIP | Arrestors for all slips | 1 | DEVELOP SCOPE | Jun 2016 | Jun 2017 | Jun 2023 | Nov 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FARRSLIP | Arrestors for all slips | 2 | DESIGN START | Jun 2017 | Jun 2019 | Dec 2023 | Nov 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FARRSLIP | Arrestors for all slips | 3 | CONSTRUCTION START | Jun 2019 | Jun 2021 | Nov 2025 | Nov 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FATERMTBC | STG & WHT Ferry Terminals Transfer Bridge Control Update | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2023 | Jun 2021 | Jun 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FATERMTBC | STG & WHT Ferry Terminals Transfer Bridge Control Update | 2 | DESIGN START | Jun 2023 | Jun 2025 | Jun 2022 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FATERMTBC | STG & WHT Ferry Terminals Transfer Bridge Control Update | 3 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Jun 2024 | Jun 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FAVESSPC | Ferry Terminals Vessel Passenger Counters | 1 | DEVELOP SCOPE | Jun 2017 | Jun 2018 | Jun 2017 | Jun 2018
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FAVESSPC | Ferry Terminals Vessel Passenger Counters | 2 | DESIGN START | Jun 2018 | Jun 2020 | Jun 2018 | Jun 2020
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FAVESSPC | Ferry Terminals Vessel Passenger Counters | 3 | CONSTRUCTION START | Jun 2020 | Jun 2022 | Jun 2020 | Jun 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEAN2019 | STREET LIGHTING ANNUAL CONSTRUCTION 2019 | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Jun 2018 | Jun 2024 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEAN2019 | STREET LIGHTING ANNUAL CONSTRUCTION 2019 | 2 | CONSTRUCTION START | Jul 2018 | Aug 2018 | Jul 2024 | Aug 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEAN2019 | STREET LIGHTING ANNUAL CONSTRUCTION 2019 | 3 | CONSTRUCTION COMPLETION | Aug 2018 | Mar 2020 | Aug 2024 | Mar 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEHD2023 | Highways & Parks Distribution, citywide FY23 | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEHD2023 | Highways & Parks Distribution, citywide FY23 | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEHD2023 | Highways & Parks Distribution, citywide FY23 | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEHD2023 | Highways & Parks Distribution, citywide FY23 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEHD2023 | Highways & Parks Distribution, citywide FY23 | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEHD2023 | Highways & Parks Distribution, citywide FY23 | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEHD2023 | Highways & Parks Distribution, citywide FY23 | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEHD2023 | Highways & Parks Distribution, citywide FY23 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEHD2023 | Highways & Parks Distribution, citywide FY23 | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEHD2023 | Highways & Parks Distribution, citywide FY23 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1013EQ | SHOP EQUIPMENT FOR BRIDGES | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1013EQ | SHOP EQUIPMENT FOR BRIDGES | 2 | DESIGN START | Jun 2023 | Jun 2027 | Jun 2022 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1013EQ | SHOP EQUIPMENT FOR BRIDGES | 3 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2023 | Jun 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1013EQ | SHOP EQUIPMENT FOR BRIDGES | 5 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2027 | Jun 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1014GP | WYTHE AVE. EXPLOSION PROOF CONTAINER | 1 | DEVELOP SCOPE | Jun 2020 | Jul 2020
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1014GP | WYTHE AVE. EXPLOSION PROOF CONTAINER | 2 | DESIGN START | Jul 2020 | Jan 2021 | Jun 2026 | Jul 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1014GP | WYTHE AVE. EXPLOSION PROOF CONTAINER | 3 | CONSTRUCTION START | Jan 2021 | Jun 2021 | Jul 2026 | Jan 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1014GP | WYTHE AVE. EXPLOSION PROOF CONTAINER | 5 | CONSTRUCTION START | Jan 2021 | Jun 2021 | Jan 2027 | Jun 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070BR | Protective Coating of Various Bridges in Brooklyn | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070BR | Protective Coating of Various Bridges in Brooklyn | 2 | DESIGN START | Jun 2021 | Jun 2025 | Jun 2022 | Jul 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070BR | Protective Coating of Various Bridges in Brooklyn | 3 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Jun 2023 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070BR | Protective Coating of Various Bridges in Brooklyn | 5 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Jun 2024 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070BW | Protective Coating of Broadway Bridge over Harlem River | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070BW | Protective Coating of Broadway Bridge over Harlem River | 2 | DESIGN START | Jun 2021 | Jun 2025 | Jun 2028 | Jun 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070BW | Protective Coating of Broadway Bridge over Harlem River | 3 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Jun 2029 | Jun 2033
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070BW | Protective Coating of Broadway Bridge over Harlem River | 5 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Jun 2033 | Jun 2035
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070BX | Protective Coating of Various Bridges in the Bronx | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070BX | Protective Coating of Various Bridges in the Bronx | 2 | DESIGN START | Jun 2023 | Jun 2027 | Jun 2022 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070BX | Protective Coating of Various Bridges in the Bronx | 3 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2023 | Jun 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070BX | Protective Coating of Various Bridges in the Bronx | 5 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2027 | Jun 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070EN | Protective Coating of LIRR and East New York Bridges | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070EN | Protective Coating of LIRR and East New York Bridges | 2 | DESIGN START | Jun 2022 | Jun 2026 | Jun 2021 | Jun 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070EN | Protective Coating of LIRR and East New York Bridges | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2022 | Jun 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070EN | Protective Coating of LIRR and East New York Bridges | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070GR | Protective Coating of Greenpoint Avenue Bridge over Newtown | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070GR | Protective Coating of Greenpoint Avenue Bridge over Newtown | 2 | DESIGN START | Jun 2024 | Jun 2028 | Jun 2023 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070GR | Protective Coating of Greenpoint Avenue Bridge over Newtown | 3 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jun 2024 | Jun 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070GR | Protective Coating of Greenpoint Avenue Bridge over Newtown | 5 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jun 2028 | Jun 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070LR | Protective Coating of LIRR Bay Ridge Bridges | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070LR | Protective Coating of LIRR Bay Ridge Bridges | 2 | DESIGN START | Jun 2023 | Jun 2027 | Jun 2022 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070LR | Protective Coating of LIRR Bay Ridge Bridges | 3 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2023 | Jun 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070LR | Protective Coating of LIRR Bay Ridge Bridges | 5 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2027 | Jun 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070MD | Protective Coating of Macombs Dam Bridge | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070MD | Protective Coating of Macombs Dam Bridge | 2 | DESIGN START | Jun 2021 | Jun 2025 | Jun 2020 | Jun 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070MD | Protective Coating of Macombs Dam Bridge | 3 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Jun 2021 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070MD | Protective Coating of Macombs Dam Bridge | 5 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Jun 2025 | Jun 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070MH | Protective Coating of Various Bridges in Manhattan | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070MH | Protective Coating of Various Bridges in Manhattan | 2 | DESIGN START | Jun 2023 | Jun 2027 | Jun 2022 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070MH | Protective Coating of Various Bridges in Manhattan | 3 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2023 | Jun 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070MH | Protective Coating of Various Bridges in Manhattan | 5 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2027 | Jun 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070RD | Protective Coating of Riverside Drive Bridge over W 125th St | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070RD | Protective Coating of Riverside Drive Bridge over W 125th St | 2 | DESIGN START | Jun 2021 | Jun 2025 | Jun 2020 | Jun 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070RD | Protective Coating of Riverside Drive Bridge over W 125th St | 3 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Jun 2021 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070RD | Protective Coating of Riverside Drive Bridge over W 125th St | 5 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Jun 2025 | Jun 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070WB | Williamsburg Bridge Painting | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070WB | Williamsburg Bridge Painting | 2 | DESIGN START | Jun 2022 | Jun 2026 | Jun 2021 | Jun 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070WB | Williamsburg Bridge Painting | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2022 | Jun 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070WB | Williamsburg Bridge Painting | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBC1070 | BRIDGE PROTECTIVE COATING | 1 | DEVELOP SCOPE | Jun 2012 | Jun 2013
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBC1070 | BRIDGE PROTECTIVE COATING | 2 | DESIGN START | Jun 2013 | Jun 2017 | Jun 2022 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBC1070 | BRIDGE PROTECTIVE COATING | 3 | CONSTRUCTION START | Jun 2017 | Jun 2019 | Jun 2023 | Jun 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBC1070 | BRIDGE PROTECTIVE COATING | 5 | CONSTRUCTION START | Jun 2017 | Jun 2019 | Jun 2027 | Jun 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE USA | 1 | DEVELOP SCOPE | Jun 2018 | May 2019
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE USA | 2 | DESIGN START | Jun 2019 | May 2023 | May 2020 | Oct 2020
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE USA | 3 | CONSTRUCTION START | May 2023 | May 2025 | Oct 2020 | Oct 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE USA | 5 | CONSTRUCTION START | May 2023 | May 2025 | Oct 2024 | Oct 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US/CAN | 1 | DEVELOP SCOPE | Jun 2018 | May 2019
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US/CAN | 2 | DESIGN START | Jun 2019 | May 2023 | May 2018 | Jul 2020
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US/CAN | 3 | CONSTRUCTION START | May 2023 | May 2025 | May 2018 | Jul 2020
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US/CAN | 5 | CONSTRUCTION START | May 2023 | May 2025 | Jun 2023 | Jul 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN NE USA | 1 | DEVELOP SCOPE | Jun 2018 | May 2019
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN NE USA | 2 | DESIGN START | Jun 2019 | May 2023 | Dec 2020 | Jul 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN NE USA | 3 | CONSTRUCTION START | May 2023 | May 2025 | Jun 2022 | Jul 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN NE USA | 5 | CONSTRUCTION START | May 2023 | May 2025 | Jun 2023 | Jul 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0012 | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | 1 | DEVELOP SCOPE | Jun 2019 | May 2020
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0012 | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | 2 | DESIGN START | May 2020 | May 2024 | May 2021 | Sep 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0012 | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | 3 | CONSTRUCTION START | May 2024 | May 2026 | Sep 2022 | Dec 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0012 | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | 5 | CONSTRUCTION START | May 2024 | May 2026 | Dec 2023 | Dec 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD007P | Citywide Inspection/Monitoring of Bridge Paint Removal & App | 1 | DEVELOP SCOPE | Jul 2023 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD007P | Citywide Inspection/Monitoring of Bridge Paint Removal & App | 2 | DESIGN START | Jun 2024 | Jun 2028 | May 2019 | Apr 2020
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD007P | Citywide Inspection/Monitoring of Bridge Paint Removal & App | 3 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Apr 2020 | Aug 2020
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD007P | Citywide Inspection/Monitoring of Bridge Paint Removal & App | 5 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Aug 2020 | Aug 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD008P | Citywide Inspection/Monitoring of Bridge Paint Removal & App | 1 | DEVELOP SCOPE | Jun 2017 | Jun 2018
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD008P | Citywide Inspection/Monitoring of Bridge Paint Removal & App | 2 | DESIGN START | Jun 2018 | Jun 2022 | May 2018 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD008P | Citywide Inspection/Monitoring of Bridge Paint Removal & App | 3 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Jun 2025 | Aug 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD008P | Citywide Inspection/Monitoring of Bridge Paint Removal & App | 5 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Aug 2026 | Aug 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD009P | Citywide Inspection/Monitoring of Bridge Paint Removal & App | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD009P | Citywide Inspection/Monitoring of Bridge Paint Removal & App | 2 | DESIGN START | Jun 2024 | Jun 2028 | Jun 2023 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD009P | Citywide Inspection/Monitoring of Bridge Paint Removal & App | 3 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jun 2024 | Jun 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD009P | Citywide Inspection/Monitoring of Bridge Paint Removal & App | 5 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jun 2028 | Jun 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD010P | Citywide Inspection/Monitoring of Bridge Paint Removal & App | 1 | DEVELOP SCOPE | Jun 2026 | Jun 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD010P | Citywide Inspection/Monitoring of Bridge Paint Removal & App | 2 | DESIGN START | Jun 2027 | Jun 2031 | Jun 2026 | Jun 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD010P | Citywide Inspection/Monitoring of Bridge Paint Removal & App | 3 | CONSTRUCTION START | Jun 2031 | Jun 2033 | Jun 2027 | Jun 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD010P | Citywide Inspection/Monitoring of Bridge Paint Removal & App | 5 | CONSTRUCTION START | Jun 2031 | Jun 2033 | Jun 2031 | Jun 2033
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013 | Inspection Services at Concrete & Asphalt Plants | 1 | DEVELOP SCOPE | Jul 2023 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013 | Inspection Services at Concrete & Asphalt Plants | 2 | DEVELOP SCOPE | Jun 2024 | Jun 2028 | May 2021 | May 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013 | Inspection Services at Concrete & Asphalt Plants | 3 | DESIGN START | Jun 2028 | Jun 2030 | May 2024 | Jul 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013 | Inspection Services at Concrete & Asphalt Plants | 5 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jul 2025 | Jul 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE US | 1 | DEVELOP SCOPE | Jul 2023 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE US | 2 | DESIGN START | Jun 2024 | Jun 2028 | May 2023 | May 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE US | 3 | CONSTRUCTION START | Jun 2028 | Jun 2030 | May 2026 | Aug 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE US | 5 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Aug 2027 | Aug 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US | 1 | DEVELOP SCOPE | Jul 2023 | Jul 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US | 2 | DESIGN START | Jul 2024 | Jul 2028 | Jul 2021 | Jul 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US | 3 | CONSTRUCTION START | Jul 2028 | Jul 2030 | Jul 2022 | Aug 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US | 5 | CONSTRUCTION START | Jul 2028 | Jul 2030 | Aug 2027 | Aug 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | 1 | DEVELOP SCOPE | Jul 2023 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | 2 | DESIGN START | Jun 2024 | Jun 2028 | Jul 2018 | Jun 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | 3 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jul 2018 | Jun 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | 5 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Aug 2025 | Aug 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD014 | Testing and Sampling of Material (Citywide) | 1 | DEVELOP SCOPE | Jul 2024 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD014 | Testing and Sampling of Material (Citywide) | 2 | DESIGN START | Jul 2025 | Jun 2029 | Jul 2017 | Jun 2018
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD014 | Testing and Sampling of Material (Citywide) | 3 | CONSTRUCTION START | Jun 2029 | Jun 2031 | Jul 2018 | Jul 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD014 | Testing and Sampling of Material (Citywide) | 5 | CONSTRUCTION START | Jun 2029 | Jun 2031 | Jul 2023 | Jul 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015 | INSPECTION SERVICES AT CONCRETE & ASPHALT PLANTS | 1 | DEVELOP SCOPE | Jun 2017 | Jun 2018
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015 | INSPECTION SERVICES AT CONCRETE & ASPHALT PLANTS | 2 | DESIGN START | Jun 2018 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015 | INSPECTION SERVICES AT CONCRETE & ASPHALT PLANTS | 3 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Jun 2022 | Aug 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015 | INSPECTION SERVICES AT CONCRETE & ASPHALT PLANTS | 5 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Aug 2027 | Aug 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE USA | 1 | DEVELOP SCOPE | Jul 2025 | Jun 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE USA | 2 | DEVELOP SCOPE | Jul 2026 | Jun 2030 | Jul 2027 | Jun 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE USA | 3 | DESIGN START | Jun 2030 | Jun 2032 | Jun 2028 | Aug 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE USA | 5 | CONSTRUCTION START | Jun 2030 | Jun 2032 | Aug 2028 | Aug 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US/CAN | 1 | DEVELOP SCOPE | Jul 2025 | Jun 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US/CAN | 2 | DEVELOP SCOPE | Jul 2026 | Jun 2030 | Jul 2023 | Jul 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US/CAN | 3 | DESIGN START | Jun 2030 | Jun 2032 | Jul 2023 | Jul 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US/CAN | 5 | CONSTRUCTION START | Jun 2030 | Jun 2032 | Jul 2023 | Jul 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | 1 | DEVELOP SCOPE | Jun 2015 | Jun 2016
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | 2 | DESIGN START | Jun 2016 | Jun 2020 | Jun 2014 | Jun 2015
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | 3 | CONSTRUCTION START | Jun 2020 | Jun 2022 | Jun 2015 | Jul 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | 5 | CONSTRUCTION START | Jun 2020 | Jun 2022 | Jul 2028 | Jul 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD016 | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | 1 | DEVELOP SCOPE | Jun 2017 | Jun 2018
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD016 | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | 2 | DESIGN START | Jun 2018 | Jun 2022 | Jun 2017 | Jun 2018
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD016 | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | 3 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Jun 2018 | Aug 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD016 | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | 5 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Aug 2026 | Aug 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD017 | Inspection of Services at Concrete and Asphalt Plants | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD017 | Inspection of Services at Concrete and Asphalt Plants | 2 | DESIGN START | Jun 2024 | Jun 2028 | Jun 2023 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD017 | Inspection of Services at Concrete and Asphalt Plants | 3 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jun 2024 | Jun 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD017 | Inspection of Services at Concrete and Asphalt Plants | 5 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jun 2028 | Jun 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD017A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE USA | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD017A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE USA | 2 | DESIGN START | Jun 2024 | Jun 2028 | Jun 2023 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD017A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE USA | 3 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jun 2024 | Jun 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD017A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE USA | 5 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jun 2028 | Jun 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD017B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE USA | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD017B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE USA | 2 | DESIGN START | Jun 2024 | Jun 2028 | Jun 2023 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD017B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE USA | 3 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jun 2024 | Jun 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD017B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE USA | 5 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jun 2028 | Jun 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD017C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD017C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | 2 | DESIGN START | Jun 2024 | Jun 2028 | Jun 2023 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD017C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | 3 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jun 2024 | Jun 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD017C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | 5 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jun 2028 | Jun 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD018 | Testing and Sampling of Material (Citywide) | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD018 | Testing and Sampling of Material (Citywide) | 2 | DESIGN START | Jun 2025 | Jun 2029 | Jun 2024 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD018 | Testing and Sampling of Material (Citywide) | 3 | CONSTRUCTION START | Jun 2029 | Jun 2031 | Jun 2025 | Jun 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD018 | Testing and Sampling of Material (Citywide) | 5 | CONSTRUCTION START | Jun 2029 | Jun 2031 | Jun 2029 | Jun 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD019 | INSPECTION SERVICES AT ASPHALT AND CONCRETE PLANTS | 1 | DEVELOP SCOPE | Jun 2025 | Jun 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD019 | INSPECTION SERVICES AT ASPHALT AND CONCRETE PLANTS | 2 | DESIGN START | Jun 2026 | Jun 2030 | Jun 2025 | Jun 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD019 | INSPECTION SERVICES AT ASPHALT AND CONCRETE PLANTS | 3 | CONSTRUCTION START | Jun 2030 | Jun 2032 | Jun 2026 | Jun 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD019 | INSPECTION SERVICES AT ASPHALT AND CONCRETE PLANTS | 5 | CONSTRUCTION START | Jun 2030 | Jun 2032 | Jun 2030 | Jun 2032
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD019A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE US | 1 | DEVELOP SCOPE | Jun 2026 | Jun 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD019A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE US | 2 | DESIGN START | Jun 2027 | Jun 2031 | Jun 2026 | Jun 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD019A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE US | 3 | CONSTRUCTION START | Jun 2031 | Jun 2033 | Jun 2027 | Jun 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD019A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE US | 5 | CONSTRUCTION START | Jun 2031 | Jun 2033 | Jun 2031 | Jun 2033
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD019B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US | 1 | DEVELOP SCOPE | Jun 2026 | Jun 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD019B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US | 2 | DESIGN START | Jun 2027 | Jun 2031 | Jun 2026 | Jun 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD019B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US | 3 | CONSTRUCTION START | Jun 2031 | Jun 2033 | Jun 2027 | Jun 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD019B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US | 5 | CONSTRUCTION START | Jun 2031 | Jun 2033 | Jun 2031 | Jun 2033
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD019C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | 1 | DEVELOP SCOPE | Jun 2026 | Jun 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD019C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | 2 | DESIGN START | Jun 2027 | Jun 2031 | Jun 2026 | Jun 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD019C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | 3 | CONSTRUCTION START | Jun 2031 | Jun 2033 | Jun 2027 | Jun 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD019C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | 5 | CONSTRUCTION START | Jun 2031 | Jun 2033 | Jun 2031 | Jun 2033
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCITYWIM | Citywide Wiegh-in-Motion System | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCITYWIM | Citywide Wiegh-in-Motion System | 2 | DESIGN START | Jun 2022 | Jun 2026 | Jun 2021 | Jun 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCITYWIM | Citywide Wiegh-in-Motion System | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2022 | Jun 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCITYWIM | Citywide Wiegh-in-Motion System | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR02B | COMPONENT REHABILITATION 02B CONSTRUCTION | 1 | DEVELOP SCOPE | Jul 2004 | Jun 2005
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR02B | COMPONENT REHABILITATION 02B CONSTRUCTION | 2 | DESIGN START | Jul 2005 | Jun 2009 | Jan 2015 | Jun 2015
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR02B | COMPONENT REHABILITATION 02B CONSTRUCTION | 3 | CONSTRUCTION START | Jun 2009 | Jun 2011 | Jun 2012 | Jun 2014
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR02B | COMPONENT REHABILITATION 02B CONSTRUCTION | 5 | CONSTRUCTION START | Jun 2009 | Jun 2011 | Jul 2014 | Jul 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR03B | COMPONENT REHABILITATION 03B CONSTRUCTION | 1 | DEVELOP SCOPE | Jul 2005 | Jun 2006
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR03B | COMPONENT REHABILITATION 03B CONSTRUCTION | 2 | DESIGN START | Jul 2006 | Jun 2010 | May 2015 | Nov 2015
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR03B | COMPONENT REHABILITATION 03B CONSTRUCTION | 3 | CONSTRUCTION START | Jun 2010 | Jun 2012 | Nov 2015 | Nov 2019
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR03B | COMPONENT REHABILITATION 03B CONSTRUCTION | 5 | CONSTRUCTION START | Jun 2010 | Jun 2012 | Nov 2019 | Nov 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR16 | COMPONENT REHAB OF BRIDGES CITYWIDE (8 BRIDGES) | 1 | DEVELOP SCOPE | Jun 2015 | Jun 2016
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR16 | COMPONENT REHAB OF BRIDGES CITYWIDE (8 BRIDGES) | 2 | DESIGN START | Jun 2016 | Jun 2020 | Jun 2015 | Jun 2016
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR16 | COMPONENT REHAB OF BRIDGES CITYWIDE (8 BRIDGES) | 3 | CONSTRUCTION START | Jun 2020 | Jun 2022 | Jun 2017 | Oct 2019
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR16 | COMPONENT REHAB OF BRIDGES CITYWIDE (8 BRIDGES) | 5 | CONSTRUCTION START | Jun 2020 | Jun 2022 | Oct 2019 | Oct 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR21A | COMPONENT REHAB OF BRIDGES 21A | 1 | DEVELOP SCOPE | Jun 2016 | Jun 2017
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR21A | COMPONENT REHAB OF BRIDGES 21A | 2 | DESIGN START | Jun 2017 | Jun 2021 | Jan 2022 | Feb 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR21A | COMPONENT REHAB OF BRIDGES 21A | 3 | CONSTRUCTION START | Jun 2021 | Jun 2023 | Feb 2022 | Jan 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR21A | COMPONENT REHAB OF BRIDGES 21A | 5 | CONSTRUCTION START | Jun 2021 | Jun 2023 | Feb 2026 | Jan 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR21B | COMPONENT REHAB OF BRIDGES 21B | 1 | DEVELOP SCOPE | Jun 2016 | Jun 2017
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR21B | COMPONENT REHAB OF BRIDGES 21B | 2 | DESIGN START | Jun 2017 | Jun 2021 | Jan 2021 | Feb 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR21B | COMPONENT REHAB OF BRIDGES 21B | 3 | CONSTRUCTION START | Jun 2021 | Jun 2023 | Feb 2021 | Feb 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR21B | COMPONENT REHAB OF BRIDGES 21B | 5 | CONSTRUCTION START | Jun 2021 | Jun 2023 | Feb 2025 | Feb 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR22A | COMPONENT REHAB OF BRIDGES 22A | 1 | DEVELOP SCOPE | Jun 2017 | Jun 2018
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR22A | COMPONENT REHAB OF BRIDGES 22A | 2 | DESIGN START | Jun 2018 | Jun 2022 | Oct 2019 | Jan 2020
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR22A | COMPONENT REHAB OF BRIDGES 22A | 3 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Jan 2020 | Jan 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR22A | COMPONENT REHAB OF BRIDGES 22A | 5 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Jan 2024 | Jan 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR22B | COMPONENT REHAB OF BRIDGES 22B | 1 | DEVELOP SCOPE | Jun 2017 | Jun 2018
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR22B | COMPONENT REHAB OF BRIDGES 22B | 2 | DESIGN START | Jun 2018 | Jun 2022 | Oct 2019 | Jan 2020
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR22B | COMPONENT REHAB OF BRIDGES 22B | 3 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Jan 2020 | Jan 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR22B | COMPONENT REHAB OF BRIDGES 22B | 5 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Jan 2024 | Jan 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23A | COMPONENT REHAB OF BRIDGES 23A | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | May 2018 | Apr 2019
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23A | COMPONENT REHAB OF BRIDGES 23A | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Apr 2019 | Aug 2019
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23A | COMPONENT REHAB OF BRIDGES 23A | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Aug 2019 | Feb 2020
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23A | COMPONENT REHAB OF BRIDGES 23A | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Feb 2020 | May 2020
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23A | COMPONENT REHAB OF BRIDGES 23A | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | May 2020 | Sep 2020
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23A | COMPONENT REHAB OF BRIDGES 23A | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Sep 2020 | Dec 2020
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23A | COMPONENT REHAB OF BRIDGES 23A | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Dec 2020 | Apr 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23A | COMPONENT REHAB OF BRIDGES 23A | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Apr 2021 | Jul 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23A | COMPONENT REHAB OF BRIDGES 23A | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jul 2021 | Sep 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23A | COMPONENT REHAB OF BRIDGES 23A | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Sep 2021 | Jul 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23B | COMPONENT REHAB OF BRIDGES 23B | 1 | DEVELOP SCOPE | Jun 2019 | Jun 2020
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23B | COMPONENT REHAB OF BRIDGES 23B | 2 | DESIGN START | Jun 2020 | Jun 2024 | May 2015 | Aug 2019
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23B | COMPONENT REHAB OF BRIDGES 23B | 3 | CONSTRUCTION START | Jun 2024 | Jun 2026 | Aug 2019 | Aug 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23B | COMPONENT REHAB OF BRIDGES 23B | 5 | CONSTRUCTION START | Jun 2024 | Jun 2026 | Aug 2023 | Aug 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR24A | COMPONENT REHAB OF BRIDGES 24A | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR24A | COMPONENT REHAB OF BRIDGES 24A | 2 | DESIGN START | Jun 2023 | Jun 2027 | Jun 2022 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR24A | COMPONENT REHAB OF BRIDGES 24A | 3 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2023 | Jun 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR24A | COMPONENT REHAB OF BRIDGES 24A | 5 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2027 | Jun 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR24B | COMPONENT REHAB OF BRIDGES 24B | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR24B | COMPONENT REHAB OF BRIDGES 24B | 2 | DESIGN START | Jun 2023 | Jun 2027 | Jun 2022 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR24B | COMPONENT REHAB OF BRIDGES 24B | 3 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2023 | Jun 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR24B | COMPONENT REHAB OF BRIDGES 24B | 5 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2027 | Jun 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR25A | COMPONENT REHAB OF BRIDGES 25A | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR25A | COMPONENT REHAB OF BRIDGES 25A | 2 | DESIGN START | Jun 2021 | Jun 2025 | Jun 2023 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR25A | COMPONENT REHAB OF BRIDGES 25A | 3 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Jun 2024 | Jun 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR25A | COMPONENT REHAB OF BRIDGES 25A | 5 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Jun 2028 | Jun 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR25B | COMPONENT REHAB OF BRIDGES 25B | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR25B | COMPONENT REHAB OF BRIDGES 25B | 2 | DESIGN START | Jun 2021 | Jun 2025 | Jun 2023 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR25B | COMPONENT REHAB OF BRIDGES 25B | 3 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Jun 2024 | Jun 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR25B | COMPONENT REHAB OF BRIDGES 25B | 5 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Jun 2028 | Jun 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR26A | COMPONENT REHAB OF BRIDGES 26A | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR26A | COMPONENT REHAB OF BRIDGES 26A | 2 | DESIGN START | Jun 2023 | Jun 2027 | Jun 2022 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR26A | COMPONENT REHAB OF BRIDGES 26A | 3 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2023 | Jun 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR26A | COMPONENT REHAB OF BRIDGES 26A | 5 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2027 | Jun 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR26B | COMPONENT REHAB OF BRIDGES 26B | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR26B | COMPONENT REHAB OF BRIDGES 26B | 2 | DESIGN START | Jun 2023 | Jun 2027 | Jun 2022 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR26B | COMPONENT REHAB OF BRIDGES 26B | 3 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2023 | Jun 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR26B | COMPONENT REHAB OF BRIDGES 26B | 5 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2027 | Jun 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR27A | COMPONENT REHAB OF BRIDGES 27A | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR27A | COMPONENT REHAB OF BRIDGES 27A | 2 | DESIGN START | Jun 2023 | Jun 2027 | Jun 2023 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR27A | COMPONENT REHAB OF BRIDGES 27A | 3 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2024 | Jun 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR27A | COMPONENT REHAB OF BRIDGES 27A | 5 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2028 | Jun 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR27B | COMPONENT REHAB OF BRIDGES 27B | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR27B | COMPONENT REHAB OF BRIDGES 27B | 2 | DESIGN START | Jun 2023 | Jun 2027 | Jun 2025 | Jun 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR27B | COMPONENT REHAB OF BRIDGES 27B | 3 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2026 | Jun 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR27B | COMPONENT REHAB OF BRIDGES 27B | 5 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2030 | Jun 2032
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBKBQE | Rehabilitation of BQE (I-278) from Sands St. to Atlantic Ave | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBKBQE | Rehabilitation of BQE (I-278) from Sands St. to Atlantic Ave | 2 | DESIGN START | Jun 2023 | Jun 2027 | Dec 2014 | Apr 2015
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBKBQE | Rehabilitation of BQE (I-278) from Sands St. to Atlantic Ave | 3 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Mar 2017 | Sep 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBKBQE | Rehabilitation of BQE (I-278) from Sands St. to Atlantic Ave | 5 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Mar 2022 | Mar 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBM24064 | Fender System for Roosevelt Island Bridge over East River | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBM24064 | Fender System for Roosevelt Island Bridge over East River | 2 | DESIGN START | Jun 2023 | Jun 2027 | Jun 2022 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBM24064 | Fender System for Roosevelt Island Bridge over East River | 3 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2023 | Jun 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBM24064 | Fender System for Roosevelt Island Bridge over East River | 5 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2027 | Jun 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBMPL10 | Citywide Independent Monitoring of Bridge Lead Paint Removal | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBMPL10 | Citywide Independent Monitoring of Bridge Lead Paint Removal | 2 | DESIGN START | Jun 2024 | Jun 2028 | Jun 2023 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBMPL10 | Citywide Independent Monitoring of Bridge Lead Paint Removal | 3 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jun 2024 | Jun 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBMPL10 | Citywide Independent Monitoring of Bridge Lead Paint Removal | 5 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jun 2028 | Jun 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBMPL11 | Citywide Independent Monitoring of Bridge Lead Paint Removal | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBMPL11 | Citywide Independent Monitoring of Bridge Lead Paint Removal | 2 | DESIGN START | Jun 2024 | Jun 2028 | Jun 2023 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBMPL11 | Citywide Independent Monitoring of Bridge Lead Paint Removal | 3 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jun 2024 | Jun 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBMPL11 | Citywide Independent Monitoring of Bridge Lead Paint Removal | 5 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jun 2028 | Jun 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBMPL12 | Citywide Independent Monitoring of Bridge Lead Paint Removal | 1 | DEVELOP SCOPE | Jun 2025 | Jun 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBMPL12 | Citywide Independent Monitoring of Bridge Lead Paint Removal | 2 | DESIGN START | Jun 2026 | Jun 2030 | Jun 2025 | Jun 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBMPL12 | Citywide Independent Monitoring of Bridge Lead Paint Removal | 3 | CONSTRUCTION START | Jun 2030 | Jun 2032 | Jun 2026 | Jun 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBMPL12 | Citywide Independent Monitoring of Bridge Lead Paint Removal | 5 | CONSTRUCTION START | Jun 2030 | Jun 2032 | Jun 2030 | Jun 2032
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBMPL8 | Citywide Independent Monitoring of Bridge Lead Paint Removal | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBMPL8 | Citywide Independent Monitoring of Bridge Lead Paint Removal | 2 | DESIGN START | Jun 2024 | Jun 2028 | Jun 2023 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBMPL8 | Citywide Independent Monitoring of Bridge Lead Paint Removal | 3 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jun 2024 | Jun 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBMPL8 | Citywide Independent Monitoring of Bridge Lead Paint Removal | 5 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jun 2028 | Jun 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBMPL9 | Citywide Independent Monitoring of Bridge Lead Paint Removal | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBMPL9 | Citywide Independent Monitoring of Bridge Lead Paint Removal | 2 | DESIGN START | Jun 2024 | Jun 2028 | Jun 2023 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBMPL9 | Citywide Independent Monitoring of Bridge Lead Paint Removal | 3 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jun 2024 | Jun 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBMPL9 | Citywide Independent Monitoring of Bridge Lead Paint Removal | 5 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jun 2028 | Jun 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBR10COMP | TEN YR COMP | 1 | DEVELOP SCOPE | Jun 2017 | Jun 2018
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBR10COMP | TEN YR COMP | 2 | DESIGN START | Jun 2018 | Jun 2022 | Jun 2023 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBR10COMP | TEN YR COMP | 3 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Jun 2024 | Jun 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBR10COMP | TEN YR COMP | 5 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Jun 2028 | Jun 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBREP6919 | Emergency Contract for 181st (Washington Bridge) over Harlem | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBREP6919 | Emergency Contract for 181st (Washington Bridge) over Harlem | 2 | DESIGN START | Jun 2021 | Jun 2025 | Jun 2020 | Jun 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBREP6919 | Emergency Contract for 181st (Washington Bridge) over Harlem | 3 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Jun 2021 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBREP6919 | Emergency Contract for 181st (Washington Bridge) over Harlem | 5 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Jun 2025 | Jun 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA1 | In-House Pedestrian Ramp Rehabilitation - Crews | 1 | DEVELOP SCOPE | Jul 2016 | Sep 2016 | Jul 2017 | Sep 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA1 | In-House Pedestrian Ramp Rehabilitation - Crews | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Sep 2028 | Jan 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA1 | In-House Pedestrian Ramp Rehabilitation - Crews | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Jan 2029 | Jul 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA1 | In-House Pedestrian Ramp Rehabilitation - Crews | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Jul 2029 | Oct 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA1 | In-House Pedestrian Ramp Rehabilitation - Crews | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Oct 2029 | Feb 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA1 | In-House Pedestrian Ramp Rehabilitation - Crews | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Feb 2030 | Jun 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA1 | In-House Pedestrian Ramp Rehabilitation - Crews | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Jun 2030 | Oct 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA1 | In-House Pedestrian Ramp Rehabilitation - Crews | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | Oct 2030 | Jan 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA1 | In-House Pedestrian Ramp Rehabilitation - Crews | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Jan 2031 | Mar 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA1 | In-House Pedestrian Ramp Rehabilitation - Crews | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Mar 2031 | Apr 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA2 | In-House Pedestrian Ramp Rehabilitation - OTPS | 1 | DEVELOP SCOPE | Jul 2016 | Sep 2016 | Jul 2017 | Sep 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA2 | In-House Pedestrian Ramp Rehabilitation - OTPS | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Sep 2028 | Jan 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA2 | In-House Pedestrian Ramp Rehabilitation - OTPS | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Jan 2029 | Jul 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA2 | In-House Pedestrian Ramp Rehabilitation - OTPS | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Jul 2029 | Oct 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA2 | In-House Pedestrian Ramp Rehabilitation - OTPS | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Oct 2029 | Feb 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA2 | In-House Pedestrian Ramp Rehabilitation - OTPS | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Feb 2030 | Jun 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA2 | In-House Pedestrian Ramp Rehabilitation - OTPS | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Jun 2030 | Oct 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA2 | In-House Pedestrian Ramp Rehabilitation - OTPS | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | Oct 2030 | Jan 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA2 | In-House Pedestrian Ramp Rehabilitation - OTPS | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Jan 2031 | Mar 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA2 | In-House Pedestrian Ramp Rehabilitation - OTPS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Mar 2031 | Apr 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR06 | CITYWIDE MILLING | 1 | DEVELOP SCOPE | May 2011 | Aug 2011 | May 2023 | Aug 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR06 | CITYWIDE MILLING | 2 | PRELIMINARY DESIGN | Aug 2011 | Dec 2011 | Aug 2024 | Dec 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR06 | CITYWIDE MILLING | 3 | FINAL DESIGN | Dec 2011 | Jun 2012 | Dec 2024 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR06 | CITYWIDE MILLING | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2012 | Sep 2012 | Jun 2025 | Sep 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR06 | CITYWIDE MILLING | 5 | CONSTRUCTION TO 25% | Sep 2012 | Jan 2013 | Sep 2025 | Jan 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR06 | CITYWIDE MILLING | 6 | CONSTRUCTION TO 50% | Jan 2013 | May 2013 | Jan 2026 | May 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR06 | CITYWIDE MILLING | 7 | CONSTRUCTION TO 75% | May 2013 | Sep 2013 | May 2026 | Sep 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR06 | CITYWIDE MILLING | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2013 | Dec 2013 | Sep 2026 | Dec 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR06 | CITYWIDE MILLING | 9 | SUBSTANTIAL COMPLETION | Dec 2013 | Feb 2014 | Dec 2026 | Feb 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR06 | CITYWIDE MILLING | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2014 | Mar 2014 | Feb 2027 | Mar 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21C | Citywide Milling - Brooklyn and Staten Island | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2020 | Sep 2020
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21C | Citywide Milling - Brooklyn and Staten Island | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2020 | Jan 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21C | Citywide Milling - Brooklyn and Staten Island | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2021 | Jul 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21C | Citywide Milling - Brooklyn and Staten Island | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2021 | Oct 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21C | Citywide Milling - Brooklyn and Staten Island | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2021 | Feb 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21C | Citywide Milling - Brooklyn and Staten Island | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2022 | Jun 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21C | Citywide Milling - Brooklyn and Staten Island | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2022 | Oct 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21C | Citywide Milling - Brooklyn and Staten Island | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2022 | Jan 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21C | Citywide Milling - Brooklyn and Staten Island | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2023 | Mar 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21C | Citywide Milling - Brooklyn and Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2023 | Apr 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21E | Citywide Milling - BK, QN, and SI | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21E | Citywide Milling - BK, QN, and SI | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21E | Citywide Milling - BK, QN, and SI | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21E | Citywide Milling - BK, QN, and SI | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21E | Citywide Milling - BK, QN, and SI | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21E | Citywide Milling - BK, QN, and SI | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21E | Citywide Milling - BK, QN, and SI | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21E | Citywide Milling - BK, QN, and SI | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21E | Citywide Milling - BK, QN, and SI | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21E | Citywide Milling - BK, QN, and SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23A | Citywide Milling - Bronx and Queens | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23A | Citywide Milling - Bronx and Queens | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23A | Citywide Milling - Bronx and Queens | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23A | Citywide Milling - Bronx and Queens | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23A | Citywide Milling - Bronx and Queens | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23A | Citywide Milling - Bronx and Queens | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23A | Citywide Milling - Bronx and Queens | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23A | Citywide Milling - Bronx and Queens | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23A | Citywide Milling - Bronx and Queens | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23A | Citywide Milling - Bronx and Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23B | Citywide Milling - Queens and Brooklyn | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23B | Citywide Milling - Queens and Brooklyn | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23B | Citywide Milling - Queens and Brooklyn | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23B | Citywide Milling - Queens and Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23B | Citywide Milling - Queens and Brooklyn | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23B | Citywide Milling - Queens and Brooklyn | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23B | Citywide Milling - Queens and Brooklyn | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23B | Citywide Milling - Queens and Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23B | Citywide Milling - Queens and Brooklyn | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23B | Citywide Milling - Queens and Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23C | Citywide Milling - Brooklyn and Staten Island | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23C | Citywide Milling - Brooklyn and Staten Island | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23C | Citywide Milling - Brooklyn and Staten Island | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23C | Citywide Milling - Brooklyn and Staten Island | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23C | Citywide Milling - Brooklyn and Staten Island | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23C | Citywide Milling - Brooklyn and Staten Island | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23C | Citywide Milling - Brooklyn and Staten Island | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23C | Citywide Milling - Brooklyn and Staten Island | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23C | Citywide Milling - Brooklyn and Staten Island | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23C | Citywide Milling - Brooklyn and Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23CW | Citywide Milling | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23CW | Citywide Milling | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23CW | Citywide Milling | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23CW | Citywide Milling | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23CW | Citywide Milling | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23CW | Citywide Milling | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23CW | Citywide Milling | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23CW | Citywide Milling | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23CW | Citywide Milling | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23CW | Citywide Milling | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW34907 | IN-HOUSE RESURFACING - CREWS&OTHER NON-ASPHALT OTPS | 1 | DEVELOP SCOPE | Jun 2007 | Sep 2007 | Jun 2007 | Sep 2007
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW34907 | IN-HOUSE RESURFACING - CREWS&OTHER NON-ASPHALT OTPS | 2 | DESIGN START | Sep 2007 | Mar 2009 | Sep 2007 | Mar 2009
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW34907 | IN-HOUSE RESURFACING - CREWS&OTHER NON-ASPHALT OTPS | 3 | CONSTRUCTION START | Mar 2009 | Mar 2011 | Mar 2009 | Mar 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWBUSPAD | CITYWIDE BUS PADS | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWBUSPAD | CITYWIDE BUS PADS | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWBUSPAD | CITYWIDE BUS PADS | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWBUSPAD | CITYWIDE BUS PADS | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWBUSPAD | CITYWIDE BUS PADS | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWBUSPAD | CITYWIDE BUS PADS | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWBUSPAD | CITYWIDE BUS PADS | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWBUSPAD | CITYWIDE BUS PADS | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWBUSPAD | CITYWIDE BUS PADS | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWBUSPAD | CITYWIDE BUS PADS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWBUSPAD7 | Bus Pads | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWBUSPAD7 | Bus Pads | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWBUSPAD7 | Bus Pads | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWBUSPAD7 | Bus Pads | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWBUSPAD7 | Bus Pads | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWBUSPAD7 | Bus Pads | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWBUSPAD7 | Bus Pads | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWBUSPAD7 | Bus Pads | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWBUSPAD7 | Bus Pads | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWBUSPAD7 | Bus Pads | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC349M03 | MANHOLE RINGS | 1 | DEVELOP SCOPE | May 2010 | Aug 2010 | May 1997 | Aug 1997
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC349M03 | MANHOLE RINGS | 2 | PRELIMINARY DESIGN | Aug 2010 | Dec 2010 | Aug 1997 | Dec 1997
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC349M03 | MANHOLE RINGS | 3 | FINAL DESIGN | Dec 2010 | Jun 2011 | Dec 1997 | Jun 1998
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC349M03 | MANHOLE RINGS | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2011 | Sep 2011 | Jun 1998 | Sep 2011
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC349M03 | MANHOLE RINGS | 5 | CONSTRUCTION TO 25% | Sep 2011 | Jan 2012 | Sep 2011 | Jan 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC349M03 | MANHOLE RINGS | 6 | CONSTRUCTION TO 50% | Jan 2012 | May 2012 | Jan 2024 | May 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC349M03 | MANHOLE RINGS | 7 | CONSTRUCTION TO 75% | May 2012 | Sep 2012 | May 2024 | Sep 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC349M03 | MANHOLE RINGS | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2012 | Dec 2012 | Sep 2024 | Dec 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC349M03 | MANHOLE RINGS | 9 | SUBSTANTIAL COMPLETION | Dec 2012 | Feb 2013 | Dec 2024 | Feb 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC349M03 | MANHOLE RINGS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2013 | Mar 2013 | Feb 2025 | Mar 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCB25KR | Curb Reconstruction - Brooklyn and Staten Island | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCB25KR | Curb Reconstruction - Brooklyn and Staten Island | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCB25KR | Curb Reconstruction - Brooklyn and Staten Island | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCB25KR | Curb Reconstruction - Brooklyn and Staten Island | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCB25KR | Curb Reconstruction - Brooklyn and Staten Island | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCB25KR | Curb Reconstruction - Brooklyn and Staten Island | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCB25KR | Curb Reconstruction - Brooklyn and Staten Island | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCB25KR | Curb Reconstruction - Brooklyn and Staten Island | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCB25KR | Curb Reconstruction - Brooklyn and Staten Island | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCB25KR | Curb Reconstruction - Brooklyn and Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCB25QXM | Curb Reconstruction - Queens, Bronx and Manhattan | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCB25QXM | Curb Reconstruction - Queens, Bronx and Manhattan | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCB25QXM | Curb Reconstruction - Queens, Bronx and Manhattan | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCB25QXM | Curb Reconstruction - Queens, Bronx and Manhattan | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCB25QXM | Curb Reconstruction - Queens, Bronx and Manhattan | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCB25QXM | Curb Reconstruction - Queens, Bronx and Manhattan | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCB25QXM | Curb Reconstruction - Queens, Bronx and Manhattan | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCB25QXM | Curb Reconstruction - Queens, Bronx and Manhattan | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCB25QXM | Curb Reconstruction - Queens, Bronx and Manhattan | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCB25QXM | Curb Reconstruction - Queens, Bronx and Manhattan | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCFTRLR | Citywide Trailer Rehabilitation | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2023 | Sep 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCFTRLR | Citywide Trailer Rehabilitation | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2023 | Jan 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCFTRLR | Citywide Trailer Rehabilitation | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jan 2024 | Jul 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCFTRLR | Citywide Trailer Rehabilitation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2024 | Oct 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCFTRLR | Citywide Trailer Rehabilitation | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Oct 2024 | Feb 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCFTRLR | Citywide Trailer Rehabilitation | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Feb 2025 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCFTRLR | Citywide Trailer Rehabilitation | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jun 2025 | Oct 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCFTRLR | Citywide Trailer Rehabilitation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Oct 2025 | Jan 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCFTRLR | Citywide Trailer Rehabilitation | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jan 2026 | Mar 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCFTRLR | Citywide Trailer Rehabilitation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Mar 2026 | Apr 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC-HDBP | High-Density Bike Parking | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2024 | Sep 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC-HDBP | High-Density Bike Parking | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2024 | Jan 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC-HDBP | High-Density Bike Parking | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jan 2025 | Jul 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC-HDBP | High-Density Bike Parking | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2025 | Oct 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC-HDBP | High-Density Bike Parking | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Oct 2025 | Feb 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC-HDBP | High-Density Bike Parking | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Feb 2026 | Jun 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC-HDBP | High-Density Bike Parking | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jun 2026 | Oct 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC-HDBP | High-Density Bike Parking | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Oct 2026 | Jan 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC-HDBP | High-Density Bike Parking | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jan 2027 | Mar 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC-HDBP | High-Density Bike Parking | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Mar 2027 | Jul 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCRCWLK | Raised Crosswalks | 1 | DEVELOP SCOPE | Jun 2028 | Sep 2028 | Jun 2028 | Sep 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCRCWLK | Raised Crosswalks | 2 | PRELIMINARY DESIGN | Sep 2028 | Jan 2029 | Sep 2028 | Jan 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCRCWLK | Raised Crosswalks | 3 | FINAL DESIGN | Jan 2029 | Jul 2029 | Jan 2029 | Jul 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCRCWLK | Raised Crosswalks | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2029 | Oct 2029 | Jul 2029 | Oct 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCRCWLK | Raised Crosswalks | 5 | CONSTRUCTION TO 25% | Oct 2029 | Feb 2030 | Oct 2029 | Feb 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCRCWLK | Raised Crosswalks | 6 | CONSTRUCTION TO 50% | Feb 2030 | Jun 2030 | Feb 2030 | Jun 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCRCWLK | Raised Crosswalks | 7 | CONSTRUCTION TO 75% | Jun 2030 | Oct 2030 | Jun 2030 | Oct 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCRCWLK | Raised Crosswalks | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2030 | Jan 2031 | Oct 2030 | Jan 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCRCWLK | Raised Crosswalks | 9 | SUBSTANTIAL COMPLETION | Jan 2031 | Mar 2031 | Jan 2031 | Mar 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCRCWLK | Raised Crosswalks | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2031 | Apr 2031 | Mar 2031 | Apr 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCHCW | School Safety Citywide Contracts | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2024 | Sep 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCHCW | School Safety Citywide Contracts | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2024 | Jan 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCHCW | School Safety Citywide Contracts | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2025 | Jul 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCHCW | School Safety Citywide Contracts | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2025 | Oct 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCHCW | School Safety Citywide Contracts | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2025 | Feb 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCHCW | School Safety Citywide Contracts | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2026 | Jun 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCHCW | School Safety Citywide Contracts | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2026 | Oct 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCHCW | School Safety Citywide Contracts | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2026 | Jan 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCHCW | School Safety Citywide Contracts | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2027 | Mar 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCHCW | School Safety Citywide Contracts | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2028 | Mar 2027 | Apr 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCURB03 | CONSTRUCTION OF ROADWAY CURB LUMP SUM(SIM) | 1 | DEVELOP SCOPE | Jun 2008 | Oct 2008 | Jun 2023 | Oct 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCURB03 | CONSTRUCTION OF ROADWAY CURB LUMP SUM(SIM) | 2 | DESIGN START | Oct 2008 | Apr 2010 | Oct 2023 | Apr 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCURB03 | CONSTRUCTION OF ROADWAY CURB LUMP SUM(SIM) | 3 | CONSTRUCTION START | Apr 2010 | Apr 2012 | Apr 2025 | Apr 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCWREC | CITYWIDE RECONSTRUCTION OF STREETS | 1 | DEVELOP SCOPE | Jun 2010 | Sep 2010 | Jun 2022 | Sep 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCWREC | CITYWIDE RECONSTRUCTION OF STREETS | 2 | PRELIMINARY DESIGN | Sep 2010 | Jan 2011 | Sep 2022 | Jan 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCWREC | CITYWIDE RECONSTRUCTION OF STREETS | 3 | FINAL DESIGN | Jan 2011 | Jul 2011 | Jan 2023 | Jul 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCWREC | CITYWIDE RECONSTRUCTION OF STREETS | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2011 | Oct 2011 | Jul 2023 | Oct 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCWREC | CITYWIDE RECONSTRUCTION OF STREETS | 5 | CONSTRUCTION TO 25% | Oct 2011 | Feb 2012 | Oct 2023 | Feb 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCWREC | CITYWIDE RECONSTRUCTION OF STREETS | 6 | CONSTRUCTION TO 50% | Feb 2012 | Jun 2012 | Feb 2024 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCWREC | CITYWIDE RECONSTRUCTION OF STREETS | 7 | CONSTRUCTION TO 75% | Jun 2012 | Oct 2012 | Jun 2024 | Oct 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCWREC | CITYWIDE RECONSTRUCTION OF STREETS | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2012 | Jan 2013 | Oct 2024 | Jan 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCWREC | CITYWIDE RECONSTRUCTION OF STREETS | 9 | SUBSTANTIAL COMPLETION | Jan 2013 | Mar 2013 | Jan 2025 | Mar 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCWREC | CITYWIDE RECONSTRUCTION OF STREETS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2013 | Apr 2013 | Mar 2025 | Apr 2032
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-SOGR | Citywide Streets - 30-Year State of Good Repair | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jun 2023 | Sep 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-SOGR | Citywide Streets - 30-Year State of Good Repair | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Sep 2023 | Jan 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-SOGR | Citywide Streets - 30-Year State of Good Repair | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2024 | Jul 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-SOGR | Citywide Streets - 30-Year State of Good Repair | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2024 | Oct 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-SOGR | Citywide Streets - 30-Year State of Good Repair | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2024 | Feb 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-SOGR | Citywide Streets - 30-Year State of Good Repair | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2025 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-SOGR | Citywide Streets - 30-Year State of Good Repair | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2025 | Oct 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-SOGR | Citywide Streets - 30-Year State of Good Repair | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2025 | Jan 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-SOGR | Citywide Streets - 30-Year State of Good Repair | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2026 | Mar 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-SOGR | Citywide Streets - 30-Year State of Good Repair | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2026 | Jun 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23KQC | Non-Standard Ped Ramps - Brooklyn and Queens | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23KQC | Non-Standard Ped Ramps - Brooklyn and Queens | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23KQC | Non-Standard Ped Ramps - Brooklyn and Queens | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23KQC | Non-Standard Ped Ramps - Brooklyn and Queens | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23KQC | Non-Standard Ped Ramps - Brooklyn and Queens | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23KQC | Non-Standard Ped Ramps - Brooklyn and Queens | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23KQC | Non-Standard Ped Ramps - Brooklyn and Queens | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23KQC | Non-Standard Ped Ramps - Brooklyn and Queens | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23KQC | Non-Standard Ped Ramps - Brooklyn and Queens | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23KQC | Non-Standard Ped Ramps - Brooklyn and Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23KRC | Non-Standard Ped Ramps - Brooklyn and Staten Island | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23KRC | Non-Standard Ped Ramps - Brooklyn and Staten Island | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23KRC | Non-Standard Ped Ramps - Brooklyn and Staten Island | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23KRC | Non-Standard Ped Ramps - Brooklyn and Staten Island | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23KRC | Non-Standard Ped Ramps - Brooklyn and Staten Island | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23KRC | Non-Standard Ped Ramps - Brooklyn and Staten Island | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23KRC | Non-Standard Ped Ramps - Brooklyn and Staten Island | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23KRC | Non-Standard Ped Ramps - Brooklyn and Staten Island | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23KRC | Non-Standard Ped Ramps - Brooklyn and Staten Island | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23KRC | Non-Standard Ped Ramps - Brooklyn and Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MQC | Non-Standard Ped Ramps - Manhattan and Queens | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MQC | Non-Standard Ped Ramps - Manhattan and Queens | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MQC | Non-Standard Ped Ramps - Manhattan and Queens | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MQC | Non-Standard Ped Ramps - Manhattan and Queens | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MQC | Non-Standard Ped Ramps - Manhattan and Queens | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MQC | Non-Standard Ped Ramps - Manhattan and Queens | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MQC | Non-Standard Ped Ramps - Manhattan and Queens | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MQC | Non-Standard Ped Ramps - Manhattan and Queens | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MQC | Non-Standard Ped Ramps - Manhattan and Queens | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MQC | Non-Standard Ped Ramps - Manhattan and Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MXC | Non-Standard Ped Ramps - Manhattan and Bronx | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MXC | Non-Standard Ped Ramps - Manhattan and Bronx | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MXC | Non-Standard Ped Ramps - Manhattan and Bronx | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MXC | Non-Standard Ped Ramps - Manhattan and Bronx | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MXC | Non-Standard Ped Ramps - Manhattan and Bronx | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MXC | Non-Standard Ped Ramps - Manhattan and Bronx | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MXC | Non-Standard Ped Ramps - Manhattan and Bronx | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MXC | Non-Standard Ped Ramps - Manhattan and Bronx | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MXC | Non-Standard Ped Ramps - Manhattan and Bronx | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MXC | Non-Standard Ped Ramps - Manhattan and Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPL20006 | PRIOR NOTICE SIDEWALK(SIM) | 1 | DEVELOP SCOPE | Jun 2012 | Sep 2012 | Jun 2023 | Sep 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPL20006 | PRIOR NOTICE SIDEWALK(SIM) | 2 | PRELIMINARY DESIGN | Sep 2012 | Jan 2013 | Sep 2023 | Jan 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPL20006 | PRIOR NOTICE SIDEWALK(SIM) | 3 | FINAL DESIGN | Jan 2013 | Jul 2013 | Jan 2024 | Jul 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPL20006 | PRIOR NOTICE SIDEWALK(SIM) | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2013 | Oct 2013 | Jul 2024 | Oct 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPL20006 | PRIOR NOTICE SIDEWALK(SIM) | 5 | CONSTRUCTION TO 25% | Oct 2013 | Feb 2014 | Oct 2024 | Feb 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPL20006 | PRIOR NOTICE SIDEWALK(SIM) | 6 | CONSTRUCTION TO 50% | Feb 2014 | Jun 2014 | Feb 2025 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPL20006 | PRIOR NOTICE SIDEWALK(SIM) | 7 | CONSTRUCTION TO 75% | Jun 2014 | Oct 2014 | Jun 2025 | Oct 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPL20006 | PRIOR NOTICE SIDEWALK(SIM) | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2014 | Jan 2015 | Oct 2025 | Jan 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPL20006 | PRIOR NOTICE SIDEWALK(SIM) | 9 | SUBSTANTIAL COMPLETION | Jan 2015 | Mar 2015 | Jan 2026 | Mar 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPL20006 | PRIOR NOTICE SIDEWALK(SIM) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Apr 2015 | Mar 2026 | Apr 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ015Q | Ozone Park Plaza | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Aug 2025 | Feb 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ015Q | Ozone Park Plaza | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Feb 2029 | Jun 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ015Q | Ozone Park Plaza | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Jun 2029 | Dec 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ015Q | Ozone Park Plaza | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Dec 2029 | Mar 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ015Q | Ozone Park Plaza | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Mar 2030 | Jul 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ015Q | Ozone Park Plaza | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Jul 2030 | Nov 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ015Q | Ozone Park Plaza | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Nov 2030 | Mar 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ015Q | Ozone Park Plaza | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | Mar 2021 | Jun 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ015Q | Ozone Park Plaza | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Jun 2023 | Aug 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ015Q | Ozone Park Plaza | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Aug 2025 | Sep 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24KQ | Simple Upgrades Ped Ramps- Brooklyn & Queens | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2024 | Sep 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24KQ | Simple Upgrades Ped Ramps- Brooklyn & Queens | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2024 | Jan 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24KQ | Simple Upgrades Ped Ramps- Brooklyn & Queens | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2025 | Jul 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24KQ | Simple Upgrades Ped Ramps- Brooklyn & Queens | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2025 | Oct 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24KQ | Simple Upgrades Ped Ramps- Brooklyn & Queens | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2025 | Feb 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24KQ | Simple Upgrades Ped Ramps- Brooklyn & Queens | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2026 | Jun 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24KQ | Simple Upgrades Ped Ramps- Brooklyn & Queens | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2026 | Oct 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24KQ | Simple Upgrades Ped Ramps- Brooklyn & Queens | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2026 | Jan 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24KQ | Simple Upgrades Ped Ramps- Brooklyn & Queens | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2027 | Mar 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24KQ | Simple Upgrades Ped Ramps- Brooklyn & Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2027 | Apr 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24KR | Simple Upgrades Ped Ramps- Brooklyn and Staten Island | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2024 | Sep 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24KR | Simple Upgrades Ped Ramps- Brooklyn and Staten Island | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2024 | Jan 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24KR | Simple Upgrades Ped Ramps- Brooklyn and Staten Island | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2025 | Jul 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24KR | Simple Upgrades Ped Ramps- Brooklyn and Staten Island | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2025 | Oct 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24KR | Simple Upgrades Ped Ramps- Brooklyn and Staten Island | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2025 | Feb 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24KR | Simple Upgrades Ped Ramps- Brooklyn and Staten Island | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2026 | Jun 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24KR | Simple Upgrades Ped Ramps- Brooklyn and Staten Island | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2026 | Oct 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24KR | Simple Upgrades Ped Ramps- Brooklyn and Staten Island | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2026 | Jan 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24KR | Simple Upgrades Ped Ramps- Brooklyn and Staten Island | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2027 | Mar 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24KR | Simple Upgrades Ped Ramps- Brooklyn and Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2027 | Apr 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24MQ | Simple Upgrades Ped Ramps- Manhattan and Queens | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24MQ | Simple Upgrades Ped Ramps- Manhattan and Queens | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24MQ | Simple Upgrades Ped Ramps- Manhattan and Queens | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24MQ | Simple Upgrades Ped Ramps- Manhattan and Queens | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24MQ | Simple Upgrades Ped Ramps- Manhattan and Queens | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24MQ | Simple Upgrades Ped Ramps- Manhattan and Queens | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24MQ | Simple Upgrades Ped Ramps- Manhattan and Queens | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24MQ | Simple Upgrades Ped Ramps- Manhattan and Queens | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24MQ | Simple Upgrades Ped Ramps- Manhattan and Queens | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24MQ | Simple Upgrades Ped Ramps- Manhattan and Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24QX | Simple Upgrades Ped Ramps - Queens and Bronx | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2024 | Sep 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24QX | Simple Upgrades Ped Ramps - Queens and Bronx | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2024 | Jan 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24QX | Simple Upgrades Ped Ramps - Queens and Bronx | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2025 | Jul 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24QX | Simple Upgrades Ped Ramps - Queens and Bronx | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2025 | Oct 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24QX | Simple Upgrades Ped Ramps - Queens and Bronx | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2025 | Feb 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24QX | Simple Upgrades Ped Ramps - Queens and Bronx | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2026 | Jun 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24QX | Simple Upgrades Ped Ramps - Queens and Bronx | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2026 | Oct 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24QX | Simple Upgrades Ped Ramps - Queens and Bronx | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2026 | Jan 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24QX | Simple Upgrades Ped Ramps - Queens and Bronx | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2027 | Mar 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24QX | Simple Upgrades Ped Ramps - Queens and Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2027 | Apr 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRINSTL | Pedestrian Ramps Installation - Lump Sum | 1 | DEVELOP SCOPE | Jun 2025 | Sep 2025 | Jun 2020 | Sep 2020
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRINSTL | Pedestrian Ramps Installation - Lump Sum | 2 | PRELIMINARY DESIGN | Sep 2025 | Jan 2026 | Sep 2020 | Jan 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRINSTL | Pedestrian Ramps Installation - Lump Sum | 3 | FINAL DESIGN | Jan 2026 | Jul 2026 | Jan 2021 | Jul 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRINSTL | Pedestrian Ramps Installation - Lump Sum | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2026 | Oct 2026 | Jul 2021 | Oct 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRINSTL | Pedestrian Ramps Installation - Lump Sum | 5 | CONSTRUCTION TO 25% | Oct 2026 | Feb 2027 | Oct 2021 | Feb 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRINSTL | Pedestrian Ramps Installation - Lump Sum | 6 | CONSTRUCTION TO 50% | Feb 2027 | Jun 2027 | Feb 2022 | Jun 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRINSTL | Pedestrian Ramps Installation - Lump Sum | 7 | CONSTRUCTION TO 75% | Jun 2027 | Oct 2027 | Jun 2022 | Oct 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRINSTL | Pedestrian Ramps Installation - Lump Sum | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jan 2028 | Oct 2024 | Jan 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRINSTL | Pedestrian Ramps Installation - Lump Sum | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Mar 2028 | Jan 2025 | Mar 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRINSTL | Pedestrian Ramps Installation - Lump Sum | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2028 | Apr 2028 | Mar 2025 | Apr 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRREHAB | Pedestrian Ramps Rehabilitation - Lump Sum | 1 | DEVELOP SCOPE | Jun 2025 | Sep 2025 | Jun 2020 | Sep 2020
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRREHAB | Pedestrian Ramps Rehabilitation - Lump Sum | 2 | PRELIMINARY DESIGN | Sep 2025 | Jan 2026 | Sep 2020 | Jan 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRREHAB | Pedestrian Ramps Rehabilitation - Lump Sum | 3 | FINAL DESIGN | Jan 2026 | Jul 2026 | Jan 2021 | Jul 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRREHAB | Pedestrian Ramps Rehabilitation - Lump Sum | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2026 | Oct 2026 | Jul 2020 | Oct 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRREHAB | Pedestrian Ramps Rehabilitation - Lump Sum | 5 | CONSTRUCTION TO 25% | Oct 2026 | Feb 2027 | Oct 2026 | Feb 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRREHAB | Pedestrian Ramps Rehabilitation - Lump Sum | 6 | CONSTRUCTION TO 50% | Feb 2027 | Jun 2027 | Feb 2027 | Jun 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRREHAB | Pedestrian Ramps Rehabilitation - Lump Sum | 7 | CONSTRUCTION TO 75% | Jun 2027 | Oct 2027 | Jun 2027 | Oct 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRREHAB | Pedestrian Ramps Rehabilitation - Lump Sum | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jan 2028 | Oct 2021 | Jan 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRREHAB | Pedestrian Ramps Rehabilitation - Lump Sum | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Mar 2028 | Jan 2022 | Mar 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRREHAB | Pedestrian Ramps Rehabilitation - Lump Sum | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2028 | Apr 2028 | Mar 2022 | Feb 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWRAP07 | RAP HAULING | 1 | DEVELOP SCOPE | Jun 2012 | Sep 2012 | Jun 2023 | Sep 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWRAP07 | RAP HAULING | 2 | PRELIMINARY DESIGN | Sep 2012 | Jan 2013 | Sep 2023 | Jan 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWRAP07 | RAP HAULING | 3 | FINAL DESIGN | Jan 2013 | Jul 2013 | Jan 2024 | Jul 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWRAP07 | RAP HAULING | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2013 | Oct 2013 | Jul 2024 | Oct 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWRAP07 | RAP HAULING | 5 | CONSTRUCTION TO 25% | Oct 2013 | Feb 2014 | Oct 2024 | Feb 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWRAP07 | RAP HAULING | 6 | CONSTRUCTION TO 50% | Feb 2014 | Jun 2014 | Feb 2025 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWRAP07 | RAP HAULING | 7 | CONSTRUCTION TO 75% | Jun 2014 | Oct 2014 | Jun 2025 | Oct 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWRAP07 | RAP HAULING | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2014 | Jan 2015 | Oct 2025 | Jan 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWRAP07 | RAP HAULING | 9 | SUBSTANTIAL COMPLETION | Jan 2015 | Mar 2015 | Jan 2026 | Mar 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWRAP07 | RAP HAULING | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Apr 2015 | Mar 2026 | Apr 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWSAFTR | Safe Routes to Transit | 1 | DEVELOP SCOPE | Jun 2008 | Oct 2008 | Jul 2013 | Oct 2013
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWSAFTR | Safe Routes to Transit | 2 | DESIGN START | Oct 2008 | Apr 2010 | Oct 2013 | Apr 2015
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWSAFTR | Safe Routes to Transit | 3 | CONSTRUCTION START | Apr 2010 | Apr 2012 | Apr 2015 | Jun 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWSTEP04 | STEP STREET REHABILITATION | 1 | DEVELOP SCOPE | May 2003 | Aug 2003 | May 2024 | Aug 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWSTEP04 | STEP STREET REHABILITATION | 2 | PRELIMINARY DESIGN | Aug 2003 | Dec 2003 | Aug 2024 | Dec 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWSTEP04 | STEP STREET REHABILITATION | 3 | FINAL DESIGN | Dec 2003 | Jun 2004 | Dec 2024 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWSTEP04 | STEP STREET REHABILITATION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2004 | Sep 2004 | Jun 2025 | Sep 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWSTEP04 | STEP STREET REHABILITATION | 5 | CONSTRUCTION TO 25% | Sep 2004 | Jan 2005 | Sep 2025 | Jan 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWSTEP04 | STEP STREET REHABILITATION | 6 | CONSTRUCTION TO 50% | Jan 2005 | May 2005 | Jan 2026 | May 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWSTEP04 | STEP STREET REHABILITATION | 7 | CONSTRUCTION TO 75% | May 2005 | Sep 2005 | May 2026 | Sep 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWSTEP04 | STEP STREET REHABILITATION | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2005 | Dec 2005 | Sep 2026 | Dec 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWSTEP04 | STEP STREET REHABILITATION | 9 | SUBSTANTIAL COMPLETION | Dec 2005 | Feb 2006 | Dec 2026 | Feb 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWSTEP04 | STEP STREET REHABILITATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2006 | Mar 2006 | Feb 2027 | Jul 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWTSQI | Public Plaza Improvements | 1 | DEVELOP SCOPE | Jun 2008 | Oct 2008 | Jul 1997 | Oct 1997
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWTSQI | Public Plaza Improvements | 2 | DESIGN START | Oct 2008 | Apr 2010 | Oct 1997 | Apr 1999
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWTSQI | Public Plaza Improvements | 3 | CONSTRUCTION START | Apr 2010 | Apr 2012 | Apr 2025 | Jul 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | ITSBELTPK | Intelligent Transportation Systems on Belt Parkway X501.62 | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Jun 2020 | Jun 2020 | Jun 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | ITSBELTPK | Intelligent Transportation Systems on Belt Parkway X501.62 | 2 | CONSTRUCTION START | Jul 2020 | Aug 2020 | Jul 2025 | Aug 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | ITSBELTPK | Intelligent Transportation Systems on Belt Parkway X501.62 | 3 | CONSTRUCTION COMPLETION | Aug 2020 | Mar 2022 | Aug 2025 | Mar 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | ITSJACKPK | Intelligent Transportation System Jackie Robinson Pk X501.60 | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Jun 2021 | Jun 2023 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | ITSJACKPK | Intelligent Transportation System Jackie Robinson Pk X501.60 | 2 | CONSTRUCTION START | Jul 2021 | Aug 2021 | Jul 2023 | Aug 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | ITSJACKPK | Intelligent Transportation System Jackie Robinson Pk X501.60 | 3 | CONSTRUCTION COMPLETION | Aug 2021 | Mar 2023 | Aug 2023 | Mar 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | MOLHYBRID | Molinari Class conversion to Inte Hybrid Diesel Electric | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2025 | Jun 2029 | Jun 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | MOLHYBRID | Molinari Class conversion to Inte Hybrid Diesel Electric | 2 | DESIGN START | Jun 2025 | Jun 2027 | Jun 2030 | Jun 2032
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | MOLHYBRID | Molinari Class conversion to Inte Hybrid Diesel Electric | 3 | CONSTRUCTION START | Jun 2027 | Jun 2028 | Jun 2032 | Jun 2033
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | MOLRETROF | MOLINARI CLASS UPGRADES-RETRO FIT | 1 | DEVELOP SCOPE | Jun 2015 | Jun 2016 | Jun 2022 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | MOLRETROF | MOLINARI CLASS UPGRADES-RETRO FIT | 2 | DESIGN START | Jun 2016 | Jun 2018 | Jun 2024 | Jun 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | MOLRETROF | MOLINARI CLASS UPGRADES-RETRO FIT | 3 | CONSTRUCTION START | Jun 2018 | Jun 2020 | Jun 2026 | Jun 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | NYCWINRPL | NYCWIN Replacement | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Jun 2018 | Aug 2021 | Aug 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | NYCWINRPL | NYCWIN Replacement | 2 | CONSTRUCTION START | Jul 2018 | Aug 2018 | Oct 2022 | Oct 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | NYCWINRPL | NYCWIN Replacement | 3 | CONSTRUCTION COMPLETION | Aug 2018 | Mar 2020 | Jun 2024 | Jul 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | PLANTRANS | TRANSIT SIGNAL PRIORITY-2030 | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2008 | Jun 2008 | Jun 2029 | Jun 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | PLANTRANS | TRANSIT SIGNAL PRIORITY-2030 | 2 | CONSTRUCTION START | Jul 2008 | Aug 2008 | Jul 2029 | Aug 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | PLANTRANS | TRANSIT SIGNAL PRIORITY-2030 | 3 | CONSTRUCTION COMPLETION | Aug 2008 | Mar 2010 | Aug 2029 | Mar 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | REALTIMPS | Real Time Passenger Information System, CW - Streets Plan | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Jun 2023 | Jun 2026 | Jun 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | REALTIMPS | Real Time Passenger Information System, CW - Streets Plan | 2 | CONSTRUCTION START | Jul 2023 | Aug 2023 | Jul 2026 | Aug 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | REALTIMPS | Real Time Passenger Information System, CW - Streets Plan | 3 | CONSTRUCTION COMPLETION | Aug 2023 | Mar 2025 | Aug 2026 | Mar 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | RTPIFY19 | REAL TIME PASSENGER INFO SIGNS - FY19 | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Jun 2018 | Jun 2019 | Jul 2019
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | RTPIFY19 | REAL TIME PASSENGER INFO SIGNS - FY19 | 2 | CONSTRUCTION START | Jul 2018 | Aug 2018 | Jun 2020 | Jul 2020
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | RTPIFY19 | REAL TIME PASSENGER INFO SIGNS - FY19 | 3 | CONSTRUCTION COMPLETION | Aug 2018 | Mar 2020 | Jun 2021 | Jul 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | RTPIFY20 | Real Time Passenger Info Signs FY20ADOP | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Jun 2019 | Jun 2023 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | RTPIFY20 | Real Time Passenger Info Signs FY20ADOP | 2 | CONSTRUCTION START | Jul 2019 | Aug 2019 | Jul 2023 | Aug 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | RTPIFY20 | Real Time Passenger Info Signs FY20ADOP | 3 | CONSTRUCTION COMPLETION | Aug 2019 | Mar 2021 | Aug 2023 | Mar 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDCONDU | SANDY CONDUIT ADDITIONAL CITY-WIDE WORK | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2015 | Jun 2015
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDCONDU | SANDY CONDUIT ADDITIONAL CITY-WIDE WORK | 2 | CONSTRUCTION START | Jul 2015 | Aug 2015 |  | Aug 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDCONDU | SANDY CONDUIT ADDITIONAL CITY-WIDE WORK | 3 | CONSTRUCTION COMPLETION | Aug 2015 | Mar 2017 | Jan 2027 | Aug 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF05 | Construction of New Ferryboats | 1 | DEVELOP SCOPE | Jul 2016 | Sep 2016 | May 2011 | Jul 2014
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF05 | Construction of New Ferryboats | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Oct 2014 | Feb 2015
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF05 | Construction of New Ferryboats | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Aug 2015 | Nov 2015
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF05 | Construction of New Ferryboats | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | May 2016 | Feb 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF05 | Construction of New Ferryboats | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Mar 2017 | Jan 2018
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF05 | Construction of New Ferryboats | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Jan 2018 | Feb 2019
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF05 | Construction of New Ferryboats | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Feb 2019 | Jan 2020
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF05 | Construction of New Ferryboats | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | Jan 2020 | Apr 2020
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF05 | Construction of New Ferryboats | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Aug 2021 | Aug 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF05 | Construction of New Ferryboats | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Feb 2025 | Feb 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF07 | STATEN ISLAND FERRY HEAVY WEATHER MOORING | 1 | DEVELOP SCOPE | Jun 2017 | Jun 2018 | Jun 2025 | Jun 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF07 | STATEN ISLAND FERRY HEAVY WEATHER MOORING | 2 | DESIGN START | Jun 2018 | Jun 2020 | Jun 2027 | Jun 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF07 | STATEN ISLAND FERRY HEAVY WEATHER MOORING | 3 | CONSTRUCTION START | Jun 2020 | Jun 2022 | Jun 2029 | Jun 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF11 | Ferry Terminal Floodproofing | 1 | DEVELOP SCOPE | Jul 2016 | Sep 2016 | Nov 2023 | May 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF11 | Ferry Terminal Floodproofing | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | May 2025 | Sep 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF11 | Ferry Terminal Floodproofing | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Sep 2025 | Feb 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF11 | Ferry Terminal Floodproofing | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Mar 2026 | May 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF11 | Ferry Terminal Floodproofing | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | May 2026 | Sep 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF11 | Ferry Terminal Floodproofing | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Sep 2026 | Jan 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF11 | Ferry Terminal Floodproofing | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Jan 2027 | May 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF11 | Ferry Terminal Floodproofing | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | May 2027 | Aug 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF11 | Ferry Terminal Floodproofing | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Aug 2027 | Oct 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF11 | Ferry Terminal Floodproofing | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Oct 2027 | Nov 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SEQUEENS | South East Queens Initiative | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2026 | Sep 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SEQUEENS | South East Queens Initiative | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2026 | Jan 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SEQUEENS | South East Queens Initiative | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2027 | Jul 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SEQUEENS | South East Queens Initiative | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2027 | Oct 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SEQUEENS | South East Queens Initiative | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2027 | Feb 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SEQUEENS | South East Queens Initiative | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2028 | Jun 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SEQUEENS | South East Queens Initiative | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2028 | Oct 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SEQUEENS | South East Queens Initiative | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2028 | Jan 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SEQUEENS | South East Queens Initiative | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2029 | Mar 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SEQUEENS | South East Queens Initiative | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2029 | Jun 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SIGNALSF3 | Traffic Signals Safety, Citywide | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Jun 2021 | Jun 2023 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SIGNALSF3 | Traffic Signals Safety, Citywide | 2 | CONSTRUCTION START | Jul 2021 | Aug 2021 | Jul 2023 | Aug 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SIGNALSF3 | Traffic Signals Safety, Citywide | 3 | CONSTRUCTION COMPLETION | Aug 2021 | Mar 2023 | Aug 2023 | Mar 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SIGNALSVZ | Signalized Intersection Improvements-Vision Zero | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Jun 2023 | Jun 2023 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SIGNALSVZ | Signalized Intersection Improvements-Vision Zero | 2 | CONSTRUCTION START | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SIGNALSVZ | Signalized Intersection Improvements-Vision Zero | 3 | CONSTRUCTION COMPLETION | Aug 2023 | Mar 2025 | Aug 2023 | Mar 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | STEFFSCMV | NYC Street Efficiency Strategic Commercial Vehicle Monitorin | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Jun 2019 | Mar 2026 | Mar 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | STEFFSCMV | NYC Street Efficiency Strategic Commercial Vehicle Monitorin | 2 | CONSTRUCTION START | Jul 2019 | Aug 2019 | Mar 2026 | Apr 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | STEFFSCMV | NYC Street Efficiency Strategic Commercial Vehicle Monitorin | 3 | CONSTRUCTION COMPLETION | Aug 2019 | Mar 2021 | Apr 2026 | Nov 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF012019 | NEW SIGNALS INSTALLATION REQUIREMENT 2019 | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Jun 2018 | Jun 2027 | Jun 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF012019 | NEW SIGNALS INSTALLATION REQUIREMENT 2019 | 2 | CONSTRUCTION START | Jul 2018 | Aug 2018 | Jul 2027 | Aug 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF012019 | NEW SIGNALS INSTALLATION REQUIREMENT 2019 | 3 | CONSTRUCTION COMPLETION | Aug 2018 | Mar 2020 | Aug 2027 | Mar 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF012023 | New Signals Installation requirement, citywide FY23 | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Jun 2022 | Jun 2023 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF012023 | New Signals Installation requirement, citywide FY23 | 2 | CONSTRUCTION START | Jul 2022 | Aug 2022 | Jul 2023 | Aug 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF012023 | New Signals Installation requirement, citywide FY23 | 3 | CONSTRUCTION COMPLETION | Aug 2022 | Mar 2024 | Aug 2023 | Mar 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01-9910 | LOCAL STREET NETWORK MGMT AND INCIDENT MGMT X500.94 | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2004 | Jun 2004 | Jun 2024 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01-9910 | LOCAL STREET NETWORK MGMT AND INCIDENT MGMT X500.94 | 2 | CONSTRUCTION START | Jun 2004 | Jul 2004 | Jun 2024 | Jul 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01-9910 | LOCAL STREET NETWORK MGMT AND INCIDENT MGMT X500.94 | 3 | CONSTRUCTION COMPLETION | Jul 2004 | Feb 2006 | Jul 2024 | Feb 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01-9911 | Advance Travel Information System Upgrade | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Jun 2022 | Jun 2023 | Jul 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01-9911 | Advance Travel Information System Upgrade | 2 | CONSTRUCTION START | Jul 2022 | Aug 2022 | Jul 2023 | Sep 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01-9911 | Advance Travel Information System Upgrade | 3 | CONSTRUCTION COMPLETION | Aug 2022 | Mar 2024 | Sep 2023 | Apr 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01APS | Accessible Pedestrian Signals, citywide - TEN YEARS | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Jun 2019 | Jun 2025 | Jun 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01APS | Accessible Pedestrian Signals, citywide - TEN YEARS | 2 | CONSTRUCTION START | Jul 2019 | Aug 2019 | Jul 2025 | Aug 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01APS | Accessible Pedestrian Signals, citywide - TEN YEARS | 3 | CONSTRUCTION COMPLETION | Aug 2019 | Mar 2021 | Aug 2025 | Mar 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01TPM21 | Thermoplastic Marking-FY21 | 1 | BID AWARD AND REGISTER CONTRCT | Mar 2022 | Mar 2022 | Mar 2023 | Mar 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01TPM21 | Thermoplastic Marking-FY21 | 2 | CONSTRUCTION START | Mar 2022 | May 2022 | Mar 2029 | May 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01TPM21 | Thermoplastic Marking-FY21 | 3 | CONSTRUCTION COMPLETION | May 2022 | Jun 2023 | May 2029 | Jun 2030
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01TPM23 | Thermoplastic Marking Citywide-FY23 | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2027 | Jun 2027 | Jun 2027 | Jun 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01TPM23 | Thermoplastic Marking Citywide-FY23 | 2 | CONSTRUCTION START | Jul 2027 | Aug 2027 | Jul 2027 | Aug 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01TPM23 | Thermoplastic Marking Citywide-FY23 | 3 | CONSTRUCTION COMPLETION | Aug 2027 | Mar 2029 | Aug 2027 | Mar 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01VARMS | Variable Message Signs Replacement, Citywide | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Jun 2020 | Jun 2024 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01VARMS | Variable Message Signs Replacement, Citywide | 2 | CONSTRUCTION START | Jul 2020 | Aug 2020 | Jul 2024 | Aug 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01VARMS | Variable Message Signs Replacement, Citywide | 3 | CONSTRUCTION COMPLETION | Aug 2020 | Mar 2022 | Aug 2024 | Mar 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF18-LUMP | LUMP SUM FOR PARKING RECONSTRUCTION | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2008 | Jun 2008 | Jun 2021 | Jun 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF18-LUMP | LUMP SUM FOR PARKING RECONSTRUCTION | 2 | CONSTRUCTION START | Jul 2008 | Aug 2008 | Jul 2021 | Aug 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF18-LUMP | LUMP SUM FOR PARKING RECONSTRUCTION | 3 | CONSTRUCTION COMPLETION | Aug 2008 | Mar 2010 | Aug 2021 | Mar 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFAPEDSY4 | Accessible Pedestrian Signals | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Jun 2022 | Jun 2031 | Jul 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFAPEDSY4 | Accessible Pedestrian Signals | 2 | CONSTRUCTION START | Jul 2022 | Aug 2022 | Jun 2032 | Jul 2032
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFAPEDSY4 | Accessible Pedestrian Signals | 3 | CONSTRUCTION COMPLETION | Aug 2022 | Mar 2024 | Aug 2032 | Mar 2033
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFCORRBAS | Replacement of Corroded Street light and Signal Poles | 1 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Feb 2020 | Feb 2031 | Feb 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFCORRBAS | Replacement of Corroded Street light and Signal Poles | 2 | CONSTRUCTION START | Feb 2020 | Apr 2020 | Feb 2031 | Apr 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFCORRBAS | Replacement of Corroded Street light and Signal Poles | 3 | CONSTRUCTION COMPLETION | Apr 2020 | Apr 2022 | Apr 2031 | Apr 2033
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFCWSBST | SBS-Citywide Real Time Totem System | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2017 | Sep 2017
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFCWSBST | SBS-Citywide Real Time Totem System | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2017 | Jan 2018
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFCWSBST | SBS-Citywide Real Time Totem System | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jan 2018 | Jul 2018
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFCWSBST | SBS-Citywide Real Time Totem System | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2018 | Oct 2018
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFCWSBST | SBS-Citywide Real Time Totem System | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFCWSBST | SBS-Citywide Real Time Totem System | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFCWSBST | SBS-Citywide Real Time Totem System | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jun 2019 | Oct 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFCWSBST | SBS-Citywide Real Time Totem System | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Oct 2025 | Jan 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFCWSBST | SBS-Citywide Real Time Totem System | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jan 2026 | Mar 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFCWSBST | SBS-Citywide Real Time Totem System | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2022 | Mar 2026 | Apr 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFITSAMS | INTELLIGENT TRANSPORTATION SYSTEM(ITS) ON HIGHWAYS | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2009 | Jun 2009 | Jun 2027 | Jul 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFITSAMS | INTELLIGENT TRANSPORTATION SYSTEM(ITS) ON HIGHWAYS | 2 | CONSTRUCTION START | Jul 2009 | Aug 2009 | Jul 2025 | Aug 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFITSAMS | INTELLIGENT TRANSPORTATION SYSTEM(ITS) ON HIGHWAYS | 3 | CONSTRUCTION COMPLETION | Aug 2009 | Mar 2011 | Aug 2027 | Mar 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFLGUDECK | Lighting at underdeck Structure, citywide | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Jun 2020 | Jun 2024 | Jun 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFLGUDECK | Lighting at underdeck Structure, citywide | 2 | CONSTRUCTION START | Jul 2020 | Aug 2020 | Jul 2024 | Aug 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFLGUDECK | Lighting at underdeck Structure, citywide | 3 | CONSTRUCTION COMPLETION | Aug 2020 | Mar 2022 | Aug 2024 | Mar 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFLGUSBWY | Furnish and Install Lighting under elevated structures | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Jun 2020 | Oct 2021 | Dec 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFLGUSBWY | Furnish and Install Lighting under elevated structures | 2 | CONSTRUCTION START | Jul 2020 | Aug 2020 | Dec 2021 | Jan 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFLGUSBWY | Furnish and Install Lighting under elevated structures | 3 | CONSTRUCTION COMPLETION | Aug 2020 | Mar 2022 | Jan 2022 | Aug 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFLTURNSG | Installation of Left Turn Signals, Citywde | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Jun 2023 | Jun 2023 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFLTURNSG | Installation of Left Turn Signals, Citywde | 2 | CONSTRUCTION START | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFLTURNSG | Installation of Left Turn Signals, Citywde | 3 | CONSTRUCTION COMPLETION | Aug 2023 | Mar 2025 | Aug 2023 | Mar 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFLUMP | Traffic projects | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2016 | Jun 2016 | Jun 2019 | Jun 2019
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFLUMP | Traffic projects | 2 | CONSTRUCTION START | Jul 2016 | Aug 2016 | Jul 2019 | Aug 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFLUMP | Traffic projects | 3 | CONSTRUCTION COMPLETION | Aug 2016 | Mar 2018 | Aug 2025 | Mar 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFMARKLMP | THERMOPLASTIC MARKINGS-TEN YEARS | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2013 | Jun 2013 | Jun 2022 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFMARKLMP | THERMOPLASTIC MARKINGS-TEN YEARS | 2 | CONSTRUCTION START | Jul 2013 | Aug 2013 | Jul 2023 | Aug 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFMARKLMP | THERMOPLASTIC MARKINGS-TEN YEARS | 3 | CONSTRUCTION COMPLETION | Aug 2013 | Mar 2015 | Aug 2023 | Mar 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFPEDCDW3 | Furnish and install Pedestrian Countdown Clocks | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Jun 2020 | Aug 2025 | Jan 2026
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFPEDCDW3 | Furnish and install Pedestrian Countdown Clocks | 2 | CONSTRUCTION START | Jul 2020 | Aug 2020 | Mar 2020 | Apr 2020
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFPEDCDW3 | Furnish and install Pedestrian Countdown Clocks | 3 | CONSTRUCTION COMPLETION | Aug 2020 | Mar 2022 | Apr 2020 | Jun 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFSBIKEPK | Purchase and installation of Secure Bike Parking | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Jun 2023 | Jun 2023 | Jun 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFSBIKEPK | Purchase and installation of Secure Bike Parking | 2 | CONSTRUCTION START | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFSBIKEPK | Purchase and installation of Secure Bike Parking | 3 | CONSTRUCTION COMPLETION | Aug 2023 | Mar 2025 | Aug 2023 | Mar 2025
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFSPDCAM | Purchase and Install Speed Cameras in School Zones Areas | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2014 | Jun 2014 | Jun 2031 | Jun 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFSPDCAM | Purchase and Install Speed Cameras in School Zones Areas | 2 | CONSTRUCTION START | Jun 2014 | Jul 2014 | Jun 2031 | Jul 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFSPDCAM | Purchase and Install Speed Cameras in School Zones Areas | 3 | CONSTRUCTION COMPLETION | Jul 2014 | Feb 2016 | Jul 2031 | Feb 2033
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFVISIONZ | Traffic Vision Zero projects-St Light Enhancement | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2016 | Jun 2016 | Jun 2021 | Jun 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFVISIONZ | Traffic Vision Zero projects-St Light Enhancement | 2 | CONSTRUCTION START | Jul 2016 | Aug 2016 | Jul 2021 | Aug 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFVISIONZ | Traffic Vision Zero projects-St Light Enhancement | 3 | CONSTRUCTION COMPLETION | Aug 2016 | Mar 2018 | Aug 2021 | Mar 2029
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TRNCHREST | Trench Restoration | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2020 | Sep 2020
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TRNCHREST | Trench Restoration | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2020 | Jan 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TRNCHREST | Trench Restoration | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jan 2021 | Jul 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TRNCHREST | Trench Restoration | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2021 | Oct 2021
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TRNCHREST | Trench Restoration | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Oct 2021 | Feb 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TRNCHREST | Trench Restoration | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Feb 2022 | Jun 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TRNCHREST | Trench Restoration | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jun 2022 | Oct 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TRNCHREST | Trench Restoration | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Oct 2022 | Jan 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TRNCHREST | Trench Restoration | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jan 2023 | Mar 2023
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TRNCHREST | Trench Restoration | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Mar 2023 | Apr 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TYPLILL | STREET LIGHTING <TEN YEAR PLAN) | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2015 | Jun 2015 | Jun 2031 | Jun 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TYPLILL | STREET LIGHTING <TEN YEAR PLAN) | 2 | CONSTRUCTION START | Jun 2015 | Jul 2015 | Jun 2031 | Jul 2031
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TYPLILL | STREET LIGHTING <TEN YEAR PLAN) | 3 | CONSTRUCTION COMPLETION | Jul 2015 | Feb 2017 | Jul 2031 | Feb 2033
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TYPLREP | TRAFFIC PARK & HIGHWAY DISTRIBUTION(TEN YEAR PLAN) | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Jun 2019 | Jun 2022 | Jun 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TYPLREP | TRAFFIC PARK & HIGHWAY DISTRIBUTION(TEN YEAR PLAN) | 2 | CONSTRUCTION START | Jun 2019 | Jul 2019 | Jun 2022 | Jul 2022
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TYPLREP | TRAFFIC PARK & HIGHWAY DISTRIBUTION(TEN YEAR PLAN) | 3 | CONSTRUCTION COMPLETION | Jul 2019 | Feb 2021 | Jul 2022 | Feb 2024
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TYPLSGM | TRAFFIC SIGNALS (TEN YEAR PLAN) | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2015 | Jun 2015 | Jun 2025 | Jun 2027
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TYPLSGM | TRAFFIC SIGNALS (TEN YEAR PLAN) | 2 | CONSTRUCTION START | Jun 2015 | Jul 2015 | Jun 2027 | Jul 2028
20231026 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TYPLSGM | TRAFFIC SIGNALS (TEN YEAR PLAN) | 3 | CONSTRUCTION COMPLETION | Jul 2015 | Feb 2017 | Jul 2028 | Feb 2031
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR403 | DPR efficient lighting @various facilities 5bor CNYG-2415MA1 | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2018 | Dec 2018
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR403 | DPR efficient lighting @various facilities 5bor CNYG-2415MA1 | 2 | DESIGN | Dec 2016 | Jun 2018 | Dec 2016 | Jun 2018
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR403 | DPR efficient lighting @various facilities 5bor CNYG-2415MA1 | 3 | BID/ REGISTER CONTRACT | Jun 2018 | Mar 2019 | Jun 2018 | Mar 2019
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR403 | DPR efficient lighting @various facilities 5bor CNYG-2415MA1 | 4 | CONSTRUCTION | Mar 2019 | Sep 2020 | Mar 2019 | Sep 2020
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR403 | DPR efficient lighting @various facilities 5bor CNYG-2415MA1 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2033
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR405 | DPR efficient lighting @ ballfields MN, BK & BX CNYG-2915 | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Apr 2018 | Jul 2018
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR405 | DPR efficient lighting @ ballfields MN, BK & BX CNYG-2915 | 2 | DESIGN | Sep 2015 | Dec 2015 | Jul 2018 | Sep 2018
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR405 | DPR efficient lighting @ ballfields MN, BK & BX CNYG-2915 | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Oct 2018 | Dec 2018
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR405 | DPR efficient lighting @ ballfields MN, BK & BX CNYG-2915 | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Dec 2018 | Dec 2019
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR405 | DPR efficient lighting @ ballfields MN, BK & BX CNYG-2915 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Dec 2019 | Jun 2033
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | GXBXBKQ1 | GI Citywide-Bioswales in Parks Bronx, Queens & Brooklyn | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | GXBXBKQ1 | GI Citywide-Bioswales in Parks Bronx, Queens & Brooklyn | 2 | DESIGN | Dec 2017 | Jun 2019 | Dec 2017 | Jun 2019
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | GXBXBKQ1 | GI Citywide-Bioswales in Parks Bronx, Queens & Brooklyn | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Mar 2020 | Jun 2019 | Mar 2020
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | GXBXBKQ1 | GI Citywide-Bioswales in Parks Bronx, Queens & Brooklyn | 4 | CONSTRUCTION | Mar 2020 | Mar 2021 | Mar 2020 | Mar 2021
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | GXBXBKQ1 | GI Citywide-Bioswales in Parks Bronx, Queens & Brooklyn | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Mar 2023 | Mar 2021 | Jun 2029
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-0PRC23A | Citywide Grow Bag, Field Grown Tree Proc. Region 2 FY23 | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-0PRC23A | Citywide Grow Bag, Field Grown Tree Proc. Region 2 FY23 | 2 | DESIGN | Sep 2023 | Mar 2024 | Sep 2023 | Mar 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-0PRC23A | Citywide Grow Bag, Field Grown Tree Proc. Region 2 FY23 | 3 | BID/ REGISTER CONTRACT | Mar 2024 | Sep 2024 | Mar 2024 | Sep 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-0PRC23A | Citywide Grow Bag, Field Grown Tree Proc. Region 2 FY23 | 4 | CONSTRUCTION | Sep 2024 | Sep 2033 | Sep 2024 | Sep 2033
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-0PRC23A | Citywide Grow Bag, Field Grown Tree Proc. Region 2 FY23 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2033 | Nov 2033 | Sep 2033 | Nov 2033
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-0PRC23B | Citywide Grow Bag, Field Grown Tree Proc. Region 1 FY23 | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-0PRC23B | Citywide Grow Bag, Field Grown Tree Proc. Region 1 FY23 | 2 | DESIGN | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-0PRC23B | Citywide Grow Bag, Field Grown Tree Proc. Region 1 FY23 | 3 | BID/ REGISTER CONTRACT | Sep 2024 | Jun 2025 | Sep 2024 | Jun 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-0PRC23B | Citywide Grow Bag, Field Grown Tree Proc. Region 1 FY23 | 4 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-0PRC23B | Citywide Grow Bag, Field Grown Tree Proc. Region 1 FY23 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Jun 2027 | Jun 2026 | Jun 2027
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-0PRC23C | Citywide Field Grown Tree Procurement from Region 1 FY23 | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-0PRC23C | Citywide Field Grown Tree Procurement from Region 1 FY23 | 2 | DESIGN | Sep 2023 | Mar 2024 | Sep 2023 | Mar 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-0PRC23C | Citywide Field Grown Tree Procurement from Region 1 FY23 | 3 | BID/ REGISTER CONTRACT | Mar 2024 | Sep 2024 | Mar 2024 | Sep 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-0PRC23C | Citywide Field Grown Tree Procurement from Region 1 FY23 | 4 | CONSTRUCTION | Sep 2024 | Sep 2033 | Sep 2024 | Sep 2033
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-0PRC23C | Citywide Field Grown Tree Procurement from Region 1 FY23 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2033 | Nov 2033 | Sep 2033 | Nov 2033
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-0PRC23D | Citywide Field Grown Tree Procurement from Region FY23 | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-0PRC23D | Citywide Field Grown Tree Procurement from Region FY23 | 2 | DESIGN | Sep 2023 | Mar 2024 | Sep 2023 | Mar 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-0PRC23D | Citywide Field Grown Tree Procurement from Region FY23 | 3 | BID/ REGISTER CONTRACT | Mar 2024 | Sep 2024 | Mar 2024 | Sep 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-0PRC23D | Citywide Field Grown Tree Procurement from Region FY23 | 4 | CONSTRUCTION | Sep 2024 | Sep 2033 | Sep 2024 | Sep 2033
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-0PRC23D | Citywide Field Grown Tree Procurement from Region FY23 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2033 | Nov 2033 | Sep 2033 | Nov 2033
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-3FREDSM | Fred Samuel Plgd Public Restroom Bldg CNYG-1922M | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-3FREDSM | Fred Samuel Plgd Public Restroom Bldg CNYG-1922M | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-3FREDSM | Fred Samuel Plgd Public Restroom Bldg CNYG-1922M | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-3FREDSM | Fred Samuel Plgd Public Restroom Bldg CNYG-1922M | 4 | CONSTRUCTION | Sep 2024 | Mar 2026 | Sep 2024 | Mar 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-3FREDSM | Fred Samuel Plgd Public Restroom Bldg CNYG-1922M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Jun 2031 | Mar 2026 | Jun 2031
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-3TREMTA | FY14 St Tree Planti for Trees removed 2nd Ave Subway MG214M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Mar 2029
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-3TREMTA | FY14 St Tree Planti for Trees removed 2nd Ave Subway MG214M | 2 | DESIGN | Sep 2013 | Dec 2013 | Mar 2029 | Jun 2029
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-3TREMTA | FY14 St Tree Planti for Trees removed 2nd Ave Subway MG214M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Jun 2029 | Sep 2029
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-3TREMTA | FY14 St Tree Planti for Trees removed 2nd Ave Subway MG214M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Sep 2029 | Sep 2030
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-3TREMTA | FY14 St Tree Planti for Trees removed 2nd Ave Subway MG214M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Sep 2030 | Sep 2031
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO3 | Citywide Zoos - roof replacements at various buildings | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Sep 2014
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO3 | Citywide Zoos - roof replacements at various buildings | 2 | DESIGN | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO3 | Citywide Zoos - roof replacements at various buildings | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2014 | Mar 2015
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO3 | Citywide Zoos - roof replacements at various buildings | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO3 | Citywide Zoos - roof replacements at various buildings | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2016 | Jun 2029
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO4 | Citywide Zoos - HVAC replacements | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Sep 2014
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO4 | Citywide Zoos - HVAC replacements | 2 | DESIGN | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO4 | Citywide Zoos - HVAC replacements | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2014 | Mar 2015
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO4 | Citywide Zoos - HVAC replacements | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO4 | Citywide Zoos - HVAC replacements | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2016 | Jun 2029
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO5 | Citywide Zoos - HVAC at CPZ snow leopard & QZ concession | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2022 | Dec 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO5 | Citywide Zoos - HVAC at CPZ snow leopard & QZ concession | 2 | DESIGN | Dec 2017 | Mar 2019 | Dec 2022 | Mar 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO5 | Citywide Zoos - HVAC at CPZ snow leopard & QZ concession | 3 | BID/ REGISTER CONTRACT | Mar 2019 | Dec 2019 | Mar 2024 | Dec 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO5 | Citywide Zoos - HVAC at CPZ snow leopard & QZ concession | 4 | CONSTRUCTION | Dec 2019 | Dec 2020 | Dec 2024 | Dec 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO5 | Citywide Zoos - HVAC at CPZ snow leopard & QZ concession | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2020 | Dec 2021 | Dec 2025 | Jun 2029
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-65BORO | 5 Boro Relocation - 850 East 138th street, Bronx | 1 | DEVELOP SCOPE | Jul 2010 | Sep 2010 | Jul 2010 | Sep 2010
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-65BORO | 5 Boro Relocation - 850 East 138th street, Bronx | 2 | DESIGN | Sep 2010 | Dec 2010 | Sep 2010 | Dec 2010
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-65BORO | 5 Boro Relocation - 850 East 138th street, Bronx | 3 | BID/ REGISTER CONTRACT | Dec 2010 | Mar 2011 | Dec 2010 | Mar 2011
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-65BORO | 5 Boro Relocation - 850 East 138th street, Bronx | 4 | CONSTRUCTION | Mar 2011 | Mar 2012 | Mar 2011 | Mar 2012
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-65BORO | 5 Boro Relocation - 850 East 138th street, Bronx | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2012 | Mar 2013 | Mar 2012 | Jun 2032
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BLDG9C | FY10 Building Requirements (CNYG-409M) | 1 | DEVELOP SCOPE | Jul 2010 | Sep 2010 | Jul 2010 | Sep 2010
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BLDG9C | FY10 Building Requirements (CNYG-409M) | 2 | DESIGN | Sep 2010 | Dec 2010 | Sep 2010 | Dec 2010
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BLDG9C | FY10 Building Requirements (CNYG-409M) | 3 | BID/ REGISTER CONTRACT | Dec 2010 | Mar 2011 | Dec 2010 | Mar 2011
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BLDG9C | FY10 Building Requirements (CNYG-409M) | 4 | CONSTRUCTION | Mar 2011 | Mar 2012 | Mar 2011 | Mar 2012
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BLDG9C | FY10 Building Requirements (CNYG-409M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2012 | Mar 2013 | Mar 2012 | Jun 2030
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BOIL15 | MOSHOLU PK PRB, PROSPECT PK PAINT SHOP, BENSONHURST SR CTR | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BOIL15 | MOSHOLU PK PRB, PROSPECT PK PAINT SHOP, BENSONHURST SR CTR | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BOIL15 | MOSHOLU PK PRB, PROSPECT PK PAINT SHOP, BENSONHURST SR CTR | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BOIL15 | MOSHOLU PK PRB, PROSPECT PK PAINT SHOP, BENSONHURST SR CTR | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BOIL15 | MOSHOLU PK PRB, PROSPECT PK PAINT SHOP, BENSONHURST SR CTR | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2022 | Jun 2030
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CBLDG4 | REQUIREMENTS - BLDGS - PLMB CNYG-404M | 1 | DEVELOP SCOPE | Jul 2006 | Sep 2006 | Jul 2006 | Sep 2006
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CBLDG4 | REQUIREMENTS - BLDGS - PLMB CNYG-404M | 2 | DESIGN | Sep 2006 | Dec 2006 | Sep 2006 | Dec 2006
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CBLDG4 | REQUIREMENTS - BLDGS - PLMB CNYG-404M | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Dec 2006 | Mar 2007
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CBLDG4 | REQUIREMENTS - BLDGS - PLMB CNYG-404M | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Mar 2007 | Mar 2008
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CBLDG4 | REQUIREMENTS - BLDGS - PLMB CNYG-404M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Mar 2008 | Aug 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CGDWTR | Greenthumb - Installation of water service | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CGDWTR | Greenthumb - Installation of water service | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CGDWTR | Greenthumb - Installation of water service | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CGDWTR | Greenthumb - Installation of water service | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CGDWTR | Greenthumb - Installation of water service | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2028
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CNGEVC | CNG FUEL SITE DECOMM & ELE VEL CHARGING | 1 | DEVELOP SCOPE | Jan 2023 | Jun 2023 | Jan 2023 | Jun 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CNGEVC | CNG FUEL SITE DECOMM & ELE VEL CHARGING | 2 | DESIGN | Jun 2023 | Jun 2024 | Jun 2023 | Jun 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CNGEVC | CNG FUEL SITE DECOMM & ELE VEL CHARGING | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CNGEVC | CNG FUEL SITE DECOMM & ELE VEL CHARGING | 4 | CONSTRUCTION | Mar 2025 | Mar 2026 | Mar 2025 | Mar 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CNGEVC | CNG FUEL SITE DECOMM & ELE VEL CHARGING | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Mar 2027 | Mar 2026 | Jun 2028
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CPIBN3 | CPI PH1- Construction of CW PRB CNYG-3215M | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Jan 2015
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CPIBN3 | CPI PH1- Construction of CW PRB CNYG-3215M | 2 | DESIGN | Sep 2014 | Dec 2014 | Jan 2015 | Jan 2016
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CPIBN3 | CPI PH1- Construction of CW PRB CNYG-3215M | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Apr 2016 | Dec 2016
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CPIBN3 | CPI PH1- Construction of CW PRB CNYG-3215M | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Feb 2017 | Oct 2020
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CPIBN3 | CPI PH1- Construction of CW PRB CNYG-3215M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Oct 2020 | Jun 2028
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CPIBN4 | CPI PH1- Bx & Mn PRB-Bundle 4 CNYG-3315M | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Sep 2014
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CPIBN4 | CPI PH1- Bx & Mn PRB-Bundle 4 CNYG-3315M | 2 | DESIGN | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CPIBN4 | CPI PH1- Bx & Mn PRB-Bundle 4 CNYG-3315M | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2014 | Mar 2015
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CPIBN4 | CPI PH1- Bx & Mn PRB-Bundle 4 CNYG-3315M | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CPIBN4 | CPI PH1- Bx & Mn PRB-Bundle 4 CNYG-3315M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2016 | Jun 2028
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CW1250 | Citywide Boilers and HVAC Systems Lump Sum | 1 | DEVELOP SCOPE | Jul 2006 | Sep 2006 | Jul 2006 | Sep 2006
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CW1250 | Citywide Boilers and HVAC Systems Lump Sum | 2 | DESIGN | Sep 2006 | Dec 2006 | Sep 2006 | Dec 2006
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CW1250 | Citywide Boilers and HVAC Systems Lump Sum | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Dec 2006 | Mar 2007
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CW1250 | Citywide Boilers and HVAC Systems Lump Sum | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Mar 2007 | Mar 2008
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CW1250 | Citywide Boilers and HVAC Systems Lump Sum | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Mar 2008 | Mar 2031
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWBOIL | BOILERS - BRONX/MANH/S I CNYG-498 | 1 | DEVELOP SCOPE | Aug 1997 | Feb 1998 | Aug 1997 | Feb 1998
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWBOIL | BOILERS - BRONX/MANH/S I CNYG-498 | 2 | DESIGN | Feb 1998 | Feb 1999 | Feb 1998 | Feb 1999
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWBOIL | BOILERS - BRONX/MANH/S I CNYG-498 | 3 | BID/ REGISTER CONTRACT | Feb 1999 | Nov 1999 | Feb 1999 | Nov 1999
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWBOIL | BOILERS - BRONX/MANH/S I CNYG-498 | 4 | CONSTRUCTION | Nov 1999 | Nov 2000 | Nov 1999 | Nov 2000
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWBOIL | BOILERS - BRONX/MANH/S I CNYG-498 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2000 | Jun 2028 | Nov 2000 | Jun 2030
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWCMVE | Citywide - Public Rest Rooms Standards Study | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWCMVE | Citywide - Public Rest Rooms Standards Study | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWCMVE | Citywide - Public Rest Rooms Standards Study | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWCMVE | Citywide - Public Rest Rooms Standards Study | 4 | CONSTRUCTION | Sep 2019 | Mar 2021 | Sep 2019 | Mar 2021
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWCMVE | Citywide - Public Rest Rooms Standards Study | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Mar 2022 | Mar 2021 | Jun 2029
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWMINI | MINI-POOLS - CITYWIDE CNYG-1601MA | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2017 | Dec 2017
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWMINI | MINI-POOLS - CITYWIDE CNYG-1601MA | 2 | DESIGN | Dec 2016 | Jun 2018 | Oct 2018 | Apr 2020
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWMINI | MINI-POOLS - CITYWIDE CNYG-1601MA | 3 | BID/ REGISTER CONTRACT | Jun 2018 | Mar 2019 | Apr 2020 | Jan 2021
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWMINI | MINI-POOLS - CITYWIDE CNYG-1601MA | 4 | CONSTRUCTION | Mar 2019 | Sep 2020 | Jan 2021 | Jul 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWMINI | MINI-POOLS - CITYWIDE CNYG-1601MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Jul 2022 | Jun 2033
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWPLE1 | Recon pool electrical systems, Citywide | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Apr 2025 | Oct 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWPLE1 | Recon pool electrical systems, Citywide | 2 | DESIGN | Dec 2019 | Jun 2021 | Oct 2025 | Apr 2027
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWPLE1 | Recon pool electrical systems, Citywide | 3 | BID/ REGISTER CONTRACT | Jun 2021 | Mar 2022 | Apr 2027 | Jan 2028
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWPLE1 | Recon pool electrical systems, Citywide | 4 | CONSTRUCTION | Mar 2022 | Sep 2023 | Jan 2028 | Jun 2029
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWPLE1 | Recon pool electrical systems, Citywide | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Jul 2029 | Jun 2030
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWPLG1 | Recon pool structural systems, Citywide | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2017 | Dec 2017
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWPLG1 | Recon pool structural systems, Citywide | 2 | DESIGN | Dec 2020 | Jun 2022 | Dec 2017 | Apr 2027
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWPLG1 | Recon pool structural systems, Citywide | 3 | BID/ REGISTER CONTRACT | Jun 2022 | Mar 2023 | Apr 2027 | Jan 2028
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWPLG1 | Recon pool structural systems, Citywide | 4 | CONSTRUCTION | Mar 2023 | Sep 2024 | Jan 2028 | Jun 2029
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWPLG1 | Recon pool structural systems, Citywide | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Jul 2029 | Jun 2030
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWR22D | Citywide HVAC R22 Reconstruction CNYG-1721M | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Apr 2023 | Oct 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWR22D | Citywide HVAC R22 Reconstruction CNYG-1721M | 2 | DESIGN | Dec 2020 | Jun 2022 | Oct 2023 | Apr 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWR22D | Citywide HVAC R22 Reconstruction CNYG-1721M | 3 | BID/ REGISTER CONTRACT | Jun 2022 | Mar 2023 | Apr 2025 | Jan 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWR22D | Citywide HVAC R22 Reconstruction CNYG-1721M | 4 | CONSTRUCTION | Mar 2023 | Sep 2024 | Jan 2026 | Jul 2027
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWR22D | Citywide HVAC R22 Reconstruction CNYG-1721M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Jul 2027 | Jun 2028
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWRDIO | CITYWIDE - RUPS/ Radio System & Field equipment Revamp | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWRDIO | CITYWIDE - RUPS/ Radio System & Field equipment Revamp | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWRDIO | CITYWIDE - RUPS/ Radio System & Field equipment Revamp | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWRDIO | CITYWIDE - RUPS/ Radio System & Field equipment Revamp | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWRDIO | CITYWIDE - RUPS/ Radio System & Field equipment Revamp | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2029
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWREWA | Retaining Walls- Citywide-Man.-S.I. & BX CNYG-1320M | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2017 | Dec 2017
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWREWA | Retaining Walls- Citywide-Man.-S.I. & BX CNYG-1320M | 2 | DESIGN | Dec 2020 | Jun 2022 | Dec 2020 | Jun 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWREWA | Retaining Walls- Citywide-Man.-S.I. & BX CNYG-1320M | 3 | BID/ REGISTER CONTRACT | Jun 2022 | Mar 2023 | Jun 2022 | Mar 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWREWA | Retaining Walls- Citywide-Man.-S.I. & BX CNYG-1320M | 4 | CONSTRUCTION | Mar 2023 | Sep 2024 | Mar 2023 | Sep 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWREWA | Retaining Walls- Citywide-Man.-S.I. & BX CNYG-1320M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Jun 2031
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWRPZ1 | Citywide RPZ Install. & Plumbing Systems MG-223M | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWRPZ1 | Citywide RPZ Install. & Plumbing Systems MG-223M | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWRPZ1 | Citywide RPZ Install. & Plumbing Systems MG-223M | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWRPZ1 | Citywide RPZ Install. & Plumbing Systems MG-223M | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWRPZ1 | Citywide RPZ Install. & Plumbing Systems MG-223M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2028
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWRWXM | Recon of retaining walls at various Parks, Bronx & Manhattan | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWRWXM | Recon of retaining walls at various Parks, Bronx & Manhattan | 2 | DESIGN | Feb 2024 | Aug 2025 | Feb 2024 | Aug 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWRWXM | Recon of retaining walls at various Parks, Bronx & Manhattan | 3 | BID/ REGISTER CONTRACT | Aug 2025 | May 2026 | Aug 2025 | May 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWRWXM | Recon of retaining walls at various Parks, Bronx & Manhattan | 4 | CONSTRUCTION | May 2026 | Nov 2027 | May 2026 | Nov 2027
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWRWXM | Recon of retaining walls at various Parks, Bronx & Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2027 | Nov 2028 | Nov 2027 | Nov 2028
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWSTF2 | Citywide Synthetic Turf Limited Scope Reconstruction | 1 | DEVELOP SCOPE | Apr 2024 | Oct 2024 | Apr 2024 | Oct 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWSTF2 | Citywide Synthetic Turf Limited Scope Reconstruction | 2 | DESIGN | Oct 2024 | Oct 2025 | Oct 2024 | Oct 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWSTF2 | Citywide Synthetic Turf Limited Scope Reconstruction | 3 | BID/ REGISTER CONTRACT | Oct 2025 | Jul 2026 | Oct 2025 | Jul 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWSTF2 | Citywide Synthetic Turf Limited Scope Reconstruction | 4 | CONSTRUCTION | Jul 2026 | Jul 2027 | Jul 2026 | Jul 2027
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWSTF2 | Citywide Synthetic Turf Limited Scope Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2027 | Jun 2028 | Jul 2027 | Jun 2028
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWTEL1 | Citywide Telecommunication New Service Installation | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWTEL1 | Citywide Telecommunication New Service Installation | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWTEL1 | Citywide Telecommunication New Service Installation | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWTEL1 | Citywide Telecommunication New Service Installation | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWTEL1 | Citywide Telecommunication New Service Installation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6DEERFE | Citywide - Deer Fencing - SI ,BX | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6DEERFE | Citywide - Deer Fencing - SI ,BX | 2 | DESIGN | Dec 2019 | Jun 2021 | Dec 2019 | Jun 2021
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6DEERFE | Citywide - Deer Fencing - SI ,BX | 3 | BID/ REGISTER CONTRACT | Jun 2021 | Mar 2022 | Jun 2021 | Mar 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6DEERFE | Citywide - Deer Fencing - SI ,BX | 4 | CONSTRUCTION | Mar 2022 | Mar 2024 | Mar 2022 | Mar 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6DEERFE | Citywide - Deer Fencing - SI ,BX | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Mar 2026 | Mar 2024 | Mar 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6DTREE7 | Trees - FY07 Spring Trees (CNYG-407M) | 1 | DEVELOP SCOPE | Jul 2007 | Sep 2007 | Jul 2017 | Dec 2017
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6DTREE7 | Trees - FY07 Spring Trees (CNYG-407M) | 2 | DESIGN | Sep 2007 | Dec 2007 | Jun 2010 | Sep 2010
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6DTREE7 | Trees - FY07 Spring Trees (CNYG-407M) | 3 | BID/ REGISTER CONTRACT | Dec 2007 | Mar 2008 | Sep 2010 | Dec 2010
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6DTREE7 | Trees - FY07 Spring Trees (CNYG-407M) | 4 | CONSTRUCTION | Mar 2008 | Mar 2009 | Dec 2010 | Dec 2011
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6DTREE7 | Trees - FY07 Spring Trees (CNYG-407M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2009 | Mar 2010 | Dec 2011 | Jun 2028
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRA | Emerald Ash Borer (EAB) Tree Remove BX & MN | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRA | Emerald Ash Borer (EAB) Tree Remove BX & MN | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRA | Emerald Ash Borer (EAB) Tree Remove BX & MN | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRA | Emerald Ash Borer (EAB) Tree Remove BX & MN | 4 | CONSTRUCTION | Sep 2020 | Sep 2022 | Sep 2020 | Sep 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRA | Emerald Ash Borer (EAB) Tree Remove BX & MN | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2030
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRB | Emerald Ash Borer (EAB) Tree Remove BK &SI-CNYG-2319M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRB | Emerald Ash Borer (EAB) Tree Remove BK &SI-CNYG-2319M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRB | Emerald Ash Borer (EAB) Tree Remove BK &SI-CNYG-2319M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRB | Emerald Ash Borer (EAB) Tree Remove BK &SI-CNYG-2319M | 4 | CONSTRUCTION | Sep 2020 | Sep 2022 | Sep 2020 | Sep 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRB | Emerald Ash Borer (EAB) Tree Remove BK &SI-CNYG-2319M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2030
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ENVTST | Citywide environment testing at DPR facilities CNYG-119M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Apr 2023 | Oct 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ENVTST | Citywide environment testing at DPR facilities CNYG-119M | 2 | DESIGN | Dec 2017 | Jun 2019 | Oct 2023 | Apr 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ENVTST | Citywide environment testing at DPR facilities CNYG-119M | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Mar 2020 | Apr 2025 | Jan 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ENVTST | Citywide environment testing at DPR facilities CNYG-119M | 4 | CONSTRUCTION | Mar 2020 | Sep 2021 | Jan 2026 | Jul 2027
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ENVTST | Citywide environment testing at DPR facilities CNYG-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Jul 2027 | Jun 2030
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ETREE6 | GREENSTREETS - CITYWIDE CNYG-3105M | 1 | DEVELOP SCOPE | Jul 2006 | Sep 2006 | Jul 2017 | Dec 2017
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ETREE6 | GREENSTREETS - CITYWIDE CNYG-3105M | 2 | DESIGN | Sep 2006 | Dec 2006 | Sep 2006 | Dec 2006
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ETREE6 | GREENSTREETS - CITYWIDE CNYG-3105M | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Dec 2006 | Mar 2007
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ETREE6 | GREENSTREETS - CITYWIDE CNYG-3105M | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Mar 2007 | Mar 2008
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ETREE6 | GREENSTREETS - CITYWIDE CNYG-3105M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Mar 2008 | Jun 2028
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6FACD21 | Citywide Facade Reconstruction CNYG-1421M | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6FACD21 | Citywide Facade Reconstruction CNYG-1421M | 2 | DESIGN | Dec 2022 | Jun 2024 | Dec 2022 | Jun 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6FACD21 | Citywide Facade Reconstruction CNYG-1421M | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6FACD21 | Citywide Facade Reconstruction CNYG-1421M | 4 | CONSTRUCTION | Mar 2025 | Sep 2026 | Mar 2025 | Sep 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6FACD21 | Citywide Facade Reconstruction CNYG-1421M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Sep 2027
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6FNCE01 | GreenThumb Capital Fencing Work, Citywide | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6FNCE01 | GreenThumb Capital Fencing Work, Citywide | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6FNCE01 | GreenThumb Capital Fencing Work, Citywide | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6FNCE01 | GreenThumb Capital Fencing Work, Citywide | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6FNCE01 | GreenThumb Capital Fencing Work, Citywide | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GASBSI | Citywide Oil-to-Gas-Conversion CNYG-2120M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Oct 2015 | Jan 2016
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GASBSI | Citywide Oil-to-Gas-Conversion CNYG-2120M | 2 | DESIGN | Sep 2013 | Dec 2013 | Jan 2016 | Apr 2016
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GASBSI | Citywide Oil-to-Gas-Conversion CNYG-2120M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Apr 2016 | Jul 2016
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GASBSI | Citywide Oil-to-Gas-Conversion CNYG-2120M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Jul 2016 | Jul 2017
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GASBSI | Citywide Oil-to-Gas-Conversion CNYG-2120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Jul 2017 | Jun 2028
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GASMAN | CONVERSION OF OIL TO GAS MANHATTAN MG-814M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Oct 2014 | Jan 2015
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GASMAN | CONVERSION OF OIL TO GAS MANHATTAN MG-814M | 2 | DESIGN | Sep 2013 | Dec 2013 | Jan 2015 | Apr 2015
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GASMAN | CONVERSION OF OIL TO GAS MANHATTAN MG-814M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Apr 2015 | Jul 2015
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GASMAN | CONVERSION OF OIL TO GAS MANHATTAN MG-814M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Jul 2015 | Jun 2016
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GASMAN | CONVERSION OF OIL TO GAS MANHATTAN MG-814M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Jul 2016 | Jun 2033
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GDRL15 | FY15 Citywide guiderail & fencing CNYG-2015M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2017 | Dec 2017
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GDRL15 | FY15 Citywide guiderail & fencing CNYG-2015M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GDRL15 | FY15 Citywide guiderail & fencing CNYG-2015M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GDRL15 | FY15 Citywide guiderail & fencing CNYG-2015M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GDRL15 | FY15 Citywide guiderail & fencing CNYG-2015M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Jun 2033
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GMBXGI | Crotona & Harlem River Green Infrastructure Cons., BX, MN | 1 | DEVELOP SCOPE | Jun 2023 | Dec 2023 | Jun 2023 | Dec 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GMBXGI | Crotona & Harlem River Green Infrastructure Cons., BX, MN | 2 | DESIGN | Dec 2023 | Dec 2025 | Dec 2023 | Dec 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GMBXGI | Crotona & Harlem River Green Infrastructure Cons., BX, MN | 3 | BID/ REGISTER CONTRACT | Dec 2025 | Sep 2026 | Dec 2025 | Sep 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GMBXGI | Crotona & Harlem River Green Infrastructure Cons., BX, MN | 4 | CONSTRUCTION | Sep 2026 | Sep 2029 | Sep 2026 | Sep 2029
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GMBXGI | Crotona & Harlem River Green Infrastructure Cons., BX, MN | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2029 | Sep 2031 | Sep 2029 | Sep 2031
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GRST05 | FY13 Greenstreets - Citywide CNYG-1013 | 1 | DEVELOP SCOPE | Jul 2012 | Sep 2012 | Jul 2012 | Sep 2012
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GRST05 | FY13 Greenstreets - Citywide CNYG-1013 | 2 | DESIGN | Sep 2012 | Dec 2012 | Sep 2012 | Dec 2012
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GRST05 | FY13 Greenstreets - Citywide CNYG-1013 | 3 | BID/ REGISTER CONTRACT | Dec 2012 | Mar 2013 | Dec 2012 | Mar 2013
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GRST05 | FY13 Greenstreets - Citywide CNYG-1013 | 4 | CONSTRUCTION | Mar 2013 | Mar 2014 | Mar 2013 | Mar 2014
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GRST05 | FY13 Greenstreets - Citywide CNYG-1013 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2014 | Mar 2015 | Mar 2014 | Jun 2028
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GTGDN1 | GreenThumb Gardens Irrigation Watershed Plan and EIS | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GTGDN1 | GreenThumb Gardens Irrigation Watershed Plan and EIS | 2 | DESIGN | Feb 2024 | Aug 2025 | Feb 2024 | Aug 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GTGDN1 | GreenThumb Gardens Irrigation Watershed Plan and EIS | 3 | BID/ REGISTER CONTRACT | Aug 2025 | May 2026 | Aug 2025 | May 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GTGDN1 | GreenThumb Gardens Irrigation Watershed Plan and EIS | 4 | CONSTRUCTION | May 2026 | Nov 2027 | May 2026 | Nov 2027
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GTGDN1 | GreenThumb Gardens Irrigation Watershed Plan and EIS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2027 | Nov 2028 | Nov 2027 | Nov 2028
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6LIGHT1 | Construction Of Multisite Path Lighting | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6LIGHT1 | Construction Of Multisite Path Lighting | 2 | DESIGN | Dec 2018 | Jun 2020 | Dec 2018 | Jun 2020
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6LIGHT1 | Construction Of Multisite Path Lighting | 3 | BID/ REGISTER CONTRACT | Jun 2020 | Mar 2021 | Jun 2020 | Mar 2021
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6LIGHT1 | Construction Of Multisite Path Lighting | 4 | CONSTRUCTION | Mar 2021 | Sep 2022 | Mar 2021 | Sep 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6LIGHT1 | Construction Of Multisite Path Lighting | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2030
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6MSHVAC | Recon HVAC at Greenbelt R/C & Queens Museum CNYG-1318M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6MSHVAC | Recon HVAC at Greenbelt R/C & Queens Museum CNYG-1318M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6MSHVAC | Recon HVAC at Greenbelt R/C & Queens Museum CNYG-1318M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6MSHVAC | Recon HVAC at Greenbelt R/C & Queens Museum CNYG-1318M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6MSHVAC | Recon HVAC at Greenbelt R/C & Queens Museum CNYG-1318M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2023 | Sep 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6NRGF01 | NRG - Bronx & Queens Reforestation FY'20 CNYG-3019MA | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6NRGF01 | NRG - Bronx & Queens Reforestation FY'20 CNYG-3019MA | 2 | DESIGN | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6NRGF01 | NRG - Bronx & Queens Reforestation FY'20 CNYG-3019MA | 3 | BID/ REGISTER CONTRACT | Sep 2021 | Jun 2022 | Sep 2021 | Jun 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6NRGF01 | NRG - Bronx & Queens Reforestation FY'20 CNYG-3019MA | 4 | CONSTRUCTION | Jun 2022 | Dec 2024 | Jun 2022 | Dec 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6NRGF01 | NRG - Bronx & Queens Reforestation FY'20 CNYG-3019MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2024 | Dec 2026 | Dec 2024 | Dec 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6OLYMPL | Citywide Olympic Pool Mechanical Systems Recon CNYG-2719M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6OLYMPL | Citywide Olympic Pool Mechanical Systems Recon CNYG-2719M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6OLYMPL | Citywide Olympic Pool Mechanical Systems Recon CNYG-2719M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6OLYMPL | Citywide Olympic Pool Mechanical Systems Recon CNYG-2719M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6OLYMPL | Citywide Olympic Pool Mechanical Systems Recon CNYG-2719M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2027
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ORCAST | Recon Orchard Beach Nature Center | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Apr 2025 | Oct 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ORCAST | Recon Orchard Beach Nature Center | 2 | DESIGN | Dec 2018 | Jun 2020 | Oct 2025 | Apr 2027
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ORCAST | Recon Orchard Beach Nature Center | 3 | BID/ REGISTER CONTRACT | Jun 2020 | Mar 2021 | Apr 2027 | Jan 2028
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ORCAST | Recon Orchard Beach Nature Center | 4 | CONSTRUCTION | Mar 2021 | Sep 2022 | Jan 2028 | Jun 2029
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ORCAST | Recon Orchard Beach Nature Center | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Jul 2029 | Jun 2030
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PBBP15 | FY15 Recon plumbing system in bldg & pool CW CNYG-1415M | 1 | DEVELOP SCOPE | Aug 2017 | Jan 2018 | Aug 2017 | Jan 2018
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PBBP15 | FY15 Recon plumbing system in bldg & pool CW CNYG-1415M | 2 | DESIGN | Jan 2018 | Jan 2019 | Jan 2018 | Jan 2019
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PBBP15 | FY15 Recon plumbing system in bldg & pool CW CNYG-1415M | 3 | BID/ REGISTER CONTRACT | Jan 2019 | Oct 2019 | Jan 2019 | Oct 2019
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PBBP15 | FY15 Recon plumbing system in bldg & pool CW CNYG-1415M | 4 | CONSTRUCTION | Oct 2019 | Oct 2020 | Oct 2019 | Oct 2020
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PBBP15 | FY15 Recon plumbing system in bldg & pool CW CNYG-1415M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2020 | Oct 2021 | Oct 2020 | Oct 2021
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PDPLEL | Recon electrical systems in pools - Citywide CNYG - 815M | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Sep 2014
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PDPLEL | Recon electrical systems in pools - Citywide CNYG - 815M | 2 | DESIGN | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PDPLEL | Recon electrical systems in pools - Citywide CNYG - 815M | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2014 | Mar 2015
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PDPLEL | Recon electrical systems in pools - Citywide CNYG - 815M | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PDPLEL | Recon electrical systems in pools - Citywide CNYG - 815M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2016 | Jun 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PKTR23 | Bronx & Manhattan Park Tree Planting FY23 | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PKTR23 | Bronx & Manhattan Park Tree Planting FY23 | 2 | DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PKTR23 | Bronx & Manhattan Park Tree Planting FY23 | 3 | BID/ REGISTER CONTRACT | Jun 2023 | Mar 2024 | Jun 2023 | Mar 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PKTR23 | Bronx & Manhattan Park Tree Planting FY23 | 4 | CONSTRUCTION | Mar 2024 | Sep 2025 | Mar 2024 | Sep 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PKTR23 | Bronx & Manhattan Park Tree Planting FY23 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PLFLTR | Recon of intermediate pool filter plants citywide CNYG-619M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Apr 2021 | Oct 2021
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PLFLTR | Recon of intermediate pool filter plants citywide CNYG-619M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2022 | Dec 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PLFLTR | Recon of intermediate pool filter plants citywide CNYG-619M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2023 | Sep 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PLFLTR | Recon of intermediate pool filter plants citywide CNYG-619M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2024 | Sep 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PLFLTR | Recon of intermediate pool filter plants citywide CNYG-619M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2025 | Jun 2030
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR39 | Reforestation Proc. FY23-28- BX, MN, QNS | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR39 | Reforestation Proc. FY23-28- BX, MN, QNS | 2 | DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR39 | Reforestation Proc. FY23-28- BX, MN, QNS | 3 | BID/ REGISTER CONTRACT | Jun 2023 | Dec 2023 | Jun 2023 | Dec 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR39 | Reforestation Proc. FY23-28- BX, MN, QNS | 4 | CONSTRUCTION | Dec 2023 | Dec 2032 | Dec 2023 | Dec 2032
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR39 | Reforestation Proc. FY23-28- BX, MN, QNS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2032 | Feb 2033 | Dec 2032 | Feb 2033
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR40 | Reforestation Proc. FY23-28- BK, Qns , SI | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2017 | Dec 2017
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR40 | Reforestation Proc. FY23-28- BK, Qns , SI | 2 | DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR40 | Reforestation Proc. FY23-28- BK, Qns , SI | 3 | BID/ REGISTER CONTRACT | Jun 2023 | Dec 2023 | Jun 2023 | Dec 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR40 | Reforestation Proc. FY23-28- BK, Qns , SI | 4 | CONSTRUCTION | Dec 2023 | Dec 2032 | Dec 2023 | Dec 2028
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR40 | Reforestation Proc. FY23-28- BK, Qns , SI | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2032 | Feb 2033 | Dec 2028 | Jun 2032
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYT25 | PlaNYC - FY21 Citiwide Tree Guard Installation | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYT25 | PlaNYC - FY21 Citiwide Tree Guard Installation | 2 | DESIGN | Dec 2019 | Jun 2021 | Dec 2019 | Jun 2021
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYT25 | PlaNYC - FY21 Citiwide Tree Guard Installation | 3 | BID/ REGISTER CONTRACT | Jun 2021 | Mar 2022 | Jun 2021 | Mar 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYT25 | PlaNYC - FY21 Citiwide Tree Guard Installation | 4 | CONSTRUCTION | Mar 2022 | Mar 2024 | Mar 2022 | Mar 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYT25 | PlaNYC - FY21 Citiwide Tree Guard Installation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Mar 2026 | Mar 2024 | Mar 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6POOL18 | Recon Citywide pools $1 Contract CNYG-918M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2017 | Dec 2017
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6POOL18 | Recon Citywide pools $1 Contract CNYG-918M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6POOL18 | Recon Citywide pools $1 Contract CNYG-918M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6POOL18 | Recon Citywide pools $1 Contract CNYG-918M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6POOL18 | Recon Citywide pools $1 Contract CNYG-918M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2030
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6POOL21 | Citywide Pool Plumbing Reconstruction | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6POOL21 | Citywide Pool Plumbing Reconstruction | 2 | DESIGN | Dec 2021 | Jun 2023 | Dec 2021 | Jun 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6POOL21 | Citywide Pool Plumbing Reconstruction | 3 | BID/ REGISTER CONTRACT | Jun 2023 | Mar 2024 | Jun 2023 | Mar 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6POOL21 | Citywide Pool Plumbing Reconstruction | 4 | CONSTRUCTION | Mar 2024 | Sep 2025 | Mar 2024 | Sep 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6POOL21 | Citywide Pool Plumbing Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PREFA1 | Compact Prefabricated PRBs for BK & SI | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PREFA1 | Compact Prefabricated PRBs for BK & SI | 2 | DESIGN | Dec 2022 | Jun 2024 | Dec 2022 | Jun 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PREFA1 | Compact Prefabricated PRBs for BK & SI | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PREFA1 | Compact Prefabricated PRBs for BK & SI | 4 | CONSTRUCTION | Mar 2025 | Sep 2026 | Mar 2025 | Sep 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PREFA1 | Compact Prefabricated PRBs for BK & SI | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Jun 2028 | Sep 2026 | Jun 2028
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PREFAB | Compact Prefabricated PRBs for BX,QN,MN | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PREFAB | Compact Prefabricated PRBs for BX,QN,MN | 2 | DESIGN | Dec 2022 | Jun 2024 | Dec 2022 | Jun 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PREFAB | Compact Prefabricated PRBs for BX,QN,MN | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PREFAB | Compact Prefabricated PRBs for BX,QN,MN | 4 | CONSTRUCTION | Mar 2025 | Sep 2026 | Mar 2025 | Sep 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PREFAB | Compact Prefabricated PRBs for BX,QN,MN | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Jun 2028 | Sep 2026 | Jun 2028
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PRKLOT | Recon 5Boro & Garage complex prkg lot M104-117M | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PRKLOT | Recon 5Boro & Garage complex prkg lot M104-117M | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PRKLOT | Recon 5Boro & Garage complex prkg lot M104-117M | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PRKLOT | Recon 5Boro & Garage complex prkg lot M104-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PVMNT1 | Reconstruct pavement various Parks CNYG-117MA | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Apr 2021 | Oct 2021
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PVMNT1 | Reconstruct pavement various Parks CNYG-117MA | 2 | DESIGN | Dec 2017 | Dec 2018 | Oct 2021 | Oct 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PVMNT1 | Reconstruct pavement various Parks CNYG-117MA | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Oct 2022 | Jul 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PVMNT1 | Reconstruct pavement various Parks CNYG-117MA | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Jul 2023 | Jun 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PVMNT1 | Reconstruct pavement various Parks CNYG-117MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Jul 2024 | Jun 2030
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PVMNT2 | Citywide Pavement Reconstruction 2 CNYG-1618M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Apr 2021 | Oct 2021
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PVMNT2 | Citywide Pavement Reconstruction 2 CNYG-1618M | 2 | DESIGN | Dec 2017 | Dec 2018 | Oct 2021 | Oct 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PVMNT2 | Citywide Pavement Reconstruction 2 CNYG-1618M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Oct 2022 | Jul 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PVMNT2 | Citywide Pavement Reconstruction 2 CNYG-1618M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Jul 2023 | Jun 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PVMNT2 | Citywide Pavement Reconstruction 2 CNYG-1618M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Jul 2024 | Jun 2029
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REC11B | Queens, Brooklyn & SI HVAC systems CNYG-1910MA1 | 1 | DEVELOP SCOPE | Jan 2010 | Feb 2010 | Dec 2009 | Feb 2010
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REC11B | Queens, Brooklyn & SI HVAC systems CNYG-1910MA1 | 2 | DESIGN | Feb 2010 | Mar 2010 | Feb 2010 | Feb 2010
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REC11B | Queens, Brooklyn & SI HVAC systems CNYG-1910MA1 | 3 | BID/ REGISTER CONTRACT | Mar 2010 | Mar 2010 | Feb 2010 | Feb 2010
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REC11B | Queens, Brooklyn & SI HVAC systems CNYG-1910MA1 | 4 | CONSTRUCTION | Mar 2010 | Mar 2010 | Feb 2010 | Feb 2010
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REC11B | Queens, Brooklyn & SI HVAC systems CNYG-1910MA1 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2010 | Mar 2011 | Feb 2010 | Jun 2028
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW14 | Retaining Wall R/C (CNYG-514M) | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Oct 2013
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW14 | Retaining Wall R/C (CNYG-514M) | 2 | DESIGN | Sep 2013 | Dec 2013 | Oct 2013 | Jan 2014
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW14 | Retaining Wall R/C (CNYG-514M) | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Apr 2014 | May 2015
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW14 | Retaining Wall R/C (CNYG-514M) | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | May 2015 | Feb 2020
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW14 | Retaining Wall R/C (CNYG-514M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Feb 2020 | Jun 2028
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW18 | Citywide Retaining Wall FY18 CNYG-1818M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW18 | Citywide Retaining Wall FY18 CNYG-1818M | 2 | DESIGN | Dec 2018 | Jun 2020 | Dec 2018 | Jun 2020
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW18 | Citywide Retaining Wall FY18 CNYG-1818M | 3 | BID/ REGISTER CONTRACT | Jun 2020 | Mar 2021 | Jun 2020 | Mar 2021
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW18 | Citywide Retaining Wall FY18 CNYG-1818M | 4 | CONSTRUCTION | Mar 2021 | Sep 2022 | Mar 2021 | Sep 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW18 | Citywide Retaining Wall FY18 CNYG-1818M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2029
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW23 | Citywide Retaining Wall Reconstruction | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW23 | Citywide Retaining Wall Reconstruction | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW23 | Citywide Retaining Wall Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW23 | Citywide Retaining Wall Reconstruction | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW23 | Citywide Retaining Wall Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Jun 2031 | Sep 2025 | Jun 2031
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ROOF22 | Citywide Roof Reconstruction | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ROOF22 | Citywide Roof Reconstruction | 2 | DESIGN | Dec 2022 | Jun 2024 | Dec 2022 | Jun 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ROOF22 | Citywide Roof Reconstruction | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ROOF22 | Citywide Roof Reconstruction | 4 | CONSTRUCTION | Mar 2025 | Sep 2026 | Mar 2025 | Sep 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ROOF22 | Citywide Roof Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Sep 2027
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RPZBKQ | Brooklyn & Queens Multi-Site RPZ Installation | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RPZBKQ | Brooklyn & Queens Multi-Site RPZ Installation | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RPZBKQ | Brooklyn & Queens Multi-Site RPZ Installation | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RPZBKQ | Brooklyn & Queens Multi-Site RPZ Installation | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RPZBKQ | Brooklyn & Queens Multi-Site RPZ Installation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SEAWAL | Citywide Seawall Reconstruction | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SEAWAL | Citywide Seawall Reconstruction | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SEAWAL | Citywide Seawall Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SEAWAL | Citywide Seawall Reconstruction | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SEAWAL | Citywide Seawall Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SECBOL | Parks Security Measures Citywide | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2023 | Dec 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SECBOL | Parks Security Measures Citywide | 2 | DESIGN | Dec 2017 | Jun 2019 | Dec 2023 | Jun 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SECBOL | Parks Security Measures Citywide | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Mar 2020 | Jun 2025 | Mar 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SECBOL | Parks Security Measures Citywide | 4 | CONSTRUCTION | Mar 2020 | Sep 2021 | Mar 2026 | Sep 2027
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SECBOL | Parks Security Measures Citywide | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2027 | Jun 2029
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SPCR15 | NRG - Spring Creek Salt Marsh Restoration CNYG-2715M | 1 | DEVELOP SCOPE | Sep 2014 | Nov 2014 | Jul 2020 | Sep 2020
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SPCR15 | NRG - Spring Creek Salt Marsh Restoration CNYG-2715M | 2 | DESIGN | Nov 2014 | Feb 2015 | Sep 2020 | Apr 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SPCR15 | NRG - Spring Creek Salt Marsh Restoration CNYG-2715M | 3 | BID/ REGISTER CONTRACT | Feb 2015 | May 2015 | Apr 2022 | Jun 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SPCR15 | NRG - Spring Creek Salt Marsh Restoration CNYG-2715M | 4 | CONSTRUCTION | May 2015 | May 2016 | Jul 2022 | Jun 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SPCR15 | NRG - Spring Creek Salt Marsh Restoration CNYG-2715M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | May 2016 | May 2017 | Jul 2026 | Jun 2030
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6STRUC1 | Citywide structural stabilization - Multisite CNYG-1617M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2017 | Dec 2017
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6STRUC1 | Citywide structural stabilization - Multisite CNYG-1617M | 2 | DESIGN | Dec 2016 | Jun 2018 | Dec 2016 | Jun 2018
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6STRUC1 | Citywide structural stabilization - Multisite CNYG-1617M | 3 | BID/ REGISTER CONTRACT | Jun 2018 | Mar 2019 | Jun 2018 | Mar 2019
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6STRUC1 | Citywide structural stabilization - Multisite CNYG-1617M | 4 | CONSTRUCTION | Mar 2019 | Sep 2020 | Mar 2019 | Sep 2020
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6STRUC1 | Citywide structural stabilization - Multisite CNYG-1617M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2031
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6STRUC2 | Citywide Structural Systems Reconstruction CNYG-2619MA | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6STRUC2 | Citywide Structural Systems Reconstruction CNYG-2619MA | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6STRUC2 | Citywide Structural Systems Reconstruction CNYG-2619MA | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6STRUC2 | Citywide Structural Systems Reconstruction CNYG-2619MA | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6STRUC2 | Citywide Structural Systems Reconstruction CNYG-2619MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SUSTN1 | Citywide Dollar Sustainability Contract CNYG-319MA | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SUSTN1 | Citywide Dollar Sustainability Contract CNYG-319MA | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SUSTN1 | Citywide Dollar Sustainability Contract CNYG-319MA | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SUSTN1 | Citywide Dollar Sustainability Contract CNYG-319MA | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SUSTN1 | Citywide Dollar Sustainability Contract CNYG-319MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SWK13A | FY13 Trees & Sidewalks Bronx, Brooklyn, & Queens CNYG-213M | 1 | DEVELOP SCOPE | Jul 2012 | Sep 2012 | Jul 2012 | Sep 2012
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SWK13A | FY13 Trees & Sidewalks Bronx, Brooklyn, & Queens CNYG-213M | 2 | DESIGN | Sep 2012 | Dec 2012 | Sep 2012 | Dec 2012
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SWK13A | FY13 Trees & Sidewalks Bronx, Brooklyn, & Queens CNYG-213M | 3 | BID/ REGISTER CONTRACT | Dec 2012 | Mar 2013 | Dec 2012 | Mar 2013
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SWK13A | FY13 Trees & Sidewalks Bronx, Brooklyn, & Queens CNYG-213M | 4 | CONSTRUCTION | Mar 2013 | Mar 2014 | Mar 2013 | Mar 2014
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SWK13A | FY13 Trees & Sidewalks Bronx, Brooklyn, & Queens CNYG-213M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2014 | Mar 2015 | Mar 2014 | Jun 2028
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRAI20 | FY19 NRG Arden Woods Trail Construction | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2017 | Dec 2017
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRAI20 | FY19 NRG Arden Woods Trail Construction | 2 | DESIGN | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRAI20 | FY19 NRG Arden Woods Trail Construction | 3 | BID/ REGISTER CONTRACT | Sep 2019 | Jun 2020 | Sep 2019 | Jun 2020
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRAI20 | FY19 NRG Arden Woods Trail Construction | 4 | CONSTRUCTION | Jun 2020 | Dec 2022 | Jun 2020 | Dec 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRAI20 | FY19 NRG Arden Woods Trail Construction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2022 | Dec 2024 | Dec 2022 | Jun 2028
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE15A | FY15 - Consultant Supervision - Street Tree Planting | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE15A | FY15 - Consultant Supervision - Street Tree Planting | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE18A | Street Trees Supervision FY18 | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2028
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE18A | Street Trees Supervision FY18 | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2028 | Dec 2029
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE18A | Street Trees Supervision FY18 | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2029 | Sep 2030
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE18A | Street Trees Supervision FY18 | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2030 | Sep 2031
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE18A | Street Trees Supervision FY18 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2031 | Sep 2032
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE19A | Street Trees Supervision FY19 | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE19A | Street Trees Supervision FY19 | 2 | DESIGN | Dec 2018 | Jun 2019 | Dec 2018 | Jun 2019
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE19A | Street Trees Supervision FY19 | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Dec 2019 | Jun 2019 | Dec 2019
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE19A | Street Trees Supervision FY19 | 4 | CONSTRUCTION | Dec 2019 | Dec 2028 | Dec 2019 | Dec 2028
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE19A | Street Trees Supervision FY19 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2028 | Feb 2029 | Dec 2028 | Feb 2029
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE23B | CW Tree & Park Planting Supervision FY 23 | 1 | DEVELOP SCOPE | Jun 2023 | Dec 2023 | Jun 2023 | Dec 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE23B | CW Tree & Park Planting Supervision FY 23 | 2 | DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE23B | CW Tree & Park Planting Supervision FY 23 | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE23B | CW Tree & Park Planting Supervision FY 23 | 4 | CONSTRUCTION | Mar 2025 | Sep 2026 | Mar 2025 | Sep 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE23B | CW Tree & Park Planting Supervision FY 23 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2028 | Sep 2026 | Sep 2028
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE24A | CW Tree Planting Supervision, FY24 ST & Pk Tree Pl & Rplce | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE24A | CW Tree Planting Supervision, FY24 ST & Pk Tree Pl & Rplce | 2 | DESIGN | Feb 2024 | Aug 2024 | Feb 2024 | Aug 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE24A | CW Tree Planting Supervision, FY24 ST & Pk Tree Pl & Rplce | 3 | BID/ REGISTER CONTRACT | Aug 2024 | May 2025 | Aug 2024 | May 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE24A | CW Tree Planting Supervision, FY24 ST & Pk Tree Pl & Rplce | 4 | CONSTRUCTION | May 2025 | Nov 2026 | May 2025 | Nov 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE24A | CW Tree Planting Supervision, FY24 ST & Pk Tree Pl & Rplce | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2028 | Nov 2026 | Nov 2028
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREEP1 | Procurement of Street Trees Region 1-CNYG-3916M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREEP1 | Procurement of Street Trees Region 1-CNYG-3916M | 2 | DESIGN | Dec 2017 | Jun 2018 | Dec 2017 | Jun 2018
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREEP1 | Procurement of Street Trees Region 1-CNYG-3916M | 3 | BID/ REGISTER CONTRACT | Jun 2018 | Dec 2018 | Jun 2018 | Dec 2018
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREEP1 | Procurement of Street Trees Region 1-CNYG-3916M | 4 | CONSTRUCTION | Dec 2018 | Dec 2027 | Dec 2018 | Dec 2027
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREEP1 | Procurement of Street Trees Region 1-CNYG-3916M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2027 | Feb 2028 | Dec 2027 | Dec 2030
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREEP2 | Procurement of Street Trees Region 2-CNYG-4016M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREEP2 | Procurement of Street Trees Region 2-CNYG-4016M | 2 | DESIGN | Dec 2017 | Jun 2018 | Dec 2017 | Jun 2018
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREEP2 | Procurement of Street Trees Region 2-CNYG-4016M | 3 | BID/ REGISTER CONTRACT | Jun 2018 | Dec 2018 | Jun 2018 | Dec 2018
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREEP2 | Procurement of Street Trees Region 2-CNYG-4016M | 4 | CONSTRUCTION | Dec 2018 | Dec 2027 | Dec 2018 | Dec 2027
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREEP2 | Procurement of Street Trees Region 2-CNYG-4016M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2027 | Feb 2028 | Dec 2027 | Dec 2030
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREESB | Citywide Street Tree Planting Lump Sum | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREESB | Citywide Street Tree Planting Lump Sum | 2 | DESIGN | Dec 2018 | Jun 2019 | Dec 2018 | Jun 2019
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREESB | Citywide Street Tree Planting Lump Sum | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Dec 2019 | Jun 2019 | Dec 2019
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREESB | Citywide Street Tree Planting Lump Sum | 4 | CONSTRUCTION | Dec 2019 | Dec 2028 | Dec 2019 | Dec 2028
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREESB | Citywide Street Tree Planting Lump Sum | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2028 | Feb 2029 | Dec 2028 | Feb 2029
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREGRD | FY21 CitywideTree Guards | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Oct 2020 | Apr 2021
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREGRD | FY21 CitywideTree Guards | 2 | DESIGN | Dec 2019 | Jun 2021 | Apr 2021 | Oct 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREGRD | FY21 CitywideTree Guards | 3 | BID/ REGISTER CONTRACT | Jun 2021 | Mar 2022 | Oct 2022 | Jul 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREGRD | FY21 CitywideTree Guards | 4 | CONSTRUCTION | Mar 2022 | Mar 2025 | Jul 2023 | Jul 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREGRD | FY21 CitywideTree Guards | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Mar 2027 | Jul 2026 | Jun 2030
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREL21 | FY21 Street Tree Long Term Supervision | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREL21 | FY21 Street Tree Long Term Supervision | 2 | DESIGN | Dec 2019 | Jun 2021 | Dec 2019 | Jun 2021
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREL21 | FY21 Street Tree Long Term Supervision | 3 | BID/ REGISTER CONTRACT | Jun 2021 | Mar 2022 | Jun 2021 | Mar 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREL21 | FY21 Street Tree Long Term Supervision | 4 | CONSTRUCTION | Mar 2022 | Mar 2025 | Mar 2022 | Mar 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREL21 | FY21 Street Tree Long Term Supervision | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Mar 2027 | Mar 2025 | Mar 2027
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRFMAT | Citywide Synthetic Turf Material Purchase | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRFMAT | Citywide Synthetic Turf Material Purchase | 2 | DESIGN | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRFMAT | Citywide Synthetic Turf Material Purchase | 3 | BID/ REGISTER CONTRACT | Sep 2024 | Jun 2025 | Sep 2024 | Jun 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRFMAT | Citywide Synthetic Turf Material Purchase | 4 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRFMAT | Citywide Synthetic Turf Material Purchase | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Jun 2027 | Jun 2026 | Jun 2027
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRGRD1 | Citywide Tree Guard Installation FY24 | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRGRD1 | Citywide Tree Guard Installation FY24 | 2 | DESIGN | Feb 2024 | Aug 2024 | Feb 2024 | Aug 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRGRD1 | Citywide Tree Guard Installation FY24 | 3 | BID/ REGISTER CONTRACT | Aug 2024 | May 2025 | Aug 2024 | May 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRGRD1 | Citywide Tree Guard Installation FY24 | 4 | CONSTRUCTION | May 2025 | Nov 2026 | May 2025 | Nov 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRGRD1 | Citywide Tree Guard Installation FY24 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2028 | Nov 2026 | Nov 2028
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRS19A | CW- RC Sidewalks Damaged by Trees Supervision CNYG-1319M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRS19A | CW- RC Sidewalks Damaged by Trees Supervision CNYG-1319M | 2 | DESIGN | Dec 2018 | Jun 2019 | Dec 2018 | Jun 2019
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRS19A | CW- RC Sidewalks Damaged by Trees Supervision CNYG-1319M | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Dec 2019 | Jun 2019 | Dec 2019
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRS19A | CW- RC Sidewalks Damaged by Trees Supervision CNYG-1319M | 4 | CONSTRUCTION | Dec 2019 | Dec 2028 | Dec 2019 | Dec 2028
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRS19A | CW- RC Sidewalks Damaged by Trees Supervision CNYG-1319M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2028 | Feb 2029 | Dec 2028 | Feb 2029
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRS23A | Bronx & Manhattan Tree-Damaged Sidewalk Reconstruction FY23 | 1 | DEVELOP SCOPE | Jan 2023 | Jun 2023 | Jan 2023 | Jun 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRS23A | Bronx & Manhattan Tree-Damaged Sidewalk Reconstruction FY23 | 2 | DESIGN | Jun 2023 | Jun 2024 | Jun 2023 | Jun 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRS23A | Bronx & Manhattan Tree-Damaged Sidewalk Reconstruction FY23 | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRS23A | Bronx & Manhattan Tree-Damaged Sidewalk Reconstruction FY23 | 4 | CONSTRUCTION | Mar 2025 | Mar 2026 | Mar 2025 | Mar 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRS23A | Bronx & Manhattan Tree-Damaged Sidewalk Reconstruction FY23 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Mar 2027 | Mar 2026 | Mar 2027
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6WATRF1 | Design services: rehabilitations of waterfriont structures | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6WATRF1 | Design services: rehabilitations of waterfriont structures | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6WATRF1 | Design services: rehabilitations of waterfriont structures | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6WATRF1 | Design services: rehabilitations of waterfriont structures | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6WATRF1 | Design services: rehabilitations of waterfriont structures | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Jun 2032 | Nov 2026 | Jun 2032
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6WTRSWR | Citywide Multisite Water and Sewer Reconstruction | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6WTRSWR | Citywide Multisite Water and Sewer Reconstruction | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6WTRSWR | Citywide Multisite Water and Sewer Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6WTRSWR | Citywide Multisite Water and Sewer Reconstruction | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6WTRSWR | Citywide Multisite Water and Sewer Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-06 | SANDY - S.I. Beaches Protective Measures North RG-813M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2013
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-06 | SANDY - S.I. Beaches Protective Measures North RG-813M | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-06 | SANDY - S.I. Beaches Protective Measures North RG-813M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2013 | Mar 2014
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-06 | SANDY - S.I. Beaches Protective Measures North RG-813M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2015
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-06 | SANDY - S.I. Beaches Protective Measures North RG-813M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2015 | Dec 2027
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-14 | SANDY - Boardwalks Design CW | 1 | DEVELOP SCOPE | Jul 2012 | Sep 2012 | Jul 2023 | Dec 2023
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-14 | SANDY - Boardwalks Design CW | 2 | DESIGN | Sep 2012 | Dec 2012 | Dec 2023 | Mar 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-14 | SANDY - Boardwalks Design CW | 3 | BID/ REGISTER CONTRACT | Dec 2012 | Mar 2013 | Mar 2025 | Dec 2025
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-14 | SANDY - Boardwalks Design CW | 4 | CONSTRUCTION | Mar 2013 | Mar 2014 | Dec 2025 | Dec 2026
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-14 | SANDY - Boardwalks Design CW | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2014 | Mar 2015 | Dec 2026 | Jun 2031
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-17 | Sandy-Trees Removal in Bk & SI CNYG-3616M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Mar 2029
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-17 | Sandy-Trees Removal in Bk & SI CNYG-3616M | 2 | DESIGN | Dec 2017 | Dec 2018 | Mar 2029 | Mar 2030
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-17 | Sandy-Trees Removal in Bk & SI CNYG-3616M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Mar 2030 | Dec 2030
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-17 | Sandy-Trees Removal in Bk & SI CNYG-3616M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Dec 2030 | Dec 2031
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-17 | Sandy-Trees Removal in Bk & SI CNYG-3616M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Dec 2031 | Dec 2032
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-18 | Sandy-Trees Removal in BX ,Mnht & Que CNYG-3516M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Mar 2029
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-18 | Sandy-Trees Removal in BX ,Mnht & Que CNYG-3516M | 2 | DESIGN | Dec 2017 | Dec 2018 | Mar 2029 | Mar 2030
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-18 | Sandy-Trees Removal in BX ,Mnht & Que CNYG-3516M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Mar 2030 | Dec 2030
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-18 | Sandy-Trees Removal in BX ,Mnht & Que CNYG-3516M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Dec 2030 | Dec 2031
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-18 | Sandy-Trees Removal in BX ,Mnht & Que CNYG-3516M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Dec 2031 | Dec 2032
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-21 | Sandy Tree Planting and Replanting - BX, Q, & M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-21 | Sandy Tree Planting and Replanting - BX, Q, & M | 2 | DESIGN | Dec 2017 | Jun 2018 | Dec 2017 | Jun 2018
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-21 | Sandy Tree Planting and Replanting - BX, Q, & M | 3 | BID/ REGISTER CONTRACT | Jun 2018 | Mar 2019 | Jun 2018 | Mar 2019
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-21 | Sandy Tree Planting and Replanting - BX, Q, & M | 4 | CONSTRUCTION | Mar 2019 | Sep 2020 | Mar 2019 | Sep 2020
20231026 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-21 | Sandy Tree Planting and Replanting - BX, Q, & M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2022 | Sep 2020 | Jun 2028
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | ARMORIES | RECONSTRUCTION OF ARMORIES IN BKLYN. AND THE BRONX | 2 | DESIGN START | Dec 2000 | Jan 2001 | Apr 1997 | May 1997
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | ARMORIES | RECONSTRUCTION OF ARMORIES IN BKLYN. AND THE BRONX | 3 | DESIGN COMPLETION | Jan 2001 | Apr 2002 | May 1997 | Aug 1998
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | ARMORIES | RECONSTRUCTION OF ARMORIES IN BKLYN. AND THE BRONX | 4 | CONSTRUCTION START | Apr 2002 | May 2002 | Aug 1998 | Aug 1998
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | ARMORIES | RECONSTRUCTION OF ARMORIES IN BKLYN. AND THE BRONX | 5 | CONSTRUCTION COMPLETION | May 2002 | May 2004 | Aug 1998 | Oct 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | ARMORIES | RECONSTRUCTION OF ARMORIES IN BKLYN. AND THE BRONX | 6 | DEVELOP SCOPE | May 2002 | May 2004 | Oct 2016 | Jan 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | ARMORIES | RECONSTRUCTION OF ARMORIES IN BKLYN. AND THE BRONX | 7 | PRELIMINARY DESIGN | May 2002 | May 2004 | Jan 2017 | May 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | ARMORIES | RECONSTRUCTION OF ARMORIES IN BKLYN. AND THE BRONX | 8 | FINAL DESIGN | May 2002 | May 2004 | May 2017 | Nov 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | ARMORIES | RECONSTRUCTION OF ARMORIES IN BKLYN. AND THE BRONX | 9 | BID AWARD AND REGISTER CONTRCT | May 2002 | May 2004 | Nov 2017 | Feb 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | ARMORIES | RECONSTRUCTION OF ARMORIES IN BKLYN. AND THE BRONX | 10 | CONSTRUCTION TO 25% | May 2002 | May 2004 | Feb 2018 | Jun 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | ARMORIES | RECONSTRUCTION OF ARMORIES IN BKLYN. AND THE BRONX | 11 | CONSTRUCTION TO 50% | May 2002 | May 2004 | Jun 2018 | Oct 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | ARMORIES | RECONSTRUCTION OF ARMORIES IN BKLYN. AND THE BRONX | 12 | CONSTRUCTION TO 75% | May 2002 | May 2004 | Oct 2018 | Feb 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | ARMORIES | RECONSTRUCTION OF ARMORIES IN BKLYN. AND THE BRONX | 13 | ORIGINAL EQUIP & FURNISHING | May 2002 | May 2004 | Feb 2019 | May 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | ARMORIES | RECONSTRUCTION OF ARMORIES IN BKLYN. AND THE BRONX | 14 | SUBSTANTIAL COMPLETION | May 2002 | May 2004 | May 2019 | Jul 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | ARMORIES | RECONSTRUCTION OF ARMORIES IN BKLYN. AND THE BRONX | 15 | PUNCHLIST COMPLETE, JOB CLOSED | May 2002 | May 2004 | Jul 2019 | Aug 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-827 | Regulator Chamber Roof Replacements | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-827 | Regulator Chamber Roof Replacements | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-827 | Regulator Chamber Roof Replacements | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-827 | Regulator Chamber Roof Replacements | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-827 | Regulator Chamber Roof Replacements | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-827 | Regulator Chamber Roof Replacements | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-827 | Regulator Chamber Roof Replacements | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-827 | Regulator Chamber Roof Replacements | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-827 | Regulator Chamber Roof Replacements | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-827 | Regulator Chamber Roof Replacements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Feb 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | C114ACADY | Construction of a New Training Academy | 1 | DESIGN | Sep 2017 | Jul 2018 | Sep 2017 | Jul 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | C114ACADY | Construction of a New Training Academy | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Jul 2019 | Jul 2018 | Jul 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | C114ACADY | Construction of a New Training Academy | 3 | CONSTRUCTION TO 75% | Jul 2019 | Feb 2021 | Jul 2019 | Feb 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | C114ACADY | Construction of a New Training Academy | 4 | SUBSTANTIAL COMPLETION | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | C114ACADY | Construction of a New Training Academy | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2021 | Aug 2021 | Jun 2021 | Aug 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | C114ACADY | Construction of a New Training Academy | 6 | PROJECT START | Jun 2021 | Aug 2021 | Sep 2025 | Sep 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | C114ACADY | Construction of a New Training Academy | 7 | DESIGN START | Jun 2021 | Aug 2021 | Sep 2025 | Sep 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | C114ACADY | Construction of a New Training Academy | 8 | DESIGN COMPLETION | Jun 2021 | Aug 2021 | Sep 2025 | Jan 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | C114ACADY | Construction of a New Training Academy | 9 | CONSTRUCTION START | Jun 2021 | Aug 2021 | Jan 2027 | May 2028
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | C114ACADY | Construction of a New Training Academy | 10 | CONSTRUCTION COMPLETION | Jun 2021 | Aug 2021 | May 2028 | Sep 2031
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | CT2-INTER | CITY TUNNEL #2, REPLACE GUARD VALVES @ 16A | 1 | DEVELOP SCOPE | Mar 2015 | May 2015 | Jul 2014 | Dec 2014
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | CT2-INTER | CITY TUNNEL #2, REPLACE GUARD VALVES @ 16A | 2 | PRELIMINARY DESIGN | May 2015 | Sep 2015 | Dec 2014 | Sep 2015
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | CT2-INTER | CITY TUNNEL #2, REPLACE GUARD VALVES @ 16A | 3 | FINAL DESIGN | Sep 2015 | Mar 2018 | Sep 2015 | Jun 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | CT2-INTER | CITY TUNNEL #2, REPLACE GUARD VALVES @ 16A | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Jun 2018 | Sep 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | CT2-INTER | CITY TUNNEL #2, REPLACE GUARD VALVES @ 16A | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Sep 2018 | Jan 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | CT2-INTER | CITY TUNNEL #2, REPLACE GUARD VALVES @ 16A | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Jan 2019 | May 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | CT2-INTER | CITY TUNNEL #2, REPLACE GUARD VALVES @ 16A | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | May 2019 | Sep 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | CT2-INTER | CITY TUNNEL #2, REPLACE GUARD VALVES @ 16A | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Jun 2019 | Sep 2019 | Sep 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | CT2-INTER | CITY TUNNEL #2, REPLACE GUARD VALVES @ 16A | 9 | SUBSTANTIAL COMPLETION | Jun 2019 | Sep 2019 | Sep 2019 | Dec 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | CT2-INTER | CITY TUNNEL #2, REPLACE GUARD VALVES @ 16A | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Oct 2019 | Dec 2019 | Mar 2028
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-GUN22 | Emergency Guniting of Sewers, Citywide | 1 | DEVELOP SCOPE | Nov 2020 | Feb 2021 | Nov 2020 | Feb 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-GUN22 | Emergency Guniting of Sewers, Citywide | 2 | PRELIMINARY DESIGN | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-GUN22 | Emergency Guniting of Sewers, Citywide | 3 | FINAL DESIGN | Jun 2021 | Dec 2021 | Jun 2021 | Dec 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-GUN22 | Emergency Guniting of Sewers, Citywide | 4 | BID AWARD AND REGISTER CONTRCT | Dec 2021 | Mar 2022 | Dec 2021 | Mar 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-GUN22 | Emergency Guniting of Sewers, Citywide | 5 | CONSTRUCTION TO 25% | Mar 2022 | Jul 2022 | Mar 2022 | Jul 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-GUN22 | Emergency Guniting of Sewers, Citywide | 6 | CONSTRUCTION TO 50% | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-GUN22 | Emergency Guniting of Sewers, Citywide | 7 | CONSTRUCTION TO 75% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-GUN22 | Emergency Guniting of Sewers, Citywide | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2023 | May 2023 | Feb 2023 | May 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-GUN22 | Emergency Guniting of Sewers, Citywide | 9 | SUBSTANTIAL COMPLETION | May 2023 | Jul 2023 | May 2023 | Jul 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-GUN22 | Emergency Guniting of Sewers, Citywide | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-GUN24 | Emergency Guniting of Sewers, Citywide | 1 | DEVELOP SCOPE | Jun 2024 | Aug 2024 | Jun 2024 | Aug 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-GUN24 | Emergency Guniting of Sewers, Citywide | 2 | PRELIMINARY DESIGN | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-GUN24 | Emergency Guniting of Sewers, Citywide | 3 | FINAL DESIGN | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-GUN24 | Emergency Guniting of Sewers, Citywide | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-GUN24 | Emergency Guniting of Sewers, Citywide | 5 | CONSTRUCTION TO 25% | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-GUN24 | Emergency Guniting of Sewers, Citywide | 6 | CONSTRUCTION TO 50% | Jan 2026 | May 2026 | Jan 2026 | May 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-GUN24 | Emergency Guniting of Sewers, Citywide | 7 | CONSTRUCTION TO 75% | May 2026 | Sep 2026 | May 2026 | Sep 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-GUN24 | Emergency Guniting of Sewers, Citywide | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2026 | Dec 2026 | Sep 2026 | Dec 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-GUN24 | Emergency Guniting of Sewers, Citywide | 9 | SUBSTANTIAL COMPLETION | Dec 2026 | Feb 2027 | Dec 2026 | Feb 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-GUN24 | Emergency Guniting of Sewers, Citywide | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2027 | Mar 2027 | Feb 2027 | Mar 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-LC24 | Emergency Sewer Lining Contract, Citywide | 1 | DEVELOP SCOPE | Jun 2024 | Aug 2024 | Jun 2024 | Aug 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-LC24 | Emergency Sewer Lining Contract, Citywide | 2 | PRELIMINARY DESIGN | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-LC24 | Emergency Sewer Lining Contract, Citywide | 3 | FINAL DESIGN | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-LC24 | Emergency Sewer Lining Contract, Citywide | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-LC24 | Emergency Sewer Lining Contract, Citywide | 5 | CONSTRUCTION TO 25% | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-LC24 | Emergency Sewer Lining Contract, Citywide | 6 | CONSTRUCTION TO 50% | Jan 2026 | May 2026 | Jan 2026 | May 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-LC24 | Emergency Sewer Lining Contract, Citywide | 7 | CONSTRUCTION TO 75% | May 2026 | Sep 2026 | May 2026 | Sep 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-LC24 | Emergency Sewer Lining Contract, Citywide | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2026 | Dec 2026 | Sep 2026 | Dec 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-LC24 | Emergency Sewer Lining Contract, Citywide | 9 | SUBSTANTIAL COMPLETION | Dec 2026 | Feb 2027 | Dec 2026 | Feb 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-LC24 | Emergency Sewer Lining Contract, Citywide | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2027 | Mar 2027 | Feb 2027 | Mar 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEC24 | Emergency Construction of Sewers, Citywide | 1 | DEVELOP SCOPE | Jun 2024 | Aug 2024 | Jun 2024 | Aug 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEC24 | Emergency Construction of Sewers, Citywide | 2 | PRELIMINARY DESIGN | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEC24 | Emergency Construction of Sewers, Citywide | 3 | FINAL DESIGN | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEC24 | Emergency Construction of Sewers, Citywide | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEC24 | Emergency Construction of Sewers, Citywide | 5 | CONSTRUCTION TO 25% | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEC24 | Emergency Construction of Sewers, Citywide | 6 | CONSTRUCTION TO 50% | Jan 2026 | May 2026 | Jan 2026 | May 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEC24 | Emergency Construction of Sewers, Citywide | 7 | CONSTRUCTION TO 75% | May 2026 | Sep 2026 | May 2026 | Sep 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEC24 | Emergency Construction of Sewers, Citywide | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2026 | Dec 2026 | Sep 2026 | Dec 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEC24 | Emergency Construction of Sewers, Citywide | 9 | SUBSTANTIAL COMPLETION | Dec 2026 | Feb 2027 | Dec 2026 | Feb 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEC24 | Emergency Construction of Sewers, Citywide | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2027 | Mar 2027 | Feb 2027 | Mar 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-WMC24 | Emergency Construction of Water Mains, Citywide | 1 | DEVELOP SCOPE | Jun 2024 | Aug 2024 | Jun 2024 | Aug 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-WMC24 | Emergency Construction of Water Mains, Citywide | 2 | PRELIMINARY DESIGN | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-WMC24 | Emergency Construction of Water Mains, Citywide | 3 | FINAL DESIGN | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-WMC24 | Emergency Construction of Water Mains, Citywide | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-WMC24 | Emergency Construction of Water Mains, Citywide | 5 | CONSTRUCTION TO 25% | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-WMC24 | Emergency Construction of Water Mains, Citywide | 6 | CONSTRUCTION TO 50% | Jan 2026 | May 2026 | Jan 2026 | May 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-WMC24 | Emergency Construction of Water Mains, Citywide | 7 | CONSTRUCTION TO 75% | May 2026 | Sep 2026 | May 2026 | Sep 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-WMC24 | Emergency Construction of Water Mains, Citywide | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2026 | Dec 2026 | Sep 2026 | Dec 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-WMC24 | Emergency Construction of Water Mains, Citywide | 9 | SUBSTANTIAL COMPLETION | Dec 2026 | Feb 2027 | Dec 2026 | Feb 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-WMC24 | Emergency Construction of Water Mains, Citywide | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2027 | Mar 2027 | Feb 2027 | Mar 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | 1 | PROJECT START | Jun 2019 | Jun 2019 | Feb 2018 | May 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | 2 | DESIGN START | Jun 2019 | Jun 2019 | May 2018 | Sep 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | 3 | DESIGN COMPLETION | Jul 2019 | Jul 2019 | Sep 2018 | Mar 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | 4 | CONSTRUCTION START | Jul 2019 | Jul 2019 | Mar 2019 | Sep 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | 5 | CONSTRUCTION COMPLETION | Jul 2019 | Jul 2019 | Sep 2023 | Jan 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | 6 | DEVELOP SCOPE | Jul 2019 | Oct 2019 | Jan 2024 | May 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | 7 | PRELIMINARY DESIGN | Oct 2019 | Jan 2020 | May 2024 | Sep 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | 8 | FINAL DESIGN | Jan 2020 | Jul 2020 | Sep 2024 | Dec 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | 9 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Dec 2024 | May 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | 10 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | May 2025 | Jun 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | 11 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | May 2025 | Jun 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | 12 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | May 2025 | Jun 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | 13 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | May 2025 | Jun 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | 14 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | May 2025 | Jun 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | 15 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | May 2025 | Jun 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-359 | Area-wide Contract for Water Mains | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-359 | Area-wide Contract for Water Mains | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-359 | Area-wide Contract for Water Mains | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-359 | Area-wide Contract for Water Mains | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-359 | Area-wide Contract for Water Mains | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-359 | Area-wide Contract for Water Mains | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-359 | Area-wide Contract for Water Mains | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-359 | Area-wide Contract for Water Mains | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Aug 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CLCC | CAMP LAGUARDIA CODE COMPLIANCE | 1 | PROJECT START | Feb 1989 | Feb 1989 | Feb 1989 | Feb 1989
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CLCC | CAMP LAGUARDIA CODE COMPLIANCE | 2 | DESIGN START | Feb 1989 | Feb 1989 | Feb 1989 | Feb 1989
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CLCC | CAMP LAGUARDIA CODE COMPLIANCE | 3 | DESIGN COMPLETION | Feb 1989 | Feb 1989 | Feb 1989 | Feb 1989
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CLCC | CAMP LAGUARDIA CODE COMPLIANCE | 4 | CONSTRUCTION START | Feb 1989 | Aug 1995 | Feb 1989 | Aug 1995
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CLCC | CAMP LAGUARDIA CODE COMPLIANCE | 5 | CONSTRUCTION COMPLETION | Oct 1996 | Jun 2004 | Oct 1996 | Jun 2004
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25FACA4 | FACADE RESTORATION MULTIPLE SITES | 1 | PROJECT START | Sep 2018 | Sep 2018 | Sep 2018 | Feb 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25FACA4 | FACADE RESTORATION MULTIPLE SITES | 2 | DESIGN START | Sep 2018 | Sep 2018 | Feb 2020 | Nov 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25FACA4 | FACADE RESTORATION MULTIPLE SITES | 3 | DESIGN COMPLETION | Oct 2018 | Oct 2018 | Nov 2022 | Nov 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25FACA4 | FACADE RESTORATION MULTIPLE SITES | 4 | CONSTRUCTION START | Oct 2018 | Aug 2020 | Nov 2022 | Sep 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25FACA4 | FACADE RESTORATION MULTIPLE SITES | 5 | CONSTRUCTION COMPLETION | Aug 2020 | Aug 2022 | Sep 2024 | Aug 2028
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCRCDB | RAISED CROSSWALKS DESIGN BUILD | 1 | PROJECT START | Nov 2022 | Nov 2022 | Nov 2022 | Nov 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCRCDB | RAISED CROSSWALKS DESIGN BUILD | 2 | DESIGN START | Nov 2022 | Dec 2023 | Nov 2022 | Dec 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCRCDB | RAISED CROSSWALKS DESIGN BUILD | 3 | DESIGN COMPLETION | Dec 2023 | Aug 2024 | Dec 2023 | Aug 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCRCDB | RAISED CROSSWALKS DESIGN BUILD | 4 | CONSTRUCTION START | Aug 2024 | Jul 2027 | Aug 2024 | Jul 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCRCDB | RAISED CROSSWALKS DESIGN BUILD | 5 | CONSTRUCTION COMPLETION | Sep 2021 | Sep 2027 | Sep 2021 | Sep 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3A | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 1 | DEVELOP SCOPE | Feb 2008 | May 2008 | Feb 2008 | May 2008
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3A | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 2 | PRELIMINARY DESIGN | May 2008 | Sep 2008 | May 2008 | Sep 2008
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3A | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 3 | FINAL DESIGN | Sep 2008 | Mar 2009 | Sep 2008 | Mar 2009
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3A | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2009 | Jun 2009 | Nov 2010 | Feb 2011
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3A | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 5 | CONSTRUCTION TO 25% | Jun 2009 | Oct 2009 | Feb 2011 | Feb 2011
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3A | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 6 | CONSTRUCTION TO 50% | Oct 2009 | Feb 2010 | Feb 2011 | Feb 2011
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3A | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 7 | CONSTRUCTION TO 75% | Feb 2010 | Jun 2010 | Feb 2011 | Feb 2011
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3A | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2010 | Sep 2010 | Feb 2011 | Feb 2011
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3A | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 9 | SUBSTANTIAL COMPLETION | Sep 2010 | Nov 2010 | Feb 2011 | Feb 2011
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3A | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2010 | Dec 2010 | Nov 2013 | Jul 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3B2 | SAFE ROUTES TO SCHOOLS - PHASE 3B2 | 1 | DEVELOP SCOPE | Mar 2014 | May 2014 | Aug 2008 | Apr 2010
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3B2 | SAFE ROUTES TO SCHOOLS - PHASE 3B2 | 2 | PRELIMINARY DESIGN | May 2014 | Sep 2014 | Apr 2010 | Jan 2013
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3B2 | SAFE ROUTES TO SCHOOLS - PHASE 3B2 | 3 | FINAL DESIGN | Sep 2014 | Mar 2015 | Jan 2013 | Jun 2013
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3B2 | SAFE ROUTES TO SCHOOLS - PHASE 3B2 | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2015 | Jun 2015 | Jul 2013 | Apr 2015
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3B2 | SAFE ROUTES TO SCHOOLS - PHASE 3B2 | 5 | CONSTRUCTION TO 25% | Jun 2015 | Oct 2015 | Apr 2015 | Aug 2015
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3B2 | SAFE ROUTES TO SCHOOLS - PHASE 3B2 | 6 | CONSTRUCTION TO 50% | Oct 2015 | Feb 2016 | Aug 2015 | Dec 2015
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3B2 | SAFE ROUTES TO SCHOOLS - PHASE 3B2 | 7 | CONSTRUCTION TO 75% | Feb 2016 | Jun 2016 | Dec 2015 | Apr 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3B2 | SAFE ROUTES TO SCHOOLS - PHASE 3B2 | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2016 | Sep 2016 | Apr 2016 | Jul 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3B2 | SAFE ROUTES TO SCHOOLS - PHASE 3B2 | 9 | SUBSTANTIAL COMPLETION | Sep 2016 | Nov 2016 | Jul 2016 | Feb 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3B2 | SAFE ROUTES TO SCHOOLS - PHASE 3B2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2016 | Dec 2016 | Feb 2018 | Jan 2029
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3B3 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 1 | DEVELOP SCOPE | Dec 2012 | Mar 2013 | Dec 2012 | Mar 2013
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3B3 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 2 | PRELIMINARY DESIGN | Mar 2013 | Jul 2013 | Mar 2013 | Jul 2013
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3B3 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 3 | FINAL DESIGN | Jul 2013 | Jan 2014 | Jul 2013 | Jan 2014
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3B3 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2014 | Apr 2014 | Jan 2014 | Apr 2014
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3B3 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 5 | CONSTRUCTION TO 25% | Apr 2014 | Aug 2014 | Apr 2014 | Aug 2014
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3B3 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 6 | CONSTRUCTION TO 50% | Aug 2014 | Dec 2014 | Aug 2014 | Dec 2014
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3B3 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 7 | CONSTRUCTION TO 75% | Dec 2014 | Apr 2015 | Dec 2014 | Apr 2015
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3B3 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2015 | Jul 2015 | Apr 2015 | Jul 2015
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3B3 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 9 | SUBSTANTIAL COMPLETION | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3B3 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2015 | Oct 2015 | Sep 2015 | Jun 2032
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3E | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 1 | DEVELOP SCOPE | Feb 2009 | May 2009 | Jul 2011 | Sep 2011
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3E | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 2 | PRELIMINARY DESIGN | May 2009 | Sep 2009 | Sep 2011 | Jan 2012
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3E | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 3 | FINAL DESIGN | Sep 2009 | Mar 2010 | Jan 2012 | Sep 2013
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3E | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2010 | Jun 2010 | Sep 2013 | Dec 2013
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3E | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 5 | CONSTRUCTION TO 25% | Jun 2010 | Oct 2010 | Dec 2013 | Mar 2014
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3E | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 6 | CONSTRUCTION TO 50% | Oct 2010 | Feb 2011 | Apr 2014 | Jul 2014
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3E | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 7 | CONSTRUCTION TO 75% | Feb 2011 | Jun 2011 | Jul 2014 | Feb 2015
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3E | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2011 | Sep 2011 | Feb 2015 | May 2015
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3E | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 9 | SUBSTANTIAL COMPLETION | Sep 2011 | Nov 2011 | May 2015 | Jul 2015
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3E | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2011 | Dec 2011 | Jul 2015 | Dec 2031
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3MM | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 1 | DEVELOP SCOPE | Feb 2014 | May 2014 | Feb 2014 | May 2014
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3MM | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 2 | PRELIMINARY DESIGN | May 2014 | Sep 2014 | May 2014 | Sep 2014
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3MM | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 3 | FINAL DESIGN | Sep 2014 | Mar 2015 | Sep 2014 | Mar 2015
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3MM | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2015 | Jun 2015 | Mar 2015 | Jun 2015
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3MM | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 5 | CONSTRUCTION TO 25% | Jun 2015 | Oct 2015 | Jun 2015 | Oct 2015
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3MM | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 6 | CONSTRUCTION TO 50% | Oct 2015 | Feb 2016 | Oct 2015 | Feb 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3MM | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 7 | CONSTRUCTION TO 75% | Feb 2016 | Jun 2016 | Feb 2016 | Jun 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3MM | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2016 | Sep 2016 | Jun 2016 | Sep 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3MM | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 9 | SUBSTANTIAL COMPLETION | Sep 2016 | Nov 2016 | Sep 2016 | Nov 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3MM | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2016 | Dec 2016 | Nov 2016 | Jun 2032
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4B1 | Safe Routes to Schools - Phase 4B1 | 1 | DEVELOP SCOPE | Feb 2015 | May 2015 | Sep 2013 | Dec 2013
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4B1 | Safe Routes to Schools - Phase 4B1 | 2 | PRELIMINARY DESIGN | May 2015 | Sep 2015 | Dec 2013 | Jul 2014
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4B1 | Safe Routes to Schools - Phase 4B1 | 3 | FINAL DESIGN | Sep 2015 | Mar 2016 | Jul 2014 | Oct 2015
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4B1 | Safe Routes to Schools - Phase 4B1 | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2016 | Jun 2016 | Oct 2015 | Oct 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4B1 | Safe Routes to Schools - Phase 4B1 | 5 | CONSTRUCTION TO 25% | Jun 2016 | Oct 2016 | Oct 2016 | Feb 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4B1 | Safe Routes to Schools - Phase 4B1 | 6 | CONSTRUCTION TO 50% | Oct 2016 | Feb 2017 | Feb 2017 | Jun 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4B1 | Safe Routes to Schools - Phase 4B1 | 7 | CONSTRUCTION TO 75% | Feb 2017 | Jun 2017 | Jun 2017 | Oct 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4B1 | Safe Routes to Schools - Phase 4B1 | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2017 | Sep 2017 | Oct 2017 | Apr 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4B1 | Safe Routes to Schools - Phase 4B1 | 9 | SUBSTANTIAL COMPLETION | Sep 2017 | Nov 2017 | Apr 2018 | Jun 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4B1 | Safe Routes to Schools - Phase 4B1 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | Dec 2017 | Jun 2018 | Feb 2032
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C2 | Safe Routes to Schools - Phase 4C2 | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2017 | Sep 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C2 | Safe Routes to Schools - Phase 4C2 | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2017 | Jan 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C2 | Safe Routes to Schools - Phase 4C2 | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jan 2018 | Jul 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C2 | Safe Routes to Schools - Phase 4C2 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2018 | Oct 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C2 | Safe Routes to Schools - Phase 4C2 | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C2 | Safe Routes to Schools - Phase 4C2 | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C2 | Safe Routes to Schools - Phase 4C2 | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jun 2019 | Oct 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C2 | Safe Routes to Schools - Phase 4C2 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Oct 2019 | Jan 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C2 | Safe Routes to Schools - Phase 4C2 | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jan 2020 | Mar 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C2 | Safe Routes to Schools - Phase 4C2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Mar 2020 | Jul 2032
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4D | Safe Routes to Schools - Phase 4D, NDF-SCH4D (HED582) | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2018 | Sep 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4D | Safe Routes to Schools - Phase 4D, NDF-SCH4D (HED582) | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2018 | Jan 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4D | Safe Routes to Schools - Phase 4D, NDF-SCH4D (HED582) | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jan 2019 | Jul 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4D | Safe Routes to Schools - Phase 4D, NDF-SCH4D (HED582) | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2019 | Oct 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4D | Safe Routes to Schools - Phase 4D, NDF-SCH4D (HED582) | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Oct 2019 | Feb 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4D | Safe Routes to Schools - Phase 4D, NDF-SCH4D (HED582) | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Feb 2020 | Jun 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4D | Safe Routes to Schools - Phase 4D, NDF-SCH4D (HED582) | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jun 2020 | Oct 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4D | Safe Routes to Schools - Phase 4D, NDF-SCH4D (HED582) | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Oct 2020 | Jan 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4D | Safe Routes to Schools - Phase 4D, NDF-SCH4D (HED582) | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jan 2021 | Mar 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4D | Safe Routes to Schools - Phase 4D, NDF-SCH4D (HED582) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Mar 2021 | Jun 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPKR | Safe Routes to Schools - Brooklyn & Staten Island | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPKR | Safe Routes to Schools - Brooklyn & Staten Island | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPKR | Safe Routes to Schools - Brooklyn & Staten Island | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPKR | Safe Routes to Schools - Brooklyn & Staten Island | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPKR | Safe Routes to Schools - Brooklyn & Staten Island | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPKR | Safe Routes to Schools - Brooklyn & Staten Island | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPKR | Safe Routes to Schools - Brooklyn & Staten Island | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPKR | Safe Routes to Schools - Brooklyn & Staten Island | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPKR | Safe Routes to Schools - Brooklyn & Staten Island | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPKR | Safe Routes to Schools - Brooklyn & Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Jun 2023 | Nov 2019 | Jun 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPKR | Safe Routes to Schools - Brooklyn & Staten Island | 11 | PROJECT START | Nov 2019 | Jun 2023 | Jul 2023 | Jul 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPKR | Safe Routes to Schools - Brooklyn & Staten Island | 12 | DESIGN START | Nov 2019 | Jun 2023 | Jul 2023 | Jul 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPKR | Safe Routes to Schools - Brooklyn & Staten Island | 13 | DESIGN COMPLETION | Nov 2019 | Jun 2023 | Jul 2023 | Jul 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPKR | Safe Routes to Schools - Brooklyn & Staten Island | 14 | CONSTRUCTION START | Nov 2019 | Jun 2023 | Jul 2023 | Jul 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPKR | Safe Routes to Schools - Brooklyn & Staten Island | 15 | CONSTRUCTION COMPLETION | Nov 2019 | Jun 2023 | Jul 2023 | Jul 2031
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPMN | SAFE ROUTES TO SCHOOLS- MANHATTAN, MED683 | 1 | DEVELOP SCOPE | Mar 2019 | May 2019 | Mar 2019 | May 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPMN | SAFE ROUTES TO SCHOOLS- MANHATTAN, MED683 | 2 | PRELIMINARY DESIGN | May 2019 | Sep 2019 | May 2019 | Sep 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPMN | SAFE ROUTES TO SCHOOLS- MANHATTAN, MED683 | 3 | FINAL DESIGN | Sep 2019 | Mar 2020 | Sep 2019 | Mar 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPMN | SAFE ROUTES TO SCHOOLS- MANHATTAN, MED683 | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Jun 2020 | Mar 2020 | Jun 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPMN | SAFE ROUTES TO SCHOOLS- MANHATTAN, MED683 | 5 | CONSTRUCTION TO 25% | Jun 2020 | Oct 2020 | Jun 2020 | Oct 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPMN | SAFE ROUTES TO SCHOOLS- MANHATTAN, MED683 | 6 | CONSTRUCTION TO 50% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPMN | SAFE ROUTES TO SCHOOLS- MANHATTAN, MED683 | 7 | CONSTRUCTION TO 75% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPMN | SAFE ROUTES TO SCHOOLS- MANHATTAN, MED683 | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPMN | SAFE ROUTES TO SCHOOLS- MANHATTAN, MED683 | 9 | SUBSTANTIAL COMPLETION | Sep 2021 | Nov 2021 | Sep 2021 | Nov 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPMN | SAFE ROUTES TO SCHOOLS- MANHATTAN, MED683 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2021 | Dec 2021 | Nov 2021 | Jul 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCURB10 | Curb Reconstruction | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCURB10 | Curb Reconstruction | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCURB10 | Curb Reconstruction | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCURB10 | Curb Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCURB10 | Curb Reconstruction | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCURB10 | Curb Reconstruction | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCURB10 | Curb Reconstruction | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCURB10 | Curb Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCURB10 | Curb Reconstruction | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCURB10 | Curb Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15XMCL | Simple, Complex & Landmark Ped Ramps - Bronx and Manhattan | 1 | DEVELOP SCOPE | Feb 2015 | May 2015 | Jun 2014 | Sep 2014
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15XMCL | Simple, Complex & Landmark Ped Ramps - Bronx and Manhattan | 2 | PRELIMINARY DESIGN | May 2015 | Sep 2015 | Sep 2014 | Apr 2015
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15XMCL | Simple, Complex & Landmark Ped Ramps - Bronx and Manhattan | 3 | FINAL DESIGN | Sep 2015 | Mar 2016 | Apr 2015 | Dec 2015
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15XMCL | Simple, Complex & Landmark Ped Ramps - Bronx and Manhattan | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2016 | Jun 2016 | Jan 2016 | Mar 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15XMCL | Simple, Complex & Landmark Ped Ramps - Bronx and Manhattan | 5 | CONSTRUCTION TO 25% | Jun 2016 | Oct 2016 | Mar 2017 | Jul 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15XMCL | Simple, Complex & Landmark Ped Ramps - Bronx and Manhattan | 6 | CONSTRUCTION TO 50% | Oct 2016 | Feb 2017 | Jul 2017 | Nov 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15XMCL | Simple, Complex & Landmark Ped Ramps - Bronx and Manhattan | 7 | CONSTRUCTION TO 75% | Feb 2017 | Jun 2017 | Nov 2017 | Mar 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15XMCL | Simple, Complex & Landmark Ped Ramps - Bronx and Manhattan | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2017 | Sep 2017 | Mar 2018 | Jun 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15XMCL | Simple, Complex & Landmark Ped Ramps - Bronx and Manhattan | 9 | SUBSTANTIAL COMPLETION | Sep 2017 | Nov 2017 | Jun 2018 | Aug 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15XMCL | Simple, Complex & Landmark Ped Ramps - Bronx and Manhattan | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | Dec 2017 | Aug 2018 | May 2033
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19CWLM | CITYWIDE COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2017 | Sep 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19CWLM | CITYWIDE COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2017 | Jun 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19CWLM | CITYWIDE COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jul 2018 | Jun 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19CWLM | CITYWIDE COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2019 | Dec 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19CWLM | CITYWIDE COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Jan 2020 | Apr 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19CWLM | CITYWIDE COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Apr 2020 | Aug 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19CWLM | CITYWIDE COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Aug 2020 | Dec 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19CWLM | CITYWIDE COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Dec 2020 | Mar 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19CWLM | CITYWIDE COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Mar 2021 | May 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19CWLM | CITYWIDE COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | May 2021 | Jun 2028
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KQTA | CITYWIDE COMPLEX PED RAMPS (TA) - BROOKLYN AND QUEENS | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2017 | Jun 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KQTA | CITYWIDE COMPLEX PED RAMPS (TA) - BROOKLYN AND QUEENS | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Jul 2018 | Dec 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KQTA | CITYWIDE COMPLEX PED RAMPS (TA) - BROOKLYN AND QUEENS | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jan 2019 | Jun 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KQTA | CITYWIDE COMPLEX PED RAMPS (TA) - BROOKLYN AND QUEENS | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2019 | Dec 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KQTA | CITYWIDE COMPLEX PED RAMPS (TA) - BROOKLYN AND QUEENS | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Jan 2020 | Apr 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KQTA | CITYWIDE COMPLEX PED RAMPS (TA) - BROOKLYN AND QUEENS | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Apr 2020 | Aug 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KQTA | CITYWIDE COMPLEX PED RAMPS (TA) - BROOKLYN AND QUEENS | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Aug 2020 | Dec 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KQTA | CITYWIDE COMPLEX PED RAMPS (TA) - BROOKLYN AND QUEENS | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Dec 2020 | Mar 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KQTA | CITYWIDE COMPLEX PED RAMPS (TA) - BROOKLYN AND QUEENS | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Mar 2021 | May 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KQTA | CITYWIDE COMPLEX PED RAMPS (TA) - BROOKLYN AND QUEENS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | May 2021 | Jun 2033
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19QRC | Citywide Complex Pedestrian Ramps - Queens and Staten Island | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Mar 2021 | May 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19QRC | Citywide Complex Pedestrian Ramps - Queens and Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | May 2021 | Jun 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2019S | Citywide Simple Pedestrian Ramps | 3 | FINAL DESIGN | Nov 2018 | May 2019 | Nov 2018 | May 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2019S | Citywide Simple Pedestrian Ramps | 4 | BID AWARD AND REGISTER CONTRCT | May 2019 | Aug 2019 | May 2019 | Aug 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2019S | Citywide Simple Pedestrian Ramps | 5 | CONSTRUCTION TO 25% | Aug 2019 | Dec 2019 | Aug 2019 | Dec 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2019S | Citywide Simple Pedestrian Ramps | 6 | CONSTRUCTION TO 50% | Dec 2019 | Apr 2020 | Dec 2019 | Apr 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2019S | Citywide Simple Pedestrian Ramps | 7 | CONSTRUCTION TO 75% | Apr 2020 | Aug 2020 | Apr 2020 | Aug 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2019S | Citywide Simple Pedestrian Ramps | 8 | ORIGINAL EQUIP & FURNISHING | Aug 2020 | Nov 2020 | Aug 2020 | Nov 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2019S | Citywide Simple Pedestrian Ramps | 9 | SUBSTANTIAL COMPLETION | Nov 2020 | Dec 2020 | Nov 2020 | Dec 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2019S | Citywide Simple Pedestrian Ramps | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2021 | Jan 2021 | Jan 2021 | Jun 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020LM | Non-Standard Ped Ramp Installs - Citywide Landmark Locations | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020LM | Non-Standard Ped Ramp Installs - Citywide Landmark Locations | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020LM | Non-Standard Ped Ramp Installs - Citywide Landmark Locations | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020LM | Non-Standard Ped Ramp Installs - Citywide Landmark Locations | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020LM | Non-Standard Ped Ramp Installs - Citywide Landmark Locations | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020LM | Non-Standard Ped Ramp Installs - Citywide Landmark Locations | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020LM | Non-Standard Ped Ramp Installs - Citywide Landmark Locations | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020LM | Non-Standard Ped Ramp Installs - Citywide Landmark Locations | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020LM | Non-Standard Ped Ramp Installs - Citywide Landmark Locations | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020LM | Non-Standard Ped Ramp Installs - Citywide Landmark Locations | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Jun 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020TA | Non-Standard Ped Ramp Installs - Manh, Brnx, Bk, & Queens | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020TA | Non-Standard Ped Ramp Installs - Manh, Brnx, Bk, & Queens | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020TA | Non-Standard Ped Ramp Installs - Manh, Brnx, Bk, & Queens | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020TA | Non-Standard Ped Ramp Installs - Manh, Brnx, Bk, & Queens | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020TA | Non-Standard Ped Ramp Installs - Manh, Brnx, Bk, & Queens | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020TA | Non-Standard Ped Ramp Installs - Manh, Brnx, Bk, & Queens | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020TA | Non-Standard Ped Ramp Installs - Manh, Brnx, Bk, & Queens | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020TA | Non-Standard Ped Ramp Installs - Manh, Brnx, Bk, & Queens | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020TA | Non-Standard Ped Ramp Installs - Manh, Brnx, Bk, & Queens | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020TA | Non-Standard Ped Ramp Installs - Manh, Brnx, Bk, & Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Jun 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021LM | Non-Standard Installs - Landmark | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2022 | Sep 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021LM | Non-Standard Installs - Landmark | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2022 | Jan 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021LM | Non-Standard Installs - Landmark | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2023 | Jul 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021LM | Non-Standard Installs - Landmark | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2023 | Oct 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021LM | Non-Standard Installs - Landmark | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2023 | Feb 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021LM | Non-Standard Installs - Landmark | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2024 | Jun 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021LM | Non-Standard Installs - Landmark | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2024 | Oct 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021LM | Non-Standard Installs - Landmark | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2024 | Jan 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021LM | Non-Standard Installs - Landmark | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2025 | Mar 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021LM | Non-Standard Installs - Landmark | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2025 | Apr 2033
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021TA | Non-Standard Installs - TA | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2023 | Sep 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021TA | Non-Standard Installs - TA | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2023 | Jan 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021TA | Non-Standard Installs - TA | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2024 | Jul 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021TA | Non-Standard Installs - TA | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2024 | Oct 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021TA | Non-Standard Installs - TA | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2024 | Feb 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021TA | Non-Standard Installs - TA | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2025 | Jun 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021TA | Non-Standard Installs - TA | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2025 | Oct 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021TA | Non-Standard Installs - TA | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2025 | Jan 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021TA | Non-Standard Installs - TA | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2026 | Mar 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021TA | Non-Standard Installs - TA | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2026 | Apr 2033
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2024S | Standard Pedestrian Ramp Installations - Unramped Locations | 1 | PROJECT START | May 2023 | May 2023 | May 2023 | May 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2024S | Standard Pedestrian Ramp Installations - Unramped Locations | 2 | DESIGN START | May 2023 | Jun 2023 | May 2023 | Jun 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2024S | Standard Pedestrian Ramp Installations - Unramped Locations | 3 | DESIGN COMPLETION | Jun 2023 | Nov 2023 | Jun 2023 | Nov 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2024S | Standard Pedestrian Ramp Installations - Unramped Locations | 4 | CONSTRUCTION START | Nov 2023 | Jul 2025 | Nov 2023 | Jul 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2024S | Standard Pedestrian Ramp Installations - Unramped Locations | 5 | CONSTRUCTION COMPLETION | Jul 2025 | Nov 2028 | Jul 2025 | Nov 2033
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20KRC | Non-Standard Ped Ramp Installs - Brooklyn & Staten Island | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20KRC | Non-Standard Ped Ramp Installs - Brooklyn & Staten Island | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20KRC | Non-Standard Ped Ramp Installs - Brooklyn & Staten Island | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20KRC | Non-Standard Ped Ramp Installs - Brooklyn & Staten Island | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20KRC | Non-Standard Ped Ramp Installs - Brooklyn & Staten Island | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20KRC | Non-Standard Ped Ramp Installs - Brooklyn & Staten Island | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20KRC | Non-Standard Ped Ramp Installs - Brooklyn & Staten Island | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20KRC | Non-Standard Ped Ramp Installs - Brooklyn & Staten Island | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20KRC | Non-Standard Ped Ramp Installs - Brooklyn & Staten Island | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20KRC | Non-Standard Ped Ramp Installs - Brooklyn & Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2024 | Jun 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MKC | Non-Standard Ped Ramp Installs - Manhattan & Brooklyn | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MKC | Non-Standard Ped Ramp Installs - Manhattan & Brooklyn | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MKC | Non-Standard Ped Ramp Installs - Manhattan & Brooklyn | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MKC | Non-Standard Ped Ramp Installs - Manhattan & Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MKC | Non-Standard Ped Ramp Installs - Manhattan & Brooklyn | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MKC | Non-Standard Ped Ramp Installs - Manhattan & Brooklyn | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MKC | Non-Standard Ped Ramp Installs - Manhattan & Brooklyn | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MKC | Non-Standard Ped Ramp Installs - Manhattan & Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MKC | Non-Standard Ped Ramp Installs - Manhattan & Brooklyn | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MKC | Non-Standard Ped Ramp Installs - Manhattan & Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Jun 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MXQC | Non-Standard Ped Ramp Install- Manh,Queens & Bronx -DSGN BLD | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MXQC | Non-Standard Ped Ramp Install- Manh,Queens & Bronx -DSGN BLD | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MXQC | Non-Standard Ped Ramp Install- Manh,Queens & Bronx -DSGN BLD | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MXQC | Non-Standard Ped Ramp Install- Manh,Queens & Bronx -DSGN BLD | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MXQC | Non-Standard Ped Ramp Install- Manh,Queens & Bronx -DSGN BLD | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MXQC | Non-Standard Ped Ramp Install- Manh,Queens & Bronx -DSGN BLD | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MXQC | Non-Standard Ped Ramp Install- Manh,Queens & Bronx -DSGN BLD | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MXQC | Non-Standard Ped Ramp Install- Manh,Queens & Bronx -DSGN BLD | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MXQC | Non-Standard Ped Ramp Install- Manh,Queens & Bronx -DSGN BLD | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MXQC | Non-Standard Ped Ramp Install- Manh,Queens & Bronx -DSGN BLD | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Jun 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21KQC | Non-Standard Installs - Brooklyn and Queens | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2023 | Sep 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21KQC | Non-Standard Installs - Brooklyn and Queens | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2023 | Jan 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21KQC | Non-Standard Installs - Brooklyn and Queens | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2024 | Jul 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21KQC | Non-Standard Installs - Brooklyn and Queens | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2024 | Oct 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21KQC | Non-Standard Installs - Brooklyn and Queens | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2024 | Feb 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21KQC | Non-Standard Installs - Brooklyn and Queens | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2025 | Jun 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21KQC | Non-Standard Installs - Brooklyn and Queens | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2025 | Oct 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21KQC | Non-Standard Installs - Brooklyn and Queens | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2025 | Jan 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21KQC | Non-Standard Installs - Brooklyn and Queens | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2026 | Mar 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21KQC | Non-Standard Installs - Brooklyn and Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2026 | Apr 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21KRC | Non-Standard Installs - Brooklyn and Staten Island | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2022 | Sep 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21KRC | Non-Standard Installs - Brooklyn and Staten Island | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2022 | Jan 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21KRC | Non-Standard Installs - Brooklyn and Staten Island | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2023 | Jul 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21KRC | Non-Standard Installs - Brooklyn and Staten Island | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2023 | Oct 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21KRC | Non-Standard Installs - Brooklyn and Staten Island | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2023 | Feb 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21KRC | Non-Standard Installs - Brooklyn and Staten Island | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2024 | Jun 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21KRC | Non-Standard Installs - Brooklyn and Staten Island | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2024 | Oct 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21KRC | Non-Standard Installs - Brooklyn and Staten Island | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2024 | Jan 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21KRC | Non-Standard Installs - Brooklyn and Staten Island | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2025 | Mar 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21KRC | Non-Standard Installs - Brooklyn and Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2025 | Apr 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21MXQC | Non-Standard Installs - Manhattan, Bronx, Queens | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21MXQC | Non-Standard Installs - Manhattan, Bronx, Queens | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21MXQC | Non-Standard Installs - Manhattan, Bronx, Queens | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21MXQC | Non-Standard Installs - Manhattan, Bronx, Queens | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21MXQC | Non-Standard Installs - Manhattan, Bronx, Queens | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21MXQC | Non-Standard Installs - Manhattan, Bronx, Queens | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21MXQC | Non-Standard Installs - Manhattan, Bronx, Queens | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21MXQC | Non-Standard Installs - Manhattan, Bronx, Queens | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21MXQC | Non-Standard Installs - Manhattan, Bronx, Queens | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2023 | Mar 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21MXQC | Non-Standard Installs - Manhattan, Bronx, Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2023 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21MXQC | Non-Standard Installs - Manhattan, Bronx, Queens | 11 | PROJECT START | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21MXQC | Non-Standard Installs - Manhattan, Bronx, Queens | 12 | DESIGN START | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21MXQC | Non-Standard Installs - Manhattan, Bronx, Queens | 13 | DESIGN COMPLETION | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21MXQC | Non-Standard Installs - Manhattan, Bronx, Queens | 14 | CONSTRUCTION START | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21MXQC | Non-Standard Installs - Manhattan, Bronx, Queens | 15 | CONSTRUCTION COMPLETION | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP22KQC | FY24 Non-Standard Pedestrian Ramp Installs - Brooklyn & Quee | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2024 | Sep 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP22KQC | FY24 Non-Standard Pedestrian Ramp Installs - Brooklyn & Quee | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2024 | Jan 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP22KQC | FY24 Non-Standard Pedestrian Ramp Installs - Brooklyn & Quee | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2025 | Jul 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP22KQC | FY24 Non-Standard Pedestrian Ramp Installs - Brooklyn & Quee | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2025 | Oct 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP22KQC | FY24 Non-Standard Pedestrian Ramp Installs - Brooklyn & Quee | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2025 | Feb 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP22KQC | FY24 Non-Standard Pedestrian Ramp Installs - Brooklyn & Quee | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2026 | Jun 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP22KQC | FY24 Non-Standard Pedestrian Ramp Installs - Brooklyn & Quee | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2026 | Oct 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP22KQC | FY24 Non-Standard Pedestrian Ramp Installs - Brooklyn & Quee | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2026 | Jan 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP22KQC | FY24 Non-Standard Pedestrian Ramp Installs - Brooklyn & Quee | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2027 | Mar 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP22KQC | FY24 Non-Standard Pedestrian Ramp Installs - Brooklyn & Quee | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2027 | Apr 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP22KRC | FY24 Non-Standard Pedestrian Ramp Installs - Brooklyn & SI | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2024 | Sep 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP22KRC | FY24 Non-Standard Pedestrian Ramp Installs - Brooklyn & SI | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2024 | Jan 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP22KRC | FY24 Non-Standard Pedestrian Ramp Installs - Brooklyn & SI | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2025 | Jul 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP22KRC | FY24 Non-Standard Pedestrian Ramp Installs - Brooklyn & SI | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2025 | Oct 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP22KRC | FY24 Non-Standard Pedestrian Ramp Installs - Brooklyn & SI | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2025 | Feb 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP22KRC | FY24 Non-Standard Pedestrian Ramp Installs - Brooklyn & SI | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2026 | Jun 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP22KRC | FY24 Non-Standard Pedestrian Ramp Installs - Brooklyn & SI | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2026 | Oct 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP22KRC | FY24 Non-Standard Pedestrian Ramp Installs - Brooklyn & SI | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2026 | Jan 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP22KRC | FY24 Non-Standard Pedestrian Ramp Installs - Brooklyn & SI | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2027 | Mar 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP22KRC | FY24 Non-Standard Pedestrian Ramp Installs - Brooklyn & SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2027 | Apr 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP22MXQC | FY24 Non-Standard Pedestrian Ramp Installs - Manhattan, Bron | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2024 | Sep 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP22MXQC | FY24 Non-Standard Pedestrian Ramp Installs - Manhattan, Bron | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2024 | Jan 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP22MXQC | FY24 Non-Standard Pedestrian Ramp Installs - Manhattan, Bron | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2025 | Jul 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP22MXQC | FY24 Non-Standard Pedestrian Ramp Installs - Manhattan, Bron | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2025 | Oct 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP22MXQC | FY24 Non-Standard Pedestrian Ramp Installs - Manhattan, Bron | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2025 | Feb 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP22MXQC | FY24 Non-Standard Pedestrian Ramp Installs - Manhattan, Bron | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2026 | Jun 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP22MXQC | FY24 Non-Standard Pedestrian Ramp Installs - Manhattan, Bron | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2026 | Oct 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP22MXQC | FY24 Non-Standard Pedestrian Ramp Installs - Manhattan, Bron | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2026 | Jan 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP22MXQC | FY24 Non-Standard Pedestrian Ramp Installs - Manhattan, Bron | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2027 | Mar 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP22MXQC | FY24 Non-Standard Pedestrian Ramp Installs - Manhattan, Bron | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2027 | Apr 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF1 | Multi-Site Pedestrian Safety | 1 | DEVELOP SCOPE | Jun 2011 | Sep 2011 | Jun 2011 | Oct 2012
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF1 | Multi-Site Pedestrian Safety | 2 | PRELIMINARY DESIGN | Sep 2011 | Jan 2012 | Oct 2012 | Jan 2014
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF1 | Multi-Site Pedestrian Safety | 3 | FINAL DESIGN | Jan 2012 | Jul 2012 | Jan 2014 | Nov 2014
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF1 | Multi-Site Pedestrian Safety | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2012 | Oct 2012 | Nov 2014 | May 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF1 | Multi-Site Pedestrian Safety | 5 | CONSTRUCTION TO 25% | Oct 2012 | Feb 2013 | May 2016 | Oct 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF1 | Multi-Site Pedestrian Safety | 6 | CONSTRUCTION TO 50% | Feb 2013 | Jun 2013 | Oct 2016 | Mar 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF1 | Multi-Site Pedestrian Safety | 7 | CONSTRUCTION TO 75% | Jun 2013 | Oct 2013 | Mar 2017 | Aug 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF1 | Multi-Site Pedestrian Safety | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2013 | Jan 2014 | Aug 2017 | Aug 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF1 | Multi-Site Pedestrian Safety | 9 | SUBSTANTIAL COMPLETION | Jan 2014 | Mar 2014 | Sep 2019 | Nov 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF1 | Multi-Site Pedestrian Safety | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2014 | Apr 2014 | Nov 2019 | Jun 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MXC | Complex Upgrades Ped Ramps - Manhattan and the Bronx | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MXC | Complex Upgrades Ped Ramps - Manhattan and the Bronx | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MXC | Complex Upgrades Ped Ramps - Manhattan and the Bronx | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MXC | Complex Upgrades Ped Ramps - Manhattan and the Bronx | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MXC | Complex Upgrades Ped Ramps - Manhattan and the Bronx | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MXC | Complex Upgrades Ped Ramps - Manhattan and the Bronx | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MXC | Complex Upgrades Ped Ramps - Manhattan and the Bronx | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MXC | Complex Upgrades Ped Ramps - Manhattan and the Bronx | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MXC | Complex Upgrades Ped Ramps - Manhattan and the Bronx | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MXC | Complex Upgrades Ped Ramps - Manhattan and the Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Jun 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19QRC | Complex Upgrades Ped Ramps - Queens and Staten Island | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19QRC | Complex Upgrades Ped Ramps - Queens and Staten Island | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19QRC | Complex Upgrades Ped Ramps - Queens and Staten Island | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19QRC | Complex Upgrades Ped Ramps - Queens and Staten Island | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19QRC | Complex Upgrades Ped Ramps - Queens and Staten Island | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19QRC | Complex Upgrades Ped Ramps - Queens and Staten Island | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19QRC | Complex Upgrades Ped Ramps - Queens and Staten Island | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19QRC | Complex Upgrades Ped Ramps - Queens and Staten Island | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19QRC | Complex Upgrades Ped Ramps - Queens and Staten Island | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19QRC | Complex Upgrades Ped Ramps - Queens and Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2023 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19QRC | Complex Upgrades Ped Ramps - Queens and Staten Island | 11 | PROJECT START | Mar 2022 | Apr 2022 | Apr 2023 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19QRC | Complex Upgrades Ped Ramps - Queens and Staten Island | 12 | DESIGN START | Mar 2022 | Apr 2022 | Apr 2023 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19QRC | Complex Upgrades Ped Ramps - Queens and Staten Island | 13 | DESIGN COMPLETION | Mar 2022 | Apr 2022 | Apr 2023 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19QRC | Complex Upgrades Ped Ramps - Queens and Staten Island | 14 | CONSTRUCTION START | Mar 2022 | Apr 2022 | Apr 2023 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19QRC | Complex Upgrades Ped Ramps - Queens and Staten Island | 15 | CONSTRUCTION COMPLETION | Mar 2022 | Apr 2022 | Apr 2023 | Apr 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KMC | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KMC | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KMC | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KMC | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KMC | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KMC | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KMC | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KMC | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KMC | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KMC | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Jun 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKL | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKL | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKL | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKL | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKL | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKL | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKL | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKL | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKL | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKL | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Jun 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKL | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 11 | PROJECT START | Mar 2022 | Apr 2022 | Jul 2023 | Jul 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKL | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 12 | DESIGN START | Mar 2022 | Apr 2022 | Jul 2023 | Jul 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKL | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 13 | DESIGN COMPLETION | Mar 2022 | Apr 2022 | Jul 2023 | Jul 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKL | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 14 | CONSTRUCTION START | Mar 2022 | Apr 2022 | Jul 2023 | Jul 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKL | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | 15 | CONSTRUCTION COMPLETION | Mar 2022 | Apr 2022 | Jul 2023 | Jul 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKT | Non-Standard Upgrades Ped Ramp - TA Manhattan & Brooklyn | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKT | Non-Standard Upgrades Ped Ramp - TA Manhattan & Brooklyn | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKT | Non-Standard Upgrades Ped Ramp - TA Manhattan & Brooklyn | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKT | Non-Standard Upgrades Ped Ramp - TA Manhattan & Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKT | Non-Standard Upgrades Ped Ramp - TA Manhattan & Brooklyn | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKT | Non-Standard Upgrades Ped Ramp - TA Manhattan & Brooklyn | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKT | Non-Standard Upgrades Ped Ramp - TA Manhattan & Brooklyn | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKT | Non-Standard Upgrades Ped Ramp - TA Manhattan & Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKT | Non-Standard Upgrades Ped Ramp - TA Manhattan & Brooklyn | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKT | Non-Standard Upgrades Ped Ramp - TA Manhattan & Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Jun 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQC | Non-Standard Upgrades Ped Ramp - Manhattan & Queens | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQC | Non-Standard Upgrades Ped Ramp - Manhattan & Queens | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQC | Non-Standard Upgrades Ped Ramp - Manhattan & Queens | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQC | Non-Standard Upgrades Ped Ramp - Manhattan & Queens | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQC | Non-Standard Upgrades Ped Ramp - Manhattan & Queens | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQC | Non-Standard Upgrades Ped Ramp - Manhattan & Queens | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQC | Non-Standard Upgrades Ped Ramp - Manhattan & Queens | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQC | Non-Standard Upgrades Ped Ramp - Manhattan & Queens | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQC | Non-Standard Upgrades Ped Ramp - Manhattan & Queens | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQC | Non-Standard Upgrades Ped Ramp - Manhattan & Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Jun 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQX | Non-Standard Upgrades Ped Ramp - TA Manhattan,Queens,&Bronx | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQX | Non-Standard Upgrades Ped Ramp - TA Manhattan,Queens,&Bronx | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQX | Non-Standard Upgrades Ped Ramp - TA Manhattan,Queens,&Bronx | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQX | Non-Standard Upgrades Ped Ramp - TA Manhattan,Queens,&Bronx | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQX | Non-Standard Upgrades Ped Ramp - TA Manhattan,Queens,&Bronx | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQX | Non-Standard Upgrades Ped Ramp - TA Manhattan,Queens,&Bronx | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQX | Non-Standard Upgrades Ped Ramp - TA Manhattan,Queens,&Bronx | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQX | Non-Standard Upgrades Ped Ramp - TA Manhattan,Queens,&Bronx | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQX | Non-Standard Upgrades Ped Ramp - TA Manhattan,Queens,&Bronx | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQX | Non-Standard Upgrades Ped Ramp - TA Manhattan,Queens,&Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Jun 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MXC | Non-Standard Upgrades Ped Ramp - Manhattan & Bronx | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MXC | Non-Standard Upgrades Ped Ramp - Manhattan & Bronx | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MXC | Non-Standard Upgrades Ped Ramp - Manhattan & Bronx | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MXC | Non-Standard Upgrades Ped Ramp - Manhattan & Bronx | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MXC | Non-Standard Upgrades Ped Ramp - Manhattan & Bronx | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MXC | Non-Standard Upgrades Ped Ramp - Manhattan & Bronx | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MXC | Non-Standard Upgrades Ped Ramp - Manhattan & Bronx | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MXC | Non-Standard Upgrades Ped Ramp - Manhattan & Bronx | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MXC | Non-Standard Upgrades Ped Ramp - Manhattan & Bronx | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MXC | Non-Standard Upgrades Ped Ramp - Manhattan & Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Jun 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KR | Rehabilitation of Standard Ped Ramps - Brooklyn&Staten Islan | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KR | Rehabilitation of Standard Ped Ramps - Brooklyn&Staten Islan | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KR | Rehabilitation of Standard Ped Ramps - Brooklyn&Staten Islan | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KR | Rehabilitation of Standard Ped Ramps - Brooklyn&Staten Islan | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KR | Rehabilitation of Standard Ped Ramps - Brooklyn&Staten Islan | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KR | Rehabilitation of Standard Ped Ramps - Brooklyn&Staten Islan | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KR | Rehabilitation of Standard Ped Ramps - Brooklyn&Staten Islan | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KR | Rehabilitation of Standard Ped Ramps - Brooklyn&Staten Islan | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KR | Rehabilitation of Standard Ped Ramps - Brooklyn&Staten Islan | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KR | Rehabilitation of Standard Ped Ramps - Brooklyn&Staten Islan | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Jun 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KRC | FY23 Non-Standard Pedestrian Ramp Upgrades | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KRC | FY23 Non-Standard Pedestrian Ramp Upgrades | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KRC | FY23 Non-Standard Pedestrian Ramp Upgrades | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KRC | FY23 Non-Standard Pedestrian Ramp Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KRC | FY23 Non-Standard Pedestrian Ramp Upgrades | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KRC | FY23 Non-Standard Pedestrian Ramp Upgrades | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KRC | FY23 Non-Standard Pedestrian Ramp Upgrades | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KRC | FY23 Non-Standard Pedestrian Ramp Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KRC | FY23 Non-Standard Pedestrian Ramp Upgrades | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2023 | Mar 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KRC | FY23 Non-Standard Pedestrian Ramp Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2023 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KRC | FY23 Non-Standard Pedestrian Ramp Upgrades | 11 | PROJECT START | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KRC | FY23 Non-Standard Pedestrian Ramp Upgrades | 12 | DESIGN START | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KRC | FY23 Non-Standard Pedestrian Ramp Upgrades | 13 | DESIGN COMPLETION | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KRC | FY23 Non-Standard Pedestrian Ramp Upgrades | 14 | CONSTRUCTION START | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KRC | FY23 Non-Standard Pedestrian Ramp Upgrades | 15 | CONSTRUCTION COMPLETION | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21LMT | FY23 Non-Standard Pedestrian Ramp Upgrades | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21LMT | FY23 Non-Standard Pedestrian Ramp Upgrades | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21LMT | FY23 Non-Standard Pedestrian Ramp Upgrades | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21LMT | FY23 Non-Standard Pedestrian Ramp Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21LMT | FY23 Non-Standard Pedestrian Ramp Upgrades | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21LMT | FY23 Non-Standard Pedestrian Ramp Upgrades | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21LMT | FY23 Non-Standard Pedestrian Ramp Upgrades | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21LMT | FY23 Non-Standard Pedestrian Ramp Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21LMT | FY23 Non-Standard Pedestrian Ramp Upgrades | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2023 | Mar 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21LMT | FY23 Non-Standard Pedestrian Ramp Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2023 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21LMT | FY23 Non-Standard Pedestrian Ramp Upgrades | 11 | PROJECT START | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21LMT | FY23 Non-Standard Pedestrian Ramp Upgrades | 12 | DESIGN START | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21LMT | FY23 Non-Standard Pedestrian Ramp Upgrades | 13 | DESIGN COMPLETION | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21LMT | FY23 Non-Standard Pedestrian Ramp Upgrades | 14 | CONSTRUCTION START | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21LMT | FY23 Non-Standard Pedestrian Ramp Upgrades | 15 | CONSTRUCTION COMPLETION | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MQ | Rehabilitation of Standard Ped Ramps - Queens & Manhattan | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MQ | Rehabilitation of Standard Ped Ramps - Queens & Manhattan | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MQ | Rehabilitation of Standard Ped Ramps - Queens & Manhattan | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MQ | Rehabilitation of Standard Ped Ramps - Queens & Manhattan | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MQ | Rehabilitation of Standard Ped Ramps - Queens & Manhattan | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MQ | Rehabilitation of Standard Ped Ramps - Queens & Manhattan | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MQ | Rehabilitation of Standard Ped Ramps - Queens & Manhattan | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MQ | Rehabilitation of Standard Ped Ramps - Queens & Manhattan | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MQ | Rehabilitation of Standard Ped Ramps - Queens & Manhattan | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MQ | Rehabilitation of Standard Ped Ramps - Queens & Manhattan | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MQ | Rehabilitation of Standard Ped Ramps - Queens & Manhattan | 11 | PROJECT START | Mar 2024 | Apr 2024 | Apr 2024 | Apr 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MQ | Rehabilitation of Standard Ped Ramps - Queens & Manhattan | 12 | DESIGN START | Mar 2024 | Apr 2024 | Apr 2024 | Apr 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MQ | Rehabilitation of Standard Ped Ramps - Queens & Manhattan | 13 | DESIGN COMPLETION | Mar 2024 | Apr 2024 | Apr 2024 | Apr 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MQ | Rehabilitation of Standard Ped Ramps - Queens & Manhattan | 14 | CONSTRUCTION START | Mar 2024 | Apr 2024 | Apr 2024 | Apr 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MQ | Rehabilitation of Standard Ped Ramps - Queens & Manhattan | 15 | CONSTRUCTION COMPLETION | Mar 2024 | Apr 2024 | Apr 2024 | Apr 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MTA | FY23 Non-Standard Pedestrian Ramp Upgrades | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MTA | FY23 Non-Standard Pedestrian Ramp Upgrades | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MTA | FY23 Non-Standard Pedestrian Ramp Upgrades | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MTA | FY23 Non-Standard Pedestrian Ramp Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MTA | FY23 Non-Standard Pedestrian Ramp Upgrades | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MTA | FY23 Non-Standard Pedestrian Ramp Upgrades | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MTA | FY23 Non-Standard Pedestrian Ramp Upgrades | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MTA | FY23 Non-Standard Pedestrian Ramp Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MTA | FY23 Non-Standard Pedestrian Ramp Upgrades | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2023 | Mar 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MTA | FY23 Non-Standard Pedestrian Ramp Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2023 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MTA | FY23 Non-Standard Pedestrian Ramp Upgrades | 11 | PROJECT START | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MTA | FY23 Non-Standard Pedestrian Ramp Upgrades | 12 | DESIGN START | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MTA | FY23 Non-Standard Pedestrian Ramp Upgrades | 13 | DESIGN COMPLETION | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MTA | FY23 Non-Standard Pedestrian Ramp Upgrades | 14 | CONSTRUCTION START | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MTA | FY23 Non-Standard Pedestrian Ramp Upgrades | 15 | CONSTRUCTION COMPLETION | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QC | FY23 Non-Standard Pedestrian Ramp Upgrades | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QC | FY23 Non-Standard Pedestrian Ramp Upgrades | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QC | FY23 Non-Standard Pedestrian Ramp Upgrades | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QC | FY23 Non-Standard Pedestrian Ramp Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QC | FY23 Non-Standard Pedestrian Ramp Upgrades | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QC | FY23 Non-Standard Pedestrian Ramp Upgrades | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QC | FY23 Non-Standard Pedestrian Ramp Upgrades | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QC | FY23 Non-Standard Pedestrian Ramp Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QC | FY23 Non-Standard Pedestrian Ramp Upgrades | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QC | FY23 Non-Standard Pedestrian Ramp Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Jun 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Jun 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21XC | FY23 Non-Standard Pedestrian Ramp Upgrades | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21XC | FY23 Non-Standard Pedestrian Ramp Upgrades | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21XC | FY23 Non-Standard Pedestrian Ramp Upgrades | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21XC | FY23 Non-Standard Pedestrian Ramp Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21XC | FY23 Non-Standard Pedestrian Ramp Upgrades | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21XC | FY23 Non-Standard Pedestrian Ramp Upgrades | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21XC | FY23 Non-Standard Pedestrian Ramp Upgrades | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21XC | FY23 Non-Standard Pedestrian Ramp Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21XC | FY23 Non-Standard Pedestrian Ramp Upgrades | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2023 | Mar 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21XC | FY23 Non-Standard Pedestrian Ramp Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2023 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21XC | FY23 Non-Standard Pedestrian Ramp Upgrades | 11 | PROJECT START | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21XC | FY23 Non-Standard Pedestrian Ramp Upgrades | 12 | DESIGN START | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21XC | FY23 Non-Standard Pedestrian Ramp Upgrades | 13 | DESIGN COMPLETION | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21XC | FY23 Non-Standard Pedestrian Ramp Upgrades | 14 | CONSTRUCTION START | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21XC | FY23 Non-Standard Pedestrian Ramp Upgrades | 15 | CONSTRUCTION COMPLETION | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KQC | FY24 Non-Standard Pedestrian Ramp Upgrades | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KQC | FY24 Non-Standard Pedestrian Ramp Upgrades | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KQC | FY24 Non-Standard Pedestrian Ramp Upgrades | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KQC | FY24 Non-Standard Pedestrian Ramp Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KQC | FY24 Non-Standard Pedestrian Ramp Upgrades | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KQC | FY24 Non-Standard Pedestrian Ramp Upgrades | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KQC | FY24 Non-Standard Pedestrian Ramp Upgrades | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KQC | FY24 Non-Standard Pedestrian Ramp Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KQC | FY24 Non-Standard Pedestrian Ramp Upgrades | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KQC | FY24 Non-Standard Pedestrian Ramp Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2027 | Mar 2025 | Apr 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KR | Rehabilitation of Standard Ped Ramps - Brooklyn & SI | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KR | Rehabilitation of Standard Ped Ramps - Brooklyn & SI | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KR | Rehabilitation of Standard Ped Ramps - Brooklyn & SI | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KR | Rehabilitation of Standard Ped Ramps - Brooklyn & SI | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KR | Rehabilitation of Standard Ped Ramps - Brooklyn & SI | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KR | Rehabilitation of Standard Ped Ramps - Brooklyn & SI | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KR | Rehabilitation of Standard Ped Ramps - Brooklyn & SI | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KR | Rehabilitation of Standard Ped Ramps - Brooklyn & SI | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KR | Rehabilitation of Standard Ped Ramps - Brooklyn & SI | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KR | Rehabilitation of Standard Ped Ramps - Brooklyn & SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2033
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KRC | FY24 Non-Standard Pedestrian Ramp Upgrades | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KRC | FY24 Non-Standard Pedestrian Ramp Upgrades | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KRC | FY24 Non-Standard Pedestrian Ramp Upgrades | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KRC | FY24 Non-Standard Pedestrian Ramp Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KRC | FY24 Non-Standard Pedestrian Ramp Upgrades | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KRC | FY24 Non-Standard Pedestrian Ramp Upgrades | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KRC | FY24 Non-Standard Pedestrian Ramp Upgrades | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KRC | FY24 Non-Standard Pedestrian Ramp Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KRC | FY24 Non-Standard Pedestrian Ramp Upgrades | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KRC | FY24 Non-Standard Pedestrian Ramp Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22MC | FY24 Non-Standard Pedestrian Ramp Upgrades | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22MC | FY24 Non-Standard Pedestrian Ramp Upgrades | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22MC | FY24 Non-Standard Pedestrian Ramp Upgrades | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22MC | FY24 Non-Standard Pedestrian Ramp Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22MC | FY24 Non-Standard Pedestrian Ramp Upgrades | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22MC | FY24 Non-Standard Pedestrian Ramp Upgrades | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22MC | FY24 Non-Standard Pedestrian Ramp Upgrades | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22MC | FY24 Non-Standard Pedestrian Ramp Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22MC | FY24 Non-Standard Pedestrian Ramp Upgrades | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22MC | FY24 Non-Standard Pedestrian Ramp Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22MXC | FY24 Non-Standard Pedestrian Ramp Upgrades | 1 | DEVELOP SCOPE | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22MXC | FY24 Non-Standard Pedestrian Ramp Upgrades | 2 | PRELIMINARY DESIGN | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22MXC | FY24 Non-Standard Pedestrian Ramp Upgrades | 3 | FINAL DESIGN | Jan 2026 | Jul 2026 | Jan 2026 | Jul 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22MXC | FY24 Non-Standard Pedestrian Ramp Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2026 | Oct 2026 | Jul 2026 | Oct 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22MXC | FY24 Non-Standard Pedestrian Ramp Upgrades | 5 | CONSTRUCTION TO 25% | Oct 2026 | Feb 2027 | Oct 2026 | Feb 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22MXC | FY24 Non-Standard Pedestrian Ramp Upgrades | 6 | CONSTRUCTION TO 50% | Feb 2027 | Jun 2027 | Feb 2027 | Jun 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22MXC | FY24 Non-Standard Pedestrian Ramp Upgrades | 7 | CONSTRUCTION TO 75% | Jun 2027 | Oct 2027 | Jun 2027 | Oct 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22MXC | FY24 Non-Standard Pedestrian Ramp Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jan 2028 | Oct 2027 | Jan 2028
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22MXC | FY24 Non-Standard Pedestrian Ramp Upgrades | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Mar 2028 | Jan 2028 | Mar 2028
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22MXC | FY24 Non-Standard Pedestrian Ramp Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2028 | Apr 2028 | Mar 2028 | Apr 2028
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2033
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23KQ | Standard Upgrades Ped Ramps - Brooklyn and Queens | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23KQ | Standard Upgrades Ped Ramps - Brooklyn and Queens | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23KQ | Standard Upgrades Ped Ramps - Brooklyn and Queens | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23KQ | Standard Upgrades Ped Ramps - Brooklyn and Queens | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23KQ | Standard Upgrades Ped Ramps - Brooklyn and Queens | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23KQ | Standard Upgrades Ped Ramps - Brooklyn and Queens | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23KQ | Standard Upgrades Ped Ramps - Brooklyn and Queens | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23KQ | Standard Upgrades Ped Ramps - Brooklyn and Queens | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23KQ | Standard Upgrades Ped Ramps - Brooklyn and Queens | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23KQ | Standard Upgrades Ped Ramps - Brooklyn and Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23KR | Standard Upgrades Ped Ramps - Brooklyn and Staten Island | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23KR | Standard Upgrades Ped Ramps - Brooklyn and Staten Island | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23KR | Standard Upgrades Ped Ramps - Brooklyn and Staten Island | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23KR | Standard Upgrades Ped Ramps - Brooklyn and Staten Island | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23KR | Standard Upgrades Ped Ramps - Brooklyn and Staten Island | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23KR | Standard Upgrades Ped Ramps - Brooklyn and Staten Island | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23KR | Standard Upgrades Ped Ramps - Brooklyn and Staten Island | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23KR | Standard Upgrades Ped Ramps - Brooklyn and Staten Island | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23KR | Standard Upgrades Ped Ramps - Brooklyn and Staten Island | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23KR | Standard Upgrades Ped Ramps - Brooklyn and Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23MQ | Standard Upgrades Ped Ramps - Manhattan and Queens | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23MQ | Standard Upgrades Ped Ramps - Manhattan and Queens | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23MQ | Standard Upgrades Ped Ramps - Manhattan and Queens | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23MQ | Standard Upgrades Ped Ramps - Manhattan and Queens | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23MQ | Standard Upgrades Ped Ramps - Manhattan and Queens | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23MQ | Standard Upgrades Ped Ramps - Manhattan and Queens | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23MQ | Standard Upgrades Ped Ramps - Manhattan and Queens | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23MQ | Standard Upgrades Ped Ramps - Manhattan and Queens | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23MQ | Standard Upgrades Ped Ramps - Manhattan and Queens | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23MQ | Standard Upgrades Ped Ramps - Manhattan and Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23QX | Standard Upgrades Ped Ramps - Queens and the Bronx | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23QX | Standard Upgrades Ped Ramps - Queens and the Bronx | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23QX | Standard Upgrades Ped Ramps - Queens and the Bronx | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23QX | Standard Upgrades Ped Ramps - Queens and the Bronx | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23QX | Standard Upgrades Ped Ramps - Queens and the Bronx | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23QX | Standard Upgrades Ped Ramps - Queens and the Bronx | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23QX | Standard Upgrades Ped Ramps - Queens and the Bronx | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23QX | Standard Upgrades Ped Ramps - Queens and the Bronx | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23QX | Standard Upgrades Ped Ramps - Queens and the Bronx | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23QX | Standard Upgrades Ped Ramps - Queens and the Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020XM | Prior Notice Sidewalks- Manhattan & Bronx | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020XM | Prior Notice Sidewalks- Manhattan & Bronx | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020XM | Prior Notice Sidewalks- Manhattan & Bronx | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020XM | Prior Notice Sidewalks- Manhattan & Bronx | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020XM | Prior Notice Sidewalks- Manhattan & Bronx | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020XM | Prior Notice Sidewalks- Manhattan & Bronx | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020XM | Prior Notice Sidewalks- Manhattan & Bronx | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020XM | Prior Notice Sidewalks- Manhattan & Bronx | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020XM | Prior Notice Sidewalks- Manhattan & Bronx | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020XM | Prior Notice Sidewalks- Manhattan & Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Apr 2028
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021XM | PRIOR NOTICE SIDEWALK - BRONX & MANHATTAN | 1 | DEVELOP SCOPE | Feb 2020 | Mar 2020 | Feb 2021 | Mar 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021XM | PRIOR NOTICE SIDEWALK - BRONX & MANHATTAN | 2 | DESIGN START | Mar 2020 | Jun 2020 | Mar 2021 | Jul 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021XM | PRIOR NOTICE SIDEWALK - BRONX & MANHATTAN | 3 | CONSTRUCTION START | Jul 2020 | Jun 2021 | Jul 2021 | Jun 2032
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRQX1 | Trench Restoration - Queens and Bronx (SEX002271) | 1 | DEVELOP SCOPE | Mar 2019 | May 2019 | Mar 2019 | May 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRQX1 | Trench Restoration - Queens and Bronx (SEX002271) | 2 | PRELIMINARY DESIGN | May 2019 | Sep 2019 | May 2019 | Sep 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRQX1 | Trench Restoration - Queens and Bronx (SEX002271) | 3 | FINAL DESIGN | Sep 2019 | Jul 2020 | Sep 2019 | Jul 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRQX1 | Trench Restoration - Queens and Bronx (SEX002271) | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Sep 2020 | Jul 2020 | Sep 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRQX1 | Trench Restoration - Queens and Bronx (SEX002271) | 5 | CONSTRUCTION TO 25% | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRQX1 | Trench Restoration - Queens and Bronx (SEX002271) | 6 | CONSTRUCTION TO 50% | Jan 2021 | May 2021 | Jan 2021 | May 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRQX1 | Trench Restoration - Queens and Bronx (SEX002271) | 7 | CONSTRUCTION TO 75% | May 2021 | Sep 2021 | May 2021 | Sep 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRQX1 | Trench Restoration - Queens and Bronx (SEX002271) | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Dec 2021 | Sep 2021 | Dec 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRQX1 | Trench Restoration - Queens and Bronx (SEX002271) | 9 | SUBSTANTIAL COMPLETION | Dec 2021 | Feb 2022 | Dec 2021 | Feb 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRQX1 | Trench Restoration - Queens and Bronx (SEX002271) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2022 | Mar 2022 | Feb 2023 | Jan 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRQX1 | Trench Restoration - Queens and Bronx (SEX002271) | 11 | PROJECT START | Feb 2022 | Mar 2022 | Jan 2024 | Jan 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRQX1 | Trench Restoration - Queens and Bronx (SEX002271) | 12 | DESIGN START | Feb 2022 | Mar 2022 | Jan 2024 | Jan 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRQX1 | Trench Restoration - Queens and Bronx (SEX002271) | 13 | DESIGN COMPLETION | Feb 2022 | Mar 2022 | Jan 2024 | Jan 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRQX1 | Trench Restoration - Queens and Bronx (SEX002271) | 14 | CONSTRUCTION START | Feb 2022 | Mar 2022 | Jan 2024 | Jan 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRQX1 | Trench Restoration - Queens and Bronx (SEX002271) | 15 | CONSTRUCTION COMPLETION | Feb 2022 | Mar 2022 | Jan 2024 | Jan 2031
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | JJ1FACREN | FACILITIES RENOVATIONS | 1 | DESIGN | Jun 2004 | Dec 2004 | Jan 2015 | Jun 2015
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | JJ1FACREN | FACILITIES RENOVATIONS | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2004 | Mar 2005 | Jun 2015 | Sep 2015
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | JJ1FACREN | FACILITIES RENOVATIONS | 3 | CONSTRUCTION | Mar 2005 | Mar 2015 | Sep 2015 | Sep 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | JJ1FACREN | FACILITIES RENOVATIONS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Sep 2015 | Sep 2018 | Mar 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | JJ1FACREN | FACILITIES RENOVATIONS | 5 | PROJECT START | Mar 2015 | Sep 2015 | Mar 2019 | Mar 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | JJ1FACREN | FACILITIES RENOVATIONS | 6 | DESIGN START | Mar 2015 | Sep 2015 | Mar 2019 | Mar 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | JJ1FACREN | FACILITIES RENOVATIONS | 7 | DESIGN COMPLETION | Mar 2015 | Sep 2015 | Mar 2019 | Mar 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | JJ1FACREN | FACILITIES RENOVATIONS | 8 | CONSTRUCTION START | Mar 2015 | Sep 2015 | Mar 2019 | Mar 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | JJ1FACREN | FACILITIES RENOVATIONS | 9 | CONSTRUCTION COMPLETION | Mar 2015 | Sep 2015 | Mar 2019 | Mar 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA16WH1 | Washington Heights - Third Floor Renovation | 1 | PROJECT START | Oct 2016 | Oct 2016 | Oct 2016 | Oct 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA16WH1 | Washington Heights - Third Floor Renovation | 2 | DESIGN START | Oct 2016 | Oct 2016 | Oct 2016 | Dec 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA16WH1 | Washington Heights - Third Floor Renovation | 3 | DESIGN COMPLETION | Oct 2017 | Oct 2017 | Oct 2017 | May 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA16WH1 | Washington Heights - Third Floor Renovation | 4 | CONSTRUCTION START | Oct 2018 | Oct 2018 | Oct 2018 | Jan 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA16WH1 | Washington Heights - Third Floor Renovation | 5 | CONSTRUCTION COMPLETION | Oct 2019 | Oct 2019 | Oct 2019 | Dec 2032
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO141-40P | NEW 40TH PRECINCT | 1 | PROJECT START | Jul 2014 | Jul 2014 | Jul 2014 | Jul 2014
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO141-40P | NEW 40TH PRECINCT | 2 | DESIGN START | Jul 2014 | Jan 2015 | Jul 2014 | Jan 2015
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO141-40P | NEW 40TH PRECINCT | 3 | DESIGN COMPLETION | Jan 2015 | Apr 2016 | Jan 2015 | Apr 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO141-40P | NEW 40TH PRECINCT | 4 | CONSTRUCTION START | Apr 2016 | Aug 2016 | Apr 2016 | Aug 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO141-40P | NEW 40TH PRECINCT | 5 | CONSTRUCTION COMPLETION | Aug 2016 | Sep 2018 | Aug 2016 | Jun 2032
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDCW1 | Front Desk Renovations for 45th, 75th, 105th, 123rd PCTS | 1 | DESIGN | Dec 2017 | May 2018 | Dec 2017 | Feb 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDCW1 | Front Desk Renovations for 45th, 75th, 105th, 123rd PCTS | 2 | BID AWARD AND REGISTER CONTRCT | May 2018 | Aug 2018 | Feb 2021 | May 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDCW1 | Front Desk Renovations for 45th, 75th, 105th, 123rd PCTS | 3 | CONSTRUCTION | Aug 2018 | Aug 2019 | May 2021 | May 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDCW1 | Front Desk Renovations for 45th, 75th, 105th, 123rd PCTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2019 | Feb 2020 | May 2022 | Nov 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDCW1 | Front Desk Renovations for 45th, 75th, 105th, 123rd PCTS | 5 | PROJECT START | Aug 2019 | Feb 2020 | Nov 2022 | Nov 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDCW1 | Front Desk Renovations for 45th, 75th, 105th, 123rd PCTS | 6 | DESIGN START | Aug 2019 | Feb 2020 | Nov 2022 | Nov 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDCW1 | Front Desk Renovations for 45th, 75th, 105th, 123rd PCTS | 7 | DESIGN COMPLETION | Aug 2019 | Feb 2020 | Nov 2022 | Nov 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDCW1 | Front Desk Renovations for 45th, 75th, 105th, 123rd PCTS | 8 | CONSTRUCTION START | Aug 2019 | Feb 2020 | Nov 2022 | Nov 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDCW1 | Front Desk Renovations for 45th, 75th, 105th, 123rd PCTS | 9 | CONSTRUCTION COMPLETION | Aug 2019 | Feb 2020 | Nov 2022 | Nov 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79WNDWS | HWY UNIT 3, 67TH, 76TH, 111TH PCT WINDOW RPLCMNT | 1 | PROJECT START | Mar 2013 | Oct 2014 | Mar 2013 | Oct 2014
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79WNDWS | HWY UNIT 3, 67TH, 76TH, 111TH PCT WINDOW RPLCMNT | 2 | DESIGN START | Oct 2014 | Mar 2015 | Oct 2014 | Mar 2015
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79WNDWS | HWY UNIT 3, 67TH, 76TH, 111TH PCT WINDOW RPLCMNT | 3 | DESIGN COMPLETION | Mar 2015 | Sep 2015 | Mar 2015 | Sep 2015
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79WNDWS | HWY UNIT 3, 67TH, 76TH, 111TH PCT WINDOW RPLCMNT | 4 | CONSTRUCTION START | Sep 2015 | Feb 2016 | Sep 2015 | Feb 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79WNDWS | HWY UNIT 3, 67TH, 76TH, 111TH PCT WINDOW RPLCMNT | 5 | CONSTRUCTION COMPLETION | Feb 2016 | Feb 2017 | Feb 2016 | Jun 2032
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | REPAIRS & REHAB OF INTERCEPTING SEWERS - MANHATTAN | 1 | DEVELOP SCOPE | Feb 2014 | May 2014 | Feb 2014 | May 2014
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | REPAIRS & REHAB OF INTERCEPTING SEWERS - MANHATTAN | 2 | PRELIMINARY DESIGN | May 2014 | Sep 2014 | May 2014 | Sep 2014
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | REPAIRS & REHAB OF INTERCEPTING SEWERS - MANHATTAN | 3 | FINAL DESIGN | Sep 2014 | Mar 2015 | Sep 2014 | Mar 2015
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | REPAIRS & REHAB OF INTERCEPTING SEWERS - MANHATTAN | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2015 | Jun 2015 | Mar 2015 | Jun 2015
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | REPAIRS & REHAB OF INTERCEPTING SEWERS - MANHATTAN | 5 | CONSTRUCTION TO 25% | Jun 2015 | Oct 2015 | Jun 2015 | Oct 2015
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | REPAIRS & REHAB OF INTERCEPTING SEWERS - MANHATTAN | 6 | CONSTRUCTION TO 50% | Oct 2015 | Feb 2016 | Oct 2015 | Feb 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | REPAIRS & REHAB OF INTERCEPTING SEWERS - MANHATTAN | 7 | CONSTRUCTION TO 75% | Feb 2016 | Jun 2016 | Feb 2016 | Jun 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | REPAIRS & REHAB OF INTERCEPTING SEWERS - MANHATTAN | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2016 | Sep 2016 | Jun 2016 | Sep 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | REPAIRS & REHAB OF INTERCEPTING SEWERS - MANHATTAN | 9 | SUBSTANTIAL COMPLETION | Sep 2016 | Nov 2016 | Sep 2016 | Nov 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | REPAIRS & REHAB OF INTERCEPTING SEWERS - MANHATTAN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2016 | Dec 2016 | Nov 2016 | Dec 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | REPAIRS & REHAB OF INTERCEPTING SEWERS - MANHATTAN | 11 | PROJECT START | Nov 2016 | Dec 2016 | Dec 2016 | Dec 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | REPAIRS & REHAB OF INTERCEPTING SEWERS - MANHATTAN | 12 | DESIGN START | Nov 2016 | Dec 2016 | Dec 2016 | Dec 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | REPAIRS & REHAB OF INTERCEPTING SEWERS - MANHATTAN | 13 | DESIGN COMPLETION | Nov 2016 | Dec 2016 | Dec 2016 | Dec 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | REPAIRS & REHAB OF INTERCEPTING SEWERS - MANHATTAN | 14 | CONSTRUCTION START | Nov 2016 | Dec 2016 | Dec 2016 | Dec 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | REPAIRS & REHAB OF INTERCEPTING SEWERS - MANHATTAN | 15 | CONSTRUCTION COMPLETION | Nov 2016 | Dec 2016 | Dec 2016 | Jun 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW335A28 | ASBESTOS ABATEMENT CONTRACT | 1 | PROJECT START | Apr 2016 | Apr 2016 | Apr 2016 | Apr 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW335A28 | ASBESTOS ABATEMENT CONTRACT | 2 | DESIGN START | Apr 2016 | Apr 2016 | Apr 2016 | Apr 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW335A28 | ASBESTOS ABATEMENT CONTRACT | 3 | DESIGN COMPLETION | Apr 2016 | Apr 2016 | Apr 2016 | Apr 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW335A28 | ASBESTOS ABATEMENT CONTRACT | 4 | CONSTRUCTION START | Apr 2016 | Apr 2016 | Apr 2016 | Apr 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW335A28 | ASBESTOS ABATEMENT CONTRACT | 5 | CONSTRUCTION COMPLETION | Apr 2016 | Apr 2022 | Apr 2016 | Apr 2035
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW335A29 | ASBESTOS ABATEMENT CONTRACT,MN,BX,QNS | 1 | PROJECT START | Jun 2022 | Jul 2023 | Jun 2022 | Jul 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW335A29 | ASBESTOS ABATEMENT CONTRACT,MN,BX,QNS | 2 | DESIGN START | Jul 2023 | Jul 2023 | Jul 2023 | Jul 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW335A29 | ASBESTOS ABATEMENT CONTRACT,MN,BX,QNS | 3 | DESIGN COMPLETION | Jul 2023 | Jul 2023 | Jul 2023 | Jul 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW335A29 | ASBESTOS ABATEMENT CONTRACT,MN,BX,QNS | 4 | CONSTRUCTION START | Jul 2023 | Jul 2023 | Jul 2023 | Jul 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW335A29 | ASBESTOS ABATEMENT CONTRACT,MN,BX,QNS | 5 | CONSTRUCTION COMPLETION | Jul 2023 | Jun 2027 | Jul 2023 | Jun 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW335A30 | ASBESTOS ABATEMENT CONTRACT, MN, BK, SI | 1 | PROJECT START | Jun 2022 | Jun 2023 | Jun 2022 | Jun 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW335A30 | ASBESTOS ABATEMENT CONTRACT, MN, BK, SI | 2 | DESIGN START | Jul 2023 | Jul 2023 | Jul 2023 | Jul 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW335A30 | ASBESTOS ABATEMENT CONTRACT, MN, BK, SI | 3 | DESIGN COMPLETION | Jul 2023 | Jul 2023 | Jul 2023 | Jul 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW335A30 | ASBESTOS ABATEMENT CONTRACT, MN, BK, SI | 4 | CONSTRUCTION START | Jul 2023 | Jul 2023 | Jul 2023 | Jul 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW335A30 | ASBESTOS ABATEMENT CONTRACT, MN, BK, SI | 5 | CONSTRUCTION COMPLETION | Jul 2023 | Jul 2031 | Jul 2023 | Jul 2031
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-51 | Upgrade/replacement/remediation/installation | 1 | PROJECT START | Jan 2007 | Jan 2007 | Jan 2007 | Apr 2007
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-51 | Upgrade/replacement/remediation/installation | 2 | DESIGN START | Feb 2007 | Feb 2007 | Apr 2007 | Aug 2008
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-51 | Upgrade/replacement/remediation/installation | 3 | DESIGN COMPLETION | Feb 2007 | Feb 2007 | Aug 2008 | Oct 2009
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-51 | Upgrade/replacement/remediation/installation | 4 | CONSTRUCTION START | Feb 2007 | Feb 2007 | Oct 2009 | Jan 2010
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-51 | Upgrade/replacement/remediation/installation | 5 | CONSTRUCTION COMPLETION | Feb 2007 | Feb 2010 | Feb 2010 | Jun 2015
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-71 | FUEL TANK REPLACEMENT | 1 | PROJECT START | Jul 2017 | Jul 2017 | Jul 2017 | Jul 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-71 | FUEL TANK REPLACEMENT | 2 | DESIGN START | Jul 2017 | Jul 2017 | Jul 2017 | Jul 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-71 | FUEL TANK REPLACEMENT | 3 | DESIGN COMPLETION | Jul 2017 | Jul 2017 | Jul 2017 | Jul 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-71 | FUEL TANK REPLACEMENT | 4 | CONSTRUCTION START | Jul 2017 | Jul 2017 | Jul 2017 | Jul 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-71 | FUEL TANK REPLACEMENT | 5 | CONSTRUCTION COMPLETION | Jul 2017 | Jul 2019 | Jul 2017 | Jun 2032
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-72 | FUEL TANK REPLACEMENT | 1 | PROJECT START | Jul 2017 | Jul 2017 | Jul 2017 | Jul 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-72 | FUEL TANK REPLACEMENT | 2 | DESIGN START | Jul 2017 | Jul 2017 | Jul 2017 | Jul 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-72 | FUEL TANK REPLACEMENT | 3 | DESIGN COMPLETION | Jul 2017 | Jul 2017 | Jul 2017 | Jul 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-72 | FUEL TANK REPLACEMENT | 4 | CONSTRUCTION START | Jul 2017 | Jul 2017 | Jul 2017 | Jul 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-72 | FUEL TANK REPLACEMENT | 5 | CONSTRUCTION COMPLETION | Jul 2017 | Jul 2019 | Jul 2017 | Nov 2032
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-73 | FUEL TANK REPLACEMENT | 1 | PROJECT START | Jul 2017 | Jul 2017 | Jul 2017 | Jul 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-73 | FUEL TANK REPLACEMENT | 2 | DESIGN START | Jul 2017 | Jul 2017 | Jul 2017 | Jul 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-73 | FUEL TANK REPLACEMENT | 3 | DESIGN COMPLETION | Jul 2017 | Jul 2017 | Jul 2017 | Jul 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-73 | FUEL TANK REPLACEMENT | 4 | CONSTRUCTION START | Jul 2017 | Jul 2017 | Jul 2017 | Jul 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-73 | FUEL TANK REPLACEMENT | 5 | CONSTRUCTION COMPLETION | Jul 2017 | Jul 2019 | Jul 2017 | Jun 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-81 | FUEL TANK REPLACEMENT | 1 | PROJECT START | Jul 2018 | Jul 2018 | Jul 2018 | Jul 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-81 | FUEL TANK REPLACEMENT | 2 | DESIGN START | Jul 2018 | Jul 2018 | Jul 2018 | Jul 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-81 | FUEL TANK REPLACEMENT | 3 | DESIGN COMPLETION | Jul 2018 | Jul 2018 | Jul 2018 | Jul 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-81 | FUEL TANK REPLACEMENT | 4 | CONSTRUCTION START | Jul 2018 | Jul 2018 | Jul 2018 | Jul 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-81 | FUEL TANK REPLACEMENT | 5 | CONSTRUCTION COMPLETION | Jul 2018 | Jul 2020 | Jul 2018 | Jun 2030
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-82 | FUEL TANK REPLACEMENT | 1 | PROJECT START | Jul 2018 | Jul 2018 | Jul 2018 | Jul 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-82 | FUEL TANK REPLACEMENT | 2 | DESIGN START | Jul 2018 | Jul 2018 | Jul 2018 | Jul 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-82 | FUEL TANK REPLACEMENT | 3 | DESIGN COMPLETION | Jul 2018 | Jul 2018 | Jul 2018 | Jul 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-82 | FUEL TANK REPLACEMENT | 4 | CONSTRUCTION START | Jul 2018 | Jul 2018 | Jul 2018 | Jul 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-82 | FUEL TANK REPLACEMENT | 5 | CONSTRUCTION COMPLETION | Jul 2018 | Jul 2020 | Jul 2018 | Jun 2030
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-83 | FUEL TANK REPLACEMENT | 1 | PROJECT START | Jul 2018 | Jul 2018 | Jul 2018 | Jul 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-83 | FUEL TANK REPLACEMENT | 2 | DESIGN START | Jul 2018 | Jul 2018 | Jul 2018 | Jul 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-83 | FUEL TANK REPLACEMENT | 3 | DESIGN COMPLETION | Jul 2018 | Jul 2018 | Jul 2018 | Jul 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-83 | FUEL TANK REPLACEMENT | 4 | CONSTRUCTION START | Jul 2018 | Jul 2018 | Jul 2018 | Jul 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-83 | FUEL TANK REPLACEMENT | 5 | CONSTRUCTION COMPLETION | Jul 2018 | Jul 2020 | Jul 2018 | Jun 2030
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-84 | FUEL TANK REPLACEMENT | 1 | PROJECT START | Jul 2018 | Jul 2018 | Jul 2018 | Jul 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-84 | FUEL TANK REPLACEMENT | 2 | DESIGN START | Jul 2018 | Jul 2018 | Jul 2018 | Jul 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-84 | FUEL TANK REPLACEMENT | 3 | DESIGN COMPLETION | Jul 2018 | Jul 2018 | Jul 2018 | Jul 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-84 | FUEL TANK REPLACEMENT | 4 | CONSTRUCTION START | Jul 2018 | Jul 2018 | Jul 2018 | Jul 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-84 | FUEL TANK REPLACEMENT | 5 | CONSTRUCTION COMPLETION | Jul 2018 | Jul 2020 | Jul 2018 | Jun 2031
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PWCOMPDAT | Comptroller's Office Data Center Replacement at 1 Centre St. | 1 | PROJECT START | Mar 2018 | Mar 2018 | Mar 2018 | Mar 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PWCOMPDAT | Comptroller's Office Data Center Replacement at 1 Centre St. | 2 | DESIGN START | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PWCOMPDAT | Comptroller's Office Data Center Replacement at 1 Centre St. | 3 | DESIGN COMPLETION | Jun 2018 | Jul 2019 | Jun 2018 | Jul 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PWCOMPDAT | Comptroller's Office Data Center Replacement at 1 Centre St. | 4 | CONSTRUCTION START | Jul 2019 | May 2020 | Jul 2019 | May 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PWCOMPDAT | Comptroller's Office Data Center Replacement at 1 Centre St. | 5 | CONSTRUCTION COMPLETION | May 2020 | Nov 2021 | May 2020 | Nov 2032
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PWHLDGFND | DCAS - DDC Programwide Project for Holding Funds | 1 | PROJECT START | Jun 2022 | Jun 2022 | Jun 2022 | Jun 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PWHLDGFND | DCAS - DDC Programwide Project for Holding Funds | 2 | DESIGN START | Jul 2022 | Jul 2022 | Jul 2022 | Jul 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PWHLDGFND | DCAS - DDC Programwide Project for Holding Funds | 3 | DESIGN COMPLETION | Jul 2022 | Jul 2022 | Jul 2022 | Jul 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PWHLDGFND | DCAS - DDC Programwide Project for Holding Funds | 4 | CONSTRUCTION START | Jul 2022 | Jul 2022 | Jul 2022 | Jul 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PWHLDGFND | DCAS - DDC Programwide Project for Holding Funds | 5 | CONSTRUCTION COMPLETION | Jul 2022 | Jul 2023 | Jul 2022 | Jun 2032
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1059 | Area Contract Install Dist WM through BX & QNS | 1 | DEVELOP SCOPE | Sep 2021 | Dec 2021 | Sep 2021 | Dec 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1059 | Area Contract Install Dist WM through BX & QNS | 2 | PRELIMINARY DESIGN | Dec 2021 | Mar 2022 | Dec 2021 | Mar 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1059 | Area Contract Install Dist WM through BX & QNS | 3 | FINAL DESIGN | Apr 2022 | Sep 2022 | Apr 2022 | Sep 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1059 | Area Contract Install Dist WM through BX & QNS | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1059 | Area Contract Install Dist WM through BX & QNS | 5 | CONSTRUCTION TO 25% | Dec 2022 | Apr 2023 | Dec 2022 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1059 | Area Contract Install Dist WM through BX & QNS | 6 | CONSTRUCTION TO 50% | Apr 2023 | Aug 2023 | Apr 2023 | Aug 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1059 | Area Contract Install Dist WM through BX & QNS | 7 | CONSTRUCTION TO 75% | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1059 | Area Contract Install Dist WM through BX & QNS | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2023 | Mar 2024 | Dec 2023 | Mar 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1059 | Area Contract Install Dist WM through BX & QNS | 9 | SUBSTANTIAL COMPLETION | Mar 2024 | May 2024 | Mar 2024 | May 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1059 | Area Contract Install Dist WM through BX & QNS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Jun 2024 | May 2024 | Jun 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1063AC | Area contract for watermain replacement in QNS and BX | 1 | DEVELOP SCOPE | Aug 2022 | Nov 2022 | Aug 2022 | Nov 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1063AC | Area contract for watermain replacement in QNS and BX | 2 | PRELIMINARY DESIGN | Nov 2022 | Mar 2023 | Nov 2022 | Mar 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1063AC | Area contract for watermain replacement in QNS and BX | 3 | FINAL DESIGN | Mar 2023 | Sep 2023 | Mar 2023 | Sep 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1063AC | Area contract for watermain replacement in QNS and BX | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2023 | Dec 2023 | Sep 2023 | Dec 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1063AC | Area contract for watermain replacement in QNS and BX | 5 | CONSTRUCTION TO 25% | Dec 2023 | Apr 2024 | Dec 2023 | Apr 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1063AC | Area contract for watermain replacement in QNS and BX | 6 | CONSTRUCTION TO 50% | Apr 2024 | Aug 2024 | Apr 2024 | Aug 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1063AC | Area contract for watermain replacement in QNS and BX | 7 | CONSTRUCTION TO 75% | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1063AC | Area contract for watermain replacement in QNS and BX | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2024 | Mar 2025 | Dec 2024 | Mar 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1063AC | Area contract for watermain replacement in QNS and BX | 9 | SUBSTANTIAL COMPLETION | Mar 2025 | May 2025 | Mar 2025 | May 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1063AC | Area contract for watermain replacement in QNS and BX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2025 | Jun 2025 | May 2025 | Jun 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-388 | Install Distribution WM throughout Brooklyn & Staten Island | 1 | DEVELOP SCOPE | Aug 2019 | Nov 2019 | Aug 2019 | Nov 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-388 | Install Distribution WM throughout Brooklyn & Staten Island | 2 | PRELIMINARY DESIGN | Nov 2019 | Mar 2020 | Nov 2019 | Mar 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-388 | Install Distribution WM throughout Brooklyn & Staten Island | 3 | FINAL DESIGN | Mar 2020 | Sep 2020 | Mar 2020 | Sep 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-388 | Install Distribution WM throughout Brooklyn & Staten Island | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2020 | Dec 2020 | Sep 2020 | Dec 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-388 | Install Distribution WM throughout Brooklyn & Staten Island | 5 | CONSTRUCTION TO 25% | Dec 2020 | Apr 2021 | Dec 2020 | Apr 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-388 | Install Distribution WM throughout Brooklyn & Staten Island | 6 | CONSTRUCTION TO 50% | Apr 2021 | Aug 2021 | Apr 2021 | Aug 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-388 | Install Distribution WM throughout Brooklyn & Staten Island | 7 | CONSTRUCTION TO 75% | Aug 2021 | Dec 2021 | Aug 2021 | Dec 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-388 | Install Distribution WM throughout Brooklyn & Staten Island | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2021 | Mar 2022 | Dec 2021 | Mar 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-388 | Install Distribution WM throughout Brooklyn & Staten Island | 9 | SUBSTANTIAL COMPLETION | Mar 2022 | May 2022 | Mar 2022 | May 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-388 | Install Distribution WM throughout Brooklyn & Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2022 | Jun 2022 | May 2022 | Jun 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED394 | Area contract - Install Dist WM throughout BKLYN & SI | 1 | DEVELOP SCOPE | Sep 2021 | Dec 2021 | Sep 2021 | Dec 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED394 | Area contract - Install Dist WM throughout BKLYN & SI | 2 | PRELIMINARY DESIGN | Dec 2021 | Mar 2022 | Dec 2021 | Mar 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED394 | Area contract - Install Dist WM throughout BKLYN & SI | 3 | FINAL DESIGN | Apr 2022 | Sep 2022 | Apr 2022 | Sep 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED394 | Area contract - Install Dist WM throughout BKLYN & SI | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED394 | Area contract - Install Dist WM throughout BKLYN & SI | 5 | CONSTRUCTION TO 25% | Dec 2022 | Apr 2023 | Dec 2022 | Apr 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED394 | Area contract - Install Dist WM throughout BKLYN & SI | 6 | CONSTRUCTION TO 50% | Apr 2023 | Aug 2023 | Apr 2023 | Aug 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED394 | Area contract - Install Dist WM throughout BKLYN & SI | 7 | CONSTRUCTION TO 75% | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED394 | Area contract - Install Dist WM throughout BKLYN & SI | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2023 | Mar 2024 | Dec 2023 | Mar 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED394 | Area contract - Install Dist WM throughout BKLYN & SI | 9 | SUBSTANTIAL COMPLETION | Mar 2024 | May 2024 | Mar 2024 | May 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED394 | Area contract - Install Dist WM throughout BKLYN & SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Jun 2024 | May 2024 | Jun 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED395AC | Area Contract Replacmt & Install Dist WM throughout BK & SI | 1 | PROJECT START | Oct 2022 | Nov 2022 | Oct 2022 | Nov 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED395AC | Area Contract Replacmt & Install Dist WM throughout BK & SI | 2 | DESIGN START | Nov 2022 | May 2023 | Nov 2022 | May 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED395AC | Area Contract Replacmt & Install Dist WM throughout BK & SI | 3 | DESIGN COMPLETION | May 2023 | Nov 2023 | May 2023 | Nov 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED395AC | Area Contract Replacmt & Install Dist WM throughout BK & SI | 4 | CONSTRUCTION START | Jun 2024 | Dec 2025 | Jun 2024 | Dec 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED395AC | Area Contract Replacmt & Install Dist WM throughout BK & SI | 5 | CONSTRUCTION COMPLETION | Dec 2025 | Dec 2025 | Dec 2025 | Dec 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND349FM | Sandy Phase 2 Resurfacing (FEMA Funded) | 1 | DEVELOP SCOPE | Feb 2014 | May 2014 | Feb 2014 | Sep 2014
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND349FM | Sandy Phase 2 Resurfacing (FEMA Funded) | 2 | PRELIMINARY DESIGN | May 2014 | Sep 2014 | Sep 2014 | Jan 2015
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND349FM | Sandy Phase 2 Resurfacing (FEMA Funded) | 3 | FINAL DESIGN | Sep 2014 | Mar 2015 | Jan 2015 | Jul 2015
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND349FM | Sandy Phase 2 Resurfacing (FEMA Funded) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2015 | Jun 2015 | Jul 2015 | Feb 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND349FM | Sandy Phase 2 Resurfacing (FEMA Funded) | 5 | CONSTRUCTION TO 25% | Jun 2015 | Oct 2015 | Feb 2016 | Jun 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND349FM | Sandy Phase 2 Resurfacing (FEMA Funded) | 6 | CONSTRUCTION TO 50% | Oct 2015 | Feb 2016 | Jun 2016 | Oct 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND349FM | Sandy Phase 2 Resurfacing (FEMA Funded) | 7 | CONSTRUCTION TO 75% | Feb 2016 | Jun 2016 | Oct 2016 | Feb 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND349FM | Sandy Phase 2 Resurfacing (FEMA Funded) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2016 | Sep 2016 | Feb 2017 | May 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND349FM | Sandy Phase 2 Resurfacing (FEMA Funded) | 9 | SUBSTANTIAL COMPLETION | Sep 2016 | Nov 2016 | May 2017 | Jul 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND349FM | Sandy Phase 2 Resurfacing (FEMA Funded) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2016 | Dec 2016 | Jul 2017 | Jun 2028
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBCHCM | HURRICANE SANDY DAMAGE CM MANAGED PROJECTS | 1 | PROJECT START | Mar 2013 | Mar 2013 | Mar 2013 | Mar 2013
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBCHCM | HURRICANE SANDY DAMAGE CM MANAGED PROJECTS | 2 | DESIGN START | Mar 2013 | Mar 2013 | Mar 2013 | Mar 2013
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBCHCM | HURRICANE SANDY DAMAGE CM MANAGED PROJECTS | 3 | DESIGN COMPLETION | Mar 2013 | Mar 2013 | Mar 2013 | Mar 2013
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBCHCM | HURRICANE SANDY DAMAGE CM MANAGED PROJECTS | 4 | CONSTRUCTION START | Mar 2013 | Mar 2013 | Mar 2013 | Mar 2013
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBCHCM | HURRICANE SANDY DAMAGE CM MANAGED PROJECTS | 5 | CONSTRUCTION COMPLETION | Mar 2013 | Mar 2015 | Mar 2013 | Jun 2031
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDISLND | HURRICANE SANDY DAMAGE ROCKAWAY BEACH ENTRY ISLANDS | 1 | PROJECT START | Dec 2012 | Dec 2012 | Dec 2012 | Dec 2012
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDISLND | HURRICANE SANDY DAMAGE ROCKAWAY BEACH ENTRY ISLANDS | 2 | DESIGN START | Dec 2012 | Dec 2012 | Dec 2012 | Dec 2012
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDISLND | HURRICANE SANDY DAMAGE ROCKAWAY BEACH ENTRY ISLANDS | 3 | DESIGN COMPLETION | Dec 2012 | Jan 2013 | Dec 2012 | Jan 2013
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDISLND | HURRICANE SANDY DAMAGE ROCKAWAY BEACH ENTRY ISLANDS | 4 | CONSTRUCTION START | Jan 2013 | Mar 2013 | Jan 2013 | Mar 2013
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDISLND | HURRICANE SANDY DAMAGE ROCKAWAY BEACH ENTRY ISLANDS | 5 | CONSTRUCTION COMPLETION | Mar 2013 | Aug 2015 | May 2023 | Jun 2031
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDPRFAB | HURRICANE SANDY DAMAGE BEACHFRONT RESTORATION PROJECT | 1 | PROJECT START | Dec 2012 | Dec 2012 | Dec 2012 | Dec 2012
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDPRFAB | HURRICANE SANDY DAMAGE BEACHFRONT RESTORATION PROJECT | 2 | DESIGN START | Dec 2012 | Dec 2012 | Dec 2012 | Dec 2012
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDPRFAB | HURRICANE SANDY DAMAGE BEACHFRONT RESTORATION PROJECT | 3 | DESIGN COMPLETION | Dec 2012 | Jan 2013 | Dec 2012 | Jan 2013
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDPRFAB | HURRICANE SANDY DAMAGE BEACHFRONT RESTORATION PROJECT | 4 | CONSTRUCTION START | Jan 2013 | Mar 2013 | Jan 2013 | Mar 2013
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDPRFAB | HURRICANE SANDY DAMAGE BEACHFRONT RESTORATION PROJECT | 5 | CONSTRUCTION COMPLETION | Mar 2013 | Aug 2015 | Mar 2013 | Jun 2031
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRENO | HURRCANE SANDY DAMAGE STATEN ISLAND BEACHES-VARIOUS | 1 | PROJECT START | Dec 2012 | Dec 2012 | Dec 2012 | Dec 2012
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRENO | HURRCANE SANDY DAMAGE STATEN ISLAND BEACHES-VARIOUS | 2 | DESIGN START | Dec 2012 | Dec 2012 | Dec 2012 | Dec 2012
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRENO | HURRCANE SANDY DAMAGE STATEN ISLAND BEACHES-VARIOUS | 3 | DESIGN COMPLETION | Dec 2012 | Jan 2013 | Dec 2012 | Jan 2013
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRENO | HURRCANE SANDY DAMAGE STATEN ISLAND BEACHES-VARIOUS | 4 | CONSTRUCTION START | Jan 2013 | Mar 2013 | Jan 2013 | Mar 2013
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRENO | HURRCANE SANDY DAMAGE STATEN ISLAND BEACHES-VARIOUS | 5 | CONSTRUCTION COMPLETION | Mar 2013 | Jul 2015 | Dec 2022 | Jun 2031
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM1 | Citywide Resiliency Measures, ESCR, Project Area 1 | 1 | DEVELOP SCOPE | Mar 2018 | May 2018 | Mar 2018 | May 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM1 | Citywide Resiliency Measures, ESCR, Project Area 1 | 2 | PRELIMINARY DESIGN | May 2018 | Sep 2018 | May 2018 | Sep 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM1 | Citywide Resiliency Measures, ESCR, Project Area 1 | 3 | FINAL DESIGN | Sep 2018 | Mar 2019 | Sep 2018 | Mar 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM1 | Citywide Resiliency Measures, ESCR, Project Area 1 | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2019 | Jun 2019 | Mar 2019 | Jun 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM1 | Citywide Resiliency Measures, ESCR, Project Area 1 | 5 | CONSTRUCTION TO 25% | Jun 2019 | Oct 2019 | Jun 2019 | Oct 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM1 | Citywide Resiliency Measures, ESCR, Project Area 1 | 6 | CONSTRUCTION TO 50% | Oct 2019 | Feb 2020 | Oct 2019 | Feb 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM1 | Citywide Resiliency Measures, ESCR, Project Area 1 | 7 | CONSTRUCTION TO 75% | Feb 2020 | Jun 2020 | Feb 2020 | Jun 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM1 | Citywide Resiliency Measures, ESCR, Project Area 1 | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM1 | Citywide Resiliency Measures, ESCR, Project Area 1 | 9 | SUBSTANTIAL COMPLETION | Sep 2020 | Nov 2020 | Sep 2020 | Nov 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM1 | Citywide Resiliency Measures, ESCR, Project Area 1 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2020 | Dec 2020 | Nov 2020 | Jun 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM2 | Citywide Resiliency Measures, ESCR, Project Area 2 | 1 | DEVELOP SCOPE | Dec 2014 | Feb 2015 | Dec 2014 | Feb 2015
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM2 | Citywide Resiliency Measures, ESCR, Project Area 2 | 2 | PRELIMINARY DESIGN | Mar 2015 | Jun 2015 | Mar 2015 | Jun 2015
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM2 | Citywide Resiliency Measures, ESCR, Project Area 2 | 3 | FINAL DESIGN | Jun 2015 | Dec 2015 | Jun 2015 | Dec 2015
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM2 | Citywide Resiliency Measures, ESCR, Project Area 2 | 4 | BID AWARD AND REGISTER CONTRCT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM2 | Citywide Resiliency Measures, ESCR, Project Area 2 | 5 | CONSTRUCTION TO 25% | Mar 2016 | Jul 2016 | Mar 2016 | Jul 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM2 | Citywide Resiliency Measures, ESCR, Project Area 2 | 6 | CONSTRUCTION TO 50% | Jul 2016 | Nov 2016 | Jul 2016 | Nov 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM2 | Citywide Resiliency Measures, ESCR, Project Area 2 | 7 | CONSTRUCTION TO 75% | Nov 2016 | Mar 2017 | Nov 2016 | Mar 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM2 | Citywide Resiliency Measures, ESCR, Project Area 2 | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2017 | Jun 2017 | Mar 2017 | Jun 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM2 | Citywide Resiliency Measures, ESCR, Project Area 2 | 9 | SUBSTANTIAL COMPLETION | Jun 2017 | Aug 2017 | Jun 2017 | Aug 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM2 | Citywide Resiliency Measures, ESCR, Project Area 2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2017 | Jun 2025 | Aug 2017 | Jun 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESPC | Citywide Resiliency Measures, ESCR, Parallel Conveyance | 1 | DEVELOP SCOPE | Mar 2018 | May 2018 | Mar 2018 | May 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESPC | Citywide Resiliency Measures, ESCR, Parallel Conveyance | 2 | PRELIMINARY DESIGN | May 2018 | Sep 2018 | May 2018 | Sep 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESPC | Citywide Resiliency Measures, ESCR, Parallel Conveyance | 3 | FINAL DESIGN | Sep 2018 | Mar 2019 | Sep 2018 | Mar 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESPC | Citywide Resiliency Measures, ESCR, Parallel Conveyance | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2019 | Jun 2019 | Mar 2019 | Jun 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESPC | Citywide Resiliency Measures, ESCR, Parallel Conveyance | 5 | CONSTRUCTION TO 25% | Jun 2019 | Oct 2019 | Jun 2019 | Oct 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESPC | Citywide Resiliency Measures, ESCR, Parallel Conveyance | 6 | CONSTRUCTION TO 50% | Oct 2019 | Feb 2020 | Oct 2019 | Feb 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESPC | Citywide Resiliency Measures, ESCR, Parallel Conveyance | 7 | CONSTRUCTION TO 75% | Feb 2020 | Jun 2020 | Feb 2020 | Jun 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESPC | Citywide Resiliency Measures, ESCR, Parallel Conveyance | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESPC | Citywide Resiliency Measures, ESCR, Parallel Conveyance | 9 | SUBSTANTIAL COMPLETION | Sep 2020 | Nov 2020 | Sep 2020 | Nov 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESPC | Citywide Resiliency Measures, ESCR, Parallel Conveyance | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2020 | Jun 2024 | Nov 2020 | Jun 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDTWOBR | CITYWIDE RESILENCY MEASURES-Lower Manhattan Two Bridges SIRR | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDTWOBR | CITYWIDE RESILENCY MEASURES-Lower Manhattan Two Bridges SIRR | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDTWOBR | CITYWIDE RESILENCY MEASURES-Lower Manhattan Two Bridges SIRR | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDTWOBR | CITYWIDE RESILENCY MEASURES-Lower Manhattan Two Bridges SIRR | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDTWOBR | CITYWIDE RESILENCY MEASURES-Lower Manhattan Two Bridges SIRR | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDTWOBR | CITYWIDE RESILENCY MEASURES-Lower Manhattan Two Bridges SIRR | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDTWOBR | CITYWIDE RESILENCY MEASURES-Lower Manhattan Two Bridges SIRR | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDTWOBR | CITYWIDE RESILENCY MEASURES-Lower Manhattan Two Bridges SIRR | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDTWOBR | CITYWIDE RESILENCY MEASURES-Lower Manhattan Two Bridges SIRR | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDTWOBR | CITYWIDE RESILENCY MEASURES-Lower Manhattan Two Bridges SIRR | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Jun 2025 | Nov 2019 | Jun 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-813 | Storm & San Sewer& WM work in "Jewel Streets"area (HWK1148) | 1 | DEVELOP SCOPE | Jun 2007 | Mar 2008 | Jun 2007 | Sep 2007
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-813 | Storm & San Sewer& WM work in "Jewel Streets"area (HWK1148) | 2 | PRELIMINARY DESIGN | Mar 2008 | Mar 2009 | Sep 2007 | Jan 2008
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-813 | Storm & San Sewer& WM work in "Jewel Streets"area (HWK1148) | 3 | FINAL DESIGN | Mar 2009 | Sep 2010 | Jan 2008 | Jul 2008
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-813 | Storm & San Sewer& WM work in "Jewel Streets"area (HWK1148) | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2010 | Jun 2011 | Mar 2022 | Jun 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-813 | Storm & San Sewer& WM work in "Jewel Streets"area (HWK1148) | 5 | CONSTRUCTION TO 25% | Jun 2011 | Jun 2012 | Jun 2022 | Jun 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-813 | Storm & San Sewer& WM work in "Jewel Streets"area (HWK1148) | 6 | CONSTRUCTION TO 50% | Jun 2012 | May 2013 | Jun 2022 | Jun 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-813 | Storm & San Sewer& WM work in "Jewel Streets"area (HWK1148) | 7 | CONSTRUCTION TO 75% | May 2013 | May 2014 | Jun 2022 | Jun 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-813 | Storm & San Sewer& WM work in "Jewel Streets"area (HWK1148) | 8 | ORIGINAL EQUIP & FURNISHING | May 2014 | Feb 2015 | Jun 2022 | Jun 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-813 | Storm & San Sewer& WM work in "Jewel Streets"area (HWK1148) | 9 | SUBSTANTIAL COMPLETION | Feb 2015 | Aug 2015 | Jun 2022 | Jun 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-813 | Storm & San Sewer& WM work in "Jewel Streets"area (HWK1148) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2015 | Nov 2015 | May 2024 | Jun 2031
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEBLQX01 | Reconstruction of existing sewers from back log QN & BX | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEBLQX01 | Reconstruction of existing sewers from back log QN & BX | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEBLQX01 | Reconstruction of existing sewers from back log QN & BX | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEBLQX01 | Reconstruction of existing sewers from back log QN & BX | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEBLQX01 | Reconstruction of existing sewers from back log QN & BX | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEBLQX01 | Reconstruction of existing sewers from back log QN & BX | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEBLQX01 | Reconstruction of existing sewers from back log QN & BX | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | May 2024 | Sep 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEBLQX01 | Reconstruction of existing sewers from back log QN & BX | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEBLQX01 | Reconstruction of existing sewers from back log QN & BX | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Dec 2024 | Feb 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEBLQX01 | Reconstruction of existing sewers from back log QN & BX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Mar 2025 | Feb 2025 | Mar 2029
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC09 | SEWER LINING CONTRACT, CITYWIDE | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC09 | SEWER LINING CONTRACT, CITYWIDE | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC09 | SEWER LINING CONTRACT, CITYWIDE | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC09 | SEWER LINING CONTRACT, CITYWIDE | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC09 | SEWER LINING CONTRACT, CITYWIDE | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC09 | SEWER LINING CONTRACT, CITYWIDE | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC09 | SEWER LINING CONTRACT, CITYWIDE | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC09 | SEWER LINING CONTRACT, CITYWIDE | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC09 | SEWER LINING CONTRACT, CITYWIDE | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC09 | SEWER LINING CONTRACT, CITYWIDE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Jun 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC10 | SEWER LINING CONTRACT, CITYWIDE | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Aug 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC10 | SEWER LINING CONTRACT, CITYWIDE | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC10 | SEWER LINING CONTRACT, CITYWIDE | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC10 | SEWER LINING CONTRACT, CITYWIDE | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC10 | SEWER LINING CONTRACT, CITYWIDE | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC10 | SEWER LINING CONTRACT, CITYWIDE | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2022 | May 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC10 | SEWER LINING CONTRACT, CITYWIDE | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2022 | Sep 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC10 | SEWER LINING CONTRACT, CITYWIDE | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC10 | SEWER LINING CONTRACT, CITYWIDE | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2022 | Feb 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC10 | SEWER LINING CONTRACT, CITYWIDE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Feb 2023 | Mar 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC10 | SEWER LINING CONTRACT, CITYWIDE | 11 | PROJECT START | Feb 2023 | Mar 2023 | Mar 2023 | Mar 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC10 | SEWER LINING CONTRACT, CITYWIDE | 12 | DESIGN START | Feb 2023 | Mar 2023 | Mar 2023 | Mar 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC10 | SEWER LINING CONTRACT, CITYWIDE | 13 | DESIGN COMPLETION | Feb 2023 | Mar 2023 | Mar 2023 | Mar 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC10 | SEWER LINING CONTRACT, CITYWIDE | 14 | CONSTRUCTION START | Feb 2023 | Mar 2023 | Mar 2023 | Mar 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC10 | SEWER LINING CONTRACT, CITYWIDE | 15 | CONSTRUCTION COMPLETION | Feb 2023 | Mar 2023 | Mar 2023 | Jun 2029
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC11 | DDC Sewer Lining Contract, Citywide | 1 | DEVELOP SCOPE | Aug 2022 | May 2023 | Aug 2022 | May 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC11 | DDC Sewer Lining Contract, Citywide | 2 | PRELIMINARY DESIGN | May 2023 | May 2024 | May 2023 | May 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC11 | DDC Sewer Lining Contract, Citywide | 3 | FINAL DESIGN | May 2024 | Nov 2025 | May 2024 | Nov 2025
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC11 | DDC Sewer Lining Contract, Citywide | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2025 | Jul 2026 | Nov 2025 | Jul 2026
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC11 | DDC Sewer Lining Contract, Citywide | 5 | CONSTRUCTION TO 25% | Aug 2026 | Jul 2027 | Aug 2026 | Jul 2027
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC11 | DDC Sewer Lining Contract, Citywide | 6 | CONSTRUCTION TO 50% | Jul 2027 | Jul 2028 | Jul 2027 | Jul 2028
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC11 | DDC Sewer Lining Contract, Citywide | 7 | CONSTRUCTION TO 75% | Jul 2028 | Jul 2029 | Jul 2028 | Jul 2029
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC11 | DDC Sewer Lining Contract, Citywide | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2029 | Apr 2030 | Jul 2029 | Apr 2030
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC11 | DDC Sewer Lining Contract, Citywide | 9 | SUBSTANTIAL COMPLETION | Apr 2030 | Oct 2030 | Apr 2030 | Oct 2030
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC11 | DDC Sewer Lining Contract, Citywide | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2030 | Jan 2031 | Oct 2030 | Jan 2031
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SETVDDC16 | CLEANING AND TELEVISING OF SEWERS BY DDC | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Aug 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SETVDDC16 | CLEANING AND TELEVISING OF SEWERS BY DDC | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SETVDDC16 | CLEANING AND TELEVISING OF SEWERS BY DDC | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SETVDDC16 | CLEANING AND TELEVISING OF SEWERS BY DDC | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SETVDDC16 | CLEANING AND TELEVISING OF SEWERS BY DDC | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SETVDDC16 | CLEANING AND TELEVISING OF SEWERS BY DDC | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2022 | May 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SETVDDC16 | CLEANING AND TELEVISING OF SEWERS BY DDC | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2022 | Sep 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SETVDDC16 | CLEANING AND TELEVISING OF SEWERS BY DDC | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SETVDDC16 | CLEANING AND TELEVISING OF SEWERS BY DDC | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2022 | Feb 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SETVDDC16 | CLEANING AND TELEVISING OF SEWERS BY DDC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Feb 2023 | Mar 2030
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002271 | Upgrade combined sewer Franklin ave- other Locs HWTRQX1 | 1 | DEVELOP SCOPE | May 2018 | Jul 2018 | May 2018 | Jul 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002271 | Upgrade combined sewer Franklin ave- other Locs HWTRQX1 | 2 | PRELIMINARY DESIGN | Jul 2018 | Nov 2018 | Jul 2018 | Nov 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002271 | Upgrade combined sewer Franklin ave- other Locs HWTRQX1 | 3 | FINAL DESIGN | Nov 2018 | May 2019 | Nov 2018 | May 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002271 | Upgrade combined sewer Franklin ave- other Locs HWTRQX1 | 4 | BID AWARD AND REGISTER CONTRCT | May 2019 | Aug 2019 | May 2019 | Aug 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002271 | Upgrade combined sewer Franklin ave- other Locs HWTRQX1 | 5 | CONSTRUCTION TO 25% | Aug 2019 | Dec 2019 | Aug 2019 | Dec 2019
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002271 | Upgrade combined sewer Franklin ave- other Locs HWTRQX1 | 6 | CONSTRUCTION TO 50% | Dec 2019 | Apr 2020 | Dec 2019 | Apr 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002271 | Upgrade combined sewer Franklin ave- other Locs HWTRQX1 | 7 | CONSTRUCTION TO 75% | Apr 2020 | Aug 2020 | Apr 2020 | Aug 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002271 | Upgrade combined sewer Franklin ave- other Locs HWTRQX1 | 8 | ORIGINAL EQUIP & FURNISHING | Aug 2020 | Nov 2020 | Aug 2020 | Nov 2020
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002271 | Upgrade combined sewer Franklin ave- other Locs HWTRQX1 | 9 | SUBSTANTIAL COMPLETION | Nov 2020 | Jan 2021 | Nov 2020 | Jan 2021
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002271 | Upgrade combined sewer Franklin ave- other Locs HWTRQX1 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2021 | Feb 2021 | Jan 2021 | Jun 2024
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | WM-LC-17 | Citywide Lining Contract for Water Mains | 1 | DEVELOP SCOPE | Mar 2016 | May 2016 | Mar 2016 | May 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | WM-LC-17 | Citywide Lining Contract for Water Mains | 2 | PRELIMINARY DESIGN | May 2016 | Sep 2016 | May 2016 | Sep 2016
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | WM-LC-17 | Citywide Lining Contract for Water Mains | 3 | FINAL DESIGN | Sep 2016 | Mar 2017 | Sep 2016 | Mar 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | WM-LC-17 | Citywide Lining Contract for Water Mains | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2017 | Jun 2017 | Mar 2017 | Jun 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | WM-LC-17 | Citywide Lining Contract for Water Mains | 5 | CONSTRUCTION TO 25% | Jun 2017 | Oct 2017 | Jun 2017 | Oct 2017
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | WM-LC-17 | Citywide Lining Contract for Water Mains | 6 | CONSTRUCTION TO 50% | Oct 2017 | Feb 2018 | Oct 2017 | Feb 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | WM-LC-17 | Citywide Lining Contract for Water Mains | 7 | CONSTRUCTION TO 75% | Feb 2018 | Jun 2018 | Feb 2018 | Jun 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | WM-LC-17 | Citywide Lining Contract for Water Mains | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | WM-LC-17 | Citywide Lining Contract for Water Mains | 9 | SUBSTANTIAL COMPLETION | Sep 2018 | Nov 2018 | Sep 2018 | Nov 2018
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | WM-LC-17 | Citywide Lining Contract for Water Mains | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2018 | Dec 2018 | Nov 2018 | Jun 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | WM-LC-17 | Citywide Lining Contract for Water Mains | 11 | PROJECT START | Nov 2018 | Dec 2018 | Jun 2023 | Jun 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | WM-LC-17 | Citywide Lining Contract for Water Mains | 12 | DESIGN START | Nov 2018 | Dec 2018 | Jun 2023 | Jun 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | WM-LC-17 | Citywide Lining Contract for Water Mains | 13 | DESIGN COMPLETION | Nov 2018 | Dec 2018 | Jun 2023 | Jun 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | WM-LC-17 | Citywide Lining Contract for Water Mains | 14 | CONSTRUCTION START | Nov 2018 | Dec 2018 | Jun 2023 | Jun 2023
20231026 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | WM-LC-17 | Citywide Lining Contract for Water Mains | 15 | CONSTRUCTION COMPLETION | Nov 2018 | Dec 2018 | Jun 2023 | Jun 2025
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP211 | DEP - Modifications at East Delaware Tunnel - Neversink | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2023 | Jun 2023 | Jun 2023
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP211 | DEP - Modifications at East Delaware Tunnel - Neversink | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP211 | DEP - Modifications at East Delaware Tunnel - Neversink | 3 | CONSTRUCTION TO 50% | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP211 | DEP - Modifications at East Delaware Tunnel - Neversink | 4 | CONSTRUCTION TO 75% | Feb 2024 | May 2024 | Feb 2024 | May 2024
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP211 | DEP - Modifications at East Delaware Tunnel - Neversink | 5 | SUBSTANTIAL COMPLETION | May 2024 | Jul 2024 | May 2024 | Jul 2024
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP211 | DEP - Modifications at East Delaware Tunnel - Neversink | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264CADA | CITYWIDE COURTS ADA LUMP SUM | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | May 2025 | Aug 2025
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264CADA | CITYWIDE COURTS ADA LUMP SUM | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2025 | Dec 2025
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264CADA | CITYWIDE COURTS ADA LUMP SUM | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2025 | Jun 2026
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264CADA | CITYWIDE COURTS ADA LUMP SUM | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2026 | Sep 2026
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264CADA | CITYWIDE COURTS ADA LUMP SUM | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264CADA | CITYWIDE COURTS ADA LUMP SUM | 6 | CONSTRUCTION TO 50% | Jan 2026 | May 2026 | Jan 2026 | May 2026
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264CADA | CITYWIDE COURTS ADA LUMP SUM | 7 | CONSTRUCTION TO 75% | May 2027 | Sep 2027 | May 2027 | Sep 2027
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264CADA | CITYWIDE COURTS ADA LUMP SUM | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2027 | Dec 2027 | Sep 2027 | Dec 2027
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264CADA | CITYWIDE COURTS ADA LUMP SUM | 9 | SUBSTANTIAL COMPLETION | Dec 2027 | Feb 2028 | Dec 2027 | Feb 2028
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264CADA | CITYWIDE COURTS ADA LUMP SUM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2028 | Mar 2028 | Feb 2028 | Mar 2031
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264DCAS | REHABILITATION OF VARIOUS COURT FACILITES | 1 | DEVELOP SCOPE | Mar 2011 | Jun 2011 | Jun 2021 | Aug 2021
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264DCAS | REHABILITATION OF VARIOUS COURT FACILITES | 2 | PRELIMINARY DESIGN | Jun 2011 | Jun 2012 | Aug 2021 | Aug 2022
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264DCAS | REHABILITATION OF VARIOUS COURT FACILITES | 3 | FINAL DESIGN | Jun 2012 | Jun 2013 | Aug 2022 | Aug 2023
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264DCAS | REHABILITATION OF VARIOUS COURT FACILITES | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2013 | May 2014 | Aug 2023 | Aug 2024
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264DCAS | REHABILITATION OF VARIOUS COURT FACILITES | 5 | CONSTRUCTION TO 25% | May 2014 | May 2015 | Jun 2026 | May 2027
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264DCAS | REHABILITATION OF VARIOUS COURT FACILITES | 6 | CONSTRUCTION TO 50% | May 2015 | May 2016 | May 2027 | May 2028
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264DCAS | REHABILITATION OF VARIOUS COURT FACILITES | 7 | CONSTRUCTION TO 75% | May 2016 | May 2017 | May 2028 | May 2029
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264DCAS | REHABILITATION OF VARIOUS COURT FACILITES | 8 | ORIGINAL EQUIP & FURNISHING | May 2017 | May 2018 | May 2029 | May 2030
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264DCAS | REHABILITATION OF VARIOUS COURT FACILITES | 9 | SUBSTANTIAL COMPLETION | May 2018 | Apr 2020 | May 2030 | Apr 2032
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264DCAS | REHABILITATION OF VARIOUS COURT FACILITES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2020 | Apr 2021 | Apr 2032 | Apr 2033
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-ADA | VARIOUS COURTS BUILDINGS - ADA WORK | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-ADA | VARIOUS COURTS BUILDINGS - ADA WORK | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-ADA | VARIOUS COURTS BUILDINGS - ADA WORK | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-ADA | VARIOUS COURTS BUILDINGS - ADA WORK | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-ADA | VARIOUS COURTS BUILDINGS - ADA WORK | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-ADA | VARIOUS COURTS BUILDINGS - ADA WORK | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-ADA | VARIOUS COURTS BUILDINGS - ADA WORK | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | May 2024 | Sep 2024
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-ADA | VARIOUS COURTS BUILDINGS - ADA WORK | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-ADA | VARIOUS COURTS BUILDINGS - ADA WORK | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Dec 2024 | Feb 2025
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-ADA | VARIOUS COURTS BUILDINGS - ADA WORK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Mar 2025 | Feb 2025 | Jun 2031
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-HVAC | VARIOUS PUBLIC BUILDINGS - COURTS HVAC UPGRADES | 1 | DEVELOP SCOPE | Jun 2024 | Aug 2024 | Jun 2024 | Aug 2024
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-HVAC | VARIOUS PUBLIC BUILDINGS - COURTS HVAC UPGRADES | 2 | PRELIMINARY DESIGN | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-HVAC | VARIOUS PUBLIC BUILDINGS - COURTS HVAC UPGRADES | 3 | FINAL DESIGN | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-HVAC | VARIOUS PUBLIC BUILDINGS - COURTS HVAC UPGRADES | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-HVAC | VARIOUS PUBLIC BUILDINGS - COURTS HVAC UPGRADES | 5 | CONSTRUCTION TO 25% | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-HVAC | VARIOUS PUBLIC BUILDINGS - COURTS HVAC UPGRADES | 6 | CONSTRUCTION TO 50% | Jan 2026 | May 2026 | Jan 2026 | May 2026
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-HVAC | VARIOUS PUBLIC BUILDINGS - COURTS HVAC UPGRADES | 7 | CONSTRUCTION TO 75% | May 2026 | Sep 2026 | May 2026 | Sep 2026
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-HVAC | VARIOUS PUBLIC BUILDINGS - COURTS HVAC UPGRADES | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2026 | Dec 2026 | Sep 2026 | Dec 2026
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-HVAC | VARIOUS PUBLIC BUILDINGS - COURTS HVAC UPGRADES | 9 | SUBSTANTIAL COMPLETION | Dec 2026 | Feb 2027 | Dec 2026 | Feb 2027
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-HVAC | VARIOUS PUBLIC BUILDINGS - COURTS HVAC UPGRADES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2027 | Mar 2027 | Feb 2027 | Mar 2031
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5 | VARIOUS PUBLIC BUILDINGS - COURTS FIRE/LIFE SAFETY | 1 | DEVELOP SCOPE | Jun 2024 | Aug 2024 | Jun 2024 | Aug 2024
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5 | VARIOUS PUBLIC BUILDINGS - COURTS FIRE/LIFE SAFETY | 2 | PRELIMINARY DESIGN | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5 | VARIOUS PUBLIC BUILDINGS - COURTS FIRE/LIFE SAFETY | 3 | FINAL DESIGN | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5 | VARIOUS PUBLIC BUILDINGS - COURTS FIRE/LIFE SAFETY | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5 | VARIOUS PUBLIC BUILDINGS - COURTS FIRE/LIFE SAFETY | 5 | CONSTRUCTION TO 25% | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5 | VARIOUS PUBLIC BUILDINGS - COURTS FIRE/LIFE SAFETY | 6 | CONSTRUCTION TO 50% | Jan 2026 | May 2026 | Jan 2026 | May 2026
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5 | VARIOUS PUBLIC BUILDINGS - COURTS FIRE/LIFE SAFETY | 7 | CONSTRUCTION TO 75% | May 2026 | Sep 2026 | May 2026 | Sep 2026
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5 | VARIOUS PUBLIC BUILDINGS - COURTS FIRE/LIFE SAFETY | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2026 | Dec 2026 | Sep 2026 | Dec 2026
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5 | VARIOUS PUBLIC BUILDINGS - COURTS FIRE/LIFE SAFETY | 9 | SUBSTANTIAL COMPLETION | Dec 2026 | Feb 2027 | Dec 2026 | Feb 2027
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5 | VARIOUS PUBLIC BUILDINGS - COURTS FIRE/LIFE SAFETY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2027 | Mar 2027 | Feb 2027 | Jun 2030
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5FS | VARIOUS PUBLIC BUILDINGS - COURTS FIRE SUPPRESSION DETECTION | 1 | DEVELOP SCOPE | Jun 2024 | Aug 2024 | Jun 2024 | Aug 2024
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5FS | VARIOUS PUBLIC BUILDINGS - COURTS FIRE SUPPRESSION DETECTION | 2 | PRELIMINARY DESIGN | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5FS | VARIOUS PUBLIC BUILDINGS - COURTS FIRE SUPPRESSION DETECTION | 3 | FINAL DESIGN | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5FS | VARIOUS PUBLIC BUILDINGS - COURTS FIRE SUPPRESSION DETECTION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5FS | VARIOUS PUBLIC BUILDINGS - COURTS FIRE SUPPRESSION DETECTION | 5 | CONSTRUCTION TO 25% | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5FS | VARIOUS PUBLIC BUILDINGS - COURTS FIRE SUPPRESSION DETECTION | 6 | CONSTRUCTION TO 50% | Jan 2026 | May 2026 | Jan 2026 | May 2026
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5FS | VARIOUS PUBLIC BUILDINGS - COURTS FIRE SUPPRESSION DETECTION | 7 | CONSTRUCTION TO 75% | May 2026 | Sep 2026 | May 2026 | Sep 2026
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5FS | VARIOUS PUBLIC BUILDINGS - COURTS FIRE SUPPRESSION DETECTION | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2026 | Dec 2026 | Sep 2026 | Dec 2026
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5FS | VARIOUS PUBLIC BUILDINGS - COURTS FIRE SUPPRESSION DETECTION | 9 | SUBSTANTIAL COMPLETION | Dec 2026 | Feb 2027 | Dec 2026 | Feb 2027
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5FS | VARIOUS PUBLIC BUILDINGS - COURTS FIRE SUPPRESSION DETECTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2027 | Mar 2027 | Feb 2027 | Mar 2031
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | F175-ES49 | Construction EMS 49 | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | F175-ES49 | Construction EMS 49 | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | F175-ES49 | Construction EMS 49 | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | F175-ES49 | Construction EMS 49 | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | F175-ES49 | Construction EMS 49 | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | F175-ES49 | Construction EMS 49 | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | F175-ES49 | Construction EMS 49 | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | May 2024 | Sep 2024
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | F175-ES49 | Construction EMS 49 | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | F175-ES49 | Construction EMS 49 | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Dec 2024 | Feb 2025
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | F175-ES49 | Construction EMS 49 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Mar 2025 | Feb 2025 | Mar 2025
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PT195-VAR | VARIOUS WATERFRONT PROPERTIES- RECONSTRUCTION | 1 | DEVELOP SCOPE | Jun 2021 | Aug 2021 | Jun 2021 | Aug 2021
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PT195-VAR | VARIOUS WATERFRONT PROPERTIES- RECONSTRUCTION | 2 | PRELIMINARY DESIGN | Aug 2021 | Dec 2021 | Aug 2021 | Dec 2021
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PT195-VAR | VARIOUS WATERFRONT PROPERTIES- RECONSTRUCTION | 3 | FINAL DESIGN | Dec 2021 | Jun 2022 | Dec 2021 | Jun 2022
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PT195-VAR | VARIOUS WATERFRONT PROPERTIES- RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PT195-VAR | VARIOUS WATERFRONT PROPERTIES- RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PT195-VAR | VARIOUS WATERFRONT PROPERTIES- RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | Jan 2023 | May 2023 | Jan 2023 | May 2023
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PT195-VAR | VARIOUS WATERFRONT PROPERTIES- RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | May 2023 | Sep 2023 | May 2023 | Sep 2023
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PT195-VAR | VARIOUS WATERFRONT PROPERTIES- RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Dec 2023 | Sep 2023 | Dec 2023
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PT195-VAR | VARIOUS WATERFRONT PROPERTIES- RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | Dec 2023 | Feb 2024 | Dec 2023 | Feb 2024
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PT195-VAR | VARIOUS WATERFRONT PROPERTIES- RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2024 | Mar 2031 | Feb 2024 | Mar 2031
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW335ASB4 | VARIOUS PUBLIC BUILDINGS- ENVIRONMENTAL REMEDIATION | 1 | DEVELOP SCOPE | Oct 2005 | Dec 2005 | Oct 2005 | Dec 2005
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW335ASB4 | VARIOUS PUBLIC BUILDINGS- ENVIRONMENTAL REMEDIATION | 2 | PRELIMINARY DESIGN | Dec 2005 | Apr 2006 | Dec 2005 | Apr 2006
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW335ASB4 | VARIOUS PUBLIC BUILDINGS- ENVIRONMENTAL REMEDIATION | 3 | FINAL DESIGN | Apr 2006 | Oct 2006 | Apr 2006 | Oct 2006
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW335ASB4 | VARIOUS PUBLIC BUILDINGS- ENVIRONMENTAL REMEDIATION | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2006 | Jan 2007 | Oct 2006 | Jan 2007
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW335ASB4 | VARIOUS PUBLIC BUILDINGS- ENVIRONMENTAL REMEDIATION | 5 | CONSTRUCTION TO 25% | Jan 2007 | Sep 2009 | Jan 2007 | Sep 2009
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW335ASB4 | VARIOUS PUBLIC BUILDINGS- ENVIRONMENTAL REMEDIATION | 6 | CONSTRUCTION TO 50% | Sep 2009 | Apr 2012 | Jun 2022 | Oct 2022
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW335ASB4 | VARIOUS PUBLIC BUILDINGS- ENVIRONMENTAL REMEDIATION | 7 | CONSTRUCTION TO 75% | Apr 2012 | Dec 2014 | Oct 2022 | Jun 2025
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW335ASB4 | VARIOUS PUBLIC BUILDINGS- ENVIRONMENTAL REMEDIATION | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2014 | Dec 2015 | Jun 2025 | Jun 2026
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW335ASB4 | VARIOUS PUBLIC BUILDINGS- ENVIRONMENTAL REMEDIATION | 9 | SUBSTANTIAL COMPLETION | Dec 2015 | Dec 2016 | Jun 2026 | Jun 2027
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW335ASB4 | VARIOUS PUBLIC BUILDINGS- ENVIRONMENTAL REMEDIATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2016 | Dec 2016 | Jun 2027 | Jul 2027
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CJC | Community Justice Center | 1 | DEVELOP SCOPE | Jan 2017 | Mar 2017 | Jun 2027 | Aug 2027
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CJC | Community Justice Center | 2 | PRELIMINARY DESIGN | Apr 2017 | Jul 2017 | Aug 2027 | Dec 2027
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CJC | Community Justice Center | 3 | FINAL DESIGN | Jul 2017 | Jan 2018 | Dec 2027 | Jun 2028
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CJC | Community Justice Center | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2018 | Apr 2018 | Jun 2028 | Sep 2028
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CJC | Community Justice Center | 5 | CONSTRUCTION TO 25% | Apr 2018 | Aug 2018 | Sep 2028 | Jan 2029
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CJC | Community Justice Center | 6 | CONSTRUCTION TO 50% | Aug 2018 | Dec 2018 | Jan 2029 | May 2029
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CJC | Community Justice Center | 7 | CONSTRUCTION TO 75% | Dec 2018 | Apr 2019 | May 2029 | Sep 2029
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CJC | Community Justice Center | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2019 | Jul 2019 | Sep 2029 | Dec 2029
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CJC | Community Justice Center | 9 | SUBSTANTIAL COMPLETION | Jul 2019 | Sep 2019 | Dec 2029 | Feb 2030
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CJC | Community Justice Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Oct 2019 | Feb 2030 | Mar 2031
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77NG911 | DoITT Next Generation 911 and SDE Expansion | 1 | DEVELOP SCOPE | Jun 2021 | Aug 2021 | Jun 2021 | Aug 2021
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77NG911 | DoITT Next Generation 911 and SDE Expansion | 2 | PRELIMINARY DESIGN | Aug 2021 | Dec 2021 | Aug 2021 | Dec 2021
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77NG911 | DoITT Next Generation 911 and SDE Expansion | 3 | FINAL DESIGN | Dec 2021 | Jun 2022 | Dec 2021 | Jun 2022
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77NG911 | DoITT Next Generation 911 and SDE Expansion | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77NG911 | DoITT Next Generation 911 and SDE Expansion | 5 | CONSTRUCTION TO 25% | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77NG911 | DoITT Next Generation 911 and SDE Expansion | 6 | CONSTRUCTION TO 50% | Jan 2023 | May 2023 | Jan 2023 | May 2023
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77NG911 | DoITT Next Generation 911 and SDE Expansion | 7 | CONSTRUCTION TO 75% | May 2023 | Sep 2023 | May 2023 | Sep 2023
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77NG911 | DoITT Next Generation 911 and SDE Expansion | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Dec 2023 | Sep 2023 | Dec 2023
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77NG911 | DoITT Next Generation 911 and SDE Expansion | 9 | SUBSTANTIAL COMPLETION | Dec 2023 | Feb 2024 | Dec 2023 | Feb 2024
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77NG911 | DoITT Next Generation 911 and SDE Expansion | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2024 | Mar 2024 | Feb 2024 | Mar 2024
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SECAM | SECURITY CAMERAS - DCAS PUBLIC BUILDINGS | 1 | DEVELOP SCOPE | Apr 2011 | Jun 2011 | Apr 2011 | Jun 2011
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SECAM | SECURITY CAMERAS - DCAS PUBLIC BUILDINGS | 2 | PRELIMINARY DESIGN | Jun 2011 | Oct 2011 | Jun 2011 | Oct 2011
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SECAM | SECURITY CAMERAS - DCAS PUBLIC BUILDINGS | 3 | FINAL DESIGN | Oct 2011 | Apr 2012 | Oct 2011 | Apr 2012
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SECAM | SECURITY CAMERAS - DCAS PUBLIC BUILDINGS | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2012 | Jul 2012 | Apr 2012 | Jul 2012
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SECAM | SECURITY CAMERAS - DCAS PUBLIC BUILDINGS | 5 | CONSTRUCTION TO 25% | Jul 2012 | Nov 2012 | Jun 2028 | Sep 2028
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SECAM | SECURITY CAMERAS - DCAS PUBLIC BUILDINGS | 6 | CONSTRUCTION TO 50% | Nov 2012 | Mar 2013 | Sep 2028 | Jan 2029
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SECAM | SECURITY CAMERAS - DCAS PUBLIC BUILDINGS | 7 | CONSTRUCTION TO 75% | Mar 2013 | Jul 2013 | Jan 2029 | May 2029
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SECAM | SECURITY CAMERAS - DCAS PUBLIC BUILDINGS | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2013 | Oct 2013 | May 2029 | Aug 2029
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SECAM | SECURITY CAMERAS - DCAS PUBLIC BUILDINGS | 9 | SUBSTANTIAL COMPLETION | Oct 2013 | Oct 2014 | Aug 2029 | Aug 2030
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SECAM | SECURITY CAMERAS - DCAS PUBLIC BUILDINGS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2014 | Oct 2015 | Aug 2030 | Aug 2031
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCOMPDA2 | Comptroller's Office Data Center Replacement at 1 Centre St. | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Aug 2020
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCOMPDA2 | Comptroller's Office Data Center Replacement at 1 Centre St. | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCOMPDA2 | Comptroller's Office Data Center Replacement at 1 Centre St. | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCOMPDA2 | Comptroller's Office Data Center Replacement at 1 Centre St. | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCOMPDA2 | Comptroller's Office Data Center Replacement at 1 Centre St. | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCOMPDA2 | Comptroller's Office Data Center Replacement at 1 Centre St. | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2022 | May 2022
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCOMPDA2 | Comptroller's Office Data Center Replacement at 1 Centre St. | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2022 | Sep 2022
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCOMPDA2 | Comptroller's Office Data Center Replacement at 1 Centre St. | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCOMPDA2 | Comptroller's Office Data Center Replacement at 1 Centre St. | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2022 | Feb 2023
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCOMPDA2 | Comptroller's Office Data Center Replacement at 1 Centre St. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Feb 2023 | Aug 2024
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARGR4 | NYPA - SOLAR PARKING | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2020 | Jun 2020 | Jun 2020
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARGR4 | NYPA - SOLAR PARKING | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Aug 2020 | Jul 2020 | Aug 2020
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARGR4 | NYPA - SOLAR PARKING | 3 | CONSTRUCTION TO 50% | Aug 2020 | Feb 2021 | Aug 2020 | Feb 2021
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARGR4 | NYPA - SOLAR PARKING | 4 | CONSTRUCTION TO 75% | Feb 2021 | Jun 2023 | Feb 2021 | Jun 2023
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARGR4 | NYPA - SOLAR PARKING | 5 | SUBSTANTIAL COMPLETION | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARGR4 | NYPA - SOLAR PARKING | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2023 | Sep 2023 | Aug 2023 | Sep 2025
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC17DRBR | DYKER INTERIOR RENOVATION | 1 | DESIGN | Jul 2020 | Jun 2021 | Jun 2025 | Jun 2026
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC17DRBR | DYKER INTERIOR RENOVATION | 2 | CONSTRUCTION | Jul 2021 | Dec 2021 | Jun 2026 | Dec 2026
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC18FHSG | FT HAMILTON ROOF | 1 | DESIGN | Jul 2019 | Jun 2020 | Jul 2024 | Jun 2025
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC18FHSG | FT HAMILTON ROOF | 2 | CONSTRUCTION | Jun 2020 | Dec 2020 | Jul 2025 | Dec 2025
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC19CHEL | Clinton Hill Wiring Upgrade | 1 | DESIGN | Sep 2019 | Jun 2021 | Sep 2023 | Jun 2025
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC19CHEL | Clinton Hill Wiring Upgrade | 2 | CONSTRUCTION | Jul 2021 | Jul 2022 | Jul 2025 | Jul 2026
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC20MPMR | MCKINLEY PARK MEETING ROOM | 1 | DESIGN | Jun 2025 | May 2026 | Jun 2025 | May 2026
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC20MPMR | MCKINLEY PARK MEETING ROOM | 2 | CONSTRUCTION | Jun 2026 | Nov 2026 | Jun 2026 | Nov 2026
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC21MNRF | Macon HVAC, BMS & Roof Replacement | 1 | DESIGN | Dec 2023 | Dec 2024 | Dec 2023 | Dec 2024
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC21MNRF | Macon HVAC, BMS & Roof Replacement | 2 | CONSTRUCTION | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC22CDEL | CLARENDON ELECTRICAL UPGRADE | 1 | DESIGN | Jun 2025 | May 2026 | Jun 2025 | May 2026
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC22CDEL | CLARENDON ELECTRICAL UPGRADE | 2 | CONSTRUCTION | Jun 2026 | Nov 2026 | Jun 2026 | Nov 2026
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC22CDOD | COURTELYOU OUTDOOR PLAZA & ROOF | 1 | DESIGN | Jun 2024 | Jun 2025 | Jun 2024 | Jun 2025
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC22CDOD | COURTELYOU OUTDOOR PLAZA & ROOF | 2 | CONSTRUCTION | Jun 2025 | Dec 2025 | Jun 2025 | Dec 2025
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC22JBIF | JAMAICA BAY INFRASTRUCTURE UPGRADE | 1 | DESIGN | Jun 2023 | May 2024 | Jun 2023 | May 2024
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC22JBIF | JAMAICA BAY INFRASTRUCTURE UPGRADE | 2 | CONSTRUCTION | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC23GSBR | GRAVESEND INTERIOR RENOVATION | 1 | DESIGN | Jul 2026 | Jun 2027 | Jul 2026 | Jun 2027
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC23GSBR | GRAVESEND INTERIOR RENOVATION | 2 | CONSTRUCTION | Jul 2027 | Dec 2027 | Jul 2027 | Dec 2027
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBCENP2B | CENTRAL RENOVATION - PHASE 2B | 1 | DESIGN | Jun 2027 | Jun 2028 | Jun 2027 | Jun 2028
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBCENP2B | CENTRAL RENOVATION - PHASE 2B | 2 | CONSTRUCTION | Jun 2028 | Dec 2028 | Jun 2028 | Dec 2028
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBCENPH2 | CENTRAL RENOVATION - PHASE 2A | 1 | DESIGN | Jul 2020 | Jun 2021 | Jul 2024 | Jun 2025
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBCENPH2 | CENTRAL RENOVATION - PHASE 2A | 2 | CONSTRUCTION | Jul 2021 | Dec 2021 | Jul 2025 | Dec 2026
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBEM05SWR | SYSTEM-WIDE FUNDING | 1 | DESIGN | Sep 2019 | Sep 2020 | Jun 2023 | Jun 2024
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBEM05SWR | SYSTEM-WIDE FUNDING | 2 | CONSTRUCTION | Sep 2020 | Jul 2022 | Jun 2024 | Apr 2026
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBK16HLRF | Highlawn - Roof Replacement | 1 | DESIGN | Sep 2019 | Sep 2020 | Jun 2024 | Jun 2025
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBK16HLRF | Highlawn - Roof Replacement | 2 | CONSTRUCTION | Sep 2020 | Mar 2021 | Jun 2025 | Dec 2025
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBK16SCRF | SPRING CREEK ROOF REPLACEMENT | 1 | DESIGN | Sep 2019 | Sep 2020 | Jun 2024 | May 2025
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBK16SCRF | SPRING CREEK ROOF REPLACEMENT | 2 | CONSTRUCTION | Sep 2020 | Jul 2022 | Jun 2025 | Nov 2025
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBK22BRHC | Bay Ridge - Heating & Cooling Upgrade | 1 | DESIGN | Jun 2022 | Jun 2023 | Jun 2024 | Jun 2025
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBK22BRHC | Bay Ridge - Heating & Cooling Upgrade | 2 | CONSTRUCTION | Jun 2023 | Dec 2023 | Jun 2025 | Dec 2025
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBM18NLOH | New Lots Overhaul | 1 | DESIGN | Jan 2020 | Dec 2020 | Jan 2027 | Dec 2027
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBM18NLOH | New Lots Overhaul | 2 | CONSTRUCTION | Dec 2020 | Jun 2023 | Jan 2026 | Jun 2027
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBM19CAOH | Canarsie Overhaul | 1 | DESIGN | Jul 2020 | Jun 2021 | Jun 2027 | May 2028
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBM19CAOH | Canarsie Overhaul | 2 | CONSTRUCTION | Jul 2021 | Jul 2023 | May 2028 | Nov 2028
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBM22PCOH | PACIFIC OVERHAUL | 1 | DESIGN | Jul 2026 | Jun 2027 | Jul 2026 | Jun 2027
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBM22PCOH | PACIFIC OVERHAUL | 2 | CONSTRUCTION | Jul 2027 | Dec 2027 | Jul 2027 | Dec 2027
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBM22WWBR | Walt Whitman Branch Overhaul | 1 | DESIGN | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBM22WWBR | Walt Whitman Branch Overhaul | 2 | CONSTRUCTION | Jun 2026 | Dec 2026 | Jun 2026 | Dec 2026
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBP18PCAD | PACIFIC ADA COMPLIANCE | 1 | DESIGN | Jul 2020 | Jun 2021 | Jun 2024 | Jun 2025
20231026 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBP18PCAD | PACIFIC ADA COMPLIANCE | 2 | CONSTRUCTION | Jul 2021 | Jul 2022 | Jun 2025 | Jun 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ACECUN214 | CUNY - Portfolio Submetering - Kingsborough CC | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2023 | Jun 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ACECUN214 | CUNY - Portfolio Submetering - Kingsborough CC | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ACECUN214 | CUNY - Portfolio Submetering - Kingsborough CC | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ACECUN214 | CUNY - Portfolio Submetering - Kingsborough CC | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ACECUN214 | CUNY - Portfolio Submetering - Kingsborough CC | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ACECUN214 | CUNY - Portfolio Submetering - Kingsborough CC | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ACECUN222 | CUNY - KCC MULTI-BUILDING HVAC UPGRADES AT 2055 ORIENTAL, BK | 1 | DEVELOP SCOPE | Jun 2024 | Aug 2024 | Jun 2023 | Aug 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ACECUN222 | CUNY - KCC MULTI-BUILDING HVAC UPGRADES AT 2055 ORIENTAL, BK | 2 | PRELIMINARY DESIGN | Aug 2024 | Dec 2024 | Aug 2023 | Dec 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ACECUN222 | CUNY - KCC MULTI-BUILDING HVAC UPGRADES AT 2055 ORIENTAL, BK | 3 | FINAL DESIGN | Dec 2024 | Jun 2025 | Dec 2023 | Jun 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ACECUN222 | CUNY - KCC MULTI-BUILDING HVAC UPGRADES AT 2055 ORIENTAL, BK | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2025 | Sep 2025 | Jun 2024 | Sep 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ACECUN222 | CUNY - KCC MULTI-BUILDING HVAC UPGRADES AT 2055 ORIENTAL, BK | 5 | CONSTRUCTION TO 25% | Sep 2025 | Jan 2026 | Sep 2024 | Jan 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ACECUN222 | CUNY - KCC MULTI-BUILDING HVAC UPGRADES AT 2055 ORIENTAL, BK | 6 | CONSTRUCTION TO 50% | Jan 2026 | May 2026 | Jan 2025 | May 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ACECUN222 | CUNY - KCC MULTI-BUILDING HVAC UPGRADES AT 2055 ORIENTAL, BK | 7 | CONSTRUCTION TO 75% | May 2026 | Sep 2026 | May 2025 | Sep 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ACECUN222 | CUNY - KCC MULTI-BUILDING HVAC UPGRADES AT 2055 ORIENTAL, BK | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2026 | Dec 2026 | Sep 2025 | Dec 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ACECUN222 | CUNY - KCC MULTI-BUILDING HVAC UPGRADES AT 2055 ORIENTAL, BK | 9 | SUBSTANTIAL COMPLETION | Dec 2026 | Feb 2027 | Dec 2025 | Feb 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ACECUN222 | CUNY - KCC MULTI-BUILDING HVAC UPGRADES AT 2055 ORIENTAL, BK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2027 | Mar 2027 | Feb 2026 | Mar 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ACECUN233 | Kingsborough Community College BMS Upgrade | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2023 | Jun 2023 | Jun 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ACECUN233 | Kingsborough Community College BMS Upgrade | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ACECUN233 | Kingsborough Community College BMS Upgrade | 3 | CONSTRUCTION TO 50% | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ACECUN233 | Kingsborough Community College BMS Upgrade | 4 | CONSTRUCTION TO 75% | Feb 2024 | May 2024 | Feb 2024 | May 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ACECUN233 | Kingsborough Community College BMS Upgrade | 5 | SUBSTANTIAL COMPLETION | May 2024 | Jul 2024 | May 2024 | Jul 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ACECUN233 | Kingsborough Community College BMS Upgrade | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-021 | Quad Rehab Project | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-021 | Quad Rehab Project | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-021 | Quad Rehab Project | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-021 | Quad Rehab Project | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-021 | Quad Rehab Project | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-021 | Quad Rehab Project | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-021 | Quad Rehab Project | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-021 | Quad Rehab Project | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-021 | Quad Rehab Project | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-021 | Quad Rehab Project | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Jul 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-022 | Lecture Halls Upgrades for Science Instruction | 1 | DEVELOP SCOPE | Jul 2021 | Sep 2021 | Jul 2021 | Sep 2021
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-022 | Lecture Halls Upgrades for Science Instruction | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-022 | Lecture Halls Upgrades for Science Instruction | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-022 | Lecture Halls Upgrades for Science Instruction | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-022 | Lecture Halls Upgrades for Science Instruction | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-022 | Lecture Halls Upgrades for Science Instruction | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-022 | Lecture Halls Upgrades for Science Instruction | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-022 | Lecture Halls Upgrades for Science Instruction | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-022 | Lecture Halls Upgrades for Science Instruction | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-022 | Lecture Halls Upgrades for Science Instruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2027
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-023 | Main Quad Rehabilitation | 1 | DEVELOP SCOPE | Jul 2023 | Sep 2024 | Jul 2023 | Sep 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-023 | Main Quad Rehabilitation | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-023 | Main Quad Rehabilitation | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-023 | Main Quad Rehabilitation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-023 | Main Quad Rehabilitation | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-023 | Main Quad Rehabilitation | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-023 | Main Quad Rehabilitation | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-023 | Main Quad Rehabilitation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-023 | Main Quad Rehabilitation | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-023 | Main Quad Rehabilitation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2029
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY024-012 | Haitian Studies Institute Initial Outfitting | 1 | DEVELOP SCOPE | Jun 2012 | Aug 2012 | Jun 2012 | Aug 2012
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY024-012 | Haitian Studies Institute Initial Outfitting | 2 | PRELIMINARY DESIGN | Aug 2012 | Dec 2012 | Aug 2012 | Dec 2012
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY024-012 | Haitian Studies Institute Initial Outfitting | 3 | FINAL DESIGN | Dec 2012 | Jun 2013 | Dec 2012 | Jun 2013
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY024-012 | Haitian Studies Institute Initial Outfitting | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2013 | Sep 2013 | Jun 2013 | Sep 2013
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY024-012 | Haitian Studies Institute Initial Outfitting | 5 | CONSTRUCTION TO 25% | Sep 2013 | Jan 2014 | Sep 2013 | Jan 2014
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY024-012 | Haitian Studies Institute Initial Outfitting | 6 | CONSTRUCTION TO 50% | Jan 2014 | May 2014 | Jan 2014 | May 2014
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY024-012 | Haitian Studies Institute Initial Outfitting | 7 | CONSTRUCTION TO 75% | May 2014 | Sep 2014 | May 2014 | Sep 2014
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY024-012 | Haitian Studies Institute Initial Outfitting | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY024-012 | Haitian Studies Institute Initial Outfitting | 9 | SUBSTANTIAL COMPLETION | Dec 2014 | Feb 2015 | Dec 2014 | Feb 2015
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY024-012 | Haitian Studies Institute Initial Outfitting | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2015 | Mar 2015 | Feb 2015 | Mar 2027
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY025-012 | Haitian Studies Institute Initial Outfitting | 1 | DEVELOP SCOPE | Jun 2012 | Aug 2012 | Jun 2012 | Aug 2012
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY025-012 | Haitian Studies Institute Initial Outfitting | 2 | PRELIMINARY DESIGN | Aug 2012 | Dec 2012 | Aug 2012 | Dec 2012
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY025-012 | Haitian Studies Institute Initial Outfitting | 3 | FINAL DESIGN | Dec 2012 | Jun 2013 | Dec 2012 | Jun 2013
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY025-012 | Haitian Studies Institute Initial Outfitting | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2013 | Sep 2013 | Jun 2013 | Sep 2013
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY025-012 | Haitian Studies Institute Initial Outfitting | 5 | CONSTRUCTION TO 25% | Sep 2013 | Jan 2014 | Sep 2013 | Jan 2014
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY025-012 | Haitian Studies Institute Initial Outfitting | 6 | CONSTRUCTION TO 50% | Jan 2014 | May 2014 | Jan 2014 | May 2014
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY025-012 | Haitian Studies Institute Initial Outfitting | 7 | CONSTRUCTION TO 75% | May 2014 | Sep 2014 | May 2014 | Sep 2014
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY025-012 | Haitian Studies Institute Initial Outfitting | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY025-012 | Haitian Studies Institute Initial Outfitting | 9 | SUBSTANTIAL COMPLETION | Dec 2014 | Feb 2015 | Dec 2014 | Feb 2015
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY025-012 | Haitian Studies Institute Initial Outfitting | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2015 | Mar 2015 | Feb 2015 | Mar 2027
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY031-017 | Electrical Upgrades | 1 | DEVELOP SCOPE | Jun 2017 | Aug 2017 | Jul 2021 | Oct 2021
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY031-017 | Electrical Upgrades | 2 | PRELIMINARY DESIGN | Aug 2017 | Dec 2017 | Oct 2021 | Jan 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY031-017 | Electrical Upgrades | 3 | FINAL DESIGN | Dec 2017 | Jun 2018 | Jan 2022 | Jul 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY031-017 | Electrical Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Sep 2018 | Jul 2022 | Oct 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY031-017 | Electrical Upgrades | 5 | CONSTRUCTION TO 25% | Sep 2018 | Jan 2019 | Oct 2022 | Feb 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY031-017 | Electrical Upgrades | 6 | CONSTRUCTION TO 50% | Jan 2019 | May 2019 | Feb 2023 | Jun 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY031-017 | Electrical Upgrades | 7 | CONSTRUCTION TO 75% | May 2019 | Sep 2019 | Jun 2023 | Oct 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY031-017 | Electrical Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Dec 2019 | Oct 2023 | Jan 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY031-017 | Electrical Upgrades | 9 | SUBSTANTIAL COMPLETION | Dec 2019 | Feb 2020 | Jan 2024 | Mar 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY031-017 | Electrical Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2020 | Mar 2020 | Mar 2024 | May 2027
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY032-018 | ADA Upgrades for the Brooklyn College Student Center | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jul 2021 | Oct 2021
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY032-018 | ADA Upgrades for the Brooklyn College Student Center | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Oct 2021 | Jan 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY032-018 | ADA Upgrades for the Brooklyn College Student Center | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Jan 2022 | Jul 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY032-018 | ADA Upgrades for the Brooklyn College Student Center | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jul 2022 | Oct 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY032-018 | ADA Upgrades for the Brooklyn College Student Center | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Oct 2022 | Feb 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY032-018 | ADA Upgrades for the Brooklyn College Student Center | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Feb 2023 | Jun 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY032-018 | ADA Upgrades for the Brooklyn College Student Center | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | Jun 2023 | Oct 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY032-018 | ADA Upgrades for the Brooklyn College Student Center | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Oct 2023 | Jan 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY032-018 | ADA Upgrades for the Brooklyn College Student Center | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Jan 2024 | Mar 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY032-018 | ADA Upgrades for the Brooklyn College Student Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Mar 2024 | May 2029
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY034-019 | Restoration of Main Quad | 1 | DEVELOP SCOPE | Jun 2019 | Aug 2019 | Jul 2021 | Sep 2021
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY034-019 | Restoration of Main Quad | 2 | PRELIMINARY DESIGN | Aug 2019 | Dec 2019 | Sep 2021 | Jan 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY034-019 | Restoration of Main Quad | 3 | FINAL DESIGN | Dec 2019 | Jun 2020 | Jan 2022 | Jul 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY034-019 | Restoration of Main Quad | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Sep 2020 | Jul 2022 | Oct 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY034-019 | Restoration of Main Quad | 5 | CONSTRUCTION TO 25% | Sep 2020 | Jan 2021 | Oct 2022 | Feb 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY034-019 | Restoration of Main Quad | 6 | CONSTRUCTION TO 50% | Jan 2021 | May 2021 | Feb 2023 | Jun 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY034-019 | Restoration of Main Quad | 7 | CONSTRUCTION TO 75% | May 2021 | Sep 2021 | Jun 2023 | Oct 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY034-019 | Restoration of Main Quad | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Dec 2021 | Oct 2023 | Jan 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY034-019 | Restoration of Main Quad | 9 | SUBSTANTIAL COMPLETION | Dec 2021 | Feb 2022 | Jan 2024 | Mar 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY034-019 | Restoration of Main Quad | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2022 | Mar 2022 | Mar 2024 | Apr 2029
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY036-020 | Main Quad Restoration | 1 | DEVELOP SCOPE | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY036-020 | Main Quad Restoration | 2 | PRELIMINARY DESIGN | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY036-020 | Main Quad Restoration | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY036-020 | Main Quad Restoration | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY036-020 | Main Quad Restoration | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY036-020 | Main Quad Restoration | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY036-020 | Main Quad Restoration | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY036-020 | Main Quad Restoration | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY036-020 | Main Quad Restoration | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | BY036-020 | Main Quad Restoration | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA002-022 | Technology Equipment and Facility upgrades | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA002-022 | Technology Equipment and Facility upgrades | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA002-022 | Technology Equipment and Facility upgrades | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA002-022 | Technology Equipment and Facility upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA002-022 | Technology Equipment and Facility upgrades | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA002-022 | Technology Equipment and Facility upgrades | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA002-022 | Technology Equipment and Facility upgrades | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA002-022 | Technology Equipment and Facility upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA002-022 | Technology Equipment and Facility upgrades | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA002-022 | Technology Equipment and Facility upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2028
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA022KG01 | Underground Utility Piping | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA022KG01 | Underground Utility Piping | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA022KG01 | Underground Utility Piping | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA022KG01 | Underground Utility Piping | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA022KG01 | Underground Utility Piping | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA022KG01 | Underground Utility Piping | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA022KG01 | Underground Utility Piping | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA022KG01 | Underground Utility Piping | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA022KG01 | Underground Utility Piping | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA022KG01 | Underground Utility Piping | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2032
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA022KG02 | Seawall Exterior Lighting | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA022KG02 | Seawall Exterior Lighting | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA022KG02 | Seawall Exterior Lighting | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA022KG02 | Seawall Exterior Lighting | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA022KG02 | Seawall Exterior Lighting | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA022KG02 | Seawall Exterior Lighting | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA022KG02 | Seawall Exterior Lighting | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA022KG02 | Seawall Exterior Lighting | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA022KG02 | Seawall Exterior Lighting | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA022KG02 | Seawall Exterior Lighting | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA034KG13 | Gas Booster Pump Upgrade | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jun 2018 | Aug 2018
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA034KG13 | Gas Booster Pump Upgrade | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Aug 2018 | Dec 2018
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA034KG13 | Gas Booster Pump Upgrade | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Dec 2018 | Jun 2019
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA034KG13 | Gas Booster Pump Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA034KG13 | Gas Booster Pump Upgrade | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA034KG13 | Gas Booster Pump Upgrade | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Jan 2020 | May 2020
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA034KG13 | Gas Booster Pump Upgrade | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | May 2020 | Sep 2020
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA034KG13 | Gas Booster Pump Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Sep 2020 | Dec 2020
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA034KG13 | Gas Booster Pump Upgrade | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Dec 2020 | Feb 2021
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA034KG13 | Gas Booster Pump Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Feb 2021 | Mar 2028
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA091KG02 | HVAC Improvements HVAC Improvements | 1 | DEVELOP SCOPE | Jul 2022 | Sep 2023 | Jul 2022 | Sep 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA091KG02 | HVAC Improvements HVAC Improvements | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA091KG02 | HVAC Improvements HVAC Improvements | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA091KG02 | HVAC Improvements HVAC Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA091KG02 | HVAC Improvements HVAC Improvements | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA091KG02 | HVAC Improvements HVAC Improvements | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA091KG02 | HVAC Improvements HVAC Improvements | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA091KG02 | HVAC Improvements HVAC Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA091KG02 | HVAC Improvements HVAC Improvements | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA091KG02 | HVAC Improvements HVAC Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA091KG03 | LL97 Gym HVAC Units Replacement | 1 | DEVELOP SCOPE | Jul 2022 | Sep 2023 | Jul 2022 | Sep 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA091KG03 | LL97 Gym HVAC Units Replacement | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA091KG03 | LL97 Gym HVAC Units Replacement | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA091KG03 | LL97 Gym HVAC Units Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA091KG03 | LL97 Gym HVAC Units Replacement | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA091KG03 | LL97 Gym HVAC Units Replacement | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA091KG03 | LL97 Gym HVAC Units Replacement | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA091KG03 | LL97 Gym HVAC Units Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA091KG03 | LL97 Gym HVAC Units Replacement | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | CA091KG03 | LL97 Gym HVAC Units Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-021 | Library Building | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-021 | Library Building | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-021 | Library Building | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-021 | Library Building | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-021 | Library Building | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-021 | Library Building | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-021 | Library Building | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-021 | Library Building | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-021 | Library Building | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-021 | Library Building | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2027
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-022 | Kibbee Library & Media Center Renovations | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-022 | Kibbee Library & Media Center Renovations | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-022 | Kibbee Library & Media Center Renovations | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-022 | Kibbee Library & Media Center Renovations | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-022 | Kibbee Library & Media Center Renovations | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-022 | Kibbee Library & Media Center Renovations | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-022 | Kibbee Library & Media Center Renovations | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-022 | Kibbee Library & Media Center Renovations | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-022 | Kibbee Library & Media Center Renovations | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-022 | Kibbee Library & Media Center Renovations | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-024 | LIGHTHOUSE ROTUNDA RENOVATIONS | 1 | DEVELOP SCOPE | Jul 2023 | Sep 2024 | Jul 2023 | Sep 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-024 | LIGHTHOUSE ROTUNDA RENOVATIONS | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-024 | LIGHTHOUSE ROTUNDA RENOVATIONS | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-024 | LIGHTHOUSE ROTUNDA RENOVATIONS | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-024 | LIGHTHOUSE ROTUNDA RENOVATIONS | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-024 | LIGHTHOUSE ROTUNDA RENOVATIONS | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-024 | LIGHTHOUSE ROTUNDA RENOVATIONS | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-024 | LIGHTHOUSE ROTUNDA RENOVATIONS | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-024 | LIGHTHOUSE ROTUNDA RENOVATIONS | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-024 | LIGHTHOUSE ROTUNDA RENOVATIONS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG002-022 | Off Shore Wind Training Equipment | 1 | DEVELOP SCOPE | Jul 2023 | Sep 2023 | Jul 2023 | Sep 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG002-022 | Off Shore Wind Training Equipment | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG002-022 | Off Shore Wind Training Equipment | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG002-022 | Off Shore Wind Training Equipment | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG002-022 | Off Shore Wind Training Equipment | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG002-022 | Off Shore Wind Training Equipment | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG002-022 | Off Shore Wind Training Equipment | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG002-022 | Off Shore Wind Training Equipment | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG002-022 | Off Shore Wind Training Equipment | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG002-022 | Off Shore Wind Training Equipment | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2028 | Mar 2026 | Apr 2028
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG025-009 | FACILITIES FOR OCCUPATIONAL & RESPIRATORY THERAPY | 1 | DEVELOP SCOPE | Jun 2009 | Aug 2009 | Jun 2009 | Aug 2009
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG025-009 | FACILITIES FOR OCCUPATIONAL & RESPIRATORY THERAPY | 2 | PRELIMINARY DESIGN | Aug 2009 | Dec 2009 | Aug 2009 | Dec 2009
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG025-009 | FACILITIES FOR OCCUPATIONAL & RESPIRATORY THERAPY | 3 | FINAL DESIGN | Dec 2009 | Jun 2010 | Dec 2009 | Jun 2010
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG025-009 | FACILITIES FOR OCCUPATIONAL & RESPIRATORY THERAPY | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2010 | Sep 2010 | Jun 2010 | Sep 2010
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG025-009 | FACILITIES FOR OCCUPATIONAL & RESPIRATORY THERAPY | 5 | CONSTRUCTION TO 25% | Sep 2010 | Jan 2011 | Sep 2010 | Jan 2011
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG025-009 | FACILITIES FOR OCCUPATIONAL & RESPIRATORY THERAPY | 6 | CONSTRUCTION TO 50% | Jan 2011 | May 2011 | Jan 2011 | May 2011
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG025-009 | FACILITIES FOR OCCUPATIONAL & RESPIRATORY THERAPY | 7 | CONSTRUCTION TO 75% | May 2011 | Sep 2011 | May 2011 | Sep 2011
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG025-009 | FACILITIES FOR OCCUPATIONAL & RESPIRATORY THERAPY | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2011 | Dec 2011 | Sep 2011 | Dec 2011
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG025-009 | FACILITIES FOR OCCUPATIONAL & RESPIRATORY THERAPY | 9 | SUBSTANTIAL COMPLETION | Dec 2011 | Feb 2012 | Dec 2011 | Feb 2012
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG025-009 | FACILITIES FOR OCCUPATIONAL & RESPIRATORY THERAPY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2012 | Mar 2012 | Feb 2012 | Jun 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG030-012 | Critical Maintenance A/P/U Buildings | 1 | DEVELOP SCOPE | Jun 2012 | Aug 2012 | Jun 2012 | Aug 2012
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG030-012 | Critical Maintenance A/P/U Buildings | 2 | PRELIMINARY DESIGN | Aug 2012 | Dec 2012 | Aug 2012 | Dec 2012
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG030-012 | Critical Maintenance A/P/U Buildings | 3 | FINAL DESIGN | Dec 2012 | Jun 2013 | Dec 2012 | Jun 2013
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG030-012 | Critical Maintenance A/P/U Buildings | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2013 | Sep 2013 | Jun 2013 | Sep 2013
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG030-012 | Critical Maintenance A/P/U Buildings | 5 | CONSTRUCTION TO 25% | Sep 2013 | Jan 2014 | Sep 2013 | Jan 2014
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG030-012 | Critical Maintenance A/P/U Buildings | 6 | CONSTRUCTION TO 50% | Jan 2014 | May 2014 | Jan 2014 | May 2014
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG030-012 | Critical Maintenance A/P/U Buildings | 7 | CONSTRUCTION TO 75% | May 2014 | Sep 2014 | May 2014 | Sep 2014
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG030-012 | Critical Maintenance A/P/U Buildings | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG030-012 | Critical Maintenance A/P/U Buildings | 9 | SUBSTANTIAL COMPLETION | Dec 2014 | Feb 2015 | Dec 2014 | Feb 2015
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG030-012 | Critical Maintenance A/P/U Buildings | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2015 | Mar 2015 | Feb 2015 | Mar 2029
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG031-013 | Renovation of Pool Facilities | 1 | DEVELOP SCOPE | Jun 2013 | Aug 2013 | Jul 2020 | Sep 2020
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG031-013 | Renovation of Pool Facilities | 2 | PRELIMINARY DESIGN | Aug 2013 | Dec 2013 | Sep 2020 | Jan 2021
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG031-013 | Renovation of Pool Facilities | 3 | FINAL DESIGN | Dec 2013 | Jun 2014 | Jan 2024 | Jul 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG031-013 | Renovation of Pool Facilities | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2014 | Sep 2014 | Jul 2024 | Oct 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG031-013 | Renovation of Pool Facilities | 5 | CONSTRUCTION TO 25% | Sep 2014 | Jan 2015 | Oct 2024 | Feb 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG031-013 | Renovation of Pool Facilities | 6 | CONSTRUCTION TO 50% | Jan 2015 | May 2015 | Feb 2025 | Jun 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG031-013 | Renovation of Pool Facilities | 7 | CONSTRUCTION TO 75% | May 2015 | Sep 2015 | Jun 2025 | Oct 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG031-013 | Renovation of Pool Facilities | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2015 | Dec 2015 | Oct 2025 | Jan 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG031-013 | Renovation of Pool Facilities | 9 | SUBSTANTIAL COMPLETION | Dec 2015 | Feb 2016 | Jan 2026 | Mar 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG031-013 | Renovation of Pool Facilities | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2016 | Mar 2016 | Mar 2026 | Apr 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG043-018 | Campus Roadway Improvements | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jul 2021 | Sep 2021
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG043-018 | Campus Roadway Improvements | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Sep 2021 | Jan 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG043-018 | Campus Roadway Improvements | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Jan 2022 | Jul 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG043-018 | Campus Roadway Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jul 2022 | Oct 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG043-018 | Campus Roadway Improvements | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Oct 2022 | Feb 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG043-018 | Campus Roadway Improvements | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Feb 2023 | Jun 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG043-018 | Campus Roadway Improvements | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | Jun 2023 | Oct 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG043-018 | Campus Roadway Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Oct 2023 | Jan 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG043-018 | Campus Roadway Improvements | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Jan 2024 | Mar 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG043-018 | Campus Roadway Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Mar 2024 | Jul 2028
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG045-020 | Performing Arts Center Upgrades | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG045-020 | Performing Arts Center Upgrades | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG045-020 | Performing Arts Center Upgrades | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2021
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG045-020 | Performing Arts Center Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG045-020 | Performing Arts Center Upgrades | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG045-020 | Performing Arts Center Upgrades | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG045-020 | Performing Arts Center Upgrades | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG045-020 | Performing Arts Center Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG045-020 | Performing Arts Center Upgrades | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2023 | Mar 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG045-020 | Performing Arts Center Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2023 | Apr 2027
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG206-006 | T4 Roof Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG206-006 | T4 Roof Replacement | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG206-006 | T4 Roof Replacement | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Jan 2020 | May 2020
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG206-006 | T4 Roof Replacement | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | May 2020 | Sep 2020
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG206-006 | T4 Roof Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Sep 2020 | Dec 2020
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG206-006 | T4 Roof Replacement | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Dec 2020 | Feb 2021
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | KG206-006 | T4 Roof Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Feb 2021 | Jun 2032
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-022 | Athletic Center Improvements | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-022 | Athletic Center Improvements | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-022 | Athletic Center Improvements | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-022 | Athletic Center Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-022 | Athletic Center Improvements | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-022 | Athletic Center Improvements | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-022 | Athletic Center Improvements | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-022 | Athletic Center Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-022 | Athletic Center Improvements | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-022 | Athletic Center Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-023 | Campus Wide Access Lock Control & Public Address Safety | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-023 | Campus Wide Access Lock Control & Public Address Safety | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-023 | Campus Wide Access Lock Control & Public Address Safety | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-023 | Campus Wide Access Lock Control & Public Address Safety | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-023 | Campus Wide Access Lock Control & Public Address Safety | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-023 | Campus Wide Access Lock Control & Public Address Safety | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-023 | Campus Wide Access Lock Control & Public Address Safety | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-023 | Campus Wide Access Lock Control & Public Address Safety | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-023 | Campus Wide Access Lock Control & Public Address Safety | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-023 | Campus Wide Access Lock Control & Public Address Safety | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-024 | Founders Auditorium Upgrade | 1 | DEVELOP SCOPE | Jul 2024 | Sep 2024 | Jul 2024 | Sep 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-024 | Founders Auditorium Upgrade | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-024 | Founders Auditorium Upgrade | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-024 | Founders Auditorium Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-024 | Founders Auditorium Upgrade | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-024 | Founders Auditorium Upgrade | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-024 | Founders Auditorium Upgrade | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-024 | Founders Auditorium Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-024 | Founders Auditorium Upgrade | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-024 | Founders Auditorium Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME018-005 | LIBRARY EXPANSION | 1 | DEVELOP SCOPE | May 2010 | May 2010 | May 2010 | May 2010
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME018-005 | LIBRARY EXPANSION | 2 | PRELIMINARY DESIGN | May 2010 | May 2010 | May 2010 | May 2010
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME018-005 | LIBRARY EXPANSION | 3 | FINAL DESIGN | May 2010 | May 2010 | May 2010 | May 2010
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME018-005 | LIBRARY EXPANSION | 4 | BID AWARD AND REGISTER CONTRCT | May 2010 | May 2010 | May 2010 | May 2010
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME018-005 | LIBRARY EXPANSION | 5 | CONSTRUCTION TO 25% | Jun 2015 | Jun 2015 | Jun 2015 | Jun 2015
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME018-005 | LIBRARY EXPANSION | 6 | CONSTRUCTION TO 50% | Jun 2015 | Jun 2015 | Jun 2015 | Jun 2015
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME018-005 | LIBRARY EXPANSION | 7 | CONSTRUCTION TO 75% | Jun 2015 | Jun 2015 | Jun 2015 | Jun 2015
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME018-005 | LIBRARY EXPANSION | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2015 | Jun 2015 | Jun 2015 | Jun 2015
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME018-005 | LIBRARY EXPANSION | 9 | SUBSTANTIAL COMPLETION | Jun 2015 | Jun 2015 | Jun 2015 | Jun 2015
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME018-005 | LIBRARY EXPANSION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2015 | Jul 2015 | Jun 2015 | Jul 2028
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME027-011 | Carroll Street Building Upgrade | 1 | DEVELOP SCOPE | Jun 2011 | Aug 2011 | Jul 2020 | Sep 2020
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME027-011 | Carroll Street Building Upgrade | 2 | PRELIMINARY DESIGN | Aug 2011 | Dec 2011 | Sep 2020 | Jan 2021
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME027-011 | Carroll Street Building Upgrade | 3 | FINAL DESIGN | Dec 2011 | Jun 2012 | Jan 2021 | Jul 2021
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME027-011 | Carroll Street Building Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2012 | Sep 2012 | Jul 2021 | Oct 2021
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME027-011 | Carroll Street Building Upgrade | 5 | CONSTRUCTION TO 25% | Sep 2012 | Jan 2013 | Oct 2021 | Feb 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME027-011 | Carroll Street Building Upgrade | 6 | CONSTRUCTION TO 50% | Jan 2013 | May 2013 | Feb 2022 | Jun 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME027-011 | Carroll Street Building Upgrade | 7 | CONSTRUCTION TO 75% | May 2013 | Sep 2013 | Jun 2022 | Oct 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME027-011 | Carroll Street Building Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2013 | Dec 2013 | Oct 2022 | Jan 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME027-011 | Carroll Street Building Upgrade | 9 | SUBSTANTIAL COMPLETION | Dec 2013 | Feb 2014 | Jan 2023 | Mar 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME027-011 | Carroll Street Building Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2014 | Mar 2014 | Mar 2023 | Apr 2028
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME031-013 | Virtual Desktop Infrastructure | 1 | DEVELOP SCOPE | Jun 2013 | Aug 2013 | Jun 2013 | Aug 2013
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME031-013 | Virtual Desktop Infrastructure | 2 | PRELIMINARY DESIGN | Aug 2013 | Dec 2013 | Aug 2013 | Dec 2013
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME031-013 | Virtual Desktop Infrastructure | 3 | FINAL DESIGN | Dec 2013 | Jun 2014 | Dec 2013 | Jun 2014
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME031-013 | Virtual Desktop Infrastructure | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2014 | Sep 2014 | Jun 2014 | Sep 2014
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME031-013 | Virtual Desktop Infrastructure | 5 | CONSTRUCTION TO 25% | Sep 2014 | Jan 2015 | Sep 2014 | Jan 2015
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME031-013 | Virtual Desktop Infrastructure | 6 | CONSTRUCTION TO 50% | Jan 2015 | May 2015 | Jan 2015 | May 2015
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME031-013 | Virtual Desktop Infrastructure | 7 | CONSTRUCTION TO 75% | May 2015 | Sep 2015 | May 2015 | Sep 2015
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME031-013 | Virtual Desktop Infrastructure | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME031-013 | Virtual Desktop Infrastructure | 9 | SUBSTANTIAL COMPLETION | Dec 2015 | Feb 2016 | Dec 2015 | Feb 2016
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME031-013 | Virtual Desktop Infrastructure | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2016 | Mar 2016 | Feb 2016 | Mar 2028
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME038-016 | Child Development Center Upgrades | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Jul 2021 | Sep 2021
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME038-016 | Child Development Center Upgrades | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Sep 2021 | Jan 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME038-016 | Child Development Center Upgrades | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Jan 2022 | Jul 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME038-016 | Child Development Center Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Jul 2022 | Oct 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME038-016 | Child Development Center Upgrades | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Oct 2022 | Feb 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME038-016 | Child Development Center Upgrades | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Feb 2023 | Jun 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME038-016 | Child Development Center Upgrades | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Jun 2023 | Oct 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME038-016 | Child Development Center Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | Oct 2023 | Jan 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME038-016 | Child Development Center Upgrades | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Jan 2024 | Mar 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME038-016 | Child Development Center Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Mar 2024 | Apr 2028
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME039-017 | Student Lounge Upgrades | 1 | DEVELOP SCOPE | Jun 2017 | Aug 2017 | Jun 2024 | Sep 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME039-017 | Student Lounge Upgrades | 2 | PRELIMINARY DESIGN | Aug 2017 | Dec 2017 | Sep 2024 | Jan 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME039-017 | Student Lounge Upgrades | 3 | FINAL DESIGN | Dec 2017 | Jun 2018 | Jan 2025 | Jul 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME039-017 | Student Lounge Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Sep 2018 | Jul 2025 | Oct 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME039-017 | Student Lounge Upgrades | 5 | CONSTRUCTION TO 25% | Sep 2018 | Jan 2019 | Oct 2025 | Feb 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME039-017 | Student Lounge Upgrades | 6 | CONSTRUCTION TO 50% | Jan 2019 | May 2019 | Feb 2026 | Jun 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME039-017 | Student Lounge Upgrades | 7 | CONSTRUCTION TO 75% | May 2019 | Sep 2019 | Jun 2026 | Oct 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME039-017 | Student Lounge Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Dec 2019 | Oct 2026 | Jan 2027
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME039-017 | Student Lounge Upgrades | 9 | SUBSTANTIAL COMPLETION | Dec 2019 | Feb 2020 | Jan 2027 | Mar 2027
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME039-017 | Student Lounge Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2020 | Mar 2020 | Mar 2027 | Apr 2028
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME041-018 | Art and Historic Space Renovation | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jul 2022 | Sep 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME041-018 | Art and Historic Space Renovation | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Sep 2022 | Jan 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME041-018 | Art and Historic Space Renovation | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Jan 2023 | Jul 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME041-018 | Art and Historic Space Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jul 2023 | Oct 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME041-018 | Art and Historic Space Renovation | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Oct 2023 | Feb 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME041-018 | Art and Historic Space Renovation | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Feb 2024 | Jun 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME041-018 | Art and Historic Space Renovation | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | Jun 2024 | Oct 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME041-018 | Art and Historic Space Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Oct 2024 | Jan 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME041-018 | Art and Historic Space Renovation | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Jan 2025 | Mar 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME041-018 | Art and Historic Space Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Mar 2025 | Apr 2029
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME042-019 | Founder's Auditorium Renovation & Upgrades | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jul 2022 | Sep 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME042-019 | Founder's Auditorium Renovation & Upgrades | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2022 | Jan 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME042-019 | Founder's Auditorium Renovation & Upgrades | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2023 | Jul 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME042-019 | Founder's Auditorium Renovation & Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2023 | Oct 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME042-019 | Founder's Auditorium Renovation & Upgrades | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2023 | Feb 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME042-019 | Founder's Auditorium Renovation & Upgrades | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2024 | Jun 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME042-019 | Founder's Auditorium Renovation & Upgrades | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2024 | Oct 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME042-019 | Founder's Auditorium Renovation & Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2024 | Jan 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME042-019 | Founder's Auditorium Renovation & Upgrades | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2025 | Mar 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME042-019 | Founder's Auditorium Renovation & Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2025 | Apr 2028
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME043-020 | Open Computer and Lab Digital Interactive Learning Spaces | 1 | DEVELOP SCOPE | Jul 2021 | Sep 2021 | Jun 2025 | Sep 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME043-020 | Open Computer and Lab Digital Interactive Learning Spaces | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2025 | Jan 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME043-020 | Open Computer and Lab Digital Interactive Learning Spaces | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2026 | Jul 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME043-020 | Open Computer and Lab Digital Interactive Learning Spaces | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2026 | Oct 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME043-020 | Open Computer and Lab Digital Interactive Learning Spaces | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2026 | Feb 2027
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME043-020 | Open Computer and Lab Digital Interactive Learning Spaces | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2027 | Jun 2027
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME043-020 | Open Computer and Lab Digital Interactive Learning Spaces | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2027 | Oct 2027
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME043-020 | Open Computer and Lab Digital Interactive Learning Spaces | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2027 | Jan 2028
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME043-020 | Open Computer and Lab Digital Interactive Learning Spaces | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2028 | Mar 2028
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ME043-020 | Open Computer and Lab Digital Interactive Learning Spaces | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2028 | Apr 2028
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY006-009 | WELCOME CENTER AND ART GALLERY | 3 | FINAL DESIGN | Dec 2009 | Jun 2010 | Dec 2009 | Jun 2010
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY006-009 | WELCOME CENTER AND ART GALLERY | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2010 | Sep 2010 | Jun 2010 | Sep 2010
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY006-009 | WELCOME CENTER AND ART GALLERY | 5 | CONSTRUCTION TO 25% | Sep 2010 | Jan 2011 | Sep 2010 | Jan 2011
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY006-009 | WELCOME CENTER AND ART GALLERY | 6 | CONSTRUCTION TO 50% | Jan 2011 | May 2011 | Jan 2011 | May 2011
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY006-009 | WELCOME CENTER AND ART GALLERY | 7 | CONSTRUCTION TO 75% | May 2011 | Sep 2011 | May 2011 | Sep 2011
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY006-009 | WELCOME CENTER AND ART GALLERY | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2011 | Dec 2011 | Sep 2011 | Dec 2011
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY006-009 | WELCOME CENTER AND ART GALLERY | 9 | SUBSTANTIAL COMPLETION | Dec 2011 | Feb 2012 | Dec 2011 | Feb 2012
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY006-009 | WELCOME CENTER AND ART GALLERY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2012 | Mar 2012 | Feb 2012 | Jun 2021
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY013-012 | Network Upgrades | 1 | DEVELOP SCOPE | Jun 2012 | Aug 2012 | Jun 2012 | Aug 2012
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY013-012 | Network Upgrades | 2 | PRELIMINARY DESIGN | Aug 2012 | Dec 2012 | Aug 2012 | Dec 2012
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY013-012 | Network Upgrades | 3 | FINAL DESIGN | Dec 2012 | Jun 2013 | Dec 2012 | Jun 2013
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY013-012 | Network Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2013 | Sep 2013 | Jun 2013 | Sep 2013
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY013-012 | Network Upgrades | 5 | CONSTRUCTION TO 25% | Sep 2013 | Jan 2014 | Sep 2013 | Jan 2014
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY013-012 | Network Upgrades | 6 | CONSTRUCTION TO 50% | Jan 2014 | May 2014 | Jan 2014 | May 2014
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY013-012 | Network Upgrades | 7 | CONSTRUCTION TO 75% | May 2014 | Sep 2014 | May 2014 | Sep 2014
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY013-012 | Network Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY013-012 | Network Upgrades | 9 | SUBSTANTIAL COMPLETION | Dec 2014 | Feb 2015 | Dec 2014 | Feb 2015
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY013-012 | Network Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2015 | Mar 2015 | Feb 2015 | Dec 2028
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY024-018 | Exterior Space Improvements | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jul 2023 | Sep 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY024-018 | Exterior Space Improvements | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY024-018 | Exterior Space Improvements | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Jan 2024 | Jul 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY024-018 | Exterior Space Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jul 2024 | Oct 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY024-018 | Exterior Space Improvements | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Oct 2024 | Feb 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY024-018 | Exterior Space Improvements | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Feb 2025 | Jun 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY024-018 | Exterior Space Improvements | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | Jun 2025 | Oct 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY024-018 | Exterior Space Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Oct 2025 | Jan 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY024-018 | Exterior Space Improvements | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Jan 2026 | Mar 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY024-018 | Exterior Space Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Mar 2026 | Apr 2028
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY025-018 | NYC College of Technolgy Pearl Street Building Renovation | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jul 2018 | Sep 2018
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY025-018 | NYC College of Technolgy Pearl Street Building Renovation | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Sep 2018 | Dec 2018
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY025-018 | NYC College of Technolgy Pearl Street Building Renovation | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Dec 2018 | Jun 2019
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY025-018 | NYC College of Technolgy Pearl Street Building Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY025-018 | NYC College of Technolgy Pearl Street Building Renovation | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Oct 2021 | Apr 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY025-018 | NYC College of Technolgy Pearl Street Building Renovation | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Apr 2022 | Jul 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY025-018 | NYC College of Technolgy Pearl Street Building Renovation | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | Jul 2022 | Nov 2022
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY025-018 | NYC College of Technolgy Pearl Street Building Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Nov 2022 | Feb 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY025-018 | NYC College of Technolgy Pearl Street Building Renovation | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Feb 2023 | Apr 2023
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | NY025-018 | NYC College of Technolgy Pearl Street Building Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Apr 2023 | May 2028
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG02 | HVAC Repair/Replacement - Sandy Related | 1 | DEVELOP SCOPE | Jun 2014 | Aug 2014 | Jun 2014 | Aug 2014
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG02 | HVAC Repair/Replacement - Sandy Related | 2 | PRELIMINARY DESIGN | Aug 2014 | Dec 2014 | Aug 2014 | Dec 2014
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG02 | HVAC Repair/Replacement - Sandy Related | 3 | FINAL DESIGN | Dec 2014 | Jun 2015 | Dec 2014 | Jun 2015
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG02 | HVAC Repair/Replacement - Sandy Related | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2015 | Sep 2015 | Jun 2015 | Sep 2015
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG02 | HVAC Repair/Replacement - Sandy Related | 5 | CONSTRUCTION TO 25% | Sep 2015 | Jan 2016 | Sep 2015 | Jan 2016
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG02 | HVAC Repair/Replacement - Sandy Related | 6 | CONSTRUCTION TO 50% | Jan 2016 | May 2016 | Jan 2016 | May 2016
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG02 | HVAC Repair/Replacement - Sandy Related | 7 | CONSTRUCTION TO 75% | May 2016 | Sep 2016 | May 2016 | Sep 2016
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG02 | HVAC Repair/Replacement - Sandy Related | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Dec 2016 | Sep 2016 | Dec 2016
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG02 | HVAC Repair/Replacement - Sandy Related | 9 | SUBSTANTIAL COMPLETION | Dec 2016 | Feb 2017 | Dec 2016 | Feb 2017
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG02 | HVAC Repair/Replacement - Sandy Related | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2017 | Mar 2017 | Feb 2017 | Mar 2027
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG03 | Marina Reconstruction Kingsborough CC - Brooklyn | 1 | DEVELOP SCOPE | Mar 2015 | May 2015 | Jun 2014 | Aug 2014
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG03 | Marina Reconstruction Kingsborough CC - Brooklyn | 2 | PRELIMINARY DESIGN | May 2015 | Sep 2015 | Sep 2014 | Aug 2015
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG03 | Marina Reconstruction Kingsborough CC - Brooklyn | 3 | FINAL DESIGN | Sep 2015 | Mar 2016 | Sep 2015 | May 2019
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG03 | Marina Reconstruction Kingsborough CC - Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2016 | Jun 2016 | May 2019 | Jul 2019
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG03 | Marina Reconstruction Kingsborough CC - Brooklyn | 5 | CONSTRUCTION TO 25% | Jun 2016 | Oct 2016 | Jul 2019 | Nov 2019
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG03 | Marina Reconstruction Kingsborough CC - Brooklyn | 6 | CONSTRUCTION TO 50% | Oct 2016 | Feb 2017 | Nov 2019 | Mar 2020
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG03 | Marina Reconstruction Kingsborough CC - Brooklyn | 7 | CONSTRUCTION TO 75% | Feb 2017 | Jun 2017 | Mar 2020 | Jul 2020
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG03 | Marina Reconstruction Kingsborough CC - Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2017 | Sep 2017 | Jul 2020 | Oct 2020
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG03 | Marina Reconstruction Kingsborough CC - Brooklyn | 9 | SUBSTANTIAL COMPLETION | Sep 2017 | Nov 2017 | Oct 2020 | Dec 2020
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG03 | Marina Reconstruction Kingsborough CC - Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | Dec 2017 | Feb 2021 | Jun 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ST001-023 | New Stem Lab | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ST001-023 | New Stem Lab | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ST001-023 | New Stem Lab | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ST001-023 | New Stem Lab | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ST001-023 | New Stem Lab | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ST001-023 | New Stem Lab | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ST001-023 | New Stem Lab | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ST001-023 | New Stem Lab | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ST001-023 | New Stem Lab | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ST001-023 | New Stem Lab | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ST002-023 | 4N Makerspace | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ST002-023 | 4N Makerspace | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ST002-023 | 4N Makerspace | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ST002-023 | 4N Makerspace | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ST002-023 | 4N Makerspace | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ST002-023 | 4N Makerspace | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ST002-023 | 4N Makerspace | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ST002-023 | 4N Makerspace | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ST002-023 | 4N Makerspace | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | BROOKLYN | 042 | CITY UNIVERSITY | ST002-023 | 4N Makerspace | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO7911FR | 11 FRONT STR RENOVATION | 1 | DEVELOP SCOPE | May 2017 | Aug 2017 | May 2017 | Aug 2017
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO7911FR | 11 FRONT STR RENOVATION | 2 | PRELIMINARY DESIGN | Aug 2017 | Dec 2017 | Aug 2017 | Dec 2017
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO7911FR | 11 FRONT STR RENOVATION | 3 | FINAL DESIGN | Dec 2017 | Apr 2018 | Dec 2017 | Apr 2018
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO7911FR | 11 FRONT STR RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2018 | Oct 2018 | Apr 2018 | Oct 2018
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO7911FR | 11 FRONT STR RENOVATION | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO7911FR | 11 FRONT STR RENOVATION | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO7911FR | 11 FRONT STR RENOVATION | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jun 2019 | Mar 2021
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO7911FR | 11 FRONT STR RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Mar 2021 | Jun 2021
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO7911FR | 11 FRONT STR RENOVATION | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jun 2021 | Aug 2021
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO7911FR | 11 FRONT STR RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Aug 2021 | Aug 2023
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHS | FIRING RANGE RECONSTRUCTION AT CONEY ISLAND | 1 | DEVELOP SCOPE | Jun 2014 | Sep 2014 | Jun 2016 | Sep 2016
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHS | FIRING RANGE RECONSTRUCTION AT CONEY ISLAND | 2 | PRELIMINARY DESIGN | Sep 2014 | Jan 2015 | Sep 2016 | Jan 2017
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHS | FIRING RANGE RECONSTRUCTION AT CONEY ISLAND | 3 | FINAL DESIGN | Jan 2015 | Jul 2015 | Jan 2017 | Jul 2017
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHS | FIRING RANGE RECONSTRUCTION AT CONEY ISLAND | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Oct 2015 | Jul 2017 | Oct 2017
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHS | FIRING RANGE RECONSTRUCTION AT CONEY ISLAND | 5 | CONSTRUCTION TO 25% | Oct 2015 | Feb 2016 | Oct 2017 | Feb 2018
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHS | FIRING RANGE RECONSTRUCTION AT CONEY ISLAND | 6 | CONSTRUCTION TO 50% | Feb 2016 | Jun 2016 | Feb 2018 | Jun 2018
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHS | FIRING RANGE RECONSTRUCTION AT CONEY ISLAND | 7 | CONSTRUCTION TO 75% | Jun 2016 | Oct 2016 | Jun 2018 | Oct 2022
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHS | FIRING RANGE RECONSTRUCTION AT CONEY ISLAND | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2016 | Jan 2017 | Oct 2022 | Jan 2023
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHS | FIRING RANGE RECONSTRUCTION AT CONEY ISLAND | 9 | SUBSTANTIAL COMPLETION | Jan 2017 | Mar 2017 | Jan 2023 | Mar 2023
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHS | FIRING RANGE RECONSTRUCTION AT CONEY ISLAND | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Apr 2017 | Mar 2023 | Jun 2026
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHX | 63RD BATHROOM RENOVATION | 1 | DEVELOP SCOPE | Jun 2014 | Sep 2014 | Jun 2014 | Sep 2014
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHX | 63RD BATHROOM RENOVATION | 2 | PRELIMINARY DESIGN | Sep 2014 | Jan 2015 | Sep 2014 | Jan 2015
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHX | 63RD BATHROOM RENOVATION | 3 | FINAL DESIGN | Jan 2015 | Jul 2015 | Jan 2015 | Jul 2015
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHX | 63RD BATHROOM RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Oct 2015 | Jul 2015 | Oct 2015
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHX | 63RD BATHROOM RENOVATION | 5 | CONSTRUCTION TO 25% | Oct 2015 | Feb 2016 | Oct 2015 | Feb 2016
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHX | 63RD BATHROOM RENOVATION | 6 | CONSTRUCTION TO 50% | Feb 2016 | Jun 2016 | Feb 2016 | Jun 2016
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHX | 63RD BATHROOM RENOVATION | 7 | CONSTRUCTION TO 75% | Jun 2016 | Oct 2016 | Jun 2016 | Oct 2021
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHX | 63RD BATHROOM RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2016 | Jan 2017 | Oct 2021 | Jan 2022
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHX | 63RD BATHROOM RENOVATION | 9 | SUBSTANTIAL COMPLETION | Jan 2017 | Mar 2017 | Jan 2022 | Mar 2022
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHX | 63RD BATHROOM RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Apr 2017 | Mar 2022 | Apr 2022
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKG | FBF AVIATION AND DRIVER TRAINING UNIT ROOF REHABILITATION | 1 | DESIGN | Jan 2020 | Jun 2020 | Jan 2022 | Jun 2022
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKG | FBF AVIATION AND DRIVER TRAINING UNIT ROOF REHABILITATION | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Sep 2020 | Jun 2022 | Sep 2022
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKG | FBF AVIATION AND DRIVER TRAINING UNIT ROOF REHABILITATION | 3 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2022 | Sep 2024
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKG | FBF AVIATION AND DRIVER TRAINING UNIT ROOF REHABILITATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Mar 2022 | Sep 2024 | Mar 2028
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKJ | REHABILITATION OF 67TH PCT ELEVATOR | 1 | DESIGN | Jul 2020 | Jan 2021 | Jul 2020 | Jan 2021
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKJ | REHABILITATION OF 67TH PCT ELEVATOR | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2021 | Apr 2021 | Jan 2021 | Apr 2021
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKJ | REHABILITATION OF 67TH PCT ELEVATOR | 3 | CONSTRUCTION | Apr 2021 | Apr 2022 | Apr 2021 | Apr 2022
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKJ | REHABILITATION OF 67TH PCT ELEVATOR | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2022 | Oct 2022 | Apr 2022 | Jun 2026
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKW | 245 GLENMORE ROOF REPLACEMENT | 1 | DEVELOP SCOPE | Dec 2020 | Mar 2021 | Dec 2020 | Mar 2021
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKW | 245 GLENMORE ROOF REPLACEMENT | 2 | PRELIMINARY DESIGN | Mar 2021 | Jul 2021 | Mar 2021 | Jul 2021
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKW | 245 GLENMORE ROOF REPLACEMENT | 3 | FINAL DESIGN | Jul 2021 | Nov 2021 | Jul 2021 | Nov 2021
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKW | 245 GLENMORE ROOF REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2021 | May 2022 | Nov 2021 | May 2022
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKW | 245 GLENMORE ROOF REPLACEMENT | 5 | CONSTRUCTION TO 25% | May 2022 | Aug 2022 | May 2022 | Aug 2022
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKW | 245 GLENMORE ROOF REPLACEMENT | 6 | CONSTRUCTION TO 50% | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKW | 245 GLENMORE ROOF REPLACEMENT | 7 | CONSTRUCTION TO 75% | Dec 2022 | Apr 2023 | Dec 2022 | Apr 2023
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKW | 245 GLENMORE ROOF REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2023 | Jul 2023 | Apr 2023 | Jul 2023
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKW | 245 GLENMORE ROOF REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | Jul 2023 | Sep 2023 | Jul 2023 | Sep 2023
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKW | 245 GLENMORE ROOF REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Oct 2023 | Sep 2023 | Oct 2027
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79HCFDR | HARBOR CHARLIE FLOATING DOCKS RENOVATION | 1 | DESIGN | Dec 2021 | Jun 2022 | Dec 2021 | Jun 2022
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79HCFDR | HARBOR CHARLIE FLOATING DOCKS RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79HCFDR | HARBOR CHARLIE FLOATING DOCKS RENOVATION | 3 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79HCFDR | HARBOR CHARLIE FLOATING DOCKS RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Mar 2024 | Sep 2023 | Sep 2027
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | POD73CMRM | 73RD PRECINCT COMMUNITY ROOM | 3 | CONSTRUCTION | Oct 2019 | Oct 2020 | Oct 2019 | Oct 2020
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | POD73CMRM | 73RD PRECINCT COMMUNITY ROOM | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2020 | Mar 2021 | Oct 2020 | Mar 2021
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO-KVEST | PEOPLE'S PRECINCTS VESTIBULE REDESIGN | 1 | DESIGN | Jan 2018 | Jun 2018 | Jan 2018 | Jun 2018
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO-KVEST | PEOPLE'S PRECINCTS VESTIBULE REDESIGN | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO-KVEST | PEOPLE'S PRECINCTS VESTIBULE REDESIGN | 3 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | PO-KVEST | PEOPLE'S PRECINCTS VESTIBULE REDESIGN | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Mar 2020 | Sep 2019 | Sep 2025
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD13 | PROPERTY CLERK ELECTRICAL CONDUIT | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Sep 2016 | Jan 2017
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD13 | PROPERTY CLERK ELECTRICAL CONDUIT | 3 | FINAL DESIGN | Jan 2017 | May 2017 | Jan 2017 | May 2017
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD13 | PROPERTY CLERK ELECTRICAL CONDUIT | 4 | BID AWARD AND REGISTER CONTRCT | May 2017 | Nov 2017 | May 2017 | Nov 2017
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD13 | PROPERTY CLERK ELECTRICAL CONDUIT | 5 | CONSTRUCTION TO 25% | Nov 2017 | Mar 2018 | Nov 2017 | Mar 2018
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD13 | PROPERTY CLERK ELECTRICAL CONDUIT | 6 | CONSTRUCTION TO 50% | Mar 2018 | Jul 2018 | Mar 2018 | Jul 2018
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD13 | PROPERTY CLERK ELECTRICAL CONDUIT | 7 | CONSTRUCTION TO 75% | Jul 2018 | Nov 2018 | Jul 2018 | Nov 2021
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD13 | PROPERTY CLERK ELECTRICAL CONDUIT | 8 | ORIGINAL EQUIP & FURNISHING | Nov 2018 | Feb 2019 | Nov 2021 | Feb 2022
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD13 | PROPERTY CLERK ELECTRICAL CONDUIT | 9 | SUBSTANTIAL COMPLETION | Feb 2019 | Apr 2019 | Feb 2022 | Apr 2022
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD13 | PROPERTY CLERK ELECTRICAL CONDUIT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2019 | May 2019 | Apr 2022 | May 2022
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD3 | POLICE SERVICE AREA 1 (PSA1) | 1 | DEVELOP SCOPE | Sep 2016 | Dec 2016 | Jun 2016 | Sep 2016
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD3 | POLICE SERVICE AREA 1 (PSA1) | 2 | PRELIMINARY DESIGN | Dec 2016 | Apr 2017 | Sep 2016 | Jan 2017
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD3 | POLICE SERVICE AREA 1 (PSA1) | 3 | FINAL DESIGN | Apr 2017 | Aug 2017 | Jan 2017 | May 2017
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD3 | POLICE SERVICE AREA 1 (PSA1) | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2017 | Feb 2018 | May 2017 | Nov 2017
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD3 | POLICE SERVICE AREA 1 (PSA1) | 5 | CONSTRUCTION TO 25% | Feb 2018 | Jun 2018 | Nov 2017 | Mar 2018
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD3 | POLICE SERVICE AREA 1 (PSA1) | 6 | CONSTRUCTION TO 50% | Jun 2018 | Sep 2018 | Mar 2018 | Jun 2018
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD3 | POLICE SERVICE AREA 1 (PSA1) | 7 | CONSTRUCTION TO 75% | Sep 2018 | Jan 2019 | Jun 2018 | Oct 2021
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD3 | POLICE SERVICE AREA 1 (PSA1) | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2019 | Apr 2019 | Oct 2021 | Jan 2022
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD3 | POLICE SERVICE AREA 1 (PSA1) | 9 | SUBSTANTIAL COMPLETION | Apr 2019 | Jun 2019 | Jan 2022 | Mar 2022
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD3 | POLICE SERVICE AREA 1 (PSA1) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2019 | Jul 2019 | Mar 2022 | Apr 2025
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD4 | FLOYD BENNETT FIELD ELECTRICAL | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Jun 2016 | Sep 2016
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD4 | FLOYD BENNETT FIELD ELECTRICAL | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Sep 2016 | Jan 2017
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD4 | FLOYD BENNETT FIELD ELECTRICAL | 3 | FINAL DESIGN | Jan 2017 | May 2017 | Jan 2017 | May 2017
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD4 | FLOYD BENNETT FIELD ELECTRICAL | 4 | BID AWARD AND REGISTER CONTRCT | May 2017 | Nov 2017 | May 2017 | Nov 2017
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD4 | FLOYD BENNETT FIELD ELECTRICAL | 5 | CONSTRUCTION TO 25% | Nov 2017 | Mar 2018 | Nov 2017 | Mar 2018
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD4 | FLOYD BENNETT FIELD ELECTRICAL | 6 | CONSTRUCTION TO 50% | Mar 2018 | Jul 2018 | Mar 2018 | Jul 2018
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD4 | FLOYD BENNETT FIELD ELECTRICAL | 7 | CONSTRUCTION TO 75% | Jul 2018 | Nov 2018 | Jul 2018 | Nov 2021
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD4 | FLOYD BENNETT FIELD ELECTRICAL | 8 | ORIGINAL EQUIP & FURNISHING | Nov 2018 | Feb 2019 | Nov 2021 | Feb 2022
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD4 | FLOYD BENNETT FIELD ELECTRICAL | 9 | SUBSTANTIAL COMPLETION | Feb 2019 | Apr 2019 | Feb 2022 | Apr 2022
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD4 | FLOYD BENNETT FIELD ELECTRICAL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2019 | May 2019 | Apr 2022 | May 2025
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD5 | TRANSIT DISTRICT 34 ELECTRICAL | 1 | DEVELOP SCOPE | Sep 2016 | Dec 2016 | Jun 2016 | Sep 2016
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD5 | TRANSIT DISTRICT 34 ELECTRICAL | 2 | PRELIMINARY DESIGN | Dec 2016 | Apr 2017 | Sep 2016 | Jan 2017
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD5 | TRANSIT DISTRICT 34 ELECTRICAL | 3 | FINAL DESIGN | Apr 2017 | Aug 2017 | Jan 2017 | May 2017
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD5 | TRANSIT DISTRICT 34 ELECTRICAL | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2017 | Feb 2018 | May 2017 | Nov 2017
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD5 | TRANSIT DISTRICT 34 ELECTRICAL | 5 | CONSTRUCTION TO 25% | Feb 2018 | Jun 2018 | Nov 2017 | Mar 2018
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD5 | TRANSIT DISTRICT 34 ELECTRICAL | 6 | CONSTRUCTION TO 50% | Jun 2018 | Sep 2018 | Mar 2018 | Jun 2018
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD5 | TRANSIT DISTRICT 34 ELECTRICAL | 7 | CONSTRUCTION TO 75% | Sep 2018 | Jan 2019 | Jun 2018 | Oct 2021
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD5 | TRANSIT DISTRICT 34 ELECTRICAL | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2019 | Apr 2019 | Oct 2021 | Jan 2022
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD5 | TRANSIT DISTRICT 34 ELECTRICAL | 9 | SUBSTANTIAL COMPLETION | Apr 2019 | Jun 2019 | Jan 2022 | Mar 2022
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD5 | TRANSIT DISTRICT 34 ELECTRICAL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2019 | Jul 2019 | Mar 2022 | Apr 2025
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDWARE | 23RD STR WAREHOUSE RECONSTRUCTION | 1 | DEVELOP SCOPE | May 2017 | Aug 2017 | May 2017 | Mar 2021
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDWARE | 23RD STR WAREHOUSE RECONSTRUCTION | 2 | PRELIMINARY DESIGN | Aug 2017 | Dec 2017 | Mar 2021 | Jul 2021
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDWARE | 23RD STR WAREHOUSE RECONSTRUCTION | 3 | FINAL DESIGN | Dec 2017 | Apr 2018 | Jul 2021 | Nov 2021
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDWARE | 23RD STR WAREHOUSE RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2018 | Oct 2018 | Nov 2021 | May 2022
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDWARE | 23RD STR WAREHOUSE RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | May 2022 | Sep 2022
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDWARE | 23RD STR WAREHOUSE RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Sep 2022 | Jan 2023
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDWARE | 23RD STR WAREHOUSE RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jan 2023 | May 2023
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDWARE | 23RD STR WAREHOUSE RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | May 2023 | Aug 2023
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDWARE | 23RD STR WAREHOUSE RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Aug 2023 | Oct 2023
20231026 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDWARE | 23RD STR WAREHOUSE RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Oct 2023 | Nov 2023
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN231 | Building Automation Controls at EC276 | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN231 | Building Automation Controls at EC276 | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN231 | Building Automation Controls at EC276 | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN231 | Building Automation Controls at EC276 | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN231 | Building Automation Controls at EC276 | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN231 | Building Automation Controls at EC276 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN703 | FDNY - DESIGN & INSTALLATION OF 37 KW SOLAR SYSTEM AT EC332 | 1 | DEVELOP SCOPE | Oct 2017 | Jan 2018 | Oct 2017 | Jan 2018
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN703 | FDNY - DESIGN & INSTALLATION OF 37 KW SOLAR SYSTEM AT EC332 | 2 | PRELIMINARY DESIGN | Jan 2018 | May 2018 | Jan 2018 | May 2018
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN703 | FDNY - DESIGN & INSTALLATION OF 37 KW SOLAR SYSTEM AT EC332 | 3 | FINAL DESIGN | May 2018 | Nov 2018 | May 2018 | Nov 2018
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN703 | FDNY - DESIGN & INSTALLATION OF 37 KW SOLAR SYSTEM AT EC332 | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2018 | Feb 2019 | Nov 2018 | Feb 2019
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN703 | FDNY - DESIGN & INSTALLATION OF 37 KW SOLAR SYSTEM AT EC332 | 5 | CONSTRUCTION TO 25% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN703 | FDNY - DESIGN & INSTALLATION OF 37 KW SOLAR SYSTEM AT EC332 | 6 | CONSTRUCTION TO 50% | Jun 2019 | Oct 2019 | Jun 2019 | Oct 2019
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN703 | FDNY - DESIGN & INSTALLATION OF 37 KW SOLAR SYSTEM AT EC332 | 7 | CONSTRUCTION TO 75% | Oct 2019 | Feb 2020 | Oct 2019 | Nov 2021
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN703 | FDNY - DESIGN & INSTALLATION OF 37 KW SOLAR SYSTEM AT EC332 | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2020 | May 2020 | Dec 2021 | Feb 2022
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN703 | FDNY - DESIGN & INSTALLATION OF 37 KW SOLAR SYSTEM AT EC332 | 9 | SUBSTANTIAL COMPLETION | May 2020 | Jun 2020 | Mar 2022 | Apr 2022
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN703 | FDNY - DESIGN & INSTALLATION OF 37 KW SOLAR SYSTEM AT EC332 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Jul 2020 | Apr 2022 | May 2024
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN801 | FDNY - Solar Photo-voltaic system at EMS 58 | 1 | DEVELOP SCOPE | Sep 2018 | Nov 2018 | Sep 2018 | Dec 2018
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN801 | FDNY - Solar Photo-voltaic system at EMS 58 | 2 | PRELIMINARY DESIGN | Nov 2018 | Mar 2019 | Dec 2018 | Apr 2019
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN801 | FDNY - Solar Photo-voltaic system at EMS 58 | 3 | FINAL DESIGN | Mar 2019 | Sep 2019 | Apr 2019 | Oct 2019
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN801 | FDNY - Solar Photo-voltaic system at EMS 58 | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Dec 2019 | Oct 2019 | Jan 2020
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN801 | FDNY - Solar Photo-voltaic system at EMS 58 | 5 | CONSTRUCTION TO 25% | Dec 2019 | Apr 2020 | Jan 2020 | May 2020
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN801 | FDNY - Solar Photo-voltaic system at EMS 58 | 6 | CONSTRUCTION TO 50% | Apr 2020 | Aug 2020 | May 2020 | Sep 2020
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN801 | FDNY - Solar Photo-voltaic system at EMS 58 | 7 | CONSTRUCTION TO 75% | Aug 2020 | Dec 2020 | Sep 2020 | Dec 2022
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN801 | FDNY - Solar Photo-voltaic system at EMS 58 | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2020 | Mar 2021 | Dec 2022 | Mar 2023
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN801 | FDNY - Solar Photo-voltaic system at EMS 58 | 9 | SUBSTANTIAL COMPLETION | Mar 2021 | May 2021 | Mar 2023 | Apr 2023
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN801 | FDNY - Solar Photo-voltaic system at EMS 58 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2021 | Jun 2021 | May 2023 | Nov 2023
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN902 | FDNY - Window Replacement at 4 FDNY Fire Houses | 1 | DEVELOP SCOPE | Jun 2021 | May 2022 | Jun 2021 | May 2022
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN902 | FDNY - Window Replacement at 4 FDNY Fire Houses | 2 | BID AWARD AND REGISTER CONTRCT | May 2022 | Jul 2022 | May 2022 | Jul 2022
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN902 | FDNY - Window Replacement at 4 FDNY Fire Houses | 3 | CONSTRUCTION TO 50% | Jul 2022 | Jan 2023 | Jul 2022 | Jan 2023
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN902 | FDNY - Window Replacement at 4 FDNY Fire Houses | 4 | CONSTRUCTION TO 75% | Jan 2023 | Apr 2023 | Jan 2023 | Apr 2023
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN902 | FDNY - Window Replacement at 4 FDNY Fire Houses | 5 | SUBSTANTIAL COMPLETION | Apr 2023 | Jun 2023 | Apr 2023 | Jun 2023
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN902 | FDNY - Window Replacement at 4 FDNY Fire Houses | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2023 | Jul 2023 | Jun 2023 | Mar 2025
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | F175FASBK | Fire Alarm System at Brooklyn CO | 1 | DESIGN | Feb 2022 | Aug 2022 | Feb 2022 | Aug 2022
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | F175FASBK | Fire Alarm System at Brooklyn CO | 2 | CONSTRUCTION | Aug 2022 | Aug 2023 | Aug 2022 | Aug 2023
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | F175FASBK | Fire Alarm System at Brooklyn CO | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2023 | Nov 2023 | Aug 2023 | Jun 2026
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | F175MC218 | Multi-Component Renovations - EC218 | 1 | DESIGN | Oct 2018 | Jan 2019 | Mar 2020 | Jun 2020
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | F175MC218 | Multi-Component Renovations - EC218 | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2019 | Oct 2019 | Jun 2020 | Mar 2021
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | F175MC218 | Multi-Component Renovations - EC218 | 3 | CONSTRUCTION | Oct 2019 | Nov 2020 | Mar 2021 | Apr 2022
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | F175MC218 | Multi-Component Renovations - EC218 | 4 | ORIGINAL EQUIP & FURNISHING | Nov 2020 | Dec 2020 | Apr 2022 | Jun 2022
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | F175MC218 | Multi-Component Renovations - EC218 | 5 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Jun 2022 | Jul 2022
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | F175MC218 | Multi-Component Renovations - EC218 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Apr 2021 | Jul 2022 | Jun 2024
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175D214 | DOOR REPLACEMENT - EC214 | 1 | CONSTRUCTION | Sep 2017 | Sep 2018 | Sep 2017 | Sep 2018
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175D214 | DOOR REPLACEMENT - EC214 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2018 | Dec 2018 | Sep 2018 | Dec 2018
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175D230 | DOOR REPLACEMENT - EC230 | 1 | CONSTRUCTION | Sep 2017 | Sep 2018 | Sep 2017 | Sep 2018
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175D230 | DOOR REPLACEMENT - EC230 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2018 | Dec 2018 | Sep 2018 | Dec 2018
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175D231 | OVERHEAD DOOR - EC 231/LADDER 120 | 1 | CONSTRUCTION | Nov 2023 | Nov 2024 | Nov 2023 | Nov 2024
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175D231 | OVERHEAD DOOR - EC 231/LADDER 120 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2024 | Feb 2025 | Nov 2024 | Feb 2025
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175D241 | DOOR REPLACEMENT - EC241 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2018 | Dec 2018 | Sep 2018 | Dec 2018
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175D271 | Door Replacement - EC271 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Jun 2020 | Sep 2021 | Dec 2021
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175D281 | DOOR REPLACEMENT - EC281 | 1 | CONSTRUCTION | Sep 2017 | Sep 2018 | Sep 2017 | Sep 2018
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175D281 | DOOR REPLACEMENT - EC281 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2018 | Dec 2018 | Sep 2018 | Dec 2018
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175DS32 | SPEED DOOR - EMS STATION 32 | 1 | CONSTRUCTION | Nov 2023 | Nov 2024 | Nov 2023 | Nov 2024
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175DS32 | SPEED DOOR - EMS STATION 32 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2024 | Feb 2025 | Nov 2024 | Feb 2025
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175G318 | GENERATOR - EC 318 | 1 | DESIGN | Feb 2024 | Aug 2024 | Feb 2024 | Aug 2024
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175G318 | GENERATOR - EC 318 | 2 | CONSTRUCTION | Aug 2024 | Aug 2025 | Aug 2024 | Aug 2025
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175G318 | GENERATOR - EC 318 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2025 | Nov 2025 | Aug 2025 | Nov 2025
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175W245 | WINDOW REPLACEMENT - EC245 | 1 | CONSTRUCTION | Mar 2018 | Feb 2019 | Mar 2018 | Mar 2019
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175W245 | WINDOW REPLACEMENT - EC245 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | May 2019 | Mar 2019 | Dec 2029
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175W248 | WINDOW REPLACEMENT - EC248 | 1 | CONSTRUCTION | Feb 2018 | Jan 2019 | Feb 2018 | Sep 2022
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175W248 | WINDOW REPLACEMENT - EC248 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2019 | May 2019 | Sep 2022 | Dec 2022
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175W330 | Window Replacement - EC330 | 1 | DESIGN | Jan 2019 | Jul 2019 | Jan 2019 | Jul 2019
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175W330 | Window Replacement - EC330 | 2 | CONSTRUCTION | Jul 2019 | Jul 2020 | Jul 2019 | Jul 2020
20231026 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175W330 | Window Replacement - EC330 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Oct 2020 | Jul 2020 | May 2024
20231026 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | CSK002NLC | NEW LIFE CHILD DEVEL. CTR. DCC AT 295 WOODBINE STREET, BK. | 1 | DEVELOP SCOPE | Jul 2007 | Oct 2007 | Jul 2007 | Oct 2007
20231026 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | CSK002NLC | NEW LIFE CHILD DEVEL. CTR. DCC AT 295 WOODBINE STREET, BK. | 2 | BID AWARD AND REGISTER CONTRCT | Oct 2007 | Jan 2008 | Oct 2007 | Jan 2008
20231026 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | CSK002NLC | NEW LIFE CHILD DEVEL. CTR. DCC AT 295 WOODBINE STREET, BK. | 3 | CONSTRUCTION TO 50% | Jan 2008 | May 2008 | Jan 2008 | May 2008
20231026 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | CSK002NLC | NEW LIFE CHILD DEVEL. CTR. DCC AT 295 WOODBINE STREET, BK. | 4 | CONSTRUCTION TO 75% | May 2008 | Jul 2008 | May 2008 | Jul 2008
20231026 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | CSK002NLC | NEW LIFE CHILD DEVEL. CTR. DCC AT 295 WOODBINE STREET, BK. | 5 | SUBSTANTIAL COMPLETION | Jul 2008 | Sep 2008 | Jul 2008 | Sep 2008
20231026 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | CSK002NLC | NEW LIFE CHILD DEVEL. CTR. DCC AT 295 WOODBINE STREET, BK. | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2008 | Oct 2008 | Sep 2008 | Oct 2008
20231026 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | HRC006KCH | LOTS FOR TOTS, KINGS COUNTY HOSPITAL (RESO A COUNCIL) | 2 | BID AWARD AND REGISTER CONTRCT | May 2011 | May 2011 | Feb 2020 | Oct 2024
20231026 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | HRC006KCH | LOTS FOR TOTS, KINGS COUNTY HOSPITAL (RESO A COUNCIL) | 3 | CONSTRUCTION | May 2011 | May 2011 | Feb 2020 | Oct 2024
20231026 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | HRC006KCH | LOTS FOR TOTS, KINGS COUNTY HOSPITAL (RESO A COUNCIL) | 4 | ORIGINAL EQUIP & FURNISHING | May 2011 | May 2011 | Feb 2020 | Oct 2024
20231026 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | HRC006KCH | LOTS FOR TOTS, KINGS COUNTY HOSPITAL (RESO A COUNCIL) | 5 | SUBSTANTIAL COMPLETION | May 2011 | May 2011 | Feb 2020 | Oct 2024
20231026 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | HRC006KCH | LOTS FOR TOTS, KINGS COUNTY HOSPITAL (RESO A COUNCIL) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2011 | May 2011 | Feb 2020 | Oct 2024
20231026 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | HRC006KCH | LOTS FOR TOTS, KINGS COUNTY HOSPITAL (RESO A COUNCIL) | 7 | DESIGN | May 2011 | Nov 2011 | Feb 2020 | Oct 2024
20231026 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | HRC006KCH | LOTS FOR TOTS, KINGS COUNTY HOSPITAL (RESO A COUNCIL) | 8 | CONSTRUCTION | Nov 2011 | May 2012 | Feb 2020 | Oct 2024
20231026 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | JJZROSSLB | THE CROSSROADS JUVENILE CENTER - LIBRARY RENOVATION | 1 | DESIGN | Oct 2013 | Mar 2014 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | JJZROSSLB | THE CROSSROADS JUVENILE CENTER - LIBRARY RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2014 | Jun 2014 | Jan 2023 | Jun 2023
20231026 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | JJZROSSLB | THE CROSSROADS JUVENILE CENTER - LIBRARY RENOVATION | 3 | CONSTRUCTION | Jun 2014 | Jun 2015 | Jul 2023 | Jun 2025
20231026 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | JJZROSSLB | THE CROSSROADS JUVENILE CENTER - LIBRARY RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2015 | Jun 2015 | Jul 2025 | Jul 2025
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112BAFS | ATLANTIC ARMORY FIRE SAFETY | 1 | DESIGN | Jul 2026 | Mar 2027 | Jul 2026 | Mar 2027
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112BAFS | ATLANTIC ARMORY FIRE SAFETY | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2027 | Sep 2027 | Mar 2027 | Sep 2027
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112BAFS | ATLANTIC ARMORY FIRE SAFETY | 3 | CONSTRUCTION | Sep 2027 | Dec 2028 | Sep 2027 | Dec 2028
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112LFER | LINDEN MEN'S SHELTER - ELEVATOR REPLACEMENT | 1 | DESIGN | Jan 2019 | Sep 2019 | Jan 2019 | Sep 2019
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112LFER | LINDEN MEN'S SHELTER - ELEVATOR REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Mar 2020 | Sep 2019 | Mar 2020
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112LFER | LINDEN MEN'S SHELTER - ELEVATOR REPLACEMENT | 3 | CONSTRUCTION | Mar 2020 | Dec 2024 | Mar 2020 | Dec 2024
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112LINT | 85 LEXINGTON AVE BATHROOM RECONSTRUCTION | 1 | DESIGN | Jan 2022 | Sep 2022 | Jan 2022 | Sep 2022
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112LINT | 85 LEXINGTON AVE BATHROOM RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2022 | Mar 2023 | Sep 2022 | Mar 2023
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112LINT | 85 LEXINGTON AVE BATHROOM RECONSTRUCTION | 3 | CONSTRUCTION | Mar 2023 | Dec 2027 | Mar 2023 | Dec 2027
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112LMEP | LINDEN BOILER RECONSTRUCTION | 1 | DESIGN | Jan 2020 | Sep 2020 | Jan 2020 | Sep 2020
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112LMEP | LINDEN BOILER RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2020 | Mar 2021 | Sep 2020 | Mar 2021
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112LMEP | LINDEN BOILER RECONSTRUCTION | 3 | CONSTRUCTION | Mar 2021 | Dec 2025 | Mar 2021 | Dec 2025
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112LXBR | 85 LEXINGTON AVE BOILER RECONSTRUCTION | 1 | DESIGN | Jul 2022 | Mar 2023 | Jul 2023 | Mar 2024
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112LXBR | 85 LEXINGTON AVE BOILER RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2023 | Sep 2023 | Mar 2024 | Sep 2024
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112LXBR | 85 LEXINGTON AVE BOILER RECONSTRUCTION | 3 | CONSTRUCTION | Sep 2023 | Jun 2027 | Sep 2024 | Jun 2028
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PAFL | PAMOJA HOUSE FLOOR | 1 | DESIGN | Jan 2022 | Sep 2022 | Jan 2022 | Sep 2022
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PAFL | PAMOJA HOUSE FLOOR | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2022 | Mar 2023 | Sep 2022 | Mar 2023
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PAFL | PAMOJA HOUSE FLOOR | 3 | CONSTRUCTION | Mar 2023 | Dec 2027 | Mar 2023 | Dec 2027
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJAB | PAMOJA BOILER | 1 | DESIGN | Jul 2028 | Mar 2029 | Jul 2028 | Mar 2029
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJAB | PAMOJA BOILER | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2029 | Sep 2029 | Mar 2029 | Sep 2029
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJAB | PAMOJA BOILER | 3 | CONSTRUCTION | Sep 2029 | Jun 2032 | Sep 2029 | Jun 2032
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJFS | PAMOJA HOUSE FIRE SAFETY | 1 | DESIGN | Jul 2028 | Mar 2029 | Jul 2028 | Mar 2029
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJFS | PAMOJA HOUSE FIRE SAFETY | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2029 | Sep 2029 | Mar 2029 | Sep 2029
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJFS | PAMOJA HOUSE FIRE SAFETY | 3 | CONSTRUCTION | Sep 2029 | Jun 2032 | Sep 2029 | Jun 2032
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJRR | PAMOJA HOUSE - ROOF REPLACEMENT | 1 | DEVELOP SCOPE | Aug 2013 | Nov 2013 | Oct 2015 | Jul 2016
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJRR | PAMOJA HOUSE - ROOF REPLACEMENT | 2 | PRELIMINARY DESIGN | Nov 2013 | Mar 2014 | Jul 2016 | Jan 2017
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJRR | PAMOJA HOUSE - ROOF REPLACEMENT | 3 | FINAL DESIGN | Mar 2014 | Jul 2014 | Jan 2017 | Jun 2026
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJRR | PAMOJA HOUSE - ROOF REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2014 | Jan 2015 | Jan 2017 | Jun 2026
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJRR | PAMOJA HOUSE - ROOF REPLACEMENT | 5 | CONSTRUCTION TO 25% | Jan 2015 | May 2015 | Jan 2017 | Jun 2026
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJRR | PAMOJA HOUSE - ROOF REPLACEMENT | 6 | CONSTRUCTION TO 50% | May 2015 | Sep 2015 | Jan 2017 | Jun 2026
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJRR | PAMOJA HOUSE - ROOF REPLACEMENT | 7 | CONSTRUCTION TO 75% | Sep 2015 | Jan 2016 | Jan 2017 | Jun 2026
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJRR | PAMOJA HOUSE - ROOF REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2016 | Apr 2016 | Jan 2017 | Jun 2026
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJRR | PAMOJA HOUSE - ROOF REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | Apr 2016 | May 2016 | Jan 2017 | Jun 2026
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJRR | PAMOJA HOUSE - ROOF REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2016 | Jun 2016 | Jan 2017 | Jun 2026
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PREK | RENOVATION AND IMPROVEMENTS TO THE PARK SLOPE ARMORY | 1 | DEVELOP SCOPE | Oct 2014 | Jan 2015 | Jan 2024 | Mar 2024
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PREK | RENOVATION AND IMPROVEMENTS TO THE PARK SLOPE ARMORY | 2 | PRELIMINARY DESIGN | Jan 2015 | May 2015 | Mar 2024 | Jul 2024
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PREK | RENOVATION AND IMPROVEMENTS TO THE PARK SLOPE ARMORY | 3 | FINAL DESIGN | May 2015 | Sep 2015 | Jul 2024 | Nov 2024
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PREK | RENOVATION AND IMPROVEMENTS TO THE PARK SLOPE ARMORY | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2015 | Mar 2016 | Nov 2024 | May 2025
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PREK | RENOVATION AND IMPROVEMENTS TO THE PARK SLOPE ARMORY | 5 | CONSTRUCTION TO 25% | Mar 2016 | Jul 2016 | May 2025 | Sep 2025
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PREK | RENOVATION AND IMPROVEMENTS TO THE PARK SLOPE ARMORY | 6 | CONSTRUCTION TO 50% | Jul 2016 | Nov 2016 | Sep 2025 | Jan 2026
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PREK | RENOVATION AND IMPROVEMENTS TO THE PARK SLOPE ARMORY | 7 | CONSTRUCTION TO 75% | Nov 2016 | Mar 2017 | Jan 2026 | May 2026
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PREK | RENOVATION AND IMPROVEMENTS TO THE PARK SLOPE ARMORY | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2017 | Jun 2017 | May 2026 | Aug 2026
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PREK | RENOVATION AND IMPROVEMENTS TO THE PARK SLOPE ARMORY | 9 | SUBSTANTIAL COMPLETION | Jun 2017 | Aug 2017 | Aug 2026 | Oct 2026
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PREK | RENOVATION AND IMPROVEMENTS TO THE PARK SLOPE ARMORY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2017 | Sep 2017 | Oct 2026 | Nov 2026
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PSBH | PARK SLOPE - BATHROOMS | 1 | DESIGN | Jul 2025 | Mar 2026 | Jul 2025 | Mar 2026
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PSBH | PARK SLOPE - BATHROOMS | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2026 | Sep 2026 | Mar 2026 | Sep 2026
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PSBH | PARK SLOPE - BATHROOMS | 3 | CONSTRUCTION | Sep 2026 | Jun 2028 | Sep 2026 | Jun 2028
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115BFRR | Bushwick Family Roof Replacement | 1 | DESIGN | Jan 2020 | Sep 2020 | Jan 2020 | Sep 2020
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115BFRR | Bushwick Family Roof Replacement | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2020 | Mar 2021 | Sep 2020 | Mar 2021
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115BFRR | Bushwick Family Roof Replacement | 3 | CONSTRUCTION | Mar 2021 | Dec 2025 | Mar 2021 | Dec 2025
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115BINT | BUSHWICK FAMILY FACADE RECONSTRUCTION | 1 | DESIGN | Jan 2022 | Sep 2022 | Jan 2022 | Sep 2022
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115BINT | BUSHWICK FAMILY FACADE RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2022 | Mar 2023 | Sep 2022 | Mar 2023
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115BINT | BUSHWICK FAMILY FACADE RECONSTRUCTION | 3 | CONSTRUCTION | Mar 2023 | Dec 2027 | Mar 2023 | Dec 2027
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115FBME | FANNIE BARNES BOILER RECONSTRUCTION | 1 | DESIGN | May 2021 | Feb 2022 | May 2021 | Feb 2022
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115FBME | FANNIE BARNES BOILER RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2022 | Aug 2022 | Feb 2022 | Aug 2022
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115FBME | FANNIE BARNES BOILER RECONSTRUCTION | 3 | CONSTRUCTION | Aug 2022 | May 2027 | Aug 2022 | May 2027
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115FLRF | FLATLANDS ROOF REPLACEMENT | 1 | DESIGN | Jan 2020 | Sep 2020 | Jan 2020 | Sep 2020
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115FLRF | FLATLANDS ROOF REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2020 | Mar 2021 | Sep 2020 | Mar 2021
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115FLRF | FLATLANDS ROOF REPLACEMENT | 3 | CONSTRUCTION | Mar 2021 | Dec 2025 | Mar 2021 | Dec 2025
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115MMEP | WAYSIDE MACDONOUGH BOILER RECONS | 1 | DESIGN | Jan 2019 | Sep 2019 | Jan 2019 | Sep 2019
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115MMEP | WAYSIDE MACDONOUGH BOILER RECONS | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Mar 2020 | Sep 2019 | Mar 2020
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115MMEP | WAYSIDE MACDONOUGH BOILER RECONS | 3 | CONSTRUCTION | Mar 2020 | Dec 2024 | Mar 2020 | Dec 2024
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115RMCX | ROSE MCCARTHY - WINDOW REPLACEMENT AND EXTERIOR RECONSTRUCT | 1 | PROJECT START | Jan 2018 | Jan 2018 | Jan 2018 | Sep 2018
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115RMCX | ROSE MCCARTHY - WINDOW REPLACEMENT AND EXTERIOR RECONSTRUCT | 2 | DESIGN START | Jan 2018 | Jul 2018 | Sep 2018 | Mar 2019
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115RMCX | ROSE MCCARTHY - WINDOW REPLACEMENT AND EXTERIOR RECONSTRUCT | 3 | DESIGN COMPLETION | Jul 2018 | Jan 2019 | Mar 2019 | Dec 2023
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115RMCX | ROSE MCCARTHY - WINDOW REPLACEMENT AND EXTERIOR RECONSTRUCT | 4 | CONSTRUCTION START | Jan 2019 | Jul 2019 | Mar 2019 | Dec 2023
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115RMCX | ROSE MCCARTHY - WINDOW REPLACEMENT AND EXTERIOR RECONSTRUCT | 5 | CONSTRUCTION COMPLETION | Jul 2019 | Dec 2020 | Mar 2019 | Dec 2023
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115SAEU | FANNIE BARNES EXTERIOR UPGRADE | 1 | DESIGN | Jan 2022 | Sep 2022 | Jan 2022 | Sep 2022
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115SAEU | FANNIE BARNES EXTERIOR UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2022 | Mar 2023 | Sep 2022 | Mar 2023
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115SAEU | FANNIE BARNES EXTERIOR UPGRADE | 3 | CONSTRUCTION | Mar 2023 | Dec 2027 | Mar 2023 | Dec 2027
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115SEXT | STOCKHOLM FAMILY CENTER - ROOF AND FACADE RECONSTRUCTION | 1 | DESIGN | Jan 2022 | Sep 2022 | Jan 2022 | Sep 2022
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115SEXT | STOCKHOLM FAMILY CENTER - ROOF AND FACADE RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2022 | Mar 2023 | Sep 2022 | Mar 2023
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115SEXT | STOCKHOLM FAMILY CENTER - ROOF AND FACADE RECONSTRUCTION | 3 | CONSTRUCTION | Mar 2023 | Dec 2027 | Mar 2023 | Dec 2027
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115STEP | STOCKHOLM FAMILY CENTER -BOILER RECONSTRUCTION | 1 | DESIGN | Jul 2019 | Mar 2020 | Aug 2019 | May 2020
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115STEP | STOCKHOLM FAMILY CENTER -BOILER RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Sep 2020 | May 2020 | Nov 2020
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115STEP | STOCKHOLM FAMILY CENTER -BOILER RECONSTRUCTION | 3 | CONSTRUCTION | Sep 2020 | Jun 2025 | Nov 2020 | Jun 2026
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN001 | BROOKLYN NEIGHBORHOOD IMPROVEMENT DIST.-BEDFORD AVE. RENOVAT | 1 | DEVELOP SCOPE | Jan 2014 | Apr 2014 | Aug 2022 | Apr 2023
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN001 | BROOKLYN NEIGHBORHOOD IMPROVEMENT DIST.-BEDFORD AVE. RENOVAT | 2 | PRELIMINARY DESIGN | Apr 2014 | Jul 2014 | Apr 2023 | Oct 2023
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN001 | BROOKLYN NEIGHBORHOOD IMPROVEMENT DIST.-BEDFORD AVE. RENOVAT | 3 | FINAL DESIGN | Jul 2014 | Nov 2014 | Oct 2023 | Jul 2028
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN001 | BROOKLYN NEIGHBORHOOD IMPROVEMENT DIST.-BEDFORD AVE. RENOVAT | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2014 | May 2015 | Oct 2023 | Jul 2028
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN001 | BROOKLYN NEIGHBORHOOD IMPROVEMENT DIST.-BEDFORD AVE. RENOVAT | 5 | CONSTRUCTION TO 25% | May 2015 | Sep 2015 | Oct 2023 | Jul 2028
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN001 | BROOKLYN NEIGHBORHOOD IMPROVEMENT DIST.-BEDFORD AVE. RENOVAT | 6 | CONSTRUCTION TO 50% | Sep 2015 | Jan 2016 | Oct 2023 | Jul 2028
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN001 | BROOKLYN NEIGHBORHOOD IMPROVEMENT DIST.-BEDFORD AVE. RENOVAT | 7 | CONSTRUCTION TO 75% | Jan 2016 | May 2016 | Oct 2023 | Jul 2028
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN001 | BROOKLYN NEIGHBORHOOD IMPROVEMENT DIST.-BEDFORD AVE. RENOVAT | 8 | ORIGINAL EQUIP & FURNISHING | May 2016 | Aug 2016 | Oct 2023 | Jul 2028
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN001 | BROOKLYN NEIGHBORHOOD IMPROVEMENT DIST.-BEDFORD AVE. RENOVAT | 9 | SUBSTANTIAL COMPLETION | Aug 2016 | Oct 2016 | Oct 2023 | Jul 2028
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN001 | BROOKLYN NEIGHBORHOOD IMPROVEMENT DIST.-BEDFORD AVE. RENOVAT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Nov 2016 | Oct 2023 | Jul 2028
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN002 | RENOVATION OF BEDFORD ATLANTIC ARMORY INTO RECREATIONAL CTR. | 1 | DEVELOP SCOPE | Jan 2017 | Apr 2017 | Jul 2023 | Mar 2024
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN002 | RENOVATION OF BEDFORD ATLANTIC ARMORY INTO RECREATIONAL CTR. | 2 | PRELIMINARY DESIGN | Apr 2017 | Aug 2017 | Mar 2024 | Sep 2024
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN002 | RENOVATION OF BEDFORD ATLANTIC ARMORY INTO RECREATIONAL CTR. | 3 | FINAL DESIGN | Aug 2017 | Dec 2017 | Sep 2024 | Jun 2029
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN002 | RENOVATION OF BEDFORD ATLANTIC ARMORY INTO RECREATIONAL CTR. | 4 | BID AWARD AND REGISTER CONTRCT | Dec 2017 | Jun 2018 | Sep 2024 | Jun 2029
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN002 | RENOVATION OF BEDFORD ATLANTIC ARMORY INTO RECREATIONAL CTR. | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Sep 2024 | Jun 2029
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN002 | RENOVATION OF BEDFORD ATLANTIC ARMORY INTO RECREATIONAL CTR. | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Sep 2024 | Jun 2029
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN002 | RENOVATION OF BEDFORD ATLANTIC ARMORY INTO RECREATIONAL CTR. | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Sep 2024 | Jun 2029
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN002 | RENOVATION OF BEDFORD ATLANTIC ARMORY INTO RECREATIONAL CTR. | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Aug 2019 | Sep 2024 | Jun 2029
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN002 | RENOVATION OF BEDFORD ATLANTIC ARMORY INTO RECREATIONAL CTR. | 9 | SUBSTANTIAL COMPLETION | Aug 2019 | Oct 2019 | Sep 2024 | Jun 2029
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN002 | RENOVATION OF BEDFORD ATLANTIC ARMORY INTO RECREATIONAL CTR. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2019 | Nov 2019 | Sep 2024 | Jun 2029
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN003 | BEDFORD ATLANTIC ARMORY ATHLETIC CENTER | 1 | DEVELOP SCOPE | Jan 2017 | Apr 2017 | Jan 2024 | Apr 2026
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN003 | BEDFORD ATLANTIC ARMORY ATHLETIC CENTER | 2 | PRELIMINARY DESIGN | Apr 2017 | Aug 2017 | Apr 2026 | Apr 2026
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN003 | BEDFORD ATLANTIC ARMORY ATHLETIC CENTER | 3 | FINAL DESIGN | Aug 2017 | Dec 2017 | Apr 2026 | Apr 2026
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN003 | BEDFORD ATLANTIC ARMORY ATHLETIC CENTER | 4 | BID AWARD AND REGISTER CONTRCT | Dec 2017 | Jun 2018 | Apr 2026 | Apr 2026
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN003 | BEDFORD ATLANTIC ARMORY ATHLETIC CENTER | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Apr 2026 | Apr 2026
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN003 | BEDFORD ATLANTIC ARMORY ATHLETIC CENTER | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Apr 2026 | Apr 2026
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN003 | BEDFORD ATLANTIC ARMORY ATHLETIC CENTER | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Apr 2026 | Apr 2026
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN003 | BEDFORD ATLANTIC ARMORY ATHLETIC CENTER | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Aug 2019 | Apr 2026 | Apr 2026
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN003 | BEDFORD ATLANTIC ARMORY ATHLETIC CENTER | 9 | SUBSTANTIAL COMPLETION | Aug 2019 | Oct 2019 | Apr 2026 | Apr 2026
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN003 | BEDFORD ATLANTIC ARMORY ATHLETIC CENTER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2019 | Nov 2019 | Apr 2026 | Jun 2027
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS3 | Solar PV system - Flatlands Residence | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2020 | Sep 2019 | Jun 2020
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS3 | Solar PV system - Flatlands Residence | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Aug 2020 | Jun 2020 | Dec 2020
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS3 | Solar PV system - Flatlands Residence | 3 | CONSTRUCTION TO 50% | Aug 2020 | Feb 2021 | Dec 2020 | Sep 2025
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS3 | Solar PV system - Flatlands Residence | 4 | CONSTRUCTION TO 75% | Feb 2021 | May 2021 | Dec 2020 | Sep 2025
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS3 | Solar PV system - Flatlands Residence | 5 | SUBSTANTIAL COMPLETION | May 2021 | Jul 2021 | Dec 2020 | Sep 2025
20231026 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS3 | Solar PV system - Flatlands Residence | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Aug 2021 | Dec 2020 | Sep 2025
20231026 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25BEDS | BedStuy MSC Life and Safety Upgrades | 1 | DESIGN | Jul 2023 | Dec 2023 | Jul 2025 | Dec 2025
20231026 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25BEDS | BedStuy MSC Life and Safety Upgrades | 2 | CONSTRUCTION | Dec 2023 | Jun 2024 | Dec 2025 | Jun 2026
20231026 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25FOST2 | Construction at 102-50 Foster Ave to accomodate warehouses | 1 | DESIGN | Oct 2019 | Mar 2020 | Oct 2025 | Mar 2026
20231026 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25FOST2 | Construction at 102-50 Foster Ave to accomodate warehouses | 2 | CONSTRUCTION | Mar 2020 | Sep 2020 | Mar 2026 | Sep 2026
20231026 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25PTMFC | Construction: 102-50 Foster Ave Print to Mail Relocation | 1 | DESIGN | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25PTMFC | Construction: 102-50 Foster Ave Print to Mail Relocation | 2 | CONSTRUCTION | Sep 2023 | Mar 2024 | Sep 2023 | Mar 2024
20231026 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HRCNBDST | Bedford Stuyvesant MSC Boiler Replacement, 1958 Fulton St | 1 | DESIGN | Nov 2010 | Feb 2011 | Jul 2027 | Dec 2027
20231026 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HRCNBDST | Bedford Stuyvesant MSC Boiler Replacement, 1958 Fulton St | 2 | CONSTRUCTION | Feb 2011 | Aug 2011 | Dec 2027 | Jun 2028
20231026 | BROOKLYN | 125 | DEPARTMENT FOR THE AGING | AGREDHOOK | PB: -Red Hook Senior Center -- Funding for senior center | 1 | DEVELOP SCOPE | Jun 2022 | Nov 2022 | Jun 2022 | Nov 2022
20231026 | BROOKLYN | 125 | DEPARTMENT FOR THE AGING | AGREDHOOK | PB: -Red Hook Senior Center -- Funding for senior center | 2 | PRELIMINARY DESIGN | Nov 2022 | May 2023 | Nov 2022 | May 2023
20231026 | BROOKLYN | 125 | DEPARTMENT FOR THE AGING | AGREDHOOK | PB: -Red Hook Senior Center -- Funding for senior center | 3 | CONSTRUCTION | May 2023 | May 2024 | May 2023 | Jun 2026
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230GLOV | NYA - Glovers Reef Exhibit Tank Reconstruction | 1 | DEVELOP SCOPE | Jul 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230GLOV | NYA - Glovers Reef Exhibit Tank Reconstruction | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230GLOV | NYA - Glovers Reef Exhibit Tank Reconstruction | 3 | CONSTRUCTION TO 50% | Dec 2025 | Apr 2026 | Dec 2025 | Apr 2026
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230GLOV | NYA - Glovers Reef Exhibit Tank Reconstruction | 4 | CONSTRUCTION TO 75% | Apr 2026 | Jun 2026 | Apr 2026 | Jun 2026
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230GLOV | NYA - Glovers Reef Exhibit Tank Reconstruction | 5 | SUBSTANTIAL COMPLETION | Jun 2026 | Aug 2026 | Jun 2026 | Aug 2026
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230GLOV | NYA - Glovers Reef Exhibit Tank Reconstruction | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2026 | Sep 2026 | Aug 2026 | Sep 2026
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230-SEA | WCS - New York Aquarium - Sea Cliffs Exhibit | 1 | DEVELOP SCOPE | Aug 2015 | Nov 2015 | Jun 2026 | Sep 2026
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230-SEA | WCS - New York Aquarium - Sea Cliffs Exhibit | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2015 | Feb 2016 | Sep 2026 | Dec 2026
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230-SEA | WCS - New York Aquarium - Sea Cliffs Exhibit | 3 | CONSTRUCTION TO 50% | Feb 2016 | Jun 2016 | Dec 2026 | Apr 2027
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230-SEA | WCS - New York Aquarium - Sea Cliffs Exhibit | 4 | CONSTRUCTION TO 75% | Jun 2016 | Aug 2016 | Apr 2027 | Jun 2027
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230-SEA | WCS - New York Aquarium - Sea Cliffs Exhibit | 5 | SUBSTANTIAL COMPLETION | Aug 2016 | Oct 2016 | Jun 2027 | Aug 2027
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230-SEA | WCS - New York Aquarium - Sea Cliffs Exhibit | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Nov 2016 | Aug 2027 | Sep 2027
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230TENS | Tensile Roof Replacement at Main Ticketing Entry | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230TENS | Tensile Roof Replacement at Main Ticketing Entry | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230TENS | Tensile Roof Replacement at Main Ticketing Entry | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230TENS | Tensile Roof Replacement at Main Ticketing Entry | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230TENS | Tensile Roof Replacement at Main Ticketing Entry | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230TENS | Tensile Roof Replacement at Main Ticketing Entry | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230TENS | Tensile Roof Replacement at Main Ticketing Entry | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230TENS | Tensile Roof Replacement at Main Ticketing Entry | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230TENS | Tensile Roof Replacement at Main Ticketing Entry | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230TENS | Tensile Roof Replacement at Main Ticketing Entry | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2028 | Sep 2028
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2023 | Dec 2023 | Sep 2028 | Jan 2029
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 3 | CONSTRUCTION TO 50% | Dec 2023 | Apr 2024 | Jan 2029 | Jul 2029
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 4 | CONSTRUCTION TO 75% | Apr 2024 | Jun 2024 | Jul 2029 | Oct 2029
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 5 | SUBSTANTIAL COMPLETION | Jun 2024 | Aug 2024 | Oct 2029 | Feb 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2024 | Sep 2024 | Feb 2030 | Jun 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 7 | DEVELOP SCOPE | Sep 2024 | Dec 2024 | Jun 2030 | Oct 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 8 | PRELIMINARY DESIGN | Dec 2024 | Apr 2025 | Oct 2030 | Jan 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 9 | FINAL DESIGN | Apr 2025 | Oct 2025 | Jan 2031 | Mar 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 10 | BID AWARD AND REGISTER CONTRCT | Oct 2025 | Jan 2026 | Mar 2031 | Apr 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 11 | CONSTRUCTION TO 25% | Jan 2026 | May 2026 | Mar 2031 | Apr 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 12 | CONSTRUCTION TO 50% | May 2026 | Sep 2026 | Mar 2031 | Apr 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 13 | CONSTRUCTION TO 75% | Sep 2026 | Jan 2027 | Mar 2031 | Apr 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 14 | ORIGINAL EQUIP & FURNISHING | Jan 2027 | Apr 2027 | Mar 2031 | Apr 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 15 | SUBSTANTIAL COMPLETION | Apr 2027 | Jun 2027 | Mar 2031 | Apr 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | 16 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2027 | Jul 2027 | Mar 2031 | Apr 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AMER | BMA - Brooklyn Museum - American Gallery Renovations | 1 | DEVELOP SCOPE | Jul 2025 | Sep 2025 | Jul 2029 | Sep 2029
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AMER | BMA - Brooklyn Museum - American Gallery Renovations | 2 | PRELIMINARY DESIGN | Sep 2025 | Jan 2026 | Sep 2029 | Jan 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AMER | BMA - Brooklyn Museum - American Gallery Renovations | 3 | FINAL DESIGN | Jan 2026 | Jul 2026 | Jan 2030 | Jul 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AMER | BMA - Brooklyn Museum - American Gallery Renovations | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2026 | Oct 2026 | Jul 2030 | Oct 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AMER | BMA - Brooklyn Museum - American Gallery Renovations | 5 | CONSTRUCTION TO 25% | Oct 2026 | Feb 2027 | Oct 2030 | Feb 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AMER | BMA - Brooklyn Museum - American Gallery Renovations | 6 | CONSTRUCTION TO 50% | Feb 2027 | Jun 2027 | Feb 2031 | Jun 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AMER | BMA - Brooklyn Museum - American Gallery Renovations | 7 | CONSTRUCTION TO 75% | Jun 2027 | Oct 2027 | Jun 2031 | Oct 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AMER | BMA - Brooklyn Museum - American Gallery Renovations | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jan 2028 | Oct 2031 | Jan 2032
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AMER | BMA - Brooklyn Museum - American Gallery Renovations | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Mar 2028 | Jan 2032 | Mar 2032
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AMER | BMA - Brooklyn Museum - American Gallery Renovations | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2028 | Apr 2028 | Mar 2032 | Apr 2032
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236AUDI | BBG - Auditorium Renovations | 1 | DEVELOP SCOPE | Dec 2010 | Feb 2011 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236AUDI | BBG - Auditorium Renovations | 2 | PRELIMINARY DESIGN | Mar 2011 | Jun 2011 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236AUDI | BBG - Auditorium Renovations | 3 | FINAL DESIGN | Jun 2011 | Dec 2011 | Jan 2024 | Jul 2024
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236AUDI | BBG - Auditorium Renovations | 4 | BID AWARD AND REGISTER CONTRCT | Dec 2011 | Mar 2012 | Jul 2024 | Oct 2024
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236AUDI | BBG - Auditorium Renovations | 5 | CONSTRUCTION TO 25% | Mar 2012 | Jul 2012 | Oct 2024 | Feb 2025
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236AUDI | BBG - Auditorium Renovations | 6 | CONSTRUCTION TO 50% | Jul 2012 | Nov 2012 | Feb 2025 | Jun 2025
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236AUDI | BBG - Auditorium Renovations | 7 | CONSTRUCTION TO 75% | Nov 2012 | Mar 2013 | Jun 2025 | Oct 2025
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236AUDI | BBG - Auditorium Renovations | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2013 | Jun 2013 | Oct 2025 | Jan 2026
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236AUDI | BBG - Auditorium Renovations | 9 | SUBSTANTIAL COMPLETION | Jun 2013 | Aug 2013 | Jan 2026 | Mar 2026
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236AUDI | BBG - Auditorium Renovations | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2013 | Sep 2013 | Mar 2026 | Apr 2026
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236BCSG | BBG - Brooklyn Botanic Garden - Sustainable Gardening Center | 1 | DESIGN | Sep 2016 | Sep 2017 | Jun 2028 | Sep 2028
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236BCSG | BBG - Brooklyn Botanic Garden - Sustainable Gardening Center | 2 | CONSTRUCTION | Sep 2017 | Sep 2018 | Sep 2028 | Sep 2029
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236BCSG | BBG - Brooklyn Botanic Garden - Sustainable Gardening Center | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2017 | Sep 2018 | Sep 2029 | Sep 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236-NSY | BBG - North Service Yard | 1 | DEVELOP SCOPE | Jul 2025 | Sep 2025 | Jun 2028 | Sep 2028
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236-NSY | BBG - North Service Yard | 2 | PRELIMINARY DESIGN | Sep 2025 | Jan 2026 | Sep 2028 | Jan 2029
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236-NSY | BBG - North Service Yard | 3 | FINAL DESIGN | Jan 2026 | Jul 2026 | Jan 2029 | Jul 2029
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236-NSY | BBG - North Service Yard | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2026 | Oct 2026 | Jul 2029 | Oct 2029
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236-NSY | BBG - North Service Yard | 5 | CONSTRUCTION TO 25% | Oct 2026 | Feb 2027 | Oct 2029 | Feb 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236-NSY | BBG - North Service Yard | 6 | CONSTRUCTION TO 50% | Feb 2027 | Jun 2027 | Feb 2030 | Jun 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236-NSY | BBG - North Service Yard | 7 | CONSTRUCTION TO 75% | Jun 2027 | Oct 2027 | Jun 2030 | Oct 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236-NSY | BBG - North Service Yard | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jan 2028 | Oct 2030 | Jan 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236-NSY | BBG - North Service Yard | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Mar 2028 | Jan 2031 | Mar 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236-NSY | BBG - North Service Yard | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2028 | Apr 2028 | Mar 2031 | Apr 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236PERG | BBG Osborne Garden Pergola | 1 | DEVELOP SCOPE | Jun 2028 | Sep 2028 | Jun 2028 | Sep 2028
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236PERG | BBG Osborne Garden Pergola | 2 | PRELIMINARY DESIGN | Sep 2028 | Jan 2029 | Sep 2028 | Jan 2029
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236PERG | BBG Osborne Garden Pergola | 3 | FINAL DESIGN | Jan 2029 | Jul 2029 | Jan 2029 | Jul 2029
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236PERG | BBG Osborne Garden Pergola | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2029 | Oct 2029 | Jul 2029 | Oct 2029
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236PERG | BBG Osborne Garden Pergola | 5 | CONSTRUCTION TO 25% | Oct 2029 | Feb 2030 | Oct 2029 | Feb 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236PERG | BBG Osborne Garden Pergola | 6 | CONSTRUCTION TO 50% | Feb 2030 | Jun 2030 | Feb 2030 | Jun 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236PERG | BBG Osborne Garden Pergola | 7 | CONSTRUCTION TO 75% | Jun 2030 | Oct 2030 | Jun 2030 | Oct 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236PERG | BBG Osborne Garden Pergola | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2030 | Jan 2031 | Oct 2030 | Jan 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236PERG | BBG Osborne Garden Pergola | 9 | SUBSTANTIAL COMPLETION | Jan 2031 | Mar 2031 | Jan 2031 | Mar 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236PERG | BBG Osborne Garden Pergola | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2031 | Apr 2031 | Mar 2031 | Apr 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236ROSE | BBG -Brooklyn Botanic Garden - Accessibility Improvements | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2027 | Sep 2027
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236ROSE | BBG -Brooklyn Botanic Garden - Accessibility Improvements | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2021 | Dec 2021 | Sep 2027 | Dec 2027
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236ROSE | BBG -Brooklyn Botanic Garden - Accessibility Improvements | 3 | CONSTRUCTION TO 50% | Dec 2021 | Apr 2022 | Dec 2027 | Apr 2028
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236ROSE | BBG -Brooklyn Botanic Garden - Accessibility Improvements | 4 | CONSTRUCTION TO 75% | Apr 2022 | Jun 2022 | Apr 2028 | Jun 2028
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236ROSE | BBG -Brooklyn Botanic Garden - Accessibility Improvements | 5 | SUBSTANTIAL COMPLETION | Jun 2022 | Aug 2022 | Jun 2028 | Aug 2028
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236ROSE | BBG -Brooklyn Botanic Garden - Accessibility Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2022 | Sep 2022 | Aug 2028 | Sep 2028
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262-GEO | BCM - Geothermal wells redesign and renovation | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2028 | Sep 2028
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262-GEO | BCM - Geothermal wells redesign and renovation | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2028 | Jan 2029
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262-GEO | BCM - Geothermal wells redesign and renovation | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2029 | Jul 2029
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262-GEO | BCM - Geothermal wells redesign and renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2029 | Oct 2029
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262-GEO | BCM - Geothermal wells redesign and renovation | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2029 | Feb 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262-GEO | BCM - Geothermal wells redesign and renovation | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2030 | Jun 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262-GEO | BCM - Geothermal wells redesign and renovation | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2030 | Oct 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262-GEO | BCM - Geothermal wells redesign and renovation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2030 | Jan 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262-GEO | BCM - Geothermal wells redesign and renovation | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2031 | Mar 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262-GEO | BCM - Geothermal wells redesign and renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2031 | Apr 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264-PJS | BAM - Peter J. Sharp Infrastructure Improvments Escalator | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264-PJS | BAM - Peter J. Sharp Infrastructure Improvments Escalator | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264-PJS | BAM - Peter J. Sharp Infrastructure Improvments Escalator | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264-PJS | BAM - Peter J. Sharp Infrastructure Improvments Escalator | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264-PJS | BAM - Peter J. Sharp Infrastructure Improvments Escalator | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264-PJS | BAM - Peter J. Sharp Infrastructure Improvments Escalator | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264-PJS | BAM - Peter J. Sharp Infrastructure Improvments Escalator | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264-PJS | BAM - Peter J. Sharp Infrastructure Improvments Escalator | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264-PJS | BAM - Peter J. Sharp Infrastructure Improvments Escalator | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264-PJS | BAM - Peter J. Sharp Infrastructure Improvments Escalator | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264ROSE | BAM - Rose Renovation | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2028 | Sep 2028
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264ROSE | BAM - Rose Renovation | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2028 | Jan 2029
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264ROSE | BAM - Rose Renovation | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2029 | Jul 2029
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264ROSE | BAM - Rose Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2029 | Oct 2029
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264ROSE | BAM - Rose Renovation | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2029 | Feb 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264ROSE | BAM - Rose Renovation | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2030 | Jun 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264ROSE | BAM - Rose Renovation | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2030 | Oct 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264ROSE | BAM - Rose Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2030 | Jan 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264ROSE | BAM - Rose Renovation | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2031 | Mar 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264ROSE | BAM - Rose Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2031 | Apr 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264RRHT | BAM- Harvey Theater Roof Replacement | 1 | DEVELOP SCOPE | Jun 2027 | Sep 2027 | Jun 2027 | Sep 2027
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264RRHT | BAM- Harvey Theater Roof Replacement | 2 | PRELIMINARY DESIGN | Sep 2027 | Jan 2028 | Sep 2027 | Jan 2028
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264RRHT | BAM- Harvey Theater Roof Replacement | 3 | FINAL DESIGN | Jan 2028 | Jul 2028 | Jan 2028 | Jul 2028
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264RRHT | BAM- Harvey Theater Roof Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2028 | Oct 2028 | Jul 2028 | Oct 2028
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264RRHT | BAM- Harvey Theater Roof Replacement | 5 | CONSTRUCTION TO 25% | Oct 2028 | Feb 2029 | Oct 2028 | Feb 2029
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264RRHT | BAM- Harvey Theater Roof Replacement | 6 | CONSTRUCTION TO 50% | Feb 2029 | Jun 2029 | Feb 2029 | Jun 2029
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264RRHT | BAM- Harvey Theater Roof Replacement | 7 | CONSTRUCTION TO 75% | Jun 2029 | Oct 2029 | Jun 2029 | Oct 2029
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264RRHT | BAM- Harvey Theater Roof Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2029 | Jan 2030 | Oct 2029 | Jan 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264RRHT | BAM- Harvey Theater Roof Replacement | 9 | SUBSTANTIAL COMPLETION | Jan 2030 | Mar 2030 | Jan 2030 | Mar 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264RRHT | BAM- Harvey Theater Roof Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2030 | Apr 2030 | Mar 2030 | Apr 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467BKLN | DCA - Brooklyn Fund | 1 | DEVELOP SCOPE | Jul 2024 | Oct 2024 | Jun 2028 | Sep 2028
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467BKLN | DCA - Brooklyn Fund | 2 | PRELIMINARY DESIGN | Oct 2024 | Feb 2025 | Sep 2028 | Jan 2029
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467BKLN | DCA - Brooklyn Fund | 3 | FINAL DESIGN | Feb 2025 | Aug 2025 | Jan 2029 | Jul 2029
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467BKLN | DCA - Brooklyn Fund | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2025 | Nov 2025 | Jul 2029 | Oct 2029
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467BKLN | DCA - Brooklyn Fund | 5 | CONSTRUCTION TO 25% | Nov 2025 | Mar 2026 | Oct 2029 | Feb 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467BKLN | DCA - Brooklyn Fund | 6 | CONSTRUCTION TO 50% | Mar 2026 | Jul 2026 | Feb 2030 | Jun 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467BKLN | DCA - Brooklyn Fund | 7 | CONSTRUCTION TO 75% | Jul 2026 | Nov 2026 | Jun 2030 | Oct 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467BKLN | DCA - Brooklyn Fund | 8 | ORIGINAL EQUIP & FURNISHING | Nov 2026 | Feb 2027 | Oct 2030 | Jan 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467BKLN | DCA - Brooklyn Fund | 9 | SUBSTANTIAL COMPLETION | Feb 2027 | Apr 2027 | Jan 2031 | Mar 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467BKLN | DCA - Brooklyn Fund | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2027 | May 2027 | Mar 2031 | Apr 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467DBCD | DBCD South Site Cultural Condo | 1 | DEVELOP SCOPE | Jul 2026 | Sep 2026 | Jun 2028 | Sep 2028
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467DBCD | DBCD South Site Cultural Condo | 2 | PRELIMINARY DESIGN | Sep 2026 | Jan 2027 | Sep 2028 | Jan 2029
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467DBCD | DBCD South Site Cultural Condo | 3 | FINAL DESIGN | Jan 2027 | Jul 2027 | Jan 2029 | Jul 2029
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467DBCD | DBCD South Site Cultural Condo | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2027 | Oct 2027 | Jul 2029 | Oct 2029
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467DBCD | DBCD South Site Cultural Condo | 5 | CONSTRUCTION TO 25% | Oct 2027 | Feb 2028 | Oct 2029 | Feb 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467DBCD | DBCD South Site Cultural Condo | 6 | CONSTRUCTION TO 50% | Feb 2028 | Jun 2028 | Feb 2030 | Jun 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467DBCD | DBCD South Site Cultural Condo | 7 | CONSTRUCTION TO 75% | Jun 2028 | Oct 2028 | Jun 2030 | Oct 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467DBCD | DBCD South Site Cultural Condo | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2028 | Jan 2029 | Oct 2030 | Jan 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467DBCD | DBCD South Site Cultural Condo | 9 | SUBSTANTIAL COMPLETION | Jan 2029 | Mar 2029 | Jan 2031 | Mar 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467DBCD | DBCD South Site Cultural Condo | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2029 | Apr 2029 | Mar 2031 | Apr 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467SWBB | AREA Brooklyn Bridge Park | 1 | DEVELOP SCOPE | Dec 2017 | Mar 2018 | Jun 2029 | Sep 2029
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467SWBB | AREA Brooklyn Bridge Park | 2 | PRELIMINARY DESIGN | Mar 2018 | Jul 2018 | Sep 2029 | Jan 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467SWBB | AREA Brooklyn Bridge Park | 3 | FINAL DESIGN | Jul 2018 | Jan 2019 | Jan 2030 | Jul 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467SWBB | AREA Brooklyn Bridge Park | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2019 | Apr 2019 | Jul 2030 | Oct 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467SWBB | AREA Brooklyn Bridge Park | 5 | CONSTRUCTION TO 25% | Apr 2019 | Aug 2019 | Oct 2030 | Feb 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467SWBB | AREA Brooklyn Bridge Park | 6 | CONSTRUCTION TO 50% | Aug 2019 | Dec 2019 | Feb 2031 | Jun 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467SWBB | AREA Brooklyn Bridge Park | 7 | CONSTRUCTION TO 75% | Dec 2019 | Apr 2020 | Jun 2031 | Oct 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467SWBB | AREA Brooklyn Bridge Park | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2020 | Jul 2020 | Oct 2031 | Jan 2032
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467SWBB | AREA Brooklyn Bridge Park | 9 | SUBSTANTIAL COMPLETION | Jul 2020 | Aug 2020 | Jan 2032 | Mar 2032
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467SWBB | AREA Brooklyn Bridge Park | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2020 | Sep 2020 | Mar 2032 | Apr 2032
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV654BSRC | BSRC - Innovation Campus EDC | 1 | DEVELOP SCOPE | Jul 2029 | Sep 2029 | Jul 2029 | Sep 2029
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV654BSRC | BSRC - Innovation Campus EDC | 2 | PRELIMINARY DESIGN | Sep 2029 | Jan 2030 | Sep 2029 | Jan 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV654BSRC | BSRC - Innovation Campus EDC | 3 | FINAL DESIGN | Jan 2030 | Jul 2030 | Jan 2030 | Jul 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV654BSRC | BSRC - Innovation Campus EDC | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2030 | Oct 2030 | Jul 2030 | Oct 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV654BSRC | BSRC - Innovation Campus EDC | 5 | CONSTRUCTION TO 25% | Oct 2030 | Feb 2031 | Oct 2030 | Feb 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV654BSRC | BSRC - Innovation Campus EDC | 6 | CONSTRUCTION TO 50% | Feb 2031 | Jun 2031 | Feb 2031 | Jun 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV654BSRC | BSRC - Innovation Campus EDC | 7 | CONSTRUCTION TO 75% | Jun 2031 | Oct 2031 | Jun 2031 | Oct 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV654BSRC | BSRC - Innovation Campus EDC | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2031 | Jan 2032 | Oct 2031 | Jan 2032
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV654BSRC | BSRC - Innovation Campus EDC | 9 | SUBSTANTIAL COMPLETION | Jan 2032 | Mar 2032 | Jan 2032 | Mar 2032
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV654BSRC | BSRC - Innovation Campus EDC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2032 | Apr 2032 | Mar 2032 | Apr 2032
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PVCPRBLDG | CPR - Preservation of Artist Workspace | 1 | DEVELOP SCOPE | Jun 2026 | Sep 2026 | Jun 2029 | Sep 2029
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PVCPRBLDG | CPR - Preservation of Artist Workspace | 2 | PRELIMINARY DESIGN | Sep 2026 | Jan 2027 | Sep 2029 | Jan 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PVCPRBLDG | CPR - Preservation of Artist Workspace | 3 | FINAL DESIGN | Jan 2027 | Jul 2027 | Jan 2030 | Jul 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PVCPRBLDG | CPR - Preservation of Artist Workspace | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2027 | Oct 2027 | Jul 2030 | Oct 2030
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PVCPRBLDG | CPR - Preservation of Artist Workspace | 5 | CONSTRUCTION TO 25% | Oct 2027 | Feb 2028 | Oct 2030 | Feb 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PVCPRBLDG | CPR - Preservation of Artist Workspace | 6 | CONSTRUCTION TO 50% | Feb 2028 | Jun 2028 | Feb 2031 | Jun 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PVCPRBLDG | CPR - Preservation of Artist Workspace | 7 | CONSTRUCTION TO 75% | Jun 2028 | Oct 2028 | Jun 2031 | Oct 2031
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PVCPRBLDG | CPR - Preservation of Artist Workspace | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2028 | Jan 2029 | Oct 2031 | Jan 2032
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PVCPRBLDG | CPR - Preservation of Artist Workspace | 9 | SUBSTANTIAL COMPLETION | Jan 2029 | Mar 2029 | Jan 2032 | Mar 2032
20231026 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PVCPRBLDG | CPR - Preservation of Artist Workspace | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2029 | Apr 2029 | Mar 2032 | Apr 2032
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMNSITEA | BAM Cultural District - North Site Condemnation | 1 | DESIGN | Jan 2010 | Jan 2012 | Jan 2012 | Jan 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMNSITEA | BAM Cultural District - North Site Condemnation | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2012 | Jan 2012 | Jan 2016 | Jan 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMNSITEA | BAM Cultural District - North Site Condemnation | 3 | CONSTRUCTION | Jan 2012 | Jan 2014 | Jan 2016 | Jan 2018
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMNSITEA | BAM Cultural District - North Site Condemnation | 4 | ORIGINAL EQUIP & FURNISHING | Jan 2014 | Jan 2014 | Jan 2018 | Jan 2018
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMNSITEA | BAM Cultural District - North Site Condemnation | 5 | SUBSTANTIAL COMPLETION | Jan 2014 | Jan 2014 | Jan 2018 | Jan 2018
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMNSITEA | BAM Cultural District - North Site Condemnation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2014 | Jan 2014 | Jan 2018 | Jun 2027
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMTFANA | FA - Theatre for a New Audience | 1 | DESIGN | Mar 2009 | Mar 2011 | Mar 2009 | Mar 2011
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMTFANA | FA - Theatre for a New Audience | 2 | BID AWARD AND REGISTER CONTRCT | Apr 2011 | Mar 2011 | Apr 2011 | Mar 2011
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMTFANA | FA - Theatre for a New Audience | 3 | CONSTRUCTION | Apr 2011 | Mar 2013 | Apr 2011 | Mar 2013
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMTFANA | FA - Theatre for a New Audience | 4 | ORIGINAL EQUIP & FURNISHING | Apr 2013 | Mar 2013 | Apr 2013 | Mar 2013
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMTFANA | FA - Theatre for a New Audience | 5 | SUBSTANTIAL COMPLETION | Apr 2013 | Mar 2013 | Apr 2013 | Mar 2013
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMTFANA | FA - Theatre for a New Audience | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2013 | Apr 2013 | Apr 2013 | Apr 2013
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAT4LAN | BAT Pier 4: Ferry Landing Rehabilitation | 1 | DESIGN | Aug 2006 | Aug 2006 | Aug 2018 | Sep 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAT4LAN | BAT Pier 4: Ferry Landing Rehabilitation | 2 | BID AWARD AND REGISTER CONTRCT | Aug 2006 | Sep 2006 | Sep 2024 | Sep 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAT4LAN | BAT Pier 4: Ferry Landing Rehabilitation | 3 | CONSTRUCTION | Sep 2006 | Oct 2006 | May 2007 | Jun 2017
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAT4LAN | BAT Pier 4: Ferry Landing Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | Oct 2006 | Oct 2006 | Jul 2017 | Jun 2017
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAT4LAN | BAT Pier 4: Ferry Landing Rehabilitation | 5 | SUBSTANTIAL COMPLETION | Oct 2006 | Nov 2006 | Jul 2017 | Jun 2017
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAT4LAN | BAT Pier 4: Ferry Landing Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2006 | Nov 2006 | Jul 2017 | Jul 2027
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATAGFLA | Brooklyn Army Terminal Building A Ground Floor Activation | 1 | DESIGN | Jul 2022 | Jul 2022 | Jul 2022 | Jul 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATAGFLA | Brooklyn Army Terminal Building A Ground Floor Activation | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Aug 2022 | Jul 2022 | Aug 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATAGFLA | Brooklyn Army Terminal Building A Ground Floor Activation | 3 | CONSTRUCTION | Aug 2022 | Sep 2022 | Aug 2022 | Sep 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATAGFLA | Brooklyn Army Terminal Building A Ground Floor Activation | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Sep 2022 | Sep 2022 | Sep 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATAGFLA | Brooklyn Army Terminal Building A Ground Floor Activation | 5 | SUBSTANTIAL COMPLETION | Sep 2022 | Oct 2022 | Sep 2022 | Oct 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATAGFLA | Brooklyn Army Terminal Building A Ground Floor Activation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2022 | Jun 2023 | Oct 2022 | Jun 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATAIMPS | Brooklyn Army Terminal Bldg A Improvements | 1 | DESIGN | Jul 2022 | Jul 2022 | Jul 2022 | Jul 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATAIMPS | Brooklyn Army Terminal Bldg A Improvements | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Aug 2022 | Jul 2022 | Aug 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATAIMPS | Brooklyn Army Terminal Bldg A Improvements | 3 | CONSTRUCTION | Aug 2022 | Sep 2022 | Aug 2022 | Sep 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATAIMPS | Brooklyn Army Terminal Bldg A Improvements | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Sep 2022 | Sep 2022 | Sep 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATAIMPS | Brooklyn Army Terminal Bldg A Improvements | 5 | SUBSTANTIAL COMPLETION | Sep 2022 | Oct 2022 | Sep 2022 | Oct 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATAIMPS | Brooklyn Army Terminal Bldg A Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2022 | Jun 2027 | Oct 2022 | Jun 2027
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATANCHOR | BAT Anchor Tenant Strategy | 1 | DESIGN | Jul 2018 | Jul 2018 | Mar 2020 | Apr 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATANCHOR | BAT Anchor Tenant Strategy | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Aug 2018 | Apr 2020 | Apr 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATANCHOR | BAT Anchor Tenant Strategy | 3 | CONSTRUCTION | Aug 2018 | Sep 2018 | Apr 2020 | May 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATANCHOR | BAT Anchor Tenant Strategy | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2018 | Sep 2018 | Jun 2020 | Jun 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATANCHOR | BAT Anchor Tenant Strategy | 5 | SUBSTANTIAL COMPLETION | Sep 2018 | Oct 2018 | Jun 2020 | Jun 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATANCHOR | BAT Anchor Tenant Strategy | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2018 | Oct 2018 | Jun 2020 | Jun 2029
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATBEYOND | BAT New Needs | 1 | DESIGN | Dec 2014 | Jan 2015 | Dec 2017 | Jan 2018
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATBEYOND | BAT New Needs | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2015 | Jan 2015 | Jan 2018 | Jan 2018
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATBEYOND | BAT New Needs | 3 | CONSTRUCTION | Jan 2015 | Mar 2015 | Jan 2018 | Mar 2018
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATBEYOND | BAT New Needs | 4 | ORIGINAL EQUIP & FURNISHING | Mar 2015 | Mar 2015 | Mar 2018 | Mar 2018
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATBEYOND | BAT New Needs | 5 | SUBSTANTIAL COMPLETION | Mar 2015 | Mar 2015 | Mar 2018 | Mar 2018
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATBEYOND | BAT New Needs | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Apr 2015 | Mar 2018 | Jun 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATBIMPS | Brooklyn Army Terminal Bldg B Improvements | 1 | DESIGN | Jul 2022 | Jul 2022 | Jul 2022 | Jul 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATBIMPS | Brooklyn Army Terminal Bldg B Improvements | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Aug 2022 | Jul 2022 | Aug 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATBIMPS | Brooklyn Army Terminal Bldg B Improvements | 3 | CONSTRUCTION | Aug 2022 | Sep 2022 | Aug 2022 | Sep 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATBIMPS | Brooklyn Army Terminal Bldg B Improvements | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Sep 2022 | Sep 2022 | Sep 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATBIMPS | Brooklyn Army Terminal Bldg B Improvements | 5 | SUBSTANTIAL COMPLETION | Sep 2022 | Oct 2022 | Sep 2022 | Oct 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATBIMPS | Brooklyn Army Terminal Bldg B Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2022 | Jun 2023 | Oct 2022 | Jun 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATIMPRO | BAT Improvements | 1 | DESIGN | Jul 2007 | Jul 2007 | Jun 2009 | Jul 2009
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATIMPRO | BAT Improvements | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2007 | Aug 2007 | Jul 2009 | Aug 2009
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATIMPRO | BAT Improvements | 3 | CONSTRUCTION | Aug 2007 | Jun 2008 | Aug 2009 | Jun 2010
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATIMPRO | BAT Improvements | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2008 | Jun 2008 | Jul 2010 | Jun 2010
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATIMPRO | BAT Improvements | 5 | SUBSTANTIAL COMPLETION | Jul 2008 | Jun 2008 | Jul 2010 | Jun 2010
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATIMPRO | BAT Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2008 | Jul 2008 | Jul 2010 | Jun 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATLUMP | Lump Sum - BAT 20-824466-Y9707 | 1 | DESIGN | Sep 2008 | Oct 2010 | Sep 2008 | Oct 2010
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATLUMP | Lump Sum - BAT 20-824466-Y9707 | 2 | BID AWARD AND REGISTER CONTRCT | Oct 2010 | Oct 2010 | Oct 2010 | Oct 2010
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATLUMP | Lump Sum - BAT 20-824466-Y9707 | 3 | CONSTRUCTION | Oct 2010 | Oct 2012 | Oct 2010 | Oct 2012
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATLUMP | Lump Sum - BAT 20-824466-Y9707 | 4 | ORIGINAL EQUIP & FURNISHING | Oct 2012 | Oct 2012 | Oct 2012 | Oct 2012
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATLUMP | Lump Sum - BAT 20-824466-Y9707 | 5 | SUBSTANTIAL COMPLETION | Oct 2012 | Oct 2012 | Oct 2012 | Oct 2012
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATLUMP | Lump Sum - BAT 20-824466-Y9707 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2012 | Oct 2012 | Oct 2012 | Jun 2031
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATPLUGIN | BAT Plug-In Industrial Strategy | 1 | DESIGN | Jul 2018 | Jul 2018 | Mar 2020 | Apr 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATPLUGIN | BAT Plug-In Industrial Strategy | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Aug 2018 | Apr 2020 | Apr 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATPLUGIN | BAT Plug-In Industrial Strategy | 3 | CONSTRUCTION | Aug 2018 | Sep 2018 | Apr 2020 | May 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATPLUGIN | BAT Plug-In Industrial Strategy | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2018 | Sep 2018 | Jun 2020 | Jun 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATPLUGIN | BAT Plug-In Industrial Strategy | 5 | SUBSTANTIAL COMPLETION | Sep 2018 | Oct 2018 | Jun 2020 | Jun 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATPLUGIN | BAT Plug-In Industrial Strategy | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2018 | Oct 2018 | Jun 2020 | Jun 2029
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATRPZDEP | BAT RPZ Installation - DEP Compliance | 1 | DESIGN | Jul 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATRPZDEP | BAT RPZ Installation - DEP Compliance | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Aug 2022 | Jul 2022 | Aug 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATRPZDEP | BAT RPZ Installation - DEP Compliance | 3 | CONSTRUCTION | Aug 2022 | Sep 2022 | Aug 2022 | Sep 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATRPZDEP | BAT RPZ Installation - DEP Compliance | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Sep 2022 | Sep 2022 | Sep 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATRPZDEP | BAT RPZ Installation - DEP Compliance | 5 | SUBSTANTIAL COMPLETION | Sep 2022 | Oct 2022 | Sep 2022 | Oct 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATRPZDEP | BAT RPZ Installation - DEP Compliance | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2022 | Jun 2024 | Oct 2022 | Jun 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BCTMCABLE | Brooklyn Cruise Terminal - Mobile Cable Positioning Device | 1 | DESIGN | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BCTMCABLE | Brooklyn Cruise Terminal - Mobile Cable Positioning Device | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Aug 2021 | Jul 2021 | Aug 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BCTMCABLE | Brooklyn Cruise Terminal - Mobile Cable Positioning Device | 3 | CONSTRUCTION | Aug 2021 | Sep 2021 | Aug 2021 | Sep 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BCTMCABLE | Brooklyn Cruise Terminal - Mobile Cable Positioning Device | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Sep 2021 | Sep 2021 | Sep 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BCTMCABLE | Brooklyn Cruise Terminal - Mobile Cable Positioning Device | 5 | SUBSTANTIAL COMPLETION | Sep 2021 | Oct 2025 | Sep 2021 | Oct 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BCTMCABLE | Brooklyn Cruise Terminal - Mobile Cable Positioning Device | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2025 | Oct 2025 | Oct 2025 | Oct 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKBRESP | Brooklyn Bridge Esplanade | 1 | DESIGN | Jul 2019 | Jul 2019 | Jul 2019 | Jul 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKBRESP | Brooklyn Bridge Esplanade | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jul 2019 | Aug 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKBRESP | Brooklyn Bridge Esplanade | 3 | CONSTRUCTION | Aug 2019 | Sep 2019 | Aug 2019 | Sep 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKBRESP | Brooklyn Bridge Esplanade | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Sep 2019 | Sep 2019 | Sep 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKBRESP | Brooklyn Bridge Esplanade | 5 | SUBSTANTIAL COMPLETION | Sep 2019 | Oct 2021 | Sep 2019 | Oct 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKBRESP | Brooklyn Bridge Esplanade | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2021 | Oct 2021 | Oct 2021 | Jun 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCRUISE | Brooklyn Cruise Terminal Substructre Rehab | 1 | DESIGN | Jan 2008 | Jan 2009 | Dec 2009 | Jun 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCRUISE | Brooklyn Cruise Terminal Substructre Rehab | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2009 | Jan 2009 | Jun 2025 | Jun 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCRUISE | Brooklyn Cruise Terminal Substructre Rehab | 3 | CONSTRUCTION | Jan 2009 | Jan 2011 | Jun 2025 | Jun 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCRUISE | Brooklyn Cruise Terminal Substructre Rehab | 4 | ORIGINAL EQUIP & FURNISHING | Jan 2011 | Jan 2011 | Jun 2025 | Jun 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCRUISE | Brooklyn Cruise Terminal Substructre Rehab | 5 | SUBSTANTIAL COMPLETION | Jan 2011 | Jan 2011 | Jun 2025 | Jun 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCRUISE | Brooklyn Cruise Terminal Substructre Rehab | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2011 | Jan 2011 | Jun 2025 | Jun 2030
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCRUISE | Brooklyn Cruise Terminal Substructre Rehab | 7 | DESIGN | Jan 2011 | Jan 2011 | Jun 2025 | Jun 2030
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCRUISE | Brooklyn Cruise Terminal Substructre Rehab | 8 | BID AWARD AND REGISTER CONTRCT | Jan 2011 | Feb 2011 | Jun 2025 | Jun 2030
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCRUISE | Brooklyn Cruise Terminal Substructre Rehab | 9 | CONSTRUCTION | Feb 2011 | Mar 2011 | Jun 2025 | Jun 2030
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCRUISE | Brooklyn Cruise Terminal Substructre Rehab | 10 | ORIGINAL EQUIP & FURNISHING | Mar 2011 | Mar 2011 | Jun 2025 | Jun 2030
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCRUISE | Brooklyn Cruise Terminal Substructre Rehab | 11 | SUBSTANTIAL COMPLETION | Mar 2011 | Apr 2011 | Jun 2025 | Jun 2030
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCRUISE | Brooklyn Cruise Terminal Substructre Rehab | 12 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2011 | Apr 2011 | Jun 2025 | Jun 2030
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCTPIER | Brooklyn Cruise Terminal Pier 12 Substructure Rehab | 1 | DESIGN | Jul 2017 | Jul 2017 | Jul 2019 | Jul 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCTPIER | Brooklyn Cruise Terminal Pier 12 Substructure Rehab | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Aug 2017 | Jul 2019 | Aug 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCTPIER | Brooklyn Cruise Terminal Pier 12 Substructure Rehab | 3 | CONSTRUCTION | Aug 2017 | Sep 2017 | Aug 2019 | Sep 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCTPIER | Brooklyn Cruise Terminal Pier 12 Substructure Rehab | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Sep 2017 | Sep 2019 | Sep 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCTPIER | Brooklyn Cruise Terminal Pier 12 Substructure Rehab | 5 | SUBSTANTIAL COMPLETION | Sep 2017 | Oct 2017 | Sep 2019 | Oct 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCTPIER | Brooklyn Cruise Terminal Pier 12 Substructure Rehab | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2017 | Oct 2017 | Oct 2019 | Jun 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNY5THST | BNYDC 5th Street Reconstruction | 1 | DESIGN | Jan 2019 | Feb 2019 | May 2023 | Sep 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNY5THST | BNYDC 5th Street Reconstruction | 2 | CONSTRUCTION | Feb 2019 | Apr 2019 | May 2023 | Sep 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNY5THST | BNYDC 5th Street Reconstruction | 3 | SUBSTANTIAL COMPLETION | Apr 2019 | Jun 2019 | Sep 2023 | Mar 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNY5THST | BNYDC 5th Street Reconstruction | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2019 | Jun 2019 | Sep 2023 | Mar 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNY5THST | BNYDC 5th Street Reconstruction | 5 | SUBSTANTIAL COMPLETION | Jun 2019 | Jun 2019 | Mar 2024 | Apr 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNY5THST | BNYDC 5th Street Reconstruction | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2019 | Jun 2019 | Apr 2024 | Jun 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNY910SBB | BNYDC Berths 9, 10 and Small Boat Basin Structural Work | 1 | DESIGN | Jun 2019 | Oct 2020 | Jun 2019 | Oct 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNY910SBB | BNYDC Berths 9, 10 and Small Boat Basin Structural Work | 2 | CONSTRUCTION | May 2020 | Feb 2023 | Jun 2019 | Oct 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNY910SBB | BNYDC Berths 9, 10 and Small Boat Basin Structural Work | 3 | SUBSTANTIAL COMPLETION | Nov 2022 | Mar 2024 | May 2020 | Nov 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNY910SBB | BNYDC Berths 9, 10 and Small Boat Basin Structural Work | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Mar 2024 | May 2020 | Nov 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNY910SBB | BNYDC Berths 9, 10 and Small Boat Basin Structural Work | 5 | SUBSTANTIAL COMPLETION | Mar 2024 | Mar 2024 | Nov 2025 | Jun 2027
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNY910SBB | BNYDC Berths 9, 10 and Small Boat Basin Structural Work | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Mar 2024 | Jun 2027 | Jun 2027
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB131RM | BNYDC Building 131 Asbestos and Mold Remediation - 1st Floor | 1 | DESIGN | Dec 2019 | Jan 2020 | Jun 2022 | Jan 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB131RM | BNYDC Building 131 Asbestos and Mold Remediation - 1st Floor | 2 | CONSTRUCTION | Jan 2020 | May 2020 | Jun 2022 | Jan 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB131RM | BNYDC Building 131 Asbestos and Mold Remediation - 1st Floor | 3 | SUBSTANTIAL COMPLETION | May 2020 | Jul 2020 | Jan 2023 | May 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB131RM | BNYDC Building 131 Asbestos and Mold Remediation - 1st Floor | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Jul 2020 | Jan 2023 | May 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB131RM | BNYDC Building 131 Asbestos and Mold Remediation - 1st Floor | 5 | SUBSTANTIAL COMPLETION | Jul 2020 | Jul 2020 | May 2023 | Jul 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB131RM | BNYDC Building 131 Asbestos and Mold Remediation - 1st Floor | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Jul 2020 | Jul 2023 | Jul 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB280RF | BNYDC Building 280 Roof | 1 | DESIGN | Jan 2020 | Mar 2020 | Jul 2022 | Oct 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB280RF | BNYDC Building 280 Roof | 2 | CONSTRUCTION | Mar 2020 | Jul 2020 | Jul 2022 | Oct 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB280RF | BNYDC Building 280 Roof | 3 | SUBSTANTIAL COMPLETION | Jul 2020 | Sep 2020 | Oct 2022 | Apr 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB280RF | BNYDC Building 280 Roof | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2020 | Oct 2022 | Apr 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB280RF | BNYDC Building 280 Roof | 5 | SUBSTANTIAL COMPLETION | Sep 2020 | Sep 2020 | Apr 2023 | Aug 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB280RF | BNYDC Building 280 Roof | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2020 | Aug 2023 | Dec 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB3SUBD | BNYDC Building 3 Subdivision | 1 | DESIGN | Jan 2020 | Mar 2020 | Jul 2022 | Aug 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB3SUBD | BNYDC Building 3 Subdivision | 2 | CONSTRUCTION | Mar 2020 | Jul 2020 | Jul 2022 | Aug 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB3SUBD | BNYDC Building 3 Subdivision | 3 | CONSTRUCTION | Jul 2020 | Sep 2020 | Aug 2022 | Apr 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB3SUBD | BNYDC Building 3 Subdivision | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2020 | Aug 2022 | Apr 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB3SUBD | BNYDC Building 3 Subdivision | 5 | SUBSTANTIAL COMPLETION | Sep 2020 | Sep 2020 | Apr 2023 | Oct 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB3SUBD | BNYDC Building 3 Subdivision | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2020 | Oct 2023 | Feb 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBD132 | BNYDC Building 132 Roof Rehabilitation | 1 | DESIGN | Dec 2018 | Aug 2019 | Dec 2018 | Jan 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBD132 | BNYDC Building 132 Roof Rehabilitation | 2 | CONSTRUCTION | Aug 2019 | Dec 2020 | Dec 2018 | Jan 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBD132 | BNYDC Building 132 Roof Rehabilitation | 3 | SUBSTANTIAL COMPLETION | Dec 2020 | Jul 2021 | Jan 2023 | Apr 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBD132 | BNYDC Building 132 Roof Rehabilitation | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Jul 2021 | Jan 2023 | Apr 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBD132 | BNYDC Building 132 Roof Rehabilitation | 5 | SUBSTANTIAL COMPLETION | Jul 2021 | Jul 2021 | Apr 2024 | Nov 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBD132 | BNYDC Building 132 Roof Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Jul 2021 | Nov 2024 | Nov 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBDELEV | BNYDC Elevator Reconstruction and Replacement | 1 | DESIGN | Jul 2016 | Jul 2016 | Jun 2019 | Jan 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBDELEV | BNYDC Elevator Reconstruction and Replacement | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Jan 2020 | Apr 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBDELEV | BNYDC Elevator Reconstruction and Replacement | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Apr 2020 | Nov 2032
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBDELEV | BNYDC Elevator Reconstruction and Replacement | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Nov 2032 | Feb 2033
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBDELEV | BNYDC Elevator Reconstruction and Replacement | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Feb 2033 | Mar 2033
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBDELEV | BNYDC Elevator Reconstruction and Replacement | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2016 | Mar 2033 | Mar 2033
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBLDG50 | BNYDC Building 50 Roof Rehabilitation | 1 | DESIGN | Dec 2018 | Aug 2019 | Dec 2018 | Aug 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBLDG50 | BNYDC Building 50 Roof Rehabilitation | 2 | CONSTRUCTION | Aug 2019 | Dec 2020 | Dec 2018 | Aug 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBLDG50 | BNYDC Building 50 Roof Rehabilitation | 3 | CONSTRUCTION | Dec 2020 | Jul 2021 | Aug 2019 | Apr 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBLDG50 | BNYDC Building 50 Roof Rehabilitation | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Jul 2021 | Aug 2019 | Apr 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBLDG50 | BNYDC Building 50 Roof Rehabilitation | 5 | SUBSTANTIAL COMPLETION | Jul 2021 | Jul 2021 | Apr 2022 | Jan 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBLDG50 | BNYDC Building 50 Roof Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Jul 2021 | Jan 2024 | Apr 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYCUNY | BNYDC - CUNY Building 3 7th Floor Buildout | 1 | DESIGN | Jan 2022 | Mar 2022 | Oct 2023 | Dec 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYCUNY | BNYDC - CUNY Building 3 7th Floor Buildout | 2 | CONSTRUCTION | Mar 2022 | Jun 2022 | Oct 2023 | Dec 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYCUNY | BNYDC - CUNY Building 3 7th Floor Buildout | 3 | SUBSTANTIAL COMPLETION | Jun 2022 | Aug 2022 | Jan 2024 | Dec 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYCUNY | BNYDC - CUNY Building 3 7th Floor Buildout | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2022 | Aug 2022 | Jan 2024 | Dec 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYCUNY | BNYDC - CUNY Building 3 7th Floor Buildout | 5 | SUBSTANTIAL COMPLETION | Aug 2022 | Aug 2022 | Dec 2024 | Apr 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYCUNY | BNYDC - CUNY Building 3 7th Floor Buildout | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2022 | Aug 2022 | Apr 2025 | Jun 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYDCSUBF | BNYDC Con Edison Substation F Upgrade | 1 | DESIGN | Jul 2018 | Jul 2018 | Mar 2018 | Jan 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYDCSUBF | BNYDC Con Edison Substation F Upgrade | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Aug 2018 | Jan 2019 | Apr 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYDCSUBF | BNYDC Con Edison Substation F Upgrade | 3 | CONSTRUCTION | Aug 2018 | Sep 2018 | Apr 2019 | Mar 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYDCSUBF | BNYDC Con Edison Substation F Upgrade | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2018 | Sep 2018 | Mar 2024 | Oct 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYDCSUBF | BNYDC Con Edison Substation F Upgrade | 5 | SUBSTANTIAL COMPLETION | Sep 2018 | Oct 2018 | Oct 2024 | Jan 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYDCSUBF | BNYDC Con Edison Substation F Upgrade | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2018 | Oct 2018 | Jan 2025 | May 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYDCWELD | BNYDC Welding Lab | 1 | DESIGN | Oct 2019 | Nov 2019 | Jun 2021 | Jul 2030
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYDCWELD | BNYDC Welding Lab | 2 | CONSTRUCTION | Nov 2019 | Mar 2020 | Jun 2021 | Jul 2030
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYDCWELD | BNYDC Welding Lab | 3 | SUBSTANTIAL COMPLETION | Mar 2020 | May 2020 | Jul 2030 | Nov 2030
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYDCWELD | BNYDC Welding Lab | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2020 | May 2020 | Jul 2030 | Nov 2030
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYDCWELD | BNYDC Welding Lab | 5 | SUBSTANTIAL COMPLETION | May 2020 | May 2020 | Nov 2030 | Dec 2030
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYDCWELD | BNYDC Welding Lab | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2020 | May 2020 | Dec 2030 | May 2031
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYFNCLIN | BNYDC Fence Line Restructuring | 1 | DESIGN | Jul 2018 | Jul 2018 | Jul 2018 | Jan 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYFNCLIN | BNYDC Fence Line Restructuring | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Aug 2018 | Jan 2022 | Feb 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYFNCLIN | BNYDC Fence Line Restructuring | 3 | CONSTRUCTION | Aug 2018 | Sep 2018 | Feb 2022 | Sep 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYFNCLIN | BNYDC Fence Line Restructuring | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2018 | Sep 2018 | Sep 2023 | Oct 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYFNCLIN | BNYDC Fence Line Restructuring | 5 | SUBSTANTIAL COMPLETION | Sep 2018 | Oct 2018 | Oct 2023 | Oct 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYFNCLIN | BNYDC Fence Line Restructuring | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2018 | Oct 2018 | Oct 2023 | Nov 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYHARBOR | BNYDC PS 331 NY Harbor School Trailer Installation | 1 | DESIGN | Jul 2016 | Jul 2016 | Jun 2028 | Aug 2028
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYHARBOR | BNYDC PS 331 NY Harbor School Trailer Installation | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Aug 2028 | Nov 2028
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYHARBOR | BNYDC PS 331 NY Harbor School Trailer Installation | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Nov 2028 | Nov 2029
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYHARBOR | BNYDC PS 331 NY Harbor School Trailer Installation | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Nov 2029 | Jul 2030
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYHARBOR | BNYDC PS 331 NY Harbor School Trailer Installation | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Jul 2030 | Mar 2031
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYHARBOR | BNYDC PS 331 NY Harbor School Trailer Installation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2016 | Mar 2031 | Jun 2031
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYHITN | BNYDC HITN Eco-Rooftop Production Studio | 1 | DESIGN | Jul 2018 | Jul 2018 | Jul 2029 | Jun 2030
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYHITN | BNYDC HITN Eco-Rooftop Production Studio | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Aug 2018 | Jul 2030 | Jul 2030
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYHITN | BNYDC HITN Eco-Rooftop Production Studio | 3 | CONSTRUCTION | Aug 2018 | Sep 2018 | Jul 2030 | Jul 2031
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYHITN | BNYDC HITN Eco-Rooftop Production Studio | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2018 | Sep 2018 | Jul 2031 | Aug 2031
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYHITN | BNYDC HITN Eco-Rooftop Production Studio | 5 | SUBSTANTIAL COMPLETION | Sep 2018 | Oct 2018 | Aug 2031 | Aug 2031
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYHITN | BNYDC HITN Eco-Rooftop Production Studio | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2018 | Oct 2018 | Aug 2031 | Feb 2032
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-BD | BNYDC Infrastructure Building Rehab | 1 | DESIGN | Jul 2010 | Jul 2010 | Jul 2010 | Jun 2011
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-BD | BNYDC Infrastructure Building Rehab | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2010 | Aug 2010 | Jul 2011 | Jan 2012
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-BD | BNYDC Infrastructure Building Rehab | 3 | CONSTRUCTION | Aug 2010 | Sep 2010 | Jul 2010 | Jan 2012
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-BD | BNYDC Infrastructure Building Rehab | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2010 | Sep 2010 | Jan 2012 | Jan 2012
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-BD | BNYDC Infrastructure Building Rehab | 5 | SUBSTANTIAL COMPLETION | Sep 2010 | Oct 2010 | Dec 2010 | Jun 2012
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-BD | BNYDC Infrastructure Building Rehab | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2010 | Oct 2010 | Jul 2012 | Jun 2029
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-WF | BNYDC Infrastructure Waterfront | 1 | DESIGN | Aug 2010 | Aug 2010 | Aug 2010 | Aug 2010
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-WF | BNYDC Infrastructure Waterfront | 2 | BID AWARD AND REGISTER CONTRCT | Aug 2010 | Sep 2010 | Aug 2010 | Sep 2010
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-WF | BNYDC Infrastructure Waterfront | 3 | CONSTRUCTION | Sep 2010 | Oct 2010 | Sep 2010 | Jun 2029
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-WF | BNYDC Infrastructure Waterfront | 4 | ORIGINAL EQUIP & FURNISHING | Oct 2010 | Oct 2010 | Jun 2029 | Jun 2029
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-WF | BNYDC Infrastructure Waterfront | 5 | SUBSTANTIAL COMPLETION | Oct 2010 | Nov 2010 | Jun 2029 | Jun 2029
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-WF | BNYDC Infrastructure Waterfront | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2010 | Nov 2010 | Jun 2029 | Jun 2029
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYLIGHT | BNYDC Lighting Replacement | 1 | DESIGN | Jun 2020 | Dec 2020 | Oct 2023 | Jan 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYLIGHT | BNYDC Lighting Replacement | 2 | CONSTRUCTION | Jan 2021 | Mar 2022 | Oct 2023 | Jan 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYLIGHT | BNYDC Lighting Replacement | 3 | CONSTRUCTION | Mar 2022 | May 2022 | Jan 2024 | Jan 2026
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYLIGHT | BNYDC Lighting Replacement | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2022 | Jun 2022 | Jan 2024 | Jan 2026
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYLIGHT | BNYDC Lighting Replacement | 5 | SUBSTANTIAL COMPLETION | May 2022 | Jun 2022 | Jan 2026 | Apr 2026
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYLIGHT | BNYDC Lighting Replacement | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2022 | Jun 2022 | Apr 2026 | Jun 2026
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYLL11 | BNYDC Local Law 11 Compliance - Buildings 3 and 5 | 1 | DESIGN | Feb 2019 | Apr 2019 | Feb 2019 | Jun 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYLL11 | BNYDC Local Law 11 Compliance - Buildings 3 and 5 | 2 | CONSTRUCTION | Apr 2019 | Aug 2019 | Feb 2019 | Jun 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYLL11 | BNYDC Local Law 11 Compliance - Buildings 3 and 5 | 3 | CONSTRUCTION | Aug 2019 | Oct 2019 | Jun 2019 | Jul 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYLL11 | BNYDC Local Law 11 Compliance - Buildings 3 and 5 | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2019 | Oct 2019 | Jun 2019 | Jul 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYLL11 | BNYDC Local Law 11 Compliance - Buildings 3 and 5 | 5 | SUBSTANTIAL COMPLETION | Oct 2019 | Oct 2019 | Jul 2021 | Sep 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYLL11 | BNYDC Local Law 11 Compliance - Buildings 3 and 5 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2019 | Oct 2019 | Sep 2021 | Apr 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMACRO | BNYDC Macro Sea | 1 | DESIGN | Jul 2016 | Jul 2016 | Jul 2016 | Apr 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMACRO | BNYDC Macro Sea | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Apr 2019 | Apr 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMACRO | BNYDC Macro Sea | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Apr 2019 | May 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMACRO | BNYDC Macro Sea | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Jun 2019 | Jun 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMACRO | BNYDC Macro Sea | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Jun 2019 | Jun 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMACRO | BNYDC Macro Sea | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2016 | Jun 2019 | Jun 2028
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMWBEEI | BNYDC MWBE Equity Incubator | 1 | DESIGN | Jul 2020 | Jul 2020 | Jul 2023 | Jul 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMWBEEI | BNYDC MWBE Equity Incubator | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Aug 2020 | Jul 2023 | Aug 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMWBEEI | BNYDC MWBE Equity Incubator | 3 | CONSTRUCTION | Aug 2020 | Sep 2020 | Aug 2023 | Sep 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMWBEEI | BNYDC MWBE Equity Incubator | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Sep 2020 | Sep 2023 | Sep 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMWBEEI | BNYDC MWBE Equity Incubator | 5 | SUBSTANTIAL COMPLETION | Sep 2020 | Oct 2020 | Sep 2023 | Oct 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMWBEEI | BNYDC MWBE Equity Incubator | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2020 | Jun 2021 | Oct 2023 | Jun 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMWBEFO | BNYDC - MWBE Industrial Space Fit Out Funding | 1 | DESIGN | Jan 2023 | Mar 2023 | Jan 2024 | Mar 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMWBEFO | BNYDC - MWBE Industrial Space Fit Out Funding | 2 | CONSTRUCTION | Mar 2023 | Jun 2023 | Jan 2024 | Mar 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMWBEFO | BNYDC - MWBE Industrial Space Fit Out Funding | 3 | CONSTRUCTION | Jun 2023 | Aug 2023 | Mar 2024 | Jun 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMWBEFO | BNYDC - MWBE Industrial Space Fit Out Funding | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2023 | Aug 2023 | Mar 2024 | Jun 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMWBEFO | BNYDC - MWBE Industrial Space Fit Out Funding | 5 | SUBSTANTIAL COMPLETION | Aug 2023 | Aug 2023 | Jun 2024 | Aug 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMWBEFO | BNYDC - MWBE Industrial Space Fit Out Funding | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2023 | Aug 2023 | Aug 2024 | Aug 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYPRATT2 | BNYDC Pratt | 1 | DESIGN | Jul 2021 | Feb 2022 | Jul 2021 | Feb 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYPRATT2 | BNYDC Pratt | 2 | CONSTRUCTION | Feb 2022 | Feb 2023 | Jul 2021 | Feb 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYPRATT2 | BNYDC Pratt | 3 | CONSTRUCTION | Feb 2023 | May 2023 | Feb 2022 | Feb 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYPRATT2 | BNYDC Pratt | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2023 | Jun 2023 | Feb 2022 | Feb 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYPRATT2 | BNYDC Pratt | 5 | SUBSTANTIAL COMPLETION | May 2023 | Jun 2023 | Feb 2024 | May 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYPRATT2 | BNYDC Pratt | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2023 | Jun 2023 | May 2024 | Jun 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYROOF77 | BNYDC - Building 77 Roof | 1 | DESIGN | Jul 2019 | Aug 2019 | Jul 2026 | Jun 2027
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYROOF77 | BNYDC - Building 77 Roof | 2 | CONSTRUCTION | Aug 2019 | Dec 2019 | Jul 2026 | Jun 2027
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYROOF77 | BNYDC - Building 77 Roof | 3 | SUBSTANTIAL COMPLETION | Dec 2019 | Feb 2020 | Jul 2027 | Jun 2029
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYROOF77 | BNYDC - Building 77 Roof | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2020 | Feb 2020 | Jul 2027 | Jun 2029
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYROOF77 | BNYDC - Building 77 Roof | 5 | SUBSTANTIAL COMPLETION | Feb 2020 | Feb 2020 | Jul 2029 | Aug 2029
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYROOF77 | BNYDC - Building 77 Roof | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2020 | Feb 2020 | Aug 2029 | Aug 2030
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYRPZBF2 | BNYDC Installation of RPZ Backflow Devices Phase II & III | 1 | DESIGN | Nov 2023 | Dec 2023 | Nov 2023 | Dec 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYRPZBF2 | BNYDC Installation of RPZ Backflow Devices Phase II & III | 2 | CONSTRUCTION | Dec 2023 | Apr 2025 | Nov 2023 | Dec 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYRPZBF2 | BNYDC Installation of RPZ Backflow Devices Phase II & III | 3 | SUBSTANTIAL COMPLETION | Apr 2025 | Jun 2025 | Dec 2023 | Apr 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYRPZBF2 | BNYDC Installation of RPZ Backflow Devices Phase II & III | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2025 | Jun 2025 | Dec 2023 | Apr 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYRPZBF2 | BNYDC Installation of RPZ Backflow Devices Phase II & III | 5 | SUBSTANTIAL COMPLETION | Jun 2025 | Jun 2025 | Apr 2025 | Jun 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYRPZBF2 | BNYDC Installation of RPZ Backflow Devices Phase II & III | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2025 | Jun 2025 | Jun 2025 | Jun 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYRPZBFL | BNYDC Installation of RPZ Backflow Devices | 1 | DESIGN | Jul 2016 | Jul 2016 | Jul 2016 | Apr 2018
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYRPZBFL | BNYDC Installation of RPZ Backflow Devices | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Apr 2018 | Apr 2018
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYRPZBFL | BNYDC Installation of RPZ Backflow Devices | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Apr 2018 | Jun 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYRPZBFL | BNYDC Installation of RPZ Backflow Devices | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Jun 2023 | Jun 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYRPZBFL | BNYDC Installation of RPZ Backflow Devices | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Jun 2023 | Jun 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYRPZBFL | BNYDC Installation of RPZ Backflow Devices | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2016 | Jun 2023 | Jun 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYSPKFIR | BNYDC Sprinkler and Fire Alarm System Upgrades | 1 | DESIGN | Jul 2018 | Jul 2018 | Jul 2018 | Jun 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYSPKFIR | BNYDC Sprinkler and Fire Alarm System Upgrades | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Aug 2018 | Jul 2019 | Sep 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYSPKFIR | BNYDC Sprinkler and Fire Alarm System Upgrades | 3 | CONSTRUCTION | Aug 2018 | Sep 2018 | Sep 2019 | Mar 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYSPKFIR | BNYDC Sprinkler and Fire Alarm System Upgrades | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2018 | Sep 2018 | Mar 2025 | Mar 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYSPKFIR | BNYDC Sprinkler and Fire Alarm System Upgrades | 5 | SUBSTANTIAL COMPLETION | Sep 2018 | Oct 2018 | Mar 2025 | Apr 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYSPKFIR | BNYDC Sprinkler and Fire Alarm System Upgrades | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2018 | Oct 2018 | Apr 2025 | Apr 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYSTEAM2 | BNYDC Brooklyn STEAM Center BP | 1 | DESIGN | Jul 2021 | Aug 2021 | Jul 2029 | Aug 2029
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYSTEAM2 | BNYDC Brooklyn STEAM Center BP | 2 | CONSTRUCTION | Aug 2021 | Dec 2021 | Jul 2029 | Aug 2029
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYSTEAM2 | BNYDC Brooklyn STEAM Center BP | 3 | SUBSTANTIAL COMPLETION | Dec 2021 | Feb 2022 | Aug 2029 | Mar 2030
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYSTEAM2 | BNYDC Brooklyn STEAM Center BP | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2022 | Jun 2022 | Aug 2029 | Mar 2030
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYSTEAM2 | BNYDC Brooklyn STEAM Center BP | 5 | SUBSTANTIAL COMPLETION | Feb 2022 | Jun 2022 | Mar 2030 | Apr 2030
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYSTEAM2 | BNYDC Brooklyn STEAM Center BP | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2022 | Jun 2022 | Apr 2030 | Jun 2030
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYTIFUND | BNYDC Tenant Improvement Fund | 1 | DESIGN | Jul 2018 | Jul 2018 | Jul 2018 | Jun 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYTIFUND | BNYDC Tenant Improvement Fund | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Aug 2018 | Jul 2019 | Jun 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYTIFUND | BNYDC Tenant Improvement Fund | 3 | CONSTRUCTION | Aug 2018 | Sep 2018 | Jun 2020 | Apr 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYTIFUND | BNYDC Tenant Improvement Fund | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2018 | Sep 2018 | Apr 2025 | May 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYTIFUND | BNYDC Tenant Improvement Fund | 5 | SUBSTANTIAL COMPLETION | Sep 2018 | Oct 2018 | May 2025 | May 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYTIFUND | BNYDC Tenant Improvement Fund | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2018 | Oct 2018 | May 2025 | May 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYUBFARM | BNYDC Urban Farm Incubator | 1 | DESIGN | Jul 2018 | Jul 2018 | Jul 2026 | Jun 2027
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYUBFARM | BNYDC Urban Farm Incubator | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Aug 2018 | Jul 2027 | Jun 2028
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYUBFARM | BNYDC Urban Farm Incubator | 3 | CONSTRUCTION | Aug 2018 | Sep 2018 | Jul 2028 | Dec 2028
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYUBFARM | BNYDC Urban Farm Incubator | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2018 | Sep 2018 | Dec 2028 | Dec 2029
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYUBFARM | BNYDC Urban Farm Incubator | 5 | SUBSTANTIAL COMPLETION | Sep 2018 | Oct 2018 | Dec 2029 | Dec 2030
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYUBFARM | BNYDC Urban Farm Incubator | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2018 | Oct 2018 | Dec 2030 | Mar 2031
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYUPSTM | BNYDC Above Ground Steam Main | 1 | DESIGN | Jul 2018 | Jul 2018 | Jul 2018 | Oct 2018
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYUPSTM | BNYDC Above Ground Steam Main | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Aug 2018 | Oct 2018 | Jan 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYUPSTM | BNYDC Above Ground Steam Main | 3 | CONSTRUCTION | Aug 2018 | Sep 2018 | Jan 2019 | Apr 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYUPSTM | BNYDC Above Ground Steam Main | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2018 | Sep 2018 | Apr 2023 | May 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYUPSTM | BNYDC Above Ground Steam Main | 5 | SUBSTANTIAL COMPLETION | Sep 2018 | Oct 2018 | May 2023 | May 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYUPSTM | BNYDC Above Ground Steam Main | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2018 | Oct 2018 | May 2023 | Feb 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYWOLF | BNYDC - TIF - She Wolf Bakery | 1 | DESIGN | Jan 2023 | Feb 2023 | Jan 2023 | Feb 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYWOLF | BNYDC - TIF - She Wolf Bakery | 2 | CONSTRUCTION | Feb 2023 | Jun 2023 | Jan 2023 | Feb 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYWOLF | BNYDC - TIF - She Wolf Bakery | 3 | SUBSTANTIAL COMPLETION | Jun 2023 | Jul 2023 | Feb 2023 | Jun 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYWOLF | BNYDC - TIF - She Wolf Bakery | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2023 | Jul 2023 | Feb 2023 | Jun 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYWOLF | BNYDC - TIF - She Wolf Bakery | 5 | SUBSTANTIAL COMPLETION | Jul 2023 | Jul 2023 | Jun 2023 | Jul 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYWOLF | BNYDC - TIF - She Wolf Bakery | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2023 | Jul 2023 | Jul 2023 | Jul 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BPMCBUA | Brooklyn Medical Plaza - BPMC Bedford Armory Clinic | 1 | DESIGN | Jul 2023 | Jul 2023 | Jul 2022 | Jul 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BPMCBUA | Brooklyn Medical Plaza - BPMC Bedford Armory Clinic | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BPMCBUA | Brooklyn Medical Plaza - BPMC Bedford Armory Clinic | 3 | CONSTRUCTION | Aug 2023 | Sep 2023 | Aug 2023 | Sep 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BPMCBUA | Brooklyn Medical Plaza - BPMC Bedford Armory Clinic | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Sep 2023 | Sep 2023 | Sep 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BPMCBUA | Brooklyn Medical Plaza - BPMC Bedford Armory Clinic | 5 | SUBSTANTIAL COMPLETION | Sep 2023 | Oct 2023 | Sep 2023 | Oct 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BPMCBUA | Brooklyn Medical Plaza - BPMC Bedford Armory Clinic | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2023 | Oct 2023 | Oct 2023 | Oct 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BROADWAYJ | Broadway Junction Plaza Gateway | 1 | DESIGN | Jul 2023 | Jul 2023 | Jul 2023 | Jul 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BROADWAYJ | Broadway Junction Plaza Gateway | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BROADWAYJ | Broadway Junction Plaza Gateway | 3 | CONSTRUCTION | Aug 2023 | Sep 2023 | Aug 2023 | Sep 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BROADWAYJ | Broadway Junction Plaza Gateway | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Sep 2023 | Sep 2023 | Sep 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BROADWAYJ | Broadway Junction Plaza Gateway | 5 | SUBSTANTIAL COMPLETION | Sep 2023 | Oct 2023 | Sep 2023 | Oct 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BROADWAYJ | Broadway Junction Plaza Gateway | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2023 | Jun 2029 | Oct 2023 | Jun 2029
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHDEVSP | Bush Terminal Development Site Preparation | 1 | DESIGN | Jan 2016 | Jun 2018 | Jan 2016 | Jun 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHDEVSP | Bush Terminal Development Site Preparation | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Jun 2018 | Jul 2019 | Jun 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHDEVSP | Bush Terminal Development Site Preparation | 3 | CONSTRUCTION | Jul 2018 | Jun 2021 | Jul 2019 | Jun 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHDEVSP | Bush Terminal Development Site Preparation | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2021 | Jun 2021 | Jun 2024 | Jun 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHDEVSP | Bush Terminal Development Site Preparation | 5 | SUBSTANTIAL COMPLETION | Jul 2021 | Jun 2021 | Jun 2024 | Jun 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHDEVSP | Bush Terminal Development Site Preparation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Jul 2021 | Jun 2024 | Jul 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHTCAFE | Bush Terminal Cafe Building Improvements | 1 | DESIGN | Jul 2017 | Jul 2017 | Jul 2017 | Apr 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHTCAFE | Bush Terminal Cafe Building Improvements | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Aug 2017 | Apr 2019 | Apr 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHTCAFE | Bush Terminal Cafe Building Improvements | 3 | CONSTRUCTION | Aug 2017 | Sep 2017 | Apr 2019 | May 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHTCAFE | Bush Terminal Cafe Building Improvements | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Sep 2017 | Jun 2019 | Jun 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHTCAFE | Bush Terminal Cafe Building Improvements | 5 | SUBSTANTIAL COMPLETION | Sep 2017 | Oct 2017 | Jun 2019 | Jun 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHTCAFE | Bush Terminal Cafe Building Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2017 | Oct 2017 | Jun 2019 | Jun 2026
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUNTAC | Bush Terminal Made in NY Unit A and C | 1 | DESIGN | Jul 2017 | Jul 2017 | Jul 2017 | Apr 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUNTAC | Bush Terminal Made in NY Unit A and C | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Aug 2017 | Apr 2021 | Apr 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUNTAC | Bush Terminal Made in NY Unit A and C | 3 | CONSTRUCTION | Aug 2017 | Sep 2017 | Apr 2021 | May 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUNTAC | Bush Terminal Made in NY Unit A and C | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Sep 2017 | Jun 2021 | Jun 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUNTAC | Bush Terminal Made in NY Unit A and C | 5 | SUBSTANTIAL COMPLETION | Sep 2017 | Oct 2017 | Jun 2021 | Jun 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUNTAC | Bush Terminal Made in NY Unit A and C | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2017 | Oct 2017 | Jun 2021 | Jun 2027
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUNTBD | BUSH MINY--UNIT D | 1 | DESIGN | Jul 2019 | Jul 2019 | Jul 2019 | Jul 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUNTBD | BUSH MINY--UNIT D | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jul 2019 | Aug 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUNTBD | BUSH MINY--UNIT D | 3 | CONSTRUCTION | Aug 2019 | Sep 2019 | Aug 2019 | Sep 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUNTBD | BUSH MINY--UNIT D | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Sep 2019 | Sep 2019 | Sep 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUNTBD | BUSH MINY--UNIT D | 5 | SUBSTANTIAL COMPLETION | Sep 2019 | Oct 2021 | Sep 2019 | Oct 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUNTBD | BUSH MINY--UNIT D | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2021 | Oct 2021 | Oct 2021 | Jun 2026
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUTIL | Bush Terminal Site and Utility Improvements | 1 | DESIGN | Jul 2017 | Jul 2017 | Jul 2017 | Apr 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUTIL | Bush Terminal Site and Utility Improvements | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Aug 2017 | Apr 2022 | Apr 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUTIL | Bush Terminal Site and Utility Improvements | 3 | CONSTRUCTION | Aug 2017 | Sep 2017 | Apr 2022 | May 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUTIL | Bush Terminal Site and Utility Improvements | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Sep 2017 | Jun 2022 | Jun 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUTIL | Bush Terminal Site and Utility Improvements | 5 | SUBSTANTIAL COMPLETION | Sep 2017 | Oct 2017 | Jun 2022 | Jun 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUTIL | Bush Terminal Site and Utility Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2017 | Oct 2017 | Jun 2022 | Jun 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CANTONBLK | Canton Court Bulkhead Replacement | 1 | DESIGN | Jul 2016 | Jul 2016 | Jul 2016 | Jul 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CANTONBLK | Canton Court Bulkhead Replacement | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Jul 2016 | Aug 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CANTONBLK | Canton Court Bulkhead Replacement | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Aug 2016 | Sep 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CANTONBLK | Canton Court Bulkhead Replacement | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Sep 2016 | Sep 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CANTONBLK | Canton Court Bulkhead Replacement | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Sep 2016 | Oct 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CANTONBLK | Canton Court Bulkhead Replacement | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2016 | Oct 2016 | Oct 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYTH | Coney Island Acquisition | 3 | CONSTRUCTION | Jan 2011 | Jan 2012 | Jan 2011 | Jan 2012
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYTH | Coney Island Acquisition | 4 | ORIGINAL EQUIP & FURNISHING | Jan 2012 | Jan 2012 | Jan 2012 | Jan 2012
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYTH | Coney Island Acquisition | 5 | SUBSTANTIAL COMPLETION | Jan 2012 | Jan 2012 | Jan 2012 | Jan 2012
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYTH | Coney Island Acquisition | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2012 | Jan 2012 | Jan 2012 | Jan 2012
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYWEST | Coney Island West | 1 | DESIGN | Mar 2018 | Apr 2018 | Apr 2015 | Dec 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYWEST | Coney Island West | 2 | BID AWARD AND REGISTER CONTRCT | Apr 2018 | Apr 2018 | Jan 2023 | Dec 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYWEST | Coney Island West | 3 | CONSTRUCTION | Apr 2018 | May 2018 | Jan 2023 | Dec 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYWEST | Coney Island West | 4 | ORIGINAL EQUIP & FURNISHING | Jun 2018 | Jun 2018 | Jan 2023 | Dec 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYWEST | Coney Island West | 5 | SUBSTANTIAL COMPLETION | Jun 2018 | Jun 2018 | Jan 2023 | Dec 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYWEST | Coney Island West | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2018 | Jun 2018 | Jan 2023 | Jun 2030
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYWIRD | Coney West - Abe Stark Ice Rink Demolition | 1 | DESIGN | Jul 2022 | Jul 2022 | Jul 2022 | Jul 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYWIRD | Coney West - Abe Stark Ice Rink Demolition | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Aug 2022 | Jul 2022 | Aug 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYWIRD | Coney West - Abe Stark Ice Rink Demolition | 3 | CONSTRUCTION | Aug 2022 | Sep 2022 | Aug 2022 | Sep 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYWIRD | Coney West - Abe Stark Ice Rink Demolition | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Sep 2022 | Sep 2022 | Sep 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYWIRD | Coney West - Abe Stark Ice Rink Demolition | 5 | SUBSTANTIAL COMPLETION | Sep 2022 | Oct 2022 | Sep 2022 | Oct 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYWIRD | Coney West - Abe Stark Ice Rink Demolition | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2022 | Jun 2023 | Oct 2022 | Jun 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CORTELYOU | FA - Cortelyou Rd. CR - Flatbush Development Corp. | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2005 | Jun 2007 | Jul 2005 | Jun 2007
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CORTELYOU | FA - Cortelyou Rd. CR - Flatbush Development Corp. | 5 | SUBSTANTIAL COMPLETION | Jul 2007 | Jun 2007 | Jul 2007 | Jun 2007
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CORTELYOU | FA - Cortelyou Rd. CR - Flatbush Development Corp. | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2007 | Jul 2007 | Dec 2007 | Dec 2007
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSHOMEP | New York City Ferry - Homeport | 1 | DESIGN | Jul 2016 | Jul 2016 | Jul 2016 | Jul 2026
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSHOMEP | New York City Ferry - Homeport | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Jul 2026 | Aug 2026
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSHOMEP | New York City Ferry - Homeport | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Aug 2026 | Sep 2026
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSHOMEP | New York City Ferry - Homeport | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Sep 2026 | Sep 2026
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSHOMEP | New York City Ferry - Homeport | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Sep 2026 | Oct 2026
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSHOMEP | New York City Ferry - Homeport | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2016 | Oct 2026 | Oct 2026
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKWSPK | Downtown Brooklyn - Willoughby Square Park | 1 | DESIGN | Jan 2009 | Jan 2010 | Jan 2009 | Jun 2011
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKWSPK | Downtown Brooklyn - Willoughby Square Park | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2010 | Jan 2010 | Jul 2011 | Jun 2012
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKWSPK | Downtown Brooklyn - Willoughby Square Park | 3 | CONSTRUCTION | Jan 2010 | Jan 2011 | Jul 2012 | Jun 2012
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKWSPK | Downtown Brooklyn - Willoughby Square Park | 4 | ORIGINAL EQUIP & FURNISHING | Jan 2011 | Jan 2011 | Jul 2012 | Dec 2013
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKWSPK | Downtown Brooklyn - Willoughby Square Park | 5 | SUBSTANTIAL COMPLETION | Jan 2011 | Jan 2011 | Dec 2013 | Dec 2013
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKWSPK | Downtown Brooklyn - Willoughby Square Park | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2011 | Jan 2011 | Dec 2013 | Jun 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | FREIGHTSP | Freight NYC - Rail Transload | 1 | DESIGN | Jul 2017 | Jul 2017 | Mar 2023 | Apr 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | FREIGHTSP | Freight NYC - Rail Transload | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Aug 2017 | Apr 2023 | Apr 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | FREIGHTSP | Freight NYC - Rail Transload | 3 | CONSTRUCTION | Aug 2017 | Sep 2017 | Apr 2023 | May 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | FREIGHTSP | Freight NYC - Rail Transload | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Sep 2017 | Jun 2023 | Jun 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | FREIGHTSP | Freight NYC - Rail Transload | 5 | SUBSTANTIAL COMPLETION | Sep 2017 | Oct 2017 | Jun 2023 | Jun 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | FREIGHTSP | Freight NYC - Rail Transload | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2017 | Oct 2017 | Jun 2023 | Jun 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GK26W5-05 | DSGN & CONS OF ROW GI IN 26W-005 | 1 | DESIGN | Feb 2015 | Jun 2017 | Feb 2016 | Jun 2018
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GK26W5-05 | DSGN & CONS OF ROW GI IN 26W-005 | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2017 | Jun 2017 | Jun 2018 | Jun 2018
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GK26W5-05 | DSGN & CONS OF ROW GI IN 26W-005 | 3 | CONSTRUCTION | Jun 2017 | Dec 2017 | Jun 2018 | Dec 2018
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GK26W5-05 | DSGN & CONS OF ROW GI IN 26W-005 | 4 | ORIGINAL EQUIP & FURNISHING | Dec 2017 | Dec 2017 | Dec 2018 | Dec 2018
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GK26W5-05 | DSGN & CONS OF ROW GI IN 26W-005 | 5 | SUBSTANTIAL COMPLETION | Dec 2017 | Dec 2017 | Dec 2018 | Dec 2018
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GK26W5-05 | DSGN & CONS OF ROW GI IN 26W-005 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2017 | Jun 2019 | Dec 2018 | Jun 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GKNC15-02 | GI - Green Infrastructure in Newtown Creek Drainage Area | 1 | DESIGN | Apr 2013 | Apr 2013 | Apr 2013 | Apr 2013
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GKNC15-02 | GI - Green Infrastructure in Newtown Creek Drainage Area | 2 | BID AWARD AND REGISTER CONTRCT | Apr 2013 | May 2013 | Apr 2013 | May 2013
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GKNC15-02 | GI - Green Infrastructure in Newtown Creek Drainage Area | 3 | CONSTRUCTION | May 2013 | Jun 2013 | May 2013 | Jun 2013
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GKNC15-02 | GI - Green Infrastructure in Newtown Creek Drainage Area | 4 | ORIGINAL EQUIP & FURNISHING | Jun 2013 | Jun 2013 | Jun 2013 | Jun 2013
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GKNC15-02 | GI - Green Infrastructure in Newtown Creek Drainage Area | 5 | SUBSTANTIAL COMPLETION | Jun 2013 | Jul 2013 | Jun 2013 | Jul 2013
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GKNC15-02 | GI - Green Infrastructure in Newtown Creek Drainage Area | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2013 | Jul 2013 | Jul 2013 | Jun 2026
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GREEN | Green Infrastructure 26W | 1 | DESIGN | Apr 2013 | May 2013 | Apr 2016 | May 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GREEN | Green Infrastructure 26W | 2 | BID AWARD AND REGISTER CONTRCT | May 2013 | May 2013 | May 2016 | May 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GREEN | Green Infrastructure 26W | 3 | CONSTRUCTION | May 2013 | Jul 2013 | May 2016 | Jul 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GREEN | Green Infrastructure 26W | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2013 | Jul 2013 | Jul 2016 | Jul 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GREEN | Green Infrastructure 26W | 5 | SUBSTANTIAL COMPLETION | Jul 2013 | Jul 2013 | Jul 2016 | Jul 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GREEN | Green Infrastructure 26W | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2013 | Aug 2013 | Jul 2016 | Jun 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWKFHAWF | Hamilton Ave - DOT Asphalt Plant (Waterfront) | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWKFHAWF | Hamilton Ave - DOT Asphalt Plant (Waterfront) | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWKFHAWF | Hamilton Ave - DOT Asphalt Plant (Waterfront) | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWKFHAWF | Hamilton Ave - DOT Asphalt Plant (Waterfront) | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWKFHAWF | Hamilton Ave - DOT Asphalt Plant (Waterfront) | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWKFHAWF | Hamilton Ave - DOT Asphalt Plant (Waterfront) | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWKFHAWF | Hamilton Ave - DOT Asphalt Plant (Waterfront) | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2022 | Jan 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWKFHAWF | Hamilton Ave - DOT Asphalt Plant (Waterfront) | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Jan 2025 | Apr 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWKFHAWF | Hamilton Ave - DOT Asphalt Plant (Waterfront) | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Apr 2025 | May 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWKFHAWF | Hamilton Ave - DOT Asphalt Plant (Waterfront) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Jun 2025 | Jun 2026
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-BIOBAT | BioBAT Life Sciences | 1 | DESIGN | Sep 2021 | Sep 2021 | Sep 2021 | Sep 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-BIOBAT | BioBAT Life Sciences | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2021 | Oct 2021 | Sep 2021 | Oct 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-BIOBAT | BioBAT Life Sciences | 3 | CONSTRUCTION | Oct 2021 | Nov 2021 | Oct 2021 | Nov 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-BIOBAT | BioBAT Life Sciences | 4 | ORIGINAL EQUIP & FURNISHING | Nov 2021 | Nov 2021 | Nov 2021 | Nov 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-BIOBAT | BioBAT Life Sciences | 5 | SUBSTANTIAL COMPLETION | Nov 2021 | Dec 2031 | Nov 2021 | Dec 2031
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-BIOBAT | BioBAT Life Sciences | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2031 | Dec 2031 | Dec 2031 | Dec 2031
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MOOREROOF | Moore Street Market Roof Rehabilitation | 1 | DESIGN | Jul 2016 | Jul 2016 | Jul 2016 | Jul 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MOOREROOF | Moore Street Market Roof Rehabilitation | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Jul 2016 | Aug 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MOOREROOF | Moore Street Market Roof Rehabilitation | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Aug 2016 | Sep 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MOOREROOF | Moore Street Market Roof Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Sep 2016 | Sep 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MOOREROOF | Moore Street Market Roof Rehabilitation | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Sep 2016 | Oct 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MOOREROOF | Moore Street Market Roof Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2016 | Oct 2016 | Oct 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MOOREST | Moore Street Market | 1 | DESIGN | Jan 2005 | Jan 2005 | Oct 2006 | Oct 2006
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MOOREST | Moore Street Market | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2003 | Feb 2005 | Feb 2003 | Feb 2005
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MOOREST | Moore Street Market | 3 | CONSTRUCTION | Feb 2005 | Feb 2005 | Oct 2006 | Oct 2009
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MOOREST | Moore Street Market | 4 | ORIGINAL EQUIP & FURNISHING | Feb 2005 | Feb 2005 | Oct 2009 | Jun 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MOOREST | Moore Street Market | 5 | SUBSTANTIAL COMPLETION | Feb 2005 | Feb 2005 | Jul 2020 | Jun 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MOOREST | Moore Street Market | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2005 | Feb 2005 | Jul 2020 | Mar 2026
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDFATLBB | NDF - Atlantic Avenue Broadband Conduit (HWD10105) | 1 | DESIGN | Jan 2022 | Jan 2022 | Jan 2022 | Jan 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDFATLBB | NDF - Atlantic Avenue Broadband Conduit (HWD10105) | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2022 | Feb 2022 | Jan 2022 | Feb 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDFATLBB | NDF - Atlantic Avenue Broadband Conduit (HWD10105) | 3 | CONSTRUCTION | Feb 2022 | Mar 2022 | Feb 2022 | Mar 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDFATLBB | NDF - Atlantic Avenue Broadband Conduit (HWD10105) | 4 | ORIGINAL EQUIP & FURNISHING | Mar 2022 | Mar 2022 | Mar 2022 | Mar 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDFATLBB | NDF - Atlantic Avenue Broadband Conduit (HWD10105) | 5 | SUBSTANTIAL COMPLETION | Mar 2022 | Apr 2022 | Mar 2022 | Apr 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDFATLBB | NDF - Atlantic Avenue Broadband Conduit (HWD10105) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2022 | Apr 2026 | Apr 2022 | Apr 2026
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-BROAD | NDF - ENY IBZ Infrastructure - Broadband | 1 | DESIGN | Jul 2016 | Jul 2016 | Jul 2019 | Jul 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-BROAD | NDF - ENY IBZ Infrastructure - Broadband | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Jul 2019 | Aug 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-BROAD | NDF - ENY IBZ Infrastructure - Broadband | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Aug 2019 | Sep 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-BROAD | NDF - ENY IBZ Infrastructure - Broadband | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Sep 2019 | Sep 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-BROAD | NDF - ENY IBZ Infrastructure - Broadband | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Sep 2019 | Oct 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-BROAD | NDF - ENY IBZ Infrastructure - Broadband | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2016 | Oct 2019 | Oct 2027
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-IBMOD | NDF - ENY Industiral Buiding Modernization and Activation | 1 | DESIGN | Jul 2016 | Jul 2016 | Mar 2019 | Apr 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-IBMOD | NDF - ENY Industiral Buiding Modernization and Activation | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Apr 2019 | Apr 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-IBMOD | NDF - ENY Industiral Buiding Modernization and Activation | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Apr 2019 | May 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-IBMOD | NDF - ENY Industiral Buiding Modernization and Activation | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Jun 2023 | Jun 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-IBMOD | NDF - ENY Industiral Buiding Modernization and Activation | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Jun 2023 | Jun 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-IBMOD | NDF - ENY Industiral Buiding Modernization and Activation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2016 | Jun 2023 | Jun 2026
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NOSTRAND | FA - Nostrand Avenue Merchants Assoc. (Flatbush Gateway) | 1 | DESIGN | Jan 2005 | Jan 2005 | Jan 2005 | Jan 2005
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NOSTRAND | FA - Nostrand Avenue Merchants Assoc. (Flatbush Gateway) | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2005 | Feb 2005 | Jan 2005 | Feb 2005
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NOSTRAND | FA - Nostrand Avenue Merchants Assoc. (Flatbush Gateway) | 3 | CONSTRUCTION | Feb 2005 | Jun 2007 | Feb 2005 | Jun 2007
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NOSTRAND | FA - Nostrand Avenue Merchants Assoc. (Flatbush Gateway) | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2007 | Jun 2007 | Jul 2007 | Jun 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NOSTRAND | FA - Nostrand Avenue Merchants Assoc. (Flatbush Gateway) | 5 | SUBSTANTIAL COMPLETION | Jul 2007 | Jun 2007 | Jul 2019 | Jun 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NOSTRAND | FA - Nostrand Avenue Merchants Assoc. (Flatbush Gateway) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2007 | Jul 2007 | Jul 2019 | Jun 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFHP2 | NYC Ferry Homeport 2 | 1 | DESIGN | Jul 2019 | Jul 2019 | Jul 2019 | Jul 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFHP2 | NYC Ferry Homeport 2 | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jul 2019 | Aug 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFHP2 | NYC Ferry Homeport 2 | 3 | CONSTRUCTION | Aug 2019 | Sep 2019 | Aug 2019 | Sep 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFHP2 | NYC Ferry Homeport 2 | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Sep 2019 | Sep 2023 | Sep 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFHP2 | NYC Ferry Homeport 2 | 5 | SUBSTANTIAL COMPLETION | Sep 2019 | Oct 2021 | Sep 2023 | Oct 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFHP2 | NYC Ferry Homeport 2 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2021 | Oct 2021 | Oct 2025 | Oct 2030
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | OFFSHRWND | Offshore Wind - Development and Manufacturing | 1 | DESIGN | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | OFFSHRWND | Offshore Wind - Development and Manufacturing | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Aug 2021 | Jul 2021 | Aug 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | OFFSHRWND | Offshore Wind - Development and Manufacturing | 3 | CONSTRUCTION | Aug 2021 | Sep 2021 | Aug 2021 | Sep 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | OFFSHRWND | Offshore Wind - Development and Manufacturing | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Sep 2021 | Sep 2021 | Sep 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | OFFSHRWND | Offshore Wind - Development and Manufacturing | 5 | SUBSTANTIAL COMPLETION | Sep 2021 | Oct 2025 | Sep 2021 | Oct 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | OFFSHRWND | Offshore Wind - Development and Manufacturing | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2025 | Oct 2025 | Oct 2025 | Jun 2028
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2BUSHDE | Bushwick Inlet Park CitiStorage Demo | 1 | DESIGN | Jul 2027 | Jul 2027 | Jul 2022 | Jul 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2BUSHDE | Bushwick Inlet Park CitiStorage Demo | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2027 | Aug 2027 | Jul 2023 | Aug 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2BUSHDE | Bushwick Inlet Park CitiStorage Demo | 3 | CONSTRUCTION | Aug 2027 | Sep 2027 | Aug 2023 | Sep 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2BUSHDE | Bushwick Inlet Park CitiStorage Demo | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2027 | Sep 2027 | Sep 2023 | Sep 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2BUSHDE | Bushwick Inlet Park CitiStorage Demo | 5 | SUBSTANTIAL COMPLETION | Sep 2027 | Oct 2027 | Sep 2023 | Oct 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2BUSHDE | Bushwick Inlet Park CitiStorage Demo | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2027 | Jun 2028 | Oct 2023 | Jun 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB07 | GPWB - Box Street and Newtown Barge Parks | 1 | DEVELOP SCOPE | Jul 2008 | Sep 2008 | Oct 2007 | Oct 2007
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB07 | GPWB - Box Street and Newtown Barge Parks | 2 | DESIGN | Sep 2008 | Dec 2008 | Oct 2007 | Nov 2007
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB07 | GPWB - Box Street and Newtown Barge Parks | 3 | BID/ REGISTER CONTRACT | Dec 2008 | Mar 2009 | Nov 2007 | Dec 2007
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB07 | GPWB - Box Street and Newtown Barge Parks | 4 | CONSTRUCTION | Mar 2009 | Mar 2010 | Dec 2007 | Dec 2007
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB07 | GPWB - Box Street and Newtown Barge Parks | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2010 | Mar 2011 | Dec 2007 | Jan 2008
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB07 | GPWB - Box Street and Newtown Barge Parks | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2010 | Mar 2011 | Jan 2008 | Jan 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB08 | GPWB - 65 Commercial St Soccer Pk-MTA Reloc. & Park Develop. | 1 | DEVELOP SCOPE | Jul 2008 | Sep 2008 | Jul 2008 | Jul 2008
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB08 | GPWB - 65 Commercial St Soccer Pk-MTA Reloc. & Park Develop. | 2 | DESIGN | Sep 2008 | Dec 2008 | Jul 2008 | Aug 2008
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB08 | GPWB - 65 Commercial St Soccer Pk-MTA Reloc. & Park Develop. | 3 | BID/ REGISTER CONTRACT | Dec 2008 | Mar 2009 | Aug 2008 | Sep 2008
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB08 | GPWB - 65 Commercial St Soccer Pk-MTA Reloc. & Park Develop. | 4 | CONSTRUCTION | Mar 2009 | Mar 2010 | Sep 2008 | Sep 2008
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB08 | GPWB - 65 Commercial St Soccer Pk-MTA Reloc. & Park Develop. | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2010 | Mar 2011 | Sep 2008 | Oct 2008
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB08 | GPWB - 65 Commercial St Soccer Pk-MTA Reloc. & Park Develop. | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2010 | Mar 2011 | Oct 2008 | Oct 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWBOX | GPWB - Box Street Park | 1 | DESIGN | Jul 2016 | Jul 2016 | Jul 2016 | Jul 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWBOX | GPWB - Box Street Park | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Jul 2016 | Aug 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWBOX | GPWB - Box Street Park | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Aug 2016 | Sep 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWBOX | GPWB - Box Street Park | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Sep 2016 | Sep 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWBOX | GPWB - Box Street Park | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Sep 2016 | Oct 2018
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWBOX | GPWB - Box Street Park | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2016 | Oct 2018 | Oct 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWNB | GPWB - Newtown Barge Park | 1 | DESIGN | Jul 2016 | Jul 2016 | Jul 2016 | Jul 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWNB | GPWB - Newtown Barge Park | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Jul 2016 | Aug 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWNB | GPWB - Newtown Barge Park | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Aug 2016 | Sep 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWNB | GPWB - Newtown Barge Park | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Sep 2016 | Sep 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWNB | GPWB - Newtown Barge Park | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Sep 2016 | Oct 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWNB | GPWB - Newtown Barge Park | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2016 | Oct 2016 | Jun 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PARACHUT2 | Coney Island - Parachute Jump Lighting 2 | 4 | ORIGINAL EQUIP & FURNISHING | Jan 2011 | Jan 2011 | Jul 2017 | Jun 2017
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PARACHUT2 | Coney Island - Parachute Jump Lighting 2 | 5 | SUBSTANTIAL COMPLETION | Jan 2011 | Jan 2011 | Jul 2017 | Jun 2017
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PARACHUT2 | Coney Island - Parachute Jump Lighting 2 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2011 | Jan 2011 | Jul 2017 | Jul 2017
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER12PH2 | Brooklyn Cruise Terminal Pier 12 Substructure Rehab phase2 | 1 | DESIGN | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER12PH2 | Brooklyn Cruise Terminal Pier 12 Substructure Rehab phase2 | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Aug 2021 | Jul 2021 | Aug 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER12PH2 | Brooklyn Cruise Terminal Pier 12 Substructure Rehab phase2 | 3 | CONSTRUCTION | Aug 2021 | Sep 2021 | Aug 2021 | Sep 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER12PH2 | Brooklyn Cruise Terminal Pier 12 Substructure Rehab phase2 | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Sep 2021 | Sep 2021 | Sep 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER12PH2 | Brooklyn Cruise Terminal Pier 12 Substructure Rehab phase2 | 5 | SUBSTANTIAL COMPLETION | Sep 2021 | Oct 2021 | Sep 2021 | Oct 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER12PH2 | Brooklyn Cruise Terminal Pier 12 Substructure Rehab phase2 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2021 | Oct 2025 | Oct 2021 | Oct 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV230-ACF | FA - WCS NEW YORK AQUARIUM - Animal Care Facility | 2 | PRELIMINARY DESIGN | Mar 2012 | Jul 2012 | Oct 2009 | Jan 2010
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV230-ACF | FA - WCS NEW YORK AQUARIUM - Animal Care Facility | 3 | FINAL DESIGN | Jul 2012 | Jan 2013 | Jan 2010 | Jul 2010
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV230-ACF | FA - WCS NEW YORK AQUARIUM - Animal Care Facility | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2013 | Apr 2013 | Jul 2010 | Oct 2010
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV230-ACF | FA - WCS NEW YORK AQUARIUM - Animal Care Facility | 5 | CONSTRUCTION TO 25% | Apr 2013 | Aug 2013 | Oct 2010 | Feb 2011
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV230-ACF | FA - WCS NEW YORK AQUARIUM - Animal Care Facility | 6 | CONSTRUCTION TO 50% | Aug 2013 | Dec 2013 | Feb 2011 | Jun 2011
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV230-ACF | FA - WCS NEW YORK AQUARIUM - Animal Care Facility | 7 | CONSTRUCTION TO 75% | Dec 2013 | Apr 2014 | Jun 2011 | Oct 2011
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV230-ACF | FA - WCS NEW YORK AQUARIUM - Animal Care Facility | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2014 | Jul 2014 | Oct 2011 | Jan 2012
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV230-ACF | FA - WCS NEW YORK AQUARIUM - Animal Care Facility | 9 | SUBSTANTIAL COMPLETION | Jul 2014 | Sep 2014 | Jan 2012 | Mar 2012
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV230-ACF | FA - WCS NEW YORK AQUARIUM - Animal Care Facility | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2014 | Oct 2014 | Mar 2012 | Apr 2012
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV230-ACF | FA - WCS NEW YORK AQUARIUM - Animal Care Facility | 11 | DESIGN | Sep 2014 | Oct 2014 | Apr 2012 | May 2012
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV230-ACF | FA - WCS NEW YORK AQUARIUM - Animal Care Facility | 12 | BID AWARD AND REGISTER CONTRCT | Sep 2014 | Oct 2014 | May 2012 | May 2012
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV230-ACF | FA - WCS NEW YORK AQUARIUM - Animal Care Facility | 13 | CONSTRUCTION | Sep 2014 | Oct 2014 | May 2012 | Jun 2017
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV230-ACF | FA - WCS NEW YORK AQUARIUM - Animal Care Facility | 14 | ORIGINAL EQUIP & FURNISHING | Sep 2014 | Oct 2014 | Jul 2017 | Jun 2017
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV230-ACF | FA - WCS NEW YORK AQUARIUM - Animal Care Facility | 15 | SUBSTANTIAL COMPLETION | Sep 2014 | Oct 2014 | Jul 2017 | Jun 2017
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV230-ACF | FA - WCS NEW YORK AQUARIUM - Animal Care Facility | 16 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2014 | Oct 2014 | Jul 2017 | Jul 2017
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV230-SHA | FA - WCS - New York Aquarium | 1 | DESIGN | Jan 2005 | Jan 2005 | Jan 2005 | Dec 2006
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV230-SHA | FA - WCS - New York Aquarium | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2005 | Feb 2007 | Dec 2006 | Dec 2006
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV230-SHA | FA - WCS - New York Aquarium | 3 | CONSTRUCTION | Feb 2007 | Feb 2007 | Jan 2007 | Jan 2009
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV230-SHA | FA - WCS - New York Aquarium | 4 | ORIGINAL EQUIP & FURNISHING | Feb 2007 | Feb 2007 | Jan 2009 | Jan 2009
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV230-SHA | FA - WCS - New York Aquarium | 5 | SUBSTANTIAL COMPLETION | Feb 2007 | Feb 2007 | Jan 2009 | Feb 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV230-SHA | FA - WCS - New York Aquarium | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2007 | Feb 2007 | Feb 2016 | Aug 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV264CINE | BAM - BAM South Site Theaters | 1 | DESIGN | Dec 2014 | Sep 2016 | Dec 2014 | Sep 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV264CINE | BAM - BAM South Site Theaters | 2 | BID AWARD AND REGISTER CONTRCT | Oct 2016 | Sep 2016 | Oct 2016 | Sep 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV264CINE | BAM - BAM South Site Theaters | 3 | CONSTRUCTION | Oct 2016 | Sep 2018 | Oct 2016 | Sep 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV264CINE | BAM - BAM South Site Theaters | 4 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Sep 2018 | Oct 2020 | Sep 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV264CINE | BAM - BAM South Site Theaters | 5 | SUBSTANTIAL COMPLETION | Oct 2018 | Sep 2018 | Oct 2020 | Sep 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV264CINE | BAM - BAM South Site Theaters | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2018 | Oct 2018 | Oct 2020 | Jun 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467SOST | DBCD South Site Cultural Condo Fitout | 1 | CONSTRUCTION | Sep 2013 | Sep 2014 | Jul 2013 | Jul 2013
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467SOST | DBCD South Site Cultural Condo Fitout | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2014 | Sep 2015 | Jul 2013 | Aug 2013
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467SOST | DBCD South Site Cultural Condo Fitout | 3 | CONSTRUCTION | Sep 2014 | Sep 2015 | Aug 2013 | Sep 2013
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467SOST | DBCD South Site Cultural Condo Fitout | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2014 | Sep 2015 | Sep 2013 | Sep 2013
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467SOST | DBCD South Site Cultural Condo Fitout | 5 | SUBSTANTIAL COMPLETION | Sep 2014 | Sep 2015 | Sep 2013 | Oct 2013
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467SOST | DBCD South Site Cultural Condo Fitout | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2014 | Sep 2015 | Oct 2013 | Oct 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467STFO | 651 Arts South Site Studios Fitout | 1 | DESIGN | Jun 2015 | Jul 2015 | Jun 2015 | Jul 2015
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467STFO | 651 Arts South Site Studios Fitout | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Aug 2015 | Jul 2015 | Aug 2015
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467STFO | 651 Arts South Site Studios Fitout | 3 | CONSTRUCTION | Aug 2015 | Sep 2015 | Aug 2015 | Sep 2015
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467STFO | 651 Arts South Site Studios Fitout | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2015 | Sep 2015 | Sep 2015 | Sep 2015
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467STFO | 651 Arts South Site Studios Fitout | 5 | SUBSTANTIAL COMPLETION | Sep 2015 | Oct 2015 | Sep 2015 | Oct 2015
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467STFO | 651 Arts South Site Studios Fitout | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2015 | Oct 2015 | Oct 2015 | Oct 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | REDHOOK | Red Hook Library | 1 | DESIGN | Jan 2016 | Jan 2016 | Jan 2016 | Jan 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | REDHOOK | Red Hook Library | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2016 | Jun 2016 | Jan 2016 | Jun 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | REDHOOK | Red Hook Library | 3 | CONSTRUCTION | Jul 2016 | Jun 2017 | Jul 2016 | Jun 2017
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | REDHOOK | Red Hook Library | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2017 | Jun 2021 | Jul 2017 | Jun 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | REDHOOK | Red Hook Library | 5 | SUBSTANTIAL COMPLETION | Jul 2021 | Jun 2021 | Jul 2023 | Jun 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | REDHOOK | Red Hook Library | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Jul 2021 | Jul 2023 | Jul 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | RS-CIC | Raise Shoreline - Coney Island Creek | 1 | DESIGN | Aug 2019 | Sep 2019 | Aug 2019 | Sep 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | RS-CIC | Raise Shoreline - Coney Island Creek | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Oct 2019 | Sep 2019 | Oct 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | RS-CIC | Raise Shoreline - Coney Island Creek | 3 | CONSTRUCTION | Oct 2019 | Nov 2019 | Oct 2019 | Nov 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | RS-CIC | Raise Shoreline - Coney Island Creek | 4 | ORIGINAL EQUIP & FURNISHING | Nov 2019 | Nov 2019 | Nov 2019 | Nov 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | RS-CIC | Raise Shoreline - Coney Island Creek | 5 | SUBSTANTIAL COMPLETION | Nov 2019 | Dec 2019 | Nov 2019 | Dec 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | RS-CIC | Raise Shoreline - Coney Island Creek | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Dec 2020 | Dec 2019 | Jun 2030
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND2605 | CIH: DESIGN & CONSTRUCTION MANAGEMENT FOR HOSPITAL CAMPUS | 1 | DESIGN | Jul 2017 | Jul 2017 | Mar 2018 | Apr 2018
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND2605 | CIH: DESIGN & CONSTRUCTION MANAGEMENT FOR HOSPITAL CAMPUS | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Aug 2017 | Apr 2018 | Apr 2018
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND2605 | CIH: DESIGN & CONSTRUCTION MANAGEMENT FOR HOSPITAL CAMPUS | 3 | CONSTRUCTION | Aug 2017 | Sep 2017 | Apr 2018 | May 2018
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND2605 | CIH: DESIGN & CONSTRUCTION MANAGEMENT FOR HOSPITAL CAMPUS | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Sep 2017 | Jun 2018 | Jun 2018
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND2605 | CIH: DESIGN & CONSTRUCTION MANAGEMENT FOR HOSPITAL CAMPUS | 5 | SUBSTANTIAL COMPLETION | Sep 2017 | Oct 2017 | Jun 2018 | Jun 2018
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND2605 | CIH: DESIGN & CONSTRUCTION MANAGEMENT FOR HOSPITAL CAMPUS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2017 | Oct 2017 | Jun 2018 | Jun 2027
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB3416 | Sandy - BNYDC - PW 3416 - Berth 6 Concrete Slab | 1 | DESIGN | Jan 2019 | Jul 2019 | Jan 2019 | Jul 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB3416 | Sandy - BNYDC - PW 3416 - Berth 6 Concrete Slab | 2 | CONSTRUCTION | Jul 2019 | Nov 2020 | Jan 2019 | Jul 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB3416 | Sandy - BNYDC - PW 3416 - Berth 6 Concrete Slab | 3 | CONSTRUCTION | Nov 2020 | Jan 2021 | Jul 2023 | Nov 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB3416 | Sandy - BNYDC - PW 3416 - Berth 6 Concrete Slab | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2021 | Jan 2021 | Jul 2023 | Nov 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB3416 | Sandy - BNYDC - PW 3416 - Berth 6 Concrete Slab | 5 | SUBSTANTIAL COMPLETION | Jan 2021 | Jan 2021 | Nov 2023 | Jan 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB3416 | Sandy - BNYDC - PW 3416 - Berth 6 Concrete Slab | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2021 | Jan 2021 | Jan 2024 | Jan 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4123 | Sandy - BNYDC - PW 4123 Rehabilitation | 1 | DESIGN | May 2021 | Jun 2021 | May 2021 | Jun 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4123 | Sandy - BNYDC - PW 4123 Rehabilitation | 2 | CONSTRUCTION | Jun 2021 | Feb 2023 | May 2021 | Jun 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4123 | Sandy - BNYDC - PW 4123 Rehabilitation | 3 | CONSTRUCTION | Feb 2023 | Apr 2023 | Jun 2021 | Dec 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4123 | Sandy - BNYDC - PW 4123 Rehabilitation | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2023 | Apr 2023 | Jun 2021 | Dec 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4123 | Sandy - BNYDC - PW 4123 Rehabilitation | 5 | SUBSTANTIAL COMPLETION | Apr 2023 | Apr 2023 | Dec 2023 | Jun 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4123 | Sandy - BNYDC - PW 4123 Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2023 | Apr 2023 | Jun 2024 | Jun 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4269 | BNYDC Sandy - PW 4269 - B270 Boilers | 1 | DESIGN | Jan 2023 | Mar 2023 | Jun 2022 | Mar 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4269 | BNYDC Sandy - PW 4269 - B270 Boilers | 2 | CONSTRUCTION | Mar 2023 | Apr 2024 | Jun 2022 | Mar 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4269 | BNYDC Sandy - PW 4269 - B270 Boilers | 3 | SUBSTANTIAL COMPLETION | Apr 2024 | Jun 2024 | Mar 2023 | Apr 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4269 | BNYDC Sandy - PW 4269 - B270 Boilers | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2024 | Jun 2024 | Mar 2023 | Apr 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4269 | BNYDC Sandy - PW 4269 - B270 Boilers | 5 | SUBSTANTIAL COMPLETION | Jun 2024 | Jun 2024 | Apr 2025 | Jun 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4269 | BNYDC Sandy - PW 4269 - B270 Boilers | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2024 | Jun 2024 | Jun 2025 | Jun 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4270 | Sandy - BNYDC - PW 4270 - BNYDC SITE-WIDE CONDUIT - PAAP | 1 | DESIGN | Mar 2019 | Jul 2019 | Mar 2019 | Jul 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4270 | Sandy - BNYDC - PW 4270 - BNYDC SITE-WIDE CONDUIT - PAAP | 2 | CONSTRUCTION | Jul 2019 | Apr 2020 | Mar 2019 | Jul 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4270 | Sandy - BNYDC - PW 4270 - BNYDC SITE-WIDE CONDUIT - PAAP | 3 | SUBSTANTIAL COMPLETION | Apr 2020 | Jun 2020 | Jul 2020 | Aug 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4270 | Sandy - BNYDC - PW 4270 - BNYDC SITE-WIDE CONDUIT - PAAP | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2020 | Jun 2020 | Jul 2020 | Aug 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4270 | Sandy - BNYDC - PW 4270 - BNYDC SITE-WIDE CONDUIT - PAAP | 5 | SUBSTANTIAL COMPLETION | Jun 2020 | Jun 2020 | Aug 2024 | Nov 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4270 | Sandy - BNYDC - PW 4270 - BNYDC SITE-WIDE CONDUIT - PAAP | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2020 | Jun 2020 | Nov 2024 | Nov 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4271 | Sandy - BNYDC - PW 4271 - Substations No. 292 and No. 542 | 1 | DESIGN | Mar 2019 | Jul 2019 | Mar 2019 | Jul 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4271 | Sandy - BNYDC - PW 4271 - Substations No. 292 and No. 542 | 2 | CONSTRUCTION | Jul 2019 | Mar 2020 | Mar 2019 | Jul 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4271 | Sandy - BNYDC - PW 4271 - Substations No. 292 and No. 542 | 3 | SUBSTANTIAL COMPLETION | Apr 2020 | Jun 2020 | Jul 2020 | Apr 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4271 | Sandy - BNYDC - PW 4271 - Substations No. 292 and No. 542 | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2020 | Jun 2020 | Jul 2020 | Apr 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4271 | Sandy - BNYDC - PW 4271 - Substations No. 292 and No. 542 | 5 | SUBSTANTIAL COMPLETION | Jun 2020 | Jun 2020 | Apr 2022 | Jun 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4271 | Sandy - BNYDC - PW 4271 - Substations No. 292 and No. 542 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2020 | Jun 2020 | Jul 2022 | Jul 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4273 | Sandy - BNYDC - PW 4273 - Steam Back-Up Plant - Bldg #41A | 1 | DESIGN | Mar 2019 | Jul 2019 | Mar 2019 | Jul 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4273 | Sandy - BNYDC - PW 4273 - Steam Back-Up Plant - Bldg #41A | 2 | CONSTRUCTION | Jul 2019 | Mar 2020 | Mar 2019 | Jul 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4273 | Sandy - BNYDC - PW 4273 - Steam Back-Up Plant - Bldg #41A | 3 | SUBSTANTIAL COMPLETION | Apr 2020 | Jun 2020 | Jul 2020 | Aug 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4273 | Sandy - BNYDC - PW 4273 - Steam Back-Up Plant - Bldg #41A | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2020 | Jun 2020 | Jul 2020 | Aug 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4273 | Sandy - BNYDC - PW 4273 - Steam Back-Up Plant - Bldg #41A | 5 | SUBSTANTIAL COMPLETION | Jun 2020 | Jun 2020 | Aug 2024 | Nov 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4273 | Sandy - BNYDC - PW 4273 - Steam Back-Up Plant - Bldg #41A | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2020 | Jun 2020 | Nov 2024 | Nov 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4274 | Sandy - BNYDC - PW 4274 - Dry Dock 1 | 1 | DESIGN | Jun 2019 | Jul 2019 | Jun 2019 | Jul 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4274 | Sandy - BNYDC - PW 4274 - Dry Dock 1 | 2 | CONSTRUCTION | Jul 2019 | Apr 2020 | Jun 2019 | Jul 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4274 | Sandy - BNYDC - PW 4274 - Dry Dock 1 | 3 | SUBSTANTIAL COMPLETION | Apr 2020 | Jun 2020 | Jul 2020 | Sep 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4274 | Sandy - BNYDC - PW 4274 - Dry Dock 1 | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2020 | Jun 2020 | Jul 2020 | Sep 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4274 | Sandy - BNYDC - PW 4274 - Dry Dock 1 | 5 | SUBSTANTIAL COMPLETION | Jun 2020 | Jun 2020 | Sep 2024 | Nov 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4274 | Sandy - BNYDC - PW 4274 - Dry Dock 1 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2020 | Jun 2020 | Nov 2024 | Nov 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4275 | Sandy - BNYDC - PW 4275 - SUB STATION G BUILDING 386 | 1 | DESIGN | Mar 2019 | Jul 2019 | Mar 2019 | Jul 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4275 | Sandy - BNYDC - PW 4275 - SUB STATION G BUILDING 386 | 2 | CONSTRUCTION | Jul 2019 | Mar 2020 | Mar 2019 | Jul 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4275 | Sandy - BNYDC - PW 4275 - SUB STATION G BUILDING 386 | 3 | SUBSTANTIAL COMPLETION | Apr 2020 | Jun 2020 | Jul 2020 | Aug 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4275 | Sandy - BNYDC - PW 4275 - SUB STATION G BUILDING 386 | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2020 | Jun 2020 | Jul 2020 | Aug 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4275 | Sandy - BNYDC - PW 4275 - SUB STATION G BUILDING 386 | 5 | SUBSTANTIAL COMPLETION | Jun 2020 | Jun 2020 | Aug 2024 | Nov 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4275 | Sandy - BNYDC - PW 4275 - SUB STATION G BUILDING 386 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2020 | Jun 2020 | Nov 2024 | Nov 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4307 | Sandy - BNYDC - PW 4307 Substation B | 1 | DESIGN | Mar 2019 | Jul 2019 | Mar 2019 | Jul 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4307 | Sandy - BNYDC - PW 4307 Substation B | 2 | CONSTRUCTION | Jul 2019 | Mar 2020 | Mar 2019 | Jul 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4307 | Sandy - BNYDC - PW 4307 Substation B | 3 | SUBSTANTIAL COMPLETION | Apr 2020 | Jun 2020 | Jul 2020 | Apr 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4307 | Sandy - BNYDC - PW 4307 Substation B | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2020 | Jun 2020 | Jul 2020 | Apr 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4307 | Sandy - BNYDC - PW 4307 Substation B | 5 | SUBSTANTIAL COMPLETION | Jun 2020 | Jun 2020 | Apr 2022 | Jun 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4307 | Sandy - BNYDC - PW 4307 Substation B | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2020 | Jun 2020 | Jul 2022 | Jul 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4388 | Sandy - BNYDC - PW 4388 - Boiler Replacement | 1 | DESIGN | Mar 2019 | Jul 2019 | Mar 2019 | Jul 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4388 | Sandy - BNYDC - PW 4388 - Boiler Replacement | 2 | CONSTRUCTION | Jul 2019 | Mar 2020 | Mar 2019 | Jul 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4388 | Sandy - BNYDC - PW 4388 - Boiler Replacement | 3 | SUBSTANTIAL COMPLETION | Apr 2020 | Jun 2020 | Jul 2020 | Oct 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4388 | Sandy - BNYDC - PW 4388 - Boiler Replacement | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2020 | Jun 2020 | Jul 2020 | Oct 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4388 | Sandy - BNYDC - PW 4388 - Boiler Replacement | 5 | SUBSTANTIAL COMPLETION | Jun 2020 | Jun 2020 | Oct 2024 | Jan 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4388 | Sandy - BNYDC - PW 4388 - Boiler Replacement | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2020 | Jun 2020 | Jan 2025 | Jan 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4582 | Sandy - BNYDC - PW 4582 - BERTH 9,9A | 1 | DESIGN | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4582 | Sandy - BNYDC - PW 4582 - BERTH 9,9A | 2 | CONSTRUCTION | Jun 2019 | Mar 2020 | Feb 2019 | Jun 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4582 | Sandy - BNYDC - PW 4582 - BERTH 9,9A | 3 | SUBSTANTIAL COMPLETION | Mar 2020 | Jun 2020 | Jun 2021 | Mar 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4582 | Sandy - BNYDC - PW 4582 - BERTH 9,9A | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2020 | Jun 2020 | Jun 2021 | Mar 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4582 | Sandy - BNYDC - PW 4582 - BERTH 9,9A | 5 | SUBSTANTIAL COMPLETION | Jun 2020 | Jun 2020 | Apr 2022 | Jun 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4582 | Sandy - BNYDC - PW 4582 - BERTH 9,9A | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2020 | Jun 2020 | Jul 2022 | Jul 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4583 | Sandy - BNYDC - PW 4583 - BERTH 10 & 10A | 1 | DESIGN | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4583 | Sandy - BNYDC - PW 4583 - BERTH 10 & 10A | 2 | CONSTRUCTION | Jun 2019 | Apr 2020 | Feb 2019 | Jun 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4583 | Sandy - BNYDC - PW 4583 - BERTH 10 & 10A | 3 | SUBSTANTIAL COMPLETION | Apr 2020 | Jun 2020 | Jun 2020 | Apr 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4583 | Sandy - BNYDC - PW 4583 - BERTH 10 & 10A | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2020 | Jun 2020 | Jun 2020 | Apr 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4583 | Sandy - BNYDC - PW 4583 - BERTH 10 & 10A | 5 | SUBSTANTIAL COMPLETION | Jun 2020 | Jun 2020 | Apr 2022 | Jun 2022
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4583 | Sandy - BNYDC - PW 4583 - BERTH 10 & 10A | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2020 | Jun 2020 | Jul 2024 | Jul 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBCT | EDC - Hurricane Sandy - BCT Repairs | 1 | DESIGN | Jun 2015 | Jul 2015 | Jun 2018 | Jul 2018
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBCT | EDC - Hurricane Sandy - BCT Repairs | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Aug 2015 | Jul 2018 | Aug 2018
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBCT | EDC - Hurricane Sandy - BCT Repairs | 3 | CONSTRUCTION | Aug 2015 | Sep 2015 | Aug 2018 | Sep 2018
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBCT | EDC - Hurricane Sandy - BCT Repairs | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2015 | Sep 2015 | Sep 2018 | Sep 2018
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBCT | EDC - Hurricane Sandy - BCT Repairs | 5 | SUBSTANTIAL COMPLETION | Sep 2015 | Oct 2015 | Sep 2018 | Oct 2018
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBCT | EDC - Hurricane Sandy - BCT Repairs | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2015 | Oct 2015 | Oct 2018 | Oct 2031
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYAM | Sandy - BNYDC Hurricane Sandy Asset Management Repairs | 1 | DESIGN | Jun 2017 | Jul 2017 | Jun 2017 | Jul 2017
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYAM | Sandy - BNYDC Hurricane Sandy Asset Management Repairs | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Aug 2017 | Jul 2017 | Aug 2017
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYAM | Sandy - BNYDC Hurricane Sandy Asset Management Repairs | 3 | CONSTRUCTION | Aug 2017 | Sep 2017 | Aug 2017 | Sep 2017
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYAM | Sandy - BNYDC Hurricane Sandy Asset Management Repairs | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Sep 2017 | Sep 2017 | Sep 2017
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYAM | Sandy - BNYDC Hurricane Sandy Asset Management Repairs | 5 | SUBSTANTIAL COMPLETION | Sep 2017 | Oct 2017 | Sep 2017 | Oct 2017
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYAM | Sandy - BNYDC Hurricane Sandy Asset Management Repairs | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2017 | Oct 2021 | Oct 2017 | Sep 2027
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYEC | Sandy - BNYDC Hurricane Sandy Electrical Repairs | 1 | DESIGN | Jan 2016 | Jan 2016 | Jan 2016 | Jan 2018
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYEC | Sandy - BNYDC Hurricane Sandy Electrical Repairs | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2016 | Jun 2016 | Jan 2018 | Jul 2018
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYEC | Sandy - BNYDC Hurricane Sandy Electrical Repairs | 3 | CONSTRUCTION | Jul 2016 | Jun 2017 | Jul 2018 | Jul 2019
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYEC | Sandy - BNYDC Hurricane Sandy Electrical Repairs | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2017 | Jun 2020 | Jul 2019 | Jun 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYEC | Sandy - BNYDC Hurricane Sandy Electrical Repairs | 5 | SUBSTANTIAL COMPLETION | Jul 2020 | Jun 2020 | Jul 2024 | Jun 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYEC | Sandy - BNYDC Hurricane Sandy Electrical Repairs | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Jul 2020 | Jul 2024 | Jul 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYWF | Sandy - BNYDC Hurricane Sandy Waterfront Repair | 1 | DESIGN | Jan 2016 | Jan 2016 | Jan 2016 | Jan 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYWF | Sandy - BNYDC Hurricane Sandy Waterfront Repair | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2016 | Jun 2016 | Jan 2016 | Jun 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYWF | Sandy - BNYDC Hurricane Sandy Waterfront Repair | 3 | CONSTRUCTION | Jul 2016 | Jun 2017 | Jul 2016 | Jun 2017
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYWF | Sandy - BNYDC Hurricane Sandy Waterfront Repair | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2017 | Jun 2020 | Jul 2017 | Jun 2027
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYWF | Sandy - BNYDC Hurricane Sandy Waterfront Repair | 5 | SUBSTANTIAL COMPLETION | Jul 2020 | Jun 2020 | Jun 2027 | Jun 2027
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYWF | Sandy - BNYDC Hurricane Sandy Waterfront Repair | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Jul 2020 | Jun 2027 | Jul 2027
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD9 | HARBOR CHARLIE | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Feb 2016 | Mar 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD9 | HARBOR CHARLIE | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Mar 2016 | Mar 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD9 | HARBOR CHARLIE | 3 | FINAL DESIGN | Jan 2017 | May 2017 | Mar 2016 | May 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD9 | HARBOR CHARLIE | 4 | BID AWARD AND REGISTER CONTRCT | May 2017 | Nov 2017 | May 2016 | May 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD9 | HARBOR CHARLIE | 5 | CONSTRUCTION TO 25% | Nov 2017 | Mar 2018 | May 2016 | May 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD9 | HARBOR CHARLIE | 6 | CONSTRUCTION TO 50% | Mar 2018 | Jul 2018 | May 2016 | Jun 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD9 | HARBOR CHARLIE | 7 | CONSTRUCTION TO 75% | Jul 2018 | Nov 2018 | May 2016 | Jun 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD9 | HARBOR CHARLIE | 8 | ORIGINAL EQUIP & FURNISHING | Nov 2018 | Feb 2019 | May 2016 | Jun 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD9 | HARBOR CHARLIE | 9 | SUBSTANTIAL COMPLETION | Feb 2019 | Apr 2019 | May 2016 | Jun 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD9 | HARBOR CHARLIE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2019 | May 2019 | May 2016 | Jun 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG3BAT | FEMA 428 Projects - Group 3 - Brooklyn Army Terminal BAT | 1 | DESIGN | Jul 2016 | Jul 2016 | Jul 2016 | Jul 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG3BAT | FEMA 428 Projects - Group 3 - Brooklyn Army Terminal BAT | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Jul 2021 | Aug 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG3BAT | FEMA 428 Projects - Group 3 - Brooklyn Army Terminal BAT | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Aug 2021 | Sep 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG3BAT | FEMA 428 Projects - Group 3 - Brooklyn Army Terminal BAT | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Sep 2021 | Sep 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG3BAT | FEMA 428 Projects - Group 3 - Brooklyn Army Terminal BAT | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Sep 2021 | Oct 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG3BAT | FEMA 428 Projects - Group 3 - Brooklyn Army Terminal BAT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2016 | Oct 2021 | Oct 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRBCT | FA Resiliency - BCT | 1 | DESIGN | Jul 2016 | Jul 2016 | Jul 2016 | Jul 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRBCT | FA Resiliency - BCT | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Jul 2016 | Aug 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRBCT | FA Resiliency - BCT | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Aug 2016 | Sep 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRBCT | FA Resiliency - BCT | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Sep 2016 | Sep 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRBCT | FA Resiliency - BCT | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Sep 2016 | Oct 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRBCT | FA Resiliency - BCT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2020 | Oct 2016 | Oct 2024
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDYNYA | WCS - New York Aquarium Sandy Renovation | 1 | DESIGN | Jan 2016 | Jan 2016 | Jan 2016 | Jan 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDYNYA | WCS - New York Aquarium Sandy Renovation | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2016 | Jun 2016 | Jan 2016 | Jun 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDYNYA | WCS - New York Aquarium Sandy Renovation | 3 | CONSTRUCTION | Jul 2016 | Jun 2017 | Jul 2016 | Jun 2017
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDYNYA | WCS - New York Aquarium Sandy Renovation | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2017 | Jun 2020 | Jul 2017 | Jun 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDYNYA | WCS - New York Aquarium Sandy Renovation | 5 | SUBSTANTIAL COMPLETION | Jul 2020 | Jun 2020 | Jul 2023 | Jun 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDYNYA | WCS - New York Aquarium Sandy Renovation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Jul 2020 | Jul 2023 | Jul 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBMTOSW | SBMT Offshore Wind | 1 | DESIGN | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBMTOSW | SBMT Offshore Wind | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Aug 2021 | Jul 2021 | Aug 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBMTOSW | SBMT Offshore Wind | 3 | CONSTRUCTION | Aug 2021 | Sep 2021 | Aug 2021 | Sep 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBMTOSW | SBMT Offshore Wind | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Sep 2021 | Sep 2021 | Sep 2021
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBMTOSW | SBMT Offshore Wind | 5 | SUBSTANTIAL COMPLETION | Sep 2021 | Oct 2029 | Sep 2021 | Oct 2029
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBMTOSW | SBMT Offshore Wind | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2029 | Oct 2029 | Oct 2029 | Oct 2029
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SEEDVANST | Broadway Junction-Van Sinderen streetscape improvements | 1 | DESIGN | Jul 2023 | Jul 2023 | Jul 2023 | Jul 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SEEDVANST | Broadway Junction-Van Sinderen streetscape improvements | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SEEDVANST | Broadway Junction-Van Sinderen streetscape improvements | 3 | CONSTRUCTION | Aug 2023 | Sep 2023 | Aug 2023 | Sep 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SEEDVANST | Broadway Junction-Van Sinderen streetscape improvements | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Sep 2023 | Sep 2023 | Sep 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SEEDVANST | Broadway Junction-Van Sinderen streetscape improvements | 5 | SUBSTANTIAL COMPLETION | Sep 2023 | Oct 2023 | Sep 2023 | Oct 2023
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SEEDVANST | Broadway Junction-Van Sinderen streetscape improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2023 | Jun 2026 | Oct 2023 | Jun 2026
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SNSTFRGH2 | Sunset Park Areawide Infrastructure Improvements | 1 | DESIGN | Jan 2016 | Jan 2016 | Jan 2016 | Jan 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SNSTFRGH2 | Sunset Park Areawide Infrastructure Improvements | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2016 | Jun 2016 | Jan 2016 | Jun 2016
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SNSTFRGH2 | Sunset Park Areawide Infrastructure Improvements | 3 | CONSTRUCTION | Jul 2016 | Jun 2017 | Jul 2016 | Jun 2017
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SNSTFRGH2 | Sunset Park Areawide Infrastructure Improvements | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2017 | Jun 2020 | Jul 2017 | Jun 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SNSTFRGH2 | Sunset Park Areawide Infrastructure Improvements | 5 | SUBSTANTIAL COMPLETION | Jul 2020 | Jun 2020 | Jul 2020 | Jun 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SNSTFRGH2 | Sunset Park Areawide Infrastructure Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Jul 2020 | Jul 2020 | Jul 2025
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SUNSETPAR | Sunset Park Waterfront Redevelopment | 1 | DESIGN | Jul 2000 | Jul 2000 | Jul 2000 | Jun 2007
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SUNSETPAR | Sunset Park Waterfront Redevelopment | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2000 | Aug 2000 | Jul 2007 | Jun 2007
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SUNSETPAR | Sunset Park Waterfront Redevelopment | 3 | CONSTRUCTION | Aug 2000 | Jun 2006 | Jul 2007 | Jun 2007
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SUNSETPAR | Sunset Park Waterfront Redevelopment | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2006 | Jun 2006 | Jul 2007 | Jun 2007
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SUNSETPAR | Sunset Park Waterfront Redevelopment | 5 | SUBSTANTIAL COMPLETION | Jul 2006 | Jun 2006 | Jul 2007 | Jun 2007
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SUNSETPAR | Sunset Park Waterfront Redevelopment | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2006 | Jul 2006 | Jan 2004 | Jun 2033
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLBKWSMM | BROOKLYN WHOLESALE MEAT MARKET | 1 | DESIGN | Jul 2020 | Jul 2020 | Jul 2020 | Jul 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLBKWSMM | BROOKLYN WHOLESALE MEAT MARKET | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Aug 2020 | Jul 2020 | Aug 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLBKWSMM | BROOKLYN WHOLESALE MEAT MARKET | 3 | CONSTRUCTION | Aug 2020 | Sep 2020 | Aug 2020 | Sep 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLBKWSMM | BROOKLYN WHOLESALE MEAT MARKET | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Sep 2020 | Sep 2020 | Sep 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLBKWSMM | BROOKLYN WHOLESALE MEAT MARKET | 5 | SUBSTANTIAL COMPLETION | Sep 2020 | Oct 2020 | Sep 2020 | Oct 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLBKWSMM | BROOKLYN WHOLESALE MEAT MARKET | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2020 | Oct 2020 | Oct 2020 | Jun 2026
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLPIER6 | BUSH TERMINAL PIER 6 RECONSTRUCTION | 1 | DESIGN | Jul 2020 | Jul 2020 | Jul 2020 | Jul 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLPIER6 | BUSH TERMINAL PIER 6 RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Aug 2020 | Jul 2020 | Aug 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLPIER6 | BUSH TERMINAL PIER 6 RECONSTRUCTION | 3 | CONSTRUCTION | Aug 2020 | Sep 2020 | Aug 2020 | Sep 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLPIER6 | BUSH TERMINAL PIER 6 RECONSTRUCTION | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Sep 2020 | Sep 2020 | Sep 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLPIER6 | BUSH TERMINAL PIER 6 RECONSTRUCTION | 5 | SUBSTANTIAL COMPLETION | Sep 2020 | Oct 2020 | Sep 2020 | Oct 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLPIER6 | BUSH TERMINAL PIER 6 RECONSTRUCTION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2020 | Oct 2020 | Oct 2020 | Jun 2026
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLPIER7 | BUSH TERMINAL PIER 7 DEMOLITION | 1 | DESIGN | Jul 2020 | Jul 2020 | Jul 2020 | Jul 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLPIER7 | BUSH TERMINAL PIER 7 DEMOLITION | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Aug 2020 | Jul 2020 | Aug 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLPIER7 | BUSH TERMINAL PIER 7 DEMOLITION | 3 | CONSTRUCTION | Aug 2020 | Sep 2020 | Aug 2020 | Sep 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLPIER7 | BUSH TERMINAL PIER 7 DEMOLITION | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Sep 2020 | Sep 2020 | Sep 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLPIER7 | BUSH TERMINAL PIER 7 DEMOLITION | 5 | SUBSTANTIAL COMPLETION | Sep 2020 | Oct 2020 | Sep 2020 | Oct 2020
20231026 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLPIER7 | BUSH TERMINAL PIER 7 DEMOLITION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2020 | Oct 2020 | Oct 2020 | Jun 2026
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | GI-RH-GR | GI - GREEN ROOF INSTALLATION AT RED HOOK HOUSES IN BKLYN | 1 | DEVELOP SCOPE | Jan 2022 | Mar 2022 | Jan 2021 | Mar 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | GI-RH-GR | GI - GREEN ROOF INSTALLATION AT RED HOOK HOUSES IN BKLYN | 2 | PRELIMINARY DESIGN | Apr 2022 | Jul 2022 | Apr 2021 | Jul 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | GI-RH-GR | GI - GREEN ROOF INSTALLATION AT RED HOOK HOUSES IN BKLYN | 3 | FINAL DESIGN | Jul 2022 | Jan 2023 | Jul 2021 | Jan 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | GI-RH-GR | GI - GREEN ROOF INSTALLATION AT RED HOOK HOUSES IN BKLYN | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2023 | Apr 2023 | Jan 2022 | Apr 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | GI-RH-GR | GI - GREEN ROOF INSTALLATION AT RED HOOK HOUSES IN BKLYN | 5 | CONSTRUCTION TO 25% | Apr 2023 | Aug 2023 | Apr 2022 | Aug 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | GI-RH-GR | GI - GREEN ROOF INSTALLATION AT RED HOOK HOUSES IN BKLYN | 6 | CONSTRUCTION TO 50% | Aug 2023 | Dec 2023 | Aug 2022 | Dec 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | GI-RH-GR | GI - GREEN ROOF INSTALLATION AT RED HOOK HOUSES IN BKLYN | 7 | CONSTRUCTION TO 75% | Dec 2023 | Apr 2024 | Dec 2022 | Apr 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | GI-RH-GR | GI - GREEN ROOF INSTALLATION AT RED HOOK HOUSES IN BKLYN | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2024 | Jul 2024 | Apr 2023 | Jul 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | GI-RH-GR | GI - GREEN ROOF INSTALLATION AT RED HOOK HOUSES IN BKLYN | 9 | SUBSTANTIAL COMPLETION | Jul 2024 | Sep 2024 | Jul 2023 | Sep 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | GI-RH-GR | GI - GREEN ROOF INSTALLATION AT RED HOOK HOUSES IN BKLYN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Oct 2024 | Sep 2023 | Oct 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM06BOBK | BOULEVARD BRICKWORK | 1 | DESIGN | Sep 2019 | Feb 2020 | Jan 2025 | Dec 2025
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM06BOBK | BOULEVARD BRICKWORK | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Aug 2020 | Jan 2026 | Dec 2026
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM06BOBK | BOULEVARD BRICKWORK | 3 | CONSTRUCTION | Aug 2020 | Aug 2021 | Jan 2027 | Dec 2027
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM06BOBK | BOULEVARD BRICKWORK | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Jan 2027 | Dec 2027
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM06BOBK | BOULEVARD BRICKWORK | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Jan 2028 | Dec 2031
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM12MCPL | MARCY HOUSES DAY CARE CENTER PLAYGROUND | 1 | DESIGN | Jan 2012 | Jun 2012 | Jan 2012 | Oct 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM12MCPL | MARCY HOUSES DAY CARE CENTER PLAYGROUND | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2012 | Nov 2012 | Oct 2019 | Oct 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM12MCPL | MARCY HOUSES DAY CARE CENTER PLAYGROUND | 3 | CONSTRUCTION | Nov 2012 | Nov 2013 | Oct 2019 | Oct 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM12MCPL | MARCY HOUSES DAY CARE CENTER PLAYGROUND | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2013 | May 2014 | Oct 2019 | Oct 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM12MCPL | MARCY HOUSES DAY CARE CENTER PLAYGROUND | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2013 | May 2014 | Oct 2019 | Oct 2024
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13SURF | SUMNER HOUSES ROOF REPLACEMENT | 1 | DESIGN | Jan 2013 | Jul 2013 | Mar 2012 | Dec 2013
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13SURF | SUMNER HOUSES ROOF REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2013 | Dec 2013 | Dec 2013 | Jun 2014
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13SURF | SUMNER HOUSES ROOF REPLACEMENT | 3 | CONSTRUCTION | Dec 2013 | Dec 2014 | Jun 2014 | Apr 2016
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13SURF | SUMNER HOUSES ROOF REPLACEMENT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2014 | Jun 2015 | Jun 2014 | Apr 2016
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13SURF | SUMNER HOUSES ROOF REPLACEMENT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2014 | Jun 2015 | Apr 2016 | Aug 2025
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM14KBEY | KINGSBOROUGH AND EXTENSION ENERGY IMPROVEMENTS | 1 | DESIGN | May 2014 | Oct 2014 | May 2014 | Oct 2014
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM14KBEY | KINGSBOROUGH AND EXTENSION ENERGY IMPROVEMENTS | 2 | BID AWARD AND REGISTER CONTRCT | Oct 2014 | Mar 2015 | Oct 2014 | Mar 2015
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM14KBEY | KINGSBOROUGH AND EXTENSION ENERGY IMPROVEMENTS | 3 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM14KBEY | KINGSBOROUGH AND EXTENSION ENERGY IMPROVEMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Sep 2016 | Mar 2015 | Mar 2016
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM14KBEY | KINGSBOROUGH AND EXTENSION ENERGY IMPROVEMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Sep 2016 | Mar 2016 | Feb 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15ODPA | O'DWYER GARDENS PLAYGROUND UPGRADES | 1 | DESIGN | Jan 2015 | Jun 2015 | Jan 2015 | Jun 2015
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15ODPA | O'DWYER GARDENS PLAYGROUND UPGRADES | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Nov 2015 | Jul 2015 | Nov 2015
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15ODPA | O'DWYER GARDENS PLAYGROUND UPGRADES | 3 | CONSTRUCTION | Nov 2015 | Nov 2016 | Nov 2015 | Nov 2016
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15ODPA | O'DWYER GARDENS PLAYGROUND UPGRADES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2016 | May 2017 | Nov 2015 | Nov 2016
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15ODPA | O'DWYER GARDENS PLAYGROUND UPGRADES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2016 | May 2017 | Nov 2016 | Nov 2024
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16HPBR | HOPE GARDENS INSTALLATION OF BOILERS AND RELATED EQUIPMENT | 1 | DESIGN | Jan 2016 | Jul 2016 | Nov 2016 | Dec 2017
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16HPBR | HOPE GARDENS INSTALLATION OF BOILERS AND RELATED EQUIPMENT | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Nov 2016 | Dec 2017 | May 2018
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16HPBR | HOPE GARDENS INSTALLATION OF BOILERS AND RELATED EQUIPMENT | 3 | CONSTRUCTION | Nov 2016 | Nov 2017 | May 2018 | May 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16HPBR | HOPE GARDENS INSTALLATION OF BOILERS AND RELATED EQUIPMENT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | May 2018 | May 2018 | May 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16HPBR | HOPE GARDENS INSTALLATION OF BOILERS AND RELATED EQUIPMENT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | May 2018 | May 2019 | May 2031
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16SURF | SURF GARDENS DEVELOPMENT - PLAYGROUND RENOVATION | 1 | DESIGN | Jan 2016 | Jul 2016 | Jan 2016 | Jul 2016
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16SURF | SURF GARDENS DEVELOPMENT - PLAYGROUND RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Nov 2016 | Jul 2016 | Nov 2016
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16SURF | SURF GARDENS DEVELOPMENT - PLAYGROUND RENOVATION | 3 | CONSTRUCTION | Nov 2016 | Nov 2017 | Nov 2016 | Nov 2017
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16SURF | SURF GARDENS DEVELOPMENT - PLAYGROUND RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | May 2018 | Nov 2016 | Nov 2017
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16SURF | SURF GARDENS DEVELOPMENT - PLAYGROUND RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | May 2018 | Nov 2017 | Nov 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ATBC | ATLANTIC TERMINAL BASKETBALL COURT RENOVATION | 1 | DESIGN | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ATBC | ATLANTIC TERMINAL BASKETBALL COURT RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2017 | Jun 2018 | Dec 2017 | Jun 2018
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ATBC | ATLANTIC TERMINAL BASKETBALL COURT RENOVATION | 3 | CONSTRUCTION | Jun 2018 | Jun 2019 | Jun 2018 | Jun 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ATBC | ATLANTIC TERMINAL BASKETBALL COURT RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2019 | Dec 2019 | Jun 2018 | Jun 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ATBC | ATLANTIC TERMINAL BASKETBALL COURT RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2019 | Dec 2019 | Jun 2019 | Jun 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BPBC | BORINQUEN PLAZA I BASKETBALL COURT UPGRADE | 1 | DESIGN | Jan 2018 | Jun 2018 | Jan 2018 | Jun 2018
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BPBC | BORINQUEN PLAZA I BASKETBALL COURT UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BPBC | BORINQUEN PLAZA I BASKETBALL COURT UPGRADE | 3 | CONSTRUCTION | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BPBC | BORINQUEN PLAZA I BASKETBALL COURT UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BPBC | BORINQUEN PLAZA I BASKETBALL COURT UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2019 | Dec 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BSVB | BROWNSVILLE AND SARATOGA VILLAGE BOILER REPAIR | 1 | DESIGN | Feb 2018 | Aug 2018 | Feb 2018 | Aug 2018
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BSVB | BROWNSVILLE AND SARATOGA VILLAGE BOILER REPAIR | 2 | BID AWARD AND REGISTER CONTRCT | Aug 2018 | Jan 2019 | Aug 2018 | Jan 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BSVB | BROWNSVILLE AND SARATOGA VILLAGE BOILER REPAIR | 3 | CONSTRUCTION | Jan 2019 | Jan 2020 | Jan 2019 | Jan 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BSVB | BROWNSVILLE AND SARATOGA VILLAGE BOILER REPAIR | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2020 | Jul 2020 | Jan 2019 | Jan 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BSVB | BROWNSVILLE AND SARATOGA VILLAGE BOILER REPAIR | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2020 | Jul 2020 | Jan 2020 | Jan 2025
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CHBW | CYPRESS HILLS BOILER WORK | 1 | DESIGN | Feb 2018 | Aug 2018 | Feb 2018 | Aug 2018
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CHBW | CYPRESS HILLS BOILER WORK | 2 | BID AWARD AND REGISTER CONTRCT | Aug 2018 | Jan 2019 | Aug 2018 | Jan 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CHBW | CYPRESS HILLS BOILER WORK | 3 | CONSTRUCTION | Jan 2019 | Jan 2020 | Jan 2019 | Jan 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CHBW | CYPRESS HILLS BOILER WORK | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2020 | Jul 2020 | Jan 2019 | Jan 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CHBW | CYPRESS HILLS BOILER WORK | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2020 | Jul 2020 | Jan 2020 | Jan 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HYEL | HYLAN ELEVATORS | 1 | DESIGN | Apr 2018 | Sep 2018 | Apr 2018 | Sep 2018
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HYEL | HYLAN ELEVATORS | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2018 | Mar 2019 | Sep 2018 | Mar 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HYEL | HYLAN ELEVATORS | 3 | CONSTRUCTION | Mar 2019 | Mar 2020 | Mar 2019 | Mar 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HYEL | HYLAN ELEVATORS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Sep 2020 | Mar 2019 | Mar 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HYEL | HYLAN ELEVATORS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Sep 2020 | Mar 2020 | Mar 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18IGIR | INGERSOLL GARDENS INSTALLATION OF IRRIGATION | 1 | DESIGN | Apr 2018 | Sep 2018 | Apr 2018 | Sep 2018
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18IGIR | INGERSOLL GARDENS INSTALLATION OF IRRIGATION | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2018 | Mar 2019 | Sep 2018 | Mar 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18IGIR | INGERSOLL GARDENS INSTALLATION OF IRRIGATION | 3 | CONSTRUCTION | Mar 2019 | Mar 2020 | Mar 2019 | Mar 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18IGIR | INGERSOLL GARDENS INSTALLATION OF IRRIGATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Sep 2020 | Mar 2019 | Mar 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18IGIR | INGERSOLL GARDENS INSTALLATION OF IRRIGATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Sep 2020 | Mar 2020 | Mar 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18INBC | INGERSOLL HOUSES BASKETBALL COURT RENOVATIONS | 1 | DESIGN | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18INBC | INGERSOLL HOUSES BASKETBALL COURT RENOVATIONS | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2018 | Jun 2019 | Dec 2018 | Jun 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18INBC | INGERSOLL HOUSES BASKETBALL COURT RENOVATIONS | 3 | CONSTRUCTION | Jun 2019 | Jun 2020 | Jun 2019 | Jun 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18INBC | INGERSOLL HOUSES BASKETBALL COURT RENOVATIONS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2020 | Dec 2020 | Jun 2019 | Jun 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18INBC | INGERSOLL HOUSES BASKETBALL COURT RENOVATIONS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2020 | Dec 2020 | Jun 2020 | Jun 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PKTV | PINK CCTV | 1 | DESIGN | Feb 2019 | Aug 2019 | Feb 2019 | Aug 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PKTV | PINK CCTV | 2 | BID AWARD AND REGISTER CONTRCT | Aug 2019 | Feb 2020 | Aug 2019 | Feb 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PKTV | PINK CCTV | 3 | CONSTRUCTION | Feb 2020 | Feb 2021 | Feb 2020 | Feb 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PKTV | PINK CCTV | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Aug 2021 | Feb 2020 | Feb 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PKTV | PINK CCTV | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Aug 2021 | Feb 2021 | Aug 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WBCC | PLAYGROUND UPGRADES AT WILLIAMSBURG DAY CARE CENTER | 1 | DESIGN | Feb 2018 | Jul 2018 | Feb 2018 | Jul 2018
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WBCC | PLAYGROUND UPGRADES AT WILLIAMSBURG DAY CARE CENTER | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Jan 2019 | Jul 2018 | Jan 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WBCC | PLAYGROUND UPGRADES AT WILLIAMSBURG DAY CARE CENTER | 3 | CONSTRUCTION | Jan 2019 | Jan 2020 | Jan 2019 | Jan 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WBCC | PLAYGROUND UPGRADES AT WILLIAMSBURG DAY CARE CENTER | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2020 | Jul 2020 | Jan 2019 | Jan 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WBCC | PLAYGROUND UPGRADES AT WILLIAMSBURG DAY CARE CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2020 | Jul 2020 | Jan 2020 | Jan 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WHIT | NYCHA WHITMAN/WILLOUGHBY SENIOR CENTER HVAC UPGRADE | 1 | DESIGN | Jan 2018 | Jun 2018 | Jan 2018 | Jun 2018
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WHIT | NYCHA WHITMAN/WILLOUGHBY SENIOR CENTER HVAC UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WHIT | NYCHA WHITMAN/WILLOUGHBY SENIOR CENTER HVAC UPGRADE | 3 | CONSTRUCTION | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WHIT | NYCHA WHITMAN/WILLOUGHBY SENIOR CENTER HVAC UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WHIT | NYCHA WHITMAN/WILLOUGHBY SENIOR CENTER HVAC UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2019 | Dec 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WIPG | WILLIAMSBURG HOUSES PLAYGROUND UPGRADE | 1 | DESIGN | Feb 2018 | Jul 2018 | Feb 2018 | Jul 2018
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WIPG | WILLIAMSBURG HOUSES PLAYGROUND UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Jan 2019 | Jul 2018 | Jan 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WIPG | WILLIAMSBURG HOUSES PLAYGROUND UPGRADE | 3 | CONSTRUCTION | Jan 2019 | Jan 2020 | Jan 2019 | Jan 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WIPG | WILLIAMSBURG HOUSES PLAYGROUND UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2020 | Jul 2020 | Jan 2019 | Jan 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WIPG | WILLIAMSBURG HOUSES PLAYGROUND UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2020 | Jul 2020 | Jan 2020 | Jan 2024
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WKCC | WYCKOFF GARDENS COMMUNITY CENTER RENOVATION | 1 | DESIGN | Jan 2018 | Jun 2018 | Jan 2018 | Jun 2018
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WKCC | WYCKOFF GARDENS COMMUNITY CENTER RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WKCC | WYCKOFF GARDENS COMMUNITY CENTER RENOVATION | 3 | CONSTRUCTION | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WKCC | WYCKOFF GARDENS COMMUNITY CENTER RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WKCC | WYCKOFF GARDENS COMMUNITY CENTER RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2019 | Dec 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WKLG | WYCKOFF GARDENS LIGHTING | 1 | DESIGN | Jan 2018 | Jun 2018 | Jan 2018 | Jun 2018
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WKLG | WYCKOFF GARDENS LIGHTING | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WKLG | WYCKOFF GARDENS LIGHTING | 3 | CONSTRUCTION | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WKLG | WYCKOFF GARDENS LIGHTING | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WKLG | WYCKOFF GARDENS LIGHTING | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2019 | Dec 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WSEC | WHITMAN BASKETBALL COURT AND SECURITY UPGRADES | 3 | CONSTRUCTION | Jun 2019 | Jun 2020 | Jun 2019 | Jun 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WSEC | WHITMAN BASKETBALL COURT AND SECURITY UPGRADES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2020 | Dec 2020 | Jun 2019 | Jun 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WSEC | WHITMAN BASKETBALL COURT AND SECURITY UPGRADES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2020 | Dec 2020 | Jun 2020 | Dec 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WSWT | WOODSON WATER TANK | 2 | BID AWARD AND REGISTER CONTRCT | Apr 2019 | Oct 2019 | Apr 2019 | Oct 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WSWT | WOODSON WATER TANK | 3 | CONSTRUCTION | Oct 2019 | Oct 2020 | Oct 2019 | Oct 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WSWT | WOODSON WATER TANK | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2020 | Apr 2021 | Oct 2019 | Oct 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WSWT | WOODSON WATER TANK | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2020 | Apr 2021 | Oct 2020 | Apr 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CSVE | SARATOGA VILLAGE ELEVATORS | 1 | DESIGN | Feb 2019 | Aug 2019 | Feb 2019 | Aug 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CSVE | SARATOGA VILLAGE ELEVATORS | 2 | BID AWARD AND REGISTER CONTRCT | Aug 2019 | Feb 2020 | Aug 2019 | Feb 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CSVE | SARATOGA VILLAGE ELEVATORS | 3 | CONSTRUCTION | Feb 2020 | Feb 2021 | Feb 2020 | Feb 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CSVE | SARATOGA VILLAGE ELEVATORS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Aug 2021 | Feb 2020 | Feb 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CSVE | SARATOGA VILLAGE ELEVATORS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Aug 2021 | Feb 2021 | Aug 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19FHSE | FARRAGUT HOUSES SECURITY LIGHTING | 1 | DESIGN | Jan 2019 | Jul 2019 | Jan 2019 | Jul 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19FHSE | FARRAGUT HOUSES SECURITY LIGHTING | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Jan 2020 | Jul 2019 | Jan 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19FHSE | FARRAGUT HOUSES SECURITY LIGHTING | 3 | CONSTRUCTION | Jan 2020 | Jan 2021 | Jan 2020 | Jan 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19FHSE | FARRAGUT HOUSES SECURITY LIGHTING | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2021 | Jul 2021 | Jan 2020 | Jan 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19FHSE | FARRAGUT HOUSES SECURITY LIGHTING | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19HHTV | HOWARD HOUSES CCTV | 1 | DESIGN | Feb 2019 | Aug 2019 | Feb 2019 | Aug 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19HHTV | HOWARD HOUSES CCTV | 2 | BID AWARD AND REGISTER CONTRCT | Aug 2019 | Feb 2020 | Aug 2019 | Feb 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19HHTV | HOWARD HOUSES CCTV | 3 | CONSTRUCTION | Feb 2020 | Feb 2021 | Feb 2020 | Feb 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19HHTV | HOWARD HOUSES CCTV | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Aug 2021 | Feb 2020 | Feb 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19HHTV | HOWARD HOUSES CCTV | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Aug 2021 | Feb 2021 | Aug 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19TCPU | TOMPKINS HOUSES CHILDRENS PARK UPGRADE | 1 | DESIGN | Mar 2019 | Sep 2019 | Mar 2019 | Sep 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19TCPU | TOMPKINS HOUSES CHILDRENS PARK UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Mar 2020 | Sep 2019 | Mar 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19TCPU | TOMPKINS HOUSES CHILDRENS PARK UPGRADE | 3 | CONSTRUCTION | Mar 2020 | Mar 2021 | Mar 2020 | Mar 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19TCPU | TOMPKINS HOUSES CHILDRENS PARK UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Sep 2021 | Mar 2020 | Mar 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19TCPU | TOMPKINS HOUSES CHILDRENS PARK UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Sep 2021 | Mar 2021 | Sep 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ALPU | PLAYGROUND RENOVATION- ALBANY HOUSES | 1 | DESIGN | Jan 2018 | Jun 2018 | Jan 2018 | Jun 2018
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ALPU | PLAYGROUND RENOVATION- ALBANY HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ALPU | PLAYGROUND RENOVATION- ALBANY HOUSES | 3 | CONSTRUCTION | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ALPU | PLAYGROUND RENOVATION- ALBANY HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ALPU | PLAYGROUND RENOVATION- ALBANY HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2019 | Dec 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BCCG | BUSHWICK HOUSES UPGRADE COMMUNITY CENTER GYM | 1 | DESIGN | Sep 2019 | Sep 2019 | Sep 2019 | Sep 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BCCG | BUSHWICK HOUSES UPGRADE COMMUNITY CENTER GYM | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Feb 2020 | Sep 2019 | Feb 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BCCG | BUSHWICK HOUSES UPGRADE COMMUNITY CENTER GYM | 3 | CONSTRUCTION | Feb 2020 | Feb 2021 | Feb 2020 | Feb 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BCCG | BUSHWICK HOUSES UPGRADE COMMUNITY CENTER GYM | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Aug 2021 | Feb 2020 | Feb 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BCCG | BUSHWICK HOUSES UPGRADE COMMUNITY CENTER GYM | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Aug 2021 | Feb 2021 | Feb 2025
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CPPU | COOPER PARK PLAY GROUND UPGRADE | 1 | DESIGN | Sep 2019 | Feb 2020 | Feb 2016 | Aug 2016
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CPPU | COOPER PARK PLAY GROUND UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Aug 2020 | Aug 2016 | Feb 2017
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CPPU | COOPER PARK PLAY GROUND UPGRADE | 3 | CONSTRUCTION | Aug 2020 | Aug 2021 | Feb 2017 | Feb 2018
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CPPU | COOPER PARK PLAY GROUND UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Feb 2017 | Feb 2018
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CPPU | COOPER PARK PLAY GROUND UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Feb 2018 | Feb 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GCBR | GLENWOOD COMMUNITY CENTER RENOVATE BATHROOM | 1 | DESIGN | Sep 2019 | Feb 2020 | Sep 2019 | Feb 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GCBR | GLENWOOD COMMUNITY CENTER RENOVATE BATHROOM | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Aug 2020 | Feb 2020 | Aug 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GCBR | GLENWOOD COMMUNITY CENTER RENOVATE BATHROOM | 3 | CONSTRUCTION | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GCBR | GLENWOOD COMMUNITY CENTER RENOVATE BATHROOM | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2020 | Aug 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GCBR | GLENWOOD COMMUNITY CENTER RENOVATE BATHROOM | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2021 | Feb 2024
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GHLC | LED LIGHTING AND CAMERAS GOWANUS HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Aug 2020 | Feb 2020 | Aug 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GHLC | LED LIGHTING AND CAMERAS GOWANUS HOUSES | 3 | CONSTRUCTION | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GHLC | LED LIGHTING AND CAMERAS GOWANUS HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2020 | Aug 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GHLC | LED LIGHTING AND CAMERAS GOWANUS HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2021 | Feb 2024
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20HCAM | PHASE 2 CAMERAS AT LANGSTON HUGES HOUSES | 1 | DEVELOP SCOPE | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20HCAM | PHASE 2 CAMERAS AT LANGSTON HUGES HOUSES | 2 | PRELIMINARY DESIGN | Nov 2019 | Mar 2020 | Nov 2019 | Mar 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20HCAM | PHASE 2 CAMERAS AT LANGSTON HUGES HOUSES | 3 | FINAL DESIGN | Mar 2020 | Sep 2020 | Mar 2020 | Sep 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20HCAM | PHASE 2 CAMERAS AT LANGSTON HUGES HOUSES | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2020 | Dec 2020 | Sep 2020 | Dec 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20HCAM | PHASE 2 CAMERAS AT LANGSTON HUGES HOUSES | 5 | CONSTRUCTION TO 25% | Dec 2020 | Apr 2021 | Dec 2020 | Apr 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20HCAM | PHASE 2 CAMERAS AT LANGSTON HUGES HOUSES | 6 | CONSTRUCTION TO 50% | Apr 2021 | Aug 2021 | Apr 2021 | Aug 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20HCAM | PHASE 2 CAMERAS AT LANGSTON HUGES HOUSES | 7 | CONSTRUCTION TO 75% | Aug 2021 | Dec 2021 | Aug 2021 | Dec 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20HCAM | PHASE 2 CAMERAS AT LANGSTON HUGES HOUSES | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2021 | Mar 2022 | Dec 2021 | Mar 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20HCAM | PHASE 2 CAMERAS AT LANGSTON HUGES HOUSES | 9 | SUBSTANTIAL COMPLETION | Mar 2022 | May 2022 | Mar 2022 | May 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20HCAM | PHASE 2 CAMERAS AT LANGSTON HUGES HOUSES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2022 | Jun 2022 | May 2022 | Jun 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20KRWJ | KINGSBOROUGH DEVELOPMENT RESTORATION OF WALLS OF JERICHO | 1 | DEVELOP SCOPE | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20KRWJ | KINGSBOROUGH DEVELOPMENT RESTORATION OF WALLS OF JERICHO | 2 | PRELIMINARY DESIGN | Nov 2019 | Mar 2020 | Nov 2019 | Mar 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20KRWJ | KINGSBOROUGH DEVELOPMENT RESTORATION OF WALLS OF JERICHO | 3 | FINAL DESIGN | Mar 2020 | Sep 2020 | Mar 2020 | Sep 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20KRWJ | KINGSBOROUGH DEVELOPMENT RESTORATION OF WALLS OF JERICHO | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2020 | Dec 2020 | Sep 2020 | Dec 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20KRWJ | KINGSBOROUGH DEVELOPMENT RESTORATION OF WALLS OF JERICHO | 5 | CONSTRUCTION TO 25% | Dec 2020 | Apr 2021 | Dec 2020 | Apr 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20KRWJ | KINGSBOROUGH DEVELOPMENT RESTORATION OF WALLS OF JERICHO | 6 | CONSTRUCTION TO 50% | Apr 2021 | Aug 2021 | Apr 2021 | Aug 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20KRWJ | KINGSBOROUGH DEVELOPMENT RESTORATION OF WALLS OF JERICHO | 7 | CONSTRUCTION TO 75% | Aug 2021 | Dec 2021 | Aug 2021 | Sep 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20KRWJ | KINGSBOROUGH DEVELOPMENT RESTORATION OF WALLS OF JERICHO | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2021 | Mar 2022 | Sep 2022 | Dec 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20KRWJ | KINGSBOROUGH DEVELOPMENT RESTORATION OF WALLS OF JERICHO | 9 | SUBSTANTIAL COMPLETION | Mar 2022 | May 2022 | Dec 2022 | Feb 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20KRWJ | KINGSBOROUGH DEVELOPMENT RESTORATION OF WALLS OF JERICHO | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2022 | Jun 2022 | Feb 2023 | Mar 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SHEL | SHEEPSHEAD HOUSES-EXTERIOR LIGHTING UPGRADE | 1 | DESIGN | Sep 2019 | Feb 2020 | Sep 2019 | Feb 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SHEL | SHEEPSHEAD HOUSES-EXTERIOR LIGHTING UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Aug 2020 | Feb 2020 | Aug 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SHEL | SHEEPSHEAD HOUSES-EXTERIOR LIGHTING UPGRADE | 3 | CONSTRUCTION | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SHEL | SHEEPSHEAD HOUSES-EXTERIOR LIGHTING UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2020 | Aug 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SHEL | SHEEPSHEAD HOUSES-EXTERIOR LIGHTING UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2021 | Feb 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20TCCU | TOMPKINS - UPGRADE THE SPACE IN THE COMMUNITY CENTER | 1 | DESIGN | Sep 2019 | Feb 2020 | Sep 2019 | Feb 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20TCCU | TOMPKINS - UPGRADE THE SPACE IN THE COMMUNITY CENTER | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Aug 2020 | Feb 2020 | Aug 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20TCCU | TOMPKINS - UPGRADE THE SPACE IN THE COMMUNITY CENTER | 3 | CONSTRUCTION | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20TCCU | TOMPKINS - UPGRADE THE SPACE IN THE COMMUNITY CENTER | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2020 | Aug 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20TCCU | TOMPKINS - UPGRADE THE SPACE IN THE COMMUNITY CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2021 | Feb 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20THRR | TOMPKINS HOUSES ROOF REPLACEMENT | 1 | DESIGN | Sep 2019 | Feb 2020 | Sep 2019 | Feb 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20THRR | TOMPKINS HOUSES ROOF REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Aug 2020 | Feb 2020 | Aug 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20THRR | TOMPKINS HOUSES ROOF REPLACEMENT | 3 | CONSTRUCTION | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20THRR | TOMPKINS HOUSES ROOF REPLACEMENT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2020 | Aug 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20THRR | TOMPKINS HOUSES ROOF REPLACEMENT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2021 | Feb 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20VDCC | VAN DYKE 1 HOUSES COMPUTERS FOR NEW DAY CARE CENTER | 1 | DESIGN | Sep 2019 | Feb 2020 | Sep 2019 | Feb 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20VDCC | VAN DYKE 1 HOUSES COMPUTERS FOR NEW DAY CARE CENTER | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Aug 2020 | Feb 2020 | Aug 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20VDCC | VAN DYKE 1 HOUSES COMPUTERS FOR NEW DAY CARE CENTER | 3 | CONSTRUCTION | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20VDCC | VAN DYKE 1 HOUSES COMPUTERS FOR NEW DAY CARE CENTER | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2020 | Aug 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20VDCC | VAN DYKE 1 HOUSES COMPUTERS FOR NEW DAY CARE CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2021 | Feb 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21BHPR | NEW PLAYGROUND-REFURBISH AT BAYVIEW HOUSES | 1 | DESIGN | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21BHPR | NEW PLAYGROUND-REFURBISH AT BAYVIEW HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21BHPR | NEW PLAYGROUND-REFURBISH AT BAYVIEW HOUSES | 3 | CONSTRUCTION | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21BHPR | NEW PLAYGROUND-REFURBISH AT BAYVIEW HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2021 | Jun 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21BHPR | NEW PLAYGROUND-REFURBISH AT BAYVIEW HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21FAST | FARRAGUT UNDERGROUND STEAM | 1 | DESIGN | May 2022 | Nov 2022 | May 2022 | Nov 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21FAST | FARRAGUT UNDERGROUND STEAM | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2022 | May 2023 | Nov 2022 | May 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21FAST | FARRAGUT UNDERGROUND STEAM | 3 | CONSTRUCTION | May 2023 | May 2024 | May 2023 | May 2024
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21FAST | FARRAGUT UNDERGROUND STEAM | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2023 | May 2024
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21FAST | FARRAGUT UNDERGROUND STEAM | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21GHCC | INSTALL AWNING AT GLENWOOD HOUSES | 1 | DESIGN | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21GHCC | INSTALL AWNING AT GLENWOOD HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21GHCC | INSTALL AWNING AT GLENWOOD HOUSES | 3 | CONSTRUCTION | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21GHCC | INSTALL AWNING AT GLENWOOD HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2021 | Jun 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21GHCC | INSTALL AWNING AT GLENWOOD HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SHCC | SHEEPSHEAD HOUSES-COMMUNITY CENTER | 1 | DESIGN | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SHCC | SHEEPSHEAD HOUSES-COMMUNITY CENTER | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SHCC | SHEEPSHEAD HOUSES-COMMUNITY CENTER | 3 | CONSTRUCTION | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SHCC | SHEEPSHEAD HOUSES-COMMUNITY CENTER | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2021 | Jun 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SHCC | SHEEPSHEAD HOUSES-COMMUNITY CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SVCU | CAMERA UPGRADES AT SARATOGA VILLAGE | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SVCU | CAMERA UPGRADES AT SARATOGA VILLAGE | 3 | CONSTRUCTION | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SVCU | CAMERA UPGRADES AT SARATOGA VILLAGE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2021 | Jun 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SVCU | CAMERA UPGRADES AT SARATOGA VILLAGE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21UPCC | BATHROOM RENOVATION AT UNITY PLAZA COMMUNITY CENTER | 1 | DESIGN | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21UPCC | BATHROOM RENOVATION AT UNITY PLAZA COMMUNITY CENTER | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21UPCC | BATHROOM RENOVATION AT UNITY PLAZA COMMUNITY CENTER | 3 | CONSTRUCTION | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21UPCC | BATHROOM RENOVATION AT UNITY PLAZA COMMUNITY CENTER | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2021 | Jun 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21UPCC | BATHROOM RENOVATION AT UNITY PLAZA COMMUNITY CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22BCAM | BROWN HOUSES- CAMERAS | 1 | DESIGN | May 2022 | Nov 2022 | May 2022 | Nov 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22BCAM | BROWN HOUSES- CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2022 | May 2023 | Nov 2022 | May 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22BCAM | BROWN HOUSES- CAMERAS | 3 | CONSTRUCTION | May 2023 | May 2024 | May 2023 | May 2024
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22BCAM | BROWN HOUSES- CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2023 | May 2024
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22BCAM | BROWN HOUSES- CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22BCCY | BORINQUEN HOUSES- COMMUNITY CENTER & YMCA UPGRADE | 1 | DESIGN | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22BCCY | BORINQUEN HOUSES- COMMUNITY CENTER & YMCA UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22BCCY | BORINQUEN HOUSES- COMMUNITY CENTER & YMCA UPGRADE | 3 | CONSTRUCTION | Jun 2023 | May 2024 | Jun 2023 | May 2024
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22BCCY | BORINQUEN HOUSES- COMMUNITY CENTER & YMCA UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2024 | Nov 2024 | Jun 2023 | May 2024
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22BCCY | BORINQUEN HOUSES- COMMUNITY CENTER & YMCA UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2024 | Nov 2024 | Jun 2024 | Nov 2024
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22BRLC | BREUKELEN HOUSES - LEARNING CENTER | 1 | DESIGN | Jan 2022 | Jun 2022 | Jan 2022 | Jun 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22BRLC | BREUKELEN HOUSES - LEARNING CENTER | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22BRLC | BREUKELEN HOUSES - LEARNING CENTER | 3 | CONSTRUCTION | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22BRLC | BREUKELEN HOUSES - LEARNING CENTER | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jun 2024 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22BRLC | BREUKELEN HOUSES - LEARNING CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22CWLB | CARTER G WOODSON- LOBBY SECURITY | 1 | DESIGN | Jan 2022 | Jun 2022 | Jan 2022 | Jun 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22CWLB | CARTER G WOODSON- LOBBY SECURITY | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22CWLB | CARTER G WOODSON- LOBBY SECURITY | 3 | CONSTRUCTION | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22CWLB | CARTER G WOODSON- LOBBY SECURITY | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jun 2024 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22CWLB | CARTER G WOODSON- LOBBY SECURITY | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22LCAM | LANGSTON HUGHES HOUSES- CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22LCAM | LANGSTON HUGHES HOUSES- CAMERAS | 3 | CONSTRUCTION | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22LCAM | LANGSTON HUGHES HOUSES- CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jun 2024 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22LCAM | LANGSTON HUGHES HOUSES- CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22LSTM | LAFAYETTE GARDENS- STEM CENTER CONSTRUCTION | 1 | DESIGN | May 2022 | Nov 2022 | May 2022 | Nov 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22LSTM | LAFAYETTE GARDENS- STEM CENTER CONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2022 | May 2023 | Nov 2022 | May 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22LSTM | LAFAYETTE GARDENS- STEM CENTER CONSTRUCTION | 3 | CONSTRUCTION | May 2023 | May 2024 | May 2023 | May 2024
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22LSTM | LAFAYETTE GARDENS- STEM CENTER CONSTRUCTION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2023 | May 2024
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22LSTM | LAFAYETTE GARDENS- STEM CENTER CONSTRUCTION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22UTPR | UNITY TOWERS- CONEY ISLAND SITE 1B- PLAYGROUND | 1 | DESIGN | Oct 2021 | Apr 2022 | Oct 2021 | Apr 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22UTPR | UNITY TOWERS- CONEY ISLAND SITE 1B- PLAYGROUND | 2 | BID AWARD AND REGISTER CONTRCT | Apr 2022 | Oct 2022 | Apr 2022 | Oct 2022
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22UTPR | UNITY TOWERS- CONEY ISLAND SITE 1B- PLAYGROUND | 3 | CONSTRUCTION | Oct 2022 | Oct 2023 | Oct 2022 | Oct 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22UTPR | UNITY TOWERS- CONEY ISLAND SITE 1B- PLAYGROUND | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2023 | Apr 2024 | Oct 2022 | Oct 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22UTPR | UNITY TOWERS- CONEY ISLAND SITE 1B- PLAYGROUND | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2023 | Apr 2024 | Oct 2023 | Apr 2024
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23B2CC | BORINQUEN PLAZA II COMMUNITY CENTER IMPROVEMENTS | 1 | DESIGN | Jan 2023 | Jun 2023 | Jan 2023 | Jun 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23B2CC | BORINQUEN PLAZA II COMMUNITY CENTER IMPROVEMENTS | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Dec 2023 | Jul 2023 | Dec 2023
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23B2CC | BORINQUEN PLAZA II COMMUNITY CENTER IMPROVEMENTS | 3 | CONSTRUCTION | Dec 2023 | Dec 2024 | Dec 2023 | Dec 2024
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23B2CC | BORINQUEN PLAZA II COMMUNITY CENTER IMPROVEMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2024 | Jun 2025 | Dec 2023 | Dec 2024
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23B2CC | BORINQUEN PLAZA II COMMUNITY CENTER IMPROVEMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23GPED | GLENMORE PLAZA EMERGENCY EXIT DOORS | 1 | DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23GPED | GLENMORE PLAZA EMERGENCY EXIT DOORS | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Jan 2025 | Jul 2024 | Jan 2025
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23GPED | GLENMORE PLAZA EMERGENCY EXIT DOORS | 3 | CONSTRUCTION | Jan 2025 | Jan 2026 | Jan 2025 | Jan 2026
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23GPED | GLENMORE PLAZA EMERGENCY EXIT DOORS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2026 | Jul 2026 | Jan 2025 | Jan 2026
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23GPED | GLENMORE PLAZA EMERGENCY EXIT DOORS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2026 | Jul 2026 | Jan 2026 | Jul 2026
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23LIBD | LONG ISLAND BAPTIST- ENTRYWAY & EXTERIOR DOORS | 1 | DESIGN | Jun 2024 | Dec 2024 | Jun 2024 | Dec 2024
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23LIBD | LONG ISLAND BAPTIST- ENTRYWAY & EXTERIOR DOORS | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23LIBD | LONG ISLAND BAPTIST- ENTRYWAY & EXTERIOR DOORS | 3 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23LIBD | LONG ISLAND BAPTIST- ENTRYWAY & EXTERIOR DOORS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Dec 2026 | Jun 2025 | Jun 2026
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23LIBD | LONG ISLAND BAPTIST- ENTRYWAY & EXTERIOR DOORS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Dec 2026 | Jun 2026 | Dec 2026
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23MCSC | MARLBORO HOUSING- INTERIOR RENO COMMUNITY/SENIOR CENTER | 1 | DESIGN | Jun 2024 | Dec 2024 | Jun 2024 | Dec 2024
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23MCSC | MARLBORO HOUSING- INTERIOR RENO COMMUNITY/SENIOR CENTER | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23MCSC | MARLBORO HOUSING- INTERIOR RENO COMMUNITY/SENIOR CENTER | 3 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23MCSC | MARLBORO HOUSING- INTERIOR RENO COMMUNITY/SENIOR CENTER | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Dec 2026 | Jun 2025 | Jun 2026
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23MCSC | MARLBORO HOUSING- INTERIOR RENO COMMUNITY/SENIOR CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Dec 2026 | Jun 2026 | Dec 2026
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23RSCK | ROSETTA GASTON SENIOR CENTER- KITCHEN AND SITE RENO | 1 | DESIGN | Jun 2024 | Dec 2024 | Jun 2024 | Dec 2024
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23RSCK | ROSETTA GASTON SENIOR CENTER- KITCHEN AND SITE RENO | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23RSCK | ROSETTA GASTON SENIOR CENTER- KITCHEN AND SITE RENO | 3 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23RSCK | ROSETTA GASTON SENIOR CENTER- KITCHEN AND SITE RENO | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Dec 2026 | Jun 2025 | Jun 2026
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23RSCK | ROSETTA GASTON SENIOR CENTER- KITCHEN AND SITE RENO | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Dec 2026 | Jun 2026 | Dec 2026
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM24VDGR | VAN DYKE I, II GAS RISERS #10 | 1 | DESIGN | Jul 2023 | Jun 2024 | Jul 2023 | Jun 2024
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM24VDGR | VAN DYKE I, II GAS RISERS #10 | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Nov 2024 | Jul 2024 | Nov 2024
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM24VDGR | VAN DYKE I, II GAS RISERS #10 | 3 | CONSTRUCTION | Nov 2024 | Jun 2026 | Nov 2024 | Jun 2026
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM24VDGR | VAN DYKE I, II GAS RISERS #10 | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Sep 2026 | Nov 2024 | Jun 2026
20231026 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM24VDGR | VAN DYKE I, II GAS RISERS #10 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Sep 2026 | Jun 2026 | Sep 2026
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BRNHC | Brownsville Health Center Renovation of interior space | 1 | DESIGN | Jan 2020 | May 2021 | Jun 2025 | Jun 2027
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BRNHC | Brownsville Health Center Renovation of interior space | 2 | CONSTRUCTION | May 2021 | May 2026 | Jul 2027 | Feb 2030
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BRNHC | Brownsville Health Center Renovation of interior space | 3 | PUNCHLIST COMPLETE, JOB CLOSED | May 2026 | May 2026 | Mar 2030 | Aug 2030
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BRNHC | Brownsville Health Center Renovation of interior space | 4 | DEVELOP SCOPE | May 2026 | May 2026 | Mar 2030 | Aug 2030
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BRNHC | Brownsville Health Center Renovation of interior space | 5 | PRELIMINARY DESIGN | May 2026 | May 2026 | Mar 2030 | Aug 2030
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BRNHC | Brownsville Health Center Renovation of interior space | 6 | FINAL DESIGN | May 2026 | May 2026 | Mar 2030 | Aug 2030
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BRNHC | Brownsville Health Center Renovation of interior space | 7 | BID AWARD AND REGISTER CONTRCT | May 2026 | May 2026 | Mar 2030 | Aug 2030
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BRNHC | Brownsville Health Center Renovation of interior space | 8 | CONSTRUCTION TO 25% | May 2026 | May 2026 | Mar 2030 | Aug 2030
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BRNHC | Brownsville Health Center Renovation of interior space | 9 | CONSTRUCTION TO 50% | May 2026 | May 2026 | Mar 2030 | Aug 2030
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BRNHC | Brownsville Health Center Renovation of interior space | 10 | CONSTRUCTION TO 75% | May 2026 | May 2026 | Mar 2030 | Aug 2030
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BRNHC | Brownsville Health Center Renovation of interior space | 11 | ORIGINAL EQUIP & FURNISHING | May 2026 | May 2026 | Mar 2030 | Aug 2030
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BRNHC | Brownsville Health Center Renovation of interior space | 12 | SUBSTANTIAL COMPLETION | May 2026 | May 2026 | Mar 2030 | Aug 2030
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BRNHC | Brownsville Health Center Renovation of interior space | 13 | PUNCHLIST COMPLETE, JOB CLOSED | May 2026 | Jun 2026 | Mar 2030 | Aug 2030
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BUSHC | Bushwick Health Center exterior renovation/interior upgrades | 1 | DESIGN | Jan 2016 | May 2017 | Jan 2028 | Apr 2028
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BUSHC | Bushwick Health Center exterior renovation/interior upgrades | 2 | CONSTRUCTION | May 2017 | May 2022 | Apr 2028 | Aug 2028
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BUSHC | Bushwick Health Center exterior renovation/interior upgrades | 3 | PUNCHLIST COMPLETE, JOB CLOSED | May 2022 | May 2022 | Aug 2028 | Jan 2029
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BUSHC | Bushwick Health Center exterior renovation/interior upgrades | 4 | DEVELOP SCOPE | May 2022 | May 2022 | Jan 2029 | Apr 2029
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BUSHC | Bushwick Health Center exterior renovation/interior upgrades | 5 | PRELIMINARY DESIGN | May 2022 | May 2022 | May 2029 | Aug 2029
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BUSHC | Bushwick Health Center exterior renovation/interior upgrades | 6 | FINAL DESIGN | May 2022 | May 2022 | Aug 2029 | Dec 2029
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BUSHC | Bushwick Health Center exterior renovation/interior upgrades | 7 | BID AWARD AND REGISTER CONTRCT | May 2022 | May 2022 | Dec 2029 | Apr 2030
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BUSHC | Bushwick Health Center exterior renovation/interior upgrades | 8 | CONSTRUCTION TO 25% | May 2022 | May 2022 | Apr 2030 | Jul 2030
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BUSHC | Bushwick Health Center exterior renovation/interior upgrades | 9 | CONSTRUCTION TO 50% | May 2022 | May 2022 | Jul 2030 | Sep 2030
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BUSHC | Bushwick Health Center exterior renovation/interior upgrades | 10 | CONSTRUCTION TO 75% | May 2022 | May 2022 | Sep 2030 | Oct 2030
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BUSHC | Bushwick Health Center exterior renovation/interior upgrades | 11 | ORIGINAL EQUIP & FURNISHING | May 2022 | May 2022 | Sep 2030 | Oct 2030
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BUSHC | Bushwick Health Center exterior renovation/interior upgrades | 12 | SUBSTANTIAL COMPLETION | May 2022 | May 2022 | Sep 2030 | Oct 2030
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BUSHC | Bushwick Health Center exterior renovation/interior upgrades | 13 | PUNCHLIST COMPLETE, JOB CLOSED | May 2022 | Jun 2022 | Sep 2030 | Oct 2030
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WLSHC | Williamsburg Health Center Interior Renovation | 1 | DESIGN | Jan 2020 | May 2021 | Aug 2025 | Nov 2025
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WLSHC | Williamsburg Health Center Interior Renovation | 2 | CONSTRUCTION | May 2021 | May 2026 | Nov 2025 | Mar 2026
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WLSHC | Williamsburg Health Center Interior Renovation | 3 | PUNCHLIST COMPLETE, JOB CLOSED | May 2026 | May 2026 | Mar 2026 | Sep 2026
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WLSHC | Williamsburg Health Center Interior Renovation | 4 | DEVELOP SCOPE | May 2026 | May 2026 | Sep 2026 | Dec 2026
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WLSHC | Williamsburg Health Center Interior Renovation | 5 | PRELIMINARY DESIGN | May 2026 | May 2026 | Dec 2026 | Apr 2027
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WLSHC | Williamsburg Health Center Interior Renovation | 6 | FINAL DESIGN | May 2026 | May 2026 | Apr 2027 | Aug 2027
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WLSHC | Williamsburg Health Center Interior Renovation | 7 | CONSTRUCTION TO 75% | May 2026 | May 2026 | Aug 2027 | Dec 2027
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WLSHC | Williamsburg Health Center Interior Renovation | 8 | CONSTRUCTION TO 25% | May 2026 | May 2026 | Dec 2027 | Mar 2028
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WLSHC | Williamsburg Health Center Interior Renovation | 9 | CONSTRUCTION TO 50% | May 2026 | May 2026 | Mar 2028 | May 2028
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WLSHC | Williamsburg Health Center Interior Renovation | 10 | CONSTRUCTION TO 75% | May 2026 | May 2026 | May 2028 | Jun 2028
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WLSHC | Williamsburg Health Center Interior Renovation | 11 | ORIGINAL EQUIP & FURNISHING | May 2026 | May 2026 | May 2028 | Jun 2028
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WLSHC | Williamsburg Health Center Interior Renovation | 12 | SUBSTANTIAL COMPLETION | May 2026 | May 2026 | May 2028 | Jun 2028
20231026 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WLSHC | Williamsburg Health Center Interior Renovation | 13 | PUNCHLIST COMPLETE, JOB CLOSED | May 2026 | Jun 2026 | May 2028 | Jun 2028
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22200601 | ENY: CAPITAL IMPROVEMENTS | 1 | DESIGN | Jan 2008 | Jan 2009 | Jun 1993 | Jun 2020
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22200601 | ENY: CAPITAL IMPROVEMENTS | 2 | CONSTRUCTION | Jan 2009 | Jan 2012 | Jun 2020 | Jun 2033
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22200601 | ENY: CAPITAL IMPROVEMENTS | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2012 | Mar 2012 | Jun 2033 | Aug 2033
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22200801 | ENY RENOVATE THIRD FLOOR CLINICAL AREAS | 1 | DESIGN | Aug 2008 | Jun 2009 | Feb 2008 | Jun 2009
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22200801 | ENY RENOVATE THIRD FLOOR CLINICAL AREAS | 2 | CONSTRUCTION | Jul 2009 | Jun 2010 | Feb 2008 | Jun 2009
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22200801 | ENY RENOVATE THIRD FLOOR CLINICAL AREAS | 3 | CONSTRUCTION | Jul 2009 | Jun 2010 | Jul 2009 | Jun 2033
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22201610 | RENOVATE BROWNSVILLE CHILD HEALTH CLINIC | 1 | DESIGN | Aug 2017 | Jun 2018 | Aug 2013 | Jun 2014
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22201610 | RENOVATE BROWNSVILLE CHILD HEALTH CLINIC | 2 | CONSTRUCTION | Jul 2018 | Jun 2019 | Aug 2013 | Jun 2014
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22201610 | RENOVATE BROWNSVILLE CHILD HEALTH CLINIC | 3 | CONSTRUCTION | Jul 2018 | Jun 2019 | Jul 2014 | May 2033
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22201611 | RENOVATE CROWN HEIGHTS CHILD HEALTH CLINIC | 1 | DESIGN | Dec 2015 | Jun 2016 | Jan 2000 | May 2017
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22201611 | RENOVATE CROWN HEIGHTS CHILD HEALTH CLINIC | 2 | CONSTRUCTION | Jun 2016 | Nov 2016 | May 2017 | May 2033
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22201901 | ENY: MODERNIZE 2 PASSENGER ELEVATORS | 1 | DESIGN | Jul 2019 | Jan 2020 | Jul 2019 | Nov 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22201901 | ENY: MODERNIZE 2 PASSENGER ELEVATORS | 2 | CONSTRUCTION | Jan 2020 | Jun 2020 | Nov 2023 | Apr 2028
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22202001 | ENY WATER SYSTEM STRUCTURAL RESTORATION | 1 | DESIGN | Apr 2020 | Sep 2021 | Jun 2011 | Jun 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22202001 | ENY WATER SYSTEM STRUCTURAL RESTORATION | 2 | CONSTRUCTION | Sep 2021 | Sep 2023 | Jun 2023 | Jun 2025
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22202001 | ENY WATER SYSTEM STRUCTURAL RESTORATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Dec 2023 | Jun 2025 | Mar 2034
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22202201 | ENY: BATHROOM ADA | 1 | DESIGN | Jun 2022 | Oct 2023 | Jun 2020 | Oct 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22202201 | ENY: BATHROOM ADA | 2 | CONSTRUCTION | Oct 2023 | Oct 2025 | Oct 2023 | Oct 2025
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22202201 | ENY: BATHROOM ADA | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22202202 | EAST NEW YORK WATER INFILTRATION | 1 | DESIGN | Jun 2021 | Nov 2022 | Jun 2022 | Nov 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22202202 | EAST NEW YORK WATER INFILTRATION | 2 | CONSTRUCTION | Nov 2022 | Nov 2025 | Nov 2023 | Nov 2026
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22202202 | EAST NEW YORK WATER INFILTRATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2025 | Feb 2026 | Nov 2026 | Feb 2027
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22202203 | ENY: Generator Replacement | 1 | DESIGN | Jun 2022 | Nov 2023 | Jun 2022 | Nov 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22202203 | ENY: Generator Replacement | 2 | CONSTRUCTION | Nov 2023 | Nov 2025 | Nov 2023 | Nov 2025
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22202203 | ENY: Generator Replacement | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2025 | Feb 2026 | Nov 2025 | Jun 2032
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22202301 | ENY: Install DCV and upgrade BMS System | 1 | DESIGN | Jun 2022 | Nov 2023 | Jun 2024 | Jun 2033
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22202301 | ENY: Install DCV and upgrade BMS System | 2 | CONSTRUCTION | Nov 2023 | Nov 2025 | Jun 2033 | Jun 2035
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22202301 | ENY: Install DCV and upgrade BMS System | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2025 | Feb 2026 | Jun 2035 | Aug 2035
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22202302 | ENY: Bolier Replacement | 1 | DESIGN | Jun 2022 | Nov 2023 | Jun 2022 | Nov 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22202302 | ENY: Bolier Replacement | 2 | CONSTRUCTION | Nov 2023 | Nov 2025 | Nov 2023 | Nov 2025
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22202302 | ENY: Bolier Replacement | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2025 | Feb 2026 | Nov 2025 | Jun 2032
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22202304 | ENY: Lighting Upgrades | 1 | DESIGN | Jun 2022 | Nov 2023 | Jun 2022 | Nov 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22202304 | ENY: Lighting Upgrades | 2 | CONSTRUCTION | Nov 2023 | Nov 2025 | Nov 2023 | Nov 2025
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22202304 | ENY: Lighting Upgrades | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2025 | Feb 2026 | Nov 2025 | Feb 2026
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22202401 | ENY GOTHAM HEALTH PHARMACY--PHARMACY - WAITING AREA UPGRADE | 1 | DESIGN | Oct 2023 | Apr 2024 | Oct 2023 | Apr 2024
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22202401 | ENY GOTHAM HEALTH PHARMACY--PHARMACY - WAITING AREA UPGRADE | 2 | CONSTRUCTION | Apr 2024 | Sep 2024 | Apr 2024 | Sep 2024
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 23202001 | MCKINNEY FRONT LOBBY RENOVATIONS | 1 | DESIGN | Sep 2020 | Feb 2022 | Sep 2020 | Jun 2032
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 23202001 | MCKINNEY FRONT LOBBY RENOVATIONS | 2 | CONSTRUCTION | Feb 2022 | Feb 2025 | Jun 2032 | Jul 2035
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 23202001 | MCKINNEY FRONT LOBBY RENOVATIONS | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | May 2025 | Jul 2035 | Oct 2035
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 23202101 | MCKINNEY: FIRE ALARM | 1 | DESIGN | Feb 2021 | Jun 2022 | Feb 2021 | Jun 2022
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 23202101 | MCKINNEY: FIRE ALARM | 2 | CONSTRUCTION | Jun 2022 | Jun 2025 | Jun 2022 | Jun 2025
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 23202101 | MCKINNEY: FIRE ALARM | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26201101 | GOTHAM: CONSTRUCT VANDERBILT AVENUE HEALTH CENTER AT S.I. | 1 | DESIGN | May 2009 | Oct 2010 | Sep 2002 | May 2020
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26201101 | GOTHAM: CONSTRUCT VANDERBILT AVENUE HEALTH CENTER AT S.I. | 2 | CONSTRUCTION | Oct 2010 | Oct 2012 | May 2020 | Apr 2033
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26201101 | GOTHAM: CONSTRUCT VANDERBILT AVENUE HEALTH CENTER AT S.I. | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2012 | Dec 2012 | May 2033 | Jul 2033
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26201402 | CONEY ADD DEHUMIDICATION & ADD'L COOLING CAPACITY TO THE ORs | 1 | DESIGN | May 2014 | Nov 2014 | Nov 1996 | Jun 2015
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26201402 | CONEY ADD DEHUMIDICATION & ADD'L COOLING CAPACITY TO THE ORs | 2 | CONSTRUCTION | Nov 2014 | Apr 2015 | Jun 2015 | Jan 2033
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26201902 | CONEY UPGRADE FIRE ALARM SYSTEM | 1 | DESIGN | Jul 2019 | Jan 2020 | Apr 2033 | Jun 2033
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26201902 | CONEY UPGRADE FIRE ALARM SYSTEM | 2 | CONSTRUCTION | Jan 2020 | Jun 2020 | Jun 2033 | Nov 2033
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26202001 | CONEY MODERNIZE 9 ELEVATORS IN MAIN BUILDING | 1 | DESIGN | Sep 2020 | Feb 2022 | Feb 2021 | Jun 2032
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26202001 | CONEY MODERNIZE 9 ELEVATORS IN MAIN BUILDING | 2 | CONSTRUCTION | Feb 2022 | Feb 2025 | Jun 2032 | Mar 2039
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26202001 | CONEY MODERNIZE 9 ELEVATORS IN MAIN BUILDING | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | May 2025 | Mar 2039 | Jun 2039
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26202101 | CONEY ROOF REPLACEMENT MAIN BUILDING | 1 | DESIGN | Feb 2021 | Jun 2022 | Nov 2023 | Mar 2025
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26202101 | CONEY ROOF REPLACEMENT MAIN BUILDING | 2 | CONSTRUCTION | Jun 2022 | Jun 2025 | Mar 2025 | Mar 2028
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26202101 | CONEY ROOF REPLACEMENT MAIN BUILDING | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2025 | Sep 2025 | Mar 2028 | Jun 2028
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26202103 | CONEY DENTAL SUITE | 1 | DESIGN | Jun 2021 | Oct 2022 | Jun 2021 | Oct 2022
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26202103 | CONEY DENTAL SUITE | 2 | CONSTRUCTION | Oct 2022 | Oct 2025 | Oct 2022 | Oct 2025
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26202103 | CONEY DENTAL SUITE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26202104 | CONEY ISLAND AMBULATORY CARE CENTER | 1 | DESIGN | Jun 2021 | Oct 2022 | Jun 2021 | Oct 2022
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26202104 | CONEY ISLAND AMBULATORY CARE CENTER | 2 | CONSTRUCTION | Oct 2022 | Oct 2025 | Oct 2022 | Oct 2025
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26202104 | CONEY ISLAND AMBULATORY CARE CENTER | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26202201 | NYC H&H CONEY ISLAND HOSPITAL - INTEGRATED WOMEN'S HEALTH | 1 | DESIGN | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26202201 | NYC H&H CONEY ISLAND HOSPITAL - INTEGRATED WOMEN'S HEALTH | 2 | CONSTRUCTION | Dec 2022 | Jun 2023 | Jan 2023 | Jul 2026
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26202301 | CONEY ISLAND: Roof Renovation, patrol car, recording system | 1 | DESIGN | Sep 2022 | Mar 2023 | Sep 2022 | Mar 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26202301 | CONEY ISLAND: Roof Renovation, patrol car, recording system | 2 | CONSTRUCTION | Mar 2023 | Sep 2024 | Mar 2023 | Sep 2024
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201201 | CUMBERLAND: RENOVATE CHEMICAL DEPENDENCY DEPARTMENT | 1 | DESIGN | Jul 2019 | Jan 2020 | Jul 2019 | Jan 2020
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201201 | CUMBERLAND: RENOVATE CHEMICAL DEPENDENCY DEPARTMENT | 2 | CONSTRUCTION | Jan 2020 | Jun 2020 | Jan 2020 | Jun 2032
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201301 | CUMBERLAND: RENOVATE PEDIATRIC PRACTICE DEPARTMENT | 1 | DESIGN | Jul 2019 | Jan 2020 | Jun 2013 | Jun 2033
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201301 | CUMBERLAND: RENOVATE PEDIATRIC PRACTICE DEPARTMENT | 2 | CONSTRUCTION | Jan 2020 | Jun 2020 | Jun 2033 | Nov 2045
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201515 | CUMBERLAND: RENOVATE WOMEN'S HEALTH SVCS DEPT. | 1 | DESIGN | Jan 2015 | Jul 2015 | Jan 2015 | Jul 2015
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201515 | CUMBERLAND: RENOVATE WOMEN'S HEALTH SVCS DEPT. | 2 | CONSTRUCTION | Jul 2015 | Dec 2015 | Jul 2015 | Jun 2032
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201610 | RENOVATE BEDFORD HEALTH CLINIC | 1 | DESIGN | Aug 2017 | Jun 2018 | May 2016 | Jun 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201610 | RENOVATE BEDFORD HEALTH CLINIC | 2 | CONSTRUCTION | Jul 2018 | Jun 2019 | May 2016 | Jun 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201610 | RENOVATE BEDFORD HEALTH CLINIC | 3 | CONSTRUCTION | Jul 2018 | Jun 2019 | Jun 2023 | Jun 2037
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201702 | CUMBERLAND: CONSTRUCT NEW DENTAL FACILITY | 1 | DESIGN | Jul 2019 | Jan 2020 | Jul 2019 | Jan 2020
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201702 | CUMBERLAND: CONSTRUCT NEW DENTAL FACILITY | 2 | CONSTRUCTION | Jan 2020 | Jun 2020 | Jan 2020 | Jun 2032
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201802 | CUMBERLAND: BEHAIVORAL HEALTH INTEGRATION INTO PRIMARY CARE | 1 | DESIGN | Aug 2019 | Jun 2032 | Aug 2019 | Jun 2032
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201802 | CUMBERLAND: BEHAIVORAL HEALTH INTEGRATION INTO PRIMARY CARE | 2 | CONSTRUCTION | Jun 2032 | Jun 2034 | Jun 2032 | Jun 2034
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201802 | CUMBERLAND: BEHAIVORAL HEALTH INTEGRATION INTO PRIMARY CARE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2034 | Aug 2034 | Jun 2034 | Aug 2034
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201803 | CUMBERLAND: FACADE REHABILITATION BUILDING B & C | 1 | DESIGN | Aug 2019 | Jun 2020 | Aug 2019 | Jun 2032
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201803 | CUMBERLAND: FACADE REHABILITATION BUILDING B & C | 2 | CONSTRUCTION | Jul 2020 | Jun 2021 | Aug 2019 | Jun 2032
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201803 | CUMBERLAND: FACADE REHABILITATION BUILDING B & C | 3 | CONSTRUCTION | Jul 2020 | Jun 2021 | Jul 2032 | Jun 2040
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201610 | KCHC: LOCAL LAW -11 COMPLIANCE - BLDG T | 1 | DESIGN | Aug 2017 | Jun 2018 | Aug 2018 | Jun 2019
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201610 | KCHC: LOCAL LAW -11 COMPLIANCE - BLDG T | 2 | CONSTRUCTION | Jul 2018 | Jun 2019 | Aug 2018 | Jun 2019
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201610 | KCHC: LOCAL LAW -11 COMPLIANCE - BLDG T | 3 | CONSTRUCTION | Jul 2018 | Jun 2019 | Jul 2019 | Jan 2024
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201612 | KCHC: BLDG "P" FACADE REMEDIATION - LOCAL LAW 11 COMPLIANCE | 1 | DESIGN | Aug 2019 | Jun 2020 | Aug 2019 | Jun 2020
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201612 | KCHC: BLDG "P" FACADE REMEDIATION - LOCAL LAW 11 COMPLIANCE | 2 | CONSTRUCTION | Jul 2020 | Jun 2021 | Aug 2019 | Jun 2020
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201612 | KCHC: BLDG "P" FACADE REMEDIATION - LOCAL LAW 11 COMPLIANCE | 3 | CONSTRUCTION | Jul 2020 | Jun 2021 | Jul 2020 | Jun 2025
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201614 | KINGS BOILER REPLACEMENT | 1 | DESIGN | Aug 2018 | Jul 2019 | Aug 2018 | Jul 2019
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201614 | KINGS BOILER REPLACEMENT | 2 | CONSTRUCTION | Jul 2019 | Jun 2020 | Aug 2018 | Jul 2019
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201614 | KINGS BOILER REPLACEMENT | 3 | CONSTRUCTION | Jul 2019 | Jun 2020 | Jul 2019 | Jun 2032
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201801 | KINGS: Express Care (CRFP) | 1 | DESIGN | Sep 2022 | Feb 2024 | Sep 2022 | Feb 2024
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201801 | KINGS: Express Care (CRFP) | 2 | CONSTRUCTION | Feb 2024 | Feb 2027 | Feb 2024 | Feb 2027
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201801 | KINGS: Express Care (CRFP) | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2027 | May 2027 | Feb 2027 | May 2027
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201802 | KCHC: REPLACEMENT OF C6 HEMODIALYSIS WATER TREATMENT SYSTEM | 1 | DESIGN | Mar 2021 | Jul 2022 | Oct 2018 | Jun 2032
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201802 | KCHC: REPLACEMENT OF C6 HEMODIALYSIS WATER TREATMENT SYSTEM | 2 | CONSTRUCTION | Jul 2022 | Jul 2025 | Jul 2032 | Jun 2038
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201802 | KCHC: REPLACEMENT OF C6 HEMODIALYSIS WATER TREATMENT SYSTEM | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Oct 2025 | Jun 2038 | Sep 2038
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202001 | KINGS REHABILITATE STEAM TUNNEL UNDER WINTHROP STREET | 1 | DESIGN | Sep 2020 | Feb 2022 | Sep 2020 | Feb 2022
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202001 | KINGS REHABILITATE STEAM TUNNEL UNDER WINTHROP STREET | 2 | CONSTRUCTION | Feb 2022 | Feb 2025 | Mar 2022 | Feb 2025
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202001 | KINGS REHABILITATE STEAM TUNNEL UNDER WINTHROP STREET | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202101 | KINGS RESTORATION OF WEST SMOKE STACK | 1 | DESIGN | May 2020 | Sep 2021 | Jun 2024 | Jun 2032
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202101 | KINGS RESTORATION OF WEST SMOKE STACK | 2 | CONSTRUCTION | Sep 2021 | Sep 2023 | Jul 2032 | Jun 2036
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202101 | KINGS RESTORATION OF WEST SMOKE STACK | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Dec 2023 | Jul 2036 | Sep 2036
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202102 | KINGS: WELLNESS CENTER | 1 | DESIGN | May 2020 | Sep 2021 | Oct 2022 | Jun 2032
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202102 | KINGS: WELLNESS CENTER | 2 | CONSTRUCTION | Sep 2021 | Sep 2023 | Jul 2032 | Jun 2036
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202102 | KINGS: WELLNESS CENTER | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Dec 2023 | Jul 2036 | Sep 2036
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202103 | KINGS P BUILDING MORGUE | 1 | DESIGN | May 2020 | Sep 2021 | Oct 2020 | Jun 2032
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202103 | KINGS P BUILDING MORGUE | 2 | CONSTRUCTION | Sep 2021 | Sep 2023 | Jul 2032 | Jun 2034
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202103 | KINGS P BUILDING MORGUE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Dec 2023 | Jul 2034 | Sep 2038
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202104 | KINGS BUILDING D ELECTRICAL UPGRADES | 1 | DESIGN | May 2020 | Sep 2021 | May 2020 | Sep 2021
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202104 | KINGS BUILDING D ELECTRICAL UPGRADES | 2 | CONSTRUCTION | Sep 2021 | Sep 2023 | Sep 2021 | Jun 2026
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202104 | KINGS BUILDING D ELECTRICAL UPGRADES | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Dec 2023 | Jul 2026 | Sep 2028
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202105 | KINGS: BlLDG S WATER BALANCING | 1 | DESIGN | May 2020 | Sep 2021 | May 2020 | Sep 2021
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202105 | KINGS: BlLDG S WATER BALANCING | 2 | CONSTRUCTION | Sep 2021 | Sep 2023 | Oct 2021 | Sep 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202105 | KINGS: BlLDG S WATER BALANCING | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Dec 2023 | Oct 2023 | Dec 2027
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202111 | KINGS: CATH LAB CONVERSION TO OR | 1 | DESIGN | Jul 2022 | Nov 2023 | Jul 2022 | Nov 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202111 | KINGS: CATH LAB CONVERSION TO OR | 2 | CONSTRUCTION | Nov 2023 | Nov 2025 | Nov 2023 | Nov 2025
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202111 | KINGS: CATH LAB CONVERSION TO OR | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2025 | Feb 2026 | Nov 2025 | Feb 2026
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202114 | KINGS PHARMACY COMPOUNDING USP 797/800 COMPLIANCE | 1 | DESIGN | Jan 2021 | May 2022 | Jan 2021 | May 2022
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202114 | KINGS PHARMACY COMPOUNDING USP 797/800 COMPLIANCE | 2 | CONSTRUCTION | May 2022 | May 2024 | Jun 2022 | May 2024
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202114 | KINGS PHARMACY COMPOUNDING USP 797/800 COMPLIANCE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Aug 2024 | May 2024 | Aug 2024
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202201 | Kings Replacement of Water Feeder Pipes for the Boilers Oper | 1 | DESIGN | Jul 2021 | Nov 2022 | Jul 2021 | Nov 2022
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202201 | Kings Replacement of Water Feeder Pipes for the Boilers Oper | 2 | CONSTRUCTION | Nov 2022 | Nov 2024 | Dec 2022 | Nov 2024
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202201 | Kings Replacement of Water Feeder Pipes for the Boilers Oper | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2024 | Feb 2025 | Nov 2024 | Feb 2025
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202203 | KINGS: E BLDG ELEVATOR MODERNIZATION | 1 | DESIGN | Jun 2021 | Nov 2022 | Jun 2021 | Nov 2022
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202203 | KINGS: E BLDG ELEVATOR MODERNIZATION | 2 | CONSTRUCTION | Nov 2022 | Nov 2025 | Nov 2022 | Nov 2025
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202203 | KINGS: E BLDG ELEVATOR MODERNIZATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2025 | Feb 2026 | Nov 2025 | Feb 2026
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202204 | NYC H&H KINGS COUNTY - MOTHER-BABY/NICU RENOVATION: RENOVAT | 1 | DESIGN | Jul 2022 | May 2023 | Jun 2024 | May 2025
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202204 | NYC H&H KINGS COUNTY - MOTHER-BABY/NICU RENOVATION: RENOVAT | 2 | CONSTRUCTION | May 2023 | May 2024 | Jun 2024 | May 2025
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202204 | NYC H&H KINGS COUNTY - MOTHER-BABY/NICU RENOVATION: RENOVAT | 3 | CONSTRUCTION | May 2023 | May 2024 | May 2025 | May 2027
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202205 | Kings Demolition of pedestrian bridge btwn buildings P & K | 1 | DESIGN | Jul 2023 | Nov 2024 | Jul 2023 | Nov 2024
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202205 | Kings Demolition of pedestrian bridge btwn buildings P & K | 2 | CONSTRUCTION | Nov 2024 | Nov 2026 | Nov 2024 | Nov 2026
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202205 | Kings Demolition of pedestrian bridge btwn buildings P & K | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2023 | Feb 2026 | Nov 2023 | Feb 2026
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202302 | KINGS: ROOF REPLACEMENT- CENTRALIZED KITCHEN BLDG | 1 | DESIGN | May 2023 | Nov 2023 | May 2023 | Nov 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202302 | KINGS: ROOF REPLACEMENT- CENTRALIZED KITCHEN BLDG | 2 | CONSTRUCTION | Nov 2023 | Apr 2024 | Nov 2023 | Apr 2024
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202303 | KINGS: Dental Practice Renovation E-BLDG | 1 | DESIGN | Jun 2023 | Jun 2032 | Jun 2023 | Jun 2032
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202303 | KINGS: Dental Practice Renovation E-BLDG | 2 | CONSTRUCTION | Jul 2032 | Dec 2032 | Jul 2032 | Dec 2032
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202443 | KINGS COUNTY LINAC MACHINE--PURCHASE OF A REPLACEMENT LINAC | 1 | DESIGN | May 2005 | Nov 2005 | May 2005 | Nov 2005
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202443 | KINGS COUNTY LINAC MACHINE--PURCHASE OF A REPLACEMENT LINAC | 2 | CONSTRUCTION | Nov 2005 | Apr 2026 | Nov 2005 | Apr 2026
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48200803 | WOODHULL: OB UNIT EXPANSION | 1 | DESIGN | Apr 2013 | Feb 2014 | Apr 2017 | Feb 2018
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48200803 | WOODHULL: OB UNIT EXPANSION | 2 | CONSTRUCTION | Mar 2014 | Feb 2015 | Apr 2017 | Feb 2018
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48200803 | WOODHULL: OB UNIT EXPANSION | 3 | CONSTRUCTION | Mar 2014 | Feb 2015 | Mar 2018 | Jun 2032
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201402 | WOODHULL: ESTABLISH CPEP | 1 | DESIGN | Jun 2013 | Dec 2013 | Jul 2015 | Jan 2016
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201402 | WOODHULL: ESTABLISH CPEP | 2 | CONSTRUCTION | Dec 2013 | May 2014 | Jan 2016 | Jun 2032
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201505 | WOODHULL: INSTALL PERMANENT EMERGENCY POWER FEEDER | 3 | CONSTRUCTION | Jan 2017 | Dec 2017 | Jan 2017 | Dec 2017
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201515 | WOODHULL: RENOVATE WOMEN'S HEALTH SVCS - RADIOLOGY | 2 | CONSTRUCTION | Jul 2015 | Dec 2015 | Jul 2015 | Dec 2015
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201516 | WOODHULL: AMBULATORY CARE RENOVATIONS (8-300) | 1 | DESIGN | Jan 2015 | Jul 2015 | Jan 2021 | Jul 2021
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201516 | WOODHULL: AMBULATORY CARE RENOVATIONS (8-300) | 2 | CONSTRUCTION | Jul 2015 | Dec 2015 | Jul 2021 | Jun 2032
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201602 | WOODHULL: LOCAL LAW 11 COMPLIANCE | 1 | DESIGN | Aug 2019 | Jun 2020 | Aug 2019 | Jun 2033
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201602 | WOODHULL: LOCAL LAW 11 COMPLIANCE | 2 | CONSTRUCTION | Jul 2020 | Jun 2021 | Aug 2019 | Jun 2033
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201602 | WOODHULL: LOCAL LAW 11 COMPLIANCE | 3 | CONSTRUCTION | Jul 2020 | Jun 2021 | Jul 2033 | Jul 2042
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201610 | RENOVATE BUSHWICK COMMUNICARE | 1 | DESIGN | Dec 2015 | Jun 2016 | Jan 2016 | May 2033
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201610 | RENOVATE BUSHWICK COMMUNICARE | 2 | CONSTRUCTION | Jun 2016 | Nov 2016 | Jun 2033 | Jun 2048
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201801 | WOODHULL: REPLACE MAIN SERVICE SWITCHES FOR ATS 1, 2 AND 5 | 1 | DESIGN | May 2018 | Oct 2019 | May 2018 | Oct 2019
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201801 | WOODHULL: REPLACE MAIN SERVICE SWITCHES FOR ATS 1, 2 AND 5 | 2 | CONSTRUCTION | Oct 2019 | Oct 2022 | Oct 2019 | Oct 2022
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201801 | WOODHULL: REPLACE MAIN SERVICE SWITCHES FOR ATS 1, 2 AND 5 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201901 | WOODHULL: CPEP RENOVATION | 1 | DESIGN | Jan 2019 | Jul 2019 | Jan 2024 | Jul 2024
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201901 | WOODHULL: CPEP RENOVATION | 2 | CONSTRUCTION | Jul 2019 | Dec 2019 | Jul 2024 | Jun 2032
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201902 | WOODHULL: EMERGENCY DEPARTMENT RENOVATION | 1 | DESIGN | Aug 2018 | Jul 2019 | Aug 2022 | Jul 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201902 | WOODHULL: EMERGENCY DEPARTMENT RENOVATION | 2 | CONSTRUCTION | Jul 2019 | Jun 2020 | Aug 2022 | Jul 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201902 | WOODHULL: EMERGENCY DEPARTMENT RENOVATION | 3 | CONSTRUCTION | Jul 2019 | Jun 2020 | Jul 2023 | Jun 2032
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201903 | WOODHULL: RETAIL PHARMACY RENOVATION | 1 | DESIGN | May 2019 | Oct 2020 | Apr 2027 | Jun 2032
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201903 | WOODHULL: RETAIL PHARMACY RENOVATION | 2 | CONSTRUCTION | Oct 2020 | Oct 2023 | Jul 2032 | Aug 2032
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201903 | WOODHULL: RETAIL PHARMACY RENOVATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2023 | Jan 2024 | Aug 2032 | Nov 2032
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202002 | WOODHULL: Modernize Elevators | 1 | DESIGN | May 2020 | Oct 2021 | May 2020 | Oct 2021
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202002 | WOODHULL: Modernize Elevators | 2 | CONSTRUCTION | Oct 2021 | Oct 2024 | Nov 2021 | Oct 2024
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202002 | WOODHULL: Modernize Elevators | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202003 | WOODHULL: Dinex Buildout and Installation | 1 | DESIGN | May 2020 | Oct 2021 | Feb 2021 | Jun 2032
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202003 | WOODHULL: Dinex Buildout and Installation | 2 | CONSTRUCTION | Oct 2021 | Oct 2024 | Jul 2032 | Jun 2035
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202003 | WOODHULL: Dinex Buildout and Installation | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2024 | Jan 2025 | Jul 2035 | Sep 2035
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202101 | WOODHULL: COMMAND CENTER MODERNIZATION | 1 | DESIGN | May 2020 | Sep 2021 | May 2020 | Sep 2021
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202101 | WOODHULL: COMMAND CENTER MODERNIZATION | 2 | CONSTRUCTION | Sep 2021 | Sep 2023 | Sep 2021 | Sep 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202101 | WOODHULL: COMMAND CENTER MODERNIZATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Dec 2023 | Sep 2023 | Jun 2027
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202106 | WOODHULL GENERATOR REPLACEMENT | 1 | DESIGN | May 2020 | Sep 2021 | May 2022 | Sep 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202106 | WOODHULL GENERATOR REPLACEMENT | 2 | CONSTRUCTION | Sep 2021 | Sep 2023 | Sep 2023 | Sep 2025
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202106 | WOODHULL GENERATOR REPLACEMENT | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Dec 2024 | Sep 2025 | Dec 2026
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202107 | WOODHULL OIL SPILL REMEDIATION | 1 | DESIGN | May 2021 | Sep 2022 | May 2021 | Sep 2022
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202107 | WOODHULL OIL SPILL REMEDIATION | 2 | CONSTRUCTION | Sep 2022 | Sep 2024 | Sep 2022 | Sep 2024
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202107 | WOODHULL OIL SPILL REMEDIATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202108 | WOODHULL DECANTING/RELOCATION (CHS OTxHU) | 1 | DESIGN | May 2020 | Sep 2021 | May 2020 | Sep 2021
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202108 | WOODHULL DECANTING/RELOCATION (CHS OTxHU) | 2 | CONSTRUCTION | Sep 2021 | Sep 2023 | Oct 2021 | Sep 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202108 | WOODHULL DECANTING/RELOCATION (CHS OTxHU) | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Dec 2023 | Oct 2023 | Dec 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202201 | WOODHULL: NEW WOMEN'S HEALTH PAVILLION (7-300) | 1 | DESIGN | May 2021 | Sep 2022 | May 2021 | Sep 2022
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202201 | WOODHULL: NEW WOMEN'S HEALTH PAVILLION (7-300) | 2 | CONSTRUCTION | Sep 2022 | Sep 2024 | Sep 2022 | Sep 2024
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202201 | WOODHULL: NEW WOMEN'S HEALTH PAVILLION (7-300) | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202202 | WOODHULL INTERVENTIONAL RADIOLOGY- SPECIAL PROCEDURE UNIT | 1 | DESIGN | Jun 2021 | Nov 2022 | Jun 2021 | Nov 2022
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202202 | WOODHULL INTERVENTIONAL RADIOLOGY- SPECIAL PROCEDURE UNIT | 2 | CONSTRUCTION | Nov 2022 | Nov 2025 | Nov 2022 | Nov 2025
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202202 | WOODHULL INTERVENTIONAL RADIOLOGY- SPECIAL PROCEDURE UNIT | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2025 | Feb 2026 | Nov 2025 | Feb 2026
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202203 | WOODHULL: OTXHU FULL ROOF REPLACEMENT | 1 | DESIGN | Jun 2021 | Nov 2022 | Jun 2021 | Nov 2022
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202203 | WOODHULL: OTXHU FULL ROOF REPLACEMENT | 2 | CONSTRUCTION | Nov 2022 | Nov 2025 | Nov 2022 | Nov 2025
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202203 | WOODHULL: OTXHU FULL ROOF REPLACEMENT | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2025 | Feb 2026 | Nov 2025 | Feb 2026
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202205 | WOODHULL OUTPOSTED THERAPEUTIC UNITS (CHS OTxHU) | 1 | DESIGN | Jun 2022 | Nov 2023 | Jun 2022 | Nov 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202205 | WOODHULL OUTPOSTED THERAPEUTIC UNITS (CHS OTxHU) | 2 | CONSTRUCTION | Nov 2023 | Nov 2026 | Nov 2023 | Nov 2026
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202205 | WOODHULL OUTPOSTED THERAPEUTIC UNITS (CHS OTxHU) | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Feb 2027 | Nov 2026 | Feb 2027
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202206 | NYC H&H WOODHULL HOSPITAL - LABOR & BIRTHING SUITE RENOVATIO | 1 | DESIGN | Jul 2022 | May 2023 | Jul 2023 | May 2024
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202206 | NYC H&H WOODHULL HOSPITAL - LABOR & BIRTHING SUITE RENOVATIO | 2 | CONSTRUCTION | May 2023 | May 2024 | Jul 2023 | May 2024
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202206 | NYC H&H WOODHULL HOSPITAL - LABOR & BIRTHING SUITE RENOVATIO | 3 | CONSTRUCTION | May 2023 | May 2024 | May 2024 | May 2026
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202207 | WOODHULL: FIRE ALARM SYSTEM UPGRADES | 1 | DESIGN | Jun 2022 | Nov 2023 | Jun 2022 | Nov 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202207 | WOODHULL: FIRE ALARM SYSTEM UPGRADES | 2 | CONSTRUCTION | Nov 2023 | Nov 2026 | Nov 2023 | Nov 2026
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202207 | WOODHULL: FIRE ALARM SYSTEM UPGRADES | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Feb 2027 | Nov 2026 | Feb 2027
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202208 | WOODHULL: Boiler Plant Replacment | 1 | DESIGN | Aug 2022 | Jan 2024 | Aug 2022 | Jan 2024
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202208 | WOODHULL: Boiler Plant Replacment | 2 | CONSTRUCTION | Jan 2024 | Jan 2027 | Jan 2024 | Jan 2027
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202208 | WOODHULL: Boiler Plant Replacment | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2027 | Apr 2027 | Jan 2027 | Apr 2027
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202209 | WOODHULL: EES UPGRADES | 1 | DESIGN | Aug 2022 | Jan 2024 | Aug 2022 | Jan 2024
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202209 | WOODHULL: EES UPGRADES | 2 | CONSTRUCTION | Jan 2024 | Jan 2027 | Jan 2024 | Jan 2027
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202209 | WOODHULL: EES UPGRADES | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2027 | Apr 2027 | Jan 2027 | Apr 2027
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202301 | Woodhull: Demolition of 3 Cooling Towers | 1 | DESIGN | Jul 2023 | Dec 2023 | Jul 2023 | Dec 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202301 | Woodhull: Demolition of 3 Cooling Towers | 2 | CONSTRUCTION | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2025
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC407 | Cumberland : Boiler Plant Replacement | 1 | DESIGN | May 2017 | Oct 2018 | May 2017 | Oct 2018
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC407 | Cumberland : Boiler Plant Replacement | 2 | CONSTRUCTION | Oct 2018 | Oct 2021 | Nov 2018 | Oct 2021
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC407 | Cumberland : Boiler Plant Replacement | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC607 | KINGS LIGHTING UPGRADES - PHASE 2 | 1 | DESIGN | Aug 2019 | Jun 2020 | Aug 2021 | Jul 2022
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC607 | KINGS LIGHTING UPGRADES - PHASE 2 | 2 | CONSTRUCTION | Jul 2020 | Jun 2021 | Aug 2021 | Jul 2022
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC607 | KINGS LIGHTING UPGRADES - PHASE 2 | 3 | CONSTRUCTION | Jul 2020 | Jun 2021 | Jul 2022 | Jun 2025
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | GABIHHC | GROUP ATTACHMENT BASED INTERVENTION | 1 | DESIGN | Jan 2019 | Mar 2019 | Jan 2019 | Mar 2019
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | GABIHHC | GROUP ATTACHMENT BASED INTERVENTION | 2 | CONSTRUCTION | Apr 2019 | Mar 2020 | Apr 2019 | Jun 2024
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | TKYHHC907 | Woodhull 5th Floor Roof Replacement, Bond+ Cap | 1 | DEVELOP SCOPE | Jun 2022 | Jul 2022 | Jul 2023 | Jul 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | TKYHHC907 | Woodhull 5th Floor Roof Replacement, Bond+ Cap | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Jan 2023 | Jul 2023 | Feb 2024
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | TKYHHC907 | Woodhull 5th Floor Roof Replacement, Bond+ Cap | 3 | CONSTRUCTION TO 50% | Feb 2023 | Jul 2023 | Feb 2024 | Jul 2024
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | TKYHHC907 | Woodhull 5th Floor Roof Replacement, Bond+ Cap | 4 | CONSTRUCTION TO 75% | Jul 2023 | Oct 2023 | Jul 2024 | Oct 2024
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | TKYHHC907 | Woodhull 5th Floor Roof Replacement, Bond+ Cap | 5 | SUBSTANTIAL COMPLETION | Oct 2023 | Dec 2023 | Oct 2024 | Dec 2024
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | TKYHHC907 | Woodhull 5th Floor Roof Replacement, Bond+ Cap | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jan 2024 | Dec 2024 | Jan 2025
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | TKYHHC908 | HHC - McKinney Nursing Center Comp Energy Upgrade | 1 | DEVELOP SCOPE | Jun 2022 | Jul 2022 | Jun 2022 | Jul 2022
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | TKYHHC908 | HHC - McKinney Nursing Center Comp Energy Upgrade | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Jan 2023 | Jul 2022 | Jan 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | TKYHHC908 | HHC - McKinney Nursing Center Comp Energy Upgrade | 3 | CONSTRUCTION TO 50% | Feb 2023 | Jul 2023 | Feb 2023 | Jul 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | TKYHHC908 | HHC - McKinney Nursing Center Comp Energy Upgrade | 4 | CONSTRUCTION TO 75% | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | TKYHHC908 | HHC - McKinney Nursing Center Comp Energy Upgrade | 5 | SUBSTANTIAL COMPLETION | Oct 2023 | Dec 2023 | Oct 2023 | Dec 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | TKYHHC908 | HHC - McKinney Nursing Center Comp Energy Upgrade | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jan 2024 | Dec 2023 | Jan 2024
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | TKYHHC910 | HHC - Kings County D Building BMS Upgrade | 1 | DEVELOP SCOPE | Jun 2022 | Jul 2022 | Jun 2022 | Jul 2022
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | TKYHHC910 | HHC - Kings County D Building BMS Upgrade | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Jan 2023 | Aug 2022 | Feb 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | TKYHHC910 | HHC - Kings County D Building BMS Upgrade | 3 | CONSTRUCTION TO 50% | Feb 2023 | Jul 2023 | Feb 2023 | Aug 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | TKYHHC910 | HHC - Kings County D Building BMS Upgrade | 4 | CONSTRUCTION TO 75% | Jul 2023 | Oct 2023 | Aug 2023 | Oct 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | TKYHHC910 | HHC - Kings County D Building BMS Upgrade | 5 | SUBSTANTIAL COMPLETION | Oct 2023 | Dec 2023 | Oct 2023 | Dec 2023
20231026 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | TKYHHC910 | HHC - Kings County D Building BMS Upgrade | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jan 2024 | Dec 2023 | Jan 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-144-L | INSTALLATION OF (13) NEW CENTRIFUGES @ 26TH WARD WPCP | 1 | DEVELOP SCOPE | Jun 2017 | Feb 2018 | Jun 2017 | Feb 2018
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-144-L | INSTALLATION OF (13) NEW CENTRIFUGES @ 26TH WARD WPCP | 2 | PRELIMINARY DESIGN | Feb 2018 | Feb 2019 | Feb 2018 | Feb 2019
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-144-L | INSTALLATION OF (13) NEW CENTRIFUGES @ 26TH WARD WPCP | 3 | FINAL DESIGN | Feb 2019 | Aug 2020 | Feb 2019 | Aug 2020
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-144-L | INSTALLATION OF (13) NEW CENTRIFUGES @ 26TH WARD WPCP | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2020 | May 2021 | Aug 2020 | May 2021
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-144-L | INSTALLATION OF (13) NEW CENTRIFUGES @ 26TH WARD WPCP | 5 | CONSTRUCTION TO 25% | May 2021 | May 2022 | May 2021 | May 2022
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-144-L | INSTALLATION OF (13) NEW CENTRIFUGES @ 26TH WARD WPCP | 6 | CONSTRUCTION TO 50% | May 2022 | Apr 2023 | May 2022 | Apr 2023
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-144-L | INSTALLATION OF (13) NEW CENTRIFUGES @ 26TH WARD WPCP | 7 | CONSTRUCTION TO 75% | May 2023 | Apr 2024 | May 2023 | Apr 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-144-L | INSTALLATION OF (13) NEW CENTRIFUGES @ 26TH WARD WPCP | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2024 | Jan 2025 | Apr 2024 | Jan 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-144-L | INSTALLATION OF (13) NEW CENTRIFUGES @ 26TH WARD WPCP | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-144-L | INSTALLATION OF (13) NEW CENTRIFUGES @ 26TH WARD WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-148-L | TRC - CONS OF DISINFECTION FACILITIES AT 26TH WARD WPCP | 1 | FINAL DESIGN | Jun 2016 | Nov 2017 | Jun 2016 | Feb 2017
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-148-L | TRC - CONS OF DISINFECTION FACILITIES AT 26TH WARD WPCP | 2 | CONSTRUCTION TO 25% | Nov 2017 | Jul 2018 | Feb 2017 | Feb 2018
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-148-L | TRC - CONS OF DISINFECTION FACILITIES AT 26TH WARD WPCP | 3 | CONSTRUCTION TO 50% | Jul 2018 | Mar 2019 | Feb 2018 | Aug 2019
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-148-L | TRC - CONS OF DISINFECTION FACILITIES AT 26TH WARD WPCP | 4 | CONSTRUCTION TO 75% | Mar 2019 | Nov 2019 | Aug 2019 | May 2020
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-148-L | TRC - CONS OF DISINFECTION FACILITIES AT 26TH WARD WPCP | 5 | CONSTRUCTION TO 25% | Mar 2019 | Nov 2019 | May 2020 | May 2021
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-148-L | TRC - CONS OF DISINFECTION FACILITIES AT 26TH WARD WPCP | 6 | CONSTRUCTION TO 50% | Mar 2019 | Nov 2019 | May 2021 | Apr 2022
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-148-L | TRC - CONS OF DISINFECTION FACILITIES AT 26TH WARD WPCP | 7 | CONSTRUCTION TO 75% | Mar 2019 | Nov 2019 | May 2022 | Apr 2023
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-148-L | TRC - CONS OF DISINFECTION FACILITIES AT 26TH WARD WPCP | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2019 | Nov 2019 | Apr 2023 | Jan 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-148-L | TRC - CONS OF DISINFECTION FACILITIES AT 26TH WARD WPCP | 9 | SUBSTANTIAL COMPLETION | Mar 2019 | Nov 2019 | Jan 2024 | Jul 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-148-L | TRC - CONS OF DISINFECTION FACILITIES AT 26TH WARD WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Nov 2019 | Jul 2028 | Oct 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-149 | RECONSTRUCT TIDE GATES/EFFLUENT CHAMBERS @ SPRING CREEK | 1 | DEVELOP SCOPE | Jun 2019 | Aug 2019 | Jun 2019 | Feb 2020
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-149 | RECONSTRUCT TIDE GATES/EFFLUENT CHAMBERS @ SPRING CREEK | 2 | PRELIMINARY DESIGN | Aug 2019 | Dec 2019 | Feb 2020 | Feb 2021
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-149 | RECONSTRUCT TIDE GATES/EFFLUENT CHAMBERS @ SPRING CREEK | 3 | FINAL DESIGN | Dec 2019 | Jun 2020 | Feb 2021 | Aug 2022
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-149 | RECONSTRUCT TIDE GATES/EFFLUENT CHAMBERS @ SPRING CREEK | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Sep 2020 | Aug 2022 | May 2023
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-149 | RECONSTRUCT TIDE GATES/EFFLUENT CHAMBERS @ SPRING CREEK | 5 | CONSTRUCTION TO 25% | Sep 2020 | Jan 2021 | May 2023 | May 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-149 | RECONSTRUCT TIDE GATES/EFFLUENT CHAMBERS @ SPRING CREEK | 6 | CONSTRUCTION TO 50% | Jan 2021 | May 2021 | May 2024 | Apr 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-149 | RECONSTRUCT TIDE GATES/EFFLUENT CHAMBERS @ SPRING CREEK | 7 | CONSTRUCTION TO 75% | May 2021 | Sep 2021 | Apr 2025 | Apr 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-149 | RECONSTRUCT TIDE GATES/EFFLUENT CHAMBERS @ SPRING CREEK | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Dec 2021 | Apr 2026 | Jan 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-149 | RECONSTRUCT TIDE GATES/EFFLUENT CHAMBERS @ SPRING CREEK | 9 | SUBSTANTIAL COMPLETION | Dec 2021 | Feb 2022 | Jan 2027 | Jul 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-149 | RECONSTRUCT TIDE GATES/EFFLUENT CHAMBERS @ SPRING CREEK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2022 | Mar 2022 | Jul 2027 | Oct 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-156-L | REPLACE WASTE ACTIVATED SLUDGE PIPING AT 26TH WARD WPCP | 1 | FINAL DESIGN | Jun 2019 | Nov 2020 | Jun 2024 | Mar 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-156-L | REPLACE WASTE ACTIVATED SLUDGE PIPING AT 26TH WARD WPCP | 2 | CONSTRUCTION TO 25% | Nov 2020 | Jul 2021 | Mar 2025 | Mar 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-156-L | REPLACE WASTE ACTIVATED SLUDGE PIPING AT 26TH WARD WPCP | 3 | CONSTRUCTION TO 50% | Jul 2021 | Mar 2022 | Mar 2026 | Aug 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-156-L | REPLACE WASTE ACTIVATED SLUDGE PIPING AT 26TH WARD WPCP | 4 | CONSTRUCTION TO 75% | Mar 2022 | Nov 2022 | Aug 2027 | May 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-156-L | REPLACE WASTE ACTIVATED SLUDGE PIPING AT 26TH WARD WPCP | 5 | CONSTRUCTION TO 25% | Mar 2022 | Nov 2022 | May 2028 | May 2029
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-156-L | REPLACE WASTE ACTIVATED SLUDGE PIPING AT 26TH WARD WPCP | 6 | CONSTRUCTION TO 50% | Mar 2022 | Nov 2022 | May 2029 | May 2030
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-156-L | REPLACE WASTE ACTIVATED SLUDGE PIPING AT 26TH WARD WPCP | 7 | CONSTRUCTION TO 75% | Mar 2022 | Nov 2022 | May 2030 | May 2031
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-156-L | REPLACE WASTE ACTIVATED SLUDGE PIPING AT 26TH WARD WPCP | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2022 | Nov 2022 | May 2031 | Feb 2032
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-156-L | REPLACE WASTE ACTIVATED SLUDGE PIPING AT 26TH WARD WPCP | 9 | SUBSTANTIAL COMPLETION | Mar 2022 | Nov 2022 | Feb 2032 | Aug 2032
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-156-L | REPLACE WASTE ACTIVATED SLUDGE PIPING AT 26TH WARD WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Nov 2022 | Aug 2032 | Oct 2032
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-167-L | Installation of SCADA System at 26W WRRF | 1 | DEVELOP SCOPE | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-167-L | Installation of SCADA System at 26W WRRF | 2 | PRELIMINARY DESIGN | Mar 2025 | Mar 2026 | Mar 2025 | Mar 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-167-L | Installation of SCADA System at 26W WRRF | 3 | FINAL DESIGN | Mar 2026 | Aug 2027 | Mar 2026 | Aug 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-167-L | Installation of SCADA System at 26W WRRF | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2027 | May 2028 | Aug 2027 | May 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-167-L | Installation of SCADA System at 26W WRRF | 5 | CONSTRUCTION TO 25% | May 2028 | May 2029 | May 2028 | May 2029
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-167-L | Installation of SCADA System at 26W WRRF | 6 | CONSTRUCTION TO 50% | May 2029 | May 2030 | May 2029 | May 2030
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-167-L | Installation of SCADA System at 26W WRRF | 7 | CONSTRUCTION TO 75% | May 2030 | May 2031 | May 2030 | May 2031
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-167-L | Installation of SCADA System at 26W WRRF | 8 | ORIGINAL EQUIP & FURNISHING | May 2031 | Feb 2032 | May 2031 | Feb 2032
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-167-L | Installation of SCADA System at 26W WRRF | 9 | SUBSTANTIAL COMPLETION | Feb 2032 | Aug 2032 | Feb 2032 | Aug 2032
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-167-L | Installation of SCADA System at 26W WRRF | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2032 | Oct 2032 | Aug 2032 | Oct 2032
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-834 | Dist WM work in Nostrand Ave from Dean St to Prospect Pl, BK | 1 | DEVELOP SCOPE | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-834 | Dist WM work in Nostrand Ave from Dean St to Prospect Pl, BK | 2 | PRELIMINARY DESIGN | Mar 2024 | Jul 2024 | Mar 2024 | Jul 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-834 | Dist WM work in Nostrand Ave from Dean St to Prospect Pl, BK | 3 | FINAL DESIGN | Jul 2024 | Jan 2025 | Jul 2024 | Jan 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-834 | Dist WM work in Nostrand Ave from Dean St to Prospect Pl, BK | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2025 | Apr 2025 | Jan 2025 | Apr 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-834 | Dist WM work in Nostrand Ave from Dean St to Prospect Pl, BK | 5 | CONSTRUCTION TO 25% | Apr 2025 | Aug 2025 | Apr 2025 | Aug 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-834 | Dist WM work in Nostrand Ave from Dean St to Prospect Pl, BK | 6 | CONSTRUCTION TO 50% | Aug 2025 | Dec 2025 | Aug 2025 | Dec 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-834 | Dist WM work in Nostrand Ave from Dean St to Prospect Pl, BK | 7 | CONSTRUCTION TO 75% | Dec 2025 | Apr 2026 | Dec 2025 | Apr 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-834 | Dist WM work in Nostrand Ave from Dean St to Prospect Pl, BK | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2026 | Jul 2026 | Apr 2026 | Jul 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-834 | Dist WM work in Nostrand Ave from Dean St to Prospect Pl, BK | 9 | SUBSTANTIAL COMPLETION | Jul 2026 | Sep 2026 | Jul 2026 | Sep 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-834 | Dist WM work in Nostrand Ave from Dean St to Prospect Pl, BK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Oct 2026 | Sep 2026 | Oct 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-K24 | Replacing substandard catch basins with upgraded designs BK | 1 | DEVELOP SCOPE | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-K24 | Replacing substandard catch basins with upgraded designs BK | 2 | PRELIMINARY DESIGN | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-K24 | Replacing substandard catch basins with upgraded designs BK | 3 | FINAL DESIGN | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-K24 | Replacing substandard catch basins with upgraded designs BK | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2024 | Feb 2025 | Nov 2024 | Feb 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-K24 | Replacing substandard catch basins with upgraded designs BK | 5 | CONSTRUCTION TO 25% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-K24 | Replacing substandard catch basins with upgraded designs BK | 6 | CONSTRUCTION TO 50% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-K24 | Replacing substandard catch basins with upgraded designs BK | 7 | CONSTRUCTION TO 75% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-K24 | Replacing substandard catch basins with upgraded designs BK | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2026 | May 2026 | Feb 2026 | May 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-K24 | Replacing substandard catch basins with upgraded designs BK | 9 | SUBSTANTIAL COMPLETION | May 2026 | Jul 2026 | May 2026 | Jul 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-K24 | Replacing substandard catch basins with upgraded designs BK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2026 | Aug 2026 | Jul 2026 | Aug 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-113-L | Replacement of Switchgear at Coney Island WRRF | 1 | DEVELOP SCOPE | Jun 2016 | Feb 2017 | Jun 2016 | Feb 2017
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-113-L | Replacement of Switchgear at Coney Island WRRF | 2 | PRELIMINARY DESIGN | Feb 2017 | Feb 2018 | Feb 2017 | Feb 2018
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-113-L | Replacement of Switchgear at Coney Island WRRF | 3 | FINAL DESIGN | Feb 2018 | Aug 2019 | Feb 2018 | Aug 2019
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-113-L | Replacement of Switchgear at Coney Island WRRF | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2019 | May 2020 | Aug 2019 | May 2020
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-113-L | Replacement of Switchgear at Coney Island WRRF | 5 | CONSTRUCTION TO 25% | May 2020 | May 2021 | May 2020 | May 2021
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-113-L | Replacement of Switchgear at Coney Island WRRF | 6 | CONSTRUCTION TO 50% | May 2021 | Apr 2022 | May 2021 | Apr 2022
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-113-L | Replacement of Switchgear at Coney Island WRRF | 7 | CONSTRUCTION TO 75% | May 2022 | Apr 2023 | May 2022 | Apr 2023
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-113-L | Replacement of Switchgear at Coney Island WRRF | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2023 | Jan 2024 | Apr 2023 | Jan 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-113-L | Replacement of Switchgear at Coney Island WRRF | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-113-L | Replacement of Switchgear at Coney Island WRRF | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2024 | Oct 2024 | Jul 2028 | Oct 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-119-L | RECONSTRUCTION OF GATES & MSP MOTORS & CONTROLS @ C.I. | 1 | DEVELOP SCOPE | Jun 2022 | Mar 2023 | Jul 2018 | Mar 2019
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-119-L | RECONSTRUCTION OF GATES & MSP MOTORS & CONTROLS @ C.I. | 2 | PRELIMINARY DESIGN | Mar 2023 | Mar 2024 | Mar 2019 | Mar 2020
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-119-L | RECONSTRUCTION OF GATES & MSP MOTORS & CONTROLS @ C.I. | 3 | FINAL DESIGN | Mar 2024 | Aug 2025 | Mar 2020 | Sep 2021
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-119-L | RECONSTRUCTION OF GATES & MSP MOTORS & CONTROLS @ C.I. | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2025 | May 2026 | Sep 2021 | Jun 2022
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-119-L | RECONSTRUCTION OF GATES & MSP MOTORS & CONTROLS @ C.I. | 5 | CONSTRUCTION TO 25% | May 2026 | May 2027 | Jun 2022 | Jun 2023
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-119-L | RECONSTRUCTION OF GATES & MSP MOTORS & CONTROLS @ C.I. | 6 | CONSTRUCTION TO 50% | May 2027 | May 2028 | Jun 2023 | May 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-119-L | RECONSTRUCTION OF GATES & MSP MOTORS & CONTROLS @ C.I. | 7 | CONSTRUCTION TO 75% | May 2028 | May 2029 | May 2024 | May 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-119-L | RECONSTRUCTION OF GATES & MSP MOTORS & CONTROLS @ C.I. | 8 | ORIGINAL EQUIP & FURNISHING | May 2029 | Feb 2030 | May 2025 | Feb 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-119-L | RECONSTRUCTION OF GATES & MSP MOTORS & CONTROLS @ C.I. | 9 | SUBSTANTIAL COMPLETION | Feb 2030 | Aug 2030 | Feb 2026 | Aug 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-119-L | RECONSTRUCTION OF GATES & MSP MOTORS & CONTROLS @ C.I. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2030 | Oct 2030 | Aug 2026 | Nov 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-124 | RECONSTRUCTION OF HEATING SYSTEM AT CONEY ISLAND WPCP | 1 | FINAL DESIGN | Jun 2022 | Nov 2023 | Jun 2025 | Feb 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-124 | RECONSTRUCTION OF HEATING SYSTEM AT CONEY ISLAND WPCP | 2 | CONSTRUCTION TO 25% | Nov 2023 | Jul 2024 | Feb 2026 | Feb 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-124 | RECONSTRUCTION OF HEATING SYSTEM AT CONEY ISLAND WPCP | 3 | CONSTRUCTION TO 50% | Jul 2024 | Mar 2025 | Feb 2027 | Aug 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-124 | RECONSTRUCTION OF HEATING SYSTEM AT CONEY ISLAND WPCP | 4 | CONSTRUCTION TO 75% | Mar 2025 | Nov 2025 | Aug 2028 | May 2029
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-124 | RECONSTRUCTION OF HEATING SYSTEM AT CONEY ISLAND WPCP | 5 | CONSTRUCTION TO 25% | Mar 2025 | Nov 2025 | May 2029 | May 2030
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-124 | RECONSTRUCTION OF HEATING SYSTEM AT CONEY ISLAND WPCP | 6 | CONSTRUCTION TO 50% | Mar 2025 | Nov 2025 | May 2030 | Apr 2031
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-124 | RECONSTRUCTION OF HEATING SYSTEM AT CONEY ISLAND WPCP | 7 | CONSTRUCTION TO 75% | Mar 2025 | Nov 2025 | May 2031 | Apr 2032
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-124 | RECONSTRUCTION OF HEATING SYSTEM AT CONEY ISLAND WPCP | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2025 | Nov 2025 | Apr 2032 | Jan 2033
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-124 | RECONSTRUCTION OF HEATING SYSTEM AT CONEY ISLAND WPCP | 9 | SUBSTANTIAL COMPLETION | Mar 2025 | Nov 2025 | Jan 2033 | Jul 2033
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-124 | RECONSTRUCTION OF HEATING SYSTEM AT CONEY ISLAND WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Nov 2025 | Jul 2033 | Oct 2033
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-140-L | INSTALL ODOR CONTROL PANELS FOR AERATION SCRUBBER SYSTEM | 1 | FINAL DESIGN | Jun 2027 | Nov 2028 | Jun 2027 | Nov 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-140-L | INSTALL ODOR CONTROL PANELS FOR AERATION SCRUBBER SYSTEM | 2 | CONSTRUCTION TO 25% | Nov 2028 | Jul 2029 | Nov 2028 | Jul 2029
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-140-L | INSTALL ODOR CONTROL PANELS FOR AERATION SCRUBBER SYSTEM | 3 | CONSTRUCTION TO 50% | Jul 2029 | Mar 2030 | Jul 2029 | Mar 2030
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-140-L | INSTALL ODOR CONTROL PANELS FOR AERATION SCRUBBER SYSTEM | 4 | CONSTRUCTION TO 75% | Mar 2030 | Nov 2030 | Mar 2030 | Nov 2030
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-GC-SFS | CONSTRUCTION OF GOWANUS CSO RETENTION FAC SUPERFUND SITE | 1 | DEVELOP SCOPE | Jul 2015 | Mar 2016 | Jul 2015 | Mar 2016
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-GC-SFS | CONSTRUCTION OF GOWANUS CSO RETENTION FAC SUPERFUND SITE | 2 | PRELIMINARY DESIGN | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-GC-SFS | CONSTRUCTION OF GOWANUS CSO RETENTION FAC SUPERFUND SITE | 3 | FINAL DESIGN | Mar 2017 | Sep 2018 | Mar 2017 | Sep 2018
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-GC-SFS | CONSTRUCTION OF GOWANUS CSO RETENTION FAC SUPERFUND SITE | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2018 | Jun 2019 | Sep 2018 | Jun 2019
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-GC-SFS | CONSTRUCTION OF GOWANUS CSO RETENTION FAC SUPERFUND SITE | 5 | CONSTRUCTION TO 25% | Jun 2019 | Jun 2020 | Jun 2019 | Jun 2020
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-GC-SFS | CONSTRUCTION OF GOWANUS CSO RETENTION FAC SUPERFUND SITE | 6 | CONSTRUCTION TO 50% | Jun 2020 | May 2021 | Jun 2020 | May 2021
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-GC-SFS | CONSTRUCTION OF GOWANUS CSO RETENTION FAC SUPERFUND SITE | 7 | CONSTRUCTION TO 75% | May 2021 | May 2022 | May 2021 | May 2022
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-GC-SFS | CONSTRUCTION OF GOWANUS CSO RETENTION FAC SUPERFUND SITE | 8 | ORIGINAL EQUIP & FURNISHING | May 2022 | Feb 2023 | May 2022 | Feb 2023
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-GC-SFS | CONSTRUCTION OF GOWANUS CSO RETENTION FAC SUPERFUND SITE | 9 | SUBSTANTIAL COMPLETION | Feb 2023 | Aug 2027 | Feb 2023 | Aug 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-GC-SFS | CONSTRUCTION OF GOWANUS CSO RETENTION FAC SUPERFUND SITE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2027 | Nov 2027 | Aug 2027 | Nov 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC | FLUSHING TUNNEL REACTIVATION & GOWANUS CANAL FORCE MAIN | 1 | DEVELOP SCOPE | Mar 2001 | Dec 2001 | Jun 2004 | Mar 2005
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC | FLUSHING TUNNEL REACTIVATION & GOWANUS CANAL FORCE MAIN | 2 | PRELIMINARY DESIGN | Dec 2001 | Dec 2002 | Mar 2005 | Mar 2006
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC | FLUSHING TUNNEL REACTIVATION & GOWANUS CANAL FORCE MAIN | 3 | FINAL DESIGN | Dec 2002 | May 2004 | Mar 2006 | Aug 2007
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC | FLUSHING TUNNEL REACTIVATION & GOWANUS CANAL FORCE MAIN | 4 | BID AWARD AND REGISTER CONTRCT | May 2004 | Feb 2005 | Aug 2007 | May 2008
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC | FLUSHING TUNNEL REACTIVATION & GOWANUS CANAL FORCE MAIN | 5 | CONSTRUCTION TO 25% | Feb 2005 | Feb 2006 | May 2008 | May 2009
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC | FLUSHING TUNNEL REACTIVATION & GOWANUS CANAL FORCE MAIN | 6 | CONSTRUCTION TO 50% | Feb 2006 | Feb 2007 | May 2009 | May 2010
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC | FLUSHING TUNNEL REACTIVATION & GOWANUS CANAL FORCE MAIN | 7 | CONSTRUCTION TO 75% | Feb 2007 | Feb 2008 | May 2010 | May 2011
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC | FLUSHING TUNNEL REACTIVATION & GOWANUS CANAL FORCE MAIN | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2008 | Nov 2008 | May 2011 | Feb 2012
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC | FLUSHING TUNNEL REACTIVATION & GOWANUS CANAL FORCE MAIN | 9 | SUBSTANTIAL COMPLETION | Nov 2008 | May 2009 | Feb 2012 | Jul 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC | FLUSHING TUNNEL REACTIVATION & GOWANUS CANAL FORCE MAIN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2009 | Jul 2009 | Jul 2024 | Oct 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC-SP | CONSTRUCTION OF GOWANUS CANAL PILOT SPONGE PARK | 1 | DEVELOP SCOPE | Oct 2014 | Dec 2014 | Jul 2020 | Oct 2020
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC-SP | CONSTRUCTION OF GOWANUS CANAL PILOT SPONGE PARK | 2 | PRELIMINARY DESIGN | Dec 2014 | Apr 2015 | Oct 2020 | Feb 2021
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC-SP | CONSTRUCTION OF GOWANUS CANAL PILOT SPONGE PARK | 3 | FINAL DESIGN | Apr 2015 | Oct 2015 | Feb 2021 | Aug 2021
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC-SP | CONSTRUCTION OF GOWANUS CANAL PILOT SPONGE PARK | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2015 | Jan 2016 | Aug 2021 | Nov 2021
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC-SP | CONSTRUCTION OF GOWANUS CANAL PILOT SPONGE PARK | 5 | CONSTRUCTION TO 25% | Jan 2016 | May 2016 | Nov 2021 | Mar 2022
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC-SP | CONSTRUCTION OF GOWANUS CANAL PILOT SPONGE PARK | 6 | CONSTRUCTION TO 50% | May 2016 | Sep 2016 | Mar 2022 | Jul 2022
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC-SP | CONSTRUCTION OF GOWANUS CANAL PILOT SPONGE PARK | 7 | CONSTRUCTION TO 75% | Sep 2016 | Jan 2017 | Jul 2022 | Nov 2022
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC-SP | CONSTRUCTION OF GOWANUS CANAL PILOT SPONGE PARK | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2017 | Apr 2017 | Nov 2022 | Feb 2023
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC-SP | CONSTRUCTION OF GOWANUS CANAL PILOT SPONGE PARK | 9 | SUBSTANTIAL COMPLETION | Apr 2017 | Jun 2017 | Feb 2023 | Apr 2023
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC-SP | CONSTRUCTION OF GOWANUS CANAL PILOT SPONGE PARK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2017 | Jul 2017 | Apr 2023 | May 2023
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKN25 | Reconstruction of Existing Sewers, North Brooklyn | 1 | DEVELOP SCOPE | Jan 2023 | Apr 2023 | Jan 2023 | Apr 2023
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKN25 | Reconstruction of Existing Sewers, North Brooklyn | 2 | PRELIMINARY DESIGN | Apr 2023 | Aug 2023 | Apr 2023 | Aug 2023
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKN25 | Reconstruction of Existing Sewers, North Brooklyn | 3 | FINAL DESIGN | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKN25 | Reconstruction of Existing Sewers, North Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2024 | May 2024 | Feb 2024 | May 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKN25 | Reconstruction of Existing Sewers, North Brooklyn | 5 | CONSTRUCTION TO 25% | May 2024 | Aug 2024 | May 2024 | Aug 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKN25 | Reconstruction of Existing Sewers, North Brooklyn | 6 | CONSTRUCTION TO 50% | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKN25 | Reconstruction of Existing Sewers, North Brooklyn | 7 | CONSTRUCTION TO 75% | Dec 2024 | Apr 2025 | Dec 2024 | Apr 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKN25 | Reconstruction of Existing Sewers, North Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2025 | Jul 2025 | Apr 2025 | Jul 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKN25 | Reconstruction of Existing Sewers, North Brooklyn | 9 | SUBSTANTIAL COMPLETION | Jul 2025 | Sep 2025 | Jul 2025 | Sep 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKN25 | Reconstruction of Existing Sewers, North Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Oct 2025 | Sep 2025 | Oct 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKS25 | Reconstruction of Existing Sewers, South Brooklyn | 1 | DEVELOP SCOPE | Jan 2023 | Apr 2023 | Jan 2023 | Apr 2023
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKS25 | Reconstruction of Existing Sewers, South Brooklyn | 2 | PRELIMINARY DESIGN | Apr 2023 | Aug 2023 | Apr 2023 | Aug 2023
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKS25 | Reconstruction of Existing Sewers, South Brooklyn | 3 | FINAL DESIGN | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKS25 | Reconstruction of Existing Sewers, South Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2024 | May 2024 | Feb 2024 | May 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKS25 | Reconstruction of Existing Sewers, South Brooklyn | 5 | CONSTRUCTION TO 25% | May 2024 | Aug 2024 | May 2024 | Aug 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKS25 | Reconstruction of Existing Sewers, South Brooklyn | 6 | CONSTRUCTION TO 50% | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKS25 | Reconstruction of Existing Sewers, South Brooklyn | 7 | CONSTRUCTION TO 75% | Dec 2024 | Apr 2025 | Dec 2024 | Apr 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKS25 | Reconstruction of Existing Sewers, South Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2025 | Jul 2025 | Apr 2025 | Jul 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKS25 | Reconstruction of Existing Sewers, South Brooklyn | 9 | SUBSTANTIAL COMPLETION | Jul 2025 | Sep 2025 | Jul 2025 | Sep 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKS25 | Reconstruction of Existing Sewers, South Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Oct 2025 | Sep 2025 | Oct 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-A | GI - INSTALL GI AT NYPD PCTS 75, 77 & 115 PARKING LOTS | 1 | FINAL DESIGN | Jun 2019 | Dec 2020 | Dec 2022 | Jun 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-A | GI - INSTALL GI AT NYPD PCTS 75, 77 & 115 PARKING LOTS | 2 | CONSTRUCTION TO 25% | Dec 2020 | Aug 2021 | Jun 2024 | Feb 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-A | GI - INSTALL GI AT NYPD PCTS 75, 77 & 115 PARKING LOTS | 3 | CONSTRUCTION TO 50% | Aug 2021 | Apr 2022 | Feb 2025 | Oct 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-A | GI - INSTALL GI AT NYPD PCTS 75, 77 & 115 PARKING LOTS | 4 | CONSTRUCTION TO 75% | Apr 2022 | Dec 2022 | Oct 2025 | Jun 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-B | GI - INSTALL GI AT NYPD PCTS 73, 79 & 81 PARKING LOTS | 1 | FINAL DESIGN | Jun 2019 | Dec 2020 | Dec 2021 | Jun 2023
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-B | GI - INSTALL GI AT NYPD PCTS 73, 79 & 81 PARKING LOTS | 2 | CONSTRUCTION TO 25% | Dec 2020 | Aug 2021 | Jun 2023 | Feb 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-B | GI - INSTALL GI AT NYPD PCTS 73, 79 & 81 PARKING LOTS | 3 | CONSTRUCTION TO 50% | Aug 2021 | Apr 2022 | Feb 2024 | Oct 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-B | GI - INSTALL GI AT NYPD PCTS 73, 79 & 81 PARKING LOTS | 4 | CONSTRUCTION TO 75% | Apr 2022 | Dec 2022 | Oct 2024 | Jun 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-C | GI - INSTALL GI AT NYPD 83 PRECINCT PARKING LOTS | 1 | FINAL DESIGN | Jun 2019 | Dec 2020 | Dec 2022 | Jun 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-C | GI - INSTALL GI AT NYPD 83 PRECINCT PARKING LOTS | 2 | CONSTRUCTION TO 25% | Dec 2020 | Aug 2021 | Jun 2024 | Feb 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-C | GI - INSTALL GI AT NYPD 83 PRECINCT PARKING LOTS | 3 | CONSTRUCTION TO 50% | Aug 2021 | Apr 2022 | Feb 2025 | Oct 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-C | GI - INSTALL GI AT NYPD 83 PRECINCT PARKING LOTS | 4 | CONSTRUCTION TO 75% | Apr 2022 | Dec 2022 | Oct 2025 | Jun 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-D | GI - INSTALL GI AT NYPD PCTS 43, 71,107 & FLUSHING ARMORY | 1 | FINAL DESIGN | Jun 2019 | Dec 2020 | Dec 2022 | Jun 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-D | GI - INSTALL GI AT NYPD PCTS 43, 71,107 & FLUSHING ARMORY | 2 | CONSTRUCTION TO 25% | Dec 2020 | Aug 2021 | Jun 2024 | Feb 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-D | GI - INSTALL GI AT NYPD PCTS 43, 71,107 & FLUSHING ARMORY | 3 | CONSTRUCTION TO 50% | Aug 2021 | Apr 2022 | Feb 2025 | Oct 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-D | GI - INSTALL GI AT NYPD PCTS 43, 71,107 & FLUSHING ARMORY | 4 | CONSTRUCTION TO 75% | Apr 2022 | Dec 2022 | Oct 2025 | Jun 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-173 | INSTALL GRAVITY BELT THICKENERS AT NEWTOWN CREEK WPCP | 1 | DEVELOP SCOPE | Jun 2024 | Feb 2025 | Jun 2024 | Feb 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-173 | INSTALL GRAVITY BELT THICKENERS AT NEWTOWN CREEK WPCP | 2 | PRELIMINARY DESIGN | Feb 2025 | Feb 2026 | Feb 2025 | Feb 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-173 | INSTALL GRAVITY BELT THICKENERS AT NEWTOWN CREEK WPCP | 3 | FINAL DESIGN | Feb 2026 | Aug 2027 | Feb 2026 | Aug 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-173 | INSTALL GRAVITY BELT THICKENERS AT NEWTOWN CREEK WPCP | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2027 | May 2028 | Aug 2027 | May 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-173 | INSTALL GRAVITY BELT THICKENERS AT NEWTOWN CREEK WPCP | 5 | CONSTRUCTION TO 25% | May 2028 | May 2029 | May 2028 | May 2029
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-173 | INSTALL GRAVITY BELT THICKENERS AT NEWTOWN CREEK WPCP | 6 | CONSTRUCTION TO 50% | May 2029 | Apr 2030 | May 2029 | Apr 2030
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-173 | INSTALL GRAVITY BELT THICKENERS AT NEWTOWN CREEK WPCP | 7 | CONSTRUCTION TO 75% | May 2030 | Apr 2031 | May 2030 | Apr 2031
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-173 | INSTALL GRAVITY BELT THICKENERS AT NEWTOWN CREEK WPCP | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2031 | Jan 2032 | Apr 2031 | Jan 2032
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-173 | INSTALL GRAVITY BELT THICKENERS AT NEWTOWN CREEK WPCP | 9 | SUBSTANTIAL COMPLETION | Jan 2032 | Jul 2032 | Jan 2032 | Jul 2032
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-173 | INSTALL GRAVITY BELT THICKENERS AT NEWTOWN CREEK WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2032 | Oct 2032 | Jul 2032 | Oct 2032
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-GATEGP | CONSTRUCTION OF NEWTOWN CREEK GATEWAY TO GREENPOINT PROJECT | 1 | FINAL DESIGN | Jun 2021 | Nov 2022 | Jun 2021 | Nov 2022
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-GATEGP | CONSTRUCTION OF NEWTOWN CREEK GATEWAY TO GREENPOINT PROJECT | 2 | CONSTRUCTION TO 25% | Nov 2022 | Jul 2023 | Nov 2022 | Jul 2023
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-GATEGP | CONSTRUCTION OF NEWTOWN CREEK GATEWAY TO GREENPOINT PROJECT | 3 | CONSTRUCTION TO 50% | Jul 2023 | Mar 2024 | Jul 2023 | Mar 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-GATEGP | CONSTRUCTION OF NEWTOWN CREEK GATEWAY TO GREENPOINT PROJECT | 4 | CONSTRUCTION TO 75% | Mar 2024 | Nov 2024 | Mar 2024 | Nov 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-UPGRD | UPGRADING THE NEWTOWN CREEK WPCP | 1 | DEVELOP SCOPE | Jun 1997 | Aug 1997 | Apr 1999 | Jul 1999
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-UPGRD | UPGRADING THE NEWTOWN CREEK WPCP | 2 | PRELIMINARY DESIGN | Aug 1997 | Dec 1997 | Jul 1999 | Oct 1999
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-UPGRD | UPGRADING THE NEWTOWN CREEK WPCP | 3 | FINAL DESIGN | Dec 1997 | Jun 1998 | Oct 1999 | Apr 2000
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-UPGRD | UPGRADING THE NEWTOWN CREEK WPCP | 4 | BID AWARD AND REGISTER CONTRCT | Jun 1998 | Sep 1998 | Apr 2000 | Jul 2000
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-UPGRD | UPGRADING THE NEWTOWN CREEK WPCP | 5 | CONSTRUCTION TO 25% | Sep 1998 | Jan 1999 | Jul 2000 | Nov 2000
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-UPGRD | UPGRADING THE NEWTOWN CREEK WPCP | 6 | CONSTRUCTION TO 50% | Jan 1999 | May 1999 | Nov 2000 | Mar 2001
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-UPGRD | UPGRADING THE NEWTOWN CREEK WPCP | 7 | CONSTRUCTION TO 75% | May 1999 | Sep 1999 | Mar 2001 | Jul 2001
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-UPGRD | UPGRADING THE NEWTOWN CREEK WPCP | 8 | ORIGINAL EQUIP & FURNISHING | Sep 1999 | Dec 1999 | Jul 2001 | Oct 2001
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-UPGRD | UPGRADING THE NEWTOWN CREEK WPCP | 9 | SUBSTANTIAL COMPLETION | Dec 1999 | Feb 2000 | Oct 2001 | Dec 2001
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-UPGRD | UPGRADING THE NEWTOWN CREEK WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2000 | Mar 2000 | Dec 2001 | Jan 2002
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-UPGRD | UPGRADING THE NEWTOWN CREEK WPCP | 11 | DEVELOP SCOPE | Feb 2000 | Mar 2000 | Jan 2002 | Oct 2002
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-UPGRD | UPGRADING THE NEWTOWN CREEK WPCP | 12 | PRELIMINARY DESIGN | Feb 2000 | Mar 2000 | Oct 2002 | Oct 2003
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-UPGRD | UPGRADING THE NEWTOWN CREEK WPCP | 13 | FINAL DESIGN | Feb 2000 | Mar 2000 | Oct 2003 | Apr 2005
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-UPGRD | UPGRADING THE NEWTOWN CREEK WPCP | 14 | BID AWARD AND REGISTER CONTRCT | Feb 2000 | Mar 2000 | Apr 2005 | Dec 2005
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-UPGRD | UPGRADING THE NEWTOWN CREEK WPCP | 15 | CONSTRUCTION TO 25% | Feb 2000 | Mar 2000 | Dec 2005 | Dec 2006
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-UPGRD | UPGRADING THE NEWTOWN CREEK WPCP | 16 | CONSTRUCTION TO 50% | Feb 2000 | Mar 2000 | Dec 2006 | Dec 2007
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-UPGRD | UPGRADING THE NEWTOWN CREEK WPCP | 17 | CONSTRUCTION TO 75% | Feb 2000 | Mar 2000 | Dec 2007 | Dec 2008
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-UPGRD | UPGRADING THE NEWTOWN CREEK WPCP | 18 | ORIGINAL EQUIP & FURNISHING | Feb 2000 | Mar 2000 | Dec 2008 | Sep 2009
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-UPGRD | UPGRADING THE NEWTOWN CREEK WPCP | 19 | SUBSTANTIAL COMPLETION | Feb 2000 | Mar 2000 | Sep 2009 | Mar 2022
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-UPGRD | UPGRADING THE NEWTOWN CREEK WPCP | 20 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2000 | Mar 2000 | Mar 2022 | Jun 2022
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-112-L | REPLACE MAIN SEWAGE PUMPS & PIPING AT OWLS HEAD WPCP | 1 | DEVELOP SCOPE | Jul 2019 | Mar 2020 | Jul 2019 | Mar 2020
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-112-L | REPLACE MAIN SEWAGE PUMPS & PIPING AT OWLS HEAD WPCP | 2 | PRELIMINARY DESIGN | Mar 2020 | Mar 2021 | Mar 2020 | Mar 2021
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-112-L | REPLACE MAIN SEWAGE PUMPS & PIPING AT OWLS HEAD WPCP | 3 | FINAL DESIGN | Mar 2021 | Sep 2022 | Mar 2021 | Sep 2022
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-112-L | REPLACE MAIN SEWAGE PUMPS & PIPING AT OWLS HEAD WPCP | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2022 | Jun 2023 | Sep 2022 | Jun 2023
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-112-L | REPLACE MAIN SEWAGE PUMPS & PIPING AT OWLS HEAD WPCP | 5 | CONSTRUCTION TO 25% | Jun 2023 | Jun 2024 | Jun 2023 | Jun 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-112-L | REPLACE MAIN SEWAGE PUMPS & PIPING AT OWLS HEAD WPCP | 6 | CONSTRUCTION TO 50% | Jun 2024 | May 2025 | Jun 2024 | May 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-112-L | REPLACE MAIN SEWAGE PUMPS & PIPING AT OWLS HEAD WPCP | 7 | CONSTRUCTION TO 75% | May 2025 | May 2026 | May 2025 | May 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-112-L | REPLACE MAIN SEWAGE PUMPS & PIPING AT OWLS HEAD WPCP | 8 | ORIGINAL EQUIP & FURNISHING | May 2026 | Feb 2027 | May 2026 | Feb 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-112-L | REPLACE MAIN SEWAGE PUMPS & PIPING AT OWLS HEAD WPCP | 9 | SUBSTANTIAL COMPLETION | Feb 2027 | Aug 2027 | Feb 2027 | Aug 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-112-L | REPLACE MAIN SEWAGE PUMPS & PIPING AT OWLS HEAD WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2027 | Nov 2027 | Aug 2027 | Nov 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-122 | Reconstruction of Diffuser System @ Owls Head WRRF | 1 | DEVELOP SCOPE | Jun 2023 | Feb 2024 | Jun 2025 | Feb 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-122 | Reconstruction of Diffuser System @ Owls Head WRRF | 2 | PRELIMINARY DESIGN | Feb 2024 | Feb 2025 | Feb 2026 | Feb 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-122 | Reconstruction of Diffuser System @ Owls Head WRRF | 3 | FINAL DESIGN | Feb 2025 | Aug 2026 | Feb 2027 | Aug 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-122 | Reconstruction of Diffuser System @ Owls Head WRRF | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2026 | May 2027 | Aug 2028 | May 2029
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-122 | Reconstruction of Diffuser System @ Owls Head WRRF | 5 | CONSTRUCTION TO 25% | May 2027 | May 2028 | May 2029 | May 2030
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-122 | Reconstruction of Diffuser System @ Owls Head WRRF | 6 | CONSTRUCTION TO 50% | May 2028 | Apr 2029 | May 2030 | Apr 2031
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-122 | Reconstruction of Diffuser System @ Owls Head WRRF | 7 | CONSTRUCTION TO 75% | Apr 2029 | Apr 2030 | May 2031 | Apr 2032
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-122 | Reconstruction of Diffuser System @ Owls Head WRRF | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2030 | Jan 2031 | Apr 2032 | Jan 2033
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-122 | Reconstruction of Diffuser System @ Owls Head WRRF | 9 | SUBSTANTIAL COMPLETION | Jan 2031 | Jul 2035 | Jan 2033 | Jul 2033
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-122 | Reconstruction of Diffuser System @ Owls Head WRRF | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2035 | Oct 2035 | Jul 2033 | Oct 2033
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-123 | INSTALL GRAVITY BELT THICKENER & ODOR CTRL @OH WPCP | 1 | DEVELOP SCOPE | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-123 | INSTALL GRAVITY BELT THICKENER & ODOR CTRL @OH WPCP | 2 | PRELIMINARY DESIGN | Mar 2025 | Mar 2026 | Mar 2025 | Mar 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-123 | INSTALL GRAVITY BELT THICKENER & ODOR CTRL @OH WPCP | 3 | FINAL DESIGN | Mar 2026 | Aug 2027 | Mar 2026 | Aug 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-123 | INSTALL GRAVITY BELT THICKENER & ODOR CTRL @OH WPCP | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2027 | May 2028 | Aug 2027 | May 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-123 | INSTALL GRAVITY BELT THICKENER & ODOR CTRL @OH WPCP | 5 | CONSTRUCTION TO 25% | May 2028 | May 2029 | May 2028 | May 2029
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-123 | INSTALL GRAVITY BELT THICKENER & ODOR CTRL @OH WPCP | 6 | CONSTRUCTION TO 50% | May 2029 | May 2030 | May 2029 | May 2030
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-123 | INSTALL GRAVITY BELT THICKENER & ODOR CTRL @OH WPCP | 7 | CONSTRUCTION TO 75% | May 2030 | May 2031 | May 2030 | May 2031
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-123 | INSTALL GRAVITY BELT THICKENER & ODOR CTRL @OH WPCP | 8 | ORIGINAL EQUIP & FURNISHING | May 2031 | Feb 2032 | May 2031 | Feb 2032
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-123 | INSTALL GRAVITY BELT THICKENER & ODOR CTRL @OH WPCP | 9 | SUBSTANTIAL COMPLETION | Feb 2032 | Aug 2032 | Feb 2032 | Aug 2032
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-123 | INSTALL GRAVITY BELT THICKENER & ODOR CTRL @OH WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2032 | Oct 2032 | Aug 2032 | Oct 2032
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 1 | DEVELOP SCOPE | Oct 2017 | Jul 2018 | Jan 2016 | Oct 2016
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 2 | PRELIMINARY DESIGN | Jul 2018 | Jul 2019 | Oct 2016 | Oct 2017
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 3 | FINAL DESIGN | Jul 2019 | Dec 2020 | Oct 2017 | Mar 2019
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 4 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Sep 2021 | Apr 2019 | Dec 2019
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 5 | CONSTRUCTION TO 25% | Sep 2021 | Sep 2022 | Dec 2019 | Dec 2020
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 6 | CONSTRUCTION TO 50% | Sep 2022 | Sep 2023 | Dec 2020 | Dec 2021
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 7 | CONSTRUCTION TO 75% | Sep 2023 | Sep 2024 | Dec 2021 | Dec 2022
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 8 | DEVELOP SCOPE | Mar 2026 | May 2026 | Dec 2022 | Sep 2023
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 9 | PRELIMINARY DESIGN | May 2026 | Sep 2026 | Sep 2023 | Mar 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 10 | FINAL DESIGN | Sep 2026 | Mar 2027 | Mar 2028 | Jun 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 11 | BID AWARD AND REGISTER CONTRCT | Mar 2027 | Jun 2027 | Mar 2028 | Jun 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 12 | CONSTRUCTION TO 25% | Jun 2027 | Oct 2027 | Mar 2028 | Jun 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 13 | CONSTRUCTION TO 50% | Oct 2027 | Feb 2028 | Mar 2028 | Jun 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 14 | CONSTRUCTION TO 75% | Feb 2028 | Jun 2028 | Mar 2028 | Jun 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 15 | ORIGINAL EQUIP & FURNISHING | Jun 2028 | Sep 2028 | Mar 2028 | Jun 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 16 | SUBSTANTIAL COMPLETION | Sep 2028 | Nov 2028 | Mar 2028 | Jun 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | 17 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2028 | Dec 2028 | Mar 2028 | Jun 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-91-L | RECONSTRUCTION OF SEA WALL AND DOCK @ OWLS HEAD WWTP | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Feb 2014 | Oct 2014
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-91-L | RECONSTRUCTION OF SEA WALL AND DOCK @ OWLS HEAD WWTP | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Oct 2014 | Oct 2015
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-91-L | RECONSTRUCTION OF SEA WALL AND DOCK @ OWLS HEAD WWTP | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Oct 2015 | Apr 2017
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-91-L | RECONSTRUCTION OF SEA WALL AND DOCK @ OWLS HEAD WWTP | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Apr 2017 | Jan 2018
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-91-L | RECONSTRUCTION OF SEA WALL AND DOCK @ OWLS HEAD WWTP | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Jan 2018 | Jan 2019
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-91-L | RECONSTRUCTION OF SEA WALL AND DOCK @ OWLS HEAD WWTP | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2019 | Dec 2019
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-91-L | RECONSTRUCTION OF SEA WALL AND DOCK @ OWLS HEAD WWTP | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | Jan 2020 | Dec 2020
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-91-L | RECONSTRUCTION OF SEA WALL AND DOCK @ OWLS HEAD WWTP | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Dec 2020 | Sep 2021
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-91-L | RECONSTRUCTION OF SEA WALL AND DOCK @ OWLS HEAD WWTP | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Sep 2021 | Mar 2030
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-91-L | RECONSTRUCTION OF SEA WALL AND DOCK @ OWLS HEAD WWTP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Mar 2030 | Jun 2030
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-95-L | REPLACE #3 ENGINE GENERATOR/SUPPORT SYS. @ OWLS HEAD WPCP | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Feb 2021
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-95-L | REPLACE #3 ENGINE GENERATOR/SUPPORT SYS. @ OWLS HEAD WPCP | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Feb 2021 | Feb 2022
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-95-L | REPLACE #3 ENGINE GENERATOR/SUPPORT SYS. @ OWLS HEAD WPCP | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Feb 2022 | Aug 2023
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-95-L | REPLACE #3 ENGINE GENERATOR/SUPPORT SYS. @ OWLS HEAD WPCP | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Aug 2023 | May 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-95-L | REPLACE #3 ENGINE GENERATOR/SUPPORT SYS. @ OWLS HEAD WPCP | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | May 2024 | May 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-95-L | REPLACE #3 ENGINE GENERATOR/SUPPORT SYS. @ OWLS HEAD WPCP | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | May 2025 | Apr 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-95-L | REPLACE #3 ENGINE GENERATOR/SUPPORT SYS. @ OWLS HEAD WPCP | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2026 | Apr 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-95-L | REPLACE #3 ENGINE GENERATOR/SUPPORT SYS. @ OWLS HEAD WPCP | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Apr 2027 | Jan 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-95-L | REPLACE #3 ENGINE GENERATOR/SUPPORT SYS. @ OWLS HEAD WPCP | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Jan 2028 | Jul 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-95-L | REPLACE #3 ENGINE GENERATOR/SUPPORT SYS. @ OWLS HEAD WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Jul 2028 | Oct 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-315 | RECONSTRUCTION OF THE VAN BRUNT PUMPING STATION | 1 | DEVELOP SCOPE | Jul 2016 | Mar 2017 | Jul 2016 | Mar 2017
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-315 | RECONSTRUCTION OF THE VAN BRUNT PUMPING STATION | 2 | PRELIMINARY DESIGN | Mar 2017 | Mar 2018 | Mar 2017 | Mar 2018
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-315 | RECONSTRUCTION OF THE VAN BRUNT PUMPING STATION | 3 | FINAL DESIGN | Mar 2018 | Sep 2019 | Mar 2018 | Sep 2019
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-315 | RECONSTRUCTION OF THE VAN BRUNT PUMPING STATION | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Jun 2020 | Sep 2019 | Jun 2020
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-315 | RECONSTRUCTION OF THE VAN BRUNT PUMPING STATION | 5 | CONSTRUCTION TO 25% | Jun 2020 | Jun 2021 | Jun 2020 | Jun 2021
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-315 | RECONSTRUCTION OF THE VAN BRUNT PUMPING STATION | 6 | CONSTRUCTION TO 50% | Jun 2021 | May 2022 | Jun 2021 | May 2022
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-315 | RECONSTRUCTION OF THE VAN BRUNT PUMPING STATION | 7 | CONSTRUCTION TO 75% | May 2022 | May 2023 | May 2022 | May 2023
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-315 | RECONSTRUCTION OF THE VAN BRUNT PUMPING STATION | 8 | ORIGINAL EQUIP & FURNISHING | May 2023 | Feb 2024 | May 2023 | Feb 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-315 | RECONSTRUCTION OF THE VAN BRUNT PUMPING STATION | 9 | SUBSTANTIAL COMPLETION | Feb 2024 | Aug 2024 | Feb 2024 | Aug 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-315 | RECONSTRUCTION OF THE VAN BRUNT PUMPING STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2024 | Nov 2024 | Aug 2024 | Nov 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-316 | RECONSTRUCTION OF AVENUE U PUMPING STATION BROOKLYN | 1 | DEVELOP SCOPE | Jul 2017 | Mar 2018 | Jul 2017 | Mar 2018
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-316 | RECONSTRUCTION OF AVENUE U PUMPING STATION BROOKLYN | 2 | PRELIMINARY DESIGN | Mar 2018 | Mar 2019 | Mar 2018 | Mar 2019
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-316 | RECONSTRUCTION OF AVENUE U PUMPING STATION BROOKLYN | 3 | FINAL DESIGN | Mar 2019 | Sep 2020 | Mar 2019 | Sep 2020
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-316 | RECONSTRUCTION OF AVENUE U PUMPING STATION BROOKLYN | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2020 | Jun 2021 | Sep 2020 | Jun 2021
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-316 | RECONSTRUCTION OF AVENUE U PUMPING STATION BROOKLYN | 5 | CONSTRUCTION TO 25% | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-316 | RECONSTRUCTION OF AVENUE U PUMPING STATION BROOKLYN | 6 | CONSTRUCTION TO 50% | Jun 2022 | May 2023 | Jun 2022 | May 2023
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-316 | RECONSTRUCTION OF AVENUE U PUMPING STATION BROOKLYN | 7 | CONSTRUCTION TO 75% | May 2023 | May 2024 | May 2023 | May 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-316 | RECONSTRUCTION OF AVENUE U PUMPING STATION BROOKLYN | 8 | ORIGINAL EQUIP & FURNISHING | May 2024 | Feb 2025 | May 2024 | Feb 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-316 | RECONSTRUCTION OF AVENUE U PUMPING STATION BROOKLYN | 9 | SUBSTANTIAL COMPLETION | Feb 2025 | Aug 2025 | Feb 2025 | Aug 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-316 | RECONSTRUCTION OF AVENUE U PUMPING STATION BROOKLYN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2025 | Nov 2025 | Aug 2025 | Nov 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-318 | RECONSTRUCTION OF PAERDEGAT PUMPING STATION, BROOKLYN, N.Y. | 1 | DEVELOP SCOPE | Jul 2017 | Mar 2018 | Jul 2017 | Mar 2018
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-318 | RECONSTRUCTION OF PAERDEGAT PUMPING STATION, BROOKLYN, N.Y. | 2 | PRELIMINARY DESIGN | Mar 2018 | Mar 2019 | Mar 2018 | Mar 2019
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-318 | RECONSTRUCTION OF PAERDEGAT PUMPING STATION, BROOKLYN, N.Y. | 3 | FINAL DESIGN | Mar 2019 | Sep 2020 | Mar 2019 | Sep 2020
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-318 | RECONSTRUCTION OF PAERDEGAT PUMPING STATION, BROOKLYN, N.Y. | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2020 | Jun 2021 | Sep 2020 | Jun 2021
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-318 | RECONSTRUCTION OF PAERDEGAT PUMPING STATION, BROOKLYN, N.Y. | 5 | CONSTRUCTION TO 25% | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-318 | RECONSTRUCTION OF PAERDEGAT PUMPING STATION, BROOKLYN, N.Y. | 6 | CONSTRUCTION TO 50% | Jun 2022 | May 2023 | Jun 2022 | May 2023
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-318 | RECONSTRUCTION OF PAERDEGAT PUMPING STATION, BROOKLYN, N.Y. | 7 | CONSTRUCTION TO 75% | May 2023 | May 2024 | May 2023 | May 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-318 | RECONSTRUCTION OF PAERDEGAT PUMPING STATION, BROOKLYN, N.Y. | 8 | ORIGINAL EQUIP & FURNISHING | May 2024 | Feb 2025 | May 2024 | Feb 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-318 | RECONSTRUCTION OF PAERDEGAT PUMPING STATION, BROOKLYN, N.Y. | 9 | SUBSTANTIAL COMPLETION | Feb 2025 | Aug 2025 | Feb 2025 | Aug 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-318 | RECONSTRUCTION OF PAERDEGAT PUMPING STATION, BROOKLYN, N.Y. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2025 | Nov 2025 | Aug 2025 | Nov 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-097 | Replacement of MCC Buckets, Wires & Conduits for the FT | 1 | FINAL DESIGN | Jun 2025 | Nov 2026 | Jun 2025 | Nov 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-097 | Replacement of MCC Buckets, Wires & Conduits for the FT | 2 | CONSTRUCTION TO 25% | Nov 2026 | Jul 2027 | Nov 2026 | Jul 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-097 | Replacement of MCC Buckets, Wires & Conduits for the FT | 3 | CONSTRUCTION TO 50% | Jul 2027 | Mar 2028 | Jul 2027 | Mar 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-097 | Replacement of MCC Buckets, Wires & Conduits for the FT | 4 | CONSTRUCTION TO 75% | Mar 2028 | Nov 2028 | Mar 2028 | Nov 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-80-L | TRC - DISINFECTION SYSTEM REHABILITATION AT RED HOOK WPCP | 1 | FINAL DESIGN | Jun 2025 | Nov 2026 | Jun 2023 | Feb 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-80-L | TRC - DISINFECTION SYSTEM REHABILITATION AT RED HOOK WPCP | 2 | CONSTRUCTION TO 25% | Nov 2026 | Jul 2027 | Feb 2024 | Feb 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-80-L | TRC - DISINFECTION SYSTEM REHABILITATION AT RED HOOK WPCP | 3 | CONSTRUCTION TO 50% | Jul 2027 | Mar 2028 | Feb 2025 | Aug 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-80-L | TRC - DISINFECTION SYSTEM REHABILITATION AT RED HOOK WPCP | 4 | CONSTRUCTION TO 75% | Mar 2028 | Nov 2028 | Aug 2026 | May 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-80-L | TRC - DISINFECTION SYSTEM REHABILITATION AT RED HOOK WPCP | 5 | CONSTRUCTION TO 25% | Mar 2028 | Nov 2028 | May 2027 | May 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-80-L | TRC - DISINFECTION SYSTEM REHABILITATION AT RED HOOK WPCP | 6 | CONSTRUCTION TO 50% | Mar 2028 | Nov 2028 | May 2028 | Apr 2029
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-80-L | TRC - DISINFECTION SYSTEM REHABILITATION AT RED HOOK WPCP | 7 | CONSTRUCTION TO 75% | Mar 2028 | Nov 2028 | Apr 2029 | Apr 2030
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-80-L | TRC - DISINFECTION SYSTEM REHABILITATION AT RED HOOK WPCP | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2028 | Nov 2028 | Apr 2030 | Jan 2031
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-80-L | TRC - DISINFECTION SYSTEM REHABILITATION AT RED HOOK WPCP | 9 | SUBSTANTIAL COMPLETION | Mar 2028 | Nov 2028 | Jan 2031 | Jul 2031
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-80-L | TRC - DISINFECTION SYSTEM REHABILITATION AT RED HOOK WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2028 | Nov 2028 | Jul 2031 | Oct 2031
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-83 | REPLACE MAIN SEWAGE PUMPS AT RED HOOK WPCP | 1 | FINAL DESIGN | Jun 2022 | Nov 2023 | Jun 2020 | Feb 2021
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-83 | REPLACE MAIN SEWAGE PUMPS AT RED HOOK WPCP | 2 | CONSTRUCTION TO 25% | Nov 2023 | Jul 2024 | Feb 2021 | Feb 2022
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-83 | REPLACE MAIN SEWAGE PUMPS AT RED HOOK WPCP | 3 | CONSTRUCTION TO 50% | Jul 2024 | Mar 2025 | Feb 2022 | Aug 2023
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-83 | REPLACE MAIN SEWAGE PUMPS AT RED HOOK WPCP | 4 | CONSTRUCTION TO 75% | Mar 2025 | Nov 2025 | Aug 2023 | May 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-83 | REPLACE MAIN SEWAGE PUMPS AT RED HOOK WPCP | 5 | CONSTRUCTION TO 25% | Mar 2025 | Nov 2025 | May 2024 | May 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-83 | REPLACE MAIN SEWAGE PUMPS AT RED HOOK WPCP | 6 | CONSTRUCTION TO 50% | Mar 2025 | Nov 2025 | May 2025 | Apr 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-83 | REPLACE MAIN SEWAGE PUMPS AT RED HOOK WPCP | 7 | CONSTRUCTION TO 75% | Mar 2025 | Nov 2025 | May 2026 | Apr 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-83 | REPLACE MAIN SEWAGE PUMPS AT RED HOOK WPCP | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2025 | Nov 2025 | Apr 2027 | Jan 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-83 | REPLACE MAIN SEWAGE PUMPS AT RED HOOK WPCP | 9 | SUBSTANTIAL COMPLETION | Mar 2025 | Nov 2025 | Jan 2028 | Jul 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-83 | REPLACE MAIN SEWAGE PUMPS AT RED HOOK WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Nov 2025 | Jul 2028 | Oct 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SAND26W | STORM MITIGATION WORK ATTHE 26TH WARD WPCP | 1 | DEVELOP SCOPE | Jun 2020 | Feb 2021 | Jun 2024 | Feb 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SAND26W | STORM MITIGATION WORK ATTHE 26TH WARD WPCP | 2 | PRELIMINARY DESIGN | Feb 2021 | Feb 2022 | Feb 2025 | Feb 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SAND26W | STORM MITIGATION WORK ATTHE 26TH WARD WPCP | 3 | FINAL DESIGN | Feb 2022 | Aug 2023 | Feb 2026 | Aug 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SAND26W | STORM MITIGATION WORK ATTHE 26TH WARD WPCP | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2023 | May 2024 | Aug 2027 | May 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SAND26W | STORM MITIGATION WORK ATTHE 26TH WARD WPCP | 5 | CONSTRUCTION TO 25% | May 2024 | May 2025 | May 2028 | May 2029
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SAND26W | STORM MITIGATION WORK ATTHE 26TH WARD WPCP | 6 | CONSTRUCTION TO 50% | May 2025 | Apr 2026 | May 2029 | Apr 2030
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SAND26W | STORM MITIGATION WORK ATTHE 26TH WARD WPCP | 7 | CONSTRUCTION TO 75% | May 2026 | Apr 2027 | May 2030 | Apr 2031
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SAND26W | STORM MITIGATION WORK ATTHE 26TH WARD WPCP | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2027 | Jan 2028 | Apr 2031 | Jan 2032
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SAND26W | STORM MITIGATION WORK ATTHE 26TH WARD WPCP | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Jul 2028 | Jan 2032 | Jul 2032
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SAND26W | STORM MITIGATION WORK ATTHE 26TH WARD WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2028 | Oct 2028 | Jul 2032 | Oct 2032
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDCI | STORM MITIGATION WORK ATTHE CONEY ISLAND WPCP | 1 | DEVELOP SCOPE | Jun 2020 | Feb 2021 | Jun 2020 | Feb 2021
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDCI | STORM MITIGATION WORK ATTHE CONEY ISLAND WPCP | 2 | PRELIMINARY DESIGN | Feb 2021 | Feb 2022 | Feb 2021 | Feb 2022
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDCI | STORM MITIGATION WORK ATTHE CONEY ISLAND WPCP | 3 | FINAL DESIGN | Feb 2022 | Aug 2023 | Feb 2022 | Aug 2023
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDCI | STORM MITIGATION WORK ATTHE CONEY ISLAND WPCP | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2023 | May 2024 | Aug 2023 | May 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDCI | STORM MITIGATION WORK ATTHE CONEY ISLAND WPCP | 5 | CONSTRUCTION TO 25% | May 2024 | May 2025 | May 2024 | May 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDCI | STORM MITIGATION WORK ATTHE CONEY ISLAND WPCP | 6 | CONSTRUCTION TO 50% | May 2025 | Apr 2026 | May 2025 | Apr 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDCI | STORM MITIGATION WORK ATTHE CONEY ISLAND WPCP | 7 | CONSTRUCTION TO 75% | May 2026 | Apr 2027 | May 2026 | Apr 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDCI | STORM MITIGATION WORK ATTHE CONEY ISLAND WPCP | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2027 | Jan 2028 | Apr 2027 | Jan 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDCI | STORM MITIGATION WORK ATTHE CONEY ISLAND WPCP | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Jul 2028 | Jan 2028 | Jul 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDCI | STORM MITIGATION WORK ATTHE CONEY ISLAND WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2028 | Oct 2028 | Jul 2028 | Oct 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOH | STORM MITIGATION WORK AT THE OWLS HEAD WPCP (HMP) | 1 | DEVELOP SCOPE | Oct 2020 | Jun 2021 | Oct 2020 | Jun 2021
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOH | STORM MITIGATION WORK AT THE OWLS HEAD WPCP (HMP) | 2 | PRELIMINARY DESIGN | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOH | STORM MITIGATION WORK AT THE OWLS HEAD WPCP (HMP) | 3 | FINAL DESIGN | Jun 2022 | Dec 2023 | Jun 2022 | Dec 2023
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOH | STORM MITIGATION WORK AT THE OWLS HEAD WPCP (HMP) | 4 | BID AWARD AND REGISTER CONTRCT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOH | STORM MITIGATION WORK AT THE OWLS HEAD WPCP (HMP) | 5 | CONSTRUCTION TO 25% | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOH | STORM MITIGATION WORK AT THE OWLS HEAD WPCP (HMP) | 6 | CONSTRUCTION TO 50% | Sep 2025 | Aug 2026 | Sep 2025 | Aug 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOH | STORM MITIGATION WORK AT THE OWLS HEAD WPCP (HMP) | 7 | CONSTRUCTION TO 75% | Aug 2026 | Aug 2027 | Aug 2026 | Aug 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOH | STORM MITIGATION WORK AT THE OWLS HEAD WPCP (HMP) | 8 | ORIGINAL EQUIP & FURNISHING | Aug 2027 | May 2028 | Aug 2027 | May 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOH | STORM MITIGATION WORK AT THE OWLS HEAD WPCP (HMP) | 9 | SUBSTANTIAL COMPLETION | May 2028 | Nov 2028 | May 2028 | Nov 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOH | STORM MITIGATION WORK AT THE OWLS HEAD WPCP (HMP) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2028 | Feb 2029 | Nov 2028 | Feb 2029
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SE883 | Storm & Comb Sanitary SE Construction in Cropsey Ave BKLYN | 1 | DEVELOP SCOPE | Aug 2024 | Nov 2024 | Jun 2028 | Aug 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SE883 | Storm & Comb Sanitary SE Construction in Cropsey Ave BKLYN | 2 | PRELIMINARY DESIGN | Nov 2024 | Mar 2025 | Aug 2028 | Dec 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SE883 | Storm & Comb Sanitary SE Construction in Cropsey Ave BKLYN | 3 | FINAL DESIGN | Mar 2025 | Sep 2025 | Dec 2028 | Jun 2029
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SE883 | Storm & Comb Sanitary SE Construction in Cropsey Ave BKLYN | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2025 | Dec 2025 | Jun 2029 | Sep 2029
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SE883 | Storm & Comb Sanitary SE Construction in Cropsey Ave BKLYN | 5 | CONSTRUCTION TO 25% | Dec 2025 | Apr 2026 | Sep 2029 | Jan 2030
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SE883 | Storm & Comb Sanitary SE Construction in Cropsey Ave BKLYN | 6 | CONSTRUCTION TO 50% | Apr 2026 | Aug 2026 | Jan 2030 | May 2030
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SE883 | Storm & Comb Sanitary SE Construction in Cropsey Ave BKLYN | 7 | CONSTRUCTION TO 75% | Aug 2026 | Dec 2026 | May 2030 | Sep 2030
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SE883 | Storm & Comb Sanitary SE Construction in Cropsey Ave BKLYN | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2026 | Mar 2027 | Sep 2030 | Dec 2030
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SE883 | Storm & Comb Sanitary SE Construction in Cropsey Ave BKLYN | 9 | SUBSTANTIAL COMPLETION | Mar 2027 | May 2027 | Dec 2030 | Feb 2031
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SE883 | Storm & Comb Sanitary SE Construction in Cropsey Ave BKLYN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2027 | Jun 2027 | Feb 2031 | Mar 2031
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002387 | Repair of CSO Outfall on Williams Avenue, BKLYN | 1 | DEVELOP SCOPE | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002387 | Repair of CSO Outfall on Williams Avenue, BKLYN | 2 | PRELIMINARY DESIGN | Apr 2025 | Jul 2025 | Apr 2025 | Jul 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002387 | Repair of CSO Outfall on Williams Avenue, BKLYN | 3 | FINAL DESIGN | Jul 2025 | Jan 2026 | Jul 2025 | Jan 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002387 | Repair of CSO Outfall on Williams Avenue, BKLYN | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2026 | Apr 2026 | Jan 2026 | Apr 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002387 | Repair of CSO Outfall on Williams Avenue, BKLYN | 5 | CONSTRUCTION TO 25% | Apr 2026 | Aug 2026 | Apr 2026 | Aug 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002387 | Repair of CSO Outfall on Williams Avenue, BKLYN | 6 | CONSTRUCTION TO 50% | Aug 2026 | Dec 2026 | Aug 2026 | Dec 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002387 | Repair of CSO Outfall on Williams Avenue, BKLYN | 7 | CONSTRUCTION TO 75% | Dec 2026 | Apr 2027 | Dec 2026 | Apr 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002387 | Repair of CSO Outfall on Williams Avenue, BKLYN | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2027 | Jul 2027 | Apr 2027 | Jul 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002387 | Repair of CSO Outfall on Williams Avenue, BKLYN | 9 | SUBSTANTIAL COMPLETION | Jul 2027 | Sep 2027 | Jul 2027 | Sep 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002387 | Repair of CSO Outfall on Williams Avenue, BKLYN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Oct 2027 | Sep 2027 | Oct 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002388 | Upgrade sewers on Ave L between Ocean & Bedford avenue BKLYN | 1 | DEVELOP SCOPE | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002388 | Upgrade sewers on Ave L between Ocean & Bedford avenue BKLYN | 2 | PRELIMINARY DESIGN | Apr 2025 | Jul 2025 | Apr 2025 | Jul 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002388 | Upgrade sewers on Ave L between Ocean & Bedford avenue BKLYN | 3 | FINAL DESIGN | Jul 2025 | Jan 2026 | Jul 2025 | Jan 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002388 | Upgrade sewers on Ave L between Ocean & Bedford avenue BKLYN | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2026 | Apr 2026 | Jan 2026 | Apr 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002388 | Upgrade sewers on Ave L between Ocean & Bedford avenue BKLYN | 5 | CONSTRUCTION TO 25% | Apr 2026 | Aug 2026 | Apr 2026 | Aug 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002388 | Upgrade sewers on Ave L between Ocean & Bedford avenue BKLYN | 6 | CONSTRUCTION TO 50% | Aug 2026 | Dec 2026 | Aug 2026 | Dec 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002388 | Upgrade sewers on Ave L between Ocean & Bedford avenue BKLYN | 7 | CONSTRUCTION TO 75% | Dec 2026 | Apr 2027 | Dec 2026 | Apr 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002388 | Upgrade sewers on Ave L between Ocean & Bedford avenue BKLYN | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2027 | Jul 2027 | Apr 2027 | Jul 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002388 | Upgrade sewers on Ave L between Ocean & Bedford avenue BKLYN | 9 | SUBSTANTIAL COMPLETION | Jul 2027 | Sep 2027 | Jul 2027 | Sep 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002388 | Upgrade sewers on Ave L between Ocean & Bedford avenue BKLYN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Oct 2027 | Sep 2027 | Oct 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002392 | Install of combined sewers & dist WM work along 3rd Ave MH | 1 | DEVELOP SCOPE | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002392 | Install of combined sewers & dist WM work along 3rd Ave MH | 2 | PRELIMINARY DESIGN | Apr 2026 | Jul 2026 | Apr 2026 | Jul 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002392 | Install of combined sewers & dist WM work along 3rd Ave MH | 3 | FINAL DESIGN | Jul 2026 | Jan 2027 | Jul 2026 | Jan 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002392 | Install of combined sewers & dist WM work along 3rd Ave MH | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2027 | Apr 2027 | Jan 2027 | Apr 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002392 | Install of combined sewers & dist WM work along 3rd Ave MH | 5 | CONSTRUCTION TO 25% | Apr 2027 | Aug 2027 | Apr 2027 | Aug 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002392 | Install of combined sewers & dist WM work along 3rd Ave MH | 6 | CONSTRUCTION TO 50% | Aug 2027 | Dec 2027 | Aug 2027 | Dec 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002392 | Install of combined sewers & dist WM work along 3rd Ave MH | 7 | CONSTRUCTION TO 75% | Dec 2027 | Apr 2028 | Dec 2027 | Apr 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002392 | Install of combined sewers & dist WM work along 3rd Ave MH | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2028 | Jul 2028 | Apr 2028 | Jul 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002392 | Install of combined sewers & dist WM work along 3rd Ave MH | 9 | SUBSTANTIAL COMPLETION | Jul 2028 | Sep 2028 | Jul 2028 | Sep 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002392 | Install of combined sewers & dist WM work along 3rd Ave MH | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2028 | Oct 2028 | Sep 2028 | Oct 2028
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002394 | Combined SE & Dist WM Replmt on 7th Ave in Brooklyn | 1 | DEVELOP SCOPE | Aug 2023 | Nov 2023 | Aug 2023 | Nov 2023
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002394 | Combined SE & Dist WM Replmt on 7th Ave in Brooklyn | 2 | PRELIMINARY DESIGN | Nov 2023 | Mar 2024 | Nov 2023 | Mar 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002394 | Combined SE & Dist WM Replmt on 7th Ave in Brooklyn | 3 | FINAL DESIGN | Mar 2024 | Sep 2024 | Mar 2024 | Sep 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002394 | Combined SE & Dist WM Replmt on 7th Ave in Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002394 | Combined SE & Dist WM Replmt on 7th Ave in Brooklyn | 5 | CONSTRUCTION TO 25% | Dec 2024 | Apr 2025 | Dec 2024 | Apr 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002394 | Combined SE & Dist WM Replmt on 7th Ave in Brooklyn | 6 | CONSTRUCTION TO 50% | Apr 2025 | Aug 2025 | Apr 2025 | Aug 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002394 | Combined SE & Dist WM Replmt on 7th Ave in Brooklyn | 7 | CONSTRUCTION TO 75% | Aug 2025 | Dec 2025 | Aug 2025 | Dec 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002394 | Combined SE & Dist WM Replmt on 7th Ave in Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2025 | Mar 2026 | Dec 2025 | Mar 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002394 | Combined SE & Dist WM Replmt on 7th Ave in Brooklyn | 9 | SUBSTANTIAL COMPLETION | Mar 2026 | May 2026 | Mar 2026 | May 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002394 | Combined SE & Dist WM Replmt on 7th Ave in Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2026 | Jun 2026 | May 2026 | Jun 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK200387 | Installation for tidegate on 9'6" x 5' sewer at Ave K BKLYN | 1 | DEVELOP SCOPE | Sep 2022 | Nov 2022 | Sep 2022 | Nov 2022
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK200387 | Installation for tidegate on 9'6" x 5' sewer at Ave K BKLYN | 2 | PRELIMINARY DESIGN | Dec 2022 | Mar 2023 | Dec 2022 | Mar 2023
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK200387 | Installation for tidegate on 9'6" x 5' sewer at Ave K BKLYN | 3 | FINAL DESIGN | Mar 2023 | Sep 2023 | Mar 2023 | Sep 2023
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK200387 | Installation for tidegate on 9'6" x 5' sewer at Ave K BKLYN | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2023 | Dec 2023 | Sep 2023 | Dec 2023
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK200387 | Installation for tidegate on 9'6" x 5' sewer at Ave K BKLYN | 5 | CONSTRUCTION TO 25% | Dec 2023 | Apr 2024 | Dec 2023 | Apr 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK200387 | Installation for tidegate on 9'6" x 5' sewer at Ave K BKLYN | 6 | CONSTRUCTION TO 50% | Apr 2024 | Aug 2024 | Apr 2024 | Aug 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK200387 | Installation for tidegate on 9'6" x 5' sewer at Ave K BKLYN | 7 | CONSTRUCTION TO 75% | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK200387 | Installation for tidegate on 9'6" x 5' sewer at Ave K BKLYN | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2024 | Mar 2025 | Dec 2024 | Mar 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK200387 | Installation for tidegate on 9'6" x 5' sewer at Ave K BKLYN | 9 | SUBSTANTIAL COMPLETION | Mar 2025 | May 2025 | Mar 2025 | May 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK200387 | Installation for tidegate on 9'6" x 5' sewer at Ave K BKLYN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2025 | Jun 2025 | May 2025 | Jun 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK20072 | Rplcmnt of Sanitary & Storm Sewers & WM on Homecrest Ave BK | 1 | DEVELOP SCOPE | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK20072 | Rplcmnt of Sanitary & Storm Sewers & WM on Homecrest Ave BK | 2 | PRELIMINARY DESIGN | Apr 2025 | Jul 2025 | Apr 2025 | Jul 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK20072 | Rplcmnt of Sanitary & Storm Sewers & WM on Homecrest Ave BK | 3 | FINAL DESIGN | Jul 2025 | Jan 2026 | Jul 2025 | Jan 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK20072 | Rplcmnt of Sanitary & Storm Sewers & WM on Homecrest Ave BK | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2026 | Apr 2026 | Jan 2026 | Apr 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK20072 | Rplcmnt of Sanitary & Storm Sewers & WM on Homecrest Ave BK | 5 | CONSTRUCTION TO 25% | Apr 2026 | Aug 2026 | Apr 2026 | Aug 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK20072 | Rplcmnt of Sanitary & Storm Sewers & WM on Homecrest Ave BK | 6 | CONSTRUCTION TO 50% | Aug 2026 | Dec 2026 | Aug 2026 | Dec 2026
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK20072 | Rplcmnt of Sanitary & Storm Sewers & WM on Homecrest Ave BK | 7 | CONSTRUCTION TO 75% | Dec 2026 | Apr 2027 | Dec 2026 | Apr 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK20072 | Rplcmnt of Sanitary & Storm Sewers & WM on Homecrest Ave BK | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2027 | Jul 2027 | Apr 2027 | Jul 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK20072 | Rplcmnt of Sanitary & Storm Sewers & WM on Homecrest Ave BK | 9 | SUBSTANTIAL COMPLETION | Jul 2027 | Sep 2027 | Jul 2027 | Sep 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK20072 | Rplcmnt of Sanitary & Storm Sewers & WM on Homecrest Ave BK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Oct 2027 | Sep 2027 | Oct 2027
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-CI | STEP FEED BNR AT CONEY ISLAND & ROCKAWAY WPCPs | 1 | DEVELOP SCOPE | Jul 2013 | Dec 2013 | Jul 2013 | Mar 2014
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-CI | STEP FEED BNR AT CONEY ISLAND & ROCKAWAY WPCPs | 2 | PRELIMINARY DESIGN | Jan 2014 | Nov 2016 | Mar 2014 | Mar 2015
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-CI | STEP FEED BNR AT CONEY ISLAND & ROCKAWAY WPCPs | 3 | FINAL DESIGN | Dec 2016 | Nov 2017 | Mar 2015 | Sep 2016
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-CI | STEP FEED BNR AT CONEY ISLAND & ROCKAWAY WPCPs | 4 | BID AWARD AND REGISTER CONTRCT | Dec 2017 | Oct 2018 | Sep 2016 | Jun 2017
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-CI | STEP FEED BNR AT CONEY ISLAND & ROCKAWAY WPCPs | 5 | CONSTRUCTION TO 25% | Oct 2018 | Jun 2019 | Jun 2017 | Jun 2018
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-CI | STEP FEED BNR AT CONEY ISLAND & ROCKAWAY WPCPs | 6 | CONSTRUCTION TO 50% | Jun 2019 | Mar 2020 | Jun 2018 | May 2019
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-CI | STEP FEED BNR AT CONEY ISLAND & ROCKAWAY WPCPs | 7 | CONSTRUCTION TO 75% | Mar 2020 | Dec 2020 | May 2019 | May 2020
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-CI | STEP FEED BNR AT CONEY ISLAND & ROCKAWAY WPCPs | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2020 | Jun 2021 | May 2020 | Feb 2021
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-CI | STEP FEED BNR AT CONEY ISLAND & ROCKAWAY WPCPs | 9 | SUBSTANTIAL COMPLETION | Jun 2021 | Nov 2021 | Feb 2021 | Aug 2025
20231026 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-CI | STEP FEED BNR AT CONEY ISLAND & ROCKAWAY WPCPs | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2021 | Dec 2022 | Aug 2025 | Nov 2025
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | ACEDOS231 | BK 01 04 District Garage Water Heaters | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2023 | Jun 2023 | Jun 2023
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | ACEDOS231 | BK 01 04 District Garage Water Heaters | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | ACEDOS231 | BK 01 04 District Garage Water Heaters | 3 | CONSTRUCTION TO 50% | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | ACEDOS231 | BK 01 04 District Garage Water Heaters | 4 | CONSTRUCTION TO 75% | Feb 2024 | May 2024 | Feb 2024 | May 2024
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | ACEDOS231 | BK 01 04 District Garage Water Heaters | 5 | SUBSTANTIAL COMPLETION | May 2024 | Jul 2024 | May 2024 | Jul 2024
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | ACEDOS231 | BK 01 04 District Garage Water Heaters | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | APIDSBK11 | DSNY ROADMAP ENERGY EFF | 1 | DEVELOP SCOPE | Feb 2023 | May 2023 | Feb 2023 | May 2023
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | APIDSBK11 | DSNY ROADMAP ENERGY EFF | 2 | PRELIMINARY DESIGN | May 2023 | Nov 2023 | May 2023 | Nov 2023
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | APIDSBK11 | DSNY ROADMAP ENERGY EFF | 3 | FINAL DESIGN | Nov 2023 | Jun 2024 | Nov 2023 | Jun 2024
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | APIDSBK11 | DSNY ROADMAP ENERGY EFF | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Jun 2025 | Jun 2024 | Jun 2025
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | APIDSBK11 | DSNY ROADMAP ENERGY EFF | 5 | CONSTRUCTION TO 25% | Jun 2025 | Dec 2025 | Jun 2025 | Dec 2025
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | APIDSBK11 | DSNY ROADMAP ENERGY EFF | 6 | CONSTRUCTION TO 50% | Dec 2025 | Jun 2026 | Dec 2025 | Jun 2026
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | APIDSBK11 | DSNY ROADMAP ENERGY EFF | 7 | CONSTRUCTION TO 75% | Jun 2026 | Dec 2026 | Jun 2026 | Dec 2026
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | APIDSBK11 | DSNY ROADMAP ENERGY EFF | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2026 | Mar 2027 | Dec 2026 | Mar 2027
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | APIDSBK11 | DSNY ROADMAP ENERGY EFF | 9 | SUBSTANTIAL COMPLETION | Mar 2027 | Mar 2028 | Mar 2027 | Mar 2028
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | APIDSBK11 | DSNY ROADMAP ENERGY EFF | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2028 | Mar 2029 | Mar 2028 | Mar 2029
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-264Y | Brooklyn Cioffe Borough Shop Roof Replacement | 1 | DEVELOP SCOPE | Jul 2016 | Sep 2016 | Jul 2016 | Sep 2016
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-264Y | Brooklyn Cioffe Borough Shop Roof Replacement | 2 | PRELIMINARY DESIGN | Sep 2016 | Sep 2017 | Sep 2016 | Sep 2017
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-264Y | Brooklyn Cioffe Borough Shop Roof Replacement | 3 | FINAL DESIGN | Sep 2017 | Sep 2018 | Sep 2017 | Sep 2018
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-264Y | Brooklyn Cioffe Borough Shop Roof Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-264Y | Brooklyn Cioffe Borough Shop Roof Replacement | 5 | CONSTRUCTION TO 25% | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-264Y | Brooklyn Cioffe Borough Shop Roof Replacement | 6 | CONSTRUCTION TO 50% | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-264Y | Brooklyn Cioffe Borough Shop Roof Replacement | 7 | CONSTRUCTION TO 75% | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-264Y | Brooklyn Cioffe Borough Shop Roof Replacement | 8 | SUBSTANTIAL COMPLETION | Sep 2022 | Jun 2025 | Sep 2022 | Jun 2025
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-264Y | Brooklyn Cioffe Borough Shop Roof Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2024 | Oct 2025 | Jun 2024 | Oct 2025
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-265A | Brooklyn 12 Garage Damaged Brick Wall Fence Replacement | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-265A | Brooklyn 12 Garage Damaged Brick Wall Fence Replacement | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-265A | Brooklyn 12 Garage Damaged Brick Wall Fence Replacement | 3 | FINAL DESIGN | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-265A | Brooklyn 12 Garage Damaged Brick Wall Fence Replacement | 4 | BID AWARD AND REGISTER CONTRCT | May 2024 | Oct 2024 | May 2024 | Oct 2024
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-265A | Brooklyn 12 Garage Damaged Brick Wall Fence Replacement | 5 | CONSTRUCTION TO 25% | Oct 2024 | Apr 2025 | Oct 2024 | Apr 2025
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-265A | Brooklyn 12 Garage Damaged Brick Wall Fence Replacement | 6 | CONSTRUCTION TO 50% | Apr 2025 | Oct 2025 | Apr 2025 | Oct 2025
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-265A | Brooklyn 12 Garage Damaged Brick Wall Fence Replacement | 7 | CONSTRUCTION TO 75% | Oct 2025 | Apr 2026 | Oct 2025 | Apr 2026
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-265A | Brooklyn 12 Garage Damaged Brick Wall Fence Replacement | 8 | SUBSTANTIAL COMPLETION | Apr 2026 | Oct 2026 | Apr 2026 | Oct 2026
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-265A | Brooklyn 12 Garage Damaged Brick Wall Fence Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2026 | Jul 2027 | Oct 2026 | Jul 2027
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-265B | Brooklyn 11 Site Safety Lighting | 1 | DEVELOP SCOPE | Jun 2023 | Jul 2023 | Jun 2023 | Jul 2023
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-265B | Brooklyn 11 Site Safety Lighting | 2 | PRELIMINARY DESIGN | Jul 2023 | Sep 2023 | Jul 2023 | Sep 2023
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-265B | Brooklyn 11 Site Safety Lighting | 3 | FINAL DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-265B | Brooklyn 11 Site Safety Lighting | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2024 | Jun 2024 | Jan 2024 | Jun 2024
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-265B | Brooklyn 11 Site Safety Lighting | 5 | CONSTRUCTION TO 25% | Jul 2024 | Sep 2024 | Jul 2024 | Sep 2024
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-265B | Brooklyn 11 Site Safety Lighting | 6 | CONSTRUCTION TO 50% | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-265B | Brooklyn 11 Site Safety Lighting | 7 | CONSTRUCTION TO 75% | Dec 2024 | Apr 2025 | Dec 2024 | Apr 2025
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-265B | Brooklyn 11 Site Safety Lighting | 8 | SUBSTANTIAL COMPLETION | Apr 2025 | Sep 2025 | Apr 2025 | Sep 2025
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-265B | Brooklyn 11 Site Safety Lighting | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | May 2026 | Sep 2025 | May 2026
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-380J | Brooklyn 1 and 4 Hot Water Heaters Replacement | 1 | DEVELOP SCOPE | Mar 2022 | Apr 2022 | Mar 2022 | Apr 2022
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-380J | Brooklyn 1 and 4 Hot Water Heaters Replacement | 2 | PRELIMINARY DESIGN | Apr 2022 | Jun 2022 | Apr 2022 | Jun 2022
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-380J | Brooklyn 1 and 4 Hot Water Heaters Replacement | 3 | FINAL DESIGN | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-380J | Brooklyn 1 and 4 Hot Water Heaters Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2022 | Nov 2022 | Aug 2022 | Nov 2022
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-380J | Brooklyn 1 and 4 Hot Water Heaters Replacement | 5 | CONSTRUCTION TO 25% | Nov 2022 | Mar 2023 | Nov 2022 | Mar 2023
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-380J | Brooklyn 1 and 4 Hot Water Heaters Replacement | 6 | CONSTRUCTION TO 50% | Mar 2023 | Jul 2023 | Mar 2023 | Jul 2023
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-380J | Brooklyn 1 and 4 Hot Water Heaters Replacement | 7 | CONSTRUCTION TO 75% | Jul 2023 | Nov 2023 | Jul 2023 | Nov 2023
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-380J | Brooklyn 1 and 4 Hot Water Heaters Replacement | 8 | SUBSTANTIAL COMPLETION | Nov 2023 | Apr 2024 | Nov 2023 | Apr 2024
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-380J | Brooklyn 1 and 4 Hot Water Heaters Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2024 | Apr 2025 | Apr 2024 | Apr 2025
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-383G | BROOKLYN CIOFFE SHOP HVAC REPLACEMENT | 1 | DEVELOP SCOPE | Aug 2008 | Nov 2008 | Aug 2008 | Nov 2008
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-383G | BROOKLYN CIOFFE SHOP HVAC REPLACEMENT | 2 | PRELIMINARY DESIGN | Nov 2008 | May 2009 | Nov 2008 | May 2009
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-383G | BROOKLYN CIOFFE SHOP HVAC REPLACEMENT | 3 | FINAL DESIGN | May 2009 | Dec 2009 | May 2009 | Dec 2009
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-383G | BROOKLYN CIOFFE SHOP HVAC REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | Dec 2009 | Oct 2010 | Dec 2009 | Oct 2016
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-383G | BROOKLYN CIOFFE SHOP HVAC REPLACEMENT | 5 | CONSTRUCTION TO 25% | Oct 2010 | Oct 2011 | Oct 2016 | Oct 2016
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-383G | BROOKLYN CIOFFE SHOP HVAC REPLACEMENT | 6 | CONSTRUCTION TO 50% | Oct 2011 | Oct 2012 | Oct 2016 | Oct 2016
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-383G | BROOKLYN CIOFFE SHOP HVAC REPLACEMENT | 7 | CONSTRUCTION TO 75% | Oct 2012 | Oct 2013 | Oct 2016 | Oct 2016
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-383G | BROOKLYN CIOFFE SHOP HVAC REPLACEMENT | 8 | SUBSTANTIAL COMPLETION | Oct 2013 | Oct 2014 | Oct 2016 | Nov 2023
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-383G | BROOKLYN CIOFFE SHOP HVAC REPLACEMENT | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2014 | Sep 2016 | Nov 2023 | Nov 2024
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-449D | Brooklyn 15 Oil Water Separator | 1 | DEVELOP SCOPE | Apr 2021 | May 2021 | Apr 2021 | Jul 2021
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-449D | Brooklyn 15 Oil Water Separator | 2 | PRELIMINARY DESIGN | May 2021 | Jul 2021 | Jul 2022 | Aug 2023
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-449D | Brooklyn 15 Oil Water Separator | 3 | FINAL DESIGN | Jul 2021 | Sep 2021 | Aug 2023 | May 2024
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-449D | Brooklyn 15 Oil Water Separator | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2021 | Dec 2021 | May 2024 | Feb 2025
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-449D | Brooklyn 15 Oil Water Separator | 5 | CONSTRUCTION TO 25% | Dec 2021 | Mar 2022 | Feb 2025 | Nov 2025
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-449D | Brooklyn 15 Oil Water Separator | 6 | CONSTRUCTION TO 50% | Mar 2022 | Jun 2022 | Nov 2025 | Sep 2026
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-449D | Brooklyn 15 Oil Water Separator | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Sep 2026 | Jun 2027
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-449D | Brooklyn 15 Oil Water Separator | 8 | SUBSTANTIAL COMPLETION | Oct 2022 | Mar 2023 | Jun 2027 | Mar 2028
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-449D | Brooklyn 15 Oil Water Separator | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Sep 2023 | Mar 2028 | Dec 2028
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-451 | Brooklyn Greenpoint Warehouse Pump Replacement | 1 | DEVELOP SCOPE | Jan 2018 | Mar 2018 | Jan 2018 | Mar 2018
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-451 | Brooklyn Greenpoint Warehouse Pump Replacement | 2 | PRELIMINARY DESIGN | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2022
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-451 | Brooklyn Greenpoint Warehouse Pump Replacement | 3 | FINAL DESIGN | Jun 2018 | Sep 2018 | Jun 2022 | Sep 2022
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-451 | Brooklyn Greenpoint Warehouse Pump Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2018 | Jan 2019 | Sep 2022 | Jan 2023
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-451 | Brooklyn Greenpoint Warehouse Pump Replacement | 5 | CONSTRUCTION TO 25% | Jan 2019 | May 2019 | Jan 2023 | May 2023
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-451 | Brooklyn Greenpoint Warehouse Pump Replacement | 6 | CONSTRUCTION TO 50% | May 2019 | Sep 2019 | May 2023 | Sep 2023
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-451 | Brooklyn Greenpoint Warehouse Pump Replacement | 7 | CONSTRUCTION TO 75% | Sep 2019 | Mar 2020 | Sep 2023 | Mar 2024
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-451 | Brooklyn Greenpoint Warehouse Pump Replacement | 8 | SUBSTANTIAL COMPLETION | Mar 2020 | Jan 2021 | Mar 2024 | Jan 2025
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-451 | Brooklyn Greenpoint Warehouse Pump Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2021 | Oct 2023 | Jan 2025 | Dec 2027
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464B | Brooklyn 8 Garage Roof and HVAC Replacement | 1 | DEVELOP SCOPE | Jul 2016 | Sep 2016 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464B | Brooklyn 8 Garage Roof and HVAC Replacement | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Aug 2018 | Jul 2019
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464B | Brooklyn 8 Garage Roof and HVAC Replacement | 3 | FINAL DESIGN | Jan 2017 | May 2017 | Jan 2022 | Dec 2023
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464B | Brooklyn 8 Garage Roof and HVAC Replacement | 4 | BID AWARD AND REGISTER CONTRCT | May 2017 | May 2018 | Dec 2023 | Dec 2024
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464B | Brooklyn 8 Garage Roof and HVAC Replacement | 5 | CONSTRUCTION TO 25% | May 2018 | May 2019 | Dec 2024 | Dec 2025
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464B | Brooklyn 8 Garage Roof and HVAC Replacement | 6 | CONSTRUCTION TO 50% | May 2019 | May 2020 | Dec 2025 | Dec 2026
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464B | Brooklyn 8 Garage Roof and HVAC Replacement | 7 | CONSTRUCTION TO 75% | May 2020 | May 2021 | Dec 2026 | Dec 2027
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464B | Brooklyn 8 Garage Roof and HVAC Replacement | 8 | SUBSTANTIAL COMPLETION | May 2021 | Feb 2024 | Dec 2027 | Dec 2028
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464B | Brooklyn 8 Garage Roof and HVAC Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Jun 2024 | Dec 2028 | Dec 2029
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464F | Brooklyn 16 923 Georgia Ave Roof Replacement | 5 | CONSTRUCTION TO 25% | Aug 2019 | Aug 2020 | Aug 2019 | Aug 2020
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464F | Brooklyn 16 923 Georgia Ave Roof Replacement | 6 | CONSTRUCTION TO 50% | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464F | Brooklyn 16 923 Georgia Ave Roof Replacement | 7 | CONSTRUCTION TO 75% | Aug 2021 | Aug 2022 | Aug 2021 | Aug 2022
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464F | Brooklyn 16 923 Georgia Ave Roof Replacement | 8 | SUBSTANTIAL COMPLETION | Aug 2022 | Aug 2023 | Aug 2022 | Aug 2023
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464F | Brooklyn 16 923 Georgia Ave Roof Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2023 | Aug 2024 | Aug 2023 | Aug 2024
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S186-224 | Brooklyn 3 Garage New Construction | 1 | DEVELOP SCOPE | Jan 2004 | Jun 2005 | Jan 2004 | Jun 2005
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S186-224 | Brooklyn 3 Garage New Construction | 2 | PRELIMINARY DESIGN | Jul 2005 | Jan 2007 | Jul 2005 | Jan 2007
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S186-224 | Brooklyn 3 Garage New Construction | 3 | FINAL DESIGN | Jan 2007 | Apr 2007 | Jan 2007 | Aug 2008
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S186-224 | Brooklyn 3 Garage New Construction | 4 | BID AWARD AND REGISTER CONTRCT | May 2007 | Jun 2007 | Sep 2018 | Jun 2019
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S186-224 | Brooklyn 3 Garage New Construction | 5 | CONSTRUCTION TO 25% | Jul 2007 | Dec 2008 | Jul 2019 | May 2021
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S186-224 | Brooklyn 3 Garage New Construction | 6 | CONSTRUCTION TO 50% | Jan 2009 | Dec 2009 | May 2021 | Mar 2022
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S186-224 | Brooklyn 3 Garage New Construction | 7 | CONSTRUCTION TO 75% | Jan 2010 | Dec 2010 | Mar 2022 | Jan 2023
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S186-224 | Brooklyn 3 Garage New Construction | 8 | SUBSTANTIAL COMPLETION | Jan 2011 | Dec 2011 | Jan 2023 | Nov 2023
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S186-224 | Brooklyn 3 Garage New Construction | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2012 | Mar 2013 | Nov 2023 | Jul 2024
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-227R | BROOKLYN 7 /10 SALT SHED ROOF DEMOLITiON | 1 | DEVELOP SCOPE | Jun 2021 | Jul 2021 | Jun 2021 | Jul 2021
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-227R | BROOKLYN 7 /10 SALT SHED ROOF DEMOLITiON | 2 | PRELIMINARY DESIGN | Jul 2021 | Sep 2021 | Jul 2021 | Sep 2021
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-227R | BROOKLYN 7 /10 SALT SHED ROOF DEMOLITiON | 3 | FINAL DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-227R | BROOKLYN 7 /10 SALT SHED ROOF DEMOLITiON | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2022 | Jun 2022 | Jan 2022 | Jun 2022
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-227R | BROOKLYN 7 /10 SALT SHED ROOF DEMOLITiON | 5 | CONSTRUCTION TO 25% | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-227R | BROOKLYN 7 /10 SALT SHED ROOF DEMOLITiON | 6 | CONSTRUCTION TO 50% | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-227R | BROOKLYN 7 /10 SALT SHED ROOF DEMOLITiON | 7 | CONSTRUCTION TO 75% | Dec 2022 | Apr 2023 | Dec 2022 | Apr 2023
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-227R | BROOKLYN 7 /10 SALT SHED ROOF DEMOLITiON | 8 | SUBSTANTIAL COMPLETION | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-227R | BROOKLYN 7 /10 SALT SHED ROOF DEMOLITiON | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403A | Hamilton Avenue MTS Bulkhead | 1 | DEVELOP SCOPE | Jan 2019 | Apr 2019 | Jan 2019 | Apr 2019
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403A | Hamilton Avenue MTS Bulkhead | 2 | PRELIMINARY DESIGN | Apr 2019 | Aug 2019 | Apr 2019 | Aug 2019
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403A | Hamilton Avenue MTS Bulkhead | 3 | FINAL DESIGN | Aug 2019 | Feb 2020 | Aug 2019 | Feb 2020
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403A | Hamilton Avenue MTS Bulkhead | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Jun 2020 | Feb 2020 | Jun 2020
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403A | Hamilton Avenue MTS Bulkhead | 5 | CONSTRUCTION TO 25% | Jul 2020 | Jun 2021 | Jul 2020 | Jun 2021
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403A | Hamilton Avenue MTS Bulkhead | 6 | CONSTRUCTION TO 50% | Jul 2021 | Jun 2022 | Jul 2021 | Jun 2022
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403A | Hamilton Avenue MTS Bulkhead | 7 | CONSTRUCTION TO 75% | Jul 2022 | Jun 2023 | Jul 2022 | Jun 2023
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403A | Hamilton Avenue MTS Bulkhead | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2023 | Jun 2024 | Jul 2023 | Jun 2024
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403A | Hamilton Avenue MTS Bulkhead | 9 | SUBSTANTIAL COMPLETION | Jun 2024 | Jun 2025 | Jun 2024 | Jun 2025
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403A | Hamilton Avenue MTS Bulkhead | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2025 | Jul 2025 | Jun 2025 | Jul 2025
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403C | Hamilton Avenue MTS Rehab | 1 | DEVELOP SCOPE | Nov 2019 | Feb 2020 | Nov 2019 | Feb 2020
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403C | Hamilton Avenue MTS Rehab | 2 | PRELIMINARY DESIGN | Feb 2020 | Aug 2020 | Feb 2020 | Aug 2020
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403C | Hamilton Avenue MTS Rehab | 3 | FINAL DESIGN | Aug 2020 | Feb 2021 | Aug 2020 | Feb 2021
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403C | Hamilton Avenue MTS Rehab | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403C | Hamilton Avenue MTS Rehab | 5 | CONSTRUCTION TO 25% | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403C | Hamilton Avenue MTS Rehab | 6 | CONSTRUCTION TO 50% | Dec 2021 | Jun 2022 | Dec 2021 | Jun 2022
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403C | Hamilton Avenue MTS Rehab | 7 | CONSTRUCTION TO 75% | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403C | Hamilton Avenue MTS Rehab | 8 | SUBSTANTIAL COMPLETION | Dec 2022 | Jan 2024 | Dec 2022 | Jan 2024
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403C | Hamilton Avenue MTS Rehab | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2024 | Mar 2025 | Jan 2024 | Mar 2025
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403D | Dredging of Hamilton Avenue MTS | 1 | DEVELOP SCOPE | Jun 2023 | Nov 2023 | Jun 2023 | Nov 2023
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403D | Dredging of Hamilton Avenue MTS | 2 | PRELIMINARY DESIGN | Nov 2023 | Mar 2024 | Nov 2023 | Mar 2024
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403D | Dredging of Hamilton Avenue MTS | 3 | FINAL DESIGN | Mar 2024 | Jul 2024 | Mar 2024 | Jul 2024
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403D | Dredging of Hamilton Avenue MTS | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Nov 2024 | Jul 2024 | Nov 2024
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403D | Dredging of Hamilton Avenue MTS | 5 | CONSTRUCTION TO 25% | Nov 2024 | Mar 2025 | Nov 2024 | Mar 2025
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403D | Dredging of Hamilton Avenue MTS | 6 | CONSTRUCTION TO 50% | Mar 2025 | Jul 2025 | Mar 2025 | Jul 2025
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403D | Dredging of Hamilton Avenue MTS | 7 | CONSTRUCTION TO 75% | Jul 2025 | Nov 2025 | Jul 2025 | Nov 2025
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403D | Dredging of Hamilton Avenue MTS | 8 | SUBSTANTIAL COMPLETION | Nov 2025 | Apr 2026 | Nov 2025 | Apr 2026
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403D | Dredging of Hamilton Avenue MTS | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2026 | May 2027 | Apr 2026 | May 2027
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11C | Hurricane Sandy Brooklyn 11 Conduit Replacement | 1 | DEVELOP SCOPE | Aug 2015 | Feb 2018 | Aug 2015 | Feb 2018
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11C | Hurricane Sandy Brooklyn 11 Conduit Replacement | 2 | PRELIMINARY DESIGN | Feb 2018 | Apr 2018 | Feb 2018 | Apr 2018
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11C | Hurricane Sandy Brooklyn 11 Conduit Replacement | 3 | FINAL DESIGN | Apr 2018 | Jun 2018 | Apr 2018 | Jun 2018
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11C | Hurricane Sandy Brooklyn 11 Conduit Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11C | Hurricane Sandy Brooklyn 11 Conduit Replacement | 5 | CONSTRUCTION TO 25% | Sep 2018 | Mar 2019 | Sep 2018 | Mar 2019
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11C | Hurricane Sandy Brooklyn 11 Conduit Replacement | 6 | CONSTRUCTION TO 50% | Mar 2019 | Oct 2019 | Mar 2019 | Oct 2019
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11C | Hurricane Sandy Brooklyn 11 Conduit Replacement | 7 | CONSTRUCTION TO 75% | Oct 2019 | Apr 2020 | Oct 2019 | Apr 2020
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11C | Hurricane Sandy Brooklyn 11 Conduit Replacement | 8 | SUBSTANTIAL COMPLETION | Apr 2020 | Sep 2021 | Apr 2020 | Sep 2021
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11C | Hurricane Sandy Brooklyn 11 Conduit Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Jun 2024 | Sep 2021 | Jun 2024
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11G | Hurricane Sandy Brooklyn 11 R/R & Haz Mitigation | 1 | DEVELOP SCOPE | Aug 2015 | Feb 2018 | Aug 2015 | Feb 2018
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11G | Hurricane Sandy Brooklyn 11 R/R & Haz Mitigation | 2 | PRELIMINARY DESIGN | Feb 2018 | Apr 2018 | Feb 2018 | Apr 2018
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11G | Hurricane Sandy Brooklyn 11 R/R & Haz Mitigation | 3 | FINAL DESIGN | Apr 2018 | Jun 2018 | Apr 2018 | Jun 2018
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11G | Hurricane Sandy Brooklyn 11 R/R & Haz Mitigation | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11G | Hurricane Sandy Brooklyn 11 R/R & Haz Mitigation | 5 | CONSTRUCTION TO 25% | Sep 2018 | Mar 2019 | Sep 2018 | Mar 2019
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11G | Hurricane Sandy Brooklyn 11 R/R & Haz Mitigation | 6 | CONSTRUCTION TO 50% | Mar 2019 | Oct 2019 | Mar 2019 | Oct 2019
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11G | Hurricane Sandy Brooklyn 11 R/R & Haz Mitigation | 7 | CONSTRUCTION TO 75% | Oct 2019 | Apr 2020 | Oct 2019 | Apr 2020
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11G | Hurricane Sandy Brooklyn 11 R/R & Haz Mitigation | 8 | SUBSTANTIAL COMPLETION | Apr 2020 | Sep 2021 | Apr 2020 | Sep 2021
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11G | Hurricane Sandy Brooklyn 11 R/R & Haz Mitigation | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Jun 2024 | Sep 2021 | Jun 2024
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK4FA | Hurricane Sandy Brooklyn 1/4 Fire Alarm Replacement | 1 | DEVELOP SCOPE | Aug 2015 | Feb 2016 | Aug 2015 | Feb 2016
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK4FA | Hurricane Sandy Brooklyn 1/4 Fire Alarm Replacement | 2 | PRELIMINARY DESIGN | Feb 2016 | Aug 2016 | Feb 2016 | Aug 2016
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK4FA | Hurricane Sandy Brooklyn 1/4 Fire Alarm Replacement | 3 | FINAL DESIGN | Aug 2016 | Aug 2017 | Aug 2016 | Aug 2017
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK4FA | Hurricane Sandy Brooklyn 1/4 Fire Alarm Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2017 | Aug 2018 | Aug 2017 | Aug 2018
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK4FA | Hurricane Sandy Brooklyn 1/4 Fire Alarm Replacement | 5 | CONSTRUCTION TO 25% | Aug 2018 | Aug 2019 | Aug 2018 | Aug 2019
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK4FA | Hurricane Sandy Brooklyn 1/4 Fire Alarm Replacement | 6 | CONSTRUCTION TO 50% | Aug 2019 | Aug 2020 | Aug 2019 | Aug 2020
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK4FA | Hurricane Sandy Brooklyn 1/4 Fire Alarm Replacement | 7 | CONSTRUCTION TO 75% | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK4FA | Hurricane Sandy Brooklyn 1/4 Fire Alarm Replacement | 8 | SUBSTANTIAL COMPLETION | Aug 2021 | May 2024 | Aug 2021 | May 2024
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK4FA | Hurricane Sandy Brooklyn 1/4 Fire Alarm Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2021 | Sep 2024 | Dec 2021 | Sep 2024
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPTWH | Hurricane Sandy GRNPT Warehouse R/R & Haz Mitigation | 1 | DEVELOP SCOPE | Aug 2015 | Dec 2015 | Aug 2015 | Dec 2015
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPTWH | Hurricane Sandy GRNPT Warehouse R/R & Haz Mitigation | 2 | PRELIMINARY DESIGN | Dec 2015 | Jun 2016 | Dec 2015 | Jun 2016
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPTWH | Hurricane Sandy GRNPT Warehouse R/R & Haz Mitigation | 3 | FINAL DESIGN | Jun 2016 | Jun 2017 | Jun 2016 | Jun 2017
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPTWH | Hurricane Sandy GRNPT Warehouse R/R & Haz Mitigation | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2017 | Jun 2018 | Jun 2017 | Jun 2018
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPTWH | Hurricane Sandy GRNPT Warehouse R/R & Haz Mitigation | 5 | CONSTRUCTION TO 25% | Jun 2018 | Jun 2019 | Jun 2018 | Jun 2019
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPTWH | Hurricane Sandy GRNPT Warehouse R/R & Haz Mitigation | 6 | CONSTRUCTION TO 50% | Jun 2019 | Jun 2020 | Jun 2019 | Jun 2020
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPTWH | Hurricane Sandy GRNPT Warehouse R/R & Haz Mitigation | 7 | CONSTRUCTION TO 75% | Jun 2020 | Mar 2023 | Jun 2020 | Mar 2023
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPTWH | Hurricane Sandy GRNPT Warehouse R/R & Haz Mitigation | 8 | SUBSTANTIAL COMPLETION | Mar 2023 | Dec 2025 | Mar 2023 | Dec 2025
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPTWH | Hurricane Sandy GRNPT Warehouse R/R & Haz Mitigation | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2023 | Apr 2026 | Jul 2023 | Apr 2026
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPWHC | Hurricane Sandy GRNPT Warehouse Conduit Replacement | 1 | DEVELOP SCOPE | Aug 2017 | May 2018 | Aug 2017 | May 2018
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPWHC | Hurricane Sandy GRNPT Warehouse Conduit Replacement | 2 | PRELIMINARY DESIGN | Jun 2018 | Mar 2019 | Jun 2018 | Mar 2019
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPWHC | Hurricane Sandy GRNPT Warehouse Conduit Replacement | 3 | FINAL DESIGN | Mar 2019 | Dec 2019 | Mar 2019 | Dec 2019
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPWHC | Hurricane Sandy GRNPT Warehouse Conduit Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPWHC | Hurricane Sandy GRNPT Warehouse Conduit Replacement | 5 | CONSTRUCTION TO 25% | Sep 2020 | Jun 2021 | Sep 2020 | Jun 2021
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPWHC | Hurricane Sandy GRNPT Warehouse Conduit Replacement | 6 | CONSTRUCTION TO 50% | Jun 2021 | Mar 2022 | Jun 2021 | Mar 2022
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPWHC | Hurricane Sandy GRNPT Warehouse Conduit Replacement | 7 | CONSTRUCTION TO 75% | Apr 2022 | Jan 2023 | Apr 2022 | Jan 2023
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPWHC | Hurricane Sandy GRNPT Warehouse Conduit Replacement | 8 | SUBSTANTIAL COMPLETION | Jan 2023 | Jun 2025 | Jan 2023 | Jun 2025
20231026 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPWHC | Hurricane Sandy GRNPT Warehouse Conduit Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2025 | Dec 2027 | Jun 2025 | Dec 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT601 | DOT - Hamilton Administrative Building | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2022 | Jun 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT601 | DOT - Hamilton Administrative Building | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2022 | Oct 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT601 | DOT - Hamilton Administrative Building | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2022 | Jan 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT601 | DOT - Hamilton Administrative Building | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2023 | Mar 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT601 | DOT - Hamilton Administrative Building | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2023 | Jun 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | BEDSTLIG | DOT BEDFORD HISTORIC LIGHT RESTORATION, BROOKLYN | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Jun 2019 | Jun 2027 | Jun 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | BEDSTLIG | DOT BEDFORD HISTORIC LIGHT RESTORATION, BROOKLYN | 2 | CONSTRUCTION START | Jul 2019 | Aug 2019 | Jul 2027 | Aug 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | BEDSTLIG | DOT BEDFORD HISTORIC LIGHT RESTORATION, BROOKLYN | 3 | CONSTRUCTION COMPLETION | Aug 2019 | Mar 2021 | Aug 2027 | Mar 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | BKBRDGCAM | Brooklyn Bridge Surveillance Cameras | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2015 | Jun 2015 | Jun 2023 | Jun 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | BKBRDGCAM | Brooklyn Bridge Surveillance Cameras | 2 | CONSTRUCTION START | Jul 2015 | Aug 2015 | Jul 2023 | Aug 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | BKBRDGCAM | Brooklyn Bridge Surveillance Cameras | 3 | CONSTRUCTION COMPLETION | Aug 2015 | Mar 2017 | Aug 2023 | Mar 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | BKBRDGITS | Brooklyn Bridge Approaches-DOT ITS | 1 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Jul 2016 | Jun 2023 | Jul 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | BKBRDGITS | Brooklyn Bridge Approaches-DOT ITS | 2 | CONSTRUCTION START | Jul 2016 | Aug 2016 | Jul 2025 | Jul 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | BKBRDGITS | Brooklyn Bridge Approaches-DOT ITS | 3 | CONSTRUCTION COMPLETION | Aug 2016 | Mar 2018 | Jul 2026 | Jul 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | BRK24027 | UNION STREET over GOWANUS CANAL BIN 2240270 | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2021
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | BRK24027 | UNION STREET over GOWANUS CANAL BIN 2240270 | 2 | DESIGN START | Jun 2021 | Jun 2025 | Jun 2020 | Jun 2021
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | BRK24027 | UNION STREET over GOWANUS CANAL BIN 2240270 | 3 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Jun 2021 | Jun 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | BRK24027 | UNION STREET over GOWANUS CANAL BIN 2240270 | 5 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Jun 2025 | Jun 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK1023 | MILL BASIN BR / BELT PARKWAY #2-23147-9/TN | 1 | DEVELOP SCOPE | Jul 2006 | Jun 2007
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK1023 | MILL BASIN BR / BELT PARKWAY #2-23147-9/TN | 2 | DESIGN START | Jul 2007 | Jun 2011 | Aug 2031 | Aug 2032
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK1023 | MILL BASIN BR / BELT PARKWAY #2-23147-9/TN | 3 | CONSTRUCTION START | Jun 2011 | Jun 2013 | Mar 2023 | Aug 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK1023 | MILL BASIN BR / BELT PARKWAY #2-23147-9/TN | 5 | CONSTRUCTION START | Jun 2011 | Jun 2013 | Aug 2024 | Aug 2031
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK1201 | ATLANTIC AVENUE/LIRR ATLANTIC AVENUE 2-243569 | 3 | CONSTRUCTION START | Jun 2007 | Jun 2009 | Jul 2017 | Jun 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK1205 | RECON OF 5TH AVE BRIDGE OVER LIRR AND SEA BEACH, BR 2-243580 | 1 | DEVELOP SCOPE | Jun 2004 | Jun 2005 | Nov 2015 | Mar 2018
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK1205 | RECON OF 5TH AVE BRIDGE OVER LIRR AND SEA BEACH, BR 2-243580 | 2 | DESIGN START | Jun 2005 | Jun 2009 | Sep 2018 | Jul 2020
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK1205 | RECON OF 5TH AVE BRIDGE OVER LIRR AND SEA BEACH, BR 2-243580 | 3 | CONSTRUCTION START | Jun 2009 | Jun 2011 | Jul 2021 | Oct 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK224404 | EAST DRIVE (E WOOD ARCH) PED PATH NEAR CENTER DRIV # 2244040 | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK224404 | EAST DRIVE (E WOOD ARCH) PED PATH NEAR CENTER DRIV # 2244040 | 2 | DESIGN START | Jun 2022 | Jun 2026 | Jun 2021 | Jun 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK224404 | EAST DRIVE (E WOOD ARCH) PED PATH NEAR CENTER DRIV # 2244040 | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2022 | Jun 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK224404 | EAST DRIVE (E WOOD ARCH) PED PATH NEAR CENTER DRIV # 2244040 | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK243140 | NEWKIRK AVE over BMT SUBWAY, BRIGHTON BIN 2243140 | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK243140 | NEWKIRK AVE over BMT SUBWAY, BRIGHTON BIN 2243140 | 2 | DESIGN START | Jun 2024 | Jun 2028 | Jun 2023 | Jun 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK243140 | NEWKIRK AVE over BMT SUBWAY, BRIGHTON BIN 2243140 | 3 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jun 2024 | Jun 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK243140 | NEWKIRK AVE over BMT SUBWAY, BRIGHTON BIN 2243140 | 5 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jun 2028 | Jun 2030
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK244120 | HILL DR (TERRACE BR) OVER PROSPECT PARK LAKE BIN:2244120 | 1 | DEVELOP SCOPE | Jun 2017 | Jun 2018
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK244120 | HILL DR (TERRACE BR) OVER PROSPECT PARK LAKE BIN:2244120 | 2 | DESIGN START | Jun 2018 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK244120 | HILL DR (TERRACE BR) OVER PROSPECT PARK LAKE BIN:2244120 | 3 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Jun 2022 | Jun 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK244120 | HILL DR (TERRACE BR) OVER PROSPECT PARK LAKE BIN:2244120 | 5 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Jun 2026 | Jun 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK4470 | SEELY STREET OVER PROSPECT AVENUE BIN: 2244470 | 1 | DEVELOP SCOPE | Jun 2015 | Jun 2016
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK4470 | SEELY STREET OVER PROSPECT AVENUE BIN: 2244470 | 2 | DESIGN START | Jun 2016 | Jun 2020 | Apr 2017 | Sep 2017
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK4470 | SEELY STREET OVER PROSPECT AVENUE BIN: 2244470 | 3 | CONSTRUCTION START | Jun 2020 | Jun 2022 | Oct 2019 | Oct 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK4470 | SEELY STREET OVER PROSPECT AVENUE BIN: 2244470 | 5 | CONSTRUCTION START | Jun 2020 | Jun 2022 | Sep 2023 | Nov 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK530 | PARKSIDE AVE AND OCEAN AVE RR BR #2-24302-0 | 1 | DEVELOP SCOPE | Jul 2006 | Jun 2007 | Nov 2018 | Feb 2019
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK530 | PARKSIDE AVE AND OCEAN AVE RR BR #2-24302-0 | 2 | DESIGN START | Jul 2007 | Jun 2011 | Jan 2018 | Feb 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK530 | PARKSIDE AVE AND OCEAN AVE RR BR #2-24302-0 | 3 | CONSTRUCTION START | Jun 2011 | Jun 2013 | Feb 2023 | Nov 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23036 | UNION ST OVER 278I BQE BIN 2230360 | 1 | DEVELOP SCOPE | Jul 2025 | Jun 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23036 | UNION ST OVER 278I BQE BIN 2230360 | 2 | DESIGN START | Jul 2026 | Jun 2030 | Nov 2020 | Nov 2021
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23036 | UNION ST OVER 278I BQE BIN 2230360 | 3 | CONSTRUCTION START | Jun 2030 | Jun 2032 | Oct 2021 | Mar 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23036 | UNION ST OVER 278I BQE BIN 2230360 | 5 | CONSTRUCTION START | Jun 2030 | Jun 2032 | Aug 2025 | Jul 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23038 | KANE ST/ 278I (BQE) BIN# 2230380 | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Apr 2021 | Jun 2021
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23038 | KANE ST/ 278I (BQE) BIN# 2230380 | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Jun 2021 | Oct 2021
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23038 | KANE ST/ 278I (BQE) BIN# 2230380 | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Oct 2021 | Apr 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23038 | KANE ST/ 278I (BQE) BIN# 2230380 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Apr 2022 | Jul 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23038 | KANE ST/ 278I (BQE) BIN# 2230380 | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Jul 2022 | Nov 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23038 | KANE ST/ 278I (BQE) BIN# 2230380 | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Nov 2022 | Mar 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23038 | KANE ST/ 278I (BQE) BIN# 2230380 | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Mar 2023 | Jul 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23038 | KANE ST/ 278I (BQE) BIN# 2230380 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Jul 2023 | Oct 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23038 | KANE ST/ 278I (BQE) BIN# 2230380 | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Oct 2023 | Dec 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23038 | KANE ST/ 278I (BQE) BIN# 2230380 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Dec 2023 | Jan 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23140 | BSHP over Sheepshead Bay Road BIN 2231409 | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23140 | BSHP over Sheepshead Bay Road BIN 2231409 | 2 | DESIGN START | Jun 2024 | Jun 2028 | Jun 2017 | Aug 2017
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23140 | BSHP over Sheepshead Bay Road BIN 2231409 | 3 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jul 2020 | May 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23140 | BSHP over Sheepshead Bay Road BIN 2231409 | 5 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jun 2024 | Jun 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23141 | BSHP over Ocean Ave BIN 2231419 | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23141 | BSHP over Ocean Ave BIN 2231419 | 2 | DESIGN START | Jun 2024 | Jun 2028 | Jun 2017 | Aug 2017
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23141 | BSHP over Ocean Ave BIN 2231419 | 3 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jul 2020 | Jul 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23141 | BSHP over Ocean Ave BIN 2231419 | 5 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jun 2024 | Sep 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23142 | BSHP OVER BEDFORD AVE BIN 2231429 | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23142 | BSHP OVER BEDFORD AVE BIN 2231429 | 2 | DESIGN START | Jun 2022 | Jun 2026 | Jun 2017 | Aug 2017
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23142 | BSHP OVER BEDFORD AVE BIN 2231429 | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jul 2020 | Jul 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23142 | BSHP OVER BEDFORD AVE BIN 2231429 | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2024 | Sep 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23143 | Belt Shore Pkwy over Nostrand Ave 2231439 | 1 | DEVELOP SCOPE | Jun 2016 | Jun 2017
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23143 | Belt Shore Pkwy over Nostrand Ave 2231439 | 2 | DESIGN START | Jun 2017 | Jun 2021 | Jun 2020 | Jun 2021
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23143 | Belt Shore Pkwy over Nostrand Ave 2231439 | 3 | CONSTRUCTION START | Jun 2021 | Jun 2023 | Jun 2021 | Jun 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23143 | Belt Shore Pkwy over Nostrand Ave 2231439 | 5 | CONSTRUCTION START | Jun 2021 | Jun 2023 | Jun 2025 | Jun 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23308 | E 14TH ST PED BRIDGE BIN:2233080 | 1 | DEVELOP SCOPE | Jun 2018 | Jun 2019
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23308 | E 14TH ST PED BRIDGE BIN:2233080 | 2 | DESIGN START | Jun 2019 | Jun 2023 | Apr 2022 | Sep 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23308 | E 14TH ST PED BRIDGE BIN:2233080 | 3 | CONSTRUCTION START | Jun 2023 | Jun 2025 | Jul 2018 | Sep 2021
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23308 | E 14TH ST PED BRIDGE BIN:2233080 | 5 | CONSTRUCTION START | Jun 2023 | Jun 2025 | Sep 2022 | Nov 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24304 | CROOKE AVENUE over BMT SUBWAY, BRIGHTON 2243040 | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24304 | CROOKE AVENUE over BMT SUBWAY, BRIGHTON 2243040 | 2 | DESIGN START | Jun 2023 | Jun 2027 | Jun 2022 | Jun 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24304 | CROOKE AVENUE over BMT SUBWAY, BRIGHTON 2243040 | 3 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2023 | Jun 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24304 | CROOKE AVENUE over BMT SUBWAY, BRIGHTON 2243040 | 5 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2027 | Jun 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24310 | Beverly Road over BMT Subway, Brighton BIN 2243100 | 1 | DEVELOP SCOPE | Jun 2017 | Jun 2018
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24310 | Beverly Road over BMT Subway, Brighton BIN 2243100 | 2 | DESIGN START | Jun 2018 | Jun 2022 | Aug 2017 | Sep 2017
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24310 | Beverly Road over BMT Subway, Brighton BIN 2243100 | 3 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Jan 2020 | Dec 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24310 | Beverly Road over BMT Subway, Brighton BIN 2243100 | 5 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Oct 2023 | Oct 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24315 | Foster Ave over BMT Subway BIN 2243150 | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24315 | Foster Ave over BMT Subway BIN 2243150 | 2 | DESIGN START | Jun 2022 | Jun 2026 | Jun 2021 | Jun 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24315 | Foster Ave over BMT Subway BIN 2243150 | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2022 | Jun 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24315 | Foster Ave over BMT Subway BIN 2243150 | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24371 | 19TH AVENUE over BMT SEA BEACH BIN 2243710 | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24371 | 19TH AVENUE over BMT SEA BEACH BIN 2243710 | 2 | DESIGN START | Jun 2022 | Jun 2026 | Jun 2021 | Jun 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24371 | 19TH AVENUE over BMT SEA BEACH BIN 2243710 | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2022 | Jun 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24371 | 19TH AVENUE over BMT SEA BEACH BIN 2243710 | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24382 | 21st Ave RR BR & 64th St #2-24382-1/TN35190 | 1 | DEVELOP SCOPE | Jun 2017 | Jun 2018
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24382 | 21st Ave RR BR & 64th St #2-24382-1/TN35190 | 2 | DESIGN START | Jun 2018 | Jun 2022 | May 2018 | Nov 2019
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24382 | 21st Ave RR BR & 64th St #2-24382-1/TN35190 | 3 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Mar 2021 | Mar 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24382 | 21st Ave RR BR & 64th St #2-24382-1/TN35190 | 5 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Jan 2025 | Apr 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBPK17K | 17TH AVENUE PEDESTRIAN BRIDGE OVER BELT PARKWAY 2231300 | 1 | DEVELOP SCOPE | Jun 2014 | May 2015 | Jun 2017 | May 2018
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBPK17K | 17TH AVENUE PEDESTRIAN BRIDGE OVER BELT PARKWAY 2231300 | 2 | DESIGN START | Jun 2015 | May 2019 | Jun 2018 | May 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBPK17K | 17TH AVENUE PEDESTRIAN BRIDGE OVER BELT PARKWAY 2231300 | 3 | CONSTRUCTION START | May 2019 | May 2021 | May 2022 | May 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBPK27K | 27TH AVENUE PEDESTRIAN BRIDGE OVER BELT PARKWAY | 1 | DEVELOP SCOPE | Jun 2014 | May 2015
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBPK27K | 27TH AVENUE PEDESTRIAN BRIDGE OVER BELT PARKWAY | 2 | DEVELOP SCOPE | Jun 2015 | May 2019 | Jun 2018 | May 2019
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBPK27K | 27TH AVENUE PEDESTRIAN BRIDGE OVER BELT PARKWAY | 3 | DESIGN START | May 2019 | May 2021 | Jun 2019 | May 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBPK27K | 27TH AVENUE PEDESTRIAN BRIDGE OVER BELT PARKWAY | 5 | CONSTRUCTION START | May 2019 | May 2021 | May 2023 | May 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HW349LUM | IN-HOUSE RESURFACING LUMP SUM - ASPHALT | 1 | DEVELOP SCOPE | Jun 2007 | Sep 2007 | Jun 2007 | Sep 2007
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HW349LUM | IN-HOUSE RESURFACING LUMP SUM - ASPHALT | 2 | DESIGN START | Sep 2007 | Mar 2009 | Sep 2007 | Mar 2009
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HW349LUM | IN-HOUSE RESURFACING LUMP SUM - ASPHALT | 3 | CONSTRUCTION START | Mar 2009 | Mar 2011 | Mar 2009 | Jun 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCH98 | East 98th Street School Safety Improvements | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Aug 2019 | Jan 2020
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCH98 | East 98th Street School Safety Improvements | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Jun 2021 | Sep 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCH98 | East 98th Street School Safety Improvements | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Sep 2022 | Mar 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCH98 | East 98th Street School Safety Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | May 2024 | Jul 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCH98 | East 98th Street School Safety Improvements | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Aug 2024 | Mar 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCH98 | East 98th Street School Safety Improvements | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Mar 2025 | Sep 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCH98 | East 98th Street School Safety Improvements | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Sep 2025 | Apr 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCH98 | East 98th Street School Safety Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Apr 2026 | Jul 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCH98 | East 98th Street School Safety Improvements | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jul 2026 | Sep 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCH98 | East 98th Street School Safety Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Sep 2026 | Oct 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10109 | JORALEMON STREET IMPROVEMENTS | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10109 | JORALEMON STREET IMPROVEMENTS | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10109 | JORALEMON STREET IMPROVEMENTS | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2024 | Jul 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10109 | JORALEMON STREET IMPROVEMENTS | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2024 | Oct 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10109 | JORALEMON STREET IMPROVEMENTS | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2024 | Feb 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10109 | JORALEMON STREET IMPROVEMENTS | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2025 | Jun 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10109 | JORALEMON STREET IMPROVEMENTS | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2025 | Oct 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10109 | JORALEMON STREET IMPROVEMENTS | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Jun 2022 | Jul 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10109 | JORALEMON STREET IMPROVEMENTS | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jul 2023 | Aug 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10109 | JORALEMON STREET IMPROVEMENTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Aug 2023 | Jul 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10110 | Strickland Avenue - Reconstruction | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2028 | Sep 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10110 | Strickland Avenue - Reconstruction | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2028 | Jan 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10110 | Strickland Avenue - Reconstruction | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2029 | Jul 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10110 | Strickland Avenue - Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2029 | Oct 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10110 | Strickland Avenue - Reconstruction | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2029 | Feb 2030
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10110 | Strickland Avenue - Reconstruction | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2030 | Jun 2030
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10110 | Strickland Avenue - Reconstruction | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2030 | Oct 2030
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10110 | Strickland Avenue - Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2030 | Jan 2031
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10110 | Strickland Avenue - Reconstruction | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2031 | Mar 2031
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10110 | Strickland Avenue - Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2031 | Apr 2032
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10111 | Intersection Safety Improvements Ocean Parkway & Ave Z | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10111 | Intersection Safety Improvements Ocean Parkway & Ave Z | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10111 | Intersection Safety Improvements Ocean Parkway & Ave Z | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2024 | Jul 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10111 | Intersection Safety Improvements Ocean Parkway & Ave Z | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2024 | Oct 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10111 | Intersection Safety Improvements Ocean Parkway & Ave Z | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2024 | Feb 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10111 | Intersection Safety Improvements Ocean Parkway & Ave Z | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2025 | Jun 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10111 | Intersection Safety Improvements Ocean Parkway & Ave Z | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2025 | Oct 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10111 | Intersection Safety Improvements Ocean Parkway & Ave Z | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2025 | Jan 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10111 | Intersection Safety Improvements Ocean Parkway & Ave Z | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2026 | Mar 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10111 | Intersection Safety Improvements Ocean Parkway & Ave Z | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2026 | Jun 2032
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10113 | Street Reconstruction in Community Board 14 | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10113 | Street Reconstruction in Community Board 14 | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10113 | Street Reconstruction in Community Board 14 | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2024 | Jul 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10113 | Street Reconstruction in Community Board 14 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2024 | Oct 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10113 | Street Reconstruction in Community Board 14 | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2024 | Feb 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10113 | Street Reconstruction in Community Board 14 | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2025 | Jun 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10113 | Street Reconstruction in Community Board 14 | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2025 | Oct 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10113 | Street Reconstruction in Community Board 14 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2025 | Jan 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10113 | Street Reconstruction in Community Board 14 | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2026 | Mar 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10113 | Street Reconstruction in Community Board 14 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2026 | Jun 2032
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10115 | Safety Improvements Broadway Corridor | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Jun 2027 | Sep 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10115 | Safety Improvements Broadway Corridor | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Sep 2027 | Jan 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10115 | Safety Improvements Broadway Corridor | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Jan 2028 | Jul 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10115 | Safety Improvements Broadway Corridor | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Jul 2028 | Oct 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10115 | Safety Improvements Broadway Corridor | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Oct 2028 | Feb 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10115 | Safety Improvements Broadway Corridor | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Feb 2029 | Jun 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10115 | Safety Improvements Broadway Corridor | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Jun 2029 | Oct 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10115 | Safety Improvements Broadway Corridor | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | Oct 2029 | Jan 2030
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10115 | Safety Improvements Broadway Corridor | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Jan 2030 | Mar 2030
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10115 | Safety Improvements Broadway Corridor | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Mar 2030 | Apr 2032
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWFKGPYRD | Build-Out Cost for Greenpoint Yard New Trailers | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2025 | Sep 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWFKGPYRD | Build-Out Cost for Greenpoint Yard New Trailers | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2025 | Jan 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWFKGPYRD | Build-Out Cost for Greenpoint Yard New Trailers | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2026 | Jul 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWFKGPYRD | Build-Out Cost for Greenpoint Yard New Trailers | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2026 | Oct 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWFKGPYRD | Build-Out Cost for Greenpoint Yard New Trailers | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2026 | Feb 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWFKGPYRD | Build-Out Cost for Greenpoint Yard New Trailers | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2027 | Jun 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWFKGPYRD | Build-Out Cost for Greenpoint Yard New Trailers | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2027 | Oct 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWFKGPYRD | Build-Out Cost for Greenpoint Yard New Trailers | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2027 | Jan 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWFKGPYRD | Build-Out Cost for Greenpoint Yard New Trailers | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2028 | Mar 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWFKGPYRD | Build-Out Cost for Greenpoint Yard New Trailers | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2028 | Apr 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK002392 | 3rd Avenue Reconstruction in Brooklyn | 1 | DEVELOP SCOPE | Jun 2027 | Sep 2027 | Jun 2027 | Sep 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK002392 | 3rd Avenue Reconstruction in Brooklyn | 2 | PRELIMINARY DESIGN | Sep 2027 | Jan 2028 | Sep 2027 | Jan 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK002392 | 3rd Avenue Reconstruction in Brooklyn | 3 | FINAL DESIGN | Jan 2028 | Jul 2028 | Jan 2028 | Jul 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK002392 | 3rd Avenue Reconstruction in Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2028 | Oct 2028 | Jul 2028 | Oct 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK002392 | 3rd Avenue Reconstruction in Brooklyn | 5 | CONSTRUCTION TO 25% | Oct 2028 | Feb 2029 | Oct 2028 | Feb 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK002392 | 3rd Avenue Reconstruction in Brooklyn | 6 | CONSTRUCTION TO 50% | Feb 2029 | Jun 2029 | Feb 2029 | Jun 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK002392 | 3rd Avenue Reconstruction in Brooklyn | 7 | CONSTRUCTION TO 75% | Jun 2029 | Oct 2029 | Jun 2029 | Oct 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK002392 | 3rd Avenue Reconstruction in Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2029 | Jan 2030 | Oct 2029 | Jan 2030
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK002392 | 3rd Avenue Reconstruction in Brooklyn | 9 | SUBSTANTIAL COMPLETION | Jan 2030 | Mar 2030 | Jan 2030 | Mar 2030
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK002392 | 3rd Avenue Reconstruction in Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2030 | Apr 2030 | Mar 2030 | Apr 2030
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00502 | 8th Avenue Sunset Park Chinatown Archway | 1 | DEVELOP SCOPE | Jun 2016 | Oct 2016 | Jun 2024 | Oct 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00502 | 8th Avenue Sunset Park Chinatown Archway | 2 | DESIGN START | Oct 2016 | Apr 2018 | Oct 2024 | Apr 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00502 | 8th Avenue Sunset Park Chinatown Archway | 3 | CONSTRUCTION START | Apr 2018 | Apr 2020 | Apr 2026 | Apr 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00503 | BQ Green | 1 | DEVELOP SCOPE | Jun 2015 | Oct 2015 | Jun 2022 | Oct 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00503 | BQ Green | 2 | DESIGN START | Oct 2015 | Apr 2017 | Oct 2022 | Apr 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00503 | BQ Green | 3 | CONSTRUCTION START | Apr 2017 | Apr 2019 | Apr 2024 | Jul 2031
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00504 | Atlantic Avenue - Purchase of WalkNYC Signs | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2021 | Sep 2021
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00504 | Atlantic Avenue - Purchase of WalkNYC Signs | 2 | PRELIMINARY DESIGN | Sep 2015 | Jan 2016 | Sep 2021 | Jan 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00504 | Atlantic Avenue - Purchase of WalkNYC Signs | 3 | FINAL DESIGN | Jan 2016 | Jul 2016 | Jan 2022 | Jul 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00504 | Atlantic Avenue - Purchase of WalkNYC Signs | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Oct 2016 | Jul 2022 | Oct 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00504 | Atlantic Avenue - Purchase of WalkNYC Signs | 5 | CONSTRUCTION TO 25% | Oct 2016 | Feb 2017 | Oct 2022 | Feb 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00504 | Atlantic Avenue - Purchase of WalkNYC Signs | 6 | CONSTRUCTION TO 50% | Feb 2017 | Jun 2017 | Feb 2023 | Jun 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00504 | Atlantic Avenue - Purchase of WalkNYC Signs | 7 | CONSTRUCTION TO 75% | Jun 2017 | Oct 2017 | Jun 2023 | Oct 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00504 | Atlantic Avenue - Purchase of WalkNYC Signs | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2017 | Jan 2018 | Oct 2023 | Jan 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00504 | Atlantic Avenue - Purchase of WalkNYC Signs | 9 | SUBSTANTIAL COMPLETION | Jan 2018 | Mar 2018 | Jan 2024 | Mar 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00504 | Atlantic Avenue - Purchase of WalkNYC Signs | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2018 | Apr 2018 | Mar 2024 | Jul 2031
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00514 | Brooklyn Greenway:Atlantic Avenue Connector | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jun 2024 | Sep 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00514 | Brooklyn Greenway:Atlantic Avenue Connector | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Sep 2024 | Jan 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00514 | Brooklyn Greenway:Atlantic Avenue Connector | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2025 | Jul 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00514 | Brooklyn Greenway:Atlantic Avenue Connector | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2025 | Oct 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00514 | Brooklyn Greenway:Atlantic Avenue Connector | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2025 | Feb 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00514 | Brooklyn Greenway:Atlantic Avenue Connector | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2026 | Jun 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00514 | Brooklyn Greenway:Atlantic Avenue Connector | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2026 | Oct 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00514 | Brooklyn Greenway:Atlantic Avenue Connector | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2026 | Jan 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00514 | Brooklyn Greenway:Atlantic Avenue Connector | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2027 | Mar 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00514 | Brooklyn Greenway:Atlantic Avenue Connector | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2027 | Jun 2030
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK20072 | Ave W, Gravesend Neck Rd, and Sheepshead Bay Rd | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2026 | Sep 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK20072 | Ave W, Gravesend Neck Rd, and Sheepshead Bay Rd | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2026 | Jan 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK20072 | Ave W, Gravesend Neck Rd, and Sheepshead Bay Rd | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2027 | Jul 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK20072 | Ave W, Gravesend Neck Rd, and Sheepshead Bay Rd | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2027 | Oct 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK20072 | Ave W, Gravesend Neck Rd, and Sheepshead Bay Rd | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2027 | Feb 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK20072 | Ave W, Gravesend Neck Rd, and Sheepshead Bay Rd | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2028 | Jun 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK20072 | Ave W, Gravesend Neck Rd, and Sheepshead Bay Rd | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2028 | Oct 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK20072 | Ave W, Gravesend Neck Rd, and Sheepshead Bay Rd | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2023 | Jan 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK20072 | Ave W, Gravesend Neck Rd, and Sheepshead Bay Rd | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2024 | Mar 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK20072 | Ave W, Gravesend Neck Rd, and Sheepshead Bay Rd | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2024 | Apr 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK2048A | Jamaica Bay Greenway - Marine Park Connector & Flatbush Ave | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2022 | Sep 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK2048A | Jamaica Bay Greenway - Marine Park Connector & Flatbush Ave | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2022 | Jan 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK2048A | Jamaica Bay Greenway - Marine Park Connector & Flatbush Ave | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2023 | Jul 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK2048A | Jamaica Bay Greenway - Marine Park Connector & Flatbush Ave | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2023 | Oct 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK2048A | Jamaica Bay Greenway - Marine Park Connector & Flatbush Ave | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2023 | Feb 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK2048A | Jamaica Bay Greenway - Marine Park Connector & Flatbush Ave | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2024 | Jun 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK2048A | Jamaica Bay Greenway - Marine Park Connector & Flatbush Ave | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2024 | Oct 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK2048A | Jamaica Bay Greenway - Marine Park Connector & Flatbush Ave | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2024 | Jan 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK2048A | Jamaica Bay Greenway - Marine Park Connector & Flatbush Ave | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2025 | Mar 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK2048A | Jamaica Bay Greenway - Marine Park Connector & Flatbush Ave | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2025 | Apr 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK2048B | Shirley Chisholm Bike Path - Seaview - Erskine to Fountain | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK2048B | Shirley Chisholm Bike Path - Seaview - Erskine to Fountain | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK2048B | Shirley Chisholm Bike Path - Seaview - Erskine to Fountain | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK2048B | Shirley Chisholm Bike Path - Seaview - Erskine to Fountain | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK2048B | Shirley Chisholm Bike Path - Seaview - Erskine to Fountain | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK2048B | Shirley Chisholm Bike Path - Seaview - Erskine to Fountain | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK2048B | Shirley Chisholm Bike Path - Seaview - Erskine to Fountain | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK2048B | Shirley Chisholm Bike Path - Seaview - Erskine to Fountain | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK2048B | Shirley Chisholm Bike Path - Seaview - Erskine to Fountain | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK2048B | Shirley Chisholm Bike Path - Seaview - Erskine to Fountain | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKA37145 | Borough Hall Pedestrian Improvements | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2023 | Jun 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKA37145 | Borough Hall Pedestrian Improvements | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Jul 2026 | Oct 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKA37145 | Borough Hall Pedestrian Improvements | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Oct 2026 | Apr 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKA37145 | Borough Hall Pedestrian Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Apr 2027 | Jul 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKA37145 | Borough Hall Pedestrian Improvements | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Jul 2027 | Nov 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKA37145 | Borough Hall Pedestrian Improvements | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Nov 2027 | Mar 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKA37145 | Borough Hall Pedestrian Improvements | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Mar 2028 | Jul 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKA37145 | Borough Hall Pedestrian Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2020 | Jan 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKA37145 | Borough Hall Pedestrian Improvements | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2023 | Mar 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKA37145 | Borough Hall Pedestrian Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2023 | Apr 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAPOLWF | Apollo Street End Waterfront | 1 | DEVELOP SCOPE | Jun 2025 | Sep 2025 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAPOLWF | Apollo Street End Waterfront | 2 | PRELIMINARY DESIGN | Sep 2025 | Jan 2026 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAPOLWF | Apollo Street End Waterfront | 3 | FINAL DESIGN | Jan 2026 | Jul 2026 | Jan 2024 | Jul 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAPOLWF | Apollo Street End Waterfront | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2026 | Oct 2026 | Jul 2024 | Oct 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAPOLWF | Apollo Street End Waterfront | 5 | CONSTRUCTION TO 25% | Oct 2026 | Feb 2027 | Oct 2024 | Feb 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAPOLWF | Apollo Street End Waterfront | 6 | CONSTRUCTION TO 50% | Feb 2027 | Jun 2027 | Feb 2025 | Jun 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAPOLWF | Apollo Street End Waterfront | 7 | CONSTRUCTION TO 75% | Jun 2027 | Oct 2027 | Jun 2025 | Oct 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAPOLWF | Apollo Street End Waterfront | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jan 2028 | Oct 2025 | Jan 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAPOLWF | Apollo Street End Waterfront | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Mar 2028 | Jan 2026 | Mar 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAPOLWF | Apollo Street End Waterfront | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2028 | Apr 2028 | Mar 2026 | Apr 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAVEJ80 | Avenue J Improvements | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAVEJ80 | Avenue J Improvements | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAVEJ80 | Avenue J Improvements | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAVEJ80 | Avenue J Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAVEJ80 | Avenue J Improvements | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAVEJ80 | Avenue J Improvements | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAVEJ80 | Avenue J Improvements | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAVEJ80 | Avenue J Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAVEJ80 | Avenue J Improvements | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAVEJ80 | Avenue J Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAVEWWF | Avenue W Waterfront Street End | 1 | DEVELOP SCOPE | Jun 2025 | Sep 2025 | Jun 2022 | Sep 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAVEWWF | Avenue W Waterfront Street End | 2 | PRELIMINARY DESIGN | Sep 2025 | Jan 2026 | Sep 2022 | Jan 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAVEWWF | Avenue W Waterfront Street End | 3 | FINAL DESIGN | Jan 2026 | Jul 2026 | Jan 2023 | Jul 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAVEWWF | Avenue W Waterfront Street End | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2026 | Oct 2026 | Jul 2023 | Oct 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAVEWWF | Avenue W Waterfront Street End | 5 | CONSTRUCTION TO 25% | Oct 2026 | Feb 2027 | Oct 2023 | Feb 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAVEWWF | Avenue W Waterfront Street End | 6 | CONSTRUCTION TO 50% | Feb 2027 | Jun 2027 | Feb 2024 | Jun 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAVEWWF | Avenue W Waterfront Street End | 7 | CONSTRUCTION TO 75% | Jun 2027 | Oct 2027 | Jun 2024 | Oct 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAVEWWF | Avenue W Waterfront Street End | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jan 2028 | Oct 2024 | Jan 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAVEWWF | Avenue W Waterfront Street End | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Mar 2028 | Jan 2025 | Mar 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAVEWWF | Avenue W Waterfront Street End | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2028 | Apr 2028 | Mar 2025 | Apr 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAVEXWF | Avenue X Waterfront Street End | 1 | DEVELOP SCOPE | Jun 2025 | Sep 2025 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAVEXWF | Avenue X Waterfront Street End | 2 | PRELIMINARY DESIGN | Sep 2025 | Jan 2026 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAVEXWF | Avenue X Waterfront Street End | 3 | FINAL DESIGN | Jan 2026 | Jul 2026 | Jan 2024 | Jul 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAVEXWF | Avenue X Waterfront Street End | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2026 | Oct 2026 | Jul 2024 | Oct 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAVEXWF | Avenue X Waterfront Street End | 5 | CONSTRUCTION TO 25% | Oct 2026 | Feb 2027 | Oct 2024 | Feb 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAVEXWF | Avenue X Waterfront Street End | 6 | CONSTRUCTION TO 50% | Feb 2027 | Jun 2027 | Feb 2025 | Jun 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAVEXWF | Avenue X Waterfront Street End | 7 | CONSTRUCTION TO 75% | Jun 2027 | Oct 2027 | Jun 2025 | Oct 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAVEXWF | Avenue X Waterfront Street End | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jan 2028 | Oct 2025 | Jan 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAVEXWF | Avenue X Waterfront Street End | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Mar 2028 | Jan 2026 | Mar 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKAVEXWF | Avenue X Waterfront Street End | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2028 | Apr 2028 | Mar 2026 | Apr 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKBCCTWF | Beacon Court Waterfront Street End | 1 | DEVELOP SCOPE | Jun 2025 | Sep 2025 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKBCCTWF | Beacon Court Waterfront Street End | 2 | PRELIMINARY DESIGN | Sep 2025 | Jan 2026 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKBCCTWF | Beacon Court Waterfront Street End | 3 | FINAL DESIGN | Jan 2026 | Jul 2026 | Jan 2024 | Jul 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKBCCTWF | Beacon Court Waterfront Street End | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2026 | Oct 2026 | Jul 2024 | Oct 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKBCCTWF | Beacon Court Waterfront Street End | 5 | CONSTRUCTION TO 25% | Oct 2026 | Feb 2027 | Oct 2024 | Feb 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKBCCTWF | Beacon Court Waterfront Street End | 6 | CONSTRUCTION TO 50% | Feb 2027 | Jun 2027 | Feb 2025 | Jun 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKBCCTWF | Beacon Court Waterfront Street End | 7 | CONSTRUCTION TO 75% | Jun 2027 | Oct 2027 | Jun 2025 | Oct 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKBCCTWF | Beacon Court Waterfront Street End | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jan 2028 | Oct 2025 | Jan 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKBCCTWF | Beacon Court Waterfront Street End | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Mar 2028 | Jan 2026 | Mar 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKBCCTWF | Beacon Court Waterfront Street End | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2028 | Apr 2028 | Mar 2026 | Apr 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKDAREWF | Plumb Beach Channel Waterfront - Dare Court Street End | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKDAREWF | Plumb Beach Channel Waterfront - Dare Court Street End | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKDAREWF | Plumb Beach Channel Waterfront - Dare Court Street End | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKDAREWF | Plumb Beach Channel Waterfront - Dare Court Street End | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKDAREWF | Plumb Beach Channel Waterfront - Dare Court Street End | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKDAREWF | Plumb Beach Channel Waterfront - Dare Court Street End | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKDAREWF | Plumb Beach Channel Waterfront - Dare Court Street End | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKDAREWF | Plumb Beach Channel Waterfront - Dare Court Street End | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKDAREWF | Plumb Beach Channel Waterfront - Dare Court Street End | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKDAREWF | Plumb Beach Channel Waterfront - Dare Court Street End | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKE68WF | East 68th Street End Waterfront | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKE68WF | East 68th Street End Waterfront | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKE68WF | East 68th Street End Waterfront | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKE68WF | East 68th Street End Waterfront | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKE68WF | East 68th Street End Waterfront | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKE68WF | East 68th Street End Waterfront | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKE68WF | East 68th Street End Waterfront | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKE68WF | East 68th Street End Waterfront | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKE68WF | East 68th Street End Waterfront | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKE68WF | East 68th Street End Waterfront | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF029Z | FLATLANDS YARD AND STRUCTURES REHABILITATION | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF029Z | FLATLANDS YARD AND STRUCTURES REHABILITATION | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Sep 2018 | Jan 2019
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF029Z | FLATLANDS YARD AND STRUCTURES REHABILITATION | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2019 | Jul 2019
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF029Z | FLATLANDS YARD AND STRUCTURES REHABILITATION | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2019 | Oct 2019
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF029Z | FLATLANDS YARD AND STRUCTURES REHABILITATION | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2019 | Feb 2020
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF029Z | FLATLANDS YARD AND STRUCTURES REHABILITATION | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2020 | Jun 2020
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF029Z | FLATLANDS YARD AND STRUCTURES REHABILITATION | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2020 | Oct 2020
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF029Z | FLATLANDS YARD AND STRUCTURES REHABILITATION | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2020 | Jan 2021
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF029Z | FLATLANDS YARD AND STRUCTURES REHABILITATION | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2021 | Mar 2021
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF029Z | FLATLANDS YARD AND STRUCTURES REHABILITATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2021 | Apr 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF3000 | 3000 Flatbush Ave Trailers | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2025 | Sep 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF3000 | 3000 Flatbush Ave Trailers | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2025 | Jan 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF3000 | 3000 Flatbush Ave Trailers | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2026 | Jul 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF3000 | 3000 Flatbush Ave Trailers | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2026 | Oct 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF3000 | 3000 Flatbush Ave Trailers | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2026 | Feb 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF3000 | 3000 Flatbush Ave Trailers | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2027 | Jun 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF3000 | 3000 Flatbush Ave Trailers | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2027 | Oct 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF3000 | 3000 Flatbush Ave Trailers | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2027 | Jan 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF3000 | 3000 Flatbush Ave Trailers | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2028 | Mar 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF3000 | 3000 Flatbush Ave Trailers | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2028 | Apr 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFANEWF | Shell Bank Creek - Fane Court Street End | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2028 | Sep 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFANEWF | Shell Bank Creek - Fane Court Street End | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2028 | Jan 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFANEWF | Shell Bank Creek - Fane Court Street End | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2029 | Jul 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFANEWF | Shell Bank Creek - Fane Court Street End | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2029 | Oct 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFANEWF | Shell Bank Creek - Fane Court Street End | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2029 | Feb 2030
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFANEWF | Shell Bank Creek - Fane Court Street End | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2030 | Jun 2030
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFANEWF | Shell Bank Creek - Fane Court Street End | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2030 | Oct 2030
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFANEWF | Shell Bank Creek - Fane Court Street End | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2023 | Jan 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFANEWF | Shell Bank Creek - Fane Court Street End | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2024 | Mar 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFANEWF | Shell Bank Creek - Fane Court Street End | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2024 | Apr 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFBERRY | Berry Street | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2028 | Sep 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFBERRY | Berry Street | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2028 | Jan 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFBERRY | Berry Street | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2029 | Jul 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFBERRY | Berry Street | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2029 | Oct 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFBERRY | Berry Street | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2029 | Feb 2030
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFBERRY | Berry Street | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2030 | Jun 2030
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFBERRY | Berry Street | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2030 | Oct 2030
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFBERRY | Berry Street | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Jun 2028 | Jan 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFBERRY | Berry Street | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2031 | Mar 2031
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFBERRY | Berry Street | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2031 | Apr 2031
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFCBWF | Fresh Creek Basin - 4 Waterfront Street Ends | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFCBWF | Fresh Creek Basin - 4 Waterfront Street Ends | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFCBWF | Fresh Creek Basin - 4 Waterfront Street Ends | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFCBWF | Fresh Creek Basin - 4 Waterfront Street Ends | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFCBWF | Fresh Creek Basin - 4 Waterfront Street Ends | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFCBWF | Fresh Creek Basin - 4 Waterfront Street Ends | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFCBWF | Fresh Creek Basin - 4 Waterfront Street Ends | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFCBWF | Fresh Creek Basin - 4 Waterfront Street Ends | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFCBWF | Fresh Creek Basin - 4 Waterfront Street Ends | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFCBWF | Fresh Creek Basin - 4 Waterfront Street Ends | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFFAWF | Flatlands Avenue Waterfront Structures | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2024 | Sep 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFFAWF | Flatlands Avenue Waterfront Structures | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2024 | Jan 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFFAWF | Flatlands Avenue Waterfront Structures | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2025 | Jul 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFFAWF | Flatlands Avenue Waterfront Structures | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2025 | Oct 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFFAWF | Flatlands Avenue Waterfront Structures | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2025 | Feb 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFFAWF | Flatlands Avenue Waterfront Structures | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2026 | Jun 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFFAWF | Flatlands Avenue Waterfront Structures | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2026 | Oct 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFFAWF | Flatlands Avenue Waterfront Structures | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2026 | Jan 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFFAWF | Flatlands Avenue Waterfront Structures | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2027 | Mar 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFFAWF | Flatlands Avenue Waterfront Structures | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2027 | Apr 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFRH | Red Hook Build-out | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2026 | Sep 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFRH | Red Hook Build-out | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2026 | Jan 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFRH | Red Hook Build-out | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2027 | Jul 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFRH | Red Hook Build-out | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2027 | Oct 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFRH | Red Hook Build-out | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2027 | Feb 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFRH | Red Hook Build-out | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2028 | Jun 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFRH | Red Hook Build-out | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2028 | Oct 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFRH | Red Hook Build-out | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2028 | Jan 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFRH | Red Hook Build-out | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2029 | Mar 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFRH | Red Hook Build-out | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2029 | Apr 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFTNT | RRM Storage Tent Replacement | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2024 | Sep 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFTNT | RRM Storage Tent Replacement | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2024 | Jan 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFTNT | RRM Storage Tent Replacement | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2025 | Jul 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFTNT | RRM Storage Tent Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2025 | Oct 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFTNT | RRM Storage Tent Replacement | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2025 | Feb 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFTNT | RRM Storage Tent Replacement | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2026 | Jun 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFTNT | RRM Storage Tent Replacement | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2026 | Oct 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFTNT | RRM Storage Tent Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2026 | Jan 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFTNT | RRM Storage Tent Replacement | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2027 | Mar 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFTNT | RRM Storage Tent Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2027 | Apr 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKGOWANS | Gowanus Points of Agreement | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKGOWANS | Gowanus Points of Agreement | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKGOWANS | Gowanus Points of Agreement | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKGOWANS | Gowanus Points of Agreement | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKGOWANS | Gowanus Points of Agreement | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKGOWANS | Gowanus Points of Agreement | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKGOWANS | Gowanus Points of Agreement | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKGOWANS | Gowanus Points of Agreement | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKGOWANS | Gowanus Points of Agreement | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKGOWANS | Gowanus Points of Agreement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2030 | Mar 2026 | Apr 2030
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKGPAVWF | Greenpoint Avenue Waterfront Street End | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKGPAVWF | Greenpoint Avenue Waterfront Street End | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKGPAVWF | Greenpoint Avenue Waterfront Street End | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKGPAVWF | Greenpoint Avenue Waterfront Street End | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKGPAVWF | Greenpoint Avenue Waterfront Street End | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKGPAVWF | Greenpoint Avenue Waterfront Street End | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKGPAVWF | Greenpoint Avenue Waterfront Street End | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKGPAVWF | Greenpoint Avenue Waterfront Street End | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKGPAVWF | Greenpoint Avenue Waterfront Street End | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKGPAVWF | Greenpoint Avenue Waterfront Street End | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMEEKWF | Meeker Avenue Waterfront Street End | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMEEKWF | Meeker Avenue Waterfront Street End | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMEEKWF | Meeker Avenue Waterfront Street End | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMEEKWF | Meeker Avenue Waterfront Street End | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMEEKWF | Meeker Avenue Waterfront Street End | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMEEKWF | Meeker Avenue Waterfront Street End | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMEEKWF | Meeker Avenue Waterfront Street End | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMEEKWF | Meeker Avenue Waterfront Street End | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMEEKWF | Meeker Avenue Waterfront Street End | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMEEKWF | Meeker Avenue Waterfront Street End | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMETWF | Newtown Creek Waterfront - Metropolitan Ave Street End | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMETWF | Newtown Creek Waterfront - Metropolitan Ave Street End | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMETWF | Newtown Creek Waterfront - Metropolitan Ave Street End | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMETWF | Newtown Creek Waterfront - Metropolitan Ave Street End | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMETWF | Newtown Creek Waterfront - Metropolitan Ave Street End | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMETWF | Newtown Creek Waterfront - Metropolitan Ave Street End | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMETWF | Newtown Creek Waterfront - Metropolitan Ave Street End | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMETWF | Newtown Creek Waterfront - Metropolitan Ave Street End | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMETWF | Newtown Creek Waterfront - Metropolitan Ave Street End | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMETWF | Newtown Creek Waterfront - Metropolitan Ave Street End | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMETWF2 | Metropolitan Avenue Waterfront at Onderdonk Avenue | 1 | DEVELOP SCOPE | Jun 2025 | Sep 2025 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMETWF2 | Metropolitan Avenue Waterfront at Onderdonk Avenue | 2 | PRELIMINARY DESIGN | Sep 2025 | Jan 2026 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMETWF2 | Metropolitan Avenue Waterfront at Onderdonk Avenue | 3 | FINAL DESIGN | Jan 2026 | Jul 2026 | Jan 2024 | Jul 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMETWF2 | Metropolitan Avenue Waterfront at Onderdonk Avenue | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2026 | Oct 2026 | Jul 2024 | Oct 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMETWF2 | Metropolitan Avenue Waterfront at Onderdonk Avenue | 5 | CONSTRUCTION TO 25% | Oct 2026 | Feb 2027 | Oct 2024 | Feb 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMETWF2 | Metropolitan Avenue Waterfront at Onderdonk Avenue | 6 | CONSTRUCTION TO 50% | Feb 2027 | Jun 2027 | Feb 2025 | Jun 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMETWF2 | Metropolitan Avenue Waterfront at Onderdonk Avenue | 7 | CONSTRUCTION TO 75% | Jun 2027 | Oct 2027 | Jun 2025 | Oct 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMETWF2 | Metropolitan Avenue Waterfront at Onderdonk Avenue | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jan 2028 | Oct 2025 | Jan 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMETWF2 | Metropolitan Avenue Waterfront at Onderdonk Avenue | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Mar 2028 | Jan 2026 | Mar 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMETWF2 | Metropolitan Avenue Waterfront at Onderdonk Avenue | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2028 | Apr 2028 | Mar 2026 | Apr 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMGB | McGuinness Blvd Safety Improvements | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2021 | Sep 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMGB | McGuinness Blvd Safety Improvements | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2027 | Jan 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMGB | McGuinness Blvd Safety Improvements | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2028 | Jul 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMGB | McGuinness Blvd Safety Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2028 | Oct 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMGB | McGuinness Blvd Safety Improvements | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2028 | Feb 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMGB | McGuinness Blvd Safety Improvements | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2029 | Jun 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMGB | McGuinness Blvd Safety Improvements | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2029 | Oct 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMGB | McGuinness Blvd Safety Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2029 | Jan 2030
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMGB | McGuinness Blvd Safety Improvements | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2030 | Mar 2030
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMGB | McGuinness Blvd Safety Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2030 | Apr 2030
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMSPTWF | Newton Creek Waterfront - Maspeth Ave Street End | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMSPTWF | Newton Creek Waterfront - Maspeth Ave Street End | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMSPTWF | Newton Creek Waterfront - Maspeth Ave Street End | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMSPTWF | Newton Creek Waterfront - Maspeth Ave Street End | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMSPTWF | Newton Creek Waterfront - Maspeth Ave Street End | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMSPTWF | Newton Creek Waterfront - Maspeth Ave Street End | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMSPTWF | Newton Creek Waterfront - Maspeth Ave Street End | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMSPTWF | Newton Creek Waterfront - Maspeth Ave Street End | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMSPTWF | Newton Creek Waterfront - Maspeth Ave Street End | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMSPTWF | Newton Creek Waterfront - Maspeth Ave Street End | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKNBP | North Brooklyn Pedestrian Safety | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2025 | Sep 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKNBP | North Brooklyn Pedestrian Safety | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2025 | Jan 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKNBP | North Brooklyn Pedestrian Safety | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2026 | Jul 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKNBP | North Brooklyn Pedestrian Safety | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2026 | Oct 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKNBP | North Brooklyn Pedestrian Safety | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2026 | Feb 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKNBP | North Brooklyn Pedestrian Safety | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2027 | Jun 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKNBP | North Brooklyn Pedestrian Safety | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2027 | Oct 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKNBP | North Brooklyn Pedestrian Safety | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2027 | Jan 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKNBP | North Brooklyn Pedestrian Safety | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2028 | Mar 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKNBP | North Brooklyn Pedestrian Safety | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2028 | Apr 2028
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKNUAV | New Utrecht Ave Micro-Milling and Reconstruction | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2024 | Sep 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKNUAV | New Utrecht Ave Micro-Milling and Reconstruction | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2024 | Jan 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKNUAV | New Utrecht Ave Micro-Milling and Reconstruction | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2025 | Jul 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKNUAV | New Utrecht Ave Micro-Milling and Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2025 | Oct 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKNUAV | New Utrecht Ave Micro-Milling and Reconstruction | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2025 | Feb 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKNUAV | New Utrecht Ave Micro-Milling and Reconstruction | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2026 | Jun 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKNUAV | New Utrecht Ave Micro-Milling and Reconstruction | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2026 | Oct 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKNUAV | New Utrecht Ave Micro-Milling and Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2026 | Jan 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKNUAV | New Utrecht Ave Micro-Milling and Reconstruction | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2027 | Mar 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKNUAV | New Utrecht Ave Micro-Milling and Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2027 | Apr 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWP23KC | Non-Standard Ped Ramps - Brooklyn | 1 | DEVELOP SCOPE | Jun 2030 | Sep 2030 | Jun 2024 | Sep 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWP23KC | Non-Standard Ped Ramps - Brooklyn | 2 | PRELIMINARY DESIGN | Sep 2030 | Jan 2031 | Sep 2024 | Jan 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWP23KC | Non-Standard Ped Ramps - Brooklyn | 3 | FINAL DESIGN | Jan 2031 | Jul 2031 | Jan 2025 | Jul 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWP23KC | Non-Standard Ped Ramps - Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2031 | Oct 2031 | Jul 2025 | Oct 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWP23KC | Non-Standard Ped Ramps - Brooklyn | 5 | CONSTRUCTION TO 25% | Oct 2031 | Feb 2032 | Oct 2025 | Feb 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWP23KC | Non-Standard Ped Ramps - Brooklyn | 6 | CONSTRUCTION TO 50% | Feb 2032 | Jun 2032 | Feb 2026 | Jun 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWP23KC | Non-Standard Ped Ramps - Brooklyn | 7 | CONSTRUCTION TO 75% | Jun 2032 | Oct 2032 | Jun 2026 | Oct 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWP23KC | Non-Standard Ped Ramps - Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2032 | Jan 2033 | Oct 2026 | Jan 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWP23KC | Non-Standard Ped Ramps - Brooklyn | 9 | SUBSTANTIAL COMPLETION | Jan 2033 | Mar 2033 | Jan 2027 | Mar 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWP23KC | Non-Standard Ped Ramps - Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2033 | Apr 2033 | Mar 2027 | Apr 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024K | Prior Notice Sidewalks - Brooklyn | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2024 | Sep 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024K | Prior Notice Sidewalks - Brooklyn | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2024 | Jan 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024K | Prior Notice Sidewalks - Brooklyn | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2025 | Jul 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024K | Prior Notice Sidewalks - Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2025 | Oct 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024K | Prior Notice Sidewalks - Brooklyn | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2025 | Feb 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024K | Prior Notice Sidewalks - Brooklyn | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2026 | Jun 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024K | Prior Notice Sidewalks - Brooklyn | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2026 | Oct 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024K | Prior Notice Sidewalks - Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2026 | Jan 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024K | Prior Notice Sidewalks - Brooklyn | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2027 | Mar 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024K | Prior Notice Sidewalks - Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2027 | Apr 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | NDF-CCIMP | NDF - Commercial Corridor Improvements | 1 | DESIGN | Jul 2016 | Jul 2016 | Jul 2018 | Jul 2018
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | NDF-CCIMP | NDF - Commercial Corridor Improvements | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Jul 2018 | Aug 2018
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | NDF-CCIMP | NDF - Commercial Corridor Improvements | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Aug 2018 | Sep 2018
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | NDF-CCIMP | NDF - Commercial Corridor Improvements | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Sep 2018 | Sep 2018
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | NDF-CCIMP | NDF - Commercial Corridor Improvements | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Sep 2018 | Oct 2018
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | NDF-CCIMP | NDF - Commercial Corridor Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2016 | Oct 2018 | Oct 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF18-2017 | AVENUE M MUNICIPAL PARKING FIELD | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2014 | Jun 2014 | Jun 2020 | Jun 2020
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF18-2017 | AVENUE M MUNICIPAL PARKING FIELD | 2 | CONSTRUCTION START | Jun 2014 | Jul 2014 | Jun 2020 | Jul 2020
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF18-2017 | AVENUE M MUNICIPAL PARKING FIELD | 3 | CONSTRUCTION COMPLETION | Jul 2014 | Feb 2016 | Jul 2020 | Jun 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50311 | Rpl St lg pl Bedford Ave fm Campus Rd to Foster Ave-XMA165.3 | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2024 | Sep 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50311 | Rpl St lg pl Bedford Ave fm Campus Rd to Foster Ave-XMA165.3 | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2024 | Jan 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50311 | Rpl St lg pl Bedford Ave fm Campus Rd to Foster Ave-XMA165.3 | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jan 2025 | Jul 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50311 | Rpl St lg pl Bedford Ave fm Campus Rd to Foster Ave-XMA165.3 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2025 | Oct 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50311 | Rpl St lg pl Bedford Ave fm Campus Rd to Foster Ave-XMA165.3 | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Oct 2025 | Feb 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50311 | Rpl St lg pl Bedford Ave fm Campus Rd to Foster Ave-XMA165.3 | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Feb 2026 | Jun 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50311 | Rpl St lg pl Bedford Ave fm Campus Rd to Foster Ave-XMA165.3 | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jun 2026 | Oct 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50311 | Rpl St lg pl Bedford Ave fm Campus Rd to Foster Ave-XMA165.3 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Oct 2026 | Jan 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50311 | Rpl St lg pl Bedford Ave fm Campus Rd to Foster Ave-XMA165.3 | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jan 2027 | Mar 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50311 | Rpl St lg pl Bedford Ave fm Campus Rd to Foster Ave-XMA165.3 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Mar 2027 | Jul 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50313 | Instl lg on Cortelyou Rd&Newkirk XMA193.30 & A835 | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Jun 2019 | Jun 2020 | Jun 2020
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50313 | Instl lg on Cortelyou Rd&Newkirk XMA193.30 & A835 | 2 | CONSTRUCTION START | Jul 2019 | Aug 2019 | Jul 2020 | Aug 2020
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50313 | Instl lg on Cortelyou Rd&Newkirk XMA193.30 & A835 | 3 | CONSTRUCTION COMPLETION | Aug 2019 | Mar 2021 | Aug 2020 | Jun 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50315 | Historic St lg poles on Mermaid Avenue bet W21St &W29th St, | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Jun 2018 | Jun 2018 | Jun 2018
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50315 | Historic St lg poles on Mermaid Avenue bet W21St &W29th St, | 2 | CONSTRUCTION START | Jul 2018 | Aug 2018 | Jul 2018 | Aug 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50315 | Historic St lg poles on Mermaid Avenue bet W21St &W29th St, | 3 | CONSTRUCTION COMPLETION | Aug 2018 | Mar 2020 | Aug 2022 | Mar 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50317 | Upgrade of poles& lg on McDonald Ave, fr BPWY&Kingshwy Ave R | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Jun 2019 | Jun 2019 | Jun 2019
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50317 | Upgrade of poles& lg on McDonald Ave, fr BPWY&Kingshwy Ave R | 2 | CONSTRUCTION START | Jul 2019 | Aug 2019 | Jul 2019 | Aug 2019
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50317 | Upgrade of poles& lg on McDonald Ave, fr BPWY&Kingshwy Ave R | 3 | CONSTRUCTION COMPLETION | Aug 2019 | Mar 2021 | Aug 2019 | Mar 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50319 | St light on Steinway Bus Corridor XA2308 | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Jun 2023 | Jun 2023 | Jun 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50319 | St light on Steinway Bus Corridor XA2308 | 2 | CONSTRUCTION START | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50319 | St light on Steinway Bus Corridor XA2308 | 3 | CONSTRUCTION COMPLETION | Aug 2023 | Mar 2026 | Aug 2023 | Mar 2026
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503K23 | BROOKLYN HEIGHTS HISTORIC LIGHTING | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2011 | Jun 2011 | Jun 2019 | Jun 2019
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503K23 | BROOKLYN HEIGHTS HISTORIC LIGHTING | 2 | CONSTRUCTION START | Jul 2011 | Aug 2011 | Jul 2019 | Aug 2019
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503K23 | BROOKLYN HEIGHTS HISTORIC LIGHTING | 3 | CONSTRUCTION COMPLETION | Aug 2011 | Mar 2013 | Aug 2019 | Mar 2025
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503K26 | FLATBUSH AVE. ST. PURCHASE AND INSTALLATION OF LAMP POST | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2011 | Jun 2011 | Jun 2022 | Jun 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503K26 | FLATBUSH AVE. ST. PURCHASE AND INSTALLATION OF LAMP POST | 2 | CONSTRUCTION START | Jul 2011 | Aug 2011 | Jul 2022 | Aug 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503K26 | FLATBUSH AVE. ST. PURCHASE AND INSTALLATION OF LAMP POST | 3 | CONSTRUCTION COMPLETION | Aug 2011 | Mar 2013 | Aug 2022 | Mar 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503KCD | COUNTDOWN CLOCKS INSTALLATION IN BENSONHURST, BKLYN | 3 | CONSTRUCTION COMPLETION | Jul 2014 | Feb 2016 | Jul 2014 | Feb 2016
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFK50313 | Historic Lighting on Broadway btw Roebling and Bedford | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2013 | Jun 2013 | Jun 2024 | Jun 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFK50313 | Historic Lighting on Broadway btw Roebling and Bedford | 2 | CONSTRUCTION START | Jul 2013 | Aug 2013 | Jul 2024 | Aug 2024
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFK50313 | Historic Lighting on Broadway btw Roebling and Bedford | 3 | CONSTRUCTION COMPLETION | Aug 2013 | Mar 2015 | Aug 2024 | Mar 2030
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFKVANDMD | VANDERBILT AVE MERCHANTS DISTRICT/PHNDC: ELEGANT STREET LIG | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2017 | Jun 2017 | Jun 2022 | Jun 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFKVANDMD | VANDERBILT AVE MERCHANTS DISTRICT/PHNDC: ELEGANT STREET LIG | 2 | CONSTRUCTION START | Jul 2017 | Aug 2017 | Jul 2022 | Aug 2022
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFKVANDMD | VANDERBILT AVE MERCHANTS DISTRICT/PHNDC: ELEGANT STREET LIG | 3 | CONSTRUCTION COMPLETION | Aug 2017 | Mar 2019 | Aug 2022 | Mar 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFLGAVEU | St Lg on Ave U from Ocean Pkwy to McDonald Ave XMA206.30A | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2017 | Jun 2017 | Jun 2027 | Jun 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFLGAVEU | St Lg on Ave U from Ocean Pkwy to McDonald Ave XMA206.30A | 2 | CONSTRUCTION START | Jul 2017 | Aug 2017 | Jul 2027 | Aug 2027
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFLGAVEU | St Lg on Ave U from Ocean Pkwy to McDonald Ave XMA206.30A | 3 | CONSTRUCTION COMPLETION | Aug 2017 | Mar 2019 | Aug 2027 | Mar 2029
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFLIVSTLG | Install lSt on Livingston Street, Brooklyn | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Jun 2023 | Jun 2023 | Jun 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFLIVSTLG | Install lSt on Livingston Street, Brooklyn | 2 | CONSTRUCTION START | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFLIVSTLG | Install lSt on Livingston Street, Brooklyn | 3 | CONSTRUCTION COMPLETION | Aug 2023 | Mar 2025 | Aug 2023 | Mar 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | GKBKGI-01 | GI - DSGN & CONS OF PARKLAND RETROFITS IN BROOKLYN | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | GKBKGI-01 | GI - DSGN & CONS OF PARKLAND RETROFITS IN BROOKLYN | 2 | DESIGN | Dec 2018 | Jun 2020 | Dec 2018 | Jun 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | GKBKGI-01 | GI - DSGN & CONS OF PARKLAND RETROFITS IN BROOKLYN | 3 | BID/ REGISTER CONTRACT | Jun 2020 | Mar 2021 | Jun 2020 | Mar 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | GKBKGI-01 | GI - DSGN & CONS OF PARKLAND RETROFITS IN BROOKLYN | 4 | CONSTRUCTION | Mar 2021 | Mar 2024 | Mar 2021 | Mar 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | GKBKGI-01 | GI - DSGN & CONS OF PARKLAND RETROFITS IN BROOKLYN | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Mar 2026 | Mar 2024 | Jun 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-BNDST | NDF- Bond Street End BZ-223M | 1 | DEVELOP SCOPE | Jun 2023 | Dec 2023 | Jun 2023 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-BNDST | NDF- Bond Street End BZ-223M | 2 | DESIGN | Dec 2023 | Dec 2024 | Dec 2023 | Dec 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-BNDST | NDF- Bond Street End BZ-223M | 3 | BID/ REGISTER CONTRACT | Dec 2024 | Sep 2025 | Dec 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-BNDST | NDF- Bond Street End BZ-223M | 4 | CONSTRUCTION | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-BNDST | NDF- Bond Street End BZ-223M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-BRMPK | NDF- Boerum Park | 1 | DEVELOP SCOPE | Jun 2023 | Dec 2023 | Jun 2023 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-BRMPK | NDF- Boerum Park | 2 | DESIGN | Dec 2023 | Dec 2024 | Dec 2023 | Dec 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-BRMPK | NDF- Boerum Park | 3 | BID/ REGISTER CONTRACT | Dec 2024 | Sep 2025 | Dec 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-BRMPK | NDF- Boerum Park | 4 | CONSTRUCTION | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-BRMPK | NDF- Boerum Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-CLNE | NDF- East New York - City Line Park | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-CLNE | NDF- East New York - City Line Park | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-CLNE | NDF- East New York - City Line Park | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-CLNE | NDF- East New York - City Line Park | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-CLNE | NDF- East New York - City Line Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2019 | Jun 2033
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-CLNKY | NDF - Callahan-Kelly Park B219-117M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-CLNKY | NDF - Callahan-Kelly Park B219-117M | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-CLNKY | NDF - Callahan-Kelly Park B219-117M | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-CLNKY | NDF - Callahan-Kelly Park B219-117M | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-CLNKY | NDF - Callahan-Kelly Park B219-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-GESPL | NDF - Gowanus Esplanade to 9th Street BZ-123M | 1 | DEVELOP SCOPE | Jun 2023 | Dec 2023 | Jun 2023 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-GESPL | NDF - Gowanus Esplanade to 9th Street BZ-123M | 2 | DESIGN | Dec 2023 | Dec 2024 | Dec 2023 | Dec 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-GESPL | NDF - Gowanus Esplanade to 9th Street BZ-123M | 3 | BID/ REGISTER CONTRACT | Dec 2024 | Sep 2025 | Dec 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-GESPL | NDF - Gowanus Esplanade to 9th Street BZ-123M | 4 | CONSTRUCTION | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-GESPL | NDF - Gowanus Esplanade to 9th Street BZ-123M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-GGPRK | NDF- Gowanus Green Park | 1 | DEVELOP SCOPE | Jun 2025 | Dec 2025 | Jun 2025 | Dec 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-GGPRK | NDF- Gowanus Green Park | 2 | DESIGN | Dec 2025 | Dec 2026 | Dec 2025 | Dec 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-GGPRK | NDF- Gowanus Green Park | 3 | BID/ REGISTER CONTRACT | Dec 2026 | Sep 2027 | Dec 2026 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-GGPRK | NDF- Gowanus Green Park | 4 | CONSTRUCTION | Sep 2027 | Sep 2028 | Sep 2027 | Sep 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-GGPRK | NDF- Gowanus Green Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2028 | Sep 2029 | Sep 2028 | Sep 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN3 | NDF - Highland Park Eastern Playground R/C Q020-119M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN3 | NDF - Highland Park Eastern Playground R/C Q020-119M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN3 | NDF - Highland Park Eastern Playground R/C Q020-119M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN3 | NDF - Highland Park Eastern Playground R/C Q020-119M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN3 | NDF - Highland Park Eastern Playground R/C Q020-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2032
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN4 | Highland Park Plgd Public Restroom building recon Q020-219M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN4 | Highland Park Plgd Public Restroom building recon Q020-219M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN4 | Highland Park Plgd Public Restroom building recon Q020-219M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN4 | Highland Park Plgd Public Restroom building recon Q020-219M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN4 | Highland Park Plgd Public Restroom building recon Q020-219M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2031
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN5 | NDF - Highland Park Pedestrian Improvements Q020-118M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN5 | NDF - Highland Park Pedestrian Improvements Q020-118M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN5 | NDF - Highland Park Pedestrian Improvements Q020-118M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN5 | NDF - Highland Park Pedestrian Improvements Q020-118M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN5 | NDF - Highland Park Pedestrian Improvements Q020-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jul 2031
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLND | Neighborhood Dev. Fund - East NY - Highland Park Q020-216M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLND | Neighborhood Dev. Fund - East NY - Highland Park Q020-216M | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLND | Neighborhood Dev. Fund - East NY - Highland Park Q020-216M | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLND | Neighborhood Dev. Fund - East NY - Highland Park Q020-216M | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLND | Neighborhood Dev. Fund - East NY - Highland Park Q020-216M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2019 | Jun 2033
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-OLDSH | NDF- Old Stone House ADA Upgrades | 1 | DEVELOP SCOPE | Jun 2023 | Dec 2023 | Jun 2023 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-OLDSH | NDF- Old Stone House ADA Upgrades | 2 | DESIGN | Dec 2023 | Dec 2024 | Dec 2023 | Dec 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-OLDSH | NDF- Old Stone House ADA Upgrades | 3 | BID/ REGISTER CONTRACT | Dec 2024 | Sep 2025 | Dec 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-OLDSH | NDF- Old Stone House ADA Upgrades | 4 | CONSTRUCTION | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-OLDSH | NDF- Old Stone House ADA Upgrades | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200884L | Prospect Park Zoo - Amur Leopard exhibit | 1 | DEVELOP SCOPE | Jul 2006 | Sep 2006 | Jul 2006 | Sep 2006
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200884L | Prospect Park Zoo - Amur Leopard exhibit | 2 | DESIGN | Sep 2006 | Dec 2006 | Sep 2006 | Dec 2006
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200884L | Prospect Park Zoo - Amur Leopard exhibit | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Dec 2006 | Mar 2007
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200884L | Prospect Park Zoo - Amur Leopard exhibit | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Mar 2007 | Mar 2008
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200884L | Prospect Park Zoo - Amur Leopard exhibit | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Mar 2008 | Nov 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200CPSW | Canarsie Park Sidewalk Reconstruction | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200CPSW | Canarsie Park Sidewalk Reconstruction | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200CPSW | Canarsie Park Sidewalk Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200CPSW | Canarsie Park Sidewalk Reconstruction | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200CPSW | Canarsie Park Sidewalk Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200CRSL | PPA- Recon. Carousel (B073-218M) | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200CRSL | PPA- Recon. Carousel (B073-218M) | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200CRSL | PPA- Recon. Carousel (B073-218M) | 4 | CONSTRUCTION | Sep 2018 | Mar 2020 | Sep 2018 | Mar 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200CRSL | PPA- Recon. Carousel (B073-218M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Mar 2021 | Mar 2020 | Mar 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200FITS | PPA- Prospect Park Fitness Playground/Equipment (B068-119M) | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200FITS | PPA- Prospect Park Fitness Playground/Equipment (B068-119M) | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200FITS | PPA- Prospect Park Fitness Playground/Equipment (B068-119M) | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200FITS | PPA- Prospect Park Fitness Playground/Equipment (B068-119M) | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200FITS | PPA- Prospect Park Fitness Playground/Equipment (B068-119M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200HPPP | PPA - Harmony Playground Improvements B073-119M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200HPPP | PPA - Harmony Playground Improvements B073-119M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200HPPP | PPA - Harmony Playground Improvements B073-119M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200HPPP | PPA - Harmony Playground Improvements B073-119M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200HPPP | PPA - Harmony Playground Improvements B073-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200K01Q | PROSP PK BANDSHELL & LNDSCPE B073-598/898 & EQMPT OMBP 305M | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Mar 2007 | Mar 2008
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200K01Q | PROSP PK BANDSHELL & LNDSCPE B073-598/898 & EQMPT OMBP 305M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Mar 2008 | Mar 2009
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200LFHH | PPA- Restor. Lefferts Historic House B073-317M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200LFHH | PPA- Restor. Lefferts Historic House B073-317M | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200LFHH | PPA- Restor. Lefferts Historic House B073-317M | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200LFHH | PPA- Restor. Lefferts Historic House B073-317M | 4 | CONSTRUCTION | Sep 2018 | Mar 2020 | Sep 2019 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200LFHH | PPA- Restor. Lefferts Historic House B073-317M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Mar 2021 | Sep 2021 | Jun 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200LMBF | Prospect Park Long Meadow Ballfields 2&3 Recon. B073-219M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PERG | PPA - Pergola Restoration | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PERG | PPA - Pergola Restoration | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PERG | PPA - Pergola Restoration | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PERG | PPA - Pergola Restoration | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PERG | PPA - Pergola Restoration | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPBL | PPA- Long Meadow Ballfields 4-5 (B073-215M) | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPBL | PPA- Long Meadow Ballfields 4-5 (B073-215M) | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPBL | PPA- Long Meadow Ballfields 4-5 (B073-215M) | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPBL | PPA- Long Meadow Ballfields 4-5 (B073-215M) | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPBL | PPA- Long Meadow Ballfields 4-5 (B073-215M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPBS | PPA - Rehabilitate the bandshell lawn | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPBS | PPA - Rehabilitate the bandshell lawn | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPBS | PPA - Rehabilitate the bandshell lawn | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPBS | PPA - Rehabilitate the bandshell lawn | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPBS | PPA - Rehabilitate the bandshell lawn | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPCC | Prospect Park - Reconstruction of Children's Corner | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPCC | Prospect Park - Reconstruction of Children's Corner | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPCC | Prospect Park - Reconstruction of Children's Corner | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPCC | Prospect Park - Reconstruction of Children's Corner | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPCC | Prospect Park - Reconstruction of Children's Corner | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPCS | PP - Shirley Chisholm Recon. Welcome Ctr./Public Rest Room | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPCS | PP - Shirley Chisholm Recon. Welcome Ctr./Public Rest Room | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPCS | PP - Shirley Chisholm Recon. Welcome Ctr./Public Rest Room | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPCS | PP - Shirley Chisholm Recon. Welcome Ctr./Public Rest Room | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPCS | PP - Shirley Chisholm Recon. Welcome Ctr./Public Rest Room | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPEB | PPA - Esdale Bridge Restoration B073-223M | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPEB | PPA - Esdale Bridge Restoration B073-223M | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPEB | PPA - Esdale Bridge Restoration B073-223M | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPEB | PPA - Esdale Bridge Restoration B073-223M | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPEB | PPA - Esdale Bridge Restoration B073-223M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPEC | PPA - Environmental Cntr. Cons., Vale of Cashmere B073-222M | 1 | DEVELOP SCOPE | Jan 2022 | Jun 2022 | Jan 2022 | Jun 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPEC | PPA - Environmental Cntr. Cons., Vale of Cashmere B073-222M | 2 | DESIGN | Jun 2022 | Jun 2023 | Jun 2022 | Jun 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPEC | PPA - Environmental Cntr. Cons., Vale of Cashmere B073-222M | 3 | BID/ REGISTER CONTRACT | Jun 2023 | Mar 2024 | Jun 2023 | Mar 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPEC | PPA - Environmental Cntr. Cons., Vale of Cashmere B073-222M | 4 | CONSTRUCTION | Mar 2024 | Mar 2025 | Mar 2024 | Mar 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPEC | PPA - Environmental Cntr. Cons., Vale of Cashmere B073-222M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Mar 2026 | Mar 2025 | Mar 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPFB | PPA - Flatbush Avenue Park Perimeter B073-315M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPFB | PPA - Flatbush Avenue Park Perimeter B073-315M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPFB | PPA - Flatbush Avenue Park Perimeter B073-315M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPFB | PPA - Flatbush Avenue Park Perimeter B073-315M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPFB | PPA - Flatbush Avenue Park Perimeter B073-315M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPLV | PPA - Recon. of the Lower Portion of the Vale of Cashmere | 1 | DEVELOP SCOPE | Jan 2022 | Jun 2022 | Jan 2022 | Jun 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPLV | PPA - Recon. of the Lower Portion of the Vale of Cashmere | 2 | DESIGN | Jun 2022 | Jun 2023 | Jun 2022 | Jun 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPLV | PPA - Recon. of the Lower Portion of the Vale of Cashmere | 3 | BID/ REGISTER CONTRACT | Jun 2023 | Mar 2024 | Jun 2023 | Mar 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPLV | PPA - Recon. of the Lower Portion of the Vale of Cashmere | 4 | CONSTRUCTION | Mar 2024 | Mar 2025 | Mar 2024 | Mar 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPLV | PPA - Recon. of the Lower Portion of the Vale of Cashmere | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Mar 2026 | Mar 2025 | Mar 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPLW | PROSPECT PARK LAKE WATERFRONT RESTORATION | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPLW | PROSPECT PARK LAKE WATERFRONT RESTORATION | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPLW | PROSPECT PARK LAKE WATERFRONT RESTORATION | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPLW | PROSPECT PARK LAKE WATERFRONT RESTORATION | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPLW | PROSPECT PARK LAKE WATERFRONT RESTORATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Jun 2028 | Sep 2025 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPMB | PPA-Building Reconstruction (B073-319M) | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPMB | PPA-Building Reconstruction (B073-319M) | 2 | DESIGN | Dec 2017 | Jun 2019 | Dec 2017 | Jun 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPMB | PPA-Building Reconstruction (B073-319M) | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Mar 2020 | Jun 2019 | Mar 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPMB | PPA-Building Reconstruction (B073-319M) | 4 | CONSTRUCTION | Mar 2020 | Sep 2021 | Mar 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPMB | PPA-Building Reconstruction (B073-319M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPMO | PPA- New M&O Facility & Compound in Prospect Park B073-415M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPMO | PPA- New M&O Facility & Compound in Prospect Park B073-415M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPMO | PPA- New M&O Facility & Compound in Prospect Park B073-415M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPMO | PPA- New M&O Facility & Compound in Prospect Park B073-415M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPMO | PPA- New M&O Facility & Compound in Prospect Park B073-415M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Mar 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPNM | Prospect Park Nethermead - Repave Walking Path B073-221M | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPNM | Prospect Park Nethermead - Repave Walking Path B073-221M | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPNM | Prospect Park Nethermead - Repave Walking Path B073-221M | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPNM | Prospect Park Nethermead - Repave Walking Path B073-221M | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPNM | Prospect Park Nethermead - Repave Walking Path B073-221M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPOC | PPA Parkside & Ocean Aves Sidewalks Reconstruction B073-118M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPOC | PPA Parkside & Ocean Aves Sidewalks Reconstruction B073-118M | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPOC | PPA Parkside & Ocean Aves Sidewalks Reconstruction B073-118M | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPOC | PPA Parkside & Ocean Aves Sidewalks Reconstruction B073-118M | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPOC | PPA Parkside & Ocean Aves Sidewalks Reconstruction B073-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2019 | Jun 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPOP | PPA - Prospect Park Oriental Pavilion B073-416M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPOP | PPA - Prospect Park Oriental Pavilion B073-416M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPOP | PPA - Prospect Park Oriental Pavilion B073-416M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPOP | PPA - Prospect Park Oriental Pavilion B073-416M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPOP | PPA - Prospect Park Oriental Pavilion B073-416M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPPH | PPA- PROSPECT PARK PICNIC HOUSE RENOVATION B073-419M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPPH | PPA- PROSPECT PARK PICNIC HOUSE RENOVATION B073-419M | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPPH | PPA- PROSPECT PARK PICNIC HOUSE RENOVATION B073-419M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2013 | Mar 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPPH | PPA- PROSPECT PARK PICNIC HOUSE RENOVATION B073-419M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPPH | PPA- PROSPECT PARK PICNIC HOUSE RENOVATION B073-419M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2015 | Apr 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPPL | PPA - Pathway Lighting btwn. Nethermead & Ballfields & 70 W. | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPPL | PPA - Pathway Lighting btwn. Nethermead & Ballfields & 70 W. | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPPL | PPA - Pathway Lighting btwn. Nethermead & Ballfields & 70 W. | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPPL | PPA - Pathway Lighting btwn. Nethermead & Ballfields & 70 W. | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPPL | PPA - Pathway Lighting btwn. Nethermead & Ballfields & 70 W. | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPUV | PPA - Recon. of the Upper Portion of the Vale of Cashmere | 1 | DEVELOP SCOPE | Jan 2022 | Jun 2022 | Jan 2022 | Jun 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPUV | PPA - Recon. of the Upper Portion of the Vale of Cashmere | 2 | DESIGN | Jun 2022 | Jun 2023 | Jun 2022 | Jun 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPUV | PPA - Recon. of the Upper Portion of the Vale of Cashmere | 3 | BID/ REGISTER CONTRACT | Jun 2023 | Mar 2024 | Jun 2023 | Mar 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPUV | PPA - Recon. of the Upper Portion of the Vale of Cashmere | 4 | CONSTRUCTION | Mar 2024 | Mar 2025 | Mar 2024 | Mar 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPUV | PPA - Recon. of the Upper Portion of the Vale of Cashmere | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Mar 2026 | Mar 2025 | Mar 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPWM | PPA - Prospect Park - Water Line Reconstruction B073-321M | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPWM | PPA - Prospect Park - Water Line Reconstruction B073-321M | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPWM | PPA - Prospect Park - Water Line Reconstruction B073-321M | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPWM | PPA - Prospect Park - Water Line Reconstruction B073-321M | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPWM | PPA - Prospect Park - Water Line Reconstruction B073-321M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PRUN | PPA- Multiside, Drinking Fountain, BBQ Pits, Running Land | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PRUN | PPA- Multiside, Drinking Fountain, BBQ Pits, Running Land | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PRUN | PPA- Multiside, Drinking Fountain, BBQ Pits, Running Land | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PRUN | PPA- Multiside, Drinking Fountain, BBQ Pits, Running Land | 4 | CONSTRUCTION | Sep 2018 | Mar 2020 | Sep 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PRUN | PPA- Multiside, Drinking Fountain, BBQ Pits, Running Land | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Mar 2021 | Sep 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200STFP | PPA - Parade Ground replace turf field 9 (B068-118M) | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200STFP | PPA - Parade Ground replace turf field 9 (B068-118M) | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200STFP | PPA - Parade Ground replace turf field 9 (B068-118M) | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200STFP | PPA - Parade Ground replace turf field 9 (B068-118M) | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200STFP | PPA - Parade Ground replace turf field 9 (B068-118M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200TNCR | PPA- Prospect Park Tennis Center B068-121M | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200TNCR | PPA- Prospect Park Tennis Center B068-121M | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200TNCR | PPA- Prospect Park Tennis Center B068-121M | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200TNCR | PPA- Prospect Park Tennis Center B068-121M | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200TNCR | PPA- Prospect Park Tennis Center B068-121M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200WCST | PPA-Wellhouse Public Rest Room Renovation - (B073-209M) | 1 | DEVELOP SCOPE | Jul 2008 | Sep 2008 | Jul 2008 | Sep 2008
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200WCST | PPA-Wellhouse Public Rest Room Renovation - (B073-209M) | 2 | DESIGN | Sep 2008 | Dec 2008 | Sep 2008 | Dec 2008
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200WCST | PPA-Wellhouse Public Rest Room Renovation - (B073-209M) | 3 | BID/ REGISTER CONTRACT | Dec 2008 | Mar 2009 | Dec 2008 | Mar 2009
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200WCST | PPA-Wellhouse Public Rest Room Renovation - (B073-209M) | 4 | CONSTRUCTION | Mar 2009 | Mar 2010 | Mar 2009 | Mar 2010
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200WCST | PPA-Wellhouse Public Rest Room Renovation - (B073-209M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2010 | Mar 2011 | Mar 2010 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200WLCS | PPA - Willink Public Rest Room Children's Corner | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200WLCS | PPA - Willink Public Rest Room Children's Corner | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200WLCS | PPA - Willink Public Rest Room Children's Corner | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200WLCS | PPA - Willink Public Rest Room Children's Corner | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200WLCS | PPA - Willink Public Rest Room Children's Corner | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Jun 2028 | Sep 2025 | Jun 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO10 | Prospect Park Zoo - Renovation of Discovery Trail | 1 | DEVELOP SCOPE | Jul 2009 | Sep 2010 | Jul 2009 | Sep 2010
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO10 | Prospect Park Zoo - Renovation of Discovery Trail | 2 | DESIGN | Sep 2010 | Sep 2010 | Sep 2010 | Sep 2010
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO10 | Prospect Park Zoo - Renovation of Discovery Trail | 3 | BID/ REGISTER CONTRACT | Sep 2010 | Sep 2010 | Sep 2010 | Sep 2010
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO10 | Prospect Park Zoo - Renovation of Discovery Trail | 4 | CONSTRUCTION | Sep 2010 | Sep 2010 | Sep 2010 | Sep 2010
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO10 | Prospect Park Zoo - Renovation of Discovery Trail | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2010 | Sep 2011 | Sep 2010 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO17 | PPZ- Building "D" Dome Restoration | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO17 | PPZ- Building "D" Dome Restoration | 2 | DESIGN | Dec 2017 | Mar 2019 | Dec 2022 | Mar 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO17 | PPZ- Building "D" Dome Restoration | 3 | BID/ REGISTER CONTRACT | Mar 2019 | Dec 2019 | Mar 2024 | Dec 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO17 | PPZ- Building "D" Dome Restoration | 4 | CONSTRUCTION | Dec 2019 | Dec 2020 | Dec 2024 | Dec 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO17 | PPZ- Building "D" Dome Restoration | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2020 | Dec 2021 | Dec 2025 | Dec 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO18 | PPZ- Baboon night quarters/exhibit RC | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2021 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO18 | PPZ- Baboon night quarters/exhibit RC | 2 | DESIGN | Dec 2017 | Mar 2019 | Dec 2021 | Mar 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO18 | PPZ- Baboon night quarters/exhibit RC | 3 | BID/ REGISTER CONTRACT | Mar 2019 | Dec 2019 | Mar 2023 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO18 | PPZ- Baboon night quarters/exhibit RC | 4 | CONSTRUCTION | Dec 2019 | Dec 2020 | Dec 2023 | Dec 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO18 | PPZ- Baboon night quarters/exhibit RC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2020 | Dec 2021 | Dec 2024 | Jun 2033
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO19 | PPZ- Central plaza stairs,benches reconstruction | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2021 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO19 | PPZ- Central plaza stairs,benches reconstruction | 2 | DESIGN | Dec 2017 | Mar 2019 | Dec 2021 | Mar 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO19 | PPZ- Central plaza stairs,benches reconstruction | 3 | BID/ REGISTER CONTRACT | Mar 2019 | Dec 2019 | Mar 2023 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO19 | PPZ- Central plaza stairs,benches reconstruction | 4 | CONSTRUCTION | Dec 2019 | Dec 2020 | Dec 2023 | Dec 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO19 | PPZ- Central plaza stairs,benches reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2020 | Dec 2021 | Dec 2024 | Jun 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201245E | WNYC TRANSMITTER TOWERS EMERGENCY DEMOLITION, B385-102M | 1 | DEVELOP SCOPE | Jul 2006 | Sep 2006 | Jul 2006 | Sep 2006
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201245E | WNYC TRANSMITTER TOWERS EMERGENCY DEMOLITION, B385-102M | 2 | DESIGN | Sep 2006 | Dec 2006 | Sep 2006 | Dec 2006
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201245E | WNYC TRANSMITTER TOWERS EMERGENCY DEMOLITION, B385-102M | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Dec 2006 | Mar 2007
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201245E | WNYC TRANSMITTER TOWERS EMERGENCY DEMOLITION, B385-102M | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Mar 2007 | Mar 2008
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201245E | WNYC TRANSMITTER TOWERS EMERGENCY DEMOLITION, B385-102M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Mar 2008 | Mar 2009
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201DEHO | De Hostos Playground | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Sep 2018 | Mar 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201DEHO | De Hostos Playground | 2 | DESIGN | Dec 2021 | Dec 2022 | Mar 2019 | Mar 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201DEHO | De Hostos Playground | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Mar 2020 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201DEHO | De Hostos Playground | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Dec 2020 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201DEHO | De Hostos Playground | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Dec 2021 | Sep 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201EYCK | Ten Eyck Plaza Reconstruction B386-119M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201EYCK | Ten Eyck Plaza Reconstruction B386-119M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201EYCK | Ten Eyck Plaza Reconstruction B386-119M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201EYCK | Ten Eyck Plaza Reconstruction B386-119M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201EYCK | Ten Eyck Plaza Reconstruction B386-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201FROS | Frost Street Playground - Basketball Court Recon. B257-121M | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201FROS | Frost Street Playground - Basketball Court Recon. B257-121M | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201FROS | Frost Street Playground - Basketball Court Recon. B257-121M | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201FROS | Frost Street Playground - Basketball Court Recon. B257-121M | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201FROS | Frost Street Playground - Basketball Court Recon. B257-121M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCBH | McCarren -RC Bathhouse B058-117M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCBH | McCarren -RC Bathhouse B058-117M | 2 | DESIGN | Dec 2016 | Dec 2018 | Dec 2016 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCBH | McCarren -RC Bathhouse B058-117M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCBH | McCarren -RC Bathhouse B058-117M | 4 | CONSTRUCTION | Sep 2019 | Sep 2022 | Sep 2019 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCBH | McCarren -RC Bathhouse B058-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2024 | Sep 2022 | Sep 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCC2 | McCarren Park - Brooklyn | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCC2 | McCarren Park - Brooklyn | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCC2 | McCarren Park - Brooklyn | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCC2 | McCarren Park - Brooklyn | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCC2 | McCarren Park - Brooklyn | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCGK | McGolrick Park - Sidewalk Replacement | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCGK | McGolrick Park - Sidewalk Replacement | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCGK | McGolrick Park - Sidewalk Replacement | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCGK | McGolrick Park - Sidewalk Replacement | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCGK | McGolrick Park - Sidewalk Replacement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2019 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MDLT | Middleton Playground - Phase 1 Renovations B022-121M | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MDLT | Middleton Playground - Phase 1 Renovations B022-121M | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MDLT | Middleton Playground - Phase 1 Renovations B022-121M | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MDLT | Middleton Playground - Phase 1 Renovations B022-121M | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MDLT | Middleton Playground - Phase 1 Renovations B022-121M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MRCY | Marcy Green Park-Reconstruction of Rec. Facilities BG-120M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MRCY | Marcy Green Park-Reconstruction of Rec. Facilities BG-120M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MRCY | Marcy Green Park-Reconstruction of Rec. Facilities BG-120M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MRCY | Marcy Green Park-Reconstruction of Rec. Facilities BG-120M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MRCY | Marcy Green Park-Reconstruction of Rec. Facilities BG-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201P245 | GRAND FERRY PARK (PRIVATE $ CITYREQMTS) B401-104MA | 2 | DESIGN | Sep 2006 | Dec 2006 | Sep 2006 | Dec 2006
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201P245 | GRAND FERRY PARK (PRIVATE $ CITYREQMTS) B401-104MA | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Dec 2006 | Mar 2007
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201P245 | GRAND FERRY PARK (PRIVATE $ CITYREQMTS) B401-104MA | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Mar 2007 | Mar 2008
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201P245 | GRAND FERRY PARK (PRIVATE $ CITYREQMTS) B401-104MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Mar 2008 | Mar 2009
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201STRN | Sternberg Park Synthetic Turf Field Reconstruction B055-117M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201STRN | Sternberg Park Synthetic Turf Field Reconstruction B055-117M | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201STRN | Sternberg Park Synthetic Turf Field Reconstruction B055-117M | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201STRN | Sternberg Park Synthetic Turf Field Reconstruction B055-117M | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201STRN | Sternberg Park Synthetic Turf Field Reconstruction B055-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2019 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201TRNS | Transmitter Park - Shoreline Rehabilitation | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201TRNS | Transmitter Park - Shoreline Rehabilitation | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201TRNS | Transmitter Park - Shoreline Rehabilitation | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201TRNS | Transmitter Park - Shoreline Rehabilitation | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201TRNS | Transmitter Park - Shoreline Rehabilitation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201WILL | William Sheridan Playground B124-119M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201WILL | William Sheridan Playground B124-119M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201WILL | William Sheridan Playground B124-119M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201WILL | William Sheridan Playground B124-119M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201WILL | William Sheridan Playground B124-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202018A | Brooklyn Bridge Park BG-38150-104M | 1 | DEVELOP SCOPE | Oct 2003 | Jan 2004 | Oct 2003 | Jan 2004
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202018A | Brooklyn Bridge Park BG-38150-104M | 2 | DESIGN | Jan 2004 | Mar 2004 | Jan 2004 | Mar 2004
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202018A | Brooklyn Bridge Park BG-38150-104M | 3 | BID/ REGISTER CONTRACT | Apr 2004 | Jun 2004 | Apr 2004 | Jun 2004
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202018A | Brooklyn Bridge Park BG-38150-104M | 4 | CONSTRUCTION | Jul 2004 | Sep 2005 | Jul 2004 | Sep 2005
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202018A | Brooklyn Bridge Park BG-38150-104M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2005 | Sep 2006 | Oct 2005 | Jun 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202BRDG | Susan Smith McKinney Steward Park Reconstruction B223-118MA | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202BRDG | Susan Smith McKinney Steward Park Reconstruction B223-118MA | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202BRDG | Susan Smith McKinney Steward Park Reconstruction B223-118MA | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202BRDG | Susan Smith McKinney Steward Park Reconstruction B223-118MA | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202BRDG | Susan Smith McKinney Steward Park Reconstruction B223-118MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2019 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202C974 | FORT GREENE PK PRISONSH MARTYRS MONU&BR EAGL B32-103MA,203MA | 1 | DEVELOP SCOPE | Jul 2002 | Mar 2003 | Jul 2002 | Mar 2003
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202C974 | FORT GREENE PK PRISONSH MARTYRS MONU&BR EAGL B32-103MA,203MA | 2 | DESIGN | Mar 2003 | Mar 2004 | Mar 2003 | Jan 2005
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202C974 | FORT GREENE PK PRISONSH MARTYRS MONU&BR EAGL B32-103MA,203MA | 3 | BID/ REGISTER CONTRACT | Apr 2004 | Jun 2004 | Mar 2005 | Oct 2005
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202C974 | FORT GREENE PK PRISONSH MARTYRS MONU&BR EAGL B32-103MA,203MA | 4 | CONSTRUCTION | Jul 2004 | Dec 2005 | Mar 2006 | Oct 2007
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202C974 | FORT GREENE PK PRISONSH MARTYRS MONU&BR EAGL B32-103MA,203MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2005 | Dec 2006 | Oct 2007 | Jun 2033
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CAD2 | Cadman Plaza Park - Brooklyn (B113A-119M) | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CAD2 | Cadman Plaza Park - Brooklyn (B113A-119M) | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CAD2 | Cadman Plaza Park - Brooklyn (B113A-119M) | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CAD2 | Cadman Plaza Park - Brooklyn (B113A-119M) | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CAD2 | Cadman Plaza Park - Brooklyn (B113A-119M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CADM | CADMAN PLAZA (RC L/S SURROND BKLN WAR MEM. BLDG ACCESS) | 1 | DEVELOP SCOPE | Jul 2011 | Sep 2011 | Jul 2011 | Sep 2011
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CADM | CADMAN PLAZA (RC L/S SURROND BKLN WAR MEM. BLDG ACCESS) | 2 | DESIGN | Sep 2011 | Dec 2011 | Sep 2011 | Dec 2011
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CADM | CADMAN PLAZA (RC L/S SURROND BKLN WAR MEM. BLDG ACCESS) | 3 | BID/ REGISTER CONTRACT | Dec 2011 | Mar 2012 | Dec 2011 | Mar 2012
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CADM | CADMAN PLAZA (RC L/S SURROND BKLN WAR MEM. BLDG ACCESS) | 4 | CONSTRUCTION | Mar 2012 | Mar 2013 | Mar 2012 | Mar 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CADM | CADMAN PLAZA (RC L/S SURROND BKLN WAR MEM. BLDG ACCESS) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2013 | Mar 2014 | Mar 2013 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CBMP | Commodore Barry Pk - RC of Multi Purpose Area B021-123M | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CBMP | Commodore Barry Pk - RC of Multi Purpose Area B021-123M | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CBMP | Commodore Barry Pk - RC of Multi Purpose Area B021-123M | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CBMP | Commodore Barry Pk - RC of Multi Purpose Area B021-123M | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CBMP | Commodore Barry Pk - RC of Multi Purpose Area B021-123M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Jun 2028 | Sep 2025 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CBPK | COMMODORE BARRY PARK (B021-119M) | 1 | DEVELOP SCOPE | Jul 2012 | Sep 2012 | Jul 2012 | Dec 2012
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CBPK | COMMODORE BARRY PARK (B021-119M) | 2 | DESIGN | Sep 2012 | Dec 2012 | Dec 2012 | Dec 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CBPK | COMMODORE BARRY PARK (B021-119M) | 3 | BID/ REGISTER CONTRACT | Dec 2012 | Mar 2013 | Dec 2013 | Sep 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CBPK | COMMODORE BARRY PARK (B021-119M) | 4 | CONSTRUCTION | Mar 2013 | Mar 2014 | Sep 2014 | Sep 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CBPK | COMMODORE BARRY PARK (B021-119M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2014 | Mar 2015 | Sep 2015 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CHAP | CHAPIN PLAYGROUND -RECON. SPRINKLER BG-311M | 1 | DEVELOP SCOPE | Jul 2012 | Sep 2012 | Jul 2012 | Sep 2012
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CHAP | CHAPIN PLAYGROUND -RECON. SPRINKLER BG-311M | 2 | DESIGN | Sep 2012 | Dec 2012 | Sep 2012 | Dec 2012
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CHAP | CHAPIN PLAYGROUND -RECON. SPRINKLER BG-311M | 3 | BID/ REGISTER CONTRACT | Dec 2012 | Mar 2013 | Dec 2012 | Mar 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CHAP | CHAPIN PLAYGROUND -RECON. SPRINKLER BG-311M | 4 | CONSTRUCTION | Mar 2013 | Mar 2014 | Mar 2013 | Mar 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CHAP | CHAPIN PLAYGROUND -RECON. SPRINKLER BG-311M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2014 | Mar 2015 | Mar 2014 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CPST | Cadman Plaza Turf -- To replace the turf at Cadman Plaza. | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CPST | Cadman Plaza Turf -- To replace the turf at Cadman Plaza. | 2 | DESIGN | Dec 2022 | Jun 2024 | Dec 2022 | Jun 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CPST | Cadman Plaza Turf -- To replace the turf at Cadman Plaza. | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CPST | Cadman Plaza Turf -- To replace the turf at Cadman Plaza. | 4 | CONSTRUCTION | Mar 2025 | Sep 2026 | Mar 2025 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CPST | Cadman Plaza Turf -- To replace the turf at Cadman Plaza. | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CUGP | Cuyler Gore Park Renovations B026-121M | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CUGP | Cuyler Gore Park Renovations B026-121M | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CUGP | Cuyler Gore Park Renovations B026-121M | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CUGP | Cuyler Gore Park Renovations B026-121M | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CUGP | Cuyler Gore Park Renovations B026-121M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202FTGN | Fort Grene Park - entrance & pass (B032-110M) | 1 | DEVELOP SCOPE | Jul 2007 | Sep 2007 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202FTGN | Fort Grene Park - entrance & pass (B032-110M) | 2 | DESIGN | Sep 2007 | Dec 2007 | Jan 2006 | Apr 2006
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202FTGN | Fort Grene Park - entrance & pass (B032-110M) | 3 | BID/ REGISTER CONTRACT | Dec 2007 | Mar 2008 | May 2006 | Jul 2006
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202FTGN | Fort Grene Park - entrance & pass (B032-110M) | 4 | CONSTRUCTION | Mar 2008 | Mar 2009 | Jul 2006 | Jul 2007
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202FTGN | Fort Grene Park - entrance & pass (B032-110M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2009 | Mar 2010 | Jul 2007 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202GRPL | Greene Playground - Reconstruction of Playground B301-121M | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202GRPL | Greene Playground - Reconstruction of Playground B301-121M | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202GRPL | Greene Playground - Reconstruction of Playground B301-121M | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202GRPL | Greene Playground - Reconstruction of Playground B301-121M | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202GRPL | Greene Playground - Reconstruction of Playground B301-121M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202K11F | Crispus Attucks Plg Public Rest Room Reconst; B102-104M-404M | 1 | DEVELOP SCOPE | Jul 2003 | Sep 2003 | Jul 2003 | Sep 2003
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202K11F | Crispus Attucks Plg Public Rest Room Reconst; B102-104M-404M | 2 | DESIGN | Sep 2003 | Dec 2003 | Sep 2003 | Jun 2004
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202K11F | Crispus Attucks Plg Public Rest Room Reconst; B102-104M-404M | 3 | BID/ REGISTER CONTRACT | Jan 2004 | Apr 2004 | Jun 2004 | Dec 2004
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202K11F | Crispus Attucks Plg Public Rest Room Reconst; B102-104M-404M | 4 | CONSTRUCTION | Jun 2004 | Mar 2005 | Jan 2005 | Sep 2006
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202K11F | Crispus Attucks Plg Public Rest Room Reconst; B102-104M-404M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2005 | Apr 2006 | Sep 2006 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202OPGR | Oracle Playground Renovation B300-123M | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202OPGR | Oracle Playground Renovation B300-123M | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202OPGR | Oracle Playground Renovation B300-123M | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202OPGR | Oracle Playground Renovation B300-123M | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202OPGR | Oracle Playground Renovation B300-123M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202WASH | Washington Hall Plgd. Basketball Courts Recon. B220-119M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202WASH | Washington Hall Plgd. Basketball Courts Recon. B220-119M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202WASH | Washington Hall Plgd. Basketball Courts Recon. B220-119M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202WASH | Washington Hall Plgd. Basketball Courts Recon. B220-119M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202WASH | Washington Hall Plgd. Basketball Courts Recon. B220-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202WPDR | Washington Park Dog Run B111-118M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202WPDR | Washington Park Dog Run B111-118M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202WPDR | Washington Park Dog Run B111-118M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202WPDR | Washington Park Dog Run B111-118M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202WPDR | Washington Park Dog Run B111-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203CHPL | Charlie's Place - Asphalt Field to Synthetic Turf | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203CHPL | Charlie's Place - Asphalt Field to Synthetic Turf | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203CHPL | Charlie's Place - Asphalt Field to Synthetic Turf | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203CHPL | Charlie's Place - Asphalt Field to Synthetic Turf | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203CHPL | Charlie's Place - Asphalt Field to Synthetic Turf | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203CHRL | Charlie's Place Reconstruction B302-119M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203CHRL | Charlie's Place Reconstruction B302-119M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203CHRL | Charlie's Place Reconstruction B302-119M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203CHRL | Charlie's Place Reconstruction B302-119M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203CHRL | Charlie's Place Reconstruction B302-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203D17E | Von King Cultural Arts Center - Phase 3 B088-111MA | 1 | DEVELOP SCOPE | Jul 2006 | Sep 2006 | May 2011 | Jun 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203D17E | Von King Cultural Arts Center - Phase 3 B088-111MA | 2 | DESIGN | Sep 2006 | Dec 2006 | May 2011 | Jan 2012
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203D17E | Von King Cultural Arts Center - Phase 3 B088-111MA | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Jun 2012 | Sep 2012
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203D17E | Von King Cultural Arts Center - Phase 3 B088-111MA | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Dec 2012 | Dec 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203D17E | Von King Cultural Arts Center - Phase 3 B088-111MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Jul 2013 | Jun 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203FULT | FULTON PARK - RESTORATION OF PRB B038-116M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Oct 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203FULT | FULTON PARK - RESTORATION OF PRB B038-116M | 2 | DESIGN | Sep 2013 | Dec 2013 | Oct 2015 | Dec 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203FULT | FULTON PARK - RESTORATION OF PRB B038-116M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Jan 2016 | Mar 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203FULT | FULTON PARK - RESTORATION OF PRB B038-116M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2016 | Mar 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203FULT | FULTON PARK - RESTORATION OF PRB B038-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2017 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203HPUP | Harmony Park - Upgrades and Beautification | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2024 | Dec 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203HPUP | Harmony Park - Upgrades and Beautification | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2024 | Dec 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203HPUP | Harmony Park - Upgrades and Beautification | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2025 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203HPUP | Harmony Park - Upgrades and Beautification | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2026 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203HPUP | Harmony Park - Upgrades and Beautification | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2027 | Sep 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203HVKP | Herbert Von King Park dog run renovations | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203HVKP | Herbert Von King Park dog run renovations | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203HVKP | Herbert Von King Park dog run renovations | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203HVKP | Herbert Von King Park dog run renovations | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203HVKP | Herbert Von King Park dog run renovations | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203LFGP | Lafayette Gardens Playground Reconstruction | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203LFGP | Lafayette Gardens Playground Reconstruction | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203LFGP | Lafayette Gardens Playground Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203LFGP | Lafayette Gardens Playground Reconstruction | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203LFGP | Lafayette Gardens Playground Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203SBIP | Bedstuy Initiative - Park upgrades across bedstuy community | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203SBIP | Bedstuy Initiative - Park upgrades across bedstuy community | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203SBIP | Bedstuy Initiative - Park upgrades across bedstuy community | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203SBIP | Bedstuy Initiative - Park upgrades across bedstuy community | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203SBIP | Bedstuy Initiative - Park upgrades across bedstuy community | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203SRTG | Saratoga Park - Playground Reconstruction (B079-119M) | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203SRTG | Saratoga Park - Playground Reconstruction (B079-119M) | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203SRTG | Saratoga Park - Playground Reconstruction (B079-119M) | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203SRTG | Saratoga Park - Playground Reconstruction (B079-119M) | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203SRTG | Saratoga Park - Playground Reconstruction (B079-119M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204ELGD | EL GARDEN--IMPROVEMENTS | 1 | DEVELOP SCOPE | Sep 2023 | Mar 2024 | Sep 2023 | Mar 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204ELGD | EL GARDEN--IMPROVEMENTS | 2 | DESIGN | Mar 2024 | Mar 2025 | Mar 2024 | Mar 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204ELGD | EL GARDEN--IMPROVEMENTS | 3 | BID/ REGISTER CONTRACT | Mar 2025 | Dec 2025 | Mar 2025 | Dec 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204ELGD | EL GARDEN--IMPROVEMENTS | 4 | CONSTRUCTION | Dec 2025 | Dec 2026 | Dec 2025 | Dec 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204ELGD | EL GARDEN--IMPROVEMENTS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2026 | Dec 2027 | Dec 2026 | Dec 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204GRCK | Green Central Knoll - PRB B395-115M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204GRCK | Green Central Knoll - PRB B395-115M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204GRCK | Green Central Knoll - PRB B395-115M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204GRCK | Green Central Knoll - PRB B395-115M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204GRCK | Green Central Knoll - PRB B395-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204ISPD | Irving Square Park Dog Run | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204ISPD | Irving Square Park Dog Run | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204ISPD | Irving Square Park Dog Run | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204ISPD | Irving Square Park Dog Run | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204ISPD | Irving Square Park Dog Run | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204MHPG | Maria Hernandez Park - Playground RC B016-123M | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204MHPG | Maria Hernandez Park - Playground RC B016-123M | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204MHPG | Maria Hernandez Park - Playground RC B016-123M | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204MHPG | Maria Hernandez Park - Playground RC B016-123M | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204MHPG | Maria Hernandez Park - Playground RC B016-123M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205CYPS | Cypress Park - Renovation of Cypress Park B103-116M | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Sep 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205CYPS | Cypress Park - Renovation of Cypress Park B103-116M | 2 | DESIGN | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205CYPS | Cypress Park - Renovation of Cypress Park B103-116M | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2014 | Mar 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205CYPS | Cypress Park - Renovation of Cypress Park B103-116M | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205CYPS | Cypress Park - Renovation of Cypress Park B103-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2016 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205GRP2 | Grace Playground Ph. 2 B078-123M | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205GRP2 | Grace Playground Ph. 2 B078-123M | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205GRP2 | Grace Playground Ph. 2 B078-123M | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205GRP2 | Grace Playground Ph. 2 B078-123M | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205GRP2 | Grace Playground Ph. 2 B078-123M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205GRPG | Grace Playground Park Renovation Phase I B078-119M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205GRPG | Grace Playground Park Renovation Phase I B078-119M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205GRPG | Grace Playground Park Renovation Phase I B078-119M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205GRPG | Grace Playground Park Renovation Phase I B078-119M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205GRPG | Grace Playground Park Renovation Phase I B078-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205HPSB | Highland Park Stone Bridge Q020-418M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205HPSB | Highland Park Stone Bridge Q020-418M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205HPSB | Highland Park Stone Bridge Q020-418M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205HPSB | Highland Park Stone Bridge Q020-418M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205HPSB | Highland Park Stone Bridge Q020-418M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LIN1 | Linden Park:Phase 4-Playground,Spray Shower & Basketball crt | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LIN1 | Linden Park:Phase 4-Playground,Spray Shower & Basketball crt | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LIN1 | Linden Park:Phase 4-Playground,Spray Shower & Basketball crt | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LIN1 | Linden Park:Phase 4-Playground,Spray Shower & Basketball crt | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LIN1 | Linden Park:Phase 4-Playground,Spray Shower & Basketball crt | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LIN2 | Linden Park: Phase 5 Area Renovation | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LIN2 | Linden Park: Phase 5 Area Renovation | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LIN2 | Linden Park: Phase 5 Area Renovation | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LIN2 | Linden Park: Phase 5 Area Renovation | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LIN2 | Linden Park: Phase 5 Area Renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LION | Lion's Pride Playground - B107-119M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LION | Lion's Pride Playground - B107-119M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LION | Lion's Pride Playground - B107-119M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LION | Lion's Pride Playground - B107-119M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LION | Lion's Pride Playground - B107-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205PPMT | Public Place - Monument Reconstruction | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205PPMT | Public Place - Monument Reconstruction | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205PPMT | Public Place - Monument Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205PPMT | Public Place - Monument Reconstruction | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205PPMT | Public Place - Monument Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205SHNK | Sankofa Park RC B261-120M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205SHNK | Sankofa Park RC B261-120M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205SHNK | Sankofa Park RC B261-120M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205SHNK | Sankofa Park RC B261-120M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205SHNK | Sankofa Park RC B261-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Mar 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206GDAM | Grand Army Plaza Arch Restoration B040-119M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206GDAM | Grand Army Plaza Arch Restoration B040-119M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206GDAM | Grand Army Plaza Arch Restoration B040-119M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206GDAM | Grand Army Plaza Arch Restoration B040-119M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206GDAM | Grand Army Plaza Arch Restoration B040-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206GDAS | Grand Army Plaza - Site Restoration B040-120M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206GDAS | Grand Army Plaza - Site Restoration B040-120M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206GDAS | Grand Army Plaza - Site Restoration B040-120M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206GDAS | Grand Army Plaza - Site Restoration B040-120M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206GDAS | Grand Army Plaza - Site Restoration B040-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206ICKE | Harold Ickes Playground PH 1 B210H-118M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206ICKE | Harold Ickes Playground PH 1 B210H-118M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206ICKE | Harold Ickes Playground PH 1 B210H-118M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206ICKE | Harold Ickes Playground PH 1 B210H-118M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206ICKE | Harold Ickes Playground PH 1 B210H-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RH02 | Red Hook - Oversight 9 | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Jun 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RH02 | Red Hook - Oversight 9 | 2 | DESIGN | Dec 2016 | Jun 2018 | Jul 2017 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RH02 | Red Hook - Oversight 9 | 3 | BID/ REGISTER CONTRACT | Jun 2018 | Mar 2019 | Dec 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RH02 | Red Hook - Oversight 9 | 4 | CONSTRUCTION | Mar 2019 | Sep 2020 | Sep 2019 | Mar 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RH02 | Red Hook - Oversight 9 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Mar 2021 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHBF | Red Hook - Ball field 9/Soccer 2 (B126-117M) | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHBF | Red Hook - Ball field 9/Soccer 2 (B126-117M) | 2 | DESIGN | Dec 2016 | Jun 2018 | Jan 2017 | Jun 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHBF | Red Hook - Ball field 9/Soccer 2 (B126-117M) | 3 | BID/ REGISTER CONTRACT | Jun 2018 | Mar 2019 | Jun 2018 | Mar 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHBF | Red Hook - Ball field 9/Soccer 2 (B126-117M) | 4 | CONSTRUCTION | Mar 2019 | Sep 2020 | Mar 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHBF | Red Hook - Ball field 9/Soccer 2 (B126-117M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jul 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHBH | Red Hook Bulkhead B126-123M | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHBH | Red Hook Bulkhead B126-123M | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHBH | Red Hook Bulkhead B126-123M | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHBH | Red Hook Bulkhead B126-123M | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHBH | Red Hook Bulkhead B126-123M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Jun 2029 | Sep 2025 | Jun 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHBS | Red Hook Track 1/Soccer 3 & Ballfields 1-4 (B126-118M) | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHBS | Red Hook Track 1/Soccer 3 & Ballfields 1-4 (B126-118M) | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHBS | Red Hook Track 1/Soccer 3 & Ballfields 1-4 (B126-118M) | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHBS | Red Hook Track 1/Soccer 3 & Ballfields 1-4 (B126-118M) | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHBS | Red Hook Track 1/Soccer 3 & Ballfields 1-4 (B126-118M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2019 | Jun 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHCF | Red Hook - Community Farm Upgrades (B126-220M) | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHCF | Red Hook - Community Farm Upgrades (B126-220M) | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHCF | Red Hook - Community Farm Upgrades (B126-220M) | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHCF | Red Hook - Community Farm Upgrades (B126-220M) | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHCF | Red Hook - Community Farm Upgrades (B126-220M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHO1 | Red Hook- EPA Oversight 5-8 | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHO1 | Red Hook- EPA Oversight 5-8 | 2 | DESIGN | Dec 2016 | Jun 2018 | Dec 2016 | Jun 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHO1 | Red Hook- EPA Oversight 5-8 | 3 | BID/ REGISTER CONTRACT | Jun 2018 | Mar 2019 | Jun 2018 | Mar 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHO1 | Red Hook- EPA Oversight 5-8 | 4 | CONSTRUCTION | Mar 2019 | Sep 2020 | Mar 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHO1 | Red Hook- EPA Oversight 5-8 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHRC | Red Hook Recreation Center Reconstruction | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHRC | Red Hook Recreation Center Reconstruction | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHRC | Red Hook Recreation Center Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHRC | Red Hook Recreation Center Reconstruction | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHRC | Red Hook Recreation Center Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHSF | Red Hook - Soccer 1 & 6 B126-119M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHSF | Red Hook - Soccer 1 & 6 B126-119M | 2 | DESIGN | Dec 2016 | Jun 2018 | Dec 2016 | Jun 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHSF | Red Hook - Soccer 1 & 6 B126-119M | 3 | BID/ REGISTER CONTRACT | Jun 2018 | Mar 2019 | Jun 2018 | Mar 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHSF | Red Hook - Soccer 1 & 6 B126-119M | 4 | CONSTRUCTION | Mar 2019 | Sep 2020 | Mar 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHSF | Red Hook - Soccer 1 & 6 B126-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206SMRY | St. Mary's Playground (B118-116M) | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206SMRY | St. Mary's Playground (B118-116M) | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206SMRY | St. Mary's Playground (B118-116M) | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206SMRY | St. Mary's Playground (B118-116M) | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206SMRY | St. Mary's Playground (B118-116M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Jul 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207GWHB | Greenwood Playground - Handball Courts RC B130-123M | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207GWHB | Greenwood Playground - Handball Courts RC B130-123M | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207GWHB | Greenwood Playground - Handball Courts RC B130-123M | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207GWHB | Greenwood Playground - Handball Courts RC B130-123M | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207GWHB | Greenwood Playground - Handball Courts RC B130-123M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207OPML | Ocean Parkway Malls - RC B065-119M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207OPML | Ocean Parkway Malls - RC B065-119M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207OPML | Ocean Parkway Malls - RC B065-119M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207OPML | Ocean Parkway Malls - RC B065-119M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207OPML | Ocean Parkway Malls - RC B065-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207RAIN | Rainbow Playground - Playground Update B265-120M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207RAIN | Rainbow Playground - Playground Update B265-120M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207RAIN | Rainbow Playground - Playground Update B265-120M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207RAIN | Rainbow Playground - Playground Update B265-120M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207RAIN | Rainbow Playground - Playground Update B265-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SNST | Sunset Park - Benches -B087-116M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SNST | Sunset Park - Benches -B087-116M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SNST | Sunset Park - Benches -B087-116M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SNST | Sunset Park - Benches -B087-116M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SNST | Sunset Park - Benches -B087-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SPHD | HANDBALL COURT RENOVATIONS AT SUNSET PARK (B087-119M) | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SPHD | HANDBALL COURT RENOVATIONS AT SUNSET PARK (B087-119M) | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SPHD | HANDBALL COURT RENOVATIONS AT SUNSET PARK (B087-119M) | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SPHD | HANDBALL COURT RENOVATIONS AT SUNSET PARK (B087-119M) | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SPHD | HANDBALL COURT RENOVATIONS AT SUNSET PARK (B087-119M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SPOS | Sunset Park - Open Stage Creation | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2025 | Dec 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SPOS | Sunset Park - Open Stage Creation | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2025 | Dec 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SPOS | Sunset Park - Open Stage Creation | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2026 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SPOS | Sunset Park - Open Stage Creation | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2027 | Sep 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SPOS | Sunset Park - Open Stage Creation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2028 | Sep 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SSPK | Sunset Park - Renovation - B087-117MA | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SSPK | Sunset Park - Renovation - B087-117MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SUNS | SUNSET PARK PLAYGROUND RC B087-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2013 | Mar 2014 | Aug 2017 | Jul 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208BROW | Brower Park - Reconstruction of basketball courts -B012-117M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208BROW | Brower Park - Reconstruction of basketball courts -B012-117M | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208BROW | Brower Park - Reconstruction of basketball courts -B012-117M | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208BROW | Brower Park - Reconstruction of basketball courts -B012-117M | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208BROW | Brower Park - Reconstruction of basketball courts -B012-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2019 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208HVAC | ST. JOHNS HVAC UPGRADE-B245-114M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208HVAC | ST. JOHNS HVAC UPGRADE-B245-114M | 2 | DESIGN | Sep 2013 | Dec 2013 | Jul 2030 | May 2031
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208HVAC | ST. JOHNS HVAC UPGRADE-B245-114M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Jun 2031 | Aug 2031
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208HVAC | ST. JOHNS HVAC UPGRADE-B245-114M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Dec 2016 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208HVAC | ST. JOHNS HVAC UPGRADE-B245-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Dec 2017 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208K11A | ST. MARK'S AVE. STREETBED PARK RECONSTR; BG-38050-199 | 1 | DEVELOP SCOPE | Jul 2006 | Sep 2006 | Jul 2006 | Sep 2006
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208K11A | ST. MARK'S AVE. STREETBED PARK RECONSTR; BG-38050-199 | 2 | DESIGN | Sep 2006 | Dec 2006 | Sep 2006 | Dec 2006
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208K11A | ST. MARK'S AVE. STREETBED PARK RECONSTR; BG-38050-199 | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Dec 2006 | Mar 2007
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208K11A | ST. MARK'S AVE. STREETBED PARK RECONSTR; BG-38050-199 | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Mar 2007 | Mar 2008
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208K11A | ST. MARK'S AVE. STREETBED PARK RECONSTR; BG-38050-199 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Mar 2008 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208K11E | St. John's Recreation Center - PRB (B245-111M) | 1 | DEVELOP SCOPE | Jul 2009 | Sep 2009 | Jul 2009 | Sep 2009
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208K11E | St. John's Recreation Center - PRB (B245-111M) | 2 | DESIGN | Sep 2009 | Dec 2009 | Nov 2012 | Feb 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208K11E | St. John's Recreation Center - PRB (B245-111M) | 3 | BID/ REGISTER CONTRACT | Dec 2009 | Mar 2010 | Mar 2013 | Sep 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208K11E | St. John's Recreation Center - PRB (B245-111M) | 4 | CONSTRUCTION | Mar 2010 | Mar 2011 | Sep 2013 | Sep 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208K11E | St. John's Recreation Center - PRB (B245-111M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2011 | Mar 2012 | Sep 2013 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208LIN2 | Lincoln Terrace Park - Brooklyn (B054-119M) | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208LIN2 | Lincoln Terrace Park - Brooklyn (B054-119M) | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208LIN2 | Lincoln Terrace Park - Brooklyn (B054-119M) | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208LIN2 | Lincoln Terrace Park - Brooklyn (B054-119M) | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208LIN2 | Lincoln Terrace Park - Brooklyn (B054-119M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208LTCS | Lincoln Terrace- Field House Construction B054-115M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208LTCS | Lincoln Terrace- Field House Construction B054-115M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208LTCS | Lincoln Terrace- Field House Construction B054-115M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208LTCS | Lincoln Terrace- Field House Construction B054-115M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208LTCS | Lincoln Terrace- Field House Construction B054-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208SJFA | ST. John's Rec. Center: Fire Alarm Reconstruction | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208SJFA | ST. John's Rec. Center: Fire Alarm Reconstruction | 2 | DESIGN | Dec 2019 | Dec 2021 | Dec 2019 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208SJFA | ST. John's Rec. Center: Fire Alarm Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208SJFA | ST. John's Rec. Center: Fire Alarm Reconstruction | 4 | CONSTRUCTION | Sep 2022 | Sep 2025 | Sep 2022 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208SJFA | ST. John's Rec. Center: Fire Alarm Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208STFE | ST. JOHNS REC CENTER - OUTDOOR FITNESS EQUIPMENT (B245-118M) | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208STFE | ST. JOHNS REC CENTER - OUTDOOR FITNESS EQUIPMENT (B245-118M) | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208STFE | ST. JOHNS REC CENTER - OUTDOOR FITNESS EQUIPMENT (B245-118M) | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208STFE | ST. JOHNS REC CENTER - OUTDOOR FITNESS EQUIPMENT (B245-118M) | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208STFE | ST. JOHNS REC CENTER - OUTDOOR FITNESS EQUIPMENT (B245-118M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209MSGT | GreenThumb Comm Garden Maple Street Garden -- Water line | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209MSGT | GreenThumb Comm Garden Maple Street Garden -- Water line | 2 | DESIGN | Dec 2022 | Jun 2024 | Dec 2022 | Jun 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209MSGT | GreenThumb Comm Garden Maple Street Garden -- Water line | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209MSGT | GreenThumb Comm Garden Maple Street Garden -- Water line | 4 | CONSTRUCTION | Mar 2025 | Sep 2026 | Mar 2025 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209MSGT | GreenThumb Comm Garden Maple Street Garden -- Water line | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209MTPP | Mount Prospect Park Improvements | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209MTPP | Mount Prospect Park Improvements | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209MTPP | Mount Prospect Park Improvements | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209MTPP | Mount Prospect Park Improvements | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209MTPP | Mount Prospect Park Improvements | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209WGTF | Wingate Park - Recon. of Track, Grass Field | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209WGTF | Wingate Park - Recon. of Track, Grass Field | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209WGTF | Wingate Park - Recon. of Track, Grass Field | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209WGTF | Wingate Park - Recon. of Track, Grass Field | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209WGTF | Wingate Park - Recon. of Track, Grass Field | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Jun 2027 | Sep 2025 | Jun 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209WNGE | Wingate Park Basketball Courts Reconstruction B254-117M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209WNGE | Wingate Park Basketball Courts Reconstruction B254-117M | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209WNGE | Wingate Park Basketball Courts Reconstruction B254-117M | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209WNGE | Wingate Park Basketball Courts Reconstruction B254-117M | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209WNGE | Wingate Park Basketball Courts Reconstruction B254-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2019 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210245A | OWL'S HEAD PK - GREENWAY CONNECTOR B066-108M | 1 | DEVELOP SCOPE | Jul 2007 | Sep 2007 | Jul 2007 | Oct 2007
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210245A | OWL'S HEAD PK - GREENWAY CONNECTOR B066-108M | 2 | DESIGN | Sep 2007 | Dec 2007 | Oct 2007 | Oct 2008
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210245A | OWL'S HEAD PK - GREENWAY CONNECTOR B066-108M | 3 | BID/ REGISTER CONTRACT | Dec 2007 | Mar 2008 | Mar 2009 | Jul 2009
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210245A | OWL'S HEAD PK - GREENWAY CONNECTOR B066-108M | 4 | CONSTRUCTION | Mar 2008 | Mar 2009 | Mar 2010 | Dec 2010
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210245A | OWL'S HEAD PK - GREENWAY CONNECTOR B066-108M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2009 | Mar 2010 | Dec 2010 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210DBDM | Dyker Beach Park Bleachers | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210DBDM | Dyker Beach Park Bleachers | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210DBDM | Dyker Beach Park Bleachers | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210DBDM | Dyker Beach Park Bleachers | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210DBDM | Dyker Beach Park Bleachers | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210DBPP | Dyker Beach Park Improvements -- Dyker Beach Park at Bay 8th | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210DBPP | Dyker Beach Park Improvements -- Dyker Beach Park at Bay 8th | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210DBPP | Dyker Beach Park Improvements -- Dyker Beach Park at Bay 8th | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210DBPP | Dyker Beach Park Improvements -- Dyker Beach Park at Bay 8th | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210DBPP | Dyker Beach Park Improvements -- Dyker Beach Park at Bay 8th | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210DOG | Shore Park and Parkway Dog Run Construction B082-120M | 1 | DEVELOP SCOPE | Sep 2019 | Mar 2020 | Sep 2019 | Mar 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210DOG | Shore Park and Parkway Dog Run Construction B082-120M | 2 | DESIGN | Mar 2020 | Mar 2021 | Mar 2020 | Mar 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210DOG | Shore Park and Parkway Dog Run Construction B082-120M | 3 | BID/ REGISTER CONTRACT | Mar 2021 | Dec 2021 | Mar 2021 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210DOG | Shore Park and Parkway Dog Run Construction B082-120M | 4 | CONSTRUCTION | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210DOG | Shore Park and Parkway Dog Run Construction B082-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2022 | Dec 2023 | Dec 2022 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210JJCP | JJ Carty Park - Renovation of Playground | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210JJCP | JJ Carty Park - Renovation of Playground | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210JJCP | JJ Carty Park - Renovation of Playground | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210JJCP | JJ Carty Park - Renovation of Playground | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210JJCP | JJ Carty Park - Renovation of Playground | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2025 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210JPPT | JOHN PAUL JONES PARK PATHS AND BENCHES--RECONSTRUCTION | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210JPPT | JOHN PAUL JONES PARK PATHS AND BENCHES--RECONSTRUCTION | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210JPPT | JOHN PAUL JONES PARK PATHS AND BENCHES--RECONSTRUCTION | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210JPPT | JOHN PAUL JONES PARK PATHS AND BENCHES--RECONSTRUCTION | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210JPPT | JOHN PAUL JONES PARK PATHS AND BENCHES--RECONSTRUCTION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210MCKP | McKinley Park Playground Reconstruction (B060-122M) | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210MCKP | McKinley Park Playground Reconstruction (B060-122M) | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210MCKP | McKinley Park Playground Reconstruction (B060-122M) | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210MCKP | McKinley Park Playground Reconstruction (B060-122M) | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210MCKP | McKinley Park Playground Reconstruction (B060-122M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210MPTC | Mckinley Park Tennis Courts | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210MPTC | Mckinley Park Tennis Courts | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210MPTC | Mckinley Park Tennis Courts | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210MPTC | Mckinley Park Tennis Courts | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210MPTC | Mckinley Park Tennis Courts | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210OWLH | Owl's Head Park - Recon. of Basketball Courts B066-121M | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210OWLH | Owl's Head Park - Recon. of Basketball Courts B066-121M | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210OWLH | Owl's Head Park - Recon. of Basketball Courts B066-121M | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210OWLH | Owl's Head Park - Recon. of Basketball Courts B066-121M | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210OWLH | Owl's Head Park - Recon. of Basketball Courts B066-121M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210OWLR | Owl's Head Park - Reconstruction of Retaining Walls & Paths | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210OWLR | Owl's Head Park - Reconstruction of Retaining Walls & Paths | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210OWLR | Owl's Head Park - Reconstruction of Retaining Walls & Paths | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210OWLR | Owl's Head Park - Reconstruction of Retaining Walls & Paths | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210OWLR | Owl's Head Park - Reconstruction of Retaining Walls & Paths | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210RPPI | Russell Pedersen Playground Improvments | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210RPPI | Russell Pedersen Playground Improvments | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210RPPI | Russell Pedersen Playground Improvments | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210RPPI | Russell Pedersen Playground Improvments | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210RPPI | Russell Pedersen Playground Improvments | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210RUPP | Russell Pedersen Playground Reconstruction | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210RUPP | Russell Pedersen Playground Reconstruction | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210RUPP | Russell Pedersen Playground Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210RUPP | Russell Pedersen Playground Reconstruction | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210RUPP | Russell Pedersen Playground Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHCP | Shore Road Park - Path Reconstruction (B082-220M) | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2023 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHCP | Shore Road Park - Path Reconstruction (B082-220M) | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2023 | Dec 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHCP | Shore Road Park - Path Reconstruction (B082-220M) | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHCP | Shore Road Park - Path Reconstruction (B082-220M) | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2025 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHCP | Shore Road Park - Path Reconstruction (B082-220M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2026 | Jun 2032
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHOR | SHORE ROAD PK - PERIMETER SIDEWALKS (B082A-110M) | 1 | DEVELOP SCOPE | Jul 2010 | Sep 2010 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHOR | SHORE ROAD PK - PERIMETER SIDEWALKS (B082A-110M) | 2 | DESIGN | Sep 2010 | Dec 2010 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHOR | SHORE ROAD PK - PERIMETER SIDEWALKS (B082A-110M) | 3 | BID/ REGISTER CONTRACT | Dec 2010 | Mar 2011 | Dec 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHOR | SHORE ROAD PK - PERIMETER SIDEWALKS (B082A-110M) | 4 | CONSTRUCTION | Mar 2011 | Mar 2012 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHOR | SHORE ROAD PK - PERIMETER SIDEWALKS (B082A-110M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2012 | Mar 2013 | Sep 2025 | Jun 2033
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHRD | Shore Road Pk- Rehab C/S -Field House B082-116M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jun 2020 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHRD | Shore Road Pk- Rehab C/S -Field House B082-116M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2020 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHRD | Shore Road Pk- Rehab C/S -Field House B082-116M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2020 | Mar 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHRD | Shore Road Pk- Rehab C/S -Field House B082-116M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2021 | Mar 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHRD | Shore Road Pk- Rehab C/S -Field House B082-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2022 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHRS | Shore Park & Parkway - Bike Path Surface Repair BG-715MA | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHRS | Shore Park & Parkway - Bike Path Surface Repair BG-715MA | 2 | DESIGN | Dec 2017 | Dec 2019 | Dec 2017 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHRS | Shore Park & Parkway - Bike Path Surface Repair BG-715MA | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHRS | Shore Park & Parkway - Bike Path Surface Repair BG-715MA | 4 | CONSTRUCTION | Sep 2020 | Sep 2022 | Sep 2020 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHRS | Shore Park & Parkway - Bike Path Surface Repair BG-715MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SRPD | SHORE ROAD PARK RESTROOM DEMOLITION--DEMOLITION OF RESTROOM | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SRPD | SHORE ROAD PARK RESTROOM DEMOLITION--DEMOLITION OF RESTROOM | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SRPD | SHORE ROAD PARK RESTROOM DEMOLITION--DEMOLITION OF RESTROOM | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SRPD | SHORE ROAD PARK RESTROOM DEMOLITION--DEMOLITION OF RESTROOM | 4 | CONSTRUCTION | Nov 2025 | May 2027 | Nov 2025 | May 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SRPD | SHORE ROAD PARK RESTROOM DEMOLITION--DEMOLITION OF RESTROOM | 5 | PUNCHLIST COMPLETE, JOB CLOSED | May 2027 | May 2028 | May 2027 | May 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SRPF | Shore Road Park Fencing | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SRPF | Shore Road Park Fencing | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SRPF | Shore Road Park Fencing | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SRPF | Shore Road Park Fencing | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SRPF | Shore Road Park Fencing | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210VINP | Shore Park & Parkway Vinland Playground Recon. B082-320M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210VINP | Shore Park & Parkway Vinland Playground Recon. B082-320M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210VINP | Shore Park & Parkway Vinland Playground Recon. B082-320M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210VINP | Shore Park & Parkway Vinland Playground Recon. B082-320M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210VINP | Shore Park & Parkway Vinland Playground Recon. B082-320M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BBCH | BATH BEACH PARK - PH2 and PH3 (B164-119M) | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BBCH | BATH BEACH PARK - PH2 and PH3 (B164-119M) | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BBCH | BATH BEACH PARK - PH2 and PH3 (B164-119M) | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BBCH | BATH BEACH PARK - PH2 and PH3 (B164-119M) | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BBCH | BATH BEACH PARK - PH2 and PH3 (B164-119M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BBST | Bath Beach Park Improvements B164-123M | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BBST | Bath Beach Park Improvements B164-123M | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BBST | Bath Beach Park Improvements B164-123M | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BBST | Bath Beach Park Improvements B164-123M | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BBST | Bath Beach Park Improvements B164-123M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BHPI | Benson Hurst Park Improvements | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BHPI | Benson Hurst Park Improvements | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BHPI | Benson Hurst Park Improvements | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BHPI | Benson Hurst Park Improvements | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BHPI | Benson Hurst Park Improvements | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BNHT | Bensonhurst Park - B007-118M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BNHT | Bensonhurst Park - B007-118M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BNHT | Bensonhurst Park - B007-118M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BNHT | Bensonhurst Park - B007-118M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BNHT | Bensonhurst Park - B007-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211SGBG | Samuel Goldberg Triangle - B231 | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211SGBG | Samuel Goldberg Triangle - B231 | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211SGBG | Samuel Goldberg Triangle - B231 | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211SGBG | Samuel Goldberg Triangle - B231 | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211SGBG | Samuel Goldberg Triangle - B231 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Mar 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212ALBE | Albemarle Playground - Resurface Soccer Field (B297-119M) | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212ALBE | Albemarle Playground - Resurface Soccer Field (B297-119M) | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212ALBE | Albemarle Playground - Resurface Soccer Field (B297-119M) | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212ALBE | Albemarle Playground - Resurface Soccer Field (B297-119M) | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212ALBE | Albemarle Playground - Resurface Soccer Field (B297-119M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212D17E | ALBEMARLE PLAYGROUND RECONSTR B297-105MA | 1 | DEVELOP SCOPE | Jul 2006 | Sep 2006 | Jul 2006 | Sep 2006
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212D17E | ALBEMARLE PLAYGROUND RECONSTR B297-105MA | 2 | DESIGN | Sep 2006 | Dec 2006 | Sep 2006 | Dec 2006
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212D17E | ALBEMARLE PLAYGROUND RECONSTR B297-105MA | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Dec 2006 | Mar 2007
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212D17E | ALBEMARLE PLAYGROUND RECONSTR B297-105MA | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Mar 2007 | Mar 2008
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212D17E | ALBEMARLE PLAYGROUND RECONSTR B297-105MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Mar 2008 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212FRFD | Friends Field - B372-116M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212FRFD | Friends Field - B372-116M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Jun 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212FRFD | Friends Field - B372-116M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Oct 2017 | Jun 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212FRFD | Friends Field - B372-116M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Sep 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212FRFD | Friends Field - B372-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Sep 2019 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213ALAE | Asser Levy Park - Adult Exercise Equipment (B080-118M) | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2023 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213ALAE | Asser Levy Park - Adult Exercise Equipment (B080-118M) | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2023 | Dec 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213ALAE | Asser Levy Park - Adult Exercise Equipment (B080-118M) | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213ALAE | Asser Levy Park - Adult Exercise Equipment (B080-118M) | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2025 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213ALAE | Asser Levy Park - Adult Exercise Equipment (B080-118M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2026 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213ALDR | Asser Levy Park Dog Run | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213ALDR | Asser Levy Park Dog Run | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213ALDR | Asser Levy Park Dog Run | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213ALDR | Asser Levy Park Dog Run | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213ALDR | Asser Levy Park Dog Run | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213ALVY | Asser Levy Park Playground & Path Reconstruction B080-116M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213ALVY | Asser Levy Park Playground & Path Reconstruction B080-116M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213ALVY | Asser Levy Park Playground & Path Reconstruction B080-116M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213ALVY | Asser Levy Park Playground & Path Reconstruction B080-116M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213ALVY | Asser Levy Park Playground & Path Reconstruction B080-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213BOIL | ABE STARK BOILERS AND CHILLERS (B169-111M) | 1 | DEVELOP SCOPE | Jul 2010 | Sep 2010 | Jul 2010 | Sep 2010
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213BOIL | ABE STARK BOILERS AND CHILLERS (B169-111M) | 2 | DESIGN | Sep 2010 | Dec 2010 | Sep 2010 | Dec 2010
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213BOIL | ABE STARK BOILERS AND CHILLERS (B169-111M) | 3 | BID/ REGISTER CONTRACT | Dec 2010 | Mar 2011 | Dec 2010 | Mar 2011
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213BOIL | ABE STARK BOILERS AND CHILLERS (B169-111M) | 4 | CONSTRUCTION | Mar 2011 | Mar 2012 | Mar 2011 | Mar 2012
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213BOIL | ABE STARK BOILERS AND CHILLERS (B169-111M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2012 | Mar 2013 | Mar 2012 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213BPLG | Brighton Playground Recon. Basketball Courts & Fitness Area | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213BPLG | Brighton Playground Recon. Basketball Courts & Fitness Area | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213BPLG | Brighton Playground Recon. Basketball Courts & Fitness Area | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213BPLG | Brighton Playground Recon. Basketball Courts & Fitness Area | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213BPLG | Brighton Playground Recon. Basketball Courts & Fitness Area | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213K11B | CONEY ISLAMD BWA;LK MISC RC W37-CORBIN B169-100MA | 1 | DEVELOP SCOPE | Jul 2006 | Sep 2006 | Jul 2006 | Sep 2006
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213K11B | CONEY ISLAMD BWA;LK MISC RC W37-CORBIN B169-100MA | 2 | DESIGN | Sep 2006 | Dec 2006 | Sep 2006 | Dec 2006
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213K11B | CONEY ISLAMD BWA;LK MISC RC W37-CORBIN B169-100MA | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Dec 2006 | Mar 2007
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213K11B | CONEY ISLAMD BWA;LK MISC RC W37-CORBIN B169-100MA | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Mar 2007 | Mar 2008
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213K11B | CONEY ISLAMD BWA;LK MISC RC W37-CORBIN B169-100MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Mar 2008 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213KPRB | KAISER PARK RECREATION BUILDING RECONSTR B129-106M/306M | 2 | DESIGN | Sep 2006 | Dec 2006 | Sep 2006 | Sep 2006
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213KPRB | KAISER PARK RECREATION BUILDING RECONSTR B129-106M/306M | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Mar 2007 | Sep 2007
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213KPRB | KAISER PARK RECREATION BUILDING RECONSTR B129-106M/306M | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Nov 2007 | Nov 2008
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213KPRB | KAISER PARK RECREATION BUILDING RECONSTR B129-106M/306M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Nov 2008 | Nov 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SCRN | Scarangella Park PRB Construction B106-117M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SCRN | Scarangella Park PRB Construction B106-117M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SCRN | Scarangella Park PRB Construction B106-117M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SCRN | Scarangella Park PRB Construction B106-117M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SCRN | Scarangella Park PRB Construction B106-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Jun 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SNPK | Scarangella Park - Reconstruction of Playground B106A-120M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SNPK | Scarangella Park - Reconstruction of Playground B106A-120M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SNPK | Scarangella Park - Reconstruction of Playground B106A-120M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SNPK | Scarangella Park - Reconstruction of Playground B106A-120M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SNPK | Scarangella Park - Reconstruction of Playground B106A-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SURF | SURF PLAYGROUND - PLAYGROUND RENOVATION (B315-118M) | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SURF | SURF PLAYGROUND - PLAYGROUND RENOVATION (B315-118M) | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SURF | SURF PLAYGROUND - PLAYGROUND RENOVATION (B315-118M) | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SURF | SURF PLAYGROUND - PLAYGROUND RENOVATION (B315-118M) | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SURF | SURF PLAYGROUND - PLAYGROUND RENOVATION (B315-118M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213WEST | West Playground PRB B252-115M | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Sep 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213WEST | West Playground PRB B252-115M | 2 | DESIGN | Sep 2014 | Dec 2014 | Oct 2014 | Dec 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213WEST | West Playground PRB B252-115M | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2014 | Mar 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213WEST | West Playground PRB B252-115M | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213WEST | West Playground PRB B252-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2016 | Jul 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214ANDP | Andries Playground - Phase 1 & 2 Reconstruction | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214ANDP | Andries Playground - Phase 1 & 2 Reconstruction | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214ANDP | Andries Playground - Phase 1 & 2 Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214ANDP | Andries Playground - Phase 1 & 2 Reconstruction | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214ANDP | Andries Playground - Phase 1 & 2 Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214DIGI | DIGILIO PLAYGROUND | 1 | DEVELOP SCOPE | Jul 2012 | Sep 2012 | Jul 2012 | Sep 2012
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214DIGI | DIGILIO PLAYGROUND | 2 | DESIGN | Sep 2012 | Dec 2012 | Sep 2012 | Dec 2012
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214DIGI | DIGILIO PLAYGROUND | 3 | BID/ REGISTER CONTRACT | Dec 2012 | Mar 2013 | Dec 2012 | Mar 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214DIGI | DIGILIO PLAYGROUND | 4 | CONSTRUCTION | Mar 2013 | Mar 2014 | Mar 2013 | Mar 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214DIGI | DIGILIO PLAYGROUND | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214K001 | PROSPECT PARK PARADE GROUNDS BLFLDS RENOV B068-101M | 1 | DEVELOP SCOPE | Jul 2000 | Sep 2000 | Jul 2000 | Oct 2000
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214K001 | PROSPECT PARK PARADE GROUNDS BLFLDS RENOV B068-101M | 2 | DESIGN | Sep 2000 | Feb 2001 | Jan 2001 | Feb 2001
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214K001 | PROSPECT PARK PARADE GROUNDS BLFLDS RENOV B068-101M | 3 | BID/ REGISTER CONTRACT | Feb 2001 | Jul 2001 | Mar 2001 | Jul 2001
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214K001 | PROSPECT PARK PARADE GROUNDS BLFLDS RENOV B068-101M | 4 | CONSTRUCTION | Aug 2001 | Sep 2003 | Aug 2001 | Mar 2004
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214K001 | PROSPECT PARK PARADE GROUNDS BLFLDS RENOV B068-101M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2003 | Sep 2004 | Mar 2004 | Apr 2005
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214KNDR | PPA-Kensington Dog Run in the Parade Grounds (B068-117M) | 2 | DESIGN | Dec 2016 | Jun 2018 | Dec 2016 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214KNDR | PPA-Kensington Dog Run in the Parade Grounds (B068-117M) | 3 | BID/ REGISTER CONTRACT | Jun 2018 | Mar 2019 | Dec 2017 | Sep 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214KNDR | PPA-Kensington Dog Run in the Parade Grounds (B068-117M) | 4 | CONSTRUCTION | Mar 2019 | Sep 2020 | Sep 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214KNDR | PPA-Kensington Dog Run in the Parade Grounds (B068-117M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214KPKP | Kolbert Park RC Perimeter B150 | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214KPKP | Kolbert Park RC Perimeter B150 | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214KPKP | Kolbert Park RC Perimeter B150 | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214KPKP | Kolbert Park RC Perimeter B150 | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214KPKP | Kolbert Park RC Perimeter B150 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214PARK | Acquisition/Recon. - Parkland in 44th Council District | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214PARK | Acquisition/Recon. - Parkland in 44th Council District | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214PARK | Acquisition/Recon. - Parkland in 44th Council District | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214PARK | Acquisition/Recon. - Parkland in 44th Council District | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214PARK | Acquisition/Recon. - Parkland in 44th Council District | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214RIDE | PPA - Riding Ring Construction B073-421M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214RIDE | PPA - Riding Ring Construction B073-421M | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214RIDE | PPA - Riding Ring Construction B073-421M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2013 | Mar 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214RIDE | PPA - Riding Ring Construction B073-421M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214RIDE | PPA - Riding Ring Construction B073-421M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2015 | Oct 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214UMMA | Umma Park & Plg Reconstruction | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214UMMA | Umma Park & Plg Reconstruction | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214UMMA | Umma Park & Plg Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214UMMA | Umma Park & Plg Reconstruction | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214UMMA | Umma Park & Plg Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215BBPG | BILL BROWN PLAYGROUND FLDHSE PRB FY'10 B109-112M | 1 | DEVELOP SCOPE | Jul 2009 | Sep 2009 | Jul 2009 | Oct 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215BBPG | BILL BROWN PLAYGROUND FLDHSE PRB FY'10 B109-112M | 2 | DESIGN | Sep 2009 | Dec 2009 | Nov 2012 | Feb 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215BBPG | BILL BROWN PLAYGROUND FLDHSE PRB FY'10 B109-112M | 3 | BID/ REGISTER CONTRACT | Dec 2009 | Mar 2010 | Mar 2013 | Sep 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215BBPG | BILL BROWN PLAYGROUND FLDHSE PRB FY'10 B109-112M | 4 | CONSTRUCTION | Mar 2010 | Mar 2011 | Oct 2013 | Oct 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215BBPG | BILL BROWN PLAYGROUND FLDHSE PRB FY'10 B109-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2011 | Mar 2012 | Oct 2014 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215HCPL | HOMECREST PLAYGROUND: RECONSTRUCT PLAYGROUND (B166B-118M) | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215HCPL | HOMECREST PLAYGROUND: RECONSTRUCT PLAYGROUND (B166B-118M) | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215HCPL | HOMECREST PLAYGROUND: RECONSTRUCT PLAYGROUND (B166B-118M) | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215HCPL | HOMECREST PLAYGROUND: RECONSTRUCT PLAYGROUND (B166B-118M) | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215HCPL | HOMECREST PLAYGROUND: RECONSTRUCT PLAYGROUND (B166B-118M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2019 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KELL | Kelly Park Playground - Recon. of Playground (B051-120M) | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KELL | Kelly Park Playground - Recon. of Playground (B051-120M) | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KELL | Kelly Park Playground - Recon. of Playground (B051-120M) | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KELL | Kelly Park Playground - Recon. of Playground (B051-120M) | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KELL | Kelly Park Playground - Recon. of Playground (B051-120M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KLCS | KELLY PARK PUBLIC RESTROOM BLDG B051-212M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KLCS | KELLY PARK PUBLIC RESTROOM BLDG B051-212M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KLCS | KELLY PARK PUBLIC RESTROOM BLDG B051-212M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KLCS | KELLY PARK PUBLIC RESTROOM BLDG B051-212M | 4 | CONSTRUCTION | Sep 2021 | Mar 2023 | Sep 2021 | Mar 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KLCS | KELLY PARK PUBLIC RESTROOM BLDG B051-212M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Mar 2024 | Mar 2023 | Mar 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KLLY | Kelly Playground Reconstruction B157-119M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KLLY | Kelly Playground Reconstruction B157-119M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KLLY | Kelly Playground Reconstruction B157-119M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KLLY | Kelly Playground Reconstruction B157-119M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KLLY | Kelly Playground Reconstruction B157-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MBP2 | Manhattan Beach Center Promenade Pavement Recon. B251-118M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MBP2 | Manhattan Beach Center Promenade Pavement Recon. B251-118M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MBP2 | Manhattan Beach Center Promenade Pavement Recon. B251-118M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MBP2 | Manhattan Beach Center Promenade Pavement Recon. B251-118M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MBP2 | Manhattan Beach Center Promenade Pavement Recon. B251-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MBTC | Manhattan Beach Park Tennis Courts Reconstruction B251-120M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MBTC | Manhattan Beach Park Tennis Courts Reconstruction B251-120M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MBTC | Manhattan Beach Park Tennis Courts Reconstruction B251-120M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MBTC | Manhattan Beach Park Tennis Courts Reconstruction B251-120M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MBTC | Manhattan Beach Park Tennis Courts Reconstruction B251-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MCDD | McDonald Playground - RC Play Equipment Area B244-118M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MCDD | McDonald Playground - RC Play Equipment Area B244-118M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MCDD | McDonald Playground - RC Play Equipment Area B244-118M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MCDD | McDonald Playground - RC Play Equipment Area B244-118M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MCDD | McDonald Playground - RC Play Equipment Area B244-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MCDP | PO Jeff Herman Ballfield Recon. - McDonald Plgd. B244-122M | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MCDP | PO Jeff Herman Ballfield Recon. - McDonald Plgd. B244-122M | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MCDP | PO Jeff Herman Ballfield Recon. - McDonald Plgd. B244-122M | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MCDP | PO Jeff Herman Ballfield Recon. - McDonald Plgd. B244-122M | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MCDP | PO Jeff Herman Ballfield Recon. - McDonald Plgd. B244-122M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MEL2 | Mellet Playground Phase 2 - Construct Basketball Courts | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MEL2 | Mellet Playground Phase 2 - Construct Basketball Courts | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MEL2 | Mellet Playground Phase 2 - Construct Basketball Courts | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MEL2 | Mellet Playground Phase 2 - Construct Basketball Courts | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MEL2 | Mellet Playground Phase 2 - Construct Basketball Courts | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MELL | MELLET PLAYGROUND- RECONSTRUCT PLAYGROUND (B197-118M) | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MELL | MELLET PLAYGROUND- RECONSTRUCT PLAYGROUND (B197-118M) | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MELL | MELLET PLAYGROUND- RECONSTRUCT PLAYGROUND (B197-118M) | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MELL | MELLET PLAYGROUND- RECONSTRUCT PLAYGROUND (B197-118M) | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MELL | MELLET PLAYGROUND- RECONSTRUCT PLAYGROUND (B197-118M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215NRTP | NORTON PLAYGROUND RECONSTRUCTION, B208-106M | 1 | DEVELOP SCOPE | Jul 2006 | Sep 2006 | Jul 2006 | Sep 2006
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215NRTP | NORTON PLAYGROUND RECONSTRUCTION, B208-106M | 2 | DESIGN | Sep 2006 | Dec 2006 | Sep 2006 | Dec 2006
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215NRTP | NORTON PLAYGROUND RECONSTRUCTION, B208-106M | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Dec 2006 | Mar 2007
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215NRTP | NORTON PLAYGROUND RECONSTRUCTION, B208-106M | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Mar 2007 | Mar 2008
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215NRTP | NORTON PLAYGROUND RECONSTRUCTION, B208-106M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Mar 2008 | Mar 2009
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215PB15 | EMMONS AVENUE SIDEWALKS & SHEEPSHEAD PIER RCNSTR NYSMMGRANTS | 1 | DEVELOP SCOPE | Jul 2007 | Sep 2007 | Jul 2007 | May 2008
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215PB15 | EMMONS AVENUE SIDEWALKS & SHEEPSHEAD PIER RCNSTR NYSMMGRANTS | 2 | DESIGN | Sep 2007 | Dec 2007 | May 2008 | Sep 2008
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215PB15 | EMMONS AVENUE SIDEWALKS & SHEEPSHEAD PIER RCNSTR NYSMMGRANTS | 3 | BID/ REGISTER CONTRACT | Dec 2007 | Mar 2008 | Sep 2008 | Sep 2008
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215PB15 | EMMONS AVENUE SIDEWALKS & SHEEPSHEAD PIER RCNSTR NYSMMGRANTS | 4 | CONSTRUCTION | Mar 2008 | Mar 2009 | Sep 2008 | Sep 2008
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215PB15 | EMMONS AVENUE SIDEWALKS & SHEEPSHEAD PIER RCNSTR NYSMMGRANTS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2009 | Mar 2010 | Sep 2008 | Jun 2033
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215PIER | SHEEPSHEAD BAY PIERS B393-118M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215PIER | SHEEPSHEAD BAY PIERS B393-118M | 2 | DESIGN | Dec 2017 | Dec 2019 | Dec 2017 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215PIER | SHEEPSHEAD BAY PIERS B393-118M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215PIER | SHEEPSHEAD BAY PIERS B393-118M | 4 | CONSTRUCTION | Sep 2020 | Sep 2022 | Sep 2020 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215PIER | SHEEPSHEAD BAY PIERS B393-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215SPBK | SHEEPSHEAD PLAYGROUND BASKETBALL COURT | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215SPBK | SHEEPSHEAD PLAYGROUND BASKETBALL COURT | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215SPBK | SHEEPSHEAD PLAYGROUND BASKETBALL COURT | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215SPBK | SHEEPSHEAD PLAYGROUND BASKETBALL COURT | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215SPBK | SHEEPSHEAD PLAYGROUND BASKETBALL COURT | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Jun 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216BHIP | BETSY HEAD - IMAGINATION PLGD PRB B008 | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216BHIP | BETSY HEAD - IMAGINATION PLGD PRB B008 | 2 | DESIGN | Dec 2016 | Dec 2017 | Jan 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216BHIP | BETSY HEAD - IMAGINATION PLGD PRB B008 | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Jan 2018 | Sep 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216BHIP | BETSY HEAD - IMAGINATION PLGD PRB B008 | 4 | CONSTRUCTION | Sep 2018 | Mar 2020 | Sep 2018 | Mar 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216BHIP | BETSY HEAD - IMAGINATION PLGD PRB B008 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Mar 2021 | Mar 2020 | Jul 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216BRCP | BROWNSVILLE REC. CTR. PLGD LIGHT. (BASKETBALL CTS) B270-109M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2010 | Mar 2011 | Mar 2010 | Mar 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216C17L | BROWNSVILLE RCR CNTR PLGD ASPH BALLFLD RECONSTR; B270-107M | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Dec 2006 | Mar 2007
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216C17L | BROWNSVILLE RCR CNTR PLGD ASPH BALLFLD RECONSTR; B270-107M | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Mar 2007 | Mar 2008
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216C17L | BROWNSVILLE RCR CNTR PLGD ASPH BALLFLD RECONSTR; B270-107M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Mar 2008 | Mar 2009
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216CHES | Chester Park - Playground Renovation Phase 1 B362-120M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216CHES | Chester Park - Playground Renovation Phase 1 B362-120M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216CHES | Chester Park - Playground Renovation Phase 1 B362-120M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216CHES | Chester Park - Playground Renovation Phase 1 B362-120M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216CHES | Chester Park - Playground Renovation Phase 1 B362-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216K11A | KINGSBOROUGH (PACIFIC) PLGD RCNSTR PRTN B153-100M | 2 | DESIGN | Sep 2006 | Dec 2006 | Sep 2006 | Dec 2006
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216K11A | KINGSBOROUGH (PACIFIC) PLGD RCNSTR PRTN B153-100M | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Dec 2006 | Mar 2007
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216K11A | KINGSBOROUGH (PACIFIC) PLGD RCNSTR PRTN B153-100M | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Mar 2007 | Mar 2008
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216K11A | KINGSBOROUGH (PACIFIC) PLGD RCNSTR PRTN B153-100M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Mar 2008 | Mar 2009
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OCAN | Ocean Hill Playground - Brooklyn B144-120M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OCAN | Ocean Hill Playground - Brooklyn B144-120M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OCAN | Ocean Hill Playground - Brooklyn B144-120M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OCAN | Ocean Hill Playground - Brooklyn B144-120M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OCAN | Ocean Hill Playground - Brooklyn B144-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OSBN | Osborn Playground - Park Renovation (B343-119M) | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OSBN | Osborn Playground - Park Renovation (B343-119M) | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OSBN | Osborn Playground - Park Renovation (B343-119M) | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OSBN | Osborn Playground - Park Renovation (B343-119M) | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OSBN | Osborn Playground - Park Renovation (B343-119M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OSBO | Osborn Playground Phase 2 - Adult Fitness Area B343-123M | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OSBO | Osborn Playground Phase 2 - Adult Fitness Area B343-123M | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OSBO | Osborn Playground Phase 2 - Adult Fitness Area B343-123M | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OSBO | Osborn Playground Phase 2 - Adult Fitness Area B343-123M | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OSBO | Osborn Playground Phase 2 - Adult Fitness Area B343-123M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OSPL | Osborn Playground - Phase 2 Reconstruction | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OSPL | Osborn Playground - Phase 2 Reconstruction | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OSPL | Osborn Playground - Phase 2 Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OSPL | Osborn Playground - Phase 2 Reconstruction | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OSPL | Osborn Playground - Phase 2 Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216PS25 | PS 125 Playground - Brooklyn B227-119MA | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216PS25 | PS 125 Playground - Brooklyn B227-119MA | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216PS25 | PS 125 Playground - Brooklyn B227-119MA | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216PS25 | PS 125 Playground - Brooklyn B227-119MA | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216PS25 | PS 125 Playground - Brooklyn B227-119MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217AQBO | Paerdegat Aquatic Center Boiler Reconstruction | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217AQBO | Paerdegat Aquatic Center Boiler Reconstruction | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217AQBO | Paerdegat Aquatic Center Boiler Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217AQBO | Paerdegat Aquatic Center Boiler Reconstruction | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217AQBO | Paerdegat Aquatic Center Boiler Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217CPRN | Chiarantano Playground Renovations | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217CPRN | Chiarantano Playground Renovations | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217CPRN | Chiarantano Playground Renovations | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217CPRN | Chiarantano Playground Renovations | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217CPRN | Chiarantano Playground Renovations | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2029 | Nov 2026 | Nov 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217D017 | WYCKOFF HOUSE PARK CULT. EDUC. COMPLX B376-113M | 1 | DEVELOP SCOPE | Oct 2003 | Jan 2004 | Oct 2003 | Aug 2008
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217D017 | WYCKOFF HOUSE PARK CULT. EDUC. COMPLX B376-113M | 2 | DESIGN | Jan 2004 | Apr 2004 | Aug 2008 | Sep 2009
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217D017 | WYCKOFF HOUSE PARK CULT. EDUC. COMPLX B376-113M | 3 | BID/ REGISTER CONTRACT | Apr 2004 | Jun 2004 | Jun 2009 | Sep 2009
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217D017 | WYCKOFF HOUSE PARK CULT. EDUC. COMPLX B376-113M | 4 | CONSTRUCTION | Jul 2004 | Jul 2005 | Jul 2004 | Jul 2005
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217D017 | WYCKOFF HOUSE PARK CULT. EDUC. COMPLX B376-113M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2005 | Jul 2006 | Jul 2005 | Jun 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217HMCS | Harry Maze Playground - Public Restroom Bldg Recon | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217HMCS | Harry Maze Playground - Public Restroom Bldg Recon | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217HMCS | Harry Maze Playground - Public Restroom Bldg Recon | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217HMCS | Harry Maze Playground - Public Restroom Bldg Recon | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217HMCS | Harry Maze Playground - Public Restroom Bldg Recon | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217NOST | Nostrand Playground - B250-117M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217NOST | Nostrand Playground - B250-117M | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217NOST | Nostrand Playground - B250-117M | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217NOST | Nostrand Playground - B250-117M | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217NOST | Nostrand Playground - B250-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PADG | Paerdegat Park - Reconstruction of Turf B218-122M | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PADG | Paerdegat Park - Reconstruction of Turf B218-122M | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PADG | Paerdegat Park - Reconstruction of Turf B218-122M | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PADG | Paerdegat Park - Reconstruction of Turf B218-122M | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PADG | Paerdegat Park - Reconstruction of Turf B218-122M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PBYC | Paerdegat Basin Yacht Club | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PBYC | Paerdegat Basin Yacht Club | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PBYC | Paerdegat Basin Yacht Club | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PDGT | PAERDEGAT ATHLETIC CLUB - HVAC WORK | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Mar 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PDGT | PAERDEGAT ATHLETIC CLUB - HVAC WORK | 2 | DESIGN | Sep 2013 | Dec 2013 | Mar 2014 | Apr 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PDGT | PAERDEGAT ATHLETIC CLUB - HVAC WORK | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Apr 2015 | Jul 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PDGT | PAERDEGAT ATHLETIC CLUB - HVAC WORK | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Jul 2017 | Jul 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PDGT | PAERDEGAT ATHLETIC CLUB - HVAC WORK | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Jul 2018 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217WYKF | WYCKOFF FARMHOUSE - ROOF RESTORATION B376-111M | 1 | DEVELOP SCOPE | Jul 2010 | Sep 2010 | Jul 2010 | Jun 2011
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217WYKF | WYCKOFF FARMHOUSE - ROOF RESTORATION B376-111M | 2 | DESIGN | Sep 2010 | Dec 2010 | Jun 2011 | Jan 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217WYKF | WYCKOFF FARMHOUSE - ROOF RESTORATION B376-111M | 3 | BID/ REGISTER CONTRACT | Dec 2010 | Mar 2011 | Jan 2016 | Apr 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217WYKF | WYCKOFF FARMHOUSE - ROOF RESTORATION B376-111M | 4 | CONSTRUCTION | Mar 2011 | Mar 2012 | Apr 2016 | Apr 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217WYKF | WYCKOFF FARMHOUSE - ROOF RESTORATION B376-111M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2012 | Mar 2013 | Apr 2017 | Jun 2033
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BILD | Bildersee Playground (B335-116M) | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BILD | Bildersee Playground (B335-116M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2016 | Aug 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BKBF | Breukelen Ball Fields Renovations (Phase I) | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BKBF | Breukelen Ball Fields Renovations (Phase I) | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BKBF | Breukelen Ball Fields Renovations (Phase I) | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BKBF | Breukelen Ball Fields Renovations (Phase I) | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BKBF | Breukelen Ball Fields Renovations (Phase I) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BPLG | Bildersee plgd-new plgd and ph2 | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BPLG | Bildersee plgd-new plgd and ph2 | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BPLG | Bildersee plgd-new plgd and ph2 | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BPLG | Bildersee plgd-new plgd and ph2 | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BPLG | Bildersee plgd-new plgd and ph2 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BVHP | Bayview Houses Playground Reconstruction - Phase 2 | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BVHP | Bayview Houses Playground Reconstruction - Phase 2 | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BVHP | Bayview Houses Playground Reconstruction - Phase 2 | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BVHP | Bayview Houses Playground Reconstruction - Phase 2 | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BVHP | Bayview Houses Playground Reconstruction - Phase 2 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218CCMF | CANARSIE PARK PHASE V- PRB B018-214M | 1 | DEVELOP SCOPE | Jul 2012 | Sep 2012 | Jul 2012 | Jan 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218CCMF | CANARSIE PARK PHASE V- PRB B018-214M | 2 | DESIGN | Sep 2012 | Dec 2012 | Jan 2015 | Feb 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218CCMF | CANARSIE PARK PHASE V- PRB B018-214M | 3 | BID/ REGISTER CONTRACT | Dec 2012 | Mar 2013 | Mar 2017 | May 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218CCMF | CANARSIE PARK PHASE V- PRB B018-214M | 4 | CONSTRUCTION | Mar 2013 | Mar 2014 | May 2017 | May 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218CCMF | CANARSIE PARK PHASE V- PRB B018-214M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2014 | Mar 2015 | May 2018 | May 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218CPBF | Canarsie Park Ball Field Renovation | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218CPBF | Canarsie Park Ball Field Renovation | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218CPBF | Canarsie Park Ball Field Renovation | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218CPBF | Canarsie Park Ball Field Renovation | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218CPBF | Canarsie Park Ball Field Renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218GOLF | BK Golf Alliance - Marine Pk. Golf Course - B057-119M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2023 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218GOLF | BK Golf Alliance - Marine Pk. Golf Course - B057-119M | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2023 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218GOLF | BK Golf Alliance - Marine Pk. Golf Course - B057-119M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2023 | Mar 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218GOLF | BK Golf Alliance - Marine Pk. Golf Course - B057-119M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2024 | Mar 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218GOLF | BK Golf Alliance - Marine Pk. Golf Course - B057-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2025 | Jun 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218HKMN | Hickman Playground Reconstruction | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218HKMN | Hickman Playground Reconstruction | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218HKMN | Hickman Playground Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218HKMN | Hickman Playground Reconstruction | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218HKMN | Hickman Playground Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218JFEE | Jacob Joffe Playground- Park Renovations | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218JFEE | Jacob Joffe Playground- Park Renovations | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218JFEE | Jacob Joffe Playground- Park Renovations | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218JFEE | Jacob Joffe Playground- Park Renovations | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218JFEE | Jacob Joffe Playground- Park Renovations | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2019 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218LOTT | HENDRICK I. LOTT HOUSE -INTERIOR RESTORATION | 1 | DEVELOP SCOPE | Jul 2010 | Sep 2010 | Dec 2014 | Mar 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218LOTT | HENDRICK I. LOTT HOUSE -INTERIOR RESTORATION | 2 | DESIGN | Sep 2010 | Dec 2010 | Mar 2015 | Jun 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218LOTT | HENDRICK I. LOTT HOUSE -INTERIOR RESTORATION | 3 | BID/ REGISTER CONTRACT | Dec 2010 | Mar 2011 | Jun 2015 | Sep 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218LOTT | HENDRICK I. LOTT HOUSE -INTERIOR RESTORATION | 4 | CONSTRUCTION | Mar 2011 | Mar 2012 | Sep 2015 | Sep 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218LOTT | HENDRICK I. LOTT HOUSE -INTERIOR RESTORATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2012 | Mar 2013 | Sep 2016 | Jun 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218MPOV | Marine Park Oval Reconstruction B057-120M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218MPOV | Marine Park Oval Reconstruction B057-120M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218MPOV | Marine Park Oval Reconstruction B057-120M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218MPOV | Marine Park Oval Reconstruction B057-120M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218MPOV | Marine Park Oval Reconstruction B057-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218MPPG | Marine Park Playground - Recon. of Playground 278 B057-220M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218MPPG | Marine Park Playground - Recon. of Playground 278 B057-220M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218MPPG | Marine Park Playground - Recon. of Playground 278 B057-220M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218MPPG | Marine Park Playground - Recon. of Playground 278 B057-220M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218MPPG | Marine Park Playground - Recon. of Playground 278 B057-220M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218PWMP | Power-Memorial- Seating Area ( B219-120M) | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218PWMP | Power-Memorial- Seating Area ( B219-120M) | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218PWMP | Power-Memorial- Seating Area ( B219-120M) | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218PWMP | Power-Memorial- Seating Area ( B219-120M) | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218PWMP | Power-Memorial- Seating Area ( B219-120M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218SUNN | Sunners Playground - Renovate Playground (B206-119M) | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218SUNN | Sunners Playground - Renovate Playground (B206-119M) | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218SUNN | Sunners Playground - Renovate Playground (B206-119M) | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218SUNN | Sunners Playground - Renovate Playground (B206-119M) | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218SUNN | Sunners Playground - Renovate Playground (B206-119M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH01 | ANCHOR PARK- Betsy Head (B008-) | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH01 | ANCHOR PARK- Betsy Head (B008-) | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH01 | ANCHOR PARK- Betsy Head (B008-) | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH01 | ANCHOR PARK- Betsy Head (B008-) | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH01 | ANCHOR PARK- Betsy Head (B008-) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2019 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH02 | Betsy Head Park Public Rest Room Reconstruction (B008-218M) | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH02 | Betsy Head Park Public Rest Room Reconstruction (B008-218M) | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH02 | Betsy Head Park Public Rest Room Reconstruction (B008-218M) | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH02 | Betsy Head Park Public Rest Room Reconstruction (B008-218M) | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH02 | Betsy Head Park Public Rest Room Reconstruction (B008-218M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BARRYP | Berry Playground Reconstruction B154-122M | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BARRYP | Berry Playground Reconstruction B154-122M | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BARRYP | Berry Playground Reconstruction B154-122M | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BARRYP | Berry Playground Reconstruction B154-122M | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BARRYP | Berry Playground Reconstruction B154-122M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BDCHOS | Green Space located on corner of Bedford & Church Ave, BK | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BDCHOS | Green Space located on corner of Bedford & Church Ave, BK | 2 | DESIGN | Dec 2022 | Jun 2024 | Dec 2022 | Jun 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BDCHOS | Green Space located on corner of Bedford & Church Ave, BK | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BDCHOS | Green Space located on corner of Bedford & Church Ave, BK | 4 | CONSTRUCTION | Mar 2025 | Sep 2026 | Mar 2025 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BDCHOS | Green Space located on corner of Bedford & Church Ave, BK | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPD | CON - BIKE PATH THRU CANARSIE PARK WEST | 1 | DEVELOP SCOPE | Mar 2013 | May 2013 | Mar 2013 | May 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPD | CON - BIKE PATH THRU CANARSIE PARK WEST | 2 | DESIGN | May 2013 | Aug 2013 | May 2013 | Aug 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPD | CON - BIKE PATH THRU CANARSIE PARK WEST | 3 | BID/ REGISTER CONTRACT | Aug 2013 | Nov 2013 | Aug 2013 | Nov 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPD | CON - BIKE PATH THRU CANARSIE PARK WEST | 4 | CONSTRUCTION | Nov 2013 | Nov 2014 | Nov 2014 | Nov 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPD | CON - BIKE PATH THRU CANARSIE PARK WEST | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2014 | Nov 2015 | Nov 2015 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPE | Mill Basin Bridge Trees | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Apr 2020 | Oct 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPE | Mill Basin Bridge Trees | 2 | DESIGN | Dec 2016 | Dec 2018 | Oct 2020 | Oct 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPE | Mill Basin Bridge Trees | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Oct 2022 | Jul 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPE | Mill Basin Bridge Trees | 4 | CONSTRUCTION | Sep 2019 | Sep 2022 | Jul 2023 | Jul 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPE | Mill Basin Bridge Trees | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2024 | Jul 2026 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPF | Belt Parkway Restoration and Tree Replacement | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPF | Belt Parkway Restoration and Tree Replacement | 2 | DESIGN | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPF | Belt Parkway Restoration and Tree Replacement | 3 | BID/ REGISTER CONTRACT | Sep 2023 | Jun 2024 | Sep 2023 | Jun 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPF | Belt Parkway Restoration and Tree Replacement | 4 | CONSTRUCTION | Jun 2024 | Dec 2026 | Jun 2024 | Dec 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPF | Belt Parkway Restoration and Tree Replacement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2026 | Jun 2028 | Dec 2026 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKHQLV | NYC PARKS - BROOKLYN HQ LITCHFIELD VILLA: RENOVATIONS TO BR | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKHQLV | NYC PARKS - BROOKLYN HQ LITCHFIELD VILLA: RENOVATIONS TO BR | 2 | DESIGN | Sep 2023 | Sep 2025 | Sep 2023 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKHQLV | NYC PARKS - BROOKLYN HQ LITCHFIELD VILLA: RENOVATIONS TO BR | 3 | BID/ REGISTER CONTRACT | Sep 2025 | Jun 2026 | Sep 2025 | Jun 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKHQLV | NYC PARKS - BROOKLYN HQ LITCHFIELD VILLA: RENOVATIONS TO BR | 4 | CONSTRUCTION | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKHQLV | NYC PARKS - BROOKLYN HQ LITCHFIELD VILLA: RENOVATIONS TO BR | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2028 | Jun 2029 | Jun 2028 | Jun 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKPAV1 | Brooklyn Multisite Pavement Reconstruction | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKPAV1 | Brooklyn Multisite Pavement Reconstruction | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKPAV1 | Brooklyn Multisite Pavement Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKPAV1 | Brooklyn Multisite Pavement Reconstruction | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKPAV1 | Brooklyn Multisite Pavement Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKPLG1 | Brooklyn MPPA SOGR Reconstruction BG-220M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Apr 2023 | Oct 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKPLG1 | Brooklyn MPPA SOGR Reconstruction BG-220M | 2 | DESIGN | Dec 2019 | Jun 2021 | Oct 2023 | Apr 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKPLG1 | Brooklyn MPPA SOGR Reconstruction BG-220M | 3 | BID/ REGISTER CONTRACT | Jun 2021 | Mar 2022 | Apr 2025 | Jan 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKPLG1 | Brooklyn MPPA SOGR Reconstruction BG-220M | 4 | CONSTRUCTION | Mar 2022 | Sep 2023 | Jan 2026 | Jul 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKPLG1 | Brooklyn MPPA SOGR Reconstruction BG-220M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Jul 2027 | Jun 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKSTF1 | Brooklyn Synthetic Turf Limited Scope Reconstruction | 1 | DEVELOP SCOPE | Apr 2024 | Oct 2024 | Apr 2024 | Oct 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKSTF1 | Brooklyn Synthetic Turf Limited Scope Reconstruction | 2 | DESIGN | Oct 2024 | Oct 2025 | Oct 2024 | Oct 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKSTF1 | Brooklyn Synthetic Turf Limited Scope Reconstruction | 3 | BID/ REGISTER CONTRACT | Oct 2025 | Jul 2026 | Oct 2025 | Jul 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKSTF1 | Brooklyn Synthetic Turf Limited Scope Reconstruction | 4 | CONSTRUCTION | Jul 2026 | Jul 2027 | Jul 2026 | Jul 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKSTF1 | Brooklyn Synthetic Turf Limited Scope Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2027 | Jun 2028 | Jul 2027 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BQGRN | BQ GREEN | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BQGRN | BQ GREEN | 2 | DESIGN | Dec 2017 | Jun 2019 | Dec 2017 | Jun 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BQGRN | BQ GREEN | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Mar 2020 | Jun 2019 | Mar 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BQGRN | BQ GREEN | 4 | CONSTRUCTION | Mar 2020 | Sep 2021 | Mar 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BQGRN | BQ GREEN | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BRIGHM | Brigham Park - plgd & passive area B057-212M/512M | 1 | DEVELOP SCOPE | Jul 2009 | Sep 2009 | Jul 2009 | Sep 2009
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BRIGHM | Brigham Park - plgd & passive area B057-212M/512M | 2 | DESIGN | Sep 2009 | Dec 2009 | Sep 2009 | Dec 2009
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BRIGHM | Brigham Park - plgd & passive area B057-212M/512M | 3 | BID/ REGISTER CONTRACT | Dec 2009 | Mar 2010 | Dec 2009 | Mar 2010
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BRIGHM | Brigham Park - plgd & passive area B057-212M/512M | 4 | CONSTRUCTION | Mar 2010 | Mar 2011 | Mar 2010 | Mar 2011
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BRIGHM | Brigham Park - plgd & passive area B057-212M/512M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2011 | Mar 2012 | Mar 2011 | Jul 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BSKBL1 | Brooklyn Basketball Courts Reconstruction (SoGR) BG-320M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Apr 2023 | Oct 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BSKBL1 | Brooklyn Basketball Courts Reconstruction (SoGR) BG-320M | 2 | DESIGN | Dec 2019 | Jun 2021 | Oct 2023 | Apr 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BSKBL1 | Brooklyn Basketball Courts Reconstruction (SoGR) BG-320M | 3 | BID/ REGISTER CONTRACT | Jun 2021 | Mar 2022 | Apr 2025 | Jan 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BSKBL1 | Brooklyn Basketball Courts Reconstruction (SoGR) BG-320M | 4 | CONSTRUCTION | Mar 2022 | Sep 2023 | Jan 2026 | Jul 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BSKBL1 | Brooklyn Basketball Courts Reconstruction (SoGR) BG-320M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Jul 2027 | Apr 2032
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWCC04 | BKLYN MULTISITE - PUBLIC RESTROOM TILDEN & BANNEKER BG-919M | 1 | DEVELOP SCOPE | Jul 2010 | Sep 2010 | Oct 2015 | Jan 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWCC04 | BKLYN MULTISITE - PUBLIC RESTROOM TILDEN & BANNEKER BG-919M | 2 | DESIGN | Sep 2010 | Dec 2010 | Jan 2016 | Apr 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWCC04 | BKLYN MULTISITE - PUBLIC RESTROOM TILDEN & BANNEKER BG-919M | 3 | BID/ REGISTER CONTRACT | Dec 2010 | Mar 2011 | Apr 2016 | Jul 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWCC04 | BKLYN MULTISITE - PUBLIC RESTROOM TILDEN & BANNEKER BG-919M | 4 | CONSTRUCTION | Mar 2011 | Mar 2012 | Jul 2016 | Jul 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWCC04 | BKLYN MULTISITE - PUBLIC RESTROOM TILDEN & BANNEKER BG-919M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2012 | Mar 2013 | Jul 2017 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWK11I | RQMT CNTR BKLYN BP FY00 PLEQ SFTYSRF PAV FNC GNLSW BG-300M | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWK11I | RQMT CNTR BKLYN BP FY00 PLEQ SFTYSRF PAV FNC GNLSW BG-300M | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWK11I | RQMT CNTR BKLYN BP FY00 PLEQ SFTYSRF PAV FNC GNLSW BG-300M | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWK11I | RQMT CNTR BKLYN BP FY00 PLEQ SFTYSRF PAV FNC GNLSW BG-300M | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWK11I | RQMT CNTR BKLYN BP FY00 PLEQ SFTYSRF PAV FNC GNLSW BG-300M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWK11J | BROOKLYN REQMT FY03/4 INCL OCEAN PKWY MALLS BENCHES BG-504M | 1 | DEVELOP SCOPE | Jul 2003 | Nov 2003 | Jul 2003 | Jan 2004
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWK11J | BROOKLYN REQMT FY03/4 INCL OCEAN PKWY MALLS BENCHES BG-504M | 2 | DESIGN | Dec 2003 | Dec 2003 | Jan 2004 | Apr 2004
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWK11J | BROOKLYN REQMT FY03/4 INCL OCEAN PKWY MALLS BENCHES BG-504M | 3 | BID/ REGISTER CONTRACT | Jan 2004 | Apr 2004 | Apr 2004 | Aug 2004
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWK11J | BROOKLYN REQMT FY03/4 INCL OCEAN PKWY MALLS BENCHES BG-504M | 4 | CONSTRUCTION | May 2004 | May 2005 | Dec 2004 | Sep 2005
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWK11J | BROOKLYN REQMT FY03/4 INCL OCEAN PKWY MALLS BENCHES BG-504M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | May 2005 | May 2006 | Sep 2005 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWRPAV | Brower Park Path Reconstruction | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWRPAV | Brower Park Path Reconstruction | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWRPAV | Brower Park Path Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWRPAV | Brower Park Path Reconstruction | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWRPAV | Brower Park Path Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIB22H | Coney Island Beach and Boardwalk (Phase 1) | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIB22H | Coney Island Beach and Boardwalk (Phase 1) | 2 | DESIGN | Dec 2022 | Dec 2024 | Dec 2022 | Dec 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIB22H | Coney Island Beach and Boardwalk (Phase 1) | 3 | BID/ REGISTER CONTRACT | Dec 2024 | Sep 2025 | Dec 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIB22H | Coney Island Beach and Boardwalk (Phase 1) | 4 | CONSTRUCTION | Sep 2025 | Sep 2028 | Sep 2025 | Sep 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIB22H | Coney Island Beach and Boardwalk (Phase 1) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2028 | Sep 2030 | Sep 2028 | Sep 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIBBOL | Coney Island Boardwalk - Cons Security Measures B169-120M | 1 | DEVELOP SCOPE | May 2018 | Nov 2018 | May 2018 | Nov 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIBBOL | Coney Island Boardwalk - Cons Security Measures B169-120M | 2 | DESIGN | Nov 2018 | Nov 2019 | Nov 2018 | Nov 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIBBOL | Coney Island Boardwalk - Cons Security Measures B169-120M | 3 | BID/ REGISTER CONTRACT | Nov 2019 | Aug 2020 | Nov 2019 | Aug 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIBBOL | Coney Island Boardwalk - Cons Security Measures B169-120M | 4 | CONSTRUCTION | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIBBOL | Coney Island Boardwalk - Cons Security Measures B169-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Aug 2022 | Aug 2021 | Jun 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIBWLK | CONEY ISLAND BOARDWALK (B169-110M) | 1 | DEVELOP SCOPE | Jul 2010 | Sep 2010 | Jul 2010 | Sep 2010
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIBWLK | CONEY ISLAND BOARDWALK (B169-110M) | 2 | DESIGN | Sep 2010 | Dec 2010 | Sep 2010 | Dec 2010
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIBWLK | CONEY ISLAND BOARDWALK (B169-110M) | 3 | BID/ REGISTER CONTRACT | Dec 2010 | Mar 2011 | Dec 2010 | Mar 2011
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIBWLK | CONEY ISLAND BOARDWALK (B169-110M) | 4 | CONSTRUCTION | Mar 2011 | Mar 2012 | Mar 2011 | Mar 2012
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIBWLK | CONEY ISLAND BOARDWALK (B169-110M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2012 | Mar 2013 | Mar 2012 | Jun 2033
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIGNWY | CONEY ISLAND GREENWAY PROPOSED SAFETEA GRANT | 1 | DEVELOP SCOPE | Jul 2011 | Sep 2011 | Jul 2021 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIGNWY | CONEY ISLAND GREENWAY PROPOSED SAFETEA GRANT | 2 | DESIGN | Sep 2011 | Dec 2011 | Sep 2011 | Dec 2011
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIGNWY | CONEY ISLAND GREENWAY PROPOSED SAFETEA GRANT | 3 | BID/ REGISTER CONTRACT | Dec 2011 | Mar 2012 | Dec 2011 | Mar 2012
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIGNWY | CONEY ISLAND GREENWAY PROPOSED SAFETEA GRANT | 4 | CONSTRUCTION | Mar 2012 | Mar 2013 | Mar 2012 | Mar 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIGNWY | CONEY ISLAND GREENWAY PROPOSED SAFETEA GRANT | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2013 | Mar 2014 | Mar 2013 | Jun 2033
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIWALK | CONEY ISLAND BWALK - RC OF VARIOUS SEGMENT B169-220M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2009 | Sep 2009
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIWALK | CONEY ISLAND BWALK - RC OF VARIOUS SEGMENT B169-220M | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2009 | Dec 2009
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIWALK | CONEY ISLAND BWALK - RC OF VARIOUS SEGMENT B169-220M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2009 | Mar 2010
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIWALK | CONEY ISLAND BWALK - RC OF VARIOUS SEGMENT B169-220M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2010 | Mar 2011
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIWALK | CONEY ISLAND BWALK - RC OF VARIOUS SEGMENT B169-220M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2011 | Mar 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CONYGS | CONEY ISLAND COASTAL RESIL. GREENSTREETS BG-515MA | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Apr 2016 | Apr 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CONYGS | CONEY ISLAND COASTAL RESIL. GREENSTREETS BG-515MA | 2 | DESIGN | Sep 2014 | Dec 2014 | Apr 2019 | Apr 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CONYGS | CONEY ISLAND COASTAL RESIL. GREENSTREETS BG-515MA | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Apr 2022 | Jul 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CONYGS | CONEY ISLAND COASTAL RESIL. GREENSTREETS BG-515MA | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Jul 2022 | Jul 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CONYGS | CONEY ISLAND COASTAL RESIL. GREENSTREETS BG-515MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Jul 2023 | Jul 2032
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2COOPCS | Cooper Park-Reconstruction of PRB | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2COOPCS | Cooper Park-Reconstruction of PRB | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2COOPCS | Cooper Park-Reconstruction of PRB | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2COOPCS | Cooper Park-Reconstruction of PRB | 4 | CONSTRUCTION | Sep 2019 | Mar 2021 | Sep 2019 | Mar 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2COOPCS | Cooper Park-Reconstruction of PRB | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Mar 2022 | Mar 2021 | Jun 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPI23D | Brooklyn CPI Engineering Services FY'23 | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPI23D | Brooklyn CPI Engineering Services FY'23 | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPI23D | Brooklyn CPI Engineering Services FY'23 | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPI23D | Brooklyn CPI Engineering Services FY'23 | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPI23D | Brooklyn CPI Engineering Services FY'23 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Jun 2028 | Sep 2025 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIBN2 | CPI PH1- J. Owens, Stockton & Stroud PRB RC BG-815M | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Sep 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIBN2 | CPI PH1- J. Owens, Stockton & Stroud PRB RC BG-815M | 2 | DESIGN | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIBN2 | CPI PH1- J. Owens, Stockton & Stroud PRB RC BG-815M | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2014 | Mar 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIBN2 | CPI PH1- J. Owens, Stockton & Stroud PRB RC BG-815M | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIBN2 | CPI PH1- J. Owens, Stockton & Stroud PRB RC BG-815M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2016 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIBPG | CPI PH2 - Bartlett Playground B286-218M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIBPG | CPI PH2 - Bartlett Playground B286-218M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIBPG | CPI PH2 - Bartlett Playground B286-218M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIBPG | CPI PH2 - Bartlett Playground B286-218M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIBPG | CPI PH2 - Bartlett Playground B286-218M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPICWC | Carter Woodson Children s Park Reconstruction | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPICWC | Carter Woodson Children s Park Reconstruction | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPICWC | Carter Woodson Children s Park Reconstruction | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPICWC | Carter Woodson Children s Park Reconstruction | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPICWC | Carter Woodson Children s Park Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2029 | Nov 2026 | Nov 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIDMC | D'Emic Playground (B210B) | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIDMC | D'Emic Playground (B210B) | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIDMC | D'Emic Playground (B210B) | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIDMC | D'Emic Playground (B210B) | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIDMC | D'Emic Playground (B210B) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIEPP | CPI PH2 - R/C Epiphany Playground (B405 -116M) | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIEPP | CPI PH2 - R/C Epiphany Playground (B405 -116M) | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIEPP | CPI PH2 - R/C Epiphany Playground (B405 -116M) | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIEPP | CPI PH2 - R/C Epiphany Playground (B405 -116M) | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIEPP | CPI PH2 - R/C Epiphany Playground (B405 -116M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Mar 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIGPP | Gonzalo Plasencia Playground Reconstruction | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIGPP | Gonzalo Plasencia Playground Reconstruction | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIGPP | Gonzalo Plasencia Playground Reconstruction | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIGPP | Gonzalo Plasencia Playground Reconstruction | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIGPP | Gonzalo Plasencia Playground Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2029 | Nov 2026 | Nov 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIHCP | Hattie Carthan Playgroound Reconstruction | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIHCP | Hattie Carthan Playgroound Reconstruction | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIHCP | Hattie Carthan Playgroound Reconstruction | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIHCP | Hattie Carthan Playgroound Reconstruction | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIHCP | Hattie Carthan Playgroound Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2031 | Nov 2026 | Nov 2031
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIJCS | CPI- Jerome Playground Public Rest Room Reconstruction | 1 | DEVELOP SCOPE | Apr 2024 | Oct 2024 | Apr 2024 | Oct 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIJCS | CPI- Jerome Playground Public Rest Room Reconstruction | 2 | DESIGN | Oct 2024 | Oct 2025 | Oct 2024 | Oct 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIJCS | CPI- Jerome Playground Public Rest Room Reconstruction | 3 | BID/ REGISTER CONTRACT | Oct 2025 | Jul 2026 | Oct 2025 | Jul 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIJCS | CPI- Jerome Playground Public Rest Room Reconstruction | 4 | CONSTRUCTION | Jul 2026 | Jul 2027 | Jul 2026 | Jul 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIJCS | CPI- Jerome Playground Public Rest Room Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2027 | Jun 2029 | Jul 2027 | Jun 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIJRM | CPI - JEROME PLGD | 1 | DEVELOP SCOPE | Jun 2022 | Nov 2022 | Jun 2022 | Nov 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIJRM | CPI - JEROME PLGD | 2 | DESIGN | Nov 2022 | Nov 2023 | Nov 2022 | Nov 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIJRM | CPI - JEROME PLGD | 3 | BID/ REGISTER CONTRACT | Nov 2023 | Aug 2024 | Nov 2023 | Aug 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIJRM | CPI - JEROME PLGD | 4 | CONSTRUCTION | Aug 2024 | Aug 2025 | Aug 2024 | Aug 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIJRM | CPI - JEROME PLGD | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2025 | Aug 2026 | Aug 2025 | Jun 2031
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILAG | CPI ph2. - LaGuardia Playground Ph 2. (B167-217M) | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILAG | CPI ph2. - LaGuardia Playground Ph 2. (B167-217M) | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILAG | CPI ph2. - LaGuardia Playground Ph 2. (B167-217M) | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILAG | CPI ph2. - LaGuardia Playground Ph 2. (B167-217M) | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILAG | CPI ph2. - LaGuardia Playground Ph 2. (B167-217M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILIP | Livonia Park Reconstruction B367 | 1 | DEVELOP SCOPE | Oct 2023 | Apr 2024 | Oct 2023 | Apr 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILIP | Livonia Park Reconstruction B367 | 2 | DESIGN | Apr 2024 | Apr 2025 | Apr 2024 | Apr 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILIP | Livonia Park Reconstruction B367 | 3 | BID/ REGISTER CONTRACT | Apr 2025 | Jan 2026 | Apr 2025 | Jan 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILIP | Livonia Park Reconstruction B367 | 4 | CONSTRUCTION | Jan 2026 | Jan 2027 | Jan 2026 | Jan 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILIP | Livonia Park Reconstruction B367 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2027 | Jun 2031 | Jan 2027 | Jun 2031
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILWS | CPI Phase 2 - Lewis Playground B430-118MA1 | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2021 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILWS | CPI Phase 2 - Lewis Playground B430-118MA1 | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILWS | CPI Phase 2 - Lewis Playground B430-118MA1 | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILWS | CPI Phase 2 - Lewis Playground B430-118MA1 | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILWS | CPI Phase 2 - Lewis Playground B430-118MA1 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIPHP | CPI - Pena Herrera Playground B210J-123M | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIPHP | CPI - Pena Herrera Playground B210J-123M | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIPHP | CPI - Pena Herrera Playground B210J-123M | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIPHP | CPI - Pena Herrera Playground B210J-123M | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIPHP | CPI - Pena Herrera Playground B210J-123M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Jun 2028 | Sep 2025 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIRHP | CPI - Rolph Henry Playground, Brooklyn | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIRHP | CPI - Rolph Henry Playground, Brooklyn | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIRHP | CPI - Rolph Henry Playground, Brooklyn | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIRHP | CPI - Rolph Henry Playground, Brooklyn | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIRHP | CPI - Rolph Henry Playground, Brooklyn | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Jun 2029 | Sep 2025 | Jun 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPISMP | St. Marks Playground Reconstruction | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPISMP | St. Marks Playground Reconstruction | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPISMP | St. Marks Playground Reconstruction | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPISMP | St. Marks Playground Reconstruction | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPISMP | St. Marks Playground Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2029 | Nov 2026 | Nov 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2DSTG01 | LEIF ERICSON PARK- DESTINATION GREENWAYS B052-123M | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2DSTG01 | LEIF ERICSON PARK- DESTINATION GREENWAYS B052-123M | 2 | DESIGN | Dec 2022 | Jun 2024 | Dec 2022 | Jun 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2DSTG01 | LEIF ERICSON PARK- DESTINATION GREENWAYS B052-123M | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2DSTG01 | LEIF ERICSON PARK- DESTINATION GREENWAYS B052-123M | 4 | CONSTRUCTION | Mar 2025 | Sep 2026 | Mar 2025 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2DSTG01 | LEIF ERICSON PARK- DESTINATION GREENWAYS B052-123M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2DSTG03 | AMER VET. MEM PIER VERRAZZANO BRDG B082-123M | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2DSTG03 | AMER VET. MEM PIER VERRAZZANO BRDG B082-123M | 2 | DESIGN | Dec 2022 | Jun 2024 | Dec 2022 | Jun 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2DSTG03 | AMER VET. MEM PIER VERRAZZANO BRDG B082-123M | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2DSTG03 | AMER VET. MEM PIER VERRAZZANO BRDG B082-123M | 4 | CONSTRUCTION | Mar 2025 | Sep 2026 | Mar 2025 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2DSTG03 | AMER VET. MEM PIER VERRAZZANO BRDG B082-123M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2DSTG04 | UNDER VERRAZZANO NARROWS BRDG B082-223M | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2DSTG04 | UNDER VERRAZZANO NARROWS BRDG B082-223M | 2 | DESIGN | Dec 2022 | Jun 2024 | Dec 2022 | Jun 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2DSTG04 | UNDER VERRAZZANO NARROWS BRDG B082-223M | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2DSTG04 | UNDER VERRAZZANO NARROWS BRDG B082-223M | 4 | CONSTRUCTION | Mar 2025 | Sep 2026 | Mar 2025 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2DSTG04 | UNDER VERRAZZANO NARROWS BRDG B082-223M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2FGCSUP | FORT GREENE PARK-PRB UPGRADES | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2025 | Dec 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2FGCSUP | FORT GREENE PARK-PRB UPGRADES | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2025 | Dec 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2FGCSUP | FORT GREENE PARK-PRB UPGRADES | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2026 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2FGCSUP | FORT GREENE PARK-PRB UPGRADES | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2027 | Sep 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2FGCSUP | FORT GREENE PARK-PRB UPGRADES | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2028 | Dec 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2FRNDFN | Recon fence at Friends Field Park | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2FRNDFN | Recon fence at Friends Field Park | 2 | DESIGN | Sep 2023 | Mar 2025 | Sep 2023 | Mar 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2FRNDFN | Recon fence at Friends Field Park | 3 | BID/ REGISTER CONTRACT | Mar 2025 | Dec 2025 | Mar 2025 | Dec 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2FRNDFN | Recon fence at Friends Field Park | 4 | CONSTRUCTION | Dec 2025 | Jun 2027 | Dec 2025 | Jun 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2FRNDFN | Recon fence at Friends Field Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2027 | Jun 2028 | Jun 2027 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2FULTON | Fulton Mall Streetscape Improvements | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2FULTON | Fulton Mall Streetscape Improvements | 2 | DESIGN | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2FULTON | Fulton Mall Streetscape Improvements | 3 | BID/ REGISTER CONTRACT | Sep 2024 | Jun 2025 | Sep 2024 | Jun 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2FULTON | Fulton Mall Streetscape Improvements | 4 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2FULTON | Fulton Mall Streetscape Improvements | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Jun 2027 | Jun 2026 | Jun 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATE10 | Gateway Estates-Multi-purpose ballfield B548-118M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATE10 | Gateway Estates-Multi-purpose ballfield B548-118M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATE10 | Gateway Estates-Multi-purpose ballfield B548-118M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATE10 | Gateway Estates-Multi-purpose ballfield B548-118M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATE10 | Gateway Estates-Multi-purpose ballfield B548-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATE12 | Gateway Estates Park Construction Phase 3 | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATE12 | Gateway Estates Park Construction Phase 3 | 2 | DESIGN | Dec 2021 | Jun 2023 | Dec 2021 | Jun 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATE12 | Gateway Estates Park Construction Phase 3 | 3 | BID/ REGISTER CONTRACT | Jun 2023 | Mar 2024 | Jun 2023 | Mar 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATE12 | Gateway Estates Park Construction Phase 3 | 4 | CONSTRUCTION | Mar 2024 | Sep 2025 | Mar 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATE12 | Gateway Estates Park Construction Phase 3 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATEW6 | Gateway Estates -Cleveland Pk playground (B547- 114M) | 1 | DEVELOP SCOPE | Aug 2013 | Nov 2013 | Aug 2013 | Nov 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATEW6 | Gateway Estates -Cleveland Pk playground (B547- 114M) | 2 | DESIGN | Nov 2013 | Feb 2014 | Nov 2013 | Feb 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATEW6 | Gateway Estates -Cleveland Pk playground (B547- 114M) | 3 | BID/ REGISTER CONTRACT | Feb 2014 | May 2014 | Feb 2014 | May 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATEW6 | Gateway Estates -Cleveland Pk playground (B547- 114M) | 4 | CONSTRUCTION | May 2014 | May 2015 | May 2014 | May 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATEW6 | Gateway Estates -Cleveland Pk playground (B547- 114M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | May 2015 | May 2016 | May 2015 | Sep 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWB12 | GPWB - Bushwick Inlet Park Site Connection Construction | 1 | DEVELOP SCOPE | Jan 2023 | Jun 2023 | Jan 2023 | Jun 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWB12 | GPWB - Bushwick Inlet Park Site Connection Construction | 2 | DESIGN | Jun 2023 | Jun 2024 | Jun 2023 | Jun 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWB12 | GPWB - Bushwick Inlet Park Site Connection Construction | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWB12 | GPWB - Bushwick Inlet Park Site Connection Construction | 4 | CONSTRUCTION | Mar 2025 | Mar 2026 | Mar 2025 | Mar 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWB12 | GPWB - Bushwick Inlet Park Site Connection Construction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Mar 2027 | Mar 2026 | Mar 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWB25 | GPWB-Bushwick Inlet Park-Motiva Parcel Remediation B529-119M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWB25 | GPWB-Bushwick Inlet Park-Motiva Parcel Remediation B529-119M | 2 | DESIGN | Dec 2017 | Mar 2019 | Dec 2017 | Mar 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWB25 | GPWB-Bushwick Inlet Park-Motiva Parcel Remediation B529-119M | 3 | BID/ REGISTER CONTRACT | Mar 2019 | Dec 2019 | Mar 2019 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWB25 | GPWB-Bushwick Inlet Park-Motiva Parcel Remediation B529-119M | 4 | CONSTRUCTION | Dec 2019 | Dec 2021 | Dec 2019 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWB25 | GPWB-Bushwick Inlet Park-Motiva Parcel Remediation B529-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWBKT | GPWB- 50 Kent Development B529-118M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWBKT | GPWB- 50 Kent Development B529-118M | 2 | DESIGN | Dec 2017 | Mar 2019 | Dec 2017 | Mar 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWBKT | GPWB- 50 Kent Development B529-118M | 3 | BID/ REGISTER CONTRACT | Mar 2019 | Dec 2019 | Mar 2019 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWBKT | GPWB- 50 Kent Development B529-118M | 4 | CONSTRUCTION | Dec 2019 | Dec 2021 | Dec 2019 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWBKT | GPWB- 50 Kent Development B529-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWBPC | FY'22 Bushwick Inlet - Park Creation | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWBPC | FY'22 Bushwick Inlet - Park Creation | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWBPC | FY'22 Bushwick Inlet - Park Creation | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWBPC | FY'22 Bushwick Inlet - Park Creation | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWBPC | FY'22 Bushwick Inlet - Park Creation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GRNTHB | Green Thumb Irrigation systems (Brooklyn) | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GRNTHB | Green Thumb Irrigation systems (Brooklyn) | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Jun 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GRNTHB | Green Thumb Irrigation systems (Brooklyn) | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Jun 2023 | Mar 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GRNTHB | Green Thumb Irrigation systems (Brooklyn) | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Mar 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GRNTHB | Green Thumb Irrigation systems (Brooklyn) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2025 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GRNTHB | Green Thumb Irrigation systems (Brooklyn) | 6 | DEVELOP SCOPE | Sep 2025 | Mar 2026 | Sep 2025 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GRNTHB | Green Thumb Irrigation systems (Brooklyn) | 7 | DESIGN | Mar 2026 | Sep 2027 | Sep 2025 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GRNTHB | Green Thumb Irrigation systems (Brooklyn) | 8 | BID/ REGISTER CONTRACT | Sep 2027 | Jun 2028 | Sep 2025 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GRNTHB | Green Thumb Irrigation systems (Brooklyn) | 9 | CONSTRUCTION | Jun 2028 | Dec 2029 | Sep 2025 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GRNTHB | Green Thumb Irrigation systems (Brooklyn) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2029 | Dec 2030 | Sep 2025 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GRST01 | Greenstreets - Brooklyn Tree Planting & Greenstreets | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GRST01 | Greenstreets - Brooklyn Tree Planting & Greenstreets | 2 | DESIGN | Dec 2020 | Jun 2022 | Dec 2020 | Jun 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GRST01 | Greenstreets - Brooklyn Tree Planting & Greenstreets | 3 | BID/ REGISTER CONTRACT | Jun 2022 | Mar 2023 | Jun 2022 | Mar 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GRST01 | Greenstreets - Brooklyn Tree Planting & Greenstreets | 4 | CONSTRUCTION | Mar 2023 | Mar 2025 | Mar 2023 | Mar 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GRST01 | Greenstreets - Brooklyn Tree Planting & Greenstreets | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Mar 2027 | Mar 2025 | Mar 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GTGRDN | RPZ installation at various sites in Brooklyn BG-618M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GTGRDN | RPZ installation at various sites in Brooklyn BG-618M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GTGRDN | RPZ installation at various sites in Brooklyn BG-618M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GTGRDN | RPZ installation at various sites in Brooklyn BG-618M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GTGRDN | RPZ installation at various sites in Brooklyn BG-618M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GTGRDN | RPZ installation at various sites in Brooklyn BG-618M | 6 | DEVELOP SCOPE | Sep 2021 | Mar 2022 | Sep 2020 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GTGRDN | RPZ installation at various sites in Brooklyn BG-618M | 7 | DESIGN | Mar 2022 | Mar 2023 | Sep 2020 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GTGRDN | RPZ installation at various sites in Brooklyn BG-618M | 8 | BID/ REGISTER CONTRACT | Mar 2023 | Dec 2023 | Sep 2020 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GTGRDN | RPZ installation at various sites in Brooklyn BG-618M | 9 | CONSTRUCTION | Dec 2023 | Dec 2024 | Sep 2020 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GTGRDN | RPZ installation at various sites in Brooklyn BG-618M | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2024 | Dec 2025 | Sep 2020 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2HWRDPL | HOWARD POOL CNYG-918MA1 | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2HWRDPL | HOWARD POOL CNYG-918MA1 | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2HWRDPL | HOWARD POOL CNYG-918MA1 | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2HWRDPL | HOWARD POOL CNYG-918MA1 | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2HWRDPL | HOWARD POOL CNYG-918MA1 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2JRCOUR | NYC PARKS - JACKIE ROBINSON PARK: RECONSTRUCT 2 FULL COURT | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2JRCOUR | NYC PARKS - JACKIE ROBINSON PARK: RECONSTRUCT 2 FULL COURT | 2 | DESIGN | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2JRCOUR | NYC PARKS - JACKIE ROBINSON PARK: RECONSTRUCT 2 FULL COURT | 3 | BID/ REGISTER CONTRACT | Sep 2024 | Jun 2025 | Sep 2024 | Jun 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2JRCOUR | NYC PARKS - JACKIE ROBINSON PARK: RECONSTRUCT 2 FULL COURT | 4 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2JRCOUR | NYC PARKS - JACKIE ROBINSON PARK: RECONSTRUCT 2 FULL COURT | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Jun 2027 | Jun 2026 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2LITCHF | PPA - Litchfield Villa Renovations B073-120M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2LITCHF | PPA - Litchfield Villa Renovations B073-120M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2LITCHF | PPA - Litchfield Villa Renovations B073-120M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2LITCHF | PPA - Litchfield Villa Renovations B073-120M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2LITCHF | PPA - Litchfield Villa Renovations B073-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2LNCON | NYC PARKS - LINCOLN ROAD PLAYGROUND: RESTORATION OF LINCOLN | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2LNCON | NYC PARKS - LINCOLN ROAD PLAYGROUND: RESTORATION OF LINCOLN | 2 | DESIGN | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2LNCON | NYC PARKS - LINCOLN ROAD PLAYGROUND: RESTORATION OF LINCOLN | 3 | BID/ REGISTER CONTRACT | Sep 2024 | Jun 2025 | Sep 2024 | Jun 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2LNCON | NYC PARKS - LINCOLN ROAD PLAYGROUND: RESTORATION OF LINCOLN | 4 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2LNCON | NYC PARKS - LINCOLN ROAD PLAYGROUND: RESTORATION OF LINCOLN | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Jun 2027 | Jun 2026 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2MCTURF | NYC PARKS - MCCARREN PARK : CONVERT ASPHALT FIELD TO SYNTHE | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2MCTURF | NYC PARKS - MCCARREN PARK : CONVERT ASPHALT FIELD TO SYNTHE | 2 | DESIGN | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2MCTURF | NYC PARKS - MCCARREN PARK : CONVERT ASPHALT FIELD TO SYNTHE | 3 | BID/ REGISTER CONTRACT | Sep 2024 | Jun 2025 | Sep 2024 | Jun 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2MCTURF | NYC PARKS - MCCARREN PARK : CONVERT ASPHALT FIELD TO SYNTHE | 4 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2MCTURF | NYC PARKS - MCCARREN PARK : CONVERT ASPHALT FIELD TO SYNTHE | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Jun 2027 | Jun 2026 | Jun 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2MTFLTR | Citywide Indoor Pool Filter Plant RC-CNYG-4622M | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2MTFLTR | Citywide Indoor Pool Filter Plant RC-CNYG-4622M | 2 | DESIGN | Dec 2021 | Jun 2023 | Dec 2021 | Jun 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2MTFLTR | Citywide Indoor Pool Filter Plant RC-CNYG-4622M | 3 | BID/ REGISTER CONTRACT | Jun 2023 | Mar 2024 | Jun 2023 | Mar 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2MTFLTR | Citywide Indoor Pool Filter Plant RC-CNYG-4622M | 4 | CONSTRUCTION | Mar 2024 | Sep 2025 | Mar 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2MTFLTR | Citywide Indoor Pool Filter Plant RC-CNYG-4622M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PDBRC2 | Brownsville Rec Ctr RC B270-214M | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Sep 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PDBRC2 | Brownsville Rec Ctr RC B270-214M | 2 | DESIGN | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PDBRC2 | Brownsville Rec Ctr RC B270-214M | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2014 | Mar 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PDBRC2 | Brownsville Rec Ctr RC B270-214M | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PDBRC2 | Brownsville Rec Ctr RC B270-214M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2016 | Jun 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PDSSRC | Sunset Pk Rec Ctr RC B087-115M | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Sep 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PDSSRC | Sunset Pk Rec Ctr RC B087-115M | 2 | DESIGN | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PDSSRC | Sunset Pk Rec Ctr RC B087-115M | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2014 | Mar 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PDSSRC | Sunset Pk Rec Ctr RC B087-115M | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PDSSRC | Sunset Pk Rec Ctr RC B087-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PEPWIN | Prospect Park Parade Ground PEP HQ window replace CNYG-2819M | 2 | DESIGN | Dec 2019 | Dec 2021 | Dec 2019 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PEPWIN | Prospect Park Parade Ground PEP HQ window replace CNYG-2819M | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PEPWIN | Prospect Park Parade Ground PEP HQ window replace CNYG-2819M | 4 | CONSTRUCTION | Sep 2022 | Sep 2024 | Sep 2022 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PEPWIN | Prospect Park Parade Ground PEP HQ window replace CNYG-2819M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PGRD11 | MULTISITE- PAVEMTS,TENNIS CTS, BB CTS, FENCING (BG-711M) | 1 | DEVELOP SCOPE | Jan 2012 | Mar 2012 | Jan 2012 | Mar 2012
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PGRD11 | MULTISITE- PAVEMTS,TENNIS CTS, BB CTS, FENCING (BG-711M) | 2 | DESIGN | Mar 2012 | Jun 2012 | Mar 2012 | Jun 2012
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PGRD11 | MULTISITE- PAVEMTS,TENNIS CTS, BB CTS, FENCING (BG-711M) | 3 | BID/ REGISTER CONTRACT | Jun 2012 | Sep 2012 | Jun 2012 | Sep 2012
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PGRD11 | MULTISITE- PAVEMTS,TENNIS CTS, BB CTS, FENCING (BG-711M) | 4 | CONSTRUCTION | Sep 2012 | Sep 2013 | Sep 2012 | Sep 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PGRD11 | MULTISITE- PAVEMTS,TENNIS CTS, BB CTS, FENCING (BG-711M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2013 | Sep 2014 | Sep 2013 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PKTR23 | Brooklyn Park Tree Planting FY23 BG-223M | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PKTR23 | Brooklyn Park Tree Planting FY23 BG-223M | 2 | DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PKTR23 | Brooklyn Park Tree Planting FY23 BG-223M | 3 | BID/ REGISTER CONTRACT | Jun 2023 | Mar 2024 | Jun 2023 | Mar 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PKTR23 | Brooklyn Park Tree Planting FY23 BG-223M | 4 | CONSTRUCTION | Mar 2024 | Sep 2025 | Mar 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PKTR23 | Brooklyn Park Tree Planting FY23 BG-223M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLAY13 | MULTISITE- OCEAN HILL PLGD, WINGATE, MLK SPRAY SHWER BG-114M | 1 | DEVELOP SCOPE | Feb 2013 | May 2013 | Feb 2013 | May 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLAY13 | MULTISITE- OCEAN HILL PLGD, WINGATE, MLK SPRAY SHWER BG-114M | 2 | DESIGN | May 2013 | Jul 2013 | May 2013 | Jul 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLAY13 | MULTISITE- OCEAN HILL PLGD, WINGATE, MLK SPRAY SHWER BG-114M | 3 | BID/ REGISTER CONTRACT | Jul 2013 | Oct 2013 | Jul 2013 | Oct 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLAY13 | MULTISITE- OCEAN HILL PLGD, WINGATE, MLK SPRAY SHWER BG-114M | 4 | CONSTRUCTION | Oct 2013 | Oct 2014 | Oct 2013 | Oct 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLAY13 | MULTISITE- OCEAN HILL PLGD, WINGATE, MLK SPRAY SHWER BG-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2014 | Oct 2015 | Oct 2014 | Oct 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG13A | RECON. FENCING & GEN. SITEWORK-RAPPAPORT HOCKEY RINK-BG311M | 1 | DEVELOP SCOPE | Feb 2013 | May 2013 | Feb 2013 | May 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG13A | RECON. FENCING & GEN. SITEWORK-RAPPAPORT HOCKEY RINK-BG311M | 2 | DESIGN | May 2013 | Jul 2013 | May 2013 | Jul 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG13A | RECON. FENCING & GEN. SITEWORK-RAPPAPORT HOCKEY RINK-BG311M | 3 | BID/ REGISTER CONTRACT | Jul 2013 | Oct 2013 | Jul 2013 | Oct 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG13A | RECON. FENCING & GEN. SITEWORK-RAPPAPORT HOCKEY RINK-BG311M | 4 | CONSTRUCTION | Oct 2013 | Oct 2014 | Oct 2013 | Oct 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG13A | RECON. FENCING & GEN. SITEWORK-RAPPAPORT HOCKEY RINK-BG311M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2014 | Oct 2015 | Oct 2014 | Oct 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PNYC01 | PlaNYC - McCarren Pk Pool & Bathhouse RC - B058-108M/408M | 1 | DEVELOP SCOPE | Jul 2007 | Sep 2007 | Oct 2006 | Jan 2007
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PNYC01 | PlaNYC - McCarren Pk Pool & Bathhouse RC - B058-108M/408M | 2 | DESIGN | Sep 2007 | Dec 2007 | Jan 2007 | Apr 2007
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PNYC01 | PlaNYC - McCarren Pk Pool & Bathhouse RC - B058-108M/408M | 3 | BID/ REGISTER CONTRACT | Dec 2007 | Mar 2008 | Apr 2007 | Jun 2007
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PNYC01 | PlaNYC - McCarren Pk Pool & Bathhouse RC - B058-108M/408M | 4 | CONSTRUCTION | Mar 2008 | Mar 2009 | Jul 2007 | Jun 2008
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PNYC01 | PlaNYC - McCarren Pk Pool & Bathhouse RC - B058-108M/408M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2009 | Mar 2010 | Jun 2008 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PNYC05 | PlaNYC - Calvert Vaux PRB/M&O bldg (B125-112M) | 1 | DEVELOP SCOPE | Mar 2012 | May 2012 | Mar 2012 | May 2012
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PNYC05 | PlaNYC - Calvert Vaux PRB/M&O bldg (B125-112M) | 2 | DESIGN | May 2012 | Aug 2012 | Sep 2015 | Mar 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PNYC05 | PlaNYC - Calvert Vaux PRB/M&O bldg (B125-112M) | 3 | BID/ REGISTER CONTRACT | Aug 2012 | Nov 2012 | Apr 2016 | Jun 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PNYC05 | PlaNYC - Calvert Vaux PRB/M&O bldg (B125-112M) | 4 | CONSTRUCTION | Nov 2012 | Nov 2013 | Jul 2016 | Jun 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PNYC05 | PlaNYC - Calvert Vaux PRB/M&O bldg (B125-112M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2013 | Nov 2014 | Jul 2017 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PPESIT | Ocean Parkway Sitting Areas Reconstruction BG-121M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PPESIT | Ocean Parkway Sitting Areas Reconstruction BG-121M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PPESIT | Ocean Parkway Sitting Areas Reconstruction BG-121M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PPESIT | Ocean Parkway Sitting Areas Reconstruction BG-121M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PPESIT | Ocean Parkway Sitting Areas Reconstruction BG-121M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PVMNRO | Recon Canarsie Park - Monroe Cohen sidewalks | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PVMNRO | Recon Canarsie Park - Monroe Cohen sidewalks | 2 | DESIGN | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PVMNRO | Recon Canarsie Park - Monroe Cohen sidewalks | 3 | BID/ REGISTER CONTRACT | Sep 2024 | Jun 2025 | Sep 2024 | Jun 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PVMNRO | Recon Canarsie Park - Monroe Cohen sidewalks | 4 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PVMNRO | Recon Canarsie Park - Monroe Cohen sidewalks | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Jun 2027 | Jun 2026 | Jun 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PWBFTG | PWOB- Fort Greene (B032-117M) | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PWBFTG | PWOB- Fort Greene (B032-117M) | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PWBFTG | PWOB- Fort Greene (B032-117M) | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PWBFTG | PWOB- Fort Greene (B032-117M) | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PWBFTG | PWOB- Fort Greene (B032-117M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PWBPFB | PWOB- PP Flatbush Avenue (B073-117M) | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2006 | Sep 2006
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PWBPFB | PWOB- PP Flatbush Avenue (B073-117M) | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PWBPFB | PWOB- PP Flatbush Avenue (B073-117M) | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PWBPFB | PWOB- PP Flatbush Avenue (B073-117M) | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PWBPFB | PWOB- PP Flatbush Avenue (B073-117M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2019 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PWPADT | Power Memorial Plgd. Phase 2 Reconstruction | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PWPADT | Power Memorial Plgd. Phase 2 Reconstruction | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PWPADT | Power Memorial Plgd. Phase 2 Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PWPADT | Power Memorial Plgd. Phase 2 Reconstruction | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PWPADT | Power Memorial Plgd. Phase 2 Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2RHBALL | Red Hook Recreation Area Ballfields 5-8 Recon. B126-116M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2RHBALL | Red Hook Recreation Area Ballfields 5-8 Recon. B126-116M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2RHBALL | Red Hook Recreation Area Ballfields 5-8 Recon. B126-116M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2RHBALL | Red Hook Recreation Area Ballfields 5-8 Recon. B126-116M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2RHBALL | Red Hook Recreation Area Ballfields 5-8 Recon. B126-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SEAGTE | SEAGATE SHORELINE REMEDIATION | 1 | DEVELOP SCOPE | Jul 2011 | Sep 2011 | Jul 2011 | Sep 2011
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SEAGTE | SEAGATE SHORELINE REMEDIATION | 2 | DESIGN | Sep 2011 | Dec 2011 | Sep 2011 | Dec 2011
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SEAGTE | SEAGATE SHORELINE REMEDIATION | 3 | BID/ REGISTER CONTRACT | Dec 2011 | Mar 2012 | Dec 2011 | Mar 2012
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SEAGTE | SEAGATE SHORELINE REMEDIATION | 4 | CONSTRUCTION | Mar 2012 | Mar 2013 | Mar 2012 | Mar 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SEAGTE | SEAGATE SHORELINE REMEDIATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2013 | Mar 2014 | Mar 2013 | Jun 2031
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SHORTR | Tree Planting Shore Parkway | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SHORTR | Tree Planting Shore Parkway | 2 | DESIGN | Dec 2022 | Jun 2024 | Dec 2022 | Jun 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SHORTR | Tree Planting Shore Parkway | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SHORTR | Tree Planting Shore Parkway | 4 | CONSTRUCTION | Mar 2025 | Sep 2026 | Mar 2025 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SHORTR | Tree Planting Shore Parkway | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SNSTRW | Commodore Barry Park PRB | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SNSTRW | Commodore Barry Park PRB | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SNSTRW | Commodore Barry Park PRB | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SNSTRW | Commodore Barry Park PRB | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SNSTRW | Commodore Barry Park PRB | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SPC21A | Marine Park Forest Restoration | 1 | DEVELOP SCOPE | Jun 2023 | Dec 2023 | Jun 2023 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SPC21A | Marine Park Forest Restoration | 2 | DESIGN | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SPC21A | Marine Park Forest Restoration | 3 | BID/ REGISTER CONTRACT | Sep 2024 | Jun 2025 | Sep 2024 | Jun 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SPC21A | Marine Park Forest Restoration | 4 | CONSTRUCTION | Jun 2025 | Dec 2027 | Jun 2025 | Dec 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SPC21A | Marine Park Forest Restoration | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2027 | Dec 2029 | Dec 2027 | Dec 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFBSH | Synthetic Turf Field Reconstruction at Bushwick Inlet Pk, BK | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Apr 2021 | Oct 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFBSH | Synthetic Turf Field Reconstruction at Bushwick Inlet Pk, BK | 2 | DESIGN | Dec 2019 | Dec 2020 | Oct 2021 | Oct 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFBSH | Synthetic Turf Field Reconstruction at Bushwick Inlet Pk, BK | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Oct 2022 | Jul 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFBSH | Synthetic Turf Field Reconstruction at Bushwick Inlet Pk, BK | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Jul 2023 | Jun 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFBSH | Synthetic Turf Field Reconstruction at Bushwick Inlet Pk, BK | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Jul 2024 | Jun 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFLEF | Synthetic Turf Field Recon at Quaker Parrot Pk, BK | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFLEF | Synthetic Turf Field Recon at Quaker Parrot Pk, BK | 2 | DESIGN | Dec 2019 | Dec 2020 | Oct 2022 | Oct 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFLEF | Synthetic Turf Field Recon at Quaker Parrot Pk, BK | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Oct 2023 | Jun 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFLEF | Synthetic Turf Field Recon at Quaker Parrot Pk, BK | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Jul 2024 | Jun 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFLEF | Synthetic Turf Field Recon at Quaker Parrot Pk, BK | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Jul 2025 | Jun 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFMH | Maria Hernandez Park - Synthetic Turf Field (B016-118M) | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFMH | Maria Hernandez Park - Synthetic Turf Field (B016-118M) | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFMH | Maria Hernandez Park - Synthetic Turf Field (B016-118M) | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFMH | Maria Hernandez Park - Synthetic Turf Field (B016-118M) | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFMH | Maria Hernandez Park - Synthetic Turf Field (B016-118M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STJNRF | St. John's Recreation Roof Reconstruction | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STJNRF | St. John's Recreation Roof Reconstruction | 2 | DESIGN | Sep 2023 | Sep 2025 | Sep 2023 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STJNRF | St. John's Recreation Roof Reconstruction | 3 | BID/ REGISTER CONTRACT | Sep 2025 | Jun 2026 | Sep 2025 | Jun 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STJNRF | St. John's Recreation Roof Reconstruction | 4 | CONSTRUCTION | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STJNRF | St. John's Recreation Roof Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2028 | Jun 2030 | Jun 2028 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SUCSGN | Success Garden - Park Renovation B383-119M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SUCSGN | Success Garden - Park Renovation B383-119M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SUCSGN | Success Garden - Park Renovation B383-119M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SUCSGN | Success Garden - Park Renovation B383-119M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SUCSGN | Success Garden - Park Renovation B383-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE16B | FY16 Street Trees Brooklyn 11,13,14,15,18, BG-1315M | 1 | DEVELOP SCOPE | Apr 2015 | Jun 2015 | Apr 2015 | Jun 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE16B | FY16 Street Trees Brooklyn 11,13,14,15,18, BG-1315M | 2 | DESIGN | Jun 2015 | Sep 2015 | Jun 2015 | Sep 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE16B | FY16 Street Trees Brooklyn 11,13,14,15,18, BG-1315M | 3 | BID/ REGISTER CONTRACT | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE16B | FY16 Street Trees Brooklyn 11,13,14,15,18, BG-1315M | 4 | CONSTRUCTION | Dec 2015 | Dec 2016 | Dec 2015 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE16B | FY16 Street Trees Brooklyn 11,13,14,15,18, BG-1315M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2016 | Dec 2017 | Dec 2016 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE17C | FY17 Street Tree Brooklyn1,11,13,15 BG- | 2 | DESIGN | Dec 2016 | Jun 2017 | Dec 2016 | Jun 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE17C | FY17 Street Tree Brooklyn1,11,13,15 BG- | 3 | BID/ REGISTER CONTRACT | Jun 2017 | Mar 2018 | Jun 2017 | Mar 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE17C | FY17 Street Tree Brooklyn1,11,13,15 BG- | 4 | CONSTRUCTION | Mar 2018 | Sep 2019 | Mar 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE17C | FY17 Street Tree Brooklyn1,11,13,15 BG- | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2021 | Sep 2019 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE23A | FY23 Street Trees BK CB's 5 & 16 | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE23A | FY23 Street Trees BK CB's 5 & 16 | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE23A | FY23 Street Trees BK CB's 5 & 16 | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE23A | FY23 Street Trees BK CB's 5 & 16 | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE23A | FY23 Street Trees BK CB's 5 & 16 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE23C | Brooklyn CB 3 & 4 Street Tree Planting FY24 | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE23C | Brooklyn CB 3 & 4 Street Tree Planting FY24 | 2 | DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE23C | Brooklyn CB 3 & 4 Street Tree Planting FY24 | 3 | BID/ REGISTER CONTRACT | Jun 2023 | Mar 2024 | Jun 2023 | Mar 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE23C | Brooklyn CB 3 & 4 Street Tree Planting FY24 | 4 | CONSTRUCTION | Mar 2024 | Sep 2025 | Mar 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE23C | Brooklyn CB 3 & 4 Street Tree Planting FY24 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE23D | Brooklyn CB 7 & 10 Street Tree Planting FY23 | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE23D | Brooklyn CB 7 & 10 Street Tree Planting FY23 | 2 | DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE23D | Brooklyn CB 7 & 10 Street Tree Planting FY23 | 3 | BID/ REGISTER CONTRACT | Jun 2023 | Mar 2024 | Jun 2023 | Mar 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE23D | Brooklyn CB 7 & 10 Street Tree Planting FY23 | 4 | CONSTRUCTION | Mar 2024 | Sep 2025 | Mar 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE23D | Brooklyn CB 7 & 10 Street Tree Planting FY23 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE23E | Brooklyn CB 1, 2, 6 Street Tree Planting FY23 | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE23E | Brooklyn CB 1, 2, 6 Street Tree Planting FY23 | 2 | DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE23E | Brooklyn CB 1, 2, 6 Street Tree Planting FY23 | 3 | BID/ REGISTER CONTRACT | Jun 2023 | Mar 2024 | Jun 2023 | Mar 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE23E | Brooklyn CB 1, 2, 6 Street Tree Planting FY23 | 4 | CONSTRUCTION | Mar 2024 | Sep 2025 | Mar 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE23E | Brooklyn CB 1, 2, 6 Street Tree Planting FY23 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE23F | Brooklyn CB 12 & 14 Street Tree Planting FY23 | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE23F | Brooklyn CB 12 & 14 Street Tree Planting FY23 | 2 | DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE23F | Brooklyn CB 12 & 14 Street Tree Planting FY23 | 3 | BID/ REGISTER CONTRACT | Jun 2023 | Mar 2024 | Jun 2023 | Mar 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE23F | Brooklyn CB 12 & 14 Street Tree Planting FY23 | 4 | CONSTRUCTION | Mar 2024 | Sep 2025 | Mar 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE23F | Brooklyn CB 12 & 14 Street Tree Planting FY23 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE23G | Brooklyn CB 11, 13, 15 Street Tree Planting FY23 | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE23G | Brooklyn CB 11, 13, 15 Street Tree Planting FY23 | 2 | DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE23G | Brooklyn CB 11, 13, 15 Street Tree Planting FY23 | 3 | BID/ REGISTER CONTRACT | Jun 2023 | Mar 2024 | Jun 2023 | Mar 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE23G | Brooklyn CB 11, 13, 15 Street Tree Planting FY23 | 4 | CONSTRUCTION | Mar 2024 | Sep 2025 | Mar 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE23G | Brooklyn CB 11, 13, 15 Street Tree Planting FY23 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE24B | Brooklyn Street Tree Planting FY24 - Community Board 5 & 16 | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE24B | Brooklyn Street Tree Planting FY24 - Community Board 5 & 16 | 2 | DESIGN | Feb 2024 | Aug 2024 | Feb 2024 | Aug 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE24B | Brooklyn Street Tree Planting FY24 - Community Board 5 & 16 | 3 | BID/ REGISTER CONTRACT | Aug 2024 | May 2025 | Aug 2024 | May 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE24B | Brooklyn Street Tree Planting FY24 - Community Board 5 & 16 | 4 | CONSTRUCTION | May 2025 | Nov 2026 | May 2025 | Nov 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE24B | Brooklyn Street Tree Planting FY24 - Community Board 5 & 16 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2028 | Nov 2026 | Nov 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE24C | Brooklyn Street Tree Planting FY24 - Community Board 7 & 10 | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE24C | Brooklyn Street Tree Planting FY24 - Community Board 7 & 10 | 2 | DESIGN | Feb 2024 | Aug 2024 | Feb 2024 | Aug 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE24C | Brooklyn Street Tree Planting FY24 - Community Board 7 & 10 | 3 | BID/ REGISTER CONTRACT | Aug 2024 | May 2025 | Aug 2024 | May 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE24C | Brooklyn Street Tree Planting FY24 - Community Board 7 & 10 | 4 | CONSTRUCTION | May 2025 | Nov 2026 | May 2025 | Nov 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE24C | Brooklyn Street Tree Planting FY24 - Community Board 7 & 10 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2028 | Nov 2026 | Nov 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE24D | Brooklyn Street Tree Planting FY24 - Community Board 1-4 & 6 | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE24D | Brooklyn Street Tree Planting FY24 - Community Board 1-4 & 6 | 2 | DESIGN | Feb 2024 | Aug 2024 | Feb 2024 | Aug 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE24D | Brooklyn Street Tree Planting FY24 - Community Board 1-4 & 6 | 3 | BID/ REGISTER CONTRACT | Aug 2024 | May 2025 | Aug 2024 | May 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE24D | Brooklyn Street Tree Planting FY24 - Community Board 1-4 & 6 | 4 | CONSTRUCTION | May 2025 | Nov 2026 | May 2025 | Nov 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE24D | Brooklyn Street Tree Planting FY24 - Community Board 1-4 & 6 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2028 | Nov 2026 | Nov 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE24E | Brooklyn Street Tree Planting FY24 - Community Board 12 & 14 | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE24E | Brooklyn Street Tree Planting FY24 - Community Board 12 & 14 | 2 | DESIGN | Feb 2024 | Aug 2024 | Feb 2024 | Aug 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE24E | Brooklyn Street Tree Planting FY24 - Community Board 12 & 14 | 3 | BID/ REGISTER CONTRACT | Aug 2024 | May 2025 | Aug 2024 | May 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE24E | Brooklyn Street Tree Planting FY24 - Community Board 12 & 14 | 4 | CONSTRUCTION | May 2025 | Nov 2026 | May 2025 | Nov 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE24E | Brooklyn Street Tree Planting FY24 - Community Board 12 & 14 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2028 | Nov 2026 | Nov 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TREL21 | FY21 Street Trees BK CB's9,17,18 (3Y)BG-1319M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TREL21 | FY21 Street Trees BK CB's9,17,18 (3Y)BG-1319M | 2 | DESIGN | Dec 2019 | Jun 2021 | Dec 2019 | Jun 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TREL21 | FY21 Street Trees BK CB's9,17,18 (3Y)BG-1319M | 3 | BID/ REGISTER CONTRACT | Jun 2021 | Mar 2022 | Jun 2021 | Mar 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TREL21 | FY21 Street Trees BK CB's9,17,18 (3Y)BG-1319M | 4 | CONSTRUCTION | Mar 2022 | Mar 2025 | Mar 2022 | Mar 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TREL21 | FY21 Street Trees BK CB's9,17,18 (3Y)BG-1319M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Mar 2027 | Mar 2025 | Mar 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TREP23 | FY23 Street Trees BK CB's 3 & 4 | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TREP23 | FY23 Street Trees BK CB's 3 & 4 | 2 | DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TREP23 | FY23 Street Trees BK CB's 3 & 4 | 3 | BID/ REGISTER CONTRACT | Jun 2023 | Mar 2024 | Jun 2023 | Mar 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TREP23 | FY23 Street Trees BK CB's 3 & 4 | 4 | CONSTRUCTION | Mar 2024 | Sep 2025 | Mar 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TREP23 | FY23 Street Trees BK CB's 3 & 4 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRS23A | Brooklyn Tree-Damaged Sidewalk R/C FY23, CBs 1,2,6,7,10 - 14 | 1 | DEVELOP SCOPE | Jan 2023 | Jun 2023 | Jan 2023 | Jun 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRS23A | Brooklyn Tree-Damaged Sidewalk R/C FY23, CBs 1,2,6,7,10 - 14 | 2 | DESIGN | Jun 2023 | Dec 2023 | Jun 2023 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRS23A | Brooklyn Tree-Damaged Sidewalk R/C FY23, CBs 1,2,6,7,10 - 14 | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRS23A | Brooklyn Tree-Damaged Sidewalk R/C FY23, CBs 1,2,6,7,10 - 14 | 4 | CONSTRUCTION | Sep 2024 | Mar 2026 | Sep 2024 | Mar 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRS23A | Brooklyn Tree-Damaged Sidewalk R/C FY23, CBs 1,2,6,7,10 - 14 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Mar 2028 | Mar 2026 | Mar 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRSD23 | Brooklyn Tree-Damaged Sidewalk Reconstruction | 1 | DEVELOP SCOPE | Jan 2023 | Jun 2023 | Jan 2023 | Jun 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRSD23 | Brooklyn Tree-Damaged Sidewalk Reconstruction | 2 | DESIGN | Jun 2023 | Dec 2023 | Jun 2023 | Dec 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRSD23 | Brooklyn Tree-Damaged Sidewalk Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRSD23 | Brooklyn Tree-Damaged Sidewalk Reconstruction | 4 | CONSTRUCTION | Sep 2024 | Mar 2026 | Sep 2024 | Mar 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRSD23 | Brooklyn Tree-Damaged Sidewalk Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Mar 2028 | Mar 2026 | Mar 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2WPKBGH | NYCHA Kingsborough Houses Open Space Construction BZ-120M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2WPKBGH | NYCHA Kingsborough Houses Open Space Construction BZ-120M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2WPKBGH | NYCHA Kingsborough Houses Open Space Construction BZ-120M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2WPKBGH | NYCHA Kingsborough Houses Open Space Construction BZ-120M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2WPKBGH | NYCHA Kingsborough Houses Open Space Construction BZ-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2029
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-6CADMAR | Recon Marlboro & Cadman Plaza Public Restroom Bldg BG-718MA | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-6CADMAR | Recon Marlboro & Cadman Plaza Public Restroom Bldg BG-718MA | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-6CADMAR | Recon Marlboro & Cadman Plaza Public Restroom Bldg BG-718MA | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-6CADMAR | Recon Marlboro & Cadman Plaza Public Restroom Bldg BG-718MA | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-6CADMAR | Recon Marlboro & Cadman Plaza Public Restroom Bldg BG-718MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-01 | SANDY-Supervision of Brooklyn Damaged Sites(Type 1) BG-311M | 1 | DEVELOP SCOPE | Dec 2012 | Feb 2013 | Dec 2012 | Feb 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-01 | SANDY-Supervision of Brooklyn Damaged Sites(Type 1) BG-311M | 2 | DESIGN | Mar 2013 | May 2013 | Mar 2013 | May 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-01 | SANDY-Supervision of Brooklyn Damaged Sites(Type 1) BG-311M | 3 | BID/ REGISTER CONTRACT | May 2013 | Aug 2013 | May 2013 | Aug 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-01 | SANDY-Supervision of Brooklyn Damaged Sites(Type 1) BG-311M | 4 | CONSTRUCTION | Aug 2013 | Aug 2014 | Aug 2013 | Aug 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-01 | SANDY-Supervision of Brooklyn Damaged Sites(Type 1) BG-311M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2014 | Aug 2015 | Aug 2014 | Aug 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-03 | SANDY-Emergency Clean up & Safe Up - Shore Pkway B166-313M | 1 | DEVELOP SCOPE | Dec 2012 | Feb 2013 | Dec 2012 | Feb 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-03 | SANDY-Emergency Clean up & Safe Up - Shore Pkway B166-313M | 2 | DESIGN | Mar 2013 | May 2013 | Mar 2013 | May 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-03 | SANDY-Emergency Clean up & Safe Up - Shore Pkway B166-313M | 3 | BID/ REGISTER CONTRACT | May 2013 | Aug 2013 | May 2013 | Aug 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-03 | SANDY-Emergency Clean up & Safe Up - Shore Pkway B166-313M | 4 | CONSTRUCTION | Aug 2013 | Aug 2014 | Aug 2013 | Aug 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-03 | SANDY-Emergency Clean up & Safe Up - Shore Pkway B166-313M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2014 | Aug 2015 | Aug 2014 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-07 | SANDY- Emergency boiler work at Red Hook B126-113M | 2 | DESIGN | Mar 2013 | May 2013 | Mar 2013 | May 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-07 | SANDY- Emergency boiler work at Red Hook B126-113M | 3 | BID/ REGISTER CONTRACT | May 2013 | Aug 2013 | May 2013 | Aug 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-07 | SANDY- Emergency boiler work at Red Hook B126-113M | 4 | CONSTRUCTION | Aug 2013 | Aug 2014 | Aug 2013 | Aug 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-07 | SANDY- Emergency boiler work at Red Hook B126-113M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2014 | Aug 2015 | Aug 2014 | Aug 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-09 | SANDY-Brooklyn Playground requirements(Type 1) BG-311M | 1 | DEVELOP SCOPE | Feb 2013 | May 2013 | Feb 2013 | May 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-09 | SANDY-Brooklyn Playground requirements(Type 1) BG-311M | 2 | DESIGN | May 2013 | Jul 2013 | May 2013 | Jul 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-09 | SANDY-Brooklyn Playground requirements(Type 1) BG-311M | 3 | BID/ REGISTER CONTRACT | Jul 2013 | Oct 2013 | Jul 2013 | Oct 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-09 | SANDY-Brooklyn Playground requirements(Type 1) BG-311M | 4 | CONSTRUCTION | Oct 2013 | Oct 2014 | Oct 2013 | Oct 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-09 | SANDY-Brooklyn Playground requirements(Type 1) BG-311M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2014 | Oct 2015 | Oct 2014 | Jun 2030
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-12 | SANDY - Brooklyn Plgd requirements (Type 2) BG-1113M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-12 | SANDY - Brooklyn Plgd requirements (Type 2) BG-1113M | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-12 | SANDY - Brooklyn Plgd requirements (Type 2) BG-1113M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2013 | Mar 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-12 | SANDY - Brooklyn Plgd requirements (Type 2) BG-1113M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-12 | SANDY - Brooklyn Plgd requirements (Type 2) BG-1113M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2015 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-13 | SANDY - PNP Prospect Park Alliance | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-13 | SANDY - PNP Prospect Park Alliance | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-13 | SANDY - PNP Prospect Park Alliance | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2013 | Mar 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-13 | SANDY - PNP Prospect Park Alliance | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-13 | SANDY - PNP Prospect Park Alliance | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2015 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-14 | SANDY- Abe Stark boilers and chillers (B169-111M) | 1 | DEVELOP SCOPE | May 2013 | Aug 2013 | May 2013 | Aug 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-14 | SANDY- Abe Stark boilers and chillers (B169-111M) | 2 | DESIGN | Aug 2013 | Nov 2013 | Aug 2013 | Nov 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-14 | SANDY- Abe Stark boilers and chillers (B169-111M) | 3 | BID/ REGISTER CONTRACT | Nov 2013 | Feb 2014 | Nov 2013 | Feb 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-14 | SANDY- Abe Stark boilers and chillers (B169-111M) | 4 | CONSTRUCTION | Feb 2014 | Feb 2015 | Feb 2014 | Feb 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-14 | SANDY- Abe Stark boilers and chillers (B169-111M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2015 | Feb 2016 | Feb 2015 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-16 | SANDY-Sheepshead Bay Piers Type 3 | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-16 | SANDY-Sheepshead Bay Piers Type 3 | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-16 | SANDY-Sheepshead Bay Piers Type 3 | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2013 | Mar 2014
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-16 | SANDY-Sheepshead Bay Piers Type 3 | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2015
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-16 | SANDY-Sheepshead Bay Piers Type 3 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2015 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-21 | SANDY - Tree removals -Brooklyn CB 7-18 BG-614M | 1 | DEVELOP SCOPE | Jan 2014 | Mar 2014 | Jan 2014 | Jun 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-21 | SANDY - Tree removals -Brooklyn CB 7-18 BG-614M | 2 | DESIGN | Apr 2014 | Jun 2014 | Jun 2019 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-21 | SANDY - Tree removals -Brooklyn CB 7-18 BG-614M | 3 | BID/ REGISTER CONTRACT | Jun 2014 | Sep 2014 | Sep 2019 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-21 | SANDY - Tree removals -Brooklyn CB 7-18 BG-614M | 4 | CONSTRUCTION | Sep 2014 | Sep 2015 | Dec 2019 | Dec 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-21 | SANDY - Tree removals -Brooklyn CB 7-18 BG-614M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2015 | Sep 2016 | Dec 2020 | Dec 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-25 | Abe Stark - Non-Boiler Repair | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-25 | Abe Stark - Non-Boiler Repair | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-25 | Abe Stark - Non-Boiler Repair | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-25 | Abe Stark - Non-Boiler Repair | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-25 | Abe Stark - Non-Boiler Repair | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-28 | Red Hook Recreation Center RC B126-121M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-28 | Red Hook Recreation Center RC B126-121M | 2 | DESIGN | Dec 2017 | Dec 2019 | Dec 2017 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-28 | Red Hook Recreation Center RC B126-121M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-28 | Red Hook Recreation Center RC B126-121M | 4 | CONSTRUCTION | Sep 2020 | Sep 2022 | Sep 2020 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-28 | Red Hook Recreation Center RC B126-121M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-30 | Hudson River Yacht Club B406-122M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-30 | Hudson River Yacht Club B406-122M | 2 | DESIGN | Dec 2017 | Dec 2019 | Dec 2017 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-30 | Hudson River Yacht Club B406-122M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-30 | Hudson River Yacht Club B406-122M | 4 | CONSTRUCTION | Sep 2020 | Sep 2022 | Sep 2020 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-30 | Hudson River Yacht Club B406-122M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-31 | Diamond Point Yacht Club B406-122M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-31 | Diamond Point Yacht Club B406-122M | 2 | DESIGN | Dec 2017 | Dec 2019 | Dec 2017 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-31 | Diamond Point Yacht Club B406-122M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-31 | Diamond Point Yacht Club B406-122M | 4 | CONSTRUCTION | Sep 2020 | Sep 2022 | Sep 2020 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-31 | Diamond Point Yacht Club B406-122M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-32 | Paerdegat Squadron Yacht Club B406-122M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-32 | Paerdegat Squadron Yacht Club B406-122M | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-32 | Paerdegat Squadron Yacht Club B406-122M | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-32 | Paerdegat Squadron Yacht Club B406-122M | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-32 | Paerdegat Squadron Yacht Club B406-122M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-33 | Sandy - Midget Squadron Yacht Club B406-122M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-33 | Sandy - Midget Squadron Yacht Club B406-122M | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-33 | Sandy - Midget Squadron Yacht Club B406-122M | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-33 | Sandy - Midget Squadron Yacht Club B406-122M | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-33 | Sandy - Midget Squadron Yacht Club B406-122M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-34 | Paerdegat Athletic Center HVAC recon. B406-114M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-34 | Paerdegat Athletic Center HVAC recon. B406-114M | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-34 | Paerdegat Athletic Center HVAC recon. B406-114M | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-34 | Paerdegat Athletic Center HVAC recon. B406-114M | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-34 | Paerdegat Athletic Center HVAC recon. B406-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2019 | Jun 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-35 | Paerdegat Athletic Center - Remaining Scope B406-521M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-35 | Paerdegat Athletic Center - Remaining Scope B406-521M | 2 | DESIGN | Dec 2017 | Dec 2019 | Dec 2022 | Dec 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-35 | Paerdegat Athletic Center - Remaining Scope B406-521M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-35 | Paerdegat Athletic Center - Remaining Scope B406-521M | 4 | CONSTRUCTION | Sep 2020 | Sep 2022 | Sep 2025 | Sep 2027
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-35 | Paerdegat Athletic Center - Remaining Scope B406-521M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2027 | Sep 2028
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-37 | SANDY-John Malone Community Center | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-37 | SANDY-John Malone Community Center | 2 | DESIGN | Dec 2019 | Dec 2021 | Dec 2019 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-37 | SANDY-John Malone Community Center | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-37 | SANDY-John Malone Community Center | 4 | CONSTRUCTION | Sep 2022 | Sep 2024 | Sep 2022 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-37 | SANDY-John Malone Community Center | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-39 | Kaiser Park Conduit Reconstruction | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-39 | Kaiser Park Conduit Reconstruction | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-39 | Kaiser Park Conduit Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-39 | Kaiser Park Conduit Reconstruction | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-39 | Kaiser Park Conduit Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SEED-SAPG | SEED- St Andrew's Playground | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SEED-SAPG | SEED- St Andrew's Playground | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SEED-SAPG | SEED- St Andrew's Playground | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SEED-SAPG | SEED- St Andrew's Playground | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SEED-SAPG | SEED- St Andrew's Playground | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | ACEDCA215 | DCLA- BCM HVAC UPGRADES | 1 | DEVELOP SCOPE | Jun 2024 | Aug 2024 | Jun 2024 | Aug 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | ACEDCA215 | DCLA- BCM HVAC UPGRADES | 2 | PRELIMINARY DESIGN | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | ACEDCA215 | DCLA- BCM HVAC UPGRADES | 3 | FINAL DESIGN | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | ACEDCA215 | DCLA- BCM HVAC UPGRADES | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | ACEDCA215 | DCLA- BCM HVAC UPGRADES | 5 | CONSTRUCTION TO 25% | Jun 2026 | Sep 2026 | Jun 2026 | Sep 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | ACEDCA215 | DCLA- BCM HVAC UPGRADES | 6 | CONSTRUCTION TO 50% | Sep 2026 | Jan 2027 | Sep 2026 | Jan 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | ACEDCA215 | DCLA- BCM HVAC UPGRADES | 7 | CONSTRUCTION TO 75% | Jan 2027 | May 2027 | Jan 2027 | May 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | ACEDCA215 | DCLA- BCM HVAC UPGRADES | 8 | ORIGINAL EQUIP & FURNISHING | May 2027 | Aug 2027 | May 2027 | Aug 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | ACEDCA215 | DCLA- BCM HVAC UPGRADES | 9 | SUBSTANTIAL COMPLETION | Aug 2027 | Oct 2027 | Aug 2027 | Oct 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | ACEDCA215 | DCLA- BCM HVAC UPGRADES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2027 | Nov 2027 | Oct 2027 | Nov 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-K | Boro Based Jails New Brooklyn Detention Facility DesignBuild | 1 | DEVELOP SCOPE | Sep 2018 | Nov 2018 | Sep 2018 | Nov 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-K | Boro Based Jails New Brooklyn Detention Facility DesignBuild | 2 | PRELIMINARY DESIGN | Nov 2018 | Mar 2019 | Nov 2018 | Mar 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-K | Boro Based Jails New Brooklyn Detention Facility DesignBuild | 3 | FINAL DESIGN | Mar 2019 | Sep 2019 | Mar 2019 | Sep 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-K | Boro Based Jails New Brooklyn Detention Facility DesignBuild | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Dec 2019 | Sep 2019 | Dec 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-K | Boro Based Jails New Brooklyn Detention Facility DesignBuild | 5 | CONSTRUCTION TO 25% | Dec 2019 | Apr 2020 | Dec 2019 | Apr 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-K | Boro Based Jails New Brooklyn Detention Facility DesignBuild | 6 | CONSTRUCTION TO 50% | Apr 2020 | Aug 2020 | Apr 2020 | Aug 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-K | Boro Based Jails New Brooklyn Detention Facility DesignBuild | 7 | CONSTRUCTION TO 75% | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-K | Boro Based Jails New Brooklyn Detention Facility DesignBuild | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2020 | Mar 2021 | Dec 2020 | Mar 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-K | Boro Based Jails New Brooklyn Detention Facility DesignBuild | 9 | SUBSTANTIAL COMPLETION | Mar 2021 | May 2021 | Mar 2021 | May 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-K | Boro Based Jails New Brooklyn Detention Facility DesignBuild | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2021 | Jun 2029 | May 2021 | Jun 2029
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-768B | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE II (HWK700B) | 1 | DEVELOP SCOPE | Aug 2009 | Nov 2011 | Aug 2009 | May 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-768B | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE II (HWK700B) | 2 | PRELIMINARY DESIGN | Nov 2011 | Nov 2011 | May 2024 | May 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-768B | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE II (HWK700B) | 3 | FINAL DESIGN | Nov 2011 | Nov 2011 | Sep 2023 | Mar 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-768B | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE II (HWK700B) | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2011 | Nov 2011 | Mar 2024 | Jun 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-768B | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE II (HWK700B) | 5 | CONSTRUCTION TO 25% | Nov 2011 | Nov 2011 | Jun 2024 | Jun 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-768B | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE II (HWK700B) | 6 | CONSTRUCTION TO 50% | Nov 2011 | Nov 2011 | Jun 2025 | Jun 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-768B | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE II (HWK700B) | 7 | CONSTRUCTION TO 75% | Nov 2011 | Nov 2011 | Jun 2026 | Jun 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-768B | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE II (HWK700B) | 8 | ORIGINAL EQUIP & FURNISHING | Nov 2011 | Nov 2011 | Jun 2027 | Aug 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-768B | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE II (HWK700B) | 9 | SUBSTANTIAL COMPLETION | Nov 2011 | Nov 2011 | Aug 2027 | Oct 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-768B | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE II (HWK700B) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2011 | Dec 2011 | Oct 2027 | Nov 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-776 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | 1 | DEVELOP SCOPE | Mar 2011 | Jun 2011 | Mar 2011 | Jun 2011
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-776 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | 2 | PRELIMINARY DESIGN | Jun 2011 | Oct 2011 | Jun 2011 | Oct 2011
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-776 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | 3 | FINAL DESIGN | Oct 2011 | Apr 2012 | Oct 2011 | Apr 2012
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-776 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2012 | Jul 2012 | Mar 2018 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-776 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | 5 | CONSTRUCTION TO 25% | Jul 2012 | Nov 2012 | Jun 2018 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-776 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | 6 | CONSTRUCTION TO 50% | Nov 2012 | Mar 2013 | Jun 2018 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-776 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | 7 | CONSTRUCTION TO 75% | Mar 2013 | Jul 2013 | Jun 2018 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-776 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2013 | Oct 2013 | Jun 2018 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-776 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | 9 | SUBSTANTIAL COMPLETION | Oct 2013 | Dec 2013 | Jun 2018 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-776 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2013 | Dec 2013 | Jan 2020 | Jun 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-778A | Trunk & Dist WM Rep in Atlantic Ave b/t Carlton & Portland | 1 | DEVELOP SCOPE | Feb 2013 | May 2013 | Feb 2013 | May 2013
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-778A | Trunk & Dist WM Rep in Atlantic Ave b/t Carlton & Portland | 2 | PRELIMINARY DESIGN | May 2013 | Sep 2013 | May 2013 | Sep 2013
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-778A | Trunk & Dist WM Rep in Atlantic Ave b/t Carlton & Portland | 3 | FINAL DESIGN | Sep 2013 | Mar 2014 | Sep 2013 | Mar 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-778A | Trunk & Dist WM Rep in Atlantic Ave b/t Carlton & Portland | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2014 | Jun 2014 | Mar 2016 | Jul 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-778A | Trunk & Dist WM Rep in Atlantic Ave b/t Carlton & Portland | 5 | CONSTRUCTION TO 25% | Jun 2014 | Oct 2014 | Jul 2016 | Nov 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-778A | Trunk & Dist WM Rep in Atlantic Ave b/t Carlton & Portland | 6 | CONSTRUCTION TO 50% | Oct 2014 | Feb 2015 | Nov 2016 | Mar 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-778A | Trunk & Dist WM Rep in Atlantic Ave b/t Carlton & Portland | 7 | CONSTRUCTION TO 75% | Feb 2015 | Jun 2015 | Mar 2017 | Jul 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-778A | Trunk & Dist WM Rep in Atlantic Ave b/t Carlton & Portland | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2015 | Sep 2015 | Jul 2017 | Jul 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-778A | Trunk & Dist WM Rep in Atlantic Ave b/t Carlton & Portland | 9 | SUBSTANTIAL COMPLETION | Sep 2015 | Nov 2015 | Jul 2017 | Nov 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-778A | Trunk & Dist WM Rep in Atlantic Ave b/t Carlton & Portland | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2015 | Dec 2015 | Nov 2017 | Jun 2031
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-782A | Reconst of water main & comb sewer,Tillary st PH2 HWK639WA | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-782A | Reconst of water main & comb sewer,Tillary st PH2 HWK639WA | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-782A | Reconst of water main & comb sewer,Tillary st PH2 HWK639WA | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-782A | Reconst of water main & comb sewer,Tillary st PH2 HWK639WA | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-782A | Reconst of water main & comb sewer,Tillary st PH2 HWK639WA | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-782A | Reconst of water main & comb sewer,Tillary st PH2 HWK639WA | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-782A | Reconst of water main & comb sewer,Tillary st PH2 HWK639WA | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-782A | Reconst of water main & comb sewer,Tillary st PH2 HWK639WA | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-782A | Reconst of water main & comb sewer,Tillary st PH2 HWK639WA | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Jan 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-782A | Reconst of water main & comb sewer,Tillary st PH2 HWK639WA | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Jan 2020 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-784 | RECON OF WM I& STORM SWR IN BERGEN AVE AREA, HWK614D | 1 | DEVELOP SCOPE | Feb 2014 | May 2014 | Feb 2014 | May 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-784 | RECON OF WM I& STORM SWR IN BERGEN AVE AREA, HWK614D | 2 | PRELIMINARY DESIGN | May 2014 | Sep 2014 | May 2023 | Sep 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-784 | RECON OF WM I& STORM SWR IN BERGEN AVE AREA, HWK614D | 3 | FINAL DESIGN | Sep 2014 | Mar 2015 | Sep 2023 | Mar 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-784 | RECON OF WM I& STORM SWR IN BERGEN AVE AREA, HWK614D | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2015 | Jun 2015 | Mar 2024 | Jun 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-784 | RECON OF WM I& STORM SWR IN BERGEN AVE AREA, HWK614D | 5 | CONSTRUCTION TO 25% | Jun 2015 | Oct 2015 | Jun 2024 | Jun 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-784 | RECON OF WM I& STORM SWR IN BERGEN AVE AREA, HWK614D | 6 | CONSTRUCTION TO 50% | Oct 2015 | Feb 2016 | Jun 2025 | Jun 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-784 | RECON OF WM I& STORM SWR IN BERGEN AVE AREA, HWK614D | 7 | CONSTRUCTION TO 75% | Feb 2016 | Jun 2016 | Jun 2026 | Jun 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-784 | RECON OF WM I& STORM SWR IN BERGEN AVE AREA, HWK614D | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2016 | Sep 2016 | Jun 2027 | Sep 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-784 | RECON OF WM I& STORM SWR IN BERGEN AVE AREA, HWK614D | 9 | SUBSTANTIAL COMPLETION | Sep 2016 | Nov 2016 | Sep 2027 | Nov 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-784 | RECON OF WM I& STORM SWR IN BERGEN AVE AREA, HWK614D | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2016 | Dec 2016 | Nov 2027 | Dec 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-794 | DUMBO/Vinegar Hill Area Reconstruction & Plaza. HWKKP005 | 1 | DEVELOP SCOPE | Mar 2014 | May 2014 | Mar 2014 | May 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-794 | DUMBO/Vinegar Hill Area Reconstruction & Plaza. HWKKP005 | 2 | PRELIMINARY DESIGN | May 2014 | Sep 2014 | May 2014 | Sep 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-794 | DUMBO/Vinegar Hill Area Reconstruction & Plaza. HWKKP005 | 3 | FINAL DESIGN | Sep 2014 | Mar 2015 | Sep 2014 | Mar 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-794 | DUMBO/Vinegar Hill Area Reconstruction & Plaza. HWKKP005 | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2015 | Jun 2015 | Mar 2017 | Jun 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-794 | DUMBO/Vinegar Hill Area Reconstruction & Plaza. HWKKP005 | 5 | CONSTRUCTION TO 25% | Jun 2015 | Oct 2015 | Jun 2017 | Oct 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-794 | DUMBO/Vinegar Hill Area Reconstruction & Plaza. HWKKP005 | 6 | CONSTRUCTION TO 50% | Oct 2015 | Feb 2016 | Oct 2017 | Feb 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-794 | DUMBO/Vinegar Hill Area Reconstruction & Plaza. HWKKP005 | 7 | CONSTRUCTION TO 75% | Feb 2016 | Jun 2016 | Feb 2018 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-794 | DUMBO/Vinegar Hill Area Reconstruction & Plaza. HWKKP005 | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2016 | Sep 2016 | Jun 2018 | Sep 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-794 | DUMBO/Vinegar Hill Area Reconstruction & Plaza. HWKKP005 | 9 | SUBSTANTIAL COMPLETION | Sep 2016 | Nov 2016 | Sep 2018 | Nov 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-794 | DUMBO/Vinegar Hill Area Reconstruction & Plaza. HWKKP005 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2016 | Dec 2016 | Nov 2018 | Sep 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-796 | Trunk & Distribution WM replcmnt in Empire Blvd, HWK779W | 1 | DEVELOP SCOPE | Mar 2015 | May 2015 | Mar 2015 | May 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-796 | Trunk & Distribution WM replcmnt in Empire Blvd, HWK779W | 2 | PRELIMINARY DESIGN | May 2015 | Sep 2015 | May 2015 | Aug 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-796 | Trunk & Distribution WM replcmnt in Empire Blvd, HWK779W | 3 | FINAL DESIGN | Sep 2015 | Mar 2016 | Aug 2017 | Feb 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-796 | Trunk & Distribution WM replcmnt in Empire Blvd, HWK779W | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2016 | Jun 2016 | Feb 2018 | May 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-796 | Trunk & Distribution WM replcmnt in Empire Blvd, HWK779W | 5 | CONSTRUCTION TO 25% | Jun 2016 | Oct 2016 | May 2018 | Sep 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-796 | Trunk & Distribution WM replcmnt in Empire Blvd, HWK779W | 6 | CONSTRUCTION TO 50% | Oct 2016 | Feb 2017 | Sep 2018 | Jan 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-796 | Trunk & Distribution WM replcmnt in Empire Blvd, HWK779W | 7 | CONSTRUCTION TO 75% | Feb 2017 | Jun 2017 | Jan 2019 | May 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-796 | Trunk & Distribution WM replcmnt in Empire Blvd, HWK779W | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2017 | Sep 2017 | May 2019 | Aug 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-796 | Trunk & Distribution WM replcmnt in Empire Blvd, HWK779W | 9 | SUBSTANTIAL COMPLETION | Sep 2017 | Nov 2017 | Aug 2019 | Oct 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-796 | Trunk & Distribution WM replcmnt in Empire Blvd, HWK779W | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | Dec 2017 | Oct 2019 | Jun 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED798 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 1 | DEVELOP SCOPE | Mar 2015 | May 2015 | Mar 2015 | May 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED798 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 2 | PRELIMINARY DESIGN | May 2015 | Sep 2015 | May 2015 | Sep 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED798 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 3 | FINAL DESIGN | Sep 2015 | Mar 2016 | Sep 2015 | Mar 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED798 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2016 | Jun 2016 | Mar 2016 | Jun 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED798 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 5 | CONSTRUCTION TO 25% | Jun 2016 | Oct 2016 | Jun 2016 | Oct 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED798 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 6 | CONSTRUCTION TO 50% | Oct 2016 | Feb 2017 | Oct 2016 | Feb 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED798 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 7 | CONSTRUCTION TO 75% | Feb 2017 | Jun 2017 | Feb 2017 | Jun 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED798 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2017 | Sep 2017 | Jun 2017 | Sep 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED798 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 9 | SUBSTANTIAL COMPLETION | Sep 2017 | Nov 2017 | Sep 2017 | Nov 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED798 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | Dec 2017 | Nov 2018 | Jan 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-802 | WM Replacement Hamilton Ave Gowanus Connector, BK HWK1048D | 1 | DEVELOP SCOPE | Mar 2016 | May 2016 | Mar 2016 | May 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-802 | WM Replacement Hamilton Ave Gowanus Connector, BK HWK1048D | 2 | PRELIMINARY DESIGN | May 2016 | Sep 2016 | May 2016 | Sep 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-802 | WM Replacement Hamilton Ave Gowanus Connector, BK HWK1048D | 3 | FINAL DESIGN | Sep 2016 | Mar 2017 | Sep 2016 | Mar 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-802 | WM Replacement Hamilton Ave Gowanus Connector, BK HWK1048D | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2017 | Jun 2017 | Mar 2017 | Jun 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-802 | WM Replacement Hamilton Ave Gowanus Connector, BK HWK1048D | 5 | CONSTRUCTION TO 25% | Jun 2017 | Oct 2017 | Jun 2017 | Oct 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-802 | WM Replacement Hamilton Ave Gowanus Connector, BK HWK1048D | 6 | CONSTRUCTION TO 50% | Oct 2017 | Feb 2018 | Oct 2017 | Feb 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-802 | WM Replacement Hamilton Ave Gowanus Connector, BK HWK1048D | 7 | CONSTRUCTION TO 75% | Feb 2018 | Jun 2018 | Feb 2018 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-802 | WM Replacement Hamilton Ave Gowanus Connector, BK HWK1048D | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-802 | WM Replacement Hamilton Ave Gowanus Connector, BK HWK1048D | 9 | SUBSTANTIAL COMPLETION | Sep 2018 | Nov 2018 | Sep 2018 | Nov 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-802 | WM Replacement Hamilton Ave Gowanus Connector, BK HWK1048D | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2018 | Dec 2018 | Nov 2018 | Jun 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-803 | WM Repl in Schenck Av b/t Flatlands & Jamaica Av Bk, HWK797W | 1 | DEVELOP SCOPE | Jun 2013 | Feb 2014 | Jun 2013 | Aug 2013
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-803 | WM Repl in Schenck Av b/t Flatlands & Jamaica Av Bk, HWK797W | 2 | PRELIMINARY DESIGN | Feb 2014 | Feb 2015 | Aug 2013 | Dec 2013
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-803 | WM Repl in Schenck Av b/t Flatlands & Jamaica Av Bk, HWK797W | 3 | FINAL DESIGN | Feb 2015 | Aug 2016 | Dec 2013 | Jun 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-803 | WM Repl in Schenck Av b/t Flatlands & Jamaica Av Bk, HWK797W | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2016 | May 2017 | Jun 2014 | Sep 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-803 | WM Repl in Schenck Av b/t Flatlands & Jamaica Av Bk, HWK797W | 5 | CONSTRUCTION TO 25% | May 2017 | May 2018 | Sep 2014 | Jan 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-803 | WM Repl in Schenck Av b/t Flatlands & Jamaica Av Bk, HWK797W | 6 | CONSTRUCTION TO 50% | May 2018 | Apr 2019 | Jan 2015 | May 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-803 | WM Repl in Schenck Av b/t Flatlands & Jamaica Av Bk, HWK797W | 7 | CONSTRUCTION TO 75% | May 2019 | Apr 2020 | May 2015 | Sep 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-803 | WM Repl in Schenck Av b/t Flatlands & Jamaica Av Bk, HWK797W | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2020 | Jan 2021 | Sep 2015 | Dec 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-803 | WM Repl in Schenck Av b/t Flatlands & Jamaica Av Bk, HWK797W | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Jul 2021 | Dec 2015 | Feb 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-803 | WM Repl in Schenck Av b/t Flatlands & Jamaica Av Bk, HWK797W | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Oct 2021 | Feb 2016 | Nov 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-805 | New Storm & San Swrs & WM-Gateway Estates, Phase E (HD-161E) | 1 | DEVELOP SCOPE | Jun 2013 | Sep 2013 | Jun 2013 | Sep 2013
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-805 | New Storm & San Swrs & WM-Gateway Estates, Phase E (HD-161E) | 2 | PRELIMINARY DESIGN | Sep 2013 | Jan 2014 | Sep 2013 | Jan 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-805 | New Storm & San Swrs & WM-Gateway Estates, Phase E (HD-161E) | 3 | FINAL DESIGN | Jan 2014 | Jul 2014 | Jan 2014 | Jul 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-805 | New Storm & San Swrs & WM-Gateway Estates, Phase E (HD-161E) | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2014 | Oct 2014 | Jul 2015 | Oct 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-805 | New Storm & San Swrs & WM-Gateway Estates, Phase E (HD-161E) | 5 | CONSTRUCTION TO 25% | Oct 2014 | Feb 2015 | Oct 2015 | Feb 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-805 | New Storm & San Swrs & WM-Gateway Estates, Phase E (HD-161E) | 6 | CONSTRUCTION TO 50% | Feb 2015 | Jun 2015 | Feb 2016 | Jun 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-805 | New Storm & San Swrs & WM-Gateway Estates, Phase E (HD-161E) | 7 | CONSTRUCTION TO 75% | Jun 2015 | Oct 2015 | Jun 2016 | Feb 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-805 | New Storm & San Swrs & WM-Gateway Estates, Phase E (HD-161E) | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2015 | Jan 2016 | Feb 2017 | Feb 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-805 | New Storm & San Swrs & WM-Gateway Estates, Phase E (HD-161E) | 9 | SUBSTANTIAL COMPLETION | Jan 2016 | Mar 2016 | Feb 2017 | Apr 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-805 | New Storm & San Swrs & WM-Gateway Estates, Phase E (HD-161E) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Apr 2016 | Apr 2017 | Apr 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway, HWK1048E | 1 | DEVELOP SCOPE | Jun 2013 | Aug 2013 | Mar 2017 | May 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway, HWK1048E | 2 | PRELIMINARY DESIGN | Aug 2013 | Dec 2013 | May 2017 | Sep 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway, HWK1048E | 3 | FINAL DESIGN | Dec 2013 | Jun 2014 | Sep 2017 | Mar 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway, HWK1048E | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2014 | Sep 2014 | Mar 2018 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway, HWK1048E | 5 | CONSTRUCTION TO 25% | Sep 2014 | Jan 2015 | Jun 2018 | Feb 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway, HWK1048E | 6 | CONSTRUCTION TO 50% | Jan 2015 | May 2015 | Feb 2019 | Oct 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway, HWK1048E | 7 | CONSTRUCTION TO 75% | May 2015 | Sep 2015 | Oct 2019 | Jun 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway, HWK1048E | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2015 | Dec 2015 | Jun 2020 | Sep 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway, HWK1048E | 9 | SUBSTANTIAL COMPLETION | Dec 2015 | Feb 2016 | Sep 2020 | Nov 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway, HWK1048E | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2016 | Mar 2016 | Nov 2020 | Sep 2028
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway, HWK1048E | 11 | DEVELOP SCOPE | Mar 2016 | Dec 2016 | Nov 2020 | Sep 2028
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway, HWK1048E | 12 | PRELIMINARY DESIGN | Dec 2016 | Dec 2017 | Nov 2020 | Sep 2028
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway, HWK1048E | 13 | FINAL DESIGN | Dec 2017 | May 2019 | Nov 2020 | Sep 2028
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway, HWK1048E | 14 | BID AWARD AND REGISTER CONTRCT | May 2019 | Feb 2020 | Nov 2020 | Sep 2028
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway, HWK1048E | 15 | CONSTRUCTION TO 25% | Feb 2020 | Feb 2021 | Nov 2020 | Sep 2028
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway, HWK1048E | 16 | CONSTRUCTION TO 50% | Feb 2021 | Feb 2022 | Nov 2020 | Sep 2028
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway, HWK1048E | 17 | CONSTRUCTION TO 75% | Feb 2022 | Feb 2023 | Nov 2020 | Sep 2028
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway, HWK1048E | 18 | ORIGINAL EQUIP & FURNISHING | Feb 2023 | Nov 2023 | Nov 2020 | Sep 2028
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway, HWK1048E | 19 | SUBSTANTIAL COMPLETION | Nov 2023 | May 2024 | Nov 2020 | Sep 2028
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway, HWK1048E | 20 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Aug 2024 | Nov 2020 | Sep 2028
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-807 | WM work in Brooklyn Waterfront Greenway. SAND1048 | 1 | DEVELOP SCOPE | Jun 2013 | Sep 2013 | Jun 2013 | Sep 2013
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-807 | WM work in Brooklyn Waterfront Greenway. SAND1048 | 2 | PRELIMINARY DESIGN | Sep 2013 | Jan 2014 | Sep 2013 | Jan 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-807 | WM work in Brooklyn Waterfront Greenway. SAND1048 | 3 | FINAL DESIGN | Jan 2014 | Jul 2014 | Jan 2014 | Jul 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-807 | WM work in Brooklyn Waterfront Greenway. SAND1048 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2014 | Oct 2014 | Jul 2014 | Oct 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-807 | WM work in Brooklyn Waterfront Greenway. SAND1048 | 5 | CONSTRUCTION TO 25% | Oct 2014 | Feb 2015 | Oct 2014 | Feb 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-807 | WM work in Brooklyn Waterfront Greenway. SAND1048 | 6 | CONSTRUCTION TO 50% | Feb 2015 | Jun 2015 | Feb 2015 | Jun 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-807 | WM work in Brooklyn Waterfront Greenway. SAND1048 | 7 | CONSTRUCTION TO 75% | Jun 2015 | Oct 2015 | Jun 2015 | Oct 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-807 | WM work in Brooklyn Waterfront Greenway. SAND1048 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2015 | Jan 2016 | Oct 2015 | Jan 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-807 | WM work in Brooklyn Waterfront Greenway. SAND1048 | 9 | SUBSTANTIAL COMPLETION | Jan 2016 | Mar 2016 | Jan 2016 | Jan 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-807 | WM work in Brooklyn Waterfront Greenway. SAND1048 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Apr 2016 | Jan 2018 | Jun 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-809 | Replacement of Water Mains in Avenue S | 1 | DEVELOP SCOPE | Jun 2013 | Mar 2014 | Jun 2013 | Mar 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-809 | Replacement of Water Mains in Avenue S | 2 | PRELIMINARY DESIGN | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-809 | Replacement of Water Mains in Avenue S | 3 | FINAL DESIGN | Mar 2015 | Sep 2016 | Mar 2015 | Sep 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-809 | Replacement of Water Mains in Avenue S | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2016 | Jun 2017 | Sep 2016 | Jun 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-809 | Replacement of Water Mains in Avenue S | 5 | CONSTRUCTION TO 25% | Jun 2017 | Jun 2018 | Jun 2017 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-809 | Replacement of Water Mains in Avenue S | 6 | CONSTRUCTION TO 50% | Jun 2018 | May 2019 | Jun 2018 | May 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-809 | Replacement of Water Mains in Avenue S | 7 | CONSTRUCTION TO 75% | May 2019 | May 2020 | May 2019 | May 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-809 | Replacement of Water Mains in Avenue S | 8 | ORIGINAL EQUIP & FURNISHING | May 2020 | Feb 2021 | May 2020 | Feb 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-809 | Replacement of Water Mains in Avenue S | 9 | SUBSTANTIAL COMPLETION | Feb 2021 | Aug 2025 | Feb 2021 | Aug 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-809 | Replacement of Water Mains in Avenue S | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2025 | Nov 2025 | Aug 2025 | Nov 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-810 | Water Main work in Brooklyn Waterfront Gateway, HWK1048C | 1 | DEVELOP SCOPE | Jun 2016 | Aug 2016 | Jun 2016 | Aug 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-810 | Water Main work in Brooklyn Waterfront Gateway, HWK1048C | 2 | PRELIMINARY DESIGN | Aug 2016 | Dec 2016 | Aug 2016 | Dec 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-810 | Water Main work in Brooklyn Waterfront Gateway, HWK1048C | 3 | FINAL DESIGN | Dec 2016 | Jun 2017 | Dec 2016 | Jun 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-810 | Water Main work in Brooklyn Waterfront Gateway, HWK1048C | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2017 | Sep 2017 | Jun 2017 | Sep 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-810 | Water Main work in Brooklyn Waterfront Gateway, HWK1048C | 5 | CONSTRUCTION TO 25% | Sep 2017 | Jan 2018 | Sep 2017 | Jan 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-810 | Water Main work in Brooklyn Waterfront Gateway, HWK1048C | 6 | CONSTRUCTION TO 50% | Jan 2018 | May 2018 | Jan 2018 | May 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-810 | Water Main work in Brooklyn Waterfront Gateway, HWK1048C | 7 | CONSTRUCTION TO 75% | May 2018 | Sep 2018 | May 2018 | Sep 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-810 | Water Main work in Brooklyn Waterfront Gateway, HWK1048C | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2018 | Dec 2018 | Sep 2018 | Dec 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-810 | Water Main work in Brooklyn Waterfront Gateway, HWK1048C | 9 | SUBSTANTIAL COMPLETION | Dec 2018 | Feb 2019 | Dec 2018 | Feb 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-810 | Water Main work in Brooklyn Waterfront Gateway, HWK1048C | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2019 | Mar 2019 | Feb 2019 | Aug 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-819 | WM replacement in Oriental Blvd | 1 | DEVELOP SCOPE | Mar 2018 | May 2018 | Mar 2018 | May 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-819 | WM replacement in Oriental Blvd | 2 | PRELIMINARY DESIGN | May 2018 | Sep 2018 | May 2018 | Sep 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-819 | WM replacement in Oriental Blvd | 3 | FINAL DESIGN | Sep 2018 | Mar 2019 | Sep 2018 | Mar 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-819 | WM replacement in Oriental Blvd | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2019 | Jun 2019 | Mar 2019 | Jun 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-819 | WM replacement in Oriental Blvd | 5 | CONSTRUCTION TO 25% | Jun 2019 | Oct 2019 | Jun 2019 | Oct 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-819 | WM replacement in Oriental Blvd | 6 | CONSTRUCTION TO 50% | Oct 2019 | Feb 2020 | Oct 2019 | Feb 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-819 | WM replacement in Oriental Blvd | 7 | CONSTRUCTION TO 75% | Feb 2020 | Jun 2020 | Feb 2020 | Jun 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-819 | WM replacement in Oriental Blvd | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-819 | WM replacement in Oriental Blvd | 9 | SUBSTANTIAL COMPLETION | Sep 2020 | Nov 2020 | Sep 2020 | Nov 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-819 | WM replacement in Oriental Blvd | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2020 | Dec 2020 | Nov 2020 | Jan 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-828 | Dist WM work in 86th St btw Bay 20th & 28th St,BK, HWSRT200E | 1 | DEVELOP SCOPE | Nov 2022 | Feb 2023 | Nov 2022 | Feb 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-828 | Dist WM work in 86th St btw Bay 20th & 28th St,BK, HWSRT200E | 2 | PRELIMINARY DESIGN | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-828 | Dist WM work in 86th St btw Bay 20th & 28th St,BK, HWSRT200E | 3 | FINAL DESIGN | Jun 2023 | Dec 2023 | Jun 2023 | Dec 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-828 | Dist WM work in 86th St btw Bay 20th & 28th St,BK, HWSRT200E | 4 | BID AWARD AND REGISTER CONTRCT | Dec 2023 | Mar 2024 | Dec 2023 | Mar 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-828 | Dist WM work in 86th St btw Bay 20th & 28th St,BK, HWSRT200E | 5 | CONSTRUCTION TO 25% | Mar 2024 | Jul 2024 | Mar 2024 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-828 | Dist WM work in 86th St btw Bay 20th & 28th St,BK, HWSRT200E | 6 | CONSTRUCTION TO 50% | Jul 2024 | Nov 2024 | Jul 2024 | Nov 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-828 | Dist WM work in 86th St btw Bay 20th & 28th St,BK, HWSRT200E | 7 | CONSTRUCTION TO 75% | Nov 2024 | Mar 2025 | Nov 2024 | Mar 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-828 | Dist WM work in 86th St btw Bay 20th & 28th St,BK, HWSRT200E | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2025 | Jun 2025 | Mar 2025 | Jun 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-828 | Dist WM work in 86th St btw Bay 20th & 28th St,BK, HWSRT200E | 9 | SUBSTANTIAL COMPLETION | Jun 2025 | Jul 2025 | Jun 2025 | Jul 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-828 | Dist WM work in 86th St btw Bay 20th & 28th St,BK, HWSRT200E | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2025 | Aug 2025 | Aug 2025 | Aug 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED829 | Dts WM Rplmt in 4th Av fr Atlantic av to 64th ST-BK HWK1669B | 1 | DEVELOP SCOPE | Sep 2021 | Dec 2021 | Sep 2021 | Dec 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED829 | Dts WM Rplmt in 4th Av fr Atlantic av to 64th ST-BK HWK1669B | 2 | PRELIMINARY DESIGN | Dec 2021 | Mar 2022 | Dec 2021 | Mar 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED829 | Dts WM Rplmt in 4th Av fr Atlantic av to 64th ST-BK HWK1669B | 3 | FINAL DESIGN | Apr 2022 | Sep 2022 | Apr 2022 | Sep 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED829 | Dts WM Rplmt in 4th Av fr Atlantic av to 64th ST-BK HWK1669B | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED829 | Dts WM Rplmt in 4th Av fr Atlantic av to 64th ST-BK HWK1669B | 5 | CONSTRUCTION TO 25% | Dec 2022 | Apr 2023 | Dec 2022 | Apr 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED829 | Dts WM Rplmt in 4th Av fr Atlantic av to 64th ST-BK HWK1669B | 6 | CONSTRUCTION TO 50% | Apr 2023 | Aug 2023 | Apr 2023 | Aug 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED829 | Dts WM Rplmt in 4th Av fr Atlantic av to 64th ST-BK HWK1669B | 7 | CONSTRUCTION TO 75% | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED829 | Dts WM Rplmt in 4th Av fr Atlantic av to 64th ST-BK HWK1669B | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2023 | Mar 2024 | Dec 2023 | Mar 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED829 | Dts WM Rplmt in 4th Av fr Atlantic av to 64th ST-BK HWK1669B | 9 | SUBSTANTIAL COMPLETION | Mar 2024 | May 2024 | Mar 2024 | May 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED829 | Dts WM Rplmt in 4th Av fr Atlantic av to 64th ST-BK HWK1669B | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Jun 2024 | May 2024 | Sep 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-830 | Rplment WM Park Ave btw Classon Ave & Ryerson (HWD007K03) | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-830 | Rplment WM Park Ave btw Classon Ave & Ryerson (HWD007K03) | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-830 | Rplment WM Park Ave btw Classon Ave & Ryerson (HWD007K03) | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-830 | Rplment WM Park Ave btw Classon Ave & Ryerson (HWD007K03) | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-830 | Rplment WM Park Ave btw Classon Ave & Ryerson (HWD007K03) | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-830 | Rplment WM Park Ave btw Classon Ave & Ryerson (HWD007K03) | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-830 | Rplment WM Park Ave btw Classon Ave & Ryerson (HWD007K03) | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | May 2024 | Sep 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-830 | Rplment WM Park Ave btw Classon Ave & Ryerson (HWD007K03) | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-830 | Rplment WM Park Ave btw Classon Ave & Ryerson (HWD007K03) | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Dec 2024 | Feb 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-830 | Rplment WM Park Ave btw Classon Ave & Ryerson (HWD007K03) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Mar 2025 | Feb 2025 | Mar 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-830 | Rplment WM Park Ave btw Classon Ave & Ryerson (HWD007K03) | 11 | PROJECT START | Feb 2025 | Mar 2025 | Mar 2025 | Apr 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-830 | Rplment WM Park Ave btw Classon Ave & Ryerson (HWD007K03) | 12 | DESIGN START | Feb 2025 | Mar 2025 | Apr 2025 | May 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-830 | Rplment WM Park Ave btw Classon Ave & Ryerson (HWD007K03) | 13 | DESIGN COMPLETION | Feb 2025 | Mar 2025 | May 2025 | Jun 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-830 | Rplment WM Park Ave btw Classon Ave & Ryerson (HWD007K03) | 14 | CONSTRUCTION START | Feb 2025 | Mar 2025 | Jun 2025 | Jul 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-830 | Rplment WM Park Ave btw Classon Ave & Ryerson (HWD007K03) | 15 | CONSTRUCTION COMPLETION | Feb 2025 | Mar 2025 | Jul 2025 | Apr 2028
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED833 | Rel.& Inst.WMs Flatland Ave bet Ralph Ave & E 76 St HWK2048 | 1 | DEVELOP SCOPE | Nov 2020 | Aug 2021 | Nov 2020 | Aug 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED833 | Rel.& Inst.WMs Flatland Ave bet Ralph Ave & E 76 St HWK2048 | 2 | PRELIMINARY DESIGN | Aug 2021 | Jul 2022 | Aug 2021 | Jul 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED833 | Rel.& Inst.WMs Flatland Ave bet Ralph Ave & E 76 St HWK2048 | 3 | FINAL DESIGN | Aug 2022 | Jan 2024 | Aug 2022 | Jan 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED833 | Rel.& Inst.WMs Flatland Ave bet Ralph Ave & E 76 St HWK2048 | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2024 | Oct 2024 | Jan 2024 | Oct 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED833 | Rel.& Inst.WMs Flatland Ave bet Ralph Ave & E 76 St HWK2048 | 5 | CONSTRUCTION TO 25% | Oct 2024 | Oct 2025 | Oct 2024 | Oct 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED833 | Rel.& Inst.WMs Flatland Ave bet Ralph Ave & E 76 St HWK2048 | 6 | CONSTRUCTION TO 50% | Oct 2025 | Oct 2026 | Oct 2025 | Oct 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED833 | Rel.& Inst.WMs Flatland Ave bet Ralph Ave & E 76 St HWK2048 | 7 | CONSTRUCTION TO 75% | Oct 2026 | Oct 2027 | Oct 2026 | Oct 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED833 | Rel.& Inst.WMs Flatland Ave bet Ralph Ave & E 76 St HWK2048 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jun 2028 | Oct 2027 | Jun 2028
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED833 | Rel.& Inst.WMs Flatland Ave bet Ralph Ave & E 76 St HWK2048 | 9 | SUBSTANTIAL COMPLETION | Jun 2028 | Dec 2028 | Jun 2028 | Dec 2028
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED833 | Rel.& Inst.WMs Flatland Ave bet Ralph Ave & E 76 St HWK2048 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2028 | Mar 2029 | Dec 2028 | Mar 2029
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 1 | DEVELOP SCOPE | Mar 2016 | May 2016 | Mar 2016 | May 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 2 | PRELIMINARY DESIGN | May 2016 | Sep 2016 | May 2016 | Sep 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 3 | FINAL DESIGN | Sep 2016 | Mar 2017 | Sep 2016 | Mar 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2017 | Jun 2017 | Mar 2017 | Jun 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 5 | CONSTRUCTION TO 25% | Jun 2017 | Oct 2017 | Jun 2017 | Oct 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 6 | CONSTRUCTION TO 50% | Oct 2017 | Feb 2018 | Oct 2017 | Feb 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 7 | CONSTRUCTION TO 75% | Feb 2018 | Jun 2018 | Feb 2018 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 9 | SUBSTANTIAL COMPLETION | Sep 2018 | Nov 2018 | Sep 2018 | Nov 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2018 | Dec 2018 | Nov 2018 | Jun 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CJCREN | FACIILITY RENOVATIONS AT CROSSROADS JC | 1 | DEVELOP SCOPE | Aug 2015 | Nov 2015 | Aug 2015 | Nov 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CJCREN | FACIILITY RENOVATIONS AT CROSSROADS JC | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2015 | Feb 2016 | Nov 2015 | Feb 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CJCREN | FACIILITY RENOVATIONS AT CROSSROADS JC | 3 | CONSTRUCTION TO 50% | Feb 2016 | Jun 2016 | Feb 2016 | Jun 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CJCREN | FACIILITY RENOVATIONS AT CROSSROADS JC | 4 | CONSTRUCTION TO 75% | Jun 2016 | Aug 2016 | Jun 2016 | Aug 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CJCREN | FACIILITY RENOVATIONS AT CROSSROADS JC | 5 | SUBSTANTIAL COMPLETION | Aug 2016 | Oct 2016 | Aug 2016 | Oct 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CJCREN | FACIILITY RENOVATIONS AT CROSSROADS JC | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Nov 2020 | Oct 2016 | Nov 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CJCREN | FACIILITY RENOVATIONS AT CROSSROADS JC | 7 | PROJECT START | Oct 2016 | Nov 2020 | Nov 2020 | Nov 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CJCREN | FACIILITY RENOVATIONS AT CROSSROADS JC | 8 | DESIGN START | Oct 2016 | Nov 2020 | Nov 2020 | Nov 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CJCREN | FACIILITY RENOVATIONS AT CROSSROADS JC | 9 | DESIGN COMPLETION | Oct 2016 | Nov 2020 | Nov 2020 | Nov 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CJCREN | FACIILITY RENOVATIONS AT CROSSROADS JC | 10 | CONSTRUCTION START | Oct 2016 | Nov 2020 | Nov 2020 | Nov 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CJCREN | FACIILITY RENOVATIONS AT CROSSROADS JC | 11 | CONSTRUCTION COMPLETION | Oct 2016 | Nov 2020 | Nov 2020 | Nov 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272DW2 | 45 MONROE PL- DRIVEWAY/PARKING LOT RECONSTRUCTION | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Aug 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272DW2 | 45 MONROE PL- DRIVEWAY/PARKING LOT RECONSTRUCTION | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272DW2 | 45 MONROE PL- DRIVEWAY/PARKING LOT RECONSTRUCTION | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272DW2 | 45 MONROE PL- DRIVEWAY/PARKING LOT RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272DW2 | 45 MONROE PL- DRIVEWAY/PARKING LOT RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272DW2 | 45 MONROE PL- DRIVEWAY/PARKING LOT RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2022 | May 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272DW2 | 45 MONROE PL- DRIVEWAY/PARKING LOT RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2022 | Sep 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272DW2 | 45 MONROE PL- DRIVEWAY/PARKING LOT RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272DW2 | 45 MONROE PL- DRIVEWAY/PARKING LOT RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2022 | Dec 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272DW2 | 45 MONROE PL- DRIVEWAY/PARKING LOT RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Dec 2023 | Jun 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | 1 | DEVELOP SCOPE | Sep 2012 | Nov 2012 | Sep 2012 | Nov 2012
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | 2 | PRELIMINARY DESIGN | Nov 2012 | Mar 2013 | Nov 2012 | Mar 2013
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | 3 | FINAL DESIGN | Apr 2013 | Sep 2013 | Apr 2013 | Sep 2013
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | 5 | CONSTRUCTION TO 25% | Dec 2013 | Apr 2014 | Dec 2013 | Apr 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | 6 | CONSTRUCTION TO 50% | Apr 2014 | Aug 2014 | Apr 2014 | Aug 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | 7 | CONSTRUCTION TO 75% | Aug 2014 | Dec 2014 | Aug 2014 | Dec 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2014 | Mar 2015 | Dec 2014 | Mar 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | 9 | SUBSTANTIAL COMPLETION | Mar 2015 | May 2015 | Mar 2015 | May 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2015 | Jun 2015 | May 2015 | Jun 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | 11 | PROJECT START | May 2015 | Jun 2015 | Jun 2020 | Jun 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | 12 | DESIGN START | May 2015 | Jun 2015 | Jun 2020 | Jun 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | 13 | DESIGN COMPLETION | May 2015 | Jun 2015 | Jun 2020 | Jun 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | 14 | CONSTRUCTION START | May 2015 | Jun 2015 | Jun 2020 | Jun 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | 15 | CONSTRUCTION COMPLETION | May 2015 | Jun 2015 | Jun 2020 | Jun 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELV2 | 45 MONROE PL. - ELEVATOR | 1 | PROJECT START | Sep 2014 | Sep 2014 | Jul 2012 | Jul 2012
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELV2 | 45 MONROE PL. - ELEVATOR | 2 | DESIGN START | Sep 2014 | Sep 2014 | Jul 2012 | Jan 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELV2 | 45 MONROE PL. - ELEVATOR | 3 | DESIGN COMPLETION | Sep 2014 | Sep 2014 | Jan 2016 | Apr 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELV2 | 45 MONROE PL. - ELEVATOR | 4 | CONSTRUCTION START | Sep 2014 | Sep 2014 | Apr 2017 | Mar 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELV2 | 45 MONROE PL. - ELEVATOR | 5 | CONSTRUCTION COMPLETION | Sep 2014 | Sep 2014 | Apr 2019 | Jun 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR & ROOF | 1 | DEVELOP SCOPE | Mar 2020 | May 2020 | Mar 2020 | May 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR & ROOF | 2 | PRELIMINARY DESIGN | May 2020 | Sep 2020 | May 2020 | Sep 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR & ROOF | 3 | FINAL DESIGN | Sep 2020 | Mar 2021 | Sep 2020 | Mar 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR & ROOF | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2021 | Jun 2021 | Mar 2021 | Jun 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR & ROOF | 5 | CONSTRUCTION TO 25% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR & ROOF | 6 | CONSTRUCTION TO 50% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR & ROOF | 7 | CONSTRUCTION TO 75% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR & ROOF | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR & ROOF | 9 | SUBSTANTIAL COMPLETION | Sep 2022 | Nov 2022 | Sep 2022 | Nov 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR & ROOF | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2022 | Dec 2022 | Nov 2022 | Nov 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR & ROOF | 11 | PROJECT START | Dec 2022 | Dec 2022 | Nov 2024 | Nov 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR & ROOF | 12 | DESIGN START | Dec 2022 | Dec 2022 | Nov 2024 | Nov 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR & ROOF | 13 | DESIGN COMPLETION | Dec 2022 | Dec 2022 | Nov 2024 | Nov 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR & ROOF | 14 | CONSTRUCTION START | Dec 2022 | Dec 2022 | Nov 2024 | Nov 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR & ROOF | 15 | CONSTRUCTION COMPLETION | Dec 2022 | Dec 2022 | Nov 2024 | Nov 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 1 | DEVELOP SCOPE | Dec 2014 | Feb 2015 | Dec 2014 | Feb 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 2 | PRELIMINARY DESIGN | Mar 2015 | Jun 2015 | Mar 2015 | Feb 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 3 | FINAL DESIGN | Jun 2015 | Dec 2015 | Feb 2017 | Jan 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | Dec 2015 | Mar 2016 | Jan 2021 | Apr 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 5 | CONSTRUCTION TO 25% | Mar 2016 | Jul 2016 | Apr 2021 | Aug 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 6 | CONSTRUCTION TO 50% | Jul 2016 | Nov 2016 | Aug 2021 | Dec 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 7 | CONSTRUCTION TO 75% | Nov 2016 | Mar 2017 | Dec 2021 | Apr 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2017 | Jun 2017 | Apr 2022 | Jul 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 9 | SUBSTANTIAL COMPLETION | Jun 2017 | Aug 2017 | Jul 2022 | Sep 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2017 | Sep 2017 | Sep 2022 | Sep 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 11 | PROJECT START | Aug 2017 | Sep 2017 | Sep 2026 | Sep 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 12 | DESIGN START | Aug 2017 | Sep 2017 | Sep 2026 | Sep 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 13 | DESIGN COMPLETION | Aug 2017 | Sep 2017 | Sep 2026 | Sep 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 14 | CONSTRUCTION START | Aug 2017 | Sep 2017 | Sep 2026 | Sep 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 15 | CONSTRUCTION COMPLETION | Aug 2017 | Sep 2017 | Sep 2026 | Sep 2030
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 1 | DEVELOP SCOPE | May 2015 | Jul 2015 | May 2015 | Jul 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 2 | PRELIMINARY DESIGN | Jul 2015 | Nov 2015 | Jul 2015 | Nov 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 3 | FINAL DESIGN | Nov 2015 | May 2016 | Nov 2015 | Jan 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | May 2016 | Aug 2016 | Jan 2020 | Apr 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 5 | CONSTRUCTION TO 25% | Aug 2016 | Dec 2016 | Apr 2020 | Aug 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 6 | CONSTRUCTION TO 50% | Dec 2016 | Apr 2017 | Aug 2020 | Dec 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 7 | CONSTRUCTION TO 75% | Apr 2017 | Aug 2017 | Dec 2020 | Apr 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | Aug 2017 | Nov 2017 | Apr 2021 | Jul 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 9 | SUBSTANTIAL COMPLETION | Nov 2017 | Jan 2018 | Jul 2021 | Aug 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2018 | Feb 2018 | Sep 2021 | Feb 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 11 | PROJECT START | Jan 2018 | Feb 2018 | Feb 2023 | Feb 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 12 | DESIGN START | Jan 2018 | Feb 2018 | Feb 2023 | Feb 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 13 | DESIGN COMPLETION | Jan 2018 | Feb 2018 | Feb 2023 | Feb 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 14 | CONSTRUCTION START | Jan 2018 | Feb 2018 | Feb 2023 | Feb 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 15 | CONSTRUCTION COMPLETION | Jan 2018 | Feb 2018 | Feb 2023 | Mar 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH04 | SAN & STRM SWR, WM1, IN CONEY ISL AREA, PH 4 | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH04 | SAN & STRM SWR, WM1, IN CONEY ISL AREA, PH 4 | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH04 | SAN & STRM SWR, WM1, IN CONEY ISL AREA, PH 4 | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH04 | SAN & STRM SWR, WM1, IN CONEY ISL AREA, PH 4 | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH04 | SAN & STRM SWR, WM1, IN CONEY ISL AREA, PH 4 | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Jan 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH04 | SAN & STRM SWR, WM1, IN CONEY ISL AREA, PH 4 | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Jan 2019 | Jul 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH04 | SAN & STRM SWR, WM1, IN CONEY ISL AREA, PH 4 | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Jul 2019 | Feb 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH04 | SAN & STRM SWR, WM1, IN CONEY ISL AREA, PH 4 | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Feb 2020 | May 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH04 | SAN & STRM SWR, WM1, IN CONEY ISL AREA, PH 4 | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | May 2020 | Jul 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH04 | SAN & STRM SWR, WM1, IN CONEY ISL AREA, PH 4 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Jul 2020 | Feb 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH04 | SAN & STRM SWR, WM1, IN CONEY ISL AREA, PH 4 | 11 | PROJECT START | Nov 2019 | Dec 2019 | Feb 2025 | Feb 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH04 | SAN & STRM SWR, WM1, IN CONEY ISL AREA, PH 4 | 12 | DESIGN START | Nov 2019 | Dec 2019 | Feb 2025 | Feb 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH04 | SAN & STRM SWR, WM1, IN CONEY ISL AREA, PH 4 | 13 | DESIGN COMPLETION | Nov 2019 | Dec 2019 | Feb 2025 | Feb 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH04 | SAN & STRM SWR, WM1, IN CONEY ISL AREA, PH 4 | 14 | CONSTRUCTION START | Nov 2019 | Dec 2019 | Mar 2025 | Mar 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH04 | SAN & STRM SWR, WM1, IN CONEY ISL AREA, PH 4 | 15 | CONSTRUCTION COMPLETION | Nov 2019 | Dec 2019 | Mar 2025 | Jun 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH3A | Storm and Sanitary Sewer, Trunk and Distribution Water Main | 1 | DEVELOP SCOPE | Mar 2016 | May 2016 | Mar 2016 | May 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH3A | Storm and Sanitary Sewer, Trunk and Distribution Water Main | 2 | PRELIMINARY DESIGN | May 2016 | Sep 2016 | May 2016 | Sep 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH3A | Storm and Sanitary Sewer, Trunk and Distribution Water Main | 3 | FINAL DESIGN | Sep 2016 | Mar 2017 | Sep 2016 | Mar 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH3A | Storm and Sanitary Sewer, Trunk and Distribution Water Main | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2017 | Jun 2017 | Mar 2017 | Jun 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH3A | Storm and Sanitary Sewer, Trunk and Distribution Water Main | 5 | CONSTRUCTION TO 25% | Jun 2017 | Oct 2017 | Jun 2017 | Oct 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH3A | Storm and Sanitary Sewer, Trunk and Distribution Water Main | 6 | CONSTRUCTION TO 50% | Oct 2017 | Feb 2018 | Oct 2017 | Feb 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH3A | Storm and Sanitary Sewer, Trunk and Distribution Water Main | 7 | CONSTRUCTION TO 75% | Feb 2018 | Jun 2018 | Feb 2018 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH3A | Storm and Sanitary Sewer, Trunk and Distribution Water Main | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH3A | Storm and Sanitary Sewer, Trunk and Distribution Water Main | 9 | SUBSTANTIAL COMPLETION | Sep 2018 | Nov 2018 | Sep 2018 | Nov 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH3A | Storm and Sanitary Sewer, Trunk and Distribution Water Main | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2018 | Dec 2018 | Nov 2018 | Mar 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E12-0043 | NYPD 84th Precinct - EE Upgrade | 1 | PROJECT START | Jun 2012 | Jun 2012 | Oct 2012 | Oct 2012
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E12-0043 | NYPD 84th Precinct - EE Upgrade | 2 | DESIGN START | Jun 2012 | Jun 2012 | Jun 2013 | Oct 2013
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E12-0043 | NYPD 84th Precinct - EE Upgrade | 3 | DESIGN COMPLETION | Jun 2012 | Jun 2012 | Jul 2014 | Jan 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E12-0043 | NYPD 84th Precinct - EE Upgrade | 4 | CONSTRUCTION START | Jun 2012 | Jun 2013 | Jan 2015 | Jul 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E12-0043 | NYPD 84th Precinct - EE Upgrade | 5 | CONSTRUCTION COMPLETION | Jun 2013 | Jun 2014 | Oct 2015 | Sep 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0006 | DSNY - BROOKLYN NORTH 1 DISTRICT &4 DISTRICT GARAGE | 1 | DEVELOP SCOPE | Mar 2019 | May 2019 | Mar 2019 | May 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0006 | DSNY - BROOKLYN NORTH 1 DISTRICT &4 DISTRICT GARAGE | 2 | PRELIMINARY DESIGN | May 2019 | Sep 2019 | May 2019 | Sep 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0006 | DSNY - BROOKLYN NORTH 1 DISTRICT &4 DISTRICT GARAGE | 3 | FINAL DESIGN | Sep 2019 | Mar 2020 | Sep 2019 | Mar 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0006 | DSNY - BROOKLYN NORTH 1 DISTRICT &4 DISTRICT GARAGE | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Jun 2020 | Mar 2020 | Jun 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0006 | DSNY - BROOKLYN NORTH 1 DISTRICT &4 DISTRICT GARAGE | 5 | CONSTRUCTION TO 25% | Jun 2020 | Oct 2020 | Jun 2020 | Oct 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0006 | DSNY - BROOKLYN NORTH 1 DISTRICT &4 DISTRICT GARAGE | 6 | CONSTRUCTION TO 50% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0006 | DSNY - BROOKLYN NORTH 1 DISTRICT &4 DISTRICT GARAGE | 7 | CONSTRUCTION TO 75% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0006 | DSNY - BROOKLYN NORTH 1 DISTRICT &4 DISTRICT GARAGE | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0006 | DSNY - BROOKLYN NORTH 1 DISTRICT &4 DISTRICT GARAGE | 9 | SUBSTANTIAL COMPLETION | Sep 2021 | Nov 2021 | Sep 2021 | Nov 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0006 | DSNY - BROOKLYN NORTH 1 DISTRICT &4 DISTRICT GARAGE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2021 | Dec 2021 | Nov 2021 | Jun 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0006 | DSNY - BROOKLYN NORTH 1 DISTRICT &4 DISTRICT GARAGE | 11 | PROJECT START | Nov 2021 | Dec 2021 | Jul 2024 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0006 | DSNY - BROOKLYN NORTH 1 DISTRICT &4 DISTRICT GARAGE | 12 | DESIGN START | Nov 2021 | Dec 2021 | Jul 2024 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0006 | DSNY - BROOKLYN NORTH 1 DISTRICT &4 DISTRICT GARAGE | 13 | DESIGN COMPLETION | Nov 2021 | Dec 2021 | Jul 2024 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0006 | DSNY - BROOKLYN NORTH 1 DISTRICT &4 DISTRICT GARAGE | 14 | CONSTRUCTION START | Nov 2021 | Dec 2021 | Jul 2024 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0006 | DSNY - BROOKLYN NORTH 1 DISTRICT &4 DISTRICT GARAGE | 15 | CONSTRUCTION COMPLETION | Nov 2021 | Dec 2021 | Jul 2024 | Jul 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKN23 | Reconstruction of Existing Sewers, North Brooklyn | 1 | DEVELOP SCOPE | Sep 2021 | Dec 2021 | Sep 2021 | Dec 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKN23 | Reconstruction of Existing Sewers, North Brooklyn | 2 | PRELIMINARY DESIGN | Dec 2021 | Apr 2022 | Dec 2021 | Apr 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKN23 | Reconstruction of Existing Sewers, North Brooklyn | 3 | FINAL DESIGN | Apr 2022 | Oct 2022 | Apr 2022 | Oct 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKN23 | Reconstruction of Existing Sewers, North Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKN23 | Reconstruction of Existing Sewers, North Brooklyn | 5 | CONSTRUCTION TO 25% | Jan 2023 | May 2023 | Jan 2023 | May 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKN23 | Reconstruction of Existing Sewers, North Brooklyn | 6 | CONSTRUCTION TO 50% | May 2023 | Sep 2023 | May 2023 | Sep 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKN23 | Reconstruction of Existing Sewers, North Brooklyn | 7 | CONSTRUCTION TO 75% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKN23 | Reconstruction of Existing Sewers, North Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2024 | Apr 2024 | Jan 2024 | Apr 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKN23 | Reconstruction of Existing Sewers, North Brooklyn | 9 | SUBSTANTIAL COMPLETION | Apr 2024 | Jun 2024 | Apr 2024 | Jun 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKN23 | Reconstruction of Existing Sewers, North Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2024 | Jul 2024 | Jun 2024 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKN24 | Reconstruction of Existing Sewers, North Brooklyn | 1 | DEVELOP SCOPE | Jun 2024 | Aug 2024 | Jun 2024 | Aug 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKN24 | Reconstruction of Existing Sewers, North Brooklyn | 2 | PRELIMINARY DESIGN | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKN24 | Reconstruction of Existing Sewers, North Brooklyn | 3 | FINAL DESIGN | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKN24 | Reconstruction of Existing Sewers, North Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKN24 | Reconstruction of Existing Sewers, North Brooklyn | 5 | CONSTRUCTION TO 25% | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKN24 | Reconstruction of Existing Sewers, North Brooklyn | 6 | CONSTRUCTION TO 50% | Jan 2026 | May 2026 | Jan 2026 | May 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKN24 | Reconstruction of Existing Sewers, North Brooklyn | 7 | CONSTRUCTION TO 75% | May 2026 | Sep 2026 | May 2026 | Sep 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKN24 | Reconstruction of Existing Sewers, North Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2026 | Dec 2026 | Sep 2026 | Dec 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKN24 | Reconstruction of Existing Sewers, North Brooklyn | 9 | SUBSTANTIAL COMPLETION | Dec 2026 | Feb 2027 | Dec 2026 | Feb 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKN24 | Reconstruction of Existing Sewers, North Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2027 | Mar 2027 | Feb 2027 | Mar 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKS23 | Reconstruction of Existing Sewers, South Brooklyn | 1 | DEVELOP SCOPE | Sep 2021 | Dec 2021 | Sep 2021 | Dec 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKS23 | Reconstruction of Existing Sewers, South Brooklyn | 2 | PRELIMINARY DESIGN | Dec 2021 | Apr 2022 | Dec 2021 | Apr 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKS23 | Reconstruction of Existing Sewers, South Brooklyn | 3 | FINAL DESIGN | Apr 2022 | Oct 2022 | Apr 2022 | Oct 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKS23 | Reconstruction of Existing Sewers, South Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKS23 | Reconstruction of Existing Sewers, South Brooklyn | 5 | CONSTRUCTION TO 25% | Jan 2023 | May 2023 | Jan 2023 | May 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKS23 | Reconstruction of Existing Sewers, South Brooklyn | 6 | CONSTRUCTION TO 50% | May 2023 | Sep 2023 | May 2023 | Sep 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKS23 | Reconstruction of Existing Sewers, South Brooklyn | 7 | CONSTRUCTION TO 75% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKS23 | Reconstruction of Existing Sewers, South Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2024 | Apr 2024 | Jan 2024 | Apr 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKS23 | Reconstruction of Existing Sewers, South Brooklyn | 9 | SUBSTANTIAL COMPLETION | Apr 2024 | Jun 2024 | Apr 2024 | Jun 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKS23 | Reconstruction of Existing Sewers, South Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2024 | Jul 2024 | Jun 2024 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKS24 | Reconstruction of Existing Sewers, South Brooklyn | 1 | DEVELOP SCOPE | Jun 2024 | Aug 2024 | Jun 2024 | Aug 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKS24 | Reconstruction of Existing Sewers, South Brooklyn | 2 | PRELIMINARY DESIGN | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKS24 | Reconstruction of Existing Sewers, South Brooklyn | 3 | FINAL DESIGN | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKS24 | Reconstruction of Existing Sewers, South Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKS24 | Reconstruction of Existing Sewers, South Brooklyn | 5 | CONSTRUCTION TO 25% | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKS24 | Reconstruction of Existing Sewers, South Brooklyn | 6 | CONSTRUCTION TO 50% | Jan 2026 | May 2026 | Jan 2026 | May 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKS24 | Reconstruction of Existing Sewers, South Brooklyn | 7 | CONSTRUCTION TO 75% | May 2026 | Sep 2026 | May 2026 | Sep 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKS24 | Reconstruction of Existing Sewers, South Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2026 | Dec 2026 | Sep 2026 | Dec 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKS24 | Reconstruction of Existing Sewers, South Brooklyn | 9 | SUBSTANTIAL COMPLETION | Dec 2026 | Feb 2027 | Dec 2026 | Feb 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKS24 | Reconstruction of Existing Sewers, South Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2027 | Mar 2027 | Feb 2027 | Mar 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EP6-KENT2 | 356 FLUSING, BUILDING REPAIR/UPGRADE | 1 | PROJECT START | Sep 2003 | Sep 2003 | Sep 2006 | Sep 2006
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EP6-KENT2 | 356 FLUSING, BUILDING REPAIR/UPGRADE | 2 | DESIGN START | Sep 2003 | Jun 2005 | Sep 2006 | Jun 2008
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EP6-KENT2 | 356 FLUSING, BUILDING REPAIR/UPGRADE | 3 | DESIGN COMPLETION | Jun 2005 | Sep 2006 | Jun 2008 | Jan 2010
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EP6-KENT2 | 356 FLUSING, BUILDING REPAIR/UPGRADE | 4 | CONSTRUCTION START | Sep 2006 | Sep 2006 | Jan 2010 | Aug 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EP6-KENT2 | 356 FLUSING, BUILDING REPAIR/UPGRADE | 5 | CONSTRUCTION COMPLETION | Sep 2006 | Sep 2006 | Aug 2014 | Jun 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKCI05-1A | GI- CONS OF ROW GREEN INFRASTRUCTURE IN CI-005 PHASE 1A | 1 | FINAL DESIGN | Mar 2022 | Aug 2023 | Mar 2022 | Aug 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKCI05-1A | GI- CONS OF ROW GREEN INFRASTRUCTURE IN CI-005 PHASE 1A | 2 | CONSTRUCTION TO 25% | Aug 2023 | Apr 2024 | Aug 2023 | Apr 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKCI05-1A | GI- CONS OF ROW GREEN INFRASTRUCTURE IN CI-005 PHASE 1A | 3 | CONSTRUCTION TO 50% | Apr 2024 | Dec 2024 | Apr 2024 | Dec 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKCI05-1A | GI- CONS OF ROW GREEN INFRASTRUCTURE IN CI-005 PHASE 1A | 4 | CONSTRUCTION TO 75% | Dec 2024 | Aug 2025 | Dec 2024 | Aug 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKCI05-2A | GI- CONS OF ROW GREEN INFRASTRUCTURE IN CI-005 PHASE 2A | 1 | FINAL DESIGN | Jul 2023 | Dec 2024 | Jul 2000 | Jul 2000
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKCI05-2A | GI- CONS OF ROW GREEN INFRASTRUCTURE IN CI-005 PHASE 2A | 2 | CONSTRUCTION TO 25% | Dec 2024 | Aug 2025 | Jul 2000 | Feb 2001
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKCI05-2A | GI- CONS OF ROW GREEN INFRASTRUCTURE IN CI-005 PHASE 2A | 3 | CONSTRUCTION TO 50% | Aug 2025 | Apr 2026 | Feb 2001 | Oct 2001
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKCI05-2A | GI- CONS OF ROW GREEN INFRASTRUCTURE IN CI-005 PHASE 2A | 4 | CONSTRUCTION TO 75% | Apr 2026 | Dec 2026 | Oct 2001 | Jun 2002
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKCI05-2A | GI- CONS OF ROW GREEN INFRASTRUCTURE IN CI-005 PHASE 2A | 5 | PROJECT START | Apr 2026 | Dec 2026 | Jun 2022 | Jun 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKCI05-2A | GI- CONS OF ROW GREEN INFRASTRUCTURE IN CI-005 PHASE 2A | 6 | DESIGN START | Apr 2026 | Dec 2026 | Jul 2024 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKCI05-2A | GI- CONS OF ROW GREEN INFRASTRUCTURE IN CI-005 PHASE 2A | 7 | DESIGN COMPLETION | Apr 2026 | Dec 2026 | Jul 2024 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKCI05-2A | GI- CONS OF ROW GREEN INFRASTRUCTURE IN CI-005 PHASE 2A | 8 | CONSTRUCTION START | Apr 2026 | Dec 2026 | Jul 2024 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKCI05-2A | GI- CONS OF ROW GREEN INFRASTRUCTURE IN CI-005 PHASE 2A | 9 | CONSTRUCTION COMPLETION | Apr 2026 | Dec 2026 | Jul 2024 | Jul 2032
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKCI05-3A | GI- CONS OF ROW GREEN INFRASTRUCTURE IN CI-005 PHASE 3A | 1 | FINAL DESIGN | Jul 2022 | Dec 2023 | Jul 2022 | Dec 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKCI05-3A | GI- CONS OF ROW GREEN INFRASTRUCTURE IN CI-005 PHASE 3A | 2 | CONSTRUCTION TO 25% | Dec 2023 | Aug 2024 | Dec 2023 | Aug 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKCI05-3A | GI- CONS OF ROW GREEN INFRASTRUCTURE IN CI-005 PHASE 3A | 3 | CONSTRUCTION TO 50% | Aug 2024 | Apr 2025 | Aug 2024 | Apr 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKCI05-3A | GI- CONS OF ROW GREEN INFRASTRUCTURE IN CI-005 PHASE 3A | 4 | CONSTRUCTION TO 75% | Apr 2025 | Dec 2025 | Apr 2025 | Dec 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-01 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 1 | 1 | DEVELOP SCOPE | Mar 2016 | May 2016 | Mar 2016 | May 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-01 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 1 | 2 | PRELIMINARY DESIGN | May 2016 | Sep 2016 | May 2016 | Sep 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-01 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 1 | 3 | FINAL DESIGN | Sep 2016 | Mar 2017 | Sep 2016 | Mar 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-01 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 1 | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2017 | Jun 2017 | Mar 2017 | Jun 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-01 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 1 | 5 | CONSTRUCTION TO 25% | Jun 2017 | Oct 2017 | Jun 2017 | Oct 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-01 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 1 | 6 | CONSTRUCTION TO 50% | Oct 2017 | Feb 2018 | Oct 2017 | Feb 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-01 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 1 | 7 | CONSTRUCTION TO 75% | Feb 2018 | Jun 2018 | Feb 2018 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-01 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 1 | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-01 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 1 | 9 | SUBSTANTIAL COMPLETION | Sep 2018 | Nov 2018 | Sep 2018 | Nov 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-01 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 1 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2018 | Dec 2018 | Nov 2018 | Oct 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-02 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 2 | 1 | DEVELOP SCOPE | Mar 2016 | May 2016 | Mar 2016 | May 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-02 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 2 | 2 | PRELIMINARY DESIGN | May 2016 | Sep 2016 | May 2016 | Sep 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-02 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 2 | 3 | FINAL DESIGN | Sep 2016 | Mar 2017 | Sep 2016 | Mar 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-02 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 2 | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2017 | Jun 2017 | Mar 2017 | Jun 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-02 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 2 | 5 | CONSTRUCTION TO 25% | Jun 2017 | Oct 2017 | Jun 2017 | Oct 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-02 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 2 | 6 | CONSTRUCTION TO 50% | Oct 2017 | Feb 2018 | Oct 2017 | Feb 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-02 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 2 | 7 | CONSTRUCTION TO 75% | Feb 2018 | Jun 2018 | Feb 2018 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-02 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 2 | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-02 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 2 | 9 | SUBSTANTIAL COMPLETION | Sep 2018 | Nov 2018 | Sep 2018 | Nov 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-02 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2018 | Dec 2018 | Nov 2018 | Jun 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-03 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 3 | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Aug 2015 | Oct 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-03 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 3 | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | Oct 2015 | Feb 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-03 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 3 | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Feb 2016 | Aug 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-03 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 3 | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Aug 2018 | Nov 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-03 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 3 | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Nov 2018 | Mar 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-03 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 3 | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Mar 2019 | Jul 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-03 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 3 | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Jul 2019 | Nov 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-03 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 3 | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Nov 2019 | Feb 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-03 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 3 | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Feb 2020 | Apr 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-03 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 3 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Apr 2020 | Jul 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-03 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 3 | 11 | PROJECT START | Nov 2019 | Dec 2019 | Jul 2022 | Jul 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-03 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 3 | 12 | DESIGN START | Nov 2019 | Dec 2019 | Jul 2022 | Jul 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-03 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 3 | 13 | DESIGN COMPLETION | Nov 2019 | Dec 2019 | Aug 2022 | Aug 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-03 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 3 | 14 | CONSTRUCTION START | Nov 2019 | Dec 2019 | Aug 2022 | Aug 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-03 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 3 | 15 | CONSTRUCTION COMPLETION | Nov 2019 | Dec 2019 | Aug 2022 | Nov 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-04 | GI - GREEN INFRA, OH-015 GRAVESEND BAY CSO PH4 | 1 | DEVELOP SCOPE | Jun 2018 | Mar 2019 | Jun 2018 | Mar 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-04 | GI - GREEN INFRA, OH-015 GRAVESEND BAY CSO PH4 | 2 | PRELIMINARY DESIGN | Mar 2019 | Mar 2020 | Mar 2019 | Mar 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-04 | GI - GREEN INFRA, OH-015 GRAVESEND BAY CSO PH4 | 3 | FINAL DESIGN | Mar 2020 | Aug 2021 | Mar 2020 | Aug 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-04 | GI - GREEN INFRA, OH-015 GRAVESEND BAY CSO PH4 | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2021 | May 2022 | Aug 2021 | May 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-04 | GI - GREEN INFRA, OH-015 GRAVESEND BAY CSO PH4 | 5 | CONSTRUCTION TO 25% | May 2022 | May 2023 | May 2022 | May 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-04 | GI - GREEN INFRA, OH-015 GRAVESEND BAY CSO PH4 | 6 | CONSTRUCTION TO 50% | May 2023 | May 2024 | May 2023 | May 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-04 | GI - GREEN INFRA, OH-015 GRAVESEND BAY CSO PH4 | 7 | CONSTRUCTION TO 75% | May 2024 | May 2025 | May 2024 | May 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-04 | GI - GREEN INFRA, OH-015 GRAVESEND BAY CSO PH4 | 8 | ORIGINAL EQUIP & FURNISHING | May 2025 | Feb 2026 | May 2025 | Feb 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-04 | GI - GREEN INFRA, OH-015 GRAVESEND BAY CSO PH4 | 9 | SUBSTANTIAL COMPLETION | Feb 2026 | Aug 2026 | Feb 2026 | Aug 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-04 | GI - GREEN INFRA, OH-015 GRAVESEND BAY CSO PH4 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2026 | Oct 2026 | Aug 2026 | Oct 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-DB | GI-DSGN BUILD ROW GI PH 4 OH-15 GRAVESEND BAY CSO TRIB AREA | 2 | CONSTRUCTION TO 25% | Oct 2023 | Jun 2024 | Oct 2023 | Jun 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-DB | GI-DSGN BUILD ROW GI PH 4 OH-15 GRAVESEND BAY CSO TRIB AREA | 3 | CONSTRUCTION TO 50% | Jun 2024 | Feb 2025 | Jun 2024 | Feb 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-DB | GI-DSGN BUILD ROW GI PH 4 OH-15 GRAVESEND BAY CSO TRIB AREA | 4 | CONSTRUCTION TO 75% | Feb 2025 | Oct 2025 | Feb 2025 | Oct 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM14GOCC | GOWANUS COMMUNITY CENTER RENOVATIONS | 1 | DESIGN | Jan 2014 | Jun 2014 | Jan 2014 | Jun 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM14GOCC | GOWANUS COMMUNITY CENTER RENOVATIONS | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2014 | Nov 2014 | Jun 2014 | Nov 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM14GOCC | GOWANUS COMMUNITY CENTER RENOVATIONS | 3 | CONSTRUCTION | Nov 2014 | Nov 2015 | Nov 2014 | Nov 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM14GOCC | GOWANUS COMMUNITY CENTER RENOVATIONS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2015 | May 2016 | Nov 2014 | Nov 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM14GOCC | GOWANUS COMMUNITY CENTER RENOVATIONS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2015 | May 2016 | Nov 2015 | Nov 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17GHSE | MARLBOROUGH HOUSES BSCAH GREENHOUSE DESIGN BUILD | 1 | DESIGN | Feb 2017 | Jul 2017 | Jul 2019 | Jul 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17GHSE | MARLBOROUGH HOUSES BSCAH GREENHOUSE DESIGN BUILD | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Dec 2017 | Jul 2019 | Jul 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17GHSE | MARLBOROUGH HOUSES BSCAH GREENHOUSE DESIGN BUILD | 3 | CONSTRUCTION | Dec 2017 | Dec 2018 | Jul 2019 | Jul 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17GHSE | MARLBOROUGH HOUSES BSCAH GREENHOUSE DESIGN BUILD | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2018 | Jun 2019 | Jul 2019 | Jul 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17GHSE | MARLBOROUGH HOUSES BSCAH GREENHOUSE DESIGN BUILD | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2018 | Jun 2019 | Jul 2019 | Jul 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17GHSE | MARLBOROUGH HOUSES BSCAH GREENHOUSE DESIGN BUILD | 7 | PROJECT START | Dec 2018 | Jun 2019 | Jul 2019 | Jul 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17GHSE | MARLBOROUGH HOUSES BSCAH GREENHOUSE DESIGN BUILD | 8 | DESIGN START | Dec 2018 | Jun 2019 | Jul 2019 | Jul 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17GHSE | MARLBOROUGH HOUSES BSCAH GREENHOUSE DESIGN BUILD | 9 | DESIGN COMPLETION | Dec 2018 | Jun 2019 | Jul 2019 | Jan 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17GHSE | MARLBOROUGH HOUSES BSCAH GREENHOUSE DESIGN BUILD | 10 | CONSTRUCTION START | Dec 2018 | Jun 2019 | Jan 2021 | Oct 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17GHSE | MARLBOROUGH HOUSES BSCAH GREENHOUSE DESIGN BUILD | 11 | CONSTRUCTION COMPLETION | Dec 2018 | Jun 2019 | Oct 2021 | Oct 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17MRCC | MARCY HOUSES - RENOVATE 492 MARCY AVE INTO A COMM CENTER | 1 | DESIGN | Feb 2017 | Jul 2017 | Feb 2017 | Feb 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17MRCC | MARCY HOUSES - RENOVATE 492 MARCY AVE INTO A COMM CENTER | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Dec 2017 | Feb 2017 | Feb 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17MRCC | MARCY HOUSES - RENOVATE 492 MARCY AVE INTO A COMM CENTER | 3 | CONSTRUCTION | Dec 2017 | Dec 2018 | Feb 2017 | Feb 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17MRCC | MARCY HOUSES - RENOVATE 492 MARCY AVE INTO A COMM CENTER | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2018 | Jun 2019 | Feb 2017 | Feb 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17MRCC | MARCY HOUSES - RENOVATE 492 MARCY AVE INTO A COMM CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2018 | Jun 2019 | Feb 2017 | Feb 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17MRCC | MARCY HOUSES - RENOVATE 492 MARCY AVE INTO A COMM CENTER | 7 | PROJECT START | Dec 2018 | Jun 2019 | Feb 2017 | Feb 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17MRCC | MARCY HOUSES - RENOVATE 492 MARCY AVE INTO A COMM CENTER | 8 | DESIGN START | Dec 2018 | Jun 2019 | Feb 2017 | Nov 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17MRCC | MARCY HOUSES - RENOVATE 492 MARCY AVE INTO A COMM CENTER | 9 | DESIGN COMPLETION | Dec 2018 | Jun 2019 | Nov 2017 | Apr 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17MRCC | MARCY HOUSES - RENOVATE 492 MARCY AVE INTO A COMM CENTER | 10 | CONSTRUCTION START | Dec 2018 | Jun 2019 | May 2018 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17MRCC | MARCY HOUSES - RENOVATE 492 MARCY AVE INTO A COMM CENTER | 11 | CONSTRUCTION COMPLETION | Dec 2018 | Jun 2019 | Jun 2018 | Jun 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM20BVBG | VAN DYKE BOXING GYM | 1 | DESIGN | Sep 2019 | Feb 2020 | Sep 2019 | Feb 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM20BVBG | VAN DYKE BOXING GYM | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Aug 2020 | Feb 2020 | Aug 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM20BVBG | VAN DYKE BOXING GYM | 3 | CONSTRUCTION | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM20BVBG | VAN DYKE BOXING GYM | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2020 | Aug 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM20BVBG | VAN DYKE BOXING GYM | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2021 | Feb 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM20BVBG | VAN DYKE BOXING GYM | 7 | PROJECT START | Aug 2021 | Feb 2022 | Sep 2019 | Feb 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM20BVBG | VAN DYKE BOXING GYM | 8 | DESIGN START | Aug 2021 | Feb 2022 | Feb 2020 | Feb 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM20BVBG | VAN DYKE BOXING GYM | 9 | DESIGN COMPLETION | Aug 2021 | Feb 2022 | Feb 2020 | Feb 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM20BVBG | VAN DYKE BOXING GYM | 10 | CONSTRUCTION START | Aug 2021 | Feb 2022 | Mar 2020 | Mar 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM20BVBG | VAN DYKE BOXING GYM | 11 | CONSTRUCTION COMPLETION | Aug 2021 | Feb 2022 | Mar 2020 | Jun 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM20BVCC | BROWNSVILLE COMMUNITY CENTER | 1 | DESIGN | Sep 2019 | Feb 2020 | Sep 2019 | Feb 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM20BVCC | BROWNSVILLE COMMUNITY CENTER | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Aug 2020 | Feb 2020 | Aug 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM20BVCC | BROWNSVILLE COMMUNITY CENTER | 3 | CONSTRUCTION | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM20BVCC | BROWNSVILLE COMMUNITY CENTER | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2020 | Aug 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM20BVCC | BROWNSVILLE COMMUNITY CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2021 | Feb 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM20BVCC | BROWNSVILLE COMMUNITY CENTER | 7 | PROJECT START | Aug 2021 | Feb 2022 | Feb 2025 | Feb 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM20BVCC | BROWNSVILLE COMMUNITY CENTER | 8 | DESIGN START | Aug 2021 | Feb 2022 | Feb 2025 | Feb 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM20BVCC | BROWNSVILLE COMMUNITY CENTER | 9 | DESIGN COMPLETION | Aug 2021 | Feb 2022 | Feb 2025 | Feb 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM20BVCC | BROWNSVILLE COMMUNITY CENTER | 10 | CONSTRUCTION START | Aug 2021 | Feb 2022 | Feb 2025 | Feb 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM20BVCC | BROWNSVILLE COMMUNITY CENTER | 11 | CONSTRUCTION COMPLETION | Aug 2021 | Feb 2022 | Feb 2025 | Jun 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161DPL | GATEWAY ESTATE - PHASE A/B/C/D PUNCH LIST | 1 | PROJECT START | Jul 2022 | Jun 2023 | Jul 2022 | Jun 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161DPL | GATEWAY ESTATE - PHASE A/B/C/D PUNCH LIST | 2 | DESIGN START | Jun 2023 | Jun 2023 | Jun 2023 | Aug 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161DPL | GATEWAY ESTATE - PHASE A/B/C/D PUNCH LIST | 3 | DESIGN COMPLETION | Jun 2023 | Jun 2023 | Aug 2023 | Nov 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161DPL | GATEWAY ESTATE - PHASE A/B/C/D PUNCH LIST | 4 | CONSTRUCTION START | Jun 2023 | Jun 2023 | Nov 2023 | Feb 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161DPL | GATEWAY ESTATE - PHASE A/B/C/D PUNCH LIST | 5 | CONSTRUCTION COMPLETION | Jun 2023 | Jun 2023 | Feb 2024 | Jun 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161E | GATEWAY ESTATE - PHASE E (BED-805) | 1 | DEVELOP SCOPE | Mar 2014 | May 2014 | Mar 2014 | May 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161E | GATEWAY ESTATE - PHASE E (BED-805) | 2 | PRELIMINARY DESIGN | May 2014 | Sep 2014 | May 2014 | Sep 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161E | GATEWAY ESTATE - PHASE E (BED-805) | 3 | FINAL DESIGN | Sep 2014 | Mar 2015 | Sep 2014 | Mar 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161E | GATEWAY ESTATE - PHASE E (BED-805) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2015 | Jun 2015 | Mar 2015 | Jun 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161E | GATEWAY ESTATE - PHASE E (BED-805) | 5 | CONSTRUCTION TO 25% | Jun 2015 | Oct 2015 | Jun 2015 | Oct 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161E | GATEWAY ESTATE - PHASE E (BED-805) | 6 | CONSTRUCTION TO 50% | Oct 2015 | Feb 2016 | Oct 2015 | Feb 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161E | GATEWAY ESTATE - PHASE E (BED-805) | 7 | CONSTRUCTION TO 75% | Feb 2016 | Jun 2016 | Feb 2016 | Jun 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161E | GATEWAY ESTATE - PHASE E (BED-805) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2016 | Sep 2016 | Jun 2016 | Sep 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161E | GATEWAY ESTATE - PHASE E (BED-805) | 9 | SUBSTANTIAL COMPLETION | Sep 2016 | Nov 2016 | Sep 2016 | Nov 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161E | GATEWAY ESTATE - PHASE E (BED-805) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2016 | Dec 2016 | Nov 2016 | Jul 2030
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BVFA | BROWNSVILLE WOMEN FIRE SAFETY | 1 | PROJECT START | Jul 2016 | Jul 2016 | Jul 2016 | Jul 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BVFA | BROWNSVILLE WOMEN FIRE SAFETY | 2 | DESIGN START | Jul 2016 | Nov 2017 | Jul 2016 | Nov 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BVFA | BROWNSVILLE WOMEN FIRE SAFETY | 3 | DESIGN COMPLETION | Nov 2017 | Aug 2018 | Nov 2017 | Aug 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BVFA | BROWNSVILLE WOMEN FIRE SAFETY | 4 | CONSTRUCTION START | Aug 2018 | Mar 2019 | Aug 2018 | Mar 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BVFA | BROWNSVILLE WOMEN FIRE SAFETY | 5 | CONSTRUCTION COMPLETION | Mar 2019 | Mar 2020 | Mar 2021 | Jun 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FBFS | FANNIE BARNES FIRE SAFETY | 1 | PROJECT START | Jul 2016 | Jul 2016 | Jul 2016 | Jul 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FBFS | FANNIE BARNES FIRE SAFETY | 2 | DESIGN START | Jul 2016 | Nov 2017 | Jul 2016 | Nov 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FBFS | FANNIE BARNES FIRE SAFETY | 3 | DESIGN COMPLETION | Nov 2017 | Aug 2018 | Nov 2017 | Aug 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FBFS | FANNIE BARNES FIRE SAFETY | 4 | CONSTRUCTION START | Aug 2018 | May 2019 | Aug 2019 | May 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FBFS | FANNIE BARNES FIRE SAFETY | 5 | CONSTRUCTION COMPLETION | May 2019 | May 2020 | May 2021 | May 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HWFS | HELP WOMEN'S CENTER FIRE SAFETY | 1 | PROJECT START | Jul 2016 | Jul 2016 | Jul 2016 | Jul 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HWFS | HELP WOMEN'S CENTER FIRE SAFETY | 2 | DESIGN START | Jul 2016 | Sep 2017 | Jul 2016 | Sep 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HWFS | HELP WOMEN'S CENTER FIRE SAFETY | 3 | DESIGN COMPLETION | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HWFS | HELP WOMEN'S CENTER FIRE SAFETY | 4 | CONSTRUCTION START | Mar 2018 | May 2019 | Mar 2018 | May 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HWFS | HELP WOMEN'S CENTER FIRE SAFETY | 5 | CONSTRUCTION COMPLETION | May 2019 | Apr 2020 | May 2019 | Jun 2031
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112LXFA | 85 LEXINGTON FIRE SAFETY SYSTEM | 2 | DESIGN START | Jul 2016 | Sep 2017 | Jul 2016 | Sep 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112LXFA | 85 LEXINGTON FIRE SAFETY SYSTEM | 3 | DESIGN COMPLETION | Sep 2017 | Aug 2018 | Sep 2017 | Aug 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112LXFA | 85 LEXINGTON FIRE SAFETY SYSTEM | 4 | CONSTRUCTION START | Aug 2018 | Feb 2019 | Aug 2018 | Feb 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112LXFA | 85 LEXINGTON FIRE SAFETY SYSTEM | 5 | CONSTRUCTION COMPLETION | Feb 2019 | Sep 2019 | Feb 2019 | Sep 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJFC | PAMOJA HOUSE - FACADE REHABILITATION/RESTORATION | 1 | PROJECT START | Jan 2018 | Jan 2018 | Jan 2018 | Jan 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJFC | PAMOJA HOUSE - FACADE REHABILITATION/RESTORATION | 2 | DESIGN START | Jan 2018 | Jul 2018 | Jan 2018 | Jul 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJFC | PAMOJA HOUSE - FACADE REHABILITATION/RESTORATION | 3 | DESIGN COMPLETION | Jul 2018 | Jan 2019 | Jul 2018 | Jun 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJFC | PAMOJA HOUSE - FACADE REHABILITATION/RESTORATION | 4 | CONSTRUCTION START | Jan 2019 | Jul 2019 | Jul 2020 | Dec 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJFC | PAMOJA HOUSE - FACADE REHABILITATION/RESTORATION | 5 | CONSTRUCTION COMPLETION | Jul 2019 | Dec 2020 | Dec 2020 | Jun 2032
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJPL | PAMOJA HOUSE - PLUMBING UPGRADE | 1 | PROJECT START | Jan 2018 | Jan 2018 | Jan 2018 | Jan 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJPL | PAMOJA HOUSE - PLUMBING UPGRADE | 2 | DESIGN START | Jan 2018 | Jul 2018 | Jan 2018 | Jun 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJPL | PAMOJA HOUSE - PLUMBING UPGRADE | 3 | DESIGN COMPLETION | Jul 2018 | Jan 2019 | Jun 2019 | Jun 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJPL | PAMOJA HOUSE - PLUMBING UPGRADE | 4 | CONSTRUCTION START | Jan 2019 | Jul 2019 | Jun 2021 | Oct 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJPL | PAMOJA HOUSE - PLUMBING UPGRADE | 5 | CONSTRUCTION COMPLETION | Jul 2019 | Dec 2020 | Oct 2021 | Jan 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115BMEP | BUSHWICK FAMILY BOILER RECONSTRUCTION | 1 | DESIGN | Jan 2020 | Sep 2020 | Jan 2020 | Sep 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115BMEP | BUSHWICK FAMILY BOILER RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2020 | Mar 2021 | Sep 2020 | Mar 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115BMEP | BUSHWICK FAMILY BOILER RECONSTRUCTION | 3 | CONSTRUCTION | Mar 2021 | Dec 2025 | Mar 2021 | Dec 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115DSFA | DEAN STREET FIRE SAFETY | 1 | PROJECT START | Jul 2016 | Jul 2016 | Jul 2016 | Jul 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115DSFA | DEAN STREET FIRE SAFETY | 2 | DESIGN START | Jul 2016 | Nov 2017 | Jul 2016 | Nov 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115DSFA | DEAN STREET FIRE SAFETY | 3 | DESIGN COMPLETION | Nov 2017 | Aug 2018 | Nov 2017 | Aug 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115DSFA | DEAN STREET FIRE SAFETY | 4 | CONSTRUCTION START | Aug 2018 | Apr 2019 | Aug 2018 | Apr 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115DSFA | DEAN STREET FIRE SAFETY | 5 | CONSTRUCTION COMPLETION | Apr 2019 | Apr 2020 | Apr 2020 | Apr 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115LFAU | LINDEN FIRE ALARM UPGRADE | 1 | PROJECT START | Jul 2016 | Jul 2016 | Jul 2016 | Jul 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115LFAU | LINDEN FIRE ALARM UPGRADE | 2 | DESIGN START | Jul 2016 | Sep 2017 | Jul 2016 | Sep 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115LFAU | LINDEN FIRE ALARM UPGRADE | 3 | DESIGN COMPLETION | Sep 2017 | Sep 2018 | Sep 2017 | Oct 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115LFAU | LINDEN FIRE ALARM UPGRADE | 4 | CONSTRUCTION START | Sep 2018 | May 2019 | Oct 2018 | May 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115LFAU | LINDEN FIRE ALARM UPGRADE | 5 | CONSTRUCTION COMPLETION | May 2018 | May 2020 | May 2018 | Jun 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SRFA | ROSE MCCARTHY - FIRE ALARM SYSTEM UPGRADE | 1 | PROJECT START | Mar 2016 | Mar 2016 | Mar 2016 | Mar 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SRFA | ROSE MCCARTHY - FIRE ALARM SYSTEM UPGRADE | 2 | DESIGN START | Apr 2016 | Jul 2016 | Apr 2016 | Jul 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SRFA | ROSE MCCARTHY - FIRE ALARM SYSTEM UPGRADE | 3 | DESIGN COMPLETION | Jul 2016 | Jun 2017 | Jul 2016 | Jun 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SRFA | ROSE MCCARTHY - FIRE ALARM SYSTEM UPGRADE | 4 | CONSTRUCTION START | Jul 2017 | Oct 2017 | Jul 2017 | Oct 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SRFA | ROSE MCCARTHY - FIRE ALARM SYSTEM UPGRADE | 5 | CONSTRUCTION COMPLETION | Nov 2017 | Jun 2023 | Nov 2017 | Jun 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BRKLN | Brooklyn Animal Care Center Upgrade | 1 | PROJECT START | Jan 2016 | Jan 2016 | Jan 2016 | Jan 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BRKLN | Brooklyn Animal Care Center Upgrade | 2 | DESIGN START | Jan 2016 | Jan 2016 | Jan 2016 | Jan 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BRKLN | Brooklyn Animal Care Center Upgrade | 3 | DESIGN COMPLETION | Jan 2016 | Jan 2016 | Jan 2016 | Jan 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BRKLN | Brooklyn Animal Care Center Upgrade | 4 | CONSTRUCTION START | Jan 2016 | Jan 2016 | Jan 2016 | Mar 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BRKLN | Brooklyn Animal Care Center Upgrade | 5 | CONSTRUCTION COMPLETION | Jan 2016 | Jun 2022 | Mar 2018 | Sep 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BUSHX | BUSHWICK HEALTH CENTER - EXTERIOR RENOVATION | 1 | PROJECT START | Aug 2004 | Aug 2004 | Aug 2008 | Aug 2008
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BUSHX | BUSHWICK HEALTH CENTER - EXTERIOR RENOVATION | 2 | DESIGN START | Aug 2004 | May 2009 | Aug 2008 | Jan 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BUSHX | BUSHWICK HEALTH CENTER - EXTERIOR RENOVATION | 3 | DESIGN COMPLETION | May 2009 | May 2009 | Jan 2016 | Nov 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BUSHX | BUSHWICK HEALTH CENTER - EXTERIOR RENOVATION | 4 | CONSTRUCTION START | May 2009 | May 2009 | Dec 2018 | Aug 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BUSHX | BUSHWICK HEALTH CENTER - EXTERIOR RENOVATION | 5 | CONSTRUCTION COMPLETION | May 2009 | Jun 2012 | Aug 2019 | Aug 2031
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25BRCS | Brownsville Community Center DESIGN BUILD | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25BRCS | Brownsville Community Center DESIGN BUILD | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25BRCS | Brownsville Community Center DESIGN BUILD | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25BRCS | Brownsville Community Center DESIGN BUILD | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25BRCS | Brownsville Community Center DESIGN BUILD | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25BRCS | Brownsville Community Center DESIGN BUILD | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25BRCS | Brownsville Community Center DESIGN BUILD | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25BRCS | Brownsville Community Center DESIGN BUILD | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25BRCS | Brownsville Community Center DESIGN BUILD | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2023 | Mar 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25BRCS | Brownsville Community Center DESIGN BUILD | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2023 | Apr 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25BRCS | Brownsville Community Center DESIGN BUILD | 11 | PROJECT START | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25BRCS | Brownsville Community Center DESIGN BUILD | 12 | DESIGN START | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25BRCS | Brownsville Community Center DESIGN BUILD | 13 | DESIGN COMPLETION | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25BRCS | Brownsville Community Center DESIGN BUILD | 14 | CONSTRUCTION START | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25BRCS | Brownsville Community Center DESIGN BUILD | 15 | CONSTRUCTION COMPLETION | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD005K01 | FULTON ST IMPROVEMENTS AT GREEN AV, HANSEN PL & GATES AV | 1 | DEVELOP SCOPE | Jun 2010 | Sep 2010 | Jun 2011 | Sep 2011
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD005K01 | FULTON ST IMPROVEMENTS AT GREEN AV, HANSEN PL & GATES AV | 2 | PRELIMINARY DESIGN | Sep 2010 | Jan 2011 | Sep 2011 | Jan 2012
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD005K01 | FULTON ST IMPROVEMENTS AT GREEN AV, HANSEN PL & GATES AV | 3 | FINAL DESIGN | Jan 2011 | Jul 2011 | Jan 2012 | May 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD005K01 | FULTON ST IMPROVEMENTS AT GREEN AV, HANSEN PL & GATES AV | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2011 | Oct 2011 | May 2015 | Aug 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD005K01 | FULTON ST IMPROVEMENTS AT GREEN AV, HANSEN PL & GATES AV | 5 | CONSTRUCTION TO 25% | Oct 2011 | Feb 2012 | Aug 2015 | Nov 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD005K01 | FULTON ST IMPROVEMENTS AT GREEN AV, HANSEN PL & GATES AV | 6 | CONSTRUCTION TO 50% | Feb 2012 | Jun 2012 | Nov 2015 | Jul 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD005K01 | FULTON ST IMPROVEMENTS AT GREEN AV, HANSEN PL & GATES AV | 7 | CONSTRUCTION TO 75% | Jun 2012 | Oct 2012 | Jul 2016 | Mar 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD005K01 | FULTON ST IMPROVEMENTS AT GREEN AV, HANSEN PL & GATES AV | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2012 | Jan 2013 | Mar 2017 | Jun 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD005K01 | FULTON ST IMPROVEMENTS AT GREEN AV, HANSEN PL & GATES AV | 9 | SUBSTANTIAL COMPLETION | Jan 2013 | Mar 2013 | Apr 2017 | Jun 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD005K01 | FULTON ST IMPROVEMENTS AT GREEN AV, HANSEN PL & GATES AV | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2013 | Apr 2013 | Jun 2017 | Jun 2032
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD007K03 | Park Avenue Ped Safety Improvement at the Crossover,BED-830 | 1 | DEVELOP SCOPE | Jun 2013 | Sep 2013 | Jun 2016 | Mar 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD007K03 | Park Avenue Ped Safety Improvement at the Crossover,BED-830 | 2 | PRELIMINARY DESIGN | Sep 2013 | Jan 2014 | Mar 2019 | Dec 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD007K03 | Park Avenue Ped Safety Improvement at the Crossover,BED-830 | 3 | FINAL DESIGN | Jan 2014 | Jul 2014 | Dec 2019 | Sep 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD007K03 | Park Avenue Ped Safety Improvement at the Crossover,BED-830 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2014 | Oct 2014 | Sep 2021 | Jul 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD007K03 | Park Avenue Ped Safety Improvement at the Crossover,BED-830 | 5 | CONSTRUCTION TO 25% | Oct 2014 | Feb 2015 | Jul 2022 | Dec 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD007K03 | Park Avenue Ped Safety Improvement at the Crossover,BED-830 | 6 | CONSTRUCTION TO 50% | Feb 2015 | Jun 2015 | Dec 2022 | Jun 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD007K03 | Park Avenue Ped Safety Improvement at the Crossover,BED-830 | 7 | CONSTRUCTION TO 75% | Jun 2015 | Oct 2015 | Jul 2023 | Jun 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD007K03 | Park Avenue Ped Safety Improvement at the Crossover,BED-830 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2015 | Jan 2016 | Jul 2024 | Oct 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD007K03 | Park Avenue Ped Safety Improvement at the Crossover,BED-830 | 9 | SUBSTANTIAL COMPLETION | Jan 2016 | Mar 2016 | Oct 2024 | Apr 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD007K03 | Park Avenue Ped Safety Improvement at the Crossover,BED-830 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Apr 2016 | Jan 2025 | Jan 2028
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105A | Ped Safety Upgrades on Atlantic Ave - Phase 2 (BED-785B) | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Mar 2017 | May 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105A | Ped Safety Upgrades on Atlantic Ave - Phase 2 (BED-785B) | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Jun 2017 | Nov 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105A | Ped Safety Upgrades on Atlantic Ave - Phase 2 (BED-785B) | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Nov 2017 | Jul 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105A | Ped Safety Upgrades on Atlantic Ave - Phase 2 (BED-785B) | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2018 | Oct 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105A | Ped Safety Upgrades on Atlantic Ave - Phase 2 (BED-785B) | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2018 | Feb 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105A | Ped Safety Upgrades on Atlantic Ave - Phase 2 (BED-785B) | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2019 | Jun 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105A | Ped Safety Upgrades on Atlantic Ave - Phase 2 (BED-785B) | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2019 | Oct 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105A | Ped Safety Upgrades on Atlantic Ave - Phase 2 (BED-785B) | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2019 | Jan 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105A | Ped Safety Upgrades on Atlantic Ave - Phase 2 (BED-785B) | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2020 | Mar 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105A | Ped Safety Upgrades on Atlantic Ave - Phase 2 (BED-785B) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2020 | Jun 2031
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK002377 | East 72nd Street Reconstruction Brooklyn, SEK002377 | 1 | DEVELOP SCOPE | Sep 2012 | Dec 2012 | Sep 2012 | Dec 2012
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK002377 | East 72nd Street Reconstruction Brooklyn, SEK002377 | 2 | PRELIMINARY DESIGN | Dec 2012 | Apr 2013 | Dec 2012 | Apr 2013
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK002377 | East 72nd Street Reconstruction Brooklyn, SEK002377 | 3 | FINAL DESIGN | Apr 2013 | Oct 2013 | Apr 2013 | Oct 2013
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK002377 | East 72nd Street Reconstruction Brooklyn, SEK002377 | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2013 | Jan 2014 | Oct 2013 | Jan 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK002377 | East 72nd Street Reconstruction Brooklyn, SEK002377 | 5 | CONSTRUCTION TO 25% | Jan 2014 | May 2014 | Jan 2014 | May 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK002377 | East 72nd Street Reconstruction Brooklyn, SEK002377 | 6 | CONSTRUCTION TO 50% | May 2014 | Sep 2014 | May 2014 | Sep 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK002377 | East 72nd Street Reconstruction Brooklyn, SEK002377 | 7 | CONSTRUCTION TO 75% | Sep 2014 | Jan 2015 | Sep 2014 | Jan 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK002377 | East 72nd Street Reconstruction Brooklyn, SEK002377 | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2015 | Apr 2015 | Jan 2015 | Apr 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK002377 | East 72nd Street Reconstruction Brooklyn, SEK002377 | 9 | SUBSTANTIAL COMPLETION | Apr 2015 | Jun 2015 | Apr 2015 | Jun 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK002377 | East 72nd Street Reconstruction Brooklyn, SEK002377 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2015 | Jul 2022 | Jun 2015 | Jun 2030
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100BUS | Utica Ave Bus Priority | 1 | DEVELOP SCOPE | Jun 2013 | Sep 2013 | Jun 2013 | Sep 2013
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100BUS | Utica Ave Bus Priority | 2 | PRELIMINARY DESIGN | Sep 2013 | Jan 2014 | Sep 2013 | Jan 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100BUS | Utica Ave Bus Priority | 3 | FINAL DESIGN | Jan 2014 | Jul 2014 | Jan 2014 | Jun 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100BUS | Utica Ave Bus Priority | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2014 | Oct 2014 | Jul 2016 | Sep 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100BUS | Utica Ave Bus Priority | 5 | CONSTRUCTION TO 25% | Oct 2014 | Feb 2015 | Sep 2016 | Jan 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100BUS | Utica Ave Bus Priority | 6 | CONSTRUCTION TO 50% | Feb 2015 | Jun 2015 | Jan 2017 | May 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100BUS | Utica Ave Bus Priority | 7 | CONSTRUCTION TO 75% | Jun 2015 | Oct 2015 | May 2017 | Sep 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100BUS | Utica Ave Bus Priority | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2015 | Jan 2016 | Sep 2017 | Sep 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100BUS | Utica Ave Bus Priority | 9 | SUBSTANTIAL COMPLETION | Jan 2016 | Mar 2016 | Sep 2017 | Jan 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100BUS | Utica Ave Bus Priority | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Apr 2016 | Jan 2018 | Jan 2032
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100SBC | South Brooklyn Crosstown SBS | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2017 | Sep 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100SBC | South Brooklyn Crosstown SBS | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2017 | Jan 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100SBC | South Brooklyn Crosstown SBS | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jan 2019 | Jan 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100SBC | South Brooklyn Crosstown SBS | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jan 2020 | Aug 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100SBC | South Brooklyn Crosstown SBS | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Aug 2021 | Nov 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100SBC | South Brooklyn Crosstown SBS | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Dec 2021 | Mar 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100SBC | South Brooklyn Crosstown SBS | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Mar 2022 | Jul 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100SBC | South Brooklyn Crosstown SBS | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Jul 2022 | Oct 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100SBC | South Brooklyn Crosstown SBS | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Oct 2022 | Dec 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100SBC | South Brooklyn Crosstown SBS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Dec 2022 | Jun 2028
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048B | FLUSHING AVE - BROOKLYN GREENWAY | 1 | DEVELOP SCOPE | Jun 2012 | Sep 2012 | Jun 2012 | Sep 2012
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048B | FLUSHING AVE - BROOKLYN GREENWAY | 2 | PRELIMINARY DESIGN | Sep 2012 | Jan 2013 | Sep 2012 | Jan 2013
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048B | FLUSHING AVE - BROOKLYN GREENWAY | 3 | FINAL DESIGN | Jan 2013 | Jul 2013 | Jan 2013 | Jul 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048B | FLUSHING AVE - BROOKLYN GREENWAY | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2013 | Oct 2013 | Jul 2014 | Oct 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048B | FLUSHING AVE - BROOKLYN GREENWAY | 5 | CONSTRUCTION TO 25% | Oct 2013 | Feb 2014 | Oct 2014 | Feb 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048B | FLUSHING AVE - BROOKLYN GREENWAY | 6 | CONSTRUCTION TO 50% | Feb 2014 | Jun 2014 | Feb 2015 | Jun 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048B | FLUSHING AVE - BROOKLYN GREENWAY | 7 | CONSTRUCTION TO 75% | Jun 2014 | Oct 2014 | Jun 2015 | Oct 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048B | FLUSHING AVE - BROOKLYN GREENWAY | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2014 | Jan 2015 | Oct 2015 | Oct 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048B | FLUSHING AVE - BROOKLYN GREENWAY | 9 | SUBSTANTIAL COMPLETION | Jan 2015 | Mar 2015 | Oct 2015 | Oct 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048B | FLUSHING AVE - BROOKLYN GREENWAY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Apr 2015 | Oct 2015 | Jun 2028
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048C | KENT AVE, BED-810 | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048C | KENT AVE, BED-810 | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048C | KENT AVE, BED-810 | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048C | KENT AVE, BED-810 | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048C | KENT AVE, BED-810 | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048C | KENT AVE, BED-810 | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048C | KENT AVE, BED-810 | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048C | KENT AVE, BED-810 | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048C | KENT AVE, BED-810 | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048C | KENT AVE, BED-810 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Jun 2032
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048D | BK Waterfront Greenway:Sunset Pk Gowanus Connect BED-802 | 1 | DEVELOP SCOPE | Feb 2015 | May 2015 | Feb 2015 | May 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048D | BK Waterfront Greenway:Sunset Pk Gowanus Connect BED-802 | 2 | PRELIMINARY DESIGN | May 2015 | Sep 2015 | May 2015 | Sep 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048D | BK Waterfront Greenway:Sunset Pk Gowanus Connect BED-802 | 3 | FINAL DESIGN | Sep 2015 | Mar 2016 | Sep 2015 | Mar 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048D | BK Waterfront Greenway:Sunset Pk Gowanus Connect BED-802 | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2016 | Jun 2016 | Mar 2016 | Jun 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048D | BK Waterfront Greenway:Sunset Pk Gowanus Connect BED-802 | 5 | CONSTRUCTION TO 25% | Jun 2016 | Oct 2016 | Jun 2016 | Oct 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048D | BK Waterfront Greenway:Sunset Pk Gowanus Connect BED-802 | 6 | CONSTRUCTION TO 50% | Oct 2016 | Feb 2017 | Oct 2016 | Feb 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048D | BK Waterfront Greenway:Sunset Pk Gowanus Connect BED-802 | 7 | CONSTRUCTION TO 75% | Feb 2017 | Jun 2017 | Feb 2017 | Jun 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048D | BK Waterfront Greenway:Sunset Pk Gowanus Connect BED-802 | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2017 | Sep 2017 | Jun 2017 | Sep 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048D | BK Waterfront Greenway:Sunset Pk Gowanus Connect BED-802 | 9 | SUBSTANTIAL COMPLETION | Sep 2017 | Nov 2017 | Sep 2017 | Nov 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048D | BK Waterfront Greenway:Sunset Pk Gowanus Connect BED-802 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | Dec 2017 | Nov 2017 | Aug 2032
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048E | Brooklyn Waterfront Greenway - Commercial St/Ash St, BED-806 | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048E | Brooklyn Waterfront Greenway - Commercial St/Ash St, BED-806 | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048E | Brooklyn Waterfront Greenway - Commercial St/Ash St, BED-806 | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048E | Brooklyn Waterfront Greenway - Commercial St/Ash St, BED-806 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048E | Brooklyn Waterfront Greenway - Commercial St/Ash St, BED-806 | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048E | Brooklyn Waterfront Greenway - Commercial St/Ash St, BED-806 | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048E | Brooklyn Waterfront Greenway - Commercial St/Ash St, BED-806 | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048E | Brooklyn Waterfront Greenway - Commercial St/Ash St, BED-806 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048E | Brooklyn Waterfront Greenway - Commercial St/Ash St, BED-806 | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048E | Brooklyn Waterfront Greenway - Commercial St/Ash St, BED-806 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2029
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1148 | JEWEL STREET AREA, SE-813 | 1 | DEVELOP SCOPE | May 2003 | Aug 2003 | May 2003 | Aug 2003
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1148 | JEWEL STREET AREA, SE-813 | 2 | PRELIMINARY DESIGN | Aug 2003 | Dec 2003 | Aug 2003 | Dec 2003
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1148 | JEWEL STREET AREA, SE-813 | 3 | FINAL DESIGN | Dec 2003 | Jun 2004 | Dec 2003 | Jun 2004
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1148 | JEWEL STREET AREA, SE-813 | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2004 | Sep 2004 | Jun 2004 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1148 | JEWEL STREET AREA, SE-813 | 5 | CONSTRUCTION TO 25% | Sep 2004 | Jan 2005 | Jun 2022 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1148 | JEWEL STREET AREA, SE-813 | 6 | CONSTRUCTION TO 50% | Jan 2005 | May 2005 | Jun 2022 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1148 | JEWEL STREET AREA, SE-813 | 7 | CONSTRUCTION TO 75% | May 2005 | Sep 2005 | Jun 2022 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1148 | JEWEL STREET AREA, SE-813 | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2005 | Dec 2005 | Jun 2022 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1148 | JEWEL STREET AREA, SE-813 | 9 | SUBSTANTIAL COMPLETION | Dec 2005 | Feb 2006 | Jun 2022 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1148 | JEWEL STREET AREA, SE-813 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2006 | Mar 2006 | Jun 2022 | Jun 2032
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1153A | DOWNTOWN BROOKLYN REHABILITATION - PHASE II | 1 | DEVELOP SCOPE | Feb 2008 | May 2008 | Jul 2009 | Sep 2009
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1153A | DOWNTOWN BROOKLYN REHABILITATION - PHASE II | 2 | PRELIMINARY DESIGN | May 2008 | Sep 2008 | Sep 2009 | Jan 2010
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1153A | DOWNTOWN BROOKLYN REHABILITATION - PHASE II | 3 | FINAL DESIGN | Sep 2008 | Mar 2009 | Jan 2010 | Jul 2010
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1153A | DOWNTOWN BROOKLYN REHABILITATION - PHASE II | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2009 | Jun 2009 | Jul 2010 | Oct 2010
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1153A | DOWNTOWN BROOKLYN REHABILITATION - PHASE II | 5 | CONSTRUCTION TO 25% | Jun 2009 | Oct 2009 | Oct 2010 | Jun 2011
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1153A | DOWNTOWN BROOKLYN REHABILITATION - PHASE II | 6 | CONSTRUCTION TO 50% | Oct 2009 | Feb 2010 | Jul 2011 | Mar 2012
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1153A | DOWNTOWN BROOKLYN REHABILITATION - PHASE II | 7 | CONSTRUCTION TO 75% | Feb 2010 | Jun 2010 | Mar 2012 | Dec 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1153A | DOWNTOWN BROOKLYN REHABILITATION - PHASE II | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2010 | Sep 2010 | Oct 2015 | May 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1153A | DOWNTOWN BROOKLYN REHABILITATION - PHASE II | 9 | SUBSTANTIAL COMPLETION | Sep 2010 | Nov 2010 | May 2016 | Aug 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1153A | DOWNTOWN BROOKLYN REHABILITATION - PHASE II | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2010 | Dec 2010 | Aug 2016 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1153A | DOWNTOWN BROOKLYN REHABILITATION - PHASE II | 11 | PROJECT START | Nov 2010 | Dec 2010 | Jun 2018 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1153A | DOWNTOWN BROOKLYN REHABILITATION - PHASE II | 12 | DESIGN START | Nov 2010 | Dec 2010 | Jun 2018 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1153A | DOWNTOWN BROOKLYN REHABILITATION - PHASE II | 13 | DESIGN COMPLETION | Nov 2010 | Dec 2010 | Jun 2018 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1153A | DOWNTOWN BROOKLYN REHABILITATION - PHASE II | 14 | CONSTRUCTION START | Nov 2010 | Dec 2010 | Jun 2018 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1153A | DOWNTOWN BROOKLYN REHABILITATION - PHASE II | 15 | CONSTRUCTION COMPLETION | Nov 2010 | Dec 2010 | Jun 2018 | Jun 2033
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669A | 4th Ave Safety Improvements - Phase A | 1 | DEVELOP SCOPE | Mar 2019 | May 2019 | Mar 2019 | May 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669A | 4th Ave Safety Improvements - Phase A | 2 | PRELIMINARY DESIGN | May 2019 | Sep 2019 | May 2019 | Sep 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669A | 4th Ave Safety Improvements - Phase A | 3 | FINAL DESIGN | Sep 2019 | Mar 2020 | Sep 2019 | Mar 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669A | 4th Ave Safety Improvements - Phase A | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Jun 2020 | Mar 2020 | Jun 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669A | 4th Ave Safety Improvements - Phase A | 5 | CONSTRUCTION TO 25% | Jun 2020 | Oct 2020 | Jun 2020 | Oct 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669A | 4th Ave Safety Improvements - Phase A | 6 | CONSTRUCTION TO 50% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669A | 4th Ave Safety Improvements - Phase A | 7 | CONSTRUCTION TO 75% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669A | 4th Ave Safety Improvements - Phase A | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669A | 4th Ave Safety Improvements - Phase A | 9 | SUBSTANTIAL COMPLETION | Sep 2021 | Nov 2021 | Sep 2021 | Nov 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669A | 4th Ave Safety Improvements - Phase A | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2021 | Dec 2021 | Nov 2021 | Dec 2029
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669B | 4th Ave Safety Improvements - Phase B, BED829 | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669B | 4th Ave Safety Improvements - Phase B, BED829 | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669B | 4th Ave Safety Improvements - Phase B, BED829 | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669B | 4th Ave Safety Improvements - Phase B, BED829 | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669B | 4th Ave Safety Improvements - Phase B, BED829 | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669B | 4th Ave Safety Improvements - Phase B, BED829 | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669B | 4th Ave Safety Improvements - Phase B, BED829 | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669B | 4th Ave Safety Improvements - Phase B, BED829 | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669B | 4th Ave Safety Improvements - Phase B, BED829 | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669B | 4th Ave Safety Improvements - Phase B, BED829 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2026 | Nov 2019 | Dec 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1672 | WASHINGTON AVENUE SAFETY IMPROVEMENTS | 1 | DEVELOP SCOPE | Mar 2020 | May 2020 | Mar 2020 | May 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1672 | WASHINGTON AVENUE SAFETY IMPROVEMENTS | 2 | PRELIMINARY DESIGN | May 2020 | Sep 2020 | May 2020 | Sep 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1672 | WASHINGTON AVENUE SAFETY IMPROVEMENTS | 3 | FINAL DESIGN | Sep 2020 | Mar 2021 | Sep 2020 | Mar 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1672 | WASHINGTON AVENUE SAFETY IMPROVEMENTS | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2021 | Jun 2021 | Mar 2021 | Jun 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1672 | WASHINGTON AVENUE SAFETY IMPROVEMENTS | 5 | CONSTRUCTION TO 25% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1672 | WASHINGTON AVENUE SAFETY IMPROVEMENTS | 6 | CONSTRUCTION TO 50% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1672 | WASHINGTON AVENUE SAFETY IMPROVEMENTS | 7 | CONSTRUCTION TO 75% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1672 | WASHINGTON AVENUE SAFETY IMPROVEMENTS | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1672 | WASHINGTON AVENUE SAFETY IMPROVEMENTS | 9 | SUBSTANTIAL COMPLETION | Sep 2022 | Nov 2022 | Sep 2022 | Nov 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1672 | WASHINGTON AVENUE SAFETY IMPROVEMENTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2022 | Dec 2022 | Nov 2022 | Dec 2032
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1673 | South Brooklyn Pedestrian Safety Improvements | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2024 | Sep 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1673 | South Brooklyn Pedestrian Safety Improvements | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2027 | Jan 2028
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1673 | South Brooklyn Pedestrian Safety Improvements | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2028 | Jul 2028
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1673 | South Brooklyn Pedestrian Safety Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2028 | Oct 2028
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1673 | South Brooklyn Pedestrian Safety Improvements | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2028 | Feb 2029
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1673 | South Brooklyn Pedestrian Safety Improvements | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2029 | Jun 2029
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1673 | South Brooklyn Pedestrian Safety Improvements | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2029 | Oct 2029
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1673 | South Brooklyn Pedestrian Safety Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2024 | Jan 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1673 | South Brooklyn Pedestrian Safety Improvements | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2025 | Mar 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1673 | South Brooklyn Pedestrian Safety Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2025 | Feb 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1674 | Flatbush Avenue Downtown Brooklyn Safety Improvements | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1674 | Flatbush Avenue Downtown Brooklyn Safety Improvements | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1674 | Flatbush Avenue Downtown Brooklyn Safety Improvements | 3 | FINAL DESIGN | Jan 2021 | Jul 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1674 | Flatbush Avenue Downtown Brooklyn Safety Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1674 | Flatbush Avenue Downtown Brooklyn Safety Improvements | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1674 | Flatbush Avenue Downtown Brooklyn Safety Improvements | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Mar 2022 | Jul 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1674 | Flatbush Avenue Downtown Brooklyn Safety Improvements | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jul 2022 | Nov 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1674 | Flatbush Avenue Downtown Brooklyn Safety Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1674 | Flatbush Avenue Downtown Brooklyn Safety Improvements | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Feb 2022 | Apr 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1674 | Flatbush Avenue Downtown Brooklyn Safety Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Apr 2022 | May 2029
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2013GB | Gerritsen Beach - Street Reconstruction | 1 | DEVELOP SCOPE | Jun 2013 | Sep 2013 | Jun 2013 | Sep 2013
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2013GB | Gerritsen Beach - Street Reconstruction | 2 | PRELIMINARY DESIGN | Sep 2013 | Jan 2014 | Sep 2013 | Jan 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2013GB | Gerritsen Beach - Street Reconstruction | 3 | FINAL DESIGN | Jan 2014 | Jul 2014 | Jan 2014 | Jul 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2013GB | Gerritsen Beach - Street Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2014 | Oct 2014 | Jul 2016 | Oct 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2013GB | Gerritsen Beach - Street Reconstruction | 5 | CONSTRUCTION TO 25% | Oct 2014 | Feb 2015 | Oct 2016 | Feb 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2013GB | Gerritsen Beach - Street Reconstruction | 6 | CONSTRUCTION TO 50% | Feb 2015 | Jun 2015 | Feb 2017 | Jun 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2013GB | Gerritsen Beach - Street Reconstruction | 7 | CONSTRUCTION TO 75% | Jun 2015 | Oct 2015 | Jun 2017 | Oct 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2013GB | Gerritsen Beach - Street Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2015 | Jan 2016 | Oct 2017 | Oct 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2013GB | Gerritsen Beach - Street Reconstruction | 9 | SUBSTANTIAL COMPLETION | Jan 2016 | Mar 2016 | Oct 2017 | Oct 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2013GB | Gerritsen Beach - Street Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Apr 2016 | Oct 2017 | Jun 2033
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2048 | Jamaica Bay Greenway - Paerdegat Ave.N Connector BED833 | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Jun 2016 | Sep 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2048 | Jamaica Bay Greenway - Paerdegat Ave.N Connector BED833 | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Sep 2016 | Jan 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2048 | Jamaica Bay Greenway - Paerdegat Ave.N Connector BED833 | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Jan 2017 | Jul 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2048 | Jamaica Bay Greenway - Paerdegat Ave.N Connector BED833 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Jul 2017 | Oct 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2048 | Jamaica Bay Greenway - Paerdegat Ave.N Connector BED833 | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Oct 2017 | Feb 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2048 | Jamaica Bay Greenway - Paerdegat Ave.N Connector BED833 | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Feb 2018 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2048 | Jamaica Bay Greenway - Paerdegat Ave.N Connector BED833 | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2048 | Jamaica Bay Greenway - Paerdegat Ave.N Connector BED833 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | Oct 2018 | Jan 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2048 | Jamaica Bay Greenway - Paerdegat Ave.N Connector BED833 | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Jan 2019 | Mar 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2048 | Jamaica Bay Greenway - Paerdegat Ave.N Connector BED833 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Mar 2019 | Oct 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK614D | RECONSTRUCTION OF BERGEN AVENUE AREA, BKLYN /BED-784 | 1 | DEVELOP SCOPE | May 2005 | Aug 2005 | May 2005 | Aug 2005
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK614D | RECONSTRUCTION OF BERGEN AVENUE AREA, BKLYN /BED-784 | 2 | PRELIMINARY DESIGN | Aug 2005 | Dec 2005 | Aug 2005 | Dec 2005
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK614D | RECONSTRUCTION OF BERGEN AVENUE AREA, BKLYN /BED-784 | 3 | FINAL DESIGN | Dec 2005 | Jun 2006 | Dec 2005 | Jun 2006
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK614D | RECONSTRUCTION OF BERGEN AVENUE AREA, BKLYN /BED-784 | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2006 | Sep 2006 | Jun 2006 | Sep 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK614D | RECONSTRUCTION OF BERGEN AVENUE AREA, BKLYN /BED-784 | 5 | CONSTRUCTION TO 25% | Sep 2006 | Jan 2007 | Sep 2022 | Sep 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK614D | RECONSTRUCTION OF BERGEN AVENUE AREA, BKLYN /BED-784 | 6 | CONSTRUCTION TO 50% | Jan 2007 | May 2007 | Sep 2022 | Sep 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK614D | RECONSTRUCTION OF BERGEN AVENUE AREA, BKLYN /BED-784 | 7 | CONSTRUCTION TO 75% | May 2007 | Sep 2007 | Sep 2022 | Sep 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK614D | RECONSTRUCTION OF BERGEN AVENUE AREA, BKLYN /BED-784 | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2007 | Dec 2007 | Sep 2022 | Sep 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK614D | RECONSTRUCTION OF BERGEN AVENUE AREA, BKLYN /BED-784 | 9 | SUBSTANTIAL COMPLETION | Dec 2007 | Feb 2008 | Sep 2022 | Sep 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK614D | RECONSTRUCTION OF BERGEN AVENUE AREA, BKLYN /BED-784 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2008 | Mar 2008 | Sep 2022 | Oct 2032
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WA | RECON: TILLARY STREET PHASE 2, BED-782A | 1 | DEVELOP SCOPE | May 2017 | Aug 2017 | May 2017 | Aug 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WA | RECON: TILLARY STREET PHASE 2, BED-782A | 2 | PRELIMINARY DESIGN | Aug 2017 | Dec 2017 | Aug 2017 | Dec 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WA | RECON: TILLARY STREET PHASE 2, BED-782A | 3 | FINAL DESIGN | Dec 2017 | Jun 2018 | Dec 2017 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WA | RECON: TILLARY STREET PHASE 2, BED-782A | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WA | RECON: TILLARY STREET PHASE 2, BED-782A | 5 | CONSTRUCTION TO 25% | Sep 2018 | Jan 2019 | Sep 2018 | Jan 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WA | RECON: TILLARY STREET PHASE 2, BED-782A | 6 | CONSTRUCTION TO 50% | Jan 2019 | May 2019 | Jan 2019 | May 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WA | RECON: TILLARY STREET PHASE 2, BED-782A | 7 | CONSTRUCTION TO 75% | May 2019 | Sep 2019 | May 2019 | Sep 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WA | RECON: TILLARY STREET PHASE 2, BED-782A | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Dec 2019 | Sep 2019 | Dec 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WA | RECON: TILLARY STREET PHASE 2, BED-782A | 9 | SUBSTANTIAL COMPLETION | Dec 2019 | Feb 2020 | Dec 2019 | Feb 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WA | RECON: TILLARY STREET PHASE 2, BED-782A | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2020 | Mar 2020 | Feb 2020 | Jun 2033
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WB | Adams Street Pedestrian Safety and Security | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WB | Adams Street Pedestrian Safety and Security | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WB | Adams Street Pedestrian Safety and Security | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WB | Adams Street Pedestrian Safety and Security | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WB | Adams Street Pedestrian Safety and Security | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | May 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WB | Adams Street Pedestrian Safety and Security | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | May 2023 | Nov 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WB | Adams Street Pedestrian Safety and Security | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Nov 2023 | Jun 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WB | Adams Street Pedestrian Safety and Security | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Jun 2024 | Sep 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WB | Adams Street Pedestrian Safety and Security | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Sep 2024 | Dec 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WB | Adams Street Pedestrian Safety and Security | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Feb 2025 | Jun 2033
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK700B | Reconstruction of Columbia Street Area Phase II (BED-768B) | 1 | DEVELOP SCOPE | May 2003 | Aug 2003 | May 2003 | Aug 2003
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK700B | Reconstruction of Columbia Street Area Phase II (BED-768B) | 2 | PRELIMINARY DESIGN | Aug 2003 | Dec 2003 | Aug 2003 | Dec 2003
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK700B | Reconstruction of Columbia Street Area Phase II (BED-768B) | 3 | FINAL DESIGN | Dec 2003 | Jun 2004 | Dec 2003 | Jun 2004
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK700B | Reconstruction of Columbia Street Area Phase II (BED-768B) | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2004 | Sep 2004 | Jun 2004 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK700B | Reconstruction of Columbia Street Area Phase II (BED-768B) | 5 | CONSTRUCTION TO 25% | Sep 2004 | Jan 2005 | Jun 2022 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK700B | Reconstruction of Columbia Street Area Phase II (BED-768B) | 6 | CONSTRUCTION TO 50% | Jan 2005 | May 2005 | Jun 2022 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK700B | Reconstruction of Columbia Street Area Phase II (BED-768B) | 7 | CONSTRUCTION TO 75% | May 2005 | Sep 2005 | Jun 2022 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK700B | Reconstruction of Columbia Street Area Phase II (BED-768B) | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2005 | Dec 2005 | Jun 2022 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK700B | Reconstruction of Columbia Street Area Phase II (BED-768B) | 9 | SUBSTANTIAL COMPLETION | Dec 2005 | Feb 2006 | Jun 2022 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK700B | Reconstruction of Columbia Street Area Phase II (BED-768B) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2006 | Mar 2006 | Jun 2022 | Feb 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK779W | EMPIRE BOULEVARD, BED-796 | 1 | DEVELOP SCOPE | May 2005 | Aug 2005 | May 2011 | Aug 2011
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK779W | EMPIRE BOULEVARD, BED-796 | 2 | PRELIMINARY DESIGN | Aug 2005 | Dec 2005 | Aug 2011 | Dec 2011
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK779W | EMPIRE BOULEVARD, BED-796 | 3 | FINAL DESIGN | Dec 2005 | Jun 2006 | Dec 2011 | Mar 2013
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK779W | EMPIRE BOULEVARD, BED-796 | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2006 | Sep 2006 | Mar 2016 | Jun 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK779W | EMPIRE BOULEVARD, BED-796 | 5 | CONSTRUCTION TO 25% | Sep 2006 | Jan 2007 | Apr 2016 | Dec 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK779W | EMPIRE BOULEVARD, BED-796 | 6 | CONSTRUCTION TO 50% | Jan 2007 | May 2007 | Dec 2016 | Aug 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK779W | EMPIRE BOULEVARD, BED-796 | 7 | CONSTRUCTION TO 75% | May 2007 | Sep 2007 | Aug 2017 | Apr 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK779W | EMPIRE BOULEVARD, BED-796 | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2007 | Dec 2007 | Apr 2018 | Jul 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK779W | EMPIRE BOULEVARD, BED-796 | 9 | SUBSTANTIAL COMPLETION | Dec 2007 | Feb 2008 | Jul 2018 | Aug 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK779W | EMPIRE BOULEVARD, BED-796 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2008 | Mar 2008 | Sep 2018 | Jun 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK779W | EMPIRE BOULEVARD, BED-796 | 11 | PROJECT START | Feb 2008 | Mar 2008 | Jul 2024 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK779W | EMPIRE BOULEVARD, BED-796 | 12 | DESIGN START | Feb 2008 | Mar 2008 | Jul 2024 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK779W | EMPIRE BOULEVARD, BED-796 | 13 | DESIGN COMPLETION | Feb 2008 | Mar 2008 | Jul 2024 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK779W | EMPIRE BOULEVARD, BED-796 | 14 | CONSTRUCTION START | Feb 2008 | Mar 2008 | Jul 2024 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK779W | EMPIRE BOULEVARD, BED-796 | 15 | CONSTRUCTION COMPLETION | Feb 2008 | Mar 2008 | Jul 2024 | Jul 2033
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK797W | Schenck Avenue, BED-803 | 1 | DEVELOP SCOPE | Feb 2015 | May 2015 | Feb 2015 | Aug 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK797W | Schenck Avenue, BED-803 | 2 | PRELIMINARY DESIGN | May 2015 | Sep 2015 | Aug 2016 | Dec 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK797W | Schenck Avenue, BED-803 | 3 | FINAL DESIGN | Sep 2015 | Mar 2016 | Dec 2016 | Apr 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK797W | Schenck Avenue, BED-803 | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2016 | Jun 2016 | Apr 2019 | Jul 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK797W | Schenck Avenue, BED-803 | 5 | CONSTRUCTION TO 25% | Jun 2016 | Oct 2016 | Jul 2019 | Nov 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK797W | Schenck Avenue, BED-803 | 6 | CONSTRUCTION TO 50% | Oct 2016 | Feb 2017 | Nov 2019 | Mar 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK797W | Schenck Avenue, BED-803 | 7 | CONSTRUCTION TO 75% | Feb 2017 | Jun 2017 | Mar 2020 | Jul 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK797W | Schenck Avenue, BED-803 | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2017 | Sep 2017 | Jul 2020 | Oct 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK797W | Schenck Avenue, BED-803 | 9 | SUBSTANTIAL COMPLETION | Sep 2017 | Nov 2017 | Oct 2020 | Dec 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK797W | Schenck Avenue, BED-803 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | Dec 2017 | Dec 2020 | Jun 2032
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK876 | RECONSTRUCTION OF WYCKOFF AVENUE, BROOKLYN, SEK002351 | 1 | DEVELOP SCOPE | May 2004 | Aug 2004 | May 2004 | Aug 2004
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK876 | RECONSTRUCTION OF WYCKOFF AVENUE, BROOKLYN, SEK002351 | 2 | PRELIMINARY DESIGN | Aug 2004 | Dec 2004 | Aug 2004 | Dec 2004
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK876 | RECONSTRUCTION OF WYCKOFF AVENUE, BROOKLYN, SEK002351 | 3 | FINAL DESIGN | Dec 2004 | Jun 2005 | Dec 2004 | Jun 2005
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK876 | RECONSTRUCTION OF WYCKOFF AVENUE, BROOKLYN, SEK002351 | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2005 | Sep 2005 | Jun 2005 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK876 | RECONSTRUCTION OF WYCKOFF AVENUE, BROOKLYN, SEK002351 | 5 | CONSTRUCTION TO 25% | Sep 2005 | Jan 2006 | Jun 2022 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK876 | RECONSTRUCTION OF WYCKOFF AVENUE, BROOKLYN, SEK002351 | 6 | CONSTRUCTION TO 50% | Jan 2006 | May 2006 | Jun 2022 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK876 | RECONSTRUCTION OF WYCKOFF AVENUE, BROOKLYN, SEK002351 | 7 | CONSTRUCTION TO 75% | May 2006 | Sep 2006 | Jun 2022 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK876 | RECONSTRUCTION OF WYCKOFF AVENUE, BROOKLYN, SEK002351 | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2006 | Dec 2006 | Jun 2022 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK876 | RECONSTRUCTION OF WYCKOFF AVENUE, BROOKLYN, SEK002351 | 9 | SUBSTANTIAL COMPLETION | Dec 2006 | Feb 2007 | Jun 2022 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK876 | RECONSTRUCTION OF WYCKOFF AVENUE, BROOKLYN, SEK002351 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2007 | Mar 2007 | Jun 2022 | Jul 2033
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK900 | Brownsville Pedestrian Safety Improvements | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2017 | Jul 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK900 | Brownsville Pedestrian Safety Improvements | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Nov 2019 | Apr 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK900 | Brownsville Pedestrian Safety Improvements | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Apr 2021 | Oct 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK900 | Brownsville Pedestrian Safety Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Oct 2021 | Dec 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK900 | Brownsville Pedestrian Safety Improvements | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Dec 2021 | Apr 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK900 | Brownsville Pedestrian Safety Improvements | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Apr 2022 | Aug 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK900 | Brownsville Pedestrian Safety Improvements | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Aug 2022 | Dec 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK900 | Brownsville Pedestrian Safety Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Mar 2023 | Mar 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK900 | Brownsville Pedestrian Safety Improvements | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Mar 2025 | May 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK900 | Brownsville Pedestrian Safety Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | May 2025 | Jun 2028
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKDTBK | Park Avenue - Ingersoll Safety Improvements | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Aug 2019 | Jan 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKDTBK | Park Avenue - Ingersoll Safety Improvements | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Jan 2020 | May 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKDTBK | Park Avenue - Ingersoll Safety Improvements | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | May 2020 | Nov 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKDTBK | Park Avenue - Ingersoll Safety Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Nov 2020 | Feb 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKDTBK | Park Avenue - Ingersoll Safety Improvements | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Feb 2021 | Jun 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKDTBK | Park Avenue - Ingersoll Safety Improvements | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Jun 2021 | Oct 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKDTBK | Park Avenue - Ingersoll Safety Improvements | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Oct 2021 | Feb 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKDTBK | Park Avenue - Ingersoll Safety Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Feb 2022 | May 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKDTBK | Park Avenue - Ingersoll Safety Improvements | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | May 2022 | Jul 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKDTBK | Park Avenue - Ingersoll Safety Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Jul 2022 | Jun 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKF488R | Hamilton Asphalt Plant Roof Replacement | 1 | DEVELOP SCOPE | Jun 2016 | Oct 2016 | Jun 2015 | Jul 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKF488R | Hamilton Asphalt Plant Roof Replacement | 2 | DESIGN START | Oct 2016 | Apr 2018 | Jul 2017 | Dec 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKF488R | Hamilton Asphalt Plant Roof Replacement | 3 | CONSTRUCTION START | Apr 2018 | Apr 2020 | Dec 2017 | May 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKF488R | Hamilton Asphalt Plant Roof Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2018 | Apr 2020 | May 2020 | Dec 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKF488R | Hamilton Asphalt Plant Roof Replacement | 5 | CONSTRUCTION TO 25% | Apr 2018 | Apr 2020 | Dec 2020 | Apr 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKF488R | Hamilton Asphalt Plant Roof Replacement | 6 | CONSTRUCTION TO 50% | Apr 2018 | Apr 2020 | Apr 2021 | Jul 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKF488R | Hamilton Asphalt Plant Roof Replacement | 7 | CONSTRUCTION TO 75% | Apr 2018 | Apr 2020 | Jul 2021 | Oct 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKF488R | Hamilton Asphalt Plant Roof Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2018 | Apr 2020 | Oct 2021 | Nov 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKF488R | Hamilton Asphalt Plant Roof Replacement | 9 | SUBSTANTIAL COMPLETION | Apr 2018 | Apr 2020 | Nov 2021 | Dec 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKF488R | Hamilton Asphalt Plant Roof Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2018 | Apr 2020 | Dec 2021 | Jul 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKF488R | Hamilton Asphalt Plant Roof Replacement | 11 | PROJECT START | Apr 2018 | Apr 2020 | Jul 2022 | Jul 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKF488R | Hamilton Asphalt Plant Roof Replacement | 12 | DESIGN START | Apr 2018 | Apr 2020 | Jul 2022 | Jul 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKF488R | Hamilton Asphalt Plant Roof Replacement | 13 | DESIGN COMPLETION | Apr 2018 | Apr 2020 | Jul 2022 | Jul 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKF488R | Hamilton Asphalt Plant Roof Replacement | 14 | CONSTRUCTION START | Apr 2018 | Apr 2020 | Jul 2022 | Jul 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKF488R | Hamilton Asphalt Plant Roof Replacement | 15 | CONSTRUCTION COMPLETION | Apr 2018 | Apr 2020 | Jul 2022 | Jul 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKKP005 | DUMBO D.M.A. - VINEGAR HILL AREA, BED-794,SANDHWK05 | 1 | DEVELOP SCOPE | Jun 2012 | Sep 2012 | Sep 2011 | Jun 2012
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKKP005 | DUMBO D.M.A. - VINEGAR HILL AREA, BED-794,SANDHWK05 | 2 | PRELIMINARY DESIGN | Sep 2012 | Jan 2013 | Jun 2012 | Jun 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKKP005 | DUMBO D.M.A. - VINEGAR HILL AREA, BED-794,SANDHWK05 | 3 | FINAL DESIGN | Jan 2013 | Jul 2013 | Jun 2015 | Dec 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKKP005 | DUMBO D.M.A. - VINEGAR HILL AREA, BED-794,SANDHWK05 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2013 | Oct 2013 | Dec 2015 | Feb 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKKP005 | DUMBO D.M.A. - VINEGAR HILL AREA, BED-794,SANDHWK05 | 5 | CONSTRUCTION TO 25% | Oct 2013 | Feb 2014 | Mar 2016 | Jun 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKKP005 | DUMBO D.M.A. - VINEGAR HILL AREA, BED-794,SANDHWK05 | 6 | CONSTRUCTION TO 50% | Feb 2014 | Jun 2014 | Jun 2016 | Oct 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKKP005 | DUMBO D.M.A. - VINEGAR HILL AREA, BED-794,SANDHWK05 | 7 | CONSTRUCTION TO 75% | Jun 2014 | Oct 2014 | Oct 2016 | Feb 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKKP005 | DUMBO D.M.A. - VINEGAR HILL AREA, BED-794,SANDHWK05 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2014 | Jan 2015 | Feb 2017 | May 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKKP005 | DUMBO D.M.A. - VINEGAR HILL AREA, BED-794,SANDHWK05 | 9 | SUBSTANTIAL COMPLETION | Jan 2015 | Mar 2015 | May 2017 | Jul 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKKP005 | DUMBO D.M.A. - VINEGAR HILL AREA, BED-794,SANDHWK05 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Apr 2015 | Jul 2017 | Jun 2032
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC1 | Citywide Complex Pedestrian Ramps - Brooklyn | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2017 | Sep 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC1 | Citywide Complex Pedestrian Ramps - Brooklyn | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2017 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC1 | Citywide Complex Pedestrian Ramps - Brooklyn | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jul 2018 | Jun 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC1 | Citywide Complex Pedestrian Ramps - Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2019 | Dec 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC1 | Citywide Complex Pedestrian Ramps - Brooklyn | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Jan 2020 | Apr 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC1 | Citywide Complex Pedestrian Ramps - Brooklyn | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Apr 2020 | Aug 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC1 | Citywide Complex Pedestrian Ramps - Brooklyn | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Aug 2020 | Dec 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC1 | Citywide Complex Pedestrian Ramps - Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Dec 2020 | Mar 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC1 | Citywide Complex Pedestrian Ramps - Brooklyn | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Mar 2021 | May 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC1 | Citywide Complex Pedestrian Ramps - Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | May 2021 | Jun 2032
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC2 | Citywide Complex Pedestrian Ramps - Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2019 | Dec 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC2 | Citywide Complex Pedestrian Ramps - Brooklyn | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Jan 2020 | Apr 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC2 | Citywide Complex Pedestrian Ramps - Brooklyn | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Apr 2020 | Aug 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC2 | Citywide Complex Pedestrian Ramps - Brooklyn | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Aug 2020 | Dec 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC2 | Citywide Complex Pedestrian Ramps - Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Dec 2020 | Mar 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC2 | Citywide Complex Pedestrian Ramps - Brooklyn | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Mar 2021 | May 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC2 | Citywide Complex Pedestrian Ramps - Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | May 2021 | May 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC3 | Citywide Complex Pedestrian Ramps - Brooklyn | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2017 | Sep 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC3 | Citywide Complex Pedestrian Ramps - Brooklyn | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2017 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC3 | Citywide Complex Pedestrian Ramps - Brooklyn | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jul 2018 | Jun 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC3 | Citywide Complex Pedestrian Ramps - Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2019 | Dec 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC3 | Citywide Complex Pedestrian Ramps - Brooklyn | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Jan 2020 | Apr 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC3 | Citywide Complex Pedestrian Ramps - Brooklyn | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Apr 2020 | Aug 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC3 | Citywide Complex Pedestrian Ramps - Brooklyn | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Aug 2020 | Dec 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC3 | Citywide Complex Pedestrian Ramps - Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Dec 2020 | Mar 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC3 | Citywide Complex Pedestrian Ramps - Brooklyn | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Mar 2021 | May 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC3 | Citywide Complex Pedestrian Ramps - Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | May 2021 | Jun 2033
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020KC | Non-Standard Ped Ramp Installs - Brooklyn | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020KC | Non-Standard Ped Ramp Installs - Brooklyn | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020KC | Non-Standard Ped Ramp Installs - Brooklyn | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020KC | Non-Standard Ped Ramp Installs - Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020KC | Non-Standard Ped Ramp Installs - Brooklyn | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020KC | Non-Standard Ped Ramp Installs - Brooklyn | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020KC | Non-Standard Ped Ramp Installs - Brooklyn | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020KC | Non-Standard Ped Ramp Installs - Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020KC | Non-Standard Ped Ramp Installs - Brooklyn | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020KC | Non-Standard Ped Ramp Installs - Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Jun 2029
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4 | Multi-Site Pedestrian Safety | 1 | DEVELOP SCOPE | Jul 2011 | Sep 2011 | Jul 2011 | Sep 2011
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4 | Multi-Site Pedestrian Safety | 2 | PRELIMINARY DESIGN | Sep 2011 | Jan 2012 | Sep 2011 | Jan 2012
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4 | Multi-Site Pedestrian Safety | 3 | FINAL DESIGN | Jan 2012 | Jul 2012 | Jan 2012 | Mar 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4 | Multi-Site Pedestrian Safety | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2012 | Oct 2012 | Mar 2017 | Jun 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4 | Multi-Site Pedestrian Safety | 5 | CONSTRUCTION TO 25% | Oct 2012 | Feb 2013 | Jun 2017 | Nov 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4 | Multi-Site Pedestrian Safety | 6 | CONSTRUCTION TO 50% | Feb 2013 | Jun 2013 | Nov 2017 | Apr 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4 | Multi-Site Pedestrian Safety | 7 | CONSTRUCTION TO 75% | Jun 2013 | Oct 2013 | Apr 2018 | Sep 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4 | Multi-Site Pedestrian Safety | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2013 | Jan 2014 | Jun 2018 | Sep 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4 | Multi-Site Pedestrian Safety | 9 | SUBSTANTIAL COMPLETION | Jan 2014 | Mar 2014 | Sep 2018 | Nov 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4 | Multi-Site Pedestrian Safety | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2014 | Apr 2014 | Nov 2018 | Jun 2032
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4A | Multi-Site Pedestrian Safety - Phase 4A | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2017 | Sep 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4A | Multi-Site Pedestrian Safety - Phase 4A | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2017 | Jan 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4A | Multi-Site Pedestrian Safety - Phase 4A | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jan 2018 | Jul 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4A | Multi-Site Pedestrian Safety - Phase 4A | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2018 | Oct 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4A | Multi-Site Pedestrian Safety - Phase 4A | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4A | Multi-Site Pedestrian Safety - Phase 4A | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4A | Multi-Site Pedestrian Safety - Phase 4A | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jun 2019 | Oct 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4A | Multi-Site Pedestrian Safety - Phase 4A | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Oct 2019 | Jan 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4A | Multi-Site Pedestrian Safety - Phase 4A | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jan 2020 | Mar 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4A | Multi-Site Pedestrian Safety - Phase 4A | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Mar 2020 | Jun 2032
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF5 | Multi-Site Pedestrian Safety Phase 5 | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Jun 2016 | Jul 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF5 | Multi-Site Pedestrian Safety Phase 5 | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Aug 2017 | Aug 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF5 | Multi-Site Pedestrian Safety Phase 5 | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Aug 2018 | Feb 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF5 | Multi-Site Pedestrian Safety Phase 5 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Feb 2019 | May 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF5 | Multi-Site Pedestrian Safety Phase 5 | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | May 2019 | Sep 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF5 | Multi-Site Pedestrian Safety Phase 5 | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Sep 2019 | Jan 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF5 | Multi-Site Pedestrian Safety Phase 5 | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Jan 2020 | May 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF5 | Multi-Site Pedestrian Safety Phase 5 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | May 2020 | Aug 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF5 | Multi-Site Pedestrian Safety Phase 5 | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Aug 2020 | Oct 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF5 | Multi-Site Pedestrian Safety Phase 5 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Oct 2020 | Jun 2032
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ010K | FOWLER SQUARE PLAZA | 1 | DEVELOP SCOPE | Jun 2012 | Sep 2012 | Jun 2012 | Sep 2012
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ010K | FOWLER SQUARE PLAZA | 2 | PRELIMINARY DESIGN | Sep 2012 | Jan 2013 | Sep 2012 | Jan 2013
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ010K | FOWLER SQUARE PLAZA | 3 | FINAL DESIGN | Jan 2013 | Jul 2013 | Jan 2013 | Mar 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ010K | FOWLER SQUARE PLAZA | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2013 | Oct 2013 | Mar 2016 | Jun 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ010K | FOWLER SQUARE PLAZA | 5 | CONSTRUCTION TO 25% | Oct 2013 | Feb 2014 | Jan 2016 | Jun 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ010K | FOWLER SQUARE PLAZA | 6 | CONSTRUCTION TO 50% | Feb 2014 | Jun 2014 | Jun 2016 | Jan 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ010K | FOWLER SQUARE PLAZA | 7 | CONSTRUCTION TO 75% | Jun 2014 | Oct 2014 | Jan 2017 | Jul 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ010K | FOWLER SQUARE PLAZA | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2014 | Jan 2015 | Jul 2017 | Oct 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ010K | FOWLER SQUARE PLAZA | 9 | SUBSTANTIAL COMPLETION | Jan 2015 | Mar 2015 | Oct 2017 | Dec 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ010K | FOWLER SQUARE PLAZA | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Apr 2015 | Dec 2017 | Jun 2029
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ017K | Osborn Street Plaza | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Jun 2016 | Sep 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ017K | Osborn Street Plaza | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Sep 2016 | Jan 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ017K | Osborn Street Plaza | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Jan 2017 | Jul 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ017K | Osborn Street Plaza | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Jul 2017 | Oct 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ017K | Osborn Street Plaza | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Oct 2017 | Feb 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ017K | Osborn Street Plaza | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Feb 2018 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ017K | Osborn Street Plaza | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ017K | Osborn Street Plaza | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | Oct 2018 | Jan 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ017K | Osborn Street Plaza | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Jan 2019 | Mar 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ017K | Osborn Street Plaza | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Mar 2019 | Jun 2032
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19KC | Complex Upgrades Ped Ramp - Brooklyn | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19KC | Complex Upgrades Ped Ramp - Brooklyn | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19KC | Complex Upgrades Ped Ramp - Brooklyn | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19KC | Complex Upgrades Ped Ramp - Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19KC | Complex Upgrades Ped Ramp - Brooklyn | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19KC | Complex Upgrades Ped Ramp - Brooklyn | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19KC | Complex Upgrades Ped Ramp - Brooklyn | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19KC | Complex Upgrades Ped Ramp - Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19KC | Complex Upgrades Ped Ramp - Brooklyn | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19KC | Complex Upgrades Ped Ramp - Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Apr 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K3 | Pedestrian Ramp Rehabilitation - Brooklyn | 1 | DEVELOP SCOPE | May 2019 | Aug 2019 | May 2019 | Aug 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K3 | Pedestrian Ramp Rehabilitation - Brooklyn | 2 | PRELIMINARY DESIGN | Aug 2019 | Dec 2019 | Aug 2019 | Dec 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K3 | Pedestrian Ramp Rehabilitation - Brooklyn | 3 | FINAL DESIGN | Dec 2019 | Jun 2020 | Dec 2019 | Jun 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K3 | Pedestrian Ramp Rehabilitation - Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K3 | Pedestrian Ramp Rehabilitation - Brooklyn | 5 | CONSTRUCTION TO 25% | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K3 | Pedestrian Ramp Rehabilitation - Brooklyn | 6 | CONSTRUCTION TO 50% | Jan 2021 | May 2021 | Jan 2021 | May 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K3 | Pedestrian Ramp Rehabilitation - Brooklyn | 7 | CONSTRUCTION TO 75% | May 2021 | Sep 2021 | May 2021 | Sep 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K3 | Pedestrian Ramp Rehabilitation - Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Dec 2021 | Sep 2021 | Dec 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K3 | Pedestrian Ramp Rehabilitation - Brooklyn | 9 | SUBSTANTIAL COMPLETION | Dec 2021 | Feb 2022 | Dec 2021 | Feb 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K3 | Pedestrian Ramp Rehabilitation - Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2022 | Jul 2024 | Feb 2022 | Jun 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KC | Non-Standard Upgrades Ped Ramp - Brooklyn | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KC | Non-Standard Upgrades Ped Ramp - Brooklyn | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KC | Non-Standard Upgrades Ped Ramp - Brooklyn | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KC | Non-Standard Upgrades Ped Ramp - Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KC | Non-Standard Upgrades Ped Ramp - Brooklyn | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KC | Non-Standard Upgrades Ped Ramp - Brooklyn | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KC | Non-Standard Upgrades Ped Ramp - Brooklyn | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KC | Non-Standard Upgrades Ped Ramp - Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KC | Non-Standard Upgrades Ped Ramp - Brooklyn | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KC | Non-Standard Upgrades Ped Ramp - Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Jun 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Jun 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2033
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23K1 | Standard Upgrades Ped Ramps - Brooklyn | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23K1 | Standard Upgrades Ped Ramps - Brooklyn | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23K1 | Standard Upgrades Ped Ramps - Brooklyn | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23K1 | Standard Upgrades Ped Ramps - Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23K1 | Standard Upgrades Ped Ramps - Brooklyn | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23K1 | Standard Upgrades Ped Ramps - Brooklyn | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23K1 | Standard Upgrades Ped Ramps - Brooklyn | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23K1 | Standard Upgrades Ped Ramps - Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23K1 | Standard Upgrades Ped Ramps - Brooklyn | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23K1 | Standard Upgrades Ped Ramps - Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2016K1 | Prior Notice Sidewalks - Brooklyn | 6 | CONSTRUCTION TO 50% | Jun 2016 | Sep 2016 | Jun 2016 | Sep 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2016K1 | Prior Notice Sidewalks - Brooklyn | 7 | CONSTRUCTION TO 75% | Sep 2016 | Jan 2017 | Sep 2016 | Jan 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2016K1 | Prior Notice Sidewalks - Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2017 | Apr 2017 | Jan 2017 | Apr 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2016K1 | Prior Notice Sidewalks - Brooklyn | 9 | SUBSTANTIAL COMPLETION | Apr 2017 | Jun 2017 | Apr 2017 | Jun 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2016K1 | Prior Notice Sidewalks - Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2017 | Jul 2017 | Jun 2017 | Jun 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K1 | Prior Notice Sidewalks- Brooklyn | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K1 | Prior Notice Sidewalks- Brooklyn | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K1 | Prior Notice Sidewalks- Brooklyn | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K1 | Prior Notice Sidewalks- Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K1 | Prior Notice Sidewalks- Brooklyn | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K1 | Prior Notice Sidewalks- Brooklyn | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K1 | Prior Notice Sidewalks- Brooklyn | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K1 | Prior Notice Sidewalks- Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K1 | Prior Notice Sidewalks- Brooklyn | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K1 | Prior Notice Sidewalks- Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Apr 2028
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K2 | Prior Notice Sidewalks- Brooklyn | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K2 | Prior Notice Sidewalks- Brooklyn | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K2 | Prior Notice Sidewalks- Brooklyn | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K2 | Prior Notice Sidewalks- Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K2 | Prior Notice Sidewalks- Brooklyn | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K2 | Prior Notice Sidewalks- Brooklyn | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K2 | Prior Notice Sidewalks- Brooklyn | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K2 | Prior Notice Sidewalks- Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K2 | Prior Notice Sidewalks- Brooklyn | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K2 | Prior Notice Sidewalks- Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Apr 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K2 | Prior Notice Sidewalks- Brooklyn | 11 | PROJECT START | Mar 2022 | Apr 2022 | Apr 2022 | Apr 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K2 | Prior Notice Sidewalks- Brooklyn | 12 | DESIGN START | Mar 2022 | Apr 2022 | Apr 2022 | Apr 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K2 | Prior Notice Sidewalks- Brooklyn | 13 | DESIGN COMPLETION | Mar 2022 | Apr 2022 | Apr 2022 | Apr 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K2 | Prior Notice Sidewalks- Brooklyn | 14 | CONSTRUCTION START | Mar 2022 | Apr 2022 | Apr 2022 | Apr 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K2 | Prior Notice Sidewalks- Brooklyn | 15 | CONSTRUCTION COMPLETION | Mar 2022 | Apr 2022 | Apr 2022 | Apr 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021K | PRIOR NOTICE SIDEWALK - BROOKLYN | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021K | PRIOR NOTICE SIDEWALK - BROOKLYN | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021K | PRIOR NOTICE SIDEWALK - BROOKLYN | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021K | PRIOR NOTICE SIDEWALK - BROOKLYN | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021K | PRIOR NOTICE SIDEWALK - BROOKLYN | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021K | PRIOR NOTICE SIDEWALK - BROOKLYN | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021K | PRIOR NOTICE SIDEWALK - BROOKLYN | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021K | PRIOR NOTICE SIDEWALK - BROOKLYN | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021K | PRIOR NOTICE SIDEWALK - BROOKLYN | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021K | PRIOR NOTICE SIDEWALK - BROOKLYN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023K | Prior Notice Sidewalks - Brooklyn | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023K | Prior Notice Sidewalks - Brooklyn | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023K | Prior Notice Sidewalks - Brooklyn | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2024 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023K | Prior Notice Sidewalks - Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2024 | Oct 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023K | Prior Notice Sidewalks - Brooklyn | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2024 | Feb 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023K | Prior Notice Sidewalks - Brooklyn | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2025 | Jun 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023K | Prior Notice Sidewalks - Brooklyn | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2025 | Oct 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023K | Prior Notice Sidewalks - Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2025 | Jan 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023K | Prior Notice Sidewalks - Brooklyn | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2026 | Mar 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023K | Prior Notice Sidewalks - Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2026 | Apr 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWSRT200E | Safe Routes to Transit: 86th Street, BED-828 | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2020 | Sep 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWSRT200E | Safe Routes to Transit: 86th Street, BED-828 | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2020 | Jan 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWSRT200E | Safe Routes to Transit: 86th Street, BED-828 | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2021 | Jul 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWSRT200E | Safe Routes to Transit: 86th Street, BED-828 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2021 | Oct 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWSRT200E | Safe Routes to Transit: 86th Street, BED-828 | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2021 | Feb 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWSRT200E | Safe Routes to Transit: 86th Street, BED-828 | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2022 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWSRT200E | Safe Routes to Transit: 86th Street, BED-828 | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2022 | Oct 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWSRT200E | Safe Routes to Transit: 86th Street, BED-828 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2022 | Jan 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWSRT200E | Safe Routes to Transit: 86th Street, BED-828 | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2023 | Mar 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWSRT200E | Safe Routes to Transit: 86th Street, BED-828 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2023 | Jun 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK1 | Trench Restoration - Brooklyn | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK1 | Trench Restoration - Brooklyn | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK1 | Trench Restoration - Brooklyn | 3 | FINAL DESIGN | Sep 2017 | Apr 2020 | Sep 2017 | Apr 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK1 | Trench Restoration - Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2020 | Jul 2020 | Apr 2020 | Jul 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK1 | Trench Restoration - Brooklyn | 5 | CONSTRUCTION TO 25% | Jul 2020 | Nov 2020 | Jul 2020 | Nov 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK1 | Trench Restoration - Brooklyn | 6 | CONSTRUCTION TO 50% | Nov 2020 | Mar 2021 | Nov 2020 | Mar 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK1 | Trench Restoration - Brooklyn | 7 | CONSTRUCTION TO 75% | Mar 2021 | Jul 2021 | Mar 2021 | Jul 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK1 | Trench Restoration - Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK1 | Trench Restoration - Brooklyn | 9 | SUBSTANTIAL COMPLETION | Oct 2021 | Dec 2021 | Oct 2021 | Dec 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK1 | Trench Restoration - Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2021 | Jan 2022 | Dec 2021 | Jan 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK1 | Trench Restoration - Brooklyn | 11 | PROJECT START | Dec 2021 | Jan 2022 | Jan 2023 | Jan 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK1 | Trench Restoration - Brooklyn | 12 | DESIGN START | Dec 2021 | Jan 2022 | Jan 2023 | Jan 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK1 | Trench Restoration - Brooklyn | 13 | DESIGN COMPLETION | Dec 2021 | Jan 2022 | Jan 2023 | Jan 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK1 | Trench Restoration - Brooklyn | 14 | CONSTRUCTION START | Dec 2021 | Jan 2022 | Jan 2023 | Jan 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK1 | Trench Restoration - Brooklyn | 15 | CONSTRUCTION COMPLETION | Dec 2021 | Jan 2022 | Jan 2023 | Jan 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK883 | Trench Restoration -- Bay Parkway, Brooklyn, SE-883 | 1 | DEVELOP SCOPE | Mar 2020 | May 2020 | Mar 2020 | May 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK883 | Trench Restoration -- Bay Parkway, Brooklyn, SE-883 | 2 | PRELIMINARY DESIGN | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK883 | Trench Restoration -- Bay Parkway, Brooklyn, SE-883 | 3 | FINAL DESIGN | Sep 2020 | Mar 2021 | Sep 2020 | Mar 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK883 | Trench Restoration -- Bay Parkway, Brooklyn, SE-883 | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2021 | Jun 2021 | Mar 2021 | Jun 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK883 | Trench Restoration -- Bay Parkway, Brooklyn, SE-883 | 5 | CONSTRUCTION TO 25% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK883 | Trench Restoration -- Bay Parkway, Brooklyn, SE-883 | 6 | CONSTRUCTION TO 50% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK883 | Trench Restoration -- Bay Parkway, Brooklyn, SE-883 | 7 | CONSTRUCTION TO 75% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK883 | Trench Restoration -- Bay Parkway, Brooklyn, SE-883 | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK883 | Trench Restoration -- Bay Parkway, Brooklyn, SE-883 | 9 | SUBSTANTIAL COMPLETION | Sep 2022 | Nov 2022 | Sep 2022 | Nov 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK883 | Trench Restoration -- Bay Parkway, Brooklyn, SE-883 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2022 | Dec 2022 | Nov 2022 | Dec 2029
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC10CDHC | CLARENDON HVAC Replacement | 1 | PROJECT START | Nov 2009 | Oct 2010 | Nov 2009 | Nov 2009
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC10CDHC | CLARENDON HVAC Replacement | 2 | DESIGN START | Oct 2010 | Aug 2011 | Oct 2015 | Jan 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC10CDHC | CLARENDON HVAC Replacement | 3 | DESIGN COMPLETION | Aug 2011 | Nov 2011 | Jan 2020 | Nov 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC10CDHC | CLARENDON HVAC Replacement | 4 | CONSTRUCTION START | Nov 2011 | Jun 2013 | Nov 2020 | Apr 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC10CDHC | CLARENDON HVAC Replacement | 5 | CONSTRUCTION COMPLETION | Jun 2013 | Jun 2013 | Apr 2022 | Apr 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC11CHHC | CLINTON HILL - HVAC Replacement | 9 | SUBSTANTIAL COMPLETION | Feb 2013 | Apr 2013 | Nov 2015 | Nov 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC11CHHC | CLINTON HILL - HVAC Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2013 | May 2013 | Nov 2015 | Dec 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC12STHC | Saratoga Heating & Cooling | 1 | PROJECT START | Feb 2012 | Feb 2012 | Jun 2012 | Jun 2012
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC12STHC | Saratoga Heating & Cooling | 2 | DESIGN START | Feb 2012 | Mar 2013 | Sep 2014 | Apr 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC12STHC | Saratoga Heating & Cooling | 3 | DESIGN COMPLETION | Apr 2013 | Feb 2014 | Apr 2018 | Mar 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC12STHC | Saratoga Heating & Cooling | 4 | CONSTRUCTION START | Feb 2014 | Oct 2014 | Mar 2020 | Nov 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC12STHC | Saratoga Heating & Cooling | 5 | CONSTRUCTION COMPLETION | Oct 2014 | Aug 2015 | Nov 2020 | Sep 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC12STHC | Saratoga Heating & Cooling | 6 | DEVELOP SCOPE | Oct 2014 | Aug 2015 | Sep 2024 | Dec 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC12STHC | Saratoga Heating & Cooling | 7 | PRELIMINARY DESIGN | Oct 2014 | Aug 2015 | Dec 2024 | Apr 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC12STHC | Saratoga Heating & Cooling | 8 | FINAL DESIGN | Oct 2014 | Aug 2015 | Apr 2025 | Oct 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC12STHC | Saratoga Heating & Cooling | 9 | BID AWARD AND REGISTER CONTRCT | Oct 2014 | Aug 2015 | Oct 2025 | Jan 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC12STHC | Saratoga Heating & Cooling | 10 | CONSTRUCTION TO 25% | Oct 2014 | Aug 2015 | Jan 2026 | May 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC12STHC | Saratoga Heating & Cooling | 11 | CONSTRUCTION TO 50% | Oct 2014 | Aug 2015 | May 2026 | Sep 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC12STHC | Saratoga Heating & Cooling | 12 | CONSTRUCTION TO 75% | Oct 2014 | Aug 2015 | Sep 2026 | Jan 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC12STHC | Saratoga Heating & Cooling | 13 | ORIGINAL EQUIP & FURNISHING | Oct 2014 | Aug 2015 | Jan 2027 | Apr 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC12STHC | Saratoga Heating & Cooling | 14 | SUBSTANTIAL COMPLETION | Oct 2014 | Aug 2015 | Apr 2027 | Jun 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC12STHC | Saratoga Heating & Cooling | 15 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2014 | Aug 2015 | Jun 2027 | Jul 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC13BPRF | Borough Park Overhaul | 1 | PROJECT START | Apr 2013 | Jul 2014 | Apr 2013 | Jul 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC13BPRF | Borough Park Overhaul | 2 | DESIGN START | Jul 2014 | Oct 2015 | Sep 2014 | Dec 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC13BPRF | Borough Park Overhaul | 3 | DESIGN COMPLETION | Oct 2015 | May 2016 | Dec 2016 | Jul 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC13BPRF | Borough Park Overhaul | 4 | CONSTRUCTION START | May 2016 | Nov 2017 | Jul 2017 | Jan 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC13BPRF | Borough Park Overhaul | 5 | CONSTRUCTION COMPLETION | Nov 2017 | Nov 2017 | Jan 2025 | Jan 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC14LDRF | LEONARD ROOF REPLACEMENT | 1 | PROJECT START | Aug 2013 | Aug 2013 | Aug 2029 | Aug 2029
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC14LDRF | LEONARD ROOF REPLACEMENT | 2 | DESIGN START | Jan 2015 | Nov 2015 | Mar 2015 | May 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC14LDRF | LEONARD ROOF REPLACEMENT | 3 | DESIGN COMPLETION | Nov 2015 | Jul 2016 | May 2019 | Jan 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC14LDRF | LEONARD ROOF REPLACEMENT | 4 | CONSTRUCTION START | Jul 2016 | Apr 2017 | Jan 2020 | Oct 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC14LDRF | LEONARD ROOF REPLACEMENT | 5 | CONSTRUCTION COMPLETION | Apr 2017 | Apr 2017 | Oct 2020 | Jun 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC15BWHC | Bushwick Heating & Cooling | 1 | PROJECT START | Oct 2014 | Oct 2014 | Oct 2014 | Oct 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC15BWHC | Bushwick Heating & Cooling | 2 | DESIGN START | May 2014 | Dec 2015 | Jan 2016 | Sep 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC15BWHC | Bushwick Heating & Cooling | 3 | DESIGN COMPLETION | Dec 2015 | May 2016 | Sep 2019 | Feb 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC15BWHC | Bushwick Heating & Cooling | 4 | CONSTRUCTION START | May 2016 | Oct 2016 | Feb 2020 | Jul 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC15BWHC | Bushwick Heating & Cooling | 5 | CONSTRUCTION COMPLETION | Oct 2016 | Oct 2016 | Oct 2022 | Oct 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC16MD2F | MIDWOOD 2ND FLOOR RENOVATIONS | 1 | PROJECT START | Oct 2015 | Oct 2015 | Oct 2015 | Oct 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC16MD2F | MIDWOOD 2ND FLOOR RENOVATIONS | 2 | DESIGN START | Jul 2016 | Oct 2017 | Jul 2016 | Oct 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC16MD2F | MIDWOOD 2ND FLOOR RENOVATIONS | 3 | DESIGN COMPLETION | Oct 2017 | Oct 2017 | Oct 2017 | Jul 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC16MD2F | MIDWOOD 2ND FLOOR RENOVATIONS | 4 | CONSTRUCTION START | Sep 2018 | Aug 2019 | Jul 2021 | Dec 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC16MD2F | MIDWOOD 2ND FLOOR RENOVATIONS | 5 | CONSTRUCTION COMPLETION | Sep 2019 | Sep 2019 | Dec 2022 | Oct 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC16MPHC | MAPLETON HVAC REPLACEMENT | 1 | PROJECT START | Aug 2015 | Aug 2015 | Aug 2015 | Aug 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC16MPHC | MAPLETON HVAC REPLACEMENT | 2 | DESIGN START | Dec 2015 | May 2016 | Apr 2016 | Oct 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC16MPHC | MAPLETON HVAC REPLACEMENT | 3 | DESIGN COMPLETION | May 2016 | May 2016 | Oct 2018 | Jul 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC16MPHC | MAPLETON HVAC REPLACEMENT | 4 | CONSTRUCTION START | Oct 2016 | Apr 2017 | Jul 2019 | Feb 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC16MPHC | MAPLETON HVAC REPLACEMENT | 5 | CONSTRUCTION COMPLETION | Apr 2017 | Apr 2017 | Feb 2021 | Oct 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17CDOP | CLARENDON OUTDOOR PLAZA | 1 | PROJECT START | Oct 2018 | Oct 2018 | Oct 2018 | Oct 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17CDOP | CLARENDON OUTDOOR PLAZA | 2 | DESIGN START | Oct 2019 | Apr 2020 | Oct 2019 | Apr 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17CDOP | CLARENDON OUTDOOR PLAZA | 3 | DESIGN COMPLETION | Apr 2020 | May 2021 | Apr 2020 | May 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17CDOP | CLARENDON OUTDOOR PLAZA | 4 | CONSTRUCTION START | May 2021 | Feb 2022 | May 2021 | Feb 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17CDOP | CLARENDON OUTDOOR PLAZA | 5 | CONSTRUCTION COMPLETION | Feb 2022 | Feb 2022 | Feb 2022 | Feb 2031
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17MPGD | MAPLETON GARDEN RENOVATION | 1 | PROJECT START | Jan 2017 | Jan 2017 | Jan 2017 | Jul 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17MPGD | MAPLETON GARDEN RENOVATION | 2 | DESIGN START | Jul 2017 | Sep 2018 | Jul 2017 | Oct 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17MPGD | MAPLETON GARDEN RENOVATION | 3 | DESIGN COMPLETION | Sep 2018 | Apr 2019 | Oct 2019 | May 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17MPGD | MAPLETON GARDEN RENOVATION | 4 | CONSTRUCTION START | Apr 2019 | Apr 2020 | Jan 2021 | Jan 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17MPGD | MAPLETON GARDEN RENOVATION | 5 | CONSTRUCTION COMPLETION | Apr 2020 | Apr 2020 | Jan 2022 | Jan 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC22KBIF | KINGS BAY INFRASTRUCTURE UPGRADE | 1 | DESIGN | Jun 2023 | May 2024 | Jun 2023 | Jun 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC22KBIF | KINGS BAY INFRASTRUCTURE UPGRADE | 2 | CONSTRUCTION | May 2024 | Nov 2024 | Jun 2023 | Nov 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC22KBIF | KINGS BAY INFRASTRUCTURE UPGRADE | 3 | PROJECT START | May 2024 | Nov 2024 | Jun 2024 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC22KBIF | KINGS BAY INFRASTRUCTURE UPGRADE | 4 | DESIGN START | May 2024 | Nov 2024 | Jul 2024 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC22KBIF | KINGS BAY INFRASTRUCTURE UPGRADE | 5 | DESIGN COMPLETION | May 2024 | Nov 2024 | Jul 2025 | Jul 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC22KBIF | KINGS BAY INFRASTRUCTURE UPGRADE | 6 | CONSTRUCTION START | May 2024 | Nov 2024 | Jul 2025 | Jul 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC22KBIF | KINGS BAY INFRASTRUCTURE UPGRADE | 7 | CONSTRUCTION COMPLETION | May 2024 | Nov 2024 | Jul 2027 | Jul 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC22SAIF | STONE AVENUE INFRASTRUCTURE UPGRADE | 1 | DESIGN | Jun 2023 | May 2024 | Jun 2023 | Jun 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC22SAIF | STONE AVENUE INFRASTRUCTURE UPGRADE | 2 | CONSTRUCTION | May 2024 | Nov 2024 | Jun 2023 | Jun 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC22SAIF | STONE AVENUE INFRASTRUCTURE UPGRADE | 3 | PROJECT START | May 2024 | Nov 2024 | Jun 2024 | Jun 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC22SAIF | STONE AVENUE INFRASTRUCTURE UPGRADE | 4 | DESIGN START | May 2024 | Nov 2024 | Jun 2024 | Jun 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC22SAIF | STONE AVENUE INFRASTRUCTURE UPGRADE | 5 | DESIGN COMPLETION | May 2024 | Nov 2024 | Jun 2025 | Jun 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC22SAIF | STONE AVENUE INFRASTRUCTURE UPGRADE | 6 | CONSTRUCTION START | May 2024 | Nov 2024 | Jun 2025 | Jun 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC22SAIF | STONE AVENUE INFRASTRUCTURE UPGRADE | 7 | CONSTRUCTION COMPLETION | May 2024 | Nov 2024 | Jun 2025 | Jun 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK13EFBR | EAST FLATBUSH - BRANCH RENOVATION | 1 | PROJECT START | Jul 2013 | Aug 2014 | Jul 2013 | Jul 2013
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK13EFBR | EAST FLATBUSH - BRANCH RENOVATION | 2 | DESIGN START | Aug 2014 | Sep 2015 | Sep 2014 | Sep 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK13EFBR | EAST FLATBUSH - BRANCH RENOVATION | 3 | DESIGN COMPLETION | Sep 2015 | Mar 2016 | Sep 2015 | Dec 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK13EFBR | EAST FLATBUSH - BRANCH RENOVATION | 4 | CONSTRUCTION START | Mar 2016 | Mar 2018 | Dec 2017 | Aug 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK13EFBR | EAST FLATBUSH - BRANCH RENOVATION | 5 | CONSTRUCTION COMPLETION | Mar 2018 | Mar 2018 | Aug 2018 | Aug 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK15BDHC | Bedford Heating & Cooling | 1 | PROJECT START | Jan 2015 | Jan 2015 | Jan 2015 | Dec 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK15BDHC | Bedford Heating & Cooling | 2 | DESIGN START | Oct 2015 | Jun 2016 | Dec 2016 | Dec 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK15BDHC | Bedford Heating & Cooling | 3 | DESIGN COMPLETION | Jul 2016 | Nov 2016 | Dec 2016 | Mar 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK15BDHC | Bedford Heating & Cooling | 4 | CONSTRUCTION START | Nov 2016 | May 2017 | Mar 2023 | Jul 2028
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK15BDHC | Bedford Heating & Cooling | 5 | CONSTRUCTION COMPLETION | May 2017 | May 2017 | Jul 2028 | Jul 2028
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK16STRF | Saratoga Envelope Rehab | 1 | PROJECT START | Sep 2017 | Sep 2017 | Sep 2017 | Sep 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK16STRF | Saratoga Envelope Rehab | 2 | DESIGN START | Nov 2018 | Nov 2019 | Nov 2018 | Nov 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK16STRF | Saratoga Envelope Rehab | 3 | DESIGN COMPLETION | Nov 2019 | May 2020 | Nov 2019 | May 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK16STRF | Saratoga Envelope Rehab | 4 | CONSTRUCTION START | May 2020 | Oct 2021 | May 2020 | Oct 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK16STRF | Saratoga Envelope Rehab | 5 | CONSTRUCTION COMPLETION | Oct 2021 | Oct 2021 | Oct 2021 | Jun 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13CGHC | Carroll Gardens HVAC & Teen Ctr | 1 | PROJECT START | Jul 2013 | Jul 2013 | Jul 2013 | Jul 2013
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13CGHC | Carroll Gardens HVAC & Teen Ctr | 2 | DESIGN START | Jul 2014 | Apr 2015 | Oct 2014 | Sep 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13CGHC | Carroll Gardens HVAC & Teen Ctr | 3 | DESIGN COMPLETION | Apr 2015 | Aug 2015 | Sep 2016 | Sep 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13CGHC | Carroll Gardens HVAC & Teen Ctr | 4 | CONSTRUCTION START | Aug 2015 | Jun 2016 | Sep 2018 | Dec 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13CGHC | Carroll Gardens HVAC & Teen Ctr | 5 | CONSTRUCTION COMPLETION | Jun 2016 | Jun 2016 | Dec 2023 | Dec 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13LDHC | LEONARD HVAC REPLACEMENT | 1 | PROJECT START | Jul 2013 | Jul 2013 | Jul 2013 | Jul 2013
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13LDHC | LEONARD HVAC REPLACEMENT | 2 | DESIGN START | Nov 2014 | Jul 2015 | Mar 2015 | Sep 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13LDHC | LEONARD HVAC REPLACEMENT | 3 | DESIGN COMPLETION | Jul 2015 | Nov 2015 | Sep 2017 | Jan 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13LDHC | LEONARD HVAC REPLACEMENT | 4 | CONSTRUCTION START | Nov 2015 | Aug 2016 | Feb 2020 | Jan 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13LDHC | LEONARD HVAC REPLACEMENT | 5 | CONSTRUCTION COMPLETION | Aug 2016 | Aug 2016 | Feb 2021 | Jun 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14BWRF | BUSHWICK ROOF REPLACEMENT | 1 | PROJECT START | Feb 2014 | Feb 2014 | Apr 2016 | Apr 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14BWRF | BUSHWICK ROOF REPLACEMENT | 2 | DESIGN START | Mar 2015 | Feb 2016 | Oct 2015 | Jan 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14BWRF | BUSHWICK ROOF REPLACEMENT | 3 | DESIGN COMPLETION | Feb 2016 | May 2016 | Jan 2020 | Mar 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14BWRF | BUSHWICK ROOF REPLACEMENT | 4 | CONSTRUCTION START | May 2016 | Jul 2017 | Mar 2020 | Jun 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14BWRF | BUSHWICK ROOF REPLACEMENT | 5 | CONSTRUCTION COMPLETION | Jul 2017 | Jul 2017 | Jun 2021 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14BWRF | BUSHWICK ROOF REPLACEMENT | 6 | DEVELOP SCOPE | Jul 2017 | Jul 2017 | Jun 2022 | Sep 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14BWRF | BUSHWICK ROOF REPLACEMENT | 7 | PRELIMINARY DESIGN | Jul 2017 | Jul 2017 | Sep 2022 | Dec 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14BWRF | BUSHWICK ROOF REPLACEMENT | 8 | FINAL DESIGN | Jul 2017 | Jul 2017 | Jan 2023 | Jun 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14BWRF | BUSHWICK ROOF REPLACEMENT | 9 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Jul 2017 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14BWRF | BUSHWICK ROOF REPLACEMENT | 10 | CONSTRUCTION TO 25% | Jul 2017 | Jul 2017 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14BWRF | BUSHWICK ROOF REPLACEMENT | 11 | CONSTRUCTION TO 50% | Jul 2017 | Jul 2017 | Jan 2024 | May 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14BWRF | BUSHWICK ROOF REPLACEMENT | 12 | CONSTRUCTION TO 75% | Jul 2017 | Jul 2017 | May 2024 | Sep 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14BWRF | BUSHWICK ROOF REPLACEMENT | 13 | ORIGINAL EQUIP & FURNISHING | Jul 2017 | Jul 2017 | Sep 2024 | Dec 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14BWRF | BUSHWICK ROOF REPLACEMENT | 14 | SUBSTANTIAL COMPLETION | Jul 2017 | Jul 2017 | Dec 2024 | Feb 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14BWRF | BUSHWICK ROOF REPLACEMENT | 15 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2017 | Jul 2017 | Feb 2025 | Mar 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15GBRF | GERRITSEN BEACH ENVELOPE REHAB | 1 | PROJECT START | Dec 2014 | Dec 2014 | Dec 2014 | Dec 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15GBRF | GERRITSEN BEACH ENVELOPE REHAB | 2 | DESIGN START | May 2015 | Aug 2015 | Mar 2016 | Nov 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15GBRF | GERRITSEN BEACH ENVELOPE REHAB | 3 | DESIGN COMPLETION | Aug 2015 | Dec 2015 | Dec 2022 | Apr 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15GBRF | GERRITSEN BEACH ENVELOPE REHAB | 4 | CONSTRUCTION START | Dec 2015 | Jul 2016 | Apr 2023 | Oct 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15GBRF | GERRITSEN BEACH ENVELOPE REHAB | 5 | CONSTRUCTION COMPLETION | Jul 2016 | Jul 2016 | Oct 2023 | Oct 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15MPRF | Mapleton Envelope Rehabilitation | 1 | PROJECT START | Nov 2014 | Nov 2014 | Nov 2014 | Nov 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15MPRF | Mapleton Envelope Rehabilitation | 2 | DESIGN START | Jun 2015 | Oct 2015 | Jun 2015 | Mar 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15MPRF | Mapleton Envelope Rehabilitation | 3 | DESIGN COMPLETION | Oct 2015 | Jul 2016 | Mar 2018 | Nov 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15MPRF | Mapleton Envelope Rehabilitation | 4 | CONSTRUCTION START | Jul 2016 | Jul 2017 | Dec 2020 | Apr 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15MPRF | Mapleton Envelope Rehabilitation | 5 | CONSTRUCTION COMPLETION | Jul 2017 | Jul 2017 | May 2023 | May 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15RDHC | Ryder Heating & Cooling | 1 | PROJECT START | Dec 2014 | Dec 2014 | Dec 2013 | Dec 2013
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15RDHC | Ryder Heating & Cooling | 2 | DESIGN START | Aug 2014 | Mar 2016 | Nov 2017 | Jan 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15RDHC | Ryder Heating & Cooling | 3 | DESIGN COMPLETION | Mar 2016 | Jul 2016 | Jan 2022 | May 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15RDHC | Ryder Heating & Cooling | 4 | CONSTRUCTION START | Jul 2016 | May 2017 | May 2022 | Apr 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15RDHC | Ryder Heating & Cooling | 5 | CONSTRUCTION COMPLETION | May 2017 | May 2017 | Apr 2023 | Jun 2031
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15RDRF | Ryder Envelope Rehabilitation | 1 | PROJECT START | Oct 2014 | Oct 2014 | Oct 2014 | Oct 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15RDRF | Ryder Envelope Rehabilitation | 2 | DESIGN START | Jan 2016 | Sep 2016 | Nov 2015 | Feb 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15RDRF | Ryder Envelope Rehabilitation | 3 | DESIGN COMPLETION | Sep 2016 | Jul 2017 | Feb 2019 | Dec 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15RDRF | Ryder Envelope Rehabilitation | 4 | CONSTRUCTION START | Jul 2017 | May 2018 | Dec 2019 | Oct 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15RDRF | Ryder Envelope Rehabilitation | 5 | CONSTRUCTION COMPLETION | May 2018 | May 2018 | Oct 2020 | May 2030
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM16GSFC | GRAVESEND FACADE REHAB | 1 | PROJECT START | Jan 2008 | Jan 2008 | Jan 2008 | Jan 2008
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM16GSFC | GRAVESEND FACADE REHAB | 2 | DESIGN START | Jan 2008 | Jan 2008 | Sep 2016 | Nov 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM16GSFC | GRAVESEND FACADE REHAB | 3 | DESIGN COMPLETION | Jan 2008 | Jan 2008 | Nov 2017 | Jul 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM16GSFC | GRAVESEND FACADE REHAB | 4 | CONSTRUCTION START | Jan 2008 | Jan 2008 | Jul 2020 | Jul 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM16GSFC | GRAVESEND FACADE REHAB | 5 | CONSTRUCTION COMPLETION | Jan 2008 | Jan 2008 | Jul 2021 | Feb 2032
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM17ARBR | ARLINGTON BRANCH RENOVATION | 1 | PROJECT START | Jan 2018 | Jan 2018 | Jan 2018 | Jan 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM17ARBR | ARLINGTON BRANCH RENOVATION | 2 | DESIGN START | Feb 2019 | Sep 2020 | Feb 2019 | Sep 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM17ARBR | ARLINGTON BRANCH RENOVATION | 3 | DESIGN COMPLETION | Sep 2020 | Jul 2021 | Sep 2020 | Jul 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM17ARBR | ARLINGTON BRANCH RENOVATION | 4 | CONSTRUCTION START | Jul 2021 | Jul 2023 | Jul 2021 | Jul 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM17ARBR | ARLINGTON BRANCH RENOVATION | 5 | CONSTRUCTION COMPLETION | Jul 2023 | Jul 2023 | Jul 2023 | Jul 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM17NUOH | New Utrecht Overhaul | 1 | PROJECT START | Sep 2017 | Sep 2017 | Sep 2017 | Sep 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM17NUOH | New Utrecht Overhaul | 2 | DESIGN START | Jul 2018 | Jun 2020 | Jul 2018 | Jun 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM17NUOH | New Utrecht Overhaul | 3 | DESIGN COMPLETION | Jun 2020 | Mar 2021 | Jun 2020 | Mar 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM17NUOH | New Utrecht Overhaul | 4 | CONSTRUCTION START | Mar 2021 | Mar 2024 | Mar 2021 | Mar 2028
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM17NUOH | New Utrecht Overhaul | 5 | CONSTRUCTION COMPLETION | Mar 2024 | Mar 2024 | Mar 2028 | Mar 2028
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM18BVOH | Brownsville Overhaul | 1 | PROJECT START | Sep 2017 | Sep 2017 | Sep 2017 | Sep 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM18BVOH | Brownsville Overhaul | 2 | DESIGN START | Jul 2018 | Jun 2020 | Jul 2018 | Jun 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM18BVOH | Brownsville Overhaul | 3 | DESIGN COMPLETION | Jun 2020 | Mar 2021 | Jun 2020 | Mar 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM18BVOH | Brownsville Overhaul | 4 | CONSTRUCTION START | Mar 2021 | Mar 2024 | Mar 2024 | Mar 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM18BVOH | Brownsville Overhaul | 5 | CONSTRUCTION COMPLETION | Mar 2024 | Mar 2024 | Mar 2027 | Mar 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM18EPOH | Eastern Parkway Overhaul | 1 | PROJECT START | Nov 2017 | Nov 2017 | Nov 2017 | Nov 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM18EPOH | Eastern Parkway Overhaul | 2 | DESIGN START | Jul 2018 | Nov 2020 | Jul 2018 | Nov 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM18EPOH | Eastern Parkway Overhaul | 3 | DESIGN COMPLETION | Nov 2020 | Mar 2021 | Nov 2020 | Mar 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM18EPOH | Eastern Parkway Overhaul | 4 | CONSTRUCTION START | Mar 2021 | Mar 2024 | Mar 2021 | Mar 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM18EPOH | Eastern Parkway Overhaul | 5 | CONSTRUCTION COMPLETION | Mar 2024 | Mar 2024 | Mar 2027 | Mar 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBP18LDIN | LEONARD INFRASTRUCTURE UPGRADE | 1 | DESIGN | Jul 2020 | Jun 2021 | Jul 2024 | Jun 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBP18LDIN | LEONARD INFRASTRUCTURE UPGRADE | 2 | CONSTRUCTION | Jul 2021 | Jun 2024 | Jul 2025 | Jun 2028
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBP21WIBR | WASHINGTON IRVING RENOVATION | 1 | DESIGN | Jul 2024 | Jun 2025 | Jul 2024 | Jun 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBP21WIBR | WASHINGTON IRVING RENOVATION | 2 | CONSTRUCTION | Jul 2025 | Dec 2025 | Jul 2025 | Dec 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBP21WIBR | WASHINGTON IRVING RENOVATION | 3 | PROJECT START | Jul 2025 | Dec 2025 | Dec 2025 | Dec 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBP21WIBR | WASHINGTON IRVING RENOVATION | 4 | DESIGN START | Jul 2025 | Dec 2025 | Dec 2025 | Dec 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBP21WIBR | WASHINGTON IRVING RENOVATION | 5 | DESIGN COMPLETION | Jul 2025 | Dec 2025 | Dec 2025 | Dec 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBP21WIBR | WASHINGTON IRVING RENOVATION | 6 | CONSTRUCTION START | Jul 2025 | Dec 2025 | Dec 2025 | Dec 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBP21WIBR | WASHINGTON IRVING RENOVATION | 7 | CONSTRUCTION COMPLETION | Jul 2025 | Dec 2025 | Jan 2026 | Jan 2032
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NEWCJC2 | NEW CONSTRUCTION AT CROSSROADS JC PHASE 2.0 | 1 | DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NEWCJC2 | NEW CONSTRUCTION AT CROSSROADS JC PHASE 2.0 | 2 | CONSTRUCTION | Jul 2023 | Jun 2024 | Jul 2023 | Jun 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NEWCJC2 | NEW CONSTRUCTION AT CROSSROADS JC PHASE 2.0 | 3 | PROJECT START | Jul 2023 | Jun 2024 | Jul 2024 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NEWCJC2 | NEW CONSTRUCTION AT CROSSROADS JC PHASE 2.0 | 4 | DESIGN START | Jul 2023 | Jun 2024 | Jul 2024 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NEWCJC2 | NEW CONSTRUCTION AT CROSSROADS JC PHASE 2.0 | 5 | DESIGN COMPLETION | Jul 2023 | Jun 2024 | Jul 2024 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NEWCJC2 | NEW CONSTRUCTION AT CROSSROADS JC PHASE 2.0 | 6 | CONSTRUCTION START | Jul 2023 | Jun 2024 | Jul 2024 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NEWCJC2 | NEW CONSTRUCTION AT CROSSROADS JC PHASE 2.0 | 7 | CONSTRUCTION COMPLETION | Jul 2023 | Jun 2024 | Jul 2024 | Jul 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-217SCRC | Shirley Chisholm Recreation Center-Nostrand Playground DB | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-217SCRC | Shirley Chisholm Recreation Center-Nostrand Playground DB | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-217SCRC | Shirley Chisholm Recreation Center-Nostrand Playground DB | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-217SCRC | Shirley Chisholm Recreation Center-Nostrand Playground DB | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-217SCRC | Shirley Chisholm Recreation Center-Nostrand Playground DB | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-2CIB1HQ | Coney Island Beach Operations HQ at West 25th Street | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-2CIB1HQ | Coney Island Beach Operations HQ at West 25th Street | 2 | DESIGN | Dec 2019 | Dec 2021 | Dec 2019 | Dec 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-2CIB1HQ | Coney Island Beach Operations HQ at West 25th Street | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-2CIB1HQ | Coney Island Beach Operations HQ at West 25th Street | 4 | CONSTRUCTION | Sep 2022 | Sep 2024 | Sep 2022 | Sep 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-2CIB1HQ | Coney Island Beach Operations HQ at West 25th Street | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77AX | 77TH PRECINCT ANNEX RENOVATION | 1 | DEVELOP SCOPE | May 2013 | Aug 2013 | May 2013 | Aug 2013
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77AX | 77TH PRECINCT ANNEX RENOVATION | 2 | PRELIMINARY DESIGN | Aug 2013 | Dec 2013 | Aug 2013 | Dec 2013
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77AX | 77TH PRECINCT ANNEX RENOVATION | 3 | FINAL DESIGN | Dec 2013 | Jun 2014 | Dec 2013 | Jun 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77AX | 77TH PRECINCT ANNEX RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2014 | Sep 2014 | Jun 2014 | Sep 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77AX | 77TH PRECINCT ANNEX RENOVATION | 5 | CONSTRUCTION TO 25% | Sep 2014 | Jan 2015 | Sep 2014 | Jan 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77AX | 77TH PRECINCT ANNEX RENOVATION | 6 | CONSTRUCTION TO 50% | Jan 2015 | May 2015 | Jan 2015 | May 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77AX | 77TH PRECINCT ANNEX RENOVATION | 7 | CONSTRUCTION TO 75% | May 2015 | Sep 2015 | May 2015 | Sep 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77AX | 77TH PRECINCT ANNEX RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77AX | 77TH PRECINCT ANNEX RENOVATION | 9 | SUBSTANTIAL COMPLETION | Dec 2015 | Feb 2016 | Dec 2015 | Feb 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77AX | 77TH PRECINCT ANNEX RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2016 | Mar 2016 | Feb 2016 | Jun 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77AX | 77TH PRECINCT ANNEX RENOVATION | 11 | PROJECT START | Feb 2016 | Mar 2016 | Jul 2023 | Jul 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77AX | 77TH PRECINCT ANNEX RENOVATION | 12 | DESIGN START | Feb 2016 | Mar 2016 | Jul 2023 | Jul 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77AX | 77TH PRECINCT ANNEX RENOVATION | 13 | DESIGN COMPLETION | Feb 2016 | Mar 2016 | Jul 2023 | Jul 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77AX | 77TH PRECINCT ANNEX RENOVATION | 14 | CONSTRUCTION START | Feb 2016 | Mar 2016 | Jul 2023 | Jul 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77AX | 77TH PRECINCT ANNEX RENOVATION | 15 | CONSTRUCTION COMPLETION | Feb 2016 | Mar 2016 | Jul 2023 | Jul 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77FA | 77TH PRECINCT FIRE ALARM SYSTEM | 1 | PROJECT START | Mar 2018 | Mar 2018 | Mar 2018 | Mar 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77FA | 77TH PRECINCT FIRE ALARM SYSTEM | 2 | DESIGN START | Mar 2018 | Mar 2018 | Mar 2018 | Jun 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77FA | 77TH PRECINCT FIRE ALARM SYSTEM | 3 | DESIGN COMPLETION | Mar 2018 | Mar 2018 | Jun 2019 | Dec 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77FA | 77TH PRECINCT FIRE ALARM SYSTEM | 4 | CONSTRUCTION START | Mar 2018 | Mar 2018 | Dec 2020 | Oct 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77FA | 77TH PRECINCT FIRE ALARM SYSTEM | 5 | CONSTRUCTION COMPLETION | Mar 2018 | Mar 2018 | Oct 2021 | Oct 2028
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | 1 | PROJECT START | May 2016 | May 2016 | May 2016 | May 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | 2 | DESIGN START | May 2016 | May 2016 | May 2016 | May 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | 3 | DESIGN COMPLETION | May 2016 | May 2016 | May 2016 | May 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | 4 | CONSTRUCTION START | May 2016 | May 2016 | May 2016 | May 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | 5 | CONSTRUCTION COMPLETION | May 2016 | May 2016 | May 2016 | May 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | 6 | DEVELOP SCOPE | May 2016 | Aug 2016 | May 2016 | Aug 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | 7 | PRELIMINARY DESIGN | Aug 2016 | Dec 2016 | Aug 2016 | Dec 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | 8 | FINAL DESIGN | Dec 2016 | Jun 2017 | Dec 2016 | Jun 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | 9 | BID AWARD AND REGISTER CONTRCT | Jun 2017 | Sep 2017 | Jun 2017 | Sep 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | 10 | CONSTRUCTION TO 25% | Sep 2017 | Jan 2018 | Sep 2017 | Jan 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | 11 | CONSTRUCTION TO 50% | Jan 2018 | May 2018 | Jan 2018 | May 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | 12 | CONSTRUCTION TO 75% | May 2018 | Sep 2018 | May 2018 | Sep 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | 13 | ORIGINAL EQUIP & FURNISHING | Sep 2018 | Dec 2018 | Sep 2018 | Dec 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | 14 | SUBSTANTIAL COMPLETION | Dec 2018 | Feb 2019 | Dec 2018 | Feb 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | 15 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2019 | Mar 2019 | Feb 2019 | Jun 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV072HVAC | CBH - HVAC Upgrade | 1 | PROJECT START | Apr 2018 | Apr 2018 | Apr 2018 | Apr 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV072HVAC | CBH - HVAC Upgrade | 2 | DESIGN START | Apr 2018 | Feb 2020 | Apr 2018 | Feb 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV072HVAC | CBH - HVAC Upgrade | 3 | DESIGN COMPLETION | Feb 2020 | Apr 2022 | Feb 2020 | Apr 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV072HVAC | CBH - HVAC Upgrade | 4 | CONSTRUCTION START | Apr 2022 | Sep 2022 | Apr 2022 | Sep 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV072HVAC | CBH - HVAC Upgrade | 5 | CONSTRUCTION COMPLETION | Sep 2022 | Jun 2023 | Sep 2022 | Jun 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235BDEV | BMA - Brooklyn Museum - Building Envelope Renovation | 1 | DEVELOP SCOPE | Oct 2019 | Apr 2020 | Apr 2020 | Apr 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235BDEV | BMA - Brooklyn Museum - Building Envelope Renovation | 2 | PRELIMINARY DESIGN | May 2020 | Aug 2020 | Apr 2020 | Aug 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235BDEV | BMA - Brooklyn Museum - Building Envelope Renovation | 3 | FINAL DESIGN | Aug 2020 | Feb 2021 | Aug 2020 | Feb 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235BDEV | BMA - Brooklyn Museum - Building Envelope Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2021 | May 2021 | Feb 2021 | May 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235BDEV | BMA - Brooklyn Museum - Building Envelope Renovation | 5 | CONSTRUCTION TO 25% | May 2021 | Sep 2021 | May 2021 | Jul 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235BDEV | BMA - Brooklyn Museum - Building Envelope Renovation | 6 | CONSTRUCTION TO 50% | Sep 2021 | Jan 2022 | May 2021 | Jul 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235BDEV | BMA - Brooklyn Museum - Building Envelope Renovation | 7 | CONSTRUCTION TO 75% | Jan 2022 | May 2022 | May 2021 | Jul 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235BDEV | BMA - Brooklyn Museum - Building Envelope Renovation | 8 | ORIGINAL EQUIP & FURNISHING | May 2022 | Aug 2022 | May 2021 | Jul 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235BDEV | BMA - Brooklyn Museum - Building Envelope Renovation | 9 | SUBSTANTIAL COMPLETION | Aug 2022 | Oct 2022 | May 2021 | Jul 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235BDEV | BMA - Brooklyn Museum - Building Envelope Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2022 | Nov 2022 | May 2021 | Jul 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235EDUC | BMA - Brooklyn Museum - Education Space | 1 | DEVELOP SCOPE | Nov 2014 | Feb 2015 | Jul 2023 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235EDUC | BMA - Brooklyn Museum - Education Space | 2 | PRELIMINARY DESIGN | Feb 2015 | Jun 2015 | Jul 2024 | Oct 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235EDUC | BMA - Brooklyn Museum - Education Space | 3 | FINAL DESIGN | Jun 2015 | Dec 2015 | Oct 2024 | Apr 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235EDUC | BMA - Brooklyn Museum - Education Space | 4 | BID AWARD AND REGISTER CONTRCT | Dec 2015 | Mar 2016 | Apr 2025 | Jul 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235EDUC | BMA - Brooklyn Museum - Education Space | 5 | CONSTRUCTION TO 25% | Mar 2016 | Jul 2016 | Jul 2025 | Nov 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235EDUC | BMA - Brooklyn Museum - Education Space | 6 | CONSTRUCTION TO 50% | Jul 2016 | Nov 2016 | Nov 2025 | Mar 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235EDUC | BMA - Brooklyn Museum - Education Space | 7 | CONSTRUCTION TO 75% | Nov 2016 | Mar 2017 | Mar 2026 | Jul 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235EDUC | BMA - Brooklyn Museum - Education Space | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2017 | Jun 2017 | Jul 2026 | Oct 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235EDUC | BMA - Brooklyn Museum - Education Space | 9 | SUBSTANTIAL COMPLETION | Jun 2017 | Jul 2017 | Oct 2026 | Dec 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235EDUC | BMA - Brooklyn Museum - Education Space | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2017 | Aug 2017 | Dec 2026 | Jan 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | 1 | DEVELOP SCOPE | Jul 2012 | Sep 2012 | Jul 2012 | Sep 2012
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | 2 | PRELIMINARY DESIGN | Sep 2012 | Jan 2013 | Sep 2012 | Jan 2013
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | 3 | FINAL DESIGN | Jan 2013 | Jul 2013 | Jan 2013 | Jul 2013
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2013 | Oct 2013 | Jul 2013 | Oct 2013
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | 5 | CONSTRUCTION TO 25% | Oct 2013 | Feb 2014 | Oct 2013 | Feb 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | 6 | CONSTRUCTION TO 50% | Feb 2014 | Jun 2014 | Feb 2014 | Jun 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | 7 | CONSTRUCTION TO 75% | Jun 2014 | Oct 2014 | Jun 2014 | Oct 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2014 | Jan 2015 | Oct 2014 | Jan 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | 9 | SUBSTANTIAL COMPLETION | Jan 2015 | Mar 2015 | Jan 2015 | Mar 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Apr 2015 | Mar 2017 | Apr 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | 11 | PROJECT START | Mar 2015 | Apr 2015 | Apr 2017 | Apr 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | 12 | DESIGN START | Mar 2015 | Apr 2015 | Apr 2017 | Apr 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | 13 | DESIGN COMPLETION | Mar 2015 | Apr 2015 | Apr 2017 | Apr 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | 14 | CONSTRUCTION START | Mar 2015 | Apr 2015 | Apr 2017 | Apr 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | 15 | CONSTRUCTION COMPLETION | Mar 2015 | Apr 2015 | Apr 2017 | Apr 2032
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-RTW | BCM - Brooklyn Children's Museum Retaining Wall | 1 | PROJECT START | Jul 2017 | Jul 2017 | Jul 2017 | Jul 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-RTW | BCM - Brooklyn Children's Museum Retaining Wall | 2 | DESIGN START | Jan 2018 | Feb 2019 | Jan 2018 | Feb 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-RTW | BCM - Brooklyn Children's Museum Retaining Wall | 3 | DESIGN COMPLETION | Feb 2019 | Feb 2019 | Feb 2019 | Feb 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-RTW | BCM - Brooklyn Children's Museum Retaining Wall | 4 | CONSTRUCTION START | Feb 2019 | Feb 2019 | Feb 2019 | Feb 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-RTW | BCM - Brooklyn Children's Museum Retaining Wall | 5 | CONSTRUCTION COMPLETION | Feb 2019 | Jul 2024 | Feb 2019 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | 1 | DEVELOP SCOPE | Jan 2015 | Mar 2015 | Jan 2015 | Mar 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | 2 | PRELIMINARY DESIGN | Apr 2015 | Jul 2015 | Apr 2015 | Jul 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | 3 | FINAL DESIGN | Jul 2015 | Jan 2016 | Jul 2015 | Jan 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2016 | Apr 2016 | Jan 2016 | Apr 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | 5 | CONSTRUCTION TO 25% | Apr 2016 | Aug 2016 | Apr 2016 | Aug 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | 6 | CONSTRUCTION TO 50% | Aug 2016 | Dec 2016 | Aug 2016 | Dec 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | 7 | CONSTRUCTION TO 75% | Dec 2016 | Apr 2017 | Dec 2016 | Apr 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2017 | Jul 2017 | Apr 2017 | Jul 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | 9 | SUBSTANTIAL COMPLETION | Jul 2017 | Sep 2017 | Jul 2017 | Sep 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2017 | Oct 2017 | Sep 2017 | Oct 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | 11 | PROJECT START | Sep 2017 | Oct 2017 | Oct 2018 | Oct 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | 12 | DESIGN START | Sep 2017 | Oct 2017 | Oct 2018 | Oct 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | 13 | DESIGN COMPLETION | Sep 2017 | Oct 2017 | Oct 2018 | Oct 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | 14 | CONSTRUCTION START | Sep 2017 | Oct 2017 | Oct 2018 | Oct 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | 15 | CONSTRUCTION COMPLETION | Sep 2017 | Oct 2017 | Oct 2018 | Oct 2030
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | 1 | DEVELOP SCOPE | Jun 2012 | Sep 2012 | Feb 2012 | Feb 2012
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | 2 | PRELIMINARY DESIGN | Sep 2012 | Jan 2013 | Feb 2012 | Nov 2013
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | 3 | FINAL DESIGN | Jan 2013 | Jul 2013 | Nov 2013 | Mar 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2013 | Oct 2013 | Mar 2019 | Nov 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | 5 | CONSTRUCTION TO 25% | Oct 2013 | Feb 2014 | Nov 2019 | Apr 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | 6 | CONSTRUCTION TO 50% | Feb 2014 | Jun 2014 | Apr 2021 | Jul 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | 7 | CONSTRUCTION TO 75% | Jun 2014 | Oct 2014 | Aug 2021 | Nov 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2014 | Dec 2014 | Nov 2021 | Feb 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | 9 | SUBSTANTIAL COMPLETION | Dec 2014 | Feb 2015 | Feb 2022 | Mar 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2015 | Mar 2023 | Mar 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | 11 | PROJECT START | Mar 2015 | Mar 2015 | Mar 2024 | Mar 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | 12 | DESIGN START | Mar 2015 | Mar 2015 | Mar 2024 | Mar 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | 13 | DESIGN COMPLETION | Mar 2015 | Mar 2015 | Mar 2024 | Mar 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | 14 | CONSTRUCTION START | Mar 2015 | Mar 2015 | Mar 2024 | Mar 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | 15 | CONSTRUCTION COMPLETION | Mar 2015 | Mar 2015 | Mar 2024 | Mar 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWKBEFORD | BEDFORD ATLANTIC ARMORY - NENOVATIONS BEDFORD ATLANTIC ARMOR | 1 | PROJECT START | May 2010 | May 2010 | May 2011 | May 2011
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWKBEFORD | BEDFORD ATLANTIC ARMORY - NENOVATIONS BEDFORD ATLANTIC ARMOR | 2 | DESIGN START | Oct 2010 | Oct 2010 | May 2011 | May 2011
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWKBEFORD | BEDFORD ATLANTIC ARMORY - NENOVATIONS BEDFORD ATLANTIC ARMOR | 3 | DESIGN COMPLETION | Jan 2011 | Jan 2011 | May 2013 | May 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWKBEFORD | BEDFORD ATLANTIC ARMORY - NENOVATIONS BEDFORD ATLANTIC ARMOR | 4 | CONSTRUCTION START | Jun 2012 | Jun 2012 | Jul 2016 | Jul 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWKBEFORD | BEDFORD ATLANTIC ARMORY - NENOVATIONS BEDFORD ATLANTIC ARMOR | 5 | CONSTRUCTION COMPLETION | May 2014 | May 2014 | Jul 2018 | Aug 2031
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383N | Brooklyn 17/18 HVAC and Roof Replacement | 1 | PROJECT START | Jul 2015 | Jul 2015 | Sep 2015 | Sep 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383N | Brooklyn 17/18 HVAC and Roof Replacement | 2 | DESIGN START | Jul 2015 | Jul 2015 | Sep 2016 | May 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383N | Brooklyn 17/18 HVAC and Roof Replacement | 3 | DESIGN COMPLETION | Jul 2015 | Jul 2015 | May 2017 | Sep 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383N | Brooklyn 17/18 HVAC and Roof Replacement | 4 | CONSTRUCTION START | Jul 2015 | Jul 2015 | Oct 2019 | May 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383N | Brooklyn 17/18 HVAC and Roof Replacement | 5 | CONSTRUCTION COMPLETION | Jul 2015 | Jul 2017 | May 2020 | Jun 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-436 | Brooklyn 6 Garage Rehabilitation | 1 | DEVELOP SCOPE | May 2015 | Jul 2016 | May 2015 | Oct 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-436 | Brooklyn 6 Garage Rehabilitation | 2 | PRELIMINARY DESIGN | Jul 2016 | Oct 2017 | Oct 2015 | Dec 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-436 | Brooklyn 6 Garage Rehabilitation | 3 | FINAL DESIGN | Oct 2017 | Jan 2019 | Dec 2016 | Jan 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-436 | Brooklyn 6 Garage Rehabilitation | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2019 | Jan 2020 | Jan 2018 | Jun 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-436 | Brooklyn 6 Garage Rehabilitation | 5 | CONSTRUCTION TO 25% | Jan 2020 | May 2021 | Jun 2020 | Oct 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-436 | Brooklyn 6 Garage Rehabilitation | 6 | CONSTRUCTION TO 50% | May 2021 | Oct 2022 | Oct 2020 | Dec 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-436 | Brooklyn 6 Garage Rehabilitation | 7 | CONSTRUCTION TO 75% | Oct 2022 | Feb 2024 | Dec 2020 | Jun 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-436 | Brooklyn 6 Garage Rehabilitation | 8 | SUBSTANTIAL COMPLETION | Feb 2024 | Jul 2025 | Jun 2021 | Oct 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-436 | Brooklyn 6 Garage Rehabilitation | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Nov 2026 | Nov 2022 | Sep 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1048 | BWG - Sunset Park North, BED-807 | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1048 | BWG - Sunset Park North, BED-807 | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1048 | BWG - Sunset Park North, BED-807 | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1048 | BWG - Sunset Park North, BED-807 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1048 | BWG - Sunset Park North, BED-807 | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1048 | BWG - Sunset Park North, BED-807 | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1048 | BWG - Sunset Park North, BED-807 | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1048 | BWG - Sunset Park North, BED-807 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1048 | BWG - Sunset Park North, BED-807 | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1048 | BWG - Sunset Park North, BED-807 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Apr 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1048 | BWG - Sunset Park North, BED-807 | 11 | PROJECT START | Mar 2022 | Apr 2022 | Apr 2023 | Apr 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1048 | BWG - Sunset Park North, BED-807 | 12 | DESIGN START | Mar 2022 | Apr 2022 | Apr 2023 | Apr 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1048 | BWG - Sunset Park North, BED-807 | 13 | DESIGN COMPLETION | Mar 2022 | Apr 2022 | Apr 2023 | Apr 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1048 | BWG - Sunset Park North, BED-807 | 14 | CONSTRUCTION START | Mar 2022 | Apr 2022 | Apr 2023 | Apr 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1048 | BWG - Sunset Park North, BED-807 | 15 | CONSTRUCTION COMPLETION | Mar 2022 | Apr 2022 | Apr 2023 | Apr 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBRIGH | SANDY - NEW BRIGHTON COMFORT STATION RECONSTRUCTION | 1 | DEVELOP SCOPE | Nov 2017 | Jan 2018 | Nov 2017 | Jan 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBRIGH | SANDY - NEW BRIGHTON COMFORT STATION RECONSTRUCTION | 2 | PRELIMINARY DESIGN | Jan 2018 | May 2018 | Jan 2018 | May 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBRIGH | SANDY - NEW BRIGHTON COMFORT STATION RECONSTRUCTION | 3 | FINAL DESIGN | May 2018 | Nov 2018 | May 2018 | Nov 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBRIGH | SANDY - NEW BRIGHTON COMFORT STATION RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2018 | Feb 2019 | Nov 2018 | Feb 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBRIGH | SANDY - NEW BRIGHTON COMFORT STATION RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBRIGH | SANDY - NEW BRIGHTON COMFORT STATION RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | Jun 2019 | Oct 2019 | Jun 2019 | Oct 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBRIGH | SANDY - NEW BRIGHTON COMFORT STATION RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | Oct 2019 | Feb 2020 | Oct 2019 | Feb 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBRIGH | SANDY - NEW BRIGHTON COMFORT STATION RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2020 | May 2020 | Feb 2024 | May 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBRIGH | SANDY - NEW BRIGHTON COMFORT STATION RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | May 2020 | Jul 2020 | May 2024 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBRIGH | SANDY - NEW BRIGHTON COMFORT STATION RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Aug 2020 | Jul 2024 | Aug 2031
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC4 | 60TH PRECINCT ELECTRICAL SYSTEM REPLACEMENT( SANDY) | 1 | PROJECT START | Dec 2012 | Dec 2012 | Dec 2012 | Dec 2012
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC4 | 60TH PRECINCT ELECTRICAL SYSTEM REPLACEMENT( SANDY) | 2 | DESIGN START | Dec 2012 | Dec 2012 | Dec 2012 | Dec 2012
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC4 | 60TH PRECINCT ELECTRICAL SYSTEM REPLACEMENT( SANDY) | 3 | DESIGN COMPLETION | Dec 2012 | Mar 2013 | Dec 2012 | Mar 2013
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC4 | 60TH PRECINCT ELECTRICAL SYSTEM REPLACEMENT( SANDY) | 4 | CONSTRUCTION START | Mar 2013 | Feb 2014 | Mar 2013 | Feb 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC4 | 60TH PRECINCT ELECTRICAL SYSTEM REPLACEMENT( SANDY) | 5 | CONSTRUCTION COMPLETION | Mar 2014 | Oct 2014 | Mar 2014 | Jun 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC8 | ERIE BASIN TOW POUND ELECTRICAL (SANDY) | 1 | PROJECT START | Nov 2013 | Nov 2013 | Nov 2013 | Nov 2013
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC8 | ERIE BASIN TOW POUND ELECTRICAL (SANDY) | 2 | DESIGN START | Nov 2013 | Feb 2014 | Nov 2013 | Nov 2013
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC8 | ERIE BASIN TOW POUND ELECTRICAL (SANDY) | 3 | DESIGN COMPLETION | Mar 2014 | Jun 2014 | Nov 2017 | Mar 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC8 | ERIE BASIN TOW POUND ELECTRICAL (SANDY) | 4 | CONSTRUCTION START | Jun 2014 | Sep 2014 | Mar 2020 | May 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC8 | ERIE BASIN TOW POUND ELECTRICAL (SANDY) | 5 | CONSTRUCTION COMPLETION | Sep 2014 | Feb 2015 | May 2020 | Nov 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW19 | Reconstruction of Downtown Brooklyn - Hurricane Sandy | 1 | DEVELOP SCOPE | Feb 2016 | May 2016 | Feb 2016 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW19 | Reconstruction of Downtown Brooklyn - Hurricane Sandy | 2 | PRELIMINARY DESIGN | May 2016 | Sep 2016 | Jul 2018 | Dec 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW19 | Reconstruction of Downtown Brooklyn - Hurricane Sandy | 3 | FINAL DESIGN | Sep 2016 | Mar 2017 | Jan 2019 | Dec 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW19 | Reconstruction of Downtown Brooklyn - Hurricane Sandy | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2017 | Jun 2017 | Jan 2020 | Dec 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW19 | Reconstruction of Downtown Brooklyn - Hurricane Sandy | 5 | CONSTRUCTION TO 25% | Jun 2017 | Oct 2017 | Jan 2021 | Apr 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW19 | Reconstruction of Downtown Brooklyn - Hurricane Sandy | 6 | CONSTRUCTION TO 50% | Oct 2017 | Feb 2018 | May 2021 | Aug 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW19 | Reconstruction of Downtown Brooklyn - Hurricane Sandy | 7 | CONSTRUCTION TO 75% | Feb 2018 | Jun 2018 | Aug 2021 | Dec 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW19 | Reconstruction of Downtown Brooklyn - Hurricane Sandy | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2018 | Sep 2018 | Dec 2021 | Mar 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW19 | Reconstruction of Downtown Brooklyn - Hurricane Sandy | 9 | SUBSTANTIAL COMPLETION | Sep 2018 | Nov 2018 | Mar 2022 | May 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW19 | Reconstruction of Downtown Brooklyn - Hurricane Sandy | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2018 | Dec 2018 | May 2022 | Jun 2031
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR03 | Jamaica Bay Greenway - Canarsie Pier Connector | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR03 | Jamaica Bay Greenway - Canarsie Pier Connector | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR03 | Jamaica Bay Greenway - Canarsie Pier Connector | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR03 | Jamaica Bay Greenway - Canarsie Pier Connector | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR03 | Jamaica Bay Greenway - Canarsie Pier Connector | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR03 | Jamaica Bay Greenway - Canarsie Pier Connector | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR03 | Jamaica Bay Greenway - Canarsie Pier Connector | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR03 | Jamaica Bay Greenway - Canarsie Pier Connector | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR03 | Jamaica Bay Greenway - Canarsie Pier Connector | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR03 | Jamaica Bay Greenway - Canarsie Pier Connector | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Apr 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR03 | Jamaica Bay Greenway - Canarsie Pier Connector | 11 | PROJECT START | Mar 2022 | Apr 2022 | Apr 2023 | Apr 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR03 | Jamaica Bay Greenway - Canarsie Pier Connector | 12 | DESIGN START | Mar 2022 | Apr 2022 | Apr 2023 | Apr 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR03 | Jamaica Bay Greenway - Canarsie Pier Connector | 13 | DESIGN COMPLETION | Mar 2022 | Apr 2022 | Apr 2023 | Apr 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR03 | Jamaica Bay Greenway - Canarsie Pier Connector | 14 | CONSTRUCTION START | Mar 2022 | Apr 2022 | Apr 2023 | Apr 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR03 | Jamaica Bay Greenway - Canarsie Pier Connector | 15 | CONSTRUCTION COMPLETION | Mar 2022 | Apr 2022 | Apr 2023 | Jun 2033
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRDHK | Red Hook HMGP | 1 | DESIGN | Jul 2016 | Jul 2016 | Jul 2016 | Jul 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRDHK | Red Hook HMGP | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Jul 2016 | Aug 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRDHK | Red Hook HMGP | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Aug 2016 | Sep 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRDHK | Red Hook HMGP | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Sep 2016 | Sep 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRDHK | Red Hook HMGP | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Sep 2016 | Oct 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRDHK | Red Hook HMGP | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2016 | Oct 2016 | Jun 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-855 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2B | 1 | DEVELOP SCOPE | Mar 2016 | May 2016 | Mar 2016 | May 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-855 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2B | 2 | PRELIMINARY DESIGN | May 2016 | Sep 2016 | May 2016 | Sep 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-855 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2B | 3 | FINAL DESIGN | Sep 2016 | Mar 2017 | Sep 2016 | Mar 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-855 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2B | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2017 | Jun 2017 | Mar 2017 | Jun 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-855 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2B | 5 | CONSTRUCTION TO 25% | Jun 2017 | Oct 2017 | Jun 2017 | Oct 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-855 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2B | 6 | CONSTRUCTION TO 50% | Oct 2017 | Feb 2018 | Oct 2017 | Feb 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-855 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2B | 7 | CONSTRUCTION TO 75% | Feb 2018 | Jun 2018 | Feb 2018 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-855 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2B | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-855 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2B | 9 | SUBSTANTIAL COMPLETION | Sep 2018 | Nov 2018 | Sep 2018 | Nov 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-855 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2B | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2018 | Dec 2018 | Nov 2018 | Jun 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-855 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2B | 11 | PROJECT START | Nov 2018 | Dec 2018 | Jul 2024 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-855 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2B | 12 | DESIGN START | Nov 2018 | Dec 2018 | Jul 2024 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-855 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2B | 13 | DESIGN COMPLETION | Nov 2018 | Dec 2018 | Jul 2024 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-855 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2B | 14 | CONSTRUCTION START | Nov 2018 | Dec 2018 | Jul 2024 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-855 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2B | 15 | CONSTRUCTION COMPLETION | Nov 2018 | Dec 2018 | Jul 2024 | Jun 2029
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002351 | Rehab of SWR & WM in Wycoff Av bt Cooper &Flushing Av,HWK876 | 1 | DEVELOP SCOPE | Jun 2010 | Sep 2010 | Jun 2010 | Sep 2010
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002351 | Rehab of SWR & WM in Wycoff Av bt Cooper &Flushing Av,HWK876 | 2 | PRELIMINARY DESIGN | Sep 2010 | Jan 2011 | Sep 2010 | Jan 2011
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002351 | Rehab of SWR & WM in Wycoff Av bt Cooper &Flushing Av,HWK876 | 3 | FINAL DESIGN | Jan 2011 | Jul 2011 | Jan 2011 | Jul 2011
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002351 | Rehab of SWR & WM in Wycoff Av bt Cooper &Flushing Av,HWK876 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2011 | Oct 2011 | Mar 2022 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002351 | Rehab of SWR & WM in Wycoff Av bt Cooper &Flushing Av,HWK876 | 5 | CONSTRUCTION TO 25% | Oct 2011 | Feb 2012 | Jun 2022 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002351 | Rehab of SWR & WM in Wycoff Av bt Cooper &Flushing Av,HWK876 | 6 | CONSTRUCTION TO 50% | Feb 2012 | Jun 2012 | Jun 2022 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002351 | Rehab of SWR & WM in Wycoff Av bt Cooper &Flushing Av,HWK876 | 7 | CONSTRUCTION TO 75% | Jun 2012 | Oct 2012 | Jun 2022 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002351 | Rehab of SWR & WM in Wycoff Av bt Cooper &Flushing Av,HWK876 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2012 | Jan 2013 | Jun 2022 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002351 | Rehab of SWR & WM in Wycoff Av bt Cooper &Flushing Av,HWK876 | 9 | SUBSTANTIAL COMPLETION | Jan 2013 | Mar 2013 | Jun 2022 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002351 | Rehab of SWR & WM in Wycoff Av bt Cooper &Flushing Av,HWK876 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2013 | Apr 2013 | Jun 2024 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002376 | COMB SWR REPLCMNT & WM WORK IN PRESIDENT ST | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002376 | COMB SWR REPLCMNT & WM WORK IN PRESIDENT ST | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002376 | COMB SWR REPLCMNT & WM WORK IN PRESIDENT ST | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002376 | COMB SWR REPLCMNT & WM WORK IN PRESIDENT ST | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002376 | COMB SWR REPLCMNT & WM WORK IN PRESIDENT ST | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002376 | COMB SWR REPLCMNT & WM WORK IN PRESIDENT ST | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002376 | COMB SWR REPLCMNT & WM WORK IN PRESIDENT ST | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002376 | COMB SWR REPLCMNT & WM WORK IN PRESIDENT ST | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002376 | COMB SWR REPLCMNT & WM WORK IN PRESIDENT ST | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002376 | COMB SWR REPLCMNT & WM WORK IN PRESIDENT ST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Jun 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002377 | San sewer & WM repl 72nd St btwn Av L & Royce Pl, HWK002377 | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jun 2018 | Aug 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002377 | San sewer & WM repl 72nd St btwn Av L & Royce Pl, HWK002377 | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Aug 2018 | Dec 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002377 | San sewer & WM repl 72nd St btwn Av L & Royce Pl, HWK002377 | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Dec 2018 | Jun 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002377 | San sewer & WM repl 72nd St btwn Av L & Royce Pl, HWK002377 | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002377 | San sewer & WM repl 72nd St btwn Av L & Royce Pl, HWK002377 | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002377 | San sewer & WM repl 72nd St btwn Av L & Royce Pl, HWK002377 | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Jan 2020 | May 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002377 | San sewer & WM repl 72nd St btwn Av L & Royce Pl, HWK002377 | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | May 2020 | Sep 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002377 | San sewer & WM repl 72nd St btwn Av L & Royce Pl, HWK002377 | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Sep 2020 | Dec 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002377 | San sewer & WM repl 72nd St btwn Av L & Royce Pl, HWK002377 | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Dec 2020 | Feb 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002377 | San sewer & WM repl 72nd St btwn Av L & Royce Pl, HWK002377 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Feb 2021 | Jun 2033
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002383 | Combined SE installation & WM replacement in Dean Street | 1 | DEVELOP SCOPE | Aug 2018 | Nov 2018 | Aug 2018 | Nov 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002383 | Combined SE installation & WM replacement in Dean Street | 2 | PRELIMINARY DESIGN | Nov 2018 | Mar 2019 | Nov 2018 | Mar 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002383 | Combined SE installation & WM replacement in Dean Street | 3 | FINAL DESIGN | Mar 2019 | Sep 2019 | Mar 2019 | Sep 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002383 | Combined SE installation & WM replacement in Dean Street | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002383 | Combined SE installation & WM replacement in Dean Street | 5 | CONSTRUCTION TO 25% | Dec 2019 | Mar 2020 | Dec 2019 | Mar 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002383 | Combined SE installation & WM replacement in Dean Street | 6 | CONSTRUCTION TO 50% | Mar 2020 | Jul 2020 | Mar 2020 | Jul 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002383 | Combined SE installation & WM replacement in Dean Street | 7 | CONSTRUCTION TO 75% | Jul 2020 | Nov 2020 | Jul 2020 | Nov 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002383 | Combined SE installation & WM replacement in Dean Street | 8 | ORIGINAL EQUIP & FURNISHING | Nov 2020 | Feb 2021 | Nov 2020 | Feb 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002383 | Combined SE installation & WM replacement in Dean Street | 9 | SUBSTANTIAL COMPLETION | Feb 2021 | Apr 2021 | Feb 2021 | Apr 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002383 | Combined SE installation & WM replacement in Dean Street | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2021 | May 2021 | Apr 2021 | Jul 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002384 | Combined SE rplcmt & dist WM Van Sinderen Av BK NDF-IBZ | 1 | DEVELOP SCOPE | Dec 2019 | Mar 2020 | Dec 2019 | Mar 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002384 | Combined SE rplcmt & dist WM Van Sinderen Av BK NDF-IBZ | 2 | PRELIMINARY DESIGN | Mar 2020 | Jul 2020 | Mar 2020 | Jul 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002384 | Combined SE rplcmt & dist WM Van Sinderen Av BK NDF-IBZ | 3 | FINAL DESIGN | Jul 2020 | Jan 2021 | Jul 2020 | Jan 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002384 | Combined SE rplcmt & dist WM Van Sinderen Av BK NDF-IBZ | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2021 | Apr 2021 | Jan 2021 | Apr 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002384 | Combined SE rplcmt & dist WM Van Sinderen Av BK NDF-IBZ | 5 | CONSTRUCTION TO 25% | Apr 2021 | Jul 2021 | Apr 2021 | Jul 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002384 | Combined SE rplcmt & dist WM Van Sinderen Av BK NDF-IBZ | 6 | CONSTRUCTION TO 50% | Jul 2021 | Nov 2021 | Jul 2021 | Nov 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002384 | Combined SE rplcmt & dist WM Van Sinderen Av BK NDF-IBZ | 7 | CONSTRUCTION TO 75% | Nov 2021 | Mar 2022 | Nov 2021 | Mar 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002384 | Combined SE rplcmt & dist WM Van Sinderen Av BK NDF-IBZ | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2022 | Jun 2022 | Mar 2022 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002384 | Combined SE rplcmt & dist WM Van Sinderen Av BK NDF-IBZ | 9 | SUBSTANTIAL COMPLETION | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002384 | Combined SE rplcmt & dist WM Van Sinderen Av BK NDF-IBZ | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2022 | Sep 2022 | Aug 2022 | Sep 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002386 | Replace combined sewer & WM work,Park Pl & Underhill Ave, BK | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002386 | Replace combined sewer & WM work,Park Pl & Underhill Ave, BK | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002386 | Replace combined sewer & WM work,Park Pl & Underhill Ave, BK | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002386 | Replace combined sewer & WM work,Park Pl & Underhill Ave, BK | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002386 | Replace combined sewer & WM work,Park Pl & Underhill Ave, BK | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002386 | Replace combined sewer & WM work,Park Pl & Underhill Ave, BK | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002386 | Replace combined sewer & WM work,Park Pl & Underhill Ave, BK | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002386 | Replace combined sewer & WM work,Park Pl & Underhill Ave, BK | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002386 | Replace combined sewer & WM work,Park Pl & Underhill Ave, BK | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002386 | Replace combined sewer & WM work,Park Pl & Underhill Ave, BK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Jun 2027
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002390 | Guniting of Outfall Sewers on Wolcott St BKLYN, SANDRDHK | 1 | DEVELOP SCOPE | Dec 2022 | Mar 2023 | Jan 2022 | Mar 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002390 | Guniting of Outfall Sewers on Wolcott St BKLYN, SANDRDHK | 2 | PRELIMINARY DESIGN | Mar 2023 | Jul 2023 | Apr 2022 | Jul 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002390 | Guniting of Outfall Sewers on Wolcott St BKLYN, SANDRDHK | 3 | FINAL DESIGN | Jul 2023 | Jan 2024 | Jul 2022 | Jan 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002390 | Guniting of Outfall Sewers on Wolcott St BKLYN, SANDRDHK | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2024 | Apr 2024 | Jan 2023 | Apr 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002390 | Guniting of Outfall Sewers on Wolcott St BKLYN, SANDRDHK | 5 | CONSTRUCTION TO 25% | Apr 2024 | Jul 2024 | Apr 2023 | Aug 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002390 | Guniting of Outfall Sewers on Wolcott St BKLYN, SANDRDHK | 6 | CONSTRUCTION TO 50% | Jul 2024 | Nov 2024 | Aug 2023 | Dec 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002390 | Guniting of Outfall Sewers on Wolcott St BKLYN, SANDRDHK | 7 | CONSTRUCTION TO 75% | Nov 2024 | Mar 2025 | Dec 2023 | Apr 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002390 | Guniting of Outfall Sewers on Wolcott St BKLYN, SANDRDHK | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2025 | Jun 2025 | Apr 2024 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002390 | Guniting of Outfall Sewers on Wolcott St BKLYN, SANDRDHK | 9 | SUBSTANTIAL COMPLETION | Jun 2025 | Aug 2025 | Jul 2024 | Sep 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002390 | Guniting of Outfall Sewers on Wolcott St BKLYN, SANDRDHK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2025 | Sep 2025 | Sep 2024 | Oct 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20056 | STORM SEWERS-GATEWAY ESTATES - PHASE C (HD-161C) | 1 | DEVELOP SCOPE | Mar 2006 | Jun 2006 | Mar 2006 | Jun 2006
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20056 | STORM SEWERS-GATEWAY ESTATES - PHASE C (HD-161C) | 2 | PRELIMINARY DESIGN | Jun 2006 | Oct 2006 | Jun 2006 | Oct 2006
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20056 | STORM SEWERS-GATEWAY ESTATES - PHASE C (HD-161C) | 3 | FINAL DESIGN | Oct 2006 | Apr 2007 | Oct 2006 | Apr 2007
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20056 | STORM SEWERS-GATEWAY ESTATES - PHASE C (HD-161C) | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2007 | Jul 2007 | Mar 2012 | Jun 2012
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20056 | STORM SEWERS-GATEWAY ESTATES - PHASE C (HD-161C) | 5 | CONSTRUCTION TO 25% | Jul 2007 | Nov 2007 | Jun 2012 | Jun 2012
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20056 | STORM SEWERS-GATEWAY ESTATES - PHASE C (HD-161C) | 6 | CONSTRUCTION TO 50% | Nov 2007 | Mar 2008 | Jun 2012 | Jun 2012
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20056 | STORM SEWERS-GATEWAY ESTATES - PHASE C (HD-161C) | 7 | CONSTRUCTION TO 75% | Mar 2008 | Jul 2008 | Jun 2012 | Jun 2012
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20056 | STORM SEWERS-GATEWAY ESTATES - PHASE C (HD-161C) | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2008 | Sep 2008 | Jun 2012 | Jun 2012
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20056 | STORM SEWERS-GATEWAY ESTATES - PHASE C (HD-161C) | 9 | SUBSTANTIAL COMPLETION | Sep 2008 | Nov 2008 | Jun 2012 | Jun 2012
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20056 | STORM SEWERS-GATEWAY ESTATES - PHASE C (HD-161C) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2008 | Dec 2008 | Jun 2012 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20056 | STORM SEWERS-GATEWAY ESTATES - PHASE C (HD-161C) | 11 | PROJECT START | Nov 2008 | Dec 2008 | Jul 2022 | Jul 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20056 | STORM SEWERS-GATEWAY ESTATES - PHASE C (HD-161C) | 12 | DESIGN START | Nov 2008 | Dec 2008 | Jul 2022 | Jul 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20056 | STORM SEWERS-GATEWAY ESTATES - PHASE C (HD-161C) | 13 | DESIGN COMPLETION | Nov 2008 | Dec 2008 | Jul 2022 | Jul 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20056 | STORM SEWERS-GATEWAY ESTATES - PHASE C (HD-161C) | 14 | CONSTRUCTION START | Nov 2008 | Dec 2008 | Jul 2022 | Jul 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20056 | STORM SEWERS-GATEWAY ESTATES - PHASE C (HD-161C) | 15 | CONSTRUCTION COMPLETION | Nov 2008 | Dec 2008 | Jul 2022 | Jun 2031
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20067 | High level storm sewer Gowanus Canal Area. Phase 2. | 1 | DEVELOP SCOPE | Mar 2019 | Jun 2019 | Feb 2015 | May 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20067 | High level storm sewer Gowanus Canal Area. Phase 2. | 2 | PRELIMINARY DESIGN | Jun 2019 | Sep 2019 | May 2017 | Sep 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20067 | High level storm sewer Gowanus Canal Area. Phase 2. | 3 | FINAL DESIGN | Oct 2019 | Mar 2020 | Sep 2017 | Mar 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20067 | High level storm sewer Gowanus Canal Area. Phase 2. | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Jun 2020 | Mar 2018 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20067 | High level storm sewer Gowanus Canal Area. Phase 2. | 5 | CONSTRUCTION TO 25% | Jun 2020 | Oct 2020 | Jun 2018 | Sep 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20067 | High level storm sewer Gowanus Canal Area. Phase 2. | 6 | CONSTRUCTION TO 50% | Oct 2020 | Feb 2021 | Sep 2018 | Jan 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20067 | High level storm sewer Gowanus Canal Area. Phase 2. | 7 | CONSTRUCTION TO 75% | Feb 2021 | Jun 2021 | Jan 2019 | Jun 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20067 | High level storm sewer Gowanus Canal Area. Phase 2. | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2021 | Sep 2021 | Jun 2020 | Sep 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20067 | High level storm sewer Gowanus Canal Area. Phase 2. | 9 | SUBSTANTIAL COMPLETION | Sep 2021 | Nov 2021 | Sep 2020 | Nov 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20067 | High level storm sewer Gowanus Canal Area. Phase 2. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2021 | Dec 2021 | Nov 2020 | Sep 2029
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20069 | Storm Sewer install & WM replace Gerritsen Beach, HWK2013GB | 1 | DEVELOP SCOPE | Jun 2013 | Mar 2014 | Jun 2013 | Mar 2014
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20069 | Storm Sewer install & WM replace Gerritsen Beach, HWK2013GB | 2 | PRELIMINARY DESIGN | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2015
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20069 | Storm Sewer install & WM replace Gerritsen Beach, HWK2013GB | 3 | FINAL DESIGN | Mar 2015 | Sep 2016 | Mar 2015 | Sep 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20069 | Storm Sewer install & WM replace Gerritsen Beach, HWK2013GB | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2016 | Jun 2017 | Sep 2016 | Jun 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20069 | Storm Sewer install & WM replace Gerritsen Beach, HWK2013GB | 5 | CONSTRUCTION TO 25% | Jun 2017 | Jun 2018 | Jun 2017 | Jun 2018
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20069 | Storm Sewer install & WM replace Gerritsen Beach, HWK2013GB | 6 | CONSTRUCTION TO 50% | Jun 2018 | May 2019 | Jun 2018 | May 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20069 | Storm Sewer install & WM replace Gerritsen Beach, HWK2013GB | 7 | CONSTRUCTION TO 75% | May 2019 | May 2020 | May 2019 | May 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20069 | Storm Sewer install & WM replace Gerritsen Beach, HWK2013GB | 8 | ORIGINAL EQUIP & FURNISHING | May 2020 | Feb 2021 | May 2020 | Feb 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20069 | Storm Sewer install & WM replace Gerritsen Beach, HWK2013GB | 9 | SUBSTANTIAL COMPLETION | Feb 2021 | Aug 2021 | Feb 2021 | Aug 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20069 | Storm Sewer install & WM replace Gerritsen Beach, HWK2013GB | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Nov 2021 | Aug 2021 | Nov 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20076 | Replace deficient combined sewers and WM in East 80 St | 1 | DEVELOP SCOPE | Dec 2019 | Mar 2020 | Dec 2019 | Mar 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20076 | Replace deficient combined sewers and WM in East 80 St | 2 | PRELIMINARY DESIGN | Mar 2020 | Jul 2020 | Mar 2020 | Jul 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20076 | Replace deficient combined sewers and WM in East 80 St | 3 | FINAL DESIGN | Jul 2020 | Jan 2021 | Jul 2020 | Jan 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20076 | Replace deficient combined sewers and WM in East 80 St | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2021 | Apr 2021 | Jan 2021 | Apr 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20076 | Replace deficient combined sewers and WM in East 80 St | 5 | CONSTRUCTION TO 25% | Apr 2021 | Jul 2021 | Apr 2021 | Jul 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20076 | Replace deficient combined sewers and WM in East 80 St | 6 | CONSTRUCTION TO 50% | Jul 2021 | Nov 2021 | Jul 2021 | Nov 2021
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20076 | Replace deficient combined sewers and WM in East 80 St | 7 | CONSTRUCTION TO 75% | Nov 2021 | Mar 2022 | Nov 2021 | Mar 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20076 | Replace deficient combined sewers and WM in East 80 St | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2022 | Jun 2022 | Mar 2022 | Jun 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20076 | Replace deficient combined sewers and WM in East 80 St | 9 | SUBSTANTIAL COMPLETION | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20076 | Replace deficient combined sewers and WM in East 80 St | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2022 | Sep 2022 | Aug 2022 | Sep 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKBN9 | Reconstruction of Existing Sewers, North Brooklyn | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2019 | Aug 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKBN9 | Reconstruction of Existing Sewers, North Brooklyn | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKBN9 | Reconstruction of Existing Sewers, North Brooklyn | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKBN9 | Reconstruction of Existing Sewers, North Brooklyn | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKBN9 | Reconstruction of Existing Sewers, North Brooklyn | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKBN9 | Reconstruction of Existing Sewers, North Brooklyn | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKBN9 | Reconstruction of Existing Sewers, North Brooklyn | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | May 2024 | Sep 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKBN9 | Reconstruction of Existing Sewers, North Brooklyn | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKBN9 | Reconstruction of Existing Sewers, North Brooklyn | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Dec 2024 | Feb 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKBN9 | Reconstruction of Existing Sewers, North Brooklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Mar 2025 | Feb 2025 | Dec 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKDSMH23 | Reconstruction and repair of deep sewer manholes, Bklyn | 1 | DEVELOP SCOPE | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKDSMH23 | Reconstruction and repair of deep sewer manholes, Bklyn | 2 | PRELIMINARY DESIGN | Mar 2024 | Jul 2024 | Mar 2024 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKDSMH23 | Reconstruction and repair of deep sewer manholes, Bklyn | 3 | FINAL DESIGN | Jul 2024 | Jan 2025 | Jul 2024 | Jan 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKDSMH23 | Reconstruction and repair of deep sewer manholes, Bklyn | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2025 | Apr 2025 | Jan 2025 | Apr 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKDSMH23 | Reconstruction and repair of deep sewer manholes, Bklyn | 5 | CONSTRUCTION TO 25% | Apr 2025 | Aug 2025 | Apr 2025 | Aug 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKDSMH23 | Reconstruction and repair of deep sewer manholes, Bklyn | 6 | CONSTRUCTION TO 50% | Aug 2025 | Dec 2025 | Aug 2025 | Dec 2025
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKDSMH23 | Reconstruction and repair of deep sewer manholes, Bklyn | 7 | CONSTRUCTION TO 75% | Dec 2025 | Apr 2026 | Dec 2025 | Apr 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKDSMH23 | Reconstruction and repair of deep sewer manholes, Bklyn | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2026 | Jul 2026 | Apr 2026 | Jul 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKDSMH23 | Reconstruction and repair of deep sewer manholes, Bklyn | 9 | SUBSTANTIAL COMPLETION | Jul 2026 | Sep 2026 | Jul 2026 | Sep 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKDSMH23 | Reconstruction and repair of deep sewer manholes, Bklyn | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Oct 2026 | Sep 2026 | Oct 2026
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARDOS1 | Brooklyn 17/18 HVAC AND ROOF REPLACEMENT | 1 | PROJECT START | Mar 2018 | Mar 2018 | Sep 2016 | Sep 2016
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARDOS1 | Brooklyn 17/18 HVAC AND ROOF REPLACEMENT | 2 | DESIGN START | Mar 2018 | Mar 2018 | Sep 2016 | May 2017
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARDOS1 | Brooklyn 17/18 HVAC AND ROOF REPLACEMENT | 3 | DESIGN COMPLETION | Mar 2018 | Mar 2018 | May 2017 | Jun 2019
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARDOS1 | Brooklyn 17/18 HVAC AND ROOF REPLACEMENT | 4 | CONSTRUCTION START | Mar 2018 | Mar 2018 | Jun 2019 | Feb 2020
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARDOS1 | Brooklyn 17/18 HVAC AND ROOF REPLACEMENT | 5 | CONSTRUCTION COMPLETION | Mar 2018 | Mar 2018 | Feb 2020 | Dec 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | WTM4SPRW | Perform Wetland Mitigation work in Four Sparrow Marsh, BKLYN | 1 | PROJECT START | Nov 2022 | Nov 2022 | Nov 2022 | Nov 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | WTM4SPRW | Perform Wetland Mitigation work in Four Sparrow Marsh, BKLYN | 2 | DESIGN START | Nov 2022 | Dec 2022 | Nov 2022 | Dec 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | WTM4SPRW | Perform Wetland Mitigation work in Four Sparrow Marsh, BKLYN | 3 | DESIGN COMPLETION | Dec 2022 | Dec 2022 | Dec 2022 | Dec 2022
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | WTM4SPRW | Perform Wetland Mitigation work in Four Sparrow Marsh, BKLYN | 4 | CONSTRUCTION START | Jul 2023 | Jul 2024 | Jul 2023 | Jul 2024
20231026 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | WTM4SPRW | Perform Wetland Mitigation work in Four Sparrow Marsh, BKLYN | 5 | CONSTRUCTION COMPLETION | Aug 2024 | Aug 2024 | Aug 2024 | Aug 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA241 | BBG Conservatory Boiler Renovation | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA241 | BBG Conservatory Boiler Renovation | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA241 | BBG Conservatory Boiler Renovation | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA241 | BBG Conservatory Boiler Renovation | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA241 | BBG Conservatory Boiler Renovation | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA241 | BBG Conservatory Boiler Renovation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP212 | DEP - Variable Frequency Drives on Owl's Head WRRF Pumps | 1 | DEVELOP SCOPE | Jun 2027 | Jun 2027 | Jun 2027 | Jun 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP212 | DEP - Variable Frequency Drives on Owl's Head WRRF Pumps | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2027 | Aug 2027 | Jul 2027 | Aug 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP212 | DEP - Variable Frequency Drives on Owl's Head WRRF Pumps | 3 | CONSTRUCTION TO 50% | Aug 2027 | Feb 2028 | Aug 2027 | Feb 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP212 | DEP - Variable Frequency Drives on Owl's Head WRRF Pumps | 4 | CONSTRUCTION TO 75% | Feb 2028 | May 2028 | Feb 2028 | May 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP212 | DEP - Variable Frequency Drives on Owl's Head WRRF Pumps | 5 | SUBSTANTIAL COMPLETION | May 2028 | Jul 2028 | May 2028 | Jul 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP212 | DEP - Variable Frequency Drives on Owl's Head WRRF Pumps | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2028 | Aug 2028 | Jul 2028 | Aug 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP213 | DEP - Membrane Style Gasholder at Newtown Creek WRRF | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP213 | DEP - Membrane Style Gasholder at Newtown Creek WRRF | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP213 | DEP - Membrane Style Gasholder at Newtown Creek WRRF | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP213 | DEP - Membrane Style Gasholder at Newtown Creek WRRF | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP213 | DEP - Membrane Style Gasholder at Newtown Creek WRRF | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP213 | DEP - Membrane Style Gasholder at Newtown Creek WRRF | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP231 | Aeration Upgrades at Owls Head WRRF | 1 | DEVELOP SCOPE | Jun 2026 | Jun 2026 | Jun 2026 | Jun 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP231 | Aeration Upgrades at Owls Head WRRF | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2026 | Aug 2026 | Jul 2026 | Aug 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP231 | Aeration Upgrades at Owls Head WRRF | 3 | CONSTRUCTION TO 50% | Aug 2026 | Feb 2027 | Aug 2026 | Feb 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP231 | Aeration Upgrades at Owls Head WRRF | 4 | CONSTRUCTION TO 75% | Feb 2027 | May 2027 | Feb 2027 | May 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP231 | Aeration Upgrades at Owls Head WRRF | 5 | SUBSTANTIAL COMPLETION | May 2027 | Jul 2027 | May 2027 | Jul 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP231 | Aeration Upgrades at Owls Head WRRF | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2027 | Aug 2027 | Jul 2027 | Aug 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP901 | DEP - Gravity Belt Thickener (GBT) at Newtown Creek WRRF | 1 | DEVELOP SCOPE | Apr 2020 | May 2020 | Jun 2021 | Jun 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP901 | DEP - Gravity Belt Thickener (GBT) at Newtown Creek WRRF | 2 | BID AWARD AND REGISTER CONTRCT | May 2020 | Jul 2020 | Jul 2023 | Aug 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP901 | DEP - Gravity Belt Thickener (GBT) at Newtown Creek WRRF | 3 | CONSTRUCTION TO 50% | Jul 2020 | Jan 2021 | Aug 2023 | Feb 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP901 | DEP - Gravity Belt Thickener (GBT) at Newtown Creek WRRF | 4 | CONSTRUCTION TO 75% | Jan 2021 | Apr 2021 | Feb 2024 | May 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP901 | DEP - Gravity Belt Thickener (GBT) at Newtown Creek WRRF | 5 | SUBSTANTIAL COMPLETION | Apr 2021 | Jun 2021 | May 2024 | Jul 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP901 | DEP - Gravity Belt Thickener (GBT) at Newtown Creek WRRF | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2021 | Jul 2021 | Jul 2024 | Aug 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE213 | DOE - K007 - Lighting, HVAC, and BMS upgrade | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE213 | DOE - K007 - Lighting, HVAC, and BMS upgrade | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE213 | DOE - K007 - Lighting, HVAC, and BMS upgrade | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE213 | DOE - K007 - Lighting, HVAC, and BMS upgrade | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE213 | DOE - K007 - Lighting, HVAC, and BMS upgrade | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE213 | DOE - K007 - Lighting, HVAC, and BMS upgrade | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE214 | DOE - K066 EER ECMs | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE214 | DOE - K066 EER ECMs | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE214 | DOE - K066 EER ECMs | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE214 | DOE - K066 EER ECMs | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE214 | DOE - K066 EER ECMs | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE214 | DOE - K066 EER ECMs | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEHRA211 | HRA - BEDFORD STUYVESANT COMPREHENSIVE UPGRADES | 1 | DEVELOP SCOPE | Jun 2027 | Jun 2027 | Jun 2027 | Jun 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEHRA211 | HRA - BEDFORD STUYVESANT COMPREHENSIVE UPGRADES | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2027 | Aug 2027 | Jul 2027 | Aug 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEHRA211 | HRA - BEDFORD STUYVESANT COMPREHENSIVE UPGRADES | 3 | CONSTRUCTION TO 50% | Aug 2027 | Feb 2028 | Aug 2027 | Feb 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEHRA211 | HRA - BEDFORD STUYVESANT COMPREHENSIVE UPGRADES | 4 | CONSTRUCTION TO 75% | Feb 2028 | May 2028 | Feb 2028 | May 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEHRA211 | HRA - BEDFORD STUYVESANT COMPREHENSIVE UPGRADES | 5 | SUBSTANTIAL COMPLETION | May 2028 | Jul 2028 | May 2028 | Jul 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEHRA211 | HRA - BEDFORD STUYVESANT COMPREHENSIVE UPGRADES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2028 | Aug 2028 | Jul 2028 | Aug 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGTIMEPLZ | RAICES TIMES PLAZA SENIOR CENER UPGRADE | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGTIMEPLZ | RAICES TIMES PLAZA SENIOR CENER UPGRADE | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGTIMEPLZ | RAICES TIMES PLAZA SENIOR CENER UPGRADE | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGTIMEPLZ | RAICES TIMES PLAZA SENIOR CENER UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGTIMEPLZ | RAICES TIMES PLAZA SENIOR CENER UPGRADE | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGTIMEPLZ | RAICES TIMES PLAZA SENIOR CENER UPGRADE | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGTIMEPLZ | RAICES TIMES PLAZA SENIOR CENER UPGRADE | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGTIMEPLZ | RAICES TIMES PLAZA SENIOR CENER UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGTIMEPLZ | RAICES TIMES PLAZA SENIOR CENER UPGRADE | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGTIMEPLZ | RAICES TIMES PLAZA SENIOR CENER UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | APIDCAS02 | BROOKLYN APPELLATE COURT COMPREHENSIVE ELECTRIFICATION | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | APIDCAS02 | BROOKLYN APPELLATE COURT COMPREHENSIVE ELECTRIFICATION | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | APIDCAS02 | BROOKLYN APPELLATE COURT COMPREHENSIVE ELECTRIFICATION | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | APIDCAS02 | BROOKLYN APPELLATE COURT COMPREHENSIVE ELECTRIFICATION | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | APIDCAS02 | BROOKLYN APPELLATE COURT COMPREHENSIVE ELECTRIFICATION | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | APIDCAS02 | BROOKLYN APPELLATE COURT COMPREHENSIVE ELECTRIFICATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2026 | Jul 2025 | Aug 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | BKLYNMTC | Consolidation of four Bklyn DCP offices into one at 12 MTC | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | BKLYNMTC | Consolidation of four Bklyn DCP offices into one at 12 MTC | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | BKLYNMTC | Consolidation of four Bklyn DCP offices into one at 12 MTC | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | BKLYNMTC | Consolidation of four Bklyn DCP offices into one at 12 MTC | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2022 | May 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | BKLYNMTC | Consolidation of four Bklyn DCP offices into one at 12 MTC | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2022 | Sep 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | BKLYNMTC | Consolidation of four Bklyn DCP offices into one at 12 MTC | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | BKLYNMTC | Consolidation of four Bklyn DCP offices into one at 12 MTC | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2022 | Feb 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | BKLYNMTC | Consolidation of four Bklyn DCP offices into one at 12 MTC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264BKCV | 210 JORALEMON ST. OCA RELOCATION | 1 | DEVELOP SCOPE | Aug 2016 | Nov 2016 | Aug 2019 | Nov 2019
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264BKCV | 210 JORALEMON ST. OCA RELOCATION | 2 | PRELIMINARY DESIGN | Nov 2016 | Mar 2017 | Nov 2019 | Mar 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264BKCV | 210 JORALEMON ST. OCA RELOCATION | 3 | FINAL DESIGN | Mar 2017 | Sep 2017 | Mar 2020 | Sep 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264BKCV | 210 JORALEMON ST. OCA RELOCATION | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2017 | Dec 2017 | Sep 2020 | Dec 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264BKCV | 210 JORALEMON ST. OCA RELOCATION | 5 | CONSTRUCTION TO 25% | Dec 2017 | Apr 2018 | Dec 2020 | Apr 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264BKCV | 210 JORALEMON ST. OCA RELOCATION | 6 | CONSTRUCTION TO 50% | Apr 2018 | Aug 2018 | Apr 2021 | Aug 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264BKCV | 210 JORALEMON ST. OCA RELOCATION | 7 | CONSTRUCTION TO 75% | Aug 2018 | Dec 2018 | Jun 2027 | Sep 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264BKCV | 210 JORALEMON ST. OCA RELOCATION | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2018 | Mar 2019 | Sep 2027 | Sep 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264BKCV | 210 JORALEMON ST. OCA RELOCATION | 9 | SUBSTANTIAL COMPLETION | Mar 2019 | May 2019 | Sep 2028 | Nov 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264BKCV | 210 JORALEMON ST. OCA RELOCATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2019 | May 2023 | Nov 2028 | Feb 2032
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272BLR | 45 MONROE PL - BOILER PLANT UPGRADE | 1 | DEVELOP SCOPE | Jun 2021 | Aug 2021 | Jun 2021 | Aug 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272BLR | 45 MONROE PL - BOILER PLANT UPGRADE | 2 | PRELIMINARY DESIGN | Aug 2021 | Dec 2021 | Aug 2021 | Dec 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272BLR | 45 MONROE PL - BOILER PLANT UPGRADE | 3 | FINAL DESIGN | Dec 2021 | Jun 2022 | Dec 2021 | Jun 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272BLR | 45 MONROE PL - BOILER PLANT UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272BLR | 45 MONROE PL - BOILER PLANT UPGRADE | 5 | CONSTRUCTION TO 25% | Jun 2024 | Oct 2025 | Jun 2024 | Oct 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272BLR | 45 MONROE PL - BOILER PLANT UPGRADE | 6 | CONSTRUCTION TO 50% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272BLR | 45 MONROE PL - BOILER PLANT UPGRADE | 7 | CONSTRUCTION TO 75% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272BLR | 45 MONROE PL - BOILER PLANT UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2026 | Sep 2026 | Jun 2026 | Sep 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272BLR | 45 MONROE PL - BOILER PLANT UPGRADE | 9 | SUBSTANTIAL COMPLETION | Sep 2026 | Nov 2026 | Sep 2026 | Nov 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272BLR | 45 MONROE PL - BOILER PLANT UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Dec 2026 | Nov 2026 | Dec 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ADA1 | 360 ADAMS ST - ADA IMPROVEMENTS | 1 | DEVELOP SCOPE | Jun 2021 | Aug 2021 | Jun 2021 | Aug 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ADA1 | 360 ADAMS ST - ADA IMPROVEMENTS | 2 | PRELIMINARY DESIGN | Aug 2021 | Dec 2021 | Aug 2021 | Dec 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ADA1 | 360 ADAMS ST - ADA IMPROVEMENTS | 3 | FINAL DESIGN | Dec 2021 | Jun 2022 | Dec 2021 | Jun 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ADA1 | 360 ADAMS ST - ADA IMPROVEMENTS | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ADA1 | 360 ADAMS ST - ADA IMPROVEMENTS | 5 | CONSTRUCTION TO 25% | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ADA1 | 360 ADAMS ST - ADA IMPROVEMENTS | 6 | CONSTRUCTION TO 50% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ADA1 | 360 ADAMS ST - ADA IMPROVEMENTS | 7 | CONSTRUCTION TO 75% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ADA1 | 360 ADAMS ST - ADA IMPROVEMENTS | 8 | ORIGINAL EQUIP & FURNISHING | May 2025 | Aug 2025 | May 2025 | Aug 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ADA1 | 360 ADAMS ST - ADA IMPROVEMENTS | 9 | SUBSTANTIAL COMPLETION | Aug 2025 | Oct 2025 | Aug 2025 | Oct 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ADA1 | 360 ADAMS ST - ADA IMPROVEMENTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2025 | Nov 2025 | Oct 2025 | Nov 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ELV | 360 ADAMS ST.- ELEVATORS MODERNIZATION | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ELV | 360 ADAMS ST.- ELEVATORS MODERNIZATION | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ELV | 360 ADAMS ST.- ELEVATORS MODERNIZATION | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ELV | 360 ADAMS ST.- ELEVATORS MODERNIZATION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ELV | 360 ADAMS ST.- ELEVATORS MODERNIZATION | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ELV | 360 ADAMS ST.- ELEVATORS MODERNIZATION | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ELV | 360 ADAMS ST.- ELEVATORS MODERNIZATION | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | May 2024 | Sep 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ELV | 360 ADAMS ST.- ELEVATORS MODERNIZATION | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ELV | 360 ADAMS ST.- ELEVATORS MODERNIZATION | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Dec 2024 | Feb 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ELV | 360 ADAMS ST.- ELEVATORS MODERNIZATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Jun 2026 | Feb 2025 | Jun 2029
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278TOIL | 360 ADAMS ST. - CODE COMPLIANT TOILET UPGRADE | 1 | DEVELOP SCOPE | Jan 2016 | Mar 2016 | Jun 2027 | Aug 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278TOIL | 360 ADAMS ST. - CODE COMPLIANT TOILET UPGRADE | 2 | PRELIMINARY DESIGN | Mar 2016 | Jul 2016 | Aug 2027 | Dec 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278TOIL | 360 ADAMS ST. - CODE COMPLIANT TOILET UPGRADE | 3 | FINAL DESIGN | Jul 2016 | Jan 2017 | Dec 2027 | Jun 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278TOIL | 360 ADAMS ST. - CODE COMPLIANT TOILET UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2017 | Apr 2017 | Jun 2028 | Sep 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278TOIL | 360 ADAMS ST. - CODE COMPLIANT TOILET UPGRADE | 5 | CONSTRUCTION TO 25% | Apr 2017 | Aug 2017 | Sep 2028 | Jan 2029
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278TOIL | 360 ADAMS ST. - CODE COMPLIANT TOILET UPGRADE | 6 | CONSTRUCTION TO 50% | Aug 2017 | Dec 2017 | Jan 2029 | May 2029
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278TOIL | 360 ADAMS ST. - CODE COMPLIANT TOILET UPGRADE | 7 | CONSTRUCTION TO 75% | Dec 2017 | Apr 2018 | May 2029 | Sep 2029
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278TOIL | 360 ADAMS ST. - CODE COMPLIANT TOILET UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2018 | Jul 2018 | Sep 2029 | Dec 2029
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278TOIL | 360 ADAMS ST. - CODE COMPLIANT TOILET UPGRADE | 9 | SUBSTANTIAL COMPLETION | Jul 2018 | Sep 2018 | Dec 2029 | Feb 2030
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278TOIL | 360 ADAMS ST. - CODE COMPLIANT TOILET UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2018 | Oct 2018 | Feb 2030 | Mar 2032
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO281ADA | 120 SCHERMERHORN ST- ADA LIFT REPLACEMENT | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO281ADA | 120 SCHERMERHORN ST- ADA LIFT REPLACEMENT | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO281ADA | 120 SCHERMERHORN ST- ADA LIFT REPLACEMENT | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO281ADA | 120 SCHERMERHORN ST- ADA LIFT REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO281ADA | 120 SCHERMERHORN ST- ADA LIFT REPLACEMENT | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO281ADA | 120 SCHERMERHORN ST- ADA LIFT REPLACEMENT | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO281ADA | 120 SCHERMERHORN ST- ADA LIFT REPLACEMENT | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO281ADA | 120 SCHERMERHORN ST- ADA LIFT REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO281ADA | 120 SCHERMERHORN ST- ADA LIFT REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO281ADA | 120 SCHERMERHORN ST- ADA LIFT REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | DOEK004 | Solar photovoltaic system | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | DOEK004 | Solar photovoltaic system | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | DOEK004 | Solar photovoltaic system | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | DOEK004 | Solar photovoltaic system | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | DOEK004 | Solar photovoltaic system | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | DOEK004 | Solar photovoltaic system | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0002 | DOHMH - Brownsville Health Center | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jun 2019 | Aug 2019
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0002 | DOHMH - Brownsville Health Center | 3 | CONSTRUCTION TO 50% | Aug 2019 | Feb 2020 | Aug 2019 | Feb 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0002 | DOHMH - Brownsville Health Center | 4 | CONSTRUCTION TO 75% | Feb 2020 | May 2020 | Jun 2025 | Aug 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0002 | DOHMH - Brownsville Health Center | 5 | SUBSTANTIAL COMPLETION | May 2020 | Jul 2020 | Aug 2025 | Oct 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0002 | DOHMH - Brownsville Health Center | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Aug 2020 | Oct 2025 | Nov 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0008 | NYPD - Brooklyn North Boro Command | 1 | DEVELOP SCOPE | Jun 2019 | Jun 2019 | Jun 2019 | Jun 2019
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0008 | NYPD - Brooklyn North Boro Command | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jul 2019 | Aug 2019
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0008 | NYPD - Brooklyn North Boro Command | 3 | CONSTRUCTION TO 50% | Aug 2019 | Feb 2020 | Aug 2019 | Feb 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0008 | NYPD - Brooklyn North Boro Command | 4 | CONSTRUCTION TO 75% | Feb 2020 | May 2020 | Feb 2020 | May 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0008 | NYPD - Brooklyn North Boro Command | 5 | SUBSTANTIAL COMPLETION | May 2020 | Jul 2020 | May 2020 | Jul 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0008 | NYPD - Brooklyn North Boro Command | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Aug 2020 | Jul 2020 | Aug 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0008 | OCME Brooklyn Chief Medical Examiner Office | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2022 | Jun 2022 | Jun 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0008 | OCME Brooklyn Chief Medical Examiner Office | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Aug 2022 | Jul 2022 | Aug 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0008 | OCME Brooklyn Chief Medical Examiner Office | 3 | CONSTRUCTION TO 50% | Aug 2022 | Feb 2023 | Aug 2022 | Feb 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0008 | OCME Brooklyn Chief Medical Examiner Office | 4 | CONSTRUCTION TO 75% | Feb 2023 | May 2023 | Feb 2023 | May 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0008 | OCME Brooklyn Chief Medical Examiner Office | 5 | SUBSTANTIAL COMPLETION | May 2023 | Jul 2023 | May 2023 | Jul 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0008 | OCME Brooklyn Chief Medical Examiner Office | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2023 | Jun 2024 | Jul 2023 | Jun 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E22-0001 | DOE - DIRECT INSTALL LIGHTING PROGRAM - 605 SHEPHERD AVE, BK | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E22-0001 | DOE - DIRECT INSTALL LIGHTING PROGRAM - 605 SHEPHERD AVE, BK | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E22-0001 | DOE - DIRECT INSTALL LIGHTING PROGRAM - 605 SHEPHERD AVE, BK | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E22-0001 | DOE - DIRECT INSTALL LIGHTING PROGRAM - 605 SHEPHERD AVE, BK | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E22-0001 | DOE - DIRECT INSTALL LIGHTING PROGRAM - 605 SHEPHERD AVE, BK | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E22-0001 | DOE - DIRECT INSTALL LIGHTING PROGRAM - 605 SHEPHERD AVE, BK | 6 | CONSTRUCTION TO 50% | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E22-0001 | DOE - DIRECT INSTALL LIGHTING PROGRAM - 605 SHEPHERD AVE, BK | 7 | CONSTRUCTION TO 75% | Jun 2026 | Sep 2026 | Jun 2026 | Sep 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E22-0001 | DOE - DIRECT INSTALL LIGHTING PROGRAM - 605 SHEPHERD AVE, BK | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2026 | Dec 2026 | Sep 2026 | Dec 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E22-0001 | DOE - DIRECT INSTALL LIGHTING PROGRAM - 605 SHEPHERD AVE, BK | 9 | SUBSTANTIAL COMPLETION | Dec 2026 | Feb 2027 | Dec 2026 | Feb 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E22-0001 | DOE - DIRECT INSTALL LIGHTING PROGRAM - 605 SHEPHERD AVE, BK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2027 | Mar 2027 | Feb 2027 | Mar 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0001 | DCLA - Brooklyn Museum Deep Energy Retrofit | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2023 | Jun 2023 | Jun 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0001 | DCLA - Brooklyn Museum Deep Energy Retrofit | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0001 | DCLA - Brooklyn Museum Deep Energy Retrofit | 3 | CONSTRUCTION TO 50% | Jun 2024 | Nov 2024 | Jun 2024 | Nov 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0001 | DCLA - Brooklyn Museum Deep Energy Retrofit | 4 | CONSTRUCTION TO 75% | Jun 2026 | Aug 2026 | Jun 2026 | Aug 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0001 | DCLA - Brooklyn Museum Deep Energy Retrofit | 5 | SUBSTANTIAL COMPLETION | Aug 2026 | Oct 2026 | Aug 2026 | Oct 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0001 | DCLA - Brooklyn Museum Deep Energy Retrofit | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2026 | Nov 2026 | Oct 2026 | Nov 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0005 | BROOKLYN SOUTH 7 AND 10 DISTRICT GARAGE ENERGY EFFICIENCY | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0005 | BROOKLYN SOUTH 7 AND 10 DISTRICT GARAGE ENERGY EFFICIENCY | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0005 | BROOKLYN SOUTH 7 AND 10 DISTRICT GARAGE ENERGY EFFICIENCY | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0005 | BROOKLYN SOUTH 7 AND 10 DISTRICT GARAGE ENERGY EFFICIENCY | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0005 | BROOKLYN SOUTH 7 AND 10 DISTRICT GARAGE ENERGY EFFICIENCY | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0005 | BROOKLYN SOUTH 7 AND 10 DISTRICT GARAGE ENERGY EFFICIENCY | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0007 | CUNY Kingsborough Community College (DI) | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0007 | CUNY Kingsborough Community College (DI) | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0007 | CUNY Kingsborough Community College (DI) | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0007 | CUNY Kingsborough Community College (DI) | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0007 | CUNY Kingsborough Community College (DI) | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0007 | CUNY Kingsborough Community College (DI) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0007 | Brownsville Health Center | 1 | DEVELOP SCOPE | Jun 2025 | Jun 2025 | Jun 2025 | Jun 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0007 | Brownsville Health Center | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0007 | Brownsville Health Center | 3 | CONSTRUCTION TO 50% | Aug 2025 | Feb 2026 | Aug 2025 | Feb 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0007 | Brownsville Health Center | 4 | CONSTRUCTION TO 75% | Feb 2026 | May 2026 | Feb 2026 | May 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0007 | Brownsville Health Center | 5 | SUBSTANTIAL COMPLETION | May 2026 | Jul 2026 | May 2026 | Jul 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0007 | Brownsville Health Center | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2026 | Aug 2026 | Jul 2026 | Aug 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-DOE01 | DOE Direct Install Lighting - Phase 2 | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-DOE01 | DOE Direct Install Lighting - Phase 2 | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-DOE01 | DOE Direct Install Lighting - Phase 2 | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-DOE01 | DOE Direct Install Lighting - Phase 2 | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-DOE01 | DOE Direct Install Lighting - Phase 2 | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-DOE01 | DOE Direct Install Lighting - Phase 2 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Jun 2026 | Jul 2025 | Jun 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0017 | BPL - Bushwick Branch Library | 3 | CONSTRUCTION TO 50% | Aug 2019 | Feb 2020 | Aug 2019 | Feb 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0017 | BPL - Bushwick Branch Library | 4 | CONSTRUCTION TO 75% | Feb 2020 | May 2020 | Feb 2020 | May 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0017 | BPL - Bushwick Branch Library | 5 | SUBSTANTIAL COMPLETION | May 2020 | Jul 2020 | May 2020 | Jul 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0017 | BPL - Bushwick Branch Library | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Aug 2020 | Jul 2020 | Aug 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0020 | NYPD - 71st Precinct | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2020 | Jun 2020 | Jun 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0020 | NYPD - 71st Precinct | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Aug 2020 | Jul 2020 | Aug 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0020 | NYPD - 71st Precinct | 3 | CONSTRUCTION TO 50% | Aug 2020 | Feb 2021 | Aug 2020 | Feb 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0020 | NYPD - 71st Precinct | 4 | CONSTRUCTION TO 75% | Feb 2021 | May 2021 | Feb 2021 | May 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0020 | NYPD - 71st Precinct | 5 | SUBSTANTIAL COMPLETION | May 2021 | Jul 2021 | May 2021 | Jul 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0020 | NYPD - 71st Precinct | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Aug 2021 | Jul 2021 | Jun 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0022 | NYPD - 79th Precinct | 1 | DEVELOP SCOPE | Jun 2019 | Jun 2019 | Jun 2019 | Jun 2019
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0022 | NYPD - 79th Precinct | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jul 2019 | Aug 2019
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0022 | NYPD - 79th Precinct | 3 | CONSTRUCTION TO 50% | Aug 2019 | Feb 2020 | Aug 2019 | Feb 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0022 | NYPD - 79th Precinct | 4 | CONSTRUCTION TO 75% | Feb 2020 | May 2020 | Feb 2020 | May 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0022 | NYPD - 79th Precinct | 5 | SUBSTANTIAL COMPLETION | May 2020 | Jul 2020 | May 2020 | Jul 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0022 | NYPD - 79th Precinct | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Aug 2020 | Jul 2020 | Aug 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0027 | DSNY - Cioffe Borough Repair Shop | 1 | DEVELOP SCOPE | Jun 2019 | Jun 2019 | Jun 2019 | Jun 2019
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0027 | DSNY - Cioffe Borough Repair Shop | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jul 2019 | Aug 2019
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0027 | DSNY - Cioffe Borough Repair Shop | 3 | CONSTRUCTION TO 50% | Aug 2019 | Feb 2020 | Aug 2019 | Feb 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0027 | DSNY - Cioffe Borough Repair Shop | 4 | CONSTRUCTION TO 75% | Feb 2020 | May 2020 | Jun 2025 | Aug 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0027 | DSNY - Cioffe Borough Repair Shop | 5 | SUBSTANTIAL COMPLETION | May 2020 | Jul 2020 | Aug 2025 | Oct 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0027 | DSNY - Cioffe Borough Repair Shop | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Aug 2020 | Oct 2025 | Nov 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0028 | DSNY - Brooklyn North 9 District Garage | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jul 2019 | Aug 2019
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0028 | DSNY - Brooklyn North 9 District Garage | 3 | CONSTRUCTION TO 50% | Aug 2019 | Feb 2020 | Aug 2019 | Feb 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0028 | DSNY - Brooklyn North 9 District Garage | 4 | CONSTRUCTION TO 75% | Feb 2020 | May 2020 | Feb 2020 | May 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0028 | DSNY - Brooklyn North 9 District Garage | 5 | SUBSTANTIAL COMPLETION | May 2020 | Jul 2020 | May 2020 | Jul 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0028 | DSNY - Brooklyn North 9 District Garage | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Aug 2020 | Jul 2020 | Aug 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0032 | DSNY-Queens West 9 District Garage (Leased In) | 1 | DEVELOP SCOPE | Jun 2019 | Jun 2019 | Jun 2019 | Jun 2019
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0032 | DSNY-Queens West 9 District Garage (Leased In) | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jul 2019 | Aug 2019
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0032 | DSNY-Queens West 9 District Garage (Leased In) | 3 | CONSTRUCTION TO 50% | Aug 2019 | Feb 2020 | Jun 2024 | Nov 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0032 | DSNY-Queens West 9 District Garage (Leased In) | 4 | CONSTRUCTION TO 75% | Feb 2020 | May 2020 | Nov 2024 | Feb 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0032 | DSNY-Queens West 9 District Garage (Leased In) | 5 | SUBSTANTIAL COMPLETION | May 2020 | Jul 2020 | Feb 2025 | Apr 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0032 | DSNY-Queens West 9 District Garage (Leased In) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Aug 2020 | Apr 2025 | May 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0037 | DOHMH - Fort Greene Health Center | 1 | DEVELOP SCOPE | Jun 2019 | Jun 2019 | Jun 2019 | Jun 2019
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0037 | DOHMH - Fort Greene Health Center | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jul 2019 | Aug 2019
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0037 | DOHMH - Fort Greene Health Center | 3 | CONSTRUCTION TO 50% | Aug 2019 | Feb 2020 | Aug 2019 | Feb 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0037 | DOHMH - Fort Greene Health Center | 4 | CONSTRUCTION TO 75% | Feb 2020 | May 2020 | Feb 2020 | May 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0037 | DOHMH - Fort Greene Health Center | 5 | SUBSTANTIAL COMPLETION | May 2020 | Jul 2020 | May 2020 | Jul 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0037 | DOHMH - Fort Greene Health Center | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Aug 2020 | Jul 2020 | Jun 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0057 | NYPD - 9 NYPD SITES COMBINED | 1 | DEVELOP SCOPE | Mar 2020 | Mar 2020 | Mar 2020 | Mar 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0057 | NYPD - 9 NYPD SITES COMBINED | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | May 2020 | Mar 2020 | May 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0057 | NYPD - 9 NYPD SITES COMBINED | 3 | CONSTRUCTION TO 50% | May 2020 | Nov 2020 | Jun 2022 | Nov 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0057 | NYPD - 9 NYPD SITES COMBINED | 4 | CONSTRUCTION TO 75% | Nov 2020 | Feb 2021 | Nov 2022 | Feb 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0057 | NYPD - 9 NYPD SITES COMBINED | 5 | SUBSTANTIAL COMPLETION | Feb 2021 | Apr 2021 | Feb 2023 | Apr 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0057 | NYPD - 9 NYPD SITES COMBINED | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2021 | May 2021 | Apr 2023 | Aug 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0058 | NYPD - 63rd Precinct | 1 | DEVELOP SCOPE | Jan 2020 | Feb 2020 | Jun 2020 | Jun 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0058 | NYPD - 63rd Precinct | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Apr 2020 | Jul 2020 | Aug 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0058 | NYPD - 63rd Precinct | 3 | CONSTRUCTION TO 50% | Apr 2020 | Sep 2020 | Jun 2022 | Nov 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0058 | NYPD - 63rd Precinct | 4 | CONSTRUCTION TO 75% | Oct 2020 | Dec 2020 | Nov 2022 | Feb 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0058 | NYPD - 63rd Precinct | 5 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Feb 2023 | Apr 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0058 | NYPD - 63rd Precinct | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Apr 2023 | Aug 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0059 | NYPD - 66th Precinct | 1 | DEVELOP SCOPE | Jan 2020 | Feb 2020 | Jun 2021 | Jun 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0059 | NYPD - 66th Precinct | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Apr 2020 | Jul 2021 | Aug 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0059 | NYPD - 66th Precinct | 3 | CONSTRUCTION TO 50% | Apr 2020 | Oct 2020 | Aug 2021 | Feb 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0059 | NYPD - 66th Precinct | 4 | CONSTRUCTION TO 75% | Oct 2020 | Jan 2021 | Feb 2022 | May 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0059 | NYPD - 66th Precinct | 5 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | May 2022 | Jul 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0059 | NYPD - 66th Precinct | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Jul 2022 | Aug 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0061 | NYPD - 88th Precinct | 1 | DEVELOP SCOPE | Feb 2020 | Mar 2020 | Jun 2022 | Jun 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0061 | NYPD - 88th Precinct | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Apr 2020 | Jul 2022 | Aug 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0061 | NYPD - 88th Precinct | 3 | CONSTRUCTION TO 50% | May 2020 | Oct 2020 | Aug 2022 | Feb 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0061 | NYPD - 88th Precinct | 4 | CONSTRUCTION TO 75% | Oct 2020 | Jan 2021 | Feb 2023 | May 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0061 | NYPD - 88th Precinct | 5 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | May 2023 | Jul 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0061 | NYPD - 88th Precinct | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Jul 2023 | Aug 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0074 | NYPD - HARBOR UNIT CHARLIE | 1 | DEVELOP SCOPE | Jan 2020 | Feb 2020 | Jun 2022 | Jun 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0074 | NYPD - HARBOR UNIT CHARLIE | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Apr 2020 | Jul 2022 | Aug 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0074 | NYPD - HARBOR UNIT CHARLIE | 3 | CONSTRUCTION TO 50% | Apr 2020 | Oct 2020 | Aug 2022 | Feb 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0074 | NYPD - HARBOR UNIT CHARLIE | 4 | CONSTRUCTION TO 75% | Oct 2020 | Jan 2021 | Feb 2023 | May 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0074 | NYPD - HARBOR UNIT CHARLIE | 5 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | May 2023 | Jul 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0074 | NYPD - HARBOR UNIT CHARLIE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Jul 2023 | Aug 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0079 | HHC/DHS - AUBURN FAMILY RESIDENCE (CUMBERLAND DIAGNOSTIC) | 1 | DEVELOP SCOPE | Feb 2020 | Mar 2020 | Feb 2020 | Mar 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0079 | HHC/DHS - AUBURN FAMILY RESIDENCE (CUMBERLAND DIAGNOSTIC) | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | May 2020 | Mar 2020 | May 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0079 | HHC/DHS - AUBURN FAMILY RESIDENCE (CUMBERLAND DIAGNOSTIC) | 3 | CONSTRUCTION TO 50% | May 2020 | Nov 2020 | May 2020 | Nov 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0079 | HHC/DHS - AUBURN FAMILY RESIDENCE (CUMBERLAND DIAGNOSTIC) | 4 | CONSTRUCTION TO 75% | Nov 2020 | Feb 2021 | Nov 2020 | Feb 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0079 | HHC/DHS - AUBURN FAMILY RESIDENCE (CUMBERLAND DIAGNOSTIC) | 5 | SUBSTANTIAL COMPLETION | Feb 2021 | Apr 2021 | Feb 2021 | Apr 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0079 | HHC/DHS - AUBURN FAMILY RESIDENCE (CUMBERLAND DIAGNOSTIC) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2021 | May 2021 | Apr 2021 | Aug 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0082 | DHS - FANNIE BARNES (URBAN TRANSITIONAL HOUSING) | 3 | CONSTRUCTION TO 50% | May 2020 | Nov 2020 | Aug 2022 | Feb 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0082 | DHS - FANNIE BARNES (URBAN TRANSITIONAL HOUSING) | 4 | CONSTRUCTION TO 75% | Nov 2020 | Feb 2021 | Feb 2023 | May 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0082 | DHS - FANNIE BARNES (URBAN TRANSITIONAL HOUSING) | 5 | SUBSTANTIAL COMPLETION | Feb 2021 | Apr 2021 | May 2023 | Jul 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0082 | DHS - FANNIE BARNES (URBAN TRANSITIONAL HOUSING) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2021 | May 2021 | Jul 2023 | Aug 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0083 | DHS - PARK SLOPE ARMORY SHELTER | 1 | DEVELOP SCOPE | Feb 2020 | Mar 2020 | Feb 2020 | Mar 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0083 | DHS - PARK SLOPE ARMORY SHELTER | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | May 2020 | Mar 2020 | May 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0083 | DHS - PARK SLOPE ARMORY SHELTER | 3 | CONSTRUCTION TO 50% | May 2020 | Nov 2020 | Jun 2022 | Nov 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0083 | DHS - PARK SLOPE ARMORY SHELTER | 4 | CONSTRUCTION TO 75% | Nov 2020 | Feb 2021 | Nov 2022 | Feb 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0083 | DHS - PARK SLOPE ARMORY SHELTER | 5 | SUBSTANTIAL COMPLETION | Feb 2021 | Apr 2021 | Feb 2023 | Apr 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0083 | DHS - PARK SLOPE ARMORY SHELTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2021 | May 2021 | Apr 2023 | Aug 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0084 | DHS - ROSE McCARTHY FAMILY RESIDENCE CAMPUS (1) | 1 | DEVELOP SCOPE | Feb 2020 | Mar 2020 | Feb 2020 | Mar 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0084 | DHS - ROSE McCARTHY FAMILY RESIDENCE CAMPUS (1) | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | May 2020 | Mar 2020 | May 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0084 | DHS - ROSE McCARTHY FAMILY RESIDENCE CAMPUS (1) | 3 | CONSTRUCTION TO 50% | May 2020 | Nov 2020 | Jun 2022 | Nov 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0084 | DHS - ROSE McCARTHY FAMILY RESIDENCE CAMPUS (1) | 4 | CONSTRUCTION TO 75% | Nov 2020 | Feb 2021 | Nov 2022 | Feb 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0084 | DHS - ROSE McCARTHY FAMILY RESIDENCE CAMPUS (1) | 5 | SUBSTANTIAL COMPLETION | Feb 2021 | Apr 2021 | Feb 2023 | Apr 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0084 | DHS - ROSE McCARTHY FAMILY RESIDENCE CAMPUS (1) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2021 | May 2021 | Apr 2023 | Aug 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0085 | DHS - ROSE McCARTHY FAMILY RESIDENCE CAMPUS (2) | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | May 2020 | Aug 2023 | Oct 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0085 | DHS - ROSE McCARTHY FAMILY RESIDENCE CAMPUS (2) | 3 | CONSTRUCTION TO 50% | May 2020 | Nov 2020 | Jun 2022 | Nov 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0085 | DHS - ROSE McCARTHY FAMILY RESIDENCE CAMPUS (2) | 4 | CONSTRUCTION TO 75% | Nov 2020 | Feb 2021 | Jun 2025 | Aug 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0085 | DHS - ROSE McCARTHY FAMILY RESIDENCE CAMPUS (2) | 5 | SUBSTANTIAL COMPLETION | Feb 2021 | Apr 2021 | Aug 2025 | Oct 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0085 | DHS - ROSE McCARTHY FAMILY RESIDENCE CAMPUS (2) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2021 | May 2021 | Oct 2025 | Dec 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0088 | DPR - McCARREN PARK RECREATION CENTER | 1 | DEVELOP SCOPE | Feb 2020 | Mar 2020 | Jun 2022 | Jun 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0088 | DPR - McCARREN PARK RECREATION CENTER | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | May 2020 | Jul 2022 | Aug 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0088 | DPR - McCARREN PARK RECREATION CENTER | 3 | CONSTRUCTION TO 50% | May 2020 | Nov 2020 | Aug 2022 | Feb 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0088 | DPR - McCARREN PARK RECREATION CENTER | 4 | CONSTRUCTION TO 75% | Nov 2020 | Feb 2021 | Feb 2023 | May 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0088 | DPR - McCARREN PARK RECREATION CENTER | 5 | SUBSTANTIAL COMPLETION | Feb 2021 | Apr 2021 | May 2023 | Jul 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0088 | DPR - McCARREN PARK RECREATION CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2021 | May 2021 | Jul 2023 | Sep 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HL82RELOC | OFFICE RELOCATION - 16 COURT ST TO 532 FULTON ST BROOKLYN | 1 | DEVELOP SCOPE | Jun 2024 | Aug 2024 | Jun 2024 | Aug 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HL82RELOC | OFFICE RELOCATION - 16 COURT ST TO 532 FULTON ST BROOKLYN | 2 | PRELIMINARY DESIGN | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HL82RELOC | OFFICE RELOCATION - 16 COURT ST TO 532 FULTON ST BROOKLYN | 3 | FINAL DESIGN | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HL82RELOC | OFFICE RELOCATION - 16 COURT ST TO 532 FULTON ST BROOKLYN | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HL82RELOC | OFFICE RELOCATION - 16 COURT ST TO 532 FULTON ST BROOKLYN | 5 | CONSTRUCTION TO 25% | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HL82RELOC | OFFICE RELOCATION - 16 COURT ST TO 532 FULTON ST BROOKLYN | 6 | CONSTRUCTION TO 50% | Jan 2026 | May 2026 | Jan 2026 | May 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HL82RELOC | OFFICE RELOCATION - 16 COURT ST TO 532 FULTON ST BROOKLYN | 7 | CONSTRUCTION TO 75% | May 2026 | Sep 2026 | May 2026 | Sep 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HL82RELOC | OFFICE RELOCATION - 16 COURT ST TO 532 FULTON ST BROOKLYN | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2026 | Dec 2026 | Sep 2026 | Dec 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HL82RELOC | OFFICE RELOCATION - 16 COURT ST TO 532 FULTON ST BROOKLYN | 9 | SUBSTANTIAL COMPLETION | Dec 2026 | Feb 2027 | Dec 2026 | Feb 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HL82RELOC | OFFICE RELOCATION - 16 COURT ST TO 532 FULTON ST BROOKLYN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2027 | Mar 2027 | Feb 2027 | Mar 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HR25ENY | East New York Office, 2440 Fulton Street, Brooklyn | 1 | DESIGN | Jul 2022 | Dec 2022 | Jun 2023 | Nov 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HR25ENY | East New York Office, 2440 Fulton Street, Brooklyn | 2 | CONSTRUCTION | Dec 2022 | Jun 2023 | Nov 2023 | Jun 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWKF2514 | 25 14th St Fleet Services Shop Rehabilitation | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2019 | Sep 2019
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWKF2514 | 25 14th St Fleet Services Shop Rehabilitation | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2019 | Jan 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWKF2514 | 25 14th St Fleet Services Shop Rehabilitation | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jan 2020 | Jul 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWKF2514 | 25 14th St Fleet Services Shop Rehabilitation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2020 | Oct 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWKF2514 | 25 14th St Fleet Services Shop Rehabilitation | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Oct 2020 | Feb 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWKF2514 | 25 14th St Fleet Services Shop Rehabilitation | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Feb 2021 | Jun 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWKF2514 | 25 14th St Fleet Services Shop Rehabilitation | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWKF2514 | 25 14th St Fleet Services Shop Rehabilitation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Sep 2023 | Dec 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWKF2514 | 25 14th St Fleet Services Shop Rehabilitation | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Dec 2023 | Feb 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWKF2514 | 25 14th St Fleet Services Shop Rehabilitation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Feb 2024 | Oct 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWKFVAR | Varick Build-out | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWKFVAR | Varick Build-out | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWKFVAR | Varick Build-out | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2024 | Jul 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWKFVAR | Varick Build-out | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2024 | Oct 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWKFVAR | Varick Build-out | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2024 | Feb 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWKFVAR | Varick Build-out | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2025 | Jun 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWKFVAR | Varick Build-out | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2025 | Oct 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWKFVAR | Varick Build-out | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2025 | Jan 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWKFVAR | Varick Build-out | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2026 | Mar 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWKFVAR | Varick Build-out | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2026 | Apr 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW291EV | 209 JORALEMON ST.- ELEVATOR UPGRADE | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Aug 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW291EV | 209 JORALEMON ST.- ELEVATOR UPGRADE | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW291EV | 209 JORALEMON ST.- ELEVATOR UPGRADE | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW291EV | 209 JORALEMON ST.- ELEVATOR UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW291EV | 209 JORALEMON ST.- ELEVATOR UPGRADE | 5 | CONSTRUCTION TO 25% | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW291EV | 209 JORALEMON ST.- ELEVATOR UPGRADE | 6 | CONSTRUCTION TO 50% | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW291EV | 209 JORALEMON ST.- ELEVATOR UPGRADE | 7 | CONSTRUCTION TO 75% | Jan 2023 | May 2023 | Jan 2023 | May 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW291EV | 209 JORALEMON ST.- ELEVATOR UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | May 2023 | Aug 2023 | May 2023 | Aug 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW291EV | 209 JORALEMON ST.- ELEVATOR UPGRADE | 9 | SUBSTANTIAL COMPLETION | Aug 2023 | Oct 2023 | Aug 2023 | Oct 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW291EV | 209 JORALEMON ST.- ELEVATOR UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2023 | Nov 2023 | Oct 2023 | Jun 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322FL12 | 345 ADAMS ST.- 12TH FLOOR BUILDOUT OF PROPERTY GROUP SPACE | 1 | DEVELOP SCOPE | Jun 2012 | Aug 2012 | Jun 2012 | Aug 2012
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322FL12 | 345 ADAMS ST.- 12TH FLOOR BUILDOUT OF PROPERTY GROUP SPACE | 2 | PRELIMINARY DESIGN | Aug 2012 | Dec 2012 | Aug 2012 | Dec 2012
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322FL12 | 345 ADAMS ST.- 12TH FLOOR BUILDOUT OF PROPERTY GROUP SPACE | 3 | FINAL DESIGN | Dec 2012 | Jun 2013 | Dec 2012 | Jun 2013
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322FL12 | 345 ADAMS ST.- 12TH FLOOR BUILDOUT OF PROPERTY GROUP SPACE | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2013 | Sep 2013 | Jun 2013 | Sep 2013
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322FL12 | 345 ADAMS ST.- 12TH FLOOR BUILDOUT OF PROPERTY GROUP SPACE | 5 | CONSTRUCTION TO 25% | Sep 2013 | Jan 2014 | Sep 2013 | Jan 2014
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322FL12 | 345 ADAMS ST.- 12TH FLOOR BUILDOUT OF PROPERTY GROUP SPACE | 6 | CONSTRUCTION TO 50% | Jan 2014 | May 2014 | Jun 2022 | Sep 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322FL12 | 345 ADAMS ST.- 12TH FLOOR BUILDOUT OF PROPERTY GROUP SPACE | 7 | CONSTRUCTION TO 75% | May 2014 | Sep 2014 | Sep 2022 | Jan 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322FL12 | 345 ADAMS ST.- 12TH FLOOR BUILDOUT OF PROPERTY GROUP SPACE | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2014 | Dec 2014 | Jan 2023 | Apr 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322FL12 | 345 ADAMS ST.- 12TH FLOOR BUILDOUT OF PROPERTY GROUP SPACE | 9 | SUBSTANTIAL COMPLETION | Dec 2014 | Feb 2015 | Apr 2023 | Jun 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322FL12 | 345 ADAMS ST.- 12TH FLOOR BUILDOUT OF PROPERTY GROUP SPACE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2015 | Mar 2015 | Jun 2023 | Aug 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLA6 | 345 Adams, 8th and 9th Fl | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLA6 | 345 Adams, 8th and 9th Fl | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLA6 | 345 Adams, 8th and 9th Fl | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLA6 | 345 Adams, 8th and 9th Fl | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLA6 | 345 Adams, 8th and 9th Fl | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLA6 | 345 Adams, 8th and 9th Fl | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLA6 | 345 Adams, 8th and 9th Fl | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | May 2024 | Sep 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLA6 | 345 Adams, 8th and 9th Fl | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLA6 | 345 Adams, 8th and 9th Fl | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Dec 2024 | Feb 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLA6 | 345 Adams, 8th and 9th Fl | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Mar 2025 | Feb 2025 | Mar 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLAN | 345 ADAMS RESTACKING PLAN | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Aug 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLAN | 345 ADAMS RESTACKING PLAN | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLAN | 345 ADAMS RESTACKING PLAN | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLAN | 345 ADAMS RESTACKING PLAN | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLAN | 345 ADAMS RESTACKING PLAN | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLAN | 345 ADAMS RESTACKING PLAN | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2022 | May 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLAN | 345 ADAMS RESTACKING PLAN | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2022 | Sep 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLAN | 345 ADAMS RESTACKING PLAN | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLAN | 345 ADAMS RESTACKING PLAN | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2022 | Feb 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLAN | 345 ADAMS RESTACKING PLAN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Feb 2023 | Jun 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325EV | 210 JORALEMON ST - SIDEWALK ELEVATOR MODERNIZATION | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325EV | 210 JORALEMON ST - SIDEWALK ELEVATOR MODERNIZATION | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325EV | 210 JORALEMON ST - SIDEWALK ELEVATOR MODERNIZATION | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325EV | 210 JORALEMON ST - SIDEWALK ELEVATOR MODERNIZATION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325EV | 210 JORALEMON ST - SIDEWALK ELEVATOR MODERNIZATION | 5 | CONSTRUCTION TO 25% | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325EV | 210 JORALEMON ST - SIDEWALK ELEVATOR MODERNIZATION | 6 | CONSTRUCTION TO 50% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325EV | 210 JORALEMON ST - SIDEWALK ELEVATOR MODERNIZATION | 7 | CONSTRUCTION TO 75% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325EV | 210 JORALEMON ST - SIDEWALK ELEVATOR MODERNIZATION | 8 | ORIGINAL EQUIP & FURNISHING | May 2025 | Aug 2025 | May 2025 | Aug 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325EV | 210 JORALEMON ST - SIDEWALK ELEVATOR MODERNIZATION | 9 | SUBSTANTIAL COMPLETION | Aug 2025 | Oct 2025 | Aug 2025 | Oct 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325EV | 210 JORALEMON ST - SIDEWALK ELEVATOR MODERNIZATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2025 | Nov 2025 | Oct 2025 | Nov 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325STA3 | 210 JORALEMON STREET STABILIZATION | 1 | DEVELOP SCOPE | Jun 2019 | Aug 2019 | Jun 2019 | Aug 2019
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325STA3 | 210 JORALEMON STREET STABILIZATION | 2 | PRELIMINARY DESIGN | Aug 2019 | Dec 2019 | Aug 2019 | Dec 2019
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325STA3 | 210 JORALEMON STREET STABILIZATION | 3 | FINAL DESIGN | Dec 2019 | Jun 2020 | Dec 2019 | Jun 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325STA3 | 210 JORALEMON STREET STABILIZATION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325STA3 | 210 JORALEMON STREET STABILIZATION | 5 | CONSTRUCTION TO 25% | Sep 2020 | Jan 2021 | Jun 2022 | Sep 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325STA3 | 210 JORALEMON STREET STABILIZATION | 6 | CONSTRUCTION TO 50% | Jan 2021 | May 2021 | Sep 2022 | Jan 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325STA3 | 210 JORALEMON STREET STABILIZATION | 7 | CONSTRUCTION TO 75% | May 2021 | Sep 2021 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325STA3 | 210 JORALEMON STREET STABILIZATION | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Dec 2021 | Sep 2023 | Dec 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325STA3 | 210 JORALEMON STREET STABILIZATION | 9 | SUBSTANTIAL COMPLETION | Dec 2021 | Feb 2022 | Dec 2023 | Feb 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325STA3 | 210 JORALEMON STREET STABILIZATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2022 | Mar 2022 | Feb 2024 | Mar 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326APPE | OCA - 1 WILLOUGHBY SQ, FLs 10,11, BK APPELLATE RELOCATION | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326APPE | OCA - 1 WILLOUGHBY SQ, FLs 10,11, BK APPELLATE RELOCATION | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326APPE | OCA - 1 WILLOUGHBY SQ, FLs 10,11, BK APPELLATE RELOCATION | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326APPE | OCA - 1 WILLOUGHBY SQ, FLs 10,11, BK APPELLATE RELOCATION | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326APPE | OCA - 1 WILLOUGHBY SQ, FLs 10,11, BK APPELLATE RELOCATION | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326APPE | OCA - 1 WILLOUGHBY SQ, FLs 10,11, BK APPELLATE RELOCATION | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326APPE | OCA - 1 WILLOUGHBY SQ, FLs 10,11, BK APPELLATE RELOCATION | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326APPE | OCA - 1 WILLOUGHBY SQ, FLs 10,11, BK APPELLATE RELOCATION | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326APPE | OCA - 1 WILLOUGHBY SQ, FLs 10,11, BK APPELLATE RELOCATION | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326APPE | OCA - 1 WILLOUGHBY SQ, FLs 10,11, BK APPELLATE RELOCATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2029
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326BKDA | BROOKLYN DA - WAREHOUSE SPACE | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326BKDA | BROOKLYN DA - WAREHOUSE SPACE | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326BKDA | BROOKLYN DA - WAREHOUSE SPACE | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326BKDA | BROOKLYN DA - WAREHOUSE SPACE | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326BKDA | BROOKLYN DA - WAREHOUSE SPACE | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326BKDA | BROOKLYN DA - WAREHOUSE SPACE | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326BKDA | BROOKLYN DA - WAREHOUSE SPACE | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326BKDA | BROOKLYN DA - WAREHOUSE SPACE | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326BKDA | BROOKLYN DA - WAREHOUSE SPACE | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326BKDA | BROOKLYN DA - WAREHOUSE SPACE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326CB17 | CB17 - 350 CLARKSON AVE, PARTIAL 1ST FL, BK RELOCATION | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326CB17 | CB17 - 350 CLARKSON AVE, PARTIAL 1ST FL, BK RELOCATION | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326CB17 | CB17 - 350 CLARKSON AVE, PARTIAL 1ST FL, BK RELOCATION | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326CB17 | CB17 - 350 CLARKSON AVE, PARTIAL 1ST FL, BK RELOCATION | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326CB17 | CB17 - 350 CLARKSON AVE, PARTIAL 1ST FL, BK RELOCATION | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326CB17 | CB17 - 350 CLARKSON AVE, PARTIAL 1ST FL, BK RELOCATION | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326CB17 | CB17 - 350 CLARKSON AVE, PARTIAL 1ST FL, BK RELOCATION | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326CB17 | CB17 - 350 CLARKSON AVE, PARTIAL 1ST FL, BK RELOCATION | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326CB17 | CB17 - 350 CLARKSON AVE, PARTIAL 1ST FL, BK RELOCATION | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326CB17 | CB17 - 350 CLARKSON AVE, PARTIAL 1ST FL, BK RELOCATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAK1 | BKLYN DA - 350 JAY ST, FLs 14-15 RENEWAL OPTION & ADDL SPACE | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAK1 | BKLYN DA - 350 JAY ST, FLs 14-15 RENEWAL OPTION & ADDL SPACE | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAK1 | BKLYN DA - 350 JAY ST, FLs 14-15 RENEWAL OPTION & ADDL SPACE | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAK1 | BKLYN DA - 350 JAY ST, FLs 14-15 RENEWAL OPTION & ADDL SPACE | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAK1 | BKLYN DA - 350 JAY ST, FLs 14-15 RENEWAL OPTION & ADDL SPACE | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAK1 | BKLYN DA - 350 JAY ST, FLs 14-15 RENEWAL OPTION & ADDL SPACE | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAK1 | BKLYN DA - 350 JAY ST, FLs 14-15 RENEWAL OPTION & ADDL SPACE | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | May 2024 | Sep 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAK1 | BKLYN DA - 350 JAY ST, FLs 14-15 RENEWAL OPTION & ADDL SPACE | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAK1 | BKLYN DA - 350 JAY ST, FLs 14-15 RENEWAL OPTION & ADDL SPACE | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Dec 2024 | Feb 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAK1 | BKLYN DA - 350 JAY ST, FLs 14-15 RENEWAL OPTION & ADDL SPACE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Mar 2025 | Feb 2025 | Mar 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAK2 | BKLYN DA - 335 ADAMS STREET, FLs 7 & 26 FAMILY JUSTICE CNTR | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAK2 | BKLYN DA - 335 ADAMS STREET, FLs 7 & 26 FAMILY JUSTICE CNTR | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAK2 | BKLYN DA - 335 ADAMS STREET, FLs 7 & 26 FAMILY JUSTICE CNTR | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAK2 | BKLYN DA - 335 ADAMS STREET, FLs 7 & 26 FAMILY JUSTICE CNTR | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAK2 | BKLYN DA - 335 ADAMS STREET, FLs 7 & 26 FAMILY JUSTICE CNTR | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAK2 | BKLYN DA - 335 ADAMS STREET, FLs 7 & 26 FAMILY JUSTICE CNTR | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAK2 | BKLYN DA - 335 ADAMS STREET, FLs 7 & 26 FAMILY JUSTICE CNTR | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | May 2024 | Sep 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAK2 | BKLYN DA - 335 ADAMS STREET, FLs 7 & 26 FAMILY JUSTICE CNTR | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAK2 | BKLYN DA - 335 ADAMS STREET, FLs 7 & 26 FAMILY JUSTICE CNTR | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Dec 2024 | Feb 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAK2 | BKLYN DA - 335 ADAMS STREET, FLs 7 & 26 FAMILY JUSTICE CNTR | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Mar 2025 | Feb 2025 | Mar 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOF5 | DOF - RELOCATION FROM 210 JORALEMON AND 345 ADAMS | 1 | DEVELOP SCOPE | Jun 2019 | Aug 2019 | Jun 2019 | Aug 2019
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOF5 | DOF - RELOCATION FROM 210 JORALEMON AND 345 ADAMS | 2 | PRELIMINARY DESIGN | Aug 2019 | Dec 2019 | Aug 2019 | Dec 2019
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOF5 | DOF - RELOCATION FROM 210 JORALEMON AND 345 ADAMS | 3 | FINAL DESIGN | Dec 2019 | Jun 2020 | Dec 2019 | Jun 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOF5 | DOF - RELOCATION FROM 210 JORALEMON AND 345 ADAMS | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOF5 | DOF - RELOCATION FROM 210 JORALEMON AND 345 ADAMS | 5 | CONSTRUCTION TO 25% | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOF5 | DOF - RELOCATION FROM 210 JORALEMON AND 345 ADAMS | 6 | CONSTRUCTION TO 50% | Jan 2021 | May 2021 | Jan 2021 | May 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOF5 | DOF - RELOCATION FROM 210 JORALEMON AND 345 ADAMS | 7 | CONSTRUCTION TO 75% | May 2021 | Sep 2021 | May 2021 | Sep 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOF5 | DOF - RELOCATION FROM 210 JORALEMON AND 345 ADAMS | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Dec 2021 | Sep 2021 | Dec 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOF5 | DOF - RELOCATION FROM 210 JORALEMON AND 345 ADAMS | 9 | SUBSTANTIAL COMPLETION | Dec 2021 | Feb 2022 | Dec 2021 | Feb 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOF5 | DOF - RELOCATION FROM 210 JORALEMON AND 345 ADAMS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2022 | Mar 2022 | Feb 2022 | Mar 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326LAW7 | LAW - 167 41ST - LAW DEPT CONSOLIDATION | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2021 | Aug 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326LAW7 | LAW - 167 41ST - LAW DEPT CONSOLIDATION | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2020 | Mar 2021 | Aug 2021 | Dec 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326LAW7 | LAW - 167 41ST - LAW DEPT CONSOLIDATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Jun 2022 | Dec 2021 | Jun 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326LAW7 | LAW - 167 41ST - LAW DEPT CONSOLIDATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2022 | Aug 2022 | Jun 2022 | Sep 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326LAW7 | LAW - 167 41ST - LAW DEPT CONSOLIDATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2022 | Jul 2022 | Sep 2022 | Jan 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326LAW7 | LAW - 167 41ST - LAW DEPT CONSOLIDATION | 6 | CONSTRUCTION TO 50% | Jul 2022 | Jul 2022 | Jan 2023 | May 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326LAW7 | LAW - 167 41ST - LAW DEPT CONSOLIDATION | 7 | CONSTRUCTION TO 75% | Jul 2022 | Jul 2022 | May 2023 | Sep 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326LAW7 | LAW - 167 41ST - LAW DEPT CONSOLIDATION | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2022 | Jul 2022 | Sep 2023 | Dec 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326LAW7 | LAW - 167 41ST - LAW DEPT CONSOLIDATION | 9 | SUBSTANTIAL COMPLETION | Jul 2022 | Jul 2022 | Dec 2023 | Feb 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326LAW7 | LAW - 167 41ST - LAW DEPT CONSOLIDATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2022 | Jul 2022 | Feb 2024 | Mar 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAK | LAW DEPT - RAISE THE AGE - BROOKLYN | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2019 | Aug 2019
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAK | LAW DEPT - RAISE THE AGE - BROOKLYN | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2019 | Dec 2019
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAK | LAW DEPT - RAISE THE AGE - BROOKLYN | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2019 | Jun 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAK | LAW DEPT - RAISE THE AGE - BROOKLYN | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2020 | Sep 2020
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAK | LAW DEPT - RAISE THE AGE - BROOKLYN | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2020 | Jan 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAK | LAW DEPT - RAISE THE AGE - BROOKLYN | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2021 | May 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAK | LAW DEPT - RAISE THE AGE - BROOKLYN | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | Jun 2028 | Sep 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAK | LAW DEPT - RAISE THE AGE - BROOKLYN | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2028 | Dec 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAK | LAW DEPT - RAISE THE AGE - BROOKLYN | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2028 | Feb 2029
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAK | LAW DEPT - RAISE THE AGE - BROOKLYN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Feb 2029 | Mar 2029
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340BOE | BOE - 345 ADAMS ST.- BATHROOMS RENOVATION | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2024 | Aug 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340BOE | BOE - 345 ADAMS ST.- BATHROOMS RENOVATION | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2024 | Dec 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340BOE | BOE - 345 ADAMS ST.- BATHROOMS RENOVATION | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2024 | Jun 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340BOE | BOE - 345 ADAMS ST.- BATHROOMS RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2025 | Sep 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340BOE | BOE - 345 ADAMS ST.- BATHROOMS RENOVATION | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2025 | Jan 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340BOE | BOE - 345 ADAMS ST.- BATHROOMS RENOVATION | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2026 | May 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340BOE | BOE - 345 ADAMS ST.- BATHROOMS RENOVATION | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2026 | Sep 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340BOE | BOE - 345 ADAMS ST.- BATHROOMS RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2026 | Dec 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340BOE | BOE - 345 ADAMS ST.- BATHROOMS RENOVATION | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2026 | Feb 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340BOE | BOE - 345 ADAMS ST.- BATHROOMS RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Feb 2027 | Mar 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340KEXP | BOE - 5112 2nd AVE, BROOKLYN EXPANSION | 1 | DEVELOP SCOPE | Jun 2021 | Aug 2021 | Jun 2021 | Aug 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340KEXP | BOE - 5112 2nd AVE, BROOKLYN EXPANSION | 2 | PRELIMINARY DESIGN | Aug 2021 | Dec 2021 | Aug 2021 | Dec 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340KEXP | BOE - 5112 2nd AVE, BROOKLYN EXPANSION | 3 | FINAL DESIGN | Dec 2021 | Jun 2022 | Dec 2021 | Jun 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340KEXP | BOE - 5112 2nd AVE, BROOKLYN EXPANSION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340KEXP | BOE - 5112 2nd AVE, BROOKLYN EXPANSION | 5 | CONSTRUCTION TO 25% | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340KEXP | BOE - 5112 2nd AVE, BROOKLYN EXPANSION | 6 | CONSTRUCTION TO 50% | Jan 2023 | May 2023 | Jan 2023 | May 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340KEXP | BOE - 5112 2nd AVE, BROOKLYN EXPANSION | 7 | CONSTRUCTION TO 75% | May 2023 | Sep 2023 | May 2023 | Sep 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340KEXP | BOE - 5112 2nd AVE, BROOKLYN EXPANSION | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Dec 2023 | Sep 2023 | Dec 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340KEXP | BOE - 5112 2nd AVE, BROOKLYN EXPANSION | 9 | SUBSTANTIAL COMPLETION | Dec 2023 | Feb 2024 | Dec 2023 | Feb 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340KEXP | BOE - 5112 2nd AVE, BROOKLYN EXPANSION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2024 | Mar 2024 | Feb 2024 | Oct 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ADM13 | 345 Adams 13th Floor DCAS Police Relocation | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ADM13 | 345 Adams 13th Floor DCAS Police Relocation | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ADM13 | 345 Adams 13th Floor DCAS Police Relocation | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ADM13 | 345 Adams 13th Floor DCAS Police Relocation | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ADM13 | 345 Adams 13th Floor DCAS Police Relocation | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ADM13 | 345 Adams 13th Floor DCAS Police Relocation | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ADM13 | 345 Adams 13th Floor DCAS Police Relocation | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ADM13 | 345 Adams 13th Floor DCAS Police Relocation | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ADM13 | 345 Adams 13th Floor DCAS Police Relocation | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ADM13 | 345 Adams 13th Floor DCAS Police Relocation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77OEM5 | OEM - EXPANSION OF HEADQUARTERS | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2032 | Aug 2032
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77OEM5 | OEM - EXPANSION OF HEADQUARTERS | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2032 | Dec 2032
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77OEM5 | OEM - EXPANSION OF HEADQUARTERS | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2032 | Jun 2033
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77OEM5 | OEM - EXPANSION OF HEADQUARTERS | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2033 | Sep 2033
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77OEM5 | OEM - EXPANSION OF HEADQUARTERS | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2033 | Jan 2034
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77OEM5 | OEM - EXPANSION OF HEADQUARTERS | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2034 | May 2034
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77OEM5 | OEM - EXPANSION OF HEADQUARTERS | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2034 | Sep 2034
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77OEM5 | OEM - EXPANSION OF HEADQUARTERS | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2034 | Dec 2034
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77OEM5 | OEM - EXPANSION OF HEADQUARTERS | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2034 | Feb 2035
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77OEM5 | OEM - EXPANSION OF HEADQUARTERS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2035 | Mar 2035
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ZK07 | BROOKLYN COMMUNITY BOARD 7- 4201 4TH AVENUE | 1 | DEVELOP SCOPE | May 2016 | Aug 2016 | Jun 2027 | Aug 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ZK07 | BROOKLYN COMMUNITY BOARD 7- 4201 4TH AVENUE | 2 | PRELIMINARY DESIGN | Aug 2016 | Dec 2016 | Jun 2027 | Sep 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ZK07 | BROOKLYN COMMUNITY BOARD 7- 4201 4TH AVENUE | 3 | FINAL DESIGN | Dec 2016 | Jun 2017 | Sep 2027 | Mar 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ZK07 | BROOKLYN COMMUNITY BOARD 7- 4201 4TH AVENUE | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2017 | Sep 2017 | Mar 2028 | Jun 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ZK07 | BROOKLYN COMMUNITY BOARD 7- 4201 4TH AVENUE | 5 | CONSTRUCTION TO 25% | Sep 2017 | Jan 2018 | Jun 2028 | Oct 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ZK07 | BROOKLYN COMMUNITY BOARD 7- 4201 4TH AVENUE | 6 | CONSTRUCTION TO 50% | Jan 2018 | May 2018 | Oct 2028 | Feb 2029
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ZK07 | BROOKLYN COMMUNITY BOARD 7- 4201 4TH AVENUE | 7 | CONSTRUCTION TO 75% | May 2018 | Sep 2018 | Feb 2029 | Jun 2029
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ZK07 | BROOKLYN COMMUNITY BOARD 7- 4201 4TH AVENUE | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2018 | Nov 2018 | Jun 2029 | Sep 2029
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ZK07 | BROOKLYN COMMUNITY BOARD 7- 4201 4TH AVENUE | 9 | SUBSTANTIAL COMPLETION | Dec 2018 | Jan 2019 | Sep 2029 | Nov 2029
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ZK07 | BROOKLYN COMMUNITY BOARD 7- 4201 4TH AVENUE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2019 | Feb 2019 | Nov 2029 | Dec 2029
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD007HPD | HPD - CONSTRUCTION AND RENOVATION OF NORTHSIDE TOWN HALL | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2024 | Aug 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD007HPD | HPD - CONSTRUCTION AND RENOVATION OF NORTHSIDE TOWN HALL | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2024 | Dec 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD007HPD | HPD - CONSTRUCTION AND RENOVATION OF NORTHSIDE TOWN HALL | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2024 | Jun 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD007HPD | HPD - CONSTRUCTION AND RENOVATION OF NORTHSIDE TOWN HALL | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2025 | Sep 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD007HPD | HPD - CONSTRUCTION AND RENOVATION OF NORTHSIDE TOWN HALL | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2025 | Jan 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD007HPD | HPD - CONSTRUCTION AND RENOVATION OF NORTHSIDE TOWN HALL | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2026 | May 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD007HPD | HPD - CONSTRUCTION AND RENOVATION OF NORTHSIDE TOWN HALL | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2026 | Sep 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD007HPD | HPD - CONSTRUCTION AND RENOVATION OF NORTHSIDE TOWN HALL | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Jun 2028 | Aug 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD007HPD | HPD - CONSTRUCTION AND RENOVATION OF NORTHSIDE TOWN HALL | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Aug 2028 | Oct 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD007HPD | HPD - CONSTRUCTION AND RENOVATION OF NORTHSIDE TOWN HALL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Oct 2028 | Nov 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD30BENC | BENJAMIN BANNEKER ACADEMY FOR COMMUNITY DEVELOPMENT | 1 | PROJECT START | Mar 2018 | Mar 2018 | Jun 2027 | Jun 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD30BENC | BENJAMIN BANNEKER ACADEMY FOR COMMUNITY DEVELOPMENT | 2 | DESIGN START | Mar 2018 | Mar 2018 | Jun 2027 | Jun 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD30BENC | BENJAMIN BANNEKER ACADEMY FOR COMMUNITY DEVELOPMENT | 3 | DESIGN COMPLETION | Mar 2018 | Sep 2018 | Jun 2027 | Dec 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD30BENC | BENJAMIN BANNEKER ACADEMY FOR COMMUNITY DEVELOPMENT | 4 | CONSTRUCTION START | Sep 2018 | Mar 2019 | Dec 2027 | Jun 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD30BENC | BENJAMIN BANNEKER ACADEMY FOR COMMUNITY DEVELOPMENT | 5 | CONSTRUCTION COMPLETION | Mar 2019 | Sep 2019 | Jun 2028 | Dec 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78BLL | 360 ADAMS STREET- BROOKLYN SUPREME COURT LAW LIBRARY | 1 | DEVELOP SCOPE | Jun 2024 | Aug 2024 | Jun 2028 | Aug 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78BLL | 360 ADAMS STREET- BROOKLYN SUPREME COURT LAW LIBRARY | 2 | PRELIMINARY DESIGN | Aug 2024 | Dec 2024 | Aug 2028 | Dec 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78BLL | 360 ADAMS STREET- BROOKLYN SUPREME COURT LAW LIBRARY | 3 | FINAL DESIGN | Dec 2024 | Jun 2025 | Dec 2028 | Jun 2029
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78BLL | 360 ADAMS STREET- BROOKLYN SUPREME COURT LAW LIBRARY | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2025 | Sep 2025 | Jun 2029 | Sep 2029
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78BLL | 360 ADAMS STREET- BROOKLYN SUPREME COURT LAW LIBRARY | 5 | CONSTRUCTION TO 25% | Sep 2025 | Jan 2026 | Sep 2029 | Jan 2030
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78BLL | 360 ADAMS STREET- BROOKLYN SUPREME COURT LAW LIBRARY | 6 | CONSTRUCTION TO 50% | Jan 2026 | May 2026 | Jan 2030 | May 2030
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78BLL | 360 ADAMS STREET- BROOKLYN SUPREME COURT LAW LIBRARY | 7 | CONSTRUCTION TO 75% | May 2026 | Sep 2026 | May 2030 | Sep 2030
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78BLL | 360 ADAMS STREET- BROOKLYN SUPREME COURT LAW LIBRARY | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2026 | Dec 2026 | Nov 2028 | Feb 2029
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78BLL | 360 ADAMS STREET- BROOKLYN SUPREME COURT LAW LIBRARY | 9 | SUBSTANTIAL COMPLETION | Dec 2026 | Feb 2027 | Feb 2029 | Apr 2029
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78BLL | 360 ADAMS STREET- BROOKLYN SUPREME COURT LAW LIBRARY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2027 | Mar 2027 | Apr 2029 | May 2032
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78SSCT | 360 ADAMS ST.- HVAC STATE SUPREME COURT | 1 | DEVELOP SCOPE | Apr 2013 | Jun 2013 | Jun 2026 | Aug 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78SSCT | 360 ADAMS ST.- HVAC STATE SUPREME COURT | 2 | PRELIMINARY DESIGN | Jun 2013 | Oct 2013 | Aug 2026 | Dec 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78SSCT | 360 ADAMS ST.- HVAC STATE SUPREME COURT | 3 | FINAL DESIGN | Oct 2013 | Apr 2014 | Dec 2026 | Jun 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78SSCT | 360 ADAMS ST.- HVAC STATE SUPREME COURT | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2014 | Jul 2014 | Jun 2027 | Sep 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78SSCT | 360 ADAMS ST.- HVAC STATE SUPREME COURT | 5 | CONSTRUCTION TO 25% | Jul 2014 | Nov 2014 | Sep 2027 | Jan 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78SSCT | 360 ADAMS ST.- HVAC STATE SUPREME COURT | 6 | CONSTRUCTION TO 50% | Nov 2014 | Mar 2015 | Jan 2028 | May 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78SSCT | 360 ADAMS ST.- HVAC STATE SUPREME COURT | 7 | CONSTRUCTION TO 75% | Mar 2015 | Jul 2015 | May 2028 | Sep 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78SSCT | 360 ADAMS ST.- HVAC STATE SUPREME COURT | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2015 | Oct 2015 | Sep 2028 | Dec 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78SSCT | 360 ADAMS ST.- HVAC STATE SUPREME COURT | 9 | SUBSTANTIAL COMPLETION | Oct 2015 | Dec 2015 | Dec 2028 | Feb 2029
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78SSCT | 360 ADAMS ST.- HVAC STATE SUPREME COURT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2015 | Jan 2016 | Feb 2029 | Mar 2032
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2LEED | Brooklyn Borough Hall - LEED- Funding for LEED | 1 | DEVELOP SCOPE | Jun 2021 | Aug 2021 | Jun 2027 | Aug 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2LEED | Brooklyn Borough Hall - LEED- Funding for LEED | 2 | PRELIMINARY DESIGN | Aug 2021 | Dec 2021 | Aug 2027 | Dec 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2LEED | Brooklyn Borough Hall - LEED- Funding for LEED | 3 | FINAL DESIGN | Dec 2021 | Jun 2022 | Dec 2027 | Jun 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2LEED | Brooklyn Borough Hall - LEED- Funding for LEED | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Sep 2022 | Jun 2028 | Sep 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2LEED | Brooklyn Borough Hall - LEED- Funding for LEED | 5 | CONSTRUCTION TO 25% | Sep 2022 | Jan 2023 | Sep 2028 | Jan 2029
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2LEED | Brooklyn Borough Hall - LEED- Funding for LEED | 6 | CONSTRUCTION TO 50% | Jan 2023 | May 2023 | Jan 2029 | May 2029
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2LEED | Brooklyn Borough Hall - LEED- Funding for LEED | 7 | CONSTRUCTION TO 75% | May 2023 | Sep 2023 | May 2029 | Sep 2029
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2LEED | Brooklyn Borough Hall - LEED- Funding for LEED | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Dec 2023 | Sep 2029 | Dec 2029
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2LEED | Brooklyn Borough Hall - LEED- Funding for LEED | 9 | SUBSTANTIAL COMPLETION | Dec 2023 | Feb 2024 | Dec 2029 | Feb 2030
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2LEED | Brooklyn Borough Hall - LEED- Funding for LEED | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2024 | Mar 2024 | Feb 2030 | Mar 2030
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2MEDIA | 209 JORALEMON ST.- BKLYN BORO HALL MEDIA ROOM | 1 | DEVELOP SCOPE | Jan 2009 | Mar 2009 | Jun 2023 | Aug 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2MEDIA | 209 JORALEMON ST.- BKLYN BORO HALL MEDIA ROOM | 2 | PRELIMINARY DESIGN | Apr 2009 | Jul 2009 | Aug 2023 | Dec 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2MEDIA | 209 JORALEMON ST.- BKLYN BORO HALL MEDIA ROOM | 3 | FINAL DESIGN | Jul 2009 | Jan 2010 | Dec 2023 | Jun 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2MEDIA | 209 JORALEMON ST.- BKLYN BORO HALL MEDIA ROOM | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2010 | Apr 2010 | Jun 2024 | Sep 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2MEDIA | 209 JORALEMON ST.- BKLYN BORO HALL MEDIA ROOM | 5 | CONSTRUCTION TO 25% | Apr 2010 | Aug 2010 | Sep 2024 | Sep 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2MEDIA | 209 JORALEMON ST.- BKLYN BORO HALL MEDIA ROOM | 6 | CONSTRUCTION TO 50% | Aug 2010 | Dec 2010 | Sep 2025 | Sep 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2MEDIA | 209 JORALEMON ST.- BKLYN BORO HALL MEDIA ROOM | 7 | CONSTRUCTION TO 75% | Dec 2010 | Apr 2011 | Sep 2026 | Sep 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2MEDIA | 209 JORALEMON ST.- BKLYN BORO HALL MEDIA ROOM | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2011 | Jul 2011 | Sep 2027 | Oct 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2MEDIA | 209 JORALEMON ST.- BKLYN BORO HALL MEDIA ROOM | 9 | SUBSTANTIAL COMPLETION | Jul 2011 | Sep 2011 | Oct 2027 | Nov 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2MEDIA | 209 JORALEMON ST.- BKLYN BORO HALL MEDIA ROOM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2011 | Oct 2011 | Nov 2027 | Nov 2031
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25LL | LOTTS LANE REPAIRING | 1 | DEVELOP SCOPE | Jun 2021 | Aug 2021 | Jun 2021 | Aug 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25LL | LOTTS LANE REPAIRING | 2 | PRELIMINARY DESIGN | Aug 2021 | Dec 2021 | Aug 2021 | Dec 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25LL | LOTTS LANE REPAIRING | 3 | FINAL DESIGN | Dec 2021 | Jun 2022 | Dec 2021 | Jun 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25LL | LOTTS LANE REPAIRING | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25LL | LOTTS LANE REPAIRING | 5 | CONSTRUCTION TO 25% | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25LL | LOTTS LANE REPAIRING | 6 | CONSTRUCTION TO 50% | Dec 2023 | Apr 2024 | Dec 2023 | Apr 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25LL | LOTTS LANE REPAIRING | 7 | CONSTRUCTION TO 75% | Apr 2024 | Aug 2024 | Apr 2024 | Aug 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25LL | LOTTS LANE REPAIRING | 8 | ORIGINAL EQUIP & FURNISHING | Aug 2024 | Nov 2024 | Aug 2024 | Nov 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25LL | LOTTS LANE REPAIRING | 9 | SUBSTANTIAL COMPLETION | Nov 2024 | Jan 2025 | Nov 2024 | Jan 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25LL | LOTTS LANE REPAIRING | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2025 | Feb 2025 | Jan 2025 | Feb 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25QR | QUENTIN ROAD BROOKLYN STREET RECONSTRUCTION | 1 | DEVELOP SCOPE | Jun 2021 | Aug 2021 | Jun 2021 | Aug 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25QR | QUENTIN ROAD BROOKLYN STREET RECONSTRUCTION | 2 | PRELIMINARY DESIGN | Aug 2021 | Dec 2021 | Aug 2021 | Dec 2021
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25QR | QUENTIN ROAD BROOKLYN STREET RECONSTRUCTION | 3 | FINAL DESIGN | Dec 2021 | Jun 2022 | Dec 2021 | Jun 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25QR | QUENTIN ROAD BROOKLYN STREET RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25QR | QUENTIN ROAD BROOKLYN STREET RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25QR | QUENTIN ROAD BROOKLYN STREET RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25QR | QUENTIN ROAD BROOKLYN STREET RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25QR | QUENTIN ROAD BROOKLYN STREET RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | May 2024 | Aug 2024 | May 2024 | Aug 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25QR | QUENTIN ROAD BROOKLYN STREET RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | Aug 2024 | Oct 2024 | Aug 2024 | Oct 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25QR | QUENTIN ROAD BROOKLYN STREET RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2024 | Nov 2024 | Oct 2024 | Nov 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCA24K191 | SCA FY24 Electrification - K191 | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCA24K191 | SCA FY24 Electrification - K191 | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCA24K191 | SCA FY24 Electrification - K191 | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCA24K191 | SCA FY24 Electrification - K191 | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCA24K191 | SCA FY24 Electrification - K191 | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCA24K191 | SCA FY24 Electrification - K191 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP08 | K005 Building Electrification | 1 | DEVELOP SCOPE | Jun 2021 | Jul 2021 | Jun 2022 | Jun 2022
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP08 | K005 Building Electrification | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Jun 2022 | Jul 2022 | Jun 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP08 | K005 Building Electrification | 3 | CONSTRUCTION TO 50% | Jul 2022 | Dec 2022 | Jun 2023 | Nov 2023
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP08 | K005 Building Electrification | 4 | CONSTRUCTION TO 75% | Dec 2022 | Mar 2023 | Nov 2023 | Feb 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP08 | K005 Building Electrification | 5 | SUBSTANTIAL COMPLETION | Mar 2023 | May 2023 | Feb 2024 | Apr 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP08 | K005 Building Electrification | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2023 | Jun 2023 | Apr 2024 | Aug 2024
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-K162 | SCA Electrification - K162 | 1 | DEVELOP SCOPE | Jun 2028 | Jun 2028 | Jun 2028 | Jun 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-K162 | SCA Electrification - K162 | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2028 | Aug 2028 | Jul 2028 | Aug 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-K162 | SCA Electrification - K162 | 3 | CONSTRUCTION TO 50% | Aug 2028 | Feb 2029 | Aug 2028 | Feb 2029
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-K162 | SCA Electrification - K162 | 4 | CONSTRUCTION TO 75% | Feb 2029 | May 2029 | Feb 2029 | May 2029
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-K162 | SCA Electrification - K162 | 5 | SUBSTANTIAL COMPLETION | May 2029 | Jul 2029 | May 2029 | Jul 2029
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-K162 | SCA Electrification - K162 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2029 | Aug 2029 | Jul 2029 | Aug 2029
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-K420 | SCA Electrification - K420 | 1 | DEVELOP SCOPE | Jun 2026 | Jun 2026 | Jun 2026 | Jun 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-K420 | SCA Electrification - K420 | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2026 | Aug 2026 | Jul 2026 | Aug 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-K420 | SCA Electrification - K420 | 3 | CONSTRUCTION TO 50% | Aug 2026 | Feb 2027 | Aug 2026 | Feb 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-K420 | SCA Electrification - K420 | 4 | CONSTRUCTION TO 75% | Feb 2027 | May 2027 | Feb 2027 | May 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-K420 | SCA Electrification - K420 | 5 | SUBSTANTIAL COMPLETION | May 2027 | Jul 2027 | May 2027 | Jul 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-K420 | SCA Electrification - K420 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2027 | Aug 2027 | Jul 2027 | Aug 2027
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | TKYHHC906 | HHC - East New York Comprehensive Energy Upgrade | 1 | DEVELOP SCOPE | Jun 2022 | Jul 2022 | Jun 2025 | Jun 2025
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | TKYHHC906 | HHC - East New York Comprehensive Energy Upgrade | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Jan 2023 | Jul 2025 | Jan 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | TKYHHC906 | HHC - East New York Comprehensive Energy Upgrade | 3 | CONSTRUCTION TO 50% | Feb 2023 | Jul 2023 | Jan 2026 | Jul 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | TKYHHC906 | HHC - East New York Comprehensive Energy Upgrade | 4 | CONSTRUCTION TO 75% | Jul 2023 | Oct 2023 | Jul 2026 | Sep 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | TKYHHC906 | HHC - East New York Comprehensive Energy Upgrade | 5 | SUBSTANTIAL COMPLETION | Oct 2023 | Dec 2023 | Sep 2026 | Nov 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | TKYHHC906 | HHC - East New York Comprehensive Energy Upgrade | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jan 2024 | Nov 2026 | Dec 2026
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | WD77STAR | STAR ENGINEERING LAB | 1 | DEVELOP SCOPE | Jul 2016 | Sep 2016 | Jun 2028 | Aug 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | WD77STAR | STAR ENGINEERING LAB | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Aug 2028 | Dec 2028
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | WD77STAR | STAR ENGINEERING LAB | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Dec 2028 | Jun 2029
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | WD77STAR | STAR ENGINEERING LAB | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Jun 2029 | Sep 2029
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | WD77STAR | STAR ENGINEERING LAB | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Sep 2029 | Jan 2030
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | WD77STAR | STAR ENGINEERING LAB | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Jan 2030 | May 2030
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | WD77STAR | STAR ENGINEERING LAB | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | May 2030 | Sep 2030
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | WD77STAR | STAR ENGINEERING LAB | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | Sep 2030 | Dec 2030
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | WD77STAR | STAR ENGINEERING LAB | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Dec 2030 | Feb 2031
20231026 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | WD77STAR | STAR ENGINEERING LAB | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Feb 2031 | Mar 2031
20231026 | MANHATTAN | 035 | NEW YORK RESEARCH LIBRARY | L23LPAFAS | LPA - Fire Alarm System Replacement | 1 | DESIGN | Jan 2024 | Jun 2024 | Jan 2024 | Jun 2024
20231026 | MANHATTAN | 035 | NEW YORK RESEARCH LIBRARY | L23LPAFAS | LPA - Fire Alarm System Replacement | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | MANHATTAN | 035 | NEW YORK RESEARCH LIBRARY | L23LPAFAS | LPA - Fire Alarm System Replacement | 3 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 035 | NEW YORK RESEARCH LIBRARY | L23LPAFAS | LPA - Fire Alarm System Replacement | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Mar 2026 | Sep 2025 | Mar 2026
20231026 | MANHATTAN | 035 | NEW YORK RESEARCH LIBRARY | L23SCHOMB | SCHOMBURG CENTER - Decarbonization Project | 1 | DESIGN | Jan 2023 | Jun 2023 | Jan 2023 | Jun 2023
20231026 | MANHATTAN | 035 | NEW YORK RESEARCH LIBRARY | L23SCHOMB | SCHOMBURG CENTER - Decarbonization Project | 2 | CONSTRUCTION | Jun 2023 | Dec 2023 | Jun 2023 | Dec 2023
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18FEEL | 58th Street - New Elevator (ADA Compliance) | 1 | DEVELOP SCOPE | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18FEEL | 58th Street - New Elevator (ADA Compliance) | 2 | DESIGN | Oct 2021 | Oct 2022 | Oct 2021 | Oct 2022
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18FEEL | 58th Street - New Elevator (ADA Compliance) | 3 | BID/ REGISTER CONTRACT | Oct 2022 | Jul 2023 | Oct 2022 | Jul 2023
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18FEEL | 58th Street - New Elevator (ADA Compliance) | 4 | CONSTRUCTION | Jul 2023 | Jul 2025 | Jul 2023 | Jul 2025
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18FEEL | 58th Street - New Elevator (ADA Compliance) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Jul 2026 | Jul 2025 | Jul 2026
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN2058FPS | 58th St - New Fire Protection Sprinkler System | 1 | DEVELOP SCOPE | Aug 2019 | Oct 2019 | Aug 2024 | Oct 2024
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN2058FPS | 58th St - New Fire Protection Sprinkler System | 2 | DESIGN | Oct 2019 | Oct 2020 | Oct 2024 | Oct 2025
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN2058FPS | 58th St - New Fire Protection Sprinkler System | 3 | BID/ REGISTER CONTRACT | Oct 2020 | Jul 2021 | Oct 2025 | Jul 2026
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN2058FPS | 58th St - New Fire Protection Sprinkler System | 4 | CONSTRUCTION | Jul 2021 | Jul 2022 | Jul 2026 | Jul 2027
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN2058FPS | 58th St - New Fire Protection Sprinkler System | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2022 | Jul 2023 | Jul 2027 | Jul 2028
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN21LBHVA | Andrew Heiskell - HVAC System Upgrade | 1 | DEVELOP SCOPE | Jul 2021 | Sep 2021 | Jul 2021 | Sep 2021
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN21LBHVA | Andrew Heiskell - HVAC System Upgrade | 2 | DESIGN | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN21LBHVA | Andrew Heiskell - HVAC System Upgrade | 3 | BID/ REGISTER CONTRACT | Sep 2022 | Jun 2023 | Sep 2022 | Jun 2023
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN21LBHVA | Andrew Heiskell - HVAC System Upgrade | 4 | CONSTRUCTION | Jun 2023 | Jun 2024 | Jun 2023 | Jun 2024
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN21LBHVA | Andrew Heiskell - HVAC System Upgrade | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2024 | Jun 2025 | Jun 2024 | Jun 2025
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN22HUDPK | Hudson Park - Comprehensive Renovation | 1 | DEVELOP SCOPE | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN22HUDPK | Hudson Park - Comprehensive Renovation | 2 | DESIGN | Oct 2023 | Oct 2024 | Oct 2023 | Oct 2024
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN22HUDPK | Hudson Park - Comprehensive Renovation | 3 | BID/ REGISTER CONTRACT | Oct 2024 | Jul 2025 | Oct 2024 | Jul 2025
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN22HUDPK | Hudson Park - Comprehensive Renovation | 4 | CONSTRUCTION | Jul 2025 | Jan 2027 | Jul 2025 | Jan 2027
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN22HUDPK | Hudson Park - Comprehensive Renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2027 | Jan 2028 | Jan 2027 | Jan 2028
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN22YVADA | Yorkville - ADA Accessibility | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN22YVADA | Yorkville - ADA Accessibility | 2 | DESIGN | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN22YVADA | Yorkville - ADA Accessibility | 3 | BID/ REGISTER CONTRACT | Sep 2024 | Jun 2025 | Sep 2024 | Jun 2025
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN22YVADA | Yorkville - ADA Accessibility | 4 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN22YVADA | Yorkville - ADA Accessibility | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Jun 2027 | Jun 2026 | Jun 2027
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN24TSCR | Tompkins Square - Comprehensive Renovation | 1 | DEVELOP SCOPE | Jun 2024 | Dec 2024 | Jun 2024 | Dec 2024
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN24TSCR | Tompkins Square - Comprehensive Renovation | 2 | DESIGN | Dec 2024 | Dec 2026 | Dec 2024 | Dec 2026
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN24TSCR | Tompkins Square - Comprehensive Renovation | 3 | BID/ REGISTER CONTRACT | Dec 2026 | Sep 2027 | Dec 2026 | Sep 2027
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN24TSCR | Tompkins Square - Comprehensive Renovation | 4 | CONSTRUCTION | Sep 2027 | Sep 2029 | Sep 2027 | Sep 2029
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN24TSCR | Tompkins Square - Comprehensive Renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2029 | Sep 2030 | Sep 2029 | Sep 2030
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA16BLD | Bloomingdale - Roof Renovation | 1 | DEVELOP SCOPE | Jul 2020 | Sep 2020 | Jul 2024 | Sep 2024
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA16BLD | Bloomingdale - Roof Renovation | 2 | DESIGN | Sep 2020 | Sep 2021 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA16BLD | Bloomingdale - Roof Renovation | 3 | BID/ REGISTER CONTRACT | Sep 2021 | Jun 2022 | Sep 2025 | Jun 2026
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA16BLD | Bloomingdale - Roof Renovation | 4 | CONSTRUCTION | Jun 2022 | Jun 2023 | Jun 2026 | Jun 2027
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA16BLD | Bloomingdale - Roof Renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2023 | Jun 2024 | Jun 2027 | Jun 2028
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA17CSQ | CHATHAM SQUARE - Boiler Replacement | 1 | DEVELOP SCOPE | Jan 2017 | Apr 2017 | Jun 2025 | Sep 2025
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA17CSQ | CHATHAM SQUARE - Boiler Replacement | 2 | PRELIMINARY DESIGN | Apr 2017 | Aug 2017 | Sep 2025 | Jan 2026
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA17CSQ | CHATHAM SQUARE - Boiler Replacement | 3 | FINAL DESIGN | Aug 2017 | Feb 2018 | Jan 2026 | Jul 2026
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA17CSQ | CHATHAM SQUARE - Boiler Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2018 | May 2018 | Jul 2026 | Oct 2026
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA17CSQ | CHATHAM SQUARE - Boiler Replacement | 5 | CONSTRUCTION TO 25% | May 2018 | Sep 2018 | Oct 2026 | Feb 2027
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA17CSQ | CHATHAM SQUARE - Boiler Replacement | 6 | CONSTRUCTION TO 50% | Sep 2018 | Jan 2019 | Feb 2027 | Jun 2027
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA17CSQ | CHATHAM SQUARE - Boiler Replacement | 7 | CONSTRUCTION TO 75% | Jan 2019 | May 2019 | Jun 2027 | Oct 2027
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA17CSQ | CHATHAM SQUARE - Boiler Replacement | 8 | ORIGINAL EQUIP & FURNISHING | May 2019 | Aug 2019 | Oct 2027 | Jan 2028
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA17CSQ | CHATHAM SQUARE - Boiler Replacement | 9 | SUBSTANTIAL COMPLETION | Aug 2019 | Oct 2019 | Jan 2028 | Mar 2028
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA17CSQ | CHATHAM SQUARE - Boiler Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2019 | Nov 2019 | Mar 2028 | Apr 2028
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNSSEXTFW | 67th St - Building Envelope - Facade & Window Restoration | 1 | DEVELOP SCOPE | Jan 2021 | Mar 2021 | Jan 2027 | Mar 2027
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNSSEXTFW | 67th St - Building Envelope - Facade & Window Restoration | 2 | DESIGN | Apr 2021 | Mar 2022 | Apr 2027 | Mar 2028
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNSSEXTFW | 67th St - Building Envelope - Facade & Window Restoration | 3 | BID/ REGISTER CONTRACT | Apr 2022 | Dec 2022 | Mar 2028 | Dec 2028
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNSSEXTFW | 67th St - Building Envelope - Facade & Window Restoration | 4 | CONSTRUCTION | Dec 2022 | Dec 2023 | Dec 2028 | Dec 2029
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNSSEXTFW | 67th St - Building Envelope - Facade & Window Restoration | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Dec 2024 | Dec 2029 | Dec 2030
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNWBEXTFA | Webster - Building Envelope, Facade Restoration | 1 | DEVELOP SCOPE | Jan 2021 | Mar 2021 | Jun 2026 | Sep 2026
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNWBEXTFA | Webster - Building Envelope, Facade Restoration | 2 | DESIGN | Apr 2021 | Mar 2022 | Sep 2026 | Sep 2027
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNWBEXTFA | Webster - Building Envelope, Facade Restoration | 3 | BID/ REGISTER CONTRACT | Apr 2022 | Dec 2022 | Sep 2027 | Jun 2028
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNWBEXTFA | Webster - Building Envelope, Facade Restoration | 4 | CONSTRUCTION | Dec 2022 | Dec 2023 | Jun 2028 | Jun 2029
20231026 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNWBEXTFA | Webster - Building Envelope, Facade Restoration | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Dec 2024 | Jun 2029 | Jun 2030
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | ACECUN211 | CUNY - Portfolio Submetering - BMCC | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2023 | Jun 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | ACECUN211 | CUNY - Portfolio Submetering - BMCC | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | ACECUN211 | CUNY - Portfolio Submetering - BMCC | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | ACECUN211 | CUNY - Portfolio Submetering - BMCC | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | ACECUN211 | CUNY - Portfolio Submetering - BMCC | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | ACECUN211 | CUNY - Portfolio Submetering - BMCC | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | ACECUN221 | CUNY - BMCC HVAC UPGRADES - 199 CHAMBERS ST, NY | 1 | DEVELOP SCOPE | Jun 2024 | Aug 2024 | Jun 2023 | Aug 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | ACECUN221 | CUNY - BMCC HVAC UPGRADES - 199 CHAMBERS ST, NY | 2 | PRELIMINARY DESIGN | Aug 2024 | Dec 2024 | Aug 2023 | Dec 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | ACECUN221 | CUNY - BMCC HVAC UPGRADES - 199 CHAMBERS ST, NY | 3 | FINAL DESIGN | Dec 2024 | Jun 2025 | Dec 2023 | Jun 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | ACECUN221 | CUNY - BMCC HVAC UPGRADES - 199 CHAMBERS ST, NY | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2025 | Sep 2025 | Jun 2024 | Sep 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | ACECUN221 | CUNY - BMCC HVAC UPGRADES - 199 CHAMBERS ST, NY | 5 | CONSTRUCTION TO 25% | Sep 2025 | Jan 2026 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | ACECUN221 | CUNY - BMCC HVAC UPGRADES - 199 CHAMBERS ST, NY | 6 | CONSTRUCTION TO 50% | Jan 2026 | May 2026 | Jan 2025 | May 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | ACECUN221 | CUNY - BMCC HVAC UPGRADES - 199 CHAMBERS ST, NY | 7 | CONSTRUCTION TO 75% | May 2026 | Sep 2026 | May 2025 | Sep 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | ACECUN221 | CUNY - BMCC HVAC UPGRADES - 199 CHAMBERS ST, NY | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2026 | Dec 2026 | Sep 2025 | Dec 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | ACECUN221 | CUNY - BMCC HVAC UPGRADES - 199 CHAMBERS ST, NY | 9 | SUBSTANTIAL COMPLETION | Dec 2026 | Feb 2027 | Dec 2025 | Feb 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | ACECUN221 | CUNY - BMCC HVAC UPGRADES - 199 CHAMBERS ST, NY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2027 | Mar 2027 | Feb 2026 | Mar 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | ACECUN232 | Borough of Manhattan Community College BMS Upgrade | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2023 | Jun 2023 | Jun 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | ACECUN232 | Borough of Manhattan Community College BMS Upgrade | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | ACECUN232 | Borough of Manhattan Community College BMS Upgrade | 3 | CONSTRUCTION TO 50% | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | ACECUN232 | Borough of Manhattan Community College BMS Upgrade | 4 | CONSTRUCTION TO 75% | Feb 2024 | May 2024 | Feb 2024 | May 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | ACECUN232 | Borough of Manhattan Community College BMS Upgrade | 5 | SUBSTANTIAL COMPLETION | May 2024 | Jul 2024 | May 2024 | Jul 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | ACECUN232 | Borough of Manhattan Community College BMS Upgrade | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-021 | Bathroom Upgrades | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-021 | Bathroom Upgrades | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-021 | Bathroom Upgrades | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-021 | Bathroom Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-021 | Bathroom Upgrades | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-021 | Bathroom Upgrades | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-021 | Bathroom Upgrades | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-021 | Bathroom Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-021 | Bathroom Upgrades | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-021 | Bathroom Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Jul 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-022 | 17 Lexington Multi-purpose Room | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-022 | 17 Lexington Multi-purpose Room | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-022 | 17 Lexington Multi-purpose Room | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-022 | 17 Lexington Multi-purpose Room | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-022 | 17 Lexington Multi-purpose Room | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-022 | 17 Lexington Multi-purpose Room | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-022 | 17 Lexington Multi-purpose Room | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-022 | 17 Lexington Multi-purpose Room | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-022 | 17 Lexington Multi-purpose Room | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-022 | 17 Lexington Multi-purpose Room | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-023 | ADA Bathrooms | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2024 | Jun 2023 | Sep 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-023 | ADA Bathrooms | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-023 | ADA Bathrooms | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-023 | ADA Bathrooms | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-023 | ADA Bathrooms | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-023 | ADA Bathrooms | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-023 | ADA Bathrooms | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-023 | ADA Bathrooms | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-023 | ADA Bathrooms | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-023 | ADA Bathrooms | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2030
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-024 | ONE STOP SHOP (BOSS) STUDENT SUPPORT OFFICES | 1 | DEVELOP SCOPE | Jul 2023 | Sep 2024 | Jul 2023 | Sep 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-024 | ONE STOP SHOP (BOSS) STUDENT SUPPORT OFFICES | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-024 | ONE STOP SHOP (BOSS) STUDENT SUPPORT OFFICES | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-024 | ONE STOP SHOP (BOSS) STUDENT SUPPORT OFFICES | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-024 | ONE STOP SHOP (BOSS) STUDENT SUPPORT OFFICES | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-024 | ONE STOP SHOP (BOSS) STUDENT SUPPORT OFFICES | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-024 | ONE STOP SHOP (BOSS) STUDENT SUPPORT OFFICES | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-024 | ONE STOP SHOP (BOSS) STUDENT SUPPORT OFFICES | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-024 | ONE STOP SHOP (BOSS) STUDENT SUPPORT OFFICES | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-024 | ONE STOP SHOP (BOSS) STUDENT SUPPORT OFFICES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA002-024 | Baruch - ADA Compliant Restroom/Bathroom Renovation | 1 | DEVELOP SCOPE | Jun 2025 | Sep 2026 | Jun 2025 | Sep 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA002-024 | Baruch - ADA Compliant Restroom/Bathroom Renovation | 2 | PRELIMINARY DESIGN | Sep 2026 | Jan 2027 | Sep 2026 | Jan 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA002-024 | Baruch - ADA Compliant Restroom/Bathroom Renovation | 3 | FINAL DESIGN | Jan 2027 | Jul 2027 | Jan 2027 | Jul 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA002-024 | Baruch - ADA Compliant Restroom/Bathroom Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2027 | Oct 2027 | Jul 2027 | Oct 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA002-024 | Baruch - ADA Compliant Restroom/Bathroom Renovation | 5 | CONSTRUCTION TO 25% | Oct 2027 | Feb 2028 | Oct 2027 | Feb 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA002-024 | Baruch - ADA Compliant Restroom/Bathroom Renovation | 6 | CONSTRUCTION TO 50% | Feb 2028 | Jun 2028 | Feb 2028 | Jun 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA002-024 | Baruch - ADA Compliant Restroom/Bathroom Renovation | 7 | CONSTRUCTION TO 75% | Jun 2028 | Oct 2028 | Jun 2028 | Oct 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA002-024 | Baruch - ADA Compliant Restroom/Bathroom Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2028 | Jan 2029 | Oct 2028 | Jan 2029
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA002-024 | Baruch - ADA Compliant Restroom/Bathroom Renovation | 9 | SUBSTANTIAL COMPLETION | Jan 2029 | Mar 2029 | Jan 2029 | Mar 2029
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA002-024 | Baruch - ADA Compliant Restroom/Bathroom Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2029 | Apr 2029 | Mar 2029 | Apr 2029
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA013-013 | Data Center, UPS, and Cooling | 1 | DEVELOP SCOPE | Jun 2013 | Aug 2013 | Jun 2013 | Aug 2013
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA013-013 | Data Center, UPS, and Cooling | 2 | PRELIMINARY DESIGN | Aug 2013 | Dec 2013 | Aug 2013 | Dec 2013
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA013-013 | Data Center, UPS, and Cooling | 3 | FINAL DESIGN | Dec 2013 | Jun 2014 | Dec 2013 | Jun 2014
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA013-013 | Data Center, UPS, and Cooling | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2014 | Sep 2014 | Jun 2014 | Sep 2014
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA013-013 | Data Center, UPS, and Cooling | 5 | CONSTRUCTION TO 25% | Sep 2014 | Jan 2015 | Sep 2014 | Jan 2015
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA013-013 | Data Center, UPS, and Cooling | 6 | CONSTRUCTION TO 50% | Jan 2015 | May 2015 | Jan 2015 | May 2015
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA013-013 | Data Center, UPS, and Cooling | 7 | CONSTRUCTION TO 75% | May 2015 | Sep 2015 | May 2015 | Sep 2015
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA013-013 | Data Center, UPS, and Cooling | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA013-013 | Data Center, UPS, and Cooling | 9 | SUBSTANTIAL COMPLETION | Dec 2015 | Feb 2016 | Dec 2015 | Feb 2016
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA013-013 | Data Center, UPS, and Cooling | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2016 | Mar 2016 | Feb 2016 | Jul 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA024-018 | Modification of Main Entrance at 17 Lexington Avenue | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jul 2024 | Sep 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA024-018 | Modification of Main Entrance at 17 Lexington Avenue | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA024-018 | Modification of Main Entrance at 17 Lexington Avenue | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Jan 2025 | Jul 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA024-018 | Modification of Main Entrance at 17 Lexington Avenue | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jul 2025 | Oct 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA024-018 | Modification of Main Entrance at 17 Lexington Avenue | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Oct 2025 | Feb 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA024-018 | Modification of Main Entrance at 17 Lexington Avenue | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Feb 2026 | Jun 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA024-018 | Modification of Main Entrance at 17 Lexington Avenue | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | Jun 2026 | Oct 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA024-018 | Modification of Main Entrance at 17 Lexington Avenue | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Oct 2026 | Jan 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA024-018 | Modification of Main Entrance at 17 Lexington Avenue | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Jan 2027 | Mar 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA024-018 | Modification of Main Entrance at 17 Lexington Avenue | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Mar 2027 | Apr 2029
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA025-018 | Marxe Lab/Public Space Upgrades for School of Public Affairs | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jul 2021 | Sep 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA025-018 | Marxe Lab/Public Space Upgrades for School of Public Affairs | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA025-018 | Marxe Lab/Public Space Upgrades for School of Public Affairs | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA025-018 | Marxe Lab/Public Space Upgrades for School of Public Affairs | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA025-018 | Marxe Lab/Public Space Upgrades for School of Public Affairs | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA025-018 | Marxe Lab/Public Space Upgrades for School of Public Affairs | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA025-018 | Marxe Lab/Public Space Upgrades for School of Public Affairs | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA025-018 | Marxe Lab/Public Space Upgrades for School of Public Affairs | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA025-018 | Marxe Lab/Public Space Upgrades for School of Public Affairs | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA025-018 | Marxe Lab/Public Space Upgrades for School of Public Affairs | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Mar 2024 | Apr 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA030-020 | Mason Hall A/V System | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA030-020 | Mason Hall A/V System | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA030-020 | Mason Hall A/V System | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA030-020 | Mason Hall A/V System | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA030-020 | Mason Hall A/V System | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA030-020 | Mason Hall A/V System | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA030-020 | Mason Hall A/V System | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA030-020 | Mason Hall A/V System | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA030-020 | Mason Hall A/V System | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2023 | Mar 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | BA030-020 | Mason Hall A/V System | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2023 | Apr 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-021 | SLUS - Facility Upgrades | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-021 | SLUS - Facility Upgrades | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-021 | SLUS - Facility Upgrades | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-021 | SLUS - Facility Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-021 | SLUS - Facility Upgrades | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-021 | SLUS - Facility Upgrades | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-021 | SLUS - Facility Upgrades | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-021 | SLUS - Facility Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-021 | SLUS - Facility Upgrades | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-021 | SLUS - Facility Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-023 | EXPANSION OF SLU CLASSROOM SPACE AND CREATION OF LABOR MUSEU | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-023 | EXPANSION OF SLU CLASSROOM SPACE AND CREATION OF LABOR MUSEU | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-023 | EXPANSION OF SLU CLASSROOM SPACE AND CREATION OF LABOR MUSEU | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-023 | EXPANSION OF SLU CLASSROOM SPACE AND CREATION OF LABOR MUSEU | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-023 | EXPANSION OF SLU CLASSROOM SPACE AND CREATION OF LABOR MUSEU | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-023 | EXPANSION OF SLU CLASSROOM SPACE AND CREATION OF LABOR MUSEU | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-023 | EXPANSION OF SLU CLASSROOM SPACE AND CREATION OF LABOR MUSEU | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-023 | EXPANSION OF SLU CLASSROOM SPACE AND CREATION OF LABOR MUSEU | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-023 | EXPANSION OF SLU CLASSROOM SPACE AND CREATION OF LABOR MUSEU | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-023 | EXPANSION OF SLU CLASSROOM SPACE AND CREATION OF LABOR MUSEU | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA002-021 | SPS - Virtual Online Desktop - Informatics & Data Analytics | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA002-021 | SPS - Virtual Online Desktop - Informatics & Data Analytics | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA002-021 | SPS - Virtual Online Desktop - Informatics & Data Analytics | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA002-021 | SPS - Virtual Online Desktop - Informatics & Data Analytics | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA002-021 | SPS - Virtual Online Desktop - Informatics & Data Analytics | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA002-021 | SPS - Virtual Online Desktop - Informatics & Data Analytics | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA002-021 | SPS - Virtual Online Desktop - Informatics & Data Analytics | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA002-021 | SPS - Virtual Online Desktop - Informatics & Data Analytics | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA002-021 | SPS - Virtual Online Desktop - Informatics & Data Analytics | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA002-021 | SPS - Virtual Online Desktop - Informatics & Data Analytics | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-021 | Critical Maintenance | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-021 | Critical Maintenance | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-021 | Critical Maintenance | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-021 | Critical Maintenance | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-021 | Critical Maintenance | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-021 | Critical Maintenance | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-021 | Critical Maintenance | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-021 | Critical Maintenance | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-021 | Critical Maintenance | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-021 | Critical Maintenance | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2032
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-023 | Restroom Renovations | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-023 | Restroom Renovations | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-023 | Restroom Renovations | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-023 | Restroom Renovations | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-023 | Restroom Renovations | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-023 | Restroom Renovations | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-023 | Restroom Renovations | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-023 | Restroom Renovations | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-023 | Restroom Renovations | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-023 | Restroom Renovations | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2029
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-021 | CUNY STEM Institute | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2025 | Sep 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-021 | CUNY STEM Institute | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2025 | Jan 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-021 | CUNY STEM Institute | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2026 | Jul 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-021 | CUNY STEM Institute | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2026 | Oct 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-021 | CUNY STEM Institute | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2026 | Feb 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-021 | CUNY STEM Institute | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2027 | Jun 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-021 | CUNY STEM Institute | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2027 | Oct 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-021 | CUNY STEM Institute | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2027 | Jan 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-021 | CUNY STEM Institute | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2028 | Mar 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-021 | CUNY STEM Institute | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2028 | Apr 2030
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-023 | Workspace Expansion & Welcome Center Relocation | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-023 | Workspace Expansion & Welcome Center Relocation | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-023 | Workspace Expansion & Welcome Center Relocation | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-023 | Workspace Expansion & Welcome Center Relocation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-023 | Workspace Expansion & Welcome Center Relocation | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-023 | Workspace Expansion & Welcome Center Relocation | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-023 | Workspace Expansion & Welcome Center Relocation | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-023 | Workspace Expansion & Welcome Center Relocation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-023 | Workspace Expansion & Welcome Center Relocation | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-023 | Workspace Expansion & Welcome Center Relocation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-021 | CUNY SPH Renovation | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-021 | CUNY SPH Renovation | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-021 | CUNY SPH Renovation | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-021 | CUNY SPH Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-021 | CUNY SPH Renovation | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-021 | CUNY SPH Renovation | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-021 | CUNY SPH Renovation | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-021 | CUNY SPH Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-021 | CUNY SPH Renovation | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-021 | CUNY SPH Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-022 | SPH Expansion and Renovation | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-022 | SPH Expansion and Renovation | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-022 | SPH Expansion and Renovation | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-022 | SPH Expansion and Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-022 | SPH Expansion and Renovation | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-022 | SPH Expansion and Renovation | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-022 | SPH Expansion and Renovation | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-022 | SPH Expansion and Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-022 | SPH Expansion and Renovation | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-022 | SPH Expansion and Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA006-022 | SLUS- Classroom Spaces Upgrade | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA006-022 | SLUS- Classroom Spaces Upgrade | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA006-022 | SLUS- Classroom Spaces Upgrade | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA006-022 | SLUS- Classroom Spaces Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA006-022 | SLUS- Classroom Spaces Upgrade | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA006-022 | SLUS- Classroom Spaces Upgrade | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA006-022 | SLUS- Classroom Spaces Upgrade | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA006-022 | SLUS- Classroom Spaces Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA006-022 | SLUS- Classroom Spaces Upgrade | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA006-022 | SLUS- Classroom Spaces Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA007-022 | SPS- Workspace Expansion and Welcome Center | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA007-022 | SPS- Workspace Expansion and Welcome Center | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA007-022 | SPS- Workspace Expansion and Welcome Center | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA007-022 | SPS- Workspace Expansion and Welcome Center | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA007-022 | SPS- Workspace Expansion and Welcome Center | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA007-022 | SPS- Workspace Expansion and Welcome Center | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA007-022 | SPS- Workspace Expansion and Welcome Center | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA007-022 | SPS- Workspace Expansion and Welcome Center | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA007-022 | SPS- Workspace Expansion and Welcome Center | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA007-022 | SPS- Workspace Expansion and Welcome Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA013-008 | WEB VIDEO SYSTEMS FOR HANDICAPPED STUDENTS, CUNYWIDE | 1 | DEVELOP SCOPE | Jun 2010 | Aug 2010 | Jun 2010 | Aug 2010
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA013-008 | WEB VIDEO SYSTEMS FOR HANDICAPPED STUDENTS, CUNYWIDE | 2 | PRELIMINARY DESIGN | Aug 2010 | Dec 2010 | Aug 2010 | Dec 2010
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA013-008 | WEB VIDEO SYSTEMS FOR HANDICAPPED STUDENTS, CUNYWIDE | 3 | FINAL DESIGN | Dec 2010 | Jun 2011 | Dec 2010 | Jun 2011
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA013-008 | WEB VIDEO SYSTEMS FOR HANDICAPPED STUDENTS, CUNYWIDE | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2011 | Sep 2011 | Jun 2011 | Sep 2011
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA013-008 | WEB VIDEO SYSTEMS FOR HANDICAPPED STUDENTS, CUNYWIDE | 5 | CONSTRUCTION TO 25% | Sep 2011 | Jan 2012 | Sep 2011 | Jan 2012
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA013-008 | WEB VIDEO SYSTEMS FOR HANDICAPPED STUDENTS, CUNYWIDE | 6 | CONSTRUCTION TO 50% | Jan 2012 | May 2012 | Jan 2012 | May 2012
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA013-008 | WEB VIDEO SYSTEMS FOR HANDICAPPED STUDENTS, CUNYWIDE | 7 | CONSTRUCTION TO 75% | May 2012 | Sep 2012 | May 2012 | Sep 2012
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA013-008 | WEB VIDEO SYSTEMS FOR HANDICAPPED STUDENTS, CUNYWIDE | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2012 | Dec 2012 | Sep 2012 | Dec 2012
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA013-008 | WEB VIDEO SYSTEMS FOR HANDICAPPED STUDENTS, CUNYWIDE | 9 | SUBSTANTIAL COMPLETION | Dec 2012 | Feb 2013 | Dec 2012 | Feb 2013
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA013-008 | WEB VIDEO SYSTEMS FOR HANDICAPPED STUDENTS, CUNYWIDE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2013 | Mar 2013 | Feb 2013 | Mar 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA032-013 | Center for Innovation and Entrepreneurship | 1 | DEVELOP SCOPE | Jun 2013 | Aug 2013 | Jun 2013 | Aug 2013
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA032-013 | Center for Innovation and Entrepreneurship | 2 | PRELIMINARY DESIGN | Aug 2013 | Dec 2013 | Aug 2013 | Dec 2013
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA032-013 | Center for Innovation and Entrepreneurship | 3 | FINAL DESIGN | Dec 2013 | Jun 2014 | Dec 2013 | Jun 2014
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA032-013 | Center for Innovation and Entrepreneurship | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2014 | Sep 2014 | Jun 2014 | Sep 2014
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA032-013 | Center for Innovation and Entrepreneurship | 5 | CONSTRUCTION TO 25% | Sep 2014 | Jan 2015 | Sep 2014 | Jan 2015
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA032-013 | Center for Innovation and Entrepreneurship | 6 | CONSTRUCTION TO 50% | Jan 2015 | May 2015 | Jan 2015 | May 2015
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA032-013 | Center for Innovation and Entrepreneurship | 7 | CONSTRUCTION TO 75% | May 2015 | Sep 2015 | May 2015 | Sep 2015
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA032-013 | Center for Innovation and Entrepreneurship | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA032-013 | Center for Innovation and Entrepreneurship | 9 | SUBSTANTIAL COMPLETION | Dec 2015 | Feb 2016 | Dec 2015 | Feb 2016
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA032-013 | Center for Innovation and Entrepreneurship | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2016 | Mar 2016 | Feb 2016 | Mar 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-019 | CUNY In The Heights | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jun 2019 | Sep 2019
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-019 | CUNY In The Heights | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Sep 2019 | Jan 2020
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-019 | CUNY In The Heights | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2020 | Jul 2020
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-019 | CUNY In The Heights | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2020 | Oct 2020
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-019 | CUNY In The Heights | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2020 | Feb 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-019 | CUNY In The Heights | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2021 | Jun 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-019 | CUNY In The Heights | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2021 | Oct 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-019 | CUNY In The Heights | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-019 | CUNY In The Heights | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2022 | Mar 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-019 | CUNY In The Heights | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2022 | Jun 2031
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-022 | CUNY in the Heights -Media Room Construction/Renovation | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-022 | CUNY in the Heights -Media Room Construction/Renovation | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-022 | CUNY in the Heights -Media Room Construction/Renovation | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-022 | CUNY in the Heights -Media Room Construction/Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-022 | CUNY in the Heights -Media Room Construction/Renovation | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-022 | CUNY in the Heights -Media Room Construction/Renovation | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-022 | CUNY in the Heights -Media Room Construction/Renovation | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-022 | CUNY in the Heights -Media Room Construction/Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-022 | CUNY in the Heights -Media Room Construction/Renovation | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-022 | CUNY in the Heights -Media Room Construction/Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA056-020 | John Jay School of Law | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA056-020 | John Jay School of Law | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA056-020 | John Jay School of Law | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA056-020 | John Jay School of Law | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA056-020 | John Jay School of Law | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA056-020 | John Jay School of Law | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA056-020 | John Jay School of Law | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA056-020 | John Jay School of Law | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA056-020 | John Jay School of Law | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2023 | Mar 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA056-020 | John Jay School of Law | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2023 | Apr 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA092-024 | Health, Safety and ADA Projects Health, Safety and ADA Proje | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2024 | Jun 2023 | Sep 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA092-024 | Health, Safety and ADA Projects Health, Safety and ADA Proje | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA092-024 | Health, Safety and ADA Projects Health, Safety and ADA Proje | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA092-024 | Health, Safety and ADA Projects Health, Safety and ADA Proje | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA092-024 | Health, Safety and ADA Projects Health, Safety and ADA Proje | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA092-024 | Health, Safety and ADA Projects Health, Safety and ADA Proje | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA092-024 | Health, Safety and ADA Projects Health, Safety and ADA Proje | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA092-024 | Health, Safety and ADA Projects Health, Safety and ADA Proje | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA092-024 | Health, Safety and ADA Projects Health, Safety and ADA Proje | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA092-024 | Health, Safety and ADA Projects Health, Safety and ADA Proje | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA200CW21 | REPLACE 109 ELEVATOR DOORS AT SIX COMMUNITY COLLEGES | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA200CW21 | REPLACE 109 ELEVATOR DOORS AT SIX COMMUNITY COLLEGES | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA200CW21 | REPLACE 109 ELEVATOR DOORS AT SIX COMMUNITY COLLEGES | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA200CW21 | REPLACE 109 ELEVATOR DOORS AT SIX COMMUNITY COLLEGES | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA200CW21 | REPLACE 109 ELEVATOR DOORS AT SIX COMMUNITY COLLEGES | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA200CW21 | REPLACE 109 ELEVATOR DOORS AT SIX COMMUNITY COLLEGES | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA200CW21 | REPLACE 109 ELEVATOR DOORS AT SIX COMMUNITY COLLEGES | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA200CW21 | REPLACE 109 ELEVATOR DOORS AT SIX COMMUNITY COLLEGES | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA200CW21 | REPLACE 109 ELEVATOR DOORS AT SIX COMMUNITY COLLEGES | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA200CW21 | REPLACE 109 ELEVATOR DOORS AT SIX COMMUNITY COLLEGES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA201MC04 | BMCC RAMP & PLAZA PEDESTAL REPAIRS | 1 | DEVELOP SCOPE | Jun 2009 | Aug 2009 | Jun 2009 | Aug 2009
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA201MC04 | BMCC RAMP & PLAZA PEDESTAL REPAIRS | 2 | PRELIMINARY DESIGN | Aug 2009 | Dec 2009 | Aug 2009 | Dec 2009
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA201MC04 | BMCC RAMP & PLAZA PEDESTAL REPAIRS | 3 | FINAL DESIGN | Dec 2009 | Jun 2010 | Dec 2009 | Jun 2010
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA201MC04 | BMCC RAMP & PLAZA PEDESTAL REPAIRS | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2010 | Sep 2010 | Jun 2010 | Sep 2010
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA201MC04 | BMCC RAMP & PLAZA PEDESTAL REPAIRS | 5 | CONSTRUCTION TO 25% | Sep 2010 | Jan 2011 | Sep 2010 | Jan 2011
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA201MC04 | BMCC RAMP & PLAZA PEDESTAL REPAIRS | 6 | CONSTRUCTION TO 50% | Jan 2011 | May 2011 | Jan 2011 | May 2011
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA201MC04 | BMCC RAMP & PLAZA PEDESTAL REPAIRS | 7 | CONSTRUCTION TO 75% | May 2011 | Sep 2011 | May 2011 | Sep 2011
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA201MC04 | BMCC RAMP & PLAZA PEDESTAL REPAIRS | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2011 | Dec 2011 | Sep 2011 | Dec 2011
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA201MC04 | BMCC RAMP & PLAZA PEDESTAL REPAIRS | 9 | SUBSTANTIAL COMPLETION | Dec 2011 | Feb 2012 | Dec 2011 | Feb 2012
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA201MC04 | BMCC RAMP & PLAZA PEDESTAL REPAIRS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2012 | Mar 2012 | Feb 2012 | Jun 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA202MC01 | ADA BATHROOM UPGRADES FOR BMCC | 1 | DEVELOP SCOPE | Jun 2009 | Aug 2009 | Jun 2009 | Aug 2009
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA202MC01 | ADA BATHROOM UPGRADES FOR BMCC | 2 | PRELIMINARY DESIGN | Aug 2009 | Dec 2009 | Aug 2009 | Dec 2009
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA202MC01 | ADA BATHROOM UPGRADES FOR BMCC | 3 | FINAL DESIGN | Dec 2009 | Jun 2010 | Dec 2009 | Jun 2010
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA202MC01 | ADA BATHROOM UPGRADES FOR BMCC | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2010 | Sep 2010 | Jun 2010 | Sep 2010
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA202MC01 | ADA BATHROOM UPGRADES FOR BMCC | 5 | CONSTRUCTION TO 25% | Sep 2010 | Jan 2011 | Sep 2010 | Jan 2011
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA202MC01 | ADA BATHROOM UPGRADES FOR BMCC | 6 | CONSTRUCTION TO 50% | Jan 2011 | May 2011 | Jan 2011 | May 2011
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA202MC01 | ADA BATHROOM UPGRADES FOR BMCC | 7 | CONSTRUCTION TO 75% | May 2011 | Sep 2011 | May 2011 | Sep 2011
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA202MC01 | ADA BATHROOM UPGRADES FOR BMCC | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2011 | Dec 2011 | Sep 2011 | Dec 2011
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA202MC01 | ADA BATHROOM UPGRADES FOR BMCC | 9 | SUBSTANTIAL COMPLETION | Dec 2011 | Feb 2012 | Dec 2011 | Feb 2012
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CA202MC01 | ADA BATHROOM UPGRADES FOR BMCC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2012 | Mar 2012 | Feb 2012 | Mar 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC001-022 | Student Disability Center | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC001-022 | Student Disability Center | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC001-022 | Student Disability Center | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC001-022 | Student Disability Center | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC001-022 | Student Disability Center | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC001-022 | Student Disability Center | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC001-022 | Student Disability Center | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC001-022 | Student Disability Center | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC001-022 | Student Disability Center | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC001-022 | Student Disability Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC001-024 | MOYNIHAN CENTER UPGRADE OF FACILITY SPACE | 1 | DEVELOP SCOPE | Jul 2023 | Sep 2024 | Jul 2023 | Sep 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC001-024 | MOYNIHAN CENTER UPGRADE OF FACILITY SPACE | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC001-024 | MOYNIHAN CENTER UPGRADE OF FACILITY SPACE | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC001-024 | MOYNIHAN CENTER UPGRADE OF FACILITY SPACE | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC001-024 | MOYNIHAN CENTER UPGRADE OF FACILITY SPACE | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC001-024 | MOYNIHAN CENTER UPGRADE OF FACILITY SPACE | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC001-024 | MOYNIHAN CENTER UPGRADE OF FACILITY SPACE | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC001-024 | MOYNIHAN CENTER UPGRADE OF FACILITY SPACE | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC001-024 | MOYNIHAN CENTER UPGRADE OF FACILITY SPACE | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC001-024 | MOYNIHAN CENTER UPGRADE OF FACILITY SPACE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC022-012 | Schiff House Day Care Center Upgrades | 1 | DEVELOP SCOPE | Jun 2012 | Aug 2012 | Jun 2012 | Aug 2012
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC022-012 | Schiff House Day Care Center Upgrades | 2 | PRELIMINARY DESIGN | Aug 2012 | Dec 2012 | Aug 2012 | Dec 2012
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC022-012 | Schiff House Day Care Center Upgrades | 3 | FINAL DESIGN | Dec 2012 | Jun 2013 | Dec 2012 | Jun 2013
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC022-012 | Schiff House Day Care Center Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2013 | Sep 2013 | Jun 2013 | Sep 2013
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC022-012 | Schiff House Day Care Center Upgrades | 5 | CONSTRUCTION TO 25% | Sep 2013 | Jan 2014 | Sep 2013 | Jan 2014
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC022-012 | Schiff House Day Care Center Upgrades | 6 | CONSTRUCTION TO 50% | Jan 2014 | May 2014 | Jan 2014 | May 2014
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC022-012 | Schiff House Day Care Center Upgrades | 7 | CONSTRUCTION TO 75% | May 2014 | Sep 2014 | May 2014 | Sep 2014
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC022-012 | Schiff House Day Care Center Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC022-012 | Schiff House Day Care Center Upgrades | 9 | SUBSTANTIAL COMPLETION | Dec 2014 | Feb 2015 | Dec 2014 | Feb 2015
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC022-012 | Schiff House Day Care Center Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2015 | Mar 2015 | Feb 2015 | Mar 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC026-013 | Aaron Davis Hall | 1 | DEVELOP SCOPE | Jun 2013 | Aug 2013 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC026-013 | Aaron Davis Hall | 2 | PRELIMINARY DESIGN | Aug 2013 | Dec 2013 | Oct 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC026-013 | Aaron Davis Hall | 3 | FINAL DESIGN | Dec 2013 | Jun 2014 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC026-013 | Aaron Davis Hall | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2014 | Sep 2014 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC026-013 | Aaron Davis Hall | 5 | CONSTRUCTION TO 25% | Sep 2014 | Jan 2015 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC026-013 | Aaron Davis Hall | 6 | CONSTRUCTION TO 50% | Jan 2015 | May 2015 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC026-013 | Aaron Davis Hall | 7 | CONSTRUCTION TO 75% | May 2015 | Sep 2015 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC026-013 | Aaron Davis Hall | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2015 | Dec 2015 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC026-013 | Aaron Davis Hall | 9 | SUBSTANTIAL COMPLETION | Dec 2015 | Feb 2016 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC026-013 | Aaron Davis Hall | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2016 | Mar 2016 | May 2025 | Aug 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC032-015 | City College Computer Lab | 1 | DEVELOP SCOPE | Mar 2015 | May 2015 | Mar 2015 | May 2015
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC032-015 | City College Computer Lab | 2 | PRELIMINARY DESIGN | May 2015 | Sep 2015 | May 2015 | Sep 2015
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC032-015 | City College Computer Lab | 3 | FINAL DESIGN | Sep 2015 | Mar 2016 | Sep 2015 | Mar 2016
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC032-015 | City College Computer Lab | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2016 | Jun 2016 | Mar 2016 | Jun 2016
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC032-015 | City College Computer Lab | 5 | CONSTRUCTION TO 25% | Jun 2016 | Oct 2016 | Jun 2016 | Oct 2016
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC032-015 | City College Computer Lab | 6 | CONSTRUCTION TO 50% | Oct 2016 | Feb 2017 | Oct 2016 | Feb 2017
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC032-015 | City College Computer Lab | 7 | CONSTRUCTION TO 75% | Feb 2017 | Jun 2017 | Feb 2017 | Jun 2017
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC032-015 | City College Computer Lab | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2017 | Sep 2017 | Jun 2017 | Sep 2017
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC032-015 | City College Computer Lab | 9 | SUBSTANTIAL COMPLETION | Sep 2017 | Nov 2017 | Sep 2017 | Nov 2017
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC032-015 | City College Computer Lab | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | Dec 2017 | Nov 2017 | Dec 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC034-016 | Computer Lab Renovation | 1 | DEVELOP SCOPE | Jun 2015 | Aug 2015 | Jun 2015 | Aug 2015
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC034-016 | Computer Lab Renovation | 2 | PRELIMINARY DESIGN | Aug 2015 | Dec 2015 | Aug 2015 | Dec 2015
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC034-016 | Computer Lab Renovation | 3 | FINAL DESIGN | Dec 2015 | Jun 2016 | Dec 2015 | Jun 2016
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC034-016 | Computer Lab Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2016 | Sep 2016 | Jun 2016 | Sep 2016
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC034-016 | Computer Lab Renovation | 5 | CONSTRUCTION TO 25% | Sep 2016 | Jan 2017 | Sep 2016 | Jan 2017
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC034-016 | Computer Lab Renovation | 6 | CONSTRUCTION TO 50% | Jan 2017 | May 2017 | Jan 2017 | May 2017
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC034-016 | Computer Lab Renovation | 7 | CONSTRUCTION TO 75% | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC034-016 | Computer Lab Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Dec 2017 | Sep 2017 | Dec 2017
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC034-016 | Computer Lab Renovation | 9 | SUBSTANTIAL COMPLETION | Dec 2017 | Feb 2018 | Dec 2017 | Feb 2018
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC034-016 | Computer Lab Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2018 | Mar 2018 | Feb 2018 | Mar 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC037-017 | Harlem Rooftop Garden | 1 | DEVELOP SCOPE | Jun 2017 | Aug 2017 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC037-017 | Harlem Rooftop Garden | 2 | PRELIMINARY DESIGN | Aug 2017 | Dec 2017 | Oct 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC037-017 | Harlem Rooftop Garden | 3 | FINAL DESIGN | Dec 2017 | Jun 2018 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC037-017 | Harlem Rooftop Garden | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Sep 2018 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC037-017 | Harlem Rooftop Garden | 5 | CONSTRUCTION TO 25% | Sep 2018 | Jan 2019 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC037-017 | Harlem Rooftop Garden | 6 | CONSTRUCTION TO 50% | Jan 2019 | May 2019 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC037-017 | Harlem Rooftop Garden | 7 | CONSTRUCTION TO 75% | May 2019 | Sep 2019 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC037-017 | Harlem Rooftop Garden | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Dec 2019 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC037-017 | Harlem Rooftop Garden | 9 | SUBSTANTIAL COMPLETION | Dec 2019 | Feb 2020 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC037-017 | Harlem Rooftop Garden | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2020 | Mar 2020 | Mar 2024 | May 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC039-017 | Street Improvements | 1 | DEVELOP SCOPE | Jun 2017 | Aug 2017 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC039-017 | Street Improvements | 2 | PRELIMINARY DESIGN | Aug 2017 | Dec 2017 | Oct 2022 | Jan 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC039-017 | Street Improvements | 3 | FINAL DESIGN | Dec 2017 | Jun 2018 | Jan 2023 | Jul 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC039-017 | Street Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Sep 2018 | Jul 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC039-017 | Street Improvements | 5 | CONSTRUCTION TO 25% | Sep 2018 | Jan 2019 | Oct 2023 | Feb 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC039-017 | Street Improvements | 6 | CONSTRUCTION TO 50% | Jan 2019 | May 2019 | Feb 2024 | Jun 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC039-017 | Street Improvements | 7 | CONSTRUCTION TO 75% | May 2019 | Sep 2019 | Jun 2024 | Oct 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC039-017 | Street Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Dec 2019 | Oct 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC039-017 | Street Improvements | 9 | SUBSTANTIAL COMPLETION | Dec 2019 | Feb 2020 | Jan 2025 | Mar 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC039-017 | Street Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2020 | Mar 2020 | Mar 2025 | May 2029
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC041-018 | Wireless Network Upgrade Expansion | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jun 2018 | Aug 2018
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC041-018 | Wireless Network Upgrade Expansion | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Aug 2018 | Dec 2018
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC041-018 | Wireless Network Upgrade Expansion | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Dec 2018 | Jun 2019
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC041-018 | Wireless Network Upgrade Expansion | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC041-018 | Wireless Network Upgrade Expansion | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC041-018 | Wireless Network Upgrade Expansion | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Jan 2020 | May 2020
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC041-018 | Wireless Network Upgrade Expansion | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | May 2020 | Sep 2020
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC041-018 | Wireless Network Upgrade Expansion | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Sep 2020 | Dec 2020
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC041-018 | Wireless Network Upgrade Expansion | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Dec 2020 | Feb 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC041-018 | Wireless Network Upgrade Expansion | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Feb 2021 | Mar 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC042-018 | Facility Upgrades | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC042-018 | Facility Upgrades | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Oct 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC042-018 | Facility Upgrades | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC042-018 | Facility Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC042-018 | Facility Upgrades | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC042-018 | Facility Upgrades | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC042-018 | Facility Upgrades | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC042-018 | Facility Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC042-018 | Facility Upgrades | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC042-018 | Facility Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Mar 2024 | May 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC045-019 | Kitchen Upgrade for the Culinary Program | 1 | DEVELOP SCOPE | Jun 2019 | Aug 2019 | Jul 2020 | Oct 2020
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC045-019 | Kitchen Upgrade for the Culinary Program | 2 | PRELIMINARY DESIGN | Aug 2019 | Dec 2019 | Oct 2020 | Jan 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC045-019 | Kitchen Upgrade for the Culinary Program | 3 | FINAL DESIGN | Dec 2019 | Jun 2020 | Jan 2021 | Jul 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC045-019 | Kitchen Upgrade for the Culinary Program | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Sep 2020 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC045-019 | Kitchen Upgrade for the Culinary Program | 5 | CONSTRUCTION TO 25% | Sep 2020 | Jan 2021 | Oct 2021 | Feb 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC045-019 | Kitchen Upgrade for the Culinary Program | 6 | CONSTRUCTION TO 50% | Jan 2021 | May 2021 | Feb 2022 | Jun 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC045-019 | Kitchen Upgrade for the Culinary Program | 7 | CONSTRUCTION TO 75% | May 2021 | Sep 2021 | Jun 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC045-019 | Kitchen Upgrade for the Culinary Program | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Dec 2021 | Oct 2022 | Jan 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC045-019 | Kitchen Upgrade for the Culinary Program | 9 | SUBSTANTIAL COMPLETION | Dec 2021 | Feb 2022 | Jan 2023 | Mar 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | CC045-019 | Kitchen Upgrade for the Culinary Program | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2022 | Mar 2022 | Mar 2023 | Apr 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR010-022 | Recital Hall & Theater Upgrades | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR010-022 | Recital Hall & Theater Upgrades | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR010-022 | Recital Hall & Theater Upgrades | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR010-022 | Recital Hall & Theater Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR010-022 | Recital Hall & Theater Upgrades | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR010-022 | Recital Hall & Theater Upgrades | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR010-022 | Recital Hall & Theater Upgrades | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR010-022 | Recital Hall & Theater Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR010-022 | Recital Hall & Theater Upgrades | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR010-022 | Recital Hall & Theater Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2031
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR017-014 | Bathroom and HVAC Upgrades | 1 | DEVELOP SCOPE | Jun 2014 | Aug 2014 | Jun 2014 | Aug 2014
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR017-014 | Bathroom and HVAC Upgrades | 2 | PRELIMINARY DESIGN | Aug 2014 | Dec 2014 | Aug 2014 | Dec 2014
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR017-014 | Bathroom and HVAC Upgrades | 3 | FINAL DESIGN | Dec 2014 | Jun 2015 | Dec 2014 | Jun 2015
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR017-014 | Bathroom and HVAC Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2015 | Sep 2015 | Jun 2015 | Sep 2015
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR017-014 | Bathroom and HVAC Upgrades | 5 | CONSTRUCTION TO 25% | Sep 2015 | Jan 2016 | Sep 2015 | Jan 2016
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR017-014 | Bathroom and HVAC Upgrades | 6 | CONSTRUCTION TO 50% | Jan 2016 | May 2016 | Jan 2016 | May 2016
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR017-014 | Bathroom and HVAC Upgrades | 7 | CONSTRUCTION TO 75% | May 2016 | Sep 2016 | May 2016 | Sep 2016
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR017-014 | Bathroom and HVAC Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Dec 2016 | Sep 2016 | Dec 2016
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR017-014 | Bathroom and HVAC Upgrades | 9 | SUBSTANTIAL COMPLETION | Dec 2016 | Feb 2017 | Dec 2016 | Feb 2017
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR017-014 | Bathroom and HVAC Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2017 | Mar 2017 | Feb 2017 | Mar 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR018-015 | Library Renovations | 1 | DEVELOP SCOPE | Oct 2014 | Dec 2014 | Jul 2020 | Oct 2020
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR018-015 | Library Renovations | 2 | PRELIMINARY DESIGN | Dec 2014 | Apr 2015 | Oct 2020 | Jan 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR018-015 | Library Renovations | 3 | FINAL DESIGN | Apr 2015 | Oct 2015 | Jan 2021 | Jul 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR018-015 | Library Renovations | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2015 | Jan 2016 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR018-015 | Library Renovations | 5 | CONSTRUCTION TO 25% | Jan 2016 | May 2016 | Oct 2021 | Feb 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR018-015 | Library Renovations | 6 | CONSTRUCTION TO 50% | May 2016 | Sep 2016 | Feb 2022 | Jun 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR018-015 | Library Renovations | 7 | CONSTRUCTION TO 75% | Sep 2016 | Jan 2017 | Jun 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR018-015 | Library Renovations | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2017 | Apr 2017 | Oct 2022 | Jan 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR018-015 | Library Renovations | 9 | SUBSTANTIAL COMPLETION | Apr 2017 | Jun 2017 | Jan 2023 | Mar 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR018-015 | Library Renovations | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2017 | Jul 2017 | Mar 2023 | May 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR022-017 | Ninth Floor Reconstruction | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR022-017 | Ninth Floor Reconstruction | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR022-017 | Ninth Floor Reconstruction | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR022-017 | Ninth Floor Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR022-017 | Ninth Floor Reconstruction | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR022-017 | Ninth Floor Reconstruction | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR022-017 | Ninth Floor Reconstruction | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR022-017 | Ninth Floor Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR022-017 | Ninth Floor Reconstruction | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR022-017 | Ninth Floor Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR023-017 | Improvement of Public Spaces | 1 | DEVELOP SCOPE | Jun 2017 | Aug 2017 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR023-017 | Improvement of Public Spaces | 2 | PRELIMINARY DESIGN | Aug 2017 | Dec 2017 | Oct 2022 | Jan 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR023-017 | Improvement of Public Spaces | 3 | FINAL DESIGN | Dec 2017 | Jun 2018 | Jan 2023 | Jul 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR023-017 | Improvement of Public Spaces | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Sep 2018 | Jul 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR023-017 | Improvement of Public Spaces | 5 | CONSTRUCTION TO 25% | Sep 2018 | Jan 2019 | Oct 2023 | Feb 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR023-017 | Improvement of Public Spaces | 6 | CONSTRUCTION TO 50% | Jan 2019 | May 2019 | Feb 2024 | Jun 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR023-017 | Improvement of Public Spaces | 7 | CONSTRUCTION TO 75% | May 2019 | Sep 2019 | Jun 2024 | Oct 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR023-017 | Improvement of Public Spaces | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Dec 2019 | Oct 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR023-017 | Improvement of Public Spaces | 9 | SUBSTANTIAL COMPLETION | Dec 2019 | Feb 2020 | Jan 2025 | Mar 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR023-017 | Improvement of Public Spaces | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2020 | Mar 2020 | Mar 2025 | May 2030
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR029-020 | AUDITORIUM SOUND SYSTEM | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR029-020 | AUDITORIUM SOUND SYSTEM | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR029-020 | AUDITORIUM SOUND SYSTEM | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR029-020 | AUDITORIUM SOUND SYSTEM | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR029-020 | AUDITORIUM SOUND SYSTEM | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR029-020 | AUDITORIUM SOUND SYSTEM | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR029-020 | AUDITORIUM SOUND SYSTEM | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR029-020 | AUDITORIUM SOUND SYSTEM | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR029-020 | AUDITORIUM SOUND SYSTEM | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2023 | Mar 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GR029-020 | AUDITORIUM SOUND SYSTEM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2023 | Apr 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GU001-012 | Space Conversion | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2024 | Jun 2023 | Sep 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GU001-012 | Space Conversion | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GU001-012 | Space Conversion | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GU001-012 | Space Conversion | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GU001-012 | Space Conversion | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GU001-012 | Space Conversion | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GU001-012 | Space Conversion | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GU001-012 | Space Conversion | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GU001-012 | Space Conversion | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GU001-012 | Space Conversion | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GU031-013 | New Community College Student Lab Renovations | 1 | DEVELOP SCOPE | Jun 2013 | Aug 2013 | Jul 2022 | Sep 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GU031-013 | New Community College Student Lab Renovations | 2 | PRELIMINARY DESIGN | Aug 2013 | Dec 2013 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GU031-013 | New Community College Student Lab Renovations | 3 | FINAL DESIGN | Dec 2013 | Jun 2014 | Jan 2023 | Jul 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GU031-013 | New Community College Student Lab Renovations | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2014 | Sep 2014 | Jul 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GU031-013 | New Community College Student Lab Renovations | 5 | CONSTRUCTION TO 25% | Sep 2014 | Jan 2015 | Oct 2023 | Feb 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GU031-013 | New Community College Student Lab Renovations | 6 | CONSTRUCTION TO 50% | Jan 2015 | May 2015 | Feb 2024 | Jun 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GU031-013 | New Community College Student Lab Renovations | 7 | CONSTRUCTION TO 75% | May 2015 | Sep 2015 | Jun 2024 | Oct 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GU031-013 | New Community College Student Lab Renovations | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2015 | Dec 2015 | Oct 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GU031-013 | New Community College Student Lab Renovations | 9 | SUBSTANTIAL COMPLETION | Dec 2015 | Feb 2016 | Jan 2025 | Mar 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GU031-013 | New Community College Student Lab Renovations | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2016 | Mar 2016 | Mar 2025 | Apr 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GU051-015 | Guttman Comm. Coll. Building Canopy | 1 | DEVELOP SCOPE | Oct 2014 | Dec 2014 | Oct 2014 | Dec 2014
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GU051-015 | Guttman Comm. Coll. Building Canopy | 2 | PRELIMINARY DESIGN | Dec 2014 | Apr 2015 | Dec 2014 | Apr 2015
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GU051-015 | Guttman Comm. Coll. Building Canopy | 3 | FINAL DESIGN | Apr 2015 | Oct 2015 | Apr 2015 | Oct 2015
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GU051-015 | Guttman Comm. Coll. Building Canopy | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2015 | Jan 2016 | Oct 2015 | Jan 2016
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GU051-015 | Guttman Comm. Coll. Building Canopy | 5 | CONSTRUCTION TO 25% | Jan 2016 | May 2016 | Jan 2016 | May 2016
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GU051-015 | Guttman Comm. Coll. Building Canopy | 6 | CONSTRUCTION TO 50% | May 2016 | Sep 2016 | May 2016 | Sep 2016
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GU051-015 | Guttman Comm. Coll. Building Canopy | 7 | CONSTRUCTION TO 75% | Sep 2016 | Jan 2017 | Sep 2016 | Jan 2017
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GU051-015 | Guttman Comm. Coll. Building Canopy | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2017 | Apr 2017 | Jan 2017 | Apr 2017
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GU051-015 | Guttman Comm. Coll. Building Canopy | 9 | SUBSTANTIAL COMPLETION | Apr 2017 | Jun 2017 | Apr 2017 | Jun 2017
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | GU051-015 | Guttman Comm. Coll. Building Canopy | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2017 | Jul 2017 | Jun 2017 | Jul 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC001-021 | Athletic Facility Renovation | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC001-021 | Athletic Facility Renovation | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC001-021 | Athletic Facility Renovation | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC001-021 | Athletic Facility Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC001-021 | Athletic Facility Renovation | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC001-021 | Athletic Facility Renovation | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC001-021 | Athletic Facility Renovation | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC001-021 | Athletic Facility Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC001-021 | Athletic Facility Renovation | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC001-021 | Athletic Facility Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC002-024 | Playground Renovation | 1 | DEVELOP SCOPE | Jun 2025 | Sep 2026 | Jun 2025 | Sep 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC002-024 | Playground Renovation | 2 | PRELIMINARY DESIGN | Sep 2026 | Jan 2027 | Sep 2026 | Jan 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC002-024 | Playground Renovation | 3 | FINAL DESIGN | Jan 2027 | Jul 2027 | Jan 2027 | Jul 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC002-024 | Playground Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2027 | Oct 2027 | Jul 2027 | Oct 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC002-024 | Playground Renovation | 5 | CONSTRUCTION TO 25% | Oct 2027 | Feb 2028 | Oct 2027 | Feb 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC002-024 | Playground Renovation | 6 | CONSTRUCTION TO 50% | Feb 2028 | Jun 2028 | Feb 2028 | Jun 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC002-024 | Playground Renovation | 7 | CONSTRUCTION TO 75% | Jun 2028 | Oct 2028 | Jun 2028 | Oct 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC002-024 | Playground Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2028 | Jan 2029 | Oct 2028 | Jan 2029
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC002-024 | Playground Renovation | 9 | SUBSTANTIAL COMPLETION | Jan 2029 | Mar 2029 | Jan 2029 | Mar 2029
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC002-024 | Playground Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2029 | Apr 2029 | Mar 2029 | Apr 2029
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC026-011 | Phone System Upgrade And Expansion | 1 | DEVELOP SCOPE | Jun 2011 | Aug 2011 | Jun 2011 | Aug 2011
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC026-011 | Phone System Upgrade And Expansion | 2 | PRELIMINARY DESIGN | Aug 2011 | Dec 2011 | Aug 2011 | Dec 2011
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC026-011 | Phone System Upgrade And Expansion | 3 | FINAL DESIGN | Dec 2011 | Jun 2012 | Dec 2011 | Jun 2012
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC026-011 | Phone System Upgrade And Expansion | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2012 | Sep 2012 | Jun 2012 | Sep 2012
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC026-011 | Phone System Upgrade And Expansion | 5 | CONSTRUCTION TO 25% | Sep 2012 | Jan 2013 | Sep 2012 | Jan 2013
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC026-011 | Phone System Upgrade And Expansion | 6 | CONSTRUCTION TO 50% | Jan 2013 | May 2013 | Jan 2013 | May 2013
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC026-011 | Phone System Upgrade And Expansion | 7 | CONSTRUCTION TO 75% | May 2013 | Sep 2013 | May 2013 | Sep 2013
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC026-011 | Phone System Upgrade And Expansion | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC026-011 | Phone System Upgrade And Expansion | 9 | SUBSTANTIAL COMPLETION | Dec 2013 | Feb 2014 | Dec 2013 | Feb 2014
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC026-011 | Phone System Upgrade And Expansion | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2014 | Mar 2014 | Feb 2014 | Mar 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC032-017 | Athletic Facilities Renovation | 1 | DEVELOP SCOPE | Jun 2017 | Aug 2017 | Jun 2017 | Aug 2017
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC032-017 | Athletic Facilities Renovation | 2 | PRELIMINARY DESIGN | Aug 2017 | Dec 2017 | Aug 2017 | Dec 2017
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC032-017 | Athletic Facilities Renovation | 3 | FINAL DESIGN | Dec 2017 | Jun 2018 | Dec 2017 | Jun 2018
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC032-017 | Athletic Facilities Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC032-017 | Athletic Facilities Renovation | 5 | CONSTRUCTION TO 25% | Sep 2018 | Jan 2019 | Sep 2018 | Jan 2019
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC032-017 | Athletic Facilities Renovation | 6 | CONSTRUCTION TO 50% | Jan 2019 | May 2019 | Jan 2019 | May 2019
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC032-017 | Athletic Facilities Renovation | 7 | CONSTRUCTION TO 75% | May 2019 | Sep 2019 | May 2019 | Sep 2019
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC032-017 | Athletic Facilities Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Dec 2019 | Sep 2019 | Dec 2019
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC032-017 | Athletic Facilities Renovation | 9 | SUBSTANTIAL COMPLETION | Dec 2019 | Feb 2020 | Dec 2019 | Feb 2020
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC032-017 | Athletic Facilities Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2020 | Mar 2020 | Feb 2020 | Mar 2029
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC033-019 | Expansive Glass Addition to the Building Facing West | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jul 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC033-019 | Expansive Glass Addition to the Building Facing West | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC033-019 | Expansive Glass Addition to the Building Facing West | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2024 | Jul 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC033-019 | Expansive Glass Addition to the Building Facing West | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2024 | Oct 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC033-019 | Expansive Glass Addition to the Building Facing West | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2024 | Feb 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC033-019 | Expansive Glass Addition to the Building Facing West | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2025 | Jun 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC033-019 | Expansive Glass Addition to the Building Facing West | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2025 | Oct 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC033-019 | Expansive Glass Addition to the Building Facing West | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2025 | Jan 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC033-019 | Expansive Glass Addition to the Building Facing West | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2026 | Mar 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC033-019 | Expansive Glass Addition to the Building Facing West | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2026 | Apr 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC034-018 | Hunter Campus Atrium | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jun 2018 | Aug 2018
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC034-018 | Hunter Campus Atrium | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Aug 2018 | Dec 2018
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC034-018 | Hunter Campus Atrium | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Dec 2018 | Jun 2019
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC034-018 | Hunter Campus Atrium | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC034-018 | Hunter Campus Atrium | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC034-018 | Hunter Campus Atrium | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Jan 2020 | May 2020
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC034-018 | Hunter Campus Atrium | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | May 2020 | Sep 2020
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC034-018 | Hunter Campus Atrium | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Sep 2020 | Dec 2020
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC034-018 | Hunter Campus Atrium | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Dec 2020 | Feb 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC034-018 | Hunter Campus Atrium | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Feb 2021 | Mar 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC036-020 | GLASS BOX | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2024 | Sep 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC036-020 | GLASS BOX | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC036-020 | GLASS BOX | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2025 | Jul 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC036-020 | GLASS BOX | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2025 | Oct 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC036-020 | GLASS BOX | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2025 | Feb 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC036-020 | GLASS BOX | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2026 | Jun 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC036-020 | GLASS BOX | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2026 | Oct 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC036-020 | GLASS BOX | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2026 | Jan 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC036-020 | GLASS BOX | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2027 | Mar 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC036-020 | GLASS BOX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2027 | Apr 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC073-094 | Elevator Upgrade | 2 | PRELIMINARY DESIGN | Dec 2009 | Apr 2010 | Dec 2009 | Apr 2010
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC073-094 | Elevator Upgrade | 3 | FINAL DESIGN | Apr 2010 | Aug 2010 | Apr 2010 | Aug 2010
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC073-094 | Elevator Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2010 | Nov 2010 | Aug 2010 | Nov 2010
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC073-094 | Elevator Upgrade | 5 | CONSTRUCTION TO 25% | Nov 2010 | Nov 2010 | Nov 2010 | Nov 2010
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC073-094 | Elevator Upgrade | 6 | CONSTRUCTION TO 50% | Nov 2010 | Dec 2010 | Nov 2010 | Dec 2010
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC073-094 | Elevator Upgrade | 7 | CONSTRUCTION TO 75% | Nov 2010 | Dec 2010 | Nov 2010 | Dec 2010
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC073-094 | Elevator Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2010 | Dec 2010 | Dec 2010 | Dec 2010
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC073-094 | Elevator Upgrade | 9 | SUBSTANTIAL COMPLETION | Dec 2010 | Dec 2010 | Dec 2010 | Dec 2010
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC073-094 | Elevator Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2010 | Jan 2011 | Dec 2010 | Jan 2014
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC075-098 | HVAC Improvements | 1 | DEVELOP SCOPE | Jun 2001 | Sep 2001 | Jun 2001 | Sep 2001
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC075-098 | HVAC Improvements | 2 | PRELIMINARY DESIGN | Sep 2001 | Mar 2002 | Sep 2001 | Mar 2002
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC075-098 | HVAC Improvements | 3 | FINAL DESIGN | Mar 2002 | Mar 2003 | Mar 2002 | Mar 2003
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC075-098 | HVAC Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2003 | Mar 2004 | Mar 2003 | Mar 2004
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC075-098 | HVAC Improvements | 5 | CONSTRUCTION TO 25% | Mar 2004 | Mar 2005 | Mar 2004 | Mar 2005
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC075-098 | HVAC Improvements | 6 | CONSTRUCTION TO 50% | Mar 2005 | Mar 2006 | Mar 2005 | Mar 2006
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC075-098 | HVAC Improvements | 7 | CONSTRUCTION TO 75% | Mar 2006 | May 2007 | Mar 2006 | May 2007
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC075-098 | HVAC Improvements | 8 | ORIGINAL EQUIP & FURNISHING | May 2007 | May 2007 | May 2007 | May 2007
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC075-098 | HVAC Improvements | 9 | SUBSTANTIAL COMPLETION | May 2007 | May 2007 | May 2007 | May 2007
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HC075-098 | HVAC Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2007 | Jun 2007 | May 2007 | May 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-023 | Performing Arts Center | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-023 | Performing Arts Center | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-023 | Performing Arts Center | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-023 | Performing Arts Center | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-023 | Performing Arts Center | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-023 | Performing Arts Center | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-023 | Performing Arts Center | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-023 | Performing Arts Center | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-023 | Performing Arts Center | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-023 | Performing Arts Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-024 | LIBRARY RENOVATION | 1 | DEVELOP SCOPE | Jul 2023 | Sep 2024 | Jul 2023 | Sep 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-024 | LIBRARY RENOVATION | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-024 | LIBRARY RENOVATION | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-024 | LIBRARY RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-024 | LIBRARY RENOVATION | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-024 | LIBRARY RENOVATION | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-024 | LIBRARY RENOVATION | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-024 | LIBRARY RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-024 | LIBRARY RENOVATION | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-024 | LIBRARY RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-022 | Auditorium Renovation in North Building | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-022 | Auditorium Renovation in North Building | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-022 | Auditorium Renovation in North Building | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-022 | Auditorium Renovation in North Building | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-022 | Auditorium Renovation in North Building | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-022 | Auditorium Renovation in North Building | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-022 | Auditorium Renovation in North Building | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-022 | Auditorium Renovation in North Building | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-022 | Auditorium Renovation in North Building | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-022 | Auditorium Renovation in North Building | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-023 | Campus Beautification Efforts | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-023 | Campus Beautification Efforts | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-023 | Campus Beautification Efforts | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-023 | Campus Beautification Efforts | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-023 | Campus Beautification Efforts | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-023 | Campus Beautification Efforts | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-023 | Campus Beautification Efforts | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-023 | Campus Beautification Efforts | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-023 | Campus Beautification Efforts | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-023 | Campus Beautification Efforts | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2029
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-021 | Auditorium Renovation | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2025 | Sep 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-021 | Auditorium Renovation | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2025 | Jan 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-021 | Auditorium Renovation | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2026 | Jul 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-021 | Auditorium Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2026 | Oct 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-021 | Auditorium Renovation | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2026 | Feb 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-021 | Auditorium Renovation | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2027 | Jun 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-021 | Auditorium Renovation | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2027 | Oct 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-021 | Auditorium Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2027 | Jan 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-021 | Auditorium Renovation | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2028 | Mar 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-021 | Auditorium Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2028 | Apr 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-023 | Performing Arts Hub | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-023 | Performing Arts Hub | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-023 | Performing Arts Hub | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-023 | Performing Arts Hub | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-023 | Performing Arts Hub | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-023 | Performing Arts Hub | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-023 | Performing Arts Hub | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-023 | Performing Arts Hub | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-023 | Performing Arts Hub | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-023 | Performing Arts Hub | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2029
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU004-021 | School of Education Renovation | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU004-021 | School of Education Renovation | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU004-021 | School of Education Renovation | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU004-021 | School of Education Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU004-021 | School of Education Renovation | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU004-021 | School of Education Renovation | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU004-021 | School of Education Renovation | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU004-021 | School of Education Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU004-021 | School of Education Renovation | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU004-021 | School of Education Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU011-022 | School of Education Renovation | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU011-022 | School of Education Renovation | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU011-022 | School of Education Renovation | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU011-022 | School of Education Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU011-022 | School of Education Renovation | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU011-022 | School of Education Renovation | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU011-022 | School of Education Renovation | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU011-022 | School of Education Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU011-022 | School of Education Renovation | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU011-022 | School of Education Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2031
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU022-009 | EXPERIMENTAL PSYCHOLOGY LAB BUILDOUT | 1 | DEVELOP SCOPE | Jun 2009 | Aug 2009 | Jun 2009 | Aug 2009
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU022-009 | EXPERIMENTAL PSYCHOLOGY LAB BUILDOUT | 2 | PRELIMINARY DESIGN | Aug 2009 | Dec 2009 | Aug 2009 | Dec 2009
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU022-009 | EXPERIMENTAL PSYCHOLOGY LAB BUILDOUT | 3 | FINAL DESIGN | Dec 2009 | Jun 2010 | Dec 2009 | Jun 2010
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU022-009 | EXPERIMENTAL PSYCHOLOGY LAB BUILDOUT | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2010 | Sep 2010 | Jun 2010 | Sep 2010
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU022-009 | EXPERIMENTAL PSYCHOLOGY LAB BUILDOUT | 5 | CONSTRUCTION TO 25% | Sep 2010 | Jan 2011 | Sep 2010 | Jan 2011
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU022-009 | EXPERIMENTAL PSYCHOLOGY LAB BUILDOUT | 6 | CONSTRUCTION TO 50% | Jan 2011 | May 2011 | Jan 2011 | May 2011
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU022-009 | EXPERIMENTAL PSYCHOLOGY LAB BUILDOUT | 7 | CONSTRUCTION TO 75% | May 2011 | Sep 2011 | May 2011 | Sep 2011
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU022-009 | EXPERIMENTAL PSYCHOLOGY LAB BUILDOUT | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2011 | Dec 2011 | Sep 2011 | Dec 2011
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU022-009 | EXPERIMENTAL PSYCHOLOGY LAB BUILDOUT | 9 | SUBSTANTIAL COMPLETION | Dec 2011 | Feb 2012 | Dec 2011 | Feb 2012
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU022-009 | EXPERIMENTAL PSYCHOLOGY LAB BUILDOUT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2012 | Mar 2012 | Feb 2012 | Jun 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU026-013 | Science and Health Professions Building | 1 | DEVELOP SCOPE | Jun 2013 | Aug 2013 | Jul 2021 | Sep 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU026-013 | Science and Health Professions Building | 2 | PRELIMINARY DESIGN | Aug 2013 | Dec 2013 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU026-013 | Science and Health Professions Building | 3 | FINAL DESIGN | Dec 2013 | Jun 2014 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU026-013 | Science and Health Professions Building | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2014 | Sep 2014 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU026-013 | Science and Health Professions Building | 5 | CONSTRUCTION TO 25% | Sep 2014 | Jan 2015 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU026-013 | Science and Health Professions Building | 6 | CONSTRUCTION TO 50% | Jan 2015 | May 2015 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU026-013 | Science and Health Professions Building | 7 | CONSTRUCTION TO 75% | May 2015 | Sep 2015 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU026-013 | Science and Health Professions Building | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2015 | Dec 2015 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU026-013 | Science and Health Professions Building | 9 | SUBSTANTIAL COMPLETION | Dec 2015 | Feb 2016 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU026-013 | Science and Health Professions Building | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2016 | Mar 2016 | Mar 2024 | Jun 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU027-013 | SCHOOL OF NURSING/HEALTH SCIENCE RELOCATION TO C3 | 1 | DEVELOP SCOPE | Jun 2015 | Aug 2015 | Jun 2027 | Sep 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU027-013 | SCHOOL OF NURSING/HEALTH SCIENCE RELOCATION TO C3 | 2 | PRELIMINARY DESIGN | Aug 2015 | Dec 2015 | Sep 2027 | Jan 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU027-013 | SCHOOL OF NURSING/HEALTH SCIENCE RELOCATION TO C3 | 3 | FINAL DESIGN | Dec 2015 | Jun 2016 | Jan 2028 | Jul 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU027-013 | SCHOOL OF NURSING/HEALTH SCIENCE RELOCATION TO C3 | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2016 | Sep 2016 | Jul 2028 | Oct 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU027-013 | SCHOOL OF NURSING/HEALTH SCIENCE RELOCATION TO C3 | 5 | CONSTRUCTION TO 25% | Sep 2016 | Jan 2017 | Oct 2028 | Feb 2029
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU027-013 | SCHOOL OF NURSING/HEALTH SCIENCE RELOCATION TO C3 | 6 | CONSTRUCTION TO 50% | Jan 2017 | May 2017 | Feb 2029 | Jun 2029
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU027-013 | SCHOOL OF NURSING/HEALTH SCIENCE RELOCATION TO C3 | 7 | CONSTRUCTION TO 75% | May 2017 | Sep 2017 | Jun 2029 | Oct 2029
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU027-013 | SCHOOL OF NURSING/HEALTH SCIENCE RELOCATION TO C3 | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Dec 2017 | Oct 2029 | Jan 2030
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU027-013 | SCHOOL OF NURSING/HEALTH SCIENCE RELOCATION TO C3 | 9 | SUBSTANTIAL COMPLETION | Dec 2017 | Feb 2018 | Jan 2030 | Mar 2030
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU027-013 | SCHOOL OF NURSING/HEALTH SCIENCE RELOCATION TO C3 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2018 | Jun 2019 | Mar 2030 | Apr 2031
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU028-015 | Black Box Performance Space | 1 | DEVELOP SCOPE | Mar 2015 | May 2015 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU028-015 | Black Box Performance Space | 2 | PRELIMINARY DESIGN | May 2015 | Sep 2015 | Oct 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU028-015 | Black Box Performance Space | 3 | FINAL DESIGN | Sep 2015 | Mar 2016 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU028-015 | Black Box Performance Space | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2016 | Jun 2016 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU028-015 | Black Box Performance Space | 5 | CONSTRUCTION TO 25% | Jun 2016 | Oct 2016 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU028-015 | Black Box Performance Space | 6 | CONSTRUCTION TO 50% | Oct 2016 | Feb 2017 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU028-015 | Black Box Performance Space | 7 | CONSTRUCTION TO 75% | Feb 2017 | Jun 2017 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU028-015 | Black Box Performance Space | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2017 | Sep 2017 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU028-015 | Black Box Performance Space | 9 | SUBSTANTIAL COMPLETION | Sep 2017 | Nov 2017 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU028-015 | Black Box Performance Space | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | Dec 2017 | Mar 2024 | May 2029
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU029-015 | Black Box Media & Arts Flex Space Improvements | 1 | DEVELOP SCOPE | Oct 2014 | Dec 2014 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU029-015 | Black Box Media & Arts Flex Space Improvements | 2 | PRELIMINARY DESIGN | Dec 2014 | Apr 2015 | Oct 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU029-015 | Black Box Media & Arts Flex Space Improvements | 3 | FINAL DESIGN | Apr 2015 | Oct 2015 | Feb 2022 | Jul 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU029-015 | Black Box Media & Arts Flex Space Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2015 | Jan 2016 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU029-015 | Black Box Media & Arts Flex Space Improvements | 5 | CONSTRUCTION TO 25% | Jan 2016 | May 2016 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU029-015 | Black Box Media & Arts Flex Space Improvements | 6 | CONSTRUCTION TO 50% | May 2016 | Sep 2016 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU029-015 | Black Box Media & Arts Flex Space Improvements | 7 | CONSTRUCTION TO 75% | Sep 2016 | Jan 2017 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU029-015 | Black Box Media & Arts Flex Space Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2017 | Apr 2017 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU029-015 | Black Box Media & Arts Flex Space Improvements | 9 | SUBSTANTIAL COMPLETION | Apr 2017 | Jun 2017 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU029-015 | Black Box Media & Arts Flex Space Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2017 | Jul 2017 | Mar 2024 | May 2029
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU035-016 | Black Box Theater Renovation Black Box Theater Renovation | 1 | DEVELOP SCOPE | Jun 2015 | Aug 2015 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU035-016 | Black Box Theater Renovation Black Box Theater Renovation | 2 | PRELIMINARY DESIGN | Aug 2015 | Dec 2015 | Oct 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU035-016 | Black Box Theater Renovation Black Box Theater Renovation | 3 | FINAL DESIGN | Dec 2015 | Jun 2016 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU035-016 | Black Box Theater Renovation Black Box Theater Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2016 | Sep 2016 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU035-016 | Black Box Theater Renovation Black Box Theater Renovation | 5 | CONSTRUCTION TO 25% | Sep 2016 | Jan 2017 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU035-016 | Black Box Theater Renovation Black Box Theater Renovation | 6 | CONSTRUCTION TO 50% | Jan 2017 | May 2017 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU035-016 | Black Box Theater Renovation Black Box Theater Renovation | 7 | CONSTRUCTION TO 75% | May 2017 | Sep 2017 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU035-016 | Black Box Theater Renovation Black Box Theater Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Dec 2017 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU035-016 | Black Box Theater Renovation Black Box Theater Renovation | 9 | SUBSTANTIAL COMPLETION | Dec 2017 | Feb 2018 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU035-016 | Black Box Theater Renovation Black Box Theater Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2018 | Mar 2018 | Mar 2024 | May 2030
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU036-017 | Black Box Renovation | 1 | DEVELOP SCOPE | Jun 2017 | Aug 2017 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU036-017 | Black Box Renovation | 2 | PRELIMINARY DESIGN | Aug 2017 | Dec 2017 | Oct 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU036-017 | Black Box Renovation | 3 | FINAL DESIGN | Dec 2017 | Jun 2018 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU036-017 | Black Box Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Sep 2018 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU036-017 | Black Box Renovation | 5 | CONSTRUCTION TO 25% | Sep 2018 | Jan 2019 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU036-017 | Black Box Renovation | 6 | CONSTRUCTION TO 50% | Jan 2019 | May 2019 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU036-017 | Black Box Renovation | 7 | CONSTRUCTION TO 75% | May 2019 | Sep 2019 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU036-017 | Black Box Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Dec 2019 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU036-017 | Black Box Renovation | 9 | SUBSTANTIAL COMPLETION | Dec 2019 | Feb 2020 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU036-017 | Black Box Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2020 | Mar 2020 | Mar 2024 | May 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU037-017 | CUNY Hunter College - Performing Arts Hub Project | 1 | DEVELOP SCOPE | Jun 2017 | Aug 2017 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU037-017 | CUNY Hunter College - Performing Arts Hub Project | 2 | PRELIMINARY DESIGN | Aug 2017 | Dec 2017 | Oct 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU037-017 | CUNY Hunter College - Performing Arts Hub Project | 3 | FINAL DESIGN | Dec 2017 | Jun 2018 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU037-017 | CUNY Hunter College - Performing Arts Hub Project | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Sep 2018 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU037-017 | CUNY Hunter College - Performing Arts Hub Project | 5 | CONSTRUCTION TO 25% | Sep 2018 | Jan 2019 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU037-017 | CUNY Hunter College - Performing Arts Hub Project | 6 | CONSTRUCTION TO 50% | Jan 2019 | May 2019 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU037-017 | CUNY Hunter College - Performing Arts Hub Project | 7 | CONSTRUCTION TO 75% | May 2019 | Sep 2019 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU037-017 | CUNY Hunter College - Performing Arts Hub Project | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Dec 2019 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU037-017 | CUNY Hunter College - Performing Arts Hub Project | 9 | SUBSTANTIAL COMPLETION | Dec 2019 | Feb 2020 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU037-017 | CUNY Hunter College - Performing Arts Hub Project | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2020 | Mar 2020 | Mar 2024 | May 2029
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU039-018 | Performing Arts Hub - Renovate N Building Auditorium | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU039-018 | Performing Arts Hub - Renovate N Building Auditorium | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Oct 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU039-018 | Performing Arts Hub - Renovate N Building Auditorium | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU039-018 | Performing Arts Hub - Renovate N Building Auditorium | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU039-018 | Performing Arts Hub - Renovate N Building Auditorium | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU039-018 | Performing Arts Hub - Renovate N Building Auditorium | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU039-018 | Performing Arts Hub - Renovate N Building Auditorium | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU039-018 | Performing Arts Hub - Renovate N Building Auditorium | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU039-018 | Performing Arts Hub - Renovate N Building Auditorium | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU039-018 | Performing Arts Hub - Renovate N Building Auditorium | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Mar 2024 | May 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-018 | Renovate Performing Arts Hub in North Building | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-018 | Renovate Performing Arts Hub in North Building | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Oct 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-018 | Renovate Performing Arts Hub in North Building | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-018 | Renovate Performing Arts Hub in North Building | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-018 | Renovate Performing Arts Hub in North Building | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-018 | Renovate Performing Arts Hub in North Building | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-018 | Renovate Performing Arts Hub in North Building | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-018 | Renovate Performing Arts Hub in North Building | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-018 | Renovate Performing Arts Hub in North Building | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-018 | Renovate Performing Arts Hub in North Building | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Mar 2024 | May 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-019 | Computer Science 10th FL. North Expansion | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jul 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-019 | Computer Science 10th FL. North Expansion | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-019 | Computer Science 10th FL. North Expansion | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2024 | Jul 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-019 | Computer Science 10th FL. North Expansion | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2024 | Oct 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-019 | Computer Science 10th FL. North Expansion | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2024 | Feb 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-019 | Computer Science 10th FL. North Expansion | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2025 | Jun 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-019 | Computer Science 10th FL. North Expansion | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2025 | Oct 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-019 | Computer Science 10th FL. North Expansion | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2025 | Jan 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-019 | Computer Science 10th FL. North Expansion | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2026 | Mar 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-019 | Computer Science 10th FL. North Expansion | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2026 | Apr 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU041-019 | Black Box Media Flex Space | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU041-019 | Black Box Media Flex Space | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Oct 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU041-019 | Black Box Media Flex Space | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU041-019 | Black Box Media Flex Space | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU041-019 | Black Box Media Flex Space | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU041-019 | Black Box Media Flex Space | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU041-019 | Black Box Media Flex Space | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU041-019 | Black Box Media Flex Space | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU041-019 | Black Box Media Flex Space | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU041-019 | Black Box Media Flex Space | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2024 | Apr 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU043-020 | Auditorium Renovation in North Building | 1 | DEVELOP SCOPE | Jul 2021 | Sep 2021 | Jul 2021 | Sep 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU043-020 | Auditorium Renovation in North Building | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU043-020 | Auditorium Renovation in North Building | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU043-020 | Auditorium Renovation in North Building | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU043-020 | Auditorium Renovation in North Building | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU043-020 | Auditorium Renovation in North Building | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU043-020 | Auditorium Renovation in North Building | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU043-020 | Auditorium Renovation in North Building | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU043-020 | Auditorium Renovation in North Building | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | HU043-020 | Auditorium Renovation in North Building | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | JJ001-021 | Multimedia Distribution System | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | JJ001-021 | Multimedia Distribution System | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | JJ001-021 | Multimedia Distribution System | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | JJ001-021 | Multimedia Distribution System | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | JJ001-021 | Multimedia Distribution System | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | JJ001-021 | Multimedia Distribution System | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | JJ001-021 | Multimedia Distribution System | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | JJ001-021 | Multimedia Distribution System | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | JJ001-021 | Multimedia Distribution System | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | JJ001-021 | Multimedia Distribution System | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | JJ024-017 | Locker Rooms and Gym Entrance | 1 | DEVELOP SCOPE | Jun 2017 | Aug 2017 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | JJ024-017 | Locker Rooms and Gym Entrance | 2 | PRELIMINARY DESIGN | Aug 2017 | Dec 2017 | Oct 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | JJ024-017 | Locker Rooms and Gym Entrance | 3 | FINAL DESIGN | Dec 2017 | Jun 2018 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | JJ024-017 | Locker Rooms and Gym Entrance | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Sep 2018 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | JJ024-017 | Locker Rooms and Gym Entrance | 5 | CONSTRUCTION TO 25% | Sep 2018 | Jan 2019 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | JJ024-017 | Locker Rooms and Gym Entrance | 6 | CONSTRUCTION TO 50% | Jan 2019 | May 2019 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | JJ024-017 | Locker Rooms and Gym Entrance | 7 | CONSTRUCTION TO 75% | May 2019 | Sep 2019 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | JJ024-017 | Locker Rooms and Gym Entrance | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Dec 2019 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | JJ024-017 | Locker Rooms and Gym Entrance | 9 | SUBSTANTIAL COMPLETION | Dec 2019 | Feb 2020 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | JJ024-017 | Locker Rooms and Gym Entrance | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2020 | Mar 2020 | Mar 2024 | May 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | JJ029-018 | Theater ADA Upgrades | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jul 2021 | Sep 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | JJ029-018 | Theater ADA Upgrades | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | JJ029-018 | Theater ADA Upgrades | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | JJ029-018 | Theater ADA Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | JJ029-018 | Theater ADA Upgrades | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | JJ029-018 | Theater ADA Upgrades | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | JJ029-018 | Theater ADA Upgrades | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | JJ029-018 | Theater ADA Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | JJ029-018 | Theater ADA Upgrades | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | JJ029-018 | Theater ADA Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Mar 2024 | Apr 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-021 | Library Interior Renovation | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-021 | Library Interior Renovation | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-021 | Library Interior Renovation | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-021 | Library Interior Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-021 | Library Interior Renovation | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-021 | Library Interior Renovation | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-021 | Library Interior Renovation | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-021 | Library Interior Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-021 | Library Interior Renovation | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-021 | Library Interior Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-022 | Library Interior Renovation | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-022 | Library Interior Renovation | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-022 | Library Interior Renovation | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-022 | Library Interior Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-022 | Library Interior Renovation | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-022 | Library Interior Renovation | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-022 | Library Interior Renovation | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-022 | Library Interior Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-022 | Library Interior Renovation | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-022 | Library Interior Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-023 | Learning Resource Center | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-023 | Learning Resource Center | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-023 | Learning Resource Center | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-023 | Learning Resource Center | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-023 | Learning Resource Center | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-023 | Learning Resource Center | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-023 | Learning Resource Center | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-023 | Learning Resource Center | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-023 | Learning Resource Center | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-023 | Learning Resource Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2032
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-024 | LEARNING RESOURCE CENTER INTERIOR RENOVATION | 1 | DEVELOP SCOPE | Jul 2023 | Sep 2024 | Jul 2023 | Sep 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-024 | LEARNING RESOURCE CENTER INTERIOR RENOVATION | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-024 | LEARNING RESOURCE CENTER INTERIOR RENOVATION | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-024 | LEARNING RESOURCE CENTER INTERIOR RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-024 | LEARNING RESOURCE CENTER INTERIOR RENOVATION | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-024 | LEARNING RESOURCE CENTER INTERIOR RENOVATION | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-024 | LEARNING RESOURCE CENTER INTERIOR RENOVATION | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-024 | LEARNING RESOURCE CENTER INTERIOR RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-024 | LEARNING RESOURCE CENTER INTERIOR RENOVATION | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-024 | LEARNING RESOURCE CENTER INTERIOR RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC028-010 | CUNY: BMCC, 199 Chambers Street - EE Upgrade | 1 | DEVELOP SCOPE | Jun 2010 | Aug 2010 | Jul 2019 | Sep 2019
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC028-010 | CUNY: BMCC, 199 Chambers Street - EE Upgrade | 2 | PRELIMINARY DESIGN | Aug 2010 | Dec 2010 | Sep 2019 | Jan 2020
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC028-010 | CUNY: BMCC, 199 Chambers Street - EE Upgrade | 3 | FINAL DESIGN | Dec 2010 | Jun 2011 | Jan 2020 | Jul 2020
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC028-010 | CUNY: BMCC, 199 Chambers Street - EE Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2011 | Sep 2011 | Jul 2020 | Oct 2020
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC028-010 | CUNY: BMCC, 199 Chambers Street - EE Upgrade | 5 | CONSTRUCTION TO 25% | Sep 2011 | Jan 2012 | Oct 2020 | Feb 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC028-010 | CUNY: BMCC, 199 Chambers Street - EE Upgrade | 6 | CONSTRUCTION TO 50% | Jan 2012 | May 2012 | Feb 2021 | Jun 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC028-010 | CUNY: BMCC, 199 Chambers Street - EE Upgrade | 7 | CONSTRUCTION TO 75% | May 2012 | Sep 2012 | Jun 2021 | Oct 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC028-010 | CUNY: BMCC, 199 Chambers Street - EE Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2012 | Dec 2012 | Oct 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC028-010 | CUNY: BMCC, 199 Chambers Street - EE Upgrade | 9 | SUBSTANTIAL COMPLETION | Dec 2012 | Feb 2013 | Jan 2022 | Mar 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC028-010 | CUNY: BMCC, 199 Chambers Street - EE Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2013 | Mar 2013 | Mar 2022 | Jun 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC029-012 | Gymnasium Air Conditioning System | 1 | DEVELOP SCOPE | Jun 2012 | Aug 2012 | Jun 2012 | Aug 2012
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC029-012 | Gymnasium Air Conditioning System | 2 | PRELIMINARY DESIGN | Aug 2012 | Dec 2012 | Aug 2012 | Dec 2012
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC029-012 | Gymnasium Air Conditioning System | 3 | FINAL DESIGN | Dec 2012 | Jun 2013 | Dec 2012 | Jun 2013
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC029-012 | Gymnasium Air Conditioning System | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2013 | Sep 2013 | Jun 2013 | Sep 2013
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC029-012 | Gymnasium Air Conditioning System | 5 | CONSTRUCTION TO 25% | Sep 2013 | Jan 2014 | Sep 2013 | Jan 2014
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC029-012 | Gymnasium Air Conditioning System | 6 | CONSTRUCTION TO 50% | Jan 2014 | May 2014 | Jan 2014 | May 2014
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC029-012 | Gymnasium Air Conditioning System | 7 | CONSTRUCTION TO 75% | May 2014 | Sep 2014 | May 2014 | Sep 2014
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC029-012 | Gymnasium Air Conditioning System | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC029-012 | Gymnasium Air Conditioning System | 9 | SUBSTANTIAL COMPLETION | Dec 2014 | Feb 2015 | Dec 2014 | Feb 2015
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC029-012 | Gymnasium Air Conditioning System | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2015 | Mar 2015 | Feb 2015 | Dec 2029
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC036-016 | Perimeter Security Lighting | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Jul 2021 | Sep 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC036-016 | Perimeter Security Lighting | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC036-016 | Perimeter Security Lighting | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC036-016 | Perimeter Security Lighting | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC036-016 | Perimeter Security Lighting | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC036-016 | Perimeter Security Lighting | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC036-016 | Perimeter Security Lighting | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC036-016 | Perimeter Security Lighting | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC036-016 | Perimeter Security Lighting | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC036-016 | Perimeter Security Lighting | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Mar 2024 | Apr 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC040-018 | LED Conversion in Public Areas | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jul 2020 | Sep 2020
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC040-018 | LED Conversion in Public Areas | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Sep 2020 | Jan 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC040-018 | LED Conversion in Public Areas | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Jan 2021 | Jul 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC040-018 | LED Conversion in Public Areas | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC040-018 | LED Conversion in Public Areas | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Oct 2021 | Feb 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC040-018 | LED Conversion in Public Areas | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Feb 2022 | Jun 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC040-018 | LED Conversion in Public Areas | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | Jun 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC040-018 | LED Conversion in Public Areas | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Oct 2022 | Jan 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC040-018 | LED Conversion in Public Areas | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Jan 2023 | Mar 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC040-018 | LED Conversion in Public Areas | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Mar 2023 | Apr 2026
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC042-018 | BMCC Pedestrian Enclosed Extension | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jul 2020 | Sep 2020
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC042-018 | BMCC Pedestrian Enclosed Extension | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Sep 2020 | Jan 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC042-018 | BMCC Pedestrian Enclosed Extension | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Jan 2021 | Jul 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC042-018 | BMCC Pedestrian Enclosed Extension | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC042-018 | BMCC Pedestrian Enclosed Extension | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Oct 2021 | Feb 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC042-018 | BMCC Pedestrian Enclosed Extension | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Feb 2022 | Jun 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC042-018 | BMCC Pedestrian Enclosed Extension | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | Jun 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC042-018 | BMCC Pedestrian Enclosed Extension | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Oct 2022 | Jan 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC042-018 | BMCC Pedestrian Enclosed Extension | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Jan 2023 | Mar 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC042-018 | BMCC Pedestrian Enclosed Extension | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Mar 2023 | Apr 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC044-019 | New Corridor Access Controls and Doors | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jul 2020 | Sep 2020
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC044-019 | New Corridor Access Controls and Doors | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2020 | Jan 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC044-019 | New Corridor Access Controls and Doors | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2021 | Jul 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC044-019 | New Corridor Access Controls and Doors | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC044-019 | New Corridor Access Controls and Doors | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2021 | Feb 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC044-019 | New Corridor Access Controls and Doors | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2022 | Jun 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC044-019 | New Corridor Access Controls and Doors | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC044-019 | New Corridor Access Controls and Doors | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2022 | Jan 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC044-019 | New Corridor Access Controls and Doors | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2023 | Mar 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC044-019 | New Corridor Access Controls and Doors | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2023 | Apr 2027
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC045-020 | Tribeca Performing Arts Center Theater 1 & 2 Lighting Upgra | 1 | DEVELOP SCOPE | Jul 2019 | Sep 2019 | Jul 2019 | Sep 2019
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC045-020 | Tribeca Performing Arts Center Theater 1 & 2 Lighting Upgra | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC045-020 | Tribeca Performing Arts Center Theater 1 & 2 Lighting Upgra | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC045-020 | Tribeca Performing Arts Center Theater 1 & 2 Lighting Upgra | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC045-020 | Tribeca Performing Arts Center Theater 1 & 2 Lighting Upgra | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC045-020 | Tribeca Performing Arts Center Theater 1 & 2 Lighting Upgra | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC045-020 | Tribeca Performing Arts Center Theater 1 & 2 Lighting Upgra | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC045-020 | Tribeca Performing Arts Center Theater 1 & 2 Lighting Upgra | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC045-020 | Tribeca Performing Arts Center Theater 1 & 2 Lighting Upgra | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MC045-020 | Tribeca Performing Arts Center Theater 1 & 2 Lighting Upgra | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Apr 2025
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH040-014 | Macaulay Honors College Classroom Upgrades | 1 | DEVELOP SCOPE | Jun 2014 | Aug 2014 | Jul 2021 | Sep 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH040-014 | Macaulay Honors College Classroom Upgrades | 2 | PRELIMINARY DESIGN | Aug 2014 | Dec 2014 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH040-014 | Macaulay Honors College Classroom Upgrades | 3 | FINAL DESIGN | Dec 2014 | Jun 2015 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH040-014 | Macaulay Honors College Classroom Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2015 | Sep 2015 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH040-014 | Macaulay Honors College Classroom Upgrades | 5 | CONSTRUCTION TO 25% | Sep 2015 | Jan 2016 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH040-014 | Macaulay Honors College Classroom Upgrades | 6 | CONSTRUCTION TO 50% | Jan 2016 | May 2016 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH040-014 | Macaulay Honors College Classroom Upgrades | 7 | CONSTRUCTION TO 75% | May 2016 | Sep 2016 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH040-014 | Macaulay Honors College Classroom Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Dec 2016 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH040-014 | Macaulay Honors College Classroom Upgrades | 9 | SUBSTANTIAL COMPLETION | Dec 2016 | Feb 2017 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH040-014 | Macaulay Honors College Classroom Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2017 | Mar 2017 | Mar 2024 | Apr 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH053-016 | Macaulay Honors College - New Media Lab | 1 | DEVELOP SCOPE | Jun 2015 | Aug 2015 | Jun 2015 | Aug 2015
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH053-016 | Macaulay Honors College - New Media Lab | 2 | PRELIMINARY DESIGN | Aug 2015 | Dec 2015 | Aug 2015 | Dec 2015
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH053-016 | Macaulay Honors College - New Media Lab | 3 | FINAL DESIGN | Dec 2015 | Jun 2016 | Dec 2015 | Jun 2016
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH053-016 | Macaulay Honors College - New Media Lab | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2016 | Sep 2016 | Jun 2016 | Sep 2016
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH053-016 | Macaulay Honors College - New Media Lab | 5 | CONSTRUCTION TO 25% | Sep 2016 | Jan 2017 | Sep 2016 | Jan 2017
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH053-016 | Macaulay Honors College - New Media Lab | 6 | CONSTRUCTION TO 50% | Jan 2017 | May 2017 | Jan 2017 | May 2017
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH053-016 | Macaulay Honors College - New Media Lab | 7 | CONSTRUCTION TO 75% | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH053-016 | Macaulay Honors College - New Media Lab | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Dec 2017 | Sep 2017 | Dec 2017
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH053-016 | Macaulay Honors College - New Media Lab | 9 | SUBSTANTIAL COMPLETION | Dec 2017 | Feb 2018 | Dec 2017 | Feb 2018
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH053-016 | Macaulay Honors College - New Media Lab | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2018 | Mar 2018 | Feb 2018 | Jun 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH059-017 | Macaulay Honors College Data Science Lab | 1 | DEVELOP SCOPE | Jun 2017 | Aug 2017 | Jul 2021 | Sep 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH059-017 | Macaulay Honors College Data Science Lab | 2 | PRELIMINARY DESIGN | Aug 2017 | Dec 2017 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH059-017 | Macaulay Honors College Data Science Lab | 3 | FINAL DESIGN | Dec 2017 | Jun 2018 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH059-017 | Macaulay Honors College Data Science Lab | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Sep 2018 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH059-017 | Macaulay Honors College Data Science Lab | 5 | CONSTRUCTION TO 25% | Sep 2018 | Jan 2019 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH059-017 | Macaulay Honors College Data Science Lab | 6 | CONSTRUCTION TO 50% | Jan 2019 | May 2019 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH059-017 | Macaulay Honors College Data Science Lab | 7 | CONSTRUCTION TO 75% | May 2019 | Sep 2019 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH059-017 | Macaulay Honors College Data Science Lab | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Dec 2019 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH059-017 | Macaulay Honors College Data Science Lab | 9 | SUBSTANTIAL COMPLETION | Dec 2019 | Feb 2020 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH059-017 | Macaulay Honors College Data Science Lab | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2020 | Mar 2020 | Mar 2024 | Apr 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH060-020 | New Media/Data Science Lab | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH060-020 | New Media/Data Science Lab | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH060-020 | New Media/Data Science Lab | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH060-020 | New Media/Data Science Lab | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH060-020 | New Media/Data Science Lab | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH060-020 | New Media/Data Science Lab | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH060-020 | New Media/Data Science Lab | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2022
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH060-020 | New Media/Data Science Lab | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH060-020 | New Media/Data Science Lab | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2023 | Mar 2023
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | MH060-020 | New Media/Data Science Lab | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2023 | Apr 2028
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | SAND-MC01 | Rehabilitation and Improvements due to Hurricane Sandy | 1 | DEVELOP SCOPE | Jun 2013 | Sep 2013 | Jun 2013 | Sep 2013
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | SAND-MC01 | Rehabilitation and Improvements due to Hurricane Sandy | 2 | PRELIMINARY DESIGN | Sep 2013 | Jan 2014 | Sep 2013 | Jan 2014
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | SAND-MC01 | Rehabilitation and Improvements due to Hurricane Sandy | 3 | FINAL DESIGN | Jan 2014 | Jul 2014 | Jan 2014 | Jul 2014
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | SAND-MC01 | Rehabilitation and Improvements due to Hurricane Sandy | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2014 | Oct 2014 | Jul 2014 | Oct 2014
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | SAND-MC01 | Rehabilitation and Improvements due to Hurricane Sandy | 5 | CONSTRUCTION TO 25% | Oct 2014 | Feb 2015 | Oct 2014 | Feb 2015
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | SAND-MC01 | Rehabilitation and Improvements due to Hurricane Sandy | 6 | CONSTRUCTION TO 50% | Feb 2015 | Jun 2015 | Feb 2015 | Jun 2015
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | SAND-MC01 | Rehabilitation and Improvements due to Hurricane Sandy | 7 | CONSTRUCTION TO 75% | Jun 2015 | Oct 2015 | Jun 2015 | Oct 2015
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | SAND-MC01 | Rehabilitation and Improvements due to Hurricane Sandy | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2015 | Jan 2016 | Oct 2015 | Jan 2016
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | SAND-MC01 | Rehabilitation and Improvements due to Hurricane Sandy | 9 | SUBSTANTIAL COMPLETION | Jan 2016 | Mar 2016 | Jan 2016 | Mar 2016
20231026 | MANHATTAN | 042 | CITY UNIVERSITY | SAND-MC01 | Rehabilitation and Improvements due to Hurricane Sandy | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Apr 2016 | Mar 2016 | Apr 2029
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | APINYPD02 | NYPD 137th Street Comprehensive Electrification | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | APINYPD02 | NYPD 137th Street Comprehensive Electrification | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | APINYPD02 | NYPD 137th Street Comprehensive Electrification | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | APINYPD02 | NYPD 137th Street Comprehensive Electrification | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | APINYPD02 | NYPD 137th Street Comprehensive Electrification | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | APINYPD02 | NYPD 137th Street Comprehensive Electrification | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79 PAL | POLICE ATHLETIC LEAGUE MASONRY | 1 | DESIGN | Dec 2009 | Jun 2010 | Dec 2012 | Jun 2013
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79 PAL | POLICE ATHLETIC LEAGUE MASONRY | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2010 | Sep 2010 | Jun 2013 | Sep 2013
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79 PAL | POLICE ATHLETIC LEAGUE MASONRY | 3 | CONSTRUCTION | Sep 2010 | Sep 2011 | Sep 2013 | Sep 2022
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79 PAL | POLICE ATHLETIC LEAGUE MASONRY | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2011 | Mar 2012 | Sep 2022 | Feb 2026
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79137CS | 137 centre street renovation | 1 | DESIGN | Jul 2020 | Jan 2021 | Jul 2020 | Jan 2022
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79137CS | 137 centre street renovation | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2021 | Apr 2021 | Jan 2022 | Apr 2022
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79137CS | 137 centre street renovation | 3 | CONSTRUCTION | Apr 2021 | Apr 2022 | Apr 2022 | Apr 2023
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79137CS | 137 centre street renovation | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2022 | Oct 2022 | Apr 2023 | Oct 2027
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPDR | One Police Plaza Doors | 1 | DESIGN | Dec 2019 | Jun 2020 | Dec 2019 | Jun 2022
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPDR | One Police Plaza Doors | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Sep 2020 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPDR | One Police Plaza Doors | 3 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPDR | One Police Plaza Doors | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Mar 2022 | Sep 2023 | Mar 2027
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPF | EMERGENCY RECONSTRUCTION OF 1 POLICE PLAZA FACADE | 1 | DESIGN | Feb 2021 | Jul 2021 | Feb 2021 | Jul 2021
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPF | EMERGENCY RECONSTRUCTION OF 1 POLICE PLAZA FACADE | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPF | EMERGENCY RECONSTRUCTION OF 1 POLICE PLAZA FACADE | 3 | CONSTRUCTION | Oct 2021 | Oct 2022 | Oct 2021 | Oct 2022
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPF | EMERGENCY RECONSTRUCTION OF 1 POLICE PLAZA FACADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2022 | Apr 2023 | Oct 2022 | Jun 2026
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPSD | 1 Police Plaza Security Desk | 1 | DEVELOP SCOPE | May 2022 | Aug 2022 | May 2022 | Aug 2022
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPSD | 1 Police Plaza Security Desk | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPSD | 1 Police Plaza Security Desk | 3 | FINAL DESIGN | Dec 2022 | Apr 2023 | Dec 2022 | Apr 2023
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPSD | 1 Police Plaza Security Desk | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2023 | Oct 2023 | Apr 2023 | Oct 2023
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPSD | 1 Police Plaza Security Desk | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPSD | 1 Police Plaza Security Desk | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPSD | 1 Police Plaza Security Desk | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPSD | 1 Police Plaza Security Desk | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPSD | 1 Police Plaza Security Desk | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPSD | 1 Police Plaza Security Desk | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Jun 2029
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAHO | HVAC REPLACEMENT FOR 20TH, 24TH AND 25TH PCTS | 1 | DEVELOP SCOPE | Jun 2014 | Sep 2014 | Jun 2014 | Sep 2014
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAHO | HVAC REPLACEMENT FOR 20TH, 24TH AND 25TH PCTS | 2 | PRELIMINARY DESIGN | Sep 2014 | Jan 2015 | Sep 2014 | Jan 2015
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAHO | HVAC REPLACEMENT FOR 20TH, 24TH AND 25TH PCTS | 3 | FINAL DESIGN | Jan 2015 | Jul 2015 | Jan 2015 | Jul 2015
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAHO | HVAC REPLACEMENT FOR 20TH, 24TH AND 25TH PCTS | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Oct 2015 | Jul 2015 | Oct 2015
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAHO | HVAC REPLACEMENT FOR 20TH, 24TH AND 25TH PCTS | 5 | CONSTRUCTION TO 25% | Oct 2015 | Feb 2016 | Oct 2015 | Feb 2016
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAHO | HVAC REPLACEMENT FOR 20TH, 24TH AND 25TH PCTS | 6 | CONSTRUCTION TO 50% | Feb 2016 | Jun 2016 | Feb 2016 | Jun 2016
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAHO | HVAC REPLACEMENT FOR 20TH, 24TH AND 25TH PCTS | 7 | CONSTRUCTION TO 75% | Jun 2016 | Oct 2016 | Jun 2016 | Oct 2020
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAHO | HVAC REPLACEMENT FOR 20TH, 24TH AND 25TH PCTS | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2016 | Jan 2017 | Oct 2020 | Jan 2021
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAHO | HVAC REPLACEMENT FOR 20TH, 24TH AND 25TH PCTS | 9 | SUBSTANTIAL COMPLETION | Jan 2017 | Mar 2017 | Jan 2021 | Mar 2021
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAHO | HVAC REPLACEMENT FOR 20TH, 24TH AND 25TH PCTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Apr 2017 | Mar 2021 | Apr 2024
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAIZ | 24th Precinct Facade | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Jun 2016 | May 2021
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAIZ | 24th Precinct Facade | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | May 2021 | Sep 2021
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAIZ | 24th Precinct Facade | 3 | FINAL DESIGN | Jan 2017 | May 2017 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAIZ | 24th Precinct Facade | 4 | BID AWARD AND REGISTER CONTRCT | May 2017 | Nov 2017 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAIZ | 24th Precinct Facade | 5 | CONSTRUCTION TO 25% | Nov 2017 | Mar 2018 | Jul 2022 | Nov 2022
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAIZ | 24th Precinct Facade | 6 | CONSTRUCTION TO 50% | Mar 2018 | Jul 2018 | Nov 2022 | Mar 2023
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAIZ | 24th Precinct Facade | 7 | CONSTRUCTION TO 75% | Jul 2018 | Nov 2018 | Mar 2023 | Jul 2026
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAIZ | 24th Precinct Facade | 8 | ORIGINAL EQUIP & FURNISHING | Nov 2018 | Feb 2019 | Jul 2026 | Oct 2026
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAIZ | 24th Precinct Facade | 9 | SUBSTANTIAL COMPLETION | Feb 2019 | Apr 2019 | Oct 2026 | Dec 2026
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAIZ | 24th Precinct Facade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2019 | May 2019 | Dec 2026 | Jan 2027
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJF | 32ND PCT PARKING LOT | 1 | DEVELOP SCOPE | Apr 2017 | Jul 2017 | Apr 2017 | Jul 2017
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJF | 32ND PCT PARKING LOT | 2 | PRELIMINARY DESIGN | Jul 2017 | Nov 2017 | Jul 2017 | Nov 2017
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJF | 32ND PCT PARKING LOT | 3 | FINAL DESIGN | Nov 2017 | May 2018 | Nov 2017 | May 2018
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJF | 32ND PCT PARKING LOT | 4 | BID AWARD AND REGISTER CONTRCT | May 2018 | Aug 2018 | May 2018 | Aug 2018
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJF | 32ND PCT PARKING LOT | 5 | CONSTRUCTION TO 25% | Aug 2018 | Dec 2018 | Aug 2018 | Dec 2018
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJF | 32ND PCT PARKING LOT | 6 | CONSTRUCTION TO 50% | Dec 2018 | Apr 2019 | Dec 2018 | Apr 2019
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJF | 32ND PCT PARKING LOT | 7 | CONSTRUCTION TO 75% | Apr 2019 | Aug 2019 | Apr 2019 | Aug 2021
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJF | 32ND PCT PARKING LOT | 8 | ORIGINAL EQUIP & FURNISHING | Aug 2019 | Nov 2019 | Aug 2021 | Nov 2021
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJF | 32ND PCT PARKING LOT | 9 | SUBSTANTIAL COMPLETION | Nov 2019 | Jan 2020 | Nov 2021 | Jan 2022
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJF | 32ND PCT PARKING LOT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2020 | Feb 2020 | Jan 2022 | Nov 2025
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJQ | 1 Police Plaza Auditorium | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2016 | Sep 2022
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJQ | 1 Police Plaza Auditorium | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJQ | 1 Police Plaza Auditorium | 3 | FINAL DESIGN | Jan 2018 | May 2018 | Jan 2023 | May 2023
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJQ | 1 Police Plaza Auditorium | 4 | BID AWARD AND REGISTER CONTRCT | May 2018 | Nov 2018 | May 2023 | Oct 2023
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJQ | 1 Police Plaza Auditorium | 5 | CONSTRUCTION TO 25% | Nov 2018 | Mar 2019 | Nov 2023 | Feb 2024
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJQ | 1 Police Plaza Auditorium | 6 | CONSTRUCTION TO 50% | Mar 2019 | Jun 2019 | Feb 2024 | Jun 2024
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJQ | 1 Police Plaza Auditorium | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jun 2021 | Feb 2025
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJQ | 1 Police Plaza Auditorium | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Feb 2025 | May 2025
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJQ | 1 Police Plaza Auditorium | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | May 2025 | Jul 2025
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJQ | 1 Police Plaza Auditorium | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Jul 2025 | Aug 2029
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKC | ELEVATOR REHABILITATION FOR MIDTOWN NORTH PCT | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Aug 2020
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKC | ELEVATOR REHABILITATION FOR MIDTOWN NORTH PCT | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKC | ELEVATOR REHABILITATION FOR MIDTOWN NORTH PCT | 3 | FINAL DESIGN | Dec 2020 | Apr 2021 | Dec 2020 | Apr 2021
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKC | ELEVATOR REHABILITATION FOR MIDTOWN NORTH PCT | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2021 | Oct 2021 | Apr 2021 | Oct 2021
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKC | ELEVATOR REHABILITATION FOR MIDTOWN NORTH PCT | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKC | ELEVATOR REHABILITATION FOR MIDTOWN NORTH PCT | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKC | ELEVATOR REHABILITATION FOR MIDTOWN NORTH PCT | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2022
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKC | ELEVATOR REHABILITATION FOR MIDTOWN NORTH PCT | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKC | ELEVATOR REHABILITATION FOR MIDTOWN NORTH PCT | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2023 | Mar 2023
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKC | ELEVATOR REHABILITATION FOR MIDTOWN NORTH PCT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2023 | Jun 2025
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKX | IAB HVAC REPLACEMENT | 1 | DEVELOP SCOPE | Dec 2020 | Mar 2021 | Dec 2020 | Mar 2021
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKX | IAB HVAC REPLACEMENT | 2 | PRELIMINARY DESIGN | Mar 2021 | Jul 2021 | Mar 2021 | Jul 2021
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKX | IAB HVAC REPLACEMENT | 3 | FINAL DESIGN | Jul 2021 | Nov 2021 | Jul 2021 | Nov 2021
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKX | IAB HVAC REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2021 | May 2022 | Nov 2021 | May 2022
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKX | IAB HVAC REPLACEMENT | 5 | CONSTRUCTION TO 25% | May 2022 | Aug 2022 | May 2022 | Aug 2022
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKX | IAB HVAC REPLACEMENT | 6 | CONSTRUCTION TO 50% | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKX | IAB HVAC REPLACEMENT | 7 | CONSTRUCTION TO 75% | Dec 2022 | Apr 2023 | Dec 2022 | Apr 2023
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKX | IAB HVAC REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2023 | Jul 2023 | Apr 2023 | Jul 2023
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKX | IAB HVAC REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | Jul 2023 | Sep 2023 | Jul 2023 | Sep 2023
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKX | IAB HVAC REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Oct 2023 | Sep 2023 | Oct 2025
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMALA | 5TH PRECINCT CONSTRUCTION RENOVATION | 1 | DESIGN | Feb 2021 | Jul 2021 | Feb 2021 | Jul 2021
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMALA | 5TH PRECINCT CONSTRUCTION RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMALA | 5TH PRECINCT CONSTRUCTION RENOVATION | 3 | CONSTRUCTION | Oct 2021 | Oct 2022 | Oct 2021 | Oct 2022
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMALA | 5TH PRECINCT CONSTRUCTION RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2022 | Apr 2023 | Oct 2022 | Jun 2029
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79-BMS | BMS PROJECTS | 1 | DESIGN | Jul 2010 | Dec 2010 | Sep 2016 | Mar 2021
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79-BMS | BMS PROJECTS | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2010 | Mar 2011 | Mar 2021 | Jun 2021
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79-BMS | BMS PROJECTS | 3 | CONSTRUCTION | Mar 2011 | Mar 2012 | Jun 2021 | Jun 2024
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79-BMS | BMS PROJECTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2012 | Sep 2012 | Jun 2024 | Dec 2024
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79CAFE | RENOVATION AND UPGRADE OF ONE POLICE PLAZA CAFETERIA | 1 | DESIGN | Jun 2019 | Dec 2019 | Jun 2019 | Dec 2019
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79CAFE | RENOVATION AND UPGRADE OF ONE POLICE PLAZA CAFETERIA | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2019 | Mar 2020 | Dec 2019 | Mar 2020
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79CAFE | RENOVATION AND UPGRADE OF ONE POLICE PLAZA CAFETERIA | 3 | CONSTRUCTION | Mar 2020 | Mar 2021 | Mar 2020 | Mar 2021
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79CAFE | RENOVATION AND UPGRADE OF ONE POLICE PLAZA CAFETERIA | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Sep 2021 | Mar 2021 | Sep 2025
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79HQBB | 1 POLICE PLAZA SECURITY BARRIERS & BOOTHS | 1 | DESIGN | May 2019 | Nov 2019 | May 2019 | Nov 2019
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79HQBB | 1 POLICE PLAZA SECURITY BARRIERS & BOOTHS | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2019 | Feb 2020 | Nov 2019 | Feb 2020
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79HQBB | 1 POLICE PLAZA SECURITY BARRIERS & BOOTHS | 3 | CONSTRUCTION | Feb 2020 | Feb 2021 | Feb 2020 | Feb 2021
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79HQBB | 1 POLICE PLAZA SECURITY BARRIERS & BOOTHS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Aug 2021 | Feb 2021 | Sep 2025
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PA13 | RENOVATION OF OLD POLICE ACADEMY/13TH PCT | 1 | DEVELOP SCOPE | Jun 2014 | Sep 2014 | Jun 2019 | Sep 2019
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PA13 | RENOVATION OF OLD POLICE ACADEMY/13TH PCT | 2 | PRELIMINARY DESIGN | Sep 2014 | Jan 2015 | Sep 2019 | Jan 2020
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PA13 | RENOVATION OF OLD POLICE ACADEMY/13TH PCT | 3 | FINAL DESIGN | Jan 2015 | Jul 2015 | Jan 2020 | Jul 2020
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PA13 | RENOVATION OF OLD POLICE ACADEMY/13TH PCT | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Oct 2015 | Jul 2020 | Oct 2020
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PA13 | RENOVATION OF OLD POLICE ACADEMY/13TH PCT | 5 | CONSTRUCTION TO 25% | Oct 2015 | Feb 2016 | Oct 2020 | Feb 2021
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PA13 | RENOVATION OF OLD POLICE ACADEMY/13TH PCT | 6 | CONSTRUCTION TO 50% | Feb 2016 | Jun 2016 | Feb 2021 | Jun 2021
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PA13 | RENOVATION OF OLD POLICE ACADEMY/13TH PCT | 7 | CONSTRUCTION TO 75% | Jun 2016 | Oct 2016 | Jun 2021 | Oct 2023
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PA13 | RENOVATION OF OLD POLICE ACADEMY/13TH PCT | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2016 | Jan 2017 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PA13 | RENOVATION OF OLD POLICE ACADEMY/13TH PCT | 9 | SUBSTANTIAL COMPLETION | Jan 2017 | Mar 2017 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PA13 | RENOVATION OF OLD POLICE ACADEMY/13TH PCT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Apr 2017 | Mar 2024 | Sep 2028
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PALB | PAL BOILER REPLACEMENT | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PALB | PAL BOILER REPLACEMENT | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PALB | PAL BOILER REPLACEMENT | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PALB | PAL BOILER REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PALB | PAL BOILER REPLACEMENT | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PALB | PAL BOILER REPLACEMENT | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PALB | PAL BOILER REPLACEMENT | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PALB | PAL BOILER REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PALB | PAL BOILER REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PALB | PAL BOILER REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Dec 2019
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD6 | HARBOR LAUNCH RANDALL'S ISLAND ELECTRICAL | 1 | DEVELOP SCOPE | Sep 2016 | Dec 2016 | Jun 2016 | Sep 2016
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD6 | HARBOR LAUNCH RANDALL'S ISLAND ELECTRICAL | 2 | PRELIMINARY DESIGN | Dec 2016 | Apr 2017 | Sep 2016 | Jan 2017
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD6 | HARBOR LAUNCH RANDALL'S ISLAND ELECTRICAL | 3 | FINAL DESIGN | Apr 2017 | Aug 2017 | Jan 2017 | May 2017
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD6 | HARBOR LAUNCH RANDALL'S ISLAND ELECTRICAL | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2017 | Feb 2018 | May 2017 | Nov 2017
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD6 | HARBOR LAUNCH RANDALL'S ISLAND ELECTRICAL | 5 | CONSTRUCTION TO 25% | Feb 2018 | Jun 2018 | Nov 2017 | Mar 2018
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD6 | HARBOR LAUNCH RANDALL'S ISLAND ELECTRICAL | 6 | CONSTRUCTION TO 50% | Jun 2018 | Sep 2018 | Mar 2018 | Jun 2018
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD6 | HARBOR LAUNCH RANDALL'S ISLAND ELECTRICAL | 7 | CONSTRUCTION TO 75% | Sep 2018 | Jan 2019 | Jun 2018 | Oct 2021
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD6 | HARBOR LAUNCH RANDALL'S ISLAND ELECTRICAL | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2019 | Apr 2019 | Oct 2021 | Jan 2022
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD6 | HARBOR LAUNCH RANDALL'S ISLAND ELECTRICAL | 9 | SUBSTANTIAL COMPLETION | Apr 2019 | Jun 2019 | Jan 2022 | Mar 2022
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD6 | HARBOR LAUNCH RANDALL'S ISLAND ELECTRICAL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2019 | Jul 2019 | Mar 2022 | May 2025
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD7 | POLICE SERVICE AREA 4 (PSA4) | 1 | DEVELOP SCOPE | Sep 2016 | Dec 2016 | Jun 2016 | Sep 2016
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD7 | POLICE SERVICE AREA 4 (PSA4) | 2 | PRELIMINARY DESIGN | Dec 2016 | Apr 2017 | Sep 2016 | Jan 2017
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD7 | POLICE SERVICE AREA 4 (PSA4) | 3 | FINAL DESIGN | Apr 2017 | Aug 2017 | Jan 2017 | May 2017
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD7 | POLICE SERVICE AREA 4 (PSA4) | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2017 | Feb 2018 | May 2017 | Nov 2017
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD7 | POLICE SERVICE AREA 4 (PSA4) | 5 | CONSTRUCTION TO 25% | Feb 2018 | Jun 2018 | Nov 2017 | Mar 2018
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD7 | POLICE SERVICE AREA 4 (PSA4) | 6 | CONSTRUCTION TO 50% | Jun 2018 | Sep 2018 | Mar 2018 | Jun 2018
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD7 | POLICE SERVICE AREA 4 (PSA4) | 7 | CONSTRUCTION TO 75% | Sep 2018 | Jan 2019 | Jun 2018 | Oct 2021
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD7 | POLICE SERVICE AREA 4 (PSA4) | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2019 | Apr 2019 | Oct 2021 | Jan 2022
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD7 | POLICE SERVICE AREA 4 (PSA4) | 9 | SUBSTANTIAL COMPLETION | Apr 2019 | Jun 2019 | Jan 2022 | Mar 2022
20231026 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD7 | POLICE SERVICE AREA 4 (PSA4) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2019 | Jul 2019 | Mar 2022 | Apr 2025
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN201 | FDNY - Lighting Upgrades at 11 FDNY Facilities | 1 | DEVELOP SCOPE | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN201 | FDNY - Lighting Upgrades at 11 FDNY Facilities | 2 | PRELIMINARY DESIGN | Apr 2022 | Jul 2022 | Apr 2022 | Jul 2022
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN201 | FDNY - Lighting Upgrades at 11 FDNY Facilities | 3 | FINAL DESIGN | Jul 2022 | Jan 2023 | Jul 2022 | Jan 2023
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN201 | FDNY - Lighting Upgrades at 11 FDNY Facilities | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2023 | Apr 2023 | Jan 2023 | Apr 2023
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN201 | FDNY - Lighting Upgrades at 11 FDNY Facilities | 5 | CONSTRUCTION TO 25% | Apr 2023 | Aug 2023 | Apr 2023 | Aug 2023
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN201 | FDNY - Lighting Upgrades at 11 FDNY Facilities | 6 | CONSTRUCTION TO 50% | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN201 | FDNY - Lighting Upgrades at 11 FDNY Facilities | 7 | CONSTRUCTION TO 75% | Dec 2023 | Apr 2024 | Dec 2023 | Apr 2024
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN201 | FDNY - Lighting Upgrades at 11 FDNY Facilities | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2024 | Jul 2024 | Apr 2024 | Jul 2024
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN201 | FDNY - Lighting Upgrades at 11 FDNY Facilities | 9 | SUBSTANTIAL COMPLETION | Jul 2024 | Sep 2024 | Jul 2024 | Sep 2024
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN201 | FDNY - Lighting Upgrades at 11 FDNY Facilities | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Oct 2024 | Sep 2024 | Oct 2024
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN803 | FDNY - Solar photo-voltaic system at SOC | 1 | DEVELOP SCOPE | Sep 2018 | Dec 2018 | Oct 2018 | Jan 2019
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN803 | FDNY - Solar photo-voltaic system at SOC | 2 | PRELIMINARY DESIGN | Dec 2018 | Apr 2019 | Jan 2019 | May 2019
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN803 | FDNY - Solar photo-voltaic system at SOC | 3 | FINAL DESIGN | Apr 2019 | Sep 2019 | May 2019 | Nov 2019
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN803 | FDNY - Solar photo-voltaic system at SOC | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Dec 2019 | Nov 2019 | Feb 2020
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN803 | FDNY - Solar photo-voltaic system at SOC | 5 | CONSTRUCTION TO 25% | Dec 2019 | Apr 2020 | Feb 2020 | Jun 2020
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN803 | FDNY - Solar photo-voltaic system at SOC | 6 | CONSTRUCTION TO 50% | Apr 2020 | Aug 2020 | Jun 2020 | Sep 2020
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN803 | FDNY - Solar photo-voltaic system at SOC | 7 | CONSTRUCTION TO 75% | Aug 2020 | Dec 2020 | Sep 2020 | Dec 2022
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN803 | FDNY - Solar photo-voltaic system at SOC | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2020 | Mar 2021 | Dec 2022 | Mar 2023
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN803 | FDNY - Solar photo-voltaic system at SOC | 9 | SUBSTANTIAL COMPLETION | Mar 2021 | May 2021 | Mar 2023 | May 2023
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN803 | FDNY - Solar photo-voltaic system at SOC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2021 | Jun 2021 | May 2023 | Jun 2024
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN901 | FDNY- Solar PV at FDNY Academy Building 12 | 1 | DEVELOP SCOPE | Dec 2019 | Mar 2020 | Dec 2019 | Mar 2020
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN901 | FDNY- Solar PV at FDNY Academy Building 12 | 2 | PRELIMINARY DESIGN | Mar 2020 | Jul 2020 | Mar 2020 | Jul 2020
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN901 | FDNY- Solar PV at FDNY Academy Building 12 | 3 | FINAL DESIGN | Jul 2020 | Jan 2021 | Jul 2020 | Jan 2021
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN901 | FDNY- Solar PV at FDNY Academy Building 12 | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2021 | Apr 2021 | Jan 2021 | Apr 2021
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN901 | FDNY- Solar PV at FDNY Academy Building 12 | 5 | CONSTRUCTION TO 25% | Apr 2021 | Aug 2021 | Apr 2021 | Aug 2021
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN901 | FDNY- Solar PV at FDNY Academy Building 12 | 6 | CONSTRUCTION TO 50% | Aug 2021 | Dec 2021 | Aug 2021 | Dec 2021
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN901 | FDNY- Solar PV at FDNY Academy Building 12 | 7 | CONSTRUCTION TO 75% | Dec 2021 | Apr 2022 | Dec 2021 | Apr 2022
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN901 | FDNY- Solar PV at FDNY Academy Building 12 | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2022 | Jul 2022 | Apr 2022 | Jul 2022
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN901 | FDNY- Solar PV at FDNY Academy Building 12 | 9 | SUBSTANTIAL COMPLETION | Jul 2022 | Sep 2022 | Jul 2022 | Sep 2022
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN901 | FDNY- Solar PV at FDNY Academy Building 12 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Oct 2022 | Sep 2022 | May 2024
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | F175KTE22 | KITCHENT RENOVATION - EC22 | 1 | DESIGN | Nov 2018 | Apr 2019 | Nov 2018 | May 2019
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | F175KTE22 | KITCHENT RENOVATION - EC22 | 2 | CONSTRUCTION | Apr 2019 | Apr 2020 | May 2019 | Apr 2020
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | F175KTE22 | KITCHENT RENOVATION - EC22 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2020 | Jul 2020 | May 2020 | Jun 2024
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE33 | Multi-Component Renovations - EC33 | 1 | DESIGN | Aug 2013 | Feb 2014 | Sep 2018 | Dec 2018
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE33 | Multi-Component Renovations - EC33 | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2014 | Feb 2015 | Dec 2018 | Sep 2019
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE33 | Multi-Component Renovations - EC33 | 3 | CONSTRUCTION | Feb 2015 | May 2015 | Sep 2019 | Oct 2020
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE33 | Multi-Component Renovations - EC33 | 4 | ORIGINAL EQUIP & FURNISHING | Feb 2015 | May 2015 | Oct 2020 | Dec 2020
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE33 | Multi-Component Renovations - EC33 | 5 | SUBSTANTIAL COMPLETION | Feb 2015 | May 2015 | Dec 2020 | Jan 2021
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE33 | Multi-Component Renovations - EC33 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2015 | May 2015 | Jan 2021 | Jun 2025
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE74 | Multi-Component Renovations - EC74 | 1 | DESIGN | Nov 2018 | Jan 2019 | Apr 2020 | Jun 2020
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE74 | Multi-Component Renovations - EC74 | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2019 | Oct 2019 | Jul 2020 | Mar 2021
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE74 | Multi-Component Renovations - EC74 | 3 | CONSTRUCTION | Oct 2019 | Nov 2020 | Mar 2021 | May 2022
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE74 | Multi-Component Renovations - EC74 | 4 | ORIGINAL EQUIP & FURNISHING | Nov 2020 | Jan 2021 | May 2022 | Jun 2022
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE74 | Multi-Component Renovations - EC74 | 5 | SUBSTANTIAL COMPLETION | Jan 2021 | Feb 2021 | Jun 2022 | Jul 2022
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE74 | Multi-Component Renovations - EC74 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Apr 2021 | Jul 2022 | Jun 2024
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE91 | Multi-Component Renovations - EC91 | 1 | DESIGN | Nov 2018 | Jan 2019 | Nov 2018 | Jan 2019
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE91 | Multi-Component Renovations - EC91 | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2019 | Oct 2019 | Jan 2019 | Oct 2019
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE91 | Multi-Component Renovations - EC91 | 3 | CONSTRUCTION | Oct 2019 | Nov 2020 | Oct 2019 | Nov 2020
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE91 | Multi-Component Renovations - EC91 | 4 | ORIGINAL EQUIP & FURNISHING | Nov 2020 | Jan 2021 | Nov 2020 | Jan 2021
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE91 | Multi-Component Renovations - EC91 | 5 | SUBSTANTIAL COMPLETION | Jan 2021 | Feb 2021 | Jan 2021 | Feb 2021
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE91 | Multi-Component Renovations - EC91 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Apr 2021 | Feb 2021 | Mar 2026
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCL20 | FIREHOUSE RENOVATIONS - LC20 | 1 | DESIGN | Dec 2012 | Jun 2013 | Sep 2018 | Dec 2018
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCL20 | FIREHOUSE RENOVATIONS - LC20 | 2 | CONSTRUCTION | Jun 2013 | Jun 2014 | Dec 2018 | Sep 2019
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCL20 | FIREHOUSE RENOVATIONS - LC20 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2014 | Sep 2014 | Sep 2019 | Oct 2020
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCL20 | FIREHOUSE RENOVATIONS - LC20 | 4 | ORIGINAL EQUIP & FURNISHING | Jun 2014 | Sep 2014 | Oct 2020 | Dec 2020
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCL20 | FIREHOUSE RENOVATIONS - LC20 | 5 | SUBSTANTIAL COMPLETION | Jun 2014 | Sep 2014 | Dec 2020 | Jan 2021
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCL20 | FIREHOUSE RENOVATIONS - LC20 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2014 | Sep 2014 | Jan 2021 | May 2026
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | F175RFE54 | ROOF AND WATERPROOFING - EC54 | 1 | DESIGN | Nov 2018 | Apr 2019 | Nov 2018 | May 2019
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | F175RFE54 | ROOF AND WATERPROOFING - EC54 | 2 | CONSTRUCTION | Apr 2019 | Apr 2020 | May 2019 | Apr 2020
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | F175RFE54 | ROOF AND WATERPROOFING - EC54 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2020 | Jul 2020 | May 2020 | Jun 2024
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175DE15 | DOOR REPLACEMENT - EC15 | 1 | CONSTRUCTION | Jul 2018 | Jul 2019 | Jul 2018 | Jul 2019
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175DE15 | DOOR REPLACEMENT - EC15 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2019 | Oct 2019 | Jul 2019 | Oct 2019
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175DE22 | Door Replacement - EC22 | 2 | CONSTRUCTION | Mar 2019 | Mar 2020 | Sep 2020 | Sep 2021
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175DE22 | Door Replacement - EC22 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Jun 2020 | Sep 2021 | Dec 2021
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175DE95 | Door Replacement - EC95 | 1 | DESIGN | Sep 2018 | Mar 2019 | Apr 2020 | Sep 2020
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175DE95 | Door Replacement - EC95 | 2 | CONSTRUCTION | Mar 2019 | Mar 2020 | Oct 2020 | Sep 2021
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175DE95 | Door Replacement - EC95 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Jun 2020 | Oct 2021 | Jun 2024
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175DRE5 | Door Replacement - EC5 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Jun 2020 | Oct 2021 | Dec 2021
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175DRS4 | SPEED DOOR - EMS STATION 4 | 1 | CONSTRUCTION | Jul 2024 | Jul 2025 | Jul 2024 | Jul 2025
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175DRS4 | SPEED DOOR - EMS STATION 4 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175DRS8 | SPEED DOOR - EMS STATION 8 | 1 | CONSTRUCTION | Nov 2023 | Nov 2024 | Nov 2023 | Nov 2024
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175DRS8 | SPEED DOOR - EMS STATION 8 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2024 | Feb 2025 | Nov 2024 | Feb 2025
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175GE95 | Generator - EC95 | 1 | DESIGN | Jan 2019 | Jul 2019 | Jan 2020 | Jul 2020
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175GE95 | Generator - EC95 | 2 | CONSTRUCTION | Jul 2019 | Jul 2020 | Jul 2020 | Jul 2021
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175GE95 | Generator - EC95 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Oct 2020 | Jul 2021 | Jun 2024
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175WHZT | WINDOWS REPLACEMENT - HAZMAT OPERATION BUILDING AT RANDALLS | 1 | DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175WHZT | WINDOWS REPLACEMENT - HAZMAT OPERATION BUILDING AT RANDALLS | 2 | CONSTRUCTION | Jun 2024 | Jun 2025 | Jun 2024 | Jun 2025
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175WHZT | WINDOWS REPLACEMENT - HAZMAT OPERATION BUILDING AT RANDALLS | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175WN22 | Windown Replacement - EC22 | 1 | DESIGN | Jan 2019 | Jul 2019 | Jan 2020 | Jul 2020
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175WN22 | Windown Replacement - EC22 | 2 | CONSTRUCTION | Jul 2019 | Jul 2020 | Jul 2020 | Jul 2021
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175WN22 | Windown Replacement - EC22 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Oct 2020 | Jul 2021 | May 2024
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175WN28 | Window Replacement - EC28 | 2 | CONSTRUCTION | Jul 2019 | Jul 2020 | Jul 2019 | Jul 2020
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175WN28 | Window Replacement - EC28 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Oct 2020 | Jul 2020 | Nov 2021
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175WN74 | Window Replacement - EC74 | 1 | DESIGN | Nov 2018 | Apr 2019 | Nov 2018 | Apr 2019
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175WN74 | Window Replacement - EC74 | 2 | CONSTRUCTION | Apr 2019 | Apr 2020 | Apr 2019 | Apr 2020
20231026 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175WN74 | Window Replacement - EC74 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2020 | Jul 2020 | Apr 2020 | May 2024
20231026 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | CAPC | CHINESE AMERICAN PLANNING COUNCIL | 1 | DESIGN | May 2011 | Nov 2011 | Jul 2025 | Jan 2026
20231026 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | CAPC | CHINESE AMERICAN PLANNING COUNCIL | 2 | CONSTRUCTION | Nov 2011 | May 2012 | Jan 2026 | Jun 2026
20231026 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | NSCC | Children's Center High Needs Unit | 1 | DESIGN | Oct 2014 | Mar 2015 | Jul 2026 | Jul 2026
20231026 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | NSCC | Children's Center High Needs Unit | 2 | CONSTRUCTION | Mar 2015 | Mar 2016 | Aug 2026 | Sep 2026
20231026 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | NSCC | Children's Center High Needs Unit | 3 | DEVELOP SCOPE | Mar 2015 | Mar 2016 | Oct 2026 | Dec 2026
20231026 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | NSCC | Children's Center High Needs Unit | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2015 | Mar 2016 | Jan 2027 | Apr 2027
20231026 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | NSCC | Children's Center High Needs Unit | 5 | CONSTRUCTION TO 50% | Mar 2015 | Mar 2016 | May 2027 | Jun 2027
20231026 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | NSCC | Children's Center High Needs Unit | 6 | CONSTRUCTION TO 75% | Mar 2015 | Mar 2016 | Jul 2027 | Aug 2027
20231026 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | NSCC | Children's Center High Needs Unit | 7 | SUBSTANTIAL COMPLETION | Mar 2015 | Mar 2016 | Sep 2027 | Dec 2027
20231026 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | NSCC | Children's Center High Needs Unit | 8 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Aug 2024 | Sep 2024
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112BLSB | BELLEVUE BASEMENT STRUCTURAL RECONSTRUCTION | 1 | DESIGN | Aug 2019 | Apr 2020 | Aug 2019 | Apr 2020
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112BLSB | BELLEVUE BASEMENT STRUCTURAL RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | Apr 2020 | Oct 2020 | Apr 2020 | Oct 2020
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112BLSB | BELLEVUE BASEMENT STRUCTURAL RECONSTRUCTION | 3 | CONSTRUCTION | Oct 2020 | Jul 2025 | Oct 2020 | Jul 2025
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112BLWB | BELLEVUE WEST BANK ELEVATORS | 1 | DESIGN | May 2023 | Feb 2024 | May 2023 | Feb 2024
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112BLWB | BELLEVUE WEST BANK ELEVATORS | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2024 | Aug 2024 | Feb 2024 | Aug 2024
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112BLWB | BELLEVUE WEST BANK ELEVATORS | 3 | CONSTRUCTION | Aug 2024 | May 2029 | Aug 2024 | May 2029
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112ETEU | 282 East 3rd Street, 10009 - Exterior Upgrade | 1 | DESIGN | Jan 2021 | Sep 2021 | Jan 2021 | Sep 2021
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112ETEU | 282 East 3rd Street, 10009 - Exterior Upgrade | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2021 | Mar 2022 | Sep 2021 | Mar 2022
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112ETEU | 282 East 3rd Street, 10009 - Exterior Upgrade | 3 | CONSTRUCTION | Mar 2022 | Dec 2026 | Mar 2022 | Dec 2026
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112FWBA | FORT WASHINGTON ARMORY- | 1 | DESIGN | Jan 2016 | Sep 2016 | Jan 2017 | Oct 2017
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112FWBA | FORT WASHINGTON ARMORY- | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2016 | Mar 2017 | Oct 2017 | Apr 2018
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112FWBA | FORT WASHINGTON ARMORY- | 3 | CONSTRUCTION | Mar 2017 | Jan 2021 | Apr 2018 | Jun 2025
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112FWBO | FT. WASHINGTON ARMORY - BOILER UPGRADE | 1 | DESIGN | Feb 2016 | Nov 2016 | Jan 2016 | Oct 2016
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112FWBO | FT. WASHINGTON ARMORY - BOILER UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2016 | May 2017 | Oct 2016 | Apr 2017
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112FWBO | FT. WASHINGTON ARMORY - BOILER UPGRADE | 3 | CONSTRUCTION | May 2017 | Feb 2022 | Apr 2017 | Jun 2024
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112FWFR | FORT WASHINGTON ARMORY-DORMITORIES FLOOR REPLACEMENT | 1 | DESIGN | Jan 2016 | Sep 2016 | Aug 2019 | Apr 2020
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112FWFR | FORT WASHINGTON ARMORY-DORMITORIES FLOOR REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2016 | Mar 2017 | Apr 2020 | Oct 2020
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112FWFR | FORT WASHINGTON ARMORY-DORMITORIES FLOOR REPLACEMENT | 3 | CONSTRUCTION | Mar 2017 | Jan 2021 | Oct 2020 | Jul 2024
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112GDFC | GEORGE DALY FACADE AND WINDOWS | 1 | DESIGN | May 2025 | Feb 2026 | May 2021 | Feb 2022
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112GDFC | GEORGE DALY FACADE AND WINDOWS | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2026 | Aug 2026 | Feb 2022 | Aug 2022
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112GDFC | GEORGE DALY FACADE AND WINDOWS | 3 | CONSTRUCTION | Aug 2026 | May 2031 | Aug 2022 | May 2027
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HBAT | HARLEM 1 BATHROOM RECONSTRUCTION | 1 | DESIGN | Jan 2019 | Sep 2019 | Jul 2025 | Mar 2026
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HBAT | HARLEM 1 BATHROOM RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Mar 2020 | Mar 2026 | Sep 2026
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HBAT | HARLEM 1 BATHROOM RECONSTRUCTION | 3 | CONSTRUCTION | Mar 2020 | Dec 2024 | Sep 2026 | Jun 2028
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HHAC | HARLEM 1 ROOF AND VENTILATION SYSTEM | 1 | DESIGN | Jan 2020 | Sep 2020 | Jan 2020 | Sep 2020
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HHAC | HARLEM 1 ROOF AND VENTILATION SYSTEM | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2020 | Mar 2021 | Sep 2020 | Mar 2021
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HHAC | HARLEM 1 ROOF AND VENTILATION SYSTEM | 3 | CONSTRUCTION | Mar 2021 | Dec 2025 | Mar 2021 | Dec 2025
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HINT | HARLEM 1 iNTERIOR RECONSTRUCTION | 1 | DESIGN | Jan 2020 | Sep 2020 | Jan 2020 | Sep 2020
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HINT | HARLEM 1 iNTERIOR RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2020 | Mar 2021 | Sep 2020 | Mar 2021
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HINT | HARLEM 1 iNTERIOR RECONSTRUCTION | 3 | CONSTRUCTION | Mar 2021 | Dec 2025 | Mar 2021 | Dec 2025
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HLET | HARLEM 1 ELECTRICAL UPGRADE | 1 | DESIGN | Jan 2020 | Sep 2020 | Jan 2020 | Sep 2020
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HLET | HARLEM 1 ELECTRICAL UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2020 | Mar 2021 | Sep 2020 | Mar 2021
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HLET | HARLEM 1 ELECTRICAL UPGRADE | 3 | CONSTRUCTION | Mar 2021 | Dec 2025 | Mar 2021 | Dec 2025
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HMED | HARLEM 1 - ELECTRICAL PANEL UPGRADE | 1 | DESIGN | Jan 2020 | Sep 2020 | Jan 2020 | Sep 2020
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HMED | HARLEM 1 - ELECTRICAL PANEL UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2020 | Mar 2021 | Sep 2020 | Mar 2021
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HMED | HARLEM 1 - ELECTRICAL PANEL UPGRADE | 3 | CONSTRUCTION | Mar 2021 | Dec 2025 | Mar 2021 | Dec 2025
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HSHP | HELP SEC.- HEATING AND PLUMBING | 1 | DESIGN | Jul 2023 | Mar 2024 | Jul 2023 | Mar 2024
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HSHP | HELP SEC.- HEATING AND PLUMBING | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2024 | Sep 2024 | Mar 2024 | Sep 2024
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HSHP | HELP SEC.- HEATING AND PLUMBING | 3 | CONSTRUCTION | Sep 2024 | Jun 2026 | Sep 2024 | Jun 2026
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HSMR | HELP SEC.-MAIN BLDG.ROOF REPLACEMENT | 1 | DESIGN | Jan 2019 | Sep 2019 | Jan 2019 | Sep 2019
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HSMR | HELP SEC.-MAIN BLDG.ROOF REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Mar 2020 | Sep 2019 | Mar 2020
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HSMR | HELP SEC.-MAIN BLDG.ROOF REPLACEMENT | 3 | CONSTRUCTION | Mar 2020 | Dec 2024 | Mar 2020 | Dec 2024
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KITC | PROJECT RENEWAL-EAST 3RD STREET KITCHEN NC#13-260288T82144 | 1 | DEVELOP SCOPE | Jan 2013 | Apr 2013 | May 2015 | Aug 2015
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KITC | PROJECT RENEWAL-EAST 3RD STREET KITCHEN NC#13-260288T82144 | 2 | PRELIMINARY DESIGN | Apr 2013 | Aug 2013 | Apr 2013 | Aug 2013
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KITC | PROJECT RENEWAL-EAST 3RD STREET KITCHEN NC#13-260288T82144 | 3 | FINAL DESIGN | Aug 2013 | Dec 2013 | Aug 2013 | Aug 2013
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KITC | PROJECT RENEWAL-EAST 3RD STREET KITCHEN NC#13-260288T82144 | 4 | BID AWARD AND REGISTER CONTRCT | Dec 2013 | Jun 2014 | Aug 2013 | Aug 2013
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KITC | PROJECT RENEWAL-EAST 3RD STREET KITCHEN NC#13-260288T82144 | 5 | CONSTRUCTION TO 25% | Jun 2014 | Oct 2014 | Aug 2013 | Aug 2013
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KITC | PROJECT RENEWAL-EAST 3RD STREET KITCHEN NC#13-260288T82144 | 6 | CONSTRUCTION TO 50% | Oct 2014 | Jan 2015 | Aug 2013 | Aug 2013
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KITC | PROJECT RENEWAL-EAST 3RD STREET KITCHEN NC#13-260288T82144 | 7 | CONSTRUCTION TO 75% | Jan 2015 | May 2015 | Aug 2013 | Apr 2027
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KITC | PROJECT RENEWAL-EAST 3RD STREET KITCHEN NC#13-260288T82144 | 8 | ORIGINAL EQUIP & FURNISHING | May 2015 | Aug 2015 | Apr 2027 | Apr 2027
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KITC | PROJECT RENEWAL-EAST 3RD STREET KITCHEN NC#13-260288T82144 | 9 | SUBSTANTIAL COMPLETION | Aug 2015 | Oct 2015 | Apr 2027 | Apr 2027
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KITC | PROJECT RENEWAL-EAST 3RD STREET KITCHEN NC#13-260288T82144 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2015 | Nov 2015 | Apr 2027 | May 2027
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KNUG | KEENER ASSESSMENT SHELTER - BUILDING UPGRADE | 1 | DESIGN | Jan 2023 | Sep 2023 | Jan 2023 | Sep 2023
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KNUG | KEENER ASSESSMENT SHELTER - BUILDING UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2023 | Mar 2024 | Sep 2023 | Mar 2024
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KNUG | KEENER ASSESSMENT SHELTER - BUILDING UPGRADE | 3 | CONSTRUCTION | Mar 2024 | Dec 2028 | Mar 2024 | Dec 2028
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KTEX | KENTON HALL - FACADE RECONSTRUCTION | 1 | DESIGN | May 2024 | Feb 2025 | May 2024 | Feb 2025
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KTEX | KENTON HALL - FACADE RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2025 | Aug 2025 | Feb 2025 | Aug 2025
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KTEX | KENTON HALL - FACADE RECONSTRUCTION | 3 | CONSTRUCTION | Aug 2025 | May 2030 | Aug 2025 | May 2030
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KTFR | FLUE REPLACEMENT AT KENTON HALL | 1 | CONSTRUCTION | Jan 2020 | Jan 2021 | Aug 2020 | May 2021
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KTFR | FLUE REPLACEMENT AT KENTON HALL | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2021 | Apr 2021 | May 2021 | Nov 2021
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KTFR | FLUE REPLACEMENT AT KENTON HALL | 3 | CONSTRUCTION | Jan 2021 | Apr 2021 | Nov 2021 | Aug 2023
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112PSST | PARK SLOPE- STABILIZATION - NEW PROJECT | 1 | DESIGN | Jul 2023 | Mar 2024 | Jul 2023 | Mar 2024
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112PSST | PARK SLOPE- STABILIZATION - NEW PROJECT | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2024 | Sep 2024 | Mar 2024 | Sep 2024
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112PSST | PARK SLOPE- STABILIZATION - NEW PROJECT | 3 | CONSTRUCTION | Sep 2024 | Jun 2027 | Sep 2024 | Jun 2027
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112RFEL | REGENT FAMILY APT. ELEC UPGRADE | 1 | DESIGN | Jul 2026 | Mar 2027 | Jul 2026 | Mar 2027
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112RFEL | REGENT FAMILY APT. ELEC UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2027 | Sep 2027 | Mar 2027 | Sep 2027
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112RFEL | REGENT FAMILY APT. ELEC UPGRADE | 3 | CONSTRUCTION | Sep 2027 | Dec 2030 | Sep 2027 | Dec 2030
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112SWBU | Schwartz Homeless Shelter | 1 | DESIGN | Jan 2022 | Sep 2022 | Jan 2022 | Sep 2022
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112SWBU | Schwartz Homeless Shelter | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2022 | Mar 2023 | Sep 2022 | Mar 2023
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112SWBU | Schwartz Homeless Shelter | 3 | CONSTRUCTION | Mar 2023 | Dec 2027 | Mar 2023 | Dec 2027
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112THBH | 8 EAST THIRD ST BATHROOM RECONSTRUCTION | 1 | DESIGN | Jun 2018 | Feb 2019 | Jul 2024 | Mar 2025
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112THBH | 8 EAST THIRD ST BATHROOM RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2019 | Aug 2019 | Mar 2025 | Sep 2025
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112THBH | 8 EAST THIRD ST BATHROOM RECONSTRUCTION | 3 | CONSTRUCTION | Aug 2019 | May 2024 | Sep 2025 | Jun 2030
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112THBR | 282 EAST THIRD ST BOILER RECONSTRUCTION | 1 | DESIGN | Jul 2020 | Dec 2020 | Jul 2020 | Mar 2021
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112THBR | 282 EAST THIRD ST BOILER RECONSTRUCTION | 2 | CONSTRUCTION | Dec 2020 | Dec 2021 | Mar 2021 | Sep 2021
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112THBR | 282 EAST THIRD ST BOILER RECONSTRUCTION | 3 | CONSTRUCTION | Dec 2020 | Dec 2021 | Sep 2021 | Jun 2026
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112THEV | 8 EAST THIRD STREET ELEVATOR REHABILITATION | 1 | DESIGN | Jun 2021 | Feb 2022 | Jun 2021 | Feb 2022
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112THEV | 8 EAST THIRD STREET ELEVATOR REHABILITATION | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2022 | Aug 2022 | Feb 2022 | Aug 2022
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112THEV | 8 EAST THIRD STREET ELEVATOR REHABILITATION | 3 | CONSTRUCTION | Aug 2022 | May 2025 | Aug 2022 | May 2025
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112THFC | 8 EAST THIRD ST SHELTER FACADE AND STAIRS | 1 | DESIGN | May 2021 | Feb 2022 | May 2021 | Feb 2022
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112THFC | 8 EAST THIRD ST SHELTER FACADE AND STAIRS | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2022 | Aug 2022 | Feb 2022 | Aug 2022
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112THFC | 8 EAST THIRD ST SHELTER FACADE AND STAIRS | 3 | CONSTRUCTION | Aug 2022 | May 2027 | Aug 2022 | May 2027
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115CTBU | 78 CATHERINE STREET - BATHROOM UPGRADE | 1 | DESIGN | Aug 2016 | Apr 2017 | Aug 2016 | Apr 2017
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115CTBU | 78 CATHERINE STREET - BATHROOM UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Apr 2017 | Oct 2017 | Apr 2017 | Oct 2017
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115CTBU | 78 CATHERINE STREET - BATHROOM UPGRADE | 3 | CONSTRUCTION | Oct 2017 | Aug 2022 | Oct 2017 | Jun 2024
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115CTEF | CATHERINE STREET ELECTRICAL UPGRADE | 1 | DESIGN | Jan 2019 | Sep 2019 | May 2017 | Feb 2018
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115CTEF | CATHERINE STREET ELECTRICAL UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Mar 2020 | Feb 2018 | Aug 2018
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115CTEF | CATHERINE STREET ELECTRICAL UPGRADE | 3 | CONSTRUCTION | Mar 2020 | Dec 2024 | Aug 2018 | Jun 2030
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115JCFA | JENNIE CLARKE BACKFLOW PREVENTER | 1 | DESIGN | Jan 2022 | Sep 2022 | Jul 2025 | Mar 2026
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115JCFA | JENNIE CLARKE BACKFLOW PREVENTER | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2022 | Mar 2023 | Mar 2026 | Sep 2026
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115JCFA | JENNIE CLARKE BACKFLOW PREVENTER | 3 | CONSTRUCTION | Mar 2023 | Dec 2027 | Sep 2026 | Jun 2029
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115REBO | REGENT BOILER | 1 | DESIGN | Jan 2020 | Sep 2020 | Jan 2020 | Sep 2020
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115REBO | REGENT BOILER | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2020 | Mar 2021 | Sep 2020 | Mar 2021
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115REBO | REGENT BOILER | 3 | CONSTRUCTION | Mar 2021 | Dec 2025 | Mar 2021 | Dec 2025
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RECL | REGENT CEILINGS | 1 | DESIGN | Aug 2016 | Apr 2017 | Mar 2018 | Dec 2018
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RECL | REGENT CEILINGS | 2 | BID AWARD AND REGISTER CONTRCT | Apr 2017 | Oct 2017 | Dec 2018 | Jun 2019
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RECL | REGENT CEILINGS | 3 | CONSTRUCTION | Oct 2017 | Aug 2022 | Jun 2019 | Jun 2027
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RFRE | REGENT FAMILY RESIDENCE LIFE SAFETY UPGRADE, FIRE SAFETY | 1 | DESIGN | Jan 2013 | Apr 2013 | Jun 2014 | Mar 2015
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RFRE | REGENT FAMILY RESIDENCE LIFE SAFETY UPGRADE, FIRE SAFETY | 2 | BID AWARD AND REGISTER CONTRCT | Apr 2013 | Aug 2013 | Mar 2015 | Sep 2015
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RFRE | REGENT FAMILY RESIDENCE LIFE SAFETY UPGRADE, FIRE SAFETY | 3 | CONSTRUCTION | Aug 2013 | Dec 2013 | Sep 2015 | Jun 2024
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RFRE | REGENT FAMILY RESIDENCE LIFE SAFETY UPGRADE, FIRE SAFETY | 4 | BID AWARD AND REGISTER CONTRCT | Dec 2013 | Jun 2014 | Sep 2015 | Jun 2024
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RFRE | REGENT FAMILY RESIDENCE LIFE SAFETY UPGRADE, FIRE SAFETY | 5 | CONSTRUCTION TO 25% | Jun 2014 | Oct 2014 | Sep 2015 | Jun 2024
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RFRE | REGENT FAMILY RESIDENCE LIFE SAFETY UPGRADE, FIRE SAFETY | 6 | CONSTRUCTION TO 50% | Oct 2014 | Feb 2015 | Sep 2015 | Jun 2024
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RFRE | REGENT FAMILY RESIDENCE LIFE SAFETY UPGRADE, FIRE SAFETY | 7 | CONSTRUCTION TO 75% | Feb 2015 | Jun 2015 | Sep 2015 | Jun 2024
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RFRE | REGENT FAMILY RESIDENCE LIFE SAFETY UPGRADE, FIRE SAFETY | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2015 | Aug 2015 | Sep 2015 | Jun 2024
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RFRE | REGENT FAMILY RESIDENCE LIFE SAFETY UPGRADE, FIRE SAFETY | 9 | SUBSTANTIAL COMPLETION | Sep 2015 | Oct 2015 | Sep 2015 | Jun 2024
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RFRE | REGENT FAMILY RESIDENCE LIFE SAFETY UPGRADE, FIRE SAFETY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2015 | Nov 2015 | Sep 2015 | Jun 2024
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHCN007 | INSTALLATION OF BACKUP GENERATOR | 1 | DEVELOP SCOPE | Jul 2016 | Sep 2016 | Jul 2022 | Mar 2023
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHCN007 | INSTALLATION OF BACKUP GENERATOR | 2 | PRELIMINARY DESIGN | Oct 2016 | Jan 2017 | Mar 2023 | Sep 2023
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHCN007 | INSTALLATION OF BACKUP GENERATOR | 3 | FINAL DESIGN | Jan 2017 | May 2017 | Sep 2023 | Jun 2028
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHCN007 | INSTALLATION OF BACKUP GENERATOR | 4 | BID AWARD AND REGISTER CONTRCT | May 2017 | Nov 2017 | Sep 2023 | Jun 2028
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHCN007 | INSTALLATION OF BACKUP GENERATOR | 5 | CONSTRUCTION TO 25% | Nov 2017 | Mar 2018 | Sep 2023 | Jun 2028
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHCN007 | INSTALLATION OF BACKUP GENERATOR | 6 | CONSTRUCTION TO 50% | Mar 2018 | Jul 2018 | Sep 2023 | Jun 2028
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHCN007 | INSTALLATION OF BACKUP GENERATOR | 7 | CONSTRUCTION TO 75% | Jul 2018 | Nov 2018 | Sep 2023 | Jun 2028
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHCN007 | INSTALLATION OF BACKUP GENERATOR | 8 | ORIGINAL EQUIP & FURNISHING | Nov 2018 | Feb 2019 | Sep 2023 | Jun 2028
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHCN007 | INSTALLATION OF BACKUP GENERATOR | 9 | SUBSTANTIAL COMPLETION | Feb 2019 | Apr 2019 | Sep 2023 | Jun 2028
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHCN007 | INSTALLATION OF BACKUP GENERATOR | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2019 | May 2019 | Sep 2023 | Jun 2028
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHNC005 | KITCHEN RENOVATION AT 8 EAST THIRD STREET HOMELESS SHELTER | 1 | DESIGN | Jul 2019 | Mar 2020 | Jul 2019 | Mar 2020
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHNC005 | KITCHEN RENOVATION AT 8 EAST THIRD STREET HOMELESS SHELTER | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Sep 2020 | Mar 2020 | Sep 2020
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHNC005 | KITCHEN RENOVATION AT 8 EAST THIRD STREET HOMELESS SHELTER | 3 | CONSTRUCTION | Sep 2020 | Jun 2025 | Sep 2020 | Jun 2025
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHNC006 | FORT WASHINGTON ARMORY - ENTRYWAY REPAIR | 1 | DESIGN | Jul 2019 | Mar 2020 | Jul 2019 | Mar 2020
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHNC006 | FORT WASHINGTON ARMORY - ENTRYWAY REPAIR | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Sep 2020 | Mar 2020 | Sep 2020
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHNC006 | FORT WASHINGTON ARMORY - ENTRYWAY REPAIR | 3 | CONSTRUCTION | Sep 2020 | Jun 2025 | Sep 2020 | Jun 2025
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HLCN014 | PROJECT RENEWAL , INC. - NEW PROVIDENCE BACKUP GENERATOR | 1 | DESIGN | Dec 2016 | Sep 2017 | Jan 2025 | Jun 2025
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HLCN014 | PROJECT RENEWAL , INC. - NEW PROVIDENCE BACKUP GENERATOR | 2 | CONSTRUCTION | Sep 2017 | Mar 2018 | Jun 2025 | Jun 2027
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HLCN014 | PROJECT RENEWAL , INC. - NEW PROVIDENCE BACKUP GENERATOR | 3 | CONSTRUCTION | Mar 2018 | Dec 2022 | Jun 2025 | Jun 2027
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HRNC0031 | PROJECT RENEWAL, INC./THIRD STREET SHELTER - Kitchen | 1 | DESIGN | Jul 2022 | Jul 2022 | Jul 2022 | Jul 2022
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HRNC0031 | PROJECT RENEWAL, INC./THIRD STREET SHELTER - Kitchen | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Aug 2022 | Jul 2022 | Aug 2022
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HRNC0031 | PROJECT RENEWAL, INC./THIRD STREET SHELTER - Kitchen | 3 | CONSTRUCTION | Aug 2022 | Sep 2022 | Aug 2022 | Sep 2022
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HRNC0031 | PROJECT RENEWAL, INC./THIRD STREET SHELTER - Kitchen | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Sep 2022 | Sep 2022 | Sep 2022
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HRNC0031 | PROJECT RENEWAL, INC./THIRD STREET SHELTER - Kitchen | 5 | SUBSTANTIAL COMPLETION | Sep 2022 | Oct 2022 | Sep 2022 | Oct 2022
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HRNC0031 | PROJECT RENEWAL, INC./THIRD STREET SHELTER - Kitchen | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2022 | Jun 2023 | Oct 2022 | Jun 2024
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS1 | Solar PV system - HELP SEC at 111 Sunken Garden Loop | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2020 | Jun 2019 | Feb 2020
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS1 | Solar PV system - HELP SEC at 111 Sunken Garden Loop | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Aug 2020 | Feb 2020 | Aug 2020
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS1 | Solar PV system - HELP SEC at 111 Sunken Garden Loop | 3 | CONSTRUCTION TO 50% | Aug 2020 | Feb 2021 | Aug 2020 | Jun 2025
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS1 | Solar PV system - HELP SEC at 111 Sunken Garden Loop | 4 | CONSTRUCTION TO 75% | Feb 2021 | May 2021 | Aug 2020 | Jun 2025
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS1 | Solar PV system - HELP SEC at 111 Sunken Garden Loop | 5 | SUBSTANTIAL COMPLETION | May 2021 | Jul 2021 | Aug 2020 | Jun 2025
20231026 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS1 | Solar PV system - HELP SEC at 111 Sunken Garden Loop | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Aug 2021 | Aug 2020 | Jun 2025
20231026 | MANHATTAN | 072 | DEPARTMENT OF CORRECTION | C75WTRMN | Replace Water Mains on Rikers Island | 1 | DESIGN | Dec 2015 | Sep 2016 | Dec 2015 | Sep 2016
20231026 | MANHATTAN | 072 | DEPARTMENT OF CORRECTION | C75WTRMN | Replace Water Mains on Rikers Island | 2 | BID AWARD AND REGISTER CONTRCT | Oct 2016 | Sep 2017 | Oct 2016 | Sep 2017
20231026 | MANHATTAN | 072 | DEPARTMENT OF CORRECTION | C75WTRMN | Replace Water Mains on Rikers Island | 3 | CONSTRUCTION TO 75% | Oct 2017 | May 2019 | Oct 2017 | May 2019
20231026 | MANHATTAN | 072 | DEPARTMENT OF CORRECTION | C75WTRMN | Replace Water Mains on Rikers Island | 4 | SUBSTANTIAL COMPLETION | May 2019 | Sep 2019 | May 2019 | Sep 2019
20231026 | MANHATTAN | 072 | DEPARTMENT OF CORRECTION | C75WTRMN | Replace Water Mains on Rikers Island | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2025
20231026 | MANHATTAN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25CHRYC | 115 Chrystie Street Construction | 1 | DESIGN | Nov 2019 | Apr 2020 | Jul 2026 | Dec 2026
20231026 | MANHATTAN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25CHRYC | 115 Chrystie Street Construction | 2 | CONSTRUCTION | Apr 2020 | Oct 2020 | Dec 2026 | Jun 2027
20231026 | MANHATTAN | 125 | DEPARTMENT FOR THE AGING | AGCBCOV | CARTER BURDEN/LEONARD COVELLO | 1 | DEVELOP SCOPE | Jun 2022 | Nov 2022 | Jun 2026 | Nov 2026
20231026 | MANHATTAN | 125 | DEPARTMENT FOR THE AGING | AGCBCOV | CARTER BURDEN/LEONARD COVELLO | 2 | PRELIMINARY DESIGN | Nov 2022 | May 2023 | Nov 2026 | May 2027
20231026 | MANHATTAN | 125 | DEPARTMENT FOR THE AGING | AGCBCOV | CARTER BURDEN/LEONARD COVELLO | 3 | CONSTRUCTION | May 2023 | May 2024 | May 2027 | May 2028
20231026 | MANHATTAN | 125 | DEPARTMENT FOR THE AGING | AGCBURDEN | LEONARD COVELLO Kitchen Renovation | 1 | DEVELOP SCOPE | Jun 2022 | Nov 2022 | May 2024 | Nov 2024
20231026 | MANHATTAN | 125 | DEPARTMENT FOR THE AGING | AGCBURDEN | LEONARD COVELLO Kitchen Renovation | 2 | PRELIMINARY DESIGN | Nov 2022 | May 2023 | Nov 2024 | May 2025
20231026 | MANHATTAN | 125 | DEPARTMENT FOR THE AGING | AGCBURDEN | LEONARD COVELLO Kitchen Renovation | 3 | CONSTRUCTION | May 2023 | May 2024 | May 2025 | May 2028
20231026 | MANHATTAN | 125 | DEPARTMENT FOR THE AGING | HAM14CRSR | CARVER HOUSES SENIOR CENTER COMPUTER LAB | 1 | DEVELOP SCOPE | Jun 2023 | Nov 2023 | May 2025 | Nov 2025
20231026 | MANHATTAN | 125 | DEPARTMENT FOR THE AGING | HAM14CRSR | CARVER HOUSES SENIOR CENTER COMPUTER LAB | 2 | PRELIMINARY DESIGN | Nov 2023 | May 2024 | Nov 2025 | May 2026
20231026 | MANHATTAN | 125 | DEPARTMENT FOR THE AGING | HAM14CRSR | CARVER HOUSES SENIOR CENTER COMPUTER LAB | 3 | CONSTRUCTION | May 2024 | May 2025 | May 2026 | May 2027
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022AAOA | MMA- Metropolitan Museum AAOA Gallery | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2025 | Sep 2025
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022AAOA | MMA- Metropolitan Museum AAOA Gallery | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2022 | Dec 2022 | Sep 2025 | Dec 2025
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022AAOA | MMA- Metropolitan Museum AAOA Gallery | 3 | CONSTRUCTION TO 50% | Dec 2022 | Apr 2023 | Dec 2025 | Apr 2026
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022AAOA | MMA- Metropolitan Museum AAOA Gallery | 4 | CONSTRUCTION TO 75% | Apr 2023 | Jun 2023 | Apr 2026 | Jun 2026
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022AAOA | MMA- Metropolitan Museum AAOA Gallery | 5 | SUBSTANTIAL COMPLETION | Jun 2023 | Aug 2023 | Jun 2026 | Aug 2026
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022AAOA | MMA- Metropolitan Museum AAOA Gallery | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2023 | Sep 2023 | Aug 2026 | Sep 2026
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022ANEG | MMA -Ancient Near East Gallery Renovation | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2028 | Sep 2028
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022ANEG | MMA -Ancient Near East Gallery Renovation | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2028 | Jan 2029
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022ANEG | MMA -Ancient Near East Gallery Renovation | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2029 | Jul 2029
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022ANEG | MMA -Ancient Near East Gallery Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2029 | Oct 2029
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022ANEG | MMA -Ancient Near East Gallery Renovation | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2029 | Feb 2030
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022ANEG | MMA -Ancient Near East Gallery Renovation | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2030 | Jun 2030
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022ANEG | MMA -Ancient Near East Gallery Renovation | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2030 | Oct 2030
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022ANEG | MMA -Ancient Near East Gallery Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2030 | Jan 2031
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022ANEG | MMA -Ancient Near East Gallery Renovation | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2031 | Mar 2031
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022ANEG | MMA -Ancient Near East Gallery Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2031 | Apr 2031
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV034-INF | AMNH - Security & Infrastructure Upgrade | 1 | DESIGN | Jun 2003 | Dec 2003 | Jun 2024 | Dec 2024
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV034-INF | AMNH - Security & Infrastructure Upgrade | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2003 | Mar 2004 | Dec 2024 | Mar 2025
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV034-INF | AMNH - Security & Infrastructure Upgrade | 3 | CONSTRUCTION | Mar 2004 | Mar 2005 | Mar 2025 | Mar 2026
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV034-INF | AMNH - Security & Infrastructure Upgrade | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2005 | Sep 2005 | Mar 2026 | Sep 2026
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV034RR77 | AMNH - Slate Roof & HVAC | 1 | DEVELOP SCOPE | Jun 2027 | Sep 2027 | Jun 2027 | Sep 2027
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV034RR77 | AMNH - Slate Roof & HVAC | 2 | PRELIMINARY DESIGN | Sep 2027 | Jan 2028 | Sep 2027 | Jan 2028
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV034RR77 | AMNH - Slate Roof & HVAC | 3 | FINAL DESIGN | Jan 2028 | Jul 2028 | Jan 2028 | Jul 2028
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV034RR77 | AMNH - Slate Roof & HVAC | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2028 | Oct 2028 | Jul 2028 | Oct 2028
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV034RR77 | AMNH - Slate Roof & HVAC | 5 | CONSTRUCTION TO 25% | Oct 2028 | Feb 2029 | Oct 2028 | Feb 2029
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV034RR77 | AMNH - Slate Roof & HVAC | 6 | CONSTRUCTION TO 50% | Feb 2029 | Jun 2029 | Feb 2029 | Jun 2029
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV034RR77 | AMNH - Slate Roof & HVAC | 7 | CONSTRUCTION TO 75% | Jun 2029 | Oct 2029 | Jun 2029 | Oct 2029
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV034RR77 | AMNH - Slate Roof & HVAC | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2029 | Jan 2030 | Oct 2029 | Jan 2030
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV034RR77 | AMNH - Slate Roof & HVAC | 9 | SUBSTANTIAL COMPLETION | Jan 2030 | Mar 2030 | Jan 2030 | Mar 2030
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV034RR77 | AMNH - Slate Roof & HVAC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2030 | Apr 2030 | Mar 2030 | Apr 2030
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV101HVAC | MJH - Museum HVAC | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2027 | Sep 2027
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV101HVAC | MJH - Museum HVAC | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2027 | Jan 2028
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV101HVAC | MJH - Museum HVAC | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2028 | Jul 2028
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV101HVAC | MJH - Museum HVAC | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2028 | Oct 2028
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV101HVAC | MJH - Museum HVAC | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2028 | Feb 2029
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV101HVAC | MJH - Museum HVAC | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2029 | Jun 2029
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV101HVAC | MJH - Museum HVAC | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2029 | Oct 2029
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV101HVAC | MJH - Museum HVAC | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2029 | Jan 2030
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV101HVAC | MJH - Museum HVAC | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2030 | Mar 2030
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV101HVAC | MJH - Museum HVAC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2030 | Apr 2030
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV219-HLD | MCC - Fresh Air Intake | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2028 | Sep 2028
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV219-HLD | MCC - Fresh Air Intake | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2028 | Jan 2029
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV219-HLD | MCC - Fresh Air Intake | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2029 | Jul 2029
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV219-HLD | MCC - Fresh Air Intake | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2029 | Oct 2029
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV219-HLD | MCC - Fresh Air Intake | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2029 | Feb 2030
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV219-HLD | MCC - Fresh Air Intake | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2030 | Jun 2030
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV219-HLD | MCC - Fresh Air Intake | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2030 | Oct 2030
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV219-HLD | MCC - Fresh Air Intake | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2030 | Jan 2031
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV219-HLD | MCC - Fresh Air Intake | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2031 | Mar 2031
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV219-HLD | MCC - Fresh Air Intake | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2031 | Apr 2031
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241BOIL | MCNY - Boiler Replacement | 1 | DEVELOP SCOPE | Jan 2011 | Mar 2011 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241BOIL | MCNY - Boiler Replacement | 2 | PRELIMINARY DESIGN | Apr 2011 | Jul 2011 | Sep 2023 | Jan 2024
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241BOIL | MCNY - Boiler Replacement | 3 | FINAL DESIGN | Jul 2011 | Jan 2012 | Jan 2024 | Jul 2024
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241BOIL | MCNY - Boiler Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2012 | Apr 2012 | Jul 2024 | Oct 2024
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241BOIL | MCNY - Boiler Replacement | 5 | CONSTRUCTION TO 25% | Apr 2012 | Aug 2012 | Oct 2024 | Feb 2025
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241BOIL | MCNY - Boiler Replacement | 6 | CONSTRUCTION TO 50% | Aug 2012 | Dec 2012 | Feb 2025 | Jun 2025
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241BOIL | MCNY - Boiler Replacement | 7 | CONSTRUCTION TO 75% | Dec 2012 | Apr 2013 | Jun 2025 | Oct 2025
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241BOIL | MCNY - Boiler Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2013 | Jul 2013 | Oct 2025 | Jan 2026
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241BOIL | MCNY - Boiler Replacement | 9 | SUBSTANTIAL COMPLETION | Jul 2013 | Sep 2013 | Jan 2026 | Mar 2026
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241BOIL | MCNY - Boiler Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2013 | Oct 2013 | Mar 2026 | Apr 2026
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ACON | NYCC - NY City Center Chiller Replacement | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2024 | Sep 2024
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ACON | NYCC - NY City Center Chiller Replacement | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ACON | NYCC - NY City Center Chiller Replacement | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2025 | Jul 2025
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ACON | NYCC - NY City Center Chiller Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2025 | Oct 2025
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ACON | NYCC - NY City Center Chiller Replacement | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2025 | Feb 2026
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ACON | NYCC - NY City Center Chiller Replacement | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2026 | Jun 2026
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ACON | NYCC - NY City Center Chiller Replacement | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2026 | Oct 2026
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ACON | NYCC - NY City Center Chiller Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2026 | Jan 2027
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ACON | NYCC - NY City Center Chiller Replacement | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2027 | Mar 2027
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ACON | NYCC - NY City Center Chiller Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2027 | Apr 2027
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ELV2 | NYCC - HOUSE RIGHT LOBBY ELEVATOR | 1 | DEVELOP SCOPE | Jun 2028 | Sep 2028 | Jun 2028 | Sep 2028
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ELV2 | NYCC - HOUSE RIGHT LOBBY ELEVATOR | 2 | PRELIMINARY DESIGN | Sep 2028 | Jan 2029 | Sep 2028 | Jan 2029
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ELV2 | NYCC - HOUSE RIGHT LOBBY ELEVATOR | 3 | FINAL DESIGN | Jan 2029 | Jul 2029 | Jan 2029 | Jul 2029
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ELV2 | NYCC - HOUSE RIGHT LOBBY ELEVATOR | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2029 | Oct 2029 | Jul 2029 | Oct 2029
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ELV2 | NYCC - HOUSE RIGHT LOBBY ELEVATOR | 5 | CONSTRUCTION TO 25% | Oct 2029 | Feb 2030 | Oct 2029 | Feb 2030
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ELV2 | NYCC - HOUSE RIGHT LOBBY ELEVATOR | 6 | CONSTRUCTION TO 50% | Feb 2030 | Jun 2030 | Feb 2030 | Jun 2030
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ELV2 | NYCC - HOUSE RIGHT LOBBY ELEVATOR | 7 | CONSTRUCTION TO 75% | Jun 2030 | Oct 2030 | Jun 2030 | Oct 2030
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ELV2 | NYCC - HOUSE RIGHT LOBBY ELEVATOR | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2030 | Jan 2031 | Oct 2030 | Jan 2031
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ELV2 | NYCC - HOUSE RIGHT LOBBY ELEVATOR | 9 | SUBSTANTIAL COMPLETION | Jan 2031 | Mar 2031 | Jan 2031 | Mar 2031
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ELV2 | NYCC - HOUSE RIGHT LOBBY ELEVATOR | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2031 | Apr 2031 | Mar 2031 | Apr 2031
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV289ANSP | NYSF - Anspacher Theater Ceiling Reconstruction | 1 | DEVELOP SCOPE | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV289ANSP | NYSF - Anspacher Theater Ceiling Reconstruction | 2 | PRELIMINARY DESIGN | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV289ANSP | NYSF - Anspacher Theater Ceiling Reconstruction | 3 | FINAL DESIGN | Jan 2026 | Jul 2026 | Jan 2026 | Jul 2026
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV289ANSP | NYSF - Anspacher Theater Ceiling Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2026 | Oct 2026 | Jul 2026 | Oct 2026
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV289ANSP | NYSF - Anspacher Theater Ceiling Reconstruction | 5 | CONSTRUCTION TO 25% | Oct 2026 | Feb 2027 | Oct 2026 | Feb 2027
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV289ANSP | NYSF - Anspacher Theater Ceiling Reconstruction | 6 | CONSTRUCTION TO 50% | Feb 2027 | Jun 2027 | Feb 2027 | Jun 2027
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV289ANSP | NYSF - Anspacher Theater Ceiling Reconstruction | 7 | CONSTRUCTION TO 75% | Jun 2027 | Oct 2027 | Jun 2027 | Oct 2027
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV289ANSP | NYSF - Anspacher Theater Ceiling Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jan 2028 | Oct 2027 | Jan 2028
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV289ANSP | NYSF - Anspacher Theater Ceiling Reconstruction | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Mar 2028 | Jan 2028 | Mar 2028
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV289ANSP | NYSF - Anspacher Theater Ceiling Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2028 | Apr 2028 | Mar 2028 | Apr 2028
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467HOLD | FUND BALANCE 467 EX | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2028 | Sep 2028
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467HOLD | FUND BALANCE 467 EX | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2028 | Jan 2029
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467HOLD | FUND BALANCE 467 EX | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2029 | Jul 2029
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467HOLD | FUND BALANCE 467 EX | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2029 | Oct 2029
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467HOLD | FUND BALANCE 467 EX | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2029 | Feb 2030
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467HOLD | FUND BALANCE 467 EX | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2030 | Jun 2030
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467HOLD | FUND BALANCE 467 EX | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2030 | Oct 2030
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467HOLD | FUND BALANCE 467 EX | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2030 | Jan 2031
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467HOLD | FUND BALANCE 467 EX | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2031 | Mar 2031
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467HOLD | FUND BALANCE 467 EX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2031 | Apr 2031
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467NEWC | ELM- El Museo del Barrio Renovation | 1 | DEVELOP SCOPE | Dec 2028 | Feb 2029 | Dec 2028 | Feb 2029
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467NEWC | ELM- El Museo del Barrio Renovation | 2 | PRELIMINARY DESIGN | Mar 2029 | Jun 2029 | Mar 2029 | Jun 2029
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467NEWC | ELM- El Museo del Barrio Renovation | 3 | FINAL DESIGN | Jun 2029 | Dec 2029 | Jun 2029 | Dec 2029
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467NEWC | ELM- El Museo del Barrio Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Dec 2029 | Mar 2030 | Dec 2029 | Mar 2030
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467NEWC | ELM- El Museo del Barrio Renovation | 5 | CONSTRUCTION TO 25% | Mar 2030 | Jul 2030 | Mar 2030 | Jul 2030
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467NEWC | ELM- El Museo del Barrio Renovation | 6 | CONSTRUCTION TO 50% | Jul 2030 | Nov 2030 | Jul 2030 | Nov 2030
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467NEWC | ELM- El Museo del Barrio Renovation | 7 | CONSTRUCTION TO 75% | Nov 2030 | Mar 2031 | Nov 2030 | Mar 2031
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467NEWC | ELM- El Museo del Barrio Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2031 | Jun 2031 | Mar 2031 | Jun 2031
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467NEWC | ELM- El Museo del Barrio Renovation | 9 | SUBSTANTIAL COMPLETION | Jun 2031 | Aug 2031 | Jun 2031 | Aug 2031
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467NEWC | ELM- El Museo del Barrio Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2031 | Sep 2031 | Aug 2031 | Sep 2031
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV475-SND | NYST - Sound System & ADA Listening Devices | 1 | DEVELOP SCOPE | Jun 2027 | Sep 2027 | Jun 2027 | Sep 2027
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV475-SND | NYST - Sound System & ADA Listening Devices | 2 | PRELIMINARY DESIGN | Sep 2027 | Jan 2028 | Sep 2027 | Jan 2028
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV475-SND | NYST - Sound System & ADA Listening Devices | 3 | FINAL DESIGN | Jan 2028 | Jul 2028 | Jan 2028 | Jul 2028
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV475-SND | NYST - Sound System & ADA Listening Devices | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2028 | Oct 2028 | Jul 2028 | Oct 2028
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV475-SND | NYST - Sound System & ADA Listening Devices | 5 | CONSTRUCTION TO 25% | Oct 2028 | Feb 2029 | Oct 2028 | Feb 2029
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV475-SND | NYST - Sound System & ADA Listening Devices | 6 | CONSTRUCTION TO 50% | Feb 2029 | Jun 2029 | Feb 2029 | Jun 2029
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV475-SND | NYST - Sound System & ADA Listening Devices | 7 | CONSTRUCTION TO 75% | Jun 2029 | Oct 2029 | Jun 2029 | Oct 2029
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV475-SND | NYST - Sound System & ADA Listening Devices | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2029 | Jan 2030 | Oct 2029 | Jan 2030
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV475-SND | NYST - Sound System & ADA Listening Devices | 9 | SUBSTANTIAL COMPLETION | Jan 2030 | Mar 2030 | Jan 2030 | Mar 2030
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV475-SND | NYST - Sound System & ADA Listening Devices | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2030 | Apr 2030 | Mar 2030 | Apr 2030
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503FACD | CH - CARNEGIE HALL Historic Facade Restoration | 1 | DEVELOP SCOPE | Jul 2025 | Sep 2025 | Jun 2023 | Aug 2023
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503FACD | CH - CARNEGIE HALL Historic Facade Restoration | 2 | PRELIMINARY DESIGN | Sep 2025 | Jan 2026 | Aug 2023 | Dec 2023
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503FACD | CH - CARNEGIE HALL Historic Facade Restoration | 3 | FINAL DESIGN | Jan 2026 | Jul 2026 | Dec 2023 | Jun 2024
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503FACD | CH - CARNEGIE HALL Historic Facade Restoration | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2026 | Oct 2026 | Jun 2024 | Sep 2024
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503FACD | CH - CARNEGIE HALL Historic Facade Restoration | 5 | CONSTRUCTION TO 25% | Oct 2026 | Feb 2027 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503FACD | CH - CARNEGIE HALL Historic Facade Restoration | 6 | CONSTRUCTION TO 50% | Feb 2027 | Jun 2027 | Jan 2025 | May 2025
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503FACD | CH - CARNEGIE HALL Historic Facade Restoration | 7 | CONSTRUCTION TO 75% | Jun 2027 | Oct 2027 | May 2025 | Sep 2025
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503FACD | CH - CARNEGIE HALL Historic Facade Restoration | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jan 2028 | Sep 2025 | Dec 2025
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503FACD | CH - CARNEGIE HALL Historic Facade Restoration | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Mar 2028 | Dec 2025 | Feb 2026
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503FACD | CH - CARNEGIE HALL Historic Facade Restoration | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2028 | Apr 2028 | Feb 2026 | Mar 2026
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-TER | 122C - 122 Community Center Roof Terrace | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2026 | Sep 2026
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-TER | 122C - 122 Community Center Roof Terrace | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2026 | Jan 2027
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-TER | 122C - 122 Community Center Roof Terrace | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2027 | Jul 2027
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-TER | 122C - 122 Community Center Roof Terrace | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2027 | Oct 2027
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-TER | 122C - 122 Community Center Roof Terrace | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2027 | Feb 2028
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-TER | 122C - 122 Community Center Roof Terrace | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2028 | Jun 2028
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-TER | 122C - 122 Community Center Roof Terrace | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2028 | Oct 2028
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-TER | 122C - 122 Community Center Roof Terrace | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2028 | Jan 2029
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-TER | 122C - 122 Community Center Roof Terrace | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2029 | Mar 2029
20231026 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-TER | 122C - 122 Community Center Roof Terrace | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2029 | Apr 2029
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 125THPDIM | 125th St & Park Ave - Pedestrian Improvements | 1 | DESIGN | Feb 2005 | Mar 2005 | Feb 2009 | Mar 2009
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 125THPDIM | 125th St & Park Ave - Pedestrian Improvements | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2005 | Mar 2005 | Mar 2009 | Mar 2009
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 125THPDIM | 125th St & Park Ave - Pedestrian Improvements | 3 | CONSTRUCTION | Mar 2005 | Apr 2005 | Mar 2009 | Apr 2009
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 125THPDIM | 125th St & Park Ave - Pedestrian Improvements | 4 | ORIGINAL EQUIP & FURNISHING | Apr 2005 | May 2005 | Apr 2009 | May 2009
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 125THPDIM | 125th St & Park Ave - Pedestrian Improvements | 5 | SUBSTANTIAL COMPLETION | May 2005 | May 2005 | May 2009 | May 2009
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 125THPDIM | 125th St & Park Ave - Pedestrian Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2005 | Jun 2016 | May 2009 | Jun 2033
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 126STDEPO | 126th Street Depot | 1 | DESIGN | Jul 2022 | Jul 2022 | Jul 2022 | Jul 2022
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 126STDEPO | 126th Street Depot | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Aug 2022 | Jul 2022 | Aug 2022
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 126STDEPO | 126th Street Depot | 3 | CONSTRUCTION | Aug 2022 | Sep 2022 | Aug 2022 | Sep 2022
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 126STDEPO | 126th Street Depot | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Sep 2022 | Sep 2022 | Sep 2022
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 126STDEPO | 126th Street Depot | 5 | SUBSTANTIAL COMPLETION | Sep 2022 | Oct 2022 | Sep 2022 | Oct 2022
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 126STDEPO | 126th Street Depot | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2022 | Jun 2027 | Feb 2022 | Jun 2027
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 34STHELI | E. 34th Street Heliport Rehabilitation | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2012 | Jan 2012 | Jan 2017 | Jan 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 34STHELI | E. 34th Street Heliport Rehabilitation | 3 | CONSTRUCTION | Jan 2012 | Jan 2014 | Jan 2017 | Jan 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 34STHELI | E. 34th Street Heliport Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | Jan 2014 | Jan 2014 | Jan 2019 | Jan 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 34STHELI | E. 34th Street Heliport Rehabilitation | 5 | SUBSTANTIAL COMPLETION | Jan 2014 | Jan 2014 | Jan 2019 | Jan 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 34STHELI | E. 34th Street Heliport Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2014 | Jan 2014 | Jan 2019 | Jun 2027
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 8THSTREET | FA - Village Alliance - Reconstruction of St. & Sidewalks | 1 | DESIGN | Dec 1999 | Jan 2000 | Dec 2002 | Jan 2003
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 8THSTREET | FA - Village Alliance - Reconstruction of St. & Sidewalks | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2000 | Feb 2000 | Jan 2003 | Jan 2003
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 8THSTREET | FA - Village Alliance - Reconstruction of St. & Sidewalks | 3 | CONSTRUCTION | Feb 2000 | Jun 2007 | Jan 2003 | Jun 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 8THSTREET | FA - Village Alliance - Reconstruction of St. & Sidewalks | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2007 | Jun 2007 | Jun 2023 | Jun 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 8THSTREET | FA - Village Alliance - Reconstruction of St. & Sidewalks | 5 | SUBSTANTIAL COMPLETION | Jul 2007 | Jun 2007 | Jun 2023 | Jun 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 8THSTREET | FA - Village Alliance - Reconstruction of St. & Sidewalks | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2007 | Jul 2007 | Jun 2023 | Jun 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 911MEMOR | 9/11 Postcard Memorial Electrical Improvements | 1 | DESIGN | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 911MEMOR | 9/11 Postcard Memorial Electrical Improvements | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Aug 2021 | Jul 2021 | Aug 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 911MEMOR | 9/11 Postcard Memorial Electrical Improvements | 3 | CONSTRUCTION | Aug 2021 | Sep 2021 | Aug 2021 | Sep 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 911MEMOR | 9/11 Postcard Memorial Electrical Improvements | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Sep 2021 | Sep 2021 | Sep 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 911MEMOR | 9/11 Postcard Memorial Electrical Improvements | 5 | SUBSTANTIAL COMPLETION | Sep 2021 | Oct 2024 | Sep 2021 | Oct 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 911MEMOR | 9/11 Postcard Memorial Electrical Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2024 | Oct 2024 | Oct 2024 | Oct 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | AHGREEN | Andrew Haswell Green Park - Phase 2B | 1 | DESIGN | Sep 2015 | Mar 2017 | Sep 2015 | Mar 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | AHGREEN | Andrew Haswell Green Park - Phase 2B | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2017 | Mar 2017 | Mar 2017 | Mar 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | AHGREEN | Andrew Haswell Green Park - Phase 2B | 3 | CONSTRUCTION | Apr 2017 | Apr 2019 | Apr 2017 | Apr 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | AHGREEN | Andrew Haswell Green Park - Phase 2B | 4 | ORIGINAL EQUIP & FURNISHING | May 2019 | Apr 2019 | May 2019 | Apr 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | AHGREEN | Andrew Haswell Green Park - Phase 2B | 5 | SUBSTANTIAL COMPLETION | May 2019 | Apr 2019 | May 2019 | Apr 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | AHGREEN | Andrew Haswell Green Park - Phase 2B | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2019 | May 2019 | May 2019 | Jun 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | AMSTCORNR | LPCA Redevelopment Final Phase -Amsterdam Corner | 1 | DESIGN | Jan 2022 | Jan 2022 | Jan 2024 | Jan 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | AMSTCORNR | LPCA Redevelopment Final Phase -Amsterdam Corner | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2022 | Feb 2022 | Jan 2024 | Feb 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | AMSTCORNR | LPCA Redevelopment Final Phase -Amsterdam Corner | 3 | CONSTRUCTION | Feb 2022 | Mar 2022 | Feb 2024 | Mar 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | AMSTCORNR | LPCA Redevelopment Final Phase -Amsterdam Corner | 4 | ORIGINAL EQUIP & FURNISHING | Mar 2022 | Mar 2022 | Mar 2024 | Mar 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | AMSTCORNR | LPCA Redevelopment Final Phase -Amsterdam Corner | 5 | SUBSTANTIAL COMPLETION | Mar 2022 | Apr 2022 | Mar 2024 | Apr 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | AMSTCORNR | LPCA Redevelopment Final Phase -Amsterdam Corner | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2022 | Apr 2024 | Apr 2024 | Jun 2028
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CIVICHALL | CIVIC HALL: NEW COMMUNITY CENTER | 1 | DESIGN | Jul 2023 | Jul 2023 | Jul 2023 | Jul 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CIVICHALL | CIVIC HALL: NEW COMMUNITY CENTER | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CIVICHALL | CIVIC HALL: NEW COMMUNITY CENTER | 3 | CONSTRUCTION | Aug 2023 | Sep 2023 | Aug 2023 | Sep 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CIVICHALL | CIVIC HALL: NEW COMMUNITY CENTER | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Sep 2023 | Sep 2023 | Sep 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CIVICHALL | CIVIC HALL: NEW COMMUNITY CENTER | 5 | SUBSTANTIAL COMPLETION | Sep 2023 | Oct 2023 | Sep 2023 | Oct 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CIVICHALL | CIVIC HALL: NEW COMMUNITY CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2023 | Jun 2024 | Oct 2023 | Jun 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CMPRENO | Chinatown Manpower Project - 4th Floor Renovation | 1 | DESIGN | Jun 2015 | Jul 2015 | Jun 2015 | Jul 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CMPRENO | Chinatown Manpower Project - 4th Floor Renovation | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Aug 2015 | Jul 2017 | Jul 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CMPRENO | Chinatown Manpower Project - 4th Floor Renovation | 3 | CONSTRUCTION | Aug 2015 | Sep 2015 | Jul 2017 | Jul 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CMPRENO | Chinatown Manpower Project - 4th Floor Renovation | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2015 | Sep 2015 | Jul 2017 | Jul 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CMPRENO | Chinatown Manpower Project - 4th Floor Renovation | 5 | SUBSTANTIAL COMPLETION | Sep 2015 | Oct 2015 | Jul 2017 | Jul 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CMPRENO | Chinatown Manpower Project - 4th Floor Renovation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2015 | Oct 2015 | Jul 2017 | Jun 2026
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSFERY2 | New York City Ferry - Infrastructure | 1 | DESIGN | Jul 2018 | Jul 2018 | Jul 2018 | Apr 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSFERY2 | New York City Ferry - Infrastructure | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Aug 2018 | Apr 2021 | Apr 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSFERY2 | New York City Ferry - Infrastructure | 3 | CONSTRUCTION | Aug 2018 | Sep 2018 | Apr 2021 | May 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSFERY2 | New York City Ferry - Infrastructure | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2018 | Sep 2018 | Jun 2021 | Jun 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSFERY2 | New York City Ferry - Infrastructure | 5 | SUBSTANTIAL COMPLETION | Sep 2018 | Oct 2018 | Jun 2021 | Jun 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSFERY2 | New York City Ferry - Infrastructure | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2018 | Oct 2018 | Jun 2021 | Jun 2027
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | DMECODOCK | Dyckman Pier -- Ferry Access to Eco-Dock | 1 | DESIGN | Jun 2015 | Jun 2021 | Jun 2021 | Jun 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | DMECODOCK | Dyckman Pier -- Ferry Access to Eco-Dock | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Jun 2021 | Jul 2021 | Jun 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | DMECODOCK | Dyckman Pier -- Ferry Access to Eco-Dock | 3 | CONSTRUCTION | Jul 2021 | Jun 2021 | Jul 2021 | Jun 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | DMECODOCK | Dyckman Pier -- Ferry Access to Eco-Dock | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2021 | Jun 2021 | Jul 2021 | Jun 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | DMECODOCK | Dyckman Pier -- Ferry Access to Eco-Dock | 5 | SUBSTANTIAL COMPLETION | Jul 2021 | Jun 2021 | Jul 2021 | Jun 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | DMECODOCK | Dyckman Pier -- Ferry Access to Eco-Dock | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | EDCLUMP | EDC Lump Sum | 1 | DESIGN | Jul 2019 | Jul 2019 | Jul 2019 | Jul 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | EDCLUMP | EDC Lump Sum | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jul 2019 | Aug 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | EDCLUMP | EDC Lump Sum | 3 | CONSTRUCTION | Aug 2019 | Sep 2019 | Aug 2019 | Sep 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | EDCLUMP | EDC Lump Sum | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Sep 2019 | Sep 2019 | Sep 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | EDCLUMP | EDC Lump Sum | 5 | SUBSTANTIAL COMPLETION | Sep 2019 | Oct 2019 | Sep 2019 | Oct 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | EDCLUMP | EDC Lump Sum | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2019 | Oct 2024 | Oct 2019 | Oct 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ERVRWALL | East River Seawall Rehabilitation (BMB to Pier 16) | 1 | DESIGN | Jan 2016 | Jun 2018 | Jan 2016 | Jun 2018
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ERVRWALL | East River Seawall Rehabilitation (BMB to Pier 16) | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Jun 2018 | Jul 2018 | Jun 2018
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ERVRWALL | East River Seawall Rehabilitation (BMB to Pier 16) | 3 | CONSTRUCTION | Jul 2018 | Jun 2021 | Jul 2018 | Jun 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ERVRWALL | East River Seawall Rehabilitation (BMB to Pier 16) | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2021 | Jun 2021 | Jul 2021 | Jun 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ERVRWALL | East River Seawall Rehabilitation (BMB to Pier 16) | 5 | SUBSTANTIAL COMPLETION | Jul 2021 | Jun 2021 | Jul 2021 | Jun 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ERVRWALL | East River Seawall Rehabilitation (BMB to Pier 16) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Jul 2021 | Jul 2021 | Jun 2029
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | FFMSHREDR | Fulton Fish Market - Pallet Shredder & Backup Power Bank | 1 | DESIGN | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | FFMSHREDR | Fulton Fish Market - Pallet Shredder & Backup Power Bank | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Aug 2021 | Jul 2021 | Aug 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | FFMSHREDR | Fulton Fish Market - Pallet Shredder & Backup Power Bank | 3 | CONSTRUCTION | Aug 2021 | Sep 2021 | Aug 2021 | Sep 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | FFMSHREDR | Fulton Fish Market - Pallet Shredder & Backup Power Bank | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Sep 2021 | Sep 2021 | Sep 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | FFMSHREDR | Fulton Fish Market - Pallet Shredder & Backup Power Bank | 5 | SUBSTANTIAL COMPLETION | Sep 2021 | Oct 2025 | Sep 2021 | Oct 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | FFMSHREDR | Fulton Fish Market - Pallet Shredder & Backup Power Bank | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2025 | Oct 2025 | Oct 2025 | Oct 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | FFREEDOMS | Four Freedoms Park Utilities | 1 | DESIGN | Jan 2021 | Jan 2021 | Jan 2021 | Jan 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | FFREEDOMS | Four Freedoms Park Utilities | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2021 | Feb 2021 | Jan 2021 | Feb 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | FFREEDOMS | Four Freedoms Park Utilities | 3 | CONSTRUCTION | Feb 2021 | Mar 2021 | Feb 2021 | Mar 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | FFREEDOMS | Four Freedoms Park Utilities | 4 | ORIGINAL EQUIP & FURNISHING | Mar 2021 | Mar 2021 | Mar 2021 | Mar 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | FFREEDOMS | Four Freedoms Park Utilities | 5 | SUBSTANTIAL COMPLETION | Mar 2021 | Apr 2021 | Mar 2021 | Apr 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | FFREEDOMS | Four Freedoms Park Utilities | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2021 | Jun 2031 | Apr 2021 | Jun 2031
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISB301 | Governors Island - Building 301 Renovation | 1 | DESIGN | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISB301 | Governors Island - Building 301 Renovation | 2 | BID AWARD AND REGISTER CONTRCT | Apr 2022 | Apr 2022 | Apr 2022 | Apr 2022
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISB301 | Governors Island - Building 301 Renovation | 3 | CONSTRUCTION | May 2022 | Apr 2023 | May 2022 | Apr 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISB301 | Governors Island - Building 301 Renovation | 4 | ORIGINAL EQUIP & FURNISHING | May 2023 | May 2023 | May 2023 | May 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISB301 | Governors Island - Building 301 Renovation | 5 | SUBSTANTIAL COMPLETION | Jun 2023 | Jun 2023 | Jun 2023 | Jun 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISB301 | Governors Island - Building 301 Renovation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISB324 | Governors Island - Building 324 Stabilization | 1 | DESIGN | May 2023 | Dec 2023 | May 2023 | Dec 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISB324 | Governors Island - Building 324 Stabilization | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2024 | Feb 2024 | Jan 2024 | Feb 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISB324 | Governors Island - Building 324 Stabilization | 3 | CONSTRUCTION | Mar 2024 | May 2025 | Mar 2024 | May 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISB324 | Governors Island - Building 324 Stabilization | 4 | ORIGINAL EQUIP & FURNISHING | Mar 2024 | May 2025 | Mar 2024 | May 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISB324 | Governors Island - Building 324 Stabilization | 5 | SUBSTANTIAL COMPLETION | Jun 2025 | Jun 2025 | Jun 2025 | Jun 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISB324 | Governors Island - Building 324 Stabilization | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Sep 2025 | Jul 2025 | Sep 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBL20 | Governors Island - Building 20 Nolan Park Renovation | 1 | DEVELOP SCOPE | Oct 2018 | Aug 2019 | Oct 2018 | Aug 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBL20 | Governors Island - Building 20 Nolan Park Renovation | 2 | PRELIMINARY DESIGN | Oct 2018 | Aug 2019 | Oct 2018 | Aug 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBL20 | Governors Island - Building 20 Nolan Park Renovation | 3 | FINAL DESIGN | Oct 2018 | Aug 2019 | Oct 2018 | Aug 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBL20 | Governors Island - Building 20 Nolan Park Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Oct 2019 | Sep 2019 | Oct 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBL20 | Governors Island - Building 20 Nolan Park Renovation | 5 | CONSTRUCTION TO 25% | Nov 2019 | Jan 2020 | Nov 2019 | Jan 2020
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBL20 | Governors Island - Building 20 Nolan Park Renovation | 6 | CONSTRUCTION TO 50% | Feb 2020 | Mar 2020 | Feb 2020 | Mar 2020
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBL20 | Governors Island - Building 20 Nolan Park Renovation | 7 | CONSTRUCTION TO 75% | Apr 2020 | May 2020 | Apr 2020 | May 2022
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBL20 | Governors Island - Building 20 Nolan Park Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2020 | Jun 2020 | May 2022 | Jun 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBL20 | Governors Island - Building 20 Nolan Park Renovation | 9 | SUBSTANTIAL COMPLETION | Jul 2020 | Jul 2020 | Jul 2023 | Dec 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBL20 | Governors Island - Building 20 Nolan Park Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2020 | Aug 2020 | Jan 2024 | Jun 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBLNP | Governors Island Building Stabilization - Nolan Park | 1 | DESIGN | Jul 2021 | Jul 2021 | Jan 2023 | Dec 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBLNP | Governors Island Building Stabilization - Nolan Park | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Aug 2021 | Jan 2024 | Apr 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBLNP | Governors Island Building Stabilization - Nolan Park | 3 | CONSTRUCTION | Aug 2021 | Sep 2021 | Apr 2024 | Jun 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBLNP | Governors Island Building Stabilization - Nolan Park | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Sep 2021 | Apr 2024 | Jun 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBLNP | Governors Island Building Stabilization - Nolan Park | 5 | SUBSTANTIAL COMPLETION | Sep 2021 | Oct 2021 | Jul 2025 | Sep 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBLNP | Governors Island Building Stabilization - Nolan Park | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2021 | Jun 2023 | Oct 2025 | Oct 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBMB2 | Governors Island BMB Slip5/6 Pile Cluster&Slip 6/7FenderRack | 1 | DESIGN | Jul 2018 | Jul 2018 | Jul 2018 | Mar 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBMB2 | Governors Island BMB Slip5/6 Pile Cluster&Slip 6/7FenderRack | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Aug 2018 | Apr 2019 | Jun 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBMB2 | Governors Island BMB Slip5/6 Pile Cluster&Slip 6/7FenderRack | 3 | CONSTRUCTION | Aug 2018 | Sep 2018 | Jul 2019 | Jun 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBMB2 | Governors Island BMB Slip5/6 Pile Cluster&Slip 6/7FenderRack | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2018 | Sep 2018 | Aug 2019 | Jun 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBMB2 | Governors Island BMB Slip5/6 Pile Cluster&Slip 6/7FenderRack | 5 | SUBSTANTIAL COMPLETION | Sep 2018 | Oct 2018 | Jul 2023 | Sep 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBMB2 | Governors Island BMB Slip5/6 Pile Cluster&Slip 6/7FenderRack | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2018 | Oct 2018 | Oct 2023 | Dec 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBMBL | Governors Island BMB Lighting | 1 | DESIGN | Jan 2024 | Jun 2024 | Jan 2024 | Jun 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBMBL | Governors Island BMB Lighting | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Sep 2024 | Jul 2024 | Sep 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBMBL | Governors Island BMB Lighting | 3 | CONSTRUCTION | Oct 2024 | Mar 2025 | Oct 2024 | Mar 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBMBL | Governors Island BMB Lighting | 4 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Mar 2025 | Oct 2024 | Mar 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBMBL | Governors Island BMB Lighting | 5 | SUBSTANTIAL COMPLETION | Apr 2025 | May 2025 | Apr 2025 | May 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBMBL | Governors Island BMB Lighting | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2025 | Jun 2025 | Jun 2025 | Jun 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBTRL | Governors Island Trailer Bathroom | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2018 | Nov 2018 | Sep 2018 | Nov 2018
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBTRL | Governors Island Trailer Bathroom | 3 | CONSTRUCTION | Dec 2018 | Mar 2019 | Dec 2018 | Mar 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBTRL | Governors Island Trailer Bathroom | 4 | ORIGINAL EQUIP & FURNISHING | Dec 2018 | Mar 2019 | Dec 2018 | Mar 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBTRL | Governors Island Trailer Bathroom | 5 | SUBSTANTIAL COMPLETION | Apr 2019 | Jun 2019 | Apr 2019 | Jun 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBTRL | Governors Island Trailer Bathroom | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2019 | Jun 2019 | May 2019 | Jun 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISELE2 | Governors Island Electric Projects | 1 | DESIGN | Oct 2017 | Feb 2018 | Oct 2017 | Feb 2018
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISELE2 | Governors Island Electric Projects | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | May 2019 | Mar 2018 | May 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISELE2 | Governors Island Electric Projects | 3 | CONSTRUCTION | Jun 2019 | Jun 2020 | Jun 2019 | Jun 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISELE2 | Governors Island Electric Projects | 4 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Jun 2020 | Jun 2019 | Jun 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISELE2 | Governors Island Electric Projects | 5 | SUBSTANTIAL COMPLETION | Jul 2020 | Jul 2020 | Jul 2024 | Jul 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISELE2 | Governors Island Electric Projects | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2020 | Oct 2020 | Aug 2024 | Oct 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISESUB | Governors Island - Electrical Substation | 1 | DESIGN | Oct 2021 | Dec 2022 | Oct 2021 | Dec 2022
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISESUB | Governors Island - Electrical Substation | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2023 | Jun 2023 | Jan 2023 | Jun 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISESUB | Governors Island - Electrical Substation | 3 | CONSTRUCTION | Jul 2023 | Dec 2024 | Jul 2023 | Dec 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISESUB | Governors Island - Electrical Substation | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2024 | Dec 2024 | Jul 2024 | Dec 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISESUB | Governors Island - Electrical Substation | 5 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISESUB | Governors Island - Electrical Substation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2025 | Jun 2025 | Apr 2025 | Jun 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISLIMA | Governors Island - Lima Pier Reconstruction | 1 | DESIGN | Jan 2022 | Dec 2022 | Jan 2022 | Dec 2022
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISLIMA | Governors Island - Lima Pier Reconstruction | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2023 | Jun 2023 | Jan 2023 | Jun 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISLIMA | Governors Island - Lima Pier Reconstruction | 3 | CONSTRUCTION | Jul 2023 | Dec 2024 | Jul 2023 | Dec 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISLIMA | Governors Island - Lima Pier Reconstruction | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2023 | Dec 2024 | Jul 2023 | Dec 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISLIMA | Governors Island - Lima Pier Reconstruction | 5 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISLIMA | Governors Island - Lima Pier Reconstruction | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2025 | Jun 2025 | Apr 2025 | Jun 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISLND2 | Governors Island Infrastructure Improvements | 1 | DESIGN | Jul 2016 | Jul 2016 | Jul 2016 | Apr 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISLND2 | Governors Island Infrastructure Improvements | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Apr 2021 | Apr 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISLND2 | Governors Island Infrastructure Improvements | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Apr 2021 | May 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISLND2 | Governors Island Infrastructure Improvements | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Jun 2021 | Jun 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISLND2 | Governors Island Infrastructure Improvements | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Jun 2021 | Jun 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISLND2 | Governors Island Infrastructure Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2016 | Jun 2021 | Jun 2029
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISTNGO | Governors Island - Tango Pier | 1 | DESIGN | Mar 2021 | Jun 2021 | Jul 2021 | Sep 2022
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISTNGO | Governors Island - Tango Pier | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Aug 2021 | Jul 2022 | Sep 2022
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISTNGO | Governors Island - Tango Pier | 3 | CONSTRUCTION | Sep 2021 | Apr 2022 | Oct 2022 | Jun 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISTNGO | Governors Island - Tango Pier | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Apr 2022 | Oct 2022 | Jun 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISTNGO | Governors Island - Tango Pier | 5 | SUBSTANTIAL COMPLETION | May 2022 | May 2022 | Jul 2023 | Sep 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISTNGO | Governors Island - Tango Pier | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Jun 2022 | Oct 2023 | Dec 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISUNUT | Governors Island Underground Utilities | 1 | DESIGN | Jun 2017 | Jul 2017 | Jun 2017 | Jul 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISUNUT | Governors Island Underground Utilities | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Aug 2017 | Jul 2017 | Aug 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISUNUT | Governors Island Underground Utilities | 3 | CONSTRUCTION | Aug 2017 | Sep 2017 | Aug 2017 | Sep 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISUNUT | Governors Island Underground Utilities | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Sep 2017 | Sep 2017 | Sep 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISUNUT | Governors Island Underground Utilities | 5 | SUBSTANTIAL COMPLETION | Sep 2017 | Oct 2017 | Sep 2017 | Oct 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISUNUT | Governors Island Underground Utilities | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2017 | Oct 2019 | Oct 2017 | Oct 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISWDZE | Governors Island WDZ Utility Infrastructure | 1 | DESIGN | Jul 2023 | Jul 2023 | Jul 2023 | Jul 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISWDZE | Governors Island WDZ Utility Infrastructure | 2 | BID AWARD AND REGISTER CONTRCT | Aug 2023 | Aug 2023 | Aug 2023 | Aug 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISWDZE | Governors Island WDZ Utility Infrastructure | 3 | CONSTRUCTION | Sep 2023 | Apr 2024 | Sep 2023 | Apr 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISWDZE | Governors Island WDZ Utility Infrastructure | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Apr 2024 | Sep 2023 | Apr 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISWDZE | Governors Island WDZ Utility Infrastructure | 5 | SUBSTANTIAL COMPLETION | May 2024 | May 2024 | May 2024 | May 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISWDZE | Governors Island WDZ Utility Infrastructure | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISWLL2 | Governors Island Seawall Rehabilitation | 1 | DESIGN | Jul 2016 | Jul 2016 | Jan 2023 | Dec 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISWLL2 | Governors Island Seawall Rehabilitation | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Jan 2024 | Jun 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISWLL2 | Governors Island Seawall Rehabilitation | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Jul 2024 | Dec 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISWLL2 | Governors Island Seawall Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Jul 2024 | Dec 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISWLL2 | Governors Island Seawall Rehabilitation | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Jan 2026 | Mar 2026
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISWLL2 | Governors Island Seawall Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2016 | Apr 2026 | Jun 2026
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISWTR2 | Governors Island Potable Water System | 1 | DESIGN | Jul 2016 | Jul 2016 | Jul 2021 | Dec 2022
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISWTR2 | Governors Island Potable Water System | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Jan 2023 | Jun 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISWTR2 | Governors Island Potable Water System | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Jul 2023 | Mar 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISWTR2 | Governors Island Potable Water System | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Jul 2023 | Mar 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISWTR2 | Governors Island Potable Water System | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Apr 2024 | May 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISWTR2 | Governors Island Potable Water System | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2016 | Jun 2024 | Aug 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISYANK | Governors Island - Yankee Pier | 1 | DESIGN | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISYANK | Governors Island - Yankee Pier | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2023 | Jun 2023 | Jan 2023 | Jun 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISYANK | Governors Island - Yankee Pier | 3 | CONSTRUCTION | Jul 2023 | Jun 2024 | Jul 2023 | Jun 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISYANK | Governors Island - Yankee Pier | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2023 | Jun 2024 | Jul 2023 | Jun 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISYANK | Governors Island - Yankee Pier | 5 | SUBSTANTIAL COMPLETION | Jul 2024 | Sep 2024 | Jul 2024 | Sep 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISYANK | Governors Island - Yankee Pier | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2024 | Dec 2024 | Oct 2024 | Dec 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HARLMPIER | Harlem Area Piers & Bulkhead Stabilization | 1 | DESIGN | Jul 1996 | Jul 1996 | Jan 2012 | Oct 2013
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HARLMPIER | Harlem Area Piers & Bulkhead Stabilization | 2 | BID AWARD AND REGISTER CONTRCT | Jul 1996 | Aug 1996 | Oct 2013 | Oct 2013
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HARLMPIER | Harlem Area Piers & Bulkhead Stabilization | 3 | CONSTRUCTION | Aug 1996 | Jun 2007 | Mar 2006 | Oct 2007
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HARLMPIER | Harlem Area Piers & Bulkhead Stabilization | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2007 | Jun 2007 | Oct 2007 | Oct 2020
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HARLMPIER | Harlem Area Piers & Bulkhead Stabilization | 5 | SUBSTANTIAL COMPLETION | Jul 2007 | Jun 2007 | Oct 2020 | Jul 2030
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HARLMPIER | Harlem Area Piers & Bulkhead Stabilization | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2007 | Jul 2007 | Jul 2030 | Jul 2030
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HBGRWESPN | Manhattan Greenway - UN Esplanade | 1 | DESIGN | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HBGRWESPN | Manhattan Greenway - UN Esplanade | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Aug 2021 | Jul 2021 | Aug 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HBGRWESPN | Manhattan Greenway - UN Esplanade | 3 | CONSTRUCTION | Aug 2021 | Sep 2021 | Aug 2021 | Sep 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HBGRWESPN | Manhattan Greenway - UN Esplanade | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Sep 2021 | Sep 2021 | Sep 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HBGRWESPN | Manhattan Greenway - UN Esplanade | 5 | SUBSTANTIAL COMPLETION | Sep 2021 | Oct 2021 | Sep 2021 | Oct 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HBGRWESPN | Manhattan Greenway - UN Esplanade | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2021 | Oct 2027 | Oct 2021 | Oct 2027
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HIGHLINE | High Line | 1 | DEVELOP SCOPE | Jul 2003 | Sep 2003 | Jul 2006 | Jul 2006
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HIGHLINE | High Line | 2 | DESIGN | Sep 2003 | Dec 2003 | Jul 2006 | Aug 2006
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HIGHLINE | High Line | 3 | BID/ REGISTER CONTRACT | Dec 2003 | Mar 2004 | Aug 2006 | Jun 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HIGHLINE | High Line | 4 | CONSTRUCTION | Mar 2004 | Mar 2005 | Jul 2024 | Jun 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HIGHLINE | High Line | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2005 | Mar 2006 | Jul 2024 | Jun 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HIGHLINE | High Line | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2005 | Mar 2006 | Jul 2024 | Jun 2031
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HL82PHL | DOHMH PHL BUILDING CONSTRUCTION | 1 | DESIGN | Jun 2018 | Nov 2019 | Jun 2018 | Nov 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HL82PHL | DOHMH PHL BUILDING CONSTRUCTION | 2 | CONSTRUCTION | Nov 2019 | Oct 2024 | Nov 2019 | Oct 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HL82PHL | DOHMH PHL BUILDING CONSTRUCTION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTFISH | Fulton Fish Market Relocation to Hunts Point | 1 | DESIGN | Mar 2001 | May 2001 | Mar 2001 | Mar 2001
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTFISH | Fulton Fish Market Relocation to Hunts Point | 2 | BID AWARD AND REGISTER CONTRCT | May 2001 | May 2001 | Apr 2001 | Apr 2001
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTFISH | Fulton Fish Market Relocation to Hunts Point | 3 | CONSTRUCTION | May 2001 | Jun 2007 | Apr 2001 | May 2001
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTFISH | Fulton Fish Market Relocation to Hunts Point | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2007 | Jun 2007 | May 2001 | May 2001
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTFISH | Fulton Fish Market Relocation to Hunts Point | 5 | SUBSTANTIAL COMPLETION | Jul 2007 | Jun 2007 | May 2001 | Jun 2001
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTFISH | Fulton Fish Market Relocation to Hunts Point | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2007 | Jun 2007 | Jun 2001 | Jun 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTFISH | Fulton Fish Market Relocation to Hunts Point | 7 | DESIGN | Jul 2007 | Jun 2007 | Jun 2001 | Jun 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTFISH | Fulton Fish Market Relocation to Hunts Point | 8 | BID AWARD AND REGISTER CONTRCT | Jul 2007 | Jun 2007 | Jun 2001 | Jun 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTFISH | Fulton Fish Market Relocation to Hunts Point | 9 | CONSTRUCTION | Jul 2007 | Jun 2007 | Jun 2001 | Jun 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTFISH | Fulton Fish Market Relocation to Hunts Point | 10 | ORIGINAL EQUIP & FURNISHING | Jul 2007 | Jun 2007 | Jun 2001 | Jun 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTFISH | Fulton Fish Market Relocation to Hunts Point | 11 | SUBSTANTIAL COMPLETION | Jul 2007 | Jun 2007 | Jun 2001 | Jun 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTFISH | Fulton Fish Market Relocation to Hunts Point | 12 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2007 | Jul 2007 | Jun 2001 | Jun 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWD10214 | Hudson Sq Streetscape Improvements | 1 | DEVELOP SCOPE | Jun 2015 | Aug 2015 | Jun 2016 | Jun 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWD10214 | Hudson Sq Streetscape Improvements | 2 | PRELIMINARY DESIGN | Aug 2015 | Dec 2015 | Jun 2019 | Jul 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWD10214 | Hudson Sq Streetscape Improvements | 3 | FINAL DESIGN | Dec 2015 | Jun 2016 | Jul 2019 | Aug 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWD10214 | Hudson Sq Streetscape Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2016 | Sep 2016 | Aug 2019 | Aug 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWD10214 | Hudson Sq Streetscape Improvements | 5 | CONSTRUCTION TO 25% | Sep 2016 | Jan 2017 | Aug 2025 | Sep 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWD10214 | Hudson Sq Streetscape Improvements | 6 | CONSTRUCTION TO 50% | Jan 2017 | May 2017 | Sep 2025 | Sep 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWD10214 | Hudson Sq Streetscape Improvements | 7 | CONSTRUCTION TO 75% | May 2017 | Sep 2017 | Sep 2025 | Sep 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWD10214 | Hudson Sq Streetscape Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Dec 2017 | Sep 2025 | Sep 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWD10214 | Hudson Sq Streetscape Improvements | 9 | SUBSTANTIAL COMPLETION | Dec 2017 | Feb 2018 | Sep 2025 | Sep 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWD10214 | Hudson Sq Streetscape Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2018 | Mar 2018 | Sep 2025 | Sep 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWM1685 | Hudson River Park Trust | 1 | DESIGN | Jul 2016 | Jul 2016 | Jul 2016 | Jul 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWM1685 | Hudson River Park Trust | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Jul 2016 | Aug 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWM1685 | Hudson River Park Trust | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Aug 2016 | Sep 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWM1685 | Hudson River Park Trust | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Sep 2016 | Sep 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWM1685 | Hudson River Park Trust | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Sep 2016 | Oct 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWM1685 | Hudson River Park Trust | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2016 | Oct 2016 | Jun 2028
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | INWDGRWAY | Inwood Greenway | 1 | DESIGN | Jul 2023 | Jul 2023 | Jul 2023 | Jul 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | INWDGRWAY | Inwood Greenway | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | INWDGRWAY | Inwood Greenway | 3 | CONSTRUCTION | Aug 2023 | Sep 2023 | Aug 2023 | Sep 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | INWDGRWAY | Inwood Greenway | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Sep 2023 | Sep 2023 | Sep 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | INWDGRWAY | Inwood Greenway | 5 | SUBSTANTIAL COMPLETION | Sep 2023 | Oct 2023 | Sep 2023 | Oct 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | INWDGRWAY | Inwood Greenway | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2023 | Jun 2031 | Oct 2023 | Jun 2031
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | JULIABURG | 1680 Lexington Avenue - Julia De Burgo Latino Cultural Ct. | 1 | DESIGN | Jul 2023 | Jul 2023 | Jul 2023 | Jul 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | JULIABURG | 1680 Lexington Avenue - Julia De Burgo Latino Cultural Ct. | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | JULIABURG | 1680 Lexington Avenue - Julia De Burgo Latino Cultural Ct. | 3 | CONSTRUCTION | Aug 2023 | Sep 2023 | Aug 2023 | Sep 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | JULIABURG | 1680 Lexington Avenue - Julia De Burgo Latino Cultural Ct. | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Sep 2023 | Sep 2023 | Sep 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | JULIABURG | 1680 Lexington Avenue - Julia De Burgo Latino Cultural Ct. | 5 | SUBSTANTIAL COMPLETION | Sep 2023 | Oct 2023 | Sep 2023 | Oct 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | JULIABURG | 1680 Lexington Avenue - Julia De Burgo Latino Cultural Ct. | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2023 | Jun 2025 | Oct 2023 | Jun 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQPLZ | La Marqueta Plaza Rehabilitation | 1 | DESIGN | Jul 2017 | Jul 2017 | Jul 2017 | Jul 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQPLZ | La Marqueta Plaza Rehabilitation | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Aug 2017 | Jul 2017 | Aug 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQPLZ | La Marqueta Plaza Rehabilitation | 3 | CONSTRUCTION | Aug 2017 | Sep 2017 | Aug 2017 | Sep 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQPLZ | La Marqueta Plaza Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Sep 2017 | Sep 2017 | Sep 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQPLZ | La Marqueta Plaza Rehabilitation | 5 | SUBSTANTIAL COMPLETION | Sep 2017 | Oct 2017 | Sep 2017 | Oct 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQPLZ | La Marqueta Plaza Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2017 | Oct 2017 | Oct 2017 | Jun 2031
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQUE2 | La Marqueta - Kitchen Incubator | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2014 | Jan 2014 | Jan 2014 | Jan 2014
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQUE3 | La Marqueta (Hot Bread Kitchen) | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Jun 2018 | Jul 2018 | Jun 2018
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQUE3 | La Marqueta (Hot Bread Kitchen) | 3 | CONSTRUCTION | Jul 2018 | Jun 2021 | Jul 2018 | Jun 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQUE3 | La Marqueta (Hot Bread Kitchen) | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2021 | Jun 2021 | Jul 2021 | Jun 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQUE3 | La Marqueta (Hot Bread Kitchen) | 5 | SUBSTANTIAL COMPLETION | Jul 2021 | Jun 2021 | Jul 2021 | Jun 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQUE3 | La Marqueta (Hot Bread Kitchen) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQUET | La Marqueta | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2005 | Feb 2007 | Jan 2005 | Feb 2007
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQUET | La Marqueta | 3 | CONSTRUCTION | Feb 2007 | Feb 2007 | Feb 2007 | Feb 2007
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQUET | La Marqueta | 4 | ORIGINAL EQUIP & FURNISHING | Feb 2007 | Feb 2007 | Feb 2007 | Feb 2007
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQUET | La Marqueta | 5 | SUBSTANTIAL COMPLETION | Feb 2007 | Feb 2007 | Feb 2007 | Feb 2007
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQUET | La Marqueta | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2007 | Feb 2007 | Feb 2007 | Jun 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LCNPARK | Lower Concourse Park | 1 | DESIGN | Jul 2019 | Jul 2019 | Jul 2019 | Jul 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LCNPARK | Lower Concourse Park | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jul 2019 | Aug 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LCNPARK | Lower Concourse Park | 3 | CONSTRUCTION | Aug 2019 | Sep 2019 | Aug 2019 | Sep 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LCNPARK | Lower Concourse Park | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Sep 2019 | Sep 2019 | Sep 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LCNPARK | Lower Concourse Park | 5 | SUBSTANTIAL COMPLETION | Sep 2019 | Oct 2019 | Sep 2019 | Oct 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LCNPARK | Lower Concourse Park | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2019 | Oct 2022 | Oct 2019 | Jun 2028
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LMCRFIDI | FIDI Seaport resilient waterfront | 1 | DESIGN | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LMCRFIDI | FIDI Seaport resilient waterfront | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Aug 2021 | Jul 2021 | Aug 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LMCRFIDI | FIDI Seaport resilient waterfront | 3 | CONSTRUCTION | Aug 2021 | Sep 2021 | Aug 2021 | Sep 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LMCRFIDI | FIDI Seaport resilient waterfront | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Sep 2021 | Sep 2021 | Sep 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LMCRFIDI | FIDI Seaport resilient waterfront | 5 | SUBSTANTIAL COMPLETION | Sep 2021 | Oct 2021 | Sep 2021 | Oct 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LMCRFIDI | FIDI Seaport resilient waterfront | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2021 | Oct 2029 | Oct 2021 | Oct 2029
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16125 | 125th St: Interior and Exterior Comprehensive Renovation | 1 | DESIGN | Aug 2016 | Jan 2017 | Aug 2016 | Jan 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16125 | 125th St: Interior and Exterior Comprehensive Renovation | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2017 | Apr 2017 | Jan 2017 | Apr 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16125 | 125th St: Interior and Exterior Comprehensive Renovation | 3 | CONSTRUCTION | Apr 2017 | Apr 2018 | Apr 2017 | Apr 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16125 | 125th St: Interior and Exterior Comprehensive Renovation | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2018 | Feb 2019 | Apr 2023 | Feb 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16FWT | FORT WASHINGTON: MAJOR RENOVATION | 1 | DESIGN | Aug 2016 | Jan 2017 | Aug 2016 | Jan 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16FWT | FORT WASHINGTON: MAJOR RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2017 | Apr 2017 | Jan 2017 | Apr 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16FWT | FORT WASHINGTON: MAJOR RENOVATION | 3 | CONSTRUCTION | Apr 2017 | Apr 2018 | Apr 2017 | Apr 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16FWT | FORT WASHINGTON: MAJOR RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2018 | Feb 2019 | Apr 2023 | Feb 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-CCNY1 | Life Sciences - City College of New York | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-CCNY1 | Life Sciences - City College of New York | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-CCNY1 | Life Sciences - City College of New York | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-CCNY1 | Life Sciences - City College of New York | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-CCNY1 | Life Sciences - City College of New York | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-CCNY1 | Life Sciences - City College of New York | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-CCNY1 | Life Sciences - City College of New York | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-CCNY1 | Life Sciences - City College of New York | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-CCNY1 | Life Sciences - City College of New York | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-CCNY1 | Life Sciences - City College of New York | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2028
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-PRI | Life Sci Pandemic Response Institute | 1 | DESIGN | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-PRI | Life Sci Pandemic Response Institute | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Aug 2021 | Jul 2021 | Aug 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-PRI | Life Sci Pandemic Response Institute | 3 | CONSTRUCTION | Aug 2021 | Sep 2021 | Aug 2021 | Sep 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-PRI | Life Sci Pandemic Response Institute | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Sep 2021 | Sep 2021 | Sep 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-PRI | Life Sci Pandemic Response Institute | 5 | SUBSTANTIAL COMPLETION | Sep 2021 | Oct 2021 | Sep 2021 | Oct 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-PRI | Life Sci Pandemic Response Institute | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2021 | Jun 2023 | Oct 2021 | Jun 2027
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-STEM | New York City Translational Stem Cell Research Facility | 1 | DESIGN | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-STEM | New York City Translational Stem Cell Research Facility | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Aug 2021 | Jul 2021 | Aug 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-STEM | New York City Translational Stem Cell Research Facility | 3 | CONSTRUCTION | Aug 2021 | Sep 2021 | Aug 2021 | Sep 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-STEM | New York City Translational Stem Cell Research Facility | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Sep 2021 | Sep 2021 | Sep 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-STEM | New York City Translational Stem Cell Research Facility | 5 | SUBSTANTIAL COMPLETION | Sep 2021 | Oct 2021 | Sep 2021 | Oct 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-STEM | New York City Translational Stem Cell Research Facility | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2021 | Jun 2023 | Oct 2021 | Jun 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MANHGREEN | Manhattan Greenway | 1 | DESIGN | Jun 2017 | Jul 2017 | Jun 2017 | Jul 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MANHGREEN | Manhattan Greenway | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Aug 2017 | Jul 2017 | Aug 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MANHGREEN | Manhattan Greenway | 3 | CONSTRUCTION | Aug 2017 | Sep 2017 | Aug 2017 | Sep 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MANHGREEN | Manhattan Greenway | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Sep 2017 | Sep 2017 | Sep 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MANHGREEN | Manhattan Greenway | 5 | SUBSTANTIAL COMPLETION | Sep 2017 | Oct 2017 | Sep 2017 | Oct 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MANHGREEN | Manhattan Greenway | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2017 | Oct 2019 | Oct 2017 | Jun 2028
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTFEND | MCT PIER 90 FENDERING | 1 | DESIGN | Jul 2019 | Jul 2019 | Jul 2022 | Jul 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTFEND | MCT PIER 90 FENDERING | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jul 2023 | Aug 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTFEND | MCT PIER 90 FENDERING | 3 | CONSTRUCTION | Aug 2019 | Sep 2019 | Aug 2023 | Sep 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTFEND | MCT PIER 90 FENDERING | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Sep 2019 | Sep 2023 | Sep 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTFEND | MCT PIER 90 FENDERING | 5 | SUBSTANTIAL COMPLETION | Sep 2019 | Oct 2019 | Sep 2023 | Oct 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTFEND | MCT PIER 90 FENDERING | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2019 | Oct 2023 | Oct 2023 | Oct 2029
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTROOFSV | MCT Piers & Viaduct Roofs | 1 | DESIGN | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTROOFSV | MCT Piers & Viaduct Roofs | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Aug 2021 | Jul 2021 | Aug 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTROOFSV | MCT Piers & Viaduct Roofs | 3 | CONSTRUCTION | Aug 2021 | Sep 2021 | Aug 2021 | Sep 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTROOFSV | MCT Piers & Viaduct Roofs | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Sep 2021 | Sep 2021 | Sep 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTROOFSV | MCT Piers & Viaduct Roofs | 5 | SUBSTANTIAL COMPLETION | Sep 2021 | Oct 2031 | Sep 2021 | Oct 2031
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTROOFSV | MCT Piers & Viaduct Roofs | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2031 | Oct 2031 | Oct 2031 | Oct 2031
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MECAFIT | MECA FITNESS CENTER RENOVATION--FITNESS CENTER RENOVATION | 1 | DESIGN | Jul 2017 | Jul 2017 | Mar 2019 | Apr 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MECAFIT | MECA FITNESS CENTER RENOVATION--FITNESS CENTER RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Aug 2017 | Apr 2019 | Apr 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MECAFIT | MECA FITNESS CENTER RENOVATION--FITNESS CENTER RENOVATION | 3 | CONSTRUCTION | Aug 2017 | Sep 2017 | Apr 2019 | May 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MECAFIT | MECA FITNESS CENTER RENOVATION--FITNESS CENTER RENOVATION | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Sep 2017 | Jun 2019 | Jun 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MECAFIT | MECA FITNESS CENTER RENOVATION--FITNESS CENTER RENOVATION | 5 | SUBSTANTIAL COMPLETION | Sep 2017 | Oct 2017 | Jun 2019 | Jun 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MECAFIT | MECA FITNESS CENTER RENOVATION--FITNESS CENTER RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2017 | Oct 2017 | Jun 2019 | Jun 2028
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-3HRGL | NDF - Harlem River Greenway Link - New Park Development | 1 | DESIGN | Jul 2019 | Jul 2019 | Jul 2019 | Jul 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-3HRGL | NDF - Harlem River Greenway Link - New Park Development | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jul 2019 | Aug 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-3HRGL | NDF - Harlem River Greenway Link - New Park Development | 3 | CONSTRUCTION | Aug 2019 | Sep 2019 | Aug 2019 | Sep 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-3HRGL | NDF - Harlem River Greenway Link - New Park Development | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Sep 2019 | Sep 2025 | Sep 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-3HRGL | NDF - Harlem River Greenway Link - New Park Development | 5 | SUBSTANTIAL COMPLETION | Sep 2019 | Oct 2019 | Sep 2025 | Oct 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-3HRGL | NDF - Harlem River Greenway Link - New Park Development | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2019 | Oct 2019 | Oct 2025 | Oct 2029
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-EHWF1 | NDF - East Harlem SBS Workforce1 Center | 1 | DESIGN | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-EHWF1 | NDF - East Harlem SBS Workforce1 Center | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Aug 2021 | Jul 2021 | Aug 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-EHWF1 | NDF - East Harlem SBS Workforce1 Center | 3 | CONSTRUCTION | Aug 2021 | Sep 2021 | Aug 2021 | Sep 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-EHWF1 | NDF - East Harlem SBS Workforce1 Center | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Sep 2021 | Sep 2021 | Sep 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-EHWF1 | NDF - East Harlem SBS Workforce1 Center | 5 | SUBSTANTIAL COMPLETION | Sep 2021 | Oct 2026 | Sep 2021 | Oct 2026
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-EHWF1 | NDF - East Harlem SBS Workforce1 Center | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2026 | Oct 2026 | Oct 2026 | Oct 2026
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-INWCC | NDF - Inwood Cultural Center | 1 | DESIGN | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-INWCC | NDF - Inwood Cultural Center | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Aug 2021 | Jul 2021 | Aug 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-INWCC | NDF - Inwood Cultural Center | 3 | CONSTRUCTION | Aug 2021 | Sep 2021 | Aug 2021 | Sep 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-INWCC | NDF - Inwood Cultural Center | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Sep 2021 | Sep 2021 | Sep 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-INWCC | NDF - Inwood Cultural Center | 5 | SUBSTANTIAL COMPLETION | Sep 2021 | Oct 2026 | Sep 2021 | Oct 2026
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-INWCC | NDF - Inwood Cultural Center | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2026 | Oct 2026 | Oct 2026 | Oct 2026
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-LAMAR | NDF - La Marqueta Redevelopment | 1 | DESIGN | Jul 2019 | Jul 2019 | Jul 2019 | Jul 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-LAMAR | NDF - La Marqueta Redevelopment | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jul 2019 | Aug 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-LAMAR | NDF - La Marqueta Redevelopment | 3 | CONSTRUCTION | Aug 2019 | Sep 2019 | Aug 2019 | Sep 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-LAMAR | NDF - La Marqueta Redevelopment | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Sep 2019 | Sep 2019 | Sep 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-LAMAR | NDF - La Marqueta Redevelopment | 5 | SUBSTANTIAL COMPLETION | Sep 2019 | Oct 2019 | Sep 2019 | Oct 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-LAMAR | NDF - La Marqueta Redevelopment | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2019 | Oct 2022 | Oct 2019 | Oct 2028
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-NWOOD | NDF - Inwood Greenway and New Parks Development | 1 | DESIGN | Jul 2019 | Jul 2019 | Jul 2019 | Jul 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-NWOOD | NDF - Inwood Greenway and New Parks Development | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jul 2019 | Aug 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-NWOOD | NDF - Inwood Greenway and New Parks Development | 3 | CONSTRUCTION | Aug 2019 | Sep 2019 | Aug 2019 | Sep 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-NWOOD | NDF - Inwood Greenway and New Parks Development | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Sep 2019 | Sep 2019 | Sep 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-NWOOD | NDF - Inwood Greenway and New Parks Development | 5 | SUBSTANTIAL COMPLETION | Sep 2019 | Oct 2019 | Sep 2019 | Oct 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-NWOOD | NDF - Inwood Greenway and New Parks Development | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2019 | Oct 2021 | Oct 2019 | Oct 2028
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NONTDW | Nontraditional Employment for Women - Renovation of HQ | 1 | DESIGN | Jul 2016 | Jul 2016 | Jul 2021 | Jul 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NONTDW | Nontraditional Employment for Women - Renovation of HQ | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Jul 2021 | Aug 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NONTDW | Nontraditional Employment for Women - Renovation of HQ | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Aug 2021 | Sep 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NONTDW | Nontraditional Employment for Women - Renovation of HQ | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Sep 2021 | Sep 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NONTDW | Nontraditional Employment for Women - Renovation of HQ | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Sep 2021 | Oct 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NONTDW | Nontraditional Employment for Women - Renovation of HQ | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2016 | Oct 2021 | Oct 2027
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFBARGE | New York City Ferry - Barge Expansion | 1 | DESIGN | Jul 2019 | Jul 2019 | Jul 2019 | Jul 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFBARGE | New York City Ferry - Barge Expansion | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jul 2019 | Aug 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFBARGE | New York City Ferry - Barge Expansion | 3 | CONSTRUCTION | Aug 2019 | Sep 2019 | Aug 2019 | Sep 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFBARGE | New York City Ferry - Barge Expansion | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Sep 2019 | Sep 2024 | Sep 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFBARGE | New York City Ferry - Barge Expansion | 5 | SUBSTANTIAL COMPLETION | Sep 2019 | Oct 2021 | Sep 2024 | Oct 2026
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFBARGE | New York City Ferry - Barge Expansion | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2021 | Oct 2021 | Oct 2026 | Jun 2033
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-301BATW | Battery Park - Wharf | 1 | DESIGN | Jul 2015 | Jul 2015 | Jul 2015 | Jul 2015
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-301BATW | Battery Park - Wharf | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Aug 2015 | Jul 2015 | Aug 2015
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-301BATW | Battery Park - Wharf | 3 | CONSTRUCTION | Aug 2015 | Sep 2015 | Aug 2015 | Sep 2015
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-301BATW | Battery Park - Wharf | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2015 | Sep 2015 | Sep 2015 | Sep 2015
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-301BATW | Battery Park - Wharf | 5 | SUBSTANTIAL COMPLETION | Sep 2015 | Oct 2015 | Sep 2015 | Oct 2015
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-301BATW | Battery Park - Wharf | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2015 | Oct 2019 | Oct 2015 | Oct 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-309RVP2 | RIVERSIDE PARK 79 ST BOAT BASIN: C DOCK | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-309RVP2 | RIVERSIDE PARK 79 ST BOAT BASIN: C DOCK | 2 | DESIGN | Dec 2017 | Dec 2019 | Dec 2017 | Dec 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-309RVP2 | RIVERSIDE PARK 79 ST BOAT BASIN: C DOCK | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-309RVP2 | RIVERSIDE PARK 79 ST BOAT BASIN: C DOCK | 4 | CONSTRUCTION | Sep 2020 | Sep 2023 | Sep 2020 | Sep 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-309RVP2 | RIVERSIDE PARK 79 ST BOAT BASIN: C DOCK | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2025 | Sep 2023 | Sep 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-311RAND | Randall's Island New Track and Field Center | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2000 | Oct 2000 | Oct 2001 | Oct 2001
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-311RAND | Randall's Island New Track and Field Center | 3 | CONSTRUCTION | Oct 2000 | Jul 2007 | Apr 2002 | Jun 2011
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-311RAND | Randall's Island New Track and Field Center | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2007 | Jul 2007 | Jul 2011 | Jun 2011
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-311RAND | Randall's Island New Track and Field Center | 5 | SUBSTANTIAL COMPLETION | Jul 2007 | Jul 2007 | Jul 2011 | Jun 2011
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-311RAND | Randall's Island New Track and Field Center | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2007 | Jul 2007 | Jul 2011 | Jul 2011
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3ERE22J | East River Esplanande phase 4+ | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3ERE22J | East River Esplanande phase 4+ | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3ERE22J | East River Esplanande phase 4+ | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3ERE22J | East River Esplanande phase 4+ | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2027
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3ERE22J | East River Esplanande phase 4+ | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2027 | Sep 2028
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HIGHLL | FRIENDS OF THE HIGH LINE-LIFE SAFETY UPGRADES & CIRCULATION | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Jul 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HIGHLL | FRIENDS OF THE HIGH LINE-LIFE SAFETY UPGRADES & CIRCULATION | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2017 | Mar 2019 | Jul 2017 | Aug 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HIGHLL | FRIENDS OF THE HIGH LINE-LIFE SAFETY UPGRADES & CIRCULATION | 3 | CONSTRUCTION | Mar 2019 | Dec 2019 | Aug 2017 | Sep 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HIGHLL | FRIENDS OF THE HIGH LINE-LIFE SAFETY UPGRADES & CIRCULATION | 4 | ORIGINAL EQUIP & FURNISHING | Dec 2019 | Dec 2021 | Sep 2017 | Sep 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HIGHLL | FRIENDS OF THE HIGH LINE-LIFE SAFETY UPGRADES & CIRCULATION | 5 | SUBSTANTIAL COMPLETION | Dec 2021 | Dec 2022 | Sep 2017 | Oct 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HIGHLL | FRIENDS OF THE HIGH LINE-LIFE SAFETY UPGRADES & CIRCULATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2021 | Dec 2022 | Oct 2017 | Jun 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HILIN3 | Highline Phase 3 | 1 | DESIGN | Jan 2016 | Jun 2018 | Jan 2016 | Jun 2020
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HILIN3 | Highline Phase 3 | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Jun 2018 | Jul 2020 | Jun 2020
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HILIN3 | Highline Phase 3 | 3 | CONSTRUCTION | Jul 2018 | Jun 2021 | Jul 2020 | Jul 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HILIN3 | Highline Phase 3 | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2021 | Jun 2021 | Jul 2023 | Jul 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HILIN3 | Highline Phase 3 | 5 | SUBSTANTIAL COMPLETION | Jul 2021 | Jun 2021 | Jul 2023 | Jul 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HILIN3 | Highline Phase 3 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Jul 2021 | Jul 2023 | Jun 2033
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HRP132 | Harlem River Park 132-135 | 1 | DESIGN | Jul 2017 | Dec 2017 | Jul 2017 | Jul 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HRP132 | Harlem River Park 132-135 | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2017 | Dec 2019 | Jul 2017 | Aug 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HRP132 | Harlem River Park 132-135 | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Aug 2017 | Sep 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HRP132 | Harlem River Park 132-135 | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Sep 2022 | Sep 2017 | Sep 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HRP132 | Harlem River Park 132-135 | 5 | SUBSTANTIAL COMPLETION | Sep 2022 | Sep 2023 | Sep 2017 | Oct 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HRP132 | Harlem River Park 132-135 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Oct 2017 | Jun 2030
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P79MBR | Pier 79 South to Middle Barge Rehabilitation | 1 | DESIGN | Jul 2022 | Jul 2022 | Jul 2022 | Jul 2022
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P79MBR | Pier 79 South to Middle Barge Rehabilitation | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Aug 2022 | Jul 2022 | Aug 2022
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P79MBR | Pier 79 South to Middle Barge Rehabilitation | 3 | CONSTRUCTION | Aug 2022 | Sep 2022 | Aug 2022 | Sep 2022
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P79MBR | Pier 79 South to Middle Barge Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Sep 2022 | Sep 2022 | Sep 2022
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P79MBR | Pier 79 South to Middle Barge Rehabilitation | 5 | SUBSTANTIAL COMPLETION | Sep 2022 | Oct 2022 | Sep 2022 | Oct 2022
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P79MBR | Pier 79 South to Middle Barge Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2022 | Jun 2023 | Oct 2022 | Jun 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PASSSHIP4 | Manhattan Cruise Terminal - Viaduct Concrete Rehabilitation | 1 | DESIGN | Jan 2016 | Jun 2018 | Jan 2016 | Jun 2020
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PASSSHIP4 | Manhattan Cruise Terminal - Viaduct Concrete Rehabilitation | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Jun 2018 | Jul 2020 | Jun 2020
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PASSSHIP4 | Manhattan Cruise Terminal - Viaduct Concrete Rehabilitation | 3 | CONSTRUCTION | Jul 2018 | Jun 2021 | Jul 2020 | Jul 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PASSSHIP4 | Manhattan Cruise Terminal - Viaduct Concrete Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2021 | Jun 2021 | Jul 2023 | Jul 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PASSSHIP4 | Manhattan Cruise Terminal - Viaduct Concrete Rehabilitation | 5 | SUBSTANTIAL COMPLETION | Jul 2021 | Jun 2021 | Jul 2023 | Jul 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PASSSHIP4 | Manhattan Cruise Terminal - Viaduct Concrete Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Jul 2021 | Jul 2023 | Jul 2026
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36 | Pier 36 Structural Rehab | 1 | DEVELOP SCOPE | May 2019 | Jul 2019 | May 2019 | Jul 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36 | Pier 36 Structural Rehab | 2 | PRELIMINARY DESIGN | Jul 2019 | Nov 2019 | Jul 2019 | Nov 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36 | Pier 36 Structural Rehab | 3 | FINAL DESIGN | Nov 2019 | Mar 2020 | Nov 2019 | Mar 2020
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36 | Pier 36 Structural Rehab | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Jun 2020 | Mar 2020 | Jun 2020
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36 | Pier 36 Structural Rehab | 5 | CONSTRUCTION TO 25% | Jul 2020 | Jun 2021 | Jul 2020 | Jun 2026
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36 | Pier 36 Structural Rehab | 6 | CONSTRUCTION TO 50% | Jul 2021 | Jun 2022 | Jul 2026 | Jun 2027
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36 | Pier 36 Structural Rehab | 7 | CONSTRUCTION TO 75% | Jul 2022 | Jun 2023 | Jul 2027 | Jun 2028
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36 | Pier 36 Structural Rehab | 8 | SUBSTANTIAL COMPLETION | Jul 2023 | Nov 2023 | Jun 2028 | Nov 2028
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36 | Pier 36 Structural Rehab | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2023 | Mar 2024 | Nov 2028 | Mar 2029
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36STR | Pier 36 Structural Rehab | 1 | DESIGN | Jul 2018 | Jul 2018 | Jul 2018 | Jul 2018
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36STR | Pier 36 Structural Rehab | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Aug 2018 | Jul 2018 | Aug 2018
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36STR | Pier 36 Structural Rehab | 3 | CONSTRUCTION | Aug 2018 | Sep 2018 | Aug 2018 | Sep 2018
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36STR | Pier 36 Structural Rehab | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2018 | Sep 2018 | Sep 2018 | Sep 2018
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36STR | Pier 36 Structural Rehab | 5 | SUBSTANTIAL COMPLETION | Sep 2018 | Oct 2018 | Sep 2018 | Oct 2018
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36STR | Pier 36 Structural Rehab | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2018 | Oct 2018 | Oct 2018 | Oct 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER42CNT | Pier 42 and East River Park Connector Program | 1 | DESIGN | Jan 2019 | Feb 2019 | Jan 2019 | Feb 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER42CNT | Pier 42 and East River Park Connector Program | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2019 | Mar 2019 | Feb 2019 | Mar 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER42CNT | Pier 42 and East River Park Connector Program | 3 | CONSTRUCTION | Mar 2019 | Apr 2019 | Mar 2019 | Apr 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER42CNT | Pier 42 and East River Park Connector Program | 4 | ORIGINAL EQUIP & FURNISHING | Apr 2019 | Apr 2019 | Apr 2019 | Apr 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER42CNT | Pier 42 and East River Park Connector Program | 5 | SUBSTANTIAL COMPLETION | Apr 2019 | May 2021 | Apr 2019 | May 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER42CNT | Pier 42 and East River Park Connector Program | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2021 | May 2021 | May 2025 | May 2026
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER6PILE | Pier 6 Pile Rehabilitation | 1 | DESIGN | Mar 2015 | Sep 2015 | Mar 2017 | Sep 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER6PILE | Pier 6 Pile Rehabilitation | 2 | BID AWARD AND REGISTER CONTRCT | Oct 2015 | Sep 2015 | Oct 2017 | Sep 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER6PILE | Pier 6 Pile Rehabilitation | 3 | CONSTRUCTION | Oct 2015 | Oct 2016 | Oct 2017 | Oct 2018
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER6PILE | Pier 6 Pile Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | Oct 2016 | Oct 2016 | Oct 2018 | Oct 2018
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER6PILE | Pier 6 Pile Rehabilitation | 5 | SUBSTANTIAL COMPLETION | Oct 2016 | Oct 2016 | Oct 2018 | Oct 2018
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER6PILE | Pier 6 Pile Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2016 | Oct 2018 | Jun 2031
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER79REH | Pier 79 Float to Barge Rehabilitation | 1 | DESIGN | Jul 2023 | Jul 2023 | Jul 2023 | Jul 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER79REH | Pier 79 Float to Barge Rehabilitation | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER79REH | Pier 79 Float to Barge Rehabilitation | 3 | CONSTRUCTION | Aug 2023 | Sep 2023 | Aug 2023 | Sep 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER79REH | Pier 79 Float to Barge Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Sep 2023 | Sep 2023 | Sep 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER79REH | Pier 79 Float to Barge Rehabilitation | 5 | SUBSTANTIAL COMPLETION | Sep 2023 | Oct 2023 | Sep 2023 | Oct 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER79REH | Pier 79 Float to Barge Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2023 | Jun 2024 | Oct 2023 | Jun 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER94ENC | PIER 94 -- RECONSTRUCTION AND ENCAPSULATION | 1 | DESIGN | Jul 2022 | Jul 2022 | Jul 2022 | Jul 2022
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER94ENC | PIER 94 -- RECONSTRUCTION AND ENCAPSULATION | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Aug 2022 | Jul 2022 | Aug 2022
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER94ENC | PIER 94 -- RECONSTRUCTION AND ENCAPSULATION | 3 | CONSTRUCTION | Aug 2022 | Sep 2022 | Aug 2022 | Sep 2022
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER94ENC | PIER 94 -- RECONSTRUCTION AND ENCAPSULATION | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Sep 2022 | Sep 2022 | Sep 2022
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER94ENC | PIER 94 -- RECONSTRUCTION AND ENCAPSULATION | 5 | SUBSTANTIAL COMPLETION | Sep 2022 | Oct 2022 | Sep 2022 | Oct 2022
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER94ENC | PIER 94 -- RECONSTRUCTION AND ENCAPSULATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2022 | Jun 2026 | Oct 2022 | Jun 2026
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER94RH | Pier 94 Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | Oct 2012 | Oct 2012 | Oct 2015 | Oct 2015
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER94RH | Pier 94 Rehabilitation | 5 | SUBSTANTIAL COMPLETION | Oct 2012 | Oct 2012 | Oct 2015 | Oct 2015
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER94RH | Pier 94 Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2012 | Oct 2012 | Oct 2015 | Jun 2020
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIERS35N6 | Pier 35 & 36 Substructure Rehabilitation | 1 | DESIGN | Jul 2016 | Jul 2016 | Jul 2018 | Jul 2018
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIERS35N6 | Pier 35 & 36 Substructure Rehabilitation | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Jul 2018 | Aug 2018
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIERS35N6 | Pier 35 & 36 Substructure Rehabilitation | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Aug 2018 | Sep 2018
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIERS35N6 | Pier 35 & 36 Substructure Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Sep 2018 | Sep 2018
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIERS35N6 | Pier 35 & 36 Substructure Rehabilitation | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Sep 2018 | Oct 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIERS35N6 | Pier 35 & 36 Substructure Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2016 | Oct 2024 | Oct 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIERS8890 | Piers 88 & 90 Cluster Encapsulation Project | 1 | DESIGN | Jun 2015 | Jul 2015 | Jun 2018 | Jul 2018
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIERS8890 | Piers 88 & 90 Cluster Encapsulation Project | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Aug 2015 | Jul 2018 | Aug 2018
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIERS8890 | Piers 88 & 90 Cluster Encapsulation Project | 3 | CONSTRUCTION | Aug 2015 | Sep 2015 | Aug 2018 | Sep 2018
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIERS8890 | Piers 88 & 90 Cluster Encapsulation Project | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2015 | Sep 2015 | Sep 2018 | Sep 2018
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIERS8890 | Piers 88 & 90 Cluster Encapsulation Project | 5 | SUBSTANTIAL COMPLETION | Sep 2015 | Oct 2015 | Sep 2018 | Oct 2018
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIERS8890 | Piers 88 & 90 Cluster Encapsulation Project | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2015 | Oct 2015 | Oct 2018 | Jun 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIR11MONO | Pier 11 Monopile Replacement | 1 | DESIGN | Jul 2023 | Jul 2023 | Jul 2023 | Jul 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIR11MONO | Pier 11 Monopile Replacement | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIR11MONO | Pier 11 Monopile Replacement | 3 | CONSTRUCTION | Aug 2023 | Sep 2023 | Aug 2023 | Sep 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIR11MONO | Pier 11 Monopile Replacement | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Sep 2023 | Sep 2023 | Sep 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIR11MONO | Pier 11 Monopile Replacement | 5 | SUBSTANTIAL COMPLETION | Sep 2023 | Oct 2023 | Sep 2023 | Oct 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIR11MONO | Pier 11 Monopile Replacement | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2023 | Jun 2024 | Oct 2023 | Jun 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV034GRUV | AMNH - Gilder Center Green Bldg. | 1 | DEVELOP SCOPE | Jul 2025 | Sep 2025 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV034GRUV | AMNH - Gilder Center Green Bldg. | 2 | PRELIMINARY DESIGN | Sep 2025 | Jan 2026 | Sep 2023 | Jan 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV034GRUV | AMNH - Gilder Center Green Bldg. | 3 | FINAL DESIGN | Jan 2026 | Jul 2026 | Jan 2024 | Jul 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV034GRUV | AMNH - Gilder Center Green Bldg. | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2026 | Oct 2026 | Jul 2024 | Oct 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV034GRUV | AMNH - Gilder Center Green Bldg. | 5 | CONSTRUCTION TO 25% | Oct 2026 | Feb 2027 | Oct 2024 | Feb 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV034GRUV | AMNH - Gilder Center Green Bldg. | 6 | CONSTRUCTION TO 50% | Feb 2027 | Jun 2027 | Feb 2025 | Jun 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV034GRUV | AMNH - Gilder Center Green Bldg. | 7 | CONSTRUCTION TO 75% | Jun 2027 | Oct 2027 | Jun 2025 | Oct 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV034GRUV | AMNH - Gilder Center Green Bldg. | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jan 2028 | Oct 2025 | Jan 2026
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV034GRUV | AMNH - Gilder Center Green Bldg. | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Mar 2028 | Jan 2026 | Mar 2026
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV034GRUV | AMNH - Gilder Center Green Bldg. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2028 | Apr 2028 | Mar 2026 | Apr 2026
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-BEY | DCA PFA - Percent for Art Beyond Sims | 1 | DESIGN | Jun 2019 | Jul 2019 | Jun 2019 | Jul 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-BEY | DCA PFA - Percent for Art Beyond Sims | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jul 2019 | Aug 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-BEY | DCA PFA - Percent for Art Beyond Sims | 3 | CONSTRUCTION | Aug 2019 | Sep 2019 | Aug 2019 | Sep 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-BEY | DCA PFA - Percent for Art Beyond Sims | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Sep 2019 | Sep 2019 | Sep 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-BEY | DCA PFA - Percent for Art Beyond Sims | 5 | SUBSTANTIAL COMPLETION | Sep 2019 | Oct 2021 | Sep 2019 | Oct 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-BEY | DCA PFA - Percent for Art Beyond Sims | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467ELMB | ELM- El Museo - Gallery Environmental Stabilzation Project | 1 | DESIGN | May 2015 | Jun 2015 | May 2015 | Jun 2015
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467ELMB | ELM- El Museo - Gallery Environmental Stabilzation Project | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2015 | Jun 2015 | Jun 2015 | Jun 2015
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467ELMB | ELM- El Museo - Gallery Environmental Stabilzation Project | 3 | CONSTRUCTION | Jun 2015 | Aug 2015 | Jun 2015 | Aug 2015
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467ELMB | ELM- El Museo - Gallery Environmental Stabilzation Project | 4 | ORIGINAL EQUIP & FURNISHING | Aug 2015 | Aug 2015 | Aug 2015 | Aug 2015
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467ELMB | ELM- El Museo - Gallery Environmental Stabilzation Project | 5 | SUBSTANTIAL COMPLETION | Aug 2015 | Aug 2015 | Aug 2015 | Aug 2015
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467ELMB | ELM- El Museo - Gallery Environmental Stabilzation Project | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2015 | Aug 2015 | Aug 2015 | Jun 2033
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-PCT | DCA PFA - Percent for Art Tito P. | 1 | DEVELOP SCOPE | Apr 2008 | Jun 2008 | Feb 2016 | Mar 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-PCT | DCA PFA - Percent for Art Tito P. | 2 | PRELIMINARY DESIGN | Jun 2008 | Oct 2008 | Mar 2016 | Apr 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-PCT | DCA PFA - Percent for Art Tito P. | 3 | FINAL DESIGN | Oct 2008 | Apr 2009 | Apr 2016 | May 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-PCT | DCA PFA - Percent for Art Tito P. | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2009 | Jul 2009 | May 2016 | May 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-PCT | DCA PFA - Percent for Art Tito P. | 5 | CONSTRUCTION TO 25% | Jul 2009 | Nov 2009 | May 2016 | Jun 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-PCT | DCA PFA - Percent for Art Tito P. | 6 | CONSTRUCTION TO 50% | Nov 2009 | Mar 2010 | Jun 2016 | Jun 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-PCT | DCA PFA - Percent for Art Tito P. | 7 | CONSTRUCTION TO 75% | Mar 2010 | Jul 2010 | Jun 2016 | Jun 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-PCT | DCA PFA - Percent for Art Tito P. | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2010 | Oct 2010 | Jun 2016 | Jun 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-PCT | DCA PFA - Percent for Art Tito P. | 9 | SUBSTANTIAL COMPLETION | Oct 2010 | Dec 2010 | Jun 2016 | Jun 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-PCT | DCA PFA - Percent for Art Tito P. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2010 | Jan 2011 | Jun 2016 | Jun 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV503SDWK | CH - Carnegie Sidewalk Restoration | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV503SDWK | CH - Carnegie Sidewalk Restoration | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV503SDWK | CH - Carnegie Sidewalk Restoration | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2023 | Jul 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV503SDWK | CH - Carnegie Sidewalk Restoration | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2023 | Oct 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV503SDWK | CH - Carnegie Sidewalk Restoration | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2023 | Feb 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV503SDWK | CH - Carnegie Sidewalk Restoration | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2024 | Jun 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV503SDWK | CH - Carnegie Sidewalk Restoration | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2024 | Oct 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV503SDWK | CH - Carnegie Sidewalk Restoration | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2024 | Jan 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV503SDWK | CH - Carnegie Sidewalk Restoration | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2025 | Mar 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV503SDWK | CH - Carnegie Sidewalk Restoration | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2025 | Apr 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PWD5CFTH | FA - Coalition for the Homeless | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2007 | Sep 2007 | Sep 2007 | Sep 2007
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PWD5CFTH | FA - Coalition for the Homeless | 5 | SUBSTANTIAL COMPLETION | Sep 2007 | Sep 2007 | Sep 2007 | Sep 2007
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PWD5CFTH | FA - Coalition for the Homeless | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2007 | Sep 2007 | Sep 2007 | Jun 2011
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | RE25-004 | FA - Courts & Sports at Pier 36 | 1 | DESIGN | Jul 1999 | Jul 1999 | Dec 2006 | Jan 2009
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | RE25-004 | FA - Courts & Sports at Pier 36 | 2 | BID AWARD AND REGISTER CONTRCT | Jul 1999 | Aug 1999 | Jan 2009 | Aug 2010
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | RE25-004 | FA - Courts & Sports at Pier 36 | 3 | CONSTRUCTION | Aug 1999 | Jun 2007 | Jun 2007 | Jun 2011
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | RE25-004 | FA - Courts & Sports at Pier 36 | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2007 | Jun 2007 | Jul 2011 | Jun 2011
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | RE25-004 | FA - Courts & Sports at Pier 36 | 5 | SUBSTANTIAL COMPLETION | Jul 2007 | Jun 2007 | Jul 2011 | Jun 2011
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | RE25-004 | FA - Courts & Sports at Pier 36 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2007 | Jul 2007 | Jul 2011 | Jul 2011
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSEDOCK | Roosevelt Island Dock | 1 | DESIGN | Aug 2006 | Aug 2006 | Aug 2018 | Aug 2018
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSEDOCK | Roosevelt Island Dock | 2 | BID AWARD AND REGISTER CONTRCT | Aug 2006 | Sep 2006 | Aug 2018 | Sep 2018
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSEDOCK | Roosevelt Island Dock | 3 | CONSTRUCTION | Sep 2006 | Oct 2006 | May 2011 | Jun 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSEDOCK | Roosevelt Island Dock | 4 | ORIGINAL EQUIP & FURNISHING | Oct 2006 | Oct 2006 | Jul 2017 | Jun 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSEDOCK | Roosevelt Island Dock | 5 | SUBSTANTIAL COMPLETION | Oct 2006 | Nov 2006 | Jul 2017 | Jun 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSEDOCK | Roosevelt Island Dock | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2006 | Nov 2006 | Dec 2018 | Dec 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSEOPER | Roosevelt Island Operating Corp - Blackwell House | 1 | DESIGN | Jul 2019 | Jul 2019 | Jul 2019 | Jul 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSEOPER | Roosevelt Island Operating Corp - Blackwell House | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jul 2019 | Aug 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSEOPER | Roosevelt Island Operating Corp - Blackwell House | 3 | CONSTRUCTION | Aug 2019 | Sep 2019 | Aug 2019 | Sep 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSEOPER | Roosevelt Island Operating Corp - Blackwell House | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Sep 2019 | Sep 2019 | Sep 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSEOPER | Roosevelt Island Operating Corp - Blackwell House | 5 | SUBSTANTIAL COMPLETION | Sep 2019 | Oct 2021 | Sep 2019 | Oct 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSEOPER | Roosevelt Island Operating Corp - Blackwell House | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2021 | Oct 2021 | Oct 2025 | Oct 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSISLTH | ROOSEVELT ISLAND LIGHTHOUSE | 1 | DESIGN | Jul 2019 | Jul 2019 | Jun 2016 | Jul 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSISLTH | ROOSEVELT ISLAND LIGHTHOUSE | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jul 2016 | Aug 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSISLTH | ROOSEVELT ISLAND LIGHTHOUSE | 3 | CONSTRUCTION | Aug 2019 | Sep 2019 | Aug 2016 | Sep 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSISLTH | ROOSEVELT ISLAND LIGHTHOUSE | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Sep 2019 | Sep 2016 | Sep 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSISLTH | ROOSEVELT ISLAND LIGHTHOUSE | 5 | SUBSTANTIAL COMPLETION | Sep 2019 | Oct 2021 | Sep 2016 | Oct 2018
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSISLTH | ROOSEVELT ISLAND LIGHTHOUSE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2021 | Oct 2021 | Oct 2018 | Oct 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1113 | HHC FEMA PMP BELLEVUE EXISTING VERTICAL TRANSPORTATION | 1 | DESIGN | Jul 2017 | Jul 2017 | Jul 2017 | Jul 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1113 | HHC FEMA PMP BELLEVUE EXISTING VERTICAL TRANSPORTATION | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Aug 2017 | Jul 2017 | Aug 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1113 | HHC FEMA PMP BELLEVUE EXISTING VERTICAL TRANSPORTATION | 3 | CONSTRUCTION | Aug 2017 | Sep 2017 | Aug 2017 | Sep 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1113 | HHC FEMA PMP BELLEVUE EXISTING VERTICAL TRANSPORTATION | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Sep 2017 | Sep 2017 | Sep 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1113 | HHC FEMA PMP BELLEVUE EXISTING VERTICAL TRANSPORTATION | 5 | SUBSTANTIAL COMPLETION | Sep 2017 | Oct 2017 | Sep 2017 | Oct 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1113 | HHC FEMA PMP BELLEVUE EXISTING VERTICAL TRANSPORTATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2017 | Oct 2017 | Oct 2017 | Oct 2028
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND3705 | METROPOLITAN HOSPITAL FLOOD MITIGATION SYSTEM | 1 | DESIGN | Jul 2016 | Jul 2016 | Mar 2015 | Apr 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND3705 | METROPOLITAN HOSPITAL FLOOD MITIGATION SYSTEM | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Apr 2023 | Apr 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND3705 | METROPOLITAN HOSPITAL FLOOD MITIGATION SYSTEM | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Apr 2023 | May 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND3705 | METROPOLITAN HOSPITAL FLOOD MITIGATION SYSTEM | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | May 2023 | Jun 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND3705 | METROPOLITAN HOSPITAL FLOOD MITIGATION SYSTEM | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Jun 2023 | Jun 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND3705 | METROPOLITAN HOSPITAL FLOOD MITIGATION SYSTEM | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2016 | Jun 2023 | Jun 2027
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6701 | COLER : DESIGN & CONSTRUCTION FOR NEW GENERATOR | 1 | DESIGN | Jan 2016 | Jan 2016 | Jan 2016 | Jan 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6701 | COLER : DESIGN & CONSTRUCTION FOR NEW GENERATOR | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2015 | Jun 2016 | Sep 2015 | Jun 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6701 | COLER : DESIGN & CONSTRUCTION FOR NEW GENERATOR | 3 | CONSTRUCTION | Jul 2016 | Jun 2017 | Jul 2016 | Jun 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6701 | COLER : DESIGN & CONSTRUCTION FOR NEW GENERATOR | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2017 | Jun 2020 | Jul 2017 | Jun 2020
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6701 | COLER : DESIGN & CONSTRUCTION FOR NEW GENERATOR | 5 | SUBSTANTIAL COMPLETION | Jul 2020 | Jun 2020 | Jul 2020 | Jun 2020
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6701 | COLER : DESIGN & CONSTRUCTION FOR NEW GENERATOR | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Jul 2020 | Jul 2020 | Jun 2029
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD15 | PIER 36 ELECTRICAL CONDUIT | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Jun 2016 | Jul 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD15 | PIER 36 ELECTRICAL CONDUIT | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Jul 2024 | Aug 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD15 | PIER 36 ELECTRICAL CONDUIT | 3 | FINAL DESIGN | Jan 2017 | May 2017 | Aug 2024 | Sep 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD15 | PIER 36 ELECTRICAL CONDUIT | 4 | BID AWARD AND REGISTER CONTRCT | May 2017 | Nov 2017 | Sep 2024 | Sep 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD15 | PIER 36 ELECTRICAL CONDUIT | 5 | CONSTRUCTION TO 25% | Nov 2017 | Mar 2018 | Sep 2024 | Oct 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD15 | PIER 36 ELECTRICAL CONDUIT | 6 | CONSTRUCTION TO 50% | Mar 2018 | Jul 2018 | Oct 2024 | Oct 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD15 | PIER 36 ELECTRICAL CONDUIT | 7 | CONSTRUCTION TO 75% | Jul 2018 | Nov 2018 | Oct 2024 | Oct 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD15 | PIER 36 ELECTRICAL CONDUIT | 8 | ORIGINAL EQUIP & FURNISHING | Nov 2018 | Feb 2019 | Oct 2024 | Oct 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD15 | PIER 36 ELECTRICAL CONDUIT | 9 | SUBSTANTIAL COMPLETION | Feb 2019 | Apr 2019 | Oct 2024 | Oct 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD15 | PIER 36 ELECTRICAL CONDUIT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2019 | May 2019 | Oct 2024 | Oct 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDR2BRG | Construction of Flex Barges | 1 | DESIGN | Jul 2016 | Jul 2016 | Jul 2016 | Jul 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDR2BRG | Construction of Flex Barges | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Jul 2016 | Aug 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDR2BRG | Construction of Flex Barges | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Aug 2016 | Sep 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDR2BRG | Construction of Flex Barges | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Sep 2016 | Sep 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDR2BRG | Construction of Flex Barges | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Sep 2016 | Oct 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDR2BRG | Construction of Flex Barges | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2020 | Oct 2016 | Oct 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRLE34 | FA Resiliency - Land Hardening E 34 street | 1 | DESIGN | Jul 2016 | Jul 2016 | Jul 2016 | Jul 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRLE34 | FA Resiliency - Land Hardening E 34 street | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Jul 2016 | Aug 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRLE34 | FA Resiliency - Land Hardening E 34 street | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Aug 2016 | Sep 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRLE34 | FA Resiliency - Land Hardening E 34 street | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Sep 2016 | Sep 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRLE34 | FA Resiliency - Land Hardening E 34 street | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Sep 2016 | Oct 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRLE34 | FA Resiliency - Land Hardening E 34 street | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2020 | Oct 2016 | Jun 2026
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGI | Governors Island Hurricane Sandy Repairs | 1 | DESIGN | Jan 2016 | Jan 2016 | Jan 2016 | Jan 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGI | Governors Island Hurricane Sandy Repairs | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2016 | Jun 2016 | Jan 2016 | Jun 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGI | Governors Island Hurricane Sandy Repairs | 3 | CONSTRUCTION | Jul 2016 | Jun 2017 | Jul 2021 | Jun 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGI | Governors Island Hurricane Sandy Repairs | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2017 | Jun 2020 | Jul 2022 | Jun 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGI | Governors Island Hurricane Sandy Repairs | 5 | SUBSTANTIAL COMPLETION | Jul 2020 | Jun 2020 | Jul 2023 | Jun 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGI | Governors Island Hurricane Sandy Repairs | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Jul 2020 | Jul 2024 | Jun 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGIBM | Governors Island - Hurricane Sandy BMB Repair | 1 | DESIGN | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGIBM | Governors Island - Hurricane Sandy BMB Repair | 2 | BID AWARD AND REGISTER CONTRCT | Apr 2024 | May 2024 | Apr 2024 | May 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGIBM | Governors Island - Hurricane Sandy BMB Repair | 3 | CONSTRUCTION | Jun 2024 | Dec 2024 | Jun 2024 | Dec 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGIBM | Governors Island - Hurricane Sandy BMB Repair | 4 | ORIGINAL EQUIP & FURNISHING | Jun 2024 | Dec 2024 | Jun 2024 | Dec 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGIBM | Governors Island - Hurricane Sandy BMB Repair | 5 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGIBM | Governors Island - Hurricane Sandy BMB Repair | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2025 | Jun 2025 | Apr 2025 | Jun 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGIEL | Governors Island - Hurricane Sandy Electrical Repairs | 1 | DESIGN | Jan 2016 | Jan 2016 | Jan 2016 | Jan 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGIEL | Governors Island - Hurricane Sandy Electrical Repairs | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2016 | Jun 2016 | Jul 2019 | Jun 2020
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGIEL | Governors Island - Hurricane Sandy Electrical Repairs | 3 | CONSTRUCTION | Jul 2016 | Jun 2017 | Jul 2020 | Jun 2022
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGIEL | Governors Island - Hurricane Sandy Electrical Repairs | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2017 | Jun 2020 | Jul 2022 | Jun 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGIEL | Governors Island - Hurricane Sandy Electrical Repairs | 5 | SUBSTANTIAL COMPLETION | Jul 2020 | Jun 2020 | Jul 2023 | Dec 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGIEL | Governors Island - Hurricane Sandy Electrical Repairs | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Jul 2020 | Jan 2024 | Jun 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBSRELOCA | SBS FY18 Relocation to 1 Liberty Plaza | 1 | DESIGN | Jul 2017 | Jul 2017 | Jul 2017 | Jul 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBSRELOCA | SBS FY18 Relocation to 1 Liberty Plaza | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Aug 2017 | Jul 2024 | Aug 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBSRELOCA | SBS FY18 Relocation to 1 Liberty Plaza | 3 | CONSTRUCTION | Aug 2017 | Sep 2017 | Aug 2024 | Sep 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBSRELOCA | SBS FY18 Relocation to 1 Liberty Plaza | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Sep 2017 | Sep 2024 | Sep 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBSRELOCA | SBS FY18 Relocation to 1 Liberty Plaza | 5 | SUBSTANTIAL COMPLETION | Sep 2017 | Oct 2017 | Sep 2024 | Oct 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBSRELOCA | SBS FY18 Relocation to 1 Liberty Plaza | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2017 | Oct 2017 | Oct 2024 | Jun 2031
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SKYPORT | Skyport Garage and Marina Rehabilitation | 1 | DESIGN | Jul 2017 | Jul 2017 | Mar 2019 | Apr 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SKYPORT | Skyport Garage and Marina Rehabilitation | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Aug 2017 | Apr 2019 | Apr 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SKYPORT | Skyport Garage and Marina Rehabilitation | 3 | CONSTRUCTION | Aug 2017 | Sep 2017 | Apr 2019 | May 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SKYPORT | Skyport Garage and Marina Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Sep 2017 | Jun 2019 | Jun 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SKYPORT | Skyport Garage and Marina Rehabilitation | 5 | SUBSTANTIAL COMPLETION | Sep 2017 | Oct 2017 | Jun 2019 | Jun 2019
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SKYPORT | Skyport Garage and Marina Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2017 | Oct 2017 | Jun 2019 | Jun 2031
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SLIPEBARG | Slip E Barge Replacement | 1 | DESIGN | Jul 2023 | Jul 2023 | Jul 2023 | Jul 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SLIPEBARG | Slip E Barge Replacement | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SLIPEBARG | Slip E Barge Replacement | 3 | CONSTRUCTION | Aug 2023 | Sep 2023 | Aug 2023 | Sep 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SLIPEBARG | Slip E Barge Replacement | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Sep 2023 | Sep 2023 | Sep 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SLIPEBARG | Slip E Barge Replacement | 5 | SUBSTANTIAL COMPLETION | Sep 2023 | Oct 2023 | Sep 2023 | Oct 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SLIPEBARG | Slip E Barge Replacement | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2023 | Jun 2024 | Oct 2023 | Jun 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SOLAR2 | CEC Stuyvesant Cove Inc.-Construction of Solar 2 | 1 | DESIGN | Jun 2015 | Jul 2015 | Jun 2015 | Jul 2015
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SOLAR2 | CEC Stuyvesant Cove Inc.-Construction of Solar 2 | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Aug 2015 | Jul 2015 | Aug 2015
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SOLAR2 | CEC Stuyvesant Cove Inc.-Construction of Solar 2 | 3 | CONSTRUCTION | Aug 2015 | Sep 2015 | Aug 2015 | Sep 2015
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SOLAR2 | CEC Stuyvesant Cove Inc.-Construction of Solar 2 | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2015 | Sep 2015 | Sep 2015 | Sep 2015
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SOLAR2 | CEC Stuyvesant Cove Inc.-Construction of Solar 2 | 5 | SUBSTANTIAL COMPLETION | Sep 2015 | Oct 2015 | Sep 2015 | Oct 2015
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SOLAR2 | CEC Stuyvesant Cove Inc.-Construction of Solar 2 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2015 | Oct 2015 | Oct 2015 | Oct 2025
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SPARCCUNY | BROOKDALE | 1 | DESIGN | Jul 2023 | Jul 2023 | Jul 2023 | Jul 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SPARCCUNY | BROOKDALE | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SPARCCUNY | BROOKDALE | 3 | CONSTRUCTION | Aug 2023 | Sep 2023 | Aug 2023 | Sep 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SPARCCUNY | BROOKDALE | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Sep 2023 | Sep 2023 | Sep 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SPARCCUNY | BROOKDALE | 5 | SUBSTANTIAL COMPLETION | Sep 2023 | Oct 2023 | Sep 2023 | Oct 2023
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SPARCCUNY | BROOKDALE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2023 | Jun 2028 | Oct 2023 | Jun 2028
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | STUYBULK2 | Stuyvesant Cove Park Bulkhead Park Repair | 1 | DESIGN | Jul 2018 | Jul 2018 | Jul 2021 | Jul 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | STUYBULK2 | Stuyvesant Cove Park Bulkhead Park Repair | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Aug 2018 | Jul 2021 | Aug 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | STUYBULK2 | Stuyvesant Cove Park Bulkhead Park Repair | 3 | CONSTRUCTION | Aug 2018 | Sep 2018 | Aug 2021 | Sep 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | STUYBULK2 | Stuyvesant Cove Park Bulkhead Park Repair | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2018 | Sep 2018 | Sep 2021 | Sep 2021
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | STUYBULK2 | Stuyvesant Cove Park Bulkhead Park Repair | 5 | SUBSTANTIAL COMPLETION | Sep 2018 | Oct 2021 | Sep 2021 | Oct 2028
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | STUYBULK2 | Stuyvesant Cove Park Bulkhead Park Repair | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2021 | Oct 2021 | Oct 2028 | Oct 2028
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | W125TRANS | West 125th Street/Manhattanville | 1 | DESIGN | Nov 2004 | Nov 2004 | Nov 2007 | Nov 2007
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | W125TRANS | West 125th Street/Manhattanville | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2004 | Dec 2004 | Nov 2007 | Dec 2007
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | W125TRANS | West 125th Street/Manhattanville | 3 | CONSTRUCTION | Dec 2004 | Jun 2008 | Dec 2007 | Jun 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | W125TRANS | West 125th Street/Manhattanville | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2008 | Jun 2008 | Jul 2024 | Jun 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | W125TRANS | West 125th Street/Manhattanville | 5 | SUBSTANTIAL COMPLETION | Jul 2008 | Jun 2008 | Jul 2024 | Jun 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | W125TRANS | West 125th Street/Manhattanville | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2008 | Jul 2008 | Jul 2024 | Jun 2031
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WATERST | Water Street Corridor Streetscape Improvements | 1 | DESIGN | Jan 2016 | Jan 2016 | Jan 2016 | Jan 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WATERST | Water Street Corridor Streetscape Improvements | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2016 | Jun 2016 | Jan 2016 | Jun 2016
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WATERST | Water Street Corridor Streetscape Improvements | 3 | CONSTRUCTION | Jul 2016 | Jun 2017 | Jul 2016 | Jun 2017
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WATERST | Water Street Corridor Streetscape Improvements | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2017 | Jun 2020 | Jul 2017 | Jun 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WATERST | Water Street Corridor Streetscape Improvements | 5 | SUBSTANTIAL COMPLETION | Jul 2020 | Jun 2020 | Jul 2024 | Jun 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WATERST | Water Street Corridor Streetscape Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Jul 2020 | Jul 2024 | Jul 2024
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WHARLMPK | West Harlem Piers Park | 1 | DESIGN | Jul 2019 | Jul 2019 | Jun 2021 | Jul 2028
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WHARLMPK | West Harlem Piers Park | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jul 2028 | Aug 2028
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WHARLMPK | West Harlem Piers Park | 3 | CONSTRUCTION | Aug 2019 | Sep 2019 | Aug 2028 | Sep 2028
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WHARLMPK | West Harlem Piers Park | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Sep 2019 | Sep 2028 | Sep 2028
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WHARLMPK | West Harlem Piers Park | 5 | SUBSTANTIAL COMPLETION | Sep 2019 | Oct 2019 | Sep 2028 | Oct 2028
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WHARLMPK | West Harlem Piers Park | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2019 | Oct 2019 | Oct 2022 | Nov 2031
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WL34STHL | EAST 34TH STREET HELIPORT SUBSTRUCTURE | 1 | DESIGN | Jul 2020 | Jul 2020 | Jul 2020 | Jul 2020
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WL34STHL | EAST 34TH STREET HELIPORT SUBSTRUCTURE | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Aug 2020 | Jul 2020 | Aug 2020
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WL34STHL | EAST 34TH STREET HELIPORT SUBSTRUCTURE | 3 | CONSTRUCTION | Aug 2020 | Sep 2020 | Aug 2020 | Sep 2020
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WL34STHL | EAST 34TH STREET HELIPORT SUBSTRUCTURE | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Sep 2020 | Sep 2020 | Sep 2020
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WL34STHL | EAST 34TH STREET HELIPORT SUBSTRUCTURE | 5 | SUBSTANTIAL COMPLETION | Sep 2020 | Oct 2020 | Sep 2020 | Oct 2020
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WL34STHL | EAST 34TH STREET HELIPORT SUBSTRUCTURE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2020 | Oct 2020 | Oct 2020 | Jun 2026
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLWCLBWF | WATER CLUB WHARF | 1 | DESIGN | Jul 2020 | Jul 2020 | Jul 2020 | Jul 2020
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLWCLBWF | WATER CLUB WHARF | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Aug 2020 | Jul 2020 | Aug 2020
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLWCLBWF | WATER CLUB WHARF | 3 | CONSTRUCTION | Aug 2020 | Sep 2020 | Aug 2020 | Sep 2020
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLWCLBWF | WATER CLUB WHARF | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Sep 2020 | Sep 2020 | Sep 2020
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLWCLBWF | WATER CLUB WHARF | 5 | SUBSTANTIAL COMPLETION | Sep 2020 | Oct 2020 | Sep 2020 | Oct 2020
20231026 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLWCLBWF | WATER CLUB WHARF | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2020 | Oct 2020 | Oct 2020 | Jun 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM02USCC | (WHITE) UNION SETTLEMENT ASSOC. - COMM. CTR. RENOVATION | 1 | DESIGN | Jan 2007 | Jun 2007 | Jun 2016 | May 2017
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM02USCC | (WHITE) UNION SETTLEMENT ASSOC. - COMM. CTR. RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2007 | Nov 2007 | May 2017 | Feb 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM02USCC | (WHITE) UNION SETTLEMENT ASSOC. - COMM. CTR. RENOVATION | 3 | CONSTRUCTION | Nov 2007 | Nov 2008 | Feb 2018 | Nov 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM02USCC | (WHITE) UNION SETTLEMENT ASSOC. - COMM. CTR. RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2008 | May 2009 | Feb 2018 | Nov 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM02USCC | (WHITE) UNION SETTLEMENT ASSOC. - COMM. CTR. RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2008 | May 2009 | Nov 2021 | May 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM06MHEL | Manhattanville Houses Elevators | 1 | DESIGN | Jan 2007 | Jun 2007 | Jul 2007 | Dec 2007
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM06MHEL | Manhattanville Houses Elevators | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2007 | Nov 2007 | Dec 2007 | May 2008
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM06MHEL | Manhattanville Houses Elevators | 3 | CONSTRUCTION | Nov 2007 | Nov 2008 | May 2008 | May 2014
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM06MHEL | Manhattanville Houses Elevators | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2008 | May 2009 | May 2008 | May 2014
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM06MHEL | Manhattanville Houses Elevators | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2008 | May 2009 | May 2014 | Apr 2030
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM07CIDC | CITIZENS CARE DAY CARE - PLAYGROUND EQUIPMENT AND MATTING | 1 | DESIGN | Jan 2007 | Jun 2007 | Jan 2007 | Jun 2007
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM07CIDC | CITIZENS CARE DAY CARE - PLAYGROUND EQUIPMENT AND MATTING | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2007 | Nov 2007 | Jun 2007 | Nov 2007
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM07CIDC | CITIZENS CARE DAY CARE - PLAYGROUND EQUIPMENT AND MATTING | 3 | CONSTRUCTION | Nov 2007 | Nov 2008 | Nov 2007 | Nov 2008
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM07CIDC | CITIZENS CARE DAY CARE - PLAYGROUND EQUIPMENT AND MATTING | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2008 | May 2009 | Nov 2007 | Nov 2008
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM07CIDC | CITIZENS CARE DAY CARE - PLAYGROUND EQUIPMENT AND MATTING | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2008 | May 2009 | Nov 2008 | Nov 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM08HSST | HENRY STREET SETTLEMENT - GOOD COMPANIONS SR CTR RENOVATIONS | 1 | DESIGN | Jan 2011 | Jun 2011 | Mar 2011 | Dec 2017
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM08HSST | HENRY STREET SETTLEMENT - GOOD COMPANIONS SR CTR RENOVATIONS | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2011 | Nov 2011 | Dec 2017 | May 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM08HSST | HENRY STREET SETTLEMENT - GOOD COMPANIONS SR CTR RENOVATIONS | 3 | CONSTRUCTION | Nov 2011 | Nov 2012 | May 2018 | May 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM08HSST | HENRY STREET SETTLEMENT - GOOD COMPANIONS SR CTR RENOVATIONS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2012 | May 2013 | May 2018 | May 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM08HSST | HENRY STREET SETTLEMENT - GOOD COMPANIONS SR CTR RENOVATIONS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2012 | May 2013 | May 2019 | Apr 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM08RUHI | RUTGERS HOUSES ENERGY INITIATIVES | 1 | DESIGN | Mar 2008 | Aug 2008 | Mar 2008 | Aug 2008
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM08RUHI | RUTGERS HOUSES ENERGY INITIATIVES | 2 | BID AWARD AND REGISTER CONTRCT | Aug 2008 | Jan 2009 | Aug 2008 | Jan 2009
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM08RUHI | RUTGERS HOUSES ENERGY INITIATIVES | 3 | CONSTRUCTION | Jan 2009 | Jan 2010 | Jan 2009 | Jan 2010
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM08RUHI | RUTGERS HOUSES ENERGY INITIATIVES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2010 | Jul 2010 | Jan 2009 | Jan 2010
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM08RUHI | RUTGERS HOUSES ENERGY INITIATIVES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2010 | Jul 2010 | Jan 2010 | Jan 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13CLEV | CLINTON HOUSES ELEVATOR REHABILITATION | 1 | DESIGN | Jan 2013 | Jun 2013 | Sep 2012 | Dec 2013
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13CLEV | CLINTON HOUSES ELEVATOR REHABILITATION | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2013 | Nov 2013 | Dec 2013 | Jun 2014
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13CLEV | CLINTON HOUSES ELEVATOR REHABILITATION | 3 | CONSTRUCTION | Nov 2013 | Nov 2014 | Jun 2014 | Jul 2016
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13CLEV | CLINTON HOUSES ELEVATOR REHABILITATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2014 | May 2015 | Jun 2014 | Jul 2016
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13CLEV | CLINTON HOUSES ELEVATOR REHABILITATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2014 | May 2015 | Jul 2016 | Aug 2031
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15ICNB | STANLEY ISAACS UPGRADE OF SENIOR AND YOUTH CENTER COMP. UPGR | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Nov 2015 | Dec 2016 | Mar 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15ICNB | STANLEY ISAACS UPGRADE OF SENIOR AND YOUTH CENTER COMP. UPGR | 3 | CONSTRUCTION | Nov 2015 | Nov 2016 | Mar 2018 | Mar 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15ICNB | STANLEY ISAACS UPGRADE OF SENIOR AND YOUTH CENTER COMP. UPGR | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2016 | May 2017 | Mar 2018 | Mar 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15ICNB | STANLEY ISAACS UPGRADE OF SENIOR AND YOUTH CENTER COMP. UPGR | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2016 | May 2017 | Mar 2019 | Oct 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15JFSR | JEFFERSON SENIOR CENTER UPGRADE | 1 | DESIGN | Sep 2015 | Mar 2016 | Feb 2015 | Apr 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15JFSR | JEFFERSON SENIOR CENTER UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2016 | Jun 2016 | Apr 2018 | Jul 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15JFSR | JEFFERSON SENIOR CENTER UPGRADE | 3 | CONSTRUCTION | Jun 2016 | Jun 2017 | Jul 2018 | Jul 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15JFSR | JEFFERSON SENIOR CENTER UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2017 | Dec 2017 | Jul 2019 | May 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15MOGD | METRO NORTH PLAZA DAY CARE CENTER PLAYGROUND RENOVATION | 1 | DESIGN | Jan 2015 | Jun 2015 | Sep 2016 | May 2017
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15MOGD | METRO NORTH PLAZA DAY CARE CENTER PLAYGROUND RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Nov 2015 | Jun 2017 | Nov 2017
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15MOGD | METRO NORTH PLAZA DAY CARE CENTER PLAYGROUND RENOVATION | 3 | CONSTRUCTION | Nov 2015 | Nov 2016 | Nov 2017 | Nov 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15MOGD | METRO NORTH PLAZA DAY CARE CENTER PLAYGROUND RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2016 | May 2017 | Nov 2017 | Nov 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15MOGD | METRO NORTH PLAZA DAY CARE CENTER PLAYGROUND RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2016 | May 2017 | Nov 2018 | Nov 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15WSPL | WASHINGTON HOUSES DAY CARE CENTER PLAYGROUND UPGRADE | 1 | DESIGN | Jan 2015 | Jun 2015 | Aug 2015 | Apr 2017
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15WSPL | WASHINGTON HOUSES DAY CARE CENTER PLAYGROUND UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Nov 2015 | Apr 2017 | Dec 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15WSPL | WASHINGTON HOUSES DAY CARE CENTER PLAYGROUND UPGRADE | 3 | CONSTRUCTION | Nov 2015 | Nov 2016 | Dec 2018 | Sep 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15WSPL | WASHINGTON HOUSES DAY CARE CENTER PLAYGROUND UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2016 | May 2017 | Dec 2018 | Sep 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15WSPL | WASHINGTON HOUSES DAY CARE CENTER PLAYGROUND UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2016 | May 2017 | Sep 2019 | Apr 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16AMBL | AMSTERDAM HOUSES BARRELS PLAYGROUND RENO | 1 | DESIGN | Jan 2016 | Jul 2016 | Jan 2016 | Jul 2016
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16AMBL | AMSTERDAM HOUSES BARRELS PLAYGROUND RENO | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Nov 2016 | Jul 2016 | Nov 2016
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16AMBL | AMSTERDAM HOUSES BARRELS PLAYGROUND RENO | 3 | CONSTRUCTION | Nov 2016 | Nov 2017 | Nov 2016 | Nov 2017
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16AMBL | AMSTERDAM HOUSES BARRELS PLAYGROUND RENO | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | May 2018 | Nov 2016 | Nov 2017
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16AMBL | AMSTERDAM HOUSES BARRELS PLAYGROUND RENO | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | May 2018 | Nov 2017 | Apr 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16AMUP | AMSTERDAM HOUSES NYCHA-UPGRADES | 1 | DESIGN | Jan 2016 | Jul 2016 | Jan 2016 | Jul 2016
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16AMUP | AMSTERDAM HOUSES NYCHA-UPGRADES | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Nov 2016 | Jul 2016 | Nov 2016
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16AMUP | AMSTERDAM HOUSES NYCHA-UPGRADES | 3 | CONSTRUCTION | Nov 2016 | Nov 2017 | Nov 2016 | Nov 2017
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16AMUP | AMSTERDAM HOUSES NYCHA-UPGRADES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | May 2018 | Nov 2016 | Nov 2017
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16AMUP | AMSTERDAM HOUSES NYCHA-UPGRADES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | May 2018 | Nov 2017 | Nov 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CRCC | CORSI HOUSES UPGRADES TO LAGUARDIA COMMUNITY CENTER | 1 | DESIGN | Jan 2016 | Jul 2016 | Jan 2016 | Jul 2016
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CRCC | CORSI HOUSES UPGRADES TO LAGUARDIA COMMUNITY CENTER | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Nov 2016 | Jul 2016 | Nov 2016
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CRCC | CORSI HOUSES UPGRADES TO LAGUARDIA COMMUNITY CENTER | 3 | CONSTRUCTION | Nov 2016 | Nov 2017 | Nov 2016 | Nov 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CRCC | CORSI HOUSES UPGRADES TO LAGUARDIA COMMUNITY CENTER | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | May 2018 | Nov 2016 | Nov 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CRCC | CORSI HOUSES UPGRADES TO LAGUARDIA COMMUNITY CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | May 2018 | Nov 2018 | Nov 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16LGSC | 282 CHERRY STREET SECURITY CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | Aug 2016 | Jan 2017 | Aug 2016 | Aug 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16LGSC | 282 CHERRY STREET SECURITY CAMERAS | 3 | CONSTRUCTION | Jan 2017 | Jan 2018 | Aug 2019 | Aug 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16LGSC | 282 CHERRY STREET SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2018 | Jul 2018 | Aug 2019 | Aug 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16LGSC | 282 CHERRY STREET SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2018 | Jul 2018 | Aug 2020 | Sep 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16UPGI | UNDERGROUND WATER AND FIRE DISTRIBUTION PIPING | 1 | DESIGN | Mar 2017 | Aug 2017 | Mar 2017 | Aug 2017
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16UPGI | UNDERGROUND WATER AND FIRE DISTRIBUTION PIPING | 2 | BID AWARD AND REGISTER CONTRCT | Aug 2017 | Jan 2018 | Aug 2017 | Jan 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16UPGI | UNDERGROUND WATER AND FIRE DISTRIBUTION PIPING | 3 | CONSTRUCTION | Jan 2018 | Jan 2019 | Jan 2018 | Jan 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16UPGI | UNDERGROUND WATER AND FIRE DISTRIBUTION PIPING | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2019 | Jul 2019 | Jan 2018 | Jan 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16UPGI | UNDERGROUND WATER AND FIRE DISTRIBUTION PIPING | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2019 | Jul 2019 | Jan 2019 | Jan 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16WRSC | WISE REHAB 54 W. 94TH STREET SECURITY CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | Aug 2016 | Jan 2017 | Aug 2016 | Jan 2017
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16WRSC | WISE REHAB 54 W. 94TH STREET SECURITY CAMERAS | 3 | CONSTRUCTION | Jan 2017 | Jan 2018 | Jan 2017 | Jan 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16WRSC | WISE REHAB 54 W. 94TH STREET SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2018 | Jul 2018 | Jan 2017 | Jan 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16WRSC | WISE REHAB 54 W. 94TH STREET SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2018 | Jul 2018 | Jan 2018 | Jan 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17CRGR | CORSI HOUSES SITTING AREA FOR SENIORS | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17CRGR | CORSI HOUSES SITTING AREA FOR SENIORS | 3 | CONSTRUCTION | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17CRGR | CORSI HOUSES SITTING AREA FOR SENIORS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2018 | Jun 2019 | Dec 2017 | Dec 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17CRGR | CORSI HOUSES SITTING AREA FOR SENIORS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2018 | Jun 2019 | Dec 2018 | May 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17HRPL | HERNANDEZ PLAYGROUND RENOVATION AY 189 ALLEN STREET | 1 | DESIGN | Feb 2017 | Jul 2017 | Dec 2018 | Jun 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17HRPL | HERNANDEZ PLAYGROUND RENOVATION AY 189 ALLEN STREET | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Dec 2017 | Jun 2019 | Nov 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17HRPL | HERNANDEZ PLAYGROUND RENOVATION AY 189 ALLEN STREET | 3 | CONSTRUCTION | Dec 2017 | Dec 2018 | Nov 2019 | Nov 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17HRPL | HERNANDEZ PLAYGROUND RENOVATION AY 189 ALLEN STREET | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2018 | Jun 2019 | Nov 2019 | Nov 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17HRPL | HERNANDEZ PLAYGROUND RENOVATION AY 189 ALLEN STREET | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2018 | Jun 2019 | Nov 2020 | Feb 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17THUR | ROOF WORK AT THURGOOD MARSHALL HOUSES | 1 | DESIGN | Apr 2013 | Apr 2017 | Apr 2013 | Apr 2017
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17THUR | ROOF WORK AT THURGOOD MARSHALL HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | Apr 2017 | Sep 2017 | Apr 2017 | Sep 2017
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17THUR | ROOF WORK AT THURGOOD MARSHALL HOUSES | 3 | CONSTRUCTION | Sep 2017 | Sep 2018 | Sep 2017 | Sep 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17THUR | ROOF WORK AT THURGOOD MARSHALL HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2018 | Mar 2019 | Sep 2017 | Sep 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17THUR | ROOF WORK AT THURGOOD MARSHALL HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2018 | Mar 2019 | Sep 2018 | Sep 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17WGPA | WAGNER HOUSES PLAY AREA UPGRADE | 1 | DESIGN | Apr 2017 | Oct 2017 | Apr 2017 | Oct 2017
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17WGPA | WAGNER HOUSES PLAY AREA UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Oct 2017 | Feb 2018 | Oct 2017 | Feb 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17WGPA | WAGNER HOUSES PLAY AREA UPGRADE | 3 | CONSTRUCTION | Feb 2018 | Feb 2019 | Feb 2018 | Feb 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17WGPA | WAGNER HOUSES PLAY AREA UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2019 | Aug 2019 | Feb 2018 | Feb 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17WGPA | WAGNER HOUSES PLAY AREA UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2019 | Aug 2019 | Feb 2019 | Feb 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17WSCR | WSUR A Community Room Bathroom Installation | 1 | DESIGN | Feb 2017 | Jul 2017 | Feb 2017 | Jul 2017
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17WSCR | WSUR A Community Room Bathroom Installation | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17WSCR | WSUR A Community Room Bathroom Installation | 3 | CONSTRUCTION | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17WSCR | WSUR A Community Room Bathroom Installation | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2018 | Jun 2019 | Dec 2017 | Dec 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17WSCR | WSUR A Community Room Bathroom Installation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2018 | Jun 2019 | Dec 2018 | Dec 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18DIGV | DIGITAL VAN | 1 | DESIGN | Jun 2018 | Nov 2018 | Jun 2018 | Nov 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18DIGV | DIGITAL VAN | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2018 | May 2019 | Nov 2018 | May 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18DIGV | DIGITAL VAN | 3 | CONSTRUCTION | May 2019 | May 2020 | May 2019 | May 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18DIGV | DIGITAL VAN | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2020 | Nov 2020 | May 2019 | May 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18DIGV | DIGITAL VAN | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2020 | Nov 2020 | May 2020 | May 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18GOBR | GOMPERS BOILER REPAIR | 1 | DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18GOBR | GOMPERS BOILER REPAIR | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Sep 2018 | Mar 2018 | Sep 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18GOBR | GOMPERS BOILER REPAIR | 3 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18GOBR | GOMPERS BOILER REPAIR | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Mar 2020 | Sep 2018 | Sep 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18GOBR | GOMPERS BOILER REPAIR | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Mar 2020 | Sep 2019 | Sep 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18GRLM | GRANT HOUSES LAUNDROMAT RENOVATION | 1 | DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18GRLM | GRANT HOUSES LAUNDROMAT RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Sep 2018 | Mar 2018 | Sep 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18GRLM | GRANT HOUSES LAUNDROMAT RENOVATION | 3 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18GRLM | GRANT HOUSES LAUNDROMAT RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Mar 2020 | Sep 2018 | Sep 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18GRLM | GRANT HOUSES LAUNDROMAT RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Mar 2020 | Sep 2019 | Sep 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18JFBC | JEFFERSON HOUSES BASKETBALL COURT | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2018 | Mar 2019 | Sep 2018 | Mar 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18JFBC | JEFFERSON HOUSES BASKETBALL COURT | 3 | CONSTRUCTION | Mar 2019 | Mar 2020 | Mar 2019 | Mar 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18JFBC | JEFFERSON HOUSES BASKETBALL COURT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Sep 2020 | Mar 2019 | Mar 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18JFBC | JEFFERSON HOUSES BASKETBALL COURT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Sep 2020 | Mar 2020 | Sep 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18JOCC | JOHNSON COMM CTR. STANLEY ISACCS NBRHD CENTER UPGRADES | 1 | DESIGN | Mar 2018 | Aug 2018 | Mar 2018 | Aug 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18JOCC | JOHNSON COMM CTR. STANLEY ISACCS NBRHD CENTER UPGRADES | 2 | BID AWARD AND REGISTER CONTRCT | Aug 2018 | Feb 2019 | Aug 2018 | Feb 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18JOCC | JOHNSON COMM CTR. STANLEY ISACCS NBRHD CENTER UPGRADES | 3 | CONSTRUCTION | Feb 2019 | Feb 2020 | Feb 2019 | Feb 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18JOCC | JOHNSON COMM CTR. STANLEY ISACCS NBRHD CENTER UPGRADES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2020 | Aug 2020 | Feb 2019 | Feb 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18JOCC | JOHNSON COMM CTR. STANLEY ISACCS NBRHD CENTER UPGRADES | 6 | 1095 | Feb 2020 | Aug 2020 | Feb 2020 | Feb 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18LIPG | RENOVATION OF A PLAYGROUND AT LOWER EAST SIDE I INFILL | 1 | DESIGN | Mar 2018 | Aug 2018 | Mar 2018 | Aug 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18LIPG | RENOVATION OF A PLAYGROUND AT LOWER EAST SIDE I INFILL | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2018 | Feb 2019 | Sep 2018 | Feb 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18LIPG | RENOVATION OF A PLAYGROUND AT LOWER EAST SIDE I INFILL | 3 | CONSTRUCTION | Feb 2019 | Feb 2020 | Feb 2019 | Feb 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18LIPG | RENOVATION OF A PLAYGROUND AT LOWER EAST SIDE I INFILL | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2020 | Aug 2020 | Feb 2019 | Feb 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18LIPG | RENOVATION OF A PLAYGROUND AT LOWER EAST SIDE I INFILL | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2020 | Aug 2020 | Feb 2020 | Feb 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18URBF | URBAN FARMS | 1 | DESIGN | Jan 2018 | Jun 2018 | Jan 2018 | Jun 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18URBF | URBAN FARMS | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18URBF | URBAN FARMS | 3 | CONSTRUCTION | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18URBF | URBAN FARMS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2018 | Dec 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18URBF | URBAN FARMS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2019 | Dec 2025
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WAGD | WASHINGTON HOUSES MAKE PLAYGROUND ADA ACCESSIBLE | 1 | DESIGN | Mar 2018 | Sep 2018 | Mar 2018 | Sep 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WAGD | WASHINGTON HOUSES MAKE PLAYGROUND ADA ACCESSIBLE | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2018 | Mar 2019 | Sep 2018 | Mar 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WAGD | WASHINGTON HOUSES MAKE PLAYGROUND ADA ACCESSIBLE | 3 | CONSTRUCTION | Mar 2019 | Mar 2020 | Mar 2019 | Mar 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WAGD | WASHINGTON HOUSES MAKE PLAYGROUND ADA ACCESSIBLE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Sep 2020 | Mar 2019 | Mar 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WAGD | WASHINGTON HOUSES MAKE PLAYGROUND ADA ACCESSIBLE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Sep 2020 | Mar 2020 | Mar 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19AMEL | AMSTERDAM HOUSES ELEVATOR UPGRADE | 1 | DESIGN | Jun 2019 | Dec 2020 | Jun 2019 | Dec 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19AMEL | AMSTERDAM HOUSES ELEVATOR UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19AMEL | AMSTERDAM HOUSES ELEVATOR UPGRADE | 3 | CONSTRUCTION | Jul 2021 | Jan 2023 | Jul 2021 | Jan 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19AMEL | AMSTERDAM HOUSES ELEVATOR UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2023 | Apr 2023 | Jul 2021 | Jan 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19AMEL | AMSTERDAM HOUSES ELEVATOR UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2023 | Apr 2023 | Jan 2023 | Apr 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DCCR | DYCKMAN HOUSES COMMUNITY CENTER RAMP | 1 | DESIGN | Feb 2019 | Aug 2019 | Feb 2019 | Aug 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DCCR | DYCKMAN HOUSES COMMUNITY CENTER RAMP | 2 | BID AWARD AND REGISTER CONTRCT | Aug 2019 | Feb 2020 | Aug 2019 | Feb 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DCCR | DYCKMAN HOUSES COMMUNITY CENTER RAMP | 3 | CONSTRUCTION | Feb 2020 | Feb 2021 | Feb 2020 | Feb 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DCCR | DYCKMAN HOUSES COMMUNITY CENTER RAMP | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Aug 2021 | Feb 2020 | Feb 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DCCR | DYCKMAN HOUSES COMMUNITY CENTER RAMP | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Aug 2021 | Feb 2021 | Aug 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DHPR | DYCKMAN HOUSES PLAYGROUND RENOVATION | 1 | DESIGN | Feb 2019 | Aug 2019 | Feb 2019 | Aug 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DHPR | DYCKMAN HOUSES PLAYGROUND RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | Aug 2019 | Feb 2020 | Aug 2019 | Feb 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DHPR | DYCKMAN HOUSES PLAYGROUND RENOVATION | 3 | CONSTRUCTION | Feb 2020 | Feb 2021 | Feb 2020 | Feb 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DHPR | DYCKMAN HOUSES PLAYGROUND RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Aug 2021 | Feb 2020 | Feb 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DHPR | DYCKMAN HOUSES PLAYGROUND RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Aug 2021 | Feb 2021 | Aug 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19GHEL | GRANT HOUSES EXTERNAL LIGHTING UPGRADES | 1 | DESIGN | Jan 2019 | Jul 2019 | Jan 2019 | Jul 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19GHEL | GRANT HOUSES EXTERNAL LIGHTING UPGRADES | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Jan 2020 | Jul 2019 | Jan 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19GHEL | GRANT HOUSES EXTERNAL LIGHTING UPGRADES | 3 | CONSTRUCTION | Jan 2020 | Jan 2021 | Jan 2020 | Jan 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19GHEL | GRANT HOUSES EXTERNAL LIGHTING UPGRADES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2021 | Jul 2021 | Jan 2020 | Jan 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19GHEL | GRANT HOUSES EXTERNAL LIGHTING UPGRADES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19HBBR | HARBORVIEW COMMUNITY/SENIOR CENTER BATHROOM RENOVATIONS | 1 | DESIGN | Jan 2018 | Jun 2018 | Jan 2018 | Jun 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19HBBR | HARBORVIEW COMMUNITY/SENIOR CENTER BATHROOM RENOVATIONS | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19HBBR | HARBORVIEW COMMUNITY/SENIOR CENTER BATHROOM RENOVATIONS | 3 | CONSTRUCTION | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19HBBR | HARBORVIEW COMMUNITY/SENIOR CENTER BATHROOM RENOVATIONS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2018 | Dec 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19HBBR | HARBORVIEW COMMUNITY/SENIOR CENTER BATHROOM RENOVATIONS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2019 | Dec 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19RCCK | RUTGERS COMMUNITY CENTER KITCHEN RENOVATION | 1 | DESIGN | Jan 2018 | Jun 2018 | Jan 2018 | Jun 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19RCCK | RUTGERS COMMUNITY CENTER KITCHEN RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19RCCK | RUTGERS COMMUNITY CENTER KITCHEN RENOVATION | 3 | CONSTRUCTION | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19RCCK | RUTGERS COMMUNITY CENTER KITCHEN RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2018 | Dec 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19RCCK | RUTGERS COMMUNITY CENTER KITCHEN RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2019 | Dec 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19STEL | ST NICHOLAS HOUSES ELEVATOR UPGRADE | 1 | DESIGN | Jun 2019 | Dec 2019 | Jun 2019 | Dec 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19STEL | ST NICHOLAS HOUSES ELEVATOR UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2020 | Jun 2022 | Jan 2020 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19STEL | ST NICHOLAS HOUSES ELEVATOR UPGRADE | 3 | CONSTRUCTION | Jul 2022 | Jan 2024 | Jul 2022 | Jan 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19STEL | ST NICHOLAS HOUSES ELEVATOR UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2024 | Apr 2024 | Jul 2022 | Jan 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19STEL | ST NICHOLAS HOUSES ELEVATOR UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2024 | Apr 2024 | Jan 2024 | Apr 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHNE | BARUCH HOUSES NEW ELEVATOR | 1 | DESIGN | Jan 2018 | Jun 2018 | Jan 2018 | Jun 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHNE | BARUCH HOUSES NEW ELEVATOR | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHNE | BARUCH HOUSES NEW ELEVATOR | 3 | CONSTRUCTION | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHNE | BARUCH HOUSES NEW ELEVATOR | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2018 | Dec 2019
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHNE | BARUCH HOUSES NEW ELEVATOR | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2019 | Dec 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CHHT | HEATING UPGRADES- CHELSEA HOUSES | 1 | DESIGN | Sep 2019 | Feb 2020 | Sep 2019 | Feb 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CHHT | HEATING UPGRADES- CHELSEA HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Aug 2020 | Feb 2020 | Aug 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CHHT | HEATING UPGRADES- CHELSEA HOUSES | 3 | CONSTRUCTION | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CHHT | HEATING UPGRADES- CHELSEA HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2020 | Aug 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CHHT | HEATING UPGRADES- CHELSEA HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2021 | Feb 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CSKR | CARVER HOUSES KITCHEN RENOVATION IN SENIOR CENTER | 1 | DESIGN | Sep 2019 | Feb 2020 | Sep 2019 | Feb 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CSKR | CARVER HOUSES KITCHEN RENOVATION IN SENIOR CENTER | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Aug 2020 | Feb 2020 | Aug 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CSKR | CARVER HOUSES KITCHEN RENOVATION IN SENIOR CENTER | 3 | CONSTRUCTION | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CSKR | CARVER HOUSES KITCHEN RENOVATION IN SENIOR CENTER | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2020 | Aug 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CSKR | CARVER HOUSES KITCHEN RENOVATION IN SENIOR CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2021 | Feb 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 1 | DESIGN | Sep 2020 | Feb 2021 | Jun 2027 | Nov 2027
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2021 | Aug 2021 | Nov 2027 | May 2028
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 3 | CONSTRUCTION | Aug 2021 | Aug 2022 | May 2028 | May 2029
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2022 | Feb 2023 | May 2028 | May 2029
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 5 | DEVELOP SCOPE | Feb 2023 | May 2023 | May 2028 | May 2029
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 6 | PRELIMINARY DESIGN | May 2023 | Sep 2023 | May 2029 | Nov 2029
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 7 | FINAL DESIGN | Sep 2023 | Mar 2024 | Nov 2029 | Feb 2030
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 8 | BID AWARD AND REGISTER CONTRCT | Mar 2024 | Jun 2024 | Feb 2030 | Jun 2030
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 9 | CONSTRUCTION TO 25% | Jun 2024 | Oct 2024 | Jun 2030 | Jun 2034
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 10 | CONSTRUCTION TO 50% | Oct 2024 | Feb 2025 | Jun 2034 | Sep 2034
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 11 | CONSTRUCTION TO 75% | Feb 2025 | Jun 2025 | Sep 2034 | Jan 2035
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 12 | ORIGINAL EQUIP & FURNISHING | Jun 2025 | Sep 2025 | Jan 2035 | May 2035
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 13 | SUBSTANTIAL COMPLETION | Sep 2025 | Nov 2025 | May 2035 | Sep 2035
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 14 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2025 | Dec 2025 | Sep 2035 | Dec 2035
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 15 | SUBSTANTIAL COMPLETION | Nov 2025 | Dec 2025 | Dec 2035 | Feb 2036
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | 16 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2025 | Dec 2025 | Feb 2036 | Mar 2036
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ELHU | HEATING UPGRADES- ELLIOTT HOUSES | 1 | DESIGN | Sep 2019 | Feb 2020 | Sep 2019 | Feb 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ELHU | HEATING UPGRADES- ELLIOTT HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Aug 2020 | Feb 2020 | Aug 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ELHU | HEATING UPGRADES- ELLIOTT HOUSES | 3 | CONSTRUCTION | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ELHU | HEATING UPGRADES- ELLIOTT HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2020 | Aug 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ELHU | HEATING UPGRADES- ELLIOTT HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2021 | Feb 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20FSHL | FULTON HOUSES STAIRWAY AND HALL LIGHTING | 1 | DESIGN | Sep 2019 | Feb 2020 | Sep 2019 | Feb 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20FSHL | FULTON HOUSES STAIRWAY AND HALL LIGHTING | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Aug 2020 | Feb 2020 | Aug 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20FSHL | FULTON HOUSES STAIRWAY AND HALL LIGHTING | 3 | CONSTRUCTION | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20FSHL | FULTON HOUSES STAIRWAY AND HALL LIGHTING | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2020 | Aug 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20FSHL | FULTON HOUSES STAIRWAY AND HALL LIGHTING | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2021 | Feb 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20FUHU | FULTON HOUSES HEATING UPGRADES | 1 | DESIGN | Sep 2019 | Feb 2020 | Sep 2019 | Feb 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20FUHU | FULTON HOUSES HEATING UPGRADES | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Aug 2020 | Feb 2020 | Aug 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20FUHU | FULTON HOUSES HEATING UPGRADES | 3 | CONSTRUCTION | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20FUHU | FULTON HOUSES HEATING UPGRADES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2020 | Aug 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20FUHU | FULTON HOUSES HEATING UPGRADES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2021 | Feb 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GHCL | GRANT - LAUNDROMART CONSTRUCTION | 1 | DESIGN | Sep 2019 | Feb 2020 | Sep 2019 | Feb 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GHCL | GRANT - LAUNDROMART CONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Aug 2020 | Feb 2020 | Aug 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GHCL | GRANT - LAUNDROMART CONSTRUCTION | 3 | CONSTRUCTION | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GHCL | GRANT - LAUNDROMART CONSTRUCTION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2020 | Aug 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GHCL | GRANT - LAUNDROMART CONSTRUCTION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2021 | Feb 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JFPG | JEFFERSON HOUSES PLAYGROUND RENOVATION | 1 | DEVELOP SCOPE | Sep 2020 | Nov 2020 | Sep 2020 | Nov 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JFPG | JEFFERSON HOUSES PLAYGROUND RENOVATION | 2 | PRELIMINARY DESIGN | Nov 2020 | Mar 2021 | Nov 2020 | Mar 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JFPG | JEFFERSON HOUSES PLAYGROUND RENOVATION | 3 | FINAL DESIGN | Mar 2021 | Sep 2021 | Mar 2021 | Sep 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JFPG | JEFFERSON HOUSES PLAYGROUND RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2021 | Dec 2021 | Sep 2021 | Dec 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JFPG | JEFFERSON HOUSES PLAYGROUND RENOVATION | 5 | CONSTRUCTION TO 25% | Dec 2021 | Apr 2022 | Dec 2021 | Dec 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JFPG | JEFFERSON HOUSES PLAYGROUND RENOVATION | 6 | CONSTRUCTION TO 50% | Apr 2022 | Aug 2022 | Dec 2023 | Apr 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JFPG | JEFFERSON HOUSES PLAYGROUND RENOVATION | 7 | CONSTRUCTION TO 75% | Aug 2022 | Dec 2022 | Apr 2024 | Apr 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JFPG | JEFFERSON HOUSES PLAYGROUND RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2022 | Mar 2023 | Apr 2026 | Jul 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JFPG | JEFFERSON HOUSES PLAYGROUND RENOVATION | 9 | SUBSTANTIAL COMPLETION | Mar 2023 | May 2023 | Jul 2026 | Sep 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JFPG | JEFFERSON HOUSES PLAYGROUND RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2023 | Jun 2023 | Sep 2026 | Oct 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LESD | LES INFILL 1 NEW LAYERED ACCESS DOORS | 1 | DEVELOP SCOPE | Sep 2020 | Nov 2020 | Sep 2020 | Nov 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LESD | LES INFILL 1 NEW LAYERED ACCESS DOORS | 2 | PRELIMINARY DESIGN | Nov 2020 | Mar 2021 | Nov 2020 | Mar 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LESD | LES INFILL 1 NEW LAYERED ACCESS DOORS | 3 | FINAL DESIGN | Mar 2021 | Sep 2021 | Mar 2021 | Sep 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LESD | LES INFILL 1 NEW LAYERED ACCESS DOORS | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2021 | Dec 2021 | Sep 2021 | Dec 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LESD | LES INFILL 1 NEW LAYERED ACCESS DOORS | 5 | CONSTRUCTION TO 25% | Dec 2021 | Apr 2022 | Dec 2021 | Apr 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LESD | LES INFILL 1 NEW LAYERED ACCESS DOORS | 6 | CONSTRUCTION TO 50% | Apr 2022 | Aug 2022 | Apr 2022 | Aug 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LESD | LES INFILL 1 NEW LAYERED ACCESS DOORS | 7 | CONSTRUCTION TO 75% | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LESD | LES INFILL 1 NEW LAYERED ACCESS DOORS | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2022 | Mar 2023 | Dec 2022 | Mar 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LESD | LES INFILL 1 NEW LAYERED ACCESS DOORS | 9 | SUBSTANTIAL COMPLETION | Mar 2023 | May 2023 | Mar 2023 | May 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LESD | LES INFILL 1 NEW LAYERED ACCESS DOORS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2023 | Jun 2023 | May 2023 | Jun 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SGCU | STRAUS HOUSES GARBAGE COMPACTOR | 1 | DESIGN | Sep 2019 | Feb 2020 | Sep 2019 | Feb 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SGCU | STRAUS HOUSES GARBAGE COMPACTOR | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Aug 2020 | Feb 2020 | Aug 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SGCU | STRAUS HOUSES GARBAGE COMPACTOR | 3 | CONSTRUCTION | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SGCU | STRAUS HOUSES GARBAGE COMPACTOR | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2020 | Aug 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SGCU | STRAUS HOUSES GARBAGE COMPACTOR | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2021 | Aug 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SHDR | ALFRED SMITH -DOG RUN FOR 10 CATHERINE SLIP | 1 | DESIGN | Sep 2019 | Feb 2020 | Sep 2019 | Feb 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SHDR | ALFRED SMITH -DOG RUN FOR 10 CATHERINE SLIP | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Aug 2020 | Feb 2020 | Aug 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SHDR | ALFRED SMITH -DOG RUN FOR 10 CATHERINE SLIP | 3 | CONSTRUCTION | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SHDR | ALFRED SMITH -DOG RUN FOR 10 CATHERINE SLIP | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2020 | Aug 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SHDR | ALFRED SMITH -DOG RUN FOR 10 CATHERINE SLIP | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2021 | Aug 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SISC | STANLEY ISAACS SENIOR CENTER BATHROOM ADA UPGRADE | 1 | DESIGN | Dec 2013 | Dec 2017 | Dec 2013 | Dec 2017
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SISC | STANLEY ISAACS SENIOR CENTER BATHROOM ADA UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2017 | Jun 2017 | Jan 2017 | Jun 2017
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SISC | STANLEY ISAACS SENIOR CENTER BATHROOM ADA UPGRADE | 3 | CONSTRUCTION | Jun 2017 | Jun 2018 | Jun 2017 | Jun 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SISC | STANLEY ISAACS SENIOR CENTER BATHROOM ADA UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2018 | Dec 2019 | Jun 2017 | Jun 2018
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SISC | STANLEY ISAACS SENIOR CENTER BATHROOM ADA UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2018 | Dec 2019 | Jul 2018 | Jul 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SPER | SEWARD PARK EXTENSION RENOVATIONS | 1 | DESIGN | Sep 2019 | Feb 2020 | Sep 2019 | Feb 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SPER | SEWARD PARK EXTENSION RENOVATIONS | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Aug 2020 | Feb 2020 | Aug 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SPER | SEWARD PARK EXTENSION RENOVATIONS | 3 | CONSTRUCTION | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SPER | SEWARD PARK EXTENSION RENOVATIONS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2020 | Aug 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SPER | SEWARD PARK EXTENSION RENOVATIONS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2021 | Feb 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20TUSD | TAFT UNDERGROUND STEAM DISTRIBUTION | 1 | DESIGN | Sep 2020 | Feb 2021 | Sep 2020 | Feb 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20TUSD | TAFT UNDERGROUND STEAM DISTRIBUTION | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2021 | Aug 2021 | Feb 2021 | Aug 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20TUSD | TAFT UNDERGROUND STEAM DISTRIBUTION | 3 | CONSTRUCTION | Aug 2021 | Aug 2022 | Aug 2021 | Aug 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20TUSD | TAFT UNDERGROUND STEAM DISTRIBUTION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2022 | Feb 2023 | Aug 2021 | Aug 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20TUSD | TAFT UNDERGROUND STEAM DISTRIBUTION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2022 | Feb 2023 | Aug 2022 | Aug 2025
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WSLP | WOODSON LIGHT POLES | 1 | DESIGN | Jun 2019 | Dec 2019 | Jan 2025 | Jun 2025
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WSLP | WOODSON LIGHT POLES | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2019 | Jun 2020 | Jun 2025 | Dec 2025
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WSLP | WOODSON LIGHT POLES | 3 | CONSTRUCTION | Jun 2020 | Jun 2021 | Dec 2025 | Dec 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WSLP | WOODSON LIGHT POLES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2021 | Dec 2021 | Dec 2025 | Dec 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WSLP | WOODSON LIGHT POLES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2021 | Dec 2021 | Dec 2026 | Jun 2027
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21CHIC | INTERIOR COMPACTOR AT CHELSEA HOUSES | 1 | DESIGN | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21CHIC | INTERIOR COMPACTOR AT CHELSEA HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21CHIC | INTERIOR COMPACTOR AT CHELSEA HOUSES | 3 | CONSTRUCTION | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21CHIC | INTERIOR COMPACTOR AT CHELSEA HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21CHIC | INTERIOR COMPACTOR AT CHELSEA HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21CHRE | RENOVATIONS FOR CHELSEA HOUSES | 1 | DESIGN | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21CHRE | RENOVATIONS FOR CHELSEA HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21CHRE | RENOVATIONS FOR CHELSEA HOUSES | 3 | CONSTRUCTION | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21CHRE | RENOVATIONS FOR CHELSEA HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21CHRE | RENOVATIONS FOR CHELSEA HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21DYEL | DYCKMAN HOUSES ELEVATOR REPLACEMENT | 1 | DESIGN | Jun 2021 | Nov 2021 | Jun 2019 | Jun 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21DYEL | DYCKMAN HOUSES ELEVATOR REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2021 | Apr 2022 | Jun 2020 | Nov 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21DYEL | DYCKMAN HOUSES ELEVATOR REPLACEMENT | 3 | CONSTRUCTION | Apr 2022 | Apr 2023 | Nov 2020 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21DYEL | DYCKMAN HOUSES ELEVATOR REPLACEMENT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2023 | Oct 2023 | Nov 2020 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21DYEL | DYCKMAN HOUSES ELEVATOR REPLACEMENT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2023 | Oct 2023 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21EHRE | RENOVATIONS AT ELLIOT HOUSES | 1 | DESIGN | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21EHRE | RENOVATIONS AT ELLIOT HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21EHRE | RENOVATIONS AT ELLIOT HOUSES | 3 | CONSTRUCTION | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21EHRE | RENOVATIONS AT ELLIOT HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21EHRE | RENOVATIONS AT ELLIOT HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21FHEC | EXTERIOR COMPACTOR AT FULTON HOUSES | 1 | DESIGN | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21FHEC | EXTERIOR COMPACTOR AT FULTON HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21FHEC | EXTERIOR COMPACTOR AT FULTON HOUSES | 3 | CONSTRUCTION | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21FHEC | EXTERIOR COMPACTOR AT FULTON HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21FHEC | EXTERIOR COMPACTOR AT FULTON HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21GHPS | REPAIR PAVEMENT AT GRANT HOUSES | 1 | DESIGN | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21GHPS | REPAIR PAVEMENT AT GRANT HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21GHPS | REPAIR PAVEMENT AT GRANT HOUSES | 3 | CONSTRUCTION | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21GHPS | REPAIR PAVEMENT AT GRANT HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21GHPS | REPAIR PAVEMENT AT GRANT HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21JHPR | PLAYGROUND RENOVATION AT JOHNSON HOUSES | 1 | DESIGN | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21JHPR | PLAYGROUND RENOVATION AT JOHNSON HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21JHPR | PLAYGROUND RENOVATION AT JOHNSON HOUSES | 3 | CONSTRUCTION | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21JHPR | PLAYGROUND RENOVATION AT JOHNSON HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21JHPR | PLAYGROUND RENOVATION AT JOHNSON HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21JUPG | JEFFERSON HOUSES UNION SETTLEMENT PLAYGROUND UPGRADE | 1 | DESIGN | May 2022 | Nov 2022 | May 2022 | Nov 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21JUPG | JEFFERSON HOUSES UNION SETTLEMENT PLAYGROUND UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2022 | May 2023 | Nov 2022 | May 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21JUPG | JEFFERSON HOUSES UNION SETTLEMENT PLAYGROUND UPGRADE | 3 | CONSTRUCTION | May 2023 | May 2024 | May 2023 | May 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21JUPG | JEFFERSON HOUSES UNION SETTLEMENT PLAYGROUND UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2023 | May 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21JUPG | JEFFERSON HOUSES UNION SETTLEMENT PLAYGROUND UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21LMPG | LEGGET MEMORIAL PLAYGROUND UPGRADE GAYLORD WHITE HOUSES | 1 | DESIGN | May 2022 | Nov 2022 | May 2022 | Nov 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21LMPG | LEGGET MEMORIAL PLAYGROUND UPGRADE GAYLORD WHITE HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2022 | May 2023 | Nov 2022 | May 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21LMPG | LEGGET MEMORIAL PLAYGROUND UPGRADE GAYLORD WHITE HOUSES | 3 | CONSTRUCTION | May 2023 | May 2024 | May 2023 | May 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21LMPG | LEGGET MEMORIAL PLAYGROUND UPGRADE GAYLORD WHITE HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2023 | May 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21LMPG | LEGGET MEMORIAL PLAYGROUND UPGRADE GAYLORD WHITE HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21LSCB | LINCOLN HOUSES SENIOR CENTER ADA BATHROOMS | 1 | DESIGN | May 2022 | Nov 2022 | May 2022 | Nov 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21LSCB | LINCOLN HOUSES SENIOR CENTER ADA BATHROOMS | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2022 | May 2023 | Nov 2022 | May 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21LSCB | LINCOLN HOUSES SENIOR CENTER ADA BATHROOMS | 3 | CONSTRUCTION | May 2023 | May 2024 | May 2023 | May 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21LSCB | LINCOLN HOUSES SENIOR CENTER ADA BATHROOMS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2023 | May 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21LSCB | LINCOLN HOUSES SENIOR CENTER ADA BATHROOMS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHEL | MELTZER HERNANDEZ HOUSES ELEVATOR REPLACEMENT | 1 | DESIGN | Jun 2021 | Nov 2021 | Dec 2019 | Dec 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHEL | MELTZER HERNANDEZ HOUSES ELEVATOR REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2021 | Apr 2022 | Dec 2020 | May 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHEL | MELTZER HERNANDEZ HOUSES ELEVATOR REPLACEMENT | 3 | CONSTRUCTION | Apr 2022 | Apr 2023 | May 2021 | Nov 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHEL | MELTZER HERNANDEZ HOUSES ELEVATOR REPLACEMENT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2023 | Oct 2023 | May 2021 | Nov 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHEL | MELTZER HERNANDEZ HOUSES ELEVATOR REPLACEMENT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2023 | Oct 2023 | Nov 2022 | Feb 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21RCCK | CC KITCHEN RENOVATION AT RUTGERS HOUSES | 1 | DESIGN | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21RCCK | CC KITCHEN RENOVATION AT RUTGERS HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21RCCK | CC KITCHEN RENOVATION AT RUTGERS HOUSES | 3 | CONSTRUCTION | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21RCCK | CC KITCHEN RENOVATION AT RUTGERS HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21RCCK | CC KITCHEN RENOVATION AT RUTGERS HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SWTI | STEPHEN WISE TOWERS NYCHA - INFRASTRUCTURE- | 1 | DESIGN | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SWTI | STEPHEN WISE TOWERS NYCHA - INFRASTRUCTURE- | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SWTI | STEPHEN WISE TOWERS NYCHA - INFRASTRUCTURE- | 3 | CONSTRUCTION | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SWTI | STEPHEN WISE TOWERS NYCHA - INFRASTRUCTURE- | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SWTI | STEPHEN WISE TOWERS NYCHA - INFRASTRUCTURE- | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21TABC | TAFT HOUSES BASKETBALL COURT | 1 | DESIGN | Sep 2021 | Mar 2022 | Sep 2021 | Mar 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21TABC | TAFT HOUSES BASKETBALL COURT | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2022 | Sep 2022 | Mar 2022 | Sep 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21TABC | TAFT HOUSES BASKETBALL COURT | 3 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21TABC | TAFT HOUSES BASKETBALL COURT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Mar 2024 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21TABC | TAFT HOUSES BASKETBALL COURT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Mar 2024 | Sep 2023 | Mar 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21THCR | COMPACTOR REPLACEMENT AT TAFT HOUSES | 1 | DESIGN | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21THCR | COMPACTOR REPLACEMENT AT TAFT HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21THCR | COMPACTOR REPLACEMENT AT TAFT HOUSES | 3 | CONSTRUCTION | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21THCR | COMPACTOR REPLACEMENT AT TAFT HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21THCR | COMPACTOR REPLACEMENT AT TAFT HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21USPR | JOHNSON- UNION SETTLEMENT PLAYGROUND RENO | 1 | DESIGN | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21USPR | JOHNSON- UNION SETTLEMENT PLAYGROUND RENO | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21USPR | JOHNSON- UNION SETTLEMENT PLAYGROUND RENO | 3 | CONSTRUCTION | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21USPR | JOHNSON- UNION SETTLEMENT PLAYGROUND RENO | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21USPR | JOHNSON- UNION SETTLEMENT PLAYGROUND RENO | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21WHBC | NYCHA WAGNER HOUSES-BASKETBALL COURT RENOVATIONS | 1 | DESIGN | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21WHBC | NYCHA WAGNER HOUSES-BASKETBALL COURT RENOVATIONS | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21WHBC | NYCHA WAGNER HOUSES-BASKETBALL COURT RENOVATIONS | 3 | CONSTRUCTION | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21WHBC | NYCHA WAGNER HOUSES-BASKETBALL COURT RENOVATIONS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21WHBC | NYCHA WAGNER HOUSES-BASKETBALL COURT RENOVATIONS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21WHCC | WAGNER HOUSES- COMMUNITY CENTER | 1 | DESIGN | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21WHCC | WAGNER HOUSES- COMMUNITY CENTER | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21WHCC | WAGNER HOUSES- COMMUNITY CENTER | 3 | CONSTRUCTION | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21WHCC | WAGNER HOUSES- COMMUNITY CENTER | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21WHCC | WAGNER HOUSES- COMMUNITY CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21WSUG | GARBAGE ENCLOSURES AT WSUR BROWNSTONES | 1 | DESIGN | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21WSUG | GARBAGE ENCLOSURES AT WSUR BROWNSTONES | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21WSUG | GARBAGE ENCLOSURES AT WSUR BROWNSTONES | 3 | CONSTRUCTION | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21WSUG | GARBAGE ENCLOSURES AT WSUR BROWNSTONES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21WSUG | GARBAGE ENCLOSURES AT WSUR BROWNSTONES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22ASEL | SMITH HOUSES- ADA UPGRADES AND EXISTING LEAKS | 1 | DESIGN | Jan 2022 | Jun 2022 | Jan 2022 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22ASEL | SMITH HOUSES- ADA UPGRADES AND EXISTING LEAKS | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22ASEL | SMITH HOUSES- ADA UPGRADES AND EXISTING LEAKS | 3 | CONSTRUCTION | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22ASEL | SMITH HOUSES- ADA UPGRADES AND EXISTING LEAKS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jun 2024 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22ASEL | SMITH HOUSES- ADA UPGRADES AND EXISTING LEAKS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22CTDR | CLINTON AVENUE- TERRACE DOOR REPLACEMENT | 1 | DESIGN | Jan 2022 | Jun 2022 | Jan 2022 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22CTDR | CLINTON AVENUE- TERRACE DOOR REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22CTDR | CLINTON AVENUE- TERRACE DOOR REPLACEMENT | 3 | CONSTRUCTION | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22CTDR | CLINTON AVENUE- TERRACE DOOR REPLACEMENT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jun 2024 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22CTDR | CLINTON AVENUE- TERRACE DOOR REPLACEMENT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22DCAM | DYCKMAN HOUSES- TECHNONOLGY UPGRADE | 3 | CONSTRUCTION | May 2023 | May 2024 | May 2023 | May 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22DCAM | DYCKMAN HOUSES- TECHNONOLGY UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2023 | May 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22DCAM | DYCKMAN HOUSES- TECHNONOLGY UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22MEBC | SMITH-HAMILTON MADISON HOUSE- ELEVATORS & ADA BATHRM SNR CTR | 1 | DESIGN | Jan 2022 | Jun 2022 | Jan 2022 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22MEBC | SMITH-HAMILTON MADISON HOUSE- ELEVATORS & ADA BATHRM SNR CTR | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22MEBC | SMITH-HAMILTON MADISON HOUSE- ELEVATORS & ADA BATHRM SNR CTR | 3 | CONSTRUCTION | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22MEBC | SMITH-HAMILTON MADISON HOUSE- ELEVATORS & ADA BATHRM SNR CTR | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jun 2024 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22MEBC | SMITH-HAMILTON MADISON HOUSE- ELEVATORS & ADA BATHRM SNR CTR | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SLAD | STRAUS HOUSES- LAYERED ACCESS | 1 | DESIGN | May 2022 | Nov 2022 | May 2022 | Nov 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SLAD | STRAUS HOUSES- LAYERED ACCESS | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2022 | May 2023 | Nov 2022 | May 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SLAD | STRAUS HOUSES- LAYERED ACCESS | 3 | CONSTRUCTION | May 2023 | May 2024 | May 2023 | May 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SLAD | STRAUS HOUSES- LAYERED ACCESS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2023 | May 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SLAD | STRAUS HOUSES- LAYERED ACCESS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SMGR | SMITH HOUSES INSTALLATION OF GAS RISERS #7 | 1 | DESIGN | Jun 2022 | Dec 2023 | Jun 2022 | Dec 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SMGR | SMITH HOUSES INSTALLATION OF GAS RISERS #7 | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SMGR | SMITH HOUSES INSTALLATION OF GAS RISERS #7 | 3 | CONSTRUCTION | Jul 2024 | Jan 2026 | Jul 2024 | Jan 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SMGR | SMITH HOUSES INSTALLATION OF GAS RISERS #7 | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2026 | Apr 2026 | Jul 2024 | Jan 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SMGR | SMITH HOUSES INSTALLATION OF GAS RISERS #7 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2026 | Apr 2026 | Jan 2026 | Apr 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SPDS | SEWARD PARK EXT- DOORS & SECURITY UPGRADE | 1 | DESIGN | May 2022 | Nov 2022 | May 2022 | Nov 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SPDS | SEWARD PARK EXT- DOORS & SECURITY UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2022 | May 2023 | Nov 2022 | May 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SPDS | SEWARD PARK EXT- DOORS & SECURITY UPGRADE | 3 | CONSTRUCTION | May 2023 | May 2024 | May 2023 | May 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SPDS | SEWARD PARK EXT- DOORS & SECURITY UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2023 | May 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SPDS | SEWARD PARK EXT- DOORS & SECURITY UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22TAEL | TAFT HOUSES ELEVATOR REHABILITATION | 1 | DESIGN | Jun 2022 | Jun 2023 | Jun 2022 | Jun 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22TAEL | TAFT HOUSES ELEVATOR REHABILITATION | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Nov 2023 | Jul 2023 | Nov 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22TAEL | TAFT HOUSES ELEVATOR REHABILITATION | 3 | CONSTRUCTION | Nov 2023 | Jun 2025 | Nov 2023 | Jun 2025
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22TAEL | TAFT HOUSES ELEVATOR REHABILITATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2025 | Sep 2025 | Nov 2023 | Jun 2025
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22TAEL | TAFT HOUSES ELEVATOR REHABILITATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2025 | Sep 2025 | Jun 2025 | Jun 2029
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22USLJ | UNION SETTLEMENT- PLAY AREA AT JEFFERSON | 1 | DESIGN | Jan 2022 | Jun 2022 | Jan 2022 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22USLJ | UNION SETTLEMENT- PLAY AREA AT JEFFERSON | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22USLJ | UNION SETTLEMENT- PLAY AREA AT JEFFERSON | 3 | CONSTRUCTION | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22USLJ | UNION SETTLEMENT- PLAY AREA AT JEFFERSON | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jun 2024 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22USLJ | UNION SETTLEMENT- PLAY AREA AT JEFFERSON | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22USLM | UNION SETTLEMENT - PLAY AREA UPGRADE WHITE HOUSES | 1 | DESIGN | Jan 2022 | Jun 2022 | Jan 2022 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22USLM | UNION SETTLEMENT - PLAY AREA UPGRADE WHITE HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22USLM | UNION SETTLEMENT - PLAY AREA UPGRADE WHITE HOUSES | 3 | CONSTRUCTION | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22USLM | UNION SETTLEMENT - PLAY AREA UPGRADE WHITE HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jun 2024 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22USLM | UNION SETTLEMENT - PLAY AREA UPGRADE WHITE HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22WAPL | WALD HOUSES- PLAYGROUND RENOVATION | 1 | DESIGN | Apr 2022 | Sep 2022 | Apr 2022 | Sep 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22WAPL | WALD HOUSES- PLAYGROUND RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2022 | Mar 2023 | Sep 2022 | Mar 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22WAPL | WALD HOUSES- PLAYGROUND RENOVATION | 3 | CONSTRUCTION | Mar 2023 | Mar 2024 | Mar 2023 | Mar 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22WAPL | WALD HOUSES- PLAYGROUND RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Sep 2024 | Mar 2023 | Mar 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22WAPL | WALD HOUSES- PLAYGROUND RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Sep 2024 | Mar 2024 | Sep 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23CBCR | CLINTON HOUSES- BASKETBALL COURT | 1 | DESIGN | Jan 2023 | Jun 2023 | Jan 2023 | Jun 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23CBCR | CLINTON HOUSES- BASKETBALL COURT | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Dec 2023 | Jul 2023 | Dec 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23CBCR | CLINTON HOUSES- BASKETBALL COURT | 3 | CONSTRUCTION | Dec 2023 | Dec 2024 | Dec 2023 | Dec 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23CBCR | CLINTON HOUSES- BASKETBALL COURT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2024 | Jun 2025 | Dec 2023 | Dec 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23CBCR | CLINTON HOUSES- BASKETBALL COURT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23SAPC | SEWARD PARK ANNEX PLAYGROUND CONSTRUCTION | 1 | DESIGN | Jun 2024 | Dec 2024 | Jun 2024 | Dec 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23SAPC | SEWARD PARK ANNEX PLAYGROUND CONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23SAPC | SEWARD PARK ANNEX PLAYGROUND CONSTRUCTION | 3 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23SAPC | SEWARD PARK ANNEX PLAYGROUND CONSTRUCTION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Dec 2026 | Jun 2025 | Jun 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23SAPC | SEWARD PARK ANNEX PLAYGROUND CONSTRUCTION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Dec 2026 | Jun 2026 | Dec 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23SFFB | SMITH HOUSES FOB PROJECT COMPLETION | 1 | DESIGN | Jun 2024 | Dec 2024 | Jun 2024 | Dec 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23SFFB | SMITH HOUSES FOB PROJECT COMPLETION | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23SFFB | SMITH HOUSES FOB PROJECT COMPLETION | 3 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23SFFB | SMITH HOUSES FOB PROJECT COMPLETION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Dec 2026 | Jun 2025 | Jun 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23SFFB | SMITH HOUSES FOB PROJECT COMPLETION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Dec 2026 | Jun 2026 | Dec 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23SIWD | STANLEY ISAACS CENTER- WINDOWS AND DOORS | 1 | DESIGN | Jun 2024 | Dec 2024 | Jun 2024 | Dec 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23SIWD | STANLEY ISAACS CENTER- WINDOWS AND DOORS | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23SIWD | STANLEY ISAACS CENTER- WINDOWS AND DOORS | 3 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23SIWD | STANLEY ISAACS CENTER- WINDOWS AND DOORS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Dec 2026 | Jun 2025 | Jun 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM23SIWD | STANLEY ISAACS CENTER- WINDOWS AND DOORS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Dec 2026 | Jun 2026 | Dec 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18BOI | Replace boilers at Lehman Village and Wilson Houses | 1 | DEVELOP SCOPE | Jul 2020 | Sep 2020 | Jul 2020 | Sep 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18BOI | Replace boilers at Lehman Village and Wilson Houses | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18BOI | Replace boilers at Lehman Village and Wilson Houses | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18BOI | Replace boilers at Lehman Village and Wilson Houses | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18BOI | Replace boilers at Lehman Village and Wilson Houses | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18BOI | Replace boilers at Lehman Village and Wilson Houses | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18BOI | Replace boilers at Lehman Village and Wilson Houses | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2025
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18BOI | Replace boilers at Lehman Village and Wilson Houses | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2025 | Jan 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18BOI | Replace boilers at Lehman Village and Wilson Houses | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2026 | Mar 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18BOI | Replace boilers at Lehman Village and Wilson Houses | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2026 | Apr 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ECC | Renovations at Early Childhood Centers in East Harlem | 1 | DEVELOP SCOPE | Jul 2020 | Sep 2020 | Jul 2020 | Sep 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ECC | Renovations at Early Childhood Centers in East Harlem | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ECC | Renovations at Early Childhood Centers in East Harlem | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ECC | Renovations at Early Childhood Centers in East Harlem | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ECC | Renovations at Early Childhood Centers in East Harlem | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ECC | Renovations at Early Childhood Centers in East Harlem | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ECC | Renovations at Early Childhood Centers in East Harlem | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2025
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ECC | Renovations at Early Childhood Centers in East Harlem | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2025 | Jan 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ECC | Renovations at Early Childhood Centers in East Harlem | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2026 | Mar 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ECC | Renovations at Early Childhood Centers in East Harlem | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2026 | Apr 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18GAS | Install new gas risers at Johnson Houses Install new gas ris | 1 | DEVELOP SCOPE | Jul 2020 | Sep 2020 | Jul 2020 | Sep 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18GAS | Install new gas risers at Johnson Houses Install new gas ris | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18GAS | Install new gas risers at Johnson Houses Install new gas ris | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18GAS | Install new gas risers at Johnson Houses Install new gas ris | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18GAS | Install new gas risers at Johnson Houses Install new gas ris | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18GAS | Install new gas risers at Johnson Houses Install new gas ris | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18GAS | Install new gas risers at Johnson Houses Install new gas ris | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2025
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18GAS | Install new gas risers at Johnson Houses Install new gas ris | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2025 | Jan 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18GAS | Install new gas risers at Johnson Houses Install new gas ris | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2026 | Mar 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18GAS | Install new gas risers at Johnson Houses Install new gas ris | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2026 | Apr 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ROF | Conduct roof and parapet work at UPACA (Site 5) | 1 | DEVELOP SCOPE | Sep 2020 | Dec 2020 | Sep 2020 | Dec 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ROF | Conduct roof and parapet work at UPACA (Site 5) | 2 | PRELIMINARY DESIGN | Dec 2020 | Apr 2021 | Dec 2020 | Apr 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ROF | Conduct roof and parapet work at UPACA (Site 5) | 3 | FINAL DESIGN | Apr 2021 | Oct 2021 | Apr 2021 | Oct 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ROF | Conduct roof and parapet work at UPACA (Site 5) | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ROF | Conduct roof and parapet work at UPACA (Site 5) | 5 | CONSTRUCTION TO 25% | Jan 2022 | May 2022 | Jan 2022 | May 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ROF | Conduct roof and parapet work at UPACA (Site 5) | 6 | CONSTRUCTION TO 50% | May 2022 | Sep 2022 | May 2022 | Sep 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ROF | Conduct roof and parapet work at UPACA (Site 5) | 7 | CONSTRUCTION TO 75% | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ROF | Conduct roof and parapet work at UPACA (Site 5) | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2023 | Apr 2023 | Jan 2026 | Apr 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ROF | Conduct roof and parapet work at UPACA (Site 5) | 9 | SUBSTANTIAL COMPLETION | Apr 2023 | Jun 2023 | Apr 2026 | Jun 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ROF | Conduct roof and parapet work at UPACA (Site 5) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2023 | Jul 2023 | Jun 2026 | Jul 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18VNT | Modernize ventilation systems in 17 East Harlem Developments | 1 | DEVELOP SCOPE | Jul 2020 | Sep 2020 | Jul 2020 | Sep 2020
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18VNT | Modernize ventilation systems in 17 East Harlem Developments | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18VNT | Modernize ventilation systems in 17 East Harlem Developments | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18VNT | Modernize ventilation systems in 17 East Harlem Developments | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18VNT | Modernize ventilation systems in 17 East Harlem Developments | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18VNT | Modernize ventilation systems in 17 East Harlem Developments | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18VNT | Modernize ventilation systems in 17 East Harlem Developments | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18VNT | Modernize ventilation systems in 17 East Harlem Developments | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18VNT | Modernize ventilation systems in 17 East Harlem Developments | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2023 | Mar 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18VNT | Modernize ventilation systems in 17 East Harlem Developments | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2023 | Apr 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | P-3HELLK2 | DEP Shaft Site -Kitchen Pk Construction | 1 | DEVELOP SCOPE | Jan 2023 | Jun 2023 | Jan 2023 | Jun 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | P-3HELLK2 | DEP Shaft Site -Kitchen Pk Construction | 2 | DESIGN | Jun 2023 | Jun 2024 | Jun 2023 | Jun 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | P-3HELLK2 | DEP Shaft Site -Kitchen Pk Construction | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | P-3HELLK2 | DEP Shaft Site -Kitchen Pk Construction | 4 | CONSTRUCTION | Mar 2025 | Mar 2026 | Mar 2025 | Mar 2026
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | P-3HELLK2 | DEP Shaft Site -Kitchen Pk Construction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Mar 2027 | Mar 2026 | Mar 2027
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | P-3WAGNER | Wagner Playground, Manhattan | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2021 | Dec 2021
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | P-3WAGNER | Wagner Playground, Manhattan | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2021 | Dec 2022
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | P-3WAGNER | Wagner Playground, Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2022 | Sep 2023
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | P-3WAGNER | Wagner Playground, Manhattan | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | P-3WAGNER | Wagner Playground, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CME520FPC | OCME - New Medical Examiner Facility | 1 | DEVELOP SCOPE | Aug 2022 | Sep 2022 | Aug 2025 | Sep 2025
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CME520FPC | OCME - New Medical Examiner Facility | 2 | PRELIMINARY DESIGN | Sep 2022 | Nov 2022 | Sep 2025 | Jan 2026
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CME520FPC | OCME - New Medical Examiner Facility | 3 | FINAL DESIGN | Nov 2022 | Mar 2023 | Jan 2026 | May 2026
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CME520FPC | OCME - New Medical Examiner Facility | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2023 | Jun 2023 | May 2026 | Aug 2026
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CME520FPC | OCME - New Medical Examiner Facility | 5 | CONSTRUCTION TO 25% | Jun 2023 | Sep 2023 | Aug 2026 | Nov 2026
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CME520FPC | OCME - New Medical Examiner Facility | 6 | CONSTRUCTION TO 50% | Sep 2023 | Nov 2023 | Nov 2026 | Jan 2027
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CME520FPC | OCME - New Medical Examiner Facility | 7 | CONSTRUCTION TO 75% | Nov 2023 | Dec 2023 | Jan 2027 | Jan 2027
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CME520FPC | OCME - New Medical Examiner Facility | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2023 | Jan 2024 | Feb 2027 | Mar 2027
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CME520FPC | OCME - New Medical Examiner Facility | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Feb 2024 | Mar 2027 | Apr 2027
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CME520FPC | OCME - New Medical Examiner Facility | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2024 | Apr 2024 | Apr 2027 | May 2027
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CHRHC | Central Harlem Health Center interior renovation | 1 | DESIGN | Jan 2019 | May 2020 | Jan 2019 | Mar 2019
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CHRHC | Central Harlem Health Center interior renovation | 2 | CONSTRUCTION | May 2020 | May 2025 | Apr 2019 | Jul 2019
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CHRHC | Central Harlem Health Center interior renovation | 3 | PUNCHLIST COMPLETE, JOB CLOSED | May 2025 | May 2025 | Jul 2019 | Jan 2020
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CHRHC | Central Harlem Health Center interior renovation | 4 | DEVELOP SCOPE | May 2025 | May 2025 | Jan 2020 | Apr 2020
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CHRHC | Central Harlem Health Center interior renovation | 5 | PRELIMINARY DESIGN | May 2025 | May 2025 | Apr 2020 | Aug 2020
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CHRHC | Central Harlem Health Center interior renovation | 6 | FINAL DESIGN | May 2025 | May 2025 | Aug 2020 | Dec 2020
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CHRHC | Central Harlem Health Center interior renovation | 7 | BID AWARD AND REGISTER CONTRCT | May 2025 | May 2025 | Dec 2020 | Apr 2021
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CHRHC | Central Harlem Health Center interior renovation | 8 | CONSTRUCTION TO 25% | May 2025 | May 2025 | Apr 2021 | Jul 2021
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CHRHC | Central Harlem Health Center interior renovation | 9 | CONSTRUCTION TO 50% | May 2025 | May 2025 | Jul 2021 | Sep 2021
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CHRHC | Central Harlem Health Center interior renovation | 10 | CONSTRUCTION TO 75% | May 2025 | May 2025 | Sep 2021 | Oct 2025
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CHRHC | Central Harlem Health Center interior renovation | 11 | ORIGINAL EQUIP & FURNISHING | May 2025 | May 2025 | Sep 2021 | Oct 2025
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CHRHC | Central Harlem Health Center interior renovation | 12 | SUBSTANTIAL COMPLETION | May 2025 | May 2025 | Sep 2021 | Oct 2025
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CHRHC | Central Harlem Health Center interior renovation | 13 | PUNCHLIST COMPLETE, JOB CLOSED | May 2025 | Jun 2025 | Sep 2021 | Oct 2025
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EASTH | EAST HARLEM HEALTH HUB | 1 | DESIGN | Feb 2017 | Mar 2017 | Feb 2017 | Mar 2017
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EASTH | EAST HARLEM HEALTH HUB | 2 | CONSTRUCTION | Mar 2017 | Mar 2017 | Mar 2017 | Mar 2018
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EASTH | EAST HARLEM HEALTH HUB | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | May 2017 | Mar 2018 | Dec 2027
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHRHC | East Harlem Health Center interior renovation | 1 | DESIGN | Jun 2015 | Oct 2016 | Jun 2026 | Oct 2026
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHRHC | East Harlem Health Center interior renovation | 2 | CONSTRUCTION | Oct 2016 | Oct 2021 | Jan 2027 | Aug 2028
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHRHC | East Harlem Health Center interior renovation | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2021 | Oct 2021 | Sep 2028 | Nov 2028
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHRHC | East Harlem Health Center interior renovation | 4 | DEVELOP SCOPE | Oct 2021 | Oct 2021 | Sep 2028 | Nov 2028
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHRHC | East Harlem Health Center interior renovation | 5 | PRELIMINARY DESIGN | Oct 2021 | Oct 2021 | Sep 2028 | Nov 2028
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHRHC | East Harlem Health Center interior renovation | 6 | FINAL DESIGN | Oct 2021 | Oct 2021 | Sep 2028 | Nov 2028
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHRHC | East Harlem Health Center interior renovation | 7 | BID AWARD AND REGISTER CONTRCT | Oct 2021 | Oct 2021 | Sep 2028 | Nov 2028
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHRHC | East Harlem Health Center interior renovation | 8 | CONSTRUCTION TO 25% | Oct 2021 | Oct 2021 | Sep 2028 | Nov 2028
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHRHC | East Harlem Health Center interior renovation | 9 | CONSTRUCTION TO 50% | Oct 2021 | Oct 2021 | Sep 2028 | Nov 2028
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHRHC | East Harlem Health Center interior renovation | 10 | CONSTRUCTION TO 75% | Oct 2021 | Oct 2021 | Sep 2028 | Nov 2028
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHRHC | East Harlem Health Center interior renovation | 11 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Oct 2021 | Sep 2028 | Nov 2028
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHRHC | East Harlem Health Center interior renovation | 12 | SUBSTANTIAL COMPLETION | Oct 2021 | Oct 2021 | Sep 2028 | Nov 2028
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHRHC | East Harlem Health Center interior renovation | 13 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2021 | Nov 2021 | Sep 2028 | Nov 2028
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82PHLNB | DOHMH FACILITIES | 1 | DESIGN | Mar 2011 | Jul 2012 | Jan 2014 | Jun 2015
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82PHLNB | DOHMH FACILITIES | 2 | CONSTRUCTION | Jul 2012 | Jul 2017 | Jun 2015 | May 2020
20231026 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82PHLNB | DOHMH FACILITIES | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2017 | Oct 2017 | May 2020 | Aug 2023
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 02200901 | CENTRAL OFFICE: PRIMARY CARE INITIATIVE | 1 | DESIGN | Feb 2019 | Jan 2020 | Feb 2024 | Apr 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 02200901 | CENTRAL OFFICE: PRIMARY CARE INITIATIVE | 2 | CONSTRUCTION | Jan 2020 | Dec 2020 | Feb 2024 | Apr 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 02200901 | CENTRAL OFFICE: PRIMARY CARE INITIATIVE | 3 | CONSTRUCTION | Jan 2020 | Dec 2020 | Apr 2024 | Jun 2032
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11200912 | BELLEVUE: EMERGENCY PIPE INSTALLATION, 22ND FLOOR | 1 | DESIGN | May 2009 | Nov 2009 | Sep 2009 | Nov 2009
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11200912 | BELLEVUE: EMERGENCY PIPE INSTALLATION, 22ND FLOOR | 2 | CONSTRUCTION | Nov 2009 | Apr 2010 | Nov 2009 | Apr 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201705 | BELLEVUE CONSTRUCT NEW ROCHE CHEMISTRY LABORATORY | 1 | DESIGN | Feb 2019 | Jan 2020 | Feb 2019 | Jan 2020
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201705 | BELLEVUE CONSTRUCT NEW ROCHE CHEMISTRY LABORATORY | 2 | CONSTRUCTION | Jan 2020 | Dec 2020 | Feb 2019 | Jan 2020
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201705 | BELLEVUE CONSTRUCT NEW ROCHE CHEMISTRY LABORATORY | 3 | CONSTRUCTION | Jan 2020 | Dec 2020 | Jan 2020 | Jun 2026
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201803 | BELLEVUE EXPAND HEIGHT OF GUARDRAILS IN THE ACB ATRIUM | 1 | DESIGN | Aug 2019 | Jun 2020 | Aug 2019 | Jun 2020
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201803 | BELLEVUE EXPAND HEIGHT OF GUARDRAILS IN THE ACB ATRIUM | 2 | CONSTRUCTION | Jul 2020 | Jun 2021 | Aug 2019 | Jun 2020
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201803 | BELLEVUE EXPAND HEIGHT OF GUARDRAILS IN THE ACB ATRIUM | 3 | CONSTRUCTION | Jul 2020 | Jun 2021 | Jul 2020 | Jun 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201903 | BELLEVUE: RENOVATION AND UPGRADE OF TRAUMA SLOTS IN ADULT ED | 1 | DESIGN | Dec 2019 | May 2021 | Dec 2019 | May 2021
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201903 | BELLEVUE: RENOVATION AND UPGRADE OF TRAUMA SLOTS IN ADULT ED | 2 | CONSTRUCTION | May 2021 | May 2024 | May 2021 | May 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201903 | BELLEVUE: RENOVATION AND UPGRADE OF TRAUMA SLOTS IN ADULT ED | 3 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Aug 2024 | May 2024 | Aug 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202101 | BELLEVUE: REPLACE EMERGENCY DEPT NURSES STATION | 1 | DESIGN | Nov 2020 | Feb 2021 | Nov 2020 | Apr 2022
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202101 | BELLEVUE: REPLACE EMERGENCY DEPT NURSES STATION | 2 | CONSTRUCTION | Feb 2021 | Jun 2021 | Apr 2022 | Apr 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202101 | BELLEVUE: REPLACE EMERGENCY DEPT NURSES STATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2021 | Aug 2021 | Apr 2025 | Jul 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202104 | Bellevue: Bldg H (16th Fl) - New Infusion Center (Interior R | 1 | DESIGN | Nov 2020 | Apr 2022 | Nov 2020 | Apr 2022
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202104 | Bellevue: Bldg H (16th Fl) - New Infusion Center (Interior R | 2 | CONSTRUCTION | Apr 2022 | Apr 2025 | Apr 2022 | Apr 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202104 | Bellevue: Bldg H (16th Fl) - New Infusion Center (Interior R | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2025 | Jul 2025 | Apr 2025 | Jul 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202106 | BELLEVUE PHARMACY COMPOUNDING USP 797/800 COMPLIANCE | 1 | DESIGN | Nov 2020 | Apr 2022 | Nov 2020 | Apr 2022
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202106 | BELLEVUE PHARMACY COMPOUNDING USP 797/800 COMPLIANCE | 2 | CONSTRUCTION | Apr 2022 | Apr 2025 | Apr 2022 | Apr 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202106 | BELLEVUE PHARMACY COMPOUNDING USP 797/800 COMPLIANCE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2025 | Jul 2025 | Apr 2025 | Jul 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202201 | BELLEVUE FIRE ALARM PANELS REPLACEMENT- MAIN HOSPITAL | 1 | DESIGN | Nov 2020 | Apr 2022 | Nov 2020 | Apr 2022
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202201 | BELLEVUE FIRE ALARM PANELS REPLACEMENT- MAIN HOSPITAL | 2 | CONSTRUCTION | Apr 2022 | Apr 2025 | Apr 2022 | Apr 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202201 | BELLEVUE FIRE ALARM PANELS REPLACEMENT- MAIN HOSPITAL | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2025 | Jul 2025 | Apr 2025 | Jul 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202202 | BELLEVUE SOUTH STAND PIPE REPLACEMENT- HOSPITAL BLD | 1 | DESIGN | Nov 2020 | Apr 2022 | Nov 2020 | Apr 2022
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202202 | BELLEVUE SOUTH STAND PIPE REPLACEMENT- HOSPITAL BLD | 2 | CONSTRUCTION | Apr 2022 | Apr 2024 | Apr 2022 | Apr 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202202 | BELLEVUE SOUTH STAND PIPE REPLACEMENT- HOSPITAL BLD | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2024 | Jul 2024 | Apr 2024 | Jul 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202204 | BELLEVUE FORENSIC PSYCH-19E | 1 | DESIGN | Jun 2021 | Nov 2022 | Jun 2021 | Nov 2022
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202204 | BELLEVUE FORENSIC PSYCH-19E | 2 | CONSTRUCTION | Nov 2022 | Nov 2025 | Nov 2022 | Nov 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202204 | BELLEVUE FORENSIC PSYCH-19E | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2025 | Feb 2026 | Nov 2025 | Feb 2026
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202205 | BELLEVUE REPLACE FIRE PUMP | 1 | DESIGN | Jun 2021 | Nov 2022 | Jun 2021 | Nov 2022
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202205 | BELLEVUE REPLACE FIRE PUMP | 2 | CONSTRUCTION | Nov 2022 | Nov 2025 | Nov 2022 | Nov 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202205 | BELLEVUE REPLACE FIRE PUMP | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2025 | Feb 2026 | Nov 2025 | Feb 2026
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202206 | BELLEVUE CHS OUTPOSTED THERAPEUTIC UNITS | 1 | DESIGN | Jun 2021 | Nov 2022 | Jun 2021 | Nov 2022
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202206 | BELLEVUE CHS OUTPOSTED THERAPEUTIC UNITS | 2 | CONSTRUCTION | Nov 2022 | Nov 2025 | Nov 2022 | Nov 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202206 | BELLEVUE CHS OUTPOSTED THERAPEUTIC UNITS | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2025 | Feb 2026 | Nov 2025 | Feb 2026
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201501 | GOUVERNEUR: ROBERTO CLEMENTE CENTER RENOVATION | 1 | DESIGN | Nov 2014 | Apr 2016 | Nov 2014 | Apr 2016
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201501 | GOUVERNEUR: ROBERTO CLEMENTE CENTER RENOVATION | 2 | CONSTRUCTION | Apr 2016 | Apr 2018 | Apr 2016 | Apr 2018
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201501 | GOUVERNEUR: ROBERTO CLEMENTE CENTER RENOVATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2018 | Jun 2018 | Apr 2018 | Jun 2032
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201702 | GOUVERNEUR INSTALL SECONDARY WATER DISINFECTION SYSTEM | 2 | CONSTRUCTION | Jan 2019 | Jun 2019 | Jan 2019 | Jun 2019
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201801 | GOUVERNEUR REHABILITATE FACADE-CYCLE 7B AMENDED AND CYCLE 8B | 1 | DESIGN | Jan 2019 | Jul 2019 | Feb 2001 | Jun 2016
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201801 | GOUVERNEUR REHABILITATE FACADE-CYCLE 7B AMENDED AND CYCLE 8B | 2 | CONSTRUCTION | Jul 2019 | Dec 2019 | Jun 2016 | May 2029
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201802 | GOUVERNEUR: Installation of Exhaust Fan, 5th Floor Air | 2 | CONSTRUCTION | Jun 2021 | Jun 2024 | Jun 2021 | Jun 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201802 | GOUVERNEUR: Installation of Exhaust Fan, 5th Floor Air | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201804 | JUDSON, REMOVE AND REPLACE FIRE LINE | 1 | DESIGN | Jan 2019 | Jul 2019 | Jan 2019 | Jul 2019
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201804 | JUDSON, REMOVE AND REPLACE FIRE LINE | 2 | CONSTRUCTION | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201902 | GOUVERNEUR: RENOVATE COURTYARD | 1 | DESIGN | Jan 2020 | Jul 2020 | Jul 2020 | Sep 2020
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201902 | GOUVERNEUR: RENOVATE COURTYARD | 2 | CONSTRUCTION | Jul 2020 | Dec 2020 | Sep 2020 | Jun 2032
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12202101 | GOUVERNEUR EXPRESS CARE | 1 | DESIGN | Feb 2021 | Jun 2022 | Feb 2024 | Jun 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12202101 | GOUVERNEUR EXPRESS CARE | 2 | CONSTRUCTION | Jun 2022 | Jun 2025 | Jun 2025 | Jun 2028
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12202101 | GOUVERNEUR EXPRESS CARE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2025 | Sep 2025 | Jun 2028 | Sep 2028
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12202201 | GOUVERNEUR: POST ACUTE DIALYSIS DENS | 1 | DESIGN | Jun 2021 | Nov 2022 | Jun 2021 | Nov 2022
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12202201 | GOUVERNEUR: POST ACUTE DIALYSIS DENS | 2 | CONSTRUCTION | Nov 2022 | Nov 2025 | Nov 2022 | Nov 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12202201 | GOUVERNEUR: POST ACUTE DIALYSIS DENS | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2025 | Feb 2026 | Nov 2025 | Feb 2026
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12202202 | NYC H+H--GOUVERNEUR HOSPITAL-PATIENT/RESIDENT OUTDOOR GARDEN | 1 | DESIGN | Jul 2022 | Nov 2023 | Jul 2022 | Nov 2023
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12202202 | NYC H+H--GOUVERNEUR HOSPITAL-PATIENT/RESIDENT OUTDOOR GARDEN | 2 | CONSTRUCTION | Nov 2023 | Nov 2026 | Nov 2023 | Nov 2026
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12202202 | NYC H+H--GOUVERNEUR HOSPITAL-PATIENT/RESIDENT OUTDOOR GARDEN | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Feb 2027 | Nov 2026 | Feb 2027
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12202401 | RENOVATE SHOWER ROOMS FOR RESIDENTS | 1 | DESIGN | Oct 2017 | Mar 2019 | Oct 2017 | Mar 2019
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12202401 | RENOVATE SHOWER ROOMS FOR RESIDENTS | 2 | CONSTRUCTION | Mar 2019 | Mar 2024 | Mar 2019 | Mar 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12202401 | RENOVATE SHOWER ROOMS FOR RESIDENTS | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | May 2024 | Mar 2024 | May 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12202402 | GOTHAM HEALTH--UPGRADE ADA ACCESS WITH VERTICAL WHEEL LIFT | 1 | DESIGN | Oct 2017 | Mar 2019 | Oct 2017 | Mar 2019
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12202402 | GOTHAM HEALTH--UPGRADE ADA ACCESS WITH VERTICAL WHEEL LIFT | 2 | CONSTRUCTION | Mar 2019 | Mar 2024 | Mar 2019 | Mar 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12202402 | GOTHAM HEALTH--UPGRADE ADA ACCESS WITH VERTICAL WHEEL LIFT | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | May 2024 | Mar 2024 | May 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12202403 | GOUVENEUR-GOTHAM: INDEPENDENT COOLING FOR PHARMACY | 1 | DESIGN | Oct 2017 | Mar 2019 | Oct 2017 | Mar 2019
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12202403 | GOUVENEUR-GOTHAM: INDEPENDENT COOLING FOR PHARMACY | 2 | CONSTRUCTION | Mar 2019 | Mar 2024 | Mar 2019 | Mar 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12202403 | GOUVENEUR-GOTHAM: INDEPENDENT COOLING FOR PHARMACY | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | May 2024 | Mar 2024 | May 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13200573 | HARLEM: CONSTRUCT NEW PARKING FACILITY | 1 | DESIGN | Feb 2017 | Dec 2017 | Feb 2017 | Dec 2017
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13200573 | HARLEM: CONSTRUCT NEW PARKING FACILITY | 2 | CONSTRUCTION | Jan 2018 | Dec 2018 | Feb 2017 | Dec 2017
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13200573 | HARLEM: CONSTRUCT NEW PARKING FACILITY | 3 | CONSTRUCTION | Jan 2018 | Dec 2018 | Jan 2018 | Jun 2032
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201101 | HARLEM: RELOCATE SYDENHAM CLINIC FROM 125TH TO 118TH STREET | 1 | DESIGN | May 2010 | Apr 2011 | May 2010 | Apr 2011
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201101 | HARLEM: RELOCATE SYDENHAM CLINIC FROM 125TH TO 118TH STREET | 2 | CONSTRUCTION | Apr 2011 | Mar 2012 | May 2010 | Apr 2011
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201101 | HARLEM: RELOCATE SYDENHAM CLINIC FROM 125TH TO 118TH STREET | 3 | CONSTRUCTION | Apr 2011 | Mar 2012 | Apr 2011 | Jun 2032
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201301 | HARLEM: RENOVATE POST PARTUM UNIT | 1 | DESIGN | May 2014 | Apr 2015 | Aug 2001 | Jun 2015
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201301 | HARLEM: RENOVATE POST PARTUM UNIT | 2 | CONSTRUCTION | Apr 2015 | Mar 2016 | Aug 2001 | Jun 2015
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201301 | HARLEM: RENOVATE POST PARTUM UNIT | 3 | CONSTRUCTION | Apr 2015 | Mar 2016 | Jun 2015 | Aug 2032
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201502 | HARLEM: UPGRADE ELECTRICAL SYSTEM | 1 | DESIGN | May 2016 | Mar 2017 | Dec 2015 | Oct 2016
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201502 | HARLEM: UPGRADE ELECTRICAL SYSTEM | 2 | CONSTRUCTION | Apr 2017 | Mar 2018 | Dec 2015 | Oct 2016
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201502 | HARLEM: UPGRADE ELECTRICAL SYSTEM | 3 | CONSTRUCTION | Apr 2017 | Mar 2018 | Apr 2017 | Jun 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201602 | HARLEM: REHABILITATE THE EXTERIOR FACADE OF MLK BLG - LL 11 | 1 | DESIGN | May 2018 | Oct 2019 | May 2018 | Oct 2019
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201602 | HARLEM: REHABILITATE THE EXTERIOR FACADE OF MLK BLG - LL 11 | 2 | CONSTRUCTION | Oct 2019 | Oct 2021 | Oct 2019 | Jun 2026
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201602 | HARLEM: REHABILITATE THE EXTERIOR FACADE OF MLK BLG - LL 11 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2021 | Dec 2021 | Jul 2026 | Sep 2026
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201603 | HARLEM: WP DECANTING, ONR DEMOLITION, & NEW DATA CENTER | 1 | DESIGN | Nov 2018 | Apr 2020 | Nov 2018 | Apr 2020
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201603 | HARLEM: WP DECANTING, ONR DEMOLITION, & NEW DATA CENTER | 2 | CONSTRUCTION | Apr 2020 | Apr 2022 | Apr 2020 | Apr 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201603 | HARLEM: WP DECANTING, ONR DEMOLITION, & NEW DATA CENTER | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2022 | Jun 2022 | Apr 2024 | Jun 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201803 | HARLEM: KOUNTZ PAVILION STAIRWELL REHABILITATION | 1 | DESIGN | Jul 2019 | Jan 2020 | Jul 2019 | Jan 2020
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201803 | HARLEM: KOUNTZ PAVILION STAIRWELL REHABILITATION | 2 | CONSTRUCTION | Jan 2020 | Jun 2020 | Jan 2020 | Jun 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202001 | HARLEM: RELOCATE VARIOUS DEPARTMENTS FROM THE WP | 1 | DESIGN | Feb 2020 | Dec 2020 | Feb 2020 | Dec 2020
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202001 | HARLEM: RELOCATE VARIOUS DEPARTMENTS FROM THE WP | 2 | CONSTRUCTION | Jan 2021 | Dec 2021 | Feb 2020 | Dec 2020
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202001 | HARLEM: RELOCATE VARIOUS DEPARTMENTS FROM THE WP | 3 | CONSTRUCTION | Jan 2021 | Dec 2021 | Jan 2021 | Jun 2028
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202101 | HARLEM ELEVATOR HVAC UPGRADE | 1 | DESIGN | Feb 2021 | Jun 2022 | Feb 2021 | Jun 2022
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202101 | HARLEM ELEVATOR HVAC UPGRADE | 2 | CONSTRUCTION | Jun 2022 | Jun 2025 | Jun 2022 | Jun 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202101 | HARLEM ELEVATOR HVAC UPGRADE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202102 | Harlem: Cooling Tower Replacement | 1 | DESIGN | Jun 2021 | Nov 2022 | Jun 2021 | Nov 2022
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202102 | Harlem: Cooling Tower Replacement | 2 | CONSTRUCTION | Nov 2022 | Nov 2025 | Nov 2022 | Nov 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202102 | Harlem: Cooling Tower Replacement | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2025 | Feb 2026 | Nov 2025 | Feb 2026
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202142 | HARLEM: X RAY & Construction Work | 1 | DESIGN | Jun 2021 | Nov 2022 | Jun 2021 | Nov 2022
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202142 | HARLEM: X RAY & Construction Work | 2 | CONSTRUCTION | Nov 2022 | Nov 2025 | Nov 2022 | Nov 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202142 | HARLEM: X RAY & Construction Work | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2025 | Feb 2026 | Nov 2025 | Feb 2026
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202201 | HARLEM CONDENSER WATER PIPING REPLACEMENT | 1 | DESIGN | Jun 2021 | Nov 2022 | Jun 2021 | Nov 2022
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202201 | HARLEM CONDENSER WATER PIPING REPLACEMENT | 2 | CONSTRUCTION | Nov 2022 | Nov 2025 | Nov 2022 | Nov 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202201 | HARLEM CONDENSER WATER PIPING REPLACEMENT | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2025 | Feb 2026 | Nov 2025 | Feb 2026
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202202 | HARLEM: ANTI-LIGATURE RISK AND PATIENT SAFETY PROJECT | 1 | DESIGN | Jun 2022 | Oct 2023 | Jun 2032 | Jun 2032
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202202 | HARLEM: ANTI-LIGATURE RISK AND PATIENT SAFETY PROJECT | 2 | CONSTRUCTION | Oct 2023 | Oct 2026 | Jun 2032 | Jun 2035
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202202 | HARLEM: ANTI-LIGATURE RISK AND PATIENT SAFETY PROJECT | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2026 | Jan 2027 | Jun 2035 | Aug 2035
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202246 | HARLEM: Retinal Camera (NICU) | 2 | CONSTRUCTION | Jun 2022 | Dec 2022 | Jun 2025 | Dec 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202301 | HARLEM RETAIL PHARMACY | 1 | DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202301 | HARLEM RETAIL PHARMACY | 2 | CONSTRUCTION | Jul 2025 | Dec 2025 | Jul 2025 | Dec 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 18201515 | SYDENHAM: RENOVATE WOMEN'S HEALTH SERVICES - MAMMOGRAPHY | 1 | DESIGN | Jan 2015 | Jul 2015 | Jan 2015 | Jul 2015
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 18201515 | SYDENHAM: RENOVATE WOMEN'S HEALTH SERVICES - MAMMOGRAPHY | 2 | CONSTRUCTION | Jul 2015 | Dec 2015 | Jul 2015 | Dec 2015
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 18201801 | SYDENHAM: ERODED WALL REPLACEMENT | 3 | CONSTRUCTION | Jul 2019 | Jun 2020 | Jul 2019 | Jun 2020
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 18202001 | SYDENHAM: RETAIL PHARMACY RENOVATION | 1 | DESIGN | Sep 2019 | Feb 2021 | Jun 2032 | Jun 2032
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 18202001 | SYDENHAM: RETAIL PHARMACY RENOVATION | 2 | CONSTRUCTION | Feb 2021 | Feb 2024 | Jun 2032 | Oct 2038
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 18202001 | SYDENHAM: RETAIL PHARMACY RENOVATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2024 | May 2024 | Oct 2038 | Jan 2039
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 18202201 | SYDENHAM BATHROOM RENOVATION | 1 | DESIGN | Jun 2021 | Oct 2022 | Jun 2033 | Jun 2033
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 18202201 | SYDENHAM BATHROOM RENOVATION | 2 | CONSTRUCTION | Oct 2022 | Oct 2025 | Jun 2033 | May 2036
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 18202201 | SYDENHAM BATHROOM RENOVATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2025 | Jan 2026 | Jun 2036 | Aug 2036
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37201301 | METROPOLITAN COMPLETE RENOVATION OF SIXTH FLOOR 6C MAIN BLDG | 1 | DESIGN | Aug 2018 | Jul 2019 | Aug 2018 | Jul 2019
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37201301 | METROPOLITAN COMPLETE RENOVATION OF SIXTH FLOOR 6C MAIN BLDG | 2 | CONSTRUCTION | Jul 2019 | Jun 2020 | Aug 2018 | Jul 2019
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37201301 | METROPOLITAN COMPLETE RENOVATION OF SIXTH FLOOR 6C MAIN BLDG | 3 | CONSTRUCTION | Jul 2019 | Jun 2020 | Jul 2019 | Jun 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37201501 | METROPOLITAN COMPREHENSIVE LGBTQ HEALTH CENTER | 1 | DESIGN | Aug 2018 | Jul 2019 | Aug 2018 | Jul 2019
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37201501 | METROPOLITAN COMPREHENSIVE LGBTQ HEALTH CENTER | 2 | CONSTRUCTION | Jul 2019 | Jun 2020 | Aug 2018 | Jul 2019
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37201501 | METROPOLITAN COMPREHENSIVE LGBTQ HEALTH CENTER | 3 | CONSTRUCTION | Jul 2019 | Jun 2020 | Aug 2019 | Jul 2026
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37201901 | MET REPLACE MEDIUM PRESSURE STEAM CONDENSATE RETURN RISER | 1 | DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37201901 | MET REPLACE MEDIUM PRESSURE STEAM CONDENSATE RETURN RISER | 2 | CONSTRUCTION | Jul 2020 | Dec 2020 | Aug 2020 | Jan 2022
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202001 | METROPOLITAN : REPLACE MRI AT MODULAR MRI BUILDING | 1 | DESIGN | May 2020 | Oct 2021 | May 2020 | Oct 2021
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202001 | METROPOLITAN : REPLACE MRI AT MODULAR MRI BUILDING | 2 | CONSTRUCTION | Oct 2021 | Oct 2024 | Oct 2021 | Oct 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202001 | METROPOLITAN : REPLACE MRI AT MODULAR MRI BUILDING | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202002 | METROPOLITAN: WINDOW REPLACEMENT | 1 | DESIGN | May 2020 | Oct 2021 | Nov 2023 | Apr 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202002 | METROPOLITAN: WINDOW REPLACEMENT | 2 | CONSTRUCTION | Oct 2021 | Oct 2024 | Apr 2025 | Apr 2028
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202002 | METROPOLITAN: WINDOW REPLACEMENT | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2024 | Jan 2025 | Apr 2028 | Jul 2028
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202003 | MET: EMERGENCY POWER SEPARATION AND UPGRADES | 1 | DESIGN | May 2020 | Oct 2021 | May 2020 | Oct 2021
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202003 | MET: EMERGENCY POWER SEPARATION AND UPGRADES | 2 | CONSTRUCTION | Oct 2021 | Oct 2024 | Oct 2021 | Oct 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202003 | MET: EMERGENCY POWER SEPARATION AND UPGRADES | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202102 | METROPOLITAN CHILLER PLANT UPGRADE | 1 | DESIGN | May 2020 | Sep 2021 | May 2023 | Sep 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202102 | METROPOLITAN CHILLER PLANT UPGRADE | 2 | CONSTRUCTION | Sep 2021 | Sep 2023 | Sep 2024 | Sep 2026
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202102 | METROPOLITAN CHILLER PLANT UPGRADE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Dec 2023 | Sep 2026 | Jun 2032
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202103 | METROPOLITAN FIRE PROTECTION UPGRADES | 1 | DESIGN | May 2020 | Sep 2021 | May 2025 | Sep 2026
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202103 | METROPOLITAN FIRE PROTECTION UPGRADES | 2 | CONSTRUCTION | Sep 2021 | Sep 2023 | Sep 2026 | Sep 2028
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202103 | METROPOLITAN FIRE PROTECTION UPGRADES | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Dec 2023 | Sep 2028 | Jun 2032
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202105 | METROPOLITAN: REPLACEMENT OF (14) ROOFS | 1 | DESIGN | Dec 2020 | May 2022 | Dec 2020 | May 2022
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202105 | METROPOLITAN: REPLACEMENT OF (14) ROOFS | 2 | CONSTRUCTION | May 2022 | May 2024 | May 2022 | May 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202105 | METROPOLITAN: REPLACEMENT OF (14) ROOFS | 3 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Jul 2024 | May 2024 | Jul 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202108 | METROPOLITAN: FIRE ALARM SYSTEM | 1 | DESIGN | May 2021 | Sep 2022 | May 2021 | Sep 2022
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202108 | METROPOLITAN: FIRE ALARM SYSTEM | 2 | CONSTRUCTION | Sep 2022 | Sep 2024 | Sep 2022 | Sep 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202108 | METROPOLITAN: FIRE ALARM SYSTEM | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202202 | METROPOLITAN: OUTPATIENT REHAB RENOVATION | 1 | DESIGN | May 2021 | Sep 2022 | May 2025 | Sep 2026
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202202 | METROPOLITAN: OUTPATIENT REHAB RENOVATION | 2 | CONSTRUCTION | Sep 2022 | Sep 2024 | Sep 2026 | Sep 2028
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202202 | METROPOLITAN: OUTPATIENT REHAB RENOVATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Dec 2024 | Sep 2028 | Jun 2032
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202203 | METROPOLITAN: INDOOR/OUTDOOR RESPITE SPACE RENOVATION | 1 | DESIGN | May 2021 | Sep 2022 | May 2021 | Sep 2022
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202203 | METROPOLITAN: INDOOR/OUTDOOR RESPITE SPACE RENOVATION | 2 | CONSTRUCTION | Sep 2022 | Sep 2024 | Sep 2022 | Sep 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202203 | METROPOLITAN: INDOOR/OUTDOOR RESPITE SPACE RENOVATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Dec 2025 | Sep 2024 | Dec 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202401 | METROPOLITAN HOSPITAL RADIOLOGY DEPARTMENT IMPROVEMENTS | 1 | DESIGN | Apr 2024 | Feb 2025 | Apr 2024 | Feb 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202401 | METROPOLITAN HOSPITAL RADIOLOGY DEPARTMENT IMPROVEMENTS | 2 | CONSTRUCTION | Mar 2025 | Mar 2026 | Apr 2024 | Feb 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202401 | METROPOLITAN HOSPITAL RADIOLOGY DEPARTMENT IMPROVEMENTS | 3 | CONSTRUCTION | Mar 2025 | Mar 2026 | Mar 2025 | Mar 2026
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 67200901 | COLER: RENOVATE THE NURSING FACILITY DAY ROOM | 1 | DESIGN | Jul 2019 | Jan 2020 | Aug 2025 | Feb 2026
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 67200901 | COLER: RENOVATE THE NURSING FACILITY DAY ROOM | 2 | CONSTRUCTION | Jan 2020 | Jun 2020 | Feb 2026 | Aug 2029
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 67201170 | COLER: WINDOW REPLACEMENT AND ROOF/FACADE REHABILITATION | 1 | DESIGN | May 2020 | Sep 2021 | May 2020 | Sep 2021
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 67201170 | COLER: WINDOW REPLACEMENT AND ROOF/FACADE REHABILITATION | 2 | CONSTRUCTION | Sep 2021 | Sep 2023 | Sep 2021 | Sep 2023
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 67201170 | COLER: WINDOW REPLACEMENT AND ROOF/FACADE REHABILITATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Dec 2023 | Sep 2023 | Dec 2023
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 67202201 | NYC H+H--COLER HOSPITAL-FIRE ALARM UPGRADE: INSTALLATION OF | 1 | DESIGN | Jul 2022 | Nov 2023 | Jul 2022 | Nov 2023
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 67202201 | NYC H+H--COLER HOSPITAL-FIRE ALARM UPGRADE: INSTALLATION OF | 2 | CONSTRUCTION | Nov 2023 | Nov 2026 | Nov 2023 | Nov 2026
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 67202201 | NYC H+H--COLER HOSPITAL-FIRE ALARM UPGRADE: INSTALLATION OF | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Feb 2027 | Nov 2026 | Feb 2027
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 67202202 | COLER: COOLING TOWER REPLACEMENT | 1 | DESIGN | Jul 2022 | Nov 2023 | Jul 2024 | Nov 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 67202202 | COLER: COOLING TOWER REPLACEMENT | 2 | CONSTRUCTION | Nov 2023 | Nov 2026 | Nov 2025 | Nov 2028
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 67202202 | COLER: COOLING TOWER REPLACEMENT | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Feb 2027 | Nov 2028 | Feb 2029
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 67202401 | COLER HOSPITAL ATRIUM--RENOVATE DAMAGED 3RD FLOOR ATRIUM | 1 | DESIGN | May 2026 | Sep 2027 | May 2026 | Sep 2027
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 67202401 | COLER HOSPITAL ATRIUM--RENOVATE DAMAGED 3RD FLOOR ATRIUM | 2 | CONSTRUCTION | Sep 2027 | Sep 2029 | Sep 2027 | Sep 2029
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 67202401 | COLER HOSPITAL ATRIUM--RENOVATE DAMAGED 3RD FLOOR ATRIUM | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2029 | Jun 2034 | Sep 2029 | Jun 2034
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 67202402 | COLER UPGRADES TO ELECTRICAL PANELS | 1 | DESIGN | May 2026 | Sep 2027 | May 2024 | Sep 2027
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 67202402 | COLER UPGRADES TO ELECTRICAL PANELS | 2 | CONSTRUCTION | Sep 2027 | Sep 2029 | Sep 2027 | Sep 2029
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 67202402 | COLER UPGRADES TO ELECTRICAL PANELS | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2029 | Jun 2034 | Sep 2029 | Jun 2034
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 68202102 | CARTER: NEW CENTRALIZED BUILDING MANAGEMENT CONTROL SYSTEM | 1 | DESIGN | Jul 2021 | May 2022 | Jul 2021 | May 2022
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 68202102 | CARTER: NEW CENTRALIZED BUILDING MANAGEMENT CONTROL SYSTEM | 2 | CONSTRUCTION | May 2022 | May 2023 | Jul 2021 | May 2022
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 68202102 | CARTER: NEW CENTRALIZED BUILDING MANAGEMENT CONTROL SYSTEM | 3 | CONSTRUCTION | May 2022 | May 2023 | May 2022 | May 2023
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 68202103 | CARTER PHARMACY COMPOUNDING USP 797/800 COMPLIANCE | 1 | DESIGN | May 2020 | Sep 2021 | May 2025 | Jun 2032
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 68202103 | CARTER PHARMACY COMPOUNDING USP 797/800 COMPLIANCE | 2 | CONSTRUCTION | Sep 2021 | Sep 2023 | Jul 2032 | Jun 2034
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 68202103 | CARTER PHARMACY COMPOUNDING USP 797/800 COMPLIANCE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Dec 2023 | Jul 2034 | Sep 2034
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 68202201 | CARTER ROOF TANK REPLACEMENT | 1 | DESIGN | May 2021 | Sep 2022 | Mar 2022 | Jun 2032
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 68202201 | CARTER ROOF TANK REPLACEMENT | 2 | CONSTRUCTION | Sep 2022 | Sep 2024 | Jul 2032 | Jun 2034
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 68202201 | CARTER ROOF TANK REPLACEMENT | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Dec 2024 | Jul 2034 | Sep 2036
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 68202202 | CARTER FACADE REHABILITATION | 1 | DESIGN | Jul 2024 | Nov 2025 | Jul 2024 | Nov 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 68202202 | CARTER FACADE REHABILITATION | 2 | CONSTRUCTION | Nov 2025 | Nov 2028 | Nov 2025 | Nov 2028
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 68202202 | CARTER FACADE REHABILITATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2028 | Feb 2029 | Nov 2028 | Feb 2029
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC403 | HARLEM HOSPITAL CENTER ENERGY UPGRADE | 1 | DEVELOP SCOPE | Mar 2013 | Jun 2013 | Mar 2013 | Jun 2013
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC403 | HARLEM HOSPITAL CENTER ENERGY UPGRADE | 2 | PRELIMINARY DESIGN | Jun 2013 | Oct 2013 | Jun 2013 | Oct 2013
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC403 | HARLEM HOSPITAL CENTER ENERGY UPGRADE | 3 | FINAL DESIGN | Oct 2013 | Apr 2014 | Oct 2013 | Apr 2014
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC403 | HARLEM HOSPITAL CENTER ENERGY UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2014 | Jul 2014 | Apr 2014 | Jul 2014
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC403 | HARLEM HOSPITAL CENTER ENERGY UPGRADE | 5 | CONSTRUCTION TO 25% | Jul 2014 | Nov 2014 | Jul 2014 | Nov 2014
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC403 | HARLEM HOSPITAL CENTER ENERGY UPGRADE | 6 | CONSTRUCTION TO 50% | Nov 2014 | Mar 2015 | Nov 2014 | Mar 2015
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC403 | HARLEM HOSPITAL CENTER ENERGY UPGRADE | 7 | CONSTRUCTION TO 75% | Mar 2015 | Jul 2015 | Mar 2015 | Jul 2015
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC403 | HARLEM HOSPITAL CENTER ENERGY UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2015 | Oct 2015 | Jul 2015 | Oct 2015
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC403 | HARLEM HOSPITAL CENTER ENERGY UPGRADE | 9 | SUBSTANTIAL COMPLETION | Oct 2015 | Dec 2015 | Oct 2015 | Dec 2023
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC403 | HARLEM HOSPITAL CENTER ENERGY UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2015 | Dec 2015 | Dec 2023 | Dec 2023
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC406 | BELLEVUE HOSPITAL CHILLERS | 1 | DESIGN | Nov 2015 | Apr 2017 | Nov 2015 | Apr 2017
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC406 | BELLEVUE HOSPITAL CHILLERS | 2 | CONSTRUCTION | Apr 2017 | Apr 2020 | Apr 2017 | May 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC406 | BELLEVUE HOSPITAL CHILLERS | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2020 | Jun 2020 | May 2024 | Jul 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC408 | COLER BOILER REPLACEMENT | 1 | DESIGN | Nov 2016 | Apr 2018 | Nov 2018 | Apr 2020
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC408 | COLER BOILER REPLACEMENT | 2 | CONSTRUCTION | Apr 2018 | Apr 2020 | Apr 2020 | May 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC408 | COLER BOILER REPLACEMENT | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2020 | Jun 2020 | May 2025 | Jul 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC602 | BELLEVUE LIGHTING AND CONTROLS UPGRADE | 1 | DESIGN | Nov 2015 | Apr 2017 | Jul 2019 | Jun 2032
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC602 | BELLEVUE LIGHTING AND CONTROLS UPGRADE | 2 | CONSTRUCTION | Apr 2017 | Apr 2020 | Jul 2032 | Jul 2037
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC602 | BELLEVUE LIGHTING AND CONTROLS UPGRADE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2020 | Jun 2020 | Jul 2037 | Oct 2037
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | GOUV/MJR | GOUVERNEUR: MAJOR MODERNIZATION | 1 | DESIGN | Sep 2007 | Jan 2009 | Sep 2007 | Jan 2009
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | GOUV/MJR | GOUVERNEUR: MAJOR MODERNIZATION | 2 | CONSTRUCTION | Feb 2009 | Jan 2013 | Feb 2009 | Jan 2013
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | GOUV/MJR | GOUVERNEUR: MAJOR MODERNIZATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2013 | Apr 2013 | Jan 2013 | Apr 2013
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SAND1117 | BHC: MEP MITIGATION | 1 | DESIGN | Feb 2019 | Jan 2020 | Feb 2021 | Jan 2022
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SAND1117 | BHC: MEP MITIGATION | 2 | CONSTRUCTION | Jan 2020 | Dec 2020 | Feb 2021 | Jan 2022
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SAND1117 | BHC: MEP MITIGATION | 3 | CONSTRUCTION | Jan 2020 | Dec 2020 | Jan 2022 | Jun 2028
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SAND1121 | BHC: Elevate Security Systems | 1 | DESIGN | May 2020 | Sep 2021 | May 2024 | Sep 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SAND1121 | BHC: Elevate Security Systems | 2 | CONSTRUCTION | Sep 2021 | Sep 2023 | Sep 2025 | Sep 2027
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SAND1121 | BHC: Elevate Security Systems | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Dec 2023 | Sep 2027 | Dec 2027
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SAND3706 | MHC: INSTALL ELECTRIC AND CHILLER QUICK CONNECTS | 1 | DESIGN | May 2018 | Oct 2019 | May 2018 | Oct 2019
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SAND3706 | MHC: INSTALL ELECTRIC AND CHILLER QUICK CONNECTS | 2 | CONSTRUCTION | Oct 2019 | Oct 2021 | Oct 2019 | Oct 2021
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SAND3706 | MHC: INSTALL ELECTRIC AND CHILLER QUICK CONNECTS | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2021 | Dec 2021 | Oct 2021 | Jun 2026
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SANDCOFW | Coler Flood Mitigation | 1 | DESIGN | May 2022 | Nov 2022 | May 2025 | Nov 2025
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SANDCOFW | Coler Flood Mitigation | 2 | CONSTRUCTION | Nov 2022 | Apr 2023 | Nov 2025 | Mar 2028
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | TKYHHC013 | COLER: LIGHTING UPGRADE | 1 | DESIGN | Apr 2023 | Sep 2024 | Apr 2023 | Sep 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | TKYHHC013 | COLER: LIGHTING UPGRADE | 2 | CONSTRUCTION | Sep 2024 | Sep 2026 | Sep 2024 | Sep 2026
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | TKYHHC013 | COLER: LIGHTING UPGRADE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Dec 2026 | Sep 2026 | Dec 2026
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | TKYHHC903 | BELLEVUE COMBINED HEAT AND POWER (CHP) | 1 | DESIGN | May 2021 | Sep 2022 | May 2021 | Sep 2022
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | TKYHHC903 | BELLEVUE COMBINED HEAT AND POWER (CHP) | 2 | CONSTRUCTION | Sep 2022 | Sep 2024 | Sep 2022 | Sep 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | TKYHHC903 | BELLEVUE COMBINED HEAT AND POWER (CHP) | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | TKYHHC904 | HARLEM BOILER PLANT REPLACEMENT AND COMBINED HEAT AND POWER | 1 | DESIGN | May 2021 | Sep 2022 | May 2021 | Sep 2022
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | TKYHHC904 | HARLEM BOILER PLANT REPLACEMENT AND COMBINED HEAT AND POWER | 2 | CONSTRUCTION | Sep 2022 | Sep 2024 | Sep 2022 | Sep 2024
20231026 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | TKYHHC904 | HARLEM BOILER PLANT REPLACEMENT AND COMBINED HEAT AND POWER | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Dec 2025 | Sep 2024 | Dec 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP502 | DEP - WARDS ISLAND SHAFT MIXERS | 1 | DEVELOP SCOPE | Jun 2015 | Aug 2015 | Jun 2015 | Feb 2016
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP502 | DEP - WARDS ISLAND SHAFT MIXERS | 2 | PRELIMINARY DESIGN | Aug 2015 | Dec 2015 | Feb 2016 | Feb 2017
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP502 | DEP - WARDS ISLAND SHAFT MIXERS | 3 | FINAL DESIGN | Dec 2015 | Jun 2016 | Feb 2017 | Aug 2018
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP502 | DEP - WARDS ISLAND SHAFT MIXERS | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2016 | Sep 2016 | Aug 2018 | May 2019
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP502 | DEP - WARDS ISLAND SHAFT MIXERS | 5 | CONSTRUCTION TO 25% | Sep 2016 | Jan 2017 | May 2019 | May 2020
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP502 | DEP - WARDS ISLAND SHAFT MIXERS | 6 | CONSTRUCTION TO 50% | Jan 2017 | May 2017 | May 2020 | Apr 2021
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP502 | DEP - WARDS ISLAND SHAFT MIXERS | 7 | CONSTRUCTION TO 75% | May 2017 | Sep 2017 | Apr 2021 | Apr 2022
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP502 | DEP - WARDS ISLAND SHAFT MIXERS | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Dec 2017 | Apr 2022 | Jan 2023
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP502 | DEP - WARDS ISLAND SHAFT MIXERS | 9 | SUBSTANTIAL COMPLETION | Dec 2017 | Feb 2018 | Jan 2023 | Jul 2023
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP502 | DEP - WARDS ISLAND SHAFT MIXERS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2018 | Mar 2018 | Jul 2023 | Oct 2023
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC25M | Emergency Sewer Lining Contract, Manhattan | 1 | DEVELOP SCOPE | Jan 2023 | Apr 2023 | Jan 2023 | Apr 2023
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC25M | Emergency Sewer Lining Contract, Manhattan | 2 | PRELIMINARY DESIGN | Apr 2023 | Aug 2023 | Apr 2023 | Aug 2023
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC25M | Emergency Sewer Lining Contract, Manhattan | 3 | FINAL DESIGN | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC25M | Emergency Sewer Lining Contract, Manhattan | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2024 | May 2024 | Feb 2024 | May 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC25M | Emergency Sewer Lining Contract, Manhattan | 5 | CONSTRUCTION TO 25% | May 2024 | Aug 2024 | May 2024 | Aug 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC25M | Emergency Sewer Lining Contract, Manhattan | 6 | CONSTRUCTION TO 50% | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC25M | Emergency Sewer Lining Contract, Manhattan | 7 | CONSTRUCTION TO 75% | Dec 2024 | Apr 2025 | Dec 2024 | Apr 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC25M | Emergency Sewer Lining Contract, Manhattan | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2025 | Jul 2025 | Apr 2025 | Jul 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC25M | Emergency Sewer Lining Contract, Manhattan | 9 | SUBSTANTIAL COMPLETION | Jul 2025 | Sep 2025 | Jul 2025 | Sep 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC25M | Emergency Sewer Lining Contract, Manhattan | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Oct 2025 | Sep 2025 | Oct 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED677 | WM work in 10th Ave, Union Sq E, FDR Drive, MN | 1 | DEVELOP SCOPE | Jan 2026 | Mar 2026 | Jun 2024 | Aug 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED677 | WM work in 10th Ave, Union Sq E, FDR Drive, MN | 2 | PRELIMINARY DESIGN | Apr 2026 | Jul 2026 | Aug 2024 | Dec 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED677 | WM work in 10th Ave, Union Sq E, FDR Drive, MN | 3 | FINAL DESIGN | Jul 2026 | Jan 2027 | Dec 2024 | Jun 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED677 | WM work in 10th Ave, Union Sq E, FDR Drive, MN | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2027 | Apr 2027 | Jun 2025 | Sep 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED677 | WM work in 10th Ave, Union Sq E, FDR Drive, MN | 5 | CONSTRUCTION TO 25% | Apr 2027 | Aug 2027 | Sep 2025 | Jan 2026
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED677 | WM work in 10th Ave, Union Sq E, FDR Drive, MN | 6 | CONSTRUCTION TO 50% | Aug 2027 | Dec 2027 | Jan 2026 | May 2026
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED677 | WM work in 10th Ave, Union Sq E, FDR Drive, MN | 7 | CONSTRUCTION TO 75% | Dec 2027 | Apr 2028 | May 2026 | Sep 2026
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED677 | WM work in 10th Ave, Union Sq E, FDR Drive, MN | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2028 | Jul 2028 | Sep 2026 | Dec 2026
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED677 | WM work in 10th Ave, Union Sq E, FDR Drive, MN | 9 | SUBSTANTIAL COMPLETION | Jul 2028 | Sep 2028 | Dec 2026 | Feb 2027
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED677 | WM work in 10th Ave, Union Sq E, FDR Drive, MN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2028 | Oct 2028 | Feb 2027 | Mar 2027
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED680 | Dist & Trunk WM in Broadway btwn W 60 ST & W 64 ST, MN | 1 | DEVELOP SCOPE | Jan 2025 | Mar 2025 | Jun 2024 | Aug 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED680 | Dist & Trunk WM in Broadway btwn W 60 ST & W 64 ST, MN | 2 | PRELIMINARY DESIGN | Apr 2025 | Jul 2025 | Aug 2024 | Dec 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED680 | Dist & Trunk WM in Broadway btwn W 60 ST & W 64 ST, MN | 3 | FINAL DESIGN | Jul 2025 | Jan 2026 | Dec 2024 | Jun 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED680 | Dist & Trunk WM in Broadway btwn W 60 ST & W 64 ST, MN | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2026 | Apr 2026 | Jun 2025 | Sep 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED680 | Dist & Trunk WM in Broadway btwn W 60 ST & W 64 ST, MN | 5 | CONSTRUCTION TO 25% | Apr 2026 | Aug 2026 | Sep 2025 | Jan 2026
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED680 | Dist & Trunk WM in Broadway btwn W 60 ST & W 64 ST, MN | 6 | CONSTRUCTION TO 50% | Aug 2026 | Dec 2026 | Jan 2026 | May 2026
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED680 | Dist & Trunk WM in Broadway btwn W 60 ST & W 64 ST, MN | 7 | CONSTRUCTION TO 75% | Dec 2026 | Apr 2027 | May 2026 | Sep 2026
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED680 | Dist & Trunk WM in Broadway btwn W 60 ST & W 64 ST, MN | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2027 | Jul 2027 | Sep 2026 | Dec 2026
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED680 | Dist & Trunk WM in Broadway btwn W 60 ST & W 64 ST, MN | 9 | SUBSTANTIAL COMPLETION | Jul 2027 | Sep 2027 | Dec 2026 | Feb 2027
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED680 | Dist & Trunk WM in Broadway btwn W 60 ST & W 64 ST, MN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Oct 2027 | Feb 2027 | Mar 2027
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED681 | Dist WM work in W 34 St from 7th to 9th Ave, MN | 1 | DEVELOP SCOPE | Jan 2026 | Mar 2026 | Jun 2024 | Aug 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED681 | Dist WM work in W 34 St from 7th to 9th Ave, MN | 2 | PRELIMINARY DESIGN | Apr 2026 | Jul 2026 | Aug 2024 | Dec 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED681 | Dist WM work in W 34 St from 7th to 9th Ave, MN | 3 | FINAL DESIGN | Jul 2026 | Jan 2027 | Dec 2024 | Jun 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED681 | Dist WM work in W 34 St from 7th to 9th Ave, MN | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2027 | Apr 2027 | Jun 2025 | Sep 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED681 | Dist WM work in W 34 St from 7th to 9th Ave, MN | 5 | CONSTRUCTION TO 25% | Apr 2027 | Aug 2027 | Sep 2025 | Jan 2026
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED681 | Dist WM work in W 34 St from 7th to 9th Ave, MN | 6 | CONSTRUCTION TO 50% | Aug 2027 | Dec 2027 | Jan 2026 | May 2026
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED681 | Dist WM work in W 34 St from 7th to 9th Ave, MN | 7 | CONSTRUCTION TO 75% | Dec 2027 | Apr 2028 | May 2026 | Sep 2026
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED681 | Dist WM work in W 34 St from 7th to 9th Ave, MN | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2028 | Jul 2028 | Sep 2026 | Dec 2026
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED681 | Dist WM work in W 34 St from 7th to 9th Ave, MN | 9 | SUBSTANTIAL COMPLETION | Jul 2028 | Sep 2028 | Dec 2026 | Feb 2027
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED681 | Dist WM work in W 34 St from 7th to 9th Ave, MN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2028 | Oct 2028 | Feb 2027 | Mar 2027
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-111-L | RECONSTRUCTION OF PRIMARY TANKS AT NORTH RIVER WPCP | 1 | DEVELOP SCOPE | Mar 2018 | May 2018 | Jun 2018 | Feb 2019
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-111-L | RECONSTRUCTION OF PRIMARY TANKS AT NORTH RIVER WPCP | 2 | PRELIMINARY DESIGN | May 2018 | Sep 2018 | Feb 2019 | Feb 2020
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-111-L | RECONSTRUCTION OF PRIMARY TANKS AT NORTH RIVER WPCP | 3 | FINAL DESIGN | Sep 2018 | Mar 2019 | Feb 2020 | Aug 2021
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-111-L | RECONSTRUCTION OF PRIMARY TANKS AT NORTH RIVER WPCP | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2019 | Jun 2019 | Aug 2021 | May 2022
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-111-L | RECONSTRUCTION OF PRIMARY TANKS AT NORTH RIVER WPCP | 5 | CONSTRUCTION TO 25% | Jun 2019 | Oct 2019 | May 2022 | May 2023
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-111-L | RECONSTRUCTION OF PRIMARY TANKS AT NORTH RIVER WPCP | 6 | CONSTRUCTION TO 50% | Oct 2019 | Feb 2020 | May 2023 | Apr 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-111-L | RECONSTRUCTION OF PRIMARY TANKS AT NORTH RIVER WPCP | 7 | CONSTRUCTION TO 75% | Feb 2020 | Jun 2020 | Apr 2024 | Apr 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-111-L | RECONSTRUCTION OF PRIMARY TANKS AT NORTH RIVER WPCP | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2020 | Sep 2020 | Apr 2025 | Jan 2026
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-111-L | RECONSTRUCTION OF PRIMARY TANKS AT NORTH RIVER WPCP | 9 | SUBSTANTIAL COMPLETION | Sep 2020 | Nov 2020 | Jan 2026 | Jul 2034
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-111-L | RECONSTRUCTION OF PRIMARY TANKS AT NORTH RIVER WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2020 | Dec 2020 | Jul 2034 | Oct 2034
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-B | RECONS POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP PH B | 1 | DEVELOP SCOPE | Jun 2020 | Feb 2021 | Jun 2020 | Feb 2021
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-B | RECONS POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP PH B | 2 | PRELIMINARY DESIGN | Feb 2021 | Feb 2022 | Feb 2021 | Feb 2022
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-B | RECONS POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP PH B | 3 | FINAL DESIGN | Feb 2022 | Aug 2023 | Feb 2022 | Aug 2023
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-B | RECONS POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP PH B | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2023 | May 2024 | Aug 2023 | May 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-B | RECONS POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP PH B | 5 | CONSTRUCTION TO 25% | May 2024 | May 2025 | May 2024 | May 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-B | RECONS POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP PH B | 6 | CONSTRUCTION TO 50% | May 2025 | Apr 2026 | May 2025 | Apr 2026
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-B | RECONS POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP PH B | 7 | CONSTRUCTION TO 75% | May 2026 | Apr 2027 | May 2026 | Apr 2027
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-B | RECONS POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP PH B | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2027 | Jan 2028 | Apr 2027 | Jan 2028
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-B | RECONS POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP PH B | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Jul 2032 | Jan 2028 | Jul 2032
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-B | RECONS POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP PH B | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2032 | Oct 2032 | Jul 2032 | Oct 2032
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP | 1 | DEVELOP SCOPE | Jul 2017 | Mar 2018 | Jul 2017 | Mar 2018
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP | 2 | PRELIMINARY DESIGN | Mar 2018 | Mar 2019 | Mar 2018 | Mar 2019
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP | 3 | FINAL DESIGN | Mar 2019 | Sep 2020 | Mar 2019 | Sep 2020
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2020 | Jun 2021 | Sep 2020 | Jun 2021
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP | 5 | CONSTRUCTION TO 25% | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP | 6 | CONSTRUCTION TO 50% | Jun 2022 | May 2023 | Jun 2022 | May 2023
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP | 7 | CONSTRUCTION TO 75% | May 2023 | May 2024 | May 2023 | May 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP | 8 | ORIGINAL EQUIP & FURNISHING | May 2024 | Feb 2025 | May 2024 | Feb 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP | 9 | SUBSTANTIAL COMPLETION | Feb 2025 | Aug 2025 | Feb 2025 | Aug 2029
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2025 | Nov 2025 | Aug 2029 | Nov 2029
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-117-L | RECONST OF FIRE PROTECTION SYSTEM @ THE NORTH RIVER WWTP | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Feb 2023
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-117-L | RECONST OF FIRE PROTECTION SYSTEM @ THE NORTH RIVER WWTP | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Feb 2023 | Feb 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-117-L | RECONST OF FIRE PROTECTION SYSTEM @ THE NORTH RIVER WWTP | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Feb 2024 | Aug 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-117-L | RECONST OF FIRE PROTECTION SYSTEM @ THE NORTH RIVER WWTP | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Aug 2025 | May 2026
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-117-L | RECONST OF FIRE PROTECTION SYSTEM @ THE NORTH RIVER WWTP | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | May 2026 | May 2027
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-117-L | RECONST OF FIRE PROTECTION SYSTEM @ THE NORTH RIVER WWTP | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | May 2027 | Apr 2028
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-117-L | RECONST OF FIRE PROTECTION SYSTEM @ THE NORTH RIVER WWTP | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | Apr 2028 | Apr 2029
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-117-L | RECONST OF FIRE PROTECTION SYSTEM @ THE NORTH RIVER WWTP | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Apr 2029 | Jan 2030
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-117-L | RECONST OF FIRE PROTECTION SYSTEM @ THE NORTH RIVER WWTP | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Jan 2030 | Jul 2030
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-117-L | RECONST OF FIRE PROTECTION SYSTEM @ THE NORTH RIVER WWTP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Mar 2025 | Jul 2030 | Oct 2030
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-124 | Installation of Gas Conditioning System at North River WRRF | 1 | FINAL DESIGN | Jun 2022 | Dec 2023 | Jun 2024 | Mar 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-124 | Installation of Gas Conditioning System at North River WRRF | 2 | CONSTRUCTION TO 25% | Dec 2023 | Aug 2024 | Mar 2025 | Mar 2026
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-124 | Installation of Gas Conditioning System at North River WRRF | 3 | CONSTRUCTION TO 50% | Aug 2024 | Mar 2025 | Mar 2026 | Aug 2027
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-124 | Installation of Gas Conditioning System at North River WRRF | 4 | CONSTRUCTION TO 75% | Mar 2025 | Nov 2025 | Aug 2027 | May 2028
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-124 | Installation of Gas Conditioning System at North River WRRF | 5 | CONSTRUCTION TO 25% | Mar 2025 | Nov 2025 | May 2028 | May 2029
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-124 | Installation of Gas Conditioning System at North River WRRF | 6 | CONSTRUCTION TO 50% | Mar 2025 | Nov 2025 | May 2029 | May 2030
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-124 | Installation of Gas Conditioning System at North River WRRF | 7 | CONSTRUCTION TO 75% | Mar 2025 | Nov 2025 | May 2030 | May 2031
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-124 | Installation of Gas Conditioning System at North River WRRF | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2025 | Nov 2025 | May 2031 | Feb 2032
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-124 | Installation of Gas Conditioning System at North River WRRF | 9 | SUBSTANTIAL COMPLETION | Mar 2025 | Nov 2025 | Feb 2032 | Aug 2032
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-124 | Installation of Gas Conditioning System at North River WRRF | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Nov 2025 | Aug 2032 | Oct 2032
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-129 | RECONS MAIN SEWAGE PUMPS & PIPING/VALVES AT NORTH RIVER WPCP | 1 | FINAL DESIGN | Jun 2022 | Nov 2023 | Jun 2022 | Nov 2023
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-129 | RECONS MAIN SEWAGE PUMPS & PIPING/VALVES AT NORTH RIVER WPCP | 2 | CONSTRUCTION TO 25% | Nov 2023 | Jul 2024 | Nov 2023 | Jul 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-129 | RECONS MAIN SEWAGE PUMPS & PIPING/VALVES AT NORTH RIVER WPCP | 3 | CONSTRUCTION TO 50% | Jul 2024 | Mar 2025 | Jul 2024 | Mar 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-129 | RECONS MAIN SEWAGE PUMPS & PIPING/VALVES AT NORTH RIVER WPCP | 4 | CONSTRUCTION TO 75% | Mar 2025 | Nov 2025 | Mar 2025 | Nov 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-141-L | RECONS (16) FINAL TANKS MECH, ELECT & STRUC WK@ NORTH RIVER | 1 | FINAL DESIGN | Jun 2025 | Nov 2026 | Jun 2025 | Nov 2026
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-141-L | RECONS (16) FINAL TANKS MECH, ELECT & STRUC WK@ NORTH RIVER | 2 | CONSTRUCTION TO 25% | Nov 2026 | Jul 2027 | Nov 2026 | Jul 2027
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-141-L | RECONS (16) FINAL TANKS MECH, ELECT & STRUC WK@ NORTH RIVER | 3 | CONSTRUCTION TO 50% | Jul 2027 | Mar 2028 | Jul 2027 | Mar 2028
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-141-L | RECONS (16) FINAL TANKS MECH, ELECT & STRUC WK@ NORTH RIVER | 4 | CONSTRUCTION TO 75% | Mar 2028 | Nov 2028 | Mar 2028 | Nov 2028
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-CH2O | FORMALDEHYDE MITIGATION @ NORTH RIVER WRRF | 1 | DEVELOP SCOPE | Jun 2022 | Feb 2023 | Jun 2022 | Feb 2023
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-CH2O | FORMALDEHYDE MITIGATION @ NORTH RIVER WRRF | 2 | PRELIMINARY DESIGN | Feb 2023 | Feb 2024 | Feb 2023 | Feb 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-CH2O | FORMALDEHYDE MITIGATION @ NORTH RIVER WRRF | 3 | FINAL DESIGN | Feb 2024 | Aug 2025 | Feb 2024 | Aug 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-CH2O | FORMALDEHYDE MITIGATION @ NORTH RIVER WRRF | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2025 | May 2026 | Aug 2025 | May 2026
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-CH2O | FORMALDEHYDE MITIGATION @ NORTH RIVER WRRF | 5 | CONSTRUCTION TO 25% | May 2026 | May 2027 | May 2026 | May 2027
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-CH2O | FORMALDEHYDE MITIGATION @ NORTH RIVER WRRF | 6 | CONSTRUCTION TO 50% | May 2027 | Apr 2028 | May 2027 | Apr 2028
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-CH2O | FORMALDEHYDE MITIGATION @ NORTH RIVER WRRF | 7 | CONSTRUCTION TO 75% | Apr 2028 | Apr 2029 | Apr 2028 | Apr 2029
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-CH2O | FORMALDEHYDE MITIGATION @ NORTH RIVER WRRF | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2029 | Jan 2030 | Apr 2029 | Jan 2030
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-CH2O | FORMALDEHYDE MITIGATION @ NORTH RIVER WRRF | 9 | SUBSTANTIAL COMPLETION | Jan 2030 | Jul 2030 | Jan 2030 | Jul 2030
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-CH2O | FORMALDEHYDE MITIGATION @ NORTH RIVER WRRF | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2030 | Oct 2030 | Jul 2030 | Oct 2030
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-COGEN | NORTH RIVER WWTP COGENERATION AND ELECTRIFICATION | 1 | DEVELOP SCOPE | Jun 2013 | Mar 2014 | Jun 2013 | Mar 2014
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-COGEN | NORTH RIVER WWTP COGENERATION AND ELECTRIFICATION | 2 | PRELIMINARY DESIGN | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2015
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-COGEN | NORTH RIVER WWTP COGENERATION AND ELECTRIFICATION | 3 | FINAL DESIGN | Mar 2015 | Sep 2016 | Mar 2015 | Sep 2016
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-COGEN | NORTH RIVER WWTP COGENERATION AND ELECTRIFICATION | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2016 | Jun 2017 | Sep 2016 | Jun 2017
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-COGEN | NORTH RIVER WWTP COGENERATION AND ELECTRIFICATION | 5 | CONSTRUCTION TO 25% | Jun 2017 | Jun 2018 | Jun 2017 | Jun 2018
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-COGEN | NORTH RIVER WWTP COGENERATION AND ELECTRIFICATION | 6 | CONSTRUCTION TO 50% | Jun 2018 | May 2019 | Jun 2018 | May 2019
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-COGEN | NORTH RIVER WWTP COGENERATION AND ELECTRIFICATION | 7 | CONSTRUCTION TO 75% | May 2019 | May 2020 | May 2019 | May 2020
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-COGEN | NORTH RIVER WWTP COGENERATION AND ELECTRIFICATION | 8 | ORIGINAL EQUIP & FURNISHING | May 2020 | Feb 2021 | May 2020 | Feb 2021
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-COGEN | NORTH RIVER WWTP COGENERATION AND ELECTRIFICATION | 9 | SUBSTANTIAL COMPLETION | Feb 2021 | Aug 2021 | Feb 2021 | Aug 2029
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-COGEN | NORTH RIVER WWTP COGENERATION AND ELECTRIFICATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Nov 2021 | Aug 2029 | Nov 2029
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-GBT-L | INSTALLATION OF GRAVITY BELT THICKENERS @ NR WRRF | 1 | DEVELOP SCOPE | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-GBT-L | INSTALLATION OF GRAVITY BELT THICKENERS @ NR WRRF | 2 | PRELIMINARY DESIGN | Mar 2025 | Mar 2026 | Mar 2025 | Mar 2026
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-GBT-L | INSTALLATION OF GRAVITY BELT THICKENERS @ NR WRRF | 3 | FINAL DESIGN | Mar 2026 | Aug 2027 | Mar 2026 | Aug 2027
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-GBT-L | INSTALLATION OF GRAVITY BELT THICKENERS @ NR WRRF | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2027 | May 2028 | Aug 2027 | May 2028
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-GBT-L | INSTALLATION OF GRAVITY BELT THICKENERS @ NR WRRF | 5 | CONSTRUCTION TO 25% | May 2028 | May 2029 | May 2028 | May 2029
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-GBT-L | INSTALLATION OF GRAVITY BELT THICKENERS @ NR WRRF | 6 | CONSTRUCTION TO 50% | May 2029 | May 2030 | May 2029 | May 2030
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-GBT-L | INSTALLATION OF GRAVITY BELT THICKENERS @ NR WRRF | 7 | CONSTRUCTION TO 75% | May 2030 | May 2031 | May 2030 | May 2031
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-GBT-L | INSTALLATION OF GRAVITY BELT THICKENERS @ NR WRRF | 8 | ORIGINAL EQUIP & FURNISHING | May 2031 | Feb 2032 | May 2031 | Feb 2032
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-GBT-L | INSTALLATION OF GRAVITY BELT THICKENERS @ NR WRRF | 9 | SUBSTANTIAL COMPLETION | Feb 2032 | Aug 2032 | Feb 2032 | Aug 2032
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-GBT-L | INSTALLATION OF GRAVITY BELT THICKENERS @ NR WRRF | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2032 | Oct 2032 | Aug 2032 | Oct 2032
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-STRUCT | STRUCTURAL IMPROVEMENTS AT NORTH RIVER WPCP | 1 | DEVELOP SCOPE | Jun 2017 | Feb 2018 | Jun 2020 | Feb 2021
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-STRUCT | STRUCTURAL IMPROVEMENTS AT NORTH RIVER WPCP | 2 | PRELIMINARY DESIGN | Feb 2018 | Feb 2019 | Feb 2021 | Feb 2022
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-STRUCT | STRUCTURAL IMPROVEMENTS AT NORTH RIVER WPCP | 3 | FINAL DESIGN | Feb 2019 | Aug 2020 | Feb 2022 | Aug 2023
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-STRUCT | STRUCTURAL IMPROVEMENTS AT NORTH RIVER WPCP | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2020 | May 2021 | Aug 2023 | May 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-STRUCT | STRUCTURAL IMPROVEMENTS AT NORTH RIVER WPCP | 5 | CONSTRUCTION TO 25% | May 2021 | May 2022 | May 2024 | May 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-STRUCT | STRUCTURAL IMPROVEMENTS AT NORTH RIVER WPCP | 6 | CONSTRUCTION TO 50% | May 2022 | Apr 2023 | May 2025 | Apr 2026
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-STRUCT | STRUCTURAL IMPROVEMENTS AT NORTH RIVER WPCP | 7 | CONSTRUCTION TO 75% | May 2023 | Apr 2024 | May 2026 | Apr 2027
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-STRUCT | STRUCTURAL IMPROVEMENTS AT NORTH RIVER WPCP | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2024 | Jan 2025 | Apr 2027 | Jan 2028
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-STRUCT | STRUCTURAL IMPROVEMENTS AT NORTH RIVER WPCP | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Jul 2025 | Jan 2028 | Jul 2032
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-STRUCT | STRUCTURAL IMPROVEMENTS AT NORTH RIVER WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Oct 2025 | Jul 2032 | Oct 2032
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-278 | PARK DRIVE EAST | 1 | DEVELOP SCOPE | Jul 2016 | Mar 2017 | Jul 2016 | Mar 2017
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-278 | PARK DRIVE EAST | 2 | PRELIMINARY DESIGN | Mar 2017 | Mar 2018 | Mar 2017 | Mar 2018
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-278 | PARK DRIVE EAST | 3 | FINAL DESIGN | Mar 2018 | Sep 2019 | Mar 2018 | Sep 2019
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-278 | PARK DRIVE EAST | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Jun 2020 | Sep 2019 | Jun 2020
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-278 | PARK DRIVE EAST | 5 | CONSTRUCTION TO 25% | Jun 2020 | Jun 2021 | Jun 2020 | Jun 2021
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-278 | PARK DRIVE EAST | 6 | CONSTRUCTION TO 50% | Jun 2021 | May 2022 | Jun 2021 | May 2022
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-278 | PARK DRIVE EAST | 7 | CONSTRUCTION TO 75% | May 2022 | May 2023 | May 2022 | May 2023
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-278 | PARK DRIVE EAST | 8 | ORIGINAL EQUIP & FURNISHING | May 2023 | Feb 2024 | May 2023 | Feb 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-278 | PARK DRIVE EAST | 9 | SUBSTANTIAL COMPLETION | Feb 2024 | Aug 2024 | Feb 2024 | Aug 2028
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-278 | PARK DRIVE EAST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2024 | Nov 2024 | Aug 2028 | Nov 2028
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-289 | 19TH STREET PUMPING STATION | 1 | DEVELOP SCOPE | Jun 2020 | Feb 2021 | Jun 2020 | Feb 2021
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-289 | 19TH STREET PUMPING STATION | 2 | PRELIMINARY DESIGN | Feb 2021 | Feb 2022 | Feb 2021 | Feb 2022
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-289 | 19TH STREET PUMPING STATION | 3 | FINAL DESIGN | Feb 2022 | Aug 2023 | Feb 2022 | Aug 2023
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-289 | 19TH STREET PUMPING STATION | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2023 | May 2024 | Aug 2023 | May 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-289 | 19TH STREET PUMPING STATION | 5 | CONSTRUCTION TO 25% | May 2024 | May 2025 | May 2024 | May 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-289 | 19TH STREET PUMPING STATION | 6 | CONSTRUCTION TO 50% | May 2025 | Apr 2026 | May 2025 | Apr 2026
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-289 | 19TH STREET PUMPING STATION | 7 | CONSTRUCTION TO 75% | May 2026 | Apr 2027 | May 2026 | Apr 2027
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-289 | 19TH STREET PUMPING STATION | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2027 | Jan 2028 | Apr 2027 | Jan 2028
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-289 | 19TH STREET PUMPING STATION | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Jul 2028 | Jan 2028 | Jul 2028
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-289 | 19TH STREET PUMPING STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2028 | Oct 2028 | Jul 2028 | Oct 2028
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-324 | RECONSTRUCTION OF CANAL STREET PUMPING STATION, MANHATTAN | 1 | DEVELOP SCOPE | Jun 2022 | Feb 2023 | Jul 2018 | Mar 2019
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-324 | RECONSTRUCTION OF CANAL STREET PUMPING STATION, MANHATTAN | 2 | PRELIMINARY DESIGN | Feb 2023 | Feb 2024 | Mar 2019 | Mar 2020
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-324 | RECONSTRUCTION OF CANAL STREET PUMPING STATION, MANHATTAN | 3 | FINAL DESIGN | Feb 2024 | Aug 2025 | Mar 2020 | Sep 2021
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-324 | RECONSTRUCTION OF CANAL STREET PUMPING STATION, MANHATTAN | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2025 | May 2026 | Sep 2021 | Jun 2022
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-324 | RECONSTRUCTION OF CANAL STREET PUMPING STATION, MANHATTAN | 5 | CONSTRUCTION TO 25% | May 2026 | May 2027 | Jun 2022 | Jun 2023
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-324 | RECONSTRUCTION OF CANAL STREET PUMPING STATION, MANHATTAN | 6 | CONSTRUCTION TO 50% | May 2027 | Apr 2028 | Jun 2023 | May 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-324 | RECONSTRUCTION OF CANAL STREET PUMPING STATION, MANHATTAN | 7 | CONSTRUCTION TO 75% | Apr 2028 | Apr 2029 | May 2024 | May 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-324 | RECONSTRUCTION OF CANAL STREET PUMPING STATION, MANHATTAN | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2029 | Jan 2030 | May 2025 | Feb 2026
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-324 | RECONSTRUCTION OF CANAL STREET PUMPING STATION, MANHATTAN | 9 | SUBSTANTIAL COMPLETION | Jan 2030 | Jul 2030 | Feb 2026 | Aug 2026
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-324 | RECONSTRUCTION OF CANAL STREET PUMPING STATION, MANHATTAN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2030 | Oct 2030 | Aug 2026 | Nov 2026
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-348 | REHABILITATION OF DAMAGED NORTH RIVER INTERCEPTOR | 1 | FINAL DESIGN | Jun 2021 | Nov 2022 | Jun 2021 | Nov 2022
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-348 | REHABILITATION OF DAMAGED NORTH RIVER INTERCEPTOR | 2 | CONSTRUCTION TO 25% | Nov 2022 | Jul 2023 | Nov 2022 | Jul 2023
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-348 | REHABILITATION OF DAMAGED NORTH RIVER INTERCEPTOR | 3 | CONSTRUCTION TO 50% | Jul 2023 | Mar 2024 | Jul 2023 | Mar 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-348 | REHABILITATION OF DAMAGED NORTH RIVER INTERCEPTOR | 4 | CONSTRUCTION TO 75% | Mar 2024 | Nov 2024 | Mar 2024 | Nov 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDNR | STORM MITIGATION WORK ATTHE NORTH RIVER WPCP | 1 | DEVELOP SCOPE | Jun 2014 | Feb 2015 | Jun 2014 | Mar 2015
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDNR | STORM MITIGATION WORK ATTHE NORTH RIVER WPCP | 2 | PRELIMINARY DESIGN | Feb 2015 | Feb 2016 | Mar 2015 | Mar 2016
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDNR | STORM MITIGATION WORK ATTHE NORTH RIVER WPCP | 3 | FINAL DESIGN | Feb 2016 | Aug 2017 | Mar 2016 | Sep 2017
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDNR | STORM MITIGATION WORK ATTHE NORTH RIVER WPCP | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2017 | May 2018 | Sep 2017 | Jun 2018
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDNR | STORM MITIGATION WORK ATTHE NORTH RIVER WPCP | 5 | CONSTRUCTION TO 25% | May 2018 | May 2019 | Jun 2018 | Jun 2019
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDNR | STORM MITIGATION WORK ATTHE NORTH RIVER WPCP | 6 | CONSTRUCTION TO 50% | May 2019 | Apr 2020 | Jun 2019 | May 2020
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDNR | STORM MITIGATION WORK ATTHE NORTH RIVER WPCP | 7 | CONSTRUCTION TO 75% | Apr 2020 | Apr 2021 | May 2020 | May 2021
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDNR | STORM MITIGATION WORK ATTHE NORTH RIVER WPCP | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2021 | Jan 2022 | May 2021 | Feb 2022
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDNR | STORM MITIGATION WORK ATTHE NORTH RIVER WPCP | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Jul 2022 | Feb 2022 | Aug 2030
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDNR | STORM MITIGATION WORK ATTHE NORTH RIVER WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2022 | Oct 2022 | Aug 2030 | Nov 2030
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002183 | Installation of new Comb. SE at 12 Ave btwn W134 & 138 St MN | 1 | DEVELOP SCOPE | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002183 | Installation of new Comb. SE at 12 Ave btwn W134 & 138 St MN | 2 | PRELIMINARY DESIGN | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002183 | Installation of new Comb. SE at 12 Ave btwn W134 & 138 St MN | 3 | FINAL DESIGN | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002183 | Installation of new Comb. SE at 12 Ave btwn W134 & 138 St MN | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2024 | Feb 2025 | Nov 2024 | Feb 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002183 | Installation of new Comb. SE at 12 Ave btwn W134 & 138 St MN | 5 | CONSTRUCTION TO 25% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002183 | Installation of new Comb. SE at 12 Ave btwn W134 & 138 St MN | 6 | CONSTRUCTION TO 50% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002183 | Installation of new Comb. SE at 12 Ave btwn W134 & 138 St MN | 7 | CONSTRUCTION TO 75% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002183 | Installation of new Comb. SE at 12 Ave btwn W134 & 138 St MN | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2026 | May 2026 | Feb 2026 | May 2026
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002183 | Installation of new Comb. SE at 12 Ave btwn W134 & 138 St MN | 9 | SUBSTANTIAL COMPLETION | May 2026 | Jul 2026 | May 2026 | Jul 2026
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002183 | Installation of new Comb. SE at 12 Ave btwn W134 & 138 St MN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2026 | Aug 2026 | Jul 2026 | Aug 2026
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002184 | Replmt Combined SE & WM btwn E 125 St & E 128 St MN | 1 | DEVELOP SCOPE | Oct 2023 | Jul 2024 | Oct 2023 | Jul 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002184 | Replmt Combined SE & WM btwn E 125 St & E 128 St MN | 2 | PRELIMINARY DESIGN | Jul 2024 | Jul 2025 | Jul 2024 | Jul 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002184 | Replmt Combined SE & WM btwn E 125 St & E 128 St MN | 3 | FINAL DESIGN | Jul 2025 | Jan 2027 | Jul 2025 | Jan 2027
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002184 | Replmt Combined SE & WM btwn E 125 St & E 128 St MN | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2027 | Sep 2027 | Jan 2027 | Sep 2027
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002184 | Replmt Combined SE & WM btwn E 125 St & E 128 St MN | 5 | CONSTRUCTION TO 25% | Sep 2027 | Sep 2028 | Sep 2027 | Sep 2028
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002184 | Replmt Combined SE & WM btwn E 125 St & E 128 St MN | 6 | CONSTRUCTION TO 50% | Sep 2028 | Sep 2029 | Sep 2028 | Sep 2029
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002184 | Replmt Combined SE & WM btwn E 125 St & E 128 St MN | 7 | CONSTRUCTION TO 75% | Sep 2029 | Sep 2030 | Sep 2029 | Sep 2030
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002184 | Replmt Combined SE & WM btwn E 125 St & E 128 St MN | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2030 | Jun 2031 | Sep 2030 | Jun 2031
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002184 | Replmt Combined SE & WM btwn E 125 St & E 128 St MN | 9 | SUBSTANTIAL COMPLETION | Jun 2031 | Dec 2031 | Jun 2031 | Dec 2031
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002184 | Replmt Combined SE & WM btwn E 125 St & E 128 St MN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2031 | Mar 2032 | Dec 2031 | Mar 2032
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CPR | WATER EFICIENCY UPGRADES AT CENTRAL PARK RECIRCULATION | 1 | DEVELOP SCOPE | Jun 2020 | Oct 2020 | Jun 2020 | Oct 2020
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CPR | WATER EFICIENCY UPGRADES AT CENTRAL PARK RECIRCULATION | 2 | PRELIMINARY DESIGN | Oct 2020 | Apr 2021 | Oct 2020 | Apr 2021
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CPR | WATER EFICIENCY UPGRADES AT CENTRAL PARK RECIRCULATION | 3 | FINAL DESIGN | Apr 2021 | Oct 2022 | Apr 2021 | Oct 2022
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CPR | WATER EFICIENCY UPGRADES AT CENTRAL PARK RECIRCULATION | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2022 | Apr 2023 | Oct 2022 | Apr 2023
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CPR | WATER EFICIENCY UPGRADES AT CENTRAL PARK RECIRCULATION | 5 | CONSTRUCTION TO 25% | Apr 2023 | Jan 2024 | Apr 2023 | Jan 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CPR | WATER EFICIENCY UPGRADES AT CENTRAL PARK RECIRCULATION | 6 | CONSTRUCTION TO 50% | Jan 2024 | Oct 2024 | Jan 2024 | Oct 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CPR | WATER EFICIENCY UPGRADES AT CENTRAL PARK RECIRCULATION | 7 | CONSTRUCTION TO 75% | Oct 2024 | Jul 2025 | Oct 2024 | Jul 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CPR | WATER EFICIENCY UPGRADES AT CENTRAL PARK RECIRCULATION | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CPR | WATER EFICIENCY UPGRADES AT CENTRAL PARK RECIRCULATION | 9 | SUBSTANTIAL COMPLETION | Oct 2025 | Dec 2025 | Oct 2025 | Dec 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CPR | WATER EFICIENCY UPGRADES AT CENTRAL PARK RECIRCULATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2025 | Mar 2026 | Dec 2025 | Mar 2026
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-279-L | INSTALLATION OF EMERGENCY GENERATORS AT WARDS ISAND WPCP | 1 | DEVELOP SCOPE | Jun 2016 | Feb 2017 | Jun 2016 | Feb 2017
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-279-L | INSTALLATION OF EMERGENCY GENERATORS AT WARDS ISAND WPCP | 2 | PRELIMINARY DESIGN | Feb 2017 | Feb 2018 | Feb 2017 | Feb 2018
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-279-L | INSTALLATION OF EMERGENCY GENERATORS AT WARDS ISAND WPCP | 3 | FINAL DESIGN | Feb 2018 | Aug 2019 | Feb 2018 | Aug 2019
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-279-L | INSTALLATION OF EMERGENCY GENERATORS AT WARDS ISAND WPCP | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2019 | May 2020 | Aug 2019 | May 2020
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-279-L | INSTALLATION OF EMERGENCY GENERATORS AT WARDS ISAND WPCP | 5 | CONSTRUCTION TO 25% | May 2020 | May 2021 | May 2020 | May 2021
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-279-L | INSTALLATION OF EMERGENCY GENERATORS AT WARDS ISAND WPCP | 6 | CONSTRUCTION TO 50% | May 2021 | Apr 2022 | May 2021 | Apr 2022
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-279-L | INSTALLATION OF EMERGENCY GENERATORS AT WARDS ISAND WPCP | 7 | CONSTRUCTION TO 75% | May 2022 | Apr 2023 | May 2022 | Apr 2023
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-279-L | INSTALLATION OF EMERGENCY GENERATORS AT WARDS ISAND WPCP | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2023 | Jan 2024 | Apr 2023 | Jan 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-279-L | INSTALLATION OF EMERGENCY GENERATORS AT WARDS ISAND WPCP | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2036
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-279-L | INSTALLATION OF EMERGENCY GENERATORS AT WARDS ISAND WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2024 | Oct 2024 | Jul 2036 | Oct 2036
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-292-L | RECONSTRUCTION OF POWER DISTRIBUTION @ THE WARDS ISLAND WWTP | 1 | DEVELOP SCOPE | Jun 2017 | Aug 2017 | Jun 2017 | Feb 2018
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-292-L | RECONSTRUCTION OF POWER DISTRIBUTION @ THE WARDS ISLAND WWTP | 2 | PRELIMINARY DESIGN | Aug 2017 | Dec 2017 | Feb 2018 | Feb 2019
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-292-L | RECONSTRUCTION OF POWER DISTRIBUTION @ THE WARDS ISLAND WWTP | 3 | FINAL DESIGN | Dec 2017 | Jun 2018 | Feb 2019 | Aug 2020
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-292-L | RECONSTRUCTION OF POWER DISTRIBUTION @ THE WARDS ISLAND WWTP | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Sep 2018 | Aug 2020 | May 2021
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-292-L | RECONSTRUCTION OF POWER DISTRIBUTION @ THE WARDS ISLAND WWTP | 5 | CONSTRUCTION TO 25% | Sep 2018 | Jan 2019 | May 2021 | May 2022
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-292-L | RECONSTRUCTION OF POWER DISTRIBUTION @ THE WARDS ISLAND WWTP | 6 | CONSTRUCTION TO 50% | Jan 2019 | May 2019 | May 2022 | Apr 2023
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-292-L | RECONSTRUCTION OF POWER DISTRIBUTION @ THE WARDS ISLAND WWTP | 7 | CONSTRUCTION TO 75% | May 2019 | Sep 2019 | May 2023 | Apr 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-292-L | RECONSTRUCTION OF POWER DISTRIBUTION @ THE WARDS ISLAND WWTP | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Dec 2019 | Apr 2024 | Jan 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-292-L | RECONSTRUCTION OF POWER DISTRIBUTION @ THE WARDS ISLAND WWTP | 9 | SUBSTANTIAL COMPLETION | Dec 2019 | Feb 2020 | Jan 2025 | Jul 2033
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-292-L | RECONSTRUCTION OF POWER DISTRIBUTION @ THE WARDS ISLAND WWTP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2020 | Mar 2020 | Jul 2033 | Oct 2033
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-298-B | CONSULTANT DESIGN FOR CONVERSION OF SHARON DEMO @ WARDS ISL | 1 | DEVELOP SCOPE | Jun 2015 | Mar 2016 | Jun 2015 | Mar 2016
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-298-B | CONSULTANT DESIGN FOR CONVERSION OF SHARON DEMO @ WARDS ISL | 2 | PRELIMINARY DESIGN | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-298-B | CONSULTANT DESIGN FOR CONVERSION OF SHARON DEMO @ WARDS ISL | 3 | FINAL DESIGN | Mar 2017 | Sep 2018 | Mar 2017 | Sep 2018
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-298-B | CONSULTANT DESIGN FOR CONVERSION OF SHARON DEMO @ WARDS ISL | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2018 | Jun 2019 | Sep 2018 | Jun 2019
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-298-B | CONSULTANT DESIGN FOR CONVERSION OF SHARON DEMO @ WARDS ISL | 5 | CONSTRUCTION TO 25% | Jun 2019 | Jun 2020 | Jun 2019 | Jun 2020
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-298-B | CONSULTANT DESIGN FOR CONVERSION OF SHARON DEMO @ WARDS ISL | 6 | CONSTRUCTION TO 50% | Jun 2020 | May 2021 | Jun 2020 | May 2021
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-298-B | CONSULTANT DESIGN FOR CONVERSION OF SHARON DEMO @ WARDS ISL | 7 | CONSTRUCTION TO 75% | May 2021 | May 2022 | May 2021 | May 2022
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-298-B | CONSULTANT DESIGN FOR CONVERSION OF SHARON DEMO @ WARDS ISL | 8 | ORIGINAL EQUIP & FURNISHING | May 2022 | Feb 2023 | May 2022 | Feb 2023
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-298-B | CONSULTANT DESIGN FOR CONVERSION OF SHARON DEMO @ WARDS ISL | 9 | SUBSTANTIAL COMPLETION | Feb 2023 | Aug 2023 | Feb 2023 | Aug 2027
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-298-B | CONSULTANT DESIGN FOR CONVERSION OF SHARON DEMO @ WARDS ISL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2023 | Nov 2023 | Aug 2027 | Nov 2027
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-305 | RECONSTRUCTION OF FENDER @ WARDS ISLAND WPCP | 1 | FINAL DESIGN | Jun 2022 | Nov 2023 | Jun 2027 | Nov 2028
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-305 | RECONSTRUCTION OF FENDER @ WARDS ISLAND WPCP | 2 | CONSTRUCTION TO 25% | Nov 2023 | Jul 2024 | Nov 2028 | Jul 2029
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-305 | RECONSTRUCTION OF FENDER @ WARDS ISLAND WPCP | 3 | CONSTRUCTION TO 50% | Jul 2024 | Mar 2025 | Jul 2029 | Mar 2030
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-305 | RECONSTRUCTION OF FENDER @ WARDS ISLAND WPCP | 4 | CONSTRUCTION TO 75% | Mar 2025 | Nov 2025 | Mar 2030 | Nov 2030
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-311-L | REHAB DIGAS LEAKS AT WARDS ISLAND WPCP | 1 | DEVELOP SCOPE | Nov 2019 | Jan 2020 | Nov 2019 | Jan 2020
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-311-L | REHAB DIGAS LEAKS AT WARDS ISLAND WPCP | 2 | PRELIMINARY DESIGN | Jan 2020 | May 2020 | Jan 2020 | May 2020
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-311-L | REHAB DIGAS LEAKS AT WARDS ISLAND WPCP | 3 | FINAL DESIGN | May 2020 | Nov 2020 | May 2020 | Nov 2020
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-311-L | REHAB DIGAS LEAKS AT WARDS ISLAND WPCP | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2020 | Feb 2021 | Nov 2020 | Feb 2021
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-311-L | REHAB DIGAS LEAKS AT WARDS ISLAND WPCP | 5 | CONSTRUCTION TO 25% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-311-L | REHAB DIGAS LEAKS AT WARDS ISLAND WPCP | 6 | CONSTRUCTION TO 50% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-311-L | REHAB DIGAS LEAKS AT WARDS ISLAND WPCP | 7 | CONSTRUCTION TO 75% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-311-L | REHAB DIGAS LEAKS AT WARDS ISLAND WPCP | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2022 | May 2022 | Feb 2022 | May 2022
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-311-L | REHAB DIGAS LEAKS AT WARDS ISLAND WPCP | 9 | SUBSTANTIAL COMPLETION | May 2022 | Jul 2022 | May 2022 | Jul 2022
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-311-L | REHAB DIGAS LEAKS AT WARDS ISLAND WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2022 | Aug 2022 | Jul 2022 | Aug 2022
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-323-L | UPGRADE MSP CC VALVE,ACTUATORS,DISCHARGE PIP REPL @ WI WRRF | 1 | FINAL DESIGN | Jun 2022 | Nov 2023 | Jun 2023 | Dec 2024
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-323-L | UPGRADE MSP CC VALVE,ACTUATORS,DISCHARGE PIP REPL @ WI WRRF | 2 | CONSTRUCTION TO 25% | Nov 2023 | Jul 2024 | Dec 2024 | Aug 2025
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-323-L | UPGRADE MSP CC VALVE,ACTUATORS,DISCHARGE PIP REPL @ WI WRRF | 3 | CONSTRUCTION TO 50% | Jul 2024 | Mar 2025 | Aug 2025 | Mar 2026
20231026 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-323-L | UPGRADE MSP CC VALVE,ACTUATORS,DISCHARGE PIP REPL @ WI WRRF | 4 | CONSTRUCTION TO 75% | Mar 2025 | Nov 2025 | Mar 2026 | Nov 2026
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | APIDSMN12 | DSNY ROADMAP ENERGY EFF | 1 | DEVELOP SCOPE | Feb 2023 | May 2023 | Feb 2023 | May 2023
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | APIDSMN12 | DSNY ROADMAP ENERGY EFF | 2 | PRELIMINARY DESIGN | May 2023 | Nov 2023 | May 2023 | Nov 2023
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | APIDSMN12 | DSNY ROADMAP ENERGY EFF | 3 | FINAL DESIGN | Nov 2023 | May 2024 | Nov 2023 | May 2024
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | APIDSMN12 | DSNY ROADMAP ENERGY EFF | 4 | BID AWARD AND REGISTER CONTRCT | May 2024 | May 2025 | May 2024 | May 2025
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | APIDSMN12 | DSNY ROADMAP ENERGY EFF | 5 | CONSTRUCTION TO 25% | May 2025 | May 2026 | May 2025 | May 2026
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | APIDSMN12 | DSNY ROADMAP ENERGY EFF | 6 | CONSTRUCTION TO 50% | May 2026 | May 2027 | May 2026 | May 2027
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | APIDSMN12 | DSNY ROADMAP ENERGY EFF | 7 | CONSTRUCTION TO 75% | May 2027 | May 2028 | May 2027 | May 2028
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | APIDSMN12 | DSNY ROADMAP ENERGY EFF | 8 | ORIGINAL EQUIP & FURNISHING | May 2028 | Aug 2028 | May 2028 | Aug 2028
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | APIDSMN12 | DSNY ROADMAP ENERGY EFF | 9 | SUBSTANTIAL COMPLETION | Aug 2028 | Aug 2029 | Aug 2028 | Aug 2029
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | APIDSMN12 | DSNY ROADMAP ENERGY EFF | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2029 | Dec 2029 | Aug 2029 | Dec 2029
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-264M | Manhattan 26th St Manhattan Borough Shop Roof Replacement | 1 | DEVELOP SCOPE | Jul 2016 | Sep 2016 | Jul 2016 | Sep 2016
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-264M | Manhattan 26th St Manhattan Borough Shop Roof Replacement | 2 | PRELIMINARY DESIGN | Sep 2016 | Jul 2017 | Sep 2016 | Jul 2017
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-264M | Manhattan 26th St Manhattan Borough Shop Roof Replacement | 3 | FINAL DESIGN | Jul 2017 | May 2018 | Jul 2017 | May 2018
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-264M | Manhattan 26th St Manhattan Borough Shop Roof Replacement | 4 | BID AWARD AND REGISTER CONTRCT | May 2018 | Feb 2019 | May 2018 | Feb 2019
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-264M | Manhattan 26th St Manhattan Borough Shop Roof Replacement | 5 | CONSTRUCTION TO 25% | Feb 2019 | Feb 2020 | Feb 2019 | Feb 2020
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-264M | Manhattan 26th St Manhattan Borough Shop Roof Replacement | 6 | CONSTRUCTION TO 50% | Feb 2020 | Feb 2021 | Feb 2020 | Feb 2021
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-264M | Manhattan 26th St Manhattan Borough Shop Roof Replacement | 7 | CONSTRUCTION TO 75% | Feb 2021 | Feb 2022 | Feb 2021 | Feb 2022
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-264M | Manhattan 26th St Manhattan Borough Shop Roof Replacement | 8 | SUBSTANTIAL COMPLETION | Feb 2022 | Nov 2024 | Feb 2022 | Nov 2024
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-264M | Manhattan 26th St Manhattan Borough Shop Roof Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2023 | Mar 2025 | Oct 2023 | Mar 2025
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-385E | MANHATTAN 4/4A/7 GARAGE GLASS FACADE REHABILITATION | 1 | DEVELOP SCOPE | Jul 2015 | Jun 2016 | Jul 2015 | Jun 2016
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-385E | MANHATTAN 4/4A/7 GARAGE GLASS FACADE REHABILITATION | 2 | PRELIMINARY DESIGN | Jun 2016 | Jun 2017 | Jun 2016 | Jun 2017
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-385E | MANHATTAN 4/4A/7 GARAGE GLASS FACADE REHABILITATION | 3 | FINAL DESIGN | Jun 2017 | Jun 2018 | Jun 2017 | Jun 2018
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-385E | MANHATTAN 4/4A/7 GARAGE GLASS FACADE REHABILITATION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Jun 2019 | Jun 2018 | Jun 2019
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-385E | MANHATTAN 4/4A/7 GARAGE GLASS FACADE REHABILITATION | 5 | CONSTRUCTION TO 25% | Jun 2019 | Jun 2020 | Jun 2019 | Jun 2020
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-385E | MANHATTAN 4/4A/7 GARAGE GLASS FACADE REHABILITATION | 6 | CONSTRUCTION TO 50% | Jun 2020 | Jun 2021 | Jun 2020 | Jun 2021
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-385E | MANHATTAN 4/4A/7 GARAGE GLASS FACADE REHABILITATION | 7 | CONSTRUCTION TO 75% | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-385E | MANHATTAN 4/4A/7 GARAGE GLASS FACADE REHABILITATION | 8 | SUBSTANTIAL COMPLETION | Jun 2022 | May 2024 | Jun 2022 | May 2024
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-385E | MANHATTAN 4/4A/7 GARAGE GLASS FACADE REHABILITATION | 9 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Apr 2026 | May 2024 | Apr 2026
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-432 | MANHATTAN 44 BEAVER ST REHABILITATION | 1 | DEVELOP SCOPE | May 2016 | Aug 2016 | May 2016 | Dec 2016
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-432 | MANHATTAN 44 BEAVER ST REHABILITATION | 2 | PRELIMINARY DESIGN | Aug 2016 | May 2017 | Feb 2023 | Nov 2023
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-432 | MANHATTAN 44 BEAVER ST REHABILITATION | 3 | FINAL DESIGN | May 2017 | Jan 2018 | Nov 2023 | Jul 2024
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-432 | MANHATTAN 44 BEAVER ST REHABILITATION | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2018 | Oct 2018 | Jul 2024 | Apr 2025
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-432 | MANHATTAN 44 BEAVER ST REHABILITATION | 5 | CONSTRUCTION TO 25% | Oct 2018 | Jul 2019 | Apr 2025 | Dec 2025
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-432 | MANHATTAN 44 BEAVER ST REHABILITATION | 6 | CONSTRUCTION TO 50% | Jul 2019 | Mar 2020 | Dec 2025 | Sep 2026
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-432 | MANHATTAN 44 BEAVER ST REHABILITATION | 7 | CONSTRUCTION TO 75% | Mar 2020 | Dec 2020 | Sep 2026 | May 2027
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-432 | MANHATTAN 44 BEAVER ST REHABILITATION | 8 | SUBSTANTIAL COMPLETION | Dec 2020 | Sep 2023 | May 2027 | Feb 2029
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-432 | MANHATTAN 44 BEAVER ST REHABILITATION | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2021 | Dec 2023 | Feb 2029 | Dec 2029
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-435 | Manhattan 11 2496 Second Ave Rehab & Building Addition | 1 | DEVELOP SCOPE | May 2015 | Apr 2016 | May 2015 | Apr 2016
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-435 | Manhattan 11 2496 Second Ave Rehab & Building Addition | 2 | PRELIMINARY DESIGN | Apr 2016 | Oct 2016 | Apr 2016 | Oct 2016
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-435 | Manhattan 11 2496 Second Ave Rehab & Building Addition | 3 | FINAL DESIGN | Oct 2016 | Apr 2017 | Oct 2016 | Jun 2019
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-435 | Manhattan 11 2496 Second Ave Rehab & Building Addition | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2017 | Oct 2017 | Jun 2019 | Nov 2020
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-435 | Manhattan 11 2496 Second Ave Rehab & Building Addition | 5 | CONSTRUCTION TO 25% | Oct 2017 | Apr 2018 | Dec 2020 | May 2021
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-435 | Manhattan 11 2496 Second Ave Rehab & Building Addition | 6 | CONSTRUCTION TO 50% | Apr 2018 | Oct 2018 | May 2021 | Nov 2021
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-435 | Manhattan 11 2496 Second Ave Rehab & Building Addition | 7 | CONSTRUCTION TO 75% | Oct 2018 | Apr 2019 | Nov 2021 | May 2022
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-435 | Manhattan 11 2496 Second Ave Rehab & Building Addition | 8 | SUBSTANTIAL COMPLETION | Apr 2019 | Oct 2019 | May 2022 | Dec 2022
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-435 | Manhattan 11 2496 Second Ave Rehab & Building Addition | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2019 | Feb 2021 | Dec 2022 | Jul 2025
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-437 | MANHATTAN 44 BEAVER ST SPRINKLER SYSTEM REPLACEMENT | 1 | DEVELOP SCOPE | May 2016 | Jun 2016 | May 2016 | Jun 2016
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-437 | MANHATTAN 44 BEAVER ST SPRINKLER SYSTEM REPLACEMENT | 2 | PRELIMINARY DESIGN | Jun 2016 | Oct 2016 | Jun 2016 | Oct 2016
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-437 | MANHATTAN 44 BEAVER ST SPRINKLER SYSTEM REPLACEMENT | 3 | FINAL DESIGN | Oct 2016 | Feb 2017 | Oct 2016 | Feb 2017
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-437 | MANHATTAN 44 BEAVER ST SPRINKLER SYSTEM REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2017 | Feb 2018 | Feb 2017 | Feb 2018
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-437 | MANHATTAN 44 BEAVER ST SPRINKLER SYSTEM REPLACEMENT | 5 | CONSTRUCTION TO 25% | Feb 2018 | Feb 2019 | Feb 2018 | Feb 2019
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-437 | MANHATTAN 44 BEAVER ST SPRINKLER SYSTEM REPLACEMENT | 6 | CONSTRUCTION TO 50% | Feb 2019 | Feb 2020 | Feb 2019 | Feb 2020
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-437 | MANHATTAN 44 BEAVER ST SPRINKLER SYSTEM REPLACEMENT | 7 | CONSTRUCTION TO 75% | Feb 2020 | Feb 2021 | Feb 2020 | Feb 2021
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-437 | MANHATTAN 44 BEAVER ST SPRINKLER SYSTEM REPLACEMENT | 8 | SUBSTANTIAL COMPLETION | Feb 2021 | Apr 2023 | Feb 2021 | Apr 2023
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-437 | MANHATTAN 44 BEAVER ST SPRINKLER SYSTEM REPLACEMENT | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2023 | Jun 2025 | Apr 2023 | Jun 2025
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-440B | Bronx 7/8 Garage Slab Replacement | 1 | DEVELOP SCOPE | Aug 2019 | Sep 2019 | Aug 2019 | Sep 2019
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-440B | Bronx 7/8 Garage Slab Replacement | 2 | PRELIMINARY DESIGN | Sep 2019 | Dec 2019 | Sep 2019 | Dec 2021
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-440B | Bronx 7/8 Garage Slab Replacement | 3 | FINAL DESIGN | Jan 2020 | Jun 2020 | Jan 2022 | May 2023
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-440B | Bronx 7/8 Garage Slab Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Mar 2021 | May 2023 | Dec 2023
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-440B | Bronx 7/8 Garage Slab Replacement | 5 | CONSTRUCTION TO 25% | Apr 2021 | Jun 2021 | Dec 2023 | Nov 2024
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-440B | Bronx 7/8 Garage Slab Replacement | 6 | CONSTRUCTION TO 50% | Jun 2021 | Sep 2021 | Dec 2024 | Aug 2025
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-440B | Bronx 7/8 Garage Slab Replacement | 7 | CONSTRUCTION TO 75% | Sep 2021 | Jan 2022 | Aug 2025 | May 2026
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-440B | Bronx 7/8 Garage Slab Replacement | 8 | SUBSTANTIAL COMPLETION | Jan 2022 | Jun 2022 | May 2026 | Feb 2027
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-440B | Bronx 7/8 Garage Slab Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2022 | Nov 2023 | Feb 2027 | Feb 2028
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441B | Manhattan 4/4A/7 Garage Broom Wash Drainage | 1 | DEVELOP SCOPE | Jan 2018 | Mar 2018 | Jan 2018 | Mar 2018
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441B | Manhattan 4/4A/7 Garage Broom Wash Drainage | 2 | PRELIMINARY DESIGN | Mar 2018 | May 2018 | Mar 2018 | May 2018
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441B | Manhattan 4/4A/7 Garage Broom Wash Drainage | 3 | FINAL DESIGN | Jun 2018 | Feb 2019 | Jun 2018 | Feb 2019
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441B | Manhattan 4/4A/7 Garage Broom Wash Drainage | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2019 | Oct 2019 | Feb 2019 | Jan 2020
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441B | Manhattan 4/4A/7 Garage Broom Wash Drainage | 5 | CONSTRUCTION TO 25% | Oct 2019 | Jun 2020 | Jan 2020 | Sep 2020
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441B | Manhattan 4/4A/7 Garage Broom Wash Drainage | 6 | CONSTRUCTION TO 50% | Jun 2020 | Feb 2021 | Sep 2020 | May 2021
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441B | Manhattan 4/4A/7 Garage Broom Wash Drainage | 7 | CONSTRUCTION TO 75% | Feb 2021 | Oct 2021 | May 2021 | Jan 2022
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441B | Manhattan 4/4A/7 Garage Broom Wash Drainage | 8 | SUBSTANTIAL COMPLETION | Oct 2021 | Oct 2022 | Jan 2022 | Oct 2022
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441B | Manhattan 4/4A/7 Garage Broom Wash Drainage | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2022 | Oct 2023 | Oct 2022 | Oct 2023
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441S | Manhattan 4/4A/7 Garage Sprinkler System Upgrades | 1 | DEVELOP SCOPE | Jan 2016 | Sep 2017 | Jan 2016 | Sep 2017
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441S | Manhattan 4/4A/7 Garage Sprinkler System Upgrades | 2 | PRELIMINARY DESIGN | Sep 2017 | Dec 2017 | Sep 2017 | Dec 2017
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441S | Manhattan 4/4A/7 Garage Sprinkler System Upgrades | 3 | FINAL DESIGN | Dec 2017 | Jun 2018 | Dec 2017 | Jun 2018
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441S | Manhattan 4/4A/7 Garage Sprinkler System Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Dec 2018 | Jun 2018 | Dec 2018
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441S | Manhattan 4/4A/7 Garage Sprinkler System Upgrades | 5 | CONSTRUCTION TO 25% | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441S | Manhattan 4/4A/7 Garage Sprinkler System Upgrades | 6 | CONSTRUCTION TO 50% | Dec 2019 | Aug 2020 | Dec 2019 | Aug 2020
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441S | Manhattan 4/4A/7 Garage Sprinkler System Upgrades | 7 | CONSTRUCTION TO 75% | Aug 2020 | Apr 2021 | Aug 2020 | Apr 2021
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441S | Manhattan 4/4A/7 Garage Sprinkler System Upgrades | 8 | SUBSTANTIAL COMPLETION | Apr 2021 | Nov 2022 | Apr 2021 | Nov 2022
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441S | Manhattan 4/4A/7 Garage Sprinkler System Upgrades | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2022 | Jul 2024 | Nov 2022 | Jul 2024
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-447 | Manhattan 44 Beaver St Elevators | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-447 | Manhattan 44 Beaver St Elevators | 2 | PRELIMINARY DESIGN | Dec 2017 | Jun 2018 | Dec 2017 | Jun 2018
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-447 | Manhattan 44 Beaver St Elevators | 3 | FINAL DESIGN | Jun 2018 | Jun 2019 | Jun 2018 | Jun 2019
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-447 | Manhattan 44 Beaver St Elevators | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Jun 2020 | Jun 2019 | Jun 2020
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-447 | Manhattan 44 Beaver St Elevators | 5 | CONSTRUCTION TO 25% | Jun 2020 | Jun 2021 | Jun 2020 | Jun 2021
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-447 | Manhattan 44 Beaver St Elevators | 6 | CONSTRUCTION TO 50% | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-447 | Manhattan 44 Beaver St Elevators | 7 | CONSTRUCTION TO 75% | Jun 2022 | May 2023 | Jun 2022 | May 2023
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-447 | Manhattan 44 Beaver St Elevators | 8 | SUBSTANTIAL COMPLETION | May 2023 | Jan 2025 | May 2023 | Jan 2025
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-447 | Manhattan 44 Beaver St Elevators | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2025 | Mar 2027 | Jan 2025 | Mar 2027
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-452 | MANHATTAN 128 WEST 17 ST REHAB | 1 | DEVELOP SCOPE | Feb 2023 | May 2023 | Feb 2023 | May 2023
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-452 | MANHATTAN 128 WEST 17 ST REHAB | 2 | PRELIMINARY DESIGN | Jun 2023 | Dec 2023 | Jun 2023 | Dec 2023
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-452 | MANHATTAN 128 WEST 17 ST REHAB | 3 | FINAL DESIGN | Dec 2023 | Jul 2024 | Dec 2023 | Jul 2024
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-452 | MANHATTAN 128 WEST 17 ST REHAB | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Mar 2025 | Jul 2024 | Mar 2025
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-452 | MANHATTAN 128 WEST 17 ST REHAB | 5 | CONSTRUCTION TO 25% | Apr 2025 | Dec 2025 | Apr 2025 | Dec 2025
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-452 | MANHATTAN 128 WEST 17 ST REHAB | 6 | CONSTRUCTION TO 50% | Dec 2025 | Sep 2026 | Dec 2025 | Sep 2026
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-452 | MANHATTAN 128 WEST 17 ST REHAB | 7 | CONSTRUCTION TO 75% | Sep 2026 | Jun 2027 | Sep 2026 | Jun 2027
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-452 | MANHATTAN 128 WEST 17 ST REHAB | 8 | SUBSTANTIAL COMPLETION | Jun 2027 | Mar 2028 | Jun 2027 | Mar 2028
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-452 | MANHATTAN 128 WEST 17 ST REHAB | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2028 | Dec 2028 | Mar 2028 | Dec 2028
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464D | Manhattan Henry St Roof Replacement | 1 | DEVELOP SCOPE | Dec 2016 | Aug 2017 | Dec 2016 | Aug 2017
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464D | Manhattan Henry St Roof Replacement | 2 | PRELIMINARY DESIGN | Aug 2017 | Feb 2018 | Aug 2017 | Feb 2018
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464D | Manhattan Henry St Roof Replacement | 3 | FINAL DESIGN | Feb 2018 | Aug 2018 | Feb 2018 | Aug 2018
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464D | Manhattan Henry St Roof Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2018 | Aug 2019 | Aug 2018 | Aug 2019
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464D | Manhattan Henry St Roof Replacement | 5 | CONSTRUCTION TO 25% | Aug 2019 | Aug 2020 | Aug 2019 | Aug 2020
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464D | Manhattan Henry St Roof Replacement | 6 | CONSTRUCTION TO 50% | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464D | Manhattan Henry St Roof Replacement | 7 | CONSTRUCTION TO 75% | Aug 2021 | Aug 2022 | Aug 2021 | Aug 2022
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464D | Manhattan Henry St Roof Replacement | 8 | SUBSTANTIAL COMPLETION | Aug 2022 | Jul 2024 | Aug 2022 | Jul 2024
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464D | Manhattan Henry St Roof Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2024 | Jun 2026 | Jul 2024 | Jun 2026
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464E | Manhattan 8 215th St Garage Roof and Masonry Replacement | 1 | DEVELOP SCOPE | Jul 2016 | Aug 2016 | Jul 2016 | Aug 2016
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464E | Manhattan 8 215th St Garage Roof and Masonry Replacement | 2 | PRELIMINARY DESIGN | Aug 2016 | Aug 2017 | Aug 2016 | Aug 2017
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464E | Manhattan 8 215th St Garage Roof and Masonry Replacement | 3 | FINAL DESIGN | Aug 2017 | Aug 2018 | Aug 2017 | Aug 2018
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464E | Manhattan 8 215th St Garage Roof and Masonry Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2018 | Aug 2019 | Aug 2018 | Aug 2019
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464E | Manhattan 8 215th St Garage Roof and Masonry Replacement | 5 | CONSTRUCTION TO 25% | Aug 2019 | Aug 2020 | Aug 2019 | Aug 2020
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464E | Manhattan 8 215th St Garage Roof and Masonry Replacement | 6 | CONSTRUCTION TO 50% | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464E | Manhattan 8 215th St Garage Roof and Masonry Replacement | 7 | CONSTRUCTION TO 75% | Aug 2021 | Aug 2022 | Aug 2021 | Aug 2022
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464E | Manhattan 8 215th St Garage Roof and Masonry Replacement | 8 | SUBSTANTIAL COMPLETION | Aug 2022 | Aug 2023 | Aug 2022 | Aug 2023
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464E | Manhattan 8 215th St Garage Roof and Masonry Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2023 | Jan 2026 | Aug 2023 | Jan 2026
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-470 | Manhattan 3 Garage Rehabilitation | 1 | DEVELOP SCOPE | Aug 2022 | Sep 2022 | Aug 2022 | Sep 2022
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-470 | Manhattan 3 Garage Rehabilitation | 2 | PRELIMINARY DESIGN | May 2023 | Sep 2023 | May 2023 | Sep 2023
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-470 | Manhattan 3 Garage Rehabilitation | 3 | FINAL DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-470 | Manhattan 3 Garage Rehabilitation | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2023 | Jun 2024 | Nov 2023 | Jun 2024
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-470 | Manhattan 3 Garage Rehabilitation | 5 | CONSTRUCTION TO 25% | Jun 2024 | Jan 2025 | Jun 2024 | Jan 2025
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-470 | Manhattan 3 Garage Rehabilitation | 6 | CONSTRUCTION TO 50% | Jan 2025 | Aug 2025 | Jan 2025 | Aug 2025
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-470 | Manhattan 3 Garage Rehabilitation | 7 | CONSTRUCTION TO 75% | Aug 2025 | Mar 2026 | Aug 2025 | Mar 2026
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-470 | Manhattan 3 Garage Rehabilitation | 8 | SUBSTANTIAL COMPLETION | Mar 2026 | Aug 2026 | Mar 2026 | Aug 2026
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-470 | Manhattan 3 Garage Rehabilitation | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2026 | Feb 2027 | Aug 2026 | Feb 2027
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S216-401D | E. 91 ST ST MTS PIER REHAB | 1 | DEVELOP SCOPE | Jun 2021 | Aug 2021 | Jun 2021 | Aug 2021
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S216-401D | E. 91 ST ST MTS PIER REHAB | 2 | PRELIMINARY DESIGN | Aug 2021 | Dec 2021 | Aug 2021 | Dec 2021
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S216-401D | E. 91 ST ST MTS PIER REHAB | 3 | FINAL DESIGN | Dec 2021 | Apr 2022 | Dec 2021 | Apr 2022
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S216-401D | E. 91 ST ST MTS PIER REHAB | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2022 | Jun 2022 | Apr 2022 | Jun 2022
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S216-401D | E. 91 ST ST MTS PIER REHAB | 5 | CONSTRUCTION TO 25% | Jun 2022 | Feb 2023 | Jun 2022 | Feb 2023
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S216-401D | E. 91 ST ST MTS PIER REHAB | 6 | CONSTRUCTION TO 50% | Feb 2023 | Oct 2023 | Feb 2023 | Oct 2023
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S216-401D | E. 91 ST ST MTS PIER REHAB | 7 | CONSTRUCTION TO 75% | Oct 2023 | Jun 2024 | Oct 2023 | Jun 2024
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S216-401D | E. 91 ST ST MTS PIER REHAB | 8 | SUBSTANTIAL COMPLETION | Jun 2024 | Nov 2024 | Jun 2024 | Nov 2024
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S216-401D | E. 91 ST ST MTS PIER REHAB | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2024 | Feb 2025 | Nov 2024 | Feb 2025
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S216-415C | West 59th street MTS Dredging | 1 | DEVELOP SCOPE | Jan 2019 | Sep 2019 | Jan 2019 | Sep 2019
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S216-415C | West 59th street MTS Dredging | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Sep 2020
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S216-415C | West 59th street MTS Dredging | 3 | FINAL DESIGN | Jan 2020 | Mar 2020 | Sep 2020 | Sep 2021
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S216-415C | West 59th street MTS Dredging | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Jun 2020 | Sep 2021 | Sep 2022
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S216-415C | West 59th street MTS Dredging | 5 | CONSTRUCTION TO 25% | Jun 2020 | Apr 2021 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S216-415C | West 59th street MTS Dredging | 6 | CONSTRUCTION TO 50% | Apr 2021 | Oct 2021 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S216-415C | West 59th street MTS Dredging | 7 | CONSTRUCTION TO 75% | Oct 2021 | Feb 2022 | Sep 2024 | Aug 2025
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S216-415C | West 59th street MTS Dredging | 8 | SUBSTANTIAL COMPLETION | Feb 2022 | Jul 2022 | Sep 2025 | Aug 2026
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S216-415C | West 59th street MTS Dredging | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2022 | Nov 2022 | Aug 2026 | Aug 2027
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBC | Hurricane Sandy 26 St Manh Boro Rpr Shop Conduit Work | 1 | DEVELOP SCOPE | Aug 2017 | May 2018 | Aug 2017 | May 2018
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBC | Hurricane Sandy 26 St Manh Boro Rpr Shop Conduit Work | 2 | PRELIMINARY DESIGN | Jun 2018 | Mar 2019 | Jun 2018 | Mar 2019
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBC | Hurricane Sandy 26 St Manh Boro Rpr Shop Conduit Work | 3 | FINAL DESIGN | Mar 2019 | Mar 2020 | Mar 2019 | Mar 2020
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBC | Hurricane Sandy 26 St Manh Boro Rpr Shop Conduit Work | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Mar 2021 | Mar 2020 | Mar 2021
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBC | Hurricane Sandy 26 St Manh Boro Rpr Shop Conduit Work | 5 | CONSTRUCTION TO 25% | Mar 2021 | Mar 2022 | Mar 2021 | Mar 2022
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBC | Hurricane Sandy 26 St Manh Boro Rpr Shop Conduit Work | 6 | CONSTRUCTION TO 50% | Mar 2022 | Mar 2023 | Mar 2022 | Mar 2023
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBC | Hurricane Sandy 26 St Manh Boro Rpr Shop Conduit Work | 7 | CONSTRUCTION TO 75% | Mar 2023 | Mar 2024 | Mar 2023 | Mar 2024
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBC | Hurricane Sandy 26 St Manh Boro Rpr Shop Conduit Work | 8 | SUBSTANTIAL COMPLETION | Mar 2024 | Oct 2025 | Mar 2024 | Oct 2025
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBC | Hurricane Sandy 26 St Manh Boro Rpr Shop Conduit Work | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBS | Hurricane Sandy 26 St Manh Boro R/R & Haz Mitigation | 1 | DEVELOP SCOPE | Aug 2015 | Feb 2016 | Aug 2015 | Feb 2016
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBS | Hurricane Sandy 26 St Manh Boro R/R & Haz Mitigation | 2 | PRELIMINARY DESIGN | Feb 2016 | Feb 2017 | Feb 2016 | Feb 2017
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBS | Hurricane Sandy 26 St Manh Boro R/R & Haz Mitigation | 3 | FINAL DESIGN | Feb 2017 | Feb 2018 | Feb 2017 | Feb 2018
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBS | Hurricane Sandy 26 St Manh Boro R/R & Haz Mitigation | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2018 | Feb 2019 | Feb 2018 | Feb 2019
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBS | Hurricane Sandy 26 St Manh Boro R/R & Haz Mitigation | 5 | CONSTRUCTION TO 25% | Feb 2019 | Feb 2020 | Feb 2019 | Feb 2020
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBS | Hurricane Sandy 26 St Manh Boro R/R & Haz Mitigation | 6 | CONSTRUCTION TO 50% | Feb 2020 | Feb 2021 | Feb 2020 | Feb 2021
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBS | Hurricane Sandy 26 St Manh Boro R/R & Haz Mitigation | 7 | CONSTRUCTION TO 75% | Feb 2021 | Feb 2022 | Feb 2021 | Feb 2022
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBS | Hurricane Sandy 26 St Manh Boro R/R & Haz Mitigation | 8 | SUBSTANTIAL COMPLETION | Feb 2022 | Feb 2023 | Feb 2022 | Feb 2023
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBS | Hurricane Sandy 26 St Manh Boro R/R & Haz Mitigation | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Nov 2025 | Feb 2023 | Nov 2025
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVC | Hurricane Sandy 44 Beaver Street Conduit Replacement | 1 | DEVELOP SCOPE | Aug 2017 | May 2018 | Aug 2017 | May 2018
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVC | Hurricane Sandy 44 Beaver Street Conduit Replacement | 2 | PRELIMINARY DESIGN | Jun 2018 | Mar 2019 | Jun 2018 | Feb 2020
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVC | Hurricane Sandy 44 Beaver Street Conduit Replacement | 3 | FINAL DESIGN | Mar 2019 | Dec 2019 | Feb 2020 | Nov 2022
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVC | Hurricane Sandy 44 Beaver Street Conduit Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Dec 2019 | Sep 2020 | Nov 2022 | Aug 2023
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVC | Hurricane Sandy 44 Beaver Street Conduit Replacement | 5 | CONSTRUCTION TO 25% | Sep 2020 | Jun 2021 | Aug 2023 | May 2024
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVC | Hurricane Sandy 44 Beaver Street Conduit Replacement | 6 | CONSTRUCTION TO 50% | Jun 2021 | Mar 2022 | May 2024 | Feb 2025
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVC | Hurricane Sandy 44 Beaver Street Conduit Replacement | 7 | CONSTRUCTION TO 75% | Apr 2022 | Jan 2023 | Feb 2025 | Nov 2025
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVC | Hurricane Sandy 44 Beaver Street Conduit Replacement | 8 | SUBSTANTIAL COMPLETION | Jan 2023 | Aug 2024 | Nov 2025 | Nov 2026
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVC | Hurricane Sandy 44 Beaver Street Conduit Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2024 | Apr 2026 | Nov 2026 | May 2028
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVR | Hurricane Sandy 44 Beaver St System Replacement | 1 | DEVELOP SCOPE | Aug 2015 | Feb 2016 | Aug 2015 | Nov 2016
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVR | Hurricane Sandy 44 Beaver St System Replacement | 2 | PRELIMINARY DESIGN | Feb 2016 | Feb 2017 | Nov 2016 | May 2019
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVR | Hurricane Sandy 44 Beaver St System Replacement | 3 | FINAL DESIGN | Feb 2017 | Feb 2018 | May 2019 | May 2022
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVR | Hurricane Sandy 44 Beaver St System Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2018 | Feb 2019 | May 2022 | May 2023
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVR | Hurricane Sandy 44 Beaver St System Replacement | 5 | CONSTRUCTION TO 25% | Feb 2019 | Feb 2020 | May 2023 | May 2024
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVR | Hurricane Sandy 44 Beaver St System Replacement | 6 | CONSTRUCTION TO 50% | Feb 2020 | Feb 2021 | May 2024 | May 2025
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVR | Hurricane Sandy 44 Beaver St System Replacement | 7 | CONSTRUCTION TO 75% | Feb 2021 | Feb 2022 | May 2025 | May 2026
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVR | Hurricane Sandy 44 Beaver St System Replacement | 8 | SUBSTANTIAL COMPLETION | Feb 2022 | Nov 2024 | May 2026 | May 2027
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVR | Hurricane Sandy 44 Beaver St System Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Mar 2025 | May 2027 | May 2028
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3C | Hurricane Sandy Manh 3 Garage Conduit Replacement | 1 | DEVELOP SCOPE | Aug 2017 | Feb 2018 | Aug 2017 | Feb 2018
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3C | Hurricane Sandy Manh 3 Garage Conduit Replacement | 2 | PRELIMINARY DESIGN | Feb 2018 | Nov 2018 | Feb 2018 | Nov 2018
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3C | Hurricane Sandy Manh 3 Garage Conduit Replacement | 3 | FINAL DESIGN | Nov 2018 | Aug 2019 | Nov 2018 | Aug 2019
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3C | Hurricane Sandy Manh 3 Garage Conduit Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2019 | Jun 2020 | Aug 2019 | Jun 2020
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3C | Hurricane Sandy Manh 3 Garage Conduit Replacement | 5 | CONSTRUCTION TO 25% | Jun 2020 | Mar 2021 | Jun 2020 | Mar 2021
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3C | Hurricane Sandy Manh 3 Garage Conduit Replacement | 6 | CONSTRUCTION TO 50% | Mar 2021 | Mar 2022 | Mar 2021 | Mar 2022
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3C | Hurricane Sandy Manh 3 Garage Conduit Replacement | 7 | CONSTRUCTION TO 75% | Mar 2022 | Mar 2023 | Mar 2022 | Mar 2023
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3C | Hurricane Sandy Manh 3 Garage Conduit Replacement | 8 | SUBSTANTIAL COMPLETION | Mar 2023 | Sep 2025 | Mar 2023 | Sep 2025
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3C | Hurricane Sandy Manh 3 Garage Conduit Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Feb 2028 | Sep 2025 | Feb 2028
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3G | Hurricane Sandy Manh 3 Garage Repl & Haz Mitigation | 1 | DEVELOP SCOPE | Aug 2015 | Feb 2016 | Aug 2015 | Feb 2016
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3G | Hurricane Sandy Manh 3 Garage Repl & Haz Mitigation | 2 | PRELIMINARY DESIGN | Feb 2016 | Feb 2017 | Feb 2016 | Feb 2017
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3G | Hurricane Sandy Manh 3 Garage Repl & Haz Mitigation | 3 | FINAL DESIGN | Feb 2017 | Feb 2018 | Feb 2017 | Feb 2018
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3G | Hurricane Sandy Manh 3 Garage Repl & Haz Mitigation | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2018 | Feb 2019 | Feb 2018 | Feb 2019
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3G | Hurricane Sandy Manh 3 Garage Repl & Haz Mitigation | 5 | CONSTRUCTION TO 25% | Feb 2019 | Feb 2020 | Feb 2019 | Feb 2020
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3G | Hurricane Sandy Manh 3 Garage Repl & Haz Mitigation | 6 | CONSTRUCTION TO 50% | Feb 2020 | Feb 2021 | Feb 2020 | Feb 2021
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3G | Hurricane Sandy Manh 3 Garage Repl & Haz Mitigation | 7 | CONSTRUCTION TO 75% | Feb 2021 | Feb 2022 | Feb 2021 | Feb 2022
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3G | Hurricane Sandy Manh 3 Garage Repl & Haz Mitigation | 8 | SUBSTANTIAL COMPLETION | Feb 2022 | Nov 2024 | Feb 2022 | Nov 2024
20231026 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3G | Hurricane Sandy Manh 3 Garage Repl & Haz Mitigation | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Mar 2025 | Jun 2022 | Mar 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT504 | Replacement of Park, Highway and Flood Lights with LEDs | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jun 2027 | Sep 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT504 | Replacement of Park, Highway and Flood Lights with LEDs | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Sep 2027 | Jan 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT504 | Replacement of Park, Highway and Flood Lights with LEDs | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2028 | Jul 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT504 | Replacement of Park, Highway and Flood Lights with LEDs | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2028 | Oct 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT504 | Replacement of Park, Highway and Flood Lights with LEDs | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2028 | Feb 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT504 | Replacement of Park, Highway and Flood Lights with LEDs | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2029 | Jun 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT504 | Replacement of Park, Highway and Flood Lights with LEDs | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2029 | Oct 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT504 | Replacement of Park, Highway and Flood Lights with LEDs | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2025 | Jan 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT504 | Replacement of Park, Highway and Flood Lights with LEDs | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2026 | Mar 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT504 | Replacement of Park, Highway and Flood Lights with LEDs | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2026 | Apr 2031
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT602 | DOT - Various locations- Rooftop Solar | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT602 | DOT - Various locations- Rooftop Solar | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT602 | DOT - Various locations- Rooftop Solar | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2023 | Jul 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT602 | DOT - Various locations- Rooftop Solar | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2023 | Oct 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT602 | DOT - Various locations- Rooftop Solar | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2023 | Feb 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT602 | DOT - Various locations- Rooftop Solar | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2024 | Jun 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT602 | DOT - Various locations- Rooftop Solar | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2024 | Oct 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT602 | DOT - Various locations- Rooftop Solar | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2024 | Jan 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT602 | DOT - Various locations- Rooftop Solar | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2025 | Mar 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT602 | DOT - Various locations- Rooftop Solar | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2025 | Jun 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | E34CCTV | East 34th St Ferry Landing CCTV upgrade | 1 | DEVELOP SCOPE | Jun 2016 | Jun 2017 | Jun 2019 | Jun 2020
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | E34CCTV | East 34th St Ferry Landing CCTV upgrade | 2 | DESIGN START | Jun 2017 | Jun 2019 | Jun 2020 | Jun 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | E34CCTV | East 34th St Ferry Landing CCTV upgrade | 3 | CONSTRUCTION START | Jun 2019 | Jun 2021 | Jun 2021 | Jun 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | EMIDTWNRZ | East Midtown Rezoning | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jun 2024 | Sep 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | EMIDTWNRZ | East Midtown Rezoning | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | EMIDTWNRZ | East Midtown Rezoning | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2025 | Jul 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | EMIDTWNRZ | East Midtown Rezoning | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2025 | Oct 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | EMIDTWNRZ | East Midtown Rezoning | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2025 | Feb 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | EMIDTWNRZ | East Midtown Rezoning | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2026 | Jun 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | EMIDTWNRZ | East Midtown Rezoning | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2026 | Oct 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | EMIDTWNRZ | East Midtown Rezoning | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2026 | Jan 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | EMIDTWNRZ | East Midtown Rezoning | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2027 | Mar 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | EMIDTWNRZ | East Midtown Rezoning | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2027 | Jun 2031
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | FAWHTSGTF | WHT Slips Gallows Towers Foundation Piles Reconstruction | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2025 | Jun 2024 | Jun 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | FAWHTSGTF | WHT Slips Gallows Towers Foundation Piles Reconstruction | 2 | DESIGN START | Jun 2025 | Jun 2027 | Jun 2025 | Jun 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | FAWHTSGTF | WHT Slips Gallows Towers Foundation Piles Reconstruction | 3 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2027 | Jun 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | FAWTCCTV | WHT Terminal CCTV Upgrades | 1 | DEVELOP SCOPE | Jun 2017 | Jun 2018 | Jun 2028 | Jun 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | FAWTCCTV | WHT Terminal CCTV Upgrades | 2 | DESIGN START | Jun 2018 | Jun 2020 | Jun 2029 | Jun 2031
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | FAWTCCTV | WHT Terminal CCTV Upgrades | 3 | CONSTRUCTION START | Jun 2020 | Jun 2022 | Jun 2031 | Jun 2033
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1027 | HARLEM RV DRIVE VIADUCT: 127TH ST - 2ND AVE #2-23305-9/TN,,, | 1 | DEVELOP SCOPE | Jul 2004 | Jun 2005
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1027 | HARLEM RV DRIVE VIADUCT: 127TH ST - 2ND AVE #2-23305-9/TN,,, | 2 | DEVELOP SCOPE | Jul 2005 | Jun 2009 | Oct 2028 | Dec 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1027 | HARLEM RV DRIVE VIADUCT: 127TH ST - 2ND AVE #2-23305-9/TN,,, | 3 | DESIGN START | Jun 2009 | Jun 2011 | Feb 2029 | Sep 2030
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1027 | HARLEM RV DRIVE VIADUCT: 127TH ST - 2ND AVE #2-23305-9/TN,,, | 5 | CONSTRUCTION START | Jun 2009 | Jun 2011 | Nov 2030 | Jul 2031
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1120B | 11TH AVENUE VIADUCT NORTH SECTION - 33 ST to 35 ST #2245010 | 1 | DEVELOP SCOPE | Jun 2013 | Jun 2014
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1120B | 11TH AVENUE VIADUCT NORTH SECTION - 33 ST to 35 ST #2245010 | 2 | DEVELOP SCOPE | Jun 2014 | Jun 2018 | Jun 2024 | Jun 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1120B | 11TH AVENUE VIADUCT NORTH SECTION - 33 ST to 35 ST #2245010 | 3 | DESIGN START | Jun 2018 | Jun 2020 | Jun 2025 | Jun 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1120B | 11TH AVENUE VIADUCT NORTH SECTION - 33 ST to 35 ST #2245010 | 5 | CONSTRUCTION START | Jun 2018 | Jun 2020 | Jun 2029 | Jun 2031
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1147 | BROADWAY BRIDGE/HARLEM RIVER (BIN 2-24013-7) | 1 | DEVELOP SCOPE | Jul 2006 | Jul 2007 | Feb 2015 | Apr 2017
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1147 | BROADWAY BRIDGE/HARLEM RIVER (BIN 2-24013-7) | 2 | DESIGN START | Jul 2007 | Jun 2011 | Jun 2006 | Sep 2017
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1147 | BROADWAY BRIDGE/HARLEM RIVER (BIN 2-24013-7) | 3 | CONSTRUCTION START | Jul 2011 | Jun 2013 | Sep 2018 | Oct 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1165 | RIVERSIDE DRIVE BR/WEST 158TH 2-24672-0 | 1 | DEVELOP SCOPE | Jul 2010 | Jun 2011
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1165 | RIVERSIDE DRIVE BR/WEST 158TH 2-24672-0 | 2 | DESIGN START | Jul 2011 | Jun 2015 | Dec 2015 | Mar 2017
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1165 | RIVERSIDE DRIVE BR/WEST 158TH 2-24672-0 | 3 | CONSTRUCTION START | Jun 2015 | Jun 2017 | Oct 2014 | Sep 2017
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1165 | RIVERSIDE DRIVE BR/WEST 158TH 2-24672-0 | 5 | CONSTRUCTION START | Jun 2015 | Jun 2017 | Oct 2018 | Sep 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1189 | WEST 79TH STREET/ AMTRAK (7 BIN#'S) | 1 | DEVELOP SCOPE | Jul 2007 | Jun 2008
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1189 | WEST 79TH STREET/ AMTRAK (7 BIN#'S) | 2 | DESIGN START | Jun 2008 | Jun 2012 | Oct 2015 | May 2016
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1189 | WEST 79TH STREET/ AMTRAK (7 BIN#'S) | 3 | CONSTRUCTION START | Jun 2012 | Jun 2014 | Jul 2000 | Sep 2019
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1189 | WEST 79TH STREET/ AMTRAK (7 BIN#'S) | 5 | CONSTRUCTION START | Jun 2012 | Jun 2014 | Aug 2020 | Nov 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1212 | REHAB OF PARK AVE VIADUCT, NORTH SIDE OF EAST 42ND STREET | 1 | DEVELOP SCOPE | Jul 2000 | Jun 2001
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1212 | REHAB OF PARK AVE VIADUCT, NORTH SIDE OF EAST 42ND STREET | 2 | DESIGN START | Jul 2001 | Jun 2005 | Jul 2014 | Jun 2015
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1212 | REHAB OF PARK AVE VIADUCT, NORTH SIDE OF EAST 42ND STREET | 3 | CONSTRUCTION START | Jun 2005 | Jun 2007 | Jul 2015 | Jun 2019
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1212 | REHAB OF PARK AVE VIADUCT, NORTH SIDE OF EAST 42ND STREET | 5 | CONSTRUCTION START | Jun 2005 | Jun 2007 | Jun 2019 | Nov 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1221 | E25TH STREET PEDESTRIAN BRIDGE OVER FDR | 1 | DEVELOP SCOPE | Jun 2008 | Jun 2015
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1221 | E25TH STREET PEDESTRIAN BRIDGE OVER FDR | 2 | DESIGN START | Jun 2015 | Jun 2015 | Jun 2018 | Jun 2019
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1221 | E25TH STREET PEDESTRIAN BRIDGE OVER FDR | 3 | CONSTRUCTION START | Jun 2015 | Jun 2017 | Jun 2019 | Jun 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1221 | E25TH STREET PEDESTRIAN BRIDGE OVER FDR | 5 | CONSTRUCTION START | Jun 2015 | Jun 2017 | Jun 2023 | Jun 2032
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM191TUN | 191st St Pedestrian Tunnel over Broadway & IRT #1 Subway | 1 | DEVELOP SCOPE | Jun 2017 | Jun 2018
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM191TUN | 191st St Pedestrian Tunnel over Broadway & IRT #1 Subway | 2 | DESIGN START | Jun 2018 | Jun 2022 | Jul 2017 | Oct 2017
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM191TUN | 191st St Pedestrian Tunnel over Broadway & IRT #1 Subway | 3 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Oct 2019 | Oct 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM191TUN | 191st St Pedestrian Tunnel over Broadway & IRT #1 Subway | 5 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Sep 2023 | Dec 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM224624 | WEST DRIVE OVER TRANSVERSE ROAD #2 BIN 2246240 | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM224624 | WEST DRIVE OVER TRANSVERSE ROAD #2 BIN 2246240 | 2 | DESIGN START | Jun 2022 | Jun 2026 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM224624 | WEST DRIVE OVER TRANSVERSE ROAD #2 BIN 2246240 | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2022 | Jun 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM224624 | WEST DRIVE OVER TRANSVERSE ROAD #2 BIN 2246240 | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM224625 | EAST DRIVE OVER TRANSVERSE ROAD #3 BIN 2246250 | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM224625 | EAST DRIVE OVER TRANSVERSE ROAD #3 BIN 2246250 | 2 | DESIGN START | Jun 2022 | Jun 2026 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM224625 | EAST DRIVE OVER TRANSVERSE ROAD #3 BIN 2246250 | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2022 | Jun 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM224625 | EAST DRIVE OVER TRANSVERSE ROAD #3 BIN 2246250 | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM224627 | EAST DRIVE OVER TRANSVERSE ROAD #4 BIN 2246270 | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM224627 | EAST DRIVE OVER TRANSVERSE ROAD #4 BIN 2246270 | 2 | DESIGN START | Jun 2022 | Jun 2026 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM224627 | EAST DRIVE OVER TRANSVERSE ROAD #4 BIN 2246270 | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2022 | Jun 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM224627 | EAST DRIVE OVER TRANSVERSE ROAD #4 BIN 2246270 | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM224628 | WEST DRIVE OVER TRANSVERSE ROAD #4 BIN 2246280 | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM224628 | WEST DRIVE OVER TRANSVERSE ROAD #4 BIN 2246280 | 2 | DESIGN START | Jun 2022 | Jun 2026 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM224628 | WEST DRIVE OVER TRANSVERSE ROAD #4 BIN 2246280 | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2022 | Jun 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM224628 | WEST DRIVE OVER TRANSVERSE ROAD #4 BIN 2246280 | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM224643 | W 110TH ST ENT (MTCLIFF ARCH) PED PATH OPP W 109ST B#2246430 | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM224643 | W 110TH ST ENT (MTCLIFF ARCH) PED PATH OPP W 109ST B#2246430 | 2 | DESIGN START | Jun 2022 | Jun 2026 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM224643 | W 110TH ST ENT (MTCLIFF ARCH) PED PATH OPP W 109ST B#2246430 | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2022 | Jun 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM224643 | W 110TH ST ENT (MTCLIFF ARCH) PED PATH OPP W 109ST B#2246430 | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM224650 | FORT TRYON PLACE ENTRANCE FROM RIVERSIDE DRIVE BIN 2246500 | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM224650 | FORT TRYON PLACE ENTRANCE FROM RIVERSIDE DRIVE BIN 2246500 | 2 | DESIGN START | Jun 2022 | Jun 2026 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM224650 | FORT TRYON PLACE ENTRANCE FROM RIVERSIDE DRIVE BIN 2246500 | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2022 | Jun 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM224650 | FORT TRYON PLACE ENTRANCE FROM RIVERSIDE DRIVE BIN 2246500 | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM245070 | West 38th St over Amtrak 30 St Branch BIN 2245070 | 1 | DEVELOP SCOPE | Jun 2019 | Jun 2020
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM245070 | West 38th St over Amtrak 30 St Branch BIN 2245070 | 2 | DEVELOP SCOPE | Jun 2020 | Jun 2024 | Jun 2020 | Jun 2021
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM245070 | West 38th St over Amtrak 30 St Branch BIN 2245070 | 3 | DESIGN START | Jun 2024 | Jun 2026 | Jun 2021 | Jun 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM245070 | West 38th St over Amtrak 30 St Branch BIN 2245070 | 5 | CONSTRUCTION START | Jun 2024 | Jun 2026 | Jun 2025 | Jun 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM245080 | West 39th St over Amtrak 30 St Branch BIN 2245080 | 1 | DEVELOP SCOPE | Jun 2019 | Jun 2020
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM245080 | West 39th St over Amtrak 30 St Branch BIN 2245080 | 2 | DESIGN START | Jun 2020 | Jun 2024 | Jun 2019 | Jun 2020
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM245080 | West 39th St over Amtrak 30 St Branch BIN 2245080 | 3 | CONSTRUCTION START | Jun 2024 | Jun 2026 | Jun 2020 | Jun 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM245080 | West 39th St over Amtrak 30 St Branch BIN 2245080 | 5 | CONSTRUCTION START | Jun 2024 | Jun 2026 | Jun 2024 | Jun 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM245230 | W 148TH ST PED BR OVER AMTRAK 30 ST BRANCH BIN 2245230 | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM245230 | W 148TH ST PED BR OVER AMTRAK 30 ST BRANCH BIN 2245230 | 2 | DESIGN START | Jun 2022 | Jun 2026 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM245230 | W 148TH ST PED BR OVER AMTRAK 30 ST BRANCH BIN 2245230 | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2022 | Jun 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM245230 | W 148TH ST PED BR OVER AMTRAK 30 ST BRANCH BIN 2245230 | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM246350 | EAST DR OVER PED PATH OPP EAST 80TH ST BIN 2246350 | 1 | DEVELOP SCOPE | Jun 2018 | Jun 2019
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM246350 | EAST DR OVER PED PATH OPP EAST 80TH ST BIN 2246350 | 2 | DESIGN START | Jun 2019 | Jun 2023 | Jun 2018 | Jun 2019
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM246350 | EAST DR OVER PED PATH OPP EAST 80TH ST BIN 2246350 | 3 | CONSTRUCTION START | Jun 2023 | Jun 2025 | Jun 2019 | Jun 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM246350 | EAST DR OVER PED PATH OPP EAST 80TH ST BIN 2246350 | 5 | CONSTRUCTION START | Jun 2023 | Jun 2025 | Jun 2023 | Jun 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM551 | PARK AVE TUNNEL FROM E34TH TO E39TH ST'S #2-24654-0/TN61420 | 1 | DEVELOP SCOPE | Jul 2005 | Jun 2006
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM551 | PARK AVE TUNNEL FROM E34TH TO E39TH ST'S #2-24654-0/TN61420 | 2 | DESIGN START | Jul 2006 | Jun 2010 | Jul 2017 | Jul 2017
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM551 | PARK AVE TUNNEL FROM E34TH TO E39TH ST'S #2-24654-0/TN61420 | 3 | CONSTRUCTION START | Jun 2010 | Jun 2012 | Jul 2006 | Dec 2015
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM551 | PARK AVE TUNNEL FROM E34TH TO E39TH ST'S #2-24654-0/TN61420 | 5 | CONSTRUCTION START | Jun 2010 | Jun 2012 | Jul 2016 | Sep 2033
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM702990 | Rehabilitation of Fort Washington Pedestrian Bridge over AMT | 1 | DEVELOP SCOPE | Jun 2019 | Jun 2020
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM702990 | Rehabilitation of Fort Washington Pedestrian Bridge over AMT | 2 | DESIGN START | Jun 2020 | Jun 2024 | Jun 2019 | Jun 2020
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM702990 | Rehabilitation of Fort Washington Pedestrian Bridge over AMT | 3 | CONSTRUCTION START | Jun 2024 | Jun 2026 | Jun 2020 | Jun 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM702990 | Rehabilitation of Fort Washington Pedestrian Bridge over AMT | 5 | CONSTRUCTION START | Jun 2024 | Jun 2026 | Jun 2024 | Jun 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM8650 | REHAB FDR NORTHBOUND FROM EAST 42-49TH ST BIN: 2268650 | 1 | DEVELOP SCOPE | Jun 2015 | Jun 2016
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM8650 | REHAB FDR NORTHBOUND FROM EAST 42-49TH ST BIN: 2268650 | 2 | DESIGN START | Jun 2016 | Jun 2020 | Sep 2016 | Jul 2017
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM8650 | REHAB FDR NORTHBOUND FROM EAST 42-49TH ST BIN: 2268650 | 3 | CONSTRUCTION START | Jun 2020 | Jun 2022 | Jun 2018 | Jul 2021
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM8650 | REHAB FDR NORTHBOUND FROM EAST 42-49TH ST BIN: 2268650 | 5 | CONSTRUCTION START | Jun 2020 | Jun 2022 | Jun 2022 | Jul 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA22934 | RAMP TO NB HHP OVER AMTRAK WEST SIDE BIN 222934A | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2021
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA22934 | RAMP TO NB HHP OVER AMTRAK WEST SIDE BIN 222934A | 2 | DESIGN START | Jun 2021 | Jun 2025 | Sep 2017 | Aug 2018
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA22934 | RAMP TO NB HHP OVER AMTRAK WEST SIDE BIN 222934A | 3 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Jan 2020 | Jan 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA22934 | RAMP TO NB HHP OVER AMTRAK WEST SIDE BIN 222934A | 5 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Dec 2023 | Mar 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA23216 | Promenade over FDR E81st - 90th St Bin 2232167 | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA23216 | Promenade over FDR E81st - 90th St Bin 2232167 | 2 | DESIGN START | Jun 2023 | Jun 2027 | Nov 2015 | Feb 2016
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA23216 | Promenade over FDR E81st - 90th St Bin 2232167 | 3 | CONSTRUCTION START | Jun 2027 | Jun 2029 | May 2017 | Mar 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA23216 | Promenade over FDR E81st - 90th St Bin 2232167 | 5 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Feb 2023 | May 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24501 | WEST 35TH ST/ AMTRAK 30ST BRANCH BIN# 224501E | 1 | DEVELOP SCOPE | Jul 2016 | Jun 2017
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24501 | WEST 35TH ST/ AMTRAK 30ST BRANCH BIN# 224501E | 2 | DESIGN START | Jul 2017 | Jun 2021 | Jan 2017 | Jun 2017
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24501 | WEST 35TH ST/ AMTRAK 30ST BRANCH BIN# 224501E | 3 | CONSTRUCTION START | Jun 2021 | Jun 2023 | Nov 2018 | May 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24501 | WEST 35TH ST/ AMTRAK 30ST BRANCH BIN# 224501E | 5 | CONSTRUCTION START | Jun 2021 | Jun 2023 | Mar 2023 | Jun 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24544 | WEST 40TH ST / AMTRAK 30ST BRANCH BIN# 2245440 | 1 | DEVELOP SCOPE | Jul 2016 | Jun 2017
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24544 | WEST 40TH ST / AMTRAK 30ST BRANCH BIN# 2245440 | 2 | DESIGN START | Jul 2017 | Jun 2021 | Apr 2017 | Jun 2017
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24544 | WEST 40TH ST / AMTRAK 30ST BRANCH BIN# 2245440 | 3 | CONSTRUCTION START | Jun 2021 | Jun 2023 | Nov 2018 | Jul 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24544 | WEST 40TH ST / AMTRAK 30ST BRANCH BIN# 2245440 | 5 | CONSTRUCTION START | Jun 2021 | Jun 2023 | Jul 2023 | Oct 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24613 | East Dr (Willowdell Arch) over Ped Path Opp East 67th st | 1 | DEVELOP SCOPE | Jun 2017 | Jun 2018
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24613 | East Dr (Willowdell Arch) over Ped Path Opp East 67th st | 2 | DESIGN START | Jun 2018 | Jun 2022 | Jun 2017 | Jun 2018
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24613 | East Dr (Willowdell Arch) over Ped Path Opp East 67th st | 3 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Jun 2018 | Jun 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24613 | East Dr (Willowdell Arch) over Ped Path Opp East 67th st | 5 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Jun 2022 | Jun 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24646 | W 77TH ST ENT (EAGLEVALE ARC) PED PATH OPP W 77TH ST 2246460 | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24646 | W 77TH ST ENT (EAGLEVALE ARC) PED PATH OPP W 77TH ST 2246460 | 2 | DESIGN START | Jun 2022 | Jun 2026 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24646 | W 77TH ST ENT (EAGLEVALE ARC) PED PATH OPP W 77TH ST 2246460 | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2022 | Jun 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24646 | W 77TH ST ENT (EAGLEVALE ARC) PED PATH OPP W 77TH ST 2246460 | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24649 | A.C. Powell Blvd NB over A.C. Powell Blvd BIN 2246490 | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24649 | A.C. Powell Blvd NB over A.C. Powell Blvd BIN 2246490 | 2 | DESIGN START | Jun 2023 | Jun 2027 | Jun 2022 | Jun 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24649 | A.C. Powell Blvd NB over A.C. Powell Blvd BIN 2246490 | 3 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2023 | Jun 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24649 | A.C. Powell Blvd NB over A.C. Powell Blvd BIN 2246490 | 5 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2027 | Jun 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24666 | RIVERSIDE DRIVE over W 125TH ST - W 134TH ST 2246660 | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24666 | RIVERSIDE DRIVE over W 125TH ST - W 134TH ST 2246660 | 2 | DESIGN START | Jun 2023 | Jun 2027 | Jun 2024 | Jun 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24666 | RIVERSIDE DRIVE over W 125TH ST - W 134TH ST 2246660 | 3 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2025 | Jun 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24666 | RIVERSIDE DRIVE over W 125TH ST - W 134TH ST 2246660 | 5 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2029 | Jun 2031
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA25756 | MILLER HIGHWAY over TERRAIN BIN 2257569 | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA25756 | MILLER HIGHWAY over TERRAIN BIN 2257569 | 2 | DESIGN START | Jun 2022 | Jun 2026 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA25756 | MILLER HIGHWAY over TERRAIN BIN 2257569 | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2022 | Jun 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA25756 | MILLER HIGHWAY over TERRAIN BIN 2257569 | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA26724 | Trans-Manhattan Expressway BIN 2267240 | 1 | DEVELOP SCOPE | Jun 2017 | Jun 2018
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA26724 | Trans-Manhattan Expressway BIN 2267240 | 2 | DESIGN START | Jun 2018 | Jun 2022 | Jun 2017 | Oct 2017
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA26724 | Trans-Manhattan Expressway BIN 2267240 | 3 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Feb 2019 | Nov 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA26724 | Trans-Manhattan Expressway BIN 2267240 | 5 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Jan 2024 | Apr 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA29349 | HHP over West 158th St BIN 2229349 | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA29349 | HHP over West 158th St BIN 2229349 | 2 | DESIGN START | Jun 2022 | Jun 2026 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA29349 | HHP over West 158th St BIN 2229349 | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2022 | Jun 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA29349 | HHP over West 158th St BIN 2229349 | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA4501D | West 34Th St over Amtrak 30 St Branch BIN 224501D | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2021
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA4501D | West 34Th St over Amtrak 30 St Branch BIN 224501D | 2 | DESIGN START | Jun 2021 | Jun 2025 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA4501D | West 34Th St over Amtrak 30 St Branch BIN 224501D | 3 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Jun 2022 | Jun 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA4501D | West 34Th St over Amtrak 30 St Branch BIN 224501D | 5 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Jun 2026 | Jun 2034
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA4501F | West 36Th St over Amtrak 30 St Branch BIN 224501F | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2021
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA4501F | West 36Th St over Amtrak 30 St Branch BIN 224501F | 2 | DESIGN START | Jun 2021 | Jun 2025 | Jun 2024 | Jun 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA4501F | West 36Th St over Amtrak 30 St Branch BIN 224501F | 3 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Jun 2025 | Jun 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA4501F | West 36Th St over Amtrak 30 St Branch BIN 224501F | 5 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Jun 2029 | Jun 2031
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMFDNY20 | FDNY/NFPA CODE UPDATE HHP VARIOUS AND PARK AVE TUNNEL | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2021
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMFDNY20 | FDNY/NFPA CODE UPDATE HHP VARIOUS AND PARK AVE TUNNEL | 2 | DESIGN START | Jun 2021 | Jun 2025 | Aug 2016 | May 2017
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMFDNY20 | FDNY/NFPA CODE UPDATE HHP VARIOUS AND PARK AVE TUNNEL | 3 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Jul 2019 | Apr 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMFDNY20 | FDNY/NFPA CODE UPDATE HHP VARIOUS AND PARK AVE TUNNEL | 5 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Jan 2024 | Apr 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBRIBIKE | Roosevelt Island Bridge Bike Lane | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBRIBIKE | Roosevelt Island Bridge Bike Lane | 2 | DESIGN START | Jun 2022 | Jun 2026 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBRIBIKE | Roosevelt Island Bridge Bike Lane | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2022 | Jun 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBRIBIKE | Roosevelt Island Bridge Bike Lane | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21D | Citywide Milling - Manhattan | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21D | Citywide Milling - Manhattan | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2023 | Jan 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21D | Citywide Milling - Manhattan | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2024 | Jul 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21D | Citywide Milling - Manhattan | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2024 | Oct 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21D | Citywide Milling - Manhattan | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2024 | Feb 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21D | Citywide Milling - Manhattan | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2025 | Jun 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21D | Citywide Milling - Manhattan | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2025 | Oct 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21D | Citywide Milling - Manhattan | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Oct 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21D | Citywide Milling - Manhattan | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Oct 2023 | Dec 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21D | Citywide Milling - Manhattan | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Dec 2023 | Nov 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23D | Citywide Milling - Manhattan | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23D | Citywide Milling - Manhattan | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23D | Citywide Milling - Manhattan | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23D | Citywide Milling - Manhattan | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23D | Citywide Milling - Manhattan | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23D | Citywide Milling - Manhattan | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23D | Citywide Milling - Manhattan | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23D | Citywide Milling - Manhattan | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23D | Citywide Milling - Manhattan | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR23D | Citywide Milling - Manhattan | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10216 | Walk of Fame -- Walk of Fame installation in CD 8 | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2028 | Sep 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10216 | Walk of Fame -- Walk of Fame installation in CD 8 | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2028 | Jan 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10216 | Walk of Fame -- Walk of Fame installation in CD 8 | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2029 | Jul 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10216 | Walk of Fame -- Walk of Fame installation in CD 8 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2029 | Oct 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10216 | Walk of Fame -- Walk of Fame installation in CD 8 | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2029 | Feb 2030
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10216 | Walk of Fame -- Walk of Fame installation in CD 8 | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2030 | Jun 2030
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10216 | Walk of Fame -- Walk of Fame installation in CD 8 | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2030 | Oct 2030
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10216 | Walk of Fame -- Walk of Fame installation in CD 8 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2030 | Jan 2031
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10216 | Walk of Fame -- Walk of Fame installation in CD 8 | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2031 | Mar 2031
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10216 | Walk of Fame -- Walk of Fame installation in CD 8 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2031 | Jun 2032
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10217 | SAFETY IMPROVEMENTS | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Jun 2027 | Sep 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10217 | SAFETY IMPROVEMENTS | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Sep 2027 | Jan 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10217 | SAFETY IMPROVEMENTS | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Jan 2028 | Jul 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10217 | SAFETY IMPROVEMENTS | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Jul 2028 | Oct 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10217 | SAFETY IMPROVEMENTS | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Oct 2028 | Feb 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10217 | SAFETY IMPROVEMENTS | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Feb 2029 | Jun 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10217 | SAFETY IMPROVEMENTS | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Jun 2029 | Oct 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10217 | SAFETY IMPROVEMENTS | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | Oct 2029 | Jan 2030
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10217 | SAFETY IMPROVEMENTS | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Jan 2030 | Mar 2030
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10217 | SAFETY IMPROVEMENTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Mar 2030 | Jun 2032
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10220 | DOT - 3rd Avenue Sidewalks | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Aug 2023 | Nov 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10220 | DOT - 3rd Avenue Sidewalks | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Nov 2023 | Mar 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10220 | DOT - 3rd Avenue Sidewalks | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Mar 2024 | Sep 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10220 | DOT - 3rd Avenue Sidewalks | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Sep 2024 | Dec 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10220 | DOT - 3rd Avenue Sidewalks | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Dec 2024 | Apr 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10220 | DOT - 3rd Avenue Sidewalks | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Apr 2025 | Aug 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10220 | DOT - 3rd Avenue Sidewalks | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Aug 2025 | Dec 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10220 | DOT - 3rd Avenue Sidewalks | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Dec 2025 | Mar 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10220 | DOT - 3rd Avenue Sidewalks | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Mar 2026 | May 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10220 | DOT - 3rd Avenue Sidewalks | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | May 2026 | Jun 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD102M01 | Forsyth Plaza Kiosk Power/Electrical Improvements | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2025 | Sep 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD102M01 | Forsyth Plaza Kiosk Power/Electrical Improvements | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2025 | Jan 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD102M01 | Forsyth Plaza Kiosk Power/Electrical Improvements | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2026 | Jul 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD102M01 | Forsyth Plaza Kiosk Power/Electrical Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2026 | Oct 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD102M01 | Forsyth Plaza Kiosk Power/Electrical Improvements | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2026 | Feb 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD102M01 | Forsyth Plaza Kiosk Power/Electrical Improvements | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2027 | Jun 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD102M01 | Forsyth Plaza Kiosk Power/Electrical Improvements | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2027 | Oct 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD102M01 | Forsyth Plaza Kiosk Power/Electrical Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2027 | Jan 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD102M01 | Forsyth Plaza Kiosk Power/Electrical Improvements | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2028 | Mar 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD102M01 | Forsyth Plaza Kiosk Power/Electrical Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2028 | Apr 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD200-05 | Sidewalk Reconstruction, 125th St & Lexington | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2026 | Sep 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD200-05 | Sidewalk Reconstruction, 125th St & Lexington | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2026 | Jan 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD200-05 | Sidewalk Reconstruction, 125th St & Lexington | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jan 2027 | Jul 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD200-05 | Sidewalk Reconstruction, 125th St & Lexington | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2027 | Oct 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD200-05 | Sidewalk Reconstruction, 125th St & Lexington | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Oct 2027 | Feb 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD200-05 | Sidewalk Reconstruction, 125th St & Lexington | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Feb 2028 | Jun 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD200-05 | Sidewalk Reconstruction, 125th St & Lexington | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jun 2028 | Oct 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD200-05 | Sidewalk Reconstruction, 125th St & Lexington | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Oct 2028 | Jan 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD200-05 | Sidewalk Reconstruction, 125th St & Lexington | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jan 2029 | Mar 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD200-05 | Sidewalk Reconstruction, 125th St & Lexington | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Mar 2029 | Apr 2031
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM100CTN | 23rd St Crosstown SBS | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Jan 2016 | Mar 2020
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM100CTN | 23rd St Crosstown SBS | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Jan 2021 | Mar 2021
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM100CTN | 23rd St Crosstown SBS | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Jul 2020 | Nov 2021
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM100CTN | 23rd St Crosstown SBS | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Jul 2021 | Nov 2021
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM100CTN | 23rd St Crosstown SBS | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Mar 2022 | Aug 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM100CTN | 23rd St Crosstown SBS | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Aug 2022 | Feb 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM100CTN | 23rd St Crosstown SBS | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Feb 2023 | Jul 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM100CTN | 23rd St Crosstown SBS | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | Jul 2023 | Oct 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM100CTN | 23rd St Crosstown SBS | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Jul 2023 | Sep 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM100CTN | 23rd St Crosstown SBS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Sep 2024 | Jun 2030
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1048 | Manhattan Waterfront Greenway - Inwood 10th Ave | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2024 | Sep 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1048 | Manhattan Waterfront Greenway - Inwood 10th Ave | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1048 | Manhattan Waterfront Greenway - Inwood 10th Ave | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2025 | Jul 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1048 | Manhattan Waterfront Greenway - Inwood 10th Ave | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2025 | Oct 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1048 | Manhattan Waterfront Greenway - Inwood 10th Ave | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2025 | Feb 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1048 | Manhattan Waterfront Greenway - Inwood 10th Ave | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2026 | Jun 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1048 | Manhattan Waterfront Greenway - Inwood 10th Ave | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2026 | Oct 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1048 | Manhattan Waterfront Greenway - Inwood 10th Ave | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2026 | Jan 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1048 | Manhattan Waterfront Greenway - Inwood 10th Ave | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2027 | Mar 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1048 | Manhattan Waterfront Greenway - Inwood 10th Ave | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2027 | Apr 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1687 | Holland Tunnel Area Pedestrian Safety Improvements & Public | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2026 | May 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1687 | Holland Tunnel Area Pedestrian Safety Improvements & Public | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | May 2027 | Sep 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1687 | Holland Tunnel Area Pedestrian Safety Improvements & Public | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Sep 2027 | Mar 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1687 | Holland Tunnel Area Pedestrian Safety Improvements & Public | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Mar 2028 | Jun 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1687 | Holland Tunnel Area Pedestrian Safety Improvements & Public | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Jun 2028 | Oct 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1687 | Holland Tunnel Area Pedestrian Safety Improvements & Public | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Oct 2028 | Feb 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1687 | Holland Tunnel Area Pedestrian Safety Improvements & Public | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Feb 2029 | Jun 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1687 | Holland Tunnel Area Pedestrian Safety Improvements & Public | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Jun 2029 | Sep 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1687 | Holland Tunnel Area Pedestrian Safety Improvements & Public | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Sep 2029 | Nov 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1687 | Holland Tunnel Area Pedestrian Safety Improvements & Public | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Nov 2029 | Dec 2031
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM2026 | Yeshiva University Public Space Improvements Phase 2 | 1 | DESIGN | Jun 2021 | Dec 2021 | Jun 2023 | Dec 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM2026 | Yeshiva University Public Space Improvements Phase 2 | 2 | CONSTRUCTION | Dec 2021 | Jun 2024 | Dec 2023 | Jun 2030
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM2027 | W Houston Pedestrian and Bike Improvements | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2025 | Sep 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM2027 | W Houston Pedestrian and Bike Improvements | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2025 | Jan 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM2027 | W Houston Pedestrian and Bike Improvements | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2026 | Jul 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM2027 | W Houston Pedestrian and Bike Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2026 | Oct 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM2027 | W Houston Pedestrian and Bike Improvements | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2026 | Feb 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM2027 | W Houston Pedestrian and Bike Improvements | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2027 | Jun 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM2027 | W Houston Pedestrian and Bike Improvements | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2027 | Oct 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM2027 | W Houston Pedestrian and Bike Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2027 | Jan 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM2027 | W Houston Pedestrian and Bike Improvements | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2028 | Mar 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM2027 | W Houston Pedestrian and Bike Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2028 | Apr 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM2028 | Security Bollards for the Met's Public Plaza | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2027 | Sep 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM2028 | Security Bollards for the Met's Public Plaza | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2027 | Jan 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM2028 | Security Bollards for the Met's Public Plaza | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2028 | Jul 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM2028 | Security Bollards for the Met's Public Plaza | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2028 | Oct 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM2028 | Security Bollards for the Met's Public Plaza | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2028 | Feb 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM2028 | Security Bollards for the Met's Public Plaza | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2029 | Jun 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM2028 | Security Bollards for the Met's Public Plaza | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2029 | Oct 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM2028 | Security Bollards for the Met's Public Plaza | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2027 | Jan 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM2028 | Security Bollards for the Met's Public Plaza | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2028 | Mar 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM2028 | Security Bollards for the Met's Public Plaza | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2029 | Apr 2030
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMBRT5 | 34th STREET | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2010 | Jun 2010 | Jun 2027 | Jun 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMBRT5 | 34th STREET | 2 | CONSTRUCTION START | Jun 2010 | Jul 2010 | Jun 2027 | Jun 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMBRT5 | 34th STREET | 3 | CONSTRUCTION COMPLETION | Jul 2010 | Feb 2012 | Jun 2028 | Jun 2032
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMBRT6 | 1st & 2nd Avenue | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2010 | Jun 2010 | Jun 2025 | Jun 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMBRT6 | 1st & 2nd Avenue | 2 | CONSTRUCTION START | Jun 2010 | Jul 2010 | Jun 2025 | Jul 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMBRT6 | 1st & 2nd Avenue | 3 | CONSTRUCTION COMPLETION | Jul 2010 | Feb 2012 | Jul 2025 | Jun 2030
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMM009 | GATEWAYS TO CHINATOWN | 1 | DEVELOP SCOPE | Jun 2009 | Sep 2009 | Apr 2012 | Jun 2012
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMM009 | GATEWAYS TO CHINATOWN | 2 | DESIGN START | Sep 2009 | Mar 2011 | Apr 2019 | Feb 2020
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMM009 | GATEWAYS TO CHINATOWN | 3 | CONSTRUCTION START | Mar 2011 | Mar 2013 | Nov 2020 | Aug 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMW215WF | West 215th Street End Waterfront | 1 | DEVELOP SCOPE | Jun 2025 | Sep 2025 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMW215WF | West 215th Street End Waterfront | 2 | PRELIMINARY DESIGN | Sep 2025 | Jan 2026 | Sep 2023 | Jan 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMW215WF | West 215th Street End Waterfront | 3 | FINAL DESIGN | Jan 2026 | Jul 2026 | Jan 2024 | Jul 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMW215WF | West 215th Street End Waterfront | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2026 | Oct 2026 | Jul 2024 | Oct 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMW215WF | West 215th Street End Waterfront | 5 | CONSTRUCTION TO 25% | Oct 2026 | Feb 2027 | Oct 2024 | Feb 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMW215WF | West 215th Street End Waterfront | 6 | CONSTRUCTION TO 50% | Feb 2027 | Jun 2027 | Feb 2025 | Jun 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMW215WF | West 215th Street End Waterfront | 7 | CONSTRUCTION TO 75% | Jun 2027 | Oct 2027 | Jun 2025 | Oct 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMW215WF | West 215th Street End Waterfront | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jan 2028 | Oct 2025 | Jan 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMW215WF | West 215th Street End Waterfront | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Mar 2028 | Jan 2026 | Mar 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMW215WF | West 215th Street End Waterfront | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2028 | Apr 2028 | Mar 2026 | Apr 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMW216WF | West 216th Street End Waterfront | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMW216WF | West 216th Street End Waterfront | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMW216WF | West 216th Street End Waterfront | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMW216WF | West 216th Street End Waterfront | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMW216WF | West 216th Street End Waterfront | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMW216WF | West 216th Street End Waterfront | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMW216WF | West 216th Street End Waterfront | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMW216WF | West 216th Street End Waterfront | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMW216WF | West 216th Street End Waterfront | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMW216WF | West 216th Street End Waterfront | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A8 | WORLD TRADE CENTER AREA 8 | 1 | DEVELOP SCOPE | Jun 2009 | Sep 2009 | Jun 2019 | Sep 2019
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A8 | WORLD TRADE CENTER AREA 8 | 2 | PRELIMINARY DESIGN | Sep 2009 | Jan 2010 | Sep 2019 | Jan 2020
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A8 | WORLD TRADE CENTER AREA 8 | 3 | FINAL DESIGN | Jan 2010 | Jul 2010 | Jan 2020 | Jul 2020
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A8 | WORLD TRADE CENTER AREA 8 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2010 | Oct 2010 | Jul 2020 | Oct 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A8 | WORLD TRADE CENTER AREA 8 | 5 | CONSTRUCTION TO 25% | Oct 2010 | Feb 2011 | Oct 2028 | Feb 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A8 | WORLD TRADE CENTER AREA 8 | 6 | CONSTRUCTION TO 50% | Feb 2011 | Jun 2011 | Feb 2029 | Jun 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A8 | WORLD TRADE CENTER AREA 8 | 7 | CONSTRUCTION TO 75% | Jun 2011 | Oct 2011 | Jun 2029 | Oct 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A8 | WORLD TRADE CENTER AREA 8 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2011 | Jan 2012 | Oct 2029 | Jan 2030
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A8 | WORLD TRADE CENTER AREA 8 | 9 | SUBSTANTIAL COMPLETION | Jan 2012 | Mar 2012 | Jan 2030 | Mar 2030
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A8 | WORLD TRADE CENTER AREA 8 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2012 | Apr 2012 | Mar 2030 | Jul 2031
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A9 | WORLD TRADE CENTER AREA 9. | 1 | DEVELOP SCOPE | Jun 2009 | Sep 2009 | Jun 2017 | Sep 2017
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A9 | WORLD TRADE CENTER AREA 9. | 2 | PRELIMINARY DESIGN | Sep 2009 | Jan 2010 | Sep 2017 | Jan 2018
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A9 | WORLD TRADE CENTER AREA 9. | 3 | FINAL DESIGN | Jan 2010 | Jul 2010 | Jan 2018 | Jul 2018
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A9 | WORLD TRADE CENTER AREA 9. | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2010 | Oct 2010 | Jul 2018 | Oct 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A9 | WORLD TRADE CENTER AREA 9. | 5 | CONSTRUCTION TO 25% | Oct 2010 | Feb 2011 | Oct 2026 | Feb 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A9 | WORLD TRADE CENTER AREA 9. | 6 | CONSTRUCTION TO 50% | Feb 2011 | Jun 2011 | Feb 2027 | Jun 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A9 | WORLD TRADE CENTER AREA 9. | 7 | CONSTRUCTION TO 75% | Jun 2011 | Oct 2011 | Jun 2027 | Oct 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A9 | WORLD TRADE CENTER AREA 9. | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2011 | Jan 2012 | Oct 2027 | Jan 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A9 | WORLD TRADE CENTER AREA 9. | 9 | SUBSTANTIAL COMPLETION | Jan 2012 | Mar 2012 | Jan 2028 | Mar 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A9 | WORLD TRADE CENTER AREA 9. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2012 | Apr 2012 | Mar 2029 | Apr 2031
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC11 | WORLD TRADE CENTER AREA 11 | 5 | CONSTRUCTION TO 25% | Oct 2011 | Feb 2012 | Oct 2020 | Feb 2021
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC11 | WORLD TRADE CENTER AREA 11 | 6 | CONSTRUCTION TO 50% | Feb 2012 | Jun 2012 | Feb 2021 | Jun 2021
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC11 | WORLD TRADE CENTER AREA 11 | 7 | CONSTRUCTION TO 75% | Jun 2012 | Oct 2012 | Jun 2021 | Oct 2021
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC11 | WORLD TRADE CENTER AREA 11 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2012 | Jan 2013 | Oct 2021 | Jan 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC11 | WORLD TRADE CENTER AREA 11 | 9 | SUBSTANTIAL COMPLETION | Jan 2013 | Mar 2013 | Jan 2022 | Mar 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC11 | WORLD TRADE CENTER AREA 11 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2013 | Apr 2013 | Mar 2022 | Jun 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCA10 | WORLD TRADE CENTER AREA 10 | 2 | PRELIMINARY DESIGN | Sep 2010 | Jan 2011 | Sep 2017 | Jan 2018
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCA10 | WORLD TRADE CENTER AREA 10 | 3 | FINAL DESIGN | Jan 2011 | Jul 2011 | Jan 2018 | Jul 2018
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCA10 | WORLD TRADE CENTER AREA 10 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2011 | Oct 2011 | Jul 2018 | Oct 2018
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCA10 | WORLD TRADE CENTER AREA 10 | 5 | CONSTRUCTION TO 25% | Oct 2011 | Feb 2012 | Oct 2018 | Feb 2019
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCA10 | WORLD TRADE CENTER AREA 10 | 6 | CONSTRUCTION TO 50% | Feb 2012 | Jun 2012 | Feb 2019 | Jun 2019
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCA10 | WORLD TRADE CENTER AREA 10 | 7 | CONSTRUCTION TO 75% | Jun 2012 | Oct 2012 | Jun 2019 | Oct 2019
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCA10 | WORLD TRADE CENTER AREA 10 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2012 | Jan 2013 | Oct 2019 | Jan 2020
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCA10 | WORLD TRADE CENTER AREA 10 | 9 | SUBSTANTIAL COMPLETION | Jan 2013 | Mar 2013 | Jan 2020 | Mar 2020
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCA10 | WORLD TRADE CENTER AREA 10 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2013 | Apr 2013 | Mar 2020 | Jun 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB3 | Reconstruction of Broadway | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Mar 2035 | Jul 2035
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB3 | Reconstruction of Broadway | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Apr 2017 | Jan 2018
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB3 | Reconstruction of Broadway | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2018 | Aug 2018
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB3 | Reconstruction of Broadway | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Feb 2019 | Mar 2019
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB3 | Reconstruction of Broadway | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Mar 2019 | Jun 2019
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB3 | Reconstruction of Broadway | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Jun 2019 | Aug 2019
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB3 | Reconstruction of Broadway | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Aug 2019 | Oct 2019
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB3 | Reconstruction of Broadway | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2024 | Jun 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB3 | Reconstruction of Broadway | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jul 2026 | Jan 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB3 | Reconstruction of Broadway | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Jan 2028 | Jun 2031
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB4 | Reconstruction of Varick St | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Oct 2021 | Jan 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB4 | Reconstruction of Varick St | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Apr 2021 | Jan 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB4 | Reconstruction of Varick St | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB4 | Reconstruction of Varick St | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Feb 2023 | Mar 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB4 | Reconstruction of Varick St | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Mar 2023 | Sep 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB4 | Reconstruction of Varick St | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Sep 2023 | Feb 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB4 | Reconstruction of Varick St | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Feb 2024 | Aug 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB4 | Reconstruction of Varick St | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Aug 2024 | Nov 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB4 | Reconstruction of Varick St | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Aug 2024 | Jan 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB4 | Reconstruction of Varick St | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Jan 2025 | Jun 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MC1 | Non-Standard Ped Ramps - Manhattan | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MC1 | Non-Standard Ped Ramps - Manhattan | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MC1 | Non-Standard Ped Ramps - Manhattan | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MC1 | Non-Standard Ped Ramps - Manhattan | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MC1 | Non-Standard Ped Ramps - Manhattan | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MC1 | Non-Standard Ped Ramps - Manhattan | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MC1 | Non-Standard Ped Ramps - Manhattan | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MC1 | Non-Standard Ped Ramps - Manhattan | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MC1 | Non-Standard Ped Ramps - Manhattan | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MC1 | Non-Standard Ped Ramps - Manhattan | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MC2 | Non-Standard Ped Ramps - Manhattan | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MC2 | Non-Standard Ped Ramps - Manhattan | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MC2 | Non-Standard Ped Ramps - Manhattan | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MC2 | Non-Standard Ped Ramps - Manhattan | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MC2 | Non-Standard Ped Ramps - Manhattan | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MC2 | Non-Standard Ped Ramps - Manhattan | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MC2 | Non-Standard Ped Ramps - Manhattan | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MC2 | Non-Standard Ped Ramps - Manhattan | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MC2 | Non-Standard Ped Ramps - Manhattan | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWP23MC2 | Non-Standard Ped Ramps - Manhattan | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ010M | Flatiron Plaza Reconstruction | 1 | DEVELOP SCOPE | Jun 2013 | Sep 2013 | Jun 2025 | Sep 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ010M | Flatiron Plaza Reconstruction | 2 | PRELIMINARY DESIGN | Sep 2013 | Jan 2014 | Sep 2025 | Jan 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ010M | Flatiron Plaza Reconstruction | 3 | FINAL DESIGN | Jan 2014 | Jul 2014 | Jan 2026 | Jul 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ010M | Flatiron Plaza Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2014 | Oct 2014 | Jul 2026 | Oct 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ010M | Flatiron Plaza Reconstruction | 5 | CONSTRUCTION TO 25% | Oct 2014 | Feb 2015 | Oct 2026 | Feb 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ010M | Flatiron Plaza Reconstruction | 6 | CONSTRUCTION TO 50% | Feb 2015 | Jun 2015 | Feb 2027 | Jun 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ010M | Flatiron Plaza Reconstruction | 7 | CONSTRUCTION TO 75% | Jun 2015 | Oct 2015 | Jun 2027 | Oct 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ010M | Flatiron Plaza Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2015 | Jan 2016 | Oct 2027 | Jan 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ010M | Flatiron Plaza Reconstruction | 9 | SUBSTANTIAL COMPLETION | Jan 2016 | Mar 2016 | Jan 2028 | Mar 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ010M | Flatiron Plaza Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Apr 2016 | Mar 2028 | Apr 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ016M | Hamilton Place Plaza | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2027 | Sep 2031
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ016M | Hamilton Place Plaza | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2027 | Jan 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ016M | Hamilton Place Plaza | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2028 | Jul 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ016M | Hamilton Place Plaza | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2028 | Oct 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ016M | Hamilton Place Plaza | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2028 | Feb 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ016M | Hamilton Place Plaza | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2029 | Jun 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ016M | Hamilton Place Plaza | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2029 | Oct 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ016M | Hamilton Place Plaza | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2027 | Jan 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ016M | Hamilton Place Plaza | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2028 | Mar 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ016M | Hamilton Place Plaza | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2028 | Apr 2031
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ018M | Quisqueya Plaza | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ018M | Quisqueya Plaza | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ018M | Quisqueya Plaza | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ018M | Quisqueya Plaza | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ018M | Quisqueya Plaza | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ018M | Quisqueya Plaza | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ018M | Quisqueya Plaza | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ018M | Quisqueya Plaza | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ018M | Quisqueya Plaza | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ018M | Quisqueya Plaza | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ019M | Midtown/Broadway Vision | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ019M | Midtown/Broadway Vision | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ019M | Midtown/Broadway Vision | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ019M | Midtown/Broadway Vision | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ019M | Midtown/Broadway Vision | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ019M | Midtown/Broadway Vision | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ019M | Midtown/Broadway Vision | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ019M | Midtown/Broadway Vision | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ019M | Midtown/Broadway Vision | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ019M | Midtown/Broadway Vision | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPSMGANC | Gansevoort/Astor Planters | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2029 | Sep 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPSMGANC | Gansevoort/Astor Planters | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2029 | Jan 2030
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPSMGANC | Gansevoort/Astor Planters | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2030 | Jul 2030
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPSMGANC | Gansevoort/Astor Planters | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2030 | Oct 2030
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPSMGANC | Gansevoort/Astor Planters | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2030 | Feb 2031
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPSMGANC | Gansevoort/Astor Planters | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2031 | Jun 2031
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPSMGANC | Gansevoort/Astor Planters | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2031 | Oct 2031
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPSMGANC | Gansevoort/Astor Planters | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2031 | Jan 2032
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPSMGANC | Gansevoort/Astor Planters | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2032 | Mar 2032
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPSMGANC | Gansevoort/Astor Planters | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2032 | Apr 2032
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024M | Prior Notice Sidewalks - Manhattan | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2026 | Sep 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024M | Prior Notice Sidewalks - Manhattan | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2026 | Jan 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024M | Prior Notice Sidewalks - Manhattan | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2027 | Jul 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024M | Prior Notice Sidewalks - Manhattan | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2027 | Oct 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024M | Prior Notice Sidewalks - Manhattan | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2027 | Feb 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024M | Prior Notice Sidewalks - Manhattan | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2028 | Jun 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024M | Prior Notice Sidewalks - Manhattan | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2028 | Oct 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024M | Prior Notice Sidewalks - Manhattan | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2026 | Jan 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024M | Prior Notice Sidewalks - Manhattan | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2028 | Mar 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024M | Prior Notice Sidewalks - Manhattan | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2030 | Apr 2033
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWTFLMAD | Street Lamp Posts on Madison Avenue | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWTFLMAD | Street Lamp Posts on Madison Avenue | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2023 | Jan 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWTFLMAD | Street Lamp Posts on Madison Avenue | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2024 | Jul 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWTFLMAD | Street Lamp Posts on Madison Avenue | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2024 | Oct 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWTFLMAD | Street Lamp Posts on Madison Avenue | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2024 | Feb 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWTFLMAD | Street Lamp Posts on Madison Avenue | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2025 | Jun 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWTFLMAD | Street Lamp Posts on Madison Avenue | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2025 | Oct 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWTFLMAD | Street Lamp Posts on Madison Avenue | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2025 | Jan 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWTFLMAD | Street Lamp Posts on Madison Avenue | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2026 | Mar 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWTFLMAD | Street Lamp Posts on Madison Avenue | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2026 | Apr 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWWTCLUMP | World Trade Center - Lump Sum | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWWTCLUMP | World Trade Center - Lump Sum | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWWTCLUMP | World Trade Center - Lump Sum | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2023 | Jul 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWWTCLUMP | World Trade Center - Lump Sum | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2023 | Oct 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWWTCLUMP | World Trade Center - Lump Sum | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2023 | Feb 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWWTCLUMP | World Trade Center - Lump Sum | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2024 | Jun 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWWTCLUMP | World Trade Center - Lump Sum | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2024 | Oct 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWWTCLUMP | World Trade Center - Lump Sum | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2024 | Jan 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWWTCLUMP | World Trade Center - Lump Sum | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2025 | Mar 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWWTCLUMP | World Trade Center - Lump Sum | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2025 | Jul 2031
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | NDF-IW10A | NDF - Improve Prioroity intersections along 10th Ave | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | NDF-IW10A | NDF - Improve Prioroity intersections along 10th Ave | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | NDF-IW10A | NDF - Improve Prioroity intersections along 10th Ave | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | NDF-IW10A | NDF - Improve Prioroity intersections along 10th Ave | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | NDF-IW10A | NDF - Improve Prioroity intersections along 10th Ave | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | NDF-IW10A | NDF - Improve Prioroity intersections along 10th Ave | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | NDF-IW10A | NDF - Improve Prioroity intersections along 10th Ave | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | NDF-IW10A | NDF - Improve Prioroity intersections along 10th Ave | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | NDF-IW10A | NDF - Improve Prioroity intersections along 10th Ave | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | NDF-IW10A | NDF - Improve Prioroity intersections along 10th Ave | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Jun 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | NDF-IWEIS | NDF - EIS Transportation Mitigation Inwood | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | NDF-IWEIS | NDF - EIS Transportation Mitigation Inwood | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | NDF-IWEIS | NDF - EIS Transportation Mitigation Inwood | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | NDF-IWEIS | NDF - EIS Transportation Mitigation Inwood | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | NDF-IWEIS | NDF - EIS Transportation Mitigation Inwood | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | NDF-IWEIS | NDF - EIS Transportation Mitigation Inwood | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | NDF-IWEIS | NDF - EIS Transportation Mitigation Inwood | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | NDF-IWEIS | NDF - EIS Transportation Mitigation Inwood | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | NDF-IWEIS | NDF - EIS Transportation Mitigation Inwood | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | NDF-IWEIS | NDF - EIS Transportation Mitigation Inwood | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Jun 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | P-3RVOVER | Rec of the Riverside Park Amtrak Overbuild 2271180 & 2271190 | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | P-3RVOVER | Rec of the Riverside Park Amtrak Overbuild 2271180 & 2271190 | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | P-3RVOVER | Rec of the Riverside Park Amtrak Overbuild 2271180 & 2271190 | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | P-3RVOVER | Rec of the Riverside Park Amtrak Overbuild 2271180 & 2271190 | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | P-3RVOVER | Rec of the Riverside Park Amtrak Overbuild 2271180 & 2271190 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | REALTIMEM | Real Time Traffic Monitoring in Lower Manhattan | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Jun 2019 | Jun 2023 | Jul 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | REALTIMEM | Real Time Traffic Monitoring in Lower Manhattan | 2 | CONSTRUCTION START | Jul 2019 | Aug 2019 | Jul 2023 | Sep 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | REALTIMEM | Real Time Traffic Monitoring in Lower Manhattan | 3 | CONSTRUCTION COMPLETION | Aug 2019 | Mar 2021 | Sep 2023 | Apr 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | REALTMIDM | Expand Real Time Traffic Monitoring in Midtown Manhattan | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Jun 2019 | Jun 2019 | Jun 2019
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | REALTMIDM | Expand Real Time Traffic Monitoring in Midtown Manhattan | 2 | CONSTRUCTION START | Jul 2019 | Aug 2019 | Jul 2019 | Aug 2019
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | REALTMIDM | Expand Real Time Traffic Monitoring in Midtown Manhattan | 3 | CONSTRUCTION COMPLETION | Aug 2019 | Mar 2021 | Aug 2019 | Mar 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHB2U | SANDY ER BETTERMENTS FOR BATTERY PARK & WEST ST UNDERPASSES | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2021
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHB2U | SANDY ER BETTERMENTS FOR BATTERY PARK & WEST ST UNDERPASSES | 2 | DESIGN START | Jun 2021 | Jun 2025 | Jun 2018 | Mar 2019
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHB2U | SANDY ER BETTERMENTS FOR BATTERY PARK & WEST ST UNDERPASSES | 3 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Mar 2019 | Mar 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHB2U | SANDY ER BETTERMENTS FOR BATTERY PARK & WEST ST UNDERPASSES | 5 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Mar 2023 | Mar 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHBFDR | SANDY ER FOR FDR 18TH TO 25TH STREET | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2021
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHBFDR | SANDY ER FOR FDR 18TH TO 25TH STREET | 2 | DESIGN START | Jun 2021 | Jun 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHBFDR | SANDY ER FOR FDR 18TH TO 25TH STREET | 3 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Nov 2015 | Nov 2019
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHBFDR | SANDY ER FOR FDR 18TH TO 25TH STREET | 5 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Nov 2019 | Nov 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW27 | Montgomery to 15th Street - Hurricane Sandy | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Aug 2023 | Jan 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW27 | Montgomery to 15th Street - Hurricane Sandy | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Jun 2021 | Oct 2021
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW27 | Montgomery to 15th Street - Hurricane Sandy | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Mar 2021 | Sep 2021
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW27 | Montgomery to 15th Street - Hurricane Sandy | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Aug 2023 | Jan 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW27 | Montgomery to 15th Street - Hurricane Sandy | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Jan 2024 | May 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW27 | Montgomery to 15th Street - Hurricane Sandy | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Jan 2024 | Jun 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW27 | Montgomery to 15th Street - Hurricane Sandy | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2024 | Nov 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW27 | Montgomery to 15th Street - Hurricane Sandy | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Nov 2024 | Feb 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW27 | Montgomery to 15th Street - Hurricane Sandy | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Feb 2025 | Apr 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW27 | Montgomery to 15th Street - Hurricane Sandy | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Apr 2025 | Jun 2030
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFCPARKLG | Central Park Light Infrastructure | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2015 | Jun 2015 | Mar 2028 | Apr 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFCPARKLG | Central Park Light Infrastructure | 2 | CONSTRUCTION START | Jun 2015 | Jul 2015 | May 2029 | May 2030
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFCPARKLG | Central Park Light Infrastructure | 3 | CONSTRUCTION COMPLETION | Jul 2015 | Feb 2017 | May 2030 | Jun 2031
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503-20 | DOWNTOWN ALLIANCE-HISTORIC LIGHTPOLES | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2009 | Jun 2009 | Jun 2024 | Jun 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503-20 | DOWNTOWN ALLIANCE-HISTORIC LIGHTPOLES | 2 | CONSTRUCTION START | Jun 2009 | Jul 2009 | Jun 2024 | Jul 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503-20 | DOWNTOWN ALLIANCE-HISTORIC LIGHTPOLES | 3 | CONSTRUCTION COMPLETION | Jul 2009 | Feb 2011 | Jul 2024 | Feb 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M24 | FLATIRON DISTINCTIVE LIGHTING ALONG 23rd ST. 3rd to 6th AV. | 3 | CONSTRUCTION COMPLETION | Aug 2011 | Mar 2013 | Aug 2014 | Mar 2016
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M27 | REPLACE AND INSTALL ST LG IN FASHION CENTER BUSINESS IMPRV | 3 | CONSTRUCTION COMPLETION | Jul 2015 | Feb 2017 | Jul 2015 | Feb 2017
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M29 | Second Avenue Street lights | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M29 | Second Avenue Street lights | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M29 | Second Avenue Street lights | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2023 | Jul 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M29 | Second Avenue Street lights | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2023 | Oct 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M29 | Second Avenue Street lights | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2023 | Feb 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M29 | Second Avenue Street lights | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2024 | Jun 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M29 | Second Avenue Street lights | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2024 | Oct 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M29 | Second Avenue Street lights | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2024 | Jan 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M29 | Second Avenue Street lights | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2025 | Mar 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M29 | Second Avenue Street lights | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2025 | Apr 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M30 | Garment District street light,Manhattan | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M30 | Garment District street light,Manhattan | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M30 | Garment District street light,Manhattan | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2023 | Jul 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M30 | Garment District street light,Manhattan | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2023 | Oct 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M30 | Garment District street light,Manhattan | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2023 | Feb 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M30 | Garment District street light,Manhattan | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2024 | Jun 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M30 | Garment District street light,Manhattan | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2024 | Oct 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M30 | Garment District street light,Manhattan | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2024 | Jan 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M30 | Garment District street light,Manhattan | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2025 | Mar 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M30 | Garment District street light,Manhattan | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2025 | Apr 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M31 | Historic St lg on 11th St and on 12th St, Manhattan | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jun 2025 | Sep 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M31 | Historic St lg on 11th St and on 12th St, Manhattan | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Sep 2025 | Jan 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M31 | Historic St lg on 11th St and on 12th St, Manhattan | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2026 | Jul 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M31 | Historic St lg on 11th St and on 12th St, Manhattan | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2026 | Oct 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M31 | Historic St lg on 11th St and on 12th St, Manhattan | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2026 | Feb 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M31 | Historic St lg on 11th St and on 12th St, Manhattan | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2027 | Jun 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M31 | Historic St lg on 11th St and on 12th St, Manhattan | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2027 | Oct 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M31 | Historic St lg on 11th St and on 12th St, Manhattan | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2027 | Jan 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M31 | Historic St lg on 11th St and on 12th St, Manhattan | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2028 | Mar 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M31 | Historic St lg on 11th St and on 12th St, Manhattan | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2029 | Apr 2031
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M33 | GREENWICH VILLAGE DECORATIVE LIGHTING | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2024 | Sep 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M33 | GREENWICH VILLAGE DECORATIVE LIGHTING | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M33 | GREENWICH VILLAGE DECORATIVE LIGHTING | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jan 2025 | Jul 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M33 | GREENWICH VILLAGE DECORATIVE LIGHTING | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2025 | Oct 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M33 | GREENWICH VILLAGE DECORATIVE LIGHTING | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Oct 2025 | Feb 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M33 | GREENWICH VILLAGE DECORATIVE LIGHTING | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Feb 2026 | Jun 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M33 | GREENWICH VILLAGE DECORATIVE LIGHTING | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jun 2026 | Oct 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M33 | GREENWICH VILLAGE DECORATIVE LIGHTING | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Oct 2026 | Jan 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M33 | GREENWICH VILLAGE DECORATIVE LIGHTING | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jan 2027 | Mar 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M33 | GREENWICH VILLAGE DECORATIVE LIGHTING | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Mar 2027 | Apr 2030
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M34 | Lg Poles on Crosby and Bleecker- NOHO, Manhattan | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Jun 2021 | Jun 2025 | Jun 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M34 | Lg Poles on Crosby and Bleecker- NOHO, Manhattan | 2 | CONSTRUCTION START | Jun 2021 | Jun 2021 | Jun 2025 | Jun 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M34 | Lg Poles on Crosby and Bleecker- NOHO, Manhattan | 3 | CONSTRUCTION COMPLETION | Jun 2021 | Jun 2021 | Jun 2025 | Jun 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M35 | JUMEL TERRACE HISTORIC DISTRICT LIGHTING, MANHATTAN | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Jun 2023 | Jun 2027 | Jul 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M35 | JUMEL TERRACE HISTORIC DISTRICT LIGHTING, MANHATTAN | 2 | CONSTRUCTION START | Jul 2023 | Aug 2023 | Jul 2027 | Aug 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M35 | JUMEL TERRACE HISTORIC DISTRICT LIGHTING, MANHATTAN | 3 | CONSTRUCTION COMPLETION | Aug 2023 | Mar 2025 | Aug 2027 | Mar 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFM50311 | INSTALL S-POLE LIGHTING- VARIOUS STREETS WEST OF BROADWAY | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2009 | Jun 2009 | Jun 2024 | Jun 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFM50311 | INSTALL S-POLE LIGHTING- VARIOUS STREETS WEST OF BROADWAY | 2 | CONSTRUCTION START | Jun 2009 | Jul 2009 | Jun 2024 | Jul 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFM50311 | INSTALL S-POLE LIGHTING- VARIOUS STREETS WEST OF BROADWAY | 3 | CONSTRUCTION COMPLETION | Jul 2009 | Feb 2011 | Jul 2024 | Feb 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFM50316 | Frederick Douglas Blvd Street Lamps | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2013 | Jun 2013 | Jun 2026 | Jun 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFM50316 | Frederick Douglas Blvd Street Lamps | 2 | CONSTRUCTION START | Jul 2013 | Aug 2013 | Jul 2026 | Aug 2026
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFM50316 | Frederick Douglas Blvd Street Lamps | 3 | CONSTRUCTION COMPLETION | Aug 2013 | Mar 2015 | Aug 2026 | Mar 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFM50320 | Union Square - 14th Street Lighting Upgrades, MANHATTAN | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Jun 2023 | Jun 2027 | Jun 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFM50320 | Union Square - 14th Street Lighting Upgrades, MANHATTAN | 2 | CONSTRUCTION START | Jul 2023 | Aug 2023 | Jul 2027 | Aug 2027
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFM50320 | Union Square - 14th Street Lighting Upgrades, MANHATTAN | 3 | CONSTRUCTION COMPLETION | Aug 2023 | Mar 2025 | Aug 2027 | Mar 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFM50321 | WEST VILLAGE UPGRADE LAMPPOST TO BISHOP CROOK, MANHATTAN | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Jun 2023 | Jun 2027 | Jul 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFM50321 | WEST VILLAGE UPGRADE LAMPPOST TO BISHOP CROOK, MANHATTAN | 2 | CONSTRUCTION START | Jul 2023 | Aug 2023 | Jul 2028 | Aug 2028
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFM50321 | WEST VILLAGE UPGRADE LAMPPOST TO BISHOP CROOK, MANHATTAN | 3 | CONSTRUCTION COMPLETION | Aug 2023 | Mar 2025 | Aug 2028 | Mar 2029
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | W147LIGH | West 147th Street Sugar Hill Historical Street Lights | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Jun 2019 | Jun 2021 | Jun 2021
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | W147LIGH | West 147th Street Sugar Hill Historical Street Lights | 2 | CONSTRUCTION START | Jul 2019 | Aug 2019 | Jul 2021 | Aug 2021
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | W147LIGH | West 147th Street Sugar Hill Historical Street Lights | 3 | CONSTRUCTION COMPLETION | Aug 2019 | Mar 2021 | Aug 2021 | Mar 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | WHTGIRDS2 | Whitehall Ferry Terminal-Slip2 Girder Reconstruction | 1 | DEVELOP SCOPE | Jun 2019 | Jun 2020 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | WHTGIRDS2 | Whitehall Ferry Terminal-Slip2 Girder Reconstruction | 2 | DESIGN START | Jun 2020 | Jun 2022 | Jun 2022 | Jun 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | WHTGIRDS2 | Whitehall Ferry Terminal-Slip2 Girder Reconstruction | 3 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Jun 2024 | Jun 2031
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | WHTGIRDS3 | Whitehall Ferry Terminal-Slip3 Girder Reconstruction | 1 | DEVELOP SCOPE | Jun 2019 | Jun 2020 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | WHTGIRDS3 | Whitehall Ferry Terminal-Slip3 Girder Reconstruction | 2 | DESIGN START | Jun 2020 | Jun 2022 | Jun 2023 | Jun 2024
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | WHTGIRDS3 | Whitehall Ferry Terminal-Slip3 Girder Reconstruction | 3 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Jun 2024 | Jun 2031
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | WHTLBRIDG | Whitehall Slips 1,2,3 Bridge Reconstruction | 1 | DEVELOP SCOPE | Jun 2019 | Jun 2020 | Jun 2022 | Jun 2023
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | WHTLBRIDG | Whitehall Slips 1,2,3 Bridge Reconstruction | 2 | DESIGN START | Jun 2020 | Jun 2022 | Jun 2023 | Jun 2025
20231026 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | WHTLBRIDG | Whitehall Slips 1,2,3 Bridge Reconstruction | 3 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Jun 2025 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | 5AVEPOSTS | CP SOUTH LAMP POSTS (5TH AVE - 8TH AVE) M010-103M | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | 5AVEPOSTS | CP SOUTH LAMP POSTS (5TH AVE - 8TH AVE) M010-103M | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | 5AVEPOSTS | CP SOUTH LAMP POSTS (5TH AVE - 8TH AVE) M010-103M | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | 5AVEPOSTS | CP SOUTH LAMP POSTS (5TH AVE - 8TH AVE) M010-103M | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | 5AVEPOSTS | CP SOUTH LAMP POSTS (5TH AVE - 8TH AVE) M010-103M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | ACEDPR408 | Centralized HVAC Controls CNYG-1317MA | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Jun 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | ACEDPR704 | DPR - BMS (Building Management System) INSTALLATION | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | ACEDPR704 | DPR - BMS (Building Management System) INSTALLATION | 2 | DESIGN | Dec 2019 | Jun 2021 | Dec 2019 | Jun 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | ACEDPR704 | DPR - BMS (Building Management System) INSTALLATION | 3 | BID/ REGISTER CONTRACT | Jun 2021 | Mar 2022 | Jun 2021 | Mar 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | ACEDPR704 | DPR - BMS (Building Management System) INSTALLATION | 4 | CONSTRUCTION | Mar 2022 | Sep 2023 | Mar 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | ACEDPR704 | DPR - BMS (Building Management System) INSTALLATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | EDMFPM | FERRY PIER AT DYCKMAN MARINA | 1 | DESIGN | Jun 2017 | Jul 2017 | Jun 2017 | Jul 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | EDMFPM | FERRY PIER AT DYCKMAN MARINA | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Aug 2017 | Jul 2017 | Aug 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | EDMFPM | FERRY PIER AT DYCKMAN MARINA | 3 | CONSTRUCTION | Aug 2017 | Sep 2017 | Aug 2017 | Sep 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | EDMFPM | FERRY PIER AT DYCKMAN MARINA | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Sep 2017 | Sep 2017 | Sep 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | EDMFPM | FERRY PIER AT DYCKMAN MARINA | 5 | SUBSTANTIAL COMPLETION | Sep 2017 | Oct 2017 | Sep 2017 | Oct 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | EDMFPM | FERRY PIER AT DYCKMAN MARINA | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2017 | Jun 2020 | Oct 2017 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-DYMAN | NDF - Highbridge Park Dyckman Rest Reconstruction M037-121M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-DYMAN | NDF - Highbridge Park Dyckman Rest Reconstruction M037-121M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-DYMAN | NDF - Highbridge Park Dyckman Rest Reconstruction M037-121M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-DYMAN | NDF - Highbridge Park Dyckman Rest Reconstruction M037-121M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-DYMAN | NDF - Highbridge Park Dyckman Rest Reconstruction M037-121M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-HRPCS | NDF Harlem River Park (M208D) - New PRB | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-HRPCS | NDF Harlem River Park (M208D) - New PRB | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-HRPCS | NDF Harlem River Park (M208D) - New PRB | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-HRPCS | NDF Harlem River Park (M208D) - New PRB | 4 | CONSTRUCTION | Sep 2019 | Mar 2021 | Sep 2019 | Mar 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-HRPCS | NDF Harlem River Park (M208D) - New PRB | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Mar 2022 | Mar 2021 | Jun 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-IWOOD | NDF - Inwood Hill Park Soccer Field #1 R/C | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Nov 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-IWOOD | NDF - Inwood Hill Park Soccer Field #1 R/C | 2 | DESIGN | Dec 2018 | Dec 2019 | Nov 2019 | Apr 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-IWOOD | NDF - Inwood Hill Park Soccer Field #1 R/C | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Aug 2023 | Oct 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-IWOOD | NDF - Inwood Hill Park Soccer Field #1 R/C | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Jan 2023 | Jan 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-IWOOD | NDF - Inwood Hill Park Soccer Field #1 R/C | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Jan 2024 | Jan 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-MKETT | NDF - Monsignor Kett Playground R/C, M199-219M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-MKETT | NDF - Monsignor Kett Playground R/C, M199-219M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-MKETT | NDF - Monsignor Kett Playground R/C, M199-219M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-MKETT | NDF - Monsignor Kett Playground R/C, M199-219M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-MKETT | NDF - Monsignor Kett Playground R/C, M199-219M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2031
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300EAST | East River Esplanade Projects - M108-119M | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Sep 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300EAST | East River Esplanade Projects - M108-119M | 2 | DESIGN | Sep 2014 | Dec 2014 | Sep 2017 | Dec 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300EAST | East River Esplanade Projects - M108-119M | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2017 | Mar 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300EAST | East River Esplanade Projects - M108-119M | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2018 | Mar 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300EAST | East River Esplanade Projects - M108-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2019 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ERES | East River Esplanade GLICK PK RC | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ERES | East River Esplanade GLICK PK RC | 2 | DESIGN | Dec 2017 | Jun 2019 | Dec 2017 | Jun 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ERES | East River Esplanade GLICK PK RC | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Mar 2020 | Jun 2019 | Mar 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ERES | East River Esplanade GLICK PK RC | 4 | CONSTRUCTION | Mar 2020 | Sep 2021 | Mar 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ERES | East River Esplanade GLICK PK RC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300FDCG | Frederick Douglass Boulevard Community Garden Restoration | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300FDCG | Frederick Douglass Boulevard Community Garden Restoration | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300FDCG | Frederick Douglass Boulevard Community Garden Restoration | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300FDCG | Frederick Douglass Boulevard Community Garden Restoration | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300LMDC | LMDC-(BUNDLED) PROJECTS MG-703M | 1 | DEVELOP SCOPE | Jul 2003 | Jul 2003 | Jun 2008 | Nov 2008
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300LMDC | LMDC-(BUNDLED) PROJECTS MG-703M | 2 | DESIGN | Jul 2003 | Jul 2003 | Nov 2008 | Nov 2009
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300LMDC | LMDC-(BUNDLED) PROJECTS MG-703M | 3 | BID/ REGISTER CONTRACT | Aug 2003 | Oct 2003 | Nov 2009 | Jul 2010
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300LMDC | LMDC-(BUNDLED) PROJECTS MG-703M | 4 | CONSTRUCTION | Nov 2003 | Nov 2004 | Jul 2010 | Jul 2011
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300LMDC | LMDC-(BUNDLED) PROJECTS MG-703M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2004 | Nov 2005 | Jul 2011 | Mar 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO18 | Central Park Zoo - Sea Lion Exhibit Renovation | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2023 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO18 | Central Park Zoo - Sea Lion Exhibit Renovation | 2 | DESIGN | Dec 2017 | Mar 2019 | Dec 2023 | Mar 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO18 | Central Park Zoo - Sea Lion Exhibit Renovation | 3 | BID/ REGISTER CONTRACT | Mar 2019 | Dec 2019 | Mar 2025 | Dec 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO18 | Central Park Zoo - Sea Lion Exhibit Renovation | 4 | CONSTRUCTION | Dec 2019 | Dec 2020 | Dec 2025 | Dec 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO18 | Central Park Zoo - Sea Lion Exhibit Renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2020 | Dec 2021 | Dec 2026 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO19 | Central Park Zoo - Roofs | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2023 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO19 | Central Park Zoo - Roofs | 2 | DESIGN | Dec 2017 | Mar 2019 | Dec 2023 | Mar 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO19 | Central Park Zoo - Roofs | 3 | BID/ REGISTER CONTRACT | Mar 2019 | Dec 2019 | Mar 2025 | Dec 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO19 | Central Park Zoo - Roofs | 4 | CONSTRUCTION | Dec 2019 | Dec 2020 | Dec 2025 | Dec 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO19 | Central Park Zoo - Roofs | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2020 | Dec 2021 | Dec 2026 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO20 | Central Park Zoo - Tractor and attachments | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2025 | Dec 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO20 | Central Park Zoo - Tractor and attachments | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2025 | Dec 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO20 | Central Park Zoo - Tractor and attachments | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2026 | Sep 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO20 | Central Park Zoo - Tractor and attachments | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2027 | Sep 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO20 | Central Park Zoo - Tractor and attachments | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2028 | Sep 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPBP | BATTERY PARK BIKEWAY PERIMETER M005-111M (SUPERCEDES 308M) | 1 | DEVELOP SCOPE | Jul 2004 | Sep 2004 | Jul 2007 | Dec 2008
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPBP | BATTERY PARK BIKEWAY PERIMETER M005-111M (SUPERCEDES 308M) | 2 | DESIGN | Sep 2004 | Dec 2004 | Dec 2008 | Sep 2011
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPBP | BATTERY PARK BIKEWAY PERIMETER M005-111M (SUPERCEDES 308M) | 3 | BID/ REGISTER CONTRACT | Dec 2004 | Mar 2005 | Jan 2012 | Jul 2012
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPBP | BATTERY PARK BIKEWAY PERIMETER M005-111M (SUPERCEDES 308M) | 4 | CONSTRUCTION | Mar 2005 | Mar 2006 | Sep 2012 | Oct 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPBP | BATTERY PARK BIKEWAY PERIMETER M005-111M (SUPERCEDES 308M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2006 | Mar 2007 | Oct 2015 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPOC | Battery Park Office convert to PRB M005 | 1 | DEVELOP SCOPE | Jul 2012 | Sep 2012 | Jul 2012 | Sep 2012
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPOC | Battery Park Office convert to PRB M005 | 2 | DESIGN | Sep 2012 | Dec 2012 | Sep 2012 | Dec 2012
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPOC | Battery Park Office convert to PRB M005 | 3 | BID/ REGISTER CONTRACT | Dec 2012 | Mar 2013 | Dec 2012 | Mar 2013
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPOC | Battery Park Office convert to PRB M005 | 4 | CONSTRUCTION | Mar 2013 | Mar 2014 | Mar 2013 | Mar 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPOC | Battery Park Office convert to PRB M005 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2014 | Mar 2015 | Mar 2014 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BURL | LMDC-BURLING SLIP - IMAGINATION PLGD MG-41100-107M | 1 | DEVELOP SCOPE | Jul 2006 | Oct 2006 | Jul 2006 | Mar 2008
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BURL | LMDC-BURLING SLIP - IMAGINATION PLGD MG-41100-107M | 2 | DESIGN | Oct 2006 | Dec 2006 | Mar 2008 | Apr 2008
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BURL | LMDC-BURLING SLIP - IMAGINATION PLGD MG-41100-107M | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Oct 2008 | Apr 2009
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BURL | LMDC-BURLING SLIP - IMAGINATION PLGD MG-41100-107M | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Apr 2009 | Jul 2010
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BURL | LMDC-BURLING SLIP - IMAGINATION PLGD MG-41100-107M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Jul 2010 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301EPPK | Elizabeth H. Berger Plaza, Manhattan | 1 | DEVELOP SCOPE | Jul 2011 | Sep 2011 | Jul 2011 | Oct 2012
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301EPPK | Elizabeth H. Berger Plaza, Manhattan | 2 | DESIGN | Sep 2011 | Dec 2011 | Oct 2012 | Apr 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301EPPK | Elizabeth H. Berger Plaza, Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2011 | Mar 2012 | Aug 2018 | Apr 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301EPPK | Elizabeth H. Berger Plaza, Manhattan | 4 | CONSTRUCTION | Mar 2012 | Mar 2013 | Aug 2019 | Jan 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301EPPK | Elizabeth H. Berger Plaza, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2013 | Mar 2014 | Jan 2021 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301PEAR | LMDC-PEARL ST PLGD MG-41000-107M | 1 | DEVELOP SCOPE | Jul 2006 | Sep 2006 | Mar 2003 | Sep 2003
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301PEAR | LMDC-PEARL ST PLGD MG-41000-107M | 2 | DESIGN | Sep 2006 | Dec 2006 | Sep 2003 | Jul 2009
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301PEAR | LMDC-PEARL ST PLGD MG-41000-107M | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Sep 2009 | Apr 2011
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301PEAR | LMDC-PEARL ST PLGD MG-41000-107M | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Jun 2011 | May 2012
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301PEAR | LMDC-PEARL ST PLGD MG-41000-107M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | May 2012 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301PECK | LMDC-PECK SLIP RECONSTRUCTION M167-106M | 1 | DEVELOP SCOPE | Jul 2006 | Sep 2006 | Sep 2004 | Dec 2004
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301PECK | LMDC-PECK SLIP RECONSTRUCTION M167-106M | 2 | DESIGN | Sep 2006 | Dec 2006 | Dec 2006 | Dec 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301PECK | LMDC-PECK SLIP RECONSTRUCTION M167-106M | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Mar 2019 | May 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301PECK | LMDC-PECK SLIP RECONSTRUCTION M167-106M | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Aug 2019 | Aug 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301PECK | LMDC-PECK SLIP RECONSTRUCTION M167-106M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Aug 2020 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301VIE2 | VIETNAM VETERANS PLAZA RC M046-114M | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301VIE2 | VIETNAM VETERANS PLAZA RC M046-114M | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301VIE2 | VIETNAM VETERANS PLAZA RC M046-114M | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301VIE2 | VIETNAM VETERANS PLAZA RC M046-114M | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301VIE2 | VIETNAM VETERANS PLAZA RC M046-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301WAPT | WASHINGTON MARKET PARK PATHWAY PAVEMENT REPLACEMENT | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301WAPT | WASHINGTON MARKET PARK PATHWAY PAVEMENT REPLACEMENT | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301WAPT | WASHINGTON MARKET PARK PATHWAY PAVEMENT REPLACEMENT | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301WAPT | WASHINGTON MARKET PARK PATHWAY PAVEMENT REPLACEMENT | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301WAPT | WASHINGTON MARKET PARK PATHWAY PAVEMENT REPLACEMENT | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302BLEE | Bleecker Street Playground,Manhattan | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302BLEE | Bleecker Street Playground,Manhattan | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302BLEE | Bleecker Street Playground,Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302BLEE | Bleecker Street Playground,Manhattan | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302BLEE | Bleecker Street Playground,Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302GLAF | DEP Shaft Site -- Grand & Lafayette Streets | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Oct 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302GLAF | DEP Shaft Site -- Grand & Lafayette Streets | 2 | DESIGN | Sep 2013 | Dec 2013 | Oct 2017 | Oct 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302GLAF | DEP Shaft Site -- Grand & Lafayette Streets | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Jun 2020 | Aug 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302GLAF | DEP Shaft Site -- Grand & Lafayette Streets | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Sep 2020 | Aug 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302GLAF | DEP Shaft Site -- Grand & Lafayette Streets | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Sep 2021 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302HGLR | HIGH LINE REPAIRS | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302HGLR | HIGH LINE REPAIRS | 2 | DESIGN | Dec 2022 | Jun 2024 | Dec 2022 | Jun 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302HGLR | HIGH LINE REPAIRS | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302HGLR | HIGH LINE REPAIRS | 4 | CONSTRUCTION | Mar 2025 | Sep 2026 | Mar 2025 | Sep 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302HGLR | HIGH LINE REPAIRS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Sep 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302HIGH | HIGH LINE RENOVATIONS M360 | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302HIGH | HIGH LINE RENOVATIONS M360 | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302HIGH | HIGH LINE RENOVATIONS M360 | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302HIGH | HIGH LINE RENOVATIONS M360 | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302HIGH | HIGH LINE RENOVATIONS M360 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302HUHO | DEP shaft site 28B - Hudson and West Houston | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302HUHO | DEP shaft site 28B - Hudson and West Houston | 2 | DESIGN | Dec 2017 | Mar 2019 | Dec 2017 | Mar 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302HUHO | DEP shaft site 28B - Hudson and West Houston | 3 | BID/ REGISTER CONTRACT | Mar 2019 | Dec 2019 | Mar 2019 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302HUHO | DEP shaft site 28B - Hudson and West Houston | 4 | CONSTRUCTION | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302HUHO | DEP shaft site 28B - Hudson and West Houston | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2020 | Dec 2021 | Dec 2020 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302TDRC | Tony Dapolito Recreation Center Emergency Reconstruction | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302TDRC | Tony Dapolito Recreation Center Emergency Reconstruction | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302TDRC | Tony Dapolito Recreation Center Emergency Reconstruction | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302TDRC | Tony Dapolito Recreation Center Emergency Reconstruction | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302TDRC | Tony Dapolito Recreation Center Emergency Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303018C | SEWARD PARK PHASE I- M082-199 | 1 | DEVELOP SCOPE | Sep 1998 | Apr 1999 | Sep 1998 | Apr 1999
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303018C | SEWARD PARK PHASE I- M082-199 | 2 | DESIGN | Sep 1998 | Oct 1999 | Sep 1998 | Oct 1999
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303018C | SEWARD PARK PHASE I- M082-199 | 3 | BID/ REGISTER CONTRACT | Dec 1999 | Apr 2000 | Dec 1999 | Apr 2000
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303018C | SEWARD PARK PHASE I- M082-199 | 4 | CONSTRUCTION | Apr 2000 | Apr 2001 | Apr 2000 | Apr 2001
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303018C | SEWARD PARK PHASE I- M082-199 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2001 | Apr 2002 | Apr 2001 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ABCP | ABC PLAYGROUND SIDEWALK REPLACEMENT | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ABCP | ABC PLAYGROUND SIDEWALK REPLACEMENT | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ABCP | ABC PLAYGROUND SIDEWALK REPLACEMENT | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ABCP | ABC PLAYGROUND SIDEWALK REPLACEMENT | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ABCP | ABC PLAYGROUND SIDEWALK REPLACEMENT | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ALEN | LMDC -PIKE - ALLEN STREET MALLS M004-108M | 1 | DEVELOP SCOPE | Jul 2005 | Sep 2005 | Sep 2001 | Jun 2004
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ALEN | LMDC -PIKE - ALLEN STREET MALLS M004-108M | 2 | DESIGN | Sep 2005 | Dec 2005 | Jun 2004 | Jan 2010
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ALEN | LMDC -PIKE - ALLEN STREET MALLS M004-108M | 3 | BID/ REGISTER CONTRACT | Dec 2005 | Mar 2006 | Jun 2010 | Sep 2010
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ALEN | LMDC -PIKE - ALLEN STREET MALLS M004-108M | 4 | CONSTRUCTION | Mar 2006 | Mar 2007 | Sep 2010 | Aug 2012
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ALEN | LMDC -PIKE - ALLEN STREET MALLS M004-108M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2007 | Mar 2008 | Aug 2012 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ASRC | Al Smith Rec Ctr fitness room recon CNYG-420M | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Sep 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ASRC | Al Smith Rec Ctr fitness room recon CNYG-420M | 2 | DESIGN | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ASRC | Al Smith Rec Ctr fitness room recon CNYG-420M | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2014 | Mar 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ASRC | Al Smith Rec Ctr fitness room recon CNYG-420M | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ASRC | Al Smith Rec Ctr fitness room recon CNYG-420M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303BPCS | Baruch Playground PRB Renovations M165A-116M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Dec 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303BPCS | Baruch Playground PRB Renovations M165A-116M | 2 | DESIGN | Sep 2013 | Dec 2013 | Dec 2015 | Jan 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303BPCS | Baruch Playground PRB Renovations M165A-116M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Oct 2017 | May 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303BPCS | Baruch Playground PRB Renovations M165A-116M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | May 2018 | Nov 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303BPCS | Baruch Playground PRB Renovations M165A-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | May 2019 | Jun 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303CRES | COMMUNITY GARDEN RESILIENCY UPGRADES | 1 | DEVELOP SCOPE | Oct 2023 | Apr 2024 | Oct 2023 | Apr 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303CRES | COMMUNITY GARDEN RESILIENCY UPGRADES | 2 | DESIGN | Apr 2024 | Apr 2025 | Apr 2024 | Apr 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303CRES | COMMUNITY GARDEN RESILIENCY UPGRADES | 3 | BID/ REGISTER CONTRACT | Apr 2025 | Jan 2026 | Apr 2025 | Jan 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303CRES | COMMUNITY GARDEN RESILIENCY UPGRADES | 4 | CONSTRUCTION | Jan 2026 | Jan 2027 | Jan 2026 | Jan 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303CRES | COMMUNITY GARDEN RESILIENCY UPGRADES | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2027 | Jun 2028 | Jan 2027 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303CRH2 | Corlears Hook Playground, Manhattan | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303CRH2 | Corlears Hook Playground, Manhattan | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303CRH2 | Corlears Hook Playground, Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303CRH2 | Corlears Hook Playground, Manhattan | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303CRH2 | Corlears Hook Playground, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ERP4 | East River Park Fireboat Wet Floodproofing | 1 | DEVELOP SCOPE | Jun 2023 | Dec 2023 | Jun 2023 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ERP4 | East River Park Fireboat Wet Floodproofing | 2 | DESIGN | Dec 2023 | Dec 2024 | Dec 2023 | Dec 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ERP4 | East River Park Fireboat Wet Floodproofing | 3 | BID/ REGISTER CONTRACT | Dec 2024 | Sep 2025 | Dec 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ERP4 | East River Park Fireboat Wet Floodproofing | 4 | CONSTRUCTION | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ERP4 | East River Park Fireboat Wet Floodproofing | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Sep 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ERSF | ERP - E 6TH ST SOCCER FLD NEW TURF M144-214m | 1 | DEVELOP SCOPE | Jul 2011 | Sep 2011 | Jul 2011 | Nov 2013
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ERSF | ERP - E 6TH ST SOCCER FLD NEW TURF M144-214m | 2 | DESIGN | Sep 2011 | Dec 2011 | Nov 2013 | Nov 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ERSF | ERP - E 6TH ST SOCCER FLD NEW TURF M144-214m | 3 | BID/ REGISTER CONTRACT | Dec 2011 | Mar 2012 | Feb 2017 | Jul 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ERSF | ERP - E 6TH ST SOCCER FLD NEW TURF M144-214m | 4 | CONSTRUCTION | Mar 2012 | Mar 2013 | Sep 2017 | Sep 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ERSF | ERP - E 6TH ST SOCCER FLD NEW TURF M144-214m | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2013 | Mar 2014 | Sep 2018 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303HFRC | Hamilton Fish Rec.Ctr-replace roof & alarm system | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Sep 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303HFRC | Hamilton Fish Rec.Ctr-replace roof & alarm system | 2 | DESIGN | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303HFRC | Hamilton Fish Rec.Ctr-replace roof & alarm system | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2014 | Mar 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303HFRC | Hamilton Fish Rec.Ctr-replace roof & alarm system | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303HFRC | Hamilton Fish Rec.Ctr-replace roof & alarm system | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2016 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303HMFS | Hamilton Fish Park-Full renovation , Manhattan | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303HMFS | Hamilton Fish Park-Full renovation , Manhattan | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303HMFS | Hamilton Fish Park-Full renovation , Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303HMFS | Hamilton Fish Park-Full renovation , Manhattan | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303HMFS | Hamilton Fish Park-Full renovation , Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303KILS | Kimlau Square Reconstruction | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303KILS | Kimlau Square Reconstruction | 2 | DESIGN | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303KILS | Kimlau Square Reconstruction | 3 | BID/ REGISTER CONTRACT | Sep 2024 | Jun 2025 | Sep 2024 | Jun 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303KILS | Kimlau Square Reconstruction | 4 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303KILS | Kimlau Square Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Jun 2027 | Jun 2026 | Jun 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303KIML | Kimlau Square Improvements , Manhattan | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303KIML | Kimlau Square Improvements , Manhattan | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303KIML | Kimlau Square Improvements , Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303KIML | Kimlau Square Improvements , Manhattan | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303KIML | Kimlau Square Improvements , Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303LFPG | Reconstruction of Little Flower Playground, Manhattan | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303LFPG | Reconstruction of Little Flower Playground, Manhattan | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303LFPG | Reconstruction of Little Flower Playground, Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303LFPG | Reconstruction of Little Flower Playground, Manhattan | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303LFPG | Reconstruction of Little Flower Playground, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303LGPK | CPI PH1 - LUTHER GULICK PARK - RECON WEST PORTION | 1 | DEVELOP SCOPE | Jul 2009 | Sep 2009 | Jul 2009 | Jun 2011
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303LGPK | CPI PH1 - LUTHER GULICK PARK - RECON WEST PORTION | 2 | DESIGN | Sep 2009 | Dec 2009 | Jun 2011 | Apr 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303LGPK | CPI PH1 - LUTHER GULICK PARK - RECON WEST PORTION | 3 | BID/ REGISTER CONTRACT | Dec 2009 | Mar 2010 | Feb 2018 | Jan 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303LGPK | CPI PH1 - LUTHER GULICK PARK - RECON WEST PORTION | 4 | CONSTRUCTION | Mar 2010 | Mar 2011 | Mar 2019 | Sep 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303LGPK | CPI PH1 - LUTHER GULICK PARK - RECON WEST PORTION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2011 | Mar 2012 | Sep 2020 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303MCKY | McKinley Playground renovation, M259-118M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Jun 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303MCKY | McKinley Playground renovation, M259-118M | 2 | DESIGN | Dec 2016 | Dec 2017 | Jun 2017 | Nov 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303MCKY | McKinley Playground renovation, M259-118M | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Feb 2019 | Jan 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303MCKY | McKinley Playground renovation, M259-118M | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303MCKY | McKinley Playground renovation, M259-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2021 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303SDRP | Sara D. Roosevelt Park - Pathways, sidewalks, exterior walls | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jan 2017 | Jul 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303SDRP | Sara D. Roosevelt Park - Pathways, sidewalks, exterior walls | 2 | DESIGN | Sep 2015 | Dec 2015 | Jul 2022 | Oct 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303SDRP | Sara D. Roosevelt Park - Pathways, sidewalks, exterior walls | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Oct 2023 | Jun 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303SDRP | Sara D. Roosevelt Park - Pathways, sidewalks, exterior walls | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Jul 2024 | Jun 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303SDRP | Sara D. Roosevelt Park - Pathways, sidewalks, exterior walls | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Jul 2025 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303TPSQ | Tompkin's Square Park - Manhattan M088-119M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303TPSQ | Tompkin's Square Park - Manhattan M088-119M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303TPSQ | Tompkin's Square Park - Manhattan M088-119M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303TPSQ | Tompkin's Square Park - Manhattan M088-119M | 4 | CONSTRUCTION | Sep 2020 | Mar 2022 | Sep 2020 | Mar 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303TPSQ | Tompkin's Square Park - Manhattan M088-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Mar 2023 | Mar 2022 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-30420S2 | West 20th St. Park Construction, M402-116M, Manhattan | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-30420S2 | West 20th St. Park Construction, M402-116M, Manhattan | 2 | DESIGN | Dec 2016 | Jun 2018 | Dec 2016 | Jul 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-30420S2 | West 20th St. Park Construction, M402-116M, Manhattan | 3 | BID/ REGISTER CONTRACT | Jun 2018 | Mar 2019 | Oct 2017 | Sep 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-30420S2 | West 20th St. Park Construction, M402-116M, Manhattan | 4 | CONSTRUCTION | Mar 2019 | Sep 2020 | Jul 2018 | Jul 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-30420S2 | West 20th St. Park Construction, M402-116M, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Jul 2019 | Jun 2033
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CBBC | Chelsea Basketball Court Renovation, Manhattan | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Feb 2017 | Aug 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CBBC | Chelsea Basketball Court Renovation, Manhattan | 2 | DESIGN | Dec 2018 | Dec 2019 | Aug 2017 | Aug 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CBBC | Chelsea Basketball Court Renovation, Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | May 2021 | Jan 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CBBC | Chelsea Basketball Court Renovation, Manhattan | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Jan 2022 | Jan 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CBBC | Chelsea Basketball Court Renovation, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Jan 2023 | Jun 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CPTF | Chelsea Park-Replace the synthetic turf field and track M011 | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CPTF | Chelsea Park-Replace the synthetic turf field and track M011 | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CPTF | Chelsea Park-Replace the synthetic turf field and track M011 | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CPTF | Chelsea Park-Replace the synthetic turf field and track M011 | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Oct 2024 | Jan 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CPTF | Chelsea Park-Replace the synthetic turf field and track M011 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304DWCP | DE WITT CLINTON PARK RECONSTRUCTION | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304DWCP | DE WITT CLINTON PARK RECONSTRUCTION | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304DWCP | DE WITT CLINTON PARK RECONSTRUCTION | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304DWCP | DE WITT CLINTON PARK RECONSTRUCTION | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304DWCP | DE WITT CLINTON PARK RECONSTRUCTION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Jun 2028 | Sep 2025 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304LRSQ | Little Red Square, Manhattan, MG-41350-115M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Jan 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304LRSQ | Little Red Square, Manhattan, MG-41350-115M | 2 | DESIGN | Sep 2013 | Dec 2013 | Jan 2014 | May 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304LRSQ | Little Red Square, Manhattan, MG-41350-115M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Sep 2017 | Aug 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304LRSQ | Little Red Square, Manhattan, MG-41350-115M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2019 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304LRSQ | Little Red Square, Manhattan, MG-41350-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Jan 2022 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304MPRC | MATTHEWS PALMER PLAYGROUND Public Restroom Renovation | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304MPRC | MATTHEWS PALMER PLAYGROUND Public Restroom Renovation | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304MPRC | MATTHEWS PALMER PLAYGROUND Public Restroom Renovation | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304MPRC | MATTHEWS PALMER PLAYGROUND Public Restroom Renovation | 4 | CONSTRUCTION | Nov 2025 | May 2027 | Nov 2025 | May 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304MPRC | MATTHEWS PALMER PLAYGROUND Public Restroom Renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | May 2027 | May 2028 | May 2027 | May 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304PENN | Penn South Playground, Manhattan | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304PENN | Penn South Playground, Manhattan | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304PENN | Penn South Playground, Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304PENN | Penn South Playground, Manhattan | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304PENN | Penn South Playground, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-305MSEL | Madison Square Park Pavement Reconstruction Manhattan | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Mar 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-305MSEL | Madison Square Park Pavement Reconstruction Manhattan | 2 | DESIGN | Dec 2017 | Dec 2018 | Mar 2019 | Apr 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-305MSEL | Madison Square Park Pavement Reconstruction Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | May 2021 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-305MSEL | Madison Square Park Pavement Reconstruction Manhattan | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Jan 2022 | Jan 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-305MSEL | Madison Square Park Pavement Reconstruction Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Jan 2023 | Jun 2031
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-30634LS | 34th Street Lot Top side Surface Treatment and Seating | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-30634LS | 34th Street Lot Top side Surface Treatment and Seating | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-30634LS | 34th Street Lot Top side Surface Treatment and Seating | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-30634LS | 34th Street Lot Top side Surface Treatment and Seating | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-30634LS | 34th Street Lot Top side Surface Treatment and Seating | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306APMU | Albano Playground Handball Court Multi-use Conve M265-117M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306APMU | Albano Playground Handball Court Multi-use Conve M265-117M | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2015 | Jul 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306APMU | Albano Playground Handball Court Multi-use Conve M265-117M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2017 | Aug 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306APMU | Albano Playground Handball Court Multi-use Conve M265-117M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Aug 2021 | Aug 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306APMU | Albano Playground Handball Court Multi-use Conve M265-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Aug 2022 | Jan 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ASEQ | Asser Levy Rec Ctr fitness room recon, Manhattan CNYG-420M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Apr 2024 | Oct 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ASEQ | Asser Levy Rec Ctr fitness room recon, Manhattan CNYG-420M | 2 | DESIGN | Dec 2019 | Dec 2020 | Oct 2024 | Oct 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ASEQ | Asser Levy Rec Ctr fitness room recon, Manhattan CNYG-420M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Oct 2025 | Jul 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ASEQ | Asser Levy Rec Ctr fitness room recon, Manhattan CNYG-420M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Jul 2026 | Jul 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ASEQ | Asser Levy Rec Ctr fitness room recon, Manhattan CNYG-420M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Jul 2027 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ASGP | Augustus Saint Gaudens Playground Renovation ( M226-123M) | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ASGP | Augustus Saint Gaudens Playground Renovation ( M226-123M) | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ASGP | Augustus Saint Gaudens Playground Renovation ( M226-123M) | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ASGP | Augustus Saint Gaudens Playground Renovation ( M226-123M) | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ASGP | Augustus Saint Gaudens Playground Renovation ( M226-123M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ASLV | Asser Levy Recreation Center | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ASLV | Asser Levy Recreation Center | 2 | DESIGN | Sep 2015 | Dec 2015 | Dec 2022 | Mar 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ASLV | Asser Levy Recreation Center | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Mar 2023 | Jun 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ASLV | Asser Levy Recreation Center | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Jun 2023 | Jun 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ASLV | Asser Levy Recreation Center | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Jun 2024 | Jun 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306DAGP | Dag Hammarskjold Plaza Phase II Reconstruction | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Mar 2022 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306DAGP | Dag Hammarskjold Plaza Phase II Reconstruction | 2 | DESIGN | Sep 2023 | Sep 2024 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306DAGP | Dag Hammarskjold Plaza Phase II Reconstruction | 3 | BID/ REGISTER CONTRACT | Sep 2024 | Jun 2025 | Sep 2023 | Jun 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306DAGP | Dag Hammarskjold Plaza Phase II Reconstruction | 4 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2024 | Jun 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306DAGP | Dag Hammarskjold Plaza Phase II Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Jun 2027 | Jun 2025 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306GLIC | Glick Park | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306GLIC | Glick Park | 2 | DESIGN | Dec 2017 | Dec 2019 | Dec 2017 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306GLIC | Glick Park | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306GLIC | Glick Park | 4 | CONSTRUCTION | Sep 2020 | Sep 2022 | Sep 2020 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306GLIC | Glick Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306PETD | Peter Detmold Park, Manhattan-M108N-121M | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306PETD | Peter Detmold Park, Manhattan-M108N-121M | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306PETD | Peter Detmold Park, Manhattan-M108N-121M | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306PETD | Peter Detmold Park, Manhattan-M108N-121M | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306PETD | Peter Detmold Park, Manhattan-M108N-121M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306SSHR | STUYVESANT SQUARE PARK EAST PARK HOUSE RENOVATION | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306SSHR | STUYVESANT SQUARE PARK EAST PARK HOUSE RENOVATION | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306SSHR | STUYVESANT SQUARE PARK EAST PARK HOUSE RENOVATION | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306SSHR | STUYVESANT SQUARE PARK EAST PARK HOUSE RENOVATION | 4 | CONSTRUCTION | Nov 2025 | May 2027 | Nov 2025 | May 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306SSHR | STUYVESANT SQUARE PARK EAST PARK HOUSE RENOVATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | May 2027 | May 2028 | May 2027 | May 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306STVA | St. Vartan Park - Manhattan | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Feb 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306STVA | St. Vartan Park - Manhattan | 2 | DESIGN | Dec 2018 | Dec 2019 | Feb 2020 | Mar 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306STVA | St. Vartan Park - Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Oct 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306STVA | St. Vartan Park - Manhattan | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Feb 2023 | Feb 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306STVA | St. Vartan Park - Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Feb 2024 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306TRPL | Tramway Plaza Irrigation | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Feb 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306TRPL | Tramway Plaza Irrigation | 2 | DESIGN | Sep 2013 | Dec 2013 | Feb 2014 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306TRPL | Tramway Plaza Irrigation | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Jul 2021 | Nov 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306TRPL | Tramway Plaza Irrigation | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Dec 2021 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306TRPL | Tramway Plaza Irrigation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Dec 2022 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306TUDO | Tudor Grove Playground - Manhattan | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Feb 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306TUDO | Tudor Grove Playground - Manhattan | 2 | DESIGN | Dec 2018 | Dec 2019 | Feb 2019 | Feb 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306TUDO | Tudor Grove Playground - Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Jun 2021 | Nov 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306TUDO | Tudor Grove Playground - Manhattan | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Jan 2022 | Jan 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306TUDO | Tudor Grove Playground - Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Jan 2023 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BENN | Bennerson Playground Renovation (M184-114M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2015 | Oct 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BLOC | CPI PH2 - Bloomingdale Public Restroom Buildings (CONS) | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2013 | Dec 2013
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BLOC | CPI PH2 - Bloomingdale Public Restroom Buildings (CONS) | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2013 | Dec 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BLOC | CPI PH2 - Bloomingdale Public Restroom Buildings (CONS) | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2014 | Sep 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BLOC | CPI PH2 - Bloomingdale Public Restroom Buildings (CONS) | 4 | CONSTRUCTION | Sep 2019 | Mar 2021 | Sep 2015 | Mar 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BLOC | CPI PH2 - Bloomingdale Public Restroom Buildings (CONS) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Mar 2022 | Mar 2017 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BLOP | CPI PH2 - Bloomingdale Playground (construction)- M238-217M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BLOP | CPI PH2 - Bloomingdale Playground (construction)- M238-217M | 2 | DESIGN | Dec 2017 | Jun 2019 | Dec 2017 | Jun 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BLOP | CPI PH2 - Bloomingdale Playground (construction)- M238-217M | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Mar 2020 | Jun 2019 | Mar 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BLOP | CPI PH2 - Bloomingdale Playground (construction)- M238-217M | 4 | CONSTRUCTION | Mar 2020 | Sep 2021 | Mar 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BLOP | CPI PH2 - Bloomingdale Playground (construction)- M238-217M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BMAP | BROADWAY MALLS - RECON & UPGRADE BROADWAY MALLS | 1 | DEVELOP SCOPE | Jul 2012 | Sep 2012 | Jul 2012 | Nov 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BMAP | BROADWAY MALLS - RECON & UPGRADE BROADWAY MALLS | 2 | DESIGN | Sep 2012 | Dec 2012 | Dec 2015 | Jun 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BMAP | BROADWAY MALLS - RECON & UPGRADE BROADWAY MALLS | 3 | BID/ REGISTER CONTRACT | Dec 2012 | Mar 2013 | Dec 2017 | Jun 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BMAP | BROADWAY MALLS - RECON & UPGRADE BROADWAY MALLS | 4 | CONSTRUCTION | Mar 2013 | Mar 2014 | Aug 2018 | Aug 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BMAP | BROADWAY MALLS - RECON & UPGRADE BROADWAY MALLS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2014 | Mar 2015 | Aug 2019 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307FDBB | Frederick Douglass Basketball Courts Reconstruction | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307FDBB | Frederick Douglass Basketball Courts Reconstruction | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307FDBB | Frederick Douglass Basketball Courts Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307FDBB | Frederick Douglass Basketball Courts Reconstruction | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307FDBB | Frederick Douglass Basketball Courts Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Jun 2028 | Sep 2025 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307MPSP | MATTHEW P. SAPOLIN PLAYGROUND RECONSTRUCTION | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307MPSP | MATTHEW P. SAPOLIN PLAYGROUND RECONSTRUCTION | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307MPSP | MATTHEW P. SAPOLIN PLAYGROUND RECONSTRUCTION | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307MPSP | MATTHEW P. SAPOLIN PLAYGROUND RECONSTRUCTION | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307MPSP | MATTHEW P. SAPOLIN PLAYGROUND RECONSTRUCTION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RIVP | RIVERSIDE PARK | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RIVP | RIVERSIDE PARK | 2 | DESIGN | Dec 2022 | Jun 2024 | Dec 2022 | Jun 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RIVP | RIVERSIDE PARK | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RIVP | RIVERSIDE PARK | 4 | CONSTRUCTION | Mar 2025 | Sep 2026 | Mar 2025 | Sep 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RIVP | RIVERSIDE PARK | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Jun 2031
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RIVR | Riverside Park River Run Playground Reconstruction | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RIVR | Riverside Park River Run Playground Reconstruction | 2 | DESIGN | Sep 2023 | Mar 2025 | Sep 2023 | Mar 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RIVR | Riverside Park River Run Playground Reconstruction | 3 | BID/ REGISTER CONTRACT | Mar 2025 | Dec 2025 | Mar 2025 | Dec 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RIVR | Riverside Park River Run Playground Reconstruction | 4 | CONSTRUCTION | Dec 2025 | Jun 2027 | Dec 2025 | Jun 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RIVR | Riverside Park River Run Playground Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2027 | Jun 2028 | Jun 2027 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPAF | RIVERSIDE PARK ADULT FITNESS AREA | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPAF | RIVERSIDE PARK ADULT FITNESS AREA | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPAF | RIVERSIDE PARK ADULT FITNESS AREA | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPAF | RIVERSIDE PARK ADULT FITNESS AREA | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPAF | RIVERSIDE PARK ADULT FITNESS AREA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPKS | RIVERSIDE PARK SOUTH - PHASE 5 M353-112M | 1 | DEVELOP SCOPE | Sep 2012 | Dec 2012 | Sep 2012 | May 2013
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPKS | RIVERSIDE PARK SOUTH - PHASE 5 M353-112M | 2 | DESIGN | Dec 2012 | Mar 2013 | May 2013 | Dec 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPKS | RIVERSIDE PARK SOUTH - PHASE 5 M353-112M | 3 | BID/ REGISTER CONTRACT | Mar 2013 | Jun 2013 | Jun 2015 | Jun 2016
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPKS | RIVERSIDE PARK SOUTH - PHASE 5 M353-112M | 4 | CONSTRUCTION | Jun 2013 | Jun 2014 | Aug 2016 | Sep 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPKS | RIVERSIDE PARK SOUTH - PHASE 5 M353-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2014 | Jun 2015 | Oct 2020 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPPI | RVSD PK SOUTH-SHADE STRUCTURES, SOCCER FIELD, REC AREA M071 | 1 | DEVELOP SCOPE | Jul 2012 | Sep 2012 | Jul 2012 | Mar 2013
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPPI | RVSD PK SOUTH-SHADE STRUCTURES, SOCCER FIELD, REC AREA M071 | 2 | DESIGN | Sep 2012 | Dec 2012 | Mar 2013 | Nov 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPPI | RVSD PK SOUTH-SHADE STRUCTURES, SOCCER FIELD, REC AREA M071 | 3 | BID/ REGISTER CONTRACT | Dec 2012 | Mar 2013 | Nov 2018 | Feb 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPPI | RVSD PK SOUTH-SHADE STRUCTURES, SOCCER FIELD, REC AREA M071 | 4 | CONSTRUCTION | Mar 2013 | Mar 2014 | Sep 2019 | Aug 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPPI | RVSD PK SOUTH-SHADE STRUCTURES, SOCCER FIELD, REC AREA M071 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2014 | Mar 2015 | Sep 2020 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPRP | RIVERSIDE PARK 78 ST. RAMP RC M071 | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPRP | RIVERSIDE PARK 78 ST. RAMP RC M071 | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPRP | RIVERSIDE PARK 78 ST. RAMP RC M071 | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPRP | RIVERSIDE PARK 78 ST. RAMP RC M071 | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPRP | RIVERSIDE PARK 78 ST. RAMP RC M071 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPSB | Riverside Park South Ph. 5 Building | 1 | DEVELOP SCOPE | Jul 2012 | Sep 2012 | Jul 2012 | Sep 2012
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPSB | Riverside Park South Ph. 5 Building | 2 | DESIGN | Sep 2012 | Dec 2012 | Sep 2012 | Feb 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPSB | Riverside Park South Ph. 5 Building | 3 | BID/ REGISTER CONTRACT | Dec 2012 | Mar 2013 | Jan 2019 | May 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPSB | Riverside Park South Ph. 5 Building | 4 | CONSTRUCTION | Mar 2013 | Mar 2014 | Jun 2019 | Jun 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPSB | Riverside Park South Ph. 5 Building | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2014 | Mar 2015 | Jun 2019 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RS91 | Riverside Park Stairwell Reconstruction | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Sep 2019 | Mar 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RS91 | Riverside Park Stairwell Reconstruction | 2 | DESIGN | Dec 2022 | Dec 2023 | Mar 2020 | Mar 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RS91 | Riverside Park Stairwell Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Mar 2021 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RS91 | Riverside Park Stairwell Reconstruction | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Dec 2021 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RS91 | Riverside Park Stairwell Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Dec 2022 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RVSD | RIVERSIDE PK- CANTILEVER 83RD-91ST M071-297A | 1 | DEVELOP SCOPE | Jul 1999 | Sep 1999 | Jul 1999 | Jan 2005
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RVSD | RIVERSIDE PK- CANTILEVER 83RD-91ST M071-297A | 2 | DESIGN | Sep 1999 | Dec 1999 | Jan 2005 | Apr 2007
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RVSD | RIVERSIDE PK- CANTILEVER 83RD-91ST M071-297A | 3 | BID/ REGISTER CONTRACT | Dec 1999 | Mar 2000 | Apr 2007 | Jul 2007
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RVSD | RIVERSIDE PK- CANTILEVER 83RD-91ST M071-297A | 4 | CONSTRUCTION | Mar 2000 | Mar 2001 | Oct 2007 | May 2010
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RVSD | RIVERSIDE PK- CANTILEVER 83RD-91ST M071-297A | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2001 | Mar 2002 | May 2010 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SAPO | MATTHEW P. SAPOLIN PARK PLAYGROUND: PLAYGROUND EQUIPMENT | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Jan 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SAPO | MATTHEW P. SAPOLIN PARK PLAYGROUND: PLAYGROUND EQUIPMENT | 2 | DESIGN | Dec 2017 | Dec 2018 | Jan 2020 | Jan 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SAPO | MATTHEW P. SAPOLIN PARK PLAYGROUND: PLAYGROUND EQUIPMENT | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2021 | Feb 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SAPO | MATTHEW P. SAPOLIN PARK PLAYGROUND: PLAYGROUND EQUIPMENT | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Mar 2022 | Mar 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SAPO | MATTHEW P. SAPOLIN PARK PLAYGROUND: PLAYGROUND EQUIPMENT | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Mar 2023 | Jun 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SASM | RIVERSIDE PARK SOLDIERS & SAILORS MONUMENT | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SASM | RIVERSIDE PARK SOLDIERS & SAILORS MONUMENT | 2 | DESIGN | Dec 2022 | Dec 2024 | Dec 2022 | Dec 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SASM | RIVERSIDE PARK SOLDIERS & SAILORS MONUMENT | 3 | BID/ REGISTER CONTRACT | Dec 2024 | Sep 2025 | Dec 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SASM | RIVERSIDE PARK SOLDIERS & SAILORS MONUMENT | 4 | CONSTRUCTION | Sep 2025 | Sep 2028 | Sep 2025 | Sep 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SASM | RIVERSIDE PARK SOLDIERS & SAILORS MONUMENT | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2028 | Sep 2030 | Sep 2028 | Sep 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SBPG | Sol Bloom Playground Renovation | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SBPG | Sol Bloom Playground Renovation | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SBPG | Sol Bloom Playground Renovation | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SBPG | Sol Bloom Playground Renovation | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SBPG | Sol Bloom Playground Renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SOLB | Sol Bloom Playground Improvements, Manhattan | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SOLB | Sol Bloom Playground Improvements, Manhattan | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SOLB | Sol Bloom Playground Improvements, Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SOLB | Sol Bloom Playground Improvements, Manhattan | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SOLB | Sol Bloom Playground Improvements, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307TDRV | Theodore Roosevelt Park- Dog run noise Reduction | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307TDRV | Theodore Roosevelt Park- Dog run noise Reduction | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2020 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307TDRV | Theodore Roosevelt Park- Dog run noise Reduction | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307TDRV | Theodore Roosevelt Park- Dog run noise Reduction | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307TDRV | Theodore Roosevelt Park- Dog run noise Reduction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2023 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307TRDR | Theodore Roosevelt Park Dog Run Renovation | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Jul 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307TRDR | Theodore Roosevelt Park Dog Run Renovation | 2 | DESIGN | Sep 2013 | Dec 2013 | Jul 2017 | Jul 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307TRDR | Theodore Roosevelt Park Dog Run Renovation | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2018 | Jun 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307TRDR | Theodore Roosevelt Park Dog Run Renovation | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Jul 2019 | Jul 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307TRDR | Theodore Roosevelt Park Dog Run Renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Jul 2020 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AG02 | Asphalt Green- Pool Filter Upgrades | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AG02 | Asphalt Green- Pool Filter Upgrades | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AG02 | Asphalt Green- Pool Filter Upgrades | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AG02 | Asphalt Green- Pool Filter Upgrades | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2021 | Mar 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AG02 | Asphalt Green- Pool Filter Upgrades | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2022 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AG03 | ASPHALT GREEN LOBBY EXPANSION & LOCKER UPGRADES | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AG03 | ASPHALT GREEN LOBBY EXPANSION & LOCKER UPGRADES | 2 | DESIGN | Dec 2016 | Dec 2018 | Dec 2016 | Dec 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AG03 | ASPHALT GREEN LOBBY EXPANSION & LOCKER UPGRADES | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AG03 | ASPHALT GREEN LOBBY EXPANSION & LOCKER UPGRADES | 4 | CONSTRUCTION | Sep 2019 | Sep 2022 | Sep 2019 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AG03 | ASPHALT GREEN LOBBY EXPANSION & LOCKER UPGRADES | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2024 | Sep 2022 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGEE | Asphalt Green- Energy Efficiency, Manhattan | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2024 | Dec 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGEE | Asphalt Green- Energy Efficiency, Manhattan | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2024 | Dec 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGEE | Asphalt Green- Energy Efficiency, Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2025 | Sep 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGEE | Asphalt Green- Energy Efficiency, Manhattan | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2026 | Sep 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGEE | Asphalt Green- Energy Efficiency, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2027 | Sep 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGFB | ASPHALT GREEN BOILER M286-114M | 1 | DEVELOP SCOPE | Jul 2012 | Sep 2012 | Jul 2012 | Sep 2012
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGFB | ASPHALT GREEN BOILER M286-114M | 2 | DESIGN | Sep 2012 | Dec 2012 | Oct 2013 | Jan 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGFB | ASPHALT GREEN BOILER M286-114M | 3 | BID/ REGISTER CONTRACT | Dec 2012 | Mar 2013 | May 2014 | Aug 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGFB | ASPHALT GREEN BOILER M286-114M | 4 | CONSTRUCTION | Mar 2013 | Mar 2014 | Aug 2013 | Aug 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGFB | ASPHALT GREEN BOILER M286-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2014 | Mar 2015 | Aug 2015 | Jun 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGMC | ASPHALT GREEN- MURPHY CENTER ELEVATION RESTORATION | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2013 | Mar 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGMC | ASPHALT GREEN- MURPHY CENTER ELEVATION RESTORATION | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGMC | ASPHALT GREEN- MURPHY CENTER ELEVATION RESTORATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Dec 2019 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGPF | Asphalt Green Pool Filtration | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2025 | Dec 2033
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGPF | Asphalt Green Pool Filtration | 2 | DESIGN | Sep 2014 | Dec 2014 | Jan 2023 | Mar 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGPF | Asphalt Green Pool Filtration | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Apr 2023 | Jun 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGPF | Asphalt Green Pool Filtration | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Jun 2023 | Jun 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGPF | Asphalt Green Pool Filtration | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Jun 2024 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGPO | Asphalt Green Pool Filtration | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGPO | Asphalt Green Pool Filtration | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGPO | Asphalt Green Pool Filtration | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGPO | Asphalt Green Pool Filtration | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGPO | Asphalt Green Pool Filtration | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308CSPC | Carl Schurz Park Courts-Hockey,Basketball,Pickleball Ct Reco | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308CSPC | Carl Schurz Park Courts-Hockey,Basketball,Pickleball Ct Reco | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308CSPC | Carl Schurz Park Courts-Hockey,Basketball,Pickleball Ct Reco | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308CSPC | Carl Schurz Park Courts-Hockey,Basketball,Pickleball Ct Reco | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308CSPC | Carl Schurz Park Courts-Hockey,Basketball,Pickleball Ct Reco | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308CSPG | Carl Schurz Playground Reconstruction | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Jul 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308CSPG | Carl Schurz Playground Reconstruction | 2 | DESIGN | Dec 2016 | Dec 2017 | Jul 2017 | Aug 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308CSPG | Carl Schurz Playground Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Jan 2019 | May 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308CSPG | Carl Schurz Playground Reconstruction | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2019 | Oct 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308CSPG | Carl Schurz Playground Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Oct 2020 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308CSPP | Carl Schurz Park -- Pathway Repavings | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308CSPP | Carl Schurz Park -- Pathway Repavings | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308CSPP | Carl Schurz Park -- Pathway Repavings | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308CSPP | Carl Schurz Park -- Pathway Repavings | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308CSPP | Carl Schurz Park -- Pathway Repavings | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308EPOA | POA East River Esplanade Improvements, Manhattan | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308EPOA | POA East River Esplanade Improvements, Manhattan | 2 | DESIGN | Dec 2018 | Dec 2020 | Dec 2018 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308EPOA | POA East River Esplanade Improvements, Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308EPOA | POA East River Esplanade Improvements, Manhattan | 4 | CONSTRUCTION | Sep 2021 | Sep 2023 | Sep 2021 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308EPOA | POA East River Esplanade Improvements, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308EREI | ERP- East River Esplanade Improvements | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | May 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308EREI | ERP- East River Esplanade Improvements | 2 | DESIGN | Dec 2016 | Dec 2017 | May 2017 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308EREI | ERP- East River Esplanade Improvements | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Nov 2019 | Apr 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308EREI | ERP- East River Esplanade Improvements | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Jul 2020 | Jul 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308EREI | ERP- East River Esplanade Improvements | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Jul 2021 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308ERP2 | East River Esplanade Stabilization And Reconstruction PHASE | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308ERP2 | East River Esplanade Stabilization And Reconstruction PHASE | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308ERP2 | East River Esplanade Stabilization And Reconstruction PHASE | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308ERP2 | East River Esplanade Stabilization And Reconstruction PHASE | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308ERP2 | East River Esplanade Stabilization And Reconstruction PHASE | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308ERP3 | EAST RIVER ESPLANADE PHASE 3+ | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308ERP3 | EAST RIVER ESPLANADE PHASE 3+ | 2 | DESIGN | Dec 2018 | Dec 2020 | Dec 2018 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308ERP3 | EAST RIVER ESPLANADE PHASE 3+ | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308ERP3 | EAST RIVER ESPLANADE PHASE 3+ | 4 | CONSTRUCTION | Sep 2021 | Sep 2023 | Sep 2021 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308ERP3 | EAST RIVER ESPLANADE PHASE 3+ | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308FFCA | FDR FOUR FREEDOMS PARK CONSERVANCY -- ENHANCED ACCESS, FDR F | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308FFCA | FDR FOUR FREEDOMS PARK CONSERVANCY -- ENHANCED ACCESS, FDR F | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308FFCA | FDR FOUR FREEDOMS PARK CONSERVANCY -- ENHANCED ACCESS, FDR F | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308FFCA | FDR FOUR FREEDOMS PARK CONSERVANCY -- ENHANCED ACCESS, FDR F | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308FFCA | FDR FOUR FREEDOMS PARK CONSERVANCY -- ENHANCED ACCESS, FDR F | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308GMBR | Gracie Mansion Rooftop Balustrade RC M081-122M | 1 | DEVELOP SCOPE | Jun 2022 | Nov 2022 | Jun 2022 | Nov 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308GMBR | Gracie Mansion Rooftop Balustrade RC M081-122M | 2 | DESIGN | Nov 2022 | Nov 2023 | Nov 2022 | Nov 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308GMBR | Gracie Mansion Rooftop Balustrade RC M081-122M | 3 | BID/ REGISTER CONTRACT | Nov 2023 | Aug 2024 | Nov 2023 | Aug 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308GMBR | Gracie Mansion Rooftop Balustrade RC M081-122M | 4 | CONSTRUCTION | Aug 2024 | Aug 2025 | Aug 2024 | Aug 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308GMBR | Gracie Mansion Rooftop Balustrade RC M081-122M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2025 | Aug 2026 | Aug 2025 | Aug 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308GMGL | GRACIE MANSION GUTTERS AND LEADERS RC M081 | 1 | DEVELOP SCOPE | Jan 2022 | Jun 2022 | Jan 2022 | Jun 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308GMGL | GRACIE MANSION GUTTERS AND LEADERS RC M081 | 2 | DESIGN | Jun 2022 | Jun 2023 | Jun 2022 | Jun 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308GMGL | GRACIE MANSION GUTTERS AND LEADERS RC M081 | 3 | BID/ REGISTER CONTRACT | Jun 2023 | Mar 2024 | Jun 2023 | Mar 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308GMGL | GRACIE MANSION GUTTERS AND LEADERS RC M081 | 4 | CONSTRUCTION | Mar 2024 | Mar 2025 | Mar 2024 | Mar 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308GMGL | GRACIE MANSION GUTTERS AND LEADERS RC M081 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Mar 2026 | Mar 2025 | Mar 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308GMRD | GRACIE MANSION RAMP AND DRAINAGE RC M081 | 1 | DEVELOP SCOPE | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308GMRD | GRACIE MANSION RAMP AND DRAINAGE RC M081 | 2 | DESIGN | Jul 2022 | Jul 2023 | Jul 2022 | Jul 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308GMRD | GRACIE MANSION RAMP AND DRAINAGE RC M081 | 3 | BID/ REGISTER CONTRACT | Jul 2023 | Apr 2024 | Jul 2023 | Apr 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308GMRD | GRACIE MANSION RAMP AND DRAINAGE RC M081 | 4 | CONSTRUCTION | Apr 2024 | Apr 2025 | Apr 2024 | Apr 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308GMRD | GRACIE MANSION RAMP AND DRAINAGE RC M081 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2025 | Apr 2026 | Apr 2025 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308HNYL | 14 HONEY LOCUSTS PARK, Manhattan, M177-119M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2016 | Dec 2016
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308HNYL | 14 HONEY LOCUSTS PARK, Manhattan, M177-119M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2016 | Dec 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308HNYL | 14 HONEY LOCUSTS PARK, Manhattan, M177-119M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2017 | Sep 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308HNYL | 14 HONEY LOCUSTS PARK, Manhattan, M177-119M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2018 | Sep 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308HNYL | 14 HONEY LOCUSTS PARK, Manhattan, M177-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2019 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308JJAD | JOHN JAY PARK ADA ACCESSIBLE | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308JJAD | JOHN JAY PARK ADA ACCESSIBLE | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308JJAD | JOHN JAY PARK ADA ACCESSIBLE | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308JJAD | JOHN JAY PARK ADA ACCESSIBLE | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308JJAD | JOHN JAY PARK ADA ACCESSIBLE | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Jun 2028 | Sep 2025 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308JJPK | John Jay Park Reconstruction, M045-118M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Mar 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308JJPK | John Jay Park Reconstruction, M045-118M | 2 | DESIGN | Sep 2015 | Dec 2015 | Mar 2018 | Mar 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308JJPK | John Jay Park Reconstruction, M045-118M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Apr 2019 | Nov 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308JJPK | John Jay Park Reconstruction, M045-118M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Dec 2019 | Nov 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308JJPK | John Jay Park Reconstruction, M045-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Dec 2020 | Nov 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308MHM2 | MERCHANT HOUSE MUSEUM- EAST FACADE & SHUTTER RESTO M318 | 1 | DEVELOP SCOPE | Jul 2011 | Sep 2011 | Jul 2011 | Sep 2011
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308MHM2 | MERCHANT HOUSE MUSEUM- EAST FACADE & SHUTTER RESTO M318 | 2 | DESIGN | Sep 2011 | Dec 2011 | Sep 2011 | Dec 2011
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308MHM2 | MERCHANT HOUSE MUSEUM- EAST FACADE & SHUTTER RESTO M318 | 3 | BID/ REGISTER CONTRACT | Dec 2011 | Mar 2012 | Dec 2011 | Mar 2012
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308MHM2 | MERCHANT HOUSE MUSEUM- EAST FACADE & SHUTTER RESTO M318 | 4 | CONSTRUCTION | Mar 2012 | Mar 2013 | Mar 2012 | Mar 2013
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308MHM2 | MERCHANT HOUSE MUSEUM- EAST FACADE & SHUTTER RESTO M318 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2013 | Mar 2014 | Mar 2013 | Jun 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308SPCS | 24 Sycamores Park C/S Renovation M108-116M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Apr 2012 | Jul 2012
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308SPCS | 24 Sycamores Park C/S Renovation M108-116M | 2 | DESIGN | Sep 2013 | Dec 2013 | Jul 2012 | Oct 2012
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308SPCS | 24 Sycamores Park C/S Renovation M108-116M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Oct 2012 | Jan 2013
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308SPCS | 24 Sycamores Park C/S Renovation M108-116M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Jan 2013 | Jan 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308SPCS | 24 Sycamores Park C/S Renovation M108-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Jan 2014 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308STCP | St. Catherine's Park -- sportscoating in the children's p | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308STCP | St. Catherine's Park -- sportscoating in the children's p | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308STCP | St. Catherine's Park -- sportscoating in the children's p | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308STCP | St. Catherine's Park -- sportscoating in the children's p | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308STCP | St. Catherine's Park -- sportscoating in the children's p | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309AHAM | Alexander Hamilton Plg Basketball Renovation M041-121M | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309AHAM | Alexander Hamilton Plg Basketball Renovation M041-121M | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309AHAM | Alexander Hamilton Plg Basketball Renovation M041-121M | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309AHAM | Alexander Hamilton Plg Basketball Renovation M041-121M | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309AHAM | Alexander Hamilton Plg Basketball Renovation M041-121M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309ANUN | Annunciation Playground | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Sep 2021 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309ANUN | Annunciation Playground | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309ANUN | Annunciation Playground | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309ANUN | Annunciation Playground | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309ANUN | Annunciation Playground | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Jun 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JRFA | Jackie Robinson Rec. Center: Fire Alarm Reconstruction | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JRFA | Jackie Robinson Rec. Center: Fire Alarm Reconstruction | 2 | DESIGN | Dec 2019 | Dec 2021 | Dec 2019 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JRFA | Jackie Robinson Rec. Center: Fire Alarm Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JRFA | Jackie Robinson Rec. Center: Fire Alarm Reconstruction | 4 | CONSTRUCTION | Sep 2022 | Sep 2025 | Sep 2022 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JRFA | Jackie Robinson Rec. Center: Fire Alarm Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JRRC | Jackie Robinson Recreation Ctr HVAC System RC M014-119M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JRRC | Jackie Robinson Recreation Ctr HVAC System RC M014-119M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JRRC | Jackie Robinson Recreation Ctr HVAC System RC M014-119M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JRRC | Jackie Robinson Recreation Ctr HVAC System RC M014-119M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JRRC | Jackie Robinson Recreation Ctr HVAC System RC M014-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JSPL | Jacob Schiff Playground Reconstruction | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Jun 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JSPL | Jacob Schiff Playground Reconstruction | 2 | DESIGN | Sep 2015 | Dec 2015 | Jun 2017 | May 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JSPL | Jacob Schiff Playground Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Sep 2018 | Jun 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JSPL | Jacob Schiff Playground Reconstruction | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Aug 2019 | Aug 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JSPL | Jacob Schiff Playground Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Aug 2020 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JSST | Jacob Schiff Park- Recons of Seating area, Manhattan | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JSST | Jacob Schiff Park- Recons of Seating area, Manhattan | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JSST | Jacob Schiff Park- Recons of Seating area, Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JSST | Jacob Schiff Park- Recons of Seating area, Manhattan | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JSST | Jacob Schiff Park- Recons of Seating area, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309MPMP | Morningside Park: Renovation of Middle Playground | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Jul 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309MPMP | Morningside Park: Renovation of Middle Playground | 2 | DESIGN | Dec 2016 | Dec 2017 | Jul 2017 | Oct 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309MPMP | Morningside Park: Renovation of Middle Playground | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Mar 2019 | Oct 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309MPMP | Morningside Park: Renovation of Middle Playground | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Dec 2019 | Mar 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309MPMP | Morningside Park: Renovation of Middle Playground | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Mar 2021 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309MPP1 | MORNINGSIDE PARK - PHASE ONE M056 | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309MPP1 | MORNINGSIDE PARK - PHASE ONE M056 | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309MPP1 | MORNINGSIDE PARK - PHASE ONE M056 | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309MPP1 | MORNINGSIDE PARK - PHASE ONE M056 | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309MPP1 | MORNINGSIDE PARK - PHASE ONE M056 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309MSSC | Morningside Park - Staircase | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309MSSC | Morningside Park - Staircase | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309MSSC | Morningside Park - Staircase | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309MSSC | Morningside Park - Staircase | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309MSSC | Morningside Park - Staircase | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Jun 2029 | Sep 2025 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309RBUS | RVSD DR -TIEMANN PL TO 97TH ST | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Dec 2005 | Jul 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309RBUS | RVSD DR -TIEMANN PL TO 97TH ST | 2 | DESIGN | Sep 2013 | Dec 2013 | Jul 2015 | Feb 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309RBUS | RVSD DR -TIEMANN PL TO 97TH ST | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Mar 2018 | Jan 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309RBUS | RVSD DR -TIEMANN PL TO 97TH ST | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2019 | May 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309RBUS | RVSD DR -TIEMANN PL TO 97TH ST | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Jun 2020 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309RPK1 | Riverside Park Improvements, Manhattan | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309RPK1 | Riverside Park Improvements, Manhattan | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309RPK1 | Riverside Park Improvements, Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309RPK1 | Riverside Park Improvements, Manhattan | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309RPK1 | Riverside Park Improvements, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309RSLG | Lighthouse Park Roosevelt Island, Manhattan | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309RSLG | Lighthouse Park Roosevelt Island, Manhattan | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309RSLG | Lighthouse Park Roosevelt Island, Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309RSLG | Lighthouse Park Roosevelt Island, Manhattan | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309RSLG | Lighthouse Park Roosevelt Island, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309SKRP | Sakura Park - Reconstruction of the Staircase | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | May 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309SKRP | Sakura Park - Reconstruction of the Staircase | 2 | DESIGN | Dec 2016 | Dec 2017 | May 2017 | Aug 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309SKRP | Sakura Park - Reconstruction of the Staircase | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Apr 2019 | Oct 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309SKRP | Sakura Park - Reconstruction of the Staircase | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Oct 2019 | Oct 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309SKRP | Sakura Park - Reconstruction of the Staircase | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Oct 2020 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309SSTF | Jacob Schiff Playground Synthetic Turf Field Recon,Manhattan | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | May 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309SSTF | Jacob Schiff Playground Synthetic Turf Field Recon,Manhattan | 2 | DESIGN | Dec 2018 | Dec 2019 | May 2019 | Apr 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309SSTF | Jacob Schiff Playground Synthetic Turf Field Recon,Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Jun 2021 | Jan 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309SSTF | Jacob Schiff Playground Synthetic Turf Field Recon,Manhattan | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Mar 2022 | Mar 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309SSTF | Jacob Schiff Playground Synthetic Turf Field Recon,Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Mar 2023 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309STN4 | St. Nicholas Park 136th Street Staircase Reconstruction | 1 | DEVELOP SCOPE | Jan 2023 | Jun 2023 | Jan 2023 | Jun 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309STN4 | St. Nicholas Park 136th Street Staircase Reconstruction | 2 | DESIGN | Jun 2023 | Jun 2024 | Jun 2023 | Jun 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309STN4 | St. Nicholas Park 136th Street Staircase Reconstruction | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309STN4 | St. Nicholas Park 136th Street Staircase Reconstruction | 4 | CONSTRUCTION | Mar 2025 | Mar 2026 | Mar 2025 | Mar 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309STN4 | St. Nicholas Park 136th Street Staircase Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Jun 2028 | Mar 2026 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309TMPR | TEN MILE RIVER PLAYGROUND RENOVATION | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309TMPR | TEN MILE RIVER PLAYGROUND RENOVATION | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309TMPR | TEN MILE RIVER PLAYGROUND RENOVATION | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309TMPR | TEN MILE RIVER PLAYGROUND RENOVATION | 4 | CONSTRUCTION | Nov 2025 | May 2027 | Nov 2025 | May 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309TMPR | TEN MILE RIVER PLAYGROUND RENOVATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | May 2027 | May 2028 | May 2027 | May 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-30AG05 | Asphalt Green- Building Management System | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-30AG05 | Asphalt Green- Building Management System | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-30AG05 | Asphalt Green- Building Management System | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-30AG05 | Asphalt Green- Building Management System | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-30AG05 | Asphalt Green- Building Management System | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310ARFA | The Arsenal: Fire Alarm Reconstruction | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310ARFA | The Arsenal: Fire Alarm Reconstruction | 2 | DESIGN | Dec 2019 | Dec 2021 | Dec 2019 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310ARFA | The Arsenal: Fire Alarm Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310ARFA | The Arsenal: Fire Alarm Reconstruction | 4 | CONSTRUCTION | Sep 2022 | Sep 2025 | Sep 2022 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310ARFA | The Arsenal: Fire Alarm Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310CCPG | Courtney Callendar Playground-handball court | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Feb 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310CCPG | Courtney Callendar Playground-handball court | 2 | DESIGN | Sep 2014 | Dec 2014 | Feb 2022 | Jul 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310CCPG | Courtney Callendar Playground-handball court | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Jun 2023 | Nov 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310CCPG | Courtney Callendar Playground-handball court | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Dec 2023 | Dec 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310CCPG | Courtney Callendar Playground-handball court | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Dec 2024 | Dec 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310EDGE | EDGECOMBE AVE - RECON SDWKS, CURBS FENCE & LNDSCP M014-108M | 1 | DEVELOP SCOPE | Jul 2006 | Sep 2006 | Jun 1983 | Sep 1984
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310EDGE | EDGECOMBE AVE - RECON SDWKS, CURBS FENCE & LNDSCP M014-108M | 2 | DESIGN | Sep 2006 | Dec 2006 | Sep 1984 | Dec 1984
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310EDGE | EDGECOMBE AVE - RECON SDWKS, CURBS FENCE & LNDSCP M014-108M | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Apr 2008 | Sep 2008
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310EDGE | EDGECOMBE AVE - RECON SDWKS, CURBS FENCE & LNDSCP M014-108M | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Oct 2008 | May 2009
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310EDGE | EDGECOMBE AVE - RECON SDWKS, CURBS FENCE & LNDSCP M014-108M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | May 2009 | Jun 2033
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310HIBR | Highbridge Recreation Center -Pool Wall Stabilization | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310HIBR | Highbridge Recreation Center -Pool Wall Stabilization | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310HIBR | Highbridge Recreation Center -Pool Wall Stabilization | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310HIBR | Highbridge Recreation Center -Pool Wall Stabilization | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310HIBR | Highbridge Recreation Center -Pool Wall Stabilization | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Jun 2028 | Sep 2025 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310JRPG | JACKIE ROBINSON PARK GREEN 2 GREENER INITIATIVE | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310JRPG | JACKIE ROBINSON PARK GREEN 2 GREENER INITIATIVE | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310JRPG | JACKIE ROBINSON PARK GREEN 2 GREENER INITIATIVE | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310JRPG | JACKIE ROBINSON PARK GREEN 2 GREENER INITIATIVE | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310JRPG | JACKIE ROBINSON PARK GREEN 2 GREENER INITIATIVE | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310MCCY | McCray Playground , Manhattan | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310MCCY | McCray Playground , Manhattan | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310MCCY | McCray Playground , Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310MCCY | McCray Playground , Manhattan | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310MCCY | McCray Playground , Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HCTR | HIGHBRIDGE RECREATION CTR -RC BOILERS AND HVAC - M037-217M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HCTR | HIGHBRIDGE RECREATION CTR -RC BOILERS AND HVAC - M037-217M | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HCTR | HIGHBRIDGE RECREATION CTR -RC BOILERS AND HVAC - M037-217M | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HCTR | HIGHBRIDGE RECREATION CTR -RC BOILERS AND HVAC - M037-217M | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HCTR | HIGHBRIDGE RECREATION CTR -RC BOILERS AND HVAC - M037-217M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2019 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HEL3 | Phase 3 of Hell Gate Pathway, below Viaduct Randalls Island | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Feb 2015 | May 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HEL3 | Phase 3 of Hell Gate Pathway, below Viaduct Randalls Island | 2 | DESIGN | Dec 2016 | Dec 2017 | May 2018 | Oct 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HEL3 | Phase 3 of Hell Gate Pathway, below Viaduct Randalls Island | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Nov 2019 | Feb 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HEL3 | Phase 3 of Hell Gate Pathway, below Viaduct Randalls Island | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Feb 2020 | Feb 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HEL3 | Phase 3 of Hell Gate Pathway, below Viaduct Randalls Island | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Feb 2021 | Jun 2033
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HWTR | HIGHBRIDGE AQUEDUCT WATER TOWER RESTORATION M037-113M | 1 | DEVELOP SCOPE | Feb 2012 | May 2012 | Feb 2012 | May 2012
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HWTR | HIGHBRIDGE AQUEDUCT WATER TOWER RESTORATION M037-113M | 2 | DESIGN | May 2012 | Aug 2012 | May 2012 | Aug 2012
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HWTR | HIGHBRIDGE AQUEDUCT WATER TOWER RESTORATION M037-113M | 3 | BID/ REGISTER CONTRACT | Aug 2012 | Nov 2012 | Aug 2012 | Nov 2012
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HWTR | HIGHBRIDGE AQUEDUCT WATER TOWER RESTORATION M037-113M | 4 | CONSTRUCTION | Nov 2012 | Nov 2013 | Nov 2012 | Nov 2013
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HWTR | HIGHBRIDGE AQUEDUCT WATER TOWER RESTORATION M037-113M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2013 | Nov 2014 | Nov 2013 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGAP | Marcus Garvey Park Acropolis Reconstruction | 1 | DEVELOP SCOPE | Jan 2023 | Jun 2023 | Jan 2023 | Jun 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGAP | Marcus Garvey Park Acropolis Reconstruction | 2 | DESIGN | Jun 2023 | Jun 2024 | Jun 2023 | Jun 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGAP | Marcus Garvey Park Acropolis Reconstruction | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGAP | Marcus Garvey Park Acropolis Reconstruction | 4 | CONSTRUCTION | Mar 2025 | Mar 2026 | Mar 2025 | Mar 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGAP | Marcus Garvey Park Acropolis Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Jun 2028 | Mar 2026 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGFI | MARCUS GARVEY PK FIRE WATCHTOWER RESTORATION M058-115M | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Sep 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGFI | MARCUS GARVEY PK FIRE WATCHTOWER RESTORATION M058-115M | 2 | DESIGN | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGFI | MARCUS GARVEY PK FIRE WATCHTOWER RESTORATION M058-115M | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2014 | Mar 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGFI | MARCUS GARVEY PK FIRE WATCHTOWER RESTORATION M058-115M | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGFI | MARCUS GARVEY PK FIRE WATCHTOWER RESTORATION M058-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2016 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGLL | MARCUS GARVEY PRB LITTLE LEAGUE FACILTY M058-116M | 1 | DEVELOP SCOPE | Jul 2006 | Sep 2006 | Jul 2006 | Jan 2009
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGLL | MARCUS GARVEY PRB LITTLE LEAGUE FACILTY M058-116M | 2 | DESIGN | Sep 2006 | Dec 2006 | Jan 2009 | Feb 2011
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGLL | MARCUS GARVEY PRB LITTLE LEAGUE FACILTY M058-116M | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Jun 2016 | Jun 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGLL | MARCUS GARVEY PRB LITTLE LEAGUE FACILTY M058-116M | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Jul 2017 | Jul 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGLL | MARCUS GARVEY PRB LITTLE LEAGUE FACILTY M058-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Jul 2021 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PFFA | Pelham Fritz Rec. Center: Fire Alarm Reconstruction | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PFFA | Pelham Fritz Rec. Center: Fire Alarm Reconstruction | 2 | DESIGN | Dec 2019 | Dec 2021 | Dec 2019 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PFFA | Pelham Fritz Rec. Center: Fire Alarm Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PFFA | Pelham Fritz Rec. Center: Fire Alarm Reconstruction | 4 | CONSTRUCTION | Sep 2022 | Sep 2025 | Sep 2022 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PFFA | Pelham Fritz Rec. Center: Fire Alarm Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PFRC | PELHAM FRITZ REC CENTER | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PFRC | PELHAM FRITZ REC CENTER | 2 | DESIGN | Dec 2022 | Jun 2024 | Dec 2022 | Jun 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PFRC | PELHAM FRITZ REC CENTER | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PFRC | PELHAM FRITZ REC CENTER | 4 | CONSTRUCTION | Mar 2025 | Sep 2026 | Mar 2025 | Sep 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PFRC | PELHAM FRITZ REC CENTER | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Sep 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PFRI | MARCUS GARVEY PK -PELHAM FRITZ RECREATION CTR CONS M058-118M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PFRI | MARCUS GARVEY PK -PELHAM FRITZ RECREATION CTR CONS M058-118M | 2 | DESIGN | Dec 2016 | Dec 2018 | Dec 2016 | Dec 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PFRI | MARCUS GARVEY PK -PELHAM FRITZ RECREATION CTR CONS M058-118M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PFRI | MARCUS GARVEY PK -PELHAM FRITZ RECREATION CTR CONS M058-118M | 4 | CONSTRUCTION | Sep 2019 | Sep 2022 | Sep 2019 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PFRI | MARCUS GARVEY PK -PELHAM FRITZ RECREATION CTR CONS M058-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2024 | Sep 2022 | Aug 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PRPL | Poor Richard's Playground Renovations | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Jan 2016
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PRPL | Poor Richard's Playground Renovations | 2 | DESIGN | Sep 2015 | Dec 2015 | Jan 2016 | Apr 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PRPL | Poor Richard's Playground Renovations | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Jul 2017 | Jan 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PRPL | Poor Richard's Playground Renovations | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Aug 2018 | Aug 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PRPL | Poor Richard's Playground Renovations | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Aug 2019 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311RILS | RANDALLS ISLAND LIVING SHORELINE M104-116M | 2 | DESIGN | Dec 2012 | Mar 2013 | Sep 2011 | Dec 2011
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311RILS | RANDALLS ISLAND LIVING SHORELINE M104-116M | 3 | BID/ REGISTER CONTRACT | Mar 2013 | Jun 2013 | Dec 2011 | Mar 2012
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311RILS | RANDALLS ISLAND LIVING SHORELINE M104-116M | 4 | CONSTRUCTION | Jun 2013 | Jun 2014 | Mar 2012 | Mar 2013
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311RILS | RANDALLS ISLAND LIVING SHORELINE M104-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2014 | Jun 2015 | Mar 2013 | Mar 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311RIWR | Randall's Island - Waterfront Revitalization Program | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311RIWR | Randall's Island - Waterfront Revitalization Program | 2 | DESIGN | Dec 2022 | Dec 2024 | Dec 2022 | Dec 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311RIWR | Randall's Island - Waterfront Revitalization Program | 3 | BID/ REGISTER CONTRACT | Dec 2024 | Sep 2025 | Dec 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311RIWR | Randall's Island - Waterfront Revitalization Program | 4 | CONSTRUCTION | Sep 2025 | Sep 2028 | Sep 2025 | Sep 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311RIWR | Randall's Island - Waterfront Revitalization Program | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2028 | Sep 2030 | Sep 2028 | Sep 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJFA | Thomas Jefferson Rec. Center: Fire Alarm Reconstruction | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJFA | Thomas Jefferson Rec. Center: Fire Alarm Reconstruction | 2 | DESIGN | Dec 2019 | Dec 2021 | Dec 2019 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJFA | Thomas Jefferson Rec. Center: Fire Alarm Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJFA | Thomas Jefferson Rec. Center: Fire Alarm Reconstruction | 4 | CONSTRUCTION | Sep 2022 | Sep 2025 | Sep 2022 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJFA | Thomas Jefferson Rec. Center: Fire Alarm Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJHV | THOMAS JEFFERSON PARK REC CTR HVAC M047-109M | 1 | DEVELOP SCOPE | Jul 2007 | Sep 2007 | Jul 2007 | Jul 2008
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJHV | THOMAS JEFFERSON PARK REC CTR HVAC M047-109M | 2 | DESIGN | Sep 2007 | Dec 2007 | Jul 2008 | Jan 2009
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJHV | THOMAS JEFFERSON PARK REC CTR HVAC M047-109M | 3 | BID/ REGISTER CONTRACT | Dec 2007 | Mar 2008 | Mar 2009 | Jul 2009
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJHV | THOMAS JEFFERSON PARK REC CTR HVAC M047-109M | 4 | CONSTRUCTION | Mar 2008 | Mar 2009 | Jul 2009 | Sep 2010
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJHV | THOMAS JEFFERSON PARK REC CTR HVAC M047-109M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2009 | Mar 2010 | Sep 2010 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJMP | Thomas Jefferson rec ctr multi purpose room reco CNYG-420M | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJMP | Thomas Jefferson rec ctr multi purpose room reco CNYG-420M | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJMP | Thomas Jefferson rec ctr multi purpose room reco CNYG-420M | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJMP | Thomas Jefferson rec ctr multi purpose room reco CNYG-420M | 4 | CONSTRUCTION | Sep 2024 | Mar 2026 | Sep 2024 | Mar 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJMP | Thomas Jefferson rec ctr multi purpose room reco CNYG-420M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Mar 2027 | Mar 2026 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TURF | Harlem River Park Synthetic Turf, Manhattan M208D-219M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2014 | Dec 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TURF | Harlem River Park Synthetic Turf, Manhattan M208D-219M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2014 | Dec 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TURF | Harlem River Park Synthetic Turf, Manhattan M208D-219M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2015 | Sep 2016
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TURF | Harlem River Park Synthetic Turf, Manhattan M208D-219M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2016 | Sep 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TURF | Harlem River Park Synthetic Turf, Manhattan M208D-219M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2017 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311WATT | RANDALLS/WARDS ISLAND WIND, TIDAL & SOLAR PROJECT M107-107M | 1 | DEVELOP SCOPE | Jul 2006 | Sep 2006 | Jul 2006 | Sep 2006
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311WATT | RANDALLS/WARDS ISLAND WIND, TIDAL & SOLAR PROJECT M107-107M | 2 | DESIGN | Sep 2006 | Dec 2006 | Sep 2006 | Dec 2006
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311WATT | RANDALLS/WARDS ISLAND WIND, TIDAL & SOLAR PROJECT M107-107M | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Sep 2011 | Feb 2012
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311WATT | RANDALLS/WARDS ISLAND WIND, TIDAL & SOLAR PROJECT M107-107M | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Jul 2011 | Jul 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311WATT | RANDALLS/WARDS ISLAND WIND, TIDAL & SOLAR PROJECT M107-107M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Jul 2014 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312DACC | New Dominican American Cultural Center | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312DACC | New Dominican American Cultural Center | 2 | DESIGN | Dec 2022 | Dec 2024 | Dec 2022 | Dec 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312DACC | New Dominican American Cultural Center | 3 | BID/ REGISTER CONTRACT | Dec 2024 | Sep 2025 | Dec 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312DACC | New Dominican American Cultural Center | 4 | CONSTRUCTION | Sep 2025 | Sep 2028 | Sep 2025 | Sep 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312DACC | New Dominican American Cultural Center | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2028 | Sep 2030 | Sep 2028 | Sep 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312DFAR | DYCKMAN FARMHOUSE : ADA RAMP AND BATHROOM RENOVATION | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2014 | Dec 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312DFAR | DYCKMAN FARMHOUSE : ADA RAMP AND BATHROOM RENOVATION | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2014 | Dec 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312DFAR | DYCKMAN FARMHOUSE : ADA RAMP AND BATHROOM RENOVATION | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2015 | Sep 2016
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312DFAR | DYCKMAN FARMHOUSE : ADA RAMP AND BATHROOM RENOVATION | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2016 | Sep 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312DFAR | DYCKMAN FARMHOUSE : ADA RAMP AND BATHROOM RENOVATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2017 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312FTDR | Ft. Tryon Dog Run -- Install Water Service at Sir William's | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312FTDR | Ft. Tryon Dog Run -- Install Water Service at Sir William's | 2 | DESIGN | Dec 2022 | Jun 2024 | Dec 2022 | Jun 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312FTDR | Ft. Tryon Dog Run -- Install Water Service at Sir William's | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312FTDR | Ft. Tryon Dog Run -- Install Water Service at Sir William's | 4 | CONSTRUCTION | Mar 2025 | Sep 2026 | Mar 2025 | Sep 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312FTDR | Ft. Tryon Dog Run -- Install Water Service at Sir William's | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INNC | Inwood Hill Nature Center M042 -116M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INNC | Inwood Hill Nature Center M042 -116M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INNC | Inwood Hill Nature Center M042 -116M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INNC | Inwood Hill Nature Center M042 -116M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INNC | Inwood Hill Nature Center M042 -116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Jun 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INNG | RIVERSIDE-INWOOD NEIGHBORHOOD GARDENS, INC. | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Nov 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INNG | RIVERSIDE-INWOOD NEIGHBORHOOD GARDENS, INC. | 2 | DESIGN | Dec 2017 | Dec 2018 | Nov 2020 | Nov 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INNG | RIVERSIDE-INWOOD NEIGHBORHOOD GARDENS, INC. | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Nov 2024 | Aug 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INNG | RIVERSIDE-INWOOD NEIGHBORHOOD GARDENS, INC. | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Aug 2025 | Aug 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INNG | RIVERSIDE-INWOOD NEIGHBORHOOD GARDENS, INC. | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Aug 2026 | Aug 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INWD | Inwood Hill Nature Center- Exhibit Display Reconstruction | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Sep 2021 | Dec 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INWD | Inwood Hill Nature Center- Exhibit Display Reconstruction | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2025 | Dec 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INWD | Inwood Hill Nature Center- Exhibit Display Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2026 | Sep 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INWD | Inwood Hill Nature Center- Exhibit Display Reconstruction | 4 | CONSTRUCTION | Sep 2019 | Mar 2021 | Sep 2027 | Mar 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INWD | Inwood Hill Nature Center- Exhibit Display Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Mar 2022 | Mar 2029 | Mar 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312ITRY | INWOOD HILL & FT TRYON PARKS M029-210M | 1 | DEVELOP SCOPE | Jul 2007 | Sep 2007 | Jul 2007 | Sep 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312ITRY | INWOOD HILL & FT TRYON PARKS M029-210M | 2 | DESIGN | Sep 2007 | Dec 2007 | Sep 2004 | Apr 2013
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312ITRY | INWOOD HILL & FT TRYON PARKS M029-210M | 3 | BID/ REGISTER CONTRACT | Dec 2007 | Mar 2008 | Jan 2014 | Oct 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312ITRY | INWOOD HILL & FT TRYON PARKS M029-210M | 4 | CONSTRUCTION | Mar 2008 | Mar 2009 | Jun 2014 | Jun 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312ITRY | INWOOD HILL & FT TRYON PARKS M029-210M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2009 | Mar 2010 | Apr 2015 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JHFA | J. Hood Wright Rec. Center: Fire Alarm Reconstruction | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JHFA | J. Hood Wright Rec. Center: Fire Alarm Reconstruction | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JHFA | J. Hood Wright Rec. Center: Fire Alarm Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JHFA | J. Hood Wright Rec. Center: Fire Alarm Reconstruction | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JHFA | J. Hood Wright Rec. Center: Fire Alarm Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JHRW | J HOOD WRIGHT PARK REC CTR WINDOWS M099 | 1 | DEVELOP SCOPE | Jul 2012 | Sep 2012 | Jul 2010 | Sep 2010
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JHRW | J HOOD WRIGHT PARK REC CTR WINDOWS M099 | 2 | DESIGN | Sep 2012 | Dec 2012 | Sep 2010 | Dec 2010
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JHRW | J HOOD WRIGHT PARK REC CTR WINDOWS M099 | 3 | BID/ REGISTER CONTRACT | Dec 2012 | Mar 2013 | Dec 2010 | Mar 2011
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JHRW | J HOOD WRIGHT PARK REC CTR WINDOWS M099 | 4 | CONSTRUCTION | Mar 2013 | Mar 2014 | Mar 2011 | Mar 2012
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JHRW | J HOOD WRIGHT PARK REC CTR WINDOWS M099 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2014 | Mar 2015 | Mar 2012 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JHWD | J HOOD WRIGHT DOG RUN RENOVATION | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JHWD | J HOOD WRIGHT DOG RUN RENOVATION | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JHWD | J HOOD WRIGHT DOG RUN RENOVATION | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JHWD | J HOOD WRIGHT DOG RUN RENOVATION | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JHWD | J HOOD WRIGHT DOG RUN RENOVATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JJPG | Jacob Javits Plgr-renovation | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Feb 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JJPG | Jacob Javits Plgr-renovation | 2 | DESIGN | Sep 2014 | Dec 2014 | Feb 2015 | May 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JJPG | Jacob Javits Plgr-renovation | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Sep 2017 | Jun 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JJPG | Jacob Javits Plgr-renovation | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Jul 2018 | Nov 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JJPG | Jacob Javits Plgr-renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Nov 2019 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312LBPG | Fort Washington - Lily Brown Playground Renovation | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312LBPG | Fort Washington - Lily Brown Playground Renovation | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312LBPG | Fort Washington - Lily Brown Playground Renovation | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312LBPG | Fort Washington - Lily Brown Playground Renovation | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312LBPG | Fort Washington - Lily Brown Playground Renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312MJCR | MORRIS JUMEL MANSION--COLUMNS RESTORATION | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312MJCR | MORRIS JUMEL MANSION--COLUMNS RESTORATION | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312MJCR | MORRIS JUMEL MANSION--COLUMNS RESTORATION | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312MJCR | MORRIS JUMEL MANSION--COLUMNS RESTORATION | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312MJCR | MORRIS JUMEL MANSION--COLUMNS RESTORATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312MJM2 | Morris Jumel mansion - exterior renovation- ph II M073 | 1 | DEVELOP SCOPE | Jul 2011 | Sep 2011 | Jul 2011 | Sep 2011
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312MJM2 | Morris Jumel mansion - exterior renovation- ph II M073 | 2 | DESIGN | Sep 2011 | Dec 2011 | May 2012 | Jul 2013
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312MJM2 | Morris Jumel mansion - exterior renovation- ph II M073 | 3 | BID/ REGISTER CONTRACT | Dec 2011 | Mar 2012 | Nov 2013 | Jun 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312MJM2 | Morris Jumel mansion - exterior renovation- ph II M073 | 4 | CONSTRUCTION | Mar 2012 | Mar 2013 | Jul 2014 | Feb 2016
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312MJM2 | Morris Jumel mansion - exterior renovation- ph II M073 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2013 | Mar 2014 | Feb 2016 | Jun 2033
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312WRIT | P.S 28 (ORVILLE & WILBUR) PLGD& ADA UPGRADE TO PRB M234-109M | 1 | DEVELOP SCOPE | Jul 2008 | Sep 2008 | Jul 2008 | Jun 2009
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312WRIT | P.S 28 (ORVILLE & WILBUR) PLGD& ADA UPGRADE TO PRB M234-109M | 2 | DESIGN | Sep 2008 | Dec 2008 | Jun 2009 | Dec 2010
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312WRIT | P.S 28 (ORVILLE & WILBUR) PLGD& ADA UPGRADE TO PRB M234-109M | 3 | BID/ REGISTER CONTRACT | Dec 2008 | Mar 2009 | Dec 2010 | Jun 2011
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312WRIT | P.S 28 (ORVILLE & WILBUR) PLGD& ADA UPGRADE TO PRB M234-109M | 4 | CONSTRUCTION | Mar 2009 | Mar 2010 | Jun 2011 | Aug 2012
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312WRIT | P.S 28 (ORVILLE & WILBUR) PLGD& ADA UPGRADE TO PRB M234-109M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2010 | Mar 2011 | Aug 2012 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-313CPSW | Central Park - Swedish Cottage M010-116M | 1 | DEVELOP SCOPE | Jul 2008 | Sep 2008 | Jul 2008 | Jan 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-313CPSW | Central Park - Swedish Cottage M010-116M | 2 | DESIGN | Sep 2008 | Dec 2008 | Jan 2014 | Jan 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-313CPSW | Central Park - Swedish Cottage M010-116M | 3 | BID/ REGISTER CONTRACT | Dec 2008 | Mar 2009 | Jan 2014 | Jan 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-313CPSW | Central Park - Swedish Cottage M010-116M | 4 | CONSTRUCTION | Mar 2009 | Mar 2010 | Jan 2014 | Jan 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-313CPSW | Central Park - Swedish Cottage M010-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2010 | Mar 2011 | Jan 2014 | Nov 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-314RPDR | RIVERSIDE PARK DOG RUN M071 | 1 | DEVELOP SCOPE | Jul 2003 | Sep 2003 | Jul 2003 | Apr 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-314RPDR | RIVERSIDE PARK DOG RUN M071 | 2 | DESIGN | Sep 2003 | Dec 2003 | Jan 2020 | Apr 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-314RPDR | RIVERSIDE PARK DOG RUN M071 | 3 | BID/ REGISTER CONTRACT | Dec 2003 | Mar 2004 | Sep 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-314RPDR | RIVERSIDE PARK DOG RUN M071 | 4 | CONSTRUCTION | Mar 2004 | Mar 2005 | Mar 2023 | Mar 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-314RPDR | RIVERSIDE PARK DOG RUN M071 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2005 | Mar 2006 | Mar 2024 | Mar 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ALXHAM | Alexander Hamilton public restroom bldg CNYG-1922M | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2011 | May 2012
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ALXHAM | Alexander Hamilton public restroom bldg CNYG-1922M | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ALXHAM | Alexander Hamilton public restroom bldg CNYG-1922M | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ALXHAM | Alexander Hamilton public restroom bldg CNYG-1922M | 4 | CONSTRUCTION | Sep 2024 | Mar 2026 | Sep 2024 | Mar 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ALXHAM | Alexander Hamilton public restroom bldg CNYG-1922M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Mar 2027 | Mar 2026 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH01 | Highbridge Anchor Park Improvment- Manhattan | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH01 | Highbridge Anchor Park Improvment- Manhattan | 2 | DESIGN | Dec 2016 | Mar 2018 | Dec 2016 | Mar 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH01 | Highbridge Anchor Park Improvment- Manhattan | 3 | BID/ REGISTER CONTRACT | Mar 2018 | Dec 2018 | Mar 2018 | Dec 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH01 | Highbridge Anchor Park Improvment- Manhattan | 4 | CONSTRUCTION | Dec 2018 | Dec 2020 | Dec 2018 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH01 | Highbridge Anchor Park Improvment- Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2020 | Dec 2021 | Dec 2020 | Jun 2032
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH02 | Highbridge Anchor Park Phase II- Manhattan M037-118M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH02 | Highbridge Anchor Park Phase II- Manhattan M037-118M | 2 | DESIGN | Dec 2017 | Jun 2019 | Dec 2022 | Jun 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH02 | Highbridge Anchor Park Phase II- Manhattan M037-118M | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Mar 2020 | Jun 2024 | Mar 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH02 | Highbridge Anchor Park Phase II- Manhattan M037-118M | 4 | CONSTRUCTION | Mar 2020 | Sep 2021 | Mar 2025 | Sep 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH02 | Highbridge Anchor Park Phase II- Manhattan M037-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2026 | Jun 2033
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH03 | Highbridge Anchor Park Phase III- Public Restroom, M037-218M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH03 | Highbridge Anchor Park Phase III- Public Restroom, M037-218M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH03 | Highbridge Anchor Park Phase III- Public Restroom, M037-218M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH03 | Highbridge Anchor Park Phase III- Public Restroom, M037-218M | 4 | CONSTRUCTION | Sep 2019 | Mar 2021 | Sep 2019 | Mar 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH03 | Highbridge Anchor Park Phase III- Public Restroom, M037-218M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Mar 2022 | Mar 2021 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH04 | Highbridge Anchor Park Reconstruction Phase I, Manhattan | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH04 | Highbridge Anchor Park Reconstruction Phase I, Manhattan | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH04 | Highbridge Anchor Park Reconstruction Phase I, Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH04 | Highbridge Anchor Park Reconstruction Phase I, Manhattan | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH04 | Highbridge Anchor Park Reconstruction Phase I, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANNEPG | ANNE LOFTUS PLAYGROUND//WATER PARK, M029-118M, Mahattan | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2011 | May 2012
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANNEPG | ANNE LOFTUS PLAYGROUND//WATER PARK, M029-118M, Mahattan | 2 | DESIGN | Dec 2017 | Jun 2019 | Dec 2017 | Jun 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANNEPG | ANNE LOFTUS PLAYGROUND//WATER PARK, M029-118M, Mahattan | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Mar 2020 | Jun 2019 | Mar 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANNEPG | ANNE LOFTUS PLAYGROUND//WATER PARK, M029-118M, Mahattan | 4 | CONSTRUCTION | Mar 2020 | Sep 2021 | Mar 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANNEPG | ANNE LOFTUS PLAYGROUND//WATER PARK, M029-118M, Mahattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ASGRGN | ASPHALT GREEN: EMERGENCY GENERATOR PROJECT | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2024 | Dec 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ASGRGN | ASPHALT GREEN: EMERGENCY GENERATOR PROJECT | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2024 | Dec 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ASGRGN | ASPHALT GREEN: EMERGENCY GENERATOR PROJECT | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2025 | Sep 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ASGRGN | ASPHALT GREEN: EMERGENCY GENERATOR PROJECT | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2026 | Sep 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ASGRGN | ASPHALT GREEN: EMERGENCY GENERATOR PROJECT | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2027 | Sep 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ASGRSU | ASPHALT GREEN: CONSTRUCTION OF SUNDIAL PLAZA | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ASGRSU | ASPHALT GREEN: CONSTRUCTION OF SUNDIAL PLAZA | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ASGRSU | ASPHALT GREEN: CONSTRUCTION OF SUNDIAL PLAZA | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ASGRSU | ASPHALT GREEN: CONSTRUCTION OF SUNDIAL PLAZA | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ASGRSU | ASPHALT GREEN: CONSTRUCTION OF SUNDIAL PLAZA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ASRLVY | Asser Levy RC Envelope | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ASRLVY | Asser Levy RC Envelope | 2 | DESIGN | Dec 2022 | Dec 2024 | Dec 2022 | Dec 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ASRLVY | Asser Levy RC Envelope | 3 | BID/ REGISTER CONTRACT | Dec 2024 | Sep 2025 | Dec 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ASRLVY | Asser Levy RC Envelope | 4 | CONSTRUCTION | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ASRLVY | Asser Levy RC Envelope | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Jun 2031 | Sep 2027 | Jun 2031
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BBASIN | Riverside Park- Moving Costs Associated With The 79th Street | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2011 | May 2012
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BBASIN | Riverside Park- Moving Costs Associated With The 79th Street | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BBASIN | Riverside Park- Moving Costs Associated With The 79th Street | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BBASIN | Riverside Park- Moving Costs Associated With The 79th Street | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BBASIN | Riverside Park- Moving Costs Associated With The 79th Street | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BBGARD | BATTERY PARK SEAGLASS CAROUSEL M005-208M | 1 | DEVELOP SCOPE | Jul 2007 | Sep 2007 | Jul 2007 | Sep 2007
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BBGARD | BATTERY PARK SEAGLASS CAROUSEL M005-208M | 2 | DESIGN | Sep 2007 | Dec 2007 | Sep 2007 | Oct 2009
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BBGARD | BATTERY PARK SEAGLASS CAROUSEL M005-208M | 3 | BID/ REGISTER CONTRACT | Dec 2007 | Mar 2008 | Mar 2010 | Jul 2010
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BBGARD | BATTERY PARK SEAGLASS CAROUSEL M005-208M | 4 | CONSTRUCTION | Mar 2008 | Mar 2009 | Sep 2010 | Jun 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BBGARD | BATTERY PARK SEAGLASS CAROUSEL M005-208M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2009 | Mar 2010 | Jun 2015 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BELLVU | BELLEVUE PARK SOUTH, RECONS Manhattan | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2015 | Jul 2016
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BELLVU | BELLEVUE PARK SOUTH, RECONS Manhattan | 2 | DESIGN | Dec 2017 | Dec 2018 | Jul 2016 | Dec 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BELLVU | BELLEVUE PARK SOUTH, RECONS Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Mar 2021 | Apr 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BELLVU | BELLEVUE PARK SOUTH, RECONS Manhattan | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Jun 2021 | Jun 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BELLVU | BELLEVUE PARK SOUTH, RECONS Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Jun 2022 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BENNSF | BENNETT PARK SYNTHETIC FIELD | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BENNSF | BENNETT PARK SYNTHETIC FIELD | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BENNSF | BENNETT PARK SYNTHETIC FIELD | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BENNSF | BENNETT PARK SYNTHETIC FIELD | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BENNSF | BENNETT PARK SYNTHETIC FIELD | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BOTWAT | 6BC Botanical Garden:Garden Water Source | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BOTWAT | 6BC Botanical Garden:Garden Water Source | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BOTWAT | 6BC Botanical Garden:Garden Water Source | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BOTWAT | 6BC Botanical Garden:Garden Water Source | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BOTWAT | 6BC Botanical Garden:Garden Water Source | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BPPLGD | BATTERY PARK Plg (SOUTH FERRY-MTA) M005-117M | 1 | DEVELOP SCOPE | Jul 2006 | Sep 2006 | Jul 2006 | Oct 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BPPLGD | BATTERY PARK Plg (SOUTH FERRY-MTA) M005-117M | 2 | DESIGN | Sep 2006 | Dec 2006 | Sep 2006 | Mar 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BPPLGD | BATTERY PARK Plg (SOUTH FERRY-MTA) M005-117M | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Jul 2019 | Nov 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BPPLGD | BATTERY PARK Plg (SOUTH FERRY-MTA) M005-117M | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Dec 2019 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BPPLGD | BATTERY PARK Plg (SOUTH FERRY-MTA) M005-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Jan 2022 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BWTRAM | TRAMWAY PLAZA RECONST - E.59TH - E.60TH STS M280-102MA1 | 1 | DEVELOP SCOPE | Jul 2003 | Sep 2003 | Jul 2003 | Sep 2003
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BWTRAM | TRAMWAY PLAZA RECONST - E.59TH - E.60TH STS M280-102MA1 | 2 | DESIGN | Sep 2003 | Mar 2004 | Sep 2003 | Dec 2005
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BWTRAM | TRAMWAY PLAZA RECONST - E.59TH - E.60TH STS M280-102MA1 | 3 | BID/ REGISTER CONTRACT | Mar 2004 | Jun 2004 | Jan 2006 | Apr 2006
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BWTRAM | TRAMWAY PLAZA RECONST - E.59TH - E.60TH STS M280-102MA1 | 4 | CONSTRUCTION | Jun 2004 | Feb 2005 | May 2006 | Feb 2007
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BWTRAM | TRAMWAY PLAZA RECONST - E.59TH - E.60TH STS M280-102MA1 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2005 | Feb 2006 | Feb 2007 | Feb 2008
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BWWAT1 | Riverside Oval and Verdi Square Water Serv. Install MG-123M | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BWWAT1 | Riverside Oval and Verdi Square Water Serv. Install MG-123M | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BWWAT1 | Riverside Oval and Verdi Square Water Serv. Install MG-123M | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BWWAT1 | Riverside Oval and Verdi Square Water Serv. Install MG-123M | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BWWAT1 | Riverside Oval and Verdi Square Water Serv. Install MG-123M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BWWATE | RPZ - WATER SERVICE INSTALLATION MG-518M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BWWATE | RPZ - WATER SERVICE INSTALLATION MG-518M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BWWATE | RPZ - WATER SERVICE INSTALLATION MG-518M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BWWATE | RPZ - WATER SERVICE INSTALLATION MG-518M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BWWATE | RPZ - WATER SERVICE INSTALLATION MG-518M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CBHVAC | Constance Baker Motley Rec Ctr HVAC Recon | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CBHVAC | Constance Baker Motley Rec Ctr HVAC Recon | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CBHVAC | Constance Baker Motley Rec Ctr HVAC Recon | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CBHVAC | Constance Baker Motley Rec Ctr HVAC Recon | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CBHVAC | Constance Baker Motley Rec Ctr HVAC Recon | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENBOL | Central Park - Construction Security Measures M010-221M | 1 | DEVELOP SCOPE | May 2018 | Nov 2018 | May 2018 | Nov 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENBOL | Central Park - Construction Security Measures M010-221M | 2 | DESIGN | Nov 2018 | Nov 2020 | Nov 2018 | Nov 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENBOL | Central Park - Construction Security Measures M010-221M | 3 | BID/ REGISTER CONTRACT | Nov 2020 | Aug 2021 | Nov 2020 | Aug 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENBOL | Central Park - Construction Security Measures M010-221M | 4 | CONSTRUCTION | Aug 2021 | Aug 2023 | Aug 2021 | Aug 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENBOL | Central Park - Construction Security Measures M010-221M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2023 | Aug 2024 | Aug 2023 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENCCA | Const-Accessibility of Chess and Checkers & Site Improvement | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENCCA | Const-Accessibility of Chess and Checkers & Site Improvement | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENCCA | Const-Accessibility of Chess and Checkers & Site Improvement | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENCCA | Const-Accessibility of Chess and Checkers & Site Improvement | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENCCA | Const-Accessibility of Chess and Checkers & Site Improvement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENCGD | Central Park Conservatory Gdn N End Drainage & Site Recon | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENCGD | Central Park Conservatory Gdn N End Drainage & Site Recon | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENCGD | Central Park Conservatory Gdn N End Drainage & Site Recon | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENCGD | Central Park Conservatory Gdn N End Drainage & Site Recon | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENCGD | Central Park Conservatory Gdn N End Drainage & Site Recon | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENDLC | Central Park Delacorte Theater Restrooms | 1 | DEVELOP SCOPE | Oct 2023 | Mar 2024 | Oct 2023 | Mar 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENDLC | Central Park Delacorte Theater Restrooms | 2 | DESIGN | Mar 2024 | Mar 2025 | Mar 2024 | Mar 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENDLC | Central Park Delacorte Theater Restrooms | 3 | BID/ REGISTER CONTRACT | Mar 2025 | Dec 2025 | Mar 2025 | Dec 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENDLC | Central Park Delacorte Theater Restrooms | 4 | CONSTRUCTION | Dec 2025 | Jun 2027 | Dec 2025 | Jun 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENDLC | Central Park Delacorte Theater Restrooms | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2027 | Jun 2028 | Jun 2027 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENHMP | CENTRAL PARK CONSERVANCY-HARLEM MEER RENO | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENHMP | CENTRAL PARK CONSERVANCY-HARLEM MEER RENO | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENHMP | CENTRAL PARK CONSERVANCY-HARLEM MEER RENO | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENHMP | CENTRAL PARK CONSERVANCY-HARLEM MEER RENO | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENHMP | CENTRAL PARK CONSERVANCY-HARLEM MEER RENO | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENNMC | Central Park N Meadow Recreation Ct Recon & Veh Charging Con | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENNMC | Central Park N Meadow Recreation Ct Recon & Veh Charging Con | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENNMC | Central Park N Meadow Recreation Ct Recon & Veh Charging Con | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENNMC | Central Park N Meadow Recreation Ct Recon & Veh Charging Con | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENNMC | Central Park N Meadow Recreation Ct Recon & Veh Charging Con | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT08 | Central Park - Recons of Perimeter E84-E108ST WO# 8 | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT08 | Central Park - Recons of Perimeter E84-E108ST WO# 8 | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT08 | Central Park - Recons of Perimeter E84-E108ST WO# 8 | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT08 | Central Park - Recons of Perimeter E84-E108ST WO# 8 | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT08 | Central Park - Recons of Perimeter E84-E108ST WO# 8 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT13 | Recon. of Naumburg Bandshell in Central Park, WO#13, | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Sep 2012 | Mar 2013
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT13 | Recon. of Naumburg Bandshell in Central Park, WO#13, | 2 | DESIGN | Dec 2018 | Dec 2019 | Mar 2013 | Mar 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT13 | Recon. of Naumburg Bandshell in Central Park, WO#13, | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Mar 2014 | Dec 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT13 | Recon. of Naumburg Bandshell in Central Park, WO#13, | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Dec 2014 | Dec 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT13 | Recon. of Naumburg Bandshell in Central Park, WO#13, | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Dec 2015 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENTRL | Central Park - Roller Skating Park Repaving, Manhattan | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENTRL | Central Park - Roller Skating Park Repaving, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CMGWAT | Childrens Magical Garden:Drinking Fountain/Water Spigot | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2011 | May 2012
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CMGWAT | Childrens Magical Garden:Drinking Fountain/Water Spigot | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CMGWAT | Childrens Magical Garden:Drinking Fountain/Water Spigot | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CMGWAT | Childrens Magical Garden:Drinking Fountain/Water Spigot | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CMGWAT | Childrens Magical Garden:Drinking Fountain/Water Spigot | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3COLPCS | COLUMBUS PARK -RENOVATE PRB ON WORTH STREET | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2024 | Dec 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3COLPCS | COLUMBUS PARK -RENOVATE PRB ON WORTH STREET | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2024 | Dec 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3COLPCS | COLUMBUS PARK -RENOVATE PRB ON WORTH STREET | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2025 | Sep 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3COLPCS | COLUMBUS PARK -RENOVATE PRB ON WORTH STREET | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2026 | Sep 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3COLPCS | COLUMBUS PARK -RENOVATE PRB ON WORTH STREET | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2027 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3COLUMB | COLUMBUS PARK - Entrance Renovation, Manhattan | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Sep 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3COLUMB | COLUMBUS PARK - Entrance Renovation, Manhattan | 2 | DESIGN | Dec 2016 | Dec 2017 | Sep 2017 | Apr 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3COLUMB | COLUMBUS PARK - Entrance Renovation, Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Aug 2018 | Jun 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3COLUMB | COLUMBUS PARK - Entrance Renovation, Manhattan | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Jul 2019 | Oct 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3COLUMB | COLUMBUS PARK - Entrance Renovation, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Oct 2020 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3A2 | CPI PH2 - ABRAHAM LINCOLN PRB RC | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3A2 | CPI PH2 - ABRAHAM LINCOLN PRB RC | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3A2 | CPI PH2 - ABRAHAM LINCOLN PRB RC | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3A2 | CPI PH2 - ABRAHAM LINCOLN PRB RC | 4 | CONSTRUCTION | Sep 2019 | Mar 2021 | Sep 2019 | Mar 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3A2 | CPI PH2 - ABRAHAM LINCOLN PRB RC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Mar 2022 | Mar 2021 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AB | CPI PH2 - Audubon Plg & PRBs Reconstruction (DESIGN) | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2016 | Dec 2016
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AB | CPI PH2 - Audubon Plg & PRBs Reconstruction (DESIGN) | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2016 | Dec 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AB | CPI PH2 - Audubon Plg & PRBs Reconstruction (DESIGN) | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2017 | Sep 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AB | CPI PH2 - Audubon Plg & PRBs Reconstruction (DESIGN) | 4 | CONSTRUCTION | Sep 2019 | Mar 2021 | Sep 2018 | Mar 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AB | CPI PH2 - Audubon Plg & PRBs Reconstruction (DESIGN) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Mar 2022 | Mar 2020 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AC | CPI PH2 - Audubon Public Restroom Buildings Recons M240-218M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AC | CPI PH2 - Audubon Public Restroom Buildings Recons M240-218M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AC | CPI PH2 - Audubon Public Restroom Buildings Recons M240-218M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AC | CPI PH2 - Audubon Public Restroom Buildings Recons M240-218M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AC | CPI PH2 - Audubon Public Restroom Buildings Recons M240-218M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AL | CPI PH2 - Abraham Lincoln plg .... | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2015 | Dec 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AL | CPI PH2 - Abraham Lincoln plg .... | 2 | DESIGN | Dec 2017 | Jun 2019 | Dec 2015 | Jun 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AL | CPI PH2 - Abraham Lincoln plg .... | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Mar 2020 | Jun 2017 | Mar 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AL | CPI PH2 - Abraham Lincoln plg .... | 4 | CONSTRUCTION | Mar 2020 | Sep 2021 | Mar 2018 | Sep 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AL | CPI PH2 - Abraham Lincoln plg .... | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2019 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIAAP | CPI - ANIBAL AVILES PLGD | 1 | DEVELOP SCOPE | Apr 2022 | Sep 2022 | Apr 2022 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIAAP | CPI - ANIBAL AVILES PLGD | 2 | DESIGN | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIAAP | CPI - ANIBAL AVILES PLGD | 3 | BID/ REGISTER CONTRACT | Sep 2023 | Jun 2024 | Sep 2023 | Jun 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIAAP | CPI - ANIBAL AVILES PLGD | 4 | CONSTRUCTION | Jun 2024 | Jun 2025 | Jun 2024 | Jun 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIAAP | CPI - ANIBAL AVILES PLGD | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIBN9 | CPI PH1 Plg 103 and St Nicholas North Plg Recons (MG-216M) | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIBN9 | CPI PH1 Plg 103 and St Nicholas North Plg Recons (MG-216M) | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIBN9 | CPI PH1 Plg 103 and St Nicholas North Plg Recons (MG-216M) | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Feb 2016 | Oct 2016
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIBN9 | CPI PH1 Plg 103 and St Nicholas North Plg Recons (MG-216M) | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Nov 2016 | May 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIBN9 | CPI PH1 Plg 103 and St Nicholas North Plg Recons (MG-216M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | May 2018 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIDOE | CPI - DETECTIVE OMAR EDWARDS PLGD | 1 | DEVELOP SCOPE | Mar 2022 | Aug 2022 | Mar 2022 | Aug 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIDOE | CPI - DETECTIVE OMAR EDWARDS PLGD | 2 | DESIGN | Aug 2022 | Aug 2023 | Aug 2022 | Aug 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIDOE | CPI - DETECTIVE OMAR EDWARDS PLGD | 3 | BID/ REGISTER CONTRACT | Aug 2023 | May 2024 | Aug 2023 | May 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIDOE | CPI - DETECTIVE OMAR EDWARDS PLGD | 4 | CONSTRUCTION | May 2024 | May 2025 | May 2024 | May 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIDOE | CPI - DETECTIVE OMAR EDWARDS PLGD | 5 | PUNCHLIST COMPLETE, JOB CLOSED | May 2025 | May 2026 | May 2025 | May 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIERP | East River Playground, FDR Drive E 106 St to E 107 St, M258 | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIERP | East River Playground, FDR Drive E 106 St to E 107 St, M258 | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIERP | East River Playground, FDR Drive E 106 St to E 107 St, M258 | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIERP | East River Playground, FDR Drive E 106 St to E 107 St, M258 | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIERP | East River Playground, FDR Drive E 106 St to E 107 St, M258 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIFGC | CPI PH2 - Frederick Johnson Public Restroom, M141-418M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIFGC | CPI PH2 - Frederick Johnson Public Restroom, M141-418M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIFGC | CPI PH2 - Frederick Johnson Public Restroom, M141-418M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIFGC | CPI PH2 - Frederick Johnson Public Restroom, M141-418M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIFGC | CPI PH2 - Frederick Johnson Public Restroom, M141-418M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIHLP | CPI PH2 - Harlem Lane Playground, MG-119M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIHLP | CPI PH2 - Harlem Lane Playground, MG-119M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIHLP | CPI PH2 - Harlem Lane Playground, MG-119M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIHLP | CPI PH2 - Harlem Lane Playground, MG-119M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIHLP | CPI PH2 - Harlem Lane Playground, MG-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIHRP | CPI - Holcombe Rucker Park Playground Reconstruction | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIHRP | CPI - Holcombe Rucker Park Playground Reconstruction | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIHRP | CPI - Holcombe Rucker Park Playground Reconstruction | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIHRP | CPI - Holcombe Rucker Park Playground Reconstruction | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIHRP | CPI - Holcombe Rucker Park Playground Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIPMP | CPI - Peter Minuit Playground Reconstruction | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIPMP | CPI - Peter Minuit Playground Reconstruction | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIPMP | CPI - Peter Minuit Playground Reconstruction | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIPMP | CPI - Peter Minuit Playground Reconstruction | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIPMP | CPI - Peter Minuit Playground Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIRNP | CPI RENAISSANCE PLGD RC M245 | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIRNP | CPI RENAISSANCE PLGD RC M245 | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIRNP | CPI RENAISSANCE PLGD RC M245 | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIRNP | CPI RENAISSANCE PLGD RC M245 | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIRNP | CPI RENAISSANCE PLGD RC M245 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Jun 2030 | Sep 2025 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPISNS | St. Nicholas Playground South Reconstruction | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPISNS | St. Nicholas Playground South Reconstruction | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPISNS | St. Nicholas Playground South Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPISNS | St. Nicholas Playground South Reconstruction | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPISNS | St. Nicholas Playground South Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Jun 2030 | Sep 2025 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPISUR | CPI PH2 - Sauer Playground | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Oct 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPISUR | CPI PH2 - Sauer Playground | 2 | DESIGN | Dec 2017 | Dec 2018 | Oct 2017 | Oct 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPISUR | CPI PH2 - Sauer Playground | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Feb 2019 | Jul 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPISUR | CPI PH2 - Sauer Playground | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Oct 2019 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPISUR | CPI PH2 - Sauer Playground | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Dec 2020 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPPERM | Central Park- RC -Perimeter Landscape E. 90th to E 110th | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPPERM | Central Park- RC -Perimeter Landscape E. 90th to E 110th | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPPERM | Central Park- RC -Perimeter Landscape E. 90th to E 110th | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPPERM | Central Park- RC -Perimeter Landscape E. 90th to E 110th | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPPERM | Central Park- RC -Perimeter Landscape E. 90th to E 110th | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CRHVAC | Chelsea Rec Ctr HVAC Recon | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CRHVAC | Chelsea Rec Ctr HVAC Recon | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CRHVAC | Chelsea Rec Ctr HVAC Recon | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CRHVAC | Chelsea Rec Ctr HVAC Recon | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CRHVAC | Chelsea Rec Ctr HVAC Recon | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CSPBOL | Carl Schulz Pk- Construction Security Measures M081-120M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CSPBOL | Carl Schulz Pk- Construction Security Measures M081-120M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CSPBOL | Carl Schulz Pk- Construction Security Measures M081-120M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CSPBOL | Carl Schulz Pk- Construction Security Measures M081-120M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CSPBOL | Carl Schulz Pk- Construction Security Measures M081-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CYPGCS | Colonel Young Plgd- Public Restroom Bldg M186-122M | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CYPGCS | Colonel Young Plgd- Public Restroom Bldg M186-122M | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CYPGCS | Colonel Young Plgd- Public Restroom Bldg M186-122M | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CYPGCS | Colonel Young Plgd- Public Restroom Bldg M186-122M | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CYPGCS | Colonel Young Plgd- Public Restroom Bldg M186-122M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DAGHAM | Dag Hammarskjold Plaza, Manhattan | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | May 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DAGHAM | Dag Hammarskjold Plaza, Manhattan | 2 | DESIGN | Dec 2016 | Dec 2017 | Jun 2017 | Jul 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DAGHAM | Dag Hammarskjold Plaza, Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2019 | Mar 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DAGHAM | Dag Hammarskjold Plaza, Manhattan | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DAGHAM | Dag Hammarskjold Plaza, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2021 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DIRVPK | Riverside Park-Critical Drainage Infrastructure | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DIRVPK | Riverside Park-Critical Drainage Infrastructure | 2 | DESIGN | Dec 2019 | Dec 2021 | Dec 2019 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DIRVPK | Riverside Park-Critical Drainage Infrastructure | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DIRVPK | Riverside Park-Critical Drainage Infrastructure | 4 | CONSTRUCTION | Sep 2022 | Sep 2024 | Sep 2022 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DIRVPK | Riverside Park-Critical Drainage Infrastructure | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Jun 2031
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3FCSADA | Fort Washington Park PRB renovation to Make it ADA Compliant | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3FCSADA | Fort Washington Park PRB renovation to Make it ADA Compliant | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3FCSADA | Fort Washington Park PRB renovation to Make it ADA Compliant | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3FCSADA | Fort Washington Park PRB renovation to Make it ADA Compliant | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3FCSADA | Fort Washington Park PRB renovation to Make it ADA Compliant | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GRST01 | Greenstreets - Manhattan Greenstreets Planting | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GRST01 | Greenstreets - Manhattan Greenstreets Planting | 2 | DESIGN | Dec 2020 | Jun 2022 | Dec 2020 | Jun 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GRST01 | Greenstreets - Manhattan Greenstreets Planting | 3 | BID/ REGISTER CONTRACT | Jun 2022 | Mar 2023 | Jun 2022 | Mar 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GRST01 | Greenstreets - Manhattan Greenstreets Planting | 4 | CONSTRUCTION | Mar 2023 | Mar 2025 | Mar 2023 | Mar 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GRST01 | Greenstreets - Manhattan Greenstreets Planting | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Mar 2027 | Mar 2025 | Mar 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GRTDRF | Gertrude Ederle Recreation Center Roof Reconstruction | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GRTDRF | Gertrude Ederle Recreation Center Roof Reconstruction | 2 | DESIGN | Sep 2023 | Sep 2025 | Sep 2023 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GRTDRF | Gertrude Ederle Recreation Center Roof Reconstruction | 3 | BID/ REGISTER CONTRACT | Sep 2025 | Jun 2026 | Sep 2025 | Jun 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GRTDRF | Gertrude Ederle Recreation Center Roof Reconstruction | 4 | CONSTRUCTION | Jun 2026 | Jun 2029 | Jun 2026 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GRTDRF | Gertrude Ederle Recreation Center Roof Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2029 | Jun 2031 | Jun 2029 | Jun 2031
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GTACQM | Land Acuisition: Green Thumb on 143rd ST, Manhattan | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GTACQM | Land Acuisition: Green Thumb on 143rd ST, Manhattan | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GTACQM | Land Acuisition: Green Thumb on 143rd ST, Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GTACQM | Land Acuisition: Green Thumb on 143rd ST, Manhattan | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GTACQM | Land Acuisition: Green Thumb on 143rd ST, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HBCGRD | Highbridge Community Garden | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HBCGRD | Highbridge Community Garden | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HBCGRD | Highbridge Community Garden | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2022 | Oct 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HBCGRD | Highbridge Community Garden | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2022 | Mar 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HBCGRD | Highbridge Community Garden | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2024 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HELIP2 | Heliport(Andrew Haswell) Park - phase 2 M108-109M | 1 | DEVELOP SCOPE | Jul 2007 | Sep 2007 | Jun 2003 | Apr 2004
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HELIP2 | Heliport(Andrew Haswell) Park - phase 2 M108-109M | 2 | DESIGN | Sep 2007 | Dec 2007 | Apr 2008 | Dec 2013
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HELIP2 | Heliport(Andrew Haswell) Park - phase 2 M108-109M | 3 | BID/ REGISTER CONTRACT | Dec 2007 | Mar 2008 | Jun 2014 | Jun 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HELIP2 | Heliport(Andrew Haswell) Park - phase 2 M108-109M | 4 | CONSTRUCTION | Mar 2008 | Mar 2009 | Aug 2015 | Jan 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HELIP2 | Heliport(Andrew Haswell) Park - phase 2 M108-109M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2009 | Mar 2010 | Feb 2017 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HGLNPH | HIGHLINE-Path replace Rail Track Rehab, Lead Paint, light | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2024 | Dec 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HGLNPH | HIGHLINE-Path replace Rail Track Rehab, Lead Paint, light | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2024 | Dec 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HGLNPH | HIGHLINE-Path replace Rail Track Rehab, Lead Paint, light | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2025 | Sep 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HGLNPH | HIGHLINE-Path replace Rail Track Rehab, Lead Paint, light | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2026 | Sep 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HGLNPH | HIGHLINE-Path replace Rail Track Rehab, Lead Paint, light | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2027 | Sep 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HGLNRC | HIGHLINE Reconstruction, Misc Park & Playground., | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2024 | Dec 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HGLNRC | HIGHLINE Reconstruction, Misc Park & Playground., | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2024 | Dec 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HGLNRC | HIGHLINE Reconstruction, Misc Park & Playground., | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2025 | Sep 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HGLNRC | HIGHLINE Reconstruction, Misc Park & Playground., | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2026 | Sep 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HGLNRC | HIGHLINE Reconstruction, Misc Park & Playground., | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2027 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HIGHL3 | FRIENDS OF THE HIGH LINE- Western Rail Yards, Manhattan | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HIGHL3 | FRIENDS OF THE HIGH LINE- Western Rail Yards, Manhattan | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2021 | Nov 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HIGHL3 | FRIENDS OF THE HIGH LINE- Western Rail Yards, Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Jan 2023 | Jul 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HIGHL3 | FRIENDS OF THE HIGH LINE- Western Rail Yards, Manhattan | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HIGHL3 | FRIENDS OF THE HIGH LINE- Western Rail Yards, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2024 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HLELV1 | FRIENDS OF THE HIGHLINE-ELEVATOR MODERNIZATION | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HLELV1 | FRIENDS OF THE HIGHLINE-ELEVATOR MODERNIZATION | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HLELV1 | FRIENDS OF THE HIGHLINE-ELEVATOR MODERNIZATION | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HLELV1 | FRIENDS OF THE HIGHLINE-ELEVATOR MODERNIZATION | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HLELV1 | FRIENDS OF THE HIGHLINE-ELEVATOR MODERNIZATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Jun 2028 | Sep 2025 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HLGATE | High Line Safety and Accessibility Improvements | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HLGATE | High Line Safety and Accessibility Improvements | 2 | DESIGN | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HLGATE | High Line Safety and Accessibility Improvements | 3 | BID/ REGISTER CONTRACT | Sep 2024 | Jun 2025 | Sep 2024 | Jun 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HLGATE | High Line Safety and Accessibility Improvements | 4 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HLGATE | High Line Safety and Accessibility Improvements | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Jun 2027 | Jun 2026 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HLNACC | Friends of Highline: accessibility, secur/safety, Manhattan | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HLNACC | Friends of Highline: accessibility, secur/safety, Manhattan | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HLNACC | Friends of Highline: accessibility, secur/safety, Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HLNACC | Friends of Highline: accessibility, secur/safety, Manhattan | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HLNACC | Friends of Highline: accessibility, secur/safety, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HLNERP | FRIENDS OF THE HIGH LINE: HIGH LINE REPAIRS | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HLNERP | FRIENDS OF THE HIGH LINE: HIGH LINE REPAIRS | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HLNERP | FRIENDS OF THE HIGH LINE: HIGH LINE REPAIRS | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HLNERP | FRIENDS OF THE HIGH LINE: HIGH LINE REPAIRS | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HLNERP | FRIENDS OF THE HIGH LINE: HIGH LINE REPAIRS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HMFISH | Hamilton Fish Park Basketball Courts and Adult Fitness | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HMFISH | Hamilton Fish Park Basketball Courts and Adult Fitness | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HMFISH | Hamilton Fish Park Basketball Courts and Adult Fitness | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HMFISH | Hamilton Fish Park Basketball Courts and Adult Fitness | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HMFISH | Hamilton Fish Park Basketball Courts and Adult Fitness | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HR2944 | HRPT - 29th to 44th Sts. Construction, Manhattan | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HR2944 | HRPT - 29th to 44th Sts. Construction, Manhattan | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HR2944 | HRPT - 29th to 44th Sts. Construction, Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Jul 2024 | Oct 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HR2944 | HRPT - 29th to 44th Sts. Construction, Manhattan | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Dec 2024 | Dec 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HR2944 | HRPT - 29th to 44th Sts. Construction, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Dec 2025 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP26S | HRPT-Pier 26 Science Playground | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP26S | HRPT-Pier 26 Science Playground | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP26S | HRPT-Pier 26 Science Playground | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP26S | HRPT-Pier 26 Science Playground | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP26S | HRPT-Pier 26 Science Playground | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP26U | HRPT: Pier 26 Upland Estuarium Construction | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP26U | HRPT: Pier 26 Upland Estuarium Construction | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP26U | HRPT: Pier 26 Upland Estuarium Construction | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2023 | Aug 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP26U | HRPT: Pier 26 Upland Estuarium Construction | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2024 | Aug 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP26U | HRPT: Pier 26 Upland Estuarium Construction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2025 | Jun 2031
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP45A | HRPT - Pier 45 Boardwalk Reconstruction | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP45A | HRPT - Pier 45 Boardwalk Reconstruction | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP45A | HRPT - Pier 45 Boardwalk Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP45A | HRPT - Pier 45 Boardwalk Reconstruction | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP45A | HRPT - Pier 45 Boardwalk Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPCW1 | HARRIET TUBMAN MEMORIAL BEAUTIFICATION, Manhattan | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2025 | Dec 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPCW1 | HARRIET TUBMAN MEMORIAL BEAUTIFICATION, Manhattan | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2025 | Dec 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPCW1 | HARRIET TUBMAN MEMORIAL BEAUTIFICATION, Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2026 | Sep 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPCW1 | HARRIET TUBMAN MEMORIAL BEAUTIFICATION, Manhattan | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2027 | Sep 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPCW1 | HARRIET TUBMAN MEMORIAL BEAUTIFICATION, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2028 | Sep 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPCWP | HRPT - Chelsea Waterside Park Phase 2 | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Mar 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPCWP | HRPT - Chelsea Waterside Park Phase 2 | 2 | DESIGN | Dec 2016 | Dec 2017 | Mar 2019 | Mar 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPCWP | HRPT - Chelsea Waterside Park Phase 2 | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Nov 2020 | May 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPCWP | HRPT - Chelsea Waterside Park Phase 2 | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Dec 2021 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPCWP | HRPT - Chelsea Waterside Park Phase 2 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Dec 2022 | Jun 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPDG8 | HUDSON RIVER PARK TRUST PIER 84 DOG RUN | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPDG8 | HUDSON RIVER PARK TRUST PIER 84 DOG RUN | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPDG8 | HUDSON RIVER PARK TRUST PIER 84 DOG RUN | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPDG8 | HUDSON RIVER PARK TRUST PIER 84 DOG RUN | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPDG8 | HUDSON RIVER PARK TRUST PIER 84 DOG RUN | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPLIT | HRPT PARK LIGHTING ENHANCEMNT | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPLIT | HRPT PARK LIGHTING ENHANCEMNT | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPLIT | HRPT PARK LIGHTING ENHANCEMNT | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPLIT | HRPT PARK LIGHTING ENHANCEMNT | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPLIT | HRPT PARK LIGHTING ENHANCEMNT | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPT34 | HUDSON RIVER PARK | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPT34 | HUDSON RIVER PARK | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPT34 | HUDSON RIVER PARK | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPT34 | HUDSON RIVER PARK | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPT34 | HUDSON RIVER PARK | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2025 | Sep 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPTEN | Houston St. Tennis Courts RC | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPTEN | Houston St. Tennis Courts RC | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPTEN | Houston St. Tennis Courts RC | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPTEN | Houston St. Tennis Courts RC | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPTEN | Houston St. Tennis Courts RC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPTPK | HRPT- Gansevoort Peninsula Park Construction., Manhattan | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPTPK | HRPT- Gansevoort Peninsula Park Construction., Manhattan | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPTPK | HRPT- Gansevoort Peninsula Park Construction., Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPTPK | HRPT- Gansevoort Peninsula Park Construction., Manhattan | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPTPK | HRPT- Gansevoort Peninsula Park Construction., Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPTSC | HUDSON RIVER PARK TRUST SECURITY CAMERAS | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPTSC | HUDSON RIVER PARK TRUST SECURITY CAMERAS | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPTSC | HUDSON RIVER PARK TRUST SECURITY CAMERAS | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPTSC | HUDSON RIVER PARK TRUST SECURITY CAMERAS | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPTSC | HUDSON RIVER PARK TRUST SECURITY CAMERAS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3INHILL | Inwood Hill Park - Baseball fields,Manhattan | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Jan 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3INHILL | Inwood Hill Park - Baseball fields,Manhattan | 2 | DESIGN | Dec 2017 | Dec 2018 | Jan 2020 | Jan 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3INHILL | Inwood Hill Park - Baseball fields,Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Apr 2021 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3INHILL | Inwood Hill Park - Baseball fields,Manhattan | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Oct 2021 | Oct 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3INHILL | Inwood Hill Park - Baseball fields,Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Oct 2022 | Jun 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ISAAC | Stanley Isaacs Playground Reconstruction | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ISAAC | Stanley Isaacs Playground Reconstruction | 2 | DESIGN | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ISAAC | Stanley Isaacs Playground Reconstruction | 3 | BID/ REGISTER CONTRACT | Sep 2024 | Jun 2025 | Sep 2024 | Jun 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ISAAC | Stanley Isaacs Playground Reconstruction | 4 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ISAAC | Stanley Isaacs Playground Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Jun 2027 | Jun 2026 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LFLWER | Little Flower Plgd Public Restroom Bldg CNYG-522M | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LFLWER | Little Flower Plgd Public Restroom Bldg CNYG-522M | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LFLWER | Little Flower Plgd Public Restroom Bldg CNYG-522M | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LFLWER | Little Flower Plgd Public Restroom Bldg CNYG-522M | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LFLWER | Little Flower Plgd Public Restroom Bldg CNYG-522M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LGTURF | Little Flower Plg Synth. Turf Field Cons, Manhattan MG-316MA | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LGTURF | Little Flower Plg Synth. Turf Field Cons, Manhattan MG-316MA | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LGTURF | Little Flower Plg Synth. Turf Field Cons, Manhattan MG-316MA | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LGTURF | Little Flower Plg Synth. Turf Field Cons, Manhattan MG-316MA | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LGTURF | Little Flower Plg Synth. Turf Field Cons, Manhattan MG-316MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LMDCCH | LMDC - Corlear's Hook PRB M017-216M | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Jan 2016
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LMDCCH | LMDC - Corlear's Hook PRB M017-216M | 2 | DESIGN | Sep 2014 | Dec 2014 | Jan 2016 | Apr 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LMDCCH | LMDC - Corlear's Hook PRB M017-216M | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Apr 2017 | Jul 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LMDCCH | LMDC - Corlear's Hook PRB M017-216M | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Jul 2017 | Jul 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LMDCCH | LMDC - Corlear's Hook PRB M017-216M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Jul 2018 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MCRPAV | Marcus Garvey | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MCRPAV | Marcus Garvey | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MCRPAV | Marcus Garvey | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MCRPAV | Marcus Garvey | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MCRPAV | Marcus Garvey | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MORNHR | MORNINGSIDE PARK HANDRAILS | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MORNHR | MORNINGSIDE PARK HANDRAILS | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MORNHR | MORNINGSIDE PARK HANDRAILS | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MORNHR | MORNINGSIDE PARK HANDRAILS | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MORNHR | MORNINGSIDE PARK HANDRAILS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3P155CS | PS 155 Plgd- Public Restroom Bldg.-ADA Acessible CNYG-522M | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3P155CS | PS 155 Plgd- Public Restroom Bldg.-ADA Acessible CNYG-522M | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3P155CS | PS 155 Plgd- Public Restroom Bldg.-ADA Acessible CNYG-522M | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3P155CS | PS 155 Plgd- Public Restroom Bldg.-ADA Acessible CNYG-522M | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3P155CS | PS 155 Plgd- Public Restroom Bldg.-ADA Acessible CNYG-522M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3P40SPR | Hudson River Park Pier 40 Fire Sprinkler Recon | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3P40SPR | Hudson River Park Pier 40 Fire Sprinkler Recon | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3P40SPR | Hudson River Park Pier 40 Fire Sprinkler Recon | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3P40SPR | Hudson River Park Pier 40 Fire Sprinkler Recon | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3P40SPR | Hudson River Park Pier 40 Fire Sprinkler Recon | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PAVRSP | Riverside Park Pavement Path Reconstruction MG-519M | 4 | CONSTRUCTION | Sep 2022 | Sep 2024 | Sep 2022 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PAVRSP | Riverside Park Pavement Path Reconstruction MG-519M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PBGHD7 | Public Greenhouse for District 7, Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PBGHD7 | Public Greenhouse for District 7, Manhattan | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PBGHD7 | Public Greenhouse for District 7, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Mar 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PDHBRC | Hansborough Rec Ctr M131-115M | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jun 2012 | Sep 2012
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PDHBRC | Hansborough Rec Ctr M131-115M | 2 | DESIGN | Sep 2014 | Dec 2014 | Sep 2012 | Dec 2012
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PDHBRC | Hansborough Rec Ctr M131-115M | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2012 | Mar 2013
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PDHBRC | Hansborough Rec Ctr M131-115M | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2013 | Mar 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PDHBRC | Hansborough Rec Ctr M131-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2014 | Mar 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PDTDRC | Tony Dapolito Rec Ctr RC M103-115M | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Sep 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PDTDRC | Tony Dapolito Rec Ctr RC M103-115M | 2 | DESIGN | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PDTDRC | Tony Dapolito Rec Ctr RC M103-115M | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2014 | Mar 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PDTDRC | Tony Dapolito Rec Ctr RC M103-115M | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PDTDRC | Tony Dapolito Rec Ctr RC M103-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2016 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PEDB81 | JOHN FINLEY WALK (EAST RIVER ESPLANADE), MG-316MA | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PEDB81 | JOHN FINLEY WALK (EAST RIVER ESPLANADE), MG-316MA | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PEDB81 | JOHN FINLEY WALK (EAST RIVER ESPLANADE), MG-316MA | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PEDB81 | JOHN FINLEY WALK (EAST RIVER ESPLANADE), MG-316MA | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PEDB81 | JOHN FINLEY WALK (EAST RIVER ESPLANADE), MG-316MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PFRCRM | Pelham Fritz Rec Ctr fitness room, classroomr econ CNYG-420M | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PFRCRM | Pelham Fritz Rec Ctr fitness room, classroomr econ CNYG-420M | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PFRCRM | Pelham Fritz Rec Ctr fitness room, classroomr econ CNYG-420M | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PFRCRM | Pelham Fritz Rec Ctr fitness room, classroomr econ CNYG-420M | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PFRCRM | Pelham Fritz Rec Ctr fitness room, classroomr econ CNYG-420M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PHILSQ | A. PHILLIP RANDOLPH SQUARE RENOVATION Manhattan | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2024 | Dec 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PHILSQ | A. PHILLIP RANDOLPH SQUARE RENOVATION Manhattan | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2024 | Dec 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PHILSQ | A. PHILLIP RANDOLPH SQUARE RENOVATION Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2025 | Sep 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PHILSQ | A. PHILLIP RANDOLPH SQUARE RENOVATION Manhattan | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2026 | Sep 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PHILSQ | A. PHILLIP RANDOLPH SQUARE RENOVATION Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2027 | Sep 2033
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PIKEMA | PIKE/ALLEN MALLS | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PIKEMA | PIKE/ALLEN MALLS | 2 | DESIGN | Dec 2022 | Jun 2024 | Dec 2022 | Jun 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PIKEMA | PIKE/ALLEN MALLS | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PIKEMA | PIKE/ALLEN MALLS | 4 | CONSTRUCTION | Mar 2025 | Sep 2026 | Mar 2025 | Sep 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PIKEMA | PIKE/ALLEN MALLS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Sep 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PIN181 | PINEHURST AV/181ST - STAIRCASE/GARDEN UPGRADES | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PIN181 | PINEHURST AV/181ST - STAIRCASE/GARDEN UPGRADES | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PIN181 | PINEHURST AV/181ST - STAIRCASE/GARDEN UPGRADES | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PIN181 | PINEHURST AV/181ST - STAIRCASE/GARDEN UPGRADES | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PIN181 | PINEHURST AV/181ST - STAIRCASE/GARDEN UPGRADES | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL14A3 | Reconstruction of Playground 89 (MG-314M) | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL14A3 | Reconstruction of Playground 89 (MG-314M) | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL14A3 | Reconstruction of Playground 89 (MG-314M) | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL14A3 | Reconstruction of Playground 89 (MG-314M) | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL14A3 | Reconstruction of Playground 89 (MG-314M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL14A5 | Site work at Sherman Creek Park (MG-314M) | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL14A5 | Site work at Sherman Creek Park (MG-314M) | 2 | DESIGN | Dec 2016 | Jun 2018 | Dec 2016 | Jun 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL14A5 | Site work at Sherman Creek Park (MG-314M) | 3 | BID/ REGISTER CONTRACT | Jun 2018 | Mar 2019 | Jun 2018 | Mar 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL14A5 | Site work at Sherman Creek Park (MG-314M) | 4 | CONSTRUCTION | Mar 2019 | Sep 2020 | Mar 2019 | Sep 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL14A5 | Site work at Sherman Creek Park (MG-314M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL14A6 | Ruppert Park Reconstruction | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL14A6 | Ruppert Park Reconstruction | 2 | DESIGN | Dec 2016 | Jun 2018 | Dec 2020 | Jun 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL14A6 | Ruppert Park Reconstruction | 3 | BID/ REGISTER CONTRACT | Jun 2018 | Mar 2019 | Jun 2026 | Sep 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL14A6 | Ruppert Park Reconstruction | 4 | CONSTRUCTION | Mar 2019 | Sep 2020 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL14A6 | Ruppert Park Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL16A1 | Reconstruction of Dekovats, Manhattan | 1 | DEVELOP SCOPE | May 2018 | Nov 2018 | May 2018 | Nov 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL16A1 | Reconstruction of Dekovats, Manhattan | 2 | DESIGN | Nov 2018 | May 2020 | Nov 2018 | May 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL16A1 | Reconstruction of Dekovats, Manhattan | 3 | BID/ REGISTER CONTRACT | May 2020 | Feb 2021 | May 2020 | Feb 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL16A1 | Reconstruction of Dekovats, Manhattan | 4 | CONSTRUCTION | Feb 2021 | Aug 2022 | Feb 2021 | Aug 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL16A1 | Reconstruction of Dekovats, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2022 | Aug 2023 | Aug 2022 | Aug 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG13B | Reconstruction of plgr, Borough of Manhattan MG-213M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2013
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG13B | Reconstruction of plgr, Borough of Manhattan MG-213M | 2 | DESIGN | Sep 2013 | Dec 2013 | Mar 2013 | Jun 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG13B | Reconstruction of plgr, Borough of Manhattan MG-213M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Oct 2014 | Jun 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG13B | Reconstruction of plgr, Borough of Manhattan MG-213M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Jun 2015 | Dec 2016
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG13B | Reconstruction of plgr, Borough of Manhattan MG-213M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Dec 2016 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3POORRD | POOR RICHARD'S PLAYGROUND RENOVATIONS M230-118MA | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Apr 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3POORRD | POOR RICHARD'S PLAYGROUND RENOVATIONS M230-118MA | 2 | DESIGN | Dec 2017 | Dec 2018 | Apr 2018 | Apr 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3POORRD | POOR RICHARD'S PLAYGROUND RENOVATIONS M230-118MA | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Apr 2021 | Jan 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3POORRD | POOR RICHARD'S PLAYGROUND RENOVATIONS M230-118MA | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Mar 2022 | Mar 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3POORRD | POOR RICHARD'S PLAYGROUND RENOVATIONS M230-118MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Mar 2023 | Jun 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PS155M | PS155M Playground , Manhattan | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2011 | May 2012
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PS155M | PS155M Playground , Manhattan | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2019 | Jan 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PS155M | PS155M Playground , Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | May 2022 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PS155M | PS155M Playground , Manhattan | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PS155M | PS155M Playground , Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2023 | Jun 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PSNNTE | William F. Passannante Ballfield Reconstruction | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PSNNTE | William F. Passannante Ballfield Reconstruction | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PSNNTE | William F. Passannante Ballfield Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PSNNTE | William F. Passannante Ballfield Reconstruction | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PSNNTE | William F. Passannante Ballfield Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Jun 2031 | Sep 2025 | Jun 2031
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3QUISCS | Quisqueya Playground-Reconstruction of PRB | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3QUISCS | Quisqueya Playground-Reconstruction of PRB | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3QUISCS | Quisqueya Playground-Reconstruction of PRB | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3QUISCS | Quisqueya Playground-Reconstruction of PRB | 4 | CONSTRUCTION | Sep 2019 | Mar 2021 | Sep 2019 | Mar 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3QUISCS | Quisqueya Playground-Reconstruction of PRB | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Mar 2022 | Mar 2021 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3R5422A | Constance Baker Motley Recreation Center RC M130-122M | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3R5422A | Constance Baker Motley Recreation Center RC M130-122M | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3R5422A | Constance Baker Motley Recreation Center RC M130-122M | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3R5422A | Constance Baker Motley Recreation Center RC M130-122M | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3R5422A | Constance Baker Motley Recreation Center RC M130-122M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2032
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RANDSC | Randall's Island Sunken Garden Connector | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RANDSC | Randall's Island Sunken Garden Connector | 2 | DESIGN | Dec 2019 | Dec 2021 | Dec 2019 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RANDSC | Randall's Island Sunken Garden Connector | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RANDSC | Randall's Island Sunken Garden Connector | 4 | CONSTRUCTION | Sep 2022 | Sep 2024 | Sep 2022 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RANDSC | Randall's Island Sunken Garden Connector | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RANDVC | RANDALL'S ISLAND VISITOR CENTER | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RANDVC | RANDALL'S ISLAND VISITOR CENTER | 2 | DESIGN | Dec 2019 | Dec 2021 | Dec 2019 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RANDVC | RANDALL'S ISLAND VISITOR CENTER | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RANDVC | RANDALL'S ISLAND VISITOR CENTER | 4 | CONSTRUCTION | Sep 2022 | Sep 2024 | Sep 2022 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RANDVC | RANDALL'S ISLAND VISITOR CENTER | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3REC54E | Constance Baker Motley Rec Ctr fitness room recon CNYG-420M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3REC54E | Constance Baker Motley Rec Ctr fitness room recon CNYG-420M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3REC54E | Constance Baker Motley Rec Ctr fitness room recon CNYG-420M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3REC54E | Constance Baker Motley Rec Ctr fitness room recon CNYG-420M | 4 | CONSTRUCTION | Sep 2021 | Mar 2023 | Sep 2021 | Mar 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3REC54E | Constance Baker Motley Rec Ctr fitness room recon CNYG-420M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Mar 2024 | Mar 2023 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIV105 | Riverside Park, 105Street MG-519M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Feb 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIV105 | Riverside Park, 105Street MG-519M | 2 | DESIGN | Dec 2019 | Dec 2020 | Feb 2022 | Mar 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIV105 | Riverside Park, 105Street MG-519M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Jul 2023 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIV105 | Riverside Park, 105Street MG-519M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIV105 | Riverside Park, 105Street MG-519M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIV110 | Riverside Park, 110 Street | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIV110 | Riverside Park, 110 Street | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIV110 | Riverside Park, 110 Street | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIV110 | Riverside Park, 110 Street | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIV110 | Riverside Park, 110 Street | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVDIN | Riverside Park - Dinosaur Playground | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2024 | Dec 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVDIN | Riverside Park - Dinosaur Playground | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2024 | Dec 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVDIN | Riverside Park - Dinosaur Playground | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2025 | Sep 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVDIN | Riverside Park - Dinosaur Playground | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2026 | Sep 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVDIN | Riverside Park - Dinosaur Playground | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2027 | Sep 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVFTW | Shoreline Work in Riverside and Fort Washington Parks | 2 | DESIGN | Dec 2018 | Jun 2020 | Dec 2018 | Jun 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVFTW | Shoreline Work in Riverside and Fort Washington Parks | 3 | BID/ REGISTER CONTRACT | Jun 2020 | Mar 2021 | Jun 2020 | Mar 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVFTW | Shoreline Work in Riverside and Fort Washington Parks | 4 | CONSTRUCTION | Mar 2021 | Sep 2022 | Mar 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVFTW | Shoreline Work in Riverside and Fort Washington Parks | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVRMP | RIVERSIDE PARK: RIVERSIDE PARK 105TH STREET STEP RAMP RECON | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVRMP | RIVERSIDE PARK: RIVERSIDE PARK 105TH STREET STEP RAMP RECON | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVRMP | RIVERSIDE PARK: RIVERSIDE PARK 105TH STREET STEP RAMP RECON | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVRMP | RIVERSIDE PARK: RIVERSIDE PARK 105TH STREET STEP RAMP RECON | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVRMP | RIVERSIDE PARK: RIVERSIDE PARK 105TH STREET STEP RAMP RECON | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVSTR | RIVERSIDE PARK--102nd ST Staircase, Manhattan | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Oct 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVSTR | RIVERSIDE PARK--102nd ST Staircase, Manhattan | 2 | DESIGN | Dec 2017 | Dec 2018 | Oct 2018 | Jan 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVSTR | RIVERSIDE PARK--102nd ST Staircase, Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Aug 2020 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVSTR | RIVERSIDE PARK--102nd ST Staircase, Manhattan | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Feb 2021 | Feb 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVSTR | RIVERSIDE PARK--102nd ST Staircase, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Feb 2022 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RVPFWP | Riverside Park & Fort Washington Park Grnwy Recon M071-322M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RVPFWP | Riverside Park & Fort Washington Park Grnwy Recon M071-322M | 2 | DESIGN | Dec 2019 | Jun 2021 | Dec 2019 | Jun 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RVPFWP | Riverside Park & Fort Washington Park Grnwy Recon M071-322M | 3 | BID/ REGISTER CONTRACT | Jun 2021 | Mar 2022 | Jun 2021 | Mar 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RVPFWP | Riverside Park & Fort Washington Park Grnwy Recon M071-322M | 4 | CONSTRUCTION | Mar 2022 | Sep 2023 | Mar 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RVPFWP | Riverside Park & Fort Washington Park Grnwy Recon M071-322M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RVSSCA | Riverside Pk-Skate park at 109 St., M071-115MA | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | May 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RVSSCA | Riverside Pk-Skate park at 109 St., M071-115MA | 2 | DESIGN | Sep 2014 | Dec 2014 | May 2015 | Feb 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RVSSCA | Riverside Pk-Skate park at 109 St., M071-115MA | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Jul 2018 | Mar 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RVSSCA | Riverside Pk-Skate park at 109 St., M071-115MA | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | May 2019 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RVSSCA | Riverside Pk-Skate park at 109 St., M071-115MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Dec 2020 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SARDRO | SARA D ROOSEVELT PARK | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SARDRO | SARA D ROOSEVELT PARK | 2 | DESIGN | Dec 2022 | Jun 2024 | Dec 2022 | Jun 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SARDRO | SARA D ROOSEVELT PARK | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SARDRO | SARA D ROOSEVELT PARK | 4 | CONSTRUCTION | Mar 2025 | Sep 2026 | Mar 2025 | Sep 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SARDRO | SARA D ROOSEVELT PARK | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Sep 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SEWARD | SEWARD PARK- RESTORATION OF SCHIFF FOUNTAIN | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Jun 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SEWARD | SEWARD PARK- RESTORATION OF SCHIFF FOUNTAIN | 2 | DESIGN | Dec 2017 | Dec 2018 | Jun 2020 | Jun 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SEWARD | SEWARD PARK- RESTORATION OF SCHIFF FOUNTAIN | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | May 2022 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SEWARD | SEWARD PARK- RESTORATION OF SCHIFF FOUNTAIN | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SEWARD | SEWARD PARK- RESTORATION OF SCHIFF FOUNTAIN | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2023 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SHARCS | Sheltering Arms Playgound PRB M190-119M | 1 | DEVELOP SCOPE | Feb 2019 | Jul 2019 | Feb 2019 | Jul 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SHARCS | Sheltering Arms Playgound PRB M190-119M | 2 | DESIGN | Jul 2019 | Jul 2020 | Jul 2019 | Jul 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SHARCS | Sheltering Arms Playgound PRB M190-119M | 3 | BID/ REGISTER CONTRACT | Jul 2020 | Apr 2021 | Jul 2020 | Apr 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SHARCS | Sheltering Arms Playgound PRB M190-119M | 4 | CONSTRUCTION | Apr 2021 | Oct 2022 | Apr 2021 | Oct 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SHARCS | Sheltering Arms Playgound PRB M190-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2022 | Oct 2023 | Oct 2022 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SHRMRW | ROW NEW YORK: SHERMAN CREEK FLOATING DOCK AND GANGWAY | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SHRMRW | ROW NEW YORK: SHERMAN CREEK FLOATING DOCK AND GANGWAY | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SHRMRW | ROW NEW YORK: SHERMAN CREEK FLOATING DOCK AND GANGWAY | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SHRMRW | ROW NEW YORK: SHERMAN CREEK FLOATING DOCK AND GANGWAY | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SHRMRW | ROW NEW YORK: SHERMAN CREEK FLOATING DOCK AND GANGWAY | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SOHAGS | Green Street Fencing - Amsterdam Ave and 126th St. | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SOHAGS | Green Street Fencing - Amsterdam Ave and 126th St. | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SOHAGS | Green Street Fencing - Amsterdam Ave and 126th St. | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SOHAGS | Green Street Fencing - Amsterdam Ave and 126th St. | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SOHAGS | Green Street Fencing - Amsterdam Ave and 126th St. | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SOHO | SOHO Square Manhattan (MG25000-116M) | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Sep 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SOHO | SOHO Square Manhattan (MG25000-116M) | 2 | DESIGN | Sep 2014 | Dec 2014 | Sep 2014 | Feb 2016
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SOHO | SOHO Square Manhattan (MG25000-116M) | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | May 2016 | Feb 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SOHO | SOHO Square Manhattan (MG25000-116M) | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2017 | Sep 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SOHO | SOHO Square Manhattan (MG25000-116M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Sep 2018 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SPT21B | Street Tree Planting - Man.-Sm. Pur. CB MG-321M | 2 | DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SPT21B | Street Tree Planting - Man.-Sm. Pur. CB MG-321M | 3 | BID/ REGISTER CONTRACT | Jun 2021 | Mar 2022 | Jun 2021 | Mar 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SPT21B | Street Tree Planting - Man.-Sm. Pur. CB MG-321M | 4 | CONSTRUCTION | Mar 2022 | Sep 2023 | Mar 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SPT21B | Street Tree Planting - Man.-Sm. Pur. CB MG-321M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2025 | Sep 2023 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3STFCRL | Syn turf renovation at Corlears hook in Manhattan | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Apr 2019 | Oct 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3STFCRL | Syn turf renovation at Corlears hook in Manhattan | 2 | DESIGN | Dec 2022 | Dec 2023 | Oct 2019 | Oct 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3STFCRL | Syn turf renovation at Corlears hook in Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Oct 2020 | Jun 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3STFCRL | Syn turf renovation at Corlears hook in Manhattan | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Jul 2021 | Jun 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3STFCRL | Syn turf renovation at Corlears hook in Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Jul 2022 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3STSTSR | Stanton Street Storehouse Relocation | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3STSTSR | Stanton Street Storehouse Relocation | 2 | DESIGN | Dec 2022 | Dec 2024 | Dec 2022 | Dec 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3STSTSR | Stanton Street Storehouse Relocation | 3 | BID/ REGISTER CONTRACT | Dec 2024 | Sep 2025 | Dec 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3STSTSR | Stanton Street Storehouse Relocation | 4 | CONSTRUCTION | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3STSTSR | Stanton Street Storehouse Relocation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Sep 2028 | Sep 2027 | Sep 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SUTTON | ONE SUTTON PLACE PARK CONSTRUCTION (M108-111M) | 1 | DEVELOP SCOPE | Jul 2008 | Sep 2008 | Jul 2008 | Sep 2008
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SUTTON | ONE SUTTON PLACE PARK CONSTRUCTION (M108-111M) | 2 | DESIGN | Sep 2008 | Dec 2008 | Mar 2012 | Jun 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SUTTON | ONE SUTTON PLACE PARK CONSTRUCTION (M108-111M) | 3 | BID/ REGISTER CONTRACT | Dec 2008 | Mar 2009 | Feb 2016 | May 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SUTTON | ONE SUTTON PLACE PARK CONSTRUCTION (M108-111M) | 4 | CONSTRUCTION | Mar 2009 | Mar 2010 | Jun 2017 | Jul 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SUTTON | ONE SUTTON PLACE PARK CONSTRUCTION (M108-111M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2010 | Mar 2011 | Jul 2019 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SYCAMO | 24 Sycamores Playground: Handball Court Renovation | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SYCAMO | 24 Sycamores Playground: Handball Court Renovation | 2 | DESIGN | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SYCAMO | 24 Sycamores Playground: Handball Court Renovation | 3 | BID/ REGISTER CONTRACT | Sep 2024 | Jun 2025 | Sep 2024 | Jun 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SYCAMO | 24 Sycamores Playground: Handball Court Renovation | 4 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SYCAMO | 24 Sycamores Playground: Handball Court Renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Jun 2027 | Jun 2026 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TDCREC | Chelsea Rec Ctr fitness room recon CNYG-420M | 1 | DEVELOP SCOPE | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TDCREC | Chelsea Rec Ctr fitness room recon CNYG-420M | 2 | DESIGN | Jul 2022 | Jul 2023 | Jul 2022 | Jul 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TDCREC | Chelsea Rec Ctr fitness room recon CNYG-420M | 3 | BID/ REGISTER CONTRACT | Jul 2023 | Apr 2024 | Jul 2023 | Apr 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TDCREC | Chelsea Rec Ctr fitness room recon CNYG-420M | 4 | CONSTRUCTION | Apr 2024 | Apr 2025 | Apr 2024 | Apr 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TDCREC | Chelsea Rec Ctr fitness room recon CNYG-420M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2025 | Apr 2026 | Apr 2025 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TDREC2 | Reconstruction of Tony Dapolito Recreation Center-Phase 2 | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TDREC2 | Reconstruction of Tony Dapolito Recreation Center-Phase 2 | 2 | DESIGN | Dec 2021 | Dec 2023 | Dec 2021 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TDREC2 | Reconstruction of Tony Dapolito Recreation Center-Phase 2 | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TDREC2 | Reconstruction of Tony Dapolito Recreation Center-Phase 2 | 4 | CONSTRUCTION | Sep 2024 | Sep 2027 | Sep 2024 | Sep 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TDREC2 | Reconstruction of Tony Dapolito Recreation Center-Phase 2 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Sep 2029 | Sep 2027 | Sep 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TJRCUP | Thomas Jefferson Recreational Center-Upgrades | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TJRCUP | Thomas Jefferson Recreational Center-Upgrades | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TJRCUP | Thomas Jefferson Recreational Center-Upgrades | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TJRCUP | Thomas Jefferson Recreational Center-Upgrades | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TJRCUP | Thomas Jefferson Recreational Center-Upgrades | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TONYDL | Tony Dapolito Rec. Center Sidewalk Vault Recon. M103-121M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TONYDL | Tony Dapolito Rec. Center Sidewalk Vault Recon. M103-121M | 2 | DESIGN | Dec 2019 | Dec 2021 | Dec 2019 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TONYDL | Tony Dapolito Rec. Center Sidewalk Vault Recon. M103-121M | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TONYDL | Tony Dapolito Rec. Center Sidewalk Vault Recon. M103-121M | 4 | CONSTRUCTION | Sep 2022 | Sep 2024 | Sep 2022 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TONYDL | Tony Dapolito Rec. Center Sidewalk Vault Recon. M103-121M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE20A | FY 20 Street Tree Mnht CB 1,3,5,6,8,11 MG-319M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE20A | FY 20 Street Tree Mnht CB 1,3,5,6,8,11 MG-319M | 2 | DESIGN | Dec 2018 | Jun 2019 | Dec 2018 | Jun 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE20A | FY 20 Street Tree Mnht CB 1,3,5,6,8,11 MG-319M | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Mar 2020 | Jun 2019 | Mar 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE20A | FY 20 Street Tree Mnht CB 1,3,5,6,8,11 MG-319M | 4 | CONSTRUCTION | Mar 2020 | Sep 2021 | Mar 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE20A | FY 20 Street Tree Mnht CB 1,3,5,6,8,11 MG-319M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2023 | Sep 2021 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE24A | Manhattan Street Tree Planting FY24 - CBs 2,4,5,7,9, 10 & 12 | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE24A | Manhattan Street Tree Planting FY24 - CBs 2,4,5,7,9, 10 & 12 | 2 | DESIGN | Feb 2024 | Aug 2024 | Feb 2024 | Aug 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE24A | Manhattan Street Tree Planting FY24 - CBs 2,4,5,7,9, 10 & 12 | 3 | BID/ REGISTER CONTRACT | Aug 2024 | May 2025 | Aug 2024 | May 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE24A | Manhattan Street Tree Planting FY24 - CBs 2,4,5,7,9, 10 & 12 | 4 | CONSTRUCTION | May 2025 | Nov 2026 | May 2025 | Nov 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE24A | Manhattan Street Tree Planting FY24 - CBs 2,4,5,7,9, 10 & 12 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2028 | Nov 2026 | Nov 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE24B | Manhattan Street Tree Planting FY24 - CBs 1, 3, 6, 8 & 11 | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE24B | Manhattan Street Tree Planting FY24 - CBs 1, 3, 6, 8 & 11 | 2 | DESIGN | Feb 2024 | Aug 2024 | Feb 2024 | Aug 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE24B | Manhattan Street Tree Planting FY24 - CBs 1, 3, 6, 8 & 11 | 3 | BID/ REGISTER CONTRACT | Aug 2024 | May 2025 | Aug 2024 | May 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE24B | Manhattan Street Tree Planting FY24 - CBs 1, 3, 6, 8 & 11 | 4 | CONSTRUCTION | May 2025 | Nov 2026 | May 2025 | Nov 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE24B | Manhattan Street Tree Planting FY24 - CBs 1, 3, 6, 8 & 11 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2028 | Nov 2026 | Nov 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TREL21 | FY21 Street Trees MN CB's 1,2,4,5,,7-12 (3Y) MG-1319M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TREL21 | FY21 Street Trees MN CB's 1,2,4,5,,7-12 (3Y) MG-1319M | 2 | DESIGN | Dec 2019 | Jun 2021 | Dec 2019 | Jun 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TREL21 | FY21 Street Trees MN CB's 1,2,4,5,,7-12 (3Y) MG-1319M | 3 | BID/ REGISTER CONTRACT | Jun 2021 | Mar 2022 | Jun 2021 | Mar 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TREL21 | FY21 Street Trees MN CB's 1,2,4,5,,7-12 (3Y) MG-1319M | 4 | CONSTRUCTION | Mar 2022 | Mar 2025 | Mar 2022 | Mar 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TREL21 | FY21 Street Trees MN CB's 1,2,4,5,,7-12 (3Y) MG-1319M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Mar 2027 | Mar 2025 | Mar 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3W185BC | WEST 186TH ST BASKEBALL COURTS, Manhattan | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3W185BC | WEST 186TH ST BASKEBALL COURTS, Manhattan | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3W185BC | WEST 186TH ST BASKEBALL COURTS, Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3W185BC | WEST 186TH ST BASKEBALL COURTS, Manhattan | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3W185BC | WEST 186TH ST BASKEBALL COURTS, Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3W69SB2 | West 69th Street transverse bridge - phase 2 M353-212M | 1 | DEVELOP SCOPE | Jul 2006 | Sep 2006 | Jul 2006 | Aug 2007
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3W69SB2 | West 69th Street transverse bridge - phase 2 M353-212M | 2 | DESIGN | Sep 2006 | Dec 2006 | Aug 2007 | May 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3W69SB2 | West 69th Street transverse bridge - phase 2 M353-212M | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Dec 2019 | Aug 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3W69SB2 | West 69th Street transverse bridge - phase 2 M353-212M | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Sep 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3W69SB2 | West 69th Street transverse bridge - phase 2 M353-212M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Sep 2021 | Jun 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-5STFMHN | Synthetic Turf Field Reconstruction at Mahoney Park, SI | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Apr 2023 | Oct 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-5STFMHN | Synthetic Turf Field Reconstruction at Mahoney Park, SI | 2 | DESIGN | Dec 2019 | Dec 2020 | Oct 2023 | Oct 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-5STFMHN | Synthetic Turf Field Reconstruction at Mahoney Park, SI | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Oct 2024 | Jun 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-5STFMHN | Synthetic Turf Field Reconstruction at Mahoney Park, SI | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Jul 2025 | Jun 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-5STFMHN | Synthetic Turf Field Reconstruction at Mahoney Park, SI | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Jul 2026 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-6STFMAT | Purchase syn turf materials to recon fields in Manhattan | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Apr 2021 | Oct 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-6STFMAT | Purchase syn turf materials to recon fields in Manhattan | 2 | DESIGN | Dec 2019 | Dec 2020 | Oct 2021 | Oct 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-6STFMAT | Purchase syn turf materials to recon fields in Manhattan | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Oct 2022 | Jul 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-6STFMAT | Purchase syn turf materials to recon fields in Manhattan | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Jul 2023 | Jun 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-6STFMAT | Purchase syn turf materials to recon fields in Manhattan | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Jul 2024 | Jun 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SAND3TREE | FY21- ESCR Tree Planting, Manhattan MG-1219M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SAND3TREE | FY21- ESCR Tree Planting, Manhattan MG-1219M | 2 | DESIGN | Dec 2019 | Jun 2021 | Dec 2019 | Jun 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SAND3TREE | FY21- ESCR Tree Planting, Manhattan MG-1219M | 3 | BID/ REGISTER CONTRACT | Jun 2021 | Mar 2022 | Jun 2021 | Mar 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SAND3TREE | FY21- ESCR Tree Planting, Manhattan MG-1219M | 4 | CONSTRUCTION | Mar 2022 | Mar 2024 | Mar 2022 | Mar 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SAND3TREE | FY21- ESCR Tree Planting, Manhattan MG-1219M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Mar 2026 | Mar 2024 | Mar 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SAND4TREE | ESCR -Stormwater Greenstreets Construction- MG-421M | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SAND4TREE | ESCR -Stormwater Greenstreets Construction- MG-421M | 2 | DESIGN | Dec 2020 | Dec 2022 | Dec 2020 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SAND4TREE | ESCR -Stormwater Greenstreets Construction- MG-421M | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SAND4TREE | ESCR -Stormwater Greenstreets Construction- MG-421M | 4 | CONSTRUCTION | Sep 2023 | Sep 2026 | Sep 2023 | Sep 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SAND4TREE | ESCR -Stormwater Greenstreets Construction- MG-421M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2028 | Sep 2026 | Sep 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SAND5TREE | ESCR- Right of Way Bioswale Construction | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SAND5TREE | ESCR- Right of Way Bioswale Construction | 2 | DESIGN | Dec 2021 | Dec 2023 | Dec 2021 | Dec 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SAND5TREE | ESCR- Right of Way Bioswale Construction | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SAND5TREE | ESCR- Right of Way Bioswale Construction | 4 | CONSTRUCTION | Sep 2024 | Sep 2027 | Sep 2024 | Sep 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SAND5TREE | ESCR- Right of Way Bioswale Construction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Sep 2029 | Sep 2027 | Sep 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-02 | SANDY - Manhattan Plgd requirements (Type 1) MG-112M | 1 | DEVELOP SCOPE | Dec 2012 | Feb 2013 | Dec 2012 | Feb 2013
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-02 | SANDY - Manhattan Plgd requirements (Type 1) MG-112M | 2 | DESIGN | Mar 2013 | May 2013 | Mar 2013 | May 2013
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-02 | SANDY - Manhattan Plgd requirements (Type 1) MG-112M | 3 | BID/ REGISTER CONTRACT | May 2013 | Aug 2013 | May 2013 | Aug 2013
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-02 | SANDY - Manhattan Plgd requirements (Type 1) MG-112M | 4 | CONSTRUCTION | Aug 2013 | Aug 2014 | Aug 2013 | Aug 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-02 | SANDY - Manhattan Plgd requirements (Type 1) MG-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2014 | Aug 2015 | Aug 2014 | Jul 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-03 | SANDY - John Jay & Tony Dapolito - boilers (MG-113M) | 1 | DEVELOP SCOPE | Dec 2012 | Feb 2013 | Dec 2012 | Feb 2013
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-03 | SANDY - John Jay & Tony Dapolito - boilers (MG-113M) | 2 | DESIGN | Mar 2013 | May 2013 | Mar 2013 | May 2013
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-03 | SANDY - John Jay & Tony Dapolito - boilers (MG-113M) | 3 | BID/ REGISTER CONTRACT | May 2013 | Aug 2013 | May 2013 | Aug 2013
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-03 | SANDY - John Jay & Tony Dapolito - boilers (MG-113M) | 4 | CONSTRUCTION | Aug 2013 | Aug 2014 | Aug 2013 | Aug 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-03 | SANDY - John Jay & Tony Dapolito - boilers (MG-113M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2014 | Aug 2015 | Aug 2014 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-06 | SANDY - PNP Friends of the Highline | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-06 | SANDY - PNP Friends of the Highline | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2020 | Dec 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-06 | SANDY - PNP Friends of the Highline | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Oct 2023 | Mar 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-06 | SANDY - PNP Friends of the Highline | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2024 | Mar 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-06 | SANDY - PNP Friends of the Highline | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2025 | Mar 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-07 | SANDY - PNP Asphalt Green | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2020 | Dec 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-07 | SANDY - PNP Asphalt Green | 2 | DESIGN | Sep 2013 | Dec 2013 | Dec 2020 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-07 | SANDY - PNP Asphalt Green | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2021 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-07 | SANDY - PNP Asphalt Green | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-07 | SANDY - PNP Asphalt Green | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Sep 2023 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-08 | SANDY - PNP Battery Conservancy | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jun 2007 | Sep 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-08 | SANDY - PNP Battery Conservancy | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2019 | Dec 2032
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-08 | SANDY - PNP Battery Conservancy | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Jun 2021 | Mar 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-08 | SANDY - PNP Battery Conservancy | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2022 | Mar 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-08 | SANDY - PNP Battery Conservancy | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2023 | Mar 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-09 | SANDY - PNP Riverside Park Conservancy | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2013
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-09 | SANDY - PNP Riverside Park Conservancy | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2013 | Jan 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-09 | SANDY - PNP Riverside Park Conservancy | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | May 2022 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-09 | SANDY - PNP Riverside Park Conservancy | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Sep 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-09 | SANDY - PNP Riverside Park Conservancy | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Sep 2023 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-10 | SANDY - High Line M&O facility - Hazard mitigation | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-10 | SANDY - High Line M&O facility - Hazard mitigation | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-10 | SANDY - High Line M&O facility - Hazard mitigation | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-10 | SANDY - High Line M&O facility - Hazard mitigation | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-10 | SANDY - High Line M&O facility - Hazard mitigation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Jun 2030
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-11 | Vietnam Vet. Memorial Lighting (M046-114M) | 1 | DEVELOP SCOPE | Jan 2013 | Mar 2013 | Jan 2013 | Jun 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-11 | Vietnam Vet. Memorial Lighting (M046-114M) | 2 | DESIGN | Apr 2013 | Jun 2013 | Jun 2015 | Apr 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-11 | Vietnam Vet. Memorial Lighting (M046-114M) | 3 | BID/ REGISTER CONTRACT | Jun 2013 | Sep 2013 | May 2019 | Sep 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-11 | Vietnam Vet. Memorial Lighting (M046-114M) | 4 | CONSTRUCTION | Sep 2013 | Sep 2014 | Oct 2019 | Oct 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-11 | Vietnam Vet. Memorial Lighting (M046-114M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2014 | Sep 2015 | Oct 2020 | Jun 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-13 | SANDY-Riverside & F. Washington Pk Shoreline (Type 3 ) | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2017 | Dec 2017
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-13 | SANDY-Riverside & F. Washington Pk Shoreline (Type 3 ) | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2013 | Jun 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-13 | SANDY-Riverside & F. Washington Pk Shoreline (Type 3 ) | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Jan 2019 | Jun 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-13 | SANDY-Riverside & F. Washington Pk Shoreline (Type 3 ) | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Oct 2019 | Jan 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-13 | SANDY-Riverside & F. Washington Pk Shoreline (Type 3 ) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Jan 2020 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-14 | SANDY-Dock at 79 Street Boat Basin M071-310M | 2 | DESIGN | Apr 2014 | Jun 2014 | Apr 2014 | Jun 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-14 | SANDY-Dock at 79 Street Boat Basin M071-310M | 3 | BID/ REGISTER CONTRACT | Jun 2014 | Sep 2014 | Jun 2014 | Sep 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-14 | SANDY-Dock at 79 Street Boat Basin M071-310M | 4 | CONSTRUCTION | Sep 2014 | Sep 2015 | Sep 2014 | Sep 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-14 | SANDY-Dock at 79 Street Boat Basin M071-310M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2015 | Sep 2016 | Sep 2015 | Sep 2016
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-15 | SANDY - Tree removals - Manhattan MG-514M | 1 | DEVELOP SCOPE | Jan 2014 | Mar 2014 | Jan 2014 | Mar 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-15 | SANDY - Tree removals - Manhattan MG-514M | 2 | DESIGN | Apr 2014 | Jun 2014 | Apr 2014 | Jun 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-15 | SANDY - Tree removals - Manhattan MG-514M | 3 | BID/ REGISTER CONTRACT | Jun 2014 | Sep 2014 | Jun 2014 | Sep 2014
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-15 | SANDY - Tree removals - Manhattan MG-514M | 4 | CONSTRUCTION | Sep 2014 | Sep 2015 | Sep 2014 | Sep 2015
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-15 | SANDY - Tree removals - Manhattan MG-514M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2015 | Sep 2016 | Sep 2015 | Sep 2016
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-17 | SANDY- E.River Esplanade (Glick Park)-Elec (Type 3) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2015 | Sep 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-18 | SANDY - Mannahatta Fountains RC (Type 3) | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Jun 2016
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-18 | SANDY - Mannahatta Fountains RC (Type 3) | 2 | DESIGN | Sep 2014 | Dec 2014 | Jun 2016 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-18 | SANDY - Mannahatta Fountains RC (Type 3) | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Oct 2019 | Apr 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-18 | SANDY - Mannahatta Fountains RC (Type 3) | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Jun 2022 | Jun 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-18 | SANDY - Mannahatta Fountains RC (Type 3) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Jun 2022 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-19 | SANDY - John Jay & Tony Dapolito - Electrical (Balance) | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Jan 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-19 | SANDY - John Jay & Tony Dapolito - Electrical (Balance) | 2 | DESIGN | Dec 2017 | Dec 2018 | Jan 2022 | Apr 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-19 | SANDY - John Jay & Tony Dapolito - Electrical (Balance) | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Jul 2023 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-19 | SANDY - John Jay & Tony Dapolito - Electrical (Balance) | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-19 | SANDY - John Jay & Tony Dapolito - Electrical (Balance) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2024 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-20 | Playground 103 (CIII) | 1 | DEVELOP SCOPE | Aug 2016 | Jan 2017 | Aug 2016 | Jan 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-20 | Playground 103 (CIII) | 2 | DESIGN | Jan 2017 | Jan 2018 | Jan 2022 | Dec 2027
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-20 | Playground 103 (CIII) | 3 | BID/ REGISTER CONTRACT | Jan 2018 | Oct 2018 | Aug 2023 | Oct 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-20 | Playground 103 (CIII) | 4 | CONSTRUCTION | Oct 2018 | Oct 2019 | Nov 2023 | Nov 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-20 | Playground 103 (CIII) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2019 | Oct 2020 | Nov 2024 | Nov 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-21 | Four Parks Safety Surface | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Feb 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-21 | Four Parks Safety Surface | 2 | DESIGN | Dec 2018 | Dec 2019 | Feb 2022 | Apr 2026
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-21 | Four Parks Safety Surface | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Jul 2023 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-21 | Four Parks Safety Surface | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-21 | Four Parks Safety Surface | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2024 | Jun 2029
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-24 | SANDY-Inwood Nature Center Exhibit Displays | 1 | DEVELOP SCOPE | Jan 2018 | Jul 2018 | Jan 2018 | Jul 2018
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-24 | SANDY-Inwood Nature Center Exhibit Displays | 2 | DESIGN | Jul 2018 | Jul 2019 | Jul 2018 | Jul 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-24 | SANDY-Inwood Nature Center Exhibit Displays | 3 | BID/ REGISTER CONTRACT | Jul 2019 | Apr 2020 | Jul 2019 | Apr 2020
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-24 | SANDY-Inwood Nature Center Exhibit Displays | 4 | CONSTRUCTION | Apr 2020 | Sep 2021 | Apr 2020 | Sep 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-24 | SANDY-Inwood Nature Center Exhibit Displays | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2028
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-25 | Riverside Park Electrical Repairs | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-25 | Riverside Park Electrical Repairs | 2 | DESIGN | Dec 2019 | Jun 2021 | Dec 2019 | Jun 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-25 | Riverside Park Electrical Repairs | 3 | BID/ REGISTER CONTRACT | Jun 2021 | Mar 2022 | Jun 2021 | Mar 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-25 | Riverside Park Electrical Repairs | 4 | CONSTRUCTION | Mar 2022 | Sep 2023 | Mar 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-25 | Riverside Park Electrical Repairs | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2031
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-26 | Battery Park Spiral Fountain Conduit Reconstruction | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-26 | Battery Park Spiral Fountain Conduit Reconstruction | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-26 | Battery Park Spiral Fountain Conduit Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-26 | Battery Park Spiral Fountain Conduit Reconstruction | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-26 | Battery Park Spiral Fountain Conduit Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-27 | Vietnam Veterans Memorial Park Plaza Conduit Reconstruction | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-27 | Vietnam Veterans Memorial Park Plaza Conduit Reconstruction | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-27 | Vietnam Veterans Memorial Park Plaza Conduit Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-27 | Vietnam Veterans Memorial Park Plaza Conduit Reconstruction | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-27 | Vietnam Veterans Memorial Park Plaza Conduit Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | 70MULBREC | 70 MULBERRY STREET - RECONSTRUCTION | 1 | DEVELOP SCOPE | Jun 2021 | Aug 2021 | Jun 2021 | Aug 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | 70MULBREC | 70 MULBERRY STREET - RECONSTRUCTION | 2 | PRELIMINARY DESIGN | Aug 2021 | Dec 2021 | Aug 2021 | Dec 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | 70MULBREC | 70 MULBERRY STREET - RECONSTRUCTION | 3 | FINAL DESIGN | Dec 2021 | Jun 2022 | Dec 2021 | Jun 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | 70MULBREC | 70 MULBERRY STREET - RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | 70MULBREC | 70 MULBERRY STREET - RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | 70MULBREC | 70 MULBERRY STREET - RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | Jan 2023 | May 2023 | Jan 2023 | May 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | 70MULBREC | 70 MULBERRY STREET - RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | May 2023 | Sep 2023 | May 2023 | Sep 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | 70MULBREC | 70 MULBERRY STREET - RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Dec 2023 | Sep 2023 | Dec 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | 70MULBREC | 70 MULBERRY STREET - RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | Dec 2023 | Feb 2024 | Dec 2023 | Feb 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | 70MULBREC | 70 MULBERRY STREET - RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2024 | Mar 2024 | Feb 2024 | Mar 2032
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | AGNYCHANG | NYCHANGE PROJECT WITH DFTA | 1 | PROJECT START | Sep 2011 | Nov 2011 | Mar 2013 | Jan 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | AGNYCHANG | NYCHANGE PROJECT WITH DFTA | 2 | DESIGN START | Nov 2011 | Mar 2012 | Jan 2017 | Nov 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | AGNYCHANG | NYCHANGE PROJECT WITH DFTA | 3 | DESIGN COMPLETION | Mar 2012 | Sep 2012 | Nov 2018 | Nov 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | AGNYCHANG | NYCHANGE PROJECT WITH DFTA | 4 | CONSTRUCTION START | Sep 2012 | Dec 2012 | Nov 2020 | Sep 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | AGNYCHANG | NYCHANGE PROJECT WITH DFTA | 5 | CONSTRUCTION COMPLETION | Dec 2012 | Apr 2013 | Sep 2021 | Apr 2031
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | AGNYCHANG | NYCHANGE PROJECT WITH DFTA | 6 | CONSTRUCTION TO 50% | Apr 2013 | Aug 2013 | Sep 2021 | Apr 2031
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | AGNYCHANG | NYCHANGE PROJECT WITH DFTA | 7 | CONSTRUCTION TO 75% | Aug 2013 | Dec 2013 | Sep 2021 | Apr 2031
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | AGNYCHANG | NYCHANGE PROJECT WITH DFTA | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2013 | Mar 2014 | Sep 2021 | Apr 2031
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | AGNYCHANG | NYCHANGE PROJECT WITH DFTA | 9 | SUBSTANTIAL COMPLETION | Mar 2014 | May 2014 | Sep 2021 | Apr 2031
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | AGNYCHANG | NYCHANGE PROJECT WITH DFTA | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2014 | Jun 2014 | Sep 2021 | Apr 2031
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-M | Boro Based Jail New Manhattan Detention Facility DesignBuild | 1 | DEVELOP SCOPE | Sep 2018 | Nov 2018 | Sep 2018 | Nov 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-M | Boro Based Jail New Manhattan Detention Facility DesignBuild | 2 | PRELIMINARY DESIGN | Nov 2018 | Mar 2019 | Nov 2018 | Mar 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-M | Boro Based Jail New Manhattan Detention Facility DesignBuild | 3 | FINAL DESIGN | Mar 2019 | Sep 2019 | Mar 2019 | Sep 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-M | Boro Based Jail New Manhattan Detention Facility DesignBuild | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Dec 2019 | Sep 2019 | Dec 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-M | Boro Based Jail New Manhattan Detention Facility DesignBuild | 5 | CONSTRUCTION TO 25% | Dec 2019 | Apr 2020 | Dec 2019 | Apr 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-M | Boro Based Jail New Manhattan Detention Facility DesignBuild | 6 | CONSTRUCTION TO 50% | Apr 2020 | Aug 2020 | Apr 2020 | Aug 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-M | Boro Based Jail New Manhattan Detention Facility DesignBuild | 7 | CONSTRUCTION TO 75% | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-M | Boro Based Jail New Manhattan Detention Facility DesignBuild | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2020 | Mar 2021 | Dec 2020 | Mar 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-M | Boro Based Jail New Manhattan Detention Facility DesignBuild | 9 | SUBSTANTIAL COMPLETION | Mar 2021 | May 2021 | Mar 2021 | May 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-M | Boro Based Jail New Manhattan Detention Facility DesignBuild | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2021 | Jun 2029 | May 2021 | Jun 2029
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 1 | DEVELOP SCOPE | Jun 2012 | Aug 2012 | Jun 2012 | Aug 2012
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 2 | PRELIMINARY DESIGN | Aug 2012 | Dec 2012 | Aug 2012 | Dec 2012
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 3 | FINAL DESIGN | Dec 2012 | Jun 2013 | Dec 2012 | Jun 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2013 | Sep 2013 | Jun 2013 | Sep 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 5 | CONSTRUCTION TO 25% | Sep 2013 | Jan 2014 | Sep 2013 | Jan 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 6 | CONSTRUCTION TO 50% | Jan 2014 | May 2014 | Jan 2014 | May 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 7 | CONSTRUCTION TO 75% | May 2014 | Sep 2014 | May 2014 | Sep 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 9 | SUBSTANTIAL COMPLETION | Dec 2014 | Feb 2015 | Dec 2016 | May 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2015 | Mar 2015 | May 2018 | Jun 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 11 | PROJECT START | Feb 2015 | Mar 2015 | Jun 2022 | Jun 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 12 | DESIGN START | Feb 2015 | Mar 2015 | Jun 2022 | Jun 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 13 | DESIGN COMPLETION | Feb 2015 | Mar 2015 | Jun 2022 | Jun 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 14 | CONSTRUCTION START | Feb 2015 | Mar 2015 | Jun 2022 | Jun 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 15 | CONSTRUCTION COMPLETION | Feb 2015 | Mar 2015 | Jun 2022 | Jun 2031
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC253B | 100 GOLD- 21C3 | 1 | DEVELOP SCOPE | Jun 2012 | Aug 2012 | Apr 2014 | Apr 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC253B | 100 GOLD- 21C3 | 2 | PRELIMINARY DESIGN | Aug 2012 | Dec 2012 | Apr 2014 | Apr 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC253B | 100 GOLD- 21C3 | 3 | FINAL DESIGN | Dec 2012 | Jun 2013 | Apr 2015 | Mar 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC253B | 100 GOLD- 21C3 | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2013 | Sep 2013 | Jul 2014 | Aug 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC253B | 100 GOLD- 21C3 | 5 | CONSTRUCTION TO 25% | Sep 2013 | Jan 2014 | Aug 2016 | Jun 2028
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC253B | 100 GOLD- 21C3 | 6 | CONSTRUCTION TO 50% | Jan 2014 | May 2014 | Aug 2016 | Jun 2028
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC253B | 100 GOLD- 21C3 | 7 | CONSTRUCTION TO 75% | May 2014 | Sep 2014 | Aug 2016 | Jun 2028
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC253B | 100 GOLD- 21C3 | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2014 | Dec 2014 | Aug 2016 | Jun 2028
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC253B | 100 GOLD- 21C3 | 9 | SUBSTANTIAL COMPLETION | Dec 2014 | Feb 2015 | Aug 2016 | Jun 2028
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC253B | 100 GOLD- 21C3 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2015 | Mar 2015 | Aug 2016 | Jun 2028
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CMERECORD | OCME - Records Room Reconstruction at 421 East 26th St, Manh | 1 | DESIGN | Jul 2016 | Jan 2017 | Jul 2023 | Mar 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CMERECORD | OCME - Records Room Reconstruction at 421 East 26th St, Manh | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2017 | Jul 2017 | Mar 2024 | Jun 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CMERECORD | OCME - Records Room Reconstruction at 421 East 26th St, Manh | 3 | CONSTRUCTION | Jul 2017 | Apr 2018 | Jun 2024 | Oct 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CMERECORD | OCME - Records Room Reconstruction at 421 East 26th St, Manh | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2018 | Jun 2018 | Oct 2024 | Dec 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 1 | DEVELOP SCOPE | Oct 2014 | Oct 2014 | Oct 2014 | Oct 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 2 | PRELIMINARY DESIGN | Oct 2014 | Dec 2014 | Oct 2014 | Dec 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 3 | FINAL DESIGN | Dec 2014 | Feb 2015 | Dec 2014 | Jun 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2015 | Mar 2015 | Jun 2019 | Jul 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 5 | CONSTRUCTION TO 25% | Mar 2015 | May 2015 | Jul 2019 | Sep 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 6 | CONSTRUCTION TO 50% | May 2015 | Jun 2015 | Sep 2019 | Oct 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 7 | CONSTRUCTION TO 75% | Jun 2015 | Jul 2015 | Oct 2019 | Nov 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2015 | Jul 2015 | Nov 2019 | Nov 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 9 | SUBSTANTIAL COMPLETION | Jul 2015 | Jul 2015 | Nov 2019 | Nov 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2015 | Aug 2015 | Nov 2019 | Feb 2028
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 11 | PROJECT START | Jul 2015 | Aug 2015 | Feb 2028 | Feb 2028
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 12 | DESIGN START | Jul 2015 | Aug 2015 | Feb 2028 | Feb 2028
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 13 | DESIGN COMPLETION | Jul 2015 | Aug 2015 | Feb 2028 | Feb 2028
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 14 | CONSTRUCTION START | Jul 2015 | Aug 2015 | Feb 2028 | Feb 2028
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 15 | CONSTRUCTION COMPLETION | Jul 2015 | Aug 2015 | Feb 2028 | Feb 2028
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283WT | 100 CENTRE STREET - WATER TANK | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283WT | 100 CENTRE STREET - WATER TANK | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283WT | 100 CENTRE STREET - WATER TANK | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283WT | 100 CENTRE STREET - WATER TANK | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283WT | 100 CENTRE STREET - WATER TANK | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283WT | 100 CENTRE STREET - WATER TANK | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283WT | 100 CENTRE STREET - WATER TANK | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | May 2024 | Sep 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283WT | 100 CENTRE STREET - WATER TANK | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283WT | 100 CENTRE STREET - WATER TANK | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Dec 2024 | Feb 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283WT | 100 CENTRE STREET - WATER TANK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Mar 2025 | Feb 2025 | Mar 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO285FIRE | 60 LAFAYETTE ST - FIRE ALARM UPGRADE | 1 | PROJECT START | Jul 2022 | Jul 2022 | Jul 2022 | Jul 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO285FIRE | 60 LAFAYETTE ST - FIRE ALARM UPGRADE | 2 | DESIGN START | Jul 2022 | Jul 2023 | Jul 2022 | Jul 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO285FIRE | 60 LAFAYETTE ST - FIRE ALARM UPGRADE | 3 | DESIGN COMPLETION | Jul 2023 | Jul 2024 | Jul 2023 | Jul 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO285FIRE | 60 LAFAYETTE ST - FIRE ALARM UPGRADE | 4 | CONSTRUCTION START | Jul 2024 | Jul 2026 | Jul 2024 | Jul 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO285FIRE | 60 LAFAYETTE ST - FIRE ALARM UPGRADE | 5 | CONSTRUCTION COMPLETION | Jul 2026 | Jul 2027 | Jul 2026 | Jul 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO304REHB | 60 CENTRE ST. - RECONSTRUCTION | 1 | DEVELOP SCOPE | Mar 2018 | May 2018 | May 2017 | Jun 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO304REHB | 60 CENTRE ST. - RECONSTRUCTION | 2 | PRELIMINARY DESIGN | May 2018 | Sep 2018 | Jun 2018 | Jan 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO304REHB | 60 CENTRE ST. - RECONSTRUCTION | 3 | FINAL DESIGN | Sep 2018 | Mar 2019 | Jan 2020 | Jan 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO304REHB | 60 CENTRE ST. - RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2019 | Jun 2019 | Jan 2021 | Oct 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO304REHB | 60 CENTRE ST. - RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | Jun 2019 | Oct 2019 | Oct 2021 | Jun 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO304REHB | 60 CENTRE ST. - RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | Oct 2019 | Feb 2020 | Jun 2022 | Jan 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO304REHB | 60 CENTRE ST. - RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | Feb 2020 | Jun 2020 | Jan 2023 | Sep 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO304REHB | 60 CENTRE ST. - RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2020 | Sep 2020 | Sep 2023 | Dec 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO304REHB | 60 CENTRE ST. - RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | Sep 2020 | Nov 2020 | Dec 2023 | Jul 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO304REHB | 60 CENTRE ST. - RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2020 | Dec 2020 | Jul 2028 | Aug 2031
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO306EXT2 | 170 E121 St. Exterior Reconstruction | 1 | DEVELOP SCOPE | Feb 2016 | Apr 2016 | Jun 2022 | Aug 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO306EXT2 | 170 E121 St. Exterior Reconstruction | 2 | PRELIMINARY DESIGN | May 2016 | Aug 2016 | Aug 2022 | Dec 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO306EXT2 | 170 E121 St. Exterior Reconstruction | 3 | FINAL DESIGN | Aug 2016 | Feb 2017 | Dec 2022 | Jun 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO306EXT2 | 170 E121 St. Exterior Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2017 | May 2017 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO306EXT2 | 170 E121 St. Exterior Reconstruction | 5 | CONSTRUCTION TO 25% | May 2017 | Sep 2017 | Sep 2023 | Jan 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO306EXT2 | 170 E121 St. Exterior Reconstruction | 6 | CONSTRUCTION TO 50% | Sep 2017 | Jan 2018 | Jan 2024 | May 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO306EXT2 | 170 E121 St. Exterior Reconstruction | 7 | CONSTRUCTION TO 75% | Jan 2018 | May 2018 | May 2024 | Sep 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO306EXT2 | 170 E121 St. Exterior Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | May 2018 | Aug 2018 | Sep 2024 | Dec 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO306EXT2 | 170 E121 St. Exterior Reconstruction | 9 | SUBSTANTIAL COMPLETION | Aug 2018 | Oct 2018 | Dec 2024 | Feb 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO306EXT2 | 170 E121 St. Exterior Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2018 | Nov 2018 | Feb 2025 | Aug 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO80ROOF2 | 27 MADISON AVE - ROOF & MISC. OPERATIONS SPACES UPGRADE | 1 | PROJECT START | Sep 2014 | Sep 2014 | Jan 2013 | Jan 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO80ROOF2 | 27 MADISON AVE - ROOF & MISC. OPERATIONS SPACES UPGRADE | 2 | DESIGN START | Sep 2014 | Sep 2014 | Apr 2015 | Jul 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO80ROOF2 | 27 MADISON AVE - ROOF & MISC. OPERATIONS SPACES UPGRADE | 3 | DESIGN COMPLETION | Sep 2014 | Sep 2014 | Jul 2017 | Jul 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO80ROOF2 | 27 MADISON AVE - ROOF & MISC. OPERATIONS SPACES UPGRADE | 4 | CONSTRUCTION START | Sep 2014 | Sep 2014 | Aug 2016 | Dec 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO80ROOF2 | 27 MADISON AVE - ROOF & MISC. OPERATIONS SPACES UPGRADE | 5 | CONSTRUCTION COMPLETION | Sep 2014 | Sep 2014 | Apr 2016 | Apr 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | 1 | DEVELOP SCOPE | Mar 2019 | May 2019 | Mar 2024 | May 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | 2 | PRELIMINARY DESIGN | May 2019 | Sep 2019 | May 2024 | Sep 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | 3 | FINAL DESIGN | Sep 2019 | Mar 2020 | Sep 2024 | Mar 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Jun 2020 | Mar 2025 | Jun 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | 5 | CONSTRUCTION TO 25% | Jun 2020 | Oct 2020 | Jun 2026 | Oct 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | 6 | CONSTRUCTION TO 50% | Oct 2020 | Feb 2021 | Oct 2026 | Feb 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | 7 | CONSTRUCTION TO 75% | Feb 2021 | Jun 2021 | Feb 2027 | Jun 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2021 | Sep 2021 | Jun 2027 | Sep 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | 9 | SUBSTANTIAL COMPLETION | Sep 2021 | Nov 2021 | Sep 2027 | Nov 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2021 | Dec 2021 | Nov 2027 | Dec 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | 11 | PROJECT START | Nov 2021 | Dec 2021 | Mar 2024 | Feb 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | 12 | DESIGN START | Nov 2021 | Dec 2021 | Feb 2025 | Feb 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | 13 | DESIGN COMPLETION | Nov 2021 | Dec 2021 | Feb 2026 | Feb 2028
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | 14 | CONSTRUCTION START | Nov 2021 | Dec 2021 | Feb 2028 | Feb 2029
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | 15 | CONSTRUCTION COMPLETION | Nov 2021 | Dec 2021 | Feb 2029 | Jun 2035
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81SKY2 | 31 CHAMBERST ST.- RENOVATE SKYLIGHT | 1 | PROJECT START | Jun 2013 | Jun 2013 | Jul 2013 | Jul 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81SKY2 | 31 CHAMBERST ST.- RENOVATE SKYLIGHT | 2 | DESIGN START | Jun 2013 | Jun 2013 | Jul 2013 | Jul 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81SKY2 | 31 CHAMBERST ST.- RENOVATE SKYLIGHT | 3 | DESIGN COMPLETION | Jun 2013 | Jun 2013 | Sep 2014 | Dec 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81SKY2 | 31 CHAMBERST ST.- RENOVATE SKYLIGHT | 4 | CONSTRUCTION START | Jun 2013 | Jun 2013 | Oct 2015 | Oct 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81SKY2 | 31 CHAMBERST ST.- RENOVATE SKYLIGHT | 5 | CONSTRUCTION COMPLETION | Dec 2014 | Jun 2016 | Jun 2018 | Jun 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | 1 | PROJECT START | Mar 2018 | Mar 2018 | Mar 2018 | Mar 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | 2 | DESIGN START | Mar 2018 | Mar 2018 | Mar 2018 | Mar 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | 3 | DESIGN COMPLETION | Mar 2018 | Mar 2018 | Mar 2018 | Mar 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | 4 | CONSTRUCTION START | Mar 2018 | Mar 2018 | Mar 2018 | Mar 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | 5 | CONSTRUCTION COMPLETION | Mar 2018 | Mar 2018 | Mar 2018 | Mar 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | 6 | DEVELOP SCOPE | Mar 2018 | Mar 2018 | Mar 2018 | Jun 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | 7 | PRELIMINARY DESIGN | Mar 2018 | Mar 2018 | Jun 2018 | Oct 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | 8 | FINAL DESIGN | Mar 2018 | Mar 2018 | Oct 2018 | Mar 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | 9 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Mar 2018 | Mar 2019 | Jun 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | 10 | CONSTRUCTION TO 25% | Mar 2018 | Mar 2018 | Jun 2019 | Oct 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | 11 | CONSTRUCTION TO 50% | Mar 2018 | Mar 2018 | Oct 2019 | Feb 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | 12 | CONSTRUCTION TO 75% | Mar 2018 | Mar 2018 | Feb 2020 | Jun 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | 13 | ORIGINAL EQUIP & FURNISHING | Mar 2018 | Mar 2018 | Jun 2020 | Sep 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | 14 | SUBSTANTIAL COMPLETION | Mar 2018 | Mar 2018 | Sep 2020 | May 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | 15 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2018 | Mar 2018 | May 2022 | May 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | 1 | PROJECT START | Mar 2018 | Mar 2018 | Mar 2018 | Mar 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | 2 | DESIGN START | Mar 2018 | Mar 2018 | Mar 2018 | Mar 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | 3 | DESIGN COMPLETION | Mar 2018 | Mar 2018 | Mar 2018 | Mar 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | 4 | CONSTRUCTION START | Mar 2018 | Mar 2018 | Mar 2018 | Mar 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | 5 | CONSTRUCTION COMPLETION | Mar 2018 | Mar 2018 | Mar 2018 | Mar 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | 6 | DEVELOP SCOPE | Mar 2018 | Mar 2018 | Mar 2018 | Jun 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | 7 | PRELIMINARY DESIGN | Mar 2018 | Mar 2018 | Jun 2018 | Oct 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | 8 | FINAL DESIGN | Mar 2018 | Mar 2018 | Oct 2018 | Mar 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | 9 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Mar 2018 | Mar 2019 | Jun 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | 10 | CONSTRUCTION TO 25% | Mar 2018 | Mar 2018 | Jun 2019 | Oct 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | 11 | CONSTRUCTION TO 50% | Mar 2018 | Mar 2018 | Oct 2019 | Feb 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | 12 | CONSTRUCTION TO 75% | Mar 2018 | Mar 2018 | Feb 2020 | Jun 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | 13 | ORIGINAL EQUIP & FURNISHING | Mar 2018 | Mar 2018 | Jun 2020 | Sep 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | 14 | SUBSTANTIAL COMPLETION | Mar 2018 | Mar 2018 | Sep 2020 | Sep 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | 15 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2018 | Mar 2018 | Sep 2021 | Sep 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0001 | DCAS - LOUIS J LEFKOWITZ - ENERGY EFFICIENCY UPGRADE | 1 | DEVELOP SCOPE | Mar 2019 | May 2019 | Mar 2019 | May 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0001 | DCAS - LOUIS J LEFKOWITZ - ENERGY EFFICIENCY UPGRADE | 2 | PRELIMINARY DESIGN | May 2019 | Sep 2019 | May 2019 | Sep 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0001 | DCAS - LOUIS J LEFKOWITZ - ENERGY EFFICIENCY UPGRADE | 3 | FINAL DESIGN | Sep 2019 | Mar 2020 | Sep 2019 | Mar 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0001 | DCAS - LOUIS J LEFKOWITZ - ENERGY EFFICIENCY UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Jun 2020 | Mar 2020 | Jun 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0001 | DCAS - LOUIS J LEFKOWITZ - ENERGY EFFICIENCY UPGRADE | 5 | CONSTRUCTION TO 25% | Jun 2020 | Oct 2020 | Jun 2020 | Oct 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0001 | DCAS - LOUIS J LEFKOWITZ - ENERGY EFFICIENCY UPGRADE | 6 | CONSTRUCTION TO 50% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0001 | DCAS - LOUIS J LEFKOWITZ - ENERGY EFFICIENCY UPGRADE | 7 | CONSTRUCTION TO 75% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0001 | DCAS - LOUIS J LEFKOWITZ - ENERGY EFFICIENCY UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0001 | DCAS - LOUIS J LEFKOWITZ - ENERGY EFFICIENCY UPGRADE | 9 | SUBSTANTIAL COMPLETION | Sep 2021 | Nov 2021 | Sep 2021 | Nov 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0001 | DCAS - LOUIS J LEFKOWITZ - ENERGY EFFICIENCY UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2021 | Dec 2021 | Nov 2021 | Dec 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0002 | DCAS-Manhattan Municipal Building | 1 | DEVELOP SCOPE | Mar 2019 | May 2019 | Mar 2019 | May 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0002 | DCAS-Manhattan Municipal Building | 2 | PRELIMINARY DESIGN | May 2019 | Sep 2019 | May 2019 | Sep 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0002 | DCAS-Manhattan Municipal Building | 3 | FINAL DESIGN | Sep 2019 | Mar 2020 | Sep 2019 | Mar 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0002 | DCAS-Manhattan Municipal Building | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Jun 2020 | Mar 2020 | Jun 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0002 | DCAS-Manhattan Municipal Building | 5 | CONSTRUCTION TO 25% | Jun 2020 | Oct 2020 | Jun 2020 | Oct 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0002 | DCAS-Manhattan Municipal Building | 6 | CONSTRUCTION TO 50% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0002 | DCAS-Manhattan Municipal Building | 7 | CONSTRUCTION TO 75% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0002 | DCAS-Manhattan Municipal Building | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0002 | DCAS-Manhattan Municipal Building | 9 | SUBSTANTIAL COMPLETION | Sep 2021 | Nov 2021 | Sep 2021 | Nov 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0002 | DCAS-Manhattan Municipal Building | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2021 | Dec 2021 | Nov 2021 | Dec 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0002 | DCAS-Manhattan Municipal Building | 11 | PROJECT START | Nov 2021 | Dec 2021 | Dec 2021 | Dec 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0002 | DCAS-Manhattan Municipal Building | 12 | DESIGN START | Nov 2021 | Dec 2021 | Dec 2021 | Dec 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0002 | DCAS-Manhattan Municipal Building | 13 | DESIGN COMPLETION | Nov 2021 | Dec 2021 | Dec 2021 | Dec 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0002 | DCAS-Manhattan Municipal Building | 14 | CONSTRUCTION START | Nov 2021 | Dec 2021 | Dec 2021 | Dec 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0002 | DCAS-Manhattan Municipal Building | 15 | CONSTRUCTION COMPLETION | Nov 2021 | Dec 2021 | Dec 2021 | Dec 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HBFDR14BP | East 14th St (near ConEd Plant) Bike Path | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2024 | Jun 2018 | Jun 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HBFDR14BP | East 14th St (near ConEd Plant) Bike Path | 2 | DESIGN START | Jun 2024 | Jun 2028 | Jul 2018 | Jul 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HBFDR14BP | East 14th St (near ConEd Plant) Bike Path | 3 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jul 2018 | Jun 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HBFDR14BP | East 14th St (near ConEd Plant) Bike Path | 4 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jul 2024 | Jul 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HBFDR14BP | East 14th St (near ConEd Plant) Bike Path | 5 | CONSTRUCTION COMPLETION | Jun 2028 | Jun 2030 | Jul 2024 | Jul 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HBMA24662 | W 128TH ST PED BRIDGE BIN:2246620 | 1 | DEVELOP SCOPE | Jun 2018 | Jun 2019 | Jun 2000 | Mar 2003
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HBMA24662 | W 128TH ST PED BRIDGE BIN:2246620 | 2 | DESIGN START | Jun 2019 | Jun 2023 | Oct 2000 | Jul 2003
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HBMA24662 | W 128TH ST PED BRIDGE BIN:2246620 | 3 | CONSTRUCTION START | Jun 2023 | Jun 2025 | Nov 2004 | Aug 2007
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HBMA24662 | W 128TH ST PED BRIDGE BIN:2246620 | 4 | CONSTRUCTION START | Jun 2023 | Jun 2025 | Aug 2007 | May 2010
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HBMA24662 | W 128TH ST PED BRIDGE BIN:2246620 | 5 | CONSTRUCTION COMPLETION | Jun 2023 | Jun 2025 | May 2010 | Jul 2029
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BEES | BELLEVUE - ELECT SVC UPGRADE | 1 | PROJECT START | Jan 2016 | Jan 2016 | Jan 2016 | Jan 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BEES | BELLEVUE - ELECT SVC UPGRADE | 2 | DESIGN START | Jan 2016 | Jul 2016 | Jan 2016 | Jul 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BEES | BELLEVUE - ELECT SVC UPGRADE | 3 | DESIGN COMPLETION | Jul 2016 | Jul 2018 | Jul 2016 | Jul 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BEES | BELLEVUE - ELECT SVC UPGRADE | 4 | CONSTRUCTION START | Jul 2018 | Jan 2020 | Jul 2018 | Jan 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BEES | BELLEVUE - ELECT SVC UPGRADE | 5 | CONSTRUCTION COMPLETION | Jan 2012 | Jan 2016 | Jan 2020 | Jun 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BELS | Bellevue Emergency Stabilization Work | 1 | PROJECT START | Jul 2023 | Jul 2023 | Jul 2023 | Jul 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BELS | Bellevue Emergency Stabilization Work | 2 | DESIGN START | Jul 2023 | Jan 2024 | Jul 2023 | Jan 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BELS | Bellevue Emergency Stabilization Work | 3 | DESIGN COMPLETION | Jul 2023 | Apr 2024 | Jul 2023 | Apr 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BELS | Bellevue Emergency Stabilization Work | 4 | CONSTRUCTION START | Apr 2024 | Jan 2027 | Apr 2024 | Jan 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BELS | Bellevue Emergency Stabilization Work | 5 | CONSTRUCTION COMPLETION | Jan 2027 | Mar 2031 | Jan 2027 | Mar 2031
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLBR | BELLEVUE BATHROOMS RECONSTRUCTION | 1 | PROJECT START | Sep 2016 | Sep 2016 | Sep 2016 | Sep 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLBR | BELLEVUE BATHROOMS RECONSTRUCTION | 2 | DESIGN START | Sep 2016 | Jan 2018 | Sep 2016 | Jan 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLBR | BELLEVUE BATHROOMS RECONSTRUCTION | 3 | DESIGN COMPLETION | Jan 2018 | Jan 2019 | Jan 2018 | Jan 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLBR | BELLEVUE BATHROOMS RECONSTRUCTION | 4 | CONSTRUCTION START | Jan 2019 | Oct 2019 | Jan 2019 | Oct 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLBR | BELLEVUE BATHROOMS RECONSTRUCTION | 5 | CONSTRUCTION COMPLETION | Oct 2019 | Jul 2023 | Oct 2019 | Jul 2030
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLEN | Bellevue Auditorium Structural Reconstruction | 1 | PROJECT START | Sep 2016 | Sep 2016 | Sep 2016 | Sep 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLEN | Bellevue Auditorium Structural Reconstruction | 2 | DESIGN START | Sep 2016 | Aug 2018 | Sep 2016 | Aug 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLEN | Bellevue Auditorium Structural Reconstruction | 3 | DESIGN COMPLETION | Aug 2018 | Aug 2019 | Aug 2018 | Aug 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLEN | Bellevue Auditorium Structural Reconstruction | 4 | CONSTRUCTION START | Aug 2019 | Apr 2020 | Aug 2019 | Apr 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLEN | Bellevue Auditorium Structural Reconstruction | 5 | CONSTRUCTION COMPLETION | Apr 2020 | Dec 2021 | Apr 2023 | Dec 2029
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLFS | BELLEVUE MEN'S RESIDENCE- FIRE SAFETY | 1 | PROJECT START | Aug 2016 | Aug 2016 | Aug 2016 | Aug 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLFS | BELLEVUE MEN'S RESIDENCE- FIRE SAFETY | 2 | DESIGN START | Sep 2016 | May 2018 | Sep 2016 | May 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLFS | BELLEVUE MEN'S RESIDENCE- FIRE SAFETY | 3 | DESIGN COMPLETION | May 2018 | May 2019 | May 2018 | May 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLFS | BELLEVUE MEN'S RESIDENCE- FIRE SAFETY | 4 | CONSTRUCTION START | May 2019 | Jan 2020 | May 2019 | Jan 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLFS | BELLEVUE MEN'S RESIDENCE- FIRE SAFETY | 5 | CONSTRUCTION COMPLETION | Feb 2020 | Nov 2021 | Feb 2020 | Nov 2031
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLFX | BELLEVUE - FACADE RESTORATION & WINDOW REPLACEMENT | 1 | PROJECT START | Jan 2016 | Jan 2016 | Jan 2016 | Jan 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLFX | BELLEVUE - FACADE RESTORATION & WINDOW REPLACEMENT | 2 | DESIGN START | Jul 2016 | Oct 2017 | Jul 2016 | Oct 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLFX | BELLEVUE - FACADE RESTORATION & WINDOW REPLACEMENT | 3 | DESIGN COMPLETION | Oct 2017 | Oct 2017 | Oct 2017 | Oct 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLFX | BELLEVUE - FACADE RESTORATION & WINDOW REPLACEMENT | 4 | CONSTRUCTION START | Jul 2022 | Apr 2027 | Jul 2022 | Apr 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLFX | BELLEVUE - FACADE RESTORATION & WINDOW REPLACEMENT | 5 | CONSTRUCTION COMPLETION | Apr 2027 | Sep 2029 | Apr 2027 | Sep 2029
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLRR | BELLEVUE ROOF | 1 | PROJECT START | Jan 2016 | Jan 2016 | Jan 2016 | Jan 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLRR | BELLEVUE ROOF | 2 | DESIGN START | Jan 2016 | Jul 2016 | Jan 2016 | Jul 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLRR | BELLEVUE ROOF | 3 | DESIGN COMPLETION | Jul 2016 | Dec 2017 | Jul 2016 | Dec 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLRR | BELLEVUE ROOF | 4 | CONSTRUCTION START | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLRR | BELLEVUE ROOF | 5 | CONSTRUCTION COMPLETION | Sep 2018 | Aug 2021 | Sep 2018 | Jun 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CGIU | Keener Assessment Shelter - Fire Alarm Upgrade | 1 | PROJECT START | Sep 2016 | Sep 2016 | Sep 2016 | Sep 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CGIU | Keener Assessment Shelter - Fire Alarm Upgrade | 2 | DESIGN START | Nov 2017 | Jan 2018 | Nov 2017 | Jan 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CGIU | Keener Assessment Shelter - Fire Alarm Upgrade | 3 | DESIGN COMPLETION | Nov 2018 | Apr 2019 | Nov 2018 | Apr 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CGIU | Keener Assessment Shelter - Fire Alarm Upgrade | 4 | CONSTRUCTION START | Jul 2019 | Jul 2024 | Jul 2019 | Jul 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CGIU | Keener Assessment Shelter - Fire Alarm Upgrade | 5 | CONSTRUCTION COMPLETION | Jul 2024 | Jan 2026 | Jul 2024 | Jan 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CGKF | CHARLES GAY KEENER FIRE SAFETY | 2 | DESIGN START | Jul 1997 | Feb 2000 | Jul 1997 | Feb 2000
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CGKF | CHARLES GAY KEENER FIRE SAFETY | 3 | DESIGN COMPLETION | Feb 2000 | Nov 2005 | Feb 2000 | Nov 2005
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CGKF | CHARLES GAY KEENER FIRE SAFETY | 4 | CONSTRUCTION START | Nov 2005 | Nov 2005 | Nov 2005 | Nov 2005
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CGKF | CHARLES GAY KEENER FIRE SAFETY | 5 | CONSTRUCTION COMPLETION | Nov 2005 | Mar 2007 | Nov 2005 | Jun 2011
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CTFS | CLARKE THOMAS FIRE SAFETY | 1 | PROJECT START | Jul 2016 | Jul 2016 | Jul 2016 | Jul 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CTFS | CLARKE THOMAS FIRE SAFETY | 2 | DESIGN START | Jul 2016 | Jan 2018 | Jul 2016 | Jan 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CTFS | CLARKE THOMAS FIRE SAFETY | 3 | DESIGN COMPLETION | Jan 2018 | Nov 2018 | Jan 2018 | Nov 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CTFS | CLARKE THOMAS FIRE SAFETY | 4 | CONSTRUCTION START | Nov 2018 | Jul 2019 | Nov 2018 | Jul 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CTFS | CLARKE THOMAS FIRE SAFETY | 5 | CONSTRUCTION COMPLETION | Jul 2019 | Jul 2020 | Jul 2021 | Jun 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FTRF | FT. WASHINGTON ARMORY ROOF REPLACEMENT | 1 | PROJECT START | Jan 2018 | Jan 2018 | Jan 2018 | Jan 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FTRF | FT. WASHINGTON ARMORY ROOF REPLACEMENT | 2 | DESIGN START | Jan 2018 | Jul 2018 | Jan 2018 | Jul 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FTRF | FT. WASHINGTON ARMORY ROOF REPLACEMENT | 3 | DESIGN COMPLETION | Jul 2018 | Jan 2019 | Jul 2018 | Jan 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FTRF | FT. WASHINGTON ARMORY ROOF REPLACEMENT | 4 | CONSTRUCTION START | Feb 2019 | Jul 2019 | Feb 2019 | Jul 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FTRF | FT. WASHINGTON ARMORY ROOF REPLACEMENT | 5 | CONSTRUCTION COMPLETION | Jul 2019 | Dec 2020 | Jul 2019 | Jun 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FWFA | FT. WASHINGTON - FIRE ALARM | 1 | PROJECT START | Mar 2016 | Mar 2016 | Mar 2016 | Mar 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FWFA | FT. WASHINGTON - FIRE ALARM | 2 | DESIGN START | Apr 2016 | Jul 2016 | Apr 2016 | Jul 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FWFA | FT. WASHINGTON - FIRE ALARM | 3 | DESIGN COMPLETION | Jul 2016 | Jun 2017 | Jul 2016 | Jun 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FWFA | FT. WASHINGTON - FIRE ALARM | 4 | CONSTRUCTION START | Jul 2017 | Oct 2017 | Jul 2017 | Oct 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FWFA | FT. WASHINGTON - FIRE ALARM | 5 | CONSTRUCTION COMPLETION | Nov 2017 | Jun 2023 | Nov 2017 | Jun 2031
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HSFA | HELP SEC - FIRE SAFETY | 1 | PROJECT START | Jul 2016 | Jul 2016 | Jul 2016 | Jul 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HSFA | HELP SEC - FIRE SAFETY | 2 | DESIGN START | Jul 2016 | Jan 2018 | Jul 2016 | Jan 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HSFA | HELP SEC - FIRE SAFETY | 3 | DESIGN COMPLETION | Jan 2018 | Nov 2018 | Jan 2018 | Nov 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HSFA | HELP SEC - FIRE SAFETY | 4 | CONSTRUCTION START | Nov 2018 | Jul 2019 | Nov 2018 | Jul 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HSFA | HELP SEC - FIRE SAFETY | 5 | CONSTRUCTION COMPLETION | Jul 2019 | Jul 2020 | Jul 2019 | Jun 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112KEFA | Kenton Hall Fire Safety | 1 | PROJECT START | Jul 2016 | Jul 2016 | Jul 2016 | Jul 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112KEFA | Kenton Hall Fire Safety | 2 | DESIGN START | Jul 2016 | Dec 2017 | Jul 2016 | Dec 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112KEFA | Kenton Hall Fire Safety | 3 | DESIGN COMPLETION | Dec 2017 | Nov 2018 | Dec 2017 | Nov 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112KEFA | Kenton Hall Fire Safety | 4 | CONSTRUCTION START | Nov 2018 | Jul 2019 | Nov 2018 | Jul 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112KEFA | Kenton Hall Fire Safety | 5 | CONSTRUCTION COMPLETION | Jul 2019 | Jan 2021 | Jul 2019 | Jun 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112KELC | 282 EAST 3RD STREET - ELECTRICAL UPGRADE | 1 | PROJECT START | Jan 2018 | Jan 2018 | Jan 2018 | Jan 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112KELC | 282 EAST 3RD STREET - ELECTRICAL UPGRADE | 2 | DESIGN START | Jan 2018 | Jul 2018 | Jan 2018 | Jul 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112KELC | 282 EAST 3RD STREET - ELECTRICAL UPGRADE | 3 | DESIGN COMPLETION | Jul 2018 | Jan 2019 | Jul 2018 | Jan 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112KELC | 282 EAST 3RD STREET - ELECTRICAL UPGRADE | 4 | CONSTRUCTION START | Jan 2019 | Jul 2019 | Jan 2019 | Jul 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112KELC | 282 EAST 3RD STREET - ELECTRICAL UPGRADE | 5 | CONSTRUCTION COMPLETION | Jul 2019 | Dec 2020 | Jul 2019 | Jun 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112SWFA | SCHWARTZ WARDS ISLAND FIRE SAFETY | 1 | PROJECT START | Jul 2016 | Jul 2016 | Jul 2016 | Jul 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112SWFA | SCHWARTZ WARDS ISLAND FIRE SAFETY | 2 | DESIGN START | Jul 2016 | Jan 2018 | Jul 2016 | Jan 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112SWFA | SCHWARTZ WARDS ISLAND FIRE SAFETY | 3 | DESIGN COMPLETION | Jan 2018 | Nov 2018 | Jan 2018 | Nov 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112SWFA | SCHWARTZ WARDS ISLAND FIRE SAFETY | 4 | CONSTRUCTION START | Nov 2018 | Jul 2019 | Nov 2018 | Jul 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112SWFA | SCHWARTZ WARDS ISLAND FIRE SAFETY | 5 | CONSTRUCTION COMPLETION | Jul 2019 | Jul 2020 | Jul 2019 | Jul 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112THFA | 8 EAST THIRD ST SHELTER FIRE SAFETY | 1 | PROJECT START | Jul 2016 | Jul 2016 | Jul 2016 | Jul 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112THFA | 8 EAST THIRD ST SHELTER FIRE SAFETY | 2 | DESIGN START | Jul 2016 | May 2017 | Jul 2016 | May 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112THFA | 8 EAST THIRD ST SHELTER FIRE SAFETY | 3 | DESIGN COMPLETION | May 2017 | Nov 2018 | May 2017 | Nov 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112THFA | 8 EAST THIRD ST SHELTER FIRE SAFETY | 4 | CONSTRUCTION START | Nov 2018 | Mar 2019 | Nov 2018 | Mar 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112THFA | 8 EAST THIRD ST SHELTER FIRE SAFETY | 5 | CONSTRUCTION COMPLETION | Mar 2019 | Sep 2020 | Mar 2019 | Sep 2031
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112THKR | 8 EAST THIRD KITCHEN DDC | 1 | PROJECT START | May 2021 | May 2021 | May 2021 | May 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112THKR | 8 EAST THIRD KITCHEN DDC | 2 | DESIGN START | May 2021 | May 2021 | May 2021 | May 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112THKR | 8 EAST THIRD KITCHEN DDC | 3 | DESIGN COMPLETION | May 2021 | May 2021 | May 2021 | May 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112THKR | 8 EAST THIRD KITCHEN DDC | 4 | CONSTRUCTION START | May 2021 | Jan 2022 | May 2021 | Jan 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112THKR | 8 EAST THIRD KITCHEN DDC | 5 | CONSTRUCTION COMPLETION | Jan 2022 | Jul 2023 | Jan 2022 | Jul 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112VETS | VETERANS SRO ADULT FACILITY- EXTERIOR UPGRADE | 5 | CONSTRUCTION COMPLETION | Sep 2005 | Aug 2006 | Sep 2005 | Aug 2006
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCEK | Jennie Clarke Elec and Kitchen | 1 | PROJECT START | Jan 2018 | Jul 2018 | Jan 2018 | Jul 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCEK | Jennie Clarke Elec and Kitchen | 2 | DESIGN START | Jul 2018 | Jan 2019 | Jul 2018 | Jan 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCEK | Jennie Clarke Elec and Kitchen | 3 | DESIGN COMPLETION | Jan 2019 | Jul 2019 | Jan 2019 | Jul 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCEK | Jennie Clarke Elec and Kitchen | 4 | CONSTRUCTION START | Jul 2019 | Jan 2020 | Jul 2020 | Jan 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCEK | Jennie Clarke Elec and Kitchen | 5 | CONSTRUCTION COMPLETION | Jan 2020 | Jul 2020 | Jan 2022 | Jun 2031
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCFB | JENNIE CLARK RESIDENCE - FIRE ALARM UPGRADE | 1 | PROJECT START | Mar 2016 | Mar 2016 | Mar 2016 | Mar 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCFB | JENNIE CLARK RESIDENCE - FIRE ALARM UPGRADE | 2 | DESIGN START | Apr 2016 | Jul 2016 | Apr 2016 | Jul 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCFB | JENNIE CLARK RESIDENCE - FIRE ALARM UPGRADE | 3 | DESIGN COMPLETION | Jul 2016 | Jun 2017 | Jul 2016 | Jun 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCFB | JENNIE CLARK RESIDENCE - FIRE ALARM UPGRADE | 4 | CONSTRUCTION START | Jul 2017 | Oct 2017 | Jul 2017 | Jun 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCFB | JENNIE CLARK RESIDENCE - FIRE ALARM UPGRADE | 5 | CONSTRUCTION COMPLETION | Nov 2017 | Jun 2023 | Jun 2018 | Aug 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115REGX | REGENT FAMILY RESIDENCE EXTERIOR UPGRADE | 1 | PROJECT START | Aug 2007 | Aug 2007 | Aug 2007 | Aug 2007
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115REGX | REGENT FAMILY RESIDENCE EXTERIOR UPGRADE | 2 | DESIGN START | Aug 2007 | Apr 2008 | Aug 2007 | Apr 2008
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115REGX | REGENT FAMILY RESIDENCE EXTERIOR UPGRADE | 3 | DESIGN COMPLETION | Apr 2008 | Apr 2009 | Apr 2008 | Apr 2009
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115REGX | REGENT FAMILY RESIDENCE EXTERIOR UPGRADE | 4 | CONSTRUCTION START | Apr 2009 | Sep 2009 | Apr 2009 | Sep 2009
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115REGX | REGENT FAMILY RESIDENCE EXTERIOR UPGRADE | 5 | CONSTRUCTION COMPLETION | Sep 2009 | Jun 2011 | Sep 2009 | Jun 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CHNWH | COMMUNITY HEALTHCARE NETWORK-WASHINGTON HEIGHTS | 1 | PROJECT START | Apr 2008 | Apr 2008 | Jul 2011 | Dec 2012
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CHNWH | COMMUNITY HEALTHCARE NETWORK-WASHINGTON HEIGHTS | 2 | DESIGN START | Apr 2008 | Apr 2008 | Dec 2012 | Dec 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CHNWH | COMMUNITY HEALTHCARE NETWORK-WASHINGTON HEIGHTS | 3 | DESIGN COMPLETION | Apr 2008 | Apr 2008 | Jan 2014 | Dec 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CHNWH | COMMUNITY HEALTHCARE NETWORK-WASHINGTON HEIGHTS | 4 | CONSTRUCTION START | Apr 2008 | Apr 2008 | Dec 2015 | Dec 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CHNWH | COMMUNITY HEALTHCARE NETWORK-WASHINGTON HEIGHTS | 5 | CONSTRUCTION COMPLETION | Apr 2008 | Apr 2008 | Dec 2017 | Jun 2031
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82MANAT | Manhattan Animal Care Center Upgrade | 1 | DESIGN | Jan 2018 | May 2019 | Jan 2018 | Apr 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82MANAT | Manhattan Animal Care Center Upgrade | 2 | CONSTRUCTION | May 2019 | May 2024 | Apr 2018 | Aug 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82MANAT | Manhattan Animal Care Center Upgrade | 3 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | May 2024 | Aug 2018 | Feb 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82MANAT | Manhattan Animal Care Center Upgrade | 4 | DEVELOP SCOPE | May 2024 | May 2024 | Feb 2019 | May 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82MANAT | Manhattan Animal Care Center Upgrade | 5 | PRELIMINARY DESIGN | May 2024 | May 2024 | May 2019 | Sep 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82MANAT | Manhattan Animal Care Center Upgrade | 6 | FINAL DESIGN | May 2024 | May 2024 | Sep 2019 | Jan 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82MANAT | Manhattan Animal Care Center Upgrade | 7 | BID AWARD AND REGISTER CONTRCT | May 2024 | May 2024 | Jan 2020 | May 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82MANAT | Manhattan Animal Care Center Upgrade | 8 | CONSTRUCTION TO 25% | May 2024 | May 2024 | May 2020 | Aug 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82MANAT | Manhattan Animal Care Center Upgrade | 9 | CONSTRUCTION TO 50% | May 2024 | May 2024 | Aug 2020 | Oct 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82MANAT | Manhattan Animal Care Center Upgrade | 10 | CONSTRUCTION TO 75% | May 2024 | May 2024 | Oct 2020 | Jun 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82MANAT | Manhattan Animal Care Center Upgrade | 11 | ORIGINAL EQUIP & FURNISHING | May 2024 | May 2024 | Oct 2020 | Jun 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82MANAT | Manhattan Animal Care Center Upgrade | 12 | SUBSTANTIAL COMPLETION | May 2024 | May 2024 | Oct 2020 | Jun 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82MANAT | Manhattan Animal Care Center Upgrade | 13 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Jun 2024 | Oct 2020 | Jun 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82WASHT | WASHINGTON HEIGHTS HEALTH CENTER FACADE RENOVATION | 1 | DESIGN | Jun 2018 | Dec 2018 | Jun 2023 | Dec 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82WASHT | WASHINGTON HEIGHTS HEALTH CENTER FACADE RENOVATION | 2 | CONSTRUCTION | Dec 2018 | May 2019 | Dec 2026 | Jun 2033
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWBARUCH | Baruch College - 25th Street Plaza (MED-634) | 1 | DEVELOP SCOPE | Mar 2015 | May 2015 | Jul 2013 | Mar 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWBARUCH | Baruch College - 25th Street Plaza (MED-634) | 2 | PRELIMINARY DESIGN | May 2015 | Sep 2015 | Mar 2014 | Nov 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWBARUCH | Baruch College - 25th Street Plaza (MED-634) | 3 | FINAL DESIGN | Sep 2015 | Mar 2016 | Nov 2015 | Sep 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWBARUCH | Baruch College - 25th Street Plaza (MED-634) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2016 | Jun 2016 | Sep 2016 | Jun 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWBARUCH | Baruch College - 25th Street Plaza (MED-634) | 5 | CONSTRUCTION TO 25% | Jun 2016 | Oct 2016 | Jun 2018 | Oct 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWBARUCH | Baruch College - 25th Street Plaza (MED-634) | 6 | CONSTRUCTION TO 50% | Oct 2016 | Feb 2017 | Oct 2018 | Feb 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWBARUCH | Baruch College - 25th Street Plaza (MED-634) | 7 | CONSTRUCTION TO 75% | Feb 2017 | Jun 2017 | Feb 2019 | Jun 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWBARUCH | Baruch College - 25th Street Plaza (MED-634) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2017 | Sep 2017 | Jun 2019 | Sep 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWBARUCH | Baruch College - 25th Street Plaza (MED-634) | 9 | SUBSTANTIAL COMPLETION | Sep 2017 | Nov 2017 | Sep 2019 | Nov 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWBARUCH | Baruch College - 25th Street Plaza (MED-634) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | Dec 2017 | Nov 2019 | Jun 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWBARUCH | Baruch College - 25th Street Plaza (MED-634) | 11 | PROJECT START | Nov 2017 | Dec 2017 | Jun 2023 | Jun 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWBARUCH | Baruch College - 25th Street Plaza (MED-634) | 12 | DESIGN START | Nov 2017 | Dec 2017 | Jun 2023 | Jun 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWBARUCH | Baruch College - 25th Street Plaza (MED-634) | 13 | DESIGN COMPLETION | Nov 2017 | Dec 2017 | Jun 2023 | Jun 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWBARUCH | Baruch College - 25th Street Plaza (MED-634) | 14 | CONSTRUCTION START | Nov 2017 | Dec 2017 | Jun 2023 | Jun 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWBARUCH | Baruch College - 25th Street Plaza (MED-634) | 15 | CONSTRUCTION COMPLETION | Nov 2017 | Dec 2017 | Jun 2023 | Jun 2032
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM100SNC | 79TH STREET SBS, MED673 | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jun 2019 | Sep 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM100SNC | 79TH STREET SBS, MED673 | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Sep 2019 | Jan 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM100SNC | 79TH STREET SBS, MED673 | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2020 | Jul 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM100SNC | 79TH STREET SBS, MED673 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2020 | Oct 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM100SNC | 79TH STREET SBS, MED673 | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2020 | Feb 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM100SNC | 79TH STREET SBS, MED673 | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2021 | Jun 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM100SNC | 79TH STREET SBS, MED673 | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2021 | Oct 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM100SNC | 79TH STREET SBS, MED673 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2021 | Jan 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM100SNC | 79TH STREET SBS, MED673 | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2022 | Mar 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM100SNC | 79TH STREET SBS, MED673 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2022 | Sep 2028
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM12AVE | 12th Avenue Accessibility Improvements | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jan 2019 | Oct 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM12AVE | 12th Avenue Accessibility Improvements | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Oct 2019 | Feb 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM12AVE | 12th Avenue Accessibility Improvements | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Feb 2020 | Aug 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM12AVE | 12th Avenue Accessibility Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Aug 2020 | Nov 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM12AVE | 12th Avenue Accessibility Improvements | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Nov 2020 | Mar 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM12AVE | 12th Avenue Accessibility Improvements | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Mar 2021 | Jun 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM12AVE | 12th Avenue Accessibility Improvements | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2021 | Oct 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM12AVE | 12th Avenue Accessibility Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Sep 2023 | Mar 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM12AVE | 12th Avenue Accessibility Improvements | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Mar 2025 | May 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM12AVE | 12th Avenue Accessibility Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | May 2025 | Jun 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM1688 | Harlem Multi-Site | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM1688 | Harlem Multi-Site | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2023 | Jan 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM1688 | Harlem Multi-Site | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2024 | Jul 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM1688 | Harlem Multi-Site | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2024 | Oct 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM1688 | Harlem Multi-Site | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2024 | Feb 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM1688 | Harlem Multi-Site | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2025 | Jun 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM1688 | Harlem Multi-Site | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2025 | Oct 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM1688 | Harlem Multi-Site | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2025 | Jan 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM1688 | Harlem Multi-Site | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2026 | Mar 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM1688 | Harlem Multi-Site | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2026 | Feb 2028
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM2025 | Delancey Street Safety Improvements (MED-667) | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM2025 | Delancey Street Safety Improvements (MED-667) | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM2025 | Delancey Street Safety Improvements (MED-667) | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM2025 | Delancey Street Safety Improvements (MED-667) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM2025 | Delancey Street Safety Improvements (MED-667) | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM2025 | Delancey Street Safety Improvements (MED-667) | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM2025 | Delancey Street Safety Improvements (MED-667) | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM2025 | Delancey Street Safety Improvements (MED-667) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM2025 | Delancey Street Safety Improvements (MED-667) | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM2025 | Delancey Street Safety Improvements (MED-667) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Jun 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM42PSM | 42nd Street Pedestrian Security Measures, MED679 | 1 | PROJECT START | Nov 2021 | Nov 2021 | Nov 2021 | Nov 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM42PSM | 42nd Street Pedestrian Security Measures, MED679 | 2 | DESIGN START | Nov 2021 | Jul 2022 | Nov 2021 | Jul 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM42PSM | 42nd Street Pedestrian Security Measures, MED679 | 3 | DESIGN COMPLETION | Jul 2022 | Dec 2024 | Jul 2022 | Dec 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM42PSM | 42nd Street Pedestrian Security Measures, MED679 | 4 | CONSTRUCTION START | Dec 2024 | Aug 2025 | Dec 2024 | Aug 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM42PSM | 42nd Street Pedestrian Security Measures, MED679 | 5 | CONSTRUCTION COMPLETION | Aug 2025 | May 2029 | Aug 2025 | May 2029
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMM008 | EAST 86TH ST STREETSCAPE-225 EAST 79TH ,MADISON TO YORK AVE | 1 | DEVELOP SCOPE | Jun 2009 | Sep 2009 | Jun 2009 | Aug 2009
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMM008 | EAST 86TH ST STREETSCAPE-225 EAST 79TH ,MADISON TO YORK AVE | 2 | DESIGN START | Sep 2009 | Mar 2011 | Aug 2009 | Dec 2009
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMM008 | EAST 86TH ST STREETSCAPE-225 EAST 79TH ,MADISON TO YORK AVE | 3 | CONSTRUCTION START | Mar 2011 | Mar 2013 | Dec 2009 | Mar 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMM008 | EAST 86TH ST STREETSCAPE-225 EAST 79TH ,MADISON TO YORK AVE | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2011 | Mar 2013 | Mar 2016 | Jun 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMM008 | EAST 86TH ST STREETSCAPE-225 EAST 79TH ,MADISON TO YORK AVE | 5 | CONSTRUCTION TO 25% | Mar 2011 | Mar 2013 | Jun 2016 | Feb 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMM008 | EAST 86TH ST STREETSCAPE-225 EAST 79TH ,MADISON TO YORK AVE | 6 | CONSTRUCTION TO 50% | Mar 2011 | Mar 2013 | Feb 2017 | Oct 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMM008 | EAST 86TH ST STREETSCAPE-225 EAST 79TH ,MADISON TO YORK AVE | 7 | CONSTRUCTION TO 75% | Mar 2011 | Mar 2013 | Oct 2017 | Jun 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMM008 | EAST 86TH ST STREETSCAPE-225 EAST 79TH ,MADISON TO YORK AVE | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2011 | Mar 2013 | Jun 2018 | Sep 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMM008 | EAST 86TH ST STREETSCAPE-225 EAST 79TH ,MADISON TO YORK AVE | 9 | SUBSTANTIAL COMPLETION | Mar 2011 | Mar 2013 | Sep 2018 | Nov 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMM008 | EAST 86TH ST STREETSCAPE-225 EAST 79TH ,MADISON TO YORK AVE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2011 | Mar 2013 | Nov 2018 | Jun 2028
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMME43ST | 43rd Street Shared Street, MED-670 | 1 | DEVELOP SCOPE | Mar 2020 | May 2020 | Mar 2020 | May 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMME43ST | 43rd Street Shared Street, MED-670 | 2 | PRELIMINARY DESIGN | May 2020 | Sep 2020 | May 2020 | Sep 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMME43ST | 43rd Street Shared Street, MED-670 | 3 | FINAL DESIGN | Sep 2020 | Mar 2021 | Sep 2020 | Mar 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMME43ST | 43rd Street Shared Street, MED-670 | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2021 | Jun 2021 | Mar 2021 | Jun 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMME43ST | 43rd Street Shared Street, MED-670 | 5 | CONSTRUCTION TO 25% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMME43ST | 43rd Street Shared Street, MED-670 | 6 | CONSTRUCTION TO 50% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMME43ST | 43rd Street Shared Street, MED-670 | 7 | CONSTRUCTION TO 75% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMME43ST | 43rd Street Shared Street, MED-670 | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMME43ST | 43rd Street Shared Street, MED-670 | 9 | SUBSTANTIAL COMPLETION | Sep 2022 | Nov 2022 | Sep 2022 | Nov 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMME43ST | 43rd Street Shared Street, MED-670 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2022 | Dec 2022 | Nov 2022 | Jun 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMMLEXAV | Lexington Av Pedestrian Safety Improvement MED678 DSGN BUILD | 1 | DESIGN | Jun 2021 | Oct 2023 | Jun 2021 | Oct 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMMLEXAV | Lexington Av Pedestrian Safety Improvement MED678 DSGN BUILD | 2 | CONSTRUCTION | Jun 2024 | Jun 2026 | Jun 2024 | Jun 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMMLEXAV | Lexington Av Pedestrian Safety Improvement MED678 DSGN BUILD | 3 | ORIGINAL EQUIP & FURNISHING | Jun 2026 | Jun 2026 | Jun 2026 | Jun 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMMLEXAV | Lexington Av Pedestrian Safety Improvement MED678 DSGN BUILD | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Jun 2026 | Mar 2026 | Jun 2030
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMNYPL | New York Public Library Pedestrian Improvements | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMNYPL | New York Public Library Pedestrian Improvements | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMNYPL | New York Public Library Pedestrian Improvements | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMNYPL | New York Public Library Pedestrian Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMNYPL | New York Public Library Pedestrian Improvements | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMNYPL | New York Public Library Pedestrian Improvements | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMNYPL | New York Public Library Pedestrian Improvements | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMNYPL | New York Public Library Pedestrian Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMNYPL | New York Public Library Pedestrian Improvements | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMNYPL | New York Public Library Pedestrian Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Feb 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2012 | TIMES SQUARE (SEN002160) | 1 | DEVELOP SCOPE | May 2005 | Aug 2005 | May 2005 | Aug 2005
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2012 | TIMES SQUARE (SEN002160) | 2 | PRELIMINARY DESIGN | Aug 2005 | Dec 2005 | Aug 2005 | Dec 2005
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2012 | TIMES SQUARE (SEN002160) | 3 | FINAL DESIGN | Dec 2005 | Jun 2006 | Dec 2005 | Jun 2006
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2012 | TIMES SQUARE (SEN002160) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2007 | Jun 2007 | Mar 2007 | Jun 2012
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2012 | TIMES SQUARE (SEN002160) | 5 | CONSTRUCTION TO 25% | Jun 2007 | Jun 2007 | Jun 2012 | Jun 2012
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2012 | TIMES SQUARE (SEN002160) | 6 | CONSTRUCTION TO 50% | Jun 2007 | Jun 2007 | Jun 2012 | Jun 2012
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2012 | TIMES SQUARE (SEN002160) | 7 | CONSTRUCTION TO 75% | Jun 2007 | Jun 2007 | Jun 2012 | Jun 2012
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2012 | TIMES SQUARE (SEN002160) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2007 | Jun 2007 | Jun 2012 | Jun 2012
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2012 | TIMES SQUARE (SEN002160) | 9 | SUBSTANTIAL COMPLETION | Jun 2007 | Jun 2007 | Jun 2012 | Jun 2012
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2012 | TIMES SQUARE (SEN002160) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2007 | Jul 2007 | Jun 2012 | Jun 2033
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2019 | RECONSTRUCTION OF EAST HOUSTON STREET (MED-604) | 1 | DEVELOP SCOPE | Mar 2008 | May 2008 | Jul 2007 | Sep 2007
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2019 | RECONSTRUCTION OF EAST HOUSTON STREET (MED-604) | 2 | PRELIMINARY DESIGN | May 2008 | Sep 2008 | Sep 2007 | Jan 2008
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2019 | RECONSTRUCTION OF EAST HOUSTON STREET (MED-604) | 3 | FINAL DESIGN | Sep 2008 | Mar 2009 | Jan 2008 | Jul 2008
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2019 | RECONSTRUCTION OF EAST HOUSTON STREET (MED-604) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2009 | Jun 2009 | Jul 2008 | Oct 2008
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2019 | RECONSTRUCTION OF EAST HOUSTON STREET (MED-604) | 5 | CONSTRUCTION TO 25% | Jun 2009 | Oct 2009 | Oct 2008 | Feb 2009
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2019 | RECONSTRUCTION OF EAST HOUSTON STREET (MED-604) | 6 | CONSTRUCTION TO 50% | Oct 2009 | Feb 2010 | Feb 2009 | Jun 2009
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2019 | RECONSTRUCTION OF EAST HOUSTON STREET (MED-604) | 7 | CONSTRUCTION TO 75% | Feb 2010 | Jun 2010 | Jun 2009 | Oct 2009
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2019 | RECONSTRUCTION OF EAST HOUSTON STREET (MED-604) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2010 | Sep 2010 | Oct 2009 | Jan 2010
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2019 | RECONSTRUCTION OF EAST HOUSTON STREET (MED-604) | 9 | SUBSTANTIAL COMPLETION | Sep 2010 | Nov 2010 | Jan 2010 | Sep 2010
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2019 | RECONSTRUCTION OF EAST HOUSTON STREET (MED-604) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2010 | Dec 2010 | Sep 2010 | Jun 2032
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7E | RECONSTRUCTION OF WORTH ST - HUDSON ST TO EAST BROADWAY | 1 | DEVELOP SCOPE | Mar 2009 | Jun 2009 | Mar 2009 | Jun 2009
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7E | RECONSTRUCTION OF WORTH ST - HUDSON ST TO EAST BROADWAY | 2 | PRELIMINARY DESIGN | Jun 2009 | Sep 2009 | Jun 2009 | Sep 2009
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7E | RECONSTRUCTION OF WORTH ST - HUDSON ST TO EAST BROADWAY | 3 | FINAL DESIGN | Oct 2009 | Mar 2010 | Oct 2009 | Mar 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7E | RECONSTRUCTION OF WORTH ST - HUDSON ST TO EAST BROADWAY | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2010 | Jun 2010 | Mar 2013 | Jun 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7E | RECONSTRUCTION OF WORTH ST - HUDSON ST TO EAST BROADWAY | 5 | CONSTRUCTION TO 25% | Jun 2010 | Oct 2010 | Jun 2016 | Jun 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7E | RECONSTRUCTION OF WORTH ST - HUDSON ST TO EAST BROADWAY | 6 | CONSTRUCTION TO 50% | Oct 2010 | Feb 2011 | Jun 2016 | Jun 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7E | RECONSTRUCTION OF WORTH ST - HUDSON ST TO EAST BROADWAY | 7 | CONSTRUCTION TO 75% | Feb 2011 | Jun 2011 | Jun 2016 | Jun 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7E | RECONSTRUCTION OF WORTH ST - HUDSON ST TO EAST BROADWAY | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2011 | Sep 2011 | Jun 2016 | Jun 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7E | RECONSTRUCTION OF WORTH ST - HUDSON ST TO EAST BROADWAY | 9 | SUBSTANTIAL COMPLETION | Sep 2011 | Nov 2011 | Jun 2016 | Jun 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7E | RECONSTRUCTION OF WORTH ST - HUDSON ST TO EAST BROADWAY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2011 | Dec 2011 | Jul 2017 | Jun 2032
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7F | RECONSTRUCTION OF WARREN ST - WEST ST TO BROADWAY | 3 | FINAL DESIGN | Jul 2012 | Jan 2013 | Jul 2012 | Jan 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7F | RECONSTRUCTION OF WARREN ST - WEST ST TO BROADWAY | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2013 | Apr 2013 | Jan 2013 | Apr 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7F | RECONSTRUCTION OF WARREN ST - WEST ST TO BROADWAY | 5 | CONSTRUCTION TO 25% | Apr 2013 | Aug 2013 | Apr 2013 | Aug 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7F | RECONSTRUCTION OF WARREN ST - WEST ST TO BROADWAY | 6 | CONSTRUCTION TO 50% | Aug 2013 | Dec 2013 | Aug 2013 | Dec 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7F | RECONSTRUCTION OF WARREN ST - WEST ST TO BROADWAY | 7 | CONSTRUCTION TO 75% | Dec 2013 | Apr 2014 | Dec 2013 | Apr 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7F | RECONSTRUCTION OF WARREN ST - WEST ST TO BROADWAY | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2014 | Jul 2014 | Apr 2014 | Jul 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7F | RECONSTRUCTION OF WARREN ST - WEST ST TO BROADWAY | 9 | SUBSTANTIAL COMPLETION | Jul 2014 | Sep 2014 | Jul 2014 | Sep 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7F | RECONSTRUCTION OF WARREN ST - WEST ST TO BROADWAY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2014 | Oct 2014 | Sep 2014 | Mar 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB1 | Reconstruction of Nassau St | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB1 | Reconstruction of Nassau St | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB1 | Reconstruction of Nassau St | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB1 | Reconstruction of Nassau St | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB1 | Reconstruction of Nassau St | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB1 | Reconstruction of Nassau St | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB1 | Reconstruction of Nassau St | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB1 | Reconstruction of Nassau St | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB1 | Reconstruction of Nassau St | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB1 | Reconstruction of Nassau St | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Oct 2033
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB2 | Reconstruction of Greenwich | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB2 | Reconstruction of Greenwich | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB2 | Reconstruction of Greenwich | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB2 | Reconstruction of Greenwich | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB2 | Reconstruction of Greenwich | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB2 | Reconstruction of Greenwich | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB2 | Reconstruction of Greenwich | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB2 | Reconstruction of Greenwich | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB2 | Reconstruction of Greenwich | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB2 | Reconstruction of Greenwich | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Sep 2033
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB6 | Reconstruction of Vesey St, MED-668 | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB6 | Reconstruction of Vesey St, MED-668 | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB6 | Reconstruction of Vesey St, MED-668 | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB6 | Reconstruction of Vesey St, MED-668 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB6 | Reconstruction of Vesey St, MED-668 | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB6 | Reconstruction of Vesey St, MED-668 | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB6 | Reconstruction of Vesey St, MED-668 | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB6 | Reconstruction of Vesey St, MED-668 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB6 | Reconstruction of Vesey St, MED-668 | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB6 | Reconstruction of Vesey St, MED-668 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Jun 2033
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB7 | Reconstruction of Trinity Pl, SEN002182 | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2019 | Sep 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB7 | Reconstruction of Trinity Pl, SEN002182 | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2019 | Jan 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB7 | Reconstruction of Trinity Pl, SEN002182 | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2020 | Jul 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB7 | Reconstruction of Trinity Pl, SEN002182 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2020 | Oct 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB7 | Reconstruction of Trinity Pl, SEN002182 | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2020 | Feb 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB7 | Reconstruction of Trinity Pl, SEN002182 | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2021 | Jun 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB7 | Reconstruction of Trinity Pl, SEN002182 | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2021 | Oct 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB7 | Reconstruction of Trinity Pl, SEN002182 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2021 | Jan 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB7 | Reconstruction of Trinity Pl, SEN002182 | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2022 | Mar 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB7 | Reconstruction of Trinity Pl, SEN002182 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2022 | Jun 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB7 | Reconstruction of Trinity Pl, SEN002182 | 11 | PROJECT START | Mar 2024 | Apr 2024 | Jul 2023 | Jul 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB7 | Reconstruction of Trinity Pl, SEN002182 | 12 | DESIGN START | Mar 2024 | Apr 2024 | Jul 2023 | Jul 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB7 | Reconstruction of Trinity Pl, SEN002182 | 13 | DESIGN COMPLETION | Mar 2024 | Apr 2024 | Jul 2023 | Jul 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB7 | Reconstruction of Trinity Pl, SEN002182 | 14 | CONSTRUCTION START | Mar 2024 | Apr 2024 | Jul 2023 | Jul 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB7 | Reconstruction of Trinity Pl, SEN002182 | 15 | CONSTRUCTION COMPLETION | Mar 2024 | Apr 2024 | Jul 2023 | Jun 2032
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ003M | Montefiore Park and Plaza Reconstruction/Improvement | 1 | DEVELOP SCOPE | Jul 2011 | Sep 2011 | Jul 2011 | Sep 2011
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ003M | Montefiore Park and Plaza Reconstruction/Improvement | 2 | PRELIMINARY DESIGN | Sep 2011 | Jan 2012 | Sep 2011 | Jan 2012
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ003M | Montefiore Park and Plaza Reconstruction/Improvement | 3 | FINAL DESIGN | Jan 2012 | Jul 2012 | Jan 2012 | Mar 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ003M | Montefiore Park and Plaza Reconstruction/Improvement | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2012 | Oct 2012 | Mar 2016 | Jun 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ003M | Montefiore Park and Plaza Reconstruction/Improvement | 5 | CONSTRUCTION TO 25% | Oct 2012 | Feb 2013 | Jun 2016 | Nov 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ003M | Montefiore Park and Plaza Reconstruction/Improvement | 6 | CONSTRUCTION TO 50% | Feb 2013 | Jun 2013 | Nov 2016 | Apr 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ003M | Montefiore Park and Plaza Reconstruction/Improvement | 7 | CONSTRUCTION TO 75% | Jun 2013 | Oct 2013 | Apr 2017 | Sep 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ003M | Montefiore Park and Plaza Reconstruction/Improvement | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2013 | Jan 2014 | Sep 2017 | Dec 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ003M | Montefiore Park and Plaza Reconstruction/Improvement | 9 | SUBSTANTIAL COMPLETION | Jan 2014 | Mar 2014 | Dec 2017 | Feb 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ003M | Montefiore Park and Plaza Reconstruction/Improvement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2014 | Apr 2014 | Feb 2018 | Apr 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ003M | Montefiore Park and Plaza Reconstruction/Improvement | 11 | PROJECT START | Mar 2014 | Apr 2014 | Apr 2023 | Apr 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ003M | Montefiore Park and Plaza Reconstruction/Improvement | 12 | DESIGN START | Mar 2014 | Apr 2014 | Apr 2023 | Apr 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ003M | Montefiore Park and Plaza Reconstruction/Improvement | 13 | DESIGN COMPLETION | Mar 2014 | Apr 2014 | Apr 2023 | Apr 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ003M | Montefiore Park and Plaza Reconstruction/Improvement | 14 | CONSTRUCTION START | Mar 2014 | Apr 2014 | Apr 2023 | Apr 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ003M | Montefiore Park and Plaza Reconstruction/Improvement | 15 | CONSTRUCTION COMPLETION | Mar 2014 | Apr 2014 | Apr 2023 | Apr 2035
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ014M | Broadway Boulevard | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jul 2022 | Oct 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ014M | Broadway Boulevard | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Oct 2022 | Feb 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ014M | Broadway Boulevard | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Feb 2023 | Aug 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ014M | Broadway Boulevard | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Aug 2023 | Nov 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ014M | Broadway Boulevard | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Nov 2023 | Mar 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ014M | Broadway Boulevard | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Mar 2024 | Jul 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ014M | Broadway Boulevard | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jul 2024 | Nov 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ014M | Broadway Boulevard | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2020 | Jan 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ014M | Broadway Boulevard | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Feb 2022 | Apr 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ014M | Broadway Boulevard | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Apr 2022 | May 2033
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ015M | Pershing Square East Plaza/Streetscape Reconstruction | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ015M | Pershing Square East Plaza/Streetscape Reconstruction | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Sep 2018 | Jan 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ015M | Pershing Square East Plaza/Streetscape Reconstruction | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2019 | Jul 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ015M | Pershing Square East Plaza/Streetscape Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2019 | Oct 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ015M | Pershing Square East Plaza/Streetscape Reconstruction | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2019 | Feb 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ015M | Pershing Square East Plaza/Streetscape Reconstruction | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2020 | Jun 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ015M | Pershing Square East Plaza/Streetscape Reconstruction | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2020 | Oct 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ015M | Pershing Square East Plaza/Streetscape Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2020 | Jan 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ015M | Pershing Square East Plaza/Streetscape Reconstruction | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2021 | Mar 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ015M | Pershing Square East Plaza/Streetscape Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2021 | Apr 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ015M | Pershing Square East Plaza/Streetscape Reconstruction | 11 | PROJECT START | Mar 2021 | Apr 2021 | Apr 2023 | Apr 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ015M | Pershing Square East Plaza/Streetscape Reconstruction | 12 | DESIGN START | Mar 2021 | Apr 2021 | Apr 2023 | Apr 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ015M | Pershing Square East Plaza/Streetscape Reconstruction | 13 | DESIGN COMPLETION | Mar 2021 | Apr 2021 | Apr 2023 | Apr 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ015M | Pershing Square East Plaza/Streetscape Reconstruction | 14 | CONSTRUCTION START | Mar 2021 | Apr 2021 | Apr 2023 | Apr 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ015M | Pershing Square East Plaza/Streetscape Reconstruction | 15 | CONSTRUCTION COMPLETION | Mar 2021 | Apr 2021 | Apr 2023 | Jun 2033
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC1 | Complex Upgrades Ped Ramps - Manhattan | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC1 | Complex Upgrades Ped Ramps - Manhattan | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC1 | Complex Upgrades Ped Ramps - Manhattan | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC1 | Complex Upgrades Ped Ramps - Manhattan | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC1 | Complex Upgrades Ped Ramps - Manhattan | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC1 | Complex Upgrades Ped Ramps - Manhattan | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC1 | Complex Upgrades Ped Ramps - Manhattan | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC1 | Complex Upgrades Ped Ramps - Manhattan | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC1 | Complex Upgrades Ped Ramps - Manhattan | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC1 | Complex Upgrades Ped Ramps - Manhattan | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Jun 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC2 | Complex Upgrades Ped Ramps - Manhattan | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC2 | Complex Upgrades Ped Ramps - Manhattan | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC2 | Complex Upgrades Ped Ramps - Manhattan | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC2 | Complex Upgrades Ped Ramps - Manhattan | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC2 | Complex Upgrades Ped Ramps - Manhattan | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC2 | Complex Upgrades Ped Ramps - Manhattan | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC2 | Complex Upgrades Ped Ramps - Manhattan | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC2 | Complex Upgrades Ped Ramps - Manhattan | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC2 | Complex Upgrades Ped Ramps - Manhattan | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC2 | Complex Upgrades Ped Ramps - Manhattan | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Apr 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC2 | Complex Upgrades Ped Ramps - Manhattan | 11 | PROJECT START | Mar 2022 | Apr 2022 | Apr 2023 | Apr 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC2 | Complex Upgrades Ped Ramps - Manhattan | 12 | DESIGN START | Mar 2022 | Apr 2022 | Apr 2023 | Apr 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC2 | Complex Upgrades Ped Ramps - Manhattan | 13 | DESIGN COMPLETION | Mar 2022 | Apr 2022 | Apr 2023 | Apr 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC2 | Complex Upgrades Ped Ramps - Manhattan | 14 | CONSTRUCTION START | Mar 2022 | Apr 2022 | Apr 2023 | Apr 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC2 | Complex Upgrades Ped Ramps - Manhattan | 15 | CONSTRUCTION COMPLETION | Mar 2022 | Apr 2022 | Apr 2023 | Jun 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MCL | Non-Standard Upgrades Ped Ramp - Manhattan Landmark | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MCL | Non-Standard Upgrades Ped Ramp - Manhattan Landmark | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MCL | Non-Standard Upgrades Ped Ramp - Manhattan Landmark | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MCL | Non-Standard Upgrades Ped Ramp - Manhattan Landmark | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MCL | Non-Standard Upgrades Ped Ramp - Manhattan Landmark | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MCL | Non-Standard Upgrades Ped Ramp - Manhattan Landmark | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MCL | Non-Standard Upgrades Ped Ramp - Manhattan Landmark | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MCL | Non-Standard Upgrades Ped Ramp - Manhattan Landmark | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MCL | Non-Standard Upgrades Ped Ramp - Manhattan Landmark | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MCL | Non-Standard Upgrades Ped Ramp - Manhattan Landmark | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Jun 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MCL | Non-Standard Upgrades Ped Ramp - Manhattan Landmark | 11 | PROJECT START | Mar 2022 | Apr 2022 | Jul 2023 | Jul 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MCL | Non-Standard Upgrades Ped Ramp - Manhattan Landmark | 12 | DESIGN START | Mar 2022 | Apr 2022 | Jul 2023 | Jul 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MCL | Non-Standard Upgrades Ped Ramp - Manhattan Landmark | 13 | DESIGN COMPLETION | Mar 2022 | Apr 2022 | Jul 2023 | Jul 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MCL | Non-Standard Upgrades Ped Ramp - Manhattan Landmark | 14 | CONSTRUCTION START | Mar 2022 | Apr 2022 | Jul 2023 | Jul 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MCL | Non-Standard Upgrades Ped Ramp - Manhattan Landmark | 15 | CONSTRUCTION COMPLETION | Mar 2022 | Apr 2022 | Jul 2023 | Jul 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2019M | Prior Notice Sidewalks- Manhattan | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2019M | Prior Notice Sidewalks- Manhattan | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Sep 2018 | Jan 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2019M | Prior Notice Sidewalks- Manhattan | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2019 | Jul 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2019M | Prior Notice Sidewalks- Manhattan | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2019 | Oct 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2019M | Prior Notice Sidewalks- Manhattan | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2019 | Feb 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2019M | Prior Notice Sidewalks- Manhattan | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2020 | Jun 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2019M | Prior Notice Sidewalks- Manhattan | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2020 | Oct 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2019M | Prior Notice Sidewalks- Manhattan | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2020 | Jan 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2019M | Prior Notice Sidewalks- Manhattan | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2021 | Mar 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2019M | Prior Notice Sidewalks- Manhattan | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2022 | Feb 2029
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023M | Prior Notice Sidewalks - Manhattan | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2025 | Sep 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023M | Prior Notice Sidewalks - Manhattan | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2025 | Jan 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023M | Prior Notice Sidewalks - Manhattan | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2026 | Jul 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023M | Prior Notice Sidewalks - Manhattan | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2026 | Oct 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023M | Prior Notice Sidewalks - Manhattan | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2026 | Feb 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023M | Prior Notice Sidewalks - Manhattan | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2027 | Jun 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023M | Prior Notice Sidewalks - Manhattan | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2027 | Oct 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023M | Prior Notice Sidewalks - Manhattan | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Jun 2025 | Jul 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023M | Prior Notice Sidewalks - Manhattan | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jul 2025 | Aug 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023M | Prior Notice Sidewalks - Manhattan | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Aug 2025 | Sep 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18HGHVA | HAMILTON GRANGE - HVAC System Replacement | 1 | DEVELOP SCOPE | Jul 2022 | Sep 2022 | Jan 2023 | Mar 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18HGHVA | HAMILTON GRANGE - HVAC System Replacement | 2 | DESIGN | Sep 2022 | Sep 2023 | Apr 2023 | Mar 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18HGHVA | HAMILTON GRANGE - HVAC System Replacement | 3 | BID/ REGISTER CONTRACT | Sep 2023 | Jun 2024 | Mar 2024 | Dec 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18HGHVA | HAMILTON GRANGE - HVAC System Replacement | 4 | CONSTRUCTION | Jun 2024 | Jun 2025 | Dec 2024 | Dec 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18HGHVA | HAMILTON GRANGE - HVAC System Replacement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2025 | Jun 2026 | Dec 2025 | Dec 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18HGHVA | HAMILTON GRANGE - HVAC System Replacement | 6 | PROJECT START | Jun 2025 | Jun 2026 | Dec 2026 | Dec 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18HGHVA | HAMILTON GRANGE - HVAC System Replacement | 7 | DESIGN START | Jun 2025 | Jun 2026 | Dec 2026 | Dec 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18HGHVA | HAMILTON GRANGE - HVAC System Replacement | 8 | DESIGN COMPLETION | Jun 2025 | Jun 2026 | Dec 2026 | Dec 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18HGHVA | HAMILTON GRANGE - HVAC System Replacement | 9 | CONSTRUCTION START | Jun 2025 | Jun 2026 | Dec 2026 | Dec 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18HGHVA | HAMILTON GRANGE - HVAC System Replacement | 10 | CONSTRUCTION COMPLETION | Jun 2025 | Jun 2026 | Dec 2026 | Dec 2032
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA0996S | 96TH STREET - Exterior Rehabilitation | 1 | PROJECT START | Mar 2009 | Mar 2009 | Mar 2009 | Mar 2009
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA0996S | 96TH STREET - Exterior Rehabilitation | 2 | DESIGN START | Mar 2009 | Sep 2010 | Mar 2009 | Sep 2010
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA0996S | 96TH STREET - Exterior Rehabilitation | 3 | DESIGN COMPLETION | Sep 2010 | Sep 2011 | Sep 2010 | Sep 2011
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA0996S | 96TH STREET - Exterior Rehabilitation | 4 | CONSTRUCTION START | Sep 2011 | Sep 2011 | Sep 2011 | Dec 2011
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA0996S | 96TH STREET - Exterior Rehabilitation | 5 | CONSTRUCTION COMPLETION | Sep 2011 | Sep 2012 | Jun 2016 | Sep 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10115 | 115TH STREET - Removal and Replacement of Floors | 1 | DESIGN | Oct 2010 | Mar 2011 | Jul 2008 | Aug 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10115 | 115TH STREET - Removal and Replacement of Floors | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2011 | Jun 2011 | Aug 2013 | Aug 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10115 | 115TH STREET - Removal and Replacement of Floors | 3 | CONSTRUCTION | Jun 2011 | Jun 2012 | Aug 2018 | Aug 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10115 | 115TH STREET - Removal and Replacement of Floors | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2012 | Dec 2014 | Aug 2019 | Feb 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10115 | 115TH STREET - Removal and Replacement of Floors | 5 | PROJECT START | Dec 2014 | Dec 2014 | Feb 2022 | May 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10115 | 115TH STREET - Removal and Replacement of Floors | 6 | DESIGN START | Dec 2014 | Dec 2014 | Jul 2011 | Aug 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10115 | 115TH STREET - Removal and Replacement of Floors | 7 | DESIGN COMPLETION | Dec 2014 | Dec 2014 | May 2017 | Jun 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10115 | 115TH STREET - Removal and Replacement of Floors | 8 | CONSTRUCTION START | Dec 2014 | Dec 2014 | Jun 2018 | Aug 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10115 | 115TH STREET - Removal and Replacement of Floors | 9 | CONSTRUCTION COMPLETION | Dec 2014 | Dec 2014 | Aug 2018 | Aug 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10AGL | AGUILAR - Facade Restoration | 1 | PROJECT START | May 2010 | May 2010 | May 2010 | May 2010
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10AGL | AGUILAR - Facade Restoration | 2 | DESIGN START | May 2010 | Nov 2010 | May 2010 | Dec 2011
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10AGL | AGUILAR - Facade Restoration | 3 | DESIGN COMPLETION | Nov 2010 | May 2011 | Dec 2011 | Jun 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10AGL | AGUILAR - Facade Restoration | 4 | CONSTRUCTION START | May 2011 | Jun 2011 | Jun 2014 | Jun 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10AGL | AGUILAR - Facade Restoration | 5 | CONSTRUCTION COMPLETION | Jun 2011 | Aug 2012 | Jun 2023 | Sep 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10JMB | JEFFERSON MARKET - ADA Accessibility | 1 | PROJECT START | Aug 2009 | Feb 2010 | Aug 2009 | Nov 2009
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10JMB | JEFFERSON MARKET - ADA Accessibility | 2 | DESIGN START | Feb 2010 | May 2010 | Nov 2009 | Jul 2010
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10JMB | JEFFERSON MARKET - ADA Accessibility | 3 | DESIGN COMPLETION | May 2010 | May 2011 | Jul 2010 | Dec 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10JMB | JEFFERSON MARKET - ADA Accessibility | 4 | CONSTRUCTION START | May 2011 | Jul 2011 | Dec 2020 | Feb 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10JMB | JEFFERSON MARKET - ADA Accessibility | 5 | CONSTRUCTION COMPLETION | Jul 2011 | Jul 2012 | Feb 2021 | Feb 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA11BLD | BLOOMINGDALE - Interior Renovation | 1 | DESIGN | Oct 2010 | Mar 2011 | Oct 2010 | Oct 2010
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA11BLD | BLOOMINGDALE - Interior Renovation | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2011 | Jun 2011 | Oct 2010 | Oct 2010
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA11BLD | BLOOMINGDALE - Interior Renovation | 3 | CONSTRUCTION | Jun 2011 | Jun 2012 | Oct 2010 | Oct 2010
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA11BLD | BLOOMINGDALE - Interior Renovation | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2012 | Dec 2012 | Oct 2010 | Oct 2010
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA11BLD | BLOOMINGDALE - Interior Renovation | 5 | CONSTRUCTION COMPLETION | Jun 2012 | Dec 2012 | Jun 2016 | Dec 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12EPH | EPIPHANY - FACADE RESTORATION | 1 | DEVELOP SCOPE | Sep 2012 | Dec 2012 | Sep 2012 | Dec 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12EPH | EPIPHANY - FACADE RESTORATION | 2 | PRELIMINARY DESIGN | Dec 2012 | Apr 2013 | Dec 2014 | Sep 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12EPH | EPIPHANY - FACADE RESTORATION | 3 | FINAL DESIGN | Apr 2013 | Oct 2013 | Oct 2016 | Jun 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12EPH | EPIPHANY - FACADE RESTORATION | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2013 | Jan 2014 | Jul 2018 | Jul 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12EPH | EPIPHANY - FACADE RESTORATION | 5 | CONSTRUCTION TO 25% | Jan 2014 | May 2014 | Jul 2020 | Nov 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12EPH | EPIPHANY - FACADE RESTORATION | 6 | CONSTRUCTION TO 50% | May 2014 | Sep 2014 | Nov 2020 | Mar 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12EPH | EPIPHANY - FACADE RESTORATION | 7 | CONSTRUCTION TO 75% | Sep 2014 | Jan 2015 | Mar 2021 | Jul 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12EPH | EPIPHANY - FACADE RESTORATION | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2015 | Apr 2015 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12EPH | EPIPHANY - FACADE RESTORATION | 9 | SUBSTANTIAL COMPLETION | Apr 2015 | Jun 2015 | Oct 2021 | Dec 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12EPH | EPIPHANY - FACADE RESTORATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2015 | Jul 2015 | Jun 2016 | Dec 2032
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12SWP | SEWARD PARK - Replace sidealk over vault and waterproof | 1 | DEVELOP SCOPE | Sep 2012 | Dec 2012 | Sep 2012 | Dec 2012
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12SWP | SEWARD PARK - Replace sidealk over vault and waterproof | 2 | PRELIMINARY DESIGN | Dec 2012 | Apr 2013 | Dec 2012 | Apr 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12SWP | SEWARD PARK - Replace sidealk over vault and waterproof | 3 | FINAL DESIGN | Apr 2013 | Oct 2013 | Apr 2013 | Oct 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12SWP | SEWARD PARK - Replace sidealk over vault and waterproof | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2013 | Jan 2014 | Oct 2013 | Jan 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12SWP | SEWARD PARK - Replace sidealk over vault and waterproof | 5 | CONSTRUCTION TO 25% | Jan 2014 | May 2014 | Jan 2014 | May 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12SWP | SEWARD PARK - Replace sidealk over vault and waterproof | 6 | CONSTRUCTION TO 50% | May 2014 | Sep 2014 | May 2014 | Sep 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12SWP | SEWARD PARK - Replace sidealk over vault and waterproof | 7 | CONSTRUCTION TO 75% | Sep 2014 | Jan 2015 | Sep 2014 | Jan 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12SWP | SEWARD PARK - Replace sidealk over vault and waterproof | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2015 | Apr 2015 | Jan 2015 | Apr 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12SWP | SEWARD PARK - Replace sidealk over vault and waterproof | 9 | SUBSTANTIAL COMPLETION | Apr 2015 | Jun 2015 | Apr 2015 | Jun 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12SWP | SEWARD PARK - Replace sidealk over vault and waterproof | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2015 | Jul 2015 | Jun 2016 | Jul 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13GBR | GEORGE BRUCE: Partial Interior/Exterior,/ Roof / Boiler | 1 | PROJECT START | Mar 2014 | Mar 2014 | Mar 2014 | Mar 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13GBR | GEORGE BRUCE: Partial Interior/Exterior,/ Roof / Boiler | 2 | DESIGN START | Mar 2014 | Mar 2014 | Mar 2014 | Mar 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13GBR | GEORGE BRUCE: Partial Interior/Exterior,/ Roof / Boiler | 3 | DESIGN COMPLETION | Mar 2014 | Mar 2014 | Mar 2014 | Mar 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13GBR | GEORGE BRUCE: Partial Interior/Exterior,/ Roof / Boiler | 4 | CONSTRUCTION START | Mar 2014 | Mar 2014 | Mar 2014 | Mar 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13GBR | GEORGE BRUCE: Partial Interior/Exterior,/ Roof / Boiler | 5 | CONSTRUCTION COMPLETION | Apr 2014 | Mar 2017 | Apr 2016 | Dec 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13HAM | HAMILTON FISH: REHABILITATION | 1 | PROJECT START | Mar 2013 | Mar 2013 | Mar 2013 | Mar 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13HAM | HAMILTON FISH: REHABILITATION | 2 | DESIGN START | Mar 2013 | Mar 2013 | Mar 2013 | Mar 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13HAM | HAMILTON FISH: REHABILITATION | 3 | DESIGN COMPLETION | Mar 2013 | Mar 2013 | Mar 2013 | Mar 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13HAM | HAMILTON FISH: REHABILITATION | 4 | CONSTRUCTION START | Mar 2013 | Mar 2013 | Mar 2013 | Mar 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13HAM | HAMILTON FISH: REHABILITATION | 5 | CONSTRUCTION COMPLETION | Mar 2013 | Feb 2017 | Jun 2016 | Dec 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MLB | MUHLENBERG: Elevator | 1 | PROJECT START | Feb 2013 | Feb 2013 | Feb 2013 | Feb 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MLB | MUHLENBERG: Elevator | 2 | DESIGN START | Feb 2013 | Feb 2015 | Feb 2013 | Feb 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MLB | MUHLENBERG: Elevator | 3 | DESIGN COMPLETION | Feb 2015 | Sep 2015 | Feb 2015 | Sep 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MLB | MUHLENBERG: Elevator | 4 | CONSTRUCTION START | Oct 2015 | Feb 2016 | Oct 2015 | Feb 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MLB | MUHLENBERG: Elevator | 5 | CONSTRUCTION COMPLETION | Feb 2016 | Oct 2016 | Feb 2016 | Oct 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13NAM | NEW AMSTERDAM - HVAC and Cooling Tower | 1 | PROJECT START | Jan 2013 | Feb 2015 | Jan 2013 | Jan 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13NAM | NEW AMSTERDAM - HVAC and Cooling Tower | 2 | DESIGN START | Feb 2015 | Nov 2015 | Jan 2013 | Mar 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13NAM | NEW AMSTERDAM - HVAC and Cooling Tower | 3 | DESIGN COMPLETION | Nov 2015 | Jul 2016 | Mar 2015 | Dec 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13NAM | NEW AMSTERDAM - HVAC and Cooling Tower | 4 | CONSTRUCTION START | Jul 2016 | Jul 2016 | Dec 2016 | Oct 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13NAM | NEW AMSTERDAM - HVAC and Cooling Tower | 5 | CONSTRUCTION COMPLETION | Jul 2016 | Jun 2017 | Oct 2018 | Jan 2029
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA14MBG | HVAC and Related Work | 1 | PROJECT START | Sep 2014 | Sep 2014 | Sep 2014 | Sep 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA14MBG | HVAC and Related Work | 2 | DESIGN START | Jun 2015 | Jun 2015 | Jun 2015 | Aug 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA14MBG | HVAC and Related Work | 3 | DESIGN COMPLETION | Dec 2015 | Dec 2015 | Dec 2015 | Jun 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA14MBG | HVAC and Related Work | 4 | CONSTRUCTION START | Jun 2016 | Jun 2016 | Jun 2016 | Feb 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA14MBG | HVAC and Related Work | 5 | CONSTRUCTION COMPLETION | Apr 2017 | Apr 2017 | Jun 2017 | Jun 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCAL15CC | Countee Cullen:Exterior Renovation | 1 | PROJECT START | Mar 2016 | Mar 2016 | Mar 2016 | Mar 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCAL15CC | Countee Cullen:Exterior Renovation | 2 | DESIGN START | Apr 2016 | Apr 2016 | Apr 2016 | Apr 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCAL15CC | Countee Cullen:Exterior Renovation | 3 | DESIGN COMPLETION | Apr 2016 | Apr 2016 | Apr 2016 | Apr 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCAL15CC | Countee Cullen:Exterior Renovation | 4 | CONSTRUCTION START | Jun 2016 | Jun 2016 | Jun 2016 | Jun 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCAL15CC | Countee Cullen:Exterior Renovation | 5 | CONSTRUCTION COMPLETION | Dec 2017 | Dec 2017 | Dec 2017 | Dec 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA08MHV | MANHATTAN (Northern) - HVAC @ Four Branch Libraries | 1 | PROJECT START | Oct 2007 | Oct 2007 | Oct 2007 | Oct 2007
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA08MHV | MANHATTAN (Northern) - HVAC @ Four Branch Libraries | 2 | DESIGN START | Apr 2009 | Apr 2009 | Oct 2009 | Oct 2009
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA08MHV | MANHATTAN (Northern) - HVAC @ Four Branch Libraries | 3 | DESIGN COMPLETION | Mar 2010 | Jul 2010 | Jan 2011 | Jan 2011
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA08MHV | MANHATTAN (Northern) - HVAC @ Four Branch Libraries | 4 | CONSTRUCTION START | Jul 2010 | Jan 2012 | Jul 2013 | Jul 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA08MHV | MANHATTAN (Northern) - HVAC @ Four Branch Libraries | 5 | CONSTRUCTION COMPLETION | Jan 2012 | Mar 2012 | Sep 2017 | Sep 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13HGR | HAMILTON GRANGE:Exterior Rehabiliation/ Window | 1 | PROJECT START | Mar 2013 | Mar 2013 | Mar 2008 | Mar 2008
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13HGR | HAMILTON GRANGE:Exterior Rehabiliation/ Window | 2 | DESIGN START | May 2014 | May 2014 | May 2014 | May 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13HGR | HAMILTON GRANGE:Exterior Rehabiliation/ Window | 3 | DESIGN COMPLETION | Jul 2015 | Jul 2015 | Jul 2015 | Jul 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13HGR | HAMILTON GRANGE:Exterior Rehabiliation/ Window | 4 | CONSTRUCTION START | Feb 2016 | Feb 2016 | Feb 2016 | Feb 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13HGR | HAMILTON GRANGE:Exterior Rehabiliation/ Window | 5 | CONSTRUCTION COMPLETION | Mar 2017 | Mar 2017 | Mar 2017 | Jun 2032
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM12MLB | MUHLENBERG - Sidewalk Vault | 1 | DESIGN | Feb 2012 | Feb 2012 | Feb 2012 | Apr 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM12MLB | MUHLENBERG - Sidewalk Vault | 2 | CONSTRUCTION | Jul 2015 | Jul 2015 | Jul 2015 | Sep 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM12MLB | MUHLENBERG - Sidewalk Vault | 3 | ORIGINAL EQUIP & FURNISHING | Aug 2015 | Aug 2015 | Aug 2015 | Sep 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM12MLB | MUHLENBERG - Sidewalk Vault | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2016 | Jan 2016 | Jan 2016 | Oct 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM12MLB | MUHLENBERG - Sidewalk Vault | 5 | PROJECT START | Jan 2016 | Jan 2016 | Oct 2021 | Oct 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM12MLB | MUHLENBERG - Sidewalk Vault | 6 | DESIGN START | Jan 2016 | Jan 2016 | Oct 2021 | Oct 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM12MLB | MUHLENBERG - Sidewalk Vault | 7 | DESIGN COMPLETION | Jan 2016 | Jan 2016 | Oct 2021 | Oct 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM12MLB | MUHLENBERG - Sidewalk Vault | 8 | CONSTRUCTION START | Jan 2016 | Jan 2016 | Oct 2021 | Oct 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM12MLB | MUHLENBERG - Sidewalk Vault | 9 | CONSTRUCTION COMPLETION | Jan 2016 | Jan 2016 | Oct 2021 | Oct 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNMNA08LS | MANHATTAN - Life Safety Projects @ 17 Branch Libraries | 1 | PROJECT START | Jan 2010 | Jan 2010 | Jan 2008 | Jan 2008
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNMNA08LS | MANHATTAN - Life Safety Projects @ 17 Branch Libraries | 2 | DESIGN START | Feb 2010 | Feb 2010 | Oct 2009 | Oct 2009
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNMNA08LS | MANHATTAN - Life Safety Projects @ 17 Branch Libraries | 3 | DESIGN COMPLETION | Feb 2010 | Feb 2010 | May 2013 | May 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNMNA08LS | MANHATTAN - Life Safety Projects @ 17 Branch Libraries | 4 | CONSTRUCTION START | Feb 2010 | Feb 2010 | Apr 2015 | Apr 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNMNA08LS | MANHATTAN - Life Safety Projects @ 17 Branch Libraries | 5 | CONSTRUCTION COMPLETION | Feb 2010 | Feb 2010 | Oct 2017 | Jun 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-594 | WM RPLMT IN E 46 ST & E 47 ST B/T MADISON AV & LEXINGTON AV | 1 | DEVELOP SCOPE | Jul 2007 | Oct 2007 | Jul 2011 | Aug 2012
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-594 | WM RPLMT IN E 46 ST & E 47 ST B/T MADISON AV & LEXINGTON AV | 2 | PRELIMINARY DESIGN | Oct 2007 | Feb 2008 | Aug 2012 | Jul 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-594 | WM RPLMT IN E 46 ST & E 47 ST B/T MADISON AV & LEXINGTON AV | 3 | FINAL DESIGN | Feb 2008 | Aug 2008 | Jul 2014 | Nov 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-594 | WM RPLMT IN E 46 ST & E 47 ST B/T MADISON AV & LEXINGTON AV | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2008 | Nov 2008 | Dec 2019 | Mar 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-594 | WM RPLMT IN E 46 ST & E 47 ST B/T MADISON AV & LEXINGTON AV | 5 | CONSTRUCTION TO 25% | Nov 2008 | Mar 2009 | Mar 2020 | Sep 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-594 | WM RPLMT IN E 46 ST & E 47 ST B/T MADISON AV & LEXINGTON AV | 6 | CONSTRUCTION TO 50% | Mar 2009 | Jul 2009 | Sep 2020 | Mar 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-594 | WM RPLMT IN E 46 ST & E 47 ST B/T MADISON AV & LEXINGTON AV | 7 | CONSTRUCTION TO 75% | Jul 2009 | Nov 2009 | Mar 2021 | Aug 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-594 | WM RPLMT IN E 46 ST & E 47 ST B/T MADISON AV & LEXINGTON AV | 8 | ORIGINAL EQUIP & FURNISHING | Nov 2009 | Feb 2010 | Aug 2021 | Nov 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-594 | WM RPLMT IN E 46 ST & E 47 ST B/T MADISON AV & LEXINGTON AV | 9 | SUBSTANTIAL COMPLETION | Feb 2010 | Apr 2010 | Nov 2021 | Jan 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-594 | WM RPLMT IN E 46 ST & E 47 ST B/T MADISON AV & LEXINGTON AV | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2010 | May 2010 | Jan 2022 | Jun 2030
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-597 | TRUNK WM IN EAST 31 STREET FRM 5TH AV TO 2ND AV | 1 | DEVELOP SCOPE | Jul 2011 | Oct 2011 | Jul 2011 | Oct 2011
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-597 | TRUNK WM IN EAST 31 STREET FRM 5TH AV TO 2ND AV | 2 | PRELIMINARY DESIGN | Oct 2011 | Feb 2012 | Oct 2011 | Feb 2012
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-597 | TRUNK WM IN EAST 31 STREET FRM 5TH AV TO 2ND AV | 3 | FINAL DESIGN | Feb 2012 | Aug 2012 | Feb 2012 | Aug 2012
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-597 | TRUNK WM IN EAST 31 STREET FRM 5TH AV TO 2ND AV | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2012 | Nov 2012 | Mar 2022 | Jun 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-597 | TRUNK WM IN EAST 31 STREET FRM 5TH AV TO 2ND AV | 5 | CONSTRUCTION TO 25% | Nov 2012 | Mar 2013 | Jun 2022 | Jun 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-597 | TRUNK WM IN EAST 31 STREET FRM 5TH AV TO 2ND AV | 6 | CONSTRUCTION TO 50% | Mar 2013 | Jul 2013 | Jun 2022 | Jun 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-597 | TRUNK WM IN EAST 31 STREET FRM 5TH AV TO 2ND AV | 7 | CONSTRUCTION TO 75% | Jul 2013 | Nov 2013 | Jun 2022 | Jun 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-597 | TRUNK WM IN EAST 31 STREET FRM 5TH AV TO 2ND AV | 8 | ORIGINAL EQUIP & FURNISHING | Nov 2013 | Feb 2014 | Jun 2022 | Jun 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-597 | TRUNK WM IN EAST 31 STREET FRM 5TH AV TO 2ND AV | 9 | SUBSTANTIAL COMPLETION | Feb 2014 | Apr 2014 | Jun 2022 | Jun 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-597 | TRUNK WM IN EAST 31 STREET FRM 5TH AV TO 2ND AV | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2014 | May 2014 | Nov 2024 | Jun 2031
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-598B | TRUNK WM IN W 30 ST - 9 AV TO 10 AV (SHAFT 26B) - PHASE B | 1 | DEVELOP SCOPE | Jul 2012 | Sep 2012 | Mar 2017 | May 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-598B | TRUNK WM IN W 30 ST - 9 AV TO 10 AV (SHAFT 26B) - PHASE B | 2 | PRELIMINARY DESIGN | Sep 2012 | Jan 2013 | May 2017 | Sep 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-598B | TRUNK WM IN W 30 ST - 9 AV TO 10 AV (SHAFT 26B) - PHASE B | 3 | FINAL DESIGN | Jan 2013 | Jul 2013 | Sep 2017 | Dec 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-598B | TRUNK WM IN W 30 ST - 9 AV TO 10 AV (SHAFT 26B) - PHASE B | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2013 | Oct 2013 | Dec 2019 | Feb 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-598B | TRUNK WM IN W 30 ST - 9 AV TO 10 AV (SHAFT 26B) - PHASE B | 5 | CONSTRUCTION TO 25% | Oct 2013 | Feb 2014 | Mar 2020 | Jun 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-598B | TRUNK WM IN W 30 ST - 9 AV TO 10 AV (SHAFT 26B) - PHASE B | 6 | CONSTRUCTION TO 50% | Feb 2014 | Jun 2014 | Jun 2020 | Oct 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-598B | TRUNK WM IN W 30 ST - 9 AV TO 10 AV (SHAFT 26B) - PHASE B | 7 | CONSTRUCTION TO 75% | Jun 2014 | Oct 2014 | Oct 2020 | Feb 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-598B | TRUNK WM IN W 30 ST - 9 AV TO 10 AV (SHAFT 26B) - PHASE B | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2014 | Jan 2015 | Feb 2021 | Feb 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-598B | TRUNK WM IN W 30 ST - 9 AV TO 10 AV (SHAFT 26B) - PHASE B | 9 | SUBSTANTIAL COMPLETION | Jan 2015 | Mar 2015 | Feb 2021 | May 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-598B | TRUNK WM IN W 30 ST - 9 AV TO 10 AV (SHAFT 26B) - PHASE B | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Apr 2015 | May 2021 | Jun 2029
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-604 | TRUNK & DIS WM IN EAST HOUSTONS ST (HWMP2019) | 1 | DEVELOP SCOPE | Aug 2009 | Nov 2009 | Aug 2009 | Nov 2009
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-604 | TRUNK & DIS WM IN EAST HOUSTONS ST (HWMP2019) | 2 | PRELIMINARY DESIGN | Nov 2009 | Mar 2010 | Nov 2009 | Mar 2010
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-604 | TRUNK & DIS WM IN EAST HOUSTONS ST (HWMP2019) | 3 | FINAL DESIGN | Mar 2010 | Feb 2012 | Mar 2010 | Oct 2011
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-604 | TRUNK & DIS WM IN EAST HOUSTONS ST (HWMP2019) | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2012 | Jun 2012 | Oct 2011 | Feb 2012
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-604 | TRUNK & DIS WM IN EAST HOUSTONS ST (HWMP2019) | 5 | CONSTRUCTION TO 25% | Jun 2012 | Jun 2012 | Feb 2012 | Jan 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-604 | TRUNK & DIS WM IN EAST HOUSTONS ST (HWMP2019) | 6 | CONSTRUCTION TO 50% | Jun 2012 | Jun 2012 | Feb 2013 | Jan 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-604 | TRUNK & DIS WM IN EAST HOUSTONS ST (HWMP2019) | 7 | CONSTRUCTION TO 75% | Jun 2012 | Jun 2012 | Feb 2014 | Dec 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-604 | TRUNK & DIS WM IN EAST HOUSTONS ST (HWMP2019) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2012 | Jun 2012 | Dec 2015 | Mar 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-604 | TRUNK & DIS WM IN EAST HOUSTONS ST (HWMP2019) | 9 | SUBSTANTIAL COMPLETION | Jun 2012 | Jun 2012 | Mar 2016 | Jun 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-604 | TRUNK & DIS WM IN EAST HOUSTONS ST (HWMP2019) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2012 | Jul 2012 | Jun 2016 | Dec 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-604 | TRUNK & DIS WM IN EAST HOUSTONS ST (HWMP2019) | 11 | PROJECT START | Jun 2012 | Jul 2012 | Dec 2021 | Dec 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-604 | TRUNK & DIS WM IN EAST HOUSTONS ST (HWMP2019) | 12 | DESIGN START | Jun 2012 | Jul 2012 | Dec 2021 | Dec 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-604 | TRUNK & DIS WM IN EAST HOUSTONS ST (HWMP2019) | 13 | DESIGN COMPLETION | Jun 2012 | Jul 2012 | Dec 2021 | Dec 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-604 | TRUNK & DIS WM IN EAST HOUSTONS ST (HWMP2019) | 14 | CONSTRUCTION START | Jun 2012 | Jul 2012 | Dec 2021 | Dec 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-604 | TRUNK & DIS WM IN EAST HOUSTONS ST (HWMP2019) | 15 | CONSTRUCTION COMPLETION | Jun 2012 | Jul 2012 | Dec 2021 | Dec 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-607 | TRUNK MAIN CONN TO SHAFT 32B IN 2ND AVE. INTER. OF E. 35ST. | 1 | DEVELOP SCOPE | Feb 2010 | May 2010 | Mar 2010 | May 2010
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-607 | TRUNK MAIN CONN TO SHAFT 32B IN 2ND AVE. INTER. OF E. 35ST. | 2 | PRELIMINARY DESIGN | May 2010 | Sep 2010 | May 2010 | Sep 2010
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-607 | TRUNK MAIN CONN TO SHAFT 32B IN 2ND AVE. INTER. OF E. 35ST. | 3 | FINAL DESIGN | Sep 2010 | Mar 2011 | Sep 2010 | Mar 2011
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-607 | TRUNK MAIN CONN TO SHAFT 32B IN 2ND AVE. INTER. OF E. 35ST. | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2011 | Jun 2011 | Mar 2016 | Jun 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-607 | TRUNK MAIN CONN TO SHAFT 32B IN 2ND AVE. INTER. OF E. 35ST. | 5 | CONSTRUCTION TO 25% | Jun 2011 | Oct 2011 | Jun 2016 | Jun 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-607 | TRUNK MAIN CONN TO SHAFT 32B IN 2ND AVE. INTER. OF E. 35ST. | 6 | CONSTRUCTION TO 50% | Oct 2011 | Feb 2012 | Jun 2016 | Jun 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-607 | TRUNK MAIN CONN TO SHAFT 32B IN 2ND AVE. INTER. OF E. 35ST. | 7 | CONSTRUCTION TO 75% | Feb 2012 | Jun 2012 | Jun 2016 | Jun 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-607 | TRUNK MAIN CONN TO SHAFT 32B IN 2ND AVE. INTER. OF E. 35ST. | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2012 | Sep 2012 | Jun 2016 | Jun 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-607 | TRUNK MAIN CONN TO SHAFT 32B IN 2ND AVE. INTER. OF E. 35ST. | 9 | SUBSTANTIAL COMPLETION | Sep 2012 | Oct 2012 | Jun 2016 | Jun 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-607 | TRUNK MAIN CONN TO SHAFT 32B IN 2ND AVE. INTER. OF E. 35ST. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2012 | Nov 2012 | Nov 2017 | Jun 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-607 | TRUNK MAIN CONN TO SHAFT 32B IN 2ND AVE. INTER. OF E. 35ST. | 11 | PROJECT START | Nov 2012 | Nov 2012 | Jun 2024 | Jun 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-607 | TRUNK MAIN CONN TO SHAFT 32B IN 2ND AVE. INTER. OF E. 35ST. | 12 | DESIGN START | Nov 2012 | Nov 2012 | Jun 2024 | Jun 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-607 | TRUNK MAIN CONN TO SHAFT 32B IN 2ND AVE. INTER. OF E. 35ST. | 13 | DESIGN COMPLETION | Nov 2012 | Nov 2012 | Jun 2024 | Jun 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-607 | TRUNK MAIN CONN TO SHAFT 32B IN 2ND AVE. INTER. OF E. 35ST. | 14 | CONSTRUCTION START | Nov 2012 | Nov 2012 | Jun 2024 | Jun 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-607 | TRUNK MAIN CONN TO SHAFT 32B IN 2ND AVE. INTER. OF E. 35ST. | 15 | CONSTRUCTION COMPLETION | Nov 2012 | Nov 2012 | Jun 2024 | Jun 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-609 | TRUNK MAIN IN W60 ST, W.E. AVE TO COLUMBUS AV | 1 | DEVELOP SCOPE | Jan 2011 | Mar 2011 | Jan 2011 | Mar 2011
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-609 | TRUNK MAIN IN W60 ST, W.E. AVE TO COLUMBUS AV | 2 | PRELIMINARY DESIGN | Apr 2011 | Jul 2011 | Apr 2011 | Jul 2011
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-609 | TRUNK MAIN IN W60 ST, W.E. AVE TO COLUMBUS AV | 3 | FINAL DESIGN | Jul 2011 | Jan 2012 | Jul 2011 | Dec 2011
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-609 | TRUNK MAIN IN W60 ST, W.E. AVE TO COLUMBUS AV | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2012 | Apr 2012 | Dec 2011 | Mar 2012
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-609 | TRUNK MAIN IN W60 ST, W.E. AVE TO COLUMBUS AV | 5 | CONSTRUCTION TO 25% | Apr 2012 | Aug 2012 | Mar 2012 | Mar 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-609 | TRUNK MAIN IN W60 ST, W.E. AVE TO COLUMBUS AV | 6 | CONSTRUCTION TO 50% | Aug 2012 | Dec 2012 | Mar 2014 | Mar 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-609 | TRUNK MAIN IN W60 ST, W.E. AVE TO COLUMBUS AV | 7 | CONSTRUCTION TO 75% | Dec 2012 | Apr 2013 | Mar 2016 | Mar 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-609 | TRUNK MAIN IN W60 ST, W.E. AVE TO COLUMBUS AV | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2013 | Jul 2013 | Mar 2019 | Mar 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-609 | TRUNK MAIN IN W60 ST, W.E. AVE TO COLUMBUS AV | 9 | SUBSTANTIAL COMPLETION | Jul 2013 | Sep 2013 | Mar 2019 | Mar 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-609 | TRUNK MAIN IN W60 ST, W.E. AVE TO COLUMBUS AV | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2013 | Oct 2013 | Mar 2019 | Jan 2032
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-610 | TRUNK MAIN CONNECTION TO SHAFT 27B | 1 | DEVELOP SCOPE | Jan 2011 | Mar 2011 | Dec 2010 | Mar 2011
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-610 | TRUNK MAIN CONNECTION TO SHAFT 27B | 2 | PRELIMINARY DESIGN | Apr 2011 | Jul 2011 | Mar 2011 | Jul 2011
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-610 | TRUNK MAIN CONNECTION TO SHAFT 27B | 3 | FINAL DESIGN | Jul 2011 | Jan 2012 | Jul 2011 | Dec 2011
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-610 | TRUNK MAIN CONNECTION TO SHAFT 27B | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2012 | Apr 2012 | Dec 2011 | Mar 2012
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-610 | TRUNK MAIN CONNECTION TO SHAFT 27B | 5 | CONSTRUCTION TO 25% | Apr 2012 | Aug 2012 | Mar 2012 | Sep 2012
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-610 | TRUNK MAIN CONNECTION TO SHAFT 27B | 6 | CONSTRUCTION TO 50% | Aug 2012 | Dec 2012 | Sep 2012 | Sep 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-610 | TRUNK MAIN CONNECTION TO SHAFT 27B | 7 | CONSTRUCTION TO 75% | Dec 2012 | Apr 2013 | Sep 2013 | Sep 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-610 | TRUNK MAIN CONNECTION TO SHAFT 27B | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2013 | Jul 2013 | Sep 2015 | Sep 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-610 | TRUNK MAIN CONNECTION TO SHAFT 27B | 9 | SUBSTANTIAL COMPLETION | Jul 2013 | Sep 2013 | Sep 2015 | Nov 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-610 | TRUNK MAIN CONNECTION TO SHAFT 27B | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2013 | Oct 2013 | Nov 2015 | Jun 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-610 | TRUNK MAIN CONNECTION TO SHAFT 27B | 11 | PROJECT START | Sep 2013 | Oct 2013 | Jul 2024 | Jul 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-610 | TRUNK MAIN CONNECTION TO SHAFT 27B | 12 | DESIGN START | Sep 2013 | Oct 2013 | Jul 2024 | Jul 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-610 | TRUNK MAIN CONNECTION TO SHAFT 27B | 13 | DESIGN COMPLETION | Sep 2013 | Oct 2013 | Jul 2024 | Jul 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-610 | TRUNK MAIN CONNECTION TO SHAFT 27B | 14 | CONSTRUCTION START | Sep 2013 | Oct 2013 | Jul 2024 | Jul 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-610 | TRUNK MAIN CONNECTION TO SHAFT 27B | 15 | CONSTRUCTION COMPLETION | Sep 2013 | Oct 2013 | Jul 2024 | Jul 2032
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-611 | TRUNK WM REPLACMT IN TRANSVERSE RD 3 | 1 | DEVELOP SCOPE | Mar 2022 | May 2022 | Mar 2015 | Mar 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-611 | TRUNK WM REPLACMT IN TRANSVERSE RD 3 | 2 | PRELIMINARY DESIGN | May 2022 | Sep 2022 | Mar 2015 | Mar 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-611 | TRUNK WM REPLACMT IN TRANSVERSE RD 3 | 3 | FINAL DESIGN | Sep 2022 | Mar 2023 | Mar 2015 | Mar 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-611 | TRUNK WM REPLACMT IN TRANSVERSE RD 3 | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2023 | Jun 2023 | Mar 2015 | Mar 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-611 | TRUNK WM REPLACMT IN TRANSVERSE RD 3 | 5 | CONSTRUCTION TO 25% | Jun 2023 | Oct 2023 | Mar 2015 | Mar 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-611 | TRUNK WM REPLACMT IN TRANSVERSE RD 3 | 6 | CONSTRUCTION TO 50% | Oct 2023 | Feb 2024 | Mar 2015 | Mar 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-611 | TRUNK WM REPLACMT IN TRANSVERSE RD 3 | 7 | CONSTRUCTION TO 75% | Feb 2024 | Jun 2024 | Mar 2015 | Mar 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-611 | TRUNK WM REPLACMT IN TRANSVERSE RD 3 | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2024 | Sep 2024 | Mar 2015 | Mar 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-611 | TRUNK WM REPLACMT IN TRANSVERSE RD 3 | 9 | SUBSTANTIAL COMPLETION | Sep 2024 | Nov 2024 | Mar 2015 | Mar 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-611 | TRUNK WM REPLACMT IN TRANSVERSE RD 3 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2024 | Dec 2024 | Mar 2015 | Mar 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-611 | TRUNK WM REPLACMT IN TRANSVERSE RD 3 | 11 | PROJECT START | Nov 2024 | Dec 2024 | Mar 2015 | Mar 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-611 | TRUNK WM REPLACMT IN TRANSVERSE RD 3 | 12 | DESIGN START | Nov 2024 | Dec 2024 | Mar 2015 | Jan 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-611 | TRUNK WM REPLACMT IN TRANSVERSE RD 3 | 13 | DESIGN COMPLETION | Nov 2024 | Dec 2024 | Jan 2022 | Jan 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-611 | TRUNK WM REPLACMT IN TRANSVERSE RD 3 | 14 | CONSTRUCTION START | Nov 2024 | Dec 2024 | Jan 2022 | Jan 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-611 | TRUNK WM REPLACMT IN TRANSVERSE RD 3 | 15 | CONSTRUCTION COMPLETION | Nov 2024 | Dec 2024 | Jan 2022 | Jun 2035
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-619 | Trunk Main replacement, b'way b/t w 93 & 97 st, Manh | 1 | DEVELOP SCOPE | Jun 2013 | Mar 2014 | Jun 2013 | Sep 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-619 | Trunk Main replacement, b'way b/t w 93 & 97 st, Manh | 2 | PRELIMINARY DESIGN | Mar 2014 | Mar 2015 | Sep 2013 | Jan 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-619 | Trunk Main replacement, b'way b/t w 93 & 97 st, Manh | 3 | FINAL DESIGN | Mar 2015 | Sep 2016 | Jan 2014 | Jul 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-619 | Trunk Main replacement, b'way b/t w 93 & 97 st, Manh | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2016 | Jun 2017 | Jul 2014 | Oct 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-619 | Trunk Main replacement, b'way b/t w 93 & 97 st, Manh | 5 | CONSTRUCTION TO 25% | Jun 2017 | Jun 2018 | Oct 2014 | Feb 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-619 | Trunk Main replacement, b'way b/t w 93 & 97 st, Manh | 6 | CONSTRUCTION TO 50% | Jun 2018 | May 2019 | Feb 2015 | Jun 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-619 | Trunk Main replacement, b'way b/t w 93 & 97 st, Manh | 7 | CONSTRUCTION TO 75% | May 2019 | May 2020 | Jun 2015 | Sep 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-619 | Trunk Main replacement, b'way b/t w 93 & 97 st, Manh | 8 | ORIGINAL EQUIP & FURNISHING | May 2020 | Feb 2021 | Oct 2015 | Dec 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-619 | Trunk Main replacement, b'way b/t w 93 & 97 st, Manh | 9 | SUBSTANTIAL COMPLETION | Feb 2021 | Aug 2021 | Dec 2015 | Feb 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-619 | Trunk Main replacement, b'way b/t w 93 & 97 st, Manh | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Nov 2021 | Feb 2016 | Jun 2033
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-645 | Distribution water main Installation, Manhattan | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-645 | Distribution water main Installation, Manhattan | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-645 | Distribution water main Installation, Manhattan | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-645 | Distribution water main Installation, Manhattan | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-645 | Distribution water main Installation, Manhattan | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-645 | Distribution water main Installation, Manhattan | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-645 | Distribution water main Installation, Manhattan | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-645 | Distribution water main Installation, Manhattan | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-645 | Distribution water main Installation, Manhattan | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-645 | Distribution water main Installation, Manhattan | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Jun 2033
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-667 | Replacement of Water main in Delancey Street (HWM2025) | 1 | DEVELOP SCOPE | Mar 2017 | Jun 2017 | Mar 2017 | Jun 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-667 | Replacement of Water main in Delancey Street (HWM2025) | 2 | PRELIMINARY DESIGN | Jun 2017 | Oct 2017 | Jun 2017 | Oct 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-667 | Replacement of Water main in Delancey Street (HWM2025) | 3 | FINAL DESIGN | Oct 2017 | Apr 2018 | Oct 2017 | Apr 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-667 | Replacement of Water main in Delancey Street (HWM2025) | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2018 | Jul 2018 | Apr 2018 | Jul 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-667 | Replacement of Water main in Delancey Street (HWM2025) | 5 | CONSTRUCTION TO 25% | Jul 2018 | Nov 2018 | Jul 2018 | Nov 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-667 | Replacement of Water main in Delancey Street (HWM2025) | 6 | CONSTRUCTION TO 50% | Nov 2018 | Mar 2019 | Nov 2018 | Mar 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-667 | Replacement of Water main in Delancey Street (HWM2025) | 7 | CONSTRUCTION TO 75% | Mar 2019 | Jul 2019 | Mar 2019 | Jul 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-667 | Replacement of Water main in Delancey Street (HWM2025) | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2019 | Oct 2019 | Jul 2019 | Oct 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-667 | Replacement of Water main in Delancey Street (HWM2025) | 9 | SUBSTANTIAL COMPLETION | Oct 2019 | Dec 2019 | Oct 2019 | Dec 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-667 | Replacement of Water main in Delancey Street (HWM2025) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2025 | Dec 2019 | Jun 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED669 | Dist. WM work in 7th Ave between W 14th & W 34th Street, MN | 1 | DEVELOP SCOPE | Nov 2020 | Aug 2021 | Nov 2020 | Aug 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED669 | Dist. WM work in 7th Ave between W 14th & W 34th Street, MN | 2 | PRELIMINARY DESIGN | Aug 2021 | Jul 2022 | Aug 2021 | Jul 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED669 | Dist. WM work in 7th Ave between W 14th & W 34th Street, MN | 3 | FINAL DESIGN | Aug 2022 | Jan 2024 | Aug 2022 | Jan 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED669 | Dist. WM work in 7th Ave between W 14th & W 34th Street, MN | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2024 | Oct 2024 | Jan 2024 | Oct 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED669 | Dist. WM work in 7th Ave between W 14th & W 34th Street, MN | 5 | CONSTRUCTION TO 25% | Oct 2024 | Oct 2025 | Oct 2024 | Oct 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED669 | Dist. WM work in 7th Ave between W 14th & W 34th Street, MN | 6 | CONSTRUCTION TO 50% | Oct 2025 | Oct 2026 | Oct 2025 | Oct 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED669 | Dist. WM work in 7th Ave between W 14th & W 34th Street, MN | 7 | CONSTRUCTION TO 75% | Oct 2026 | Oct 2027 | Oct 2026 | Oct 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED669 | Dist. WM work in 7th Ave between W 14th & W 34th Street, MN | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jun 2028 | Oct 2027 | Jun 2028
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED669 | Dist. WM work in 7th Ave between W 14th & W 34th Street, MN | 9 | SUBSTANTIAL COMPLETION | Jun 2028 | Dec 2028 | Jun 2028 | Dec 2028
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED669 | Dist. WM work in 7th Ave between W 14th & W 34th Street, MN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2028 | Mar 2029 | Dec 2028 | Mar 2029
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-670 | Replacement of distriibution WM in 43rd Street, HWMME43ST | 1 | DEVELOP SCOPE | Aug 2019 | Nov 2019 | Aug 2019 | Nov 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-670 | Replacement of distriibution WM in 43rd Street, HWMME43ST | 2 | PRELIMINARY DESIGN | Nov 2019 | Mar 2020 | Nov 2019 | Mar 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-670 | Replacement of distriibution WM in 43rd Street, HWMME43ST | 3 | FINAL DESIGN | Mar 2020 | Sep 2020 | Mar 2020 | Sep 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-670 | Replacement of distriibution WM in 43rd Street, HWMME43ST | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2020 | Dec 2020 | Sep 2020 | Dec 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-670 | Replacement of distriibution WM in 43rd Street, HWMME43ST | 5 | CONSTRUCTION TO 25% | Dec 2020 | Apr 2021 | Dec 2020 | Apr 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-670 | Replacement of distriibution WM in 43rd Street, HWMME43ST | 6 | CONSTRUCTION TO 50% | Apr 2021 | Aug 2021 | Apr 2021 | Aug 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-670 | Replacement of distriibution WM in 43rd Street, HWMME43ST | 7 | CONSTRUCTION TO 75% | Aug 2021 | Dec 2021 | Aug 2021 | Dec 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-670 | Replacement of distriibution WM in 43rd Street, HWMME43ST | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2021 | Mar 2022 | Dec 2021 | Mar 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-670 | Replacement of distriibution WM in 43rd Street, HWMME43ST | 9 | SUBSTANTIAL COMPLETION | Mar 2022 | May 2022 | Mar 2022 | May 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-670 | Replacement of distriibution WM in 43rd Street, HWMME43ST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2022 | Jun 2022 | May 2022 | Jun 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED673 | WM Rplcmt in 79 ST fr Henry Hudson Pkwy to FDR, MN HWM100SNC | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED673 | WM Rplcmt in 79 ST fr Henry Hudson Pkwy to FDR, MN HWM100SNC | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED673 | WM Rplcmt in 79 ST fr Henry Hudson Pkwy to FDR, MN HWM100SNC | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED673 | WM Rplcmt in 79 ST fr Henry Hudson Pkwy to FDR, MN HWM100SNC | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED673 | WM Rplcmt in 79 ST fr Henry Hudson Pkwy to FDR, MN HWM100SNC | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED673 | WM Rplcmt in 79 ST fr Henry Hudson Pkwy to FDR, MN HWM100SNC | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED673 | WM Rplcmt in 79 ST fr Henry Hudson Pkwy to FDR, MN HWM100SNC | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED673 | WM Rplcmt in 79 ST fr Henry Hudson Pkwy to FDR, MN HWM100SNC | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED673 | WM Rplcmt in 79 ST fr Henry Hudson Pkwy to FDR, MN HWM100SNC | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED673 | WM Rplcmt in 79 ST fr Henry Hudson Pkwy to FDR, MN HWM100SNC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Feb 2027 | Mar 2025 | Feb 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED674 | Water Main and trunk main installin Broadway MN | 1 | DEVELOP SCOPE | Sep 2021 | Dec 2021 | Sep 2021 | Dec 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED674 | Water Main and trunk main installin Broadway MN | 2 | PRELIMINARY DESIGN | Dec 2021 | Mar 2022 | Dec 2021 | Mar 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED674 | Water Main and trunk main installin Broadway MN | 3 | FINAL DESIGN | Apr 2022 | Sep 2022 | Apr 2022 | Sep 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED674 | Water Main and trunk main installin Broadway MN | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED674 | Water Main and trunk main installin Broadway MN | 5 | CONSTRUCTION TO 25% | Dec 2022 | Apr 2023 | Dec 2022 | Apr 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED674 | Water Main and trunk main installin Broadway MN | 6 | CONSTRUCTION TO 50% | Apr 2023 | Aug 2023 | Apr 2023 | Aug 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED674 | Water Main and trunk main installin Broadway MN | 7 | CONSTRUCTION TO 75% | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED674 | Water Main and trunk main installin Broadway MN | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2023 | Mar 2024 | Dec 2023 | Mar 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED674 | Water Main and trunk main installin Broadway MN | 9 | SUBSTANTIAL COMPLETION | Mar 2024 | May 2024 | Mar 2024 | May 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED674 | Water Main and trunk main installin Broadway MN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Jun 2024 | May 2024 | Jun 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED674 | Water Main and trunk main installin Broadway MN | 11 | PROJECT START | May 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED674 | Water Main and trunk main installin Broadway MN | 12 | DESIGN START | May 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED674 | Water Main and trunk main installin Broadway MN | 13 | DESIGN COMPLETION | May 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED674 | Water Main and trunk main installin Broadway MN | 14 | CONSTRUCTION START | May 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED674 | Water Main and trunk main installin Broadway MN | 15 | CONSTRUCTION COMPLETION | May 2024 | Jun 2024 | Jun 2024 | Jun 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED678 | WM Rplmt Lexington Av btwn E 45 & E 49 St, MN HWMMLEXAV-DB | 1 | DEVELOP SCOPE | Jan 2024 | Mar 2024 | Jan 2022 | Mar 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED678 | WM Rplmt Lexington Av btwn E 45 & E 49 St, MN HWMMLEXAV-DB | 2 | PRELIMINARY DESIGN | Mar 2024 | Jul 2024 | Mar 2022 | Jul 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED678 | WM Rplmt Lexington Av btwn E 45 & E 49 St, MN HWMMLEXAV-DB | 3 | FINAL DESIGN | Jul 2024 | Jan 2025 | Jul 2022 | Jan 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED678 | WM Rplmt Lexington Av btwn E 45 & E 49 St, MN HWMMLEXAV-DB | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2025 | Apr 2025 | Jan 2023 | Apr 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED678 | WM Rplmt Lexington Av btwn E 45 & E 49 St, MN HWMMLEXAV-DB | 5 | CONSTRUCTION TO 25% | Apr 2025 | Aug 2025 | Apr 2023 | Aug 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED678 | WM Rplmt Lexington Av btwn E 45 & E 49 St, MN HWMMLEXAV-DB | 6 | CONSTRUCTION TO 50% | Aug 2025 | Dec 2025 | Aug 2023 | Dec 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED678 | WM Rplmt Lexington Av btwn E 45 & E 49 St, MN HWMMLEXAV-DB | 7 | CONSTRUCTION TO 75% | Dec 2025 | Apr 2026 | Dec 2023 | Apr 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED678 | WM Rplmt Lexington Av btwn E 45 & E 49 St, MN HWMMLEXAV-DB | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2026 | Jul 2026 | Apr 2024 | Jul 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED678 | WM Rplmt Lexington Av btwn E 45 & E 49 St, MN HWMMLEXAV-DB | 9 | SUBSTANTIAL COMPLETION | Jul 2026 | Sep 2026 | Jul 2024 | Sep 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED678 | WM Rplmt Lexington Av btwn E 45 & E 49 St, MN HWMMLEXAV-DB | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Oct 2026 | Sep 2024 | Oct 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED679 | Dist WM & SE Rpl work- W. 42nd St btwn 7 & 8 Av,MN, HWM42PSM | 1 | DEVELOP SCOPE | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED679 | Dist WM & SE Rpl work- W. 42nd St btwn 7 & 8 Av,MN, HWM42PSM | 2 | PRELIMINARY DESIGN | Apr 2026 | Jul 2026 | Apr 2026 | Jul 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED679 | Dist WM & SE Rpl work- W. 42nd St btwn 7 & 8 Av,MN, HWM42PSM | 3 | FINAL DESIGN | Jul 2026 | Jan 2027 | Jul 2026 | Jan 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED679 | Dist WM & SE Rpl work- W. 42nd St btwn 7 & 8 Av,MN, HWM42PSM | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2027 | Apr 2027 | Jan 2027 | Apr 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED679 | Dist WM & SE Rpl work- W. 42nd St btwn 7 & 8 Av,MN, HWM42PSM | 5 | CONSTRUCTION TO 25% | Apr 2027 | Aug 2027 | Apr 2027 | Aug 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED679 | Dist WM & SE Rpl work- W. 42nd St btwn 7 & 8 Av,MN, HWM42PSM | 6 | CONSTRUCTION TO 50% | Aug 2027 | Dec 2027 | Aug 2027 | Dec 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED679 | Dist WM & SE Rpl work- W. 42nd St btwn 7 & 8 Av,MN, HWM42PSM | 7 | CONSTRUCTION TO 75% | Dec 2027 | Apr 2028 | Dec 2027 | Apr 2028
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED679 | Dist WM & SE Rpl work- W. 42nd St btwn 7 & 8 Av,MN, HWM42PSM | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2028 | Jul 2028 | Apr 2028 | Jul 2028
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED679 | Dist WM & SE Rpl work- W. 42nd St btwn 7 & 8 Av,MN, HWM42PSM | 9 | SUBSTANTIAL COMPLETION | Jul 2028 | Sep 2028 | Jul 2028 | Sep 2028
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED679 | Dist WM & SE Rpl work- W. 42nd St btwn 7 & 8 Av,MN, HWM42PSM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2028 | Oct 2028 | Sep 2028 | Oct 2028
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED682 | WM work in Central Park W btwn W 81 & 85 Streets, MN | 1 | DEVELOP SCOPE | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED682 | WM work in Central Park W btwn W 81 & 85 Streets, MN | 2 | PRELIMINARY DESIGN | Apr 2025 | Jul 2025 | Apr 2025 | Jul 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED682 | WM work in Central Park W btwn W 81 & 85 Streets, MN | 3 | FINAL DESIGN | Jul 2025 | Jan 2026 | Jul 2025 | Jan 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED682 | WM work in Central Park W btwn W 81 & 85 Streets, MN | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2026 | Apr 2026 | Jan 2026 | Apr 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED682 | WM work in Central Park W btwn W 81 & 85 Streets, MN | 5 | CONSTRUCTION TO 25% | Apr 2026 | Aug 2026 | Apr 2026 | Aug 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED682 | WM work in Central Park W btwn W 81 & 85 Streets, MN | 6 | CONSTRUCTION TO 50% | Aug 2026 | Dec 2026 | Aug 2026 | Dec 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED682 | WM work in Central Park W btwn W 81 & 85 Streets, MN | 7 | CONSTRUCTION TO 75% | Dec 2026 | Apr 2027 | Dec 2026 | Apr 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED682 | WM work in Central Park W btwn W 81 & 85 Streets, MN | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2027 | Jul 2027 | Apr 2027 | Jul 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED682 | WM work in Central Park W btwn W 81 & 85 Streets, MN | 9 | SUBSTANTIAL COMPLETION | Jul 2027 | Sep 2027 | Jul 2027 | Sep 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED682 | WM work in Central Park W btwn W 81 & 85 Streets, MN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Oct 2027 | Sep 2027 | Oct 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED683 | Dist Trunk WM Rplmt at BDWY & W 135 St, Manhattan, HWCSCHPMN | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED683 | Dist Trunk WM Rplmt at BDWY & W 135 St, Manhattan, HWCSCHPMN | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED683 | Dist Trunk WM Rplmt at BDWY & W 135 St, Manhattan, HWCSCHPMN | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED683 | Dist Trunk WM Rplmt at BDWY & W 135 St, Manhattan, HWCSCHPMN | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED683 | Dist Trunk WM Rplmt at BDWY & W 135 St, Manhattan, HWCSCHPMN | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED683 | Dist Trunk WM Rplmt at BDWY & W 135 St, Manhattan, HWCSCHPMN | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED683 | Dist Trunk WM Rplmt at BDWY & W 135 St, Manhattan, HWCSCHPMN | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | May 2024 | Sep 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED683 | Dist Trunk WM Rplmt at BDWY & W 135 St, Manhattan, HWCSCHPMN | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED683 | Dist Trunk WM Rplmt at BDWY & W 135 St, Manhattan, HWCSCHPMN | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Dec 2024 | Feb 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED683 | Dist Trunk WM Rplmt at BDWY & W 135 St, Manhattan, HWCSCHPMN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Mar 2025 | Feb 2025 | Mar 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MEDA-002 | Accelerated Distribution WM replcmnt & sewer rebhab - MAN | 1 | DEVELOP SCOPE | Oct 2014 | Jan 2015 | Oct 2014 | Jan 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MEDA-002 | Accelerated Distribution WM replcmnt & sewer rebhab - MAN | 2 | PRELIMINARY DESIGN | Jan 2015 | May 2015 | Jan 2015 | May 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MEDA-002 | Accelerated Distribution WM replcmnt & sewer rebhab - MAN | 3 | FINAL DESIGN | May 2015 | Nov 2015 | May 2015 | Nov 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MEDA-002 | Accelerated Distribution WM replcmnt & sewer rebhab - MAN | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2015 | Feb 2016 | Nov 2015 | Feb 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MEDA-002 | Accelerated Distribution WM replcmnt & sewer rebhab - MAN | 5 | CONSTRUCTION TO 25% | Feb 2016 | May 2016 | Feb 2016 | May 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MEDA-002 | Accelerated Distribution WM replcmnt & sewer rebhab - MAN | 6 | CONSTRUCTION TO 50% | Jun 2016 | Sep 2016 | Jun 2016 | Sep 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MEDA-002 | Accelerated Distribution WM replcmnt & sewer rebhab - MAN | 7 | CONSTRUCTION TO 75% | Sep 2016 | Jan 2017 | Sep 2016 | Jan 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MEDA-002 | Accelerated Distribution WM replcmnt & sewer rebhab - MAN | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2017 | Apr 2017 | Jan 2017 | Apr 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MEDA-002 | Accelerated Distribution WM replcmnt & sewer rebhab - MAN | 9 | SUBSTANTIAL COMPLETION | Apr 2017 | Jun 2017 | Apr 2017 | Jun 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MEDA-002 | Accelerated Distribution WM replcmnt & sewer rebhab - MAN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2017 | Jul 2017 | Jun 2017 | Mar 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MURPHCOMF | Murphy's Brother Playground Comfort Station DESIGN BUILD | 1 | PROJECT START | Aug 2023 | Aug 2023 | Aug 2023 | Aug 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MURPHCOMF | Murphy's Brother Playground Comfort Station DESIGN BUILD | 2 | DESIGN START | Aug 2023 | Aug 2023 | Aug 2023 | Aug 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MURPHCOMF | Murphy's Brother Playground Comfort Station DESIGN BUILD | 3 | DESIGN COMPLETION | Aug 2023 | Aug 2023 | Aug 2023 | Aug 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MURPHCOMF | Murphy's Brother Playground Comfort Station DESIGN BUILD | 4 | CONSTRUCTION START | Aug 2023 | Aug 2023 | Aug 2023 | Aug 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MURPHCOMF | Murphy's Brother Playground Comfort Station DESIGN BUILD | 5 | CONSTRUCTION COMPLETION | Aug 2023 | Aug 2026 | Aug 2023 | Aug 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-303ERPK | East River Park | 1 | PROJECT START | Mar 2018 | Mar 2018 | Nov 2007 | Nov 2007
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-303ERPK | East River Park | 2 | DESIGN START | Mar 2018 | Mar 2018 | Nov 2007 | Nov 2007
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-303ERPK | East River Park | 3 | DESIGN COMPLETION | Mar 2018 | Mar 2018 | Nov 2007 | Nov 2007
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-303ERPK | East River Park | 4 | CONSTRUCTION START | Mar 2018 | Mar 2018 | Nov 2007 | Nov 2007
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-303ERPK | East River Park | 5 | CONSTRUCTION COMPLETION | Mar 2018 | Mar 2018 | Nov 2007 | Apr 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-308RPCS | Ruppert Park PRB | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-308RPCS | Ruppert Park PRB | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-308RPCS | Ruppert Park PRB | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-308RPCS | Ruppert Park PRB | 4 | CONSTRUCTION | Sep 2024 | Mar 2026 | Sep 2024 | Mar 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-308RPCS | Ruppert Park PRB | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Mar 2027 | Mar 2026 | Mar 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-3RANDAL | Randall's Island Infrastructure, Roadways, Drainage, & CS | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Dec 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-3RANDAL | Randall's Island Infrastructure, Roadways, Drainage, & CS | 2 | DESIGN | Sep 2015 | Dec 2015 | Dec 2015 | Mar 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-3RANDAL | Randall's Island Infrastructure, Roadways, Drainage, & CS | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Mar 2017 | Dec 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-3RANDAL | Randall's Island Infrastructure, Roadways, Drainage, & CS | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Dec 2017 | Dec 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-3RANDAL | Randall's Island Infrastructure, Roadways, Drainage, & CS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Dec 2018 | Jun 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHQ | ONE POLICE PLAZA PAVING AND LANDSCAPING | 1 | PROJECT START | Nov 2013 | Nov 2013 | Nov 2013 | Nov 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHQ | ONE POLICE PLAZA PAVING AND LANDSCAPING | 2 | DESIGN START | Nov 2013 | May 2014 | Nov 2013 | May 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHQ | ONE POLICE PLAZA PAVING AND LANDSCAPING | 3 | DESIGN COMPLETION | May 2014 | Jul 2015 | May 2014 | Jul 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHQ | ONE POLICE PLAZA PAVING AND LANDSCAPING | 4 | CONSTRUCTION START | Jul 2015 | Nov 2015 | Jul 2015 | Nov 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHQ | ONE POLICE PLAZA PAVING AND LANDSCAPING | 5 | CONSTRUCTION COMPLETION | Nov 2015 | Mar 2017 | Nov 2015 | Jun 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | 1 | DEVELOP SCOPE | Dec 2017 | Mar 2018 | Dec 2017 | Mar 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | 2 | PRELIMINARY DESIGN | Mar 2018 | Jul 2018 | Mar 2018 | May 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | 3 | FINAL DESIGN | Jul 2018 | Nov 2018 | May 2019 | Mar 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2018 | May 2019 | Mar 2021 | Nov 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | 5 | CONSTRUCTION TO 25% | May 2019 | Sep 2019 | Dec 2021 | Mar 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | 6 | CONSTRUCTION TO 50% | Sep 2019 | Jan 2020 | Mar 2022 | Jul 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | 7 | CONSTRUCTION TO 75% | Jan 2020 | May 2020 | Jul 2022 | Jun 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | 8 | ORIGINAL EQUIP & FURNISHING | May 2020 | Aug 2020 | Jul 2026 | Jul 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | 9 | SUBSTANTIAL COMPLETION | Aug 2020 | Oct 2020 | Jul 2026 | Dec 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2020 | Nov 2020 | Dec 2026 | Dec 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | 11 | PROJECT START | Oct 2020 | Nov 2020 | Dec 2027 | Dec 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | 12 | DESIGN START | Oct 2020 | Nov 2020 | Dec 2027 | Dec 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | 13 | DESIGN COMPLETION | Oct 2020 | Nov 2020 | Dec 2027 | Dec 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | 14 | CONSTRUCTION START | Oct 2020 | Nov 2020 | Dec 2027 | Dec 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | 15 | CONSTRUCTION COMPLETION | Oct 2020 | Nov 2020 | Dec 2027 | Dec 2032
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV022-SKY | MMA - Metropolitan Museum Skylight Replacement for A, B, C W | 1 | DEVELOP SCOPE | Apr 2022 | Jul 2022 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV022-SKY | MMA - Metropolitan Museum Skylight Replacement for A, B, C W | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Sep 2022 | Dec 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV022-SKY | MMA - Metropolitan Museum Skylight Replacement for A, B, C W | 3 | CONSTRUCTION TO 50% | Oct 2022 | Jan 2023 | Dec 2022 | Apr 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV022-SKY | MMA - Metropolitan Museum Skylight Replacement for A, B, C W | 4 | CONSTRUCTION TO 75% | Feb 2023 | Apr 2023 | Apr 2023 | Jun 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV022-SKY | MMA - Metropolitan Museum Skylight Replacement for A, B, C W | 5 | SUBSTANTIAL COMPLETION | Apr 2023 | May 2023 | Jun 2023 | Aug 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV022-SKY | MMA - Metropolitan Museum Skylight Replacement for A, B, C W | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2023 | Jun 2023 | Aug 2023 | Sep 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV022-SKY | MMA - Metropolitan Museum Skylight Replacement for A, B, C W | 7 | PROJECT START | Jun 2023 | Jun 2023 | Sep 2023 | Sep 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV022-SKY | MMA - Metropolitan Museum Skylight Replacement for A, B, C W | 8 | DESIGN START | Jun 2023 | Jun 2023 | Sep 2023 | Sep 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV022-SKY | MMA - Metropolitan Museum Skylight Replacement for A, B, C W | 9 | DESIGN COMPLETION | Jun 2023 | Jun 2023 | Sep 2023 | Sep 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV022-SKY | MMA - Metropolitan Museum Skylight Replacement for A, B, C W | 10 | CONSTRUCTION START | Jun 2023 | Jun 2023 | Sep 2023 | Sep 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV022-SKY | MMA - Metropolitan Museum Skylight Replacement for A, B, C W | 11 | CONSTRUCTION COMPLETION | Jun 2023 | Jun 2023 | Sep 2023 | Sep 2029
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | 1 | DEVELOP SCOPE | Oct 2010 | Jan 2011 | Oct 2016 | Jan 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | 2 | PRELIMINARY DESIGN | Jan 2011 | May 2011 | Jan 2017 | May 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | 3 | FINAL DESIGN | May 2011 | Nov 2011 | May 2017 | Nov 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2011 | Feb 2012 | Nov 2017 | Feb 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | 5 | CONSTRUCTION TO 25% | Feb 2012 | Jun 2012 | Feb 2018 | Jun 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | 6 | CONSTRUCTION TO 50% | Jun 2012 | Oct 2012 | Jun 2018 | Oct 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | 7 | CONSTRUCTION TO 75% | Oct 2012 | Feb 2013 | Oct 2018 | Feb 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2013 | May 2013 | Feb 2019 | May 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | 9 | SUBSTANTIAL COMPLETION | May 2013 | Jul 2013 | May 2019 | Jul 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2013 | Aug 2013 | Jul 2019 | Jun 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | 11 | PROJECT START | Jul 2013 | Aug 2013 | Jul 2022 | Jul 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | 12 | DESIGN START | Jul 2013 | Aug 2013 | Jul 2022 | Jul 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | 13 | DESIGN COMPLETION | Jul 2013 | Aug 2013 | Jul 2022 | Jul 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | 14 | CONSTRUCTION START | Jul 2013 | Aug 2013 | Jul 2022 | Jul 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | 15 | CONSTRUCTION COMPLETION | Jul 2013 | Aug 2013 | Jul 2022 | Jul 2032
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV241EXTR | MCNY - Exterior Facade Rehabilitation | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Nov 2016 | Nov 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV241EXTR | MCNY - Exterior Facade Rehabilitation | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Nov 2016 | Aug 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV241EXTR | MCNY - Exterior Facade Rehabilitation | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Aug 2018 | Oct 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV241EXTR | MCNY - Exterior Facade Rehabilitation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Oct 2019 | Oct 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV241EXTR | MCNY - Exterior Facade Rehabilitation | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Oct 2020 | Dec 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV241EXTR | MCNY - Exterior Facade Rehabilitation | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Oct 2020 | Dec 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV241EXTR | MCNY - Exterior Facade Rehabilitation | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Oct 2020 | Dec 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV241EXTR | MCNY - Exterior Facade Rehabilitation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | Oct 2020 | Dec 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV241EXTR | MCNY - Exterior Facade Rehabilitation | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Oct 2020 | Dec 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV241EXTR | MCNY - Exterior Facade Rehabilitation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Oct 2020 | Dec 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV289-DEL | NYSF - DELACORTE Theater Renovation | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2024 | Sep 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV289-DEL | NYSF - DELACORTE Theater Renovation | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2022 | Dec 2022 | Sep 2024 | Dec 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV289-DEL | NYSF - DELACORTE Theater Renovation | 3 | CONSTRUCTION TO 50% | Dec 2022 | Apr 2023 | Dec 2024 | Apr 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV289-DEL | NYSF - DELACORTE Theater Renovation | 4 | CONSTRUCTION TO 75% | Apr 2023 | Jun 2023 | Apr 2025 | Jun 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV289-DEL | NYSF - DELACORTE Theater Renovation | 5 | SUBSTANTIAL COMPLETION | Jun 2023 | Aug 2023 | Jun 2025 | Aug 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV289-DEL | NYSF - DELACORTE Theater Renovation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2023 | Sep 2023 | Aug 2025 | Sep 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV475ROOF | NYST - NYC Ballet Roof Replacement | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | May 2021 | Aug 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV475ROOF | NYST - NYC Ballet Roof Replacement | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Aug 2021 | Dec 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV475ROOF | NYST - NYC Ballet Roof Replacement | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Dec 2021 | Jun 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV475ROOF | NYST - NYC Ballet Roof Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV475ROOF | NYST - NYC Ballet Roof Replacement | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV475ROOF | NYST - NYC Ballet Roof Replacement | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Jan 2023 | May 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV475ROOF | NYST - NYC Ballet Roof Replacement | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | May 2023 | Sep 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV475ROOF | NYST - NYC Ballet Roof Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Sep 2023 | Dec 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV475ROOF | NYST - NYC Ballet Roof Replacement | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Dec 2023 | Feb 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV475ROOF | NYST - NYC Ballet Roof Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Feb 2024 | Mar 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV475ROOF | NYST - NYC Ballet Roof Replacement | 11 | PROJECT START | Mar 2026 | Apr 2026 | Mar 2024 | Mar 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV475ROOF | NYST - NYC Ballet Roof Replacement | 12 | DESIGN START | Mar 2026 | Apr 2026 | Mar 2024 | Mar 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV475ROOF | NYST - NYC Ballet Roof Replacement | 13 | DESIGN COMPLETION | Mar 2026 | Apr 2026 | Mar 2024 | Mar 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV475ROOF | NYST - NYC Ballet Roof Replacement | 14 | CONSTRUCTION START | Mar 2026 | Apr 2026 | Mar 2024 | Mar 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV475ROOF | NYST - NYC Ballet Roof Replacement | 15 | CONSTRUCTION COMPLETION | Mar 2026 | Apr 2026 | Mar 2024 | Mar 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV503ELEV | CH- Carnegie Hall Elevators | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV503ELEV | CH- Carnegie Hall Elevators | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV503ELEV | CH- Carnegie Hall Elevators | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2023 | Jul 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV503ELEV | CH- Carnegie Hall Elevators | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2023 | Oct 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV503ELEV | CH- Carnegie Hall Elevators | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2023 | Feb 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV503ELEV | CH- Carnegie Hall Elevators | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2024 | Jun 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV503ELEV | CH- Carnegie Hall Elevators | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2024 | Oct 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV503ELEV | CH- Carnegie Hall Elevators | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2024 | Jan 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV503ELEV | CH- Carnegie Hall Elevators | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2025 | Mar 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV503ELEV | CH- Carnegie Hall Elevators | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2025 | Apr 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV788-FAC | 122C - 122 CC Facade Reconstruction | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV788-FAC | 122C - 122 CC Facade Reconstruction | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV788-FAC | 122C - 122 CC Facade Reconstruction | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV788-FAC | 122C - 122 CC Facade Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV788-FAC | 122C - 122 CC Facade Reconstruction | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV788-FAC | 122C - 122 CC Facade Reconstruction | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV788-FAC | 122C - 122 CC Facade Reconstruction | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV788-FAC | 122C - 122 CC Facade Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV788-FAC | 122C - 122 CC Facade Reconstruction | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2023 | Mar 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV788-FAC | 122C - 122 CC Facade Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2023 | Apr 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV788-FAC | 122C - 122 CC Facade Reconstruction | 11 | PROJECT START | Mar 2023 | Apr 2023 | Apr 2024 | Apr 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV788-FAC | 122C - 122 CC Facade Reconstruction | 12 | DESIGN START | Mar 2023 | Apr 2023 | Apr 2024 | Apr 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV788-FAC | 122C - 122 CC Facade Reconstruction | 13 | DESIGN COMPLETION | Mar 2023 | Apr 2023 | Apr 2024 | Apr 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV788-FAC | 122C - 122 CC Facade Reconstruction | 14 | CONSTRUCTION START | Mar 2023 | Apr 2023 | Apr 2024 | Apr 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV788-FAC | 122C - 122 CC Facade Reconstruction | 15 | CONSTRUCTION COMPLETION | Mar 2023 | Apr 2023 | Apr 2024 | Apr 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW195SW2 | 80 CENTRE ST. - SIDEWALK REHABILITATION | 1 | PROJECT START | Mar 2014 | Mar 2014 | Mar 2012 | Mar 2012
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW195SW2 | 80 CENTRE ST. - SIDEWALK REHABILITATION | 2 | DESIGN START | Mar 2014 | Dec 2014 | Mar 2012 | Dec 2012
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW195SW2 | 80 CENTRE ST. - SIDEWALK REHABILITATION | 3 | DESIGN COMPLETION | Dec 2014 | Dec 2015 | Dec 2012 | Dec 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW195SW2 | 80 CENTRE ST. - SIDEWALK REHABILITATION | 4 | CONSTRUCTION START | Dec 2015 | May 2016 | Dec 2013 | May 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW195SW2 | 80 CENTRE ST. - SIDEWALK REHABILITATION | 5 | CONSTRUCTION COMPLETION | May 2016 | Mar 2017 | Jul 2015 | Jul 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW29380FC | 80 CENTRE ST.- FIRE ALARMS/SPRINKLERS | 1 | PROJECT START | Aug 2019 | Aug 2019 | Aug 2019 | Aug 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW29380FC | 80 CENTRE ST.- FIRE ALARMS/SPRINKLERS | 2 | DESIGN START | Aug 2019 | Aug 2020 | Aug 2019 | Aug 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW29380FC | 80 CENTRE ST.- FIRE ALARMS/SPRINKLERS | 3 | DESIGN COMPLETION | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW29380FC | 80 CENTRE ST.- FIRE ALARMS/SPRINKLERS | 4 | CONSTRUCTION START | Aug 2021 | May 2022 | Aug 2021 | May 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW29380FC | 80 CENTRE ST.- FIRE ALARMS/SPRINKLERS | 5 | CONSTRUCTION COMPLETION | May 2022 | May 2024 | May 2022 | May 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW3171C | 1 CENTRE STREET- FACADE REHAB | 1 | PROJECT START | Jun 2016 | Jun 2016 | Dec 2020 | Dec 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW3171C | 1 CENTRE STREET- FACADE REHAB | 2 | DESIGN START | Jul 2016 | Nov 2016 | Dec 2020 | Feb 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW3171C | 1 CENTRE STREET- FACADE REHAB | 3 | DESIGN COMPLETION | Nov 2016 | Feb 2017 | Mar 2021 | Feb 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW3171C | 1 CENTRE STREET- FACADE REHAB | 4 | CONSTRUCTION START | Feb 2017 | Sep 2017 | Mar 2022 | Nov 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW3171C | 1 CENTRE STREET- FACADE REHAB | 5 | CONSTRUCTION COMPLETION | Oct 2017 | Oct 2021 | Nov 2022 | Aug 2032
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW3172L | 2 LAFAYETTE STREET - FACADE REPAIRS | 1 | PROJECT START | Jun 2016 | Jun 2016 | Jun 2016 | Jun 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW3172L | 2 LAFAYETTE STREET - FACADE REPAIRS | 2 | DESIGN START | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW3172L | 2 LAFAYETTE STREET - FACADE REPAIRS | 3 | DESIGN COMPLETION | Dec 2016 | Apr 2017 | Dec 2016 | Apr 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW3172L | 2 LAFAYETTE STREET - FACADE REPAIRS | 4 | CONSTRUCTION START | May 2017 | Nov 2017 | May 2017 | Nov 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW3172L | 2 LAFAYETTE STREET - FACADE REPAIRS | 5 | CONSTRUCTION COMPLETION | Dec 2017 | Dec 2025 | Dec 2017 | Dec 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357ELEV | 253 BROADWAY- ELEVATOR MODERNIZATION | 1 | PROJECT START | Jun 2012 | Aug 2012 | Dec 2013 | Dec 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357ELEV | 253 BROADWAY- ELEVATOR MODERNIZATION | 2 | DESIGN START | Aug 2012 | Dec 2012 | May 2014 | May 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357ELEV | 253 BROADWAY- ELEVATOR MODERNIZATION | 3 | FINAL DESIGN | Dec 2012 | Jun 2013 | Jan 2015 | Jan 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357ELEV | 253 BROADWAY- ELEVATOR MODERNIZATION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2013 | Sep 2013 | Jul 2016 | Jul 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357ELEV | 253 BROADWAY- ELEVATOR MODERNIZATION | 5 | CONSTRUCTION TO 25% | Sep 2013 | Jan 2014 | Sep 2017 | Sep 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357ELEV | 253 BROADWAY- ELEVATOR MODERNIZATION | 6 | CONSTRUCTION TO 50% | Jan 2014 | May 2014 | Sep 2017 | Sep 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357ELEV | 253 BROADWAY- ELEVATOR MODERNIZATION | 7 | CONSTRUCTION TO 75% | May 2014 | Sep 2014 | Sep 2017 | Sep 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357ELEV | 253 BROADWAY- ELEVATOR MODERNIZATION | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2014 | Dec 2014 | Sep 2017 | Sep 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357ELEV | 253 BROADWAY- ELEVATOR MODERNIZATION | 9 | SUBSTANTIAL COMPLETION | Dec 2014 | Feb 2015 | Sep 2017 | Sep 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357ELEV | 253 BROADWAY- ELEVATOR MODERNIZATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2015 | Mar 2015 | Sep 2017 | Sep 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | 1 | DEVELOP SCOPE | Jun 2011 | Aug 2011 | Nov 2016 | Nov 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | 2 | PRELIMINARY DESIGN | Aug 2011 | Dec 2011 | Nov 2016 | Nov 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | 3 | FINAL DESIGN | Dec 2011 | Jun 2012 | Nov 2018 | Jan 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2012 | Sep 2012 | Feb 2020 | Apr 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | 5 | CONSTRUCTION TO 25% | Sep 2012 | Jan 2013 | May 2020 | Aug 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | 6 | CONSTRUCTION TO 50% | Jan 2013 | May 2013 | Aug 2020 | Dec 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | 7 | CONSTRUCTION TO 75% | May 2013 | Sep 2013 | Dec 2020 | Apr 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2013 | Dec 2013 | Apr 2021 | Jul 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | Dec 2013 | Feb 2014 | Jul 2021 | Sep 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2014 | Mar 2014 | Sep 2021 | Jul 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | 11 | PROJECT START | Feb 2014 | Mar 2014 | Aug 2023 | Aug 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | 12 | DESIGN START | Feb 2014 | Mar 2014 | Aug 2023 | Aug 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | 13 | DESIGN COMPLETION | Feb 2014 | Mar 2014 | Aug 2023 | Aug 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | 14 | CONSTRUCTION START | Feb 2014 | Mar 2014 | Aug 2023 | Aug 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | 15 | CONSTRUCTION COMPLETION | Feb 2014 | Mar 2014 | Aug 2023 | Aug 2032
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357MOCS | 253 BROADWAY- 9TH FLOOR REHABILITATION OF MOCS SPACE | 4 | CONSTRUCTION START | Sep 2013 | Sep 2013 | Sep 2013 | Sep 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357MOCS | 253 BROADWAY- 9TH FLOOR REHABILITATION OF MOCS SPACE | 5 | CONSTRUCTION COMPLETION | Dec 2013 | Dec 2013 | Dec 2013 | Dec 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77102S3 | CITY HALL STEPS RECONSTRUCTION | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Aug 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77102S3 | CITY HALL STEPS RECONSTRUCTION | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77102S3 | CITY HALL STEPS RECONSTRUCTION | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77102S3 | CITY HALL STEPS RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77102S3 | CITY HALL STEPS RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77102S3 | CITY HALL STEPS RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2022 | May 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77102S3 | CITY HALL STEPS RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2022 | Sep 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77102S3 | CITY HALL STEPS RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77102S3 | CITY HALL STEPS RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2022 | Feb 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77102S3 | CITY HALL STEPS RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2025 | Feb 2023 | Mar 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW7722R | 22 READE STREET EXTERIOR | 1 | PROJECT START | Jun 2016 | Jun 2016 | Jun 2016 | Jun 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW7722R | 22 READE STREET EXTERIOR | 2 | DESIGN START | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW7722R | 22 READE STREET EXTERIOR | 3 | DESIGN COMPLETION | Dec 2016 | Apr 2017 | Dec 2016 | Apr 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW7722R | 22 READE STREET EXTERIOR | 4 | CONSTRUCTION START | Apr 2017 | Nov 2017 | Apr 2017 | Nov 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW7722R | 22 READE STREET EXTERIOR | 5 | CONSTRUCTION COMPLETION | Dec 2017 | Dec 2024 | Dec 2017 | Dec 2032
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | 1 | DEVELOP SCOPE | Oct 2012 | Oct 2012 | Oct 2016 | Oct 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | 2 | PRELIMINARY DESIGN | Oct 2012 | Oct 2012 | Oct 2016 | Oct 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | 3 | FINAL DESIGN | Oct 2012 | Oct 2012 | Oct 2016 | Oct 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2012 | Oct 2012 | Oct 2016 | Oct 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | 5 | CONSTRUCTION TO 25% | Oct 2012 | Oct 2012 | Oct 2016 | Oct 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | 6 | CONSTRUCTION TO 50% | Oct 2012 | Oct 2012 | Oct 2016 | Oct 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | 7 | CONSTRUCTION TO 75% | Oct 2012 | Oct 2012 | Oct 2016 | Oct 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2012 | Oct 2012 | Oct 2016 | Oct 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | 9 | SUBSTANTIAL COMPLETION | Oct 2012 | Oct 2012 | Oct 2016 | Oct 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2012 | Dec 2015 | Oct 2016 | Oct 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | 11 | PROJECT START | Oct 2012 | Dec 2015 | Oct 2016 | Oct 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | 12 | DESIGN START | Oct 2012 | Dec 2015 | Oct 2016 | Oct 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | 13 | DESIGN COMPLETION | Oct 2012 | Dec 2015 | Oct 2016 | Oct 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | 14 | CONSTRUCTION START | Oct 2012 | Dec 2015 | Oct 2016 | Oct 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | 15 | CONSTRUCTION COMPLETION | Oct 2012 | Dec 2015 | Oct 2016 | Jul 2025
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77LYA | 253 BROADWAY- LPC MOVE TO 2nd, 11th, 12th, 13th FLS | 1 | PROJECT START | Jun 2012 | Jun 2012 | Jun 2014 | Jun 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77LYA | 253 BROADWAY- LPC MOVE TO 2nd, 11th, 12th, 13th FLS | 2 | DESIGN START | Jan 2013 | Jan 2013 | Jun 2014 | Jun 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77LYA | 253 BROADWAY- LPC MOVE TO 2nd, 11th, 12th, 13th FLS | 3 | DESIGN COMPLETION | Dec 2013 | Dec 2013 | Jun 2015 | Jun 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77LYA | 253 BROADWAY- LPC MOVE TO 2nd, 11th, 12th, 13th FLS | 4 | CONSTRUCTION START | Apr 2015 | Apr 2015 | Jun 2017 | Jun 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77LYA | 253 BROADWAY- LPC MOVE TO 2nd, 11th, 12th, 13th FLS | 5 | CONSTRUCTION COMPLETION | Jun 2016 | Jun 2016 | Oct 2020 | Oct 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW80DYCD2 | 2 LAFAYETTE STREET- DYCD RELOCATION | 1 | PROJECT START | Oct 2011 | Oct 2011 | Oct 2011 | Oct 2011
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW80DYCD2 | 2 LAFAYETTE STREET- DYCD RELOCATION | 2 | DESIGN START | Jan 2012 | Jan 2012 | Jan 2012 | Jan 2012
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW80DYCD2 | 2 LAFAYETTE STREET- DYCD RELOCATION | 3 | DESIGN COMPLETION | Aug 2012 | Aug 2012 | Sep 2012 | Sep 2012
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW80DYCD2 | 2 LAFAYETTE STREET- DYCD RELOCATION | 4 | CONSTRUCTION START | Jan 2013 | Jan 2013 | Apr 2013 | Apr 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW80DYCD2 | 2 LAFAYETTE STREET- DYCD RELOCATION | 5 | CONSTRUCTION COMPLETION | Dec 2013 | Dec 2013 | Oct 2014 | Jul 2028
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD005NEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN | 1 | PROJECT START | Apr 2005 | Apr 2005 | Feb 2009 | Aug 2009
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD005NEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN | 2 | DESIGN START | Jan 2006 | Jan 2006 | Sep 2009 | Sep 2010
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD005NEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN | 3 | DESIGN COMPLETION | Jul 2006 | Jul 2006 | Jun 2011 | Jan 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD005NEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN | 4 | CONSTRUCTION START | Dec 2006 | Dec 2006 | Jan 2016 | Feb 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD005NEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN | 5 | CONSTRUCTION COMPLETION | Aug 2007 | Aug 2007 | Feb 2018 | Aug 2032
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S195-227S | Spring St Salt Enclosure | 1 | PROJECT START | Jun 2013 | Jun 2013 | Jun 2013 | Jun 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S195-227S | Spring St Salt Enclosure | 2 | DESIGN START | Jun 2013 | Jun 2013 | Jun 2013 | Jun 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S195-227S | Spring St Salt Enclosure | 3 | DESIGN COMPLETION | Jun 2013 | Jun 2013 | Jun 2013 | Apr 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S195-227S | Spring St Salt Enclosure | 4 | CONSTRUCTION START | Jun 2013 | Jun 2013 | Apr 2014 | Apr 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S195-227S | Spring St Salt Enclosure | 5 | CONSTRUCTION COMPLETION | Jun 2013 | Jun 2014 | Apr 2014 | Jun 2032
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-401A | EAST 91st ST MARINE TRANSFER STATION | 2 | DESIGN START | Sep 2011 | Sep 2012 | Sep 2011 | Sep 2012
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-401A | EAST 91st ST MARINE TRANSFER STATION | 3 | DESIGN COMPLETION | Sep 2012 | Sep 2013 | Sep 2012 | Sep 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-401A | EAST 91st ST MARINE TRANSFER STATION | 4 | CONSTRUCTION START | Sep 2013 | Sep 2014 | Sep 2013 | Sep 2014
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-401A | EAST 91st ST MARINE TRANSFER STATION | 5 | CONSTRUCTION COMPLETION | Sep 2014 | Sep 2015 | Sep 2014 | Jun 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-415A | WEST 59th STREET MTS | 1 | PROJECT START | Sep 2011 | Sep 2011 | Sep 2011 | Sep 2011
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-415A | WEST 59th STREET MTS | 2 | DESIGN START | Sep 2011 | Sep 2011 | Sep 2011 | Sep 2011
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-415A | WEST 59th STREET MTS | 3 | DESIGN COMPLETION | Sep 2011 | Sep 2012 | Sep 2011 | Sep 2012
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-415A | WEST 59th STREET MTS | 4 | CONSTRUCTION START | Sep 2012 | Sep 2013 | Sep 2012 | Sep 2013
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-415A | WEST 59th STREET MTS | 5 | CONSTRUCTION COMPLETION | Sep 2013 | Sep 2014 | Sep 2013 | Jun 2029
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S219-233A | CONSTRUCTION MANHATTAN 1/2/5 GARAGE | 1 | PROJECT START | Sep 2011 | Sep 2011 | Sep 2011 | Sep 2011
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S219-233A | CONSTRUCTION MANHATTAN 1/2/5 GARAGE | 2 | DESIGN START | Sep 2011 | Sep 2011 | Sep 2011 | Sep 2011
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S219-233A | CONSTRUCTION MANHATTAN 1/2/5 GARAGE | 3 | DESIGN COMPLETION | Sep 2011 | Sep 2011 | Sep 2011 | Sep 2011
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S219-233A | CONSTRUCTION MANHATTAN 1/2/5 GARAGE | 4 | CONSTRUCTION START | Sep 2011 | Sep 2011 | Sep 2011 | Sep 2011
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S219-233A | CONSTRUCTION MANHATTAN 1/2/5 GARAGE | 5 | CONSTRUCTION COMPLETION | Sep 2011 | Sep 2011 | Sep 2011 | Jun 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBHFW | Sandy: Bellevue Flood Wall | 1 | DESIGN | Apr 2021 | Sep 2022 | Apr 2021 | Sep 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBHFW | Sandy: Bellevue Flood Wall | 2 | CONSTRUCTION | Sep 2022 | Sep 2024 | Sep 2022 | Sep 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBHFW | Sandy: Bellevue Flood Wall | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBHFW | Sandy: Bellevue Flood Wall | 4 | PROJECT START | Sep 2024 | Dec 2024 | Dec 2024 | Dec 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBHFW | Sandy: Bellevue Flood Wall | 5 | DESIGN START | Sep 2024 | Dec 2024 | Dec 2024 | Dec 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBHFW | Sandy: Bellevue Flood Wall | 6 | DESIGN COMPLETION | Sep 2024 | Dec 2024 | Dec 2024 | Dec 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBHFW | Sandy: Bellevue Flood Wall | 7 | CONSTRUCTION START | Sep 2024 | Dec 2024 | Dec 2024 | Dec 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBHFW | Sandy: Bellevue Flood Wall | 8 | CONSTRUCTION COMPLETION | Sep 2024 | Dec 2024 | Dec 2024 | Dec 2029
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW06 | Reconstruction of Vestry Street- Hurricane Sandy | 1 | DEVELOP SCOPE | Sep 2014 | Nov 2014 | Feb 2014 | Mar 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW06 | Reconstruction of Vestry Street- Hurricane Sandy | 2 | PRELIMINARY DESIGN | Nov 2014 | Mar 2016 | Mar 2015 | Oct 2015
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW06 | Reconstruction of Vestry Street- Hurricane Sandy | 3 | FINAL DESIGN | Mar 2016 | Jan 2017 | Oct 2015 | Sep 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW06 | Reconstruction of Vestry Street- Hurricane Sandy | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2017 | Jun 2017 | Oct 2016 | Jul 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW06 | Reconstruction of Vestry Street- Hurricane Sandy | 5 | CONSTRUCTION TO 25% | Jun 2017 | Sep 2017 | Jul 2019 | Nov 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW06 | Reconstruction of Vestry Street- Hurricane Sandy | 6 | CONSTRUCTION TO 50% | Jun 2017 | Sep 2017 | Jun 2017 | Sep 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW06 | Reconstruction of Vestry Street- Hurricane Sandy | 7 | CONSTRUCTION TO 75% | Jun 2017 | Sep 2017 | Jun 2017 | Sep 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW06 | Reconstruction of Vestry Street- Hurricane Sandy | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Dec 2017 | Sep 2017 | Dec 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW06 | Reconstruction of Vestry Street- Hurricane Sandy | 9 | SUBSTANTIAL COMPLETION | Dec 2017 | Feb 2018 | Dec 2017 | Feb 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW06 | Reconstruction of Vestry Street- Hurricane Sandy | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2018 | Mar 2018 | Feb 2018 | Jun 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW06 | Reconstruction of Vestry Street- Hurricane Sandy | 11 | PROJECT START | Feb 2018 | Mar 2018 | Jun 2024 | Jun 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW06 | Reconstruction of Vestry Street- Hurricane Sandy | 12 | DESIGN START | Feb 2018 | Mar 2018 | Jun 2024 | Jun 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW06 | Reconstruction of Vestry Street- Hurricane Sandy | 13 | DESIGN COMPLETION | Feb 2018 | Mar 2018 | Jun 2024 | Jun 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW06 | Reconstruction of Vestry Street- Hurricane Sandy | 14 | CONSTRUCTION START | Feb 2018 | Mar 2018 | Jun 2024 | Jun 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW06 | Reconstruction of Vestry Street- Hurricane Sandy | 15 | CONSTRUCTION COMPLETION | Feb 2018 | Mar 2018 | Jun 2024 | Jun 2027
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW08 | Reconstruction of Front Street-Hurricane Sandy | 1 | DEVELOP SCOPE | Feb 2016 | May 2016 | Feb 2016 | May 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW08 | Reconstruction of Front Street-Hurricane Sandy | 2 | PRELIMINARY DESIGN | May 2016 | Sep 2016 | May 2016 | Sep 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW08 | Reconstruction of Front Street-Hurricane Sandy | 3 | FINAL DESIGN | Sep 2016 | Mar 2017 | Sep 2016 | Mar 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW08 | Reconstruction of Front Street-Hurricane Sandy | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2017 | Jun 2017 | Mar 2017 | Jun 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW08 | Reconstruction of Front Street-Hurricane Sandy | 5 | CONSTRUCTION TO 25% | Jun 2017 | Oct 2017 | Jun 2017 | Oct 2017
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW08 | Reconstruction of Front Street-Hurricane Sandy | 6 | CONSTRUCTION TO 50% | Oct 2017 | Feb 2018 | Oct 2017 | Feb 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW08 | Reconstruction of Front Street-Hurricane Sandy | 7 | CONSTRUCTION TO 75% | Feb 2018 | Jun 2018 | Feb 2018 | Jun 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW08 | Reconstruction of Front Street-Hurricane Sandy | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW08 | Reconstruction of Front Street-Hurricane Sandy | 9 | SUBSTANTIAL COMPLETION | Sep 2018 | Nov 2018 | Sep 2018 | Nov 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW08 | Reconstruction of Front Street-Hurricane Sandy | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2018 | Dec 2018 | Nov 2018 | Jan 2032
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDSLIP | 100 OLD SLIP RESTORATION & SYSTEMS REPLACEMENT | 1 | DESIGN | Sep 2019 | Feb 2020 | Sep 2019 | Feb 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDSLIP | 100 OLD SLIP RESTORATION & SYSTEMS REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | May 2020 | Feb 2020 | May 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDSLIP | 100 OLD SLIP RESTORATION & SYSTEMS REPLACEMENT | 3 | CONSTRUCTION | May 2020 | May 2021 | May 2020 | May 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDSLIP | 100 OLD SLIP RESTORATION & SYSTEMS REPLACEMENT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2021 | Apr 2022 | May 2021 | Apr 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDSLIP | 100 OLD SLIP RESTORATION & SYSTEMS REPLACEMENT | 5 | PROJECT START | May 2021 | Apr 2022 | Apr 2023 | Apr 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDSLIP | 100 OLD SLIP RESTORATION & SYSTEMS REPLACEMENT | 6 | DESIGN START | May 2021 | Apr 2022 | Apr 2023 | Apr 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDSLIP | 100 OLD SLIP RESTORATION & SYSTEMS REPLACEMENT | 7 | DESIGN COMPLETION | May 2021 | Apr 2022 | Apr 2023 | Apr 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDSLIP | 100 OLD SLIP RESTORATION & SYSTEMS REPLACEMENT | 8 | CONSTRUCTION START | May 2021 | Apr 2022 | Apr 2023 | Apr 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDSLIP | 100 OLD SLIP RESTORATION & SYSTEMS REPLACEMENT | 9 | CONSTRUCTION COMPLETION | May 2021 | Apr 2022 | Apr 2023 | Jun 2032
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002157 | Replacement of Combined Sewer in E. 26th Street, Manhattan | 1 | DEVELOP SCOPE | Feb 2009 | May 2009 | Feb 2009 | May 2009
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002157 | Replacement of Combined Sewer in E. 26th Street, Manhattan | 2 | PRELIMINARY DESIGN | May 2009 | Sep 2009 | May 2009 | Sep 2009
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002157 | Replacement of Combined Sewer in E. 26th Street, Manhattan | 3 | FINAL DESIGN | Sep 2009 | Mar 2010 | Sep 2009 | Mar 2010
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002157 | Replacement of Combined Sewer in E. 26th Street, Manhattan | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2010 | Jun 2010 | May 2016 | Jun 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002157 | Replacement of Combined Sewer in E. 26th Street, Manhattan | 5 | CONSTRUCTION TO 25% | Jun 2010 | Oct 2010 | Jun 2016 | Jun 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002157 | Replacement of Combined Sewer in E. 26th Street, Manhattan | 6 | CONSTRUCTION TO 50% | Oct 2010 | Feb 2011 | Jun 2016 | Jun 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002157 | Replacement of Combined Sewer in E. 26th Street, Manhattan | 7 | CONSTRUCTION TO 75% | Feb 2011 | Jun 2011 | Jun 2016 | Jun 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002157 | Replacement of Combined Sewer in E. 26th Street, Manhattan | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2011 | Sep 2011 | Jun 2016 | Jun 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002157 | Replacement of Combined Sewer in E. 26th Street, Manhattan | 9 | SUBSTANTIAL COMPLETION | Sep 2011 | Nov 2011 | Jun 2016 | Jun 2016
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002157 | Replacement of Combined Sewer in E. 26th Street, Manhattan | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2011 | Dec 2011 | Dec 2017 | Oct 2032
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002169 | RECON OF COMBINED SEWER & WM IN YORK AVE | 1 | DEVELOP SCOPE | Jan 2011 | Mar 2011 | Jul 2021 | Oct 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002169 | RECON OF COMBINED SEWER & WM IN YORK AVE | 2 | PRELIMINARY DESIGN | Apr 2011 | Jul 2011 | Oct 2021 | Feb 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002169 | RECON OF COMBINED SEWER & WM IN YORK AVE | 3 | FINAL DESIGN | Jul 2011 | Jan 2012 | Feb 2022 | Aug 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002169 | RECON OF COMBINED SEWER & WM IN YORK AVE | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2012 | Apr 2012 | Mar 2022 | Jun 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002169 | RECON OF COMBINED SEWER & WM IN YORK AVE | 5 | CONSTRUCTION TO 25% | Apr 2012 | Aug 2012 | Jun 2022 | Jun 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002169 | RECON OF COMBINED SEWER & WM IN YORK AVE | 6 | CONSTRUCTION TO 50% | Aug 2012 | Dec 2012 | Jun 2022 | Jun 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002169 | RECON OF COMBINED SEWER & WM IN YORK AVE | 7 | CONSTRUCTION TO 75% | Dec 2012 | Apr 2013 | Jun 2022 | Jun 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002169 | RECON OF COMBINED SEWER & WM IN YORK AVE | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2013 | Jul 2013 | Jun 2022 | Jun 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002169 | RECON OF COMBINED SEWER & WM IN YORK AVE | 9 | SUBSTANTIAL COMPLETION | Jul 2013 | Sep 2013 | Jun 2022 | Jun 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002169 | RECON OF COMBINED SEWER & WM IN YORK AVE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2013 | Oct 2013 | Jun 2023 | Jul 2026
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002178 | Replacement & guniting comb SE in W. Broadway | 1 | DEVELOP SCOPE | May 2018 | Aug 2018 | May 2018 | Aug 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002178 | Replacement & guniting comb SE in W. Broadway | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Aug 2018 | Dec 2018
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002178 | Replacement & guniting comb SE in W. Broadway | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Dec 2018 | Jun 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002178 | Replacement & guniting comb SE in W. Broadway | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002178 | Replacement & guniting comb SE in W. Broadway | 5 | CONSTRUCTION TO 25% | Sep 2019 | Dec 2019 | Sep 2019 | Dec 2019
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002178 | Replacement & guniting comb SE in W. Broadway | 6 | CONSTRUCTION TO 50% | Dec 2019 | Apr 2020 | Dec 2019 | Apr 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002178 | Replacement & guniting comb SE in W. Broadway | 7 | CONSTRUCTION TO 75% | Apr 2020 | Aug 2020 | Apr 2020 | Aug 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002178 | Replacement & guniting comb SE in W. Broadway | 8 | ORIGINAL EQUIP & FURNISHING | Aug 2020 | Nov 2020 | Aug 2020 | Nov 2020
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002178 | Replacement & guniting comb SE in W. Broadway | 9 | SUBSTANTIAL COMPLETION | Nov 2020 | Jan 2021 | Nov 2020 | Jan 2021
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002178 | Replacement & guniting comb SE in W. Broadway | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2021 | Feb 2021 | Jan 2021 | Feb 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002178 | Replacement & guniting comb SE in W. Broadway | 11 | PROJECT START | Jan 2021 | Feb 2021 | Feb 2023 | Feb 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002178 | Replacement & guniting comb SE in W. Broadway | 12 | DESIGN START | Jan 2021 | Feb 2021 | Feb 2023 | Feb 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002178 | Replacement & guniting comb SE in W. Broadway | 13 | DESIGN COMPLETION | Jan 2021 | Feb 2021 | Feb 2023 | Feb 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002178 | Replacement & guniting comb SE in W. Broadway | 14 | CONSTRUCTION START | Jan 2021 | Feb 2021 | Feb 2023 | Feb 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002178 | Replacement & guniting comb SE in W. Broadway | 15 | CONSTRUCTION COMPLETION | Jan 2021 | Feb 2021 | Feb 2023 | Jun 2032
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002182 | Rplmt SE on Trinity Pl betw Thames & Rector Str MN HWMWTCB7 | 1 | DEVELOP SCOPE | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002182 | Rplmt SE on Trinity Pl betw Thames & Rector Str MN HWMWTCB7 | 2 | PRELIMINARY DESIGN | Apr 2022 | Jul 2022 | Apr 2022 | Jul 2022
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002182 | Rplmt SE on Trinity Pl betw Thames & Rector Str MN HWMWTCB7 | 3 | FINAL DESIGN | Jul 2022 | Jan 2023 | Jul 2022 | Jan 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002182 | Rplmt SE on Trinity Pl betw Thames & Rector Str MN HWMWTCB7 | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2023 | Apr 2023 | Jan 2023 | Apr 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002182 | Rplmt SE on Trinity Pl betw Thames & Rector Str MN HWMWTCB7 | 5 | CONSTRUCTION TO 25% | Apr 2023 | Aug 2023 | Apr 2023 | Aug 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002182 | Rplmt SE on Trinity Pl betw Thames & Rector Str MN HWMWTCB7 | 6 | CONSTRUCTION TO 50% | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002182 | Rplmt SE on Trinity Pl betw Thames & Rector Str MN HWMWTCB7 | 7 | CONSTRUCTION TO 75% | Dec 2023 | Apr 2024 | Dec 2023 | Apr 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002182 | Rplmt SE on Trinity Pl betw Thames & Rector Str MN HWMWTCB7 | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2024 | Jul 2024 | Apr 2024 | Jul 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002182 | Rplmt SE on Trinity Pl betw Thames & Rector Str MN HWMWTCB7 | 9 | SUBSTANTIAL COMPLETION | Jul 2024 | Sep 2024 | Jul 2024 | Sep 2024
20231026 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002182 | Rplmt SE on Trinity Pl betw Thames & Rector Str MN HWMWTCB7 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Oct 2024 | Sep 2024 | Oct 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA212 | DCLA - Met - Special Exhibition Lighting Improvement | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2023 | Jun 2023 | Jun 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA212 | DCLA - Met - Special Exhibition Lighting Improvement | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA212 | DCLA - Met - Special Exhibition Lighting Improvement | 3 | CONSTRUCTION TO 50% | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA212 | DCLA - Met - Special Exhibition Lighting Improvement | 4 | CONSTRUCTION TO 75% | Feb 2024 | May 2024 | Feb 2024 | May 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA212 | DCLA - Met - Special Exhibition Lighting Improvement | 5 | SUBSTANTIAL COMPLETION | May 2024 | Jul 2024 | May 2024 | Jul 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA212 | DCLA - Met - Special Exhibition Lighting Improvement | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA213 | DCLA - AMNH - S3A Air Handling Unit | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA213 | DCLA - AMNH - S3A Air Handling Unit | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA213 | DCLA - AMNH - S3A Air Handling Unit | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA213 | DCLA - AMNH - S3A Air Handling Unit | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA213 | DCLA - AMNH - S3A Air Handling Unit | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA213 | DCLA - AMNH - S3A Air Handling Unit | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA214 | DCLA - Met Museum - HVAC and Envelope Improvements to Renov | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA214 | DCLA - Met Museum - HVAC and Envelope Improvements to Renov | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA214 | DCLA - Met Museum - HVAC and Envelope Improvements to Renov | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA214 | DCLA - Met Museum - HVAC and Envelope Improvements to Renov | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA214 | DCLA - Met Museum - HVAC and Envelope Improvements to Renov | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA214 | DCLA - Met Museum - HVAC and Envelope Improvements to Renov | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE215 | DOE - M088 EER ECMs | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE215 | DOE - M088 EER ECMs | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE215 | DOE - M088 EER ECMs | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE215 | DOE - M088 EER ECMs | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE215 | DOE - M088 EER ECMs | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE215 | DOE - M088 EER ECMs | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE216 | DOE - M189 EER ECMs | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE216 | DOE - M189 EER ECMs | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE216 | DOE - M189 EER ECMs | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE216 | DOE - M189 EER ECMs | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE216 | DOE - M189 EER ECMs | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE216 | DOE - M189 EER ECMs | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE217 | DOE - M477 EER ECMs | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE217 | DOE - M477 EER ECMs | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE217 | DOE - M477 EER ECMs | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE217 | DOE - M477 EER ECMs | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE217 | DOE - M477 EER ECMs | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE217 | DOE - M477 EER ECMs | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDPR223 | DPR - Al Smith Windows and AC Replacement | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2023 | Jun 2023 | Jun 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDPR223 | DPR - Al Smith Windows and AC Replacement | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDPR223 | DPR - Al Smith Windows and AC Replacement | 3 | CONSTRUCTION TO 50% | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDPR223 | DPR - Al Smith Windows and AC Replacement | 4 | CONSTRUCTION TO 75% | Feb 2024 | May 2024 | Feb 2024 | May 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDPR223 | DPR - Al Smith Windows and AC Replacement | 5 | SUBSTANTIAL COMPLETION | May 2024 | Jul 2024 | May 2024 | Jul 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDPR223 | DPR - Al Smith Windows and AC Replacement | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT211 | FIT - Replacement of Air Handling Units with higher efficien | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2022 | Jun 2022 | Jun 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT211 | FIT - Replacement of Air Handling Units with higher efficien | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Aug 2022 | Jul 2022 | Aug 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT211 | FIT - Replacement of Air Handling Units with higher efficien | 3 | CONSTRUCTION TO 50% | Aug 2022 | Feb 2023 | Aug 2022 | Feb 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT211 | FIT - Replacement of Air Handling Units with higher efficien | 4 | CONSTRUCTION TO 75% | Feb 2023 | May 2023 | Feb 2023 | May 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT211 | FIT - Replacement of Air Handling Units with higher efficien | 5 | SUBSTANTIAL COMPLETION | May 2023 | Jul 2023 | May 2023 | Jul 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT211 | FIT - Replacement of Air Handling Units with higher efficien | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2023 | Aug 2023 | Jul 2023 | Jul 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT212 | FIT - Replace Air Handling Unit with high efficiency | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2022 | Jun 2022 | Jun 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT212 | FIT - Replace Air Handling Unit with high efficiency | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Aug 2022 | Jul 2022 | Aug 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT212 | FIT - Replace Air Handling Unit with high efficiency | 3 | CONSTRUCTION TO 50% | Aug 2022 | Feb 2023 | Aug 2022 | Feb 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT212 | FIT - Replace Air Handling Unit with high efficiency | 4 | CONSTRUCTION TO 75% | Feb 2023 | May 2023 | Feb 2023 | May 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT212 | FIT - Replace Air Handling Unit with high efficiency | 5 | SUBSTANTIAL COMPLETION | May 2023 | Jul 2023 | May 2023 | Jul 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT212 | FIT - Replace Air Handling Unit with high efficiency | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT213 | FIT - COED Residence Hall - New fan coil | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT213 | FIT - COED Residence Hall - New fan coil | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT213 | FIT - COED Residence Hall - New fan coil | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT213 | FIT - COED Residence Hall - New fan coil | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT213 | FIT - COED Residence Hall - New fan coil | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT213 | FIT - COED Residence Hall - New fan coil | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT221 | CUNY - FIT AIR HANDLING UNITS WITH HEAT RECOVERY 245 W 27 ST | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT221 | CUNY - FIT AIR HANDLING UNITS WITH HEAT RECOVERY 245 W 27 ST | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT221 | CUNY - FIT AIR HANDLING UNITS WITH HEAT RECOVERY 245 W 27 ST | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT221 | CUNY - FIT AIR HANDLING UNITS WITH HEAT RECOVERY 245 W 27 ST | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT221 | CUNY - FIT AIR HANDLING UNITS WITH HEAT RECOVERY 245 W 27 ST | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT221 | CUNY - FIT AIR HANDLING UNITS WITH HEAT RECOVERY 245 W 27 ST | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT221 | CUNY - FIT AIR HANDLING UNITS WITH HEAT RECOVERY 245 W 27 ST | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT221 | CUNY - FIT AIR HANDLING UNITS WITH HEAT RECOVERY 245 W 27 ST | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT221 | CUNY - FIT AIR HANDLING UNITS WITH HEAT RECOVERY 245 W 27 ST | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT221 | CUNY - FIT AIR HANDLING UNITS WITH HEAT RECOVERY 245 W 27 ST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT231 | ACE FIT POMERANTZ 4TH FLR LIGHTING | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT231 | ACE FIT POMERANTZ 4TH FLR LIGHTING | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT231 | ACE FIT POMERANTZ 4TH FLR LIGHTING | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT231 | ACE FIT POMERANTZ 4TH FLR LIGHTING | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT231 | ACE FIT POMERANTZ 4TH FLR LIGHTING | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT231 | ACE FIT POMERANTZ 4TH FLR LIGHTING | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGHQ | DFTA- relocation from 2 Lafayette St | 1 | DEVELOP SCOPE | Jun 2024 | Aug 2024 | Jun 2024 | Aug 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGHQ | DFTA- relocation from 2 Lafayette St | 2 | PRELIMINARY DESIGN | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGHQ | DFTA- relocation from 2 Lafayette St | 3 | FINAL DESIGN | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGHQ | DFTA- relocation from 2 Lafayette St | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGHQ | DFTA- relocation from 2 Lafayette St | 5 | CONSTRUCTION TO 25% | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGHQ | DFTA- relocation from 2 Lafayette St | 6 | CONSTRUCTION TO 50% | Jan 2026 | May 2026 | Jan 2026 | May 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGHQ | DFTA- relocation from 2 Lafayette St | 7 | CONSTRUCTION TO 75% | May 2026 | Sep 2026 | May 2026 | Sep 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGHQ | DFTA- relocation from 2 Lafayette St | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2026 | Dec 2026 | Sep 2026 | Dec 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGHQ | DFTA- relocation from 2 Lafayette St | 9 | SUBSTANTIAL COMPLETION | Dec 2026 | Feb 2027 | Dec 2026 | Feb 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGHQ | DFTA- relocation from 2 Lafayette St | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2027 | Mar 2027 | Feb 2027 | Mar 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264MN60 | DASNY - 60 CENTRE ST RENOVATION | 1 | DEVELOP SCOPE | Mar 2026 | May 2026 | Mar 2026 | May 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264MN60 | DASNY - 60 CENTRE ST RENOVATION | 2 | PRELIMINARY DESIGN | May 2026 | Sep 2026 | May 2026 | Sep 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264MN60 | DASNY - 60 CENTRE ST RENOVATION | 3 | FINAL DESIGN | Sep 2026 | Mar 2027 | Sep 2026 | Mar 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264MN60 | DASNY - 60 CENTRE ST RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2027 | Jun 2027 | Mar 2027 | Jun 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264MN60 | DASNY - 60 CENTRE ST RENOVATION | 5 | CONSTRUCTION TO 25% | Jun 2027 | Oct 2027 | Jun 2027 | Oct 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264MN60 | DASNY - 60 CENTRE ST RENOVATION | 6 | CONSTRUCTION TO 50% | Oct 2027 | Feb 2028 | Oct 2027 | Feb 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264MN60 | DASNY - 60 CENTRE ST RENOVATION | 7 | CONSTRUCTION TO 75% | Feb 2028 | Jun 2028 | Feb 2028 | Jun 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264MN60 | DASNY - 60 CENTRE ST RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2028 | Sep 2028 | Jun 2028 | Sep 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264MN60 | DASNY - 60 CENTRE ST RENOVATION | 9 | SUBSTANTIAL COMPLETION | Sep 2028 | Nov 2028 | Sep 2028 | Nov 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264MN60 | DASNY - 60 CENTRE ST RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2028 | Dec 2028 | Nov 2028 | Dec 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283DANY | 100 CENTRE- 1 HOGAN PL ENTRANCE - SECURITY ENHANCEMENTS | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283DANY | 100 CENTRE- 1 HOGAN PL ENTRANCE - SECURITY ENHANCEMENTS | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283DANY | 100 CENTRE- 1 HOGAN PL ENTRANCE - SECURITY ENHANCEMENTS | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283DANY | 100 CENTRE- 1 HOGAN PL ENTRANCE - SECURITY ENHANCEMENTS | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283DANY | 100 CENTRE- 1 HOGAN PL ENTRANCE - SECURITY ENHANCEMENTS | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283DANY | 100 CENTRE- 1 HOGAN PL ENTRANCE - SECURITY ENHANCEMENTS | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283DANY | 100 CENTRE- 1 HOGAN PL ENTRANCE - SECURITY ENHANCEMENTS | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283DANY | 100 CENTRE- 1 HOGAN PL ENTRANCE - SECURITY ENHANCEMENTS | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283DANY | 100 CENTRE- 1 HOGAN PL ENTRANCE - SECURITY ENHANCEMENTS | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283DANY | 100 CENTRE- 1 HOGAN PL ENTRANCE - SECURITY ENHANCEMENTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283FIRE | 100 CENTRE ST.- FIRE SAFETY | 1 | DEVELOP SCOPE | Nov 2009 | Jan 2010 | Nov 2009 | Jan 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283FIRE | 100 CENTRE ST.- FIRE SAFETY | 2 | PRELIMINARY DESIGN | May 2005 | Feb 2006 | May 2005 | Feb 2006
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283FIRE | 100 CENTRE ST.- FIRE SAFETY | 3 | FINAL DESIGN | Mar 2006 | May 2007 | Mar 2006 | May 2007
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283FIRE | 100 CENTRE ST.- FIRE SAFETY | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2007 | Aug 2007 | Jun 2007 | Aug 2007
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283FIRE | 100 CENTRE ST.- FIRE SAFETY | 5 | CONSTRUCTION TO 25% | Sep 2007 | Nov 2007 | Sep 2007 | Nov 2007
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283FIRE | 100 CENTRE ST.- FIRE SAFETY | 6 | CONSTRUCTION TO 50% | Dec 2007 | Feb 2008 | Dec 2007 | Feb 2008
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283FIRE | 100 CENTRE ST.- FIRE SAFETY | 7 | CONSTRUCTION TO 75% | Mar 2008 | Mar 2008 | Mar 2008 | Mar 2008
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283FIRE | 100 CENTRE ST.- FIRE SAFETY | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2008 | Mar 2008 | Mar 2008 | Mar 2008
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283FIRE | 100 CENTRE ST.- FIRE SAFETY | 9 | SUBSTANTIAL COMPLETION | Jul 2008 | Sep 2008 | Jul 2008 | Jun 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283FIRE | 100 CENTRE ST.- FIRE SAFETY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2008 | Dec 2011 | Jul 2024 | Sep 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283RF | 100 CENTRE ST- ROOF REHAB | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283RF | 100 CENTRE ST- ROOF REHAB | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283RF | 100 CENTRE ST- ROOF REHAB | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283RF | 100 CENTRE ST- ROOF REHAB | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283RF | 100 CENTRE ST- ROOF REHAB | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283RF | 100 CENTRE ST- ROOF REHAB | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283RF | 100 CENTRE ST- ROOF REHAB | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283RF | 100 CENTRE ST- ROOF REHAB | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283RF | 100 CENTRE ST- ROOF REHAB | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283RF | 100 CENTRE ST- ROOF REHAB | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO305REHB | 314 W. 54TH ST.- MIDTOWN COMM COURT EXPANSION | 1 | DEVELOP SCOPE | May 2002 | Aug 2002 | Jan 2001 | Mar 2001
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO305REHB | 314 W. 54TH ST.- MIDTOWN COMM COURT EXPANSION | 2 | PRELIMINARY DESIGN | Aug 2002 | Dec 2002 | Apr 2001 | Jul 2001
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO305REHB | 314 W. 54TH ST.- MIDTOWN COMM COURT EXPANSION | 3 | FINAL DESIGN | Dec 2002 | Jun 2003 | Jul 2001 | Jan 2002
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO305REHB | 314 W. 54TH ST.- MIDTOWN COMM COURT EXPANSION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2003 | Sep 2003 | Jun 2021 | Aug 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO305REHB | 314 W. 54TH ST.- MIDTOWN COMM COURT EXPANSION | 5 | CONSTRUCTION TO 25% | Sep 2003 | Jan 2004 | Aug 2021 | Apr 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO305REHB | 314 W. 54TH ST.- MIDTOWN COMM COURT EXPANSION | 6 | CONSTRUCTION TO 50% | Jan 2004 | May 2004 | Apr 2022 | Oct 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO305REHB | 314 W. 54TH ST.- MIDTOWN COMM COURT EXPANSION | 7 | CONSTRUCTION TO 75% | May 2004 | Aug 2004 | Oct 2022 | Jun 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO305REHB | 314 W. 54TH ST.- MIDTOWN COMM COURT EXPANSION | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2004 | Nov 2004 | Jun 2025 | Jan 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO305REHB | 314 W. 54TH ST.- MIDTOWN COMM COURT EXPANSION | 9 | SUBSTANTIAL COMPLETION | Nov 2004 | Jan 2005 | Jan 2026 | Jul 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO305REHB | 314 W. 54TH ST.- MIDTOWN COMM COURT EXPANSION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2005 | Feb 2005 | Jul 2026 | Nov 2030
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306FASP | 170 E 121st ST FIRE ALARM AND SPRINKLER | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306FASP | 170 E 121st ST FIRE ALARM AND SPRINKLER | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306FASP | 170 E 121st ST FIRE ALARM AND SPRINKLER | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306FASP | 170 E 121st ST FIRE ALARM AND SPRINKLER | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306FASP | 170 E 121st ST FIRE ALARM AND SPRINKLER | 5 | CONSTRUCTION TO 25% | Jun 2026 | Sep 2026 | Jun 2026 | Sep 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306FASP | 170 E 121st ST FIRE ALARM AND SPRINKLER | 6 | CONSTRUCTION TO 50% | Sep 2026 | Jan 2027 | Sep 2026 | Jan 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306FASP | 170 E 121st ST FIRE ALARM AND SPRINKLER | 7 | CONSTRUCTION TO 75% | Jan 2027 | May 2027 | Jan 2027 | May 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306FASP | 170 E 121st ST FIRE ALARM AND SPRINKLER | 8 | ORIGINAL EQUIP & FURNISHING | May 2027 | Aug 2027 | May 2027 | Aug 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306FASP | 170 E 121st ST FIRE ALARM AND SPRINKLER | 9 | SUBSTANTIAL COMPLETION | Aug 2027 | Oct 2027 | Aug 2027 | Oct 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306FASP | 170 E 121st ST FIRE ALARM AND SPRINKLER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2027 | Nov 2027 | Oct 2027 | Nov 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306MHCB | 170 E. 121 ST. - HEATING PLANT AND ENVELOPE | 1 | DEVELOP SCOPE | Jan 2012 | Mar 2012 | Jun 2022 | Aug 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306MHCB | 170 E. 121 ST. - HEATING PLANT AND ENVELOPE | 2 | PRELIMINARY DESIGN | Mar 2012 | Jul 2012 | Aug 2022 | Dec 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306MHCB | 170 E. 121 ST. - HEATING PLANT AND ENVELOPE | 3 | FINAL DESIGN | Jul 2012 | Jan 2013 | Dec 2022 | Jun 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306MHCB | 170 E. 121 ST. - HEATING PLANT AND ENVELOPE | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2013 | Apr 2013 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306MHCB | 170 E. 121 ST. - HEATING PLANT AND ENVELOPE | 5 | CONSTRUCTION TO 25% | Apr 2013 | Aug 2013 | Sep 2023 | Jan 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306MHCB | 170 E. 121 ST. - HEATING PLANT AND ENVELOPE | 6 | CONSTRUCTION TO 50% | Aug 2013 | Dec 2013 | Jan 2024 | May 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306MHCB | 170 E. 121 ST. - HEATING PLANT AND ENVELOPE | 7 | CONSTRUCTION TO 75% | Dec 2013 | Apr 2014 | May 2024 | Sep 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306MHCB | 170 E. 121 ST. - HEATING PLANT AND ENVELOPE | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2014 | Jul 2014 | Sep 2024 | Dec 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306MHCB | 170 E. 121 ST. - HEATING PLANT AND ENVELOPE | 9 | SUBSTANTIAL COMPLETION | Jul 2014 | Sep 2014 | Dec 2024 | Feb 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306MHCB | 170 E. 121 ST. - HEATING PLANT AND ENVELOPE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2014 | Oct 2014 | Feb 2025 | Mar 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO81ADA1 | 31 Chambers Entrance ADA Compliance | 1 | DEVELOP SCOPE | Jun 2021 | Aug 2021 | Jun 2021 | Aug 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO81ADA1 | 31 Chambers Entrance ADA Compliance | 2 | PRELIMINARY DESIGN | Aug 2021 | Dec 2021 | Aug 2021 | Dec 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO81ADA1 | 31 Chambers Entrance ADA Compliance | 3 | FINAL DESIGN | Dec 2021 | Jun 2022 | Dec 2021 | Jun 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO81ADA1 | 31 Chambers Entrance ADA Compliance | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO81ADA1 | 31 Chambers Entrance ADA Compliance | 5 | CONSTRUCTION TO 25% | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO81ADA1 | 31 Chambers Entrance ADA Compliance | 6 | CONSTRUCTION TO 50% | Jan 2023 | May 2023 | Jan 2023 | May 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO81ADA1 | 31 Chambers Entrance ADA Compliance | 7 | CONSTRUCTION TO 75% | May 2023 | Sep 2023 | May 2023 | Sep 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO81ADA1 | 31 Chambers Entrance ADA Compliance | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Dec 2023 | Sep 2023 | Dec 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO81ADA1 | 31 Chambers Entrance ADA Compliance | 9 | SUBSTANTIAL COMPLETION | Dec 2023 | Feb 2024 | Dec 2023 | Feb 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO81ADA1 | 31 Chambers Entrance ADA Compliance | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2024 | Mar 2024 | Feb 2024 | Mar 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E09-0006A | DPR - 09-47: CENTRAL PARK ZOO, 830 5th AVENUE | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2020 | Jun 2020 | Jun 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E09-0006A | DPR - 09-47: CENTRAL PARK ZOO, 830 5th AVENUE | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Aug 2020 | Jul 2020 | Aug 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E09-0006A | DPR - 09-47: CENTRAL PARK ZOO, 830 5th AVENUE | 3 | CONSTRUCTION TO 50% | Aug 2020 | Feb 2021 | Aug 2020 | Feb 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E09-0006A | DPR - 09-47: CENTRAL PARK ZOO, 830 5th AVENUE | 4 | CONSTRUCTION TO 75% | Feb 2021 | May 2021 | Jun 2024 | Aug 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E09-0006A | DPR - 09-47: CENTRAL PARK ZOO, 830 5th AVENUE | 5 | SUBSTANTIAL COMPLETION | May 2021 | Jul 2021 | Aug 2024 | Oct 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E09-0006A | DPR - 09-47: CENTRAL PARK ZOO, 830 5th AVENUE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Aug 2021 | Oct 2024 | Nov 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0001 | NYPD Comprehensice Lighting Upgrade | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2022 | Jun 2022 | Jun 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0001 | NYPD Comprehensice Lighting Upgrade | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Aug 2022 | Jul 2022 | Aug 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0001 | NYPD Comprehensice Lighting Upgrade | 3 | CONSTRUCTION TO 50% | Aug 2022 | Feb 2023 | Aug 2022 | Feb 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0001 | NYPD Comprehensice Lighting Upgrade | 4 | CONSTRUCTION TO 75% | Feb 2023 | May 2023 | Feb 2023 | May 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0001 | NYPD Comprehensice Lighting Upgrade | 5 | SUBSTANTIAL COMPLETION | May 2023 | Jul 2023 | May 2023 | Jul 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0001 | NYPD Comprehensice Lighting Upgrade | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0003 | DSNY - W57th Street Garage Comprehensive Energy Upgrade | 1 | DEVELOP SCOPE | Aug 2022 | Sep 2022 | Aug 2022 | Sep 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0003 | DSNY - W57th Street Garage Comprehensive Energy Upgrade | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2022 | Nov 2022 | Sep 2022 | Nov 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0003 | DSNY - W57th Street Garage Comprehensive Energy Upgrade | 3 | CONSTRUCTION TO 50% | Nov 2022 | May 2023 | Nov 2022 | May 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0003 | DSNY - W57th Street Garage Comprehensive Energy Upgrade | 4 | CONSTRUCTION TO 75% | May 2023 | Aug 2023 | May 2023 | Aug 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0003 | DSNY - W57th Street Garage Comprehensive Energy Upgrade | 5 | SUBSTANTIAL COMPLETION | Aug 2023 | Oct 2023 | Aug 2023 | Oct 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0003 | DSNY - W57th Street Garage Comprehensive Energy Upgrade | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2023 | Aug 2025 | Oct 2023 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0007 | OCME Center for Forensic Sciences | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2022 | Jun 2022 | Jun 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0007 | OCME Center for Forensic Sciences | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Aug 2022 | Jul 2022 | Aug 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0007 | OCME Center for Forensic Sciences | 3 | CONSTRUCTION TO 50% | Aug 2022 | Feb 2023 | Aug 2022 | Feb 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0007 | OCME Center for Forensic Sciences | 4 | CONSTRUCTION TO 75% | Feb 2023 | May 2023 | Feb 2023 | May 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0007 | OCME Center for Forensic Sciences | 5 | SUBSTANTIAL COMPLETION | May 2023 | Jul 2023 | May 2023 | Jul 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0007 | OCME Center for Forensic Sciences | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2023 | Jun 2024 | Jul 2023 | Jun 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0009 | CUNY Hunter College High School (DI) | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0009 | CUNY Hunter College High School (DI) | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0009 | CUNY Hunter College High School (DI) | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0009 | CUNY Hunter College High School (DI) | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0009 | CUNY Hunter College High School (DI) | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0009 | CUNY Hunter College High School (DI) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0001 | DCAS 115 Chrystie Street - Electrification | 1 | DEVELOP SCOPE | Jun 2025 | Jun 2025 | Jun 2025 | Jun 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0001 | DCAS 115 Chrystie Street - Electrification | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0001 | DCAS 115 Chrystie Street - Electrification | 3 | CONSTRUCTION TO 50% | Aug 2025 | Feb 2026 | Aug 2025 | Feb 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0001 | DCAS 115 Chrystie Street - Electrification | 4 | CONSTRUCTION TO 75% | Feb 2026 | May 2026 | Feb 2026 | May 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0001 | DCAS 115 Chrystie Street - Electrification | 5 | SUBSTANTIAL COMPLETION | May 2026 | Jul 2026 | May 2026 | Jul 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0001 | DCAS 115 Chrystie Street - Electrification | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2026 | Aug 2026 | Jul 2026 | Aug 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0003 | DPR Multisite Recreation Centers (DI) | 1 | DEVELOP SCOPE | Jun 2025 | Jun 2025 | Jun 2025 | Jun 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0003 | DPR Multisite Recreation Centers (DI) | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0003 | DPR Multisite Recreation Centers (DI) | 3 | CONSTRUCTION TO 50% | Aug 2025 | Feb 2026 | Aug 2025 | Feb 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0003 | DPR Multisite Recreation Centers (DI) | 4 | CONSTRUCTION TO 75% | Feb 2026 | May 2026 | Feb 2026 | May 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0003 | DPR Multisite Recreation Centers (DI) | 5 | SUBSTANTIAL COMPLETION | May 2026 | Jul 2026 | May 2026 | Jul 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0003 | DPR Multisite Recreation Centers (DI) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2026 | Aug 2026 | Jul 2026 | Aug 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0005 | Gouverneur Hospital | 1 | DEVELOP SCOPE | Jun 2025 | Jun 2025 | Jun 2025 | Jun 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0005 | Gouverneur Hospital | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0005 | Gouverneur Hospital | 3 | CONSTRUCTION TO 50% | Aug 2025 | Feb 2026 | Aug 2025 | Feb 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0005 | Gouverneur Hospital | 4 | CONSTRUCTION TO 75% | Feb 2026 | May 2026 | Feb 2026 | May 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0005 | Gouverneur Hospital | 5 | SUBSTANTIAL COMPLETION | May 2026 | Jul 2026 | May 2026 | Jul 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0005 | Gouverneur Hospital | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2026 | Aug 2026 | Jul 2026 | Aug 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0008 | Chelsea Health Center | 1 | DEVELOP SCOPE | Jun 2025 | Jun 2025 | Jun 2025 | Jun 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0008 | Chelsea Health Center | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0008 | Chelsea Health Center | 3 | CONSTRUCTION TO 50% | Aug 2025 | Feb 2026 | Aug 2025 | Feb 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0008 | Chelsea Health Center | 4 | CONSTRUCTION TO 75% | Feb 2026 | May 2026 | Feb 2026 | May 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0008 | Chelsea Health Center | 5 | SUBSTANTIAL COMPLETION | May 2026 | Jul 2026 | May 2026 | Jul 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0008 | Chelsea Health Center | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2026 | Aug 2026 | Jul 2026 | Aug 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0018 | DCLA - Lincoln Center Campus: Damrosch Park/Public Spaces | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2020 | Jun 2024 | Jun 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0018 | DCLA - Lincoln Center Campus: Damrosch Park/Public Spaces | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Aug 2020 | Jul 2024 | Aug 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0018 | DCLA - Lincoln Center Campus: Damrosch Park/Public Spaces | 3 | CONSTRUCTION TO 50% | Aug 2020 | Feb 2021 | Aug 2024 | Feb 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0018 | DCLA - Lincoln Center Campus: Damrosch Park/Public Spaces | 4 | CONSTRUCTION TO 75% | Feb 2021 | May 2021 | Feb 2025 | May 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0018 | DCLA - Lincoln Center Campus: Damrosch Park/Public Spaces | 5 | SUBSTANTIAL COMPLETION | May 2021 | Jul 2021 | May 2025 | Jul 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0018 | DCLA - Lincoln Center Campus: Damrosch Park/Public Spaces | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Aug 2021 | Jul 2025 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0019 | DCLA - Lincoln Center Campus: Plaza/Public Spaces/Garages | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2020 | Jun 2020 | Jun 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0019 | DCLA - Lincoln Center Campus: Plaza/Public Spaces/Garages | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Aug 2020 | Jul 2020 | Aug 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0019 | DCLA - Lincoln Center Campus: Plaza/Public Spaces/Garages | 3 | CONSTRUCTION TO 50% | Aug 2020 | Feb 2021 | Aug 2020 | Feb 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0019 | DCLA - Lincoln Center Campus: Plaza/Public Spaces/Garages | 4 | CONSTRUCTION TO 75% | Feb 2021 | May 2021 | Feb 2021 | May 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0019 | DCLA - Lincoln Center Campus: Plaza/Public Spaces/Garages | 5 | SUBSTANTIAL COMPLETION | May 2021 | Jul 2021 | Jun 2025 | Jul 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0019 | DCLA - Lincoln Center Campus: Plaza/Public Spaces/Garages | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Aug 2021 | Jul 2025 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0026 | NYPL - The Library for the Performing Arts | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2020 | Jun 2020 | Jun 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0026 | NYPL - The Library for the Performing Arts | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Aug 2020 | Jul 2020 | Aug 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0026 | NYPL - The Library for the Performing Arts | 3 | CONSTRUCTION TO 50% | Aug 2020 | Feb 2021 | Aug 2020 | Feb 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0026 | NYPL - The Library for the Performing Arts | 4 | CONSTRUCTION TO 75% | Feb 2021 | May 2021 | Feb 2021 | May 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0026 | NYPL - The Library for the Performing Arts | 5 | SUBSTANTIAL COMPLETION | May 2021 | Jul 2021 | May 2021 | Jul 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0026 | NYPL - The Library for the Performing Arts | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Aug 2021 | Jul 2021 | Jun 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0036 | DPR - Central Park Campus: CPC 79th St Maintenance Yard | 3 | CONSTRUCTION TO 50% | Aug 2019 | Feb 2020 | Aug 2019 | Feb 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0036 | DPR - Central Park Campus: CPC 79th St Maintenance Yard | 4 | CONSTRUCTION TO 75% | Feb 2020 | May 2020 | Feb 2020 | May 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0036 | DPR - Central Park Campus: CPC 79th St Maintenance Yard | 5 | SUBSTANTIAL COMPLETION | May 2020 | Jul 2020 | May 2020 | Jul 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0036 | DPR - Central Park Campus: CPC 79th St Maintenance Yard | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Aug 2020 | Jul 2020 | Aug 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0041 | DSNY - Manhattan Borough Repair Shop | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2020 | Jun 2020 | Jun 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0041 | DSNY - Manhattan Borough Repair Shop | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Aug 2020 | Jul 2020 | Aug 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0041 | DSNY - Manhattan Borough Repair Shop | 3 | CONSTRUCTION TO 50% | Aug 2020 | Feb 2021 | Aug 2020 | Feb 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0041 | DSNY - Manhattan Borough Repair Shop | 4 | CONSTRUCTION TO 75% | Feb 2021 | May 2021 | Feb 2021 | May 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0041 | DSNY - Manhattan Borough Repair Shop | 5 | SUBSTANTIAL COMPLETION | May 2021 | Jul 2021 | May 2021 | Jul 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0041 | DSNY - Manhattan Borough Repair Shop | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Aug 2021 | Jul 2021 | Aug 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0046 | CUNY - BMCC Campus: Chambers St. Building (Main Campus) | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2020 | Jun 2020 | Jun 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0046 | CUNY - BMCC Campus: Chambers St. Building (Main Campus) | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Aug 2020 | Jul 2020 | Aug 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0046 | CUNY - BMCC Campus: Chambers St. Building (Main Campus) | 3 | CONSTRUCTION TO 50% | Aug 2020 | Feb 2021 | Aug 2020 | Feb 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0046 | CUNY - BMCC Campus: Chambers St. Building (Main Campus) | 4 | CONSTRUCTION TO 75% | Feb 2021 | May 2021 | Feb 2021 | May 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0046 | CUNY - BMCC Campus: Chambers St. Building (Main Campus) | 5 | SUBSTANTIAL COMPLETION | May 2021 | Jul 2021 | May 2021 | Jul 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0046 | CUNY - BMCC Campus: Chambers St. Building (Main Campus) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Aug 2021 | Jul 2021 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0054 | CIG - David H. Koch Theater | 1 | DEVELOP SCOPE | May 2020 | May 2020 | May 2020 | May 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0054 | CIG - David H. Koch Theater | 2 | BID AWARD AND REGISTER CONTRCT | May 2020 | Jul 2020 | May 2020 | Jul 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0054 | CIG - David H. Koch Theater | 3 | CONSTRUCTION TO 50% | Jul 2020 | Jan 2021 | Jul 2020 | Jan 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0054 | CIG - David H. Koch Theater | 4 | CONSTRUCTION TO 75% | Jan 2021 | Apr 2021 | Jan 2021 | Apr 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0054 | CIG - David H. Koch Theater | 5 | SUBSTANTIAL COMPLETION | Apr 2021 | Jun 2021 | Apr 2021 | Jun 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0054 | CIG - David H. Koch Theater | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2021 | Jul 2021 | Jun 2021 | Oct 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0055 | DCAS - Midtown Community Court | 1 | DEVELOP SCOPE | Feb 2020 | Mar 2020 | Jun 2022 | Aug 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0055 | DCAS - Midtown Community Court | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Apr 2020 | Aug 2022 | Oct 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0055 | DCAS - Midtown Community Court | 3 | CONSTRUCTION TO 50% | May 2020 | Oct 2020 | Jun 2025 | Nov 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0055 | DCAS - Midtown Community Court | 4 | CONSTRUCTION TO 75% | Oct 2020 | Jan 2021 | Nov 2025 | Feb 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0055 | DCAS - Midtown Community Court | 5 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Feb 2026 | Apr 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0055 | DCAS - Midtown Community Court | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Apr 2026 | May 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0056 | NYPD - 18th Precinct (Midtown North) | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Apr 2020 | Jul 2022 | Aug 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0056 | NYPD - 18th Precinct (Midtown North) | 3 | CONSTRUCTION TO 50% | May 2020 | Oct 2020 | Aug 2022 | Feb 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0056 | NYPD - 18th Precinct (Midtown North) | 4 | CONSTRUCTION TO 75% | Oct 2020 | Jan 2021 | Jun 2025 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0056 | NYPD - 18th Precinct (Midtown North) | 5 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Aug 2025 | Oct 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0056 | NYPD - 18th Precinct (Midtown North) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Oct 2025 | Sep 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0065 | NYPD - 10th Precinct | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | May 2020 | Jul 2022 | Aug 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0065 | NYPD - 10th Precinct | 3 | CONSTRUCTION TO 50% | May 2020 | Nov 2020 | Aug 2022 | Feb 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0065 | NYPD - 10th Precinct | 4 | CONSTRUCTION TO 75% | Nov 2020 | Feb 2021 | Feb 2023 | May 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0065 | NYPD - 10th Precinct | 5 | SUBSTANTIAL COMPLETION | Feb 2021 | Apr 2021 | May 2023 | Jul 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0065 | NYPD - 10th Precinct | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2021 | May 2021 | Jul 2023 | Aug 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0066 | NYPD -Engine Co. 39, Ladder Co. 16 and 19th Precinct Campus | 1 | DEVELOP SCOPE | Feb 2020 | Mar 2020 | Jun 2022 | Jun 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0066 | NYPD -Engine Co. 39, Ladder Co. 16 and 19th Precinct Campus | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Apr 2020 | Jul 2022 | Aug 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0066 | NYPD -Engine Co. 39, Ladder Co. 16 and 19th Precinct Campus | 3 | CONSTRUCTION TO 50% | May 2020 | Oct 2020 | Aug 2022 | Feb 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0066 | NYPD -Engine Co. 39, Ladder Co. 16 and 19th Precinct Campus | 4 | CONSTRUCTION TO 75% | Oct 2020 | Jan 2021 | Feb 2023 | May 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0066 | NYPD -Engine Co. 39, Ladder Co. 16 and 19th Precinct Campus | 5 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | May 2023 | Jul 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0066 | NYPD -Engine Co. 39, Ladder Co. 16 and 19th Precinct Campus | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Jul 2023 | Aug 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0067 | NYPD - 30th Precinct | 2 | BID AWARD AND REGISTER CONTRCT | Apr 2020 | Jun 2020 | Jul 2022 | Aug 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0067 | NYPD - 30th Precinct | 3 | CONSTRUCTION TO 50% | Jun 2020 | Dec 2020 | Aug 2022 | Feb 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0067 | NYPD - 30th Precinct | 4 | CONSTRUCTION TO 75% | Dec 2020 | Mar 2021 | Feb 2023 | May 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0067 | NYPD - 30th Precinct | 5 | SUBSTANTIAL COMPLETION | Mar 2021 | May 2021 | May 2023 | Jul 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0067 | NYPD - 30th Precinct | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2021 | Jun 2021 | Jul 2023 | Jun 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0068 | NYPD - 32nd Precinct | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | May 2020 | Jul 2022 | Aug 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0068 | NYPD - 32nd Precinct | 3 | CONSTRUCTION TO 50% | May 2020 | Oct 2020 | Aug 2022 | Feb 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0068 | NYPD - 32nd Precinct | 4 | CONSTRUCTION TO 75% | Oct 2020 | Jan 2021 | Feb 2023 | May 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0068 | NYPD - 32nd Precinct | 5 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | May 2023 | Jul 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0068 | NYPD - 32nd Precinct | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Jul 2023 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0078 | DHS - MANHATTAN BOWERY SHELTER | 1 | DEVELOP SCOPE | Feb 2020 | Mar 2020 | Jun 2022 | Jun 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0078 | DHS - MANHATTAN BOWERY SHELTER | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Apr 2020 | Jul 2022 | Aug 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0078 | DHS - MANHATTAN BOWERY SHELTER | 3 | CONSTRUCTION TO 50% | May 2020 | Oct 2020 | Aug 2022 | Feb 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0078 | DHS - MANHATTAN BOWERY SHELTER | 4 | CONSTRUCTION TO 75% | Oct 2020 | Jan 2021 | Feb 2023 | May 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0078 | DHS - MANHATTAN BOWERY SHELTER | 5 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | May 2023 | Jul 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0078 | DHS - MANHATTAN BOWERY SHELTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Jul 2023 | Aug 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0081 | DHS - FORT WASHINGTON ARMORY - SHELTER (PROJECT RENEWAL) | 1 | DEVELOP SCOPE | Feb 2020 | Mar 2020 | Jun 2023 | Jun 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0081 | DHS - FORT WASHINGTON ARMORY - SHELTER (PROJECT RENEWAL) | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Apr 2020 | Jul 2023 | Aug 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0081 | DHS - FORT WASHINGTON ARMORY - SHELTER (PROJECT RENEWAL) | 3 | CONSTRUCTION TO 50% | May 2020 | Oct 2020 | Jun 2022 | Nov 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0081 | DHS - FORT WASHINGTON ARMORY - SHELTER (PROJECT RENEWAL) | 4 | CONSTRUCTION TO 75% | Oct 2020 | Jan 2021 | Nov 2022 | Feb 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0081 | DHS - FORT WASHINGTON ARMORY - SHELTER (PROJECT RENEWAL) | 5 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Feb 2023 | Apr 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0081 | DHS - FORT WASHINGTON ARMORY - SHELTER (PROJECT RENEWAL) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Apr 2023 | Sep 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0093 | CIG - METROPOLITAN MUSEUM OF ART - OFFICE SPACES | 1 | DEVELOP SCOPE | Mar 2021 | Apr 2021 | Jun 2023 | Jun 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0093 | CIG - METROPOLITAN MUSEUM OF ART - OFFICE SPACES | 2 | BID AWARD AND REGISTER CONTRCT | Apr 2021 | Jun 2021 | Jul 2023 | Aug 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0093 | CIG - METROPOLITAN MUSEUM OF ART - OFFICE SPACES | 3 | CONSTRUCTION TO 50% | Jun 2021 | Dec 2021 | Jun 2024 | Nov 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0093 | CIG - METROPOLITAN MUSEUM OF ART - OFFICE SPACES | 4 | CONSTRUCTION TO 75% | Dec 2021 | Mar 2022 | Nov 2024 | Feb 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0093 | CIG - METROPOLITAN MUSEUM OF ART - OFFICE SPACES | 5 | SUBSTANTIAL COMPLETION | Mar 2022 | May 2022 | Feb 2025 | Apr 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0093 | CIG - METROPOLITAN MUSEUM OF ART - OFFICE SPACES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2022 | Jun 2022 | Apr 2025 | May 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0094 | NYPD - 13TH PRECINCT (OLD ACADEMY) | 1 | DEVELOP SCOPE | Feb 2021 | Mar 2021 | Jun 2024 | Jun 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0094 | NYPD - 13TH PRECINCT (OLD ACADEMY) | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2021 | May 2021 | Jul 2024 | Aug 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0094 | NYPD - 13TH PRECINCT (OLD ACADEMY) | 3 | CONSTRUCTION TO 50% | May 2021 | Nov 2021 | Aug 2024 | Feb 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0094 | NYPD - 13TH PRECINCT (OLD ACADEMY) | 4 | CONSTRUCTION TO 75% | Nov 2021 | Feb 2022 | Feb 2025 | May 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0094 | NYPD - 13TH PRECINCT (OLD ACADEMY) | 5 | SUBSTANTIAL COMPLETION | Feb 2022 | Apr 2022 | May 2025 | Jul 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0094 | NYPD - 13TH PRECINCT (OLD ACADEMY) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2022 | May 2022 | Jul 2025 | Aug 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HR258AVEC | 400 8th Ave Construction | 1 | DESIGN | Jul 2020 | Dec 2020 | Jul 2022 | Jan 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HR258AVEC | 400 8th Ave Construction | 2 | CONSTRUCTION | Dec 2020 | Jun 2021 | Jan 2023 | May 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWMFCNTR | Relocation to 1 Centre Street | 1 | DEVELOP SCOPE | Jun 2027 | Sep 2027 | Jun 2027 | Sep 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWMFCNTR | Relocation to 1 Centre Street | 2 | PRELIMINARY DESIGN | Sep 2027 | Jan 2028 | Sep 2027 | Jan 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWMFCNTR | Relocation to 1 Centre Street | 3 | FINAL DESIGN | Jan 2028 | Jul 2028 | Jan 2028 | Jul 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWMFCNTR | Relocation to 1 Centre Street | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2028 | Oct 2028 | Jul 2028 | Oct 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWMFCNTR | Relocation to 1 Centre Street | 5 | CONSTRUCTION TO 25% | Oct 2028 | Feb 2029 | Oct 2028 | Feb 2029
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWMFCNTR | Relocation to 1 Centre Street | 6 | CONSTRUCTION TO 50% | Feb 2029 | Jun 2029 | Feb 2029 | Jun 2029
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWMFCNTR | Relocation to 1 Centre Street | 7 | CONSTRUCTION TO 75% | Jun 2029 | Oct 2029 | Jun 2029 | Oct 2029
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWMFCNTR | Relocation to 1 Centre Street | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2029 | Jan 2030 | Oct 2029 | Jan 2030
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWMFCNTR | Relocation to 1 Centre Street | 9 | SUBSTANTIAL COMPLETION | Jan 2030 | Mar 2030 | Jan 2030 | Mar 2030
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWMFCNTR | Relocation to 1 Centre Street | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2030 | Apr 2031 | Mar 2030 | Apr 2031
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79SRG1 | NYPD - RELOCATE STRATEGIC RESPONSE GROUP TO 521-533 W 57 ST | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79SRG1 | NYPD - RELOCATE STRATEGIC RESPONSE GROUP TO 521-533 W 57 ST | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79SRG1 | NYPD - RELOCATE STRATEGIC RESPONSE GROUP TO 521-533 W 57 ST | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79SRG1 | NYPD - RELOCATE STRATEGIC RESPONSE GROUP TO 521-533 W 57 ST | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79SRG1 | NYPD - RELOCATE STRATEGIC RESPONSE GROUP TO 521-533 W 57 ST | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79SRG1 | NYPD - RELOCATE STRATEGIC RESPONSE GROUP TO 521-533 W 57 ST | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79SRG1 | NYPD - RELOCATE STRATEGIC RESPONSE GROUP TO 521-533 W 57 ST | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | May 2024 | Sep 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79SRG1 | NYPD - RELOCATE STRATEGIC RESPONSE GROUP TO 521-533 W 57 ST | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79SRG1 | NYPD - RELOCATE STRATEGIC RESPONSE GROUP TO 521-533 W 57 ST | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Dec 2024 | Feb 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79SRG1 | NYPD - RELOCATE STRATEGIC RESPONSE GROUP TO 521-533 W 57 ST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Mar 2025 | Feb 2025 | Mar 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79TEDR | Traffic Enforcement Division Relocation | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79TEDR | Traffic Enforcement Division Relocation | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79TEDR | Traffic Enforcement Division Relocation | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79TEDR | Traffic Enforcement Division Relocation | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79TEDR | Traffic Enforcement Division Relocation | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79TEDR | Traffic Enforcement Division Relocation | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79TEDR | Traffic Enforcement Division Relocation | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79TEDR | Traffic Enforcement Division Relocation | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79TEDR | Traffic Enforcement Division Relocation | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79TEDR | Traffic Enforcement Division Relocation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Aug 2023 | Nov 2019 | Aug 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79WTC | NYPD - RELOCATE OF WORLD TRADE CENTER COMMAND | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79WTC | NYPD - RELOCATE OF WORLD TRADE CENTER COMMAND | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79WTC | NYPD - RELOCATE OF WORLD TRADE CENTER COMMAND | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79WTC | NYPD - RELOCATE OF WORLD TRADE CENTER COMMAND | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79WTC | NYPD - RELOCATE OF WORLD TRADE CENTER COMMAND | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79WTC | NYPD - RELOCATE OF WORLD TRADE CENTER COMMAND | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79WTC | NYPD - RELOCATE OF WORLD TRADE CENTER COMMAND | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79WTC | NYPD - RELOCATE OF WORLD TRADE CENTER COMMAND | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79WTC | NYPD - RELOCATE OF WORLD TRADE CENTER COMMAND | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79WTC | NYPD - RELOCATE OF WORLD TRADE CENTER COMMAND | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325A | 1 CENTRE ST.- 25TH FL BUILDOUT | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2022 | Aug 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325A | 1 CENTRE ST.- 25TH FL BUILDOUT | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2022 | Dec 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325A | 1 CENTRE ST.- 25TH FL BUILDOUT | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2022 | Jun 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325A | 1 CENTRE ST.- 25TH FL BUILDOUT | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325A | 1 CENTRE ST.- 25TH FL BUILDOUT | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2023 | Jan 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325A | 1 CENTRE ST.- 25TH FL BUILDOUT | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2024 | May 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325A | 1 CENTRE ST.- 25TH FL BUILDOUT | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2024 | Sep 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325A | 1 CENTRE ST.- 25TH FL BUILDOUT | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2024 | Dec 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325A | 1 CENTRE ST.- 25TH FL BUILDOUT | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2024 | Feb 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325A | 1 CENTRE ST.- 25TH FL BUILDOUT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Feb 2025 | Mar 2030
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193ELV | 1 CENTRE ST - ELEVATOR MODERNIZATION | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193ELV | 1 CENTRE ST - ELEVATOR MODERNIZATION | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193ELV | 1 CENTRE ST - ELEVATOR MODERNIZATION | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193ELV | 1 CENTRE ST - ELEVATOR MODERNIZATION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Aug 2024 | Jun 2024 | Aug 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193ELV | 1 CENTRE ST - ELEVATOR MODERNIZATION | 5 | CONSTRUCTION TO 25% | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193ELV | 1 CENTRE ST - ELEVATOR MODERNIZATION | 6 | CONSTRUCTION TO 50% | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193ELV | 1 CENTRE ST - ELEVATOR MODERNIZATION | 7 | CONSTRUCTION TO 75% | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193ELV | 1 CENTRE ST - ELEVATOR MODERNIZATION | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2026 | Apr 2026 | Jan 2026 | Apr 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193ELV | 1 CENTRE ST - ELEVATOR MODERNIZATION | 9 | SUBSTANTIAL COMPLETION | Apr 2026 | Jun 2026 | Apr 2026 | Jun 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193ELV | 1 CENTRE ST - ELEVATOR MODERNIZATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Jul 2026 | Jun 2026 | Jul 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193FANS | 1 CENTRE ST. - REPLACEMENT OF LOBBY FANS | 1 | DEVELOP SCOPE | May 2008 | Jul 2008 | Oct 1996 | Jan 1997
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193FANS | 1 CENTRE ST. - REPLACEMENT OF LOBBY FANS | 2 | PRELIMINARY DESIGN | Jul 2008 | Oct 2008 | Jan 1997 | Apr 1997
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193FANS | 1 CENTRE ST. - REPLACEMENT OF LOBBY FANS | 3 | FINAL DESIGN | Oct 2008 | Jan 2009 | Apr 1997 | Jul 1997
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193FANS | 1 CENTRE ST. - REPLACEMENT OF LOBBY FANS | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2009 | Apr 2009 | Jul 1997 | Oct 1997
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193FANS | 1 CENTRE ST. - REPLACEMENT OF LOBBY FANS | 5 | CONSTRUCTION TO 25% | Apr 2009 | Apr 2010 | Oct 1997 | Oct 1998
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193FANS | 1 CENTRE ST. - REPLACEMENT OF LOBBY FANS | 6 | CONSTRUCTION TO 50% | Apr 2010 | Apr 2011 | Jun 2026 | Jun 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193FANS | 1 CENTRE ST. - REPLACEMENT OF LOBBY FANS | 7 | CONSTRUCTION TO 75% | Apr 2011 | Apr 2012 | Jun 2027 | Jun 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193FANS | 1 CENTRE ST. - REPLACEMENT OF LOBBY FANS | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2012 | Apr 2013 | Apr 2012 | Apr 2013
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193FANS | 1 CENTRE ST. - REPLACEMENT OF LOBBY FANS | 9 | SUBSTANTIAL COMPLETION | Apr 2013 | Mar 2014 | Apr 2013 | Mar 2014
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193FANS | 1 CENTRE ST. - REPLACEMENT OF LOBBY FANS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2014 | Dec 2014 | Mar 2014 | Jun 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195ADA | 80 CENTRE ST - ADA LIFT | 1 | DEVELOP SCOPE | Jun 2021 | Aug 2021 | Jun 2021 | Aug 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195ADA | 80 CENTRE ST - ADA LIFT | 2 | PRELIMINARY DESIGN | Aug 2021 | Dec 2021 | Aug 2021 | Dec 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195ADA | 80 CENTRE ST - ADA LIFT | 3 | FINAL DESIGN | Dec 2021 | Jun 2022 | Dec 2021 | Jun 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195ADA | 80 CENTRE ST - ADA LIFT | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195ADA | 80 CENTRE ST - ADA LIFT | 5 | CONSTRUCTION TO 25% | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195ADA | 80 CENTRE ST - ADA LIFT | 6 | CONSTRUCTION TO 50% | Jan 2023 | May 2023 | Jan 2023 | May 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195ADA | 80 CENTRE ST - ADA LIFT | 7 | CONSTRUCTION TO 75% | May 2023 | Sep 2023 | May 2023 | Sep 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195ADA | 80 CENTRE ST - ADA LIFT | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Dec 2023 | Sep 2023 | Dec 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195ADA | 80 CENTRE ST - ADA LIFT | 9 | SUBSTANTIAL COMPLETION | Dec 2023 | Feb 2024 | Dec 2023 | Feb 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195ADA | 80 CENTRE ST - ADA LIFT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2024 | Mar 2024 | Feb 2024 | Mar 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195RF | 80 CENTRE ST.- ROOF REPLACEMENT | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195RF | 80 CENTRE ST.- ROOF REPLACEMENT | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195RF | 80 CENTRE ST.- ROOF REPLACEMENT | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195RF | 80 CENTRE ST.- ROOF REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195RF | 80 CENTRE ST.- ROOF REPLACEMENT | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195RF | 80 CENTRE ST.- ROOF REPLACEMENT | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195RF | 80 CENTRE ST.- ROOF REPLACEMENT | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | May 2024 | Sep 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195RF | 80 CENTRE ST.- ROOF REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195RF | 80 CENTRE ST.- ROOF REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Dec 2024 | Feb 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195RF | 80 CENTRE ST.- ROOF REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Mar 2026 | Feb 2025 | Mar 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266FE | 125 WORTH ST - FREIGHT ELEVATOR | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266FE | 125 WORTH ST - FREIGHT ELEVATOR | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266FE | 125 WORTH ST - FREIGHT ELEVATOR | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266FE | 125 WORTH ST - FREIGHT ELEVATOR | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266FE | 125 WORTH ST - FREIGHT ELEVATOR | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266FE | 125 WORTH ST - FREIGHT ELEVATOR | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266FE | 125 WORTH ST - FREIGHT ELEVATOR | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | May 2024 | Sep 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266FE | 125 WORTH ST - FREIGHT ELEVATOR | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266FE | 125 WORTH ST - FREIGHT ELEVATOR | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Dec 2024 | Feb 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266FE | 125 WORTH ST - FREIGHT ELEVATOR | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Mar 2025 | Feb 2025 | Mar 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266TOIL | 125 WORTH ST.- CODE COMPLIANT TOILET UPGRADES | 1 | DEVELOP SCOPE | Jan 2016 | Apr 2016 | Jun 2021 | Aug 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266TOIL | 125 WORTH ST.- CODE COMPLIANT TOILET UPGRADES | 2 | BID AWARD AND REGISTER CONTRCT | Apr 2016 | Oct 2016 | Aug 2021 | Dec 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266TOIL | 125 WORTH ST.- CODE COMPLIANT TOILET UPGRADES | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Nov 2016 | Dec 2021 | Jun 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266TOIL | 125 WORTH ST.- CODE COMPLIANT TOILET UPGRADES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2016 | Jan 2017 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266TOIL | 125 WORTH ST.- CODE COMPLIANT TOILET UPGRADES | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2016 | Dec 2016 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266TOIL | 125 WORTH ST.- CODE COMPLIANT TOILET UPGRADES | 6 | CONSTRUCTION TO 50% | Nov 2016 | Dec 2016 | Jan 2023 | May 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266TOIL | 125 WORTH ST.- CODE COMPLIANT TOILET UPGRADES | 7 | CONSTRUCTION TO 75% | Nov 2016 | Dec 2016 | May 2023 | Sep 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266TOIL | 125 WORTH ST.- CODE COMPLIANT TOILET UPGRADES | 8 | ORIGINAL EQUIP & FURNISHING | Nov 2016 | Dec 2016 | Sep 2023 | Dec 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266TOIL | 125 WORTH ST.- CODE COMPLIANT TOILET UPGRADES | 9 | SUBSTANTIAL COMPLETION | Nov 2016 | Dec 2016 | Dec 2023 | Feb 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266TOIL | 125 WORTH ST.- CODE COMPLIANT TOILET UPGRADES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2016 | Dec 2016 | Feb 2024 | Mar 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW282253B | 253 BROADWAY - ADA LIFT REPLACEMENT | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW282253B | 253 BROADWAY - ADA LIFT REPLACEMENT | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW282253B | 253 BROADWAY - ADA LIFT REPLACEMENT | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW282253B | 253 BROADWAY - ADA LIFT REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW282253B | 253 BROADWAY - ADA LIFT REPLACEMENT | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW282253B | 253 BROADWAY - ADA LIFT REPLACEMENT | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW282253B | 253 BROADWAY - ADA LIFT REPLACEMENT | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW282253B | 253 BROADWAY - ADA LIFT REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW282253B | 253 BROADWAY - ADA LIFT REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW282253B | 253 BROADWAY - ADA LIFT REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW282-2L | 2 LAFAYETTE BATHROOMS ADA RENOVATION | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW282-2L | 2 LAFAYETTE BATHROOMS ADA RENOVATION | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW282-2L | 2 LAFAYETTE BATHROOMS ADA RENOVATION | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW282-2L | 2 LAFAYETTE BATHROOMS ADA RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW282-2L | 2 LAFAYETTE BATHROOMS ADA RENOVATION | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW282-2L | 2 LAFAYETTE BATHROOMS ADA RENOVATION | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW282-2L | 2 LAFAYETTE BATHROOMS ADA RENOVATION | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW282-2L | 2 LAFAYETTE BATHROOMS ADA RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW282-2L | 2 LAFAYETTE BATHROOMS ADA RENOVATION | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW282-2L | 2 LAFAYETTE BATHROOMS ADA RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Jun 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW28280C | 80 CENTRE ST.- ADA IMPROVEMENTS | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW28280C | 80 CENTRE ST.- ADA IMPROVEMENTS | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW28280C | 80 CENTRE ST.- ADA IMPROVEMENTS | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW28280C | 80 CENTRE ST.- ADA IMPROVEMENTS | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW28280C | 80 CENTRE ST.- ADA IMPROVEMENTS | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW28280C | 80 CENTRE ST.- ADA IMPROVEMENTS | 6 | CONSTRUCTION TO 50% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW28280C | 80 CENTRE ST.- ADA IMPROVEMENTS | 7 | CONSTRUCTION TO 75% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW28280C | 80 CENTRE ST.- ADA IMPROVEMENTS | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW28280C | 80 CENTRE ST.- ADA IMPROVEMENTS | 9 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW28280C | 80 CENTRE ST.- ADA IMPROVEMENTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Jun 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293125D | 125 WORTH STREET - FIRE ALARM -SPRINKLERS | 1 | DEVELOP SCOPE | Jun 2021 | Aug 2021 | Jun 2021 | Aug 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293125D | 125 WORTH STREET - FIRE ALARM -SPRINKLERS | 2 | PRELIMINARY DESIGN | Aug 2021 | Dec 2021 | Aug 2021 | Dec 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293125D | 125 WORTH STREET - FIRE ALARM -SPRINKLERS | 3 | FINAL DESIGN | Dec 2021 | Jun 2022 | Dec 2021 | Jun 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293125D | 125 WORTH STREET - FIRE ALARM -SPRINKLERS | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293125D | 125 WORTH STREET - FIRE ALARM -SPRINKLERS | 5 | CONSTRUCTION TO 25% | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293125D | 125 WORTH STREET - FIRE ALARM -SPRINKLERS | 6 | CONSTRUCTION TO 50% | Jan 2023 | May 2023 | Jan 2023 | May 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293125D | 125 WORTH STREET - FIRE ALARM -SPRINKLERS | 7 | CONSTRUCTION TO 75% | May 2023 | Sep 2023 | May 2023 | Sep 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293125D | 125 WORTH STREET - FIRE ALARM -SPRINKLERS | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Dec 2023 | Sep 2023 | Dec 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293125D | 125 WORTH STREET - FIRE ALARM -SPRINKLERS | 9 | SUBSTANTIAL COMPLETION | Dec 2023 | Feb 2024 | Dec 2023 | Feb 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293125D | 125 WORTH STREET - FIRE ALARM -SPRINKLERS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2024 | Mar 2024 | Feb 2024 | Mar 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW2931C | 1 CENTRE STREET - FIRE SPRINKLERS | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Aug 2019
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW2931C | 1 CENTRE STREET - FIRE SPRINKLERS | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Aug 2019 | Dec 2019
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW2931C | 1 CENTRE STREET - FIRE SPRINKLERS | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Dec 2019 | Jun 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW2931C | 1 CENTRE STREET - FIRE SPRINKLERS | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jun 2024 | Aug 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW2931C | 1 CENTRE STREET - FIRE SPRINKLERS | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Aug 2024 | Dec 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW2931C | 1 CENTRE STREET - FIRE SPRINKLERS | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Dec 2024 | Apr 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW2931C | 1 CENTRE STREET - FIRE SPRINKLERS | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Apr 2025 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW2931C | 1 CENTRE STREET - FIRE SPRINKLERS | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Sep 2021 | Dec 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW2931C | 1 CENTRE STREET - FIRE SPRINKLERS | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Dec 2021 | Feb 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW2931C | 1 CENTRE STREET - FIRE SPRINKLERS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Feb 2022 | Mar 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293280A | 280 Broadway Sprinkler | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2020 | Aug 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293280A | 280 Broadway Sprinkler | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2020 | Dec 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293280A | 280 Broadway Sprinkler | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2020 | Jun 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293280A | 280 Broadway Sprinkler | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2021 | Sep 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293280A | 280 Broadway Sprinkler | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293280A | 280 Broadway Sprinkler | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | Jan 2022 | May 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293280A | 280 Broadway Sprinkler | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | May 2022 | Sep 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293280A | 280 Broadway Sprinkler | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Sep 2022 | Dec 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293280A | 280 Broadway Sprinkler | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Dec 2022 | Feb 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293280A | 280 Broadway Sprinkler | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Mar 2025 | Feb 2023 | Jun 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293GLDS | 100 Gold St Sprinkler | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293GLDS | 100 Gold St Sprinkler | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293GLDS | 100 Gold St Sprinkler | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293GLDS | 100 Gold St Sprinkler | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293GLDS | 100 Gold St Sprinkler | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293GLDS | 100 Gold St Sprinkler | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293GLDS | 100 Gold St Sprinkler | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | May 2024 | Sep 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293GLDS | 100 Gold St Sprinkler | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293GLDS | 100 Gold St Sprinkler | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Dec 2024 | Feb 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293GLDS | 100 Gold St Sprinkler | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Mar 2025 | Feb 2025 | Mar 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW308PS1 | MAYOR'S OFFICE - 100 GOLD ST - PRINTSHOP UPGRADE | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Aug 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW308PS1 | MAYOR'S OFFICE - 100 GOLD ST - PRINTSHOP UPGRADE | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW308PS1 | MAYOR'S OFFICE - 100 GOLD ST - PRINTSHOP UPGRADE | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW308PS1 | MAYOR'S OFFICE - 100 GOLD ST - PRINTSHOP UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW308PS1 | MAYOR'S OFFICE - 100 GOLD ST - PRINTSHOP UPGRADE | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW308PS1 | MAYOR'S OFFICE - 100 GOLD ST - PRINTSHOP UPGRADE | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2022 | May 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW308PS1 | MAYOR'S OFFICE - 100 GOLD ST - PRINTSHOP UPGRADE | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2022 | Sep 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW308PS1 | MAYOR'S OFFICE - 100 GOLD ST - PRINTSHOP UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW308PS1 | MAYOR'S OFFICE - 100 GOLD ST - PRINTSHOP UPGRADE | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2022 | Feb 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW308PS1 | MAYOR'S OFFICE - 100 GOLD ST - PRINTSHOP UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Feb 2023 | Sep 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310COOL | 31 CHAMBERS ST.- COLD STORAGE SYSTEM FOR DORIS | 1 | DEVELOP SCOPE | Jun 2006 | Sep 2006 | Jun 2016 | Aug 2016
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310COOL | 31 CHAMBERS ST.- COLD STORAGE SYSTEM FOR DORIS | 2 | PRELIMINARY DESIGN | Sep 2006 | Jan 2007 | Aug 2016 | Dec 2016
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310COOL | 31 CHAMBERS ST.- COLD STORAGE SYSTEM FOR DORIS | 3 | FINAL DESIGN | Jan 2007 | Jul 2007 | Dec 2016 | Jun 2017
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310COOL | 31 CHAMBERS ST.- COLD STORAGE SYSTEM FOR DORIS | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2007 | Oct 2007 | Jun 2017 | Sep 2017
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310COOL | 31 CHAMBERS ST.- COLD STORAGE SYSTEM FOR DORIS | 5 | CONSTRUCTION TO 25% | Oct 2007 | Feb 2008 | Sep 2017 | Jan 2018
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310COOL | 31 CHAMBERS ST.- COLD STORAGE SYSTEM FOR DORIS | 6 | CONSTRUCTION TO 50% | Feb 2008 | Jun 2008 | Jan 2018 | May 2018
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310COOL | 31 CHAMBERS ST.- COLD STORAGE SYSTEM FOR DORIS | 7 | CONSTRUCTION TO 75% | Jun 2008 | Oct 2008 | May 2018 | Sep 2018
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310COOL | 31 CHAMBERS ST.- COLD STORAGE SYSTEM FOR DORIS | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2008 | Jan 2009 | Sep 2018 | Dec 2018
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310COOL | 31 CHAMBERS ST.- COLD STORAGE SYSTEM FOR DORIS | 9 | SUBSTANTIAL COMPLETION | Jan 2009 | Mar 2009 | Dec 2018 | Feb 2019
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310COOL | 31 CHAMBERS ST.- COLD STORAGE SYSTEM FOR DORIS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2009 | Apr 2009 | Feb 2019 | Jun 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310FAN | 31 CHAMBERS ST. - REPLACEMENT OF FAN COIL UNITS ON FIRST FL. | 1 | DEVELOP SCOPE | Jan 2007 | Feb 2007 | Jan 2007 | Mar 2007
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310FAN | 31 CHAMBERS ST. - REPLACEMENT OF FAN COIL UNITS ON FIRST FL. | 2 | PRELIMINARY DESIGN | Mar 2007 | May 2007 | Apr 2007 | Jul 2007
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310FAN | 31 CHAMBERS ST. - REPLACEMENT OF FAN COIL UNITS ON FIRST FL. | 3 | FINAL DESIGN | Jun 2007 | May 2008 | Jul 2007 | Jan 2008
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310FAN | 31 CHAMBERS ST. - REPLACEMENT OF FAN COIL UNITS ON FIRST FL. | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2008 | Oct 2008 | Jan 2008 | Apr 2008
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310FAN | 31 CHAMBERS ST. - REPLACEMENT OF FAN COIL UNITS ON FIRST FL. | 5 | CONSTRUCTION TO 25% | Nov 2008 | Dec 2008 | Apr 2008 | Dec 2010
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310FAN | 31 CHAMBERS ST. - REPLACEMENT OF FAN COIL UNITS ON FIRST FL. | 6 | CONSTRUCTION TO 50% | Jan 2009 | Feb 2009 | Jun 2027 | Jan 2030
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310FAN | 31 CHAMBERS ST. - REPLACEMENT OF FAN COIL UNITS ON FIRST FL. | 7 | CONSTRUCTION TO 75% | Mar 2009 | Mar 2009 | Jan 2030 | Sep 2032
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310FAN | 31 CHAMBERS ST. - REPLACEMENT OF FAN COIL UNITS ON FIRST FL. | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2009 | Mar 2009 | Sep 2032 | Feb 2033
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310FAN | 31 CHAMBERS ST. - REPLACEMENT OF FAN COIL UNITS ON FIRST FL. | 9 | SUBSTANTIAL COMPLETION | Apr 2009 | May 2009 | Mar 2033 | May 2033
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310FAN | 31 CHAMBERS ST. - REPLACEMENT OF FAN COIL UNITS ON FIRST FL. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2009 | Jun 2009 | May 2033 | May 2033
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW316EL | 280 BROADWAY - VAULT, ELECTRICAL AND FIRE ALARM UPGRADE | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW316EL | 280 BROADWAY - VAULT, ELECTRICAL AND FIRE ALARM UPGRADE | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW316EL | 280 BROADWAY - VAULT, ELECTRICAL AND FIRE ALARM UPGRADE | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW316EL | 280 BROADWAY - VAULT, ELECTRICAL AND FIRE ALARM UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Aug 2024 | Jun 2024 | Aug 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW316EL | 280 BROADWAY - VAULT, ELECTRICAL AND FIRE ALARM UPGRADE | 5 | CONSTRUCTION TO 25% | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW316EL | 280 BROADWAY - VAULT, ELECTRICAL AND FIRE ALARM UPGRADE | 6 | CONSTRUCTION TO 50% | Dec 2024 | Apr 2025 | Dec 2024 | Apr 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW316EL | 280 BROADWAY - VAULT, ELECTRICAL AND FIRE ALARM UPGRADE | 7 | CONSTRUCTION TO 75% | Apr 2025 | Aug 2025 | Apr 2025 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW316EL | 280 BROADWAY - VAULT, ELECTRICAL AND FIRE ALARM UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | Aug 2025 | Nov 2025 | Aug 2025 | Nov 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW316EL | 280 BROADWAY - VAULT, ELECTRICAL AND FIRE ALARM UPGRADE | 9 | SUBSTANTIAL COMPLETION | Nov 2025 | Jan 2026 | Nov 2025 | Jan 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW316EL | 280 BROADWAY - VAULT, ELECTRICAL AND FIRE ALARM UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2026 | Feb 2026 | Jan 2026 | Feb 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324CLIP | DCAS - Replacement of CLIPS & Direct Order App | 1 | DEVELOP SCOPE | Jun 2025 | Aug 2025 | Jun 2025 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324CLIP | DCAS - Replacement of CLIPS & Direct Order App | 2 | PRELIMINARY DESIGN | Aug 2025 | Dec 2025 | Aug 2025 | Dec 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324CLIP | DCAS - Replacement of CLIPS & Direct Order App | 3 | FINAL DESIGN | Dec 2025 | Jun 2026 | Dec 2025 | Jun 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324CLIP | DCAS - Replacement of CLIPS & Direct Order App | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2026 | Sep 2026 | Jun 2026 | Sep 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324CLIP | DCAS - Replacement of CLIPS & Direct Order App | 5 | CONSTRUCTION TO 25% | Sep 2026 | Jan 2027 | Sep 2026 | Jan 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324CLIP | DCAS - Replacement of CLIPS & Direct Order App | 6 | CONSTRUCTION TO 50% | Jan 2027 | May 2027 | Jan 2027 | May 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324CLIP | DCAS - Replacement of CLIPS & Direct Order App | 7 | CONSTRUCTION TO 75% | May 2027 | Sep 2027 | May 2027 | Sep 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324CLIP | DCAS - Replacement of CLIPS & Direct Order App | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2027 | Dec 2027 | Sep 2027 | Dec 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324CLIP | DCAS - Replacement of CLIPS & Direct Order App | 9 | SUBSTANTIAL COMPLETION | Dec 2027 | Feb 2028 | Dec 2027 | Feb 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324CLIP | DCAS - Replacement of CLIPS & Direct Order App | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2028 | Mar 2028 | Feb 2028 | Mar 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324OMIS | DCAS IT LUMP SUM | 1 | DEVELOP SCOPE | Jun 2004 | Aug 2004 | Jun 2009 | Aug 2009
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324OMIS | DCAS IT LUMP SUM | 2 | PRELIMINARY DESIGN | Aug 2004 | Dec 2004 | Aug 2009 | Dec 2009
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324OMIS | DCAS IT LUMP SUM | 3 | FINAL DESIGN | Dec 2004 | Jun 2005 | Dec 2009 | Jun 2010
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324OMIS | DCAS IT LUMP SUM | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2005 | Sep 2005 | Jun 2010 | Sep 2010
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324OMIS | DCAS IT LUMP SUM | 5 | CONSTRUCTION TO 25% | Sep 2005 | May 2008 | Sep 2010 | May 2013
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324OMIS | DCAS IT LUMP SUM | 6 | CONSTRUCTION TO 50% | May 2008 | Dec 2010 | May 2013 | Dec 2015
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324OMIS | DCAS IT LUMP SUM | 7 | CONSTRUCTION TO 75% | Dec 2010 | Aug 2013 | Dec 2015 | Aug 2018
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324OMIS | DCAS IT LUMP SUM | 8 | ORIGINAL EQUIP & FURNISHING | Aug 2013 | Mar 2016 | Aug 2018 | Mar 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324OMIS | DCAS IT LUMP SUM | 9 | SUBSTANTIAL COMPLETION | Mar 2016 | Nov 2018 | Jun 2028 | Jan 2031
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324OMIS | DCAS IT LUMP SUM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2018 | Jul 2021 | Jan 2031 | Sep 2033
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326NYCC | CITY COUNCIL - 250 BROADWAY, FLS 14-18, 30 RENO & EXPANSION | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2028 | Aug 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326NYCC | CITY COUNCIL - 250 BROADWAY, FLS 14-18, 30 RENO & EXPANSION | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2028 | Dec 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326NYCC | CITY COUNCIL - 250 BROADWAY, FLS 14-18, 30 RENO & EXPANSION | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2028 | Jun 2029
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326NYCC | CITY COUNCIL - 250 BROADWAY, FLS 14-18, 30 RENO & EXPANSION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2029 | Sep 2029
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326NYCC | CITY COUNCIL - 250 BROADWAY, FLS 14-18, 30 RENO & EXPANSION | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2029 | Jan 2030
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326NYCC | CITY COUNCIL - 250 BROADWAY, FLS 14-18, 30 RENO & EXPANSION | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2030 | May 2030
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326NYCC | CITY COUNCIL - 250 BROADWAY, FLS 14-18, 30 RENO & EXPANSION | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2030 | Sep 2030
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326NYCC | CITY COUNCIL - 250 BROADWAY, FLS 14-18, 30 RENO & EXPANSION | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2030 | Dec 2030
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326NYCC | CITY COUNCIL - 250 BROADWAY, FLS 14-18, 30 RENO & EXPANSION | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2030 | Feb 2031
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326NYCC | CITY COUNCIL - 250 BROADWAY, FLS 14-18, 30 RENO & EXPANSION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Feb 2031 | Mar 2031
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OMBP | OMB Pantry at 255 Greenwich | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Dec 2020 | Jun 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OMBP | OMB Pantry at 255 Greenwich | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2021 | Jun 2021 | Jun 2021 | Sep 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OMBP | OMB Pantry at 255 Greenwich | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2021 | May 2021 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OMBP | OMB Pantry at 255 Greenwich | 6 | CONSTRUCTION TO 50% | Apr 2021 | May 2021 | Jan 2022 | May 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OMBP | OMB Pantry at 255 Greenwich | 7 | CONSTRUCTION TO 75% | Apr 2021 | May 2021 | May 2022 | Sep 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OMBP | OMB Pantry at 255 Greenwich | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2021 | May 2021 | Sep 2022 | Dec 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OMBP | OMB Pantry at 255 Greenwich | 9 | SUBSTANTIAL COMPLETION | Apr 2021 | May 2021 | Dec 2022 | Feb 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OMBP | OMB Pantry at 255 Greenwich | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2021 | May 2021 | Feb 2023 | Mar 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAM | LAW DEPT - RAISE THE AGE - MANHATTAN | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2022 | Aug 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAM | LAW DEPT - RAISE THE AGE - MANHATTAN | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2022 | Dec 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAM | LAW DEPT - RAISE THE AGE - MANHATTAN | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2022 | Jun 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAM | LAW DEPT - RAISE THE AGE - MANHATTAN | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAM | LAW DEPT - RAISE THE AGE - MANHATTAN | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2023 | Jan 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAM | LAW DEPT - RAISE THE AGE - MANHATTAN | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jun 2027 | Sep 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAM | LAW DEPT - RAISE THE AGE - MANHATTAN | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | Sep 2027 | Jan 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAM | LAW DEPT - RAISE THE AGE - MANHATTAN | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Jan 2028 | Apr 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAM | LAW DEPT - RAISE THE AGE - MANHATTAN | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Apr 2028 | Jun 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAM | LAW DEPT - RAISE THE AGE - MANHATTAN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Jun 2028 | Jul 2032
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM03 | CBMN - RELOCATE COMM BD 3 FROM 59 E. 4TH STREET | 1 | DEVELOP SCOPE | Sep 2014 | Nov 2014 | Jun 2026 | Aug 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM03 | CBMN - RELOCATE COMM BD 3 FROM 59 E. 4TH STREET | 2 | PRELIMINARY DESIGN | Nov 2014 | Mar 2015 | Aug 2026 | Dec 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM03 | CBMN - RELOCATE COMM BD 3 FROM 59 E. 4TH STREET | 3 | FINAL DESIGN | Mar 2015 | Sep 2015 | Dec 2026 | Jun 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM03 | CBMN - RELOCATE COMM BD 3 FROM 59 E. 4TH STREET | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2015 | Dec 2015 | Jun 2027 | Sep 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM03 | CBMN - RELOCATE COMM BD 3 FROM 59 E. 4TH STREET | 5 | CONSTRUCTION TO 25% | Dec 2015 | Apr 2016 | Sep 2027 | Jan 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM03 | CBMN - RELOCATE COMM BD 3 FROM 59 E. 4TH STREET | 6 | CONSTRUCTION TO 50% | Apr 2016 | Aug 2016 | Jan 2028 | May 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM03 | CBMN - RELOCATE COMM BD 3 FROM 59 E. 4TH STREET | 7 | CONSTRUCTION TO 75% | Aug 2016 | Dec 2016 | May 2028 | Sep 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM03 | CBMN - RELOCATE COMM BD 3 FROM 59 E. 4TH STREET | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2016 | Mar 2017 | Sep 2028 | Dec 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM03 | CBMN - RELOCATE COMM BD 3 FROM 59 E. 4TH STREET | 9 | SUBSTANTIAL COMPLETION | Mar 2017 | May 2017 | Dec 2028 | Feb 2029
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM03 | CBMN - RELOCATE COMM BD 3 FROM 59 E. 4TH STREET | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2017 | Jun 2017 | Feb 2029 | Mar 2029
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW327PLZ2 | 1 CENTRE STREET PLAZA REHABILITATION | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Aug 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW327PLZ2 | 1 CENTRE STREET PLAZA REHABILITATION | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW327PLZ2 | 1 CENTRE STREET PLAZA REHABILITATION | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW327PLZ2 | 1 CENTRE STREET PLAZA REHABILITATION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW327PLZ2 | 1 CENTRE STREET PLAZA REHABILITATION | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Jun 2024 | Sep 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW327PLZ2 | 1 CENTRE STREET PLAZA REHABILITATION | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jun 2027 | Sep 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW327PLZ2 | 1 CENTRE STREET PLAZA REHABILITATION | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | Sep 2027 | Jan 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW327PLZ2 | 1 CENTRE STREET PLAZA REHABILITATION | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Jan 2028 | Apr 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW327PLZ2 | 1 CENTRE STREET PLAZA REHABILITATION | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Apr 2028 | Jun 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW327PLZ2 | 1 CENTRE STREET PLAZA REHABILITATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Jun 2028 | Jun 2031
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340FIP2 | BOE- FACILITIES IMPROVEMENT PROJECT | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2024 | Aug 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340FIP2 | BOE- FACILITIES IMPROVEMENT PROJECT | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2024 | Dec 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340FIP2 | BOE- FACILITIES IMPROVEMENT PROJECT | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2024 | Jun 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340FIP2 | BOE- FACILITIES IMPROVEMENT PROJECT | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2025 | Sep 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340FIP2 | BOE- FACILITIES IMPROVEMENT PROJECT | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2025 | Jan 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340FIP2 | BOE- FACILITIES IMPROVEMENT PROJECT | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2026 | May 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340FIP2 | BOE- FACILITIES IMPROVEMENT PROJECT | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2026 | Sep 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340FIP2 | BOE- FACILITIES IMPROVEMENT PROJECT | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2026 | Dec 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340FIP2 | BOE- FACILITIES IMPROVEMENT PROJECT | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2026 | Feb 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340FIP2 | BOE- FACILITIES IMPROVEMENT PROJECT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Feb 2027 | Mar 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357ELC2 | 253 BROADWAY- ELECTRICAL UPGRADES PHASE 2 | 1 | DEVELOP SCOPE | May 2016 | Jul 2016 | May 2016 | Aug 2016
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357ELC2 | 253 BROADWAY- ELECTRICAL UPGRADES PHASE 2 | 2 | PRELIMINARY DESIGN | Jul 2016 | Nov 2016 | Jun 2020 | Sep 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357ELC2 | 253 BROADWAY- ELECTRICAL UPGRADES PHASE 2 | 3 | FINAL DESIGN | Nov 2016 | May 2017 | Sep 2020 | Mar 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357ELC2 | 253 BROADWAY- ELECTRICAL UPGRADES PHASE 2 | 4 | BID AWARD AND REGISTER CONTRCT | May 2017 | Aug 2017 | Mar 2021 | Jun 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357ELC2 | 253 BROADWAY- ELECTRICAL UPGRADES PHASE 2 | 5 | CONSTRUCTION TO 25% | Aug 2017 | Dec 2017 | Jun 2021 | Oct 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357ELC2 | 253 BROADWAY- ELECTRICAL UPGRADES PHASE 2 | 6 | CONSTRUCTION TO 50% | Dec 2017 | Apr 2018 | Oct 2021 | Feb 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357ELC2 | 253 BROADWAY- ELECTRICAL UPGRADES PHASE 2 | 7 | CONSTRUCTION TO 75% | Apr 2018 | Aug 2018 | Feb 2022 | Jun 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357ELC2 | 253 BROADWAY- ELECTRICAL UPGRADES PHASE 2 | 8 | ORIGINAL EQUIP & FURNISHING | Aug 2018 | Nov 2018 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357ELC2 | 253 BROADWAY- ELECTRICAL UPGRADES PHASE 2 | 9 | SUBSTANTIAL COMPLETION | Nov 2018 | Jan 2019 | Sep 2023 | Nov 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357ELC2 | 253 BROADWAY- ELECTRICAL UPGRADES PHASE 2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2019 | Feb 2019 | Nov 2023 | Dec 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357STM2 | 253 BROADWAY - RECONSTRUCT STEAM STATION | 1 | DEVELOP SCOPE | Jan 2017 | Mar 2017 | Jun 2021 | Aug 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357STM2 | 253 BROADWAY - RECONSTRUCT STEAM STATION | 2 | PRELIMINARY DESIGN | Apr 2017 | Jul 2017 | Jun 2020 | Sep 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357STM2 | 253 BROADWAY - RECONSTRUCT STEAM STATION | 3 | FINAL DESIGN | Jul 2017 | Jan 2018 | Sep 2020 | Mar 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357STM2 | 253 BROADWAY - RECONSTRUCT STEAM STATION | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2018 | Apr 2018 | Mar 2021 | Jun 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357STM2 | 253 BROADWAY - RECONSTRUCT STEAM STATION | 5 | CONSTRUCTION TO 25% | Apr 2018 | Aug 2018 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357STM2 | 253 BROADWAY - RECONSTRUCT STEAM STATION | 6 | CONSTRUCTION TO 50% | Aug 2018 | Dec 2018 | Sep 2023 | Jan 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357STM2 | 253 BROADWAY - RECONSTRUCT STEAM STATION | 7 | CONSTRUCTION TO 75% | Dec 2018 | Apr 2019 | Jan 2024 | May 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357STM2 | 253 BROADWAY - RECONSTRUCT STEAM STATION | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2019 | Jul 2019 | May 2024 | Aug 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357STM2 | 253 BROADWAY - RECONSTRUCT STEAM STATION | 9 | SUBSTANTIAL COMPLETION | Jul 2019 | Sep 2019 | Aug 2024 | Oct 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357STM2 | 253 BROADWAY - RECONSTRUCT STEAM STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Oct 2019 | Oct 2024 | Jun 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357VAUL | 253 BROADWAY - VAULT RECONSTRUCTION | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Aug 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357VAUL | 253 BROADWAY - VAULT RECONSTRUCTION | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357VAUL | 253 BROADWAY - VAULT RECONSTRUCTION | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357VAUL | 253 BROADWAY - VAULT RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357VAUL | 253 BROADWAY - VAULT RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357VAUL | 253 BROADWAY - VAULT RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2022 | May 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357VAUL | 253 BROADWAY - VAULT RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2022 | Sep 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357VAUL | 253 BROADWAY - VAULT RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357VAUL | 253 BROADWAY - VAULT RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2022 | Feb 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357VAUL | 253 BROADWAY - VAULT RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2024 | Feb 2023 | Jun 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77115CH | 115 CHRYSTIE ST. - INTERIOR RENOVATIONS | 1 | DEVELOP SCOPE | Jun 2012 | Aug 2012 | Jun 2027 | Aug 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77115CH | 115 CHRYSTIE ST. - INTERIOR RENOVATIONS | 2 | PRELIMINARY DESIGN | Aug 2012 | Dec 2012 | Aug 2027 | Dec 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77115CH | 115 CHRYSTIE ST. - INTERIOR RENOVATIONS | 3 | FINAL DESIGN | Dec 2012 | Jun 2013 | Dec 2027 | Jun 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77115CH | 115 CHRYSTIE ST. - INTERIOR RENOVATIONS | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2013 | Sep 2013 | Jun 2028 | Sep 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77115CH | 115 CHRYSTIE ST. - INTERIOR RENOVATIONS | 5 | CONSTRUCTION TO 25% | Sep 2013 | Jan 2014 | Sep 2028 | Jan 2029
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77115CH | 115 CHRYSTIE ST. - INTERIOR RENOVATIONS | 6 | CONSTRUCTION TO 50% | Jan 2014 | May 2014 | Jan 2029 | May 2029
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77115CH | 115 CHRYSTIE ST. - INTERIOR RENOVATIONS | 7 | CONSTRUCTION TO 75% | May 2014 | Sep 2014 | May 2029 | Sep 2029
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77115CH | 115 CHRYSTIE ST. - INTERIOR RENOVATIONS | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2014 | Dec 2014 | Sep 2029 | Dec 2029
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77115CH | 115 CHRYSTIE ST. - INTERIOR RENOVATIONS | 9 | SUBSTANTIAL COMPLETION | Dec 2014 | Feb 2015 | Dec 2029 | Feb 2030
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77115CH | 115 CHRYSTIE ST. - INTERIOR RENOVATIONS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2015 | Mar 2015 | Feb 2030 | Mar 2030
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77136A | 60 LAFAYETTE ST, 2nd 4th FL - DOP | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Aug 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77136A | 60 LAFAYETTE ST, 2nd 4th FL - DOP | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77136A | 60 LAFAYETTE ST, 2nd 4th FL - DOP | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77136A | 60 LAFAYETTE ST, 2nd 4th FL - DOP | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77136A | 60 LAFAYETTE ST, 2nd 4th FL - DOP | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Jun 2024 | Sep 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77136A | 60 LAFAYETTE ST, 2nd 4th FL - DOP | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77136A | 60 LAFAYETTE ST, 2nd 4th FL - DOP | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | Jan 2025 | May 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77136A | 60 LAFAYETTE ST, 2nd 4th FL - DOP | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | May 2025 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77136A | 60 LAFAYETTE ST, 2nd 4th FL - DOP | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Aug 2025 | Oct 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77136A | 60 LAFAYETTE ST, 2nd 4th FL - DOP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Oct 2025 | Nov 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C09 | 1 CENTRE ST. - 9th Floor Renovation | 1 | DEVELOP SCOPE | Jun 2021 | Aug 2021 | Jun 2025 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C09 | 1 CENTRE ST. - 9th Floor Renovation | 2 | PRELIMINARY DESIGN | Aug 2021 | Dec 2021 | Aug 2025 | Dec 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C09 | 1 CENTRE ST. - 9th Floor Renovation | 3 | FINAL DESIGN | Dec 2021 | Jun 2022 | Dec 2025 | Jun 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C09 | 1 CENTRE ST. - 9th Floor Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Sep 2022 | Jun 2026 | Sep 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C09 | 1 CENTRE ST. - 9th Floor Renovation | 5 | CONSTRUCTION TO 25% | Sep 2022 | Jan 2023 | Sep 2026 | Jan 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C09 | 1 CENTRE ST. - 9th Floor Renovation | 6 | CONSTRUCTION TO 50% | Jan 2023 | May 2023 | Jan 2027 | May 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C09 | 1 CENTRE ST. - 9th Floor Renovation | 7 | CONSTRUCTION TO 75% | May 2023 | Sep 2023 | May 2027 | Sep 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C09 | 1 CENTRE ST. - 9th Floor Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Dec 2023 | Sep 2027 | Dec 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C09 | 1 CENTRE ST. - 9th Floor Renovation | 9 | SUBSTANTIAL COMPLETION | Dec 2023 | Feb 2024 | Dec 2027 | Feb 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C09 | 1 CENTRE ST. - 9th Floor Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2024 | Mar 2024 | Feb 2028 | Mar 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C21 | 1 CENTRE ST. - 21st Floor Renovation | 1 | DEVELOP SCOPE | Jun 2021 | Aug 2021 | Jun 2025 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C21 | 1 CENTRE ST. - 21st Floor Renovation | 2 | PRELIMINARY DESIGN | Aug 2021 | Dec 2021 | Aug 2025 | Dec 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C21 | 1 CENTRE ST. - 21st Floor Renovation | 3 | FINAL DESIGN | Dec 2021 | Jun 2022 | Dec 2025 | Jun 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C21 | 1 CENTRE ST. - 21st Floor Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Sep 2022 | Jun 2026 | Sep 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C21 | 1 CENTRE ST. - 21st Floor Renovation | 5 | CONSTRUCTION TO 25% | Sep 2022 | Jan 2023 | Sep 2026 | Jan 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C21 | 1 CENTRE ST. - 21st Floor Renovation | 6 | CONSTRUCTION TO 50% | Jan 2023 | May 2023 | Jan 2027 | May 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C21 | 1 CENTRE ST. - 21st Floor Renovation | 7 | CONSTRUCTION TO 75% | May 2023 | Sep 2023 | May 2027 | Sep 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C21 | 1 CENTRE ST. - 21st Floor Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Dec 2023 | Sep 2027 | Dec 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C21 | 1 CENTRE ST. - 21st Floor Renovation | 9 | SUBSTANTIAL COMPLETION | Dec 2023 | Feb 2024 | Dec 2027 | Feb 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C21 | 1 CENTRE ST. - 21st Floor Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2024 | Mar 2024 | Feb 2028 | Mar 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722R5 | 22 READE ST.- 5th AND 6th FLOOR BUILDOUT | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Aug 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722R5 | 22 READE ST.- 5th AND 6th FLOOR BUILDOUT | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722R5 | 22 READE ST.- 5th AND 6th FLOOR BUILDOUT | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722R5 | 22 READE ST.- 5th AND 6th FLOOR BUILDOUT | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722R5 | 22 READE ST.- 5th AND 6th FLOOR BUILDOUT | 5 | CONSTRUCTION TO 25% | Sep 2022 | May 2023 | Sep 2022 | May 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722R5 | 22 READE ST.- 5th AND 6th FLOOR BUILDOUT | 6 | CONSTRUCTION TO 50% | May 2023 | Sep 2023 | May 2023 | Sep 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722R5 | 22 READE ST.- 5th AND 6th FLOOR BUILDOUT | 7 | CONSTRUCTION TO 75% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722R5 | 22 READE ST.- 5th AND 6th FLOOR BUILDOUT | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2024 | Apr 2024 | Jan 2024 | Apr 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722R5 | 22 READE ST.- 5th AND 6th FLOOR BUILDOUT | 9 | SUBSTANTIAL COMPLETION | Apr 2024 | Jun 2024 | Apr 2024 | Jun 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722R5 | 22 READE ST.- 5th AND 6th FLOOR BUILDOUT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2024 | Jul 2024 | Jun 2024 | Jul 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DAK01 | NY COUNTY DA'S OFFICE FIRE UPGRADES | 1 | DEVELOP SCOPE | Sep 2012 | Nov 2012 | Sep 2012 | Nov 2012
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DAK01 | NY COUNTY DA'S OFFICE FIRE UPGRADES | 2 | PRELIMINARY DESIGN | Nov 2012 | Mar 2013 | Nov 2012 | Mar 2013
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DAK01 | NY COUNTY DA'S OFFICE FIRE UPGRADES | 3 | FINAL DESIGN | Apr 2013 | Sep 2013 | Apr 2013 | Sep 2013
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DAK01 | NY COUNTY DA'S OFFICE FIRE UPGRADES | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DAK01 | NY COUNTY DA'S OFFICE FIRE UPGRADES | 5 | CONSTRUCTION TO 25% | Dec 2013 | Apr 2014 | Dec 2013 | Apr 2014
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DAK01 | NY COUNTY DA'S OFFICE FIRE UPGRADES | 6 | CONSTRUCTION TO 50% | Apr 2014 | Aug 2014 | Apr 2014 | Aug 2014
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DAK01 | NY COUNTY DA'S OFFICE FIRE UPGRADES | 7 | CONSTRUCTION TO 75% | Aug 2014 | Dec 2014 | Aug 2014 | Dec 2014
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DAK01 | NY COUNTY DA'S OFFICE FIRE UPGRADES | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2014 | Mar 2015 | Dec 2014 | Mar 2015
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DAK01 | NY COUNTY DA'S OFFICE FIRE UPGRADES | 9 | SUBSTANTIAL COMPLETION | Mar 2015 | May 2015 | Mar 2015 | May 2015
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DAK01 | NY COUNTY DA'S OFFICE FIRE UPGRADES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2015 | Jun 2015 | May 2015 | Jun 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DATU | DA MANHATTAN - ADA BATHROOM UPGRADE | 1 | DEVELOP SCOPE | Jun 2021 | Aug 2021 | Jun 2021 | Aug 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DATU | DA MANHATTAN - ADA BATHROOM UPGRADE | 2 | PRELIMINARY DESIGN | Aug 2021 | Dec 2021 | Aug 2021 | Dec 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DATU | DA MANHATTAN - ADA BATHROOM UPGRADE | 3 | FINAL DESIGN | Dec 2021 | Jun 2022 | Dec 2021 | Jun 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DATU | DA MANHATTAN - ADA BATHROOM UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DATU | DA MANHATTAN - ADA BATHROOM UPGRADE | 5 | CONSTRUCTION TO 25% | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DATU | DA MANHATTAN - ADA BATHROOM UPGRADE | 6 | CONSTRUCTION TO 50% | Jan 2023 | May 2023 | Jan 2023 | May 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DATU | DA MANHATTAN - ADA BATHROOM UPGRADE | 7 | CONSTRUCTION TO 75% | May 2023 | Sep 2023 | May 2023 | Sep 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DATU | DA MANHATTAN - ADA BATHROOM UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Dec 2023 | Sep 2023 | Dec 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DATU | DA MANHATTAN - ADA BATHROOM UPGRADE | 9 | SUBSTANTIAL COMPLETION | Dec 2023 | Feb 2024 | Dec 2023 | Feb 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DATU | DA MANHATTAN - ADA BATHROOM UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2024 | Mar 2024 | Feb 2024 | Mar 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DFTAR | 2 Lafayette Street Renovation | 1 | DEVELOP SCOPE | Jun 2025 | Aug 2025 | Jun 2024 | Aug 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DFTAR | 2 Lafayette Street Renovation | 2 | PRELIMINARY DESIGN | Aug 2025 | Dec 2025 | Aug 2024 | Dec 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DFTAR | 2 Lafayette Street Renovation | 3 | FINAL DESIGN | Dec 2025 | Jun 2026 | Dec 2024 | Jun 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DFTAR | 2 Lafayette Street Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2026 | Sep 2026 | Jun 2025 | Sep 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DFTAR | 2 Lafayette Street Renovation | 5 | CONSTRUCTION TO 25% | Sep 2026 | Jan 2027 | Sep 2025 | Jan 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DFTAR | 2 Lafayette Street Renovation | 6 | CONSTRUCTION TO 50% | Jan 2027 | May 2027 | Jan 2026 | May 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DFTAR | 2 Lafayette Street Renovation | 7 | CONSTRUCTION TO 75% | May 2027 | Sep 2027 | May 2026 | Sep 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DFTAR | 2 Lafayette Street Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2027 | Dec 2027 | Sep 2026 | Dec 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DFTAR | 2 Lafayette Street Renovation | 9 | SUBSTANTIAL COMPLETION | Dec 2027 | Feb 2028 | Dec 2026 | Feb 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DFTAR | 2 Lafayette Street Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2028 | Mar 2028 | Feb 2027 | Mar 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DOOR | 1 CENTRE ST - FIRE DOOR REPLACEMENT CONSTRUCTION ONLY | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DOOR | 1 CENTRE ST - FIRE DOOR REPLACEMENT CONSTRUCTION ONLY | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DOOR | 1 CENTRE ST - FIRE DOOR REPLACEMENT CONSTRUCTION ONLY | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DOOR | 1 CENTRE ST - FIRE DOOR REPLACEMENT CONSTRUCTION ONLY | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DOOR | 1 CENTRE ST - FIRE DOOR REPLACEMENT CONSTRUCTION ONLY | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DOOR | 1 CENTRE ST - FIRE DOOR REPLACEMENT CONSTRUCTION ONLY | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DOOR | 1 CENTRE ST - FIRE DOOR REPLACEMENT CONSTRUCTION ONLY | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DOOR | 1 CENTRE ST - FIRE DOOR REPLACEMENT CONSTRUCTION ONLY | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DOOR | 1 CENTRE ST - FIRE DOOR REPLACEMENT CONSTRUCTION ONLY | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DOOR | 1 CENTRE ST - FIRE DOOR REPLACEMENT CONSTRUCTION ONLY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DOTRE | DOT- Relocation of HIQA & AEU | 1 | DEVELOP SCOPE | Jun 2024 | Aug 2024 | Jun 2024 | Aug 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DOTRE | DOT- Relocation of HIQA & AEU | 2 | PRELIMINARY DESIGN | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DOTRE | DOT- Relocation of HIQA & AEU | 3 | FINAL DESIGN | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DOTRE | DOT- Relocation of HIQA & AEU | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DOTRE | DOT- Relocation of HIQA & AEU | 5 | CONSTRUCTION TO 25% | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DOTRE | DOT- Relocation of HIQA & AEU | 6 | CONSTRUCTION TO 50% | Jan 2026 | May 2026 | Jan 2026 | May 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DOTRE | DOT- Relocation of HIQA & AEU | 7 | CONSTRUCTION TO 75% | May 2026 | Sep 2026 | May 2026 | Sep 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DOTRE | DOT- Relocation of HIQA & AEU | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2026 | Dec 2026 | Sep 2026 | Dec 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DOTRE | DOT- Relocation of HIQA & AEU | 9 | SUBSTANTIAL COMPLETION | Dec 2026 | Feb 2027 | Dec 2026 | Feb 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DOTRE | DOT- Relocation of HIQA & AEU | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2027 | Mar 2027 | Feb 2027 | Mar 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLD2F | 100 GOLD STREET 2 FLOOR - MOCs | 1 | DEVELOP SCOPE | Jun 2019 | Aug 2019 | May 2019 | Aug 2019
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLD2F | 100 GOLD STREET 2 FLOOR - MOCs | 2 | PRELIMINARY DESIGN | Aug 2019 | Dec 2019 | Aug 2019 | Dec 2019
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLD2F | 100 GOLD STREET 2 FLOOR - MOCs | 3 | FINAL DESIGN | Dec 2019 | Jun 2020 | Dec 2019 | Jun 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLD2F | 100 GOLD STREET 2 FLOOR - MOCs | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLD2F | 100 GOLD STREET 2 FLOOR - MOCs | 5 | CONSTRUCTION TO 25% | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLD2F | 100 GOLD STREET 2 FLOOR - MOCs | 6 | CONSTRUCTION TO 50% | Jan 2021 | May 2021 | Jan 2021 | May 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLD2F | 100 GOLD STREET 2 FLOOR - MOCs | 7 | CONSTRUCTION TO 75% | May 2021 | Sep 2021 | May 2021 | Sep 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLD2F | 100 GOLD STREET 2 FLOOR - MOCs | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Dec 2021 | Sep 2021 | Dec 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLD2F | 100 GOLD STREET 2 FLOOR - MOCs | 9 | SUBSTANTIAL COMPLETION | Dec 2021 | Feb 2022 | Dec 2021 | Feb 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLD2F | 100 GOLD STREET 2 FLOOR - MOCs | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2022 | Mar 2022 | Feb 2022 | Jun 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDBR | 100 GOLD ST - BATHROOM RENOVATION | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Dec 2021 | Mar 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDBR | 100 GOLD ST - BATHROOM RENOVATION | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Mar 2022 | Jul 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDBR | 100 GOLD ST - BATHROOM RENOVATION | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Jul 2022 | Jan 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDBR | 100 GOLD ST - BATHROOM RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jan 2023 | Apr 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDBR | 100 GOLD ST - BATHROOM RENOVATION | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | Apr 2023 | Aug 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDBR | 100 GOLD ST - BATHROOM RENOVATION | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | Aug 2023 | Dec 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDBR | 100 GOLD ST - BATHROOM RENOVATION | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | Dec 2023 | Apr 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDBR | 100 GOLD ST - BATHROOM RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Apr 2024 | Jul 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDBR | 100 GOLD ST - BATHROOM RENOVATION | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Jul 2024 | Sep 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDBR | 100 GOLD ST - BATHROOM RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Mar 2025 | Sep 2024 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDEV | 100 GOLD ST - ELEVATOR MODERNIZATION | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDEV | 100 GOLD ST - ELEVATOR MODERNIZATION | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDEV | 100 GOLD ST - ELEVATOR MODERNIZATION | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDEV | 100 GOLD ST - ELEVATOR MODERNIZATION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDEV | 100 GOLD ST - ELEVATOR MODERNIZATION | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDEV | 100 GOLD ST - ELEVATOR MODERNIZATION | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDEV | 100 GOLD ST - ELEVATOR MODERNIZATION | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | May 2024 | Sep 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDEV | 100 GOLD ST - ELEVATOR MODERNIZATION | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDEV | 100 GOLD ST - ELEVATOR MODERNIZATION | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Dec 2024 | Feb 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDEV | 100 GOLD ST - ELEVATOR MODERNIZATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Mar 2025 | Feb 2025 | Mar 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDFA | 100 GOLD ST - FIRE ALARM | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Aug 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDFA | 100 GOLD ST - FIRE ALARM | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDFA | 100 GOLD ST - FIRE ALARM | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDFA | 100 GOLD ST - FIRE ALARM | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDFA | 100 GOLD ST - FIRE ALARM | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDFA | 100 GOLD ST - FIRE ALARM | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2022 | May 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDFA | 100 GOLD ST - FIRE ALARM | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2023 | May 2022 | Sep 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDFA | 100 GOLD ST - FIRE ALARM | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Dec 2023 | Sep 2023 | Dec 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDFA | 100 GOLD ST - FIRE ALARM | 9 | SUBSTANTIAL COMPLETION | Dec 2023 | Feb 2024 | Dec 2023 | Feb 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDFA | 100 GOLD ST - FIRE ALARM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2024 | Mar 2024 | Feb 2024 | Mar 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77MBAC | CITY CLERK MARRIAGE BUREAU - SERVER ROOM AC UPGRADE | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77MBAC | CITY CLERK MARRIAGE BUREAU - SERVER ROOM AC UPGRADE | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77MBAC | CITY CLERK MARRIAGE BUREAU - SERVER ROOM AC UPGRADE | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77MBAC | CITY CLERK MARRIAGE BUREAU - SERVER ROOM AC UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Jan 2024 | Jul 2023 | Jan 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77MBAC | CITY CLERK MARRIAGE BUREAU - SERVER ROOM AC UPGRADE | 5 | CONSTRUCTION TO 25% | Jan 2024 | Apr 2024 | Jan 2024 | Apr 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77MBAC | CITY CLERK MARRIAGE BUREAU - SERVER ROOM AC UPGRADE | 6 | CONSTRUCTION TO 50% | May 2024 | Aug 2024 | May 2024 | Aug 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77MBAC | CITY CLERK MARRIAGE BUREAU - SERVER ROOM AC UPGRADE | 7 | CONSTRUCTION TO 75% | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77MBAC | CITY CLERK MARRIAGE BUREAU - SERVER ROOM AC UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2024 | Mar 2025 | Dec 2024 | Mar 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77MBAC | CITY CLERK MARRIAGE BUREAU - SERVER ROOM AC UPGRADE | 9 | SUBSTANTIAL COMPLETION | Mar 2025 | May 2025 | Mar 2025 | May 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77MBAC | CITY CLERK MARRIAGE BUREAU - SERVER ROOM AC UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2025 | Jun 2025 | May 2025 | Jun 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77OPER | DCAS Police Operations Center - 1 Centre St. | 1 | DEVELOP SCOPE | Jun 2025 | Aug 2025 | Jun 2025 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77OPER | DCAS Police Operations Center - 1 Centre St. | 2 | PRELIMINARY DESIGN | Aug 2025 | Dec 2025 | Aug 2025 | Dec 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77OPER | DCAS Police Operations Center - 1 Centre St. | 3 | FINAL DESIGN | Dec 2025 | Jun 2026 | Dec 2025 | Jun 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77OPER | DCAS Police Operations Center - 1 Centre St. | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2026 | Sep 2026 | Jun 2026 | Sep 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77OPER | DCAS Police Operations Center - 1 Centre St. | 5 | CONSTRUCTION TO 25% | Sep 2026 | Jan 2027 | Sep 2026 | Jan 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77OPER | DCAS Police Operations Center - 1 Centre St. | 6 | CONSTRUCTION TO 50% | Jan 2027 | May 2027 | Jan 2027 | May 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77OPER | DCAS Police Operations Center - 1 Centre St. | 7 | CONSTRUCTION TO 75% | May 2027 | Sep 2027 | May 2027 | Sep 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77OPER | DCAS Police Operations Center - 1 Centre St. | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2027 | Dec 2027 | Sep 2027 | Dec 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77OPER | DCAS Police Operations Center - 1 Centre St. | 9 | SUBSTANTIAL COMPLETION | Dec 2027 | Feb 2028 | Dec 2027 | Feb 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77OPER | DCAS Police Operations Center - 1 Centre St. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2028 | Mar 2028 | Feb 2028 | Mar 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SANIT | DSNY - RELOCATE DSNY SPACE FROM 137 CENTRE ST. | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2022 | Aug 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SANIT | DSNY - RELOCATE DSNY SPACE FROM 137 CENTRE ST. | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2022 | Dec 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SANIT | DSNY - RELOCATE DSNY SPACE FROM 137 CENTRE ST. | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2022 | Jun 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SANIT | DSNY - RELOCATE DSNY SPACE FROM 137 CENTRE ST. | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SANIT | DSNY - RELOCATE DSNY SPACE FROM 137 CENTRE ST. | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Jun 2024 | Sep 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SANIT | DSNY - RELOCATE DSNY SPACE FROM 137 CENTRE ST. | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SANIT | DSNY - RELOCATE DSNY SPACE FROM 137 CENTRE ST. | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | Jan 2025 | May 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SANIT | DSNY - RELOCATE DSNY SPACE FROM 137 CENTRE ST. | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | May 2025 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SANIT | DSNY - RELOCATE DSNY SPACE FROM 137 CENTRE ST. | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Aug 2025 | Oct 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SANIT | DSNY - RELOCATE DSNY SPACE FROM 137 CENTRE ST. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Oct 2025 | Nov 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC14 | 1 CENTRE ST.- 14 FL SECURITY CAMERAS | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Aug 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC14 | 1 CENTRE ST.- 14 FL SECURITY CAMERAS | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC14 | 1 CENTRE ST.- 14 FL SECURITY CAMERAS | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC14 | 1 CENTRE ST.- 14 FL SECURITY CAMERAS | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC14 | 1 CENTRE ST.- 14 FL SECURITY CAMERAS | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC14 | 1 CENTRE ST.- 14 FL SECURITY CAMERAS | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2022 | May 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC14 | 1 CENTRE ST.- 14 FL SECURITY CAMERAS | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2022 | Sep 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC14 | 1 CENTRE ST.- 14 FL SECURITY CAMERAS | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC14 | 1 CENTRE ST.- 14 FL SECURITY CAMERAS | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2022 | Feb 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC14 | 1 CENTRE ST.- 14 FL SECURITY CAMERAS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Feb 2023 | Mar 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC1C | 1 CENTRE ST - DCAS POLICE CCTV SYSTEM UPGRADE | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Aug 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC1C | 1 CENTRE ST - DCAS POLICE CCTV SYSTEM UPGRADE | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC1C | 1 CENTRE ST - DCAS POLICE CCTV SYSTEM UPGRADE | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC1C | 1 CENTRE ST - DCAS POLICE CCTV SYSTEM UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC1C | 1 CENTRE ST - DCAS POLICE CCTV SYSTEM UPGRADE | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC1C | 1 CENTRE ST - DCAS POLICE CCTV SYSTEM UPGRADE | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2022 | May 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC1C | 1 CENTRE ST - DCAS POLICE CCTV SYSTEM UPGRADE | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2022 | Sep 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC1C | 1 CENTRE ST - DCAS POLICE CCTV SYSTEM UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC1C | 1 CENTRE ST - DCAS POLICE CCTV SYSTEM UPGRADE | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2022 | Feb 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC1C | 1 CENTRE ST - DCAS POLICE CCTV SYSTEM UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Feb 2023 | Mar 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC22R | 22 READE ST - DCAS POLICE CCTV SYSTEM | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Aug 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC22R | 22 READE ST - DCAS POLICE CCTV SYSTEM | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC22R | 22 READE ST - DCAS POLICE CCTV SYSTEM | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC22R | 22 READE ST - DCAS POLICE CCTV SYSTEM | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC22R | 22 READE ST - DCAS POLICE CCTV SYSTEM | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC22R | 22 READE ST - DCAS POLICE CCTV SYSTEM | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2022 | May 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC22R | 22 READE ST - DCAS POLICE CCTV SYSTEM | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2022 | Sep 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC22R | 22 READE ST - DCAS POLICE CCTV SYSTEM | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC22R | 22 READE ST - DCAS POLICE CCTV SYSTEM | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2022 | Feb 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC22R | 22 READE ST - DCAS POLICE CCTV SYSTEM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Feb 2023 | Mar 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC280 | 280 BROADWAY - DCAS POLICE CCTV SYSTEM | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Aug 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC280 | 280 BROADWAY - DCAS POLICE CCTV SYSTEM | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC280 | 280 BROADWAY - DCAS POLICE CCTV SYSTEM | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC280 | 280 BROADWAY - DCAS POLICE CCTV SYSTEM | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC280 | 280 BROADWAY - DCAS POLICE CCTV SYSTEM | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC280 | 280 BROADWAY - DCAS POLICE CCTV SYSTEM | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2022 | May 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC280 | 280 BROADWAY - DCAS POLICE CCTV SYSTEM | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2022 | Sep 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC280 | 280 BROADWAY - DCAS POLICE CCTV SYSTEM | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC280 | 280 BROADWAY - DCAS POLICE CCTV SYSTEM | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2022 | Feb 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC280 | 280 BROADWAY - DCAS POLICE CCTV SYSTEM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Feb 2023 | Mar 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC2C | 2 LAFAYETTE ST - DCAS POLICE CCTV SYSTEM | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Aug 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC2C | 2 LAFAYETTE ST - DCAS POLICE CCTV SYSTEM | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC2C | 2 LAFAYETTE ST - DCAS POLICE CCTV SYSTEM | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC2C | 2 LAFAYETTE ST - DCAS POLICE CCTV SYSTEM | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC2C | 2 LAFAYETTE ST - DCAS POLICE CCTV SYSTEM | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC2C | 2 LAFAYETTE ST - DCAS POLICE CCTV SYSTEM | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2022 | May 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC2C | 2 LAFAYETTE ST - DCAS POLICE CCTV SYSTEM | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2022 | Sep 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC2C | 2 LAFAYETTE ST - DCAS POLICE CCTV SYSTEM | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC2C | 2 LAFAYETTE ST - DCAS POLICE CCTV SYSTEM | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2022 | Feb 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC2C | 2 LAFAYETTE ST - DCAS POLICE CCTV SYSTEM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Feb 2023 | Mar 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77TAX | 1 CENTRE ST.- 11TH FL. TAX COMMISSION REHAB | 1 | DEVELOP SCOPE | Jun 2012 | Aug 2012 | Jun 2012 | Aug 2012
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77TAX | 1 CENTRE ST.- 11TH FL. TAX COMMISSION REHAB | 2 | PRELIMINARY DESIGN | Aug 2012 | Dec 2012 | Aug 2012 | Dec 2012
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77TAX | 1 CENTRE ST.- 11TH FL. TAX COMMISSION REHAB | 3 | FINAL DESIGN | Dec 2012 | Jun 2013 | Dec 2012 | Jun 2013
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77TAX | 1 CENTRE ST.- 11TH FL. TAX COMMISSION REHAB | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2013 | Sep 2013 | Jun 2013 | Sep 2013
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77TAX | 1 CENTRE ST.- 11TH FL. TAX COMMISSION REHAB | 5 | CONSTRUCTION TO 25% | Sep 2013 | Jan 2014 | Sep 2023 | May 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77TAX | 1 CENTRE ST.- 11TH FL. TAX COMMISSION REHAB | 6 | CONSTRUCTION TO 50% | Jan 2014 | May 2014 | May 2024 | Sep 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77TAX | 1 CENTRE ST.- 11TH FL. TAX COMMISSION REHAB | 7 | CONSTRUCTION TO 75% | May 2014 | Sep 2014 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77TAX | 1 CENTRE ST.- 11TH FL. TAX COMMISSION REHAB | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2014 | Dec 2014 | Jan 2025 | Apr 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77TAX | 1 CENTRE ST.- 11TH FL. TAX COMMISSION REHAB | 9 | SUBSTANTIAL COMPLETION | Dec 2014 | Feb 2015 | Apr 2025 | Jun 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77TAX | 1 CENTRE ST.- 11TH FL. TAX COMMISSION REHAB | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2015 | Mar 2015 | Jun 2025 | Jul 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80CT1 | 2 LAFAYETTE ST.- COOLING TOWER | 1 | DEVELOP SCOPE | Jun 2021 | Aug 2021 | Jun 2021 | Aug 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80CT1 | 2 LAFAYETTE ST.- COOLING TOWER | 2 | PRELIMINARY DESIGN | Aug 2021 | Dec 2021 | Aug 2021 | Dec 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80CT1 | 2 LAFAYETTE ST.- COOLING TOWER | 3 | FINAL DESIGN | Dec 2021 | Jun 2022 | Dec 2021 | Jun 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80CT1 | 2 LAFAYETTE ST.- COOLING TOWER | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80CT1 | 2 LAFAYETTE ST.- COOLING TOWER | 5 | CONSTRUCTION TO 25% | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80CT1 | 2 LAFAYETTE ST.- COOLING TOWER | 6 | CONSTRUCTION TO 50% | Jan 2023 | May 2023 | Jan 2023 | May 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80CT1 | 2 LAFAYETTE ST.- COOLING TOWER | 7 | CONSTRUCTION TO 75% | May 2023 | Sep 2023 | May 2023 | Sep 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80CT1 | 2 LAFAYETTE ST.- COOLING TOWER | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Dec 2023 | Sep 2023 | Dec 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80CT1 | 2 LAFAYETTE ST.- COOLING TOWER | 9 | SUBSTANTIAL COMPLETION | Dec 2023 | Feb 2024 | Dec 2023 | Feb 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80CT1 | 2 LAFAYETTE ST.- COOLING TOWER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2024 | Mar 2024 | Feb 2024 | Mar 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEC | 2 LAFAYETTE STREET ELECTRICAL UPGRADE | 1 | DEVELOP SCOPE | Jan 2017 | Mar 2017 | Jun 2021 | Aug 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEC | 2 LAFAYETTE STREET ELECTRICAL UPGRADE | 2 | PRELIMINARY DESIGN | Apr 2017 | Jul 2017 | Aug 2021 | Dec 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEC | 2 LAFAYETTE STREET ELECTRICAL UPGRADE | 3 | FINAL DESIGN | Jul 2017 | Jan 2018 | Dec 2021 | Jun 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEC | 2 LAFAYETTE STREET ELECTRICAL UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2018 | Apr 2018 | Jun 2023 | Aug 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEC | 2 LAFAYETTE STREET ELECTRICAL UPGRADE | 5 | CONSTRUCTION TO 25% | Apr 2018 | Aug 2018 | Aug 2023 | Dec 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEC | 2 LAFAYETTE STREET ELECTRICAL UPGRADE | 6 | CONSTRUCTION TO 50% | Aug 2018 | Dec 2018 | Dec 2023 | Apr 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEC | 2 LAFAYETTE STREET ELECTRICAL UPGRADE | 7 | CONSTRUCTION TO 75% | Dec 2018 | Apr 2019 | Apr 2024 | Aug 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEC | 2 LAFAYETTE STREET ELECTRICAL UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2019 | Jul 2019 | Aug 2024 | Nov 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEC | 2 LAFAYETTE STREET ELECTRICAL UPGRADE | 9 | SUBSTANTIAL COMPLETION | Jul 2019 | Sep 2019 | Nov 2024 | Jan 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEC | 2 LAFAYETTE STREET ELECTRICAL UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Oct 2019 | Jan 2025 | Nov 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEV | 2 LAFAYETTE ST - ELEVATOR MODERNIZATION | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEV | 2 LAFAYETTE ST - ELEVATOR MODERNIZATION | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEV | 2 LAFAYETTE ST - ELEVATOR MODERNIZATION | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEV | 2 LAFAYETTE ST - ELEVATOR MODERNIZATION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEV | 2 LAFAYETTE ST - ELEVATOR MODERNIZATION | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEV | 2 LAFAYETTE ST - ELEVATOR MODERNIZATION | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEV | 2 LAFAYETTE ST - ELEVATOR MODERNIZATION | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | May 2024 | Sep 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEV | 2 LAFAYETTE ST - ELEVATOR MODERNIZATION | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEV | 2 LAFAYETTE ST - ELEVATOR MODERNIZATION | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Dec 2024 | Feb 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEV | 2 LAFAYETTE ST - ELEVATOR MODERNIZATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Mar 2025 | Feb 2025 | Mar 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCN001 | Sixth Street compost project | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jun 2024 | Aug 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCN001 | Sixth Street compost project | 2 | PRELIMINARY DESIGN | Sep 2015 | Jan 2016 | Aug 2024 | Dec 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCN001 | Sixth Street compost project | 3 | FINAL DESIGN | Jan 2016 | Jul 2016 | Dec 2024 | Jun 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCN001 | Sixth Street compost project | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Oct 2016 | Jun 2025 | Sep 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCN001 | Sixth Street compost project | 5 | CONSTRUCTION TO 25% | Oct 2016 | Feb 2017 | Sep 2025 | Jan 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCN001 | Sixth Street compost project | 6 | CONSTRUCTION TO 50% | Feb 2017 | Jun 2017 | Jan 2026 | May 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCN001 | Sixth Street compost project | 7 | CONSTRUCTION TO 75% | Jun 2017 | Oct 2017 | May 2026 | Sep 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCN001 | Sixth Street compost project | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2017 | Jan 2018 | Jun 2028 | Aug 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCN001 | Sixth Street compost project | 9 | SUBSTANTIAL COMPLETION | Jan 2018 | Mar 2018 | Aug 2028 | Oct 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCN001 | Sixth Street compost project | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2018 | Apr 2018 | Oct 2028 | Nov 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05CYBR | 80 CENTRE ST. - NY COUNTY DA CYBERCRIME AND IDENTITY THEFT | 1 | DEVELOP SCOPE | Feb 2012 | May 2012 | Feb 2012 | Apr 2012
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05CYBR | 80 CENTRE ST. - NY COUNTY DA CYBERCRIME AND IDENTITY THEFT | 2 | PRELIMINARY DESIGN | May 2012 | Sep 2012 | May 2012 | Aug 2012
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05CYBR | 80 CENTRE ST. - NY COUNTY DA CYBERCRIME AND IDENTITY THEFT | 3 | FINAL DESIGN | Sep 2012 | Mar 2013 | Aug 2012 | Feb 2013
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05CYBR | 80 CENTRE ST. - NY COUNTY DA CYBERCRIME AND IDENTITY THEFT | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2013 | Jun 2013 | Feb 2013 | May 2013
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05CYBR | 80 CENTRE ST. - NY COUNTY DA CYBERCRIME AND IDENTITY THEFT | 5 | CONSTRUCTION TO 25% | Jun 2013 | Oct 2013 | May 2013 | Sep 2013
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05CYBR | 80 CENTRE ST. - NY COUNTY DA CYBERCRIME AND IDENTITY THEFT | 6 | CONSTRUCTION TO 50% | Oct 2013 | Jan 2014 | Sep 2013 | Jan 2014
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05CYBR | 80 CENTRE ST. - NY COUNTY DA CYBERCRIME AND IDENTITY THEFT | 7 | CONSTRUCTION TO 75% | Feb 2014 | May 2014 | Jun 2027 | Sep 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05CYBR | 80 CENTRE ST. - NY COUNTY DA CYBERCRIME AND IDENTITY THEFT | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2014 | Aug 2014 | Sep 2027 | Dec 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05CYBR | 80 CENTRE ST. - NY COUNTY DA CYBERCRIME AND IDENTITY THEFT | 9 | SUBSTANTIAL COMPLETION | Aug 2014 | Oct 2014 | Dec 2027 | Feb 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05CYBR | 80 CENTRE ST. - NY COUNTY DA CYBERCRIME AND IDENTITY THEFT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2014 | Nov 2014 | Feb 2028 | Mar 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05DAHV | 80 CENTRE ST. - NY COUNTY DA HVAC UPGRADE SERVER ROOM | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2026 | Aug 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05DAHV | 80 CENTRE ST. - NY COUNTY DA HVAC UPGRADE SERVER ROOM | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2026 | Dec 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05DAHV | 80 CENTRE ST. - NY COUNTY DA HVAC UPGRADE SERVER ROOM | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2026 | Jun 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05DAHV | 80 CENTRE ST. - NY COUNTY DA HVAC UPGRADE SERVER ROOM | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2027 | Sep 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05DAHV | 80 CENTRE ST. - NY COUNTY DA HVAC UPGRADE SERVER ROOM | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2027 | Jan 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05DAHV | 80 CENTRE ST. - NY COUNTY DA HVAC UPGRADE SERVER ROOM | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2028 | May 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05DAHV | 80 CENTRE ST. - NY COUNTY DA HVAC UPGRADE SERVER ROOM | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2028 | Sep 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05DAHV | 80 CENTRE ST. - NY COUNTY DA HVAC UPGRADE SERVER ROOM | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2028 | Dec 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05DAHV | 80 CENTRE ST. - NY COUNTY DA HVAC UPGRADE SERVER ROOM | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2028 | Feb 2029
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05DAHV | 80 CENTRE ST. - NY COUNTY DA HVAC UPGRADE SERVER ROOM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Feb 2029 | Mar 2029
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BAG | 1 CENTRE ST.- BIG APPLE GREETER | 1 | DEVELOP SCOPE | Jul 2005 | Sep 2005 | Jul 2005 | Sep 2005
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BAG | 1 CENTRE ST.- BIG APPLE GREETER | 2 | PRELIMINARY DESIGN | Sep 2005 | Jan 2006 | Sep 2005 | Jan 2006
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BAG | 1 CENTRE ST.- BIG APPLE GREETER | 3 | FINAL DESIGN | Jan 2006 | Jul 2006 | Jan 2006 | Jul 2006
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BAG | 1 CENTRE ST.- BIG APPLE GREETER | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2006 | Oct 2006 | Jul 2006 | Oct 2006
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BAG | 1 CENTRE ST.- BIG APPLE GREETER | 5 | CONSTRUCTION TO 25% | Oct 2006 | Oct 2007 | Jun 2024 | Jan 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BAG | 1 CENTRE ST.- BIG APPLE GREETER | 6 | CONSTRUCTION TO 50% | Oct 2007 | Oct 2008 | Jan 2027 | Sep 2029
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BAG | 1 CENTRE ST.- BIG APPLE GREETER | 7 | CONSTRUCTION TO 75% | Oct 2008 | Oct 2009 | Sep 2029 | Aug 2030
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BAG | 1 CENTRE ST.- BIG APPLE GREETER | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2009 | Oct 2010 | Aug 2030 | Oct 2030
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BAG | 1 CENTRE ST.- BIG APPLE GREETER | 9 | SUBSTANTIAL COMPLETION | Oct 2010 | Sep 2011 | Oct 2030 | Nov 2030
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BAG | 1 CENTRE ST.- BIG APPLE GREETER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2011 | Dec 2011 | Nov 2030 | Jun 2032
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5HSCHR | HECKSCHER Building -- Roof Renovation at 1 East 104th Street | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2027 | Aug 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5HSCHR | HECKSCHER Building -- Roof Renovation at 1 East 104th Street | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Aug 2027 | Dec 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5HSCHR | HECKSCHER Building -- Roof Renovation at 1 East 104th Street | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Dec 2027 | Jun 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5HSCHR | HECKSCHER Building -- Roof Renovation at 1 East 104th Street | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Mar 2024 | Jun 2028 | Sep 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5HSCHR | HECKSCHER Building -- Roof Renovation at 1 East 104th Street | 5 | CONSTRUCTION TO 25% | Mar 2024 | Jul 2024 | Sep 2028 | Jan 2029
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5HSCHR | HECKSCHER Building -- Roof Renovation at 1 East 104th Street | 6 | CONSTRUCTION TO 50% | Jul 2024 | Nov 2024 | Jan 2029 | May 2029
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5HSCHR | HECKSCHER Building -- Roof Renovation at 1 East 104th Street | 7 | CONSTRUCTION TO 75% | Nov 2024 | Mar 2025 | May 2029 | Sep 2029
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5HSCHR | HECKSCHER Building -- Roof Renovation at 1 East 104th Street | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2025 | Jun 2025 | Sep 2029 | Dec 2029
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5HSCHR | HECKSCHER Building -- Roof Renovation at 1 East 104th Street | 9 | SUBSTANTIAL COMPLETION | Jun 2025 | Aug 2025 | Dec 2029 | Feb 2030
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5HSCHR | HECKSCHER Building -- Roof Renovation at 1 East 104th Street | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2025 | Sep 2025 | Feb 2030 | Mar 2030
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNIBO1 | Independent Budget Office - New Location Outfitting | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Aug 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNIBO1 | Independent Budget Office - New Location Outfitting | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2023 | Mar 2024 | Aug 2023 | Dec 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNIBO1 | Independent Budget Office - New Location Outfitting | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Dec 2023 | Jun 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNIBO1 | Independent Budget Office - New Location Outfitting | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Jun 2024 | Jun 2024 | Sep 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNIBO1 | Independent Budget Office - New Location Outfitting | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2024 | May 2024 | Sep 2024 | Jan 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNIBO1 | Independent Budget Office - New Location Outfitting | 6 | CONSTRUCTION TO 50% | Apr 2024 | May 2024 | Jan 2025 | May 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNIBO1 | Independent Budget Office - New Location Outfitting | 7 | CONSTRUCTION TO 75% | Apr 2024 | May 2024 | May 2025 | Sep 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNIBO1 | Independent Budget Office - New Location Outfitting | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2024 | May 2024 | Sep 2025 | Dec 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNIBO1 | Independent Budget Office - New Location Outfitting | 9 | SUBSTANTIAL COMPLETION | Apr 2024 | May 2024 | Dec 2025 | Feb 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNIBO1 | Independent Budget Office - New Location Outfitting | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2024 | May 2024 | Feb 2026 | Mar 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNTEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN 243 W 20th St | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2027 | Aug 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNTEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN 243 W 20th St | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2027 | Dec 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNTEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN 243 W 20th St | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2027 | Jun 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNTEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN 243 W 20th St | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2028 | Sep 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNTEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN 243 W 20th St | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2028 | Jan 2029
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNTEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN 243 W 20th St | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2029 | May 2029
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNTEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN 243 W 20th St | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2029 | Sep 2029
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNTEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN 243 W 20th St | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2029 | Dec 2029
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNTEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN 243 W 20th St | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2029 | Feb 2030
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNTEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN 243 W 20th St | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Feb 2030 | Mar 2030
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWM77FJC | 80 CENTRE ST. - MANHATTAN FAMILY JUSTICE CENTER | 1 | DEVELOP SCOPE | Jun 2012 | Sep 2012 | Jun 2012 | Sep 2012
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWM77FJC | 80 CENTRE ST. - MANHATTAN FAMILY JUSTICE CENTER | 2 | PRELIMINARY DESIGN | Sep 2012 | Jan 2013 | Sep 2012 | Jan 2013
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWM77FJC | 80 CENTRE ST. - MANHATTAN FAMILY JUSTICE CENTER | 3 | FINAL DESIGN | Jan 2013 | Jul 2013 | Jan 2013 | Jul 2013
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWM77FJC | 80 CENTRE ST. - MANHATTAN FAMILY JUSTICE CENTER | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2013
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWM77FJC | 80 CENTRE ST. - MANHATTAN FAMILY JUSTICE CENTER | 5 | CONSTRUCTION TO 25% | Oct 2013 | Jan 2014 | Oct 2013 | Jan 2014
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWM77FJC | 80 CENTRE ST. - MANHATTAN FAMILY JUSTICE CENTER | 6 | CONSTRUCTION TO 50% | Jan 2014 | May 2014 | Jun 2028 | Sep 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWM77FJC | 80 CENTRE ST. - MANHATTAN FAMILY JUSTICE CENTER | 7 | CONSTRUCTION TO 75% | May 2014 | Sep 2014 | Sep 2028 | Jan 2029
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWM77FJC | 80 CENTRE ST. - MANHATTAN FAMILY JUSTICE CENTER | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2014 | Dec 2014 | Jan 2029 | Apr 2029
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWM77FJC | 80 CENTRE ST. - MANHATTAN FAMILY JUSTICE CENTER | 9 | SUBSTANTIAL COMPLETION | Dec 2014 | Feb 2015 | Apr 2029 | Jun 2029
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWM77FJC | 80 CENTRE ST. - MANHATTAN FAMILY JUSTICE CENTER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2015 | Mar 2015 | Jun 2029 | Jul 2029
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWMOCSIT1 | MOCS IT NETWORK INFRASTRUCTURE 100 GOLD STREET 2ND FL | 1 | DEVELOP SCOPE | Jun 2021 | Aug 2021 | Jun 2021 | Aug 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWMOCSIT1 | MOCS IT NETWORK INFRASTRUCTURE 100 GOLD STREET 2ND FL | 2 | PRELIMINARY DESIGN | Aug 2021 | Dec 2021 | Aug 2021 | Dec 2021
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWMOCSIT1 | MOCS IT NETWORK INFRASTRUCTURE 100 GOLD STREET 2ND FL | 3 | FINAL DESIGN | Dec 2021 | Jun 2022 | Dec 2021 | Jun 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWMOCSIT1 | MOCS IT NETWORK INFRASTRUCTURE 100 GOLD STREET 2ND FL | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWMOCSIT1 | MOCS IT NETWORK INFRASTRUCTURE 100 GOLD STREET 2ND FL | 5 | CONSTRUCTION TO 25% | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWMOCSIT1 | MOCS IT NETWORK INFRASTRUCTURE 100 GOLD STREET 2ND FL | 6 | CONSTRUCTION TO 50% | Jan 2023 | May 2023 | Jan 2023 | May 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWMOCSIT1 | MOCS IT NETWORK INFRASTRUCTURE 100 GOLD STREET 2ND FL | 7 | CONSTRUCTION TO 75% | May 2023 | Sep 2023 | May 2023 | Sep 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWMOCSIT1 | MOCS IT NETWORK INFRASTRUCTURE 100 GOLD STREET 2ND FL | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Dec 2023 | Sep 2023 | Dec 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWMOCSIT1 | MOCS IT NETWORK INFRASTRUCTURE 100 GOLD STREET 2ND FL | 9 | SUBSTANTIAL COMPLETION | Dec 2023 | Feb 2024 | Dec 2023 | Feb 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWMOCSIT1 | MOCS IT NETWORK INFRASTRUCTURE 100 GOLD STREET 2ND FL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2024 | Mar 2024 | Feb 2024 | Mar 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCA24M030 | SCA FY24 Electrification - M030 | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCA24M030 | SCA FY24 Electrification - M030 | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCA24M030 | SCA FY24 Electrification - M030 | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCA24M030 | SCA FY24 Electrification - M030 | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCA24M030 | SCA FY24 Electrification - M030 | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCA24M030 | SCA FY24 Electrification - M030 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCA24M155 | SCA FY24 Electrification - M155 | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCA24M155 | SCA FY24 Electrification - M155 | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCA24M155 | SCA FY24 Electrification - M155 | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCA24M155 | SCA FY24 Electrification - M155 | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCA24M155 | SCA FY24 Electrification - M155 | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCA24M155 | SCA FY24 Electrification - M155 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-M048 | SCA Electrification - M048 | 1 | DEVELOP SCOPE | Jun 2025 | Jun 2025 | Jun 2025 | Jun 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-M048 | SCA Electrification - M048 | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-M048 | SCA Electrification - M048 | 3 | CONSTRUCTION TO 50% | Aug 2025 | Feb 2026 | Aug 2025 | Feb 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-M048 | SCA Electrification - M048 | 4 | CONSTRUCTION TO 75% | Feb 2026 | May 2026 | Feb 2026 | May 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-M048 | SCA Electrification - M048 | 5 | SUBSTANTIAL COMPLETION | May 2026 | Jul 2026 | May 2026 | Jul 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-M048 | SCA Electrification - M048 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2026 | Aug 2026 | Jul 2026 | Aug 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-M129 | SCA Electrification - M129 | 1 | DEVELOP SCOPE | Jun 2026 | Jun 2026 | Jun 2026 | Jun 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-M129 | SCA Electrification - M129 | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2026 | Aug 2026 | Jul 2026 | Aug 2026
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-M129 | SCA Electrification - M129 | 3 | CONSTRUCTION TO 50% | Aug 2026 | Feb 2027 | Aug 2026 | Feb 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-M129 | SCA Electrification - M129 | 4 | CONSTRUCTION TO 75% | Feb 2027 | May 2027 | Feb 2027 | May 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-M129 | SCA Electrification - M129 | 5 | SUBSTANTIAL COMPLETION | May 2027 | Jul 2027 | May 2027 | Jul 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-M129 | SCA Electrification - M129 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2027 | Aug 2027 | Jul 2027 | Aug 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-M218 | SCA Electrification - M218 | 1 | DEVELOP SCOPE | Jun 2027 | Jun 2027 | Jun 2027 | Jun 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-M218 | SCA Electrification - M218 | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2027 | Aug 2027 | Jul 2027 | Aug 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-M218 | SCA Electrification - M218 | 3 | CONSTRUCTION TO 50% | Aug 2027 | Feb 2028 | Aug 2027 | Feb 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-M218 | SCA Electrification - M218 | 4 | CONSTRUCTION TO 75% | Feb 2028 | May 2028 | Feb 2028 | May 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-M218 | SCA Electrification - M218 | 5 | SUBSTANTIAL COMPLETION | May 2028 | Jul 2028 | May 2028 | Jul 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-M218 | SCA Electrification - M218 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2028 | Aug 2028 | Jul 2028 | Aug 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-M501 | SCA Electrification - M501 | 1 | DEVELOP SCOPE | Jun 2027 | Jun 2027 | Jun 2027 | Jun 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-M501 | SCA Electrification - M501 | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2027 | Aug 2027 | Jul 2027 | Aug 2027
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-M501 | SCA Electrification - M501 | 3 | CONSTRUCTION TO 50% | Aug 2027 | Feb 2028 | Aug 2027 | Feb 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-M501 | SCA Electrification - M501 | 4 | CONSTRUCTION TO 75% | Feb 2028 | May 2028 | Feb 2028 | May 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-M501 | SCA Electrification - M501 | 5 | SUBSTANTIAL COMPLETION | May 2028 | Jul 2028 | May 2028 | Jul 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-M501 | SCA Electrification - M501 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2028 | Aug 2028 | Jul 2028 | Aug 2028
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | TKYHHC012 | HHC - Bellevue Cooling Towers and Chillers Upgrade | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2023 | Jun 2023 | Jun 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | TKYHHC012 | HHC - Bellevue Cooling Towers and Chillers Upgrade | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | TKYHHC012 | HHC - Bellevue Cooling Towers and Chillers Upgrade | 3 | CONSTRUCTION TO 50% | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | TKYHHC012 | HHC - Bellevue Cooling Towers and Chillers Upgrade | 4 | CONSTRUCTION TO 75% | Feb 2024 | May 2024 | Feb 2024 | May 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | TKYHHC012 | HHC - Bellevue Cooling Towers and Chillers Upgrade | 5 | SUBSTANTIAL COMPLETION | May 2024 | Jul 2024 | May 2024 | Jul 2024
20231026 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | TKYHHC012 | HHC - Bellevue Cooling Towers and Chillers Upgrade | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | QUEENS | 037 | NEW YORK PUBLIC LIBRARY | LN20LSCRF | Library Services Center - Roof Deck Replacement | 1 | DEVELOP SCOPE | Sep 2019 | Nov 2019 | Jul 2030 | Sep 2030
20231026 | QUEENS | 037 | NEW YORK PUBLIC LIBRARY | LN20LSCRF | Library Services Center - Roof Deck Replacement | 2 | DESIGN | Nov 2019 | Nov 2020 | Sep 2030 | Sep 2031
20231026 | QUEENS | 037 | NEW YORK PUBLIC LIBRARY | LN20LSCRF | Library Services Center - Roof Deck Replacement | 3 | BID/ REGISTER CONTRACT | Nov 2020 | Aug 2021 | Sep 2031 | Jun 2032
20231026 | QUEENS | 037 | NEW YORK PUBLIC LIBRARY | LN20LSCRF | Library Services Center - Roof Deck Replacement | 4 | CONSTRUCTION | Aug 2021 | Aug 2022 | Jun 2032 | Jun 2033
20231026 | QUEENS | 037 | NEW YORK PUBLIC LIBRARY | LN20LSCRF | Library Services Center - Roof Deck Replacement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2022 | Aug 2023 | Jun 2033 | Jun 2034
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQ122-GEN | SYSTEMWIDE - General Projects/Infrastructure | 1 | DESIGN | Apr 2012 | Apr 2012 | Apr 2012 | Apr 2012
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQ122-GEN | SYSTEMWIDE - General Projects/Infrastructure | 2 | BID AWARD AND REGISTER CONTRCT | May 2012 | Jul 2012 | May 2012 | Jul 2012
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQ122-GEN | SYSTEMWIDE - General Projects/Infrastructure | 3 | CONSTRUCTION | Jul 2012 | Jan 2013 | Jul 2012 | Jul 2030
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQ122-GEN | SYSTEMWIDE - General Projects/Infrastructure | 4 | ORIGINAL EQUIP & FURNISHING | Jan 2013 | Apr 2013 | Jul 2030 | Oct 2030
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQ122-GEN | SYSTEMWIDE - General Projects/Infrastructure | 5 | SUBSTANTIAL COMPLETION | Apr 2013 | May 2013 | Oct 2030 | Nov 2030
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQ122-GEN | SYSTEMWIDE - General Projects/Infrastructure | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2013 | Jun 2013 | Nov 2030 | Dec 2030
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQBCHREAD | BROAD CHANNEL: Library Seating Area | 1 | DESIGN | Dec 2019 | Nov 2021 | Dec 2019 | Nov 2021
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQBCHREAD | BROAD CHANNEL: Library Seating Area | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2021 | Nov 2022 | Nov 2021 | Nov 2022
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQBCHREAD | BROAD CHANNEL: Library Seating Area | 3 | CONSTRUCTION | Nov 2022 | Nov 2028 | Nov 2022 | Nov 2028
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQBC-ROOF | BROAD CHANNEL: New roof | 1 | DESIGN | Jan 2019 | Dec 2020 | Jan 2019 | Dec 2020
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQBC-ROOF | BROAD CHANNEL: New roof | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQBC-ROOF | BROAD CHANNEL: New roof | 3 | CONSTRUCTION | Dec 2021 | Dec 2027 | Dec 2021 | Dec 2027
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQBR-ROOF | BROADWAY - ROOF | 1 | DESIGN | Jan 2019 | Dec 2020 | Jan 2019 | Dec 2020
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQBR-ROOF | BROADWAY - ROOF | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQBR-ROOF | BROADWAY - ROOF | 3 | CONSTRUCTION | Dec 2021 | Dec 2027 | Dec 2021 | Dec 2027
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA19LHS | LANGSTON HUGHES:BMS SYSTEM | 1 | DESIGN | Jan 2019 | Dec 2020 | Jan 2019 | Dec 2020
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA19LHS | LANGSTON HUGHES:BMS SYSTEM | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA19LHS | LANGSTON HUGHES:BMS SYSTEM | 3 | CONSTRUCTION | Dec 2021 | Dec 2027 | Dec 2021 | Dec 2027
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA19WSD | WOODSIDE: Branch Renovation | 1 | DESIGN | Jan 2019 | Dec 2020 | Jan 2019 | Dec 2020
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA19WSD | WOODSIDE: Branch Renovation | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA19WSD | WOODSIDE: Branch Renovation | 3 | CONSTRUCTION | Dec 2021 | Dec 2027 | Dec 2021 | Dec 2027
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA20MGR | McGoldrick: New Roof | 1 | DESIGN | Jul 2020 | Jun 2022 | Jul 2020 | Jun 2022
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA20MGR | McGoldrick: New Roof | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Jun 2023 | Jun 2022 | Jun 2023
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA20MGR | McGoldrick: New Roof | 3 | CONSTRUCTION | Jul 2018 | Jun 2024 | Jul 2018 | Jun 2024
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCC-XCES | SYSTEMWIDE - CC Excess Funding | 1 | DESIGN | Jul 2024 | Jul 2024 | Jul 2024 | Jul 2024
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCC-XCES | SYSTEMWIDE - CC Excess Funding | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCC-XCES | SYSTEMWIDE - CC Excess Funding | 3 | CONSTRUCTION | Oct 2024 | Apr 2025 | Oct 2024 | Apr 2025
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCC-XCES | SYSTEMWIDE - CC Excess Funding | 4 | ORIGINAL EQUIP & FURNISHING | Apr 2025 | Jul 2025 | Apr 2025 | Jul 2025
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCC-XCES | SYSTEMWIDE - CC Excess Funding | 5 | SUBSTANTIAL COMPLETION | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCC-XCES | SYSTEMWIDE - CC Excess Funding | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2025 | Sep 2025 | Aug 2025 | Sep 2025
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCELHVAC | CENTRAL: Facade Restoration, Replace HVAC, Roof Replacement | 1 | DESIGN | Jan 2019 | Dec 2020 | Jan 2019 | Dec 2020
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCELHVAC | CENTRAL: Facade Restoration, Replace HVAC, Roof Replacement | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCELHVAC | CENTRAL: Facade Restoration, Replace HVAC, Roof Replacement | 3 | CONSTRUCTION | Dec 2021 | Dec 2027 | Dec 2021 | Dec 2027
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCORENOV | CORONA : Branch Expansion and Renovation | 1 | DESIGN | Jan 2019 | Dec 2020 | Jan 2019 | Dec 2020
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCORENOV | CORONA : Branch Expansion and Renovation | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCORENOV | CORONA : Branch Expansion and Renovation | 3 | CONSTRUCTION | Dec 2021 | Dec 2027 | Dec 2021 | Dec 2027
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQFL-REP | Flushing - Replacement of Roof, HVAC, and Cooling Tower | 1 | DESIGN | Jul 2025 | Jun 2027 | Jul 2025 | Jun 2027
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQFL-REP | Flushing - Replacement of Roof, HVAC, and Cooling Tower | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2027 | Jun 2028 | Jun 2027 | Jun 2028
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQFL-REP | Flushing - Replacement of Roof, HVAC, and Cooling Tower | 3 | CONSTRUCTION | Jun 2028 | Jun 2034 | Jun 2028 | Jun 2034
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQHILRENO | HILLCREST: Renovation | 1 | DESIGN | Jan 2019 | Dec 2020 | Jan 2019 | Dec 2020
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQHILRENO | HILLCREST: Renovation | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQHILRENO | HILLCREST: Renovation | 3 | CONSTRUCTION | Dec 2021 | Dec 2027 | Dec 2021 | Dec 2027
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLAHEXTR | LANGSTON HUGHES: Exterior Restoration | 1 | DESIGN | Jan 2019 | Dec 2020 | Jan 2019 | Dec 2020
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLAHEXTR | LANGSTON HUGHES: Exterior Restoration | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLAHEXTR | LANGSTON HUGHES: Exterior Restoration | 3 | CONSTRUCTION | Dec 2021 | Dec 2027 | Dec 2021 | Dec 2027
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLFK-INT | Lefrak City Library - Interior renovations | 1 | DESIGN | Jan 2019 | Dec 2020 | Jan 2019 | Dec 2020
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLFK-INT | Lefrak City Library - Interior renovations | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLFK-INT | Lefrak City Library - Interior renovations | 3 | CONSTRUCTION | Dec 2021 | Dec 2027 | Dec 2021 | Dec 2027
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLI-ROOF | LONG ISLAND CITY: New Roof | 1 | DESIGN | Jan 2019 | Dec 2020 | Jan 2028 | Dec 2029
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLI-ROOF | LONG ISLAND CITY: New Roof | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Dec 2021 | Dec 2029 | Dec 2030
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLI-ROOF | LONG ISLAND CITY: New Roof | 3 | CONSTRUCTION | Dec 2021 | Dec 2027 | Dec 2030 | Dec 2031
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQNFP-ADA | North Forest - Main Entrance Accessibility | 1 | DESIGN | Aug 2022 | Jul 2024 | Aug 2022 | Jul 2024
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQNFP-ADA | North Forest - Main Entrance Accessibility | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Jul 2025 | Jul 2024 | Jul 2025
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQNFP-ADA | North Forest - Main Entrance Accessibility | 3 | CONSTRUCTION | Jul 2025 | Jul 2031 | Jul 2025 | Jul 2031
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQNO-HVAC | NORTH HILLS - HVAC | 1 | DESIGN | Jan 2019 | Dec 2020 | Jan 2019 | Dec 2020
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQNO-HVAC | NORTH HILLS - HVAC | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQNO-HVAC | NORTH HILLS - HVAC | 3 | CONSTRUCTION | Dec 2021 | Dec 2027 | Dec 2021 | Dec 2027
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQPOMHVAC | POMONOK - HVAC System Replacement | 1 | DESIGN | Jun 2018 | Jul 2018 | Jun 2023 | Jul 2023
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQPOMHVAC | POMONOK - HVAC System Replacement | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2023 | Oct 2023
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQPOMHVAC | POMONOK - HVAC System Replacement | 3 | CONSTRUCTION | Oct 2018 | Apr 2019 | Oct 2023 | Apr 2024
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQPOMHVAC | POMONOK - HVAC System Replacement | 4 | ORIGINAL EQUIP & FURNISHING | Apr 2019 | Jul 2019 | Apr 2024 | Jul 2024
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQPOMHVAC | POMONOK - HVAC System Replacement | 5 | SUBSTANTIAL COMPLETION | Jul 2019 | Aug 2019 | Jul 2024 | Aug 2024
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQPOMHVAC | POMONOK - HVAC System Replacement | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2019 | Sep 2019 | Aug 2024 | Sep 2024
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQQA21CTQ | Court Square - New Library Fit Out | 1 | DESIGN | Jul 2020 | Jun 2022 | Jul 2020 | Jun 2022
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQQA21CTQ | Court Square - New Library Fit Out | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Jun 2023 | Jun 2022 | Jun 2023
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQQA21CTQ | Court Square - New Library Fit Out | 3 | CONSTRUCTION | Jun 2023 | Jun 2029 | Jun 2023 | Jun 2029
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQQBH-RES | QUEENSBORO HILL - Resiliency | 1 | DESIGN | Jul 2025 | Jul 2025 | Jul 2025 | Jul 2025
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQQBH-RES | QUEENSBORO HILL - Resiliency | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQQBH-RES | QUEENSBORO HILL - Resiliency | 3 | CONSTRUCTION | Oct 2025 | Apr 2026 | Oct 2025 | Apr 2026
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQQBH-RES | QUEENSBORO HILL - Resiliency | 4 | ORIGINAL EQUIP & FURNISHING | Apr 2026 | Jul 2026 | Apr 2026 | Jul 2026
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQQBH-RES | QUEENSBORO HILL - Resiliency | 5 | SUBSTANTIAL COMPLETION | Jul 2026 | Aug 2026 | Jul 2026 | Aug 2026
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQQBH-RES | QUEENSBORO HILL - Resiliency | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2026 | Sep 2026 | Aug 2026 | Sep 2026
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQQV-TECH | QUEENS VILLAGE: Improvements | 1 | DESIGN | Jan 2019 | Dec 2020 | Jan 2019 | Dec 2020
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQQV-TECH | QUEENS VILLAGE: Improvements | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQQV-TECH | QUEENS VILLAGE: Improvements | 3 | CONSTRUCTION | Dec 2021 | Dec 2027 | Dec 2021 | Dec 2027
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQRH-RENO | Richmond Hill - Branch Renovation | 1 | DESIGN | Aug 2023 | Jul 2025 | Aug 2023 | Jul 2025
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQRH-RENO | Richmond Hill - Branch Renovation | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Jul 2026 | Jul 2025 | Jul 2026
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQRH-RENO | Richmond Hill - Branch Renovation | 3 | CONSTRUCTION | Jul 2026 | Jul 2032 | Jul 2026 | Jul 2032
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSE-ROOF | SEASIDE: New Roof | 1 | DESIGN | Jan 2019 | Dec 2020 | Jan 2019 | Dec 2020
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSE-ROOF | SEASIDE: New Roof | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSE-ROOF | SEASIDE: New Roof | 3 | CONSTRUCTION | Dec 2021 | Dec 2027 | Dec 2021 | Dec 2027
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSE-WIN | SEASIDE: Windows and Doors | 1 | DESIGN | Jan 2019 | Dec 2020 | Jan 2019 | Dec 2020
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSE-WIN | SEASIDE: Windows and Doors | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSE-WIN | SEASIDE: Windows and Doors | 3 | CONSTRUCTION | Dec 2021 | Dec 2027 | Dec 2021 | Dec 2027
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSJ-INT | SOUTH JAMAICA: Branch Renovation | 1 | DESIGN | Jan 2019 | Dec 2020 | Jan 2019 | Dec 2020
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSJ-INT | SOUTH JAMAICA: Branch Renovation | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSJ-INT | SOUTH JAMAICA: Branch Renovation | 3 | CONSTRUCTION | Dec 2021 | Dec 2027 | Dec 2021 | Dec 2027
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSTWSOLR | STEINWAY: Solar Panels | 1 | DESIGN | Jan 2019 | Dec 2020 | Jan 2019 | Dec 2020
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSTWSOLR | STEINWAY: Solar Panels | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSTWSOLR | STEINWAY: Solar Panels | 3 | CONSTRUCTION | Dec 2021 | Dec 2027 | Dec 2021 | Dec 2027
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSZ-RENO | SOUTH OZONE PARK - Branch Expansion and Renovation | 1 | DESIGN | Jan 2019 | Dec 2020 | Jan 2019 | Dec 2020
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSZ-RENO | SOUTH OZONE PARK - Branch Expansion and Renovation | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSZ-RENO | SOUTH OZONE PARK - Branch Expansion and Renovation | 3 | CONSTRUCTION | Dec 2021 | Dec 2027 | Dec 2021 | Dec 2027
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWP-MASO | WINDSOR PARK - MASONRY | 1 | DESIGN | Jan 2019 | Dec 2020 | Jan 2019 | Dec 2020
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWP-MASO | WINDSOR PARK - MASONRY | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWP-MASO | WINDSOR PARK - MASONRY | 3 | CONSTRUCTION | Dec 2021 | Dec 2027 | Dec 2021 | Dec 2027
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWP-TECH | WINDSOR PARK: Improvement | 1 | DESIGN | Jan 2019 | Dec 2020 | Jan 2019 | Dec 2020
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWP-TECH | WINDSOR PARK: Improvement | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWP-TECH | WINDSOR PARK: Improvement | 3 | CONSTRUCTION | Dec 2021 | Dec 2027 | Dec 2021 | Dec 2027
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWS-TEEN | WOODSIDE: Renovation | 1 | DESIGN | Jan 2019 | Dec 2020 | Jan 2019 | Dec 2020
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWS-TEEN | WOODSIDE: Renovation | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWS-TEEN | WOODSIDE: Renovation | 3 | CONSTRUCTION | Dec 2021 | Dec 2027 | Dec 2021 | Dec 2027
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWSTTECH | WHITESTONE: Technology Initiative | 1 | DESIGN | Jan 2019 | Dec 2020 | Jan 2019 | Dec 2020
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWSTTECH | WHITESTONE: Technology Initiative | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWSTTECH | WHITESTONE: Technology Initiative | 3 | CONSTRUCTION | Dec 2021 | Dec 2027 | Dec 2021 | Dec 2027
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | SANDYLQLS | SANDY DAMAGES - QBPL | 1 | DESIGN | Jan 2019 | Dec 2020 | Jan 2019 | Dec 2020
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | SANDYLQLS | SANDY DAMAGES - QBPL | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | SANDYLQLS | SANDY DAMAGES - QBPL | 3 | CONSTRUCTION | Dec 2021 | Dec 2027 | Dec 2021 | Dec 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN215 | CUNY - Portfolio Submetering - LaGuardia CC | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2023 | Jun 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN215 | CUNY - Portfolio Submetering - LaGuardia CC | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN215 | CUNY - Portfolio Submetering - LaGuardia CC | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN215 | CUNY - Portfolio Submetering - LaGuardia CC | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN215 | CUNY - Portfolio Submetering - LaGuardia CC | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN215 | CUNY - Portfolio Submetering - LaGuardia CC | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN216 | CUNY - Portfolio Submetering - Queensborough CC | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2023 | Jun 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN216 | CUNY - Portfolio Submetering - Queensborough CC | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN216 | CUNY - Portfolio Submetering - Queensborough CC | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN216 | CUNY - Portfolio Submetering - Queensborough CC | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN216 | CUNY - Portfolio Submetering - Queensborough CC | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN216 | CUNY - Portfolio Submetering - Queensborough CC | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN218 | CUNY - LaGuardia CC - HVAC Upgrades | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2023 | Jun 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN218 | CUNY - LaGuardia CC - HVAC Upgrades | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2023 | Aug 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN218 | CUNY - LaGuardia CC - HVAC Upgrades | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2023 | Feb 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN218 | CUNY - LaGuardia CC - HVAC Upgrades | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2024 | May 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN218 | CUNY - LaGuardia CC - HVAC Upgrades | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2024 | Jul 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN218 | CUNY - LaGuardia CC - HVAC Upgrades | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2024 | Aug 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN223 | CUNY - Queensborough Community College: Central Chiller Plan | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2023 | Jun 2023 | Jun 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN223 | CUNY - Queensborough Community College: Central Chiller Plan | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN223 | CUNY - Queensborough Community College: Central Chiller Plan | 3 | CONSTRUCTION TO 50% | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN223 | CUNY - Queensborough Community College: Central Chiller Plan | 4 | CONSTRUCTION TO 75% | Feb 2024 | May 2024 | Feb 2024 | May 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN223 | CUNY - Queensborough Community College: Central Chiller Plan | 5 | SUBSTANTIAL COMPLETION | May 2024 | Jul 2024 | May 2024 | Jul 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN223 | CUNY - Queensborough Community College: Central Chiller Plan | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN234 | Laguardia Community College BMS Upgrade | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2023 | Jun 2023 | Jun 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN234 | Laguardia Community College BMS Upgrade | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN234 | Laguardia Community College BMS Upgrade | 3 | CONSTRUCTION TO 50% | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN234 | Laguardia Community College BMS Upgrade | 4 | CONSTRUCTION TO 75% | Feb 2024 | May 2024 | Feb 2024 | May 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN234 | Laguardia Community College BMS Upgrade | 5 | SUBSTANTIAL COMPLETION | May 2024 | Jul 2024 | May 2024 | Jul 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN234 | Laguardia Community College BMS Upgrade | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN801 | CUNY - Building Automation Controls Upgrade @ QCC | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jun 2018 | Aug 2018
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN801 | CUNY - Building Automation Controls Upgrade @ QCC | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Aug 2018 | Dec 2018
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN801 | CUNY - Building Automation Controls Upgrade @ QCC | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Dec 2018 | Jun 2019
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN801 | CUNY - Building Automation Controls Upgrade @ QCC | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN801 | CUNY - Building Automation Controls Upgrade @ QCC | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN801 | CUNY - Building Automation Controls Upgrade @ QCC | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Jan 2020 | May 2020
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN801 | CUNY - Building Automation Controls Upgrade @ QCC | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | May 2020 | Sep 2020
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN801 | CUNY - Building Automation Controls Upgrade @ QCC | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Sep 2020 | Dec 2020
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN801 | CUNY - Building Automation Controls Upgrade @ QCC | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Dec 2020 | Feb 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | ACECUN801 | CUNY - Building Automation Controls Upgrade @ QCC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Feb 2021 | Jul 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA008QB01 | Underground High Temperature Hot Water Piping | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA008QB01 | Underground High Temperature Hot Water Piping | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA008QB01 | Underground High Temperature Hot Water Piping | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA008QB01 | Underground High Temperature Hot Water Piping | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA008QB01 | Underground High Temperature Hot Water Piping | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA008QB01 | Underground High Temperature Hot Water Piping | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA008QB01 | Underground High Temperature Hot Water Piping | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA008QB01 | Underground High Temperature Hot Water Piping | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA008QB01 | Underground High Temperature Hot Water Piping | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA008QB01 | Underground High Temperature Hot Water Piping | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA022QB01 | Boiler Improvements | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA022QB01 | Boiler Improvements | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA022QB01 | Boiler Improvements | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA022QB01 | Boiler Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA022QB01 | Boiler Improvements | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA022QB01 | Boiler Improvements | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA022QB01 | Boiler Improvements | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA022QB01 | Boiler Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA022QB01 | Boiler Improvements | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA022QB01 | Boiler Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA034QB13 | Fire Alarm Reconstruction - Phase 3 | 1 | DEVELOP SCOPE | Jun 2017 | Aug 2017 | Jun 2017 | Aug 2017
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA034QB13 | Fire Alarm Reconstruction - Phase 3 | 2 | PRELIMINARY DESIGN | Aug 2017 | Dec 2017 | Aug 2017 | Dec 2017
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA034QB13 | Fire Alarm Reconstruction - Phase 3 | 3 | FINAL DESIGN | Dec 2017 | Jun 2018 | Dec 2017 | Jun 2018
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA034QB13 | Fire Alarm Reconstruction - Phase 3 | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA034QB13 | Fire Alarm Reconstruction - Phase 3 | 5 | CONSTRUCTION TO 25% | Sep 2018 | Jan 2019 | Sep 2018 | Jan 2019
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA034QB13 | Fire Alarm Reconstruction - Phase 3 | 6 | CONSTRUCTION TO 50% | Jan 2019 | May 2019 | Jan 2019 | May 2019
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA034QB13 | Fire Alarm Reconstruction - Phase 3 | 7 | CONSTRUCTION TO 75% | May 2019 | Sep 2019 | May 2019 | Sep 2019
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA034QB13 | Fire Alarm Reconstruction - Phase 3 | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Dec 2019 | Sep 2019 | Dec 2019
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA034QB13 | Fire Alarm Reconstruction - Phase 3 | 9 | SUBSTANTIAL COMPLETION | Dec 2019 | Feb 2020 | Dec 2019 | Feb 2020
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA034QB13 | Fire Alarm Reconstruction - Phase 3 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2020 | Mar 2020 | Feb 2020 | Mar 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA052-017 | Flushing Immigration Center | 1 | DEVELOP SCOPE | Jun 2017 | Aug 2017 | Jul 2020 | Oct 2020
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA052-017 | Flushing Immigration Center | 2 | PRELIMINARY DESIGN | Aug 2017 | Dec 2017 | Oct 2020 | Jan 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA052-017 | Flushing Immigration Center | 3 | FINAL DESIGN | Dec 2017 | Jun 2018 | Jan 2021 | Jul 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA052-017 | Flushing Immigration Center | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Sep 2018 | Jul 2021 | Oct 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA052-017 | Flushing Immigration Center | 5 | CONSTRUCTION TO 25% | Sep 2018 | Jan 2019 | Oct 2021 | Feb 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA052-017 | Flushing Immigration Center | 6 | CONSTRUCTION TO 50% | Jan 2019 | May 2019 | Feb 2022 | Jun 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA052-017 | Flushing Immigration Center | 7 | CONSTRUCTION TO 75% | May 2019 | Sep 2019 | Jun 2022 | Oct 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA052-017 | Flushing Immigration Center | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Dec 2019 | Oct 2022 | Jan 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA052-017 | Flushing Immigration Center | 9 | SUBSTANTIAL COMPLETION | Dec 2019 | Feb 2020 | Jan 2023 | Mar 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA052-017 | Flushing Immigration Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2020 | Mar 2020 | Mar 2023 | May 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA055QB17 | CUNY ASAP Expansion | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jul 2020 | Sep 2020
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA055QB17 | CUNY ASAP Expansion | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2020 | Jan 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA055QB17 | CUNY ASAP Expansion | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2021 | Jul 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA055QB17 | CUNY ASAP Expansion | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2021 | Oct 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA055QB17 | CUNY ASAP Expansion | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2021 | Feb 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA055QB17 | CUNY ASAP Expansion | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2022 | Jun 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA055QB17 | CUNY ASAP Expansion | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2022 | Oct 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA055QB17 | CUNY ASAP Expansion | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2022 | Jan 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA055QB17 | CUNY ASAP Expansion | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2023 | Mar 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA055QB17 | CUNY ASAP Expansion | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2023 | Apr 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091LG22 | E Building North Roof Replacement | 1 | DEVELOP SCOPE | Jul 2023 | Sep 2023 | Jul 2023 | Sep 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091LG22 | E Building North Roof Replacement | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091LG22 | E Building North Roof Replacement | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091LG22 | E Building North Roof Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091LG22 | E Building North Roof Replacement | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091LG22 | E Building North Roof Replacement | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091LG22 | E Building North Roof Replacement | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091LG22 | E Building North Roof Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091LG22 | E Building North Roof Replacement | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091LG22 | E Building North Roof Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2028 | Mar 2026 | Apr 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091LG23 | LGCC M Building HVAC Replacement | 1 | DEVELOP SCOPE | Jul 2023 | Sep 2023 | Jul 2023 | Sep 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091LG23 | LGCC M Building HVAC Replacement | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091LG23 | LGCC M Building HVAC Replacement | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091LG23 | LGCC M Building HVAC Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091LG23 | LGCC M Building HVAC Replacement | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091LG23 | LGCC M Building HVAC Replacement | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091LG23 | LGCC M Building HVAC Replacement | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091LG23 | LGCC M Building HVAC Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091LG23 | LGCC M Building HVAC Replacement | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091LG23 | LGCC M Building HVAC Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB23 | QBCC - Science and Med Arts Elevator Project | 1 | DEVELOP SCOPE | Jul 2023 | Sep 2023 | Jul 2023 | Sep 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB23 | QBCC - Science and Med Arts Elevator Project | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB23 | QBCC - Science and Med Arts Elevator Project | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB23 | QBCC - Science and Med Arts Elevator Project | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB23 | QBCC - Science and Med Arts Elevator Project | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB23 | QBCC - Science and Med Arts Elevator Project | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB23 | QBCC - Science and Med Arts Elevator Project | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB23 | QBCC - Science and Med Arts Elevator Project | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB23 | QBCC - Science and Med Arts Elevator Project | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB23 | QBCC - Science and Med Arts Elevator Project | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB24 | LL97 AHU Replacement | 1 | DEVELOP SCOPE | Jul 2023 | Sep 2023 | Jul 2023 | Sep 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB24 | LL97 AHU Replacement | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB24 | LL97 AHU Replacement | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB24 | LL97 AHU Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB24 | LL97 AHU Replacement | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB24 | LL97 AHU Replacement | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB24 | LL97 AHU Replacement | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB24 | LL97 AHU Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB24 | LL97 AHU Replacement | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB24 | LL97 AHU Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB25 | LL97 Fan Systems Replacements | 1 | DEVELOP SCOPE | Jul 2023 | Sep 2023 | Jul 2023 | Sep 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB25 | LL97 Fan Systems Replacements | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB25 | LL97 Fan Systems Replacements | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB25 | LL97 Fan Systems Replacements | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB25 | LL97 Fan Systems Replacements | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB25 | LL97 Fan Systems Replacements | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB25 | LL97 Fan Systems Replacements | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB25 | LL97 Fan Systems Replacements | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB25 | LL97 Fan Systems Replacements | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB25 | LL97 Fan Systems Replacements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB26 | LL97 Heat Recovery Boiler Plant | 1 | DEVELOP SCOPE | Jul 2023 | Sep 2023 | Jul 2023 | Sep 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB26 | LL97 Heat Recovery Boiler Plant | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB26 | LL97 Heat Recovery Boiler Plant | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB26 | LL97 Heat Recovery Boiler Plant | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB26 | LL97 Heat Recovery Boiler Plant | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB26 | LL97 Heat Recovery Boiler Plant | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB26 | LL97 Heat Recovery Boiler Plant | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB26 | LL97 Heat Recovery Boiler Plant | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB26 | LL97 Heat Recovery Boiler Plant | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | CA091QB26 | LL97 Heat Recovery Boiler Plant | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL001-024 | CUNY SCHOOL OF LAW REPURPOSE SPACE | 1 | DEVELOP SCOPE | Jul 2023 | Sep 2024 | Jul 2023 | Sep 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL001-024 | CUNY SCHOOL OF LAW REPURPOSE SPACE | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL001-024 | CUNY SCHOOL OF LAW REPURPOSE SPACE | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL001-024 | CUNY SCHOOL OF LAW REPURPOSE SPACE | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL001-024 | CUNY SCHOOL OF LAW REPURPOSE SPACE | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL001-024 | CUNY SCHOOL OF LAW REPURPOSE SPACE | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL001-024 | CUNY SCHOOL OF LAW REPURPOSE SPACE | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL001-024 | CUNY SCHOOL OF LAW REPURPOSE SPACE | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL001-024 | CUNY SCHOOL OF LAW REPURPOSE SPACE | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL001-024 | CUNY SCHOOL OF LAW REPURPOSE SPACE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL002-024 | Commercial Kitchen Conversion | 1 | DEVELOP SCOPE | Jun 2025 | Sep 2026 | Jun 2025 | Sep 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL002-024 | Commercial Kitchen Conversion | 2 | PRELIMINARY DESIGN | Sep 2026 | Jan 2027 | Sep 2026 | Jan 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL002-024 | Commercial Kitchen Conversion | 3 | FINAL DESIGN | Jan 2027 | Jul 2027 | Jan 2027 | Jul 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL002-024 | Commercial Kitchen Conversion | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2027 | Oct 2027 | Jul 2027 | Oct 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL002-024 | Commercial Kitchen Conversion | 5 | CONSTRUCTION TO 25% | Oct 2027 | Feb 2028 | Oct 2027 | Feb 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL002-024 | Commercial Kitchen Conversion | 6 | CONSTRUCTION TO 50% | Feb 2028 | Jun 2028 | Feb 2028 | Jun 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL002-024 | Commercial Kitchen Conversion | 7 | CONSTRUCTION TO 75% | Jun 2028 | Oct 2028 | Jun 2028 | Oct 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL002-024 | Commercial Kitchen Conversion | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2028 | Jan 2029 | Oct 2028 | Jan 2029
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL002-024 | Commercial Kitchen Conversion | 9 | SUBSTANTIAL COMPLETION | Jan 2029 | Mar 2029 | Jan 2029 | Mar 2029
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL002-024 | Commercial Kitchen Conversion | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2029 | Apr 2029 | Mar 2029 | Apr 2029
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL018-015 | Trial Practice Room | 1 | DEVELOP SCOPE | Mar 2015 | May 2015 | Mar 2015 | May 2015
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL018-015 | Trial Practice Room | 2 | PRELIMINARY DESIGN | May 2015 | Sep 2015 | May 2015 | Sep 2015
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL018-015 | Trial Practice Room | 3 | FINAL DESIGN | Sep 2015 | Mar 2016 | Sep 2015 | Mar 2016
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL018-015 | Trial Practice Room | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2016 | Jun 2016 | Mar 2016 | Jun 2016
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL018-015 | Trial Practice Room | 5 | CONSTRUCTION TO 25% | Jun 2016 | Oct 2016 | Jun 2016 | Oct 2016
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL018-015 | Trial Practice Room | 6 | CONSTRUCTION TO 50% | Oct 2016 | Feb 2017 | Oct 2016 | Feb 2017
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL018-015 | Trial Practice Room | 7 | CONSTRUCTION TO 75% | Feb 2017 | Jun 2017 | Feb 2017 | Jun 2017
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL018-015 | Trial Practice Room | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2017 | Sep 2017 | Jun 2017 | Sep 2017
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL018-015 | Trial Practice Room | 9 | SUBSTANTIAL COMPLETION | Sep 2017 | Nov 2017 | Sep 2017 | Nov 2017
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL018-015 | Trial Practice Room | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | Dec 2017 | Nov 2017 | Jun 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL021-018 | Renovation of Community Room | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jul 2021 | Oct 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL021-018 | Renovation of Community Room | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Oct 2021 | Jan 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL021-018 | Renovation of Community Room | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Jan 2022 | Jul 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL021-018 | Renovation of Community Room | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jul 2022 | Oct 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL021-018 | Renovation of Community Room | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Oct 2022 | Feb 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL021-018 | Renovation of Community Room | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Feb 2023 | Jun 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL021-018 | Renovation of Community Room | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | Jun 2023 | Oct 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL021-018 | Renovation of Community Room | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Oct 2023 | Jan 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL021-018 | Renovation of Community Room | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Jan 2024 | Mar 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL021-018 | Renovation of Community Room | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Mar 2024 | May 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL023-019 | Worker Educational and Development Center | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jul 2021 | Oct 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL023-019 | Worker Educational and Development Center | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Oct 2021 | Jan 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL023-019 | Worker Educational and Development Center | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2022 | Jul 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL023-019 | Worker Educational and Development Center | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2022 | Oct 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL023-019 | Worker Educational and Development Center | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2022 | Feb 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL023-019 | Worker Educational and Development Center | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2023 | Jun 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL023-019 | Worker Educational and Development Center | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2023 | Oct 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL023-019 | Worker Educational and Development Center | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2023 | Jan 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL023-019 | Worker Educational and Development Center | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2024 | Mar 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | CL023-019 | Worker Educational and Development Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2024 | Apr 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | KG037-015 | Science and Resilience Institute at Jamaica Bay | 1 | DEVELOP SCOPE | Jun 2014 | Aug 2014 | Jul 2022 | Sep 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | KG037-015 | Science and Resilience Institute at Jamaica Bay | 2 | PRELIMINARY DESIGN | Aug 2014 | Dec 2014 | Sep 2022 | Jan 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | KG037-015 | Science and Resilience Institute at Jamaica Bay | 3 | FINAL DESIGN | Dec 2014 | Jun 2015 | Jan 2023 | Jul 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | KG037-015 | Science and Resilience Institute at Jamaica Bay | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2015 | Sep 2015 | Jul 2023 | Oct 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | KG037-015 | Science and Resilience Institute at Jamaica Bay | 5 | CONSTRUCTION TO 25% | Sep 2015 | Jan 2016 | Oct 2023 | Feb 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | KG037-015 | Science and Resilience Institute at Jamaica Bay | 6 | CONSTRUCTION TO 50% | Jan 2016 | May 2016 | Feb 2024 | Jun 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | KG037-015 | Science and Resilience Institute at Jamaica Bay | 7 | CONSTRUCTION TO 75% | May 2016 | Sep 2016 | Jun 2024 | Oct 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | KG037-015 | Science and Resilience Institute at Jamaica Bay | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Dec 2016 | Oct 2024 | Jan 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | KG037-015 | Science and Resilience Institute at Jamaica Bay | 9 | SUBSTANTIAL COMPLETION | Dec 2016 | Feb 2017 | Jan 2025 | Mar 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | KG037-015 | Science and Resilience Institute at Jamaica Bay | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2017 | Mar 2017 | Mar 2025 | Jul 2030
20231026 | QUEENS | 042 | CITY UNIVERSITY | LAGUARDIA | LaGuardia Community College Streetscape | 1 | DEVELOP SCOPE | Mar 2007 | May 2007 | Mar 2007 | May 2007
20231026 | QUEENS | 042 | CITY UNIVERSITY | LAGUARDIA | LaGuardia Community College Streetscape | 2 | PRELIMINARY DESIGN | May 2007 | Sep 2007 | May 2007 | Sep 2007
20231026 | QUEENS | 042 | CITY UNIVERSITY | LAGUARDIA | LaGuardia Community College Streetscape | 3 | FINAL DESIGN | Sep 2007 | Mar 2008 | Sep 2007 | Mar 2008
20231026 | QUEENS | 042 | CITY UNIVERSITY | LAGUARDIA | LaGuardia Community College Streetscape | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2008 | Jun 2008 | Mar 2008 | Jun 2008
20231026 | QUEENS | 042 | CITY UNIVERSITY | LAGUARDIA | LaGuardia Community College Streetscape | 5 | CONSTRUCTION TO 25% | Jun 2008 | Oct 2008 | Jun 2008 | Oct 2008
20231026 | QUEENS | 042 | CITY UNIVERSITY | LAGUARDIA | LaGuardia Community College Streetscape | 6 | CONSTRUCTION TO 50% | Oct 2008 | Feb 2009 | Oct 2008 | Feb 2009
20231026 | QUEENS | 042 | CITY UNIVERSITY | LAGUARDIA | LaGuardia Community College Streetscape | 7 | CONSTRUCTION TO 75% | Feb 2009 | Jun 2009 | Feb 2009 | Jun 2009
20231026 | QUEENS | 042 | CITY UNIVERSITY | LAGUARDIA | LaGuardia Community College Streetscape | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2009 | Sep 2009 | Jun 2009 | Sep 2009
20231026 | QUEENS | 042 | CITY UNIVERSITY | LAGUARDIA | LaGuardia Community College Streetscape | 9 | SUBSTANTIAL COMPLETION | Sep 2009 | Nov 2009 | Sep 2009 | Nov 2009
20231026 | QUEENS | 042 | CITY UNIVERSITY | LAGUARDIA | LaGuardia Community College Streetscape | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2009 | Dec 2009 | Nov 2009 | Nov 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG001-023 | CONVERT TRAINING SPACE TO ALLOW HANDS-ON EDUCATION AND SKILL | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG001-023 | CONVERT TRAINING SPACE TO ALLOW HANDS-ON EDUCATION AND SKILL | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG001-023 | CONVERT TRAINING SPACE TO ALLOW HANDS-ON EDUCATION AND SKILL | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG001-023 | CONVERT TRAINING SPACE TO ALLOW HANDS-ON EDUCATION AND SKILL | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG001-023 | CONVERT TRAINING SPACE TO ALLOW HANDS-ON EDUCATION AND SKILL | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG001-023 | CONVERT TRAINING SPACE TO ALLOW HANDS-ON EDUCATION AND SKILL | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG001-023 | CONVERT TRAINING SPACE TO ALLOW HANDS-ON EDUCATION AND SKILL | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG001-023 | CONVERT TRAINING SPACE TO ALLOW HANDS-ON EDUCATION AND SKILL | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG001-023 | CONVERT TRAINING SPACE TO ALLOW HANDS-ON EDUCATION AND SKILL | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG001-023 | CONVERT TRAINING SPACE TO ALLOW HANDS-ON EDUCATION AND SKILL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG001-024 | POOL FACILITY RENOVATION | 1 | DEVELOP SCOPE | Jul 2023 | Sep 2024 | Jul 2023 | Sep 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG001-024 | POOL FACILITY RENOVATION | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG001-024 | POOL FACILITY RENOVATION | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG001-024 | POOL FACILITY RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG001-024 | POOL FACILITY RENOVATION | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG001-024 | POOL FACILITY RENOVATION | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG001-024 | POOL FACILITY RENOVATION | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG001-024 | POOL FACILITY RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG001-024 | POOL FACILITY RENOVATION | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG001-024 | POOL FACILITY RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG002-021 | Greenhouse Construction | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG002-021 | Greenhouse Construction | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG002-021 | Greenhouse Construction | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG002-021 | Greenhouse Construction | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG002-021 | Greenhouse Construction | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG002-021 | Greenhouse Construction | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG002-021 | Greenhouse Construction | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG002-021 | Greenhouse Construction | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG002-021 | Greenhouse Construction | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG002-021 | Greenhouse Construction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG002-024 | Student Plaza Transformation | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2024 | Jun 2023 | Sep 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG002-024 | Student Plaza Transformation | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG002-024 | Student Plaza Transformation | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG002-024 | Student Plaza Transformation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG002-024 | Student Plaza Transformation | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG002-024 | Student Plaza Transformation | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG002-024 | Student Plaza Transformation | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG002-024 | Student Plaza Transformation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG002-024 | Student Plaza Transformation | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG002-024 | Student Plaza Transformation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG003-023 | Training Space Renovation Training Space Renovation | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG003-023 | Training Space Renovation Training Space Renovation | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG003-023 | Training Space Renovation Training Space Renovation | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG003-023 | Training Space Renovation Training Space Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG003-023 | Training Space Renovation Training Space Renovation | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG003-023 | Training Space Renovation Training Space Renovation | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG003-023 | Training Space Renovation Training Space Renovation | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG003-023 | Training Space Renovation Training Space Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG003-023 | Training Space Renovation Training Space Renovation | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG003-023 | Training Space Renovation Training Space Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2030
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG020-009 | NEW LIBRARY SPACE at LaGuardia CC | 1 | DEVELOP SCOPE | Jun 2009 | Aug 2009 | Jun 2009 | Aug 2009
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG020-009 | NEW LIBRARY SPACE at LaGuardia CC | 2 | PRELIMINARY DESIGN | Aug 2009 | Dec 2009 | Aug 2009 | Dec 2009
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG020-009 | NEW LIBRARY SPACE at LaGuardia CC | 3 | FINAL DESIGN | Dec 2009 | Jun 2010 | Dec 2009 | Jun 2010
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG020-009 | NEW LIBRARY SPACE at LaGuardia CC | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2010 | Sep 2010 | Jun 2010 | Sep 2010
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG020-009 | NEW LIBRARY SPACE at LaGuardia CC | 5 | CONSTRUCTION TO 25% | Sep 2010 | Jan 2011 | Sep 2010 | Jan 2011
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG020-009 | NEW LIBRARY SPACE at LaGuardia CC | 6 | CONSTRUCTION TO 50% | Jan 2011 | May 2011 | Jan 2011 | May 2011
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG020-009 | NEW LIBRARY SPACE at LaGuardia CC | 7 | CONSTRUCTION TO 75% | May 2011 | Sep 2011 | May 2011 | Sep 2011
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG020-009 | NEW LIBRARY SPACE at LaGuardia CC | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2011 | Dec 2011 | Sep 2011 | Dec 2011
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG020-009 | NEW LIBRARY SPACE at LaGuardia CC | 9 | SUBSTANTIAL COMPLETION | Dec 2011 | Feb 2012 | Dec 2011 | Feb 2012
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG020-009 | NEW LIBRARY SPACE at LaGuardia CC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2012 | Mar 2012 | Feb 2012 | Dec 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG024-009 | ADA UPGRADES | 2 | PRELIMINARY DESIGN | Aug 2010 | Dec 2010 | Aug 2010 | Dec 2010
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG024-009 | ADA UPGRADES | 3 | FINAL DESIGN | Dec 2010 | Jun 2011 | Dec 2010 | Jun 2011
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG024-009 | ADA UPGRADES | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2011 | Sep 2011 | Jun 2011 | Sep 2011
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG024-009 | ADA UPGRADES | 5 | CONSTRUCTION TO 25% | Sep 2011 | Jan 2012 | Sep 2011 | Jan 2012
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG024-009 | ADA UPGRADES | 6 | CONSTRUCTION TO 50% | Jan 2012 | May 2012 | Jan 2012 | May 2012
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG024-009 | ADA UPGRADES | 7 | CONSTRUCTION TO 75% | May 2012 | Sep 2012 | May 2012 | Sep 2012
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG024-009 | ADA UPGRADES | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2012 | Dec 2012 | Sep 2012 | Dec 2012
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG024-009 | ADA UPGRADES | 9 | SUBSTANTIAL COMPLETION | Dec 2012 | Feb 2013 | Dec 2012 | Feb 2013
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG024-009 | ADA UPGRADES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2013 | Mar 2013 | Feb 2013 | Mar 2013
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG024-022 | E Bldg - Scince & Occu Physical Therapy Labs Recon | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG024-022 | E Bldg - Scince & Occu Physical Therapy Labs Recon | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG024-022 | E Bldg - Scince & Occu Physical Therapy Labs Recon | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG024-022 | E Bldg - Scince & Occu Physical Therapy Labs Recon | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG024-022 | E Bldg - Scince & Occu Physical Therapy Labs Recon | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG024-022 | E Bldg - Scince & Occu Physical Therapy Labs Recon | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG024-022 | E Bldg - Scince & Occu Physical Therapy Labs Recon | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG024-022 | E Bldg - Scince & Occu Physical Therapy Labs Recon | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG024-022 | E Bldg - Scince & Occu Physical Therapy Labs Recon | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG024-022 | E Bldg - Scince & Occu Physical Therapy Labs Recon | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG036-014 | Library Expansion and HVAC Upgrade | 1 | DEVELOP SCOPE | Jun 2014 | Aug 2014 | Jul 2020 | Sep 2020
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG036-014 | Library Expansion and HVAC Upgrade | 2 | PRELIMINARY DESIGN | Aug 2014 | Dec 2014 | Sep 2020 | Jan 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG036-014 | Library Expansion and HVAC Upgrade | 3 | FINAL DESIGN | Dec 2014 | Jun 2015 | Jan 2021 | Jul 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG036-014 | Library Expansion and HVAC Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2015 | Sep 2015 | Jul 2021 | Oct 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG036-014 | Library Expansion and HVAC Upgrade | 5 | CONSTRUCTION TO 25% | Sep 2015 | Jan 2016 | Oct 2021 | Feb 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG036-014 | Library Expansion and HVAC Upgrade | 6 | CONSTRUCTION TO 50% | Jan 2016 | May 2016 | Feb 2022 | Jun 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG036-014 | Library Expansion and HVAC Upgrade | 7 | CONSTRUCTION TO 75% | May 2016 | Sep 2016 | Jun 2022 | Oct 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG036-014 | Library Expansion and HVAC Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Dec 2016 | Oct 2022 | Jan 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG036-014 | Library Expansion and HVAC Upgrade | 9 | SUBSTANTIAL COMPLETION | Dec 2016 | Feb 2017 | Jan 2023 | Mar 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG036-014 | Library Expansion and HVAC Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2017 | Mar 2017 | Mar 2023 | Jul 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG041-016 | Business and Entrepreneurial Training Center | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Jul 2020 | Sep 2020
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG041-016 | Business and Entrepreneurial Training Center | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Sep 2020 | Jan 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG041-016 | Business and Entrepreneurial Training Center | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Jan 2021 | Jul 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG041-016 | Business and Entrepreneurial Training Center | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Jul 2021 | Oct 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG041-016 | Business and Entrepreneurial Training Center | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Oct 2021 | Feb 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG041-016 | Business and Entrepreneurial Training Center | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Feb 2022 | Jun 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG041-016 | Business and Entrepreneurial Training Center | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Jun 2022 | Oct 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG041-016 | Business and Entrepreneurial Training Center | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | Oct 2022 | Jan 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG041-016 | Business and Entrepreneurial Training Center | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Jan 2023 | Mar 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG041-016 | Business and Entrepreneurial Training Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Mar 2023 | Jul 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG043-018 | Shenker Hall Lab Renovation | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jun 2019 | Sep 2020
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG043-018 | Shenker Hall Lab Renovation | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Sep 2020 | Jan 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG043-018 | Shenker Hall Lab Renovation | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Jan 2021 | Jul 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG043-018 | Shenker Hall Lab Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jul 2021 | Oct 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG043-018 | Shenker Hall Lab Renovation | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Oct 2021 | Feb 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG043-018 | Shenker Hall Lab Renovation | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Feb 2022 | Jun 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG043-018 | Shenker Hall Lab Renovation | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | Jun 2022 | Oct 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG043-018 | Shenker Hall Lab Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Oct 2022 | Jan 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG043-018 | Shenker Hall Lab Renovation | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Jan 2023 | Mar 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG043-018 | Shenker Hall Lab Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Mar 2023 | Apr 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG071-019 | Student Success Center: Tutoring Hub | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jun 2025 | Sep 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG071-019 | Student Success Center: Tutoring Hub | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Sep 2025 | Jan 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG071-019 | Student Success Center: Tutoring Hub | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2026 | Jul 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG071-019 | Student Success Center: Tutoring Hub | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2026 | Oct 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG071-019 | Student Success Center: Tutoring Hub | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2026 | Feb 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG071-019 | Student Success Center: Tutoring Hub | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2027 | Jun 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG071-019 | Student Success Center: Tutoring Hub | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2027 | Oct 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG071-019 | Student Success Center: Tutoring Hub | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2027 | Jan 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG071-019 | Student Success Center: Tutoring Hub | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2028 | Mar 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG071-019 | Student Success Center: Tutoring Hub | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2028 | Apr 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG072-019 | Archive Construction | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jul 2019 | Sep 2019
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG072-019 | Archive Construction | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG072-019 | Archive Construction | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG072-019 | Archive Construction | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG072-019 | Archive Construction | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG072-019 | Archive Construction | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG072-019 | Archive Construction | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG072-019 | Archive Construction | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG072-019 | Archive Construction | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG072-019 | Archive Construction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Apr 2031
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG073-020 | LIBRARY PHASE II CONSTRUCTION | 1 | DEVELOP SCOPE | Jul 2019 | Sep 2019 | Jun 2025 | Sep 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG073-020 | LIBRARY PHASE II CONSTRUCTION | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2025 | Jan 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG073-020 | LIBRARY PHASE II CONSTRUCTION | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2026 | Jul 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG073-020 | LIBRARY PHASE II CONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2026 | Oct 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG073-020 | LIBRARY PHASE II CONSTRUCTION | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2026 | Feb 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG073-020 | LIBRARY PHASE II CONSTRUCTION | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2027 | Jun 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG073-020 | LIBRARY PHASE II CONSTRUCTION | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2027 | Oct 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG073-020 | LIBRARY PHASE II CONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2027 | Jan 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG073-020 | LIBRARY PHASE II CONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2028 | Mar 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | LG073-020 | LIBRARY PHASE II CONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2028 | Apr 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-021 | ADA Restroom Upgrades | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2025 | Sep 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-021 | ADA Restroom Upgrades | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2025 | Jan 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-021 | ADA Restroom Upgrades | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2026 | Jul 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-021 | ADA Restroom Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2026 | Oct 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-021 | ADA Restroom Upgrades | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2026 | Feb 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-021 | ADA Restroom Upgrades | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2027 | Jun 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-021 | ADA Restroom Upgrades | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2027 | Oct 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-021 | ADA Restroom Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2027 | Jan 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-021 | ADA Restroom Upgrades | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2028 | Mar 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-021 | ADA Restroom Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2028 | Apr 2030
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-022 | Renovate Chemistry Lab | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-022 | Renovate Chemistry Lab | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-022 | Renovate Chemistry Lab | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-022 | Renovate Chemistry Lab | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-022 | Renovate Chemistry Lab | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-022 | Renovate Chemistry Lab | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-022 | Renovate Chemistry Lab | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-022 | Renovate Chemistry Lab | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-022 | Renovate Chemistry Lab | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-022 | Renovate Chemistry Lab | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-023 | KENNEDY HALL GYMNASIUM - LOCKER AND SHOWER ROOM RENOVATION | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-023 | KENNEDY HALL GYMNASIUM - LOCKER AND SHOWER ROOM RENOVATION | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-023 | KENNEDY HALL GYMNASIUM - LOCKER AND SHOWER ROOM RENOVATION | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-023 | KENNEDY HALL GYMNASIUM - LOCKER AND SHOWER ROOM RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-023 | KENNEDY HALL GYMNASIUM - LOCKER AND SHOWER ROOM RENOVATION | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-023 | KENNEDY HALL GYMNASIUM - LOCKER AND SHOWER ROOM RENOVATION | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-023 | KENNEDY HALL GYMNASIUM - LOCKER AND SHOWER ROOM RENOVATION | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-023 | KENNEDY HALL GYMNASIUM - LOCKER AND SHOWER ROOM RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-023 | KENNEDY HALL GYMNASIUM - LOCKER AND SHOWER ROOM RENOVATION | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-023 | KENNEDY HALL GYMNASIUM - LOCKER AND SHOWER ROOM RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-024 | SCIENCE BUILDING - CAFETERIA AND KITCHEN PHASE II | 1 | DEVELOP SCOPE | Jul 2023 | Sep 2024 | Jul 2023 | Sep 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-024 | SCIENCE BUILDING - CAFETERIA AND KITCHEN PHASE II | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-024 | SCIENCE BUILDING - CAFETERIA AND KITCHEN PHASE II | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-024 | SCIENCE BUILDING - CAFETERIA AND KITCHEN PHASE II | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-024 | SCIENCE BUILDING - CAFETERIA AND KITCHEN PHASE II | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-024 | SCIENCE BUILDING - CAFETERIA AND KITCHEN PHASE II | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-024 | SCIENCE BUILDING - CAFETERIA AND KITCHEN PHASE II | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-024 | SCIENCE BUILDING - CAFETERIA AND KITCHEN PHASE II | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-024 | SCIENCE BUILDING - CAFETERIA AND KITCHEN PHASE II | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB001-024 | SCIENCE BUILDING - CAFETERIA AND KITCHEN PHASE II | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB002-024 | Cafeteria and Kitchen Renovation Project | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2024 | Jun 2023 | Sep 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB002-024 | Cafeteria and Kitchen Renovation Project | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB002-024 | Cafeteria and Kitchen Renovation Project | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB002-024 | Cafeteria and Kitchen Renovation Project | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB002-024 | Cafeteria and Kitchen Renovation Project | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB002-024 | Cafeteria and Kitchen Renovation Project | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB002-024 | Cafeteria and Kitchen Renovation Project | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB002-024 | Cafeteria and Kitchen Renovation Project | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB002-024 | Cafeteria and Kitchen Renovation Project | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB002-024 | Cafeteria and Kitchen Renovation Project | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB023-022 | ADA Restroom Reconstruction | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB023-022 | ADA Restroom Reconstruction | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB023-022 | ADA Restroom Reconstruction | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB023-022 | ADA Restroom Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB023-022 | ADA Restroom Reconstruction | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB023-022 | ADA Restroom Reconstruction | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB023-022 | ADA Restroom Reconstruction | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB023-022 | ADA Restroom Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB023-022 | ADA Restroom Reconstruction | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB023-022 | ADA Restroom Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2029
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB031-007 | Cafeteria and Central Kitchen | 1 | DEVELOP SCOPE | May 2007 | Aug 2007 | May 2007 | Aug 2007
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB031-007 | Cafeteria and Central Kitchen | 2 | PRELIMINARY DESIGN | Aug 2007 | Dec 2007 | Aug 2007 | Dec 2007
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB031-007 | Cafeteria and Central Kitchen | 3 | FINAL DESIGN | Dec 2007 | Jun 2008 | Dec 2007 | Jun 2008
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB031-007 | Cafeteria and Central Kitchen | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2008 | Sep 2008 | Jun 2008 | Sep 2008
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB031-007 | Cafeteria and Central Kitchen | 5 | CONSTRUCTION TO 25% | Sep 2008 | Jan 2009 | Sep 2008 | Jan 2009
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB031-007 | Cafeteria and Central Kitchen | 6 | CONSTRUCTION TO 50% | Jan 2009 | May 2009 | Jan 2009 | May 2009
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB031-007 | Cafeteria and Central Kitchen | 7 | CONSTRUCTION TO 75% | May 2009 | Sep 2009 | May 2009 | Sep 2009
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB031-007 | Cafeteria and Central Kitchen | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2009 | Dec 2009 | Sep 2009 | Dec 2009
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB031-007 | Cafeteria and Central Kitchen | 9 | SUBSTANTIAL COMPLETION | Dec 2009 | Feb 2010 | Dec 2009 | Feb 2010
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB031-007 | Cafeteria and Central Kitchen | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2010 | Mar 2010 | Feb 2010 | Dec 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB041-011 | Fire Sprinklers and Standpipe System Restoration | 1 | DEVELOP SCOPE | Jun 2011 | Aug 2011 | Jun 2011 | Aug 2011
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB041-011 | Fire Sprinklers and Standpipe System Restoration | 2 | PRELIMINARY DESIGN | Aug 2011 | Dec 2011 | Aug 2011 | Dec 2011
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB041-011 | Fire Sprinklers and Standpipe System Restoration | 3 | FINAL DESIGN | Dec 2011 | Jun 2012 | Dec 2011 | Jun 2012
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB041-011 | Fire Sprinklers and Standpipe System Restoration | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2012 | Sep 2012 | Jun 2012 | Sep 2012
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB041-011 | Fire Sprinklers and Standpipe System Restoration | 5 | CONSTRUCTION TO 25% | Sep 2012 | Jan 2013 | Sep 2012 | Jan 2013
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB041-011 | Fire Sprinklers and Standpipe System Restoration | 6 | CONSTRUCTION TO 50% | Jan 2013 | May 2013 | Jan 2013 | May 2013
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB041-011 | Fire Sprinklers and Standpipe System Restoration | 7 | CONSTRUCTION TO 75% | May 2013 | Sep 2013 | May 2013 | Sep 2013
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB041-011 | Fire Sprinklers and Standpipe System Restoration | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB041-011 | Fire Sprinklers and Standpipe System Restoration | 9 | SUBSTANTIAL COMPLETION | Dec 2013 | Feb 2014 | Dec 2013 | Feb 2014
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB041-011 | Fire Sprinklers and Standpipe System Restoration | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2014 | Mar 2014 | Feb 2014 | Mar 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB054-016 | Refurbishment and Upgrade of Research Labs | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Jun 2016 | Sep 2016
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB054-016 | Refurbishment and Upgrade of Research Labs | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Sep 2016 | Jan 2017
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB054-016 | Refurbishment and Upgrade of Research Labs | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Jan 2017 | Jul 2017
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB054-016 | Refurbishment and Upgrade of Research Labs | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Jul 2017 | Oct 2017
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB054-016 | Refurbishment and Upgrade of Research Labs | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Oct 2017 | Feb 2018
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB054-016 | Refurbishment and Upgrade of Research Labs | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Feb 2018 | Jun 2018
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB054-016 | Refurbishment and Upgrade of Research Labs | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB054-016 | Refurbishment and Upgrade of Research Labs | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | Oct 2018 | Jan 2019
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB054-016 | Refurbishment and Upgrade of Research Labs | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Jan 2019 | Mar 2019
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB054-016 | Refurbishment and Upgrade of Research Labs | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Mar 2019 | Apr 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB062-020 | RFK Gymnasium Ventilation and Air Conditioning | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB062-020 | RFK Gymnasium Ventilation and Air Conditioning | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB062-020 | RFK Gymnasium Ventilation and Air Conditioning | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB062-020 | RFK Gymnasium Ventilation and Air Conditioning | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB062-020 | RFK Gymnasium Ventilation and Air Conditioning | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB062-020 | RFK Gymnasium Ventilation and Air Conditioning | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB062-020 | RFK Gymnasium Ventilation and Air Conditioning | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB062-020 | RFK Gymnasium Ventilation and Air Conditioning | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB062-020 | RFK Gymnasium Ventilation and Air Conditioning | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2023 | Mar 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB062-020 | RFK Gymnasium Ventilation and Air Conditioning | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2023 | Apr 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB063-020 | Theater Upgrades (PHASE II) | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB063-020 | Theater Upgrades (PHASE II) | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB063-020 | Theater Upgrades (PHASE II) | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB063-020 | Theater Upgrades (PHASE II) | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2023 | Mar 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QB063-020 | Theater Upgrades (PHASE II) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2023 | Apr 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-021 | Renovate and Upgrade Lab Spaces | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-021 | Renovate and Upgrade Lab Spaces | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-021 | Renovate and Upgrade Lab Spaces | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-021 | Renovate and Upgrade Lab Spaces | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-021 | Renovate and Upgrade Lab Spaces | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-021 | Renovate and Upgrade Lab Spaces | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-021 | Renovate and Upgrade Lab Spaces | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-021 | Renovate and Upgrade Lab Spaces | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-021 | Renovate and Upgrade Lab Spaces | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-021 | Renovate and Upgrade Lab Spaces | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-022 | Food and Science Mgmt Lab Renovation | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-022 | Food and Science Mgmt Lab Renovation | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-022 | Food and Science Mgmt Lab Renovation | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-022 | Food and Science Mgmt Lab Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-022 | Food and Science Mgmt Lab Renovation | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-022 | Food and Science Mgmt Lab Renovation | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-022 | Food and Science Mgmt Lab Renovation | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-022 | Food and Science Mgmt Lab Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-022 | Food and Science Mgmt Lab Renovation | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-022 | Food and Science Mgmt Lab Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-023 | RENOVATION OF RATHUS HALL | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-023 | RENOVATION OF RATHUS HALL | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-023 | RENOVATION OF RATHUS HALL | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-023 | RENOVATION OF RATHUS HALL | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-023 | RENOVATION OF RATHUS HALL | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-023 | RENOVATION OF RATHUS HALL | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-023 | RENOVATION OF RATHUS HALL | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-023 | RENOVATION OF RATHUS HALL | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-023 | RENOVATION OF RATHUS HALL | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-023 | RENOVATION OF RATHUS HALL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-024 | RENOVATION OF FOOD SCIENCE AND MANAGEMENT LABORATORY | 1 | DEVELOP SCOPE | Jul 2023 | Sep 2024 | Jul 2023 | Sep 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-024 | RENOVATION OF FOOD SCIENCE AND MANAGEMENT LABORATORY | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-024 | RENOVATION OF FOOD SCIENCE AND MANAGEMENT LABORATORY | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-024 | RENOVATION OF FOOD SCIENCE AND MANAGEMENT LABORATORY | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-024 | RENOVATION OF FOOD SCIENCE AND MANAGEMENT LABORATORY | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-024 | RENOVATION OF FOOD SCIENCE AND MANAGEMENT LABORATORY | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-024 | RENOVATION OF FOOD SCIENCE AND MANAGEMENT LABORATORY | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-024 | RENOVATION OF FOOD SCIENCE AND MANAGEMENT LABORATORY | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-024 | RENOVATION OF FOOD SCIENCE AND MANAGEMENT LABORATORY | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC001-024 | RENOVATION OF FOOD SCIENCE AND MANAGEMENT LABORATORY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC002-024 | Music Building / Aaron Copland School of Music Building Reno | 1 | DEVELOP SCOPE | Jun 2025 | Sep 2026 | Jun 2025 | Sep 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC002-024 | Music Building / Aaron Copland School of Music Building Reno | 2 | PRELIMINARY DESIGN | Sep 2026 | Jan 2027 | Sep 2026 | Jan 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC002-024 | Music Building / Aaron Copland School of Music Building Reno | 3 | FINAL DESIGN | Jan 2027 | Jul 2027 | Jan 2027 | Jul 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC002-024 | Music Building / Aaron Copland School of Music Building Reno | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2027 | Oct 2027 | Jul 2027 | Oct 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC002-024 | Music Building / Aaron Copland School of Music Building Reno | 5 | CONSTRUCTION TO 25% | Oct 2027 | Feb 2028 | Oct 2027 | Feb 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC002-024 | Music Building / Aaron Copland School of Music Building Reno | 6 | CONSTRUCTION TO 50% | Feb 2028 | Jun 2028 | Feb 2028 | Jun 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC002-024 | Music Building / Aaron Copland School of Music Building Reno | 7 | CONSTRUCTION TO 75% | Jun 2028 | Oct 2028 | Jun 2028 | Oct 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC002-024 | Music Building / Aaron Copland School of Music Building Reno | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2028 | Jan 2029 | Oct 2028 | Jan 2029
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC002-024 | Music Building / Aaron Copland School of Music Building Reno | 9 | SUBSTANTIAL COMPLETION | Jan 2029 | Mar 2029 | Jan 2029 | Mar 2029
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC002-024 | Music Building / Aaron Copland School of Music Building Reno | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2029 | Apr 2029 | Mar 2029 | Apr 2029
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC003-024 | Tech Incubator | 1 | DEVELOP SCOPE | Jun 2025 | Sep 2026 | Jun 2025 | Sep 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC003-024 | Tech Incubator | 2 | PRELIMINARY DESIGN | Sep 2026 | Jan 2027 | Sep 2026 | Jan 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC003-024 | Tech Incubator | 3 | FINAL DESIGN | Jan 2027 | Jul 2027 | Jan 2027 | Jul 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC003-024 | Tech Incubator | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2027 | Oct 2027 | Jul 2027 | Oct 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC003-024 | Tech Incubator | 5 | CONSTRUCTION TO 25% | Oct 2027 | Feb 2028 | Oct 2027 | Feb 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC003-024 | Tech Incubator | 6 | CONSTRUCTION TO 50% | Feb 2028 | Jun 2028 | Feb 2028 | Jun 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC003-024 | Tech Incubator | 7 | CONSTRUCTION TO 75% | Jun 2028 | Oct 2028 | Jun 2028 | Oct 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC003-024 | Tech Incubator | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2028 | Jan 2029 | Oct 2028 | Jan 2029
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC003-024 | Tech Incubator | 9 | SUBSTANTIAL COMPLETION | Jan 2029 | Mar 2029 | Jan 2029 | Mar 2029
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC003-024 | Tech Incubator | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2029 | Apr 2029 | Mar 2029 | Apr 2029
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC004-013 | Library and Classroom Space Upgrades | 2 | PRELIMINARY DESIGN | Aug 2013 | Dec 2013 | Sep 2021 | Jan 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC004-013 | Library and Classroom Space Upgrades | 3 | FINAL DESIGN | Dec 2013 | Jun 2014 | Jan 2022 | Jul 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC004-013 | Library and Classroom Space Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2014 | Sep 2014 | Jul 2022 | Oct 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC004-013 | Library and Classroom Space Upgrades | 5 | CONSTRUCTION TO 25% | Sep 2014 | Jan 2015 | Oct 2022 | Feb 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC004-013 | Library and Classroom Space Upgrades | 6 | CONSTRUCTION TO 50% | Jan 2015 | May 2015 | Feb 2023 | Jun 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC004-013 | Library and Classroom Space Upgrades | 7 | CONSTRUCTION TO 75% | May 2015 | Sep 2015 | Jun 2023 | Oct 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC004-013 | Library and Classroom Space Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2015 | Dec 2015 | Oct 2023 | Jan 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC004-013 | Library and Classroom Space Upgrades | 9 | SUBSTANTIAL COMPLETION | Dec 2015 | Feb 2016 | Jan 2024 | Mar 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC004-013 | Library and Classroom Space Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2016 | Mar 2016 | Mar 2024 | Apr 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC004-024 | Technology Infrstructure Improvements | 1 | DEVELOP SCOPE | Jun 2025 | Sep 2026 | Jun 2025 | Sep 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC004-024 | Technology Infrstructure Improvements | 2 | PRELIMINARY DESIGN | Sep 2026 | Jan 2027 | Sep 2026 | Jan 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC004-024 | Technology Infrstructure Improvements | 3 | FINAL DESIGN | Jan 2027 | Jul 2027 | Jan 2027 | Jul 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC004-024 | Technology Infrstructure Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2027 | Oct 2027 | Jul 2027 | Oct 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC004-024 | Technology Infrstructure Improvements | 5 | CONSTRUCTION TO 25% | Oct 2027 | Feb 2028 | Oct 2027 | Feb 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC004-024 | Technology Infrstructure Improvements | 6 | CONSTRUCTION TO 50% | Feb 2028 | Jun 2028 | Feb 2028 | Jun 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC004-024 | Technology Infrstructure Improvements | 7 | CONSTRUCTION TO 75% | Jun 2028 | Oct 2028 | Jun 2028 | Oct 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC004-024 | Technology Infrstructure Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2028 | Jan 2029 | Oct 2028 | Jan 2029
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC004-024 | Technology Infrstructure Improvements | 9 | SUBSTANTIAL COMPLETION | Jan 2029 | Mar 2029 | Jan 2029 | Mar 2029
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC004-024 | Technology Infrstructure Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2029 | Apr 2029 | Mar 2029 | Apr 2029
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC006-022 | Colden Auditorium | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC006-022 | Colden Auditorium | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC006-022 | Colden Auditorium | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC006-022 | Colden Auditorium | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC006-022 | Colden Auditorium | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC006-022 | Colden Auditorium | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC006-022 | Colden Auditorium | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC006-022 | Colden Auditorium | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC006-022 | Colden Auditorium | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC006-022 | Colden Auditorium | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC039-011 | Louis Armstrong Visitor's Center | 1 | DEVELOP SCOPE | Jun 2011 | Aug 2011 | Jun 2011 | Aug 2011
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC039-011 | Louis Armstrong Visitor's Center | 2 | PRELIMINARY DESIGN | Aug 2011 | Dec 2011 | Aug 2011 | Dec 2011
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC039-011 | Louis Armstrong Visitor's Center | 3 | FINAL DESIGN | Dec 2011 | Jun 2012 | Dec 2011 | Jun 2012
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC039-011 | Louis Armstrong Visitor's Center | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2012 | Sep 2012 | Jun 2012 | Sep 2012
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC039-011 | Louis Armstrong Visitor's Center | 5 | CONSTRUCTION TO 25% | Sep 2012 | Jan 2013 | Sep 2012 | Jan 2013
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC039-011 | Louis Armstrong Visitor's Center | 6 | CONSTRUCTION TO 50% | Jan 2013 | May 2013 | Jan 2013 | May 2013
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC039-011 | Louis Armstrong Visitor's Center | 7 | CONSTRUCTION TO 75% | May 2013 | Sep 2013 | May 2013 | Sep 2013
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC039-011 | Louis Armstrong Visitor's Center | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC039-011 | Louis Armstrong Visitor's Center | 9 | SUBSTANTIAL COMPLETION | Dec 2013 | Feb 2014 | Dec 2013 | Feb 2014
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC039-011 | Louis Armstrong Visitor's Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2014 | Mar 2014 | Feb 2014 | Dec 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC047-013 | Kupferberg Renovation | 1 | DEVELOP SCOPE | Jun 2013 | Aug 2013 | Jul 2022 | Sep 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC047-013 | Kupferberg Renovation | 2 | PRELIMINARY DESIGN | Aug 2013 | Dec 2013 | Sep 2022 | Jan 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC047-013 | Kupferberg Renovation | 3 | FINAL DESIGN | Dec 2013 | Jun 2014 | Jan 2023 | Jul 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC047-013 | Kupferberg Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2014 | Sep 2014 | Jul 2023 | Oct 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC047-013 | Kupferberg Renovation | 5 | CONSTRUCTION TO 25% | Sep 2014 | Jan 2015 | Oct 2023 | Feb 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC047-013 | Kupferberg Renovation | 6 | CONSTRUCTION TO 50% | Jan 2015 | May 2015 | Feb 2024 | Jun 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC047-013 | Kupferberg Renovation | 7 | CONSTRUCTION TO 75% | May 2015 | Sep 2015 | Jun 2024 | Oct 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC047-013 | Kupferberg Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2015 | Dec 2015 | Oct 2024 | Jan 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC047-013 | Kupferberg Renovation | 9 | SUBSTANTIAL COMPLETION | Dec 2015 | Feb 2016 | Jan 2025 | Mar 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC047-013 | Kupferberg Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2016 | Mar 2016 | Mar 2025 | Apr 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC054-015 | Speech & Hearing Center Upgrade Ph 2 | 1 | DEVELOP SCOPE | Mar 2015 | May 2015 | Mar 2015 | May 2015
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC054-015 | Speech & Hearing Center Upgrade Ph 2 | 2 | PRELIMINARY DESIGN | May 2015 | Sep 2015 | May 2015 | Sep 2015
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC054-015 | Speech & Hearing Center Upgrade Ph 2 | 3 | FINAL DESIGN | Sep 2015 | Mar 2016 | Sep 2015 | Mar 2016
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC054-015 | Speech & Hearing Center Upgrade Ph 2 | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2016 | Jun 2016 | Mar 2016 | Jun 2016
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC054-015 | Speech & Hearing Center Upgrade Ph 2 | 5 | CONSTRUCTION TO 25% | Jun 2016 | Oct 2016 | Jun 2016 | Oct 2016
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC054-015 | Speech & Hearing Center Upgrade Ph 2 | 6 | CONSTRUCTION TO 50% | Oct 2016 | Feb 2017 | Oct 2016 | Feb 2017
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC054-015 | Speech & Hearing Center Upgrade Ph 2 | 7 | CONSTRUCTION TO 75% | Feb 2017 | Jun 2017 | Feb 2017 | Jun 2017
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC054-015 | Speech & Hearing Center Upgrade Ph 2 | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2017 | Sep 2017 | Jun 2017 | Sep 2017
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC054-015 | Speech & Hearing Center Upgrade Ph 2 | 9 | SUBSTANTIAL COMPLETION | Sep 2017 | Nov 2017 | Sep 2017 | Nov 2017
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC054-015 | Speech & Hearing Center Upgrade Ph 2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | Dec 2017 | Nov 2017 | Dec 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC061-016 | One Stop Service Center | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Jul 2021 | Sep 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC061-016 | One Stop Service Center | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Sep 2021 | Jan 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC061-016 | One Stop Service Center | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Jan 2022 | Jul 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC061-016 | One Stop Service Center | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Jul 2022 | Oct 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC061-016 | One Stop Service Center | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Oct 2022 | Feb 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC061-016 | One Stop Service Center | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Feb 2023 | Jun 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC061-016 | One Stop Service Center | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Jun 2023 | Oct 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC061-016 | One Stop Service Center | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | Oct 2023 | Jan 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC061-016 | One Stop Service Center | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Jan 2024 | Mar 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC061-016 | One Stop Service Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Mar 2024 | Apr 2029
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC061-017 | One Stop Center | 1 | DEVELOP SCOPE | Jun 2017 | Aug 2017 | Jul 2021 | Sep 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC061-017 | One Stop Center | 2 | PRELIMINARY DESIGN | Aug 2017 | Dec 2017 | Sep 2021 | Jan 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC061-017 | One Stop Center | 3 | FINAL DESIGN | Dec 2017 | Jun 2018 | Jan 2022 | Jul 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC061-017 | One Stop Center | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Sep 2018 | Jul 2022 | Oct 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC061-017 | One Stop Center | 5 | CONSTRUCTION TO 25% | Sep 2018 | Jan 2019 | Oct 2022 | Feb 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC061-017 | One Stop Center | 6 | CONSTRUCTION TO 50% | Jan 2019 | May 2019 | Feb 2023 | Jun 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC061-017 | One Stop Center | 7 | CONSTRUCTION TO 75% | May 2019 | Sep 2019 | Jun 2023 | Oct 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC061-017 | One Stop Center | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Dec 2019 | Oct 2023 | Jan 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC061-017 | One Stop Center | 9 | SUBSTANTIAL COMPLETION | Dec 2019 | Feb 2020 | Jan 2024 | Mar 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC061-017 | One Stop Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2020 | Mar 2020 | Mar 2024 | Apr 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC065-017 | Recording Studio Renovation in the Music Bldg | 1 | DEVELOP SCOPE | Jun 2017 | Aug 2017 | Jun 2017 | Aug 2017
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC065-017 | Recording Studio Renovation in the Music Bldg | 2 | PRELIMINARY DESIGN | Aug 2017 | Dec 2017 | Aug 2017 | Dec 2017
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC065-017 | Recording Studio Renovation in the Music Bldg | 3 | FINAL DESIGN | Dec 2017 | Jun 2018 | Dec 2017 | Jun 2018
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC065-017 | Recording Studio Renovation in the Music Bldg | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC065-017 | Recording Studio Renovation in the Music Bldg | 5 | CONSTRUCTION TO 25% | Sep 2018 | Jan 2019 | Sep 2018 | Jan 2019
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC065-017 | Recording Studio Renovation in the Music Bldg | 6 | CONSTRUCTION TO 50% | Jan 2019 | May 2019 | Jan 2019 | May 2019
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC065-017 | Recording Studio Renovation in the Music Bldg | 7 | CONSTRUCTION TO 75% | May 2019 | Sep 2019 | May 2019 | Sep 2019
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC065-017 | Recording Studio Renovation in the Music Bldg | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Dec 2019 | Sep 2019 | Dec 2019
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC065-017 | Recording Studio Renovation in the Music Bldg | 9 | SUBSTANTIAL COMPLETION | Dec 2019 | Feb 2020 | Dec 2019 | Feb 2020
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC065-017 | Recording Studio Renovation in the Music Bldg | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2020 | Mar 2020 | Feb 2020 | Mar 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC066-017 | Digital Film Center Construction | 1 | DEVELOP SCOPE | Jun 2017 | Aug 2017 | Jun 2017 | Aug 2017
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC066-017 | Digital Film Center Construction | 2 | PRELIMINARY DESIGN | Aug 2017 | Dec 2017 | Aug 2017 | Dec 2017
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC066-017 | Digital Film Center Construction | 3 | FINAL DESIGN | Dec 2017 | Jun 2018 | Dec 2017 | Jun 2018
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC066-017 | Digital Film Center Construction | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC066-017 | Digital Film Center Construction | 5 | CONSTRUCTION TO 25% | Sep 2018 | Jan 2019 | Sep 2018 | Jan 2019
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC066-017 | Digital Film Center Construction | 6 | CONSTRUCTION TO 50% | Jan 2019 | May 2019 | Jan 2019 | May 2019
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC066-017 | Digital Film Center Construction | 7 | CONSTRUCTION TO 75% | May 2019 | Sep 2019 | May 2019 | Sep 2019
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC066-017 | Digital Film Center Construction | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Dec 2019 | Sep 2019 | Dec 2019
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC066-017 | Digital Film Center Construction | 9 | SUBSTANTIAL COMPLETION | Dec 2019 | Feb 2020 | Dec 2019 | Feb 2020
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC066-017 | Digital Film Center Construction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2020 | Mar 2020 | Feb 2020 | Mar 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC070-018 | Psychology and Digital Photography Labs | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jul 2021 | Sep 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC070-018 | Psychology and Digital Photography Labs | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Sep 2021 | Jan 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC070-018 | Psychology and Digital Photography Labs | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Jan 2022 | Jul 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC070-018 | Psychology and Digital Photography Labs | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jul 2022 | Oct 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC070-018 | Psychology and Digital Photography Labs | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Oct 2022 | Feb 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC070-018 | Psychology and Digital Photography Labs | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Feb 2023 | Jun 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC070-018 | Psychology and Digital Photography Labs | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | Jun 2023 | Oct 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC070-018 | Psychology and Digital Photography Labs | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Oct 2023 | Jan 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC070-018 | Psychology and Digital Photography Labs | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Jan 2024 | Mar 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC070-018 | Psychology and Digital Photography Labs | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Mar 2024 | Apr 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC072-019 | Renovation of Rathaus Hall Arts Center | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jul 2021 | Sep 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC072-019 | Renovation of Rathaus Hall Arts Center | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Sep 2021 | Jan 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC072-019 | Renovation of Rathaus Hall Arts Center | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2022 | Jul 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC072-019 | Renovation of Rathaus Hall Arts Center | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2022 | Oct 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC072-019 | Renovation of Rathaus Hall Arts Center | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2022 | Feb 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC072-019 | Renovation of Rathaus Hall Arts Center | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2023 | Jun 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC072-019 | Renovation of Rathaus Hall Arts Center | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2023 | Oct 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC072-019 | Renovation of Rathaus Hall Arts Center | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2023 | Jan 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC072-019 | Renovation of Rathaus Hall Arts Center | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2024 | Mar 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC072-019 | Renovation of Rathaus Hall Arts Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2024 | Apr 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC074-019 | Biology Core Facility Upgrade | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jul 2021 | Oct 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC074-019 | Biology Core Facility Upgrade | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Oct 2021 | Feb 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC074-019 | Biology Core Facility Upgrade | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Feb 2022 | Aug 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC074-019 | Biology Core Facility Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Aug 2022 | Nov 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC074-019 | Biology Core Facility Upgrade | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Nov 2022 | Mar 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC074-019 | Biology Core Facility Upgrade | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Mar 2023 | Jul 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC074-019 | Biology Core Facility Upgrade | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jul 2023 | Nov 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC074-019 | Biology Core Facility Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Nov 2023 | Feb 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC074-019 | Biology Core Facility Upgrade | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Feb 2024 | Apr 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC074-019 | Biology Core Facility Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2023 | Apr 2024 | May 2029
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC075-020 | Colden Auditorium Renovation and Upgrades | 1 | DEVELOP SCOPE | Jul 2021 | Sep 2021 | Jul 2021 | Sep 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC075-020 | Colden Auditorium Renovation and Upgrades | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC075-020 | Colden Auditorium Renovation and Upgrades | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC075-020 | Colden Auditorium Renovation and Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC075-020 | Colden Auditorium Renovation and Upgrades | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC075-020 | Colden Auditorium Renovation and Upgrades | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC075-020 | Colden Auditorium Renovation and Upgrades | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC075-020 | Colden Auditorium Renovation and Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC075-020 | Colden Auditorium Renovation and Upgrades | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC075-020 | Colden Auditorium Renovation and Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC076-020 | Air Pollution Laboratory-Commoner Center | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC076-020 | Air Pollution Laboratory-Commoner Center | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC076-020 | Air Pollution Laboratory-Commoner Center | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC076-020 | Air Pollution Laboratory-Commoner Center | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC076-020 | Air Pollution Laboratory-Commoner Center | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC076-020 | Air Pollution Laboratory-Commoner Center | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC076-020 | Air Pollution Laboratory-Commoner Center | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC076-020 | Air Pollution Laboratory-Commoner Center | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC076-020 | Air Pollution Laboratory-Commoner Center | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2023 | Mar 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC076-020 | Air Pollution Laboratory-Commoner Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2023 | Apr 2029
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC077-020 | Remsen Hall Science Bldg Upgrades | 1 | DEVELOP SCOPE | Jul 2020 | Sep 2020 | Jul 2020 | Sep 2020
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC077-020 | Remsen Hall Science Bldg Upgrades | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC077-020 | Remsen Hall Science Bldg Upgrades | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC077-020 | Remsen Hall Science Bldg Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC077-020 | Remsen Hall Science Bldg Upgrades | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC077-020 | Remsen Hall Science Bldg Upgrades | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC077-020 | Remsen Hall Science Bldg Upgrades | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC077-020 | Remsen Hall Science Bldg Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC077-020 | Remsen Hall Science Bldg Upgrades | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2023 | Mar 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC077-020 | Remsen Hall Science Bldg Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2023 | Jun 2029
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC078-020 | Construction of a Student Engagement and learning Ctr. | 1 | DEVELOP SCOPE | Jul 2021 | Sep 2021 | Jul 2021 | Sep 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC078-020 | Construction of a Student Engagement and learning Ctr. | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC078-020 | Construction of a Student Engagement and learning Ctr. | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC078-020 | Construction of a Student Engagement and learning Ctr. | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC078-020 | Construction of a Student Engagement and learning Ctr. | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC078-020 | Construction of a Student Engagement and learning Ctr. | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC078-020 | Construction of a Student Engagement and learning Ctr. | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC078-020 | Construction of a Student Engagement and learning Ctr. | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC078-020 | Construction of a Student Engagement and learning Ctr. | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC078-020 | Construction of a Student Engagement and learning Ctr. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2029
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC079-020 | Louis Armstrong House - Theater Lighting and Sound Systems | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC079-020 | Louis Armstrong House - Theater Lighting and Sound Systems | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC079-020 | Louis Armstrong House - Theater Lighting and Sound Systems | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC079-020 | Louis Armstrong House - Theater Lighting and Sound Systems | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC079-020 | Louis Armstrong House - Theater Lighting and Sound Systems | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC079-020 | Louis Armstrong House - Theater Lighting and Sound Systems | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC079-020 | Louis Armstrong House - Theater Lighting and Sound Systems | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC079-020 | Louis Armstrong House - Theater Lighting and Sound Systems | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC079-020 | Louis Armstrong House - Theater Lighting and Sound Systems | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2023 | Mar 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | QC079-020 | Louis Armstrong House - Theater Lighting and Sound Systems | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2023 | Apr 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC001-010 | YORK COLLEGE - DISABLED ACCESS UPGRADE | 1 | DEVELOP SCOPE | Jun 2010 | Aug 2010 | Jul 2020 | Sep 2020
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC001-010 | YORK COLLEGE - DISABLED ACCESS UPGRADE | 2 | PRELIMINARY DESIGN | Aug 2010 | Dec 2010 | Sep 2020 | Jan 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC001-010 | YORK COLLEGE - DISABLED ACCESS UPGRADE | 3 | FINAL DESIGN | Dec 2010 | Jun 2011 | Jan 2021 | Jul 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC001-010 | YORK COLLEGE - DISABLED ACCESS UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2011 | Sep 2011 | Jul 2021 | Oct 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC001-010 | YORK COLLEGE - DISABLED ACCESS UPGRADE | 5 | CONSTRUCTION TO 25% | Sep 2011 | Jan 2012 | Oct 2021 | Feb 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC001-010 | YORK COLLEGE - DISABLED ACCESS UPGRADE | 6 | CONSTRUCTION TO 50% | Jan 2012 | May 2012 | Feb 2022 | Jun 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC001-010 | YORK COLLEGE - DISABLED ACCESS UPGRADE | 7 | CONSTRUCTION TO 75% | May 2012 | Sep 2012 | Jun 2022 | Oct 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC001-010 | YORK COLLEGE - DISABLED ACCESS UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2012 | Dec 2012 | Oct 2022 | Jan 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC001-010 | YORK COLLEGE - DISABLED ACCESS UPGRADE | 9 | SUBSTANTIAL COMPLETION | Dec 2012 | Feb 2013 | Jan 2023 | Mar 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC001-010 | YORK COLLEGE - DISABLED ACCESS UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2013 | Mar 2013 | Mar 2023 | Apr 2029
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC001-021 | Track & Field Renovations | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC001-021 | Track & Field Renovations | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC001-021 | Track & Field Renovations | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC001-021 | Track & Field Renovations | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC001-021 | Track & Field Renovations | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC001-021 | Track & Field Renovations | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC001-021 | Track & Field Renovations | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC001-021 | Track & Field Renovations | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC001-021 | Track & Field Renovations | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC001-021 | Track & Field Renovations | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2029
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC001-022 | Track and Field Renovation | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC001-022 | Track and Field Renovation | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC001-022 | Track and Field Renovation | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC001-022 | Track and Field Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC001-022 | Track and Field Renovation | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC001-022 | Track and Field Renovation | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC001-022 | Track and Field Renovation | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC001-022 | Track and Field Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC001-022 | Track and Field Renovation | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC001-022 | Track and Field Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC002-023 | Tennis Court & Field Office Restroom Renovation | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2025 | Jun 2024 | Sep 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC002-023 | Tennis Court & Field Office Restroom Renovation | 2 | PRELIMINARY DESIGN | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC002-023 | Tennis Court & Field Office Restroom Renovation | 3 | FINAL DESIGN | Jan 2026 | Jul 2026 | Jan 2026 | Jul 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC002-023 | Tennis Court & Field Office Restroom Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2026 | Oct 2026 | Jul 2026 | Oct 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC002-023 | Tennis Court & Field Office Restroom Renovation | 5 | CONSTRUCTION TO 25% | Oct 2026 | Feb 2027 | Oct 2026 | Feb 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC002-023 | Tennis Court & Field Office Restroom Renovation | 6 | CONSTRUCTION TO 50% | Feb 2027 | Jun 2027 | Feb 2027 | Jun 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC002-023 | Tennis Court & Field Office Restroom Renovation | 7 | CONSTRUCTION TO 75% | Jun 2027 | Oct 2027 | Jun 2027 | Oct 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC002-023 | Tennis Court & Field Office Restroom Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jan 2028 | Oct 2027 | Jan 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC002-023 | Tennis Court & Field Office Restroom Renovation | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Mar 2028 | Jan 2028 | Mar 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC002-023 | Tennis Court & Field Office Restroom Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2028 | Apr 2028 | Mar 2028 | Apr 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC002-024 | Science Building Lecture Hall Renovations | 1 | DEVELOP SCOPE | Jun 2025 | Sep 2026 | Jun 2025 | Sep 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC002-024 | Science Building Lecture Hall Renovations | 2 | PRELIMINARY DESIGN | Sep 2026 | Jan 2027 | Sep 2026 | Jan 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC002-024 | Science Building Lecture Hall Renovations | 3 | FINAL DESIGN | Jan 2027 | Jul 2027 | Jan 2027 | Jul 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC002-024 | Science Building Lecture Hall Renovations | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2027 | Oct 2027 | Jul 2027 | Oct 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC002-024 | Science Building Lecture Hall Renovations | 5 | CONSTRUCTION TO 25% | Oct 2027 | Feb 2028 | Oct 2027 | Feb 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC002-024 | Science Building Lecture Hall Renovations | 6 | CONSTRUCTION TO 50% | Feb 2028 | Jun 2028 | Feb 2028 | Jun 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC002-024 | Science Building Lecture Hall Renovations | 7 | CONSTRUCTION TO 75% | Jun 2028 | Oct 2028 | Jun 2028 | Oct 2028
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC002-024 | Science Building Lecture Hall Renovations | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2028 | Jan 2029 | Oct 2028 | Jan 2029
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC002-024 | Science Building Lecture Hall Renovations | 9 | SUBSTANTIAL COMPLETION | Jan 2029 | Mar 2029 | Jan 2029 | Mar 2029
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC002-024 | Science Building Lecture Hall Renovations | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2029 | Apr 2029 | Mar 2029 | Apr 2029
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC008-022 | Track & Field Facility Upgrades | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC008-022 | Track & Field Facility Upgrades | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC008-022 | Track & Field Facility Upgrades | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC008-022 | Track & Field Facility Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC008-022 | Track & Field Facility Upgrades | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC008-022 | Track & Field Facility Upgrades | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC008-022 | Track & Field Facility Upgrades | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC008-022 | Track & Field Facility Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC008-022 | Track & Field Facility Upgrades | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC008-022 | Track & Field Facility Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC022-007 | Financial Aid Office Renovation | 1 | DEVELOP SCOPE | May 2007 | Aug 2007 | Jul 2020 | Sep 2020
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC022-007 | Financial Aid Office Renovation | 2 | PRELIMINARY DESIGN | Aug 2007 | Dec 2007 | Sep 2020 | Jan 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC022-007 | Financial Aid Office Renovation | 3 | FINAL DESIGN | Dec 2007 | Jun 2008 | Jan 2021 | Jul 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC022-007 | Financial Aid Office Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2008 | Sep 2008 | Jul 2021 | Oct 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC022-007 | Financial Aid Office Renovation | 5 | CONSTRUCTION TO 25% | Sep 2008 | Jan 2009 | Oct 2021 | Feb 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC022-007 | Financial Aid Office Renovation | 6 | CONSTRUCTION TO 50% | Jan 2009 | May 2009 | Feb 2022 | Jun 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC022-007 | Financial Aid Office Renovation | 7 | CONSTRUCTION TO 75% | May 2009 | Sep 2009 | Jun 2022 | Oct 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC022-007 | Financial Aid Office Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2009 | Dec 2009 | Oct 2022 | Jan 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC022-007 | Financial Aid Office Renovation | 9 | SUBSTANTIAL COMPLETION | Dec 2009 | Feb 2010 | Jan 2023 | Mar 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC022-007 | Financial Aid Office Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2010 | Mar 2010 | Mar 2023 | Apr 2029
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC025-008 | SCIENCE FACILITY UPGRADES | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jun 2018 | Aug 2018
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC025-008 | SCIENCE FACILITY UPGRADES | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Aug 2018 | Dec 2018
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC025-008 | SCIENCE FACILITY UPGRADES | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Dec 2018 | Jun 2019
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC025-008 | SCIENCE FACILITY UPGRADES | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC025-008 | SCIENCE FACILITY UPGRADES | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC025-008 | SCIENCE FACILITY UPGRADES | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Jan 2020 | May 2020
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC025-008 | SCIENCE FACILITY UPGRADES | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | May 2020 | Sep 2020
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC025-008 | SCIENCE FACILITY UPGRADES | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Sep 2020 | Dec 2020
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC025-008 | SCIENCE FACILITY UPGRADES | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Dec 2020 | Feb 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC025-008 | SCIENCE FACILITY UPGRADES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Feb 2021 | Mar 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC027-008 | EXTERIOR BEAUTIFICATION, YORK COLLEGE | 1 | DEVELOP SCOPE | Jun 2009 | Aug 2009 | Jun 2009 | Aug 2009
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC027-008 | EXTERIOR BEAUTIFICATION, YORK COLLEGE | 2 | PRELIMINARY DESIGN | Aug 2009 | Dec 2009 | Aug 2009 | Dec 2009
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC027-008 | EXTERIOR BEAUTIFICATION, YORK COLLEGE | 3 | FINAL DESIGN | Dec 2009 | Jun 2010 | Dec 2009 | Jun 2010
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC027-008 | EXTERIOR BEAUTIFICATION, YORK COLLEGE | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2010 | Sep 2010 | Jun 2010 | Sep 2010
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC027-008 | EXTERIOR BEAUTIFICATION, YORK COLLEGE | 5 | CONSTRUCTION TO 25% | Sep 2010 | Jan 2011 | Sep 2010 | Jan 2011
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC027-008 | EXTERIOR BEAUTIFICATION, YORK COLLEGE | 6 | CONSTRUCTION TO 50% | Jan 2011 | May 2011 | Jan 2011 | May 2011
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC027-008 | EXTERIOR BEAUTIFICATION, YORK COLLEGE | 7 | CONSTRUCTION TO 75% | May 2011 | Sep 2011 | May 2011 | Sep 2011
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC027-008 | EXTERIOR BEAUTIFICATION, YORK COLLEGE | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2011 | Dec 2011 | Sep 2011 | Dec 2011
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC027-008 | EXTERIOR BEAUTIFICATION, YORK COLLEGE | 9 | SUBSTANTIAL COMPLETION | Dec 2011 | Feb 2012 | Dec 2011 | Feb 2012
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC027-008 | EXTERIOR BEAUTIFICATION, YORK COLLEGE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2012 | Mar 2012 | Feb 2012 | Mar 2027
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC028-008 | IMPROVEMENTS TO THE PERFORMING ARTS CENTER | 1 | DEVELOP SCOPE | Jun 2009 | Aug 2009 | Jun 2009 | Aug 2009
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC028-008 | IMPROVEMENTS TO THE PERFORMING ARTS CENTER | 2 | PRELIMINARY DESIGN | Aug 2009 | Dec 2009 | Aug 2009 | Dec 2009
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC028-008 | IMPROVEMENTS TO THE PERFORMING ARTS CENTER | 3 | FINAL DESIGN | Dec 2009 | Jun 2010 | Dec 2009 | Jun 2010
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC028-008 | IMPROVEMENTS TO THE PERFORMING ARTS CENTER | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2010 | Sep 2010 | Jun 2010 | Sep 2010
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC028-008 | IMPROVEMENTS TO THE PERFORMING ARTS CENTER | 5 | CONSTRUCTION TO 25% | Sep 2010 | Jan 2011 | Sep 2010 | Jan 2011
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC028-008 | IMPROVEMENTS TO THE PERFORMING ARTS CENTER | 6 | CONSTRUCTION TO 50% | Jan 2011 | May 2011 | Jan 2011 | May 2011
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC028-008 | IMPROVEMENTS TO THE PERFORMING ARTS CENTER | 7 | CONSTRUCTION TO 75% | May 2011 | Sep 2011 | May 2011 | Sep 2011
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC028-008 | IMPROVEMENTS TO THE PERFORMING ARTS CENTER | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2011 | Dec 2011 | Sep 2011 | Dec 2011
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC028-008 | IMPROVEMENTS TO THE PERFORMING ARTS CENTER | 9 | SUBSTANTIAL COMPLETION | Dec 2011 | Feb 2012 | Dec 2011 | Feb 2012
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC028-008 | IMPROVEMENTS TO THE PERFORMING ARTS CENTER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2012 | Mar 2012 | Feb 2012 | Mar 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC043-013 | Daycare Facility Improvements | 1 | DEVELOP SCOPE | Jun 2013 | Aug 2013 | Jun 2013 | Aug 2013
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC043-013 | Daycare Facility Improvements | 2 | PRELIMINARY DESIGN | Aug 2013 | Dec 2013 | Aug 2013 | Dec 2013
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC043-013 | Daycare Facility Improvements | 3 | FINAL DESIGN | Dec 2013 | Jun 2014 | Dec 2013 | Jun 2014
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC043-013 | Daycare Facility Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2014 | Sep 2014 | Jun 2014 | Sep 2014
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC043-013 | Daycare Facility Improvements | 5 | CONSTRUCTION TO 25% | Sep 2014 | Jan 2015 | Sep 2014 | Jan 2015
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC043-013 | Daycare Facility Improvements | 6 | CONSTRUCTION TO 50% | Jan 2015 | May 2015 | Jan 2015 | May 2015
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC043-013 | Daycare Facility Improvements | 7 | CONSTRUCTION TO 75% | May 2015 | Sep 2015 | May 2015 | Sep 2015
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC043-013 | Daycare Facility Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC043-013 | Daycare Facility Improvements | 9 | SUBSTANTIAL COMPLETION | Dec 2015 | Feb 2016 | Dec 2015 | Feb 2016
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC043-013 | Daycare Facility Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2016 | Mar 2016 | Feb 2016 | Mar 2029
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC049-014 | Renovate/Build 3D Graphics and Printing Lab | 1 | DEVELOP SCOPE | Jun 2014 | Aug 2014 | Jun 2014 | Aug 2014
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC049-014 | Renovate/Build 3D Graphics and Printing Lab | 2 | PRELIMINARY DESIGN | Aug 2014 | Dec 2014 | Aug 2014 | Dec 2014
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC049-014 | Renovate/Build 3D Graphics and Printing Lab | 3 | FINAL DESIGN | Dec 2014 | Jun 2015 | Dec 2014 | Jun 2015
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC049-014 | Renovate/Build 3D Graphics and Printing Lab | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2015 | Sep 2015 | Jun 2015 | Sep 2015
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC049-014 | Renovate/Build 3D Graphics and Printing Lab | 5 | CONSTRUCTION TO 25% | Sep 2015 | Jan 2016 | Sep 2015 | Jan 2016
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC049-014 | Renovate/Build 3D Graphics and Printing Lab | 6 | CONSTRUCTION TO 50% | Jan 2016 | May 2016 | Jan 2016 | May 2016
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC049-014 | Renovate/Build 3D Graphics and Printing Lab | 7 | CONSTRUCTION TO 75% | May 2016 | Sep 2016 | May 2016 | Sep 2016
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC049-014 | Renovate/Build 3D Graphics and Printing Lab | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Dec 2016 | Sep 2016 | Dec 2016
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC049-014 | Renovate/Build 3D Graphics and Printing Lab | 9 | SUBSTANTIAL COMPLETION | Dec 2016 | Feb 2017 | Dec 2016 | Feb 2017
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC049-014 | Renovate/Build 3D Graphics and Printing Lab | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2017 | Mar 2017 | Feb 2017 | Mar 2029
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC051-015 | Performing Arts Center Renovations | 1 | DEVELOP SCOPE | Oct 2014 | Dec 2014 | Jul 2020 | Sep 2020
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC051-015 | Performing Arts Center Renovations | 2 | PRELIMINARY DESIGN | Dec 2014 | Apr 2015 | Sep 2020 | Jan 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC051-015 | Performing Arts Center Renovations | 3 | FINAL DESIGN | Apr 2015 | Oct 2015 | Jan 2021 | Jul 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC051-015 | Performing Arts Center Renovations | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2015 | Jan 2016 | Jul 2021 | Oct 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC051-015 | Performing Arts Center Renovations | 5 | CONSTRUCTION TO 25% | Jan 2016 | May 2016 | Oct 2021 | Feb 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC051-015 | Performing Arts Center Renovations | 6 | CONSTRUCTION TO 50% | May 2016 | Sep 2016 | Feb 2022 | Jun 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC051-015 | Performing Arts Center Renovations | 7 | CONSTRUCTION TO 75% | Sep 2016 | Jan 2017 | Jun 2022 | Oct 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC051-015 | Performing Arts Center Renovations | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2017 | Apr 2017 | Oct 2022 | Jan 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC051-015 | Performing Arts Center Renovations | 9 | SUBSTANTIAL COMPLETION | Apr 2017 | Jun 2017 | Jan 2023 | Mar 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC051-015 | Performing Arts Center Renovations | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2017 | Jul 2017 | Mar 2023 | Apr 2029
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC052-016 | Laboratory and Classroom Upgrades | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Jun 2016 | Sep 2016
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC052-016 | Laboratory and Classroom Upgrades | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Sep 2016 | Jan 2017
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC052-016 | Laboratory and Classroom Upgrades | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Jan 2017 | Jul 2017
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC052-016 | Laboratory and Classroom Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Jul 2017 | Oct 2017
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC052-016 | Laboratory and Classroom Upgrades | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Oct 2017 | Feb 2018
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC052-016 | Laboratory and Classroom Upgrades | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Feb 2018 | Jun 2018
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC052-016 | Laboratory and Classroom Upgrades | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC052-016 | Laboratory and Classroom Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | Oct 2018 | Jan 2019
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC052-016 | Laboratory and Classroom Upgrades | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Jan 2019 | Mar 2019
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC052-016 | Laboratory and Classroom Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Mar 2019 | Apr 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC054-017 | Greenhouse Renovation | 1 | DEVELOP SCOPE | Jun 2017 | Aug 2017 | Jul 2020 | Sep 2020
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC054-017 | Greenhouse Renovation | 2 | PRELIMINARY DESIGN | Aug 2017 | Dec 2017 | Sep 2020 | Jan 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC054-017 | Greenhouse Renovation | 3 | FINAL DESIGN | Dec 2017 | Jun 2018 | Jan 2021 | Jul 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC054-017 | Greenhouse Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Sep 2018 | Jul 2021 | Oct 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC054-017 | Greenhouse Renovation | 5 | CONSTRUCTION TO 25% | Sep 2018 | Jan 2019 | Oct 2021 | Feb 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC054-017 | Greenhouse Renovation | 6 | CONSTRUCTION TO 50% | Jan 2019 | May 2019 | Feb 2022 | Jun 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC054-017 | Greenhouse Renovation | 7 | CONSTRUCTION TO 75% | May 2019 | Sep 2019 | Jun 2022 | Oct 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC054-017 | Greenhouse Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Dec 2019 | Oct 2022 | Jan 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC054-017 | Greenhouse Renovation | 9 | SUBSTANTIAL COMPLETION | Dec 2019 | Feb 2020 | Jan 2023 | Mar 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC054-017 | Greenhouse Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2020 | Mar 2020 | Mar 2023 | Apr 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC055-017 | Digital Convergence Center | 1 | DEVELOP SCOPE | Jun 2017 | Aug 2017 | Jul 2021 | Sep 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC055-017 | Digital Convergence Center | 2 | PRELIMINARY DESIGN | Aug 2017 | Dec 2017 | Sep 2021 | Jan 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC055-017 | Digital Convergence Center | 3 | FINAL DESIGN | Dec 2017 | Jun 2018 | Jan 2022 | Jul 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC055-017 | Digital Convergence Center | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Sep 2018 | Jul 2022 | Oct 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC055-017 | Digital Convergence Center | 5 | CONSTRUCTION TO 25% | Sep 2018 | Jan 2019 | Oct 2022 | Feb 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC055-017 | Digital Convergence Center | 6 | CONSTRUCTION TO 50% | Jan 2019 | May 2019 | Feb 2023 | Jun 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC055-017 | Digital Convergence Center | 7 | CONSTRUCTION TO 75% | May 2019 | Sep 2019 | Jun 2023 | Oct 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC055-017 | Digital Convergence Center | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Dec 2019 | Oct 2023 | Jan 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC055-017 | Digital Convergence Center | 9 | SUBSTANTIAL COMPLETION | Dec 2019 | Feb 2020 | Jan 2024 | Mar 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC055-017 | Digital Convergence Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2020 | Mar 2020 | Mar 2024 | Apr 2029
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC059-019 | Renovation to Track | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC059-019 | Renovation to Track | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Sep 2018 | Jan 2019
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC059-019 | Renovation to Track | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2019 | Jul 2019
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC059-019 | Renovation to Track | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2019 | Oct 2019
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC059-019 | Renovation to Track | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2019 | Feb 2020
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC059-019 | Renovation to Track | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2020 | Jun 2020
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC059-019 | Renovation to Track | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2020 | Oct 2020
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC059-019 | Renovation to Track | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2020 | Jan 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC059-019 | Renovation to Track | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2021 | Mar 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC059-019 | Renovation to Track | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2021 | Apr 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC061-020 | Performing Arts Center Upgrades | 1 | DEVELOP SCOPE | Jul 2019 | Sep 2019 | Jun 2023 | Sep 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC061-020 | Performing Arts Center Upgrades | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2023 | Jan 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC061-020 | Performing Arts Center Upgrades | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2024 | Jul 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC061-020 | Performing Arts Center Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2024 | Oct 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC061-020 | Performing Arts Center Upgrades | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2024 | Feb 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC061-020 | Performing Arts Center Upgrades | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2025 | Jun 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC061-020 | Performing Arts Center Upgrades | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2025 | Oct 2025
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC061-020 | Performing Arts Center Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2025 | Jan 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC061-020 | Performing Arts Center Upgrades | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2026 | Mar 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC061-020 | Performing Arts Center Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2026 | Apr 2026
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC063-020 | Recapture Academic Space | 1 | DEVELOP SCOPE | Jul 2021 | Sep 2021 | Jul 2021 | Sep 2021
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC063-020 | Recapture Academic Space | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC063-020 | Recapture Academic Space | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC063-020 | Recapture Academic Space | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC063-020 | Recapture Academic Space | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC063-020 | Recapture Academic Space | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC063-020 | Recapture Academic Space | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC063-020 | Recapture Academic Space | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC063-020 | Recapture Academic Space | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | QUEENS | 042 | CITY UNIVERSITY | YC063-020 | Recapture Academic Space | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2029
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHH | HWY # 3 SEPTIC TANK | 1 | DEVELOP SCOPE | Jun 2014 | Sep 2014 | Jun 2014 | Sep 2014
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHH | HWY # 3 SEPTIC TANK | 2 | PRELIMINARY DESIGN | Sep 2014 | Jan 2015 | Sep 2014 | Jan 2015
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHH | HWY # 3 SEPTIC TANK | 3 | FINAL DESIGN | Jan 2015 | Jul 2015 | Jan 2015 | Jul 2015
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHH | HWY # 3 SEPTIC TANK | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Oct 2015 | Jul 2015 | Oct 2015
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHH | HWY # 3 SEPTIC TANK | 5 | CONSTRUCTION TO 25% | Oct 2015 | Feb 2016 | Oct 2015 | Feb 2016
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHH | HWY # 3 SEPTIC TANK | 6 | CONSTRUCTION TO 50% | Feb 2016 | Jun 2016 | Feb 2016 | Jun 2016
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHH | HWY # 3 SEPTIC TANK | 7 | CONSTRUCTION TO 75% | Jun 2016 | Oct 2016 | Jun 2016 | Oct 2022
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHH | HWY # 3 SEPTIC TANK | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2016 | Jan 2017 | Oct 2022 | Jan 2023
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHH | HWY # 3 SEPTIC TANK | 9 | SUBSTANTIAL COMPLETION | Jan 2017 | Mar 2017 | Jan 2023 | Mar 2023
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHH | HWY # 3 SEPTIC TANK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Apr 2017 | Mar 2023 | Apr 2028
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHM | 101ST PCT HANDICAP RAMP | 1 | DEVELOP SCOPE | Jun 2014 | Sep 2014 | Jun 2014 | Sep 2014
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHM | 101ST PCT HANDICAP RAMP | 2 | PRELIMINARY DESIGN | Sep 2014 | Jan 2015 | Sep 2014 | Jan 2015
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHM | 101ST PCT HANDICAP RAMP | 3 | FINAL DESIGN | Jan 2015 | Jul 2015 | Jan 2015 | Jul 2015
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHM | 101ST PCT HANDICAP RAMP | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Oct 2015 | Jul 2015 | Oct 2015
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHM | 101ST PCT HANDICAP RAMP | 5 | CONSTRUCTION TO 25% | Oct 2015 | Feb 2016 | Oct 2015 | Feb 2016
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHM | 101ST PCT HANDICAP RAMP | 6 | CONSTRUCTION TO 50% | Feb 2016 | Jun 2016 | Feb 2016 | Jun 2016
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHM | 101ST PCT HANDICAP RAMP | 7 | CONSTRUCTION TO 75% | Jun 2016 | Oct 2016 | Jun 2016 | Oct 2023
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHM | 101ST PCT HANDICAP RAMP | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2016 | Jan 2017 | Oct 2023 | Jan 2024
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHM | 101ST PCT HANDICAP RAMP | 9 | SUBSTANTIAL COMPLETION | Jan 2017 | Mar 2017 | Jan 2024 | Mar 2024
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHM | 101ST PCT HANDICAP RAMP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Apr 2017 | Mar 2024 | Jul 2026
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAII | FACADE AT NYPD'S FORENSIC LABORATORY | 1 | DEVELOP SCOPE | Sep 2016 | Dec 2016 | Jun 2019 | Sep 2019
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAII | FACADE AT NYPD'S FORENSIC LABORATORY | 2 | PRELIMINARY DESIGN | Dec 2016 | Apr 2017 | Sep 2019 | Jan 2020
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAII | FACADE AT NYPD'S FORENSIC LABORATORY | 3 | FINAL DESIGN | Apr 2017 | Aug 2017 | Jan 2020 | May 2020
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAII | FACADE AT NYPD'S FORENSIC LABORATORY | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2017 | Feb 2018 | May 2020 | Oct 2020
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAII | FACADE AT NYPD'S FORENSIC LABORATORY | 5 | CONSTRUCTION TO 25% | Feb 2018 | Jun 2018 | Nov 2020 | Feb 2021
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAII | FACADE AT NYPD'S FORENSIC LABORATORY | 6 | CONSTRUCTION TO 50% | Jun 2018 | Sep 2018 | Mar 2021 | Jun 2021
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAII | FACADE AT NYPD'S FORENSIC LABORATORY | 7 | CONSTRUCTION TO 75% | Sep 2018 | Jan 2019 | Jun 2021 | Apr 2025
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAII | FACADE AT NYPD'S FORENSIC LABORATORY | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2019 | Apr 2019 | Apr 2025 | Jul 2025
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAII | FACADE AT NYPD'S FORENSIC LABORATORY | 9 | SUBSTANTIAL COMPLETION | Apr 2019 | Jun 2019 | Jul 2025 | Sep 2025
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAII | FACADE AT NYPD'S FORENSIC LABORATORY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2019 | Jul 2019 | Sep 2025 | Oct 2025
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKB | REPLACEMENT OF GASOLINE PIPES AT HARBOR GEORGE | 1 | DEVELOP SCOPE | Jun 2019 | Aug 2019 | Jun 2019 | Aug 2019
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKB | REPLACEMENT OF GASOLINE PIPES AT HARBOR GEORGE | 2 | PRELIMINARY DESIGN | Aug 2019 | Dec 2019 | Aug 2019 | Dec 2019
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKB | REPLACEMENT OF GASOLINE PIPES AT HARBOR GEORGE | 3 | FINAL DESIGN | Dec 2019 | Apr 2020 | Dec 2019 | Apr 2020
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKB | REPLACEMENT OF GASOLINE PIPES AT HARBOR GEORGE | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2020 | Oct 2020 | Apr 2020 | Oct 2020
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKB | REPLACEMENT OF GASOLINE PIPES AT HARBOR GEORGE | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKB | REPLACEMENT OF GASOLINE PIPES AT HARBOR GEORGE | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKB | REPLACEMENT OF GASOLINE PIPES AT HARBOR GEORGE | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKB | REPLACEMENT OF GASOLINE PIPES AT HARBOR GEORGE | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKB | REPLACEMENT OF GASOLINE PIPES AT HARBOR GEORGE | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKB | REPLACEMENT OF GASOLINE PIPES AT HARBOR GEORGE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Oct 2024
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79FTTIL | K9 RELOCATION FROM BAT TO FORT TILDEN | 1 | DESIGN | Feb 2021 | Jul 2021 | Feb 2021 | Jul 2021
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79FTTIL | K9 RELOCATION FROM BAT TO FORT TILDEN | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79FTTIL | K9 RELOCATION FROM BAT TO FORT TILDEN | 3 | CONSTRUCTION | Oct 2021 | Oct 2022 | Oct 2021 | Oct 2022
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79FTTIL | K9 RELOCATION FROM BAT TO FORT TILDEN | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2022 | Apr 2023 | Oct 2022 | Sep 2027
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79HWAVE | NYOD harbor George wave screen replacent | 1 | DEVELOP SCOPE | Sep 2022 | Nov 2022 | Sep 2022 | Nov 2022
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79HWAVE | NYOD harbor George wave screen replacent | 2 | PRELIMINARY DESIGN | Nov 2022 | Mar 2023 | Nov 2022 | Mar 2023
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79HWAVE | NYOD harbor George wave screen replacent | 3 | FINAL DESIGN | Mar 2023 | Sep 2023 | Mar 2023 | Sep 2023
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79HWAVE | NYOD harbor George wave screen replacent | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2023 | Dec 2023 | Sep 2023 | Dec 2023
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79HWAVE | NYOD harbor George wave screen replacent | 5 | CONSTRUCTION TO 25% | Dec 2023 | Apr 2024 | Dec 2023 | Apr 2024
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79HWAVE | NYOD harbor George wave screen replacent | 6 | CONSTRUCTION TO 50% | Apr 2024 | Aug 2024 | Apr 2024 | Aug 2024
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79HWAVE | NYOD harbor George wave screen replacent | 7 | CONSTRUCTION TO 75% | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79HWAVE | NYOD harbor George wave screen replacent | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2024 | Mar 2025 | Dec 2024 | Mar 2025
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79HWAVE | NYOD harbor George wave screen replacent | 9 | SUBSTANTIAL COMPLETION | Mar 2025 | May 2025 | Mar 2025 | May 2025
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79HWAVE | NYOD harbor George wave screen replacent | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2025 | Jun 2025 | May 2025 | Jun 2032
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79-MED | MEDICAL DIVISION RELOCATION | 1 | DESIGN | Jul 2020 | Jan 2021 | Jul 2020 | Jan 2021
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79-MED | MEDICAL DIVISION RELOCATION | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2021 | Apr 2021 | Jan 2021 | Apr 2021
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79-MED | MEDICAL DIVISION RELOCATION | 3 | CONSTRUCTION | Apr 2021 | Apr 2022 | Apr 2021 | Apr 2022
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79-MED | MEDICAL DIVISION RELOCATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2022 | Oct 2022 | Apr 2022 | Jun 2035
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79PADRS | POLICE ACADEMY DOORS & SMOKE PURGE SYSTEM | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79PADRS | POLICE ACADEMY DOORS & SMOKE PURGE SYSTEM | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79PADRS | POLICE ACADEMY DOORS & SMOKE PURGE SYSTEM | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79PADRS | POLICE ACADEMY DOORS & SMOKE PURGE SYSTEM | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79PADRS | POLICE ACADEMY DOORS & SMOKE PURGE SYSTEM | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79PADRS | POLICE ACADEMY DOORS & SMOKE PURGE SYSTEM | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79PADRS | POLICE ACADEMY DOORS & SMOKE PURGE SYSTEM | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79PADRS | POLICE ACADEMY DOORS & SMOKE PURGE SYSTEM | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79PADRS | POLICE ACADEMY DOORS & SMOKE PURGE SYSTEM | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO79PADRS | POLICE ACADEMY DOORS & SMOKE PURGE SYSTEM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2024 | Nov 2019 | Dec 2024
20231026 | QUEENS | 056 | POLICE DEPARTMENT | POD106COM | 106TH PCT - UPGRADE COMMUNITY ROOM | 1 | DEVELOP SCOPE | Dec 2014 | Mar 2015 | Oct 2019 | Dec 2019
20231026 | QUEENS | 056 | POLICE DEPARTMENT | POD106COM | 106TH PCT - UPGRADE COMMUNITY ROOM | 2 | PRELIMINARY DESIGN | Mar 2015 | Jul 2015 | Dec 2019 | Apr 2020
20231026 | QUEENS | 056 | POLICE DEPARTMENT | POD106COM | 106TH PCT - UPGRADE COMMUNITY ROOM | 3 | FINAL DESIGN | Jul 2015 | Nov 2015 | Apr 2020 | Aug 2020
20231026 | QUEENS | 056 | POLICE DEPARTMENT | POD106COM | 106TH PCT - UPGRADE COMMUNITY ROOM | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2015 | May 2016 | Aug 2020 | Feb 2021
20231026 | QUEENS | 056 | POLICE DEPARTMENT | POD106COM | 106TH PCT - UPGRADE COMMUNITY ROOM | 5 | CONSTRUCTION TO 25% | May 2016 | Sep 2016 | Feb 2021 | Jun 2024
20231026 | QUEENS | 056 | POLICE DEPARTMENT | POD106COM | 106TH PCT - UPGRADE COMMUNITY ROOM | 6 | CONSTRUCTION TO 50% | Sep 2016 | Jan 2017 | Jun 2024 | Oct 2024
20231026 | QUEENS | 056 | POLICE DEPARTMENT | POD106COM | 106TH PCT - UPGRADE COMMUNITY ROOM | 7 | CONSTRUCTION TO 75% | Jan 2017 | May 2017 | Oct 2024 | Feb 2025
20231026 | QUEENS | 056 | POLICE DEPARTMENT | POD106COM | 106TH PCT - UPGRADE COMMUNITY ROOM | 8 | ORIGINAL EQUIP & FURNISHING | May 2017 | Aug 2017 | Feb 2025 | May 2025
20231026 | QUEENS | 056 | POLICE DEPARTMENT | POD106COM | 106TH PCT - UPGRADE COMMUNITY ROOM | 9 | SUBSTANTIAL COMPLETION | Aug 2017 | Oct 2017 | May 2025 | Jul 2025
20231026 | QUEENS | 056 | POLICE DEPARTMENT | POD106COM | 106TH PCT - UPGRADE COMMUNITY ROOM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2017 | Nov 2017 | Jul 2025 | Aug 2025
20231026 | QUEENS | 056 | POLICE DEPARTMENT | POD106REN | 106 Pct. Batthroom and Facade Renovation | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | QUEENS | 056 | POLICE DEPARTMENT | POD106REN | 106 Pct. Batthroom and Facade Renovation | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | QUEENS | 056 | POLICE DEPARTMENT | POD106REN | 106 Pct. Batthroom and Facade Renovation | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | QUEENS | 056 | POLICE DEPARTMENT | POD106REN | 106 Pct. Batthroom and Facade Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | QUEENS | 056 | POLICE DEPARTMENT | POD106REN | 106 Pct. Batthroom and Facade Renovation | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | QUEENS | 056 | POLICE DEPARTMENT | POD106REN | 106 Pct. Batthroom and Facade Renovation | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | QUEENS | 056 | POLICE DEPARTMENT | POD106REN | 106 Pct. Batthroom and Facade Renovation | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | QUEENS | 056 | POLICE DEPARTMENT | POD106REN | 106 Pct. Batthroom and Facade Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | QUEENS | 056 | POLICE DEPARTMENT | POD106REN | 106 Pct. Batthroom and Facade Renovation | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | QUEENS | 056 | POLICE DEPARTMENT | POD106REN | 106 Pct. Batthroom and Facade Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Dec 2019
20231026 | QUEENS | 056 | POLICE DEPARTMENT | POD115PRK | Parking Lot - 115th Precinct | 1 | DESIGN | Dec 2019 | Jun 2020 | Dec 2019 | Jun 2020
20231026 | QUEENS | 056 | POLICE DEPARTMENT | POD115PRK | Parking Lot - 115th Precinct | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | QUEENS | 056 | POLICE DEPARTMENT | POD115PRK | Parking Lot - 115th Precinct | 3 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | QUEENS | 056 | POLICE DEPARTMENT | POD115PRK | Parking Lot - 115th Precinct | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Mar 2022 | Sep 2021 | Mar 2025
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q106 | 106th Precinct Renovation | 1 | DESIGN | Dec 2017 | Jun 2018 | Dec 2017 | Jun 2018
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q106 | 106th Precinct Renovation | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q106 | 106th Precinct Renovation | 3 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2022
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q106 | 106th Precinct Renovation | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Mar 2020 | Sep 2022 | Mar 2025
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q109 | 109th Precinct Locker Room Upgrade | 1 | DEVELOP SCOPE | Apr 2017 | Jul 2017 | Apr 2017 | Jul 2017
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q109 | 109th Precinct Locker Room Upgrade | 2 | PRELIMINARY DESIGN | Jul 2017 | Nov 2017 | Jul 2017 | Nov 2017
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q109 | 109th Precinct Locker Room Upgrade | 3 | FINAL DESIGN | Nov 2017 | May 2018 | Nov 2017 | May 2018
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q109 | 109th Precinct Locker Room Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | May 2018 | Aug 2018 | May 2018 | Aug 2018
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q109 | 109th Precinct Locker Room Upgrade | 5 | CONSTRUCTION TO 25% | Aug 2018 | Dec 2018 | Aug 2018 | Dec 2018
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q109 | 109th Precinct Locker Room Upgrade | 6 | CONSTRUCTION TO 50% | Dec 2018 | Apr 2019 | Dec 2018 | Apr 2019
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q109 | 109th Precinct Locker Room Upgrade | 7 | CONSTRUCTION TO 75% | Apr 2019 | Aug 2019 | Apr 2019 | Aug 2022
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q109 | 109th Precinct Locker Room Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | Aug 2019 | Nov 2019 | Aug 2022 | Nov 2022
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q109 | 109th Precinct Locker Room Upgrade | 9 | SUBSTANTIAL COMPLETION | Nov 2019 | Jan 2020 | Nov 2022 | Jan 2023
20231026 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q109 | 109th Precinct Locker Room Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2020 | Feb 2020 | Jan 2023 | Sep 2025
20231026 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD08 | TRANSIT DISTRICT 23 ELECTRICAL | 1 | DEVELOP SCOPE | Sep 2016 | Dec 2016 | Jun 2016 | Sep 2016
20231026 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD08 | TRANSIT DISTRICT 23 ELECTRICAL | 2 | PRELIMINARY DESIGN | Dec 2016 | Apr 2017 | Sep 2016 | Jan 2017
20231026 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD08 | TRANSIT DISTRICT 23 ELECTRICAL | 3 | FINAL DESIGN | Apr 2017 | Aug 2017 | Jan 2017 | May 2017
20231026 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD08 | TRANSIT DISTRICT 23 ELECTRICAL | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2017 | Feb 2018 | May 2017 | Nov 2017
20231026 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD08 | TRANSIT DISTRICT 23 ELECTRICAL | 5 | CONSTRUCTION TO 25% | Feb 2018 | Jun 2018 | Nov 2017 | Mar 2018
20231026 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD08 | TRANSIT DISTRICT 23 ELECTRICAL | 6 | CONSTRUCTION TO 50% | Jun 2018 | Sep 2018 | Mar 2018 | Jul 2018
20231026 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD08 | TRANSIT DISTRICT 23 ELECTRICAL | 7 | CONSTRUCTION TO 75% | Sep 2018 | Jan 2019 | Jul 2018 | Nov 2021
20231026 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD08 | TRANSIT DISTRICT 23 ELECTRICAL | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2019 | Apr 2019 | Nov 2021 | Feb 2022
20231026 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD08 | TRANSIT DISTRICT 23 ELECTRICAL | 9 | SUBSTANTIAL COMPLETION | Apr 2019 | Jun 2019 | Feb 2022 | Apr 2022
20231026 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD08 | TRANSIT DISTRICT 23 ELECTRICAL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2019 | Jul 2019 | Apr 2022 | May 2025
20231026 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD10 | HARBOR GEORGE | 1 | DEVELOP SCOPE | Sep 2016 | Dec 2016 | Jun 2016 | Sep 2016
20231026 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD10 | HARBOR GEORGE | 2 | PRELIMINARY DESIGN | Dec 2016 | Apr 2017 | Sep 2016 | Jan 2017
20231026 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD10 | HARBOR GEORGE | 3 | FINAL DESIGN | Apr 2017 | Aug 2017 | Jan 2017 | May 2017
20231026 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD10 | HARBOR GEORGE | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2017 | Feb 2018 | May 2017 | Nov 2017
20231026 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD10 | HARBOR GEORGE | 5 | CONSTRUCTION TO 25% | Feb 2018 | Jun 2018 | Nov 2017 | Mar 2018
20231026 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD10 | HARBOR GEORGE | 6 | CONSTRUCTION TO 50% | Jun 2018 | Sep 2018 | Mar 2018 | Jun 2018
20231026 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD10 | HARBOR GEORGE | 7 | CONSTRUCTION TO 75% | Sep 2018 | Jan 2019 | Jun 2018 | Oct 2021
20231026 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD10 | HARBOR GEORGE | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2019 | Apr 2019 | Oct 2021 | Jan 2022
20231026 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD10 | HARBOR GEORGE | 9 | SUBSTANTIAL COMPLETION | Apr 2019 | Jun 2019 | Jan 2022 | Mar 2022
20231026 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD10 | HARBOR GEORGE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2019 | Jul 2019 | Mar 2022 | Apr 2025
20231026 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN203 | FDNY - Wind Turbine | 1 | DEVELOP SCOPE | Jun 2026 | Jun 2026 | Jun 2024 | Jul 2024
20231026 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN203 | FDNY - Wind Turbine | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2026 | Aug 2026 | Jul 2024 | Sep 2024
20231026 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN203 | FDNY - Wind Turbine | 3 | CONSTRUCTION TO 50% | Aug 2026 | Feb 2027 | Sep 2024 | Mar 2025
20231026 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN203 | FDNY - Wind Turbine | 4 | CONSTRUCTION TO 75% | Feb 2027 | May 2027 | Mar 2025 | Jun 2025
20231026 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN203 | FDNY - Wind Turbine | 5 | SUBSTANTIAL COMPLETION | May 2027 | Jul 2027 | Jun 2025 | Aug 2025
20231026 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN203 | FDNY - Wind Turbine | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2027 | Aug 2027 | Aug 2025 | Sep 2025
20231026 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN211 | FDNY- Lighting upgrade in 9 EMS Stations | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2023 | Jun 2023 | Jun 2023
20231026 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN211 | FDNY- Lighting upgrade in 9 EMS Stations | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN211 | FDNY- Lighting upgrade in 9 EMS Stations | 3 | CONSTRUCTION TO 50% | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN211 | FDNY- Lighting upgrade in 9 EMS Stations | 4 | CONSTRUCTION TO 75% | Feb 2024 | May 2024 | Feb 2024 | May 2024
20231026 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN211 | FDNY- Lighting upgrade in 9 EMS Stations | 5 | SUBSTANTIAL COMPLETION | May 2024 | Jul 2024 | May 2024 | Jul 2024
20231026 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN211 | FDNY- Lighting upgrade in 9 EMS Stations | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN704 | FDNY - DESIGN & INSTALLATION OF 97 KW SOLAR SYSTEMS AT EMS45 | 1 | DEVELOP SCOPE | Nov 2017 | Feb 2018 | Nov 2017 | Feb 2018
20231026 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN704 | FDNY - DESIGN & INSTALLATION OF 97 KW SOLAR SYSTEMS AT EMS45 | 2 | PRELIMINARY DESIGN | Feb 2018 | Jun 2018 | Feb 2018 | Jun 2018
20231026 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN704 | FDNY - DESIGN & INSTALLATION OF 97 KW SOLAR SYSTEMS AT EMS45 | 3 | FINAL DESIGN | Jun 2018 | Dec 2018 | Jun 2018 | Dec 2018
20231026 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN704 | FDNY - DESIGN & INSTALLATION OF 97 KW SOLAR SYSTEMS AT EMS45 | 4 | BID AWARD AND REGISTER CONTRCT | Dec 2018 | Mar 2019 | Dec 2018 | Mar 2019
20231026 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN704 | FDNY - DESIGN & INSTALLATION OF 97 KW SOLAR SYSTEMS AT EMS45 | 5 | CONSTRUCTION TO 25% | Mar 2019 | Jul 2019 | Mar 2019 | Jul 2019
20231026 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN704 | FDNY - DESIGN & INSTALLATION OF 97 KW SOLAR SYSTEMS AT EMS45 | 6 | CONSTRUCTION TO 50% | Jul 2019 | Nov 2019 | Jul 2019 | Nov 2019
20231026 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN704 | FDNY - DESIGN & INSTALLATION OF 97 KW SOLAR SYSTEMS AT EMS45 | 7 | CONSTRUCTION TO 75% | Nov 2019 | Mar 2020 | Nov 2019 | Nov 2021
20231026 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN704 | FDNY - DESIGN & INSTALLATION OF 97 KW SOLAR SYSTEMS AT EMS45 | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2020 | Jun 2020 | Nov 2021 | Feb 2022
20231026 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN704 | FDNY - DESIGN & INSTALLATION OF 97 KW SOLAR SYSTEMS AT EMS45 | 9 | SUBSTANTIAL COMPLETION | Jun 2020 | Aug 2020 | Feb 2022 | Apr 2022
20231026 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN704 | FDNY - DESIGN & INSTALLATION OF 97 KW SOLAR SYSTEMS AT EMS45 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2020 | Sep 2020 | Apr 2022 | May 2024
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175FMHVC | FLEET MAINTENANCE HVAC SYSTEM UPGRADE | 1 | CONSTRUCTION | Jun 2017 | Jun 2018 | Jun 2017 | Jun 2018
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175FMHVC | FLEET MAINTENANCE HVAC SYSTEM UPGRADE | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2018 | Sep 2018 | Jun 2018 | Jun 2025
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175MC266 | Multi-Component Renovations - EC266 | 1 | DESIGN | Jan 2019 | Apr 2019 | Jan 2019 | Apr 2019
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175MC266 | Multi-Component Renovations - EC266 | 2 | BID AWARD AND REGISTER CONTRCT | Apr 2019 | Jan 2020 | Apr 2019 | Jan 2020
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175MC266 | Multi-Component Renovations - EC266 | 3 | CONSTRUCTION | Jan 2020 | Feb 2021 | Jan 2020 | Feb 2021
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175MC266 | Multi-Component Renovations - EC266 | 4 | ORIGINAL EQUIP & FURNISHING | Feb 2021 | Mar 2021 | Feb 2021 | Mar 2021
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175MC266 | Multi-Component Renovations - EC266 | 5 | SUBSTANTIAL COMPLETION | Mar 2021 | May 2021 | Mar 2021 | May 2021
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175MC266 | Multi-Component Renovations - EC266 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2021 | Jul 2021 | May 2021 | Oct 2025
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175MC304 | Multi-Component Renovations - EC304 | 1 | DESIGN | Oct 2018 | Jan 2019 | Oct 2018 | Jan 2019
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175MC304 | Multi-Component Renovations - EC304 | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2019 | Oct 2019 | Jan 2019 | Oct 2019
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175MC304 | Multi-Component Renovations - EC304 | 3 | CONSTRUCTION | Oct 2019 | Nov 2020 | Oct 2019 | Nov 2020
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175MC304 | Multi-Component Renovations - EC304 | 4 | ORIGINAL EQUIP & FURNISHING | Nov 2020 | Dec 2020 | Nov 2020 | Dec 2020
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175MC304 | Multi-Component Renovations - EC304 | 5 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Dec 2020 | Feb 2021
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175MC304 | Multi-Component Renovations - EC304 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Apr 2021 | Feb 2021 | Oct 2023
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175MC307 | Multi-Component Renovations - EC307 | 1 | DESIGN | Oct 2018 | Jan 2019 | Sep 2021 | Dec 2021
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175MC307 | Multi-Component Renovations - EC307 | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2019 | Oct 2019 | Dec 2021 | Sep 2022
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175MC307 | Multi-Component Renovations - EC307 | 3 | CONSTRUCTION | Oct 2019 | Nov 2020 | Sep 2022 | Oct 2023
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175MC307 | Multi-Component Renovations - EC307 | 4 | ORIGINAL EQUIP & FURNISHING | Nov 2020 | Dec 2020 | Oct 2023 | Nov 2023
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175MC307 | Multi-Component Renovations - EC307 | 5 | SUBSTANTIAL COMPLETION | Jan 2021 | Feb 2021 | Jan 2021 | Feb 2021
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175MC307 | Multi-Component Renovations - EC307 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Apr 2021 | Feb 2021 | Apr 2021
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175WN266 | WINDOW REPLACEMENT - EC266 | 1 | DESIGN | Jan 2019 | Jul 2019 | Jan 2019 | Jul 2019
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175WN266 | WINDOW REPLACEMENT - EC266 | 2 | CONSTRUCTION | Jul 2019 | Jul 2020 | Jul 2019 | Jul 2020
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175WN266 | WINDOW REPLACEMENT - EC266 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Oct 2020 | Jul 2020 | Mar 2025
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175WN329 | WINDOW REPLACEMENT - EC329 | 1 | CONSTRUCTION | Oct 2019 | Oct 2020 | Oct 2019 | Sep 2020
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175WN329 | WINDOW REPLACEMENT - EC329 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2020 | Dec 2020 | Oct 2020 | Jun 2024
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175WP301 | Waterproofing - EC301 | 1 | DESIGN | Oct 2018 | Apr 2019 | Oct 2018 | Apr 2019
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175WP301 | Waterproofing - EC301 | 2 | CONSTRUCTION | Apr 2019 | Apr 2020 | Apr 2019 | Apr 2020
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175WP301 | Waterproofing - EC301 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2020 | Jul 2020 | Apr 2020 | Jun 2024
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175WP303 | Waterproofing - EC303 | 1 | DESIGN | Oct 2018 | Apr 2019 | Oct 2018 | Apr 2019
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175WP303 | Waterproofing - EC303 | 2 | CONSTRUCTION | Apr 2019 | Apr 2020 | Apr 2019 | Apr 2020
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175WP303 | Waterproofing - EC303 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2020 | Jul 2020 | Apr 2020 | Jun 2024
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175WP325 | Roofing and Waterproofing - EC325 | 1 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2020 | Sep 2021
20231026 | QUEENS | 057 | FIRE DEPARTMENT | F175WP325 | Roofing and Waterproofing - EC325 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Dec 2020 | Sep 2021 | Jun 2024
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175D262 | Door Replacement - EC262 | 1 | DESIGN | Sep 2018 | Mar 2019 | Apr 2020 | Sep 2020
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175D262 | Door Replacement - EC262 | 2 | CONSTRUCTION | Mar 2019 | Mar 2020 | Sep 2020 | Sep 2021
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175D262 | Door Replacement - EC262 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Jun 2020 | Sep 2021 | Dec 2029
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175D288 | OVERHEAD DOOR - SQUAD 288 | 1 | CONSTRUCTION | Nov 2023 | Nov 2024 | Nov 2023 | Nov 2024
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175D288 | OVERHEAD DOOR - SQUAD 288 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2024 | Feb 2025 | Nov 2024 | Feb 2025
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175D291 | Door Replacement - EC291 | 2 | CONSTRUCTION | Mar 2019 | Mar 2020 | Sep 2020 | Sep 2021
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175D291 | Door Replacement - EC291 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Jun 2020 | Sep 2021 | Dec 2021
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175D301 | OVERHEAD DOOR - EC 301 / LADDER 150 | 1 | CONSTRUCTION | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175D301 | OVERHEAD DOOR - EC 301 / LADDER 150 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175D311 | OVERHEAD DOOR - EC 311 | 1 | CONSTRUCTION | Nov 2023 | Nov 2024 | Nov 2023 | Nov 2024
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175D311 | OVERHEAD DOOR - EC 311 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2024 | Feb 2025 | Nov 2024 | Feb 2025
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175D314 | OVERHEAD DOOR - EC 314 | 1 | CONSTRUCTION | Nov 2023 | Nov 2024 | Nov 2023 | Nov 2024
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175D314 | OVERHEAD DOOR - EC 314 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2024 | Feb 2025 | Nov 2024 | Feb 2025
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175D324 | Door Replacement - EC324 | 1 | DESIGN | Sep 2018 | Mar 2019 | Apr 2020 | Sep 2020
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175D324 | Door Replacement - EC324 | 2 | CONSTRUCTION | Mar 2019 | Mar 2020 | Sep 2020 | Sep 2021
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175D324 | Door Replacement - EC324 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Jun 2020 | Sep 2021 | Dec 2029
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175D325 | OVERHEAD DOOR - EC 325/LADDER 163 | 1 | CONSTRUCTION | Nov 2023 | Nov 2024 | Nov 2023 | Nov 2024
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175D325 | OVERHEAD DOOR - EC 325/LADDER 163 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2024 | Feb 2025 | Nov 2024 | Feb 2025
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175D326 | OVERHEAD DOOR - EC 326 / LADDER 160 | 1 | CONSTRUCTION | Nov 2023 | Nov 2024 | Nov 2023 | Nov 2024
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175D326 | OVERHEAD DOOR - EC 326 / LADDER 160 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2024 | Feb 2025 | Nov 2024 | Feb 2025
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175DS47 | SPEED DOOR - EMS STATION 47 | 1 | CONSTRUCTION | Mar 2024 | Mar 2025 | Mar 2024 | Mar 2025
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175DS47 | SPEED DOOR - EMS STATION 47 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Jun 2025 | Mar 2025 | Jun 2025
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175G289 | Generator - EC289 | 1 | DESIGN | Jan 2019 | Jul 2019 | Jan 2020 | Jul 2020
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175G289 | Generator - EC289 | 2 | CONSTRUCTION | Jul 2019 | Jul 2020 | Jul 2020 | Jul 2021
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175G289 | Generator - EC289 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Oct 2020 | Jul 2021 | Aug 2023
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175G320 | GENERATOR - EC 320 / LADDER 167 | 1 | DESIGN | Feb 2024 | Aug 2024 | Feb 2024 | Aug 2024
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175G320 | GENERATOR - EC 320 / LADDER 167 | 2 | CONSTRUCTION | Aug 2024 | Aug 2025 | Aug 2024 | Aug 2025
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175G320 | GENERATOR - EC 320 / LADDER 167 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2025 | Nov 2025 | Aug 2025 | Nov 2025
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175W288 | WINDOWS REPLACEMENT - SQUAD 288 | 1 | DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175W288 | WINDOWS REPLACEMENT - SQUAD 288 | 2 | CONSTRUCTION | Jun 2024 | Jun 2025 | Jun 2024 | Jun 2025
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175W288 | WINDOWS REPLACEMENT - SQUAD 288 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175W316 | Window Replacement - EC316 | 1 | CONSTRUCTION | Jun 2020 | Jun 2021 | Jun 2020 | Jun 2021
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FD175W316 | Window Replacement - EC316 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2021 | Sep 2021 | Jun 2021 | May 2024
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FQ175G260 | Generator - EC260 | 1 | DESIGN | Oct 2019 | Apr 2020 | Oct 2019 | Apr 2020
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FQ175G260 | Generator - EC260 | 2 | CONSTRUCTION | Apr 2020 | Apr 2021 | Apr 2020 | Apr 2021
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FQ175G260 | Generator - EC260 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2021 | Jul 2021 | Apr 2021 | Jun 2024
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FQ175K307 | KITCHEN RENOVATION - EC307 | 1 | DESIGN | Jun 2018 | Nov 2018 | Jan 2021 | Jul 2021
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FQ175K307 | KITCHEN RENOVATION - EC307 | 2 | CONSTRUCTION | Nov 2018 | Nov 2019 | Jul 2021 | Jul 2022
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FQ175K307 | KITCHEN RENOVATION - EC307 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Feb 2020 | Jul 2022 | Sep 2025
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FQ175WASH | REPLACEMENT OF WASHERS AND DRYERS | 1 | DESIGN | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FQ175WASH | REPLACEMENT OF WASHERS AND DRYERS | 2 | CONSTRUCTION | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 057 | FIRE DEPARTMENT | FQ175WASH | REPLACEMENT OF WASHERS AND DRYERS | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2021 | Mar 2022 | Dec 2021 | Jun 2024
20231026 | QUEENS | 057 | FIRE DEPARTMENT | ID21WD299 | Ida Storm Water Damage Restoration - EC299 | 1 | CONSTRUCTION | Dec 2023 | Dec 2024 | Dec 2023 | Dec 2024
20231026 | QUEENS | 057 | FIRE DEPARTMENT | ID21WD299 | Ida Storm Water Damage Restoration - EC299 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2024 | Mar 2025 | Dec 2024 | Mar 2025
20231026 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | ACEDHS801 | DHS - Gas fired condensing hot water systems | 1 | DESIGN | May 2021 | Feb 2022 | May 2021 | Feb 2022
20231026 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | ACEDHS801 | DHS - Gas fired condensing hot water systems | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2022 | Aug 2022 | Feb 2022 | Aug 2022
20231026 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | ACEDHS801 | DHS - Gas fired condensing hot water systems | 3 | CONSTRUCTION | Aug 2022 | May 2027 | Aug 2022 | May 2027
20231026 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH112BARS | Shelter at 21-10 Borden Avenue, 11110 - Roof/Skylight Replac | 1 | DESIGN | Jan 2019 | Sep 2019 | Jul 2021 | Mar 2022
20231026 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH112BARS | Shelter at 21-10 Borden Avenue, 11110 - Roof/Skylight Replac | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Mar 2020 | Mar 2022 | Sep 2022
20231026 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH112BARS | Shelter at 21-10 Borden Avenue, 11110 - Roof/Skylight Replac | 3 | CONSTRUCTION | Mar 2020 | Dec 2024 | Sep 2022 | Jun 2027
20231026 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH112BOFW | Borden Avenue Flood Mitigation | 1 | DESIGN | Jan 2019 | Sep 2019 | Jan 2019 | Sep 2019
20231026 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH112BOFW | Borden Avenue Flood Mitigation | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Mar 2020 | Sep 2019 | Mar 2020
20231026 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH112BOFW | Borden Avenue Flood Mitigation | 3 | CONSTRUCTION | Mar 2020 | Dec 2024 | Mar 2020 | Dec 2024
20231026 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH112FRRF | Franklin Women's Shelter - Roof Reconstruction | 1 | DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH112FRRF | Franklin Women's Shelter - Roof Reconstruction | 2 | CONSTRUCTION | Jun 2023 | Jun 2024 | Jun 2023 | Jun 2024
20231026 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115BWRF | BRIARWOOD FAMILY RESIDENCE - ROOF AND FACADE UPGRADE | 1 | DESIGN | Jan 2019 | Sep 2019 | Jan 2019 | Sep 2019
20231026 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115BWRF | BRIARWOOD FAMILY RESIDENCE - ROOF AND FACADE UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Mar 2020 | Sep 2019 | Mar 2020
20231026 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115BWRF | BRIARWOOD FAMILY RESIDENCE - ROOF AND FACADE UPGRADE | 3 | CONSTRUCTION | Mar 2020 | Dec 2024 | Mar 2020 | Dec 2024
20231026 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115JAEX | JAMAICA FAMILY EXTERIOR | 1 | DESIGN | Jan 2020 | Sep 2020 | Jan 2020 | Sep 2020
20231026 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115JAEX | JAMAICA FAMILY EXTERIOR | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2020 | Mar 2021 | Sep 2020 | Mar 2021
20231026 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115JAEX | JAMAICA FAMILY EXTERIOR | 3 | CONSTRUCTION | Mar 2021 | Dec 2025 | Mar 2021 | Dec 2025
20231026 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115SINT | SPRINGFIELD BLD FACADE RECONSTRUCTION | 1 | DESIGN | May 2022 | Feb 2023 | May 2022 | Feb 2023
20231026 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115SINT | SPRINGFIELD BLD FACADE RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2023 | Aug 2023 | Feb 2023 | Aug 2023
20231026 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115SINT | SPRINGFIELD BLD FACADE RECONSTRUCTION | 3 | CONSTRUCTION | Aug 2023 | May 2028 | Aug 2023 | May 2028
20231026 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115SMEP | SPRINGFIELD BLD BOILER RECONSTRUCTION | 1 | DESIGN | May 2021 | Feb 2022 | May 2021 | Feb 2022
20231026 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115SMEP | SPRINGFIELD BLD BOILER RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2022 | Aug 2022 | Feb 2022 | Aug 2022
20231026 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115SMEP | SPRINGFIELD BLD BOILER RECONSTRUCTION | 3 | CONSTRUCTION | Aug 2022 | May 2027 | Aug 2022 | May 2027
20231026 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS2 | Solar PV system at Borden Avenue facility | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2020 | Aug 2019 | May 2020
20231026 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS2 | Solar PV system at Borden Avenue facility | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Aug 2020 | May 2020 | Nov 2020
20231026 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS2 | Solar PV system at Borden Avenue facility | 3 | CONSTRUCTION TO 50% | Aug 2020 | Feb 2021 | Nov 2020 | Aug 2025
20231026 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS2 | Solar PV system at Borden Avenue facility | 4 | CONSTRUCTION TO 75% | Feb 2021 | May 2021 | Nov 2020 | Aug 2025
20231026 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS2 | Solar PV system at Borden Avenue facility | 5 | SUBSTANTIAL COMPLETION | May 2021 | Jul 2021 | Nov 2020 | Aug 2025
20231026 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS2 | Solar PV system at Borden Avenue facility | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Aug 2021 | Nov 2020 | Aug 2025
20231026 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C101-SEC | PERIMETER SECURITY & CAMERA REPLACEMENT | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C101-SEC | PERIMETER SECURITY & CAMERA REPLACEMENT | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C101-SEC | PERIMETER SECURITY & CAMERA REPLACEMENT | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2021
20231026 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C101-SEC | PERIMETER SECURITY & CAMERA REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C101-SEC | PERIMETER SECURITY & CAMERA REPLACEMENT | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C101-SEC | PERIMETER SECURITY & CAMERA REPLACEMENT | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C101-SEC | PERIMETER SECURITY & CAMERA REPLACEMENT | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2022
20231026 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C101-SEC | PERIMETER SECURITY & CAMERA REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C101-SEC | PERIMETER SECURITY & CAMERA REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2023 | Mar 2023
20231026 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C101-SEC | PERIMETER SECURITY & CAMERA REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2023 | Dec 2028
20231026 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C75SEWR | RECONSTRUCTION OF RI SEWER LINES | 1 | DEVELOP SCOPE | Jul 2012 | Sep 2012 | Aug 2013 | Nov 2013
20231026 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C75SEWR | RECONSTRUCTION OF RI SEWER LINES | 2 | PRELIMINARY DESIGN | Sep 2012 | Jan 2013 | Nov 2013 | Mar 2014
20231026 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C75SEWR | RECONSTRUCTION OF RI SEWER LINES | 3 | FINAL DESIGN | Jan 2013 | Jul 2013 | Mar 2014 | Sep 2014
20231026 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C75SEWR | RECONSTRUCTION OF RI SEWER LINES | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2013 | Oct 2013 | Sep 2014 | Dec 2014
20231026 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C75SEWR | RECONSTRUCTION OF RI SEWER LINES | 5 | CONSTRUCTION TO 25% | Oct 2013 | Feb 2014 | Dec 2014 | Apr 2015
20231026 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C75SEWR | RECONSTRUCTION OF RI SEWER LINES | 6 | CONSTRUCTION TO 50% | Feb 2014 | Jun 2014 | Apr 2015 | Aug 2015
20231026 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C75SEWR | RECONSTRUCTION OF RI SEWER LINES | 7 | CONSTRUCTION TO 75% | Jun 2014 | Oct 2014 | Aug 2015 | Dec 2015
20231026 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C75SEWR | RECONSTRUCTION OF RI SEWER LINES | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2014 | Jan 2015 | Dec 2015 | Mar 2016
20231026 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C75SEWR | RECONSTRUCTION OF RI SEWER LINES | 9 | SUBSTANTIAL COMPLETION | Jan 2015 | Mar 2015 | Mar 2016 | May 2016
20231026 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C75SEWR | RECONSTRUCTION OF RI SEWER LINES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Apr 2015 | May 2016 | Jun 2026
20231026 | QUEENS | 096 | HUMAN RESOURCES ADMINISTRATION | HRCNSJMS2 | South Jamaica MSC renovation. | 1 | DESIGN | Jun 2014 | Nov 2014 | Jul 2028 | Dec 2028
20231026 | QUEENS | 096 | HUMAN RESOURCES ADMINISTRATION | HRCNSJMS2 | South Jamaica MSC renovation. | 2 | CONSTRUCTION | Nov 2014 | May 2015 | Dec 2028 | Jun 2029
20231026 | QUEENS | 096 | HUMAN RESOURCES ADMINISTRATION | HRCNSJMSC | South Jamaica MSC renovation | 1 | DESIGN | Jun 2014 | Nov 2014 | Jul 2028 | Dec 2028
20231026 | QUEENS | 096 | HUMAN RESOURCES ADMINISTRATION | HRCNSJMSC | South Jamaica MSC renovation | 2 | CONSTRUCTION | Nov 2014 | May 2015 | Dec 2028 | Jun 2029
20231026 | QUEENS | 125 | DEPARTMENT FOR THE AGING | AGWOODRE1 | Woodside houses new gym for the elderly | 1 | DESIGN | Jun 2015 | Nov 2015 | Jun 2027 | Dec 2027
20231026 | QUEENS | 125 | DEPARTMENT FOR THE AGING | AGWOODRE1 | Woodside houses new gym for the elderly | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2015 | Feb 2016 | Dec 2027 | Mar 2028
20231026 | QUEENS | 125 | DEPARTMENT FOR THE AGING | AGWOODRE1 | Woodside houses new gym for the elderly | 3 | CONSTRUCTION | Feb 2016 | Feb 2017 | Mar 2028 | Mar 2029
20231026 | QUEENS | 125 | DEPARTMENT FOR THE AGING | AGWOODRE1 | Woodside houses new gym for the elderly | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2017 | Aug 2017 | Mar 2029 | Sep 2029
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV040BTH1 | FTH - Flushing Town Hall - Bathroom Renovations | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2024 | Sep 2024
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV040BTH1 | FTH - Flushing Town Hall - Bathroom Renovations | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2024 | Jan 2025
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV040BTH1 | FTH - Flushing Town Hall - Bathroom Renovations | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2025 | Jul 2025
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV040BTH1 | FTH - Flushing Town Hall - Bathroom Renovations | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2025 | Oct 2025
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV040BTH1 | FTH - Flushing Town Hall - Bathroom Renovations | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2025 | Feb 2026
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV040BTH1 | FTH - Flushing Town Hall - Bathroom Renovations | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2026 | Jun 2026
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV040BTH1 | FTH - Flushing Town Hall - Bathroom Renovations | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2026 | Oct 2026
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV040BTH1 | FTH - Flushing Town Hall - Bathroom Renovations | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2026 | Jan 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV040BTH1 | FTH - Flushing Town Hall - Bathroom Renovations | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2027 | Mar 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV040BTH1 | FTH - Flushing Town Hall - Bathroom Renovations | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2027 | Apr 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CORE | American Museum of Moving Images - New Core Exhibition | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2028 | Sep 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CORE | American Museum of Moving Images - New Core Exhibition | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2028 | Jan 2029
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CORE | American Museum of Moving Images - New Core Exhibition | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2029 | Jul 2029
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CORE | American Museum of Moving Images - New Core Exhibition | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2029 | Oct 2029
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CORE | American Museum of Moving Images - New Core Exhibition | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2029 | Feb 2030
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CORE | American Museum of Moving Images - New Core Exhibition | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2030 | Jun 2030
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CORE | American Museum of Moving Images - New Core Exhibition | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2030 | Oct 2030
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CORE | American Museum of Moving Images - New Core Exhibition | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2030 | Jan 2031
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CORE | American Museum of Moving Images - New Core Exhibition | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2031 | Mar 2031
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CORE | American Museum of Moving Images - New Core Exhibition | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2031 | Apr 2031
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CYLT | MMI - Courtyard Lighting | 1 | DEVELOP SCOPE | Apr 2018 | Jun 2019 | Jun 2024 | Sep 2025
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CYLT | MMI - Courtyard Lighting | 2 | PRELIMINARY DESIGN | Jul 2019 | Oct 2019 | Sep 2025 | Jan 2026
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CYLT | MMI - Courtyard Lighting | 3 | FINAL DESIGN | Oct 2019 | Apr 2020 | Jan 2026 | Jul 2026
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CYLT | MMI - Courtyard Lighting | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2020 | Jul 2020 | Jul 2026 | Oct 2026
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CYLT | MMI - Courtyard Lighting | 5 | CONSTRUCTION TO 25% | Jul 2020 | Nov 2020 | Oct 2026 | Feb 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CYLT | MMI - Courtyard Lighting | 6 | CONSTRUCTION TO 50% | Nov 2020 | Mar 2021 | Feb 2027 | Jun 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CYLT | MMI - Courtyard Lighting | 7 | CONSTRUCTION TO 75% | Mar 2021 | Jul 2021 | Jun 2027 | Oct 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CYLT | MMI - Courtyard Lighting | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2021 | Oct 2021 | Oct 2027 | Jan 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CYLT | MMI - Courtyard Lighting | 9 | SUBSTANTIAL COMPLETION | Oct 2021 | Dec 2021 | Jan 2028 | Mar 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CYLT | MMI - Courtyard Lighting | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2021 | Jan 2022 | Mar 2028 | Apr 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050ENTR | MMI - Upgrades to Building Entrance | 1 | CONSTRUCTION | Sep 2021 | Sep 2022 | Jun 2025 | Sep 2025
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050ENTR | MMI - Upgrades to Building Entrance | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2025 | Sep 2026
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050ENTR | MMI - Upgrades to Building Entrance | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2026 | Sep 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050MECH | MMI - Mechanical Systems Upgrade | 1 | CONSTRUCTION | Sep 2021 | Sep 2022 | Jun 2024 | Sep 2024
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050MECH | MMI - Mechanical Systems Upgrade | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2024 | Sep 2025
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050MECH | MMI - Mechanical Systems Upgrade | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2025 | Sep 2026
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV272-PAV | QBG PAVILION GARDEN | 1 | DEVELOP SCOPE | Jun 2027 | Sep 2027 | Jun 2027 | Sep 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV272-PAV | QBG PAVILION GARDEN | 2 | PRELIMINARY DESIGN | Sep 2027 | Jan 2028 | Sep 2027 | Jan 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV272-PAV | QBG PAVILION GARDEN | 3 | FINAL DESIGN | Jan 2028 | Jul 2028 | Jan 2028 | Jul 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV272-PAV | QBG PAVILION GARDEN | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2028 | Oct 2028 | Jul 2028 | Oct 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV272-PAV | QBG PAVILION GARDEN | 5 | CONSTRUCTION TO 25% | Oct 2028 | Feb 2029 | Oct 2028 | Feb 2029
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV272-PAV | QBG PAVILION GARDEN | 6 | CONSTRUCTION TO 50% | Feb 2029 | Jun 2029 | Feb 2029 | Jun 2029
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV272-PAV | QBG PAVILION GARDEN | 7 | CONSTRUCTION TO 75% | Jun 2029 | Oct 2029 | Jun 2029 | Oct 2029
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV272-PAV | QBG PAVILION GARDEN | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2029 | Jan 2030 | Oct 2029 | Jan 2030
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV272-PAV | QBG PAVILION GARDEN | 9 | SUBSTANTIAL COMPLETION | Jan 2030 | Mar 2030 | Jan 2030 | Mar 2030
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV272-PAV | QBG PAVILION GARDEN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2030 | Apr 2030 | Mar 2030 | Apr 2030
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV272QUAD | QBG - Welcome Garden & Sustainability Educ. Quad | 1 | DEVELOP SCOPE | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV272QUAD | QBG - Welcome Garden & Sustainability Educ. Quad | 2 | PRELIMINARY DESIGN | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV272QUAD | QBG - Welcome Garden & Sustainability Educ. Quad | 3 | FINAL DESIGN | Jan 2026 | Jul 2026 | Jan 2026 | Jul 2026
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV272QUAD | QBG - Welcome Garden & Sustainability Educ. Quad | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2026 | Oct 2026 | Jul 2026 | Oct 2026
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV272QUAD | QBG - Welcome Garden & Sustainability Educ. Quad | 5 | CONSTRUCTION TO 25% | Oct 2026 | Feb 2027 | Oct 2026 | Feb 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV272QUAD | QBG - Welcome Garden & Sustainability Educ. Quad | 6 | CONSTRUCTION TO 50% | Feb 2027 | Jun 2027 | Feb 2027 | Jun 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV272QUAD | QBG - Welcome Garden & Sustainability Educ. Quad | 7 | CONSTRUCTION TO 75% | Jun 2027 | Oct 2027 | Jun 2027 | Oct 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV272QUAD | QBG - Welcome Garden & Sustainability Educ. Quad | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jan 2028 | Oct 2027 | Jan 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV272QUAD | QBG - Welcome Garden & Sustainability Educ. Quad | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Mar 2028 | Jan 2028 | Mar 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV272QUAD | QBG - Welcome Garden & Sustainability Educ. Quad | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2028 | Apr 2028 | Mar 2028 | Apr 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274-AH2 | NYHOS - New York Hall of Science - Air Handlers Replacement | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2026 | Sep 2026
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274-AH2 | NYHOS - New York Hall of Science - Air Handlers Replacement | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2026 | Jan 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274-AH2 | NYHOS - New York Hall of Science - Air Handlers Replacement | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2027 | Jul 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274-AH2 | NYHOS - New York Hall of Science - Air Handlers Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2027 | Oct 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274-AH2 | NYHOS - New York Hall of Science - Air Handlers Replacement | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2027 | Feb 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274-AH2 | NYHOS - New York Hall of Science - Air Handlers Replacement | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2028 | Jun 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274-AH2 | NYHOS - New York Hall of Science - Air Handlers Replacement | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2028 | Oct 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274-AH2 | NYHOS - New York Hall of Science - Air Handlers Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2028 | Jan 2029
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274-AH2 | NYHOS - New York Hall of Science - Air Handlers Replacement | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2029 | Mar 2029
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274-AH2 | NYHOS - New York Hall of Science - Air Handlers Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2029 | Apr 2029
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274NWRF | NYHOS - New York Hall of Science - North Wing Roof | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274NWRF | NYHOS - New York Hall of Science - North Wing Roof | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274NWRF | NYHOS - New York Hall of Science - North Wing Roof | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274NWRF | NYHOS - New York Hall of Science - North Wing Roof | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274NWRF | NYHOS - New York Hall of Science - North Wing Roof | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274NWRF | NYHOS - New York Hall of Science - North Wing Roof | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274NWRF | NYHOS - New York Hall of Science - North Wing Roof | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274NWRF | NYHOS - New York Hall of Science - North Wing Roof | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274NWRF | NYHOS - New York Hall of Science - North Wing Roof | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274NWRF | NYHOS - New York Hall of Science - North Wing Roof | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274PERI | NYHOS - New York Hall of Science, Perimeter Landscaping | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2027 | Aug 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274PERI | NYHOS - New York Hall of Science, Perimeter Landscaping | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Aug 2027 | Dec 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274PERI | NYHOS - New York Hall of Science, Perimeter Landscaping | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Dec 2027 | Jun 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274PERI | NYHOS - New York Hall of Science, Perimeter Landscaping | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jun 2028 | Sep 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274PERI | NYHOS - New York Hall of Science, Perimeter Landscaping | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Sep 2028 | Jan 2029
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274PERI | NYHOS - New York Hall of Science, Perimeter Landscaping | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Jan 2029 | May 2029
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274PERI | NYHOS - New York Hall of Science, Perimeter Landscaping | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | May 2029 | Sep 2029
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274PERI | NYHOS - New York Hall of Science, Perimeter Landscaping | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Sep 2029 | Dec 2029
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274PERI | NYHOS - New York Hall of Science, Perimeter Landscaping | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Dec 2029 | Feb 2030
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274PERI | NYHOS - New York Hall of Science, Perimeter Landscaping | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Feb 2030 | Mar 2030
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274THTR | NYHOS - New York Hall of Science -THEATER RENOVATION | 1 | DEVELOP SCOPE | Jun 2028 | Sep 2028 | Jun 2028 | Sep 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274THTR | NYHOS - New York Hall of Science -THEATER RENOVATION | 2 | PRELIMINARY DESIGN | Sep 2028 | Jan 2029 | Sep 2028 | Jan 2029
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274THTR | NYHOS - New York Hall of Science -THEATER RENOVATION | 3 | FINAL DESIGN | Jan 2029 | Jul 2029 | Jan 2029 | Jul 2029
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274THTR | NYHOS - New York Hall of Science -THEATER RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2029 | Oct 2029 | Jul 2029 | Oct 2029
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274THTR | NYHOS - New York Hall of Science -THEATER RENOVATION | 5 | CONSTRUCTION TO 25% | Oct 2029 | Feb 2030 | Oct 2029 | Feb 2030
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274THTR | NYHOS - New York Hall of Science -THEATER RENOVATION | 6 | CONSTRUCTION TO 50% | Feb 2030 | Jun 2030 | Feb 2030 | Jun 2030
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274THTR | NYHOS - New York Hall of Science -THEATER RENOVATION | 7 | CONSTRUCTION TO 75% | Jun 2030 | Oct 2030 | Jun 2030 | Oct 2030
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274THTR | NYHOS - New York Hall of Science -THEATER RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2030 | Jan 2031 | Oct 2030 | Jan 2031
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274THTR | NYHOS - New York Hall of Science -THEATER RENOVATION | 9 | SUBSTANTIAL COMPLETION | Jan 2031 | Mar 2031 | Jan 2031 | Mar 2031
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274THTR | NYHOS - New York Hall of Science -THEATER RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2031 | Apr 2031 | Mar 2031 | Apr 2031
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466QTP | QTIP - Queens Theater in the Park Shulman Theatre Renovation | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2022 | Sep 2022
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466QTP | QTIP - Queens Theater in the Park Shulman Theatre Renovation | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2022 | Jan 2023
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466QTP | QTIP - Queens Theater in the Park Shulman Theatre Renovation | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2023 | Jul 2023
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466QTP | QTIP - Queens Theater in the Park Shulman Theatre Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2023 | Oct 2023
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466QTP | QTIP - Queens Theater in the Park Shulman Theatre Renovation | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2023 | Feb 2024
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466QTP | QTIP - Queens Theater in the Park Shulman Theatre Renovation | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2024 | Jun 2024
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466QTP | QTIP - Queens Theater in the Park Shulman Theatre Renovation | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2024 | Oct 2024
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466QTP | QTIP - Queens Theater in the Park Shulman Theatre Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2024 | Jan 2025
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466QTP | QTIP - Queens Theater in the Park Shulman Theatre Renovation | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2025 | Mar 2025
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466QTP | QTIP - Queens Theater in the Park Shulman Theatre Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2025 | Apr 2025
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ATTC | PS1 - Attic Renovation for Studios | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Jul 2026 | Sep 2026
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ATTC | PS1 - Attic Renovation for Studios | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Sep 2026 | Jan 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ATTC | PS1 - Attic Renovation for Studios | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Jan 2027 | Jul 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ATTC | PS1 - Attic Renovation for Studios | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Jul 2027 | Oct 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ATTC | PS1 - Attic Renovation for Studios | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Oct 2027 | Feb 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ATTC | PS1 - Attic Renovation for Studios | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Feb 2028 | Jun 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ATTC | PS1 - Attic Renovation for Studios | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Jun 2028 | Oct 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ATTC | PS1 - Attic Renovation for Studios | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Dec 2018 | Oct 2028 | Jan 2029
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ATTC | PS1 - Attic Renovation for Studios | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Jan 2019 | Mar 2019
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ATTC | PS1 - Attic Renovation for Studios | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Mar 2019 | Mar 2019 | Mar 2019
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ELEV | PS1 - Elevator Renovation | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2025 | Sep 2025
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ELEV | PS1 - Elevator Renovation | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2025 | Jan 2026
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ELEV | PS1 - Elevator Renovation | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2026 | Jul 2026
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ELEV | PS1 - Elevator Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2026 | Oct 2026
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ELEV | PS1 - Elevator Renovation | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2026 | Feb 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ELEV | PS1 - Elevator Renovation | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2027 | Jun 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ELEV | PS1 - Elevator Renovation | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2027 | Oct 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ELEV | PS1 - Elevator Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Dec 2021 | Oct 2027 | Jan 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ELEV | PS1 - Elevator Renovation | 9 | SUBSTANTIAL COMPLETION | Dec 2021 | Feb 2022 | Jan 2028 | Mar 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ELEV | PS1 - Elevator Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Mar 2022 | Mar 2028 | Apr 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ROOF | PS1 - Renovation of PS1 Roof Areas PH 2 | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2026 | Aug 2026
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ROOF | PS1 - Renovation of PS1 Roof Areas PH 2 | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Aug 2026 | Dec 2026
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ROOF | PS1 - Renovation of PS1 Roof Areas PH 2 | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Dec 2026 | Jun 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ROOF | PS1 - Renovation of PS1 Roof Areas PH 2 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jun 2027 | Sep 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ROOF | PS1 - Renovation of PS1 Roof Areas PH 2 | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Sep 2027 | Jan 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ROOF | PS1 - Renovation of PS1 Roof Areas PH 2 | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Jan 2028 | May 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ROOF | PS1 - Renovation of PS1 Roof Areas PH 2 | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | May 2028 | Sep 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ROOF | PS1 - Renovation of PS1 Roof Areas PH 2 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Sep 2028 | Dec 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ROOF | PS1 - Renovation of PS1 Roof Areas PH 2 | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Dec 2028 | Feb 2029
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ROOF | PS1 - Renovation of PS1 Roof Areas PH 2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Feb 2029 | Mar 2029
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501RPH1 | PS1 - Renovation of PS1 Roof Areas PH 1 | 1 | DEVELOP SCOPE | Jul 2023 | Sep 2023 | Jun 2027 | Sep 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501RPH1 | PS1 - Renovation of PS1 Roof Areas PH 1 | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2027 | Jan 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501RPH1 | PS1 - Renovation of PS1 Roof Areas PH 1 | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2028 | Jul 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501RPH1 | PS1 - Renovation of PS1 Roof Areas PH 1 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2028 | Oct 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501RPH1 | PS1 - Renovation of PS1 Roof Areas PH 1 | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2028 | Feb 2029
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501RPH1 | PS1 - Renovation of PS1 Roof Areas PH 1 | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2029 | Jun 2029
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501RPH1 | PS1 - Renovation of PS1 Roof Areas PH 1 | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2029 | Oct 2029
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501RPH1 | PS1 - Renovation of PS1 Roof Areas PH 1 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2029 | Jan 2030
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501RPH1 | PS1 - Renovation of PS1 Roof Areas PH 1 | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2030 | Mar 2030
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501RPH1 | PS1 - Renovation of PS1 Roof Areas PH 1 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2030 | Apr 2030
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502ELEV | JCAL - Elevator Reconstruction/Modernization Section | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2025 | Sep 2025
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502ELEV | JCAL - Elevator Reconstruction/Modernization Section | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2025 | Jan 2026