20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502ELEV | JCAL - Elevator Reconstruction/Modernization Section | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2026 | Jul 2026
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502ELEV | JCAL - Elevator Reconstruction/Modernization Section | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2026 | Oct 2026
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502ELEV | JCAL - Elevator Reconstruction/Modernization Section | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2026 | Feb 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502ELEV | JCAL - Elevator Reconstruction/Modernization Section | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2027 | Jun 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502ELEV | JCAL - Elevator Reconstruction/Modernization Section | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2027 | Oct 2027
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502ELEV | JCAL - Elevator Reconstruction/Modernization Section | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2027 | Jan 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502ELEV | JCAL - Elevator Reconstruction/Modernization Section | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2028 | Mar 2028
20231026 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502ELEV | JCAL - Elevator Reconstruction/Modernization Section | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2028 | Apr 2028
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ECODOCKHC | ECO-DOCK AT HALLETS COVE | 1 | DESIGN | Jan 2016 | Jun 2018 | Jan 2023 | Jun 2025
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ECODOCKHC | ECO-DOCK AT HALLETS COVE | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Jun 2018 | Jul 2025 | Jun 2025
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ECODOCKHC | ECO-DOCK AT HALLETS COVE | 3 | CONSTRUCTION | Jul 2018 | Jun 2021 | Jul 2025 | Jun 2030
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ECODOCKHC | ECO-DOCK AT HALLETS COVE | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2021 | Jun 2021 | Jul 2030 | Jun 2030
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ECODOCKHC | ECO-DOCK AT HALLETS COVE | 5 | SUBSTANTIAL COMPLETION | Jul 2021 | Jun 2021 | Jul 2030 | Jun 2030
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ECODOCKHC | ECO-DOCK AT HALLETS COVE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Jul 2021 | Jul 2030 | Jun 2033
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1191 | Vernon Boulevard Bulkhead Replacement | 1 | DESIGN | Jan 2002 | Jan 2002 | Jan 2002 | Jan 2002
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1191 | Vernon Boulevard Bulkhead Replacement | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2002 | Feb 2002 | Jan 2002 | Feb 2002
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1191 | Vernon Boulevard Bulkhead Replacement | 3 | CONSTRUCTION | Jul 2016 | Jul 2019 | Jul 2016 | Jul 2021
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1191 | Vernon Boulevard Bulkhead Replacement | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2019 | Jul 2019 | Jul 2021 | Jul 2021
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1191 | Vernon Boulevard Bulkhead Replacement | 5 | SUBSTANTIAL COMPLETION | Jul 2019 | Jul 2019 | Jul 2021 | Jul 2021
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1191 | Vernon Boulevard Bulkhead Replacement | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2019 | Jul 2019 | Jul 2021 | Jun 2026
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1209 | Utopia Parkway Safety Improvements & Seawall Repair | 1 | DESIGN | Jul 2023 | Jul 2023 | Jul 2023 | Jul 2023
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1209 | Utopia Parkway Safety Improvements & Seawall Repair | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1209 | Utopia Parkway Safety Improvements & Seawall Repair | 3 | CONSTRUCTION | Aug 2023 | Sep 2023 | Aug 2023 | Sep 2023
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1209 | Utopia Parkway Safety Improvements & Seawall Repair | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Sep 2023 | Sep 2023 | Sep 2023
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1209 | Utopia Parkway Safety Improvements & Seawall Repair | 5 | SUBSTANTIAL COMPLETION | Sep 2023 | Oct 2023 | Sep 2023 | Oct 2023
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1209 | Utopia Parkway Safety Improvements & Seawall Repair | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2023 | Jun 2025 | Oct 2023 | Jun 2025
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ187A | 132nd St Construction - 20th Ave to Linden Place | 1 | DESIGN | Jan 2008 | Jan 2009 | Jun 2010 | Jun 2010
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ187A | 132nd St Construction - 20th Ave to Linden Place | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2009 | Jan 2009 | Jun 2010 | Jun 2010
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ187A | 132nd St Construction - 20th Ave to Linden Place | 3 | CONSTRUCTION | Jan 2009 | Jan 2011 | Jul 2001 | Jun 2019
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ187A | 132nd St Construction - 20th Ave to Linden Place | 4 | ORIGINAL EQUIP & FURNISHING | Jan 2011 | Jan 2011 | Jul 2019 | Jun 2019
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ187A | 132nd St Construction - 20th Ave to Linden Place | 5 | SUBSTANTIAL COMPLETION | Jan 2011 | Jan 2011 | Jul 2019 | Jun 2019
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ187A | 132nd St Construction - 20th Ave to Linden Place | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2011 | Jan 2011 | Jul 2019 | Jul 2024
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQBCH6WF | Reynolds Channel Waterfront - Beach 6 Street End | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQBCH6WF | Reynolds Channel Waterfront - Beach 6 Street End | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQBCH6WF | Reynolds Channel Waterfront - Beach 6 Street End | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQBCH6WF | Reynolds Channel Waterfront - Beach 6 Street End | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQBCH6WF | Reynolds Channel Waterfront - Beach 6 Street End | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQBCH6WF | Reynolds Channel Waterfront - Beach 6 Street End | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQBCH6WF | Reynolds Channel Waterfront - Beach 6 Street End | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQBCH6WF | Reynolds Channel Waterfront - Beach 6 Street End | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQBCH6WF | Reynolds Channel Waterfront - Beach 6 Street End | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQBCH6WF | Reynolds Channel Waterfront - Beach 6 Street End | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2025
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQBCH8WF | Reynolds Channel Waterfront - Beach 8 Street End | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQBCH8WF | Reynolds Channel Waterfront - Beach 8 Street End | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQBCH8WF | Reynolds Channel Waterfront - Beach 8 Street End | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQBCH8WF | Reynolds Channel Waterfront - Beach 8 Street End | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQBCH8WF | Reynolds Channel Waterfront - Beach 8 Street End | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQBCH8WF | Reynolds Channel Waterfront - Beach 8 Street End | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQBCH8WF | Reynolds Channel Waterfront - Beach 8 Street End | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQBCH8WF | Reynolds Channel Waterfront - Beach 8 Street End | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQBCH8WF | Reynolds Channel Waterfront - Beach 8 Street End | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQBCH8WF | Reynolds Channel Waterfront - Beach 8 Street End | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2025
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMAAECT | GDJC - Atlantic Avenue Extension - Construction | 1 | DESIGN | Dec 2013 | May 2014 | Dec 2013 | Jun 2014
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMAAECT | GDJC - Atlantic Avenue Extension - Construction | 2 | BID AWARD AND REGISTER CONTRCT | May 2014 | May 2014 | Jun 2014 | Jun 2014
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMAAECT | GDJC - Atlantic Avenue Extension - Construction | 3 | CONSTRUCTION | May 2014 | Jan 2016 | Jun 2014 | Jan 2016
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMAAECT | GDJC - Atlantic Avenue Extension - Construction | 4 | ORIGINAL EQUIP & FURNISHING | Jan 2016 | Jan 2016 | Jan 2016 | Jan 2016
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMAAECT | GDJC - Atlantic Avenue Extension - Construction | 5 | SUBSTANTIAL COMPLETION | Jan 2016 | Jan 2016 | Jan 2016 | Jan 2016
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMAAECT | GDJC - Atlantic Avenue Extension - Construction | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2016 | Jan 2016 | Jan 2016 | Jun 2029
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMSTPLZ | Station Plaza Design & Construction | 1 | DESIGN | Jan 2016 | Jun 2018 | Jan 2016 | Jun 2018
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMSTPLZ | Station Plaza Design & Construction | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Jun 2018 | Jul 2018 | Jun 2018
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMSTPLZ | Station Plaza Design & Construction | 3 | CONSTRUCTION | Jul 2018 | Jun 2021 | Jul 2018 | Jun 2031
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMSTPLZ | Station Plaza Design & Construction | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2021 | Jun 2021 | Jul 2031 | Jun 2031
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMSTPLZ | Station Plaza Design & Construction | 5 | SUBSTANTIAL COMPLETION | Jul 2021 | Jun 2021 | Jul 2031 | Jun 2031
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMSTPLZ | Station Plaza Design & Construction | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Jul 2021 | Jul 2031 | Jul 2031
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | P-4QNSWAY | Queensway - LIRR Rockaway Branch Line Into A Park | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | P-4QNSWAY | Queensway - LIRR Rockaway Branch Line Into A Park | 2 | DESIGN | Dec 2022 | Dec 2024 | Dec 2022 | Dec 2024
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | P-4QNSWAY | Queensway - LIRR Rockaway Branch Line Into A Park | 3 | BID/ REGISTER CONTRACT | Dec 2024 | Sep 2025 | Dec 2024 | Sep 2025
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | P-4QNSWAY | Queensway - LIRR Rockaway Branch Line Into A Park | 4 | CONSTRUCTION | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | P-4QNSWAY | Queensway - LIRR Rockaway Branch Line Into A Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Sep 2028 | Sep 2027 | Sep 2028
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETDEM | Willets Point Above Grade Demolition | 1 | DESIGN | Jul 2015 | Jul 2015 | Jul 2015 | Jul 2015
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETDEM | Willets Point Above Grade Demolition | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Aug 2015 | Jul 2015 | Aug 2015
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETDEM | Willets Point Above Grade Demolition | 3 | CONSTRUCTION | Aug 2015 | Sep 2015 | Aug 2015 | Sep 2015
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETDEM | Willets Point Above Grade Demolition | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2015 | Sep 2015 | Sep 2015 | Sep 2015
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETDEM | Willets Point Above Grade Demolition | 5 | SUBSTANTIAL COMPLETION | Sep 2015 | Oct 2015 | Sep 2015 | Oct 2015
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETDEM | Willets Point Above Grade Demolition | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2015 | Oct 2019 | Oct 2015 | Oct 2031
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETINF | Willets Point Redevelopment Infrastructure | 1 | DESIGN | Jan 2010 | Jan 2011 | Aug 2019 | Sep 2019
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETINF | Willets Point Redevelopment Infrastructure | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2011 | Jan 2011 | Sep 2019 | Sep 2019
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETINF | Willets Point Redevelopment Infrastructure | 3 | CONSTRUCTION | Jan 2011 | Jan 2013 | Sep 2019 | Sep 2019
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETINF | Willets Point Redevelopment Infrastructure | 4 | ORIGINAL EQUIP & FURNISHING | Jan 2013 | Jan 2013 | Sep 2019 | Sep 2019
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETINF | Willets Point Redevelopment Infrastructure | 5 | SUBSTANTIAL COMPLETION | Jan 2013 | Jan 2013 | Sep 2019 | Jun 2031
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETINF | Willets Point Redevelopment Infrastructure | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2013 | Jan 2013 | Jun 2031 | Jun 2031
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETPH2 | FA - Willets Point Phase 2 | 1 | DESIGN | Jul 2023 | Jul 2023 | Jul 2023 | Jul 2023
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETPH2 | FA - Willets Point Phase 2 | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETPH2 | FA - Willets Point Phase 2 | 3 | CONSTRUCTION | Aug 2023 | Sep 2023 | Aug 2023 | Sep 2023
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETPH2 | FA - Willets Point Phase 2 | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Sep 2023 | Sep 2023 | Sep 2023
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETPH2 | FA - Willets Point Phase 2 | 5 | SUBSTANTIAL COMPLETION | Sep 2023 | Oct 2023 | Sep 2023 | Oct 2023
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETPH2 | FA - Willets Point Phase 2 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2023 | Jun 2027 | Oct 2023 | Jun 2027
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETS23 | Willets Point Redevelopment - Relocation Services | 1 | DESIGN | Jul 2023 | Jul 2023 | Jul 2023 | Jul 2023
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETS23 | Willets Point Redevelopment - Relocation Services | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETS23 | Willets Point Redevelopment - Relocation Services | 3 | CONSTRUCTION | Aug 2023 | Sep 2023 | Aug 2023 | Sep 2023
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETS23 | Willets Point Redevelopment - Relocation Services | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Sep 2023 | Sep 2023 | Sep 2023
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETS23 | Willets Point Redevelopment - Relocation Services | 5 | SUBSTANTIAL COMPLETION | Sep 2023 | Oct 2023 | Sep 2023 | Oct 2023
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLETS23 | Willets Point Redevelopment - Relocation Services | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2023 | Jun 2025 | Oct 2023 | Jun 2025
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLTFAON | FA - Willet's Point Onsite Infrastructure | 1 | DESIGN | Jul 2019 | Jul 2019 | Jul 2019 | Jul 2019
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLTFAON | FA - Willet's Point Onsite Infrastructure | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jul 2019 | Aug 2019
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLTFAON | FA - Willet's Point Onsite Infrastructure | 3 | CONSTRUCTION | Aug 2019 | Sep 2019 | Aug 2019 | Sep 2019
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLTFAON | FA - Willet's Point Onsite Infrastructure | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Sep 2022 | Sep 2019 | Sep 2024
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLTFAON | FA - Willet's Point Onsite Infrastructure | 5 | SUBSTANTIAL COMPLETION | Sep 2022 | Oct 2022 | Sep 2024 | Oct 2024
20231026 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLTFAON | FA - Willet's Point Onsite Infrastructure | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2022 | Oct 2022 | Oct 2024 | Jun 2030
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM15RFGR | REDFERN COMMUNITY CENTER PLAYGROUND | 1 | DESIGN | Jan 2015 | Jun 2015 | Jun 2018 | Dec 2018
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM15RFGR | REDFERN COMMUNITY CENTER PLAYGROUND | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Nov 2015 | Jan 2019 | May 2019
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM15RFGR | REDFERN COMMUNITY CENTER PLAYGROUND | 3 | CONSTRUCTION | Nov 2015 | Nov 2016 | May 2019 | May 2020
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM15RFGR | REDFERN COMMUNITY CENTER PLAYGROUND | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2016 | May 2017 | May 2019 | May 2020
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM15RFGR | REDFERN COMMUNITY CENTER PLAYGROUND | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2016 | May 2017 | May 2020 | Feb 2024
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SJBC | SOUTH JAMAICA HOUSES BASKETBALL COURT UPGRADES | 1 | DESIGN | Jan 2015 | Jun 2015 | Jul 2016 | Jan 2017
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SJBC | SOUTH JAMAICA HOUSES BASKETBALL COURT UPGRADES | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Nov 2015 | Jan 2017 | Jun 2017
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SJBC | SOUTH JAMAICA HOUSES BASKETBALL COURT UPGRADES | 3 | CONSTRUCTION | Nov 2015 | Nov 2016 | Jun 2017 | Jun 2018
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SJBC | SOUTH JAMAICA HOUSES BASKETBALL COURT UPGRADES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2016 | May 2017 | Jun 2017 | Jun 2018
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SJBC | SOUTH JAMAICA HOUSES BASKETBALL COURT UPGRADES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2016 | May 2017 | Jun 2018 | Oct 2024
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CMPL | CARLTON MANOR PLAYGROUND RENOVATIONS BASKETBALL COURTS | 1 | DESIGN | Jan 2016 | Jul 2016 | Jan 2018 | Jun 2018
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CMPL | CARLTON MANOR PLAYGROUND RENOVATIONS BASKETBALL COURTS | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Nov 2016 | Jun 2018 | Nov 2018
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CMPL | CARLTON MANOR PLAYGROUND RENOVATIONS BASKETBALL COURTS | 3 | CONSTRUCTION | Nov 2016 | Nov 2017 | Nov 2018 | Nov 2019
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CMPL | CARLTON MANOR PLAYGROUND RENOVATIONS BASKETBALL COURTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | May 2018 | Nov 2018 | Nov 2019
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CMPL | CARLTON MANOR PLAYGROUND RENOVATIONS BASKETBALL COURTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | May 2018 | Nov 2019 | May 2024
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17AHPL | ASTORIA HOUSES PLAYGROUND UPGRADE | 1 | DESIGN | Feb 2017 | Jul 2017 | Feb 2017 | Jul 2017
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17AHPL | ASTORIA HOUSES PLAYGROUND UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17AHPL | ASTORIA HOUSES PLAYGROUND UPGRADE | 3 | CONSTRUCTION | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17AHPL | ASTORIA HOUSES PLAYGROUND UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2018 | Jun 2019 | Dec 2017 | Dec 2018
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17AHPL | ASTORIA HOUSES PLAYGROUND UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2018 | Jun 2019 | Dec 2018 | Jun 2023
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17BPSC | BAISLEY PARK INSTALLATION OF SECURITY CAMERAS | 1 | DESIGN | Feb 2017 | Jul 2017 | Feb 2017 | Jul 2017
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17BPSC | BAISLEY PARK INSTALLATION OF SECURITY CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17BPSC | BAISLEY PARK INSTALLATION OF SECURITY CAMERAS | 3 | CONSTRUCTION | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17BPSC | BAISLEY PARK INSTALLATION OF SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2018 | Jun 2019 | Dec 2017 | Dec 2018
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17BPSC | BAISLEY PARK INSTALLATION OF SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2018 | Jun 2019 | Dec 2018 | May 2023
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17LGPL | LATIMER GARDENS PLAYGROUND UPGRADE | 1 | DESIGN | Feb 2017 | Jul 2017 | Feb 2017 | Jul 2017
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17LGPL | LATIMER GARDENS PLAYGROUND UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17LGPL | LATIMER GARDENS PLAYGROUND UPGRADE | 3 | CONSTRUCTION | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17LGPL | LATIMER GARDENS PLAYGROUND UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2018 | Jun 2019 | Dec 2017 | Dec 2018
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17LGPL | LATIMER GARDENS PLAYGROUND UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2018 | Jun 2019 | Dec 2018 | Jul 2022
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17SHSC | SHELTON HOUSES INSTALLATION OF CCTV'S AND LAC'S | 1 | DESIGN | Feb 2017 | Jul 2017 | Feb 2017 | Jul 2017
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17SHSC | SHELTON HOUSES INSTALLATION OF CCTV'S AND LAC'S | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17SHSC | SHELTON HOUSES INSTALLATION OF CCTV'S AND LAC'S | 3 | CONSTRUCTION | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17SHSC | SHELTON HOUSES INSTALLATION OF CCTV'S AND LAC'S | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2018 | Jun 2019 | Dec 2017 | Dec 2018
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17SHSC | SHELTON HOUSES INSTALLATION OF CCTV'S AND LAC'S | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2018 | Jun 2019 | Dec 2018 | Dec 2022
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17WHPL | WOODSIDE HOUSES PLAYGROUND UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2018 | Jun 2019 | Dec 2017 | Dec 2018
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17WHPL | WOODSIDE HOUSES PLAYGROUND UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2018 | Jun 2019 | Dec 2018 | Jun 2019
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BLGR | BLAND HOUSES GROUNDS BEAUTIFICATION | 1 | DESIGN | Jan 2018 | Jun 2018 | Jan 2018 | Jun 2018
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BLGR | BLAND HOUSES GROUNDS BEAUTIFICATION | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BLGR | BLAND HOUSES GROUNDS BEAUTIFICATION | 3 | CONSTRUCTION | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BLGR | BLAND HOUSES GROUNDS BEAUTIFICATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2018 | Dec 2019
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BLGR | BLAND HOUSES GROUNDS BEAUTIFICATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2019 | Dec 2022
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18COTV | LAYERED SECURITY ACCESS AT CONLON LIFHE | 1 | DESIGN | Jan 2018 | Jun 2018 | Jan 2018 | Jun 2018
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18COTV | LAYERED SECURITY ACCESS AT CONLON LIFHE | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18COTV | LAYERED SECURITY ACCESS AT CONLON LIFHE | 3 | CONSTRUCTION | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18COTV | LAYERED SECURITY ACCESS AT CONLON LIFHE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2018 | Dec 2019
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18COTV | LAYERED SECURITY ACCESS AT CONLON LIFHE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2019 | Dec 2024
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19AHSC | ASTORIA HOUSES SECURITY CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2019 | May 2020 | Nov 2019 | May 2020
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19AHSC | ASTORIA HOUSES SECURITY CAMERAS | 3 | CONSTRUCTION | May 2020 | May 2021 | May 2020 | May 2021
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19AHSC | ASTORIA HOUSES SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2021 | Nov 2021 | May 2020 | May 2021
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19AHSC | ASTORIA HOUSES SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2021 | Nov 2021 | May 2021 | Nov 2021
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CLHS | CONLON LIHFE HVAC SYSTEM | 1 | DESIGN | Oct 2018 | Apr 2019 | Oct 2018 | Apr 2019
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CLHS | CONLON LIHFE HVAC SYSTEM | 2 | BID AWARD AND REGISTER CONTRCT | Apr 2019 | Oct 2019 | Apr 2019 | Oct 2019
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CLHS | CONLON LIHFE HVAC SYSTEM | 3 | CONSTRUCTION | Oct 2019 | Oct 2020 | Oct 2019 | Oct 2020
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CLHS | CONLON LIHFE HVAC SYSTEM | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2020 | Apr 2021 | Oct 2019 | Oct 2020
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CLHS | CONLON LIHFE HVAC SYSTEM | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2020 | Apr 2021 | Oct 2020 | Oct 2024
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19WHRB | WOODSIDE HOUSES RENOVATION OF BOYS AND GIRLS BATHROOMS | 1 | DESIGN | Nov 2018 | May 2019 | Nov 2018 | May 2019
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19WHRB | WOODSIDE HOUSES RENOVATION OF BOYS AND GIRLS BATHROOMS | 2 | BID AWARD AND REGISTER CONTRCT | May 2019 | Nov 2019 | May 2019 | Nov 2019
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19WHRB | WOODSIDE HOUSES RENOVATION OF BOYS AND GIRLS BATHROOMS | 3 | CONSTRUCTION | Nov 2019 | Nov 2020 | Nov 2019 | Nov 2020
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19WHRB | WOODSIDE HOUSES RENOVATION OF BOYS AND GIRLS BATHROOMS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2020 | May 2021 | Nov 2019 | Nov 2020
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19WHRB | WOODSIDE HOUSES RENOVATION OF BOYS AND GIRLS BATHROOMS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2020 | May 2021 | Nov 2020 | Nov 2022
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ASGR | ASTORIA- GARDEN AND GROUNDS BEAUTIFICATION | 1 | DESIGN | Jan 2018 | Jun 2018 | Jan 2018 | Jun 2018
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ASGR | ASTORIA- GARDEN AND GROUNDS BEAUTIFICATION | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ASGR | ASTORIA- GARDEN AND GROUNDS BEAUTIFICATION | 3 | CONSTRUCTION | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ASGR | ASTORIA- GARDEN AND GROUNDS BEAUTIFICATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2018 | Dec 2019
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ASGR | ASTORIA- GARDEN AND GROUNDS BEAUTIFICATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2019 | Dec 2023
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHCS | BAISLEY - CCTV CAMERA SYSTEM FOR ALL 27 BUILDINGS | 1 | DESIGN | Jan 2018 | Jun 2018 | Jan 2018 | Jun 2018
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHCS | BAISLEY - CCTV CAMERA SYSTEM FOR ALL 27 BUILDINGS | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHCS | BAISLEY - CCTV CAMERA SYSTEM FOR ALL 27 BUILDINGS | 3 | CONSTRUCTION | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHCS | BAISLEY - CCTV CAMERA SYSTEM FOR ALL 27 BUILDINGS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2018 | Dec 2019
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHCS | BAISLEY - CCTV CAMERA SYSTEM FOR ALL 27 BUILDINGS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2019 | Dec 2023
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHLL | BLAND HOUSES- LED LIGHTING | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHLL | BLAND HOUSES- LED LIGHTING | 3 | CONSTRUCTION | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHLL | BLAND HOUSES- LED LIGHTING | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2018 | Dec 2019
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHLL | BLAND HOUSES- LED LIGHTING | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2019 | Dec 2023
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JYCL | S JAMAICA - UPGRADE TO COMPUTER LAB AT YOUTH CENTER | 1 | DEVELOP SCOPE | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JYCL | S JAMAICA - UPGRADE TO COMPUTER LAB AT YOUTH CENTER | 2 | PRELIMINARY DESIGN | Nov 2019 | Mar 2020 | Nov 2019 | Mar 2020
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JYCL | S JAMAICA - UPGRADE TO COMPUTER LAB AT YOUTH CENTER | 3 | FINAL DESIGN | Mar 2020 | Sep 2020 | Mar 2020 | Sep 2020
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JYCL | S JAMAICA - UPGRADE TO COMPUTER LAB AT YOUTH CENTER | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2020 | Dec 2020 | Sep 2020 | Dec 2020
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JYCL | S JAMAICA - UPGRADE TO COMPUTER LAB AT YOUTH CENTER | 5 | CONSTRUCTION TO 25% | Dec 2020 | Apr 2021 | Dec 2020 | Apr 2021
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JYCL | S JAMAICA - UPGRADE TO COMPUTER LAB AT YOUTH CENTER | 6 | CONSTRUCTION TO 50% | Apr 2021 | Aug 2021 | Apr 2021 | Aug 2021
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JYCL | S JAMAICA - UPGRADE TO COMPUTER LAB AT YOUTH CENTER | 7 | CONSTRUCTION TO 75% | Aug 2021 | Dec 2021 | Aug 2021 | Jun 2022
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JYCL | S JAMAICA - UPGRADE TO COMPUTER LAB AT YOUTH CENTER | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2021 | Mar 2022 | Jun 2022 | Sep 2022
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JYCL | S JAMAICA - UPGRADE TO COMPUTER LAB AT YOUTH CENTER | 9 | SUBSTANTIAL COMPLETION | Mar 2022 | May 2022 | Sep 2022 | Nov 2022
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JYCL | S JAMAICA - UPGRADE TO COMPUTER LAB AT YOUTH CENTER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2022 | Jun 2022 | Nov 2022 | Dec 2022
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LCSC | LEWIS H. LATIMER SECURITY CAMERAS AT SENIOR CENTER | 2 | PRELIMINARY DESIGN | Nov 2020 | Mar 2021 | Nov 2020 | Mar 2021
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LCSC | LEWIS H. LATIMER SECURITY CAMERAS AT SENIOR CENTER | 3 | FINAL DESIGN | Mar 2021 | Sep 2021 | Mar 2021 | Sep 2021
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LCSC | LEWIS H. LATIMER SECURITY CAMERAS AT SENIOR CENTER | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2021 | Dec 2021 | Sep 2021 | Dec 2021
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LCSC | LEWIS H. LATIMER SECURITY CAMERAS AT SENIOR CENTER | 5 | CONSTRUCTION TO 25% | Dec 2021 | Apr 2022 | Dec 2021 | Apr 2022
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LCSC | LEWIS H. LATIMER SECURITY CAMERAS AT SENIOR CENTER | 6 | CONSTRUCTION TO 50% | Apr 2022 | Aug 2022 | Apr 2022 | Aug 2022
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LCSC | LEWIS H. LATIMER SECURITY CAMERAS AT SENIOR CENTER | 7 | CONSTRUCTION TO 75% | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LCSC | LEWIS H. LATIMER SECURITY CAMERAS AT SENIOR CENTER | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2022 | Mar 2023 | Dec 2022 | Mar 2023
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LCSC | LEWIS H. LATIMER SECURITY CAMERAS AT SENIOR CENTER | 9 | SUBSTANTIAL COMPLETION | Mar 2023 | May 2023 | Mar 2023 | May 2023
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LCSC | LEWIS H. LATIMER SECURITY CAMERAS AT SENIOR CENTER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2023 | Jun 2023 | May 2023 | Jun 2023
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20RCCB | RAVENSWOOD COMMUNITY CENTER BATHROOMS | 1 | DESIGN | Sep 2019 | Feb 2020 | Sep 2019 | Feb 2020
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20RCCB | RAVENSWOOD COMMUNITY CENTER BATHROOMS | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Aug 2020 | Feb 2020 | Aug 2020
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20RCCB | RAVENSWOOD COMMUNITY CENTER BATHROOMS | 3 | CONSTRUCTION | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20RCCB | RAVENSWOOD COMMUNITY CENTER BATHROOMS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2020 | Aug 2021
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20RCCB | RAVENSWOOD COMMUNITY CENTER BATHROOMS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2021 | Aug 2023
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM21BHEL | BEACH 41 STREET SECURITY UPGRADES | 1 | DESIGN | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM21BHEL | BEACH 41 STREET SECURITY UPGRADES | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM21BHEL | BEACH 41 STREET SECURITY UPGRADES | 3 | CONSTRUCTION | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM21BHEL | BEACH 41 STREET SECURITY UPGRADES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2021 | Jun 2022
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM21BHEL | BEACH 41 STREET SECURITY UPGRADES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SJWW | DIAGONAL CEMENT WALKWAY AT SOUTH JAMAICA HOUSES II | 1 | DESIGN | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SJWW | DIAGONAL CEMENT WALKWAY AT SOUTH JAMAICA HOUSES II | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SJWW | DIAGONAL CEMENT WALKWAY AT SOUTH JAMAICA HOUSES II | 3 | CONSTRUCTION | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SJWW | DIAGONAL CEMENT WALKWAY AT SOUTH JAMAICA HOUSES II | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2021 | Jun 2022
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SJWW | DIAGONAL CEMENT WALKWAY AT SOUTH JAMAICA HOUSES II | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22AHSL | ASTORIA HOUSES- SCIENCE LAB | 1 | DESIGN | Jan 2022 | Jun 2022 | Jan 2022 | Jun 2022
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22AHSL | ASTORIA HOUSES- SCIENCE LAB | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22AHSL | ASTORIA HOUSES- SCIENCE LAB | 3 | CONSTRUCTION | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22AHSL | ASTORIA HOUSES- SCIENCE LAB | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jun 2024 | Dec 2022 | Dec 2023
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22AHSL | ASTORIA HOUSES- SCIENCE LAB | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22BPCC | Baisley Park Houses Community Center Reopen | 1 | DESIGN | Jun 2022 | Nov 2022 | Jun 2022 | Nov 2022
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22BPCC | Baisley Park Houses Community Center Reopen | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2022 | May 2023 | Nov 2022 | May 2023
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22BPCC | Baisley Park Houses Community Center Reopen | 3 | CONSTRUCTION | May 2023 | May 2024 | May 2023 | May 2024
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22BPCC | Baisley Park Houses Community Center Reopen | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2023 | May 2024
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22BPCC | Baisley Park Houses Community Center Reopen | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22LMTU | LATIMER GARDENS - TECHNOLOGY UPGRADE | 1 | DESIGN | Jan 2022 | Jun 2022 | Jan 2022 | Jun 2022
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22LMTU | LATIMER GARDENS - TECHNOLOGY UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22LMTU | LATIMER GARDENS - TECHNOLOGY UPGRADE | 3 | CONSTRUCTION | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22LMTU | LATIMER GARDENS - TECHNOLOGY UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jun 2024 | Dec 2022 | Dec 2023
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22LMTU | LATIMER GARDENS - TECHNOLOGY UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22PBBQ | POMONOK HOUSES- OUTDOOR RENOVATIONS | 1 | DESIGN | Jan 2022 | Jun 2022 | Jan 2022 | Jun 2022
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22PBBQ | POMONOK HOUSES- OUTDOOR RENOVATIONS | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22PBBQ | POMONOK HOUSES- OUTDOOR RENOVATIONS | 3 | CONSTRUCTION | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22PBBQ | POMONOK HOUSES- OUTDOOR RENOVATIONS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jun 2024 | Dec 2022 | Dec 2023
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22PBBQ | POMONOK HOUSES- OUTDOOR RENOVATIONS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SJCA | SOUTH JAMAICA I & II- SECURITY OPERATIONS CENTER & CAMERAS | 1 | DESIGN | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SJCA | SOUTH JAMAICA I & II- SECURITY OPERATIONS CENTER & CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SJCA | SOUTH JAMAICA I & II- SECURITY OPERATIONS CENTER & CAMERAS | 3 | CONSTRUCTION | Jun 2023 | Jun 2024 | Jun 2023 | Jun 2024
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SJCA | SOUTH JAMAICA I & II- SECURITY OPERATIONS CENTER & CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2024 | Dec 2024 | Jun 2023 | Jun 2024
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SJCA | SOUTH JAMAICA I & II- SECURITY OPERATIONS CENTER & CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2024 | Dec 2024 | Jun 2024 | Dec 2024
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SJCB | SOUTH JAMAICA HOUSES- CLOUDBURST PLA ADDITIONS | 1 | DESIGN | Jan 2022 | Jun 2022 | Jan 2022 | Jun 2022
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SJCB | SOUTH JAMAICA HOUSES- CLOUDBURST PLA ADDITIONS | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SJCB | SOUTH JAMAICA HOUSES- CLOUDBURST PLA ADDITIONS | 3 | CONSTRUCTION | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SJCB | SOUTH JAMAICA HOUSES- CLOUDBURST PLA ADDITIONS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jun 2024 | Dec 2022 | Dec 2023
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SJCB | SOUTH JAMAICA HOUSES- CLOUDBURST PLA ADDITIONS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM23ALPL | ASTORIA HOUSES- OUTDOOR LIGHTING | 1 | DESIGN | Jan 2023 | Jun 2023 | Jan 2023 | Jun 2023
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM23ALPL | ASTORIA HOUSES- OUTDOOR LIGHTING | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Dec 2023 | Jul 2023 | Dec 2023
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM23ALPL | ASTORIA HOUSES- OUTDOOR LIGHTING | 3 | CONSTRUCTION | Dec 2023 | Dec 2024 | Dec 2023 | Dec 2024
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM23ALPL | ASTORIA HOUSES- OUTDOOR LIGHTING | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2024 | Jun 2025 | Dec 2023 | Dec 2024
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM23ALPL | ASTORIA HOUSES- OUTDOOR LIGHTING | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM23OSSC | OCEAN SIDE HOUSES - SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2025 | Dec 2025 | Jun 2024 | Jun 2025
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM23OSSC | OCEAN SIDE HOUSES - SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2025 | Dec 2025 | Jun 2025 | Dec 2025
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | SEQ-SJH | CONSTRUCTION FOR CLOUDBURST PROJECT AT SOUTH JAMAICA HOUSES | 1 | DEVELOP SCOPE | Jun 2022 | Mar 2023 | Jun 2022 | Mar 2023
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | SEQ-SJH | CONSTRUCTION FOR CLOUDBURST PROJECT AT SOUTH JAMAICA HOUSES | 2 | PRELIMINARY DESIGN | Mar 2023 | Mar 2024 | Mar 2023 | Mar 2024
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | SEQ-SJH | CONSTRUCTION FOR CLOUDBURST PROJECT AT SOUTH JAMAICA HOUSES | 3 | FINAL DESIGN | Mar 2024 | Aug 2025 | Mar 2024 | Aug 2025
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | SEQ-SJH | CONSTRUCTION FOR CLOUDBURST PROJECT AT SOUTH JAMAICA HOUSES | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2025 | May 2026 | Aug 2025 | May 2026
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | SEQ-SJH | CONSTRUCTION FOR CLOUDBURST PROJECT AT SOUTH JAMAICA HOUSES | 5 | CONSTRUCTION TO 25% | May 2026 | May 2027 | May 2026 | May 2027
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | SEQ-SJH | CONSTRUCTION FOR CLOUDBURST PROJECT AT SOUTH JAMAICA HOUSES | 6 | CONSTRUCTION TO 50% | May 2027 | May 2028 | May 2027 | May 2028
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | SEQ-SJH | CONSTRUCTION FOR CLOUDBURST PROJECT AT SOUTH JAMAICA HOUSES | 7 | CONSTRUCTION TO 75% | May 2028 | May 2029 | May 2028 | May 2029
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | SEQ-SJH | CONSTRUCTION FOR CLOUDBURST PROJECT AT SOUTH JAMAICA HOUSES | 8 | ORIGINAL EQUIP & FURNISHING | May 2029 | Feb 2030 | May 2029 | Feb 2030
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | SEQ-SJH | CONSTRUCTION FOR CLOUDBURST PROJECT AT SOUTH JAMAICA HOUSES | 9 | SUBSTANTIAL COMPLETION | Feb 2030 | Aug 2030 | Feb 2030 | Aug 2030
20231026 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | SEQ-SJH | CONSTRUCTION FOR CLOUDBURST PROJECT AT SOUTH JAMAICA HOUSES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2030 | Oct 2030 | Aug 2030 | Oct 2030
20231026 | QUEENS | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH212 | DOH - Jamaica Health Center - Chiller Upgrade | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2022 | Jun 2022 | Jun 2022
20231026 | QUEENS | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH212 | DOH - Jamaica Health Center - Chiller Upgrade | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Aug 2022 | Jul 2022 | Aug 2022
20231026 | QUEENS | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH212 | DOH - Jamaica Health Center - Chiller Upgrade | 3 | CONSTRUCTION TO 50% | Aug 2022 | Feb 2023 | Aug 2022 | Feb 2023
20231026 | QUEENS | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH212 | DOH - Jamaica Health Center - Chiller Upgrade | 4 | CONSTRUCTION TO 75% | Feb 2023 | May 2023 | Feb 2023 | May 2023
20231026 | QUEENS | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH212 | DOH - Jamaica Health Center - Chiller Upgrade | 5 | SUBSTANTIAL COMPLETION | May 2023 | Jul 2023 | May 2023 | Jul 2023
20231026 | QUEENS | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH212 | DOH - Jamaica Health Center - Chiller Upgrade | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | QUEENS | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82JAMPH | JAMAICA HEALTH CENTER PHARMACY RETRO-FIT | 2 | CONSTRUCTION | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | QUEENS | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82JAMPH | JAMAICA HEALTH CENTER PHARMACY RETRO-FIT | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 02201804 | LIC OUTFIT OFFICE SPACE | 1 | DESIGN | Jul 2018 | Jan 2019 | Jul 2019 | Dec 2027
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 02201804 | LIC OUTFIT OFFICE SPACE | 2 | CONSTRUCTION | Jan 2019 | Jun 2019 | Dec 2027 | Jun 2033
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201301 | ELMHURST RENOVATION OF ADULT ER | 1 | DESIGN | Feb 2016 | Jul 2017 | Feb 2016 | Jul 2017
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201301 | ELMHURST RENOVATION OF ADULT ER | 2 | CONSTRUCTION | Jul 2017 | Jul 2019 | Jul 2017 | Jul 2019
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201301 | ELMHURST RENOVATION OF ADULT ER | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2019 | Sep 2019 | Jul 2019 | Sep 2019
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201505 | ELMHURST: PURCHASE & INSTALL BIPLANE/CT SCANNER | 2 | CONSTRUCTION | Jan 2019 | Jun 2019 | Jan 2019 | Jun 2019
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201602 | EHC PARAPET & CORNER FACADE REHAB A,B,D,E, J AND O&G ANNEX. | 1 | DESIGN | Aug 2019 | Jun 2020 | Aug 2019 | Jun 2020
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201602 | EHC PARAPET & CORNER FACADE REHAB A,B,D,E, J AND O&G ANNEX. | 2 | CONSTRUCTION | Jul 2020 | Jun 2021 | Aug 2019 | Jun 2020
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201602 | EHC PARAPET & CORNER FACADE REHAB A,B,D,E, J AND O&G ANNEX. | 3 | CONSTRUCTION | Jul 2020 | Jun 2021 | Jul 2020 | Jun 2025
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201610 | RENOVATE JUNCTION BLVD CHILD HEALTH CLINIC | 1 | DESIGN | Aug 2017 | Jun 2018 | Aug 2017 | Jun 2018
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201610 | RENOVATE JUNCTION BLVD CHILD HEALTH CLINIC | 2 | CONSTRUCTION | Jul 2018 | Jun 2022 | Aug 2017 | Jun 2018
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201610 | RENOVATE JUNCTION BLVD CHILD HEALTH CLINIC | 3 | CONSTRUCTION | Jul 2018 | Jun 2022 | Jul 2018 | Jun 2026
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201804 | ELMHURST: REHABILITATE N & S STAIRWELLS IN PARKING GARAGE | 1 | DESIGN | Jul 2019 | Jan 2020 | Jul 2020 | Jan 2021
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201804 | ELMHURST: REHABILITATE N & S STAIRWELLS IN PARKING GARAGE | 2 | CONSTRUCTION | Jan 2020 | Jun 2020 | Jan 2021 | Jun 2032
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201901 | ELMHURST L&D ROOMS AND MFM UNIT SUITE RENOVATIONS | 1 | DESIGN | Jul 2019 | Jan 2020 | Jul 2019 | Jan 2020
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201901 | ELMHURST L&D ROOMS AND MFM UNIT SUITE RENOVATIONS | 2 | CONSTRUCTION | Jan 2020 | Jun 2022 | Jan 2020 | Jun 2025
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202002 | ELMHURST: CONSTRUCT AMBULATORY CENTER | 1 | DESIGN | Jul 2019 | Nov 2020 | Jul 2020 | Nov 2021
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202002 | ELMHURST: CONSTRUCT AMBULATORY CENTER | 2 | CONSTRUCTION | Nov 2020 | Nov 2023 | Nov 2021 | Nov 2024
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202002 | ELMHURST: CONSTRUCT AMBULATORY CENTER | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2023 | Feb 2024 | Nov 2024 | Feb 2025
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202003 | ELMHURST: Upgrade of Emergency Electrical System | 1 | DESIGN | Jul 2019 | Nov 2020 | Jul 2019 | Nov 2020
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202003 | ELMHURST: Upgrade of Emergency Electrical System | 2 | CONSTRUCTION | Nov 2020 | Nov 2023 | Nov 2020 | Nov 2023
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202003 | ELMHURST: Upgrade of Emergency Electrical System | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2023 | Feb 2024 | Nov 2023 | Feb 2024
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202102 | ELMHURST: MED SURG | 1 | DESIGN | May 2020 | Sep 2021 | May 2020 | Sep 2021
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202102 | ELMHURST: MED SURG | 2 | CONSTRUCTION | Sep 2021 | Sep 2023 | Oct 2021 | Sep 2023
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202102 | ELMHURST: MED SURG | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Dec 2023 | Oct 2023 | Dec 2023
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202103 | ELMHURST CATH LAB ROOF REPLACEMENT | 2 | CONSTRUCTION | Sep 2021 | Sep 2023 | Sep 2021 | Sep 2023
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202103 | ELMHURST CATH LAB ROOF REPLACEMENT | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Dec 2023 | Sep 2023 | Jun 2029
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202104 | ELMURST MODERNIZE FREIGHT ELEVATORS | 1 | DESIGN | May 2020 | Sep 2021 | May 2021 | Sep 2022
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202104 | ELMURST MODERNIZE FREIGHT ELEVATORS | 2 | CONSTRUCTION | Sep 2021 | Sep 2023 | Sep 2022 | Sep 2024
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202104 | ELMURST MODERNIZE FREIGHT ELEVATORS | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Dec 2023 | Sep 2024 | Jun 2025
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202111 | ELM A5: Certified Pediatric/NeoNatal ICU | 1 | DESIGN | Jan 2021 | Nov 2021 | Jan 2021 | Nov 2021
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202111 | ELM A5: Certified Pediatric/NeoNatal ICU | 2 | CONSTRUCTION | Nov 2021 | Nov 2022 | Jan 2021 | Nov 2021
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202111 | ELM A5: Certified Pediatric/NeoNatal ICU | 3 | CONSTRUCTION | Nov 2021 | Nov 2022 | Dec 2021 | Nov 2024
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202112 | ELMHURST ELEVATOR MODERNIZATION CARS 1-5, O & G | 1 | DESIGN | Jul 2020 | Nov 2021 | Jul 2021 | Nov 2022
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202112 | ELMHURST ELEVATOR MODERNIZATION CARS 1-5, O & G | 2 | CONSTRUCTION | Nov 2021 | Nov 2023 | Nov 2022 | Nov 2024
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202112 | ELMHURST ELEVATOR MODERNIZATION CARS 1-5, O & G | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2023 | Feb 2024 | Nov 2024 | Jun 2027
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202201 | ELMHURST CONVERSION OF CYSTO ROOMS TO FULL ORS | 1 | DESIGN | May 2021 | Sep 2022 | May 2022 | Jun 2028
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202201 | ELMHURST CONVERSION OF CYSTO ROOMS TO FULL ORS | 2 | CONSTRUCTION | Sep 2022 | Sep 2024 | Jul 2028 | Jun 2030
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202201 | ELMHURST CONVERSION OF CYSTO ROOMS TO FULL ORS | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Dec 2024 | Jul 2030 | Sep 2030
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202202 | ELM E1: Oncology Suite Renovation | 1 | DESIGN | May 2021 | Sep 2022 | May 2021 | Sep 2022
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202202 | ELM E1: Oncology Suite Renovation | 2 | CONSTRUCTION | Sep 2022 | Sep 2024 | Sep 2022 | Sep 2024
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202202 | ELM E1: Oncology Suite Renovation | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202203 | ELMHURST FIRE SYSTEMS UPGRADE | 1 | DESIGN | Dec 2021 | May 2023 | Dec 2021 | May 2023
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202203 | ELMHURST FIRE SYSTEMS UPGRADE | 2 | CONSTRUCTION | May 2023 | May 2026 | May 2023 | May 2026
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202203 | ELMHURST FIRE SYSTEMS UPGRADE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | May 2026 | Aug 2026 | May 2026 | Aug 2026
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202204 | ELM E4: NEURO CRITICAL CARE UNIT | 1 | DESIGN | Dec 2021 | May 2023 | Jan 2024 | May 2025
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202204 | ELM E4: NEURO CRITICAL CARE UNIT | 2 | CONSTRUCTION | May 2023 | May 2026 | May 2025 | May 2028
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202204 | ELM E4: NEURO CRITICAL CARE UNIT | 3 | PUNCHLIST COMPLETE, JOB CLOSED | May 2026 | Aug 2026 | May 2028 | Aug 2028
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202205 | ELMHURST ROOF REPLACEMENT (8 Roofs) | 1 | DESIGN | Dec 2021 | May 2023 | Dec 2021 | May 2023
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202205 | ELMHURST ROOF REPLACEMENT (8 Roofs) | 2 | CONSTRUCTION | May 2023 | May 2026 | May 2023 | May 2026
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202205 | ELMHURST ROOF REPLACEMENT (8 Roofs) | 3 | PUNCHLIST COMPLETE, JOB CLOSED | May 2026 | Aug 2026 | May 2026 | Aug 2026
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202207 | ELMHURST: ENTRY WAY RENOVATIONS | 1 | DESIGN | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202207 | ELMHURST: ENTRY WAY RENOVATIONS | 2 | CONSTRUCTION | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2024
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202301 | ELMHURST: Integrated Women's Health | 1 | DESIGN | Sep 2022 | Mar 2023 | Sep 2025 | Mar 2026
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202301 | ELMHURST: Integrated Women's Health | 2 | CONSTRUCTION | Mar 2023 | Jun 2024 | Mar 2026 | Jun 2030
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202302 | Elmhurst: Renovate J1 infectious disease clinic | 1 | DESIGN | Sep 2022 | Mar 2023 | Sep 2022 | Mar 2023
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202302 | Elmhurst: Renovate J1 infectious disease clinic | 2 | CONSTRUCTION | Mar 2023 | Jun 2024 | Mar 2023 | Jun 2024
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202303 | Elmhurst: Install New Cooling Tower | 1 | DESIGN | Sep 2022 | Mar 2023 | Sep 2023 | Mar 2024
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202303 | Elmhurst: Install New Cooling Tower | 2 | CONSTRUCTION | Mar 2023 | Jun 2024 | Mar 2024 | Jun 2027
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202402 | ELMHURST HOSPITAL CATH LAB--REPLACE CATH LAB 1 | 1 | DESIGN | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202402 | ELMHURST HOSPITAL CATH LAB--REPLACE CATH LAB 1 | 2 | CONSTRUCTION | Feb 2024 | Aug 2024 | Feb 2024 | Aug 2024
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202404 | ELMHURST HOSPITAL SURGICAL SUBSPECIALTIES SUITE--SURGICAL SU | 1 | DESIGN | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202404 | ELMHURST HOSPITAL SURGICAL SUBSPECIALTIES SUITE--SURGICAL SU | 2 | CONSTRUCTION | Feb 2024 | Aug 2026 | Feb 2024 | Aug 2026
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202405 | ELMHURST HOSPITAL NICU--NICU RELOCATION TO 5TH FLOOR | 1 | DESIGN | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202405 | ELMHURST HOSPITAL NICU--NICU RELOCATION TO 5TH FLOOR | 2 | CONSTRUCTION | Feb 2024 | Aug 2024 | Feb 2024 | Aug 2024
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202406 | ELMHURST HOSPITAL HAND UNIT-CONSTRUCT & OUTFIT | 1 | DESIGN | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202406 | ELMHURST HOSPITAL HAND UNIT-CONSTRUCT & OUTFIT | 2 | CONSTRUCTION | Feb 2024 | Aug 2026 | Feb 2024 | Aug 2026
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34200304 | QUEENS EXPANSION OF DIABETES CENTER | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201401 | QUEENS RENOVATIONS TO RELOCATE ACUTE DIALYSIS PROG. | 1 | DESIGN | Jan 2015 | Jul 2015 | Jan 2016 | Jul 2016
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201401 | QUEENS RENOVATIONS TO RELOCATE ACUTE DIALYSIS PROG. | 2 | CONSTRUCTION | Jul 2015 | Dec 2015 | Jul 2016 | Jun 2032
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201402 | QUEENS RENOVATE/EXPAND ADULT EMERGENCY DEPARTMENT | 1 | DESIGN | Apr 2015 | Oct 2015 | Apr 2015 | Oct 2015
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201402 | QUEENS RENOVATE/EXPAND ADULT EMERGENCY DEPARTMENT | 2 | CONSTRUCTION | Oct 2015 | Mar 2016 | Oct 2015 | Jun 2026
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201502 | QUEENS BOILER CONTROLS REPLACEMENT | 1 | DESIGN | Jul 2019 | Jan 2020 | Jul 2020 | Jan 2021
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201502 | QUEENS BOILER CONTROLS REPLACEMENT | 2 | CONSTRUCTION | Jan 2020 | Jun 2020 | Jan 2021 | Jun 2032
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201503 | QUEENS EXPAND AND RENOVATE PHARMACY | 1 | DESIGN | Jul 2019 | Jan 2020 | Jul 2022 | Jan 2023
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201503 | QUEENS EXPAND AND RENOVATE PHARMACY | 2 | CONSTRUCTION | Jan 2020 | Jun 2020 | Jan 2023 | Jun 2032
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201741 | QHC: IR SUITE RENOVATION | 1 | DESIGN | Dec 2021 | Jun 2022 | Dec 2021 | Jun 2022
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201741 | QHC: IR SUITE RENOVATION | 2 | CONSTRUCTION | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2024
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201901 | QUEENS SIDEWALK REPLACEMENT | 1 | DESIGN | Jul 2018 | Jan 2019 | Jul 2018 | Jan 2019
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201901 | QUEENS SIDEWALK REPLACEMENT | 2 | CONSTRUCTION | Jan 2019 | Jun 2019 | Jan 2019 | Jun 2019
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34202101 | QUEENS CONSTRUCT PARKING GARAGE | 1 | DESIGN | May 2020 | Sep 2021 | May 2020 | Sep 2021
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34202101 | QUEENS CONSTRUCT PARKING GARAGE | 2 | CONSTRUCTION | Sep 2021 | Sep 2023 | Sep 2021 | Sep 2023
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34202101 | QUEENS CONSTRUCT PARKING GARAGE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Dec 2023 | Sep 2023 | Dec 2027
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34202102 | QUEENS BUILDING F ROOF REPLACEMENT | 1 | DESIGN | May 2020 | Sep 2021 | May 2023 | Sep 2024
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34202102 | QUEENS BUILDING F ROOF REPLACEMENT | 2 | CONSTRUCTION | Sep 2021 | Sep 2023 | Sep 2024 | Sep 2026
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34202102 | QUEENS BUILDING F ROOF REPLACEMENT | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Dec 2023 | Sep 2026 | Dec 2028
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34202201 | QUEENS ADULT EMERGENCY ROOM OBSERVATION UNIT RENOVATIONS | 1 | DESIGN | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34202201 | QUEENS ADULT EMERGENCY ROOM OBSERVATION UNIT RENOVATIONS | 2 | CONSTRUCTION | Dec 2022 | Jun 2023 | Jan 2023 | Jun 2025
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34202301 | QUEENS: Dialysis Space Construction | 1 | DESIGN | Jun 2024 | Dec 2024 | Jun 2024 | Dec 2024
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34202301 | QUEENS: Dialysis Space Construction | 2 | CONSTRUCTION | Dec 2024 | May 2025 | Jan 2025 | Jun 2025
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34202302 | Queens Hospital: MRI Purchase and Renovation | 1 | DESIGN | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34202302 | Queens Hospital: MRI Purchase and Renovation | 2 | CONSTRUCTION | Feb 2024 | Aug 2024 | Feb 2024 | Aug 2024
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34202305 | Queens T-Building Basement Fit-Out | 1 | DESIGN | Jun 2023 | Dec 2023 | Jun 2023 | Dec 2023
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34202305 | Queens T-Building Basement Fit-Out | 2 | CONSTRUCTION | Dec 2023 | Jun 2024 | Jan 2024 | Jun 2024
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 60202201 | GOTHAM - Far Rockaway Primary Care Center | 1 | DESIGN | Jul 2022 | Dec 2022 | Jul 2023 | Dec 2023
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 60202201 | GOTHAM - Far Rockaway Primary Care Center | 2 | CONSTRUCTION | Dec 2022 | Jun 2023 | Dec 2023 | Jun 2025
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 69202101 | NEPONSIT DEMOLITION, RESTORATION AND NEW LIFE GUARD FACILITY | 1 | DESIGN | May 2021 | Sep 2022 | Apr 2024 | Sep 2025
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 69202101 | NEPONSIT DEMOLITION, RESTORATION AND NEW LIFE GUARD FACILITY | 2 | CONSTRUCTION | Sep 2022 | Sep 2024 | Sep 2025 | Sep 2027
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 69202101 | NEPONSIT DEMOLITION, RESTORATION AND NEW LIFE GUARD FACILITY | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Dec 2024 | Sep 2027 | Dec 2027
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 71202301 | PARSONS: SPACE MODERNIZATION FOR DENTAL, OPTOMETRY, AND PC | 1 | DESIGN | Apr 2023 | Sep 2024 | Apr 2023 | Sep 2024
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 71202301 | PARSONS: SPACE MODERNIZATION FOR DENTAL, OPTOMETRY, AND PC | 2 | CONSTRUCTION | Sep 2024 | Sep 2027 | Sep 2024 | Sep 2027
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 71202301 | PARSONS: SPACE MODERNIZATION FOR DENTAL, OPTOMETRY, AND PC | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Dec 2027 | Sep 2027 | Dec 2027
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 73202301 | SPRINGFIELD: AIR HANDLING UNIT- HVAC ROOF TOP UNIT | 1 | DESIGN | Apr 2023 | Sep 2024 | Apr 2023 | Sep 2024
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 73202301 | SPRINGFIELD: AIR HANDLING UNIT- HVAC ROOF TOP UNIT | 2 | CONSTRUCTION | Sep 2024 | Sep 2027 | Sep 2024 | Sep 2027
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 73202301 | SPRINGFIELD: AIR HANDLING UNIT- HVAC ROOF TOP UNIT | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Dec 2027 | Sep 2027 | Dec 2027
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 77202301 | WOODSIDE: SPACE MODERNIZATION FOR ADMINISTRATIVE OFFICES | 1 | DESIGN | Apr 2023 | Sep 2024 | Apr 2023 | Sep 2024
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 77202301 | WOODSIDE: SPACE MODERNIZATION FOR ADMINISTRATIVE OFFICES | 2 | CONSTRUCTION | Sep 2024 | Sep 2027 | Sep 2024 | Sep 2027
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 77202301 | WOODSIDE: SPACE MODERNIZATION FOR ADMINISTRATIVE OFFICES | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Dec 2027 | Sep 2027 | Dec 2027
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 78202301 | SOUTH QUEENS: HVAC MODERNIZATION | 1 | DESIGN | Apr 2023 | Sep 2024 | Apr 2023 | Sep 2024
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 78202301 | SOUTH QUEENS: HVAC MODERNIZATION | 2 | CONSTRUCTION | Sep 2024 | Sep 2027 | Sep 2024 | Sep 2027
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 78202301 | SOUTH QUEENS: HVAC MODERNIZATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Dec 2027 | Sep 2027 | Dec 2027
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | ACEHHC803 | QUEENS: ENERGY EFFICIENCY UPGRADES | 1 | DESIGN | May 2020 | Oct 2021 | May 2020 | Oct 2021
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | ACEHHC803 | QUEENS: ENERGY EFFICIENCY UPGRADES | 2 | CONSTRUCTION | Oct 2021 | Oct 2024 | Oct 2021 | Oct 2024
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | ACEHHC803 | QUEENS: ENERGY EFFICIENCY UPGRADES | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | ACEHHC902 | QUEENS ENERGY UPGRADES- N BUILDING | 1 | DEVELOP SCOPE | Mar 2021 | Mar 2021 | Mar 2021 | Mar 2021
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | ACEHHC902 | QUEENS ENERGY UPGRADES- N BUILDING | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2021 | May 2021 | Mar 2021 | May 2021
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | ACEHHC902 | QUEENS ENERGY UPGRADES- N BUILDING | 3 | CONSTRUCTION TO 50% | May 2021 | Nov 2021 | May 2021 | Nov 2021
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | ACEHHC902 | QUEENS ENERGY UPGRADES- N BUILDING | 4 | CONSTRUCTION TO 75% | Nov 2021 | Feb 2022 | Nov 2021 | Feb 2022
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | ACEHHC902 | QUEENS ENERGY UPGRADES- N BUILDING | 5 | SUBSTANTIAL COMPLETION | Feb 2022 | Apr 2022 | Feb 2022 | Apr 2022
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | ACEHHC902 | QUEENS ENERGY UPGRADES- N BUILDING | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2022 | May 2022 | Apr 2022 | Jun 2025
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | TKYHHC014 | QUEENS: LIGHTING UPGRADE | 1 | DESIGN | Apr 2023 | Sep 2024 | Apr 2023 | Sep 2024
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | TKYHHC014 | QUEENS: LIGHTING UPGRADE | 2 | CONSTRUCTION | Sep 2024 | Sep 2026 | Sep 2024 | Sep 2026
20231026 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | TKYHHC014 | QUEENS: LIGHTING UPGRADE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Dec 2026 | Sep 2026 | Dec 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP601 | DEP - LED LIGHTING AT CATSKILL DELAWARE UV FACILITY | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2020 | Jun 2021 | Nov 2022
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP601 | DEP - LED LIGHTING AT CATSKILL DELAWARE UV FACILITY | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Aug 2020 | Nov 2022 | Nov 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP601 | DEP - LED LIGHTING AT CATSKILL DELAWARE UV FACILITY | 3 | CONSTRUCTION TO 50% | Aug 2020 | Feb 2021 | Nov 2023 | Nov 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP601 | DEP - LED LIGHTING AT CATSKILL DELAWARE UV FACILITY | 4 | CONSTRUCTION TO 75% | Feb 2021 | May 2021 | Nov 2024 | Nov 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP601 | DEP - LED LIGHTING AT CATSKILL DELAWARE UV FACILITY | 5 | SUBSTANTIAL COMPLETION | May 2021 | Jul 2021 | Nov 2024 | Nov 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP601 | DEP - LED LIGHTING AT CATSKILL DELAWARE UV FACILITY | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Aug 2021 | Nov 2024 | Nov 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-215-L | POWER DISTRIBUTION AT BOWERY BAY WPCP | 1 | DEVELOP SCOPE | Jun 2015 | Sep 2015 | Jun 2015 | Mar 2016
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-215-L | POWER DISTRIBUTION AT BOWERY BAY WPCP | 2 | PRELIMINARY DESIGN | Sep 2015 | Jan 2016 | Mar 2016 | Mar 2017
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-215-L | POWER DISTRIBUTION AT BOWERY BAY WPCP | 3 | FINAL DESIGN | Jan 2016 | Jul 2016 | Mar 2017 | Sep 2018
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-215-L | POWER DISTRIBUTION AT BOWERY BAY WPCP | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Oct 2016 | Sep 2018 | Jun 2019
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-215-L | POWER DISTRIBUTION AT BOWERY BAY WPCP | 5 | CONSTRUCTION TO 25% | Oct 2016 | Feb 2017 | Jun 2019 | Jun 2020
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-215-L | POWER DISTRIBUTION AT BOWERY BAY WPCP | 6 | CONSTRUCTION TO 50% | Feb 2017 | Jun 2017 | Jun 2020 | May 2021
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-215-L | POWER DISTRIBUTION AT BOWERY BAY WPCP | 7 | CONSTRUCTION TO 75% | Jun 2017 | Oct 2017 | May 2021 | May 2022
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-215-L | POWER DISTRIBUTION AT BOWERY BAY WPCP | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2017 | Jan 2018 | May 2022 | Feb 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-215-L | POWER DISTRIBUTION AT BOWERY BAY WPCP | 9 | SUBSTANTIAL COMPLETION | Jan 2018 | Mar 2018 | Feb 2023 | Aug 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-215-L | POWER DISTRIBUTION AT BOWERY BAY WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2018 | Apr 2018 | Aug 2023 | Nov 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-216-L | RECONSTRUCTION OF PRIMARY TANKS AT BOWERY BAY WPCP | 1 | DEVELOP SCOPE | Jul 2017 | Sep 2017 | Jan 2019 | Oct 2019
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-216-L | RECONSTRUCTION OF PRIMARY TANKS AT BOWERY BAY WPCP | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Oct 2019 | Oct 2020
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-216-L | RECONSTRUCTION OF PRIMARY TANKS AT BOWERY BAY WPCP | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Oct 2020 | Mar 2022
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-216-L | RECONSTRUCTION OF PRIMARY TANKS AT BOWERY BAY WPCP | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Mar 2022 | Dec 2022
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-216-L | RECONSTRUCTION OF PRIMARY TANKS AT BOWERY BAY WPCP | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Dec 2022 | Dec 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-216-L | RECONSTRUCTION OF PRIMARY TANKS AT BOWERY BAY WPCP | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Dec 2023 | Dec 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-216-L | RECONSTRUCTION OF PRIMARY TANKS AT BOWERY BAY WPCP | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Dec 2024 | Dec 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-216-L | RECONSTRUCTION OF PRIMARY TANKS AT BOWERY BAY WPCP | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Dec 2025 | Sep 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-216-L | RECONSTRUCTION OF PRIMARY TANKS AT BOWERY BAY WPCP | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Sep 2026 | Mar 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-216-L | RECONSTRUCTION OF PRIMARY TANKS AT BOWERY BAY WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Mar 2027 | Jun 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-220-L | REPLACEMENT OF EXISTING EMERGENCY GENERATORS @ BOWERY BAY | 1 | DEVELOP SCOPE | Jul 2017 | Sep 2017 | Jul 2022 | Sep 2022
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-220-L | REPLACEMENT OF EXISTING EMERGENCY GENERATORS @ BOWERY BAY | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2022 | Jan 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-220-L | REPLACEMENT OF EXISTING EMERGENCY GENERATORS @ BOWERY BAY | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jan 2023 | Jul 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-220-L | REPLACEMENT OF EXISTING EMERGENCY GENERATORS @ BOWERY BAY | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2023 | Oct 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-220-L | REPLACEMENT OF EXISTING EMERGENCY GENERATORS @ BOWERY BAY | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Oct 2023 | Feb 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-220-L | REPLACEMENT OF EXISTING EMERGENCY GENERATORS @ BOWERY BAY | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Feb 2024 | Jun 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-220-L | REPLACEMENT OF EXISTING EMERGENCY GENERATORS @ BOWERY BAY | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jun 2024 | Oct 2030
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-220-L | REPLACEMENT OF EXISTING EMERGENCY GENERATORS @ BOWERY BAY | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Oct 2030 | Jan 2031
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-220-L | REPLACEMENT OF EXISTING EMERGENCY GENERATORS @ BOWERY BAY | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jan 2031 | Mar 2031
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-220-L | REPLACEMENT OF EXISTING EMERGENCY GENERATORS @ BOWERY BAY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Mar 2031 | Apr 2031
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-236-L | RECONSTRUCTION OF GRIT WASHERS @ THE BOWERY BAY WWTP | 1 | FINAL DESIGN | Jun 2019 | Nov 2020 | Jun 2019 | Feb 2020
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-236-L | RECONSTRUCTION OF GRIT WASHERS @ THE BOWERY BAY WWTP | 2 | CONSTRUCTION TO 25% | Nov 2020 | Jul 2021 | Feb 2020 | Feb 2021
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-236-L | RECONSTRUCTION OF GRIT WASHERS @ THE BOWERY BAY WWTP | 3 | CONSTRUCTION TO 50% | Jul 2021 | Mar 2022 | Feb 2021 | Aug 2022
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-236-L | RECONSTRUCTION OF GRIT WASHERS @ THE BOWERY BAY WWTP | 4 | CONSTRUCTION TO 75% | Mar 2022 | Nov 2022 | Aug 2022 | May 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-236-L | RECONSTRUCTION OF GRIT WASHERS @ THE BOWERY BAY WWTP | 5 | CONSTRUCTION TO 25% | Mar 2022 | Nov 2022 | May 2023 | May 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-236-L | RECONSTRUCTION OF GRIT WASHERS @ THE BOWERY BAY WWTP | 6 | CONSTRUCTION TO 50% | Mar 2022 | Nov 2022 | May 2024 | Apr 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-236-L | RECONSTRUCTION OF GRIT WASHERS @ THE BOWERY BAY WWTP | 7 | CONSTRUCTION TO 75% | Mar 2022 | Nov 2022 | Apr 2025 | Apr 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-236-L | RECONSTRUCTION OF GRIT WASHERS @ THE BOWERY BAY WWTP | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2022 | Nov 2022 | Apr 2026 | Jan 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-236-L | RECONSTRUCTION OF GRIT WASHERS @ THE BOWERY BAY WWTP | 9 | SUBSTANTIAL COMPLETION | Mar 2022 | Nov 2022 | Jan 2027 | Jul 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-236-L | RECONSTRUCTION OF GRIT WASHERS @ THE BOWERY BAY WWTP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Nov 2022 | Jul 2027 | Oct 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-237-L | RECONS CROSS COLLECTOR SYS & SUCTION PIPING @ BOWERY BAY | 1 | DEVELOP SCOPE | Jun 2019 | Aug 2019 | Jun 2019 | Feb 2020
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-237-L | RECONS CROSS COLLECTOR SYS & SUCTION PIPING @ BOWERY BAY | 2 | PRELIMINARY DESIGN | Aug 2019 | Dec 2019 | Feb 2020 | Feb 2021
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-237-L | RECONS CROSS COLLECTOR SYS & SUCTION PIPING @ BOWERY BAY | 3 | FINAL DESIGN | Dec 2019 | Jun 2020 | Feb 2021 | Aug 2022
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-237-L | RECONS CROSS COLLECTOR SYS & SUCTION PIPING @ BOWERY BAY | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Sep 2020 | Aug 2022 | May 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-237-L | RECONS CROSS COLLECTOR SYS & SUCTION PIPING @ BOWERY BAY | 5 | CONSTRUCTION TO 25% | Sep 2020 | Jan 2021 | May 2023 | May 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-237-L | RECONS CROSS COLLECTOR SYS & SUCTION PIPING @ BOWERY BAY | 6 | CONSTRUCTION TO 50% | Jan 2021 | May 2021 | May 2024 | Apr 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-237-L | RECONS CROSS COLLECTOR SYS & SUCTION PIPING @ BOWERY BAY | 7 | CONSTRUCTION TO 75% | May 2021 | Sep 2021 | Apr 2025 | Apr 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-237-L | RECONS CROSS COLLECTOR SYS & SUCTION PIPING @ BOWERY BAY | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Dec 2021 | Apr 2026 | Jan 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-237-L | RECONS CROSS COLLECTOR SYS & SUCTION PIPING @ BOWERY BAY | 9 | SUBSTANTIAL COMPLETION | Dec 2021 | Feb 2022 | Jan 2027 | Jul 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-237-L | RECONS CROSS COLLECTOR SYS & SUCTION PIPING @ BOWERY BAY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2022 | Mar 2022 | Jul 2027 | Oct 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | C540 | Completion of CT3 Stage 2 B/Q Leg & Bklyn Downtake Intercon. | 1 | DEVELOP SCOPE | Jul 2007 | Apr 2008 | Jun 2017 | Mar 2018
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | C540 | Completion of CT3 Stage 2 B/Q Leg & Bklyn Downtake Intercon. | 2 | PRELIMINARY DESIGN | Apr 2008 | Apr 2009 | Mar 2018 | Mar 2019
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | C540 | Completion of CT3 Stage 2 B/Q Leg & Bklyn Downtake Intercon. | 3 | FINAL DESIGN | Apr 2009 | Sep 2010 | Mar 2019 | Aug 2020
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | C540 | Completion of CT3 Stage 2 B/Q Leg & Bklyn Downtake Intercon. | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2010 | Jun 2011 | Aug 2020 | May 2021
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | C540 | Completion of CT3 Stage 2 B/Q Leg & Bklyn Downtake Intercon. | 5 | CONSTRUCTION TO 25% | Jun 2011 | Jun 2012 | May 2021 | May 2022
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | C540 | Completion of CT3 Stage 2 B/Q Leg & Bklyn Downtake Intercon. | 6 | CONSTRUCTION TO 50% | Jun 2012 | Jun 2013 | May 2022 | May 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | C540 | Completion of CT3 Stage 2 B/Q Leg & Bklyn Downtake Intercon. | 7 | CONSTRUCTION TO 75% | Jun 2013 | Jun 2014 | May 2023 | May 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | C540 | Completion of CT3 Stage 2 B/Q Leg & Bklyn Downtake Intercon. | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2014 | Mar 2015 | May 2024 | Feb 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | C540 | Completion of CT3 Stage 2 B/Q Leg & Bklyn Downtake Intercon. | 9 | SUBSTANTIAL COMPLETION | Mar 2015 | Aug 2015 | Feb 2025 | Aug 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | C540 | Completion of CT3 Stage 2 B/Q Leg & Bklyn Downtake Intercon. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2015 | Nov 2015 | Aug 2025 | Nov 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-QE24 | Replacing substandard catch basins with upgraded designs QNS | 1 | DEVELOP SCOPE | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-QE24 | Replacing substandard catch basins with upgraded designs QNS | 2 | PRELIMINARY DESIGN | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-QE24 | Replacing substandard catch basins with upgraded designs QNS | 3 | FINAL DESIGN | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-QE24 | Replacing substandard catch basins with upgraded designs QNS | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2024 | Feb 2025 | Nov 2024 | Feb 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-QE24 | Replacing substandard catch basins with upgraded designs QNS | 5 | CONSTRUCTION TO 25% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-QE24 | Replacing substandard catch basins with upgraded designs QNS | 6 | CONSTRUCTION TO 50% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-QE24 | Replacing substandard catch basins with upgraded designs QNS | 7 | CONSTRUCTION TO 75% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-QE24 | Replacing substandard catch basins with upgraded designs QNS | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2026 | May 2026 | Feb 2026 | May 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-QE24 | Replacing substandard catch basins with upgraded designs QNS | 9 | SUBSTANTIAL COMPLETION | May 2026 | Jul 2026 | May 2026 | Jul 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-QE24 | Replacing substandard catch basins with upgraded designs QNS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2026 | Aug 2026 | Jul 2026 | Aug 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-QW24 | Replacing substandard catch basins with upgraded design QNSW | 1 | DEVELOP SCOPE | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-QW24 | Replacing substandard catch basins with upgraded design QNSW | 2 | PRELIMINARY DESIGN | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-QW24 | Replacing substandard catch basins with upgraded design QNSW | 3 | FINAL DESIGN | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-QW24 | Replacing substandard catch basins with upgraded design QNSW | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2024 | Feb 2025 | Nov 2024 | Feb 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-QW24 | Replacing substandard catch basins with upgraded design QNSW | 5 | CONSTRUCTION TO 25% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-QW24 | Replacing substandard catch basins with upgraded design QNSW | 6 | CONSTRUCTION TO 50% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-QW24 | Replacing substandard catch basins with upgraded design QNSW | 7 | CONSTRUCTION TO 75% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-QW24 | Replacing substandard catch basins with upgraded design QNSW | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2026 | May 2026 | Feb 2026 | May 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-QW24 | Replacing substandard catch basins with upgraded design QNSW | 9 | SUBSTANTIAL COMPLETION | May 2026 | Jul 2026 | May 2026 | Jul 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CB-QW24 | Replacing substandard catch basins with upgraded design QNSW | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2026 | Aug 2026 | Jul 2026 | Aug 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-BAP | BORDEN AVENUE PUMP STATION EXPANSION | 1 | DEVELOP SCOPE | May 2020 | Jan 2021 | May 2020 | Jan 2021
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-BAP | BORDEN AVENUE PUMP STATION EXPANSION | 2 | PRELIMINARY DESIGN | Jan 2021 | Jan 2022 | Jan 2021 | Jan 2022
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-BAP | BORDEN AVENUE PUMP STATION EXPANSION | 3 | FINAL DESIGN | Jan 2022 | Jul 2023 | Jan 2022 | Jul 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-BAP | BORDEN AVENUE PUMP STATION EXPANSION | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Apr 2024 | Jul 2023 | Apr 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-BAP | BORDEN AVENUE PUMP STATION EXPANSION | 5 | CONSTRUCTION TO 25% | Apr 2024 | Apr 2025 | Apr 2024 | Apr 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-BAP | BORDEN AVENUE PUMP STATION EXPANSION | 6 | CONSTRUCTION TO 50% | Apr 2025 | Mar 2026 | Apr 2025 | Mar 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-BAP | BORDEN AVENUE PUMP STATION EXPANSION | 7 | CONSTRUCTION TO 75% | Mar 2026 | Mar 2027 | Mar 2026 | Mar 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-BAP | BORDEN AVENUE PUMP STATION EXPANSION | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2027 | Dec 2027 | Mar 2027 | Dec 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-BAP | BORDEN AVENUE PUMP STATION EXPANSION | 9 | SUBSTANTIAL COMPLETION | Dec 2027 | Jun 2028 | Dec 2027 | Jun 2028
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-BAP | BORDEN AVENUE PUMP STATION EXPANSION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2028 | Sep 2028 | Jun 2028 | Sep 2028
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-CST | NEWTOWN CREEK CSO STORAGE TUNNEL | 1 | DEVELOP SCOPE | Jun 2013 | Mar 2014 | Jul 2022 | Mar 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-CST | NEWTOWN CREEK CSO STORAGE TUNNEL | 2 | PRELIMINARY DESIGN | Mar 2014 | Mar 2015 | Oct 2005 | Oct 2006
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-CST | NEWTOWN CREEK CSO STORAGE TUNNEL | 3 | FINAL DESIGN | Mar 2015 | Aug 2016 | Oct 2006 | Apr 2008
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-CST | NEWTOWN CREEK CSO STORAGE TUNNEL | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2016 | May 2017 | Apr 2008 | Dec 2008
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-CST | NEWTOWN CREEK CSO STORAGE TUNNEL | 5 | CONSTRUCTION TO 25% | May 2017 | May 2018 | Dec 2008 | Dec 2009
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-CST | NEWTOWN CREEK CSO STORAGE TUNNEL | 6 | CONSTRUCTION TO 50% | May 2018 | May 2019 | Dec 2009 | Dec 2010
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-CST | NEWTOWN CREEK CSO STORAGE TUNNEL | 7 | CONSTRUCTION TO 75% | May 2019 | May 2020 | Dec 2010 | Dec 2011
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-CST | NEWTOWN CREEK CSO STORAGE TUNNEL | 8 | ORIGINAL EQUIP & FURNISHING | May 2020 | Feb 2021 | Dec 2011 | Sep 2012
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-CST | NEWTOWN CREEK CSO STORAGE TUNNEL | 9 | SUBSTANTIAL COMPLETION | Feb 2021 | Aug 2021 | Sep 2012 | Mar 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-CST | NEWTOWN CREEK CSO STORAGE TUNNEL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Oct 2021 | Mar 2025 | Jun 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-CST | NEWTOWN CREEK CSO STORAGE TUNNEL | 11 | PRE-CONSTRUCTION MOBILIZATION | Aug 2021 | Oct 2021 | Jun 2025 | May 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-CST | NEWTOWN CREEK CSO STORAGE TUNNEL | 12 | ON-SITE CONSTRUCTION MANAGEMEN | Aug 2021 | Oct 2021 | May 2026 | Apr 2032
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-CST | NEWTOWN CREEK CSO STORAGE TUNNEL | 13 | POST-CONSTRUCTION CLOSE-OUT | Aug 2021 | Oct 2021 | Apr 2032 | Apr 2033
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-EKE | ENGLISH KILLS AERATION BORDEN AVE PUMP STATION UPGRADE | 1 | DEVELOP SCOPE | Jun 2013 | Mar 2014 | Jan 2000 | Oct 2000
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-EKE | ENGLISH KILLS AERATION BORDEN AVE PUMP STATION UPGRADE | 2 | PRELIMINARY DESIGN | Mar 2014 | Mar 2015 | Oct 2000 | Sep 2003
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-EKE | ENGLISH KILLS AERATION BORDEN AVE PUMP STATION UPGRADE | 3 | FINAL DESIGN | Mar 2015 | Aug 2016 | Sep 2003 | Aug 2009
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-EKE | ENGLISH KILLS AERATION BORDEN AVE PUMP STATION UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2016 | May 2017 | Aug 2009 | Dec 2014
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-EKE | ENGLISH KILLS AERATION BORDEN AVE PUMP STATION UPGRADE | 5 | CONSTRUCTION TO 25% | May 2017 | May 2018 | Dec 2014 | Jan 2021
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-EKE | ENGLISH KILLS AERATION BORDEN AVE PUMP STATION UPGRADE | 6 | CONSTRUCTION TO 50% | May 2018 | May 2019 | Jan 2021 | Mar 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-EKE | ENGLISH KILLS AERATION BORDEN AVE PUMP STATION UPGRADE | 7 | CONSTRUCTION TO 75% | May 2019 | May 2020 | Mar 2023 | Jun 2028
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-EKE | ENGLISH KILLS AERATION BORDEN AVE PUMP STATION UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | May 2020 | Feb 2021 | Jun 2028 | Jun 2029
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-EKE | ENGLISH KILLS AERATION BORDEN AVE PUMP STATION UPGRADE | 9 | SUBSTANTIAL COMPLETION | Feb 2021 | Aug 2021 | Jun 2029 | Oct 2030
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-EKE | ENGLISH KILLS AERATION BORDEN AVE PUMP STATION UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Oct 2021 | Oct 2030 | Jun 2031
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-FC-DF | CSO FLUSHING CREEK & TI-011 DISINFECTION | 1 | DEVELOP SCOPE | Jul 2017 | Mar 2018 | Jul 2017 | Mar 2018
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-FC-DF | CSO FLUSHING CREEK & TI-011 DISINFECTION | 2 | PRELIMINARY DESIGN | Mar 2018 | Mar 2019 | Mar 2018 | Mar 2019
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-FC-DF | CSO FLUSHING CREEK & TI-011 DISINFECTION | 3 | FINAL DESIGN | Mar 2019 | Sep 2020 | Mar 2019 | Sep 2020
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-FC-DF | CSO FLUSHING CREEK & TI-011 DISINFECTION | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2020 | Jun 2021 | Sep 2020 | Jun 2021
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-FC-DF | CSO FLUSHING CREEK & TI-011 DISINFECTION | 5 | CONSTRUCTION TO 25% | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-FC-DF | CSO FLUSHING CREEK & TI-011 DISINFECTION | 6 | CONSTRUCTION TO 50% | Jun 2022 | May 2023 | Jun 2022 | May 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-FC-DF | CSO FLUSHING CREEK & TI-011 DISINFECTION | 7 | CONSTRUCTION TO 75% | May 2023 | May 2024 | May 2023 | May 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-FC-DF | CSO FLUSHING CREEK & TI-011 DISINFECTION | 8 | ORIGINAL EQUIP & FURNISHING | May 2024 | Feb 2025 | May 2024 | Feb 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-FC-DF | CSO FLUSHING CREEK & TI-011 DISINFECTION | 9 | SUBSTANTIAL COMPLETION | Feb 2025 | Aug 2025 | Feb 2025 | Aug 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-FC-DF | CSO FLUSHING CREEK & TI-011 DISINFECTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2025 | Nov 2025 | Aug 2025 | Nov 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | DMCCSG | REPLACE SWITCHEARS & MCCS AT DOUGLASTON PS | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Mar 2016
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | DMCCSG | REPLACE SWITCHEARS & MCCS AT DOUGLASTON PS | 2 | PRELIMINARY DESIGN | Sep 2015 | Jan 2016 | Mar 2016 | Mar 2017
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | DMCCSG | REPLACE SWITCHEARS & MCCS AT DOUGLASTON PS | 3 | FINAL DESIGN | Jan 2016 | Jul 2016 | Mar 2017 | Sep 2018
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | DMCCSG | REPLACE SWITCHEARS & MCCS AT DOUGLASTON PS | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Oct 2016 | Sep 2018 | Jun 2019
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | DMCCSG | REPLACE SWITCHEARS & MCCS AT DOUGLASTON PS | 5 | CONSTRUCTION TO 25% | Oct 2016 | Feb 2017 | Jun 2019 | Jun 2020
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | DMCCSG | REPLACE SWITCHEARS & MCCS AT DOUGLASTON PS | 6 | CONSTRUCTION TO 50% | Feb 2017 | Jun 2017 | Jun 2020 | May 2021
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | DMCCSG | REPLACE SWITCHEARS & MCCS AT DOUGLASTON PS | 7 | CONSTRUCTION TO 75% | Jun 2017 | Oct 2017 | May 2021 | May 2022
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | DMCCSG | REPLACE SWITCHEARS & MCCS AT DOUGLASTON PS | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2017 | Jan 2018 | May 2022 | Feb 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | DMCCSG | REPLACE SWITCHEARS & MCCS AT DOUGLASTON PS | 9 | SUBSTANTIAL COMPLETION | Jan 2018 | Mar 2018 | Feb 2023 | Aug 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | DMCCSG | REPLACE SWITCHEARS & MCCS AT DOUGLASTON PS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2018 | Apr 2018 | Aug 2023 | Nov 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQN25 | Reconstruction of Existing Sewers, North Queens | 1 | DEVELOP SCOPE | Jan 2023 | Apr 2023 | Jan 2023 | Apr 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQN25 | Reconstruction of Existing Sewers, North Queens | 2 | PRELIMINARY DESIGN | Apr 2023 | Aug 2023 | Apr 2023 | Aug 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQN25 | Reconstruction of Existing Sewers, North Queens | 3 | FINAL DESIGN | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQN25 | Reconstruction of Existing Sewers, North Queens | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2024 | May 2024 | Feb 2024 | May 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQN25 | Reconstruction of Existing Sewers, North Queens | 5 | CONSTRUCTION TO 25% | May 2024 | Aug 2024 | May 2024 | Aug 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQN25 | Reconstruction of Existing Sewers, North Queens | 6 | CONSTRUCTION TO 50% | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQN25 | Reconstruction of Existing Sewers, North Queens | 7 | CONSTRUCTION TO 75% | Dec 2024 | Apr 2025 | Dec 2024 | Apr 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQN25 | Reconstruction of Existing Sewers, North Queens | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2025 | Jul 2025 | Apr 2025 | Jul 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQN25 | Reconstruction of Existing Sewers, North Queens | 9 | SUBSTANTIAL COMPLETION | Jul 2025 | Sep 2025 | Jul 2025 | Sep 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQN25 | Reconstruction of Existing Sewers, North Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Oct 2025 | Sep 2025 | Oct 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQS25 | Reconstruction of Existing Sewers, South Queens | 1 | DEVELOP SCOPE | Jan 2023 | Apr 2023 | Jan 2023 | Apr 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQS25 | Reconstruction of Existing Sewers, South Queens | 2 | PRELIMINARY DESIGN | Apr 2023 | Aug 2023 | Apr 2023 | Aug 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQS25 | Reconstruction of Existing Sewers, South Queens | 3 | FINAL DESIGN | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQS25 | Reconstruction of Existing Sewers, South Queens | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2024 | May 2024 | Feb 2024 | May 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQS25 | Reconstruction of Existing Sewers, South Queens | 5 | CONSTRUCTION TO 25% | May 2024 | Aug 2024 | May 2024 | Aug 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQS25 | Reconstruction of Existing Sewers, South Queens | 6 | CONSTRUCTION TO 50% | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQS25 | Reconstruction of Existing Sewers, South Queens | 7 | CONSTRUCTION TO 75% | Dec 2024 | Apr 2025 | Dec 2024 | Apr 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQS25 | Reconstruction of Existing Sewers, South Queens | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2025 | Jul 2025 | Apr 2025 | Jul 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQS25 | Reconstruction of Existing Sewers, South Queens | 9 | SUBSTANTIAL COMPLETION | Jul 2025 | Sep 2025 | Jul 2025 | Sep 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQS25 | Reconstruction of Existing Sewers, South Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Oct 2025 | Sep 2025 | Oct 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FCWET | CONSTRUCTION OF FLUSHING CREEK WETLAND PROJECT | 1 | DEVELOP SCOPE | Jun 2022 | Mar 2023 | Jun 2022 | Mar 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FCWET | CONSTRUCTION OF FLUSHING CREEK WETLAND PROJECT | 2 | PRELIMINARY DESIGN | Mar 2023 | Mar 2024 | Mar 2023 | Mar 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FCWET | CONSTRUCTION OF FLUSHING CREEK WETLAND PROJECT | 3 | FINAL DESIGN | Mar 2024 | Aug 2025 | Mar 2024 | Aug 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FCWET | CONSTRUCTION OF FLUSHING CREEK WETLAND PROJECT | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2025 | May 2026 | Aug 2025 | May 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FCWET | CONSTRUCTION OF FLUSHING CREEK WETLAND PROJECT | 5 | CONSTRUCTION TO 25% | May 2026 | May 2027 | May 2026 | May 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FCWET | CONSTRUCTION OF FLUSHING CREEK WETLAND PROJECT | 6 | CONSTRUCTION TO 50% | May 2027 | May 2028 | May 2027 | May 2028
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FCWET | CONSTRUCTION OF FLUSHING CREEK WETLAND PROJECT | 7 | CONSTRUCTION TO 75% | May 2028 | May 2029 | May 2028 | May 2029
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FCWET | CONSTRUCTION OF FLUSHING CREEK WETLAND PROJECT | 8 | ORIGINAL EQUIP & FURNISHING | May 2029 | Feb 2030 | May 2029 | Feb 2030
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FCWET | CONSTRUCTION OF FLUSHING CREEK WETLAND PROJECT | 9 | SUBSTANTIAL COMPLETION | Feb 2030 | Aug 2030 | Feb 2030 | Aug 2030
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FCWET | CONSTRUCTION OF FLUSHING CREEK WETLAND PROJECT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2030 | Oct 2030 | Aug 2030 | Oct 2030
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-187 | REPLACE MAIN SEWAGE PUMP CONTROLS AT JAMAICA WPCP | 1 | FINAL DESIGN | Jun 2022 | Dec 2023 | Jun 2022 | Dec 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-187 | REPLACE MAIN SEWAGE PUMP CONTROLS AT JAMAICA WPCP | 2 | CONSTRUCTION TO 25% | Dec 2023 | Aug 2024 | Dec 2023 | Aug 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-187 | REPLACE MAIN SEWAGE PUMP CONTROLS AT JAMAICA WPCP | 3 | CONSTRUCTION TO 50% | Aug 2024 | Mar 2025 | Aug 2024 | Mar 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-187 | REPLACE MAIN SEWAGE PUMP CONTROLS AT JAMAICA WPCP | 4 | CONSTRUCTION TO 75% | Mar 2025 | Nov 2025 | Mar 2025 | Nov 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-STAB | STABILIZATION PROGRAM AT JAMAICA WPCP | 1 | DEVELOP SCOPE | Jan 2005 | Oct 2005 | Jan 2005 | Oct 2005
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-STAB | STABILIZATION PROGRAM AT JAMAICA WPCP | 2 | PRELIMINARY DESIGN | Oct 2005 | Oct 2006 | Oct 2005 | Oct 2006
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-STAB | STABILIZATION PROGRAM AT JAMAICA WPCP | 3 | FINAL DESIGN | Oct 2006 | Apr 2008 | Oct 2006 | Apr 2008
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-STAB | STABILIZATION PROGRAM AT JAMAICA WPCP | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2008 | Dec 2008 | Apr 2008 | Dec 2008
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-STAB | STABILIZATION PROGRAM AT JAMAICA WPCP | 5 | CONSTRUCTION TO 25% | Dec 2008 | Dec 2009 | Dec 2008 | Dec 2009
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-STAB | STABILIZATION PROGRAM AT JAMAICA WPCP | 6 | CONSTRUCTION TO 50% | Dec 2009 | Dec 2010 | Dec 2009 | Dec 2010
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-STAB | STABILIZATION PROGRAM AT JAMAICA WPCP | 7 | CONSTRUCTION TO 75% | Dec 2010 | Dec 2011 | Dec 2010 | Dec 2011
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-STAB | STABILIZATION PROGRAM AT JAMAICA WPCP | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2011 | Sep 2012 | Dec 2011 | Sep 2012
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-STAB | STABILIZATION PROGRAM AT JAMAICA WPCP | 9 | SUBSTANTIAL COMPLETION | Sep 2012 | Mar 2013 | Sep 2012 | Mar 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-STAB | STABILIZATION PROGRAM AT JAMAICA WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2013 | Jun 2013 | Mar 2025 | Jun 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JFK-INTER | REROUTING OF INTERCEPTOR AT NEW JFK CARGO BUILDIING | 1 | FINAL DESIGN | Jun 2021 | Nov 2022 | Jun 2021 | Nov 2022
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JFK-INTER | REROUTING OF INTERCEPTOR AT NEW JFK CARGO BUILDIING | 2 | CONSTRUCTION TO 25% | Nov 2022 | Jul 2023 | Nov 2022 | Jul 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JFK-INTER | REROUTING OF INTERCEPTOR AT NEW JFK CARGO BUILDIING | 3 | CONSTRUCTION TO 50% | Jul 2023 | Mar 2024 | Jul 2023 | Mar 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JFK-INTER | REROUTING OF INTERCEPTOR AT NEW JFK CARGO BUILDIING | 4 | CONSTRUCTION TO 75% | Mar 2024 | Nov 2024 | Mar 2024 | Nov 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | MASPETH | RECONSTRUCTION OF BUILDING, MASPETH, QUEENS | 1 | DEVELOP SCOPE | Sep 2004 | Jan 2005 | Jun 2020 | Oct 2020
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | MASPETH | RECONSTRUCTION OF BUILDING, MASPETH, QUEENS | 2 | PRELIMINARY DESIGN | Jan 2005 | Jul 2005 | Oct 2020 | Apr 2021
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | MASPETH | RECONSTRUCTION OF BUILDING, MASPETH, QUEENS | 3 | FINAL DESIGN | Jul 2005 | Jan 2007 | Apr 2021 | Oct 2022
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | MASPETH | RECONSTRUCTION OF BUILDING, MASPETH, QUEENS | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2007 | Jul 2007 | Oct 2022 | Apr 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | MASPETH | RECONSTRUCTION OF BUILDING, MASPETH, QUEENS | 5 | CONSTRUCTION TO 25% | Jul 2007 | Apr 2008 | Apr 2023 | Jan 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | MASPETH | RECONSTRUCTION OF BUILDING, MASPETH, QUEENS | 6 | CONSTRUCTION TO 50% | Apr 2008 | Jan 2009 | Jan 2024 | Oct 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | MASPETH | RECONSTRUCTION OF BUILDING, MASPETH, QUEENS | 7 | CONSTRUCTION TO 75% | Jan 2009 | Oct 2009 | Oct 2024 | Jul 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | MASPETH | RECONSTRUCTION OF BUILDING, MASPETH, QUEENS | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2009 | Jan 2010 | Jul 2025 | Oct 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | MASPETH | RECONSTRUCTION OF BUILDING, MASPETH, QUEENS | 9 | SUBSTANTIAL COMPLETION | Jan 2010 | Mar 2010 | Oct 2025 | Dec 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | MASPETH | RECONSTRUCTION OF BUILDING, MASPETH, QUEENS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2010 | Jun 2010 | Dec 2025 | Mar 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-277 | RECONSTRUCTION AT 108 STREET PUMPING STATION | 1 | DEVELOP SCOPE | Jul 2017 | Mar 2018 | Jul 2017 | Mar 2018
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-277 | RECONSTRUCTION AT 108 STREET PUMPING STATION | 2 | PRELIMINARY DESIGN | Mar 2018 | Mar 2019 | Mar 2018 | Mar 2019
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-277 | RECONSTRUCTION AT 108 STREET PUMPING STATION | 3 | FINAL DESIGN | Mar 2019 | Sep 2020 | Mar 2019 | Sep 2020
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-277 | RECONSTRUCTION AT 108 STREET PUMPING STATION | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2020 | Jun 2021 | Sep 2020 | Jun 2021
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-277 | RECONSTRUCTION AT 108 STREET PUMPING STATION | 5 | CONSTRUCTION TO 25% | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-277 | RECONSTRUCTION AT 108 STREET PUMPING STATION | 6 | CONSTRUCTION TO 50% | Jun 2022 | May 2023 | Jun 2022 | May 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-277 | RECONSTRUCTION AT 108 STREET PUMPING STATION | 7 | CONSTRUCTION TO 75% | May 2023 | May 2024 | May 2023 | May 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-277 | RECONSTRUCTION AT 108 STREET PUMPING STATION | 8 | ORIGINAL EQUIP & FURNISHING | May 2024 | Feb 2025 | May 2024 | Feb 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-277 | RECONSTRUCTION AT 108 STREET PUMPING STATION | 9 | SUBSTANTIAL COMPLETION | Feb 2025 | Aug 2025 | Feb 2025 | Aug 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-277 | RECONSTRUCTION AT 108 STREET PUMPING STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2025 | Nov 2025 | Aug 2025 | Nov 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-285 | RIKERS ISLAND NORTH AND SOUTH PUMPING STATION | 1 | DEVELOP SCOPE | Jul 2016 | Mar 2017 | Jul 2016 | Mar 2017
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-285 | RIKERS ISLAND NORTH AND SOUTH PUMPING STATION | 2 | PRELIMINARY DESIGN | Mar 2017 | Mar 2018 | Mar 2017 | Mar 2018
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-285 | RIKERS ISLAND NORTH AND SOUTH PUMPING STATION | 3 | FINAL DESIGN | Mar 2018 | Sep 2019 | Mar 2018 | Sep 2019
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-285 | RIKERS ISLAND NORTH AND SOUTH PUMPING STATION | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Jun 2020 | Sep 2019 | Jun 2020
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-285 | RIKERS ISLAND NORTH AND SOUTH PUMPING STATION | 5 | CONSTRUCTION TO 25% | Jun 2020 | Jun 2021 | Jun 2020 | Jun 2021
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-285 | RIKERS ISLAND NORTH AND SOUTH PUMPING STATION | 6 | CONSTRUCTION TO 50% | Jun 2021 | May 2022 | Jun 2021 | May 2022
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-285 | RIKERS ISLAND NORTH AND SOUTH PUMPING STATION | 7 | CONSTRUCTION TO 75% | May 2022 | May 2023 | May 2022 | May 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-285 | RIKERS ISLAND NORTH AND SOUTH PUMPING STATION | 8 | ORIGINAL EQUIP & FURNISHING | May 2023 | Feb 2024 | May 2023 | Feb 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-285 | RIKERS ISLAND NORTH AND SOUTH PUMPING STATION | 9 | SUBSTANTIAL COMPLETION | Feb 2024 | Aug 2024 | Feb 2024 | Aug 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-285 | RIKERS ISLAND NORTH AND SOUTH PUMPING STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2024 | Nov 2024 | Aug 2024 | Nov 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-286 | ST ALBANS PUMPING STATION | 1 | DEVELOP SCOPE | Jul 2016 | Mar 2017 | Jul 2016 | Mar 2017
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-286 | ST ALBANS PUMPING STATION | 2 | PRELIMINARY DESIGN | Mar 2017 | Mar 2018 | Mar 2017 | Mar 2018
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-286 | ST ALBANS PUMPING STATION | 3 | FINAL DESIGN | Mar 2018 | Sep 2019 | Mar 2018 | Sep 2019
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-286 | ST ALBANS PUMPING STATION | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Jun 2020 | Sep 2019 | Jun 2020
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-286 | ST ALBANS PUMPING STATION | 5 | CONSTRUCTION TO 25% | Jun 2020 | Jun 2021 | Jun 2020 | Jun 2021
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-286 | ST ALBANS PUMPING STATION | 6 | CONSTRUCTION TO 50% | Jun 2021 | May 2022 | Jun 2021 | May 2022
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-286 | ST ALBANS PUMPING STATION | 7 | CONSTRUCTION TO 75% | May 2022 | May 2023 | May 2022 | May 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-286 | ST ALBANS PUMPING STATION | 8 | ORIGINAL EQUIP & FURNISHING | May 2023 | Feb 2024 | May 2023 | Feb 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-286 | ST ALBANS PUMPING STATION | 9 | SUBSTANTIAL COMPLETION | Feb 2024 | Aug 2024 | Feb 2024 | Aug 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-286 | ST ALBANS PUMPING STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2024 | Nov 2024 | Aug 2024 | Nov 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-291 | 154TH STREET PUMPING STATION | 1 | DEVELOP SCOPE | Jun 2020 | Feb 2021 | Jun 2019 | Feb 2020
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-291 | 154TH STREET PUMPING STATION | 2 | PRELIMINARY DESIGN | Feb 2021 | Feb 2022 | Feb 2020 | Feb 2021
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-291 | 154TH STREET PUMPING STATION | 3 | FINAL DESIGN | Feb 2022 | Aug 2023 | Feb 2021 | Aug 2022
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-291 | 154TH STREET PUMPING STATION | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2023 | May 2024 | Aug 2022 | May 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-291 | 154TH STREET PUMPING STATION | 5 | CONSTRUCTION TO 25% | May 2024 | May 2025 | May 2023 | May 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-291 | 154TH STREET PUMPING STATION | 6 | CONSTRUCTION TO 50% | May 2025 | Apr 2026 | May 2024 | Apr 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-291 | 154TH STREET PUMPING STATION | 7 | CONSTRUCTION TO 75% | May 2026 | Apr 2027 | Apr 2025 | Apr 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-291 | 154TH STREET PUMPING STATION | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2027 | Jan 2028 | Apr 2026 | Jan 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-291 | 154TH STREET PUMPING STATION | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Jul 2028 | Jan 2027 | Jul 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-291 | 154TH STREET PUMPING STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2028 | Oct 2028 | Jul 2027 | Oct 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-292 | RECONSTRUCTIONOF LINDEN PLACE PUMPING STATION | 1 | DEVELOP SCOPE | Jul 2016 | Mar 2017 | Jul 2016 | Mar 2017
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-292 | RECONSTRUCTIONOF LINDEN PLACE PUMPING STATION | 2 | PRELIMINARY DESIGN | Mar 2017 | Mar 2018 | Mar 2017 | Mar 2018
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-292 | RECONSTRUCTIONOF LINDEN PLACE PUMPING STATION | 3 | FINAL DESIGN | Mar 2018 | Sep 2019 | Mar 2018 | Sep 2019
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-292 | RECONSTRUCTIONOF LINDEN PLACE PUMPING STATION | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Jun 2020 | Sep 2019 | Jun 2020
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-292 | RECONSTRUCTIONOF LINDEN PLACE PUMPING STATION | 5 | CONSTRUCTION TO 25% | Jun 2020 | Jun 2021 | Jun 2020 | Jun 2021
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-292 | RECONSTRUCTIONOF LINDEN PLACE PUMPING STATION | 6 | CONSTRUCTION TO 50% | Jun 2021 | May 2022 | Jun 2021 | May 2022
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-292 | RECONSTRUCTIONOF LINDEN PLACE PUMPING STATION | 7 | CONSTRUCTION TO 75% | May 2022 | May 2023 | May 2022 | May 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-292 | RECONSTRUCTIONOF LINDEN PLACE PUMPING STATION | 8 | ORIGINAL EQUIP & FURNISHING | May 2023 | Feb 2024 | May 2023 | Feb 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-292 | RECONSTRUCTIONOF LINDEN PLACE PUMPING STATION | 9 | SUBSTANTIAL COMPLETION | Feb 2024 | Aug 2024 | Feb 2024 | Aug 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-292 | RECONSTRUCTIONOF LINDEN PLACE PUMPING STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2024 | Nov 2024 | Aug 2024 | Nov 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-293 | RECONSTRUCTION AT HOWARD BEACH PUMPING STATION | 1 | DEVELOP SCOPE | Jun 2022 | Feb 2023 | Jul 2018 | Mar 2019
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-293 | RECONSTRUCTION AT HOWARD BEACH PUMPING STATION | 2 | PRELIMINARY DESIGN | Feb 2023 | Feb 2024 | Mar 2019 | Mar 2020
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-293 | RECONSTRUCTION AT HOWARD BEACH PUMPING STATION | 3 | FINAL DESIGN | Feb 2024 | Aug 2025 | Mar 2020 | Sep 2021
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-293 | RECONSTRUCTION AT HOWARD BEACH PUMPING STATION | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2025 | May 2026 | Sep 2021 | Jun 2022
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-293 | RECONSTRUCTION AT HOWARD BEACH PUMPING STATION | 5 | CONSTRUCTION TO 25% | May 2026 | May 2027 | Jun 2022 | Jun 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-293 | RECONSTRUCTION AT HOWARD BEACH PUMPING STATION | 6 | CONSTRUCTION TO 50% | May 2027 | Apr 2028 | Jun 2023 | May 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-293 | RECONSTRUCTION AT HOWARD BEACH PUMPING STATION | 7 | CONSTRUCTION TO 75% | Apr 2028 | Apr 2029 | May 2024 | May 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-293 | RECONSTRUCTION AT HOWARD BEACH PUMPING STATION | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2029 | Jan 2030 | May 2025 | Feb 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-293 | RECONSTRUCTION AT HOWARD BEACH PUMPING STATION | 9 | SUBSTANTIAL COMPLETION | Jan 2030 | Jul 2030 | Feb 2026 | Aug 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-293 | RECONSTRUCTION AT HOWARD BEACH PUMPING STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2030 | Oct 2030 | Aug 2026 | Nov 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-304 | RECONSTRUCTION AT GLENDALE PUMPING STATION | 1 | DEVELOP SCOPE | Jul 2016 | Mar 2017 | Jul 2016 | Mar 2017
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-304 | RECONSTRUCTION AT GLENDALE PUMPING STATION | 2 | PRELIMINARY DESIGN | Mar 2017 | Mar 2018 | Mar 2017 | Mar 2018
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-304 | RECONSTRUCTION AT GLENDALE PUMPING STATION | 3 | FINAL DESIGN | Mar 2018 | Sep 2019 | Mar 2018 | Sep 2019
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-304 | RECONSTRUCTION AT GLENDALE PUMPING STATION | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Jun 2020 | Sep 2019 | Jun 2020
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-304 | RECONSTRUCTION AT GLENDALE PUMPING STATION | 5 | CONSTRUCTION TO 25% | Jun 2020 | Jun 2021 | Jun 2020 | Jun 2021
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-304 | RECONSTRUCTION AT GLENDALE PUMPING STATION | 6 | CONSTRUCTION TO 50% | Jun 2021 | May 2022 | Jun 2021 | May 2022
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-304 | RECONSTRUCTION AT GLENDALE PUMPING STATION | 7 | CONSTRUCTION TO 75% | May 2022 | May 2023 | May 2022 | May 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-304 | RECONSTRUCTION AT GLENDALE PUMPING STATION | 8 | ORIGINAL EQUIP & FURNISHING | May 2023 | Feb 2024 | May 2023 | Feb 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-304 | RECONSTRUCTION AT GLENDALE PUMPING STATION | 9 | SUBSTANTIAL COMPLETION | Feb 2024 | Aug 2024 | Feb 2024 | Aug 2028
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-304 | RECONSTRUCTION AT GLENDALE PUMPING STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2024 | Nov 2024 | Aug 2028 | Nov 2028
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-321 | RECONSTRUCTION OF LITTLE NECK PUMPING STATION, QUEENS, N.Y. | 1 | DEVELOP SCOPE | Jul 2016 | Mar 2017 | Jul 2016 | Mar 2017
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-321 | RECONSTRUCTION OF LITTLE NECK PUMPING STATION, QUEENS, N.Y. | 2 | PRELIMINARY DESIGN | Mar 2017 | Mar 2018 | Mar 2017 | Mar 2018
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-321 | RECONSTRUCTION OF LITTLE NECK PUMPING STATION, QUEENS, N.Y. | 3 | FINAL DESIGN | Mar 2018 | Sep 2019 | Mar 2018 | Sep 2019
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-321 | RECONSTRUCTION OF LITTLE NECK PUMPING STATION, QUEENS, N.Y. | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Jun 2020 | Sep 2019 | Jun 2020
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-321 | RECONSTRUCTION OF LITTLE NECK PUMPING STATION, QUEENS, N.Y. | 5 | CONSTRUCTION TO 25% | Jun 2020 | Jun 2021 | Jun 2020 | Jun 2021
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-321 | RECONSTRUCTION OF LITTLE NECK PUMPING STATION, QUEENS, N.Y. | 6 | CONSTRUCTION TO 50% | Jun 2021 | May 2022 | Jun 2021 | May 2022
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-321 | RECONSTRUCTION OF LITTLE NECK PUMPING STATION, QUEENS, N.Y. | 7 | CONSTRUCTION TO 75% | May 2022 | May 2023 | May 2022 | May 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-321 | RECONSTRUCTION OF LITTLE NECK PUMPING STATION, QUEENS, N.Y. | 8 | ORIGINAL EQUIP & FURNISHING | May 2023 | Feb 2024 | May 2023 | Feb 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-321 | RECONSTRUCTION OF LITTLE NECK PUMPING STATION, QUEENS, N.Y. | 9 | SUBSTANTIAL COMPLETION | Feb 2024 | Aug 2024 | Feb 2024 | Aug 2028
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-321 | RECONSTRUCTION OF LITTLE NECK PUMPING STATION, QUEENS, N.Y. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2024 | Nov 2024 | Aug 2028 | Nov 2028
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1042B | WM & TM repmnt & SE repair in Queens Blvd | 1 | DEVELOP SCOPE | Sep 2021 | May 2022 | Sep 2021 | May 2022
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1042B | WM & TM repmnt & SE repair in Queens Blvd | 2 | PRELIMINARY DESIGN | May 2022 | May 2023 | May 2022 | May 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1042B | WM & TM repmnt & SE repair in Queens Blvd | 3 | FINAL DESIGN | May 2023 | Nov 2024 | May 2023 | Nov 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1042B | WM & TM repmnt & SE repair in Queens Blvd | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2024 | Aug 2025 | Nov 2024 | Aug 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1042B | WM & TM repmnt & SE repair in Queens Blvd | 5 | CONSTRUCTION TO 25% | Aug 2025 | Aug 2026 | Aug 2025 | Aug 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1042B | WM & TM repmnt & SE repair in Queens Blvd | 6 | CONSTRUCTION TO 50% | Aug 2026 | Aug 2027 | Aug 2026 | Aug 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1042B | WM & TM repmnt & SE repair in Queens Blvd | 7 | CONSTRUCTION TO 75% | Aug 2027 | Jul 2028 | Aug 2027 | Jul 2028
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1042B | WM & TM repmnt & SE repair in Queens Blvd | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2028 | Apr 2029 | Jul 2028 | Apr 2029
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1042B | WM & TM repmnt & SE repair in Queens Blvd | 9 | SUBSTANTIAL COMPLETION | Apr 2029 | Oct 2029 | Apr 2029 | Oct 2029
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1042B | WM & TM repmnt & SE repair in Queens Blvd | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2029 | Jan 2030 | Oct 2029 | Jan 2030
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1053 | Trunk Water Main Replacement in Rockaway Blvd | 1 | DEVELOP SCOPE | Jun 2021 | Aug 2021 | Jun 2025 | Aug 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1053 | Trunk Water Main Replacement in Rockaway Blvd | 2 | PRELIMINARY DESIGN | Aug 2021 | Dec 2021 | Aug 2025 | Dec 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1053 | Trunk Water Main Replacement in Rockaway Blvd | 3 | FINAL DESIGN | Dec 2021 | Jun 2022 | Dec 2025 | Jun 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1053 | Trunk Water Main Replacement in Rockaway Blvd | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Sep 2022 | Jun 2026 | Sep 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1053 | Trunk Water Main Replacement in Rockaway Blvd | 5 | CONSTRUCTION TO 25% | Sep 2022 | Jan 2023 | Sep 2026 | Jan 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1053 | Trunk Water Main Replacement in Rockaway Blvd | 6 | CONSTRUCTION TO 50% | Jan 2023 | May 2023 | Jan 2027 | May 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1053 | Trunk Water Main Replacement in Rockaway Blvd | 7 | CONSTRUCTION TO 75% | May 2023 | Sep 2023 | May 2027 | Sep 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1053 | Trunk Water Main Replacement in Rockaway Blvd | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Dec 2023 | Sep 2027 | Dec 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1053 | Trunk Water Main Replacement in Rockaway Blvd | 9 | SUBSTANTIAL COMPLETION | Dec 2023 | Feb 2024 | Dec 2027 | Feb 2028
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1053 | Trunk Water Main Replacement in Rockaway Blvd | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2024 | Mar 2024 | Feb 2028 | Mar 2028
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED1058 | Dist WM in Francis Lewis Blvd from Weeks Ln to 53 Ave, QNS | 1 | DEVELOP SCOPE | Jan 2025 | Mar 2025 | Aug 2026 | Nov 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED1058 | Dist WM in Francis Lewis Blvd from Weeks Ln to 53 Ave, QNS | 2 | PRELIMINARY DESIGN | Apr 2025 | Jul 2025 | Nov 2026 | Mar 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED1058 | Dist WM in Francis Lewis Blvd from Weeks Ln to 53 Ave, QNS | 3 | FINAL DESIGN | Jul 2025 | Jan 2026 | Mar 2027 | Sep 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED1058 | Dist WM in Francis Lewis Blvd from Weeks Ln to 53 Ave, QNS | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2026 | Apr 2026 | Sep 2027 | Dec 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED1058 | Dist WM in Francis Lewis Blvd from Weeks Ln to 53 Ave, QNS | 5 | CONSTRUCTION TO 25% | Apr 2026 | Aug 2026 | Dec 2027 | Apr 2028
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED1058 | Dist WM in Francis Lewis Blvd from Weeks Ln to 53 Ave, QNS | 6 | CONSTRUCTION TO 50% | Aug 2026 | Dec 2026 | Apr 2028 | Aug 2028
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED1058 | Dist WM in Francis Lewis Blvd from Weeks Ln to 53 Ave, QNS | 7 | CONSTRUCTION TO 75% | Dec 2026 | Apr 2027 | Aug 2028 | Dec 2028
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED1058 | Dist WM in Francis Lewis Blvd from Weeks Ln to 53 Ave, QNS | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2027 | Jul 2027 | Dec 2028 | Mar 2029
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED1058 | Dist WM in Francis Lewis Blvd from Weeks Ln to 53 Ave, QNS | 9 | SUBSTANTIAL COMPLETION | Jul 2027 | Sep 2027 | Mar 2029 | May 2029
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED1058 | Dist WM in Francis Lewis Blvd from Weeks Ln to 53 Ave, QNS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Oct 2027 | May 2029 | Jun 2029
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QNSREPAIR | REHABILITATION OF QUEENS REPAIR FACILITY | 1 | DEVELOP SCOPE | Jun 2019 | Oct 2019 | Aug 2023 | Dec 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QNSREPAIR | REHABILITATION OF QUEENS REPAIR FACILITY | 2 | PRELIMINARY DESIGN | Oct 2019 | Apr 2020 | Dec 2023 | Jun 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QNSREPAIR | REHABILITATION OF QUEENS REPAIR FACILITY | 3 | FINAL DESIGN | Apr 2020 | Oct 2021 | Jun 2024 | Dec 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QNSREPAIR | REHABILITATION OF QUEENS REPAIR FACILITY | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2021 | Apr 2022 | Dec 2025 | Jun 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QNSREPAIR | REHABILITATION OF QUEENS REPAIR FACILITY | 5 | CONSTRUCTION TO 25% | Apr 2022 | Jan 2023 | Jun 2026 | Mar 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QNSREPAIR | REHABILITATION OF QUEENS REPAIR FACILITY | 6 | CONSTRUCTION TO 50% | Jan 2023 | Nov 2023 | Mar 2027 | Dec 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QNSREPAIR | REHABILITATION OF QUEENS REPAIR FACILITY | 7 | CONSTRUCTION TO 75% | Nov 2023 | Aug 2024 | Dec 2027 | Oct 2028
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QNSREPAIR | REHABILITATION OF QUEENS REPAIR FACILITY | 8 | ORIGINAL EQUIP & FURNISHING | Aug 2024 | Nov 2024 | Oct 2028 | Jan 2029
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QNSREPAIR | REHABILITATION OF QUEENS REPAIR FACILITY | 9 | SUBSTANTIAL COMPLETION | Nov 2024 | Jan 2025 | Jan 2029 | Mar 2029
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QNSREPAIR | REHABILITATION OF QUEENS REPAIR FACILITY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2025 | Apr 2025 | Mar 2029 | Jun 2029
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-151-L | RECONS FENDER & BULKHEAD AT THE ROCKAWAY WPCP | 1 | DEVELOP SCOPE | Jul 2013 | Apr 2014 | Jul 2013 | Apr 2014
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-151-L | RECONS FENDER & BULKHEAD AT THE ROCKAWAY WPCP | 2 | PRELIMINARY DESIGN | Apr 2014 | Apr 2015 | Apr 2014 | Apr 2015
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-151-L | RECONS FENDER & BULKHEAD AT THE ROCKAWAY WPCP | 3 | FINAL DESIGN | Apr 2015 | Sep 2016 | Apr 2015 | Sep 2016
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-151-L | RECONS FENDER & BULKHEAD AT THE ROCKAWAY WPCP | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2016 | Jun 2017 | Sep 2016 | Jun 2017
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-151-L | RECONS FENDER & BULKHEAD AT THE ROCKAWAY WPCP | 5 | CONSTRUCTION TO 25% | Jun 2017 | Jun 2018 | Jun 2017 | Jun 2018
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-151-L | RECONS FENDER & BULKHEAD AT THE ROCKAWAY WPCP | 6 | CONSTRUCTION TO 50% | Jun 2018 | Jun 2019 | Jun 2018 | Jun 2019
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-151-L | RECONS FENDER & BULKHEAD AT THE ROCKAWAY WPCP | 7 | CONSTRUCTION TO 75% | Jun 2019 | Jun 2020 | Jun 2019 | Jun 2020
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-151-L | RECONS FENDER & BULKHEAD AT THE ROCKAWAY WPCP | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2020 | Feb 2021 | Jun 2020 | Feb 2021
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-151-L | RECONS FENDER & BULKHEAD AT THE ROCKAWAY WPCP | 9 | SUBSTANTIAL COMPLETION | Mar 2021 | Aug 2021 | Mar 2021 | Aug 2029
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-151-L | RECONS FENDER & BULKHEAD AT THE ROCKAWAY WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Nov 2021 | Aug 2029 | Nov 2029
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-153-L | RECONSTRUCT FINAL SETTLING SYSTEM @ ROCKAWAY WWTP | 1 | DEVELOP SCOPE | Jun 2020 | Feb 2021 | Jun 2019 | Feb 2020
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-153-L | RECONSTRUCT FINAL SETTLING SYSTEM @ ROCKAWAY WWTP | 2 | PRELIMINARY DESIGN | Feb 2021 | Feb 2022 | Feb 2020 | Feb 2021
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-153-L | RECONSTRUCT FINAL SETTLING SYSTEM @ ROCKAWAY WWTP | 3 | FINAL DESIGN | Feb 2022 | Aug 2023 | Feb 2021 | Aug 2022
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-153-L | RECONSTRUCT FINAL SETTLING SYSTEM @ ROCKAWAY WWTP | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2023 | May 2024 | Aug 2022 | May 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-153-L | RECONSTRUCT FINAL SETTLING SYSTEM @ ROCKAWAY WWTP | 5 | CONSTRUCTION TO 25% | May 2024 | May 2025 | May 2023 | May 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-153-L | RECONSTRUCT FINAL SETTLING SYSTEM @ ROCKAWAY WWTP | 6 | CONSTRUCTION TO 50% | May 2025 | Apr 2026 | May 2024 | Apr 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-153-L | RECONSTRUCT FINAL SETTLING SYSTEM @ ROCKAWAY WWTP | 7 | CONSTRUCTION TO 75% | May 2026 | Apr 2027 | Apr 2025 | Apr 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-153-L | RECONSTRUCT FINAL SETTLING SYSTEM @ ROCKAWAY WWTP | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2027 | Jan 2028 | Apr 2026 | Jan 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-153-L | RECONSTRUCT FINAL SETTLING SYSTEM @ ROCKAWAY WWTP | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Jul 2028 | Jan 2027 | Jul 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-153-L | RECONSTRUCT FINAL SETTLING SYSTEM @ ROCKAWAY WWTP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2028 | Oct 2028 | Jul 2027 | Oct 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-156-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ ROCKAWAY WWTP | 1 | DEVELOP SCOPE | Jan 2017 | Oct 2017 | Jun 2023 | Feb 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-156-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ ROCKAWAY WWTP | 2 | PRELIMINARY DESIGN | Oct 2017 | Oct 2018 | Feb 2024 | Feb 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-156-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ ROCKAWAY WWTP | 3 | FINAL DESIGN | Oct 2018 | Mar 2020 | Feb 2025 | Aug 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-156-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ ROCKAWAY WWTP | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Dec 2020 | Aug 2026 | May 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-156-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ ROCKAWAY WWTP | 5 | CONSTRUCTION TO 25% | Dec 2020 | Dec 2021 | May 2027 | May 2028
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-156-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ ROCKAWAY WWTP | 6 | CONSTRUCTION TO 50% | Dec 2021 | Dec 2022 | May 2028 | Apr 2029
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-156-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ ROCKAWAY WWTP | 7 | CONSTRUCTION TO 75% | Dec 2022 | Dec 2023 | Apr 2029 | Apr 2030
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-156-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ ROCKAWAY WWTP | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2023 | Sep 2024 | Apr 2030 | Jan 2031
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-156-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ ROCKAWAY WWTP | 9 | SUBSTANTIAL COMPLETION | Sep 2024 | Mar 2025 | Jan 2031 | Jul 2031
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-156-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ ROCKAWAY WWTP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Jun 2025 | Jul 2031 | Oct 2031
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-2 | REPLACE MAIN SEWAGE PUMPS AT ROCKAWAY WPCP | 1 | FINAL DESIGN | Jun 2022 | Nov 2023 | Jun 2019 | Feb 2020
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-2 | REPLACE MAIN SEWAGE PUMPS AT ROCKAWAY WPCP | 2 | CONSTRUCTION TO 25% | Nov 2023 | Jul 2024 | Feb 2020 | Feb 2021
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-2 | REPLACE MAIN SEWAGE PUMPS AT ROCKAWAY WPCP | 3 | CONSTRUCTION TO 50% | Jul 2024 | Mar 2025 | Feb 2021 | Aug 2022
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-2 | REPLACE MAIN SEWAGE PUMPS AT ROCKAWAY WPCP | 4 | CONSTRUCTION TO 75% | Mar 2025 | Nov 2025 | Aug 2022 | May 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-2 | REPLACE MAIN SEWAGE PUMPS AT ROCKAWAY WPCP | 5 | CONSTRUCTION TO 25% | Mar 2025 | Nov 2025 | May 2023 | May 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-2 | REPLACE MAIN SEWAGE PUMPS AT ROCKAWAY WPCP | 6 | CONSTRUCTION TO 50% | Mar 2025 | Nov 2025 | May 2024 | Apr 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-2 | REPLACE MAIN SEWAGE PUMPS AT ROCKAWAY WPCP | 7 | CONSTRUCTION TO 75% | Mar 2025 | Nov 2025 | Apr 2025 | Apr 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-2 | REPLACE MAIN SEWAGE PUMPS AT ROCKAWAY WPCP | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2025 | Nov 2025 | Apr 2026 | Jan 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-2 | REPLACE MAIN SEWAGE PUMPS AT ROCKAWAY WPCP | 9 | SUBSTANTIAL COMPLETION | Mar 2025 | Nov 2025 | Jan 2027 | Jul 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-2 | REPLACE MAIN SEWAGE PUMPS AT ROCKAWAY WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Nov 2025 | Jul 2027 | Oct 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-ODOR | ODOR CONTROL UPGRADE IN THE THICKENER BLDG AT ROCKAWAY WPCP | 1 | FINAL DESIGN | Jun 2023 | Nov 2024 | Jun 2029 | Nov 2030
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-ODOR | ODOR CONTROL UPGRADE IN THE THICKENER BLDG AT ROCKAWAY WPCP | 2 | CONSTRUCTION TO 25% | Nov 2024 | Jul 2025 | Nov 2030 | Jul 2031
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-ODOR | ODOR CONTROL UPGRADE IN THE THICKENER BLDG AT ROCKAWAY WPCP | 3 | CONSTRUCTION TO 50% | Jul 2025 | Mar 2026 | Jul 2031 | Mar 2032
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-ODOR | ODOR CONTROL UPGRADE IN THE THICKENER BLDG AT ROCKAWAY WPCP | 4 | CONSTRUCTION TO 75% | Mar 2026 | Nov 2026 | Mar 2032 | Nov 2032
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDROCK | RECONS OF THE ROCKAWAY WPCP DUE TO HURRICANE SANDY | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Mar 2015
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDROCK | RECONS OF THE ROCKAWAY WPCP DUE TO HURRICANE SANDY | 2 | PRELIMINARY DESIGN | Sep 2014 | Jan 2015 | Mar 2015 | Mar 2016
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDROCK | RECONS OF THE ROCKAWAY WPCP DUE TO HURRICANE SANDY | 3 | FINAL DESIGN | Jan 2015 | Jul 2015 | Mar 2016 | Sep 2017
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDROCK | RECONS OF THE ROCKAWAY WPCP DUE TO HURRICANE SANDY | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Oct 2015 | Sep 2017 | Jun 2018
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDROCK | RECONS OF THE ROCKAWAY WPCP DUE TO HURRICANE SANDY | 5 | CONSTRUCTION TO 25% | Oct 2015 | Feb 2016 | Jun 2018 | Jun 2019
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDROCK | RECONS OF THE ROCKAWAY WPCP DUE TO HURRICANE SANDY | 6 | CONSTRUCTION TO 50% | Feb 2016 | Jun 2016 | Jun 2019 | May 2020
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDROCK | RECONS OF THE ROCKAWAY WPCP DUE TO HURRICANE SANDY | 7 | CONSTRUCTION TO 75% | Jun 2016 | Oct 2016 | May 2020 | May 2021
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDROCK | RECONS OF THE ROCKAWAY WPCP DUE TO HURRICANE SANDY | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2016 | Jan 2017 | May 2021 | Feb 2022
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDROCK | RECONS OF THE ROCKAWAY WPCP DUE TO HURRICANE SANDY | 9 | SUBSTANTIAL COMPLETION | Jan 2017 | Mar 2017 | Feb 2022 | Aug 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDROCK | RECONS OF THE ROCKAWAY WPCP DUE TO HURRICANE SANDY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Apr 2017 | Aug 2026 | Nov 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-861A | HLSS; Strm, san & comb swers & WM, Borden Ave, Phase 2, Qns | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Aug 2028 | Nov 2028
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-861A | HLSS; Strm, san & comb swers & WM, Borden Ave, Phase 2, Qns | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Nov 2028 | Mar 2029
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-861A | HLSS; Strm, san & comb swers & WM, Borden Ave, Phase 2, Qns | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Mar 2029 | Sep 2029
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-861A | HLSS; Strm, san & comb swers & WM, Borden Ave, Phase 2, Qns | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Sep 2029 | Dec 2029
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-861A | HLSS; Strm, san & comb swers & WM, Borden Ave, Phase 2, Qns | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Dec 2029 | Apr 2030
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-861A | HLSS; Strm, san & comb swers & WM, Borden Ave, Phase 2, Qns | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Apr 2030 | Aug 2030
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-861A | HLSS; Strm, san & comb swers & WM, Borden Ave, Phase 2, Qns | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | Aug 2030 | Dec 2030
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-861A | HLSS; Strm, san & comb swers & WM, Borden Ave, Phase 2, Qns | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Dec 2030 | Mar 2031
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-861A | HLSS; Strm, san & comb swers & WM, Borden Ave, Phase 2, Qns | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Mar 2031 | May 2031
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-861A | HLSS; Strm, san & comb swers & WM, Borden Ave, Phase 2, Qns | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | May 2031 | Jun 2031
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ002717 | WM & SE work on 48 St btwn Barnett & 37th Ave, QN Shaft 17B | 1 | DEVELOP SCOPE | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ002717 | WM & SE work on 48 St btwn Barnett & 37th Ave, QN Shaft 17B | 2 | PRELIMINARY DESIGN | Apr 2025 | Jul 2025 | Apr 2025 | Jul 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ002717 | WM & SE work on 48 St btwn Barnett & 37th Ave, QN Shaft 17B | 3 | FINAL DESIGN | Jul 2025 | Jan 2026 | Jul 2025 | Jan 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ002717 | WM & SE work on 48 St btwn Barnett & 37th Ave, QN Shaft 17B | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2026 | Apr 2026 | Jan 2026 | Apr 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ002717 | WM & SE work on 48 St btwn Barnett & 37th Ave, QN Shaft 17B | 5 | CONSTRUCTION TO 25% | Apr 2026 | Aug 2026 | Apr 2026 | Aug 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ002717 | WM & SE work on 48 St btwn Barnett & 37th Ave, QN Shaft 17B | 6 | CONSTRUCTION TO 50% | Aug 2026 | Dec 2026 | Aug 2026 | Dec 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ002717 | WM & SE work on 48 St btwn Barnett & 37th Ave, QN Shaft 17B | 7 | CONSTRUCTION TO 75% | Dec 2026 | Apr 2027 | Dec 2026 | Apr 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ002717 | WM & SE work on 48 St btwn Barnett & 37th Ave, QN Shaft 17B | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2027 | Jul 2027 | Apr 2027 | Jul 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ002717 | WM & SE work on 48 St btwn Barnett & 37th Ave, QN Shaft 17B | 9 | SUBSTANTIAL COMPLETION | Jul 2027 | Sep 2027 | Jul 2027 | Sep 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ002717 | WM & SE work on 48 St btwn Barnett & 37th Ave, QN Shaft 17B | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Oct 2027 | Sep 2027 | Oct 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200601 | Storm SE Ext at intersection of E 16 Rd & Channel Rd, QNS | 1 | DEVELOP SCOPE | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200601 | Storm SE Ext at intersection of E 16 Rd & Channel Rd, QNS | 2 | PRELIMINARY DESIGN | Apr 2026 | Jul 2026 | Apr 2026 | Jul 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200601 | Storm SE Ext at intersection of E 16 Rd & Channel Rd, QNS | 3 | FINAL DESIGN | Jul 2026 | Jan 2027 | Jul 2026 | Jan 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200601 | Storm SE Ext at intersection of E 16 Rd & Channel Rd, QNS | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2027 | Apr 2027 | Jan 2027 | Apr 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200601 | Storm SE Ext at intersection of E 16 Rd & Channel Rd, QNS | 5 | CONSTRUCTION TO 25% | Apr 2027 | Aug 2027 | Apr 2027 | Aug 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200601 | Storm SE Ext at intersection of E 16 Rd & Channel Rd, QNS | 6 | CONSTRUCTION TO 50% | Aug 2027 | Dec 2027 | Aug 2027 | Dec 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200601 | Storm SE Ext at intersection of E 16 Rd & Channel Rd, QNS | 7 | CONSTRUCTION TO 75% | Dec 2027 | Apr 2028 | Dec 2027 | Apr 2028
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200601 | Storm SE Ext at intersection of E 16 Rd & Channel Rd, QNS | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2028 | Jul 2028 | Apr 2028 | Jul 2028
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200601 | Storm SE Ext at intersection of E 16 Rd & Channel Rd, QNS | 9 | SUBSTANTIAL COMPLETION | Jul 2028 | Sep 2028 | Jul 2028 | Sep 2028
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200601 | Storm SE Ext at intersection of E 16 Rd & Channel Rd, QNS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2028 | Oct 2028 | Sep 2028 | Oct 2028
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-CAMB | GREEN INFRASTRUCTURE AT CAMBRIA PLAYGROUND | 1 | DEVELOP SCOPE | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-CAMB | GREEN INFRASTRUCTURE AT CAMBRIA PLAYGROUND | 2 | PRELIMINARY DESIGN | Mar 2025 | Mar 2026 | Mar 2025 | Mar 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-CAMB | GREEN INFRASTRUCTURE AT CAMBRIA PLAYGROUND | 3 | FINAL DESIGN | Mar 2026 | Sep 2027 | Mar 2026 | Sep 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-CAMB | GREEN INFRASTRUCTURE AT CAMBRIA PLAYGROUND | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2027 | Jun 2028 | Sep 2027 | Jun 2028
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-CAMB | GREEN INFRASTRUCTURE AT CAMBRIA PLAYGROUND | 5 | CONSTRUCTION TO 25% | Jun 2028 | Jun 2029 | Jun 2028 | Jun 2029
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-CAMB | GREEN INFRASTRUCTURE AT CAMBRIA PLAYGROUND | 6 | CONSTRUCTION TO 50% | Jun 2029 | May 2030 | Jun 2029 | May 2030
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-CAMB | GREEN INFRASTRUCTURE AT CAMBRIA PLAYGROUND | 7 | CONSTRUCTION TO 75% | May 2030 | May 2031 | May 2030 | May 2031
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-CAMB | GREEN INFRASTRUCTURE AT CAMBRIA PLAYGROUND | 8 | ORIGINAL EQUIP & FURNISHING | May 2031 | Feb 2032 | May 2031 | Feb 2032
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-CAMB | GREEN INFRASTRUCTURE AT CAMBRIA PLAYGROUND | 9 | SUBSTANTIAL COMPLETION | Feb 2032 | Aug 2032 | Feb 2032 | Aug 2032
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-CAMB | GREEN INFRASTRUCTURE AT CAMBRIA PLAYGROUND | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2032 | Nov 2032 | Aug 2032 | Nov 2032
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-DKWPK | CONSTRUCTION FOR DETECTIVE KEITH WILLIAMS PARK | 1 | DEVELOP SCOPE | Jun 2021 | Mar 2022 | Jun 2021 | Mar 2022
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-DKWPK | CONSTRUCTION FOR DETECTIVE KEITH WILLIAMS PARK | 2 | PRELIMINARY DESIGN | Mar 2022 | Mar 2023 | Mar 2022 | Mar 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-DKWPK | CONSTRUCTION FOR DETECTIVE KEITH WILLIAMS PARK | 3 | FINAL DESIGN | Mar 2023 | Aug 2024 | Mar 2023 | Aug 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-DKWPK | CONSTRUCTION FOR DETECTIVE KEITH WILLIAMS PARK | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2024 | May 2025 | Aug 2024 | May 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-DKWPK | CONSTRUCTION FOR DETECTIVE KEITH WILLIAMS PARK | 5 | CONSTRUCTION TO 25% | May 2025 | May 2026 | May 2025 | May 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-DKWPK | CONSTRUCTION FOR DETECTIVE KEITH WILLIAMS PARK | 6 | CONSTRUCTION TO 50% | May 2026 | May 2027 | May 2026 | May 2027
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-DKWPK | CONSTRUCTION FOR DETECTIVE KEITH WILLIAMS PARK | 7 | CONSTRUCTION TO 75% | May 2027 | May 2028 | May 2027 | May 2028
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-DKWPK | CONSTRUCTION FOR DETECTIVE KEITH WILLIAMS PARK | 8 | ORIGINAL EQUIP & FURNISHING | May 2028 | Feb 2029 | May 2028 | Feb 2029
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-DKWPK | CONSTRUCTION FOR DETECTIVE KEITH WILLIAMS PARK | 9 | SUBSTANTIAL COMPLETION | Feb 2029 | Aug 2029 | Feb 2029 | Aug 2029
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-DKWPK | CONSTRUCTION FOR DETECTIVE KEITH WILLIAMS PARK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2029 | Oct 2029 | Aug 2029 | Oct 2029
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQGI-01 | SEQ - CONSTRUCTION OF GREEN INFRASTRUCTURE SOUTHEAST QUEENS | 1 | FINAL DESIGN | Jan 2018 | Jun 2019 | Jan 2018 | Sep 2018
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQGI-01 | SEQ - CONSTRUCTION OF GREEN INFRASTRUCTURE SOUTHEAST QUEENS | 2 | CONSTRUCTION TO 25% | Jun 2019 | Feb 2020 | Sep 2018 | Sep 2019
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQGI-01 | SEQ - CONSTRUCTION OF GREEN INFRASTRUCTURE SOUTHEAST QUEENS | 3 | CONSTRUCTION TO 50% | Feb 2020 | Oct 2020 | Sep 2019 | Mar 2021
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQGI-01 | SEQ - CONSTRUCTION OF GREEN INFRASTRUCTURE SOUTHEAST QUEENS | 4 | CONSTRUCTION TO 75% | Oct 2020 | Jun 2021 | Mar 2021 | Dec 2021
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQGI-01 | SEQ - CONSTRUCTION OF GREEN INFRASTRUCTURE SOUTHEAST QUEENS | 5 | CONSTRUCTION TO 25% | Oct 2020 | Jun 2021 | Dec 2021 | Dec 2022
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQGI-01 | SEQ - CONSTRUCTION OF GREEN INFRASTRUCTURE SOUTHEAST QUEENS | 6 | CONSTRUCTION TO 50% | Oct 2020 | Jun 2021 | Dec 2022 | Nov 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQGI-01 | SEQ - CONSTRUCTION OF GREEN INFRASTRUCTURE SOUTHEAST QUEENS | 7 | CONSTRUCTION TO 75% | Oct 2020 | Jun 2021 | Dec 2023 | Nov 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQGI-01 | SEQ - CONSTRUCTION OF GREEN INFRASTRUCTURE SOUTHEAST QUEENS | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jun 2021 | Nov 2024 | Aug 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQGI-01 | SEQ - CONSTRUCTION OF GREEN INFRASTRUCTURE SOUTHEAST QUEENS | 9 | SUBSTANTIAL COMPLETION | Oct 2020 | Jun 2021 | Aug 2025 | Feb 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQGI-01 | SEQ - CONSTRUCTION OF GREEN INFRASTRUCTURE SOUTHEAST QUEENS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2020 | Jun 2021 | Feb 2026 | May 2026
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-006 | WESTERN CRIBWALL REPLACEMENT AT THE TALLMAN ISLAND WRRF | 1 | DEVELOP SCOPE | Nov 2022 | Jan 2023 | Nov 2022 | Jan 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-006 | WESTERN CRIBWALL REPLACEMENT AT THE TALLMAN ISLAND WRRF | 2 | PRELIMINARY DESIGN | Jan 2023 | May 2023 | Jan 2023 | May 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-006 | WESTERN CRIBWALL REPLACEMENT AT THE TALLMAN ISLAND WRRF | 3 | FINAL DESIGN | May 2023 | Nov 2023 | May 2023 | Nov 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-006 | WESTERN CRIBWALL REPLACEMENT AT THE TALLMAN ISLAND WRRF | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2023 | Feb 2024 | Nov 2023 | Feb 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-006 | WESTERN CRIBWALL REPLACEMENT AT THE TALLMAN ISLAND WRRF | 5 | CONSTRUCTION TO 25% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-006 | WESTERN CRIBWALL REPLACEMENT AT THE TALLMAN ISLAND WRRF | 6 | CONSTRUCTION TO 50% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-006 | WESTERN CRIBWALL REPLACEMENT AT THE TALLMAN ISLAND WRRF | 7 | CONSTRUCTION TO 75% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-006 | WESTERN CRIBWALL REPLACEMENT AT THE TALLMAN ISLAND WRRF | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-006 | WESTERN CRIBWALL REPLACEMENT AT THE TALLMAN ISLAND WRRF | 9 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-006 | WESTERN CRIBWALL REPLACEMENT AT THE TALLMAN ISLAND WRRF | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-168-L | HEADWORKS IMPROVEMENTS AT THE TALLMAN ISLAND WPCP | 1 | DEVELOP SCOPE | Jul 2016 | Mar 2017 | Jul 2015 | Mar 2016
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-168-L | HEADWORKS IMPROVEMENTS AT THE TALLMAN ISLAND WPCP | 2 | PRELIMINARY DESIGN | Mar 2017 | Mar 2018 | Mar 2016 | Mar 2017
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-168-L | HEADWORKS IMPROVEMENTS AT THE TALLMAN ISLAND WPCP | 3 | FINAL DESIGN | Mar 2018 | Sep 2019 | Mar 2017 | Sep 2018
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-168-L | HEADWORKS IMPROVEMENTS AT THE TALLMAN ISLAND WPCP | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Jun 2020 | Sep 2018 | Jun 2019
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-168-L | HEADWORKS IMPROVEMENTS AT THE TALLMAN ISLAND WPCP | 5 | CONSTRUCTION TO 25% | Jun 2020 | Jun 2021 | Jun 2019 | Jun 2020
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-168-L | HEADWORKS IMPROVEMENTS AT THE TALLMAN ISLAND WPCP | 6 | CONSTRUCTION TO 50% | Jun 2021 | May 2022 | Jun 2020 | May 2021
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-168-L | HEADWORKS IMPROVEMENTS AT THE TALLMAN ISLAND WPCP | 7 | CONSTRUCTION TO 75% | May 2022 | May 2023 | May 2021 | May 2022
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-168-L | HEADWORKS IMPROVEMENTS AT THE TALLMAN ISLAND WPCP | 8 | ORIGINAL EQUIP & FURNISHING | May 2023 | Feb 2024 | May 2022 | Feb 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-168-L | HEADWORKS IMPROVEMENTS AT THE TALLMAN ISLAND WPCP | 9 | SUBSTANTIAL COMPLETION | Feb 2024 | Aug 2024 | Feb 2023 | Aug 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-168-L | HEADWORKS IMPROVEMENTS AT THE TALLMAN ISLAND WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2024 | Nov 2024 | Aug 2023 | Nov 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-5 | TALLMAN ISLAND LANDSCAPING UPGRADE & MISC. SITE IMPROVEMENTS | 1 | DEVELOP SCOPE | Jul 2015 | Mar 2016 | Jul 2015 | Mar 2016
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-5 | TALLMAN ISLAND LANDSCAPING UPGRADE & MISC. SITE IMPROVEMENTS | 2 | PRELIMINARY DESIGN | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-5 | TALLMAN ISLAND LANDSCAPING UPGRADE & MISC. SITE IMPROVEMENTS | 3 | FINAL DESIGN | Mar 2017 | Sep 2018 | Mar 2017 | Sep 2018
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-5 | TALLMAN ISLAND LANDSCAPING UPGRADE & MISC. SITE IMPROVEMENTS | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2018 | Jun 2019 | Sep 2018 | Jun 2019
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-5 | TALLMAN ISLAND LANDSCAPING UPGRADE & MISC. SITE IMPROVEMENTS | 5 | CONSTRUCTION TO 25% | Jun 2019 | Jun 2020 | Jun 2019 | Jun 2020
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-5 | TALLMAN ISLAND LANDSCAPING UPGRADE & MISC. SITE IMPROVEMENTS | 6 | CONSTRUCTION TO 50% | Jun 2020 | May 2021 | Jun 2020 | May 2021
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-5 | TALLMAN ISLAND LANDSCAPING UPGRADE & MISC. SITE IMPROVEMENTS | 7 | CONSTRUCTION TO 75% | May 2021 | May 2022 | May 2021 | May 2022
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-5 | TALLMAN ISLAND LANDSCAPING UPGRADE & MISC. SITE IMPROVEMENTS | 8 | ORIGINAL EQUIP & FURNISHING | May 2022 | Feb 2023 | May 2022 | Feb 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-5 | TALLMAN ISLAND LANDSCAPING UPGRADE & MISC. SITE IMPROVEMENTS | 9 | SUBSTANTIAL COMPLETION | Feb 2023 | Aug 2023 | Feb 2023 | Aug 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-5 | TALLMAN ISLAND LANDSCAPING UPGRADE & MISC. SITE IMPROVEMENTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2023 | Nov 2023 | Aug 2023 | Nov 2023
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-STAB | STABILIZATION OF THE TALLMANS' ISLAND WPCP | 1 | DEVELOP SCOPE | Feb 2002 | May 2002 | Jun 2004 | Mar 2005
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-STAB | STABILIZATION OF THE TALLMANS' ISLAND WPCP | 2 | PRELIMINARY DESIGN | May 2002 | Sep 2002 | Mar 2005 | Mar 2006
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-STAB | STABILIZATION OF THE TALLMANS' ISLAND WPCP | 3 | FINAL DESIGN | Sep 2002 | Mar 2003 | Mar 2006 | Aug 2007
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-STAB | STABILIZATION OF THE TALLMANS' ISLAND WPCP | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2003 | Jun 2003 | Aug 2007 | May 2008
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-STAB | STABILIZATION OF THE TALLMANS' ISLAND WPCP | 5 | CONSTRUCTION TO 25% | Jun 2003 | Oct 2003 | May 2008 | May 2009
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-STAB | STABILIZATION OF THE TALLMANS' ISLAND WPCP | 6 | CONSTRUCTION TO 50% | Oct 2003 | Feb 2004 | May 2009 | May 2010
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-STAB | STABILIZATION OF THE TALLMANS' ISLAND WPCP | 7 | CONSTRUCTION TO 75% | Feb 2004 | Jun 2004 | May 2010 | May 2011
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-STAB | STABILIZATION OF THE TALLMANS' ISLAND WPCP | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2004 | Sep 2004 | May 2011 | Feb 2012
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-STAB | STABILIZATION OF THE TALLMANS' ISLAND WPCP | 9 | SUBSTANTIAL COMPLETION | Sep 2004 | Nov 2004 | Feb 2012 | Jul 2024
20231026 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-STAB | STABILIZATION OF THE TALLMANS' ISLAND WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2004 | Dec 2004 | Jul 2024 | Oct 2024
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | ID21-QEFN | ID21 TROPICAL STORM IDA QUEENS ENF BOILERS Replacement | 1 | DEVELOP SCOPE | Oct 2021 | Nov 2021 | Oct 2021 | Nov 2021
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | ID21-QEFN | ID21 TROPICAL STORM IDA QUEENS ENF BOILERS Replacement | 2 | PRELIMINARY DESIGN | Nov 2021 | Jan 2022 | Nov 2021 | Jan 2022
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | ID21-QEFN | ID21 TROPICAL STORM IDA QUEENS ENF BOILERS Replacement | 3 | FINAL DESIGN | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | ID21-QEFN | ID21 TROPICAL STORM IDA QUEENS ENF BOILERS Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2022 | Jun 2022 | Mar 2022 | Jun 2022
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | ID21-QEFN | ID21 TROPICAL STORM IDA QUEENS ENF BOILERS Replacement | 5 | CONSTRUCTION TO 25% | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | ID21-QEFN | ID21 TROPICAL STORM IDA QUEENS ENF BOILERS Replacement | 6 | CONSTRUCTION TO 50% | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | ID21-QEFN | ID21 TROPICAL STORM IDA QUEENS ENF BOILERS Replacement | 7 | CONSTRUCTION TO 75% | Dec 2022 | Apr 2023 | Dec 2022 | Apr 2023
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | ID21-QEFN | ID21 TROPICAL STORM IDA QUEENS ENF BOILERS Replacement | 8 | SUBSTANTIAL COMPLETION | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | ID21-QEFN | ID21 TROPICAL STORM IDA QUEENS ENF BOILERS Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251E | QUEENS CRS AIR COMPRESSORS REPLACEMENT | 1 | DEVELOP SCOPE | Oct 2016 | Dec 2016 | Oct 2016 | Dec 2016
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251E | QUEENS CRS AIR COMPRESSORS REPLACEMENT | 2 | PRELIMINARY DESIGN | Jan 2017 | Jun 2017 | Jan 2017 | Jun 2017
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251E | QUEENS CRS AIR COMPRESSORS REPLACEMENT | 3 | FINAL DESIGN | Jun 2017 | Dec 2017 | Jun 2017 | Dec 2017
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251E | QUEENS CRS AIR COMPRESSORS REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251E | QUEENS CRS AIR COMPRESSORS REPLACEMENT | 5 | CONSTRUCTION TO 25% | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251E | QUEENS CRS AIR COMPRESSORS REPLACEMENT | 6 | CONSTRUCTION TO 50% | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251E | QUEENS CRS AIR COMPRESSORS REPLACEMENT | 7 | CONSTRUCTION TO 75% | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251E | QUEENS CRS AIR COMPRESSORS REPLACEMENT | 8 | SUBSTANTIAL COMPLETION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251E | QUEENS CRS AIR COMPRESSORS REPLACEMENT | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Aug 2024 | Sep 2022 | Aug 2024
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251F | QUEENS CRS FIFTH FLOOR SLAB SECTIONS REPLACEMENT | 1 | DEVELOP SCOPE | Jun 2015 | Aug 2015 | Jun 2015 | Aug 2015
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251F | QUEENS CRS FIFTH FLOOR SLAB SECTIONS REPLACEMENT | 2 | PRELIMINARY DESIGN | Sep 2015 | Feb 2016 | Sep 2015 | Feb 2016
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251F | QUEENS CRS FIFTH FLOOR SLAB SECTIONS REPLACEMENT | 3 | FINAL DESIGN | Feb 2016 | Sep 2016 | Feb 2016 | Sep 2016
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251F | QUEENS CRS FIFTH FLOOR SLAB SECTIONS REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2016 | Apr 2017 | Sep 2016 | Apr 2017
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251F | QUEENS CRS FIFTH FLOOR SLAB SECTIONS REPLACEMENT | 5 | CONSTRUCTION TO 25% | Apr 2017 | Apr 2018 | Apr 2017 | Apr 2018
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251F | QUEENS CRS FIFTH FLOOR SLAB SECTIONS REPLACEMENT | 6 | CONSTRUCTION TO 50% | Apr 2018 | Apr 2019 | Apr 2018 | Apr 2021
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251F | QUEENS CRS FIFTH FLOOR SLAB SECTIONS REPLACEMENT | 7 | CONSTRUCTION TO 75% | Apr 2019 | Apr 2020 | Apr 2021 | Aug 2022
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251F | QUEENS CRS FIFTH FLOOR SLAB SECTIONS REPLACEMENT | 8 | SUBSTANTIAL COMPLETION | Apr 2020 | Apr 2021 | Aug 2022 | Aug 2023
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251F | QUEENS CRS FIFTH FLOOR SLAB SECTIONS REPLACEMENT | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2021 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-332N | QUEENS 8/10/12 GARAGE REHAB | 1 | DEVELOP SCOPE | Jul 2016 | Jul 2017 | Jul 2016 | Jul 2017
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-332N | QUEENS 8/10/12 GARAGE REHAB | 2 | PRELIMINARY DESIGN | Jul 2017 | Jul 2018 | Jul 2017 | Jul 2018
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-332N | QUEENS 8/10/12 GARAGE REHAB | 3 | FINAL DESIGN | Jul 2018 | Jul 2019 | Jul 2018 | Jul 2019
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-332N | QUEENS 8/10/12 GARAGE REHAB | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2020 | Jul 2019 | Aug 2020
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-332N | QUEENS 8/10/12 GARAGE REHAB | 5 | CONSTRUCTION TO 25% | Aug 2020 | Dec 2021 | Aug 2020 | Dec 2021
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-332N | QUEENS 8/10/12 GARAGE REHAB | 6 | CONSTRUCTION TO 50% | Dec 2021 | May 2023 | Dec 2021 | May 2023
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-332N | QUEENS 8/10/12 GARAGE REHAB | 7 | CONSTRUCTION TO 75% | May 2023 | Sep 2024 | May 2023 | Sep 2024
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-332N | QUEENS 8/10/12 GARAGE REHAB | 8 | SUBSTANTIAL COMPLETION | Sep 2024 | Jan 2026 | Sep 2024 | Jan 2026
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-332N | QUEENS 8/10/12 GARAGE REHAB | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2026 | Jun 2027 | Jan 2026 | Jun 2027
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-380K | Queens 7 A Hot Water Heaters Replacement | 1 | DEVELOP SCOPE | Feb 2023 | Mar 2023 | Feb 2023 | Mar 2023
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-380K | Queens 7 A Hot Water Heaters Replacement | 2 | PRELIMINARY DESIGN | Mar 2023 | Apr 2023 | Mar 2023 | Apr 2023
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-380K | Queens 7 A Hot Water Heaters Replacement | 3 | FINAL DESIGN | Apr 2023 | May 2023 | Apr 2023 | May 2023
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-380K | Queens 7 A Hot Water Heaters Replacement | 4 | BID AWARD AND REGISTER CONTRCT | May 2023 | Aug 2023 | May 2023 | Aug 2023
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-380K | Queens 7 A Hot Water Heaters Replacement | 5 | CONSTRUCTION TO 25% | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-380K | Queens 7 A Hot Water Heaters Replacement | 6 | CONSTRUCTION TO 50% | Dec 2023 | Apr 2024 | Dec 2023 | Apr 2024
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-380K | Queens 7 A Hot Water Heaters Replacement | 7 | CONSTRUCTION TO 75% | Apr 2024 | Aug 2024 | Apr 2024 | Aug 2024
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-380K | Queens 7 A Hot Water Heaters Replacement | 8 | SUBSTANTIAL COMPLETION | Aug 2024 | Aug 2025 | Aug 2024 | Aug 2025
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-380K | Queens 7 A Hot Water Heaters Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2025 | Aug 2026 | Aug 2025 | Aug 2026
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431 | QUEENS 1 GARAGE | 1 | DEVELOP SCOPE | Sep 2015 | Aug 2016 | Sep 2015 | Jul 2021
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431 | QUEENS 1 GARAGE | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2018 | Jul 2021 | Mar 2022
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431 | QUEENS 1 GARAGE | 3 | FINAL DESIGN | Sep 2018 | Feb 2020 | Mar 2022 | Jul 2023
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431 | QUEENS 1 GARAGE | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Jun 2021 | Jul 2023 | Dec 2024
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431 | QUEENS 1 GARAGE | 5 | CONSTRUCTION TO 25% | Jun 2021 | Oct 2022 | Dec 2024 | Apr 2026
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431 | QUEENS 1 GARAGE | 6 | CONSTRUCTION TO 50% | Oct 2022 | Mar 2024 | Apr 2026 | Aug 2027
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431 | QUEENS 1 GARAGE | 7 | CONSTRUCTION TO 75% | Mar 2024 | Jul 2025 | Aug 2027 | Jan 2029
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431 | QUEENS 1 GARAGE | 8 | SUBSTANTIAL COMPLETION | Jul 2025 | Dec 2026 | Jan 2029 | May 2029
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431 | QUEENS 1 GARAGE | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2026 | Apr 2028 | May 2029 | Oct 2029
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431A | Queens 1 Garage Rehabilitation | 1 | DEVELOP SCOPE | Feb 2020 | Mar 2020 | Feb 2020 | Mar 2020
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431A | Queens 1 Garage Rehabilitation | 2 | PRELIMINARY DESIGN | Mar 2020 | May 2020 | Mar 2020 | Dec 2020
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431A | Queens 1 Garage Rehabilitation | 3 | FINAL DESIGN | May 2020 | Jul 2020 | Dec 2020 | Oct 2021
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431A | Queens 1 Garage Rehabilitation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Oct 2021 | Oct 2022
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431A | Queens 1 Garage Rehabilitation | 5 | CONSTRUCTION TO 25% | Oct 2020 | Jan 2021 | Oct 2022 | Apr 2023
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431A | Queens 1 Garage Rehabilitation | 6 | CONSTRUCTION TO 50% | Jan 2021 | Apr 2021 | Apr 2023 | Oct 2023
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431A | Queens 1 Garage Rehabilitation | 7 | CONSTRUCTION TO 75% | Apr 2021 | Aug 2021 | Oct 2023 | Apr 2024
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431A | Queens 1 Garage Rehabilitation | 8 | SUBSTANTIAL COMPLETION | Aug 2021 | Jan 2022 | Apr 2024 | Oct 2024
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431A | Queens 1 Garage Rehabilitation | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2022 | Mar 2023 | Oct 2024 | Dec 2024
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431B | QUEENS 1 PARKING LOT | 1 | DEVELOP SCOPE | Feb 2023 | Mar 2023 | Feb 2023 | Mar 2023
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431B | QUEENS 1 PARKING LOT | 2 | PRELIMINARY DESIGN | Mar 2023 | May 2023 | Mar 2023 | May 2023
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431B | QUEENS 1 PARKING LOT | 3 | FINAL DESIGN | May 2023 | Jun 2023 | May 2023 | Jun 2023
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431B | QUEENS 1 PARKING LOT | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431B | QUEENS 1 PARKING LOT | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431B | QUEENS 1 PARKING LOT | 6 | CONSTRUCTION TO 50% | Jan 2024 | Apr 2024 | Jan 2024 | Apr 2024
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431B | QUEENS 1 PARKING LOT | 7 | CONSTRUCTION TO 75% | Apr 2024 | Aug 2024 | Apr 2024 | Aug 2024
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431B | QUEENS 1 PARKING LOT | 8 | SUBSTANTIAL COMPLETION | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431B | QUEENS 1 PARKING LOT | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Feb 2026 | Feb 2025 | Feb 2026
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-445 | Queens 6 Betts Ave Garage Rehab | 1 | DEVELOP SCOPE | Aug 2020 | Jul 2021 | Aug 2020 | Jul 2021
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-445 | Queens 6 Betts Ave Garage Rehab | 2 | PRELIMINARY DESIGN | Aug 2021 | Apr 2022 | Aug 2021 | Apr 2022
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-445 | Queens 6 Betts Ave Garage Rehab | 3 | FINAL DESIGN | Apr 2022 | Dec 2022 | Apr 2022 | Dec 2022
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-445 | Queens 6 Betts Ave Garage Rehab | 4 | BID AWARD AND REGISTER CONTRCT | Dec 2022 | Aug 2023 | Dec 2022 | Aug 2023
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-445 | Queens 6 Betts Ave Garage Rehab | 5 | CONSTRUCTION TO 25% | Aug 2023 | Aug 2024 | Aug 2023 | Aug 2024
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-445 | Queens 6 Betts Ave Garage Rehab | 6 | CONSTRUCTION TO 50% | Aug 2024 | Aug 2025 | Aug 2024 | Aug 2025
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-445 | Queens 6 Betts Ave Garage Rehab | 7 | CONSTRUCTION TO 75% | Aug 2025 | Aug 2026 | Aug 2025 | Aug 2026
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-445 | Queens 6 Betts Ave Garage Rehab | 8 | SUBSTANTIAL COMPLETION | Aug 2026 | Aug 2027 | Aug 2026 | Aug 2027
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-445 | Queens 6 Betts Ave Garage Rehab | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2027 | Jul 2029 | Aug 2027 | Jul 2029
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-449B | Queens 5/5A Site Drainage Rehabilitation | 1 | DEVELOP SCOPE | Mar 2019 | Jul 2019 | Mar 2019 | Jul 2019
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-449B | Queens 5/5A Site Drainage Rehabilitation | 2 | PRELIMINARY DESIGN | Jul 2019 | Jan 2020 | Jul 2019 | Jan 2022
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-449B | Queens 5/5A Site Drainage Rehabilitation | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2022 | Mar 2024
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-449B | Queens 5/5A Site Drainage Rehabilitation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | May 2021 | Mar 2024 | Jan 2025
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-449B | Queens 5/5A Site Drainage Rehabilitation | 5 | CONSTRUCTION TO 25% | May 2021 | Nov 2021 | Jan 2025 | Jul 2025
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-449B | Queens 5/5A Site Drainage Rehabilitation | 6 | CONSTRUCTION TO 50% | Nov 2021 | May 2022 | Jul 2025 | Jan 2026
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-449B | Queens 5/5A Site Drainage Rehabilitation | 7 | CONSTRUCTION TO 75% | May 2022 | Nov 2022 | Jan 2026 | Jul 2026
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-449B | Queens 5/5A Site Drainage Rehabilitation | 8 | SUBSTANTIAL COMPLETION | Nov 2022 | Apr 2023 | Jul 2026 | Dec 2026
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-449B | Queens 5/5A Site Drainage Rehabilitation | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2023 | May 2024 | Dec 2026 | Jan 2028
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-464H | Queens Flushing Ave Enforcement Garage Roof Replacement | 1 | DEVELOP SCOPE | Jul 2017 | Aug 2017 | Jul 2017 | Aug 2017
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-464H | Queens Flushing Ave Enforcement Garage Roof Replacement | 2 | PRELIMINARY DESIGN | Aug 2017 | Feb 2018 | Aug 2017 | Feb 2018
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-464H | Queens Flushing Ave Enforcement Garage Roof Replacement | 3 | FINAL DESIGN | Feb 2018 | Feb 2019 | Feb 2018 | Feb 2019
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-464H | Queens Flushing Ave Enforcement Garage Roof Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2019 | Feb 2020 | Feb 2019 | Feb 2020
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-464H | Queens Flushing Ave Enforcement Garage Roof Replacement | 5 | CONSTRUCTION TO 25% | Feb 2020 | Feb 2021 | Feb 2020 | Feb 2021
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-464H | Queens Flushing Ave Enforcement Garage Roof Replacement | 6 | CONSTRUCTION TO 50% | Feb 2021 | Feb 2022 | Feb 2021 | Feb 2022
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-464H | Queens Flushing Ave Enforcement Garage Roof Replacement | 7 | CONSTRUCTION TO 75% | Feb 2022 | Feb 2023 | Feb 2022 | Feb 2023
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-464H | Queens Flushing Ave Enforcement Garage Roof Replacement | 8 | SUBSTANTIAL COMPLETION | Feb 2023 | Jul 2024 | Feb 2023 | Jul 2024
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-464H | Queens Flushing Ave Enforcement Garage Roof Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2024 | Feb 2026 | Jul 2024 | Feb 2026
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S216-402F | NORTH SHORE MTS FUELING SYSTEM | 1 | DEVELOP SCOPE | Jun 2020 | Jul 2020 | Jun 2020 | Jul 2020
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S216-402F | NORTH SHORE MTS FUELING SYSTEM | 2 | PRELIMINARY DESIGN | Jul 2020 | Nov 2020 | Jul 2020 | Nov 2020
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S216-402F | NORTH SHORE MTS FUELING SYSTEM | 3 | FINAL DESIGN | Nov 2020 | Mar 2021 | Nov 2020 | Mar 2021
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S216-402F | NORTH SHORE MTS FUELING SYSTEM | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2021 | Mar 2022 | Mar 2021 | Mar 2022
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S216-402F | NORTH SHORE MTS FUELING SYSTEM | 5 | CONSTRUCTION TO 25% | Mar 2022 | Oct 2022 | Mar 2022 | Oct 2022
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S216-402F | NORTH SHORE MTS FUELING SYSTEM | 6 | CONSTRUCTION TO 50% | Oct 2022 | May 2023 | Oct 2022 | May 2023
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S216-402F | NORTH SHORE MTS FUELING SYSTEM | 7 | CONSTRUCTION TO 75% | May 2023 | Nov 2023 | May 2023 | Nov 2023
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S216-402F | NORTH SHORE MTS FUELING SYSTEM | 8 | SUBSTANTIAL COMPLETION | Nov 2023 | Jun 2024 | Nov 2023 | Jun 2024
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | S216-402F | NORTH SHORE MTS FUELING SYSTEM | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2024 | Jun 2025 | Jun 2024 | Jun 2025
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | SANDQ14EL | Hurricane Sandy Queens 14 Electrical Replacement | 1 | DEVELOP SCOPE | Aug 2014 | Oct 2014 | Aug 2014 | Oct 2014
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | SANDQ14EL | Hurricane Sandy Queens 14 Electrical Replacement | 2 | PRELIMINARY DESIGN | Oct 2014 | Oct 2015 | Oct 2014 | Oct 2015
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | SANDQ14EL | Hurricane Sandy Queens 14 Electrical Replacement | 3 | FINAL DESIGN | Oct 2015 | Oct 2016 | Oct 2015 | Oct 2016
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | SANDQ14EL | Hurricane Sandy Queens 14 Electrical Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2016 | Oct 2017 | Oct 2016 | Oct 2017
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | SANDQ14EL | Hurricane Sandy Queens 14 Electrical Replacement | 5 | CONSTRUCTION TO 25% | Oct 2017 | Oct 2018 | Oct 2017 | Oct 2018
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | SANDQ14EL | Hurricane Sandy Queens 14 Electrical Replacement | 6 | CONSTRUCTION TO 50% | Oct 2018 | Oct 2019 | Oct 2018 | Oct 2019
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | SANDQ14EL | Hurricane Sandy Queens 14 Electrical Replacement | 7 | CONSTRUCTION TO 75% | Oct 2019 | Oct 2020 | Oct 2019 | Oct 2020
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | SANDQ14EL | Hurricane Sandy Queens 14 Electrical Replacement | 8 | SUBSTANTIAL COMPLETION | Oct 2020 | Jun 2022 | Oct 2020 | Jun 2022
20231026 | QUEENS | 827 | DEPARTMENT OF SANITATION | SANDQ14EL | Hurricane Sandy Queens 14 Electrical Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Mar 2025 | Jun 2022 | Mar 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT212 | DOT- 32-11 Harper St Roll Up Doors | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT212 | DOT- 32-11 Harper St Roll Up Doors | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT212 | DOT- 32-11 Harper St Roll Up Doors | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT212 | DOT- 32-11 Harper St Roll Up Doors | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT212 | DOT- 32-11 Harper St Roll Up Doors | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT212 | DOT- 32-11 Harper St Roll Up Doors | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT212 | DOT- 32-11 Harper St Roll Up Doors | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT212 | DOT- 32-11 Harper St Roll Up Doors | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT212 | DOT- 32-11 Harper St Roll Up Doors | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT212 | DOT- 32-11 Harper St Roll Up Doors | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HB1070NB | Protective Coating of N blvd Bridges over Flushing River | 1 | DEVELOP SCOPE | Jun 2019 | Jun 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HB1070NB | Protective Coating of N blvd Bridges over Flushing River | 2 | DEVELOP SCOPE | Jun 2020 | Jun 2024 | Jun 2019 | Jun 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HB1070NB | Protective Coating of N blvd Bridges over Flushing River | 3 | DESIGN START | Jun 2024 | Jun 2026 | Jun 2020 | Jun 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HB1070NB | Protective Coating of N blvd Bridges over Flushing River | 5 | CONSTRUCTION START | Jun 2024 | Jun 2026 | Jun 2024 | Jun 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HB1070QN | Protective Coating of Various Bridges in Queens | 1 | DEVELOP SCOPE | Jun 2019 | Jun 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HB1070QN | Protective Coating of Various Bridges in Queens | 2 | DEVELOP SCOPE | Jun 2020 | Jun 2024 | Jun 2020 | Jun 2021
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HB1070QN | Protective Coating of Various Bridges in Queens | 3 | DESIGN START | Jun 2024 | Jun 2026 | Jun 2021 | Jun 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HB1070QN | Protective Coating of Various Bridges in Queens | 5 | CONSTRUCTION START | Jun 2024 | Jun 2026 | Jun 2025 | Jun 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBGATES | Barrier Gates | 1 | DEVELOP SCOPE | Jun 2019 | Jun 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBGATES | Barrier Gates | 2 | DESIGN START | Jun 2020 | Jun 2024 | Jun 2019 | Jun 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBGATES | Barrier Gates | 3 | CONSTRUCTION START | Jun 2024 | Jun 2026 | Jun 2020 | Jun 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBGATES | Barrier Gates | 5 | CONSTRUCTION START | Jun 2024 | Jun 2026 | Jun 2024 | Jun 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1114 | HEMPSTEAD AVE BR/CIP 2231780 | 1 | DEVELOP SCOPE | Jul 2004 | Jun 2005 | Oct 2010 | Feb 2011
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1114 | HEMPSTEAD AVE BR/CIP 2231780 | 2 | DESIGN START | Jul 2005 | Jun 2009 | Jun 2011 | Jun 2019
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1114 | HEMPSTEAD AVE BR/CIP 2231780 | 3 | CONSTRUCTION START | Jun 2009 | Jun 2011 | Jun 2019 | Jun 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1115 | UNION TURNPIKE / CROSS ISLAND PKWY 2-23185-0 | 1 | DEVELOP SCOPE | Jul 2005 | Jun 2006 | Dec 2016 | Dec 2016
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1115 | UNION TURNPIKE / CROSS ISLAND PKWY 2-23185-0 | 2 | DESIGN START | Jul 2006 | Jun 2010 | Jun 2016 | Jun 2016
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1115 | UNION TURNPIKE / CROSS ISLAND PKWY 2-23185-0 | 3 | CONSTRUCTION START | Jun 2010 | Jun 2012 | Jun 2016 | Jun 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1137 | RECON ELLIOT AVE BRIDGE OVER QUEENS BLVD 2-24816-0 | 1 | DEVELOP SCOPE | Jul 2006 | Jun 2007 | Jun 2020 | Jun 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1137 | RECON ELLIOT AVE BRIDGE OVER QUEENS BLVD 2-24816-0 | 2 | DESIGN START | Jul 2007 | Jun 2011 | Jun 2023 | Jun 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1137 | RECON ELLIOT AVE BRIDGE OVER QUEENS BLVD 2-24816-0 | 3 | CONSTRUCTION START | Jun 2011 | Jun 2013 | Jun 2023 | Jun 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1203 | RECON ROOSEVELT AVE BR OVER VAN WYCK EXPWY QUEENS 2-240507 | 1 | DEVELOP SCOPE | Jul 2004 | Jun 2005
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1203 | RECON ROOSEVELT AVE BR OVER VAN WYCK EXPWY QUEENS 2-240507 | 2 | DESIGN START | Jul 2005 | Jun 2009 | Jul 2022 | Jul 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1203 | RECON ROOSEVELT AVE BR OVER VAN WYCK EXPWY QUEENS 2-240507 | 3 | CONSTRUCTION START | Jun 2009 | Jun 2011 | Jul 2022 | Jul 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1203 | RECON ROOSEVELT AVE BR OVER VAN WYCK EXPWY QUEENS 2-240507 | 5 | CONSTRUCTION START | Jun 2009 | Jun 2011 | Jul 2023 | Jun 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1208 | LINDEN BLVD BRIDGE OVER CROSS ISLAND PKWY , QUEENS 2-23175-0 | 1 | DEVELOP SCOPE | Jun 2006 | Jun 2007
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1208 | LINDEN BLVD BRIDGE OVER CROSS ISLAND PKWY , QUEENS 2-23175-0 | 2 | DESIGN START | Jun 2007 | Jun 2011 | May 2018 | Mar 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1208 | LINDEN BLVD BRIDGE OVER CROSS ISLAND PKWY , QUEENS 2-23175-0 | 3 | CONSTRUCTION START | Jun 2011 | Jun 2013 | Apr 2021 | Apr 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1208 | LINDEN BLVD BRIDGE OVER CROSS ISLAND PKWY , QUEENS 2-23175-0 | 5 | CONSTRUCTION START | Jun 2011 | Jun 2013 | Apr 2025 | Jun 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1209 | SUNRISE HWY W/B BRIDGE OVER BLP W/B, QUEENS 2-23166-0 | 1 | DEVELOP SCOPE | Jun 2006 | Jun 2007
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1209 | SUNRISE HWY W/B BRIDGE OVER BLP W/B, QUEENS 2-23166-0 | 2 | DESIGN START | Jun 2007 | Jun 2011 | May 2023 | Jan 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1209 | SUNRISE HWY W/B BRIDGE OVER BLP W/B, QUEENS 2-23166-0 | 3 | CONSTRUCTION START | Jun 2011 | Jun 2013 | Feb 2021 | Feb 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1209 | SUNRISE HWY W/B BRIDGE OVER BLP W/B, QUEENS 2-23166-0 | 5 | CONSTRUCTION START | Jun 2011 | Jun 2013 | Feb 2025 | Apr 2032
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ224766 | FOREST PARK DRIVE OVER ABANDONED LIRR BIN 2247660 | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ224766 | FOREST PARK DRIVE OVER ABANDONED LIRR BIN 2247660 | 2 | DESIGN START | Jun 2022 | Jun 2026 | Jun 2022 | Jun 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ224766 | FOREST PARK DRIVE OVER ABANDONED LIRR BIN 2247660 | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2023 | Jun 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ224766 | FOREST PARK DRIVE OVER ABANDONED LIRR BIN 2247660 | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2027 | Jun 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ224814 | Meridian Road over Stream North of LIE BIN 2248140 | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ224814 | Meridian Road over Stream North of LIE BIN 2248140 | 2 | DESIGN START | Jun 2022 | Jun 2026 | Jun 2021 | Jun 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ224814 | Meridian Road over Stream North of LIE BIN 2248140 | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2022 | Jun 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ224814 | Meridian Road over Stream North of LIE BIN 2248140 | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ224837 | BOATHOUSE BRIDGE OVER AQUACADE LAKE BIN 2248379 | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ224837 | BOATHOUSE BRIDGE OVER AQUACADE LAKE BIN 2248379 | 2 | DESIGN START | Jun 2022 | Jun 2026 | Jun 2021 | Jun 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ224837 | BOATHOUSE BRIDGE OVER AQUACADE LAKE BIN 2248379 | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2022 | Jun 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ224837 | BOATHOUSE BRIDGE OVER AQUACADE LAKE BIN 2248379 | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ231620 | Farmers Boulevard Over BSOP BIN 2231620 | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ231620 | Farmers Boulevard Over BSOP BIN 2231620 | 2 | DESIGN START | Jun 2024 | Jun 2028 | Jun 2023 | Jun 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ231620 | Farmers Boulevard Over BSOP BIN 2231620 | 3 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jun 2024 | Jun 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ231620 | Farmers Boulevard Over BSOP BIN 2231620 | 5 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jun 2028 | Jun 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ231710 | Merrick Blvd over BLP NB BIN 2231710 | 1 | DEVELOP SCOPE | Jun 2019 | Jun 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ231710 | Merrick Blvd over BLP NB BIN 2231710 | 2 | DESIGN START | Jun 2020 | Jun 2024 | Jun 2021 | Jun 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ231710 | Merrick Blvd over BLP NB BIN 2231710 | 3 | CONSTRUCTION START | Jun 2024 | Jun 2026 | Jun 2022 | Jun 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ231710 | Merrick Blvd over BLP NB BIN 2231710 | 5 | CONSTRUCTION START | Jun 2024 | Jun 2026 | Jun 2026 | Jun 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ231720 | Merrick Blvd over BLP SB BIN 2231720 | 1 | DEVELOP SCOPE | Jun 2019 | Jun 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ231720 | Merrick Blvd over BLP SB BIN 2231720 | 2 | DESIGN START | Jun 2020 | Jun 2024 | Jun 2021 | Jun 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ231720 | Merrick Blvd over BLP SB BIN 2231720 | 3 | CONSTRUCTION START | Jun 2024 | Jun 2026 | Jun 2022 | Jun 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ231720 | Merrick Blvd over BLP SB BIN 2231720 | 5 | CONSTRUCTION START | Jun 2024 | Jun 2026 | Jun 2026 | Jun 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ231880 | CROCHERON PARK PEDESTRIAN OVER BCIP BIN 223188 | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ231880 | CROCHERON PARK PEDESTRIAN OVER BCIP BIN 223188 | 2 | DESIGN START | Jun 2022 | Jun 2026 | Jun 2021 | Jun 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ231880 | CROCHERON PARK PEDESTRIAN OVER BCIP BIN 223188 | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2022 | Jun 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ231880 | CROCHERON PARK PEDESTRIAN OVER BCIP BIN 223188 | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ49AV | 49TH AVE OVER LIRR, AMT, CON NE (BIN2247290) | 1 | DEVELOP SCOPE | Jul 2015 | Jun 2016
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ49AV | 49TH AVE OVER LIRR, AMT, CON NE (BIN2247290) | 2 | DESIGN START | Jun 2016 | Jun 2020 | Jun 2022 | Dec 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ49AV | 49TH AVE OVER LIRR, AMT, CON NE (BIN2247290) | 3 | CONSTRUCTION START | Jun 2020 | Jun 2022 | Aug 2017 | Oct 2021
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ49AV | 49TH AVE OVER LIRR, AMT, CON NE (BIN2247290) | 5 | CONSTRUCTION START | Jun 2020 | Jun 2022 | Aug 2021 | Apr 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ8019 | WOODHAVEN BLVD OVER ATLANTIC AVE BIN 2248019 | 1 | DEVELOP SCOPE | Jun 2016 | Jun 2017
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ8019 | WOODHAVEN BLVD OVER ATLANTIC AVE BIN 2248019 | 2 | DESIGN START | Jun 2017 | Jun 2021 | May 2018 | Jul 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ8019 | WOODHAVEN BLVD OVER ATLANTIC AVE BIN 2248019 | 3 | CONSTRUCTION START | Jun 2021 | Jun 2023 | Jun 2021 | Aug 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ8019 | WOODHAVEN BLVD OVER ATLANTIC AVE BIN 2248019 | 5 | CONSTRUCTION START | Jun 2021 | Jun 2023 | Aug 2025 | Oct 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23081 | ASTORIA BLVD EB/ 278I( BQE WEST LEG) BIN# 2230810 | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jul 2017 | Sep 2017
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23081 | ASTORIA BLVD EB/ 278I( BQE WEST LEG) BIN# 2230810 | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Aug 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23081 | ASTORIA BLVD EB/ 278I( BQE WEST LEG) BIN# 2230810 | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Aug 2022 | Feb 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23081 | ASTORIA BLVD EB/ 278I( BQE WEST LEG) BIN# 2230810 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Feb 2023 | May 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23081 | ASTORIA BLVD EB/ 278I( BQE WEST LEG) BIN# 2230810 | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | May 2023 | Sep 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23081 | ASTORIA BLVD EB/ 278I( BQE WEST LEG) BIN# 2230810 | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Sep 2023 | Jan 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23081 | ASTORIA BLVD EB/ 278I( BQE WEST LEG) BIN# 2230810 | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jan 2024 | May 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23081 | ASTORIA BLVD EB/ 278I( BQE WEST LEG) BIN# 2230810 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | May 2024 | Aug 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23081 | ASTORIA BLVD EB/ 278I( BQE WEST LEG) BIN# 2230810 | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Aug 2024 | Oct 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23081 | ASTORIA BLVD EB/ 278I( BQE WEST LEG) BIN# 2230810 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Oct 2024 | Nov 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23157 | COHANCY STREET over BSOP BIN 2231570 | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23157 | COHANCY STREET over BSOP BIN 2231570 | 2 | DESIGN START | Jun 2023 | Jun 2027 | Jun 2022 | Jun 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23157 | COHANCY STREET over BSOP BIN 2231570 | 3 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2023 | Jun 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23157 | COHANCY STREET over BSOP BIN 2231570 | 5 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2027 | Jun 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23165 | Sunrise Hwy WB over BLP EB BIN 2231650 | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2021
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23165 | Sunrise Hwy WB over BLP EB BIN 2231650 | 2 | DESIGN START | Jun 2021 | Jun 2025 | Jun 2025 | Jun 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23165 | Sunrise Hwy WB over BLP EB BIN 2231650 | 3 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Jun 2026 | Jun 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23165 | Sunrise Hwy WB over BLP EB BIN 2231650 | 5 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Jun 2030 | Jun 2032
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23176 | BCIP OVER DUTCH BROADWAY-115 AVE BIN 2231760 | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23176 | BCIP OVER DUTCH BROADWAY-115 AVE BIN 2231760 | 2 | DESIGN START | Jun 2022 | Jun 2026 | May 2017 | Oct 2017
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23176 | BCIP OVER DUTCH BROADWAY-115 AVE BIN 2231760 | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Sep 2018 | Jun 2021
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23176 | BCIP OVER DUTCH BROADWAY-115 AVE BIN 2231760 | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | May 2022 | Aug 2034
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24066 | RIKERS ISLAND BRIDGE over RIKERS ISLAND CHANNEL 2240660 | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24066 | RIKERS ISLAND BRIDGE over RIKERS ISLAND CHANNEL 2240660 | 2 | DESIGN START | Jun 2023 | Jun 2027 | Jun 2022 | Jun 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24066 | RIKERS ISLAND BRIDGE over RIKERS ISLAND CHANNEL 2240660 | 3 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2023 | Jun 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24066 | RIKERS ISLAND BRIDGE over RIKERS ISLAND CHANNEL 2240660 | 5 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2027 | Jun 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24718 | GRAND AVENUE over LIRR MAIN LINE BIN 2247180 | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24718 | GRAND AVENUE over LIRR MAIN LINE BIN 2247180 | 2 | DESIGN START | Jun 2023 | Jun 2027 | Jun 2022 | Jun 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24718 | GRAND AVENUE over LIRR MAIN LINE BIN 2247180 | 3 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2023 | Jun 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24718 | GRAND AVENUE over LIRR MAIN LINE BIN 2247180 | 5 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2027 | Jun 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24750 | METROPOLITAN AVE OVER CSX TRANSPORT | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24750 | METROPOLITAN AVE OVER CSX TRANSPORT | 2 | DESIGN START | Jun 2022 | Jun 2026 | Apr 2017 | Sep 2017
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24750 | METROPOLITAN AVE OVER CSX TRANSPORT | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Apr 2018 | May 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24750 | METROPOLITAN AVE OVER CSX TRANSPORT | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Apr 2023 | Jul 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24815 | WOODHAVEN BLVD/ QUEENS BLVD BIN# 2248159 | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2023 | Sep 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24815 | WOODHAVEN BLVD/ QUEENS BLVD BIN# 2248159 | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2023 | Jan 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24815 | WOODHAVEN BLVD/ QUEENS BLVD BIN# 2248159 | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2024 | Jul 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24815 | WOODHAVEN BLVD/ QUEENS BLVD BIN# 2248159 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2024 | Oct 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24815 | WOODHAVEN BLVD/ QUEENS BLVD BIN# 2248159 | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2024 | Feb 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24815 | WOODHAVEN BLVD/ QUEENS BLVD BIN# 2248159 | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2025 | Jun 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24815 | WOODHAVEN BLVD/ QUEENS BLVD BIN# 2248159 | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2025 | Oct 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24815 | WOODHAVEN BLVD/ QUEENS BLVD BIN# 2248159 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2025 | Jan 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24815 | WOODHAVEN BLVD/ QUEENS BLVD BIN# 2248159 | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2026 | Mar 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24815 | WOODHAVEN BLVD/ QUEENS BLVD BIN# 2248159 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2026 | Apr 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24823 | BEACH CHANNEL DR WB over DR EB BIN 2248230 | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24823 | BEACH CHANNEL DR WB over DR EB BIN 2248230 | 2 | DESIGN START | Jun 2022 | Jun 2026 | Jun 2021 | Jun 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24823 | BEACH CHANNEL DR WB over DR EB BIN 2248230 | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2022 | Jun 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24823 | BEACH CHANNEL DR WB over DR EB BIN 2248230 | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA26614 | HEMPSTEAD AVE OVER BCIP RAMP NB BIN 2266149 | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA26614 | HEMPSTEAD AVE OVER BCIP RAMP NB BIN 2266149 | 2 | DESIGN START | Jun 2024 | Jun 2028 | Jul 2023 | Jun 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA26614 | HEMPSTEAD AVE OVER BCIP RAMP NB BIN 2266149 | 3 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jun 2024 | Jun 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA26614 | HEMPSTEAD AVE OVER BCIP RAMP NB BIN 2266149 | 5 | CONSTRUCTION START | Jun 2028 | Jun 2030 | Jun 2028 | Jun 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQENB012 | Emergency Fender System Northern Blvd WB/EB | 1 | DEVELOP SCOPE | Jun 2019 | Jun 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQENB012 | Emergency Fender System Northern Blvd WB/EB | 2 | DESIGN START | Jun 2020 | Jun 2024 | Jun 2019 | Jun 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQENB012 | Emergency Fender System Northern Blvd WB/EB | 3 | CONSTRUCTION START | Jun 2024 | Jun 2026 | Jun 2020 | Jun 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQENB012 | Emergency Fender System Northern Blvd WB/EB | 5 | CONSTRUCTION START | Jun 2024 | Jun 2026 | Jun 2024 | Jun 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21B | Citywide Milling - Queens | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21B | Citywide Milling - Queens | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21B | Citywide Milling - Queens | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21B | Citywide Milling - Queens | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21B | Citywide Milling - Queens | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21B | Citywide Milling - Queens | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21B | Citywide Milling - Queens | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21B | Citywide Milling - Queens | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21B | Citywide Milling - Queens | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21B | Citywide Milling - Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HW349TOUR | NYS Touring Route Program | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HW349TOUR | NYS Touring Route Program | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HW349TOUR | NYS Touring Route Program | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HW349TOUR | NYS Touring Route Program | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HW349TOUR | NYS Touring Route Program | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HW349TOUR | NYS Touring Route Program | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HW349TOUR | NYS Touring Route Program | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HW349TOUR | NYS Touring Route Program | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HW349TOUR | NYS Touring Route Program | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HW349TOUR | NYS Touring Route Program | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWCOINFAC | METER PROCESSING FACILITY REHABILITATION | 1 | DEVELOP SCOPE | Jun 2009 | Sep 2009 | Jun 2019 | Sep 2019
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWCOINFAC | METER PROCESSING FACILITY REHABILITATION | 2 | PRELIMINARY DESIGN | Sep 2009 | Jan 2010 | Sep 2019 | Jun 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWCOINFAC | METER PROCESSING FACILITY REHABILITATION | 3 | FINAL DESIGN | Jan 2010 | Jul 2010 | Jul 2027 | Dec 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWCOINFAC | METER PROCESSING FACILITY REHABILITATION | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2010 | Oct 2010 | Dec 2027 | Mar 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWCOINFAC | METER PROCESSING FACILITY REHABILITATION | 5 | CONSTRUCTION TO 25% | Oct 2010 | Feb 2011 | Mar 2028 | Jul 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWCOINFAC | METER PROCESSING FACILITY REHABILITATION | 6 | CONSTRUCTION TO 50% | Feb 2011 | Jun 2011 | Jul 2028 | Nov 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWCOINFAC | METER PROCESSING FACILITY REHABILITATION | 7 | CONSTRUCTION TO 75% | Jun 2011 | Oct 2011 | Nov 2028 | Mar 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWCOINFAC | METER PROCESSING FACILITY REHABILITATION | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2011 | Jan 2012 | Mar 2029 | Jun 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWCOINFAC | METER PROCESSING FACILITY REHABILITATION | 9 | SUBSTANTIAL COMPLETION | Jan 2012 | Mar 2012 | Jun 2029 | Aug 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWCOINFAC | METER PROCESSING FACILITY REHABILITATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2012 | Apr 2012 | Aug 2029 | Oct 2033
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103100 | RECON OF MYRTLE AVE / UNION TURNPIKE ENTRANCE TO FOREST PK | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2022 | Sep 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103100 | RECON OF MYRTLE AVE / UNION TURNPIKE ENTRANCE TO FOREST PK | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2022 | Jan 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103100 | RECON OF MYRTLE AVE / UNION TURNPIKE ENTRANCE TO FOREST PK | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jan 2023 | Jul 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103100 | RECON OF MYRTLE AVE / UNION TURNPIKE ENTRANCE TO FOREST PK | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2023 | Oct 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103100 | RECON OF MYRTLE AVE / UNION TURNPIKE ENTRANCE TO FOREST PK | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Oct 2023 | Feb 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103100 | RECON OF MYRTLE AVE / UNION TURNPIKE ENTRANCE TO FOREST PK | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Feb 2024 | Jun 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103100 | RECON OF MYRTLE AVE / UNION TURNPIKE ENTRANCE TO FOREST PK | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jun 2024 | Oct 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103100 | RECON OF MYRTLE AVE / UNION TURNPIKE ENTRANCE TO FOREST PK | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Oct 2024 | Jan 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103100 | RECON OF MYRTLE AVE / UNION TURNPIKE ENTRANCE TO FOREST PK | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jan 2025 | Mar 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103100 | RECON OF MYRTLE AVE / UNION TURNPIKE ENTRANCE TO FOREST PK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Mar 2025 | Jul 2031
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10312 | Safety Improvements at St. Margaret's School | 1 | DEVELOP SCOPE | Jun 2015 | Aug 2015 | Jun 2026 | Aug 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10312 | Safety Improvements at St. Margaret's School | 2 | PRELIMINARY DESIGN | Aug 2015 | Dec 2015 | Aug 2026 | Dec 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10312 | Safety Improvements at St. Margaret's School | 3 | FINAL DESIGN | Dec 2015 | Jun 2016 | Dec 2026 | Jun 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10312 | Safety Improvements at St. Margaret's School | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2016 | Sep 2016 | Jun 2027 | Sep 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10312 | Safety Improvements at St. Margaret's School | 5 | CONSTRUCTION TO 25% | Sep 2016 | Jan 2017 | Sep 2027 | Jan 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10312 | Safety Improvements at St. Margaret's School | 6 | CONSTRUCTION TO 50% | Jan 2017 | May 2017 | Jan 2028 | May 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10312 | Safety Improvements at St. Margaret's School | 7 | CONSTRUCTION TO 75% | May 2017 | Sep 2017 | May 2028 | Sep 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10312 | Safety Improvements at St. Margaret's School | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Dec 2017 | Sep 2028 | Dec 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10312 | Safety Improvements at St. Margaret's School | 9 | SUBSTANTIAL COMPLETION | Dec 2017 | Feb 2018 | Dec 2028 | Feb 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10312 | Safety Improvements at St. Margaret's School | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2018 | Mar 2018 | Feb 2029 | Jun 2031
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10323 | Upgrades within the Bayside BID | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2021 | Sep 2021
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10323 | Upgrades within the Bayside BID | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2021 | Jan 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10323 | Upgrades within the Bayside BID | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2022 | Jul 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10323 | Upgrades within the Bayside BID | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2022 | Oct 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10323 | Upgrades within the Bayside BID | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2022 | Feb 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10323 | Upgrades within the Bayside BID | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2023 | Jun 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10323 | Upgrades within the Bayside BID | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2023 | Oct 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10323 | Upgrades within the Bayside BID | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2023 | Jan 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10323 | Upgrades within the Bayside BID | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2024 | Mar 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10323 | Upgrades within the Bayside BID | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2024 | Apr 2031
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10324 | Parsons Blvd & 84th Ave & Hoover Ave Ped Safety Improvements | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10324 | Parsons Blvd & 84th Ave & Hoover Ave Ped Safety Improvements | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10324 | Parsons Blvd & 84th Ave & Hoover Ave Ped Safety Improvements | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10324 | Parsons Blvd & 84th Ave & Hoover Ave Ped Safety Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10324 | Parsons Blvd & 84th Ave & Hoover Ave Ped Safety Improvements | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10324 | Parsons Blvd & 84th Ave & Hoover Ave Ped Safety Improvements | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10324 | Parsons Blvd & 84th Ave & Hoover Ave Ped Safety Improvements | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10324 | Parsons Blvd & 84th Ave & Hoover Ave Ped Safety Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10324 | Parsons Blvd & 84th Ave & Hoover Ave Ped Safety Improvements | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10324 | Parsons Blvd & 84th Ave & Hoover Ave Ped Safety Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Apr 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10326 | Long Island City Bikeway Improvements | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2022 | Sep 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10326 | Long Island City Bikeway Improvements | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2022 | Jan 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10326 | Long Island City Bikeway Improvements | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2023 | Jul 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10326 | Long Island City Bikeway Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2023 | Oct 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10326 | Long Island City Bikeway Improvements | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2023 | Feb 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10326 | Long Island City Bikeway Improvements | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2024 | Jun 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10326 | Long Island City Bikeway Improvements | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2024 | Oct 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10326 | Long Island City Bikeway Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2024 | Jan 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10326 | Long Island City Bikeway Improvements | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2025 | Mar 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10326 | Long Island City Bikeway Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2025 | Jul 2031
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10327 | Dutch Kills Pedestrian Safety Project | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2027 | Sep 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10327 | Dutch Kills Pedestrian Safety Project | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2027 | Jan 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10327 | Dutch Kills Pedestrian Safety Project | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2028 | Jul 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10327 | Dutch Kills Pedestrian Safety Project | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2028 | Oct 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10327 | Dutch Kills Pedestrian Safety Project | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2028 | Feb 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10327 | Dutch Kills Pedestrian Safety Project | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2029 | Jun 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10327 | Dutch Kills Pedestrian Safety Project | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2029 | Oct 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10327 | Dutch Kills Pedestrian Safety Project | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2029 | Jan 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10327 | Dutch Kills Pedestrian Safety Project | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2030 | Mar 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10327 | Dutch Kills Pedestrian Safety Project | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2030 | Jun 2031
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10328 | A Safer Intersection at 71st Avenue and Austin Street | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2023 | Sep 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10328 | A Safer Intersection at 71st Avenue and Austin Street | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2023 | Jan 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10328 | A Safer Intersection at 71st Avenue and Austin Street | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2024 | Jul 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10328 | A Safer Intersection at 71st Avenue and Austin Street | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2024 | Oct 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10328 | A Safer Intersection at 71st Avenue and Austin Street | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2024 | Feb 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10328 | A Safer Intersection at 71st Avenue and Austin Street | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2025 | Jun 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10328 | A Safer Intersection at 71st Avenue and Austin Street | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2025 | Oct 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10328 | A Safer Intersection at 71st Avenue and Austin Street | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2025 | Jan 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10328 | A Safer Intersection at 71st Avenue and Austin Street | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2026 | Mar 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10328 | A Safer Intersection at 71st Avenue and Austin Street | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2026 | Jul 2031
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10330 | Median and Street Reconstruction in Broad Channel | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2024 | Sep 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10330 | Median and Street Reconstruction in Broad Channel | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2024 | Jan 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10330 | Median and Street Reconstruction in Broad Channel | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2025 | Jul 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10330 | Median and Street Reconstruction in Broad Channel | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2025 | Oct 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10330 | Median and Street Reconstruction in Broad Channel | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2025 | Feb 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10330 | Median and Street Reconstruction in Broad Channel | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2026 | Jun 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10330 | Median and Street Reconstruction in Broad Channel | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2026 | Oct 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10330 | Median and Street Reconstruction in Broad Channel | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2026 | Jan 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10330 | Median and Street Reconstruction in Broad Channel | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2027 | Mar 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10330 | Median and Street Reconstruction in Broad Channel | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2027 | Apr 2031
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10332 | Reconstruct Curbs along median of Rockaway Freeway | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2028 | Sep 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10332 | Reconstruct Curbs along median of Rockaway Freeway | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2028 | Jan 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10332 | Reconstruct Curbs along median of Rockaway Freeway | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2029 | Jul 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10332 | Reconstruct Curbs along median of Rockaway Freeway | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2029 | Oct 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10332 | Reconstruct Curbs along median of Rockaway Freeway | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2029 | Feb 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10332 | Reconstruct Curbs along median of Rockaway Freeway | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2030 | Jun 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10332 | Reconstruct Curbs along median of Rockaway Freeway | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2030 | Oct 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10332 | Reconstruct Curbs along median of Rockaway Freeway | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2030 | Jan 2031
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10332 | Reconstruct Curbs along median of Rockaway Freeway | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2031 | Mar 2031
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10332 | Reconstruct Curbs along median of Rockaway Freeway | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2031 | Apr 2031
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103Q01 | Broad Channel Volunteer Fire Department Median Cut/Signal | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103Q01 | Broad Channel Volunteer Fire Department Median Cut/Signal | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103Q01 | Broad Channel Volunteer Fire Department Median Cut/Signal | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103Q01 | Broad Channel Volunteer Fire Department Median Cut/Signal | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103Q01 | Broad Channel Volunteer Fire Department Median Cut/Signal | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103Q01 | Broad Channel Volunteer Fire Department Median Cut/Signal | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103Q01 | Broad Channel Volunteer Fire Department Median Cut/Signal | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103Q01 | Broad Channel Volunteer Fire Department Median Cut/Signal | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103Q01 | Broad Channel Volunteer Fire Department Median Cut/Signal | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103Q01 | Broad Channel Volunteer Fire Department Median Cut/Signal | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWFQ3211 | 32-11 Harper Street Pantry and Locker Room | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2024 | Sep 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWFQ3211 | 32-11 Harper Street Pantry and Locker Room | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2024 | Jan 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWFQ3211 | 32-11 Harper Street Pantry and Locker Room | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2025 | Jul 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWFQ3211 | 32-11 Harper Street Pantry and Locker Room | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2025 | Oct 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWFQ3211 | 32-11 Harper Street Pantry and Locker Room | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2025 | Feb 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWFQ3211 | 32-11 Harper Street Pantry and Locker Room | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2026 | Jun 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWFQ3211 | 32-11 Harper Street Pantry and Locker Room | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2026 | Oct 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWFQ3211 | 32-11 Harper Street Pantry and Locker Room | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2028 | Jan 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWFQ3211 | 32-11 Harper Street Pantry and Locker Room | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2029 | Mar 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWFQ3211 | 32-11 Harper Street Pantry and Locker Room | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2029 | Apr 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWNBVZ | Vision Zero Great Streets on Northern Blvd | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2028 | Sep 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWNBVZ | Vision Zero Great Streets on Northern Blvd | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2028 | Jan 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWNBVZ | Vision Zero Great Streets on Northern Blvd | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2029 | Jul 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWNBVZ | Vision Zero Great Streets on Northern Blvd | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2029 | Oct 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWNBVZ | Vision Zero Great Streets on Northern Blvd | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2029 | Feb 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWNBVZ | Vision Zero Great Streets on Northern Blvd | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2030 | Jun 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWNBVZ | Vision Zero Great Streets on Northern Blvd | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2030 | Oct 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWNBVZ | Vision Zero Great Streets on Northern Blvd | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2030 | Jan 2031
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWNBVZ | Vision Zero Great Streets on Northern Blvd | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2031 | Mar 2031
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWNBVZ | Vision Zero Great Streets on Northern Blvd | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2031 | Apr 2031
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWP23QC1 | Non-Standard Ped Ramps - Queens | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWP23QC1 | Non-Standard Ped Ramps - Queens | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWP23QC1 | Non-Standard Ped Ramps - Queens | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWP23QC1 | Non-Standard Ped Ramps - Queens | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWP23QC1 | Non-Standard Ped Ramps - Queens | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWP23QC1 | Non-Standard Ped Ramps - Queens | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWP23QC1 | Non-Standard Ped Ramps - Queens | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWP23QC1 | Non-Standard Ped Ramps - Queens | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWP23QC1 | Non-Standard Ped Ramps - Queens | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWP23QC1 | Non-Standard Ped Ramps - Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWP23QC2 | Non-Standard Ped Ramps - Queens | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWP23QC2 | Non-Standard Ped Ramps - Queens | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWP23QC2 | Non-Standard Ped Ramps - Queens | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWP23QC2 | Non-Standard Ped Ramps - Queens | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWP23QC2 | Non-Standard Ped Ramps - Queens | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWP23QC2 | Non-Standard Ped Ramps - Queens | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWP23QC2 | Non-Standard Ped Ramps - Queens | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWP23QC2 | Non-Standard Ped Ramps - Queens | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWP23QC2 | Non-Standard Ped Ramps - Queens | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWP23QC2 | Non-Standard Ped Ramps - Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ016Q | Woodside Avenue | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ016Q | Woodside Avenue | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ016Q | Woodside Avenue | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ016Q | Woodside Avenue | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ016Q | Woodside Avenue | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ016Q | Woodside Avenue | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ016Q | Woodside Avenue | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ016Q | Woodside Avenue | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ016Q | Woodside Avenue | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ016Q | Woodside Avenue | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24Q1 | Simple Upgrades Ped Ramps- Queens | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2024 | Sep 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24Q1 | Simple Upgrades Ped Ramps- Queens | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2024 | Jan 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24Q1 | Simple Upgrades Ped Ramps- Queens | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2025 | Jul 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24Q1 | Simple Upgrades Ped Ramps- Queens | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2025 | Oct 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24Q1 | Simple Upgrades Ped Ramps- Queens | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2025 | Feb 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24Q1 | Simple Upgrades Ped Ramps- Queens | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2026 | Jun 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24Q1 | Simple Upgrades Ped Ramps- Queens | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2026 | Oct 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24Q1 | Simple Upgrades Ped Ramps- Queens | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2026 | Jan 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24Q1 | Simple Upgrades Ped Ramps- Queens | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2027 | Mar 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWPR24Q1 | Simple Upgrades Ped Ramps- Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2027 | Apr 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ100SBS | Woodhaven Blvd SBS | 1 | DEVELOP SCOPE | Jun 2013 | Sep 2013 | Jun 2019 | Sep 2019
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ100SBS | Woodhaven Blvd SBS | 2 | PRELIMINARY DESIGN | Sep 2013 | Jan 2014 | Sep 2019 | Jan 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ100SBS | Woodhaven Blvd SBS | 3 | FINAL DESIGN | Jan 2014 | Jul 2014 | Jan 2020 | Jul 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ100SBS | Woodhaven Blvd SBS | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2014 | Oct 2014 | Jul 2020 | Oct 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ100SBS | Woodhaven Blvd SBS | 5 | CONSTRUCTION TO 25% | Oct 2014 | Feb 2015 | Oct 2020 | Feb 2021
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ100SBS | Woodhaven Blvd SBS | 6 | CONSTRUCTION TO 50% | Feb 2015 | Jun 2015 | Feb 2021 | Jun 2021
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ100SBS | Woodhaven Blvd SBS | 7 | CONSTRUCTION TO 75% | Jun 2015 | Oct 2015 | Jun 2021 | Oct 2021
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ100SBS | Woodhaven Blvd SBS | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2015 | Jan 2016 | Oct 2021 | Jan 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ100SBS | Woodhaven Blvd SBS | 9 | SUBSTANTIAL COMPLETION | Jan 2016 | Mar 2016 | Jan 2022 | Mar 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ100SBS | Woodhaven Blvd SBS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Apr 2016 | Mar 2022 | Jul 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ102WF | 102nd Street Waterfront - Hawtree Basin | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ102WF | 102nd Street Waterfront - Hawtree Basin | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ102WF | 102nd Street Waterfront - Hawtree Basin | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ102WF | 102nd Street Waterfront - Hawtree Basin | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ102WF | 102nd Street Waterfront - Hawtree Basin | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ102WF | 102nd Street Waterfront - Hawtree Basin | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ102WF | 102nd Street Waterfront - Hawtree Basin | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ102WF | 102nd Street Waterfront - Hawtree Basin | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ102WF | 102nd Street Waterfront - Hawtree Basin | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ102WF | 102nd Street Waterfront - Hawtree Basin | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1190 | Reconstruction of Queens Blvd | 1 | DEVELOP SCOPE | Sep 2019 | Dec 2019 | Sep 2028 | Dec 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1190 | Reconstruction of Queens Blvd | 2 | PRELIMINARY DESIGN | Dec 2019 | Apr 2020 | Dec 2028 | Apr 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1190 | Reconstruction of Queens Blvd | 3 | FINAL DESIGN | Apr 2020 | Oct 2020 | Apr 2029 | Oct 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1190 | Reconstruction of Queens Blvd | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2020 | Jan 2021 | Oct 2029 | Jan 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1190 | Reconstruction of Queens Blvd | 5 | CONSTRUCTION TO 25% | Jan 2021 | May 2021 | Jan 2030 | May 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1190 | Reconstruction of Queens Blvd | 6 | CONSTRUCTION TO 50% | May 2021 | Sep 2021 | May 2030 | Sep 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1190 | Reconstruction of Queens Blvd | 7 | CONSTRUCTION TO 75% | Sep 2021 | Jan 2022 | Sep 2030 | Jan 2031
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1190 | Reconstruction of Queens Blvd | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2022 | Apr 2022 | Jan 2031 | Apr 2031
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1190 | Reconstruction of Queens Blvd | 9 | SUBSTANTIAL COMPLETION | Apr 2022 | Jun 2022 | Apr 2031 | Jun 2031
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1190 | Reconstruction of Queens Blvd | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Jul 2022 | Jun 2031 | Jul 2031
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1192 | Jewel Ave | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jan 2029 | Apr 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1192 | Jewel Ave | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Apr 2029 | Aug 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1192 | Jewel Ave | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Aug 2029 | Feb 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1192 | Jewel Ave | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Feb 2030 | May 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1192 | Jewel Ave | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | May 2030 | Sep 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1192 | Jewel Ave | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Sep 2030 | Jan 2031
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1192 | Jewel Ave | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jan 2031 | Sep 2031
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1192 | Jewel Ave | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Oct 2026 | Jan 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1192 | Jewel Ave | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jan 2027 | Mar 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1192 | Jewel Ave | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Mar 2027 | Jul 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1199 | Beach 84th Street End | 1 | DEVELOP SCOPE | May 2019 | Dec 2019 | May 2023 | Jan 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1199 | Beach 84th Street End | 2 | PRELIMINARY DESIGN | Jun 2020 | Jul 2021 | Jun 2020 | Jul 2021
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1199 | Beach 84th Street End | 3 | FINAL DESIGN | Jul 2021 | Sep 2022 | Jul 2021 | Sep 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1199 | Beach 84th Street End | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1199 | Beach 84th Street End | 5 | CONSTRUCTION TO 25% | Aug 2023 | Feb 2024 | Jun 2023 | Dec 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1199 | Beach 84th Street End | 6 | CONSTRUCTION TO 50% | Feb 2024 | Aug 2024 | Dec 2023 | Jul 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1199 | Beach 84th Street End | 7 | CONSTRUCTION TO 75% | Aug 2024 | Feb 2025 | Jul 2024 | Jan 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1199 | Beach 84th Street End | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2025 | May 2025 | Jan 2025 | Apr 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1199 | Beach 84th Street End | 9 | SUBSTANTIAL COMPLETION | Aug 2023 | Aug 2025 | Aug 2023 | Aug 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1199 | Beach 84th Street End | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2025 | Nov 2025 | Aug 2027 | Jul 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1200 | Vision Zero Great Streets Northern Boulevard Phase 1 | 1 | DEVELOP SCOPE | Jun 2020 | Dec 2020 | Jun 2022 | Dec 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1200 | Vision Zero Great Streets Northern Boulevard Phase 1 | 2 | PRELIMINARY DESIGN | May 2021 | Aug 2022 | May 2021 | Aug 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1200 | Vision Zero Great Streets Northern Boulevard Phase 1 | 3 | FINAL DESIGN | Aug 2022 | Nov 2023 | Aug 2022 | Nov 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1200 | Vision Zero Great Streets Northern Boulevard Phase 1 | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2024 | May 2024 | Mar 2024 | May 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1200 | Vision Zero Great Streets Northern Boulevard Phase 1 | 5 | CONSTRUCTION TO 25% | Jun 2024 | Jan 2025 | Jun 2024 | Jan 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1200 | Vision Zero Great Streets Northern Boulevard Phase 1 | 6 | CONSTRUCTION TO 50% | Jan 2025 | Aug 2025 | Jan 2025 | Aug 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1200 | Vision Zero Great Streets Northern Boulevard Phase 1 | 7 | CONSTRUCTION TO 75% | Aug 2025 | Feb 2026 | Aug 2025 | Feb 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1200 | Vision Zero Great Streets Northern Boulevard Phase 1 | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2026 | May 2026 | Feb 2028 | May 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1200 | Vision Zero Great Streets Northern Boulevard Phase 1 | 9 | SUBSTANTIAL COMPLETION | Sep 2026 | Sep 2026 | Sep 2026 | Sep 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1200 | Vision Zero Great Streets Northern Boulevard Phase 1 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Dec 2026 | Sep 2026 | Dec 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1202 | 34TH AVENUE MALLS | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2024 | Sep 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1202 | 34TH AVENUE MALLS | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2024 | Jan 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1202 | 34TH AVENUE MALLS | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2025 | Jul 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1202 | 34TH AVENUE MALLS | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2025 | Oct 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1202 | 34TH AVENUE MALLS | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2025 | Feb 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1202 | 34TH AVENUE MALLS | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2026 | Jun 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1202 | 34TH AVENUE MALLS | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2026 | Oct 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1202 | 34TH AVENUE MALLS | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2026 | Jan 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1202 | 34TH AVENUE MALLS | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2027 | Mar 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1202 | 34TH AVENUE MALLS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2027 | Jul 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1203 | Maspeth Ave and Rust Street Safety Improvements | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2027 | Sep 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1203 | Maspeth Ave and Rust Street Safety Improvements | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2027 | Jan 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1203 | Maspeth Ave and Rust Street Safety Improvements | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2028 | Jul 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1203 | Maspeth Ave and Rust Street Safety Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2028 | Oct 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1203 | Maspeth Ave and Rust Street Safety Improvements | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2028 | Feb 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1203 | Maspeth Ave and Rust Street Safety Improvements | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2029 | Jun 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1203 | Maspeth Ave and Rust Street Safety Improvements | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2029 | Oct 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1203 | Maspeth Ave and Rust Street Safety Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2029 | Jan 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1203 | Maspeth Ave and Rust Street Safety Improvements | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2030 | Mar 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1203 | Maspeth Ave and Rust Street Safety Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2030 | Jun 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1204 | Bayswater Park Pedestrian Access | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2024 | Sep 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1204 | Bayswater Park Pedestrian Access | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2024 | Jan 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1204 | Bayswater Park Pedestrian Access | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2025 | Jul 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1204 | Bayswater Park Pedestrian Access | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2025 | Oct 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1204 | Bayswater Park Pedestrian Access | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2025 | Feb 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1204 | Bayswater Park Pedestrian Access | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2026 | Jun 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1204 | Bayswater Park Pedestrian Access | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2026 | Oct 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1204 | Bayswater Park Pedestrian Access | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2026 | Jan 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1204 | Bayswater Park Pedestrian Access | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2027 | Mar 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1204 | Bayswater Park Pedestrian Access | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2027 | Jul 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1206 | Reconstruction of 108th Avenue, South Jamaica | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jul 2022 | Sep 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1206 | Reconstruction of 108th Avenue, South Jamaica | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2026 | Jan 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1206 | Reconstruction of 108th Avenue, South Jamaica | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2027 | Jul 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1206 | Reconstruction of 108th Avenue, South Jamaica | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2027 | Oct 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1206 | Reconstruction of 108th Avenue, South Jamaica | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2027 | Feb 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1206 | Reconstruction of 108th Avenue, South Jamaica | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2028 | Jun 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1206 | Reconstruction of 108th Avenue, South Jamaica | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2028 | Oct 2031
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1206 | Reconstruction of 108th Avenue, South Jamaica | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Oct 2023 | Oct 2022 | Oct 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1206 | Reconstruction of 108th Avenue, South Jamaica | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2025 | Jan 2024 | Mar 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1206 | Reconstruction of 108th Avenue, South Jamaica | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Feb 2026 | Mar 2025 | Feb 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1208 | Downtown Far Rockaway Phase 2 | 1 | DEVELOP SCOPE | Jun 2026 | Sep 2026 | Jun 2027 | Sep 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1208 | Downtown Far Rockaway Phase 2 | 2 | PRELIMINARY DESIGN | Sep 2026 | Jan 2027 | Sep 2027 | Jan 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1208 | Downtown Far Rockaway Phase 2 | 3 | FINAL DESIGN | Jan 2027 | Jul 2027 | Jan 2028 | Jul 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1208 | Downtown Far Rockaway Phase 2 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2027 | Oct 2027 | Jul 2028 | Oct 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1208 | Downtown Far Rockaway Phase 2 | 5 | CONSTRUCTION TO 25% | Oct 2027 | Feb 2028 | Oct 2028 | Feb 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1208 | Downtown Far Rockaway Phase 2 | 6 | CONSTRUCTION TO 50% | Feb 2028 | Jun 2028 | Feb 2029 | Jun 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1208 | Downtown Far Rockaway Phase 2 | 7 | CONSTRUCTION TO 75% | Jun 2028 | Oct 2028 | Jun 2029 | Oct 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1208 | Downtown Far Rockaway Phase 2 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2028 | Jan 2029 | Oct 2029 | Jan 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1208 | Downtown Far Rockaway Phase 2 | 9 | SUBSTANTIAL COMPLETION | Jan 2029 | Mar 2029 | Jan 2030 | Mar 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1208 | Downtown Far Rockaway Phase 2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2029 | Apr 2029 | Mar 2030 | Apr 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1209 | Utopia Parkway Safety Improvements & Seawall Repair | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1209 | Utopia Parkway Safety Improvements & Seawall Repair | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1209 | Utopia Parkway Safety Improvements & Seawall Repair | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1209 | Utopia Parkway Safety Improvements & Seawall Repair | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1209 | Utopia Parkway Safety Improvements & Seawall Repair | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1209 | Utopia Parkway Safety Improvements & Seawall Repair | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1209 | Utopia Parkway Safety Improvements & Seawall Repair | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1209 | Utopia Parkway Safety Improvements & Seawall Repair | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1209 | Utopia Parkway Safety Improvements & Seawall Repair | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1209 | Utopia Parkway Safety Improvements & Seawall Repair | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1210 | Jamaica Avenue Safety and Streetscape Improvements | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2026 | Sep 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1210 | Jamaica Avenue Safety and Streetscape Improvements | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2026 | Jan 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1210 | Jamaica Avenue Safety and Streetscape Improvements | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2027 | Jul 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1210 | Jamaica Avenue Safety and Streetscape Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2027 | Oct 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1210 | Jamaica Avenue Safety and Streetscape Improvements | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2027 | Feb 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1210 | Jamaica Avenue Safety and Streetscape Improvements | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2028 | Jun 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1210 | Jamaica Avenue Safety and Streetscape Improvements | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2028 | Oct 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1210 | Jamaica Avenue Safety and Streetscape Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2028 | Jan 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1210 | Jamaica Avenue Safety and Streetscape Improvements | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2029 | Mar 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1210 | Jamaica Avenue Safety and Streetscape Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2029 | Apr 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1500 | Replacement of Existing and Installation of New Storm Sewer | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2025 | Sep 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1500 | Replacement of Existing and Installation of New Storm Sewer | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2025 | Jan 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1500 | Replacement of Existing and Installation of New Storm Sewer | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2026 | Jul 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1500 | Replacement of Existing and Installation of New Storm Sewer | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2026 | Oct 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1500 | Replacement of Existing and Installation of New Storm Sewer | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2026 | Feb 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1500 | Replacement of Existing and Installation of New Storm Sewer | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2027 | Jun 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1500 | Replacement of Existing and Installation of New Storm Sewer | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2027 | Oct 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1500 | Replacement of Existing and Installation of New Storm Sewer | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2027 | Jan 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1500 | Replacement of Existing and Installation of New Storm Sewer | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2028 | Mar 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1500 | Replacement of Existing and Installation of New Storm Sewer | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2028 | Apr 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ20AVWF | East River Waterfront - 20th Avenue Street End | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2027 | Sep 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ20AVWF | East River Waterfront - 20th Avenue Street End | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2027 | Jan 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ20AVWF | East River Waterfront - 20th Avenue Street End | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2028 | Jul 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ20AVWF | East River Waterfront - 20th Avenue Street End | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2028 | Oct 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ20AVWF | East River Waterfront - 20th Avenue Street End | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2028 | Feb 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ20AVWF | East River Waterfront - 20th Avenue Street End | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2029 | Jun 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ20AVWF | East River Waterfront - 20th Avenue Street End | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2029 | Oct 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ20AVWF | East River Waterfront - 20th Avenue Street End | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ20AVWF | East River Waterfront - 20th Avenue Street End | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2030 | Mar 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ20AVWF | East River Waterfront - 20th Avenue Street End | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2030 | Apr 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ49STWF | 49th Street Waterfront - Newtown Creek | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ49STWF | 49th Street Waterfront - Newtown Creek | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ49STWF | 49th Street Waterfront - Newtown Creek | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ49STWF | 49th Street Waterfront - Newtown Creek | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ49STWF | 49th Street Waterfront - Newtown Creek | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ49STWF | 49th Street Waterfront - Newtown Creek | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ49STWF | 49th Street Waterfront - Newtown Creek | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ49STWF | 49th Street Waterfront - Newtown Creek | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ49STWF | 49th Street Waterfront - Newtown Creek | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ49STWF | 49th Street Waterfront - Newtown Creek | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ631B2 | Somerville Area - Phase II | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2026 | Sep 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ631B2 | Somerville Area - Phase II | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2026 | Jan 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ631B2 | Somerville Area - Phase II | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2027 | Jul 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ631B2 | Somerville Area - Phase II | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2027 | Oct 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ631B2 | Somerville Area - Phase II | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2027 | Feb 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ631B2 | Somerville Area - Phase II | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2028 | Jun 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ631B2 | Somerville Area - Phase II | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2028 | Oct 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ631B2 | Somerville Area - Phase II | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2028 | Jan 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ631B2 | Somerville Area - Phase II | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2029 | Mar 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ631B2 | Somerville Area - Phase II | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2029 | Apr 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ788 | LIC/Hunters Point Area-wide Reconstruction | 1 | DEVELOP SCOPE | May 2005 | Aug 2005 | May 2017 | Dec 2018
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ788 | LIC/Hunters Point Area-wide Reconstruction | 2 | PRELIMINARY DESIGN | Aug 2005 | Dec 2005 | Oct 2014 | Aug 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ788 | LIC/Hunters Point Area-wide Reconstruction | 3 | FINAL DESIGN | Dec 2005 | Jun 2006 | May 2023 | Nov 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ788 | LIC/Hunters Point Area-wide Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2006 | Sep 2006 | May 2023 | Nov 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ788 | LIC/Hunters Point Area-wide Reconstruction | 5 | CONSTRUCTION TO 25% | Sep 2006 | Jan 2007 | May 2023 | Nov 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ788 | LIC/Hunters Point Area-wide Reconstruction | 6 | CONSTRUCTION TO 50% | Jan 2007 | May 2007 | May 2023 | Nov 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ788 | LIC/Hunters Point Area-wide Reconstruction | 7 | CONSTRUCTION TO 75% | May 2007 | Sep 2007 | May 2023 | Nov 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ788 | LIC/Hunters Point Area-wide Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2007 | Dec 2007 | May 2023 | Nov 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ788 | LIC/Hunters Point Area-wide Reconstruction | 9 | SUBSTANTIAL COMPLETION | Dec 2007 | Feb 2008 | May 2023 | Nov 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ788 | LIC/Hunters Point Area-wide Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2008 | Mar 2008 | May 2023 | Nov 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ789 | THOMSON AVE. SAFETY IMPROVEMENTS -- LAGUARDIA COMM. COLLEGE | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | May 2021 | Nov 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ789 | THOMSON AVE. SAFETY IMPROVEMENTS -- LAGUARDIA COMM. COLLEGE | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Nov 2024 | Mar 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ789 | THOMSON AVE. SAFETY IMPROVEMENTS -- LAGUARDIA COMM. COLLEGE | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Mar 2025 | Sep 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ789 | THOMSON AVE. SAFETY IMPROVEMENTS -- LAGUARDIA COMM. COLLEGE | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Sep 2025 | Dec 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ789 | THOMSON AVE. SAFETY IMPROVEMENTS -- LAGUARDIA COMM. COLLEGE | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Dec 2025 | Apr 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ789 | THOMSON AVE. SAFETY IMPROVEMENTS -- LAGUARDIA COMM. COLLEGE | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Apr 2026 | Aug 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ789 | THOMSON AVE. SAFETY IMPROVEMENTS -- LAGUARDIA COMM. COLLEGE | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Aug 2026 | Dec 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ789 | THOMSON AVE. SAFETY IMPROVEMENTS -- LAGUARDIA COMM. COLLEGE | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Dec 2026 | Mar 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ789 | THOMSON AVE. SAFETY IMPROVEMENTS -- LAGUARDIA COMM. COLLEGE | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Mar 2027 | May 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ789 | THOMSON AVE. SAFETY IMPROVEMENTS -- LAGUARDIA COMM. COLLEGE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | May 2027 | Jul 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ985A | Shore Road Embankment Repair | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2027 | Sep 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ985A | Shore Road Embankment Repair | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2027 | Jan 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ985A | Shore Road Embankment Repair | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2028 | Jul 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ985A | Shore Road Embankment Repair | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2028 | Oct 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ985A | Shore Road Embankment Repair | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2028 | Feb 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ985A | Shore Road Embankment Repair | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2029 | Jun 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ985A | Shore Road Embankment Repair | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2029 | Oct 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ985A | Shore Road Embankment Repair | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2029 | Jan 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ985A | Shore Road Embankment Repair | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2030 | Mar 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ985A | Shore Road Embankment Repair | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2030 | Apr 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQEDGM1 | Edgemere Avenue Phase 1 (B56 Pl to B62) | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQEDGM1 | Edgemere Avenue Phase 1 (B56 Pl to B62) | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQEDGM1 | Edgemere Avenue Phase 1 (B56 Pl to B62) | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQEDGM1 | Edgemere Avenue Phase 1 (B56 Pl to B62) | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQEDGM1 | Edgemere Avenue Phase 1 (B56 Pl to B62) | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQEDGM1 | Edgemere Avenue Phase 1 (B56 Pl to B62) | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQEDGM1 | Edgemere Avenue Phase 1 (B56 Pl to B62) | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQEDGM1 | Edgemere Avenue Phase 1 (B56 Pl to B62) | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQEDGM1 | Edgemere Avenue Phase 1 (B56 Pl to B62) | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQEDGM1 | Edgemere Avenue Phase 1 (B56 Pl to B62) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF031C | Glendale Yard Pre-Engineered Shed | 1 | DEVELOP SCOPE | Jun 2014 | Aug 2014 | Jun 2020 | Aug 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF031C | Glendale Yard Pre-Engineered Shed | 2 | PRELIMINARY DESIGN | Aug 2014 | Dec 2014 | Aug 2020 | Dec 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF031C | Glendale Yard Pre-Engineered Shed | 3 | FINAL DESIGN | Dec 2014 | Jun 2015 | Dec 2020 | Jun 2021
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF031C | Glendale Yard Pre-Engineered Shed | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2015 | Sep 2015 | Jun 2021 | Sep 2021
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF031C | Glendale Yard Pre-Engineered Shed | 5 | CONSTRUCTION TO 25% | Sep 2015 | Jan 2016 | Sep 2021 | Jan 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF031C | Glendale Yard Pre-Engineered Shed | 6 | CONSTRUCTION TO 50% | Jan 2016 | May 2016 | Jan 2022 | May 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF031C | Glendale Yard Pre-Engineered Shed | 7 | CONSTRUCTION TO 75% | May 2016 | Sep 2016 | May 2022 | Sep 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF031C | Glendale Yard Pre-Engineered Shed | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Dec 2016 | Sep 2022 | Dec 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF031C | Glendale Yard Pre-Engineered Shed | 9 | SUBSTANTIAL COMPLETION | Dec 2016 | Feb 2017 | Dec 2022 | Feb 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF031C | Glendale Yard Pre-Engineered Shed | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2017 | Mar 2017 | Feb 2023 | Jul 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF041 | QUEENS SAFETY CITY CONSTRUCTION 2 | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF041 | QUEENS SAFETY CITY CONSTRUCTION 2 | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF041 | QUEENS SAFETY CITY CONSTRUCTION 2 | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jun 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF041 | QUEENS SAFETY CITY CONSTRUCTION 2 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2026 | Sep 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF041 | QUEENS SAFETY CITY CONSTRUCTION 2 | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Sep 2026 | Jan 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF041 | QUEENS SAFETY CITY CONSTRUCTION 2 | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Jan 2027 | May 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF041 | QUEENS SAFETY CITY CONSTRUCTION 2 | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | May 2027 | Sep 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF041 | QUEENS SAFETY CITY CONSTRUCTION 2 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Sep 2027 | Dec 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF041 | QUEENS SAFETY CITY CONSTRUCTION 2 | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Dec 2027 | Feb 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF041 | QUEENS SAFETY CITY CONSTRUCTION 2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Feb 2028 | Oct 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF12ST | 38-21 12th Street Rehabilitation | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2017 | Sep 2017
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF12ST | 38-21 12th Street Rehabilitation | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2017 | Jan 2018
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF12ST | 38-21 12th Street Rehabilitation | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jan 2018 | Jul 2018
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF12ST | 38-21 12th Street Rehabilitation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2018 | Oct 2018
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF12ST | 38-21 12th Street Rehabilitation | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF12ST | 38-21 12th Street Rehabilitation | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF12ST | 38-21 12th Street Rehabilitation | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jun 2019 | Oct 2019
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF12ST | 38-21 12th Street Rehabilitation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Oct 2019 | Jan 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF12ST | 38-21 12th Street Rehabilitation | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jan 2020 | Mar 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF12ST | 38-21 12th Street Rehabilitation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Mar 2020 | Apr 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF2002V | GLENDALE YARD TRAILERS | 1 | DEVELOP SCOPE | Jun 2015 | Oct 2015 | Jun 2022 | Oct 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF2002V | GLENDALE YARD TRAILERS | 2 | DESIGN START | Oct 2015 | Apr 2017 | Oct 2022 | Apr 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF2002V | GLENDALE YARD TRAILERS | 3 | CONSTRUCTION START | Apr 2017 | Apr 2019 | Apr 2024 | Apr 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF4200V | Installation of Sewer & Water Services for 4200 Vernon Blvd. | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2028 | Sep 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF4200V | Installation of Sewer & Water Services for 4200 Vernon Blvd. | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2028 | Jan 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF4200V | Installation of Sewer & Water Services for 4200 Vernon Blvd. | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2029 | Jul 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF4200V | Installation of Sewer & Water Services for 4200 Vernon Blvd. | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2029 | Oct 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF4200V | Installation of Sewer & Water Services for 4200 Vernon Blvd. | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2029 | Feb 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF4200V | Installation of Sewer & Water Services for 4200 Vernon Blvd. | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2030 | Jun 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF4200V | Installation of Sewer & Water Services for 4200 Vernon Blvd. | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2030 | Oct 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF4200V | Installation of Sewer & Water Services for 4200 Vernon Blvd. | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2030 | Jan 2031
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF4200V | Installation of Sewer & Water Services for 4200 Vernon Blvd. | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2031 | Mar 2031
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF4200V | Installation of Sewer & Water Services for 4200 Vernon Blvd. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2031 | Apr 2031
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF5850 | HVAC Replacement Maspeth | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF5850 | HVAC Replacement Maspeth | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF5850 | HVAC Replacement Maspeth | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF5850 | HVAC Replacement Maspeth | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF5850 | HVAC Replacement Maspeth | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF5850 | HVAC Replacement Maspeth | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF5850 | HVAC Replacement Maspeth | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF5850 | HVAC Replacement Maspeth | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF5850 | HVAC Replacement Maspeth | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF5850 | HVAC Replacement Maspeth | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFFRTN | Fort Totten | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFFRTN | Fort Totten | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFFRTN | Fort Totten | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFFRTN | Fort Totten | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFFRTN | Fort Totten | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFFRTN | Fort Totten | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFFRTN | Fort Totten | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFFRTN | Fort Totten | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFFRTN | Fort Totten | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFFRTN | Fort Totten | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFGYWF | Greenpoint Avenue Bridge Yard Waterfront Structures | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFGYWF | Greenpoint Avenue Bridge Yard Waterfront Structures | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFGYWF | Greenpoint Avenue Bridge Yard Waterfront Structures | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFGYWF | Greenpoint Avenue Bridge Yard Waterfront Structures | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFGYWF | Greenpoint Avenue Bridge Yard Waterfront Structures | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFGYWF | Greenpoint Avenue Bridge Yard Waterfront Structures | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFGYWF | Greenpoint Avenue Bridge Yard Waterfront Structures | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFGYWF | Greenpoint Avenue Bridge Yard Waterfront Structures | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFGYWF | Greenpoint Avenue Bridge Yard Waterfront Structures | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFGYWF | Greenpoint Avenue Bridge Yard Waterfront Structures | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFHVAC | Koldwave Trailer Mounted AC units | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFHVAC | Koldwave Trailer Mounted AC units | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFHVAC | Koldwave Trailer Mounted AC units | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFHVAC | Koldwave Trailer Mounted AC units | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFHVAC | Koldwave Trailer Mounted AC units | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFHVAC | Koldwave Trailer Mounted AC units | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFHVAC | Koldwave Trailer Mounted AC units | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFHVAC | Koldwave Trailer Mounted AC units | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFHVAC | Koldwave Trailer Mounted AC units | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFHVAC | Koldwave Trailer Mounted AC units | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFSW033 | 33-00 Northern Blvd Swing Space | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2027 | Sep 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFSW033 | 33-00 Northern Blvd Swing Space | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2027 | Jan 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFSW033 | 33-00 Northern Blvd Swing Space | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2028 | Jul 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFSW033 | 33-00 Northern Blvd Swing Space | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2028 | Oct 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFSW033 | 33-00 Northern Blvd Swing Space | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2028 | Feb 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFSW033 | 33-00 Northern Blvd Swing Space | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2029 | Jun 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFSW033 | 33-00 Northern Blvd Swing Space | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2029 | Oct 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFSW033 | 33-00 Northern Blvd Swing Space | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2029 | Jan 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFSW033 | 33-00 Northern Blvd Swing Space | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2030 | Mar 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFSW033 | 33-00 Northern Blvd Swing Space | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2030 | Apr 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQHUXWF | Huxley Street Waterfront - Hook Creek | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQHUXWF | Huxley Street Waterfront - Hook Creek | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQHUXWF | Huxley Street Waterfront - Hook Creek | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQHUXWF | Huxley Street Waterfront - Hook Creek | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQHUXWF | Huxley Street Waterfront - Hook Creek | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQHUXWF | Huxley Street Waterfront - Hook Creek | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQHUXWF | Huxley Street Waterfront - Hook Creek | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQHUXWF | Huxley Street Waterfront - Hook Creek | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQHUXWF | Huxley Street Waterfront - Hook Creek | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQHUXWF | Huxley Street Waterfront - Hook Creek | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQMASPET | Maspeth Climate Control and Air Quality Improvements | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Feb 2018 | Aug 2018
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQMASPET | Maspeth Climate Control and Air Quality Improvements | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Aug 2018 | Dec 2018
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQMASPET | Maspeth Climate Control and Air Quality Improvements | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Dec 2018 | Jun 2019
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQMASPET | Maspeth Climate Control and Air Quality Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jun 2019 | Sep 2019
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQMASPET | Maspeth Climate Control and Air Quality Improvements | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Sep 2019 | Jan 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQMASPET | Maspeth Climate Control and Air Quality Improvements | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Jan 2020 | May 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQMASPET | Maspeth Climate Control and Air Quality Improvements | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | May 2020 | Sep 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQMASPET | Maspeth Climate Control and Air Quality Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Oct 2018 | Jul 2019
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQMASPET | Maspeth Climate Control and Air Quality Improvements | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jul 2019 | Sep 2019
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQMASPET | Maspeth Climate Control and Air Quality Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Sep 2019 | Oct 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSE877 | Woodhaven SBS - Metropolitan Ave SE-877 | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2024 | Sep 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSE877 | Woodhaven SBS - Metropolitan Ave SE-877 | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2024 | Jan 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSE877 | Woodhaven SBS - Metropolitan Ave SE-877 | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2025 | Jul 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSE877 | Woodhaven SBS - Metropolitan Ave SE-877 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2025 | Oct 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSE877 | Woodhaven SBS - Metropolitan Ave SE-877 | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2025 | Feb 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSE877 | Woodhaven SBS - Metropolitan Ave SE-877 | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2026 | Jun 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSE877 | Woodhaven SBS - Metropolitan Ave SE-877 | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2026 | Oct 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSE877 | Woodhaven SBS - Metropolitan Ave SE-877 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2026 | Jan 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSE877 | Woodhaven SBS - Metropolitan Ave SE-877 | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2028 | Mar 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSE877 | Woodhaven SBS - Metropolitan Ave SE-877 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2028 | Apr 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSHORWF | Shore Road Waterfront - Kenmore Road to Grosvenor Street | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSHORWF | Shore Road Waterfront - Kenmore Road to Grosvenor Street | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSHORWF | Shore Road Waterfront - Kenmore Road to Grosvenor Street | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSHORWF | Shore Road Waterfront - Kenmore Road to Grosvenor Street | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSHORWF | Shore Road Waterfront - Kenmore Road to Grosvenor Street | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSHORWF | Shore Road Waterfront - Kenmore Road to Grosvenor Street | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSHORWF | Shore Road Waterfront - Kenmore Road to Grosvenor Street | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSHORWF | Shore Road Waterfront - Kenmore Road to Grosvenor Street | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSHORWF | Shore Road Waterfront - Kenmore Road to Grosvenor Street | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSHORWF | Shore Road Waterfront - Kenmore Road to Grosvenor Street | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWF164 | Hawtree Basin Waterfront - 164 Ave/McKee Ave Street End | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWF164 | Hawtree Basin Waterfront - 164 Ave/McKee Ave Street End | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWF164 | Hawtree Basin Waterfront - 164 Ave/McKee Ave Street End | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWF164 | Hawtree Basin Waterfront - 164 Ave/McKee Ave Street End | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWF164 | Hawtree Basin Waterfront - 164 Ave/McKee Ave Street End | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWF164 | Hawtree Basin Waterfront - 164 Ave/McKee Ave Street End | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWF164 | Hawtree Basin Waterfront - 164 Ave/McKee Ave Street End | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWF164 | Hawtree Basin Waterfront - 164 Ave/McKee Ave Street End | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWF164 | Hawtree Basin Waterfront - 164 Ave/McKee Ave Street End | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWF164 | Hawtree Basin Waterfront - 164 Ave/McKee Ave Street End | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWILLPT | Willets Point Engineered Resurfacing | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | May 2023 | Nov 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWILLPT | Willets Point Engineered Resurfacing | 2 | PRELIMINARY DESIGN | May 2020 | Aug 2021 | May 2020 | Aug 2021
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWILLPT | Willets Point Engineered Resurfacing | 3 | FINAL DESIGN | Aug 2021 | Nov 2022 | Aug 2021 | Nov 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWILLPT | Willets Point Engineered Resurfacing | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2022 | Mar 2023 | Nov 2022 | Mar 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWILLPT | Willets Point Engineered Resurfacing | 5 | CONSTRUCTION TO 25% | Oct 2023 | Apr 2024 | Jun 2023 | Jul 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWILLPT | Willets Point Engineered Resurfacing | 6 | CONSTRUCTION TO 50% | Apr 2024 | Oct 2024 | Jul 2024 | Jan 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWILLPT | Willets Point Engineered Resurfacing | 7 | CONSTRUCTION TO 75% | Oct 2024 | Apr 2025 | Jan 2025 | Jun 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWILLPT | Willets Point Engineered Resurfacing | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2025 | Jun 2025 | May 2020 | Jun 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWILLPT | Willets Point Engineered Resurfacing | 9 | SUBSTANTIAL COMPLETION | Oct 2023 | Sep 2025 | Jul 2020 | Sep 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWILLPT | Willets Point Engineered Resurfacing | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Dec 2025 | Sep 2025 | Jul 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024Q | Prior Notice Sidewalks - Queens | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2024 | Sep 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024Q | Prior Notice Sidewalks - Queens | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2024 | Jan 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024Q | Prior Notice Sidewalks - Queens | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2025 | Jul 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024Q | Prior Notice Sidewalks - Queens | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2025 | Oct 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024Q | Prior Notice Sidewalks - Queens | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2025 | Feb 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024Q | Prior Notice Sidewalks - Queens | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2026 | Jun 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024Q | Prior Notice Sidewalks - Queens | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2026 | Oct 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024Q | Prior Notice Sidewalks - Queens | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2026 | Jan 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024Q | Prior Notice Sidewalks - Queens | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2027 | Mar 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024Q | Prior Notice Sidewalks - Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2027 | Apr 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWWATER37 | 37TH AVE DOT MOVE DUE TO DEP WATER TUN 3 | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2023 | Sep 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWWATER37 | 37TH AVE DOT MOVE DUE TO DEP WATER TUN 3 | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2023 | Jan 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWWATER37 | 37TH AVE DOT MOVE DUE TO DEP WATER TUN 3 | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2024 | Jul 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWWATER37 | 37TH AVE DOT MOVE DUE TO DEP WATER TUN 3 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2024 | Oct 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWWATER37 | 37TH AVE DOT MOVE DUE TO DEP WATER TUN 3 | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2024 | Feb 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWWATER37 | 37TH AVE DOT MOVE DUE TO DEP WATER TUN 3 | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2025 | Jun 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWWATER37 | 37TH AVE DOT MOVE DUE TO DEP WATER TUN 3 | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2025 | Oct 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWWATER37 | 37TH AVE DOT MOVE DUE TO DEP WATER TUN 3 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2025 | Jan 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWWATER37 | 37TH AVE DOT MOVE DUE TO DEP WATER TUN 3 | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2026 | Mar 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWWATER37 | 37TH AVE DOT MOVE DUE TO DEP WATER TUN 3 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2026 | Apr 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | JAMASTPLZ | Greater Jamaica Dev Corp Station Plaza Acquisition | 1 | DEVELOP SCOPE | Jun 2014 | Sep 2014 | Jun 2019 | Sep 2019
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | JAMASTPLZ | Greater Jamaica Dev Corp Station Plaza Acquisition | 2 | PRELIMINARY DESIGN | Sep 2014 | Jan 2015 | Sep 2019 | Jan 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | JAMASTPLZ | Greater Jamaica Dev Corp Station Plaza Acquisition | 3 | FINAL DESIGN | Jan 2015 | Jul 2015 | Jan 2020 | Jul 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | JAMASTPLZ | Greater Jamaica Dev Corp Station Plaza Acquisition | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Oct 2015 | Jul 2020 | Oct 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | JAMASTPLZ | Greater Jamaica Dev Corp Station Plaza Acquisition | 5 | CONSTRUCTION TO 25% | Oct 2015 | Feb 2016 | Oct 2020 | Feb 2021
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | JAMASTPLZ | Greater Jamaica Dev Corp Station Plaza Acquisition | 6 | CONSTRUCTION TO 50% | Feb 2016 | Jun 2016 | Feb 2021 | Jun 2021
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | JAMASTPLZ | Greater Jamaica Dev Corp Station Plaza Acquisition | 7 | CONSTRUCTION TO 75% | Jun 2016 | Oct 2016 | Jun 2021 | Oct 2021
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | JAMASTPLZ | Greater Jamaica Dev Corp Station Plaza Acquisition | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2016 | Jan 2017 | Oct 2021 | Jan 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | JAMASTPLZ | Greater Jamaica Dev Corp Station Plaza Acquisition | 9 | SUBSTANTIAL COMPLETION | Jan 2017 | Mar 2017 | Jan 2022 | Mar 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | JAMASTPLZ | Greater Jamaica Dev Corp Station Plaza Acquisition | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Apr 2017 | Mar 2022 | Apr 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | QUEENSCWH | QUEENS COMMERCIAL CORRIDOR AT WOODHAVEN | 1 | DESIGN | Jul 2014 | Jul 2014 | Jul 2019 | Sep 2019
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | QUEENSCWH | QUEENS COMMERCIAL CORRIDOR AT WOODHAVEN | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2014 | Aug 2014 | Sep 2019 | Jan 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | QUEENSCWH | QUEENS COMMERCIAL CORRIDOR AT WOODHAVEN | 3 | CONSTRUCTION | Aug 2014 | Sep 2014 | Jan 2020 | Jul 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | QUEENSCWH | QUEENS COMMERCIAL CORRIDOR AT WOODHAVEN | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2014 | Sep 2014 | Jul 2020 | Oct 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | QUEENSCWH | QUEENS COMMERCIAL CORRIDOR AT WOODHAVEN | 5 | SUBSTANTIAL COMPLETION | Sep 2014 | Oct 2014 | Oct 2020 | Feb 2021
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | QUEENSCWH | QUEENS COMMERCIAL CORRIDOR AT WOODHAVEN | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2014 | Oct 2014 | Feb 2021 | Jun 2021
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | QUEENSCWH | QUEENS COMMERCIAL CORRIDOR AT WOODHAVEN | 7 | CONSTRUCTION TO 75% | Oct 2014 | Oct 2014 | Jun 2021 | Oct 2021
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | QUEENSCWH | QUEENS COMMERCIAL CORRIDOR AT WOODHAVEN | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2014 | Oct 2014 | Oct 2021 | Jan 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | QUEENSCWH | QUEENS COMMERCIAL CORRIDOR AT WOODHAVEN | 9 | SUBSTANTIAL COMPLETION | Oct 2014 | Oct 2014 | Jan 2022 | Mar 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | QUEENSCWH | QUEENS COMMERCIAL CORRIDOR AT WOODHAVEN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2014 | Oct 2014 | Mar 2022 | Jun 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEEDQSTWY | SEED Steinway Streetscape Project | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEEDQSTWY | SEED Steinway Streetscape Project | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEEDQSTWY | SEED Steinway Streetscape Project | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEEDQSTWY | SEED Steinway Streetscape Project | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEEDQSTWY | SEED Steinway Streetscape Project | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEEDQSTWY | SEED Steinway Streetscape Project | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEEDQSTWY | SEED Steinway Streetscape Project | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEEDQSTWY | SEED Steinway Streetscape Project | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEEDQSTWY | SEED Steinway Streetscape Project | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEEDQSTWY | SEED Steinway Streetscape Project | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD4 | Southeast Queens Priority Grids 31-40 | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jun 2027 | Sep 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD4 | Southeast Queens Priority Grids 31-40 | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Sep 2027 | Jan 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD4 | Southeast Queens Priority Grids 31-40 | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2028 | Jul 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD4 | Southeast Queens Priority Grids 31-40 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2028 | Oct 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD4 | Southeast Queens Priority Grids 31-40 | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2028 | Feb 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD4 | Southeast Queens Priority Grids 31-40 | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2029 | Jun 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD4 | Southeast Queens Priority Grids 31-40 | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2029 | Oct 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD4 | Southeast Queens Priority Grids 31-40 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2029 | Jan 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD4 | Southeast Queens Priority Grids 31-40 | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2030 | Mar 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD4 | Southeast Queens Priority Grids 31-40 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2030 | Apr 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD5 | Southeast Queens Priority Grids 41-50 | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Jun 2025 | Sep 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD5 | Southeast Queens Priority Grids 41-50 | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Sep 2025 | Jan 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD5 | Southeast Queens Priority Grids 41-50 | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Jan 2026 | Jul 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD5 | Southeast Queens Priority Grids 41-50 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Jul 2026 | Oct 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD5 | Southeast Queens Priority Grids 41-50 | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Oct 2026 | Feb 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD5 | Southeast Queens Priority Grids 41-50 | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Feb 2027 | Jun 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD5 | Southeast Queens Priority Grids 41-50 | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Jun 2027 | Oct 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD5 | Southeast Queens Priority Grids 41-50 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | Oct 2027 | Jun 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD5 | Southeast Queens Priority Grids 41-50 | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Jan 2028 | Mar 2028
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD5 | Southeast Queens Priority Grids 41-50 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Mar 2028 | Jun 2030
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF072017 | Extension of lighting project Woodhaven | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Jun 2018 | Jun 2023 | Jun 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF072017 | Extension of lighting project Woodhaven | 2 | CONSTRUCTION START | Jul 2018 | Aug 2018 | Jul 2023 | Aug 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF072017 | Extension of lighting project Woodhaven | 3 | CONSTRUCTION COMPLETION | Aug 2018 | Mar 2020 | Aug 2023 | Mar 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF18-2020 | STEINWAY #1&2 MUNICIPAL PARKING FIELDS | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Jun 2019 | Jun 2020 | Jun 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF18-2020 | STEINWAY #1&2 MUNICIPAL PARKING FIELDS | 2 | CONSTRUCTION START | Jun 2019 | Jul 2019 | Jun 2020 | Jul 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF18-2020 | STEINWAY #1&2 MUNICIPAL PARKING FIELDS | 3 | CONSTRUCTION COMPLETION | Jul 2019 | Feb 2021 | Jul 2020 | Jun 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF18GRANP | Construction of Grand Central Parking Lot, Queens | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Jun 2023 | Jun 2027 | Jun 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF18GRANP | Construction of Grand Central Parking Lot, Queens | 2 | CONSTRUCTION START | Jul 2023 | Aug 2023 | Jul 2027 | Aug 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF18GRANP | Construction of Grand Central Parking Lot, Queens | 3 | CONSTRUCTION COMPLETION | Aug 2023 | Mar 2025 | Aug 2027 | Mar 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50308 | St lg Poles:Cross Bay Blvd ,156th to 165th Ave -S4319,MA122. | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2021 | Sep 2021
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50308 | St lg Poles:Cross Bay Blvd ,156th to 165th Ave -S4319,MA122. | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2021 | Jan 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50308 | St lg Poles:Cross Bay Blvd ,156th to 165th Ave -S4319,MA122. | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jan 2022 | Jul 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50308 | St lg Poles:Cross Bay Blvd ,156th to 165th Ave -S4319,MA122. | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2022 | Oct 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50308 | St lg Poles:Cross Bay Blvd ,156th to 165th Ave -S4319,MA122. | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Oct 2022 | Feb 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50308 | St lg Poles:Cross Bay Blvd ,156th to 165th Ave -S4319,MA122. | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Feb 2023 | Jun 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50308 | St lg Poles:Cross Bay Blvd ,156th to 165th Ave -S4319,MA122. | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jun 2023 | Oct 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50308 | St lg Poles:Cross Bay Blvd ,156th to 165th Ave -S4319,MA122. | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Oct 2023 | Jan 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50308 | St lg Poles:Cross Bay Blvd ,156th to 165th Ave -S4319,MA122. | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jan 2024 | Mar 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50308 | St lg Poles:Cross Bay Blvd ,156th to 165th Ave -S4319,MA122. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Mar 2024 | Apr 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50310 | Rlp lg brackets 102nd St and 159 Ave, -XMA123.30A | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2024 | Sep 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50310 | Rlp lg brackets 102nd St and 159 Ave, -XMA123.30A | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2024 | Jan 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50310 | Rlp lg brackets 102nd St and 159 Ave, -XMA123.30A | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jan 2025 | Jul 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50310 | Rlp lg brackets 102nd St and 159 Ave, -XMA123.30A | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2025 | Oct 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50310 | Rlp lg brackets 102nd St and 159 Ave, -XMA123.30A | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Oct 2025 | Feb 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50310 | Rlp lg brackets 102nd St and 159 Ave, -XMA123.30A | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Feb 2026 | Jun 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50310 | Rlp lg brackets 102nd St and 159 Ave, -XMA123.30A | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jun 2026 | Oct 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50310 | Rlp lg brackets 102nd St and 159 Ave, -XMA123.30A | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Oct 2026 | Jan 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50310 | Rlp lg brackets 102nd St and 159 Ave, -XMA123.30A | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jan 2027 | Mar 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50310 | Rlp lg brackets 102nd St and 159 Ave, -XMA123.30A | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Mar 2027 | Apr 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50312 | St lg repl Union Turnpike:Main St to Utopia Pkwy MA2179.30 | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2022 | Sep 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50312 | St lg repl Union Turnpike:Main St to Utopia Pkwy MA2179.30 | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2022 | Jan 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50312 | St lg repl Union Turnpike:Main St to Utopia Pkwy MA2179.30 | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jan 2023 | Jul 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50312 | St lg repl Union Turnpike:Main St to Utopia Pkwy MA2179.30 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2023 | Oct 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50312 | St lg repl Union Turnpike:Main St to Utopia Pkwy MA2179.30 | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Oct 2023 | Feb 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50312 | St lg repl Union Turnpike:Main St to Utopia Pkwy MA2179.30 | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Feb 2024 | Jun 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50312 | St lg repl Union Turnpike:Main St to Utopia Pkwy MA2179.30 | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jun 2024 | Oct 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50312 | St lg repl Union Turnpike:Main St to Utopia Pkwy MA2179.30 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Oct 2024 | Jan 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50312 | St lg repl Union Turnpike:Main St to Utopia Pkwy MA2179.30 | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jan 2025 | Mar 2025
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50312 | St lg repl Union Turnpike:Main St to Utopia Pkwy MA2179.30 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Mar 2025 | Jun 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50318 | St on Myrtle Avenue Bus Corridor XA839 | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Jun 2023 | Jun 2023 | Jun 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50318 | St on Myrtle Avenue Bus Corridor XA839 | 2 | CONSTRUCTION START | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50318 | St on Myrtle Avenue Bus Corridor XA839 | 3 | CONSTRUCTION COMPLETION | Aug 2023 | Mar 2026 | Aug 2023 | Mar 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503-04 | ROOSEVELT AVENUE STREET LIGHTING | 1 | BID AWARD AND REGISTER CONTRCT | May 2005 | May 2005 | May 2026 | May 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503-04 | ROOSEVELT AVENUE STREET LIGHTING | 2 | CONSTRUCTION START | May 2005 | Jun 2005 | May 2026 | Jun 2026
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503-04 | ROOSEVELT AVENUE STREET LIGHTING | 3 | CONSTRUCTION COMPLETION | Jun 2005 | Jan 2007 | Jun 2026 | Jun 2033
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q32 | MYRTLE AVE DECORATIVE LIGHTING QUEENS | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2021 | Sep 2021
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q32 | MYRTLE AVE DECORATIVE LIGHTING QUEENS | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2021 | Jan 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q32 | MYRTLE AVE DECORATIVE LIGHTING QUEENS | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jan 2022 | Jul 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q32 | MYRTLE AVE DECORATIVE LIGHTING QUEENS | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2022 | Oct 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q32 | MYRTLE AVE DECORATIVE LIGHTING QUEENS | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Oct 2022 | Feb 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q32 | MYRTLE AVE DECORATIVE LIGHTING QUEENS | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Feb 2023 | Jun 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q32 | MYRTLE AVE DECORATIVE LIGHTING QUEENS | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jun 2023 | Oct 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q32 | MYRTLE AVE DECORATIVE LIGHTING QUEENS | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Jun 2028 | Jan 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q32 | MYRTLE AVE DECORATIVE LIGHTING QUEENS | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jan 2024 | Mar 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q32 | MYRTLE AVE DECORATIVE LIGHTING QUEENS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Mar 2024 | Apr 2027
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q33 | Lght along Merrick bt. Hook Creek Blvd &Springfield Blvd | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2017 | Jan 2018
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q33 | Lght along Merrick bt. Hook Creek Blvd &Springfield Blvd | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jan 2018 | Jul 2018
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q33 | Lght along Merrick bt. Hook Creek Blvd &Springfield Blvd | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2018 | Oct 2018
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q33 | Lght along Merrick bt. Hook Creek Blvd &Springfield Blvd | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q33 | Lght along Merrick bt. Hook Creek Blvd &Springfield Blvd | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q33 | Lght along Merrick bt. Hook Creek Blvd &Springfield Blvd | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jun 2019 | Oct 2019
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q33 | Lght along Merrick bt. Hook Creek Blvd &Springfield Blvd | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Oct 2019 | Jan 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q33 | Lght along Merrick bt. Hook Creek Blvd &Springfield Blvd | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jan 2020 | Mar 2020
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q33 | Lght along Merrick bt. Hook Creek Blvd &Springfield Blvd | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Mar 2020 | Jun 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFWHSBSRT | SBS - Real Time Totem System | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Jun 2020 | Jun 2024 | Jun 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFWHSBSRT | SBS - Real Time Totem System | 2 | CONSTRUCTION START | Jul 2020 | Aug 2020 | Jul 2024 | Aug 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFWHSBSRT | SBS - Real Time Totem System | 3 | CONSTRUCTION COMPLETION | Aug 2020 | Mar 2022 | Aug 2024 | Mar 2029
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | WHAMBEACH | HAMILTON BEACH BULKHEADS AND ROADWAYS | 1 | DEVELOP SCOPE | Jun 2019 | Aug 2019 | Jun 2021 | Aug 2021
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | WHAMBEACH | HAMILTON BEACH BULKHEADS AND ROADWAYS | 2 | PRELIMINARY DESIGN | Aug 2019 | Dec 2019 | Aug 2021 | Dec 2021
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | WHAMBEACH | HAMILTON BEACH BULKHEADS AND ROADWAYS | 3 | FINAL DESIGN | Dec 2019 | Jun 2020 | Dec 2021 | Jun 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | WHAMBEACH | HAMILTON BEACH BULKHEADS AND ROADWAYS | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Sep 2020 | Jun 2022 | Sep 2022
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | WHAMBEACH | HAMILTON BEACH BULKHEADS AND ROADWAYS | 5 | CONSTRUCTION TO 25% | Sep 2020 | Jan 2021 | Sep 2022 | Jan 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | WHAMBEACH | HAMILTON BEACH BULKHEADS AND ROADWAYS | 6 | CONSTRUCTION TO 50% | Jan 2021 | May 2021 | Jan 2023 | May 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | WHAMBEACH | HAMILTON BEACH BULKHEADS AND ROADWAYS | 7 | CONSTRUCTION TO 75% | May 2021 | Sep 2021 | May 2023 | Sep 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | WHAMBEACH | HAMILTON BEACH BULKHEADS AND ROADWAYS | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Dec 2021 | Sep 2023 | Dec 2023
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | WHAMBEACH | HAMILTON BEACH BULKHEADS AND ROADWAYS | 9 | SUBSTANTIAL COMPLETION | Dec 2021 | Feb 2022 | Dec 2023 | Feb 2024
20231026 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | WHAMBEACH | HAMILTON BEACH BULKHEADS AND ROADWAYS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2022 | Mar 2022 | Feb 2024 | Jul 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | GQGIKISE | GI - CONS OF PARKLAND RETROFITS IN KISSENA PK | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Jul 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | GQQNGI-01 | GI - DSGN & CONS OF PARKLAND RETROFITS IN QUEENS | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | GQQNGI-01 | GI - DSGN & CONS OF PARKLAND RETROFITS IN QUEENS | 2 | DESIGN | Dec 2018 | Jun 2020 | Dec 2018 | Jun 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | GQQNGI-01 | GI - DSGN & CONS OF PARKLAND RETROFITS IN QUEENS | 3 | BID/ REGISTER CONTRACT | Jun 2020 | Mar 2021 | Jun 2020 | Mar 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | GQQNGI-01 | GI - DSGN & CONS OF PARKLAND RETROFITS IN QUEENS | 4 | CONSTRUCTION | Mar 2021 | Mar 2024 | Mar 2021 | Mar 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | GQQNGI-01 | GI - DSGN & CONS OF PARKLAND RETROFITS IN QUEENS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Mar 2026 | Mar 2024 | Mar 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | IDA21-01 | OLMSTED CTR RC (BUILDING) Q099-808MA | 1 | DEVELOP SCOPE | Apr 2010 | Oct 2010 | Apr 2010 | Oct 2010
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | IDA21-01 | OLMSTED CTR RC (BUILDING) Q099-808MA | 2 | DESIGN | Oct 2010 | Oct 2011 | Oct 2010 | Oct 2011
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | IDA21-01 | OLMSTED CTR RC (BUILDING) Q099-808MA | 3 | BID/ REGISTER CONTRACT | Oct 2011 | Jul 2012 | Oct 2011 | Jul 2012
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | IDA21-01 | OLMSTED CTR RC (BUILDING) Q099-808MA | 4 | CONSTRUCTION | Jul 2012 | Jul 2013 | Jul 2012 | Jul 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | IDA21-01 | OLMSTED CTR RC (BUILDING) Q099-808MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2013 | Jul 2014 | Jul 2013 | Jul 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | LIC-CTSQP | LIC- Court Square Park - Q267-120M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | LIC-CTSQP | LIC- Court Square Park - Q267-120M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | LIC-CTSQP | LIC- Court Square Park - Q267-120M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | LIC-CTSQP | LIC- Court Square Park - Q267-120M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | LIC-CTSQP | LIC- Court Square Park - Q267-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | LIC-QNBBP | LIC-Queensbridge Baby Park Q104 | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | LIC-QNBBP | LIC-Queensbridge Baby Park Q104 | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | LIC-QNBBP | LIC-Queensbridge Baby Park Q104 | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | LIC-QNBBP | LIC-Queensbridge Baby Park Q104 | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | LIC-QNBBP | LIC-Queensbridge Baby Park Q104 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-NMKE1 | Nameoke Avenue Park- Site Work-Q509-220M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-NMKE1 | Nameoke Avenue Park- Site Work-Q509-220M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-NMKE1 | Nameoke Avenue Park- Site Work-Q509-220M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-NMKE1 | Nameoke Avenue Park- Site Work-Q509-220M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-NMKE1 | Nameoke Avenue Park- Site Work-Q509-220M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-NMKE2 | Nameoke Avenue Park- Public Restroom | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-NMKE2 | Nameoke Avenue Park- Public Restroom | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-NMKE2 | Nameoke Avenue Park- Public Restroom | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-NMKE2 | Nameoke Avenue Park- Public Restroom | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-NMKE2 | Nameoke Avenue Park- Public Restroom | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-RDFR | NDF - Redfern Playground | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-RDFR | NDF - Redfern Playground | 2 | DESIGN | Dec 2017 | Dec 2019 | Dec 2017 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-RDFR | NDF - Redfern Playground | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-RDFR | NDF - Redfern Playground | 4 | CONSTRUCTION | Sep 2020 | Sep 2022 | Sep 2020 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-RDFR | NDF - Redfern Playground | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2030
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-218MPNC | MARINE PARK- SALT MARSH CTR B057-115M | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Sep 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-218MPNC | MARINE PARK- SALT MARSH CTR B057-115M | 2 | DESIGN | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-218MPNC | MARINE PARK- SALT MARSH CTR B057-115M | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2014 | Mar 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-218MPNC | MARINE PARK- SALT MARSH CTR B057-115M | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-218MPNC | MARINE PARK- SALT MARSH CTR B057-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2016 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400FMCP | FMCP Vaults | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400FMCP | FMCP Vaults | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400FMCP | FMCP Vaults | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400FMCP | FMCP Vaults | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400FMCP | FMCP Vaults | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Jun 2031 | Sep 2025 | Jun 2031
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400LNCP | Challenge Playground R/C Q346-118M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400LNCP | Challenge Playground R/C Q346-118M | 2 | DESIGN | Dec 2017 | Dec 2019 | Dec 2017 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400LNCP | Challenge Playground R/C Q346-118M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400LNCP | Challenge Playground R/C Q346-118M | 4 | CONSTRUCTION | Sep 2020 | Sep 2022 | Sep 2020 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400LNCP | Challenge Playground R/C Q346-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400QZOO | QUEENS ZOO - AVIARY WALKWAY | 1 | DEVELOP SCOPE | Jul 2004 | Sep 2004 | Jul 2004 | Sep 2004
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400QZOO | QUEENS ZOO - AVIARY WALKWAY | 2 | DESIGN | Sep 2004 | Dec 2004 | Sep 2004 | Dec 2004
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400QZOO | QUEENS ZOO - AVIARY WALKWAY | 3 | BID/ REGISTER CONTRACT | Dec 2004 | Mar 2005 | Dec 2004 | Mar 2005
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400QZOO | QUEENS ZOO - AVIARY WALKWAY | 4 | CONSTRUCTION | Mar 2005 | Mar 2006 | Mar 2005 | Mar 2006
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400QZOO | QUEENS ZOO - AVIARY WALKWAY | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2006 | Mar 2007 | Mar 2006 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO15 | Queens Zoo - public and service path paving | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Sep 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO15 | Queens Zoo - public and service path paving | 2 | DESIGN | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO15 | Queens Zoo - public and service path paving | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2014 | Mar 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO15 | Queens Zoo - public and service path paving | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO15 | Queens Zoo - public and service path paving | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO16 | QUEENS WILDLIFE CTR - OWL EXHIBIT | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Sep 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO16 | QUEENS WILDLIFE CTR - OWL EXHIBIT | 2 | DESIGN | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO16 | QUEENS WILDLIFE CTR - OWL EXHIBIT | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2014 | Mar 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO16 | QUEENS WILDLIFE CTR - OWL EXHIBIT | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO16 | QUEENS WILDLIFE CTR - OWL EXHIBIT | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO17 | Queens Zoo - Aviary Mesh Replacement | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2022 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO17 | Queens Zoo - Aviary Mesh Replacement | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO17 | Queens Zoo - Aviary Mesh Replacement | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2022 | Mar 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO17 | Queens Zoo - Aviary Mesh Replacement | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2023 | Mar 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO17 | Queens Zoo - Aviary Mesh Replacement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2024 | Jul 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO18 | Wildlife Conservation Society Farm Fence | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO18 | Wildlife Conservation Society Farm Fence | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO18 | Wildlife Conservation Society Farm Fence | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO18 | Wildlife Conservation Society Farm Fence | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO18 | Wildlife Conservation Society Farm Fence | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO20 | Queens Zoo - Concessions Roof Replacement | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2024 | Dec 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO20 | Queens Zoo - Concessions Roof Replacement | 2 | DESIGN | Dec 2017 | Mar 2019 | Dec 2024 | Mar 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO20 | Queens Zoo - Concessions Roof Replacement | 3 | BID/ REGISTER CONTRACT | Mar 2019 | Dec 2019 | Mar 2026 | Dec 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO20 | Queens Zoo - Concessions Roof Replacement | 4 | CONSTRUCTION | Dec 2019 | Dec 2020 | Dec 2026 | Dec 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO20 | Queens Zoo - Concessions Roof Replacement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2020 | Dec 2021 | Dec 2027 | Dec 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO22 | Queens Zoo - Bear ExhibitGuest Railing/Bench replacement | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2023 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO22 | Queens Zoo - Bear ExhibitGuest Railing/Bench replacement | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2023 | Dec 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO22 | Queens Zoo - Bear ExhibitGuest Railing/Bench replacement | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO22 | Queens Zoo - Bear ExhibitGuest Railing/Bench replacement | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2025 | Sep 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO22 | Queens Zoo - Bear ExhibitGuest Railing/Bench replacement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2026 | Jun 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO23 | Queens Zoo - sh/Eagle Boardwalk/Dance Floor Replacement | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2024 | Dec 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO23 | Queens Zoo - sh/Eagle Boardwalk/Dance Floor Replacement | 2 | DESIGN | Dec 2017 | Mar 2019 | Dec 2024 | Mar 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO23 | Queens Zoo - sh/Eagle Boardwalk/Dance Floor Replacement | 3 | BID/ REGISTER CONTRACT | Mar 2019 | Dec 2019 | Mar 2026 | Dec 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO23 | Queens Zoo - sh/Eagle Boardwalk/Dance Floor Replacement | 4 | CONSTRUCTION | Dec 2019 | Dec 2020 | Dec 2026 | Dec 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO23 | Queens Zoo - sh/Eagle Boardwalk/Dance Floor Replacement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2020 | Dec 2021 | Dec 2027 | Dec 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZOO4 | Queens Zoo - Admnistration Building - roof replacement | 1 | DEVELOP SCOPE | Jul 2008 | Sep 2008 | Jul 2021 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZOO4 | Queens Zoo - Admnistration Building - roof replacement | 2 | DESIGN | Sep 2008 | Dec 2008 | Sep 2021 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZOO4 | Queens Zoo - Admnistration Building - roof replacement | 3 | BID/ REGISTER CONTRACT | Dec 2008 | Mar 2009 | Dec 2021 | Mar 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZOO4 | Queens Zoo - Admnistration Building - roof replacement | 4 | CONSTRUCTION | Mar 2009 | Mar 2010 | Mar 2022 | Mar 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZOO4 | Queens Zoo - Admnistration Building - roof replacement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2010 | Mar 2011 | Mar 2023 | Jun 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZOO8 | Queens Zoo Education Classroom Construction Q099-123M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZOO8 | Queens Zoo Education Classroom Construction Q099-123M | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZOO8 | Queens Zoo Education Classroom Construction Q099-123M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2013 | Mar 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZOO8 | Queens Zoo Education Classroom Construction Q099-123M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZOO8 | Queens Zoo Education Classroom Construction Q099-123M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2015 | Jun 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401APFS | Astoria Pool Filtration System | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401APFS | Astoria Pool Filtration System | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401APFS | Astoria Pool Filtration System | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401APFS | Astoria Pool Filtration System | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401APFS | Astoria Pool Filtration System | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401ATH2 | ATHENS SQUARE PLAZA RC Q436-111M | 1 | DEVELOP SCOPE | Jul 2010 | Sep 2010 | Jul 2010 | Sep 2010
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401ATH2 | ATHENS SQUARE PLAZA RC Q436-111M | 2 | DESIGN | Sep 2010 | Dec 2010 | Sep 2010 | Dec 2010
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401ATH2 | ATHENS SQUARE PLAZA RC Q436-111M | 3 | BID/ REGISTER CONTRACT | Dec 2010 | Mar 2011 | Dec 2010 | Mar 2011
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401ATH2 | ATHENS SQUARE PLAZA RC Q436-111M | 4 | CONSTRUCTION | Mar 2011 | Mar 2012 | Mar 2011 | Mar 2012
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401ATH2 | ATHENS SQUARE PLAZA RC Q436-111M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2012 | Mar 2013 | Mar 2012 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401DKLL | Dutch Kills Playground R/C Q218-116M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401DKLL | Dutch Kills Playground R/C Q218-116M | 2 | DESIGN | Dec 2016 | Mar 2018 | Dec 2016 | Mar 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401DKLL | Dutch Kills Playground R/C Q218-116M | 3 | BID/ REGISTER CONTRACT | Mar 2018 | Dec 2018 | Mar 2018 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401DKLL | Dutch Kills Playground R/C Q218-116M | 4 | CONSTRUCTION | Dec 2018 | Dec 2020 | Dec 2018 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401DKLL | Dutch Kills Playground R/C Q218-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2020 | Dec 2021 | Dec 2020 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401DMPG | Ditmars Playground basketball and handball court upgrade | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401DMPG | Ditmars Playground basketball and handball court upgrade | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401DMPG | Ditmars Playground basketball and handball court upgrade | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401DMPG | Ditmars Playground basketball and handball court upgrade | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401DMPG | Ditmars Playground basketball and handball court upgrade | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Jun 2028 | Sep 2025 | Jun 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401HCSW | Hallets Cove Seawall Q226-118M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401HCSW | Hallets Cove Seawall Q226-118M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401HCSW | Hallets Cove Seawall Q226-118M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401HCSW | Hallets Cove Seawall Q226-118M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401HCSW | Hallets Cove Seawall Q226-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2030
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401HOY2 | Hoyt Playground renovations -- Improvements and restorations | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Apr 2019 | Oct 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401HOY2 | Hoyt Playground renovations -- Improvements and restorations | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401HOY2 | Hoyt Playground renovations -- Improvements and restorations | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401HOY2 | Hoyt Playground renovations -- Improvements and restorations | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401HOY2 | Hoyt Playground renovations -- Improvements and restorations | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401QBHB | Queensbridge Baby Park Handball Courts Q104-119M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401QBHB | Queensbridge Baby Park Handball Courts Q104-119M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401QBHB | Queensbridge Baby Park Handball Courts Q104-119M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401QBHB | Queensbridge Baby Park Handball Courts Q104-119M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401QBHB | Queensbridge Baby Park Handball Courts Q104-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401QSE2 | QUEENSBRIDGE PARK FIELDHOUSE CONS. Q104-114M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401QSE2 | QUEENSBRIDGE PARK FIELDHOUSE CONS. Q104-114M | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2014 | Feb 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401QSE2 | QUEENSBRIDGE PARK FIELDHOUSE CONS. Q104-114M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401QSE2 | QUEENSBRIDGE PARK FIELDHOUSE CONS. Q104-114M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Jan 2018 | Mar 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401QSE2 | QUEENSBRIDGE PARK FIELDHOUSE CONS. Q104-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2020 | Jun 2030
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401RANP | RAINEY PARK | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401RANP | RAINEY PARK | 2 | DESIGN | Dec 2022 | Dec 2024 | Dec 2022 | Dec 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401RANP | RAINEY PARK | 3 | BID/ REGISTER CONTRACT | Dec 2024 | Sep 2025 | Dec 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401RANP | RAINEY PARK | 4 | CONSTRUCTION | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401RANP | RAINEY PARK | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Sep 2028 | Sep 2027 | Sep 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401RAV2 | Ravenswood Playground R/C Q333-118M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2011 | Dec 2011
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401RAV2 | Ravenswood Playground R/C Q333-118M | 2 | DESIGN | Dec 2016 | Mar 2018 | Dec 2011 | Mar 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401RAV2 | Ravenswood Playground R/C Q333-118M | 3 | BID/ REGISTER CONTRACT | Mar 2018 | Dec 2018 | Mar 2013 | Dec 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401RAV2 | Ravenswood Playground R/C Q333-118M | 4 | CONSTRUCTION | Dec 2018 | Dec 2020 | Dec 2013 | Dec 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401RAV2 | Ravenswood Playground R/C Q333-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2020 | Dec 2021 | Dec 2015 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SHOR | Ralph Demarco Park Shoreline Reconstruction Q004-213M | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SHOR | Ralph Demarco Park Shoreline Reconstruction Q004-213M | 4 | CONSTRUCTION | Sep 2023 | Sep 2025 | Sep 2023 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SHOR | Ralph Demarco Park Shoreline Reconstruction Q004-213M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SMST | St. Michael's Playground Synthetic Turf Field R/C Q174A-119M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SMST | St. Michael's Playground Synthetic Turf Field R/C Q174A-119M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SMST | St. Michael's Playground Synthetic Turf Field R/C Q174A-119M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SMST | St. Michael's Playground Synthetic Turf Field R/C Q174A-119M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SMST | St. Michael's Playground Synthetic Turf Field R/C Q174A-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SOC2 | Socrates Sculpture Park Building Expansion Q465-117M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SOC2 | Socrates Sculpture Park Building Expansion Q465-117M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SOC2 | Socrates Sculpture Park Building Expansion Q465-117M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SOC2 | Socrates Sculpture Park Building Expansion Q465-117M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SOC2 | Socrates Sculpture Park Building Expansion Q465-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SOC3 | SOCRATES SCULPTURE PARK -REPAIR TO SEAWALL | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SOC3 | SOCRATES SCULPTURE PARK -REPAIR TO SEAWALL | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SOC3 | SOCRATES SCULPTURE PARK -REPAIR TO SEAWALL | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SOC3 | SOCRATES SCULPTURE PARK -REPAIR TO SEAWALL | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SOC3 | SOCRATES SCULPTURE PARK -REPAIR TO SEAWALL | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SOGP | SIXTEEN OAKS GROVE PK RENO | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2020 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SOGP | SIXTEEN OAKS GROVE PK RENO | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SOGP | SIXTEEN OAKS GROVE PK RENO | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SOGP | SIXTEEN OAKS GROVE PK RENO | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SOGP | SIXTEEN OAKS GROVE PK RENO | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401TBDR | Triborough Bridge Plgd C Dog Run & Bball Court Q066-116M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401TBDR | Triborough Bridge Plgd C Dog Run & Bball Court Q066-116M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401TBDR | Triborough Bridge Plgd C Dog Run & Bball Court Q066-116M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401TBDR | Triborough Bridge Plgd C Dog Run & Bball Court Q066-116M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401TBDR | Triborough Bridge Plgd C Dog Run & Bball Court Q066-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401WFF1 | WHITEY FORD FIELD: R/C OF BASEBALL FIELD Q215-118M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401WFF1 | WHITEY FORD FIELD: R/C OF BASEBALL FIELD Q215-118M | 2 | DESIGN | Dec 2017 | Mar 2019 | Dec 2017 | Mar 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401WFF1 | WHITEY FORD FIELD: R/C OF BASEBALL FIELD Q215-118M | 3 | BID/ REGISTER CONTRACT | Mar 2019 | Dec 2019 | Mar 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401WFF1 | WHITEY FORD FIELD: R/C OF BASEBALL FIELD Q215-118M | 4 | CONSTRUCTION | Dec 2019 | Dec 2021 | Dec 2019 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401WFF1 | WHITEY FORD FIELD: R/C OF BASEBALL FIELD Q215-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2021 | Dec 2022 | Dec 2021 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402DBOY | Doughboy Plaza Park Seating Area R/C Q031A-118M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402DBOY | Doughboy Plaza Park Seating Area R/C Q031A-118M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402DBOY | Doughboy Plaza Park Seating Area R/C Q031A-118M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402DBOY | Doughboy Plaza Park Seating Area R/C Q031A-118M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402DBOY | Doughboy Plaza Park Seating Area R/C Q031A-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402MPDR | Murray Plgd Dog Run | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402MPDR | Murray Plgd Dog Run | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402MPDR | Murray Plgd Dog Run | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402MPDR | Murray Plgd Dog Run | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402MPDR | Murray Plgd Dog Run | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402MPST | Murray Plgd -Replacement of synthetic turf in athletic field | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402MPST | Murray Plgd -Replacement of synthetic turf in athletic field | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402MPST | Murray Plgd -Replacement of synthetic turf in athletic field | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402MPST | Murray Plgd -Replacement of synthetic turf in athletic field | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402MPST | Murray Plgd -Replacement of synthetic turf in athletic field | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402SOHN | Carl R. Sohncke Square Renovations with Flagpole Q057-120M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jun 2016 | Dec 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402SOHN | Carl R. Sohncke Square Renovations with Flagpole Q057-120M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2016 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402SOHN | Carl R. Sohncke Square Renovations with Flagpole Q057-120M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2017 | Sep 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402SOHN | Carl R. Sohncke Square Renovations with Flagpole Q057-120M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402SOHN | Carl R. Sohncke Square Renovations with Flagpole Q057-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2019 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402TLLP | TORSNEY/LOU LODATI PARK--RECONSTRUCTION | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402TLLP | TORSNEY/LOU LODATI PARK--RECONSTRUCTION | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402TLLP | TORSNEY/LOU LODATI PARK--RECONSTRUCTION | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402TLLP | TORSNEY/LOU LODATI PARK--RECONSTRUCTION | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402TLLP | TORSNEY/LOU LODATI PARK--RECONSTRUCTION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403GOR2 | Gorman Playground Upgrades-Q085-120M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403GOR2 | Gorman Playground Upgrades-Q085-120M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403GOR2 | Gorman Playground Upgrades-Q085-120M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403GOR2 | Gorman Playground Upgrades-Q085-120M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403GOR2 | Gorman Playground Upgrades-Q085-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403NORT | Northern Playground Synthetic Field Upgrade Q363-118M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403NORT | Northern Playground Synthetic Field Upgrade Q363-118M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403NORT | Northern Playground Synthetic Field Upgrade Q363-118M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403NORT | Northern Playground Synthetic Field Upgrade Q363-118M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403NORT | Northern Playground Synthetic Field Upgrade Q363-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403TPP4 | Travers Park and Staunton Play Field R/C QG-714M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403TPP4 | Travers Park and Staunton Play Field R/C QG-714M | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403TPP4 | Travers Park and Staunton Play Field R/C QG-714M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2013 | Mar 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403TPP4 | Travers Park and Staunton Play Field R/C QG-714M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403TPP4 | Travers Park and Staunton Play Field R/C QG-714M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2015 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403TRVR | TRAVERS PARK RECONSTRUCT THE BASKETBALL COURTS | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403TRVR | TRAVERS PARK RECONSTRUCT THE BASKETBALL COURTS | 2 | DESIGN | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403TRVR | TRAVERS PARK RECONSTRUCT THE BASKETBALL COURTS | 3 | BID/ REGISTER CONTRACT | Sep 2024 | Jun 2025 | Sep 2024 | Jun 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403TRVR | TRAVERS PARK RECONSTRUCT THE BASKETBALL COURTS | 4 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403TRVR | TRAVERS PARK RECONSTRUCT THE BASKETBALL COURTS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Jun 2027 | Jun 2026 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403TTOT | Travers Park Tot Lot R/C Q303-117M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403TTOT | Travers Park Tot Lot R/C Q303-117M | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403TTOT | Travers Park Tot Lot R/C Q303-117M | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403TTOT | Travers Park Tot Lot R/C Q303-117M | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403TTOT | Travers Park Tot Lot R/C Q303-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2019 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404ATRI | AMERICAN TRIANGLE RECON | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404ATRI | AMERICAN TRIANGLE RECON | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404ATRI | AMERICAN TRIANGLE RECON | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404ATRI | AMERICAN TRIANGLE RECON | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404ATRI | AMERICAN TRIANGLE RECON | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404CCPS | Moore Homestead Playground R/C Q361-115M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404CCPS | Moore Homestead Playground R/C Q361-115M | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404CCPS | Moore Homestead Playground R/C Q361-115M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2013 | Mar 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404CCPS | Moore Homestead Playground R/C Q361-115M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404CCPS | Moore Homestead Playground R/C Q361-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2015 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404CROW | Crowley Playground R/C Q360J-121M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404CROW | Crowley Playground R/C Q360J-121M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404CROW | Crowley Playground R/C Q360J-121M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404CROW | Crowley Playground R/C Q360J-121M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404CROW | Crowley Playground R/C Q360J-121M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Mar 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404GSPS | GRAND SLOPE PK STAIRCASE RECON | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404GSPS | GRAND SLOPE PK STAIRCASE RECON | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404GSPS | GRAND SLOPE PK STAIRCASE RECON | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404GSPS | GRAND SLOPE PK STAIRCASE RECON | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404GSPS | GRAND SLOPE PK STAIRCASE RECON | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404HOPK | CPI - HOFFMAN PARK RECON Q360N-122M | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404HOPK | CPI - HOFFMAN PARK RECON Q360N-122M | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404HOPK | CPI - HOFFMAN PARK RECON Q360N-122M | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404HOPK | CPI - HOFFMAN PARK RECON Q360N-122M | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404HOPK | CPI - HOFFMAN PARK RECON Q360N-122M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Jun 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404LIND | PARK OF AMERICANS BBALL COURT RECON- LINDEN PK | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404LIND | PARK OF AMERICANS BBALL COURT RECON- LINDEN PK | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404LIND | PARK OF AMERICANS BBALL COURT RECON- LINDEN PK | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404LIND | PARK OF AMERICANS BBALL COURT RECON- LINDEN PK | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404LIND | PARK OF AMERICANS BBALL COURT RECON- LINDEN PK | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Jun 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404PATF | Park of the Americas Renovation- Q026-119M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Apr 2019 | Oct 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404PATF | Park of the Americas Renovation- Q026-119M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404PATF | Park of the Americas Renovation- Q026-119M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404PATF | Park of the Americas Renovation- Q026-119M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404PATF | Park of the Americas Renovation- Q026-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404PKAM | PARK OF THE AMERICAS PUBLIC RESTROOM BLDG Q026-123M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2014 | Dec 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404PKAM | PARK OF THE AMERICAS PUBLIC RESTROOM BLDG Q026-123M | 2 | DESIGN | Dec 2016 | Dec 2018 | Dec 2014 | Dec 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404PKAM | PARK OF THE AMERICAS PUBLIC RESTROOM BLDG Q026-123M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2016 | Sep 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404PKAM | PARK OF THE AMERICAS PUBLIC RESTROOM BLDG Q026-123M | 4 | CONSTRUCTION | Sep 2019 | Sep 2021 | Sep 2017 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404PKAM | PARK OF THE AMERICAS PUBLIC RESTROOM BLDG Q026-123M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2019 | Jun 2032
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404WMPG | William F Moore Park RECONSTRUCTION | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404WMPG | William F Moore Park RECONSTRUCTION | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404WMPG | William F Moore Park RECONSTRUCTION | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404WMPG | William F Moore Park RECONSTRUCTION | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404WMPG | William F Moore Park RECONSTRUCTION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405BENN | BENNINGER PK PLGD RENO | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405BENN | BENNINGER PK PLGD RENO | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405BENN | BENNINGER PK PLGD RENO | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405BENN | BENNINGER PK PLGD RENO | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405BENN | BENNINGER PK PLGD RENO | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Jun 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405EVE2 | Evergreen Park R/C Phase II Q302-121M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405EVE2 | Evergreen Park R/C Phase II Q302-121M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405EVE2 | Evergreen Park R/C Phase II Q302-121M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405EVE2 | Evergreen Park R/C Phase II Q302-121M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405EVE2 | Evergreen Park R/C Phase II Q302-121M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405FPPR | Frank Principe Park Renovation -Children's Play area | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405FPPR | Frank Principe Park Renovation -Children's Play area | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405FPPR | Frank Principe Park Renovation -Children's Play area | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405FPPR | Frank Principe Park Renovation -Children's Play area | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405FPPR | Frank Principe Park Renovation -Children's Play area | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405HIDR | HIGHLAND PARK DOG RUN | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405HIDR | HIGHLAND PARK DOG RUN | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405HIDR | HIGHLAND PARK DOG RUN | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405HIDR | HIGHLAND PARK DOG RUN | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405HIDR | HIGHLAND PARK DOG RUN | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405HPRR | Highland Park Ridgewood Reservoir Site Restoration | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405HPRR | Highland Park Ridgewood Reservoir Site Restoration | 2 | DESIGN | Dec 2017 | Mar 2019 | Dec 2017 | Mar 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405HPRR | Highland Park Ridgewood Reservoir Site Restoration | 3 | BID/ REGISTER CONTRACT | Mar 2019 | Dec 2019 | Mar 2019 | Mar 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405HPRR | Highland Park Ridgewood Reservoir Site Restoration | 4 | CONSTRUCTION | Dec 2019 | Dec 2021 | Mar 2021 | Mar 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405HPRR | Highland Park Ridgewood Reservoir Site Restoration | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2021 | Dec 2022 | Mar 2023 | Jun 2031
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JPCS | Juniper Park - Public Restroom Bldg recon CNYG-1922M | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JPCS | Juniper Park - Public Restroom Bldg recon CNYG-1922M | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JPCS | Juniper Park - Public Restroom Bldg recon CNYG-1922M | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JPCS | Juniper Park - Public Restroom Bldg recon CNYG-1922M | 4 | CONSTRUCTION | Sep 2024 | Mar 2026 | Sep 2024 | Mar 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JPCS | Juniper Park - Public Restroom Bldg recon CNYG-1922M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Mar 2027 | Mar 2026 | Mar 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JPSS | Juniper Valley Park Spray Shower R/C Q102-117M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JPSS | Juniper Valley Park Spray Shower R/C Q102-117M | 2 | DESIGN | Dec 2016 | Mar 2018 | Dec 2017 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JPSS | Juniper Valley Park Spray Shower R/C Q102-117M | 3 | BID/ REGISTER CONTRACT | Mar 2018 | Dec 2018 | Dec 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JPSS | Juniper Valley Park Spray Shower R/C Q102-117M | 4 | CONSTRUCTION | Dec 2018 | Dec 2020 | Sep 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JPSS | Juniper Valley Park Spray Shower R/C Q102-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2020 | Dec 2021 | Sep 2020 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JPTK | Juniper Valley Park Track & Syn. Turf Field R/C Q102-118M | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Sep 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JPTK | Juniper Valley Park Track & Syn. Turf Field R/C Q102-118M | 2 | DESIGN | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JPTK | Juniper Valley Park Track & Syn. Turf Field R/C Q102-118M | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2014 | Mar 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JPTK | Juniper Valley Park Track & Syn. Turf Field R/C Q102-118M | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JPTK | Juniper Valley Park Track & Syn. Turf Field R/C Q102-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2016 | Jun 2030
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JUNP | JUNIPER PARK MULTIPURPOSE AREA & HANDBALL COURT | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JUNP | JUNIPER PARK MULTIPURPOSE AREA & HANDBALL COURT | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JUNP | JUNIPER PARK MULTIPURPOSE AREA & HANDBALL COURT | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JUNP | JUNIPER PARK MULTIPURPOSE AREA & HANDBALL COURT | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JUNP | JUNIPER PARK MULTIPURPOSE AREA & HANDBALL COURT | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JVBB | Juniper Valley Park Baseball Fields | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JVBB | Juniper Valley Park Baseball Fields | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JVBB | Juniper Valley Park Baseball Fields | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JVBB | Juniper Valley Park Baseball Fields | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JVBB | Juniper Valley Park Baseball Fields | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405MPPG | Mafera Park--Playground Renovation | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405MPPG | Mafera Park--Playground Renovation | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405MPPG | Mafera Park--Playground Renovation | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405MPPG | Mafera Park--Playground Renovation | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405MPPG | Mafera Park--Playground Renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Jun 2028 | Sep 2025 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405MPSL | MAURICE (FRANK PRINCIPE) PARK LIGHTING--CONST OF SPORT Light | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405MPSL | MAURICE (FRANK PRINCIPE) PARK LIGHTING--CONST OF SPORT Light | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405MPSL | MAURICE (FRANK PRINCIPE) PARK LIGHTING--CONST OF SPORT Light | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405MPSL | MAURICE (FRANK PRINCIPE) PARK LIGHTING--CONST OF SPORT Light | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405MPSL | MAURICE (FRANK PRINCIPE) PARK LIGHTING--CONST OF SPORT Light | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405RRGH | Ridgewood Reservoir Gatehouse Rehab Q020-318M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405RRGH | Ridgewood Reservoir Gatehouse Rehab Q020-318M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405RRGH | Ridgewood Reservoir Gatehouse Rehab Q020-318M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405RRGH | Ridgewood Reservoir Gatehouse Rehab Q020-318M | 4 | CONSTRUCTION | Sep 2019 | Mar 2021 | Sep 2019 | Mar 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405RRGH | Ridgewood Reservoir Gatehouse Rehab Q020-318M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Mar 2022 | Mar 2021 | Jun 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405RRIV | Ridgewood Reservoir Invasive Removals -Q020-518M | 2 | DESIGN | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405RRIV | Ridgewood Reservoir Invasive Removals -Q020-518M | 3 | BID/ REGISTER CONTRACT | Sep 2018 | Jun 2019 | Sep 2018 | Jun 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405RRIV | Ridgewood Reservoir Invasive Removals -Q020-518M | 4 | CONSTRUCTION | Jun 2019 | Dec 2021 | Jun 2019 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405RRIV | Ridgewood Reservoir Invasive Removals -Q020-518M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2021 | Dec 2023 | Dec 2021 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405STR2 | Starr Playground R/C Phase II Q291-120M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2013 | Dec 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405STR2 | Starr Playground R/C Phase II Q291-120M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2013 | Dec 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405STR2 | Starr Playground R/C Phase II Q291-120M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2014 | Sep 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405STR2 | Starr Playground R/C Phase II Q291-120M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2015 | Sep 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405STR2 | Starr Playground R/C Phase II Q291-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2016 | Sep 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405STRR | Starr Playground MPPA R/C Q291-118M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405STRR | Starr Playground MPPA R/C Q291-118M | 2 | DESIGN | Dec 2016 | Mar 2018 | Dec 2016 | Mar 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405STRR | Starr Playground MPPA R/C Q291-118M | 3 | BID/ REGISTER CONTRACT | Mar 2018 | Dec 2018 | Mar 2018 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405STRR | Starr Playground MPPA R/C Q291-118M | 4 | CONSTRUCTION | Dec 2018 | Dec 2020 | Dec 2018 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405STRR | Starr Playground MPPA R/C Q291-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2020 | Dec 2021 | Dec 2020 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405VITO | Vito F. Maranzano Glendale Park- mats & drainage work | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405VITO | Vito F. Maranzano Glendale Park- mats & drainage work | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405VITO | Vito F. Maranzano Glendale Park- mats & drainage work | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405VITO | Vito F. Maranzano Glendale Park- mats & drainage work | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405VITO | Vito F. Maranzano Glendale Park- mats & drainage work | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406GCPK | GRAND CENTRAL PARKWAY LANDSCAPING Q084-106M | 1 | DEVELOP SCOPE | Jun 2007 | Aug 2007 | Jun 2007 | Dec 2009
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406GCPK | GRAND CENTRAL PARKWAY LANDSCAPING Q084-106M | 2 | DESIGN | Aug 2007 | Nov 2007 | Jul 2009 | Sep 2009
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406GCPK | GRAND CENTRAL PARKWAY LANDSCAPING Q084-106M | 3 | BID/ REGISTER CONTRACT | Nov 2007 | Feb 2008 | Sep 2009 | Sep 2009
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406GCPK | GRAND CENTRAL PARKWAY LANDSCAPING Q084-106M | 4 | CONSTRUCTION | Feb 2008 | Feb 2009 | Sep 2009 | Dec 2010
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406GCPK | GRAND CENTRAL PARKWAY LANDSCAPING Q084-106M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2009 | Feb 2010 | Dec 2010 | Sep 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406PEGT | Project Eden- Greenthumb Community Gardens--Internal Water I | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406PEGT | Project Eden- Greenthumb Community Gardens--Internal Water I | 2 | DESIGN | Dec 2022 | Jun 2024 | Dec 2022 | Jun 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406PEGT | Project Eden- Greenthumb Community Gardens--Internal Water I | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406PEGT | Project Eden- Greenthumb Community Gardens--Internal Water I | 4 | CONSTRUCTION | Mar 2025 | Sep 2026 | Mar 2025 | Sep 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406PEGT | Project Eden- Greenthumb Community Gardens--Internal Water I | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Sep 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406PG62 | Playground Sixty Two R/C Q377-120M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406PG62 | Playground Sixty Two R/C Q377-120M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406PG62 | Playground Sixty Two R/C Q377-120M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406PG62 | Playground Sixty Two R/C Q377-120M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406PG62 | Playground Sixty Two R/C Q377-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Mar 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406YPFN | Yellowstone Park Fencing Pt. 1 R/C 68th Avenue Q425-118M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Sep 2012 | Mar 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406YPFN | Yellowstone Park Fencing Pt. 1 R/C 68th Avenue Q425-118M | 2 | DESIGN | Dec 2018 | Dec 2019 | Mar 2013 | Mar 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406YPFN | Yellowstone Park Fencing Pt. 1 R/C 68th Avenue Q425-118M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Mar 2014 | Dec 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406YPFN | Yellowstone Park Fencing Pt. 1 R/C 68th Avenue Q425-118M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Dec 2014 | Dec 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406YPFN | Yellowstone Park Fencing Pt. 1 R/C 68th Avenue Q425-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Dec 2015 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BBSF | COLLEGE PT FIELDS CONVERT BASEBALL TO SOCCER FIELD | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BBSF | COLLEGE PT FIELDS CONVERT BASEBALL TO SOCCER FIELD | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BBSF | COLLEGE PT FIELDS CONVERT BASEBALL TO SOCCER FIELD | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BBSF | COLLEGE PT FIELDS CONVERT BASEBALL TO SOCCER FIELD | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BBSF | COLLEGE PT FIELDS CONVERT BASEBALL TO SOCCER FIELD | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BLND | Bland Playground Lighting (Q326-120M) | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BLND | Bland Playground Lighting (Q326-120M) | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BLND | Bland Playground Lighting (Q326-120M) | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BLND | Bland Playground Lighting (Q326-120M) | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BLND | Bland Playground Lighting (Q326-120M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BPBC | BOWNE PARK BOCCE COURTS Q006-111M | 1 | DEVELOP SCOPE | Jul 2010 | Sep 2010 | Jul 2010 | Sep 2010
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BPBC | BOWNE PARK BOCCE COURTS Q006-111M | 2 | DESIGN | Sep 2010 | Dec 2010 | Sep 2010 | Dec 2010
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BPBC | BOWNE PARK BOCCE COURTS Q006-111M | 3 | BID/ REGISTER CONTRACT | Dec 2010 | Mar 2011 | Dec 2010 | Mar 2011
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BPBC | BOWNE PARK BOCCE COURTS Q006-111M | 4 | CONSTRUCTION | Mar 2011 | Mar 2012 | Mar 2011 | Mar 2012
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BPBC | BOWNE PARK BOCCE COURTS Q006-111M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2012 | Mar 2013 | Mar 2012 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BPFF | BOWNE PK POND R/C Q006-215MA | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Apr 2019 | Oct 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BPFF | BOWNE PK POND R/C Q006-215MA | 2 | DESIGN | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BPFF | BOWNE PK POND R/C Q006-215MA | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2014 | Mar 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BPFF | BOWNE PK POND R/C Q006-215MA | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BPFF | BOWNE PK POND R/C Q006-215MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2016 | Jun 2030
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BTPL | Bay Terrace Playground R/C Q399-118M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BTPL | Bay Terrace Playground R/C Q399-118M | 2 | DESIGN | Dec 2016 | Mar 2018 | Dec 2016 | Mar 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BTPL | Bay Terrace Playground R/C Q399-118M | 3 | BID/ REGISTER CONTRACT | Mar 2018 | Dec 2018 | Mar 2018 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BTPL | Bay Terrace Playground R/C Q399-118M | 4 | CONSTRUCTION | Dec 2018 | Dec 2020 | Dec 2018 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BTPL | Bay Terrace Playground R/C Q399-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2020 | Dec 2021 | Dec 2020 | Jun 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BWPK | Bowne Park Plaza Renovations ( bocce courts) | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2007 | Sep 2007
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BWPK | Bowne Park Plaza Renovations ( bocce courts) | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BWPK | Bowne Park Plaza Renovations ( bocce courts) | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BWPK | Bowne Park Plaza Renovations ( bocce courts) | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BWPK | Bowne Park Plaza Renovations ( bocce courts) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407CPSC | College Point Fields Cons. of a Football Field Q476-117M | 1 | DEVELOP SCOPE | Jul 2010 | Sep 2010 | Jul 2007 | Sep 2007
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407CPSC | College Point Fields Cons. of a Football Field Q476-117M | 2 | DESIGN | Sep 2010 | Dec 2010 | Sep 2010 | Dec 2010
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407CPSC | College Point Fields Cons. of a Football Field Q476-117M | 3 | BID/ REGISTER CONTRACT | Dec 2010 | Mar 2011 | Dec 2010 | Mar 2011
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407CPSC | College Point Fields Cons. of a Football Field Q476-117M | 4 | CONSTRUCTION | Mar 2011 | Mar 2012 | Mar 2011 | Mar 2012
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407CPSC | College Point Fields Cons. of a Football Field Q476-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2012 | Mar 2013 | Mar 2012 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FFAR | Flushing Fields Athletic Renovation Q086-223M | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FFAR | Flushing Fields Athletic Renovation Q086-223M | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FFAR | Flushing Fields Athletic Renovation Q086-223M | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FFAR | Flushing Fields Athletic Renovation Q086-223M | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FFAR | Flushing Fields Athletic Renovation Q086-223M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FGP2 | Frank Golden Pk - R/C of Athletic Fields Phase II Q445-118M | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Sep 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FGP2 | Frank Golden Pk - R/C of Athletic Fields Phase II Q445-118M | 2 | DESIGN | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FGP2 | Frank Golden Pk - R/C of Athletic Fields Phase II Q445-118M | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2014 | Mar 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FGP2 | Frank Golden Pk - R/C of Athletic Fields Phase II Q445-118M | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FGP2 | Frank Golden Pk - R/C of Athletic Fields Phase II Q445-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2016 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FLBC | FRANCIS LEWIS PK BOCCIE CTS Q126-107MA | 2 | DESIGN | Sep 2006 | Dec 2006 | Sep 2006 | Dec 2006
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FLBC | FRANCIS LEWIS PK BOCCIE CTS Q126-107MA | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Apr 2009 | Apr 2009
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FLBC | FRANCIS LEWIS PK BOCCIE CTS Q126-107MA | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Aug 2009 | Apr 2010
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FLBC | FRANCIS LEWIS PK BOCCIE CTS Q126-107MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Apr 2010 | Nov 2011
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FLPT | Francis Lewis Park Pathway & Entrance Way Impts Q126-120M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FLPT | Francis Lewis Park Pathway & Entrance Way Impts Q126-120M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FLPT | Francis Lewis Park Pathway & Entrance Way Impts Q126-120M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FLPT | Francis Lewis Park Pathway & Entrance Way Impts Q126-120M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FLPT | Francis Lewis Park Pathway & Entrance Way Impts Q126-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FLPU | FRANCIS LEWIS PARK UPGRADE--PUBLIC RESTROOMS, etc. | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FLPU | FRANCIS LEWIS PARK UPGRADE--PUBLIC RESTROOMS, etc. | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FLPU | FRANCIS LEWIS PARK UPGRADE--PUBLIC RESTROOMS, etc. | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FLPU | FRANCIS LEWIS PARK UPGRADE--PUBLIC RESTROOMS, etc. | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FLPU | FRANCIS LEWIS PARK UPGRADE--PUBLIC RESTROOMS, etc. | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407LBCS | LITTLE BAY PARK C/S & PARKING LOT Q010-112M/412M | 1 | DEVELOP SCOPE | Jul 2006 | Sep 2006 | Jul 2006 | Sep 2006
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407LBCS | LITTLE BAY PARK C/S & PARKING LOT Q010-112M/412M | 2 | DESIGN | Sep 2006 | Dec 2006 | Sep 2006 | Dec 2006
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407LBCS | LITTLE BAY PARK C/S & PARKING LOT Q010-112M/412M | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Dec 2006 | Mar 2007
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407LBCS | LITTLE BAY PARK C/S & PARKING LOT Q010-112M/412M | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Mar 2007 | Mar 2008
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407LBCS | LITTLE BAY PARK C/S & PARKING LOT Q010-112M/412M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Mar 2008 | Dec 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407LBDR | LITTLE BAY PARK (CLEARVIEW BEACH) DOG RUN Q010-107M | 1 | DEVELOP SCOPE | Jul 2006 | Sep 2006 | Jul 2006 | Sep 2006
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407LBDR | LITTLE BAY PARK (CLEARVIEW BEACH) DOG RUN Q010-107M | 2 | DESIGN | Sep 2006 | Dec 2006 | Sep 2006 | Dec 2006
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407LBDR | LITTLE BAY PARK (CLEARVIEW BEACH) DOG RUN Q010-107M | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Dec 2006 | Mar 2007
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407LBDR | LITTLE BAY PARK (CLEARVIEW BEACH) DOG RUN Q010-107M | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Mar 2007 | Mar 2008
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407LBDR | LITTLE BAY PARK (CLEARVIEW BEACH) DOG RUN Q010-107M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Mar 2008 | Jun 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407LBSF | LITTLE BAY PARK SOCCER FIELD R/C Q010-114M | 1 | DEVELOP SCOPE | Jul 2010 | Sep 2010 | Jul 2010 | Sep 2010
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407LBSF | LITTLE BAY PARK SOCCER FIELD R/C Q010-114M | 2 | DESIGN | Sep 2010 | Dec 2010 | Sep 2010 | Dec 2010
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407LBSF | LITTLE BAY PARK SOCCER FIELD R/C Q010-114M | 3 | BID/ REGISTER CONTRACT | Dec 2010 | Mar 2011 | Dec 2010 | Mar 2011
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407LBSF | LITTLE BAY PARK SOCCER FIELD R/C Q010-114M | 4 | CONSTRUCTION | Mar 2011 | Mar 2012 | Mar 2011 | Mar 2012
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407LBSF | LITTLE BAY PARK SOCCER FIELD R/C Q010-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2012 | Mar 2013 | Mar 2012 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407LLHM | LEWIS LATIMER HOUSE MUSEUM INTERNET--INTERNET INSTALLATION | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407LLHM | LEWIS LATIMER HOUSE MUSEUM INTERNET--INTERNET INSTALLATION | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407LLHM | LEWIS LATIMER HOUSE MUSEUM INTERNET--INTERNET INSTALLATION | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407LLHM | LEWIS LATIMER HOUSE MUSEUM INTERNET--INTERNET INSTALLATION | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407LLHM | LEWIS LATIMER HOUSE MUSEUM INTERNET--INTERNET INSTALLATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Jun 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MAPL | Maple Playground R/C Q211-117M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2007 | Sep 2007
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MAPL | Maple Playground R/C Q211-117M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MAPL | Maple Playground R/C Q211-117M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MAPL | Maple Playground R/C Q211-117M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MAPL | Maple Playground R/C Q211-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Jun 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MCN4 | Herman MacNeil Park Entrance and Pathways | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MCN4 | Herman MacNeil Park Entrance and Pathways | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MCN4 | Herman MacNeil Park Entrance and Pathways | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MCN4 | Herman MacNeil Park Entrance and Pathways | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MCN4 | Herman MacNeil Park Entrance and Pathways | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MNPW | MACNEIL PARK WATERFRONT REPAIRS | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MNPW | MACNEIL PARK WATERFRONT REPAIRS | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MNPW | MACNEIL PARK WATERFRONT REPAIRS | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MNPW | MACNEIL PARK WATERFRONT REPAIRS | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MNPW | MACNEIL PARK WATERFRONT REPAIRS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MPSW | MACNEIL PARK SEAWALL Q009-114MA | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MPSW | MACNEIL PARK SEAWALL Q009-114MA | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MPSW | MACNEIL PARK SEAWALL Q009-114MA | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2013 | Mar 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MPSW | MACNEIL PARK SEAWALL Q009-114MA | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MPSW | MACNEIL PARK SEAWALL Q009-114MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2015 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407PWLL | Powells Cove Park - Restoration | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407PWLL | Powells Cove Park - Restoration | 2 | DESIGN | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407PWLL | Powells Cove Park - Restoration | 3 | BID/ REGISTER CONTRACT | Sep 2021 | Jun 2022 | Sep 2021 | Jun 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407PWLL | Powells Cove Park - Restoration | 4 | CONSTRUCTION | Jun 2022 | Dec 2024 | Jun 2022 | Dec 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407PWLL | Powells Cove Park - Restoration | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2024 | Dec 2026 | Dec 2024 | Dec 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407WBPK | WEEPING BEECH PK RENO MULTI PLAY AREA, BBALL COURTS | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407WBPK | WEEPING BEECH PK RENO MULTI PLAY AREA, BBALL COURTS | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407WBPK | WEEPING BEECH PK RENO MULTI PLAY AREA, BBALL COURTS | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407WBPK | WEEPING BEECH PK RENO MULTI PLAY AREA, BBALL COURTS | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407WBPK | WEEPING BEECH PK RENO MULTI PLAY AREA, BBALL COURTS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Jun 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CHLG | Challenge Playground MPPA Reconstruction | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CHLG | Challenge Playground MPPA Reconstruction | 2 | DESIGN | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CHLG | Challenge Playground MPPA Reconstruction | 3 | BID/ REGISTER CONTRACT | Sep 2024 | Jun 2025 | Sep 2024 | Jun 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CHLG | Challenge Playground MPPA Reconstruction | 4 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CHLG | Challenge Playground MPPA Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Jun 2027 | Jun 2026 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CPGA | Cunningham Park Garage Space Conversion Q021-119M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2013 | Sep 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CPGA | Cunningham Park Garage Space Conversion Q021-119M | 2 | DESIGN | Dec 2016 | Dec 2018 | Dec 2016 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CPGA | Cunningham Park Garage Space Conversion Q021-119M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CPGA | Cunningham Park Garage Space Conversion Q021-119M | 4 | CONSTRUCTION | Sep 2019 | Sep 2021 | Sep 2019 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CPGA | Cunningham Park Garage Space Conversion Q021-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408HMSC | Hoover - Manton Plgd -- Resurface basketball & Handball ct | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408HMSC | Hoover - Manton Plgd -- Resurface basketball & Handball ct | 2 | DESIGN | Dec 2022 | Jun 2024 | Dec 2022 | Jun 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408HMSC | Hoover - Manton Plgd -- Resurface basketball & Handball ct | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408HMSC | Hoover - Manton Plgd -- Resurface basketball & Handball ct | 4 | CONSTRUCTION | Mar 2025 | Sep 2026 | Mar 2025 | Sep 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408HMSC | Hoover - Manton Plgd -- Resurface basketball & Handball ct | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Sep 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408HOV2 | Hoover Playground Q220G-121M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408HOV2 | Hoover Playground Q220G-121M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408HOV2 | Hoover Playground Q220G-121M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408HOV2 | Hoover Playground Q220G-121M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408HOV2 | Hoover Playground Q220G-121M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Jun 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408MLDY | Site for Mother Language Day in Captain Tilly Park | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2024 | Dec 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408MLDY | Site for Mother Language Day in Captain Tilly Park | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2024 | Dec 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408MLDY | Site for Mother Language Day in Captain Tilly Park | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2025 | Sep 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408MLDY | Site for Mother Language Day in Captain Tilly Park | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2026 | Sep 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408MLDY | Site for Mother Language Day in Captain Tilly Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2027 | Sep 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408VAN2 | Vanderbilt Motor Parkway Repaving Phase II QG-719M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jun 2016 | Dec 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408VAN2 | Vanderbilt Motor Parkway Repaving Phase II QG-719M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2016 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408VAN2 | Vanderbilt Motor Parkway Repaving Phase II QG-719M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2017 | Sep 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408VAN2 | Vanderbilt Motor Parkway Repaving Phase II QG-719M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408VAN2 | Vanderbilt Motor Parkway Repaving Phase II QG-719M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2019 | Jun 2030
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408VAND | Vanderbilt Motor Parkway Repaving QG-718M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Jul 2021 | Jul 2020 | Jul 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409EQTY | Equity Park Playground Upgrades | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2013 | Dec 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409EQTY | Equity Park Playground Upgrades | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2013 | Dec 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409EQTY | Equity Park Playground Upgrades | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2014 | Sep 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409EQTY | Equity Park Playground Upgrades | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2015 | Sep 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409EQTY | Equity Park Playground Upgrades | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2016 | Sep 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPAP | Forest Park Asphalt Pathways Improvements | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Apr 2024 | Oct 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPAP | Forest Park Asphalt Pathways Improvements | 2 | DESIGN | Dec 2020 | Dec 2021 | Oct 2024 | Oct 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPAP | Forest Park Asphalt Pathways Improvements | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Oct 2025 | Jul 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPAP | Forest Park Asphalt Pathways Improvements | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Jul 2026 | Jul 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPAP | Forest Park Asphalt Pathways Improvements | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Jul 2027 | Apr 2032
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPG3 | FOREST PARK GREENHOUSES Q015-117MA1 | 1 | DEVELOP SCOPE | Dec 2012 | Feb 2013 | Dec 2012 | Feb 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPG3 | FOREST PARK GREENHOUSES Q015-117MA1 | 2 | DESIGN | Mar 2013 | May 2013 | Mar 2013 | May 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPG3 | FOREST PARK GREENHOUSES Q015-117MA1 | 3 | BID/ REGISTER CONTRACT | May 2013 | Aug 2013 | May 2013 | Aug 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPG3 | FOREST PARK GREENHOUSES Q015-117MA1 | 4 | CONSTRUCTION | Aug 2013 | Aug 2014 | Aug 2013 | Aug 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPG3 | FOREST PARK GREENHOUSES Q015-117MA1 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2014 | Aug 2015 | Aug 2014 | Aug 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPP2 | Forest Park Pathways | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Oct 2016 | Jan 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPP2 | Forest Park Pathways | 2 | DESIGN | Sep 2015 | Dec 2015 | Jan 2017 | Apr 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPP2 | Forest Park Pathways | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Apr 2017 | Jul 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPP2 | Forest Park Pathways | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Jul 2017 | Jul 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPP2 | Forest Park Pathways | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Jul 2018 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FRDR | FOREST PARK DOG RUN RENO | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FRDR | FOREST PARK DOG RUN RENO | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FRDR | FOREST PARK DOG RUN RENO | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FRDR | FOREST PARK DOG RUN RENO | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FRDR | FOREST PARK DOG RUN RENO | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409MARD | Glendale Entrance to Forest Park Q015-217MA | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409MARD | Glendale Entrance to Forest Park Q015-217MA | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409MARD | Glendale Entrance to Forest Park Q015-217MA | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409MARD | Glendale Entrance to Forest Park Q015-217MA | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409MARD | Glendale Entrance to Forest Park Q015-217MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409PRPC | PHIL "SCOOTER" RIZZUTO PARK/SMOKEY OVAL BB HANDBALL COURT RC | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409PRPC | PHIL "SCOOTER" RIZZUTO PARK/SMOKEY OVAL BB HANDBALL COURT RC | 2 | DESIGN | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409PRPC | PHIL "SCOOTER" RIZZUTO PARK/SMOKEY OVAL BB HANDBALL COURT RC | 3 | BID/ REGISTER CONTRACT | Sep 2024 | Jun 2025 | Sep 2024 | Jun 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409PRPC | PHIL "SCOOTER" RIZZUTO PARK/SMOKEY OVAL BB HANDBALL COURT RC | 4 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409PRPC | PHIL "SCOOTER" RIZZUTO PARK/SMOKEY OVAL BB HANDBALL COURT RC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Jun 2027 | Jun 2026 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410ALST | Al Stabile Playground Renovation Q285-119M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2016 | Dec 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410ALST | Al Stabile Playground Renovation Q285-119M | 2 | DESIGN | Dec 2018 | Dec 2020 | Dec 2016 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410ALST | Al Stabile Playground Renovation Q285-119M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410ALST | Al Stabile Playground Renovation Q285-119M | 4 | CONSTRUCTION | Sep 2021 | Sep 2023 | Sep 2019 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410ALST | Al Stabile Playground Renovation Q285-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2021 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410BYRN | Edward Byrne Park Playground PRB X092-118M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410BYRN | Edward Byrne Park Playground PRB X092-118M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410BYRN | Edward Byrne Park Playground PRB X092-118M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410BYRN | Edward Byrne Park Playground PRB X092-118M | 4 | CONSTRUCTION | Sep 2019 | Mar 2021 | Sep 2019 | Mar 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410BYRN | Edward Byrne Park Playground PRB X092-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Mar 2022 | Mar 2021 | Jun 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410PEBP | Recon of Police Officer Edward O'Byrne Park Q092-119M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410PEBP | Recon of Police Officer Edward O'Byrne Park Q092-119M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410PEBP | Recon of Police Officer Edward O'Byrne Park Q092-119M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410PEBP | Recon of Police Officer Edward O'Byrne Park Q092-119M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410PEBP | Recon of Police Officer Edward O'Byrne Park Q092-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2030
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410ROCK | ROCKET PLGD RENOVATION | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410ROCK | ROCKET PLGD RENOVATION | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410ROCK | ROCKET PLGD RENOVATION | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410ROCK | ROCKET PLGD RENOVATION | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410ROCK | ROCKET PLGD RENOVATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410SCN2 | Harold Schneiderman Playground Upgrades Q408-121M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410SCN2 | Harold Schneiderman Playground Upgrades Q408-121M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410SCN2 | Harold Schneiderman Playground Upgrades Q408-121M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410SCN2 | Harold Schneiderman Playground Upgrades Q408-121M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410SCN2 | Harold Schneiderman Playground Upgrades Q408-121M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410TPAF | TUDOR PARK CONSTRUCT NEW ADULT FITNESS AREA | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410TPAF | TUDOR PARK CONSTRUCT NEW ADULT FITNESS AREA | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410TPAF | TUDOR PARK CONSTRUCT NEW ADULT FITNESS AREA | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410TPAF | TUDOR PARK CONSTRUCT NEW ADULT FITNESS AREA | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410TPAF | TUDOR PARK CONSTRUCT NEW ADULT FITNESS AREA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411APE2 | ALLEY POND ENVIRONMENTAL CENTER & CONS. OF ANNEX Q001-110M | 1 | DEVELOP SCOPE | Jul 2006 | Sep 2006 | Jul 2006 | Sep 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411APE2 | ALLEY POND ENVIRONMENTAL CENTER & CONS. OF ANNEX Q001-110M | 2 | DESIGN | Sep 2006 | Dec 2006 | Oct 2013 | Dec 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411APE2 | ALLEY POND ENVIRONMENTAL CENTER & CONS. OF ANNEX Q001-110M | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Jan 2014 | May 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411APE2 | ALLEY POND ENVIRONMENTAL CENTER & CONS. OF ANNEX Q001-110M | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | May 2017 | May 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411APE2 | ALLEY POND ENVIRONMENTAL CENTER & CONS. OF ANNEX Q001-110M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | May 2018 | Apr 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411APNA | Alley Pond Park Natural Areas Restoration Phase 3 | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411APNA | Alley Pond Park Natural Areas Restoration Phase 3 | 2 | DESIGN | Dec 2021 | Dec 2023 | Dec 2021 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411APNA | Alley Pond Park Natural Areas Restoration Phase 3 | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411APNA | Alley Pond Park Natural Areas Restoration Phase 3 | 4 | CONSTRUCTION | Sep 2024 | Sep 2027 | Sep 2024 | Sep 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411APNA | Alley Pond Park Natural Areas Restoration Phase 3 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Sep 2029 | Sep 2027 | Sep 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411CDTR | Captain Dermody Triangle- Reconstruction of the triangle | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411CDTR | Captain Dermody Triangle- Reconstruction of the triangle | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411CDTR | Captain Dermody Triangle- Reconstruction of the triangle | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411CDTR | Captain Dermody Triangle- Reconstruction of the triangle | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411CDTR | Captain Dermody Triangle- Reconstruction of the triangle | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411CRPG | CROCHERON PK RECON PLGD | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411CRPG | CROCHERON PK RECON PLGD | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411CRPG | CROCHERON PK RECON PLGD | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411CRPG | CROCHERON PK RECON PLGD | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411CRPG | CROCHERON PK RECON PLGD | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411OKPG | OAKLAND GARDENS - RECON OF MULI PLAY AREA & PLGD | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411OKPG | OAKLAND GARDENS - RECON OF MULI PLAY AREA & PLGD | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411OKPG | OAKLAND GARDENS - RECON OF MULI PLAY AREA & PLGD | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411OKPG | OAKLAND GARDENS - RECON OF MULI PLAY AREA & PLGD | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411OKPG | OAKLAND GARDENS - RECON OF MULI PLAY AREA & PLGD | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411OKPT | Oakland Lake Pathways Reconstruction Q001-120M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411OKPT | Oakland Lake Pathways Reconstruction Q001-120M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411OKPT | Oakland Lake Pathways Reconstruction Q001-120M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411OKPT | Oakland Lake Pathways Reconstruction Q001-120M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411OKPT | Oakland Lake Pathways Reconstruction Q001-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411TELE | TELEPHONE PLGD RENOVATION | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411TELE | TELEPHONE PLGD RENOVATION | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411TELE | TELEPHONE PLGD RENOVATION | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411TELE | TELEPHONE PLGD RENOVATION | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411TELE | TELEPHONE PLGD RENOVATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412BAI2 | Baisley Pond Park Track & Field, Syn. Turf R/C Q005-119M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412BAI2 | Baisley Pond Park Track & Field, Syn. Turf R/C Q005-119M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412BAI2 | Baisley Pond Park Track & Field, Syn. Turf R/C Q005-119M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412BAI2 | Baisley Pond Park Track & Field, Syn. Turf R/C Q005-119M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412BAI2 | Baisley Pond Park Track & Field, Syn. Turf R/C Q005-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412BPTH | BAISLEY PARK PATHS--PATHWAY RESURFACING FOR BAISLEY PARK | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412BPTH | BAISLEY PARK PATHS--PATHWAY RESURFACING FOR BAISLEY PARK | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412BPTH | BAISLEY PARK PATHS--PATHWAY RESURFACING FOR BAISLEY PARK | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412BPTH | BAISLEY PARK PATHS--PATHWAY RESURFACING FOR BAISLEY PARK | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412BPTH | BAISLEY PARK PATHS--PATHWAY RESURFACING FOR BAISLEY PARK | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412CRDP | Dr. Charles Drew Park- Fields Sidewalks and lighting | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412CRDP | Dr. Charles Drew Park- Fields Sidewalks and lighting | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412CRDP | Dr. Charles Drew Park- Fields Sidewalks and lighting | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412CRDP | Dr. Charles Drew Park- Fields Sidewalks and lighting | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412CRDP | Dr. Charles Drew Park- Fields Sidewalks and lighting | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412DKWP | Detective Keith L Williams Park (Liberty) Basketball Cts | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412DKWP | Detective Keith L Williams Park (Liberty) Basketball Cts | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412DKWP | Detective Keith L Williams Park (Liberty) Basketball Cts | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412DKWP | Detective Keith L Williams Park (Liberty) Basketball Cts | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412DKWP | Detective Keith L Williams Park (Liberty) Basketball Cts | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412DOP3 | Daniel M. O'Connell Playground Renovation Q106-120M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412DOP3 | Daniel M. O'Connell Playground Renovation Q106-120M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412DOP3 | Daniel M. O'Connell Playground Renovation Q106-120M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412DOP3 | Daniel M. O'Connell Playground Renovation Q106-120M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412DOP3 | Daniel M. O'Connell Playground Renovation Q106-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412GECG | George Eagle Carr Comm Garden -- Install water infrastructur | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412GECG | George Eagle Carr Comm Garden -- Install water infrastructur | 2 | DESIGN | Dec 2022 | Jun 2024 | Dec 2022 | Jun 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412GECG | George Eagle Carr Comm Garden -- Install water infrastructur | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412GECG | George Eagle Carr Comm Garden -- Install water infrastructur | 4 | CONSTRUCTION | Mar 2025 | Sep 2026 | Mar 2025 | Sep 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412GECG | George Eagle Carr Comm Garden -- Install water infrastructur | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Sep 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412HARP | HARVARD PLGD RECON | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412HARP | HARVARD PLGD RECON | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412HARP | HARVARD PLGD RECON | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412HARP | HARVARD PLGD RECON | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412HARP | HARVARD PLGD RECON | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412JAMP | Jamaica Playground -- Renovate MPPA Q301-121M | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2013 | Sep 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412JAMP | Jamaica Playground -- Renovate MPPA Q301-121M | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412JAMP | Jamaica Playground -- Renovate MPPA Q301-121M | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412JAMP | Jamaica Playground -- Renovate MPPA Q301-121M | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412JAMP | Jamaica Playground -- Renovate MPPA Q301-121M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412JMIC | Jamaica Playground R/C Q301-119M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412JMIC | Jamaica Playground R/C Q301-119M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412JMIC | Jamaica Playground R/C Q301-119M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412JMIC | Jamaica Playground R/C Q301-119M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412JMIC | Jamaica Playground R/C Q301-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2030
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412KLWP | Det. Keith Williams Pk--Reno The Synthetic Turf Q121-121M | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412KLWP | Det. Keith Williams Pk--Reno The Synthetic Turf Q121-121M | 2 | DESIGN | Dec 2020 | Jun 2022 | Dec 2020 | Jun 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412KLWP | Det. Keith Williams Pk--Reno The Synthetic Turf Q121-121M | 3 | BID/ REGISTER CONTRACT | Jun 2022 | Mar 2023 | Jun 2022 | Mar 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412KLWP | Det. Keith Williams Pk--Reno The Synthetic Turf Q121-121M | 4 | CONSTRUCTION | Mar 2023 | Sep 2024 | Mar 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412KLWP | Det. Keith Williams Pk--Reno The Synthetic Turf Q121-121M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Jun 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412MBPF | Montebellier Park Field - Playing Field Upgrades | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412MBPF | Montebellier Park Field - Playing Field Upgrades | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412MBPF | Montebellier Park Field - Playing Field Upgrades | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412MBPF | Montebellier Park Field - Playing Field Upgrades | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412MBPF | Montebellier Park Field - Playing Field Upgrades | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412NAUT | Nautilus Playground R/C Q448-119M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412NAUT | Nautilus Playground R/C Q448-119M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412NAUT | Nautilus Playground R/C Q448-119M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412NAUT | Nautilus Playground R/C Q448-119M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412NAUT | Nautilus Playground R/C Q448-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412NRPG | North Rochdale Park -- renovation | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412NRPG | North Rochdale Park -- renovation | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412NRPG | North Rochdale Park -- renovation | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412NRPG | North Rochdale Park -- renovation | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412NRPG | North Rochdale Park -- renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RCON | RAYMOND O'CONNOR PK PATHWAY & SOCCER RENO | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RCON | RAYMOND O'CONNOR PK PATHWAY & SOCCER RENO | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RCON | RAYMOND O'CONNOR PK PATHWAY & SOCCER RENO | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RCON | RAYMOND O'CONNOR PK PATHWAY & SOCCER RENO | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RCON | RAYMOND O'CONNOR PK PATHWAY & SOCCER RENO | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RKM2 | RUFUS KING MANOR MUSEUM -HVAC Q23-116M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RKM2 | RUFUS KING MANOR MUSEUM -HVAC Q23-116M | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RKM2 | RUFUS KING MANOR MUSEUM -HVAC Q23-116M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2013 | Dec 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RKM2 | RUFUS KING MANOR MUSEUM -HVAC Q23-116M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Dec 2014 | Dec 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RKM2 | RUFUS KING MANOR MUSEUM -HVAC Q23-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Dec 2015 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RKPP | RUFUS KING PARK RENO OF PLGD | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RKPP | RUFUS KING PARK RENO OF PLGD | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RKPP | RUFUS KING PARK RENO OF PLGD | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RKPP | RUFUS KING PARK RENO OF PLGD | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RKPP | RUFUS KING PARK RENO OF PLGD | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RUKM | Rufus King Manor Museum Reconstruction | 1 | DEVELOP SCOPE | Oct 2023 | Mar 2024 | Oct 2023 | Mar 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RUKM | Rufus King Manor Museum Reconstruction | 2 | DESIGN | Mar 2024 | Mar 2026 | Mar 2024 | Mar 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RUKM | Rufus King Manor Museum Reconstruction | 3 | BID/ REGISTER CONTRACT | Mar 2026 | Dec 2026 | Mar 2026 | Dec 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RUKM | Rufus King Manor Museum Reconstruction | 4 | CONSTRUCTION | Dec 2026 | Dec 2028 | Dec 2026 | Dec 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RUKM | Rufus King Manor Museum Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2028 | Dec 2029 | Dec 2028 | Dec 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWFA | Roy Wilkens Rec. Center: Fire Alarm Reconstruction | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWFA | Roy Wilkens Rec. Center: Fire Alarm Reconstruction | 2 | DESIGN | Dec 2019 | Dec 2021 | Dec 2019 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWFA | Roy Wilkens Rec. Center: Fire Alarm Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWFA | Roy Wilkens Rec. Center: Fire Alarm Reconstruction | 4 | CONSTRUCTION | Sep 2022 | Sep 2025 | Sep 2022 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWFA | Roy Wilkens Rec. Center: Fire Alarm Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWIL | ROY WILKINS REC CTR ROOF & SITE Q448-112M | 1 | DEVELOP SCOPE | Jul 2011 | Sep 2011 | Jul 2011 | Sep 2011
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWIL | ROY WILKINS REC CTR ROOF & SITE Q448-112M | 2 | DESIGN | Sep 2011 | Dec 2011 | Sep 2011 | Dec 2011
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWIL | ROY WILKINS REC CTR ROOF & SITE Q448-112M | 3 | BID/ REGISTER CONTRACT | Dec 2011 | Mar 2012 | Dec 2011 | Mar 2012
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWIL | ROY WILKINS REC CTR ROOF & SITE Q448-112M | 4 | CONSTRUCTION | Mar 2012 | Mar 2013 | Mar 2012 | Mar 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWIL | ROY WILKINS REC CTR ROOF & SITE Q448-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2013 | Mar 2014 | Mar 2013 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWP3 | ROY WILKINS PARK RECREATION CTR RC Q448-115M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Jan 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWP3 | ROY WILKINS PARK RECREATION CTR RC Q448-115M | 2 | DESIGN | Sep 2013 | Dec 2013 | Jan 2016 | Jun 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWP3 | ROY WILKINS PARK RECREATION CTR RC Q448-115M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Feb 2019 | Nov 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWP3 | ROY WILKINS PARK RECREATION CTR RC Q448-115M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Sep 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWP3 | ROY WILKINS PARK RECREATION CTR RC Q448-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Sep 2021 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWPK | ROY WILKINS PK. REC CTR - POOL RENOVATION Q448-204M/504M | 2 | DESIGN | Dec 2003 | Mar 2004 | Dec 2003 | Mar 2004
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWPK | ROY WILKINS PK. REC CTR - POOL RENOVATION Q448-204M/504M | 3 | BID/ REGISTER CONTRACT | Sep 2004 | Nov 2004 | Sep 2004 | Nov 2004
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWPK | ROY WILKINS PK. REC CTR - POOL RENOVATION Q448-204M/504M | 4 | CONSTRUCTION | Jan 2005 | Jan 2006 | Jan 2005 | Jan 2006
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWPK | ROY WILKINS PK. REC CTR - POOL RENOVATION Q448-204M/504M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2006 | Jan 2007 | Jan 2006 | Dec 2011
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWR3 | ROY WILKINS REC CENTER | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWR3 | ROY WILKINS REC CENTER | 2 | DESIGN | Dec 2022 | Dec 2024 | Dec 2022 | Dec 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWR3 | ROY WILKINS REC CENTER | 3 | BID/ REGISTER CONTRACT | Dec 2024 | Sep 2025 | Dec 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWR3 | ROY WILKINS REC CENTER | 4 | CONSTRUCTION | Sep 2025 | Sep 2028 | Sep 2025 | Sep 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWR3 | ROY WILKINS REC CENTER | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2028 | Sep 2030 | Sep 2028 | Sep 2030
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412SRPC | SOUTH ROCHDALE PLGD- RENO OF PLGD & CS | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412SRPC | SOUTH ROCHDALE PLGD- RENO OF PLGD & CS | 2 | DESIGN | Dec 2020 | Jun 2022 | Dec 2020 | Jun 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412SRPC | SOUTH ROCHDALE PLGD- RENO OF PLGD & CS | 3 | BID/ REGISTER CONTRACT | Jun 2022 | Mar 2023 | Jun 2022 | Mar 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412SRPC | SOUTH ROCHDALE PLGD- RENO OF PLGD & CS | 4 | CONSTRUCTION | Mar 2023 | Sep 2024 | Mar 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412SRPC | SOUTH ROCHDALE PLGD- RENO OF PLGD & CS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412WATR | DPR Greenthumb Paradise & 2 Discovery Gardens -- Water sourc | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412WATR | DPR Greenthumb Paradise & 2 Discovery Gardens -- Water sourc | 2 | DESIGN | Dec 2022 | Jun 2024 | Dec 2022 | Jun 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412WATR | DPR Greenthumb Paradise & 2 Discovery Gardens -- Water sourc | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412WATR | DPR Greenthumb Paradise & 2 Discovery Gardens -- Water sourc | 4 | CONSTRUCTION | Mar 2025 | Sep 2026 | Mar 2025 | Sep 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412WATR | DPR Greenthumb Paradise & 2 Discovery Gardens -- Water sourc | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Sep 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413010F | QUEENS COUNTY FARM MUSEUM - WINDMILL, ROADWAY Q453-202M | 1 | DEVELOP SCOPE | Jul 2003 | Sep 2003 | Jul 2003 | Sep 2003
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413010F | QUEENS COUNTY FARM MUSEUM - WINDMILL, ROADWAY Q453-202M | 2 | DESIGN | Dec 2002 | Apr 2003 | Dec 2002 | Apr 2003
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413010F | QUEENS COUNTY FARM MUSEUM - WINDMILL, ROADWAY Q453-202M | 3 | BID/ REGISTER CONTRACT | Sep 2003 | Nov 2003 | Sep 2003 | Nov 2003
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413010F | QUEENS COUNTY FARM MUSEUM - WINDMILL, ROADWAY Q453-202M | 4 | CONSTRUCTION | Jan 2004 | Dec 2004 | Jan 2004 | Dec 2004
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413010F | QUEENS COUNTY FARM MUSEUM - WINDMILL, ROADWAY Q453-202M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2005 | Dec 2005 | Jan 2005 | Dec 2005
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BPRC | BROOKVILLE PARK REC CENTER--RECREATION CENTER WITH POOL | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BPRC | BROOKVILLE PARK REC CENTER--RECREATION CENTER WITH POOL | 2 | DESIGN | Feb 2024 | Feb 2026 | Feb 2024 | Feb 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BPRC | BROOKVILLE PARK REC CENTER--RECREATION CENTER WITH POOL | 3 | BID/ REGISTER CONTRACT | Feb 2026 | Nov 2026 | Feb 2026 | Nov 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BPRC | BROOKVILLE PARK REC CENTER--RECREATION CENTER WITH POOL | 4 | CONSTRUCTION | Nov 2026 | Nov 2029 | Nov 2026 | Nov 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BPRC | BROOKVILLE PARK REC CENTER--RECREATION CENTER WITH POOL | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2029 | Nov 2031 | Nov 2029 | Nov 2031
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRKE | Brookville Park Basketball Court Reconstruction | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRKE | Brookville Park Basketball Court Reconstruction | 2 | DESIGN | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRKE | Brookville Park Basketball Court Reconstruction | 3 | BID/ REGISTER CONTRACT | Sep 2024 | Jun 2025 | Sep 2024 | Jun 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRKE | Brookville Park Basketball Court Reconstruction | 4 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRKE | Brookville Park Basketball Court Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Jun 2027 | Jun 2026 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRO4 | Brookville Park Dog Run | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2016 | Dec 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRO4 | Brookville Park Dog Run | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRO4 | Brookville Park Dog Run | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRO4 | Brookville Park Dog Run | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRO4 | Brookville Park Dog Run | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BROK | BROOKVILLE PARK RENO PATHS & BRIDGES | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BROK | BROOKVILLE PARK RENO PATHS & BRIDGES | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BROK | BROOKVILLE PARK RENO PATHS & BRIDGES | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BROK | BROOKVILLE PARK RENO PATHS & BRIDGES | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BROK | BROOKVILLE PARK RENO PATHS & BRIDGES | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRSY | Brookville Park Synthetic Turf Field R/C Q008-119M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRSY | Brookville Park Synthetic Turf Field R/C Q008-119M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRSY | Brookville Park Synthetic Turf Field R/C Q008-119M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRSY | Brookville Park Synthetic Turf Field R/C Q008-119M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRSY | Brookville Park Synthetic Turf Field R/C Q008-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413CAMB | CAMBRIA PLGD RECONSTRUCTION Q339-121M | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413CAMB | CAMBRIA PLGD RECONSTRUCTION Q339-121M | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413CAMB | CAMBRIA PLGD RECONSTRUCTION Q339-121M | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413CAMB | CAMBRIA PLGD RECONSTRUCTION Q339-121M | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413CAMB | CAMBRIA PLGD RECONSTRUCTION Q339-121M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413CAST | Castlewood Playground - Reconstruction of the MPPA Q327-119M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413CAST | Castlewood Playground - Reconstruction of the MPPA Q327-119M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413CAST | Castlewood Playground - Reconstruction of the MPPA Q327-119M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413CAST | Castlewood Playground - Reconstruction of the MPPA Q327-119M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413CAST | Castlewood Playground - Reconstruction of the MPPA Q327-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413COV2 | Sunset Cove Pk Oyster Garden/Boardwalk Cons. Q498-117M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413COV2 | Sunset Cove Pk Oyster Garden/Boardwalk Cons. Q498-117M | 2 | DESIGN | Dec 2016 | Dec 2018 | Dec 2016 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413COV2 | Sunset Cove Pk Oyster Garden/Boardwalk Cons. Q498-117M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413COV2 | Sunset Cove Pk Oyster Garden/Boardwalk Cons. Q498-117M | 4 | CONSTRUCTION | Sep 2019 | Sep 2021 | Sep 2019 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413COV2 | Sunset Cove Pk Oyster Garden/Boardwalk Cons. Q498-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413ESPG | East Springfield Plgd PS 147-Recon of plgd, bball courts | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413ESPG | East Springfield Plgd PS 147-Recon of plgd, bball courts | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413ESPG | East Springfield Plgd PS 147-Recon of plgd, bball courts | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413ESPG | East Springfield Plgd PS 147-Recon of plgd, bball courts | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413ESPG | East Springfield Plgd PS 147-Recon of plgd, bball courts | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413IDL3 | IDLEWILD PK SITE B Q392-219M | 1 | DEVELOP SCOPE | Jul 2011 | Sep 2011 | Jul 2011 | Sep 2011
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413IDL3 | IDLEWILD PK SITE B Q392-219M | 2 | DESIGN | Sep 2011 | Dec 2011 | Sep 2011 | Dec 2011
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413IDL3 | IDLEWILD PK SITE B Q392-219M | 3 | BID/ REGISTER CONTRACT | Dec 2011 | Mar 2012 | Dec 2011 | Mar 2012
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413IDL3 | IDLEWILD PK SITE B Q392-219M | 4 | CONSTRUCTION | Mar 2012 | Mar 2013 | Mar 2012 | Mar 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413IDL3 | IDLEWILD PK SITE B Q392-219M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2013 | Mar 2014 | Mar 2013 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413IDPK | IDLEWILD PK MARSH NATURE CENTER Q392-210M | 1 | DEVELOP SCOPE | Jul 2006 | Sep 2006 | Jul 2008 | Oct 2008
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413IDPK | IDLEWILD PK MARSH NATURE CENTER Q392-210M | 2 | DESIGN | Sep 2006 | Dec 2006 | Jun 2012 | Sep 2012
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413IDPK | IDLEWILD PK MARSH NATURE CENTER Q392-210M | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Sep 2012 | Mar 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413IDPK | IDLEWILD PK MARSH NATURE CENTER Q392-210M | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Apr 2013 | Apr 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413IDPK | IDLEWILD PK MARSH NATURE CENTER Q392-210M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Apr 2012 | Jun 2030
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413JH72 | VIC HANSON/JHS 72 PLGD RC Q352 | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2007 | Sep 2007
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413JH72 | VIC HANSON/JHS 72 PLGD RC Q352 | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413JH72 | VIC HANSON/JHS 72 PLGD RC Q352 | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2013 | Mar 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413JH72 | VIC HANSON/JHS 72 PLGD RC Q352 | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413JH72 | VIC HANSON/JHS 72 PLGD RC Q352 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2015 | Jun 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413LAPC | LAURELTON PLGD- SPORTS COURT RECON | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413LAPC | LAURELTON PLGD- SPORTS COURT RECON | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413LAPC | LAURELTON PLGD- SPORTS COURT RECON | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413LAPC | LAURELTON PLGD- SPORTS COURT RECON | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413LAPC | LAURELTON PLGD- SPORTS COURT RECON | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413LPCT | Laurelton Playground BBall and Handball Courts Q108-120M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413LPCT | Laurelton Playground BBall and Handball Courts Q108-120M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413LPCT | Laurelton Playground BBall and Handball Courts Q108-120M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413LPCT | Laurelton Playground BBall and Handball Courts Q108-120M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413LPCT | Laurelton Playground BBall and Handball Courts Q108-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413QCFM | QNS FMHSE-RENOV ED BLDG,GRNHSE & ADRIANCE FMHSE Q453-102MA | 1 | DEVELOP SCOPE | Jul 2001 | Jul 2001 | Jul 2001 | Jul 2001
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413QCFM | QNS FMHSE-RENOV ED BLDG,GRNHSE & ADRIANCE FMHSE Q453-102MA | 2 | DESIGN | Jul 2001 | Apr 2002 | Jul 2001 | Apr 2002
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413QCFM | QNS FMHSE-RENOV ED BLDG,GRNHSE & ADRIANCE FMHSE Q453-102MA | 3 | BID/ REGISTER CONTRACT | Jun 2002 | Nov 2002 | Jun 2002 | Nov 2002
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413QCFM | QNS FMHSE-RENOV ED BLDG,GRNHSE & ADRIANCE FMHSE Q453-102MA | 4 | CONSTRUCTION | Feb 2003 | Feb 2004 | Feb 2003 | Feb 2004
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413QCFM | QNS FMHSE-RENOV ED BLDG,GRNHSE & ADRIANCE FMHSE Q453-102MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2004 | Feb 2005 | Feb 2004 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413READ | Bellerose Playground (PS 133) Creation of Reading Garden | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413READ | Bellerose Playground (PS 133) Creation of Reading Garden | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413READ | Bellerose Playground (PS 133) Creation of Reading Garden | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413READ | Bellerose Playground (PS 133) Creation of Reading Garden | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413READ | Bellerose Playground (PS 133) Creation of Reading Garden | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413SPBD | Springfield Park Basketball Courts and BBQ Area Q107-119M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413SPBD | Springfield Park Basketball Courts and BBQ Area Q107-119M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413SPBD | Springfield Park Basketball Courts and BBQ Area Q107-119M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413SPBD | Springfield Park Basketball Courts and BBQ Area Q107-119M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413SPBD | Springfield Park Basketball Courts and BBQ Area Q107-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2030
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413WGPF | WILLIAM GUNN PLAYGROUND EXPANSION | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413WGPF | WILLIAM GUNN PLAYGROUND EXPANSION | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413WGPF | WILLIAM GUNN PLAYGROUND EXPANSION | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2013 | Mar 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413WGPF | WILLIAM GUNN PLAYGROUND EXPANSION | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413WGPF | WILLIAM GUNN PLAYGROUND EXPANSION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2015 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-41417PG | BROAD CHANNEL 17TH STREET PLAYGROUND Q460-118M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-41417PG | BROAD CHANNEL 17TH STREET PLAYGROUND Q460-118M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-41417PG | BROAD CHANNEL 17TH STREET PLAYGROUND Q460-118M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-41417PG | BROAD CHANNEL 17TH STREET PLAYGROUND Q460-118M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-41417PG | BROAD CHANNEL 17TH STREET PLAYGROUND Q460-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414ARVR | Arverne Playground Reconstruction | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414ARVR | Arverne Playground Reconstruction | 2 | DESIGN | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414ARVR | Arverne Playground Reconstruction | 3 | BID/ REGISTER CONTRACT | Sep 2024 | Jun 2025 | Sep 2024 | Jun 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414ARVR | Arverne Playground Reconstruction | 4 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414ARVR | Arverne Playground Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Jun 2027 | Jun 2026 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414B9TH | Beach 9th Street Basketball Courts | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414B9TH | Beach 9th Street Basketball Courts | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414B9TH | Beach 9th Street Basketball Courts | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414B9TH | Beach 9th Street Basketball Courts | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414B9TH | Beach 9th Street Basketball Courts | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BAY6 | Michaelis-Bayswater Park Reconstruction Q007-119M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BAY6 | Michaelis-Bayswater Park Reconstruction Q007-119M | 2 | DESIGN | Dec 2017 | Jun 2019 | Dec 2017 | Jun 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BAY6 | Michaelis-Bayswater Park Reconstruction Q007-119M | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Mar 2020 | Jun 2019 | Mar 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BAY6 | Michaelis-Bayswater Park Reconstruction Q007-119M | 4 | CONSTRUCTION | Mar 2020 | Sep 2021 | Mar 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BAY6 | Michaelis-Bayswater Park Reconstruction Q007-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BAY9 | Michaelis-Bayswater Park Reconstruction | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BAY9 | Michaelis-Bayswater Park Reconstruction | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BAY9 | Michaelis-Bayswater Park Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BAY9 | Michaelis-Bayswater Park Reconstruction | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BAY9 | Michaelis-Bayswater Park Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BC32 | BEACH 32ND STR PLGD- SYNTHETIC TURF | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BC32 | BEACH 32ND STR PLGD- SYNTHETIC TURF | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BC32 | BEACH 32ND STR PLGD- SYNTHETIC TURF | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BC32 | BEACH 32ND STR PLGD- SYNTHETIC TURF | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BC32 | BEACH 32ND STR PLGD- SYNTHETIC TURF | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BC88 | Beach 88th Street Park Construction Q499-118M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BC88 | Beach 88th Street Park Construction Q499-118M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BC88 | Beach 88th Street Park Construction Q499-118M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BC88 | Beach 88th Street Park Construction Q499-118M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BC88 | Beach 88th Street Park Construction Q499-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BCAP | Broad Channel American Park Q467-120M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BCAP | Broad Channel American Park Q467-120M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BCAP | Broad Channel American Park Q467-120M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BCAP | Broad Channel American Park Q467-120M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BCAP | Broad Channel American Park Q467-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Jun 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414LABY | Shorefront Labyrinth and Seating Area Q163-518M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Feb 2021 | Aug 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414LABY | Shorefront Labyrinth and Seating Area Q163-518M | 2 | DESIGN | Dec 2017 | Jun 2019 | Aug 2021 | Feb 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414LABY | Shorefront Labyrinth and Seating Area Q163-518M | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Mar 2020 | Feb 2023 | Oct 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414LABY | Shorefront Labyrinth and Seating Area Q163-518M | 4 | CONSTRUCTION | Mar 2020 | Sep 2021 | Oct 2023 | Apr 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414LABY | Shorefront Labyrinth and Seating Area Q163-518M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Apr 2025 | Jun 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414LAN2 | Lannett Playground Sitting Area R/C Q407-118M | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Sep 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414LAN2 | Lannett Playground Sitting Area R/C Q407-118M | 2 | DESIGN | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414LAN2 | Lannett Playground Sitting Area R/C Q407-118M | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2014 | Mar 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414LAN2 | Lannett Playground Sitting Area R/C Q407-118M | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414LAN2 | Lannett Playground Sitting Area R/C Q407-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2016 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414LANN | Cons of PRB & RC of PLGD at PS 197 Q407-109M | 1 | DEVELOP SCOPE | Jul 2008 | Sep 2008 | Jul 2008 | Sep 2008
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414LANN | Cons of PRB & RC of PLGD at PS 197 Q407-109M | 2 | DESIGN | Sep 2008 | Dec 2008 | Sep 2008 | Dec 2008
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414LANN | Cons of PRB & RC of PLGD at PS 197 Q407-109M | 3 | BID/ REGISTER CONTRACT | Dec 2008 | Mar 2009 | Dec 2008 | Mar 2009
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414LANN | Cons of PRB & RC of PLGD at PS 197 Q407-109M | 4 | CONSTRUCTION | Mar 2009 | Mar 2010 | Mar 2009 | Mar 2010
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414LANN | Cons of PRB & RC of PLGD at PS 197 Q407-109M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2010 | Mar 2011 | Mar 2010 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414ODON | O'Donohue Park Picnic Grove Construction | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2015 | Dec 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414ODON | O'Donohue Park Picnic Grove Construction | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2015 | Dec 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414ODON | O'Donohue Park Picnic Grove Construction | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2016 | Sep 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414ODON | O'Donohue Park Picnic Grove Construction | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2017 | Sep 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414ODON | O'Donohue Park Picnic Grove Construction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2018 | Sep 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RB59 | Beach 59th Street Playground R/C Q162E-118M | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jun 2023 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RB59 | Beach 59th Street Playground R/C Q162E-118M | 2 | DESIGN | Sep 2014 | Dec 2014 | Sep 2023 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RB59 | Beach 59th Street Playground R/C Q162E-118M | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2023 | Mar 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RB59 | Beach 59th Street Playground R/C Q162E-118M | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2024 | Mar 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RB59 | Beach 59th Street Playground R/C Q162E-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2025 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RCPR | Rockaway Community Park Reconstruction | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RCPR | Rockaway Community Park Reconstruction | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RCPR | Rockaway Community Park Reconstruction | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RCPR | Rockaway Community Park Reconstruction | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RCPR | Rockaway Community Park Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RKSP | ROCKAWAY BEACH SKATE PARK FACILITY- RC Q163-111MA | 2 | DESIGN | Sep 2010 | Dec 2010 | Sep 2010 | Dec 2010
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RKSP | ROCKAWAY BEACH SKATE PARK FACILITY- RC Q163-111MA | 3 | BID/ REGISTER CONTRACT | Dec 2010 | Mar 2011 | Dec 2010 | Mar 2011
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RKSP | ROCKAWAY BEACH SKATE PARK FACILITY- RC Q163-111MA | 4 | CONSTRUCTION | Mar 2011 | Mar 2012 | Mar 2011 | Mar 2012
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RKSP | ROCKAWAY BEACH SKATE PARK FACILITY- RC Q163-111MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2012 | Mar 2013 | Mar 2012 | Apr 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414SFHR | Shore Front Parkway Repave Roller Hockey Rink | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414SFHR | Shore Front Parkway Repave Roller Hockey Rink | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414SFHR | Shore Front Parkway Repave Roller Hockey Rink | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414SFHR | Shore Front Parkway Repave Roller Hockey Rink | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414SFHR | Shore Front Parkway Repave Roller Hockey Rink | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414THUR | Thursby Basin Park Construction | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414THUR | Thursby Basin Park Construction | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414THUR | Thursby Basin Park Construction | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414THUR | Thursby Basin Park Construction | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414THUR | Thursby Basin Park Construction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415ALOT | AL OERTER REC CENTER GYM--GYM REPLACEMENT | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415ALOT | AL OERTER REC CENTER GYM--GYM REPLACEMENT | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415ALOT | AL OERTER REC CENTER GYM--GYM REPLACEMENT | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415ALOT | AL OERTER REC CENTER GYM--GYM REPLACEMENT | 4 | CONSTRUCTION | Nov 2025 | May 2027 | Nov 2025 | May 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415ALOT | AL OERTER REC CENTER GYM--GYM REPLACEMENT | 5 | PUNCHLIST COMPLETE, JOB CLOSED | May 2027 | May 2028 | May 2027 | May 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415AQFL | Flushing Mead Cor Aquatic Center Pool Floor Recon Q099-322M | 1 | DEVELOP SCOPE | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415AQFL | Flushing Mead Cor Aquatic Center Pool Floor Recon Q099-322M | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415AQFL | Flushing Mead Cor Aquatic Center Pool Floor Recon Q099-322M | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415AQFL | Flushing Mead Cor Aquatic Center Pool Floor Recon Q099-322M | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415AQFL | Flushing Mead Cor Aquatic Center Pool Floor Recon Q099-322M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415AQNT | FMCP Aquatic Center Netting | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415AQNT | FMCP Aquatic Center Netting | 2 | DESIGN | Dec 2019 | Dec 2021 | Dec 2019 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415AQNT | FMCP Aquatic Center Netting | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415AQNT | FMCP Aquatic Center Netting | 4 | CONSTRUCTION | Sep 2022 | Sep 2025 | Sep 2022 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415AQNT | FMCP Aquatic Center Netting | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2027 | Sep 2025 | Aug 2030
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415AQUA | FMCP - Aquatic Center Roof Replacement | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415AQUA | FMCP - Aquatic Center Roof Replacement | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415AQUA | FMCP - Aquatic Center Roof Replacement | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415AQUA | FMCP - Aquatic Center Roof Replacement | 4 | CONSTRUCTION | Sep 2019 | Mar 2021 | Sep 2019 | Mar 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415AQUA | FMCP - Aquatic Center Roof Replacement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Mar 2022 | Mar 2021 | Jun 2030
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415CAND | FMCP - Reconstruction of Candela Structures Q099-120M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415CAND | FMCP - Reconstruction of Candela Structures Q099-120M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415CAND | FMCP - Reconstruction of Candela Structures Q099-120M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415CAND | FMCP - Reconstruction of Candela Structures Q099-120M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415CAND | FMCP - Reconstruction of Candela Structures Q099-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FMCP | FMCP - BOAT HOUSE UPGRADE Q099-207MA/507M & 409M OMBP | 1 | DEVELOP SCOPE | Jul 2006 | Sep 2006 | Oct 2003 | Jan 2004
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FMCP | FMCP - BOAT HOUSE UPGRADE Q099-207MA/507M & 409M OMBP | 2 | DESIGN | Sep 2006 | Dec 2006 | Jan 2004 | Apr 2004
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FMCP | FMCP - BOAT HOUSE UPGRADE Q099-207MA/507M & 409M OMBP | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Apr 2004 | Jul 2004
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FMCP | FMCP - BOAT HOUSE UPGRADE Q099-207MA/507M & 409M OMBP | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Jul 2004 | Jul 2005
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FMCP | FMCP - BOAT HOUSE UPGRADE Q099-207MA/507M & 409M OMBP | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Jul 2005 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FMWS | FMCP - Adult Fitness Equipment Installation Q099-318M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2007 | Sep 2007
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FMWS | FMCP - Adult Fitness Equipment Installation Q099-318M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FMWS | FMCP - Adult Fitness Equipment Installation Q099-318M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FMWS | FMCP - Adult Fitness Equipment Installation Q099-318M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FMWS | FMCP - Adult Fitness Equipment Installation Q099-318M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FSTF | FMCP - Synthetic Turf Fields 8 & 9 R/C Q099-319M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FSTF | FMCP - Synthetic Turf Fields 8 & 9 R/C Q099-319M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FSTF | FMCP - Synthetic Turf Fields 8 & 9 R/C Q099-319M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FSTF | FMCP - Synthetic Turf Fields 8 & 9 R/C Q099-319M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FSTF | FMCP - Synthetic Turf Fields 8 & 9 R/C Q099-319M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415LWCS | FMCP - Lawrence Playground Pulic Rest Room R/C Q099-817MA | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415LWCS | FMCP - Lawrence Playground Pulic Rest Room R/C Q099-817MA | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415LWCS | FMCP - Lawrence Playground Pulic Rest Room R/C Q099-817MA | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415LWCS | FMCP - Lawrence Playground Pulic Rest Room R/C Q099-817MA | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415LWCS | FMCP - Lawrence Playground Pulic Rest Room R/C Q099-817MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2033
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415MEA2 | FMCP - MEADOW LAKE- PATHS Q099-215M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415MEA2 | FMCP - MEADOW LAKE- PATHS Q099-215M | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415MEA2 | FMCP - MEADOW LAKE- PATHS Q099-215M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2013 | Mar 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415MEA2 | FMCP - MEADOW LAKE- PATHS Q099-215M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415MEA2 | FMCP - MEADOW LAKE- PATHS Q099-215M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2015 | Jun 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415PAS4 | FMCP-Passerelle Roof | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415PAS4 | FMCP-Passerelle Roof | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415PAS4 | FMCP-Passerelle Roof | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415PAS4 | FMCP-Passerelle Roof | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415PAS4 | FMCP-Passerelle Roof | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2032
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415PAVI | FMCP - NYS PAVILION RC Q099-116M | 1 | DEVELOP SCOPE | Jul 2007 | Sep 2007 | Jul 2014 | Sep 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415PAVI | FMCP - NYS PAVILION RC Q099-116M | 2 | DESIGN | Sep 2007 | Dec 2007 | Sep 2015 | Jun 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415PAVI | FMCP - NYS PAVILION RC Q099-116M | 3 | BID/ REGISTER CONTRACT | Dec 2007 | Mar 2008 | Jul 2017 | Jul 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415PAVI | FMCP - NYS PAVILION RC Q099-116M | 4 | CONSTRUCTION | Mar 2008 | Mar 2009 | Oct 2019 | Feb 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415PAVI | FMCP - NYS PAVILION RC Q099-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2009 | Mar 2010 | Mar 2022 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415WRD2 | FMCP - World's Fair Marina Pier 1 & 3 R/C Q099-218M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415WRD2 | FMCP - World's Fair Marina Pier 1 & 3 R/C Q099-218M | 2 | DESIGN | Dec 2017 | Dec 2019 | Dec 2017 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415WRD2 | FMCP - World's Fair Marina Pier 1 & 3 R/C Q099-218M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415WRD2 | FMCP - World's Fair Marina Pier 1 & 3 R/C Q099-218M | 4 | CONSTRUCTION | Sep 2020 | Sep 2023 | Sep 2020 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415WRD2 | FMCP - World's Fair Marina Pier 1 & 3 R/C Q099-218M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2025 | Sep 2023 | Jun 2031
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ALHVAC | Al Oerter Recreation Center HVAC Reconstruction | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ALHVAC | Al Oerter Recreation Center HVAC Reconstruction | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ALHVAC | Al Oerter Recreation Center HVAC Reconstruction | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ALHVAC | Al Oerter Recreation Center HVAC Reconstruction | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ALHVAC | Al Oerter Recreation Center HVAC Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ALYPND | Alley Pond Park adventure course path reconstruction | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2007 | Sep 2007
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ALYPND | Alley Pond Park adventure course path reconstruction | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ALYPND | Alley Pond Park adventure course path reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ALYPND | Alley Pond Park adventure course path reconstruction | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ALYPND | Alley Pond Park adventure course path reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH01 | Anchor Park Site - Astoria Park (DESIGN ONLY - ALL PHASES) | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH01 | Anchor Park Site - Astoria Park (DESIGN ONLY - ALL PHASES) | 2 | DESIGN | Dec 2016 | Dec 2018 | Dec 2016 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH01 | Anchor Park Site - Astoria Park (DESIGN ONLY - ALL PHASES) | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2017 | Sep 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH01 | Anchor Park Site - Astoria Park (DESIGN ONLY - ALL PHASES) | 4 | CONSTRUCTION | Sep 2019 | Sep 2021 | Sep 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH01 | Anchor Park Site - Astoria Park (DESIGN ONLY - ALL PHASES) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2019 | Jun 2030
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH04 | Anchor Pk - Astoria Pk PH2B: Charybdis Plgd PRBR/C Q004-418M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH04 | Anchor Pk - Astoria Pk PH2B: Charybdis Plgd PRBR/C Q004-418M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH04 | Anchor Pk - Astoria Pk PH2B: Charybdis Plgd PRBR/C Q004-418M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH04 | Anchor Pk - Astoria Pk PH2B: Charybdis Plgd PRBR/C Q004-418M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH04 | Anchor Pk - Astoria Pk PH2B: Charybdis Plgd PRBR/C Q004-418M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2022 | Aug 2030
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH05 | Anchor Park - Astoria Park Phase 3 | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH05 | Anchor Park - Astoria Park Phase 3 | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH05 | Anchor Park - Astoria Park Phase 3 | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH05 | Anchor Park - Astoria Park Phase 3 | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH05 | Anchor Park - Astoria Park Phase 3 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BASDCS | Bayside Playground-Reconstruction of PRB | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BASDCS | Bayside Playground-Reconstruction of PRB | 2 | DESIGN | Dec 2017 | Dec 2019 | Dec 2017 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BASDCS | Bayside Playground-Reconstruction of PRB | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BASDCS | Bayside Playground-Reconstruction of PRB | 4 | CONSTRUCTION | Sep 2020 | Sep 2022 | Sep 2020 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BASDCS | Bayside Playground-Reconstruction of PRB | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BAYMAR | Bayside Marina RC | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BAYMAR | Bayside Marina RC | 2 | DESIGN | Dec 2018 | Dec 2020 | Dec 2018 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BAYMAR | Bayside Marina RC | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BAYMAR | Bayside Marina RC | 4 | CONSTRUCTION | Sep 2021 | Sep 2023 | Sep 2021 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BAYMAR | Bayside Marina RC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BC94S1 | Beach 94th Street Performance Space Cons. Q163-418M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2023 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BC94S1 | Beach 94th Street Performance Space Cons. Q163-418M | 2 | DESIGN | Dec 2017 | Jun 2019 | Dec 2023 | Dec 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BC94S1 | Beach 94th Street Performance Space Cons. Q163-418M | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Mar 2020 | Dec 2025 | Sep 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BC94S1 | Beach 94th Street Performance Space Cons. Q163-418M | 4 | CONSTRUCTION | Mar 2020 | Sep 2021 | Sep 2026 | Sep 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BC94S1 | Beach 94th Street Performance Space Cons. Q163-418M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2028 | Dec 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BC94S1 | Beach 94th Street Performance Space Cons. Q163-418M | 6 | DEVELOP SCOPE | Sep 2022 | Mar 2023 | Sep 2028 | Dec 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BC94S1 | Beach 94th Street Performance Space Cons. Q163-418M | 7 | DESIGN | Mar 2023 | Mar 2025 | Sep 2028 | Dec 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BC94S1 | Beach 94th Street Performance Space Cons. Q163-418M | 8 | BID/ REGISTER CONTRACT | Mar 2025 | Nov 2025 | Sep 2028 | Dec 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BC94S1 | Beach 94th Street Performance Space Cons. Q163-418M | 9 | CONSTRUCTION | Dec 2025 | Nov 2027 | Sep 2028 | Dec 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BC94S1 | Beach 94th Street Performance Space Cons. Q163-418M | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2027 | Nov 2028 | Sep 2028 | Dec 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BCSGC2 | QUEENS - ELEC OFFICIALS BLDG REQ - GC QG-108MA | 1 | DEVELOP SCOPE | Jul 2008 | Sep 2008 | Jul 2008 | Sep 2008
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BCSGC2 | QUEENS - ELEC OFFICIALS BLDG REQ - GC QG-108MA | 2 | DESIGN | Sep 2008 | Dec 2008 | Sep 2008 | Dec 2008
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BCSGC2 | QUEENS - ELEC OFFICIALS BLDG REQ - GC QG-108MA | 3 | BID/ REGISTER CONTRACT | Dec 2008 | Mar 2009 | Dec 2008 | Mar 2009
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BCSGC2 | QUEENS - ELEC OFFICIALS BLDG REQ - GC QG-108MA | 4 | CONSTRUCTION | Mar 2009 | Mar 2010 | Mar 2009 | Mar 2010
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BCSGC2 | QUEENS - ELEC OFFICIALS BLDG REQ - GC QG-108MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2010 | Mar 2011 | Mar 2010 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BCSHV2 | QUEENS - ELEC OFFICIALS BLDG REQ - HVAC QG-408MA OMBP | 1 | DEVELOP SCOPE | Jul 2010 | Sep 2010 | Jul 2010 | Sep 2010
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BCSHV2 | QUEENS - ELEC OFFICIALS BLDG REQ - HVAC QG-408MA OMBP | 2 | DESIGN | Sep 2010 | Dec 2010 | Sep 2010 | Dec 2010
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BCSHV2 | QUEENS - ELEC OFFICIALS BLDG REQ - HVAC QG-408MA OMBP | 3 | BID/ REGISTER CONTRACT | Dec 2010 | Mar 2011 | Dec 2010 | Mar 2011
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BCSHV2 | QUEENS - ELEC OFFICIALS BLDG REQ - HVAC QG-408MA OMBP | 4 | CONSTRUCTION | Mar 2011 | Mar 2012 | Mar 2011 | Mar 2012
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BCSHV2 | QUEENS - ELEC OFFICIALS BLDG REQ - HVAC QG-408MA OMBP | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2012 | Mar 2013 | Mar 2012 | Mar 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BCSPL2 | QUEENS - ELEC OFFICIALS BLDG REQ - PLMB QG-308M | 1 | DEVELOP SCOPE | Jul 2008 | Sep 2008 | Jul 2008 | Sep 2008
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BCSPL2 | QUEENS - ELEC OFFICIALS BLDG REQ - PLMB QG-308M | 2 | DESIGN | Sep 2008 | Dec 2008 | Sep 2008 | Dec 2008
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BCSPL2 | QUEENS - ELEC OFFICIALS BLDG REQ - PLMB QG-308M | 3 | BID/ REGISTER CONTRACT | Dec 2008 | Mar 2009 | Dec 2008 | Mar 2009
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BCSPL2 | QUEENS - ELEC OFFICIALS BLDG REQ - PLMB QG-308M | 4 | CONSTRUCTION | Mar 2009 | Mar 2010 | Mar 2009 | Mar 2010
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BCSPL2 | QUEENS - ELEC OFFICIALS BLDG REQ - PLMB QG-308M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2010 | Mar 2011 | Mar 2010 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BIGSTF | Big Bush Park Turf - Queens | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BIGSTF | Big Bush Park Turf - Queens | 2 | DESIGN | Dec 2022 | Jun 2024 | Dec 2022 | Jun 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BIGSTF | Big Bush Park Turf - Queens | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BIGSTF | Big Bush Park Turf - Queens | 4 | CONSTRUCTION | Mar 2025 | Sep 2026 | Mar 2025 | Sep 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BIGSTF | Big Bush Park Turf - Queens | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Jun 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BLISSV | BLISSVILLE VET MEMORIAL FLAGPOLE & UPGRADES | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BLISSV | BLISSVILLE VET MEMORIAL FLAGPOLE & UPGRADES | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BLISSV | BLISSVILLE VET MEMORIAL FLAGPOLE & UPGRADES | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BLISSV | BLISSVILLE VET MEMORIAL FLAGPOLE & UPGRADES | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BLISSV | BLISSVILLE VET MEMORIAL FLAGPOLE & UPGRADES | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BLSPTH | Black Spectrum Theatre -Interior renovations q448-219m | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2007 | Sep 2007
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BLSPTH | Black Spectrum Theatre -Interior renovations q448-219m | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BLSPTH | Black Spectrum Theatre -Interior renovations q448-219m | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BLSPTH | Black Spectrum Theatre -Interior renovations q448-219m | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BLSPTH | Black Spectrum Theatre -Interior renovations q448-219m | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BRKVBB | BROOKVILLE PARK TWO BASEBALL FIELD Q008-121M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BRKVBB | BROOKVILLE PARK TWO BASEBALL FIELD Q008-121M | 2 | DESIGN | Dec 2019 | Dec 2021 | Dec 2019 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BRKVBB | BROOKVILLE PARK TWO BASEBALL FIELD Q008-121M | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BRKVBB | BROOKVILLE PARK TWO BASEBALL FIELD Q008-121M | 4 | CONSTRUCTION | Sep 2022 | Sep 2024 | Sep 2022 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BRKVBB | BROOKVILLE PARK TWO BASEBALL FIELD Q008-121M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BRODCH | Broad Channel American Park Shad Creek Road Reconstruction | 1 | DEVELOP SCOPE | Jun 2023 | Dec 2023 | Jun 2023 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BRODCH | Broad Channel American Park Shad Creek Road Reconstruction | 2 | DESIGN | Dec 2023 | Dec 2024 | Dec 2023 | Dec 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BRODCH | Broad Channel American Park Shad Creek Road Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2024 | Sep 2025 | Dec 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BRODCH | Broad Channel American Park Shad Creek Road Reconstruction | 4 | CONSTRUCTION | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BRODCH | Broad Channel American Park Shad Creek Road Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Sep 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BSHIST | Ft. Totten Bayside Historical Society Officers ClubQ458-116M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Nov 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BSHIST | Ft. Totten Bayside Historical Society Officers ClubQ458-116M | 2 | DESIGN | Sep 2013 | Dec 2013 | Nov 2015 | Jul 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BSHIST | Ft. Totten Bayside Historical Society Officers ClubQ458-116M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Mar 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BSHIST | Ft. Totten Bayside Historical Society Officers ClubQ458-116M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2018 | Mar 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BSHIST | Ft. Totten Bayside Historical Society Officers ClubQ458-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2019 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEF | QUEENS - MULTI SITE QG-210M | 1 | DEVELOP SCOPE | Jul 2010 | Sep 2010 | Jul 2007 | Sep 2007
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEF | QUEENS - MULTI SITE QG-210M | 2 | DESIGN | Sep 2010 | Dec 2010 | Sep 2010 | Dec 2010
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEF | QUEENS - MULTI SITE QG-210M | 3 | BID/ REGISTER CONTRACT | Dec 2010 | Mar 2011 | Dec 2010 | Mar 2011
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEF | QUEENS - MULTI SITE QG-210M | 4 | CONSTRUCTION | Mar 2011 | Mar 2012 | Mar 2011 | Mar 2012
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEF | QUEENS - MULTI SITE QG-210M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2012 | Mar 2013 | Mar 2012 | Jun 2033
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEN | QUEENS - COUNCIL & BP MULTI SITE QG-1316M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEN | QUEENS - COUNCIL & BP MULTI SITE QG-1316M | 2 | DESIGN | Dec 2016 | Mar 2018 | Dec 2016 | Mar 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEN | QUEENS - COUNCIL & BP MULTI SITE QG-1316M | 3 | BID/ REGISTER CONTRACT | Mar 2018 | Dec 2018 | Mar 2018 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEN | QUEENS - COUNCIL & BP MULTI SITE QG-1316M | 4 | CONSTRUCTION | Dec 2018 | Dec 2020 | Dec 2018 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEN | QUEENS - COUNCIL & BP MULTI SITE QG-1316M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2020 | Dec 2021 | Dec 2020 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEP | QUEENS - COUNCIL MULTI SITE QG-217M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEP | QUEENS - COUNCIL MULTI SITE QG-217M | 2 | DESIGN | Dec 2016 | Dec 2018 | Dec 2016 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEP | QUEENS - COUNCIL MULTI SITE QG-217M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2017 | Sep 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEP | QUEENS - COUNCIL MULTI SITE QG-217M | 4 | CONSTRUCTION | Sep 2019 | Sep 2021 | Sep 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEP | QUEENS - COUNCIL MULTI SITE QG-217M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2019 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDER | QUEENS - COUNCIL MULTISITE QG-618M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDER | QUEENS - COUNCIL MULTISITE QG-618M | 2 | DESIGN | Dec 2017 | Jun 2019 | Dec 2017 | Jun 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDER | QUEENS - COUNCIL MULTISITE QG-618M | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Mar 2020 | Jun 2019 | Mar 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDER | QUEENS - COUNCIL MULTISITE QG-618M | 4 | CONSTRUCTION | Mar 2020 | Sep 2021 | Mar 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDER | QUEENS - COUNCIL MULTISITE QG-618M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CAPTGP | CAPT. TILLY PK RESTORE GOOSE POND | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CAPTGP | CAPT. TILLY PK RESTORE GOOSE POND | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CAPTGP | CAPT. TILLY PK RESTORE GOOSE POND | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CAPTGP | CAPT. TILLY PK RESTORE GOOSE POND | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CAPTGP | CAPT. TILLY PK RESTORE GOOSE POND | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Jun 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CLILLO | CARLOS LILLO TRIANGLE Q491-107M | 1 | DEVELOP SCOPE | Jul 2006 | Sep 2006 | Jul 2006 | Sep 2006
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CLILLO | CARLOS LILLO TRIANGLE Q491-107M | 2 | DESIGN | Sep 2006 | Dec 2006 | Sep 2006 | Dec 2006
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CLILLO | CARLOS LILLO TRIANGLE Q491-107M | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Dec 2006 | Mar 2007
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CLILLO | CARLOS LILLO TRIANGLE Q491-107M | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Mar 2007 | Mar 2008
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CLILLO | CARLOS LILLO TRIANGLE Q491-107M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Mar 2008 | Dec 2011
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4COLLEG | COLLEGE PT PK-soccer & baseball fields Q476-106M/107MA-OMBP | 1 | DEVELOP SCOPE | Jul 2006 | Sep 2006 | Jul 2006 | Sep 2006
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4COLLEG | COLLEGE PT PK-soccer & baseball fields Q476-106M/107MA-OMBP | 2 | DESIGN | Sep 2006 | Dec 2006 | Sep 2006 | Dec 2006
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4COLLEG | COLLEGE PT PK-soccer & baseball fields Q476-106M/107MA-OMBP | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Dec 2006 | Mar 2007
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4COLLEG | COLLEGE PT PK-soccer & baseball fields Q476-106M/107MA-OMBP | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Mar 2007 | Mar 2008
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4COLLEG | COLLEGE PT PK-soccer & baseball fields Q476-106M/107MA-OMBP | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Mar 2008 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIBN5 | CPI PH1- RC- Astoria Heights & Bowne Plgd PRB QG-1015M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIBN5 | CPI PH1- RC- Astoria Heights & Bowne Plgd PRB QG-1015M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIBN5 | CPI PH1- RC- Astoria Heights & Bowne Plgd PRB QG-1015M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIBN5 | CPI PH1- RC- Astoria Heights & Bowne Plgd PRB QG-1015M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIBN5 | CPI PH1- RC- Astoria Heights & Bowne Plgd PRB QG-1015M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPICOL | CPI - Colden Playground Reconstruction | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPICOL | CPI - Colden Playground Reconstruction | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPICOL | CPI - Colden Playground Reconstruction | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPICOL | CPI - Colden Playground Reconstruction | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPICOL | CPI - Colden Playground Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Jun 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIHCS | CPI - Hoffman Public Restroom | 1 | DEVELOP SCOPE | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIHCS | CPI - Hoffman Public Restroom | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIHCS | CPI - Hoffman Public Restroom | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIHCS | CPI - Hoffman Public Restroom | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIHCS | CPI - Hoffman Public Restroom | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIHPP | Hallets Point Playground Reconstruction | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIHPP | Hallets Point Playground Reconstruction | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIHPP | Hallets Point Playground Reconstruction | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIHPP | Hallets Point Playground Reconstruction | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIHPP | Hallets Point Playground Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Jun 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIP35 | CPI PH2 - Playground Thirty Five XXXV R/C Q296-116M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIP35 | CPI PH2 - Playground Thirty Five XXXV R/C Q296-116M | 2 | DESIGN | Dec 2016 | Mar 2018 | Dec 2016 | Mar 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIP35 | CPI PH2 - Playground Thirty Five XXXV R/C Q296-116M | 3 | BID/ REGISTER CONTRACT | Mar 2018 | Dec 2018 | Mar 2018 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIP35 | CPI PH2 - Playground Thirty Five XXXV R/C Q296-116M | 4 | CONSTRUCTION | Dec 2018 | Dec 2020 | Dec 2018 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIP35 | CPI PH2 - Playground Thirty Five XXXV R/C Q296-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2020 | Dec 2021 | Dec 2020 | Jun 2030
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPPLGD | Cunningham Park Upper Playground R/C Q021-120M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPPLGD | Cunningham Park Upper Playground R/C Q021-120M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPPLGD | Cunningham Park Upper Playground R/C Q021-120M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPPLGD | Cunningham Park Upper Playground R/C Q021-120M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPPLGD | Cunningham Park Upper Playground R/C Q021-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPSLIT | College Point Sports Park - New Lighting | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Sep 2002 | Dec 2002
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPSLIT | College Point Sports Park - New Lighting | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPSLIT | College Point Sports Park - New Lighting | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPSLIT | College Point Sports Park - New Lighting | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPSLIT | College Point Sports Park - New Lighting | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPTLCS | Captain Tilly Park PRB | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPTLCS | Captain Tilly Park PRB | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPTLCS | Captain Tilly Park PRB | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPTLCS | Captain Tilly Park PRB | 4 | CONSTRUCTION | Sep 2020 | Mar 2022 | Sep 2020 | Mar 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPTLCS | Captain Tilly Park PRB | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Mar 2023 | Mar 2022 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CROCHP | Crocheron Park Path Reconstruction | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CROCHP | Crocheron Park Path Reconstruction | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CROCHP | Crocheron Park Path Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CROCHP | Crocheron Park Path Reconstruction | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CROCHP | Crocheron Park Path Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CUN210 | CUNNINGHAM PARK 210 ST PLAYGROUND UPGRADE Q021-220M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CUN210 | CUNNINGHAM PARK 210 ST PLAYGROUND UPGRADE Q021-220M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CUN210 | CUNNINGHAM PARK 210 ST PLAYGROUND UPGRADE Q021-220M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CUN210 | CUNNINGHAM PARK 210 ST PLAYGROUND UPGRADE Q021-220M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CUN210 | CUNNINGHAM PARK 210 ST PLAYGROUND UPGRADE Q021-220M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CUNHCP | CUNNINGHAM PARK - HOLY COW PLAYGROUND: INSTALL PICKLEBALL C | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CUNHCP | CUNNINGHAM PARK - HOLY COW PLAYGROUND: INSTALL PICKLEBALL C | 2 | DESIGN | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CUNHCP | CUNNINGHAM PARK - HOLY COW PLAYGROUND: INSTALL PICKLEBALL C | 3 | BID/ REGISTER CONTRACT | Sep 2024 | Jun 2025 | Sep 2024 | Jun 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CUNHCP | CUNNINGHAM PARK - HOLY COW PLAYGROUND: INSTALL PICKLEBALL C | 4 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CUNHCP | CUNNINGHAM PARK - HOLY COW PLAYGROUND: INSTALL PICKLEBALL C | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Jun 2027 | Jun 2026 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DCTALP | Alley Pond Park, Queens | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DCTALP | Alley Pond Park, Queens | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DCTALP | Alley Pond Park, Queens | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DCTALP | Alley Pond Park, Queens | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DCTALP | Alley Pond Park, Queens | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DELGRP | DELPHIN H. GREENE PLAYGROUND RENOVATION | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DELGRP | DELPHIN H. GREENE PLAYGROUND RENOVATION | 2 | DESIGN | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DELGRP | DELPHIN H. GREENE PLAYGROUND RENOVATION | 3 | BID/ REGISTER CONTRACT | Sep 2024 | Jun 2025 | Sep 2024 | Jun 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DELGRP | DELPHIN H. GREENE PLAYGROUND RENOVATION | 4 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DELGRP | DELPHIN H. GREENE PLAYGROUND RENOVATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Jun 2027 | Jun 2026 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DSTG02 | MEADOW LAKE CREEK OVERLOOK - DESTINATION GREENWAYS | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DSTG02 | MEADOW LAKE CREEK OVERLOOK - DESTINATION GREENWAYS | 2 | DESIGN | Dec 2022 | Jun 2024 | Dec 2022 | Jun 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DSTG02 | MEADOW LAKE CREEK OVERLOOK - DESTINATION GREENWAYS | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DSTG02 | MEADOW LAKE CREEK OVERLOOK - DESTINATION GREENWAYS | 4 | CONSTRUCTION | Mar 2025 | Sep 2026 | Mar 2025 | Sep 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DSTG02 | MEADOW LAKE CREEK OVERLOOK - DESTINATION GREENWAYS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Sep 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DSTG5A | KISSENA PARK PATHS - DESTINATION GREENWAYS | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DSTG5A | KISSENA PARK PATHS - DESTINATION GREENWAYS | 2 | DESIGN | Dec 2022 | Jun 2024 | Dec 2022 | Jun 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DSTG5A | KISSENA PARK PATHS - DESTINATION GREENWAYS | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DSTG5A | KISSENA PARK PATHS - DESTINATION GREENWAYS | 4 | CONSTRUCTION | Mar 2025 | Sep 2026 | Mar 2025 | Sep 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DSTG5A | KISSENA PARK PATHS - DESTINATION GREENWAYS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Sep 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DUTCH1 | Dutch Kills PRB Q218-216M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DUTCH1 | Dutch Kills PRB Q218-216M | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DUTCH1 | Dutch Kills PRB Q218-216M | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DUTCH1 | Dutch Kills PRB Q218-216M | 4 | CONSTRUCTION | Sep 2018 | Mar 2020 | Sep 2018 | Mar 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DUTCH1 | Dutch Kills PRB Q218-216M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Mar 2021 | Mar 2020 | Jun 2030
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4EABTRC | Emerald Ash Borer (EAB) Tree Remove Queens QG-819M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4EABTRC | Emerald Ash Borer (EAB) Tree Remove Queens QG-819M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4EABTRC | Emerald Ash Borer (EAB) Tree Remove Queens QG-819M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4EABTRC | Emerald Ash Borer (EAB) Tree Remove Queens QG-819M | 4 | CONSTRUCTION | Sep 2020 | Sep 2022 | Sep 2020 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4EABTRC | Emerald Ash Borer (EAB) Tree Remove Queens QG-819M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2030
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ELMPRK | HELEN MARSHALL PLGD TURF FIELD Q373-121M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jun 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ELMPRK | HELEN MARSHALL PLGD TURF FIELD Q373-121M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2017 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ELMPRK | HELEN MARSHALL PLGD TURF FIELD Q373-121M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ELMPRK | HELEN MARSHALL PLGD TURF FIELD Q373-121M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ELMPRK | HELEN MARSHALL PLGD TURF FIELD Q373-121M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2020 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FITZPG | FITZGERALD PLAYGROUND | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FITZPG | FITZGERALD PLAYGROUND | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2022 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FITZPG | FITZGERALD PLAYGROUND | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FITZPG | FITZGERALD PLAYGROUND | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FITZPG | FITZGERALD PLAYGROUND | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2025 | Sep 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FLBAY2 | FLUSHING BAY DREDGING & CONSTR OF BOAT RAMP Q099-300M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FLBAY2 | FLUSHING BAY DREDGING & CONSTR OF BOAT RAMP Q099-300M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FLBAY2 | FLUSHING BAY DREDGING & CONSTR OF BOAT RAMP Q099-300M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FLBAY2 | FLUSHING BAY DREDGING & CONSTR OF BOAT RAMP Q099-300M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FLBAY2 | FLUSHING BAY DREDGING & CONSTR OF BOAT RAMP Q099-300M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2030
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMCPIC | Recon ice plant at FMCP, Queens Q099-420M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2021 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMCPIC | Recon ice plant at FMCP, Queens Q099-420M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2021 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMCPIC | Recon ice plant at FMCP, Queens Q099-420M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMCPIC | Recon ice plant at FMCP, Queens Q099-420M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMCPIC | Recon ice plant at FMCP, Queens Q099-420M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2024 | Sep 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMDOOR | Flushing Meadows Corona Park Aquatic Center Exterior Doors R | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMDOOR | Flushing Meadows Corona Park Aquatic Center Exterior Doors R | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMDOOR | Flushing Meadows Corona Park Aquatic Center Exterior Doors R | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMDOOR | Flushing Meadows Corona Park Aquatic Center Exterior Doors R | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMDOOR | Flushing Meadows Corona Park Aquatic Center Exterior Doors R | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMGARG | Flushing Meadows Corona Park Garage Q099-217MA | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2011 | Jun 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMGARG | Flushing Meadows Corona Park Garage Q099-217MA | 2 | DESIGN | Sep 2015 | Dec 2015 | Jul 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMGARG | Flushing Meadows Corona Park Garage Q099-217MA | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Sep 2025 | Jun 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMGARG | Flushing Meadows Corona Park Garage Q099-217MA | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Jun 2026 | Jun 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMGARG | Flushing Meadows Corona Park Garage Q099-217MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Jun 2027 | Dec 2032
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FRDJPU | FREDERICK JUDGE PLAYGROUND UPGRADES Q119-120M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FRDJPU | FREDERICK JUDGE PLAYGROUND UPGRADES Q119-120M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FRDJPU | FREDERICK JUDGE PLAYGROUND UPGRADES Q119-120M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FRDJPU | FREDERICK JUDGE PLAYGROUND UPGRADES Q119-120M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FRDJPU | FREDERICK JUDGE PLAYGROUND UPGRADES Q119-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FRNOCP | CPI-FRANK D. O'CONNOR PLAYGROUND: PLAYGROUND RENOVATION | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FRNOCP | CPI-FRANK D. O'CONNOR PLAYGROUND: PLAYGROUND RENOVATION | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FRNOCP | CPI-FRANK D. O'CONNOR PLAYGROUND: PLAYGROUND RENOVATION | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FRNOCP | CPI-FRANK D. O'CONNOR PLAYGROUND: PLAYGROUND RENOVATION | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FRNOCP | CPI-FRANK D. O'CONNOR PLAYGROUND: PLAYGROUND RENOVATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FTTOTB | FT. TOTTEN PK CHAPEL & COMMANDER'S HOUSE Q458-112M | 1 | DEVELOP SCOPE | Jul 2011 | Sep 2011 | Jul 2011 | Aug 2011
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FTTOTB | FT. TOTTEN PK CHAPEL & COMMANDER'S HOUSE Q458-112M | 2 | DESIGN | Sep 2011 | Dec 2011 | Aug 2011 | Sep 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FTTOTB | FT. TOTTEN PK CHAPEL & COMMANDER'S HOUSE Q458-112M | 3 | BID/ REGISTER CONTRACT | Dec 2011 | Mar 2012 | Feb 2016 | Jun 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FTTOTB | FT. TOTTEN PK CHAPEL & COMMANDER'S HOUSE Q458-112M | 4 | CONSTRUCTION | Mar 2012 | Mar 2013 | Sep 2017 | Mar 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FTTOTB | FT. TOTTEN PK CHAPEL & COMMANDER'S HOUSE Q458-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2013 | Mar 2014 | Mar 2021 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FTTOTC | FT. TOTTEN ELEVATORS Q458 | 1 | DEVELOP SCOPE | Aug 2016 | Jan 2017 | Aug 2016 | Jan 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FTTOTC | FT. TOTTEN ELEVATORS Q458 | 2 | DESIGN | Jan 2017 | Jan 2018 | Jan 2017 | Jan 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FTTOTC | FT. TOTTEN ELEVATORS Q458 | 3 | BID/ REGISTER CONTRACT | Jan 2018 | Oct 2018 | Jan 2018 | Oct 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FTTOTC | FT. TOTTEN ELEVATORS Q458 | 4 | CONSTRUCTION | Oct 2018 | Oct 2019 | Oct 2018 | Oct 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FTTOTC | FT. TOTTEN ELEVATORS Q458 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2019 | Oct 2020 | Oct 2019 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FTTOTP | FT. TOTTEN PK PORCHES | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FTTOTP | FT. TOTTEN PK PORCHES | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FTTOTP | FT. TOTTEN PK PORCHES | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FTTOTP | FT. TOTTEN PK PORCHES | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FTTOTP | FT. TOTTEN PK PORCHES | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GBLPLG | SEVEN GABLES PLAYGROUND | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GBLPLG | SEVEN GABLES PLAYGROUND | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GBLPLG | SEVEN GABLES PLAYGROUND | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GBLPLG | SEVEN GABLES PLAYGROUND | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GBLPLG | SEVEN GABLES PLAYGROUND | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GLNOAK | Tenney Pk (Glen Oaks) Bball Ct./Play Equip. R/C Q310-118M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GLNOAK | Tenney Pk (Glen Oaks) Bball Ct./Play Equip. R/C Q310-118M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GLNOAK | Tenney Pk (Glen Oaks) Bball Ct./Play Equip. R/C Q310-118M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GLNOAK | Tenney Pk (Glen Oaks) Bball Ct./Play Equip. R/C Q310-118M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GLNOAK | Tenney Pk (Glen Oaks) Bball Ct./Play Equip. R/C Q310-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GRST21 | Greenstreets - Queens | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GRST21 | Greenstreets - Queens | 2 | DESIGN | Dec 2020 | Jun 2022 | Dec 2020 | Jun 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GRST21 | Greenstreets - Queens | 3 | BID/ REGISTER CONTRACT | Jun 2022 | Mar 2023 | Jun 2022 | Mar 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GRST21 | Greenstreets - Queens | 4 | CONSTRUCTION | Mar 2023 | Mar 2025 | Mar 2023 | Mar 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GRST21 | Greenstreets - Queens | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Mar 2027 | Mar 2025 | Mar 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GWENCS | Gwen Ifill Park PRB Construction | 1 | DEVELOP SCOPE | Feb 2022 | Jul 2022 | Feb 2022 | Jul 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GWENCS | Gwen Ifill Park PRB Construction | 2 | DESIGN | Jul 2022 | Jul 2023 | Jul 2022 | Jul 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GWENCS | Gwen Ifill Park PRB Construction | 3 | BID/ REGISTER CONTRACT | Jul 2023 | Apr 2024 | Jul 2023 | Apr 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GWENCS | Gwen Ifill Park PRB Construction | 4 | CONSTRUCTION | Apr 2024 | Apr 2025 | Apr 2024 | Apr 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GWENCS | Gwen Ifill Park PRB Construction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2025 | Apr 2026 | Apr 2025 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HCHAND | HALLET'S COVE RENOVATION OF HANDBALL COURT AND FENCING | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2007 | Sep 2007
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HCHAND | HALLET'S COVE RENOVATION OF HANDBALL COURT AND FENCING | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HCHAND | HALLET'S COVE RENOVATION OF HANDBALL COURT AND FENCING | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HCHAND | HALLET'S COVE RENOVATION OF HANDBALL COURT AND FENCING | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HCHAND | HALLET'S COVE RENOVATION OF HANDBALL COURT AND FENCING | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HCOVP2 | Hallet's Cove Playground MPPA Q226-119M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HCOVP2 | Hallet's Cove Playground MPPA Q226-119M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HCOVP2 | Hallet's Cove Playground MPPA Q226-119M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HCOVP2 | Hallet's Cove Playground MPPA Q226-119M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HCOVP2 | Hallet's Cove Playground MPPA Q226-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HILNDP | Highland Park Path Reconstruction | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2007 | Sep 2007
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HILNDP | Highland Park Path Reconstruction | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HILNDP | Highland Park Path Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HILNDP | Highland Park Path Reconstruction | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HILNDP | Highland Park Path Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HOLSCS | Hollis Playground Public Restroom Bldg Recon CNYG-522M | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HOLSCS | Hollis Playground Public Restroom Bldg Recon CNYG-522M | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HOLSCS | Hollis Playground Public Restroom Bldg Recon CNYG-522M | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HOLSCS | Hollis Playground Public Restroom Bldg Recon CNYG-522M | 4 | CONSTRUCTION | Sep 2024 | Mar 2026 | Sep 2024 | Mar 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HOLSCS | Hollis Playground Public Restroom Bldg Recon CNYG-522M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Mar 2027 | Mar 2026 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4IDLETB | IDLEWILD PARK CONSTRUCTION OF NATURE TRAIL AND BOARDWALK | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2025 | Dec 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4IDLETB | IDLEWILD PARK CONSTRUCTION OF NATURE TRAIL AND BOARDWALK | 2 | DESIGN | Dec 2016 | Mar 2018 | Dec 2025 | Mar 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4IDLETB | IDLEWILD PARK CONSTRUCTION OF NATURE TRAIL AND BOARDWALK | 3 | BID/ REGISTER CONTRACT | Mar 2018 | Dec 2018 | Mar 2027 | Dec 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4IDLETB | IDLEWILD PARK CONSTRUCTION OF NATURE TRAIL AND BOARDWALK | 4 | CONSTRUCTION | Dec 2018 | Dec 2020 | Dec 2027 | Dec 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4IDLETB | IDLEWILD PARK CONSTRUCTION OF NATURE TRAIL AND BOARDWALK | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2020 | Dec 2021 | Dec 2029 | Mar 2033
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4IDLTRF | IDLEWILD PARK: SYNTHETIC TURF FIELD RENOVATION | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4IDLTRF | IDLEWILD PARK: SYNTHETIC TURF FIELD RENOVATION | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4IDLTRF | IDLEWILD PARK: SYNTHETIC TURF FIELD RENOVATION | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4IDLTRF | IDLEWILD PARK: SYNTHETIC TURF FIELD RENOVATION | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4IDLTRF | IDLEWILD PARK: SYNTHETIC TURF FIELD RENOVATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4INGRVL | FLUSHING FIELDS (LEONARDO INGRAVALLO PLAYGROUND) RENO | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4INGRVL | FLUSHING FIELDS (LEONARDO INGRAVALLO PLAYGROUND) RENO | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4INGRVL | FLUSHING FIELDS (LEONARDO INGRAVALLO PLAYGROUND) RENO | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4INGRVL | FLUSHING FIELDS (LEONARDO INGRAVALLO PLAYGROUND) RENO | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4INGRVL | FLUSHING FIELDS (LEONARDO INGRAVALLO PLAYGROUND) RENO | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4JMMPP2 | JOE MICHAEL MILE PHASE 2 PATH RENO NORTH | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4JMMPP2 | JOE MICHAEL MILE PHASE 2 PATH RENO NORTH | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4JMMPP2 | JOE MICHAEL MILE PHASE 2 PATH RENO NORTH | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4JMMPP2 | JOE MICHAEL MILE PHASE 2 PATH RENO NORTH | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4JMMPP2 | JOE MICHAEL MILE PHASE 2 PATH RENO NORTH | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4KCPPAV | KISSENA CORRIDOR PARK: NEW SECURITY LIGHTING AND REPAVING | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4KCPPAV | KISSENA CORRIDOR PARK: NEW SECURITY LIGHTING AND REPAVING | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4KCPPAV | KISSENA CORRIDOR PARK: NEW SECURITY LIGHTING AND REPAVING | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4KCPPAV | KISSENA CORRIDOR PARK: NEW SECURITY LIGHTING AND REPAVING | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4KCPPAV | KISSENA CORRIDOR PARK: NEW SECURITY LIGHTING AND REPAVING | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4KNDYFL | Kennedy Playground Field House Reconstruction | 1 | DEVELOP SCOPE | Apr 2024 | Oct 2024 | Apr 2024 | Oct 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4KNDYFL | Kennedy Playground Field House Reconstruction | 2 | DESIGN | Oct 2024 | Oct 2025 | Oct 2024 | Oct 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4KNDYFL | Kennedy Playground Field House Reconstruction | 3 | BID/ REGISTER CONTRACT | Oct 2025 | Jul 2026 | Oct 2025 | Jul 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4KNDYFL | Kennedy Playground Field House Reconstruction | 4 | CONSTRUCTION | Jul 2026 | Jul 2027 | Jul 2026 | Jul 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4KNDYFL | Kennedy Playground Field House Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2027 | Jun 2028 | Jul 2027 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4KSNAPK | Kissena Park Path Reconstruction | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2007 | Sep 2007
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4KSNAPK | Kissena Park Path Reconstruction | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4KSNAPK | Kissena Park Path Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4KSNAPK | Kissena Park Path Reconstruction | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4KSNAPK | Kissena Park Path Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LATRUF | RUFUS KING MANOR & LEWIS H LATIMER HOUSE ROOFS QG-411M | 1 | DEVELOP SCOPE | Jul 2010 | Jul 2011 | Jul 2010 | Feb 2011
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LATRUF | RUFUS KING MANOR & LEWIS H LATIMER HOUSE ROOFS QG-411M | 2 | DESIGN | Jul 2011 | Oct 2011 | Feb 2011 | Jan 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LATRUF | RUFUS KING MANOR & LEWIS H LATIMER HOUSE ROOFS QG-411M | 3 | BID/ REGISTER CONTRACT | Oct 2011 | Jan 2012 | Jan 2015 | Apr 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LATRUF | RUFUS KING MANOR & LEWIS H LATIMER HOUSE ROOFS QG-411M | 4 | CONSTRUCTION | Jan 2012 | Jan 2013 | Apr 2015 | Apr 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LATRUF | RUFUS KING MANOR & LEWIS H LATIMER HOUSE ROOFS QG-411M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2013 | Jan 2014 | Apr 2016 | Jul 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LLVIRG | LAWRENCE VIRGILIO PLAYGROUND: PLAYGROUND RENOVATION | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LLVIRG | LAWRENCE VIRGILIO PLAYGROUND: PLAYGROUND RENOVATION | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LLVIRG | LAWRENCE VIRGILIO PLAYGROUND: PLAYGROUND RENOVATION | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LLVIRG | LAWRENCE VIRGILIO PLAYGROUND: PLAYGROUND RENOVATION | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LLVIRG | LAWRENCE VIRGILIO PLAYGROUND: PLAYGROUND RENOVATION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4MARFAJ | MARIO FAJARDO PLAYGROUND Q300-121M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Sep 2004 | Dec 2004
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4MARFAJ | MARIO FAJARDO PLAYGROUND Q300-121M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4MARFAJ | MARIO FAJARDO PLAYGROUND Q300-121M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4MARFAJ | MARIO FAJARDO PLAYGROUND Q300-121M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4MARFAJ | MARIO FAJARDO PLAYGROUND Q300-121M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4NNANPG | NOONAN PLAYGROUNDDOG RUN & SEATING AREA RECON- Q044-119M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4NNANPG | NOONAN PLAYGROUNDDOG RUN & SEATING AREA RECON- Q044-119M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4NNANPG | NOONAN PLAYGROUNDDOG RUN & SEATING AREA RECON- Q044-119M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4NNANPG | NOONAN PLAYGROUNDDOG RUN & SEATING AREA RECON- Q044-119M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4NNANPG | NOONAN PLAYGROUNDDOG RUN & SEATING AREA RECON- Q044-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OLMSRF | RC of the roof at Olmsted Center | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OLMSRF | RC of the roof at Olmsted Center | 2 | DESIGN | Dec 2021 | Dec 2023 | Dec 2021 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OLMSRF | RC of the roof at Olmsted Center | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OLMSRF | RC of the roof at Olmsted Center | 4 | CONSTRUCTION | Sep 2024 | Sep 2027 | Sep 2024 | Sep 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OLMSRF | RC of the roof at Olmsted Center | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Sep 2029 | Sep 2027 | Sep 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OLMST3 | OLMSTED CTR FURNITURE Q099-808MA1 | 1 | DEVELOP SCOPE | Jul 2009 | Sep 2009 | Jul 2009 | Sep 2009
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OLMST3 | OLMSTED CTR FURNITURE Q099-808MA1 | 2 | DESIGN | Sep 2009 | Dec 2009 | Sep 2009 | Dec 2009
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OLMST3 | OLMSTED CTR FURNITURE Q099-808MA1 | 3 | BID/ REGISTER CONTRACT | Dec 2009 | Mar 2010 | Dec 2009 | Mar 2010
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OLMST3 | OLMSTED CTR FURNITURE Q099-808MA1 | 4 | CONSTRUCTION | Mar 2010 | Mar 2011 | Mar 2010 | Mar 2011
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OLMST3 | OLMSTED CTR FURNITURE Q099-808MA1 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2011 | Mar 2012 | Mar 2011 | Jun 2031
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OLMST4 | OLMSTED CTR RC (BUILDING) Q099-808MA | 1 | DEVELOP SCOPE | Jul 2010 | Sep 2010 | Jul 2010 | Sep 2010
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OLMST4 | OLMSTED CTR RC (BUILDING) Q099-808MA | 2 | DESIGN | Sep 2010 | Dec 2010 | Jun 2013 | Sep 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OLMST4 | OLMSTED CTR RC (BUILDING) Q099-808MA | 3 | BID/ REGISTER CONTRACT | Dec 2010 | Mar 2011 | Sep 2013 | Mar 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OLMST4 | OLMSTED CTR RC (BUILDING) Q099-808MA | 4 | CONSTRUCTION | Mar 2011 | Mar 2012 | Mar 2014 | Feb 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OLMST4 | OLMSTED CTR RC (BUILDING) Q099-808MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2012 | Mar 2013 | Mar 2019 | Apr 2032
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OVERLO | Overlook Envelope | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OVERLO | Overlook Envelope | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OVERLO | Overlook Envelope | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OVERLO | Overlook Envelope | 4 | CONSTRUCTION | Sep 2024 | Mar 2026 | Sep 2024 | Mar 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OVERLO | Overlook Envelope | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Jun 2031 | Mar 2026 | Jun 2031
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PASAIR | Passerelle Building/ Port Arth. AirTrain | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PASAIR | Passerelle Building/ Port Arth. AirTrain | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PASAIR | Passerelle Building/ Port Arth. AirTrain | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PASAIR | Passerelle Building/ Port Arth. AirTrain | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PASAIR | Passerelle Building/ Port Arth. AirTrain | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2032
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PDLBRC | Lost Battalion Rec Ctr RC Q401-115M | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Sep 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PDLBRC | Lost Battalion Rec Ctr RC Q401-115M | 2 | DESIGN | Sep 2014 | Dec 2014 | Sep 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PDLBRC | Lost Battalion Rec Ctr RC Q401-115M | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2017 | Mar 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PDLBRC | Lost Battalion Rec Ctr RC Q401-115M | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2018 | Mar 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PDLBRC | Lost Battalion Rec Ctr RC Q401-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2019 | Dec 2032
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PHIPPS | Lt. Michael R. Davidson Playground Construction Q516-120M | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PHIPPS | Lt. Michael R. Davidson Playground Construction Q516-120M | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PHIPPS | Lt. Michael R. Davidson Playground Construction Q516-120M | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PHIPPS | Lt. Michael R. Davidson Playground Construction Q516-120M | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PHIPPS | Lt. Michael R. Davidson Playground Construction Q516-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PKTR23 | Queens Park Tree Planting FY23 | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PKTR23 | Queens Park Tree Planting FY23 | 2 | DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PKTR23 | Queens Park Tree Planting FY23 | 3 | BID/ REGISTER CONTRACT | Jun 2023 | Mar 2024 | Jun 2023 | Mar 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PKTR23 | Queens Park Tree Planting FY23 | 4 | CONSTRUCTION | Mar 2024 | Sep 2025 | Mar 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PKTR23 | Queens Park Tree Planting FY23 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PKTR24 | Queens Park Tree Planting FY24 | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PKTR24 | Queens Park Tree Planting FY24 | 2 | DESIGN | Feb 2024 | Aug 2024 | Feb 2024 | Aug 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PKTR24 | Queens Park Tree Planting FY24 | 3 | BID/ REGISTER CONTRACT | Aug 2024 | May 2025 | Aug 2024 | May 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PKTR24 | Queens Park Tree Planting FY24 | 4 | CONSTRUCTION | May 2025 | Nov 2026 | May 2025 | Nov 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PKTR24 | Queens Park Tree Planting FY24 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2028 | Nov 2026 | Nov 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG12A | Reconstruction of plgr, Borough ofQueens (QG-112M) | 1 | DEVELOP SCOPE | Jul 2011 | Sep 2011 | Jul 2007 | Sep 2007
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG12A | Reconstruction of plgr, Borough ofQueens (QG-112M) | 2 | DESIGN | Sep 2011 | Dec 2011 | Sep 2011 | Dec 2011
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG12A | Reconstruction of plgr, Borough ofQueens (QG-112M) | 3 | BID/ REGISTER CONTRACT | Dec 2011 | Mar 2012 | Dec 2011 | Mar 2012
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG12A | Reconstruction of plgr, Borough ofQueens (QG-112M) | 4 | CONSTRUCTION | Mar 2012 | Mar 2013 | Mar 2012 | Mar 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG12A | Reconstruction of plgr, Borough ofQueens (QG-112M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2013 | Mar 2014 | Mar 2013 | Jun 2033
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PNYT24 | FY14 St Tree Planting, Qns CB's 10, 12-14, PlaNYC (QG-1213M) | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PNYT24 | FY14 St Tree Planting, Qns CB's 10, 12-14, PlaNYC (QG-1213M) | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PNYT24 | FY14 St Tree Planting, Qns CB's 10, 12-14, PlaNYC (QG-1213M) | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2013 | Mar 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PNYT24 | FY14 St Tree Planting, Qns CB's 10, 12-14, PlaNYC (QG-1213M) | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PNYT24 | FY14 St Tree Planting, Qns CB's 10, 12-14, PlaNYC (QG-1213M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2015 | Jun 2030
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PNYT32 | Queens PLANYC CB 6, 9, 10 Street Tree Planting FY23 | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PNYT32 | Queens PLANYC CB 6, 9, 10 Street Tree Planting FY23 | 2 | DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PNYT32 | Queens PLANYC CB 6, 9, 10 Street Tree Planting FY23 | 3 | BID/ REGISTER CONTRACT | Jun 2023 | Mar 2024 | Jun 2023 | Mar 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PNYT32 | Queens PLANYC CB 6, 9, 10 Street Tree Planting FY23 | 4 | CONSTRUCTION | Mar 2024 | Sep 2025 | Mar 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PNYT32 | Queens PLANYC CB 6, 9, 10 Street Tree Planting FY23 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QMULT2 | QUEENS MULTISITE QG-506M | 1 | DEVELOP SCOPE | Jul 2005 | Sep 2005 | Jul 2005 | Sep 2005
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QMULT2 | QUEENS MULTISITE QG-506M | 2 | DESIGN | Sep 2005 | Dec 2005 | Sep 2005 | Dec 2005
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QMULT2 | QUEENS MULTISITE QG-506M | 3 | BID/ REGISTER CONTRACT | Dec 2005 | Mar 2006 | Dec 2005 | Mar 2006
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QMULT2 | QUEENS MULTISITE QG-506M | 4 | CONSTRUCTION | Mar 2006 | Mar 2007 | Mar 2006 | Mar 2007
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QMULT2 | QUEENS MULTISITE QG-506M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2007 | Mar 2008 | Mar 2007 | Jun 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QNPAV1 | State of Good Repair - Queens QG-121M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QNPAV1 | State of Good Repair - Queens QG-121M | 2 | DESIGN | Dec 2019 | Jun 2021 | Dec 2019 | Jun 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QNPAV1 | State of Good Repair - Queens QG-121M | 3 | BID/ REGISTER CONTRACT | Jun 2021 | Mar 2022 | Jun 2021 | Mar 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QNPAV1 | State of Good Repair - Queens QG-121M | 4 | CONSTRUCTION | Mar 2022 | Sep 2023 | Mar 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QNPAV1 | State of Good Repair - Queens QG-121M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QSTORE | QUEENS STOREHOUSE Q099-520M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QSTORE | QUEENS STOREHOUSE Q099-520M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QSTORE | QUEENS STOREHOUSE Q099-520M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QSTORE | QUEENS STOREHOUSE Q099-520M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QSTORE | QUEENS STOREHOUSE Q099-520M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QWCABR | Queens Wildlife Center Marsh Bridge Repair | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QWCABR | Queens Wildlife Center Marsh Bridge Repair | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QWCABR | Queens Wildlife Center Marsh Bridge Repair | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QWCABR | Queens Wildlife Center Marsh Bridge Repair | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QWCABR | Queens Wildlife Center Marsh Bridge Repair | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Mar 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QWCAMS | Queens Wildlife Center Aviary Mesh Replacement | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2023 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QWCAMS | Queens Wildlife Center Aviary Mesh Replacement | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2023 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QWCAMS | Queens Wildlife Center Aviary Mesh Replacement | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2023 | Mar 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QWCAMS | Queens Wildlife Center Aviary Mesh Replacement | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2024 | Mar 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QWCAMS | Queens Wildlife Center Aviary Mesh Replacement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2025 | Mar 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RAINE2 | Rainey Pk Picnic Grove, Bsktball Ct, & Dog Run R/C Q048-119M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RAINE2 | Rainey Pk Picnic Grove, Bsktball Ct, & Dog Run R/C Q048-119M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RAINE2 | Rainey Pk Picnic Grove, Bsktball Ct, & Dog Run R/C Q048-119M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RAINE2 | Rainey Pk Picnic Grove, Bsktball Ct, & Dog Run R/C Q048-119M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RAINE2 | Rainey Pk Picnic Grove, Bsktball Ct, & Dog Run R/C Q048-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Mar 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RAMBLE | Ramblersville Restoration Areas | 1 | DEVELOP SCOPE | Jun 2023 | Dec 2023 | Jun 2023 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RAMBLE | Ramblersville Restoration Areas | 2 | DESIGN | Dec 2023 | Dec 2025 | Dec 2023 | Dec 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RAMBLE | Ramblersville Restoration Areas | 3 | BID/ REGISTER CONTRACT | Dec 2025 | Sep 2026 | Dec 2025 | Sep 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RAMBLE | Ramblersville Restoration Areas | 4 | CONSTRUCTION | Sep 2026 | Sep 2029 | Sep 2026 | Sep 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RAMBLE | Ramblersville Restoration Areas | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2029 | Sep 2031 | Sep 2029 | Sep 2031
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RDGEWD | Rosemary's Plgd R/C Q398-117M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RDGEWD | Rosemary's Plgd R/C Q398-117M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RDGEWD | Rosemary's Plgd R/C Q398-117M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RDGEWD | Rosemary's Plgd R/C Q398-117M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RDGEWD | Rosemary's Plgd R/C Q398-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RGROI2 | Rockaway Beach Reformulation- Groin removal & crossing cons | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RGROI2 | Rockaway Beach Reformulation- Groin removal & crossing cons | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RGROI2 | Rockaway Beach Reformulation- Groin removal & crossing cons | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RGROI2 | Rockaway Beach Reformulation- Groin removal & crossing cons | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RGROI2 | Rockaway Beach Reformulation- Groin removal & crossing cons | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2024 | Sep 2022 | Sep 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RRDPK | Gwen Ifill Park Construction Q412-122M | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RRDPK | Gwen Ifill Park Construction Q412-122M | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RRDPK | Gwen Ifill Park Construction Q412-122M | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RRDPK | Gwen Ifill Park Construction Q412-122M | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RRDPK | Gwen Ifill Park Construction Q412-122M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SAND01 | SANDY - Sunset Cove Salt Marsh Restoration Q498-115M | 4 | CONSTRUCTION | Sep 2019 | Sep 2021 | Sep 2019 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SAND01 | SANDY - Sunset Cove Salt Marsh Restoration Q498-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SAND03 | SANDY - Spring Creek Reforestation CNYG-316M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jan 2021 | Jul 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SAND03 | SANDY - Spring Creek Reforestation CNYG-316M | 2 | DESIGN | Dec 2016 | Mar 2018 | Jul 2021 | Oct 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SAND03 | SANDY - Spring Creek Reforestation CNYG-316M | 3 | BID/ REGISTER CONTRACT | Mar 2018 | Dec 2018 | Oct 2022 | Jul 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SAND03 | SANDY - Spring Creek Reforestation CNYG-316M | 4 | CONSTRUCTION | Dec 2018 | Dec 2020 | Jul 2023 | Jun 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SAND03 | SANDY - Spring Creek Reforestation CNYG-316M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2020 | Dec 2021 | Jul 2025 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREAC | Shorefront Parkway Adventure Course Q163-218M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREAC | Shorefront Parkway Adventure Course Q163-218M | 2 | DESIGN | Dec 2017 | Jun 2019 | Dec 2017 | Jun 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREAC | Shorefront Parkway Adventure Course Q163-218M | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Mar 2020 | Jun 2019 | Mar 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREAC | Shorefront Parkway Adventure Course Q163-218M | 4 | CONSTRUCTION | Mar 2020 | Sep 2021 | Mar 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREAC | Shorefront Parkway Adventure Course Q163-218M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREDP | Shorefront Parkway Dog Run Cons. Q163-118M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREDP | Shorefront Parkway Dog Run Cons. Q163-118M | 2 | DESIGN | Dec 2017 | Jun 2019 | Dec 2017 | Jun 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREDP | Shorefront Parkway Dog Run Cons. Q163-118M | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Mar 2020 | Jun 2019 | Mar 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREDP | Shorefront Parkway Dog Run Cons. Q163-118M | 4 | CONSTRUCTION | Mar 2020 | Sep 2021 | Mar 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREDP | Shorefront Parkway Dog Run Cons. Q163-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREPG | Shorefront Tot Playground and Plaza Area Q163-318M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREPG | Shorefront Tot Playground and Plaza Area Q163-318M | 2 | DESIGN | Dec 2017 | Jun 2019 | Dec 2017 | Jun 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREPG | Shorefront Tot Playground and Plaza Area Q163-318M | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Mar 2020 | Jun 2019 | Mar 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREPG | Shorefront Tot Playground and Plaza Area Q163-318M | 4 | CONSTRUCTION | Mar 2020 | Sep 2021 | Mar 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREPG | Shorefront Tot Playground and Plaza Area Q163-318M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHRESA | Shorefront Parkway Park Amenities Q163-120M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHRESA | Shorefront Parkway Park Amenities Q163-120M | 2 | DESIGN | Dec 2017 | Jun 2019 | Dec 2017 | Jun 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHRESA | Shorefront Parkway Park Amenities Q163-120M | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Mar 2020 | Jun 2019 | Mar 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHRESA | Shorefront Parkway Park Amenities Q163-120M | 4 | CONSTRUCTION | Mar 2020 | Sep 2021 | Mar 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHRESA | Shorefront Parkway Park Amenities Q163-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHRESF | Shorefront Parkway Multi-Purpose Sports Field Cons Q163-618M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHRESF | Shorefront Parkway Multi-Purpose Sports Field Cons Q163-618M | 2 | DESIGN | Dec 2017 | Jun 2019 | Dec 2017 | Jun 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHRESF | Shorefront Parkway Multi-Purpose Sports Field Cons Q163-618M | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Mar 2020 | Jun 2019 | Mar 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHRESF | Shorefront Parkway Multi-Purpose Sports Field Cons Q163-618M | 4 | CONSTRUCTION | Mar 2020 | Sep 2021 | Mar 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHRESF | Shorefront Parkway Multi-Purpose Sports Field Cons Q163-618M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4STFCAR | Syn Turf Field Recon at Rachel Carson at Kessina, QN | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4STFCAR | Syn Turf Field Recon at Rachel Carson at Kessina, QN | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4STFCAR | Syn Turf Field Recon at Rachel Carson at Kessina, QN | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4STFCAR | Syn Turf Field Recon at Rachel Carson at Kessina, QN | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4STFCAR | Syn Turf Field Recon at Rachel Carson at Kessina, QN | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4STMCPG | ST. MICHAEL'S PLAYGROUND RECONSTRUCTION | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4STMCPG | ST. MICHAEL'S PLAYGROUND RECONSTRUCTION | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4STMCPG | ST. MICHAEL'S PLAYGROUND RECONSTRUCTION | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4STMCPG | ST. MICHAEL'S PLAYGROUND RECONSTRUCTION | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4STMCPG | ST. MICHAEL'S PLAYGROUND RECONSTRUCTION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SUNRSE | Sunrise Stables Acquisition | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SUNRSE | Sunrise Stables Acquisition | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SUNRSE | Sunrise Stables Acquisition | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SUNRSE | Sunrise Stables Acquisition | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SUNRSE | Sunrise Stables Acquisition | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE14A | FY14 Street Tree Planting, Queens CB's 1 - 6 (QG-1013M) | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE14A | FY14 Street Tree Planting, Queens CB's 1 - 6 (QG-1013M) | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE14A | FY14 Street Tree Planting, Queens CB's 1 - 6 (QG-1013M) | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2013 | Mar 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE14A | FY14 Street Tree Planting, Queens CB's 1 - 6 (QG-1013M) | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE14A | FY14 Street Tree Planting, Queens CB's 1 - 6 (QG-1013M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2015 | Jun 2030
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE21A | FY21 Street Tree Queens CBs 1-6 QG- | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE21A | FY21 Street Tree Queens CBs 1-6 QG- | 2 | DESIGN | Dec 2019 | Jun 2020 | Dec 2019 | Jun 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE21A | FY21 Street Tree Queens CBs 1-6 QG- | 3 | BID/ REGISTER CONTRACT | Jun 2020 | Mar 2021 | Jun 2020 | Mar 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE21A | FY21 Street Tree Queens CBs 1-6 QG- | 4 | CONSTRUCTION | Mar 2021 | Sep 2022 | Mar 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE21A | FY21 Street Tree Queens CBs 1-6 QG- | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2024 | Sep 2022 | Jun 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE23B | Queens CB 7 Street Tree Planting FY23 | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE23B | Queens CB 7 Street Tree Planting FY23 | 2 | DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE23B | Queens CB 7 Street Tree Planting FY23 | 3 | BID/ REGISTER CONTRACT | Jun 2023 | Mar 2024 | Jun 2023 | Mar 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE23B | Queens CB 7 Street Tree Planting FY23 | 4 | CONSTRUCTION | Mar 2024 | Sep 2025 | Mar 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE23B | Queens CB 7 Street Tree Planting FY23 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE23C | Queens CB 1-5 Street Tree Planting FY23 | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE23C | Queens CB 1-5 Street Tree Planting FY23 | 2 | DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE23C | Queens CB 1-5 Street Tree Planting FY23 | 3 | BID/ REGISTER CONTRACT | Jun 2023 | Mar 2024 | Jun 2023 | Mar 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE23C | Queens CB 1-5 Street Tree Planting FY23 | 4 | CONSTRUCTION | Mar 2024 | Sep 2025 | Mar 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE23C | Queens CB 1-5 Street Tree Planting FY23 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE24C | Queens Street Tree Planting FY24 - Community Board 6, 9 & 10 | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE24C | Queens Street Tree Planting FY24 - Community Board 6, 9 & 10 | 2 | DESIGN | Feb 2024 | Aug 2024 | Feb 2024 | Aug 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE24C | Queens Street Tree Planting FY24 - Community Board 6, 9 & 10 | 3 | BID/ REGISTER CONTRACT | Aug 2024 | May 2025 | Aug 2024 | May 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE24C | Queens Street Tree Planting FY24 - Community Board 6, 9 & 10 | 4 | CONSTRUCTION | May 2025 | Nov 2026 | May 2025 | Nov 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE24C | Queens Street Tree Planting FY24 - Community Board 6, 9 & 10 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2028 | Nov 2026 | Nov 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREE08 | FY13 Street Tree Planting Qns CB 1-8 (QG-911MR PlaNYC) | 2 | DESIGN | Sep 2012 | Dec 2012 | Sep 2012 | Dec 2012
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREE08 | FY13 Street Tree Planting Qns CB 1-8 (QG-911MR PlaNYC) | 3 | BID/ REGISTER CONTRACT | Dec 2012 | Mar 2013 | Dec 2012 | Mar 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREE08 | FY13 Street Tree Planting Qns CB 1-8 (QG-911MR PlaNYC) | 4 | CONSTRUCTION | Mar 2013 | Mar 2014 | Mar 2013 | Mar 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREE08 | FY13 Street Tree Planting Qns CB 1-8 (QG-911MR PlaNYC) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREE10 | FY13 Street Tree Planting Queens CBs 7-10, 12-14(QG-213M) | 3 | BID/ REGISTER CONTRACT | Dec 2012 | Mar 2013 | Dec 2012 | Mar 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREE10 | FY13 Street Tree Planting Queens CBs 7-10, 12-14(QG-213M) | 4 | CONSTRUCTION | Mar 2013 | Mar 2014 | Mar 2013 | Mar 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREE10 | FY13 Street Tree Planting Queens CBs 7-10, 12-14(QG-213M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREL21 | FY21 Street Trees QN CB's 8,11-13, QG-1219M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREL21 | FY21 Street Trees QN CB's 8,11-13, QG-1219M | 2 | DESIGN | Dec 2019 | Jun 2021 | Dec 2019 | Jun 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREL21 | FY21 Street Trees QN CB's 8,11-13, QG-1219M | 3 | BID/ REGISTER CONTRACT | Jun 2021 | Mar 2022 | Jun 2021 | Mar 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREL21 | FY21 Street Trees QN CB's 8,11-13, QG-1219M | 4 | CONSTRUCTION | Mar 2022 | Mar 2025 | Mar 2022 | Mar 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREL21 | FY21 Street Trees QN CB's 8,11-13, QG-1219M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Mar 2027 | Mar 2025 | Sep 2030
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREP23 | FY23 Street Trees QN CB's 1-6 | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREP23 | FY23 Street Trees QN CB's 1-6 | 2 | DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREP23 | FY23 Street Trees QN CB's 1-6 | 3 | BID/ REGISTER CONTRACT | Jun 2023 | Mar 2024 | Jun 2023 | Mar 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREP23 | FY23 Street Trees QN CB's 1-6 | 4 | CONSTRUCTION | Mar 2024 | Sep 2025 | Mar 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREP23 | FY23 Street Trees QN CB's 1-6 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRS23A | Queens Tree-Damaged Sidewalk Reconstruction FY23, CBs 9 -14 | 1 | DEVELOP SCOPE | Jan 2023 | Jun 2023 | Jan 2023 | Jun 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRS23A | Queens Tree-Damaged Sidewalk Reconstruction FY23, CBs 9 -14 | 2 | DESIGN | Jun 2023 | Dec 2023 | Jun 2023 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRS23A | Queens Tree-Damaged Sidewalk Reconstruction FY23, CBs 9 -14 | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRS23A | Queens Tree-Damaged Sidewalk Reconstruction FY23, CBs 9 -14 | 4 | CONSTRUCTION | Sep 2024 | Mar 2026 | Sep 2024 | Mar 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRS23A | Queens Tree-Damaged Sidewalk Reconstruction FY23, CBs 9 -14 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Mar 2028 | Mar 2026 | Mar 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRS23B | Queens Tree-Damaged Sidewalk Reconstruction FY23, CB 3,4 | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRS23B | Queens Tree-Damaged Sidewalk Reconstruction FY23, CB 3,4 | 2 | DESIGN | Feb 2024 | Aug 2024 | Feb 2024 | Aug 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRS23B | Queens Tree-Damaged Sidewalk Reconstruction FY23, CB 3,4 | 3 | BID/ REGISTER CONTRACT | Aug 2024 | May 2025 | Aug 2024 | May 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRS23B | Queens Tree-Damaged Sidewalk Reconstruction FY23, CB 3,4 | 4 | CONSTRUCTION | May 2025 | Nov 2026 | May 2025 | Nov 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRS23B | Queens Tree-Damaged Sidewalk Reconstruction FY23, CB 3,4 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2028 | Nov 2026 | Nov 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRSD23 | Queens Tree-Damaged Sidewalk Reconstruction | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRSD23 | Queens Tree-Damaged Sidewalk Reconstruction | 2 | DESIGN | Feb 2024 | Feb 2026 | Feb 2024 | Feb 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRSD23 | Queens Tree-Damaged Sidewalk Reconstruction | 3 | BID/ REGISTER CONTRACT | Feb 2026 | Nov 2026 | Feb 2026 | Nov 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRSD23 | Queens Tree-Damaged Sidewalk Reconstruction | 4 | CONSTRUCTION | Nov 2026 | Nov 2029 | Nov 2026 | Nov 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRSD23 | Queens Tree-Damaged Sidewalk Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2029 | Nov 2031 | Nov 2029 | Nov 2031
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4UDALNP | Udalls Cove Park & Nature Preserve | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4UDALNP | Udalls Cove Park & Nature Preserve | 2 | DESIGN | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4UDALNP | Udalls Cove Park & Nature Preserve | 3 | BID/ REGISTER CONTRACT | Sep 2021 | Jun 2022 | Sep 2021 | Jun 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4UDALNP | Udalls Cove Park & Nature Preserve | 4 | CONSTRUCTION | Jun 2022 | Dec 2024 | Jun 2022 | Dec 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4UDALNP | Udalls Cove Park & Nature Preserve | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2024 | Dec 2026 | Dec 2024 | Dec 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4UNION | Union Street Beautification | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4UNION | Union Street Beautification | 2 | DESIGN | Dec 2021 | Jun 2022 | Dec 2021 | Jun 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4UNION | Union Street Beautification | 3 | BID/ REGISTER CONTRACT | Jun 2022 | Mar 2023 | Jun 2022 | Mar 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4UNION | Union Street Beautification | 4 | CONSTRUCTION | Mar 2023 | Sep 2024 | Mar 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4UNION | Union Street Beautification | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2026 | Sep 2024 | Sep 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WATECS | WATERS EDGE PLGD PRB RECON | 1 | DEVELOP SCOPE | Feb 2022 | Jul 2022 | Feb 2022 | Jul 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WATECS | WATERS EDGE PLGD PRB RECON | 2 | DESIGN | Jul 2022 | Jul 2023 | Jul 2022 | Jul 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WATECS | WATERS EDGE PLGD PRB RECON | 3 | BID/ REGISTER CONTRACT | Jul 2023 | Apr 2024 | Jul 2023 | Apr 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WATECS | WATERS EDGE PLGD PRB RECON | 4 | CONSTRUCTION | Apr 2024 | Apr 2025 | Apr 2024 | Apr 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WATECS | WATERS EDGE PLGD PRB RECON | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2025 | Apr 2026 | Apr 2025 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WATEDG | Cross Island Parkway Waters Edge Drive PLGD CONS Q135-122M | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WATEDG | Cross Island Parkway Waters Edge Drive PLGD CONS Q135-122M | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WATEDG | Cross Island Parkway Waters Edge Drive PLGD CONS Q135-122M | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WATEDG | Cross Island Parkway Waters Edge Drive PLGD CONS Q135-122M | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WATEDG | Cross Island Parkway Waters Edge Drive PLGD CONS Q135-122M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WOODPG | WOODTREE PLAYGROUND: RENOVATE THE BASKETBALL COURTS | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WOODPG | WOODTREE PLAYGROUND: RENOVATE THE BASKETBALL COURTS | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WOODPG | WOODTREE PLAYGROUND: RENOVATE THE BASKETBALL COURTS | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WOODPG | WOODTREE PLAYGROUND: RENOVATE THE BASKETBALL COURTS | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WOODPG | WOODTREE PLAYGROUND: RENOVATE THE BASKETBALL COURTS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WOODPZ | WOODSIDE PLAZA Q198-121M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WOODPZ | WOODSIDE PLAZA Q198-121M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WOODPZ | WOODSIDE PLAZA Q198-121M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WOODPZ | WOODSIDE PLAZA Q198-121M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WOODPZ | WOODSIDE PLAZA Q198-121M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WPWSDE | Walk to Park NYCHA Woodside Playground Construction | 1 | DEVELOP SCOPE | Mar 2018 | Sep 2018 | Mar 2018 | Sep 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WPWSDE | Walk to Park NYCHA Woodside Playground Construction | 2 | DESIGN | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WPWSDE | Walk to Park NYCHA Woodside Playground Construction | 3 | BID/ REGISTER CONTRACT | Sep 2019 | May 2020 | Sep 2019 | May 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WPWSDE | Walk to Park NYCHA Woodside Playground Construction | 4 | CONSTRUCTION | May 2020 | May 2021 | May 2020 | May 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WPWSDE | Walk to Park NYCHA Woodside Playground Construction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | May 2021 | May 2022 | May 2021 | Jun 2030
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | RE2544DR2 | RC 44TH DRIVE PIER QG-47250-108MA | 1 | DEVELOP SCOPE | Jul 2008 | Sep 2008 | Jul 2008 | Sep 2008
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | RE2544DR2 | RC 44TH DRIVE PIER QG-47250-108MA | 2 | DESIGN | Sep 2008 | Dec 2008 | Sep 2008 | Dec 2008
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | RE2544DR2 | RC 44TH DRIVE PIER QG-47250-108MA | 3 | BID/ REGISTER CONTRACT | Dec 2008 | Mar 2009 | Dec 2008 | Mar 2009
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | RE2544DR2 | RC 44TH DRIVE PIER QG-47250-108MA | 4 | CONSTRUCTION | Mar 2009 | Mar 2010 | Mar 2009 | Mar 2010
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | RE2544DR2 | RC 44TH DRIVE PIER QG-47250-108MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2010 | Mar 2011 | Mar 2010 | Jun 2033
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-01 | SANDY - Queens Plgd requirements (Type 1) QG-112M | 1 | DEVELOP SCOPE | Dec 2012 | Feb 2013 | Dec 2012 | Feb 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-01 | SANDY - Queens Plgd requirements (Type 1) QG-112M | 2 | DESIGN | Mar 2013 | May 2013 | Mar 2013 | May 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-01 | SANDY - Queens Plgd requirements (Type 1) QG-112M | 3 | BID/ REGISTER CONTRACT | May 2013 | Aug 2013 | May 2013 | Aug 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-01 | SANDY - Queens Plgd requirements (Type 1) QG-112M | 4 | CONSTRUCTION | Aug 2013 | Aug 2014 | Aug 2013 | Aug 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-01 | SANDY - Queens Plgd requirements (Type 1) QG-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2014 | Aug 2015 | Aug 2014 | Aug 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-02 | SANDY- Emergency Storm Make Safe - Rockaway Beach Q162-213M | 1 | DEVELOP SCOPE | Dec 2012 | Feb 2013 | Dec 2012 | Feb 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-02 | SANDY- Emergency Storm Make Safe - Rockaway Beach Q162-213M | 2 | DESIGN | Mar 2013 | May 2013 | Mar 2013 | May 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-02 | SANDY- Emergency Storm Make Safe - Rockaway Beach Q162-213M | 3 | BID/ REGISTER CONTRACT | May 2013 | Aug 2013 | May 2013 | Aug 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-02 | SANDY- Emergency Storm Make Safe - Rockaway Beach Q162-213M | 4 | CONSTRUCTION | Aug 2013 | Aug 2014 | Aug 2013 | Aug 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-02 | SANDY- Emergency Storm Make Safe - Rockaway Beach Q162-213M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2014 | Aug 2015 | Aug 2014 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-08 | PNP Socrates Sculpture Park | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-08 | PNP Socrates Sculpture Park | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-08 | PNP Socrates Sculpture Park | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2013 | Mar 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-08 | PNP Socrates Sculpture Park | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-08 | PNP Socrates Sculpture Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2015 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-09 | SANDY - Queens Plgrd requirements (Type 1) QG-112M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-09 | SANDY - Queens Plgrd requirements (Type 1) QG-112M | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-09 | SANDY - Queens Plgrd requirements (Type 1) QG-112M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2013 | Mar 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-09 | SANDY - Queens Plgrd requirements (Type 1) QG-112M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-09 | SANDY - Queens Plgrd requirements (Type 1) QG-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2015 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-10 | Ralph DeMarco Pk, Shoreline R/C Q004-213M | 1 | DEVELOP SCOPE | Jun 2013 | Aug 2013 | Jun 2013 | Aug 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-10 | Ralph DeMarco Pk, Shoreline R/C Q004-213M | 2 | DESIGN | Aug 2013 | Nov 2013 | Aug 2016 | Sep 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-10 | Ralph DeMarco Pk, Shoreline R/C Q004-213M | 3 | BID/ REGISTER CONTRACT | Nov 2013 | Feb 2014 | Sep 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-10 | Ralph DeMarco Pk, Shoreline R/C Q004-213M | 4 | CONSTRUCTION | Feb 2014 | Feb 2015 | Dec 2017 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-10 | Ralph DeMarco Pk, Shoreline R/C Q004-213M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2015 | Feb 2016 | Dec 2018 | Dec 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-12 | SANDY- Joe Michael's Mile Promenade Q135-214M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-12 | SANDY- Joe Michael's Mile Promenade Q135-214M | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-12 | SANDY- Joe Michael's Mile Promenade Q135-214M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2013 | Mar 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-12 | SANDY- Joe Michael's Mile Promenade Q135-214M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-12 | SANDY- Joe Michael's Mile Promenade Q135-214M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2015 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-13 | SANDY-Rockaway Beach roller hockey rink - Type 3 Q163-114M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-13 | SANDY-Rockaway Beach roller hockey rink - Type 3 Q163-114M | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-13 | SANDY-Rockaway Beach roller hockey rink - Type 3 Q163-114M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2013 | Mar 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-13 | SANDY-Rockaway Beach roller hockey rink - Type 3 Q163-114M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-13 | SANDY-Rockaway Beach roller hockey rink - Type 3 Q163-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2015 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-14 | SANDY - Tree removals - Queens CB 1-5 QG-314M | 3 | BID/ REGISTER CONTRACT | Jun 2014 | Sep 2014 | Jun 2014 | Sep 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-14 | SANDY - Tree removals - Queens CB 1-5 QG-314M | 4 | CONSTRUCTION | Sep 2014 | Sep 2015 | Sep 2014 | Sep 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-14 | SANDY - Tree removals - Queens CB 1-5 QG-314M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2015 | Sep 2016 | Sep 2015 | Sep 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-15 | SANDY - Tree removals - Queens CB 6-15 QG-414M | 1 | DEVELOP SCOPE | Jan 2014 | Mar 2014 | Jan 2014 | Jun 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-15 | SANDY - Tree removals - Queens CB 6-15 QG-414M | 2 | DESIGN | Apr 2014 | Jun 2014 | Jun 2019 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-15 | SANDY - Tree removals - Queens CB 6-15 QG-414M | 3 | BID/ REGISTER CONTRACT | Jun 2014 | Sep 2014 | Sep 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-15 | SANDY - Tree removals - Queens CB 6-15 QG-414M | 4 | CONSTRUCTION | Sep 2014 | Sep 2015 | Dec 2019 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-15 | SANDY - Tree removals - Queens CB 6-15 QG-414M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2015 | Sep 2016 | Dec 2020 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-18 | SANDY - Tribute Park Reconstruction Q028-116M | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Sep 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-18 | SANDY - Tribute Park Reconstruction Q028-116M | 2 | DESIGN | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-18 | SANDY - Tribute Park Reconstruction Q028-116M | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2014 | Mar 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-18 | SANDY - Tribute Park Reconstruction Q028-116M | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-18 | SANDY - Tribute Park Reconstruction Q028-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2016 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-19 | SANDY - BAYSIDE MARINA ELECTRICAL UPGRADE Q135-115M | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2014 | Mar 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-19 | SANDY - BAYSIDE MARINA ELECTRICAL UPGRADE Q135-115M | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-19 | SANDY - BAYSIDE MARINA ELECTRICAL UPGRADE Q135-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-21 | SANDY-FOREST PARK GREENHOUSE BROKEN GLASS REPLACEMENT | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-21 | SANDY-FOREST PARK GREENHOUSE BROKEN GLASS REPLACEMENT | 2 | DESIGN | Dec 2016 | Dec 2018 | Dec 2016 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-21 | SANDY-FOREST PARK GREENHOUSE BROKEN GLASS REPLACEMENT | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-21 | SANDY-FOREST PARK GREENHOUSE BROKEN GLASS REPLACEMENT | 4 | CONSTRUCTION | Sep 2019 | Sep 2021 | Sep 2019 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-21 | SANDY-FOREST PARK GREENHOUSE BROKEN GLASS REPLACEMENT | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-22 | SANDY - Rockaway Beach Shorefront Pkwy Handball Ct Q163-315M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-22 | SANDY - Rockaway Beach Shorefront Pkwy Handball Ct Q163-315M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-22 | SANDY - Rockaway Beach Shorefront Pkwy Handball Ct Q163-315M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-22 | SANDY - Rockaway Beach Shorefront Pkwy Handball Ct Q163-315M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-22 | SANDY - Rockaway Beach Shorefront Pkwy Handball Ct Q163-315M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-25 | Bayside Marina Reconstruction (Q135-117M) | 1 | DEVELOP SCOPE | Aug 2016 | Jan 2017 | Aug 2016 | Jan 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-25 | Bayside Marina Reconstruction (Q135-117M) | 2 | DESIGN | Jan 2017 | Jan 2019 | Jan 2017 | Jan 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-25 | Bayside Marina Reconstruction (Q135-117M) | 3 | BID/ REGISTER CONTRACT | Jan 2019 | Oct 2019 | Jan 2019 | Oct 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-25 | Bayside Marina Reconstruction (Q135-117M) | 4 | CONSTRUCTION | Oct 2019 | Oct 2021 | Oct 2019 | Oct 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-25 | Bayside Marina Reconstruction (Q135-117M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2021 | Oct 2022 | Oct 2021 | Jun 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-26 | World's Fair Marina Q099-218M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-26 | World's Fair Marina Q099-218M | 2 | DESIGN | Dec 2016 | Dec 2018 | Dec 2016 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-26 | World's Fair Marina Q099-218M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-26 | World's Fair Marina Q099-218M | 4 | CONSTRUCTION | Sep 2019 | Sep 2021 | Sep 2019 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-26 | World's Fair Marina Q099-218M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-27 | Little Bay Revetment | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-27 | Little Bay Revetment | 2 | DESIGN | Dec 2016 | Dec 2018 | Dec 2016 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-27 | Little Bay Revetment | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-27 | Little Bay Revetment | 4 | CONSTRUCTION | Sep 2019 | Sep 2021 | Sep 2019 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-27 | Little Bay Revetment | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-29 | FMCP Electrical Repairs Q099-220M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-29 | FMCP Electrical Repairs Q099-220M | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-29 | FMCP Electrical Repairs Q099-220M | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-29 | FMCP Electrical Repairs Q099-220M | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-29 | FMCP Electrical Repairs Q099-220M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-33 | SANDY - Shorefront Park MPPA Sports Field Cons. Q163-618M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-33 | SANDY - Shorefront Park MPPA Sports Field Cons. Q163-618M | 2 | DESIGN | Dec 2017 | Jun 2019 | Dec 2017 | Jun 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-33 | SANDY - Shorefront Park MPPA Sports Field Cons. Q163-618M | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Mar 2020 | Jun 2019 | Mar 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-33 | SANDY - Shorefront Park MPPA Sports Field Cons. Q163-618M | 4 | CONSTRUCTION | Mar 2020 | Sep 2021 | Mar 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-33 | SANDY - Shorefront Park MPPA Sports Field Cons. Q163-618M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-34 | SANDY - Shorefront Labyrinth and Seating Area Q163-518M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-34 | SANDY - Shorefront Labyrinth and Seating Area Q163-518M | 2 | DESIGN | Dec 2017 | Jun 2019 | Dec 2017 | Jun 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-34 | SANDY - Shorefront Labyrinth and Seating Area Q163-518M | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Mar 2020 | Jun 2019 | Mar 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-34 | SANDY - Shorefront Labyrinth and Seating Area Q163-518M | 4 | CONSTRUCTION | Mar 2020 | Sep 2021 | Mar 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-34 | SANDY - Shorefront Labyrinth and Seating Area Q163-518M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-35 | SANDY - Shorefront Tot Playground and Plaza Area Q163-318M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-35 | SANDY - Shorefront Tot Playground and Plaza Area Q163-318M | 2 | DESIGN | Dec 2017 | Jun 2019 | Dec 2017 | Jun 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-35 | SANDY - Shorefront Tot Playground and Plaza Area Q163-318M | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Mar 2020 | Jun 2019 | Mar 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-35 | SANDY - Shorefront Tot Playground and Plaza Area Q163-318M | 4 | CONSTRUCTION | Mar 2020 | Sep 2021 | Mar 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-35 | SANDY - Shorefront Tot Playground and Plaza Area Q163-318M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-36 | SANDY - Shorefront Parkway Adventure Course Q163-218M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-36 | SANDY - Shorefront Parkway Adventure Course Q163-218M | 2 | DESIGN | Dec 2017 | Jun 2019 | Dec 2017 | Jun 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-36 | SANDY - Shorefront Parkway Adventure Course Q163-218M | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Mar 2020 | Jun 2019 | Mar 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-36 | SANDY - Shorefront Parkway Adventure Course Q163-218M | 4 | CONSTRUCTION | Mar 2020 | Sep 2021 | Mar 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-36 | SANDY - Shorefront Parkway Adventure Course Q163-218M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-37 | SANDY - Beach 88th Street Park Construction Q499-118M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-37 | SANDY - Beach 88th Street Park Construction Q499-118M | 2 | DESIGN | Dec 2017 | Jun 2019 | Dec 2017 | Jun 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-37 | SANDY - Beach 88th Street Park Construction Q499-118M | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Mar 2020 | Jun 2019 | Mar 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-37 | SANDY - Beach 88th Street Park Construction Q499-118M | 4 | CONSTRUCTION | Mar 2020 | Sep 2021 | Mar 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-37 | SANDY - Beach 88th Street Park Construction Q499-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-38 | SANDY - Beach 24th to Beach 25th Street Ramp Q162-218M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-38 | SANDY - Beach 24th to Beach 25th Street Ramp Q162-218M | 2 | DESIGN | Dec 2018 | Dec 2020 | Dec 2018 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-38 | SANDY - Beach 24th to Beach 25th Street Ramp Q162-218M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-38 | SANDY - Beach 24th to Beach 25th Street Ramp Q162-218M | 4 | CONSTRUCTION | Sep 2021 | Sep 2023 | Sep 2021 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-38 | SANDY - Beach 24th to Beach 25th Street Ramp Q162-218M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-39 | SANDY - Rockaway Community Park Shoreline R/C Q371-119M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-39 | SANDY - Rockaway Community Park Shoreline R/C Q371-119M | 2 | DESIGN | Dec 2017 | Jun 2019 | Dec 2017 | Jun 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-39 | SANDY - Rockaway Community Park Shoreline R/C Q371-119M | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Mar 2020 | Jun 2019 | Mar 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-39 | SANDY - Rockaway Community Park Shoreline R/C Q371-119M | 4 | CONSTRUCTION | Mar 2020 | Sep 2021 | Mar 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-39 | SANDY - Rockaway Community Park Shoreline R/C Q371-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-41 | SANDY - Michaelis-Bayswater Park R/C Q007-119M | 2 | DESIGN | Dec 2017 | Jun 2019 | Dec 2017 | Jun 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-41 | SANDY - Michaelis-Bayswater Park R/C Q007-119M | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Mar 2020 | Jun 2019 | Mar 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-41 | SANDY - Michaelis-Bayswater Park R/C Q007-119M | 4 | CONSTRUCTION | Mar 2020 | Sep 2021 | Mar 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-41 | SANDY - Michaelis-Bayswater Park R/C Q007-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-42 | SANDY - Shorefront Parkway Dog Run Cons. Q163-118M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-42 | SANDY - Shorefront Parkway Dog Run Cons. Q163-118M | 2 | DESIGN | Dec 2017 | Jun 2019 | Dec 2017 | Jun 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-42 | SANDY - Shorefront Parkway Dog Run Cons. Q163-118M | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Mar 2020 | Jun 2019 | Mar 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-42 | SANDY - Shorefront Parkway Dog Run Cons. Q163-118M | 4 | CONSTRUCTION | Mar 2020 | Sep 2021 | Mar 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-42 | SANDY - Shorefront Parkway Dog Run Cons. Q163-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-44 | SANDY - Shorefront Parkway Park Amenities | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-44 | SANDY - Shorefront Parkway Park Amenities | 2 | DESIGN | Dec 2017 | Jun 2019 | Dec 2017 | Jun 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-44 | SANDY - Shorefront Parkway Park Amenities | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Mar 2020 | Jun 2019 | Mar 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-44 | SANDY - Shorefront Parkway Park Amenities | 4 | CONSTRUCTION | Mar 2020 | Sep 2021 | Mar 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-44 | SANDY - Shorefront Parkway Park Amenities | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-45 | SANDY - Thursby Basin Park Construction Q479-120M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-45 | SANDY - Thursby Basin Park Construction Q479-120M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-45 | SANDY - Thursby Basin Park Construction Q479-120M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-45 | SANDY - Thursby Basin Park Construction Q479-120M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-45 | SANDY - Thursby Basin Park Construction Q479-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-46 | Joe Michael's Mile (Q012-120M) | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-46 | Joe Michael's Mile (Q012-120M) | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-46 | Joe Michael's Mile (Q012-120M) | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-46 | Joe Michael's Mile (Q012-120M) | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-46 | Joe Michael's Mile (Q012-120M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-48 | Bayswater Park Reconstruction-FEMA | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-48 | Bayswater Park Reconstruction-FEMA | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-48 | Bayswater Park Reconstruction-FEMA | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-48 | Bayswater Park Reconstruction-FEMA | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-48 | Bayswater Park Reconstruction-FEMA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-49 | Bayswater Park Recons of Maint. & Operations-FEMA | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-49 | Bayswater Park Recons of Maint. & Operations-FEMA | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-49 | Bayswater Park Recons of Maint. & Operations-FEMA | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-49 | Bayswater Park Recons of Maint. & Operations-FEMA | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-49 | Bayswater Park Recons of Maint. & Operations-FEMA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-51 | Bayswater Park Public Rest Room Construction-FEMA | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-51 | Bayswater Park Public Rest Room Construction-FEMA | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-51 | Bayswater Park Public Rest Room Construction-FEMA | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-51 | Bayswater Park Public Rest Room Construction-FEMA | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-51 | Bayswater Park Public Rest Room Construction-FEMA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-52 | Beach 32nd Street Sport Field Conduit | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-52 | Beach 32nd Street Sport Field Conduit | 2 | DESIGN | Dec 2021 | Jun 2023 | Dec 2021 | Jun 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-52 | Beach 32nd Street Sport Field Conduit | 3 | BID/ REGISTER CONTRACT | Jun 2023 | Mar 2024 | Jun 2023 | Mar 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-52 | Beach 32nd Street Sport Field Conduit | 4 | CONSTRUCTION | Mar 2024 | Sep 2025 | Mar 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-52 | Beach 32nd Street Sport Field Conduit | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-53 | Flight 587 Memorial Plaza Conduit Reconstruction | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-53 | Flight 587 Memorial Plaza Conduit Reconstruction | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-53 | Flight 587 Memorial Plaza Conduit Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-53 | Flight 587 Memorial Plaza Conduit Reconstruction | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-53 | Flight 587 Memorial Plaza Conduit Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY6-08 | Asser Levy HMP (Hazard Mitigation Plan ) Funding | 1 | DEVELOP SCOPE | Dec 2012 | Feb 2013 | Dec 2012 | May 2013
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY6-08 | Asser Levy HMP (Hazard Mitigation Plan ) Funding | 2 | DESIGN | Mar 2013 | May 2013 | May 2013 | May 2015
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY6-08 | Asser Levy HMP (Hazard Mitigation Plan ) Funding | 3 | BID/ REGISTER CONTRACT | May 2013 | Aug 2013 | May 2015 | Feb 2016
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY6-08 | Asser Levy HMP (Hazard Mitigation Plan ) Funding | 4 | CONSTRUCTION | Aug 2013 | Aug 2014 | Feb 2016 | Feb 2018
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY6-08 | Asser Levy HMP (Hazard Mitigation Plan ) Funding | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2014 | Aug 2015 | Feb 2018 | Jun 2028
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SEQ-TREES | South East Queens Sewer Build-out Trees Restitution | 1 | DESIGN | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SEQ-TREES | South East Queens Sewer Build-out Trees Restitution | 2 | BID/ REGISTER CONTRACT | Dec 2019 | Jun 2020 | Dec 2019 | Jun 2020
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SEQ-TREES | South East Queens Sewer Build-out Trees Restitution | 3 | CONSTRUCTION | Jun 2020 | Jun 2029 | Jun 2020 | Jun 2029
20231026 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SEQ-TREES | South East Queens Sewer Build-out Trees Restitution | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2029 | Aug 2029 | Jun 2029 | Aug 2029
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BB05-02-A | GI - Cons of ROW Bioswales & Stormwwater GS in BB-005, Ph 2 | 1 | FINAL DESIGN | Jun 2019 | Dec 2020 | Jul 2019 | Jan 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BB05-02-A | GI - Cons of ROW Bioswales & Stormwwater GS in BB-005, Ph 2 | 2 | CONSTRUCTION TO 25% | Dec 2020 | Aug 2021 | Jan 2021 | Sep 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BB05-02-A | GI - Cons of ROW Bioswales & Stormwwater GS in BB-005, Ph 2 | 3 | CONSTRUCTION TO 50% | Aug 2021 | Mar 2022 | Sep 2021 | Apr 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BB05-02-A | GI - Cons of ROW Bioswales & Stormwwater GS in BB-005, Ph 2 | 4 | CONSTRUCTION TO 75% | Mar 2022 | Nov 2022 | Apr 2022 | Jul 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BB05-02-A | GI - Cons of ROW Bioswales & Stormwwater GS in BB-005, Ph 2 | 5 | PROJECT START | Mar 2022 | Nov 2022 | Jul 2026 | Jul 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BB05-02-A | GI - Cons of ROW Bioswales & Stormwwater GS in BB-005, Ph 2 | 6 | DESIGN START | Mar 2022 | Nov 2022 | Aug 2026 | Aug 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BB05-02-A | GI - Cons of ROW Bioswales & Stormwwater GS in BB-005, Ph 2 | 7 | DESIGN COMPLETION | Mar 2022 | Nov 2022 | Aug 2026 | Aug 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BB05-02-A | GI - Cons of ROW Bioswales & Stormwwater GS in BB-005, Ph 2 | 8 | CONSTRUCTION START | Mar 2022 | Nov 2022 | Aug 2026 | Aug 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BB05-02-A | GI - Cons of ROW Bioswales & Stormwwater GS in BB-005, Ph 2 | 9 | CONSTRUCTION COMPLETION | Mar 2022 | Nov 2022 | Aug 2026 | Aug 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-Q | Boro Based Jails New Queens Detention Facility DesignBuild | 1 | DEVELOP SCOPE | Sep 2021 | Nov 2021 | Sep 2021 | Nov 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-Q | Boro Based Jails New Queens Detention Facility DesignBuild | 2 | PRELIMINARY DESIGN | Nov 2021 | Mar 2022 | Nov 2021 | Mar 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-Q | Boro Based Jails New Queens Detention Facility DesignBuild | 3 | FINAL DESIGN | Mar 2022 | Sep 2022 | Mar 2022 | Sep 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-Q | Boro Based Jails New Queens Detention Facility DesignBuild | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-Q | Boro Based Jails New Queens Detention Facility DesignBuild | 5 | CONSTRUCTION TO 25% | Dec 2022 | Apr 2023 | Dec 2022 | Apr 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-Q | Boro Based Jails New Queens Detention Facility DesignBuild | 6 | CONSTRUCTION TO 50% | Apr 2023 | Aug 2023 | Apr 2023 | Aug 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-Q | Boro Based Jails New Queens Detention Facility DesignBuild | 7 | CONSTRUCTION TO 75% | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-Q | Boro Based Jails New Queens Detention Facility DesignBuild | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2023 | Mar 2024 | Dec 2023 | Mar 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-Q | Boro Based Jails New Queens Detention Facility DesignBuild | 9 | SUBSTANTIAL COMPLETION | Mar 2024 | May 2024 | Mar 2024 | May 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-Q | Boro Based Jails New Queens Detention Facility DesignBuild | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Jun 2029 | May 2024 | Jun 2029
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-QGAR | Borough Based Jails Queens Garage Design Build | 1 | DEVELOP SCOPE | Sep 2021 | Nov 2021 | Sep 2021 | Nov 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-QGAR | Borough Based Jails Queens Garage Design Build | 2 | PRELIMINARY DESIGN | Nov 2021 | Mar 2022 | Nov 2021 | Mar 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-QGAR | Borough Based Jails Queens Garage Design Build | 3 | FINAL DESIGN | Mar 2022 | Sep 2022 | Mar 2022 | Sep 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-QGAR | Borough Based Jails Queens Garage Design Build | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-QGAR | Borough Based Jails Queens Garage Design Build | 5 | CONSTRUCTION TO 25% | Dec 2022 | Apr 2023 | Dec 2022 | Apr 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-QGAR | Borough Based Jails Queens Garage Design Build | 6 | CONSTRUCTION TO 50% | Apr 2023 | Aug 2023 | Apr 2023 | Aug 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-QGAR | Borough Based Jails Queens Garage Design Build | 7 | CONSTRUCTION TO 75% | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-QGAR | Borough Based Jails Queens Garage Design Build | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2023 | Mar 2024 | Dec 2023 | Mar 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-QGAR | Borough Based Jails Queens Garage Design Build | 9 | SUBSTANTIAL COMPLETION | Mar 2024 | May 2024 | Mar 2024 | May 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-QGAR | Borough Based Jails Queens Garage Design Build | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Apr 2025 | May 2024 | Apr 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277ELV2 | 25-10 COURT HOUSE SQ.- ELEVATORS | 1 | PROJECT START | Dec 2014 | Dec 2014 | Jul 2012 | Jul 2012
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277ELV2 | 25-10 COURT HOUSE SQ.- ELEVATORS | 2 | DESIGN START | Dec 2014 | Dec 2014 | Jul 2012 | Jul 2012
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277ELV2 | 25-10 COURT HOUSE SQ.- ELEVATORS | 3 | DESIGN COMPLETION | Dec 2014 | Dec 2014 | Jul 2012 | Sep 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277ELV2 | 25-10 COURT HOUSE SQ.- ELEVATORS | 4 | CONSTRUCTION START | Dec 2014 | Dec 2014 | Sep 2017 | Feb 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277ELV2 | 25-10 COURT HOUSE SQ.- ELEVATORS | 5 | CONSTRUCTION COMPLETION | Dec 2014 | Dec 2014 | Feb 2020 | Jun 2032
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277FA | 25-10 COURT HOUSE SQ.- FIRE ALARM SYSTEM | 1 | DEVELOP SCOPE | Sep 2007 | Nov 2007 | Dec 2019 | Feb 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277FA | 25-10 COURT HOUSE SQ.- FIRE ALARM SYSTEM | 2 | PRELIMINARY DESIGN | Nov 2007 | Mar 2008 | Feb 2021 | Jul 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277FA | 25-10 COURT HOUSE SQ.- FIRE ALARM SYSTEM | 3 | FINAL DESIGN | Mar 2008 | Sep 2008 | Jul 2021 | Oct 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277FA | 25-10 COURT HOUSE SQ.- FIRE ALARM SYSTEM | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2008 | Dec 2008 | Oct 2022 | Oct 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277FA | 25-10 COURT HOUSE SQ.- FIRE ALARM SYSTEM | 5 | CONSTRUCTION TO 25% | Dec 2008 | Apr 2009 | Oct 2023 | Feb 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277FA | 25-10 COURT HOUSE SQ.- FIRE ALARM SYSTEM | 6 | CONSTRUCTION TO 50% | Apr 2009 | Aug 2009 | Feb 2024 | Jun 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277FA | 25-10 COURT HOUSE SQ.- FIRE ALARM SYSTEM | 7 | CONSTRUCTION TO 75% | Aug 2009 | Dec 2009 | Jun 2024 | Oct 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277FA | 25-10 COURT HOUSE SQ.- FIRE ALARM SYSTEM | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2009 | Mar 2010 | Oct 2024 | Jan 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277FA | 25-10 COURT HOUSE SQ.- FIRE ALARM SYSTEM | 9 | SUBSTANTIAL COMPLETION | Mar 2010 | May 2010 | Jan 2025 | Oct 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277FA | 25-10 COURT HOUSE SQ.- FIRE ALARM SYSTEM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2010 | Jun 2010 | Oct 2025 | Oct 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296ELEC | 125-01 QUEENS BLVD - ELECTRICAL, FA, SPRINKLER UPGRADES | 1 | DEVELOP SCOPE | Jan 2018 | Mar 2018 | Jan 2018 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296ELEC | 125-01 QUEENS BLVD - ELECTRICAL, FA, SPRINKLER UPGRADES | 2 | PRELIMINARY DESIGN | Apr 2018 | Jul 2018 | Apr 2018 | Jul 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296ELEC | 125-01 QUEENS BLVD - ELECTRICAL, FA, SPRINKLER UPGRADES | 3 | FINAL DESIGN | Jul 2018 | Jan 2019 | Jul 2018 | Jan 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296ELEC | 125-01 QUEENS BLVD - ELECTRICAL, FA, SPRINKLER UPGRADES | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2019 | Apr 2019 | Jan 2019 | Apr 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296ELEC | 125-01 QUEENS BLVD - ELECTRICAL, FA, SPRINKLER UPGRADES | 5 | CONSTRUCTION TO 25% | Apr 2019 | Aug 2019 | Apr 2019 | Feb 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296ELEC | 125-01 QUEENS BLVD - ELECTRICAL, FA, SPRINKLER UPGRADES | 6 | CONSTRUCTION TO 50% | Aug 2019 | Dec 2019 | Feb 2022 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296ELEC | 125-01 QUEENS BLVD - ELECTRICAL, FA, SPRINKLER UPGRADES | 7 | CONSTRUCTION TO 75% | Dec 2019 | Apr 2020 | Jun 2022 | Oct 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296ELEC | 125-01 QUEENS BLVD - ELECTRICAL, FA, SPRINKLER UPGRADES | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2020 | Jul 2020 | Oct 2022 | Jan 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296ELEC | 125-01 QUEENS BLVD - ELECTRICAL, FA, SPRINKLER UPGRADES | 9 | SUBSTANTIAL COMPLETION | Jul 2020 | Sep 2020 | Jan 2026 | Jun 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296ELEC | 125-01 QUEENS BLVD - ELECTRICAL, FA, SPRINKLER UPGRADES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Oct 2020 | Jul 2026 | Mar 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296RF | 125-01 QUEENS BLVD.- ROOF | 1 | PROJECT START | Mar 2018 | Mar 2018 | Mar 2018 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296RF | 125-01 QUEENS BLVD.- ROOF | 2 | DESIGN START | Mar 2018 | Mar 2018 | Mar 2018 | Mar 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296RF | 125-01 QUEENS BLVD.- ROOF | 3 | DESIGN COMPLETION | Mar 2018 | Mar 2018 | Mar 2019 | Apr 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296RF | 125-01 QUEENS BLVD.- ROOF | 4 | CONSTRUCTION START | Mar 2018 | Mar 2018 | May 2021 | Dec 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296RF | 125-01 QUEENS BLVD.- ROOF | 5 | CONSTRUCTION COMPLETION | Mar 2018 | Mar 2018 | Dec 2021 | Jun 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299EXT2 | 89-17 SUTPHIN BLVD.- PLAZA/SIDEWALK RECONSTRUCTION | 1 | DEVELOP SCOPE | Mar 2019 | May 2019 | Mar 2019 | May 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299EXT2 | 89-17 SUTPHIN BLVD.- PLAZA/SIDEWALK RECONSTRUCTION | 2 | PRELIMINARY DESIGN | May 2019 | Sep 2019 | May 2019 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299EXT2 | 89-17 SUTPHIN BLVD.- PLAZA/SIDEWALK RECONSTRUCTION | 3 | FINAL DESIGN | Sep 2019 | Mar 2020 | Jun 2022 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299EXT2 | 89-17 SUTPHIN BLVD.- PLAZA/SIDEWALK RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Jun 2020 | Jun 2022 | Sep 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299EXT2 | 89-17 SUTPHIN BLVD.- PLAZA/SIDEWALK RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | Jun 2020 | Oct 2020 | Sep 2022 | Jan 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299EXT2 | 89-17 SUTPHIN BLVD.- PLAZA/SIDEWALK RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | Oct 2020 | Feb 2021 | Mar 2023 | Jul 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299EXT2 | 89-17 SUTPHIN BLVD.- PLAZA/SIDEWALK RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | Feb 2021 | Jun 2021 | Jul 2023 | Nov 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299EXT2 | 89-17 SUTPHIN BLVD.- PLAZA/SIDEWALK RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2021 | Sep 2021 | Nov 2023 | Nov 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299EXT2 | 89-17 SUTPHIN BLVD.- PLAZA/SIDEWALK RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | Sep 2021 | Nov 2021 | Nov 2023 | Nov 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299EXT2 | 89-17 SUTPHIN BLVD.- PLAZA/SIDEWALK RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2021 | Dec 2021 | Nov 2023 | Nov 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299FIRE | 89-17 SUTPHIN BLVD - FIRE ALARM DESIGN & REPLACEMENT | 1 | DEVELOP SCOPE | Jun 2019 | Aug 2019 | Jun 2019 | Aug 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299FIRE | 89-17 SUTPHIN BLVD - FIRE ALARM DESIGN & REPLACEMENT | 2 | PRELIMINARY DESIGN | Aug 2019 | Dec 2019 | Aug 2019 | Dec 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299FIRE | 89-17 SUTPHIN BLVD - FIRE ALARM DESIGN & REPLACEMENT | 3 | FINAL DESIGN | Dec 2019 | Jun 2020 | Dec 2019 | Jun 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299FIRE | 89-17 SUTPHIN BLVD - FIRE ALARM DESIGN & REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299FIRE | 89-17 SUTPHIN BLVD - FIRE ALARM DESIGN & REPLACEMENT | 5 | CONSTRUCTION TO 25% | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299FIRE | 89-17 SUTPHIN BLVD - FIRE ALARM DESIGN & REPLACEMENT | 6 | CONSTRUCTION TO 50% | Jan 2021 | May 2021 | Jan 2021 | May 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299FIRE | 89-17 SUTPHIN BLVD - FIRE ALARM DESIGN & REPLACEMENT | 7 | CONSTRUCTION TO 75% | May 2021 | Sep 2021 | May 2021 | Sep 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299FIRE | 89-17 SUTPHIN BLVD - FIRE ALARM DESIGN & REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Dec 2021 | Sep 2024 | Dec 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299FIRE | 89-17 SUTPHIN BLVD - FIRE ALARM DESIGN & REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | Dec 2021 | Feb 2022 | Dec 2024 | Feb 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299FIRE | 89-17 SUTPHIN BLVD - FIRE ALARM DESIGN & REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2022 | Mar 2022 | Feb 2025 | Mar 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CS-NC-BAF | BORDEN AVENUE PUMP STATION FORCE MAIN | 1 | DEVELOP SCOPE | Jun 2022 | Feb 2023 | Jun 2022 | Feb 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CS-NC-BAF | BORDEN AVENUE PUMP STATION FORCE MAIN | 2 | PRELIMINARY DESIGN | Feb 2023 | Feb 2024 | Feb 2023 | Feb 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CS-NC-BAF | BORDEN AVENUE PUMP STATION FORCE MAIN | 3 | FINAL DESIGN | Feb 2024 | Aug 2025 | Feb 2024 | Aug 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CS-NC-BAF | BORDEN AVENUE PUMP STATION FORCE MAIN | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2025 | May 2026 | Aug 2025 | May 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CS-NC-BAF | BORDEN AVENUE PUMP STATION FORCE MAIN | 5 | CONSTRUCTION TO 25% | May 2026 | May 2027 | May 2026 | May 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CS-NC-BAF | BORDEN AVENUE PUMP STATION FORCE MAIN | 6 | CONSTRUCTION TO 50% | May 2027 | Apr 2028 | May 2027 | Apr 2028
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CS-NC-BAF | BORDEN AVENUE PUMP STATION FORCE MAIN | 7 | CONSTRUCTION TO 75% | Apr 2028 | Apr 2029 | Apr 2028 | Apr 2029
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CS-NC-BAF | BORDEN AVENUE PUMP STATION FORCE MAIN | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2029 | Jan 2030 | Apr 2029 | Jan 2030
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CS-NC-BAF | BORDEN AVENUE PUMP STATION FORCE MAIN | 9 | SUBSTANTIAL COMPLETION | Jan 2030 | Jul 2030 | Jan 2030 | Jul 2030
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CS-NC-BAF | BORDEN AVENUE PUMP STATION FORCE MAIN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2030 | Oct 2030 | Jul 2030 | Oct 2030
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ01 | Southeast Queens - DOT Priority Grids Group 1 (SEQPGRD1) | 1 | DEVELOP SCOPE | Mar 2019 | May 2019 | Mar 2019 | May 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ01 | Southeast Queens - DOT Priority Grids Group 1 (SEQPGRD1) | 2 | PRELIMINARY DESIGN | May 2019 | Sep 2019 | May 2019 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ01 | Southeast Queens - DOT Priority Grids Group 1 (SEQPGRD1) | 3 | FINAL DESIGN | Sep 2019 | Mar 2020 | Sep 2019 | Mar 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ01 | Southeast Queens - DOT Priority Grids Group 1 (SEQPGRD1) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Jun 2020 | Mar 2020 | Jun 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ01 | Southeast Queens - DOT Priority Grids Group 1 (SEQPGRD1) | 5 | CONSTRUCTION TO 25% | Jun 2020 | Oct 2020 | Jun 2020 | Oct 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ01 | Southeast Queens - DOT Priority Grids Group 1 (SEQPGRD1) | 6 | CONSTRUCTION TO 50% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ01 | Southeast Queens - DOT Priority Grids Group 1 (SEQPGRD1) | 7 | CONSTRUCTION TO 75% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ01 | Southeast Queens - DOT Priority Grids Group 1 (SEQPGRD1) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ01 | Southeast Queens - DOT Priority Grids Group 1 (SEQPGRD1) | 9 | SUBSTANTIAL COMPLETION | Sep 2021 | Nov 2021 | Sep 2021 | Nov 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ01 | Southeast Queens - DOT Priority Grids Group 1 (SEQPGRD1) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2021 | Dec 2021 | Nov 2021 | Sep 2031
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ02 | Southeast Queens - DOT Priority Grids Group 2 (SEQPGRD2) | 1 | DEVELOP SCOPE | Mar 2020 | May 2020 | Mar 2020 | May 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ02 | Southeast Queens - DOT Priority Grids Group 2 (SEQPGRD2) | 2 | PRELIMINARY DESIGN | May 2020 | Sep 2020 | May 2020 | Sep 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ02 | Southeast Queens - DOT Priority Grids Group 2 (SEQPGRD2) | 3 | FINAL DESIGN | Sep 2020 | Mar 2021 | Sep 2020 | Mar 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ02 | Southeast Queens - DOT Priority Grids Group 2 (SEQPGRD2) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2021 | Jun 2021 | Mar 2021 | Jun 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ02 | Southeast Queens - DOT Priority Grids Group 2 (SEQPGRD2) | 5 | CONSTRUCTION TO 25% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ02 | Southeast Queens - DOT Priority Grids Group 2 (SEQPGRD2) | 6 | CONSTRUCTION TO 50% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ02 | Southeast Queens - DOT Priority Grids Group 2 (SEQPGRD2) | 7 | CONSTRUCTION TO 75% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ02 | Southeast Queens - DOT Priority Grids Group 2 (SEQPGRD2) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ02 | Southeast Queens - DOT Priority Grids Group 2 (SEQPGRD2) | 9 | SUBSTANTIAL COMPLETION | Sep 2022 | Nov 2022 | Sep 2022 | Nov 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ02 | Southeast Queens - DOT Priority Grids Group 2 (SEQPGRD2) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2022 | Dec 2022 | Nov 2022 | Nov 2031
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | 1 | PROJECT START | Mar 2018 | Mar 2018 | Mar 2018 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | 2 | DESIGN START | Mar 2018 | Mar 2018 | Mar 2018 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | 3 | DESIGN COMPLETION | Mar 2018 | Mar 2018 | Mar 2018 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | 4 | CONSTRUCTION START | Mar 2018 | Mar 2018 | Mar 2018 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | 5 | CONSTRUCTION COMPLETION | Mar 2018 | Mar 2018 | Mar 2018 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | 6 | DEVELOP SCOPE | Mar 2018 | Mar 2018 | Mar 2018 | Jun 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | 7 | PRELIMINARY DESIGN | Mar 2018 | Mar 2018 | Jun 2018 | Oct 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | 8 | FINAL DESIGN | Mar 2018 | Mar 2018 | Oct 2018 | Mar 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | 9 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Mar 2018 | Mar 2019 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | 10 | CONSTRUCTION TO 25% | Mar 2018 | Mar 2018 | Jun 2019 | Oct 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | 11 | CONSTRUCTION TO 50% | Mar 2018 | Mar 2018 | Oct 2019 | Feb 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | 12 | CONSTRUCTION TO 75% | Mar 2018 | Mar 2018 | Feb 2020 | Jun 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | 13 | ORIGINAL EQUIP & FURNISHING | Mar 2018 | Mar 2018 | Jun 2020 | Sep 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | 14 | SUBSTANTIAL COMPLETION | Mar 2018 | Mar 2018 | Sep 2020 | Nov 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | 15 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2018 | Mar 2018 | Nov 2020 | Jun 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | 1 | PROJECT START | Mar 2018 | Mar 2018 | Mar 2018 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | 2 | DESIGN START | Mar 2018 | Mar 2018 | Mar 2018 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | 3 | DESIGN COMPLETION | Mar 2018 | Mar 2018 | Mar 2018 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | 4 | CONSTRUCTION START | Mar 2018 | Mar 2018 | Mar 2018 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | 5 | CONSTRUCTION COMPLETION | Mar 2018 | Mar 2018 | Mar 2018 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | 6 | DEVELOP SCOPE | Mar 2018 | Mar 2018 | Mar 2018 | Jun 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | 7 | PRELIMINARY DESIGN | Mar 2018 | Mar 2018 | Jun 2018 | Oct 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | 8 | FINAL DESIGN | Mar 2018 | Mar 2018 | Oct 2018 | Mar 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | 9 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Mar 2018 | Mar 2019 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | 10 | CONSTRUCTION TO 25% | Mar 2018 | Mar 2018 | Jun 2019 | Oct 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | 11 | CONSTRUCTION TO 50% | Mar 2018 | Mar 2018 | Oct 2019 | Feb 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | 12 | CONSTRUCTION TO 75% | Mar 2018 | Mar 2018 | Feb 2020 | Jun 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | 13 | ORIGINAL EQUIP & FURNISHING | Mar 2018 | Mar 2018 | Jun 2020 | Sep 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | 14 | SUBSTANTIAL COMPLETION | Mar 2018 | Mar 2018 | Sep 2020 | Nov 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | 15 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2018 | Mar 2018 | Nov 2020 | Oct 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQN23 | Reconstruction of Existing Sewers, North Queens | 1 | DEVELOP SCOPE | Sep 2021 | Dec 2021 | Sep 2021 | Dec 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQN23 | Reconstruction of Existing Sewers, North Queens | 2 | PRELIMINARY DESIGN | Dec 2021 | Apr 2022 | Dec 2021 | Apr 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQN23 | Reconstruction of Existing Sewers, North Queens | 3 | FINAL DESIGN | Apr 2022 | Oct 2022 | Apr 2022 | Oct 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQN23 | Reconstruction of Existing Sewers, North Queens | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQN23 | Reconstruction of Existing Sewers, North Queens | 5 | CONSTRUCTION TO 25% | Jan 2023 | May 2023 | Jan 2023 | May 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQN23 | Reconstruction of Existing Sewers, North Queens | 6 | CONSTRUCTION TO 50% | May 2023 | Sep 2023 | May 2023 | Sep 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQN23 | Reconstruction of Existing Sewers, North Queens | 7 | CONSTRUCTION TO 75% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQN23 | Reconstruction of Existing Sewers, North Queens | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2024 | Apr 2024 | Jan 2024 | Apr 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQN23 | Reconstruction of Existing Sewers, North Queens | 9 | SUBSTANTIAL COMPLETION | Apr 2024 | Jun 2024 | Apr 2024 | Jun 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQN23 | Reconstruction of Existing Sewers, North Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2024 | Jul 2024 | Jun 2024 | Jul 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQN24 | Reconstruction of Existing Sewers, North Queens. | 1 | DEVELOP SCOPE | Jun 2024 | Aug 2024 | Jun 2024 | Aug 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQN24 | Reconstruction of Existing Sewers, North Queens. | 2 | PRELIMINARY DESIGN | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQN24 | Reconstruction of Existing Sewers, North Queens. | 3 | FINAL DESIGN | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQN24 | Reconstruction of Existing Sewers, North Queens. | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQN24 | Reconstruction of Existing Sewers, North Queens. | 5 | CONSTRUCTION TO 25% | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQN24 | Reconstruction of Existing Sewers, North Queens. | 6 | CONSTRUCTION TO 50% | Jan 2026 | May 2026 | Jan 2026 | May 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQN24 | Reconstruction of Existing Sewers, North Queens. | 7 | CONSTRUCTION TO 75% | May 2026 | Sep 2026 | May 2026 | Sep 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQN24 | Reconstruction of Existing Sewers, North Queens. | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2026 | Dec 2026 | Sep 2026 | Dec 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQN24 | Reconstruction of Existing Sewers, North Queens. | 9 | SUBSTANTIAL COMPLETION | Dec 2026 | Feb 2027 | Dec 2026 | Feb 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQN24 | Reconstruction of Existing Sewers, North Queens. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2027 | Mar 2027 | Feb 2027 | Mar 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQS23 | Reconstruction of Existing Sewers, South Queens | 1 | DEVELOP SCOPE | Sep 2021 | Dec 2021 | Sep 2021 | Dec 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQS23 | Reconstruction of Existing Sewers, South Queens | 2 | PRELIMINARY DESIGN | Dec 2021 | Apr 2022 | Dec 2021 | Apr 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQS23 | Reconstruction of Existing Sewers, South Queens | 3 | FINAL DESIGN | Apr 2022 | Oct 2022 | Apr 2022 | Oct 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQS23 | Reconstruction of Existing Sewers, South Queens | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQS23 | Reconstruction of Existing Sewers, South Queens | 5 | CONSTRUCTION TO 25% | Jan 2023 | May 2023 | Jan 2023 | May 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQS23 | Reconstruction of Existing Sewers, South Queens | 6 | CONSTRUCTION TO 50% | May 2023 | Sep 2023 | May 2023 | Sep 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQS23 | Reconstruction of Existing Sewers, South Queens | 7 | CONSTRUCTION TO 75% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQS23 | Reconstruction of Existing Sewers, South Queens | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2024 | Apr 2024 | Jan 2024 | Apr 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQS23 | Reconstruction of Existing Sewers, South Queens | 9 | SUBSTANTIAL COMPLETION | Apr 2024 | Jun 2024 | Apr 2024 | Jun 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQS23 | Reconstruction of Existing Sewers, South Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2024 | Jul 2024 | Jun 2024 | Jul 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQS24 | Reconstruction of Existing Sewers, South Queens | 1 | DEVELOP SCOPE | Jun 2024 | Aug 2024 | Jun 2024 | Aug 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQS24 | Reconstruction of Existing Sewers, South Queens | 2 | PRELIMINARY DESIGN | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQS24 | Reconstruction of Existing Sewers, South Queens | 3 | FINAL DESIGN | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQS24 | Reconstruction of Existing Sewers, South Queens | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQS24 | Reconstruction of Existing Sewers, South Queens | 5 | CONSTRUCTION TO 25% | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQS24 | Reconstruction of Existing Sewers, South Queens | 6 | CONSTRUCTION TO 50% | Jan 2026 | May 2026 | Jan 2026 | May 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQS24 | Reconstruction of Existing Sewers, South Queens | 7 | CONSTRUCTION TO 75% | May 2026 | Sep 2026 | May 2026 | Sep 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQS24 | Reconstruction of Existing Sewers, South Queens | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2026 | Dec 2026 | Sep 2026 | Dec 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQS24 | Reconstruction of Existing Sewers, South Queens | 9 | SUBSTANTIAL COMPLETION | Dec 2026 | Feb 2027 | Dec 2026 | Feb 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQS24 | Reconstruction of Existing Sewers, South Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2027 | Mar 2027 | Feb 2027 | Mar 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EC268 | NEW FIREHOUSE - EC268 | 1 | DESIGN | Jun 2018 | Sep 2018 | Oct 2019 | Jul 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EC268 | NEW FIREHOUSE - EC268 | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2018 | Jun 2019 | Jul 2022 | Apr 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EC268 | NEW FIREHOUSE - EC268 | 3 | CONSTRUCTION | Jun 2019 | Jul 2020 | Apr 2023 | May 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EC268 | NEW FIREHOUSE - EC268 | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2020 | Aug 2020 | May 2024 | Jun 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EC268 | NEW FIREHOUSE - EC268 | 5 | SUBSTANTIAL COMPLETION | Aug 2020 | Oct 2020 | Jun 2024 | Aug 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EC268 | NEW FIREHOUSE - EC268 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2020 | Dec 2020 | Aug 2024 | Aug 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F204INFRA | Fort Totten Infrastructure Upgrade | 1 | PROJECT START | Jan 2020 | Jun 2020 | Jan 2020 | Jun 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F204INFRA | Fort Totten Infrastructure Upgrade | 2 | DESIGN START | Jun 2020 | Jan 2021 | Jun 2020 | Jan 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F204INFRA | Fort Totten Infrastructure Upgrade | 3 | DESIGN COMPLETION | Jan 2021 | Jan 2022 | Jan 2021 | Jan 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F204INFRA | Fort Totten Infrastructure Upgrade | 4 | CONSTRUCTION START | Jan 2022 | Dec 2022 | Jan 2022 | Dec 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F204INFRA | Fort Totten Infrastructure Upgrade | 5 | CONSTRUCTION COMPLETION | Dec 2022 | Nov 2024 | Dec 2022 | Nov 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3B | GI - CONS OF ROW GI IN JAMAICA BAY CSO AREAS JAM-03 & JAM-3A | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Sep 2015 | Dec 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3B | GI - CONS OF ROW GI IN JAMAICA BAY CSO AREAS JAM-03 & JAM-3A | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | Dec 2015 | Apr 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3B | GI - CONS OF ROW GI IN JAMAICA BAY CSO AREAS JAM-03 & JAM-3A | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Apr 2016 | Oct 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3B | GI - CONS OF ROW GI IN JAMAICA BAY CSO AREAS JAM-03 & JAM-3A | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Oct 2016 | Jan 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3B | GI - CONS OF ROW GI IN JAMAICA BAY CSO AREAS JAM-03 & JAM-3A | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jan 2017 | May 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3B | GI - CONS OF ROW GI IN JAMAICA BAY CSO AREAS JAM-03 & JAM-3A | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | May 2017 | Sep 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3B | GI - CONS OF ROW GI IN JAMAICA BAY CSO AREAS JAM-03 & JAM-3A | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Sep 2017 | Jan 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3B | GI - CONS OF ROW GI IN JAMAICA BAY CSO AREAS JAM-03 & JAM-3A | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jan 2018 | Apr 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3B | GI - CONS OF ROW GI IN JAMAICA BAY CSO AREAS JAM-03 & JAM-3A | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Apr 2018 | Jun 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3B | GI - CONS OF ROW GI IN JAMAICA BAY CSO AREAS JAM-03 & JAM-3A | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Jun 2018 | Mar 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1B | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH B | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Nov 2014 | May 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1B | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH B | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1B | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH B | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1B | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH B | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1B | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH B | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1B | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH B | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1B | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH B | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1B | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH B | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1B | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH B | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1B | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH B | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Jun 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GQTI03-23 | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GQTI03-23 | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GQTI03-23 | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO | 3 | FINAL DESIGN | Sep 2017 | Jun 2019 | Sep 2017 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GQTI03-23 | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GQTI03-23 | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Sep 2019 | Jul 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GQTI03-23 | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Jul 2020 | May 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GQTI03-23 | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | May 2021 | Mar 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GQTI03-23 | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Mar 2022 | Jan 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GQTI03-23 | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Jan 2023 | Nov 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GQTI03-23 | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Nov 2023 | Aug 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GQTI03-23 | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO | 11 | PROJECT START | Feb 2021 | Mar 2021 | Aug 2024 | Oct 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GQTI03-23 | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO | 12 | DESIGN START | Feb 2021 | Mar 2021 | Oct 2024 | Dec 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GQTI03-23 | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO | 13 | DESIGN COMPLETION | Feb 2021 | Mar 2021 | Dec 2024 | Feb 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GQTI03-23 | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO | 14 | CONSTRUCTION START | Feb 2021 | Mar 2021 | Feb 2025 | Jun 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GQTI03-23 | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO | 15 | CONSTRUCTION COMPLETION | Feb 2021 | Mar 2021 | Jun 2025 | Feb 2030
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED216S | PED BRIDGE - 216 ST (Q) | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Sep 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED216S | PED BRIDGE - 216 ST (Q) | 2 | PRELIMINARY DESIGN | Sep 2014 | Jan 2015 | Sep 2014 | Jan 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED216S | PED BRIDGE - 216 ST (Q) | 3 | FINAL DESIGN | Jan 2015 | Jul 2015 | Jan 2015 | Jul 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED216S | PED BRIDGE - 216 ST (Q) | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Oct 2015 | Jul 2015 | Oct 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED216S | PED BRIDGE - 216 ST (Q) | 5 | CONSTRUCTION TO 25% | Oct 2015 | Feb 2016 | Oct 2015 | Feb 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED216S | PED BRIDGE - 216 ST (Q) | 6 | CONSTRUCTION TO 50% | Feb 2016 | Jun 2016 | Feb 2016 | Jun 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED216S | PED BRIDGE - 216 ST (Q) | 7 | CONSTRUCTION TO 75% | Jun 2016 | Oct 2016 | Jun 2016 | Oct 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED216S | PED BRIDGE - 216 ST (Q) | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2016 | Jan 2017 | Oct 2016 | Jan 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED216S | PED BRIDGE - 216 ST (Q) | 9 | SUBSTANTIAL COMPLETION | Jan 2017 | Mar 2017 | Jan 2017 | Mar 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED216S | PED BRIDGE - 216 ST (Q) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Apr 2017 | Mar 2017 | Jun 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED800Q | PED BRIDGE - PORPOISE BR & TIDE GATE(SANDY4-30, 4-31)QED1062 | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED800Q | PED BRIDGE - PORPOISE BR & TIDE GATE(SANDY4-30, 4-31)QED1062 | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED800Q | PED BRIDGE - PORPOISE BR & TIDE GATE(SANDY4-30, 4-31)QED1062 | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED800Q | PED BRIDGE - PORPOISE BR & TIDE GATE(SANDY4-30, 4-31)QED1062 | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED800Q | PED BRIDGE - PORPOISE BR & TIDE GATE(SANDY4-30, 4-31)QED1062 | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED800Q | PED BRIDGE - PORPOISE BR & TIDE GATE(SANDY4-30, 4-31)QED1062 | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED800Q | PED BRIDGE - PORPOISE BR & TIDE GATE(SANDY4-30, 4-31)QED1062 | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED800Q | PED BRIDGE - PORPOISE BR & TIDE GATE(SANDY4-30, 4-31)QED1062 | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED800Q | PED BRIDGE - PORPOISE BR & TIDE GATE(SANDY4-30, 4-31)QED1062 | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED800Q | PED BRIDGE - PORPOISE BR & TIDE GATE(SANDY4-30, 4-31)QED1062 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Feb 2028
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SGFA | SPRINGFIELD GARDEN - FIRE ALARM SYSTEM UPGRADE | 1 | PROJECT START | Mar 2016 | Mar 2016 | Mar 2016 | Mar 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SGFA | SPRINGFIELD GARDEN - FIRE ALARM SYSTEM UPGRADE | 2 | DESIGN START | Apr 2016 | Jul 2016 | Apr 2016 | Jul 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SGFA | SPRINGFIELD GARDEN - FIRE ALARM SYSTEM UPGRADE | 3 | DESIGN COMPLETION | Jul 2016 | Jun 2017 | Jul 2016 | Jun 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SGFA | SPRINGFIELD GARDEN - FIRE ALARM SYSTEM UPGRADE | 4 | CONSTRUCTION START | Jul 2017 | Oct 2017 | Jul 2017 | Oct 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SGFA | SPRINGFIELD GARDEN - FIRE ALARM SYSTEM UPGRADE | 5 | CONSTRUCTION COMPLETION | Nov 2017 | Jun 2023 | Nov 2017 | Jun 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CORHC | Corona Health Center-Exterior Facade, Basement and Lobby | 1 | DESIGN | Jan 2016 | May 2017 | Jan 2016 | Jan 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CORHC | Corona Health Center-Exterior Facade, Basement and Lobby | 2 | CONSTRUCTION | May 2017 | May 2022 | Jan 2016 | Jan 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CORHC | Corona Health Center-Exterior Facade, Basement and Lobby | 3 | PUNCHLIST COMPLETE, JOB CLOSED | May 2022 | May 2022 | Jan 2017 | Jan 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CORHC | Corona Health Center-Exterior Facade, Basement and Lobby | 4 | DEVELOP SCOPE | May 2022 | May 2022 | Jan 2018 | Jan 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CORHC | Corona Health Center-Exterior Facade, Basement and Lobby | 5 | PRELIMINARY DESIGN | May 2022 | May 2022 | Jan 2019 | Jan 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CORHC | Corona Health Center-Exterior Facade, Basement and Lobby | 6 | FINAL DESIGN | May 2022 | May 2022 | Jan 2019 | Jan 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CORHC | Corona Health Center-Exterior Facade, Basement and Lobby | 7 | BID AWARD AND REGISTER CONTRCT | May 2022 | May 2022 | Jan 2019 | Jan 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CORHC | Corona Health Center-Exterior Facade, Basement and Lobby | 8 | CONSTRUCTION TO 25% | May 2022 | May 2022 | Jan 2019 | Jan 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CORHC | Corona Health Center-Exterior Facade, Basement and Lobby | 9 | CONSTRUCTION TO 50% | May 2022 | May 2022 | Jan 2019 | Jan 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CORHC | Corona Health Center-Exterior Facade, Basement and Lobby | 10 | CONSTRUCTION TO 75% | May 2022 | May 2022 | Jan 2019 | Jan 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CORHC | Corona Health Center-Exterior Facade, Basement and Lobby | 11 | ORIGINAL EQUIP & FURNISHING | May 2022 | May 2022 | Jan 2019 | Jan 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CORHC | Corona Health Center-Exterior Facade, Basement and Lobby | 12 | SUBSTANTIAL COMPLETION | May 2022 | May 2022 | Jan 2019 | Jan 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CORHC | Corona Health Center-Exterior Facade, Basement and Lobby | 13 | PUNCHLIST COMPLETE, JOB CLOSED | May 2022 | Jun 2022 | Jan 2019 | Jan 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HW2CR12C | CITYWIDE MILLING - QUEENS | 1 | DEVELOP SCOPE | Mar 2011 | May 2011 | Mar 2011 | May 2011
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HW2CR12C | CITYWIDE MILLING - QUEENS | 2 | PRELIMINARY DESIGN | Jun 2011 | Sep 2011 | Jun 2011 | Sep 2011
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HW2CR12C | CITYWIDE MILLING - QUEENS | 3 | FINAL DESIGN | Sep 2011 | Mar 2012 | Sep 2011 | Mar 2012
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HW2CR12C | CITYWIDE MILLING - QUEENS | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2012 | Jun 2012 | Mar 2012 | Jun 2012
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HW2CR12C | CITYWIDE MILLING - QUEENS | 5 | CONSTRUCTION TO 25% | Jun 2012 | Oct 2012 | Jun 2012 | Oct 2012
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HW2CR12C | CITYWIDE MILLING - QUEENS | 6 | CONSTRUCTION TO 50% | Oct 2012 | Feb 2013 | Oct 2012 | Feb 2013
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HW2CR12C | CITYWIDE MILLING - QUEENS | 7 | CONSTRUCTION TO 75% | Feb 2013 | Jun 2013 | Feb 2013 | Jun 2013
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HW2CR12C | CITYWIDE MILLING - QUEENS | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2013 | Sep 2013 | Jun 2013 | Sep 2013
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HW2CR12C | CITYWIDE MILLING - QUEENS | 9 | SUBSTANTIAL COMPLETION | Sep 2013 | Nov 2013 | Sep 2013 | Nov 2013
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HW2CR12C | CITYWIDE MILLING - QUEENS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2013 | Dec 2013 | Nov 2013 | Jan 2033
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPQN | SAFE ROUTES TO SCHOOLS- QUEENS | 1 | DEVELOP SCOPE | Jan 2018 | Mar 2018 | Jan 2018 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPQN | SAFE ROUTES TO SCHOOLS- QUEENS | 2 | PRELIMINARY DESIGN | Apr 2018 | Jul 2018 | Apr 2018 | Jul 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPQN | SAFE ROUTES TO SCHOOLS- QUEENS | 3 | FINAL DESIGN | Jul 2018 | Jan 2019 | Jul 2018 | Jan 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPQN | SAFE ROUTES TO SCHOOLS- QUEENS | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2019 | Jun 2021 | Jan 2019 | Jun 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPQN | SAFE ROUTES TO SCHOOLS- QUEENS | 5 | CONSTRUCTION TO 25% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPQN | SAFE ROUTES TO SCHOOLS- QUEENS | 6 | CONSTRUCTION TO 50% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPQN | SAFE ROUTES TO SCHOOLS- QUEENS | 7 | CONSTRUCTION TO 75% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPQN | SAFE ROUTES TO SCHOOLS- QUEENS | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPQN | SAFE ROUTES TO SCHOOLS- QUEENS | 9 | SUBSTANTIAL COMPLETION | Sep 2022 | Nov 2022 | Sep 2022 | Nov 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPQN | SAFE ROUTES TO SCHOOLS- QUEENS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2022 | Dec 2022 | Nov 2022 | Jun 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPQN | SAFE ROUTES TO SCHOOLS- QUEENS | 11 | PROJECT START | Nov 2022 | Dec 2022 | Jul 2024 | Jul 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPQN | SAFE ROUTES TO SCHOOLS- QUEENS | 12 | DESIGN START | Nov 2022 | Dec 2022 | Jul 2024 | Jul 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPQN | SAFE ROUTES TO SCHOOLS- QUEENS | 13 | DESIGN COMPLETION | Nov 2022 | Dec 2022 | Jul 2024 | Jul 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPQN | SAFE ROUTES TO SCHOOLS- QUEENS | 14 | CONSTRUCTION START | Nov 2022 | Dec 2022 | Jul 2024 | Jul 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPQN | SAFE ROUTES TO SCHOOLS- QUEENS | 15 | CONSTRUCTION COMPLETION | Nov 2022 | Dec 2022 | Jul 2024 | Jul 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10311 | 111th Street Malls (QED-1049 | 1 | DEVELOP SCOPE | Jun 2015 | Aug 2015 | Jun 2016 | Aug 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10311 | 111th Street Malls (QED-1049 | 2 | PRELIMINARY DESIGN | Aug 2015 | Dec 2015 | Aug 2016 | Dec 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10311 | 111th Street Malls (QED-1049 | 3 | FINAL DESIGN | Dec 2015 | Jun 2016 | Dec 2016 | Feb 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10311 | 111th Street Malls (QED-1049 | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2016 | Sep 2016 | Feb 2019 | Mar 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10311 | 111th Street Malls (QED-1049 | 5 | CONSTRUCTION TO 25% | Sep 2016 | Jan 2017 | Mar 2019 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10311 | 111th Street Malls (QED-1049 | 6 | CONSTRUCTION TO 50% | Jan 2017 | May 2017 | Jun 2019 | Oct 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10311 | 111th Street Malls (QED-1049 | 7 | CONSTRUCTION TO 75% | May 2017 | Sep 2017 | Oct 2019 | Feb 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10311 | 111th Street Malls (QED-1049 | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Dec 2017 | Feb 2020 | May 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10311 | 111th Street Malls (QED-1049 | 9 | SUBSTANTIAL COMPLETION | Dec 2017 | Feb 2018 | May 2020 | Jul 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10311 | 111th Street Malls (QED-1049 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2018 | Mar 2018 | Jul 2020 | Sep 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWHARPADM | Harper Street Administration Building Reconstruction DB | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2021 | Sep 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWHARPADM | Harper Street Administration Building Reconstruction DB | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2021 | Jan 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWHARPADM | Harper Street Administration Building Reconstruction DB | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2022 | Jul 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWHARPADM | Harper Street Administration Building Reconstruction DB | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2022 | Oct 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWHARPADM | Harper Street Administration Building Reconstruction DB | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2022 | Feb 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWHARPADM | Harper Street Administration Building Reconstruction DB | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2023 | Jun 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWHARPADM | Harper Street Administration Building Reconstruction DB | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2023 | Oct 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWHARPADM | Harper Street Administration Building Reconstruction DB | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2023 | Jan 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWHARPADM | Harper Street Administration Building Reconstruction DB | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2024 | Mar 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWHARPADM | Harper Street Administration Building Reconstruction DB | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2024 | Apr 2029
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWHARPER | Reconstruction of Harper Street Asphalt Plant - Construction | 1 | PROJECT START | Jun 2017 | Jun 2017 | Jun 2017 | Jun 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWHARPER | Reconstruction of Harper Street Asphalt Plant - Construction | 2 | DESIGN START | Jun 2017 | Jun 2017 | Jun 2017 | Apr 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWHARPER | Reconstruction of Harper Street Asphalt Plant - Construction | 3 | DESIGN COMPLETION | Jun 2017 | Jun 2017 | Apr 2019 | Aug 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWHARPER | Reconstruction of Harper Street Asphalt Plant - Construction | 4 | CONSTRUCTION START | Jun 2017 | Jun 2017 | Aug 2021 | Apr 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWHARPER | Reconstruction of Harper Street Asphalt Plant - Construction | 5 | CONSTRUCTION COMPLETION | Jun 2017 | Jul 2020 | Apr 2022 | Aug 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPMWBEQ | Installation of Standard Pedestrian Ramps - MWBE | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPMWBEQ | Installation of Standard Pedestrian Ramps - MWBE | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPMWBEQ | Installation of Standard Pedestrian Ramps - MWBE | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPMWBEQ | Installation of Standard Pedestrian Ramps - MWBE | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPMWBEQ | Installation of Standard Pedestrian Ramps - MWBE | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPMWBEQ | Installation of Standard Pedestrian Ramps - MWBE | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPMWBEQ | Installation of Standard Pedestrian Ramps - MWBE | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPMWBEQ | Installation of Standard Pedestrian Ramps - MWBE | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPMWBEQ | Installation of Standard Pedestrian Ramps - MWBE | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPMWBEQ | Installation of Standard Pedestrian Ramps - MWBE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q2 | Pedestrian Ramp Rehabilitation - Queens | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2017 | Sep 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q2 | Pedestrian Ramp Rehabilitation - Queens | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2017 | Jan 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q2 | Pedestrian Ramp Rehabilitation - Queens | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jan 2018 | Jul 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q2 | Pedestrian Ramp Rehabilitation - Queens | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2018 | Oct 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q2 | Pedestrian Ramp Rehabilitation - Queens | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q2 | Pedestrian Ramp Rehabilitation - Queens | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q2 | Pedestrian Ramp Rehabilitation - Queens | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jun 2019 | Oct 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q2 | Pedestrian Ramp Rehabilitation - Queens | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Oct 2019 | Jan 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q2 | Pedestrian Ramp Rehabilitation - Queens | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jan 2020 | Mar 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q2 | Pedestrian Ramp Rehabilitation - Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Mar 2020 | Sep 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20QC | Non-Standard Upgrades Ped Ramp - Queens | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20QC | Non-Standard Upgrades Ped Ramp - Queens | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20QC | Non-Standard Upgrades Ped Ramp - Queens | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20QC | Non-Standard Upgrades Ped Ramp - Queens | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20QC | Non-Standard Upgrades Ped Ramp - Queens | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20QC | Non-Standard Upgrades Ped Ramp - Queens | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20QC | Non-Standard Upgrades Ped Ramp - Queens | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20QC | Non-Standard Upgrades Ped Ramp - Queens | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20QC | Non-Standard Upgrades Ped Ramp - Queens | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20QC | Non-Standard Upgrades Ped Ramp - Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Jun 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21Q1 | Rehabilitation of Standard Ped Ramps - Queens | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21Q1 | Rehabilitation of Standard Ped Ramps - Queens | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21Q1 | Rehabilitation of Standard Ped Ramps - Queens | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21Q1 | Rehabilitation of Standard Ped Ramps - Queens | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21Q1 | Rehabilitation of Standard Ped Ramps - Queens | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21Q1 | Rehabilitation of Standard Ped Ramps - Queens | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21Q1 | Rehabilitation of Standard Ped Ramps - Queens | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21Q1 | Rehabilitation of Standard Ped Ramps - Queens | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21Q1 | Rehabilitation of Standard Ped Ramps - Queens | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21Q1 | Rehabilitation of Standard Ped Ramps - Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21Q1 | Rehabilitation of Standard Ped Ramps - Queens | 11 | PROJECT START | Mar 2024 | Apr 2024 | Apr 2024 | Apr 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21Q1 | Rehabilitation of Standard Ped Ramps - Queens | 12 | DESIGN START | Mar 2024 | Apr 2024 | Apr 2024 | Apr 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21Q1 | Rehabilitation of Standard Ped Ramps - Queens | 13 | DESIGN COMPLETION | Mar 2024 | Apr 2024 | Apr 2024 | Apr 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21Q1 | Rehabilitation of Standard Ped Ramps - Queens | 14 | CONSTRUCTION START | Mar 2024 | Apr 2024 | Apr 2024 | Apr 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21Q1 | Rehabilitation of Standard Ped Ramps - Queens | 15 | CONSTRUCTION COMPLETION | Mar 2024 | Apr 2024 | Apr 2024 | Apr 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22Q1 | Rehabilitation of Standard Ped Ramps - Queens | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22Q1 | Rehabilitation of Standard Ped Ramps - Queens | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22Q1 | Rehabilitation of Standard Ped Ramps - Queens | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22Q1 | Rehabilitation of Standard Ped Ramps - Queens | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22Q1 | Rehabilitation of Standard Ped Ramps - Queens | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22Q1 | Rehabilitation of Standard Ped Ramps - Queens | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22Q1 | Rehabilitation of Standard Ped Ramps - Queens | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22Q1 | Rehabilitation of Standard Ped Ramps - Queens | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22Q1 | Rehabilitation of Standard Ped Ramps - Queens | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22Q1 | Rehabilitation of Standard Ped Ramps - Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2033
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23Q1 | Standard Upgrades Ped Ramps - Queens | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23Q1 | Standard Upgrades Ped Ramps - Queens | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23Q1 | Standard Upgrades Ped Ramps - Queens | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23Q1 | Standard Upgrades Ped Ramps - Queens | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23Q1 | Standard Upgrades Ped Ramps - Queens | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23Q1 | Standard Upgrades Ped Ramps - Queens | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23Q1 | Standard Upgrades Ped Ramps - Queens | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23Q1 | Standard Upgrades Ped Ramps - Queens | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23Q1 | Standard Upgrades Ped Ramps - Queens | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR23Q1 | Standard Upgrades Ped Ramps - Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBB | Woodhaven Blvd SBS Phase B (QED-1040B) | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBB | Woodhaven Blvd SBS Phase B (QED-1040B) | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBB | Woodhaven Blvd SBS Phase B (QED-1040B) | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBB | Woodhaven Blvd SBS Phase B (QED-1040B) | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBB | Woodhaven Blvd SBS Phase B (QED-1040B) | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBB | Woodhaven Blvd SBS Phase B (QED-1040B) | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBB | Woodhaven Blvd SBS Phase B (QED-1040B) | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBB | Woodhaven Blvd SBS Phase B (QED-1040B) | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBB | Woodhaven Blvd SBS Phase B (QED-1040B) | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBB | Woodhaven Blvd SBS Phase B (QED-1040B) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Sep 2029
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1182B | Broad Channel Bulkheads - Phase II (SEQ200586) | 1 | DEVELOP SCOPE | Jun 2015 | Oct 2015 | Jun 2015 | Oct 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1182B | Broad Channel Bulkheads - Phase II (SEQ200586) | 2 | DESIGN START | Oct 2015 | Apr 2017 | Oct 2015 | Apr 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1182B | Broad Channel Bulkheads - Phase II (SEQ200586) | 3 | CONSTRUCTION START | Apr 2017 | Apr 2019 | Apr 2017 | Jul 2032
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1184A | James Court Roadway & Bulkhead, Queens (Joint Bid) | 1 | DEVELOP SCOPE | Feb 2011 | May 2013 | Feb 2011 | May 2013
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1184A | James Court Roadway & Bulkhead, Queens (Joint Bid) | 2 | PRELIMINARY DESIGN | May 2013 | May 2013 | May 2013 | May 2013
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1184A | James Court Roadway & Bulkhead, Queens (Joint Bid) | 3 | FINAL DESIGN | May 2013 | May 2013 | May 2013 | May 2013
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1184A | James Court Roadway & Bulkhead, Queens (Joint Bid) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2013 | Jun 2013 | Mar 2013 | Sep 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1184A | James Court Roadway & Bulkhead, Queens (Joint Bid) | 5 | CONSTRUCTION TO 25% | Jun 2013 | Jun 2013 | Sep 2018 | Sep 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1184A | James Court Roadway & Bulkhead, Queens (Joint Bid) | 6 | CONSTRUCTION TO 50% | Jun 2013 | Jun 2013 | Sep 2018 | Sep 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1184A | James Court Roadway & Bulkhead, Queens (Joint Bid) | 7 | CONSTRUCTION TO 75% | Jun 2013 | Jun 2013 | Sep 2018 | Sep 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1184A | James Court Roadway & Bulkhead, Queens (Joint Bid) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2013 | Jun 2013 | Sep 2018 | Sep 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1184A | James Court Roadway & Bulkhead, Queens (Joint Bid) | 9 | SUBSTANTIAL COMPLETION | Jun 2013 | Jun 2013 | Sep 2018 | Sep 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1184A | James Court Roadway & Bulkhead, Queens (Joint Bid) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2013 | Jul 2015 | Sep 2020 | Aug 2031
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1187 | Westbourne-Dunbar Roadways & Bulkheads (SAND1187, SEQ200595) | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2016 | Sep 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1187 | Westbourne-Dunbar Roadways & Bulkheads (SAND1187, SEQ200595) | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2016 | Jan 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1187 | Westbourne-Dunbar Roadways & Bulkheads (SAND1187, SEQ200595) | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jan 2017 | Jul 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1187 | Westbourne-Dunbar Roadways & Bulkheads (SAND1187, SEQ200595) | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2017 | Oct 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1187 | Westbourne-Dunbar Roadways & Bulkheads (SAND1187, SEQ200595) | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Oct 2017 | Feb 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1187 | Westbourne-Dunbar Roadways & Bulkheads (SAND1187, SEQ200595) | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Feb 2018 | Jun 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1187 | Westbourne-Dunbar Roadways & Bulkheads (SAND1187, SEQ200595) | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jun 2018 | Oct 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1187 | Westbourne-Dunbar Roadways & Bulkheads (SAND1187, SEQ200595) | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Oct 2018 | Jan 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1187 | Westbourne-Dunbar Roadways & Bulkheads (SAND1187, SEQ200595) | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jan 2019 | Mar 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1187 | Westbourne-Dunbar Roadways & Bulkheads (SAND1187, SEQ200595) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Mar 2019 | Sep 2029
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190A | Reconstruction of Queens Blvd Phase 1 (QED-1042A) | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190A | Reconstruction of Queens Blvd Phase 1 (QED-1042A) | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190A | Reconstruction of Queens Blvd Phase 1 (QED-1042A) | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190A | Reconstruction of Queens Blvd Phase 1 (QED-1042A) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190A | Reconstruction of Queens Blvd Phase 1 (QED-1042A) | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190A | Reconstruction of Queens Blvd Phase 1 (QED-1042A) | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190A | Reconstruction of Queens Blvd Phase 1 (QED-1042A) | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190A | Reconstruction of Queens Blvd Phase 1 (QED-1042A) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190A | Reconstruction of Queens Blvd Phase 1 (QED-1042A) | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190A | Reconstruction of Queens Blvd Phase 1 (QED-1042A) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Mar 2029
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190B | Reconstruction of Queens Blvd Phase 2( QED-1042B) | 1 | DEVELOP SCOPE | Mar 2016 | May 2016 | Mar 2016 | May 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190B | Reconstruction of Queens Blvd Phase 2( QED-1042B) | 2 | PRELIMINARY DESIGN | May 2016 | Sep 2016 | May 2016 | Sep 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190B | Reconstruction of Queens Blvd Phase 2( QED-1042B) | 3 | FINAL DESIGN | Sep 2016 | Mar 2017 | Sep 2016 | Mar 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190B | Reconstruction of Queens Blvd Phase 2( QED-1042B) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2017 | Jun 2017 | Mar 2017 | Jun 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190B | Reconstruction of Queens Blvd Phase 2( QED-1042B) | 5 | CONSTRUCTION TO 25% | Jun 2017 | Oct 2017 | Jun 2017 | Oct 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190B | Reconstruction of Queens Blvd Phase 2( QED-1042B) | 6 | CONSTRUCTION TO 50% | Oct 2017 | Feb 2018 | Oct 2017 | Feb 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190B | Reconstruction of Queens Blvd Phase 2( QED-1042B) | 7 | CONSTRUCTION TO 75% | Feb 2018 | Jun 2018 | Feb 2018 | Jun 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190B | Reconstruction of Queens Blvd Phase 2( QED-1042B) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190B | Reconstruction of Queens Blvd Phase 2( QED-1042B) | 9 | SUBSTANTIAL COMPLETION | Sep 2018 | Nov 2018 | Sep 2018 | Nov 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190B | Reconstruction of Queens Blvd Phase 2( QED-1042B) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2018 | Dec 2018 | Nov 2018 | Apr 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190B | Reconstruction of Queens Blvd Phase 2( QED-1042B) | 11 | PROJECT START | Nov 2018 | Dec 2018 | Apr 2026 | Apr 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190B | Reconstruction of Queens Blvd Phase 2( QED-1042B) | 12 | DESIGN START | Nov 2018 | Dec 2018 | Apr 2026 | Apr 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190B | Reconstruction of Queens Blvd Phase 2( QED-1042B) | 13 | DESIGN COMPLETION | Nov 2018 | Dec 2018 | Apr 2026 | Apr 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190B | Reconstruction of Queens Blvd Phase 2( QED-1042B) | 14 | CONSTRUCTION START | Nov 2018 | Dec 2018 | Apr 2026 | Apr 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190B | Reconstruction of Queens Blvd Phase 2( QED-1042B) | 15 | CONSTRUCTION COMPLETION | Nov 2018 | Dec 2018 | Apr 2026 | Apr 2031
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190-C | Reconstruction of Queens Blvd Phase 3, QED-1042C | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190-C | Reconstruction of Queens Blvd Phase 3, QED-1042C | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190-C | Reconstruction of Queens Blvd Phase 3, QED-1042C | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Nov 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190-C | Reconstruction of Queens Blvd Phase 3, QED-1042C | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Dec 2020 | Feb 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190-C | Reconstruction of Queens Blvd Phase 3, QED-1042C | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Mar 2021 | Jun 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190-C | Reconstruction of Queens Blvd Phase 3, QED-1042C | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Jun 2021 | Oct 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190-C | Reconstruction of Queens Blvd Phase 3, QED-1042C | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Oct 2021 | Feb 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190-C | Reconstruction of Queens Blvd Phase 3, QED-1042C | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Feb 2022 | May 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190-C | Reconstruction of Queens Blvd Phase 3, QED-1042C | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | May 2022 | Jul 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190-C | Reconstruction of Queens Blvd Phase 3, QED-1042C | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Jul 2022 | Jun 2029
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1193 | Union Turnpike Curb Repair | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Jun 2016 | Sep 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1193 | Union Turnpike Curb Repair | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Sep 2016 | Jan 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1193 | Union Turnpike Curb Repair | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Jan 2017 | Jul 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1193 | Union Turnpike Curb Repair | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Jul 2017 | Oct 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1193 | Union Turnpike Curb Repair | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Oct 2017 | Feb 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1193 | Union Turnpike Curb Repair | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Feb 2018 | Jun 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1193 | Union Turnpike Curb Repair | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1193 | Union Turnpike Curb Repair | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | Oct 2018 | Jan 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1193 | Union Turnpike Curb Repair | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Jan 2019 | Mar 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1193 | Union Turnpike Curb Repair | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Mar 2019 | Sep 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1195 | Colfax and Murdock Street Raising (SEQNS003) | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Jun 2018 | Sep 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1195 | Colfax and Murdock Street Raising (SEQNS003) | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Sep 2018 | Jan 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1195 | Colfax and Murdock Street Raising (SEQNS003) | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Jan 2019 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1195 | Colfax and Murdock Street Raising (SEQNS003) | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Sep 2019 | Jul 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1195 | Colfax and Murdock Street Raising (SEQNS003) | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Jul 2020 | Nov 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1195 | Colfax and Murdock Street Raising (SEQNS003) | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Nov 2020 | Mar 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1195 | Colfax and Murdock Street Raising (SEQNS003) | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Mar 2021 | Jul 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1195 | Colfax and Murdock Street Raising (SEQNS003) | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | Jul 2021 | Oct 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1195 | Colfax and Murdock Street Raising (SEQNS003) | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Oct 2021 | Apr 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1195 | Colfax and Murdock Street Raising (SEQNS003) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Apr 2025 | Nov 2031
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1196 | Cloudburst Project - St Albans (SEQ-SACBA) | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Oct 2020 | Aug 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1196 | Cloudburst Project - St Albans (SEQ-SACBA) | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Dec 2020 | Feb 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1196 | Cloudburst Project - St Albans (SEQ-SACBA) | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Feb 2022 | Dec 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1196 | Cloudburst Project - St Albans (SEQ-SACBA) | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Dec 2022 | May 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1196 | Cloudburst Project - St Albans (SEQ-SACBA) | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | May 2023 | Aug 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1196 | Cloudburst Project - St Albans (SEQ-SACBA) | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Aug 2023 | Nov 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1196 | Cloudburst Project - St Albans (SEQ-SACBA) | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Nov 2023 | Feb 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1196 | Cloudburst Project - St Albans (SEQ-SACBA) | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | Feb 2024 | May 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1196 | Cloudburst Project - St Albans (SEQ-SACBA) | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Feb 2024 | May 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1196 | Cloudburst Project - St Albans (SEQ-SACBA) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | May 2024 | Jun 2028
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1198 | Reconst. of Beach Channel Drive-Phase B Non Sandy(QED-1030B) | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2022 | Apr 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1198 | Reconst. of Beach Channel Drive-Phase B Non Sandy(QED-1030B) | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1198 | Reconst. of Beach Channel Drive-Phase B Non Sandy(QED-1030B) | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1198 | Reconst. of Beach Channel Drive-Phase B Non Sandy(QED-1030B) | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1198 | Reconst. of Beach Channel Drive-Phase B Non Sandy(QED-1030B) | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1198 | Reconst. of Beach Channel Drive-Phase B Non Sandy(QED-1030B) | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1198 | Reconst. of Beach Channel Drive-Phase B Non Sandy(QED-1030B) | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1198 | Reconst. of Beach Channel Drive-Phase B Non Sandy(QED-1030B) | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Jun 2022 | Mar 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1198 | Reconst. of Beach Channel Drive-Phase B Non Sandy(QED-1030B) | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Mar 2023 | Apr 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1198 | Reconst. of Beach Channel Drive-Phase B Non Sandy(QED-1030B) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | May 2023 | May 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1198 | Reconst. of Beach Channel Drive-Phase B Non Sandy(QED-1030B) | 11 | PROJECT START | Mar 2022 | Apr 2022 | May 2024 | May 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1198 | Reconst. of Beach Channel Drive-Phase B Non Sandy(QED-1030B) | 12 | DESIGN START | Mar 2022 | Apr 2022 | May 2024 | May 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1198 | Reconst. of Beach Channel Drive-Phase B Non Sandy(QED-1030B) | 13 | DESIGN COMPLETION | Mar 2022 | Apr 2022 | Jun 2024 | Jun 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1198 | Reconst. of Beach Channel Drive-Phase B Non Sandy(QED-1030B) | 14 | CONSTRUCTION START | Mar 2022 | Apr 2022 | Jun 2024 | Jun 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1198 | Reconst. of Beach Channel Drive-Phase B Non Sandy(QED-1030B) | 15 | CONSTRUCTION COMPLETION | Mar 2022 | Apr 2022 | Jun 2024 | Jun 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1201 | ASTORIA BLVD SAFETY IMPROVEMENTS | 1 | DESIGN | May 2021 | Oct 2023 | May 2021 | Oct 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1201 | ASTORIA BLVD SAFETY IMPROVEMENTS | 2 | CONSTRUCTION | May 2024 | Aug 2026 | May 2024 | Aug 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1201 | ASTORIA BLVD SAFETY IMPROVEMENTS | 3 | ORIGINAL EQUIP & FURNISHING | Aug 2026 | Aug 2026 | Aug 2026 | Aug 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1201 | ASTORIA BLVD SAFETY IMPROVEMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2026 | Nov 2026 | Aug 2026 | Nov 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1205 | Belt Parkway Guardrail at Sunrise Highway | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1205 | Belt Parkway Guardrail at Sunrise Highway | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1205 | Belt Parkway Guardrail at Sunrise Highway | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1205 | Belt Parkway Guardrail at Sunrise Highway | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1205 | Belt Parkway Guardrail at Sunrise Highway | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1205 | Belt Parkway Guardrail at Sunrise Highway | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1205 | Belt Parkway Guardrail at Sunrise Highway | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1205 | Belt Parkway Guardrail at Sunrise Highway | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1205 | Belt Parkway Guardrail at Sunrise Highway | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1205 | Belt Parkway Guardrail at Sunrise Highway | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ121B3 | RECONSTRUCTION OF SOUTH JAMAICA AREA (SEQ200562) | 1 | DEVELOP SCOPE | May 2005 | Aug 2005 | May 2005 | Aug 2005
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ121B3 | RECONSTRUCTION OF SOUTH JAMAICA AREA (SEQ200562) | 2 | PRELIMINARY DESIGN | Aug 2005 | Dec 2005 | Aug 2005 | Dec 2005
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ121B3 | RECONSTRUCTION OF SOUTH JAMAICA AREA (SEQ200562) | 3 | FINAL DESIGN | Dec 2005 | Jun 2006 | Dec 2005 | Jun 2006
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ121B3 | RECONSTRUCTION OF SOUTH JAMAICA AREA (SEQ200562) | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2006 | Sep 2006 | Jun 2006 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ121B3 | RECONSTRUCTION OF SOUTH JAMAICA AREA (SEQ200562) | 5 | CONSTRUCTION TO 25% | Sep 2006 | Jan 2007 | Jun 2022 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ121B3 | RECONSTRUCTION OF SOUTH JAMAICA AREA (SEQ200562) | 6 | CONSTRUCTION TO 50% | Jan 2007 | May 2007 | Jun 2022 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ121B3 | RECONSTRUCTION OF SOUTH JAMAICA AREA (SEQ200562) | 7 | CONSTRUCTION TO 75% | May 2007 | Sep 2007 | Jun 2022 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ121B3 | RECONSTRUCTION OF SOUTH JAMAICA AREA (SEQ200562) | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2007 | Dec 2007 | Jun 2022 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ121B3 | RECONSTRUCTION OF SOUTH JAMAICA AREA (SEQ200562) | 9 | SUBSTANTIAL COMPLETION | Dec 2007 | Feb 2008 | Jun 2022 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ121B3 | RECONSTRUCTION OF SOUTH JAMAICA AREA (SEQ200562) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2008 | Mar 2008 | Jun 2022 | Dec 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ200578 | SEQ - Foch Boulevard Safety Improvements (SEQ200578) | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ200578 | SEQ - Foch Boulevard Safety Improvements (SEQ200578) | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ200578 | SEQ - Foch Boulevard Safety Improvements (SEQ200578) | 3 | FINAL DESIGN | Sep 2017 | Oct 2018 | Sep 2017 | Oct 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ200578 | SEQ - Foch Boulevard Safety Improvements (SEQ200578) | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2018 | Jan 2019 | Oct 2018 | Jan 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ200578 | SEQ - Foch Boulevard Safety Improvements (SEQ200578) | 5 | CONSTRUCTION TO 25% | Jan 2019 | May 2019 | Jan 2019 | May 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ200578 | SEQ - Foch Boulevard Safety Improvements (SEQ200578) | 6 | CONSTRUCTION TO 50% | May 2019 | Sep 2019 | May 2019 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ200578 | SEQ - Foch Boulevard Safety Improvements (SEQ200578) | 7 | CONSTRUCTION TO 75% | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ200578 | SEQ - Foch Boulevard Safety Improvements (SEQ200578) | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2020 | Apr 2020 | Jan 2020 | Apr 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ200578 | SEQ - Foch Boulevard Safety Improvements (SEQ200578) | 9 | SUBSTANTIAL COMPLETION | Apr 2020 | Jun 2020 | Apr 2020 | Jun 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ200578 | SEQ - Foch Boulevard Safety Improvements (SEQ200578) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2020 | Jul 2020 | Jun 2020 | Jun 2035
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F2 | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 (SEQ200592) | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F2 | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 (SEQ200592) | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F2 | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 (SEQ200592) | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F2 | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 (SEQ200592) | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F2 | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 (SEQ200592) | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F2 | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 (SEQ200592) | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F2 | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 (SEQ200592) | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F2 | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 (SEQ200592) | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F2 | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 (SEQ200592) | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2023 | Mar 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F2 | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 (SEQ200592) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2023 | Apr 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F2 | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 (SEQ200592) | 11 | PROJECT START | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F2 | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 (SEQ200592) | 12 | DESIGN START | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F2 | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 (SEQ200592) | 13 | DESIGN COMPLETION | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F2 | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 (SEQ200592) | 14 | CONSTRUCTION START | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F2 | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 (SEQ200592) | 15 | CONSTRUCTION COMPLETION | Mar 2023 | Apr 2023 | Apr 2023 | Jun 2032
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ631B-3 | ALMEDA AV - PHASE III | 1 | DEVELOP SCOPE | Mar 2011 | Jun 2011 | Mar 2011 | Jun 2011
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ631B-3 | ALMEDA AV - PHASE III | 2 | PRELIMINARY DESIGN | Jun 2011 | Oct 2011 | Jun 2011 | Oct 2011
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ631B-3 | ALMEDA AV - PHASE III | 3 | FINAL DESIGN | Oct 2011 | Mar 2012 | Oct 2011 | Mar 2012
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ631B-3 | ALMEDA AV - PHASE III | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2012 | Jun 2012 | Mar 2022 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ631B-3 | ALMEDA AV - PHASE III | 5 | CONSTRUCTION TO 25% | Jun 2012 | Oct 2012 | Jun 2022 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ631B-3 | ALMEDA AV - PHASE III | 6 | CONSTRUCTION TO 50% | Oct 2012 | Feb 2013 | Jun 2022 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ631B-3 | ALMEDA AV - PHASE III | 7 | CONSTRUCTION TO 75% | Feb 2013 | Jun 2013 | Jun 2022 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ631B-3 | ALMEDA AV - PHASE III | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2013 | Sep 2013 | Jun 2022 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ631B-3 | ALMEDA AV - PHASE III | 9 | SUBSTANTIAL COMPLETION | Sep 2013 | Nov 2013 | Jun 2022 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ631B-3 | ALMEDA AV - PHASE III | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2013 | Dec 2013 | Jan 2024 | Jun 2035
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ662G | Springfield Gardens Phase V (SE-862) | 1 | DEVELOP SCOPE | Jun 2014 | Aug 2014 | Mar 2020 | May 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ662G | Springfield Gardens Phase V (SE-862) | 2 | PRELIMINARY DESIGN | Aug 2014 | Dec 2014 | May 2020 | Sep 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ662G | Springfield Gardens Phase V (SE-862) | 3 | FINAL DESIGN | Dec 2014 | Jun 2015 | Sep 2020 | Mar 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ662G | Springfield Gardens Phase V (SE-862) | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2015 | Sep 2015 | Mar 2021 | Jun 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ662G | Springfield Gardens Phase V (SE-862) | 5 | CONSTRUCTION TO 25% | Sep 2015 | Jan 2016 | Jun 2021 | Oct 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ662G | Springfield Gardens Phase V (SE-862) | 6 | CONSTRUCTION TO 50% | Jan 2016 | May 2016 | Oct 2021 | Feb 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ662G | Springfield Gardens Phase V (SE-862) | 7 | CONSTRUCTION TO 75% | May 2016 | Sep 2016 | Feb 2022 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ662G | Springfield Gardens Phase V (SE-862) | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Dec 2016 | Jun 2022 | Sep 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ662G | Springfield Gardens Phase V (SE-862) | 9 | SUBSTANTIAL COMPLETION | Dec 2016 | Feb 2017 | Sep 2022 | Nov 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ662G | Springfield Gardens Phase V (SE-862) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2017 | Mar 2017 | Nov 2022 | Jun 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ724B | Recon of Streets in Brookville-Edgewood Triangle (SEQ200519) | 1 | DEVELOP SCOPE | Aug 2003 | Nov 2003 | Aug 2003 | Nov 2003
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ724B | Recon of Streets in Brookville-Edgewood Triangle (SEQ200519) | 2 | PRELIMINARY DESIGN | Nov 2003 | Mar 2004 | Nov 2003 | Mar 2004
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ724B | Recon of Streets in Brookville-Edgewood Triangle (SEQ200519) | 3 | FINAL DESIGN | Mar 2004 | Sep 2004 | Mar 2004 | Mar 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ724B | Recon of Streets in Brookville-Edgewood Triangle (SEQ200519) | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2004 | Dec 2004 | Mar 2017 | Jun 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ724B | Recon of Streets in Brookville-Edgewood Triangle (SEQ200519) | 5 | CONSTRUCTION TO 25% | Dec 2004 | Apr 2005 | Jun 2017 | Jan 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ724B | Recon of Streets in Brookville-Edgewood Triangle (SEQ200519) | 6 | CONSTRUCTION TO 50% | Apr 2005 | Aug 2005 | Jan 2018 | Aug 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ724B | Recon of Streets in Brookville-Edgewood Triangle (SEQ200519) | 7 | CONSTRUCTION TO 75% | Aug 2005 | Nov 2005 | Mar 2018 | Mar 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ724B | Recon of Streets in Brookville-Edgewood Triangle (SEQ200519) | 8 | ORIGINAL EQUIP & FURNISHING | Nov 2005 | Feb 2006 | Mar 2019 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ724B | Recon of Streets in Brookville-Edgewood Triangle (SEQ200519) | 9 | SUBSTANTIAL COMPLETION | Feb 2006 | Apr 2006 | Jun 2019 | Aug 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ724B | Recon of Streets in Brookville-Edgewood Triangle (SEQ200519) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2006 | May 2006 | Aug 2019 | Mar 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ787B3 | Sutter Ave, Etc - Phase V (B3) | 1 | DEVELOP SCOPE | Feb 2012 | May 2012 | Feb 2012 | May 2012
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ787B3 | Sutter Ave, Etc - Phase V (B3) | 2 | PRELIMINARY DESIGN | May 2012 | Sep 2012 | May 2012 | Sep 2012
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ787B3 | Sutter Ave, Etc - Phase V (B3) | 3 | FINAL DESIGN | Sep 2012 | Mar 2013 | Sep 2012 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ787B3 | Sutter Ave, Etc - Phase V (B3) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2013 | Jun 2013 | Mar 2018 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ787B3 | Sutter Ave, Etc - Phase V (B3) | 5 | CONSTRUCTION TO 25% | Jun 2013 | Oct 2013 | Mar 2018 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ787B3 | Sutter Ave, Etc - Phase V (B3) | 6 | CONSTRUCTION TO 50% | Oct 2013 | Feb 2014 | Mar 2018 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ787B3 | Sutter Ave, Etc - Phase V (B3) | 7 | CONSTRUCTION TO 75% | Feb 2014 | Jun 2014 | Mar 2018 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ787B3 | Sutter Ave, Etc - Phase V (B3) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2014 | Sep 2014 | Mar 2018 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ787B3 | Sutter Ave, Etc - Phase V (B3) | 9 | SUBSTANTIAL COMPLETION | Sep 2014 | Nov 2014 | Mar 2018 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ787B3 | Sutter Ave, Etc - Phase V (B3) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2014 | Dec 2014 | Mar 2018 | Jun 2029
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ788CS | Court Square Pedestrian Improvements | 1 | PROJECT START | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ788CS | Court Square Pedestrian Improvements | 2 | DESIGN START | Jul 2022 | Jul 2022 | Jul 2022 | Jul 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ788CS | Court Square Pedestrian Improvements | 3 | DESIGN COMPLETION | Jul 2022 | Aug 2024 | Jul 2022 | Aug 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ788CS | Court Square Pedestrian Improvements | 4 | CONSTRUCTION START | Aug 2024 | Apr 2025 | Aug 2024 | Apr 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ788CS | Court Square Pedestrian Improvements | 5 | CONSTRUCTION COMPLETION | Apr 2025 | Apr 2028 | Apr 2025 | Apr 2028
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ985 | SHORE ROAD RECONSTRUCTION (SEQ200585) | 1 | DEVELOP SCOPE | Jun 2009 | Sep 2009 | Jul 2011 | Sep 2011
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ985 | SHORE ROAD RECONSTRUCTION (SEQ200585) | 2 | PRELIMINARY DESIGN | Sep 2009 | Jan 2010 | Sep 2011 | Jan 2012
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ985 | SHORE ROAD RECONSTRUCTION (SEQ200585) | 3 | FINAL DESIGN | Jan 2010 | Jul 2010 | Jan 2012 | Aug 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ985 | SHORE ROAD RECONSTRUCTION (SEQ200585) | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2010 | Oct 2010 | Aug 2014 | Nov 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ985 | SHORE ROAD RECONSTRUCTION (SEQ200585) | 5 | CONSTRUCTION TO 25% | Oct 2010 | Feb 2011 | Nov 2014 | Apr 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ985 | SHORE ROAD RECONSTRUCTION (SEQ200585) | 6 | CONSTRUCTION TO 50% | Feb 2011 | Jun 2011 | Apr 2015 | Aug 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ985 | SHORE ROAD RECONSTRUCTION (SEQ200585) | 7 | CONSTRUCTION TO 75% | Jun 2011 | Oct 2011 | Aug 2015 | Jan 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ985 | SHORE ROAD RECONSTRUCTION (SEQ200585) | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2011 | Jan 2012 | Jan 2016 | Apr 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ985 | SHORE ROAD RECONSTRUCTION (SEQ200585) | 9 | SUBSTANTIAL COMPLETION | Jan 2012 | Mar 2012 | Apr 2016 | Jun 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ985 | SHORE ROAD RECONSTRUCTION (SEQ200585) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2012 | Apr 2012 | Jun 2016 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ985 | SHORE ROAD RECONSTRUCTION (SEQ200585) | 11 | PROJECT START | Mar 2012 | Apr 2012 | Jul 2022 | Jul 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ985 | SHORE ROAD RECONSTRUCTION (SEQ200585) | 12 | DESIGN START | Mar 2012 | Apr 2012 | Jul 2022 | Jul 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ985 | SHORE ROAD RECONSTRUCTION (SEQ200585) | 13 | DESIGN COMPLETION | Mar 2012 | Apr 2012 | Jul 2022 | Jul 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ985 | SHORE ROAD RECONSTRUCTION (SEQ200585) | 14 | CONSTRUCTION START | Mar 2012 | Apr 2012 | Jul 2022 | Jul 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ985 | SHORE ROAD RECONSTRUCTION (SEQ200585) | 15 | CONSTRUCTION COMPLETION | Mar 2012 | Apr 2012 | Jul 2022 | Jun 2032
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF028 | SUNRISE YARD AS ELEC PLUMB HVAC | 6 | CONSTRUCTION TO 50% | Nov 2008 | Nov 2008 | Nov 2008 | Nov 2008
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF028 | SUNRISE YARD AS ELEC PLUMB HVAC | 7 | CONSTRUCTION TO 75% | Nov 2008 | Nov 2008 | Nov 2008 | Nov 2008
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF028 | SUNRISE YARD AS ELEC PLUMB HVAC | 8 | ORIGINAL EQUIP & FURNISHING | Nov 2008 | Nov 2008 | Nov 2008 | Nov 2008
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF028 | SUNRISE YARD AS ELEC PLUMB HVAC | 9 | SUBSTANTIAL COMPLETION | Nov 2008 | Nov 2008 | Nov 2008 | Nov 2008
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF028 | SUNRISE YARD AS ELEC PLUMB HVAC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2008 | Nov 2008 | Nov 2008 | Nov 2008
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF028 | SUNRISE YARD AS ELEC PLUMB HVAC | 11 | PROJECT START | Nov 2008 | Nov 2008 | Nov 2008 | Nov 2008
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF028 | SUNRISE YARD AS ELEC PLUMB HVAC | 12 | DESIGN START | Nov 2008 | Nov 2008 | Nov 2008 | Nov 2008
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF028 | SUNRISE YARD AS ELEC PLUMB HVAC | 13 | DESIGN COMPLETION | Nov 2008 | Nov 2008 | Nov 2008 | Nov 2008
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF028 | SUNRISE YARD AS ELEC PLUMB HVAC | 14 | CONSTRUCTION START | Nov 2008 | Nov 2008 | Nov 2008 | Nov 2008
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF028 | SUNRISE YARD AS ELEC PLUMB HVAC | 15 | CONSTRUCTION COMPLETION | Nov 2008 | Nov 2008 | Jun 2012 | Jun 2012
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF033 | 28-11 QPN 7TH FL REHABILITATION | 1 | DEVELOP SCOPE | Jun 2015 | Aug 2015 | Jun 2018 | Aug 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF033 | 28-11 QPN 7TH FL REHABILITATION | 2 | PRELIMINARY DESIGN | Aug 2015 | Dec 2015 | Aug 2018 | Dec 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF033 | 28-11 QPN 7TH FL REHABILITATION | 3 | FINAL DESIGN | Dec 2015 | Jun 2016 | Dec 2018 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF033 | 28-11 QPN 7TH FL REHABILITATION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2016 | Sep 2016 | Jun 2019 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF033 | 28-11 QPN 7TH FL REHABILITATION | 5 | CONSTRUCTION TO 25% | Sep 2016 | Jan 2017 | Sep 2019 | Jan 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF033 | 28-11 QPN 7TH FL REHABILITATION | 6 | CONSTRUCTION TO 50% | Jan 2017 | May 2017 | Jan 2020 | May 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF033 | 28-11 QPN 7TH FL REHABILITATION | 7 | CONSTRUCTION TO 75% | May 2017 | Sep 2017 | May 2020 | Sep 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF033 | 28-11 QPN 7TH FL REHABILITATION | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Dec 2017 | Sep 2020 | Dec 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF033 | 28-11 QPN 7TH FL REHABILITATION | 9 | SUBSTANTIAL COMPLETION | Dec 2017 | Feb 2018 | Dec 2020 | Feb 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF033 | 28-11 QPN 7TH FL REHABILITATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2018 | Mar 2018 | Feb 2021 | Jun 2033
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q1 | Prior Notice Sidewalks- Queens | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q1 | Prior Notice Sidewalks- Queens | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q1 | Prior Notice Sidewalks- Queens | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q1 | Prior Notice Sidewalks- Queens | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q1 | Prior Notice Sidewalks- Queens | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q1 | Prior Notice Sidewalks- Queens | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q1 | Prior Notice Sidewalks- Queens | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q1 | Prior Notice Sidewalks- Queens | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q1 | Prior Notice Sidewalks- Queens | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q1 | Prior Notice Sidewalks- Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Apr 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q2 | Prior Notice Sidewalks- Queens | 1 | DEVELOP SCOPE | Jan 2019 | Apr 2019 | Jan 2019 | Apr 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q2 | Prior Notice Sidewalks- Queens | 2 | PRELIMINARY DESIGN | Apr 2019 | Aug 2019 | Apr 2019 | Aug 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q2 | Prior Notice Sidewalks- Queens | 3 | FINAL DESIGN | Aug 2019 | Feb 2020 | Aug 2019 | Feb 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q2 | Prior Notice Sidewalks- Queens | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | May 2020 | Feb 2020 | May 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q2 | Prior Notice Sidewalks- Queens | 5 | CONSTRUCTION TO 25% | May 2020 | Sep 2020 | May 2020 | Sep 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q2 | Prior Notice Sidewalks- Queens | 6 | CONSTRUCTION TO 50% | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q2 | Prior Notice Sidewalks- Queens | 7 | CONSTRUCTION TO 75% | Jan 2021 | May 2021 | Jan 2021 | May 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q2 | Prior Notice Sidewalks- Queens | 8 | ORIGINAL EQUIP & FURNISHING | May 2021 | Aug 2021 | May 2021 | Aug 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q2 | Prior Notice Sidewalks- Queens | 9 | SUBSTANTIAL COMPLETION | Aug 2021 | Oct 2021 | Aug 2021 | Oct 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q2 | Prior Notice Sidewalks- Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2021 | Nov 2021 | Oct 2021 | Nov 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q2 | Prior Notice Sidewalks- Queens | 11 | PROJECT START | Oct 2021 | Nov 2021 | Nov 2023 | Nov 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q2 | Prior Notice Sidewalks- Queens | 12 | DESIGN START | Oct 2021 | Nov 2021 | Nov 2023 | Nov 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q2 | Prior Notice Sidewalks- Queens | 13 | DESIGN COMPLETION | Oct 2021 | Nov 2021 | Nov 2023 | Nov 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q2 | Prior Notice Sidewalks- Queens | 14 | CONSTRUCTION START | Oct 2021 | Nov 2021 | Nov 2023 | Nov 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q2 | Prior Notice Sidewalks- Queens | 15 | CONSTRUCTION COMPLETION | Oct 2021 | Nov 2021 | Nov 2023 | Nov 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021Q | PRIOR NOTICE SIDEWALK - QUEENS | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021Q | PRIOR NOTICE SIDEWALK - QUEENS | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021Q | PRIOR NOTICE SIDEWALK - QUEENS | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021Q | PRIOR NOTICE SIDEWALK - QUEENS | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021Q | PRIOR NOTICE SIDEWALK - QUEENS | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021Q | PRIOR NOTICE SIDEWALK - QUEENS | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021Q | PRIOR NOTICE SIDEWALK - QUEENS | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021Q | PRIOR NOTICE SIDEWALK - QUEENS | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021Q | PRIOR NOTICE SIDEWALK - QUEENS | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021Q | PRIOR NOTICE SIDEWALK - QUEENS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023Q | Prior Notice Sidewalks - Queens | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023Q | Prior Notice Sidewalks - Queens | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023Q | Prior Notice Sidewalks - Queens | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023Q | Prior Notice Sidewalks - Queens | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023Q | Prior Notice Sidewalks - Queens | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023Q | Prior Notice Sidewalks - Queens | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023Q | Prior Notice Sidewalks - Queens | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023Q | Prior Notice Sidewalks - Queens | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2022 | Jan 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023Q | Prior Notice Sidewalks - Queens | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2023 | Mar 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023Q | Prior Notice Sidewalks - Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2024 | Apr 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQARVEXPN | Arverne Library - Replacement facility | 1 | PROJECT START | Apr 2016 | Apr 2016 | Sep 2015 | Sep 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQARVEXPN | Arverne Library - Replacement facility | 2 | DESIGN START | Apr 2016 | Apr 2016 | Oct 2015 | Apr 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQARVEXPN | Arverne Library - Replacement facility | 3 | DESIGN COMPLETION | Apr 2016 | Apr 2016 | Apr 2018 | Jan 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQARVEXPN | Arverne Library - Replacement facility | 4 | CONSTRUCTION START | Apr 2016 | Apr 2016 | Jan 2021 | Oct 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQARVEXPN | Arverne Library - Replacement facility | 5 | CONSTRUCTION COMPLETION | Apr 2016 | Dec 2021 | Oct 2021 | Oct 2032
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQASADA | ASTORIA - Brach renovation with ADA | 1 | PROJECT START | Feb 2016 | Feb 2016 | Oct 2015 | Oct 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQASADA | ASTORIA - Brach renovation with ADA | 2 | DESIGN START | Feb 2016 | Feb 2016 | Oct 2015 | Jun 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQASADA | ASTORIA - Brach renovation with ADA | 3 | DESIGN COMPLETION | Feb 2016 | Feb 2016 | Jun 2016 | Nov 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQASADA | ASTORIA - Brach renovation with ADA | 4 | CONSTRUCTION START | Feb 2016 | Feb 2016 | Nov 2019 | Nov 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQASADA | ASTORIA - Brach renovation with ADA | 5 | CONSTRUCTION COMPLETION | Feb 2016 | Dec 2018 | Nov 2019 | May 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQAUB-RG | Auburndale - Reading Garden | 1 | DESIGN | May 2022 | May 2022 | May 2022 | May 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQAUB-RG | Auburndale - Reading Garden | 2 | BID AWARD AND REGISTER CONTRCT | May 2022 | Aug 2022 | May 2022 | Aug 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQAUB-RG | Auburndale - Reading Garden | 3 | CONSTRUCTION | Aug 2022 | Feb 2023 | Aug 2022 | Feb 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQAUB-RG | Auburndale - Reading Garden | 4 | ORIGINAL EQUIP & FURNISHING | Feb 2023 | May 2023 | Feb 2023 | May 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQAUB-RG | Auburndale - Reading Garden | 5 | SUBSTANTIAL COMPLETION | May 2023 | Jun 2023 | May 2023 | Jun 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQAUB-RG | Auburndale - Reading Garden | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2023 | Jul 2023 | Jun 2023 | Jul 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQAUB-RG | Auburndale - Reading Garden | 7 | PROJECT START | Jun 2023 | Jul 2023 | Jul 2023 | Jul 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQAUB-RG | Auburndale - Reading Garden | 8 | DESIGN START | Jun 2023 | Jul 2023 | Jul 2023 | Jul 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQAUB-RG | Auburndale - Reading Garden | 9 | DESIGN COMPLETION | Jun 2023 | Jul 2023 | Jul 2023 | Jul 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQAUB-RG | Auburndale - Reading Garden | 10 | CONSTRUCTION START | Jun 2023 | Jul 2023 | Jul 2023 | Jul 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQAUB-RG | Auburndale - Reading Garden | 11 | CONSTRUCTION COMPLETION | Jun 2023 | Jul 2023 | Jul 2023 | Jul 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBPEXPN | BAISLEY PARK - Branch Renovation | 1 | DESIGN | Jun 2018 | Jul 2018 | Jun 2020 | Jul 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBPEXPN | BAISLEY PARK - Branch Renovation | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2021 | Oct 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBPEXPN | BAISLEY PARK - Branch Renovation | 3 | CONSTRUCTION | Oct 2018 | Apr 2019 | Oct 2021 | Apr 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBPEXPN | BAISLEY PARK - Branch Renovation | 4 | ORIGINAL EQUIP & FURNISHING | Apr 2019 | Jul 2019 | Apr 2023 | Jul 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBPEXPN | BAISLEY PARK - Branch Renovation | 5 | SUBSTANTIAL COMPLETION | Jul 2019 | Aug 2019 | Jul 2023 | Aug 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBPEXPN | BAISLEY PARK - Branch Renovation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2019 | Sep 2019 | Aug 2023 | Sep 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBPEXPN | BAISLEY PARK - Branch Renovation | 7 | PROJECT START | Aug 2019 | Sep 2019 | Sep 2023 | Sep 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBPEXPN | BAISLEY PARK - Branch Renovation | 8 | DESIGN START | Aug 2019 | Sep 2019 | Sep 2023 | Sep 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBPEXPN | BAISLEY PARK - Branch Renovation | 9 | DESIGN COMPLETION | Aug 2019 | Sep 2019 | Sep 2023 | Sep 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBPEXPN | BAISLEY PARK - Branch Renovation | 10 | CONSTRUCTION START | Aug 2019 | Sep 2019 | Sep 2023 | Sep 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBPEXPN | BAISLEY PARK - Branch Renovation | 11 | CONSTRUCTION COMPLETION | Aug 2019 | Sep 2019 | Sep 2023 | Sep 2032
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBTRENOV | BAY TERRACE: Branch Renovation and Expansion | 1 | DESIGN | Jun 2018 | Jul 2018 | Jun 2018 | Jul 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBTRENOV | BAY TERRACE: Branch Renovation and Expansion | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2018 | Oct 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBTRENOV | BAY TERRACE: Branch Renovation and Expansion | 3 | CONSTRUCTION | Oct 2018 | Apr 2019 | Oct 2018 | Apr 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBTRENOV | BAY TERRACE: Branch Renovation and Expansion | 4 | ORIGINAL EQUIP & FURNISHING | Apr 2019 | Jul 2019 | Apr 2022 | Jul 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBTRENOV | BAY TERRACE: Branch Renovation and Expansion | 5 | SUBSTANTIAL COMPLETION | Jul 2019 | Aug 2019 | Jul 2022 | Aug 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBTRENOV | BAY TERRACE: Branch Renovation and Expansion | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2019 | Sep 2019 | Aug 2022 | Sep 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBTRENOV | BAY TERRACE: Branch Renovation and Expansion | 7 | PROJECT START | Aug 2019 | Sep 2019 | Sep 2022 | Sep 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBTRENOV | BAY TERRACE: Branch Renovation and Expansion | 8 | DESIGN START | Aug 2019 | Sep 2019 | Sep 2022 | Sep 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBTRENOV | BAY TERRACE: Branch Renovation and Expansion | 9 | DESIGN COMPLETION | Aug 2019 | Sep 2019 | Sep 2022 | Sep 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBTRENOV | BAY TERRACE: Branch Renovation and Expansion | 10 | CONSTRUCTION START | Aug 2019 | Sep 2019 | Sep 2022 | Sep 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBTRENOV | BAY TERRACE: Branch Renovation and Expansion | 11 | CONSTRUCTION COMPLETION | Aug 2019 | Sep 2019 | Sep 2022 | Sep 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBW-EXP | Briarwood: Branch Renovation | 1 | DESIGN | Jan 2019 | Dec 2020 | Jan 2019 | Dec 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBW-EXP | Briarwood: Branch Renovation | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBW-EXP | Briarwood: Branch Renovation | 3 | CONSTRUCTION | Dec 2021 | Dec 2027 | Dec 2021 | Dec 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQC122-JH | JACKSON HEIGHTS - Branch Expansion & Renovation | 1 | DEVELOP SCOPE | Jul 2010 | Sep 2010 | Jun 2020 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQC122-JH | JACKSON HEIGHTS - Branch Expansion & Renovation | 2 | PRELIMINARY DESIGN | Sep 2010 | Jan 2011 | Jul 2022 | Oct 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQC122-JH | JACKSON HEIGHTS - Branch Expansion & Renovation | 3 | FINAL DESIGN | Jan 2011 | Jul 2011 | Oct 2022 | Apr 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQC122-JH | JACKSON HEIGHTS - Branch Expansion & Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2011 | Oct 2011 | Apr 2023 | Jul 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQC122-JH | JACKSON HEIGHTS - Branch Expansion & Renovation | 5 | CONSTRUCTION TO 25% | Oct 2011 | Feb 2012 | Jul 2023 | Nov 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQC122-JH | JACKSON HEIGHTS - Branch Expansion & Renovation | 6 | CONSTRUCTION TO 50% | Feb 2012 | Jun 2012 | Nov 2023 | Mar 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQC122-JH | JACKSON HEIGHTS - Branch Expansion & Renovation | 7 | CONSTRUCTION TO 75% | Jun 2012 | Oct 2012 | Mar 2024 | Jul 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQC122-JH | JACKSON HEIGHTS - Branch Expansion & Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2012 | Jan 2013 | Jul 2024 | Oct 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQC122-JH | JACKSON HEIGHTS - Branch Expansion & Renovation | 9 | SUBSTANTIAL COMPLETION | Jan 2013 | Mar 2013 | Oct 2024 | Dec 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQC122-JH | JACKSON HEIGHTS - Branch Expansion & Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2013 | Apr 2013 | Dec 2024 | Jan 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQC122-JH | JACKSON HEIGHTS - Branch Expansion & Renovation | 11 | PROJECT START | Mar 2013 | Apr 2013 | Jan 2025 | Jan 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQC122-JH | JACKSON HEIGHTS - Branch Expansion & Renovation | 12 | DESIGN START | Mar 2013 | Apr 2013 | Jan 2025 | Jan 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQC122-JH | JACKSON HEIGHTS - Branch Expansion & Renovation | 13 | DESIGN COMPLETION | Mar 2013 | Apr 2013 | Jan 2025 | Jan 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQC122-JH | JACKSON HEIGHTS - Branch Expansion & Renovation | 14 | CONSTRUCTION START | Mar 2013 | Apr 2013 | Jan 2025 | Jan 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQC122-JH | JACKSON HEIGHTS - Branch Expansion & Renovation | 15 | CONSTRUCTION COMPLETION | Mar 2013 | Apr 2013 | Jan 2025 | Jan 2031
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122BR2 | BROADWAY LIBRARY - RENOVATION (PHASE THREE AND FOUR) | 1 | PROJECT START | Feb 2014 | Feb 2014 | Feb 2014 | Feb 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122BR2 | BROADWAY LIBRARY - RENOVATION (PHASE THREE AND FOUR) | 2 | DESIGN START | Mar 2015 | Mar 2016 | Mar 2015 | Sep 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122BR2 | BROADWAY LIBRARY - RENOVATION (PHASE THREE AND FOUR) | 3 | DESIGN COMPLETION | Mar 2016 | Jul 2016 | Sep 2016 | Nov 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122BR2 | BROADWAY LIBRARY - RENOVATION (PHASE THREE AND FOUR) | 4 | CONSTRUCTION START | Jul 2016 | Dec 2017 | Nov 2018 | Aug 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122BR2 | BROADWAY LIBRARY - RENOVATION (PHASE THREE AND FOUR) | 5 | CONSTRUCTION COMPLETION | Dec 2017 | Dec 2017 | Aug 2019 | Apr 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122GL2 | GLENDALE LIBRARY RENOVATION | 1 | PROJECT START | Mar 2010 | Mar 2010 | Mar 2010 | Mar 2010
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122GL2 | GLENDALE LIBRARY RENOVATION | 2 | DESIGN START | Dec 2011 | Dec 2011 | Dec 2011 | Dec 2011
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122GL2 | GLENDALE LIBRARY RENOVATION | 3 | DESIGN COMPLETION | Jun 2013 | Jun 2013 | Dec 2011 | Mar 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122GL2 | GLENDALE LIBRARY RENOVATION | 4 | CONSTRUCTION START | Feb 2014 | Feb 2014 | Mar 2014 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122GL2 | GLENDALE LIBRARY RENOVATION | 5 | CONSTRUCTION COMPLETION | Feb 2015 | Feb 2015 | Mar 2018 | Dec 2032
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122HO1 | Hollis Library - Building Infrastructure | 1 | PROJECT START | Feb 2014 | Feb 2014 | Feb 2014 | Feb 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122HO1 | Hollis Library - Building Infrastructure | 2 | DESIGN START | Jan 2015 | Jan 2016 | Jan 2015 | Apr 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122HO1 | Hollis Library - Building Infrastructure | 3 | DESIGN COMPLETION | Jan 2016 | Aug 2016 | Apr 2015 | Apr 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122HO1 | Hollis Library - Building Infrastructure | 4 | CONSTRUCTION START | Aug 2016 | Feb 2018 | May 2019 | Jul 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122HO1 | Hollis Library - Building Infrastructure | 5 | CONSTRUCTION COMPLETION | Feb 2018 | Feb 2018 | Jul 2020 | Dec 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122LAE | LAURELTON: Branch Renovation | 1 | DESIGN | Jan 2019 | Dec 2020 | Jan 2019 | Dec 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122LAE | LAURELTON: Branch Renovation | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122LAE | LAURELTON: Branch Renovation | 3 | CONSTRUCTION | Dec 2021 | Dec 2027 | Dec 2021 | Dec 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-QW | QUEENS WEST BRANCH | 1 | DEVELOP SCOPE | Jul 2010 | Sep 2010 | Feb 2010 | Feb 2010
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-QW | QUEENS WEST BRANCH | 2 | PRELIMINARY DESIGN | Sep 2010 | Jan 2011 | Jul 2010 | Jul 2010
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-QW | QUEENS WEST BRANCH | 3 | FINAL DESIGN | Jan 2011 | Jul 2011 | Mar 2013 | Jan 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-QW | QUEENS WEST BRANCH | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2011 | Oct 2011 | Jan 2014 | Feb 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-QW | QUEENS WEST BRANCH | 5 | CONSTRUCTION TO 25% | Oct 2011 | Feb 2012 | Feb 2022 | Aug 2031
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-QW | QUEENS WEST BRANCH | 6 | CONSTRUCTION TO 50% | Feb 2012 | Jun 2012 | Feb 2022 | Aug 2031
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-QW | QUEENS WEST BRANCH | 7 | CONSTRUCTION TO 75% | Jun 2012 | Oct 2012 | Feb 2022 | Aug 2031
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-QW | QUEENS WEST BRANCH | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2012 | Jan 2013 | Feb 2022 | Aug 2031
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-QW | QUEENS WEST BRANCH | 9 | SUBSTANTIAL COMPLETION | Jan 2013 | Mar 2013 | Feb 2022 | Aug 2031
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-QW | QUEENS WEST BRANCH | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2013 | Apr 2013 | Feb 2022 | Aug 2031
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122RO2 | ROCHDALE VILLAGE - HVAC & Controls | 1 | DESIGN | Oct 2010 | Oct 2010 | Jan 2011 | Jan 2011
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122RO2 | ROCHDALE VILLAGE - HVAC & Controls | 2 | BID AWARD AND REGISTER CONTRCT | Oct 2010 | Jan 2011 | May 2014 | May 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122RO2 | ROCHDALE VILLAGE - HVAC & Controls | 3 | CONSTRUCTION | Jan 2011 | Jul 2011 | Oct 2014 | Nov 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122RO2 | ROCHDALE VILLAGE - HVAC & Controls | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2011 | Oct 2011 | Apr 2015 | Mar 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122RO2 | ROCHDALE VILLAGE - HVAC & Controls | 5 | SUBSTANTIAL COMPLETION | Oct 2011 | Nov 2011 | Nov 2015 | Nov 2032
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122RO2 | ROCHDALE VILLAGE - HVAC & Controls | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2011 | Dec 2011 | Nov 2015 | Nov 2032
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-WN | WOODHAVEN - Renovation | 1 | DESIGN | Oct 2010 | Oct 2010 | Feb 2014 | Feb 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-WN | WOODHAVEN - Renovation | 2 | BID AWARD AND REGISTER CONTRCT | Oct 2010 | Jan 2011 | Feb 2014 | Jun 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-WN | WOODHAVEN - Renovation | 3 | CONSTRUCTION | Jan 2011 | Jul 2011 | Jun 2015 | Jun 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-WN | WOODHAVEN - Renovation | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2011 | Oct 2011 | Jun 2017 | Dec 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-WN | WOODHAVEN - Renovation | 5 | SUBSTANTIAL COMPLETION | Oct 2011 | Nov 2011 | Dec 2019 | Jun 2032
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-WN | WOODHAVEN - Renovation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2011 | Dec 2011 | Dec 2019 | Jun 2032
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQDL-NEW | DOUGLASTON: Replacement Facility | 1 | DESIGN | Jan 2019 | Dec 2020 | Jan 2019 | Dec 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQDL-NEW | DOUGLASTON: Replacement Facility | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQDL-NEW | DOUGLASTON: Replacement Facility | 3 | CONSTRUCTION | Dec 2021 | Dec 2027 | Dec 2021 | Dec 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FFA | FLUSHING: FIRE ALARM | 1 | DESIGN | Jan 2020 | Dec 2021 | Jan 2020 | Dec 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FFA | FLUSHING: FIRE ALARM | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FFA | FLUSHING: FIRE ALARM | 3 | CONSTRUCTION | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FFA | FLUSHING: FIRE ALARM | 4 | PROJECT START | Dec 2022 | Dec 2023 | Dec 2023 | Dec 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FFA | FLUSHING: FIRE ALARM | 5 | DESIGN START | Dec 2022 | Dec 2023 | Dec 2023 | Dec 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FFA | FLUSHING: FIRE ALARM | 6 | DESIGN COMPLETION | Dec 2022 | Dec 2023 | Dec 2023 | Dec 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FFA | FLUSHING: FIRE ALARM | 7 | CONSTRUCTION START | Dec 2022 | Dec 2023 | Dec 2023 | Dec 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FFA | FLUSHING: FIRE ALARM | 8 | CONSTRUCTION COMPLETION | Dec 2022 | Dec 2023 | Dec 2023 | Dec 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FLU | FLUSHING:Emergency Functionality | 1 | DESIGN | Jan 2020 | Dec 2021 | Jan 2020 | Dec 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FLU | FLUSHING:Emergency Functionality | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FLU | FLUSHING:Emergency Functionality | 3 | CONSTRUCTION | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FLU | FLUSHING:Emergency Functionality | 4 | PROJECT START | Dec 2022 | Dec 2023 | Dec 2023 | Dec 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FLU | FLUSHING:Emergency Functionality | 5 | DESIGN START | Dec 2022 | Dec 2023 | Dec 2023 | Dec 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FLU | FLUSHING:Emergency Functionality | 6 | DESIGN COMPLETION | Dec 2022 | Dec 2023 | Dec 2023 | Dec 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FLU | FLUSHING:Emergency Functionality | 7 | CONSTRUCTION START | Dec 2022 | Dec 2023 | Dec 2023 | Dec 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FLU | FLUSHING:Emergency Functionality | 8 | CONSTRUCTION COMPLETION | Dec 2022 | Dec 2023 | Dec 2023 | Dec 2033
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQFH-ADA | Forest Hills - Main Entrance Accessibility | 1 | DESIGN | May 2022 | Apr 2024 | May 2022 | Apr 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQFH-ADA | Forest Hills - Main Entrance Accessibility | 2 | BID AWARD AND REGISTER CONTRCT | Apr 2024 | Apr 2025 | Apr 2024 | Apr 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQFH-ADA | Forest Hills - Main Entrance Accessibility | 3 | CONSTRUCTION | Apr 2025 | Apr 2031 | Apr 2025 | Apr 2031
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQFLELV | FLUSHING LIBRARY - CONSTRUCTION OF SECOND ELEVATOR | 1 | PROJECT START | May 2016 | May 2016 | Oct 2015 | Oct 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQFLELV | FLUSHING LIBRARY - CONSTRUCTION OF SECOND ELEVATOR | 2 | DESIGN START | May 2016 | May 2016 | Oct 2015 | Jun 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQFLELV | FLUSHING LIBRARY - CONSTRUCTION OF SECOND ELEVATOR | 3 | DESIGN COMPLETION | May 2016 | May 2016 | Jun 2016 | Nov 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQFLELV | FLUSHING LIBRARY - CONSTRUCTION OF SECOND ELEVATOR | 4 | CONSTRUCTION START | May 2016 | May 2016 | Nov 2018 | Feb 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQFLELV | FLUSHING LIBRARY - CONSTRUCTION OF SECOND ELEVATOR | 5 | CONSTRUCTION COMPLETION | May 2016 | Dec 2019 | Feb 2020 | Sep 2032
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQHIROOF | HILLCREST ROOF | 1 | PROJECT START | May 2016 | May 2016 | Oct 2015 | Oct 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQHIROOF | HILLCREST ROOF | 2 | DESIGN START | May 2016 | May 2016 | Oct 2015 | Mar 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQHIROOF | HILLCREST ROOF | 3 | DESIGN COMPLETION | May 2016 | May 2016 | Mar 2017 | May 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQHIROOF | HILLCREST ROOF | 4 | CONSTRUCTION START | May 2016 | May 2016 | May 2019 | Feb 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQHIROOF | HILLCREST ROOF | 5 | CONSTRUCTION COMPLETION | May 2016 | Dec 2019 | Feb 2020 | Sep 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQLAROOF | LAURELTON ROOF | 1 | PROJECT START | Apr 2016 | Apr 2016 | Apr 2016 | Apr 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQLAROOF | LAURELTON ROOF | 2 | DESIGN START | Apr 2016 | Apr 2016 | Apr 2016 | Apr 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQLAROOF | LAURELTON ROOF | 3 | DESIGN COMPLETION | Apr 2016 | Apr 2016 | Apr 2016 | Apr 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQLAROOF | LAURELTON ROOF | 4 | CONSTRUCTION START | Apr 2016 | Apr 2016 | Apr 2016 | Apr 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQLAROOF | LAURELTON ROOF | 5 | CONSTRUCTION COMPLETION | Apr 2016 | Dec 2020 | Apr 2016 | Dec 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-BL | Masonry Repairs - Bellerose | 3 | DESIGN COMPLETION | Nov 2014 | Nov 2014 | Nov 2014 | Jun 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-BL | Masonry Repairs - Bellerose | 4 | CONSTRUCTION START | May 2015 | May 2015 | May 2015 | Oct 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-BL | Masonry Repairs - Bellerose | 5 | CONSTRUCTION COMPLETION | Nov 2015 | Nov 2015 | Nov 2015 | Nov 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122EE2 | EAST ELMHURST - Expansion | 1 | PROJECT START | Jan 2010 | Jan 2010 | Jan 2010 | Jan 2010
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122EE2 | EAST ELMHURST - Expansion | 2 | DESIGN START | Oct 2010 | Oct 2011 | Jan 2010 | Oct 2011
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122EE2 | EAST ELMHURST - Expansion | 3 | DESIGN COMPLETION | Oct 2011 | Feb 2012 | Oct 2011 | Jul 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122EE2 | EAST ELMHURST - Expansion | 4 | CONSTRUCTION START | Feb 2012 | Jul 2013 | Jul 2014 | Aug 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122EE2 | EAST ELMHURST - Expansion | 5 | CONSTRUCTION COMPLETION | Jul 2013 | Jul 2013 | Aug 2015 | Aug 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-FA | FAR ROCKAWAY - Replacement Facility | 1 | DEVELOP SCOPE | Jul 2010 | Sep 2010 | Sep 2011 | Sep 2011
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-FA | FAR ROCKAWAY - Replacement Facility | 2 | PRELIMINARY DESIGN | Sep 2010 | Jan 2011 | Jan 2012 | Jan 2012
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-FA | FAR ROCKAWAY - Replacement Facility | 3 | FINAL DESIGN | Jan 2011 | Jul 2011 | Oct 2015 | Oct 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-FA | FAR ROCKAWAY - Replacement Facility | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2011 | Oct 2011 | Oct 2017 | Jul 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-FA | FAR ROCKAWAY - Replacement Facility | 5 | CONSTRUCTION TO 25% | Oct 2011 | Feb 2012 | Aug 2018 | Aug 2031
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-FA | FAR ROCKAWAY - Replacement Facility | 6 | CONSTRUCTION TO 50% | Feb 2012 | Jun 2012 | Aug 2018 | Aug 2031
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-FA | FAR ROCKAWAY - Replacement Facility | 7 | CONSTRUCTION TO 75% | Jun 2012 | Oct 2012 | Aug 2018 | Aug 2031
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-FA | FAR ROCKAWAY - Replacement Facility | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2012 | Jan 2013 | Aug 2018 | Aug 2031
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-FA | FAR ROCKAWAY - Replacement Facility | 9 | SUBSTANTIAL COMPLETION | Jan 2013 | Mar 2013 | Aug 2018 | Aug 2031
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-FA | FAR ROCKAWAY - Replacement Facility | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2013 | Apr 2013 | Aug 2018 | Aug 2031
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-RG | REGO PARK LIBRARY - REPLACEMENT FACILITY | 1 | DEVELOP SCOPE | Jul 2010 | Sep 2010 | Jun 2018 | Apr 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-RG | REGO PARK LIBRARY - REPLACEMENT FACILITY | 2 | PRELIMINARY DESIGN | Sep 2010 | Jan 2011 | Apr 2019 | Jul 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-RG | REGO PARK LIBRARY - REPLACEMENT FACILITY | 3 | FINAL DESIGN | Jan 2011 | Jul 2011 | Jul 2019 | Feb 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-RG | REGO PARK LIBRARY - REPLACEMENT FACILITY | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2011 | Oct 2011 | Nov 2021 | Nov 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-RG | REGO PARK LIBRARY - REPLACEMENT FACILITY | 5 | CONSTRUCTION TO 25% | Oct 2011 | Feb 2012 | Nov 2024 | Nov 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-RG | REGO PARK LIBRARY - REPLACEMENT FACILITY | 6 | CONSTRUCTION TO 50% | Feb 2012 | Jun 2012 | Nov 2024 | Nov 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-RG | REGO PARK LIBRARY - REPLACEMENT FACILITY | 7 | CONSTRUCTION TO 75% | Jun 2012 | Oct 2012 | Nov 2024 | Nov 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-RG | REGO PARK LIBRARY - REPLACEMENT FACILITY | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2012 | Jan 2013 | Nov 2024 | Nov 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-RG | REGO PARK LIBRARY - REPLACEMENT FACILITY | 9 | SUBSTANTIAL COMPLETION | Jan 2013 | Mar 2013 | Nov 2024 | Nov 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-RG | REGO PARK LIBRARY - REPLACEMENT FACILITY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2013 | Apr 2013 | Nov 2024 | Nov 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQBHHVAC | QUEENSBORO HILL - HVAC | 1 | PROJECT START | Oct 2003 | Oct 2003 | Oct 2003 | Oct 2003
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQBHHVAC | QUEENSBORO HILL - HVAC | 2 | DESIGN START | Oct 2003 | Oct 2003 | Oct 2003 | Oct 2003
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQBHHVAC | QUEENSBORO HILL - HVAC | 3 | DESIGN COMPLETION | Oct 2003 | Oct 2003 | Oct 2003 | Oct 2003
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQBHHVAC | QUEENSBORO HILL - HVAC | 4 | CONSTRUCTION START | Oct 2003 | Oct 2003 | Oct 2003 | Oct 2003
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQBHHVAC | QUEENSBORO HILL - HVAC | 5 | CONSTRUCTION COMPLETION | Oct 2003 | Dec 2020 | Oct 2003 | Jun 2028
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQVHVAC | QUEENS VILLAGE - HVAC | 1 | PROJECT START | Dec 2016 | Dec 2016 | Dec 2016 | Dec 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQVHVAC | QUEENS VILLAGE - HVAC | 2 | DESIGN START | Dec 2016 | Dec 2016 | Dec 2016 | Dec 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQVHVAC | QUEENS VILLAGE - HVAC | 3 | DESIGN COMPLETION | Dec 2016 | Dec 2016 | Dec 2016 | Dec 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQVHVAC | QUEENS VILLAGE - HVAC | 4 | CONSTRUCTION START | Dec 2016 | Dec 2016 | Dec 2016 | Dec 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQVHVAC | QUEENS VILLAGE - HVAC | 5 | CONSTRUCTION COMPLETION | Dec 2016 | Dec 2021 | Dec 2016 | Dec 2032
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQVROOF | QUEENS VILLAGE - ROOF | 1 | PROJECT START | Dec 2016 | Dec 2016 | Dec 2016 | Dec 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQVROOF | QUEENS VILLAGE - ROOF | 2 | DESIGN START | Dec 2016 | Dec 2016 | Dec 2016 | Dec 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQVROOF | QUEENS VILLAGE - ROOF | 3 | DESIGN COMPLETION | Dec 2016 | Dec 2016 | Dec 2016 | Dec 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQVROOF | QUEENS VILLAGE - ROOF | 4 | CONSTRUCTION START | Dec 2016 | Dec 2016 | Dec 2016 | Dec 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQVROOF | QUEENS VILLAGE - ROOF | 5 | CONSTRUCTION COMPLETION | Dec 2021 | Jan 2027 | Dec 2021 | Jan 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQRDMASON | RIDGEWOOD - MASONRY | 1 | PROJECT START | Dec 2016 | Dec 2016 | Dec 2016 | Dec 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQRDMASON | RIDGEWOOD - MASONRY | 2 | DESIGN START | Dec 2016 | Dec 2016 | Dec 2016 | Dec 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQRDMASON | RIDGEWOOD - MASONRY | 3 | DESIGN COMPLETION | Dec 2016 | Dec 2016 | Dec 2016 | Dec 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQRDMASON | RIDGEWOOD - MASONRY | 4 | CONSTRUCTION START | Dec 2016 | Dec 2016 | Dec 2016 | Dec 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQRDMASON | RIDGEWOOD - MASONRY | 5 | CONSTRUCTION COMPLETION | Dec 2016 | Dec 2021 | Dec 2016 | Dec 2033
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQRS-EXTR | ROSEDALE: Branch Expansion and Renovation | 1 | DESIGN | Jan 2019 | Dec 2020 | Jan 2019 | Dec 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQRS-EXTR | ROSEDALE: Branch Expansion and Renovation | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQRS-EXTR | ROSEDALE: Branch Expansion and Renovation | 3 | CONSTRUCTION | Dec 2021 | Dec 2027 | Dec 2021 | Dec 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSARENOV | ST. ALBANS RENOVATION | 1 | PROJECT START | Dec 2016 | Dec 2016 | Dec 2016 | Dec 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSARENOV | ST. ALBANS RENOVATION | 2 | DESIGN START | Dec 2016 | Dec 2016 | Dec 2016 | Dec 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSARENOV | ST. ALBANS RENOVATION | 3 | DESIGN COMPLETION | Dec 2016 | Dec 2016 | Dec 2016 | Dec 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSARENOV | ST. ALBANS RENOVATION | 4 | CONSTRUCTION START | Dec 2016 | Dec 2016 | Dec 2016 | Dec 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSARENOV | ST. ALBANS RENOVATION | 5 | CONSTRUCTION COMPLETION | Dec 2016 | Dec 2021 | Dec 2016 | Dec 2028
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSEHVAC | SEASIDE -HVAC | 1 | PROJECT START | Jan 2015 | Jan 2015 | Jan 2015 | Jan 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSEHVAC | SEASIDE -HVAC | 2 | DESIGN START | Jan 2015 | Jan 2015 | Jan 2015 | Jan 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSEHVAC | SEASIDE -HVAC | 3 | DESIGN COMPLETION | Jan 2015 | Jan 2015 | Jan 2015 | Jan 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSEHVAC | SEASIDE -HVAC | 4 | CONSTRUCTION START | Jan 2015 | Jan 2015 | Jan 2015 | Jan 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSEHVAC | SEASIDE -HVAC | 5 | CONSTRUCTION COMPLETION | Jan 2015 | Dec 2021 | Jan 2015 | Dec 2029
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-407BHI3 | BOWNE HOUSE INTERIOR RESTORATIONS | 1 | PROJECT START | Sep 2015 | Sep 2015 | Sep 2015 | Sep 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-407BHI3 | BOWNE HOUSE INTERIOR RESTORATIONS | 2 | DESIGN START | Oct 2015 | Oct 2015 | Oct 2016 | Oct 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-407BHI3 | BOWNE HOUSE INTERIOR RESTORATIONS | 3 | DESIGN COMPLETION | Oct 2015 | Oct 2015 | Oct 2016 | Jan 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-407BHI3 | BOWNE HOUSE INTERIOR RESTORATIONS | 4 | CONSTRUCTION START | Oct 2015 | Oct 2015 | Jun 2018 | Jun 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-407BHI3 | BOWNE HOUSE INTERIOR RESTORATIONS | 5 | CONSTRUCTION COMPLETION | Oct 2015 | Oct 2017 | Jun 2018 | Jun 2029
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-407BHV4 | BOWNE HOUSE VISITORS CENTER Q022 | 1 | PROJECT START | Jan 2016 | Jan 2016 | Nov 2019 | Nov 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-407BHV4 | BOWNE HOUSE VISITORS CENTER Q022 | 2 | DESIGN START | Jan 2016 | Feb 2016 | Dec 2019 | Dec 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-407BHV4 | BOWNE HOUSE VISITORS CENTER Q022 | 3 | DESIGN COMPLETION | Feb 2016 | Jun 2016 | Dec 2019 | Apr 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-407BHV4 | BOWNE HOUSE VISITORS CENTER Q022 | 4 | CONSTRUCTION START | Jul 2016 | Jul 2016 | May 2022 | May 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-407BHV4 | BOWNE HOUSE VISITORS CENTER Q022 | 5 | CONSTRUCTION COMPLETION | Jul 2016 | Jul 2018 | May 2022 | Jun 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-412RWR1 | Roy Wilkins Recreation Center | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-412RWR1 | Roy Wilkins Recreation Center | 2 | DESIGN | Dec 2021 | Dec 2023 | Dec 2021 | Dec 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-412RWR1 | Roy Wilkins Recreation Center | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-412RWR1 | Roy Wilkins Recreation Center | 4 | CONSTRUCTION | Sep 2024 | Sep 2027 | Sep 2024 | Sep 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-412RWR1 | Roy Wilkins Recreation Center | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Sep 2029 | Sep 2027 | Sep 2029
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-413SCS1 | Brookville Park - Cons. PRB | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-413SCS1 | Brookville Park - Cons. PRB | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-413SCS1 | Brookville Park - Cons. PRB | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-413SCS1 | Brookville Park - Cons. PRB | 4 | CONSTRUCTION | Sep 2024 | Mar 2026 | Sep 2024 | Mar 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-413SCS1 | Brookville Park - Cons. PRB | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Jun 2028 | Mar 2026 | Jun 2028
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-4DSTG06 | Kissena Park Velodrome Conn- Destination Greenways | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-4DSTG06 | Kissena Park Velodrome Conn- Destination Greenways | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-4DSTG06 | Kissena Park Velodrome Conn- Destination Greenways | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-4DSTG06 | Kissena Park Velodrome Conn- Destination Greenways | 4 | CONSTRUCTION | Sep 2024 | Mar 2026 | Sep 2024 | Mar 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-4DSTG06 | Kissena Park Velodrome Conn- Destination Greenways | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Mar 2027 | Mar 2026 | Mar 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-4QNHSR1 | Queens Historical Society Construction and Renovation to DDC | 1 | PROJECT START | Jun 2022 | Jun 2023 | Jun 2022 | Jun 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-4QNHSR1 | Queens Historical Society Construction and Renovation to DDC | 2 | DESIGN START | Jul 2023 | Jul 2023 | Jul 2023 | Jul 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-4QNHSR1 | Queens Historical Society Construction and Renovation to DDC | 3 | DESIGN COMPLETION | Jul 2023 | Jul 2023 | Jul 2023 | Jul 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-4QNHSR1 | Queens Historical Society Construction and Renovation to DDC | 4 | CONSTRUCTION START | Jul 2023 | Jul 2023 | Jul 2023 | Jul 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-4QNHSR1 | Queens Historical Society Construction and Renovation to DDC | 5 | CONSTRUCTION COMPLETION | Jul 2023 | Jun 2029 | Jul 2023 | Jun 2029
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-4RCKGHQ | Rockaway Operational Headquarters, SANDY4-50 and Sandy4-11 | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-4RCKGHQ | Rockaway Operational Headquarters, SANDY4-50 and Sandy4-11 | 2 | DESIGN | Dec 2019 | Dec 2021 | Dec 2019 | Dec 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-4RCKGHQ | Rockaway Operational Headquarters, SANDY4-50 and Sandy4-11 | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-4RCKGHQ | Rockaway Operational Headquarters, SANDY4-50 and Sandy4-11 | 4 | CONSTRUCTION | Sep 2022 | Sep 2024 | Sep 2022 | Sep 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-4RCKGHQ | Rockaway Operational Headquarters, SANDY4-50 and Sandy4-11 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO002-116 | NEW 116TH PCT | 1 | DEVELOP SCOPE | Apr 2017 | Jul 2017 | Apr 2017 | Jul 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO002-116 | NEW 116TH PCT | 2 | PRELIMINARY DESIGN | Jul 2017 | Nov 2017 | Jul 2017 | Nov 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO002-116 | NEW 116TH PCT | 3 | FINAL DESIGN | Nov 2017 | May 2018 | Nov 2017 | May 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO002-116 | NEW 116TH PCT | 4 | BID AWARD AND REGISTER CONTRCT | May 2018 | Aug 2018 | May 2018 | Aug 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO002-116 | NEW 116TH PCT | 5 | CONSTRUCTION TO 25% | Aug 2018 | Dec 2018 | Aug 2018 | Dec 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO002-116 | NEW 116TH PCT | 6 | CONSTRUCTION TO 50% | Dec 2018 | Apr 2019 | Dec 2018 | Apr 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO002-116 | NEW 116TH PCT | 7 | CONSTRUCTION TO 75% | Apr 2019 | Aug 2019 | Apr 2019 | Aug 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO002-116 | NEW 116TH PCT | 8 | ORIGINAL EQUIP & FURNISHING | Aug 2019 | Nov 2019 | Aug 2019 | Nov 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO002-116 | NEW 116TH PCT | 9 | SUBSTANTIAL COMPLETION | Nov 2019 | Jan 2020 | Nov 2019 | Jan 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO002-116 | NEW 116TH PCT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2020 | Feb 2020 | Jan 2020 | Jan 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO002-116 | NEW 116TH PCT | 11 | PROJECT START | Jan 2020 | Feb 2020 | Feb 2023 | Feb 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO002-116 | NEW 116TH PCT | 12 | DESIGN START | Jan 2020 | Feb 2020 | Feb 2023 | Feb 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO002-116 | NEW 116TH PCT | 13 | DESIGN COMPLETION | Jan 2020 | Feb 2020 | Feb 2023 | Feb 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO002-116 | NEW 116TH PCT | 14 | CONSTRUCTION START | Jan 2020 | Feb 2020 | Feb 2023 | Feb 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO002-116 | NEW 116TH PCT | 15 | CONSTRUCTION COMPLETION | Jan 2020 | Feb 2020 | Feb 2023 | Feb 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHW | 114TH PCT PLUMBING SYSTEM REPLACEMENT | 1 | DEVELOP SCOPE | Jun 2014 | Sep 2014 | Jun 2014 | Sep 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHW | 114TH PCT PLUMBING SYSTEM REPLACEMENT | 2 | PRELIMINARY DESIGN | Sep 2014 | Jan 2015 | Sep 2014 | Jan 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHW | 114TH PCT PLUMBING SYSTEM REPLACEMENT | 3 | FINAL DESIGN | Jan 2015 | Jul 2015 | Jan 2015 | Jul 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHW | 114TH PCT PLUMBING SYSTEM REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Oct 2015 | Jul 2015 | Oct 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHW | 114TH PCT PLUMBING SYSTEM REPLACEMENT | 5 | CONSTRUCTION TO 25% | Oct 2015 | Feb 2016 | Oct 2015 | Feb 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHW | 114TH PCT PLUMBING SYSTEM REPLACEMENT | 6 | CONSTRUCTION TO 50% | Feb 2016 | Jun 2016 | Feb 2016 | Jun 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHW | 114TH PCT PLUMBING SYSTEM REPLACEMENT | 7 | CONSTRUCTION TO 75% | Jun 2016 | Oct 2016 | Jun 2016 | Oct 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHW | 114TH PCT PLUMBING SYSTEM REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2016 | Jan 2017 | Oct 2016 | Jan 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHW | 114TH PCT PLUMBING SYSTEM REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | Jan 2017 | Mar 2017 | Jan 2017 | Mar 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHW | 114TH PCT PLUMBING SYSTEM REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Apr 2017 | Mar 2017 | Oct 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHW | 114TH PCT PLUMBING SYSTEM REPLACEMENT | 11 | PROJECT START | Mar 2017 | Apr 2017 | Oct 2022 | Oct 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHW | 114TH PCT PLUMBING SYSTEM REPLACEMENT | 12 | DESIGN START | Mar 2017 | Apr 2017 | Oct 2022 | Oct 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHW | 114TH PCT PLUMBING SYSTEM REPLACEMENT | 13 | DESIGN COMPLETION | Mar 2017 | Apr 2017 | Oct 2022 | Oct 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHW | 114TH PCT PLUMBING SYSTEM REPLACEMENT | 14 | CONSTRUCTION START | Mar 2017 | Apr 2017 | Oct 2022 | Oct 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHW | 114TH PCT PLUMBING SYSTEM REPLACEMENT | 15 | CONSTRUCTION COMPLETION | Mar 2017 | Apr 2017 | Oct 2022 | Oct 2029
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-349 | REHABILITATION OF DAMAGED ROCKAWAY INTERCEPTOR | 1 | DEVELOP SCOPE | Jun 2023 | Feb 2024 | Jun 2023 | Feb 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-349 | REHABILITATION OF DAMAGED ROCKAWAY INTERCEPTOR | 2 | PRELIMINARY DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-349 | REHABILITATION OF DAMAGED ROCKAWAY INTERCEPTOR | 3 | FINAL DESIGN | Feb 2025 | Aug 2026 | Feb 2025 | Aug 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-349 | REHABILITATION OF DAMAGED ROCKAWAY INTERCEPTOR | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2026 | May 2027 | Aug 2026 | May 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-349 | REHABILITATION OF DAMAGED ROCKAWAY INTERCEPTOR | 5 | CONSTRUCTION TO 25% | May 2027 | May 2028 | May 2027 | May 2028
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-349 | REHABILITATION OF DAMAGED ROCKAWAY INTERCEPTOR | 6 | CONSTRUCTION TO 50% | May 2028 | Apr 2029 | May 2028 | Apr 2029
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-349 | REHABILITATION OF DAMAGED ROCKAWAY INTERCEPTOR | 7 | CONSTRUCTION TO 75% | Apr 2029 | Apr 2030 | Apr 2029 | Apr 2030
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-349 | REHABILITATION OF DAMAGED ROCKAWAY INTERCEPTOR | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2030 | Jan 2031 | Apr 2030 | Jan 2031
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-349 | REHABILITATION OF DAMAGED ROCKAWAY INTERCEPTOR | 9 | SUBSTANTIAL COMPLETION | Jan 2031 | Jul 2031 | Jan 2031 | Jul 2031
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-349 | REHABILITATION OF DAMAGED ROCKAWAY INTERCEPTOR | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2031 | Oct 2031 | Jul 2031 | Oct 2031
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV001SELM | LAH - Louis Armstrong House - Administration Facility | 1 | PROJECT START | Jun 2015 | Jun 2015 | Sep 2015 | Sep 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV001SELM | LAH - Louis Armstrong House - Administration Facility | 2 | DESIGN START | Jun 2015 | Jun 2015 | Sep 2015 | Sep 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV001SELM | LAH - Louis Armstrong House - Administration Facility | 3 | DESIGN COMPLETION | Jun 2015 | Jun 2015 | Sep 2017 | Dec 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV001SELM | LAH - Louis Armstrong House - Administration Facility | 4 | CONSTRUCTION START | Jun 2015 | Jun 2015 | Dec 2018 | Jan 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV001SELM | LAH - Louis Armstrong House - Administration Facility | 5 | CONSTRUCTION COMPLETION | Jun 2015 | Jun 2018 | Jan 2020 | Jun 2032
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040ELEV | FTH - Flushing Town Hall Elevator Replacement | 1 | DEVELOP SCOPE | Sep 2018 | Jun 2019 | Sep 2018 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040ELEV | FTH - Flushing Town Hall Elevator Replacement | 2 | PRELIMINARY DESIGN | Jul 2019 | Oct 2019 | Jul 2019 | Oct 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040ELEV | FTH - Flushing Town Hall Elevator Replacement | 3 | FINAL DESIGN | Oct 2019 | Apr 2020 | Oct 2019 | Apr 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040ELEV | FTH - Flushing Town Hall Elevator Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2020 | Jul 2020 | Apr 2020 | Jul 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040ELEV | FTH - Flushing Town Hall Elevator Replacement | 5 | CONSTRUCTION TO 25% | Jul 2020 | Nov 2020 | Jul 2020 | Nov 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040ELEV | FTH - Flushing Town Hall Elevator Replacement | 6 | CONSTRUCTION TO 50% | Nov 2020 | Mar 2021 | Nov 2020 | Mar 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040ELEV | FTH - Flushing Town Hall Elevator Replacement | 7 | CONSTRUCTION TO 75% | Mar 2021 | Jul 2021 | Mar 2021 | Jul 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040ELEV | FTH - Flushing Town Hall Elevator Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040ELEV | FTH - Flushing Town Hall Elevator Replacement | 9 | SUBSTANTIAL COMPLETION | Oct 2021 | Dec 2021 | Oct 2021 | Dec 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040ELEV | FTH - Flushing Town Hall Elevator Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2021 | Jan 2022 | Dec 2021 | Jan 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040ELEV | FTH - Flushing Town Hall Elevator Replacement | 11 | PROJECT START | Dec 2021 | Jan 2022 | Jan 2022 | Jan 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040ELEV | FTH - Flushing Town Hall Elevator Replacement | 12 | DESIGN START | Dec 2021 | Jan 2022 | Jan 2022 | Jan 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040ELEV | FTH - Flushing Town Hall Elevator Replacement | 13 | DESIGN COMPLETION | Dec 2021 | Jan 2022 | Jan 2022 | Jan 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040ELEV | FTH - Flushing Town Hall Elevator Replacement | 14 | CONSTRUCTION START | Dec 2021 | Jan 2022 | Jan 2022 | Jan 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040ELEV | FTH - Flushing Town Hall Elevator Replacement | 15 | CONSTRUCTION COMPLETION | Dec 2021 | Jan 2022 | Jan 2022 | Jun 2031
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | 1 | DEVELOP SCOPE | Sep 2018 | Jun 2019 | Sep 2018 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | 2 | PRELIMINARY DESIGN | Jul 2019 | Oct 2019 | Jul 2019 | Oct 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | 3 | FINAL DESIGN | Oct 2019 | Apr 2020 | Oct 2019 | Apr 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2020 | Jul 2020 | Apr 2020 | Jul 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | 5 | CONSTRUCTION TO 25% | Jul 2020 | Nov 2020 | Jul 2020 | Nov 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | 6 | CONSTRUCTION TO 50% | Nov 2020 | Mar 2021 | Nov 2020 | Mar 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | 7 | CONSTRUCTION TO 75% | Mar 2021 | Jul 2021 | Mar 2021 | Jul 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | 9 | SUBSTANTIAL COMPLETION | Oct 2021 | Dec 2021 | Oct 2021 | Dec 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2021 | Jan 2022 | Dec 2021 | Sep 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | 11 | PROJECT START | Dec 2021 | Jan 2022 | Oct 2023 | Oct 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | 12 | DESIGN START | Dec 2021 | Jan 2022 | Oct 2023 | Oct 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | 13 | DESIGN COMPLETION | Dec 2021 | Jan 2022 | Oct 2023 | Oct 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | 14 | CONSTRUCTION START | Dec 2021 | Jan 2022 | Oct 2023 | Oct 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | 15 | CONSTRUCTION COMPLETION | Dec 2021 | Jan 2022 | Oct 2023 | Oct 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272EDUC | QBG - Queens Botanical Garden Educ Bldg Renovation | 1 | DEVELOP SCOPE | Jun 2014 | Sep 2014 | Jun 2014 | Sep 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272EDUC | QBG - Queens Botanical Garden Educ Bldg Renovation | 2 | PRELIMINARY DESIGN | Sep 2014 | Jan 2015 | Sep 2014 | Jan 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272EDUC | QBG - Queens Botanical Garden Educ Bldg Renovation | 3 | FINAL DESIGN | Jan 2015 | Jul 2015 | Jan 2015 | Jul 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272EDUC | QBG - Queens Botanical Garden Educ Bldg Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Oct 2015 | Jul 2015 | Oct 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272EDUC | QBG - Queens Botanical Garden Educ Bldg Renovation | 5 | CONSTRUCTION TO 25% | Oct 2015 | Feb 2016 | Oct 2015 | Feb 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272EDUC | QBG - Queens Botanical Garden Educ Bldg Renovation | 6 | CONSTRUCTION TO 50% | Feb 2016 | Jun 2016 | Feb 2016 | Jun 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272EDUC | QBG - Queens Botanical Garden Educ Bldg Renovation | 7 | CONSTRUCTION TO 75% | Jun 2016 | Oct 2016 | Feb 2021 | Jun 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272EDUC | QBG - Queens Botanical Garden Educ Bldg Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2015 | Jul 2015 | Apr 2015 | Jul 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272EDUC | QBG - Queens Botanical Garden Educ Bldg Renovation | 9 | SUBSTANTIAL COMPLETION | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272EDUC | QBG - Queens Botanical Garden Educ Bldg Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2021 | Jun 2021 | May 2021 | Jun 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274CHLL | NYHOS - New York Hall of Science - Chiller Replacement | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Jan 2018 | Apr 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274CHLL | NYHOS - New York Hall of Science - Chiller Replacement | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Apr 2018 | Feb 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274CHLL | NYHOS - New York Hall of Science - Chiller Replacement | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Feb 2019 | Sep 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274CHLL | NYHOS - New York Hall of Science - Chiller Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Sep 2020 | Oct 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274CHLL | NYHOS - New York Hall of Science - Chiller Replacement | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Oct 2021 | Jun 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274CHLL | NYHOS - New York Hall of Science - Chiller Replacement | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Oct 2021 | Jun 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274CHLL | NYHOS - New York Hall of Science - Chiller Replacement | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Oct 2021 | Jun 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274CHLL | NYHOS - New York Hall of Science - Chiller Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | Oct 2021 | Jun 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274CHLL | NYHOS - New York Hall of Science - Chiller Replacement | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Oct 2021 | Jun 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274CHLL | NYHOS - New York Hall of Science - Chiller Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Oct 2021 | Jun 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274KITR | NYHOS - NY Hall of Science,Great Hall, Kitchen & Restroom | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Jul 2016 | Jul 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274KITR | NYHOS - NY Hall of Science,Great Hall, Kitchen & Restroom | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Jul 2016 | Jul 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274KITR | NYHOS - NY Hall of Science,Great Hall, Kitchen & Restroom | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Jul 2016 | Feb 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274KITR | NYHOS - NY Hall of Science,Great Hall, Kitchen & Restroom | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Feb 2019 | Aug 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274KITR | NYHOS - NY Hall of Science,Great Hall, Kitchen & Restroom | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Aug 2019 | Oct 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274KITR | NYHOS - NY Hall of Science,Great Hall, Kitchen & Restroom | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Aug 2019 | Oct 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274KITR | NYHOS - NY Hall of Science,Great Hall, Kitchen & Restroom | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Aug 2019 | Oct 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274KITR | NYHOS - NY Hall of Science,Great Hall, Kitchen & Restroom | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | Aug 2019 | Oct 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274KITR | NYHOS - NY Hall of Science,Great Hall, Kitchen & Restroom | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Aug 2019 | Oct 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274KITR | NYHOS - NY Hall of Science,Great Hall, Kitchen & Restroom | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Aug 2019 | Oct 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV291-QM2 | QMA - Queen's Museum of Art Expansion Phase II | 1 | PROJECT START | Sep 2013 | Sep 2014 | Mar 2018 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV291-QM2 | QMA - Queen's Museum of Art Expansion Phase II | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2014 | Sep 2015 | Mar 2018 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV291-QM2 | QMA - Queen's Museum of Art Expansion Phase II | 3 | DESIGN COMPLETION | Sep 2014 | Sep 2015 | Sep 2019 | Jan 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV291-QM2 | QMA - Queen's Museum of Art Expansion Phase II | 4 | CONSTRUCTION START | Sep 2014 | Sep 2015 | Jan 2021 | Feb 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV291-QM2 | QMA - Queen's Museum of Art Expansion Phase II | 5 | CONSTRUCTION COMPLETION | Sep 2014 | Sep 2015 | Feb 2022 | Apr 2028
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV466BOIL | QTIP - Queens Theater in the Park Boiler | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2021 | Aug 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV466BOIL | QTIP - Queens Theater in the Park Boiler | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Aug 2021 | Dec 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV466BOIL | QTIP - Queens Theater in the Park Boiler | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Dec 2021 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV466BOIL | QTIP - Queens Theater in the Park Boiler | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jun 2022 | Sep 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV466BOIL | QTIP - Queens Theater in the Park Boiler | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Sep 2022 | Jan 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV466BOIL | QTIP - Queens Theater in the Park Boiler | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Jan 2023 | May 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV466BOIL | QTIP - Queens Theater in the Park Boiler | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | May 2023 | Sep 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV466BOIL | QTIP - Queens Theater in the Park Boiler | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Sep 2023 | Dec 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV466BOIL | QTIP - Queens Theater in the Park Boiler | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Dec 2023 | Feb 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV466BOIL | QTIP - Queens Theater in the Park Boiler | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Feb 2024 | Mar 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | 1 | DEVELOP SCOPE | Dec 2015 | Mar 2016 | Jan 2016 | Jan 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | 2 | PRELIMINARY DESIGN | Mar 2016 | Jul 2016 | Jan 2016 | Jan 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | 3 | FINAL DESIGN | Jul 2016 | Jan 2017 | Jan 2016 | Jan 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2017 | Apr 2017 | Jan 2016 | Jan 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | 5 | CONSTRUCTION TO 25% | Apr 2017 | Aug 2017 | Jan 2016 | Jan 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | 6 | CONSTRUCTION TO 50% | Aug 2017 | Dec 2017 | Jan 2016 | Jan 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | 7 | CONSTRUCTION TO 75% | Dec 2017 | Apr 2018 | Jan 2016 | Jan 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2018 | Jul 2018 | Jan 2016 | Jan 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | 9 | SUBSTANTIAL COMPLETION | Jul 2018 | Aug 2018 | Jan 2016 | Jan 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2018 | Sep 2018 | Jan 2016 | Jan 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | 11 | PROJECT START | Aug 2018 | Sep 2018 | Jan 2016 | Jan 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | 12 | DESIGN START | Aug 2018 | Sep 2018 | Jan 2016 | Sep 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | 13 | DESIGN COMPLETION | Aug 2018 | Sep 2018 | Sep 2017 | May 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | 14 | CONSTRUCTION START | Aug 2018 | Sep 2018 | May 2019 | May 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | 15 | CONSTRUCTION COMPLETION | Aug 2018 | Sep 2018 | May 2020 | May 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV502-SDW | JCAL - JPAC Outdoor Performance Space & Sidewals | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2024 | Sep 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV502-SDW | JCAL - JPAC Outdoor Performance Space & Sidewals | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2024 | Jan 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV502-SDW | JCAL - JPAC Outdoor Performance Space & Sidewals | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2025 | Jul 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV502-SDW | JCAL - JPAC Outdoor Performance Space & Sidewals | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2025 | Oct 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV502-SDW | JCAL - JPAC Outdoor Performance Space & Sidewals | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2025 | Feb 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV502-SDW | JCAL - JPAC Outdoor Performance Space & Sidewals | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2026 | Jun 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV502-SDW | JCAL - JPAC Outdoor Performance Space & Sidewals | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2026 | Oct 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV502-SDW | JCAL - JPAC Outdoor Performance Space & Sidewals | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2026 | Jan 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV502-SDW | JCAL - JPAC Outdoor Performance Space & Sidewals | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2027 | Mar 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV502-SDW | JCAL - JPAC Outdoor Performance Space & Sidewals | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2027 | Apr 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV655QCFM | QCFM - Queen's County Farm Museum Greenhouse Restoration | 2 | DESIGN START | Sep 2011 | Jun 2012 | Sep 2011 | Jun 2012
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV655QCFM | QCFM - Queen's County Farm Museum Greenhouse Restoration | 3 | DESIGN COMPLETION | Jun 2012 | Jun 2014 | Jun 2012 | Jun 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV655QCFM | QCFM - Queen's County Farm Museum Greenhouse Restoration | 4 | CONSTRUCTION START | Jun 2014 | Oct 2015 | Jun 2014 | Oct 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV655QCFM | QCFM - Queen's County Farm Museum Greenhouse Restoration | 5 | CONSTRUCTION COMPLETION | Oct 2015 | Jun 2019 | Oct 2015 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW293QBLV | 120-55 QUEENS BLVD - FIRE ALARM | 1 | PROJECT START | Jun 2016 | Jun 2016 | Jun 2016 | Jun 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW293QBLV | 120-55 QUEENS BLVD - FIRE ALARM | 2 | DESIGN START | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW293QBLV | 120-55 QUEENS BLVD - FIRE ALARM | 3 | DESIGN COMPLETION | Dec 2016 | Sep 2017 | Dec 2016 | Sep 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW293QBLV | 120-55 QUEENS BLVD - FIRE ALARM | 4 | CONSTRUCTION START | Oct 2017 | Mar 2018 | Oct 2017 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW293QBLV | 120-55 QUEENS BLVD - FIRE ALARM | 5 | CONSTRUCTION COMPLETION | Mar 2018 | Mar 2023 | Mar 2018 | Mar 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77417DA | 120-55 QUEENS BLVD.- QUEENS DA TRAINING ROOM | 1 | PROJECT START | Apr 2013 | Apr 2013 | Apr 2013 | Apr 2013
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77417DA | 120-55 QUEENS BLVD.- QUEENS DA TRAINING ROOM | 2 | DESIGN START | Mar 2014 | Mar 2014 | Apr 2013 | Apr 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77417DA | 120-55 QUEENS BLVD.- QUEENS DA TRAINING ROOM | 3 | DESIGN COMPLETION | Feb 2015 | Feb 2015 | Apr 2015 | Jan 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77417DA | 120-55 QUEENS BLVD.- QUEENS DA TRAINING ROOM | 4 | CONSTRUCTION START | Jun 2015 | Aug 2015 | Jan 2018 | May 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77417DA | 120-55 QUEENS BLVD.- QUEENS DA TRAINING ROOM | 5 | CONSTRUCTION COMPLETION | Dec 2015 | Apr 2016 | Jun 2019 | May 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77417P2 | 120-55 QUEENS BLVD - PLAZA, STEPS AND ENTRANCE | 1 | PROJECT START | May 2016 | May 2016 | May 2016 | May 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77417P2 | 120-55 QUEENS BLVD - PLAZA, STEPS AND ENTRANCE | 2 | DESIGN START | Oct 2016 | Oct 2016 | Oct 2016 | Oct 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77417P2 | 120-55 QUEENS BLVD - PLAZA, STEPS AND ENTRANCE | 3 | DESIGN COMPLETION | Oct 2016 | Oct 2017 | Oct 2016 | Oct 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77417P2 | 120-55 QUEENS BLVD - PLAZA, STEPS AND ENTRANCE | 4 | CONSTRUCTION START | Oct 2017 | Oct 2017 | Oct 2017 | Oct 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77417P2 | 120-55 QUEENS BLVD - PLAZA, STEPS AND ENTRANCE | 5 | CONSTRUCTION COMPLETION | Oct 2017 | Oct 2019 | Oct 2017 | Jul 2032
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DDCAC | HVAC Equipment Upgrade in DDC Computer Room | 1 | PROJECT START | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DDCAC | HVAC Equipment Upgrade in DDC Computer Room | 2 | DESIGN START | Mar 2022 | Mar 2022 | Mar 2022 | Mar 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DDCAC | HVAC Equipment Upgrade in DDC Computer Room | 3 | DESIGN COMPLETION | Mar 2022 | Jun 2022 | Mar 2022 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DDCAC | HVAC Equipment Upgrade in DDC Computer Room | 4 | CONSTRUCTION START | Jun 2022 | Jun 2022 | Jun 2022 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DDCAC | HVAC Equipment Upgrade in DDC Computer Room | 5 | CONSTRUCTION COMPLETION | Jun 2022 | May 2024 | Jun 2022 | May 2029
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | 1 | DEVELOP SCOPE | Jan 2017 | Mar 2017 | Jan 2020 | Jan 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | 2 | PRELIMINARY DESIGN | Apr 2017 | Jul 2017 | Jan 2020 | Jan 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | 3 | FINAL DESIGN | Jul 2017 | Jan 2018 | Jan 2020 | Jan 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2018 | Apr 2018 | Jan 2020 | Jan 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | 5 | CONSTRUCTION TO 25% | Apr 2018 | Aug 2018 | Jan 2020 | Jan 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | 6 | CONSTRUCTION TO 50% | Aug 2018 | Dec 2018 | Jan 2020 | Jan 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | 7 | CONSTRUCTION TO 75% | Dec 2018 | Apr 2019 | Jan 2020 | Jan 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2019 | Jul 2019 | Jan 2020 | Jan 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | 9 | SUBSTANTIAL COMPLETION | Jul 2019 | Sep 2019 | Jan 2020 | Jan 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Oct 2019 | Jan 2020 | Jan 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | 11 | PROJECT START | Sep 2019 | Oct 2019 | Jan 2020 | Jan 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | 12 | DESIGN START | Sep 2019 | Oct 2019 | Jan 2020 | Sep 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | 13 | DESIGN COMPLETION | Sep 2019 | Oct 2019 | Sep 2020 | Sep 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | 14 | CONSTRUCTION START | Sep 2019 | Oct 2019 | Sep 2021 | Sep 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | 15 | CONSTRUCTION COMPLETION | Sep 2019 | Oct 2019 | Sep 2022 | Sep 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD99WNY1 | CENTER FOR THE WOMEN OF NEW YORK | 1 | DEVELOP SCOPE | Jul 2008 | Sep 2008 | May 2017 | May 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD99WNY1 | CENTER FOR THE WOMEN OF NEW YORK | 2 | PRELIMINARY DESIGN | Sep 2008 | Jan 2009 | May 2017 | Nov 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD99WNY1 | CENTER FOR THE WOMEN OF NEW YORK | 3 | FINAL DESIGN | Jan 2009 | Jul 2009 | May 2018 | Dec 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD99WNY1 | CENTER FOR THE WOMEN OF NEW YORK | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2009 | Oct 2009 | Jul 2019 | Jul 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD99WNY1 | CENTER FOR THE WOMEN OF NEW YORK | 5 | CONSTRUCTION TO 25% | Oct 2009 | Feb 2010 | Sep 2021 | Jun 2030
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD99WNY1 | CENTER FOR THE WOMEN OF NEW YORK | 6 | CONSTRUCTION TO 50% | Feb 2010 | Jun 2010 | Sep 2021 | Jun 2030
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD99WNY1 | CENTER FOR THE WOMEN OF NEW YORK | 7 | CONSTRUCTION TO 75% | Jun 2010 | Oct 2010 | Sep 2021 | Jun 2030
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD99WNY1 | CENTER FOR THE WOMEN OF NEW YORK | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2010 | Jan 2011 | Sep 2021 | Jun 2030
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD99WNY1 | CENTER FOR THE WOMEN OF NEW YORK | 9 | SUBSTANTIAL COMPLETION | Jan 2011 | Mar 2011 | Sep 2021 | Jun 2030
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD99WNY1 | CENTER FOR THE WOMEN OF NEW YORK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2011 | Apr 2011 | Sep 2021 | Jun 2030
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWQ077AT2 | 120-55 QUEENS BLVD- QUEENS BOROUGH HALL ATRIUM | 1 | PROJECT START | Jun 2012 | Jun 2012 | Feb 2012 | Feb 2012
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWQ077AT2 | 120-55 QUEENS BLVD- QUEENS BOROUGH HALL ATRIUM | 2 | DESIGN START | Jun 2012 | Jun 2012 | Feb 2013 | Feb 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWQ077AT2 | 120-55 QUEENS BLVD- QUEENS BOROUGH HALL ATRIUM | 3 | DESIGN COMPLETION | Jun 2012 | Jun 2012 | Feb 2015 | Apr 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWQ077AT2 | 120-55 QUEENS BLVD- QUEENS BOROUGH HALL ATRIUM | 4 | CONSTRUCTION START | Jun 2012 | Jun 2012 | Apr 2017 | Jun 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWQ077AT2 | 120-55 QUEENS BLVD- QUEENS BOROUGH HALL ATRIUM | 5 | CONSTRUCTION COMPLETION | Aug 2015 | Aug 2015 | Jun 2018 | Aug 2032
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023B | Distr & Trunk WM Replacement Cypress Ave, Queens (Joint Bid) | 1 | DEVELOP SCOPE | Dec 2013 | Sep 2014 | Jun 2025 | Jun 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023B | Distr & Trunk WM Replacement Cypress Ave, Queens (Joint Bid) | 2 | PRELIMINARY DESIGN | Sep 2014 | Sep 2015 | Jul 2014 | Sep 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023B | Distr & Trunk WM Replacement Cypress Ave, Queens (Joint Bid) | 3 | FINAL DESIGN | Sep 2015 | Mar 2017 | Sep 2017 | Dec 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023B | Distr & Trunk WM Replacement Cypress Ave, Queens (Joint Bid) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2017 | Dec 2017 | Dec 2017 | Dec 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023B | Distr & Trunk WM Replacement Cypress Ave, Queens (Joint Bid) | 5 | CONSTRUCTION TO 25% | Dec 2017 | Nov 2018 | Jul 2014 | Jul 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023B | Distr & Trunk WM Replacement Cypress Ave, Queens (Joint Bid) | 6 | CONSTRUCTION TO 50% | Nov 2018 | Nov 2019 | Jul 2014 | Jul 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023B | Distr & Trunk WM Replacement Cypress Ave, Queens (Joint Bid) | 7 | CONSTRUCTION TO 75% | Nov 2019 | Nov 2020 | Jul 2014 | Jul 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023B | Distr & Trunk WM Replacement Cypress Ave, Queens (Joint Bid) | 8 | ORIGINAL EQUIP & FURNISHING | Nov 2020 | Aug 2021 | Aug 2021 | Aug 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023B | Distr & Trunk WM Replacement Cypress Ave, Queens (Joint Bid) | 9 | SUBSTANTIAL COMPLETION | Aug 2021 | Feb 2022 | Aug 2021 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023B | Distr & Trunk WM Replacement Cypress Ave, Queens (Joint Bid) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2022 | May 2022 | Jun 2023 | Jun 2032
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1027 | Replacement of Dist WM in 222nd St | 1 | DEVELOP SCOPE | Mar 2019 | May 2019 | Mar 2019 | May 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1027 | Replacement of Dist WM in 222nd St | 2 | PRELIMINARY DESIGN | May 2019 | Sep 2019 | May 2019 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1027 | Replacement of Dist WM in 222nd St | 3 | FINAL DESIGN | Sep 2019 | Mar 2020 | Sep 2019 | Mar 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1027 | Replacement of Dist WM in 222nd St | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Jun 2020 | Mar 2020 | Jun 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1027 | Replacement of Dist WM in 222nd St | 5 | CONSTRUCTION TO 25% | Jun 2020 | Oct 2020 | Jun 2020 | Oct 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1027 | Replacement of Dist WM in 222nd St | 6 | CONSTRUCTION TO 50% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1027 | Replacement of Dist WM in 222nd St | 7 | CONSTRUCTION TO 75% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1027 | Replacement of Dist WM in 222nd St | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1027 | Replacement of Dist WM in 222nd St | 9 | SUBSTANTIAL COMPLETION | Sep 2021 | Nov 2021 | Sep 2021 | Nov 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1027 | Replacement of Dist WM in 222nd St | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2021 | Dec 2021 | Nov 2021 | Jun 2029
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1030 | Water Main & Sewer Work, Beach Channel Drive Area (SANDHW11) | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1030 | Water Main & Sewer Work, Beach Channel Drive Area (SANDHW11) | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1030 | Water Main & Sewer Work, Beach Channel Drive Area (SANDHW11) | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1030 | Water Main & Sewer Work, Beach Channel Drive Area (SANDHW11) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1030 | Water Main & Sewer Work, Beach Channel Drive Area (SANDHW11) | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1030 | Water Main & Sewer Work, Beach Channel Drive Area (SANDHW11) | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1030 | Water Main & Sewer Work, Beach Channel Drive Area (SANDHW11) | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1030 | Water Main & Sewer Work, Beach Channel Drive Area (SANDHW11) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1030 | Water Main & Sewer Work, Beach Channel Drive Area (SANDHW11) | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1030 | Water Main & Sewer Work, Beach Channel Drive Area (SANDHW11) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Jun 2029
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1040B | Dist. WM work along Woodhaven Blvd, Phase B (HWQ100SBB) | 1 | DEVELOP SCOPE | Sep 2021 | May 2022 | Sep 2021 | May 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1040B | Dist. WM work along Woodhaven Blvd, Phase B (HWQ100SBB) | 2 | PRELIMINARY DESIGN | May 2022 | May 2023 | May 2022 | May 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1040B | Dist. WM work along Woodhaven Blvd, Phase B (HWQ100SBB) | 3 | FINAL DESIGN | May 2023 | Nov 2024 | May 2023 | Nov 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1040B | Dist. WM work along Woodhaven Blvd, Phase B (HWQ100SBB) | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2024 | Aug 2025 | Nov 2024 | Aug 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1040B | Dist. WM work along Woodhaven Blvd, Phase B (HWQ100SBB) | 5 | CONSTRUCTION TO 25% | Aug 2025 | Aug 2026 | Aug 2025 | Aug 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1040B | Dist. WM work along Woodhaven Blvd, Phase B (HWQ100SBB) | 6 | CONSTRUCTION TO 50% | Aug 2026 | Aug 2027 | Aug 2026 | Aug 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1040B | Dist. WM work along Woodhaven Blvd, Phase B (HWQ100SBB) | 7 | CONSTRUCTION TO 75% | Aug 2027 | Jul 2028 | Aug 2027 | Jul 2028
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1040B | Dist. WM work along Woodhaven Blvd, Phase B (HWQ100SBB) | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2028 | Apr 2029 | Jul 2028 | Apr 2029
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1040B | Dist. WM work along Woodhaven Blvd, Phase B (HWQ100SBB) | 9 | SUBSTANTIAL COMPLETION | Apr 2029 | Oct 2029 | Apr 2029 | Oct 2029
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1040B | Dist. WM work along Woodhaven Blvd, Phase B (HWQ100SBB) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2029 | Jan 2030 | Oct 2029 | Jan 2030
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1042A | Watermain replacement & sewer repair on Queens Blvd-HWQ1190A | 1 | DEVELOP SCOPE | Mar 2020 | May 2020 | Mar 2020 | May 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1042A | Watermain replacement & sewer repair on Queens Blvd-HWQ1190A | 2 | PRELIMINARY DESIGN | May 2020 | Sep 2020 | May 2020 | Sep 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1042A | Watermain replacement & sewer repair on Queens Blvd-HWQ1190A | 3 | FINAL DESIGN | Sep 2020 | Mar 2021 | Sep 2020 | Mar 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1042A | Watermain replacement & sewer repair on Queens Blvd-HWQ1190A | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2021 | Jun 2021 | Mar 2021 | Jun 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1042A | Watermain replacement & sewer repair on Queens Blvd-HWQ1190A | 5 | CONSTRUCTION TO 25% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1042A | Watermain replacement & sewer repair on Queens Blvd-HWQ1190A | 6 | CONSTRUCTION TO 50% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1042A | Watermain replacement & sewer repair on Queens Blvd-HWQ1190A | 7 | CONSTRUCTION TO 75% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1042A | Watermain replacement & sewer repair on Queens Blvd-HWQ1190A | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1042A | Watermain replacement & sewer repair on Queens Blvd-HWQ1190A | 9 | SUBSTANTIAL COMPLETION | Sep 2022 | Nov 2022 | Sep 2022 | Nov 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1042A | Watermain replacement & sewer repair on Queens Blvd-HWQ1190A | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2022 | Dec 2022 | Nov 2022 | Nov 2030
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1044 | Replacement of Water Mains in Beach 108th Street (SANDR04) | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1044 | Replacement of Water Mains in Beach 108th Street (SANDR04) | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1044 | Replacement of Water Mains in Beach 108th Street (SANDR04) | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Oct 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1044 | Replacement of Water Mains in Beach 108th Street (SANDR04) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Nov 2019 | Jan 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1044 | Replacement of Water Mains in Beach 108th Street (SANDR04) | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jan 2020 | May 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1044 | Replacement of Water Mains in Beach 108th Street (SANDR04) | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | May 2020 | Sep 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1044 | Replacement of Water Mains in Beach 108th Street (SANDR04) | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Sep 2020 | Jan 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1044 | Replacement of Water Mains in Beach 108th Street (SANDR04) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jan 2021 | Apr 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1044 | Replacement of Water Mains in Beach 108th Street (SANDR04) | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Apr 2021 | Jun 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1044 | Replacement of Water Mains in Beach 108th Street (SANDR04) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Jun 2021 | Jul 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1049 | Rplmnt WM at 111 St btw 45th & Corona Ave (HWD10311) | 1 | DEVELOP SCOPE | Jun 2021 | Aug 2021 | Jun 2021 | Aug 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1049 | Rplmnt WM at 111 St btw 45th & Corona Ave (HWD10311) | 2 | PRELIMINARY DESIGN | Aug 2021 | Dec 2021 | Aug 2021 | Dec 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1049 | Rplmnt WM at 111 St btw 45th & Corona Ave (HWD10311) | 3 | FINAL DESIGN | Dec 2021 | Jun 2022 | Dec 2021 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1049 | Rplmnt WM at 111 St btw 45th & Corona Ave (HWD10311) | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1049 | Rplmnt WM at 111 St btw 45th & Corona Ave (HWD10311) | 5 | CONSTRUCTION TO 25% | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1049 | Rplmnt WM at 111 St btw 45th & Corona Ave (HWD10311) | 6 | CONSTRUCTION TO 50% | Jan 2023 | May 2023 | Jan 2023 | May 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1049 | Rplmnt WM at 111 St btw 45th & Corona Ave (HWD10311) | 7 | CONSTRUCTION TO 75% | May 2023 | Sep 2023 | May 2023 | Sep 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1049 | Rplmnt WM at 111 St btw 45th & Corona Ave (HWD10311) | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Dec 2023 | Sep 2023 | Dec 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1049 | Rplmnt WM at 111 St btw 45th & Corona Ave (HWD10311) | 9 | SUBSTANTIAL COMPLETION | Dec 2023 | Feb 2024 | Dec 2023 | Feb 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1049 | Rplmnt WM at 111 St btw 45th & Corona Ave (HWD10311) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2024 | Mar 2024 | Feb 2024 | Mar 2029
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1051 | Water Main Replacement in Maspeth Avenue | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2020 | Jun 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1051 | Water Main Replacement in Maspeth Avenue | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Jun 2020 | Oct 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1051 | Water Main Replacement in Maspeth Avenue | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Oct 2020 | Apr 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1051 | Water Main Replacement in Maspeth Avenue | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Apr 2021 | Jul 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1051 | Water Main Replacement in Maspeth Avenue | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Jul 2021 | Nov 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1051 | Water Main Replacement in Maspeth Avenue | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Nov 2021 | Mar 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1051 | Water Main Replacement in Maspeth Avenue | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | Mar 2022 | Jul 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1051 | Water Main Replacement in Maspeth Avenue | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Jul 2022 | Oct 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1051 | Water Main Replacement in Maspeth Avenue | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Oct 2022 | Dec 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1051 | Water Main Replacement in Maspeth Avenue | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Dec 2022 | Jun 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1054 | Dist WM work in Ellwell Crescent from Alderton to Carlton St | 1 | DEVELOP SCOPE | Nov 2020 | Aug 2021 | Nov 2020 | Aug 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1054 | Dist WM work in Ellwell Crescent from Alderton to Carlton St | 2 | PRELIMINARY DESIGN | Aug 2021 | Jul 2022 | Aug 2021 | Jul 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1054 | Dist WM work in Ellwell Crescent from Alderton to Carlton St | 3 | FINAL DESIGN | Aug 2022 | Jan 2024 | Aug 2022 | Jan 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1054 | Dist WM work in Ellwell Crescent from Alderton to Carlton St | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2024 | Oct 2024 | Jan 2024 | Oct 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1054 | Dist WM work in Ellwell Crescent from Alderton to Carlton St | 5 | CONSTRUCTION TO 25% | Oct 2024 | Oct 2025 | Oct 2024 | Oct 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1054 | Dist WM work in Ellwell Crescent from Alderton to Carlton St | 6 | CONSTRUCTION TO 50% | Oct 2025 | Oct 2026 | Oct 2025 | Oct 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1054 | Dist WM work in Ellwell Crescent from Alderton to Carlton St | 7 | CONSTRUCTION TO 75% | Oct 2026 | Oct 2027 | Oct 2026 | Oct 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1054 | Dist WM work in Ellwell Crescent from Alderton to Carlton St | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jun 2028 | Oct 2027 | Jun 2028
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1054 | Dist WM work in Ellwell Crescent from Alderton to Carlton St | 9 | SUBSTANTIAL COMPLETION | Jun 2028 | Dec 2028 | Jun 2028 | Dec 2028
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1054 | Dist WM work in Ellwell Crescent from Alderton to Carlton St | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2028 | Mar 2029 | Dec 2028 | Mar 2029
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1055 | Dist. WM work in Jay Ave btwn Borden Ave & 66th St, QNS | 1 | DEVELOP SCOPE | Nov 2020 | Aug 2021 | Nov 2020 | Aug 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1055 | Dist. WM work in Jay Ave btwn Borden Ave & 66th St, QNS | 2 | PRELIMINARY DESIGN | Aug 2021 | Jul 2022 | Aug 2021 | Jul 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1055 | Dist. WM work in Jay Ave btwn Borden Ave & 66th St, QNS | 3 | FINAL DESIGN | Aug 2022 | Jan 2024 | Aug 2022 | Jan 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1055 | Dist. WM work in Jay Ave btwn Borden Ave & 66th St, QNS | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2024 | Oct 2024 | Jan 2024 | Oct 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1055 | Dist. WM work in Jay Ave btwn Borden Ave & 66th St, QNS | 5 | CONSTRUCTION TO 25% | Oct 2024 | Oct 2025 | Oct 2024 | Oct 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1055 | Dist. WM work in Jay Ave btwn Borden Ave & 66th St, QNS | 6 | CONSTRUCTION TO 50% | Oct 2025 | Oct 2026 | Oct 2025 | Oct 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1055 | Dist. WM work in Jay Ave btwn Borden Ave & 66th St, QNS | 7 | CONSTRUCTION TO 75% | Oct 2026 | Oct 2027 | Oct 2026 | Oct 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1055 | Dist. WM work in Jay Ave btwn Borden Ave & 66th St, QNS | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jun 2028 | Oct 2027 | Jun 2028
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1055 | Dist. WM work in Jay Ave btwn Borden Ave & 66th St, QNS | 9 | SUBSTANTIAL COMPLETION | Jun 2028 | Dec 2028 | Jun 2028 | Dec 2028
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1055 | Dist. WM work in Jay Ave btwn Borden Ave & 66th St, QNS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2028 | Mar 2029 | Dec 2028 | Mar 2029
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1056 | Dist WM work in 43rd Ave btwn National St & 104 St, QNS | 1 | DEVELOP SCOPE | Nov 2020 | Aug 2021 | Nov 2020 | Aug 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1056 | Dist WM work in 43rd Ave btwn National St & 104 St, QNS | 2 | PRELIMINARY DESIGN | Aug 2021 | Jul 2022 | Aug 2021 | Jul 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1056 | Dist WM work in 43rd Ave btwn National St & 104 St, QNS | 3 | FINAL DESIGN | Aug 2022 | Jan 2024 | Aug 2022 | Jan 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1056 | Dist WM work in 43rd Ave btwn National St & 104 St, QNS | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2024 | Oct 2024 | Jan 2024 | Oct 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1056 | Dist WM work in 43rd Ave btwn National St & 104 St, QNS | 5 | CONSTRUCTION TO 25% | Oct 2024 | Oct 2025 | Oct 2024 | Oct 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1056 | Dist WM work in 43rd Ave btwn National St & 104 St, QNS | 6 | CONSTRUCTION TO 50% | Oct 2025 | Oct 2026 | Oct 2025 | Oct 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1056 | Dist WM work in 43rd Ave btwn National St & 104 St, QNS | 7 | CONSTRUCTION TO 75% | Oct 2026 | Oct 2027 | Oct 2026 | Oct 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1056 | Dist WM work in 43rd Ave btwn National St & 104 St, QNS | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jun 2028 | Oct 2027 | Jun 2028
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1056 | Dist WM work in 43rd Ave btwn National St & 104 St, QNS | 9 | SUBSTANTIAL COMPLETION | Jun 2028 | Dec 2028 | Jun 2028 | Dec 2028
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1056 | Dist WM work in 43rd Ave btwn National St & 104 St, QNS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2028 | Mar 2029 | Dec 2028 | Mar 2029
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1062 | WM Lining in Porpoise Bridge Flushing Meadows QNS, HBPED800Q | 1 | DEVELOP SCOPE | Sep 2021 | Dec 2021 | Sep 2021 | Dec 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1062 | WM Lining in Porpoise Bridge Flushing Meadows QNS, HBPED800Q | 2 | PRELIMINARY DESIGN | Dec 2021 | Mar 2022 | Dec 2021 | Mar 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1062 | WM Lining in Porpoise Bridge Flushing Meadows QNS, HBPED800Q | 3 | FINAL DESIGN | Apr 2022 | Sep 2022 | Apr 2022 | Sep 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1062 | WM Lining in Porpoise Bridge Flushing Meadows QNS, HBPED800Q | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1062 | WM Lining in Porpoise Bridge Flushing Meadows QNS, HBPED800Q | 5 | CONSTRUCTION TO 25% | Dec 2022 | Apr 2023 | Dec 2022 | Apr 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1062 | WM Lining in Porpoise Bridge Flushing Meadows QNS, HBPED800Q | 6 | CONSTRUCTION TO 50% | Apr 2023 | Aug 2023 | Apr 2023 | Aug 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1062 | WM Lining in Porpoise Bridge Flushing Meadows QNS, HBPED800Q | 7 | CONSTRUCTION TO 75% | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1062 | WM Lining in Porpoise Bridge Flushing Meadows QNS, HBPED800Q | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2023 | Mar 2024 | Dec 2023 | Mar 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1062 | WM Lining in Porpoise Bridge Flushing Meadows QNS, HBPED800Q | 9 | SUBSTANTIAL COMPLETION | Mar 2024 | May 2024 | Mar 2024 | May 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1062 | WM Lining in Porpoise Bridge Flushing Meadows QNS, HBPED800Q | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Jun 2024 | May 2024 | Jun 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-976 | SEQ - Trunk Water Main in Francis Lewis Blvd | 1 | DEVELOP SCOPE | May 2007 | Jul 2007 | May 2007 | Jul 2007
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-976 | SEQ - Trunk Water Main in Francis Lewis Blvd | 2 | PRELIMINARY DESIGN | Jul 2007 | Nov 2007 | Jul 2007 | Nov 2007
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-976 | SEQ - Trunk Water Main in Francis Lewis Blvd | 3 | FINAL DESIGN | Nov 2007 | May 2008 | Nov 2007 | May 2008
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-976 | SEQ - Trunk Water Main in Francis Lewis Blvd | 4 | BID AWARD AND REGISTER CONTRCT | May 2008 | Aug 2008 | Mar 2019 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-976 | SEQ - Trunk Water Main in Francis Lewis Blvd | 5 | CONSTRUCTION TO 25% | Aug 2008 | Dec 2008 | Jun 2019 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-976 | SEQ - Trunk Water Main in Francis Lewis Blvd | 6 | CONSTRUCTION TO 50% | Dec 2008 | Apr 2009 | Jun 2019 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-976 | SEQ - Trunk Water Main in Francis Lewis Blvd | 7 | CONSTRUCTION TO 75% | Apr 2009 | Aug 2009 | Jun 2019 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-976 | SEQ - Trunk Water Main in Francis Lewis Blvd | 8 | ORIGINAL EQUIP & FURNISHING | Aug 2009 | Nov 2009 | Jun 2019 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-976 | SEQ - Trunk Water Main in Francis Lewis Blvd | 9 | SUBSTANTIAL COMPLETION | Nov 2009 | Jan 2010 | Jun 2019 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-976 | SEQ - Trunk Water Main in Francis Lewis Blvd | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2010 | Feb 2010 | Dec 2020 | Jan 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-976 | SEQ - Trunk Water Main in Francis Lewis Blvd | 11 | PROJECT START | Jan 2010 | Feb 2010 | Jan 2022 | Jan 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-976 | SEQ - Trunk Water Main in Francis Lewis Blvd | 12 | DESIGN START | Jan 2010 | Feb 2010 | Jan 2022 | Jan 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-976 | SEQ - Trunk Water Main in Francis Lewis Blvd | 13 | DESIGN COMPLETION | Jan 2010 | Feb 2010 | Jan 2022 | Jan 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-976 | SEQ - Trunk Water Main in Francis Lewis Blvd | 14 | CONSTRUCTION START | Jan 2010 | Feb 2010 | Jan 2022 | Jan 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-976 | SEQ - Trunk Water Main in Francis Lewis Blvd | 15 | CONSTRUCTION COMPLETION | Jan 2010 | Feb 2010 | Jan 2022 | Jun 2032
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-991 | New WM, Trunk Main Ext, 33 Ave & Francis Lewis Blvd, Queens | 1 | DEVELOP SCOPE | Oct 2014 | May 2015 | Oct 2014 | May 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-991 | New WM, Trunk Main Ext, 33 Ave & Francis Lewis Blvd, Queens | 2 | PRELIMINARY DESIGN | May 2014 | May 2015 | May 2014 | May 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-991 | New WM, Trunk Main Ext, 33 Ave & Francis Lewis Blvd, Queens | 3 | FINAL DESIGN | May 2015 | Mar 2016 | May 2015 | Mar 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-991 | New WM, Trunk Main Ext, 33 Ave & Francis Lewis Blvd, Queens | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2016 | Jun 2016 | Mar 2016 | Jun 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-991 | New WM, Trunk Main Ext, 33 Ave & Francis Lewis Blvd, Queens | 5 | CONSTRUCTION TO 25% | Jun 2016 | Dec 2016 | Jun 2016 | Dec 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-991 | New WM, Trunk Main Ext, 33 Ave & Francis Lewis Blvd, Queens | 6 | CONSTRUCTION TO 50% | Dec 2016 | Jul 2017 | Dec 2016 | Jul 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-991 | New WM, Trunk Main Ext, 33 Ave & Francis Lewis Blvd, Queens | 7 | CONSTRUCTION TO 75% | Jul 2017 | May 2018 | Jul 2017 | May 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-991 | New WM, Trunk Main Ext, 33 Ave & Francis Lewis Blvd, Queens | 8 | ORIGINAL EQUIP & FURNISHING | May 2018 | Jul 2018 | May 2018 | Jul 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-991 | New WM, Trunk Main Ext, 33 Ave & Francis Lewis Blvd, Queens | 9 | SUBSTANTIAL COMPLETION | Aug 2018 | Sep 2018 | Aug 2018 | Sep 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-991 | New WM, Trunk Main Ext, 33 Ave & Francis Lewis Blvd, Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2018 | Oct 2018 | Sep 2018 | Jun 2029
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-419L | OAU Offices Expansion at CRS | 1 | DEVELOP SCOPE | Jun 2014 | Jul 2014 | Jun 2014 | Jul 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-419L | OAU Offices Expansion at CRS | 2 | PRELIMINARY DESIGN | Jul 2014 | Jan 2015 | Jul 2014 | Dec 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-419L | OAU Offices Expansion at CRS | 3 | FINAL DESIGN | Feb 2015 | Aug 2015 | Dec 2016 | Jan 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-419L | OAU Offices Expansion at CRS | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2015 | Mar 2016 | Jan 2019 | Dec 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-419L | OAU Offices Expansion at CRS | 5 | CONSTRUCTION TO 25% | Mar 2016 | Sep 2016 | Dec 2019 | Dec 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-419L | OAU Offices Expansion at CRS | 6 | CONSTRUCTION TO 50% | Sep 2016 | Apr 2017 | Dec 2019 | Dec 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-419L | OAU Offices Expansion at CRS | 7 | CONSTRUCTION TO 75% | Apr 2017 | Oct 2017 | Dec 2019 | Dec 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-419L | OAU Offices Expansion at CRS | 8 | SUBSTANTIAL COMPLETION | Oct 2017 | May 2018 | Dec 2019 | Apr 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-419L | OAU Offices Expansion at CRS | 9 | PUNCHLIST COMPLETE, JOB CLOSED | May 2018 | Feb 2021 | Apr 2021 | Apr 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-423 | Queens 11/13 FLOOR SLAB REPLACEMENT | 1 | DEVELOP SCOPE | Jul 2014 | Aug 2014 | Dec 2015 | Mar 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-423 | Queens 11/13 FLOOR SLAB REPLACEMENT | 2 | PRELIMINARY DESIGN | Aug 2014 | Apr 2015 | Mar 2017 | Mar 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-423 | Queens 11/13 FLOOR SLAB REPLACEMENT | 3 | FINAL DESIGN | Apr 2015 | Apr 2016 | Mar 2019 | Mar 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-423 | Queens 11/13 FLOOR SLAB REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2016 | Sep 2017 | Apr 2020 | Dec 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-423 | Queens 11/13 FLOOR SLAB REPLACEMENT | 5 | CONSTRUCTION TO 25% | Sep 2017 | Nov 2025 | Jan 2021 | Dec 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-423 | Queens 11/13 FLOOR SLAB REPLACEMENT | 6 | CONSTRUCTION TO 50% | Nov 2025 | Nov 2025 | Jan 2022 | Apr 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-423 | Queens 11/13 FLOOR SLAB REPLACEMENT | 7 | CONSTRUCTION TO 75% | Nov 2025 | Nov 2025 | May 2022 | Aug 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-423 | Queens 11/13 FLOOR SLAB REPLACEMENT | 8 | SUBSTANTIAL COMPLETION | Nov 2025 | Nov 2025 | Aug 2022 | Nov 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-423 | Queens 11/13 FLOOR SLAB REPLACEMENT | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2025 | May 2031 | Nov 2022 | Jul 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-423 | Queens 11/13 FLOOR SLAB REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2025 | May 2031 | Aug 2023 | Dec 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-438 | QUEENS 7 GARAGE REHABILITATION | 1 | PROJECT START | Sep 2015 | Sep 2015 | Sep 2015 | Sep 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-438 | QUEENS 7 GARAGE REHABILITATION | 2 | DESIGN START | Sep 2015 | Nov 2016 | Sep 2015 | Apr 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-438 | QUEENS 7 GARAGE REHABILITATION | 3 | DESIGN COMPLETION | Nov 2016 | Jun 2018 | Apr 2017 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-438 | QUEENS 7 GARAGE REHABILITATION | 4 | CONSTRUCTION START | Jun 2018 | Apr 2019 | Jun 2019 | Feb 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-438 | QUEENS 7 GARAGE REHABILITATION | 5 | CONSTRUCTION COMPLETION | Apr 2019 | Nov 2021 | Feb 2020 | Jun 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | 1 | DEVELOP SCOPE | Mar 2017 | Mar 2017 | Mar 2017 | Mar 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | 2 | PRELIMINARY DESIGN | Mar 2017 | Mar 2017 | Mar 2017 | Mar 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | 3 | FINAL DESIGN | Mar 2017 | Mar 2017 | Mar 2017 | Mar 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2017 | Mar 2017 | Mar 2017 | Mar 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | 5 | CONSTRUCTION TO 25% | Mar 2017 | Mar 2017 | Mar 2017 | Mar 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | 6 | CONSTRUCTION TO 50% | Mar 2017 | Mar 2017 | Mar 2017 | Mar 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | 7 | CONSTRUCTION TO 75% | Mar 2017 | Mar 2017 | Mar 2017 | Mar 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2017 | Mar 2017 | Mar 2017 | Mar 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | 9 | SUBSTANTIAL COMPLETION | Mar 2017 | Mar 2017 | Mar 2017 | Mar 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2017 | Mar 2017 | Mar 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | 11 | PROJECT START | Mar 2017 | Mar 2017 | Mar 2017 | Mar 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | 12 | DESIGN START | Mar 2017 | Sep 2017 | Mar 2017 | Sep 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | 13 | DESIGN COMPLETION | Sep 2017 | Sep 2018 | Sep 2017 | Sep 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | 14 | CONSTRUCTION START | Sep 2018 | Mar 2019 | Sep 2018 | Mar 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANBROAD2 | BROAD CHANNEL LIBRARY GUTTERS AND LEADERS | 15 | CONSTRUCTION COMPLETION | Mar 2019 | Mar 2023 | Mar 2019 | Mar 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBROAD | SANDY DAMAGES BROAD CHANNEL BRANCH LIBRARY | 1 | PROJECT START | Nov 2012 | Nov 2012 | Nov 2012 | Nov 2012
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBROAD | SANDY DAMAGES BROAD CHANNEL BRANCH LIBRARY | 2 | DESIGN START | Nov 2012 | Nov 2012 | Nov 2012 | Nov 2012
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBROAD | SANDY DAMAGES BROAD CHANNEL BRANCH LIBRARY | 3 | DESIGN COMPLETION | Nov 2012 | Nov 2012 | Nov 2012 | Nov 2012
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBROAD | SANDY DAMAGES BROAD CHANNEL BRANCH LIBRARY | 4 | CONSTRUCTION START | Nov 2012 | Jan 2016 | Nov 2012 | Apr 2013
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBROAD | SANDY DAMAGES BROAD CHANNEL BRANCH LIBRARY | 5 | CONSTRUCTION COMPLETION | Jan 2016 | Jan 2016 | Apr 2013 | Apr 2031
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC5 | 100 the precint electrical system replacement, Sandy | 1 | PROJECT START | Jan 2013 | Jan 2013 | Jan 2013 | Jan 2013
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC5 | 100 the precint electrical system replacement, Sandy | 2 | DESIGN START | Jan 2013 | Jan 2013 | Jan 2013 | Jan 2013
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC5 | 100 the precint electrical system replacement, Sandy | 3 | DESIGN COMPLETION | Jan 2013 | Mar 2013 | Jan 2013 | Mar 2013
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC5 | 100 the precint electrical system replacement, Sandy | 4 | CONSTRUCTION START | Mar 2013 | Apr 2014 | Mar 2013 | Apr 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC5 | 100 the precint electrical system replacement, Sandy | 5 | CONSTRUCTION COMPLETION | Apr 2014 | Dec 2014 | Apr 2014 | Jun 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW11 | Recon of Beach Channel Drive - Hurricane Sandy (QED-1030) | 1 | DEVELOP SCOPE | Feb 2016 | May 2016 | Feb 2014 | Sep 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW11 | Recon of Beach Channel Drive - Hurricane Sandy (QED-1030) | 2 | PRELIMINARY DESIGN | May 2016 | Sep 2016 | Sep 2014 | Jun 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW11 | Recon of Beach Channel Drive - Hurricane Sandy (QED-1030) | 3 | FINAL DESIGN | Sep 2016 | Mar 2017 | Jun 2016 | Dec 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW11 | Recon of Beach Channel Drive - Hurricane Sandy (QED-1030) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2017 | Jun 2017 | Dec 2016 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW11 | Recon of Beach Channel Drive - Hurricane Sandy (QED-1030) | 5 | CONSTRUCTION TO 25% | Jun 2017 | Oct 2017 | Mar 2018 | Jul 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW11 | Recon of Beach Channel Drive - Hurricane Sandy (QED-1030) | 6 | CONSTRUCTION TO 50% | Oct 2017 | Feb 2018 | Jul 2018 | Nov 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW11 | Recon of Beach Channel Drive - Hurricane Sandy (QED-1030) | 7 | CONSTRUCTION TO 75% | Feb 2018 | Jun 2018 | Nov 2018 | Mar 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW11 | Recon of Beach Channel Drive - Hurricane Sandy (QED-1030) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2018 | Sep 2018 | Mar 2019 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW11 | Recon of Beach Channel Drive - Hurricane Sandy (QED-1030) | 9 | SUBSTANTIAL COMPLETION | Sep 2018 | Nov 2018 | Jun 2019 | Aug 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW11 | Recon of Beach Channel Drive - Hurricane Sandy (QED-1030) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2018 | Dec 2018 | Aug 2019 | Jun 2035
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW12 | Reconstruction of Edgemere - Hurricane Sandy (QED-1007) | 1 | DEVELOP SCOPE | Feb 2016 | May 2016 | Feb 2016 | May 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW12 | Reconstruction of Edgemere - Hurricane Sandy (QED-1007) | 2 | PRELIMINARY DESIGN | May 2016 | Sep 2016 | May 2016 | Sep 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW12 | Reconstruction of Edgemere - Hurricane Sandy (QED-1007) | 3 | FINAL DESIGN | Sep 2016 | Mar 2017 | Sep 2016 | Mar 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW12 | Reconstruction of Edgemere - Hurricane Sandy (QED-1007) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2017 | Jun 2017 | Mar 2017 | Aug 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW12 | Reconstruction of Edgemere - Hurricane Sandy (QED-1007) | 5 | CONSTRUCTION TO 25% | Jun 2017 | Oct 2017 | Aug 2018 | Dec 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW12 | Reconstruction of Edgemere - Hurricane Sandy (QED-1007) | 6 | CONSTRUCTION TO 50% | Oct 2017 | Feb 2018 | Dec 2018 | Apr 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW12 | Reconstruction of Edgemere - Hurricane Sandy (QED-1007) | 7 | CONSTRUCTION TO 75% | Feb 2018 | Jun 2018 | Apr 2019 | Jul 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW12 | Reconstruction of Edgemere - Hurricane Sandy (QED-1007) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2018 | Sep 2018 | Aug 2019 | Oct 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW12 | Reconstruction of Edgemere - Hurricane Sandy (QED-1007) | 9 | SUBSTANTIAL COMPLETION | Sep 2018 | Nov 2018 | Oct 2019 | Dec 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW12 | Reconstruction of Edgemere - Hurricane Sandy (QED-1007) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2018 | Dec 2018 | Dec 2019 | Aug 2032
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW13 | Reconstruction of Rockaway Beach - Hurricane Sandy (QED-982) | 1 | DEVELOP SCOPE | Feb 2016 | May 2016 | Feb 2016 | May 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW13 | Reconstruction of Rockaway Beach - Hurricane Sandy (QED-982) | 2 | PRELIMINARY DESIGN | May 2016 | Sep 2016 | May 2016 | Sep 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW13 | Reconstruction of Rockaway Beach - Hurricane Sandy (QED-982) | 3 | FINAL DESIGN | Sep 2016 | Mar 2017 | Sep 2016 | Mar 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW13 | Reconstruction of Rockaway Beach - Hurricane Sandy (QED-982) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2017 | Jun 2017 | Mar 2017 | Jun 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW13 | Reconstruction of Rockaway Beach - Hurricane Sandy (QED-982) | 5 | CONSTRUCTION TO 25% | Jun 2017 | Oct 2017 | Jun 2017 | Oct 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW13 | Reconstruction of Rockaway Beach - Hurricane Sandy (QED-982) | 6 | CONSTRUCTION TO 50% | Oct 2017 | Feb 2018 | Oct 2017 | Feb 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW13 | Reconstruction of Rockaway Beach - Hurricane Sandy (QED-982) | 7 | CONSTRUCTION TO 75% | Feb 2018 | Jun 2018 | Feb 2018 | Jun 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW13 | Reconstruction of Rockaway Beach - Hurricane Sandy (QED-982) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW13 | Reconstruction of Rockaway Beach - Hurricane Sandy (QED-982) | 9 | SUBSTANTIAL COMPLETION | Sep 2018 | Nov 2018 | Sep 2018 | Nov 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW13 | Reconstruction of Rockaway Beach - Hurricane Sandy (QED-982) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2018 | Dec 2018 | Nov 2018 | Jun 2033
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW24 | WHEN AND WHERE HURRICANE SANDY - QUEENS | 1 | DEVELOP SCOPE | Aug 2013 | Nov 2013 | Aug 2013 | Nov 2013
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW24 | WHEN AND WHERE HURRICANE SANDY - QUEENS | 2 | PRELIMINARY DESIGN | Nov 2013 | Mar 2014 | Nov 2013 | Mar 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW24 | WHEN AND WHERE HURRICANE SANDY - QUEENS | 3 | FINAL DESIGN | Mar 2014 | Sep 2014 | Mar 2014 | Sep 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW24 | WHEN AND WHERE HURRICANE SANDY - QUEENS | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW24 | WHEN AND WHERE HURRICANE SANDY - QUEENS | 5 | CONSTRUCTION TO 25% | Dec 2014 | Oct 2015 | Dec 2014 | Oct 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW24 | WHEN AND WHERE HURRICANE SANDY - QUEENS | 6 | CONSTRUCTION TO 50% | Oct 2015 | Aug 2016 | Oct 2015 | Aug 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW24 | WHEN AND WHERE HURRICANE SANDY - QUEENS | 7 | CONSTRUCTION TO 75% | Aug 2016 | May 2017 | Aug 2016 | May 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW24 | WHEN AND WHERE HURRICANE SANDY - QUEENS | 8 | ORIGINAL EQUIP & FURNISHING | May 2017 | Aug 2017 | May 2017 | Aug 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW24 | WHEN AND WHERE HURRICANE SANDY - QUEENS | 9 | SUBSTANTIAL COMPLETION | Aug 2017 | Oct 2017 | Aug 2017 | Oct 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW24 | WHEN AND WHERE HURRICANE SANDY - QUEENS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2017 | Dec 2017 | Oct 2017 | Jun 2032
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW26 | Reconstruction of East 10th Road - Hurricane Sandy | 1 | DEVELOP SCOPE | Feb 2014 | May 2014 | Feb 2014 | May 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW26 | Reconstruction of East 10th Road - Hurricane Sandy | 2 | PRELIMINARY DESIGN | May 2014 | May 2015 | May 2014 | May 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW26 | Reconstruction of East 10th Road - Hurricane Sandy | 3 | FINAL DESIGN | Sep 2015 | Mar 2017 | Sep 2015 | Mar 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW26 | Reconstruction of East 10th Road - Hurricane Sandy | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2017 | Jun 2017 | Mar 2017 | Jun 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW26 | Reconstruction of East 10th Road - Hurricane Sandy | 5 | CONSTRUCTION TO 25% | Jun 2017 | Sep 2017 | Jun 2017 | Sep 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW26 | Reconstruction of East 10th Road - Hurricane Sandy | 6 | CONSTRUCTION TO 50% | Sep 2017 | Jan 2018 | Sep 2017 | Jan 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW26 | Reconstruction of East 10th Road - Hurricane Sandy | 7 | CONSTRUCTION TO 75% | Jan 2018 | May 2018 | Jan 2018 | May 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW26 | Reconstruction of East 10th Road - Hurricane Sandy | 8 | ORIGINAL EQUIP & FURNISHING | May 2018 | Aug 2018 | May 2018 | Aug 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW26 | Reconstruction of East 10th Road - Hurricane Sandy | 9 | SUBSTANTIAL COMPLETION | Aug 2018 | Oct 2018 | Aug 2018 | Oct 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW26 | Reconstruction of East 10th Road - Hurricane Sandy | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2018 | Nov 2018 | Oct 2018 | Jun 2028
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR02 | FAR ROCKAWAY BUSINESS DISTRICT IMPROVEMENTS (SE-830) | 1 | DEVELOP SCOPE | Jun 2011 | Sep 2011 | Mar 2017 | May 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR02 | FAR ROCKAWAY BUSINESS DISTRICT IMPROVEMENTS (SE-830) | 2 | DESIGN START | Sep 2011 | Mar 2013 | May 2017 | Sep 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR02 | FAR ROCKAWAY BUSINESS DISTRICT IMPROVEMENTS (SE-830) | 3 | CONSTRUCTION START | Mar 2013 | Mar 2015 | Sep 2017 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR02 | FAR ROCKAWAY BUSINESS DISTRICT IMPROVEMENTS (SE-830) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2013 | Mar 2015 | Mar 2018 | Jun 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR02 | FAR ROCKAWAY BUSINESS DISTRICT IMPROVEMENTS (SE-830) | 5 | CONSTRUCTION TO 25% | Mar 2013 | Mar 2015 | Jun 2018 | Oct 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR02 | FAR ROCKAWAY BUSINESS DISTRICT IMPROVEMENTS (SE-830) | 6 | CONSTRUCTION TO 50% | Mar 2013 | Mar 2015 | Oct 2018 | Feb 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR02 | FAR ROCKAWAY BUSINESS DISTRICT IMPROVEMENTS (SE-830) | 7 | CONSTRUCTION TO 75% | Mar 2013 | Mar 2015 | Feb 2019 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR02 | FAR ROCKAWAY BUSINESS DISTRICT IMPROVEMENTS (SE-830) | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2013 | Mar 2015 | Jun 2019 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR02 | FAR ROCKAWAY BUSINESS DISTRICT IMPROVEMENTS (SE-830) | 9 | SUBSTANTIAL COMPLETION | Mar 2013 | Mar 2015 | Sep 2019 | Jan 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR02 | FAR ROCKAWAY BUSINESS DISTRICT IMPROVEMENTS (SE-830) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2013 | Mar 2015 | Jan 2020 | Aug 2033
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR04 | Beach 108th Streetscape Improvements (QED-1044) | 1 | DEVELOP SCOPE | Sep 2012 | Dec 2012 | Sep 2017 | Dec 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR04 | Beach 108th Streetscape Improvements (QED-1044) | 2 | PRELIMINARY DESIGN | Dec 2012 | Apr 2013 | Dec 2017 | Apr 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR04 | Beach 108th Streetscape Improvements (QED-1044) | 3 | FINAL DESIGN | Apr 2013 | Oct 2013 | Apr 2018 | Oct 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR04 | Beach 108th Streetscape Improvements (QED-1044) | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2013 | Jan 2014 | Oct 2018 | Jan 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR04 | Beach 108th Streetscape Improvements (QED-1044) | 5 | CONSTRUCTION TO 25% | Jan 2014 | May 2014 | Jan 2019 | May 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR04 | Beach 108th Streetscape Improvements (QED-1044) | 6 | CONSTRUCTION TO 50% | May 2014 | Sep 2014 | May 2019 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR04 | Beach 108th Streetscape Improvements (QED-1044) | 7 | CONSTRUCTION TO 75% | Sep 2014 | Jan 2015 | Sep 2019 | Jan 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR04 | Beach 108th Streetscape Improvements (QED-1044) | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2015 | Apr 2015 | Jan 2020 | Apr 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR04 | Beach 108th Streetscape Improvements (QED-1044) | 9 | SUBSTANTIAL COMPLETION | Apr 2015 | Jun 2015 | Apr 2020 | Jun 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR04 | Beach 108th Streetscape Improvements (QED-1044) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2015 | Jul 2015 | Jun 2020 | Jun 2032
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-11 | SANDY- R/C of Rockaway Garage DB | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-11 | SANDY- R/C of Rockaway Garage DB | 2 | DESIGN | Dec 2017 | Dec 2019 | Dec 2017 | Dec 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-11 | SANDY- R/C of Rockaway Garage DB | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-11 | SANDY- R/C of Rockaway Garage DB | 4 | CONSTRUCTION | Sep 2020 | Sep 2022 | Sep 2020 | Sep 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-11 | SANDY- R/C of Rockaway Garage DB | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-11 | SANDY- R/C of Rockaway Garage DB | 6 | PROJECT START | Sep 2022 | Sep 2023 | Nov 2020 | Mar 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-11 | SANDY- R/C of Rockaway Garage DB | 7 | DESIGN START | Sep 2022 | Sep 2023 | Mar 2022 | Mar 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-11 | SANDY- R/C of Rockaway Garage DB | 8 | DESIGN COMPLETION | Sep 2022 | Sep 2023 | Dec 2022 | Dec 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-11 | SANDY- R/C of Rockaway Garage DB | 9 | CONSTRUCTION START | Sep 2022 | Sep 2023 | Dec 2022 | Aug 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-11 | SANDY- R/C of Rockaway Garage DB | 10 | CONSTRUCTION COMPLETION | Sep 2022 | Sep 2023 | Aug 2025 | Aug 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-30 | Tide Gate - FEMA 406 In-Kind, HMP & 428 Conduit HBPED800Q | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-30 | Tide Gate - FEMA 406 In-Kind, HMP & 428 Conduit HBPED800Q | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-30 | Tide Gate - FEMA 406 In-Kind, HMP & 428 Conduit HBPED800Q | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-30 | Tide Gate - FEMA 406 In-Kind, HMP & 428 Conduit HBPED800Q | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-30 | Tide Gate - FEMA 406 In-Kind, HMP & 428 Conduit HBPED800Q | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-30 | Tide Gate - FEMA 406 In-Kind, HMP & 428 Conduit HBPED800Q | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-30 | Tide Gate - FEMA 406 In-Kind, HMP & 428 Conduit HBPED800Q | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-30 | Tide Gate - FEMA 406 In-Kind, HMP & 428 Conduit HBPED800Q | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Jun 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-789B-3 | B 63 ST - BAYFIELD AV & ROCKAWAY FWAY (SOMMERVILLE III) | 1 | DEVELOP SCOPE | Jun 2010 | Sep 2010 | Jun 2010 | Sep 2010
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-789B-3 | B 63 ST - BAYFIELD AV & ROCKAWAY FWAY (SOMMERVILLE III) | 2 | PRELIMINARY DESIGN | Sep 2010 | Jan 2011 | Sep 2010 | Jan 2011
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-789B-3 | B 63 ST - BAYFIELD AV & ROCKAWAY FWAY (SOMMERVILLE III) | 3 | FINAL DESIGN | Jan 2011 | Jul 2011 | Jan 2011 | Jul 2011
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-789B-3 | B 63 ST - BAYFIELD AV & ROCKAWAY FWAY (SOMMERVILLE III) | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2011 | Oct 2011 | Jul 2011 | Oct 2011
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-789B-3 | B 63 ST - BAYFIELD AV & ROCKAWAY FWAY (SOMMERVILLE III) | 5 | CONSTRUCTION TO 25% | Oct 2011 | Feb 2012 | Feb 2022 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-789B-3 | B 63 ST - BAYFIELD AV & ROCKAWAY FWAY (SOMMERVILLE III) | 6 | CONSTRUCTION TO 50% | Feb 2012 | Jun 2012 | Jun 2022 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-789B-3 | B 63 ST - BAYFIELD AV & ROCKAWAY FWAY (SOMMERVILLE III) | 7 | CONSTRUCTION TO 75% | Jun 2012 | Oct 2012 | Jun 2022 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-789B-3 | B 63 ST - BAYFIELD AV & ROCKAWAY FWAY (SOMMERVILLE III) | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2012 | Jan 2013 | Jun 2022 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-789B-3 | B 63 ST - BAYFIELD AV & ROCKAWAY FWAY (SOMMERVILLE III) | 9 | SUBSTANTIAL COMPLETION | Jan 2013 | Mar 2013 | Jun 2022 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-789B-3 | B 63 ST - BAYFIELD AV & ROCKAWAY FWAY (SOMMERVILLE III) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2013 | Apr 2013 | Nov 2023 | Jun 2035
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-807 | Storm & San Sewers in 20th Ave b/t 126 St & US Bulkhead Line | 1 | DEVELOP SCOPE | Jun 2012 | Mar 2013 | Jun 2012 | Mar 2013
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-807 | Storm & San Sewers in 20th Ave b/t 126 St & US Bulkhead Line | 2 | PRELIMINARY DESIGN | Mar 2013 | Mar 2014 | Mar 2013 | Mar 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-807 | Storm & San Sewers in 20th Ave b/t 126 St & US Bulkhead Line | 3 | FINAL DESIGN | Mar 2014 | Sep 2015 | Mar 2014 | Sep 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-807 | Storm & San Sewers in 20th Ave b/t 126 St & US Bulkhead Line | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2015 | Jun 2016 | Sep 2015 | Jun 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-807 | Storm & San Sewers in 20th Ave b/t 126 St & US Bulkhead Line | 5 | CONSTRUCTION TO 25% | Jun 2016 | Jun 2017 | Jun 2016 | Jun 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-807 | Storm & San Sewers in 20th Ave b/t 126 St & US Bulkhead Line | 6 | CONSTRUCTION TO 50% | Jun 2017 | May 2018 | Jun 2017 | May 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-807 | Storm & San Sewers in 20th Ave b/t 126 St & US Bulkhead Line | 7 | CONSTRUCTION TO 75% | May 2018 | May 2019 | May 2018 | May 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-807 | Storm & San Sewers in 20th Ave b/t 126 St & US Bulkhead Line | 8 | ORIGINAL EQUIP & FURNISHING | May 2019 | Feb 2020 | May 2019 | Feb 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-807 | Storm & San Sewers in 20th Ave b/t 126 St & US Bulkhead Line | 9 | SUBSTANTIAL COMPLETION | Feb 2020 | Aug 2020 | Feb 2020 | Aug 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-807 | Storm & San Sewers in 20th Ave b/t 126 St & US Bulkhead Line | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2020 | Nov 2020 | Aug 2020 | Jun 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-810 | STORM & SAN SWR, WILLET PT BLVD WHITESTONE AREA PHASE 2 | 1 | DEVELOP SCOPE | Jun 2010 | Mar 2011 | Jun 2010 | Mar 2011
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-810 | STORM & SAN SWR, WILLET PT BLVD WHITESTONE AREA PHASE 2 | 2 | PRELIMINARY DESIGN | Mar 2011 | Mar 2012 | Mar 2011 | Mar 2012
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-810 | STORM & SAN SWR, WILLET PT BLVD WHITESTONE AREA PHASE 2 | 3 | FINAL DESIGN | Mar 2012 | Sep 2013 | Mar 2012 | Sep 2013
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-810 | STORM & SAN SWR, WILLET PT BLVD WHITESTONE AREA PHASE 2 | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2013 | Jun 2014 | Sep 2013 | Jun 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-810 | STORM & SAN SWR, WILLET PT BLVD WHITESTONE AREA PHASE 2 | 5 | CONSTRUCTION TO 25% | Jun 2014 | Jun 2015 | Jun 2014 | Jun 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-810 | STORM & SAN SWR, WILLET PT BLVD WHITESTONE AREA PHASE 2 | 6 | CONSTRUCTION TO 50% | Jun 2015 | May 2016 | Jun 2015 | May 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-810 | STORM & SAN SWR, WILLET PT BLVD WHITESTONE AREA PHASE 2 | 7 | CONSTRUCTION TO 75% | May 2016 | May 2017 | May 2016 | May 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-810 | STORM & SAN SWR, WILLET PT BLVD WHITESTONE AREA PHASE 2 | 8 | ORIGINAL EQUIP & FURNISHING | May 2017 | Feb 2018 | May 2017 | Feb 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-810 | STORM & SAN SWR, WILLET PT BLVD WHITESTONE AREA PHASE 2 | 9 | SUBSTANTIAL COMPLETION | Feb 2018 | Aug 2018 | Feb 2018 | Aug 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-810 | STORM & SAN SWR, WILLET PT BLVD WHITESTONE AREA PHASE 2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2018 | Nov 2018 | Aug 2018 | Sep 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-811 | STORM & SAN SWR, N.B. WHITESTONE EXPWY SERV RD PHASE 3 | 1 | DEVELOP SCOPE | Jun 2010 | Mar 2011 | Jun 2010 | Jul 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-811 | STORM & SAN SWR, N.B. WHITESTONE EXPWY SERV RD PHASE 3 | 2 | PRELIMINARY DESIGN | Mar 2011 | Mar 2012 | Jul 2016 | Jul 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-811 | STORM & SAN SWR, N.B. WHITESTONE EXPWY SERV RD PHASE 3 | 3 | FINAL DESIGN | Mar 2012 | Sep 2013 | Jul 2017 | Dec 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-811 | STORM & SAN SWR, N.B. WHITESTONE EXPWY SERV RD PHASE 3 | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2013 | Jun 2014 | Jan 2019 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-811 | STORM & SAN SWR, N.B. WHITESTONE EXPWY SERV RD PHASE 3 | 5 | CONSTRUCTION TO 25% | Jun 2014 | Jun 2015 | Sep 2019 | Sep 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-811 | STORM & SAN SWR, N.B. WHITESTONE EXPWY SERV RD PHASE 3 | 6 | CONSTRUCTION TO 50% | Jun 2015 | May 2016 | Sep 2020 | Sep 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-811 | STORM & SAN SWR, N.B. WHITESTONE EXPWY SERV RD PHASE 3 | 7 | CONSTRUCTION TO 75% | May 2016 | May 2017 | Sep 2021 | Sep 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-811 | STORM & SAN SWR, N.B. WHITESTONE EXPWY SERV RD PHASE 3 | 8 | ORIGINAL EQUIP & FURNISHING | May 2017 | Feb 2018 | Sep 2022 | Jun 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-811 | STORM & SAN SWR, N.B. WHITESTONE EXPWY SERV RD PHASE 3 | 9 | SUBSTANTIAL COMPLETION | Feb 2018 | Aug 2018 | Jun 2023 | Dec 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-811 | STORM & SAN SWR, N.B. WHITESTONE EXPWY SERV RD PHASE 3 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2018 | Nov 2018 | Dec 2023 | Mar 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-811 | STORM & SAN SWR, N.B. WHITESTONE EXPWY SERV RD PHASE 3 | 11 | PROJECT START | Aug 2018 | Nov 2018 | Mar 2024 | Mar 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-811 | STORM & SAN SWR, N.B. WHITESTONE EXPWY SERV RD PHASE 3 | 12 | DESIGN START | Aug 2018 | Nov 2018 | Mar 2024 | Mar 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-811 | STORM & SAN SWR, N.B. WHITESTONE EXPWY SERV RD PHASE 3 | 13 | DESIGN COMPLETION | Aug 2018 | Nov 2018 | Mar 2024 | Mar 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-811 | STORM & SAN SWR, N.B. WHITESTONE EXPWY SERV RD PHASE 3 | 14 | CONSTRUCTION START | Aug 2018 | Nov 2018 | Mar 2024 | Mar 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-811 | STORM & SAN SWR, N.B. WHITESTONE EXPWY SERV RD PHASE 3 | 15 | CONSTRUCTION COMPLETION | Aug 2018 | Nov 2018 | Mar 2024 | Jun 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-823 | SEQ - 229th Street Laurelton Area - Part 1, Phase A (HWQ823) | 1 | DEVELOP SCOPE | Mar 2014 | Jun 2014 | Mar 2014 | Jun 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-823 | SEQ - 229th Street Laurelton Area - Part 1, Phase A (HWQ823) | 2 | PRELIMINARY DESIGN | Jun 2014 | Sep 2014 | Jun 2014 | Apr 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-823 | SEQ - 229th Street Laurelton Area - Part 1, Phase A (HWQ823) | 3 | FINAL DESIGN | Oct 2014 | Mar 2015 | May 2015 | Dec 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-823 | SEQ - 229th Street Laurelton Area - Part 1, Phase A (HWQ823) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2015 | Jun 2015 | Dec 2017 | Jul 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-823 | SEQ - 229th Street Laurelton Area - Part 1, Phase A (HWQ823) | 5 | CONSTRUCTION TO 25% | Jun 2015 | Oct 2015 | Jul 2018 | Nov 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-823 | SEQ - 229th Street Laurelton Area - Part 1, Phase A (HWQ823) | 6 | CONSTRUCTION TO 50% | Oct 2015 | Feb 2016 | Nov 2018 | Mar 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-823 | SEQ - 229th Street Laurelton Area - Part 1, Phase A (HWQ823) | 7 | CONSTRUCTION TO 75% | Feb 2016 | Jun 2016 | Mar 2019 | Jul 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-823 | SEQ - 229th Street Laurelton Area - Part 1, Phase A (HWQ823) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2016 | Sep 2016 | Jul 2019 | Oct 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-823 | SEQ - 229th Street Laurelton Area - Part 1, Phase A (HWQ823) | 9 | SUBSTANTIAL COMPLETION | Sep 2016 | Nov 2016 | Oct 2019 | Dec 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-823 | SEQ - 229th Street Laurelton Area - Part 1, Phase A (HWQ823) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2016 | Dec 2016 | Dec 2019 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-823 | SEQ - 229th Street Laurelton Area - Part 1, Phase A (HWQ823) | 11 | PROJECT START | Nov 2016 | Dec 2016 | Jul 2022 | Jul 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-823 | SEQ - 229th Street Laurelton Area - Part 1, Phase A (HWQ823) | 12 | DESIGN START | Nov 2016 | Dec 2016 | Jul 2022 | Jul 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-823 | SEQ - 229th Street Laurelton Area - Part 1, Phase A (HWQ823) | 13 | DESIGN COMPLETION | Nov 2016 | Dec 2016 | Jul 2022 | Jul 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-823 | SEQ - 229th Street Laurelton Area - Part 1, Phase A (HWQ823) | 14 | CONSTRUCTION START | Nov 2016 | Dec 2016 | Jul 2022 | Jul 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-823 | SEQ - 229th Street Laurelton Area - Part 1, Phase A (HWQ823) | 15 | CONSTRUCTION COMPLETION | Nov 2016 | Dec 2016 | Jul 2022 | Jun 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-824 | SEQ - 230th Place Laurelton Area - Part 1, Phase B | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-824 | SEQ - 230th Place Laurelton Area - Part 1, Phase B | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-824 | SEQ - 230th Place Laurelton Area - Part 1, Phase B | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-824 | SEQ - 230th Place Laurelton Area - Part 1, Phase B | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-824 | SEQ - 230th Place Laurelton Area - Part 1, Phase B | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-824 | SEQ - 230th Place Laurelton Area - Part 1, Phase B | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-824 | SEQ - 230th Place Laurelton Area - Part 1, Phase B | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-824 | SEQ - 230th Place Laurelton Area - Part 1, Phase B | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-824 | SEQ - 230th Place Laurelton Area - Part 1, Phase B | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-824 | SEQ - 230th Place Laurelton Area - Part 1, Phase B | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Oct 2032
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-825 | SEQ - Laurelton Area - Part 1, Phase C | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-825 | SEQ - Laurelton Area - Part 1, Phase C | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-825 | SEQ - Laurelton Area - Part 1, Phase C | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-825 | SEQ - Laurelton Area - Part 1, Phase C | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-825 | SEQ - Laurelton Area - Part 1, Phase C | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-825 | SEQ - Laurelton Area - Part 1, Phase C | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-825 | SEQ - Laurelton Area - Part 1, Phase C | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-825 | SEQ - Laurelton Area - Part 1, Phase C | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-825 | SEQ - Laurelton Area - Part 1, Phase C | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-825 | SEQ - Laurelton Area - Part 1, Phase C | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Jun 2032
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-829 | NDF -- Storm and Sanitary Sewers in Brundwick Ave, Queens | 1 | DEVELOP SCOPE | May 2012 | Feb 2013 | May 2012 | Feb 2013
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-829 | NDF -- Storm and Sanitary Sewers in Brundwick Ave, Queens | 2 | PRELIMINARY DESIGN | Feb 2013 | Feb 2014 | Jan 2020 | Feb 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-829 | NDF -- Storm and Sanitary Sewers in Brundwick Ave, Queens | 3 | FINAL DESIGN | Feb 2014 | Aug 2015 | Feb 2021 | Jan 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-829 | NDF -- Storm and Sanitary Sewers in Brundwick Ave, Queens | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2015 | May 2016 | Jan 2022 | Sep 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-829 | NDF -- Storm and Sanitary Sewers in Brundwick Ave, Queens | 5 | CONSTRUCTION TO 25% | May 2016 | Apr 2017 | Sep 2022 | Sep 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-829 | NDF -- Storm and Sanitary Sewers in Brundwick Ave, Queens | 6 | CONSTRUCTION TO 50% | Apr 2017 | Apr 2018 | Sep 2023 | Sep 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-829 | NDF -- Storm and Sanitary Sewers in Brundwick Ave, Queens | 7 | CONSTRUCTION TO 75% | Apr 2018 | Apr 2019 | Sep 2024 | Sep 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-829 | NDF -- Storm and Sanitary Sewers in Brundwick Ave, Queens | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2019 | Jan 2020 | Sep 2025 | Jun 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-829 | NDF -- Storm and Sanitary Sewers in Brundwick Ave, Queens | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Jul 2020 | Jun 2026 | Dec 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-829 | NDF -- Storm and Sanitary Sewers in Brundwick Ave, Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Oct 2020 | Dec 2026 | Mar 2031
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-830 | NDF Storm & Sanitary SE, WM Work in Mott Ave, QNS (SANDR02) | 1 | DEVELOP SCOPE | Mar 2019 | May 2019 | Mar 2019 | May 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-830 | NDF Storm & Sanitary SE, WM Work in Mott Ave, QNS (SANDR02) | 2 | PRELIMINARY DESIGN | May 2019 | Sep 2019 | May 2019 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-830 | NDF Storm & Sanitary SE, WM Work in Mott Ave, QNS (SANDR02) | 3 | FINAL DESIGN | Sep 2019 | Mar 2020 | Sep 2019 | Mar 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-830 | NDF Storm & Sanitary SE, WM Work in Mott Ave, QNS (SANDR02) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Jun 2020 | Mar 2020 | Jun 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-830 | NDF Storm & Sanitary SE, WM Work in Mott Ave, QNS (SANDR02) | 5 | CONSTRUCTION TO 25% | Jun 2020 | Oct 2020 | Jun 2020 | Oct 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-830 | NDF Storm & Sanitary SE, WM Work in Mott Ave, QNS (SANDR02) | 6 | CONSTRUCTION TO 50% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-830 | NDF Storm & Sanitary SE, WM Work in Mott Ave, QNS (SANDR02) | 7 | CONSTRUCTION TO 75% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-830 | NDF Storm & Sanitary SE, WM Work in Mott Ave, QNS (SANDR02) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-830 | NDF Storm & Sanitary SE, WM Work in Mott Ave, QNS (SANDR02) | 9 | SUBSTANTIAL COMPLETION | Sep 2021 | Nov 2021 | Sep 2021 | Nov 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-830 | NDF Storm & Sanitary SE, WM Work in Mott Ave, QNS (SANDR02) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2021 | Dec 2021 | Nov 2021 | Jun 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A | SEQ - Storm, Sanitary Sewers & WM in 225th Street | 1 | DEVELOP SCOPE | Mar 2018 | May 2018 | Mar 2018 | May 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A | SEQ - Storm, Sanitary Sewers & WM in 225th Street | 2 | PRELIMINARY DESIGN | May 2018 | Sep 2018 | May 2018 | Sep 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A | SEQ - Storm, Sanitary Sewers & WM in 225th Street | 3 | FINAL DESIGN | Sep 2018 | Mar 2019 | Sep 2018 | Mar 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A | SEQ - Storm, Sanitary Sewers & WM in 225th Street | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2019 | Jun 2019 | Mar 2019 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A | SEQ - Storm, Sanitary Sewers & WM in 225th Street | 5 | CONSTRUCTION TO 25% | Jun 2019 | Oct 2019 | Jun 2019 | Oct 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A | SEQ - Storm, Sanitary Sewers & WM in 225th Street | 6 | CONSTRUCTION TO 50% | Oct 2019 | Feb 2020 | Oct 2019 | Feb 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A | SEQ - Storm, Sanitary Sewers & WM in 225th Street | 7 | CONSTRUCTION TO 75% | Feb 2020 | Jun 2020 | Feb 2020 | Jun 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A | SEQ - Storm, Sanitary Sewers & WM in 225th Street | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A | SEQ - Storm, Sanitary Sewers & WM in 225th Street | 9 | SUBSTANTIAL COMPLETION | Sep 2020 | Nov 2020 | Sep 2020 | Nov 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A | SEQ - Storm, Sanitary Sewers & WM in 225th Street | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2020 | Dec 2020 | Nov 2020 | Jun 2028
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A1 | SEQ - Storm Sewer Outlet in 224th Street | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A1 | SEQ - Storm Sewer Outlet in 224th Street | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A1 | SEQ - Storm Sewer Outlet in 224th Street | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A1 | SEQ - Storm Sewer Outlet in 224th Street | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A1 | SEQ - Storm Sewer Outlet in 224th Street | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A1 | SEQ - Storm Sewer Outlet in 224th Street | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A1 | SEQ - Storm Sewer Outlet in 224th Street | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A1 | SEQ - Storm Sewer Outlet in 224th Street | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A1 | SEQ - Storm Sewer Outlet in 224th Street | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A1 | SEQ - Storm Sewer Outlet in 224th Street | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Jun 2029
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842B | SEQ - Storm & Sanitary Sewers & WM Work in 224th Street | 1 | DEVELOP SCOPE | Mar 2020 | May 2020 | Mar 2020 | May 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842B | SEQ - Storm & Sanitary Sewers & WM Work in 224th Street | 2 | PRELIMINARY DESIGN | May 2020 | Sep 2020 | May 2020 | Sep 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842B | SEQ - Storm & Sanitary Sewers & WM Work in 224th Street | 3 | FINAL DESIGN | Sep 2020 | Mar 2021 | Sep 2020 | Mar 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842B | SEQ - Storm & Sanitary Sewers & WM Work in 224th Street | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2021 | Jun 2021 | Mar 2021 | Jun 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842B | SEQ - Storm & Sanitary Sewers & WM Work in 224th Street | 5 | CONSTRUCTION TO 25% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842B | SEQ - Storm & Sanitary Sewers & WM Work in 224th Street | 6 | CONSTRUCTION TO 50% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842B | SEQ - Storm & Sanitary Sewers & WM Work in 224th Street | 7 | CONSTRUCTION TO 75% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842B | SEQ - Storm & Sanitary Sewers & WM Work in 224th Street | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842B | SEQ - Storm & Sanitary Sewers & WM Work in 224th Street | 9 | SUBSTANTIAL COMPLETION | Sep 2022 | Nov 2022 | Sep 2022 | Nov 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842B | SEQ - Storm & Sanitary Sewers & WM Work in 224th Street | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2022 | Dec 2022 | Nov 2022 | Jun 2028
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-859 | Combined Sewer Replmnt & WM work 70 st & calamus ave, Qns | 1 | DEVELOP SCOPE | Jun 2018 | Mar 2019 | Jun 2018 | Mar 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-859 | Combined Sewer Replmnt & WM work 70 st & calamus ave, Qns | 2 | PRELIMINARY DESIGN | Mar 2019 | Mar 2020 | Mar 2019 | Mar 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-859 | Combined Sewer Replmnt & WM work 70 st & calamus ave, Qns | 3 | FINAL DESIGN | Mar 2020 | Sep 2021 | Mar 2020 | Sep 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-859 | Combined Sewer Replmnt & WM work 70 st & calamus ave, Qns | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2021 | Jun 2022 | Sep 2021 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-859 | Combined Sewer Replmnt & WM work 70 st & calamus ave, Qns | 5 | CONSTRUCTION TO 25% | Jun 2022 | Jun 2023 | Jun 2022 | Jun 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-859 | Combined Sewer Replmnt & WM work 70 st & calamus ave, Qns | 6 | CONSTRUCTION TO 50% | Jun 2023 | May 2024 | Jun 2023 | May 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-859 | Combined Sewer Replmnt & WM work 70 st & calamus ave, Qns | 7 | CONSTRUCTION TO 75% | May 2024 | May 2025 | May 2024 | May 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-859 | Combined Sewer Replmnt & WM work 70 st & calamus ave, Qns | 8 | ORIGINAL EQUIP & FURNISHING | May 2025 | Feb 2026 | May 2025 | Feb 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-859 | Combined Sewer Replmnt & WM work 70 st & calamus ave, Qns | 9 | SUBSTANTIAL COMPLETION | Feb 2026 | Aug 2026 | Feb 2026 | Aug 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-859 | Combined Sewer Replmnt & WM work 70 st & calamus ave, Qns | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2026 | Nov 2026 | Aug 2026 | Nov 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-860 | Combined Swr Replac & WM work 71st, QNS | 1 | DEVELOP SCOPE | Mar 2019 | May 2019 | Mar 2019 | May 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-860 | Combined Swr Replac & WM work 71st, QNS | 2 | PRELIMINARY DESIGN | May 2019 | Sep 2019 | May 2019 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-860 | Combined Swr Replac & WM work 71st, QNS | 3 | FINAL DESIGN | Sep 2019 | Mar 2020 | Sep 2019 | Mar 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-860 | Combined Swr Replac & WM work 71st, QNS | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Jun 2020 | Mar 2020 | Jun 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-860 | Combined Swr Replac & WM work 71st, QNS | 5 | CONSTRUCTION TO 25% | Jun 2020 | Oct 2020 | Jun 2020 | Oct 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-860 | Combined Swr Replac & WM work 71st, QNS | 6 | CONSTRUCTION TO 50% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-860 | Combined Swr Replac & WM work 71st, QNS | 7 | CONSTRUCTION TO 75% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-860 | Combined Swr Replac & WM work 71st, QNS | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-860 | Combined Swr Replac & WM work 71st, QNS | 9 | SUBSTANTIAL COMPLETION | Sep 2021 | Nov 2021 | Sep 2021 | Nov 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-860 | Combined Swr Replac & WM work 71st, QNS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2021 | Dec 2021 | Nov 2021 | Dec 2029
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-862 | SEQ - Storm & Sanitary Sewer Replcmnt/Ext. 146 Ave (HWQ662G) | 1 | DEVELOP SCOPE | Mar 2018 | May 2018 | Mar 2018 | May 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-862 | SEQ - Storm & Sanitary Sewer Replcmnt/Ext. 146 Ave (HWQ662G) | 2 | PRELIMINARY DESIGN | May 2018 | Sep 2018 | May 2018 | Sep 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-862 | SEQ - Storm & Sanitary Sewer Replcmnt/Ext. 146 Ave (HWQ662G) | 3 | FINAL DESIGN | Sep 2018 | Mar 2019 | Sep 2018 | Mar 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-862 | SEQ - Storm & Sanitary Sewer Replcmnt/Ext. 146 Ave (HWQ662G) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2019 | Jun 2019 | Mar 2019 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-862 | SEQ - Storm & Sanitary Sewer Replcmnt/Ext. 146 Ave (HWQ662G) | 5 | CONSTRUCTION TO 25% | Jun 2019 | Oct 2019 | Jun 2019 | Oct 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-862 | SEQ - Storm & Sanitary Sewer Replcmnt/Ext. 146 Ave (HWQ662G) | 6 | CONSTRUCTION TO 50% | Oct 2019 | Feb 2020 | Oct 2019 | Feb 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-862 | SEQ - Storm & Sanitary Sewer Replcmnt/Ext. 146 Ave (HWQ662G) | 7 | CONSTRUCTION TO 75% | Feb 2020 | Jun 2020 | Feb 2020 | Jun 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-862 | SEQ - Storm & Sanitary Sewer Replcmnt/Ext. 146 Ave (HWQ662G) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-862 | SEQ - Storm & Sanitary Sewer Replcmnt/Ext. 146 Ave (HWQ662G) | 9 | SUBSTANTIAL COMPLETION | Sep 2020 | Nov 2020 | Sep 2020 | Nov 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-862 | SEQ - Storm & Sanitary Sewer Replcmnt/Ext. 146 Ave (HWQ662G) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2020 | Dec 2020 | Nov 2020 | Jun 2031
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE877 | Combined Swr Install & WM Replac,77 Av & 81-88st Qn HWQSE877 | 1 | DEVELOP SCOPE | Jan 2027 | Mar 2027 | Jun 2025 | Aug 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE877 | Combined Swr Install & WM Replac,77 Av & 81-88st Qn HWQSE877 | 2 | PRELIMINARY DESIGN | Apr 2027 | Jul 2027 | Aug 2025 | Dec 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE877 | Combined Swr Install & WM Replac,77 Av & 81-88st Qn HWQSE877 | 3 | FINAL DESIGN | Jul 2027 | Jan 2028 | Dec 2025 | Jun 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE877 | Combined Swr Install & WM Replac,77 Av & 81-88st Qn HWQSE877 | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2028 | Apr 2028 | Jun 2026 | Sep 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE877 | Combined Swr Install & WM Replac,77 Av & 81-88st Qn HWQSE877 | 5 | CONSTRUCTION TO 25% | Apr 2028 | Aug 2028 | Sep 2026 | Jan 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE877 | Combined Swr Install & WM Replac,77 Av & 81-88st Qn HWQSE877 | 6 | CONSTRUCTION TO 50% | Aug 2028 | Dec 2028 | Jan 2027 | May 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE877 | Combined Swr Install & WM Replac,77 Av & 81-88st Qn HWQSE877 | 7 | CONSTRUCTION TO 75% | Dec 2028 | Apr 2029 | May 2027 | Sep 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE877 | Combined Swr Install & WM Replac,77 Av & 81-88st Qn HWQSE877 | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2029 | Jul 2029 | Sep 2027 | Dec 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE877 | Combined Swr Install & WM Replac,77 Av & 81-88st Qn HWQSE877 | 9 | SUBSTANTIAL COMPLETION | Jul 2029 | Sep 2029 | Dec 2027 | Feb 2028
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE877 | Combined Swr Install & WM Replac,77 Av & 81-88st Qn HWQSE877 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2029 | Oct 2029 | Feb 2028 | Mar 2028
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885 | SEQ - 150th St Spine: Phase I, Outlet at Bergen Basin | 1 | DEVELOP SCOPE | Mar 2019 | May 2019 | Mar 2019 | May 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885 | SEQ - 150th St Spine: Phase I, Outlet at Bergen Basin | 2 | PRELIMINARY DESIGN | May 2019 | Sep 2019 | May 2019 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885 | SEQ - 150th St Spine: Phase I, Outlet at Bergen Basin | 3 | FINAL DESIGN | Sep 2019 | Mar 2020 | Sep 2019 | Mar 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885 | SEQ - 150th St Spine: Phase I, Outlet at Bergen Basin | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Jun 2020 | Mar 2020 | Jun 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885 | SEQ - 150th St Spine: Phase I, Outlet at Bergen Basin | 5 | CONSTRUCTION TO 25% | Jun 2020 | Oct 2020 | Jun 2020 | Oct 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885 | SEQ - 150th St Spine: Phase I, Outlet at Bergen Basin | 6 | CONSTRUCTION TO 50% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885 | SEQ - 150th St Spine: Phase I, Outlet at Bergen Basin | 7 | CONSTRUCTION TO 75% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885 | SEQ - 150th St Spine: Phase I, Outlet at Bergen Basin | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885 | SEQ - 150th St Spine: Phase I, Outlet at Bergen Basin | 9 | SUBSTANTIAL COMPLETION | Sep 2021 | Nov 2021 | Sep 2021 | Nov 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885 | SEQ - 150th St Spine: Phase I, Outlet at Bergen Basin | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2021 | Dec 2021 | Nov 2021 | Jun 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885A | SEQ - 150th St Spine: Phase II, Trunk Storm Sewer in JFK | 1 | DEVELOP SCOPE | Aug 2020 | Nov 2020 | Aug 2020 | Nov 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885A | SEQ - 150th St Spine: Phase II, Trunk Storm Sewer in JFK | 2 | PRELIMINARY DESIGN | Nov 2020 | Mar 2021 | Nov 2020 | Mar 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885A | SEQ - 150th St Spine: Phase II, Trunk Storm Sewer in JFK | 3 | FINAL DESIGN | Mar 2021 | Sep 2021 | Mar 2021 | Sep 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885A | SEQ - 150th St Spine: Phase II, Trunk Storm Sewer in JFK | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2021 | Dec 2021 | Sep 2021 | Dec 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885A | SEQ - 150th St Spine: Phase II, Trunk Storm Sewer in JFK | 5 | CONSTRUCTION TO 25% | Dec 2021 | Apr 2022 | Dec 2021 | Apr 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885A | SEQ - 150th St Spine: Phase II, Trunk Storm Sewer in JFK | 6 | CONSTRUCTION TO 50% | Apr 2022 | Aug 2022 | Apr 2022 | Aug 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885A | SEQ - 150th St Spine: Phase II, Trunk Storm Sewer in JFK | 7 | CONSTRUCTION TO 75% | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885A | SEQ - 150th St Spine: Phase II, Trunk Storm Sewer in JFK | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2022 | Mar 2023 | Dec 2022 | Mar 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885A | SEQ - 150th St Spine: Phase II, Trunk Storm Sewer in JFK | 9 | SUBSTANTIAL COMPLETION | Mar 2023 | May 2023 | Mar 2023 | May 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885A | SEQ - 150th St Spine: Phase II, Trunk Storm Sewer in JFK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2023 | Jun 2023 | May 2023 | Jun 2028
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-886 | NDF -- Storm & Sanitary Sewers in Beach Channel Drive, Qns | 1 | DEVELOP SCOPE | Mar 2019 | May 2019 | Mar 2019 | May 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-886 | NDF -- Storm & Sanitary Sewers in Beach Channel Drive, Qns | 2 | PRELIMINARY DESIGN | May 2019 | Sep 2019 | May 2019 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-886 | NDF -- Storm & Sanitary Sewers in Beach Channel Drive, Qns | 3 | FINAL DESIGN | Sep 2019 | Mar 2020 | Sep 2019 | Mar 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-886 | NDF -- Storm & Sanitary Sewers in Beach Channel Drive, Qns | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Jun 2020 | Mar 2020 | Jun 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-886 | NDF -- Storm & Sanitary Sewers in Beach Channel Drive, Qns | 5 | CONSTRUCTION TO 25% | Jun 2020 | Oct 2020 | Jun 2020 | Oct 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-886 | NDF -- Storm & Sanitary Sewers in Beach Channel Drive, Qns | 6 | CONSTRUCTION TO 50% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-886 | NDF -- Storm & Sanitary Sewers in Beach Channel Drive, Qns | 7 | CONSTRUCTION TO 75% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-886 | NDF -- Storm & Sanitary Sewers in Beach Channel Drive, Qns | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-886 | NDF -- Storm & Sanitary Sewers in Beach Channel Drive, Qns | 9 | SUBSTANTIAL COMPLETION | Sep 2021 | Nov 2021 | Sep 2021 | Nov 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-886 | NDF -- Storm & Sanitary Sewers in Beach Channel Drive, Qns | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2021 | Dec 2021 | Nov 2021 | Jun 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-887 | NDF -- Storm & Sanitary Sewers, WM work in Cornaga Ave, Qns | 1 | DEVELOP SCOPE | Mar 2019 | May 2019 | Mar 2019 | May 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-887 | NDF -- Storm & Sanitary Sewers, WM work in Cornaga Ave, Qns | 2 | PRELIMINARY DESIGN | May 2019 | Sep 2019 | May 2019 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-887 | NDF -- Storm & Sanitary Sewers, WM work in Cornaga Ave, Qns | 3 | FINAL DESIGN | Sep 2019 | Mar 2020 | Sep 2019 | Mar 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-887 | NDF -- Storm & Sanitary Sewers, WM work in Cornaga Ave, Qns | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Jun 2020 | Mar 2020 | Jun 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-887 | NDF -- Storm & Sanitary Sewers, WM work in Cornaga Ave, Qns | 5 | CONSTRUCTION TO 25% | Jun 2020 | Oct 2020 | Jun 2020 | Oct 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-887 | NDF -- Storm & Sanitary Sewers, WM work in Cornaga Ave, Qns | 6 | CONSTRUCTION TO 50% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-887 | NDF -- Storm & Sanitary Sewers, WM work in Cornaga Ave, Qns | 7 | CONSTRUCTION TO 75% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-887 | NDF -- Storm & Sanitary Sewers, WM work in Cornaga Ave, Qns | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-887 | NDF -- Storm & Sanitary Sewers, WM work in Cornaga Ave, Qns | 9 | SUBSTANTIAL COMPLETION | Sep 2021 | Nov 2021 | Sep 2021 | Nov 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-887 | NDF -- Storm & Sanitary Sewers, WM work in Cornaga Ave, Qns | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2021 | Dec 2021 | Nov 2021 | Jun 2032
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-889 | SEQ - New Storm Sewer N. Conduit Ave | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-889 | SEQ - New Storm Sewer N. Conduit Ave | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-889 | SEQ - New Storm Sewer N. Conduit Ave | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-889 | SEQ - New Storm Sewer N. Conduit Ave | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-889 | SEQ - New Storm Sewer N. Conduit Ave | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-889 | SEQ - New Storm Sewer N. Conduit Ave | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-889 | SEQ - New Storm Sewer N. Conduit Ave | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-889 | SEQ - New Storm Sewer N. Conduit Ave | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-889 | SEQ - New Storm Sewer N. Conduit Ave | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-889 | SEQ - New Storm Sewer N. Conduit Ave | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Jun 2028
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002700 | REHABILITATION OF COMBINED SEWER AND WATER MAIN | 1 | DEVELOP SCOPE | Jan 2011 | Mar 2011 | Aug 2013 | Nov 2013
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002700 | REHABILITATION OF COMBINED SEWER AND WATER MAIN | 2 | PRELIMINARY DESIGN | Apr 2011 | Jul 2011 | Nov 2013 | May 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002700 | REHABILITATION OF COMBINED SEWER AND WATER MAIN | 3 | FINAL DESIGN | Jul 2011 | Jan 2012 | May 2014 | Mar 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002700 | REHABILITATION OF COMBINED SEWER AND WATER MAIN | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2012 | Apr 2012 | Mar 2015 | Jun 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002700 | REHABILITATION OF COMBINED SEWER AND WATER MAIN | 5 | CONSTRUCTION TO 25% | Apr 2012 | Aug 2012 | Jun 2015 | Jun 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002700 | REHABILITATION OF COMBINED SEWER AND WATER MAIN | 6 | CONSTRUCTION TO 50% | Aug 2012 | Dec 2012 | Jun 2018 | Jun 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002700 | REHABILITATION OF COMBINED SEWER AND WATER MAIN | 7 | CONSTRUCTION TO 75% | Dec 2012 | Apr 2013 | Jun 2021 | Jul 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002700 | REHABILITATION OF COMBINED SEWER AND WATER MAIN | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2013 | Jul 2013 | Jul 2022 | Oct 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002700 | REHABILITATION OF COMBINED SEWER AND WATER MAIN | 9 | SUBSTANTIAL COMPLETION | Jul 2013 | Sep 2013 | Oct 2022 | Dec 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002700 | REHABILITATION OF COMBINED SEWER AND WATER MAIN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2013 | Oct 2013 | Dec 2022 | Aug 2032
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200467 | STRM & SAN SWRS IN 14 AV B/T 115 ST & US BULKHEAD LINE | 1 | DEVELOP SCOPE | Aug 2006 | May 2007 | Jul 2020 | Sep 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200467 | STRM & SAN SWRS IN 14 AV B/T 115 ST & US BULKHEAD LINE | 2 | PRELIMINARY DESIGN | May 2007 | May 2008 | Sep 2020 | Jan 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200467 | STRM & SAN SWRS IN 14 AV B/T 115 ST & US BULKHEAD LINE | 3 | FINAL DESIGN | May 2008 | Oct 2009 | Jan 2021 | Jul 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200467 | STRM & SAN SWRS IN 14 AV B/T 115 ST & US BULKHEAD LINE | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2009 | Jul 2010 | Jul 2021 | Oct 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200467 | STRM & SAN SWRS IN 14 AV B/T 115 ST & US BULKHEAD LINE | 5 | CONSTRUCTION TO 25% | Jul 2010 | Jul 2011 | Oct 2021 | Feb 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200467 | STRM & SAN SWRS IN 14 AV B/T 115 ST & US BULKHEAD LINE | 6 | CONSTRUCTION TO 50% | Jul 2011 | Jul 2012 | Feb 2022 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200467 | STRM & SAN SWRS IN 14 AV B/T 115 ST & US BULKHEAD LINE | 7 | CONSTRUCTION TO 75% | Jul 2012 | Jul 2013 | Jun 2022 | Oct 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200467 | STRM & SAN SWRS IN 14 AV B/T 115 ST & US BULKHEAD LINE | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2013 | Apr 2014 | Oct 2022 | Jan 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200467 | STRM & SAN SWRS IN 14 AV B/T 115 ST & US BULKHEAD LINE | 9 | SUBSTANTIAL COMPLETION | Apr 2014 | Oct 2014 | Jan 2023 | Mar 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200467 | STRM & SAN SWRS IN 14 AV B/T 115 ST & US BULKHEAD LINE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2014 | Dec 2014 | Mar 2023 | Apr 2037
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200519 | SEQ - Brookville-Edgewood Triangle West - Phase II (HWQ724B) | 1 | DEVELOP SCOPE | Jun 2010 | Sep 2010 | Jun 2010 | Sep 2010
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200519 | SEQ - Brookville-Edgewood Triangle West - Phase II (HWQ724B) | 2 | PRELIMINARY DESIGN | Sep 2010 | Jan 2011 | Sep 2010 | Jan 2011
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200519 | SEQ - Brookville-Edgewood Triangle West - Phase II (HWQ724B) | 3 | FINAL DESIGN | Jan 2011 | Jul 2011 | Jan 2011 | Jul 2011
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200519 | SEQ - Brookville-Edgewood Triangle West - Phase II (HWQ724B) | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2011 | Oct 2011 | Mar 2014 | Jun 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200519 | SEQ - Brookville-Edgewood Triangle West - Phase II (HWQ724B) | 5 | CONSTRUCTION TO 25% | Oct 2011 | Feb 2012 | Jun 2014 | Jun 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200519 | SEQ - Brookville-Edgewood Triangle West - Phase II (HWQ724B) | 6 | CONSTRUCTION TO 50% | Feb 2012 | Jun 2012 | Jun 2014 | Jun 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200519 | SEQ - Brookville-Edgewood Triangle West - Phase II (HWQ724B) | 7 | CONSTRUCTION TO 75% | Jun 2012 | Oct 2012 | Jun 2014 | Jun 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200519 | SEQ - Brookville-Edgewood Triangle West - Phase II (HWQ724B) | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2012 | Jan 2013 | Jun 2014 | Jun 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200519 | SEQ - Brookville-Edgewood Triangle West - Phase II (HWQ724B) | 9 | SUBSTANTIAL COMPLETION | Jan 2013 | Mar 2013 | Jun 2014 | Jun 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200519 | SEQ - Brookville-Edgewood Triangle West - Phase II (HWQ724B) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2013 | Apr 2013 | Jun 2014 | Mar 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200558 | Install of storm SE & replacement of sanitary SE&dist.WM | 1 | DEVELOP SCOPE | Aug 2019 | May 2020 | Aug 2019 | May 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200558 | Install of storm SE & replacement of sanitary SE&dist.WM | 2 | PRELIMINARY DESIGN | May 2020 | May 2021 | May 2020 | May 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200558 | Install of storm SE & replacement of sanitary SE&dist.WM | 3 | FINAL DESIGN | May 2021 | Nov 2022 | May 2021 | Nov 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200558 | Install of storm SE & replacement of sanitary SE&dist.WM | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2022 | Aug 2023 | Nov 2022 | Aug 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200558 | Install of storm SE & replacement of sanitary SE&dist.WM | 5 | CONSTRUCTION TO 25% | Aug 2023 | Jul 2024 | Aug 2023 | Jul 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200558 | Install of storm SE & replacement of sanitary SE&dist.WM | 6 | CONSTRUCTION TO 50% | Jul 2024 | Jul 2025 | Jul 2024 | Jul 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200558 | Install of storm SE & replacement of sanitary SE&dist.WM | 7 | CONSTRUCTION TO 75% | Jul 2025 | Jul 2026 | Jul 2025 | Jul 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200558 | Install of storm SE & replacement of sanitary SE&dist.WM | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2026 | Apr 2027 | Jul 2026 | Apr 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200558 | Install of storm SE & replacement of sanitary SE&dist.WM | 9 | SUBSTANTIAL COMPLETION | Apr 2027 | Oct 2027 | Apr 2027 | Oct 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200558 | Install of storm SE & replacement of sanitary SE&dist.WM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2027 | Jan 2028 | Oct 2027 | Jan 2028
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200562 | SEQ - Storm Sewer & WM Work in 158th Street (HWQ121B3) | 1 | DEVELOP SCOPE | Feb 2014 | May 2014 | Feb 2014 | May 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200562 | SEQ - Storm Sewer & WM Work in 158th Street (HWQ121B3) | 2 | PRELIMINARY DESIGN | May 2014 | Sep 2014 | May 2014 | Sep 2014
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200562 | SEQ - Storm Sewer & WM Work in 158th Street (HWQ121B3) | 3 | FINAL DESIGN | Sep 2014 | Mar 2015 | Sep 2014 | Mar 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200562 | SEQ - Storm Sewer & WM Work in 158th Street (HWQ121B3) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2015 | Jun 2015 | Mar 2015 | Jun 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200562 | SEQ - Storm Sewer & WM Work in 158th Street (HWQ121B3) | 5 | CONSTRUCTION TO 25% | Jun 2015 | Oct 2015 | Jun 2015 | Oct 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200562 | SEQ - Storm Sewer & WM Work in 158th Street (HWQ121B3) | 6 | CONSTRUCTION TO 50% | Oct 2015 | Feb 2016 | Oct 2015 | Feb 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200562 | SEQ - Storm Sewer & WM Work in 158th Street (HWQ121B3) | 7 | CONSTRUCTION TO 75% | Feb 2016 | Jun 2016 | Feb 2016 | Jun 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200562 | SEQ - Storm Sewer & WM Work in 158th Street (HWQ121B3) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2016 | Sep 2016 | Jun 2016 | Sep 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200562 | SEQ - Storm Sewer & WM Work in 158th Street (HWQ121B3) | 9 | SUBSTANTIAL COMPLETION | Sep 2016 | Nov 2016 | Sep 2016 | Nov 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200562 | SEQ - Storm Sewer & WM Work in 158th Street (HWQ121B3) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2016 | Dec 2016 | Nov 2016 | Sep 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200578 | SEQ - Storm & San Sewers, WM Work in Foch Blvd (HWQ200578) | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200578 | SEQ - Storm & San Sewers, WM Work in Foch Blvd (HWQ200578) | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200578 | SEQ - Storm & San Sewers, WM Work in Foch Blvd (HWQ200578) | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200578 | SEQ - Storm & San Sewers, WM Work in Foch Blvd (HWQ200578) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200578 | SEQ - Storm & San Sewers, WM Work in Foch Blvd (HWQ200578) | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200578 | SEQ - Storm & San Sewers, WM Work in Foch Blvd (HWQ200578) | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200578 | SEQ - Storm & San Sewers, WM Work in Foch Blvd (HWQ200578) | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200578 | SEQ - Storm & San Sewers, WM Work in Foch Blvd (HWQ200578) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200578 | SEQ - Storm & San Sewers, WM Work in Foch Blvd (HWQ200578) | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200578 | SEQ - Storm & San Sewers, WM Work in Foch Blvd (HWQ200578) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Jun 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200586 | Broad Channel: Storm & San Sewers in W 11th Rd. (HWQ1182B) | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200586 | Broad Channel: Storm & San Sewers in W 11th Rd. (HWQ1182B) | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200586 | Broad Channel: Storm & San Sewers in W 11th Rd. (HWQ1182B) | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200586 | Broad Channel: Storm & San Sewers in W 11th Rd. (HWQ1182B) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200586 | Broad Channel: Storm & San Sewers in W 11th Rd. (HWQ1182B) | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200586 | Broad Channel: Storm & San Sewers in W 11th Rd. (HWQ1182B) | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200586 | Broad Channel: Storm & San Sewers in W 11th Rd. (HWQ1182B) | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200586 | Broad Channel: Storm & San Sewers in W 11th Rd. (HWQ1182B) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200586 | Broad Channel: Storm & San Sewers in W 11th Rd. (HWQ1182B) | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200586 | Broad Channel: Storm & San Sewers in W 11th Rd. (HWQ1182B) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Jul 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200592 | SEQ - Rosedale South, HWQ274F2 | 1 | DEVELOP SCOPE | Jun 2019 | Feb 2020 | Jun 2019 | Feb 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200592 | SEQ - Rosedale South, HWQ274F2 | 2 | PRELIMINARY DESIGN | Feb 2020 | Feb 2021 | Feb 2020 | Feb 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200592 | SEQ - Rosedale South, HWQ274F2 | 3 | FINAL DESIGN | Feb 2021 | Aug 2022 | Feb 2021 | Aug 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200592 | SEQ - Rosedale South, HWQ274F2 | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2022 | May 2023 | Aug 2022 | May 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200592 | SEQ - Rosedale South, HWQ274F2 | 5 | CONSTRUCTION TO 25% | May 2023 | May 2024 | May 2023 | May 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200592 | SEQ - Rosedale South, HWQ274F2 | 6 | CONSTRUCTION TO 50% | May 2024 | Apr 2025 | May 2024 | Apr 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200592 | SEQ - Rosedale South, HWQ274F2 | 7 | CONSTRUCTION TO 75% | Apr 2025 | Apr 2026 | Apr 2025 | Apr 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200592 | SEQ - Rosedale South, HWQ274F2 | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2026 | Jan 2027 | Apr 2026 | Jan 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200592 | SEQ - Rosedale South, HWQ274F2 | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Jul 2027 | Jan 2027 | Jul 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200592 | SEQ - Rosedale South, HWQ274F2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2027 | Oct 2027 | Jul 2027 | Oct 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200595 | Westbourne Ave-Norton Drive Recon (HWQ1187, SAND1187) | 1 | DEVELOP SCOPE | Mar 2018 | May 2018 | Mar 2018 | May 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200595 | Westbourne Ave-Norton Drive Recon (HWQ1187, SAND1187) | 2 | PRELIMINARY DESIGN | May 2018 | Sep 2018 | May 2018 | Sep 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200595 | Westbourne Ave-Norton Drive Recon (HWQ1187, SAND1187) | 3 | FINAL DESIGN | Sep 2018 | Mar 2019 | Sep 2018 | Mar 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200595 | Westbourne Ave-Norton Drive Recon (HWQ1187, SAND1187) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2019 | Jun 2019 | Mar 2019 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200595 | Westbourne Ave-Norton Drive Recon (HWQ1187, SAND1187) | 5 | CONSTRUCTION TO 25% | Jun 2019 | Oct 2019 | Jun 2019 | Oct 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200595 | Westbourne Ave-Norton Drive Recon (HWQ1187, SAND1187) | 6 | CONSTRUCTION TO 50% | Oct 2019 | Feb 2020 | Oct 2019 | Feb 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200595 | Westbourne Ave-Norton Drive Recon (HWQ1187, SAND1187) | 7 | CONSTRUCTION TO 75% | Feb 2020 | Jun 2020 | Feb 2020 | Jun 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200595 | Westbourne Ave-Norton Drive Recon (HWQ1187, SAND1187) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200595 | Westbourne Ave-Norton Drive Recon (HWQ1187, SAND1187) | 9 | SUBSTANTIAL COMPLETION | Sep 2020 | Nov 2020 | Sep 2020 | Nov 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200595 | Westbourne Ave-Norton Drive Recon (HWQ1187, SAND1187) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2020 | Dec 2020 | Nov 2020 | Sep 2029
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200604 | St. SE Ext in College Pl btwn 5th ave to US Bulkhead Line QN | 1 | DEVELOP SCOPE | Nov 2020 | Feb 2021 | Nov 2020 | Feb 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200604 | St. SE Ext in College Pl btwn 5th ave to US Bulkhead Line QN | 2 | PRELIMINARY DESIGN | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200604 | St. SE Ext in College Pl btwn 5th ave to US Bulkhead Line QN | 3 | FINAL DESIGN | Jun 2021 | Dec 2021 | Jun 2021 | Dec 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200604 | St. SE Ext in College Pl btwn 5th ave to US Bulkhead Line QN | 4 | BID AWARD AND REGISTER CONTRCT | Dec 2021 | Mar 2022 | Dec 2021 | Mar 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200604 | St. SE Ext in College Pl btwn 5th ave to US Bulkhead Line QN | 5 | CONSTRUCTION TO 25% | Mar 2022 | Jul 2022 | Mar 2022 | Jul 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200604 | St. SE Ext in College Pl btwn 5th ave to US Bulkhead Line QN | 6 | CONSTRUCTION TO 50% | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200604 | St. SE Ext in College Pl btwn 5th ave to US Bulkhead Line QN | 7 | CONSTRUCTION TO 75% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200604 | St. SE Ext in College Pl btwn 5th ave to US Bulkhead Line QN | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2023 | May 2023 | Feb 2023 | May 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200604 | St. SE Ext in College Pl btwn 5th ave to US Bulkhead Line QN | 9 | SUBSTANTIAL COMPLETION | May 2023 | Jul 2023 | May 2023 | Jul 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200604 | St. SE Ext in College Pl btwn 5th ave to US Bulkhead Line QN | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200605 | SEQ - Installation of relief sewer,storm sewers&WM(HWQ1206) | 1 | DEVELOP SCOPE | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200605 | SEQ - Installation of relief sewer,storm sewers&WM(HWQ1206) | 2 | PRELIMINARY DESIGN | Apr 2025 | Jul 2025 | Apr 2025 | Jul 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200605 | SEQ - Installation of relief sewer,storm sewers&WM(HWQ1206) | 3 | FINAL DESIGN | Jul 2025 | Jan 2026 | Jul 2025 | Jan 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200605 | SEQ - Installation of relief sewer,storm sewers&WM(HWQ1206) | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2026 | Apr 2026 | Jan 2026 | Apr 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200605 | SEQ - Installation of relief sewer,storm sewers&WM(HWQ1206) | 5 | CONSTRUCTION TO 25% | Apr 2026 | Aug 2026 | Apr 2026 | Aug 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200605 | SEQ - Installation of relief sewer,storm sewers&WM(HWQ1206) | 6 | CONSTRUCTION TO 50% | Aug 2026 | Dec 2026 | Aug 2026 | Dec 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200605 | SEQ - Installation of relief sewer,storm sewers&WM(HWQ1206) | 7 | CONSTRUCTION TO 75% | Dec 2026 | Apr 2027 | Dec 2026 | Apr 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200605 | SEQ - Installation of relief sewer,storm sewers&WM(HWQ1206) | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2027 | Jul 2027 | Apr 2027 | Jul 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200605 | SEQ - Installation of relief sewer,storm sewers&WM(HWQ1206) | 9 | SUBSTANTIAL COMPLETION | Jul 2027 | Sep 2027 | Jul 2027 | Sep 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200605 | SEQ - Installation of relief sewer,storm sewers&WM(HWQ1206) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Oct 2027 | Sep 2027 | Oct 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS003 | SEQ - Sewer When & Where Contract in SE Queens (HWQ1195) | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS003 | SEQ - Sewer When & Where Contract in SE Queens (HWQ1195) | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS003 | SEQ - Sewer When & Where Contract in SE Queens (HWQ1195) | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS003 | SEQ - Sewer When & Where Contract in SE Queens (HWQ1195) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS003 | SEQ - Sewer When & Where Contract in SE Queens (HWQ1195) | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS003 | SEQ - Sewer When & Where Contract in SE Queens (HWQ1195) | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS003 | SEQ - Sewer When & Where Contract in SE Queens (HWQ1195) | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS003 | SEQ - Sewer When & Where Contract in SE Queens (HWQ1195) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS003 | SEQ - Sewer When & Where Contract in SE Queens (HWQ1195) | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS003 | SEQ - Sewer When & Where Contract in SE Queens (HWQ1195) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Jun 2028
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS004 | SEQ -SEWER WHEN & WHERE CONTRACT IN S.E. QNS | 1 | DEVELOP SCOPE | Jun 2019 | Aug 2019 | Jun 2019 | Aug 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS004 | SEQ -SEWER WHEN & WHERE CONTRACT IN S.E. QNS | 2 | PRELIMINARY DESIGN | Aug 2019 | Dec 2019 | Aug 2019 | Dec 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS004 | SEQ -SEWER WHEN & WHERE CONTRACT IN S.E. QNS | 3 | FINAL DESIGN | Dec 2019 | Jun 2020 | Dec 2019 | Jun 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS004 | SEQ -SEWER WHEN & WHERE CONTRACT IN S.E. QNS | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS004 | SEQ -SEWER WHEN & WHERE CONTRACT IN S.E. QNS | 5 | CONSTRUCTION TO 25% | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS004 | SEQ -SEWER WHEN & WHERE CONTRACT IN S.E. QNS | 6 | CONSTRUCTION TO 50% | Jan 2021 | May 2021 | Jan 2021 | May 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS004 | SEQ -SEWER WHEN & WHERE CONTRACT IN S.E. QNS | 7 | CONSTRUCTION TO 75% | May 2021 | Sep 2021 | May 2021 | Sep 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS004 | SEQ -SEWER WHEN & WHERE CONTRACT IN S.E. QNS | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Dec 2021 | Sep 2021 | Dec 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS004 | SEQ -SEWER WHEN & WHERE CONTRACT IN S.E. QNS | 9 | SUBSTANTIAL COMPLETION | Dec 2021 | Feb 2022 | Dec 2021 | Feb 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS004 | SEQ -SEWER WHEN & WHERE CONTRACT IN S.E. QNS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2022 | Mar 2022 | Feb 2022 | Jun 2028
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS005 | SEQ - Sewer When & Where Contract in SE Queens | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Aug 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS005 | SEQ - Sewer When & Where Contract in SE Queens | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS005 | SEQ - Sewer When & Where Contract in SE Queens | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS005 | SEQ - Sewer When & Where Contract in SE Queens | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS005 | SEQ - Sewer When & Where Contract in SE Queens | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS005 | SEQ - Sewer When & Where Contract in SE Queens | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2022 | May 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS005 | SEQ - Sewer When & Where Contract in SE Queens | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2022 | Sep 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS005 | SEQ - Sewer When & Where Contract in SE Queens | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS005 | SEQ - Sewer When & Where Contract in SE Queens | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2022 | Feb 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS005 | SEQ - Sewer When & Where Contract in SE Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Feb 2023 | Jun 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD1 | Southeast Queens Priority Grids -- Group 1 (DOTSEQ01) | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Jun 2016 | Sep 2016
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD1 | Southeast Queens Priority Grids -- Group 1 (DOTSEQ01) | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Sep 2016 | Jan 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD1 | Southeast Queens Priority Grids -- Group 1 (DOTSEQ01) | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Jan 2017 | Jul 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD1 | Southeast Queens Priority Grids -- Group 1 (DOTSEQ01) | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Jul 2017 | Oct 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD1 | Southeast Queens Priority Grids -- Group 1 (DOTSEQ01) | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Oct 2017 | Feb 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD1 | Southeast Queens Priority Grids -- Group 1 (DOTSEQ01) | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Feb 2018 | Jun 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD1 | Southeast Queens Priority Grids -- Group 1 (DOTSEQ01) | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD1 | Southeast Queens Priority Grids -- Group 1 (DOTSEQ01) | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | Oct 2018 | Jan 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD1 | Southeast Queens Priority Grids -- Group 1 (DOTSEQ01) | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Jan 2019 | Mar 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD1 | Southeast Queens Priority Grids -- Group 1 (DOTSEQ01) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Mar 2019 | Aug 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD2 | Southeast Queens Priority Grids -- Group 2 (DOTSEQ02) | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2017 | Sep 2017
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD2 | Southeast Queens Priority Grids -- Group 2 (DOTSEQ02) | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2017 | Jan 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD2 | Southeast Queens Priority Grids -- Group 2 (DOTSEQ02) | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jan 2018 | Jul 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD2 | Southeast Queens Priority Grids -- Group 2 (DOTSEQ02) | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2018 | Oct 2018
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD2 | Southeast Queens Priority Grids -- Group 2 (DOTSEQ02) | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD2 | Southeast Queens Priority Grids -- Group 2 (DOTSEQ02) | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD2 | Southeast Queens Priority Grids -- Group 2 (DOTSEQ02) | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jun 2019 | Oct 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD2 | Southeast Queens Priority Grids -- Group 2 (DOTSEQ02) | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Oct 2019 | Jan 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD2 | Southeast Queens Priority Grids -- Group 2 (DOTSEQ02) | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jan 2020 | Mar 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD2 | Southeast Queens Priority Grids -- Group 2 (DOTSEQ02) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Mar 2020 | Sep 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ-SACBA | SEQ -Design & Constr St. Albans Cloudburst Green, HWQ1196 | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ-SACBA | SEQ -Design & Constr St. Albans Cloudburst Green, HWQ1196 | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ-SACBA | SEQ -Design & Constr St. Albans Cloudburst Green, HWQ1196 | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ-SACBA | SEQ -Design & Constr St. Albans Cloudburst Green, HWQ1196 | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ-SACBA | SEQ -Design & Constr St. Albans Cloudburst Green, HWQ1196 | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ-SACBA | SEQ -Design & Constr St. Albans Cloudburst Green, HWQ1196 | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ-SACBA | SEQ -Design & Constr St. Albans Cloudburst Green, HWQ1196 | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | May 2024 | Sep 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ-SACBA | SEQ -Design & Constr St. Albans Cloudburst Green, HWQ1196 | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ-SACBA | SEQ -Design & Constr St. Albans Cloudburst Green, HWQ1196 | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Dec 2024 | Feb 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ-SACBA | SEQ -Design & Constr St. Albans Cloudburst Green, HWQ1196 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Mar 2025 | Feb 2025 | Mar 2025
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TLCWOOD | TLC - NEW OFFICE FACILITY - 24-55 BQE WEST | 1 | DEVELOP SCOPE | May 2015 | Jul 2015 | May 2015 | Jul 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TLCWOOD | TLC - NEW OFFICE FACILITY - 24-55 BQE WEST | 2 | PRELIMINARY DESIGN | Jul 2015 | Nov 2015 | Jul 2015 | Nov 2015
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TLCWOOD | TLC - NEW OFFICE FACILITY - 24-55 BQE WEST | 3 | FINAL DESIGN | Nov 2015 | May 2016 | Nov 2015 | May 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TLCWOOD | TLC - NEW OFFICE FACILITY - 24-55 BQE WEST | 4 | BID AWARD AND REGISTER CONTRCT | May 2016 | Aug 2016 | May 2019 | Aug 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TLCWOOD | TLC - NEW OFFICE FACILITY - 24-55 BQE WEST | 5 | CONSTRUCTION TO 25% | Aug 2016 | Dec 2016 | Aug 2019 | Dec 2019
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TLCWOOD | TLC - NEW OFFICE FACILITY - 24-55 BQE WEST | 6 | CONSTRUCTION TO 50% | Dec 2016 | Apr 2017 | Dec 2019 | Apr 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TLCWOOD | TLC - NEW OFFICE FACILITY - 24-55 BQE WEST | 7 | CONSTRUCTION TO 75% | Apr 2017 | Aug 2017 | Apr 2020 | Aug 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TLCWOOD | TLC - NEW OFFICE FACILITY - 24-55 BQE WEST | 8 | ORIGINAL EQUIP & FURNISHING | Aug 2017 | Nov 2017 | Aug 2020 | Nov 2020
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TLCWOOD | TLC - NEW OFFICE FACILITY - 24-55 BQE WEST | 9 | SUBSTANTIAL COMPLETION | Nov 2017 | Jan 2018 | Nov 2020 | Jan 2021
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TLCWOOD | TLC - NEW OFFICE FACILITY - 24-55 BQE WEST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2018 | Feb 2018 | Jan 2021 | Jun 2027
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TLCWOOD1 | TLC - NEW OFFICE FACILITY -FY22 April Plan | 1 | PROJECT START | Jun 2022 | Jun 2022 | Jun 2022 | Jun 2022
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TLCWOOD1 | TLC - NEW OFFICE FACILITY -FY22 April Plan | 2 | DESIGN START | Jun 2022 | Jul 2024 | Jun 2022 | Jul 2024
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TLCWOOD1 | TLC - NEW OFFICE FACILITY -FY22 April Plan | 3 | DESIGN COMPLETION | Jul 2024 | Sep 2026 | Jul 2024 | Sep 2026
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TLCWOOD1 | TLC - NEW OFFICE FACILITY -FY22 April Plan | 4 | CONSTRUCTION START | Sep 2026 | Oct 2028 | Sep 2026 | Oct 2028
20231026 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TLCWOOD1 | TLC - NEW OFFICE FACILITY -FY22 April Plan | 5 | CONSTRUCTION COMPLETION | Oct 2028 | Apr 2031 | Oct 2028 | Apr 2031
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOS201 | DSNY - Rapid Roll Up Doors | 1 | DEVELOP SCOPE | Jun 2026 | Jun 2026 | Jun 2026 | Jun 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOS201 | DSNY - Rapid Roll Up Doors | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2026 | Aug 2026 | Jul 2026 | Aug 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOS201 | DSNY - Rapid Roll Up Doors | 3 | CONSTRUCTION TO 50% | Aug 2026 | Feb 2027 | Aug 2026 | Feb 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOS201 | DSNY - Rapid Roll Up Doors | 4 | CONSTRUCTION TO 75% | Feb 2027 | May 2027 | Feb 2027 | May 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOS201 | DSNY - Rapid Roll Up Doors | 5 | SUBSTANTIAL COMPLETION | May 2027 | Jul 2027 | May 2027 | Jul 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOS201 | DSNY - Rapid Roll Up Doors | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2027 | Aug 2027 | Jul 2027 | Aug 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOT211 | DOT- 32-11 Harper St Envelope Improvements and Solar PV | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2022 | Jun 2022 | Jun 2022
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOT211 | DOT- 32-11 Harper St Envelope Improvements and Solar PV | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Aug 2022 | Jul 2022 | Aug 2022
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOT211 | DOT- 32-11 Harper St Envelope Improvements and Solar PV | 3 | CONSTRUCTION TO 50% | Aug 2022 | Feb 2023 | Aug 2022 | Feb 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOT211 | DOT- 32-11 Harper St Envelope Improvements and Solar PV | 4 | CONSTRUCTION TO 75% | Feb 2023 | May 2023 | Feb 2023 | May 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOT211 | DOT- 32-11 Harper St Envelope Improvements and Solar PV | 5 | SUBSTANTIAL COMPLETION | May 2023 | Jul 2023 | May 2023 | Jul 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOT211 | DOT- 32-11 Harper St Envelope Improvements and Solar PV | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | APINYPD01 | 100th PRECINCT COMPREHENSIVE ELECTRIFICATION | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | APINYPD01 | 100th PRECINCT COMPREHENSIVE ELECTRIFICATION | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | APINYPD01 | 100th PRECINCT COMPREHENSIVE ELECTRIFICATION | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | APINYPD01 | 100th PRECINCT COMPREHENSIVE ELECTRIFICATION | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | APINYPD01 | 100th PRECINCT COMPREHENSIVE ELECTRIFICATION | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | APINYPD01 | 100th PRECINCT COMPREHENSIVE ELECTRIFICATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | C75BULOVA | Reconstruction of Bulova Building Suite 330 | 1 | DESIGN | Jun 2022 | Apr 2023 | Jun 2022 | Apr 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | C75BULOVA | Reconstruction of Bulova Building Suite 330 | 2 | BID AWARD AND REGISTER CONTRCT | Apr 2023 | Mar 2024 | Apr 2023 | Mar 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | C75BULOVA | Reconstruction of Bulova Building Suite 330 | 3 | CONSTRUCTION TO 75% | Apr 2024 | Nov 2025 | Apr 2024 | Nov 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | C75BULOVA | Reconstruction of Bulova Building Suite 330 | 4 | SUBSTANTIAL COMPLETION | Nov 2025 | Mar 2026 | Nov 2025 | Mar 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | C75BULOVA | Reconstruction of Bulova Building Suite 330 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | May 2026 | Mar 2026 | Aug 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO277ADA | 25-10 COURT SQUARE - ADA LIFT REPLACEMENT | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO277ADA | 25-10 COURT SQUARE - ADA LIFT REPLACEMENT | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO277ADA | 25-10 COURT SQUARE - ADA LIFT REPLACEMENT | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO277ADA | 25-10 COURT SQUARE - ADA LIFT REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO277ADA | 25-10 COURT SQUARE - ADA LIFT REPLACEMENT | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO277ADA | 25-10 COURT SQUARE - ADA LIFT REPLACEMENT | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO277ADA | 25-10 COURT SQUARE - ADA LIFT REPLACEMENT | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO277ADA | 25-10 COURT SQUARE - ADA LIFT REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO277ADA | 25-10 COURT SQUARE - ADA LIFT REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO277ADA | 25-10 COURT SQUARE - ADA LIFT REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296EV | 125-01 QUEENS BLVD. ANNEX ELEVATOR MODERNIZATION | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296EV | 125-01 QUEENS BLVD. ANNEX ELEVATOR MODERNIZATION | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296EV | 125-01 QUEENS BLVD. ANNEX ELEVATOR MODERNIZATION | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296EV | 125-01 QUEENS BLVD. ANNEX ELEVATOR MODERNIZATION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296EV | 125-01 QUEENS BLVD. ANNEX ELEVATOR MODERNIZATION | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296EV | 125-01 QUEENS BLVD. ANNEX ELEVATOR MODERNIZATION | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296EV | 125-01 QUEENS BLVD. ANNEX ELEVATOR MODERNIZATION | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | May 2024 | Sep 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296EV | 125-01 QUEENS BLVD. ANNEX ELEVATOR MODERNIZATION | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296EV | 125-01 QUEENS BLVD. ANNEX ELEVATOR MODERNIZATION | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Dec 2024 | Feb 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296EV | 125-01 QUEENS BLVD. ANNEX ELEVATOR MODERNIZATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Jun 2026 | Feb 2025 | Jun 2030
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298CHIL | 151-20 JAMAICA AVE.- CHILLER REPLACEMENT | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298CHIL | 151-20 JAMAICA AVE.- CHILLER REPLACEMENT | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298CHIL | 151-20 JAMAICA AVE.- CHILLER REPLACEMENT | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298CHIL | 151-20 JAMAICA AVE.- CHILLER REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298CHIL | 151-20 JAMAICA AVE.- CHILLER REPLACEMENT | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298CHIL | 151-20 JAMAICA AVE.- CHILLER REPLACEMENT | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298CHIL | 151-20 JAMAICA AVE.- CHILLER REPLACEMENT | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | May 2024 | Sep 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298CHIL | 151-20 JAMAICA AVE.- CHILLER REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298CHIL | 151-20 JAMAICA AVE.- CHILLER REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Dec 2024 | Feb 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298CHIL | 151-20 JAMAICA AVE.- CHILLER REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Mar 2025 | Feb 2025 | Mar 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298RF | 151-20 JAMAICA AVE ROOF REHAB | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298RF | 151-20 JAMAICA AVE ROOF REHAB | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298RF | 151-20 JAMAICA AVE ROOF REHAB | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298RF | 151-20 JAMAICA AVE ROOF REHAB | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298RF | 151-20 JAMAICA AVE ROOF REHAB | 5 | CONSTRUCTION TO 25% | Jun 2022 | Sep 2022 | Jun 2025 | Sep 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298RF | 151-20 JAMAICA AVE ROOF REHAB | 6 | CONSTRUCTION TO 50% | Sep 2022 | Jan 2023 | Sep 2025 | Jan 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298RF | 151-20 JAMAICA AVE ROOF REHAB | 7 | CONSTRUCTION TO 75% | Jan 2023 | May 2023 | Jan 2026 | May 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298RF | 151-20 JAMAICA AVE ROOF REHAB | 8 | ORIGINAL EQUIP & FURNISHING | May 2023 | Aug 2023 | May 2026 | Aug 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298RF | 151-20 JAMAICA AVE ROOF REHAB | 9 | SUBSTANTIAL COMPLETION | Aug 2023 | Oct 2023 | Aug 2026 | Oct 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298RF | 151-20 JAMAICA AVE ROOF REHAB | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2023 | Nov 2023 | Oct 2026 | Jun 2028
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO299RF | 89-17 SUTPHIN BLVD- ROOF | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO299RF | 89-17 SUTPHIN BLVD- ROOF | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO299RF | 89-17 SUTPHIN BLVD- ROOF | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO299RF | 89-17 SUTPHIN BLVD- ROOF | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO299RF | 89-17 SUTPHIN BLVD- ROOF | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO299RF | 89-17 SUTPHIN BLVD- ROOF | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO299RF | 89-17 SUTPHIN BLVD- ROOF | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO299RF | 89-17 SUTPHIN BLVD- ROOF | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO299RF | 89-17 SUTPHIN BLVD- ROOF | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO299RF | 89-17 SUTPHIN BLVD- ROOF | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300415A | DASNY - 88-11 SUTPHIN BLVD.- RENOVATION | 1 | DEVELOP SCOPE | Jan 2002 | Mar 2002 | Jan 2002 | Mar 2002
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300415A | DASNY - 88-11 SUTPHIN BLVD.- RENOVATION | 2 | PRELIMINARY DESIGN | Apr 2002 | Jul 2002 | Apr 2002 | Jul 2002
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300415A | DASNY - 88-11 SUTPHIN BLVD.- RENOVATION | 3 | FINAL DESIGN | Jul 2002 | Jan 2003 | Jul 2002 | Jan 2003
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300415A | DASNY - 88-11 SUTPHIN BLVD.- RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2003 | Apr 2003 | Jan 2003 | Apr 2003
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300415A | DASNY - 88-11 SUTPHIN BLVD.- RENOVATION | 5 | CONSTRUCTION TO 25% | Apr 2003 | Dec 2005 | Apr 2003 | Dec 2005
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300415A | DASNY - 88-11 SUTPHIN BLVD.- RENOVATION | 6 | CONSTRUCTION TO 50% | Dec 2005 | Jul 2008 | Jun 2027 | Sep 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300415A | DASNY - 88-11 SUTPHIN BLVD.- RENOVATION | 7 | CONSTRUCTION TO 75% | Jul 2008 | Mar 2011 | Sep 2027 | May 2028
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300415A | DASNY - 88-11 SUTPHIN BLVD.- RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2011 | Sep 2011 | Jun 2028 | Nov 2028
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300415A | DASNY - 88-11 SUTPHIN BLVD.- RENOVATION | 9 | SUBSTANTIAL COMPLETION | Sep 2011 | Dec 2011 | Nov 2028 | Feb 2029
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300415A | DASNY - 88-11 SUTPHIN BLVD.- RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2011 | Dec 2011 | Feb 2029 | Feb 2029
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300FIRE | 88-11 SUTPHIN BLVD. FIRE ALARM SPRINKLER SYSTEM UPGRADE | 1 | DEVELOP SCOPE | Feb 2016 | Apr 2016 | Jun 2022 | Jun 2028
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300FIRE | 88-11 SUTPHIN BLVD. FIRE ALARM SPRINKLER SYSTEM UPGRADE | 2 | PRELIMINARY DESIGN | May 2016 | Aug 2016 | Jul 2028 | Oct 2028
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300FIRE | 88-11 SUTPHIN BLVD. FIRE ALARM SPRINKLER SYSTEM UPGRADE | 3 | FINAL DESIGN | Aug 2016 | Feb 2017 | Oct 2028 | Apr 2029
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300FIRE | 88-11 SUTPHIN BLVD. FIRE ALARM SPRINKLER SYSTEM UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2017 | May 2017 | Apr 2029 | Jul 2029
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300FIRE | 88-11 SUTPHIN BLVD. FIRE ALARM SPRINKLER SYSTEM UPGRADE | 5 | CONSTRUCTION TO 25% | May 2017 | Sep 2017 | Jul 2029 | Nov 2029
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300FIRE | 88-11 SUTPHIN BLVD. FIRE ALARM SPRINKLER SYSTEM UPGRADE | 6 | CONSTRUCTION TO 50% | Sep 2017 | Jan 2018 | Nov 2029 | Mar 2030
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300FIRE | 88-11 SUTPHIN BLVD. FIRE ALARM SPRINKLER SYSTEM UPGRADE | 7 | CONSTRUCTION TO 75% | Jan 2018 | May 2018 | Mar 2030 | Jul 2030
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300FIRE | 88-11 SUTPHIN BLVD. FIRE ALARM SPRINKLER SYSTEM UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | May 2018 | Aug 2018 | Jul 2030 | Oct 2030
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300FIRE | 88-11 SUTPHIN BLVD. FIRE ALARM SPRINKLER SYSTEM UPGRADE | 9 | SUBSTANTIAL COMPLETION | Aug 2018 | Oct 2018 | Oct 2030 | Dec 2030
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300FIRE | 88-11 SUTPHIN BLVD. FIRE ALARM SPRINKLER SYSTEM UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2018 | Nov 2018 | Dec 2030 | Jan 2031
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300RF | 88-11 SUTPHIN BOULEVARD - ROOF | 1 | DEVELOP SCOPE | Jan 2022 | Apr 2022 | Jan 2022 | Apr 2022
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300RF | 88-11 SUTPHIN BOULEVARD - ROOF | 2 | PRELIMINARY DESIGN | Apr 2022 | Aug 2022 | Apr 2022 | Aug 2022
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300RF | 88-11 SUTPHIN BOULEVARD - ROOF | 3 | FINAL DESIGN | Aug 2022 | Feb 2023 | Aug 2022 | Feb 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300RF | 88-11 SUTPHIN BOULEVARD - ROOF | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2023 | May 2023 | Feb 2023 | May 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300RF | 88-11 SUTPHIN BOULEVARD - ROOF | 5 | CONSTRUCTION TO 25% | May 2023 | Sep 2023 | May 2023 | Sep 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300RF | 88-11 SUTPHIN BOULEVARD - ROOF | 6 | CONSTRUCTION TO 50% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300RF | 88-11 SUTPHIN BOULEVARD - ROOF | 7 | CONSTRUCTION TO 75% | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300RF | 88-11 SUTPHIN BOULEVARD - ROOF | 8 | ORIGINAL EQUIP & FURNISHING | May 2024 | Aug 2024 | May 2024 | Aug 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300RF | 88-11 SUTPHIN BOULEVARD - ROOF | 9 | SUBSTANTIAL COMPLETION | Aug 2024 | Sep 2024 | Aug 2024 | Sep 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300RF | 88-11 SUTPHIN BOULEVARD - ROOF | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2024 | Oct 2024 | Oct 2024 | Oct 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | DOEQ388 | Solar photovoltaic system | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | DOEQ388 | Solar photovoltaic system | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | DOEQ388 | Solar photovoltaic system | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | DOEQ388 | Solar photovoltaic system | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | DOEQ388 | Solar photovoltaic system | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | DOEQ388 | Solar photovoltaic system | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0005 | Jamaica Arms Hotel/Family Respite Residence | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2023 | Jun 2023 | Jun 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0005 | Jamaica Arms Hotel/Family Respite Residence | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0005 | Jamaica Arms Hotel/Family Respite Residence | 3 | CONSTRUCTION TO 50% | Aug 2023 | Feb 2024 | Jun 2024 | Nov 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0005 | Jamaica Arms Hotel/Family Respite Residence | 4 | CONSTRUCTION TO 75% | Feb 2024 | May 2024 | Nov 2024 | Feb 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0005 | Jamaica Arms Hotel/Family Respite Residence | 5 | SUBSTANTIAL COMPLETION | May 2024 | Jul 2024 | Feb 2025 | Apr 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0005 | Jamaica Arms Hotel/Family Respite Residence | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2024 | Aug 2024 | Apr 2025 | May 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0009 | OCME Queens Chief Medical Examiner | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2022 | Jun 2022 | Jun 2022
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0009 | OCME Queens Chief Medical Examiner | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Aug 2022 | Jul 2022 | Aug 2022
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0009 | OCME Queens Chief Medical Examiner | 3 | CONSTRUCTION TO 50% | Aug 2022 | Feb 2023 | Aug 2022 | Feb 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0009 | OCME Queens Chief Medical Examiner | 4 | CONSTRUCTION TO 75% | Feb 2023 | May 2023 | Feb 2023 | May 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0009 | OCME Queens Chief Medical Examiner | 5 | SUBSTANTIAL COMPLETION | May 2023 | Jul 2023 | May 2023 | Jul 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0009 | OCME Queens Chief Medical Examiner | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0002 | DCAS - Queens Borough Repair Shop Comprehensive Energy Upgr | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2023 | Jun 2023 | Jun 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0002 | DCAS - Queens Borough Repair Shop Comprehensive Energy Upgr | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0002 | DCAS - Queens Borough Repair Shop Comprehensive Energy Upgr | 3 | CONSTRUCTION TO 50% | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0002 | DCAS - Queens Borough Repair Shop Comprehensive Energy Upgr | 4 | CONSTRUCTION TO 75% | Feb 2024 | May 2024 | Feb 2024 | May 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0002 | DCAS - Queens Borough Repair Shop Comprehensive Energy Upgr | 5 | SUBSTANTIAL COMPLETION | May 2024 | Jul 2024 | May 2024 | Jul 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0002 | DCAS - Queens Borough Repair Shop Comprehensive Energy Upgr | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0003 | NYPD - Building Maintenance Section (BMS) Facility Comp | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2023 | Jun 2023 | Jun 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0003 | NYPD - Building Maintenance Section (BMS) Facility Comp | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0003 | NYPD - Building Maintenance Section (BMS) Facility Comp | 3 | CONSTRUCTION TO 50% | Jun 2025 | Nov 2025 | Jun 2025 | Nov 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0003 | NYPD - Building Maintenance Section (BMS) Facility Comp | 4 | CONSTRUCTION TO 75% | Nov 2025 | Feb 2026 | Nov 2025 | Feb 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0003 | NYPD - Building Maintenance Section (BMS) Facility Comp | 5 | SUBSTANTIAL COMPLETION | Feb 2026 | Apr 2026 | Feb 2026 | Apr 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0003 | NYPD - Building Maintenance Section (BMS) Facility Comp | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2026 | May 2026 | Apr 2026 | May 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0004 | QUEENS WEST 5/5A ENERGY EFFICIENCY UPGRADES PROJECT | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0004 | QUEENS WEST 5/5A ENERGY EFFICIENCY UPGRADES PROJECT | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0004 | QUEENS WEST 5/5A ENERGY EFFICIENCY UPGRADES PROJECT | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0004 | QUEENS WEST 5/5A ENERGY EFFICIENCY UPGRADES PROJECT | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0004 | QUEENS WEST 5/5A ENERGY EFFICIENCY UPGRADES PROJECT | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0004 | QUEENS WEST 5/5A ENERGY EFFICIENCY UPGRADES PROJECT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0010 | CUNY Laguardia Community College (DI) | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0010 | CUNY Laguardia Community College (DI) | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0010 | CUNY Laguardia Community College (DI) | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0010 | CUNY Laguardia Community College (DI) | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0010 | CUNY Laguardia Community College (DI) | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0010 | CUNY Laguardia Community College (DI) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0002 | CUNY Queensborough Community College (DI) | 1 | DEVELOP SCOPE | Jun 2025 | Jun 2025 | Jun 2025 | Jun 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0002 | CUNY Queensborough Community College (DI) | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0002 | CUNY Queensborough Community College (DI) | 3 | CONSTRUCTION TO 50% | Aug 2025 | Feb 2026 | Aug 2025 | Feb 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0002 | CUNY Queensborough Community College (DI) | 4 | CONSTRUCTION TO 75% | Feb 2026 | May 2026 | Feb 2026 | May 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0002 | CUNY Queensborough Community College (DI) | 5 | SUBSTANTIAL COMPLETION | May 2026 | Jul 2026 | May 2026 | Jul 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0002 | CUNY Queensborough Community College (DI) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2026 | Aug 2026 | Jul 2026 | Aug 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0004 | Elmhurst Hospital | 1 | DEVELOP SCOPE | Jun 2025 | Jun 2025 | Jun 2025 | Jun 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0004 | Elmhurst Hospital | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0004 | Elmhurst Hospital | 3 | CONSTRUCTION TO 50% | Aug 2025 | Feb 2026 | Aug 2025 | Feb 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0004 | Elmhurst Hospital | 4 | CONSTRUCTION TO 75% | Feb 2026 | May 2026 | Feb 2026 | May 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0004 | Elmhurst Hospital | 5 | SUBSTANTIAL COMPLETION | May 2026 | Jul 2026 | May 2026 | Jul 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-0004 | Elmhurst Hospital | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2026 | Aug 2026 | Jul 2026 | Aug 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0090 | QPL - McGOLDRICK COMMUNITY LIBRARY | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | May 2020 | Jul 2022 | Aug 2022
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0090 | QPL - McGOLDRICK COMMUNITY LIBRARY | 3 | CONSTRUCTION TO 50% | May 2020 | Nov 2020 | Aug 2022 | Feb 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0090 | QPL - McGOLDRICK COMMUNITY LIBRARY | 4 | CONSTRUCTION TO 75% | Nov 2020 | Feb 2021 | Feb 2023 | May 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0090 | QPL - McGOLDRICK COMMUNITY LIBRARY | 5 | SUBSTANTIAL COMPLETION | Feb 2021 | Apr 2021 | May 2023 | Jul 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0090 | QPL - McGOLDRICK COMMUNITY LIBRARY | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2021 | May 2021 | Jul 2023 | Aug 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0091 | QPL - OZONE PARK COMMUNITY LIBRARY | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | May 2020 | Jul 2022 | Aug 2022
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0091 | QPL - OZONE PARK COMMUNITY LIBRARY | 3 | CONSTRUCTION TO 50% | May 2020 | Nov 2020 | Aug 2022 | Feb 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0091 | QPL - OZONE PARK COMMUNITY LIBRARY | 4 | CONSTRUCTION TO 75% | Nov 2020 | Feb 2021 | Feb 2023 | May 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0091 | QPL - OZONE PARK COMMUNITY LIBRARY | 5 | SUBSTANTIAL COMPLETION | Feb 2021 | Apr 2021 | May 2023 | Jul 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0091 | QPL - OZONE PARK COMMUNITY LIBRARY | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2021 | May 2021 | Jul 2023 | Aug 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | HR25QCRT | 151-20 Jamaica Ave 4th floor | 1 | DESIGN | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | HR25QCRT | 151-20 Jamaica Ave 4th floor | 2 | CONSTRUCTION | Dec 2019 | Jun 2020 | Jun 2021 | Nov 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWQF3108 | Northern Blvd Buildout | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWQF3108 | Northern Blvd Buildout | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWQF3108 | Northern Blvd Buildout | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWQF3108 | Northern Blvd Buildout | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWQF3108 | Northern Blvd Buildout | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWQF3108 | Northern Blvd Buildout | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWQF3108 | Northern Blvd Buildout | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWQF3108 | Northern Blvd Buildout | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWQF3108 | Northern Blvd Buildout | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWQF3108 | Northern Blvd Buildout | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Jun 2027 | Mar 2026 | Jun 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWQFHUB | Hub Buildout | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2024 | Sep 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWQFHUB | Hub Buildout | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2024 | Jan 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWQFHUB | Hub Buildout | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2025 | Jul 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWQFHUB | Hub Buildout | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2025 | Oct 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWQFHUB | Hub Buildout | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2025 | Feb 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWQFHUB | Hub Buildout | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2026 | Jun 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWQFHUB | Hub Buildout | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2026 | Oct 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWQFHUB | Hub Buildout | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2026 | Jan 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWQFHUB | Hub Buildout | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2027 | Mar 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWQFHUB | Hub Buildout | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2027 | Apr 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | P0950DPR | DPR - 97-77 QUEENS BLVD - CENTRAL FORESTY RELOCATION | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | P0950DPR | DPR - 97-77 QUEENS BLVD - CENTRAL FORESTY RELOCATION | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | P0950DPR | DPR - 97-77 QUEENS BLVD - CENTRAL FORESTY RELOCATION | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | P0950DPR | DPR - 97-77 QUEENS BLVD - CENTRAL FORESTY RELOCATION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | P0950DPR | DPR - 97-77 QUEENS BLVD - CENTRAL FORESTY RELOCATION | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | P0950DPR | DPR - 97-77 QUEENS BLVD - CENTRAL FORESTY RELOCATION | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | P0950DPR | DPR - 97-77 QUEENS BLVD - CENTRAL FORESTY RELOCATION | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | P0950DPR | DPR - 97-77 QUEENS BLVD - CENTRAL FORESTY RELOCATION | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | P0950DPR | DPR - 97-77 QUEENS BLVD - CENTRAL FORESTY RELOCATION | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | P0950DPR | DPR - 97-77 QUEENS BLVD - CENTRAL FORESTY RELOCATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79QDBR | Queens Detective Bureau Relocation | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79QDBR | Queens Detective Bureau Relocation | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79QDBR | Queens Detective Bureau Relocation | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79QDBR | Queens Detective Bureau Relocation | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79QDBR | Queens Detective Bureau Relocation | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79QDBR | Queens Detective Bureau Relocation | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79QDBR | Queens Detective Bureau Relocation | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79QDBR | Queens Detective Bureau Relocation | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79QDBR | Queens Detective Bureau Relocation | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79QDBR | Queens Detective Bureau Relocation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Jun 2024 | Nov 2019 | Jun 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79-QSVD | queens special victimsdivision relocation | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79-QSVD | queens special victimsdivision relocation | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79-QSVD | queens special victimsdivision relocation | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79-QSVD | queens special victimsdivision relocation | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79-QSVD | queens special victimsdivision relocation | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79-QSVD | queens special victimsdivision relocation | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79-QSVD | queens special victimsdivision relocation | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79-QSVD | queens special victimsdivision relocation | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79-QSVD | queens special victimsdivision relocation | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79-QSVD | queens special victimsdivision relocation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Dec 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324QBH | Queens Borough Hall - Wifi Upgrade and Cisco Hardware (Queen | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324QBH | Queens Borough Hall - Wifi Upgrade and Cisco Hardware (Queen | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324QBH | Queens Borough Hall - Wifi Upgrade and Cisco Hardware (Queen | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324QBH | Queens Borough Hall - Wifi Upgrade and Cisco Hardware (Queen | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324QBH | Queens Borough Hall - Wifi Upgrade and Cisco Hardware (Queen | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324QBH | Queens Borough Hall - Wifi Upgrade and Cisco Hardware (Queen | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324QBH | Queens Borough Hall - Wifi Upgrade and Cisco Hardware (Queen | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324QBH | Queens Borough Hall - Wifi Upgrade and Cisco Hardware (Queen | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324QBH | Queens Borough Hall - Wifi Upgrade and Cisco Hardware (Queen | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324QBH | Queens Borough Hall - Wifi Upgrade and Cisco Hardware (Queen | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ3 | DA QUEENS - CYBER CRIME UNIT | 1 | DEVELOP SCOPE | Jun 2019 | Aug 2019 | Jun 2019 | Aug 2019
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ3 | DA QUEENS - CYBER CRIME UNIT | 2 | PRELIMINARY DESIGN | Aug 2019 | Dec 2019 | Aug 2019 | Dec 2019
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ3 | DA QUEENS - CYBER CRIME UNIT | 3 | FINAL DESIGN | Dec 2019 | Jun 2020 | Dec 2019 | Jun 2020
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ3 | DA QUEENS - CYBER CRIME UNIT | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ3 | DA QUEENS - CYBER CRIME UNIT | 5 | CONSTRUCTION TO 25% | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ3 | DA QUEENS - CYBER CRIME UNIT | 6 | CONSTRUCTION TO 50% | Jan 2021 | May 2021 | Jun 2022 | Sep 2022
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ3 | DA QUEENS - CYBER CRIME UNIT | 7 | CONSTRUCTION TO 75% | May 2021 | Sep 2021 | Jun 2024 | Sep 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ3 | DA QUEENS - CYBER CRIME UNIT | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Dec 2021 | Sep 2024 | Dec 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ3 | DA QUEENS - CYBER CRIME UNIT | 9 | SUBSTANTIAL COMPLETION | Dec 2021 | Feb 2022 | Dec 2024 | Feb 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ3 | DA QUEENS - CYBER CRIME UNIT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2022 | Mar 2022 | Feb 2025 | Jun 2028
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOPQ | DOP - 162-24 JAMAICA AVE, QUEENS ADD'L SPACE (MEZZANINE) | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOPQ | DOP - 162-24 JAMAICA AVE, QUEENS ADD'L SPACE (MEZZANINE) | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOPQ | DOP - 162-24 JAMAICA AVE, QUEENS ADD'L SPACE (MEZZANINE) | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOPQ | DOP - 162-24 JAMAICA AVE, QUEENS ADD'L SPACE (MEZZANINE) | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOPQ | DOP - 162-24 JAMAICA AVE, QUEENS ADD'L SPACE (MEZZANINE) | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOPQ | DOP - 162-24 JAMAICA AVE, QUEENS ADD'L SPACE (MEZZANINE) | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOPQ | DOP - 162-24 JAMAICA AVE, QUEENS ADD'L SPACE (MEZZANINE) | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOPQ | DOP - 162-24 JAMAICA AVE, QUEENS ADD'L SPACE (MEZZANINE) | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOPQ | DOP - 162-24 JAMAICA AVE, QUEENS ADD'L SPACE (MEZZANINE) | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOPQ | DOP - 162-24 JAMAICA AVE, QUEENS ADD'L SPACE (MEZZANINE) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DRIV | TLC - 31-00 47th AVE, QNS DRIVERS ASSISTANCE CENTER | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DRIV | TLC - 31-00 47th AVE, QNS DRIVERS ASSISTANCE CENTER | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DRIV | TLC - 31-00 47th AVE, QNS DRIVERS ASSISTANCE CENTER | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DRIV | TLC - 31-00 47th AVE, QNS DRIVERS ASSISTANCE CENTER | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DRIV | TLC - 31-00 47th AVE, QNS DRIVERS ASSISTANCE CENTER | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DRIV | TLC - 31-00 47th AVE, QNS DRIVERS ASSISTANCE CENTER | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DRIV | TLC - 31-00 47th AVE, QNS DRIVERS ASSISTANCE CENTER | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DRIV | TLC - 31-00 47th AVE, QNS DRIVERS ASSISTANCE CENTER | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DRIV | TLC - 31-00 47th AVE, QNS DRIVERS ASSISTANCE CENTER | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DRIV | TLC - 31-00 47th AVE, QNS DRIVERS ASSISTANCE CENTER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326EV | DOHMH - 2 GOTHAM CHARGING STATION INFRASTRUCTURE | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Aug 2020
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326EV | DOHMH - 2 GOTHAM CHARGING STATION INFRASTRUCTURE | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326EV | DOHMH - 2 GOTHAM CHARGING STATION INFRASTRUCTURE | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326EV | DOHMH - 2 GOTHAM CHARGING STATION INFRASTRUCTURE | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326EV | DOHMH - 2 GOTHAM CHARGING STATION INFRASTRUCTURE | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326EV | DOHMH - 2 GOTHAM CHARGING STATION INFRASTRUCTURE | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2022 | May 2022
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326EV | DOHMH - 2 GOTHAM CHARGING STATION INFRASTRUCTURE | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2022 | Sep 2022
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326EV | DOHMH - 2 GOTHAM CHARGING STATION INFRASTRUCTURE | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326EV | DOHMH - 2 GOTHAM CHARGING STATION INFRASTRUCTURE | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2022 | Feb 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326EV | DOHMH - 2 GOTHAM CHARGING STATION INFRASTRUCTURE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Feb 2023 | Aug 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAQ | LAW DEPT - RAISE THE AGE - QUEENS | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Aug 2020
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAQ | LAW DEPT - RAISE THE AGE - QUEENS | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAQ | LAW DEPT - RAISE THE AGE - QUEENS | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAQ | LAW DEPT - RAISE THE AGE - QUEENS | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAQ | LAW DEPT - RAISE THE AGE - QUEENS | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAQ | LAW DEPT - RAISE THE AGE - QUEENS | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2022 | May 2022
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAQ | LAW DEPT - RAISE THE AGE - QUEENS | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2022 | Sep 2022
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAQ | LAW DEPT - RAISE THE AGE - QUEENS | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAQ | LAW DEPT - RAISE THE AGE - QUEENS | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2022 | Feb 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAQ | LAW DEPT - RAISE THE AGE - QUEENS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Feb 2023 | Mar 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ3 | TLC -31-00 47 AVE QUEENS | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2024 | Aug 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ3 | TLC -31-00 47 AVE QUEENS | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2024 | Mar 2025 | Aug 2024 | Dec 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ3 | TLC -31-00 47 AVE QUEENS | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Dec 2024 | Jun 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ3 | TLC -31-00 47 AVE QUEENS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2025 | Jun 2025 | Jun 2025 | Sep 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ3 | TLC -31-00 47 AVE QUEENS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2025 | May 2025 | Sep 2025 | Jan 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ3 | TLC -31-00 47 AVE QUEENS | 6 | CONSTRUCTION TO 50% | Apr 2025 | May 2025 | Jan 2026 | May 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ3 | TLC -31-00 47 AVE QUEENS | 7 | CONSTRUCTION TO 75% | Apr 2025 | May 2025 | May 2026 | Sep 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ3 | TLC -31-00 47 AVE QUEENS | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2025 | May 2025 | Sep 2026 | Dec 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ3 | TLC -31-00 47 AVE QUEENS | 9 | SUBSTANTIAL COMPLETION | Apr 2025 | May 2025 | Dec 2026 | Feb 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ3 | TLC -31-00 47 AVE QUEENS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2025 | May 2025 | Feb 2027 | Mar 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ5 | TLC - Swing Space in Queens | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2018 | Aug 2018
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ5 | TLC - Swing Space in Queens | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2018 | Dec 2018
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ5 | TLC - Swing Space in Queens | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2018 | Jun 2019
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ5 | TLC - Swing Space in Queens | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2019 | Sep 2019
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ5 | TLC - Swing Space in Queens | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2019 | Jan 2020
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ5 | TLC - Swing Space in Queens | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2020 | May 2020
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ5 | TLC - Swing Space in Queens | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2020 | Sep 2020
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ5 | TLC - Swing Space in Queens | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ5 | TLC - Swing Space in Queens | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2022 | Feb 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ5 | TLC - Swing Space in Queens | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Feb 2023 | Mar 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417SW | 120-55 QUEENS BLVD.- SITE WORK | 1 | DEVELOP SCOPE | Jun 2006 | Aug 2006 | Jan 2009 | Apr 2009
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417SW | 120-55 QUEENS BLVD.- SITE WORK | 2 | PRELIMINARY DESIGN | Aug 2006 | Nov 2006 | Apr 2009 | Aug 2009
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417SW | 120-55 QUEENS BLVD.- SITE WORK | 3 | FINAL DESIGN | Nov 2006 | Feb 2007 | Aug 2009 | Feb 2010
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417SW | 120-55 QUEENS BLVD.- SITE WORK | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2007 | May 2007 | Jun 2022 | Aug 2022
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417SW | 120-55 QUEENS BLVD.- SITE WORK | 5 | CONSTRUCTION TO 25% | May 2007 | Jun 2008 | Aug 2022 | Aug 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417SW | 120-55 QUEENS BLVD.- SITE WORK | 6 | CONSTRUCTION TO 50% | Jun 2008 | Aug 2009 | Aug 2024 | Aug 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417SW | 120-55 QUEENS BLVD.- SITE WORK | 7 | CONSTRUCTION TO 75% | Aug 2009 | Sep 2010 | Aug 2026 | Aug 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417SW | 120-55 QUEENS BLVD.- SITE WORK | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2010 | Aug 2011 | Aug 2027 | Sep 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417SW | 120-55 QUEENS BLVD.- SITE WORK | 9 | SUBSTANTIAL COMPLETION | Aug 2011 | Jun 2012 | Sep 2027 | Sep 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417SW | 120-55 QUEENS BLVD.- SITE WORK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2012 | Mar 2013 | Sep 2027 | Oct 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417TU | 120-55 QUEENS BOULEVARD- CODE COMPLIANT TOILET UPGRADES | 1 | DEVELOP SCOPE | Jun 2016 | Aug 2016 | Jun 2022 | Aug 2022
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417TU | 120-55 QUEENS BOULEVARD- CODE COMPLIANT TOILET UPGRADES | 2 | PRELIMINARY DESIGN | Aug 2016 | Dec 2016 | Jun 2022 | Sep 2022
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417TU | 120-55 QUEENS BOULEVARD- CODE COMPLIANT TOILET UPGRADES | 3 | FINAL DESIGN | Dec 2016 | Jun 2017 | Sep 2022 | Mar 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417TU | 120-55 QUEENS BOULEVARD- CODE COMPLIANT TOILET UPGRADES | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2017 | Sep 2017 | Mar 2023 | Jun 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417TU | 120-55 QUEENS BOULEVARD- CODE COMPLIANT TOILET UPGRADES | 5 | CONSTRUCTION TO 25% | Sep 2017 | Jan 2018 | Jun 2024 | Sep 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417TU | 120-55 QUEENS BOULEVARD- CODE COMPLIANT TOILET UPGRADES | 6 | CONSTRUCTION TO 50% | Jan 2018 | May 2018 | Sep 2024 | Jan 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417TU | 120-55 QUEENS BOULEVARD- CODE COMPLIANT TOILET UPGRADES | 7 | CONSTRUCTION TO 75% | May 2018 | Sep 2018 | Jan 2025 | May 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417TU | 120-55 QUEENS BOULEVARD- CODE COMPLIANT TOILET UPGRADES | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2018 | Dec 2018 | Jun 2022 | Sep 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417TU | 120-55 QUEENS BOULEVARD- CODE COMPLIANT TOILET UPGRADES | 9 | SUBSTANTIAL COMPLETION | Dec 2018 | Feb 2019 | Sep 2025 | Nov 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417TU | 120-55 QUEENS BOULEVARD- CODE COMPLIANT TOILET UPGRADES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2019 | Mar 2019 | Nov 2025 | Dec 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77QHVAC | 120-55 Queens BLVD - Queens Borough Hall - HVAC Upgrade | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77QHVAC | 120-55 Queens BLVD - Queens Borough Hall - HVAC Upgrade | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77QHVAC | 120-55 Queens BLVD - Queens Borough Hall - HVAC Upgrade | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77QHVAC | 120-55 Queens BLVD - Queens Borough Hall - HVAC Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77QHVAC | 120-55 Queens BLVD - Queens Borough Hall - HVAC Upgrade | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77QHVAC | 120-55 Queens BLVD - Queens Borough Hall - HVAC Upgrade | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77QHVAC | 120-55 Queens BLVD - Queens Borough Hall - HVAC Upgrade | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77QHVAC | 120-55 Queens BLVD - Queens Borough Hall - HVAC Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77QHVAC | 120-55 Queens BLVD - Queens Borough Hall - HVAC Upgrade | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77QHVAC | 120-55 Queens BLVD - Queens Borough Hall - HVAC Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78415A | 88-11 SUTPHIN BLVD.- FACADE RESTORATION | 1 | DEVELOP SCOPE | Jun 2011 | Aug 2011 | Jun 2026 | Aug 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78415A | 88-11 SUTPHIN BLVD.- FACADE RESTORATION | 2 | PRELIMINARY DESIGN | Aug 2011 | Dec 2011 | Aug 2026 | Dec 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78415A | 88-11 SUTPHIN BLVD.- FACADE RESTORATION | 3 | FINAL DESIGN | Dec 2011 | Jun 2012 | Dec 2026 | Jun 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78415A | 88-11 SUTPHIN BLVD.- FACADE RESTORATION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2012 | Sep 2012 | Jun 2027 | Sep 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78415A | 88-11 SUTPHIN BLVD.- FACADE RESTORATION | 5 | CONSTRUCTION TO 25% | Sep 2012 | Jan 2013 | Sep 2027 | Jan 2028
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78415A | 88-11 SUTPHIN BLVD.- FACADE RESTORATION | 6 | CONSTRUCTION TO 50% | Jan 2013 | May 2013 | Jan 2028 | May 2028
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78415A | 88-11 SUTPHIN BLVD.- FACADE RESTORATION | 7 | CONSTRUCTION TO 75% | May 2013 | Sep 2013 | May 2028 | Sep 2028
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78415A | 88-11 SUTPHIN BLVD.- FACADE RESTORATION | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2013 | Dec 2013 | Sep 2028 | Dec 2028
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78415A | 88-11 SUTPHIN BLVD.- FACADE RESTORATION | 9 | SUBSTANTIAL COMPLETION | Dec 2013 | Feb 2014 | Dec 2028 | Feb 2029
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78415A | 88-11 SUTPHIN BLVD.- FACADE RESTORATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2014 | Mar 2014 | Feb 2029 | Mar 2029
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW-Q077 | 120-55 QUEENS BLVD- DISCOVER QUEENS VISITORS CENTER | 1 | DEVELOP SCOPE | May 2007 | Jul 2007 | May 2007 | Jul 2007
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW-Q077 | 120-55 QUEENS BLVD- DISCOVER QUEENS VISITORS CENTER | 2 | PRELIMINARY DESIGN | Jul 2007 | Nov 2007 | Jul 2007 | Nov 2007
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW-Q077 | 120-55 QUEENS BLVD- DISCOVER QUEENS VISITORS CENTER | 3 | FINAL DESIGN | Nov 2007 | May 2008 | Nov 2007 | May 2008
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW-Q077 | 120-55 QUEENS BLVD- DISCOVER QUEENS VISITORS CENTER | 4 | BID AWARD AND REGISTER CONTRCT | May 2008 | Aug 2008 | May 2008 | Aug 2008
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW-Q077 | 120-55 QUEENS BLVD- DISCOVER QUEENS VISITORS CENTER | 5 | CONSTRUCTION TO 25% | Aug 2008 | Aug 2009 | Aug 2008 | Aug 2009
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW-Q077 | 120-55 QUEENS BLVD- DISCOVER QUEENS VISITORS CENTER | 6 | CONSTRUCTION TO 50% | Aug 2009 | Aug 2010 | Aug 2009 | Aug 2010
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW-Q077 | 120-55 QUEENS BLVD- DISCOVER QUEENS VISITORS CENTER | 7 | CONSTRUCTION TO 75% | Aug 2010 | Aug 2011 | Aug 2010 | Aug 2011
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW-Q077 | 120-55 QUEENS BLVD- DISCOVER QUEENS VISITORS CENTER | 8 | ORIGINAL EQUIP & FURNISHING | Aug 2011 | Aug 2012 | Aug 2011 | Aug 2012
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW-Q077 | 120-55 QUEENS BLVD- DISCOVER QUEENS VISITORS CENTER | 9 | SUBSTANTIAL COMPLETION | Aug 2012 | Jul 2013 | Aug 2012 | Jul 2013
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW-Q077 | 120-55 QUEENS BLVD- DISCOVER QUEENS VISITORS CENTER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2013 | Dec 2013 | Jul 2013 | Dec 2013
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77QBH2 | 120-55 QUEENS BLVD.- RENOVATIONS | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2025 | Aug 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77QBH2 | 120-55 QUEENS BLVD.- RENOVATIONS | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2025 | Dec 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77QBH2 | 120-55 QUEENS BLVD.- RENOVATIONS | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2025 | Jun 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77QBH2 | 120-55 QUEENS BLVD.- RENOVATIONS | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2026 | Sep 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77QBH2 | 120-55 QUEENS BLVD.- RENOVATIONS | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2026 | Jan 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77QBH2 | 120-55 QUEENS BLVD.- RENOVATIONS | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2027 | May 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77QBH2 | 120-55 QUEENS BLVD.- RENOVATIONS | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2027 | Sep 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77QBH2 | 120-55 QUEENS BLVD.- RENOVATIONS | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2027 | Dec 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77QBH2 | 120-55 QUEENS BLVD.- RENOVATIONS | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2027 | Feb 2028
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77QBH2 | 120-55 QUEENS BLVD.- RENOVATIONS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Feb 2028 | Mar 2032
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77R213 | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS | 1 | DEVELOP SCOPE | Sep 2014 | Nov 2014 | Jun 2024 | Aug 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77R213 | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS | 2 | PRELIMINARY DESIGN | Nov 2014 | Mar 2015 | Aug 2024 | Dec 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77R213 | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS | 3 | FINAL DESIGN | Mar 2015 | Sep 2015 | Dec 2024 | Jun 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77R213 | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2015 | Dec 2015 | Jun 2025 | Sep 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77R213 | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS | 5 | CONSTRUCTION TO 25% | Dec 2015 | Apr 2016 | Sep 2025 | Jan 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77R213 | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS | 6 | CONSTRUCTION TO 50% | Apr 2016 | Aug 2016 | Jan 2026 | May 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77R213 | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS | 7 | CONSTRUCTION TO 75% | Aug 2016 | Dec 2016 | May 2026 | Sep 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77R213 | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2016 | Mar 2017 | Sep 2026 | Dec 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77R213 | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS | 9 | SUBSTANTIAL COMPLETION | Mar 2017 | May 2017 | Dec 2026 | Feb 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77R213 | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2017 | Jun 2017 | Feb 2027 | Apr 2032
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77TOPO | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS-TOPOGRAPHY | 1 | DEVELOP SCOPE | Oct 2009 | Dec 2009 | Oct 2009 | Dec 2009
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77TOPO | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS-TOPOGRAPHY | 2 | PRELIMINARY DESIGN | Dec 2009 | Apr 2010 | Dec 2009 | Apr 2010
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77TOPO | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS-TOPOGRAPHY | 3 | FINAL DESIGN | Apr 2010 | Oct 2010 | Apr 2010 | Oct 2010
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77TOPO | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS-TOPOGRAPHY | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2010 | Jan 2011 | Oct 2010 | Jan 2011
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77TOPO | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS-TOPOGRAPHY | 5 | CONSTRUCTION TO 25% | Jan 2011 | May 2011 | Jan 2011 | May 2011
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77TOPO | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS-TOPOGRAPHY | 6 | CONSTRUCTION TO 50% | May 2011 | Sep 2011 | May 2011 | Sep 2011
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77TOPO | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS-TOPOGRAPHY | 7 | CONSTRUCTION TO 75% | Sep 2011 | Jan 2012 | Sep 2011 | Jan 2012
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77TOPO | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS-TOPOGRAPHY | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2012 | Apr 2012 | Jun 2028 | Aug 2028
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77TOPO | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS-TOPOGRAPHY | 9 | SUBSTANTIAL COMPLETION | Apr 2012 | Jun 2012 | Aug 2028 | Oct 2028
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77TOPO | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS-TOPOGRAPHY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2012 | Jul 2012 | Oct 2028 | Nov 2031
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25-162 | 99-01 162nd AVE BULKHEAD REHABILITATION | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2023 | Jun 2023 | Jun 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25-162 | 99-01 162nd AVE BULKHEAD REHABILITATION | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25-162 | 99-01 162nd AVE BULKHEAD REHABILITATION | 3 | CONSTRUCTION TO 50% | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25-162 | 99-01 162nd AVE BULKHEAD REHABILITATION | 4 | CONSTRUCTION TO 75% | Feb 2024 | May 2024 | Feb 2024 | May 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25-162 | 99-01 162nd AVE BULKHEAD REHABILITATION | 5 | SUBSTANTIAL COMPLETION | May 2024 | Jul 2024 | May 2024 | Jul 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25-162 | 99-01 162nd AVE BULKHEAD REHABILITATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25VERN | PLATFORM / BULKHEAD REPLACEMENT | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2027 | Aug 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25VERN | PLATFORM / BULKHEAD REPLACEMENT | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2027 | Dec 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25VERN | PLATFORM / BULKHEAD REPLACEMENT | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2027 | Jun 2028
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25VERN | PLATFORM / BULKHEAD REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2028 | Sep 2028
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25VERN | PLATFORM / BULKHEAD REPLACEMENT | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2028 | Jan 2029
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25VERN | PLATFORM / BULKHEAD REPLACEMENT | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2029 | May 2029
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25VERN | PLATFORM / BULKHEAD REPLACEMENT | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2029 | Sep 2029
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25VERN | PLATFORM / BULKHEAD REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2029 | Dec 2029
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25VERN | PLATFORM / BULKHEAD REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2029 | Feb 2030
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25VERN | PLATFORM / BULKHEAD REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2030 | Mar 2030
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP10 | SCA - SCA HEATING ELECTRIFICATION PROGRAM 252-12 72ND AVE | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP10 | SCA - SCA HEATING ELECTRIFICATION PROGRAM 252-12 72ND AVE | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP10 | SCA - SCA HEATING ELECTRIFICATION PROGRAM 252-12 72ND AVE | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP10 | SCA - SCA HEATING ELECTRIFICATION PROGRAM 252-12 72ND AVE | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP10 | SCA - SCA HEATING ELECTRIFICATION PROGRAM 252-12 72ND AVE | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP10 | SCA - SCA HEATING ELECTRIFICATION PROGRAM 252-12 72ND AVE | 6 | CONSTRUCTION TO 50% | Jun 2026 | Sep 2026 | Jun 2026 | Sep 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP10 | SCA - SCA HEATING ELECTRIFICATION PROGRAM 252-12 72ND AVE | 7 | CONSTRUCTION TO 75% | Sep 2026 | Jan 2027 | Sep 2026 | Jan 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP10 | SCA - SCA HEATING ELECTRIFICATION PROGRAM 252-12 72ND AVE | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2027 | Apr 2027 | Jan 2027 | Apr 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP10 | SCA - SCA HEATING ELECTRIFICATION PROGRAM 252-12 72ND AVE | 9 | SUBSTANTIAL COMPLETION | Apr 2027 | Jun 2027 | Apr 2027 | Jun 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP10 | SCA - SCA HEATING ELECTRIFICATION PROGRAM 252-12 72ND AVE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2027 | Jul 2027 | Jun 2027 | Jul 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-Q169 | SCA Electrification - Q169 | 1 | DEVELOP SCOPE | Jun 2028 | Jun 2028 | Jun 2028 | Jun 2028
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-Q169 | SCA Electrification - Q169 | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2028 | Aug 2028 | Jul 2028 | Aug 2028
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-Q169 | SCA Electrification - Q169 | 3 | CONSTRUCTION TO 50% | Aug 2028 | Feb 2029 | Aug 2028 | Feb 2029
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-Q169 | SCA Electrification - Q169 | 4 | CONSTRUCTION TO 75% | Feb 2029 | May 2029 | Feb 2029 | May 2029
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-Q169 | SCA Electrification - Q169 | 5 | SUBSTANTIAL COMPLETION | May 2029 | Jul 2029 | May 2029 | Jul 2029
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-Q169 | SCA Electrification - Q169 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2029 | Aug 2029 | Jul 2029 | Aug 2029
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-Q186 | SCA Electrification - Q186 | 1 | DEVELOP SCOPE | Jun 2027 | Jun 2027 | Jun 2027 | Jun 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-Q186 | SCA Electrification - Q186 | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2027 | Aug 2027 | Jul 2027 | Aug 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-Q186 | SCA Electrification - Q186 | 3 | CONSTRUCTION TO 50% | Aug 2027 | Feb 2028 | Aug 2027 | Feb 2028
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-Q186 | SCA Electrification - Q186 | 4 | CONSTRUCTION TO 75% | Feb 2028 | May 2028 | Feb 2028 | May 2028
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-Q186 | SCA Electrification - Q186 | 5 | SUBSTANTIAL COMPLETION | May 2028 | Jul 2028 | May 2028 | Jul 2028
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-Q186 | SCA Electrification - Q186 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2028 | Aug 2028 | Jul 2028 | Aug 2028
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-Q510 | SCA Electrification - Q510 | 1 | DEVELOP SCOPE | Jun 2027 | Jun 2027 | Jun 2027 | Jun 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-Q510 | SCA Electrification - Q510 | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2027 | Aug 2027 | Jul 2027 | Aug 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-Q510 | SCA Electrification - Q510 | 3 | CONSTRUCTION TO 50% | Aug 2027 | Feb 2028 | Aug 2027 | Feb 2028
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-Q510 | SCA Electrification - Q510 | 4 | CONSTRUCTION TO 75% | Feb 2028 | May 2028 | Feb 2028 | May 2028
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-Q510 | SCA Electrification - Q510 | 5 | SUBSTANTIAL COMPLETION | May 2028 | Jul 2028 | May 2028 | Jul 2028
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-Q510 | SCA Electrification - Q510 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2028 | Aug 2028 | Jul 2028 | Aug 2028
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARPQL1 | DCAS PQL Round 1 (EME) DCAS PQL Round 1 (EME) | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2020 | Mar 2023 | Apr 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARPQL1 | DCAS PQL Round 1 (EME) DCAS PQL Round 1 (EME) | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Aug 2020 | Apr 2023 | Jun 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARPQL1 | DCAS PQL Round 1 (EME) DCAS PQL Round 1 (EME) | 3 | CONSTRUCTION TO 50% | Aug 2020 | Feb 2021 | Jun 2023 | Dec 2023
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARPQL1 | DCAS PQL Round 1 (EME) DCAS PQL Round 1 (EME) | 4 | CONSTRUCTION TO 75% | Feb 2021 | May 2021 | Dec 2023 | Mar 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARPQL1 | DCAS PQL Round 1 (EME) DCAS PQL Round 1 (EME) | 5 | SUBSTANTIAL COMPLETION | May 2021 | Jul 2021 | Mar 2024 | May 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARPQL1 | DCAS PQL Round 1 (EME) DCAS PQL Round 1 (EME) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Aug 2021 | May 2024 | Jun 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | UNIONHALL | ACS - WORKFORCE INSTITUTE UNION HALL | 1 | DESIGN | May 2018 | Aug 2018 | May 2026 | Jul 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | UNIONHALL | ACS - WORKFORCE INSTITUTE UNION HALL | 2 | CONSTRUCTION | Aug 2018 | Aug 2021 | Jul 2026 | Nov 2026
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | UNIONHALL | ACS - WORKFORCE INSTITUTE UNION HALL | 3 | FINAL DESIGN | Aug 2018 | Aug 2021 | Nov 2026 | May 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | UNIONHALL | ACS - WORKFORCE INSTITUTE UNION HALL | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2018 | Aug 2021 | May 2027 | Aug 2027
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | UNIONHALL | ACS - WORKFORCE INSTITUTE UNION HALL | 5 | CONSTRUCTION TO 25% | Aug 2018 | Aug 2021 | Jun 2022 | Sep 2022
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | UNIONHALL | ACS - WORKFORCE INSTITUTE UNION HALL | 6 | CONSTRUCTION TO 50% | Aug 2018 | Aug 2021 | Jun 2024 | Sep 2024
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | UNIONHALL | ACS - WORKFORCE INSTITUTE UNION HALL | 7 | CONSTRUCTION TO 75% | Aug 2018 | Aug 2021 | Sep 2024 | Jan 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | UNIONHALL | ACS - WORKFORCE INSTITUTE UNION HALL | 8 | ORIGINAL EQUIP & FURNISHING | Aug 2018 | Aug 2021 | Jan 2025 | Apr 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | UNIONHALL | ACS - WORKFORCE INSTITUTE UNION HALL | 9 | SUBSTANTIAL COMPLETION | Aug 2018 | Aug 2021 | Apr 2025 | Jun 2025
20231026 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | UNIONHALL | ACS - WORKFORCE INSTITUTE UNION HALL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2018 | Aug 2021 | Jun 2025 | Jul 2029
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNCA17THL | TODT HILL - New Lighting | 1 | DEVELOP SCOPE | Jul 2021 | Sep 2021 | Jun 2026 | Sep 2026
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNCA17THL | TODT HILL - New Lighting | 2 | DESIGN | Sep 2021 | Sep 2022 | Sep 2026 | Sep 2027
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNCA17THL | TODT HILL - New Lighting | 3 | BID/ REGISTER CONTRACT | Sep 2022 | Jun 2023 | Sep 2027 | Jun 2028
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNCA17THL | TODT HILL - New Lighting | 4 | CONSTRUCTION | Jun 2023 | Jun 2024 | Jun 2028 | Jun 2029
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNCA17THL | TODT HILL - New Lighting | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2024 | Jun 2025 | Jun 2029 | Jun 2030
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNCM15STB | South Beach - New Roof | 1 | DEVELOP SCOPE | Jul 2021 | Sep 2021 | Jun 2026 | Sep 2026
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNCM15STB | South Beach - New Roof | 2 | DESIGN | Sep 2021 | Sep 2022 | Sep 2026 | Sep 2027
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNCM15STB | South Beach - New Roof | 3 | BID/ REGISTER CONTRACT | Sep 2022 | Jun 2023 | Sep 2027 | Jun 2028
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNCM15STB | South Beach - New Roof | 4 | CONSTRUCTION | Jun 2023 | Jun 2024 | Jun 2028 | Jun 2029
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNCM15STB | South Beach - New Roof | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2024 | Jun 2025 | Jun 2029 | Jun 2030
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNEM17RTW | RICHMONDTOWN - HVAC System Replacement | 1 | DEVELOP SCOPE | Jan 2021 | Mar 2021 | Dec 2030 | Feb 2031
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNEM17RTW | RICHMONDTOWN - HVAC System Replacement | 2 | DESIGN | Apr 2021 | Mar 2022 | Mar 2031 | Feb 2032
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNEM17RTW | RICHMONDTOWN - HVAC System Replacement | 3 | BID/ REGISTER CONTRACT | Apr 2022 | Dec 2022 | Feb 2032 | Nov 2032
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNEM17RTW | RICHMONDTOWN - HVAC System Replacement | 4 | CONSTRUCTION | Dec 2022 | Dec 2023 | Nov 2032 | Nov 2033
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNEM17RTW | RICHMONDTOWN - HVAC System Replacement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Dec 2024 | Nov 2033 | Nov 2034
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17WNB | WEST NEW BRIGHTON - ADA-compliant Elevators | 1 | DEVELOP SCOPE | Dec 2017 | Feb 2018 | Jun 2027 | Sep 2027
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17WNB | WEST NEW BRIGHTON - ADA-compliant Elevators | 2 | PRELIMINARY DESIGN | Mar 2018 | Jun 2018 | Sep 2027 | Jan 2028
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17WNB | WEST NEW BRIGHTON - ADA-compliant Elevators | 3 | FINAL DESIGN | Jun 2018 | Dec 2018 | Jan 2028 | Jul 2028
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17WNB | WEST NEW BRIGHTON - ADA-compliant Elevators | 4 | BID AWARD AND REGISTER CONTRCT | Dec 2018 | Mar 2019 | Jul 2028 | Oct 2028
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17WNB | WEST NEW BRIGHTON - ADA-compliant Elevators | 5 | CONSTRUCTION TO 25% | Mar 2019 | Jul 2019 | Oct 2028 | Feb 2029
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17WNB | WEST NEW BRIGHTON - ADA-compliant Elevators | 6 | CONSTRUCTION TO 50% | Jul 2019 | Nov 2019 | Feb 2029 | Jun 2029
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17WNB | WEST NEW BRIGHTON - ADA-compliant Elevators | 7 | CONSTRUCTION TO 75% | Nov 2019 | Mar 2020 | Jun 2029 | Oct 2029
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17WNB | WEST NEW BRIGHTON - ADA-compliant Elevators | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2020 | Jun 2020 | Oct 2029 | Jan 2030
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17WNB | WEST NEW BRIGHTON - ADA-compliant Elevators | 9 | SUBSTANTIAL COMPLETION | Jun 2020 | Aug 2020 | Jan 2030 | Mar 2030
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17WNB | WEST NEW BRIGHTON - ADA-compliant Elevators | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2020 | Sep 2020 | Mar 2030 | Apr 2030
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA18GCK | Great Kills - ADA-compliant Restrooms | 1 | DEVELOP SCOPE | Jul 2019 | Sep 2019 | Jun 2025 | Sep 2025
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA18GCK | Great Kills - ADA-compliant Restrooms | 2 | DESIGN | Sep 2019 | Sep 2020 | Sep 2025 | Sep 2026
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA18GCK | Great Kills - ADA-compliant Restrooms | 3 | BID/ REGISTER CONTRACT | Sep 2020 | Jun 2021 | Sep 2026 | Jun 2027
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA18GCK | Great Kills - ADA-compliant Restrooms | 4 | CONSTRUCTION | Jun 2021 | Jun 2022 | Jun 2027 | Jun 2028
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA18GCK | Great Kills - ADA-compliant Restrooms | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Jun 2023 | Jun 2028 | Jun 2029
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA18RCH | Richmondtown - New Boiler | 1 | DEVELOP SCOPE | Dec 2019 | Feb 2020 | Jun 2025 | Sep 2025
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA18RCH | Richmondtown - New Boiler | 2 | DESIGN | Feb 2020 | Feb 2021 | Sep 2025 | Sep 2026
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA18RCH | Richmondtown - New Boiler | 3 | BID/ REGISTER CONTRACT | Feb 2021 | Nov 2021 | Sep 2026 | Jun 2027
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA18RCH | Richmondtown - New Boiler | 4 | CONSTRUCTION | Nov 2021 | Nov 2022 | Jun 2027 | Jun 2028
20231026 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA18RCH | Richmondtown - New Boiler | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2022 | Nov 2023 | Jun 2028 | Jun 2029
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST001-021 | Science Lecture Room | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST001-021 | Science Lecture Room | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST001-021 | Science Lecture Room | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST001-021 | Science Lecture Room | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST001-021 | Science Lecture Room | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST001-021 | Science Lecture Room | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST001-021 | Science Lecture Room | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST001-021 | Science Lecture Room | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST001-021 | Science Lecture Room | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST001-021 | Science Lecture Room | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2027
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST002-024 | Athlectic Lighting and Locker Room Improvements | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2025 | Jun 2024 | Sep 2025
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST002-024 | Athlectic Lighting and Locker Room Improvements | 2 | PRELIMINARY DESIGN | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST002-024 | Athlectic Lighting and Locker Room Improvements | 3 | FINAL DESIGN | Jan 2026 | Jul 2026 | Jan 2026 | Jul 2026
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST002-024 | Athlectic Lighting and Locker Room Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2026 | Oct 2026 | Jul 2026 | Oct 2026
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST002-024 | Athlectic Lighting and Locker Room Improvements | 5 | CONSTRUCTION TO 25% | Oct 2026 | Feb 2027 | Oct 2026 | Feb 2027
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST002-024 | Athlectic Lighting and Locker Room Improvements | 6 | CONSTRUCTION TO 50% | Feb 2027 | Jun 2027 | Feb 2027 | Jun 2027
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST002-024 | Athlectic Lighting and Locker Room Improvements | 7 | CONSTRUCTION TO 75% | Jun 2027 | Oct 2027 | Jun 2027 | Oct 2027
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST002-024 | Athlectic Lighting and Locker Room Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jan 2028 | Oct 2027 | Jan 2028
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST002-024 | Athlectic Lighting and Locker Room Improvements | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Mar 2028 | Jan 2028 | Mar 2028
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST002-024 | Athlectic Lighting and Locker Room Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2028 | Apr 2028 | Mar 2028 | Apr 2028
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST039-019 | Maker Space Lab | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jul 2021 | Sep 2021
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST039-019 | Maker Space Lab | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Sep 2021 | Jan 2022
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST039-019 | Maker Space Lab | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2022 | Jul 2022
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST039-019 | Maker Space Lab | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2022 | Oct 2022
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST039-019 | Maker Space Lab | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2022 | Feb 2023
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST039-019 | Maker Space Lab | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2023 | Jun 2023
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST039-019 | Maker Space Lab | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2023 | Oct 2023
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST039-019 | Maker Space Lab | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2023 | Jan 2024
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST039-019 | Maker Space Lab | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2024 | Mar 2024
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST039-019 | Maker Space Lab | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2024 | Apr 2026
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST041-020 | Room Conversion for the Genomic Research Center | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST041-020 | Room Conversion for the Genomic Research Center | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST041-020 | Room Conversion for the Genomic Research Center | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2021
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST041-020 | Room Conversion for the Genomic Research Center | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST041-020 | Room Conversion for the Genomic Research Center | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST041-020 | Room Conversion for the Genomic Research Center | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST041-020 | Room Conversion for the Genomic Research Center | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2022
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST041-020 | Room Conversion for the Genomic Research Center | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST041-020 | Room Conversion for the Genomic Research Center | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2023 | Mar 2023
20231026 | RICHMOND | 042 | CITY UNIVERSITY | ST041-020 | Room Conversion for the Genomic Research Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2023 | Apr 2026
20231026 | RICHMOND | 056 | POLICE DEPARTMENT | PO79120AC | 120TH PCT - NEW HVAC SYSTEM | 1 | DEVELOP SCOPE | Sep 2012 | Dec 2012 | Jun 2016 | Sep 2016
20231026 | RICHMOND | 056 | POLICE DEPARTMENT | PO79120AC | 120TH PCT - NEW HVAC SYSTEM | 2 | PRELIMINARY DESIGN | Dec 2012 | Apr 2013 | Sep 2016 | Jan 2017
20231026 | RICHMOND | 056 | POLICE DEPARTMENT | PO79120AC | 120TH PCT - NEW HVAC SYSTEM | 3 | FINAL DESIGN | Apr 2013 | Aug 2013 | Jan 2017 | May 2017
20231026 | RICHMOND | 056 | POLICE DEPARTMENT | PO79120AC | 120TH PCT - NEW HVAC SYSTEM | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2013 | Feb 2014 | May 2017 | Nov 2017
20231026 | RICHMOND | 056 | POLICE DEPARTMENT | PO79120AC | 120TH PCT - NEW HVAC SYSTEM | 5 | CONSTRUCTION TO 25% | Feb 2014 | Jun 2014 | Nov 2017 | Mar 2018
20231026 | RICHMOND | 056 | POLICE DEPARTMENT | PO79120AC | 120TH PCT - NEW HVAC SYSTEM | 6 | CONSTRUCTION TO 50% | Jun 2014 | Oct 2014 | Mar 2018 | Jul 2018
20231026 | RICHMOND | 056 | POLICE DEPARTMENT | PO79120AC | 120TH PCT - NEW HVAC SYSTEM | 7 | CONSTRUCTION TO 75% | Oct 2014 | Feb 2015 | Jul 2018 | Nov 2021
20231026 | RICHMOND | 056 | POLICE DEPARTMENT | PO79120AC | 120TH PCT - NEW HVAC SYSTEM | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2015 | May 2015 | Nov 2021 | Feb 2022
20231026 | RICHMOND | 056 | POLICE DEPARTMENT | PO79120AC | 120TH PCT - NEW HVAC SYSTEM | 9 | SUBSTANTIAL COMPLETION | May 2015 | Jul 2015 | Feb 2022 | Apr 2022
20231026 | RICHMOND | 056 | POLICE DEPARTMENT | PO79120AC | 120TH PCT - NEW HVAC SYSTEM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2015 | Aug 2015 | Apr 2022 | Apr 2027
20231026 | RICHMOND | 057 | FIRE DEPARTMENT | F175MC152 | Multi-Component Renovations - EC152 | 1 | DESIGN | Mar 2019 | Sep 2019 | Mar 2019 | Aug 2019
20231026 | RICHMOND | 057 | FIRE DEPARTMENT | F175MC152 | Multi-Component Renovations - EC152 | 2 | CONSTRUCTION | Sep 2019 | Aug 2020 | Aug 2019 | Aug 2020
20231026 | RICHMOND | 057 | FIRE DEPARTMENT | F175MC152 | Multi-Component Renovations - EC152 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Nov 2020 | Aug 2020 | May 2026
20231026 | RICHMOND | 057 | FIRE DEPARTMENT | F175MC159 | Multi-Component Renovations - EC159 | 1 | DESIGN | Jan 2019 | Apr 2019 | Jan 2019 | Apr 2019
20231026 | RICHMOND | 057 | FIRE DEPARTMENT | F175MC159 | Multi-Component Renovations - EC159 | 2 | BID AWARD AND REGISTER CONTRCT | Apr 2019 | Jan 2020 | Apr 2019 | Jan 2020
20231026 | RICHMOND | 057 | FIRE DEPARTMENT | F175MC159 | Multi-Component Renovations - EC159 | 3 | CONSTRUCTION | Jan 2020 | Feb 2021 | Jan 2020 | Feb 2021
20231026 | RICHMOND | 057 | FIRE DEPARTMENT | F175MC159 | Multi-Component Renovations - EC159 | 4 | ORIGINAL EQUIP & FURNISHING | Feb 2021 | Mar 2021 | Feb 2021 | Mar 2021
20231026 | RICHMOND | 057 | FIRE DEPARTMENT | F175MC159 | Multi-Component Renovations - EC159 | 5 | SUBSTANTIAL COMPLETION | Mar 2021 | May 2021 | Mar 2021 | May 2021
20231026 | RICHMOND | 057 | FIRE DEPARTMENT | F175MC159 | Multi-Component Renovations - EC159 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2021 | Jul 2021 | May 2021 | Dec 2024
20231026 | RICHMOND | 057 | FIRE DEPARTMENT | F175SEWER | New Sewer Main and Pumping Station - Outside Plant Garage | 1 | DESIGN | Nov 2018 | May 2019 | Nov 2018 | May 2019
20231026 | RICHMOND | 057 | FIRE DEPARTMENT | F175SEWER | New Sewer Main and Pumping Station - Outside Plant Garage | 2 | CONSTRUCTION | May 2019 | May 2020 | May 2019 | May 2020
20231026 | RICHMOND | 057 | FIRE DEPARTMENT | F175SEWER | New Sewer Main and Pumping Station - Outside Plant Garage | 3 | PUNCHLIST COMPLETE, JOB CLOSED | May 2020 | Aug 2020 | May 2020 | Jun 2024
20231026 | RICHMOND | 057 | FIRE DEPARTMENT | FD175D152 | OVERHEAD DOOR - EC 152 | 1 | CONSTRUCTION | Nov 2023 | Nov 2024 | Nov 2023 | Nov 2024
20231026 | RICHMOND | 057 | FIRE DEPARTMENT | FD175D152 | OVERHEAD DOOR - EC 152 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2024 | Feb 2025 | Nov 2024 | Feb 2025
20231026 | RICHMOND | 057 | FIRE DEPARTMENT | FD175D156 | OVERHEAD DOOR - EC 156 | 1 | CONSTRUCTION | Nov 2023 | Nov 2024 | Nov 2023 | Nov 2024
20231026 | RICHMOND | 057 | FIRE DEPARTMENT | FD175D156 | OVERHEAD DOOR - EC 156 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2024 | Feb 2025 | Nov 2024 | Feb 2025
20231026 | RICHMOND | 057 | FIRE DEPARTMENT | FD175G155 | GENERATOR - EC155/LADDER 78 | 1 | DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | RICHMOND | 057 | FIRE DEPARTMENT | FD175G155 | GENERATOR - EC155/LADDER 78 | 2 | CONSTRUCTION | Jun 2024 | Jun 2025 | Jun 2024 | Jun 2025
20231026 | RICHMOND | 057 | FIRE DEPARTMENT | FD175G155 | GENERATOR - EC155/LADDER 78 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | RICHMOND | 057 | FIRE DEPARTMENT | FD175G161 | Generator - EC161 | 1 | DESIGN | Jan 2019 | Jul 2019 | Jan 2020 | Jul 2020
20231026 | RICHMOND | 057 | FIRE DEPARTMENT | FD175G161 | Generator - EC161 | 2 | CONSTRUCTION | Jul 2019 | Jul 2020 | Jul 2020 | Jul 2021
20231026 | RICHMOND | 057 | FIRE DEPARTMENT | FD175G161 | Generator - EC161 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Oct 2020 | Jul 2021 | Jun 2024
20231026 | RICHMOND | 057 | FIRE DEPARTMENT | FD175G165 | Generator - EC165 | 1 | DESIGN | Jan 2019 | Jul 2019 | Jan 2020 | Jul 2020
20231026 | RICHMOND | 057 | FIRE DEPARTMENT | FD175G165 | Generator - EC165 | 2 | CONSTRUCTION | Jul 2019 | Jul 2020 | Jul 2020 | Jul 2021
20231026 | RICHMOND | 057 | FIRE DEPARTMENT | FD175G165 | Generator - EC165 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Oct 2020 | Jul 2021 | Jun 2024
20231026 | RICHMOND | 057 | FIRE DEPARTMENT | FR175G166 | Generator - EC166 | 1 | DESIGN | Jun 2019 | Dec 2019 | Jun 2020 | Dec 2020
20231026 | RICHMOND | 057 | FIRE DEPARTMENT | FR175G166 | Generator - EC166 | 2 | CONSTRUCTION | Dec 2019 | Dec 2020 | Dec 2020 | Dec 2021
20231026 | RICHMOND | 057 | FIRE DEPARTMENT | FR175G166 | Generator - EC166 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2020 | Mar 2021 | Dec 2021 | Jun 2024
20231026 | RICHMOND | 071 | DEPT OF HOMELESS SERVICES | HH115HOBU | HOSPITALITY HOUSE BUILDING UPGRADE | 1 | DESIGN | Jan 2022 | Sep 2022 | Jan 2022 | Sep 2022
20231026 | RICHMOND | 071 | DEPT OF HOMELESS SERVICES | HH115HOBU | HOSPITALITY HOUSE BUILDING UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2022 | Mar 2023 | Sep 2022 | Mar 2023
20231026 | RICHMOND | 071 | DEPT OF HOMELESS SERVICES | HH115HOBU | HOSPITALITY HOUSE BUILDING UPGRADE | 3 | CONSTRUCTION | Mar 2023 | Dec 2027 | Mar 2023 | Dec 2027
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV175HVAC | SIZ - HVAC Building Systems Upgrades | 1 | DEVELOP SCOPE | Jun 2027 | Sep 2027 | Jun 2027 | Sep 2027
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV175HVAC | SIZ - HVAC Building Systems Upgrades | 2 | PRELIMINARY DESIGN | Sep 2027 | Jan 2028 | Sep 2027 | Jan 2028
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV175HVAC | SIZ - HVAC Building Systems Upgrades | 3 | FINAL DESIGN | Jan 2028 | Jul 2028 | Jan 2028 | Jul 2028
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV175HVAC | SIZ - HVAC Building Systems Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2028 | Oct 2028 | Jul 2028 | Oct 2028
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV175HVAC | SIZ - HVAC Building Systems Upgrades | 5 | CONSTRUCTION TO 25% | Oct 2028 | Feb 2029 | Oct 2028 | Feb 2029
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV175HVAC | SIZ - HVAC Building Systems Upgrades | 6 | CONSTRUCTION TO 50% | Feb 2029 | Jun 2029 | Feb 2029 | Jun 2029
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV175HVAC | SIZ - HVAC Building Systems Upgrades | 7 | CONSTRUCTION TO 75% | Jun 2029 | Oct 2029 | Jun 2029 | Oct 2029
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV175HVAC | SIZ - HVAC Building Systems Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2029 | Jan 2030 | Oct 2029 | Jan 2030
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV175HVAC | SIZ - HVAC Building Systems Upgrades | 9 | SUBSTANTIAL COMPLETION | Jan 2030 | Mar 2030 | Jan 2030 | Mar 2030
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV175HVAC | SIZ - HVAC Building Systems Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2030 | Apr 2030 | Mar 2030 | Apr 2030
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV302BPH2 | SIIAS - Building B at SHCC Phase 2 | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV302BPH2 | SIIAS - Building B at SHCC Phase 2 | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV302BPH2 | SIIAS - Building B at SHCC Phase 2 | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV302BPH2 | SIIAS - Building B at SHCC Phase 2 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV302BPH2 | SIIAS - Building B at SHCC Phase 2 | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV302BPH2 | SIIAS - Building B at SHCC Phase 2 | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV302BPH2 | SIIAS - Building B at SHCC Phase 2 | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV302BPH2 | SIIAS - Building B at SHCC Phase 2 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV302BPH2 | SIIAS - Building B at SHCC Phase 2 | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV302BPH2 | SIIAS - Building B at SHCC Phase 2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341CAR2 | SIHS - Carriage Barn Phase 2 | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2024 | Sep 2024
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341CAR2 | SIHS - Carriage Barn Phase 2 | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2024 | Jan 2025
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341CAR2 | SIHS - Carriage Barn Phase 2 | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2025 | Jul 2025
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341CAR2 | SIHS - Carriage Barn Phase 2 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2025 | Oct 2025
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341CAR2 | SIHS - Carriage Barn Phase 2 | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2025 | Feb 2026
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341CAR2 | SIHS - Carriage Barn Phase 2 | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2026 | Jun 2026
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341CAR2 | SIHS - Carriage Barn Phase 2 | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2026 | Oct 2026
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341CAR2 | SIHS - Carriage Barn Phase 2 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2026 | Jan 2027
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341CAR2 | SIHS - Carriage Barn Phase 2 | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2027 | Mar 2027
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341CAR2 | SIHS - Carriage Barn Phase 2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2027 | Apr 2027
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341GALL | SIHS - Gallery Renovation | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341GALL | SIHS - Gallery Renovation | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341GALL | SIHS - Gallery Renovation | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341GALL | SIHS - Gallery Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341GALL | SIHS - Gallery Renovation | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341GALL | SIHS - Gallery Renovation | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341GALL | SIHS - Gallery Renovation | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341GALL | SIHS - Gallery Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341GALL | SIHS - Gallery Renovation | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341GALL | SIHS - Gallery Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341-HLD | SIHS Britton Cottage Return | 1 | DEVELOP SCOPE | Sep 2026 | Dec 2026 | Sep 2022 | Dec 2022
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341-HLD | SIHS Britton Cottage Return | 2 | PRELIMINARY DESIGN | Dec 2026 | Apr 2027 | Dec 2022 | Apr 2023
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341-HLD | SIHS Britton Cottage Return | 3 | FINAL DESIGN | Apr 2027 | Oct 2027 | Apr 2023 | Oct 2023
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341-HLD | SIHS Britton Cottage Return | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2027 | Jan 2028 | Oct 2023 | Jan 2024
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341-HLD | SIHS Britton Cottage Return | 5 | CONSTRUCTION TO 25% | Jan 2028 | May 2028 | Jan 2024 | May 2024
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341-HLD | SIHS Britton Cottage Return | 6 | CONSTRUCTION TO 50% | May 2028 | Sep 2028 | May 2024 | Sep 2024
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341-HLD | SIHS Britton Cottage Return | 7 | CONSTRUCTION TO 75% | Sep 2028 | Jan 2029 | Sep 2024 | Jan 2025
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341-HLD | SIHS Britton Cottage Return | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2029 | Apr 2029 | Jan 2025 | Apr 2025
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341-HLD | SIHS Britton Cottage Return | 9 | SUBSTANTIAL COMPLETION | Apr 2029 | Jun 2029 | Apr 2025 | Jun 2025
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341-HLD | SIHS Britton Cottage Return | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2029 | Jul 2029 | Jun 2025 | Jul 2025
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341SIPA | SIHS - Security System and Security Gates | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341SIPA | SIHS - Security System and Security Gates | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341SIPA | SIHS - Security System and Security Gates | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341SIPA | SIHS - Security System and Security Gates | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341SIPA | SIHS - Security System and Security Gates | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341SIPA | SIHS - Security System and Security Gates | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341SIPA | SIHS - Security System and Security Gates | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341SIPA | SIHS - Security System and Security Gates | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341SIPA | SIHS - Security System and Security Gates | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341SIPA | SIHS - Security System and Security Gates | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490CHIL | SHCC - Chiller and AC System | 1 | DEVELOP SCOPE | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490CHIL | SHCC - Chiller and AC System | 2 | PRELIMINARY DESIGN | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490CHIL | SHCC - Chiller and AC System | 3 | FINAL DESIGN | Jan 2026 | Jul 2026 | Jan 2026 | Jul 2026
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490CHIL | SHCC - Chiller and AC System | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2026 | Oct 2026 | Jul 2026 | Oct 2026
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490CHIL | SHCC - Chiller and AC System | 5 | CONSTRUCTION TO 25% | Oct 2026 | Feb 2027 | Oct 2026 | Feb 2027
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490CHIL | SHCC - Chiller and AC System | 6 | CONSTRUCTION TO 50% | Feb 2027 | Jun 2027 | Feb 2027 | Jun 2027
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490CHIL | SHCC - Chiller and AC System | 7 | CONSTRUCTION TO 75% | Jun 2027 | Oct 2027 | Jun 2027 | Oct 2027
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490CHIL | SHCC - Chiller and AC System | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jan 2028 | Oct 2027 | Jan 2028
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490CHIL | SHCC - Chiller and AC System | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Mar 2028 | Jan 2028 | Mar 2028
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490CHIL | SHCC - Chiller and AC System | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2028 | Apr 2028 | Mar 2028 | Apr 2028
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490CPSD | SHCC - Snug Harbor CPSD: Phase 1A | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490CPSD | SHCC - Snug Harbor CPSD: Phase 1A | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490CPSD | SHCC - Snug Harbor CPSD: Phase 1A | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490CPSD | SHCC - Snug Harbor CPSD: Phase 1A | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490CPSD | SHCC - Snug Harbor CPSD: Phase 1A | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490CPSD | SHCC - Snug Harbor CPSD: Phase 1A | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490CPSD | SHCC - Snug Harbor CPSD: Phase 1A | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490CPSD | SHCC - Snug Harbor CPSD: Phase 1A | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Dec 2026 | Oct 2026 | Dec 2026
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490CPSD | SHCC - Snug Harbor CPSD: Phase 1A | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Feb 2028 | Jan 2028 | Feb 2028
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490CPSD | SHCC - Snug Harbor CPSD: Phase 1A | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2028 | Mar 2028 | Mar 2028 | Mar 2028
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-GOV | SHCC - SNUG HARBOR - Governor's House Exterior Renovation | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2029 | Sep 2029
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-GOV | SHCC - SNUG HARBOR - Governor's House Exterior Renovation | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2029 | Jan 2030
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-GOV | SHCC - SNUG HARBOR - Governor's House Exterior Renovation | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2030 | Jul 2030
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-GOV | SHCC - SNUG HARBOR - Governor's House Exterior Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2030 | Oct 2030
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-GOV | SHCC - SNUG HARBOR - Governor's House Exterior Renovation | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2030 | Feb 2031
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-GOV | SHCC - SNUG HARBOR - Governor's House Exterior Renovation | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2031 | Jun 2031
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-GOV | SHCC - SNUG HARBOR - Governor's House Exterior Renovation | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2031 | Oct 2031
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-GOV | SHCC - SNUG HARBOR - Governor's House Exterior Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2031 | Jan 2032
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-GOV | SHCC - SNUG HARBOR - Governor's House Exterior Renovation | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2032 | Mar 2032
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-GOV | SHCC - SNUG HARBOR - Governor's House Exterior Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2032 | Apr 2032
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490INSR | SHCC - Site-Wide Infrastructure & Security BLDG. R | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490INSR | SHCC - Site-Wide Infrastructure & Security BLDG. R | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490INSR | SHCC - Site-Wide Infrastructure & Security BLDG. R | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490INSR | SHCC - Site-Wide Infrastructure & Security BLDG. R | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490INSR | SHCC - Site-Wide Infrastructure & Security BLDG. R | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490INSR | SHCC - Site-Wide Infrastructure & Security BLDG. R | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490INSR | SHCC - Site-Wide Infrastructure & Security BLDG. R | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490INSR | SHCC - Site-Wide Infrastructure & Security BLDG. R | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490INSR | SHCC - Site-Wide Infrastructure & Security BLDG. R | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490INSR | SHCC - Site-Wide Infrastructure & Security BLDG. R | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490INT | SHCC - Music Hall Interior | 1 | DEVELOP SCOPE | Jun 2026 | Sep 2026 | Jun 2026 | Sep 2026
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490INT | SHCC - Music Hall Interior | 2 | PRELIMINARY DESIGN | Sep 2026 | Jan 2027 | Sep 2026 | Jan 2027
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490INT | SHCC - Music Hall Interior | 3 | FINAL DESIGN | Jan 2027 | Jul 2027 | Jan 2027 | Jul 2027
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490INT | SHCC - Music Hall Interior | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2027 | Oct 2027 | Jul 2027 | Oct 2027
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490INT | SHCC - Music Hall Interior | 5 | CONSTRUCTION TO 25% | Oct 2027 | Feb 2028 | Oct 2027 | Feb 2028
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490INT | SHCC - Music Hall Interior | 6 | CONSTRUCTION TO 50% | Feb 2028 | Jun 2028 | Feb 2028 | Jun 2028
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490INT | SHCC - Music Hall Interior | 7 | CONSTRUCTION TO 75% | Jun 2028 | Oct 2028 | Jun 2028 | Oct 2028
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490INT | SHCC - Music Hall Interior | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2028 | Jan 2029 | Oct 2028 | Jan 2029
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490INT | SHCC - Music Hall Interior | 9 | SUBSTANTIAL COMPLETION | Jan 2029 | Mar 2029 | Jan 2029 | Mar 2029
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490INT | SHCC - Music Hall Interior | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2029 | Apr 2029 | Mar 2029 | Apr 2029
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490SWTG | SHCC - Emergency Electrical Switchgear | 1 | DEVELOP SCOPE | Jul 2025 | Sep 2025 | Jun 2022 | Sep 2022
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490SWTG | SHCC - Emergency Electrical Switchgear | 2 | PRELIMINARY DESIGN | Sep 2025 | Jan 2026 | Sep 2022 | Jan 2023
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490SWTG | SHCC - Emergency Electrical Switchgear | 3 | FINAL DESIGN | Jan 2026 | Jul 2026 | Jan 2023 | Jul 2023
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490SWTG | SHCC - Emergency Electrical Switchgear | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2026 | Oct 2026 | Jul 2023 | Oct 2023
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490SWTG | SHCC - Emergency Electrical Switchgear | 5 | CONSTRUCTION TO 25% | Oct 2026 | Feb 2027 | Oct 2023 | Feb 2024
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490SWTG | SHCC - Emergency Electrical Switchgear | 6 | CONSTRUCTION TO 50% | Feb 2027 | Jun 2027 | Feb 2024 | Jun 2024
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490SWTG | SHCC - Emergency Electrical Switchgear | 7 | CONSTRUCTION TO 75% | Jun 2027 | Oct 2027 | Jun 2024 | Oct 2024
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490SWTG | SHCC - Emergency Electrical Switchgear | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jan 2028 | Oct 2024 | Jan 2025
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490SWTG | SHCC - Emergency Electrical Switchgear | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Mar 2028 | Jan 2025 | Mar 2025
20231026 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490SWTG | SHCC - Emergency Electrical Switchgear | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2028 | Apr 2028 | Mar 2025 | Apr 2025
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | ANNADALE | Annadale Road Streetscape Project - Infrastructure Reno | 1 | DESIGN | Jun 2015 | Jul 2015 | Jun 2018 | Jul 2018
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | ANNADALE | Annadale Road Streetscape Project - Infrastructure Reno | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Aug 2015 | Jul 2018 | Aug 2018
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | ANNADALE | Annadale Road Streetscape Project - Infrastructure Reno | 3 | CONSTRUCTION | Aug 2015 | Sep 2015 | Aug 2018 | Sep 2018
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | ANNADALE | Annadale Road Streetscape Project - Infrastructure Reno | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2015 | Sep 2015 | Sep 2018 | Sep 2018
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | ANNADALE | Annadale Road Streetscape Project - Infrastructure Reno | 5 | SUBSTANTIAL COMPLETION | Sep 2015 | Oct 2015 | Sep 2018 | Oct 2018
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | ANNADALE | Annadale Road Streetscape Project - Infrastructure Reno | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2015 | Oct 2015 | Oct 2018 | Oct 2029
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | FORESTAVE | FOREST AVENUE | 1 | DESIGN | Jul 2019 | Jul 2019 | Jul 2019 | Jul 2019
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | FORESTAVE | FOREST AVENUE | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jul 2019 | Aug 2019
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | FORESTAVE | FOREST AVENUE | 3 | CONSTRUCTION | Aug 2019 | Sep 2019 | Aug 2019 | Sep 2019
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | FORESTAVE | FOREST AVENUE | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Sep 2019 | Sep 2019 | Sep 2019
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | FORESTAVE | FOREST AVENUE | 5 | SUBSTANTIAL COMPLETION | Sep 2019 | Oct 2021 | Sep 2019 | Oct 2021
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | FORESTAVE | FOREST AVENUE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2021 | Oct 2021 | Oct 2021 | Jun 2025
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | GE-343 | Replacement of Siphons b/t Brooklyn & SI | 1 | DESIGN | Jan 2005 | Mar 2007 | Jan 2005 | Mar 2007
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | GE-343 | Replacement of Siphons b/t Brooklyn & SI | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2007 | Mar 2007 | Mar 2007 | Mar 2007
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | GE-343 | Replacement of Siphons b/t Brooklyn & SI | 3 | CONSTRUCTION | Jul 2007 | Aug 2009 | Jul 2007 | Aug 2009
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | GE-343 | Replacement of Siphons b/t Brooklyn & SI | 4 | ORIGINAL EQUIP & FURNISHING | Aug 2009 | Aug 2009 | Aug 2009 | Aug 2009
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | GE-343 | Replacement of Siphons b/t Brooklyn & SI | 5 | SUBSTANTIAL COMPLETION | Aug 2009 | Aug 2009 | Aug 2009 | Jul 2020
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | GE-343 | Replacement of Siphons b/t Brooklyn & SI | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2009 | Aug 2009 | Jul 2020 | Jun 2033
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HOMEPORT2 | Stapleton Waterfront Phase II & III | 1 | DESIGN | Jun 2015 | Jul 2015 | Jun 2015 | Jul 2018
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HOMEPORT2 | Stapleton Waterfront Phase II & III | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Aug 2015 | Jul 2018 | Aug 2018
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HOMEPORT2 | Stapleton Waterfront Phase II & III | 3 | CONSTRUCTION | Aug 2015 | Sep 2015 | Aug 2018 | Sep 2018
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HOMEPORT2 | Stapleton Waterfront Phase II & III | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2015 | Sep 2015 | Sep 2018 | Sep 2018
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HOMEPORT2 | Stapleton Waterfront Phase II & III | 5 | SUBSTANTIAL COMPLETION | Sep 2015 | Oct 2015 | Sep 2018 | Oct 2018
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HOMEPORT2 | Stapleton Waterfront Phase II & III | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2015 | Oct 2015 | Oct 2018 | Jun 2028
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LNC018CHA | CHARLESTON - Site Acquisition and New Branch Construction | 1 | DESIGN | Jul 2017 | Jul 2017 | Jul 2017 | Jul 2017
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LNC018CHA | CHARLESTON - Site Acquisition and New Branch Construction | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Aug 2017 | Jul 2017 | Aug 2017
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LNC018CHA | CHARLESTON - Site Acquisition and New Branch Construction | 3 | CONSTRUCTION | Aug 2017 | Sep 2017 | Aug 2017 | Sep 2017
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LNC018CHA | CHARLESTON - Site Acquisition and New Branch Construction | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Sep 2017 | Sep 2017 | Sep 2017
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LNC018CHA | CHARLESTON - Site Acquisition and New Branch Construction | 5 | SUBSTANTIAL COMPLETION | Sep 2017 | Oct 2017 | Sep 2017 | Oct 2017
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LNC018CHA | CHARLESTON - Site Acquisition and New Branch Construction | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2017 | Oct 2017 | Oct 2017 | Jun 2033
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16PRT | PORT RICHMOND: MAJOR RENOVATION | 1 | DESIGN | Aug 2016 | Jan 2017 | Aug 2016 | Jan 2017
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16PRT | PORT RICHMOND: MAJOR RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2017 | Apr 2017 | Jan 2017 | Apr 2017
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16PRT | PORT RICHMOND: MAJOR RENOVATION | 3 | CONSTRUCTION | Apr 2017 | Apr 2018 | Apr 2017 | Apr 2022
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16PRT | PORT RICHMOND: MAJOR RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2018 | Feb 2019 | Apr 2022 | Feb 2024
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-TOMPK | NDF - Tompkinsville Esplanade and Pier | 1 | DESIGN | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-TOMPK | NDF - Tompkinsville Esplanade and Pier | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Aug 2021 | Jul 2021 | Aug 2021
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-TOMPK | NDF - Tompkinsville Esplanade and Pier | 3 | CONSTRUCTION | Aug 2021 | Sep 2021 | Aug 2021 | Sep 2021
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-TOMPK | NDF - Tompkinsville Esplanade and Pier | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Sep 2021 | Sep 2021 | Sep 2021
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-TOMPK | NDF - Tompkinsville Esplanade and Pier | 5 | SUBSTANTIAL COMPLETION | Sep 2021 | Oct 2021 | Sep 2021 | Oct 2021
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-TOMPK | NDF - Tompkinsville Esplanade and Pier | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2021 | Jun 2025 | Oct 2021 | Jun 2027
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | PWDSIBPCT | Van for the Staten Island Borough President's Clean Team -- | 1 | DESIGN | Jun 2015 | Jul 2015 | Jun 2015 | Jul 2015
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | PWDSIBPCT | Van for the Staten Island Borough President's Clean Team -- | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Aug 2015 | Jul 2015 | Aug 2015
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | PWDSIBPCT | Van for the Staten Island Borough President's Clean Team -- | 3 | CONSTRUCTION | Aug 2015 | Sep 2015 | Aug 2015 | Sep 2015
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | PWDSIBPCT | Van for the Staten Island Borough President's Clean Team -- | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2015 | Sep 2015 | Sep 2015 | Sep 2015
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | PWDSIBPCT | Van for the Staten Island Borough President's Clean Team -- | 5 | SUBSTANTIAL COMPLETION | Sep 2015 | Oct 2015 | Sep 2015 | Oct 2015
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | PWDSIBPCT | Van for the Staten Island Borough President's Clean Team -- | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2015 | Oct 2015 | Oct 2015 | Oct 2023
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | RCBBALLPK | RICHMOND COUNTY BANK BALLPARK AT ST. GEORGE | 1 | DESIGN | Jul 2019 | Jul 2019 | Jul 2019 | Jul 2019
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | RCBBALLPK | RICHMOND COUNTY BANK BALLPARK AT ST. GEORGE | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jul 2019 | Aug 2019
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | RCBBALLPK | RICHMOND COUNTY BANK BALLPARK AT ST. GEORGE | 3 | CONSTRUCTION | Aug 2019 | Sep 2019 | Aug 2019 | Sep 2019
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | RCBBALLPK | RICHMOND COUNTY BANK BALLPARK AT ST. GEORGE | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Sep 2019 | Sep 2019 | Sep 2019
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | RCBBALLPK | RICHMOND COUNTY BANK BALLPARK AT ST. GEORGE | 5 | SUBSTANTIAL COMPLETION | Sep 2019 | Oct 2021 | Sep 2019 | Oct 2021
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | RCBBALLPK | RICHMOND COUNTY BANK BALLPARK AT ST. GEORGE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2024
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDEDCG5 | Tompkinsville Esplanade - FEMA 428 Group 5 | 1 | DESIGN | Jul 2016 | Jul 2016 | Jul 2019 | Jul 2019
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDEDCG5 | Tompkinsville Esplanade - FEMA 428 Group 5 | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Jul 2019 | Aug 2019
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDEDCG5 | Tompkinsville Esplanade - FEMA 428 Group 5 | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Aug 2019 | Sep 2019
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDEDCG5 | Tompkinsville Esplanade - FEMA 428 Group 5 | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Sep 2019 | Sep 2019
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDEDCG5 | Tompkinsville Esplanade - FEMA 428 Group 5 | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Sep 2019 | Oct 2019
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDEDCG5 | Tompkinsville Esplanade - FEMA 428 Group 5 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2016 | Oct 2019 | Jun 2025
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG1HP | FEMA 428 G1 - Homeport Pier | 1 | DESIGN | Jul 2016 | Jul 2016 | Jul 2016 | Jul 2016
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG1HP | FEMA 428 G1 - Homeport Pier | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Jul 2016 | Aug 2016
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG1HP | FEMA 428 G1 - Homeport Pier | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Aug 2016 | Sep 2016
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG1HP | FEMA 428 G1 - Homeport Pier | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Sep 2016 | Sep 2016
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG1HP | FEMA 428 G1 - Homeport Pier | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Sep 2016 | Oct 2016
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG1HP | FEMA 428 G1 - Homeport Pier | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2016 | Oct 2016 | Oct 2024
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG1HS | FEMA 428 G1 - Homeport Substation | 1 | DESIGN | Jul 2016 | Jul 2016 | Jul 2019 | Jul 2019
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG1HS | FEMA 428 G1 - Homeport Substation | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Jul 2019 | Aug 2019
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG1HS | FEMA 428 G1 - Homeport Substation | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Aug 2019 | Sep 2019
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG1HS | FEMA 428 G1 - Homeport Substation | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Sep 2019 | Sep 2019
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG1HS | FEMA 428 G1 - Homeport Substation | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Sep 2019 | Oct 2019
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG1HS | FEMA 428 G1 - Homeport Substation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2016 | Oct 2019 | Oct 2022
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG4DOC | FEMA 428 G4- DOCKBUILDERS | 1 | DESIGN | Jul 2016 | Jul 2016 | Mar 2019 | Apr 2019
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG4DOC | FEMA 428 G4- DOCKBUILDERS | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Apr 2019 | Apr 2019
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG4DOC | FEMA 428 G4- DOCKBUILDERS | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Apr 2019 | Jun 2019
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG4DOC | FEMA 428 G4- DOCKBUILDERS | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Jun 2019 | Jun 2019
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG4DOC | FEMA 428 G4- DOCKBUILDERS | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Jun 2019 | Jun 2019
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG4DOC | FEMA 428 G4- DOCKBUILDERS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2016 | Jun 2019 | Jun 2030
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHOME | Repairs to Homeport as a result of Hurricane Sandy | 1 | DESIGN | Jun 2015 | Jul 2015 | Jun 2018 | Jul 2018
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHOME | Repairs to Homeport as a result of Hurricane Sandy | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Aug 2015 | Jul 2018 | Aug 2018
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHOME | Repairs to Homeport as a result of Hurricane Sandy | 3 | CONSTRUCTION | Aug 2015 | Sep 2015 | Aug 2018 | Sep 2018
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHOME | Repairs to Homeport as a result of Hurricane Sandy | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2015 | Sep 2015 | Sep 2018 | Sep 2018
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHOME | Repairs to Homeport as a result of Hurricane Sandy | 5 | SUBSTANTIAL COMPLETION | Sep 2015 | Oct 2015 | Sep 2018 | Oct 2018
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHOME | Repairs to Homeport as a result of Hurricane Sandy | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2015 | Oct 2015 | Oct 2018 | Jun 2028
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDSIHP2 | Stapleton Waterfront Phase II & III - Sandy Repairs | 1 | DESIGN | Jul 2018 | Jul 2018 | Jul 2018 | Jul 2018
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDSIHP2 | Stapleton Waterfront Phase II & III - Sandy Repairs | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Aug 2018 | Jul 2018 | Aug 2018
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDSIHP2 | Stapleton Waterfront Phase II & III - Sandy Repairs | 3 | CONSTRUCTION | Aug 2018 | Sep 2018 | Aug 2018 | Sep 2018
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDSIHP2 | Stapleton Waterfront Phase II & III - Sandy Repairs | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2018 | Sep 2018 | Sep 2018 | Sep 2018
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDSIHP2 | Stapleton Waterfront Phase II & III - Sandy Repairs | 5 | SUBSTANTIAL COMPLETION | Sep 2018 | Oct 2018 | Sep 2018 | Oct 2018
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDSIHP2 | Stapleton Waterfront Phase II & III - Sandy Repairs | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2018 | Oct 2018 | Oct 2018 | Jun 2025
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDSMC | Hurricane Sandy - Saw Mill Creek Marsh Restoration | 1 | DESIGN | Jan 2016 | Jan 2016 | Jan 2016 | Jan 2016
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDSMC | Hurricane Sandy - Saw Mill Creek Marsh Restoration | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2016 | Jun 2016 | Jan 2016 | Jun 2016
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDSMC | Hurricane Sandy - Saw Mill Creek Marsh Restoration | 3 | CONSTRUCTION | Jul 2016 | Jun 2017 | Jul 2016 | Jun 2017
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDSMC | Hurricane Sandy - Saw Mill Creek Marsh Restoration | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2017 | Jun 2020 | Jul 2017 | Jun 2024
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDSMC | Hurricane Sandy - Saw Mill Creek Marsh Restoration | 5 | SUBSTANTIAL COMPLETION | Jul 2020 | Jun 2020 | Jul 2024 | Jun 2024
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDSMC | Hurricane Sandy - Saw Mill Creek Marsh Restoration | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Jul 2020 | Jul 2024 | Jul 2024
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIBULK | Sandy Staten Island Esplanade Emergency Bulkhead Work | 1 | DESIGN | Jun 2011 | Jul 2011 | Jun 2014 | Jul 2014
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIBULK | Sandy Staten Island Esplanade Emergency Bulkhead Work | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2011 | Aug 2011 | Jul 2014 | Aug 2014
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIBULK | Sandy Staten Island Esplanade Emergency Bulkhead Work | 3 | CONSTRUCTION | Aug 2011 | Sep 2011 | Aug 2014 | Jun 2020
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIBULK | Sandy Staten Island Esplanade Emergency Bulkhead Work | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2011 | Sep 2011 | Jul 2020 | Jun 2020
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIBULK | Sandy Staten Island Esplanade Emergency Bulkhead Work | 5 | SUBSTANTIAL COMPLETION | Sep 2011 | Sep 2012 | Jul 2020 | Jun 2020
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIBULK | Sandy Staten Island Esplanade Emergency Bulkhead Work | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2012 | Oct 2012 | Jul 2020 | Jul 2025
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TRAVLIFT | Travis Avenue Lift Project -- Elevating section of Travis Av | 1 | DESIGN | Jan 2022 | Jan 2022 | Jan 2021 | Jan 2022
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TRAVLIFT | Travis Avenue Lift Project -- Elevating section of Travis Av | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2022 | Feb 2022 | Jan 2022 | Feb 2022
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TRAVLIFT | Travis Avenue Lift Project -- Elevating section of Travis Av | 3 | CONSTRUCTION | Feb 2022 | Mar 2022 | Feb 2022 | Mar 2022
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TRAVLIFT | Travis Avenue Lift Project -- Elevating section of Travis Av | 4 | ORIGINAL EQUIP & FURNISHING | Mar 2022 | Mar 2022 | Mar 2022 | Mar 2022
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TRAVLIFT | Travis Avenue Lift Project -- Elevating section of Travis Av | 5 | SUBSTANTIAL COMPLETION | Mar 2022 | Apr 2022 | Mar 2022 | Apr 2022
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TRAVLIFT | Travis Avenue Lift Project -- Elevating section of Travis Av | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2022 | Apr 2022 | Apr 2022 | Apr 2026
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TRAVSIDEW | TRAVIS AVENUE ELEVATION - FOR SIDEWALK/WALKWAY TO NATURE PRE | 1 | DESIGN | Jan 2022 | Jan 2022 | Jan 2021 | Jan 2022
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TRAVSIDEW | TRAVIS AVENUE ELEVATION - FOR SIDEWALK/WALKWAY TO NATURE PRE | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2022 | Feb 2022 | Jan 2022 | Feb 2022
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TRAVSIDEW | TRAVIS AVENUE ELEVATION - FOR SIDEWALK/WALKWAY TO NATURE PRE | 3 | CONSTRUCTION | Feb 2022 | Mar 2022 | Feb 2022 | Mar 2022
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TRAVSIDEW | TRAVIS AVENUE ELEVATION - FOR SIDEWALK/WALKWAY TO NATURE PRE | 4 | ORIGINAL EQUIP & FURNISHING | Mar 2022 | Mar 2022 | Mar 2022 | Mar 2022
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TRAVSIDEW | TRAVIS AVENUE ELEVATION - FOR SIDEWALK/WALKWAY TO NATURE PRE | 5 | SUBSTANTIAL COMPLETION | Mar 2022 | Apr 2022 | Mar 2022 | Apr 2022
20231026 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TRAVSIDEW | TRAVIS AVENUE ELEVATION - FOR SIDEWALK/WALKWAY TO NATURE PRE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2022 | Apr 2022 | Apr 2022 | Apr 2026
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CSLF | CASSIDY LAFAYETTE SECURITY CAMERAS | 1 | DESIGN | Jan 2018 | Jun 2018 | Jan 2018 | Jun 2018
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CSLF | CASSIDY LAFAYETTE SECURITY CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CSLF | CASSIDY LAFAYETTE SECURITY CAMERAS | 3 | CONSTRUCTION | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CSLF | CASSIDY LAFAYETTE SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2018 | Dec 2019
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CSLF | CASSIDY LAFAYETTE SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2019 | Dec 2023
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18NLAC | NEW LANE SHORES LUNCH ROOM AC | 1 | DESIGN | May 2018 | Oct 2018 | May 2018 | Oct 2018
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18NLAC | NEW LANE SHORES LUNCH ROOM AC | 2 | BID AWARD AND REGISTER CONTRCT | Oct 2018 | Apr 2019 | Oct 2018 | Apr 2019
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18NLAC | NEW LANE SHORES LUNCH ROOM AC | 3 | CONSTRUCTION | Apr 2019 | Apr 2020 | Apr 2019 | Apr 2020
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18NLAC | NEW LANE SHORES LUNCH ROOM AC | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2020 | Oct 2020 | Apr 2019 | Apr 2020
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18NLAC | NEW LANE SHORES LUNCH ROOM AC | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2020 | Oct 2020 | Apr 2020 | Apr 2023
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM19SBCU | SOUTH BEACH HOUSES CAMERA UPGRADES | 1 | DESIGN | Oct 2018 | Apr 2019 | Oct 2018 | Apr 2019
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM19SBCU | SOUTH BEACH HOUSES CAMERA UPGRADES | 2 | BID AWARD AND REGISTER CONTRCT | Apr 2019 | Oct 2019 | Apr 2019 | Oct 2019
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM19SBCU | SOUTH BEACH HOUSES CAMERA UPGRADES | 3 | CONSTRUCTION | Oct 2019 | Oct 2020 | Oct 2019 | Oct 2020
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM19SBCU | SOUTH BEACH HOUSES CAMERA UPGRADES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2020 | Apr 2021 | Oct 2019 | Oct 2020
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM19SBCU | SOUTH BEACH HOUSES CAMERA UPGRADES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2020 | Apr 2021 | Oct 2020 | Apr 2021
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHCC | BERRY HOUSES CAMERA UPGRADES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2018 | Dec 2019
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHCC | BERRY HOUSES CAMERA UPGRADES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2019 | Dec 2021
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SBLU | SOUTH BEACH HOUSES- LIGHTING UPGRADES | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Aug 2020 | Feb 2020 | Aug 2020
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SBLU | SOUTH BEACH HOUSES- LIGHTING UPGRADES | 3 | CONSTRUCTION | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SBLU | SOUTH BEACH HOUSES- LIGHTING UPGRADES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2020 | Aug 2021
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SBLU | SOUTH BEACH HOUSES- LIGHTING UPGRADES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2021 | Aug 2023
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHTV | CCTV CAMERAS AT MARINERS HARBOR HOUSES | 1 | DESIGN | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHTV | CCTV CAMERAS AT MARINERS HARBOR HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHTV | CCTV CAMERAS AT MARINERS HARBOR HOUSES | 3 | CONSTRUCTION | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHTV | CCTV CAMERAS AT MARINERS HARBOR HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2021 | Jun 2022
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHTV | CCTV CAMERAS AT MARINERS HARBOR HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM21NLCI | CONCRETE INSTALLATION AT NEW LANE HOUSES | 1 | DESIGN | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM21NLCI | CONCRETE INSTALLATION AT NEW LANE HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM21NLCI | CONCRETE INSTALLATION AT NEW LANE HOUSES | 3 | CONSTRUCTION | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM21NLCI | CONCRETE INSTALLATION AT NEW LANE HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2021 | Jun 2022
20231026 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM21NLCI | CONCRETE INSTALLATION AT NEW LANE HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 26202302 | GOTHAM: VANDERBILT DENTAL SUITE | 1 | DESIGN | Sep 2022 | Mar 2023 | Sep 2022 | Mar 2023
20231026 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 26202302 | GOTHAM: VANDERBILT DENTAL SUITE | 2 | CONSTRUCTION | Mar 2023 | Sep 2028 | Mar 2023 | Sep 2028
20231026 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75200902 | SEAVIEW: RENOVATION OF ISOLATION BUILDING | 1 | DESIGN | Jul 2012 | May 2013 | Jun 2013 | Jun 2033
20231026 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75200902 | SEAVIEW: RENOVATION OF ISOLATION BUILDING | 2 | CONSTRUCTION | Jun 2013 | May 2014 | Jun 2013 | Jun 2033
20231026 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75200902 | SEAVIEW: RENOVATION OF ISOLATION BUILDING | 3 | CONSTRUCTION | Jun 2013 | May 2014 | Jul 2033 | Jul 2046
20231026 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75201502 | SEAVIEW EMERGENCY GENERATOR REPLACEMENT | 1 | DESIGN | May 2015 | Mar 2016 | Apr 2016 | Jun 2032
20231026 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75201502 | SEAVIEW EMERGENCY GENERATOR REPLACEMENT | 2 | CONSTRUCTION | Mar 2016 | Mar 2017 | Apr 2016 | Jun 2032
20231026 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75201502 | SEAVIEW EMERGENCY GENERATOR REPLACEMENT | 3 | CONSTRUCTION | Mar 2016 | Mar 2017 | Jul 2032 | Sep 2042
20231026 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75202201 | SEAVIEW SHOWER ROOMS REPLACEMENT | 1 | DESIGN | May 2020 | Sep 2021 | May 2022 | Jun 2032
20231026 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75202201 | SEAVIEW SHOWER ROOMS REPLACEMENT | 2 | CONSTRUCTION | Sep 2021 | Sep 2023 | Jul 2032 | Jun 2034
20231026 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75202201 | SEAVIEW SHOWER ROOMS REPLACEMENT | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Dec 2023 | Jul 2034 | Apr 2038
20231026 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75202202 | SEAVIEW PEDIATRIC CENTER | 1 | DESIGN | Jun 2025 | Apr 2026 | Jun 2026 | Apr 2027
20231026 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75202202 | SEAVIEW PEDIATRIC CENTER | 2 | CONSTRUCTION | Apr 2026 | Apr 2027 | Jun 2026 | Apr 2027
20231026 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75202202 | SEAVIEW PEDIATRIC CENTER | 3 | CONSTRUCTION | Apr 2026 | Apr 2027 | Apr 2027 | Apr 2028
20231026 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75202401 | SEAVIEW KITCHEN UPDATE--KITCHEN UPDATE | 1 | DESIGN | Apr 2023 | Sep 2024 | Apr 2023 | Sep 2024
20231026 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75202401 | SEAVIEW KITCHEN UPDATE--KITCHEN UPDATE | 2 | CONSTRUCTION | Sep 2024 | Sep 2027 | Sep 2024 | Sep 2027
20231026 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75202401 | SEAVIEW KITCHEN UPDATE--KITCHEN UPDATE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Dec 2027 | Sep 2027 | Dec 2027
20231026 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75202402 | SEAVIEW HOSPITAL: UPGRADE TO OCCUPATIONAL ROOM | 1 | DESIGN | Apr 2023 | Sep 2024 | Apr 2023 | Sep 2024
20231026 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75202402 | SEAVIEW HOSPITAL: UPGRADE TO OCCUPATIONAL ROOM | 2 | CONSTRUCTION | Sep 2024 | Sep 2027 | Sep 2024 | Sep 2027
20231026 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75202402 | SEAVIEW HOSPITAL: UPGRADE TO OCCUPATIONAL ROOM | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Dec 2027 | Sep 2027 | Dec 2027
20231026 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75202403 | SEAVIEW HOSPITAL: UPGRADE TO PHYSICAL THERAPY ROOM | 1 | DESIGN | Apr 2023 | Sep 2024 | Apr 2023 | Sep 2024
20231026 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75202403 | SEAVIEW HOSPITAL: UPGRADE TO PHYSICAL THERAPY ROOM | 2 | CONSTRUCTION | Sep 2024 | Sep 2027 | Sep 2024 | Sep 2027
20231026 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75202403 | SEAVIEW HOSPITAL: UPGRADE TO PHYSICAL THERAPY ROOM | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Dec 2027 | Sep 2027 | Dec 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SER25 | Reconstruction of Existing Sewers, Staten Island | 1 | DEVELOP SCOPE | Jan 2023 | Apr 2023 | Jan 2023 | Apr 2023
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SER25 | Reconstruction of Existing Sewers, Staten Island | 2 | PRELIMINARY DESIGN | Apr 2023 | Aug 2023 | Apr 2023 | Aug 2023
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SER25 | Reconstruction of Existing Sewers, Staten Island | 3 | FINAL DESIGN | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SER25 | Reconstruction of Existing Sewers, Staten Island | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2024 | May 2024 | Feb 2024 | May 2024
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SER25 | Reconstruction of Existing Sewers, Staten Island | 5 | CONSTRUCTION TO 25% | May 2024 | Aug 2024 | May 2024 | Aug 2024
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SER25 | Reconstruction of Existing Sewers, Staten Island | 6 | CONSTRUCTION TO 50% | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SER25 | Reconstruction of Existing Sewers, Staten Island | 7 | CONSTRUCTION TO 75% | Dec 2024 | Apr 2025 | Dec 2024 | Apr 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SER25 | Reconstruction of Existing Sewers, Staten Island | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2025 | Jul 2025 | Apr 2025 | Jul 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SER25 | Reconstruction of Existing Sewers, Staten Island | 9 | SUBSTANTIAL COMPLETION | Jul 2025 | Sep 2025 | Jul 2025 | Sep 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SER25 | Reconstruction of Existing Sewers, Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Oct 2025 | Sep 2025 | Oct 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | MIBBNC05B | Instal New Storm SE & Rplmt San SE & Dist WM Hylan Blvd SI | 1 | DEVELOP SCOPE | Jan 2026 | Mar 2026 | Jan 2024 | Mar 2024
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | MIBBNC05B | Instal New Storm SE & Rplmt San SE & Dist WM Hylan Blvd SI | 2 | PRELIMINARY DESIGN | Apr 2026 | Jul 2026 | Mar 2024 | Jul 2024
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | MIBBNC05B | Instal New Storm SE & Rplmt San SE & Dist WM Hylan Blvd SI | 3 | FINAL DESIGN | Jul 2026 | Jan 2027 | Jul 2024 | Jan 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | MIBBNC05B | Instal New Storm SE & Rplmt San SE & Dist WM Hylan Blvd SI | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2027 | Apr 2027 | Jan 2025 | Apr 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | MIBBNC05B | Instal New Storm SE & Rplmt San SE & Dist WM Hylan Blvd SI | 5 | CONSTRUCTION TO 25% | Apr 2027 | Aug 2027 | Apr 2025 | Aug 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | MIBBNC05B | Instal New Storm SE & Rplmt San SE & Dist WM Hylan Blvd SI | 6 | CONSTRUCTION TO 50% | Aug 2027 | Dec 2027 | Aug 2025 | Dec 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | MIBBNC05B | Instal New Storm SE & Rplmt San SE & Dist WM Hylan Blvd SI | 7 | CONSTRUCTION TO 75% | Dec 2027 | Apr 2028 | Dec 2025 | Apr 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | MIBBNC05B | Instal New Storm SE & Rplmt San SE & Dist WM Hylan Blvd SI | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2028 | Jul 2028 | Apr 2026 | Jul 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | MIBBNC05B | Instal New Storm SE & Rplmt San SE & Dist WM Hylan Blvd SI | 9 | SUBSTANTIAL COMPLETION | Jul 2028 | Sep 2028 | Jul 2026 | Sep 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | MIBBNC05B | Instal New Storm SE & Rplmt San SE & Dist WM Hylan Blvd SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2028 | Oct 2028 | Sep 2026 | Oct 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | NCMCCSG | NEW CLOVE PS: EQUIPMENT REPLACEMENT | 1 | PRE-CONSTRUCTION MOBILIZATION | Jun 2019 | May 2020 | Jun 2019 | May 2020
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | NCMCCSG | NEW CLOVE PS: EQUIPMENT REPLACEMENT | 2 | ON-SITE CONSTRUCTION MANAGEMEN | May 2020 | Apr 2026 | May 2020 | Apr 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | NCMCCSG | NEW CLOVE PS: EQUIPMENT REPLACEMENT | 3 | POST-CONSTRUCTION CLOSE-OUT | Apr 2026 | Apr 2027 | Apr 2026 | Apr 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-134-L | POWER DISTRIBUTION AT OAKWOOD BEACH WPCP | 1 | DEVELOP SCOPE | Jul 2017 | Sep 2017 | Jul 2017 | Mar 2018
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-134-L | POWER DISTRIBUTION AT OAKWOOD BEACH WPCP | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Mar 2018 | Mar 2019
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-134-L | POWER DISTRIBUTION AT OAKWOOD BEACH WPCP | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Mar 2019 | Sep 2020
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-134-L | POWER DISTRIBUTION AT OAKWOOD BEACH WPCP | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Sep 2020 | Jun 2021
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-134-L | POWER DISTRIBUTION AT OAKWOOD BEACH WPCP | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Jun 2021 | Jun 2022
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-134-L | POWER DISTRIBUTION AT OAKWOOD BEACH WPCP | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Jun 2022 | May 2023
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-134-L | POWER DISTRIBUTION AT OAKWOOD BEACH WPCP | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | May 2023 | May 2024
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-134-L | POWER DISTRIBUTION AT OAKWOOD BEACH WPCP | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | May 2024 | Feb 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-134-L | POWER DISTRIBUTION AT OAKWOOD BEACH WPCP | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Feb 2025 | Aug 2029
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-134-L | POWER DISTRIBUTION AT OAKWOOD BEACH WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Aug 2029 | Nov 2029
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-135-L | HEADWORKS AT OAKWOOD BEACH WPCP | 1 | DEVELOP SCOPE | Jul 2017 | Sep 2017 | Jun 2020 | Feb 2021
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-135-L | HEADWORKS AT OAKWOOD BEACH WPCP | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Feb 2021 | Feb 2022
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-135-L | HEADWORKS AT OAKWOOD BEACH WPCP | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Feb 2022 | Aug 2023
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-135-L | HEADWORKS AT OAKWOOD BEACH WPCP | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Aug 2023 | May 2024
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-135-L | HEADWORKS AT OAKWOOD BEACH WPCP | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | May 2024 | May 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-135-L | HEADWORKS AT OAKWOOD BEACH WPCP | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | May 2025 | Apr 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-135-L | HEADWORKS AT OAKWOOD BEACH WPCP | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | May 2026 | Apr 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-135-L | HEADWORKS AT OAKWOOD BEACH WPCP | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Apr 2027 | Jan 2028
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-135-L | HEADWORKS AT OAKWOOD BEACH WPCP | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jan 2028 | Jul 2032
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-135-L | HEADWORKS AT OAKWOOD BEACH WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Jul 2032 | Oct 2032
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-136-L | INSTALLATION OF (2) MAIN TRANSFORMERS @ OAKWOOD BEACH WPCP | 1 | DEVELOP SCOPE | Jun 2013 | Mar 2014 | Jun 2014 | Feb 2015
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-136-L | INSTALLATION OF (2) MAIN TRANSFORMERS @ OAKWOOD BEACH WPCP | 2 | PRELIMINARY DESIGN | Mar 2014 | Mar 2015 | Feb 2015 | Feb 2016
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-136-L | INSTALLATION OF (2) MAIN TRANSFORMERS @ OAKWOOD BEACH WPCP | 3 | FINAL DESIGN | Mar 2015 | Aug 2016 | Feb 2016 | Aug 2017
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-136-L | INSTALLATION OF (2) MAIN TRANSFORMERS @ OAKWOOD BEACH WPCP | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2016 | May 2017 | Aug 2017 | May 2018
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-136-L | INSTALLATION OF (2) MAIN TRANSFORMERS @ OAKWOOD BEACH WPCP | 5 | CONSTRUCTION TO 25% | May 2017 | May 2018 | May 2018 | May 2019
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-136-L | INSTALLATION OF (2) MAIN TRANSFORMERS @ OAKWOOD BEACH WPCP | 6 | CONSTRUCTION TO 50% | May 2018 | May 2019 | May 2019 | Apr 2020
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-136-L | INSTALLATION OF (2) MAIN TRANSFORMERS @ OAKWOOD BEACH WPCP | 7 | CONSTRUCTION TO 75% | May 2019 | May 2020 | Apr 2020 | Apr 2021
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-136-L | INSTALLATION OF (2) MAIN TRANSFORMERS @ OAKWOOD BEACH WPCP | 8 | ORIGINAL EQUIP & FURNISHING | May 2020 | Jan 2021 | Apr 2021 | Jan 2022
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-136-L | INSTALLATION OF (2) MAIN TRANSFORMERS @ OAKWOOD BEACH WPCP | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Jul 2021 | Jan 2022 | Jul 2030
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-136-L | INSTALLATION OF (2) MAIN TRANSFORMERS @ OAKWOOD BEACH WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Oct 2021 | Jul 2030 | Oct 2030
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-143-L | DEWATERING BUILDING IMPROVEMENTS @ OAKWOOD BEACH WPCP | 1 | DEVELOP SCOPE | Jun 2025 | Feb 2026 | Jun 2025 | Feb 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-143-L | DEWATERING BUILDING IMPROVEMENTS @ OAKWOOD BEACH WPCP | 2 | PRELIMINARY DESIGN | Feb 2026 | Feb 2027 | Feb 2026 | Feb 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-143-L | DEWATERING BUILDING IMPROVEMENTS @ OAKWOOD BEACH WPCP | 3 | FINAL DESIGN | Feb 2027 | Aug 2028 | Feb 2027 | Aug 2028
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-143-L | DEWATERING BUILDING IMPROVEMENTS @ OAKWOOD BEACH WPCP | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2028 | May 2029 | Aug 2028 | May 2029
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-143-L | DEWATERING BUILDING IMPROVEMENTS @ OAKWOOD BEACH WPCP | 5 | CONSTRUCTION TO 25% | May 2029 | May 2030 | May 2029 | May 2030
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-143-L | DEWATERING BUILDING IMPROVEMENTS @ OAKWOOD BEACH WPCP | 6 | CONSTRUCTION TO 50% | May 2030 | Apr 2031 | May 2030 | Apr 2031
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-143-L | DEWATERING BUILDING IMPROVEMENTS @ OAKWOOD BEACH WPCP | 7 | CONSTRUCTION TO 75% | May 2031 | Apr 2032 | May 2031 | Apr 2032
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-143-L | DEWATERING BUILDING IMPROVEMENTS @ OAKWOOD BEACH WPCP | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2032 | Jan 2033 | Apr 2032 | Jan 2033
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-143-L | DEWATERING BUILDING IMPROVEMENTS @ OAKWOOD BEACH WPCP | 9 | SUBSTANTIAL COMPLETION | Jan 2033 | Jul 2033 | Jan 2033 | Jul 2033
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-143-L | DEWATERING BUILDING IMPROVEMENTS @ OAKWOOD BEACH WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2033 | Oct 2033 | Jul 2033 | Oct 2033
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-144-L | TRC - CONS OF DISINFECTION FACILITIES AT OAKWOOD BEACH | 1 | DEVELOP SCOPE | Jul 2017 | Mar 2018 | Jul 2017 | Mar 2018
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-144-L | TRC - CONS OF DISINFECTION FACILITIES AT OAKWOOD BEACH | 2 | PRELIMINARY DESIGN | Mar 2018 | Mar 2019 | Mar 2018 | Mar 2019
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-144-L | TRC - CONS OF DISINFECTION FACILITIES AT OAKWOOD BEACH | 3 | FINAL DESIGN | Mar 2019 | Sep 2020 | Mar 2019 | Sep 2020
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-144-L | TRC - CONS OF DISINFECTION FACILITIES AT OAKWOOD BEACH | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2020 | Jun 2021 | Sep 2020 | Jun 2021
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-144-L | TRC - CONS OF DISINFECTION FACILITIES AT OAKWOOD BEACH | 5 | CONSTRUCTION TO 25% | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-144-L | TRC - CONS OF DISINFECTION FACILITIES AT OAKWOOD BEACH | 6 | CONSTRUCTION TO 50% | Jun 2022 | May 2023 | Jun 2022 | May 2023
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-144-L | TRC - CONS OF DISINFECTION FACILITIES AT OAKWOOD BEACH | 7 | CONSTRUCTION TO 75% | May 2023 | May 2024 | May 2023 | May 2024
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-144-L | TRC - CONS OF DISINFECTION FACILITIES AT OAKWOOD BEACH | 8 | ORIGINAL EQUIP & FURNISHING | May 2024 | Feb 2025 | May 2024 | Feb 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-144-L | TRC - CONS OF DISINFECTION FACILITIES AT OAKWOOD BEACH | 9 | SUBSTANTIAL COMPLETION | Feb 2025 | Aug 2025 | Feb 2025 | Aug 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-144-L | TRC - CONS OF DISINFECTION FACILITIES AT OAKWOOD BEACH | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2025 | Nov 2025 | Aug 2025 | Nov 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-149-L | UPGRADE FIRE ALARM SYSTEM @ OAKWOOD BEACH DEWATERING BLDG | 1 | FINAL DESIGN | Jun 2022 | Nov 2023 | Jun 2029 | Nov 2030
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-149-L | UPGRADE FIRE ALARM SYSTEM @ OAKWOOD BEACH DEWATERING BLDG | 2 | CONSTRUCTION TO 25% | Nov 2023 | Jul 2024 | Nov 2030 | Jul 2031
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-149-L | UPGRADE FIRE ALARM SYSTEM @ OAKWOOD BEACH DEWATERING BLDG | 3 | CONSTRUCTION TO 50% | Jul 2024 | Mar 2025 | Jul 2031 | Mar 2032
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-149-L | UPGRADE FIRE ALARM SYSTEM @ OAKWOOD BEACH DEWATERING BLDG | 4 | CONSTRUCTION TO 75% | Mar 2025 | Nov 2025 | Mar 2032 | Nov 2032
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-132-L | RECONSTRUCTION OF SEA WALL/SLUDGE DOCK IMPROVEMENTS | 1 | DEVELOP SCOPE | Jul 2022 | Sep 2022 | Jul 2018 | Mar 2019
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-132-L | RECONSTRUCTION OF SEA WALL/SLUDGE DOCK IMPROVEMENTS | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Mar 2019 | Mar 2020
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-132-L | RECONSTRUCTION OF SEA WALL/SLUDGE DOCK IMPROVEMENTS | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Mar 2020 | Sep 2021
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-132-L | RECONSTRUCTION OF SEA WALL/SLUDGE DOCK IMPROVEMENTS | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Sep 2021 | Jun 2022
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-132-L | RECONSTRUCTION OF SEA WALL/SLUDGE DOCK IMPROVEMENTS | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Jun 2022 | Jun 2023
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-132-L | RECONSTRUCTION OF SEA WALL/SLUDGE DOCK IMPROVEMENTS | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Jun 2023 | May 2024
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-132-L | RECONSTRUCTION OF SEA WALL/SLUDGE DOCK IMPROVEMENTS | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | May 2024 | May 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-132-L | RECONSTRUCTION OF SEA WALL/SLUDGE DOCK IMPROVEMENTS | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | May 2025 | Feb 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-132-L | RECONSTRUCTION OF SEA WALL/SLUDGE DOCK IMPROVEMENTS | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Feb 2026 | Aug 2030
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-132-L | RECONSTRUCTION OF SEA WALL/SLUDGE DOCK IMPROVEMENTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Aug 2030 | Nov 2030
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-134-L | RECONSTRUCT FINAL SETTLING SYSTEM EQUIPMENT @ PORT RICHMOND | 1 | DEVELOP SCOPE | Jul 2017 | Mar 2018 | Jun 2021 | Feb 2022
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-134-L | RECONSTRUCT FINAL SETTLING SYSTEM EQUIPMENT @ PORT RICHMOND | 2 | PRELIMINARY DESIGN | Mar 2018 | Mar 2019 | Feb 2022 | Feb 2023
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-134-L | RECONSTRUCT FINAL SETTLING SYSTEM EQUIPMENT @ PORT RICHMOND | 3 | FINAL DESIGN | Mar 2019 | Sep 2020 | Feb 2023 | Aug 2024
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-134-L | RECONSTRUCT FINAL SETTLING SYSTEM EQUIPMENT @ PORT RICHMOND | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2020 | Jun 2021 | Aug 2024 | May 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-134-L | RECONSTRUCT FINAL SETTLING SYSTEM EQUIPMENT @ PORT RICHMOND | 5 | CONSTRUCTION TO 25% | Jun 2021 | Jun 2022 | May 2025 | May 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-134-L | RECONSTRUCT FINAL SETTLING SYSTEM EQUIPMENT @ PORT RICHMOND | 6 | CONSTRUCTION TO 50% | Jun 2022 | May 2023 | May 2026 | Apr 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-134-L | RECONSTRUCT FINAL SETTLING SYSTEM EQUIPMENT @ PORT RICHMOND | 7 | CONSTRUCTION TO 75% | May 2023 | May 2024 | May 2027 | Apr 2028
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-134-L | RECONSTRUCT FINAL SETTLING SYSTEM EQUIPMENT @ PORT RICHMOND | 8 | ORIGINAL EQUIP & FURNISHING | May 2024 | Feb 2025 | Apr 2028 | Jan 2029
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-134-L | RECONSTRUCT FINAL SETTLING SYSTEM EQUIPMENT @ PORT RICHMOND | 9 | SUBSTANTIAL COMPLETION | Feb 2025 | Aug 2025 | Jan 2029 | Jul 2033
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-134-L | RECONSTRUCT FINAL SETTLING SYSTEM EQUIPMENT @ PORT RICHMOND | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2025 | Nov 2025 | Jul 2033 | Oct 2033
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-135-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ PORT RICHMOND | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Feb 2023
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-135-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ PORT RICHMOND | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Feb 2023 | Feb 2024
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-135-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ PORT RICHMOND | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Feb 2024 | Aug 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-135-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ PORT RICHMOND | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Aug 2025 | May 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-135-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ PORT RICHMOND | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | May 2026 | May 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-135-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ PORT RICHMOND | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | May 2027 | Apr 2028
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-135-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ PORT RICHMOND | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | Apr 2028 | Apr 2029
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-135-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ PORT RICHMOND | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Apr 2029 | Jan 2030
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-135-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ PORT RICHMOND | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Jan 2030 | Jul 2030
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-135-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ PORT RICHMOND | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Mar 2025 | Jul 2030 | Oct 2030
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-139-L | RECONSTRUCT AERATION EQUIPMENT @ THE PORT RICHMOND WWTP | 1 | DEVELOP SCOPE | Jun 2023 | Feb 2024 | Jul 2019 | Mar 2020
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-139-L | RECONSTRUCT AERATION EQUIPMENT @ THE PORT RICHMOND WWTP | 2 | PRELIMINARY DESIGN | Feb 2024 | Feb 2025 | Mar 2020 | Mar 2021
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-139-L | RECONSTRUCT AERATION EQUIPMENT @ THE PORT RICHMOND WWTP | 3 | FINAL DESIGN | Feb 2025 | Aug 2026 | Mar 2021 | Sep 2022
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-139-L | RECONSTRUCT AERATION EQUIPMENT @ THE PORT RICHMOND WWTP | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2026 | May 2027 | Sep 2022 | Jun 2023
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-139-L | RECONSTRUCT AERATION EQUIPMENT @ THE PORT RICHMOND WWTP | 5 | CONSTRUCTION TO 25% | May 2027 | May 2028 | Jun 2023 | Jun 2024
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-139-L | RECONSTRUCT AERATION EQUIPMENT @ THE PORT RICHMOND WWTP | 6 | CONSTRUCTION TO 50% | May 2028 | Apr 2029 | Jun 2024 | May 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-139-L | RECONSTRUCT AERATION EQUIPMENT @ THE PORT RICHMOND WWTP | 7 | CONSTRUCTION TO 75% | Apr 2029 | Apr 2030 | May 2025 | May 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-139-L | RECONSTRUCT AERATION EQUIPMENT @ THE PORT RICHMOND WWTP | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2030 | Jan 2031 | May 2026 | Feb 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-139-L | RECONSTRUCT AERATION EQUIPMENT @ THE PORT RICHMOND WWTP | 9 | SUBSTANTIAL COMPLETION | Jan 2031 | Jul 2031 | Feb 2027 | Aug 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-139-L | RECONSTRUCT AERATION EQUIPMENT @ THE PORT RICHMOND WWTP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2031 | Oct 2031 | Aug 2027 | Nov 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-144-L | RECONSTRUCT BLOWERS AND CONTROLS @ PORT RICHMOND WPCP | 1 | FINAL DESIGN | Jun 2023 | Nov 2024 | Jun 2023 | Nov 2024
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-144-L | RECONSTRUCT BLOWERS AND CONTROLS @ PORT RICHMOND WPCP | 2 | CONSTRUCTION TO 25% | Nov 2024 | Jul 2025 | Nov 2024 | Jul 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-144-L | RECONSTRUCT BLOWERS AND CONTROLS @ PORT RICHMOND WPCP | 3 | CONSTRUCTION TO 50% | Jul 2025 | Mar 2026 | Jul 2025 | Mar 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-144-L | RECONSTRUCT BLOWERS AND CONTROLS @ PORT RICHMOND WPCP | 4 | CONSTRUCTION TO 75% | Mar 2026 | Nov 2026 | Mar 2026 | Nov 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-151-L | RECONST AERATION TANK GATES/ACTUATOR & SUPPORTS @ PR WRRF | 1 | DESIGN | Jun 2022 | Nov 2022 | Jun 2022 | Feb 2023
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-151-L | RECONST AERATION TANK GATES/ACTUATOR & SUPPORTS @ PR WRRF | 2 | CONSTRUCTION | Nov 2022 | May 2023 | Feb 2023 | Feb 2024
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-151-L | RECONST AERATION TANK GATES/ACTUATOR & SUPPORTS @ PR WRRF | 3 | FINAL DESIGN | Nov 2022 | May 2023 | Feb 2024 | Aug 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-151-L | RECONST AERATION TANK GATES/ACTUATOR & SUPPORTS @ PR WRRF | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2022 | May 2023 | Aug 2025 | May 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-151-L | RECONST AERATION TANK GATES/ACTUATOR & SUPPORTS @ PR WRRF | 5 | CONSTRUCTION TO 25% | Nov 2022 | May 2023 | May 2026 | May 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-151-L | RECONST AERATION TANK GATES/ACTUATOR & SUPPORTS @ PR WRRF | 6 | CONSTRUCTION TO 50% | Nov 2022 | May 2023 | May 2027 | Apr 2028
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-151-L | RECONST AERATION TANK GATES/ACTUATOR & SUPPORTS @ PR WRRF | 7 | CONSTRUCTION TO 75% | Nov 2022 | May 2023 | Apr 2028 | Apr 2029
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-151-L | RECONST AERATION TANK GATES/ACTUATOR & SUPPORTS @ PR WRRF | 8 | ORIGINAL EQUIP & FURNISHING | Nov 2022 | May 2023 | Apr 2029 | Jan 2030
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-151-L | RECONST AERATION TANK GATES/ACTUATOR & SUPPORTS @ PR WRRF | 9 | SUBSTANTIAL COMPLETION | Nov 2022 | May 2023 | Jan 2030 | Jul 2030
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-151-L | RECONST AERATION TANK GATES/ACTUATOR & SUPPORTS @ PR WRRF | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2022 | May 2023 | Jul 2030 | Oct 2030
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-287 | RECONSTRUCT ELTINGVILLE PUMPING STATION | 1 | DEVELOP SCOPE | Jul 2016 | Mar 2017 | Jul 2017 | Mar 2018
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-287 | RECONSTRUCT ELTINGVILLE PUMPING STATION | 2 | PRELIMINARY DESIGN | Mar 2017 | Mar 2018 | Mar 2018 | Mar 2019
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-287 | RECONSTRUCT ELTINGVILLE PUMPING STATION | 3 | FINAL DESIGN | Mar 2018 | Sep 2019 | Mar 2019 | Sep 2020
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-287 | RECONSTRUCT ELTINGVILLE PUMPING STATION | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Jun 2020 | Sep 2020 | Jun 2021
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-287 | RECONSTRUCT ELTINGVILLE PUMPING STATION | 5 | CONSTRUCTION TO 25% | Jun 2020 | Jun 2021 | Jun 2021 | Jun 2022
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-287 | RECONSTRUCT ELTINGVILLE PUMPING STATION | 6 | CONSTRUCTION TO 50% | Jun 2021 | May 2022 | Jun 2022 | May 2023
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-287 | RECONSTRUCT ELTINGVILLE PUMPING STATION | 7 | CONSTRUCTION TO 75% | May 2022 | May 2023 | May 2023 | May 2024
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-287 | RECONSTRUCT ELTINGVILLE PUMPING STATION | 8 | ORIGINAL EQUIP & FURNISHING | May 2023 | Feb 2024 | May 2024 | Feb 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-287 | RECONSTRUCT ELTINGVILLE PUMPING STATION | 9 | SUBSTANTIAL COMPLETION | Feb 2024 | Aug 2024 | Feb 2025 | Aug 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-287 | RECONSTRUCT ELTINGVILLE PUMPING STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2024 | Nov 2024 | Aug 2025 | Nov 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-295 | RECONSTRUCTION AT MERSEREAU PUMPING STATION | 1 | DEVELOP SCOPE | Jun 2020 | Feb 2021 | Jul 2018 | Mar 2019
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-295 | RECONSTRUCTION AT MERSEREAU PUMPING STATION | 2 | PRELIMINARY DESIGN | Feb 2021 | Feb 2022 | Mar 2019 | Mar 2020
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-295 | RECONSTRUCTION AT MERSEREAU PUMPING STATION | 3 | FINAL DESIGN | Feb 2022 | Aug 2023 | Mar 2020 | Sep 2021
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-295 | RECONSTRUCTION AT MERSEREAU PUMPING STATION | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2023 | May 2024 | Sep 2021 | Jun 2022
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-295 | RECONSTRUCTION AT MERSEREAU PUMPING STATION | 5 | CONSTRUCTION TO 25% | May 2024 | May 2025 | Jun 2022 | Jun 2023
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-295 | RECONSTRUCTION AT MERSEREAU PUMPING STATION | 6 | CONSTRUCTION TO 50% | May 2025 | Apr 2026 | Jun 2023 | May 2024
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-295 | RECONSTRUCTION AT MERSEREAU PUMPING STATION | 7 | CONSTRUCTION TO 75% | May 2026 | Apr 2027 | May 2024 | May 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-295 | RECONSTRUCTION AT MERSEREAU PUMPING STATION | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2027 | Jan 2028 | May 2025 | Feb 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-295 | RECONSTRUCTION AT MERSEREAU PUMPING STATION | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Jul 2028 | Feb 2026 | Aug 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-295 | RECONSTRUCTION AT MERSEREAU PUMPING STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2028 | Oct 2028 | Aug 2026 | Nov 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-317 | RECONSTRUCT VICTORY BOULEVARD PUMPING STATION STATEN ISLAND | 1 | DEVELOP SCOPE | Jul 2016 | Mar 2017 | Jun 2019 | Feb 2020
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-317 | RECONSTRUCT VICTORY BOULEVARD PUMPING STATION STATEN ISLAND | 2 | PRELIMINARY DESIGN | Mar 2017 | Mar 2018 | Feb 2020 | Feb 2021
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-317 | RECONSTRUCT VICTORY BOULEVARD PUMPING STATION STATEN ISLAND | 3 | FINAL DESIGN | Mar 2018 | Sep 2019 | Feb 2021 | Aug 2022
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-317 | RECONSTRUCT VICTORY BOULEVARD PUMPING STATION STATEN ISLAND | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Jun 2020 | Aug 2022 | May 2023
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-317 | RECONSTRUCT VICTORY BOULEVARD PUMPING STATION STATEN ISLAND | 5 | CONSTRUCTION TO 25% | Jun 2020 | Jun 2021 | May 2023 | May 2024
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-317 | RECONSTRUCT VICTORY BOULEVARD PUMPING STATION STATEN ISLAND | 6 | CONSTRUCTION TO 50% | Jun 2021 | May 2022 | May 2024 | Apr 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-317 | RECONSTRUCT VICTORY BOULEVARD PUMPING STATION STATEN ISLAND | 7 | CONSTRUCTION TO 75% | May 2022 | May 2023 | Apr 2025 | Apr 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-317 | RECONSTRUCT VICTORY BOULEVARD PUMPING STATION STATEN ISLAND | 8 | ORIGINAL EQUIP & FURNISHING | May 2023 | Feb 2024 | Apr 2026 | Jan 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-317 | RECONSTRUCT VICTORY BOULEVARD PUMPING STATION STATEN ISLAND | 9 | SUBSTANTIAL COMPLETION | Feb 2024 | Aug 2024 | Jan 2027 | Jul 2031
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-317 | RECONSTRUCT VICTORY BOULEVARD PUMPING STATION STATEN ISLAND | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2024 | Nov 2024 | Jul 2031 | Oct 2031
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-322 | RECONSTRUCT MAYFLOWER AVENUE PUMPING STATION, STATEN ISLAND | 1 | DEVELOP SCOPE | Jun 2022 | Feb 2023 | Jul 2018 | Mar 2019
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-322 | RECONSTRUCT MAYFLOWER AVENUE PUMPING STATION, STATEN ISLAND | 2 | PRELIMINARY DESIGN | Feb 2023 | Feb 2024 | Mar 2019 | Mar 2020
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-322 | RECONSTRUCT MAYFLOWER AVENUE PUMPING STATION, STATEN ISLAND | 3 | FINAL DESIGN | Feb 2024 | Aug 2025 | Mar 2020 | Sep 2021
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-322 | RECONSTRUCT MAYFLOWER AVENUE PUMPING STATION, STATEN ISLAND | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2025 | May 2026 | Sep 2021 | Jun 2022
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-322 | RECONSTRUCT MAYFLOWER AVENUE PUMPING STATION, STATEN ISLAND | 5 | CONSTRUCTION TO 25% | May 2026 | May 2027 | Jun 2022 | Jun 2023
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-322 | RECONSTRUCT MAYFLOWER AVENUE PUMPING STATION, STATEN ISLAND | 6 | CONSTRUCTION TO 50% | May 2027 | Apr 2028 | Jun 2023 | May 2024
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-322 | RECONSTRUCT MAYFLOWER AVENUE PUMPING STATION, STATEN ISLAND | 7 | CONSTRUCTION TO 75% | Apr 2028 | Apr 2029 | May 2024 | May 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-322 | RECONSTRUCT MAYFLOWER AVENUE PUMPING STATION, STATEN ISLAND | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2029 | Jan 2030 | May 2025 | Feb 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-322 | RECONSTRUCT MAYFLOWER AVENUE PUMPING STATION, STATEN ISLAND | 9 | SUBSTANTIAL COMPLETION | Jan 2030 | Jul 2030 | Feb 2026 | Aug 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-322 | RECONSTRUCT MAYFLOWER AVENUE PUMPING STATION, STATEN ISLAND | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2030 | Oct 2030 | Aug 2026 | Nov 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-323 | RECONSTRUCT RICHMOND AVENUE PUMPING STATION, STATEN ISLAND | 1 | DEVELOP SCOPE | Jun 2022 | Feb 2023 | Jun 2019 | Feb 2020
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-323 | RECONSTRUCT RICHMOND AVENUE PUMPING STATION, STATEN ISLAND | 2 | PRELIMINARY DESIGN | Feb 2023 | Feb 2024 | Feb 2020 | Feb 2021
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-323 | RECONSTRUCT RICHMOND AVENUE PUMPING STATION, STATEN ISLAND | 3 | FINAL DESIGN | Feb 2024 | Aug 2025 | Feb 2021 | Aug 2022
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-323 | RECONSTRUCT RICHMOND AVENUE PUMPING STATION, STATEN ISLAND | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2025 | May 2026 | Aug 2022 | May 2023
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-323 | RECONSTRUCT RICHMOND AVENUE PUMPING STATION, STATEN ISLAND | 5 | CONSTRUCTION TO 25% | May 2026 | May 2027 | May 2023 | May 2024
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-323 | RECONSTRUCT RICHMOND AVENUE PUMPING STATION, STATEN ISLAND | 6 | CONSTRUCTION TO 50% | May 2027 | Apr 2028 | May 2024 | Apr 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-323 | RECONSTRUCT RICHMOND AVENUE PUMPING STATION, STATEN ISLAND | 7 | CONSTRUCTION TO 75% | Apr 2028 | Apr 2029 | Apr 2025 | Apr 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-323 | RECONSTRUCT RICHMOND AVENUE PUMPING STATION, STATEN ISLAND | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2029 | Jan 2030 | Apr 2026 | Jan 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-323 | RECONSTRUCT RICHMOND AVENUE PUMPING STATION, STATEN ISLAND | 9 | SUBSTANTIAL COMPLETION | Jan 2030 | Jul 2030 | Jan 2027 | Jul 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-323 | RECONSTRUCT RICHMOND AVENUE PUMPING STATION, STATEN ISLAND | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2030 | Oct 2030 | Jul 2027 | Oct 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-384 | TRUNK AND DISTRIBUTION WATER MAIN IN FRONT ST, SI | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jan 2025 | Mar 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-384 | TRUNK AND DISTRIBUTION WATER MAIN IN FRONT ST, SI | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Apr 2025 | Jul 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-384 | TRUNK AND DISTRIBUTION WATER MAIN IN FRONT ST, SI | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Jul 2025 | Jan 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-384 | TRUNK AND DISTRIBUTION WATER MAIN IN FRONT ST, SI | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jan 2026 | Apr 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-384 | TRUNK AND DISTRIBUTION WATER MAIN IN FRONT ST, SI | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Apr 2026 | Aug 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-384 | TRUNK AND DISTRIBUTION WATER MAIN IN FRONT ST, SI | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Aug 2026 | Dec 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-384 | TRUNK AND DISTRIBUTION WATER MAIN IN FRONT ST, SI | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | Dec 2026 | Apr 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-384 | TRUNK AND DISTRIBUTION WATER MAIN IN FRONT ST, SI | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Apr 2027 | Jul 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-384 | TRUNK AND DISTRIBUTION WATER MAIN IN FRONT ST, SI | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Jul 2027 | Sep 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-384 | TRUNK AND DISTRIBUTION WATER MAIN IN FRONT ST, SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Sep 2027 | Oct 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED391A | Rplmt Upgrade WM & SE Infra Westervelt Ave Phase A, SI | 1 | DEVELOP SCOPE | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED391A | Rplmt Upgrade WM & SE Infra Westervelt Ave Phase A, SI | 2 | PRELIMINARY DESIGN | Apr 2025 | Jul 2025 | Apr 2025 | Jul 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED391A | Rplmt Upgrade WM & SE Infra Westervelt Ave Phase A, SI | 3 | FINAL DESIGN | Jul 2025 | Jan 2026 | Jul 2025 | Jan 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED391A | Rplmt Upgrade WM & SE Infra Westervelt Ave Phase A, SI | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2026 | Apr 2026 | Jan 2026 | Apr 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED391A | Rplmt Upgrade WM & SE Infra Westervelt Ave Phase A, SI | 5 | CONSTRUCTION TO 25% | Apr 2026 | Aug 2026 | Apr 2026 | Aug 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED391A | Rplmt Upgrade WM & SE Infra Westervelt Ave Phase A, SI | 6 | CONSTRUCTION TO 50% | Aug 2026 | Dec 2026 | Aug 2026 | Dec 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED391A | Rplmt Upgrade WM & SE Infra Westervelt Ave Phase A, SI | 7 | CONSTRUCTION TO 75% | Dec 2026 | Apr 2027 | Dec 2026 | Apr 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED391A | Rplmt Upgrade WM & SE Infra Westervelt Ave Phase A, SI | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2027 | Jul 2027 | Apr 2027 | Jul 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED391A | Rplmt Upgrade WM & SE Infra Westervelt Ave Phase A, SI | 9 | SUBSTANTIAL COMPLETION | Jul 2027 | Sep 2027 | Jul 2027 | Sep 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED391A | Rplmt Upgrade WM & SE Infra Westervelt Ave Phase A, SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Oct 2027 | Sep 2027 | Oct 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-392 | WM rplcmt in Bay St between Slosson Ter & Minthorne St SI | 1 | DEVELOP SCOPE | Nov 2020 | Aug 2021 | Nov 2020 | Aug 2021
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-392 | WM rplcmt in Bay St between Slosson Ter & Minthorne St SI | 2 | PRELIMINARY DESIGN | Aug 2021 | Jul 2022 | Aug 2021 | Jul 2022
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-392 | WM rplcmt in Bay St between Slosson Ter & Minthorne St SI | 3 | FINAL DESIGN | Aug 2022 | Jan 2024 | Aug 2022 | Jan 2024
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-392 | WM rplcmt in Bay St between Slosson Ter & Minthorne St SI | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2024 | Oct 2024 | Jan 2024 | Oct 2024
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-392 | WM rplcmt in Bay St between Slosson Ter & Minthorne St SI | 5 | CONSTRUCTION TO 25% | Oct 2024 | Oct 2025 | Oct 2024 | Oct 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-392 | WM rplcmt in Bay St between Slosson Ter & Minthorne St SI | 6 | CONSTRUCTION TO 50% | Oct 2025 | Oct 2026 | Oct 2025 | Oct 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-392 | WM rplcmt in Bay St between Slosson Ter & Minthorne St SI | 7 | CONSTRUCTION TO 75% | Oct 2026 | Oct 2027 | Oct 2026 | Oct 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-392 | WM rplcmt in Bay St between Slosson Ter & Minthorne St SI | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jun 2028 | Oct 2027 | Jun 2028
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-392 | WM rplcmt in Bay St between Slosson Ter & Minthorne St SI | 9 | SUBSTANTIAL COMPLETION | Jun 2028 | Dec 2028 | Jun 2028 | Dec 2028
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-392 | WM rplcmt in Bay St between Slosson Ter & Minthorne St SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2028 | Mar 2029 | Dec 2028 | Mar 2029
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED393 | Dist WM Rplmt on Hylan Blvd btwn Arbutus Hales Ave, SI | 1 | DEVELOP SCOPE | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED393 | Dist WM Rplmt on Hylan Blvd btwn Arbutus Hales Ave, SI | 2 | PRELIMINARY DESIGN | Apr 2025 | Jul 2025 | Apr 2025 | Jul 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED393 | Dist WM Rplmt on Hylan Blvd btwn Arbutus Hales Ave, SI | 3 | FINAL DESIGN | Jul 2025 | Jan 2026 | Jul 2025 | Jan 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED393 | Dist WM Rplmt on Hylan Blvd btwn Arbutus Hales Ave, SI | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2026 | Apr 2026 | Jan 2026 | Apr 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED393 | Dist WM Rplmt on Hylan Blvd btwn Arbutus Hales Ave, SI | 5 | CONSTRUCTION TO 25% | Apr 2026 | Aug 2026 | Apr 2026 | Aug 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED393 | Dist WM Rplmt on Hylan Blvd btwn Arbutus Hales Ave, SI | 6 | CONSTRUCTION TO 50% | Aug 2026 | Dec 2026 | Aug 2026 | Dec 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED393 | Dist WM Rplmt on Hylan Blvd btwn Arbutus Hales Ave, SI | 7 | CONSTRUCTION TO 75% | Dec 2026 | Apr 2027 | Dec 2026 | Apr 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED393 | Dist WM Rplmt on Hylan Blvd btwn Arbutus Hales Ave, SI | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2027 | Jul 2027 | Apr 2027 | Jul 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED393 | Dist WM Rplmt on Hylan Blvd btwn Arbutus Hales Ave, SI | 9 | SUBSTANTIAL COMPLETION | Jul 2027 | Sep 2027 | Jul 2027 | Sep 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED393 | Dist WM Rplmt on Hylan Blvd btwn Arbutus Hales Ave, SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Oct 2027 | Sep 2027 | Oct 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOB | RECONS OF THE OAKWOOD BEACH WPCP DUE TO HURRICANE SANDY | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jun 2017 | Feb 2018
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOB | RECONS OF THE OAKWOOD BEACH WPCP DUE TO HURRICANE SANDY | 2 | PRELIMINARY DESIGN | Sep 2014 | Jan 2015 | Feb 2018 | Feb 2019
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOB | RECONS OF THE OAKWOOD BEACH WPCP DUE TO HURRICANE SANDY | 3 | FINAL DESIGN | Jan 2015 | Jul 2015 | Feb 2019 | Aug 2020
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOB | RECONS OF THE OAKWOOD BEACH WPCP DUE TO HURRICANE SANDY | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Oct 2015 | Aug 2020 | May 2021
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOB | RECONS OF THE OAKWOOD BEACH WPCP DUE TO HURRICANE SANDY | 5 | CONSTRUCTION TO 25% | Oct 2015 | Feb 2016 | May 2021 | May 2022
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOB | RECONS OF THE OAKWOOD BEACH WPCP DUE TO HURRICANE SANDY | 6 | CONSTRUCTION TO 50% | Feb 2016 | Jun 2016 | May 2022 | Apr 2023
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOB | RECONS OF THE OAKWOOD BEACH WPCP DUE TO HURRICANE SANDY | 7 | CONSTRUCTION TO 75% | Jun 2016 | Oct 2016 | May 2023 | Apr 2024
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOB | RECONS OF THE OAKWOOD BEACH WPCP DUE TO HURRICANE SANDY | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2016 | Jan 2017 | Apr 2024 | Jan 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOB | RECONS OF THE OAKWOOD BEACH WPCP DUE TO HURRICANE SANDY | 9 | SUBSTANTIAL COMPLETION | Jan 2017 | Mar 2017 | Jan 2025 | Jul 2029
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOB | RECONS OF THE OAKWOOD BEACH WPCP DUE TO HURRICANE SANDY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Apr 2017 | Jul 2029 | Oct 2029
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER002331 | Dist WM & San Storm SE Rplmt work in Rice Ave, SI | 1 | DEVELOP SCOPE | Jan 2026 | Mar 2026 | Jun 2024 | Aug 2024
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER002331 | Dist WM & San Storm SE Rplmt work in Rice Ave, SI | 2 | PRELIMINARY DESIGN | Apr 2026 | Jul 2026 | Aug 2024 | Dec 2024
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER002331 | Dist WM & San Storm SE Rplmt work in Rice Ave, SI | 3 | FINAL DESIGN | Jul 2026 | Jan 2027 | Dec 2024 | Jun 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER002331 | Dist WM & San Storm SE Rplmt work in Rice Ave, SI | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2027 | Apr 2027 | Jun 2025 | Sep 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER002331 | Dist WM & San Storm SE Rplmt work in Rice Ave, SI | 5 | CONSTRUCTION TO 25% | Apr 2027 | Aug 2027 | Sep 2025 | Jan 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER002331 | Dist WM & San Storm SE Rplmt work in Rice Ave, SI | 6 | CONSTRUCTION TO 50% | Aug 2027 | Dec 2027 | Jan 2026 | May 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER002331 | Dist WM & San Storm SE Rplmt work in Rice Ave, SI | 7 | CONSTRUCTION TO 75% | Dec 2027 | Apr 2028 | May 2026 | Sep 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER002331 | Dist WM & San Storm SE Rplmt work in Rice Ave, SI | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2028 | Jul 2028 | Sep 2026 | Dec 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER002331 | Dist WM & San Storm SE Rplmt work in Rice Ave, SI | 9 | SUBSTANTIAL COMPLETION | Jul 2028 | Sep 2028 | Dec 2026 | Feb 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER002331 | Dist WM & San Storm SE Rplmt work in Rice Ave, SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2028 | Oct 2028 | Feb 2027 | Mar 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200199 | STRM & SAN SEWER IN LAMOKA AV, LOVELACE AV, GENESSE AV, ETC | 1 | DEVELOP SCOPE | Jan 2025 | Mar 2025 | Aug 2026 | Nov 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200199 | STRM & SAN SEWER IN LAMOKA AV, LOVELACE AV, GENESSE AV, ETC | 2 | PRELIMINARY DESIGN | Apr 2025 | Jul 2025 | Nov 2026 | Mar 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200199 | STRM & SAN SEWER IN LAMOKA AV, LOVELACE AV, GENESSE AV, ETC | 3 | FINAL DESIGN | Jul 2025 | Jan 2026 | Mar 2027 | Sep 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200199 | STRM & SAN SEWER IN LAMOKA AV, LOVELACE AV, GENESSE AV, ETC | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2026 | Apr 2026 | Sep 2027 | Dec 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200199 | STRM & SAN SEWER IN LAMOKA AV, LOVELACE AV, GENESSE AV, ETC | 5 | CONSTRUCTION TO 25% | Apr 2026 | Aug 2026 | Dec 2027 | Apr 2028
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200199 | STRM & SAN SEWER IN LAMOKA AV, LOVELACE AV, GENESSE AV, ETC | 6 | CONSTRUCTION TO 50% | Aug 2026 | Dec 2026 | Apr 2028 | Aug 2028
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200199 | STRM & SAN SEWER IN LAMOKA AV, LOVELACE AV, GENESSE AV, ETC | 7 | CONSTRUCTION TO 75% | Dec 2026 | Apr 2027 | Aug 2028 | Dec 2028
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200199 | STRM & SAN SEWER IN LAMOKA AV, LOVELACE AV, GENESSE AV, ETC | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2027 | Jul 2027 | Dec 2028 | Mar 2029
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200199 | STRM & SAN SEWER IN LAMOKA AV, LOVELACE AV, GENESSE AV, ETC | 9 | SUBSTANTIAL COMPLETION | Jul 2027 | Sep 2027 | Mar 2029 | May 2029
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200199 | STRM & SAN SEWER IN LAMOKA AV, LOVELACE AV, GENESSE AV, ETC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Oct 2027 | May 2029 | Jun 2029
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200256 | Extension & Replacmt of San Sewers in Victory Blvd SI | 1 | DEVELOP SCOPE | Dec 2019 | Sep 2020 | Jan 2021 | Oct 2021
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200256 | Extension & Replacmt of San Sewers in Victory Blvd SI | 2 | PRELIMINARY DESIGN | Sep 2020 | Aug 2021 | Oct 2021 | Oct 2022
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200256 | Extension & Replacmt of San Sewers in Victory Blvd SI | 3 | FINAL DESIGN | Aug 2021 | Feb 2023 | Oct 2022 | Mar 2024
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200256 | Extension & Replacmt of San Sewers in Victory Blvd SI | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2023 | Nov 2023 | Mar 2024 | Dec 2024
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200256 | Extension & Replacmt of San Sewers in Victory Blvd SI | 5 | CONSTRUCTION TO 25% | Nov 2023 | Nov 2024 | Dec 2024 | Dec 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200256 | Extension & Replacmt of San Sewers in Victory Blvd SI | 6 | CONSTRUCTION TO 50% | Nov 2024 | Nov 2025 | Dec 2025 | Dec 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200256 | Extension & Replacmt of San Sewers in Victory Blvd SI | 7 | CONSTRUCTION TO 75% | Nov 2025 | Nov 2026 | Dec 2026 | Dec 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200256 | Extension & Replacmt of San Sewers in Victory Blvd SI | 8 | ORIGINAL EQUIP & FURNISHING | Nov 2026 | Jul 2027 | Dec 2027 | Sep 2028
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200256 | Extension & Replacmt of San Sewers in Victory Blvd SI | 9 | SUBSTANTIAL COMPLETION | Jul 2027 | Jan 2028 | Sep 2028 | Mar 2029
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200256 | Extension & Replacmt of San Sewers in Victory Blvd SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2028 | Apr 2028 | Mar 2029 | Jun 2029
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200265 | Storm SE Ext in Park Dr N btwn Rivington Ave & Plymouth Rd | 1 | DEVELOP SCOPE | Jan 2025 | Mar 2025 | Jun 2023 | Aug 2023
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200265 | Storm SE Ext in Park Dr N btwn Rivington Ave & Plymouth Rd | 2 | PRELIMINARY DESIGN | Apr 2025 | Jul 2025 | Aug 2023 | Dec 2023
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200265 | Storm SE Ext in Park Dr N btwn Rivington Ave & Plymouth Rd | 3 | FINAL DESIGN | Jul 2025 | Jan 2026 | Dec 2023 | Jun 2024
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200265 | Storm SE Ext in Park Dr N btwn Rivington Ave & Plymouth Rd | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2026 | Apr 2026 | Jun 2024 | Sep 2024
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200265 | Storm SE Ext in Park Dr N btwn Rivington Ave & Plymouth Rd | 5 | CONSTRUCTION TO 25% | Apr 2026 | Aug 2026 | Sep 2024 | Jan 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200265 | Storm SE Ext in Park Dr N btwn Rivington Ave & Plymouth Rd | 6 | CONSTRUCTION TO 50% | Aug 2026 | Dec 2026 | Jan 2025 | May 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200265 | Storm SE Ext in Park Dr N btwn Rivington Ave & Plymouth Rd | 7 | CONSTRUCTION TO 75% | Dec 2026 | Apr 2027 | May 2025 | Sep 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200265 | Storm SE Ext in Park Dr N btwn Rivington Ave & Plymouth Rd | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2027 | Jul 2027 | Sep 2025 | Dec 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200265 | Storm SE Ext in Park Dr N btwn Rivington Ave & Plymouth Rd | 9 | SUBSTANTIAL COMPLETION | Jul 2027 | Sep 2027 | Dec 2025 | Feb 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200265 | Storm SE Ext in Park Dr N btwn Rivington Ave & Plymouth Rd | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Oct 2027 | Feb 2026 | Mar 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200319 | New Storm SE in S. Gannon Ave btw Woodward & Warwick Ave, SI | 1 | DEVELOP SCOPE | Aug 2024 | Nov 2024 | Aug 2025 | Nov 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200319 | New Storm SE in S. Gannon Ave btw Woodward & Warwick Ave, SI | 2 | PRELIMINARY DESIGN | Nov 2024 | Mar 2025 | Nov 2025 | Mar 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200319 | New Storm SE in S. Gannon Ave btw Woodward & Warwick Ave, SI | 3 | FINAL DESIGN | Mar 2025 | Sep 2025 | Mar 2026 | Sep 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200319 | New Storm SE in S. Gannon Ave btw Woodward & Warwick Ave, SI | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2025 | Dec 2025 | Sep 2026 | Dec 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200319 | New Storm SE in S. Gannon Ave btw Woodward & Warwick Ave, SI | 5 | CONSTRUCTION TO 25% | Dec 2025 | Apr 2026 | Dec 2026 | Apr 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200319 | New Storm SE in S. Gannon Ave btw Woodward & Warwick Ave, SI | 6 | CONSTRUCTION TO 50% | Apr 2026 | Aug 2026 | Apr 2027 | Aug 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200319 | New Storm SE in S. Gannon Ave btw Woodward & Warwick Ave, SI | 7 | CONSTRUCTION TO 75% | Aug 2026 | Dec 2026 | Aug 2027 | Dec 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200319 | New Storm SE in S. Gannon Ave btw Woodward & Warwick Ave, SI | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2026 | Mar 2027 | Dec 2027 | Mar 2028
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200319 | New Storm SE in S. Gannon Ave btw Woodward & Warwick Ave, SI | 9 | SUBSTANTIAL COMPLETION | Mar 2027 | May 2027 | Mar 2028 | May 2028
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200319 | New Storm SE in S. Gannon Ave btw Woodward & Warwick Ave, SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2027 | Jun 2027 | May 2028 | Jun 2028
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SIBB2-OAK | STATEN ISLAND BLUEBELT - OAKWOOD BEACH | 1 | DEVELOP SCOPE | Jun 2013 | Aug 2013 | Jun 2013 | Aug 2013
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SIBB2-OAK | STATEN ISLAND BLUEBELT - OAKWOOD BEACH | 2 | PRELIMINARY DESIGN | Aug 2013 | Dec 2013 | Aug 2013 | Dec 2013
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SIBB2-OAK | STATEN ISLAND BLUEBELT - OAKWOOD BEACH | 3 | FINAL DESIGN | Dec 2013 | Jun 2014 | Dec 2013 | Jun 2014
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SIBB2-OAK | STATEN ISLAND BLUEBELT - OAKWOOD BEACH | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2014 | Sep 2014 | Jun 2014 | Sep 2014
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SIBB2-OAK | STATEN ISLAND BLUEBELT - OAKWOOD BEACH | 5 | CONSTRUCTION TO 25% | Sep 2014 | Jan 2015 | Sep 2014 | Jan 2015
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SIBB2-OAK | STATEN ISLAND BLUEBELT - OAKWOOD BEACH | 6 | CONSTRUCTION TO 50% | Jan 2015 | May 2015 | Jan 2015 | May 2015
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SIBB2-OAK | STATEN ISLAND BLUEBELT - OAKWOOD BEACH | 7 | CONSTRUCTION TO 75% | May 2015 | Sep 2015 | May 2015 | Sep 2015
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SIBB2-OAK | STATEN ISLAND BLUEBELT - OAKWOOD BEACH | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SIBB2-OAK | STATEN ISLAND BLUEBELT - OAKWOOD BEACH | 9 | SUBSTANTIAL COMPLETION | Dec 2015 | Feb 2016 | Dec 2015 | Feb 2028
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SIBB2-OAK | STATEN ISLAND BLUEBELT - OAKWOOD BEACH | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2016 | Mar 2016 | Feb 2028 | Mar 2028
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SISEAWL-1 | US Army Corps SI Seawall Project | 1 | DEVELOP SCOPE | Jan 2022 | Mar 2022 | Aug 2024 | Nov 2024
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SISEAWL-1 | US Army Corps SI Seawall Project | 2 | PRELIMINARY DESIGN | Apr 2022 | Jul 2022 | Nov 2024 | Mar 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SISEAWL-1 | US Army Corps SI Seawall Project | 3 | FINAL DESIGN | Jul 2022 | Jan 2023 | Mar 2025 | Sep 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SISEAWL-1 | US Army Corps SI Seawall Project | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2023 | Apr 2023 | Sep 2025 | Dec 2025
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SISEAWL-1 | US Army Corps SI Seawall Project | 5 | CONSTRUCTION TO 25% | Apr 2023 | Aug 2023 | Dec 2025 | Apr 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SISEAWL-1 | US Army Corps SI Seawall Project | 6 | CONSTRUCTION TO 50% | Aug 2023 | Dec 2023 | Apr 2026 | Aug 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SISEAWL-1 | US Army Corps SI Seawall Project | 7 | CONSTRUCTION TO 75% | Dec 2023 | Apr 2024 | Aug 2026 | Dec 2026
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SISEAWL-1 | US Army Corps SI Seawall Project | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2024 | Jul 2024 | Dec 2026 | Mar 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SISEAWL-1 | US Army Corps SI Seawall Project | 9 | SUBSTANTIAL COMPLETION | Jul 2024 | Sep 2024 | Mar 2027 | May 2027
20231026 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SISEAWL-1 | US Army Corps SI Seawall Project | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Oct 2024 | May 2027 | Jun 2027
20231026 | RICHMOND | 827 | DEPARTMENT OF SANITATION | APIDSSI02 | DSNY ROADMAP ENERGY EFF | 1 | DEVELOP SCOPE | Feb 2023 | May 2023 | Feb 2023 | May 2023
20231026 | RICHMOND | 827 | DEPARTMENT OF SANITATION | APIDSSI02 | DSNY ROADMAP ENERGY EFF | 2 | PRELIMINARY DESIGN | May 2023 | Nov 2023 | May 2023 | Nov 2023
20231026 | RICHMOND | 827 | DEPARTMENT OF SANITATION | APIDSSI02 | DSNY ROADMAP ENERGY EFF | 3 | FINAL DESIGN | Nov 2023 | May 2024 | Nov 2023 | May 2024
20231026 | RICHMOND | 827 | DEPARTMENT OF SANITATION | APIDSSI02 | DSNY ROADMAP ENERGY EFF | 4 | BID AWARD AND REGISTER CONTRCT | May 2024 | May 2025 | May 2024 | May 2025
20231026 | RICHMOND | 827 | DEPARTMENT OF SANITATION | APIDSSI02 | DSNY ROADMAP ENERGY EFF | 5 | CONSTRUCTION TO 25% | May 2025 | May 2026 | May 2025 | May 2026
20231026 | RICHMOND | 827 | DEPARTMENT OF SANITATION | APIDSSI02 | DSNY ROADMAP ENERGY EFF | 6 | CONSTRUCTION TO 50% | May 2026 | May 2027 | May 2026 | May 2027
20231026 | RICHMOND | 827 | DEPARTMENT OF SANITATION | APIDSSI02 | DSNY ROADMAP ENERGY EFF | 7 | CONSTRUCTION TO 75% | May 2027 | May 2028 | May 2027 | May 2028
20231026 | RICHMOND | 827 | DEPARTMENT OF SANITATION | APIDSSI02 | DSNY ROADMAP ENERGY EFF | 8 | ORIGINAL EQUIP & FURNISHING | May 2028 | Aug 2028 | May 2028 | Aug 2028
20231026 | RICHMOND | 827 | DEPARTMENT OF SANITATION | APIDSSI02 | DSNY ROADMAP ENERGY EFF | 9 | SUBSTANTIAL COMPLETION | Aug 2028 | Aug 2029 | Aug 2028 | Aug 2029
20231026 | RICHMOND | 827 | DEPARTMENT OF SANITATION | APIDSSI02 | DSNY ROADMAP ENERGY EFF | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2029 | Dec 2029 | Aug 2029 | Dec 2029
20231026 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S111-395D | DSNY STATEN ISLAND TRANSFER STATION Scales | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S111-395D | DSNY STATEN ISLAND TRANSFER STATION Scales | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S111-395D | DSNY STATEN ISLAND TRANSFER STATION Scales | 3 | FINAL DESIGN | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S111-395D | DSNY STATEN ISLAND TRANSFER STATION Scales | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2022 | Jun 2022 | Mar 2022 | Jun 2022
20231026 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S111-395D | DSNY STATEN ISLAND TRANSFER STATION Scales | 5 | CONSTRUCTION TO 25% | Jun 2022 | Feb 2023 | Jun 2022 | Feb 2023
20231026 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S111-395D | DSNY STATEN ISLAND TRANSFER STATION Scales | 6 | CONSTRUCTION TO 50% | Feb 2023 | Oct 2023 | Feb 2023 | Oct 2023
20231026 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S111-395D | DSNY STATEN ISLAND TRANSFER STATION Scales | 7 | CONSTRUCTION TO 75% | Oct 2023 | Jun 2024 | Oct 2023 | Jun 2024
20231026 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S111-395D | DSNY STATEN ISLAND TRANSFER STATION Scales | 8 | SUBSTANTIAL COMPLETION | Jun 2024 | Feb 2025 | Jun 2024 | Feb 2025
20231026 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S111-395D | DSNY STATEN ISLAND TRANSFER STATION Scales | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Oct 2025 | Feb 2025 | Oct 2025
20231026 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-367D | Staten Island 1 and 3 Garage Initial Outfitting | 1 | DEVELOP SCOPE | Jun 2021 | Jul 2021 | Jun 2021 | Jul 2021
20231026 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-367D | Staten Island 1 and 3 Garage Initial Outfitting | 2 | PRELIMINARY DESIGN | Jul 2021 | Sep 2021 | Jul 2021 | Sep 2021
20231026 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-367D | Staten Island 1 and 3 Garage Initial Outfitting | 3 | FINAL DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-367D | Staten Island 1 and 3 Garage Initial Outfitting | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2022 | Jun 2022 | Jan 2022 | Jun 2022
20231026 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-367D | Staten Island 1 and 3 Garage Initial Outfitting | 5 | CONSTRUCTION TO 25% | Jun 2022 | Feb 2023 | Jun 2022 | Feb 2023
20231026 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-367D | Staten Island 1 and 3 Garage Initial Outfitting | 6 | CONSTRUCTION TO 50% | Feb 2023 | Oct 2023 | Feb 2023 | Oct 2023
20231026 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-367D | Staten Island 1 and 3 Garage Initial Outfitting | 7 | CONSTRUCTION TO 75% | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-367D | Staten Island 1 and 3 Garage Initial Outfitting | 8 | SUBSTANTIAL COMPLETION | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-367D | Staten Island 1 and 3 Garage Initial Outfitting | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | BOATSANDY | Sandy Ground - Ollis Class Ferryboat Reconstruction | 1 | DEVELOP SCOPE | Jun 2029 | Sep 2029 | Jun 2029 | Sep 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | BOATSANDY | Sandy Ground - Ollis Class Ferryboat Reconstruction | 2 | PRELIMINARY DESIGN | Sep 2029 | Jan 2030 | Sep 2029 | Jan 2030
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | BOATSANDY | Sandy Ground - Ollis Class Ferryboat Reconstruction | 3 | FINAL DESIGN | Jan 2030 | Jul 2030 | Jan 2030 | Jul 2030
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | BOATSANDY | Sandy Ground - Ollis Class Ferryboat Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2030 | Oct 2030 | Jul 2030 | Oct 2030
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | BOATSANDY | Sandy Ground - Ollis Class Ferryboat Reconstruction | 5 | CONSTRUCTION TO 25% | Oct 2030 | Feb 2031 | Oct 2030 | Feb 2031
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | BOATSANDY | Sandy Ground - Ollis Class Ferryboat Reconstruction | 6 | CONSTRUCTION TO 50% | Feb 2031 | Jun 2031 | Feb 2031 | Jun 2031
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | BOATSANDY | Sandy Ground - Ollis Class Ferryboat Reconstruction | 7 | CONSTRUCTION TO 75% | Jun 2031 | Oct 2031 | Jun 2031 | Oct 2031
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | BOATSANDY | Sandy Ground - Ollis Class Ferryboat Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2031 | Jan 2032 | Oct 2031 | Jan 2032
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | BOATSANDY | Sandy Ground - Ollis Class Ferryboat Reconstruction | 9 | SUBSTANTIAL COMPLETION | Jan 2032 | Mar 2032 | Jan 2032 | Mar 2032
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | BOATSANDY | Sandy Ground - Ollis Class Ferryboat Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2032 | Apr 2032 | Mar 2032 | Apr 2032
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | C5517B | DOCKBUILDING HARDWOOD TIMBER | 1 | DEVELOP SCOPE | Jul 2009 | Jun 2010 | Jul 2009 | Jun 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | C5517B | DOCKBUILDING HARDWOOD TIMBER | 2 | DESIGN START | Jul 2010 | Jun 2012 | Jul 2025 | Jun 2027
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | C5517B | DOCKBUILDING HARDWOOD TIMBER | 3 | CONSTRUCTION START | Jun 2012 | Jun 2014 | Jul 2027 | Jun 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | C5588 | REPLACEMENT OF OIL BARGE #5 | 1 | DEVELOP SCOPE | Jun 2009 | May 2010 | Jun 2019 | Jun 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | C5588 | REPLACEMENT OF OIL BARGE #5 | 2 | DESIGN START | Jun 2010 | May 2012 | Jun 2027 | Jul 2027
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | C5588 | REPLACEMENT OF OIL BARGE #5 | 3 | CONSTRUCTION START | May 2012 | May 2014 | Jul 2027 | Jul 2030
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | C5590 | DRYDOCK MOLINARI FERRY BOATS | 1 | DEVELOP SCOPE | Jun 2004 | May 2005 | Jun 2022 | May 2023
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | C5590 | DRYDOCK MOLINARI FERRY BOATS | 2 | DESIGN START | Jun 2005 | May 2007 | Jun 2023 | May 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | C5590 | DRYDOCK MOLINARI FERRY BOATS | 3 | CONSTRUCTION START | Jun 2007 | May 2009 | May 2025 | May 2027
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FABLDG45R | Building 45 Rehabilitation | 1 | DEVELOP SCOPE | Jun 2016 | Jun 2017 | Sep 2022 | Jun 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FABLDG45R | Building 45 Rehabilitation | 2 | DESIGN START | Jun 2017 | Jun 2019 | Jun 2024 | Jun 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FABLDG45R | Building 45 Rehabilitation | 3 | CONSTRUCTION START | Jun 2019 | Jun 2021 | Jun 2026 | Jun 2028
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FABOLLIS | Drydock and Reconstruction of Ollis Class Ferryboats | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FABOLLIS | Drydock and Reconstruction of Ollis Class Ferryboats | 2 | DESIGN START | Jun 2022 | Jun 2024 | Jun 2022 | Jun 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FABOLLIS | Drydock and Reconstruction of Ollis Class Ferryboats | 3 | CONSTRUCTION START | Jun 2024 | Jun 2026 | Jun 2024 | Jun 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FASEAWALL | Ferry Maintenance Facility Seawall PinX823.78 | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2021 | Jun 2020 | Jun 2021
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FASEAWALL | Ferry Maintenance Facility Seawall PinX823.78 | 2 | DESIGN START | Jun 2021 | Jun 2023 | Jun 2021 | Jun 2023
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FASEAWALL | Ferry Maintenance Facility Seawall PinX823.78 | 3 | CONSTRUCTION START | Jun 2023 | Jun 2025 | Jun 2023 | Jun 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FASGTRCN | St.George Ferry Terminal Waterfront Remediation | 1 | DEVELOP SCOPE | Jun 2018 | Jun 2019 | Jun 2021 | Jun 2022
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FASGTRCN | St.George Ferry Terminal Waterfront Remediation | 2 | DESIGN START | Jun 2019 | Jun 2021 | Jun 2022 | Jun 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FASGTRCN | St.George Ferry Terminal Waterfront Remediation | 3 | CONSTRUCTION START | Jun 2021 | Jun 2023 | Jun 2024 | Jun 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FASGTRHB | SGT Terminal Brick Facade Rehabilitation | 1 | DEVELOP SCOPE | Jun 2018 | Jun 2019 | Jun 2021 | Jun 2022
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FASGTRHB | SGT Terminal Brick Facade Rehabilitation | 2 | DESIGN START | Jun 2019 | Jun 2021 | Jun 2022 | Jun 2028
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FASGTRHB | SGT Terminal Brick Facade Rehabilitation | 3 | CONSTRUCTION START | Jun 2021 | Jun 2023 | Jul 2028 | Jun 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FASTGCCTV | STG Terminal CCTV Upgrade | 1 | DEVELOP SCOPE | Jun 2017 | Jun 2018 | Jun 2025 | Jun 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FASTGCCTV | STG Terminal CCTV Upgrade | 2 | DESIGN START | Jun 2018 | Jun 2020 | Jun 2026 | Jun 2028
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FASTGCCTV | STG Terminal CCTV Upgrade | 3 | CONSTRUCTION START | Jun 2020 | Jun 2022 | Jun 2028 | Jun 2030
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FAUREABRG | SIF Diesel Exhaust Fluid (DEF) Storage & Distribution | 1 | DEVELOP SCOPE | Jun 2018 | Jun 2019 | Jun 2023 | Jun 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FAUREABRG | SIF Diesel Exhaust Fluid (DEF) Storage & Distribution | 2 | DESIGN START | Jun 2019 | Jun 2021 | Jun 2024 | Jun 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FAUREABRG | SIF Diesel Exhaust Fluid (DEF) Storage & Distribution | 3 | CONSTRUCTION START | Jun 2021 | Jun 2023 | Jun 2026 | Jun 2028
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FBENVCOM | Ferryboat Environmental Compliance Upgrades | 1 | DEVELOP SCOPE | Jul 2016 | Jun 2017 | Jul 2025 | Jun 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FBENVCOM | Ferryboat Environmental Compliance Upgrades | 2 | DESIGN START | Jul 2017 | Jun 2019 | Jul 2026 | Jun 2027
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FBENVCOM | Ferryboat Environmental Compliance Upgrades | 3 | CONSTRUCTION START | Jul 2019 | Jun 2021 | Jul 2021 | Jun 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FERRYR1SG | Construction of Ferryrack at Slip1, St. George Terminal | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2021 | Jun 2026 | Jun 2027
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FERRYR1SG | Construction of Ferryrack at Slip1, St. George Terminal | 2 | DESIGN START | Jun 2021 | Jun 2023 | Jun 2027 | Jun 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FERRYR1SG | Construction of Ferryrack at Slip1, St. George Terminal | 3 | CONSTRUCTION START | Jun 2023 | Jun 2025 | Jun 2029 | Jun 2031
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FERRYR3SG | Construction of Ferryrack at Slip3, St. George Terminal | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2021 | Jun 2022 | Jun 2023
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FERRYR3SG | Construction of Ferryrack at Slip3, St. George Terminal | 2 | DESIGN START | Jun 2021 | Jun 2023 | Jun 2023 | Jun 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FERRYR3SG | Construction of Ferryrack at Slip3, St. George Terminal | 3 | CONSTRUCTION START | Jun 2023 | Jun 2025 | Jun 2025 | Jun 2027
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FERRYRACK | CONSTRUCTION OF FERRY RACK | 1 | DEVELOP SCOPE | Oct 2007 | Sep 2008 | Oct 2023 | Sep 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FERRYRACK | CONSTRUCTION OF FERRY RACK | 2 | DESIGN START | Sep 2008 | Sep 2010 | Sep 2024 | Sep 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FERRYRACK | CONSTRUCTION OF FERRY RACK | 3 | CONSTRUCTION START | Sep 2010 | Sep 2012 | Sep 2026 | Sep 2028
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FMFVARNR | FMF Vehicle Access Ramps and Nose Upgrade | 1 | DEVELOP SCOPE | Jun 2016 | Jun 2017 | Jun 2020 | Jun 2021
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FMFVARNR | FMF Vehicle Access Ramps and Nose Upgrade | 2 | DESIGN START | Jun 2017 | Jun 2019 | Jun 2021 | Jun 2023
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FMFVARNR | FMF Vehicle Access Ramps and Nose Upgrade | 3 | CONSTRUCTION START | Jun 2019 | Jun 2021 | Jun 2023 | Jun 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FVESSGANR | Facility/Vessel Gangways Replacement/Upgrade | 1 | DEVELOP SCOPE | Jun 2017 | Jun 2018 | Jun 2028 | Jul 2028
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FVESSGANR | Facility/Vessel Gangways Replacement/Upgrade | 2 | DESIGN START | Jun 2018 | Jun 2020 | Jun 2029 | Jul 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FVESSGANR | Facility/Vessel Gangways Replacement/Upgrade | 3 | CONSTRUCTION START | Jun 2020 | Jun 2022 | Jul 2029 | Jul 2030
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBR249730 | BR OVER DAM OVER NORTH END CLOVE LAKE BIN 2249730 | 1 | DEVELOP SCOPE | Jun 2017 | Jun 2018
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBR249730 | BR OVER DAM OVER NORTH END CLOVE LAKE BIN 2249730 | 2 | DESIGN START | Jun 2018 | Jun 2022 | Jun 2017 | Jun 2018
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBR249730 | BR OVER DAM OVER NORTH END CLOVE LAKE BIN 2249730 | 3 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Jun 2018 | Jun 2022
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBR249730 | BR OVER DAM OVER NORTH END CLOVE LAKE BIN 2249730 | 5 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Jun 2022 | Jun 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24939 | CEDARVIEW AVE PED BRIDGE BIN: 2249390 | 1 | DEVELOP SCOPE | Jun 2018 | Jun 2019
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24939 | CEDARVIEW AVE PED BRIDGE BIN: 2249390 | 2 | DESIGN START | Jun 2019 | Jun 2023 | Oct 2021 | Feb 2022
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24939 | CEDARVIEW AVE PED BRIDGE BIN: 2249390 | 3 | CONSTRUCTION START | Jun 2023 | Jun 2025 | Nov 2017 | Feb 2022
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24939 | CEDARVIEW AVE PED BRIDGE BIN: 2249390 | 5 | CONSTRUCTION START | Jun 2023 | Jun 2025 | Jan 2013 | Apr 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24982 | ARTHUR KILL RD/ ARTHUR KILL STREAM BIN#2249820 | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24982 | ARTHUR KILL RD/ ARTHUR KILL STREAM BIN#2249820 | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24982 | ARTHUR KILL RD/ ARTHUR KILL STREAM BIN#2249820 | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24982 | ARTHUR KILL RD/ ARTHUR KILL STREAM BIN#2249820 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24982 | ARTHUR KILL RD/ ARTHUR KILL STREAM BIN#2249820 | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24982 | ARTHUR KILL RD/ ARTHUR KILL STREAM BIN#2249820 | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24982 | ARTHUR KILL RD/ ARTHUR KILL STREAM BIN#2249820 | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24982 | ARTHUR KILL RD/ ARTHUR KILL STREAM BIN#2249820 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24982 | ARTHUR KILL RD/ ARTHUR KILL STREAM BIN#2249820 | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24982 | ARTHUR KILL RD/ ARTHUR KILL STREAM BIN#2249820 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRSGFT17 | ARMAJANI STRUCTURE | 1 | DEVELOP SCOPE | Jun 2017 | Jun 2018
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRSGFT17 | ARMAJANI STRUCTURE | 2 | DESIGN START | Jun 2018 | Jun 2022 | Jun 2017 | Jun 2018
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRSGFT17 | ARMAJANI STRUCTURE | 3 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Jun 2018 | Jun 2019
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRSGFT17 | ARMAJANI STRUCTURE | 5 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Jun 2019 | Jun 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-07 | North Bridge Street/South Bridge Street - Construction | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2024 | Sep 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-07 | North Bridge Street/South Bridge Street - Construction | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2024 | Jan 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-07 | North Bridge Street/South Bridge Street - Construction | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2025 | Jul 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-07 | North Bridge Street/South Bridge Street - Construction | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2025 | Oct 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-07 | North Bridge Street/South Bridge Street - Construction | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2025 | Feb 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-07 | North Bridge Street/South Bridge Street - Construction | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2026 | Jun 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-07 | North Bridge Street/South Bridge Street - Construction | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2026 | Oct 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-07 | North Bridge Street/South Bridge Street - Construction | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2026 | Jan 2027
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-07 | North Bridge Street/South Bridge Street - Construction | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2027 | Mar 2027
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-07 | North Bridge Street/South Bridge Street - Construction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2027 | Apr 2031
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-08 | Victory CPI | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2022 | Sep 2022
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-08 | Victory CPI | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2022 | Jan 2023
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-08 | Victory CPI | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2023 | Jul 2023
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-08 | Victory CPI | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2023 | Oct 2023
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-08 | Victory CPI | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2023 | Feb 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-08 | Victory CPI | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2024 | Jun 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-08 | Victory CPI | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2024 | Oct 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-08 | Victory CPI | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2024 | Jan 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-08 | Victory CPI | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2025 | Mar 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-08 | Victory CPI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2025 | Jul 2031
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-09 | Pleasant Plains Park and Ride | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2028 | Sep 2028
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-09 | Pleasant Plains Park and Ride | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2028 | Jan 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-09 | Pleasant Plains Park and Ride | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2029 | Jul 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-09 | Pleasant Plains Park and Ride | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2029 | Oct 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-09 | Pleasant Plains Park and Ride | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2029 | Feb 2030
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-09 | Pleasant Plains Park and Ride | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2030 | Jun 2030
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-09 | Pleasant Plains Park and Ride | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2030 | Oct 2030
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-09 | Pleasant Plains Park and Ride | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2030 | Jan 2031
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-09 | Pleasant Plains Park and Ride | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2031 | Mar 2031
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-09 | Pleasant Plains Park and Ride | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2031 | Apr 2031
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-10 | Sidewalks along Forest Hill Rd btw Ashworth and Ballfield | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2028 | Sep 2028
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-10 | Sidewalks along Forest Hill Rd btw Ashworth and Ballfield | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2028 | Jan 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-10 | Sidewalks along Forest Hill Rd btw Ashworth and Ballfield | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2029 | Jul 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-10 | Sidewalks along Forest Hill Rd btw Ashworth and Ballfield | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2029 | Oct 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-10 | Sidewalks along Forest Hill Rd btw Ashworth and Ballfield | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2029 | Feb 2030
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-10 | Sidewalks along Forest Hill Rd btw Ashworth and Ballfield | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2030 | Jun 2030
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-10 | Sidewalks along Forest Hill Rd btw Ashworth and Ballfield | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2030 | Oct 2030
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-10 | Sidewalks along Forest Hill Rd btw Ashworth and Ballfield | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2030 | Jan 2031
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-10 | Sidewalks along Forest Hill Rd btw Ashworth and Ballfield | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2031 | Mar 2031
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-10 | Sidewalks along Forest Hill Rd btw Ashworth and Ballfield | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2031 | Apr 2031
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-11 | Christopher Lane Extension | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2024 | Sep 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-11 | Christopher Lane Extension | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2024 | Jan 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-11 | Christopher Lane Extension | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2025 | Jul 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-11 | Christopher Lane Extension | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2025 | Oct 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-11 | Christopher Lane Extension | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2025 | Feb 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-11 | Christopher Lane Extension | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2026 | Jun 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-11 | Christopher Lane Extension | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2026 | Oct 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-11 | Christopher Lane Extension | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2026 | Jan 2027
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-11 | Christopher Lane Extension | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2027 | Mar 2027
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-11 | Christopher Lane Extension | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2027 | Apr 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR00513 | Street Widening in the 50th Council District | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2027 | Sep 2027
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR00513 | Street Widening in the 50th Council District | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2027 | Jan 2028
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR00513 | Street Widening in the 50th Council District | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2028 | Jul 2028
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR00513 | Street Widening in the 50th Council District | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2028 | Oct 2028
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR00513 | Street Widening in the 50th Council District | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2028 | Feb 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR00513 | Street Widening in the 50th Council District | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2029 | Jun 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR00513 | Street Widening in the 50th Council District | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2029 | Oct 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR00513 | Street Widening in the 50th Council District | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2029 | Jan 2030
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR00513 | Street Widening in the 50th Council District | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2030 | Mar 2030
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR00513 | Street Widening in the 50th Council District | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2030 | Apr 2030
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR705 | Clove Road and Howard Avenue Re-alignment | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2023 | Sep 2023
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR705 | Clove Road and Howard Avenue Re-alignment | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2023 | Jan 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR705 | Clove Road and Howard Avenue Re-alignment | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2024 | Jul 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR705 | Clove Road and Howard Avenue Re-alignment | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2024 | Oct 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR705 | Clove Road and Howard Avenue Re-alignment | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2024 | Feb 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR705 | Clove Road and Howard Avenue Re-alignment | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2025 | Jun 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR705 | Clove Road and Howard Avenue Re-alignment | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2025 | Oct 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR705 | Clove Road and Howard Avenue Re-alignment | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2029 | Jan 2030
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR705 | Clove Road and Howard Avenue Re-alignment | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2030 | Mar 2030
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR705 | Clove Road and Howard Avenue Re-alignment | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2030 | Apr 2030
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR706 | Forest Hill Sidewalk Improvements | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2023 | Sep 2023
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR706 | Forest Hill Sidewalk Improvements | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2023 | Jan 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR706 | Forest Hill Sidewalk Improvements | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2024 | Jul 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR706 | Forest Hill Sidewalk Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2024 | Oct 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR706 | Forest Hill Sidewalk Improvements | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2024 | Feb 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR706 | Forest Hill Sidewalk Improvements | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2025 | Jun 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR706 | Forest Hill Sidewalk Improvements | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2025 | Oct 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR706 | Forest Hill Sidewalk Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2025 | Jan 2028
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR706 | Forest Hill Sidewalk Improvements | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2028 | Mar 2028
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR706 | Forest Hill Sidewalk Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2028 | Apr 2030
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR707 | South Gannon Avenue Reconstruction | 1 | DEVELOP SCOPE | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR707 | South Gannon Avenue Reconstruction | 2 | PRELIMINARY DESIGN | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR707 | South Gannon Avenue Reconstruction | 3 | FINAL DESIGN | Jan 2026 | Jul 2026 | Jan 2026 | Jul 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR707 | South Gannon Avenue Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2026 | Oct 2026 | Jul 2026 | Oct 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR707 | South Gannon Avenue Reconstruction | 5 | CONSTRUCTION TO 25% | Oct 2026 | Feb 2027 | Oct 2026 | Feb 2027
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR707 | South Gannon Avenue Reconstruction | 6 | CONSTRUCTION TO 50% | Feb 2027 | Jun 2027 | Feb 2027 | Jun 2027
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR707 | South Gannon Avenue Reconstruction | 7 | CONSTRUCTION TO 75% | Jun 2027 | Oct 2027 | Jun 2027 | Oct 2027
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR707 | South Gannon Avenue Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jan 2028 | Oct 2027 | Jan 2028
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR707 | South Gannon Avenue Reconstruction | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Mar 2028 | Jan 2028 | Mar 2028
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR707 | South Gannon Avenue Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2028 | Apr 2028 | Mar 2028 | Apr 2028
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR708 | Manee Avenue Reconstruction | 1 | DEVELOP SCOPE | Jun 2026 | Sep 2026 | Jun 2028 | Sep 2028
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR708 | Manee Avenue Reconstruction | 2 | PRELIMINARY DESIGN | Sep 2026 | Jan 2027 | Sep 2028 | Jan 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR708 | Manee Avenue Reconstruction | 3 | FINAL DESIGN | Jan 2027 | Jul 2027 | Jan 2029 | Jul 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR708 | Manee Avenue Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2027 | Oct 2027 | Jul 2029 | Oct 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR708 | Manee Avenue Reconstruction | 5 | CONSTRUCTION TO 25% | Oct 2027 | Feb 2028 | Oct 2029 | Feb 2030
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR708 | Manee Avenue Reconstruction | 6 | CONSTRUCTION TO 50% | Feb 2028 | Jun 2028 | Feb 2030 | Jun 2030
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR708 | Manee Avenue Reconstruction | 7 | CONSTRUCTION TO 75% | Jun 2028 | Oct 2028 | Jun 2030 | Oct 2030
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR708 | Manee Avenue Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2028 | Jan 2029 | Oct 2030 | Jan 2031
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR708 | Manee Avenue Reconstruction | 9 | SUBSTANTIAL COMPLETION | Jan 2029 | Mar 2029 | Jan 2031 | Mar 2031
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR708 | Manee Avenue Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2029 | Apr 2029 | Mar 2031 | Apr 2031
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR709 | Roma Avenue Reconstruction | 1 | DEVELOP SCOPE | Jun 2025 | Sep 2025 | Jun 2028 | Sep 2028
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR709 | Roma Avenue Reconstruction | 2 | PRELIMINARY DESIGN | Sep 2025 | Jan 2026 | Sep 2028 | Jan 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR709 | Roma Avenue Reconstruction | 3 | FINAL DESIGN | Jan 2026 | Jul 2026 | Jan 2029 | Jul 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR709 | Roma Avenue Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2026 | Oct 2026 | Jul 2029 | Oct 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR709 | Roma Avenue Reconstruction | 5 | CONSTRUCTION TO 25% | Oct 2026 | Feb 2027 | Oct 2029 | Feb 2030
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR709 | Roma Avenue Reconstruction | 6 | CONSTRUCTION TO 50% | Feb 2027 | Jun 2027 | Feb 2030 | Jun 2030
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR709 | Roma Avenue Reconstruction | 7 | CONSTRUCTION TO 75% | Jun 2027 | Oct 2027 | Jun 2030 | Oct 2030
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR709 | Roma Avenue Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jan 2028 | Oct 2030 | Jan 2031
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR709 | Roma Avenue Reconstruction | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Mar 2028 | Jan 2031 | Mar 2031
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR709 | Roma Avenue Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2028 | Apr 2028 | Mar 2031 | Apr 2031
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR72017 | Richmond Ave Ped Safety | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jun 2021 | Sep 2021
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR72017 | Richmond Ave Ped Safety | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Sep 2021 | Jan 2022
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR72017 | Richmond Ave Ped Safety | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2022 | Jul 2022
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR72017 | Richmond Ave Ped Safety | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2022 | Oct 2022
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR72017 | Richmond Ave Ped Safety | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2022 | Feb 2023
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR72017 | Richmond Ave Ped Safety | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2023 | Jun 2023
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR72017 | Richmond Ave Ped Safety | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2023 | Oct 2023
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR72017 | Richmond Ave Ped Safety | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2023 | Jan 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR72017 | Richmond Ave Ped Safety | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2024 | Mar 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR72017 | Richmond Ave Ped Safety | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2024 | Jul 2030
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR920 | Huguenot Park N Ride | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jun 2022 | Sep 2022
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR920 | Huguenot Park N Ride | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Sep 2022 | Jan 2023
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR920 | Huguenot Park N Ride | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2023 | Jul 2023
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR920 | Huguenot Park N Ride | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2023 | Oct 2023
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR920 | Huguenot Park N Ride | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2023 | Feb 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR920 | Huguenot Park N Ride | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2024 | Jun 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR920 | Huguenot Park N Ride | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2024 | Oct 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR920 | Huguenot Park N Ride | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2024 | Jan 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR920 | Huguenot Park N Ride | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2025 | Mar 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR920 | Huguenot Park N Ride | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2025 | Jun 2030
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR921 | Mid Island Blue Belt Street Reconstruction | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2027 | Sep 2027
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR921 | Mid Island Blue Belt Street Reconstruction | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2027 | Jan 2028
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR921 | Mid Island Blue Belt Street Reconstruction | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2028 | Jul 2028
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR921 | Mid Island Blue Belt Street Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2028 | Oct 2028
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR921 | Mid Island Blue Belt Street Reconstruction | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2028 | Feb 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR921 | Mid Island Blue Belt Street Reconstruction | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2029 | Jun 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR921 | Mid Island Blue Belt Street Reconstruction | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2029 | Oct 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR921 | Mid Island Blue Belt Street Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2029 | Jan 2030
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR921 | Mid Island Blue Belt Street Reconstruction | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2030 | Mar 2030
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR921 | Mid Island Blue Belt Street Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2030 | Apr 2030
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWRBENTWF | Bentley Street End Waterfront | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWRBENTWF | Bentley Street End Waterfront | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWRBENTWF | Bentley Street End Waterfront | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWRBENTWF | Bentley Street End Waterfront | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWRBENTWF | Bentley Street End Waterfront | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWRBENTWF | Bentley Street End Waterfront | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWRBENTWF | Bentley Street End Waterfront | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWRBENTWF | Bentley Street End Waterfront | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWRBENTWF | Bentley Street End Waterfront | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWRBENTWF | Bentley Street End Waterfront | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWRFRTWF | Richmond Yard Area Waterfront Structures | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWRFRTWF | Richmond Yard Area Waterfront Structures | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWRFRTWF | Richmond Yard Area Waterfront Structures | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWRFRTWF | Richmond Yard Area Waterfront Structures | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWRFRTWF | Richmond Yard Area Waterfront Structures | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWRFRTWF | Richmond Yard Area Waterfront Structures | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWRFRTWF | Richmond Yard Area Waterfront Structures | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWRFRTWF | Richmond Yard Area Waterfront Structures | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWRFRTWF | Richmond Yard Area Waterfront Structures | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWRFRTWF | Richmond Yard Area Waterfront Structures | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024R | Prior Notice Sidewalks - Staten Island | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2024 | Sep 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024R | Prior Notice Sidewalks - Staten Island | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2024 | Jan 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024R | Prior Notice Sidewalks - Staten Island | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2025 | Jul 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024R | Prior Notice Sidewalks - Staten Island | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2025 | Oct 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024R | Prior Notice Sidewalks - Staten Island | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2025 | Feb 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024R | Prior Notice Sidewalks - Staten Island | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2026 | Jun 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024R | Prior Notice Sidewalks - Staten Island | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2026 | Oct 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024R | Prior Notice Sidewalks - Staten Island | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2026 | Jan 2027
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024R | Prior Notice Sidewalks - Staten Island | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2027 | Mar 2027
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024R | Prior Notice Sidewalks - Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2027 | Apr 2027
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWSCD50 | Sidewalk Construction in Council District 50 | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2025 | Sep 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWSCD50 | Sidewalk Construction in Council District 50 | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2025 | Jan 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWSCD50 | Sidewalk Construction in Council District 50 | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2026 | Jul 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWSCD50 | Sidewalk Construction in Council District 50 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2026 | Oct 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWSCD50 | Sidewalk Construction in Council District 50 | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2026 | Feb 2027
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWSCD50 | Sidewalk Construction in Council District 50 | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2027 | Jun 2027
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWSCD50 | Sidewalk Construction in Council District 50 | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2027 | Oct 2027
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWSCD50 | Sidewalk Construction in Council District 50 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2027 | Jan 2028
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWSCD50 | Sidewalk Construction in Council District 50 | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2028 | Mar 2028
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWSCD50 | Sidewalk Construction in Council District 50 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2028 | Apr 2028
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | ITSKOREAN | Intelligent Transportation Systems on Korean Vet Pky X501.65 | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Jun 2018 | Jun 2024 | Jun 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | ITSKOREAN | Intelligent Transportation Systems on Korean Vet Pky X501.65 | 2 | CONSTRUCTION START | Jul 2018 | Aug 2018 | Jul 2024 | Aug 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | ITSKOREAN | Intelligent Transportation Systems on Korean Vet Pky X501.65 | 3 | CONSTRUCTION COMPLETION | Aug 2018 | Mar 2020 | Aug 2024 | Mar 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | NDF-BSRTP | NDF - Real Time Passenger Information Bay Street | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | NDF-BSRTP | NDF - Real Time Passenger Information Bay Street | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | NDF-BSRTP | NDF - Real Time Passenger Information Bay Street | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | NDF-BSRTP | NDF - Real Time Passenger Information Bay Street | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | NDF-BSRTP | NDF - Real Time Passenger Information Bay Street | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | NDF-BSRTP | NDF - Real Time Passenger Information Bay Street | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | NDF-BSRTP | NDF - Real Time Passenger Information Bay Street | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | NDF-BSRTP | NDF - Real Time Passenger Information Bay Street | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | NDF-BSRTP | NDF - Real Time Passenger Information Bay Street | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | NDF-BSRTP | NDF - Real Time Passenger Information Bay Street | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | PIER1WHAR | FMF Pier1 & Adjacent Wharves Reconstruction | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2024 | Jun 2023 | Jun 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | PIER1WHAR | FMF Pier1 & Adjacent Wharves Reconstruction | 2 | DESIGN START | Jun 2024 | Jun 2026 | Jun 2024 | Jun 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | PIER1WHAR | FMF Pier1 & Adjacent Wharves Reconstruction | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | PIER2WHAR | FMF Pier2 & Adjacent Wharves Reconstruction | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2024 | Jun 2023 | Jun 2024
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | PIER2WHAR | FMF Pier2 & Adjacent Wharves Reconstruction | 2 | DESIGN START | Jun 2024 | Jun 2026 | Jun 2024 | Jun 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | PIER2WHAR | FMF Pier2 & Adjacent Wharves Reconstruction | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF09 | FMF Emergency Generator Installation | 1 | DEVELOP SCOPE | Jul 2016 | Sep 2016 | Jul 2028 | Sep 2028
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF09 | FMF Emergency Generator Installation | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Sep 2028 | Jan 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF09 | FMF Emergency Generator Installation | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Jan 2029 | Jul 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF09 | FMF Emergency Generator Installation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Jan 2019 | Apr 2019
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF09 | FMF Emergency Generator Installation | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Apr 2019 | Aug 2019
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF09 | FMF Emergency Generator Installation | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Aug 2019 | Dec 2019
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF09 | FMF Emergency Generator Installation | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Dec 2019 | Apr 2020
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF09 | FMF Emergency Generator Installation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | May 2019 | Aug 2019
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF09 | FMF Emergency Generator Installation | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Jul 2020 | Sep 2020
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF09 | FMF Emergency Generator Installation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Sep 2020 | Jul 2031
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDSIFMF | Whitehall Ferry Terminal Roof Replacement | 1 | DEVELOP SCOPE | Jun 2013 | Jun 2014 | Jun 2024 | Jun 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDSIFMF | Whitehall Ferry Terminal Roof Replacement | 2 | DESIGN START | Jun 2014 | Jun 2016 | Jun 2025 | Jun 2027
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDSIFMF | Whitehall Ferry Terminal Roof Replacement | 3 | CONSTRUCTION START | Jun 2016 | Jun 2018 | Jun 2027 | Jun 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | STGTELPAN | St. George Terminal Electrical Panel Upgrade | 1 | DEVELOP SCOPE | Jun 2016 | May 2017 | Jun 2026 | Jul 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | STGTELPAN | St. George Terminal Electrical Panel Upgrade | 2 | DESIGN START | Jun 2017 | May 2019 | Aug 2026 | Jul 2028
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | STGTELPAN | St. George Terminal Electrical Panel Upgrade | 3 | CONSTRUCTION START | Jun 2019 | May 2021 | Jul 2028 | Jul 2031
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | STGTROOF | Reconstruction of St.George Terminal Roof | 1 | DEVELOP SCOPE | Jun 2016 | May 2017 | Jun 2024 | May 2025
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | STGTROOF | Reconstruction of St.George Terminal Roof | 2 | DESIGN START | Jun 2017 | May 2019 | Jun 2025 | May 2026
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | STGTROOF | Reconstruction of St.George Terminal Roof | 3 | CONSTRUCTION START | Jun 2019 | May 2021 | May 2027 | May 2032
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | STGWIRERP | ST. GEORGE FERRY SLIPS WIRE ROPES, X823.66 | 1 | DEVELOP SCOPE | Jun 2014 | Jun 2015 | Jun 2019 | Jun 2020
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | STGWIRERP | ST. GEORGE FERRY SLIPS WIRE ROPES, X823.66 | 2 | DESIGN START | Jun 2015 | Jun 2017 | Jun 2020 | Jun 2021
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | STGWIRERP | ST. GEORGE FERRY SLIPS WIRE ROPES, X823.66 | 3 | CONSTRUCTION START | Jun 2017 | Jun 2019 | Jun 2021 | Jun 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | TFD503-07 | GREAT KILLS MUNICIPAL PARKING LOT LIGHTING | 1 | BID AWARD AND REGISTER CONTRCT | May 2005 | May 2005 | May 2029 | May 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | TFD503-07 | GREAT KILLS MUNICIPAL PARKING LOT LIGHTING | 2 | CONSTRUCTION START | May 2005 | Jun 2005 | May 2029 | Jun 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | TFD503-07 | GREAT KILLS MUNICIPAL PARKING LOT LIGHTING | 3 | CONSTRUCTION COMPLETION | Jun 2005 | Jan 2007 | Jun 2028 | Jun 2029
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | TFR0103 | Smart Lights-various locations Staten Island | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2013 | Jun 2013 | Jun 2023 | Jun 2023
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | TFR0103 | Smart Lights-various locations Staten Island | 2 | CONSTRUCTION START | Jul 2013 | Aug 2013 | Jul 2023 | Aug 2023
20231026 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | TFR0103 | Smart Lights-various locations Staten Island | 3 | CONSTRUCTION COMPLETION | Aug 2013 | Mar 2015 | Aug 2023 | Mar 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | GRSIGI-01 | Staten Island Parking Lot Green Infrastructure Construction | 1 | DEVELOP SCOPE | Jun 2023 | Dec 2023 | Jun 2023 | Dec 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | GRSIGI-01 | Staten Island Parking Lot Green Infrastructure Construction | 2 | DESIGN | Dec 2023 | Dec 2025 | Dec 2023 | Dec 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | GRSIGI-01 | Staten Island Parking Lot Green Infrastructure Construction | 3 | BID/ REGISTER CONTRACT | Dec 2025 | Sep 2026 | Dec 2025 | Sep 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | GRSIGI-01 | Staten Island Parking Lot Green Infrastructure Construction | 4 | CONSTRUCTION | Sep 2026 | Sep 2029 | Sep 2026 | Sep 2029
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | GRSIGI-01 | Staten Island Parking Lot Green Infrastructure Construction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2029 | Sep 2031 | Sep 2029 | Sep 2031
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | HWPLZ001R | Van Name/Van Pelt Plaza R167-113MA | 1 | DEVELOP SCOPE | Jun 2014 | Sep 2014 | Jun 2014 | Sep 2014
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | HWPLZ001R | Van Name/Van Pelt Plaza R167-113MA | 2 | PRELIMINARY DESIGN | Sep 2014 | Jan 2015 | Sep 2014 | Jan 2015
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | HWPLZ001R | Van Name/Van Pelt Plaza R167-113MA | 3 | FINAL DESIGN | Jan 2015 | Jul 2015 | Jan 2015 | Jul 2015
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | HWPLZ001R | Van Name/Van Pelt Plaza R167-113MA | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Oct 2015 | Jul 2015 | Oct 2015
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | HWPLZ001R | Van Name/Van Pelt Plaza R167-113MA | 5 | CONSTRUCTION TO 25% | Oct 2015 | Feb 2016 | Oct 2015 | Feb 2016
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | HWPLZ001R | Van Name/Van Pelt Plaza R167-113MA | 6 | CONSTRUCTION TO 50% | Feb 2016 | Jun 2016 | Feb 2016 | Jun 2016
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | HWPLZ001R | Van Name/Van Pelt Plaza R167-113MA | 7 | CONSTRUCTION TO 75% | Jun 2016 | Oct 2016 | Jun 2016 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | HWPLZ001R | Van Name/Van Pelt Plaza R167-113MA | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2016 | Jan 2017 | Jul 2028 | Sep 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | HWPLZ001R | Van Name/Van Pelt Plaza R167-113MA | 9 | SUBSTANTIAL COMPLETION | Jan 2017 | Mar 2017 | Sep 2028 | Nov 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | HWPLZ001R | Van Name/Van Pelt Plaza R167-113MA | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Apr 2017 | Nov 2028 | Jun 2030
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | NDF-VHALL | NDF-Village Hall Roof R028-120M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | NDF-VHALL | NDF-Village Hall Roof R028-120M | 2 | DESIGN | Dec 2019 | Dec 2021 | Dec 2019 | Dec 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | NDF-VHALL | NDF-Village Hall Roof R028-120M | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | NDF-VHALL | NDF-Village Hall Roof R028-120M | 4 | CONSTRUCTION | Sep 2022 | Sep 2024 | Sep 2022 | Sep 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | NDF-VHALL | NDF-Village Hall Roof R028-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Jun 2031
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-3ALSMTH | Al Smith RC Envelope | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-3ALSMTH | Al Smith RC Envelope | 2 | DESIGN | Dec 2022 | Dec 2024 | Dec 2022 | Dec 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-3ALSMTH | Al Smith RC Envelope | 3 | BID/ REGISTER CONTRACT | Dec 2024 | Sep 2025 | Dec 2024 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-3ALSMTH | Al Smith RC Envelope | 4 | CONSTRUCTION | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-3ALSMTH | Al Smith RC Envelope | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Sep 2028 | Sep 2027 | Sep 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-500BEAC | STATEN ISLAND BIKEWAY & CULTURAL TRAIL & BIKEWAY/ RG-500M | 3 | BID/ REGISTER CONTRACT | Feb 2004 | May 2004 | Nov 2004 | Jul 2005
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-500BEAC | STATEN ISLAND BIKEWAY & CULTURAL TRAIL & BIKEWAY/ RG-500M | 4 | CONSTRUCTION | May 2004 | May 2005 | Dec 2005 | Jun 2006
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-500BEAC | STATEN ISLAND BIKEWAY & CULTURAL TRAIL & BIKEWAY/ RG-500M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | May 2005 | May 2006 | Jun 2006 | Jun 2007
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-500LEM2 | LEMON CREEK MARINA WATERFRONT RC R079 | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-500LEM2 | LEMON CREEK MARINA WATERFRONT RC R079 | 2 | DESIGN | Dec 2022 | Dec 2024 | Dec 2022 | Dec 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-500LEM2 | LEMON CREEK MARINA WATERFRONT RC R079 | 3 | BID/ REGISTER CONTRACT | Dec 2024 | Sep 2025 | Dec 2024 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-500LEM2 | LEMON CREEK MARINA WATERFRONT RC R079 | 4 | CONSTRUCTION | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-500LEM2 | LEMON CREEK MARINA WATERFRONT RC R079 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Sep 2028 | Sep 2027 | Sep 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501ALAS | Alice Austen House-Landscape & Site Impr. R117- | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jun 2012 | Sep 2012
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501ALAS | Alice Austen House-Landscape & Site Impr. R117- | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2012 | Dec 2012
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501ALAS | Alice Austen House-Landscape & Site Impr. R117- | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2012 | Mar 2013
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501ALAS | Alice Austen House-Landscape & Site Impr. R117- | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2013 | Mar 2014
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501ALAS | Alice Austen House-Landscape & Site Impr. R117- | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2014 | Jun 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501BRE1 | MCFARLANE-BREDT HOUSE R117-110MA | 1 | DEVELOP SCOPE | Jul 2007 | Sep 2007 | Jul 2007 | Sep 2007
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501BRE1 | MCFARLANE-BREDT HOUSE R117-110MA | 2 | DESIGN | Sep 2007 | Dec 2007 | Sep 2007 | Dec 2007
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501BRE1 | MCFARLANE-BREDT HOUSE R117-110MA | 3 | BID/ REGISTER CONTRACT | Dec 2007 | Mar 2008 | Dec 2007 | Mar 2008
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501BRE1 | MCFARLANE-BREDT HOUSE R117-110MA | 4 | CONSTRUCTION | Mar 2008 | Mar 2009 | Mar 2008 | Mar 2009
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501BRE1 | MCFARLANE-BREDT HOUSE R117-110MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2009 | Mar 2010 | Mar 2009 | Oct 2011
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CLEX | Clove Lakes Pk-Adult Exercise Equipment R005-118M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Apr 2021 | Oct 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CLEX | Clove Lakes Pk-Adult Exercise Equipment R005-118M | 2 | DESIGN | Dec 2017 | Dec 2018 | Oct 2021 | Oct 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CLEX | Clove Lakes Pk-Adult Exercise Equipment R005-118M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Oct 2022 | Jul 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CLEX | Clove Lakes Pk-Adult Exercise Equipment R005-118M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Jul 2023 | Jun 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CLEX | Clove Lakes Pk-Adult Exercise Equipment R005-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Jul 2024 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CLP2 | Cloves Lakes Walking Path Rehab R005 | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CLP2 | Cloves Lakes Walking Path Rehab R005 | 2 | DESIGN | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CLP2 | Cloves Lakes Walking Path Rehab R005 | 3 | BID/ REGISTER CONTRACT | Sep 2021 | Jun 2022 | Sep 2021 | Jun 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CLP2 | Cloves Lakes Walking Path Rehab R005 | 4 | CONSTRUCTION | Jun 2022 | Dec 2024 | Jun 2022 | Dec 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CLP2 | Cloves Lakes Walking Path Rehab R005 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2024 | Dec 2026 | Dec 2024 | Dec 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CLPR | CLOVE LAKES PARK-RENOVATION OF EXISTING BASEBALL FIELDS, ART | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CLPR | CLOVE LAKES PARK-RENOVATION OF EXISTING BASEBALL FIELDS, ART | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CLPR | CLOVE LAKES PARK-RENOVATION OF EXISTING BASEBALL FIELDS, ART | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CLPR | CLOVE LAKES PARK-RENOVATION OF EXISTING BASEBALL FIELDS, ART | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CLPR | CLOVE LAKES PARK-RENOVATION OF EXISTING BASEBALL FIELDS, ART | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CPTP | Corporal Thompson PK reconstruction | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CPTP | Corporal Thompson PK reconstruction | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CPTP | Corporal Thompson PK reconstruction | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CPTP | Corporal Thompson PK reconstruction | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CPTP | Corporal Thompson PK reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CRPL | CPL. Thompson Park | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CRPL | CPL. Thompson Park | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CRPL | CPL. Thompson Park | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CRPL | CPL. Thompson Park | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CRPL | CPL. Thompson Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501FABL | Faber Park-Install of active recreation, lighting-R008-117M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2007 | Sep 2007
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501FABL | Faber Park-Install of active recreation, lighting-R008-117M | 2 | DESIGN | Dec 2017 | Dec 2018 | Oct 2021 | Oct 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501FABL | Faber Park-Install of active recreation, lighting-R008-117M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Oct 2022 | Jul 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501FABL | Faber Park-Install of active recreation, lighting-R008-117M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Jul 2023 | Jun 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501FABL | Faber Park-Install of active recreation, lighting-R008-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Jul 2024 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501FPFA | Faber Park Rec. Center: Fire Alarm Reconstruction | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501FPFA | Faber Park Rec. Center: Fire Alarm Reconstruction | 2 | DESIGN | Dec 2019 | Dec 2021 | Dec 2019 | Dec 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501FPFA | Faber Park Rec. Center: Fire Alarm Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501FPFA | Faber Park Rec. Center: Fire Alarm Reconstruction | 4 | CONSTRUCTION | Sep 2022 | Sep 2025 | Sep 2022 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501FPFA | Faber Park Rec. Center: Fire Alarm Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501LLCS | Luis Lopez Park Modular PRB Cons. R125-120M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501LLCS | Luis Lopez Park Modular PRB Cons. R125-120M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501LLCS | Luis Lopez Park Modular PRB Cons. R125-120M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501LLCS | Luis Lopez Park Modular PRB Cons. R125-120M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501LLCS | Luis Lopez Park Modular PRB Cons. R125-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2029
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501LPFA | Lyons Pool Rec. Center: Fire Alarm Reconstruction | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501LPFA | Lyons Pool Rec. Center: Fire Alarm Reconstruction | 2 | DESIGN | Dec 2019 | Dec 2021 | Dec 2019 | Dec 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501LPFA | Lyons Pool Rec. Center: Fire Alarm Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501LPFA | Lyons Pool Rec. Center: Fire Alarm Reconstruction | 4 | CONSTRUCTION | Sep 2022 | Sep 2025 | Sep 2022 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501LPFA | Lyons Pool Rec. Center: Fire Alarm Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501MAHO | Parks - Mahoney Playground Reconstruction | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501MAHO | Parks - Mahoney Playground Reconstruction | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501MAHO | Parks - Mahoney Playground Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501MAHO | Parks - Mahoney Playground Reconstruction | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501MAHO | Parks - Mahoney Playground Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501NAPL | Naple Plgr-Reconstruction R073-119M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2022 | Dec 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501NAPL | Naple Plgr-Reconstruction R073-119M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2022 | Dec 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501NAPL | Naple Plgr-Reconstruction R073-119M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2023 | Sep 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501NAPL | Naple Plgr-Reconstruction R073-119M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2024 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501NAPL | Naple Plgr-Reconstruction R073-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2025 | Jun 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501NSEP | North Shore Esplanade Park Reconstruction | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501NSEP | North Shore Esplanade Park Reconstruction | 2 | DESIGN | Feb 2024 | Feb 2026 | Feb 2024 | Feb 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501NSEP | North Shore Esplanade Park Reconstruction | 3 | BID/ REGISTER CONTRACT | Feb 2026 | Nov 2026 | Feb 2026 | Nov 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501NSEP | North Shore Esplanade Park Reconstruction | 4 | CONSTRUCTION | Nov 2026 | Nov 2028 | Nov 2026 | Nov 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501NSEP | North Shore Esplanade Park Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2028 | Nov 2029 | Nov 2028 | Nov 2029
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501PRLL | Prall Playground - Remove & Replace Artifical Turf | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501PRLL | Prall Playground - Remove & Replace Artifical Turf | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501PRLL | Prall Playground - Remove & Replace Artifical Turf | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501PRLL | Prall Playground - Remove & Replace Artifical Turf | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501PRLL | Prall Playground - Remove & Replace Artifical Turf | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501SKYL | Skyline Playground Field Reconstruction | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501SKYL | Skyline Playground Field Reconstruction | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501SKYL | Skyline Playground Field Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501SKYL | Skyline Playground Field Reconstruction | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501SKYL | Skyline Playground Field Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501WLKR | WALKER PARK - PLAYGROUND RECONSTRUCTION | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501WLKR | WALKER PARK - PLAYGROUND RECONSTRUCTION | 2 | DESIGN | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501WLKR | WALKER PARK - PLAYGROUND RECONSTRUCTION | 3 | BID/ REGISTER CONTRACT | Sep 2024 | Jun 2025 | Sep 2024 | Jun 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501WLKR | WALKER PARK - PLAYGROUND RECONSTRUCTION | 4 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501WLKR | WALKER PARK - PLAYGROUND RECONSTRUCTION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Jun 2027 | Jun 2026 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502GBFA | Greenbelt Rec. Center: Fire Alarm Reconstruction | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502GBFA | Greenbelt Rec. Center: Fire Alarm Reconstruction | 2 | DESIGN | Dec 2019 | Dec 2021 | Dec 2019 | Dec 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502GBFA | Greenbelt Rec. Center: Fire Alarm Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502GBFA | Greenbelt Rec. Center: Fire Alarm Reconstruction | 4 | CONSTRUCTION | Sep 2022 | Sep 2025 | Sep 2022 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502GBFA | Greenbelt Rec. Center: Fire Alarm Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502GBRE | Greenbelt Recreation Center Basketball Cts RC | 1 | DEVELOP SCOPE | Jun 2022 | Nov 2022 | Jun 2022 | Nov 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502GBRE | Greenbelt Recreation Center Basketball Cts RC | 2 | DESIGN | Nov 2022 | Nov 2023 | Nov 2022 | Nov 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502GBRE | Greenbelt Recreation Center Basketball Cts RC | 3 | BID/ REGISTER CONTRACT | Nov 2023 | Aug 2024 | Nov 2023 | Aug 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502GBRE | Greenbelt Recreation Center Basketball Cts RC | 4 | CONSTRUCTION | Aug 2024 | Aug 2025 | Aug 2024 | Aug 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502GBRE | Greenbelt Recreation Center Basketball Cts RC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2025 | Aug 2026 | Aug 2025 | Aug 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502MLPG | Midland Playground Reconstruction | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502MLPG | Midland Playground Reconstruction | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502MLPG | Midland Playground Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502MLPG | Midland Playground Reconstruction | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502MLPG | Midland Playground Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502OBRF | Ocean Breeze Athletic Center Roof | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502OBRF | Ocean Breeze Athletic Center Roof | 2 | DESIGN | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502OBRF | Ocean Breeze Athletic Center Roof | 3 | BID/ REGISTER CONTRACT | Sep 2024 | Jun 2025 | Sep 2024 | Jun 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502OBRF | Ocean Breeze Athletic Center Roof | 4 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502OBRF | Ocean Breeze Athletic Center Roof | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Jun 2027 | Jun 2026 | Jun 2032
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502OCEA | Ocean Breeze Athletic Complex Track RC R149-122M | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502OCEA | Ocean Breeze Athletic Complex Track RC R149-122M | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502OCEA | Ocean Breeze Athletic Complex Track RC R149-122M | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502OCEA | Ocean Breeze Athletic Complex Track RC R149-122M | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502OCEA | Ocean Breeze Athletic Complex Track RC R149-122M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2030
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502RUSS | Detective Russell Timoshenko Synthetic Turf Field | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502RUSS | Detective Russell Timoshenko Synthetic Turf Field | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502RUSS | Detective Russell Timoshenko Synthetic Turf Field | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502RUSS | Detective Russell Timoshenko Synthetic Turf Field | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502RUSS | Detective Russell Timoshenko Synthetic Turf Field | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502SHML | Schmul Park Playground | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502SHML | Schmul Park Playground | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502SHML | Schmul Park Playground | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502SHML | Schmul Park Playground | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502SHML | Schmul Park Playground | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502WBBF | Willowbrook Park Improvements | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502WBBF | Willowbrook Park Improvements | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502WBBF | Willowbrook Park Improvements | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502WBBF | Willowbrook Park Improvements | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502WBBF | Willowbrook Park Improvements | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Jun 2028 | Sep 2025 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503AESP | Aesop Park Playground Recon - Safety Surface | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503AESP | Aesop Park Playground Recon - Safety Surface | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503AESP | Aesop Park Playground Recon - Safety Surface | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503AESP | Aesop Park Playground Recon - Safety Surface | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503AESP | Aesop Park Playground Recon - Safety Surface | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Jun 2027
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503ANNA | Annadale Green Reconstruction | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503ANNA | Annadale Green Reconstruction | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503ANNA | Annadale Green Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503ANNA | Annadale Green Reconstruction | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503ANNA | Annadale Green Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CHLP | Conference House LENAPE PARK SPRAY SHOWER | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CHLP | Conference House LENAPE PARK SPRAY SHOWER | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CHLP | Conference House LENAPE PARK SPRAY SHOWER | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CHLP | Conference House LENAPE PARK SPRAY SHOWER | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CHLP | Conference House LENAPE PARK SPRAY SHOWER | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CHRF | Conference House Roof and Exterior Restoration | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CHRF | Conference House Roof and Exterior Restoration | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CHRF | Conference House Roof and Exterior Restoration | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CHRF | Conference House Roof and Exterior Restoration | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CHRF | Conference House Roof and Exterior Restoration | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CRBP | CRESCENT BEACH PARK CONS 135-113MA | 1 | DEVELOP SCOPE | Jul 2008 | Sep 2008 | Jul 2008 | Jun 2011
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CRBP | CRESCENT BEACH PARK CONS 135-113MA | 2 | DESIGN | Sep 2008 | Dec 2008 | Jun 2011 | Sep 2011
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CRBP | CRESCENT BEACH PARK CONS 135-113MA | 3 | BID/ REGISTER CONTRACT | Dec 2008 | Mar 2009 | Sep 2011 | Dec 2011
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CRBP | CRESCENT BEACH PARK CONS 135-113MA | 4 | CONSTRUCTION | Mar 2009 | Mar 2010 | Dec 2011 | Dec 2012
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CRBP | CRESCENT BEACH PARK CONS 135-113MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2010 | Mar 2011 | Dec 2012 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503DUPL | DUGAN PLAYGROUND R/C R026-119M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503DUPL | DUGAN PLAYGROUND R/C R026-119M | 2 | DESIGN | Dec 2018 | Dec 2020 | Dec 2018 | Dec 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503DUPL | DUGAN PLAYGROUND R/C R026-119M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503DUPL | DUGAN PLAYGROUND R/C R026-119M | 4 | CONSTRUCTION | Sep 2021 | Sep 2023 | Sep 2021 | Sep 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503DUPL | DUGAN PLAYGROUND R/C R026-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2030
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503GCPG | Greencroft Playgroud R089-122M | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503GCPG | Greencroft Playgroud R089-122M | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503GCPG | Greencroft Playgroud R089-122M | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503GCPG | Greencroft Playgroud R089-122M | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503GCPG | Greencroft Playgroud R089-122M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2031
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503GCPL | Greencroft Plgr- R/C of PRB R089-115M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | May 2015
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503GCPL | Greencroft Plgr- R/C of PRB R089-115M | 2 | DESIGN | Sep 2013 | Dec 2013 | May 2015 | Aug 2017
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503GCPL | Greencroft Plgr- R/C of PRB R089-115M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Aug 2017 | Nov 2017
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503GCPL | Greencroft Plgr- R/C of PRB R089-115M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Nov 2017 | Nov 2018
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503GCPL | Greencroft Plgr- R/C of PRB R089-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Nov 2018 | Jun 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503LEMN | Lemon Creek Park- Reconstruction | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503LEMN | Lemon Creek Park- Reconstruction | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503LEMN | Lemon Creek Park- Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503LEMN | Lemon Creek Park- Reconstruction | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503LEMN | Lemon Creek Park- Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503LEMO | LEMON CREEK PARK, PHASE I R079-190 | 1 | DEVELOP SCOPE | Jul 2008 | Sep 2008 | Jul 2008 | Sep 2008
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503LEMO | LEMON CREEK PARK, PHASE I R079-190 | 2 | DESIGN | Sep 2008 | Dec 2008 | Sep 2008 | Dec 2008
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503LEMO | LEMON CREEK PARK, PHASE I R079-190 | 3 | BID/ REGISTER CONTRACT | Dec 2008 | Mar 2009 | Dec 2008 | Mar 2009
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503LEMO | LEMON CREEK PARK, PHASE I R079-190 | 4 | CONSTRUCTION | Mar 2009 | Mar 2010 | Mar 2009 | Mar 2010
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503LEMO | LEMON CREEK PARK, PHASE I R079-190 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2010 | Mar 2011 | Mar 2010 | Aug 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503SNCS | Seaside Nature Pk PRB construction R145-119M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2017
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503SNCS | Seaside Nature Pk PRB construction R145-119M | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2017 | Dec 2017
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503SNCS | Seaside Nature Pk PRB construction R145-119M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2017 | Mar 2018
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503SNCS | Seaside Nature Pk PRB construction R145-119M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2018 | Mar 2019
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503SNCS | Seaside Nature Pk PRB construction R145-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2019 | Aug 2029
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503SOUT | South Shore Little League | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2007 | Sep 2007
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503SOUT | South Shore Little League | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503SOUT | South Shore Little League | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503SOUT | South Shore Little League | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503SOUT | South Shore Little League | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2029
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503TOTT | Tottenville Shoreline Protection - Staten Island | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2007 | Sep 2007
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503TOTT | Tottenville Shoreline Protection - Staten Island | 2 | DESIGN | Dec 2018 | Mar 2020 | Dec 2018 | Mar 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503TOTT | Tottenville Shoreline Protection - Staten Island | 3 | BID/ REGISTER CONTRACT | Mar 2020 | Dec 2020 | Mar 2020 | Dec 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503TOTT | Tottenville Shoreline Protection - Staten Island | 4 | CONSTRUCTION | Dec 2020 | Dec 2022 | Dec 2020 | Dec 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503TOTT | Tottenville Shoreline Protection - Staten Island | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2022 | Dec 2023 | Dec 2022 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503WLFP | Wolfe's Pond Park Playground Reconstruction | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503WLFP | Wolfe's Pond Park Playground Reconstruction | 2 | DESIGN | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503WLFP | Wolfe's Pond Park Playground Reconstruction | 3 | BID/ REGISTER CONTRACT | Sep 2024 | Jun 2025 | Sep 2024 | Jun 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503WLFP | Wolfe's Pond Park Playground Reconstruction | 4 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503WLFP | Wolfe's Pond Park Playground Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Jun 2027 | Jun 2026 | Jun 2027
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503WPMO | Wolfe's Pond Park Maintenance and Operations Building | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503WPMO | Wolfe's Pond Park Maintenance and Operations Building | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503WPMO | Wolfe's Pond Park Maintenance and Operations Building | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503WPMO | Wolfe's Pond Park Maintenance and Operations Building | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503WPMO | Wolfe's Pond Park Maintenance and Operations Building | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Jun 2026 | Sep 2025 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH01 | Anchor Park Site - South Pk Fresh kills DESIGN | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Apr 2020 | Oct 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH01 | Anchor Park Site - South Pk Fresh kills DESIGN | 2 | DESIGN | Dec 2016 | Dec 2017 | Oct 2020 | Oct 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH01 | Anchor Park Site - South Pk Fresh kills DESIGN | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Oct 2023 | Jun 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH01 | Anchor Park Site - South Pk Fresh kills DESIGN | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Jul 2024 | Jun 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH01 | Anchor Park Site - South Pk Fresh kills DESIGN | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Jul 2025 | Jun 2029
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH02 | Anchor Park Site - South Pk Construction /Fresh kills | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2023 | Dec 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH02 | Anchor Park Site - South Pk Construction /Fresh kills | 2 | DESIGN | Dec 2019 | Dec 2021 | Dec 2023 | Dec 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH02 | Anchor Park Site - South Pk Construction /Fresh kills | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2025 | Sep 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH02 | Anchor Park Site - South Pk Construction /Fresh kills | 4 | CONSTRUCTION | Sep 2022 | Sep 2024 | Sep 2026 | Sep 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH02 | Anchor Park Site - South Pk Construction /Fresh kills | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2028 | Jun 2030
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH03 | Anchor Park Site - South Pk PRB/Fresh kills | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2023 | Dec 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH03 | Anchor Park Site - South Pk PRB/Fresh kills | 2 | DESIGN | Dec 2019 | Dec 2021 | Dec 2023 | Dec 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH03 | Anchor Park Site - South Pk PRB/Fresh kills | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2025 | Sep 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH03 | Anchor Park Site - South Pk PRB/Fresh kills | 4 | CONSTRUCTION | Sep 2022 | Sep 2024 | Sep 2026 | Sep 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH03 | Anchor Park Site - South Pk PRB/Fresh kills | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2028 | Dec 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BBPAV | Multisite SI-Basketball Cours paving R | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Apr 2020 | Oct 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BBPAV | Multisite SI-Basketball Cours paving R | 2 | DESIGN | Dec 2017 | Jun 2019 | Oct 2020 | Apr 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BBPAV | Multisite SI-Basketball Cours paving R | 3 | BID/ REGISTER CONTRACT | Jun 2019 | Mar 2020 | Apr 2022 | Jan 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BBPAV | Multisite SI-Basketball Cours paving R | 4 | CONSTRUCTION | Mar 2020 | Sep 2021 | Jan 2023 | Jun 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BBPAV | Multisite SI-Basketball Cours paving R | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Jul 2024 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BLOOMB | BLOOMINGDALE PARK : RECONSTRUCT TWO BASKETBALL COURTS. | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BLOOMB | BLOOMINGDALE PARK : RECONSTRUCT TWO BASKETBALL COURTS. | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BLOOMB | BLOOMINGDALE PARK : RECONSTRUCT TWO BASKETBALL COURTS. | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BLOOMB | BLOOMINGDALE PARK : RECONSTRUCT TWO BASKETBALL COURTS. | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BLOOMB | BLOOMINGDALE PARK : RECONSTRUCT TWO BASKETBALL COURTS. | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BUNBCH | Buono Beach-Reconstruction of Fountain | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BUNBCH | Buono Beach-Reconstruction of Fountain | 2 | DESIGN | Dec 2018 | Dec 2020 | Dec 2018 | Dec 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BUNBCH | Buono Beach-Reconstruction of Fountain | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BUNBCH | Buono Beach-Reconstruction of Fountain | 4 | CONSTRUCTION | Sep 2021 | Sep 2023 | Sep 2021 | Sep 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BUNBCH | Buono Beach-Reconstruction of Fountain | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CHARCS | Fairview Park - Cons. Public Rest Room R153-218M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CHARCS | Fairview Park - Cons. Public Rest Room R153-218M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CHARCS | Fairview Park - Cons. Public Rest Room R153-218M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CHARCS | Fairview Park - Cons. Public Rest Room R153-218M | 4 | CONSTRUCTION | Sep 2019 | Mar 2021 | Sep 2019 | Mar 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CHARCS | Fairview Park - Cons. Public Rest Room R153-218M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Mar 2022 | Mar 2021 | Jun 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CHARLS | Fairview Park Landscape Construction | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Apr 2021 | Oct 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CHARLS | Fairview Park Landscape Construction | 2 | DESIGN | Dec 2017 | Dec 2018 | Oct 2021 | Oct 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CHARLS | Fairview Park Landscape Construction | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Oct 2022 | Jul 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CHARLS | Fairview Park Landscape Construction | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Jul 2023 | Jun 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CHARLS | Fairview Park Landscape Construction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Jul 2024 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLAWS | RENOVATION OF CLAWSON PLAYGROUND | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Apr 2019 | Oct 2019
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLAWS | RENOVATION OF CLAWSON PLAYGROUND | 2 | DESIGN | Dec 2016 | Jun 2018 | Oct 2019 | Oct 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLAWS | RENOVATION OF CLAWSON PLAYGROUND | 3 | BID/ REGISTER CONTRACT | Jun 2018 | Mar 2019 | Oct 2020 | Jul 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLAWS | RENOVATION OF CLAWSON PLAYGROUND | 4 | CONSTRUCTION | Mar 2019 | Sep 2020 | Jul 2021 | Jul 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLAWS | RENOVATION OF CLAWSON PLAYGROUND | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Jul 2022 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLVCHL | Recon chiller slab & header at Cloves Lake Park R005-120M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2007 | Sep 2007
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLVCHL | Recon chiller slab & header at Cloves Lake Park R005-120M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLVCHL | Recon chiller slab & header at Cloves Lake Park R005-120M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLVCHL | Recon chiller slab & header at Cloves Lake Park R005-120M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLVCHL | Recon chiller slab & header at Cloves Lake Park R005-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2031
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLVLKP | Clove Lakes Park RG-120M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLVLKP | Clove Lakes Park RG-120M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLVLKP | Clove Lakes Park RG-120M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLVLKP | Clove Lakes Park RG-120M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLVLKP | Clove Lakes Park RG-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jan 2032
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIB12 | CPI PH1- SI PRBs -BUNDLE 3 RG-216MA | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIB12 | CPI PH1- SI PRBs -BUNDLE 3 RG-216MA | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIB12 | CPI PH1- SI PRBs -BUNDLE 3 RG-216MA | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIB12 | CPI PH1- SI PRBs -BUNDLE 3 RG-216MA | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIB12 | CPI PH1- SI PRBs -BUNDLE 3 RG-216MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2030
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIBN6 | CPI - SI PRBs-Bundle 2 RG-515M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIBN6 | CPI - SI PRBs-Bundle 2 RG-515M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIBN6 | CPI - SI PRBs-Bundle 2 RG-515M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIBN6 | CPI - SI PRBs-Bundle 2 RG-515M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIBN6 | CPI - SI PRBs-Bundle 2 RG-515M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Jun 2030
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPILCS | Lt. Lia Playground PRB RC R111-123M | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPILCS | Lt. Lia Playground PRB RC R111-123M | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPILCS | Lt. Lia Playground PRB RC R111-123M | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPILCS | Lt. Lia Playground PRB RC R111-123M | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPILCS | Lt. Lia Playground PRB RC R111-123M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Jun 2028 | Sep 2025 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPILIP | CPI - Liotti Ikefugi Playground Reconstruction | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPILIP | CPI - Liotti Ikefugi Playground Reconstruction | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPILIP | CPI - Liotti Ikefugi Playground Reconstruction | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPILIP | CPI - Liotti Ikefugi Playground Reconstruction | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPILIP | CPI - Liotti Ikefugi Playground Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Jun 2032
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPILLP | CPI - LT LIA PLGD | 1 | DEVELOP SCOPE | Jun 2022 | Nov 2022 | Jun 2022 | Nov 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPILLP | CPI - LT LIA PLGD | 2 | DESIGN | Nov 2022 | Nov 2023 | Nov 2022 | Nov 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPILLP | CPI - LT LIA PLGD | 3 | BID/ REGISTER CONTRACT | Nov 2023 | Aug 2024 | Nov 2023 | Aug 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPILLP | CPI - LT LIA PLGD | 4 | CONSTRUCTION | Aug 2024 | Aug 2025 | Aug 2024 | Aug 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPILLP | CPI - LT LIA PLGD | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2025 | Aug 2026 | Aug 2025 | Jun 2027
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIMDP | CPI PH1- McDonald Playground reconstruction | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Jan 2015
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIMDP | CPI PH1- McDonald Playground reconstruction | 2 | DESIGN | Sep 2014 | Dec 2014 | Jan 2015 | Jan 2016
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIMDP | CPI PH1- McDonald Playground reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Mar 2016 | Sep 2016
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIMDP | CPI PH1- McDonald Playground reconstruction | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Oct 2016 | Apr 2018
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIMDP | CPI PH1- McDonald Playground reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Apr 2018 | Jun 2030
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIMH | CPI PH2 - Mariner's Harbor Playground-RC R036-118M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Apr 2022 | Oct 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIMH | CPI PH2 - Mariner's Harbor Playground-RC R036-118M | 2 | DESIGN | Dec 2017 | Dec 2018 | Oct 2022 | Oct 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIMH | CPI PH2 - Mariner's Harbor Playground-RC R036-118M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Oct 2023 | Jun 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIMH | CPI PH2 - Mariner's Harbor Playground-RC R036-118M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Jul 2024 | Jun 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIMH | CPI PH2 - Mariner's Harbor Playground-RC R036-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Jul 2025 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPISCP | Sobel Court Park Reconstruction R144 | 1 | DEVELOP SCOPE | Oct 2023 | Apr 2024 | Oct 2023 | Apr 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPISCP | Sobel Court Park Reconstruction R144 | 2 | DESIGN | Apr 2024 | Apr 2025 | Apr 2024 | Apr 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPISCP | Sobel Court Park Reconstruction R144 | 3 | BID/ REGISTER CONTRACT | Apr 2025 | Jan 2026 | Apr 2025 | Jan 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPISCP | Sobel Court Park Reconstruction R144 | 4 | CONSTRUCTION | Jan 2026 | Jan 2027 | Jan 2026 | Jan 2027
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPISCP | Sobel Court Park Reconstruction R144 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2027 | Jun 2031 | Jan 2027 | Jun 2031
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5DONGAN | Dongan Plgr-reconstruction | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5DONGAN | Dongan Plgr-reconstruction | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5DONGAN | Dongan Plgr-reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5DONGAN | Dongan Plgr-reconstruction | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5DONGAN | Dongan Plgr-reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FABBAS | Faber Park -Remove Equipment & Install Basketball Court | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FABBAS | Faber Park -Remove Equipment & Install Basketball Court | 2 | DESIGN | Dec 2018 | Dec 2020 | Dec 2018 | Dec 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FABBAS | Faber Park -Remove Equipment & Install Basketball Court | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FABBAS | Faber Park -Remove Equipment & Install Basketball Court | 4 | CONSTRUCTION | Sep 2021 | Sep 2023 | Sep 2021 | Sep 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FABBAS | Faber Park -Remove Equipment & Install Basketball Court | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRES10 | FRESH KILLS OWL HOLLOW FIELDS PRB | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRES10 | FRESH KILLS OWL HOLLOW FIELDS PRB | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRES10 | FRESH KILLS OWL HOLLOW FIELDS PRB | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRES10 | FRESH KILLS OWL HOLLOW FIELDS PRB | 4 | CONSTRUCTION | Sep 2019 | Mar 2021 | Sep 2019 | Mar 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRES10 | FRESH KILLS OWL HOLLOW FIELDS PRB | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Mar 2022 | Mar 2021 | Jun 2030
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRES11 | Owl Hollow Parking Access Road - R017-121M | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2023 | Dec 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRES11 | Owl Hollow Parking Access Road - R017-121M | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2023 | Dec 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRES11 | Owl Hollow Parking Access Road - R017-121M | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2024 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRES11 | Owl Hollow Parking Access Road - R017-121M | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2025 | Sep 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRES11 | Owl Hollow Parking Access Road - R017-121M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2026 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRESH9 | Fresh Kills - construction of North Park R017-115M | 1 | DEVELOP SCOPE | Jul 2006 | Sep 2006 | Jul 2006 | Oct 2012
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRESH9 | Fresh Kills - construction of North Park R017-115M | 2 | DESIGN | Sep 2006 | Dec 2006 | Oct 2012 | Jan 2013
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRESH9 | Fresh Kills - construction of North Park R017-115M | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Jan 2013 | Apr 2013
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRESH9 | Fresh Kills - construction of North Park R017-115M | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Apr 2013 | Apr 2014
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRESH9 | Fresh Kills - construction of North Park R017-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Apr 2014 | Sep 2030
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GBRCTF | Greenbelt Rec.Cntr-Constr. of turf field | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GBRCTF | Greenbelt Rec.Cntr-Constr. of turf field | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GBRCTF | Greenbelt Rec.Cntr-Constr. of turf field | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GBRCTF | Greenbelt Rec.Cntr-Constr. of turf field | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GBRCTF | Greenbelt Rec.Cntr-Constr. of turf field | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GKBIKE | GREAT KILLS BICYCLE PATH R016-204MA | 1 | DEVELOP SCOPE | Jul 2006 | Sep 2006 | Aug 2008 | Nov 2008
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GKBIKE | GREAT KILLS BICYCLE PATH R016-204MA | 2 | DESIGN | Sep 2006 | Dec 2006 | Nov 2008 | Jun 2012
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GKBIKE | GREAT KILLS BICYCLE PATH R016-204MA | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Jun 2012 | Sep 2012
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GKBIKE | GREAT KILLS BICYCLE PATH R016-204MA | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Sep 2012 | Sep 2013
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GKBIKE | GREAT KILLS BICYCLE PATH R016-204MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Sep 2013 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GRNBRC | Greenbelt Rec Ctr Partial RC R129-119M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Dec 2022 | Jun 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GRNBRC | Greenbelt Rec Ctr Partial RC R129-119M | 2 | DESIGN | Dec 2018 | Dec 2019 | Jun 2023 | Jun 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GRNBRC | Greenbelt Rec Ctr Partial RC R129-119M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Jun 2024 | Mar 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GRNBRC | Greenbelt Rec Ctr Partial RC R129-119M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Mar 2025 | Mar 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GRNBRC | Greenbelt Rec Ctr Partial RC R129-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Mar 2026 | Jun 2029
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GSIGI1 | Staten Island Parks Green Infrastructure Construction | 1 | DEVELOP SCOPE | Jun 2023 | Dec 2023 | Jun 2023 | Dec 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GSIGI1 | Staten Island Parks Green Infrastructure Construction | 2 | DESIGN | Dec 2023 | Dec 2025 | Dec 2023 | Dec 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GSIGI1 | Staten Island Parks Green Infrastructure Construction | 3 | BID/ REGISTER CONTRACT | Dec 2025 | Sep 2026 | Dec 2025 | Sep 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GSIGI1 | Staten Island Parks Green Infrastructure Construction | 4 | CONSTRUCTION | Sep 2026 | Sep 2029 | Sep 2026 | Sep 2029
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GSIGI1 | Staten Island Parks Green Infrastructure Construction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2029 | Sep 2031 | Sep 2029 | Sep 2031
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5IRENE | IRENE - Wolfe's Pond Park Berm | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5IRENE | IRENE - Wolfe's Pond Park Berm | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5IRENE | IRENE - Wolfe's Pond Park Berm | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5IRENE | IRENE - Wolfe's Pond Park Berm | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5IRENE | IRENE - Wolfe's Pond Park Berm | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2033
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5IRRIG | GOLF COURSE IRRIGATION - S.I. RG-200M | 2 | DESIGN | Nov 1999 | Dec 1999 | Nov 1999 | Dec 1999
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5IRRIG | GOLF COURSE IRRIGATION - S.I. RG-200M | 3 | BID/ REGISTER CONTRACT | Jan 2000 | Mar 2000 | Jan 2000 | Mar 2000
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5IRRIG | GOLF COURSE IRRIGATION - S.I. RG-200M | 4 | CONSTRUCTION | Mar 2000 | Apr 2001 | Mar 2000 | Apr 2001
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5IRRIG | GOLF COURSE IRRIGATION - S.I. RG-200M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2001 | Apr 2002 | Apr 2001 | Apr 2002
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5MCARPK | Gen. MacArthur Park Baseball Field Renovation R067-117M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Dec 2017 | Mar 2018
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5MCARPK | Gen. MacArthur Park Baseball Field Renovation R067-117M | 2 | DESIGN | Sep 2015 | Dec 2015 | Mar 2018 | Jun 2018
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5MCARPK | Gen. MacArthur Park Baseball Field Renovation R067-117M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Jun 2018 | Sep 2018
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5MCARPK | Gen. MacArthur Park Baseball Field Renovation R067-117M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Sep 2018 | Sep 2019
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5MCARPK | Gen. MacArthur Park Baseball Field Renovation R067-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Sep 2019 | Jun 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5OBRZDR | Ocean Breeze Athletic Complex Exterior Doors Reconstruction | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5OBRZDR | Ocean Breeze Athletic Complex Exterior Doors Reconstruction | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5OBRZDR | Ocean Breeze Athletic Complex Exterior Doors Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5OBRZDR | Ocean Breeze Athletic Complex Exterior Doors Reconstruction | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5OBRZDR | Ocean Breeze Athletic Complex Exterior Doors Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PL15A4 | $1Contract-Conference House Pk-ADA at Visitor Ct WO4 RG-215M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PL15A4 | $1Contract-Conference House Pk-ADA at Visitor Ct WO4 RG-215M | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PL15A4 | $1Contract-Conference House Pk-ADA at Visitor Ct WO4 RG-215M | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PL15A4 | $1Contract-Conference House Pk-ADA at Visitor Ct WO4 RG-215M | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PL15A4 | $1Contract-Conference House Pk-ADA at Visitor Ct WO4 RG-215M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2019 | Jun 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PNYC08 | PlaNYC-Ocean Breeze Beach Parking Lot | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2024 | Dec 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PNYC08 | PlaNYC-Ocean Breeze Beach Parking Lot | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2024 | Dec 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PNYC08 | PlaNYC-Ocean Breeze Beach Parking Lot | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2025 | Sep 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PNYC08 | PlaNYC-Ocean Breeze Beach Parking Lot | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2026 | Sep 2027
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PNYC08 | PlaNYC-Ocean Breeze Beach Parking Lot | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2027 | Sep 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PRALCS | Prall Playground-Reconstruction of PRB R105-119MA | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PRALCS | Prall Playground-Reconstruction of PRB R105-119MA | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PRALCS | Prall Playground-Reconstruction of PRB R105-119MA | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PRALCS | Prall Playground-Reconstruction of PRB R105-119MA | 4 | CONSTRUCTION | Sep 2020 | Mar 2022 | Sep 2020 | Mar 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PRALCS | Prall Playground-Reconstruction of PRB R105-119MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Mar 2023 | Mar 2022 | Jun 2029
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PRESPL | Prescott Playground RC R085-118M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Apr 2021 | Oct 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PRESPL | Prescott Playground RC R085-118M | 2 | DESIGN | Dec 2017 | Dec 2018 | Oct 2021 | Oct 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PRESPL | Prescott Playground RC R085-118M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Oct 2022 | Jul 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PRESPL | Prescott Playground RC R085-118M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Jul 2023 | Jun 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PRESPL | Prescott Playground RC R085-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Jul 2024 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5RECSI | Lyons Rec Ctr RC in Staten Island R043-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Sep 2021 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SEGNRF | Seguine House Roof Reconstruction | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2017 | Dec 2017
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SEGNRF | Seguine House Roof Reconstruction | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SEGNRF | Seguine House Roof Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SEGNRF | Seguine House Roof Reconstruction | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SEGNRF | Seguine House Roof Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2029
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SIFRTN | Staten Island Forest Restoration | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SIFRTN | Staten Island Forest Restoration | 2 | DESIGN | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SIFRTN | Staten Island Forest Restoration | 3 | BID/ REGISTER CONTRACT | Sep 2022 | Jun 2023 | Sep 2022 | Jun 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SIFRTN | Staten Island Forest Restoration | 4 | CONSTRUCTION | Jun 2023 | Dec 2025 | Jun 2023 | Dec 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SIFRTN | Staten Island Forest Restoration | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2025 | Dec 2027 | Dec 2025 | Dec 2027
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SIPOOL | Staten Island Indoor Pool | 1 | DEVELOP SCOPE | Aug 2016 | Jan 2017 | Jul 2022 | Dec 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SIPOOL | Staten Island Indoor Pool | 2 | DESIGN | Jan 2017 | Jan 2019 | Dec 2022 | Dec 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SIPOOL | Staten Island Indoor Pool | 3 | BID/ REGISTER CONTRACT | Jan 2019 | Oct 2019 | Dec 2024 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SIPOOL | Staten Island Indoor Pool | 4 | CONSTRUCTION | Oct 2019 | Oct 2022 | Sep 2025 | Sep 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SIPOOL | Staten Island Indoor Pool | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2022 | Oct 2024 | Sep 2030 | Sep 2032
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SNUGLL | Snug Harbor Little League | 1 | DEVELOP SCOPE | Jul 2023 | Dec 2023 | Jul 2023 | Dec 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SNUGLL | Snug Harbor Little League | 2 | DESIGN | Dec 2023 | Dec 2024 | Dec 2023 | Dec 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SNUGLL | Snug Harbor Little League | 3 | BID/ REGISTER CONTRACT | Dec 2024 | Sep 2025 | Dec 2024 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SNUGLL | Snug Harbor Little League | 4 | CONSTRUCTION | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SNUGLL | Snug Harbor Little League | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Jun 2029
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TPSBF | Tappen Park & South Beach Fountain Reconstruction | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TPSBF | Tappen Park & South Beach Fountain Reconstruction | 2 | DESIGN | Dec 2018 | Jun 2020 | Dec 2018 | Jun 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TPSBF | Tappen Park & South Beach Fountain Reconstruction | 3 | BID/ REGISTER CONTRACT | Jun 2020 | Mar 2021 | Jun 2020 | Mar 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TPSBF | Tappen Park & South Beach Fountain Reconstruction | 4 | CONSTRUCTION | Mar 2021 | Sep 2022 | Mar 2021 | Sep 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TPSBF | Tappen Park & South Beach Fountain Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2030
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRE21A | FY21 Street Trees Staten Island, CB 1-3 RG- | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRE21A | FY21 Street Trees Staten Island, CB 1-3 RG- | 2 | DESIGN | Dec 2019 | Jun 2020 | Dec 2019 | Jun 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRE21A | FY21 Street Trees Staten Island, CB 1-3 RG- | 3 | BID/ REGISTER CONTRACT | Jun 2020 | Mar 2021 | Jun 2020 | Mar 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRE21A | FY21 Street Trees Staten Island, CB 1-3 RG- | 4 | CONSTRUCTION | Mar 2021 | Sep 2022 | Mar 2021 | Sep 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRE21A | FY21 Street Trees Staten Island, CB 1-3 RG- | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2024 | Sep 2022 | Jun 2030
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRE23A | Staten Island Street Tree Planting FY23 | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRE23A | Staten Island Street Tree Planting FY23 | 2 | DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRE23A | Staten Island Street Tree Planting FY23 | 3 | BID/ REGISTER CONTRACT | Jun 2023 | Mar 2024 | Jun 2023 | Mar 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRE23A | Staten Island Street Tree Planting FY23 | 4 | CONSTRUCTION | Mar 2024 | Sep 2025 | Mar 2024 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRE23A | Staten Island Street Tree Planting FY23 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRSD23 | Staten Island Tree-Damaged Sidewalk Reconstruction FY23 | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRSD23 | Staten Island Tree-Damaged Sidewalk Reconstruction FY23 | 2 | DESIGN | Feb 2024 | Aug 2024 | Feb 2024 | Aug 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRSD23 | Staten Island Tree-Damaged Sidewalk Reconstruction FY23 | 3 | BID/ REGISTER CONTRACT | Aug 2024 | May 2025 | Aug 2024 | May 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRSD23 | Staten Island Tree-Damaged Sidewalk Reconstruction FY23 | 4 | CONSTRUCTION | May 2025 | Nov 2026 | May 2025 | Nov 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRSD23 | Staten Island Tree-Damaged Sidewalk Reconstruction FY23 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2028 | Nov 2026 | Nov 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5WHITEP | White Plgr-Hillside Slide Construction R012-119m | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5WHITEP | White Plgr-Hillside Slide Construction R012-119m | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5WHITEP | White Plgr-Hillside Slide Construction R012-119m | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5WHITEP | White Plgr-Hillside Slide Construction R012-119m | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5WHITEP | White Plgr-Hillside Slide Construction R012-119m | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-6PAVESI | Staten Island Pavement Reconstruction (SoGR) RG-120M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Apr 2025 | Oct 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-6PAVESI | Staten Island Pavement Reconstruction (SoGR) RG-120M | 2 | DESIGN | Dec 2019 | Jun 2021 | Oct 2025 | Apr 2027
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-6PAVESI | Staten Island Pavement Reconstruction (SoGR) RG-120M | 3 | BID/ REGISTER CONTRACT | Jun 2021 | Mar 2022 | Apr 2027 | Jan 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-6PAVESI | Staten Island Pavement Reconstruction (SoGR) RG-120M | 4 | CONSTRUCTION | Mar 2022 | Sep 2023 | Jan 2028 | Jun 2029
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-6PAVESI | Staten Island Pavement Reconstruction (SoGR) RG-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Jul 2029 | Jun 2030
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-HLG | SIBG -SI BOTANICAL GARDEN Healing Garden R116-506M | 1 | DEVELOP SCOPE | Jul 2008 | Sep 2008 | Jul 2008 | Sep 2008
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-HLG | SIBG -SI BOTANICAL GARDEN Healing Garden R116-506M | 2 | PRELIMINARY DESIGN | Sep 2008 | Jan 2009 | Sep 2008 | Jan 2009
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-HLG | SIBG -SI BOTANICAL GARDEN Healing Garden R116-506M | 3 | FINAL DESIGN | Jan 2009 | Jul 2009 | Jan 2009 | Jul 2009
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-HLG | SIBG -SI BOTANICAL GARDEN Healing Garden R116-506M | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2009 | Oct 2009 | Jul 2009 | Oct 2009
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-HLG | SIBG -SI BOTANICAL GARDEN Healing Garden R116-506M | 5 | CONSTRUCTION TO 25% | Oct 2009 | Feb 2010 | Oct 2009 | Feb 2010
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-HLG | SIBG -SI BOTANICAL GARDEN Healing Garden R116-506M | 6 | CONSTRUCTION TO 50% | Feb 2010 | Jun 2010 | Feb 2010 | Jun 2010
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-HLG | SIBG -SI BOTANICAL GARDEN Healing Garden R116-506M | 7 | CONSTRUCTION TO 75% | Jun 2010 | Oct 2010 | Jun 2010 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-HLG | SIBG -SI BOTANICAL GARDEN Healing Garden R116-506M | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2010 | Jan 2011 | Jul 2028 | Sep 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-HLG | SIBG -SI BOTANICAL GARDEN Healing Garden R116-506M | 9 | SUBSTANTIAL COMPLETION | Jan 2011 | Mar 2011 | Sep 2028 | Nov 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-HLG | SIBG -SI BOTANICAL GARDEN Healing Garden R116-506M | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2011 | Apr 2011 | Nov 2028 | Jun 2030
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-IRR | SIBG -SI BOTANICAL GARDEN Site Irrigation | 1 | DEVELOP SCOPE | Jul 2008 | Sep 2008 | Jul 2008 | Sep 2008
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-IRR | SIBG -SI BOTANICAL GARDEN Site Irrigation | 2 | PRELIMINARY DESIGN | Sep 2008 | Jan 2009 | Sep 2008 | Jan 2009
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-IRR | SIBG -SI BOTANICAL GARDEN Site Irrigation | 3 | FINAL DESIGN | Jan 2009 | Jul 2009 | Jan 2009 | Jul 2009
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-IRR | SIBG -SI BOTANICAL GARDEN Site Irrigation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2009 | Oct 2009 | Jul 2009 | Oct 2009
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-IRR | SIBG -SI BOTANICAL GARDEN Site Irrigation | 5 | CONSTRUCTION TO 25% | Oct 2009 | Feb 2010 | Oct 2009 | Feb 2010
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-IRR | SIBG -SI BOTANICAL GARDEN Site Irrigation | 6 | CONSTRUCTION TO 50% | Feb 2010 | Jun 2010 | Feb 2010 | Jun 2010
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-IRR | SIBG -SI BOTANICAL GARDEN Site Irrigation | 7 | CONSTRUCTION TO 75% | Jun 2010 | Oct 2010 | Jun 2010 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-IRR | SIBG -SI BOTANICAL GARDEN Site Irrigation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2010 | Jan 2011 | Jul 2028 | Sep 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-IRR | SIBG -SI BOTANICAL GARDEN Site Irrigation | 9 | SUBSTANTIAL COMPLETION | Jan 2011 | Mar 2011 | Sep 2028 | Nov 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-IRR | SIBG -SI BOTANICAL GARDEN Site Irrigation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2011 | Apr 2011 | Nov 2028 | Jun 2030
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-05 | SANDY - Blissenbach Marina Demo (Type 3) R160-113M | 1 | DEVELOP SCOPE | Dec 2012 | Feb 2013 | Dec 2012 | Feb 2013
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-05 | SANDY - Blissenbach Marina Demo (Type 3) R160-113M | 2 | DESIGN | Mar 2013 | May 2013 | Mar 2013 | May 2013
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-05 | SANDY - Blissenbach Marina Demo (Type 3) R160-113M | 3 | BID/ REGISTER CONTRACT | May 2013 | Aug 2013 | May 2013 | Aug 2013
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-05 | SANDY - Blissenbach Marina Demo (Type 3) R160-113M | 4 | CONSTRUCTION | Aug 2013 | Aug 2014 | Aug 2013 | Aug 2014
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-05 | SANDY - Blissenbach Marina Demo (Type 3) R160-113M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2014 | Aug 2015 | Aug 2014 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-13 | SANDY - SI Type 2 Plgrd R/C (RG-713M) | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2013
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-13 | SANDY - SI Type 2 Plgrd R/C (RG-713M) | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-13 | SANDY - SI Type 2 Plgrd R/C (RG-713M) | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2013 | Mar 2014
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-13 | SANDY - SI Type 2 Plgrd R/C (RG-713M) | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2015
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-13 | SANDY - SI Type 2 Plgrd R/C (RG-713M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2015 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-16 | Conference House Pk landscape (Type 3 ) R006-114M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | May 2015
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-16 | Conference House Pk landscape (Type 3 ) R006-114M | 2 | DESIGN | Sep 2013 | Dec 2013 | May 2015 | Dec 2016
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-16 | Conference House Pk landscape (Type 3 ) R006-114M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Jun 2017 | May 2018
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-16 | Conference House Pk landscape (Type 3 ) R006-114M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Jun 2018 | Jan 2019
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-16 | Conference House Pk landscape (Type 3 ) R006-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Jan 2019 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-17 | Tappen Park & Dolphin Fountains (Type3) | 1 | DEVELOP SCOPE | Jun 2013 | Aug 2013 | Jun 2011 | Jun 2013
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-17 | Tappen Park & Dolphin Fountains (Type3) | 2 | DESIGN | Aug 2013 | Nov 2013 | Jul 2013 | Mar 2015
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-17 | Tappen Park & Dolphin Fountains (Type3) | 3 | BID/ REGISTER CONTRACT | Nov 2013 | Feb 2014 | Apr 2015 | Jun 2015
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-17 | Tappen Park & Dolphin Fountains (Type3) | 4 | CONSTRUCTION | Feb 2014 | Feb 2015 | Jun 2015 | Jun 2016
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-17 | Tappen Park & Dolphin Fountains (Type3) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2015 | Feb 2016 | Jun 2016 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-18 | SANDY-Midland Beach Protective Berm Emergency | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2013
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-18 | SANDY-Midland Beach Protective Berm Emergency | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-18 | SANDY-Midland Beach Protective Berm Emergency | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2013 | Mar 2014
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-18 | SANDY-Midland Beach Protective Berm Emergency | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Nov 2013 | Apr 2014
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-18 | SANDY-Midland Beach Protective Berm Emergency | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Apr 2014 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-20 | SANDY - Tree removals - Staten Island RG-614M | 1 | DEVELOP SCOPE | Jan 2014 | Mar 2014 | Jan 2009 | Mar 2009
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-20 | SANDY - Tree removals - Staten Island RG-614M | 2 | DESIGN | Apr 2014 | Jun 2014 | Apr 2009 | Jun 2009
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-20 | SANDY - Tree removals - Staten Island RG-614M | 3 | BID/ REGISTER CONTRACT | Jun 2014 | Sep 2014 | Jun 2009 | Sep 2009
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-20 | SANDY - Tree removals - Staten Island RG-614M | 4 | CONSTRUCTION | Sep 2014 | Sep 2015 | Sep 2009 | Sep 2010
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-20 | SANDY - Tree removals - Staten Island RG-614M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2015 | Sep 2016 | Sep 2010 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-24 | Sandy-Seaside Wildlife Nature Pk-reconstruction | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Apr 2023 | Oct 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-24 | Sandy-Seaside Wildlife Nature Pk-reconstruction | 2 | DESIGN | Dec 2016 | Jun 2018 | Oct 2023 | Apr 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-24 | Sandy-Seaside Wildlife Nature Pk-reconstruction | 3 | BID/ REGISTER CONTRACT | Jun 2018 | Mar 2019 | Apr 2025 | Jan 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-24 | Sandy-Seaside Wildlife Nature Pk-reconstruction | 4 | CONSTRUCTION | Mar 2019 | Sep 2020 | Jan 2026 | Jul 2027
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-24 | Sandy-Seaside Wildlife Nature Pk-reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Jul 2027 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-26 | Sandy-R/C of playground at Wolfe's Pond Park | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Dec 2019 | Mar 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-26 | Sandy-R/C of playground at Wolfe's Pond Park | 2 | DESIGN | Sep 2015 | Dec 2015 | Mar 2020 | Jun 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-26 | Sandy-R/C of playground at Wolfe's Pond Park | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Jun 2020 | Sep 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-26 | Sandy-R/C of playground at Wolfe's Pond Park | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Sep 2020 | Sep 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-26 | Sandy-R/C of playground at Wolfe's Pond Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Sep 2021 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-27 | Sandy-Wolfe's Pond Park-R/C of the berm | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Oct 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-27 | Sandy-Wolfe's Pond Park-R/C of the berm | 2 | DESIGN | Dec 2017 | Dec 2018 | Oct 2024 | Oct 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-27 | Sandy-Wolfe's Pond Park-R/C of the berm | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Oct 2025 | Jul 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-27 | Sandy-Wolfe's Pond Park-R/C of the berm | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Jul 2026 | Jul 2027
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-27 | Sandy-Wolfe's Pond Park-R/C of the berm | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Jul 2027 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-28 | Sandy-FDR bdwk & Midland Plgr-R/C of tthe pavements,etc | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Sep 2014
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-28 | Sandy-FDR bdwk & Midland Plgr-R/C of tthe pavements,etc | 2 | DESIGN | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-28 | Sandy-FDR bdwk & Midland Plgr-R/C of tthe pavements,etc | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2014 | Mar 2015
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-28 | Sandy-FDR bdwk & Midland Plgr-R/C of tthe pavements,etc | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-28 | Sandy-FDR bdwk & Midland Plgr-R/C of tthe pavements,etc | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2016 | Dec 2029
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-30 | Sandy-New Dorp Bch Site Restor.R016-115M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Dec 2021 | Mar 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-30 | Sandy-New Dorp Bch Site Restor.R016-115M | 2 | DESIGN | Sep 2015 | Dec 2015 | Mar 2022 | Jun 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-30 | Sandy-New Dorp Bch Site Restor.R016-115M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Jun 2022 | Sep 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-30 | Sandy-New Dorp Bch Site Restor.R016-115M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Sep 2022 | Sep 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-30 | Sandy-New Dorp Bch Site Restor.R016-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Sep 2023 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-32 | Sandy-R/C of S. Bch-Playland Plgr, RG-212M WO 1 | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Dec 2019 | Mar 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-32 | Sandy-R/C of S. Bch-Playland Plgr, RG-212M WO 1 | 2 | DESIGN | Sep 2014 | Dec 2014 | Mar 2020 | Jun 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-32 | Sandy-R/C of S. Bch-Playland Plgr, RG-212M WO 1 | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Jun 2020 | Sep 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-32 | Sandy-R/C of S. Bch-Playland Plgr, RG-212M WO 1 | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Sep 2020 | Sep 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-32 | Sandy-R/C of S. Bch-Playland Plgr, RG-212M WO 1 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Sep 2021 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-33 | Sandy-R/C of S.Bch-SaturnPlgr, RG-212M WO 2 | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2014 | Mar 2015
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-33 | Sandy-R/C of S.Bch-SaturnPlgr, RG-212M WO 2 | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-33 | Sandy-R/C of S.Bch-SaturnPlgr, RG-212M WO 2 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-34 | Sandy-R/C of Faber Plgr, SI RG-212M WO 3 | 2 | DESIGN | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-34 | Sandy-R/C of Faber Plgr, SI RG-212M WO 3 | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2014 | Mar 2015
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-34 | Sandy-R/C of Faber Plgr, SI RG-212M WO 3 | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-34 | Sandy-R/C of Faber Plgr, SI RG-212M WO 3 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-37 | SANDY - BUONO BEACH FOUNTAIN REPAIR - R117-117MA | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2022 | Dec 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-37 | SANDY - BUONO BEACH FOUNTAIN REPAIR - R117-117MA | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2022 | Dec 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-37 | SANDY - BUONO BEACH FOUNTAIN REPAIR - R117-117MA | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2023 | Sep 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-37 | SANDY - BUONO BEACH FOUNTAIN REPAIR - R117-117MA | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2024 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-37 | SANDY - BUONO BEACH FOUNTAIN REPAIR - R117-117MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2025 | Jun 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-41 | Sandy-Lemon Creek Pk -timbler rail RG-212M WO 5 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Mar 2018
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-42 | Sandy-Conference House Barrier Rail RG-212M WO6 | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2017 | Oct 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-42 | Sandy-Conference House Barrier Rail RG-212M WO6 | 2 | DESIGN | Dec 2020 | Dec 2021 | Oct 2024 | Oct 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-42 | Sandy-Conference House Barrier Rail RG-212M WO6 | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Oct 2025 | Jul 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-42 | Sandy-Conference House Barrier Rail RG-212M WO6 | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Jul 2026 | Jul 2027
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-42 | Sandy-Conference House Barrier Rail RG-212M WO6 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Jul 2027 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-43 | Lemon Creek Marina R079-120M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Apr 2020 | Oct 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-43 | Lemon Creek Marina R079-120M | 2 | DESIGN | Dec 2016 | Dec 2018 | Oct 2020 | Oct 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-43 | Lemon Creek Marina R079-120M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Oct 2022 | Jul 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-43 | Lemon Creek Marina R079-120M | 4 | CONSTRUCTION | Sep 2019 | Sep 2022 | Jul 2023 | Jul 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-43 | Lemon Creek Marina R079-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2024 | Jul 2026 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-44 | New Dorp Pk./Corp. Kivlehan Pk. | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-44 | New Dorp Pk./Corp. Kivlehan Pk. | 2 | DESIGN | Dec 2016 | Jun 2018 | Dec 2016 | Jun 2018
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-44 | New Dorp Pk./Corp. Kivlehan Pk. | 3 | BID/ REGISTER CONTRACT | Jun 2018 | Mar 2019 | Jun 2018 | Mar 2019
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-44 | New Dorp Pk./Corp. Kivlehan Pk. | 4 | CONSTRUCTION | Mar 2019 | Sep 2020 | Mar 2019 | Sep 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-44 | New Dorp Pk./Corp. Kivlehan Pk. | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2028
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-47 | Midland Beach Bath House | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-47 | Midland Beach Bath House | 2 | DESIGN | Dec 2017 | Dec 2019 | Dec 2017 | Dec 2019
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-47 | Midland Beach Bath House | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-47 | Midland Beach Bath House | 4 | CONSTRUCTION | Sep 2020 | Sep 2023 | Sep 2020 | Sep 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-47 | Midland Beach Bath House | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2025 | Sep 2023 | Sep 2027
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-48 | Five Parks in SI | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jun 2016 | Dec 2016
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-48 | Five Parks in SI | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2016 | Dec 2017
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-48 | Five Parks in SI | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2017 | Sep 2018
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-48 | Five Parks in SI | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2018 | Sep 2019
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-48 | Five Parks in SI | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2019 | Jun 2029
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-49 | Fairview Park Public Restroom Construction | 1 | DEVELOP SCOPE | Aug 2017 | Jan 2018 | Aug 2017 | Jan 2018
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-49 | Fairview Park Public Restroom Construction | 2 | DESIGN | Jan 2018 | Jul 2019 | Jan 2018 | Jul 2019
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-49 | Fairview Park Public Restroom Construction | 3 | BID/ REGISTER CONTRACT | Jul 2019 | Apr 2020 | Jul 2019 | Apr 2020
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-49 | Fairview Park Public Restroom Construction | 4 | CONSTRUCTION | Apr 2020 | Oct 2021 | Apr 2020 | Oct 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-49 | Fairview Park Public Restroom Construction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2021 | Oct 2022 | Oct 2021 | Jun 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-50 | Fairview Park Landscape Construction R153-118M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Apr 2022 | Oct 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-50 | Fairview Park Landscape Construction R153-118M | 2 | DESIGN | Dec 2017 | Dec 2018 | Oct 2022 | Oct 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-50 | Fairview Park Landscape Construction R153-118M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Oct 2023 | Jun 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-50 | Fairview Park Landscape Construction R153-118M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Jul 2024 | Jun 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-50 | Fairview Park Landscape Construction R153-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Jul 2025 | Jun 2029
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-52 | Lemon Creek Marina (406 Buildings) Conduit Reconstruction | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-52 | Lemon Creek Marina (406 Buildings) Conduit Reconstruction | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-52 | Lemon Creek Marina (406 Buildings) Conduit Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-52 | Lemon Creek Marina (406 Buildings) Conduit Reconstruction | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-52 | Lemon Creek Marina (406 Buildings) Conduit Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-53 | Seaside Nature Park Conduit Reconstruction | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-53 | Seaside Nature Park Conduit Reconstruction | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-53 | Seaside Nature Park Conduit Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-53 | Seaside Nature Park Conduit Reconstruction | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-53 | Seaside Nature Park Conduit Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-54 | Midland Beach Fishing Pier Parking Lot Conduit Recon. | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-54 | Midland Beach Fishing Pier Parking Lot Conduit Recon. | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-54 | Midland Beach Fishing Pier Parking Lot Conduit Recon. | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-54 | Midland Beach Fishing Pier Parking Lot Conduit Recon. | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-54 | Midland Beach Fishing Pier Parking Lot Conduit Recon. | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-55 | Detective Russell Timoshenko Synthetic Turf Field | 1 | DEVELOP SCOPE | Jun 2023 | Dec 2023 | Jun 2023 | Dec 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-55 | Detective Russell Timoshenko Synthetic Turf Field | 2 | DESIGN | Dec 2023 | Dec 2024 | Dec 2023 | Dec 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-55 | Detective Russell Timoshenko Synthetic Turf Field | 3 | BID/ REGISTER CONTRACT | Dec 2024 | Sep 2025 | Dec 2024 | Sep 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-55 | Detective Russell Timoshenko Synthetic Turf Field | 4 | CONSTRUCTION | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-55 | Detective Russell Timoshenko Synthetic Turf Field | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Sep 2027
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-56 | Alice Austen Park Revetment Reconstruction (Hurricane Sandy) | 1 | DEVELOP SCOPE | Feb 2022 | Jul 2022 | Feb 2022 | Jul 2022
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-56 | Alice Austen Park Revetment Reconstruction (Hurricane Sandy) | 2 | DESIGN | Jul 2022 | Jul 2023 | Jul 2022 | Jul 2023
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-56 | Alice Austen Park Revetment Reconstruction (Hurricane Sandy) | 3 | BID/ REGISTER CONTRACT | Jul 2023 | Apr 2024 | Jul 2023 | Apr 2024
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-56 | Alice Austen Park Revetment Reconstruction (Hurricane Sandy) | 4 | CONSTRUCTION | Apr 2024 | Apr 2025 | Apr 2024 | Apr 2025
20231026 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-56 | Alice Austen Park Revetment Reconstruction (Hurricane Sandy) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2025 | Apr 2026 | Apr 2025 | Apr 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301LL | 130 STUYVESANT PL - FACADE REPAIRS LOCAL LAW 11 | 1 | DEVELOP SCOPE | Mar 2018 | May 2018 | Mar 2018 | May 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301LL | 130 STUYVESANT PL - FACADE REPAIRS LOCAL LAW 11 | 2 | PRELIMINARY DESIGN | May 2018 | Sep 2018 | May 2018 | Sep 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301LL | 130 STUYVESANT PL - FACADE REPAIRS LOCAL LAW 11 | 3 | FINAL DESIGN | Sep 2018 | Mar 2019 | Sep 2018 | Mar 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301LL | 130 STUYVESANT PL - FACADE REPAIRS LOCAL LAW 11 | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2019 | Jun 2019 | Mar 2019 | Jun 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301LL | 130 STUYVESANT PL - FACADE REPAIRS LOCAL LAW 11 | 5 | CONSTRUCTION TO 25% | Jun 2019 | Oct 2019 | Jun 2019 | Oct 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301LL | 130 STUYVESANT PL - FACADE REPAIRS LOCAL LAW 11 | 6 | CONSTRUCTION TO 50% | Oct 2019 | Feb 2020 | Oct 2019 | Feb 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301LL | 130 STUYVESANT PL - FACADE REPAIRS LOCAL LAW 11 | 7 | CONSTRUCTION TO 75% | Feb 2020 | Jun 2020 | Feb 2020 | Jun 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301LL | 130 STUYVESANT PL - FACADE REPAIRS LOCAL LAW 11 | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301LL | 130 STUYVESANT PL - FACADE REPAIRS LOCAL LAW 11 | 9 | SUBSTANTIAL COMPLETION | Sep 2020 | Nov 2020 | Sep 2020 | Nov 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301LL | 130 STUYVESANT PL - FACADE REPAIRS LOCAL LAW 11 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2020 | Dec 2020 | Nov 2020 | Jun 2025
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | 1 | DEVELOP SCOPE | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | 2 | PRELIMINARY DESIGN | Dec 2014 | Apr 2015 | Dec 2014 | Apr 2015
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | 3 | FINAL DESIGN | Apr 2015 | Oct 2015 | Apr 2015 | Aug 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2015 | Jan 2016 | Aug 2018 | Nov 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | 5 | CONSTRUCTION TO 25% | Jan 2016 | May 2016 | Nov 2018 | Mar 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | 6 | CONSTRUCTION TO 50% | May 2016 | Sep 2016 | Mar 2019 | Jul 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | 7 | CONSTRUCTION TO 75% | Sep 2016 | Jan 2017 | Jul 2019 | Nov 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2017 | Apr 2017 | Nov 2019 | Feb 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | 9 | SUBSTANTIAL COMPLETION | Apr 2017 | Jun 2017 | Feb 2020 | Apr 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2017 | Jul 2017 | Apr 2020 | Apr 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | 11 | PROJECT START | Jun 2017 | Jul 2017 | May 2023 | May 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | 12 | DESIGN START | Jun 2017 | Jul 2017 | May 2023 | May 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | 13 | DESIGN COMPLETION | Jun 2017 | Jul 2017 | May 2023 | May 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | 14 | CONSTRUCTION START | Jun 2017 | Jul 2017 | May 2023 | May 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | 15 | CONSTRUCTION COMPLETION | Jun 2017 | Jul 2017 | May 2023 | Jun 2025
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO302ST | 18 RICHMOND TERRACE - EXTERIOR STEPS RECONSTRUCTION | 1 | DEVELOP SCOPE | Mar 2019 | May 2019 | Jan 2019 | Apr 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO302ST | 18 RICHMOND TERRACE - EXTERIOR STEPS RECONSTRUCTION | 2 | PRELIMINARY DESIGN | May 2019 | Sep 2019 | Apr 2019 | Aug 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO302ST | 18 RICHMOND TERRACE - EXTERIOR STEPS RECONSTRUCTION | 3 | FINAL DESIGN | Sep 2019 | Mar 2020 | Aug 2019 | Feb 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO302ST | 18 RICHMOND TERRACE - EXTERIOR STEPS RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Jun 2020 | Feb 2020 | May 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO302ST | 18 RICHMOND TERRACE - EXTERIOR STEPS RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | Jun 2020 | Oct 2020 | May 2020 | Sep 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO302ST | 18 RICHMOND TERRACE - EXTERIOR STEPS RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | Oct 2020 | Feb 2021 | Sep 2020 | Jan 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO302ST | 18 RICHMOND TERRACE - EXTERIOR STEPS RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | Feb 2021 | Jun 2021 | Jan 2021 | May 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO302ST | 18 RICHMOND TERRACE - EXTERIOR STEPS RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2021 | Sep 2021 | May 2021 | Aug 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO302ST | 18 RICHMOND TERRACE - EXTERIOR STEPS RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | Sep 2021 | Nov 2021 | Aug 2021 | Oct 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO302ST | 18 RICHMOND TERRACE - EXTERIOR STEPS RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2021 | Dec 2021 | Oct 2021 | Apr 2027
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER22 | Reconstruction of Existing Sewers, Staten Island | 1 | DEVELOP SCOPE | Jan 2021 | Apr 2021 | Jan 2021 | Apr 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER22 | Reconstruction of Existing Sewers, Staten Island | 2 | PRELIMINARY DESIGN | Apr 2021 | Aug 2021 | Apr 2021 | Aug 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER22 | Reconstruction of Existing Sewers, Staten Island | 3 | FINAL DESIGN | Aug 2021 | Feb 2022 | Aug 2021 | Feb 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER22 | Reconstruction of Existing Sewers, Staten Island | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2022 | May 2022 | Feb 2022 | May 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER22 | Reconstruction of Existing Sewers, Staten Island | 5 | CONSTRUCTION TO 25% | May 2022 | Sep 2022 | May 2022 | Sep 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER22 | Reconstruction of Existing Sewers, Staten Island | 6 | CONSTRUCTION TO 50% | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER22 | Reconstruction of Existing Sewers, Staten Island | 7 | CONSTRUCTION TO 75% | Jan 2023 | May 2023 | Jan 2023 | May 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER22 | Reconstruction of Existing Sewers, Staten Island | 8 | ORIGINAL EQUIP & FURNISHING | May 2023 | Aug 2023 | May 2023 | Aug 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER22 | Reconstruction of Existing Sewers, Staten Island | 9 | SUBSTANTIAL COMPLETION | Aug 2023 | Sep 2023 | Aug 2023 | Sep 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER22 | Reconstruction of Existing Sewers, Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2023 | Oct 2023 | Oct 2023 | Oct 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER23 | Reconstruction of Existing Sewers, Staten Island | 1 | DEVELOP SCOPE | Sep 2021 | Dec 2021 | Sep 2021 | Dec 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER23 | Reconstruction of Existing Sewers, Staten Island | 2 | PRELIMINARY DESIGN | Dec 2021 | Apr 2022 | Dec 2021 | Apr 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER23 | Reconstruction of Existing Sewers, Staten Island | 3 | FINAL DESIGN | Apr 2022 | Oct 2022 | Apr 2022 | Oct 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER23 | Reconstruction of Existing Sewers, Staten Island | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER23 | Reconstruction of Existing Sewers, Staten Island | 5 | CONSTRUCTION TO 25% | Jan 2023 | May 2023 | Jan 2023 | May 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER23 | Reconstruction of Existing Sewers, Staten Island | 6 | CONSTRUCTION TO 50% | May 2023 | Sep 2023 | May 2023 | Sep 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER23 | Reconstruction of Existing Sewers, Staten Island | 7 | CONSTRUCTION TO 75% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER23 | Reconstruction of Existing Sewers, Staten Island | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2024 | Apr 2024 | Jan 2024 | Apr 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER23 | Reconstruction of Existing Sewers, Staten Island | 9 | SUBSTANTIAL COMPLETION | Apr 2024 | Jun 2024 | Apr 2024 | Jun 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER23 | Reconstruction of Existing Sewers, Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2024 | Jul 2024 | Jun 2024 | Jul 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER24 | Reconstruction of Existing Sewers, Staten Island | 1 | DEVELOP SCOPE | Jun 2024 | Aug 2024 | Jun 2024 | Aug 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER24 | Reconstruction of Existing Sewers, Staten Island | 2 | PRELIMINARY DESIGN | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER24 | Reconstruction of Existing Sewers, Staten Island | 3 | FINAL DESIGN | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER24 | Reconstruction of Existing Sewers, Staten Island | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER24 | Reconstruction of Existing Sewers, Staten Island | 5 | CONSTRUCTION TO 25% | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER24 | Reconstruction of Existing Sewers, Staten Island | 6 | CONSTRUCTION TO 50% | Jan 2026 | May 2026 | Jan 2026 | May 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER24 | Reconstruction of Existing Sewers, Staten Island | 7 | CONSTRUCTION TO 75% | May 2026 | Sep 2026 | May 2026 | Sep 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER24 | Reconstruction of Existing Sewers, Staten Island | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2026 | Dec 2026 | Sep 2026 | Dec 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER24 | Reconstruction of Existing Sewers, Staten Island | 9 | SUBSTANTIAL COMPLETION | Dec 2026 | Feb 2027 | Dec 2026 | Feb 2027
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER24 | Reconstruction of Existing Sewers, Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2027 | Mar 2027 | Feb 2027 | Mar 2027
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM18MHCC | Mariner's Harbor Community Center | 1 | PROJECT START | Feb 2019 | Feb 2019 | Feb 2019 | Feb 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM18MHCC | Mariner's Harbor Community Center | 2 | DESIGN START | Mar 2019 | Jul 2019 | Mar 2019 | Jul 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM18MHCC | Mariner's Harbor Community Center | 3 | DESIGN COMPLETION | Jul 2019 | Jul 2020 | Jul 2019 | Jul 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM18MHCC | Mariner's Harbor Community Center | 4 | CONSTRUCTION START | Jul 2020 | Apr 2021 | Jul 2020 | Apr 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM18MHCC | Mariner's Harbor Community Center | 5 | CONSTRUCTION COMPLETION | Apr 2021 | Apr 2022 | Apr 2021 | Jun 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115HHFA | Hospitality at 100 Central Ave., 10301 - Fire Alarm Upgrade | 1 | PROJECT START | Mar 2016 | Mar 2016 | Mar 2016 | Mar 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115HHFA | Hospitality at 100 Central Ave., 10301 - Fire Alarm Upgrade | 2 | DESIGN START | Apr 2016 | Jul 2016 | Apr 2016 | Jul 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115HHFA | Hospitality at 100 Central Ave., 10301 - Fire Alarm Upgrade | 3 | DESIGN COMPLETION | Jul 2016 | Jun 2017 | Jul 2016 | Jun 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115HHFA | Hospitality at 100 Central Ave., 10301 - Fire Alarm Upgrade | 4 | CONSTRUCTION START | Jul 2017 | Oct 2017 | Jul 2017 | Oct 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115HHFA | Hospitality at 100 Central Ave., 10301 - Fire Alarm Upgrade | 5 | CONSTRUCTION COMPLETION | Nov 2017 | Jun 2023 | Nov 2017 | Jun 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82SIABE | REHAB OF THE STATEN ISLAND ANIMAL SHELTER | 1 | PROJECT START | Dec 2008 | Dec 2008 | Dec 2008 | Dec 2008
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82SIABE | REHAB OF THE STATEN ISLAND ANIMAL SHELTER | 2 | DESIGN START | Dec 2008 | May 2009 | Dec 2008 | May 2009
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82SIABE | REHAB OF THE STATEN ISLAND ANIMAL SHELTER | 3 | DESIGN COMPLETION | May 2009 | May 2010 | May 2009 | May 2010
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82SIABE | REHAB OF THE STATEN ISLAND ANIMAL SHELTER | 4 | CONSTRUCTION START | Jun 2010 | Dec 2010 | Jun 2010 | Dec 2010
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82SIABE | REHAB OF THE STATEN ISLAND ANIMAL SHELTER | 5 | CONSTRUCTION COMPLETION | Dec 2010 | Jun 2011 | Dec 2010 | Jun 2025
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021RC | Non-Standard Installs - Staten Island | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2023 | Sep 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021RC | Non-Standard Installs - Staten Island | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2023 | Jan 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021RC | Non-Standard Installs - Staten Island | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2024 | Jul 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021RC | Non-Standard Installs - Staten Island | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2024 | Oct 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021RC | Non-Standard Installs - Staten Island | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2024 | Feb 2025
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021RC | Non-Standard Installs - Staten Island | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2025 | Jun 2025
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021RC | Non-Standard Installs - Staten Island | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2025 | Oct 2025
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021RC | Non-Standard Installs - Staten Island | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2025 | Jan 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021RC | Non-Standard Installs - Staten Island | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2026 | Mar 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021RC | Non-Standard Installs - Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2026 | Apr 2033
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00505 | VICTORY BLVD AND MANOR ROAD INTERSECTION IMPROVEMENT | 1 | DEVELOP SCOPE | Mar 2011 | May 2011 | Mar 2011 | May 2011
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00505 | VICTORY BLVD AND MANOR ROAD INTERSECTION IMPROVEMENT | 2 | PRELIMINARY DESIGN | May 2011 | Sep 2011 | May 2011 | Sep 2011
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00505 | VICTORY BLVD AND MANOR ROAD INTERSECTION IMPROVEMENT | 3 | FINAL DESIGN | Sep 2011 | Mar 2012 | Sep 2011 | Mar 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00505 | VICTORY BLVD AND MANOR ROAD INTERSECTION IMPROVEMENT | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2012 | Jun 2012 | Mar 2016 | Jun 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00505 | VICTORY BLVD AND MANOR ROAD INTERSECTION IMPROVEMENT | 5 | CONSTRUCTION TO 25% | Jun 2012 | Oct 2012 | Jun 2016 | Dec 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00505 | VICTORY BLVD AND MANOR ROAD INTERSECTION IMPROVEMENT | 6 | CONSTRUCTION TO 50% | Oct 2012 | Feb 2013 | Dec 2016 | Jun 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00505 | VICTORY BLVD AND MANOR ROAD INTERSECTION IMPROVEMENT | 7 | CONSTRUCTION TO 75% | Feb 2013 | Jun 2013 | Jun 2017 | Dec 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00505 | VICTORY BLVD AND MANOR ROAD INTERSECTION IMPROVEMENT | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2013 | Sep 2013 | Dec 2017 | Mar 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00505 | VICTORY BLVD AND MANOR ROAD INTERSECTION IMPROVEMENT | 9 | SUBSTANTIAL COMPLETION | Sep 2013 | Nov 2013 | Mar 2018 | Jun 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00505 | VICTORY BLVD AND MANOR ROAD INTERSECTION IMPROVEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2013 | Dec 2013 | Jul 2022 | May 2029
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00508 | AMBOY ROAD IMPROVEMENTS AT ELTINGVILLE CORRIDOR | 1 | DEVELOP SCOPE | Jun 2011 | Sep 2011 | Jun 2011 | Sep 2011
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00508 | AMBOY ROAD IMPROVEMENTS AT ELTINGVILLE CORRIDOR | 2 | PRELIMINARY DESIGN | Sep 2011 | Jan 2012 | Sep 2011 | Jan 2012
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00508 | AMBOY ROAD IMPROVEMENTS AT ELTINGVILLE CORRIDOR | 3 | FINAL DESIGN | Jan 2012 | Jul 2012 | Jan 2012 | Mar 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00508 | AMBOY ROAD IMPROVEMENTS AT ELTINGVILLE CORRIDOR | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2012 | Oct 2012 | Mar 2016 | Jun 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00508 | AMBOY ROAD IMPROVEMENTS AT ELTINGVILLE CORRIDOR | 5 | CONSTRUCTION TO 25% | Oct 2012 | Feb 2013 | Jun 2016 | Dec 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00508 | AMBOY ROAD IMPROVEMENTS AT ELTINGVILLE CORRIDOR | 6 | CONSTRUCTION TO 50% | Feb 2013 | Jun 2013 | Dec 2016 | Jun 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00508 | AMBOY ROAD IMPROVEMENTS AT ELTINGVILLE CORRIDOR | 7 | CONSTRUCTION TO 75% | Jun 2013 | Oct 2013 | Jun 2017 | Dec 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00508 | AMBOY ROAD IMPROVEMENTS AT ELTINGVILLE CORRIDOR | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2013 | Jan 2014 | Dec 2017 | Mar 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00508 | AMBOY ROAD IMPROVEMENTS AT ELTINGVILLE CORRIDOR | 9 | SUBSTANTIAL COMPLETION | Jan 2014 | Mar 2014 | Mar 2018 | May 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00508 | AMBOY ROAD IMPROVEMENTS AT ELTINGVILLE CORRIDOR | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2014 | Apr 2014 | May 2018 | Dec 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00508 | AMBOY ROAD IMPROVEMENTS AT ELTINGVILLE CORRIDOR | 11 | PROJECT START | Mar 2014 | Apr 2014 | Dec 2022 | Dec 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00508 | AMBOY ROAD IMPROVEMENTS AT ELTINGVILLE CORRIDOR | 12 | DESIGN START | Mar 2014 | Apr 2014 | Dec 2022 | Dec 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00508 | AMBOY ROAD IMPROVEMENTS AT ELTINGVILLE CORRIDOR | 13 | DESIGN COMPLETION | Mar 2014 | Apr 2014 | Dec 2022 | Dec 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00508 | AMBOY ROAD IMPROVEMENTS AT ELTINGVILLE CORRIDOR | 14 | CONSTRUCTION START | Mar 2014 | Apr 2014 | Dec 2022 | Dec 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00508 | AMBOY ROAD IMPROVEMENTS AT ELTINGVILLE CORRIDOR | 15 | CONSTRUCTION COMPLETION | Mar 2014 | Apr 2014 | Dec 2022 | Dec 2033
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00510 | Woodrow Rd Improvements btw Gladwin Ave & Veterans Rd East | 1 | DEVELOP SCOPE | Jun 2013 | Sep 2013 | Jun 2013 | Sep 2013
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00510 | Woodrow Rd Improvements btw Gladwin Ave & Veterans Rd East | 2 | PRELIMINARY DESIGN | Sep 2013 | Jan 2014 | Sep 2013 | Sep 2014
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00510 | Woodrow Rd Improvements btw Gladwin Ave & Veterans Rd East | 3 | FINAL DESIGN | Jan 2014 | Jul 2014 | Sep 2014 | Sep 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00510 | Woodrow Rd Improvements btw Gladwin Ave & Veterans Rd East | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2014 | Oct 2014 | Sep 2017 | Sep 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00510 | Woodrow Rd Improvements btw Gladwin Ave & Veterans Rd East | 5 | CONSTRUCTION TO 25% | Oct 2014 | Feb 2015 | Sep 2017 | Sep 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00510 | Woodrow Rd Improvements btw Gladwin Ave & Veterans Rd East | 6 | CONSTRUCTION TO 50% | Feb 2015 | Jun 2015 | Sep 2017 | Sep 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00510 | Woodrow Rd Improvements btw Gladwin Ave & Veterans Rd East | 7 | CONSTRUCTION TO 75% | Jun 2015 | Oct 2015 | Sep 2017 | Sep 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00510 | Woodrow Rd Improvements btw Gladwin Ave & Veterans Rd East | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2015 | Jan 2016 | Sep 2017 | Sep 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00510 | Woodrow Rd Improvements btw Gladwin Ave & Veterans Rd East | 9 | SUBSTANTIAL COMPLETION | Jan 2016 | Mar 2016 | Sep 2017 | Sep 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00510 | Woodrow Rd Improvements btw Gladwin Ave & Veterans Rd East | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Apr 2016 | Sep 2017 | Jun 2032
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00511 | Travis Avenue Widening, SER200322 | 1 | DEVELOP SCOPE | Jun 2013 | Sep 2013 | Jun 2013 | Sep 2013
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00511 | Travis Avenue Widening, SER200322 | 2 | PRELIMINARY DESIGN | Sep 2013 | Jan 2014 | Sep 2013 | Jan 2014
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00511 | Travis Avenue Widening, SER200322 | 3 | FINAL DESIGN | Jan 2014 | Jul 2014 | Jan 2014 | Mar 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00511 | Travis Avenue Widening, SER200322 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2014 | Oct 2014 | Mar 2017 | Jun 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00511 | Travis Avenue Widening, SER200322 | 5 | CONSTRUCTION TO 25% | Oct 2014 | Feb 2015 | Jun 2017 | Dec 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00511 | Travis Avenue Widening, SER200322 | 6 | CONSTRUCTION TO 50% | Feb 2015 | Jun 2015 | Dec 2017 | Jun 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00511 | Travis Avenue Widening, SER200322 | 7 | CONSTRUCTION TO 75% | Jun 2015 | Oct 2015 | Jun 2018 | Dec 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00511 | Travis Avenue Widening, SER200322 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2015 | Jan 2016 | Dec 2018 | Mar 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00511 | Travis Avenue Widening, SER200322 | 9 | SUBSTANTIAL COMPLETION | Jan 2016 | Mar 2016 | Mar 2019 | May 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00511 | Travis Avenue Widening, SER200322 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Apr 2016 | May 2019 | Mar 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00511 | Travis Avenue Widening, SER200322 | 11 | PROJECT START | Mar 2016 | Apr 2016 | Mar 2024 | Mar 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00511 | Travis Avenue Widening, SER200322 | 12 | DESIGN START | Mar 2016 | Apr 2016 | Mar 2024 | Mar 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00511 | Travis Avenue Widening, SER200322 | 13 | DESIGN COMPLETION | Mar 2016 | Apr 2016 | Mar 2024 | Mar 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00511 | Travis Avenue Widening, SER200322 | 14 | CONSTRUCTION START | Mar 2016 | Apr 2016 | Mar 2024 | Mar 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00511 | Travis Avenue Widening, SER200322 | 15 | CONSTRUCTION COMPLETION | Mar 2016 | Apr 2016 | Mar 2024 | Jun 2032
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00512 | Richmond Valley Road | 1 | DEVELOP SCOPE | Mar 2016 | May 2016 | Mar 2016 | May 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00512 | Richmond Valley Road | 2 | PRELIMINARY DESIGN | May 2016 | Sep 2016 | May 2016 | Sep 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00512 | Richmond Valley Road | 3 | FINAL DESIGN | Sep 2016 | Mar 2017 | Sep 2016 | Mar 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00512 | Richmond Valley Road | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2017 | Jun 2017 | Mar 2017 | Jun 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00512 | Richmond Valley Road | 5 | CONSTRUCTION TO 25% | Jun 2017 | Oct 2017 | Jun 2017 | Oct 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00512 | Richmond Valley Road | 6 | CONSTRUCTION TO 50% | Oct 2017 | Feb 2018 | Oct 2017 | Feb 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00512 | Richmond Valley Road | 7 | CONSTRUCTION TO 75% | Feb 2018 | Jun 2018 | Feb 2018 | Jun 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00512 | Richmond Valley Road | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00512 | Richmond Valley Road | 9 | SUBSTANTIAL COMPLETION | Sep 2018 | Nov 2018 | Sep 2018 | Nov 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00512 | Richmond Valley Road | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2018 | Dec 2018 | Nov 2018 | Sep 2032
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B1 | TODT HILL ROAD - CIRCLE RD, SER200285 | 1 | DEVELOP SCOPE | Feb 2008 | May 2008 | Feb 2008 | May 2008
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B1 | TODT HILL ROAD - CIRCLE RD, SER200285 | 2 | PRELIMINARY DESIGN | May 2008 | Sep 2008 | May 2008 | Sep 2008
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B1 | TODT HILL ROAD - CIRCLE RD, SER200285 | 3 | FINAL DESIGN | Sep 2008 | Mar 2009 | Sep 2008 | Mar 2009
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B1 | TODT HILL ROAD - CIRCLE RD, SER200285 | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2009 | Jun 2009 | Nov 2011 | Feb 2012
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B1 | TODT HILL ROAD - CIRCLE RD, SER200285 | 5 | CONSTRUCTION TO 25% | Jun 2009 | Oct 2009 | Feb 2012 | Feb 2012
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B1 | TODT HILL ROAD - CIRCLE RD, SER200285 | 6 | CONSTRUCTION TO 50% | Oct 2009 | Feb 2010 | Feb 2012 | Feb 2012
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B1 | TODT HILL ROAD - CIRCLE RD, SER200285 | 7 | CONSTRUCTION TO 75% | Feb 2010 | Jun 2010 | Feb 2012 | Feb 2012
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B1 | TODT HILL ROAD - CIRCLE RD, SER200285 | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2010 | Sep 2010 | Feb 2012 | Feb 2012
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B1 | TODT HILL ROAD - CIRCLE RD, SER200285 | 9 | SUBSTANTIAL COMPLETION | Sep 2010 | Nov 2010 | Feb 2012 | Feb 2012
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B1 | TODT HILL ROAD - CIRCLE RD, SER200285 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2010 | Dec 2010 | Feb 2014 | Jun 2035
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140A | ARTHUR KILL ROAD (PHASE I) - CLARKE AVE, RICHMOD AV, RED-366 | 1 | DEVELOP SCOPE | May 2004 | Aug 2004 | May 2004 | Aug 2004
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140A | ARTHUR KILL ROAD (PHASE I) - CLARKE AVE, RICHMOD AV, RED-366 | 2 | PRELIMINARY DESIGN | Aug 2004 | Dec 2004 | Aug 2004 | Dec 2004
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140A | ARTHUR KILL ROAD (PHASE I) - CLARKE AVE, RICHMOD AV, RED-366 | 3 | FINAL DESIGN | Dec 2004 | Jun 2005 | Dec 2004 | Jun 2005
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140A | ARTHUR KILL ROAD (PHASE I) - CLARKE AVE, RICHMOD AV, RED-366 | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2005 | Sep 2005 | Jun 2005 | Jun 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140A | ARTHUR KILL ROAD (PHASE I) - CLARKE AVE, RICHMOD AV, RED-366 | 5 | CONSTRUCTION TO 25% | Sep 2005 | Jan 2006 | Jun 2022 | Jun 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140A | ARTHUR KILL ROAD (PHASE I) - CLARKE AVE, RICHMOD AV, RED-366 | 6 | CONSTRUCTION TO 50% | Jan 2006 | May 2006 | Jun 2022 | Jun 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140A | ARTHUR KILL ROAD (PHASE I) - CLARKE AVE, RICHMOD AV, RED-366 | 7 | CONSTRUCTION TO 75% | May 2006 | Sep 2006 | Jun 2022 | Jun 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140A | ARTHUR KILL ROAD (PHASE I) - CLARKE AVE, RICHMOD AV, RED-366 | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2006 | Dec 2006 | Jun 2022 | Jun 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140A | ARTHUR KILL ROAD (PHASE I) - CLARKE AVE, RICHMOD AV, RED-366 | 9 | SUBSTANTIAL COMPLETION | Dec 2006 | Feb 2007 | Jun 2022 | Jun 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140A | ARTHUR KILL ROAD (PHASE I) - CLARKE AVE, RICHMOD AV, RED-366 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2007 | Mar 2007 | Nov 2023 | Dec 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140A | ARTHUR KILL ROAD (PHASE I) - CLARKE AVE, RICHMOD AV, RED-366 | 11 | PROJECT START | Feb 2007 | Mar 2007 | Dec 2023 | Dec 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140A | ARTHUR KILL ROAD (PHASE I) - CLARKE AVE, RICHMOD AV, RED-366 | 12 | DESIGN START | Feb 2007 | Mar 2007 | Dec 2023 | Dec 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140A | ARTHUR KILL ROAD (PHASE I) - CLARKE AVE, RICHMOD AV, RED-366 | 13 | DESIGN COMPLETION | Feb 2007 | Mar 2007 | Dec 2023 | Dec 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140A | ARTHUR KILL ROAD (PHASE I) - CLARKE AVE, RICHMOD AV, RED-366 | 14 | CONSTRUCTION START | Feb 2007 | Mar 2007 | Dec 2023 | Dec 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140A | ARTHUR KILL ROAD (PHASE I) - CLARKE AVE, RICHMOD AV, RED-366 | 15 | CONSTRUCTION COMPLETION | Feb 2007 | Mar 2007 | Dec 2023 | Dec 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1160 | RE- ALIGN ROCKLAND AVE AT MANOR RD/MEISNER AVE, SE-740B | 1 | DEVELOP SCOPE | Jul 2003 | Sep 2003 | Jul 2003 | Sep 2003
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1160 | RE- ALIGN ROCKLAND AVE AT MANOR RD/MEISNER AVE, SE-740B | 2 | PRELIMINARY DESIGN | Sep 2003 | Jan 2004 | Sep 2003 | Jan 2004
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1160 | RE- ALIGN ROCKLAND AVE AT MANOR RD/MEISNER AVE, SE-740B | 3 | FINAL DESIGN | Jan 2004 | Jul 2004 | Jan 2004 | Jul 2004
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1160 | RE- ALIGN ROCKLAND AVE AT MANOR RD/MEISNER AVE, SE-740B | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2004 | Oct 2004 | Mar 2022 | Jun 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1160 | RE- ALIGN ROCKLAND AVE AT MANOR RD/MEISNER AVE, SE-740B | 5 | CONSTRUCTION TO 25% | Oct 2004 | Feb 2005 | Jun 2022 | Jun 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1160 | RE- ALIGN ROCKLAND AVE AT MANOR RD/MEISNER AVE, SE-740B | 6 | CONSTRUCTION TO 50% | Feb 2005 | Jun 2005 | Jun 2022 | Jun 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1160 | RE- ALIGN ROCKLAND AVE AT MANOR RD/MEISNER AVE, SE-740B | 7 | CONSTRUCTION TO 75% | Jun 2005 | Oct 2005 | Jun 2022 | Jun 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1160 | RE- ALIGN ROCKLAND AVE AT MANOR RD/MEISNER AVE, SE-740B | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2005 | Jan 2006 | Jun 2022 | Jun 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1160 | RE- ALIGN ROCKLAND AVE AT MANOR RD/MEISNER AVE, SE-740B | 9 | SUBSTANTIAL COMPLETION | Jan 2006 | Mar 2006 | Jun 2022 | Jun 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1160 | RE- ALIGN ROCKLAND AVE AT MANOR RD/MEISNER AVE, SE-740B | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2006 | Apr 2006 | Jun 2022 | Jun 2032
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR300-03 | ROAD WIDENING AT SOUTH AVENUE AND FOREST AVENUE | 1 | DEVELOP SCOPE | Jun 2010 | Aug 2010 | Jun 2010 | Aug 2010
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR300-03 | ROAD WIDENING AT SOUTH AVENUE AND FOREST AVENUE | 2 | PRELIMINARY DESIGN | Aug 2010 | Dec 2010 | Aug 2010 | Dec 2010
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR300-03 | ROAD WIDENING AT SOUTH AVENUE AND FOREST AVENUE | 3 | FINAL DESIGN | Dec 2010 | Jun 2011 | Dec 2010 | May 2015
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR300-03 | ROAD WIDENING AT SOUTH AVENUE AND FOREST AVENUE | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2011 | Sep 2011 | May 2015 | Aug 2015
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR300-03 | ROAD WIDENING AT SOUTH AVENUE AND FOREST AVENUE | 5 | CONSTRUCTION TO 25% | Sep 2011 | Jan 2012 | Aug 2015 | Feb 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR300-03 | ROAD WIDENING AT SOUTH AVENUE AND FOREST AVENUE | 6 | CONSTRUCTION TO 50% | Jan 2012 | May 2012 | Feb 2016 | Aug 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR300-03 | ROAD WIDENING AT SOUTH AVENUE AND FOREST AVENUE | 7 | CONSTRUCTION TO 75% | May 2012 | Sep 2012 | Feb 2016 | Feb 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR300-03 | ROAD WIDENING AT SOUTH AVENUE AND FOREST AVENUE | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2012 | Dec 2012 | Feb 2017 | May 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR300-03 | ROAD WIDENING AT SOUTH AVENUE AND FOREST AVENUE | 9 | SUBSTANTIAL COMPLETION | Dec 2012 | Feb 2013 | May 2017 | Jul 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR300-03 | ROAD WIDENING AT SOUTH AVENUE AND FOREST AVENUE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2013 | Mar 2013 | Jul 2017 | Jun 2030
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR669C | RECONSTRUCTION OF ROMA, HETT, ETC, SAND669C | 1 | DEVELOP SCOPE | May 2004 | Aug 2004 | May 2004 | Aug 2004
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR669C | RECONSTRUCTION OF ROMA, HETT, ETC, SAND669C | 2 | PRELIMINARY DESIGN | Aug 2004 | Dec 2004 | Aug 2004 | Dec 2004
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR669C | RECONSTRUCTION OF ROMA, HETT, ETC, SAND669C | 3 | FINAL DESIGN | Dec 2004 | Jun 2005 | Dec 2004 | Jun 2005
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR669C | RECONSTRUCTION OF ROMA, HETT, ETC, SAND669C | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2005 | Sep 2005 | Mar 2022 | Jun 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR669C | RECONSTRUCTION OF ROMA, HETT, ETC, SAND669C | 5 | CONSTRUCTION TO 25% | Sep 2005 | Jan 2006 | Jun 2022 | Jun 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR669C | RECONSTRUCTION OF ROMA, HETT, ETC, SAND669C | 6 | CONSTRUCTION TO 50% | Jan 2006 | May 2006 | Jun 2022 | Jun 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR669C | RECONSTRUCTION OF ROMA, HETT, ETC, SAND669C | 7 | CONSTRUCTION TO 75% | May 2006 | Sep 2006 | Jun 2022 | Jun 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR669C | RECONSTRUCTION OF ROMA, HETT, ETC, SAND669C | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2006 | Dec 2006 | Jun 2022 | Jun 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR669C | RECONSTRUCTION OF ROMA, HETT, ETC, SAND669C | 9 | SUBSTANTIAL COMPLETION | Dec 2006 | Feb 2007 | Jun 2022 | Jun 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR669C | RECONSTRUCTION OF ROMA, HETT, ETC, SAND669C | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2007 | Mar 2007 | Nov 2023 | Dec 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR669C | RECONSTRUCTION OF ROMA, HETT, ETC, SAND669C | 11 | PROJECT START | Feb 2007 | Mar 2007 | Dec 2023 | Dec 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR669C | RECONSTRUCTION OF ROMA, HETT, ETC, SAND669C | 12 | DESIGN START | Feb 2007 | Mar 2007 | Dec 2023 | Dec 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR669C | RECONSTRUCTION OF ROMA, HETT, ETC, SAND669C | 13 | DESIGN COMPLETION | Feb 2007 | Mar 2007 | Dec 2023 | Dec 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR669C | RECONSTRUCTION OF ROMA, HETT, ETC, SAND669C | 14 | CONSTRUCTION START | Feb 2007 | Mar 2007 | Dec 2023 | Dec 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR669C | RECONSTRUCTION OF ROMA, HETT, ETC, SAND669C | 15 | CONSTRUCTION COMPLETION | Feb 2007 | Mar 2007 | Dec 2023 | Dec 2032
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR700 | St George-Richmond Terrace Intersection Improvements | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Nov 2018 | Nov 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR700 | St George-Richmond Terrace Intersection Improvements | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2020 | Jan 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR700 | St George-Richmond Terrace Intersection Improvements | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Aug 2021 | Dec 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR700 | St George-Richmond Terrace Intersection Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Dec 2022 | Jun 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR700 | St George-Richmond Terrace Intersection Improvements | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Jun 2023 | Jun 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR700 | St George-Richmond Terrace Intersection Improvements | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Jun 2023 | Jun 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR700 | St George-Richmond Terrace Intersection Improvements | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2023 | Jun 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR700 | St George-Richmond Terrace Intersection Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2023 | Jan 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR700 | St George-Richmond Terrace Intersection Improvements | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Aug 2023 | Oct 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR700 | St George-Richmond Terrace Intersection Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Feb 2025 | May 2025
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR700 | St George-Richmond Terrace Intersection Improvements | 11 | PROJECT START | Mar 2025 | Apr 2025 | May 2025 | May 2025
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR700 | St George-Richmond Terrace Intersection Improvements | 12 | DESIGN START | Mar 2025 | Apr 2025 | May 2025 | May 2025
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR700 | St George-Richmond Terrace Intersection Improvements | 13 | DESIGN COMPLETION | Mar 2025 | Apr 2025 | May 2025 | May 2025
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR700 | St George-Richmond Terrace Intersection Improvements | 14 | CONSTRUCTION START | Mar 2025 | Apr 2025 | May 2025 | May 2025
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR700 | St George-Richmond Terrace Intersection Improvements | 15 | CONSTRUCTION COMPLETION | Mar 2025 | Apr 2025 | May 2025 | May 2027
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR703 | Bay Street Area Safety Improvements, NDF-BSIMP, RED-392 | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Sep 2017 | Oct 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR703 | Bay Street Area Safety Improvements, NDF-BSIMP, RED-392 | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Jun 2020 | May 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR703 | Bay Street Area Safety Improvements, NDF-BSIMP, RED-392 | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Apr 2021 | Jan 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR703 | Bay Street Area Safety Improvements, NDF-BSIMP, RED-392 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Feb 2022 | Jun 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR703 | Bay Street Area Safety Improvements, NDF-BSIMP, RED-392 | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Sep 2022 | Mar 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR703 | Bay Street Area Safety Improvements, NDF-BSIMP, RED-392 | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Mar 2023 | Aug 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR703 | Bay Street Area Safety Improvements, NDF-BSIMP, RED-392 | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Aug 2023 | Feb 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR703 | Bay Street Area Safety Improvements, NDF-BSIMP, RED-392 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Feb 2024 | May 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR703 | Bay Street Area Safety Improvements, NDF-BSIMP, RED-392 | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Feb 2024 | Aug 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR703 | Bay Street Area Safety Improvements, NDF-BSIMP, RED-392 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Aug 2024 | Jul 2028
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR919 | BLOOMINGDALE ROAD: AMBOY ROAD TO ARTHUR KILL ROAD | 1 | DEVELOP SCOPE | May 2004 | Aug 2004 | May 2004 | Aug 2004
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR919 | BLOOMINGDALE ROAD: AMBOY ROAD TO ARTHUR KILL ROAD | 2 | PRELIMINARY DESIGN | Aug 2004 | Dec 2004 | Aug 2004 | Dec 2004
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR919 | BLOOMINGDALE ROAD: AMBOY ROAD TO ARTHUR KILL ROAD | 3 | FINAL DESIGN | Dec 2004 | Jun 2005 | Dec 2004 | Jun 2005
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR919 | BLOOMINGDALE ROAD: AMBOY ROAD TO ARTHUR KILL ROAD | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2010 | Jun 2010 | Mar 2020 | Jun 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR919 | BLOOMINGDALE ROAD: AMBOY ROAD TO ARTHUR KILL ROAD | 5 | CONSTRUCTION TO 25% | Jun 2010 | Jun 2010 | Jun 2020 | Jun 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR919 | BLOOMINGDALE ROAD: AMBOY ROAD TO ARTHUR KILL ROAD | 6 | CONSTRUCTION TO 50% | Jun 2010 | Jun 2010 | Jun 2020 | Jun 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR919 | BLOOMINGDALE ROAD: AMBOY ROAD TO ARTHUR KILL ROAD | 7 | CONSTRUCTION TO 75% | Jun 2010 | Jun 2010 | Jun 2020 | Jun 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR919 | BLOOMINGDALE ROAD: AMBOY ROAD TO ARTHUR KILL ROAD | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2010 | Jun 2010 | Jun 2020 | Jun 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR919 | BLOOMINGDALE ROAD: AMBOY ROAD TO ARTHUR KILL ROAD | 9 | SUBSTANTIAL COMPLETION | Jun 2010 | Jun 2010 | Jun 2020 | Jun 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR919 | BLOOMINGDALE ROAD: AMBOY ROAD TO ARTHUR KILL ROAD | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2010 | Jul 2010 | Jan 2022 | Aug 2030
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWRF05R | Dubois Yard Roof | 1 | DEVELOP SCOPE | Jun 2015 | Oct 2015 | Jun 2015 | Oct 2015
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWRF05R | Dubois Yard Roof | 2 | DESIGN START | Oct 2015 | Apr 2017 | Oct 2015 | Apr 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWRF05R | Dubois Yard Roof | 3 | CONSTRUCTION START | Apr 2017 | Apr 2019 | Apr 2017 | Apr 2032
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020R | Prior Notice Sidewalks- Staten Island | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020R | Prior Notice Sidewalks- Staten Island | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020R | Prior Notice Sidewalks- Staten Island | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020R | Prior Notice Sidewalks- Staten Island | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020R | Prior Notice Sidewalks- Staten Island | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020R | Prior Notice Sidewalks- Staten Island | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020R | Prior Notice Sidewalks- Staten Island | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020R | Prior Notice Sidewalks- Staten Island | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020R | Prior Notice Sidewalks- Staten Island | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020R | Prior Notice Sidewalks- Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Apr 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020R | Prior Notice Sidewalks- Staten Island | 11 | PROJECT START | Mar 2022 | Apr 2022 | Apr 2022 | Apr 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020R | Prior Notice Sidewalks- Staten Island | 12 | DESIGN START | Mar 2022 | Apr 2022 | Apr 2022 | Apr 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020R | Prior Notice Sidewalks- Staten Island | 13 | DESIGN COMPLETION | Mar 2022 | Apr 2022 | Apr 2022 | Apr 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020R | Prior Notice Sidewalks- Staten Island | 14 | CONSTRUCTION START | Mar 2022 | Apr 2022 | Apr 2022 | Apr 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020R | Prior Notice Sidewalks- Staten Island | 15 | CONSTRUCTION COMPLETION | Mar 2022 | Apr 2022 | Apr 2022 | Apr 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020X | Prior Notice Sidewalks- Bronx | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020X | Prior Notice Sidewalks- Bronx | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020X | Prior Notice Sidewalks- Bronx | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020X | Prior Notice Sidewalks- Bronx | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2020 | Oct 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020X | Prior Notice Sidewalks- Bronx | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020X | Prior Notice Sidewalks- Bronx | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020X | Prior Notice Sidewalks- Bronx | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020X | Prior Notice Sidewalks- Bronx | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020X | Prior Notice Sidewalks- Bronx | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020X | Prior Notice Sidewalks- Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2022 | Jun 2029
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021R | PRIOR NOTICE SIDEWALK - STATEN ISLAND | 2 | DESIGN START | Mar 2020 | Sep 2020 | Mar 2021 | Sep 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021R | PRIOR NOTICE SIDEWALK - STATEN ISLAND | 3 | CONSTRUCTION START | Sep 2020 | Jun 2021 | Sep 2021 | Jul 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023R | Prior Notice Sidewalks - Staten Island | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2023 | Sep 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023R | Prior Notice Sidewalks - Staten Island | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2023 | Jan 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023R | Prior Notice Sidewalks - Staten Island | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2024 | Jul 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023R | Prior Notice Sidewalks - Staten Island | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2024 | Oct 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023R | Prior Notice Sidewalks - Staten Island | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2024 | Feb 2025
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023R | Prior Notice Sidewalks - Staten Island | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2025 | Jun 2025
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023R | Prior Notice Sidewalks - Staten Island | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2025 | Oct 2025
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023R | Prior Notice Sidewalks - Staten Island | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2025 | Jan 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023R | Prior Notice Sidewalks - Staten Island | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2026 | Mar 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023R | Prior Notice Sidewalks - Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2026 | Apr 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRR1 | Trench Restoration - Staten Island (SER002333) | 1 | DEVELOP SCOPE | Mar 2020 | May 2020 | Mar 2020 | May 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRR1 | Trench Restoration - Staten Island (SER002333) | 2 | PRELIMINARY DESIGN | May 2020 | Sep 2020 | May 2020 | Sep 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRR1 | Trench Restoration - Staten Island (SER002333) | 3 | FINAL DESIGN | Sep 2020 | Mar 2021 | Sep 2020 | Mar 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRR1 | Trench Restoration - Staten Island (SER002333) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2021 | Jun 2021 | Mar 2021 | Jun 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRR1 | Trench Restoration - Staten Island (SER002333) | 5 | CONSTRUCTION TO 25% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRR1 | Trench Restoration - Staten Island (SER002333) | 6 | CONSTRUCTION TO 50% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRR1 | Trench Restoration - Staten Island (SER002333) | 7 | CONSTRUCTION TO 75% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRR1 | Trench Restoration - Staten Island (SER002333) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRR1 | Trench Restoration - Staten Island (SER002333) | 9 | SUBSTANTIAL COMPLETION | Sep 2022 | Nov 2022 | Sep 2022 | Nov 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRR1 | Trench Restoration - Staten Island (SER002333) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2022 | Dec 2022 | Nov 2022 | Dec 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRR1 | Trench Restoration - Staten Island (SER002333) | 11 | PROJECT START | Nov 2022 | Dec 2022 | Dec 2022 | Dec 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRR1 | Trench Restoration - Staten Island (SER002333) | 12 | DESIGN START | Nov 2022 | Dec 2022 | Dec 2022 | Dec 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRR1 | Trench Restoration - Staten Island (SER002333) | 13 | DESIGN COMPLETION | Nov 2022 | Dec 2022 | Dec 2022 | Dec 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRR1 | Trench Restoration - Staten Island (SER002333) | 14 | CONSTRUCTION START | Nov 2022 | Dec 2022 | Dec 2022 | Dec 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRR1 | Trench Restoration - Staten Island (SER002333) | 15 | CONSTRUCTION COMPLETION | Nov 2022 | Dec 2022 | Dec 2022 | Dec 2033
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNC2STAPL | STAPLETON - Renovation and Expansion | 2 | PRELIMINARY DESIGN | Jun 2006 | Oct 2006 | Jun 2006 | Oct 2006
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNC2STAPL | STAPLETON - Renovation and Expansion | 3 | FINAL DESIGN | Oct 2006 | Apr 2007 | Oct 2006 | Aug 2007
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNC2STAPL | STAPLETON - Renovation and Expansion | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2007 | Jul 2007 | Aug 2007 | Sep 2007
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNC2STAPL | STAPLETON - Renovation and Expansion | 5 | CONSTRUCTION TO 25% | Jul 2007 | Nov 2007 | Sep 2007 | May 2010
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNC2STAPL | STAPLETON - Renovation and Expansion | 6 | CONSTRUCTION TO 50% | Nov 2007 | Mar 2008 | May 2010 | Jun 2011
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNC2STAPL | STAPLETON - Renovation and Expansion | 7 | CONSTRUCTION TO 75% | Mar 2008 | Jul 2008 | Jun 2011 | Sep 2014
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNC2STAPL | STAPLETON - Renovation and Expansion | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2008 | Oct 2008 | Sep 2014 | Sep 2014
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNC2STAPL | STAPLETON - Renovation and Expansion | 9 | SUBSTANTIAL COMPLETION | Oct 2008 | Dec 2008 | Sep 2014 | Sep 2014
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNC2STAPL | STAPLETON - Renovation and Expansion | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2008 | Jan 2009 | Sep 2014 | Sep 2014
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNC2STAPL | STAPLETON - Renovation and Expansion | 11 | PROJECT START | Dec 2008 | Jan 2009 | Nov 2005 | Apr 2006
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNC2STAPL | STAPLETON - Renovation and Expansion | 12 | DESIGN START | Dec 2008 | Jan 2009 | Apr 2006 | Oct 2008
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNC2STAPL | STAPLETON - Renovation and Expansion | 13 | DESIGN COMPLETION | Dec 2008 | Jan 2009 | Oct 2008 | May 2009
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNC2STAPL | STAPLETON - Renovation and Expansion | 14 | CONSTRUCTION START | Dec 2008 | Jan 2009 | May 2009 | Nov 2011
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNC2STAPL | STAPLETON - Renovation and Expansion | 15 | CONSTRUCTION COMPLETION | Dec 2008 | Jan 2009 | Nov 2011 | May 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13STG | ST GEORGE: Exterior and Interior renovation | 1 | PROJECT START | Feb 2013 | Feb 2013 | Feb 2013 | Feb 2013
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13STG | ST GEORGE: Exterior and Interior renovation | 2 | DESIGN START | Feb 2015 | Feb 2015 | Feb 2015 | Feb 2015
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13STG | ST GEORGE: Exterior and Interior renovation | 3 | DESIGN COMPLETION | Dec 2015 | Dec 2015 | Dec 2015 | Dec 2015
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13STG | ST GEORGE: Exterior and Interior renovation | 4 | CONSTRUCTION START | May 2016 | May 2016 | May 2016 | May 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13STG | ST GEORGE: Exterior and Interior renovation | 5 | CONSTRUCTION COMPLETION | Oct 2017 | Oct 2017 | Oct 2020 | Oct 2028
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNRA17NDP | NEW DORP - HVAC System Replacement | 1 | DEVELOP SCOPE | Dec 2016 | Mar 2017 | Jun 2021 | Aug 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNRA17NDP | NEW DORP - HVAC System Replacement | 2 | PRELIMINARY DESIGN | Mar 2017 | Jul 2017 | Aug 2021 | Dec 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNRA17NDP | NEW DORP - HVAC System Replacement | 3 | FINAL DESIGN | Jul 2017 | Jan 2018 | Dec 2021 | Jun 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNRA17NDP | NEW DORP - HVAC System Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2018 | Apr 2018 | Jun 2022 | Sep 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNRA17NDP | NEW DORP - HVAC System Replacement | 5 | CONSTRUCTION TO 25% | Apr 2018 | Aug 2018 | Sep 2022 | Jan 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNRA17NDP | NEW DORP - HVAC System Replacement | 6 | CONSTRUCTION TO 50% | Aug 2018 | Dec 2018 | Jan 2023 | May 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNRA17NDP | NEW DORP - HVAC System Replacement | 7 | CONSTRUCTION TO 75% | Dec 2018 | Apr 2019 | May 2023 | Sep 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNRA17NDP | NEW DORP - HVAC System Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2019 | Jul 2019 | Sep 2023 | Dec 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNRA17NDP | NEW DORP - HVAC System Replacement | 9 | SUBSTANTIAL COMPLETION | Jul 2019 | Sep 2019 | Dec 2023 | Feb 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNRA17NDP | NEW DORP - HVAC System Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Oct 2019 | Feb 2024 | Mar 2025
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC002 | Last Chance Pond BMP NC 11/12, storm & sanitary sewer constr | 1 | DEVELOP SCOPE | May 2017 | Aug 2017 | May 2017 | Aug 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC002 | Last Chance Pond BMP NC 11/12, storm & sanitary sewer constr | 2 | PRELIMINARY DESIGN | Aug 2017 | Dec 2017 | Aug 2017 | Dec 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC002 | Last Chance Pond BMP NC 11/12, storm & sanitary sewer constr | 3 | FINAL DESIGN | Dec 2017 | May 2018 | Dec 2017 | May 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC002 | Last Chance Pond BMP NC 11/12, storm & sanitary sewer constr | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Aug 2018 | Jun 2018 | Aug 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC002 | Last Chance Pond BMP NC 11/12, storm & sanitary sewer constr | 5 | CONSTRUCTION TO 25% | Aug 2018 | Dec 2018 | Aug 2018 | Dec 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC002 | Last Chance Pond BMP NC 11/12, storm & sanitary sewer constr | 6 | CONSTRUCTION TO 50% | Dec 2018 | Apr 2019 | Dec 2018 | Apr 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC002 | Last Chance Pond BMP NC 11/12, storm & sanitary sewer constr | 7 | CONSTRUCTION TO 75% | Apr 2019 | Aug 2019 | Apr 2019 | Aug 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC002 | Last Chance Pond BMP NC 11/12, storm & sanitary sewer constr | 8 | ORIGINAL EQUIP & FURNISHING | Aug 2019 | Nov 2019 | Aug 2019 | Nov 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC002 | Last Chance Pond BMP NC 11/12, storm & sanitary sewer constr | 9 | SUBSTANTIAL COMPLETION | Nov 2019 | Jan 2020 | Nov 2019 | Jan 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC002 | Last Chance Pond BMP NC 11/12, storm & sanitary sewer constr | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2020 | Feb 2020 | Jan 2020 | May 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC003 | Strm & Sani Swr const & WM replac in Mason Ave, SI | 1 | DEVELOP SCOPE | Jun 2018 | Feb 2019 | Jun 2018 | Feb 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC003 | Strm & Sani Swr const & WM replac in Mason Ave, SI | 2 | PRELIMINARY DESIGN | Feb 2019 | Feb 2020 | Feb 2019 | Feb 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC003 | Strm & Sani Swr const & WM replac in Mason Ave, SI | 3 | FINAL DESIGN | Feb 2020 | Aug 2021 | Feb 2020 | Aug 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC003 | Strm & Sani Swr const & WM replac in Mason Ave, SI | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2021 | May 2022 | Aug 2021 | May 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC003 | Strm & Sani Swr const & WM replac in Mason Ave, SI | 5 | CONSTRUCTION TO 25% | May 2022 | May 2023 | May 2022 | May 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC003 | Strm & Sani Swr const & WM replac in Mason Ave, SI | 6 | CONSTRUCTION TO 50% | May 2023 | Apr 2024 | May 2023 | Apr 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC003 | Strm & Sani Swr const & WM replac in Mason Ave, SI | 7 | CONSTRUCTION TO 75% | Apr 2024 | Apr 2025 | Apr 2024 | Apr 2025
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC003 | Strm & Sani Swr const & WM replac in Mason Ave, SI | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2025 | Jan 2026 | Apr 2025 | Jan 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC003 | Strm & Sani Swr const & WM replac in Mason Ave, SI | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Jul 2026 | Jan 2026 | Jul 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC003 | Strm & Sani Swr const & WM replac in Mason Ave, SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2026 | Oct 2026 | Jul 2026 | Oct 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04A | BMP NC 6 and 15 storm & sanitary sewer installation | 1 | DEVELOP SCOPE | Mar 2018 | May 2018 | Mar 2018 | May 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04A | BMP NC 6 and 15 storm & sanitary sewer installation | 2 | PRELIMINARY DESIGN | May 2018 | Sep 2018 | May 2018 | Sep 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04A | BMP NC 6 and 15 storm & sanitary sewer installation | 3 | FINAL DESIGN | Sep 2018 | Mar 2019 | Sep 2018 | Mar 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04A | BMP NC 6 and 15 storm & sanitary sewer installation | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2019 | Jun 2019 | Mar 2019 | Jun 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04A | BMP NC 6 and 15 storm & sanitary sewer installation | 5 | CONSTRUCTION TO 25% | Jun 2019 | Oct 2019 | Jun 2019 | Oct 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04A | BMP NC 6 and 15 storm & sanitary sewer installation | 6 | CONSTRUCTION TO 50% | Oct 2019 | Feb 2020 | Oct 2019 | Feb 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04A | BMP NC 6 and 15 storm & sanitary sewer installation | 7 | CONSTRUCTION TO 75% | Feb 2020 | Jun 2020 | Feb 2020 | Jun 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04A | BMP NC 6 and 15 storm & sanitary sewer installation | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04A | BMP NC 6 and 15 storm & sanitary sewer installation | 9 | SUBSTANTIAL COMPLETION | Sep 2020 | Nov 2020 | Sep 2020 | Nov 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04A | BMP NC 6 and 15 storm & sanitary sewer installation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2020 | Dec 2020 | Nov 2020 | Nov 2029
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04B | Storm and sanitary sewer installation | 1 | DEVELOP SCOPE | Mar 2021 | May 2021 | Mar 2021 | May 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04B | Storm and sanitary sewer installation | 2 | PRELIMINARY DESIGN | May 2021 | Sep 2021 | May 2021 | Sep 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04B | Storm and sanitary sewer installation | 3 | FINAL DESIGN | Sep 2021 | Mar 2022 | Sep 2021 | Mar 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04B | Storm and sanitary sewer installation | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2022 | Jun 2022 | Mar 2022 | Jun 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04B | Storm and sanitary sewer installation | 5 | CONSTRUCTION TO 25% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04B | Storm and sanitary sewer installation | 6 | CONSTRUCTION TO 50% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04B | Storm and sanitary sewer installation | 7 | CONSTRUCTION TO 75% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04B | Storm and sanitary sewer installation | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04B | Storm and sanitary sewer installation | 9 | SUBSTANTIAL COMPLETION | Sep 2023 | Nov 2023 | Sep 2023 | Nov 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04B | Storm and sanitary sewer installation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2023 | Dec 2023 | Nov 2023 | Jun 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04B | Storm and sanitary sewer installation | 11 | PROJECT START | Nov 2023 | Dec 2023 | Jul 2026 | Jul 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04B | Storm and sanitary sewer installation | 12 | DESIGN START | Nov 2023 | Dec 2023 | Jul 2026 | Jul 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04B | Storm and sanitary sewer installation | 13 | DESIGN COMPLETION | Nov 2023 | Dec 2023 | Jul 2026 | Jul 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04B | Storm and sanitary sewer installation | 14 | CONSTRUCTION START | Nov 2023 | Dec 2023 | Jul 2026 | Jul 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04B | Storm and sanitary sewer installation | 15 | CONSTRUCTION COMPLETION | Nov 2023 | Dec 2023 | Jul 2026 | Jul 2027
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-BSIMP | NDF - Bay Street Streetscape Improvements, HWR703 | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-BSIMP | NDF - Bay Street Streetscape Improvements, HWR703 | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-BSIMP | NDF - Bay Street Streetscape Improvements, HWR703 | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-BSIMP | NDF - Bay Street Streetscape Improvements, HWR703 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-BSIMP | NDF - Bay Street Streetscape Improvements, HWR703 | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-BSIMP | NDF - Bay Street Streetscape Improvements, HWR703 | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-BSIMP | NDF - Bay Street Streetscape Improvements, HWR703 | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-BSIMP | NDF - Bay Street Streetscape Improvements, HWR703 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-BSIMP | NDF - Bay Street Streetscape Improvements, HWR703 | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-BSIMP | NDF - Bay Street Streetscape Improvements, HWR703 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Jun 2028
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-CRLYN | Mary Cali Dalton Recreation Center DB | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-CRLYN | Mary Cali Dalton Recreation Center DB | 2 | DESIGN | Dec 2019 | Dec 2021 | Dec 2019 | Dec 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-CRLYN | Mary Cali Dalton Recreation Center DB | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-CRLYN | Mary Cali Dalton Recreation Center DB | 4 | CONSTRUCTION | Sep 2022 | Sep 2024 | Sep 2022 | Sep 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-CRLYN | Mary Cali Dalton Recreation Center DB | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | P-5PNYC06 | PlaNYC-Ocean Breeze Athletic Fac-Building Fit-Out R149-108M | 1 | PROJECT START | Oct 2010 | Oct 2010 | Jul 2010 | Jul 2010
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | P-5PNYC06 | PlaNYC-Ocean Breeze Athletic Fac-Building Fit-Out R149-108M | 2 | DESIGN START | Oct 2010 | Oct 2010 | Jul 2010 | Jul 2010
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | P-5PNYC06 | PlaNYC-Ocean Breeze Athletic Fac-Building Fit-Out R149-108M | 3 | DESIGN COMPLETION | Oct 2010 | Oct 2010 | Jul 2010 | Oct 2010
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | P-5PNYC06 | PlaNYC-Ocean Breeze Athletic Fac-Building Fit-Out R149-108M | 4 | CONSTRUCTION START | Oct 2010 | Jan 2011 | Oct 2010 | Jan 2011
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | P-5PNYC06 | PlaNYC-Ocean Breeze Athletic Fac-Building Fit-Out R149-108M | 5 | CONSTRUCTION COMPLETION | Jan 2011 | Jan 2015 | Jan 2011 | Jun 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175CLOV | SIZ - Staten Island Zoo Clove Road Restoration | 1 | DEVELOP SCOPE | Jun 2018 | Jun 2019 | Jun 2020 | Jun 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175CLOV | SIZ - Staten Island Zoo Clove Road Restoration | 2 | PRELIMINARY DESIGN | Jul 2019 | Oct 2019 | Jul 2021 | Oct 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175CLOV | SIZ - Staten Island Zoo Clove Road Restoration | 3 | FINAL DESIGN | Oct 2019 | Apr 2020 | Oct 2021 | Apr 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175CLOV | SIZ - Staten Island Zoo Clove Road Restoration | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2020 | Jul 2020 | Apr 2022 | Jul 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175CLOV | SIZ - Staten Island Zoo Clove Road Restoration | 5 | CONSTRUCTION TO 25% | Jul 2020 | Nov 2020 | Jul 2022 | Nov 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175CLOV | SIZ - Staten Island Zoo Clove Road Restoration | 6 | CONSTRUCTION TO 50% | Nov 2020 | Mar 2021 | Nov 2022 | Mar 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175CLOV | SIZ - Staten Island Zoo Clove Road Restoration | 7 | CONSTRUCTION TO 75% | Mar 2021 | Jul 2021 | Mar 2023 | Jul 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175CLOV | SIZ - Staten Island Zoo Clove Road Restoration | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2021 | Oct 2021 | Jul 2023 | Oct 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175CLOV | SIZ - Staten Island Zoo Clove Road Restoration | 9 | SUBSTANTIAL COMPLETION | Oct 2021 | Dec 2021 | Oct 2023 | Dec 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175CLOV | SIZ - Staten Island Zoo Clove Road Restoration | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2021 | Jan 2022 | Dec 2023 | Jan 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175CLOV | SIZ - Staten Island Zoo Clove Road Restoration | 11 | PROJECT START | Dec 2021 | Jan 2022 | Jan 2024 | Jan 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175CLOV | SIZ - Staten Island Zoo Clove Road Restoration | 12 | DESIGN START | Dec 2021 | Jan 2022 | Jan 2024 | Jan 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175CLOV | SIZ - Staten Island Zoo Clove Road Restoration | 13 | DESIGN COMPLETION | Dec 2021 | Jan 2022 | Jan 2024 | Jan 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175CLOV | SIZ - Staten Island Zoo Clove Road Restoration | 14 | CONSTRUCTION START | Dec 2021 | Jan 2022 | Jan 2024 | Jan 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175CLOV | SIZ - Staten Island Zoo Clove Road Restoration | 15 | CONSTRUCTION COMPLETION | Dec 2021 | Jan 2022 | Jan 2024 | Jan 2028
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | 1 | DEVELOP SCOPE | Jun 2015 | Aug 2015 | Jan 2017 | Apr 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | 2 | PRELIMINARY DESIGN | Aug 2015 | Dec 2015 | Apr 2017 | Jul 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | 3 | FINAL DESIGN | Dec 2015 | Jun 2016 | Jul 2017 | Jan 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2016 | Sep 2016 | Jan 2018 | Apr 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | 5 | CONSTRUCTION TO 25% | Sep 2016 | Jan 2017 | Apr 2018 | Aug 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | 6 | CONSTRUCTION TO 50% | Jan 2017 | May 2017 | Aug 2018 | Dec 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | 7 | CONSTRUCTION TO 75% | May 2017 | Sep 2017 | Dec 2018 | Apr 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Dec 2017 | Apr 2019 | Jul 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | 9 | SUBSTANTIAL COMPLETION | Dec 2017 | Feb 2018 | Jul 2019 | Sep 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2018 | Mar 2018 | Sep 2019 | Oct 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | 11 | PROJECT START | Feb 2018 | Mar 2018 | Oct 2021 | Oct 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | 12 | DESIGN START | Feb 2018 | Mar 2018 | Oct 2021 | Oct 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | 13 | DESIGN COMPLETION | Feb 2018 | Mar 2018 | Oct 2021 | Oct 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | 14 | CONSTRUCTION START | Feb 2018 | Mar 2018 | Oct 2021 | Oct 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | 15 | CONSTRUCTION COMPLETION | Feb 2018 | Mar 2018 | Oct 2021 | Oct 2032
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | 1 | DEVELOP SCOPE | Jun 2015 | Aug 2015 | Jun 2015 | Aug 2015
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | 2 | PRELIMINARY DESIGN | Aug 2015 | Dec 2015 | Aug 2015 | Dec 2015
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | 3 | FINAL DESIGN | Dec 2015 | Jun 2016 | Dec 2015 | Jun 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2016 | Sep 2016 | Jun 2016 | Sep 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | 5 | CONSTRUCTION TO 25% | Sep 2016 | Jan 2017 | Sep 2016 | Jan 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | 6 | CONSTRUCTION TO 50% | Jan 2017 | May 2017 | Jan 2017 | May 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | 7 | CONSTRUCTION TO 75% | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Dec 2017 | Sep 2017 | Dec 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | 9 | SUBSTANTIAL COMPLETION | Dec 2017 | Feb 2018 | Dec 2017 | Feb 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2018 | Mar 2018 | Feb 2018 | Mar 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | 11 | PROJECT START | Feb 2018 | Mar 2018 | Mar 2021 | Mar 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | 12 | DESIGN START | Feb 2018 | Mar 2018 | Mar 2021 | Mar 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | 13 | DESIGN COMPLETION | Feb 2018 | Mar 2018 | Mar 2021 | Mar 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | 14 | CONSTRUCTION START | Feb 2018 | Mar 2018 | Mar 2021 | Mar 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | 15 | CONSTRUCTION COMPLETION | Feb 2018 | Mar 2018 | Mar 2023 | Jun 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV477TEMP | SICM -Staten Island Children's Museum Temp Control System | 1 | PROJECT START | Aug 2018 | Aug 2018 | Aug 2018 | Aug 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV477TEMP | SICM -Staten Island Children's Museum Temp Control System | 2 | DESIGN START | Aug 2018 | Jun 2019 | Aug 2018 | Jun 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV477TEMP | SICM -Staten Island Children's Museum Temp Control System | 3 | DESIGN COMPLETION | Sep 2020 | Sep 2020 | Sep 2020 | Sep 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV477TEMP | SICM -Staten Island Children's Museum Temp Control System | 4 | CONSTRUCTION START | Jun 2022 | May 2024 | Jun 2022 | May 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV477TEMP | SICM -Staten Island Children's Museum Temp Control System | 5 | CONSTRUCTION COMPLETION | Dec 2025 | Dec 2025 | Dec 2025 | Dec 2025
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | 1 | DEVELOP SCOPE | Jun 2015 | Sep 2015 | Jun 2015 | Sep 2015
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | 2 | PRELIMINARY DESIGN | Sep 2015 | Jan 2016 | Sep 2015 | Jan 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | 3 | FINAL DESIGN | Jan 2016 | Jul 2016 | Jan 2016 | Jul 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Oct 2016 | Jul 2016 | Oct 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | 5 | CONSTRUCTION TO 25% | Oct 2016 | Feb 2017 | Oct 2016 | Feb 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | 6 | CONSTRUCTION TO 50% | Feb 2017 | Jun 2017 | Feb 2017 | Jun 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | 7 | CONSTRUCTION TO 75% | Jun 2017 | Oct 2017 | Jun 2017 | Oct 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2017 | Dec 2017 | Oct 2017 | Dec 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | 9 | SUBSTANTIAL COMPLETION | Dec 2017 | Feb 2018 | Dec 2017 | Feb 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2018 | Mar 2018 | Mar 2018 | Mar 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | 11 | PROJECT START | Mar 2018 | Mar 2018 | Mar 2021 | Mar 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | 12 | DESIGN START | Mar 2018 | Mar 2018 | Apr 2021 | Apr 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | 13 | DESIGN COMPLETION | Mar 2018 | Mar 2018 | Apr 2021 | Apr 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | 14 | CONSTRUCTION START | Mar 2018 | Mar 2018 | Apr 2021 | Apr 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | 15 | CONSTRUCTION COMPLETION | Mar 2018 | Mar 2018 | Apr 2021 | Apr 2029
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | 1 | DEVELOP SCOPE | Jun 2015 | Sep 2015 | Jun 2015 | Sep 2015
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | 2 | PRELIMINARY DESIGN | Sep 2015 | Jan 2016 | Sep 2015 | Jan 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | 3 | FINAL DESIGN | Jan 2016 | Jul 2016 | Jan 2016 | Jul 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Oct 2016 | Jul 2016 | Oct 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | 5 | CONSTRUCTION TO 25% | Oct 2016 | Feb 2017 | Oct 2016 | Feb 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | 6 | CONSTRUCTION TO 50% | Feb 2017 | Jun 2017 | Feb 2017 | Jun 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | 7 | CONSTRUCTION TO 75% | Jun 2017 | Oct 2017 | Jun 2017 | Oct 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2017 | Dec 2017 | Oct 2017 | Dec 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | 9 | SUBSTANTIAL COMPLETION | Dec 2017 | Feb 2018 | Dec 2017 | Feb 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2018 | Mar 2018 | Mar 2018 | Mar 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | 11 | PROJECT START | Mar 2018 | Mar 2018 | Mar 2021 | Mar 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | 12 | DESIGN START | Mar 2018 | Mar 2018 | Apr 2021 | Apr 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | 13 | DESIGN COMPLETION | Mar 2018 | Mar 2018 | Apr 2021 | Apr 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | 14 | CONSTRUCTION START | Mar 2018 | Mar 2018 | Apr 2021 | Apr 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | 15 | CONSTRUCTION COMPLETION | Mar 2018 | Mar 2018 | Apr 2021 | Aug 2029
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Jun 2016 | Sep 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Sep 2016 | Jan 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Jan 2017 | Jul 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Jul 2017 | Oct 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Oct 2017 | Feb 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Feb 2018 | Jun 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | Oct 2018 | Jan 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Jan 2019 | Mar 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Mar 2019 | Apr 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | 11 | PROJECT START | Mar 2019 | Apr 2019 | Apr 2019 | Apr 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | 12 | DESIGN START | Mar 2019 | Apr 2019 | Apr 2019 | Apr 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | 13 | DESIGN COMPLETION | Mar 2019 | Apr 2019 | Apr 2019 | Apr 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | 14 | CONSTRUCTION START | Mar 2019 | Apr 2019 | Apr 2019 | Apr 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | 15 | CONSTRUCTION COMPLETION | Mar 2019 | Apr 2019 | Apr 2022 | Jul 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-Q3 | SHCC - Snug Harbor Cult. Ctr. Music Hall, Dressing Rooms | 1 | CONSTRUCTION | Apr 2013 | Apr 2014 | Jan 2013 | Apr 2013
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-Q3 | SHCC - Snug Harbor Cult. Ctr. Music Hall, Dressing Rooms | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2014 | Apr 2015 | Apr 2013 | Apr 2014
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-Q3 | SHCC - Snug Harbor Cult. Ctr. Music Hall, Dressing Rooms | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2014 | Apr 2015 | Apr 2014 | Apr 2015
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-Q3 | SHCC - Snug Harbor Cult. Ctr. Music Hall, Dressing Rooms | 4 | PROJECT START | Apr 2014 | Apr 2015 | Apr 2015 | Apr 2015
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-Q3 | SHCC - Snug Harbor Cult. Ctr. Music Hall, Dressing Rooms | 5 | DESIGN START | Apr 2014 | Apr 2015 | Apr 2015 | Apr 2015
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-Q3 | SHCC - Snug Harbor Cult. Ctr. Music Hall, Dressing Rooms | 6 | DESIGN COMPLETION | Apr 2014 | Apr 2015 | Apr 2015 | Apr 2015
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-Q3 | SHCC - Snug Harbor Cult. Ctr. Music Hall, Dressing Rooms | 7 | CONSTRUCTION START | Apr 2014 | Apr 2015 | Apr 2015 | Apr 2015
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-Q3 | SHCC - Snug Harbor Cult. Ctr. Music Hall, Dressing Rooms | 8 | CONSTRUCTION COMPLETION | Apr 2014 | Apr 2015 | Jun 2016 | Jun 2025
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PW29310R | 10 RICHMOND TERRACE - FIRE ALARM | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PW29310R | 10 RICHMOND TERRACE - FIRE ALARM | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PW29310R | 10 RICHMOND TERRACE - FIRE ALARM | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2020 | Jul 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PW29310R | 10 RICHMOND TERRACE - FIRE ALARM | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PW29310R | 10 RICHMOND TERRACE - FIRE ALARM | 5 | CONSTRUCTION TO 25% | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PW29310R | 10 RICHMOND TERRACE - FIRE ALARM | 6 | CONSTRUCTION TO 50% | Dec 2022 | Apr 2023 | Dec 2022 | Apr 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PW29310R | 10 RICHMOND TERRACE - FIRE ALARM | 7 | CONSTRUCTION TO 75% | Apr 2023 | Aug 2023 | Apr 2023 | Aug 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PW29310R | 10 RICHMOND TERRACE - FIRE ALARM | 8 | ORIGINAL EQUIP & FURNISHING | Aug 2023 | Nov 2023 | Aug 2023 | Nov 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PW29310R | 10 RICHMOND TERRACE - FIRE ALARM | 9 | SUBSTANTIAL COMPLETION | Nov 2023 | Jan 2024 | Nov 2023 | Jan 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PW29310R | 10 RICHMOND TERRACE - FIRE ALARM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2024 | Feb 2024 | Jan 2024 | Feb 2025
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-74 | FUEL TANK REPLACEMENT | 1 | PROJECT START | Jul 2017 | Jul 2017 | Jul 2017 | Jul 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-74 | FUEL TANK REPLACEMENT | 2 | DESIGN START | Jul 2017 | Jul 2017 | Jul 2017 | Oct 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-74 | FUEL TANK REPLACEMENT | 3 | DESIGN COMPLETION | Jul 2017 | Jul 2017 | Oct 2017 | Sep 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-74 | FUEL TANK REPLACEMENT | 4 | CONSTRUCTION START | Jul 2017 | Jul 2017 | Sep 2018 | Oct 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-74 | FUEL TANK REPLACEMENT | 5 | CONSTRUCTION COMPLETION | Jul 2017 | Jul 2019 | Oct 2018 | Jul 2032
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-366 | WM WORK ARTHUR KILL RD BTW RICHMOND & ABINGTON AVE HWR1140A | 1 | DEVELOP SCOPE | Mar 2014 | Jun 2014 | Jul 2011 | Sep 2012
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-366 | WM WORK ARTHUR KILL RD BTW RICHMOND & ABINGTON AVE HWR1140A | 2 | PRELIMINARY DESIGN | Jun 2014 | Sep 2014 | Sep 2011 | Jan 2012
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-366 | WM WORK ARTHUR KILL RD BTW RICHMOND & ABINGTON AVE HWR1140A | 3 | FINAL DESIGN | Oct 2014 | Mar 2015 | Jan 2012 | Mar 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-366 | WM WORK ARTHUR KILL RD BTW RICHMOND & ABINGTON AVE HWR1140A | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2015 | Jun 2015 | Mar 2022 | Jun 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-366 | WM WORK ARTHUR KILL RD BTW RICHMOND & ABINGTON AVE HWR1140A | 5 | CONSTRUCTION TO 25% | Jun 2015 | Oct 2015 | Jun 2022 | Oct 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-366 | WM WORK ARTHUR KILL RD BTW RICHMOND & ABINGTON AVE HWR1140A | 6 | CONSTRUCTION TO 50% | Oct 2015 | Feb 2016 | Oct 2022 | Feb 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-366 | WM WORK ARTHUR KILL RD BTW RICHMOND & ABINGTON AVE HWR1140A | 7 | CONSTRUCTION TO 75% | Feb 2016 | Jun 2016 | Feb 2023 | Mar 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-366 | WM WORK ARTHUR KILL RD BTW RICHMOND & ABINGTON AVE HWR1140A | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2016 | Sep 2016 | Mar 2023 | Jul 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-366 | WM WORK ARTHUR KILL RD BTW RICHMOND & ABINGTON AVE HWR1140A | 9 | SUBSTANTIAL COMPLETION | Sep 2016 | Nov 2016 | Jul 2023 | Nov 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-366 | WM WORK ARTHUR KILL RD BTW RICHMOND & ABINGTON AVE HWR1140A | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2016 | Dec 2016 | Nov 2023 | Jun 2029
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-386 | Water Main replacement, South & Arlington Aves, SI | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-386 | Water Main replacement, South & Arlington Aves, SI | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-386 | Water Main replacement, South & Arlington Aves, SI | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-386 | Water Main replacement, South & Arlington Aves, SI | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-386 | Water Main replacement, South & Arlington Aves, SI | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-386 | Water Main replacement, South & Arlington Aves, SI | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-386 | Water Main replacement, South & Arlington Aves, SI | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-386 | Water Main replacement, South & Arlington Aves, SI | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-386 | Water Main replacement, South & Arlington Aves, SI | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2023 | Mar 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-386 | Water Main replacement, South & Arlington Aves, SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2023 | Apr 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-386 | Water Main replacement, South & Arlington Aves, SI | 11 | PROJECT START | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-386 | Water Main replacement, South & Arlington Aves, SI | 12 | DESIGN START | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-386 | Water Main replacement, South & Arlington Aves, SI | 13 | DESIGN COMPLETION | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-386 | Water Main replacement, South & Arlington Aves, SI | 14 | CONSTRUCTION START | Mar 2023 | Apr 2023 | Apr 2023 | Apr 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-386 | Water Main replacement, South & Arlington Aves, SI | 15 | CONSTRUCTION COMPLETION | Mar 2023 | Apr 2023 | Apr 2023 | Jun 2027
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-367 | Staten Island 1 and 3 Garage Construction + SOLARGR10 | 1 | PROJECT START | Mar 2019 | Mar 2019 | Mar 2019 | Mar 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-367 | Staten Island 1 and 3 Garage Construction + SOLARGR10 | 2 | DESIGN START | Mar 2019 | Mar 2019 | Mar 2019 | Mar 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-367 | Staten Island 1 and 3 Garage Construction + SOLARGR10 | 3 | DESIGN COMPLETION | Mar 2019 | Mar 2019 | Mar 2019 | Jun 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-367 | Staten Island 1 and 3 Garage Construction + SOLARGR10 | 4 | CONSTRUCTION START | Mar 2019 | Mar 2019 | Jun 2019 | Feb 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-367 | Staten Island 1 and 3 Garage Construction + SOLARGR10 | 5 | CONSTRUCTION COMPLETION | Mar 2019 | Mar 2019 | Feb 2020 | Jun 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383S | STATEN ISLAND 3 GARAGE HVAC | 1 | DEVELOP SCOPE | Aug 2007 | Feb 2008 | Aug 2007 | Feb 2008
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383S | STATEN ISLAND 3 GARAGE HVAC | 2 | PRELIMINARY DESIGN | Feb 2008 | Sep 2008 | Feb 2008 | Jul 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383S | STATEN ISLAND 3 GARAGE HVAC | 3 | FINAL DESIGN | Sep 2008 | Mar 2009 | Jul 2017 | Jun 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383S | STATEN ISLAND 3 GARAGE HVAC | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2009 | Oct 2009 | Jun 2019 | Feb 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383S | STATEN ISLAND 3 GARAGE HVAC | 5 | CONSTRUCTION TO 25% | Oct 2009 | Oct 2010 | Feb 2020 | Feb 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383S | STATEN ISLAND 3 GARAGE HVAC | 6 | CONSTRUCTION TO 50% | Oct 2010 | Oct 2011 | Feb 2020 | Feb 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383S | STATEN ISLAND 3 GARAGE HVAC | 7 | CONSTRUCTION TO 75% | Oct 2011 | Oct 2012 | Feb 2020 | Feb 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383S | STATEN ISLAND 3 GARAGE HVAC | 8 | SUBSTANTIAL COMPLETION | Oct 2012 | Oct 2013 | Feb 2020 | Feb 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383S | STATEN ISLAND 3 GARAGE HVAC | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2013 | Sep 2015 | Feb 2021 | Aug 2025
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND669C | Reconstruction of Roma,Hett,Etc - Hurricane Sandy | 1 | DEVELOP SCOPE | Feb 2016 | May 2016 | Feb 2016 | May 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND669C | Reconstruction of Roma,Hett,Etc - Hurricane Sandy | 2 | PRELIMINARY DESIGN | May 2016 | Sep 2016 | May 2016 | Sep 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND669C | Reconstruction of Roma,Hett,Etc - Hurricane Sandy | 3 | FINAL DESIGN | Sep 2016 | Mar 2017 | Sep 2016 | Mar 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND669C | Reconstruction of Roma,Hett,Etc - Hurricane Sandy | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2017 | Jun 2017 | Mar 2017 | Jun 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND669C | Reconstruction of Roma,Hett,Etc - Hurricane Sandy | 5 | CONSTRUCTION TO 25% | Jun 2017 | Oct 2017 | Jun 2017 | Oct 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND669C | Reconstruction of Roma,Hett,Etc - Hurricane Sandy | 6 | CONSTRUCTION TO 50% | Oct 2017 | Feb 2018 | Oct 2017 | Feb 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND669C | Reconstruction of Roma,Hett,Etc - Hurricane Sandy | 7 | CONSTRUCTION TO 75% | Feb 2018 | Jun 2018 | Feb 2018 | Jun 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND669C | Reconstruction of Roma,Hett,Etc - Hurricane Sandy | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND669C | Reconstruction of Roma,Hett,Etc - Hurricane Sandy | 9 | SUBSTANTIAL COMPLETION | Sep 2018 | Nov 2018 | Sep 2018 | Nov 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND669C | Reconstruction of Roma,Hett,Etc - Hurricane Sandy | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2018 | Dec 2018 | Nov 2018 | Jun 2028
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW14 | Reconstruction of South Beach - Hurricane Sandy - RED-375 | 1 | DEVELOP SCOPE | Feb 2016 | May 2016 | Feb 2016 | May 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW14 | Reconstruction of South Beach - Hurricane Sandy - RED-375 | 2 | PRELIMINARY DESIGN | May 2016 | Sep 2016 | May 2016 | Sep 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW14 | Reconstruction of South Beach - Hurricane Sandy - RED-375 | 3 | FINAL DESIGN | Sep 2016 | Mar 2017 | Sep 2016 | Mar 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW14 | Reconstruction of South Beach - Hurricane Sandy - RED-375 | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2017 | Jun 2017 | Mar 2017 | Jun 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW14 | Reconstruction of South Beach - Hurricane Sandy - RED-375 | 5 | CONSTRUCTION TO 25% | Jun 2017 | Oct 2017 | Jun 2017 | Oct 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW14 | Reconstruction of South Beach - Hurricane Sandy - RED-375 | 6 | CONSTRUCTION TO 50% | Oct 2017 | Feb 2018 | Oct 2017 | Feb 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW14 | Reconstruction of South Beach - Hurricane Sandy - RED-375 | 7 | CONSTRUCTION TO 75% | Feb 2018 | Jun 2018 | Feb 2018 | Jun 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW14 | Reconstruction of South Beach - Hurricane Sandy - RED-375 | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW14 | Reconstruction of South Beach - Hurricane Sandy - RED-375 | 9 | SUBSTANTIAL COMPLETION | Sep 2018 | Nov 2018 | Sep 2018 | Nov 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW14 | Reconstruction of South Beach - Hurricane Sandy - RED-375 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2018 | Dec 2018 | Nov 2018 | Jun 2032
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSI | Non When & Where - Staten Island - Hurricane Sandy | 1 | DEVELOP SCOPE | Oct 2015 | Jan 2016 | Oct 2015 | Jan 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSI | Non When & Where - Staten Island - Hurricane Sandy | 2 | PRELIMINARY DESIGN | Jan 2016 | May 2016 | Jan 2016 | May 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSI | Non When & Where - Staten Island - Hurricane Sandy | 3 | FINAL DESIGN | May 2016 | Nov 2016 | May 2016 | Nov 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSI | Non When & Where - Staten Island - Hurricane Sandy | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2016 | Jan 2017 | Nov 2016 | Jan 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSI | Non When & Where - Staten Island - Hurricane Sandy | 5 | CONSTRUCTION TO 25% | Feb 2017 | May 2017 | Feb 2017 | May 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSI | Non When & Where - Staten Island - Hurricane Sandy | 6 | CONSTRUCTION TO 50% | Jun 2017 | Sep 2017 | Jun 2017 | Sep 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSI | Non When & Where - Staten Island - Hurricane Sandy | 7 | CONSTRUCTION TO 75% | Sep 2017 | Jan 2018 | Sep 2017 | Jan 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSI | Non When & Where - Staten Island - Hurricane Sandy | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2018 | Apr 2018 | Jan 2018 | Apr 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSI | Non When & Where - Staten Island - Hurricane Sandy | 9 | SUBSTANTIAL COMPLETION | Apr 2018 | Jun 2018 | Apr 2018 | Jun 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSI | Non When & Where - Staten Island - Hurricane Sandy | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2018 | Jul 2018 | Jun 2018 | Feb 2033
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSIB | Swaim & Huguenot Ave Improvements | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2022 | Sep 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSIB | Swaim & Huguenot Ave Improvements | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2022 | Jan 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSIB | Swaim & Huguenot Ave Improvements | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2023 | Jul 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSIB | Swaim & Huguenot Ave Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2023 | Oct 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSIB | Swaim & Huguenot Ave Improvements | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2023 | Feb 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSIB | Swaim & Huguenot Ave Improvements | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2024 | Jun 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSIB | Swaim & Huguenot Ave Improvements | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2024 | Oct 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSIB | Swaim & Huguenot Ave Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2024 | Jan 2025
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSIB | Swaim & Huguenot Ave Improvements | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2025 | Mar 2025
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSIB | Swaim & Huguenot Ave Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2025 | Apr 2033
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR01 | Hylan Blvd Streetscape Improvements (MIBBNC05) | 1 | DEVELOP SCOPE | Jul 2016 | Sep 2016 | Jul 2016 | Sep 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR01 | Hylan Blvd Streetscape Improvements (MIBBNC05) | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Sep 2016 | Jan 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR01 | Hylan Blvd Streetscape Improvements (MIBBNC05) | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Jan 2017 | Jul 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR01 | Hylan Blvd Streetscape Improvements (MIBBNC05) | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Jul 2017 | Oct 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR01 | Hylan Blvd Streetscape Improvements (MIBBNC05) | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Oct 2017 | Feb 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR01 | Hylan Blvd Streetscape Improvements (MIBBNC05) | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Feb 2018 | Jun 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR01 | Hylan Blvd Streetscape Improvements (MIBBNC05) | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR01 | Hylan Blvd Streetscape Improvements (MIBBNC05) | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | Oct 2018 | Jan 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR01 | Hylan Blvd Streetscape Improvements (MIBBNC05) | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Jan 2019 | Mar 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR01 | Hylan Blvd Streetscape Improvements (MIBBNC05) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Mar 2019 | Jun 2032
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-740B | SANITARY SEWERS IN ROCKLAND AVENUE, HWR1160 | 1 | DEVELOP SCOPE | Mar 2009 | Jun 2009 | Jun 2004 | Sep 2004
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-740B | SANITARY SEWERS IN ROCKLAND AVENUE, HWR1160 | 2 | PRELIMINARY DESIGN | Jun 2009 | Oct 2009 | Sep 2004 | Mar 2005
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-740B | SANITARY SEWERS IN ROCKLAND AVENUE, HWR1160 | 3 | FINAL DESIGN | Oct 2009 | Apr 2010 | Mar 2005 | Mar 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-740B | SANITARY SEWERS IN ROCKLAND AVENUE, HWR1160 | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2010 | Jul 2010 | Mar 2017 | Jun 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-740B | SANITARY SEWERS IN ROCKLAND AVENUE, HWR1160 | 5 | CONSTRUCTION TO 25% | Jul 2010 | Nov 2010 | Jun 2017 | Oct 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-740B | SANITARY SEWERS IN ROCKLAND AVENUE, HWR1160 | 6 | CONSTRUCTION TO 50% | Nov 2010 | Mar 2011 | Oct 2017 | Oct 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-740B | SANITARY SEWERS IN ROCKLAND AVENUE, HWR1160 | 7 | CONSTRUCTION TO 75% | Mar 2011 | Jul 2011 | Oct 2018 | Feb 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-740B | SANITARY SEWERS IN ROCKLAND AVENUE, HWR1160 | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2011 | Oct 2011 | Feb 2019 | Mar 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-740B | SANITARY SEWERS IN ROCKLAND AVENUE, HWR1160 | 9 | SUBSTANTIAL COMPLETION | Oct 2011 | Dec 2011 | Mar 2019 | Aug 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-740B | SANITARY SEWERS IN ROCKLAND AVENUE, HWR1160 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2011 | Jan 2012 | Aug 2019 | Sep 2032
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-751 | CHESTER AV - IRVINGTON ST AND ARBUTUS AVE | 1 | DEVELOP SCOPE | Feb 2004 | May 2004 | Feb 2004 | May 2004
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-751 | CHESTER AV - IRVINGTON ST AND ARBUTUS AVE | 2 | PRELIMINARY DESIGN | May 2004 | Sep 2004 | May 2004 | Aug 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-751 | CHESTER AV - IRVINGTON ST AND ARBUTUS AVE | 3 | FINAL DESIGN | Sep 2004 | Mar 2005 | Aug 2015 | Feb 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-751 | CHESTER AV - IRVINGTON ST AND ARBUTUS AVE | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2005 | Jun 2005 | Feb 2016 | Jun 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-751 | CHESTER AV - IRVINGTON ST AND ARBUTUS AVE | 5 | CONSTRUCTION TO 25% | Jun 2005 | Oct 2005 | Jun 2016 | Sep 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-751 | CHESTER AV - IRVINGTON ST AND ARBUTUS AVE | 6 | CONSTRUCTION TO 50% | Oct 2005 | Feb 2006 | Sep 2016 | Jan 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-751 | CHESTER AV - IRVINGTON ST AND ARBUTUS AVE | 7 | CONSTRUCTION TO 75% | Feb 2006 | Jun 2006 | Jan 2017 | May 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-751 | CHESTER AV - IRVINGTON ST AND ARBUTUS AVE | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2006 | Sep 2006 | Jan 2017 | Apr 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-751 | CHESTER AV - IRVINGTON ST AND ARBUTUS AVE | 9 | SUBSTANTIAL COMPLETION | Sep 2006 | Nov 2006 | Apr 2017 | Jun 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-751 | CHESTER AV - IRVINGTON ST AND ARBUTUS AVE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2006 | Dec 2006 | Jun 2017 | Jun 2031
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-812 | Sanitary & Storm swr in Page Av b/t Amboy Rd & Estella Pl | 1 | DEVELOP SCOPE | Jun 2009 | Mar 2010 | Mar 2016 | May 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-812 | Sanitary & Storm swr in Page Av b/t Amboy Rd & Estella Pl | 2 | PRELIMINARY DESIGN | Mar 2010 | Mar 2011 | May 2016 | Sep 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-812 | Sanitary & Storm swr in Page Av b/t Amboy Rd & Estella Pl | 3 | FINAL DESIGN | Mar 2011 | Sep 2012 | Sep 2016 | Mar 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-812 | Sanitary & Storm swr in Page Av b/t Amboy Rd & Estella Pl | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2012 | Jun 2013 | Mar 2017 | Jun 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-812 | Sanitary & Storm swr in Page Av b/t Amboy Rd & Estella Pl | 5 | CONSTRUCTION TO 25% | Jun 2013 | Jun 2014 | Jun 2017 | Feb 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-812 | Sanitary & Storm swr in Page Av b/t Amboy Rd & Estella Pl | 6 | CONSTRUCTION TO 50% | Jun 2014 | May 2015 | Feb 2018 | Oct 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-812 | Sanitary & Storm swr in Page Av b/t Amboy Rd & Estella Pl | 7 | CONSTRUCTION TO 75% | May 2015 | May 2016 | Oct 2018 | Jun 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-812 | Sanitary & Storm swr in Page Av b/t Amboy Rd & Estella Pl | 8 | ORIGINAL EQUIP & FURNISHING | May 2016 | Feb 2017 | Jun 2019 | Sep 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-812 | Sanitary & Storm swr in Page Av b/t Amboy Rd & Estella Pl | 9 | SUBSTANTIAL COMPLETION | Feb 2017 | Aug 2017 | Sep 2019 | Nov 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-812 | Sanitary & Storm swr in Page Av b/t Amboy Rd & Estella Pl | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2017 | Nov 2017 | Nov 2019 | Dec 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-812 | Sanitary & Storm swr in Page Av b/t Amboy Rd & Estella Pl | 11 | PROJECT START | Aug 2017 | Nov 2017 | Dec 2023 | Dec 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-812 | Sanitary & Storm swr in Page Av b/t Amboy Rd & Estella Pl | 12 | DESIGN START | Aug 2017 | Nov 2017 | Dec 2023 | Dec 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-812 | Sanitary & Storm swr in Page Av b/t Amboy Rd & Estella Pl | 13 | DESIGN COMPLETION | Aug 2017 | Nov 2017 | Dec 2023 | Dec 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-812 | Sanitary & Storm swr in Page Av b/t Amboy Rd & Estella Pl | 14 | CONSTRUCTION START | Aug 2017 | Nov 2017 | Dec 2023 | Dec 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-812 | Sanitary & Storm swr in Page Av b/t Amboy Rd & Estella Pl | 15 | CONSTRUCTION COMPLETION | Aug 2017 | Nov 2017 | Dec 2023 | Jun 2032
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002237 | Sanitary and Storm Sewer in Manee Avenue | 1 | DEVELOP SCOPE | Feb 2013 | Nov 2013 | Feb 2013 | Nov 2013
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002237 | Sanitary and Storm Sewer in Manee Avenue | 2 | PRELIMINARY DESIGN | Nov 2013 | Nov 2014 | Nov 2013 | Nov 2014
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002237 | Sanitary and Storm Sewer in Manee Avenue | 3 | FINAL DESIGN | Nov 2014 | Apr 2016 | Nov 2014 | Apr 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002237 | Sanitary and Storm Sewer in Manee Avenue | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2016 | Jan 2017 | Apr 2016 | Jan 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002237 | Sanitary and Storm Sewer in Manee Avenue | 5 | CONSTRUCTION TO 25% | Jan 2017 | Jan 2018 | Jan 2017 | Jan 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002237 | Sanitary and Storm Sewer in Manee Avenue | 6 | CONSTRUCTION TO 50% | Jan 2018 | Jan 2019 | Jan 2018 | Jan 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002237 | Sanitary and Storm Sewer in Manee Avenue | 7 | CONSTRUCTION TO 75% | Jan 2019 | Jan 2020 | Jan 2019 | Jan 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002237 | Sanitary and Storm Sewer in Manee Avenue | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2020 | Oct 2020 | Jan 2020 | Oct 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002237 | Sanitary and Storm Sewer in Manee Avenue | 9 | SUBSTANTIAL COMPLETION | Oct 2020 | Apr 2021 | Oct 2020 | Apr 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002237 | Sanitary and Storm Sewer in Manee Avenue | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2021 | Jul 2021 | Apr 2021 | Jun 2031
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002311 | SAN & STRM SWR IN BERTRAM AV B/T ZEPHYR AV & HYLAN BLVD. ETC | 1 | DEVELOP SCOPE | Jun 2012 | Sep 2012 | Jun 2011 | Sep 2011
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002311 | SAN & STRM SWR IN BERTRAM AV B/T ZEPHYR AV & HYLAN BLVD. ETC | 2 | PRELIMINARY DESIGN | Sep 2012 | Jan 2013 | Sep 2011 | Jan 2012
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002311 | SAN & STRM SWR IN BERTRAM AV B/T ZEPHYR AV & HYLAN BLVD. ETC | 3 | FINAL DESIGN | Jan 2013 | Jul 2013 | Jan 2012 | Aug 2013
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002311 | SAN & STRM SWR IN BERTRAM AV B/T ZEPHYR AV & HYLAN BLVD. ETC | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2013 | Oct 2013 | Aug 2013 | Nov 2013
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002311 | SAN & STRM SWR IN BERTRAM AV B/T ZEPHYR AV & HYLAN BLVD. ETC | 5 | CONSTRUCTION TO 25% | Oct 2013 | Feb 2014 | Nov 2013 | May 2014
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002311 | SAN & STRM SWR IN BERTRAM AV B/T ZEPHYR AV & HYLAN BLVD. ETC | 6 | CONSTRUCTION TO 50% | Feb 2014 | Jun 2014 | May 2014 | Nov 2014
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002311 | SAN & STRM SWR IN BERTRAM AV B/T ZEPHYR AV & HYLAN BLVD. ETC | 7 | CONSTRUCTION TO 75% | Jun 2014 | Oct 2014 | Nov 2014 | May 2015
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002311 | SAN & STRM SWR IN BERTRAM AV B/T ZEPHYR AV & HYLAN BLVD. ETC | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2014 | Jan 2015 | May 2015 | Aug 2015
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002311 | SAN & STRM SWR IN BERTRAM AV B/T ZEPHYR AV & HYLAN BLVD. ETC | 9 | SUBSTANTIAL COMPLETION | Jan 2015 | Mar 2015 | Aug 2015 | Aug 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002311 | SAN & STRM SWR IN BERTRAM AV B/T ZEPHYR AV & HYLAN BLVD. ETC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Apr 2015 | Aug 2016 | Oct 2025
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002317 | SAN & STRM SEWER IN HALPIN AVE | 1 | DEVELOP SCOPE | Jun 2012 | Sep 2012 | Jun 2010 | Sep 2010
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002317 | SAN & STRM SEWER IN HALPIN AVE | 2 | PRELIMINARY DESIGN | Sep 2012 | Jan 2013 | Sep 2010 | Jan 2011
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002317 | SAN & STRM SEWER IN HALPIN AVE | 3 | FINAL DESIGN | Jan 2013 | Jul 2013 | Jan 2011 | Jul 2011
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002317 | SAN & STRM SEWER IN HALPIN AVE | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2013 | Oct 2013 | Mar 2014 | Jun 2014
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002317 | SAN & STRM SEWER IN HALPIN AVE | 5 | CONSTRUCTION TO 25% | Oct 2013 | Feb 2014 | Jun 2014 | Jun 2014
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002317 | SAN & STRM SEWER IN HALPIN AVE | 6 | CONSTRUCTION TO 50% | Feb 2014 | Jun 2014 | Jun 2014 | Jun 2014
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002317 | SAN & STRM SEWER IN HALPIN AVE | 7 | CONSTRUCTION TO 75% | Jun 2014 | Oct 2014 | Jun 2014 | Jun 2014
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002317 | SAN & STRM SEWER IN HALPIN AVE | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2014 | Jan 2015 | Jun 2014 | Jun 2014
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002317 | SAN & STRM SEWER IN HALPIN AVE | 9 | SUBSTANTIAL COMPLETION | Jan 2015 | Mar 2015 | Jun 2014 | Jun 2014
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002317 | SAN & STRM SEWER IN HALPIN AVE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Apr 2015 | Jun 2014 | Jul 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002317 | SAN & STRM SEWER IN HALPIN AVE | 11 | PROJECT START | Mar 2015 | Apr 2015 | Jul 2024 | Jul 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002317 | SAN & STRM SEWER IN HALPIN AVE | 12 | DESIGN START | Mar 2015 | Apr 2015 | Aug 2024 | Aug 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002317 | SAN & STRM SEWER IN HALPIN AVE | 13 | DESIGN COMPLETION | Mar 2015 | Apr 2015 | Aug 2024 | Aug 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002317 | SAN & STRM SEWER IN HALPIN AVE | 14 | CONSTRUCTION START | Mar 2015 | Apr 2015 | Aug 2024 | Aug 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002317 | SAN & STRM SEWER IN HALPIN AVE | 15 | CONSTRUCTION COMPLETION | Mar 2015 | Apr 2015 | Aug 2024 | Jun 2027
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002324 | New sanitary sewers in Camden ave. Staten Island | 1 | DEVELOP SCOPE | Aug 2010 | Apr 2011 | Aug 2010 | Apr 2011
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002324 | New sanitary sewers in Camden ave. Staten Island | 2 | PRELIMINARY DESIGN | Apr 2011 | Apr 2012 | Apr 2011 | Apr 2012
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002324 | New sanitary sewers in Camden ave. Staten Island | 3 | FINAL DESIGN | Apr 2012 | Oct 2013 | Apr 2012 | Oct 2013
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002324 | New sanitary sewers in Camden ave. Staten Island | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2013 | Jul 2014 | Oct 2013 | Jul 2014
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002324 | New sanitary sewers in Camden ave. Staten Island | 5 | CONSTRUCTION TO 25% | Jul 2014 | Jul 2015 | Jul 2014 | Jul 2015
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002324 | New sanitary sewers in Camden ave. Staten Island | 6 | CONSTRUCTION TO 50% | Jul 2015 | Jul 2016 | Jul 2015 | Jul 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002324 | New sanitary sewers in Camden ave. Staten Island | 7 | CONSTRUCTION TO 75% | Jul 2016 | Jun 2017 | Jul 2016 | Jun 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002324 | New sanitary sewers in Camden ave. Staten Island | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2017 | Mar 2018 | Jun 2017 | Mar 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002324 | New sanitary sewers in Camden ave. Staten Island | 9 | SUBSTANTIAL COMPLETION | Mar 2018 | Sep 2018 | Mar 2018 | Sep 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002324 | New sanitary sewers in Camden ave. Staten Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2018 | Dec 2018 | Sep 2018 | Jun 2028
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002329 | SAN, STM & WM IN LANDMARK COLONY | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002329 | SAN, STM & WM IN LANDMARK COLONY | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002329 | SAN, STM & WM IN LANDMARK COLONY | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002329 | SAN, STM & WM IN LANDMARK COLONY | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002329 | SAN, STM & WM IN LANDMARK COLONY | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002329 | SAN, STM & WM IN LANDMARK COLONY | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002329 | SAN, STM & WM IN LANDMARK COLONY | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002329 | SAN, STM & WM IN LANDMARK COLONY | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002329 | SAN, STM & WM IN LANDMARK COLONY | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002329 | SAN, STM & WM IN LANDMARK COLONY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2021 | Nov 2019 | Dec 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002333 | SE & WM Van Buren St btwn York Ave & FranklIn Ave SI, HWTRR1 | 1 | DEVELOP SCOPE | Jan 2023 | Mar 2023 | Jan 2023 | Mar 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002333 | SE & WM Van Buren St btwn York Ave & FranklIn Ave SI, HWTRR1 | 2 | PRELIMINARY DESIGN | Apr 2023 | Jul 2023 | Apr 2023 | Jul 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002333 | SE & WM Van Buren St btwn York Ave & FranklIn Ave SI, HWTRR1 | 3 | FINAL DESIGN | Jul 2023 | Jan 2024 | Jul 2023 | Jan 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002333 | SE & WM Van Buren St btwn York Ave & FranklIn Ave SI, HWTRR1 | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2024 | Apr 2024 | Jan 2024 | Apr 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002333 | SE & WM Van Buren St btwn York Ave & FranklIn Ave SI, HWTRR1 | 5 | CONSTRUCTION TO 25% | Apr 2024 | Aug 2024 | Apr 2024 | Aug 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002333 | SE & WM Van Buren St btwn York Ave & FranklIn Ave SI, HWTRR1 | 6 | CONSTRUCTION TO 50% | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002333 | SE & WM Van Buren St btwn York Ave & FranklIn Ave SI, HWTRR1 | 7 | CONSTRUCTION TO 75% | Dec 2024 | Apr 2025 | Dec 2024 | Apr 2025
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002333 | SE & WM Van Buren St btwn York Ave & FranklIn Ave SI, HWTRR1 | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2025 | Jul 2025 | Apr 2025 | Jul 2025
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002333 | SE & WM Van Buren St btwn York Ave & FranklIn Ave SI, HWTRR1 | 9 | SUBSTANTIAL COMPLETION | Jul 2025 | Sep 2025 | Jul 2025 | Sep 2025
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002333 | SE & WM Van Buren St btwn York Ave & FranklIn Ave SI, HWTRR1 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Oct 2025 | Sep 2025 | Oct 2032
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002334 | NDF - Rplcmt 6" sanitary sewers & distribution wtr mains SI | 1 | DEVELOP SCOPE | Nov 2020 | Aug 2021 | Nov 2020 | Aug 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002334 | NDF - Rplcmt 6" sanitary sewers & distribution wtr mains SI | 2 | PRELIMINARY DESIGN | Aug 2021 | Jul 2022 | Aug 2021 | Jul 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002334 | NDF - Rplcmt 6" sanitary sewers & distribution wtr mains SI | 3 | FINAL DESIGN | Aug 2022 | Jan 2024 | Aug 2022 | Jan 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002334 | NDF - Rplcmt 6" sanitary sewers & distribution wtr mains SI | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2024 | Oct 2024 | Jan 2024 | Oct 2024
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002334 | NDF - Rplcmt 6" sanitary sewers & distribution wtr mains SI | 5 | CONSTRUCTION TO 25% | Oct 2024 | Oct 2025 | Oct 2024 | Oct 2025
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002334 | NDF - Rplcmt 6" sanitary sewers & distribution wtr mains SI | 6 | CONSTRUCTION TO 50% | Oct 2025 | Oct 2026 | Oct 2025 | Oct 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002334 | NDF - Rplcmt 6" sanitary sewers & distribution wtr mains SI | 7 | CONSTRUCTION TO 75% | Oct 2026 | Oct 2027 | Oct 2026 | Oct 2027
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002334 | NDF - Rplcmt 6" sanitary sewers & distribution wtr mains SI | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jun 2028 | Oct 2027 | Jun 2028
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002334 | NDF - Rplcmt 6" sanitary sewers & distribution wtr mains SI | 9 | SUBSTANTIAL COMPLETION | Jun 2028 | Dec 2028 | Jun 2028 | Dec 2028
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002334 | NDF - Rplcmt 6" sanitary sewers & distribution wtr mains SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2028 | Mar 2029 | Dec 2028 | Mar 2029
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200232 | STORM,SANIT SEWERS & WATER MAIN IN XENIA ST | 1 | DEVELOP SCOPE | Feb 2014 | May 2014 | Feb 2014 | May 2014
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200232 | STORM,SANIT SEWERS & WATER MAIN IN XENIA ST | 2 | PRELIMINARY DESIGN | May 2014 | Sep 2014 | May 2014 | Sep 2014
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200232 | STORM,SANIT SEWERS & WATER MAIN IN XENIA ST | 3 | FINAL DESIGN | Sep 2014 | Mar 2015 | Sep 2014 | Mar 2015
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200232 | STORM,SANIT SEWERS & WATER MAIN IN XENIA ST | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2015 | Jun 2015 | Mar 2015 | Jun 2015
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200232 | STORM,SANIT SEWERS & WATER MAIN IN XENIA ST | 5 | CONSTRUCTION TO 25% | Jun 2015 | Oct 2015 | Jun 2015 | Oct 2015
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200232 | STORM,SANIT SEWERS & WATER MAIN IN XENIA ST | 6 | CONSTRUCTION TO 50% | Oct 2015 | Feb 2016 | Oct 2015 | Feb 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200232 | STORM,SANIT SEWERS & WATER MAIN IN XENIA ST | 7 | CONSTRUCTION TO 75% | Feb 2016 | Jun 2016 | Feb 2016 | Jun 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200232 | STORM,SANIT SEWERS & WATER MAIN IN XENIA ST | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2016 | Sep 2016 | Jun 2016 | Sep 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200232 | STORM,SANIT SEWERS & WATER MAIN IN XENIA ST | 9 | SUBSTANTIAL COMPLETION | Sep 2016 | Nov 2016 | Sep 2016 | Nov 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200232 | STORM,SANIT SEWERS & WATER MAIN IN XENIA ST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2016 | Dec 2016 | Nov 2016 | Sep 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200236 | STRM SWR EXT & WM WORK IN NORTH AV, ETC. | 1 | DEVELOP SCOPE | Mar 2019 | May 2019 | Mar 2019 | May 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200236 | STRM SWR EXT & WM WORK IN NORTH AV, ETC. | 2 | PRELIMINARY DESIGN | May 2019 | Sep 2019 | May 2019 | Sep 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200236 | STRM SWR EXT & WM WORK IN NORTH AV, ETC. | 3 | FINAL DESIGN | Sep 2019 | Mar 2020 | Sep 2019 | Mar 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200236 | STRM SWR EXT & WM WORK IN NORTH AV, ETC. | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Jun 2020 | Mar 2020 | Jun 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200236 | STRM SWR EXT & WM WORK IN NORTH AV, ETC. | 5 | CONSTRUCTION TO 25% | Jun 2020 | Oct 2020 | Jun 2020 | Oct 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200236 | STRM SWR EXT & WM WORK IN NORTH AV, ETC. | 6 | CONSTRUCTION TO 50% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200236 | STRM SWR EXT & WM WORK IN NORTH AV, ETC. | 7 | CONSTRUCTION TO 75% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200236 | STRM SWR EXT & WM WORK IN NORTH AV, ETC. | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200236 | STRM SWR EXT & WM WORK IN NORTH AV, ETC. | 9 | SUBSTANTIAL COMPLETION | Sep 2021 | Nov 2021 | Sep 2021 | Nov 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200236 | STRM SWR EXT & WM WORK IN NORTH AV, ETC. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2021 | Dec 2021 | Nov 2021 | Dec 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200247 | New Storm Sewers in King St | 1 | DEVELOP SCOPE | Apr 2013 | Jan 2014 | Apr 2013 | Jan 2014
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200247 | New Storm Sewers in King St | 2 | PRELIMINARY DESIGN | Jan 2014 | Jan 2015 | Jan 2014 | Jan 2015
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200247 | New Storm Sewers in King St | 3 | FINAL DESIGN | Jan 2015 | Jun 2016 | Jan 2015 | Jun 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200247 | New Storm Sewers in King St | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Mar 2017 | Jul 2016 | Mar 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200247 | New Storm Sewers in King St | 5 | CONSTRUCTION TO 25% | Mar 2017 | Mar 2018 | Mar 2017 | Mar 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200247 | New Storm Sewers in King St | 6 | CONSTRUCTION TO 50% | Mar 2018 | Mar 2019 | Mar 2018 | Mar 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200247 | New Storm Sewers in King St | 7 | CONSTRUCTION TO 75% | Mar 2019 | Mar 2020 | Mar 2019 | Mar 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200247 | New Storm Sewers in King St | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2020 | Dec 2020 | Mar 2020 | Dec 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200247 | New Storm Sewers in King St | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200247 | New Storm Sewers in King St | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2028
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200251 | EXT OF STRM SWR AND WM WORK IN 3RD ST | 1 | DEVELOP SCOPE | Mar 2021 | May 2021 | Mar 2021 | May 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200251 | EXT OF STRM SWR AND WM WORK IN 3RD ST | 2 | PRELIMINARY DESIGN | May 2021 | Sep 2021 | May 2021 | Sep 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200251 | EXT OF STRM SWR AND WM WORK IN 3RD ST | 3 | FINAL DESIGN | Sep 2021 | Mar 2022 | Sep 2021 | Mar 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200251 | EXT OF STRM SWR AND WM WORK IN 3RD ST | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2022 | Jun 2022 | Mar 2022 | Jun 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200251 | EXT OF STRM SWR AND WM WORK IN 3RD ST | 5 | CONSTRUCTION TO 25% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200251 | EXT OF STRM SWR AND WM WORK IN 3RD ST | 6 | CONSTRUCTION TO 50% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200251 | EXT OF STRM SWR AND WM WORK IN 3RD ST | 7 | CONSTRUCTION TO 75% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200251 | EXT OF STRM SWR AND WM WORK IN 3RD ST | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200251 | EXT OF STRM SWR AND WM WORK IN 3RD ST | 9 | SUBSTANTIAL COMPLETION | Sep 2023 | Nov 2023 | Sep 2023 | Nov 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200251 | EXT OF STRM SWR AND WM WORK IN 3RD ST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2023 | Dec 2023 | Nov 2023 | Dec 2032
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200258 | Sanitary and Storm Sewer in West Castor Place between Alvers | 1 | DEVELOP SCOPE | Feb 2015 | May 2015 | Feb 2015 | May 2015
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200258 | Sanitary and Storm Sewer in West Castor Place between Alvers | 2 | PRELIMINARY DESIGN | May 2015 | Sep 2015 | May 2015 | Sep 2015
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200258 | Sanitary and Storm Sewer in West Castor Place between Alvers | 3 | FINAL DESIGN | Sep 2015 | Mar 2016 | Sep 2015 | Mar 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200258 | Sanitary and Storm Sewer in West Castor Place between Alvers | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2016 | Jun 2016 | Mar 2016 | Jun 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200258 | Sanitary and Storm Sewer in West Castor Place between Alvers | 5 | CONSTRUCTION TO 25% | Jun 2016 | Oct 2016 | Jun 2016 | Oct 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200258 | Sanitary and Storm Sewer in West Castor Place between Alvers | 6 | CONSTRUCTION TO 50% | Oct 2016 | Feb 2017 | Oct 2016 | Feb 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200258 | Sanitary and Storm Sewer in West Castor Place between Alvers | 7 | CONSTRUCTION TO 75% | Feb 2017 | Jun 2017 | Feb 2017 | Jun 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200258 | Sanitary and Storm Sewer in West Castor Place between Alvers | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2017 | Sep 2017 | Jun 2017 | Sep 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200258 | Sanitary and Storm Sewer in West Castor Place between Alvers | 9 | SUBSTANTIAL COMPLETION | Sep 2017 | Nov 2017 | Sep 2017 | Nov 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200258 | Sanitary and Storm Sewer in West Castor Place between Alvers | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | Dec 2017 | Nov 2017 | Jun 2030
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200261 | Storm sewer in Roma Ave bet Tysens Lane & Ebbits Street | 1 | DEVELOP SCOPE | Mar 2018 | May 2018 | Mar 2018 | May 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200261 | Storm sewer in Roma Ave bet Tysens Lane & Ebbits Street | 2 | PRELIMINARY DESIGN | May 2018 | Sep 2018 | May 2018 | Sep 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200261 | Storm sewer in Roma Ave bet Tysens Lane & Ebbits Street | 3 | FINAL DESIGN | Sep 2018 | Mar 2019 | Sep 2018 | Mar 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200261 | Storm sewer in Roma Ave bet Tysens Lane & Ebbits Street | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2019 | Jun 2019 | Mar 2019 | Jun 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200261 | Storm sewer in Roma Ave bet Tysens Lane & Ebbits Street | 5 | CONSTRUCTION TO 25% | Jun 2019 | Oct 2019 | Jun 2019 | Oct 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200261 | Storm sewer in Roma Ave bet Tysens Lane & Ebbits Street | 6 | CONSTRUCTION TO 50% | Oct 2019 | Feb 2020 | Oct 2019 | Feb 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200261 | Storm sewer in Roma Ave bet Tysens Lane & Ebbits Street | 7 | CONSTRUCTION TO 75% | Feb 2020 | Jun 2020 | Feb 2020 | Jun 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200261 | Storm sewer in Roma Ave bet Tysens Lane & Ebbits Street | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200261 | Storm sewer in Roma Ave bet Tysens Lane & Ebbits Street | 9 | SUBSTANTIAL COMPLETION | Sep 2020 | Nov 2020 | Sep 2020 | Nov 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200261 | Storm sewer in Roma Ave bet Tysens Lane & Ebbits Street | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2020 | Dec 2020 | Nov 2020 | Dec 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200285 | NEW STM. SWR EXT. & WM REPL IN TODT HILL RD., SI, HWR005B1 | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200285 | NEW STM. SWR EXT. & WM REPL IN TODT HILL RD., SI, HWR005B1 | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200285 | NEW STM. SWR EXT. & WM REPL IN TODT HILL RD., SI, HWR005B1 | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200285 | NEW STM. SWR EXT. & WM REPL IN TODT HILL RD., SI, HWR005B1 | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200285 | NEW STM. SWR EXT. & WM REPL IN TODT HILL RD., SI, HWR005B1 | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200285 | NEW STM. SWR EXT. & WM REPL IN TODT HILL RD., SI, HWR005B1 | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200285 | NEW STM. SWR EXT. & WM REPL IN TODT HILL RD., SI, HWR005B1 | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200285 | NEW STM. SWR EXT. & WM REPL IN TODT HILL RD., SI, HWR005B1 | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200285 | NEW STM. SWR EXT. & WM REPL IN TODT HILL RD., SI, HWR005B1 | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200285 | NEW STM. SWR EXT. & WM REPL IN TODT HILL RD., SI, HWR005B1 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Sep 2032
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200290 | New Storm Sewer Ext & Water Main Replacement in Forest Ave | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jun 2018 | Aug 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200290 | New Storm Sewer Ext & Water Main Replacement in Forest Ave | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Aug 2018 | Dec 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200290 | New Storm Sewer Ext & Water Main Replacement in Forest Ave | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Dec 2018 | Jun 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200290 | New Storm Sewer Ext & Water Main Replacement in Forest Ave | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200290 | New Storm Sewer Ext & Water Main Replacement in Forest Ave | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200290 | New Storm Sewer Ext & Water Main Replacement in Forest Ave | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Jan 2020 | May 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200290 | New Storm Sewer Ext & Water Main Replacement in Forest Ave | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | May 2020 | Sep 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200290 | New Storm Sewer Ext & Water Main Replacement in Forest Ave | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Sep 2020 | Dec 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200290 | New Storm Sewer Ext & Water Main Replacement in Forest Ave | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Dec 2020 | Feb 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200290 | New Storm Sewer Ext & Water Main Replacement in Forest Ave | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Feb 2021 | Jan 2031
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200292 | SAN & STRM SWR REPLACMT & WM WORK IN FLOYD ST | 1 | DEVELOP SCOPE | Oct 2020 | Dec 2020 | Oct 2020 | Dec 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200292 | SAN & STRM SWR REPLACMT & WM WORK IN FLOYD ST | 2 | PRELIMINARY DESIGN | Dec 2020 | Apr 2021 | Dec 2020 | Apr 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200292 | SAN & STRM SWR REPLACMT & WM WORK IN FLOYD ST | 3 | FINAL DESIGN | Apr 2021 | Oct 2021 | Apr 2021 | Oct 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200292 | SAN & STRM SWR REPLACMT & WM WORK IN FLOYD ST | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2021 | Jan 2022 | Oct 2021 | Jan 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200292 | SAN & STRM SWR REPLACMT & WM WORK IN FLOYD ST | 5 | CONSTRUCTION TO 25% | Jan 2022 | May 2022 | Jan 2022 | May 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200292 | SAN & STRM SWR REPLACMT & WM WORK IN FLOYD ST | 6 | CONSTRUCTION TO 50% | May 2022 | Sep 2022 | May 2022 | Sep 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200292 | SAN & STRM SWR REPLACMT & WM WORK IN FLOYD ST | 7 | CONSTRUCTION TO 75% | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200292 | SAN & STRM SWR REPLACMT & WM WORK IN FLOYD ST | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2023 | Apr 2023 | Jan 2023 | Apr 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200292 | SAN & STRM SWR REPLACMT & WM WORK IN FLOYD ST | 9 | SUBSTANTIAL COMPLETION | Apr 2023 | Jun 2023 | Apr 2023 | Jun 2023
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200292 | SAN & STRM SWR REPLACMT & WM WORK IN FLOYD ST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2023 | Jul 2023 | Jun 2023 | Oct 2032
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200309 | Strm swr R+Ext & WM Work, Maguire Avenue | 1 | DEVELOP SCOPE | Jan 2018 | Apr 2018 | Jan 2018 | Apr 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200309 | Strm swr R+Ext & WM Work, Maguire Avenue | 2 | PRELIMINARY DESIGN | Apr 2018 | Aug 2018 | Apr 2018 | Aug 2018
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200309 | Strm swr R+Ext & WM Work, Maguire Avenue | 3 | FINAL DESIGN | Aug 2018 | Feb 2019 | Aug 2018 | Feb 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200309 | Strm swr R+Ext & WM Work, Maguire Avenue | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2019 | May 2019 | Feb 2019 | May 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200309 | Strm swr R+Ext & WM Work, Maguire Avenue | 5 | CONSTRUCTION TO 25% | May 2019 | Sep 2019 | May 2019 | Sep 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200309 | Strm swr R+Ext & WM Work, Maguire Avenue | 6 | CONSTRUCTION TO 50% | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200309 | Strm swr R+Ext & WM Work, Maguire Avenue | 7 | CONSTRUCTION TO 75% | Jan 2020 | May 2020 | Jan 2020 | May 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200309 | Strm swr R+Ext & WM Work, Maguire Avenue | 8 | ORIGINAL EQUIP & FURNISHING | May 2020 | Aug 2020 | May 2020 | Aug 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200309 | Strm swr R+Ext & WM Work, Maguire Avenue | 9 | SUBSTANTIAL COMPLETION | Aug 2020 | Sep 2020 | Aug 2020 | Sep 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200309 | Strm swr R+Ext & WM Work, Maguire Avenue | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2020 | Oct 2020 | Oct 2020 | Jun 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200322 | New Storm Sewers in Saxon Ave & Draper Pl, SI, HWR00511 | 1 | DEVELOP SCOPE | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200322 | New Storm Sewers in Saxon Ave & Draper Pl, SI, HWR00511 | 2 | PRELIMINARY DESIGN | Apr 2026 | Jul 2026 | Apr 2026 | Jul 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200322 | New Storm Sewers in Saxon Ave & Draper Pl, SI, HWR00511 | 3 | FINAL DESIGN | Jul 2026 | Jan 2027 | Jul 2026 | Jan 2027
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200322 | New Storm Sewers in Saxon Ave & Draper Pl, SI, HWR00511 | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2027 | Apr 2027 | Jan 2027 | Apr 2027
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200322 | New Storm Sewers in Saxon Ave & Draper Pl, SI, HWR00511 | 5 | CONSTRUCTION TO 25% | Apr 2027 | Aug 2027 | Apr 2027 | Aug 2027
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200322 | New Storm Sewers in Saxon Ave & Draper Pl, SI, HWR00511 | 6 | CONSTRUCTION TO 50% | Aug 2027 | Dec 2027 | Aug 2027 | Dec 2027
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200322 | New Storm Sewers in Saxon Ave & Draper Pl, SI, HWR00511 | 7 | CONSTRUCTION TO 75% | Dec 2027 | Apr 2028 | Dec 2027 | Apr 2028
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200322 | New Storm Sewers in Saxon Ave & Draper Pl, SI, HWR00511 | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2028 | Jul 2028 | Apr 2028 | Jul 2028
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200322 | New Storm Sewers in Saxon Ave & Draper Pl, SI, HWR00511 | 9 | SUBSTANTIAL COMPLETION | Jul 2028 | Sep 2028 | Jul 2028 | Sep 2028
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200322 | New Storm Sewers in Saxon Ave & Draper Pl, SI, HWR00511 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2028 | Oct 2028 | Sep 2028 | Oct 2028
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200552 | STRM & SAN SWR AND WM WORK IN GRANITE AV | 1 | DEVELOP SCOPE | Oct 2019 | Dec 2019 | Oct 2019 | Dec 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200552 | STRM & SAN SWR AND WM WORK IN GRANITE AV | 2 | PRELIMINARY DESIGN | Dec 2019 | Apr 2020 | Dec 2019 | Apr 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200552 | STRM & SAN SWR AND WM WORK IN GRANITE AV | 3 | FINAL DESIGN | Apr 2020 | Oct 2020 | Apr 2020 | Oct 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200552 | STRM & SAN SWR AND WM WORK IN GRANITE AV | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2020 | Jan 2021 | Oct 2020 | Jan 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200552 | STRM & SAN SWR AND WM WORK IN GRANITE AV | 5 | CONSTRUCTION TO 25% | Jan 2021 | May 2021 | Jan 2021 | May 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200552 | STRM & SAN SWR AND WM WORK IN GRANITE AV | 6 | CONSTRUCTION TO 50% | May 2021 | Sep 2021 | May 2021 | Sep 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200552 | STRM & SAN SWR AND WM WORK IN GRANITE AV | 7 | CONSTRUCTION TO 75% | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200552 | STRM & SAN SWR AND WM WORK IN GRANITE AV | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2022 | Apr 2022 | Jan 2022 | Apr 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200552 | STRM & SAN SWR AND WM WORK IN GRANITE AV | 9 | SUBSTANTIAL COMPLETION | Apr 2022 | Jun 2022 | Apr 2022 | Jun 2022
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200552 | STRM & SAN SWR AND WM WORK IN GRANITE AV | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Jul 2022 | Jun 2022 | Jun 2031
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER20079 | RECON OF STORM SEWER, WILLOW AV(TOMPKINS-EDGEWATER AVS) | 1 | DEVELOP SCOPE | Feb 2008 | May 2008 | Jun 2011 | Sep 2011
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER20079 | RECON OF STORM SEWER, WILLOW AV(TOMPKINS-EDGEWATER AVS) | 2 | PRELIMINARY DESIGN | May 2008 | Sep 2008 | Sep 2011 | Mar 2012
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER20079 | RECON OF STORM SEWER, WILLOW AV(TOMPKINS-EDGEWATER AVS) | 3 | FINAL DESIGN | Sep 2008 | Mar 2009 | Mar 2012 | Mar 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER20079 | RECON OF STORM SEWER, WILLOW AV(TOMPKINS-EDGEWATER AVS) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2009 | Jun 2009 | Mar 2016 | Mar 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER20079 | RECON OF STORM SEWER, WILLOW AV(TOMPKINS-EDGEWATER AVS) | 5 | CONSTRUCTION TO 25% | Jun 2009 | Oct 2009 | Mar 2016 | Mar 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER20079 | RECON OF STORM SEWER, WILLOW AV(TOMPKINS-EDGEWATER AVS) | 6 | CONSTRUCTION TO 50% | Oct 2009 | Feb 2010 | Mar 2016 | Mar 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER20079 | RECON OF STORM SEWER, WILLOW AV(TOMPKINS-EDGEWATER AVS) | 7 | CONSTRUCTION TO 75% | Feb 2010 | Jun 2010 | Mar 2016 | Mar 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER20079 | RECON OF STORM SEWER, WILLOW AV(TOMPKINS-EDGEWATER AVS) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2010 | Sep 2010 | Mar 2016 | Mar 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER20079 | RECON OF STORM SEWER, WILLOW AV(TOMPKINS-EDGEWATER AVS) | 9 | SUBSTANTIAL COMPLETION | Sep 2010 | Nov 2010 | Mar 2016 | Mar 2016
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER20079 | RECON OF STORM SEWER, WILLOW AV(TOMPKINS-EDGEWATER AVS) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2010 | Dec 2010 | Mar 2016 | Sep 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER20079 | RECON OF STORM SEWER, WILLOW AV(TOMPKINS-EDGEWATER AVS) | 11 | PROJECT START | Nov 2010 | Dec 2010 | Sep 2021 | Sep 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER20079 | RECON OF STORM SEWER, WILLOW AV(TOMPKINS-EDGEWATER AVS) | 12 | DESIGN START | Nov 2010 | Dec 2010 | Sep 2021 | Sep 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER20079 | RECON OF STORM SEWER, WILLOW AV(TOMPKINS-EDGEWATER AVS) | 13 | DESIGN COMPLETION | Nov 2010 | Dec 2010 | Oct 2021 | Oct 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER20079 | RECON OF STORM SEWER, WILLOW AV(TOMPKINS-EDGEWATER AVS) | 14 | CONSTRUCTION START | Nov 2010 | Dec 2010 | Oct 2021 | Oct 2021
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER20079 | RECON OF STORM SEWER, WILLOW AV(TOMPKINS-EDGEWATER AVS) | 15 | CONSTRUCTION COMPLETION | Nov 2010 | Dec 2010 | Oct 2021 | Jun 2032
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARDOS2 | Staten Island 3 Garage HVAC | 1 | PROJECT START | Mar 2019 | Mar 2019 | Dec 2015 | Dec 2015
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARDOS2 | Staten Island 3 Garage HVAC | 2 | DESIGN START | Mar 2019 | Mar 2019 | Dec 2015 | Jul 2017
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARDOS2 | Staten Island 3 Garage HVAC | 3 | DESIGN COMPLETION | Mar 2019 | Mar 2019 | Jul 2017 | Jun 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARDOS2 | Staten Island 3 Garage HVAC | 4 | CONSTRUCTION START | Mar 2019 | Mar 2019 | Jun 2019 | Mar 2020
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARDOS2 | Staten Island 3 Garage HVAC | 5 | CONSTRUCTION COMPLETION | Mar 2019 | Mar 2019 | Mar 2020 | Mar 2026
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARGR10 | DSNY - PV INSTALLATION ON NEW GARAGE- STATEN ISLAND 1/3 | 1 | PROJECT START | Mar 2019 | Mar 2019 | Mar 2019 | Mar 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARGR10 | DSNY - PV INSTALLATION ON NEW GARAGE- STATEN ISLAND 1/3 | 2 | DESIGN START | Mar 2019 | Mar 2019 | Mar 2019 | Mar 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARGR10 | DSNY - PV INSTALLATION ON NEW GARAGE- STATEN ISLAND 1/3 | 3 | DESIGN COMPLETION | Mar 2019 | Mar 2019 | Mar 2019 | Mar 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARGR10 | DSNY - PV INSTALLATION ON NEW GARAGE- STATEN ISLAND 1/3 | 4 | CONSTRUCTION START | Mar 2019 | Mar 2019 | Mar 2019 | Mar 2019
20231026 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARGR10 | DSNY - PV INSTALLATION ON NEW GARAGE- STATEN ISLAND 1/3 | 5 | CONSTRUCTION COMPLETION | Mar 2019 | Dec 2022 | Mar 2019 | Dec 2024
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACENPL231 | NYPL St. George Library Center Electrification | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2023 | Jun 2023 | Jun 2023
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACENPL231 | NYPL St. George Library Center Electrification | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACENPL231 | NYPL St. George Library Center Electrification | 3 | CONSTRUCTION TO 50% | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACENPL231 | NYPL St. George Library Center Electrification | 4 | CONSTRUCTION TO 75% | Feb 2024 | May 2024 | Feb 2024 | May 2024
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACENPL231 | NYPL St. George Library Center Electrification | 5 | SUBSTANTIAL COMPLETION | May 2024 | Jul 2024 | May 2024 | Jul 2024
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACENPL231 | NYPL St. George Library Center Electrification | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264SIMP | DASNY - STATEN ISLAND MASTER PLAN- PHASE 2 | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264SIMP | DASNY - STATEN ISLAND MASTER PLAN- PHASE 2 | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264SIMP | DASNY - STATEN ISLAND MASTER PLAN- PHASE 2 | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264SIMP | DASNY - STATEN ISLAND MASTER PLAN- PHASE 2 | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264SIMP | DASNY - STATEN ISLAND MASTER PLAN- PHASE 2 | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264SIMP | DASNY - STATEN ISLAND MASTER PLAN- PHASE 2 | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264SIMP | DASNY - STATEN ISLAND MASTER PLAN- PHASE 2 | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264SIMP | DASNY - STATEN ISLAND MASTER PLAN- PHASE 2 | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264SIMP | DASNY - STATEN ISLAND MASTER PLAN- PHASE 2 | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264SIMP | DASNY - STATEN ISLAND MASTER PLAN- PHASE 2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2026
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO287R-1 | DASNY - NEW STATEN ISLAND SUPREME COURT | 1 | DEVELOP SCOPE | Jun 2006 | Aug 2006 | Jun 2006 | Aug 2006
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO287R-1 | DASNY - NEW STATEN ISLAND SUPREME COURT | 2 | PRELIMINARY DESIGN | Aug 2006 | Dec 2006 | Aug 2006 | Dec 2006
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO287R-1 | DASNY - NEW STATEN ISLAND SUPREME COURT | 3 | FINAL DESIGN | Dec 2006 | Jun 2007 | Dec 2006 | Jun 2007
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO287R-1 | DASNY - NEW STATEN ISLAND SUPREME COURT | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2007 | Sep 2007 | Jun 2007 | Sep 2007
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO287R-1 | DASNY - NEW STATEN ISLAND SUPREME COURT | 5 | CONSTRUCTION TO 25% | Sep 2007 | Jan 2009 | Sep 2007 | Jan 2009
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO287R-1 | DASNY - NEW STATEN ISLAND SUPREME COURT | 6 | CONSTRUCTION TO 50% | Jan 2009 | May 2010 | Jun 2027 | Sep 2028
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO287R-1 | DASNY - NEW STATEN ISLAND SUPREME COURT | 7 | CONSTRUCTION TO 75% | May 2010 | May 2011 | Sep 2028 | Sep 2029
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO287R-1 | DASNY - NEW STATEN ISLAND SUPREME COURT | 8 | ORIGINAL EQUIP & FURNISHING | May 2011 | Aug 2011 | Jun 2027 | May 2028
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO287R-1 | DASNY - NEW STATEN ISLAND SUPREME COURT | 9 | SUBSTANTIAL COMPLETION | Aug 2011 | Nov 2011 | May 2028 | Aug 2028
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO287R-1 | DASNY - NEW STATEN ISLAND SUPREME COURT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2011 | Dec 2011 | Aug 2028 | Sep 2028
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO288MS4 | 927 CASTLETON AVE- SI CIVIL CT- MS-4 SITE RENOVATION | 1 | DEVELOP SCOPE | Jun 2024 | Aug 2024 | Jun 2024 | Aug 2024
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO288MS4 | 927 CASTLETON AVE- SI CIVIL CT- MS-4 SITE RENOVATION | 2 | PRELIMINARY DESIGN | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO288MS4 | 927 CASTLETON AVE- SI CIVIL CT- MS-4 SITE RENOVATION | 3 | FINAL DESIGN | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO288MS4 | 927 CASTLETON AVE- SI CIVIL CT- MS-4 SITE RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO288MS4 | 927 CASTLETON AVE- SI CIVIL CT- MS-4 SITE RENOVATION | 5 | CONSTRUCTION TO 25% | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO288MS4 | 927 CASTLETON AVE- SI CIVIL CT- MS-4 SITE RENOVATION | 6 | CONSTRUCTION TO 50% | Jan 2026 | May 2026 | Jan 2026 | May 2026
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO288MS4 | 927 CASTLETON AVE- SI CIVIL CT- MS-4 SITE RENOVATION | 7 | CONSTRUCTION TO 75% | May 2026 | Sep 2026 | May 2026 | Sep 2026
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO288MS4 | 927 CASTLETON AVE- SI CIVIL CT- MS-4 SITE RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2026 | Dec 2026 | Sep 2026 | Dec 2026
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO288MS4 | 927 CASTLETON AVE- SI CIVIL CT- MS-4 SITE RENOVATION | 9 | SUBSTANTIAL COMPLETION | Dec 2026 | Feb 2027 | Dec 2026 | Feb 2027
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO288MS4 | 927 CASTLETON AVE- SI CIVIL CT- MS-4 SITE RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2027 | Mar 2027 | Feb 2027 | Mar 2027
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301FA | 130 STUYVESANT PL.- ELEC/FIRE ALARM UPGRADE | 1 | DEVELOP SCOPE | Mar 2016 | May 2016 | Jun 2022 | Aug 2022
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301FA | 130 STUYVESANT PL.- ELEC/FIRE ALARM UPGRADE | 2 | PRELIMINARY DESIGN | May 2016 | Sep 2016 | Aug 2022 | Dec 2022
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301FA | 130 STUYVESANT PL.- ELEC/FIRE ALARM UPGRADE | 3 | FINAL DESIGN | Sep 2016 | Mar 2017 | Dec 2022 | Jun 2023
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301FA | 130 STUYVESANT PL.- ELEC/FIRE ALARM UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2017 | Jun 2017 | Jun 2023 | Sep 2023
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301FA | 130 STUYVESANT PL.- ELEC/FIRE ALARM UPGRADE | 5 | CONSTRUCTION TO 25% | Jun 2017 | Oct 2017 | Jun 2027 | Sep 2027
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301FA | 130 STUYVESANT PL.- ELEC/FIRE ALARM UPGRADE | 6 | CONSTRUCTION TO 50% | Oct 2017 | Feb 2018 | Sep 2027 | Jan 2028
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301FA | 130 STUYVESANT PL.- ELEC/FIRE ALARM UPGRADE | 7 | CONSTRUCTION TO 75% | Feb 2018 | Jun 2018 | Jan 2028 | May 2028
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301FA | 130 STUYVESANT PL.- ELEC/FIRE ALARM UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2018 | Sep 2018 | May 2028 | Aug 2028
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301FA | 130 STUYVESANT PL.- ELEC/FIRE ALARM UPGRADE | 9 | SUBSTANTIAL COMPLETION | Sep 2018 | Nov 2018 | Aug 2028 | Oct 2028
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301FA | 130 STUYVESANT PL.- ELEC/FIRE ALARM UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2018 | Dec 2018 | Oct 2028 | Nov 2028
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0010 | DCAS - S.I. Campus - Deep Energy Retrofit | 1 | DEVELOP SCOPE | Aug 2021 | Sep 2021 | Aug 2021 | Sep 2021
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0010 | DCAS - S.I. Campus - Deep Energy Retrofit | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2021 | Nov 2021 | Sep 2021 | Nov 2021
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0010 | DCAS - S.I. Campus - Deep Energy Retrofit | 3 | CONSTRUCTION TO 50% | Nov 2021 | May 2022 | Nov 2021 | May 2022
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0010 | DCAS - S.I. Campus - Deep Energy Retrofit | 4 | CONSTRUCTION TO 75% | May 2022 | Aug 2022 | May 2022 | Aug 2022
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0010 | DCAS - S.I. Campus - Deep Energy Retrofit | 5 | SUBSTANTIAL COMPLETION | Aug 2022 | Oct 2022 | Aug 2022 | Oct 2022
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0010 | DCAS - S.I. Campus - Deep Energy Retrofit | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2022 | Jun 2024 | Oct 2022 | Jun 2025
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EDCSOLAR1 | Tompkinsville Dockbuilder's Building Solar | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EDCSOLAR1 | Tompkinsville Dockbuilder's Building Solar | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EDCSOLAR1 | Tompkinsville Dockbuilder's Building Solar | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EDCSOLAR1 | Tompkinsville Dockbuilder's Building Solar | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EDCSOLAR1 | Tompkinsville Dockbuilder's Building Solar | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EDCSOLAR1 | Tompkinsville Dockbuilder's Building Solar | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EDCSOLAR2 | Homeport Pier Solar | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EDCSOLAR2 | Homeport Pier Solar | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EDCSOLAR2 | Homeport Pier Solar | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EDCSOLAR2 | Homeport Pier Solar | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EDCSOLAR2 | Homeport Pier Solar | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EDCSOLAR2 | Homeport Pier Solar | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0035 | DPR-Greenbelt Recreation Center | 1 | DEVELOP SCOPE | Jun 2019 | Jun 2019 | Jun 2019 | Jun 2019
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0035 | DPR-Greenbelt Recreation Center | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jul 2019 | Aug 2019
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0035 | DPR-Greenbelt Recreation Center | 3 | CONSTRUCTION TO 50% | Aug 2019 | Feb 2020 | Aug 2019 | Feb 2020
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0035 | DPR-Greenbelt Recreation Center | 4 | CONSTRUCTION TO 75% | Feb 2020 | May 2020 | Feb 2020 | May 2020
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0035 | DPR-Greenbelt Recreation Center | 5 | SUBSTANTIAL COMPLETION | May 2020 | Jul 2020 | May 2020 | Jul 2020
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0035 | DPR-Greenbelt Recreation Center | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Aug 2020 | Jul 2020 | Aug 2025
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0076 | NYPD - 122ND PRECINCT | 1 | DEVELOP SCOPE | Feb 2020 | Mar 2020 | Jun 2022 | Jun 2022
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0076 | NYPD - 122ND PRECINCT | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | May 2020 | Jul 2022 | Aug 2022
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0076 | NYPD - 122ND PRECINCT | 3 | CONSTRUCTION TO 50% | May 2020 | Nov 2020 | Aug 2022 | Feb 2023
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0076 | NYPD - 122ND PRECINCT | 4 | CONSTRUCTION TO 75% | Nov 2020 | Feb 2021 | Feb 2023 | May 2023
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0076 | NYPD - 122ND PRECINCT | 5 | SUBSTANTIAL COMPLETION | Feb 2021 | Apr 2021 | May 2023 | Jul 2023
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0076 | NYPD - 122ND PRECINCT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2021 | May 2021 | Jul 2023 | Aug 2023
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWRFPATH | Arthur Kill Road Build-out | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWRFPATH | Arthur Kill Road Build-out | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWRFPATH | Arthur Kill Road Build-out | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWRFPATH | Arthur Kill Road Build-out | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWRFPATH | Arthur Kill Road Build-out | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWRFPATH | Arthur Kill Road Build-out | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWRFPATH | Arthur Kill Road Build-out | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWRFPATH | Arthur Kill Road Build-out | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWRFPATH | Arthur Kill Road Build-out | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWRFPATH | Arthur Kill Road Build-out | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOFR | DOF - 350 ST. MARK'S PLACE - LEASED SPACE | 1 | DEVELOP SCOPE | Jun 2014 | Aug 2014 | Jun 2023 | Aug 2023
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOFR | DOF - 350 ST. MARK'S PLACE - LEASED SPACE | 2 | PRELIMINARY DESIGN | Aug 2014 | Dec 2014 | Aug 2023 | Dec 2023
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOFR | DOF - 350 ST. MARK'S PLACE - LEASED SPACE | 3 | FINAL DESIGN | Dec 2014 | Jun 2015 | Dec 2023 | Jun 2024
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOFR | DOF - 350 ST. MARK'S PLACE - LEASED SPACE | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2015 | Sep 2015 | Jun 2024 | Sep 2024
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOFR | DOF - 350 ST. MARK'S PLACE - LEASED SPACE | 5 | CONSTRUCTION TO 25% | Sep 2015 | Jan 2016 | Sep 2024 | Jan 2025
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOFR | DOF - 350 ST. MARK'S PLACE - LEASED SPACE | 6 | CONSTRUCTION TO 50% | Jan 2016 | May 2016 | Jan 2025 | May 2025
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOFR | DOF - 350 ST. MARK'S PLACE - LEASED SPACE | 7 | CONSTRUCTION TO 75% | May 2016 | Sep 2016 | May 2025 | Sep 2025
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOFR | DOF - 350 ST. MARK'S PLACE - LEASED SPACE | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Dec 2016 | Sep 2025 | Dec 2025
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOFR | DOF - 350 ST. MARK'S PLACE - LEASED SPACE | 9 | SUBSTANTIAL COMPLETION | Dec 2016 | Feb 2017 | Dec 2025 | Feb 2026
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOFR | DOF - 350 ST. MARK'S PLACE - LEASED SPACE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2017 | Mar 2017 | Feb 2026 | Mar 2027
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAR | LAW DEPT - RAISE THE AGE -SI | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Aug 2020
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAR | LAW DEPT - RAISE THE AGE -SI | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAR | LAW DEPT - RAISE THE AGE -SI | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAR | LAW DEPT - RAISE THE AGE -SI | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAR | LAW DEPT - RAISE THE AGE -SI | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAR | LAW DEPT - RAISE THE AGE -SI | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2022 | May 2022
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAR | LAW DEPT - RAISE THE AGE -SI | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2022 | Sep 2022
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAR | LAW DEPT - RAISE THE AGE -SI | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAR | LAW DEPT - RAISE THE AGE -SI | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2022 | Feb 2023
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAR | LAW DEPT - RAISE THE AGE -SI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Feb 2023 | Mar 2027
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RHP | OCA RELOCATION FROM HOMEPORT - STATEN ISLAND | 1 | DEVELOP SCOPE | Jun 2002 | Sep 2002 | Jun 2008 | Aug 2008
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RHP | OCA RELOCATION FROM HOMEPORT - STATEN ISLAND | 2 | PRELIMINARY DESIGN | Sep 2006 | Oct 2006 | Sep 2006 | Oct 2006
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RHP | OCA RELOCATION FROM HOMEPORT - STATEN ISLAND | 3 | FINAL DESIGN | Nov 2006 | Jan 2007 | Nov 2006 | Jan 2007
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RHP | OCA RELOCATION FROM HOMEPORT - STATEN ISLAND | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2007 | Mar 2007 | Feb 2007 | Mar 2007
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RHP | OCA RELOCATION FROM HOMEPORT - STATEN ISLAND | 5 | CONSTRUCTION TO 25% | Feb 2007 | Apr 2007 | Feb 2007 | Apr 2007
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RHP | OCA RELOCATION FROM HOMEPORT - STATEN ISLAND | 6 | CONSTRUCTION TO 50% | May 2007 | Jun 2007 | May 2007 | Jun 2007
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RHP | OCA RELOCATION FROM HOMEPORT - STATEN ISLAND | 7 | CONSTRUCTION TO 75% | Jul 2007 | Jul 2007 | Jul 2007 | Jul 2007
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RHP | OCA RELOCATION FROM HOMEPORT - STATEN ISLAND | 8 | ORIGINAL EQUIP & FURNISHING | Aug 2007 | Jul 2007 | Aug 2007 | Mar 2010
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RHP | OCA RELOCATION FROM HOMEPORT - STATEN ISLAND | 9 | SUBSTANTIAL COMPLETION | Aug 2007 | Sep 2007 | Mar 2010 | Jul 2011
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RHP | OCA RELOCATION FROM HOMEPORT - STATEN ISLAND | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2007 | Dec 2007 | Jul 2011 | Jun 2025
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZR02 | CB#2 - 2 TELEPORT DR | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZR02 | CB#2 - 2 TELEPORT DR | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZR02 | CB#2 - 2 TELEPORT DR | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZR02 | CB#2 - 2 TELEPORT DR | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZR02 | CB#2 - 2 TELEPORT DR | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZR02 | CB#2 - 2 TELEPORT DR | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZR02 | CB#2 - 2 TELEPORT DR | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZR02 | CB#2 - 2 TELEPORT DR | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Jun 2028 | Aug 2028
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZR02 | CB#2 - 2 TELEPORT DR | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Aug 2028 | Oct 2028
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZR02 | CB#2 - 2 TELEPORT DR | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Oct 2028 | Nov 2028
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501DB | 10 RICHMOND TERRACE - 2nd & 3rd FLs CCHR/DOB RENOVATION | 1 | DEVELOP SCOPE | Jun 2021 | Aug 2021 | Jun 2021 | Aug 2021
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501DB | 10 RICHMOND TERRACE - 2nd & 3rd FLs CCHR/DOB RENOVATION | 2 | PRELIMINARY DESIGN | Aug 2021 | Dec 2021 | Aug 2021 | Dec 2021
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501DB | 10 RICHMOND TERRACE - 2nd & 3rd FLs CCHR/DOB RENOVATION | 3 | FINAL DESIGN | Dec 2021 | Jun 2022 | Dec 2021 | Jun 2022
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501DB | 10 RICHMOND TERRACE - 2nd & 3rd FLs CCHR/DOB RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501DB | 10 RICHMOND TERRACE - 2nd & 3rd FLs CCHR/DOB RENOVATION | 5 | CONSTRUCTION TO 25% | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501DB | 10 RICHMOND TERRACE - 2nd & 3rd FLs CCHR/DOB RENOVATION | 6 | CONSTRUCTION TO 50% | Jan 2023 | May 2023 | Jan 2023 | May 2023
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501DB | 10 RICHMOND TERRACE - 2nd & 3rd FLs CCHR/DOB RENOVATION | 7 | CONSTRUCTION TO 75% | May 2023 | Sep 2023 | May 2023 | Sep 2023
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501DB | 10 RICHMOND TERRACE - 2nd & 3rd FLs CCHR/DOB RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Dec 2023 | Sep 2023 | Dec 2023
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501DB | 10 RICHMOND TERRACE - 2nd & 3rd FLs CCHR/DOB RENOVATION | 9 | SUBSTANTIAL COMPLETION | Dec 2023 | Feb 2024 | Dec 2023 | Feb 2024
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501DB | 10 RICHMOND TERRACE - 2nd & 3rd FLs CCHR/DOB RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2024 | Mar 2024 | Feb 2024 | Mar 2026
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR077MUR | 18 RICHMOND TERRACE- STATEN ISLAND COURTHOUSE MURALS | 1 | DEVELOP SCOPE | Sep 2012 | Oct 2012 | Jun 2012 | Aug 2012
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR077MUR | 18 RICHMOND TERRACE- STATEN ISLAND COURTHOUSE MURALS | 2 | PRELIMINARY DESIGN | Oct 2012 | Nov 2012 | Aug 2012 | Dec 2012
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR077MUR | 18 RICHMOND TERRACE- STATEN ISLAND COURTHOUSE MURALS | 3 | FINAL DESIGN | Nov 2012 | Dec 2012 | Dec 2012 | Jun 2013
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR077MUR | 18 RICHMOND TERRACE- STATEN ISLAND COURTHOUSE MURALS | 4 | BID AWARD AND REGISTER CONTRCT | Dec 2012 | Jan 2013 | Jun 2013 | Sep 2013
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR077MUR | 18 RICHMOND TERRACE- STATEN ISLAND COURTHOUSE MURALS | 5 | CONSTRUCTION TO 25% | Jan 2013 | Feb 2013 | Sep 2013 | Jan 2014
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR077MUR | 18 RICHMOND TERRACE- STATEN ISLAND COURTHOUSE MURALS | 6 | CONSTRUCTION TO 50% | Feb 2013 | Apr 2013 | Jan 2014 | May 2014
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR077MUR | 18 RICHMOND TERRACE- STATEN ISLAND COURTHOUSE MURALS | 7 | CONSTRUCTION TO 75% | Apr 2013 | May 2013 | May 2014 | Sep 2014
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR077MUR | 18 RICHMOND TERRACE- STATEN ISLAND COURTHOUSE MURALS | 8 | ORIGINAL EQUIP & FURNISHING | May 2013 | May 2013 | Sep 2014 | Dec 2014
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR077MUR | 18 RICHMOND TERRACE- STATEN ISLAND COURTHOUSE MURALS | 9 | SUBSTANTIAL COMPLETION | May 2013 | May 2013 | Dec 2014 | Feb 2015
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR077MUR | 18 RICHMOND TERRACE- STATEN ISLAND COURTHOUSE MURALS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2013 | Jun 2013 | Feb 2015 | Mar 2032
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77GRGE | ST. GEORGE COURTHOUSE & HYATT STREET PLAZA | 1 | DEVELOP SCOPE | Apr 2015 | Jun 2015 | Jun 2028 | Aug 2028
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77GRGE | ST. GEORGE COURTHOUSE & HYATT STREET PLAZA | 2 | PRELIMINARY DESIGN | Jun 2015 | Oct 2015 | Aug 2028 | Dec 2028
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77GRGE | ST. GEORGE COURTHOUSE & HYATT STREET PLAZA | 3 | FINAL DESIGN | Oct 2015 | Apr 2016 | Dec 2028 | Jun 2029
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77GRGE | ST. GEORGE COURTHOUSE & HYATT STREET PLAZA | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2016 | Jul 2016 | Jun 2029 | Sep 2029
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77GRGE | ST. GEORGE COURTHOUSE & HYATT STREET PLAZA | 5 | CONSTRUCTION TO 25% | Jul 2016 | Nov 2016 | Sep 2029 | Jan 2030
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77GRGE | ST. GEORGE COURTHOUSE & HYATT STREET PLAZA | 6 | CONSTRUCTION TO 50% | Nov 2016 | Mar 2017 | Jan 2030 | May 2030
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77GRGE | ST. GEORGE COURTHOUSE & HYATT STREET PLAZA | 7 | CONSTRUCTION TO 75% | Mar 2017 | Jul 2017 | May 2030 | Sep 2030
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77GRGE | ST. GEORGE COURTHOUSE & HYATT STREET PLAZA | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2017 | Oct 2017 | Sep 2030 | Dec 2030
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77GRGE | ST. GEORGE COURTHOUSE & HYATT STREET PLAZA | 9 | SUBSTANTIAL COMPLETION | Oct 2017 | Dec 2017 | Dec 2030 | Feb 2031
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77GRGE | ST. GEORGE COURTHOUSE & HYATT STREET PLAZA | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2017 | Jan 2018 | Feb 2031 | Mar 2032
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77SICC | NYC OFFICE OF EMERGENCY MANAGEMENT BOROUGH COMMAND CENTER ON | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77SICC | NYC OFFICE OF EMERGENCY MANAGEMENT BOROUGH COMMAND CENTER ON | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77SICC | NYC OFFICE OF EMERGENCY MANAGEMENT BOROUGH COMMAND CENTER ON | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77SICC | NYC OFFICE OF EMERGENCY MANAGEMENT BOROUGH COMMAND CENTER ON | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77SICC | NYC OFFICE OF EMERGENCY MANAGEMENT BOROUGH COMMAND CENTER ON | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77SICC | NYC OFFICE OF EMERGENCY MANAGEMENT BOROUGH COMMAND CENTER ON | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77SICC | NYC OFFICE OF EMERGENCY MANAGEMENT BOROUGH COMMAND CENTER ON | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | May 2024 | Sep 2024
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77SICC | NYC OFFICE OF EMERGENCY MANAGEMENT BOROUGH COMMAND CENTER ON | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77SICC | NYC OFFICE OF EMERGENCY MANAGEMENT BOROUGH COMMAND CENTER ON | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Dec 2024 | Feb 2025
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77SICC | NYC OFFICE OF EMERGENCY MANAGEMENT BOROUGH COMMAND CENTER ON | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Mar 2025 | Feb 2025 | Aug 2032
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-R041 | SCA Electrification - R041 | 1 | DEVELOP SCOPE | Jun 2028 | Jun 2028 | Jun 2028 | Jun 2028
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-R041 | SCA Electrification - R041 | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2028 | Aug 2028 | Jul 2028 | Aug 2028
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-R041 | SCA Electrification - R041 | 3 | CONSTRUCTION TO 50% | Aug 2028 | Feb 2029 | Aug 2028 | Feb 2029
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-R041 | SCA Electrification - R041 | 4 | CONSTRUCTION TO 75% | Feb 2029 | May 2029 | Feb 2029 | May 2029
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-R041 | SCA Electrification - R041 | 5 | SUBSTANTIAL COMPLETION | May 2029 | Jul 2029 | May 2029 | Jul 2029
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-R041 | SCA Electrification - R041 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2029 | Aug 2029 | Jul 2029 | Aug 2029
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | STGESPLND | ST. GEORGE ESPLANADE | 1 | DEVELOP SCOPE | Jun 2004 | Sep 2004 | Jun 2004 | Aug 2004
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | STGESPLND | ST. GEORGE ESPLANADE | 2 | PRELIMINARY DESIGN | Sep 2004 | Jan 2005 | Aug 2004 | Dec 2004
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | STGESPLND | ST. GEORGE ESPLANADE | 3 | FINAL DESIGN | Jan 2005 | Jul 2005 | Dec 2004 | Jun 2005
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | STGESPLND | ST. GEORGE ESPLANADE | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2005 | Oct 2005 | Jun 2005 | Sep 2005
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | STGESPLND | ST. GEORGE ESPLANADE | 5 | CONSTRUCTION TO 25% | Oct 2005 | Feb 2006 | Sep 2005 | May 2008
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | STGESPLND | ST. GEORGE ESPLANADE | 6 | CONSTRUCTION TO 50% | Feb 2006 | Jun 2006 | May 2008 | Dec 2010
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | STGESPLND | ST. GEORGE ESPLANADE | 7 | CONSTRUCTION TO 75% | Jun 2006 | Oct 2006 | Jun 2027 | Jun 2029
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | STGESPLND | ST. GEORGE ESPLANADE | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2006 | Jan 2007 | Jun 2029 | Jul 2029
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | STGESPLND | ST. GEORGE ESPLANADE | 9 | SUBSTANTIAL COMPLETION | Jan 2007 | Mar 2007 | Jul 2029 | Aug 2029
20231026 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | STGESPLND | ST. GEORGE ESPLANADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2007 | Apr 2007 | Aug 2029 | Aug 2029
20231026 | RICHMOND | 858 | DEPT OF INFO TECH & TELECOMM | DATACENTR | FISA Alternative Data Center | 1 | DEVELOP SCOPE | Jul 2011 | Sep 2011 | Jul 2011 | Jun 2012
20231026 | RICHMOND | 858 | DEPT OF INFO TECH & TELECOMM | DATACENTR | FISA Alternative Data Center | 2 | PRELIMINARY DESIGN | Sep 2011 | Jan 2012 | Jun 2012 | Jan 2014
20231026 | RICHMOND | 858 | DEPT OF INFO TECH & TELECOMM | DATACENTR | FISA Alternative Data Center | 3 | FINAL DESIGN | Jan 2012 | Jul 2012 | Jan 2014 | Jan 2015
20231026 | RICHMOND | 858 | DEPT OF INFO TECH & TELECOMM | DATACENTR | FISA Alternative Data Center | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2012 | Oct 2012 | Jan 2015 | Jan 2016
20231026 | RICHMOND | 858 | DEPT OF INFO TECH & TELECOMM | DATACENTR | FISA Alternative Data Center | 5 | CONSTRUCTION TO 25% | Oct 2012 | Feb 2013 | Jan 2016 | Apr 2017
20231026 | RICHMOND | 858 | DEPT OF INFO TECH & TELECOMM | DATACENTR | FISA Alternative Data Center | 6 | CONSTRUCTION TO 50% | Feb 2013 | Jun 2013 | Apr 2017 | Jun 2018
20231026 | RICHMOND | 858 | DEPT OF INFO TECH & TELECOMM | DATACENTR | FISA Alternative Data Center | 7 | CONSTRUCTION TO 75% | Jun 2013 | Oct 2013 | Jun 2018 | Sep 2019
20231026 | RICHMOND | 858 | DEPT OF INFO TECH & TELECOMM | DATACENTR | FISA Alternative Data Center | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2013 | Jan 2014 | Sep 2019 | Mar 2021
20231026 | RICHMOND | 858 | DEPT OF INFO TECH & TELECOMM | DATACENTR | FISA Alternative Data Center | 9 | SUBSTANTIAL COMPLETION | Jan 2014 | Mar 2014 | Mar 2021 | May 2022
20231026 | RICHMOND | 858 | DEPT OF INFO TECH & TELECOMM | DATACENTR | FISA Alternative Data Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2014 | Apr 2014 | May 2022 | Jun 2023
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18ALRFW | Allerton - New Roof and Windows | 1 | DEVELOP SCOPE | Jul 2021 | Sep 2021 | Jul 2023 | Sep 2023
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18ALRFW | Allerton - New Roof and Windows | 2 | DESIGN | Sep 2021 | Sep 2022 | Sep 2023 | Sep 2024
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18ALRFW | Allerton - New Roof and Windows | 3 | BID/ REGISTER CONTRACT | Sep 2022 | Jun 2023 | Sep 2024 | Jun 2025
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18ALRFW | Allerton - New Roof and Windows | 4 | CONSTRUCTION | Jun 2023 | Jun 2024 | Jun 2025 | Jun 2026
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18ALRFW | Allerton - New Roof and Windows | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2024 | Jun 2025 | Jun 2026 | Jun 2027
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18BEADA | BELMONT- ADA-compliant Restrooms | 1 | DEVELOP SCOPE | Jul 2021 | Sep 2021 | Jul 2022 | Sep 2022
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18BEADA | BELMONT- ADA-compliant Restrooms | 2 | DESIGN | Sep 2021 | Sep 2022 | Sep 2022 | Sep 2023
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18BEADA | BELMONT- ADA-compliant Restrooms | 3 | BID/ REGISTER CONTRACT | Sep 2022 | Jun 2023 | Sep 2023 | Jun 2024
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18BEADA | BELMONT- ADA-compliant Restrooms | 4 | CONSTRUCTION | Jun 2023 | Jun 2024 | Jun 2024 | Jun 2025
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18BEADA | BELMONT- ADA-compliant Restrooms | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2024 | Jun 2025 | Jun 2025 | Jun 2026
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18CPBOI | CLASON'S POINT - New Boiler | 1 | DEVELOP SCOPE | Jul 2024 | Sep 2024 | Jul 2024 | Sep 2024
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18CPBOI | CLASON'S POINT - New Boiler | 2 | DESIGN | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18CPBOI | CLASON'S POINT - New Boiler | 3 | BID/ REGISTER CONTRACT | Sep 2025 | Jun 2026 | Sep 2025 | Jun 2026
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18CPBOI | CLASON'S POINT - New Boiler | 4 | CONSTRUCTION | Jun 2026 | Jun 2027 | Jun 2026 | Jun 2027
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18CPBOI | CLASON'S POINT - New Boiler | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2027 | Jun 2028 | Jun 2027 | Jun 2028
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18DYBHV | SPUYTEN DUYVIL - Boiler and HVAC Replacement | 1 | DEVELOP SCOPE | Jul 2022 | Sep 2022 | Jul 2026 | Sep 2026
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18DYBHV | SPUYTEN DUYVIL - Boiler and HVAC Replacement | 2 | DESIGN | Sep 2022 | Sep 2023 | Sep 2026 | Sep 2027
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18DYBHV | SPUYTEN DUYVIL - Boiler and HVAC Replacement | 3 | BID/ REGISTER CONTRACT | Sep 2023 | Jun 2024 | Sep 2027 | Jun 2028
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18DYBHV | SPUYTEN DUYVIL - Boiler and HVAC Replacement | 4 | CONSTRUCTION | Jun 2024 | Jun 2025 | Jun 2028 | Jun 2029
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18DYBHV | SPUYTEN DUYVIL - Boiler and HVAC Replacement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2025 | Jun 2026 | Jun 2029 | Jun 2030
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18RDADA | Riverdale - ADA-compliant Bathroom Renovation | 1 | DEVELOP SCOPE | Jul 2021 | Sep 2021 | Jul 2025 | Sep 2025
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18RDADA | Riverdale - ADA-compliant Bathroom Renovation | 2 | DESIGN | Sep 2021 | Sep 2022 | Sep 2025 | Sep 2026
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18RDADA | Riverdale - ADA-compliant Bathroom Renovation | 3 | BID/ REGISTER CONTRACT | Sep 2022 | Jun 2023 | Sep 2026 | Jun 2027
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18RDADA | Riverdale - ADA-compliant Bathroom Renovation | 4 | CONSTRUCTION | Jun 2023 | Jun 2024 | Jun 2027 | Jun 2028
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18RDADA | Riverdale - ADA-compliant Bathroom Renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2024 | Jun 2025 | Jun 2028 | Jun 2029
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN23EDWCR | EDENWALD - Comprehensive Renovation | 1 | DEVELOP SCOPE | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN23EDWCR | EDENWALD - Comprehensive Renovation | 2 | DESIGN | Oct 2023 | Oct 2024 | Oct 2023 | Oct 2024
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN23EDWCR | EDENWALD - Comprehensive Renovation | 3 | BID/ REGISTER CONTRACT | Oct 2024 | Jul 2025 | Oct 2024 | Jul 2025
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN23EDWCR | EDENWALD - Comprehensive Renovation | 4 | CONSTRUCTION | Jul 2025 | Jan 2027 | Jul 2025 | Jan 2027
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN23EDWCR | EDENWALD - Comprehensive Renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2027 | Jan 2028 | Jan 2027 | Jan 2028
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNBEREXRE | Belmont - Exterior Renovation | 1 | DEVELOP SCOPE | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNBEREXRE | Belmont - Exterior Renovation | 2 | DESIGN | Oct 2021 | Oct 2022 | Oct 2021 | Oct 2022
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNBEREXRE | Belmont - Exterior Renovation | 3 | BID/ REGISTER CONTRACT | Oct 2022 | Jul 2023 | Oct 2022 | Jul 2023
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNBEREXRE | Belmont - Exterior Renovation | 4 | CONSTRUCTION | Jul 2023 | Jan 2025 | Jul 2023 | Jan 2025
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNBEREXRE | Belmont - Exterior Renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2025 | Jan 2026 | Jan 2025 | Jan 2026
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNBERHVAC | Belmont - HVAC /Mechnical Systems Upgrade | 1 | DEVELOP SCOPE | Jul 2021 | Sep 2021 | Jul 2022 | Sep 2022
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNBERHVAC | Belmont - HVAC /Mechnical Systems Upgrade | 2 | DESIGN | Sep 2021 | Sep 2022 | Sep 2022 | Sep 2023
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNBERHVAC | Belmont - HVAC /Mechnical Systems Upgrade | 3 | BID/ REGISTER CONTRACT | Sep 2022 | Jun 2023 | Sep 2023 | Jun 2024
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNBERHVAC | Belmont - HVAC /Mechnical Systems Upgrade | 4 | CONSTRUCTION | Jun 2023 | Jun 2024 | Jun 2024 | Jun 2025
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNBERHVAC | Belmont - HVAC /Mechnical Systems Upgrade | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2024 | Jun 2025 | Jun 2025 | Jun 2026
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNCA16SDW | Sedgwick - New Roof | 1 | DEVELOP SCOPE | Jul 2021 | Sep 2021 | Jun 2026 | Sep 2026
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNCA16SDW | Sedgwick - New Roof | 2 | DESIGN | Sep 2021 | Sep 2022 | Sep 2026 | Sep 2027
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNCA16SDW | Sedgwick - New Roof | 3 | BID/ REGISTER CONTRACT | Sep 2022 | Jun 2023 | Sep 2027 | Jun 2028
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNCA16SDW | Sedgwick - New Roof | 4 | CONSTRUCTION | Jun 2023 | Jun 2024 | Jun 2028 | Jun 2029
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNCA16SDW | Sedgwick - New Roof | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2024 | Jun 2025 | Jun 2029 | Jun 2030
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNCA17PBY | PELHAM BAY - ADA Restrooms, New Roof | 1 | DEVELOP SCOPE | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNCA17PBY | PELHAM BAY - ADA Restrooms, New Roof | 2 | DESIGN | Oct 2021 | Oct 2022 | Oct 2021 | Oct 2022
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNCA17PBY | PELHAM BAY - ADA Restrooms, New Roof | 3 | BID/ REGISTER CONTRACT | Oct 2022 | Jul 2023 | Oct 2022 | Jul 2023
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNCA17PBY | PELHAM BAY - ADA Restrooms, New Roof | 4 | CONSTRUCTION | Jul 2023 | Jul 2025 | Jul 2023 | Jul 2025
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNCA17PBY | PELHAM BAY - ADA Restrooms, New Roof | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Jul 2026 | Jul 2025 | Jul 2026
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNMPADA01 | Morris Park - ADA-compliant Entrance | 1 | DEVELOP SCOPE | Dec 2020 | Feb 2021 | Jun 2026 | Sep 2026
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNMPADA01 | Morris Park - ADA-compliant Entrance | 2 | DESIGN | Mar 2021 | Feb 2022 | Sep 2026 | Sep 2027
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNMPADA01 | Morris Park - ADA-compliant Entrance | 3 | BID/ REGISTER CONTRACT | Mar 2022 | Nov 2022 | Sep 2027 | Jun 2028
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNMPADA01 | Morris Park - ADA-compliant Entrance | 4 | CONSTRUCTION | Nov 2022 | Nov 2023 | Jun 2028 | Jun 2029
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNMPADA01 | Morris Park - ADA-compliant Entrance | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2023 | Nov 2024 | Jun 2029 | Jun 2030
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNVNADABA | Pelham Pkwy/Van Nest - ADA-compliant Bathroom | 1 | DEVELOP SCOPE | Jan 2021 | Mar 2021 | Jun 2026 | Sep 2026
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNVNADABA | Pelham Pkwy/Van Nest - ADA-compliant Bathroom | 2 | DESIGN | Apr 2021 | Mar 2022 | Sep 2026 | Sep 2027
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNVNADABA | Pelham Pkwy/Van Nest - ADA-compliant Bathroom | 3 | BID/ REGISTER CONTRACT | Apr 2022 | Dec 2022 | Sep 2027 | Jun 2028
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNVNADABA | Pelham Pkwy/Van Nest - ADA-compliant Bathroom | 4 | CONSTRUCTION | Dec 2022 | Dec 2023 | Jun 2028 | Jun 2029
20231026 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNVNADABA | Pelham Pkwy/Van Nest - ADA-compliant Bathroom | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Dec 2024 | Jun 2029 | Jun 2030
20231026 | BRONX | 042 | CITY UNIVERSITY | ACECUN212 | CUNY - Portfolio Submetering - Bronx CC | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2023 | Jun 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | ACECUN212 | CUNY - Portfolio Submetering - Bronx CC | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | ACECUN212 | CUNY - Portfolio Submetering - Bronx CC | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | ACECUN212 | CUNY - Portfolio Submetering - Bronx CC | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | ACECUN212 | CUNY - Portfolio Submetering - Bronx CC | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | ACECUN212 | CUNY - Portfolio Submetering - Bronx CC | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | ACECUN213 | CUNY - Portfolio Submetering - Hostos CC | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2023 | Jun 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | ACECUN213 | CUNY - Portfolio Submetering - Hostos CC | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | ACECUN213 | CUNY - Portfolio Submetering - Hostos CC | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | ACECUN213 | CUNY - Portfolio Submetering - Hostos CC | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | ACECUN213 | CUNY - Portfolio Submetering - Hostos CC | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | ACECUN213 | CUNY - Portfolio Submetering - Hostos CC | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | ACECUN217 | CUNY - Hostos CC - HVAC Upgrades | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2023 | Jun 2023 | Jun 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | ACECUN217 | CUNY - Hostos CC - HVAC Upgrades | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | ACECUN217 | CUNY - Hostos CC - HVAC Upgrades | 3 | CONSTRUCTION TO 50% | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | ACECUN217 | CUNY - Hostos CC - HVAC Upgrades | 4 | CONSTRUCTION TO 75% | Feb 2024 | May 2024 | Feb 2024 | May 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | ACECUN217 | CUNY - Hostos CC - HVAC Upgrades | 5 | SUBSTANTIAL COMPLETION | May 2024 | Jul 2024 | May 2024 | Jul 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | ACECUN217 | CUNY - Hostos CC - HVAC Upgrades | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | ACECUN231 | Bronx Community College BMS Upgrade | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2023 | Jun 2023 | Jun 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | ACECUN231 | Bronx Community College BMS Upgrade | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | ACECUN231 | Bronx Community College BMS Upgrade | 3 | CONSTRUCTION TO 50% | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | ACECUN231 | Bronx Community College BMS Upgrade | 4 | CONSTRUCTION TO 75% | Feb 2024 | May 2024 | Feb 2024 | May 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | ACECUN231 | Bronx Community College BMS Upgrade | 5 | SUBSTANTIAL COMPLETION | May 2024 | Jul 2024 | May 2024 | Jul 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | ACECUN231 | Bronx Community College BMS Upgrade | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | ACECUN901 | CUNY - BMS Upgrade at 4 Hostos College Buildings | 1 | DEVELOP SCOPE | Mar 2020 | Apr 2020 | Mar 2020 | Apr 2020
20231026 | BRONX | 042 | CITY UNIVERSITY | ACECUN901 | CUNY - BMS Upgrade at 4 Hostos College Buildings | 2 | BID AWARD AND REGISTER CONTRCT | Apr 2020 | Jun 2020 | Apr 2020 | Jun 2020
20231026 | BRONX | 042 | CITY UNIVERSITY | ACECUN901 | CUNY - BMS Upgrade at 4 Hostos College Buildings | 3 | CONSTRUCTION TO 50% | Jun 2020 | Dec 2020 | Jun 2020 | Dec 2020
20231026 | BRONX | 042 | CITY UNIVERSITY | ACECUN901 | CUNY - BMS Upgrade at 4 Hostos College Buildings | 4 | CONSTRUCTION TO 75% | Dec 2020 | Mar 2021 | Dec 2020 | Mar 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | ACECUN901 | CUNY - BMS Upgrade at 4 Hostos College Buildings | 5 | SUBSTANTIAL COMPLETION | Mar 2021 | May 2021 | Mar 2021 | May 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | ACECUN901 | CUNY - BMS Upgrade at 4 Hostos College Buildings | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2021 | Jun 2021 | May 2021 | Jul 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | BX001-021 | Roscoe Brown Memorial | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | BX001-021 | Roscoe Brown Memorial | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX001-021 | Roscoe Brown Memorial | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX001-021 | Roscoe Brown Memorial | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX001-021 | Roscoe Brown Memorial | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | BX001-021 | Roscoe Brown Memorial | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | BX001-021 | Roscoe Brown Memorial | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | BX001-021 | Roscoe Brown Memorial | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | BX001-021 | Roscoe Brown Memorial | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | BX001-021 | Roscoe Brown Memorial | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2029
20231026 | BRONX | 042 | CITY UNIVERSITY | BX001-023 | GOULD MEMORIAL LIBRARY ELEVATOR INSTALLATION | 1 | DEVELOP SCOPE | Jul 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | BX001-023 | GOULD MEMORIAL LIBRARY ELEVATOR INSTALLATION | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | BX001-023 | GOULD MEMORIAL LIBRARY ELEVATOR INSTALLATION | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | BX001-023 | GOULD MEMORIAL LIBRARY ELEVATOR INSTALLATION | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | BX001-023 | GOULD MEMORIAL LIBRARY ELEVATOR INSTALLATION | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | BX001-023 | GOULD MEMORIAL LIBRARY ELEVATOR INSTALLATION | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | BX001-023 | GOULD MEMORIAL LIBRARY ELEVATOR INSTALLATION | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | BX001-023 | GOULD MEMORIAL LIBRARY ELEVATOR INSTALLATION | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | BX001-023 | GOULD MEMORIAL LIBRARY ELEVATOR INSTALLATION | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | BX001-023 | GOULD MEMORIAL LIBRARY ELEVATOR INSTALLATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | BX001-024 | LIBRARY ELEVATOR INSTALLATION | 1 | DEVELOP SCOPE | Jul 2023 | Sep 2024 | Jul 2023 | Sep 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | BX001-024 | LIBRARY ELEVATOR INSTALLATION | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | BX001-024 | LIBRARY ELEVATOR INSTALLATION | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | BX001-024 | LIBRARY ELEVATOR INSTALLATION | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | BX001-024 | LIBRARY ELEVATOR INSTALLATION | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | BX001-024 | LIBRARY ELEVATOR INSTALLATION | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | BX001-024 | LIBRARY ELEVATOR INSTALLATION | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | BX001-024 | LIBRARY ELEVATOR INSTALLATION | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | BRONX | 042 | CITY UNIVERSITY | BX001-024 | LIBRARY ELEVATOR INSTALLATION | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | BRONX | 042 | CITY UNIVERSITY | BX001-024 | LIBRARY ELEVATOR INSTALLATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | BRONX | 042 | CITY UNIVERSITY | BX002-023 | Elevator Installation | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | BX002-023 | Elevator Installation | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | BX002-023 | Elevator Installation | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | BX002-023 | Elevator Installation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | BX002-023 | Elevator Installation | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | BX002-023 | Elevator Installation | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | BX002-023 | Elevator Installation | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | BX002-023 | Elevator Installation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | BX002-023 | Elevator Installation | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | BX002-023 | Elevator Installation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2030
20231026 | BRONX | 042 | CITY UNIVERSITY | BX006-022 | Food Pantry Construction | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX006-022 | Food Pantry Construction | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | BX006-022 | Food Pantry Construction | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | BX006-022 | Food Pantry Construction | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | BX006-022 | Food Pantry Construction | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | BX006-022 | Food Pantry Construction | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | BX006-022 | Food Pantry Construction | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | BX006-022 | Food Pantry Construction | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | BX006-022 | Food Pantry Construction | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | BX006-022 | Food Pantry Construction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2027
20231026 | BRONX | 042 | CITY UNIVERSITY | BX022-009 | Gould Memorial Lib Rotunda Staircase Installation | 1 | DEVELOP SCOPE | Jun 2009 | Aug 2009 | Jun 2009 | Aug 2009
20231026 | BRONX | 042 | CITY UNIVERSITY | BX022-009 | Gould Memorial Lib Rotunda Staircase Installation | 2 | PRELIMINARY DESIGN | Aug 2009 | Dec 2009 | Aug 2009 | Dec 2009
20231026 | BRONX | 042 | CITY UNIVERSITY | BX022-009 | Gould Memorial Lib Rotunda Staircase Installation | 3 | FINAL DESIGN | Dec 2009 | Jun 2010 | Dec 2009 | Jun 2010
20231026 | BRONX | 042 | CITY UNIVERSITY | BX022-009 | Gould Memorial Lib Rotunda Staircase Installation | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2010 | Sep 2010 | Jun 2010 | Sep 2010
20231026 | BRONX | 042 | CITY UNIVERSITY | BX022-009 | Gould Memorial Lib Rotunda Staircase Installation | 5 | CONSTRUCTION TO 25% | Sep 2010 | Jan 2011 | Sep 2010 | Jan 2011
20231026 | BRONX | 042 | CITY UNIVERSITY | BX022-009 | Gould Memorial Lib Rotunda Staircase Installation | 6 | CONSTRUCTION TO 50% | Jan 2011 | May 2011 | Jan 2011 | May 2011
20231026 | BRONX | 042 | CITY UNIVERSITY | BX022-009 | Gould Memorial Lib Rotunda Staircase Installation | 7 | CONSTRUCTION TO 75% | May 2011 | Sep 2011 | May 2011 | Sep 2011
20231026 | BRONX | 042 | CITY UNIVERSITY | BX022-009 | Gould Memorial Lib Rotunda Staircase Installation | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2011 | Dec 2011 | Sep 2011 | Dec 2011
20231026 | BRONX | 042 | CITY UNIVERSITY | BX022-009 | Gould Memorial Lib Rotunda Staircase Installation | 9 | SUBSTANTIAL COMPLETION | Dec 2011 | Feb 2012 | Dec 2011 | Feb 2012
20231026 | BRONX | 042 | CITY UNIVERSITY | BX022-009 | Gould Memorial Lib Rotunda Staircase Installation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2012 | Mar 2012 | Feb 2012 | Feb 2028
20231026 | BRONX | 042 | CITY UNIVERSITY | BX024-011 | Roof Replacement | 9 | SUBSTANTIAL COMPLETION | Dec 2013 | Feb 2014 | Dec 2013 | Feb 2014
20231026 | BRONX | 042 | CITY UNIVERSITY | BX024-011 | Roof Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2014 | Mar 2014 | Feb 2014 | Apr 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | BX026-013 | ADA Entrance Ramps | 1 | DEVELOP SCOPE | Jun 2013 | Aug 2013 | Jun 2013 | Aug 2013
20231026 | BRONX | 042 | CITY UNIVERSITY | BX026-013 | ADA Entrance Ramps | 2 | PRELIMINARY DESIGN | Aug 2013 | Dec 2013 | Aug 2013 | Dec 2013
20231026 | BRONX | 042 | CITY UNIVERSITY | BX026-013 | ADA Entrance Ramps | 3 | FINAL DESIGN | Dec 2013 | Jun 2014 | Dec 2013 | Jun 2014
20231026 | BRONX | 042 | CITY UNIVERSITY | BX026-013 | ADA Entrance Ramps | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2014 | Sep 2014 | Jun 2014 | Sep 2014
20231026 | BRONX | 042 | CITY UNIVERSITY | BX026-013 | ADA Entrance Ramps | 5 | CONSTRUCTION TO 25% | Sep 2014 | Jan 2015 | Sep 2014 | Jan 2015
20231026 | BRONX | 042 | CITY UNIVERSITY | BX026-013 | ADA Entrance Ramps | 6 | CONSTRUCTION TO 50% | Jan 2015 | May 2015 | Jan 2015 | May 2015
20231026 | BRONX | 042 | CITY UNIVERSITY | BX026-013 | ADA Entrance Ramps | 7 | CONSTRUCTION TO 75% | May 2015 | Sep 2015 | May 2015 | Sep 2015
20231026 | BRONX | 042 | CITY UNIVERSITY | BX026-013 | ADA Entrance Ramps | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | BRONX | 042 | CITY UNIVERSITY | BX026-013 | ADA Entrance Ramps | 9 | SUBSTANTIAL COMPLETION | Dec 2015 | Feb 2016 | Dec 2015 | Feb 2016
20231026 | BRONX | 042 | CITY UNIVERSITY | BX026-013 | ADA Entrance Ramps | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2016 | Mar 2016 | Feb 2016 | Mar 2027
20231026 | BRONX | 042 | CITY UNIVERSITY | BX027-015 | Ohio Track & Field Restoration | 1 | DEVELOP SCOPE | Mar 2015 | May 2015 | Mar 2015 | May 2015
20231026 | BRONX | 042 | CITY UNIVERSITY | BX027-015 | Ohio Track & Field Restoration | 2 | PRELIMINARY DESIGN | May 2015 | Sep 2015 | May 2015 | Sep 2015
20231026 | BRONX | 042 | CITY UNIVERSITY | BX027-015 | Ohio Track & Field Restoration | 3 | FINAL DESIGN | Sep 2015 | Mar 2016 | Sep 2015 | Mar 2016
20231026 | BRONX | 042 | CITY UNIVERSITY | BX027-015 | Ohio Track & Field Restoration | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2016 | Jun 2016 | Mar 2016 | Jun 2016
20231026 | BRONX | 042 | CITY UNIVERSITY | BX027-015 | Ohio Track & Field Restoration | 5 | CONSTRUCTION TO 25% | Jun 2016 | Oct 2016 | Jun 2016 | Oct 2016
20231026 | BRONX | 042 | CITY UNIVERSITY | BX027-015 | Ohio Track & Field Restoration | 6 | CONSTRUCTION TO 50% | Oct 2016 | Feb 2017 | Oct 2016 | Feb 2017
20231026 | BRONX | 042 | CITY UNIVERSITY | BX027-015 | Ohio Track & Field Restoration | 7 | CONSTRUCTION TO 75% | Feb 2017 | Jun 2017 | Feb 2017 | Jun 2017
20231026 | BRONX | 042 | CITY UNIVERSITY | BX027-015 | Ohio Track & Field Restoration | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2017 | Sep 2017 | Jun 2017 | Sep 2017
20231026 | BRONX | 042 | CITY UNIVERSITY | BX027-015 | Ohio Track & Field Restoration | 9 | SUBSTANTIAL COMPLETION | Sep 2017 | Nov 2017 | Sep 2017 | Nov 2017
20231026 | BRONX | 042 | CITY UNIVERSITY | BX027-015 | Ohio Track & Field Restoration | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | Dec 2017 | Nov 2017 | Dec 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | BX038-016 | Lowe Hall ADA Accessibility Improvements | 1 | DEVELOP SCOPE | Jun 2015 | Aug 2015 | Jul 2019 | Oct 2019
20231026 | BRONX | 042 | CITY UNIVERSITY | BX038-016 | Lowe Hall ADA Accessibility Improvements | 2 | PRELIMINARY DESIGN | Aug 2015 | Dec 2015 | Oct 2019 | Jan 2020
20231026 | BRONX | 042 | CITY UNIVERSITY | BX038-016 | Lowe Hall ADA Accessibility Improvements | 3 | FINAL DESIGN | Dec 2015 | Jun 2016 | Jan 2020 | Jul 2020
20231026 | BRONX | 042 | CITY UNIVERSITY | BX038-016 | Lowe Hall ADA Accessibility Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2016 | Sep 2016 | Jul 2020 | Oct 2020
20231026 | BRONX | 042 | CITY UNIVERSITY | BX038-016 | Lowe Hall ADA Accessibility Improvements | 5 | CONSTRUCTION TO 25% | Sep 2016 | Jan 2017 | Oct 2020 | Feb 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | BX038-016 | Lowe Hall ADA Accessibility Improvements | 6 | CONSTRUCTION TO 50% | Jan 2017 | May 2017 | Feb 2021 | Jun 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | BX038-016 | Lowe Hall ADA Accessibility Improvements | 7 | CONSTRUCTION TO 75% | May 2017 | Sep 2017 | Jun 2021 | Oct 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | BX038-016 | Lowe Hall ADA Accessibility Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Dec 2017 | Oct 2021 | Jan 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX038-016 | Lowe Hall ADA Accessibility Improvements | 9 | SUBSTANTIAL COMPLETION | Dec 2017 | Feb 2018 | Jan 2022 | Mar 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX038-016 | Lowe Hall ADA Accessibility Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2018 | Mar 2018 | Mar 2022 | May 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | BX040-017 | Bronx Express | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jul 2019 | Oct 2019
20231026 | BRONX | 042 | CITY UNIVERSITY | BX040-017 | Bronx Express | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Oct 2019 | Jan 2020
20231026 | BRONX | 042 | CITY UNIVERSITY | BX040-017 | Bronx Express | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jan 2020 | Jul 2020
20231026 | BRONX | 042 | CITY UNIVERSITY | BX040-017 | Bronx Express | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2020 | Oct 2020
20231026 | BRONX | 042 | CITY UNIVERSITY | BX040-017 | Bronx Express | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Oct 2020 | Feb 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | BX040-017 | Bronx Express | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Feb 2021 | Jun 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | BX040-017 | Bronx Express | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jun 2021 | Oct 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | BX040-017 | Bronx Express | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Oct 2021 | Jan 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX040-017 | Bronx Express | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jan 2022 | Mar 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX040-017 | Bronx Express | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Mar 2022 | Apr 2028
20231026 | BRONX | 042 | CITY UNIVERSITY | BX041-017 | STEM Resource Center | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | BRONX | 042 | CITY UNIVERSITY | BX041-017 | STEM Resource Center | 5 | CONSTRUCTION TO 25% | Sep 2018 | Jan 2019 | Sep 2018 | Jan 2019
20231026 | BRONX | 042 | CITY UNIVERSITY | BX041-017 | STEM Resource Center | 6 | CONSTRUCTION TO 50% | Jan 2019 | May 2019 | Jan 2019 | May 2019
20231026 | BRONX | 042 | CITY UNIVERSITY | BX041-017 | STEM Resource Center | 7 | CONSTRUCTION TO 75% | May 2019 | Sep 2019 | May 2019 | Sep 2019
20231026 | BRONX | 042 | CITY UNIVERSITY | BX041-017 | STEM Resource Center | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Dec 2019 | Sep 2019 | Dec 2019
20231026 | BRONX | 042 | CITY UNIVERSITY | BX041-017 | STEM Resource Center | 9 | SUBSTANTIAL COMPLETION | Dec 2019 | Feb 2020 | Dec 2019 | Feb 2020
20231026 | BRONX | 042 | CITY UNIVERSITY | BX041-017 | STEM Resource Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2020 | Mar 2020 | Feb 2020 | Mar 2031
20231026 | BRONX | 042 | CITY UNIVERSITY | BX042-018 | Renovate Roscoe Brown Student Center | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jul 2021 | Oct 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | BX042-018 | Renovate Roscoe Brown Student Center | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Oct 2021 | Jan 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX042-018 | Renovate Roscoe Brown Student Center | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Jan 2022 | Jul 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX042-018 | Renovate Roscoe Brown Student Center | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jul 2022 | Oct 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX042-018 | Renovate Roscoe Brown Student Center | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Oct 2022 | Feb 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | BX042-018 | Renovate Roscoe Brown Student Center | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Feb 2023 | Jun 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | BX042-018 | Renovate Roscoe Brown Student Center | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | Jun 2023 | Oct 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | BX042-018 | Renovate Roscoe Brown Student Center | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Oct 2023 | Jan 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | BX042-018 | Renovate Roscoe Brown Student Center | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Jan 2024 | Mar 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | BX042-018 | Renovate Roscoe Brown Student Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Mar 2024 | May 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | BX044-018 | Community Hall First Floor Renovation | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jul 2021 | Oct 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | BX044-018 | Community Hall First Floor Renovation | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Oct 2021 | Jan 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX044-018 | Community Hall First Floor Renovation | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Jan 2022 | Jul 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX044-018 | Community Hall First Floor Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jul 2022 | Oct 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX044-018 | Community Hall First Floor Renovation | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Oct 2022 | Feb 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | BX044-018 | Community Hall First Floor Renovation | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Feb 2023 | Jun 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | BX044-018 | Community Hall First Floor Renovation | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | Jun 2023 | Oct 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | BX044-018 | Community Hall First Floor Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Oct 2023 | Jan 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | BX044-018 | Community Hall First Floor Renovation | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Jan 2024 | Mar 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | BX044-018 | Community Hall First Floor Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Mar 2024 | May 2030
20231026 | BRONX | 042 | CITY UNIVERSITY | BX045-018 | ADA Accessibility for Roscoe C Brown Student Center | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jul 2021 | Oct 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | BX045-018 | ADA Accessibility for Roscoe C Brown Student Center | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Oct 2021 | Jan 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX045-018 | ADA Accessibility for Roscoe C Brown Student Center | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Jan 2022 | Jul 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX045-018 | ADA Accessibility for Roscoe C Brown Student Center | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jul 2022 | Oct 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX045-018 | ADA Accessibility for Roscoe C Brown Student Center | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Oct 2022 | Feb 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | BX045-018 | ADA Accessibility for Roscoe C Brown Student Center | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Feb 2023 | Jun 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | BX045-018 | ADA Accessibility for Roscoe C Brown Student Center | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | Jun 2023 | Oct 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | BX045-018 | ADA Accessibility for Roscoe C Brown Student Center | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Oct 2023 | Jan 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | BX045-018 | ADA Accessibility for Roscoe C Brown Student Center | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Jan 2024 | Mar 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | BX045-018 | ADA Accessibility for Roscoe C Brown Student Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Mar 2024 | May 2030
20231026 | BRONX | 042 | CITY UNIVERSITY | BX046-019 | Alumni Gym HVAC & ADA Improvements | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jul 2020 | Oct 2020
20231026 | BRONX | 042 | CITY UNIVERSITY | BX046-019 | Alumni Gym HVAC & ADA Improvements | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Oct 2020 | Jan 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | BX046-019 | Alumni Gym HVAC & ADA Improvements | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2021 | Jul 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | BX046-019 | Alumni Gym HVAC & ADA Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2021 | Oct 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | BX046-019 | Alumni Gym HVAC & ADA Improvements | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2021 | Feb 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX046-019 | Alumni Gym HVAC & ADA Improvements | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2022 | Jun 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX046-019 | Alumni Gym HVAC & ADA Improvements | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2022 | Oct 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX046-019 | Alumni Gym HVAC & ADA Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2022 | Jan 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | BX046-019 | Alumni Gym HVAC & ADA Improvements | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2023 | Mar 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | BX046-019 | Alumni Gym HVAC & ADA Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2023 | Apr 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | BX047-020 | Ohio Track & Field Upgrade | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | BRONX | 042 | CITY UNIVERSITY | BX047-020 | Ohio Track & Field Upgrade | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | BX047-020 | Ohio Track & Field Upgrade | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | BX047-020 | Ohio Track & Field Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | BX047-020 | Ohio Track & Field Upgrade | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX047-020 | Ohio Track & Field Upgrade | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX047-020 | Ohio Track & Field Upgrade | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX047-020 | Ohio Track & Field Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | BX047-020 | Ohio Track & Field Upgrade | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2023 | Mar 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | BX047-020 | Ohio Track & Field Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2023 | Mar 2027
20231026 | BRONX | 042 | CITY UNIVERSITY | BX048-020 | ELEVATOR UPGRADES | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | BRONX | 042 | CITY UNIVERSITY | BX048-020 | ELEVATOR UPGRADES | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | BX048-020 | ELEVATOR UPGRADES | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | BX048-020 | ELEVATOR UPGRADES | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | BX048-020 | ELEVATOR UPGRADES | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX048-020 | ELEVATOR UPGRADES | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX048-020 | ELEVATOR UPGRADES | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX048-020 | ELEVATOR UPGRADES | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | BX048-020 | ELEVATOR UPGRADES | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2023 | Mar 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | BX048-020 | ELEVATOR UPGRADES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2023 | Apr 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | BX049-020 | Carl Polowczyk Hall Upgrades | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | BRONX | 042 | CITY UNIVERSITY | BX049-020 | Carl Polowczyk Hall Upgrades | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | BX049-020 | Carl Polowczyk Hall Upgrades | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | BX049-020 | Carl Polowczyk Hall Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2021 | Oct 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | BX049-020 | Carl Polowczyk Hall Upgrades | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX049-020 | Carl Polowczyk Hall Upgrades | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2022 | Jun 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX049-020 | Carl Polowczyk Hall Upgrades | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX049-020 | Carl Polowczyk Hall Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | BX049-020 | Carl Polowczyk Hall Upgrades | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2023 | Mar 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | BX049-020 | Carl Polowczyk Hall Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2023 | Apr 2030
20231026 | BRONX | 042 | CITY UNIVERSITY | BX050-021 | Elevator Installation Gould Memorial Library | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | BX050-021 | Elevator Installation Gould Memorial Library | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX050-021 | Elevator Installation Gould Memorial Library | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX050-021 | Elevator Installation Gould Memorial Library | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | BX050-021 | Elevator Installation Gould Memorial Library | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | BX050-021 | Elevator Installation Gould Memorial Library | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | BX050-021 | Elevator Installation Gould Memorial Library | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | BX050-021 | Elevator Installation Gould Memorial Library | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | BX050-021 | Elevator Installation Gould Memorial Library | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | BX050-021 | Elevator Installation Gould Memorial Library | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | CA002CA01 | CUNY Prep HVAC Upgrade Project | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2023 | Jun 2022 | Sep 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | CA002CA01 | CUNY Prep HVAC Upgrade Project | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | CA002CA01 | CUNY Prep HVAC Upgrade Project | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | CA002CA01 | CUNY Prep HVAC Upgrade Project | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | CA002CA01 | CUNY Prep HVAC Upgrade Project | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | CA002CA01 | CUNY Prep HVAC Upgrade Project | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | CA002CA01 | CUNY Prep HVAC Upgrade Project | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | CA002CA01 | CUNY Prep HVAC Upgrade Project | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | CA002CA01 | CUNY Prep HVAC Upgrade Project | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | CA002CA01 | CUNY Prep HVAC Upgrade Project | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | CA022BX01 | Bronx CC HVAC Improvements | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | CA022BX01 | Bronx CC HVAC Improvements | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | CA022BX01 | Bronx CC HVAC Improvements | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | CA022BX01 | Bronx CC HVAC Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | CA022BX01 | Bronx CC HVAC Improvements | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | CA022BX01 | Bronx CC HVAC Improvements | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | CA022BX01 | Bronx CC HVAC Improvements | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | CA022BX01 | Bronx CC HVAC Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | CA022BX01 | Bronx CC HVAC Improvements | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | CA022BX01 | Bronx CC HVAC Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2027 | Feb 2026 | Mar 2027
20231026 | BRONX | 042 | CITY UNIVERSITY | CA034HS13 | 500 Grand Concourse 3rd Floor Renovation | 1 | DEVELOP SCOPE | Jun 2017 | Aug 2017 | Jun 2017 | Aug 2017
20231026 | BRONX | 042 | CITY UNIVERSITY | CA034HS13 | 500 Grand Concourse 3rd Floor Renovation | 2 | PRELIMINARY DESIGN | Aug 2017 | Dec 2017 | Aug 2017 | Dec 2017
20231026 | BRONX | 042 | CITY UNIVERSITY | CA034HS13 | 500 Grand Concourse 3rd Floor Renovation | 3 | FINAL DESIGN | Dec 2017 | Jun 2018 | Dec 2017 | Jun 2018
20231026 | BRONX | 042 | CITY UNIVERSITY | CA034HS13 | 500 Grand Concourse 3rd Floor Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | BRONX | 042 | CITY UNIVERSITY | CA034HS13 | 500 Grand Concourse 3rd Floor Renovation | 5 | CONSTRUCTION TO 25% | Sep 2018 | Jan 2019 | Sep 2018 | Jan 2019
20231026 | BRONX | 042 | CITY UNIVERSITY | CA034HS13 | 500 Grand Concourse 3rd Floor Renovation | 6 | CONSTRUCTION TO 50% | Jan 2019 | May 2019 | Jan 2019 | May 2019
20231026 | BRONX | 042 | CITY UNIVERSITY | CA034HS13 | 500 Grand Concourse 3rd Floor Renovation | 7 | CONSTRUCTION TO 75% | May 2019 | Sep 2019 | May 2019 | Sep 2019
20231026 | BRONX | 042 | CITY UNIVERSITY | CA034HS13 | 500 Grand Concourse 3rd Floor Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Dec 2019 | Sep 2019 | Dec 2019
20231026 | BRONX | 042 | CITY UNIVERSITY | CA034HS13 | 500 Grand Concourse 3rd Floor Renovation | 9 | SUBSTANTIAL COMPLETION | Dec 2019 | Feb 2020 | Dec 2019 | Feb 2020
20231026 | BRONX | 042 | CITY UNIVERSITY | CA034HS13 | 500 Grand Concourse 3rd Floor Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2020 | Mar 2020 | Feb 2020 | Mar 2028
20231026 | BRONX | 042 | CITY UNIVERSITY | CA036-014 | Hostos CC: Allied Health and Sciences Building | 1 | DEVELOP SCOPE | Jun 2014 | Aug 2014 | Jul 2021 | Sep 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | CA036-014 | Hostos CC: Allied Health and Sciences Building | 2 | PRELIMINARY DESIGN | Aug 2014 | Dec 2014 | Sep 2021 | Jan 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | CA036-014 | Hostos CC: Allied Health and Sciences Building | 3 | FINAL DESIGN | Dec 2014 | Jun 2015 | Jan 2022 | Jul 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | CA036-014 | Hostos CC: Allied Health and Sciences Building | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2015 | Sep 2015 | Jul 2022 | Oct 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | CA036-014 | Hostos CC: Allied Health and Sciences Building | 5 | CONSTRUCTION TO 25% | Sep 2015 | Jan 2016 | Oct 2022 | Feb 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | CA036-014 | Hostos CC: Allied Health and Sciences Building | 6 | CONSTRUCTION TO 50% | Jan 2016 | May 2016 | Feb 2023 | Jun 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | CA036-014 | Hostos CC: Allied Health and Sciences Building | 7 | CONSTRUCTION TO 75% | May 2016 | Sep 2016 | Jun 2023 | Oct 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | CA036-014 | Hostos CC: Allied Health and Sciences Building | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Dec 2016 | Oct 2023 | Jan 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | CA036-014 | Hostos CC: Allied Health and Sciences Building | 9 | SUBSTANTIAL COMPLETION | Dec 2016 | Feb 2017 | Jan 2024 | Mar 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | CA036-014 | Hostos CC: Allied Health and Sciences Building | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2017 | Mar 2017 | Mar 2024 | Apr 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | CA091BX23 | Hall of Fame Roof Replacement | 1 | DEVELOP SCOPE | Jul 2023 | Sep 2023 | Jul 2023 | Sep 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | CA091BX23 | Hall of Fame Roof Replacement | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | CA091BX23 | Hall of Fame Roof Replacement | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | CA091BX23 | Hall of Fame Roof Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | CA091BX23 | Hall of Fame Roof Replacement | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | CA091BX23 | Hall of Fame Roof Replacement | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | CA091BX23 | Hall of Fame Roof Replacement | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | CA091BX23 | Hall of Fame Roof Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | CA091BX23 | Hall of Fame Roof Replacement | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | CA091BX23 | Hall of Fame Roof Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | CA091HS96 | Hostos Retaining Wall Project | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | BRONX | 042 | CITY UNIVERSITY | CA091HS96 | Hostos Retaining Wall Project | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Sep 2018 | Jan 2019
20231026 | BRONX | 042 | CITY UNIVERSITY | CA091HS96 | Hostos Retaining Wall Project | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2019 | Jul 2019
20231026 | BRONX | 042 | CITY UNIVERSITY | CA091HS96 | Hostos Retaining Wall Project | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2019 | Oct 2019
20231026 | BRONX | 042 | CITY UNIVERSITY | CA091HS96 | Hostos Retaining Wall Project | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2019 | Feb 2020
20231026 | BRONX | 042 | CITY UNIVERSITY | CA091HS96 | Hostos Retaining Wall Project | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2020 | Jun 2020
20231026 | BRONX | 042 | CITY UNIVERSITY | CA091HS96 | Hostos Retaining Wall Project | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2020 | Oct 2020
20231026 | BRONX | 042 | CITY UNIVERSITY | CA091HS96 | Hostos Retaining Wall Project | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2020 | Jan 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | CA091HS96 | Hostos Retaining Wall Project | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2021 | Mar 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | CA091HS96 | Hostos Retaining Wall Project | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2021 | Apr 2028
20231026 | BRONX | 042 | CITY UNIVERSITY | CA200BX21 | BCC Boiler Plant Upgrade | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | CA200BX21 | BCC Boiler Plant Upgrade | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | CA200BX21 | BCC Boiler Plant Upgrade | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | CA200BX21 | BCC Boiler Plant Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | CA200BX21 | BCC Boiler Plant Upgrade | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | CA200BX21 | BCC Boiler Plant Upgrade | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | CA200BX21 | BCC Boiler Plant Upgrade | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | CA200BX21 | BCC Boiler Plant Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | CA200BX21 | BCC Boiler Plant Upgrade | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | CA200BX21 | BCC Boiler Plant Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | CA201BX21 | Bronx CC - Philosophy Hall Roof Replacement | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | CA201BX21 | Bronx CC - Philosophy Hall Roof Replacement | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | CA201BX21 | Bronx CC - Philosophy Hall Roof Replacement | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | CA201BX21 | Bronx CC - Philosophy Hall Roof Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | CA201BX21 | Bronx CC - Philosophy Hall Roof Replacement | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | CA201BX21 | Bronx CC - Philosophy Hall Roof Replacement | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | CA201BX21 | Bronx CC - Philosophy Hall Roof Replacement | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | CA201BX21 | Bronx CC - Philosophy Hall Roof Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | CA201BX21 | Bronx CC - Philosophy Hall Roof Replacement | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | CA201BX21 | Bronx CC - Philosophy Hall Roof Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2029
20231026 | BRONX | 042 | CITY UNIVERSITY | CA202HS04 | ADA Improvements | 1 | DEVELOP SCOPE | May 2007 | Aug 2007 | May 2007 | Aug 2007
20231026 | BRONX | 042 | CITY UNIVERSITY | CA202HS04 | ADA Improvements | 2 | PRELIMINARY DESIGN | Aug 2007 | Dec 2007 | Aug 2007 | Dec 2007
20231026 | BRONX | 042 | CITY UNIVERSITY | CA202HS04 | ADA Improvements | 3 | FINAL DESIGN | Dec 2007 | Jun 2008 | Dec 2007 | Jun 2008
20231026 | BRONX | 042 | CITY UNIVERSITY | CA202HS04 | ADA Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2008 | Sep 2008 | Jun 2008 | Sep 2008
20231026 | BRONX | 042 | CITY UNIVERSITY | CA202HS04 | ADA Improvements | 5 | CONSTRUCTION TO 25% | Sep 2008 | Jan 2009 | Sep 2008 | Jan 2009
20231026 | BRONX | 042 | CITY UNIVERSITY | CA202HS04 | ADA Improvements | 6 | CONSTRUCTION TO 50% | Jan 2009 | May 2009 | Jan 2009 | May 2009
20231026 | BRONX | 042 | CITY UNIVERSITY | CA202HS04 | ADA Improvements | 7 | CONSTRUCTION TO 75% | May 2009 | Sep 2009 | May 2009 | Sep 2009
20231026 | BRONX | 042 | CITY UNIVERSITY | CA202HS04 | ADA Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2009 | Dec 2009 | Sep 2009 | Dec 2009
20231026 | BRONX | 042 | CITY UNIVERSITY | CA202HS04 | ADA Improvements | 9 | SUBSTANTIAL COMPLETION | Dec 2009 | Feb 2010 | Dec 2009 | Feb 2010
20231026 | BRONX | 042 | CITY UNIVERSITY | CA202HS04 | ADA Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2010 | Mar 2010 | Feb 2010 | Jun 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | HS001-024 | CAFETERIA RENOVATION | 1 | DEVELOP SCOPE | Jul 2023 | Sep 2024 | Jul 2023 | Sep 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | HS001-024 | CAFETERIA RENOVATION | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | HS001-024 | CAFETERIA RENOVATION | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | HS001-024 | CAFETERIA RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | HS001-024 | CAFETERIA RENOVATION | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | HS001-024 | CAFETERIA RENOVATION | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | HS001-024 | CAFETERIA RENOVATION | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | HS001-024 | CAFETERIA RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | BRONX | 042 | CITY UNIVERSITY | HS001-024 | CAFETERIA RENOVATION | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | BRONX | 042 | CITY UNIVERSITY | HS001-024 | CAFETERIA RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | BRONX | 042 | CITY UNIVERSITY | HS007-010 | PEDESTRIAN BRIDGE ROOF REPLACEMENT | 1 | DEVELOP SCOPE | Jun 2010 | Aug 2010 | Jun 2010 | Aug 2010
20231026 | BRONX | 042 | CITY UNIVERSITY | HS007-010 | PEDESTRIAN BRIDGE ROOF REPLACEMENT | 2 | PRELIMINARY DESIGN | Aug 2010 | Dec 2010 | Aug 2010 | Dec 2010
20231026 | BRONX | 042 | CITY UNIVERSITY | HS007-010 | PEDESTRIAN BRIDGE ROOF REPLACEMENT | 3 | FINAL DESIGN | Dec 2010 | Jun 2011 | Dec 2010 | Jun 2011
20231026 | BRONX | 042 | CITY UNIVERSITY | HS007-010 | PEDESTRIAN BRIDGE ROOF REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2011 | Sep 2011 | Jun 2011 | Sep 2011
20231026 | BRONX | 042 | CITY UNIVERSITY | HS007-010 | PEDESTRIAN BRIDGE ROOF REPLACEMENT | 5 | CONSTRUCTION TO 25% | Sep 2011 | Jan 2012 | Sep 2011 | Jan 2012
20231026 | BRONX | 042 | CITY UNIVERSITY | HS007-010 | PEDESTRIAN BRIDGE ROOF REPLACEMENT | 6 | CONSTRUCTION TO 50% | Jan 2012 | May 2012 | Jan 2012 | May 2012
20231026 | BRONX | 042 | CITY UNIVERSITY | HS007-010 | PEDESTRIAN BRIDGE ROOF REPLACEMENT | 7 | CONSTRUCTION TO 75% | May 2012 | Sep 2012 | May 2012 | Sep 2012
20231026 | BRONX | 042 | CITY UNIVERSITY | HS007-010 | PEDESTRIAN BRIDGE ROOF REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2012 | Dec 2012 | Sep 2012 | Dec 2012
20231026 | BRONX | 042 | CITY UNIVERSITY | HS007-010 | PEDESTRIAN BRIDGE ROOF REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | Dec 2012 | Feb 2013 | Dec 2012 | Feb 2013
20231026 | BRONX | 042 | CITY UNIVERSITY | HS007-010 | PEDESTRIAN BRIDGE ROOF REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2013 | Mar 2013 | Feb 2013 | Dec 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | HS007-022 | Second Floor & Basement Renovations | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | HS007-022 | Second Floor & Basement Renovations | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | HS007-022 | Second Floor & Basement Renovations | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | HS007-022 | Second Floor & Basement Renovations | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | HS007-022 | Second Floor & Basement Renovations | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | HS007-022 | Second Floor & Basement Renovations | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | HS007-022 | Second Floor & Basement Renovations | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | HS007-022 | Second Floor & Basement Renovations | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | HS007-022 | Second Floor & Basement Renovations | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | HS007-022 | Second Floor & Basement Renovations | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | HS033-007 | Brick Wall Restoration/Garden Upgrades | 1 | DEVELOP SCOPE | May 2007 | Aug 2007 | Jul 2021 | Oct 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | HS033-007 | Brick Wall Restoration/Garden Upgrades | 2 | PRELIMINARY DESIGN | Aug 2007 | Dec 2007 | Oct 2021 | Jan 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | HS033-007 | Brick Wall Restoration/Garden Upgrades | 3 | FINAL DESIGN | Dec 2007 | Jun 2008 | Jan 2022 | Jul 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | HS033-007 | Brick Wall Restoration/Garden Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2008 | Sep 2008 | Jul 2022 | Oct 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | HS033-007 | Brick Wall Restoration/Garden Upgrades | 5 | CONSTRUCTION TO 25% | Sep 2008 | Jan 2009 | Oct 2022 | Feb 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | HS033-007 | Brick Wall Restoration/Garden Upgrades | 6 | CONSTRUCTION TO 50% | Jan 2009 | May 2009 | Feb 2023 | Jun 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | HS033-007 | Brick Wall Restoration/Garden Upgrades | 7 | CONSTRUCTION TO 75% | May 2009 | Sep 2009 | Jun 2023 | Oct 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | HS033-007 | Brick Wall Restoration/Garden Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2009 | Dec 2009 | Oct 2023 | Jan 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | HS033-007 | Brick Wall Restoration/Garden Upgrades | 9 | SUBSTANTIAL COMPLETION | Dec 2009 | Feb 2010 | Jan 2024 | Mar 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | HS033-007 | Brick Wall Restoration/Garden Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2010 | Mar 2010 | Mar 2024 | Apr 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | HS034-007 | 450 Grand Concourse Theater Improvements | 1 | DEVELOP SCOPE | Jun 2014 | Aug 2014 | Jun 2014 | Aug 2014
20231026 | BRONX | 042 | CITY UNIVERSITY | HS034-007 | 450 Grand Concourse Theater Improvements | 2 | PRELIMINARY DESIGN | Aug 2014 | Dec 2014 | Aug 2014 | Dec 2014
20231026 | BRONX | 042 | CITY UNIVERSITY | HS034-007 | 450 Grand Concourse Theater Improvements | 3 | FINAL DESIGN | Dec 2014 | Jun 2015 | Dec 2014 | Jun 2015
20231026 | BRONX | 042 | CITY UNIVERSITY | HS034-007 | 450 Grand Concourse Theater Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2015 | Sep 2015 | Jun 2015 | Sep 2015
20231026 | BRONX | 042 | CITY UNIVERSITY | HS034-007 | 450 Grand Concourse Theater Improvements | 5 | CONSTRUCTION TO 25% | Sep 2015 | Jan 2016 | Sep 2015 | Jan 2016
20231026 | BRONX | 042 | CITY UNIVERSITY | HS034-007 | 450 Grand Concourse Theater Improvements | 6 | CONSTRUCTION TO 50% | Jan 2016 | May 2016 | Jan 2016 | May 2016
20231026 | BRONX | 042 | CITY UNIVERSITY | HS034-007 | 450 Grand Concourse Theater Improvements | 7 | CONSTRUCTION TO 75% | May 2016 | Sep 2016 | May 2016 | Sep 2016
20231026 | BRONX | 042 | CITY UNIVERSITY | HS034-007 | 450 Grand Concourse Theater Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Dec 2016 | Sep 2016 | Dec 2016
20231026 | BRONX | 042 | CITY UNIVERSITY | HS034-007 | 450 Grand Concourse Theater Improvements | 9 | SUBSTANTIAL COMPLETION | Dec 2016 | Feb 2017 | Dec 2016 | Feb 2017
20231026 | BRONX | 042 | CITY UNIVERSITY | HS034-007 | 450 Grand Concourse Theater Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2017 | Mar 2017 | Feb 2017 | Jul 2030
20231026 | BRONX | 042 | CITY UNIVERSITY | HS041-011 | 500 Grand Concourse 4th Floor and Emerg. Generator | 1 | DEVELOP SCOPE | Jun 2011 | Aug 2011 | Jun 2011 | Aug 2011
20231026 | BRONX | 042 | CITY UNIVERSITY | HS041-011 | 500 Grand Concourse 4th Floor and Emerg. Generator | 2 | PRELIMINARY DESIGN | Aug 2011 | Dec 2011 | Aug 2011 | Dec 2011
20231026 | BRONX | 042 | CITY UNIVERSITY | HS041-011 | 500 Grand Concourse 4th Floor and Emerg. Generator | 3 | FINAL DESIGN | Dec 2011 | Jun 2012 | Dec 2011 | Jun 2012
20231026 | BRONX | 042 | CITY UNIVERSITY | HS041-011 | 500 Grand Concourse 4th Floor and Emerg. Generator | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2012 | Sep 2012 | Jun 2012 | Sep 2012
20231026 | BRONX | 042 | CITY UNIVERSITY | HS041-011 | 500 Grand Concourse 4th Floor and Emerg. Generator | 5 | CONSTRUCTION TO 25% | Sep 2012 | Jan 2013 | Sep 2012 | Jan 2013
20231026 | BRONX | 042 | CITY UNIVERSITY | HS041-011 | 500 Grand Concourse 4th Floor and Emerg. Generator | 6 | CONSTRUCTION TO 50% | Jan 2013 | May 2013 | Jan 2013 | May 2013
20231026 | BRONX | 042 | CITY UNIVERSITY | HS041-011 | 500 Grand Concourse 4th Floor and Emerg. Generator | 7 | CONSTRUCTION TO 75% | May 2013 | Sep 2013 | May 2013 | Sep 2013
20231026 | BRONX | 042 | CITY UNIVERSITY | HS041-011 | 500 Grand Concourse 4th Floor and Emerg. Generator | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | BRONX | 042 | CITY UNIVERSITY | HS041-011 | 500 Grand Concourse 4th Floor and Emerg. Generator | 9 | SUBSTANTIAL COMPLETION | Dec 2013 | Feb 2014 | Dec 2013 | Feb 2014
20231026 | BRONX | 042 | CITY UNIVERSITY | HS041-011 | 500 Grand Concourse 4th Floor and Emerg. Generator | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2014 | Mar 2014 | Feb 2014 | Dec 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | HS043-011 | Hostos CC - 500 Grand Concourse Renovations | 1 | DEVELOP SCOPE | Jun 2011 | Aug 2011 | Jul 2019 | Oct 2019
20231026 | BRONX | 042 | CITY UNIVERSITY | HS043-011 | Hostos CC - 500 Grand Concourse Renovations | 2 | PRELIMINARY DESIGN | Aug 2011 | Dec 2011 | Oct 2019 | Jan 2020
20231026 | BRONX | 042 | CITY UNIVERSITY | HS043-011 | Hostos CC - 500 Grand Concourse Renovations | 3 | FINAL DESIGN | Dec 2011 | Jun 2012 | Jan 2020 | Jul 2020
20231026 | BRONX | 042 | CITY UNIVERSITY | HS043-011 | Hostos CC - 500 Grand Concourse Renovations | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2012 | Sep 2012 | Jul 2020 | Oct 2020
20231026 | BRONX | 042 | CITY UNIVERSITY | HS043-011 | Hostos CC - 500 Grand Concourse Renovations | 5 | CONSTRUCTION TO 25% | Sep 2012 | Jan 2013 | Oct 2020 | Feb 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | HS043-011 | Hostos CC - 500 Grand Concourse Renovations | 6 | CONSTRUCTION TO 50% | Jan 2013 | May 2013 | Feb 2021 | Jun 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | HS043-011 | Hostos CC - 500 Grand Concourse Renovations | 7 | CONSTRUCTION TO 75% | May 2013 | Sep 2013 | Jun 2021 | Oct 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | HS043-011 | Hostos CC - 500 Grand Concourse Renovations | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2013 | Dec 2013 | Oct 2021 | Jan 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | HS043-011 | Hostos CC - 500 Grand Concourse Renovations | 9 | SUBSTANTIAL COMPLETION | Dec 2013 | Feb 2014 | Jan 2022 | Mar 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | HS043-011 | Hostos CC - 500 Grand Concourse Renovations | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2014 | Mar 2014 | Mar 2022 | Apr 2027
20231026 | BRONX | 042 | CITY UNIVERSITY | HS047-013 | Savoy Building Roof Replacement | 1 | DEVELOP SCOPE | Jun 2013 | Aug 2013 | Jun 2013 | Aug 2013
20231026 | BRONX | 042 | CITY UNIVERSITY | HS047-013 | Savoy Building Roof Replacement | 2 | PRELIMINARY DESIGN | Aug 2013 | Dec 2013 | Aug 2013 | Dec 2013
20231026 | BRONX | 042 | CITY UNIVERSITY | HS047-013 | Savoy Building Roof Replacement | 3 | FINAL DESIGN | Dec 2013 | Jun 2014 | Dec 2013 | Jun 2014
20231026 | BRONX | 042 | CITY UNIVERSITY | HS047-013 | Savoy Building Roof Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2014 | Sep 2014 | Jun 2014 | Sep 2014
20231026 | BRONX | 042 | CITY UNIVERSITY | HS047-013 | Savoy Building Roof Replacement | 5 | CONSTRUCTION TO 25% | Sep 2014 | Jan 2015 | Sep 2014 | Jan 2015
20231026 | BRONX | 042 | CITY UNIVERSITY | HS047-013 | Savoy Building Roof Replacement | 6 | CONSTRUCTION TO 50% | Jan 2015 | May 2015 | Jan 2015 | May 2015
20231026 | BRONX | 042 | CITY UNIVERSITY | HS047-013 | Savoy Building Roof Replacement | 7 | CONSTRUCTION TO 75% | May 2015 | Sep 2015 | May 2015 | Sep 2015
20231026 | BRONX | 042 | CITY UNIVERSITY | HS047-013 | Savoy Building Roof Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | BRONX | 042 | CITY UNIVERSITY | HS047-013 | Savoy Building Roof Replacement | 9 | SUBSTANTIAL COMPLETION | Dec 2015 | Feb 2016 | Dec 2015 | Feb 2016
20231026 | BRONX | 042 | CITY UNIVERSITY | HS047-013 | Savoy Building Roof Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2016 | Mar 2016 | Feb 2016 | Mar 2031
20231026 | BRONX | 042 | CITY UNIVERSITY | HS048-013 | Renovation and HVAC Upgrade | 1 | DEVELOP SCOPE | Jun 2013 | Aug 2013 | Jun 2013 | Aug 2013
20231026 | BRONX | 042 | CITY UNIVERSITY | HS048-013 | Renovation and HVAC Upgrade | 2 | PRELIMINARY DESIGN | Aug 2013 | Dec 2013 | Aug 2013 | Dec 2013
20231026 | BRONX | 042 | CITY UNIVERSITY | HS048-013 | Renovation and HVAC Upgrade | 3 | FINAL DESIGN | Dec 2013 | Jun 2014 | Dec 2013 | Jun 2014
20231026 | BRONX | 042 | CITY UNIVERSITY | HS048-013 | Renovation and HVAC Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2014 | Sep 2014 | Jun 2014 | Sep 2014
20231026 | BRONX | 042 | CITY UNIVERSITY | HS048-013 | Renovation and HVAC Upgrade | 5 | CONSTRUCTION TO 25% | Sep 2014 | Jan 2015 | Sep 2014 | Jan 2015
20231026 | BRONX | 042 | CITY UNIVERSITY | HS048-013 | Renovation and HVAC Upgrade | 6 | CONSTRUCTION TO 50% | Jan 2015 | May 2015 | Jan 2015 | May 2015
20231026 | BRONX | 042 | CITY UNIVERSITY | HS048-013 | Renovation and HVAC Upgrade | 7 | CONSTRUCTION TO 75% | May 2015 | Sep 2015 | May 2015 | Sep 2015
20231026 | BRONX | 042 | CITY UNIVERSITY | HS048-013 | Renovation and HVAC Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | BRONX | 042 | CITY UNIVERSITY | HS048-013 | Renovation and HVAC Upgrade | 9 | SUBSTANTIAL COMPLETION | Dec 2015 | Feb 2016 | Dec 2015 | Feb 2016
20231026 | BRONX | 042 | CITY UNIVERSITY | HS048-013 | Renovation and HVAC Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2016 | Mar 2016 | Feb 2016 | Mar 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | HS050-014 | Allied Health and Sciences Building | 1 | DEVELOP SCOPE | Jun 2014 | Aug 2014 | Jul 2021 | Sep 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | HS050-014 | Allied Health and Sciences Building | 2 | PRELIMINARY DESIGN | Aug 2014 | Dec 2014 | Sep 2021 | Jan 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | HS050-014 | Allied Health and Sciences Building | 3 | FINAL DESIGN | Dec 2014 | Jun 2015 | Jan 2022 | Jul 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | HS050-014 | Allied Health and Sciences Building | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2015 | Sep 2015 | Jul 2022 | Oct 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | HS050-014 | Allied Health and Sciences Building | 5 | CONSTRUCTION TO 25% | Sep 2015 | Jan 2016 | Oct 2022 | Feb 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | HS050-014 | Allied Health and Sciences Building | 6 | CONSTRUCTION TO 50% | Jan 2016 | May 2016 | Feb 2023 | Jun 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | HS050-014 | Allied Health and Sciences Building | 7 | CONSTRUCTION TO 75% | May 2016 | Sep 2016 | Jun 2023 | Oct 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | HS050-014 | Allied Health and Sciences Building | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Dec 2016 | Oct 2023 | Jan 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | HS050-014 | Allied Health and Sciences Building | 9 | SUBSTANTIAL COMPLETION | Dec 2016 | Feb 2017 | Jan 2024 | Mar 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | HS050-014 | Allied Health and Sciences Building | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2017 | Mar 2017 | Mar 2024 | Apr 2027
20231026 | BRONX | 042 | CITY UNIVERSITY | HS054-017 | Create one Stop Center -425 Grand Concourse | 1 | DEVELOP SCOPE | Jun 2017 | Aug 2017 | Jul 2019 | Oct 2019
20231026 | BRONX | 042 | CITY UNIVERSITY | HS054-017 | Create one Stop Center -425 Grand Concourse | 2 | PRELIMINARY DESIGN | Aug 2017 | Dec 2017 | Oct 2019 | Jan 2020
20231026 | BRONX | 042 | CITY UNIVERSITY | HS054-017 | Create one Stop Center -425 Grand Concourse | 3 | FINAL DESIGN | Dec 2017 | Jun 2018 | Jan 2020 | Jul 2020
20231026 | BRONX | 042 | CITY UNIVERSITY | HS054-017 | Create one Stop Center -425 Grand Concourse | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Sep 2018 | Jul 2020 | Oct 2020
20231026 | BRONX | 042 | CITY UNIVERSITY | HS054-017 | Create one Stop Center -425 Grand Concourse | 5 | CONSTRUCTION TO 25% | Sep 2018 | Jan 2019 | Oct 2020 | Feb 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | HS054-017 | Create one Stop Center -425 Grand Concourse | 6 | CONSTRUCTION TO 50% | Jan 2019 | May 2019 | Feb 2021 | Jun 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | HS054-017 | Create one Stop Center -425 Grand Concourse | 7 | CONSTRUCTION TO 75% | May 2019 | Sep 2019 | Jun 2021 | Oct 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | HS054-017 | Create one Stop Center -425 Grand Concourse | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Dec 2019 | Oct 2021 | Jan 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | HS054-017 | Create one Stop Center -425 Grand Concourse | 9 | SUBSTANTIAL COMPLETION | Dec 2019 | Feb 2020 | Jan 2022 | Mar 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | HS054-017 | Create one Stop Center -425 Grand Concourse | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2020 | Mar 2020 | Mar 2022 | May 2027
20231026 | BRONX | 042 | CITY UNIVERSITY | HS055-098 | Window Rehab - 471 Walton | 2 | PRELIMINARY DESIGN | May 2007 | Sep 2007 | May 2007 | Sep 2007
20231026 | BRONX | 042 | CITY UNIVERSITY | HS055-098 | Window Rehab - 471 Walton | 3 | FINAL DESIGN | Sep 2007 | Mar 2008 | Sep 2007 | Mar 2008
20231026 | BRONX | 042 | CITY UNIVERSITY | HS055-098 | Window Rehab - 471 Walton | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2008 | Jun 2008 | Mar 2008 | Jun 2008
20231026 | BRONX | 042 | CITY UNIVERSITY | HS055-098 | Window Rehab - 471 Walton | 5 | CONSTRUCTION TO 25% | Jun 2008 | Oct 2008 | Jun 2008 | Oct 2008
20231026 | BRONX | 042 | CITY UNIVERSITY | HS055-098 | Window Rehab - 471 Walton | 6 | CONSTRUCTION TO 50% | Oct 2008 | Jun 2009 | Oct 2008 | Jun 2009
20231026 | BRONX | 042 | CITY UNIVERSITY | HS055-098 | Window Rehab - 471 Walton | 7 | CONSTRUCTION TO 75% | Jun 2009 | Jun 2010 | Jun 2009 | Jun 2010
20231026 | BRONX | 042 | CITY UNIVERSITY | HS055-098 | Window Rehab - 471 Walton | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2010 | Jun 2010 | Jun 2010 | Jun 2010
20231026 | BRONX | 042 | CITY UNIVERSITY | HS055-098 | Window Rehab - 471 Walton | 9 | SUBSTANTIAL COMPLETION | Jun 2010 | Jun 2010 | Jun 2010 | Jun 2010
20231026 | BRONX | 042 | CITY UNIVERSITY | HS055-098 | Window Rehab - 471 Walton | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2010 | Jul 2010 | Jun 2010 | Jul 2018
20231026 | BRONX | 042 | CITY UNIVERSITY | HS057-019 | Smart Classroom Conversion | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jul 2020 | Oct 2020
20231026 | BRONX | 042 | CITY UNIVERSITY | HS057-019 | Smart Classroom Conversion | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Oct 2020 | Jan 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | HS057-019 | Smart Classroom Conversion | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2021 | Jul 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | HS057-019 | Smart Classroom Conversion | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2021 | Oct 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | HS057-019 | Smart Classroom Conversion | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2021 | Feb 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | HS057-019 | Smart Classroom Conversion | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2022 | Jun 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | HS057-019 | Smart Classroom Conversion | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2022 | Oct 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | HS057-019 | Smart Classroom Conversion | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2022 | Jan 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | HS057-019 | Smart Classroom Conversion | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2023 | Mar 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | HS057-019 | Smart Classroom Conversion | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2023 | Apr 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | HS059-021 | Video Projection | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | HS059-021 | Video Projection | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | HS059-021 | Video Projection | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | HS059-021 | Video Projection | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | HS059-021 | Video Projection | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | HS059-021 | Video Projection | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | HS059-021 | Video Projection | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | HS059-021 | Video Projection | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | HS059-021 | Video Projection | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | HS059-021 | Video Projection | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | LM001-024 | ANIMATION LAB | 1 | DEVELOP SCOPE | Jul 2023 | Sep 2024 | Jul 2023 | Sep 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | LM001-024 | ANIMATION LAB | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | LM001-024 | ANIMATION LAB | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | LM001-024 | ANIMATION LAB | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | LM001-024 | ANIMATION LAB | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | LM001-024 | ANIMATION LAB | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | LM001-024 | ANIMATION LAB | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | LM001-024 | ANIMATION LAB | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | BRONX | 042 | CITY UNIVERSITY | LM001-024 | ANIMATION LAB | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | BRONX | 042 | CITY UNIVERSITY | LM001-024 | ANIMATION LAB | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | BRONX | 042 | CITY UNIVERSITY | LM002-021 | Teaching and Learning Innovation Space - Art | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | LM002-021 | Teaching and Learning Innovation Space - Art | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | LM002-021 | Teaching and Learning Innovation Space - Art | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | LM002-021 | Teaching and Learning Innovation Space - Art | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | LM002-021 | Teaching and Learning Innovation Space - Art | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | LM002-021 | Teaching and Learning Innovation Space - Art | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | LM002-021 | Teaching and Learning Innovation Space - Art | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | LM002-021 | Teaching and Learning Innovation Space - Art | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | LM002-021 | Teaching and Learning Innovation Space - Art | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | LM002-021 | Teaching and Learning Innovation Space - Art | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2029
20231026 | BRONX | 042 | CITY UNIVERSITY | LM004-022 | Lecture Hall Upgrades | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | LM004-022 | Lecture Hall Upgrades | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | LM004-022 | Lecture Hall Upgrades | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | LM004-022 | Lecture Hall Upgrades | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | LM004-022 | Lecture Hall Upgrades | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | LM004-022 | Lecture Hall Upgrades | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | LM004-022 | Lecture Hall Upgrades | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | LM004-022 | Lecture Hall Upgrades | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | LM004-022 | Lecture Hall Upgrades | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | BRONX | 042 | CITY UNIVERSITY | LM004-022 | Lecture Hall Upgrades | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2027
20231026 | BRONX | 042 | CITY UNIVERSITY | LM019-011 | Concert Hall Lighting Upgrade / Acoustics Upgrade | 1 | DEVELOP SCOPE | Jun 2011 | Aug 2011 | Jun 2011 | Aug 2011
20231026 | BRONX | 042 | CITY UNIVERSITY | LM019-011 | Concert Hall Lighting Upgrade / Acoustics Upgrade | 2 | PRELIMINARY DESIGN | Aug 2011 | Dec 2011 | Aug 2011 | Dec 2011
20231026 | BRONX | 042 | CITY UNIVERSITY | LM019-011 | Concert Hall Lighting Upgrade / Acoustics Upgrade | 3 | FINAL DESIGN | Dec 2011 | Jun 2012 | Dec 2011 | Jun 2012
20231026 | BRONX | 042 | CITY UNIVERSITY | LM019-011 | Concert Hall Lighting Upgrade / Acoustics Upgrade | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2012 | Sep 2012 | Jun 2012 | Sep 2012
20231026 | BRONX | 042 | CITY UNIVERSITY | LM019-011 | Concert Hall Lighting Upgrade / Acoustics Upgrade | 5 | CONSTRUCTION TO 25% | Sep 2012 | Jan 2013 | Sep 2012 | Jan 2013
20231026 | BRONX | 042 | CITY UNIVERSITY | LM019-011 | Concert Hall Lighting Upgrade / Acoustics Upgrade | 6 | CONSTRUCTION TO 50% | Jan 2013 | May 2013 | Jan 2013 | May 2013
20231026 | BRONX | 042 | CITY UNIVERSITY | LM019-011 | Concert Hall Lighting Upgrade / Acoustics Upgrade | 7 | CONSTRUCTION TO 75% | May 2013 | Sep 2013 | May 2013 | Sep 2013
20231026 | BRONX | 042 | CITY UNIVERSITY | LM019-011 | Concert Hall Lighting Upgrade / Acoustics Upgrade | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | BRONX | 042 | CITY UNIVERSITY | LM019-011 | Concert Hall Lighting Upgrade / Acoustics Upgrade | 9 | SUBSTANTIAL COMPLETION | Dec 2013 | Feb 2014 | Dec 2013 | Feb 2014
20231026 | BRONX | 042 | CITY UNIVERSITY | LM019-011 | Concert Hall Lighting Upgrade / Acoustics Upgrade | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2014 | Mar 2014 | Feb 2014 | Jun 2026
20231026 | BRONX | 042 | CITY UNIVERSITY | LM022-013 | One-Stop Student Services & Transfer Center | 1 | DEVELOP SCOPE | Jun 2013 | Aug 2013 | Jun 2013 | Aug 2013
20231026 | BRONX | 042 | CITY UNIVERSITY | LM022-013 | One-Stop Student Services & Transfer Center | 2 | PRELIMINARY DESIGN | Aug 2013 | Dec 2013 | Aug 2013 | Dec 2013
20231026 | BRONX | 042 | CITY UNIVERSITY | LM022-013 | One-Stop Student Services & Transfer Center | 3 | FINAL DESIGN | Dec 2013 | Jun 2014 | Dec 2013 | Jun 2014
20231026 | BRONX | 042 | CITY UNIVERSITY | LM022-013 | One-Stop Student Services & Transfer Center | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2014 | Sep 2014 | Jun 2014 | Sep 2014
20231026 | BRONX | 042 | CITY UNIVERSITY | LM022-013 | One-Stop Student Services & Transfer Center | 5 | CONSTRUCTION TO 25% | Sep 2014 | Jan 2015 | Sep 2014 | Jan 2015
20231026 | BRONX | 042 | CITY UNIVERSITY | LM022-013 | One-Stop Student Services & Transfer Center | 6 | CONSTRUCTION TO 50% | Jan 2015 | May 2015 | Jan 2015 | May 2015
20231026 | BRONX | 042 | CITY UNIVERSITY | LM022-013 | One-Stop Student Services & Transfer Center | 7 | CONSTRUCTION TO 75% | May 2015 | Sep 2015 | May 2015 | Sep 2015
20231026 | BRONX | 042 | CITY UNIVERSITY | LM022-013 | One-Stop Student Services & Transfer Center | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | BRONX | 042 | CITY UNIVERSITY | LM022-013 | One-Stop Student Services & Transfer Center | 9 | SUBSTANTIAL COMPLETION | Dec 2015 | Feb 2016 | Dec 2015 | Feb 2016
20231026 | BRONX | 042 | CITY UNIVERSITY | LM022-013 | One-Stop Student Services & Transfer Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2016 | Mar 2016 | Feb 2016 | Mar 2016
20231026 | BRONX | 042 | CITY UNIVERSITY | LM025-014 | Cloudlink Student Lab Virtual Desktop (iCloud Upgrade) | 3 | FINAL DESIGN | Dec 2014 | Jun 2015 | Dec 2014 | Jun 2015
20231026 | BRONX | 042 | CITY UNIVERSITY | LM025-014 | Cloudlink Student Lab Virtual Desktop (iCloud Upgrade) | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2015 | Sep 2015 | Jun 2015 | Sep 2015
20231026 | BRONX | 042 | CITY UNIVERSITY | LM025-014 | Cloudlink Student Lab Virtual Desktop (iCloud Upgrade) | 5 | CONSTRUCTION TO 25% | Sep 2015 | Jan 2016 | Sep 2015 | Jan 2016
20231026 | BRONX | 042 | CITY UNIVERSITY | LM025-014 | Cloudlink Student Lab Virtual Desktop (iCloud Upgrade) | 6 | CONSTRUCTION TO 50% | Jan 2016 | May 2016 | Jan 2016 | May 2016
20231026 | BRONX | 042 | CITY UNIVERSITY | LM025-014 | Cloudlink Student Lab Virtual Desktop (iCloud Upgrade) | 7 | CONSTRUCTION TO 75% | May 2016 | Sep 2016 | May 2016 | Sep 2016
20231026 | BRONX | 042 | CITY UNIVERSITY | LM025-014 | Cloudlink Student Lab Virtual Desktop (iCloud Upgrade) | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Dec 2016 | Sep 2016 | Dec 2016
20231026 | BRONX | 042 | CITY UNIVERSITY | LM025-014 | Cloudlink Student Lab Virtual Desktop (iCloud Upgrade) | 9 | SUBSTANTIAL COMPLETION | Dec 2016 | Feb 2017 | Dec 2016 | Feb 2017
20231026 | BRONX | 042 | CITY UNIVERSITY | LM025-014 | Cloudlink Student Lab Virtual Desktop (iCloud Upgrade) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2017 | Mar 2017 | Feb 2017 | Mar 2020
20231026 | BRONX | 042 | CITY UNIVERSITY | LM029016 | Upgrade and Convert Carman Hall | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Jul 2021 | Sep 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | LM029016 | Upgrade and Convert Carman Hall | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Sep 2021 | Jan 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | LM029016 | Upgrade and Convert Carman Hall | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Jan 2022 | Jul 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | LM029016 | Upgrade and Convert Carman Hall | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Jul 2022 | Oct 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | LM029016 | Upgrade and Convert Carman Hall | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Oct 2022 | Feb 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | LM029016 | Upgrade and Convert Carman Hall | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Feb 2023 | Jun 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | LM029016 | Upgrade and Convert Carman Hall | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Jun 2023 | Oct 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | LM029016 | Upgrade and Convert Carman Hall | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | Oct 2023 | Jan 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | LM029016 | Upgrade and Convert Carman Hall | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Jan 2024 | Mar 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | LM029016 | Upgrade and Convert Carman Hall | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Mar 2024 | Jul 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | LM032-017 | Gillet Auditorium Renovation | 1 | DEVELOP SCOPE | Jun 2017 | Aug 2017 | Jul 2021 | Sep 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | LM032-017 | Gillet Auditorium Renovation | 2 | PRELIMINARY DESIGN | Aug 2017 | Dec 2017 | Sep 2021 | Jan 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | LM032-017 | Gillet Auditorium Renovation | 3 | FINAL DESIGN | Dec 2017 | Jun 2018 | Jan 2022 | Jul 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | LM032-017 | Gillet Auditorium Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Sep 2018 | Jul 2022 | Oct 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | LM032-017 | Gillet Auditorium Renovation | 5 | CONSTRUCTION TO 25% | Sep 2018 | Jan 2019 | Oct 2022 | Feb 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | LM032-017 | Gillet Auditorium Renovation | 6 | CONSTRUCTION TO 50% | Jan 2019 | May 2019 | Feb 2023 | Jun 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | LM032-017 | Gillet Auditorium Renovation | 7 | CONSTRUCTION TO 75% | May 2019 | Sep 2019 | Jun 2023 | Oct 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | LM032-017 | Gillet Auditorium Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Dec 2019 | Oct 2023 | Jan 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | LM032-017 | Gillet Auditorium Renovation | 9 | SUBSTANTIAL COMPLETION | Dec 2019 | Feb 2020 | Jan 2024 | Mar 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | LM032-017 | Gillet Auditorium Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2020 | Mar 2020 | Mar 2024 | Apr 2028
20231026 | BRONX | 042 | CITY UNIVERSITY | LM034-018 | Convert classrooms into NetworkSmart Rooms | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jul 2021 | Sep 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | LM034-018 | Convert classrooms into NetworkSmart Rooms | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Sep 2021 | Jan 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | LM034-018 | Convert classrooms into NetworkSmart Rooms | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Jan 2022 | Jul 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | LM034-018 | Convert classrooms into NetworkSmart Rooms | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jul 2022 | Oct 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | LM034-018 | Convert classrooms into NetworkSmart Rooms | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Oct 2022 | Feb 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | LM034-018 | Convert classrooms into NetworkSmart Rooms | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Feb 2023 | Jun 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | LM034-018 | Convert classrooms into NetworkSmart Rooms | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | Jun 2023 | Oct 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | LM034-018 | Convert classrooms into NetworkSmart Rooms | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Oct 2023 | Jan 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | LM034-018 | Convert classrooms into NetworkSmart Rooms | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Jan 2024 | Mar 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | LM034-018 | Convert classrooms into NetworkSmart Rooms | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Mar 2024 | Jul 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | LM035-018 | Gillet Auditorium Renovation | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jul 2021 | Sep 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | LM035-018 | Gillet Auditorium Renovation | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Sep 2021 | Jan 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | LM035-018 | Gillet Auditorium Renovation | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Jan 2022 | Jul 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | LM035-018 | Gillet Auditorium Renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jul 2022 | Oct 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | LM035-018 | Gillet Auditorium Renovation | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Oct 2022 | Feb 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | LM035-018 | Gillet Auditorium Renovation | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Feb 2023 | Jun 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | LM035-018 | Gillet Auditorium Renovation | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | Jun 2023 | Oct 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | LM035-018 | Gillet Auditorium Renovation | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Oct 2023 | Jan 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | LM035-018 | Gillet Auditorium Renovation | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Jan 2024 | Mar 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | LM035-018 | Gillet Auditorium Renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Mar 2024 | Apr 2028
20231026 | BRONX | 042 | CITY UNIVERSITY | LM036-019 | Concert Hall Fixed Seating | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | BRONX | 042 | CITY UNIVERSITY | LM036-019 | Concert Hall Fixed Seating | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Sep 2018 | Jan 2019
20231026 | BRONX | 042 | CITY UNIVERSITY | LM036-019 | Concert Hall Fixed Seating | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2019 | Jul 2019
20231026 | BRONX | 042 | CITY UNIVERSITY | LM036-019 | Concert Hall Fixed Seating | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2019 | Oct 2019
20231026 | BRONX | 042 | CITY UNIVERSITY | LM036-019 | Concert Hall Fixed Seating | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2019 | Feb 2020
20231026 | BRONX | 042 | CITY UNIVERSITY | LM036-019 | Concert Hall Fixed Seating | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2020 | Jun 2020
20231026 | BRONX | 042 | CITY UNIVERSITY | LM036-019 | Concert Hall Fixed Seating | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2020 | Oct 2020
20231026 | BRONX | 042 | CITY UNIVERSITY | LM036-019 | Concert Hall Fixed Seating | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2020 | Jan 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | LM036-019 | Concert Hall Fixed Seating | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2021 | Mar 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | LM036-019 | Concert Hall Fixed Seating | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2021 | Apr 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | LM041-020 | Studio Theatre Lighting & Dimming System | 1 | DEVELOP SCOPE | Jul 2021 | Sep 2021 | Jul 2021 | Sep 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | LM041-020 | Studio Theatre Lighting & Dimming System | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | LM041-020 | Studio Theatre Lighting & Dimming System | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | LM041-020 | Studio Theatre Lighting & Dimming System | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | LM041-020 | Studio Theatre Lighting & Dimming System | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | LM041-020 | Studio Theatre Lighting & Dimming System | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | LM041-020 | Studio Theatre Lighting & Dimming System | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | LM041-020 | Studio Theatre Lighting & Dimming System | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | LM041-020 | Studio Theatre Lighting & Dimming System | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | LM041-020 | Studio Theatre Lighting & Dimming System | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2029
20231026 | BRONX | 042 | CITY UNIVERSITY | LM043-021 | Social Work Department Expansion | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | BRONX | 042 | CITY UNIVERSITY | LM043-021 | Social Work Department Expansion | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | LM043-021 | Social Work Department Expansion | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2022 | Jul 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | LM043-021 | Social Work Department Expansion | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | BRONX | 042 | CITY UNIVERSITY | LM043-021 | Social Work Department Expansion | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | LM043-021 | Social Work Department Expansion | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | LM043-021 | Social Work Department Expansion | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | BRONX | 042 | CITY UNIVERSITY | LM043-021 | Social Work Department Expansion | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | LM043-021 | Social Work Department Expansion | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | BRONX | 042 | CITY UNIVERSITY | LM043-021 | Social Work Department Expansion | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2024 | Apr 2029
20231026 | BRONX | 042 | CITY UNIVERSITY | LM058-995 | KIOSK AND DIRECTIONAL SIGNAGE ON CAMPUS | 2 | PRELIMINARY DESIGN | May 2007 | Sep 2007 | May 2007 | Sep 2007
20231026 | BRONX | 042 | CITY UNIVERSITY | LM058-995 | KIOSK AND DIRECTIONAL SIGNAGE ON CAMPUS | 3 | FINAL DESIGN | Sep 2007 | Mar 2008 | Sep 2007 | Mar 2008
20231026 | BRONX | 042 | CITY UNIVERSITY | LM058-995 | KIOSK AND DIRECTIONAL SIGNAGE ON CAMPUS | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2008 | Jun 2008 | Mar 2008 | Jun 2008
20231026 | BRONX | 042 | CITY UNIVERSITY | LM058-995 | KIOSK AND DIRECTIONAL SIGNAGE ON CAMPUS | 5 | CONSTRUCTION TO 25% | Jun 2008 | Oct 2008 | Jun 2008 | Oct 2008
20231026 | BRONX | 042 | CITY UNIVERSITY | LM058-995 | KIOSK AND DIRECTIONAL SIGNAGE ON CAMPUS | 6 | CONSTRUCTION TO 50% | Oct 2008 | Feb 2009 | Oct 2008 | Feb 2009
20231026 | BRONX | 042 | CITY UNIVERSITY | LM058-995 | KIOSK AND DIRECTIONAL SIGNAGE ON CAMPUS | 7 | CONSTRUCTION TO 75% | Feb 2009 | Jun 2009 | Feb 2009 | Jun 2009
20231026 | BRONX | 042 | CITY UNIVERSITY | LM058-995 | KIOSK AND DIRECTIONAL SIGNAGE ON CAMPUS | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2009 | Sep 2009 | Jun 2009 | Sep 2009
20231026 | BRONX | 042 | CITY UNIVERSITY | LM058-995 | KIOSK AND DIRECTIONAL SIGNAGE ON CAMPUS | 9 | SUBSTANTIAL COMPLETION | Sep 2009 | Nov 2009 | Sep 2009 | Nov 2009
20231026 | BRONX | 042 | CITY UNIVERSITY | LM058-995 | KIOSK AND DIRECTIONAL SIGNAGE ON CAMPUS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2009 | Dec 2009 | Nov 2009 | May 2011
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79-52P | 52ND PRECINCT RENOVATION | 1 | DESIGN | Jul 2020 | Jan 2021 | Jul 2020 | Jan 2022
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79-52P | 52ND PRECINCT RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2021 | Apr 2021 | Jan 2022 | Apr 2022
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79-52P | 52ND PRECINCT RENOVATION | 3 | CONSTRUCTION | Apr 2021 | Apr 2022 | Apr 2022 | Apr 2023
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79-52P | 52ND PRECINCT RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2022 | Oct 2022 | Apr 2023 | Jun 2029
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAJX | 46th PRECINCT ADA RAMP | 1 | DESIGN | Sep 2018 | Mar 2019 | Sep 2017 | Mar 2018
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAJX | 46th PRECINCT ADA RAMP | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2019 | Jun 2019 | Mar 2018 | Jun 2018
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAJX | 46th PRECINCT ADA RAMP | 3 | CONSTRUCTION | Jun 2019 | Jun 2020 | Jun 2018 | Jun 2021
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAJX | 46th PRECINCT ADA RAMP | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2020 | Dec 2020 | Jun 2021 | Dec 2021
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKD | RODMAN'S NECK BATHROOM TRAILERS | 1 | DEVELOP SCOPE | Oct 2019 | Dec 2019 | Oct 2019 | Dec 2019
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKD | RODMAN'S NECK BATHROOM TRAILERS | 2 | PRELIMINARY DESIGN | Dec 2019 | Apr 2020 | Dec 2019 | Apr 2020
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKD | RODMAN'S NECK BATHROOM TRAILERS | 3 | FINAL DESIGN | Apr 2020 | Aug 2020 | Apr 2020 | Aug 2020
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKD | RODMAN'S NECK BATHROOM TRAILERS | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2020 | Feb 2021 | Aug 2020 | Feb 2021
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKD | RODMAN'S NECK BATHROOM TRAILERS | 5 | CONSTRUCTION TO 25% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKD | RODMAN'S NECK BATHROOM TRAILERS | 6 | CONSTRUCTION TO 50% | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKD | RODMAN'S NECK BATHROOM TRAILERS | 7 | CONSTRUCTION TO 75% | Oct 2021 | Feb 2022 | Oct 2021 | Feb 2022
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKD | RODMAN'S NECK BATHROOM TRAILERS | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2022 | May 2022 | Feb 2022 | May 2022
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKD | RODMAN'S NECK BATHROOM TRAILERS | 9 | SUBSTANTIAL COMPLETION | May 2022 | Jul 2022 | May 2022 | Jul 2022
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKD | RODMAN'S NECK BATHROOM TRAILERS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2022 | Aug 2022 | Jul 2022 | Sep 2026
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKK | REHABILITATION OF 48TH PCT ELEVATOR | 1 | DEVELOP SCOPE | Dec 2020 | Mar 2021 | Dec 2020 | Mar 2021
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKK | REHABILITATION OF 48TH PCT ELEVATOR | 2 | PRELIMINARY DESIGN | Mar 2021 | Jul 2021 | Mar 2021 | Jul 2021
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKK | REHABILITATION OF 48TH PCT ELEVATOR | 3 | FINAL DESIGN | Jul 2021 | Nov 2021 | Jul 2021 | Nov 2021
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKK | REHABILITATION OF 48TH PCT ELEVATOR | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2021 | May 2022 | Nov 2021 | May 2022
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKK | REHABILITATION OF 48TH PCT ELEVATOR | 5 | CONSTRUCTION TO 25% | May 2022 | Aug 2022 | May 2022 | Aug 2022
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKK | REHABILITATION OF 48TH PCT ELEVATOR | 6 | CONSTRUCTION TO 50% | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKK | REHABILITATION OF 48TH PCT ELEVATOR | 7 | CONSTRUCTION TO 75% | Dec 2022 | Apr 2023 | Dec 2022 | Apr 2023
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKK | REHABILITATION OF 48TH PCT ELEVATOR | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2023 | Jul 2023 | Apr 2023 | Jul 2023
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKK | REHABILITATION OF 48TH PCT ELEVATOR | 9 | SUBSTANTIAL COMPLETION | Jul 2023 | Sep 2023 | Jul 2023 | Sep 2023
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKK | REHABILITATION OF 48TH PCT ELEVATOR | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Oct 2023 | Sep 2023 | Oct 2027
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKO | ROOF REPLACEMENT AT 49TH PCT | 1 | DEVELOP SCOPE | Dec 2020 | Mar 2021 | Dec 2020 | Mar 2021
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKO | ROOF REPLACEMENT AT 49TH PCT | 2 | PRELIMINARY DESIGN | Mar 2021 | Jul 2021 | Mar 2021 | Jul 2021
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKO | ROOF REPLACEMENT AT 49TH PCT | 3 | FINAL DESIGN | Jul 2021 | Nov 2021 | Jul 2021 | Nov 2021
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKO | ROOF REPLACEMENT AT 49TH PCT | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2021 | May 2022 | Nov 2021 | May 2022
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKO | ROOF REPLACEMENT AT 49TH PCT | 5 | CONSTRUCTION TO 25% | May 2022 | Aug 2022 | May 2022 | Aug 2022
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKO | ROOF REPLACEMENT AT 49TH PCT | 6 | CONSTRUCTION TO 50% | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKO | ROOF REPLACEMENT AT 49TH PCT | 7 | CONSTRUCTION TO 75% | Dec 2022 | Apr 2023 | Dec 2022 | Apr 2023
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKO | ROOF REPLACEMENT AT 49TH PCT | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2023 | Jul 2023 | Apr 2023 | Jul 2023
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKO | ROOF REPLACEMENT AT 49TH PCT | 9 | SUBSTANTIAL COMPLETION | Jul 2023 | Sep 2023 | Jul 2023 | Sep 2023
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKO | ROOF REPLACEMENT AT 49TH PCT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Oct 2023 | Sep 2023 | Oct 2027
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79RNSA | RODMAN'S NECK SOUND ABATEMENT | 1 | DEVELOP SCOPE | Aug 2021 | Nov 2021 | Aug 2021 | Nov 2021
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79RNSA | RODMAN'S NECK SOUND ABATEMENT | 2 | PRELIMINARY DESIGN | Nov 2021 | Mar 2022 | Nov 2021 | Mar 2022
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79RNSA | RODMAN'S NECK SOUND ABATEMENT | 3 | FINAL DESIGN | Mar 2022 | Jul 2022 | Mar 2022 | Jul 2022
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79RNSA | RODMAN'S NECK SOUND ABATEMENT | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Jan 2023 | Jul 2022 | Jan 2023
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79RNSA | RODMAN'S NECK SOUND ABATEMENT | 5 | CONSTRUCTION TO 25% | Jan 2023 | May 2023 | Jan 2023 | May 2023
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79RNSA | RODMAN'S NECK SOUND ABATEMENT | 6 | CONSTRUCTION TO 50% | May 2023 | Sep 2023 | May 2023 | Sep 2023
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79RNSA | RODMAN'S NECK SOUND ABATEMENT | 7 | CONSTRUCTION TO 75% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79RNSA | RODMAN'S NECK SOUND ABATEMENT | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2024 | Mar 2024 | Jan 2024 | Mar 2024
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79RNSA | RODMAN'S NECK SOUND ABATEMENT | 9 | SUBSTANTIAL COMPLETION | Apr 2024 | May 2024 | Apr 2024 | May 2024
20231026 | BRONX | 056 | POLICE DEPARTMENT | PO79RNSA | RODMAN'S NECK SOUND ABATEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Jun 2024 | May 2024 | Jun 2029
20231026 | BRONX | 056 | POLICE DEPARTMENT | POD47RENO | Renovate/Upgrade 47th Precinct. | 1 | DESIGN | Nov 2017 | Apr 2018 | Nov 2017 | Apr 2018
20231026 | BRONX | 056 | POLICE DEPARTMENT | POD47RENO | Renovate/Upgrade 47th Precinct. | 2 | BID AWARD AND REGISTER CONTRCT | Apr 2018 | Jul 2018 | Apr 2018 | Jul 2018
20231026 | BRONX | 056 | POLICE DEPARTMENT | POD47RENO | Renovate/Upgrade 47th Precinct. | 3 | CONSTRUCTION | Jul 2018 | Jul 2019 | Jul 2018 | Jul 2022
20231026 | BRONX | 056 | POLICE DEPARTMENT | POD47RENO | Renovate/Upgrade 47th Precinct. | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2019 | Jan 2020 | Jul 2022 | Jan 2025
20231026 | BRONX | 056 | POLICE DEPARTMENT | POD50ELGE | 50TH PCT REPLACE ELEVATORS AND GENERATORS | 1 | DEVELOP SCOPE | Jun 2005 | Sep 2005 | Apr 2019 | Jul 2019
20231026 | BRONX | 056 | POLICE DEPARTMENT | POD50ELGE | 50TH PCT REPLACE ELEVATORS AND GENERATORS | 2 | PRELIMINARY DESIGN | Sep 2005 | Jan 2006 | Jul 2019 | Oct 2019
20231026 | BRONX | 056 | POLICE DEPARTMENT | POD50ELGE | 50TH PCT REPLACE ELEVATORS AND GENERATORS | 3 | FINAL DESIGN | Jan 2006 | May 2006 | Oct 2019 | Feb 2020
20231026 | BRONX | 056 | POLICE DEPARTMENT | POD50ELGE | 50TH PCT REPLACE ELEVATORS AND GENERATORS | 4 | BID AWARD AND REGISTER CONTRCT | May 2006 | Nov 2006 | Feb 2020 | Aug 2020
20231026 | BRONX | 056 | POLICE DEPARTMENT | POD50ELGE | 50TH PCT REPLACE ELEVATORS AND GENERATORS | 5 | CONSTRUCTION TO 25% | Nov 2006 | Mar 2007 | Aug 2020 | Dec 2020
20231026 | BRONX | 056 | POLICE DEPARTMENT | POD50ELGE | 50TH PCT REPLACE ELEVATORS AND GENERATORS | 6 | CONSTRUCTION TO 50% | Mar 2007 | Jul 2007 | Dec 2020 | Apr 2021
20231026 | BRONX | 056 | POLICE DEPARTMENT | POD50ELGE | 50TH PCT REPLACE ELEVATORS AND GENERATORS | 7 | CONSTRUCTION TO 75% | Jul 2007 | Nov 2007 | Apr 2021 | Aug 2023
20231026 | BRONX | 056 | POLICE DEPARTMENT | POD50ELGE | 50TH PCT REPLACE ELEVATORS AND GENERATORS | 8 | ORIGINAL EQUIP & FURNISHING | Nov 2007 | Feb 2008 | Aug 2023 | Nov 2023
20231026 | BRONX | 056 | POLICE DEPARTMENT | POD50ELGE | 50TH PCT REPLACE ELEVATORS AND GENERATORS | 9 | SUBSTANTIAL COMPLETION | Feb 2008 | Apr 2008 | Nov 2023 | Jan 2024
20231026 | BRONX | 056 | POLICE DEPARTMENT | POD50ELGE | 50TH PCT REPLACE ELEVATORS AND GENERATORS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2008 | May 2008 | Jan 2024 | Jun 2028
20231026 | BRONX | 056 | POLICE DEPARTMENT | POD52PARK | 52nd Precinct Parking Lot Renovation Upgrade | 1 | DESIGN | Dec 2019 | Jun 2020 | Dec 2020 | Jun 2021
20231026 | BRONX | 056 | POLICE DEPARTMENT | POD52PARK | 52nd Precinct Parking Lot Renovation Upgrade | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Sep 2020 | Jun 2021 | Sep 2021
20231026 | BRONX | 056 | POLICE DEPARTMENT | POD52PARK | 52nd Precinct Parking Lot Renovation Upgrade | 3 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2021 | Sep 2023
20231026 | BRONX | 056 | POLICE DEPARTMENT | POD52PARK | 52nd Precinct Parking Lot Renovation Upgrade | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Mar 2022 | Sep 2023 | Jun 2027
20231026 | BRONX | 057 | FIRE DEPARTMENT | ACEFDN202 | FDNY - PV Installation at 4 Facilities | 1 | DEVELOP SCOPE | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | BRONX | 057 | FIRE DEPARTMENT | ACEFDN202 | FDNY - PV Installation at 4 Facilities | 2 | PRELIMINARY DESIGN | Apr 2022 | Jul 2022 | Apr 2022 | Jul 2022
20231026 | BRONX | 057 | FIRE DEPARTMENT | ACEFDN202 | FDNY - PV Installation at 4 Facilities | 3 | FINAL DESIGN | Jul 2022 | Jan 2023 | Jul 2022 | Jan 2023
20231026 | BRONX | 057 | FIRE DEPARTMENT | ACEFDN202 | FDNY - PV Installation at 4 Facilities | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2023 | Apr 2023 | Jan 2023 | Apr 2023
20231026 | BRONX | 057 | FIRE DEPARTMENT | ACEFDN202 | FDNY - PV Installation at 4 Facilities | 5 | CONSTRUCTION TO 25% | Apr 2023 | Aug 2023 | Apr 2023 | Aug 2023
20231026 | BRONX | 057 | FIRE DEPARTMENT | ACEFDN202 | FDNY - PV Installation at 4 Facilities | 6 | CONSTRUCTION TO 50% | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | BRONX | 057 | FIRE DEPARTMENT | ACEFDN202 | FDNY - PV Installation at 4 Facilities | 7 | CONSTRUCTION TO 75% | Dec 2023 | Apr 2024 | Dec 2023 | Apr 2024
20231026 | BRONX | 057 | FIRE DEPARTMENT | ACEFDN202 | FDNY - PV Installation at 4 Facilities | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2024 | Jul 2024 | Apr 2024 | Jul 2024
20231026 | BRONX | 057 | FIRE DEPARTMENT | ACEFDN202 | FDNY - PV Installation at 4 Facilities | 9 | SUBSTANTIAL COMPLETION | Jul 2024 | Sep 2024 | Jul 2024 | Sep 2024
20231026 | BRONX | 057 | FIRE DEPARTMENT | ACEFDN202 | FDNY - PV Installation at 4 Facilities | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Oct 2024 | Sep 2024 | Oct 2024
20231026 | BRONX | 057 | FIRE DEPARTMENT | F175KIT42 | KITCHEN REPLACEMENT - EC42 | 1 | DESIGN | Aug 2013 | Feb 2014 | Dec 2016 | Jun 2017
20231026 | BRONX | 057 | FIRE DEPARTMENT | F175KIT42 | KITCHEN REPLACEMENT - EC42 | 2 | CONSTRUCTION | Feb 2014 | Feb 2015 | Jun 2017 | Jun 2018
20231026 | BRONX | 057 | FIRE DEPARTMENT | F175KIT42 | KITCHEN REPLACEMENT - EC42 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2015 | May 2015 | Jun 2018 | Jun 2024
20231026 | BRONX | 057 | FIRE DEPARTMENT | F175XIN82 | Exterior and Interior Renovations - EC 82 | 1 | DESIGN | Dec 2017 | Jun 2018 | Dec 2017 | Jun 2018
20231026 | BRONX | 057 | FIRE DEPARTMENT | F175XIN82 | Exterior and Interior Renovations - EC 82 | 2 | CONSTRUCTION | Jun 2018 | Jun 2019 | Jun 2018 | Jun 2019
20231026 | BRONX | 057 | FIRE DEPARTMENT | F175XIN82 | Exterior and Interior Renovations - EC 82 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2019 | Sep 2019 | Jun 2019 | Jul 2023
20231026 | BRONX | 057 | FIRE DEPARTMENT | FD175DR70 | OVERHEAD DOOR - EC 70/LADDDER 53 | 1 | CONSTRUCTION | Nov 2023 | Nov 2024 | Nov 2023 | Nov 2024
20231026 | BRONX | 057 | FIRE DEPARTMENT | FD175DR70 | OVERHEAD DOOR - EC 70/LADDDER 53 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2024 | Feb 2025 | Nov 2024 | Feb 2025
20231026 | BRONX | 057 | FIRE DEPARTMENT | FD175DRS3 | SPEED DOOR - EMS STATION 3 | 1 | CONSTRUCTION | Nov 2023 | Nov 2024 | Nov 2023 | Nov 2024
20231026 | BRONX | 057 | FIRE DEPARTMENT | FD175DRS3 | SPEED DOOR - EMS STATION 3 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2024 | Feb 2025 | Nov 2024 | Feb 2025
20231026 | BRONX | 057 | FIRE DEPARTMENT | FD175DS20 | SPEED DOOR - EMS STATION 20 | 1 | CONSTRUCTION | Nov 2023 | Nov 2024 | Nov 2023 | Nov 2024
20231026 | BRONX | 057 | FIRE DEPARTMENT | FD175DS20 | SPEED DOOR - EMS STATION 20 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2024 | Feb 2025 | Nov 2024 | Feb 2025
20231026 | BRONX | 057 | FIRE DEPARTMENT | FD175DS61 | DOOR REPLACEMENT - SQ61 | 2 | PUNCHLIST COMPLETE, JOB CLOSED | May 2019 | Jul 2019 | May 2019 | Jul 2019
20231026 | BRONX | 057 | FIRE DEPARTMENT | FD175GE97 | GENERATOR - EC 97 | 1 | DESIGN | Feb 2024 | Aug 2024 | Feb 2024 | Aug 2024
20231026 | BRONX | 057 | FIRE DEPARTMENT | FD175GE97 | GENERATOR - EC 97 | 2 | CONSTRUCTION | Aug 2024 | Aug 2025 | Aug 2024 | Aug 2025
20231026 | BRONX | 057 | FIRE DEPARTMENT | FD175GE97 | GENERATOR - EC 97 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2025 | Nov 2025 | Aug 2025 | Nov 2025
20231026 | BRONX | 057 | FIRE DEPARTMENT | FX175GE42 | Generator - EC42 | 1 | DESIGN | Oct 2019 | Apr 2020 | Oct 2019 | Apr 2020
20231026 | BRONX | 057 | FIRE DEPARTMENT | FX175GE42 | Generator - EC42 | 2 | CONSTRUCTION | Apr 2020 | Apr 2021 | Apr 2020 | Apr 2021
20231026 | BRONX | 057 | FIRE DEPARTMENT | FX175GE42 | Generator - EC42 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2021 | Jul 2021 | Apr 2021 | Jun 2024
20231026 | BRONX | 057 | FIRE DEPARTMENT | FX175WN46 | Window Replacement - EC46 | 1 | DESIGN | Nov 2018 | Apr 2019 | Nov 2018 | Apr 2019
20231026 | BRONX | 057 | FIRE DEPARTMENT | FX175WN46 | Window Replacement - EC46 | 2 | CONSTRUCTION | Apr 2019 | Apr 2020 | Apr 2019 | Apr 2020
20231026 | BRONX | 057 | FIRE DEPARTMENT | FX175WN46 | Window Replacement - EC46 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2020 | Jul 2020 | Apr 2020 | May 2030
20231026 | BRONX | 068 | ADMIN FOR CHILDREN'S SERVICES | BXELEVFAR | 1250 E229th Street Elevator and Fire Alarm Replacement | 1 | DEVELOP SCOPE | Apr 2019 | Jul 2019 | Jul 2023 | Jul 2023
20231026 | BRONX | 068 | ADMIN FOR CHILDREN'S SERVICES | BXELEVFAR | 1250 E229th Street Elevator and Fire Alarm Replacement | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Aug 2023 | Nov 2023
20231026 | BRONX | 068 | ADMIN FOR CHILDREN'S SERVICES | BXELEVFAR | 1250 E229th Street Elevator and Fire Alarm Replacement | 3 | CONSTRUCTION TO 50% | Oct 2019 | Feb 2020 | Nov 2023 | Mar 2024
20231026 | BRONX | 068 | ADMIN FOR CHILDREN'S SERVICES | BXELEVFAR | 1250 E229th Street Elevator and Fire Alarm Replacement | 4 | CONSTRUCTION TO 75% | Feb 2020 | Apr 2020 | Mar 2024 | May 2024
20231026 | BRONX | 068 | ADMIN FOR CHILDREN'S SERVICES | BXELEVFAR | 1250 E229th Street Elevator and Fire Alarm Replacement | 5 | SUBSTANTIAL COMPLETION | Apr 2020 | Jun 2020 | May 2024 | Jul 2024
20231026 | BRONX | 068 | ADMIN FOR CHILDREN'S SERVICES | BXELEVFAR | 1250 E229th Street Elevator and Fire Alarm Replacement | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2020 | Jul 2020 | Jul 2024 | Jul 2024
20231026 | BRONX | 068 | ADMIN FOR CHILDREN'S SERVICES | JJCONS | Secure Detention Facility Renovations | 1 | DESIGN | Jul 2020 | Jan 2021 | Jul 2021 | Jun 2022
20231026 | BRONX | 068 | ADMIN FOR CHILDREN'S SERVICES | JJCONS | Secure Detention Facility Renovations | 2 | CONSTRUCTION | Jan 2021 | Jan 2022 | Jul 2022 | Jun 2027
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH112FAFC | FRANKLIN'S WOMEN'S SHELTER - FACADE REHABILITATION | 1 | DESIGN | Jan 2022 | Sep 2022 | Jan 2022 | Sep 2022
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH112FAFC | FRANKLIN'S WOMEN'S SHELTER - FACADE REHABILITATION | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2022 | Mar 2023 | Sep 2022 | Mar 2023
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH112FAFC | FRANKLIN'S WOMEN'S SHELTER - FACADE REHABILITATION | 3 | CONSTRUCTION | Mar 2023 | Dec 2027 | Mar 2023 | Dec 2027
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115JEXT | UNIVERSITY AVENUE FAMILY FACAD | 1 | DESIGN | Jan 2022 | Sep 2022 | Jan 2022 | Sep 2022
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115JEXT | UNIVERSITY AVENUE FAMILY FACAD | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2022 | Mar 2023 | Sep 2022 | Mar 2023
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115JEXT | UNIVERSITY AVENUE FAMILY FACAD | 3 | CONSTRUCTION | Mar 2023 | Dec 2027 | Mar 2023 | Dec 2027
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115NLBR | JAMAICA'S WOMENN'S SHELTER - BATHROOM RECONSTRUCTION | 1 | DESIGN | Jan 2022 | Sep 2022 | Jan 2022 | Sep 2022
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115NLBR | JAMAICA'S WOMENN'S SHELTER - BATHROOM RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | Sep 2022 | Mar 2023 | Sep 2022 | Mar 2023
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115NLBR | JAMAICA'S WOMENN'S SHELTER - BATHROOM RECONSTRUCTION | 3 | CONSTRUCTION | Mar 2023 | Dec 2027 | Mar 2023 | Dec 2027
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115SNBH | SENECA HOUSES - BOILER AND HEATING | 1 | DESIGN | Jul 2022 | Mar 2023 | Jul 2022 | Mar 2023
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115SNBH | SENECA HOUSES - BOILER AND HEATING | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2023 | Sep 2023 | Mar 2023 | Sep 2023
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115SNBH | SENECA HOUSES - BOILER AND HEATING | 3 | CONSTRUCTION | Sep 2023 | Jun 2025 | Sep 2023 | Jun 2025
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115SNRF | SENECA HOUSES - ROOF REPLACEMENT AND FACADE REHABILITATION | 1 | DESIGN | Jul 2019 | Mar 2020 | Jul 2019 | Mar 2020
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115SNRF | SENECA HOUSES - ROOF REPLACEMENT AND FACADE REHABILITATION | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Sep 2020 | Mar 2020 | Sep 2020
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115SNRF | SENECA HOUSES - ROOF REPLACEMENT AND FACADE REHABILITATION | 3 | CONSTRUCTION | Sep 2020 | Jun 2025 | Sep 2020 | Jun 2025
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNBT | UNIVERSITY FAMILY KITCHEN BATHROOMS AND VENTILATION | 1 | DESIGN | Jul 2019 | Mar 2020 | Jul 2019 | Mar 2020
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNBT | UNIVERSITY FAMILY KITCHEN BATHROOMS AND VENTILATION | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Sep 2020 | Mar 2020 | Sep 2020
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNBT | UNIVERSITY FAMILY KITCHEN BATHROOMS AND VENTILATION | 3 | CONSTRUCTION | Sep 2020 | Jun 2025 | Sep 2020 | Jun 2025
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNEU | UNIVERSITY FAMILY RESIDENCE ROOF REPLACEMENT | 1 | DEVELOP SCOPE | Nov 2012 | Feb 2013 | Jan 2017 | Apr 2027
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNEU | UNIVERSITY FAMILY RESIDENCE ROOF REPLACEMENT | 2 | PRELIMINARY DESIGN | Feb 2013 | Jun 2013 | Apr 2027 | Aug 2027
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNEU | UNIVERSITY FAMILY RESIDENCE ROOF REPLACEMENT | 3 | FINAL DESIGN | Jun 2013 | Oct 2013 | Aug 2027 | Dec 2027
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNEU | UNIVERSITY FAMILY RESIDENCE ROOF REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2013 | Apr 2014 | Dec 2027 | Jun 2028
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNEU | UNIVERSITY FAMILY RESIDENCE ROOF REPLACEMENT | 5 | CONSTRUCTION TO 25% | Apr 2014 | Aug 2014 | Jun 2028 | Oct 2028
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNEU | UNIVERSITY FAMILY RESIDENCE ROOF REPLACEMENT | 6 | CONSTRUCTION TO 50% | Aug 2014 | Dec 2014 | Oct 2028 | Feb 2029
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNEU | UNIVERSITY FAMILY RESIDENCE ROOF REPLACEMENT | 7 | CONSTRUCTION TO 75% | Dec 2014 | Apr 2015 | Feb 2029 | Jun 2029
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNEU | UNIVERSITY FAMILY RESIDENCE ROOF REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2015 | Jul 2015 | Jun 2029 | Aug 2029
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNEU | UNIVERSITY FAMILY RESIDENCE ROOF REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | Jul 2015 | Aug 2015 | Aug 2029 | Oct 2029
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNEU | UNIVERSITY FAMILY RESIDENCE ROOF REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2015 | Sep 2015 | Oct 2029 | Nov 2029
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNFL | UNIVERSITY AVENUE FOUNDATION RECONSTRUCTION | 1 | DESIGN | Jul 2019 | Mar 2020 | Jul 2019 | Mar 2020
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNFL | UNIVERSITY AVENUE FOUNDATION RECONSTRUCTION | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Sep 2020 | Mar 2020 | Sep 2020
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNFL | UNIVERSITY AVENUE FOUNDATION RECONSTRUCTION | 3 | CONSTRUCTION | Sep 2020 | Jun 2025 | Sep 2020 | Jun 2025
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HHNC001 | NEW ERA VETERANS SRO- KITCHEN RENOVATION | 1 | DEVELOP SCOPE | Nov 2014 | Jan 2015 | Jan 2027 | Jun 2027
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HHNC001 | NEW ERA VETERANS SRO- KITCHEN RENOVATION | 2 | PRELIMINARY DESIGN | Jan 2015 | May 2015 | Jun 2027 | Jun 2028
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HHNC001 | NEW ERA VETERANS SRO- KITCHEN RENOVATION | 3 | FINAL DESIGN | May 2015 | Sep 2015 | Jun 2027 | Jun 2028
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HHNC001 | NEW ERA VETERANS SRO- KITCHEN RENOVATION | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2015 | Mar 2016 | Jun 2027 | Jun 2028
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HHNC001 | NEW ERA VETERANS SRO- KITCHEN RENOVATION | 5 | CONSTRUCTION TO 25% | Mar 2016 | Jul 2016 | Jun 2027 | Jun 2028
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HHNC001 | NEW ERA VETERANS SRO- KITCHEN RENOVATION | 6 | CONSTRUCTION TO 50% | Jul 2016 | Nov 2016 | Jun 2027 | Jun 2028
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HHNC001 | NEW ERA VETERANS SRO- KITCHEN RENOVATION | 7 | CONSTRUCTION TO 75% | Nov 2016 | Mar 2017 | Jun 2027 | Jun 2028
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HHNC001 | NEW ERA VETERANS SRO- KITCHEN RENOVATION | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2017 | Jun 2017 | Jun 2027 | Jun 2028
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HHNC001 | NEW ERA VETERANS SRO- KITCHEN RENOVATION | 9 | SUBSTANTIAL COMPLETION | Jun 2017 | Aug 2017 | Jun 2027 | Jun 2028
20231026 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HHNC001 | NEW ERA VETERANS SRO- KITCHEN RENOVATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2017 | Sep 2017 | Jun 2027 | Jun 2028
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C-101WEST | RI WEST PERIMETER EXTERIOR FENCING REPLACEMENT | 1 | DEVELOP SCOPE | Jan 2006 | Mar 2006 | Jul 2012 | Sep 2012
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C-101WEST | RI WEST PERIMETER EXTERIOR FENCING REPLACEMENT | 2 | PRELIMINARY DESIGN | Apr 2006 | Jul 2006 | Oct 2012 | Jan 2013
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C-101WEST | RI WEST PERIMETER EXTERIOR FENCING REPLACEMENT | 3 | FINAL DESIGN | Jul 2006 | Jan 2007 | Jan 2013 | Jul 2013
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C-101WEST | RI WEST PERIMETER EXTERIOR FENCING REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2007 | Apr 2007 | Jul 2013 | Oct 2013
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C-101WEST | RI WEST PERIMETER EXTERIOR FENCING REPLACEMENT | 5 | CONSTRUCTION TO 25% | Apr 2007 | Aug 2007 | Oct 2013 | Feb 2014
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C-101WEST | RI WEST PERIMETER EXTERIOR FENCING REPLACEMENT | 6 | CONSTRUCTION TO 50% | Aug 2007 | Dec 2007 | Feb 2014 | Jun 2014
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C-101WEST | RI WEST PERIMETER EXTERIOR FENCING REPLACEMENT | 7 | CONSTRUCTION TO 75% | Dec 2007 | Apr 2008 | Jun 2014 | Oct 2014
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C-101WEST | RI WEST PERIMETER EXTERIOR FENCING REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2008 | Jul 2008 | Oct 2014 | Jan 2015
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C-101WEST | RI WEST PERIMETER EXTERIOR FENCING REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | Jul 2008 | Sep 2008 | Jan 2015 | Mar 2015
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C-101WEST | RI WEST PERIMETER EXTERIOR FENCING REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2008 | Oct 2008 | Mar 2015 | Jul 2028
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C130PANEL | REPLACEMENT OF ELECTRICAL DISTRIBUTION PANELS- RI POWERHOUSE | 1 | DESIGN | May 2016 | Jun 2016 | May 2016 | Jun 2016
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C130PANEL | REPLACEMENT OF ELECTRICAL DISTRIBUTION PANELS- RI POWERHOUSE | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2016 | Sep 2016 | Jun 2016 | Sep 2016
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C130PANEL | REPLACEMENT OF ELECTRICAL DISTRIBUTION PANELS- RI POWERHOUSE | 3 | CONSTRUCTION | Sep 2016 | Mar 2017 | Sep 2016 | Mar 2017
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C130PANEL | REPLACEMENT OF ELECTRICAL DISTRIBUTION PANELS- RI POWERHOUSE | 4 | ORIGINAL EQUIP & FURNISHING | Mar 2017 | Jun 2017 | Mar 2017 | Jun 2017
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C130PANEL | REPLACEMENT OF ELECTRICAL DISTRIBUTION PANELS- RI POWERHOUSE | 5 | SUBSTANTIAL COMPLETION | Jun 2017 | Jul 2017 | Jun 2017 | Jul 2017
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C130PANEL | REPLACEMENT OF ELECTRICAL DISTRIBUTION PANELS- RI POWERHOUSE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2017 | Aug 2017 | Jul 2017 | Jul 2029
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FEDER | NIC Power Feder Replacement | 1 | DESIGN | Jun 2014 | Jul 2014 | Jun 2014 | Aug 2015
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FEDER | NIC Power Feder Replacement | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2014 | Oct 2014 | Aug 2015 | Oct 2015
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FEDER | NIC Power Feder Replacement | 3 | CONSTRUCTION | Oct 2014 | Apr 2015 | Oct 2015 | Apr 2016
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FEDER | NIC Power Feder Replacement | 4 | ORIGINAL EQUIP & FURNISHING | Apr 2015 | Jul 2015 | Apr 2016 | Jul 2016
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FEDER | NIC Power Feder Replacement | 5 | SUBSTANTIAL COMPLETION | Jul 2015 | Aug 2015 | Jul 2016 | Aug 2016
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FEDER | NIC Power Feder Replacement | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2015 | Sep 2015 | Aug 2016 | Sep 2028
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSPH2 | Fire Life Safety Phase II | 1 | DESIGN | Jul 2015 | May 2016 | Jul 2008 | May 2012
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSPH2 | Fire Life Safety Phase II | 2 | BID AWARD AND REGISTER CONTRCT | May 2016 | May 2017 | May 2012 | May 2013
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSPH2 | Fire Life Safety Phase II | 3 | CONSTRUCTION TO 75% | May 2017 | Mar 2018 | May 2013 | Mar 2014
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSPH2 | Fire Life Safety Phase II | 4 | SUBSTANTIAL COMPLETION | Mar 2018 | May 2018 | Mar 2014 | Jul 2022
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSPH2 | Fire Life Safety Phase II | 5 | PUNCHLIST COMPLETE, JOB CLOSED | May 2018 | Jul 2018 | Jul 2022 | Aug 2030
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSYS | FIRE SAFETY SYSTEM CONSTRUCTION | 1 | DEVELOP SCOPE | Jun 2008 | Mar 2009 | Jun 2011 | Mar 2012
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSYS | FIRE SAFETY SYSTEM CONSTRUCTION | 2 | PRELIMINARY DESIGN | Mar 2009 | Nov 2009 | Mar 2012 | Nov 2012
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSYS | FIRE SAFETY SYSTEM CONSTRUCTION | 3 | FINAL DESIGN | Nov 2009 | Nov 2010 | Nov 2012 | Nov 2013
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSYS | FIRE SAFETY SYSTEM CONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2010 | May 2011 | Nov 2013 | May 2014
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSYS | FIRE SAFETY SYSTEM CONSTRUCTION | 5 | CONSTRUCTION TO 25% | May 2011 | Jan 2012 | May 2014 | Jan 2015
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSYS | FIRE SAFETY SYSTEM CONSTRUCTION | 6 | CONSTRUCTION TO 50% | Jan 2012 | Sep 2012 | Jan 2015 | Sep 2015
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSYS | FIRE SAFETY SYSTEM CONSTRUCTION | 7 | CONSTRUCTION TO 75% | Sep 2012 | May 2013 | Sep 2015 | May 2016
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSYS | FIRE SAFETY SYSTEM CONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | May 2013 | Jan 2014 | May 2013 | Jan 2014
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSYS | FIRE SAFETY SYSTEM CONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | Jan 2014 | Jul 2014 | Jan 2014 | Jan 2014
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSYS | FIRE SAFETY SYSTEM CONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2014 | Oct 2014 | Jan 2014 | Jun 2031
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138GRFS2 | GRVC - Fire Life Safety Phase II | 1 | DESIGN | Sep 2017 | Jul 2018 | Sep 2017 | Jul 2018
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138GRFS2 | GRVC - Fire Life Safety Phase II | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Jul 2019 | Jul 2018 | Jul 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138GRFS2 | GRVC - Fire Life Safety Phase II | 3 | CONSTRUCTION TO 75% | Jul 2019 | May 2020 | Jul 2019 | May 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138GRFS2 | GRVC - Fire Life Safety Phase II | 4 | SUBSTANTIAL COMPLETION | May 2020 | Jul 2020 | May 2020 | Jul 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138GRFS2 | GRVC - Fire Life Safety Phase II | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Sep 2020 | Jul 2020 | Sep 2030
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138NCFS2 | Fire Life Safety Phase II for NIC Annex | 1 | DESIGN | Sep 2017 | Jul 2018 | Sep 2017 | Jul 2018
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138NCFS2 | Fire Life Safety Phase II for NIC Annex | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Jul 2019 | Jul 2018 | Jul 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138NCFS2 | Fire Life Safety Phase II for NIC Annex | 3 | CONSTRUCTION TO 75% | Jul 2019 | May 2020 | Jul 2019 | May 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138NCFS2 | Fire Life Safety Phase II for NIC Annex | 4 | SUBSTANTIAL COMPLETION | May 2020 | Jul 2020 | May 2020 | Jul 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138NCFS2 | Fire Life Safety Phase II for NIC Annex | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Sep 2020 | Jul 2020 | Sep 2029
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PROB5 | POST FIRE PURGE SYSTEM UPGRADE AT OBCC 500 BED ADDITION | 1 | DESIGN | May 2015 | Jun 2015 | May 2015 | Jun 2015
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PROB5 | POST FIRE PURGE SYSTEM UPGRADE AT OBCC 500 BED ADDITION | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2015 | Sep 2015 | Jun 2015 | Sep 2015
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PROB5 | POST FIRE PURGE SYSTEM UPGRADE AT OBCC 500 BED ADDITION | 3 | CONSTRUCTION | Sep 2015 | Mar 2016 | Sep 2015 | Mar 2016
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PROB5 | POST FIRE PURGE SYSTEM UPGRADE AT OBCC 500 BED ADDITION | 4 | ORIGINAL EQUIP & FURNISHING | Mar 2016 | Jun 2016 | Mar 2016 | Jun 2016
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PROB5 | POST FIRE PURGE SYSTEM UPGRADE AT OBCC 500 BED ADDITION | 5 | SUBSTANTIAL COMPLETION | Jun 2016 | Jul 2016 | Jun 2016 | Jul 2016
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PROB5 | POST FIRE PURGE SYSTEM UPGRADE AT OBCC 500 BED ADDITION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2016 | Dec 2017 | Jul 2016 | Dec 2028
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PURGR | POST FIRE PURGE SYSTEM AT GRVC | 1 | DESIGN | May 2015 | Jun 2015 | May 2015 | Jun 2015
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PURGR | POST FIRE PURGE SYSTEM AT GRVC | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2015 | Sep 2015 | Jun 2015 | Sep 2015
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PURGR | POST FIRE PURGE SYSTEM AT GRVC | 3 | CONSTRUCTION | Sep 2015 | Mar 2016 | Sep 2015 | Mar 2016
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PURGR | POST FIRE PURGE SYSTEM AT GRVC | 4 | ORIGINAL EQUIP & FURNISHING | Mar 2016 | Jun 2016 | Mar 2016 | Jun 2016
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PURGR | POST FIRE PURGE SYSTEM AT GRVC | 5 | SUBSTANTIAL COMPLETION | Jun 2016 | Jul 2016 | Jun 2016 | Jul 2016
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PURGR | POST FIRE PURGE SYSTEM AT GRVC | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2016 | Dec 2017 | Jul 2016 | Dec 2030
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PWRHS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT EXISTING POWERHOUSE | 1 | DEVELOP SCOPE | Jan 2016 | Mar 2016 | Jan 2016 | Mar 2016
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PWRHS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT EXISTING POWERHOUSE | 2 | PRELIMINARY DESIGN | Mar 2016 | Jul 2016 | Mar 2016 | Jul 2016
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PWRHS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT EXISTING POWERHOUSE | 3 | FINAL DESIGN | Jul 2016 | Jan 2017 | Jul 2016 | Jan 2017
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PWRHS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT EXISTING POWERHOUSE | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2017 | Apr 2017 | Jan 2017 | Apr 2017
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PWRHS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT EXISTING POWERHOUSE | 5 | CONSTRUCTION TO 25% | Apr 2017 | Aug 2017 | Apr 2017 | Dec 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PWRHS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT EXISTING POWERHOUSE | 6 | CONSTRUCTION TO 50% | Aug 2017 | Dec 2017 | Dec 2019 | Apr 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PWRHS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT EXISTING POWERHOUSE | 7 | CONSTRUCTION TO 75% | Dec 2017 | Apr 2018 | Apr 2020 | Aug 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PWRHS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT EXISTING POWERHOUSE | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2018 | Jul 2018 | Aug 2020 | Nov 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PWRHS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT EXISTING POWERHOUSE | 9 | SUBSTANTIAL COMPLETION | Jul 2018 | Sep 2018 | Nov 2020 | Jan 2021
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PWRHS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT EXISTING POWERHOUSE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2018 | Oct 2018 | Jan 2021 | Jul 2028
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138TRANS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT TRANSPORTATION DIV | 1 | DESIGN | Jul 2015 | May 2016 | Jan 2017 | Apr 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138TRANS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT TRANSPORTATION DIV | 2 | BID AWARD AND REGISTER CONTRCT | May 2016 | May 2017 | Apr 2019 | Sep 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138TRANS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT TRANSPORTATION DIV | 3 | CONSTRUCTION TO 75% | May 2017 | Mar 2018 | Sep 2019 | May 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138TRANS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT TRANSPORTATION DIV | 4 | SUBSTANTIAL COMPLETION | Mar 2018 | May 2018 | May 2020 | Jul 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138TRANS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT TRANSPORTATION DIV | 5 | PUNCHLIST COMPLETE, JOB CLOSED | May 2018 | Jul 2018 | Aug 2020 | Oct 2028
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACOM | ADA COMPLIANCE FOR NIC, CENTRAL VISITS, FACILITY VISIT AREAS | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2017 | Sep 2017
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACOM | ADA COMPLIANCE FOR NIC, CENTRAL VISITS, FACILITY VISIT AREAS | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2017 | Jan 2018
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACOM | ADA COMPLIANCE FOR NIC, CENTRAL VISITS, FACILITY VISIT AREAS | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jan 2018 | Jul 2018
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACOM | ADA COMPLIANCE FOR NIC, CENTRAL VISITS, FACILITY VISIT AREAS | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2018 | Oct 2018
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACOM | ADA COMPLIANCE FOR NIC, CENTRAL VISITS, FACILITY VISIT AREAS | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACOM | ADA COMPLIANCE FOR NIC, CENTRAL VISITS, FACILITY VISIT AREAS | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACOM | ADA COMPLIANCE FOR NIC, CENTRAL VISITS, FACILITY VISIT AREAS | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jun 2019 | Oct 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACOM | ADA COMPLIANCE FOR NIC, CENTRAL VISITS, FACILITY VISIT AREAS | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Oct 2019 | Jan 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACOM | ADA COMPLIANCE FOR NIC, CENTRAL VISITS, FACILITY VISIT AREAS | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jan 2020 | Mar 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACOM | ADA COMPLIANCE FOR NIC, CENTRAL VISITS, FACILITY VISIT AREAS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Mar 2020 | Jul 2028
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACVT | ADA Compliance for Central Visits | 1 | DESIGN | Sep 2017 | Jul 2018 | Sep 2017 | Jul 2018
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACVT | ADA Compliance for Central Visits | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Jul 2019 | Jul 2018 | Jul 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACVT | ADA Compliance for Central Visits | 3 | CONSTRUCTION TO 75% | Jul 2019 | May 2020 | Jul 2019 | May 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACVT | ADA Compliance for Central Visits | 4 | SUBSTANTIAL COMPLETION | May 2020 | Jul 2020 | May 2020 | Jul 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACVT | ADA Compliance for Central Visits | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Sep 2020 | Jul 2020 | Sep 2028
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADAGRV | ADA Compliance for GRVC | 1 | DESIGN | Sep 2017 | Jul 2018 | Sep 2017 | Jul 2018
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADAGRV | ADA Compliance for GRVC | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Jul 2019 | Jul 2018 | Jul 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADAGRV | ADA Compliance for GRVC | 3 | CONSTRUCTION TO 75% | Jul 2019 | May 2020 | Jul 2019 | May 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADAGRV | ADA Compliance for GRVC | 4 | SUBSTANTIAL COMPLETION | May 2020 | Jul 2020 | May 2020 | Jul 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADAGRV | ADA Compliance for GRVC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Sep 2020 | Jul 2020 | Jul 2028
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADARMS | ADA Compliance for RMSC | 1 | DESIGN | Sep 2017 | Jul 2018 | Sep 2017 | Jul 2018
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADARMS | ADA Compliance for RMSC | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Jul 2019 | Jul 2018 | Jul 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADARMS | ADA Compliance for RMSC | 3 | CONSTRUCTION TO 75% | Jul 2019 | May 2020 | Jul 2019 | May 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADARMS | ADA Compliance for RMSC | 4 | SUBSTANTIAL COMPLETION | May 2020 | Jul 2020 | May 2020 | Jul 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADARMS | ADA Compliance for RMSC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Sep 2020 | Jul 2020 | Jul 2029
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ASBEST | Asbestos Abatement and Air Monitoring - Various Facilities | 1 | DESIGN | Oct 2015 | Aug 2016 | Oct 2015 | Aug 2016
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ASBEST | Asbestos Abatement and Air Monitoring - Various Facilities | 2 | BID AWARD AND REGISTER CONTRCT | Aug 2016 | Aug 2017 | Aug 2016 | Aug 2017
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ASBEST | Asbestos Abatement and Air Monitoring - Various Facilities | 3 | CONSTRUCTION TO 75% | Aug 2017 | Apr 2019 | Aug 2017 | Apr 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ASBEST | Asbestos Abatement and Air Monitoring - Various Facilities | 4 | SUBSTANTIAL COMPLETION | Apr 2019 | Aug 2019 | Apr 2019 | Aug 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ASBEST | Asbestos Abatement and Air Monitoring - Various Facilities | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2019 | Oct 2019 | Aug 2019 | Jun 2030
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75CELLD | Electronic Cell Door Panels at All Facilities | 1 | DESIGN | Jul 2016 | May 2017 | Jul 2016 | May 2017
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75CELLD | Electronic Cell Door Panels at All Facilities | 2 | BID AWARD AND REGISTER CONTRCT | May 2017 | May 2018 | May 2017 | May 2018
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75CELLD | Electronic Cell Door Panels at All Facilities | 3 | CONSTRUCTION TO 75% | May 2018 | Mar 2019 | May 2018 | Mar 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75CELLD | Electronic Cell Door Panels at All Facilities | 4 | SUBSTANTIAL COMPLETION | Mar 2019 | May 2019 | Mar 2019 | May 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75CELLD | Electronic Cell Door Panels at All Facilities | 5 | PUNCHLIST COMPLETE, JOB CLOSED | May 2019 | Jul 2019 | May 2019 | Jul 2027
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-ELEV | ELEVATOR REHAB VARIOUS FACILITIES | 1 | DEVELOP SCOPE | Jun 2012 | Mar 2013 | Jun 2011 | Mar 2012
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-ELEV | ELEVATOR REHAB VARIOUS FACILITIES | 2 | PRELIMINARY DESIGN | Mar 2013 | Nov 2013 | Mar 2012 | Nov 2012
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-ELEV | ELEVATOR REHAB VARIOUS FACILITIES | 3 | FINAL DESIGN | Nov 2013 | Nov 2014 | Nov 2012 | Nov 2013
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-ELEV | ELEVATOR REHAB VARIOUS FACILITIES | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2014 | May 2015 | Nov 2013 | May 2014
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-ELEV | ELEVATOR REHAB VARIOUS FACILITIES | 5 | CONSTRUCTION TO 25% | May 2015 | Jan 2016 | May 2014 | Jan 2015
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-ELEV | ELEVATOR REHAB VARIOUS FACILITIES | 6 | CONSTRUCTION TO 50% | Jan 2016 | Sep 2016 | Jan 2015 | Sep 2015
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-ELEV | ELEVATOR REHAB VARIOUS FACILITIES | 7 | CONSTRUCTION TO 75% | Sep 2016 | May 2017 | Sep 2015 | May 2016
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-ELEV | ELEVATOR REHAB VARIOUS FACILITIES | 8 | ORIGINAL EQUIP & FURNISHING | May 2017 | Jan 2018 | May 2016 | Jan 2017
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-ELEV | ELEVATOR REHAB VARIOUS FACILITIES | 9 | SUBSTANTIAL COMPLETION | Jan 2018 | Jul 2018 | Jan 2017 | Jul 2017
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-ELEV | ELEVATOR REHAB VARIOUS FACILITIES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2018 | Oct 2018 | Jul 2017 | Oct 2028
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ENTNC | Modification for Facility Entries - NIC | 1 | DESIGN | Sep 2017 | Jul 2018 | Sep 2017 | Jul 2018
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ENTNC | Modification for Facility Entries - NIC | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Jul 2019 | Jul 2018 | Jul 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ENTNC | Modification for Facility Entries - NIC | 3 | CONSTRUCTION TO 75% | Jul 2019 | May 2020 | Jul 2019 | May 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ENTNC | Modification for Facility Entries - NIC | 4 | SUBSTANTIAL COMPLETION | May 2020 | Jul 2020 | May 2020 | Jul 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ENTNC | Modification for Facility Entries - NIC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Sep 2020 | Jul 2020 | Jun 2029
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ESUCP | New ESU Compound at Rikers Island | 1 | DESIGN | May 2019 | Jul 2019 | May 2019 | Jul 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ESUCP | New ESU Compound at Rikers Island | 2 | BID AWARD AND REGISTER CONTRCT | Aug 2019 | Mar 2020 | Aug 2019 | Mar 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ESUCP | New ESU Compound at Rikers Island | 3 | CONSTRUCTION TO 75% | Mar 2020 | Sep 2020 | Mar 2020 | Sep 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ESUCP | New ESU Compound at Rikers Island | 4 | SUBSTANTIAL COMPLETION | Oct 2020 | Oct 2020 | Oct 2020 | Oct 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ESUCP | New ESU Compound at Rikers Island | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2020 | Dec 2020 | Nov 2020 | Dec 2030
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75FENCE1 | FENCING RECONSTRUCTION | 1 | DEVELOP SCOPE | Aug 2005 | Nov 2005 | Aug 2010 | Nov 2010
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75FENCE1 | FENCING RECONSTRUCTION | 2 | PRELIMINARY DESIGN | Nov 2005 | Mar 2006 | Nov 2010 | Mar 2011
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75FENCE1 | FENCING RECONSTRUCTION | 3 | FINAL DESIGN | Mar 2006 | Sep 2006 | Mar 2011 | Sep 2011
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75FENCE1 | FENCING RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2006 | Dec 2006 | Sep 2011 | Dec 2011
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75FENCE1 | FENCING RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | Dec 2006 | Apr 2007 | Dec 2011 | Apr 2012
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75FENCE1 | FENCING RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | Apr 2007 | Aug 2007 | Apr 2012 | Aug 2012
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75FENCE1 | FENCING RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | Aug 2007 | Dec 2007 | Aug 2012 | Dec 2012
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75FENCE1 | FENCING RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2007 | Mar 2008 | Dec 2012 | Mar 2013
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75FENCE1 | FENCING RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | Mar 2008 | May 2008 | Mar 2013 | May 2013
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75FENCE1 | FENCING RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2008 | Jun 2008 | May 2013 | Jun 2024
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-GCELL | GANG CELL DOOR RELEASE | 1 | DEVELOP SCOPE | Jun 2011 | Sep 2011 | Jul 2018 | Jan 2024
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-GCELL | GANG CELL DOOR RELEASE | 2 | PRELIMINARY DESIGN | Sep 2011 | Jan 2012 | Jan 2024 | Jan 2024
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-GCELL | GANG CELL DOOR RELEASE | 3 | FINAL DESIGN | Jan 2012 | Jul 2012 | Jan 2024 | Jan 2024
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-GCELL | GANG CELL DOOR RELEASE | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2012 | Oct 2012 | Jan 2024 | Jan 2024
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-GCELL | GANG CELL DOOR RELEASE | 5 | CONSTRUCTION TO 25% | Oct 2012 | Feb 2013 | Jan 2024 | Jan 2024
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-GCELL | GANG CELL DOOR RELEASE | 6 | CONSTRUCTION TO 50% | Feb 2013 | Jun 2013 | Jan 2024 | Jan 2024
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-GCELL | GANG CELL DOOR RELEASE | 7 | CONSTRUCTION TO 75% | Jun 2013 | Oct 2013 | Jan 2024 | Jan 2024
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-GCELL | GANG CELL DOOR RELEASE | 8 | DESIGN | Apr 2014 | May 2014 | Jan 2024 | Jan 2024
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-GCELL | GANG CELL DOOR RELEASE | 9 | BID AWARD AND REGISTER CONTRCT | May 2014 | Aug 2014 | Jan 2024 | Jan 2024
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-GCELL | GANG CELL DOOR RELEASE | 10 | CONSTRUCTION | Aug 2014 | Feb 2015 | Jan 2024 | Jun 2030
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-GCELL | GANG CELL DOOR RELEASE | 11 | ORIGINAL EQUIP & FURNISHING | Feb 2015 | May 2015 | Jan 2024 | Jun 2030
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-GCELL | GANG CELL DOOR RELEASE | 12 | SUBSTANTIAL COMPLETION | May 2015 | Jun 2015 | Jan 2024 | Jun 2030
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-GCELL | GANG CELL DOOR RELEASE | 13 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2015 | Jul 2015 | Jan 2024 | Jun 2030
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GPARK | Construction of Parking Lot for GMDC Academy | 1 | DEVELOP SCOPE | Apr 2020 | Jun 2020 | Apr 2020 | Jun 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GPARK | Construction of Parking Lot for GMDC Academy | 2 | PRELIMINARY DESIGN | Jun 2020 | Oct 2020 | Jun 2020 | Oct 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GPARK | Construction of Parking Lot for GMDC Academy | 3 | FINAL DESIGN | Oct 2020 | Apr 2021 | Oct 2020 | Apr 2021
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GPARK | Construction of Parking Lot for GMDC Academy | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2021 | Jul 2021 | Apr 2021 | Jul 2021
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GPARK | Construction of Parking Lot for GMDC Academy | 5 | CONSTRUCTION TO 25% | Jul 2021 | Nov 2021 | Jul 2021 | Nov 2021
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GPARK | Construction of Parking Lot for GMDC Academy | 6 | CONSTRUCTION TO 50% | Nov 2021 | Mar 2022 | Nov 2021 | Mar 2022
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GPARK | Construction of Parking Lot for GMDC Academy | 7 | CONSTRUCTION TO 75% | Mar 2022 | Jul 2022 | Mar 2022 | Jul 2022
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GPARK | Construction of Parking Lot for GMDC Academy | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GPARK | Construction of Parking Lot for GMDC Academy | 9 | SUBSTANTIAL COMPLETION | Oct 2022 | Dec 2022 | Oct 2022 | Dec 2022
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GPARK | Construction of Parking Lot for GMDC Academy | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2022 | Jan 2023 | Dec 2022 | Jun 2029
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GRVCHV | GRVC HVAC Upgrades and Related Housing Area Renovations | 1 | DESIGN | Sep 2015 | Jul 2016 | Sep 2015 | Jul 2016
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GRVCHV | GRVC HVAC Upgrades and Related Housing Area Renovations | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Jul 2017 | Jul 2016 | Jul 2017
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GRVCHV | GRVC HVAC Upgrades and Related Housing Area Renovations | 3 | CONSTRUCTION TO 75% | Jul 2017 | May 2018 | Jul 2017 | May 2018
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GRVCHV | GRVC HVAC Upgrades and Related Housing Area Renovations | 4 | SUBSTANTIAL COMPLETION | May 2018 | Jul 2018 | May 2018 | Jul 2018
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GRVCHV | GRVC HVAC Upgrades and Related Housing Area Renovations | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2018 | Sep 2018 | Jul 2018 | Jul 2028
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GRVRFW | GRVC Roof Replacement, Exterior Facades, Windows, Court Yard | 1 | DESIGN | Jun 2016 | Dec 2016 | Jun 2016 | Dec 2023
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GRVRFW | GRVC Roof Replacement, Exterior Facades, Windows, Court Yard | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2016 | Dec 2017 | Jan 2024 | Dec 2024
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GRVRFW | GRVC Roof Replacement, Exterior Facades, Windows, Court Yard | 3 | CONSTRUCTION TO 75% | Dec 2017 | Dec 2020 | Dec 2024 | Dec 2025
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GRVRFW | GRVC Roof Replacement, Exterior Facades, Windows, Court Yard | 4 | SUBSTANTIAL COMPLETION | Jan 2021 | Dec 2020 | Jan 2024 | Aug 2024
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GRVRFW | GRVC Roof Replacement, Exterior Facades, Windows, Court Yard | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2021 | May 2021 | Aug 2024 | Jun 2029
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75K9UNIT | New K 9 Facility at Rikers Island | 1 | DEVELOP SCOPE | Jul 2012 | Sep 2012 | Nov 2015 | Jan 2016
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75K9UNIT | New K 9 Facility at Rikers Island | 2 | PRELIMINARY DESIGN | Sep 2012 | Jan 2013 | Jan 2016 | May 2016
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75K9UNIT | New K 9 Facility at Rikers Island | 3 | FINAL DESIGN | Jan 2013 | Jul 2013 | May 2016 | Nov 2016
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75K9UNIT | New K 9 Facility at Rikers Island | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2013 | Oct 2013 | Nov 2016 | Dec 2016
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75K9UNIT | New K 9 Facility at Rikers Island | 5 | CONSTRUCTION TO 25% | Oct 2013 | Feb 2014 | Aug 2019 | Oct 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75K9UNIT | New K 9 Facility at Rikers Island | 6 | CONSTRUCTION TO 50% | Feb 2014 | Jun 2014 | Oct 2019 | Jan 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75K9UNIT | New K 9 Facility at Rikers Island | 7 | CONSTRUCTION TO 75% | Jun 2014 | Oct 2014 | Jan 2020 | Mar 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75K9UNIT | New K 9 Facility at Rikers Island | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2014 | Jan 2015 | Mar 2020 | May 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75K9UNIT | New K 9 Facility at Rikers Island | 9 | SUBSTANTIAL COMPLETION | Jan 2015 | Mar 2015 | May 2020 | Jun 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75K9UNIT | New K 9 Facility at Rikers Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Apr 2015 | Jun 2020 | Jun 2028
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75MARINA | Rehabilitation of Existing Marina on RI | 1 | DEVELOP SCOPE | Apr 2020 | Jun 2020 | Apr 2020 | Jun 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75MARINA | Rehabilitation of Existing Marina on RI | 2 | PRELIMINARY DESIGN | Jun 2020 | Oct 2020 | Jun 2020 | Oct 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75MARINA | Rehabilitation of Existing Marina on RI | 3 | FINAL DESIGN | Oct 2020 | Apr 2021 | Oct 2020 | Apr 2021
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75MARINA | Rehabilitation of Existing Marina on RI | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2021 | Jul 2021 | Apr 2021 | Jul 2021
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75MARINA | Rehabilitation of Existing Marina on RI | 5 | CONSTRUCTION TO 25% | Jul 2021 | Nov 2021 | Jul 2021 | Nov 2021
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75MARINA | Rehabilitation of Existing Marina on RI | 6 | CONSTRUCTION TO 50% | Nov 2021 | Mar 2022 | Nov 2021 | Mar 2022
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75MARINA | Rehabilitation of Existing Marina on RI | 7 | CONSTRUCTION TO 75% | Mar 2022 | Jul 2022 | Mar 2022 | Jul 2022
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75MARINA | Rehabilitation of Existing Marina on RI | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2022 | Oct 2022 | Jul 2022 | Oct 2022
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75MARINA | Rehabilitation of Existing Marina on RI | 9 | SUBSTANTIAL COMPLETION | Oct 2022 | Dec 2022 | Oct 2022 | Dec 2022
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75MARINA | Rehabilitation of Existing Marina on RI | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2022 | Jan 2023 | Dec 2022 | Jan 2026
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-METH | Methane Detection System Replacement and Central Monitoring | 1 | DESIGN | Dec 2015 | Sep 2016 | Dec 2015 | Sep 2016
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-METH | Methane Detection System Replacement and Central Monitoring | 2 | BID AWARD AND REGISTER CONTRCT | Oct 2016 | Sep 2017 | Oct 2016 | Sep 2017
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-METH | Methane Detection System Replacement and Central Monitoring | 3 | CONSTRUCTION TO 75% | Oct 2017 | May 2019 | Oct 2017 | May 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-METH | Methane Detection System Replacement and Central Monitoring | 4 | SUBSTANTIAL COMPLETION | May 2019 | Sep 2019 | May 2019 | Sep 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-METH | Methane Detection System Replacement and Central Monitoring | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2028
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICA/C | NIC Air Conditioning -Benjamin Ventilation Order | 1 | DEVELOP SCOPE | Jun 2008 | Sep 2008 | Jun 2008 | Sep 2008
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICA/C | NIC Air Conditioning -Benjamin Ventilation Order | 2 | PRELIMINARY DESIGN | Sep 2008 | Jan 2009 | Sep 2008 | Jan 2009
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICA/C | NIC Air Conditioning -Benjamin Ventilation Order | 3 | FINAL DESIGN | Jan 2009 | Jul 2009 | Jan 2009 | Jul 2009
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICA/C | NIC Air Conditioning -Benjamin Ventilation Order | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2009 | Oct 2009 | Jul 2009 | Oct 2009
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICA/C | NIC Air Conditioning -Benjamin Ventilation Order | 5 | CONSTRUCTION TO 25% | Oct 2009 | Feb 2010 | Oct 2009 | Feb 2010
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICA/C | NIC Air Conditioning -Benjamin Ventilation Order | 6 | CONSTRUCTION TO 50% | Feb 2010 | Jun 2010 | Feb 2010 | Jun 2010
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICA/C | NIC Air Conditioning -Benjamin Ventilation Order | 7 | CONSTRUCTION TO 75% | Jun 2010 | Oct 2010 | Jun 2010 | Oct 2010
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICA/C | NIC Air Conditioning -Benjamin Ventilation Order | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2010 | Jan 2011 | Oct 2010 | Jan 2011
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICA/C | NIC Air Conditioning -Benjamin Ventilation Order | 9 | SUBSTANTIAL COMPLETION | Jan 2011 | Mar 2011 | Jan 2011 | Mar 2011
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICA/C | NIC Air Conditioning -Benjamin Ventilation Order | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2011 | Apr 2011 | Mar 2011 | Jun 2028
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICFAC | ROOF & FACADE RECONSTRUCTION FOR MAIN AND ANNEX | 1 | DESIGN | Jun 2015 | Apr 2016 | Jul 2016 | May 2017
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICFAC | ROOF & FACADE RECONSTRUCTION FOR MAIN AND ANNEX | 2 | BID AWARD AND REGISTER CONTRCT | May 2016 | Apr 2017 | Jun 2017 | Dec 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICFAC | ROOF & FACADE RECONSTRUCTION FOR MAIN AND ANNEX | 3 | CONSTRUCTION TO 75% | May 2017 | Mar 2018 | Dec 2019 | Jul 2021
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICFAC | ROOF & FACADE RECONSTRUCTION FOR MAIN AND ANNEX | 4 | SUBSTANTIAL COMPLETION | Mar 2018 | May 2018 | Jul 2021 | Nov 2021
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICFAC | ROOF & FACADE RECONSTRUCTION FOR MAIN AND ANNEX | 5 | PUNCHLIST COMPLETE, JOB CLOSED | May 2018 | Jun 2018 | Nov 2021 | Jun 2030
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75PTREAT | Water Treatment for Powerhouse | 1 | DESIGN | Sep 2018 | Jul 2019 | Sep 2018 | Jul 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75PTREAT | Water Treatment for Powerhouse | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Jul 2020 | Jul 2019 | Jul 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75PTREAT | Water Treatment for Powerhouse | 3 | CONSTRUCTION TO 75% | Jul 2020 | May 2021 | Jul 2020 | May 2021
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75PTREAT | Water Treatment for Powerhouse | 4 | SUBSTANTIAL COMPLETION | May 2021 | Jul 2021 | May 2021 | Jul 2021
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75PTREAT | Water Treatment for Powerhouse | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Sep 2021 | Jul 2021 | Jun 2028
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RDSRNG | New Modular Trailers and Classroom Renovation- Rodman's Neck | 1 | DESIGN | Oct 2018 | Aug 2019 | Oct 2018 | Aug 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RDSRNG | New Modular Trailers and Classroom Renovation- Rodman's Neck | 2 | BID AWARD AND REGISTER CONTRCT | Aug 2019 | Jul 2020 | Aug 2019 | Jul 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RDSRNG | New Modular Trailers and Classroom Renovation- Rodman's Neck | 3 | CONSTRUCTION TO 75% | Aug 2020 | Mar 2022 | Aug 2020 | Mar 2022
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RDSRNG | New Modular Trailers and Classroom Renovation- Rodman's Neck | 4 | SUBSTANTIAL COMPLETION | Mar 2022 | Jul 2022 | Mar 2022 | Jul 2022
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RDSRNG | New Modular Trailers and Classroom Renovation- Rodman's Neck | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2022 | Sep 2022 | Jul 2022 | Sep 2024
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMPWR | RMSC Power Upgrades for buildings 1,2,3,4,5,6 & 7 | 1 | DESIGN | Jun 2016 | Apr 2017 | Jun 2016 | Apr 2017
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMPWR | RMSC Power Upgrades for buildings 1,2,3,4,5,6 & 7 | 2 | BID AWARD AND REGISTER CONTRCT | May 2017 | Apr 2018 | May 2017 | Apr 2018
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMPWR | RMSC Power Upgrades for buildings 1,2,3,4,5,6 & 7 | 3 | CONSTRUCTION TO 75% | May 2018 | Dec 2019 | May 2018 | Dec 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMPWR | RMSC Power Upgrades for buildings 1,2,3,4,5,6 & 7 | 4 | SUBSTANTIAL COMPLETION | Dec 2019 | Apr 2020 | Dec 2019 | Apr 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMPWR | RMSC Power Upgrades for buildings 1,2,3,4,5,6 & 7 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2020 | Jun 2020 | Apr 2020 | Jun 2029
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSCAC | RMSC Air Conditioning-Benjamin Vent.Order | 1 | DEVELOP SCOPE | Jun 2008 | Sep 2008 | Jun 2008 | Sep 2008
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSCAC | RMSC Air Conditioning-Benjamin Vent.Order | 2 | PRELIMINARY DESIGN | Sep 2008 | Jan 2009 | Sep 2008 | Jan 2009
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSCAC | RMSC Air Conditioning-Benjamin Vent.Order | 3 | FINAL DESIGN | Jan 2009 | Jul 2009 | Jan 2009 | Jul 2009
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSCAC | RMSC Air Conditioning-Benjamin Vent.Order | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2009 | Oct 2009 | Jul 2009 | Oct 2009
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSCAC | RMSC Air Conditioning-Benjamin Vent.Order | 5 | CONSTRUCTION TO 25% | Oct 2009 | Feb 2010 | Oct 2009 | Feb 2010
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSCAC | RMSC Air Conditioning-Benjamin Vent.Order | 6 | CONSTRUCTION TO 50% | Feb 2010 | Jun 2010 | Feb 2010 | Jun 2010
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSCAC | RMSC Air Conditioning-Benjamin Vent.Order | 7 | CONSTRUCTION TO 75% | Jun 2010 | Oct 2010 | Jun 2010 | Oct 2010
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSCAC | RMSC Air Conditioning-Benjamin Vent.Order | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2010 | Jan 2011 | Oct 2010 | Jan 2011
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSCAC | RMSC Air Conditioning-Benjamin Vent.Order | 9 | SUBSTANTIAL COMPLETION | Jan 2011 | Mar 2011 | Jan 2011 | Mar 2011
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSCAC | RMSC Air Conditioning-Benjamin Vent.Order | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2011 | Apr 2011 | Mar 2011 | Dec 2011
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SEAWLL | Construction of Sea Wall and Raising of Madanici Road | 1 | DESIGN | Jun 2014 | Jul 2014 | Apr 2016 | Dec 2017
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SEAWLL | Construction of Sea Wall and Raising of Madanici Road | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2014 | Oct 2014 | Jan 2018 | May 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SEAWLL | Construction of Sea Wall and Raising of Madanici Road | 3 | CONSTRUCTION | Oct 2014 | Apr 2015 | May 2020 | Jan 2022
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SEAWLL | Construction of Sea Wall and Raising of Madanici Road | 4 | ORIGINAL EQUIP & FURNISHING | Apr 2015 | Jul 2015 | Jan 2022 | May 2022
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SEAWLL | Construction of Sea Wall and Raising of Madanici Road | 5 | SUBSTANTIAL COMPLETION | Jul 2015 | Aug 2015 | May 2022 | Jul 2030
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SEAWLL | Construction of Sea Wall and Raising of Madanici Road | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2015 | Sep 2015 | May 2022 | Jul 2030
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75STDRN | Replace Storm Water Mains and Outfalls | 1 | DESIGN | Dec 2015 | Sep 2016 | Dec 2015 | Sep 2016
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75STDRN | Replace Storm Water Mains and Outfalls | 2 | BID AWARD AND REGISTER CONTRCT | Oct 2016 | Sep 2017 | Oct 2016 | Sep 2017
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75STDRN | Replace Storm Water Mains and Outfalls | 3 | CONSTRUCTION TO 75% | Oct 2017 | May 2019 | Oct 2017 | May 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75STDRN | Replace Storm Water Mains and Outfalls | 4 | SUBSTANTIAL COMPLETION | May 2019 | Sep 2019 | May 2019 | Sep 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75STDRN | Replace Storm Water Mains and Outfalls | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Nov 2019 | Sep 2019 | Jun 2026
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75STEAM | Upgrade Steam Lines | 1 | DESIGN | Dec 2015 | Sep 2016 | Dec 2015 | Sep 2016
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75STEAM | Upgrade Steam Lines | 2 | BID AWARD AND REGISTER CONTRCT | Oct 2016 | Sep 2017 | Oct 2016 | Sep 2017
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75STEAM | Upgrade Steam Lines | 3 | CONSTRUCTION TO 75% | Oct 2017 | May 2019 | Oct 2017 | May 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75STEAM | Upgrade Steam Lines | 4 | SUBSTANTIAL COMPLETION | May 2019 | Sep 2019 | May 2019 | Sep 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75STEAM | Upgrade Steam Lines | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Nov 2019 | Sep 2019 | Jun 2028
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SUPFC | Exterior Reconstruction for Support Facilities | 1 | DEVELOP SCOPE | Aug 2015 | Oct 2015 | Aug 2015 | Oct 2015
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SUPFC | Exterior Reconstruction for Support Facilities | 2 | PRELIMINARY DESIGN | Oct 2015 | Feb 2016 | Oct 2015 | Feb 2016
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SUPFC | Exterior Reconstruction for Support Facilities | 3 | FINAL DESIGN | Feb 2016 | Aug 2016 | Feb 2016 | Aug 2016
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SUPFC | Exterior Reconstruction for Support Facilities | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2016 | Nov 2016 | Aug 2016 | Nov 2016
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SUPFC | Exterior Reconstruction for Support Facilities | 5 | CONSTRUCTION TO 25% | Nov 2016 | Mar 2017 | Nov 2016 | Mar 2017
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SUPFC | Exterior Reconstruction for Support Facilities | 6 | CONSTRUCTION TO 50% | Mar 2017 | Jul 2017 | Mar 2017 | Jul 2017
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SUPFC | Exterior Reconstruction for Support Facilities | 7 | CONSTRUCTION TO 75% | Jul 2017 | Nov 2017 | Jul 2017 | Nov 2017
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SUPFC | Exterior Reconstruction for Support Facilities | 8 | ORIGINAL EQUIP & FURNISHING | Nov 2017 | Feb 2018 | Nov 2017 | Feb 2018
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SUPFC | Exterior Reconstruction for Support Facilities | 9 | SUBSTANTIAL COMPLETION | Feb 2018 | Apr 2018 | Feb 2018 | Apr 2018
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SUPFC | Exterior Reconstruction for Support Facilities | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2018 | May 2018 | Apr 2018 | Jun 2030
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SWITCH | REPLACEMENT OF ELECTRICAL AUTOMATIC TRANSFER SWITCHES | 1 | DESIGN | May 2016 | Jun 2016 | Jul 2015 | May 2016
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SWITCH | REPLACEMENT OF ELECTRICAL AUTOMATIC TRANSFER SWITCHES | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2016 | Sep 2016 | May 2016 | May 2017
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SWITCH | REPLACEMENT OF ELECTRICAL AUTOMATIC TRANSFER SWITCHES | 3 | CONSTRUCTION | Sep 2016 | Mar 2017 | May 2017 | Mar 2018
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SWITCH | REPLACEMENT OF ELECTRICAL AUTOMATIC TRANSFER SWITCHES | 4 | ORIGINAL EQUIP & FURNISHING | Mar 2017 | Jun 2017 | Mar 2018 | May 2018
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SWITCH | REPLACEMENT OF ELECTRICAL AUTOMATIC TRANSFER SWITCHES | 5 | SUBSTANTIAL COMPLETION | Jun 2017 | Jul 2017 | May 2018 | Jul 2031
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SWITCH | REPLACEMENT OF ELECTRICAL AUTOMATIC TRANSFER SWITCHES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2017 | Aug 2017 | May 2018 | Jul 2031
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SWITCH | REPLACEMENT OF ELECTRICAL AUTOMATIC TRANSFER SWITCHES | 7 | DESIGN | Aug 2017 | Jun 2018 | May 2018 | Jul 2031
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SWITCH | REPLACEMENT OF ELECTRICAL AUTOMATIC TRANSFER SWITCHES | 8 | BID AWARD AND REGISTER CONTRCT | Jun 2018 | Jun 2019 | May 2018 | Jul 2031
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SWITCH | REPLACEMENT OF ELECTRICAL AUTOMATIC TRANSFER SWITCHES | 9 | CONSTRUCTION TO 75% | Jun 2019 | Feb 2021 | May 2018 | Jul 2031
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SWITCH | REPLACEMENT OF ELECTRICAL AUTOMATIC TRANSFER SWITCHES | 10 | SUBSTANTIAL COMPLETION | Feb 2021 | Jun 2021 | May 2018 | Jul 2031
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SWITCH | REPLACEMENT OF ELECTRICAL AUTOMATIC TRANSFER SWITCHES | 11 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2021 | Aug 2021 | May 2018 | Jul 2031
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75TMTRLR | Design and Installation of new Teams Modular Building | 1 | DEVELOP SCOPE | Apr 2019 | Jun 2019 | Apr 2019 | Jun 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75TMTRLR | Design and Installation of new Teams Modular Building | 2 | PRELIMINARY DESIGN | Jun 2019 | Oct 2019 | Jun 2019 | Oct 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75TMTRLR | Design and Installation of new Teams Modular Building | 3 | FINAL DESIGN | Oct 2019 | Dec 2019 | Oct 2019 | Dec 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75TMTRLR | Design and Installation of new Teams Modular Building | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2020 | Mar 2020 | Jan 2020 | Mar 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75TMTRLR | Design and Installation of new Teams Modular Building | 5 | CONSTRUCTION TO 25% | Mar 2020 | Jul 2020 | Mar 2020 | Jul 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75TMTRLR | Design and Installation of new Teams Modular Building | 6 | CONSTRUCTION TO 50% | Jul 2020 | Nov 2020 | Jul 2020 | Nov 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75TMTRLR | Design and Installation of new Teams Modular Building | 7 | CONSTRUCTION TO 75% | Nov 2020 | Mar 2021 | Nov 2020 | Mar 2021
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75TMTRLR | Design and Installation of new Teams Modular Building | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2021 | Jun 2021 | Mar 2021 | Jun 2021
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75TMTRLR | Design and Installation of new Teams Modular Building | 9 | SUBSTANTIAL COMPLETION | Jun 2021 | Aug 2021 | Jun 2021 | Aug 2021
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75TMTRLR | Design and Installation of new Teams Modular Building | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Sep 2021 | Aug 2021 | Jun 2031
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75VLAUND | VCBC Laundry System Installation | 1 | DESIGN | Jun 2014 | Jul 2014 | Jun 2014 | Jul 2014
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75VLAUND | VCBC Laundry System Installation | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2014 | Oct 2014 | Jul 2014 | Oct 2014
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75VLAUND | VCBC Laundry System Installation | 3 | CONSTRUCTION | Oct 2014 | Apr 2015 | Oct 2014 | Apr 2015
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75VLAUND | VCBC Laundry System Installation | 4 | ORIGINAL EQUIP & FURNISHING | Apr 2015 | Jul 2015 | Apr 2015 | Jul 2015
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75VLAUND | VCBC Laundry System Installation | 5 | SUBSTANTIAL COMPLETION | Jul 2015 | Aug 2015 | Jul 2015 | Aug 2015
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75VLAUND | VCBC Laundry System Installation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2015 | Sep 2015 | Aug 2015 | Jul 2028
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDAMKC | Hurricane Sandy - AMKC Roof Reconstruction | 1 | DEVELOP SCOPE | Dec 2012 | Feb 2013 | Dec 2012 | Feb 2013
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDAMKC | Hurricane Sandy - AMKC Roof Reconstruction | 2 | PRELIMINARY DESIGN | Mar 2013 | Jun 2013 | Mar 2013 | Jun 2013
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDAMKC | Hurricane Sandy - AMKC Roof Reconstruction | 3 | FINAL DESIGN | Jun 2013 | Dec 2013 | Jun 2013 | Dec 2013
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDAMKC | Hurricane Sandy - AMKC Roof Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | Dec 2013 | Mar 2014 | Dec 2013 | Mar 2014
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDAMKC | Hurricane Sandy - AMKC Roof Reconstruction | 5 | CONSTRUCTION TO 25% | Mar 2014 | Jul 2014 | Mar 2014 | Jul 2014
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDAMKC | Hurricane Sandy - AMKC Roof Reconstruction | 6 | CONSTRUCTION TO 50% | Jul 2014 | Nov 2014 | Jul 2014 | Nov 2014
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDAMKC | Hurricane Sandy - AMKC Roof Reconstruction | 7 | CONSTRUCTION TO 75% | Nov 2014 | Mar 2015 | Nov 2014 | Mar 2015
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDAMKC | Hurricane Sandy - AMKC Roof Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2015 | Jun 2015 | Mar 2015 | Jun 2015
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDAMKC | Hurricane Sandy - AMKC Roof Reconstruction | 9 | SUBSTANTIAL COMPLETION | Jun 2015 | Aug 2015 | Jun 2015 | Aug 2015
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDAMKC | Hurricane Sandy - AMKC Roof Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2015 | Sep 2015 | Aug 2015 | Jun 2024
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDGRVC | Hurricane Sandy - GRVC Roof Replacement due to Storm Damage | 1 | DEVELOP SCOPE | Mar 2021 | Jun 2021 | Mar 2021 | Jun 2021
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDGRVC | Hurricane Sandy - GRVC Roof Replacement due to Storm Damage | 2 | PRELIMINARY DESIGN | Jun 2021 | Oct 2021 | Jun 2021 | Oct 2021
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDGRVC | Hurricane Sandy - GRVC Roof Replacement due to Storm Damage | 3 | FINAL DESIGN | Oct 2021 | Apr 2022 | Oct 2021 | Apr 2022
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDGRVC | Hurricane Sandy - GRVC Roof Replacement due to Storm Damage | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2022 | Jul 2022 | Apr 2022 | Jul 2022
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDGRVC | Hurricane Sandy - GRVC Roof Replacement due to Storm Damage | 5 | CONSTRUCTION TO 25% | Jul 2022 | Nov 2022 | Jul 2022 | Nov 2022
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDGRVC | Hurricane Sandy - GRVC Roof Replacement due to Storm Damage | 6 | CONSTRUCTION TO 50% | Nov 2022 | Mar 2023 | Nov 2022 | Mar 2023
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDGRVC | Hurricane Sandy - GRVC Roof Replacement due to Storm Damage | 7 | CONSTRUCTION TO 75% | Mar 2023 | Jul 2023 | Mar 2023 | Jul 2023
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDGRVC | Hurricane Sandy - GRVC Roof Replacement due to Storm Damage | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDGRVC | Hurricane Sandy - GRVC Roof Replacement due to Storm Damage | 9 | SUBSTANTIAL COMPLETION | Oct 2023 | Dec 2023 | Oct 2023 | Dec 2023
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDGRVC | Hurricane Sandy - GRVC Roof Replacement due to Storm Damage | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jan 2024 | Dec 2023 | Jan 2024
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDHART | Hurricane Sandy-harts island Reconstruct from storm damage | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2013
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDHART | Hurricane Sandy-harts island Reconstruct from storm damage | 2 | PRELIMINARY DESIGN | Sep 2013 | Jan 2014 | Sep 2013 | Jan 2014
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDHART | Hurricane Sandy-harts island Reconstruct from storm damage | 3 | FINAL DESIGN | Jan 2014 | Jul 2014 | Jan 2014 | Jul 2014
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDHART | Hurricane Sandy-harts island Reconstruct from storm damage | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2014 | Oct 2014 | Jul 2014 | Oct 2014
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDHART | Hurricane Sandy-harts island Reconstruct from storm damage | 5 | CONSTRUCTION TO 25% | Oct 2014 | Feb 2015 | Oct 2014 | Feb 2015
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDHART | Hurricane Sandy-harts island Reconstruct from storm damage | 6 | CONSTRUCTION TO 50% | Feb 2015 | Jun 2015 | Feb 2015 | Jun 2015
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDHART | Hurricane Sandy-harts island Reconstruct from storm damage | 7 | CONSTRUCTION TO 75% | Jun 2015 | Oct 2015 | Jun 2015 | Oct 2015
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDHART | Hurricane Sandy-harts island Reconstruct from storm damage | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2015 | Jan 2016 | Oct 2015 | Jan 2016
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDHART | Hurricane Sandy-harts island Reconstruct from storm damage | 9 | SUBSTANTIAL COMPLETION | Jan 2016 | Mar 2016 | Jan 2016 | Mar 2016
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDHART | Hurricane Sandy-harts island Reconstruct from storm damage | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Apr 2016 | Mar 2016 | Jun 2024
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDRNDC | Hurricane Sandy - RNDC Roof Reconstruction | 1 | DEVELOP SCOPE | Jul 2013 | Oct 2013 | Jul 2013 | Oct 2013
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDRNDC | Hurricane Sandy - RNDC Roof Reconstruction | 2 | PRELIMINARY DESIGN | Oct 2013 | Feb 2014 | Oct 2013 | Feb 2014
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDRNDC | Hurricane Sandy - RNDC Roof Reconstruction | 3 | FINAL DESIGN | Feb 2014 | Aug 2014 | Feb 2014 | Aug 2014
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDRNDC | Hurricane Sandy - RNDC Roof Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2014 | Nov 2014 | Aug 2014 | Nov 2014
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDRNDC | Hurricane Sandy - RNDC Roof Reconstruction | 5 | CONSTRUCTION TO 25% | Nov 2014 | Mar 2015 | Nov 2014 | Mar 2018
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDRNDC | Hurricane Sandy - RNDC Roof Reconstruction | 6 | CONSTRUCTION TO 50% | Mar 2015 | Jul 2015 | Mar 2018 | Jul 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDRNDC | Hurricane Sandy - RNDC Roof Reconstruction | 7 | CONSTRUCTION TO 75% | Jul 2015 | Nov 2015 | Jul 2019 | Nov 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDRNDC | Hurricane Sandy - RNDC Roof Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | Nov 2015 | Feb 2016 | Nov 2019 | Feb 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDRNDC | Hurricane Sandy - RNDC Roof Reconstruction | 9 | SUBSTANTIAL COMPLETION | Feb 2016 | Apr 2016 | Feb 2020 | Apr 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDRNDC | Hurricane Sandy - RNDC Roof Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2016 | May 2016 | Apr 2020 | Jun 2024
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDSHORE | Hurricane Sandy- RI NShoreline Reconstruct from Storm Damage | 1 | DEVELOP SCOPE | Nov 2012 | Jan 2013 | Nov 2012 | Jan 2013
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDSHORE | Hurricane Sandy- RI NShoreline Reconstruct from Storm Damage | 2 | PRELIMINARY DESIGN | Jan 2013 | May 2013 | Jan 2013 | May 2013
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDSHORE | Hurricane Sandy- RI NShoreline Reconstruct from Storm Damage | 3 | FINAL DESIGN | May 2013 | Nov 2013 | May 2013 | Nov 2013
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDSHORE | Hurricane Sandy- RI NShoreline Reconstruct from Storm Damage | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2013 | Feb 2014 | Nov 2013 | Feb 2014
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDSHORE | Hurricane Sandy- RI NShoreline Reconstruct from Storm Damage | 5 | CONSTRUCTION TO 25% | Feb 2014 | Jun 2014 | Feb 2014 | Jun 2014
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDSHORE | Hurricane Sandy- RI NShoreline Reconstruct from Storm Damage | 6 | CONSTRUCTION TO 50% | Jun 2014 | Oct 2014 | Jun 2014 | Oct 2014
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDSHORE | Hurricane Sandy- RI NShoreline Reconstruct from Storm Damage | 7 | CONSTRUCTION TO 75% | Oct 2014 | Feb 2015 | Oct 2014 | Feb 2015
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDSHORE | Hurricane Sandy- RI NShoreline Reconstruct from Storm Damage | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2015 | May 2015 | Feb 2015 | May 2015
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDSHORE | Hurricane Sandy- RI NShoreline Reconstruct from Storm Damage | 9 | SUBSTANTIAL COMPLETION | May 2015 | Jul 2015 | May 2015 | Jul 2015
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDSHORE | Hurricane Sandy- RI NShoreline Reconstruct from Storm Damage | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2015 | Aug 2015 | Jul 2015 | Jun 2024
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDTRLR | Hurricane Sandy-Relocation of RI Trailers - Storm Damage | 1 | DEVELOP SCOPE | Jun 2013 | Aug 2013 | Jun 2013 | Aug 2013
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDTRLR | Hurricane Sandy-Relocation of RI Trailers - Storm Damage | 2 | PRELIMINARY DESIGN | Aug 2013 | Dec 2013 | Aug 2013 | Dec 2013
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDTRLR | Hurricane Sandy-Relocation of RI Trailers - Storm Damage | 3 | FINAL DESIGN | Dec 2013 | Jun 2014 | Dec 2013 | Jun 2014
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDTRLR | Hurricane Sandy-Relocation of RI Trailers - Storm Damage | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2014 | Sep 2014 | Jun 2014 | Sep 2019
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDTRLR | Hurricane Sandy-Relocation of RI Trailers - Storm Damage | 5 | CONSTRUCTION TO 25% | Sep 2014 | Jan 2015 | Sep 2019 | Jan 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDTRLR | Hurricane Sandy-Relocation of RI Trailers - Storm Damage | 6 | CONSTRUCTION TO 50% | Jan 2015 | May 2015 | Jan 2020 | May 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDTRLR | Hurricane Sandy-Relocation of RI Trailers - Storm Damage | 7 | CONSTRUCTION TO 75% | May 2015 | Sep 2015 | May 2020 | Sep 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDTRLR | Hurricane Sandy-Relocation of RI Trailers - Storm Damage | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2015 | Dec 2015 | Sep 2020 | Dec 2020
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDTRLR | Hurricane Sandy-Relocation of RI Trailers - Storm Damage | 9 | SUBSTANTIAL COMPLETION | Dec 2015 | Feb 2016 | Dec 2020 | Feb 2021
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDTRLR | Hurricane Sandy-Relocation of RI Trailers - Storm Damage | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2016 | Mar 2016 | Feb 2021 | Jun 2024
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDVCBC | Hurricane Sandy - VCBC Reconstruction Due To Storm Damage | 1 | DEVELOP SCOPE | Nov 2012 | Jan 2013 | Nov 2012 | Jan 2013
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDVCBC | Hurricane Sandy - VCBC Reconstruction Due To Storm Damage | 2 | PRELIMINARY DESIGN | Jan 2013 | May 2013 | Jan 2013 | May 2013
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDVCBC | Hurricane Sandy - VCBC Reconstruction Due To Storm Damage | 3 | FINAL DESIGN | May 2013 | Nov 2013 | May 2013 | Nov 2013
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDVCBC | Hurricane Sandy - VCBC Reconstruction Due To Storm Damage | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2013 | Feb 2014 | Nov 2013 | Feb 2014
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDVCBC | Hurricane Sandy - VCBC Reconstruction Due To Storm Damage | 5 | CONSTRUCTION TO 25% | Feb 2014 | Jun 2014 | Feb 2014 | Jun 2014
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDVCBC | Hurricane Sandy - VCBC Reconstruction Due To Storm Damage | 6 | CONSTRUCTION TO 50% | Jun 2014 | Oct 2014 | Jun 2014 | Oct 2014
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDVCBC | Hurricane Sandy - VCBC Reconstruction Due To Storm Damage | 7 | CONSTRUCTION TO 75% | Oct 2014 | Feb 2015 | Oct 2014 | Feb 2015
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDVCBC | Hurricane Sandy - VCBC Reconstruction Due To Storm Damage | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2015 | May 2015 | Feb 2015 | May 2015
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDVCBC | Hurricane Sandy - VCBC Reconstruction Due To Storm Damage | 9 | SUBSTANTIAL COMPLETION | May 2015 | Jul 2015 | May 2015 | Jul 2015
20231026 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDVCBC | Hurricane Sandy - VCBC Reconstruction Due To Storm Damage | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2015 | Aug 2015 | Jul 2015 | Jun 2026
20231026 | BRONX | 096 | HUMAN RESOURCES ADMINISTRATION | HR25TREMC | 555 E Tremont Construction | 1 | DESIGN | Oct 2021 | Mar 2022
20231026 | BRONX | 096 | HUMAN RESOURCES ADMINISTRATION | HR25TREMC | 555 E Tremont Construction | 2 | CONSTRUCTION | Mar 2022 | Sep 2022
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176AVRY | WCS - Bronx Zoo - New Aviary at the Pheasantry | 1 | DEVELOP SCOPE | Jun 2028 | Sep 2028 | Jun 2028 | Sep 2028
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176AVRY | WCS - Bronx Zoo - New Aviary at the Pheasantry | 2 | PRELIMINARY DESIGN | Sep 2028 | Jan 2029 | Sep 2028 | Jan 2029
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176AVRY | WCS - Bronx Zoo - New Aviary at the Pheasantry | 3 | FINAL DESIGN | Jan 2029 | Jul 2029 | Jan 2029 | Jul 2029
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176AVRY | WCS - Bronx Zoo - New Aviary at the Pheasantry | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2029 | Oct 2029 | Jul 2029 | Oct 2029
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176AVRY | WCS - Bronx Zoo - New Aviary at the Pheasantry | 5 | CONSTRUCTION TO 25% | Oct 2029 | Feb 2030 | Oct 2029 | Feb 2030
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176AVRY | WCS - Bronx Zoo - New Aviary at the Pheasantry | 6 | CONSTRUCTION TO 50% | Feb 2030 | Jun 2030 | Feb 2030 | Jun 2030
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176AVRY | WCS - Bronx Zoo - New Aviary at the Pheasantry | 7 | CONSTRUCTION TO 75% | Jun 2030 | Oct 2030 | Jun 2030 | Oct 2030
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176AVRY | WCS - Bronx Zoo - New Aviary at the Pheasantry | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2030 | Jan 2031 | Oct 2030 | Jan 2031
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176AVRY | WCS - Bronx Zoo - New Aviary at the Pheasantry | 9 | SUBSTANTIAL COMPLETION | Jan 2031 | Mar 2031 | Jan 2031 | Mar 2031
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176AVRY | WCS - Bronx Zoo - New Aviary at the Pheasantry | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2031 | Apr 2031 | Mar 2031 | Apr 2031
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR1 | WCS - BZ World of Birds Bldg. Boiler/Chiller/AHU Replacement | 1 | DEVELOP SCOPE | Jun 2026 | Sep 2026 | Jun 2026 | Sep 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR1 | WCS - BZ World of Birds Bldg. Boiler/Chiller/AHU Replacement | 2 | PRELIMINARY DESIGN | Sep 2026 | Jan 2027 | Sep 2026 | Jan 2027
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR1 | WCS - BZ World of Birds Bldg. Boiler/Chiller/AHU Replacement | 3 | FINAL DESIGN | Jan 2027 | Jul 2027 | Jan 2027 | Jul 2027
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR1 | WCS - BZ World of Birds Bldg. Boiler/Chiller/AHU Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2027 | Oct 2027 | Jul 2027 | Oct 2027
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR1 | WCS - BZ World of Birds Bldg. Boiler/Chiller/AHU Replacement | 5 | CONSTRUCTION TO 25% | Oct 2027 | Feb 2028 | Oct 2027 | Feb 2028
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR1 | WCS - BZ World of Birds Bldg. Boiler/Chiller/AHU Replacement | 6 | CONSTRUCTION TO 50% | Feb 2028 | Jun 2028 | Feb 2028 | Jun 2028
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR1 | WCS - BZ World of Birds Bldg. Boiler/Chiller/AHU Replacement | 7 | CONSTRUCTION TO 75% | Jun 2028 | Oct 2028 | Jun 2028 | Oct 2028
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR1 | WCS - BZ World of Birds Bldg. Boiler/Chiller/AHU Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2028 | Jan 2029 | Oct 2028 | Jan 2029
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR1 | WCS - BZ World of Birds Bldg. Boiler/Chiller/AHU Replacement | 9 | SUBSTANTIAL COMPLETION | Jan 2029 | Mar 2029 | Jan 2029 | Mar 2029
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR1 | WCS - BZ World of Birds Bldg. Boiler/Chiller/AHU Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2029 | Apr 2029 | Mar 2029 | Apr 2029
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR2 | WCS - BZ Carter Giraffe Bldg. Boiler Replacement | 1 | DEVELOP SCOPE | Jun 2026 | Sep 2026 | Jun 2026 | Sep 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR2 | WCS - BZ Carter Giraffe Bldg. Boiler Replacement | 2 | PRELIMINARY DESIGN | Sep 2026 | Jan 2027 | Sep 2026 | Jan 2027
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR2 | WCS - BZ Carter Giraffe Bldg. Boiler Replacement | 3 | FINAL DESIGN | Jan 2027 | Jul 2027 | Jan 2027 | Jul 2027
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR2 | WCS - BZ Carter Giraffe Bldg. Boiler Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2027 | Oct 2027 | Jul 2027 | Oct 2027
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR2 | WCS - BZ Carter Giraffe Bldg. Boiler Replacement | 5 | CONSTRUCTION TO 25% | Oct 2027 | Feb 2028 | Oct 2027 | Feb 2028
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR2 | WCS - BZ Carter Giraffe Bldg. Boiler Replacement | 6 | CONSTRUCTION TO 50% | Feb 2028 | Jun 2028 | Feb 2028 | Jun 2028
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR2 | WCS - BZ Carter Giraffe Bldg. Boiler Replacement | 7 | CONSTRUCTION TO 75% | Jun 2028 | Oct 2028 | Jun 2028 | Oct 2028
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR2 | WCS - BZ Carter Giraffe Bldg. Boiler Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2028 | Jan 2029 | Oct 2028 | Jan 2029
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR2 | WCS - BZ Carter Giraffe Bldg. Boiler Replacement | 9 | SUBSTANTIAL COMPLETION | Jan 2029 | Mar 2029 | Jan 2029 | Mar 2029
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR2 | WCS - BZ Carter Giraffe Bldg. Boiler Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2029 | Apr 2029 | Mar 2029 | Apr 2029
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR3 | WCS - BZ Shelter Building - Boiler Replacement | 1 | DEVELOP SCOPE | Jun 2026 | Sep 2026 | Jun 2024 | Sep 2024
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR3 | WCS - BZ Shelter Building - Boiler Replacement | 2 | PRELIMINARY DESIGN | Sep 2026 | Jan 2027 | Sep 2024 | Jan 2025
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR3 | WCS - BZ Shelter Building - Boiler Replacement | 3 | FINAL DESIGN | Jan 2027 | Jul 2027 | Jan 2025 | Jul 2025
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR3 | WCS - BZ Shelter Building - Boiler Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2027 | Oct 2027 | Jul 2025 | Oct 2025
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR3 | WCS - BZ Shelter Building - Boiler Replacement | 5 | CONSTRUCTION TO 25% | Oct 2027 | Feb 2028 | Oct 2025 | Feb 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR3 | WCS - BZ Shelter Building - Boiler Replacement | 6 | CONSTRUCTION TO 50% | Feb 2028 | Jun 2028 | Feb 2026 | Jun 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR3 | WCS - BZ Shelter Building - Boiler Replacement | 7 | CONSTRUCTION TO 75% | Jun 2028 | Oct 2028 | Jun 2026 | Oct 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR3 | WCS - BZ Shelter Building - Boiler Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2028 | Jan 2029 | Oct 2026 | Jan 2027
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR3 | WCS - BZ Shelter Building - Boiler Replacement | 9 | SUBSTANTIAL COMPLETION | Jan 2029 | Mar 2029 | Jan 2027 | Mar 2027
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR3 | WCS - BZ Shelter Building - Boiler Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2029 | Apr 2029 | Mar 2027 | Apr 2027
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR4 | WCS - BZ Jungle World Building - Boiler Replacement | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR4 | WCS - BZ Jungle World Building - Boiler Replacement | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR4 | WCS - BZ Jungle World Building - Boiler Replacement | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR4 | WCS - BZ Jungle World Building - Boiler Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR4 | WCS - BZ Jungle World Building - Boiler Replacement | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR4 | WCS - BZ Jungle World Building - Boiler Replacement | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR4 | WCS - BZ Jungle World Building - Boiler Replacement | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR4 | WCS - BZ Jungle World Building - Boiler Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR4 | WCS - BZ Jungle World Building - Boiler Replacement | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR4 | WCS - BZ Jungle World Building - Boiler Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR5 | WCS - BZ Ostrich-Mouse House Building - Boiler Replacement | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR5 | WCS - BZ Ostrich-Mouse House Building - Boiler Replacement | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR5 | WCS - BZ Ostrich-Mouse House Building - Boiler Replacement | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR5 | WCS - BZ Ostrich-Mouse House Building - Boiler Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR5 | WCS - BZ Ostrich-Mouse House Building - Boiler Replacement | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR5 | WCS - BZ Ostrich-Mouse House Building - Boiler Replacement | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR5 | WCS - BZ Ostrich-Mouse House Building - Boiler Replacement | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR5 | WCS - BZ Ostrich-Mouse House Building - Boiler Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR5 | WCS - BZ Ostrich-Mouse House Building - Boiler Replacement | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR5 | WCS - BZ Ostrich-Mouse House Building - Boiler Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR6 | WCS - BZ African Plains Building - Boiler Replacement | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR6 | WCS - BZ African Plains Building - Boiler Replacement | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR6 | WCS - BZ African Plains Building - Boiler Replacement | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR6 | WCS - BZ African Plains Building - Boiler Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR6 | WCS - BZ African Plains Building - Boiler Replacement | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR6 | WCS - BZ African Plains Building - Boiler Replacement | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR6 | WCS - BZ African Plains Building - Boiler Replacement | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR6 | WCS - BZ African Plains Building - Boiler Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR6 | WCS - BZ African Plains Building - Boiler Replacement | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR6 | WCS - BZ African Plains Building - Boiler Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR7 | WCS - BZ Pheasant Aviary Building - Boiler Replacement | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR7 | WCS - BZ Pheasant Aviary Building - Boiler Replacement | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR7 | WCS - BZ Pheasant Aviary Building - Boiler Replacement | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR7 | WCS - BZ Pheasant Aviary Building - Boiler Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR7 | WCS - BZ Pheasant Aviary Building - Boiler Replacement | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR7 | WCS - BZ Pheasant Aviary Building - Boiler Replacement | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR7 | WCS - BZ Pheasant Aviary Building - Boiler Replacement | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR7 | WCS - BZ Pheasant Aviary Building - Boiler Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR7 | WCS - BZ Pheasant Aviary Building - Boiler Replacement | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176BLR7 | WCS - BZ Pheasant Aviary Building - Boiler Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176CES2 | WCS - Bronx Zoo - Switch Gear Phase 2 | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2025 | Sep 2025
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176CES2 | WCS - Bronx Zoo - Switch Gear Phase 2 | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2025 | Jan 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176CES2 | WCS - Bronx Zoo - Switch Gear Phase 2 | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2026 | Jul 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176CES2 | WCS - Bronx Zoo - Switch Gear Phase 2 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2026 | Oct 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176CES2 | WCS - Bronx Zoo - Switch Gear Phase 2 | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2026 | Feb 2027
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176CES2 | WCS - Bronx Zoo - Switch Gear Phase 2 | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2027 | Jun 2027
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176CES2 | WCS - Bronx Zoo - Switch Gear Phase 2 | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2027 | Oct 2027
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176CES2 | WCS - Bronx Zoo - Switch Gear Phase 2 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2027 | Jan 2028
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176CES2 | WCS - Bronx Zoo - Switch Gear Phase 2 | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2028 | Mar 2028
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176CES2 | WCS - Bronx Zoo - Switch Gear Phase 2 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2028 | Apr 2028
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176GELA | WCS - Bronx Zoo - Gelada Exhibit | 1 | DEVELOP SCOPE | Mar 2019 | Sep 2019 | Jun 2023 | Dec 2023
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176GELA | WCS - Bronx Zoo - Gelada Exhibit | 2 | PRELIMINARY DESIGN | Sep 2019 | Dec 2019 | Jan 2024 | Apr 2024
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176GELA | WCS - Bronx Zoo - Gelada Exhibit | 3 | FINAL DESIGN | Dec 2019 | Jun 2020 | Apr 2024 | Oct 2024
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176GELA | WCS - Bronx Zoo - Gelada Exhibit | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Sep 2020 | Oct 2024 | Jan 2025
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176GELA | WCS - Bronx Zoo - Gelada Exhibit | 5 | CONSTRUCTION TO 25% | Sep 2020 | Jan 2021 | Jan 2025 | May 2025
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176GELA | WCS - Bronx Zoo - Gelada Exhibit | 6 | CONSTRUCTION TO 50% | Jan 2021 | May 2021 | May 2025 | Sep 2025
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176GELA | WCS - Bronx Zoo - Gelada Exhibit | 7 | CONSTRUCTION TO 75% | May 2021 | Sep 2021 | Sep 2025 | Jan 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176GELA | WCS - Bronx Zoo - Gelada Exhibit | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Dec 2021 | Jan 2026 | Apr 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176GELA | WCS - Bronx Zoo - Gelada Exhibit | 9 | SUBSTANTIAL COMPLETION | Dec 2021 | Feb 2022 | Apr 2026 | Jun 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176GELA | WCS - Bronx Zoo - Gelada Exhibit | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2022 | Mar 2022 | Jun 2026 | Jul 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176MONK | WCS - Bronx Zoo - World of Primates Exhibit | 1 | DEVELOP SCOPE | Jun 2027 | Sep 2027 | Jun 2028 | Sep 2028
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176MONK | WCS - Bronx Zoo - World of Primates Exhibit | 2 | PRELIMINARY DESIGN | Sep 2027 | Jan 2028 | Sep 2028 | Jan 2029
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176MONK | WCS - Bronx Zoo - World of Primates Exhibit | 3 | FINAL DESIGN | Jan 2028 | Jul 2028 | Jan 2029 | Jul 2029
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176MONK | WCS - Bronx Zoo - World of Primates Exhibit | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2028 | Oct 2028 | Jul 2029 | Oct 2029
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176MONK | WCS - Bronx Zoo - World of Primates Exhibit | 5 | CONSTRUCTION TO 25% | Oct 2028 | Feb 2029 | Oct 2029 | Feb 2030
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176MONK | WCS - Bronx Zoo - World of Primates Exhibit | 6 | CONSTRUCTION TO 50% | Feb 2029 | Jun 2029 | Feb 2030 | Jun 2030
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176MONK | WCS - Bronx Zoo - World of Primates Exhibit | 7 | CONSTRUCTION TO 75% | Jun 2029 | Oct 2029 | Jun 2030 | Oct 2030
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176MONK | WCS - Bronx Zoo - World of Primates Exhibit | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2029 | Jan 2030 | Oct 2030 | Jan 2031
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176MONK | WCS - Bronx Zoo - World of Primates Exhibit | 9 | SUBSTANTIAL COMPLETION | Jan 2030 | Mar 2030 | Jan 2031 | Mar 2031
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176MONK | WCS - Bronx Zoo - World of Primates Exhibit | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2030 | Apr 2030 | Mar 2031 | Apr 2031
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176-REP | WCS - Bronx Zoo - Reptile House Facade Restoration | 1 | CONSTRUCTION | Sep 2013 | Sep 2014 | Jun 2025 | Jul 2027
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176-REP | WCS - Bronx Zoo - Reptile House Facade Restoration | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2014 | Sep 2015 | Sep 2013 | Sep 2014
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176-REP | WCS - Bronx Zoo - Reptile House Facade Restoration | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2014 | Sep 2015 | Sep 2014 | Sep 2015
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176WILD | WCS - Bronx Zoo - Wildlife Exhibit Center | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176WILD | WCS - Bronx Zoo - Wildlife Exhibit Center | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176WILD | WCS - Bronx Zoo - Wildlife Exhibit Center | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176WILD | WCS - Bronx Zoo - Wildlife Exhibit Center | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176WILD | WCS - Bronx Zoo - Wildlife Exhibit Center | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176WILD | WCS - Bronx Zoo - Wildlife Exhibit Center | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176WILD | WCS - Bronx Zoo - Wildlife Exhibit Center | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176WILD | WCS - Bronx Zoo - Wildlife Exhibit Center | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176WILD | WCS - Bronx Zoo - Wildlife Exhibit Center | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176WILD | WCS - Bronx Zoo - Wildlife Exhibit Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2025
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV205GLIB | NYBG - Green Library/Energy Reduction Project | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV205GLIB | NYBG - Green Library/Energy Reduction Project | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV205GLIB | NYBG - Green Library/Energy Reduction Project | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV205GLIB | NYBG - Green Library/Energy Reduction Project | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV205GLIB | NYBG - Green Library/Energy Reduction Project | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV205GLIB | NYBG - Green Library/Energy Reduction Project | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV205GLIB | NYBG - Green Library/Energy Reduction Project | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV205GLIB | NYBG - Green Library/Energy Reduction Project | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV205GLIB | NYBG - Green Library/Energy Reduction Project | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV205GLIB | NYBG - Green Library/Energy Reduction Project | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV293-ADD | BCHS - ADA Accessible Addition | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2028 | Sep 2028
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV293-ADD | BCHS - ADA Accessible Addition | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2028 | Jan 2029
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV293-ADD | BCHS - ADA Accessible Addition | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2029 | Jul 2029
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV293-ADD | BCHS - ADA Accessible Addition | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2029 | Oct 2029
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV293-ADD | BCHS - ADA Accessible Addition | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2029 | Feb 2030
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV293-ADD | BCHS - ADA Accessible Addition | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2030 | Jun 2030
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV293-ADD | BCHS - ADA Accessible Addition | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2030 | Oct 2030
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV293-ADD | BCHS - ADA Accessible Addition | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2030 | Jan 2031
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV293-ADD | BCHS - ADA Accessible Addition | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2031 | Mar 2031
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV293-ADD | BCHS - ADA Accessible Addition | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2031 | Apr 2031
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV293-EXT | BCHS - IT Tech Upgrade | 1 | CONSTRUCTION | Sep 2023 | Sep 2024
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV293-EXT | BCHS - IT Tech Upgrade | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-ARM | Wave Hill (WH) - Armor Hall AHU Replacement Project | 1 | DEVELOP SCOPE | Jun 2027 | Sep 2027 | Jun 2027 | Sep 2027
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-ARM | Wave Hill (WH) - Armor Hall AHU Replacement Project | 2 | PRELIMINARY DESIGN | Sep 2027 | Jan 2028 | Sep 2027 | Jan 2028
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-ARM | Wave Hill (WH) - Armor Hall AHU Replacement Project | 3 | FINAL DESIGN | Jan 2028 | Jul 2028 | Jan 2028 | Jul 2028
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-ARM | Wave Hill (WH) - Armor Hall AHU Replacement Project | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2028 | Oct 2028 | Jul 2028 | Oct 2028
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-ARM | Wave Hill (WH) - Armor Hall AHU Replacement Project | 5 | CONSTRUCTION TO 25% | Oct 2028 | Feb 2029 | Oct 2028 | Feb 2029
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-ARM | Wave Hill (WH) - Armor Hall AHU Replacement Project | 6 | CONSTRUCTION TO 50% | Feb 2029 | Jun 2029 | Feb 2029 | Jun 2029
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-ARM | Wave Hill (WH) - Armor Hall AHU Replacement Project | 7 | CONSTRUCTION TO 75% | Jun 2029 | Oct 2029 | Jun 2029 | Oct 2029
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-ARM | Wave Hill (WH) - Armor Hall AHU Replacement Project | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2029 | Jan 2030 | Oct 2029 | Jan 2030
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-ARM | Wave Hill (WH) - Armor Hall AHU Replacement Project | 9 | SUBSTANTIAL COMPLETION | Jan 2030 | Mar 2030 | Jan 2030 | Mar 2030
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-ARM | Wave Hill (WH) - Armor Hall AHU Replacement Project | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2030 | Apr 2030 | Mar 2030 | Apr 2030
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464GLYN | WH - Wave Hill - Glyndor Hse. Boiler/Armor Hall AHU | 1 | DEVELOP SCOPE | May 2016 | Aug 2016 | Jun 2024 | Sep 2024
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464GLYN | WH - Wave Hill - Glyndor Hse. Boiler/Armor Hall AHU | 2 | PRELIMINARY DESIGN | Aug 2016 | Dec 2016 | Sep 2024 | Jan 2025
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464GLYN | WH - Wave Hill - Glyndor Hse. Boiler/Armor Hall AHU | 3 | FINAL DESIGN | Dec 2016 | Jun 2017 | Jan 2025 | Jul 2025
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464GLYN | WH - Wave Hill - Glyndor Hse. Boiler/Armor Hall AHU | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2017 | Sep 2017 | Jul 2025 | Oct 2025
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464GLYN | WH - Wave Hill - Glyndor Hse. Boiler/Armor Hall AHU | 5 | CONSTRUCTION TO 25% | Sep 2017 | Jan 2018 | Oct 2025 | Feb 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464GLYN | WH - Wave Hill - Glyndor Hse. Boiler/Armor Hall AHU | 6 | CONSTRUCTION TO 50% | Jan 2018 | May 2018 | Feb 2026 | Jun 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464GLYN | WH - Wave Hill - Glyndor Hse. Boiler/Armor Hall AHU | 7 | CONSTRUCTION TO 75% | May 2018 | Sep 2018 | Jun 2026 | Oct 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464GLYN | WH - Wave Hill - Glyndor Hse. Boiler/Armor Hall AHU | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2018 | Dec 2018 | Oct 2026 | Jan 2027
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464GLYN | WH - Wave Hill - Glyndor Hse. Boiler/Armor Hall AHU | 9 | SUBSTANTIAL COMPLETION | Dec 2018 | Feb 2019 | Jan 2027 | Mar 2027
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464GLYN | WH - Wave Hill - Glyndor Hse. Boiler/Armor Hall AHU | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2019 | Mar 2019 | Mar 2027 | Apr 2027
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-PAV | WH - Wave Hill - Woodland Pavilion | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2026 | Sep 2026
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-PAV | WH - Wave Hill - Woodland Pavilion | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2026 | Jan 2027
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-PAV | WH - Wave Hill - Woodland Pavilion | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2027 | Jul 2027
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-PAV | WH - Wave Hill - Woodland Pavilion | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2027 | Oct 2027
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-PAV | WH - Wave Hill - Woodland Pavilion | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2027 | Feb 2028
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-PAV | WH - Wave Hill - Woodland Pavilion | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2028 | Jun 2028
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-PAV | WH - Wave Hill - Woodland Pavilion | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2028 | Oct 2028
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-PAV | WH - Wave Hill - Woodland Pavilion | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2028 | Jan 2029
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-PAV | WH - Wave Hill - Woodland Pavilion | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2029 | Mar 2029
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-PAV | WH - Wave Hill - Woodland Pavilion | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2029 | Apr 2029
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464QUAD | WH - Elevated Walkway: Upper Garden Access | 1 | DEVELOP SCOPE | Jun 2027 | Sep 2027 | Jun 2027 | Sep 2027
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464QUAD | WH - Elevated Walkway: Upper Garden Access | 2 | PRELIMINARY DESIGN | Sep 2027 | Jan 2028 | Sep 2027 | Jan 2028
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464QUAD | WH - Elevated Walkway: Upper Garden Access | 3 | FINAL DESIGN | Jan 2028 | Jul 2028 | Jan 2028 | Jul 2028
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464QUAD | WH - Elevated Walkway: Upper Garden Access | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2028 | Oct 2028 | Jul 2028 | Oct 2028
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464QUAD | WH - Elevated Walkway: Upper Garden Access | 5 | CONSTRUCTION TO 25% | Oct 2028 | Feb 2029 | Oct 2028 | Feb 2029
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464QUAD | WH - Elevated Walkway: Upper Garden Access | 6 | CONSTRUCTION TO 50% | Feb 2029 | Jun 2029 | Feb 2029 | Jun 2029
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464QUAD | WH - Elevated Walkway: Upper Garden Access | 7 | CONSTRUCTION TO 75% | Jun 2029 | Oct 2029 | Jun 2029 | Oct 2029
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464QUAD | WH - Elevated Walkway: Upper Garden Access | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2029 | Jan 2030 | Oct 2029 | Jan 2030
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464QUAD | WH - Elevated Walkway: Upper Garden Access | 9 | SUBSTANTIAL COMPLETION | Jan 2030 | Mar 2030 | Jan 2030 | Mar 2030
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464QUAD | WH - Elevated Walkway: Upper Garden Access | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2030 | Apr 2030 | Mar 2030 | Apr 2030
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464SITE | WH - Wave Hill - Sitewide Pathway Replacement | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Jun 2028 | Sep 2028
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464SITE | WH - Wave Hill - Sitewide Pathway Replacement | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Sep 2028 | Jan 2029
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464SITE | WH - Wave Hill - Sitewide Pathway Replacement | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Jan 2029 | Jul 2029
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464SITE | WH - Wave Hill - Sitewide Pathway Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Jul 2029 | Oct 2029
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464SITE | WH - Wave Hill - Sitewide Pathway Replacement | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Oct 2029 | Feb 2030
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464SITE | WH - Wave Hill - Sitewide Pathway Replacement | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Feb 2030 | Jun 2030
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464SITE | WH - Wave Hill - Sitewide Pathway Replacement | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Jun 2030 | Oct 2030
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464SITE | WH - Wave Hill - Sitewide Pathway Replacement | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | Oct 2030 | Jan 2031
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464SITE | WH - Wave Hill - Sitewide Pathway Replacement | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Jan 2031 | Mar 2031
20231026 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464SITE | WH - Wave Hill - Sitewide Pathway Replacement | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Mar 2031 | Apr 2031
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | 600FCDRNV | 600 FCD 2nd Fl Renovation | 1 | DESIGN | Jul 2022 | Jul 2022 | Jul 2022 | Jul 2022
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | 600FCDRNV | 600 FCD 2nd Fl Renovation | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Aug 2022 | Jul 2022 | Aug 2022
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | 600FCDRNV | 600 FCD 2nd Fl Renovation | 3 | CONSTRUCTION | Aug 2022 | Sep 2022 | Aug 2022 | Sep 2022
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | 600FCDRNV | 600 FCD 2nd Fl Renovation | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Sep 2022 | Sep 2022 | Sep 2022
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | 600FCDRNV | 600 FCD 2nd Fl Renovation | 5 | SUBSTANTIAL COMPLETION | Sep 2022 | Oct 2022 | Sep 2022 | Oct 2022
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | 600FCDRNV | 600 FCD 2nd Fl Renovation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2022 | Jun 2025 | Oct 2022 | Jun 2025
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | ARTHURAVE | ARTHUR AVENUE MARKET | 1 | DESIGN | Jul 2019 | Jul 2019 | Jul 2019 | Jul 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | ARTHURAVE | ARTHUR AVENUE MARKET | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jul 2019 | Aug 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | ARTHURAVE | ARTHUR AVENUE MARKET | 3 | CONSTRUCTION | Aug 2019 | Sep 2019 | Aug 2019 | Sep 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | ARTHURAVE | ARTHUR AVENUE MARKET | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Sep 2019 | Sep 2019 | Sep 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | ARTHURAVE | ARTHUR AVENUE MARKET | 5 | SUBSTANTIAL COMPLETION | Sep 2019 | Oct 2022 | Sep 2019 | Oct 2022
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | ARTHURAVE | ARTHUR AVENUE MARKET | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2022 | Oct 2022 | Oct 2022 | Jun 2027
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | BATHGATE | Bathgate Campus Improvements | 1 | DESIGN | Jul 2022 | Jul 2022 | Jul 2023 | Jul 2023
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | BATHGATE | Bathgate Campus Improvements | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Aug 2022 | Jul 2023 | Aug 2023
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | BATHGATE | Bathgate Campus Improvements | 3 | CONSTRUCTION | Aug 2022 | Sep 2022 | Aug 2023 | Sep 2023
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | BATHGATE | Bathgate Campus Improvements | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Sep 2022 | Sep 2023 | Sep 2023
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | BATHGATE | Bathgate Campus Improvements | 5 | SUBSTANTIAL COMPLETION | Sep 2022 | Oct 2022 | Sep 2023 | Oct 2023
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | BATHGATE | Bathgate Campus Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2022 | Jun 2023 | Oct 2023 | Jun 2025
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | EDXHPGEN | Hunts Point Cooperative Market | 1 | DESIGN | Jul 2016 | Jul 2016 | Jul 2019 | Jul 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | EDXHPGEN | Hunts Point Cooperative Market | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Jul 2019 | Aug 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | EDXHPGEN | Hunts Point Cooperative Market | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Aug 2019 | Sep 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | EDXHPGEN | Hunts Point Cooperative Market | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Sep 2019 | Sep 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | EDXHPGEN | Hunts Point Cooperative Market | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Sep 2019 | Oct 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | EDXHPGEN | Hunts Point Cooperative Market | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2016 | Oct 2019 | Oct 2029
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | FFMDRAIN | New Fulton Fish Market -- Facility Upgrades: New Drainage Sy | 1 | DESIGN | Jul 2019 | Jul 2019 | Jul 2019 | Jul 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | FFMDRAIN | New Fulton Fish Market -- Facility Upgrades: New Drainage Sy | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jul 2019 | Aug 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | FFMDRAIN | New Fulton Fish Market -- Facility Upgrades: New Drainage Sy | 3 | CONSTRUCTION | Aug 2019 | Sep 2019 | Aug 2019 | Sep 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | FFMDRAIN | New Fulton Fish Market -- Facility Upgrades: New Drainage Sy | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Sep 2019 | Sep 2019 | Sep 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | FFMDRAIN | New Fulton Fish Market -- Facility Upgrades: New Drainage Sy | 5 | SUBSTANTIAL COMPLETION | Sep 2019 | Oct 2019 | Sep 2019 | Oct 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | FFMDRAIN | New Fulton Fish Market -- Facility Upgrades: New Drainage Sy | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2019 | Oct 2020 | Oct 2019 | Jun 2027
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | FREIGHTHP | Freight NYC - Hunts Point Marine Highway | 1 | DESIGN | Jul 2018 | Jul 2018 | Mar 2020 | Apr 2020
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | FREIGHTHP | Freight NYC - Hunts Point Marine Highway | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Aug 2018 | Apr 2020 | Apr 2020
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | FREIGHTHP | Freight NYC - Hunts Point Marine Highway | 3 | CONSTRUCTION | Aug 2018 | Sep 2018 | Apr 2020 | May 2020
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | FREIGHTHP | Freight NYC - Hunts Point Marine Highway | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2018 | Sep 2018 | Jun 2020 | Jun 2020
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | FREIGHTHP | Freight NYC - Hunts Point Marine Highway | 5 | SUBSTANTIAL COMPLETION | Sep 2018 | Oct 2018 | Jun 2020 | Jun 2020
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | FREIGHTHP | Freight NYC - Hunts Point Marine Highway | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2018 | Oct 2018 | Jun 2024 | Jun 2029
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP07-02 | GI - DSGN & CONS OF ROW BIOSWALES & GREENSTREETS IN HP-007 | 1 | DESIGN | Feb 2015 | Jun 2017 | Feb 2015 | Jun 2017
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP07-02 | GI - DSGN & CONS OF ROW BIOSWALES & GREENSTREETS IN HP-007 | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2017 | Jun 2017 | Jun 2017 | Jun 2017
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP07-02 | GI - DSGN & CONS OF ROW BIOSWALES & GREENSTREETS IN HP-007 | 3 | CONSTRUCTION | Jun 2017 | Dec 2017 | Jun 2017 | Dec 2017
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP07-02 | GI - DSGN & CONS OF ROW BIOSWALES & GREENSTREETS IN HP-007 | 4 | ORIGINAL EQUIP & FURNISHING | Dec 2017 | Dec 2017 | Dec 2017 | Dec 2017
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP07-02 | GI - DSGN & CONS OF ROW BIOSWALES & GREENSTREETS IN HP-007 | 5 | SUBSTANTIAL COMPLETION | Dec 2017 | Dec 2017 | Dec 2017 | Dec 2017
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP07-02 | GI - DSGN & CONS OF ROW BIOSWALES & GREENSTREETS IN HP-007 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2017 | Jun 2019 | Dec 2017 | Jun 2024
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP14-01 | GI - Green infrastructure in Westchester Creek HP-14 | 1 | DESIGN | Jun 2014 | Jun 2014 | Jun 2014 | Jun 2014
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP14-01 | GI - Green infrastructure in Westchester Creek HP-14 | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2014 | Jul 2014 | Jun 2014 | Jul 2014
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP14-01 | GI - Green infrastructure in Westchester Creek HP-14 | 3 | CONSTRUCTION | Jul 2014 | Aug 2014 | Jul 2014 | Jun 2020
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP14-01 | GI - Green infrastructure in Westchester Creek HP-14 | 4 | ORIGINAL EQUIP & FURNISHING | Aug 2014 | Aug 2014 | Jul 2020 | Jun 2020
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP14-01 | GI - Green infrastructure in Westchester Creek HP-14 | 5 | SUBSTANTIAL COMPLETION | Aug 2014 | Sep 2014 | Jul 2020 | Jun 2020
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP14-01 | GI - Green infrastructure in Westchester Creek HP-14 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2014 | Sep 2014 | Jul 2020 | Jun 2024
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HOMESTACT | Home Street Properties activation of vacant lots | 1 | DESIGN | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HOMESTACT | Home Street Properties activation of vacant lots | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Aug 2021 | Jul 2021 | Aug 2021
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HOMESTACT | Home Street Properties activation of vacant lots | 3 | CONSTRUCTION | Aug 2021 | Sep 2021 | Aug 2021 | Sep 2021
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HOMESTACT | Home Street Properties activation of vacant lots | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Sep 2021 | Sep 2021 | Sep 2021
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HOMESTACT | Home Street Properties activation of vacant lots | 5 | SUBSTANTIAL COMPLETION | Sep 2021 | Oct 2021 | Sep 2021 | Oct 2021
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HOMESTACT | Home Street Properties activation of vacant lots | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2021 | Oct 2024 | Oct 2021 | Oct 2024
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPBOILER | HUNTS POINT MEAT MARKET (EDC)--BOILER UPDATES | 1 | DESIGN | Jul 2017 | Jul 2017 | Mar 2019 | Apr 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPBOILER | HUNTS POINT MEAT MARKET (EDC)--BOILER UPDATES | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Aug 2017 | Apr 2019 | Apr 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPBOILER | HUNTS POINT MEAT MARKET (EDC)--BOILER UPDATES | 3 | CONSTRUCTION | Aug 2017 | Sep 2017 | Apr 2019 | May 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPBOILER | HUNTS POINT MEAT MARKET (EDC)--BOILER UPDATES | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Sep 2017 | Jun 2019 | Jun 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPBOILER | HUNTS POINT MEAT MARKET (EDC)--BOILER UPDATES | 5 | SUBSTANTIAL COMPLETION | Sep 2017 | Oct 2017 | Jun 2019 | Jun 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPBOILER | HUNTS POINT MEAT MARKET (EDC)--BOILER UPDATES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2017 | Oct 2017 | Jun 2019 | Jun 2026
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPPRINGLE | HP Pringle Switch - Electrical Upgrades | 1 | DESIGN | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPPRINGLE | HP Pringle Switch - Electrical Upgrades | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Aug 2021 | Jul 2021 | Aug 2021
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPPRINGLE | HP Pringle Switch - Electrical Upgrades | 3 | CONSTRUCTION | Aug 2021 | Sep 2021 | Aug 2021 | Sep 2021
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPPRINGLE | HP Pringle Switch - Electrical Upgrades | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Sep 2021 | Sep 2021 | Sep 2021
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPPRINGLE | HP Pringle Switch - Electrical Upgrades | 5 | SUBSTANTIAL COMPLETION | Sep 2021 | Oct 2021 | Sep 2021 | Oct 2021
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPPRINGLE | HP Pringle Switch - Electrical Upgrades | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2021 | Oct 2025 | Oct 2021 | Oct 2025
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPPRODUCE | Hunts Point Produce Market | 1 | DESIGN | Jul 2023 | Jul 2023 | Jul 2023 | Jul 2023
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPPRODUCE | Hunts Point Produce Market | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPPRODUCE | Hunts Point Produce Market | 3 | CONSTRUCTION | Aug 2023 | Sep 2023 | Aug 2023 | Sep 2023
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPPRODUCE | Hunts Point Produce Market | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Sep 2023 | Sep 2023 | Sep 2023
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPPRODUCE | Hunts Point Produce Market | 5 | SUBSTANTIAL COMPLETION | Sep 2023 | Oct 2023 | Sep 2023 | Oct 2023
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPPRODUCE | Hunts Point Produce Market | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2023 | Jun 2029 | Oct 2023 | Jun 2029
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HTPRODUC2 | Hunts Point Market | 1 | DESIGN | Jan 2011 | Jun 2011 | Jan 2015 | Jun 2015
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HTPRODUC2 | Hunts Point Market | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2011 | Jun 2011 | Jun 2015 | Jun 2015
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HTPRODUC2 | Hunts Point Market | 3 | CONSTRUCTION | Jun 2011 | Jun 2012 | Jun 2015 | Jun 2017
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HTPRODUC2 | Hunts Point Market | 4 | ORIGINAL EQUIP & FURNISHING | Jun 2012 | Jun 2012 | Jun 2017 | Jun 2017
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HTPRODUC2 | Hunts Point Market | 5 | SUBSTANTIAL COMPLETION | Jun 2012 | Jun 2012 | Jun 2017 | Jun 2017
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HTPRODUC2 | Hunts Point Market | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2012 | Jun 2012 | Jun 2017 | Jun 2025
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTLUMP | Lump Sum - Hunts Point | 1 | DESIGN | Sep 2008 | Oct 2010 | Sep 2008 | Oct 2010
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTLUMP | Lump Sum - Hunts Point | 2 | BID AWARD AND REGISTER CONTRCT | Oct 2010 | Oct 2010 | Oct 2010 | Oct 2010
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTLUMP | Lump Sum - Hunts Point | 3 | CONSTRUCTION | Oct 2010 | Oct 2012 | Oct 2010 | Oct 2012
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTLUMP | Lump Sum - Hunts Point | 4 | ORIGINAL EQUIP & FURNISHING | Oct 2012 | Oct 2012 | Oct 2012 | Oct 2012
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTLUMP | Lump Sum - Hunts Point | 5 | SUBSTANTIAL COMPLETION | Oct 2012 | Oct 2012 | Oct 2012 | Oct 2012
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTLUMP | Lump Sum - Hunts Point | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2012 | Oct 2012 | Oct 2012 | Jun 2031
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTMEAT2 | Hunts Point Meat Market 2 | 1 | DESIGN | Jan 2016 | Jun 2018 | Jan 2016 | Jun 2018
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTMEAT2 | Hunts Point Meat Market 2 | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Jun 2018 | Jul 2018 | Jun 2018
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTMEAT2 | Hunts Point Meat Market 2 | 3 | CONSTRUCTION | Jul 2018 | Jun 2021 | Jul 2018 | Jun 2027
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTMEAT2 | Hunts Point Meat Market 2 | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2021 | Jun 2021 | Jul 2027 | Jun 2027
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTMEAT2 | Hunts Point Meat Market 2 | 5 | SUBSTANTIAL COMPLETION | Jul 2021 | Jun 2021 | Jul 2027 | Jun 2027
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTMEAT2 | Hunts Point Meat Market 2 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Jul 2021 | Jul 2027 | Jul 2027
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSAOU2 | Hunts Point AOU-2 and Building G Development | 1 | DESIGN | Jul 2017 | Jul 2017 | Mar 2019 | Apr 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSAOU2 | Hunts Point AOU-2 and Building G Development | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Aug 2017 | Apr 2019 | Apr 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSAOU2 | Hunts Point AOU-2 and Building G Development | 3 | CONSTRUCTION | Aug 2017 | Sep 2017 | Apr 2019 | May 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSAOU2 | Hunts Point AOU-2 and Building G Development | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Sep 2017 | Jun 2019 | Jun 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSAOU2 | Hunts Point AOU-2 and Building G Development | 5 | SUBSTANTIAL COMPLETION | Sep 2017 | Oct 2017 | Jun 2019 | Jun 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSAOU2 | Hunts Point AOU-2 and Building G Development | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2017 | Oct 2017 | Jun 2019 | Jun 2031
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSFISH | Hunts Point Fish Market | 1 | DESIGN | Jan 2016 | Jun 2018 | Jan 2016 | Jun 2018
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSFISH | Hunts Point Fish Market | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Jun 2018 | Jul 2018 | Jun 2018
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSFISH | Hunts Point Fish Market | 3 | CONSTRUCTION | Jul 2018 | Jun 2021 | Jul 2018 | Jun 2026
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSFISH | Hunts Point Fish Market | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2021 | Jun 2021 | Jul 2026 | Jun 2026
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSFISH | Hunts Point Fish Market | 5 | SUBSTANTIAL COMPLETION | Jul 2021 | Jun 2021 | Jul 2026 | Jun 2026
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSFISH | Hunts Point Fish Market | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Jul 2021 | Jul 2026 | Jul 2026
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSPROD | Hunts Point Produce Market | 1 | DESIGN | Jan 2016 | Jun 2018 | Jan 2016 | Jun 2018
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSPROD | Hunts Point Produce Market | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Jun 2018 | Jul 2018 | Jun 2018
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSPROD | Hunts Point Produce Market | 3 | CONSTRUCTION | Jul 2018 | Jun 2021 | Jul 2018 | Jun 2024
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSPROD | Hunts Point Produce Market | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2021 | Jun 2021 | Jul 2024 | Jun 2024
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSPROD | Hunts Point Produce Market | 5 | SUBSTANTIAL COMPLETION | Jul 2021 | Jun 2021 | Jul 2024 | Jun 2024
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSPROD | Hunts Point Produce Market | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Jul 2021 | Jul 2024 | Jun 2026
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | KINGBRARM | Kingsbridge Armory Renovations | 1 | DESIGN | Jul 2022 | Jul 2022 | Jul 2022 | Jul 2022
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | KINGBRARM | Kingsbridge Armory Renovations | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Aug 2022 | Jul 2022 | Aug 2022
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | KINGBRARM | Kingsbridge Armory Renovations | 3 | CONSTRUCTION | Aug 2022 | Sep 2022 | Aug 2022 | Sep 2022
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | KINGBRARM | Kingsbridge Armory Renovations | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Sep 2022 | Sep 2022 | Sep 2022
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | KINGBRARM | Kingsbridge Armory Renovations | 5 | SUBSTANTIAL COMPLETION | Sep 2022 | Oct 2022 | Sep 2022 | Oct 2022
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | KINGBRARM | Kingsbridge Armory Renovations | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2022 | Jun 2023 | Oct 2022 | Jun 2024
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LAFFAVELT | Laffayette Avenue Street Lighting | 1 | DESIGN | Jul 2019 | Jul 2019 | Jul 2019 | Jul 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LAFFAVELT | Laffayette Avenue Street Lighting | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jul 2019 | Aug 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LAFFAVELT | Laffayette Avenue Street Lighting | 3 | CONSTRUCTION | Aug 2019 | Sep 2019 | Aug 2019 | Sep 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LAFFAVELT | Laffayette Avenue Street Lighting | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Sep 2019 | Sep 2019 | Sep 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LAFFAVELT | Laffayette Avenue Street Lighting | 5 | SUBSTANTIAL COMPLETION | Sep 2019 | Oct 2019 | Sep 2019 | Oct 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LAFFAVELT | Laffayette Avenue Street Lighting | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2019 | Oct 2020 | Oct 2019 | Jun 2031
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16HPT | HUNTS POINT: MAJOR RENOVATION | 1 | DESIGN | Aug 2016 | Jan 2017 | Aug 2016 | Jan 2017
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16HPT | HUNTS POINT: MAJOR RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2017 | Apr 2017 | Jan 2017 | Apr 2017
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16HPT | HUNTS POINT: MAJOR RENOVATION | 3 | CONSTRUCTION | Apr 2017 | Apr 2018 | Apr 2017 | Apr 2023
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16HPT | HUNTS POINT: MAJOR RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2018 | Feb 2019 | Apr 2023 | Feb 2025
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16MLR | Melrose: Major Renovation | 1 | DESIGN | Aug 2016 | Jan 2017 | Aug 2016 | Jan 2017
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16MLR | Melrose: Major Renovation | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2017 | Apr 2017 | Jan 2017 | Apr 2017
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16MLR | Melrose: Major Renovation | 3 | CONSTRUCTION | Apr 2017 | Apr 2018 | Apr 2017 | Apr 2022
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16MLR | Melrose: Major Renovation | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2018 | Feb 2019 | Apr 2022 | Feb 2024
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-MONTE | Montefiore Biotechnology Accelerated Research Center | 1 | DESIGN | Jul 2022 | Jul 2022 | Sep 2021 | Jul 2022
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-MONTE | Montefiore Biotechnology Accelerated Research Center | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Aug 2022 | Jul 2022 | Aug 2022
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-MONTE | Montefiore Biotechnology Accelerated Research Center | 3 | CONSTRUCTION | Aug 2022 | Sep 2022 | Aug 2022 | Sep 2022
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-MONTE | Montefiore Biotechnology Accelerated Research Center | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Sep 2022 | Sep 2022 | Sep 2022
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-MONTE | Montefiore Biotechnology Accelerated Research Center | 5 | SUBSTANTIAL COMPLETION | Sep 2022 | Oct 2022 | Sep 2022 | Oct 2022
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-MONTE | Montefiore Biotechnology Accelerated Research Center | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2022 | Jun 2023 | Oct 2022 | Jun 2026
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | NFFMSTORG | NEW FULTON FISH MARKET RENOVATION-- REFRIGERATED STORAGE ARE | 1 | DESIGN | Jul 2019 | Jul 2019 | Jul 2019 | Jul 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | NFFMSTORG | NEW FULTON FISH MARKET RENOVATION-- REFRIGERATED STORAGE ARE | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jul 2019 | Aug 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | NFFMSTORG | NEW FULTON FISH MARKET RENOVATION-- REFRIGERATED STORAGE ARE | 3 | CONSTRUCTION | Aug 2019 | Sep 2019 | Aug 2019 | Sep 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | NFFMSTORG | NEW FULTON FISH MARKET RENOVATION-- REFRIGERATED STORAGE ARE | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Sep 2019 | Sep 2019 | Sep 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | NFFMSTORG | NEW FULTON FISH MARKET RENOVATION-- REFRIGERATED STORAGE ARE | 5 | SUBSTANTIAL COMPLETION | Sep 2019 | Oct 2020 | Sep 2019 | Oct 2020
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | NFFMSTORG | NEW FULTON FISH MARKET RENOVATION-- REFRIGERATED STORAGE ARE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2020 | Oct 2020 | Oct 2020 | Oct 2024
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | P-1ORCHPA | Orchard Beach Pavillion & Ancillary Reconstruction | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Jul 2016
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | P-1ORCHPA | Orchard Beach Pavillion & Ancillary Reconstruction | 2 | DESIGN | Dec 2016 | Dec 2018 | Jul 2016 | Aug 2016
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | P-1ORCHPA | Orchard Beach Pavillion & Ancillary Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Aug 2016 | Sep 2016
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | P-1ORCHPA | Orchard Beach Pavillion & Ancillary Reconstruction | 4 | CONSTRUCTION | Sep 2019 | Sep 2021 | Sep 2016 | Sep 2016
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | P-1ORCHPA | Orchard Beach Pavillion & Ancillary Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2016 | Oct 2016
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | P-1ORCHPA | Orchard Beach Pavillion & Ancillary Reconstruction | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Oct 2016 | Jun 2030
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | PV471SWA2 | BxMA - South Wing Atrium Renovation | 1 | DESIGN | Jun 2021 | Jun 2021 | Jun 2021 | Jun 2021
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | PV471SWA2 | BxMA - South Wing Atrium Renovation | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Jul 2021 | Jun 2021 | Jul 2021
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | PV471SWA2 | BxMA - South Wing Atrium Renovation | 3 | CONSTRUCTION | Jul 2021 | Aug 2021 | Jul 2021 | Aug 2021
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | PV471SWA2 | BxMA - South Wing Atrium Renovation | 4 | ORIGINAL EQUIP & FURNISHING | Aug 2021 | Aug 2021 | Aug 2021 | Aug 2021
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | PV471SWA2 | BxMA - South Wing Atrium Renovation | 5 | SUBSTANTIAL COMPLETION | Aug 2021 | Sep 2021 | Aug 2021 | Sep 2021
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | PV471SWA2 | BxMA - South Wing Atrium Renovation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2023 | Sep 2021 | Jun 2025
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHPRX2 | Hunts Point Resiliency Mob-Gen/SP | 1 | DESIGN | Jan 2020 | Jan 2020 | Jan 2020 | Jan 2020
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHPRX2 | Hunts Point Resiliency Mob-Gen/SP | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2020 | Feb 2020 | Jan 2020 | Feb 2020
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHPRX2 | Hunts Point Resiliency Mob-Gen/SP | 3 | CONSTRUCTION | Feb 2020 | Mar 2020 | Feb 2020 | Mar 2020
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHPRX2 | Hunts Point Resiliency Mob-Gen/SP | 4 | ORIGINAL EQUIP & FURNISHING | Mar 2020 | Mar 2020 | Mar 2020 | Mar 2020
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHPRX2 | Hunts Point Resiliency Mob-Gen/SP | 5 | SUBSTANTIAL COMPLETION | Mar 2020 | Apr 2020 | Mar 2020 | Apr 2020
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHPRX2 | Hunts Point Resiliency Mob-Gen/SP | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2020 | Apr 2020 | Apr 2020 | Apr 2024
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHPRXD | Hunts Point Energy Resiliency Pilot - DR | 1 | DESIGN | Jul 2016 | Jul 2016 | Jul 2016 | Jul 2016
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHPRXD | Hunts Point Energy Resiliency Pilot - DR | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Aug 2016 | Jul 2016 | Aug 2016
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHPRXD | Hunts Point Energy Resiliency Pilot - DR | 3 | CONSTRUCTION | Aug 2016 | Sep 2016 | Aug 2016 | Sep 2016
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHPRXD | Hunts Point Energy Resiliency Pilot - DR | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2016 | Sep 2016 | Sep 2016 | Sep 2016
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHPRXD | Hunts Point Energy Resiliency Pilot - DR | 5 | SUBSTANTIAL COMPLETION | Sep 2016 | Oct 2016 | Sep 2016 | Oct 2016
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHPRXD | Hunts Point Energy Resiliency Pilot - DR | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2016 | Oct 2016 | Oct 2016 | Jun 2030
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SEEDDAVID | SEED - Davidson Community Center | 1 | DESIGN | Jul 2023 | Jul 2023 | Jul 2023 | Jul 2023
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SEEDDAVID | SEED - Davidson Community Center | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SEEDDAVID | SEED - Davidson Community Center | 3 | CONSTRUCTION | Aug 2023 | Sep 2023 | Aug 2023 | Sep 2023
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SEEDDAVID | SEED - Davidson Community Center | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Sep 2023 | Sep 2023 | Sep 2023
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SEEDDAVID | SEED - Davidson Community Center | 5 | SUBSTANTIAL COMPLETION | Sep 2023 | Oct 2023 | Sep 2023 | Oct 2023
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SEEDDAVID | SEED - Davidson Community Center | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2023 | Jun 2030 | Oct 2023 | Jun 2030
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | STHBRXGRN | South Bronx Greenway | 1 | DESIGN | Aug 2006 | Aug 2006 | May 2021 | Jun 2028
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | STHBRXGRN | South Bronx Greenway | 2 | BID AWARD AND REGISTER CONTRCT | Aug 2006 | Sep 2006 | Apr 2011 | Jul 2011
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | STHBRXGRN | South Bronx Greenway | 3 | CONSTRUCTION | Sep 2006 | Oct 2006 | May 2009 | Jun 2028
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | STHBRXGRN | South Bronx Greenway | 4 | ORIGINAL EQUIP & FURNISHING | Oct 2006 | Oct 2006 | Jul 2028 | Jun 2028
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | STHBRXGRN | South Bronx Greenway | 5 | SUBSTANTIAL COMPLETION | Oct 2006 | Nov 2006 | Jul 2028 | Jun 2028
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | STHBRXGRN | South Bronx Greenway | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2006 | Nov 2006 | Jul 2028 | Jul 2028
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SWBXINFRA | LC - Southwest Bronx Infrastructure Improvements | 1 | DESIGN | Jan 2016 | Jan 2016 | Jan 2016 | Jan 2016
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SWBXINFRA | LC - Southwest Bronx Infrastructure Improvements | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2016 | Jun 2016 | Jan 2016 | Jun 2016
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SWBXINFRA | LC - Southwest Bronx Infrastructure Improvements | 3 | CONSTRUCTION | Jul 2016 | Jun 2017 | Jul 2016 | Jun 2017
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SWBXINFRA | LC - Southwest Bronx Infrastructure Improvements | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2017 | Jun 2020 | Jul 2017 | Jun 2025
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SWBXINFRA | LC - Southwest Bronx Infrastructure Improvements | 5 | SUBSTANTIAL COMPLETION | Jul 2020 | Jun 2020 | Jul 2025 | Jun 2025
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SWBXINFRA | LC - Southwest Bronx Infrastructure Improvements | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Jul 2020 | Jul 2025 | Jul 2028
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SWBXLCN | Lower Concourse North | 1 | DESIGN | Jan 2021 | Jan 2021 | Dec 2019 | Jan 2021
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SWBXLCN | Lower Concourse North | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2021 | Feb 2021 | Jan 2021 | Feb 2021
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SWBXLCN | Lower Concourse North | 3 | CONSTRUCTION | Feb 2021 | Mar 2021 | Feb 2021 | Mar 2021
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SWBXLCN | Lower Concourse North | 4 | ORIGINAL EQUIP & FURNISHING | Mar 2021 | Mar 2021 | Mar 2021 | Mar 2021
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SWBXLCN | Lower Concourse North | 5 | SUBSTANTIAL COMPLETION | Mar 2021 | Apr 2021 | Mar 2021 | Apr 2021
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SWBXLCN | Lower Concourse North | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2021 | Apr 2021 | Apr 2021 | Jun 2025
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | VINCEAVE | Vincent Avenue Seawall Rehabilitation | 1 | DESIGN | Jul 2017 | Jul 2017 | Mar 2019 | Apr 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | VINCEAVE | Vincent Avenue Seawall Rehabilitation | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Aug 2017 | Apr 2019 | Apr 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | VINCEAVE | Vincent Avenue Seawall Rehabilitation | 3 | CONSTRUCTION | Aug 2017 | Sep 2017 | Apr 2019 | May 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | VINCEAVE | Vincent Avenue Seawall Rehabilitation | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2017 | Sep 2017 | Jun 2019 | Jun 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | VINCEAVE | Vincent Avenue Seawall Rehabilitation | 5 | SUBSTANTIAL COMPLETION | Sep 2017 | Oct 2017 | Jun 2019 | Jun 2019
20231026 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | VINCEAVE | Vincent Avenue Seawall Rehabilitation | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2017 | Oct 2017 | Jun 2019 | Jun 2025
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM07VYSE | VYSE AVENUE FRONT ENTRANCE DOORS | 1 | DESIGN | Jan 2011 | Jun 2011 | Dec 2002 | May 2017
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM07VYSE | VYSE AVENUE FRONT ENTRANCE DOORS | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2011 | Nov 2011 | May 2017 | Feb 2019
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM07VYSE | VYSE AVENUE FRONT ENTRANCE DOORS | 3 | CONSTRUCTION | Nov 2011 | Nov 2012 | Feb 2019 | Aug 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM07VYSE | VYSE AVENUE FRONT ENTRANCE DOORS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2012 | May 2013 | Feb 2019 | Aug 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM07VYSE | VYSE AVENUE FRONT ENTRANCE DOORS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2012 | May 2013 | Aug 2020 | May 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM11CPGP | CLASON POINT PLAYGROUND AND OUTDOOR AREA IMPROVEMENTS | 1 | DESIGN | Jan 2011 | Jun 2011 | May 2014 | Oct 2016
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM11CPGP | CLASON POINT PLAYGROUND AND OUTDOOR AREA IMPROVEMENTS | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2011 | Nov 2011 | Oct 2016 | Nov 2017
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM11CPGP | CLASON POINT PLAYGROUND AND OUTDOOR AREA IMPROVEMENTS | 3 | CONSTRUCTION | Nov 2011 | Nov 2012 | Nov 2017 | Nov 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM11CPGP | CLASON POINT PLAYGROUND AND OUTDOOR AREA IMPROVEMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2012 | May 2013 | Nov 2017 | Nov 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM11CPGP | CLASON POINT PLAYGROUND AND OUTDOOR AREA IMPROVEMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2012 | May 2013 | Nov 2018 | Jul 2031
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM11DAVC | DAVIDSON/ SITE 166 RES. ASSN SPORTS DOME AND CULINARY PROG. | 1 | DESIGN | Oct 2014 | Apr 2015 | Jun 2012 | Jun 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM11DAVC | DAVIDSON/ SITE 166 RES. ASSN SPORTS DOME AND CULINARY PROG. | 2 | BID AWARD AND REGISTER CONTRCT | Apr 2015 | Sep 2015 | Jun 2018 | Dec 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM11DAVC | DAVIDSON/ SITE 166 RES. ASSN SPORTS DOME AND CULINARY PROG. | 3 | CONSTRUCTION | Sep 2015 | Sep 2016 | Dec 2018 | Mar 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM11DAVC | DAVIDSON/ SITE 166 RES. ASSN SPORTS DOME AND CULINARY PROG. | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2016 | Mar 2017 | Dec 2018 | Mar 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM11DAVC | DAVIDSON/ SITE 166 RES. ASSN SPORTS DOME AND CULINARY PROG. | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2016 | Mar 2017 | Jan 2022 | Jul 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM13BRPG | BRONX RIVER HOUSES PLAYGROUND RENOVATION | 1 | DESIGN | Jan 2013 | Jun 2013 | May 2014 | Oct 2016
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM13BRPG | BRONX RIVER HOUSES PLAYGROUND RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2013 | Nov 2013 | Oct 2016 | Mar 2017
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM13BRPG | BRONX RIVER HOUSES PLAYGROUND RENOVATION | 3 | CONSTRUCTION | Nov 2013 | Nov 2014 | Mar 2017 | Jun 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM13BRPG | BRONX RIVER HOUSES PLAYGROUND RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2014 | May 2015 | Mar 2017 | Jun 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM13BRPG | BRONX RIVER HOUSES PLAYGROUND RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2014 | May 2015 | Jun 2018 | Feb 2031
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MRSR | MONROE HOUSES SENIOR CENTER RENOVATION | 1 | DESIGN | Jan 2014 | Jun 2014 | May 2015 | Mar 2017
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MRSR | MONROE HOUSES SENIOR CENTER RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2014 | Nov 2014 | Mar 2017 | Aug 2017
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MRSR | MONROE HOUSES SENIOR CENTER RENOVATION | 3 | CONSTRUCTION | Nov 2014 | Nov 2015 | Aug 2017 | May 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MRSR | MONROE HOUSES SENIOR CENTER RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2015 | May 2016 | Aug 2017 | May 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MRSR | MONROE HOUSES SENIOR CENTER RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2015 | May 2016 | May 2018 | Mar 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SHGC | STEBBINS AVENUE-HEWITT PLACE INFRASTRUCTURE IMPROVEMENTS | 1 | DESIGN | Jan 2015 | Jun 2015 | Dec 2015 | Dec 2016
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SHGC | STEBBINS AVENUE-HEWITT PLACE INFRASTRUCTURE IMPROVEMENTS | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2015 | Nov 2015 | Dec 2016 | Mar 2017
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SHGC | STEBBINS AVENUE-HEWITT PLACE INFRASTRUCTURE IMPROVEMENTS | 3 | CONSTRUCTION | Nov 2015 | Nov 2016 | Mar 2017 | Nov 2017
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SHGC | STEBBINS AVENUE-HEWITT PLACE INFRASTRUCTURE IMPROVEMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2016 | May 2017 | Mar 2017 | Nov 2017
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SHGC | STEBBINS AVENUE-HEWITT PLACE INFRASTRUCTURE IMPROVEMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2016 | May 2017 | Dec 2017 | Feb 2026
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CLGY | CLAREMONT HOUSES GYM RENOVATION FOR CLAREMONT NEIGHBORHOOD | 1 | DESIGN | Jan 2016 | Jul 2016 | May 2016 | Dec 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CLGY | CLAREMONT HOUSES GYM RENOVATION FOR CLAREMONT NEIGHBORHOOD | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Nov 2016 | Dec 2018 | Jun 2019
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CLGY | CLAREMONT HOUSES GYM RENOVATION FOR CLAREMONT NEIGHBORHOOD | 3 | CONSTRUCTION | Nov 2016 | Nov 2017 | Jun 2018 | Nov 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CLGY | CLAREMONT HOUSES GYM RENOVATION FOR CLAREMONT NEIGHBORHOOD | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | May 2018 | Jun 2018 | Nov 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CLGY | CLAREMONT HOUSES GYM RENOVATION FOR CLAREMONT NEIGHBORHOOD | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | May 2018 | Nov 2020 | Dec 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16MODC | JAMES MONROE HOUSES RENOVATE COMMUNITY CENTER | 1 | DESIGN | Jan 2016 | Jul 2016 | Jan 2016 | Jul 2016
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16MODC | JAMES MONROE HOUSES RENOVATE COMMUNITY CENTER | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2016 | Nov 2016 | Jul 2016 | Nov 2016
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16MODC | JAMES MONROE HOUSES RENOVATE COMMUNITY CENTER | 3 | CONSTRUCTION | Nov 2016 | Nov 2017 | Nov 2016 | Nov 2017
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16MODC | JAMES MONROE HOUSES RENOVATE COMMUNITY CENTER | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | May 2018 | Nov 2016 | Nov 2017
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16MODC | JAMES MONROE HOUSES RENOVATE COMMUNITY CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2017 | May 2018 | Nov 2017 | Feb 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17BASK | BASKETBALL COURTS RENOVATION AT ADAMS HOUSES | 3 | CONSTRUCTION | Oct 2018 | Oct 2019 | Oct 2018 | Oct 2019
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17BASK | BASKETBALL COURTS RENOVATION AT ADAMS HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2019 | Apr 2020 | Oct 2018 | Oct 2019
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17BASK | BASKETBALL COURTS RENOVATION AT ADAMS HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2019 | Apr 2020 | Oct 2019 | Apr 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17FORF | ROOF REPLACEMENT AT FOREST HOUSES | 1 | DESIGN | Jan 2017 | Jun 2017 | Jan 2017 | Jun 2017
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17FORF | ROOF REPLACEMENT AT FOREST HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Nov 2017 | Jul 2017 | Nov 2017
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17FORF | ROOF REPLACEMENT AT FOREST HOUSES | 3 | CONSTRUCTION | Nov 2017 | Nov 2018 | Nov 2017 | Nov 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17FORF | ROOF REPLACEMENT AT FOREST HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2018 | May 2019 | Nov 2017 | Nov 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17FORF | ROOF REPLACEMENT AT FOREST HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2018 | May 2019 | Nov 2018 | Feb 2025
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MASC | MORRISANIA SECURITY ENHANCEMENTS | 1 | DESIGN | Aug 2016 | Jan 2017 | Aug 2016 | Jan 2017
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MASC | MORRISANIA SECURITY ENHANCEMENTS | 2 | BID AWARD AND REGISTER CONTRCT | Jan 2017 | Jun 2017 | Jan 2017 | Jun 2017
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MASC | MORRISANIA SECURITY ENHANCEMENTS | 3 | CONSTRUCTION | Jun 2017 | Jun 2018 | Jun 2017 | Jun 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MASC | MORRISANIA SECURITY ENHANCEMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2018 | Dec 2018 | Jun 2017 | Jun 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MASC | MORRISANIA SECURITY ENHANCEMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2018 | Dec 2018 | Jun 2018 | Aug 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MRPL | MORRIS HOUSES PLAYGROUND RENOVATION | 1 | DESIGN | Feb 2017 | Jul 2017 | Feb 2017 | Jul 2017
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MRPL | MORRIS HOUSES PLAYGROUND RENOVATION | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MRPL | MORRIS HOUSES PLAYGROUND RENOVATION | 3 | CONSTRUCTION | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MRPL | MORRIS HOUSES PLAYGROUND RENOVATION | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2018 | Jun 2019 | Dec 2017 | Dec 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MRPL | MORRIS HOUSES PLAYGROUND RENOVATION | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2018 | Jun 2019 | Dec 2018 | Dec 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17PHCC | PATTERSON HOUSES COMMUNITY CENTER REHAB | 1 | DESIGN | Feb 2017 | Jul 2017 | Feb 2017 | Jul 2017
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17PHCC | PATTERSON HOUSES COMMUNITY CENTER REHAB | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17PHCC | PATTERSON HOUSES COMMUNITY CENTER REHAB | 3 | CONSTRUCTION | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17PHCC | PATTERSON HOUSES COMMUNITY CENTER REHAB | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2018 | Jun 2019 | Dec 2017 | Dec 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17PHCC | PATTERSON HOUSES COMMUNITY CENTER REHAB | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2018 | Jun 2019 | Dec 2018 | Jun 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17SOSK | PLAYGROUND UPGRADE AT SOTOMAYOR HOUSES | 1 | DESIGN | Feb 2017 | Jul 2017 | Feb 2017 | Jul 2017
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17SOSK | PLAYGROUND UPGRADE AT SOTOMAYOR HOUSES | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17SOSK | PLAYGROUND UPGRADE AT SOTOMAYOR HOUSES | 3 | CONSTRUCTION | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17SOSK | PLAYGROUND UPGRADE AT SOTOMAYOR HOUSES | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2018 | Jun 2019 | Dec 2017 | Dec 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17SOSK | PLAYGROUND UPGRADE AT SOTOMAYOR HOUSES | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2018 | Jun 2019 | Dec 2018 | Feb 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BRCB | BOSTON ROAD SENIOR CENTER ROOF REPLACEMENT | 1 | DESIGN | Jan 2018 | Jun 2018 | Jan 2018 | Jun 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BRCB | BOSTON ROAD SENIOR CENTER ROOF REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BRCB | BOSTON ROAD SENIOR CENTER ROOF REPLACEMENT | 3 | CONSTRUCTION | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BRCB | BOSTON ROAD SENIOR CENTER ROOF REPLACEMENT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2018 | Dec 2019
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BRCB | BOSTON ROAD SENIOR CENTER ROOF REPLACEMENT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2019 | Dec 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CCMH | MELROSE HOUSES CCTV AND LAC | 2 | BID AWARD AND REGISTER CONTRCT | Aug 2018 | Jan 2019 | Aug 2018 | Jan 2019
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CCMH | MELROSE HOUSES CCTV AND LAC | 3 | CONSTRUCTION | Jan 2019 | Jan 2020 | Jan 2019 | Jan 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CCMH | MELROSE HOUSES CCTV AND LAC | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2020 | Jul 2020 | Jan 2019 | Jan 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CCMH | MELROSE HOUSES CCTV AND LAC | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2020 | Jul 2020 | Jan 2020 | Jan 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18COSC | SECURITY CAMERA INSTALLATION AT 372 EAST 152ND ST COURTLANDT | 1 | DESIGN | Jan 2018 | Jun 2018 | Jan 2018 | Jun 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18COSC | SECURITY CAMERA INSTALLATION AT 372 EAST 152ND ST COURTLANDT | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18COSC | SECURITY CAMERA INSTALLATION AT 372 EAST 152ND ST COURTLANDT | 3 | CONSTRUCTION | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18COSC | SECURITY CAMERA INSTALLATION AT 372 EAST 152ND ST COURTLANDT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2018 | Dec 2019
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18COSC | SECURITY CAMERA INSTALLATION AT 372 EAST 152ND ST COURTLANDT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2019 | Dec 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18FSBO | Boiler Replacements at Pelham Parkway | 1 | DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18FSBO | Boiler Replacements at Pelham Parkway | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Sep 2018 | Mar 2018 | Sep 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18FSBO | Boiler Replacements at Pelham Parkway | 3 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18FSBO | Boiler Replacements at Pelham Parkway | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Mar 2020 | Sep 2018 | Sep 2019
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18FSBO | Boiler Replacements at Pelham Parkway | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Mar 2020 | Sep 2019 | Sep 2025
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PCCK | KITCHEN RENOVATION AT PATTERSON HOUSES COMMUNITY CENTER | 1 | DESIGN | Jan 2018 | Jun 2018 | Jan 2018 | Jun 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PCCK | KITCHEN RENOVATION AT PATTERSON HOUSES COMMUNITY CENTER | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PCCK | KITCHEN RENOVATION AT PATTERSON HOUSES COMMUNITY CENTER | 3 | CONSTRUCTION | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PCCK | KITCHEN RENOVATION AT PATTERSON HOUSES COMMUNITY CENTER | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2018 | Dec 2019
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PCCK | KITCHEN RENOVATION AT PATTERSON HOUSES COMMUNITY CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2019 | Dec 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SOCC | Sotomayor CC Cornerstone Program - Computer Technology | 1 | DESIGN | Jan 2018 | Jun 2018 | Jan 2018 | Jun 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SOCC | Sotomayor CC Cornerstone Program - Computer Technology | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SOCC | Sotomayor CC Cornerstone Program - Computer Technology | 3 | CONSTRUCTION | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SOCC | Sotomayor CC Cornerstone Program - Computer Technology | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2018 | Dec 2019
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SOCC | Sotomayor CC Cornerstone Program - Computer Technology | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2019 | Dec 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SOMO | SOTOMAYOR HOUSES/MONTEFIORE BEHAVIOR HC - PSYCH CENTER | 1 | DESIGN | Jan 2018 | Jun 2018 | Jan 2018 | Jun 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SOMO | SOTOMAYOR HOUSES/MONTEFIORE BEHAVIOR HC - PSYCH CENTER | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SOMO | SOTOMAYOR HOUSES/MONTEFIORE BEHAVIOR HC - PSYCH CENTER | 3 | CONSTRUCTION | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SOMO | SOTOMAYOR HOUSES/MONTEFIORE BEHAVIOR HC - PSYCH CENTER | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2018 | Dec 2019
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SOMO | SOTOMAYOR HOUSES/MONTEFIORE BEHAVIOR HC - PSYCH CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2019 | Dec 2027
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SVCC | Soundview CC Cornerstone Program - Computer Technology | 1 | DESIGN | Jan 2018 | Jun 2018 | Jan 2018 | Jun 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SVCC | Soundview CC Cornerstone Program - Computer Technology | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SVCC | Soundview CC Cornerstone Program - Computer Technology | 3 | CONSTRUCTION | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SVCC | Soundview CC Cornerstone Program - Computer Technology | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2018 | Dec 2019
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SVCC | Soundview CC Cornerstone Program - Computer Technology | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2019 | Dec 2025
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TNCR | THROGGS NECK COMMUNITY - ROOF RENOVATIONS | 1 | DESIGN | Oct 2017 | Apr 2018 | Oct 2017 | Apr 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TNCR | THROGGS NECK COMMUNITY - ROOF RENOVATIONS | 2 | BID AWARD AND REGISTER CONTRCT | Apr 2018 | Oct 2018 | Apr 2018 | Oct 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TNCR | THROGGS NECK COMMUNITY - ROOF RENOVATIONS | 3 | CONSTRUCTION | Oct 2018 | Oct 2019 | Oct 2018 | Oct 2019
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TNCR | THROGGS NECK COMMUNITY - ROOF RENOVATIONS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2019 | Apr 2020 | Oct 2018 | Oct 2019
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TNCR | THROGGS NECK COMMUNITY - ROOF RENOVATIONS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2019 | Apr 2020 | Oct 2019 | Oct 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19ADEL | ADAMS HOUSES ELEVATOR REPLACEMENT | 1 | DESIGN | Jun 2019 | Nov 2019 | Feb 2019 | Aug 2019
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19ADEL | ADAMS HOUSES ELEVATOR REPLACEMENT | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2019 | Apr 2020 | Aug 2019 | Jan 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19ADEL | ADAMS HOUSES ELEVATOR REPLACEMENT | 3 | CONSTRUCTION | Apr 2020 | Apr 2021 | Jan 2020 | Jan 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19ADEL | ADAMS HOUSES ELEVATOR REPLACEMENT | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2021 | Oct 2021 | Jan 2020 | Jan 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19ADEL | ADAMS HOUSES ELEVATOR REPLACEMENT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2021 | Oct 2021 | Jan 2021 | Jul 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BPWS | BUTLER HOUSES PLAYGROUND WATER SPRAYS | 1 | DESIGN | Jan 2019 | Jul 2019 | Jan 2019 | Jul 2019
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BPWS | BUTLER HOUSES PLAYGROUND WATER SPRAYS | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Jan 2020 | Jul 2019 | Jan 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BPWS | BUTLER HOUSES PLAYGROUND WATER SPRAYS | 3 | CONSTRUCTION | Jan 2020 | Jan 2021 | Jan 2020 | Jan 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BPWS | BUTLER HOUSES PLAYGROUND WATER SPRAYS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2021 | Jul 2021 | Jan 2020 | Jan 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BPWS | BUTLER HOUSES PLAYGROUND WATER SPRAYS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BRSC | BRONX RIVER SENIOR CENTER KITCHEN RENOVATIONS | 1 | DESIGN | Oct 2018 | Apr 2019 | Oct 2018 | Apr 2019
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BRSC | BRONX RIVER SENIOR CENTER KITCHEN RENOVATIONS | 2 | BID AWARD AND REGISTER CONTRCT | Apr 2019 | Oct 2019 | Apr 2019 | Oct 2019
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BRSC | BRONX RIVER SENIOR CENTER KITCHEN RENOVATIONS | 3 | CONSTRUCTION | Oct 2019 | Oct 2020 | Oct 2019 | Oct 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BRSC | BRONX RIVER SENIOR CENTER KITCHEN RENOVATIONS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2020 | Apr 2021 | Oct 2019 | Oct 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BRSC | BRONX RIVER SENIOR CENTER KITCHEN RENOVATIONS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2020 | Apr 2021 | Oct 2020 | Apr 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CAGR | CASTLE HILL HOUSES GAS RISER REPLACEMENTS | 1 | DESIGN | Jul 2019 | Jun 2020 | Mar 2019 | Mar 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CAGR | CASTLE HILL HOUSES GAS RISER REPLACEMENTS | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Dec 2020 | Mar 2020 | Sep 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CAGR | CASTLE HILL HOUSES GAS RISER REPLACEMENTS | 3 | CONSTRUCTION | Dec 2020 | Jun 2022 | Sep 2020 | Feb 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CAGR | CASTLE HILL HOUSES GAS RISER REPLACEMENTS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Sep 2022 | Sep 2020 | Feb 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CAGR | CASTLE HILL HOUSES GAS RISER REPLACEMENTS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Sep 2022 | Feb 2022 | May 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CASC | EAST 152ND-COURTLANDT AVENUE SECURITY CAMERAS | 1 | DESIGN | Jan 2018 | Jun 2018 | Jan 2018 | Jun 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CASC | EAST 152ND-COURTLANDT AVENUE SECURITY CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CASC | EAST 152ND-COURTLANDT AVENUE SECURITY CAMERAS | 3 | CONSTRUCTION | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CASC | EAST 152ND-COURTLANDT AVENUE SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2018 | Dec 2019
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CASC | EAST 152ND-COURTLANDT AVENUE SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2019 | Jun 2020 | Dec 2019 | Dec 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CMHP | MOORE HOUSES PLAYGROUND | 1 | DESIGN | Jan 2019 | Jul 2019 | Jan 2019 | Jul 2019
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CMHP | MOORE HOUSES PLAYGROUND | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Jan 2020 | Jul 2019 | Jan 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CMHP | MOORE HOUSES PLAYGROUND | 3 | CONSTRUCTION | Jan 2020 | Jan 2021 | Jan 2020 | Jan 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CMHP | MOORE HOUSES PLAYGROUND | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2021 | Jul 2021 | Jan 2020 | Jan 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CMHP | MOORE HOUSES PLAYGROUND | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MARE | MORRISANIA AIR RIGHTS ELEVATOR REPLACEMENT AT 3135 PARK AVE | 1 | DESIGN | Feb 2019 | Aug 2019 | Feb 2019 | Aug 2019
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MARE | MORRISANIA AIR RIGHTS ELEVATOR REPLACEMENT AT 3135 PARK AVE | 2 | BID AWARD AND REGISTER CONTRCT | Aug 2019 | Feb 2020 | Aug 2019 | Feb 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MARE | MORRISANIA AIR RIGHTS ELEVATOR REPLACEMENT AT 3135 PARK AVE | 3 | CONSTRUCTION | Feb 2020 | Feb 2021 | Feb 2020 | Feb 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MARE | MORRISANIA AIR RIGHTS ELEVATOR REPLACEMENT AT 3135 PARK AVE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Aug 2021 | Feb 2020 | Feb 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MARE | MORRISANIA AIR RIGHTS ELEVATOR REPLACEMENT AT 3135 PARK AVE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Aug 2021 | Feb 2021 | Aug 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19PHBC | PATTERSON HOUSES BASKETBALL COURT UPGRADE | 1 | DESIGN | Jan 2019 | Jul 2019 | Jan 2019 | Jul 2019
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19PHBC | PATTERSON HOUSES BASKETBALL COURT UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Jan 2020 | Jul 2019 | Jan 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19PHBC | PATTERSON HOUSES BASKETBALL COURT UPGRADE | 3 | CONSTRUCTION | Jan 2020 | Jan 2021 | Jan 2020 | Jan 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19PHBC | PATTERSON HOUSES BASKETBALL COURT UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2021 | Jul 2021 | Jan 2020 | Jan 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19PHBC | PATTERSON HOUSES BASKETBALL COURT UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2021 | Jul 2021 | Jan 2021 | Jul 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19UNSC | 1865 UNIVERSITY AVE- SECURITY CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | Oct 2019 | Apr 2020 | Oct 2019 | Apr 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19UNSC | 1865 UNIVERSITY AVE- SECURITY CAMERAS | 3 | CONSTRUCTION | Apr 2020 | Apr 2021 | Apr 2020 | Apr 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19UNSC | 1865 UNIVERSITY AVE- SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2021 | Oct 2021 | Apr 2020 | Apr 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19UNSC | 1865 UNIVERSITY AVE- SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2021 | Oct 2021 | Apr 2021 | Oct 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20EGCC | EASTCHESTER GARDENS COMMUNITY CENTER UPGRADE | 1 | DESIGN | Sep 2020 | Feb 2021 | Sep 2020 | Feb 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20EGCC | EASTCHESTER GARDENS COMMUNITY CENTER UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2021 | Aug 2021 | Feb 2021 | Aug 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20EGCC | EASTCHESTER GARDENS COMMUNITY CENTER UPGRADE | 3 | CONSTRUCTION | Aug 2021 | Aug 2022 | Aug 2021 | Aug 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20EGCC | EASTCHESTER GARDENS COMMUNITY CENTER UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2022 | Feb 2023 | Aug 2021 | Aug 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20EGCC | EASTCHESTER GARDENS COMMUNITY CENTER UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2022 | Feb 2023 | Aug 2022 | Feb 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GMEL | GOUVERNEUR MORRIS- GROUNDS | 1 | DESIGN | Sep 2019 | Feb 2020 | Sep 2019 | Feb 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GMEL | GOUVERNEUR MORRIS- GROUNDS | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Aug 2020 | Feb 2020 | Aug 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GMEL | GOUVERNEUR MORRIS- GROUNDS | 3 | CONSTRUCTION | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GMEL | GOUVERNEUR MORRIS- GROUNDS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2020 | Aug 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GMEL | GOUVERNEUR MORRIS- GROUNDS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2021 | Feb 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MCIE | JAMES MONROE HOUSES- CAMERAS, INSTALLATION, EQUIPMENT | 1 | DEVELOP SCOPE | Sep 2020 | Nov 2020 | Sep 2020 | Nov 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MCIE | JAMES MONROE HOUSES- CAMERAS, INSTALLATION, EQUIPMENT | 2 | PRELIMINARY DESIGN | Nov 2020 | Mar 2021 | Nov 2020 | Mar 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MCIE | JAMES MONROE HOUSES- CAMERAS, INSTALLATION, EQUIPMENT | 3 | FINAL DESIGN | Mar 2021 | Sep 2021 | Mar 2021 | Sep 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MCIE | JAMES MONROE HOUSES- CAMERAS, INSTALLATION, EQUIPMENT | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2021 | Dec 2021 | Sep 2021 | Dec 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MCIE | JAMES MONROE HOUSES- CAMERAS, INSTALLATION, EQUIPMENT | 5 | CONSTRUCTION TO 25% | Dec 2021 | Apr 2022 | Dec 2021 | Apr 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MCIE | JAMES MONROE HOUSES- CAMERAS, INSTALLATION, EQUIPMENT | 6 | CONSTRUCTION TO 50% | Apr 2022 | Aug 2022 | Apr 2022 | Aug 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MCIE | JAMES MONROE HOUSES- CAMERAS, INSTALLATION, EQUIPMENT | 7 | CONSTRUCTION TO 75% | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MCIE | JAMES MONROE HOUSES- CAMERAS, INSTALLATION, EQUIPMENT | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2022 | Mar 2023 | Dec 2022 | Mar 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MCIE | JAMES MONROE HOUSES- CAMERAS, INSTALLATION, EQUIPMENT | 9 | SUBSTANTIAL COMPLETION | Mar 2023 | May 2023 | Mar 2023 | May 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MCIE | JAMES MONROE HOUSES- CAMERAS, INSTALLATION, EQUIPMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2023 | Jun 2023 | May 2023 | Jun 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MHGR | MONTEREY HOUSES-RENOVATIONS TO PLAYGROUND | 1 | DEVELOP SCOPE | Sep 2020 | Nov 2020 | Sep 2020 | Nov 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MHGR | MONTEREY HOUSES-RENOVATIONS TO PLAYGROUND | 2 | PRELIMINARY DESIGN | Nov 2020 | Mar 2021 | Nov 2020 | Mar 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MHGR | MONTEREY HOUSES-RENOVATIONS TO PLAYGROUND | 3 | FINAL DESIGN | Mar 2021 | Sep 2021 | Mar 2021 | Sep 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MHGR | MONTEREY HOUSES-RENOVATIONS TO PLAYGROUND | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2021 | Dec 2021 | Sep 2021 | Dec 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MHGR | MONTEREY HOUSES-RENOVATIONS TO PLAYGROUND | 5 | CONSTRUCTION TO 25% | Dec 2021 | Apr 2022 | Dec 2021 | Apr 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MHGR | MONTEREY HOUSES-RENOVATIONS TO PLAYGROUND | 6 | CONSTRUCTION TO 50% | Apr 2022 | Aug 2022 | Apr 2022 | Aug 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MHGR | MONTEREY HOUSES-RENOVATIONS TO PLAYGROUND | 7 | CONSTRUCTION TO 75% | Aug 2022 | Dec 2022 | Aug 2022 | Aug 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MHGR | MONTEREY HOUSES-RENOVATIONS TO PLAYGROUND | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2022 | Mar 2023 | Aug 2024 | Nov 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MHGR | MONTEREY HOUSES-RENOVATIONS TO PLAYGROUND | 9 | SUBSTANTIAL COMPLETION | Mar 2023 | May 2023 | Nov 2024 | Jan 2025
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MHGR | MONTEREY HOUSES-RENOVATIONS TO PLAYGROUND | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2023 | Jun 2023 | Jan 2025 | Feb 2025
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MLPC | MILLBROOK- LIGHTS, PLAYGROUNDS UPGRADES AND CAMERAS | 1 | DESIGN | Sep 2019 | Feb 2020 | Sep 2019 | Feb 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MLPC | MILLBROOK- LIGHTS, PLAYGROUNDS UPGRADES AND CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Aug 2020 | Feb 2020 | Aug 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MLPC | MILLBROOK- LIGHTS, PLAYGROUNDS UPGRADES AND CAMERAS | 3 | CONSTRUCTION | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MLPC | MILLBROOK- LIGHTS, PLAYGROUNDS UPGRADES AND CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2020 | Aug 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MLPC | MILLBROOK- LIGHTS, PLAYGROUNDS UPGRADES AND CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2021 | Feb 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20PSCC | PARKSIDE COMMUNITY CENTER UPGRADE | 1 | DEVELOP SCOPE | Sep 2020 | Nov 2020 | Sep 2020 | Nov 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20PSCC | PARKSIDE COMMUNITY CENTER UPGRADE | 2 | PRELIMINARY DESIGN | Nov 2020 | Mar 2021 | Nov 2020 | Mar 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20PSCC | PARKSIDE COMMUNITY CENTER UPGRADE | 3 | FINAL DESIGN | Mar 2021 | Sep 2021 | Mar 2021 | Sep 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20PSCC | PARKSIDE COMMUNITY CENTER UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2021 | Dec 2021 | Sep 2021 | Dec 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20PSCC | PARKSIDE COMMUNITY CENTER UPGRADE | 5 | CONSTRUCTION TO 25% | Dec 2021 | Apr 2022 | Dec 2021 | Apr 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20PSCC | PARKSIDE COMMUNITY CENTER UPGRADE | 6 | CONSTRUCTION TO 50% | Apr 2022 | Aug 2022 | Apr 2022 | Aug 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20PSCC | PARKSIDE COMMUNITY CENTER UPGRADE | 7 | CONSTRUCTION TO 75% | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20PSCC | PARKSIDE COMMUNITY CENTER UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2022 | Mar 2023 | Dec 2022 | Mar 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20PSCC | PARKSIDE COMMUNITY CENTER UPGRADE | 9 | SUBSTANTIAL COMPLETION | Mar 2023 | May 2023 | Mar 2023 | May 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20PSCC | PARKSIDE COMMUNITY CENTER UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2023 | Jun 2023 | May 2023 | Jun 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SEED | SEDGWICK HOUSES ENHANCEMENT ENTRANCE DOORS AND CCTV | 1 | DESIGN | Sep 2019 | Feb 2020 | Sep 2019 | Feb 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SEED | SEDGWICK HOUSES ENHANCEMENT ENTRANCE DOORS AND CCTV | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Aug 2020 | Feb 2020 | Aug 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SEED | SEDGWICK HOUSES ENHANCEMENT ENTRANCE DOORS AND CCTV | 3 | CONSTRUCTION | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SEED | SEDGWICK HOUSES ENHANCEMENT ENTRANCE DOORS AND CCTV | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2020 | Aug 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SEED | SEDGWICK HOUSES ENHANCEMENT ENTRANCE DOORS AND CCTV | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2021 | Aug 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21BRST | BRONX RIVER UNDERGROUND STEAM | 1 | DESIGN | May 2022 | Nov 2022 | May 2022 | Nov 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21BRST | BRONX RIVER UNDERGROUND STEAM | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2022 | May 2023 | Nov 2022 | May 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21BRST | BRONX RIVER UNDERGROUND STEAM | 3 | CONSTRUCTION | May 2023 | May 2024 | May 2023 | May 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21BRST | BRONX RIVER UNDERGROUND STEAM | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2023 | May 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21BRST | BRONX RIVER UNDERGROUND STEAM | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21EWGR | EDENWALD GAS RISERS #6 | 1 | DESIGN | Jul 2020 | Jun 2021 | Jan 2025 | Dec 2025
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21EWGR | EDENWALD GAS RISERS #6 | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Nov 2021 | Jan 2026 | May 2026
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21EWGR | EDENWALD GAS RISERS #6 | 3 | CONSTRUCTION | Nov 2021 | Jun 2023 | May 2026 | Dec 2027
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21EWGR | EDENWALD GAS RISERS #6 | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2023 | Sep 2023 | May 2026 | Dec 2027
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21EWGR | EDENWALD GAS RISERS #6 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2023 | Sep 2023 | Dec 2027 | Mar 2028
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21HMCC | MONROE HOUSES- COMMUNITY CENTER | 1 | DESIGN | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21HMCC | MONROE HOUSES- COMMUNITY CENTER | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21HMCC | MONROE HOUSES- COMMUNITY CENTER | 3 | CONSTRUCTION | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21HMCC | MONROE HOUSES- COMMUNITY CENTER | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2021 | Jun 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21HMCC | MONROE HOUSES- COMMUNITY CENTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHCC | UPGRADE COMMUNITY CENTER MOTT HAVEN | 1 | DESIGN | Sep 2019 | Feb 2020 | Sep 2019 | Feb 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHCC | UPGRADE COMMUNITY CENTER MOTT HAVEN | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Aug 2020 | Feb 2020 | Aug 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHCC | UPGRADE COMMUNITY CENTER MOTT HAVEN | 3 | CONSTRUCTION | Aug 2020 | Aug 2021 | Aug 2020 | Aug 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHCC | UPGRADE COMMUNITY CENTER MOTT HAVEN | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2020 | Aug 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHCC | UPGRADE COMMUNITY CENTER MOTT HAVEN | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2021 | Feb 2022 | Aug 2024 | Feb 2025
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHOA | NYCHA MONTEREY HOUSES-OUTDOOR AREA RENOVATIONS | 1 | DESIGN | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHOA | NYCHA MONTEREY HOUSES-OUTDOOR AREA RENOVATIONS | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHOA | NYCHA MONTEREY HOUSES-OUTDOOR AREA RENOVATIONS | 3 | CONSTRUCTION | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHOA | NYCHA MONTEREY HOUSES-OUTDOOR AREA RENOVATIONS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2021 | Jun 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHOA | NYCHA MONTEREY HOUSES-OUTDOOR AREA RENOVATIONS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MICC | UPGRADE COMMUNITY CENTER MITCHEL | 1 | DESIGN | Jan 2021 | Jun 2021 | Jan 2021 | Jun 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MICC | UPGRADE COMMUNITY CENTER MITCHEL | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MICC | UPGRADE COMMUNITY CENTER MITCHEL | 3 | CONSTRUCTION | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MICC | UPGRADE COMMUNITY CENTER MITCHEL | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2022 | Jun 2023 | Dec 2021 | Dec 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MICC | UPGRADE COMMUNITY CENTER MITCHEL | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MLCC | UPGRADE COMMUNITY CENTER MILLBROOK | 1 | DESIGN | Sep 2021 | Mar 2022 | Sep 2021 | Mar 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MLCC | UPGRADE COMMUNITY CENTER MILLBROOK | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2022 | Sep 2022 | Mar 2022 | Sep 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MLCC | UPGRADE COMMUNITY CENTER MILLBROOK | 3 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MLCC | UPGRADE COMMUNITY CENTER MILLBROOK | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Mar 2024 | Sep 2022 | Sep 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MLCC | UPGRADE COMMUNITY CENTER MILLBROOK | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Mar 2024 | Sep 2023 | Mar 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MMMP | UPGRADES TO MILL BROOK, MITCHELL, MOTT HAVEN AND PATTERSON | 1 | DESIGN | Jun 2021 | Dec 2021 | Jun 2021 | Dec 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MMMP | UPGRADES TO MILL BROOK, MITCHELL, MOTT HAVEN AND PATTERSON | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2021 | Jun 2022 | Dec 2021 | Jun 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MMMP | UPGRADES TO MILL BROOK, MITCHELL, MOTT HAVEN AND PATTERSON | 3 | CONSTRUCTION | Jun 2022 | Jun 2023 | Jun 2022 | Jun 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MMMP | UPGRADES TO MILL BROOK, MITCHELL, MOTT HAVEN AND PATTERSON | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2023 | Dec 2023 | Jun 2022 | Jun 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MMMP | UPGRADES TO MILL BROOK, MITCHELL, MOTT HAVEN AND PATTERSON | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2023 | Dec 2023 | Jun 2023 | Dec 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21PHCC | UPGRADE COMMUNITY CENTER PATTERSON | 1 | DESIGN | Sep 2021 | Mar 2022 | Sep 2021 | Mar 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21PHCC | UPGRADE COMMUNITY CENTER PATTERSON | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2022 | Sep 2022 | Mar 2022 | Sep 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21PHCC | UPGRADE COMMUNITY CENTER PATTERSON | 3 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21PHCC | UPGRADE COMMUNITY CENTER PATTERSON | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Mar 2024 | Sep 2022 | Sep 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21PHCC | UPGRADE COMMUNITY CENTER PATTERSON | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Mar 2024 | Sep 2023 | Mar 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SORF | SOTOMAYOR BRICKS AND ROOFS | 1 | DESIGN | Oct 2021 | Apr 2022 | Oct 2021 | Apr 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SORF | SOTOMAYOR BRICKS AND ROOFS | 2 | BID AWARD AND REGISTER CONTRCT | Apr 2022 | Sep 2022 | Apr 2022 | Sep 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SORF | SOTOMAYOR BRICKS AND ROOFS | 3 | CONSTRUCTION | Oct 2022 | Sep 2023 | Oct 2022 | Sep 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SORF | SOTOMAYOR BRICKS AND ROOFS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2023 | Mar 2024 | Oct 2022 | Sep 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SORF | SOTOMAYOR BRICKS AND ROOFS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2023 | Mar 2024 | Oct 2023 | Mar 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21WMCI | SECURITY CAMERA INSTALLATION AT WEBSTER MORRISANIA | 1 | DESIGN | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21WMCI | SECURITY CAMERA INSTALLATION AT WEBSTER MORRISANIA | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21WMCI | SECURITY CAMERA INSTALLATION AT WEBSTER MORRISANIA | 3 | CONSTRUCTION | Jun 2021 | Jun 2022 | Jun 2021 | Jun 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21WMCI | SECURITY CAMERA INSTALLATION AT WEBSTER MORRISANIA | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2021 | Jun 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21WMCI | SECURITY CAMERA INSTALLATION AT WEBSTER MORRISANIA | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22MHIL | MONTEREY HOUSES SECURITY CAMERAS | 1 | DESIGN | May 2022 | Nov 2022 | May 2022 | Nov 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22MHIL | MONTEREY HOUSES SECURITY CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2022 | May 2023 | Nov 2022 | May 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22MHIL | MONTEREY HOUSES SECURITY CAMERAS | 3 | CONSTRUCTION | May 2023 | May 2024 | May 2023 | May 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22MHIL | MONTEREY HOUSES SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2023 | May 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22MHIL | MONTEREY HOUSES SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22MHPF | MARBLE HILL HOUSES- PERIMETER FENCING | 1 | DESIGN | May 2022 | Nov 2022 | May 2022 | Nov 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22MHPF | MARBLE HILL HOUSES- PERIMETER FENCING | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2022 | May 2023 | Nov 2022 | May 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22MHPF | MARBLE HILL HOUSES- PERIMETER FENCING | 3 | CONSTRUCTION | May 2023 | May 2024 | May 2023 | May 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22MHPF | MARBLE HILL HOUSES- PERIMETER FENCING | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2023 | May 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22MHPF | MARBLE HILL HOUSES- PERIMETER FENCING | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22MHRC | MARBLE HILL- TECHNOLOFY UPGRADE - ROOF CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | Apr 2022 | Sep 2022 | Apr 2022 | Sep 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22MHRC | MARBLE HILL- TECHNOLOFY UPGRADE - ROOF CAMERAS | 3 | CONSTRUCTION | Oct 2022 | Sep 2023 | Oct 2022 | Sep 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22MHRC | MARBLE HILL- TECHNOLOFY UPGRADE - ROOF CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2023 | Mar 2024 | Oct 2022 | Sep 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22MHRC | MARBLE HILL- TECHNOLOFY UPGRADE - ROOF CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2023 | Mar 2024 | Oct 2023 | Mar 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22MUIL | MURPHY HOUSES- INTERIOR LIGHTING & CAMERAS | 1 | DESIGN | May 2022 | Nov 2022 | May 2022 | Nov 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22MUIL | MURPHY HOUSES- INTERIOR LIGHTING & CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2022 | May 2023 | Nov 2022 | May 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22MUIL | MURPHY HOUSES- INTERIOR LIGHTING & CAMERAS | 3 | CONSTRUCTION | May 2023 | May 2024 | May 2023 | May 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22MUIL | MURPHY HOUSES- INTERIOR LIGHTING & CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2023 | May 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22MUIL | MURPHY HOUSES- INTERIOR LIGHTING & CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22PHIL | PARKSIDE HOUSES- CCTV | 1 | DESIGN | May 2022 | Nov 2022 | May 2022 | Nov 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22PHIL | PARKSIDE HOUSES- CCTV | 2 | BID AWARD AND REGISTER CONTRCT | Nov 2022 | May 2023 | Nov 2022 | May 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22PHIL | PARKSIDE HOUSES- CCTV | 3 | CONSTRUCTION | May 2023 | May 2024 | May 2023 | May 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22PHIL | PARKSIDE HOUSES- CCTV | 4 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2023 | May 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22PHIL | PARKSIDE HOUSES- CCTV | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SMRA | SAINT MARYS HOUSES- ADA RAMP | 1 | DESIGN | Oct 2021 | Apr 2022 | Oct 2021 | Apr 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SMRA | SAINT MARYS HOUSES- ADA RAMP | 2 | BID AWARD AND REGISTER CONTRCT | Apr 2022 | Oct 2022 | Apr 2022 | Oct 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SMRA | SAINT MARYS HOUSES- ADA RAMP | 3 | CONSTRUCTION | Oct 2022 | Oct 2023 | Oct 2022 | Oct 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SMRA | SAINT MARYS HOUSES- ADA RAMP | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2023 | Apr 2024 | Oct 2022 | Oct 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SMRA | SAINT MARYS HOUSES- ADA RAMP | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2023 | Apr 2024 | Oct 2023 | Apr 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SREB | Heating at Soundview Houses | 1 | DESIGN | Jan 2022 | Jun 2022 | Jan 2022 | Jun 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SREB | Heating at Soundview Houses | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SREB | Heating at Soundview Houses | 3 | CONSTRUCTION | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SREB | Heating at Soundview Houses | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jun 2024 | Dec 2022 | Dec 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SREB | Heating at Soundview Houses | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM23BRSE | BOSTON RD PLAZA SECURITY CAMERAS | 1 | DESIGN | Jan 2023 | Jun 2023 | Jan 2023 | Jun 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM23BRSE | BOSTON RD PLAZA SECURITY CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Dec 2023 | Jul 2023 | Dec 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM23BRSE | BOSTON RD PLAZA SECURITY CAMERAS | 3 | CONSTRUCTION | Dec 2023 | Dec 2024 | Dec 2023 | Dec 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM23BRSE | BOSTON RD PLAZA SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2024 | Jun 2025 | Dec 2023 | Dec 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM23BRSE | BOSTON RD PLAZA SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM23DHSC | DYCKMAN HOUSES - SECURITY CAMERAS | 1 | DESIGN | Jan 2023 | Jun 2023 | Jan 2023 | Jun 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM23DHSC | DYCKMAN HOUSES - SECURITY CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Dec 2023 | Jul 2023 | Dec 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM23DHSC | DYCKMAN HOUSES - SECURITY CAMERAS | 3 | CONSTRUCTION | Dec 2023 | Dec 2024 | Dec 2023 | Dec 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM23DHSC | DYCKMAN HOUSES - SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2024 | Jun 2025 | Dec 2023 | Dec 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM23DHSC | DYCKMAN HOUSES - SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM23GHSC | GUN HILL HOUSES - NEW SECURITY CAMERAS | 1 | DESIGN | Jan 2023 | Jun 2023 | Jan 2023 | Jun 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM23GHSC | GUN HILL HOUSES - NEW SECURITY CAMERAS | 2 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Dec 2023 | Jun 2023 | Dec 2023
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM23GHSC | GUN HILL HOUSES - NEW SECURITY CAMERAS | 3 | CONSTRUCTION | Dec 2023 | Dec 2024 | Dec 2023 | Dec 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM23GHSC | GUN HILL HOUSES - NEW SECURITY CAMERAS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2024 | Jun 2025 | Dec 2023 | Dec 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM23GHSC | GUN HILL HOUSES - NEW SECURITY CAMERAS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM23MRSC | MARBLE HILL - COMMUNITY/SENIOR CENTER UPGRADE | 1 | DESIGN | Jun 2024 | Dec 2024 | Jun 2024 | Dec 2024
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM23MRSC | MARBLE HILL - COMMUNITY/SENIOR CENTER UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM23MRSC | MARBLE HILL - COMMUNITY/SENIOR CENTER UPGRADE | 3 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM23MRSC | MARBLE HILL - COMMUNITY/SENIOR CENTER UPGRADE | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Dec 2026 | Jun 2025 | Jun 2026
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM23MRSC | MARBLE HILL - COMMUNITY/SENIOR CENTER UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Dec 2026 | Jun 2026 | Dec 2026
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM24CHBR | CASTLE HILL BATHROOMS | 1 | DESIGN | Jun 2024 | Dec 2025 | Jun 2024 | Dec 2025
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM24CHBR | CASTLE HILL BATHROOMS | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2025 | May 2026 | Dec 2025 | May 2026
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM24CHBR | CASTLE HILL BATHROOMS | 3 | CONSTRUCTION | May 2026 | Dec 2027 | May 2026 | Dec 2027
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM24CHBR | CASTLE HILL BATHROOMS | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2027 | Mar 2028 | May 2026 | Dec 2027
20231026 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM24CHBR | CASTLE HILL BATHROOMS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2027 | Mar 2028 | Dec 2027 | Mar 2028
20231026 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH211 | DOH - Morrisania Health Center - Boiler Plant Upgrade | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2022 | Jun 2022 | Jun 2022
20231026 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH211 | DOH - Morrisania Health Center - Boiler Plant Upgrade | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Aug 2022 | Jul 2022 | Aug 2022
20231026 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH211 | DOH - Morrisania Health Center - Boiler Plant Upgrade | 3 | CONSTRUCTION TO 50% | Aug 2022 | Feb 2023 | Aug 2022 | Feb 2023
20231026 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH211 | DOH - Morrisania Health Center - Boiler Plant Upgrade | 4 | CONSTRUCTION TO 75% | Feb 2023 | May 2023 | Feb 2023 | May 2023
20231026 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH211 | DOH - Morrisania Health Center - Boiler Plant Upgrade | 5 | SUBSTANTIAL COMPLETION | May 2023 | Jul 2023 | May 2023 | Jul 2023
20231026 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH211 | DOH - Morrisania Health Center - Boiler Plant Upgrade | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82GLEEB | BUILDING RENOVATION - 2527 GLEBE AVE, BRONX, NY | 1 | DESIGN | Jan 2019 | Jul 2019 | Jan 2019 | Jul 2019
20231026 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82GLEEB | BUILDING RENOVATION - 2527 GLEBE AVE, BRONX, NY | 2 | CONSTRUCTION | Jul 2019 | Jul 2020 | Jul 2019 | Jul 2020
20231026 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82GLEEB | BUILDING RENOVATION - 2527 GLEBE AVE, BRONX, NY | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2020 | Jan 2021 | Jul 2020 | Dec 2025
20231026 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82MORHC | Morrisania Health Center interior renovation | 1 | DESIGN | Jan 2020 | May 2021 | Aug 2027 | Jan 2028
20231026 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82MORHC | Morrisania Health Center interior renovation | 2 | CONSTRUCTION | May 2021 | May 2026 | Aug 2028 | Aug 2030
20231026 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82MORHC | Morrisania Health Center interior renovation | 3 | PUNCHLIST COMPLETE, JOB CLOSED | May 2026 | May 2026 | Dec 2030 | Jan 2031
20231026 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82MORHC | Morrisania Health Center interior renovation | 4 | DEVELOP SCOPE | May 2026 | May 2026 | Dec 2030 | Jan 2031
20231026 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82MORHC | Morrisania Health Center interior renovation | 5 | PRELIMINARY DESIGN | May 2026 | May 2026 | Dec 2030 | Jan 2031
20231026 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82MORHC | Morrisania Health Center interior renovation | 6 | FINAL DESIGN | May 2026 | May 2026 | Dec 2030 | Jan 2031
20231026 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82MORHC | Morrisania Health Center interior renovation | 7 | BID AWARD AND REGISTER CONTRCT | May 2026 | May 2026 | Dec 2030 | Jan 2031
20231026 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82MORHC | Morrisania Health Center interior renovation | 8 | CONSTRUCTION TO 25% | May 2026 | May 2026 | Dec 2030 | Jan 2031
20231026 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82MORHC | Morrisania Health Center interior renovation | 9 | CONSTRUCTION TO 50% | May 2026 | May 2026 | Dec 2030 | Jan 2031
20231026 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82MORHC | Morrisania Health Center interior renovation | 10 | CONSTRUCTION TO 75% | May 2026 | May 2026 | Dec 2030 | Jan 2031
20231026 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82MORHC | Morrisania Health Center interior renovation | 11 | ORIGINAL EQUIP & FURNISHING | May 2026 | May 2026 | Dec 2030 | Jan 2031
20231026 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82MORHC | Morrisania Health Center interior renovation | 12 | SUBSTANTIAL COMPLETION | May 2026 | May 2026 | Dec 2030 | Jan 2031
20231026 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82MORHC | Morrisania Health Center interior renovation | 13 | PUNCHLIST COMPLETE, JOB CLOSED | May 2026 | Jun 2026 | Dec 2030 | Jan 2031
20231026 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82ZERGA | LEASE SPACE RENOVATION - 1235 ZEREGA AVENUE, BRONX, NY | 1 | DESIGN | Mar 2019 | Sep 2019 | Mar 2019 | Sep 2019
20231026 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82ZERGA | LEASE SPACE RENOVATION - 1235 ZEREGA AVENUE, BRONX, NY | 2 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Jan 2022
20231026 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82ZERGA | LEASE SPACE RENOVATION - 1235 ZEREGA AVENUE, BRONX, NY | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Mar 2021 | Jan 2022 | Mar 2024
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 02201801 | JACOBI: BUILDING #4 RENOVATIONS | 1 | DESIGN | Aug 2018 | Jul 2019 | Aug 2018 | Jun 2024
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 02201801 | JACOBI: BUILDING #4 RENOVATIONS | 2 | CONSTRUCTION | Jul 2019 | Jun 2020 | Aug 2018 | Jun 2024
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 02201801 | JACOBI: BUILDING #4 RENOVATIONS | 3 | CONSTRUCTION | Jul 2019 | Jun 2020 | Jul 2024 | Jun 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 02201802 | JACOBI: CONSTRUCT PLAYGROUND FOR THE PEDIATRIC DEPT | 2 | CONSTRUCTION | Jan 2019 | Dec 2019 | Feb 2018 | Dec 2018
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 02201802 | JACOBI: CONSTRUCT PLAYGROUND FOR THE PEDIATRIC DEPT | 3 | CONSTRUCTION | Jan 2019 | Dec 2019 | Jan 2019 | Dec 2024
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 11202209 | BEL: ANTI LIGATURE RENOVATIONS TO BH UNITS | 1 | DESIGN | Jun 2022 | Oct 2023 | Jun 2022 | Oct 2023
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 11202209 | BEL: ANTI LIGATURE RENOVATIONS TO BH UNITS | 2 | CONSTRUCTION | Oct 2023 | Oct 2026 | Oct 2023 | Oct 2026
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 11202209 | BEL: ANTI LIGATURE RENOVATIONS TO BH UNITS | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 20201501 | BELVIS: PEDIATRIC SUITE MODERNIZATION | 1 | DESIGN | Jul 2019 | Jan 2020 | Jun 2032 | Jun 2032
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 20201501 | BELVIS: PEDIATRIC SUITE MODERNIZATION | 2 | CONSTRUCTION | Jan 2020 | Jun 2020 | Jun 2032 | Nov 2032
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 20201801 | BELVIS: REPLACEMENT OF MAIN ENTRANCE DOORS | 2 | CONSTRUCTION | Jan 2020 | Jun 2020 | Jan 2020 | Jun 2020
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 20202201 | BELVIS: Security System | 1 | DESIGN | Jun 2022 | Oct 2023 | Jun 2022 | Oct 2023
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 20202201 | BELVIS: Security System | 2 | CONSTRUCTION | Oct 2023 | Oct 2026 | Oct 2023 | Oct 2026
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 20202201 | BELVIS: Security System | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21201601 | JACOBI: LOCAL LAW 11 COMPLIANCE | 1 | DESIGN | Aug 2019 | Jun 2020 | Aug 2019 | Jun 2020
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21201601 | JACOBI: LOCAL LAW 11 COMPLIANCE | 2 | CONSTRUCTION | Jul 2020 | Jun 2021 | Aug 2019 | Jun 2020
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21201601 | JACOBI: LOCAL LAW 11 COMPLIANCE | 3 | CONSTRUCTION | Jul 2020 | Jun 2021 | Jul 2020 | Jun 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21201751 | JACOBI: PURCHASE NEW MRI & Construction | 1 | DESIGN | Jun 2020 | Oct 2021 | Jun 2020 | Oct 2021
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21201751 | JACOBI: PURCHASE NEW MRI & Construction | 2 | CONSTRUCTION | Oct 2021 | Oct 2024 | Oct 2021 | Oct 2024
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21201751 | JACOBI: PURCHASE NEW MRI & Construction | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202001 | JACOBI CHILLERS FOR MRI UNIT | 1 | DESIGN | Sep 2019 | Feb 2021 | Aug 2021 | Jun 2032
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202001 | JACOBI CHILLERS FOR MRI UNIT | 2 | CONSTRUCTION | Feb 2021 | Feb 2024 | Jun 2032 | Jun 2035
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202001 | JACOBI CHILLERS FOR MRI UNIT | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2024 | May 2024 | Jun 2035 | Aug 2035
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202004 | JACOBI: WELLNESS GYM | 1 | DESIGN | Jan 2020 | May 2021 | Jan 2021 | May 2022
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202004 | JACOBI: WELLNESS GYM | 2 | CONSTRUCTION | May 2021 | May 2023 | May 2022 | May 2024
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202004 | JACOBI: WELLNESS GYM | 3 | PUNCHLIST COMPLETE, JOB CLOSED | May 2023 | Aug 2023 | May 2024 | Aug 2024
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202101 | JACOBI: HVAC SYSTEM LAB UPGRADE | 1 | DESIGN | Feb 2021 | Jun 2022 | Feb 2021 | Jun 2022
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202101 | JACOBI: HVAC SYSTEM LAB UPGRADE | 2 | CONSTRUCTION | Jun 2022 | Jun 2025 | Jun 2022 | Jun 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202101 | JACOBI: HVAC SYSTEM LAB UPGRADE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202108 | JACOBI COMPOUNDING USP 797/800 COMPLIANCE | 1 | DESIGN | Feb 2021 | Jun 2022 | Feb 2021 | Jun 2022
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202108 | JACOBI COMPOUNDING USP 797/800 COMPLIANCE | 2 | CONSTRUCTION | Jun 2022 | Jun 2025 | Jun 2022 | Jun 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202108 | JACOBI COMPOUNDING USP 797/800 COMPLIANCE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202109 | JACOBI: Post-Partum Renovation in Building # 1 | 1 | DESIGN | Feb 2021 | Jun 2022 | Feb 2021 | Jun 2022
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202109 | JACOBI: Post-Partum Renovation in Building # 1 | 2 | CONSTRUCTION | Jun 2022 | Jun 2025 | Jun 2022 | Jun 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202109 | JACOBI: Post-Partum Renovation in Building # 1 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202110 | JACOBI: 11E OR ROOMS UPGRADE | 1 | DESIGN | Feb 2021 | Jun 2022 | Feb 2021 | Jun 2022
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202110 | JACOBI: 11E OR ROOMS UPGRADE | 2 | CONSTRUCTION | Jun 2022 | Jun 2025 | Jun 2022 | Jun 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202110 | JACOBI: 11E OR ROOMS UPGRADE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202111 | JACOBI: SPRINKLER SYSTEM UPGRADE BUILDING 4 | 1 | DESIGN | Feb 2021 | Jun 2022 | Feb 2021 | Jun 2022
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202111 | JACOBI: SPRINKLER SYSTEM UPGRADE BUILDING 4 | 2 | CONSTRUCTION | Jun 2022 | Jun 2025 | Jun 2022 | Jun 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202111 | JACOBI: SPRINKLER SYSTEM UPGRADE BUILDING 4 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202112 | JACOBI: FIRE ALARM SYSTEM BLDG 1 | 1 | DESIGN | Feb 2021 | Jun 2022 | Feb 2021 | Jun 2022
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202112 | JACOBI: FIRE ALARM SYSTEM BLDG 1 | 2 | CONSTRUCTION | Jun 2022 | Jun 2025 | Jun 2022 | Jun 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202112 | JACOBI: FIRE ALARM SYSTEM BLDG 1 | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202144 | JACOBI : NUCLEAR CAMERA & Construction | 1 | DESIGN | Jun 2024 | Nov 2025 | Jun 2024 | Nov 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202144 | JACOBI : NUCLEAR CAMERA & Construction | 2 | CONSTRUCTION | Nov 2025 | Nov 2028 | Nov 2025 | Nov 2028
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202144 | JACOBI : NUCLEAR CAMERA & Construction | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2028 | Feb 2029 | Nov 2028 | Feb 2029
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202242 | JACOBI: Central Sterile & Construction | 1 | DESIGN | Jun 2023 | Nov 2024 | Jun 2023 | Nov 2024
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202242 | JACOBI: Central Sterile & Construction | 2 | CONSTRUCTION | Nov 2024 | Nov 2027 | Nov 2024 | Nov 2027
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202242 | JACOBI: Central Sterile & Construction | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2027 | Feb 2028 | Nov 2027 | Feb 2028
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202301 | Jacobi: Hyperbaric Area Upgrade | 1 | DESIGN | Jun 2022 | Nov 2023 | Jun 2022 | Nov 2023
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202301 | Jacobi: Hyperbaric Area Upgrade | 2 | CONSTRUCTION | Nov 2023 | Nov 2026 | Nov 2023 | Nov 2026
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202301 | Jacobi: Hyperbaric Area Upgrade | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Feb 2027 | Nov 2026 | Feb 2027
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202303 | Jacobi Retail Pharmacy | 1 | DESIGN | Oct 2023 | Sep 2024 | Oct 2023 | Sep 2024
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202303 | Jacobi Retail Pharmacy | 2 | CONSTRUCTION | Sep 2024 | Sep 2027 | Sep 2024 | Sep 2027
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202303 | Jacobi Retail Pharmacy | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Dec 2027 | Sep 2027 | Dec 2027
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24201502 | NCB: OB/GYN NURSING UNIT UPGRADE | 1 | DESIGN | Dec 2013 | Jun 2014 | Dec 2015 | Jun 2016
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24201502 | NCB: OB/GYN NURSING UNIT UPGRADE | 2 | CONSTRUCTION | Jun 2014 | Dec 2014 | Jun 2016 | Dec 2027
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24201610 | RENOVATE TREMONT HEALTH CLINIC | 1 | DESIGN | Dec 2015 | Jun 2016 | Jan 2016 | Jan 2033
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24201610 | RENOVATE TREMONT HEALTH CLINIC | 2 | CONSTRUCTION | Jun 2016 | Nov 2016 | Jun 2022 | Jun 2032
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24201901 | NCB: FACADE REHABILITATION & WINDOW REPLACEMENT | 1 | DESIGN | Aug 2020 | Jun 2021 | Aug 2022 | Jul 2023
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24201901 | NCB: FACADE REHABILITATION & WINDOW REPLACEMENT | 2 | CONSTRUCTION | Jul 2021 | Jun 2022 | Aug 2022 | Jul 2023
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24201901 | NCB: FACADE REHABILITATION & WINDOW REPLACEMENT | 3 | CONSTRUCTION | Jul 2021 | Jun 2022 | Jul 2023 | Jun 2024
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24201920 | NCB: REPLACE DISHWASHER | 1 | DESIGN | Feb 2021 | Jun 2022 | Feb 2021 | Jun 2022
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24201920 | NCB: REPLACE DISHWASHER | 2 | CONSTRUCTION | Jun 2022 | Jun 2025 | Jun 2022 | Jun 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24201920 | NCB: REPLACE DISHWASHER | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202001 | NCB - ELEVATOR UPGRADE | 1 | DESIGN | Apr 2020 | Sep 2021 | Apr 2020 | Sep 2021
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202001 | NCB - ELEVATOR UPGRADE | 2 | CONSTRUCTION | Sep 2021 | Sep 2023 | Sep 2021 | Sep 2023
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202001 | NCB - ELEVATOR UPGRADE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Dec 2023 | Sep 2023 | Jun 2032
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202102 | NCB: NEW EMERGENCY GENERATOR | 1 | DESIGN | Jun 2022 | Oct 2023 | Jun 2022 | Oct 2023
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202102 | NCB: NEW EMERGENCY GENERATOR | 2 | CONSTRUCTION | Oct 2023 | Oct 2026 | Oct 2023 | Oct 2026
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202102 | NCB: NEW EMERGENCY GENERATOR | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202104 | NCB OR RENOVATIONS | 1 | DESIGN | Jun 2021 | Oct 2022 | Jun 2021 | Oct 2022
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202104 | NCB OR RENOVATIONS | 2 | CONSTRUCTION | Oct 2022 | Oct 2025 | Oct 2022 | Oct 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202104 | NCB OR RENOVATIONS | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202202 | NCB: RADIOLOGY DR ROOM | 1 | DESIGN | Jun 2021 | Oct 2022 | Jun 2021 | Oct 2022
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202202 | NCB: RADIOLOGY DR ROOM | 2 | CONSTRUCTION | Oct 2022 | Oct 2025 | Oct 2022 | Oct 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202202 | NCB: RADIOLOGY DR ROOM | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202204 | NCB OUTPOSTED UNITS | 1 | DESIGN | May 2022 | Sep 2023 | May 2022 | Sep 2023
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202204 | NCB OUTPOSTED UNITS | 2 | CONSTRUCTION | Sep 2023 | Sep 2025 | Sep 2023 | Sep 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202204 | NCB OUTPOSTED UNITS | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202205 | NCB: FIRE ALARM REPLACEMENT | 1 | DESIGN | Jun 2021 | Nov 2022 | Jun 2021 | Nov 2022
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202205 | NCB: FIRE ALARM REPLACEMENT | 2 | CONSTRUCTION | Nov 2022 | Nov 2025 | Nov 2022 | Nov 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202205 | NCB: FIRE ALARM REPLACEMENT | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2025 | Feb 2026 | Nov 2025 | Feb 2026
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202206 | NCB: EMERGENCY POWER SEPARATION | 1 | DESIGN | Jun 2021 | Nov 2022 | Jun 2021 | Nov 2022
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202206 | NCB: EMERGENCY POWER SEPARATION | 2 | CONSTRUCTION | Nov 2022 | Nov 2025 | Nov 2022 | Nov 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202206 | NCB: EMERGENCY POWER SEPARATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2025 | Feb 2026 | Nov 2025 | Feb 2026
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202207 | NCB: SPRINKLER SYSTEM REPLACEMENT | 1 | DESIGN | Jun 2021 | Nov 2022 | Jun 2021 | Nov 2022
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202207 | NCB: SPRINKLER SYSTEM REPLACEMENT | 2 | CONSTRUCTION | Nov 2022 | Nov 2025 | Nov 2022 | Nov 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202207 | NCB: SPRINKLER SYSTEM REPLACEMENT | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2025 | Feb 2026 | Nov 2025 | Feb 2026
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202208 | NCB: BOILER REPLACEMENT | 1 | DESIGN | Jun 2021 | Nov 2022 | Jun 2021 | Nov 2022
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202208 | NCB: BOILER REPLACEMENT | 2 | CONSTRUCTION | Nov 2022 | Nov 2025 | Nov 2022 | Nov 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202208 | NCB: BOILER REPLACEMENT | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2025 | Feb 2026 | Nov 2025 | Feb 2026
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201401 | LINCOLN: RENOVATE ADOLESCENT CLINIC | 1 | DESIGN | Jul 2019 | Jan 2020 | Jul 2019 | Jan 2020
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201401 | LINCOLN: RENOVATE ADOLESCENT CLINIC | 2 | CONSTRUCTION | Jan 2020 | Jun 2020 | Jan 2020 | Jun 2032
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201601 | LINCOLN: COOLING TOWER REPLACEMENT | 1 | DESIGN | Aug 2018 | Jul 2019 | Aug 2018 | Jul 2019
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201601 | LINCOLN: COOLING TOWER REPLACEMENT | 2 | CONSTRUCTION | Jul 2019 | Jun 2020 | Aug 2018 | Jul 2019
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201601 | LINCOLN: COOLING TOWER REPLACEMENT | 3 | CONSTRUCTION | Jul 2019 | Jun 2020 | Jul 2019 | Jun 2028
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201602 | LINCOLN: REPLACE UNDERGROUND FUEL TANKS | 1 | DESIGN | Aug 2019 | Jun 2020 | Aug 2019 | Jun 2020
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201602 | LINCOLN: REPLACE UNDERGROUND FUEL TANKS | 2 | CONSTRUCTION | Jul 2020 | Jun 2021 | Aug 2019 | Jun 2020
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201602 | LINCOLN: REPLACE UNDERGROUND FUEL TANKS | 3 | CONSTRUCTION | Jul 2020 | Jun 2021 | Jul 2020 | Jun 2032
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201604 | LINCOLN: EXTERIOR FACADE RESTORATION - LL11 COMPLIANCE | 1 | DESIGN | Jun 2019 | Dec 2019 | Jul 2021 | Jan 2022
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201604 | LINCOLN: EXTERIOR FACADE RESTORATION - LL11 COMPLIANCE | 2 | CONSTRUCTION | Dec 2019 | Jun 2020 | Jan 2022 | Jun 2032
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201701 | LINCOLN: EES UPGRADE | 1 | DESIGN | Aug 2019 | Jun 2020 | Aug 2019 | Jun 2020
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201701 | LINCOLN: EES UPGRADE | 2 | CONSTRUCTION | Jul 2020 | Jun 2021 | Aug 2019 | Jun 2020
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201701 | LINCOLN: EES UPGRADE | 3 | CONSTRUCTION | Jul 2020 | Jun 2021 | Jul 2020 | Jun 2032
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201805 | LINCOLN: REHABILITATE ELECTRICAL DISTRIBUTION SYSTEM | 2 | CONSTRUCTION | Jan 2019 | Jun 2019 | Jan 2019 | Jun 2019
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201807 | LINCOLN: UPGRADE ELEVATORS 18 & 19 | 1 | DESIGN | Jul 2019 | Jan 2020 | Jul 2019 | Jan 2020
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201807 | LINCOLN: UPGRADE ELEVATORS 18 & 19 | 2 | CONSTRUCTION | Jan 2020 | Jun 2020 | Jan 2020 | Jun 2024
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201901 | LINCOLN: RETAIL PHARMACY RENOVATION | 1 | DESIGN | Jul 2019 | Jan 2020 | Jul 2019 | Jun 2033
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201901 | LINCOLN: RETAIL PHARMACY RENOVATION | 2 | CONSTRUCTION | Jan 2020 | Jun 2020 | Jun 2033 | Nov 2045
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201942 | LINCOLN: PURCHASE MRI & CONSTRUCT SUITE | 1 | DESIGN | Feb 2021 | Jun 2022 | Feb 2021 | Jun 2022
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201942 | LINCOLN: PURCHASE MRI & CONSTRUCT SUITE | 2 | CONSTRUCTION | Jun 2022 | Jun 2025 | Jun 2022 | Jun 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201942 | LINCOLN: PURCHASE MRI & CONSTRUCT SUITE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202001 | LINCOLN CONSTRUCT INPATIENT PHARMACY VAULT | 1 | DESIGN | Sep 2020 | Feb 2022 | Mar 2020 | Aug 2021
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202001 | LINCOLN CONSTRUCT INPATIENT PHARMACY VAULT | 2 | CONSTRUCTION | Feb 2022 | Feb 2025 | Aug 2021 | Aug 2024
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202001 | LINCOLN CONSTRUCT INPATIENT PHARMACY VAULT | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | May 2025 | Aug 2024 | Nov 2024
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202002 | LINCOLN MEDICAL CENTER - DEVELOP A BRIDGE CLINIC | 1 | DESIGN | Apr 2021 | Sep 2022 | Apr 2021 | Sep 2022
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202002 | LINCOLN MEDICAL CENTER - DEVELOP A BRIDGE CLINIC | 2 | CONSTRUCTION | Sep 2022 | Sep 2024 | Sep 2022 | Sep 2024
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202002 | LINCOLN MEDICAL CENTER - DEVELOP A BRIDGE CLINIC | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Dec 2024 | Sep 2024 | Jun 2032
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202003 | LINCOLN: INSTALLATION OF ENTRANCE TURNSTILES | 1 | DESIGN | Feb 2021 | Jun 2022 | Feb 2022 | Jun 2023
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202003 | LINCOLN: INSTALLATION OF ENTRANCE TURNSTILES | 2 | CONSTRUCTION | Jun 2022 | Jun 2025 | Jun 2023 | Jun 2029
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202003 | LINCOLN: INSTALLATION OF ENTRANCE TURNSTILES | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2025 | Sep 2025 | Jul 2029 | Sep 2029
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202106 | LINCOLN PHARMACY COMPOUNDING USP 797/800 COMPLIANCE | 1 | DESIGN | Jun 2021 | Oct 2022 | Jun 2021 | Oct 2022
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202106 | LINCOLN PHARMACY COMPOUNDING USP 797/800 COMPLIANCE | 2 | CONSTRUCTION | Oct 2022 | Oct 2025 | Oct 2022 | Oct 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202106 | LINCOLN PHARMACY COMPOUNDING USP 797/800 COMPLIANCE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202201 | LINCOLN MAIN ENTRANCE AND PLAZA RENOVATION | 1 | DESIGN | Dec 2022 | May 2024 | Dec 2022 | May 2024
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202201 | LINCOLN MAIN ENTRANCE AND PLAZA RENOVATION | 2 | CONSTRUCTION | May 2024 | May 2027 | May 2024 | May 2027
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202201 | LINCOLN MAIN ENTRANCE AND PLAZA RENOVATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | May 2027 | Aug 2027 | May 2027 | Aug 2027
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202202 | LINCOLN FIRE ALARM SYSTEM UPGRADE | 1 | DESIGN | Dec 2022 | May 2024 | Dec 2022 | May 2024
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202202 | LINCOLN FIRE ALARM SYSTEM UPGRADE | 2 | CONSTRUCTION | May 2024 | May 2027 | May 2024 | May 2027
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202202 | LINCOLN FIRE ALARM SYSTEM UPGRADE | 3 | PUNCHLIST COMPLETE, JOB CLOSED | May 2027 | Aug 2027 | May 2027 | Aug 2027
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202203H | LIN: PARKING GARAGE RENOVATION | 1 | DESIGN | Dec 2022 | May 2024 | Dec 2022 | May 2024
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202203H | LIN: PARKING GARAGE RENOVATION | 2 | CONSTRUCTION | May 2024 | May 2027 | May 2024 | May 2027
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202203H | LIN: PARKING GARAGE RENOVATION | 3 | PUNCHLIST COMPLETE, JOB CLOSED | May 2027 | Aug 2027 | May 2027 | Aug 2027
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202204 | LINCOLN: LOADING DOCK & UNDERGROUND DRAINAGE RECON | 1 | DESIGN | Dec 2022 | May 2024 | Dec 2022 | May 2024
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202204 | LINCOLN: LOADING DOCK & UNDERGROUND DRAINAGE RECON | 2 | CONSTRUCTION | May 2024 | May 2027 | May 2024 | May 2027
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202204 | LINCOLN: LOADING DOCK & UNDERGROUND DRAINAGE RECON | 3 | PUNCHLIST COMPLETE, JOB CLOSED | May 2027 | Aug 2027 | May 2027 | Aug 2027
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 42201301 | MORRISANIA: RENOVATE DENTAL SUITE | 1 | DESIGN | Jul 2019 | Jan 2020 | Jul 2019 | Jan 2020
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 42201301 | MORRISANIA: RENOVATE DENTAL SUITE | 2 | CONSTRUCTION | Jan 2020 | Jun 2020 | Jan 2020 | Jun 2032
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 42201515 | MORRISANIA: RENOVATE WOMEN'S HEALTH SERVICES - RADIOLOGY | 1 | DESIGN | Jan 2015 | Jul 2015 | Jan 2018 | Jul 2018
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 42201515 | MORRISANIA: RENOVATE WOMEN'S HEALTH SERVICES - RADIOLOGY | 2 | CONSTRUCTION | Jul 2015 | Dec 2015 | Jul 2018 | Jun 2032
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 42202202 | MORRISANIA: ELEVATOR SYSTEM MODERNIZATION | 1 | DESIGN | Apr 2022 | Feb 2023 | Apr 2022 | Feb 2023
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 42202202 | MORRISANIA: ELEVATOR SYSTEM MODERNIZATION | 2 | CONSTRUCTION | Feb 2023 | Feb 2024 | Apr 2022 | Feb 2023
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 42202202 | MORRISANIA: ELEVATOR SYSTEM MODERNIZATION | 3 | CONSTRUCTION | Feb 2023 | Feb 2024 | Feb 2023 | Feb 2024
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 42202203 | Morrisania: Security System | 1 | DESIGN | Aug 2022 | Jul 2023 | Aug 2022 | Jul 2023
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 42202203 | Morrisania: Security System | 2 | CONSTRUCTION | Jul 2023 | Jul 2024 | Aug 2022 | Jul 2023
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 42202203 | Morrisania: Security System | 3 | CONSTRUCTION | Jul 2023 | Jul 2024 | Jul 2023 | Jul 2024
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 42202401 | GOTHAM HEALTH, MORRISANIA COMMUNITY RESOURCE CENTER--CONSTRU | 1 | DESIGN | Feb 2024 | Dec 2024 | Feb 2024 | Dec 2024
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 42202401 | GOTHAM HEALTH, MORRISANIA COMMUNITY RESOURCE CENTER--CONSTRU | 2 | CONSTRUCTION | Dec 2024 | Dec 2024 | Feb 2024 | Dec 2024
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 42202401 | GOTHAM HEALTH, MORRISANIA COMMUNITY RESOURCE CENTER--CONSTRU | 3 | CONSTRUCTION | Dec 2024 | Dec 2024 | Dec 2024 | Dec 2024
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 42202402 | MORISSANIA: ASTHMA PEDIATRIC SUITE | 1 | DESIGN | Aug 2023 | Jul 2024 | Aug 2023 | Jul 2024
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 42202402 | MORISSANIA: ASTHMA PEDIATRIC SUITE | 2 | CONSTRUCTION | Jul 2024 | Mar 2025 | Aug 2023 | Jul 2024
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 42202402 | MORISSANIA: ASTHMA PEDIATRIC SUITE | 3 | CONSTRUCTION | Jul 2024 | Mar 2025 | Jul 2024 | Mar 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | ACEHHC409 | LINCOLN ENERGY UPGRADE | 1 | DESIGN | Aug 2019 | Jun 2020 | Aug 2019 | Jun 2020
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | ACEHHC409 | LINCOLN ENERGY UPGRADE | 2 | CONSTRUCTION | Jul 2020 | Jun 2021 | Jul 2020 | Jun 2024
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | ACEHHC606 | JMC ENERGY CONSERVATION MEASURES | 1 | DESIGN | Aug 2019 | Jun 2020 | Aug 2021 | Jul 2022
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | ACEHHC606 | JMC ENERGY CONSERVATION MEASURES | 2 | CONSTRUCTION | Jul 2020 | Jun 2021 | Aug 2021 | Jul 2022
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | ACEHHC606 | JMC ENERGY CONSERVATION MEASURES | 3 | CONSTRUCTION | Jul 2020 | Jun 2021 | Jul 2022 | Jun 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | ACEHHC901 | LINCOLN ENERGY UPGRADES PHASE 2 | 1 | DEVELOP SCOPE | Mar 2021 | Mar 2021 | Mar 2021 | Mar 2021
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | ACEHHC901 | LINCOLN ENERGY UPGRADES PHASE 2 | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2021 | May 2021 | Mar 2021 | May 2021
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | ACEHHC901 | LINCOLN ENERGY UPGRADES PHASE 2 | 3 | CONSTRUCTION TO 50% | May 2021 | Nov 2021 | May 2021 | Nov 2021
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | ACEHHC901 | LINCOLN ENERGY UPGRADES PHASE 2 | 4 | CONSTRUCTION TO 75% | Nov 2021 | Feb 2022 | Nov 2021 | Feb 2022
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | ACEHHC901 | LINCOLN ENERGY UPGRADES PHASE 2 | 5 | SUBSTANTIAL COMPLETION | Feb 2022 | Apr 2022 | Feb 2022 | Apr 2022
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | ACEHHC901 | LINCOLN ENERGY UPGRADES PHASE 2 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2022 | May 2022 | Apr 2022 | Jun 2025
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | TKYHHC905 | NCB ENERGY EFFICIENY MEASURES | 1 | DESIGN | May 2021 | Sep 2022 | May 2021 | Sep 2022
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | TKYHHC905 | NCB ENERGY EFFICIENY MEASURES | 2 | CONSTRUCTION | Sep 2022 | Sep 2024 | Sep 2022 | Sep 2024
20231026 | BRONX | 819 | HEALTH AND HOSPITALS CORP | TKYHHC905 | NCB ENERGY EFFICIENY MEASURES | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-590 | Jerome Park Gate House #7 Sluice Gate and Operator Replacmnt | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-590 | Jerome Park Gate House #7 Sluice Gate and Operator Replacmnt | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-590 | Jerome Park Gate House #7 Sluice Gate and Operator Replacmnt | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-590 | Jerome Park Gate House #7 Sluice Gate and Operator Replacmnt | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-590 | Jerome Park Gate House #7 Sluice Gate and Operator Replacmnt | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-590 | Jerome Park Gate House #7 Sluice Gate and Operator Replacmnt | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-590 | Jerome Park Gate House #7 Sluice Gate and Operator Replacmnt | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | May 2024 | Sep 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-590 | Jerome Park Gate House #7 Sluice Gate and Operator Replacmnt | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-590 | Jerome Park Gate House #7 Sluice Gate and Operator Replacmnt | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Dec 2024 | Feb 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-590 | Jerome Park Gate House #7 Sluice Gate and Operator Replacmnt | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Mar 2025 | Feb 2025 | Mar 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-604 | Croton Filtration Optimization | 1 | DEVELOP SCOPE | Jun 2024 | Aug 2024 | Jun 2024 | Aug 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-604 | Croton Filtration Optimization | 2 | PRELIMINARY DESIGN | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-604 | Croton Filtration Optimization | 3 | FINAL DESIGN | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-604 | Croton Filtration Optimization | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-604 | Croton Filtration Optimization | 5 | CONSTRUCTION TO 25% | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-604 | Croton Filtration Optimization | 6 | CONSTRUCTION TO 50% | Jan 2026 | May 2026 | Jan 2026 | May 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-604 | Croton Filtration Optimization | 7 | CONSTRUCTION TO 75% | May 2026 | Sep 2026 | May 2026 | Sep 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-604 | Croton Filtration Optimization | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2026 | Dec 2026 | Sep 2026 | Dec 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-604 | Croton Filtration Optimization | 9 | SUBSTANTIAL COMPLETION | Dec 2026 | Feb 2027 | Dec 2026 | Feb 2027
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-604 | Croton Filtration Optimization | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2027 | Mar 2027 | Feb 2027 | Mar 2027
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-M&A | MITIGATION AND AMENITIES FOR WTP | 1 | DEVELOP SCOPE | Jan 2017 | Oct 2017 | Jan 2017 | Oct 2017
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-M&A | MITIGATION AND AMENITIES FOR WTP | 2 | PRELIMINARY DESIGN | Oct 2017 | Oct 2018 | Oct 2017 | Oct 2018
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-M&A | MITIGATION AND AMENITIES FOR WTP | 3 | FINAL DESIGN | Oct 2018 | Mar 2020 | Oct 2018 | Mar 2020
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-M&A | MITIGATION AND AMENITIES FOR WTP | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Dec 2020 | Mar 2020 | Dec 2020
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-M&A | MITIGATION AND AMENITIES FOR WTP | 5 | CONSTRUCTION TO 25% | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-M&A | MITIGATION AND AMENITIES FOR WTP | 6 | CONSTRUCTION TO 50% | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-M&A | MITIGATION AND AMENITIES FOR WTP | 7 | CONSTRUCTION TO 75% | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-M&A | MITIGATION AND AMENITIES FOR WTP | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-M&A | MITIGATION AND AMENITIES FOR WTP | 9 | SUBSTANTIAL COMPLETION | Sep 2024 | Mar 2029 | Sep 2024 | Mar 2029
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-M&A | MITIGATION AND AMENITIES FOR WTP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2029 | May 2029 | Mar 2029 | May 2029
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-BX-LTP | BRONX RIVER LONG TERM CONTROL PLAN FOR CSO ABATEMENT | 1 | DEVELOP SCOPE | Jun 2018 | Feb 2019 | Jun 2018 | Feb 2019
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-BX-LTP | BRONX RIVER LONG TERM CONTROL PLAN FOR CSO ABATEMENT | 2 | PRELIMINARY DESIGN | Feb 2019 | Feb 2020 | Feb 2019 | Feb 2020
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-BX-LTP | BRONX RIVER LONG TERM CONTROL PLAN FOR CSO ABATEMENT | 3 | FINAL DESIGN | Feb 2020 | Aug 2021 | Feb 2020 | Aug 2021
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-BX-LTP | BRONX RIVER LONG TERM CONTROL PLAN FOR CSO ABATEMENT | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2021 | May 2022 | Aug 2021 | May 2022
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-BX-LTP | BRONX RIVER LONG TERM CONTROL PLAN FOR CSO ABATEMENT | 5 | CONSTRUCTION TO 25% | May 2022 | May 2023 | May 2022 | May 2023
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-BX-LTP | BRONX RIVER LONG TERM CONTROL PLAN FOR CSO ABATEMENT | 6 | CONSTRUCTION TO 50% | May 2023 | Apr 2024 | May 2023 | Apr 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-BX-LTP | BRONX RIVER LONG TERM CONTROL PLAN FOR CSO ABATEMENT | 7 | CONSTRUCTION TO 75% | Apr 2024 | Apr 2025 | Apr 2024 | Apr 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-BX-LTP | BRONX RIVER LONG TERM CONTROL PLAN FOR CSO ABATEMENT | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2025 | Jan 2026 | Apr 2025 | Jan 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-BX-LTP | BRONX RIVER LONG TERM CONTROL PLAN FOR CSO ABATEMENT | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Jul 2026 | Jan 2026 | Jul 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-BX-LTP | BRONX RIVER LONG TERM CONTROL PLAN FOR CSO ABATEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2026 | Oct 2026 | Jul 2026 | Oct 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-HR-DF | CSO HUTCHINSON RIVER DISINFECTION FACILITY | 1 | DEVELOP SCOPE | Jul 2015 | Mar 2016 | Jul 2015 | Mar 2016
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-HR-DF | CSO HUTCHINSON RIVER DISINFECTION FACILITY | 2 | PRELIMINARY DESIGN | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-HR-DF | CSO HUTCHINSON RIVER DISINFECTION FACILITY | 3 | FINAL DESIGN | Mar 2017 | Sep 2018 | Mar 2017 | Sep 2018
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-HR-DF | CSO HUTCHINSON RIVER DISINFECTION FACILITY | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2018 | Jun 2019 | Sep 2018 | Jun 2019
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-HR-DF | CSO HUTCHINSON RIVER DISINFECTION FACILITY | 5 | CONSTRUCTION TO 25% | Jun 2019 | Jun 2020 | Jun 2019 | Jun 2020
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-HR-DF | CSO HUTCHINSON RIVER DISINFECTION FACILITY | 6 | CONSTRUCTION TO 50% | Jun 2020 | May 2021 | Jun 2020 | May 2021
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-HR-DF | CSO HUTCHINSON RIVER DISINFECTION FACILITY | 7 | CONSTRUCTION TO 75% | May 2021 | May 2022 | May 2021 | May 2022
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-HR-DF | CSO HUTCHINSON RIVER DISINFECTION FACILITY | 8 | ORIGINAL EQUIP & FURNISHING | May 2022 | Feb 2023 | May 2022 | Feb 2023
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-HR-DF | CSO HUTCHINSON RIVER DISINFECTION FACILITY | 9 | SUBSTANTIAL COMPLETION | Feb 2023 | Aug 2027 | Feb 2023 | Aug 2027
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-HR-DF | CSO HUTCHINSON RIVER DISINFECTION FACILITY | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2027 | Nov 2027 | Aug 2027 | Nov 2027
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEX25 | Reconstruction of Existing Sewers, the Bronx | 1 | DEVELOP SCOPE | Jan 2023 | Apr 2023 | Jan 2023 | Apr 2023
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEX25 | Reconstruction of Existing Sewers, the Bronx | 2 | PRELIMINARY DESIGN | Apr 2023 | Aug 2023 | Apr 2023 | Aug 2023
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEX25 | Reconstruction of Existing Sewers, the Bronx | 3 | FINAL DESIGN | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEX25 | Reconstruction of Existing Sewers, the Bronx | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2024 | May 2024 | Feb 2024 | May 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEX25 | Reconstruction of Existing Sewers, the Bronx | 5 | CONSTRUCTION TO 25% | May 2024 | Aug 2024 | May 2024 | Aug 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEX25 | Reconstruction of Existing Sewers, the Bronx | 6 | CONSTRUCTION TO 50% | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEX25 | Reconstruction of Existing Sewers, the Bronx | 7 | CONSTRUCTION TO 75% | Dec 2024 | Apr 2025 | Dec 2024 | Apr 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEX25 | Reconstruction of Existing Sewers, the Bronx | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2025 | Jul 2025 | Apr 2025 | Jul 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEX25 | Reconstruction of Existing Sewers, the Bronx | 9 | SUBSTANTIAL COMPLETION | Jul 2025 | Sep 2025 | Jul 2025 | Sep 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEX25 | Reconstruction of Existing Sewers, the Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Oct 2025 | Sep 2025 | Oct 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CD11 | GI - CONSTRUCTION OF BIOSWALES IN CITY COUNCIL DISTRICT 11 | 1 | FINAL DESIGN | Feb 2021 | Aug 2022 | Feb 2021 | Aug 2022
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CD11 | GI - CONSTRUCTION OF BIOSWALES IN CITY COUNCIL DISTRICT 11 | 2 | CONSTRUCTION TO 25% | Aug 2022 | Apr 2023 | Aug 2022 | Apr 2023
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CD11 | GI - CONSTRUCTION OF BIOSWALES IN CITY COUNCIL DISTRICT 11 | 3 | CONSTRUCTION TO 50% | Apr 2023 | Dec 2023 | Apr 2023 | Dec 2023
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CD11 | GI - CONSTRUCTION OF BIOSWALES IN CITY COUNCIL DISTRICT 11 | 4 | CONSTRUCTION TO 75% | Dec 2023 | Jul 2024 | Dec 2023 | Jul 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-NYCHA | GI - NYCHA GREEN INFRASTRUCTURE AT EDENWALD HOUSES - NO & SO | 2 | PRELIMINARY DESIGN | Dec 2011 | Apr 2012 | Jun 2012 | Jun 2013
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-NYCHA | GI - NYCHA GREEN INFRASTRUCTURE AT EDENWALD HOUSES - NO & SO | 3 | FINAL DESIGN | Apr 2012 | Oct 2012 | Jun 2013 | Dec 2014
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-NYCHA | GI - NYCHA GREEN INFRASTRUCTURE AT EDENWALD HOUSES - NO & SO | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2012 | Jan 2013 | Dec 2014 | Sep 2015
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-NYCHA | GI - NYCHA GREEN INFRASTRUCTURE AT EDENWALD HOUSES - NO & SO | 5 | CONSTRUCTION TO 25% | Jan 2013 | May 2013 | Sep 2015 | Sep 2016
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-NYCHA | GI - NYCHA GREEN INFRASTRUCTURE AT EDENWALD HOUSES - NO & SO | 6 | CONSTRUCTION TO 50% | May 2013 | Sep 2013 | Sep 2016 | Aug 2017
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-NYCHA | GI - NYCHA GREEN INFRASTRUCTURE AT EDENWALD HOUSES - NO & SO | 7 | CONSTRUCTION TO 75% | Sep 2013 | Jan 2014 | Aug 2017 | Aug 2018
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-NYCHA | GI - NYCHA GREEN INFRASTRUCTURE AT EDENWALD HOUSES - NO & SO | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2014 | Apr 2014 | Aug 2018 | May 2019
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-NYCHA | GI - NYCHA GREEN INFRASTRUCTURE AT EDENWALD HOUSES - NO & SO | 9 | SUBSTANTIAL COMPLETION | Apr 2014 | Jun 2014 | May 2019 | Nov 2019
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-NYCHA | GI - NYCHA GREEN INFRASTRUCTURE AT EDENWALD HOUSES - NO & SO | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2014 | Jul 2014 | Nov 2019 | Feb 2020
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-TIBBET | GI - TIBBETS BROOK AND VAN CORTLAND LAKE IMPROVEMENTS | 1 | DEVELOP SCOPE | Jul 2022 | Mar 2023 | Jul 2022 | Mar 2023
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-TIBBET | GI - TIBBETS BROOK AND VAN CORTLAND LAKE IMPROVEMENTS | 2 | PRELIMINARY DESIGN | Mar 2023 | Mar 2024 | Mar 2023 | Mar 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-TIBBET | GI - TIBBETS BROOK AND VAN CORTLAND LAKE IMPROVEMENTS | 3 | FINAL DESIGN | Mar 2024 | Sep 2025 | Mar 2024 | Sep 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-TIBBET | GI - TIBBETS BROOK AND VAN CORTLAND LAKE IMPROVEMENTS | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2025 | Jun 2026 | Sep 2025 | Jun 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-TIBBET | GI - TIBBETS BROOK AND VAN CORTLAND LAKE IMPROVEMENTS | 5 | CONSTRUCTION TO 25% | Jun 2026 | Jun 2027 | Jun 2026 | Jun 2027
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-TIBBET | GI - TIBBETS BROOK AND VAN CORTLAND LAKE IMPROVEMENTS | 6 | CONSTRUCTION TO 50% | Jun 2027 | May 2028 | Jun 2027 | May 2028
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-TIBBET | GI - TIBBETS BROOK AND VAN CORTLAND LAKE IMPROVEMENTS | 7 | CONSTRUCTION TO 75% | May 2028 | May 2029 | May 2028 | May 2029
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-TIBBET | GI - TIBBETS BROOK AND VAN CORTLAND LAKE IMPROVEMENTS | 8 | ORIGINAL EQUIP & FURNISHING | May 2029 | Feb 2030 | May 2029 | Feb 2030
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-TIBBET | GI - TIBBETS BROOK AND VAN CORTLAND LAKE IMPROVEMENTS | 9 | SUBSTANTIAL COMPLETION | Feb 2030 | Aug 2030 | Feb 2030 | Aug 2030
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-TIBBET | GI - TIBBETS BROOK AND VAN CORTLAND LAKE IMPROVEMENTS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2030 | Nov 2030 | Aug 2030 | Nov 2030
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HBBA24181 | Replacement of WM Infra on E 188 Street, Bronx | 1 | DEVELOP SCOPE | Nov 2020 | Aug 2021 | Nov 2020 | Aug 2021
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HBBA24181 | Replacement of WM Infra on E 188 Street, Bronx | 2 | PRELIMINARY DESIGN | Aug 2021 | Jul 2022 | Aug 2021 | Jul 2022
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HBBA24181 | Replacement of WM Infra on E 188 Street, Bronx | 3 | FINAL DESIGN | Aug 2022 | Jan 2024 | Aug 2022 | Jan 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HBBA24181 | Replacement of WM Infra on E 188 Street, Bronx | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2024 | Oct 2024 | Jan 2024 | Oct 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HBBA24181 | Replacement of WM Infra on E 188 Street, Bronx | 5 | CONSTRUCTION TO 25% | Oct 2024 | Oct 2025 | Oct 2024 | Oct 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HBBA24181 | Replacement of WM Infra on E 188 Street, Bronx | 6 | CONSTRUCTION TO 50% | Oct 2025 | Oct 2026 | Oct 2025 | Oct 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HBBA24181 | Replacement of WM Infra on E 188 Street, Bronx | 7 | CONSTRUCTION TO 75% | Oct 2026 | Oct 2027 | Oct 2026 | Oct 2027
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HBBA24181 | Replacement of WM Infra on E 188 Street, Bronx | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jun 2028 | Oct 2027 | Jun 2028
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HBBA24181 | Replacement of WM Infra on E 188 Street, Bronx | 9 | SUBSTANTIAL COMPLETION | Jun 2028 | Dec 2028 | Jun 2028 | Dec 2028
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HBBA24181 | Replacement of WM Infra on E 188 Street, Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2028 | Mar 2029 | Dec 2028 | Mar 2029
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-545 | CROTON FILTRATION PLANT | 1 | DEVELOP SCOPE | Sep 2004 | Dec 2004 | Jul 2007 | Apr 2008
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-545 | CROTON FILTRATION PLANT | 2 | PRELIMINARY DESIGN | Dec 2004 | Apr 2005 | Apr 2008 | Mar 2009
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-545 | CROTON FILTRATION PLANT | 3 | FINAL DESIGN | Apr 2005 | Oct 2005 | Mar 2009 | Sep 2010
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-545 | CROTON FILTRATION PLANT | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2005 | Jan 2006 | Sep 2010 | Jun 2011
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-545 | CROTON FILTRATION PLANT | 5 | CONSTRUCTION TO 25% | Jan 2006 | May 2006 | Jun 2011 | Jun 2012
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-545 | CROTON FILTRATION PLANT | 6 | CONSTRUCTION TO 50% | May 2006 | Aug 2006 | Jun 2012 | Jun 2013
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-545 | CROTON FILTRATION PLANT | 7 | CONSTRUCTION TO 75% | Aug 2006 | Dec 2006 | Jun 2013 | Jun 2014
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-545 | CROTON FILTRATION PLANT | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2006 | Mar 2007 | Jun 2014 | Feb 2015
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-545 | CROTON FILTRATION PLANT | 9 | SUBSTANTIAL COMPLETION | Mar 2007 | May 2007 | Feb 2015 | Aug 2023
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-545 | CROTON FILTRATION PLANT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2007 | Jun 2007 | Aug 2023 | Nov 2023
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED583 | Trunk & Dist WM work on W 177 St, Bronx | 1 | DEVELOP SCOPE | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED583 | Trunk & Dist WM work on W 177 St, Bronx | 2 | PRELIMINARY DESIGN | Apr 2025 | Jul 2025 | Apr 2025 | Jul 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED583 | Trunk & Dist WM work on W 177 St, Bronx | 3 | FINAL DESIGN | Jul 2025 | Jan 2026 | Jul 2025 | Jan 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED583 | Trunk & Dist WM work on W 177 St, Bronx | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2026 | Apr 2026 | Jan 2026 | Apr 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED583 | Trunk & Dist WM work on W 177 St, Bronx | 5 | CONSTRUCTION TO 25% | Apr 2026 | Aug 2026 | Apr 2026 | Aug 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED583 | Trunk & Dist WM work on W 177 St, Bronx | 6 | CONSTRUCTION TO 50% | Aug 2026 | Dec 2026 | Aug 2026 | Dec 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED583 | Trunk & Dist WM work on W 177 St, Bronx | 7 | CONSTRUCTION TO 75% | Dec 2026 | Apr 2027 | Dec 2026 | Apr 2027
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED583 | Trunk & Dist WM work on W 177 St, Bronx | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2027 | Jul 2027 | Apr 2027 | Jul 2027
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED583 | Trunk & Dist WM work on W 177 St, Bronx | 9 | SUBSTANTIAL COMPLETION | Jul 2027 | Sep 2027 | Jul 2027 | Sep 2027
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED583 | Trunk & Dist WM work on W 177 St, Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Oct 2027 | Sep 2027 | Oct 2027
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED585 | New Trunk WM install from W 181 st & Jerome Ave, Bronx | 1 | DEVELOP SCOPE | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED585 | New Trunk WM install from W 181 st & Jerome Ave, Bronx | 2 | PRELIMINARY DESIGN | Apr 2025 | Jul 2025 | Apr 2025 | Jul 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED585 | New Trunk WM install from W 181 st & Jerome Ave, Bronx | 3 | FINAL DESIGN | Jul 2025 | Jan 2026 | Jul 2025 | Jan 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED585 | New Trunk WM install from W 181 st & Jerome Ave, Bronx | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2026 | Apr 2026 | Jan 2026 | Apr 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED585 | New Trunk WM install from W 181 st & Jerome Ave, Bronx | 5 | CONSTRUCTION TO 25% | Apr 2026 | Aug 2026 | Apr 2026 | Aug 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED585 | New Trunk WM install from W 181 st & Jerome Ave, Bronx | 6 | CONSTRUCTION TO 50% | Aug 2026 | Dec 2026 | Aug 2026 | Dec 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED585 | New Trunk WM install from W 181 st & Jerome Ave, Bronx | 7 | CONSTRUCTION TO 75% | Dec 2026 | Apr 2027 | Dec 2026 | Apr 2027
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED585 | New Trunk WM install from W 181 st & Jerome Ave, Bronx | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2027 | Jul 2027 | Apr 2027 | Jul 2027
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED585 | New Trunk WM install from W 181 st & Jerome Ave, Bronx | 9 | SUBSTANTIAL COMPLETION | Jul 2027 | Sep 2027 | Jul 2027 | Sep 2027
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED585 | New Trunk WM install from W 181 st & Jerome Ave, Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Oct 2027 | Sep 2027 | Oct 2027
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED599 | Dist WM Replmt intersection White Plains Rd & Mace Ave in BX | 1 | DEVELOP SCOPE | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED599 | Dist WM Replmt intersection White Plains Rd & Mace Ave in BX | 2 | PRELIMINARY DESIGN | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED599 | Dist WM Replmt intersection White Plains Rd & Mace Ave in BX | 3 | FINAL DESIGN | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED599 | Dist WM Replmt intersection White Plains Rd & Mace Ave in BX | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2024 | Feb 2025 | Nov 2024 | Feb 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED599 | Dist WM Replmt intersection White Plains Rd & Mace Ave in BX | 5 | CONSTRUCTION TO 25% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED599 | Dist WM Replmt intersection White Plains Rd & Mace Ave in BX | 6 | CONSTRUCTION TO 50% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED599 | Dist WM Replmt intersection White Plains Rd & Mace Ave in BX | 7 | CONSTRUCTION TO 75% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED599 | Dist WM Replmt intersection White Plains Rd & Mace Ave in BX | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2026 | May 2026 | Feb 2026 | May 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED599 | Dist WM Replmt intersection White Plains Rd & Mace Ave in BX | 9 | SUBSTANTIAL COMPLETION | May 2026 | Jul 2026 | May 2026 | Jul 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED599 | Dist WM Replmt intersection White Plains Rd & Mace Ave in BX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2026 | Aug 2026 | Jul 2026 | Aug 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED600 | Storm SE repair in Allertonn Ave btwn Brurner & Ely Ave, BX | 1 | DEVELOP SCOPE | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED600 | Storm SE repair in Allertonn Ave btwn Brurner & Ely Ave, BX | 2 | PRELIMINARY DESIGN | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED600 | Storm SE repair in Allertonn Ave btwn Brurner & Ely Ave, BX | 3 | FINAL DESIGN | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED600 | Storm SE repair in Allertonn Ave btwn Brurner & Ely Ave, BX | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2024 | Feb 2025 | Nov 2024 | Feb 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED600 | Storm SE repair in Allertonn Ave btwn Brurner & Ely Ave, BX | 5 | CONSTRUCTION TO 25% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED600 | Storm SE repair in Allertonn Ave btwn Brurner & Ely Ave, BX | 6 | CONSTRUCTION TO 50% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED600 | Storm SE repair in Allertonn Ave btwn Brurner & Ely Ave, BX | 7 | CONSTRUCTION TO 75% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED600 | Storm SE repair in Allertonn Ave btwn Brurner & Ely Ave, BX | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2026 | May 2026 | Feb 2026 | May 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED600 | Storm SE repair in Allertonn Ave btwn Brurner & Ely Ave, BX | 9 | SUBSTANTIAL COMPLETION | May 2026 | Jul 2026 | May 2026 | Jul 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED600 | Storm SE repair in Allertonn Ave btwn Brurner & Ely Ave, BX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2026 | Aug 2026 | Jul 2026 | Aug 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-238-L | REPLACEMENT OF THE DIGESTER @ THE HUNTS POINT WWTP | 1 | DEVELOP SCOPE | Jun 2015 | Mar 2016 | Jun 2015 | Mar 2016
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-238-L | REPLACEMENT OF THE DIGESTER @ THE HUNTS POINT WWTP | 2 | PRELIMINARY DESIGN | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-238-L | REPLACEMENT OF THE DIGESTER @ THE HUNTS POINT WWTP | 3 | FINAL DESIGN | Mar 2017 | Sep 2018 | Mar 2017 | Sep 2018
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-238-L | REPLACEMENT OF THE DIGESTER @ THE HUNTS POINT WWTP | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2018 | Jun 2019 | Sep 2018 | Jun 2019
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-238-L | REPLACEMENT OF THE DIGESTER @ THE HUNTS POINT WWTP | 5 | CONSTRUCTION TO 25% | Jun 2019 | Jun 2020 | Jun 2019 | Jun 2020
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-238-L | REPLACEMENT OF THE DIGESTER @ THE HUNTS POINT WWTP | 6 | CONSTRUCTION TO 50% | Jun 2020 | May 2021 | Jun 2020 | May 2021
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-238-L | REPLACEMENT OF THE DIGESTER @ THE HUNTS POINT WWTP | 7 | CONSTRUCTION TO 75% | May 2021 | May 2022 | May 2021 | May 2022
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-238-L | REPLACEMENT OF THE DIGESTER @ THE HUNTS POINT WWTP | 8 | ORIGINAL EQUIP & FURNISHING | May 2022 | Feb 2023 | May 2022 | Feb 2023
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-238-L | REPLACEMENT OF THE DIGESTER @ THE HUNTS POINT WWTP | 9 | SUBSTANTIAL COMPLETION | Feb 2023 | Aug 2023 | Feb 2023 | Aug 2023
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-238-L | REPLACEMENT OF THE DIGESTER @ THE HUNTS POINT WWTP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2023 | Nov 2023 | Aug 2023 | Nov 2023
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-239-L | RECONSTRUCT SLUDGE HANDLING EQUIPMENT @ HUNTS POINT WWTP | 1 | DEVELOP SCOPE | Jun 2019 | Feb 2020 | Jun 2023 | Feb 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-239-L | RECONSTRUCT SLUDGE HANDLING EQUIPMENT @ HUNTS POINT WWTP | 2 | PRELIMINARY DESIGN | Feb 2020 | Feb 2021 | Feb 2024 | Feb 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-239-L | RECONSTRUCT SLUDGE HANDLING EQUIPMENT @ HUNTS POINT WWTP | 3 | FINAL DESIGN | Feb 2021 | Aug 2022 | Feb 2025 | Aug 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-239-L | RECONSTRUCT SLUDGE HANDLING EQUIPMENT @ HUNTS POINT WWTP | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2022 | May 2023 | Aug 2026 | May 2027
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-239-L | RECONSTRUCT SLUDGE HANDLING EQUIPMENT @ HUNTS POINT WWTP | 5 | CONSTRUCTION TO 25% | May 2023 | May 2024 | May 2027 | May 2028
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-239-L | RECONSTRUCT SLUDGE HANDLING EQUIPMENT @ HUNTS POINT WWTP | 6 | CONSTRUCTION TO 50% | May 2024 | Apr 2025 | May 2028 | Apr 2029
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-239-L | RECONSTRUCT SLUDGE HANDLING EQUIPMENT @ HUNTS POINT WWTP | 7 | CONSTRUCTION TO 75% | Apr 2025 | Apr 2026 | Apr 2029 | Apr 2030
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-239-L | RECONSTRUCT SLUDGE HANDLING EQUIPMENT @ HUNTS POINT WWTP | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2026 | Jan 2027 | Apr 2030 | Jan 2031
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-239-L | RECONSTRUCT SLUDGE HANDLING EQUIPMENT @ HUNTS POINT WWTP | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Jul 2027 | Jan 2031 | Jul 2031
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-239-L | RECONSTRUCT SLUDGE HANDLING EQUIPMENT @ HUNTS POINT WWTP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2027 | Oct 2027 | Jul 2031 | Oct 2031
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-242-L | RECONSTRUCTION OF SEAWALL/SLUDGE LOADING DOCK AT HUNTS POINT | 1 | FINAL DESIGN | Jun 2025 | Nov 2026 | Jun 2023 | Nov 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-242-L | RECONSTRUCTION OF SEAWALL/SLUDGE LOADING DOCK AT HUNTS POINT | 2 | CONSTRUCTION TO 25% | Nov 2026 | Jul 2027 | Nov 2024 | Jul 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-242-L | RECONSTRUCTION OF SEAWALL/SLUDGE LOADING DOCK AT HUNTS POINT | 3 | CONSTRUCTION TO 50% | Jul 2027 | Mar 2028 | Jul 2025 | Mar 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-242-L | RECONSTRUCTION OF SEAWALL/SLUDGE LOADING DOCK AT HUNTS POINT | 4 | CONSTRUCTION TO 75% | Mar 2028 | Nov 2028 | Mar 2026 | Nov 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-247-L | RECONS FIRE ALARM SYS IN DEWATERING FACILITY @ HUNTS POINT | 1 | DEVELOP SCOPE | Jun 2019 | Aug 2019 | Jun 2019 | Feb 2020
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-247-L | RECONS FIRE ALARM SYS IN DEWATERING FACILITY @ HUNTS POINT | 2 | PRELIMINARY DESIGN | Aug 2019 | Dec 2019 | Feb 2020 | Feb 2021
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-247-L | RECONS FIRE ALARM SYS IN DEWATERING FACILITY @ HUNTS POINT | 3 | FINAL DESIGN | Dec 2019 | Jun 2020 | Feb 2021 | Aug 2022
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-247-L | RECONS FIRE ALARM SYS IN DEWATERING FACILITY @ HUNTS POINT | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Sep 2020 | Aug 2022 | May 2023
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-247-L | RECONS FIRE ALARM SYS IN DEWATERING FACILITY @ HUNTS POINT | 5 | CONSTRUCTION TO 25% | Sep 2020 | Jan 2021 | May 2023 | May 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-247-L | RECONS FIRE ALARM SYS IN DEWATERING FACILITY @ HUNTS POINT | 6 | CONSTRUCTION TO 50% | Jan 2021 | May 2021 | May 2024 | Apr 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-247-L | RECONS FIRE ALARM SYS IN DEWATERING FACILITY @ HUNTS POINT | 7 | CONSTRUCTION TO 75% | May 2021 | Sep 2021 | Apr 2025 | Apr 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-247-L | RECONS FIRE ALARM SYS IN DEWATERING FACILITY @ HUNTS POINT | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Dec 2021 | Apr 2026 | Jan 2027
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-247-L | RECONS FIRE ALARM SYS IN DEWATERING FACILITY @ HUNTS POINT | 9 | SUBSTANTIAL COMPLETION | Dec 2021 | Feb 2022 | Jan 2027 | Jul 2027
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-247-L | RECONS FIRE ALARM SYS IN DEWATERING FACILITY @ HUNTS POINT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2022 | Mar 2022 | Jul 2027 | Oct 2027
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-252-L | INSTALL (2) MOTOR CONTROL CENTERS (MCCS) @ HUNTS POINT WWTP | 1 | DEVELOP SCOPE | Jun 2019 | Aug 2019 | Jun 2019 | Aug 2019
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-252-L | INSTALL (2) MOTOR CONTROL CENTERS (MCCS) @ HUNTS POINT WWTP | 2 | PRELIMINARY DESIGN | Aug 2019 | Dec 2019 | Aug 2019 | Dec 2019
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-252-L | INSTALL (2) MOTOR CONTROL CENTERS (MCCS) @ HUNTS POINT WWTP | 3 | FINAL DESIGN | Dec 2019 | Jun 2020 | Dec 2019 | Jun 2020
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-252-L | INSTALL (2) MOTOR CONTROL CENTERS (MCCS) @ HUNTS POINT WWTP | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-252-L | INSTALL (2) MOTOR CONTROL CENTERS (MCCS) @ HUNTS POINT WWTP | 5 | CONSTRUCTION TO 25% | Sep 2020 | Jan 2021 | Sep 2020 | Jan 2021
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-252-L | INSTALL (2) MOTOR CONTROL CENTERS (MCCS) @ HUNTS POINT WWTP | 6 | CONSTRUCTION TO 50% | Jan 2021 | May 2021 | Jan 2021 | May 2021
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-252-L | INSTALL (2) MOTOR CONTROL CENTERS (MCCS) @ HUNTS POINT WWTP | 7 | CONSTRUCTION TO 75% | May 2021 | Sep 2021 | May 2021 | Sep 2021
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-252-L | INSTALL (2) MOTOR CONTROL CENTERS (MCCS) @ HUNTS POINT WWTP | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Dec 2021 | Sep 2021 | Dec 2021
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-252-L | INSTALL (2) MOTOR CONTROL CENTERS (MCCS) @ HUNTS POINT WWTP | 9 | SUBSTANTIAL COMPLETION | Dec 2021 | Feb 2022 | Dec 2021 | Feb 2022
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-252-L | INSTALL (2) MOTOR CONTROL CENTERS (MCCS) @ HUNTS POINT WWTP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2022 | Mar 2022 | Feb 2022 | Mar 2022
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-253-L | INSTALL EDDY CURRENT DRIVE SYS. FOR MSP @ HUNTS POINT | 1 | FINAL DESIGN | Jun 2022 | Nov 2023 | Jun 2019 | Feb 2020
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-253-L | INSTALL EDDY CURRENT DRIVE SYS. FOR MSP @ HUNTS POINT | 2 | CONSTRUCTION TO 25% | Nov 2023 | Jul 2024 | Feb 2020 | Feb 2021
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-253-L | INSTALL EDDY CURRENT DRIVE SYS. FOR MSP @ HUNTS POINT | 3 | CONSTRUCTION TO 50% | Jul 2024 | Mar 2025 | Feb 2021 | Aug 2022
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-253-L | INSTALL EDDY CURRENT DRIVE SYS. FOR MSP @ HUNTS POINT | 4 | CONSTRUCTION TO 75% | Mar 2025 | Nov 2025 | Aug 2022 | May 2023
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-253-L | INSTALL EDDY CURRENT DRIVE SYS. FOR MSP @ HUNTS POINT | 5 | CONSTRUCTION TO 25% | Mar 2025 | Nov 2025 | May 2023 | May 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-253-L | INSTALL EDDY CURRENT DRIVE SYS. FOR MSP @ HUNTS POINT | 6 | CONSTRUCTION TO 50% | Mar 2025 | Nov 2025 | May 2024 | Apr 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-253-L | INSTALL EDDY CURRENT DRIVE SYS. FOR MSP @ HUNTS POINT | 7 | CONSTRUCTION TO 75% | Mar 2025 | Nov 2025 | Apr 2025 | Apr 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-253-L | INSTALL EDDY CURRENT DRIVE SYS. FOR MSP @ HUNTS POINT | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2025 | Nov 2025 | Apr 2026 | Jan 2027
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-253-L | INSTALL EDDY CURRENT DRIVE SYS. FOR MSP @ HUNTS POINT | 9 | SUBSTANTIAL COMPLETION | Mar 2025 | Nov 2025 | Jan 2027 | Jul 2031
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-253-L | INSTALL EDDY CURRENT DRIVE SYS. FOR MSP @ HUNTS POINT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Nov 2025 | Jul 2031 | Oct 2031
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-254-L | TRC - CONS OF DECHLORINATION FACILITY @ HUNTS POINT WWTP | 1 | PRE-CONSTRUCTION MOBILIZATION | Feb 2020 | Jan 2021 | Feb 2020 | Jan 2021
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-254-L | TRC - CONS OF DECHLORINATION FACILITY @ HUNTS POINT WWTP | 2 | ON-SITE CONSTRUCTION MANAGEMEN | Jan 2021 | Dec 2026 | Jan 2021 | Dec 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-254-L | TRC - CONS OF DECHLORINATION FACILITY @ HUNTS POINT WWTP | 3 | POST-CONSTRUCTION CLOSE-OUT | Dec 2026 | Dec 2027 | Dec 2026 | Dec 2027
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-3R | RECONSTRUCTION OF EXISTING DIGESTERS AT HUNTS POINT WPCP | 2 | PRELIMINARY DESIGN | Mar 2009 | Mar 2010 | Apr 2011 | Apr 2012
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-3R | RECONSTRUCTION OF EXISTING DIGESTERS AT HUNTS POINT WPCP | 3 | FINAL DESIGN | Mar 2010 | Aug 2011 | Apr 2012 | Sep 2013
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-3R | RECONSTRUCTION OF EXISTING DIGESTERS AT HUNTS POINT WPCP | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2011 | May 2012 | Sep 2013 | Jun 2014
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-3R | RECONSTRUCTION OF EXISTING DIGESTERS AT HUNTS POINT WPCP | 5 | CONSTRUCTION TO 25% | May 2012 | May 2013 | Jun 2014 | Jun 2015
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-3R | RECONSTRUCTION OF EXISTING DIGESTERS AT HUNTS POINT WPCP | 6 | CONSTRUCTION TO 50% | May 2013 | May 2014 | Jun 2015 | Jun 2016
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-3R | RECONSTRUCTION OF EXISTING DIGESTERS AT HUNTS POINT WPCP | 7 | CONSTRUCTION TO 75% | May 2014 | May 2015 | Jun 2016 | Jun 2017
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-3R | RECONSTRUCTION OF EXISTING DIGESTERS AT HUNTS POINT WPCP | 8 | ORIGINAL EQUIP & FURNISHING | May 2015 | Feb 2016 | Jun 2017 | Mar 2018
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-3R | RECONSTRUCTION OF EXISTING DIGESTERS AT HUNTS POINT WPCP | 9 | SUBSTANTIAL COMPLETION | Feb 2016 | Aug 2016 | Mar 2018 | Aug 2022
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-3R | RECONSTRUCTION OF EXISTING DIGESTERS AT HUNTS POINT WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2016 | Oct 2016 | Aug 2022 | Nov 2022
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-STAB | STABILIZATION OF THE HUNTS POINT WPCP | 2 | PRELIMINARY DESIGN | Apr 1999 | Apr 2000
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-STAB | STABILIZATION OF THE HUNTS POINT WPCP | 3 | FINAL DESIGN | Apr 2000 | Sep 2001
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-STAB | STABILIZATION OF THE HUNTS POINT WPCP | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2001 | Jun 2002
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-STAB | STABILIZATION OF THE HUNTS POINT WPCP | 5 | CONSTRUCTION TO 25% | Jun 2002 | Jun 2003
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-STAB | STABILIZATION OF THE HUNTS POINT WPCP | 6 | CONSTRUCTION TO 50% | Jun 2003 | Jun 2004
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-STAB | STABILIZATION OF THE HUNTS POINT WPCP | 7 | CONSTRUCTION TO 75% | Jun 2004 | Jun 2005
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-STAB | STABILIZATION OF THE HUNTS POINT WPCP | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2005 | Mar 2006
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-STAB | STABILIZATION OF THE HUNTS POINT WPCP | 9 | SUBSTANTIAL COMPLETION | Mar 2006 | Aug 2006
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-STAB | STABILIZATION OF THE HUNTS POINT WPCP | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2006 | Nov 2006
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | JRAQ-REH | JEROME RESERVOIR & AQUEDUCT REHABILITATION | 1 | DEVELOP SCOPE | Jun 2019 | Feb 2020 | Jun 2017 | Feb 2018
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | JRAQ-REH | JEROME RESERVOIR & AQUEDUCT REHABILITATION | 2 | PRELIMINARY DESIGN | Feb 2020 | Feb 2021 | Feb 2018 | Feb 2019
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | JRAQ-REH | JEROME RESERVOIR & AQUEDUCT REHABILITATION | 3 | FINAL DESIGN | Feb 2021 | Aug 2022 | Feb 2019 | Aug 2020
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | JRAQ-REH | JEROME RESERVOIR & AQUEDUCT REHABILITATION | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2022 | May 2023 | Aug 2020 | May 2021
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | JRAQ-REH | JEROME RESERVOIR & AQUEDUCT REHABILITATION | 5 | CONSTRUCTION TO 25% | May 2023 | May 2024 | May 2021 | May 2022
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | JRAQ-REH | JEROME RESERVOIR & AQUEDUCT REHABILITATION | 6 | CONSTRUCTION TO 50% | May 2024 | Apr 2025 | May 2022 | Apr 2023
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | JRAQ-REH | JEROME RESERVOIR & AQUEDUCT REHABILITATION | 7 | CONSTRUCTION TO 75% | Apr 2025 | Apr 2026 | May 2023 | Apr 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | JRAQ-REH | JEROME RESERVOIR & AQUEDUCT REHABILITATION | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2026 | Jan 2027 | Apr 2024 | Jan 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | JRAQ-REH | JEROME RESERVOIR & AQUEDUCT REHABILITATION | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Jul 2027 | Jan 2025 | Jul 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | JRAQ-REH | JEROME RESERVOIR & AQUEDUCT REHABILITATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2027 | Oct 2027 | Jul 2025 | Oct 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | LSLRPBX1 | Lead Service Line Replacement Program for the Bronx | 1 | DEVELOP SCOPE | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | LSLRPBX1 | Lead Service Line Replacement Program for the Bronx | 2 | PRELIMINARY DESIGN | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | LSLRPBX1 | Lead Service Line Replacement Program for the Bronx | 3 | FINAL DESIGN | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | LSLRPBX1 | Lead Service Line Replacement Program for the Bronx | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2024 | Feb 2025 | Nov 2024 | Feb 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | LSLRPBX1 | Lead Service Line Replacement Program for the Bronx | 5 | CONSTRUCTION TO 25% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | LSLRPBX1 | Lead Service Line Replacement Program for the Bronx | 6 | CONSTRUCTION TO 50% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | LSLRPBX1 | Lead Service Line Replacement Program for the Bronx | 7 | CONSTRUCTION TO 75% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | LSLRPBX1 | Lead Service Line Replacement Program for the Bronx | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2026 | May 2026 | Feb 2026 | May 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | LSLRPBX1 | Lead Service Line Replacement Program for the Bronx | 9 | SUBSTANTIAL COMPLETION | May 2026 | Jul 2026 | May 2026 | Jul 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | LSLRPBX1 | Lead Service Line Replacement Program for the Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2026 | Aug 2026 | Jul 2026 | Aug 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | LSLRPBX2 | Lead Service Line Replacement Program for the Bronx | 1 | DEVELOP SCOPE | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | LSLRPBX2 | Lead Service Line Replacement Program for the Bronx | 2 | PRELIMINARY DESIGN | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | LSLRPBX2 | Lead Service Line Replacement Program for the Bronx | 3 | FINAL DESIGN | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | LSLRPBX2 | Lead Service Line Replacement Program for the Bronx | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2024 | Feb 2025 | Nov 2024 | Feb 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | LSLRPBX2 | Lead Service Line Replacement Program for the Bronx | 5 | CONSTRUCTION TO 25% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | LSLRPBX2 | Lead Service Line Replacement Program for the Bronx | 6 | CONSTRUCTION TO 50% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | LSLRPBX2 | Lead Service Line Replacement Program for the Bronx | 7 | CONSTRUCTION TO 75% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | LSLRPBX2 | Lead Service Line Replacement Program for the Bronx | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2026 | May 2026 | Feb 2026 | May 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | LSLRPBX2 | Lead Service Line Replacement Program for the Bronx | 9 | SUBSTANTIAL COMPLETION | May 2026 | Jul 2026 | May 2026 | Jul 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | LSLRPBX2 | Lead Service Line Replacement Program for the Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2026 | Aug 2026 | Jul 2026 | Aug 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | LSLRPBX3 | Lead Service Line Replacement Program for the Bronx | 1 | DEVELOP SCOPE | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | LSLRPBX3 | Lead Service Line Replacement Program for the Bronx | 2 | PRELIMINARY DESIGN | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | LSLRPBX3 | Lead Service Line Replacement Program for the Bronx | 3 | FINAL DESIGN | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | LSLRPBX3 | Lead Service Line Replacement Program for the Bronx | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2024 | Feb 2025 | Nov 2024 | Feb 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | LSLRPBX3 | Lead Service Line Replacement Program for the Bronx | 5 | CONSTRUCTION TO 25% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | LSLRPBX3 | Lead Service Line Replacement Program for the Bronx | 6 | CONSTRUCTION TO 50% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | LSLRPBX3 | Lead Service Line Replacement Program for the Bronx | 7 | CONSTRUCTION TO 75% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | LSLRPBX3 | Lead Service Line Replacement Program for the Bronx | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2026 | May 2026 | Feb 2026 | May 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | LSLRPBX3 | Lead Service Line Replacement Program for the Bronx | 9 | SUBSTANTIAL COMPLETION | May 2026 | Jul 2026 | May 2026 | Jul 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | LSLRPBX3 | Lead Service Line Replacement Program for the Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2026 | Aug 2026 | Jul 2026 | Aug 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | NCA24A | Demolition of NCA Shaft 24 Blow-Off Chamber | 1 | DEVELOP SCOPE | Mar 2023 | Dec 2023 | Mar 2023 | Dec 2023
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | NCA24A | Demolition of NCA Shaft 24 Blow-Off Chamber | 2 | PRELIMINARY DESIGN | Dec 2023 | Dec 2024 | Dec 2023 | Dec 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | NCA24A | Demolition of NCA Shaft 24 Blow-Off Chamber | 3 | FINAL DESIGN | Dec 2024 | Jun 2026 | Dec 2024 | Jun 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | NCA24A | Demolition of NCA Shaft 24 Blow-Off Chamber | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2026 | Mar 2027 | Jun 2026 | Mar 2027
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | NCA24A | Demolition of NCA Shaft 24 Blow-Off Chamber | 5 | CONSTRUCTION TO 25% | Mar 2027 | Feb 2028 | Mar 2027 | Feb 2028
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | NCA24A | Demolition of NCA Shaft 24 Blow-Off Chamber | 6 | CONSTRUCTION TO 50% | Feb 2028 | Feb 2029 | Feb 2028 | Feb 2029
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | NCA24A | Demolition of NCA Shaft 24 Blow-Off Chamber | 7 | CONSTRUCTION TO 75% | Feb 2029 | Feb 2030 | Feb 2029 | Feb 2030
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | NCA24A | Demolition of NCA Shaft 24 Blow-Off Chamber | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2030 | Nov 2030 | Feb 2030 | Nov 2030
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | NCA24A | Demolition of NCA Shaft 24 Blow-Off Chamber | 9 | SUBSTANTIAL COMPLETION | Nov 2030 | May 2031 | Nov 2030 | May 2031
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | NCA24A | Demolition of NCA Shaft 24 Blow-Off Chamber | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2031 | Aug 2031 | May 2031 | Aug 2031
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PINX11029 | Dist WM Replacement over Tremont Ave Bridge, Bronx | 1 | DEVELOP SCOPE | Oct 2023 | Jan 2024 | Oct 2023 | Jan 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PINX11029 | Dist WM Replacement over Tremont Ave Bridge, Bronx | 2 | PRELIMINARY DESIGN | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PINX11029 | Dist WM Replacement over Tremont Ave Bridge, Bronx | 3 | FINAL DESIGN | May 2024 | Nov 2024 | May 2024 | Nov 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PINX11029 | Dist WM Replacement over Tremont Ave Bridge, Bronx | 4 | BID AWARD AND REGISTER CONTRCT | Nov 2024 | Feb 2025 | Nov 2024 | Feb 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PINX11029 | Dist WM Replacement over Tremont Ave Bridge, Bronx | 5 | CONSTRUCTION TO 25% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PINX11029 | Dist WM Replacement over Tremont Ave Bridge, Bronx | 6 | CONSTRUCTION TO 50% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PINX11029 | Dist WM Replacement over Tremont Ave Bridge, Bronx | 7 | CONSTRUCTION TO 75% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PINX11029 | Dist WM Replacement over Tremont Ave Bridge, Bronx | 8 | ORIGINAL EQUIP & FURNISHING | Feb 2026 | May 2026 | Feb 2026 | May 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PINX11029 | Dist WM Replacement over Tremont Ave Bridge, Bronx | 9 | SUBSTANTIAL COMPLETION | May 2026 | Jul 2026 | May 2026 | Jul 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PINX11029 | Dist WM Replacement over Tremont Ave Bridge, Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2026 | Aug 2026 | Jul 2026 | Aug 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-236A | Throgs Neck Pumping Station Rehabilitation and Improvements | 1 | DEVELOP SCOPE | Jul 2019 | Mar 2020 | Jul 2019 | Mar 2020
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-236A | Throgs Neck Pumping Station Rehabilitation and Improvements | 2 | PRELIMINARY DESIGN | Mar 2020 | Mar 2021 | Mar 2020 | Mar 2021
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-236A | Throgs Neck Pumping Station Rehabilitation and Improvements | 3 | FINAL DESIGN | Mar 2021 | Sep 2022 | Mar 2021 | Sep 2022
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-236A | Throgs Neck Pumping Station Rehabilitation and Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2022 | Jun 2023 | Sep 2022 | Jun 2023
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-236A | Throgs Neck Pumping Station Rehabilitation and Improvements | 5 | CONSTRUCTION TO 25% | Jun 2023 | Jun 2024 | Jun 2023 | Jun 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-236A | Throgs Neck Pumping Station Rehabilitation and Improvements | 6 | CONSTRUCTION TO 50% | Jun 2024 | May 2025 | Jun 2024 | May 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-236A | Throgs Neck Pumping Station Rehabilitation and Improvements | 7 | CONSTRUCTION TO 75% | May 2025 | May 2026 | May 2025 | May 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-236A | Throgs Neck Pumping Station Rehabilitation and Improvements | 8 | ORIGINAL EQUIP & FURNISHING | May 2026 | Feb 2027 | May 2026 | Feb 2027
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-236A | Throgs Neck Pumping Station Rehabilitation and Improvements | 9 | SUBSTANTIAL COMPLETION | Feb 2027 | Aug 2027 | Feb 2027 | Aug 2027
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-236A | Throgs Neck Pumping Station Rehabilitation and Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2027 | Nov 2027 | Aug 2027 | Nov 2027
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-288 | 233RD STREET PUMPING STATION | 1 | FINAL DESIGN | Jun 2020 | Nov 2021 | Jun 2021 | Feb 2022
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-288 | 233RD STREET PUMPING STATION | 2 | CONSTRUCTION TO 25% | Nov 2021 | Jul 2022 | Feb 2022 | Feb 2023
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-288 | 233RD STREET PUMPING STATION | 3 | CONSTRUCTION TO 50% | Jul 2022 | Mar 2023 | Feb 2023 | Aug 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-288 | 233RD STREET PUMPING STATION | 4 | CONSTRUCTION TO 75% | Mar 2023 | Nov 2023 | Aug 2024 | May 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-288 | 233RD STREET PUMPING STATION | 5 | CONSTRUCTION TO 25% | Mar 2023 | Nov 2023 | May 2025 | May 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-288 | 233RD STREET PUMPING STATION | 6 | CONSTRUCTION TO 50% | Mar 2023 | Nov 2023 | May 2026 | Apr 2027
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-288 | 233RD STREET PUMPING STATION | 7 | CONSTRUCTION TO 75% | Mar 2023 | Nov 2023 | May 2027 | Apr 2028
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-288 | 233RD STREET PUMPING STATION | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2023 | Nov 2023 | Apr 2028 | Jan 2029
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-288 | 233RD STREET PUMPING STATION | 9 | SUBSTANTIAL COMPLETION | Mar 2023 | Nov 2023 | Jan 2029 | Jul 2033
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-288 | 233RD STREET PUMPING STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Nov 2023 | Jul 2033 | Oct 2033
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-290 | CONNER STREET PUMPING STATION | 1 | DEVELOP SCOPE | Jul 2016 | Mar 2017 | Jul 2022 | Mar 2023
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-290 | CONNER STREET PUMPING STATION | 2 | PRELIMINARY DESIGN | Mar 2017 | Mar 2018 | Mar 2023 | Mar 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-290 | CONNER STREET PUMPING STATION | 3 | FINAL DESIGN | Mar 2018 | Sep 2019 | Mar 2024 | Sep 2025
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-290 | CONNER STREET PUMPING STATION | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Jun 2020 | Sep 2025 | Jun 2026
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-290 | CONNER STREET PUMPING STATION | 5 | CONSTRUCTION TO 25% | Jun 2020 | Jun 2021 | Jun 2026 | Jun 2027
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-290 | CONNER STREET PUMPING STATION | 6 | CONSTRUCTION TO 50% | Jun 2021 | May 2022 | Jun 2027 | May 2028
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-290 | CONNER STREET PUMPING STATION | 7 | CONSTRUCTION TO 75% | May 2022 | May 2023 | May 2028 | May 2029
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-290 | CONNER STREET PUMPING STATION | 8 | ORIGINAL EQUIP & FURNISHING | May 2023 | Feb 2024 | May 2029 | Feb 2030
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-290 | CONNER STREET PUMPING STATION | 9 | SUBSTANTIAL COMPLETION | Feb 2024 | Aug 2024 | Feb 2030 | Aug 2030
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-290 | CONNER STREET PUMPING STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2024 | Nov 2024 | Aug 2030 | Nov 2030
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-313 | RECONSTRUCTION OF 235TH STREET PUMPING STATION | 1 | DEVELOP SCOPE | Jul 2016 | Mar 2017 | Jul 2016 | Mar 2017
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-313 | RECONSTRUCTION OF 235TH STREET PUMPING STATION | 2 | PRELIMINARY DESIGN | Mar 2017 | Mar 2018 | Mar 2017 | Mar 2018
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-313 | RECONSTRUCTION OF 235TH STREET PUMPING STATION | 3 | FINAL DESIGN | Mar 2018 | Sep 2019 | Mar 2018 | Sep 2019
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-313 | RECONSTRUCTION OF 235TH STREET PUMPING STATION | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Jun 2020 | Sep 2019 | Jun 2020
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-313 | RECONSTRUCTION OF 235TH STREET PUMPING STATION | 5 | CONSTRUCTION TO 25% | Jun 2020 | Jun 2021 | Jun 2020 | Jun 2021
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-313 | RECONSTRUCTION OF 235TH STREET PUMPING STATION | 6 | CONSTRUCTION TO 50% | Jun 2021 | May 2022 | Jun 2021 | May 2022
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-313 | RECONSTRUCTION OF 235TH STREET PUMPING STATION | 7 | CONSTRUCTION TO 75% | May 2022 | May 2023 | May 2022 | May 2023
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-313 | RECONSTRUCTION OF 235TH STREET PUMPING STATION | 8 | ORIGINAL EQUIP & FURNISHING | May 2023 | Feb 2024 | May 2023 | Feb 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-313 | RECONSTRUCTION OF 235TH STREET PUMPING STATION | 9 | SUBSTANTIAL COMPLETION | Feb 2024 | Aug 2024 | Feb 2024 | Aug 2024
20231026 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-313 | RECONSTRUCTION OF 235TH STREET PUMPING STATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2024 | Nov 2024 | Aug 2024 | Nov 2024
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-332M | BRONX 6/6A GARAGE REHAB | 1 | DEVELOP SCOPE | Jul 2016 | Jun 2017 | Jul 2016 | Jun 2017
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-332M | BRONX 6/6A GARAGE REHAB | 2 | PRELIMINARY DESIGN | Jul 2017 | Mar 2018 | Jul 2017 | Mar 2018
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-332M | BRONX 6/6A GARAGE REHAB | 3 | FINAL DESIGN | Mar 2018 | Dec 2018 | Mar 2018 | Dec 2018
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-332M | BRONX 6/6A GARAGE REHAB | 4 | BID AWARD AND REGISTER CONTRCT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-332M | BRONX 6/6A GARAGE REHAB | 5 | CONSTRUCTION TO 25% | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-332M | BRONX 6/6A GARAGE REHAB | 6 | CONSTRUCTION TO 50% | Sep 2020 | Aug 2022 | Sep 2020 | Aug 2022
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-332M | BRONX 6/6A GARAGE REHAB | 7 | CONSTRUCTION TO 75% | Aug 2022 | Jul 2024 | Aug 2022 | Jul 2024
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-332M | BRONX 6/6A GARAGE REHAB | 8 | SUBSTANTIAL COMPLETION | Jul 2024 | Jun 2026 | Jul 2024 | Jun 2026
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-332M | BRONX 6/6A GARAGE REHAB | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | May 2028 | Jun 2026 | May 2028
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-424 | Bronx 12 Rehabilitation (Slabs, Roof, Fueling Enclosure) | 1 | DEVELOP SCOPE | Jul 2014 | Aug 2014 | Jul 2014 | Aug 2014
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-424 | Bronx 12 Rehabilitation (Slabs, Roof, Fueling Enclosure) | 2 | PRELIMINARY DESIGN | Aug 2014 | Sep 2015 | Aug 2014 | Sep 2015
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-424 | Bronx 12 Rehabilitation (Slabs, Roof, Fueling Enclosure) | 3 | FINAL DESIGN | Sep 2015 | May 2017 | Sep 2015 | May 2017
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-424 | Bronx 12 Rehabilitation (Slabs, Roof, Fueling Enclosure) | 4 | BID AWARD AND REGISTER CONTRCT | May 2017 | Jun 2021 | May 2017 | Jun 2021
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-424 | Bronx 12 Rehabilitation (Slabs, Roof, Fueling Enclosure) | 5 | CONSTRUCTION TO 25% | Jun 2021 | Jun 2021 | Jun 2021 | Jun 2021
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-424 | Bronx 12 Rehabilitation (Slabs, Roof, Fueling Enclosure) | 6 | CONSTRUCTION TO 50% | Jun 2021 | Jun 2021 | Jun 2021 | Jun 2021
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-424 | Bronx 12 Rehabilitation (Slabs, Roof, Fueling Enclosure) | 7 | CONSTRUCTION TO 75% | Jun 2021 | Jun 2021 | Jun 2021 | Jun 2021
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-424 | Bronx 12 Rehabilitation (Slabs, Roof, Fueling Enclosure) | 8 | SUBSTANTIAL COMPLETION | Jun 2021 | Aug 2023 | Jun 2021 | Aug 2023
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-424 | Bronx 12 Rehabilitation (Slabs, Roof, Fueling Enclosure) | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2023 | May 2026 | Aug 2023 | May 2026
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-449C | Bronx 1787 W Farms Rd Rehab | 1 | DEVELOP SCOPE | Apr 2022 | Jun 2022 | Apr 2022 | Jun 2022
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-449C | Bronx 1787 W Farms Rd Rehab | 2 | PRELIMINARY DESIGN | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2022
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-449C | Bronx 1787 W Farms Rd Rehab | 3 | FINAL DESIGN | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-449C | Bronx 1787 W Farms Rd Rehab | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-449C | Bronx 1787 W Farms Rd Rehab | 5 | CONSTRUCTION TO 25% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-449C | Bronx 1787 W Farms Rd Rehab | 6 | CONSTRUCTION TO 50% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-449C | Bronx 1787 W Farms Rd Rehab | 7 | CONSTRUCTION TO 75% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-449C | Bronx 1787 W Farms Rd Rehab | 8 | SUBSTANTIAL COMPLETION | Jun 2024 | Nov 2024 | Jun 2024 | Nov 2024
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-449C | Bronx 1787 W Farms Rd Rehab | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2024 | Sep 2025 | Nov 2024 | Sep 2025
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S195-227 | BRONX 8 Van Cortlandt Park Salt Shed Tent | 1 | DEVELOP SCOPE | Mar 2023 | May 2023 | Mar 2023 | May 2023
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S195-227 | BRONX 8 Van Cortlandt Park Salt Shed Tent | 2 | PRELIMINARY DESIGN | May 2023 | Jul 2023 | May 2023 | Jul 2023
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S195-227 | BRONX 8 Van Cortlandt Park Salt Shed Tent | 3 | FINAL DESIGN | Jul 2023 | Sep 2023 | Jul 2023 | Sep 2023
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S195-227 | BRONX 8 Van Cortlandt Park Salt Shed Tent | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2023 | Dec 2023 | Sep 2023 | Dec 2023
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S195-227 | BRONX 8 Van Cortlandt Park Salt Shed Tent | 5 | CONSTRUCTION TO 25% | Dec 2023 | Mar 2024 | Dec 2023 | Mar 2024
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S195-227 | BRONX 8 Van Cortlandt Park Salt Shed Tent | 6 | CONSTRUCTION TO 50% | Mar 2024 | Jun 2024 | Mar 2024 | Jun 2024
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S195-227 | BRONX 8 Van Cortlandt Park Salt Shed Tent | 7 | CONSTRUCTION TO 75% | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S195-227 | BRONX 8 Van Cortlandt Park Salt Shed Tent | 8 | SUBSTANTIAL COMPLETION | Sep 2024 | Apr 2025 | Sep 2024 | Apr 2025
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S195-227 | BRONX 8 Van Cortlandt Park Salt Shed Tent | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2025 | Feb 2026 | Apr 2025 | Feb 2026
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S248-423 | Bronx 9/10/11 Garage Replacement | 1 | DEVELOP SCOPE | Dec 2015 | Jan 2017 | Dec 2015 | Jan 2017
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S248-423 | Bronx 9/10/11 Garage Replacement | 2 | PRELIMINARY DESIGN | Jan 2017 | May 2018 | Jan 2017 | May 2018
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S248-423 | Bronx 9/10/11 Garage Replacement | 3 | FINAL DESIGN | May 2018 | Sep 2019 | May 2018 | Jun 2020
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S248-423 | Bronx 9/10/11 Garage Replacement | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2019 | Jul 2020 | Jun 2020 | Mar 2021
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S248-423 | Bronx 9/10/11 Garage Replacement | 5 | CONSTRUCTION TO 25% | Jul 2020 | Nov 2021 | Mar 2021 | Jul 2022
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S248-423 | Bronx 9/10/11 Garage Replacement | 6 | CONSTRUCTION TO 50% | Nov 2021 | Mar 2023 | Jul 2022 | Dec 2023
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S248-423 | Bronx 9/10/11 Garage Replacement | 7 | CONSTRUCTION TO 75% | Mar 2023 | Aug 2024 | Dec 2023 | Apr 2025
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S248-423 | Bronx 9/10/11 Garage Replacement | 8 | SUBSTANTIAL COMPLETION | Aug 2024 | Dec 2025 | Apr 2025 | Aug 2026
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | S248-423 | Bronx 9/10/11 Garage Replacement | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2025 | Sep 2028 | Aug 2026 | Sep 2028
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12C | Hurricane Sandy Bronx 12 Garage Conduit Work | 3 | FINAL DESIGN | Nov 2018 | Sep 2019 | Nov 2018 | Sep 2019
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12C | Hurricane Sandy Bronx 12 Garage Conduit Work | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Jun 2020 | Sep 2019 | Jun 2020
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12C | Hurricane Sandy Bronx 12 Garage Conduit Work | 5 | CONSTRUCTION TO 25% | Jun 2020 | Mar 2021 | Jun 2020 | Mar 2021
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12C | Hurricane Sandy Bronx 12 Garage Conduit Work | 6 | CONSTRUCTION TO 50% | Mar 2021 | Jan 2022 | Mar 2021 | Jan 2022
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12C | Hurricane Sandy Bronx 12 Garage Conduit Work | 7 | CONSTRUCTION TO 75% | Jan 2022 | Apr 2023 | Jan 2022 | Apr 2023
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12C | Hurricane Sandy Bronx 12 Garage Conduit Work | 8 | SUBSTANTIAL COMPLETION | Apr 2023 | Nov 2024 | Apr 2023 | Nov 2024
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12C | Hurricane Sandy Bronx 12 Garage Conduit Work | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2024 | May 2027 | Nov 2024 | May 2027
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12G | Hurricane Sandy Bronx 12 Garage R/R & Haz Mitigation | 1 | DEVELOP SCOPE | Aug 2015 | Dec 2015 | Aug 2015 | Dec 2015
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12G | Hurricane Sandy Bronx 12 Garage R/R & Haz Mitigation | 2 | PRELIMINARY DESIGN | Dec 2015 | Jun 2016 | Dec 2015 | Jun 2016
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12G | Hurricane Sandy Bronx 12 Garage R/R & Haz Mitigation | 3 | FINAL DESIGN | Jun 2016 | Jun 2017 | Jun 2016 | Jun 2017
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12G | Hurricane Sandy Bronx 12 Garage R/R & Haz Mitigation | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2017 | Jun 2018 | Jun 2017 | Jun 2018
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12G | Hurricane Sandy Bronx 12 Garage R/R & Haz Mitigation | 5 | CONSTRUCTION TO 25% | Jun 2018 | Jun 2019 | Jun 2018 | Jun 2019
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12G | Hurricane Sandy Bronx 12 Garage R/R & Haz Mitigation | 6 | CONSTRUCTION TO 50% | Jun 2019 | Jun 2020 | Jun 2019 | Jun 2020
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12G | Hurricane Sandy Bronx 12 Garage R/R & Haz Mitigation | 7 | CONSTRUCTION TO 75% | Jun 2020 | Jun 2021 | Jun 2020 | Jun 2021
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12G | Hurricane Sandy Bronx 12 Garage R/R & Haz Mitigation | 8 | SUBSTANTIAL COMPLETION | Jun 2021 | Mar 2024 | Jun 2021 | Mar 2024
20231026 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12G | Hurricane Sandy Bronx 12 Garage R/R & Haz Mitigation | 9 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2021 | Jul 2024 | Oct 2021 | Jul 2024
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BRX2110 | BOSTON ROAD OVER BRONX RIVER BIN: 2242110 | 1 | DEVELOP SCOPE | Jun 2016 | Jun 2017 | Aug 2025 | Sep 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BRX2110 | BOSTON ROAD OVER BRONX RIVER BIN: 2242110 | 2 | DESIGN START | Jun 2017 | Jun 2021 | Nov 2019 | Sep 2021
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BRX2110 | BOSTON ROAD OVER BRONX RIVER BIN: 2242110 | 3 | CONSTRUCTION START | Jun 2021 | Jun 2023 | Sep 2023 | Aug 2031
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BRX9579 | BOSTON ROAD OVER HUTCHINSON RIVER BIN: 2229579 | 1 | DEVELOP SCOPE | Jun 2016 | Jun 2017 | Oct 2014 | Oct 2014
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BRX9579 | BOSTON ROAD OVER HUTCHINSON RIVER BIN: 2229579 | 2 | DESIGN START | Jun 2017 | Jun 2021 | Nov 2016 | Jun 2021
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BRX9579 | BOSTON ROAD OVER HUTCHINSON RIVER BIN: 2229579 | 3 | CONSTRUCTION START | Jun 2021 | Jun 2023 | Jun 2021 | Jun 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BXECONDEV | FA - BX Council for Economic Devel. - Streetscape Furniture | 1 | DESIGN | Jan 2006 | Jan 2006 | Jan 2025 | Mar 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BXECONDEV | FA - BX Council for Economic Devel. - Streetscape Furniture | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2004 | Aug 2004 | Apr 2025 | Jul 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BXECONDEV | FA - BX Council for Economic Devel. - Streetscape Furniture | 3 | CONSTRUCTION | Aug 2004 | Jun 2007 | Jul 2025 | Jan 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BXECONDEV | FA - BX Council for Economic Devel. - Streetscape Furniture | 4 | ORIGINAL EQUIP & FURNISHING | Jul 2007 | Jun 2007 | Jan 2026 | Apr 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BXECONDEV | FA - BX Council for Economic Devel. - Streetscape Furniture | 5 | SUBSTANTIAL COMPLETION | Jul 2007 | Jun 2007 | Apr 2026 | Aug 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BXECONDEV | FA - BX Council for Economic Devel. - Streetscape Furniture | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2007 | Jul 2007 | Aug 2026 | Dec 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BXECONDEV | FA - BX Council for Economic Devel. - Streetscape Furniture | 7 | CONSTRUCTION TO 75% | Jul 2007 | Jul 2007 | Dec 2026 | Apr 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BXECONDEV | FA - BX Council for Economic Devel. - Streetscape Furniture | 8 | ORIGINAL EQUIP & FURNISHING | Jul 2007 | Jul 2007 | Apr 2027 | Jul 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BXECONDEV | FA - BX Council for Economic Devel. - Streetscape Furniture | 9 | SUBSTANTIAL COMPLETION | Jul 2007 | Jul 2007 | Jul 2027 | Sep 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BXECONDEV | FA - BX Council for Economic Devel. - Streetscape Furniture | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2007 | Jul 2007 | Sep 2027 | Oct 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | CTYISLBRD | Reconstruction of City Island Access Bridge | 1 | DEVELOP SCOPE | Jun 2019 | Jun 2020 | Jun 2012 | Jun 2013
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | CTYISLBRD | Reconstruction of City Island Access Bridge | 2 | DESIGN START | Jun 2020 | Jun 2022 | Jun 2013 | Jun 2015
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | CTYISLBRD | Reconstruction of City Island Access Bridge | 3 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Jun 2015 | Jun 2031
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HB1070MN | Protective Coating of Metro North Bridges | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2021
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HB1070MN | Protective Coating of Metro North Bridges | 2 | DEVELOP SCOPE | Jun 2021 | Jun 2025 | Jun 2023 | Jun 2024
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HB1070MN | Protective Coating of Metro North Bridges | 3 | DESIGN START | Jun 2025 | Jun 2027 | Jun 2024 | Jun 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HB1070MN | Protective Coating of Metro North Bridges | 5 | CONSTRUCTION START | Jun 2025 | Jun 2027 | Jun 2028 | Jun 2030
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBB224222 | SNUFF MILL ROAD OVER BRONX RIVER BIN 2242220 | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBB224222 | SNUFF MILL ROAD OVER BRONX RIVER BIN 2242220 | 2 | DESIGN START | Jun 2022 | Jun 2026 | Jun 2021 | Jun 2022
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBB224222 | SNUFF MILL ROAD OVER BRONX RIVER BIN 2242220 | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2022 | Jun 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBB224222 | SNUFF MILL ROAD OVER BRONX RIVER BIN 2242220 | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBB241850 | CONN RD BETWEEN MOS OVER METRO NORTH RR-HAR BIN 2241850 | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBB241850 | CONN RD BETWEEN MOS OVER METRO NORTH RR-HAR BIN 2241850 | 2 | DESIGN START | Jun 2022 | Jun 2026 | Jun 2021 | Jun 2022
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBB241850 | CONN RD BETWEEN MOS OVER METRO NORTH RR-HAR BIN 2241850 | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2022 | Jun 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBB241850 | CONN RD BETWEEN MOS OVER METRO NORTH RR-HAR BIN 2241850 | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA06672 | EAST 174TH ST/SHERIDAN EXPWY AMTRAK BIN# 2066720 | 1 | DEVELOP SCOPE | Jul 2016 | Jun 2017
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA06672 | EAST 174TH ST/SHERIDAN EXPWY AMTRAK BIN# 2066720 | 2 | DESIGN START | Jul 2017 | Jun 2021 | Jan 2017 | Aug 2017
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA06672 | EAST 174TH ST/SHERIDAN EXPWY AMTRAK BIN# 2066720 | 3 | CONSTRUCTION START | Jun 2021 | Jun 2023 | Jun 2019 | Mar 2021
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA06672 | EAST 174TH ST/SHERIDAN EXPWY AMTRAK BIN# 2066720 | 5 | CONSTRUCTION START | Jun 2021 | Jun 2023 | Jul 2023 | Jul 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA06715 | NEREID AVE (E 240TH ST) over BRONX RIVER PKW BIN 1067150 | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2023
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA06715 | NEREID AVE (E 240TH ST) over BRONX RIVER PKW BIN 1067150 | 2 | DESIGN START | Jun 2023 | Jun 2027 | Jun 2022 | Jun 2023
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA06715 | NEREID AVE (E 240TH ST) over BRONX RIVER PKW BIN 1067150 | 3 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2023 | Jun 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA06715 | NEREID AVE (E 240TH ST) over BRONX RIVER PKW BIN 1067150 | 5 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2027 | Jun 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA07664 | DEPOT PLACE over METRO NORTH RR HUD 2076640 | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2023
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA07664 | DEPOT PLACE over METRO NORTH RR HUD 2076640 | 2 | DESIGN START | Jun 2023 | Jun 2027 | Jun 2024 | Jun 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA07664 | DEPOT PLACE over METRO NORTH RR HUD 2076640 | 3 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2025 | Jun 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA07664 | DEPOT PLACE over METRO NORTH RR HUD 2076640 | 5 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2029 | Jun 2031
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA07692 | BRUCKNER EXPRESSWAY over CSX - HUNTS POINT 2076929 | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2023
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA07692 | BRUCKNER EXPRESSWAY over CSX - HUNTS POINT 2076929 | 2 | DESIGN START | Jun 2023 | Jun 2027 | Jun 2022 | Jun 2023
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA07692 | BRUCKNER EXPRESSWAY over CSX - HUNTS POINT 2076929 | 3 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2023 | Jun 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA07692 | BRUCKNER EXPRESSWAY over CSX - HUNTS POINT 2076929 | 5 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2027 | Jun 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA23025 | MOSHOLU PKWY/BRONX RIVER 2-23025-0 (TD PKG) | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA23025 | MOSHOLU PKWY/BRONX RIVER 2-23025-0 (TD PKG) | 2 | DESIGN START | Jun 2022 | Jun 2026 | Jun 2021 | Jun 2022
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA23025 | MOSHOLU PKWY/BRONX RIVER 2-23025-0 (TD PKG) | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2022 | Jun 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA23025 | MOSHOLU PKWY/BRONX RIVER 2-23025-0 (TD PKG) | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24138 | Pelham Bay Park Equestrian over Amtrak- CSX BIN 2241380 | 1 | DEVELOP SCOPE | Jun 2017 | Jun 2018
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24138 | Pelham Bay Park Equestrian over Amtrak- CSX BIN 2241380 | 2 | DEVELOP SCOPE | Jun 2018 | Jun 2022 | Jun 2020 | Jun 2021
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24138 | Pelham Bay Park Equestrian over Amtrak- CSX BIN 2241380 | 3 | DESIGN START | Jun 2022 | Jun 2024 | Jun 2021 | Jun 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24138 | Pelham Bay Park Equestrian over Amtrak- CSX BIN 2241380 | 5 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Jun 2025 | Jun 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24180 | East 183rd St over MNRR Har BIN 2241800 | 1 | DEVELOP SCOPE | Jun 2017 | Jun 2018
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24180 | East 183rd St over MNRR Har BIN 2241800 | 2 | DESIGN START | Jun 2018 | Jun 2022 | Jul 2017 | Sep 2017
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24180 | East 183rd St over MNRR Har BIN 2241800 | 3 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Apr 2019 | Oct 2022
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24180 | East 183rd St over MNRR Har BIN 2241800 | 5 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Oct 2023 | Dec 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24181 | East 188th St over MNRR Har BIN 2241810 | 1 | DEVELOP SCOPE | Jun 2016 | Jun 2017
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24181 | East 188th St over MNRR Har BIN 2241810 | 2 | DESIGN START | Jun 2017 | Jun 2021 | Mar 2015 | Apr 2015
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24181 | East 188th St over MNRR Har BIN 2241810 | 3 | CONSTRUCTION START | Jun 2021 | Jun 2023 | Oct 2018 | Jan 2021
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24181 | East 188th St over MNRR Har BIN 2241810 | 5 | CONSTRUCTION START | Jun 2021 | Jun 2023 | Dec 2021 | Mar 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24214 | EAST TREMONT AVENUE over BRONX RIVER BIN 2242149 | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2023
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24214 | EAST TREMONT AVENUE over BRONX RIVER BIN 2242149 | 2 | DESIGN START | Jun 2023 | Jun 2027 | Jun 2024 | Jun 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24214 | EAST TREMONT AVENUE over BRONX RIVER BIN 2242149 | 3 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2025 | Jun 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24214 | EAST TREMONT AVENUE over BRONX RIVER BIN 2242149 | 5 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2029 | Jun 2031
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24236 | GRAND CONCOURSE over BURNSIDE AVENUE BIN 2242360 | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24236 | GRAND CONCOURSE over BURNSIDE AVENUE BIN 2242360 | 2 | DESIGN START | Jun 2022 | Jun 2026 | Jun 2021 | Jun 2022
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24236 | GRAND CONCOURSE over BURNSIDE AVENUE BIN 2242360 | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2022 | Jun 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24236 | GRAND CONCOURSE over BURNSIDE AVENUE BIN 2242360 | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24245 | EAST 233RD ST/ BRONX RIVER BIN # 2242459 | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Jun 2028 | Sep 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24245 | EAST 233RD ST/ BRONX RIVER BIN # 2242459 | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Sep 2028 | Jan 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24245 | EAST 233RD ST/ BRONX RIVER BIN # 2242459 | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Jan 2029 | Jul 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24245 | EAST 233RD ST/ BRONX RIVER BIN # 2242459 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Jul 2029 | Oct 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24245 | EAST 233RD ST/ BRONX RIVER BIN # 2242459 | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Oct 2029 | Feb 2030
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24245 | EAST 233RD ST/ BRONX RIVER BIN # 2242459 | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Feb 2030 | Jun 2030
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24245 | EAST 233RD ST/ BRONX RIVER BIN # 2242459 | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Jun 2030 | Oct 2030
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24245 | EAST 233RD ST/ BRONX RIVER BIN # 2242459 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Oct 2030 | Jan 2031
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24245 | EAST 233RD ST/ BRONX RIVER BIN # 2242459 | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Jan 2031 | Mar 2031
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24245 | EAST 233RD ST/ BRONX RIVER BIN # 2242459 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | Mar 2031 | Apr 2031
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA26654 | 278I over BRUCKNER BOULVARD 2266540 | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2023
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA26654 | 278I over BRUCKNER BOULVARD 2266540 | 2 | DESIGN START | Jun 2023 | Jun 2027 | Jun 2022 | Jun 2023
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA26654 | 278I over BRUCKNER BOULVARD 2266540 | 3 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2023 | Jun 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA26654 | 278I over BRUCKNER BOULVARD 2266540 | 5 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2027 | Jun 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA42081 | BRONX BOULEVARD SOUTHBOUND over BRONX RIVER BIN 2242081 | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA42081 | BRONX BOULEVARD SOUTHBOUND over BRONX RIVER BIN 2242081 | 2 | DESIGN START | Jun 2022 | Jun 2026 | Jun 2021 | Jun 2022
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA42081 | BRONX BOULEVARD SOUTHBOUND over BRONX RIVER BIN 2242081 | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2022 | Jun 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA42081 | BRONX BOULEVARD SOUTHBOUND over BRONX RIVER BIN 2242081 | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA42082 | BRONX BOULEVARD NORTHBOUND over BRONX RIVER BIN 2242082 | 1 | DEVELOP SCOPE | Jun 2021 | Jun 2022
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA42082 | BRONX BOULEVARD NORTHBOUND over BRONX RIVER BIN 2242082 | 2 | DESIGN START | Jun 2022 | Jun 2026 | Jun 2021 | Jun 2022
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA42082 | BRONX BOULEVARD NORTHBOUND over BRONX RIVER BIN 2242082 | 3 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2022 | Jun 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA42082 | BRONX BOULEVARD NORTHBOUND over BRONX RIVER BIN 2242082 | 5 | CONSTRUCTION START | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA66671 | BRUCKNER EXPESSWAY SOUTHBOUND over BRONX RIVER 2066671 | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2023
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA66671 | BRUCKNER EXPESSWAY SOUTHBOUND over BRONX RIVER 2066671 | 2 | DESIGN START | Jun 2023 | Jun 2027 | Jun 2024 | Jun 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA66671 | BRUCKNER EXPESSWAY SOUTHBOUND over BRONX RIVER 2066671 | 3 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2025 | Jun 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA66671 | BRUCKNER EXPESSWAY SOUTHBOUND over BRONX RIVER 2066671 | 5 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2029 | Jun 2031
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA66672 | BRUCKNER EXRESSWAY NORTHBOUND OVER BRONX RIVER 2066672 | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2023
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA66672 | BRUCKNER EXRESSWAY NORTHBOUND OVER BRONX RIVER 2066672 | 2 | DESIGN START | Jun 2023 | Jun 2027 | Jun 2024 | Jun 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA66672 | BRUCKNER EXRESSWAY NORTHBOUND OVER BRONX RIVER 2066672 | 3 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2025 | Jun 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA66672 | BRUCKNER EXRESSWAY NORTHBOUND OVER BRONX RIVER 2066672 | 5 | CONSTRUCTION START | Jun 2027 | Jun 2029 | Jun 2029 | Jun 2031
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1086 | WESTCHESTER AVE BR OVER HUTCH RIVER PKWY 2-075837 | 1 | DEVELOP SCOPE | Jul 2003 | Jun 2004
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1086 | WESTCHESTER AVE BR OVER HUTCH RIVER PKWY 2-075837 | 2 | DESIGN START | Jun 2004 | Jun 2008 | Jul 2017 | Jun 2018
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1086 | WESTCHESTER AVE BR OVER HUTCH RIVER PKWY 2-075837 | 3 | CONSTRUCTION START | Jun 2008 | Jun 2010 | Jul 2019 | Jun 2020
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1086 | WESTCHESTER AVE BR OVER HUTCH RIVER PKWY 2-075837 | 5 | CONSTRUCTION START | Jun 2008 | Jun 2010 | Jul 2021 | Jun 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1103 | CONCOURSE VLGE AVE/ M-N 2-24159-0 | 1 | DEVELOP SCOPE | Jul 2004 | Jun 2005 | Mar 2016 | Sep 2016
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1103 | CONCOURSE VLGE AVE/ M-N 2-24159-0 | 2 | DESIGN START | Jul 2005 | Jun 2009 | Jan 2019 | May 2022
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1103 | CONCOURSE VLGE AVE/ M-N 2-24159-0 | 3 | CONSTRUCTION START | Jun 2009 | Jun 2011 | Apr 2023 | Jul 2030
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1127 | RECON PELHAM PKWY BRIDGE OVER HUTCHINSON PKWY 2-07584-9 | 1 | DEVELOP SCOPE | Jul 2005 | Jun 2006
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1127 | RECON PELHAM PKWY BRIDGE OVER HUTCHINSON PKWY 2-07584-9 | 2 | DESIGN START | Jul 2006 | Jun 2010 | Nov 2021 | Mar 2022
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1127 | RECON PELHAM PKWY BRIDGE OVER HUTCHINSON PKWY 2-07584-9 | 3 | CONSTRUCTION START | Jun 2010 | Jun 2012 | Nov 2017 | Aug 2022
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1127 | RECON PELHAM PKWY BRIDGE OVER HUTCHINSON PKWY 2-07584-9 | 5 | CONSTRUCTION START | Jun 2010 | Jun 2012 | Jun 2022 | Sep 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1131 | BRUCKNER EXP / WESTCHESTER CREEK 1-066510 | 1 | DEVELOP SCOPE | Jul 2001 | Jun 2003
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1131 | BRUCKNER EXP / WESTCHESTER CREEK 1-066510 | 2 | DESIGN START | Jul 1999 | Jun 2003
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1131 | BRUCKNER EXP / WESTCHESTER CREEK 1-066510 | 3 | CONSTRUCTION START | Jun 2008 | Jun 2010
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1131 | BRUCKNER EXP / WESTCHESTER CREEK 1-066510 | 6 | DEVELOP SCOPE | Jun 2008 | Jun 2010 | Jun 2014 | Jul 2014
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1131 | BRUCKNER EXP / WESTCHESTER CREEK 1-066510 | 7 | DESIGN START | Jun 2008 | Jun 2010 | Jun 2014 | Aug 2016
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1131 | BRUCKNER EXP / WESTCHESTER CREEK 1-066510 | 8 | CONSTRUCTION START | Jun 2008 | Jun 2010 | Jul 2017 | Sep 2024
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1148B | SHORE ROAD BRIDGE / HUTCHINSON RIVER 2-240200 | 1 | DEVELOP SCOPE | Jul 2007 | Jun 2008 | Jul 2013 | Sep 2015
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1148B | SHORE ROAD BRIDGE / HUTCHINSON RIVER 2-240200 | 2 | DESIGN START | Jun 2008 | Jun 2012 | May 2017 | Mar 2023
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1148B | SHORE ROAD BRIDGE / HUTCHINSON RIVER 2-240200 | 3 | CONSTRUCTION START | Jun 2012 | Jun 2014 | Jan 2024 | Mar 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1190 | GRAND CONCOURSE / METRO NORTH RR HUD2-24140-9 | 1 | DEVELOP SCOPE | Jun 2004 | Jun 2005
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1190 | GRAND CONCOURSE / METRO NORTH RR HUD2-24140-9 | 2 | DESIGN START | Jun 2005 | Jun 2009 | Jan 2002 | Jul 2002
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1190 | GRAND CONCOURSE / METRO NORTH RR HUD2-24140-9 | 3 | CONSTRUCTION START | Jun 2009 | Jun 2011 | Jan 2000 | Oct 2019
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1190 | GRAND CONCOURSE / METRO NORTH RR HUD2-24140-9 | 5 | CONSTRUCTION START | Jun 2009 | Jun 2011 | Nov 2019 | Aug 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1215 | E. 175TH ST/METRO NORTH RR HAR 2-24174-0 TD PKG 1 | 1 | DEVELOP SCOPE | Jul 2005 | Jun 2006 | Jun 2007 | Jun 2010
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1215 | E. 175TH ST/METRO NORTH RR HAR 2-24174-0 TD PKG 1 | 2 | DESIGN START | Jul 2006 | Jun 2010 | Jul 2016 | Jun 2018
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1215 | E. 175TH ST/METRO NORTH RR HAR 2-24174-0 TD PKG 1 | 3 | CONSTRUCTION START | Jun 2010 | Jun 2012 | Jul 2018 | Jun 2024
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1460 | WEST TREMONT AVENUE OVER METRO NORTH RR BIN:2241460 | 1 | DEVELOP SCOPE | Jun 2015 | Jun 2016
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1460 | WEST TREMONT AVENUE OVER METRO NORTH RR BIN:2241460 | 2 | DESIGN START | Jun 2016 | Jun 2020 | Jun 2015 | Jun 2016
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1460 | WEST TREMONT AVENUE OVER METRO NORTH RR BIN:2241460 | 3 | CONSTRUCTION START | Jun 2020 | Jun 2022 | Jan 2018 | Feb 2021
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1460 | WEST TREMONT AVENUE OVER METRO NORTH RR BIN:2241460 | 5 | CONSTRUCTION START | Jun 2020 | Jun 2022 | Feb 2021 | May 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX156 | E 156TH ST BRIDGE OVER ACCESS TO HOUSING (BIN 2270030) | 1 | DEVELOP SCOPE | Jul 2015 | Jun 2016
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX156 | E 156TH ST BRIDGE OVER ACCESS TO HOUSING (BIN 2270030) | 2 | DESIGN START | Jun 2016 | Jun 2020 | Mar 2016 | Sep 2016
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX156 | E 156TH ST BRIDGE OVER ACCESS TO HOUSING (BIN 2270030) | 3 | CONSTRUCTION START | Jun 2020 | Jun 2022 | Jan 2019 | May 2022
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX156 | E 156TH ST BRIDGE OVER ACCESS TO HOUSING (BIN 2270030) | 5 | CONSTRUCTION START | Jun 2020 | Jun 2022 | May 2023 | Aug 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX163 | 5 Bridges - Melrose, Bronx | 1 | DEVELOP SCOPE | Jun 2014 | Jun 2015
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX163 | 5 Bridges - Melrose, Bronx | 2 | DEVELOP SCOPE | Jun 2015 | Jun 2019 | Jun 2012 | Jun 2013
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX163 | 5 Bridges - Melrose, Bronx | 3 | DESIGN START | Jun 2019 | Jun 2021 | Jul 2013 | Nov 2015
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX163 | 5 Bridges - Melrose, Bronx | 5 | CONSTRUCTION START | Jun 2019 | Jun 2021 | Jul 2017 | Jun 2021
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX180 | E. 180TH ST OVER METRO NORTH RR HAR (BIN 2-24179-0) | 1 | DEVELOP SCOPE | Jun 2011 | Jun 2014 | Jun 2017 | Jun 2018
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX180 | E. 180TH ST OVER METRO NORTH RR HAR (BIN 2-24179-0) | 2 | DESIGN START | Jun 2014 | Jun 2014 | Jun 2020 | Jul 2021
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX180 | E. 180TH ST OVER METRO NORTH RR HAR (BIN 2-24179-0) | 3 | CONSTRUCTION START | Jun 2014 | Jun 2020 | Jul 2022 | Jul 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX199 | E153RD ST BR AT PARK AVE OVER RR | 1 | DEVELOP SCOPE | Jul 2003 | Jun 2004
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX199 | E153RD ST BR AT PARK AVE OVER RR | 2 | DESIGN START | Jul 2004 | Jun 2008 | May 2021 | Feb 2023
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX199 | E153RD ST BR AT PARK AVE OVER RR | 3 | CONSTRUCTION START | Jun 2008 | Jun 2010 | Apr 2023 | Apr 2024
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX199 | E153RD ST BR AT PARK AVE OVER RR | 5 | CONSTRUCTION START | Jun 2008 | Jun 2010 | Mar 2025 | May 2031
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX2370 | REHAB GRAND CONCOURSE BIN 2242370 | 1 | DEVELOP SCOPE | Jun 2016 | Jun 2017
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX2370 | REHAB GRAND CONCOURSE BIN 2242370 | 2 | DESIGN START | Jun 2017 | Jun 2021 | Jul 2026 | Dec 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX2370 | REHAB GRAND CONCOURSE BIN 2242370 | 3 | CONSTRUCTION START | Jun 2021 | Jun 2023 | Dec 2027 | Dec 2031
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX2370 | REHAB GRAND CONCOURSE BIN 2242370 | 5 | CONSTRUCTION START | Jun 2021 | Jun 2023 | Dec 2031 | Dec 2035
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX644S | MADISON AVE BR - REHAB OF ELECTRICAL AND MECHANICAL SYSTEM | 1 | DEVELOP SCOPE | Jul 2005 | Jun 2006
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX644S | MADISON AVE BR - REHAB OF ELECTRICAL AND MECHANICAL SYSTEM | 2 | DESIGN START | Jul 2006 | Jun 2010 | Jan 2016 | Mar 2016
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX644S | MADISON AVE BR - REHAB OF ELECTRICAL AND MECHANICAL SYSTEM | 3 | CONSTRUCTION START | Jun 2010 | Jun 2012 | Feb 2011 | Feb 2016
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX644S | MADISON AVE BR - REHAB OF ELECTRICAL AND MECHANICAL SYSTEM | 5 | CONSTRUCTION START | Jun 2010 | Jun 2012 | Dec 2024 | Sep 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21A | Citywide Milling - Bronx | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21A | Citywide Milling - Bronx | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21A | Citywide Milling - Bronx | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21A | Citywide Milling - Bronx | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21A | Citywide Milling - Bronx | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21A | Citywide Milling - Bronx | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21A | Citywide Milling - Bronx | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21A | Citywide Milling - Bronx | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21A | Citywide Milling - Bronx | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21A | Citywide Milling - Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWCWSTPR | NY RESTORATION PROJECT - DEVELOP & DESIGN STREET PIER | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2020 | Sep 2020
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWCWSTPR | NY RESTORATION PROJECT - DEVELOP & DESIGN STREET PIER | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2020 | Jan 2021
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWCWSTPR | NY RESTORATION PROJECT - DEVELOP & DESIGN STREET PIER | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jan 2021 | Jul 2021
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWCWSTPR | NY RESTORATION PROJECT - DEVELOP & DESIGN STREET PIER | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2021 | Oct 2021
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWCWSTPR | NY RESTORATION PROJECT - DEVELOP & DESIGN STREET PIER | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Oct 2021 | Feb 2022
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWCWSTPR | NY RESTORATION PROJECT - DEVELOP & DESIGN STREET PIER | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Feb 2022 | Jun 2022
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWCWSTPR | NY RESTORATION PROJECT - DEVELOP & DESIGN STREET PIER | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jun 2022 | Oct 2022
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWCWSTPR | NY RESTORATION PROJECT - DEVELOP & DESIGN STREET PIER | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Oct 2022 | Jan 2023
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWCWSTPR | NY RESTORATION PROJECT - DEVELOP & DESIGN STREET PIER | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jan 2023 | Mar 2023
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWCWSTPR | NY RESTORATION PROJECT - DEVELOP & DESIGN STREET PIER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Mar 2023 | Jun 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWP23XC | Non-Standard Ped Ramps - Bronx | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWP23XC | Non-Standard Ped Ramps - Bronx | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWP23XC | Non-Standard Ped Ramps - Bronx | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWP23XC | Non-Standard Ped Ramps - Bronx | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWP23XC | Non-Standard Ped Ramps - Bronx | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWP23XC | Non-Standard Ped Ramps - Bronx | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWP23XC | Non-Standard Ped Ramps - Bronx | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWP23XC | Non-Standard Ped Ramps - Bronx | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWP23XC | Non-Standard Ped Ramps - Bronx | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWP23XC | Non-Standard Ped Ramps - Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ006X | Westchester Square Plaza | 1 | DEVELOP SCOPE | Jun 2025 | Sep 2025 | Jun 2027 | Sep 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ006X | Westchester Square Plaza | 2 | PRELIMINARY DESIGN | Sep 2025 | Jan 2026 | Sep 2027 | Jan 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ006X | Westchester Square Plaza | 3 | FINAL DESIGN | Jan 2026 | Jul 2026 | Jan 2028 | Jul 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ006X | Westchester Square Plaza | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2026 | Oct 2026 | Jul 2028 | Oct 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ006X | Westchester Square Plaza | 5 | CONSTRUCTION TO 25% | Oct 2026 | Feb 2027 | Oct 2028 | Feb 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ006X | Westchester Square Plaza | 6 | CONSTRUCTION TO 50% | Feb 2027 | Jun 2027 | Feb 2029 | Jun 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ006X | Westchester Square Plaza | 7 | CONSTRUCTION TO 75% | Jun 2027 | Oct 2027 | Jun 2029 | Oct 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ006X | Westchester Square Plaza | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jan 2028 | Oct 2029 | Jan 2030
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ006X | Westchester Square Plaza | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Mar 2028 | Jan 2030 | Mar 2030
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ006X | Westchester Square Plaza | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2028 | Apr 2028 | Mar 2030 | Apr 2030
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024X | Prior Notice Sidewalks - Bronx | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2024 | Sep 2024
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024X | Prior Notice Sidewalks - Bronx | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2024 | Jan 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024X | Prior Notice Sidewalks - Bronx | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2025 | Jul 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024X | Prior Notice Sidewalks - Bronx | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2025 | Oct 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024X | Prior Notice Sidewalks - Bronx | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2025 | Feb 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024X | Prior Notice Sidewalks - Bronx | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2026 | Jun 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024X | Prior Notice Sidewalks - Bronx | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2026 | Oct 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024X | Prior Notice Sidewalks - Bronx | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2026 | Jan 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024X | Prior Notice Sidewalks - Bronx | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2027 | Mar 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWS2024X | Prior Notice Sidewalks - Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2027 | Apr 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWSRT200F | Bus Stops Under the EI - Southern Blvd | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2027 | Sep 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWSRT200F | Bus Stops Under the EI - Southern Blvd | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2027 | Jan 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWSRT200F | Bus Stops Under the EI - Southern Blvd | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2028 | Jul 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWSRT200F | Bus Stops Under the EI - Southern Blvd | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2028 | Oct 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWSRT200F | Bus Stops Under the EI - Southern Blvd | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2028 | Feb 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWSRT200F | Bus Stops Under the EI - Southern Blvd | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2029 | Jun 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWSRT200F | Bus Stops Under the EI - Southern Blvd | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2029 | Oct 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWSRT200F | Bus Stops Under the EI - Southern Blvd | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2029 | Jan 2030
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWSRT200F | Bus Stops Under the EI - Southern Blvd | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2030 | Mar 2030
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWSRT200F | Bus Stops Under the EI - Southern Blvd | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2030 | Apr 2030
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX132WF | 132nd Street End Waterfront | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX132WF | 132nd Street End Waterfront | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX132WF | 132nd Street End Waterfront | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2024 | Jul 2024
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX132WF | 132nd Street End Waterfront | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2024 | Oct 2024
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX132WF | 132nd Street End Waterfront | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2024 | Feb 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX132WF | 132nd Street End Waterfront | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2025 | Jun 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX132WF | 132nd Street End Waterfront | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2025 | Oct 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX132WF | 132nd Street End Waterfront | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2025 | Jan 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX132WF | 132nd Street End Waterfront | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2026 | Mar 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX132WF | 132nd Street End Waterfront | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2026 | Apr 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX149WF | 149th Street End Waterfront | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2028 | Sep 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX149WF | 149th Street End Waterfront | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2028 | Jan 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX149WF | 149th Street End Waterfront | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2029 | Jul 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX149WF | 149th Street End Waterfront | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2029 | Oct 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX149WF | 149th Street End Waterfront | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2029 | Feb 2030
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX149WF | 149th Street End Waterfront | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2030 | Jun 2030
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX149WF | 149th Street End Waterfront | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2030 | Oct 2030
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX149WF | 149th Street End Waterfront | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2030 | Jan 2031
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX149WF | 149th Street End Waterfront | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2031 | Mar 2031
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX149WF | 149th Street End Waterfront | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2031 | Apr 2031
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX407 | Mott Haven Pedestrian and Cyclist Safety Improvements | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2024 | Sep 2024
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX407 | Mott Haven Pedestrian and Cyclist Safety Improvements | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2024 | Jan 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX407 | Mott Haven Pedestrian and Cyclist Safety Improvements | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2025 | Jul 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX407 | Mott Haven Pedestrian and Cyclist Safety Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2025 | Oct 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX407 | Mott Haven Pedestrian and Cyclist Safety Improvements | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2025 | Feb 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX407 | Mott Haven Pedestrian and Cyclist Safety Improvements | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2026 | Jun 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX407 | Mott Haven Pedestrian and Cyclist Safety Improvements | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2026 | Oct 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX407 | Mott Haven Pedestrian and Cyclist Safety Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2026 | Jan 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX407 | Mott Haven Pedestrian and Cyclist Safety Improvements | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2027 | Mar 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX407 | Mott Haven Pedestrian and Cyclist Safety Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2027 | Apr 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX409 | Willis Ave Bikeway Improvements | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX409 | Willis Ave Bikeway Improvements | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX409 | Willis Ave Bikeway Improvements | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX409 | Willis Ave Bikeway Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX409 | Willis Ave Bikeway Improvements | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX409 | Willis Ave Bikeway Improvements | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX409 | Willis Ave Bikeway Improvements | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX409 | Willis Ave Bikeway Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX409 | Willis Ave Bikeway Improvements | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX409 | Willis Ave Bikeway Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX410 | Harding Park Area Reconstruction | 1 | DEVELOP SCOPE | Jun 2027 | Sep 2027 | Jun 2027 | Sep 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX410 | Harding Park Area Reconstruction | 2 | PRELIMINARY DESIGN | Sep 2027 | Jan 2028 | Sep 2027 | Jan 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX410 | Harding Park Area Reconstruction | 3 | FINAL DESIGN | Jan 2028 | Jul 2028 | Jan 2028 | Jul 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX410 | Harding Park Area Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2028 | Oct 2028 | Jul 2028 | Oct 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX410 | Harding Park Area Reconstruction | 5 | CONSTRUCTION TO 25% | Oct 2028 | Feb 2029 | Oct 2028 | Feb 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX410 | Harding Park Area Reconstruction | 6 | CONSTRUCTION TO 50% | Feb 2029 | Jun 2029 | Feb 2029 | Jun 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX410 | Harding Park Area Reconstruction | 7 | CONSTRUCTION TO 75% | Jun 2029 | Oct 2029 | Jun 2029 | Oct 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX410 | Harding Park Area Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2029 | Jan 2030 | Oct 2029 | Jan 2030
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX410 | Harding Park Area Reconstruction | 9 | SUBSTANTIAL COMPLETION | Jan 2030 | Mar 2030 | Jan 2030 | Mar 2030
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX410 | Harding Park Area Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2030 | Apr 2030 | Mar 2030 | Apr 2030
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX413 | Hunts Point Avenue | 1 | DEVELOP SCOPE | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX413 | Hunts Point Avenue | 2 | PRELIMINARY DESIGN | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX413 | Hunts Point Avenue | 3 | FINAL DESIGN | Jan 2026 | Jul 2026 | Jan 2026 | Jul 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX413 | Hunts Point Avenue | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2026 | Oct 2026 | Jul 2026 | Oct 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX413 | Hunts Point Avenue | 5 | CONSTRUCTION TO 25% | Oct 2026 | Feb 2027 | Oct 2026 | Feb 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX413 | Hunts Point Avenue | 6 | CONSTRUCTION TO 50% | Feb 2027 | Jun 2027 | Feb 2027 | Jun 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX413 | Hunts Point Avenue | 7 | CONSTRUCTION TO 75% | Jun 2027 | Oct 2027 | Jun 2027 | Oct 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX413 | Hunts Point Avenue | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jan 2028 | Oct 2027 | Jan 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX413 | Hunts Point Avenue | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Mar 2028 | Jan 2028 | Mar 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX413 | Hunts Point Avenue | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2028 | Apr 2028 | Mar 2028 | Apr 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX414 | Lower Grand Concourse Reconstruction | 1 | DEVELOP SCOPE | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX414 | Lower Grand Concourse Reconstruction | 2 | PRELIMINARY DESIGN | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX414 | Lower Grand Concourse Reconstruction | 3 | FINAL DESIGN | Jan 2026 | Jul 2026 | Jan 2026 | Jul 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX414 | Lower Grand Concourse Reconstruction | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2026 | Oct 2026 | Jul 2026 | Oct 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX414 | Lower Grand Concourse Reconstruction | 5 | CONSTRUCTION TO 25% | Oct 2026 | Feb 2027 | Oct 2026 | Feb 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX414 | Lower Grand Concourse Reconstruction | 6 | CONSTRUCTION TO 50% | Feb 2027 | Jun 2027 | Feb 2027 | Jun 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX414 | Lower Grand Concourse Reconstruction | 7 | CONSTRUCTION TO 75% | Jun 2027 | Oct 2027 | Jun 2027 | Oct 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX414 | Lower Grand Concourse Reconstruction | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jan 2028 | Oct 2027 | Jan 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX414 | Lower Grand Concourse Reconstruction | 9 | SUBSTANTIAL COMPLETION | Jan 2028 | Mar 2028 | Jan 2028 | Mar 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX414 | Lower Grand Concourse Reconstruction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2028 | Apr 2028 | Mar 2028 | Apr 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX415 | North Bronx Multi-Site Safety | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2025 | Sep 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX415 | North Bronx Multi-Site Safety | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2025 | Jan 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX415 | North Bronx Multi-Site Safety | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2026 | Jul 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX415 | North Bronx Multi-Site Safety | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2026 | Oct 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX415 | North Bronx Multi-Site Safety | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2026 | Feb 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX415 | North Bronx Multi-Site Safety | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2027 | Jun 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX415 | North Bronx Multi-Site Safety | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2027 | Oct 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX415 | North Bronx Multi-Site Safety | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2027 | Jan 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX415 | North Bronx Multi-Site Safety | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2028 | Mar 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX415 | North Bronx Multi-Site Safety | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2028 | Apr 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX416 | Southern Blvd Area Multi-Site | 1 | DEVELOP SCOPE | Jun 2023 | Sep 2023 | Jun 2027 | Sep 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX416 | Southern Blvd Area Multi-Site | 2 | PRELIMINARY DESIGN | Sep 2023 | Jan 2024 | Sep 2027 | Jan 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX416 | Southern Blvd Area Multi-Site | 3 | FINAL DESIGN | Jan 2024 | Jul 2024 | Jan 2028 | Jul 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX416 | Southern Blvd Area Multi-Site | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Oct 2024 | Jul 2028 | Oct 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX416 | Southern Blvd Area Multi-Site | 5 | CONSTRUCTION TO 25% | Oct 2024 | Feb 2025 | Oct 2028 | Feb 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX416 | Southern Blvd Area Multi-Site | 6 | CONSTRUCTION TO 50% | Feb 2025 | Jun 2025 | Feb 2029 | Jun 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX416 | Southern Blvd Area Multi-Site | 7 | CONSTRUCTION TO 75% | Jun 2025 | Oct 2025 | Jun 2029 | Oct 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX416 | Southern Blvd Area Multi-Site | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2025 | Jan 2026 | Oct 2029 | Jan 2030
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX416 | Southern Blvd Area Multi-Site | 9 | SUBSTANTIAL COMPLETION | Jan 2026 | Mar 2026 | Jan 2030 | Mar 2030
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX416 | Southern Blvd Area Multi-Site | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Apr 2026 | Mar 2030 | Apr 2030
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX711 | Bronx River Greenway @ 233rd St | 1 | DEVELOP SCOPE | Jul 2016 | Sep 2016 | Jul 2027 | Sep 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX711 | Bronx River Greenway @ 233rd St | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Sep 2027 | Jan 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX711 | Bronx River Greenway @ 233rd St | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Jan 2028 | Jul 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX711 | Bronx River Greenway @ 233rd St | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Jul 2028 | Oct 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX711 | Bronx River Greenway @ 233rd St | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Oct 2028 | Feb 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX711 | Bronx River Greenway @ 233rd St | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Feb 2029 | Jun 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX711 | Bronx River Greenway @ 233rd St | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Jun 2029 | Oct 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX711 | Bronx River Greenway @ 233rd St | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | Oct 2029 | Jan 2030
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX711 | Bronx River Greenway @ 233rd St | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Jan 2030 | Mar 2030
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX711 | Bronx River Greenway @ 233rd St | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Mar 2030 | Apr 2030
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXBSAVWF | Bay Shore Avenue Waterfront - Eastchester Bay | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXBSAVWF | Bay Shore Avenue Waterfront - Eastchester Bay | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXBSAVWF | Bay Shore Avenue Waterfront - Eastchester Bay | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXBSAVWF | Bay Shore Avenue Waterfront - Eastchester Bay | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXBSAVWF | Bay Shore Avenue Waterfront - Eastchester Bay | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXBSAVWF | Bay Shore Avenue Waterfront - Eastchester Bay | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXBSAVWF | Bay Shore Avenue Waterfront - Eastchester Bay | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXBSAVWF | Bay Shore Avenue Waterfront - Eastchester Bay | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXBSAVWF | Bay Shore Avenue Waterfront - Eastchester Bay | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXBSAVWF | Bay Shore Avenue Waterfront - Eastchester Bay | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXFSCWF | Safety City Waterfront Structures | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXFSCWF | Safety City Waterfront Structures | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXFSCWF | Safety City Waterfront Structures | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXFSCWF | Safety City Waterfront Structures | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2023 | Oct 2023
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXFSCWF | Safety City Waterfront Structures | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXFSCWF | Safety City Waterfront Structures | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXFSCWF | Safety City Waterfront Structures | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2024 | Oct 2024
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXFSCWF | Safety City Waterfront Structures | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2024 | Jan 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXFSCWF | Safety City Waterfront Structures | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2025 | Mar 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXFSCWF | Safety City Waterfront Structures | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2025 | Apr 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXHUTCH | Hutchinson River Parkway Access Road | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2026 | Sep 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXHUTCH | Hutchinson River Parkway Access Road | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2026 | Jan 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXHUTCH | Hutchinson River Parkway Access Road | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2027 | Jul 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXHUTCH | Hutchinson River Parkway Access Road | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2027 | Oct 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXHUTCH | Hutchinson River Parkway Access Road | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2027 | Feb 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXHUTCH | Hutchinson River Parkway Access Road | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2028 | Jun 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXHUTCH | Hutchinson River Parkway Access Road | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2028 | Oct 2028
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXHUTCH | Hutchinson River Parkway Access Road | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2028 | Jan 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXHUTCH | Hutchinson River Parkway Access Road | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2029 | Mar 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXHUTCH | Hutchinson River Parkway Access Road | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2029 | Apr 2030
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXS1011 | Reconstruction of the E 169th Street Step Street | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2024 | Sep 2024
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXS1011 | Reconstruction of the E 169th Street Step Street | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2024 | Jan 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXS1011 | Reconstruction of the E 169th Street Step Street | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2025 | Jul 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXS1011 | Reconstruction of the E 169th Street Step Street | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2025 | Oct 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXS1011 | Reconstruction of the E 169th Street Step Street | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2025 | Feb 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXS1011 | Reconstruction of the E 169th Street Step Street | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2026 | Jun 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXS1011 | Reconstruction of the E 169th Street Step Street | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2026 | Oct 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXS1011 | Reconstruction of the E 169th Street Step Street | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2026 | Jan 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXS1011 | Reconstruction of the E 169th Street Step Street | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2027 | Mar 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXS1011 | Reconstruction of the E 169th Street Step Street | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2027 | Apr 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | RWX023 | Concourse Village West | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2024 | Sep 2024
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | RWX023 | Concourse Village West | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2024 | Jan 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | RWX023 | Concourse Village West | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2025 | Jul 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | RWX023 | Concourse Village West | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2025 | Oct 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | RWX023 | Concourse Village West | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2025 | Feb 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | RWX023 | Concourse Village West | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2026 | Jun 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | RWX023 | Concourse Village West | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2026 | Oct 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | RWX023 | Concourse Village West | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2026 | Jan 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | RWX023 | Concourse Village West | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2027 | Mar 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | RWX023 | Concourse Village West | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2027 | Apr 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TF18-JGH | JEROME GUN HILL MUNICIPAL PARKING GARAGE, BRONX | 1 | PROJECT START | Mar 2006 | Mar 2006 | Mar 2021 | Mar 2021
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TF18-JGH | JEROME GUN HILL MUNICIPAL PARKING GARAGE, BRONX | 2 | DESIGN START | Mar 2006 | Oct 2006 | Mar 2021 | Oct 2021
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TF18-JGH | JEROME GUN HILL MUNICIPAL PARKING GARAGE, BRONX | 3 | DESIGN COMPLETION | Oct 2006 | Jul 2007 | Oct 2021 | Jul 2022
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TF18-JGH | JEROME GUN HILL MUNICIPAL PARKING GARAGE, BRONX | 4 | CONSTRUCTION START | Jul 2007 | Jan 2008 | Jul 2022 | Jan 2023
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TF18-JGH | JEROME GUN HILL MUNICIPAL PARKING GARAGE, BRONX | 5 | CONSTRUCTION COMPLETION | Jan 2008 | May 2009 | Jan 2023 | May 2024
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TF18-JGH | JEROME GUN HILL MUNICIPAL PARKING GARAGE, BRONX | 6 | DEVELOP SCOPE | Jan 2008 | May 2009 | May 2024 | Aug 2024
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TF18-JGH | JEROME GUN HILL MUNICIPAL PARKING GARAGE, BRONX | 7 | PRELIMINARY DESIGN | Jan 2008 | May 2009 | Aug 2024 | Dec 2024
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TF18-JGH | JEROME GUN HILL MUNICIPAL PARKING GARAGE, BRONX | 8 | FINAL DESIGN | Jan 2008 | May 2009 | Dec 2024 | May 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TF18-JGH | JEROME GUN HILL MUNICIPAL PARKING GARAGE, BRONX | 9 | BID AWARD AND REGISTER CONTRCT | Jan 2008 | May 2009 | Jun 2025 | Aug 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TF18-JGH | JEROME GUN HILL MUNICIPAL PARKING GARAGE, BRONX | 10 | CONSTRUCTION TO 25% | Jan 2008 | May 2009 | Aug 2025 | Dec 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TF18-JGH | JEROME GUN HILL MUNICIPAL PARKING GARAGE, BRONX | 11 | CONSTRUCTION TO 50% | Jan 2008 | May 2009 | Dec 2025 | Apr 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TF18-JGH | JEROME GUN HILL MUNICIPAL PARKING GARAGE, BRONX | 12 | CONSTRUCTION TO 75% | Jan 2008 | May 2009 | Apr 2026 | Aug 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TF18-JGH | JEROME GUN HILL MUNICIPAL PARKING GARAGE, BRONX | 13 | ORIGINAL EQUIP & FURNISHING | Jan 2008 | May 2009 | Aug 2026 | Nov 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TF18-JGH | JEROME GUN HILL MUNICIPAL PARKING GARAGE, BRONX | 14 | SUBSTANTIAL COMPLETION | Jan 2008 | May 2009 | Nov 2026 | Jan 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TF18-JGH | JEROME GUN HILL MUNICIPAL PARKING GARAGE, BRONX | 15 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2008 | May 2009 | Jan 2027 | Feb 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TFD503X21 | CLAY AV.HISTORIC DISTRICT OLD-STYLE ST LAMP BET. E165& 167TH | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2011 | Jun 2011 | Jun 2026 | Jul 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TFD503X21 | CLAY AV.HISTORIC DISTRICT OLD-STYLE ST LAMP BET. E165& 167TH | 2 | CONSTRUCTION START | Jul 2011 | Aug 2011 | Jul 2027 | Aug 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TFD503X21 | CLAY AV.HISTORIC DISTRICT OLD-STYLE ST LAMP BET. E165& 167TH | 3 | CONSTRUCTION COMPLETION | Aug 2011 | Mar 2013 | Aug 2028 | Mar 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TFX50301 | GRAND CONCOURSE DECORATIVE STREET LIGHTING | 1 | BID AWARD AND REGISTER CONTRCT | Jun 2006 | Jun 2006 | Jun 2026 | Jun 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TFX50301 | GRAND CONCOURSE DECORATIVE STREET LIGHTING | 2 | CONSTRUCTION START | Jun 2006 | Jul 2006 | Jun 2026 | Jul 2026
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TFX50301 | GRAND CONCOURSE DECORATIVE STREET LIGHTING | 3 | CONSTRUCTION COMPLETION | Jul 2006 | Feb 2008 | Jul 2026 | Feb 2029
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TRANSBCTY | Reconstruction Transfer Bridge Structure at City Island | 1 | DEVELOP SCOPE | Jun 2019 | Jun 2020 | Jun 2024 | Jun 2025
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TRANSBCTY | Reconstruction Transfer Bridge Structure at City Island | 2 | DESIGN START | Jun 2020 | Jun 2022 | Jun 2025 | Jun 2027
20231026 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TRANSBCTY | Reconstruction Transfer Bridge Structure at City Island | 3 | CONSTRUCTION START | Jun 2022 | Jun 2024 | Jun 2027 | Jun 2029
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | GXBXGI-02 | Bronx Green Inrastructure | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | GXBXGI-02 | Bronx Green Inrastructure | 2 | DESIGN | Dec 2021 | Dec 2023 | Dec 2021 | Dec 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | GXBXGI-02 | Bronx Green Inrastructure | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | GXBXGI-02 | Bronx Green Inrastructure | 4 | CONSTRUCTION | Sep 2024 | Sep 2027 | Sep 2024 | Sep 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | GXBXGI-02 | Bronx Green Inrastructure | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Sep 2029 | Sep 2027 | Sep 2029
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | GXBXGI-03 | GI- Van Cortlandt Park | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | GXBXGI-03 | GI- Van Cortlandt Park | 2 | DESIGN | Dec 2021 | Dec 2023 | Dec 2021 | Dec 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | GXBXGI-03 | GI- Van Cortlandt Park | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | GXBXGI-03 | GI- Van Cortlandt Park | 4 | CONSTRUCTION | Sep 2024 | Sep 2027 | Sep 2024 | Sep 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | GXBXGI-03 | GI- Van Cortlandt Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Sep 2029 | Sep 2027 | Sep 2029
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | HIF-1FSPB | Franz Sigel Park Ballfields-Install BallField Lighting | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | HIF-1FSPB | Franz Sigel Park Ballfields-Install BallField Lighting | 2 | DESIGN | Dec 2018 | Mar 2020 | Dec 2018 | Mar 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | HIF-1FSPB | Franz Sigel Park Ballfields-Install BallField Lighting | 3 | BID/ REGISTER CONTRACT | Mar 2020 | Dec 2020 | Mar 2020 | Dec 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | HIF-1FSPB | Franz Sigel Park Ballfields-Install BallField Lighting | 4 | CONSTRUCTION | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | HIF-1FSPB | Franz Sigel Park Ballfields-Install BallField Lighting | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | HPF-BPPK | HPF - Barretto Point Park | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | HPF-BPPK | HPF - Barretto Point Park | 2 | DESIGN | Dec 2022 | Dec 2024 | Dec 2022 | Dec 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | HPF-BPPK | HPF - Barretto Point Park | 3 | BID/ REGISTER CONTRACT | Dec 2024 | Sep 2025 | Dec 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | HPF-BPPK | HPF - Barretto Point Park | 4 | CONSTRUCTION | Sep 2025 | Sep 2028 | Sep 2025 | Sep 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | HPF-BPPK | HPF - Barretto Point Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2028 | Sep 2030 | Sep 2028 | Sep 2030
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | IDA21-02 | St. James Rec Ctr - RC HVAC Emer. | 1 | DEVELOP SCOPE | Jan 2023 | Jun 2023 | Sep 2020 | Mar 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | IDA21-02 | St. James Rec Ctr - RC HVAC Emer. | 2 | DESIGN | Jun 2023 | Jun 2024 | Mar 2021 | Mar 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | IDA21-02 | St. James Rec Ctr - RC HVAC Emer. | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Mar 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | IDA21-02 | St. James Rec Ctr - RC HVAC Emer. | 4 | CONSTRUCTION | Mar 2025 | Mar 2026 | Dec 2022 | Dec 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | IDA21-02 | St. James Rec Ctr - RC HVAC Emer. | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Mar 2027 | Dec 2023 | Jun 2029
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-BRPLG | NDF-Bridge Playground- X148A3-318M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-BRPLG | NDF-Bridge Playground- X148A3-318M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-BRPLG | NDF-Bridge Playground- X148A3-318M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-BRPLG | NDF-Bridge Playground- X148A3-318M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-BRPLG | NDF-Bridge Playground- X148A3-318M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-CPFSP | NDF-CORPORAL FISCHER PLAYGROUND X269-119M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-CPFSP | NDF-CORPORAL FISCHER PLAYGROUND X269-119M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Feb 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-CPFSP | NDF-CORPORAL FISCHER PLAYGROUND X269-119M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Feb 2020 | Nov 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-CPFSP | NDF-CORPORAL FISCHER PLAYGROUND X269-119M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Nov 2020 | Nov 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-CPFSP | NDF-CORPORAL FISCHER PLAYGROUND X269-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Nov 2021 | Nov 2031
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-DVDSO | Neighborhood Dev. Fund-1801 Davidson X367-120M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-DVDSO | Neighborhood Dev. Fund-1801 Davidson X367-120M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-DVDSO | Neighborhood Dev. Fund-1801 Davidson X367-120M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-DVDSO | Neighborhood Dev. Fund-1801 Davidson X367-120M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-DVDSO | Neighborhood Dev. Fund-1801 Davidson X367-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2031
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-GRANT | NDF-Grant Park X271-119M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-GRANT | NDF-Grant Park X271-119M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-GRANT | NDF-Grant Park X271-119M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-GRANT | NDF-Grant Park X271-119M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-GRANT | NDF-Grant Park X271-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2033
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-JROME | NDF- Jerome Trees XG-122M | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-JROME | NDF- Jerome Trees XG-122M | 2 | DESIGN | Dec 2021 | Jun 2022 | Dec 2021 | Jun 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-JROME | NDF- Jerome Trees XG-122M | 3 | BID/ REGISTER CONTRACT | Jun 2022 | Mar 2023 | Jun 2022 | Mar 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-JROME | NDF- Jerome Trees XG-122M | 4 | CONSTRUCTION | Mar 2023 | Sep 2024 | Mar 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-JROME | NDF- Jerome Trees XG-122M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2026 | Sep 2024 | Sep 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-MORTN | NDF-MORTON PLAYGROUND RECONSTRUCTION (X001A) | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-MORTN | NDF-MORTON PLAYGROUND RECONSTRUCTION (X001A) | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-MORTN | NDF-MORTON PLAYGROUND RECONSTRUCTION (X001A) | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-MORTN | NDF-MORTON PLAYGROUND RECONSTRUCTION (X001A) | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-MORTN | NDF-MORTON PLAYGROUND RECONSTRUCTION (X001A) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2031
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-SOAQK | NDF-Aqueduct Walk X001A-121M | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-SOAQK | NDF-Aqueduct Walk X001A-121M | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-SOAQK | NDF-Aqueduct Walk X001A-121M | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-SOAQK | NDF-Aqueduct Walk X001A-121M | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-SOAQK | NDF-Aqueduct Walk X001A-121M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2033
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-100CDAR | Cedar Playground - RC PRB X111-114M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Nov 2014
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-100CDAR | Cedar Playground - RC PRB X111-114M | 2 | DESIGN | Sep 2013 | Dec 2013 | Nov 2014 | Aug 2016
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-100CDAR | Cedar Playground - RC PRB X111-114M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Aug 2016 | Nov 2016
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-100CDAR | Cedar Playground - RC PRB X111-114M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Nov 2016 | Nov 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-100CDAR | Cedar Playground - RC PRB X111-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Nov 2017 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101BPAR | Brook Park - sitting area & public restroom X246-120M | 1 | DEVELOP SCOPE | Jul 2006 | Sep 2006 | Jul 2006 | Jan 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101BPAR | Brook Park - sitting area & public restroom X246-120M | 2 | DESIGN | Sep 2006 | Dec 2006 | Jan 2021 | Apr 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101BPAR | Brook Park - sitting area & public restroom X246-120M | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Apr 2021 | Jul 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101BPAR | Brook Park - sitting area & public restroom X246-120M | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Jul 2021 | Jul 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101BPAR | Brook Park - sitting area & public restroom X246-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Jul 2022 | Jul 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101CGDN | CENTRO CULTURAL RINCON CRIOLLO COMM GARDEN WATER INSTALL | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101CGDN | CENTRO CULTURAL RINCON CRIOLLO COMM GARDEN WATER INSTALL | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101CGDN | CENTRO CULTURAL RINCON CRIOLLO COMM GARDEN WATER INSTALL | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101CGDN | CENTRO CULTURAL RINCON CRIOLLO COMM GARDEN WATER INSTALL | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101CGDN | CENTRO CULTURAL RINCON CRIOLLO COMM GARDEN WATER INSTALL | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101LZDA | Lozada Park Renovation- New play equip.,spray shower, swings | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2024 | Dec 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101LZDA | Lozada Park Renovation- New play equip.,spray shower, swings | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2024 | Dec 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101LZDA | Lozada Park Renovation- New play equip.,spray shower, swings | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2025 | Sep 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101LZDA | Lozada Park Renovation- New play equip.,spray shower, swings | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2026 | Sep 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101LZDA | Lozada Park Renovation- New play equip.,spray shower, swings | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2027 | Sep 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101MAR2 | St. Mary's Plgd West - ADA PRB X045-118M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101MAR2 | St. Mary's Plgd West - ADA PRB X045-118M | 2 | DESIGN | Dec 2016 | Dec 2018 | Jan 2017 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101MAR2 | St. Mary's Plgd West - ADA PRB X045-118M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Jan 2019 | Sep 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101MAR2 | St. Mary's Plgd West - ADA PRB X045-118M | 4 | CONSTRUCTION | Sep 2019 | Sep 2022 | Sep 2019 | Sep 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101MAR2 | St. Mary's Plgd West - ADA PRB X045-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2024 | Sep 2022 | Jul 2030
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101STMH | ST. MARY'S PK REC CTR HVAC X045-116M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101STMH | ST. MARY'S PK REC CTR HVAC X045-116M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101STMH | ST. MARY'S PK REC CTR HVAC X045-116M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101STMH | ST. MARY'S PK REC CTR HVAC X045-116M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101STMH | ST. MARY'S PK REC CTR HVAC X045-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Jun 2030
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101WLSP | Willis Plgd Recon - X217-118M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101WLSP | Willis Plgd Recon - X217-118M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101WLSP | Willis Plgd Recon - X217-118M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101WLSP | Willis Plgd Recon - X217-118M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101WLSP | Willis Plgd Recon - X217-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102BRPP | Bill Rainey Park--Lights For Baseball Field & Score Board | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102BRPP | Bill Rainey Park--Lights For Baseball Field & Score Board | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102BRPP | Bill Rainey Park--Lights For Baseball Field & Score Board | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102BRPP | Bill Rainey Park--Lights For Baseball Field & Score Board | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102BRPP | Bill Rainey Park--Lights For Baseball Field & Score Board | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102HNT2 | Hunts Point - Riverside Park - Dock Repair X336-119M | 1 | DEVELOP SCOPE | Jul 2010 | Sep 2010 | Jul 2010 | Sep 2010
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102HNT2 | Hunts Point - Riverside Park - Dock Repair X336-119M | 2 | DESIGN | Sep 2010 | Dec 2010 | Sep 2010 | Dec 2010
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102HNT2 | Hunts Point - Riverside Park - Dock Repair X336-119M | 3 | BID/ REGISTER CONTRACT | Dec 2010 | Mar 2011 | Dec 2010 | Mar 2011
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102HNT2 | Hunts Point - Riverside Park - Dock Repair X336-119M | 4 | CONSTRUCTION | Mar 2011 | Mar 2012 | Mar 2011 | Mar 2012
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102HNT2 | Hunts Point - Riverside Park - Dock Repair X336-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2012 | Mar 2013 | Mar 2012 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102HPRC | HUNTS POINT REC CTR INDOOR TRACK AND MECHANICAL LIFT RECONST | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102HPRC | HUNTS POINT REC CTR INDOOR TRACK AND MECHANICAL LIFT RECONST | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102HPRC | HUNTS POINT REC CTR INDOOR TRACK AND MECHANICAL LIFT RECONST | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102HPRC | HUNTS POINT REC CTR INDOOR TRACK AND MECHANICAL LIFT RECONST | 4 | CONSTRUCTION | Nov 2025 | May 2027 | Nov 2025 | May 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102HPRC | HUNTS POINT REC CTR INDOOR TRACK AND MECHANICAL LIFT RECONST | 5 | PUNCHLIST COMPLETE, JOB CLOSED | May 2027 | May 2028 | May 2027 | May 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102JCAP | JULIO CARBALLO FIELDS PLAYGROUND | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102JCAP | JULIO CARBALLO FIELDS PLAYGROUND | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102JCAP | JULIO CARBALLO FIELDS PLAYGROUND | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102JCAP | JULIO CARBALLO FIELDS PLAYGROUND | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102JCAP | JULIO CARBALLO FIELDS PLAYGROUND | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102MNDA | Manida Park-Lighting & Scoreboard Renovation | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102MNDA | Manida Park-Lighting & Scoreboard Renovation | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102MNDA | Manida Park-Lighting & Scoreboard Renovation | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102MNDA | Manida Park-Lighting & Scoreboard Renovation | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102MNDA | Manida Park-Lighting & Scoreboard Renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102PL52 | CPI PH1 - Playground 52 - Reconstruct Kelly Plgd X179-112M | 1 | DEVELOP SCOPE | Jul 2010 | Sep 2010 | Jul 2010 | Jun 2011
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102PL52 | CPI PH1 - Playground 52 - Reconstruct Kelly Plgd X179-112M | 2 | DESIGN | Sep 2010 | Dec 2010 | Jun 2011 | Dec 2015
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102PL52 | CPI PH1 - Playground 52 - Reconstruct Kelly Plgd X179-112M | 3 | BID/ REGISTER CONTRACT | Dec 2010 | Mar 2011 | Feb 2015 | Apr 2016
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102PL52 | CPI PH1 - Playground 52 - Reconstruct Kelly Plgd X179-112M | 4 | CONSTRUCTION | Mar 2011 | Mar 2012 | May 2016 | Jul 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102PL52 | CPI PH1 - Playground 52 - Reconstruct Kelly Plgd X179-112M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2012 | Mar 2013 | Jul 2018 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102TOWD | Concrete Plant Park - emergency tower demolition | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102TOWD | Concrete Plant Park - emergency tower demolition | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102TOWD | Concrete Plant Park - emergency tower demolition | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102TOWD | Concrete Plant Park - emergency tower demolition | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102TOWD | Concrete Plant Park - emergency tower demolition | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102WWGT | NYC GreenThumb -Wishing Well Community Garden Water System - | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102WWGT | NYC GreenThumb -Wishing Well Community Garden Water System - | 2 | DESIGN | Dec 2022 | Jun 2024 | Dec 2022 | Jun 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102WWGT | NYC GreenThumb -Wishing Well Community Garden Water System - | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102WWGT | NYC GreenThumb -Wishing Well Community Garden Water System - | 4 | CONSTRUCTION | Mar 2025 | Sep 2026 | Mar 2025 | Sep 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102WWGT | NYC GreenThumb -Wishing Well Community Garden Water System - | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Sep 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CGJF | CS-134-Fence and Water Supply- (X340-116MA) | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Mar 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CGJF | CS-134-Fence and Water Supply- (X340-116MA) | 2 | DESIGN | Sep 2013 | Dec 2013 | Mar 2017 | Nov 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CGJF | CS-134-Fence and Water Supply- (X340-116MA) | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Nov 2018 | Mar 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CGJF | CS-134-Fence and Water Supply- (X340-116MA) | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Apr 2019 | Apr 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CGJF | CS-134-Fence and Water Supply- (X340-116MA) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Apr 2020 | Apr 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPB5 | Crotona Park - ballfield #5 - X010-115M | 1 | DEVELOP SCOPE | Jul 2012 | Sep 2012 | Jul 2012 | Apr 2016
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPB5 | Crotona Park - ballfield #5 - X010-115M | 2 | DESIGN | Sep 2012 | Dec 2012 | Apr 2016 | Jun 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPB5 | Crotona Park - ballfield #5 - X010-115M | 3 | BID/ REGISTER CONTRACT | Dec 2012 | Mar 2013 | Feb 2018 | Jun 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPB5 | Crotona Park - ballfield #5 - X010-115M | 4 | CONSTRUCTION | Mar 2013 | Mar 2014 | Aug 2018 | Aug 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPB5 | Crotona Park - ballfield #5 - X010-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2014 | Mar 2015 | Aug 2019 | Aug 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPBT | TREE RESTITUTION REQ FOR CROTONA PARK | 1 | DEVELOP SCOPE | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPBT | TREE RESTITUTION REQ FOR CROTONA PARK | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPBT | TREE RESTITUTION REQ FOR CROTONA PARK | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPBT | TREE RESTITUTION REQ FOR CROTONA PARK | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPBT | TREE RESTITUTION REQ FOR CROTONA PARK | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPEW | CROTONA PARK GREENWAY - X010-105M | 1 | DEVELOP SCOPE | Jul 2004 | Sep 2004 | Jul 2004 | Aug 2004
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPEW | CROTONA PARK GREENWAY - X010-105M | 2 | DESIGN | Sep 2004 | Dec 2004 | Aug 2004 | Sep 2004
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPEW | CROTONA PARK GREENWAY - X010-105M | 3 | BID/ REGISTER CONTRACT | Dec 2004 | Mar 2005 | Sep 2004 | Dec 2004
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPEW | CROTONA PARK GREENWAY - X010-105M | 4 | CONSTRUCTION | Mar 2005 | Mar 2006 | Dec 2004 | May 2006
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPEW | CROTONA PARK GREENWAY - X010-105M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2006 | Mar 2007 | Jan 2007 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103DBPR | Daniel Boone Playground Public Restroom Construction | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103DBPR | Daniel Boone Playground Public Restroom Construction | 2 | DESIGN | Feb 2024 | Feb 2026 | Feb 2024 | Feb 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103DBPR | Daniel Boone Playground Public Restroom Construction | 3 | BID/ REGISTER CONTRACT | Feb 2026 | Nov 2026 | Feb 2026 | Nov 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103DBPR | Daniel Boone Playground Public Restroom Construction | 4 | CONSTRUCTION | Nov 2026 | Nov 2028 | Nov 2026 | Nov 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103DBPR | Daniel Boone Playground Public Restroom Construction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2028 | Nov 2029 | Nov 2028 | Nov 2029
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103DPLS | Drew Playground Security Lighting X021-119M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103DPLS | Drew Playground Security Lighting X021-119M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103DPLS | Drew Playground Security Lighting X021-119M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103DPLS | Drew Playground Security Lighting X021-119M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103DPLS | Drew Playground Security Lighting X021-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2030
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103RBGT | NYC GreenThumb - Rainbow Garden of Life & Health Water Syste | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103RBGT | NYC GreenThumb - Rainbow Garden of Life & Health Water Syste | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103RBGT | NYC GreenThumb - Rainbow Garden of Life & Health Water Syste | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103RBGT | NYC GreenThumb - Rainbow Garden of Life & Health Water Syste | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103RBGT | NYC GreenThumb - Rainbow Garden of Life & Health Water Syste | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103WPBC | Waring Plgd Basketball Courts Recon (X002-118M) | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Oct 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103WPBC | Waring Plgd Basketball Courts Recon (X002-118M) | 2 | DESIGN | Sep 2015 | Dec 2015 | Oct 2017 | Dec 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103WPBC | Waring Plgd Basketball Courts Recon (X002-118M) | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Apr 2019 | Oct 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103WPBC | Waring Plgd Basketball Courts Recon (X002-118M) | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Dec 2019 | Nov 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103WPBC | Waring Plgd Basketball Courts Recon (X002-118M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Nov 2020 | Jun 2030
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104BCMR | Bronx Children's Museum Roof Reconstruction | 1 | DEVELOP SCOPE | Apr 2023 | Sep 2023 | Apr 2023 | Sep 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104BCMR | Bronx Children's Museum Roof Reconstruction | 2 | DESIGN | Sep 2023 | Sep 2025 | Sep 2023 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104BCMR | Bronx Children's Museum Roof Reconstruction | 3 | BID/ REGISTER CONTRACT | Sep 2025 | Jun 2026 | Sep 2025 | Jun 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104BCMR | Bronx Children's Museum Roof Reconstruction | 4 | CONSTRUCTION | Jun 2026 | Jun 2028 | Jun 2026 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104BCMR | Bronx Children's Museum Roof Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2028 | Jun 2030 | Jun 2028 | Jun 2030
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104FIS2 | Cons of Fish Passage Twin Dams | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104FIS2 | Cons of Fish Passage Twin Dams | 2 | DESIGN | Dec 2018 | Jun 2020 | Dec 2018 | Jun 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104FIS2 | Cons of Fish Passage Twin Dams | 3 | BID/ REGISTER CONTRACT | Jun 2020 | Mar 2021 | Jun 2020 | Mar 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104FIS2 | Cons of Fish Passage Twin Dams | 4 | CONSTRUCTION | Mar 2021 | Mar 2023 | Mar 2021 | Mar 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104FIS2 | Cons of Fish Passage Twin Dams | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Mar 2025 | Mar 2023 | Mar 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104GBLE | Goble Playground- new BBall equip., swings, handball court | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Mar 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104GBLE | Goble Playground- new BBall equip., swings, handball court | 2 | DESIGN | Dec 2018 | Dec 2019 | Apr 2021 | Mar 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104GBLE | Goble Playground- new BBall equip., swings, handball court | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Apr 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104GBLE | Goble Playground- new BBall equip., swings, handball court | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Dec 2022 | Dec 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104GBLE | Goble Playground- new BBall equip., swings, handball court | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Dec 2023 | Dec 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104HGBG | Highbridge Park - step streets/park ldscape X120-110M | 1 | DEVELOP SCOPE | Jul 2007 | Sep 2007 | Jul 2007 | Aug 2011
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104HGBG | Highbridge Park - step streets/park ldscape X120-110M | 2 | DESIGN | Sep 2007 | Dec 2007 | Aug 2011 | Aug 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104HGBG | Highbridge Park - step streets/park ldscape X120-110M | 3 | BID/ REGISTER CONTRACT | Dec 2007 | Mar 2008 | Feb 2019 | May 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104HGBG | Highbridge Park - step streets/park ldscape X120-110M | 4 | CONSTRUCTION | Mar 2008 | Mar 2009 | Nov 2019 | Oct 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104HGBG | Highbridge Park - step streets/park ldscape X120-110M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2009 | Mar 2010 | Oct 2020 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104HPRM | Bridge Park-Highbridge Greenway promenade | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2013
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104HPRM | Bridge Park-Highbridge Greenway promenade | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104HPRM | Bridge Park-Highbridge Greenway promenade | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2020 | Mar 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104HPRM | Bridge Park-Highbridge Greenway promenade | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2021 | Mar 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104HPRM | Bridge Park-Highbridge Greenway promenade | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2022 | Feb 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104JKIL | Joyce Kilmer Park - Fencing (X028-114M) | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Nov 2013
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104JKIL | Joyce Kilmer Park - Fencing (X028-114M) | 2 | DESIGN | Sep 2013 | Dec 2013 | Nov 2013 | Aug 2015
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104JKIL | Joyce Kilmer Park - Fencing (X028-114M) | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | May 2016 | Feb 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104JKIL | Joyce Kilmer Park - Fencing (X028-114M) | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2017 | Mar 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104JKIL | Joyce Kilmer Park - Fencing (X028-114M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2018 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104JRME | Jerome Playground S- Handball courts renovation X148C7-120M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104JRME | Jerome Playground S- Handball courts renovation X148C7-120M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104JRME | Jerome Playground S- Handball courts renovation X148C7-120M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104JRME | Jerome Playground S- Handball courts renovation X148C7-120M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104JRME | Jerome Playground S- Handball courts renovation X148C7-120M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104MPSK | Mullaly Park Skate Park Reconstruction | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104MPSK | Mullaly Park Skate Park Reconstruction | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104MPSK | Mullaly Park Skate Park Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104MPSK | Mullaly Park Skate Park Reconstruction | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104MPSK | Mullaly Park Skate Park Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104MRPG | Merriam Playground-RC of Upper & Lower | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Oct 2023 | Mar 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104MRPG | Merriam Playground-RC of Upper & Lower | 2 | DESIGN | Dec 2022 | Dec 2023 | Mar 2024 | Mar 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104MRPG | Merriam Playground-RC of Upper & Lower | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Mar 2025 | Dec 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104MRPG | Merriam Playground-RC of Upper & Lower | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Dec 2025 | Dec 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104MRPG | Merriam Playground-RC of Upper & Lower | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Dec 2026 | Dec 2029
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104SMPG | Summit Playground - Improvements | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104SMPG | Summit Playground - Improvements | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104SMPG | Summit Playground - Improvements | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104SMPG | Summit Playground - Improvements | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104SMPG | Summit Playground - Improvements | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-105GALO | Galileo Playground - bring surface area to grade | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2024 | Dec 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-105GALO | Galileo Playground - bring surface area to grade | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2024 | Dec 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-105GALO | Galileo Playground - bring surface area to grade | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2025 | Sep 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-105GALO | Galileo Playground - bring surface area to grade | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2026 | Sep 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-105GALO | Galileo Playground - bring surface area to grade | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2027 | Sep 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-105HOPE | Mount Hope Garden (X274-113M) | 3 | BID/ REGISTER CONTRACT | Dec 2012 | Mar 2013 | Dec 2012 | Mar 2013
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-105HOPE | Mount Hope Garden (X274-113M) | 4 | CONSTRUCTION | Mar 2013 | Mar 2014 | Mar 2013 | Mar 2014
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-105HOPE | Mount Hope Garden (X274-113M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-105MHGT | MABEL HAMPTON Garden accessibilIty & garden bed renovations | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-105MHGT | MABEL HAMPTON Garden accessibilIty & garden bed renovations | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-105MHGT | MABEL HAMPTON Garden accessibilIty & garden bed renovations | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-105MHGT | MABEL HAMPTON Garden accessibilIty & garden bed renovations | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-105MHGT | MABEL HAMPTON Garden accessibilIty & garden bed renovations | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-105UWPB | University Woods Parks Beautification - Tree Plantings | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-105UWPB | University Woods Parks Beautification - Tree Plantings | 2 | DESIGN | Feb 2024 | Feb 2026 | Feb 2024 | Feb 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-105UWPB | University Woods Parks Beautification - Tree Plantings | 3 | BID/ REGISTER CONTRACT | Feb 2026 | Nov 2026 | Feb 2026 | Nov 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-105UWPB | University Woods Parks Beautification - Tree Plantings | 4 | CONSTRUCTION | Nov 2026 | Nov 2029 | Nov 2026 | Nov 2029
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-105UWPB | University Woods Parks Beautification - Tree Plantings | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2029 | Nov 2031 | Nov 2029 | Nov 2031
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106CICP | CICCARONE PARK- NEW ADDITIONS INCLUDING BASKETBALL COURTS | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106CICP | CICCARONE PARK- NEW ADDITIONS INCLUDING BASKETBALL COURTS | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106CICP | CICCARONE PARK- NEW ADDITIONS INCLUDING BASKETBALL COURTS | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106CICP | CICCARONE PARK- NEW ADDITIONS INCLUDING BASKETBALL COURTS | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106CICP | CICCARONE PARK- NEW ADDITIONS INCLUDING BASKETBALL COURTS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106CRTN | CROTONA PARKWAY MALLS NO. 4, 6, 7, 8, AND 9 RECONSTRUCTION | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106CRTN | CROTONA PARKWAY MALLS NO. 4, 6, 7, 8, AND 9 RECONSTRUCTION | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106CRTN | CROTONA PARKWAY MALLS NO. 4, 6, 7, 8, AND 9 RECONSTRUCTION | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106CRTN | CROTONA PARKWAY MALLS NO. 4, 6, 7, 8, AND 9 RECONSTRUCTION | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106CRTN | CROTONA PARKWAY MALLS NO. 4, 6, 7, 8, AND 9 RECONSTRUCTION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106PCCA | Poe Cottage Caretaker Apartment RC | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106PCCA | Poe Cottage Caretaker Apartment RC | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106PCCA | Poe Cottage Caretaker Apartment RC | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106PCCA | Poe Cottage Caretaker Apartment RC | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106PCCA | Poe Cottage Caretaker Apartment RC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Jun 2029 | Nov 2026 | Jun 2029
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106QUAR | Quarry Ballfield-Cons of synthetic turf soccer fd-X263-119M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106QUAR | Quarry Ballfield-Cons of synthetic turf soccer fd-X263-119M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106QUAR | Quarry Ballfield-Cons of synthetic turf soccer fd-X263-119M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106QUAR | Quarry Ballfield-Cons of synthetic turf soccer fd-X263-119M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106QUAR | Quarry Ballfield-Cons of synthetic turf soccer fd-X263-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107CPFE | Classic Plgd in Van Cortlandt Park-Install Fitness Equipment | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Oct 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107CPFE | Classic Plgd in Van Cortlandt Park-Install Fitness Equipment | 2 | DESIGN | Dec 2017 | Dec 2018 | Oct 2020 | Oct 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107CPFE | Classic Plgd in Van Cortlandt Park-Install Fitness Equipment | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Oct 2021 | Jul 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107CPFE | Classic Plgd in Van Cortlandt Park-Install Fitness Equipment | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Jul 2022 | Jul 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107CPFE | Classic Plgd in Van Cortlandt Park-Install Fitness Equipment | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Jul 2023 | Dec 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107HRSP | HARRIS PARK (HARRIS FIELD)--NEW FIELD | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107HRSP | HARRIS PARK (HARRIS FIELD)--NEW FIELD | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107HRSP | HARRIS PARK (HARRIS FIELD)--NEW FIELD | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107HRSP | HARRIS PARK (HARRIS FIELD)--NEW FIELD | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107HRSP | HARRIS PARK (HARRIS FIELD)--NEW FIELD | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107POEP | POE PARK PLAZA RECON | 1 | DEVELOP SCOPE | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107POEP | POE PARK PLAZA RECON | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107POEP | POE PARK PLAZA RECON | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107POEP | POE PARK PLAZA RECON | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107POEP | POE PARK PLAZA RECON | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107PPPE | Poe Park Play Equ. - new play equ. & add a sprinkler system | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107PPPE | Poe Park Play Equ. - new play equ. & add a sprinkler system | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107PPPE | Poe Park Play Equ. - new play equ. & add a sprinkler system | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107PPPE | Poe Park Play Equ. - new play equ. & add a sprinkler system | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107PPPE | Poe Park Play Equ. - new play equ. & add a sprinkler system | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107PPV1 | Poe Park - Poe Cottage - ADA ramp X040-116M | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Sep 2014
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107PPV1 | Poe Park - Poe Cottage - ADA ramp X040-116M | 2 | DESIGN | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107PPV1 | Poe Park - Poe Cottage - ADA ramp X040-116M | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2014 | Mar 2015
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107PPV1 | Poe Park - Poe Cottage - ADA ramp X040-116M | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107PPV1 | Poe Park - Poe Cottage - ADA ramp X040-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2016 | Jun 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107SJDR | St. James Park--Dog Run- X044-118M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107SJDR | St. James Park--Dog Run- X044-118M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107SJDR | St. James Park--Dog Run- X044-118M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107SJDR | St. James Park--Dog Run- X044-118M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107SJDR | St. James Park--Dog Run- X044-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2030
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107SJRC | ST JAMES PARK REC CTR RENOV. | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107SJRC | ST JAMES PARK REC CTR RENOV. | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107SJRC | ST JAMES PARK REC CTR RENOV. | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107SJRC | ST JAMES PARK REC CTR RENOV. | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107SJRC | ST JAMES PARK REC CTR RENOV. | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2029
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107WBSK | Williamsbridge Oval const Skate Park- X104-115M | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | May 2015
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107WBSK | Williamsbridge Oval const Skate Park- X104-115M | 2 | DESIGN | Sep 2014 | Dec 2014 | May 2015 | Feb 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107WBSK | Williamsbridge Oval const Skate Park- X104-115M | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Nov 2016 | Jan 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107WBSK | Williamsbridge Oval const Skate Park- X104-115M | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Feb 2018 | Mar 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107WBSK | Williamsbridge Oval const Skate Park- X104-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2019 | Jun 2030
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107WOIF | WILLIAMSBRIDGE OVAL IMPROVEMENT | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107WOIF | WILLIAMSBRIDGE OVAL IMPROVEMENT | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107WOIF | WILLIAMSBRIDGE OVAL IMPROVEMENT | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107WOIF | WILLIAMSBRIDGE OVAL IMPROVEMENT | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107WOIF | WILLIAMSBRIDGE OVAL IMPROVEMENT | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108EWNP | Ewen Park Installation of adult fitness equipment(X019-119M) | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108EWNP | Ewen Park Installation of adult fitness equipment(X019-119M) | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108EWNP | Ewen Park Installation of adult fitness equipment(X019-119M) | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108EWNP | Ewen Park Installation of adult fitness equipment(X019-119M) | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108EWNP | Ewen Park Installation of adult fitness equipment(X019-119M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108EWPK | Ewen Park - Reconstruct. Staircase | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108EWPK | Ewen Park - Reconstruct. Staircase | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108EWPK | Ewen Park - Reconstruct. Staircase | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108EWPK | Ewen Park - Reconstruct. Staircase | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108EWPK | Ewen Park - Reconstruct. Staircase | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108FTFR | Washington's Walk Fort Four Plgd PRB X038-118M | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jun 2017 | Sep 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108FTFR | Washington's Walk Fort Four Plgd PRB X038-118M | 2 | DESIGN | Sep 2014 | Dec 2014 | Oct 2020 | Dec 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108FTFR | Washington's Walk Fort Four Plgd PRB X038-118M | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2020 | Mar 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108FTFR | Washington's Walk Fort Four Plgd PRB X038-118M | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2021 | Mar 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108FTFR | Washington's Walk Fort Four Plgd PRB X038-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2022 | Mar 2030
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108HHPK | Henry Hudson Park basketball court renovation (X080-115M) | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Sep 2014
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108HHPK | Henry Hudson Park basketball court renovation (X080-115M) | 2 | DESIGN | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108HHPK | Henry Hudson Park basketball court renovation (X080-115M) | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2014 | Mar 2015
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108HHPK | Henry Hudson Park basketball court renovation (X080-115M) | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108HHPK | Henry Hudson Park basketball court renovation (X080-115M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2016 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108MUSE | Van Cortlandt Park -Museum- New perimeter Fencing | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108MUSE | Van Cortlandt Park -Museum- New perimeter Fencing | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108MUSE | Van Cortlandt Park -Museum- New perimeter Fencing | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108MUSE | Van Cortlandt Park -Museum- New perimeter Fencing | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108MUSE | Van Cortlandt Park -Museum- New perimeter Fencing | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108MUSM | Van Cortlandt Park - House Museum Renovation | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108MUSM | Van Cortlandt Park - House Museum Renovation | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108MUSM | Van Cortlandt Park - House Museum Renovation | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108MUSM | Van Cortlandt Park - House Museum Renovation | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108MUSM | Van Cortlandt Park - House Museum Renovation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108RIVE | RIVERDALE PARK-WETLANDS & SLOPES / X142-101M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2017 | Oct 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108RIVE | RIVERDALE PARK-WETLANDS & SLOPES / X142-101M | 2 | DESIGN | Dec 2016 | Sep 2017 | Dec 2016 | Sep 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108RIVE | RIVERDALE PARK-WETLANDS & SLOPES / X142-101M | 3 | BID/ REGISTER CONTRACT | Sep 2017 | Jun 2018 | Sep 2017 | Jun 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108RIVE | RIVERDALE PARK-WETLANDS & SLOPES / X142-101M | 4 | CONSTRUCTION | Jun 2018 | Dec 2020 | Jun 2018 | Dec 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108RIVE | RIVERDALE PARK-WETLANDS & SLOPES / X142-101M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2020 | Dec 2022 | Dec 2020 | Jun 2033
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SDPW | Spuyten Duyvil Shorefront Park - pond wall construction | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SDPW | Spuyten Duyvil Shorefront Park - pond wall construction | 2 | DESIGN | Dec 2022 | Dec 2024 | Dec 2022 | Dec 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SDPW | Spuyten Duyvil Shorefront Park - pond wall construction | 3 | BID/ REGISTER CONTRACT | Dec 2024 | Sep 2025 | Dec 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SDPW | Spuyten Duyvil Shorefront Park - pond wall construction | 4 | CONSTRUCTION | Sep 2025 | Sep 2028 | Sep 2025 | Sep 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SDPW | Spuyten Duyvil Shorefront Park - pond wall construction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2028 | Sep 2030 | Sep 2028 | Sep 2030
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SPBC | Seton Park Adult Fitness Area & Skate Park Const (X201-120M) | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Nov 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SPBC | Seton Park Adult Fitness Area & Skate Park Const (X201-120M) | 2 | DESIGN | Sep 2015 | Dec 2015 | Nov 2020 | Nov 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SPBC | Seton Park Adult Fitness Area & Skate Park Const (X201-120M) | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Nov 2021 | Aug 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SPBC | Seton Park Adult Fitness Area & Skate Park Const (X201-120M) | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Aug 2022 | Aug 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SPBC | Seton Park Adult Fitness Area & Skate Park Const (X201-120M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Aug 2023 | Aug 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108TBTF | Tibbett's Tail - Fence | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108TBTF | Tibbett's Tail - Fence | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108TBTF | Tibbett's Tail - Fence | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108TBTF | Tibbett's Tail - Fence | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108TBTF | Tibbett's Tail - Fence | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCIW | Van Cortlandt Park renovate Indian Fields (X092-116M) | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Sep 2014
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCIW | Van Cortlandt Park renovate Indian Fields (X092-116M) | 2 | DESIGN | Sep 2014 | Dec 2014 | Sep 2014 | Dec 2014
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCIW | Van Cortlandt Park renovate Indian Fields (X092-116M) | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Dec 2014 | Mar 2015
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCIW | Van Cortlandt Park renovate Indian Fields (X092-116M) | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Mar 2015 | Mar 2016
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCIW | Van Cortlandt Park renovate Indian Fields (X092-116M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2016 | Jun 2030
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCPT | Van Cortlandt Park Trails Recon (X092- | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2003 | Sep 2003
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCPT | Van Cortlandt Park Trails Recon (X092- | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCPT | Van Cortlandt Park Trails Recon (X092- | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCPT | Van Cortlandt Park Trails Recon (X092- | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCPT | Van Cortlandt Park Trails Recon (X092- | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Jun 2033
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WDLN | WOODLAWN PARK RENOVATIONS X092-121M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WDLN | WOODLAWN PARK RENOVATIONS X092-121M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WDLN | WOODLAWN PARK RENOVATIONS X092-121M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WDLN | WOODLAWN PARK RENOVATIONS X092-121M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WDLN | WOODLAWN PARK RENOVATIONS X092-121M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WORC | Williamsbridge Oval - Rec center Replacement of Rubber floor | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WORC | Williamsbridge Oval - Rec center Replacement of Rubber floor | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WORC | Williamsbridge Oval - Rec center Replacement of Rubber floor | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WORC | Williamsbridge Oval - Rec center Replacement of Rubber floor | 4 | CONSTRUCTION | Sep 2024 | Mar 2026 | Sep 2024 | Mar 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WORC | Williamsbridge Oval - Rec center Replacement of Rubber floor | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Mar 2028 | Mar 2026 | Jun 2029
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WWFF | Fort Four Playground | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WWFF | Fort Four Playground | 2 | DESIGN | Dec 2022 | Jun 2024 | Dec 2022 | Jun 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WWFF | Fort Four Playground | 3 | BID/ REGISTER CONTRACT | Jun 2024 | Mar 2025 | Jun 2024 | Mar 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WWFF | Fort Four Playground | 4 | CONSTRUCTION | Mar 2025 | Sep 2026 | Mar 2025 | Sep 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WWFF | Fort Four Playground | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2026 | Sep 2027 | Sep 2026 | Sep 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WWST | Strong Street Plg Reconstruction | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WWST | Strong Street Plg Reconstruction | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WWST | Strong Street Plg Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WWST | Strong Street Plg Reconstruction | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WWST | Strong Street Plg Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109NBLE | Noble Playground - RC PRB X123-118M | 1 | DEVELOP SCOPE | Apr 2014 | Jul 2014 | Apr 2014 | Jul 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109NBLE | Noble Playground - RC PRB X123-118M | 2 | DESIGN | Jul 2014 | Oct 2014 | Jul 2017 | Oct 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109NBLE | Noble Playground - RC PRB X123-118M | 3 | BID/ REGISTER CONTRACT | Oct 2014 | Jan 2015 | Oct 2017 | Jan 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109NBLE | Noble Playground - RC PRB X123-118M | 4 | CONSTRUCTION | Jan 2015 | Jan 2016 | Jan 2018 | Jan 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109NBLE | Noble Playground - RC PRB X123-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2016 | Jan 2017 | Jan 2019 | Jan 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109NOBE | Noble Playground Reconstruction (X123-119M) | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109NOBE | Noble Playground Reconstruction (X123-119M) | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109NOBE | Noble Playground Reconstruction (X123-119M) | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109NOBE | Noble Playground Reconstruction (X123-119M) | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109NOBE | Noble Playground Reconstruction (X123-119M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109SVPT | Soundview Park - Bronx River access X118-201MA | 1 | DEVELOP SCOPE | Jul 2006 | Oct 2006 | Jul 2006 | Oct 2006
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109SVPT | Soundview Park - Bronx River access X118-201MA | 2 | DESIGN | Oct 2006 | Jan 2007 | Oct 2006 | Jan 2007
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109SVPT | Soundview Park - Bronx River access X118-201MA | 3 | BID/ REGISTER CONTRACT | Jan 2007 | Apr 2007 | Jan 2007 | Apr 2007
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109SVPT | Soundview Park - Bronx River access X118-201MA | 4 | CONSTRUCTION | Apr 2007 | Apr 2008 | Apr 2007 | Apr 2008
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109SVPT | Soundview Park - Bronx River access X118-201MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2008 | Apr 2009 | Apr 2008 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110BFPG | Bufano Playground Upgrade | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110BFPG | Bufano Playground Upgrade | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110BFPG | Bufano Playground Upgrade | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110BFPG | Bufano Playground Upgrade | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110BFPG | Bufano Playground Upgrade | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110EXPA | ORCHARD BEACH BATHHOUSE -- X039-102M/402M | 1 | DEVELOP SCOPE | Jan 2003 | Mar 2003 | Jan 2003 | Mar 2003
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110EXPA | ORCHARD BEACH BATHHOUSE -- X039-102M/402M | 2 | DESIGN | Mar 2003 | Mar 2003 | Mar 2003 | Mar 2003
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110EXPA | ORCHARD BEACH BATHHOUSE -- X039-102M/402M | 3 | BID/ REGISTER CONTRACT | Apr 2003 | Mar 2004 | Apr 2003 | Mar 2004
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110EXPA | ORCHARD BEACH BATHHOUSE -- X039-102M/402M | 4 | CONSTRUCTION | Apr 2004 | Apr 2005 | Apr 2004 | Apr 2005
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110EXPA | ORCHARD BEACH BATHHOUSE -- X039-102M/402M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2005 | Mar 2006 | Apr 2005 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110FLAG | Ferry Point Park - Flagpole at 911 Memorial Hilltop Grove | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110FLAG | Ferry Point Park - Flagpole at 911 Memorial Hilltop Grove | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110FLAG | Ferry Point Park - Flagpole at 911 Memorial Hilltop Grove | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110FLAG | Ferry Point Park - Flagpole at 911 Memorial Hilltop Grove | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110FLAG | Ferry Point Park - Flagpole at 911 Memorial Hilltop Grove | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110FPPP | Ferry Point Playground Reconstruction X126 | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110FPPP | Ferry Point Playground Reconstruction X126 | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110FPPP | Ferry Point Playground Reconstruction X126 | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110FPPP | Ferry Point Playground Reconstruction X126 | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110FPPP | Ferry Point Playground Reconstruction X126 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110GCWP | Givans Creek Woods Pathways | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110GCWP | Givans Creek Woods Pathways | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110GCWP | Givans Creek Woods Pathways | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110GCWP | Givans Creek Woods Pathways | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110GCWP | Givans Creek Woods Pathways | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110HART | Hart Island Shoreline Restoration | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110HART | Hart Island Shoreline Restoration | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110HART | Hart Island Shoreline Restoration | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110HART | Hart Island Shoreline Restoration | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110HART | Hart Island Shoreline Restoration | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110HRMO | Hutchinson River Parkway M&O Facility Construction | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110HRMO | Hutchinson River Parkway M&O Facility Construction | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110HRMO | Hutchinson River Parkway M&O Facility Construction | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110HRMO | Hutchinson River Parkway M&O Facility Construction | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110HRMO | Hutchinson River Parkway M&O Facility Construction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2029
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110MAN2 | Bartow Mansion Structural Stabilization&Carriage House Roof | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110MAN2 | Bartow Mansion Structural Stabilization&Carriage House Roof | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2022 | Dec 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110MAN2 | Bartow Mansion Structural Stabilization&Carriage House Roof | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110MAN2 | Bartow Mansion Structural Stabilization&Carriage House Roof | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110MAN2 | Bartow Mansion Structural Stabilization&Carriage House Roof | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2025 | Sep 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110ODFA | Owen Dolen Rec. Center: Fire Alarm Reconstruction | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110ODFA | Owen Dolen Rec. Center: Fire Alarm Reconstruction | 2 | DESIGN | Dec 2019 | Dec 2021 | Dec 2019 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110ODFA | Owen Dolen Rec. Center: Fire Alarm Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110ODFA | Owen Dolen Rec. Center: Fire Alarm Reconstruction | 4 | CONSTRUCTION | Sep 2022 | Sep 2025 | Sep 2022 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110ODFA | Owen Dolen Rec. Center: Fire Alarm Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110PPTH | PELHAM BAY PARK - PATHWAYS | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110PPTH | PELHAM BAY PARK - PATHWAYS | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110PPTH | PELHAM BAY PARK - PATHWAYS | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110PPTH | PELHAM BAY PARK - PATHWAYS | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110PPTH | PELHAM BAY PARK - PATHWAYS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111BPWF | Bronx PK- Installation of a water fountain X002-320M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2003 | Sep 2003
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111BPWF | Bronx PK- Installation of a water fountain X002-320M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111BPWF | Bronx PK- Installation of a water fountain X002-320M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111BPWF | Bronx PK- Installation of a water fountain X002-320M | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111BPWF | Bronx PK- Installation of a water fountain X002-320M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2029
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111BRAD | Brady Playground- Reconstruction | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111BRAD | Brady Playground- Reconstruction | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111BRAD | Brady Playground- Reconstruction | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111BRAD | Brady Playground- Reconstruction | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111BRAD | Brady Playground- Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Jun 2029
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111ESPG | Eastchester Playground | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111ESPG | Eastchester Playground | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111ESPG | Eastchester Playground | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111ESPG | Eastchester Playground | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111ESPG | Eastchester Playground | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Jun 2029
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111FFBB | FRISCH FIELD IN BRONX PK- RENO OF BBALL FIELD | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111FFBB | FRISCH FIELD IN BRONX PK- RENO OF BBALL FIELD | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111FFBB | FRISCH FIELD IN BRONX PK- RENO OF BBALL FIELD | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111FFBB | FRISCH FIELD IN BRONX PK- RENO OF BBALL FIELD | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111FFBB | FRISCH FIELD IN BRONX PK- RENO OF BBALL FIELD | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111LRTO | Loreto Park - Recon Soccer field Asphalt to Turf (X163-118M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Feb 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111LRTO | Loreto Park - Recon Soccer field Asphalt to Turf (X163-118M | 2 | DESIGN | Sep 2015 | Dec 2015 | Feb 2018 | Feb 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111LRTO | Loreto Park - Recon Soccer field Asphalt to Turf (X163-118M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Jun 2019 | Nov 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111LRTO | Loreto Park - Recon Soccer field Asphalt to Turf (X163-118M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Sep 2020 | Nov 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111LRTO | Loreto Park - Recon Soccer field Asphalt to Turf (X163-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Nov 2020 | Jun 2030
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111ZIMP | Zimmerman Playground Basketball Court RC X087-118M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2012 | Dec 2012
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111ZIMP | Zimmerman Playground Basketball Court RC X087-118M | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2012 | Dec 2013
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111ZIMP | Zimmerman Playground Basketball Court RC X087-118M | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2013 | Sep 2014
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111ZIMP | Zimmerman Playground Basketball Court RC X087-118M | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2014 | Sep 2015
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111ZIMP | Zimmerman Playground Basketball Court RC X087-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2015 | Jun 2029
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112AGNS | Agnes Haywood Park - basketball court & park house X169-114M | 1 | DEVELOP SCOPE | Jul 2010 | Sep 2010 | Jul 2010 | Mar 2015
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112AGNS | Agnes Haywood Park - basketball court & park house X169-114M | 2 | DESIGN | Sep 2010 | Dec 2010 | Mar 2015 | Apr 2016
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112AGNS | Agnes Haywood Park - basketball court & park house X169-114M | 3 | BID/ REGISTER CONTRACT | Dec 2010 | Mar 2011 | Jul 2016 | Jun 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112AGNS | Agnes Haywood Park - basketball court & park house X169-114M | 4 | CONSTRUCTION | Mar 2011 | Mar 2012 | Jul 2017 | Mar 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112AGNS | Agnes Haywood Park - basketball court & park house X169-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2012 | Mar 2013 | Mar 2019 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112LACE | BX River Shoelace Pk- Recon of Paths & Entrance (X004-117M) | 2 | DESIGN | Mar 2016 | Jun 2017 | Nov 2016 | Jul 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112LACE | BX River Shoelace Pk- Recon of Paths & Entrance (X004-117M) | 3 | BID/ REGISTER CONTRACT | Jun 2017 | Mar 2018 | Jan 2019 | Sep 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112LACE | BX River Shoelace Pk- Recon of Paths & Entrance (X004-117M) | 4 | CONSTRUCTION | Mar 2018 | Mar 2019 | Nov 2019 | Apr 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112LACE | BX River Shoelace Pk- Recon of Paths & Entrance (X004-117M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Mar 2020 | Apr 2021 | Apr 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112SETW | Seton Falls Park Walkways Renovations X092-113M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2003 | Sep 2003
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112SETW | Seton Falls Park Walkways Renovations X092-113M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112SETW | Seton Falls Park Walkways Renovations X092-113M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112SETW | Seton Falls Park Walkways Renovations X092-113M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112SETW | Seton Falls Park Walkways Renovations X092-113M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112SHLP | Shoelace Park - Fitness Equipment | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112SHLP | Shoelace Park - Fitness Equipment | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112SHLP | Shoelace Park - Fitness Equipment | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112SHLP | Shoelace Park - Fitness Equipment | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112SHLP | Shoelace Park - Fitness Equipment | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112WKFD | Wakefield Park Reconstruction (X188-116M) | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Dec 2016
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112WKFD | Wakefield Park Reconstruction (X188-116M) | 2 | DESIGN | Sep 2015 | Dec 2015 | Dec 2016 | Mar 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112WKFD | Wakefield Park Reconstruction (X188-116M) | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Mar 2020 | Jun 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112WKFD | Wakefield Park Reconstruction (X188-116M) | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Jun 2020 | Jun 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112WKFD | Wakefield Park Reconstruction (X188-116M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Jun 2021 | Oct 2030
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-117CPBM | Crotona Park- Install Bluelight Monitors in CD17 | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2023 | Dec 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-117CPBM | Crotona Park- Install Bluelight Monitors in CD17 | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2023 | Dec 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-117CPBM | Crotona Park- Install Bluelight Monitors in CD17 | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-117CPBM | Crotona Park- Install Bluelight Monitors in CD17 | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2025 | Sep 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-117CPBM | Crotona Park- Install Bluelight Monitors in CD17 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2026 | Sep 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-118FOXP | FOX PLAYGROUND PRB X247-118M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-118FOXP | FOX PLAYGROUND PRB X247-118M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-118FOXP | FOX PLAYGROUND PRB X247-118M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-118FOXP | FOX PLAYGROUND PRB X247-118M | 4 | CONSTRUCTION | Sep 2019 | Mar 2021 | Sep 2019 | Mar 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-118FOXP | FOX PLAYGROUND PRB X247-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Mar 2022 | Mar 2021 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ANCH02 | St. Mary's Anchor Pk Ph. 2-Amphi, Plaza &Pathways X045-218M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ANCH02 | St. Mary's Anchor Pk Ph. 2-Amphi, Plaza &Pathways X045-218M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ANCH02 | St. Mary's Anchor Pk Ph. 2-Amphi, Plaza &Pathways X045-218M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ANCH02 | St. Mary's Anchor Pk Ph. 2-Amphi, Plaza &Pathways X045-218M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ANCH02 | St. Mary's Anchor Pk Ph. 2-Amphi, Plaza &Pathways X045-218M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2030
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1AQWALK | MLK Triangle/Aqueduct Walk X001-114M | 1 | DEVELOP SCOPE | Jul 2010 | Sep 2010 | Jul 2010 | Nov 2016
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1AQWALK | MLK Triangle/Aqueduct Walk X001-114M | 2 | DESIGN | Sep 2010 | Dec 2010 | Nov 2016 | Jul 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1AQWALK | MLK Triangle/Aqueduct Walk X001-114M | 3 | BID/ REGISTER CONTRACT | Dec 2010 | Mar 2011 | Jan 2019 | Sep 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1AQWALK | MLK Triangle/Aqueduct Walk X001-114M | 4 | CONSTRUCTION | Mar 2011 | Mar 2012 | Nov 2019 | Apr 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1AQWALK | MLK Triangle/Aqueduct Walk X001-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2012 | Mar 2013 | Apr 2021 | Apr 2030
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ARAELV | Bronx Aramark building for elevator - X360-119M | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ARAELV | Bronx Aramark building for elevator - X360-119M | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ARAELV | Bronx Aramark building for elevator - X360-119M | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ARAELV | Bronx Aramark building for elevator - X360-119M | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ARAELV | Bronx Aramark building for elevator - X360-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ARAMEZ | Mezzanine dsgn & cons Aramark Bldg Shops & store X360-119M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ARAMEZ | Mezzanine dsgn & cons Aramark Bldg Shops & store X360-119M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ARAMEZ | Mezzanine dsgn & cons Aramark Bldg Shops & store X360-119M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ARAMEZ | Mezzanine dsgn & cons Aramark Bldg Shops & store X360-119M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ARAMEZ | Mezzanine dsgn & cons Aramark Bldg Shops & store X360-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2031
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1AWRWR | Aqueduct Walk Retaining Wall RC | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1AWRWR | Aqueduct Walk Retaining Wall RC | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1AWRWR | Aqueduct Walk Retaining Wall RC | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1AWRWR | Aqueduct Walk Retaining Wall RC | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1AWRWR | Aqueduct Walk Retaining Wall RC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BILYRF | Bailey Plgd public restroom building Roof Recon CNYG-1018MA1 | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BILYRF | Bailey Plgd public restroom building Roof Recon CNYG-1018MA1 | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BILYRF | Bailey Plgd public restroom building Roof Recon CNYG-1018MA1 | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BILYRF | Bailey Plgd public restroom building Roof Recon CNYG-1018MA1 | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BILYRF | Bailey Plgd public restroom building Roof Recon CNYG-1018MA1 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BOLTPK | Bolton Park Wetland Restore. & PK Con. | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BOLTPK | Bolton Park Wetland Restore. & PK Con. | 2 | DESIGN | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BOLTPK | Bolton Park Wetland Restore. & PK Con. | 3 | BID/ REGISTER CONTRACT | Sep 2021 | Jun 2022 | Sep 2021 | Jun 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BOLTPK | Bolton Park Wetland Restore. & PK Con. | 4 | CONSTRUCTION | Jun 2022 | Dec 2024 | Jun 2022 | Dec 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BOLTPK | Bolton Park Wetland Restore. & PK Con. | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2024 | Dec 2026 | Dec 2024 | Dec 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BWBXP1 | Reconstruction of plgrs, Borough of Bronx (XG-508M) | 1 | DEVELOP SCOPE | Jul 2011 | Sep 2011 | Jul 2018 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BWBXP1 | Reconstruction of plgrs, Borough of Bronx (XG-508M) | 2 | DESIGN | Sep 2011 | Dec 2011 | Sep 2011 | Dec 2011
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BWBXP1 | Reconstruction of plgrs, Borough of Bronx (XG-508M) | 3 | BID/ REGISTER CONTRACT | Dec 2011 | Mar 2012 | Dec 2011 | Mar 2012
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BWBXP1 | Reconstruction of plgrs, Borough of Bronx (XG-508M) | 4 | CONSTRUCTION | Mar 2012 | Mar 2013 | Mar 2012 | Mar 2013
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BWBXP1 | Reconstruction of plgrs, Borough of Bronx (XG-508M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2013 | Mar 2014 | Mar 2013 | Jun 2033
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CHRLRF | French Charley's Plgd public restroom bldg Roof CNYG-1018MA1 | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CHRLRF | French Charley's Plgd public restroom bldg Roof CNYG-1018MA1 | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CHRLRF | French Charley's Plgd public restroom bldg Roof CNYG-1018MA1 | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CHRLRF | French Charley's Plgd public restroom bldg Roof CNYG-1018MA1 | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CHRLRF | French Charley's Plgd public restroom bldg Roof CNYG-1018MA1 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIBR2 | CPI PH2-174TH St.Plgd/BX River House-Plgd/Mini Pool X159-118 | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2015 | Dec 2015
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIBR2 | CPI PH2-174TH St.Plgd/BX River House-Plgd/Mini Pool X159-118 | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2015 | Dec 2016
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIBR2 | CPI PH2-174TH St.Plgd/BX River House-Plgd/Mini Pool X159-118 | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2016 | Sep 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIBR2 | CPI PH2-174TH St.Plgd/BX River House-Plgd/Mini Pool X159-118 | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2017 | Sep 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIBR2 | CPI PH2-174TH St.Plgd/BX River House-Plgd/Mini Pool X159-118 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2018 | Jun 2030
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIBR3 | CPI PH2-174TH St.Plgd/BX River House - PRB X159-218M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIBR3 | CPI PH2-174TH St.Plgd/BX River House - PRB X159-218M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIBR3 | CPI PH2-174TH St.Plgd/BX River House - PRB X159-218M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIBR3 | CPI PH2-174TH St.Plgd/BX River House - PRB X159-218M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIBR3 | CPI PH2-174TH St.Plgd/BX River House - PRB X159-218M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2030
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIDPG | Dawson Playground RC | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIDPG | Dawson Playground RC | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIDPG | Dawson Playground RC | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIDPG | Dawson Playground RC | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIDPG | Dawson Playground RC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIDVP | CPI-CHIEF DENNIS L. DEVLIN PK RECON | 1 | DEVELOP SCOPE | Mar 2022 | Sep 2022 | Mar 2022 | Sep 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIDVP | CPI-CHIEF DENNIS L. DEVLIN PK RECON | 2 | DESIGN | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIDVP | CPI-CHIEF DENNIS L. DEVLIN PK RECON | 3 | BID/ REGISTER CONTRACT | Sep 2023 | Jun 2024 | Sep 2023 | Jun 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIDVP | CPI-CHIEF DENNIS L. DEVLIN PK RECON | 4 | CONSTRUCTION | Jun 2024 | Jun 2025 | Jun 2024 | Jun 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIDVP | CPI-CHIEF DENNIS L. DEVLIN PK RECON | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIEJM | CPI - Eae J. Mitchell Park Reconstruction | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIEJM | CPI - Eae J. Mitchell Park Reconstruction | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIEJM | CPI - Eae J. Mitchell Park Reconstruction | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIEJM | CPI - Eae J. Mitchell Park Reconstruction | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIEJM | CPI - Eae J. Mitchell Park Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIFIP | Fort Independence Playground Reconstruction X020 | 1 | DEVELOP SCOPE | Oct 2023 | Mar 2024 | Oct 2023 | Mar 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIFIP | Fort Independence Playground Reconstruction X020 | 2 | DESIGN | Mar 2024 | Mar 2025 | Mar 2024 | Mar 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIFIP | Fort Independence Playground Reconstruction X020 | 3 | BID/ REGISTER CONTRACT | Mar 2025 | Dec 2025 | Mar 2025 | Dec 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIFIP | Fort Independence Playground Reconstruction X020 | 4 | CONSTRUCTION | Dec 2025 | Dec 2026 | Dec 2025 | Dec 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIFIP | Fort Independence Playground Reconstruction X020 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2026 | Jun 2031 | Dec 2026 | Jun 2031
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIHAP | Harding Park Playground Reconstruction | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIHAP | Harding Park Playground Reconstruction | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIHAP | Harding Park Playground Reconstruction | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIHAP | Harding Park Playground Reconstruction | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIHAP | Harding Park Playground Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIHCS | CPI - Horseshoe Public Restroom | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIHCS | CPI - Horseshoe Public Restroom | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIHCS | CPI - Horseshoe Public Restroom | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIHCS | CPI - Horseshoe Public Restroom | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIHCS | CPI - Horseshoe Public Restroom | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIHNT | CPI PH 1- Hunts Point Playground (X113-115M) | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Dec 2014
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIHNT | CPI PH 1- Hunts Point Playground (X113-115M) | 2 | DESIGN | Sep 2014 | Dec 2014 | Dec 2014 | Mar 2015
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIHNT | CPI PH 1- Hunts Point Playground (X113-115M) | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Feb 2017 | Aug 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIHNT | CPI PH 1- Hunts Point Playground (X113-115M) | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Aug 2017 | Mar 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIHNT | CPI PH 1- Hunts Point Playground (X113-115M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Mar 2019 | Jun 2030
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIHSP | CPI - HORESHOE PLGD | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIHSP | CPI - HORESHOE PLGD | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIHSP | CPI - HORESHOE PLGD | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIHSP | CPI - HORESHOE PLGD | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIHSP | CPI - HORESHOE PLGD | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIJJP | Jennie Jerome Playground RC | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIJJP | Jennie Jerome Playground RC | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIJJP | Jennie Jerome Playground RC | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIJJP | Jennie Jerome Playground RC | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIJJP | Jennie Jerome Playground RC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIP52 | CPI - Plgd 52 (LII) Reconstruction-X179-115M | 1 | DEVELOP SCOPE | Jul 2014 | Sep 2014 | Jul 2014 | Dec 2014
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIP52 | CPI - Plgd 52 (LII) Reconstruction-X179-115M | 2 | DESIGN | Sep 2014 | Dec 2014 | Dec 2014 | Mar 2016
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIP52 | CPI - Plgd 52 (LII) Reconstruction-X179-115M | 3 | BID/ REGISTER CONTRACT | Dec 2014 | Mar 2015 | Mar 2016 | Dec 2016
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIP52 | CPI - Plgd 52 (LII) Reconstruction-X179-115M | 4 | CONSTRUCTION | Mar 2015 | Mar 2016 | Dec 2016 | Dec 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIP52 | CPI - Plgd 52 (LII) Reconstruction-X179-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Mar 2017 | Dec 2017 | Dec 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIPNT | CPI - Pontiac Playground Reconstruction X207-122M | 1 | DEVELOP SCOPE | Feb 2022 | Aug 2022 | Feb 2022 | Aug 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIPNT | CPI - Pontiac Playground Reconstruction X207-122M | 2 | DESIGN | Aug 2022 | Aug 2023 | Aug 2022 | Aug 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIPNT | CPI - Pontiac Playground Reconstruction X207-122M | 3 | BID/ REGISTER CONTRACT | Aug 2023 | May 2024 | Aug 2023 | May 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIPNT | CPI - Pontiac Playground Reconstruction X207-122M | 4 | CONSTRUCTION | May 2024 | May 2025 | May 2024 | May 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIPNT | CPI - Pontiac Playground Reconstruction X207-122M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | May 2025 | May 2026 | May 2025 | Jun 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIYVP | Youth Village Playground Reconstruction X242 | 1 | DEVELOP SCOPE | Oct 2023 | Mar 2024 | Oct 2023 | Mar 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIYVP | Youth Village Playground Reconstruction X242 | 2 | DESIGN | Mar 2024 | Mar 2025 | Mar 2024 | Mar 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIYVP | Youth Village Playground Reconstruction X242 | 3 | BID/ REGISTER CONTRACT | Mar 2025 | Dec 2025 | Mar 2025 | Dec 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIYVP | Youth Village Playground Reconstruction X242 | 4 | CONSTRUCTION | Dec 2025 | Dec 2026 | Dec 2025 | Dec 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIYVP | Youth Village Playground Reconstruction X242 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2026 | Jun 2031 | Dec 2026 | Jun 2031
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROALG | CROTONA PARK INDIAN LAKE ALGAE REDUCTION | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROALG | CROTONA PARK INDIAN LAKE ALGAE REDUCTION | 2 | DESIGN | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROALG | CROTONA PARK INDIAN LAKE ALGAE REDUCTION | 3 | BID/ REGISTER CONTRACT | Sep 2020 | Jun 2021 | Sep 2020 | Jun 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROALG | CROTONA PARK INDIAN LAKE ALGAE REDUCTION | 4 | CONSTRUCTION | Jun 2021 | Dec 2023 | Jun 2021 | Dec 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROALG | CROTONA PARK INDIAN LAKE ALGAE REDUCTION | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2023 | Dec 2025 | Dec 2023 | Dec 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT13 | VC PK- Recon Headhouse & Demolish Greenhouse X092-207M | 1 | DEVELOP SCOPE | Jul 2006 | Sep 2006 | Jul 2006 | Sep 2006
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT13 | VC PK- Recon Headhouse & Demolish Greenhouse X092-207M | 2 | DESIGN | Sep 2006 | Dec 2006 | Mar 2012 | May 2012
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT13 | VC PK- Recon Headhouse & Demolish Greenhouse X092-207M | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Aug 2012 | Oct 2012
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT13 | VC PK- Recon Headhouse & Demolish Greenhouse X092-207M | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Nov 2012 | Feb 2014
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT13 | VC PK- Recon Headhouse & Demolish Greenhouse X092-207M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Mar 2014 | Jun 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRPOHS | Crotona Park - pool towers X010-210MA3 | 1 | DEVELOP SCOPE | Jul 2009 | Sep 2009 | Jul 2009 | Nov 2010
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRPOHS | Crotona Park - pool towers X010-210MA3 | 2 | DESIGN | Sep 2009 | Dec 2009 | Nov 2010 | Nov 2012
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRPOHS | Crotona Park - pool towers X010-210MA3 | 3 | BID/ REGISTER CONTRACT | Dec 2009 | Mar 2010 | Dec 2012 | Jun 2013
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRPOHS | Crotona Park - pool towers X010-210MA3 | 4 | CONSTRUCTION | Mar 2010 | Mar 2011 | Jun 2013 | Jun 2014
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRPOHS | Crotona Park - pool towers X010-210MA3 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2011 | Mar 2012 | Jun 2014 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRPOOL | CROTONA POOL BATHHOUSE ENTRANCE & LOBBY X010-106M | 1 | DEVELOP SCOPE | Jul 2006 | Sep 2006 | Jul 2006 | Apr 2010
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRPOOL | CROTONA POOL BATHHOUSE ENTRANCE & LOBBY X010-106M | 2 | DESIGN | Sep 2006 | Dec 2006 | Apr 2010 | Jun 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRPOOL | CROTONA POOL BATHHOUSE ENTRANCE & LOBBY X010-106M | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Nov 2017 | Jun 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRPOOL | CROTONA POOL BATHHOUSE ENTRANCE & LOBBY X010-106M | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Sep 2018 | Mar 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRPOOL | CROTONA POOL BATHHOUSE ENTRANCE & LOBBY X010-106M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Mar 2021 | Mar 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRTORF | Crotona Park Pool Roof Reconstruction X010-121M | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRTORF | Crotona Park Pool Roof Reconstruction X010-121M | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRTORF | Crotona Park Pool Roof Reconstruction X010-121M | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRTORF | Crotona Park Pool Roof Reconstruction X010-121M | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRTORF | Crotona Park Pool Roof Reconstruction X010-121M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1DBPLYG | DANIEL BOONE PLAYGROUND - CONSTRUCT A PLAYGROUND | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1DBPLYG | DANIEL BOONE PLAYGROUND - CONSTRUCT A PLAYGROUND | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1DBPLYG | DANIEL BOONE PLAYGROUND - CONSTRUCT A PLAYGROUND | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1DBPLYG | DANIEL BOONE PLAYGROUND - CONSTRUCT A PLAYGROUND | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1DBPLYG | DANIEL BOONE PLAYGROUND - CONSTRUCT A PLAYGROUND | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1DCTVCP | Van Cortlandt Park Museum Telecom Service Installation | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1DCTVCP | Van Cortlandt Park Museum Telecom Service Installation | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1DCTVCP | Van Cortlandt Park Museum Telecom Service Installation | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1DCTVCP | Van Cortlandt Park Museum Telecom Service Installation | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1DCTVCP | Van Cortlandt Park Museum Telecom Service Installation | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1DEPOT | Depot Place - portion of Harlem River greenway XG-31800-106M | 1 | DEVELOP SCOPE | Jul 2006 | Sep 2006 | Jul 2006 | Sep 2006
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1DEPOT | Depot Place - portion of Harlem River greenway XG-31800-106M | 2 | DESIGN | Sep 2006 | Dec 2006 | Sep 2006 | Dec 2006
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1DEPOT | Depot Place - portion of Harlem River greenway XG-31800-106M | 3 | BID/ REGISTER CONTRACT | Dec 2006 | Mar 2007 | Dec 2006 | Mar 2007
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1DEPOT | Depot Place - portion of Harlem River greenway XG-31800-106M | 4 | CONSTRUCTION | Mar 2007 | Mar 2008 | Mar 2007 | Mar 2008
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1DEPOT | Depot Place - portion of Harlem River greenway XG-31800-106M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2008 | Mar 2009 | Mar 2008 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ECHOPK | Echo Park Playground and Sports Fields- X017-117M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ECHOPK | Echo Park Playground and Sports Fields- X017-117M | 2 | DESIGN | Dec 2016 | Dec 2017 | Dec 2016 | Dec 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ECHOPK | Echo Park Playground and Sports Fields- X017-117M | 3 | BID/ REGISTER CONTRACT | Dec 2017 | Sep 2018 | Dec 2017 | Sep 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ECHOPK | Echo Park Playground and Sports Fields- X017-117M | 4 | CONSTRUCTION | Sep 2018 | Sep 2019 | Sep 2018 | Sep 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ECHOPK | Echo Park Playground and Sports Fields- X017-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2019 | Sep 2020 | Sep 2019 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1EDENPG | Edenwald PLGD - basketball & handball crts (X165-116MA) | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2018 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1EDENPG | Edenwald PLGD - basketball & handball crts (X165-116MA) | 2 | DESIGN | Sep 2013 | Dec 2013 | Oct 2015 | Jun 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1EDENPG | Edenwald PLGD - basketball & handball crts (X165-116MA) | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | May 2018 | Jun 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1EDENPG | Edenwald PLGD - basketball & handball crts (X165-116MA) | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Jun 2022 | Jun 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1EDENPG | Edenwald PLGD - basketball & handball crts (X165-116MA) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Jun 2023 | Jan 2030
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1FACDCR | Crotona Park Pool Facade Reconstruction | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1FACDCR | Crotona Park Pool Facade Reconstruction | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1FACDCR | Crotona Park Pool Facade Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1FACDCR | Crotona Park Pool Facade Reconstruction | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1FACDCR | Crotona Park Pool Facade Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1FERRY6 | Ferry Point Golf Course Construction X126-109M | 1 | DEVELOP SCOPE | Jul 2007 | Sep 2007 | Jul 2007 | Sep 2007
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1FERRY6 | Ferry Point Golf Course Construction X126-109M | 2 | DESIGN | Sep 2007 | Dec 2007 | Sep 2007 | Dec 2007
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1FERRY6 | Ferry Point Golf Course Construction X126-109M | 3 | BID/ REGISTER CONTRACT | Dec 2007 | Mar 2008 | Dec 2007 | Mar 2008
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1FERRY6 | Ferry Point Golf Course Construction X126-109M | 4 | CONSTRUCTION | Mar 2008 | Mar 2009 | Mar 2008 | Mar 2009
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1FERRY6 | Ferry Point Golf Course Construction X126-109M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2009 | Mar 2010 | Mar 2009 | Jun 2030
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1FERRY8 | Ferry Point Park - Waterfront Park X126-116M | 1 | DEVELOP SCOPE | Jul 2009 | Sep 2009 | Jul 2009 | Nov 2015
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1FERRY8 | Ferry Point Park - Waterfront Park X126-116M | 2 | DESIGN | Sep 2009 | Dec 2009 | Nov 2015 | Jul 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1FERRY8 | Ferry Point Park - Waterfront Park X126-116M | 3 | BID/ REGISTER CONTRACT | Dec 2009 | Mar 2010 | Nov 2018 | Apr 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1FERRY8 | Ferry Point Park - Waterfront Park X126-116M | 4 | CONSTRUCTION | Mar 2010 | Mar 2011 | Apr 2025 | Apr 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1FERRY8 | Ferry Point Park - Waterfront Park X126-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2011 | Mar 2012 | Apr 2025 | Apr 2032
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1GHPCSR | Grove Hill Playground-PRB Reconstruction | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1GHPCSR | Grove Hill Playground-PRB Reconstruction | 2 | DESIGN | Dec 2017 | Dec 2018 | Jan 2018 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1GHPCSR | Grove Hill Playground-PRB Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Jan 2019 | Sep 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1GHPCSR | Grove Hill Playground-PRB Reconstruction | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1GHPCSR | Grove Hill Playground-PRB Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2030
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAFFP1 | Haffen Park - RC- Tennis & Basketball Court X196 | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAFFP1 | Haffen Park - RC- Tennis & Basketball Court X196 | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAFFP1 | Haffen Park - RC- Tennis & Basketball Court X196 | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAFFP1 | Haffen Park - RC- Tennis & Basketball Court X196 | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAFFP1 | Haffen Park - RC- Tennis & Basketball Court X196 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Jun 2029
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAFFP3 | Haffen Park - Fld House,Bathrooms, & Amphitheater | 1 | DEVELOP SCOPE | Dec 2021 | May 2022 | Jun 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAFFP3 | Haffen Park - Fld House,Bathrooms, & Amphitheater | 2 | DESIGN | May 2022 | May 2023 | Dec 2022 | Dec 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAFFP3 | Haffen Park - Fld House,Bathrooms, & Amphitheater | 3 | BID/ REGISTER CONTRACT | May 2023 | Feb 2024 | Dec 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAFFP3 | Haffen Park - Fld House,Bathrooms, & Amphitheater | 4 | CONSTRUCTION | Feb 2024 | Feb 2025 | Sep 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAFFP3 | Haffen Park - Fld House,Bathrooms, & Amphitheater | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Feb 2026 | Sep 2025 | Jun 2029
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAFFPL | Haffen Park Pool Reconstruction | 1 | DEVELOP SCOPE | Jun 2022 | Dec 2022 | Jun 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAFFPL | Haffen Park Pool Reconstruction | 2 | DESIGN | Dec 2022 | Dec 2024 | Dec 2022 | Dec 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAFFPL | Haffen Park Pool Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2024 | Sep 2025 | Dec 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAFFPL | Haffen Park Pool Reconstruction | 4 | CONSTRUCTION | Sep 2025 | Sep 2028 | Sep 2025 | Sep 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAFFPL | Haffen Park Pool Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2028 | Sep 2030 | Sep 2028 | Sep 2030
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAFFPT | HAFFEN PARK - CONSTRUCT ADULT FITNESS AREA | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAFFPT | HAFFEN PARK - CONSTRUCT ADULT FITNESS AREA | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAFFPT | HAFFEN PARK - CONSTRUCT ADULT FITNESS AREA | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAFFPT | HAFFEN PARK - CONSTRUCT ADULT FITNESS AREA | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAFFPT | HAFFEN PARK - CONSTRUCT ADULT FITNESS AREA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAMMON | Hammond Cove Shoreline Stabilization and Restoration | 1 | DEVELOP SCOPE | Jun 2023 | Dec 2023 | Jun 2023 | Dec 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAMMON | Hammond Cove Shoreline Stabilization and Restoration | 2 | DESIGN | Dec 2023 | Dec 2025 | Dec 2023 | Dec 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAMMON | Hammond Cove Shoreline Stabilization and Restoration | 3 | BID/ REGISTER CONTRACT | Dec 2025 | Sep 2026 | Dec 2025 | Sep 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAMMON | Hammond Cove Shoreline Stabilization and Restoration | 4 | CONSTRUCTION | Sep 2026 | Sep 2029 | Sep 2026 | Sep 2029
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAMMON | Hammond Cove Shoreline Stabilization and Restoration | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2029 | Sep 2031 | Sep 2029 | Sep 2031
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HCMARI | Hammond Cove Marina | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HCMARI | Hammond Cove Marina | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HCMARI | Hammond Cove Marina | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HCMARI | Hammond Cove Marina | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Sep 2020 | Sep 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HCMARI | Hammond Cove Marina | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Sep 2021 | Jun 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HGCVPR | PWOB-Hugh Grant Circle & Virginia Pk. Recon. XG-117MA | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2016 | Dec 2016
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HGCVPR | PWOB-Hugh Grant Circle & Virginia Pk. Recon. XG-117MA | 2 | DESIGN | Dec 2016 | Mar 2018 | Dec 2016 | Dec 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HGCVPR | PWOB-Hugh Grant Circle & Virginia Pk. Recon. XG-117MA | 3 | BID/ REGISTER CONTRACT | Mar 2018 | Dec 2018 | Dec 2017 | Sep 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HGCVPR | PWOB-Hugh Grant Circle & Virginia Pk. Recon. XG-117MA | 4 | CONSTRUCTION | Dec 2018 | Dec 2020 | Sep 2018 | Sep 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HGCVPR | PWOB-Hugh Grant Circle & Virginia Pk. Recon. XG-117MA | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2020 | Dec 2021 | Sep 2019 | Jun 2030
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HUNTPT | Hunts Point Rec Ctr Gym floor & stage recon CNYG-420M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HUNTPT | Hunts Point Rec Ctr Gym floor & stage recon CNYG-420M | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HUNTPT | Hunts Point Rec Ctr Gym floor & stage recon CNYG-420M | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HUNTPT | Hunts Point Rec Ctr Gym floor & stage recon CNYG-420M | 4 | CONSTRUCTION | Sep 2021 | Mar 2023 | Sep 2021 | Mar 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HUNTPT | Hunts Point Rec Ctr Gym floor & stage recon CNYG-420M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Mar 2024 | Mar 2023 | Jun 2029
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HVMRCS | Havemeyer Playground PRB | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HVMRCS | Havemeyer Playground PRB | 2 | DESIGN | Dec 2018 | Dec 2019 | Jan 2019 | Dec 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HVMRCS | Havemeyer Playground PRB | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Jan 2020 | Sep 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HVMRCS | Havemeyer Playground PRB | 4 | CONSTRUCTION | Sep 2020 | Mar 2022 | Sep 2020 | Mar 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HVMRCS | Havemeyer Playground PRB | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Mar 2023 | Mar 2022 | Mar 2029
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1JASPBB | JASPER BASEBALL STADIUM | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1JASPBB | JASPER BASEBALL STADIUM | 2 | DESIGN | Dec 2019 | Dec 2021 | Dec 2019 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1JASPBB | JASPER BASEBALL STADIUM | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1JASPBB | JASPER BASEBALL STADIUM | 4 | CONSTRUCTION | Sep 2022 | Sep 2024 | Sep 2022 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1JASPBB | JASPER BASEBALL STADIUM | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1LZDARF | Lozada Plgd public restroom bldg Roof Recon CNYG-1018MA1 | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1LZDARF | Lozada Plgd public restroom bldg Roof Recon CNYG-1018MA1 | 2 | DESIGN | Dec 2022 | Dec 2024 | Dec 2022 | Dec 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1LZDARF | Lozada Plgd public restroom bldg Roof Recon CNYG-1018MA1 | 3 | BID/ REGISTER CONTRACT | Dec 2024 | Sep 2025 | Dec 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1LZDARF | Lozada Plgd public restroom bldg Roof Recon CNYG-1018MA1 | 4 | CONSTRUCTION | Sep 2025 | Sep 2028 | Sep 2025 | Sep 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1LZDARF | Lozada Plgd public restroom bldg Roof Recon CNYG-1018MA1 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2028 | Sep 2030 | Sep 2028 | Sep 2030
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1MBRKCS | Millbrook Playground public restroom bldg Recon CNYG-522M | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1MBRKCS | Millbrook Playground public restroom bldg Recon CNYG-522M | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1MBRKCS | Millbrook Playground public restroom bldg Recon CNYG-522M | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1MBRKCS | Millbrook Playground public restroom bldg Recon CNYG-522M | 4 | CONSTRUCTION | Sep 2023 | Mar 2025 | Sep 2023 | Mar 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1MBRKCS | Millbrook Playground public restroom bldg Recon CNYG-522M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Mar 2026 | Mar 2025 | Mar 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1MELRO | Melrose Commons URA Site 62 Park Development (X350-119M) | 1 | DEVELOP SCOPE | Oct 2015 | Apr 2016 | Oct 2015 | Apr 2016
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1MELRO | Melrose Commons URA Site 62 Park Development (X350-119M) | 2 | DESIGN | Apr 2016 | Jul 2017 | Apr 2016 | Jul 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1MELRO | Melrose Commons URA Site 62 Park Development (X350-119M) | 3 | BID/ REGISTER CONTRACT | Jul 2017 | Apr 2018 | Jul 2017 | Apr 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1MELRO | Melrose Commons URA Site 62 Park Development (X350-119M) | 4 | CONSTRUCTION | Apr 2018 | Apr 2019 | Apr 2018 | Apr 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1MELRO | Melrose Commons URA Site 62 Park Development (X350-119M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2019 | Apr 2020 | Apr 2019 | Jun 2030
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1OWEND2 | OWEN F. DOLEN PK GOLDEN AGE CTR X016-114M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2013
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1OWEND2 | OWEN F. DOLEN PK GOLDEN AGE CTR X016-114M | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2013 | Jan 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1OWEND2 | OWEN F. DOLEN PK GOLDEN AGE CTR X016-114M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2017 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1OWEND2 | OWEN F. DOLEN PK GOLDEN AGE CTR X016-114M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Apr 2019 | Aug 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1OWEND2 | OWEN F. DOLEN PK GOLDEN AGE CTR X016-114M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Aug 2020 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1OWEND3 | OWEN DOLEN RECREATION CENTER - X016-118M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1OWEND3 | OWEN DOLEN RECREATION CENTER - X016-118M | 2 | DESIGN | Dec 2017 | Dec 2019 | Dec 2017 | Dec 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1OWEND3 | OWEN DOLEN RECREATION CENTER - X016-118M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1OWEND3 | OWEN DOLEN RECREATION CENTER - X016-118M | 4 | CONSTRUCTION | Sep 2020 | Sep 2022 | Sep 2020 | Sep 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1OWEND3 | OWEN DOLEN RECREATION CENTER - X016-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2029
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PAVBRX | Bronx Pavement Reconstruction (SoGR) XG-419M | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PAVBRX | Bronx Pavement Reconstruction (SoGR) XG-419M | 2 | DESIGN | Dec 2019 | Jun 2021 | Dec 2019 | Jun 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PAVBRX | Bronx Pavement Reconstruction (SoGR) XG-419M | 3 | BID/ REGISTER CONTRACT | Jun 2021 | Mar 2022 | Jun 2021 | Mar 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PAVBRX | Bronx Pavement Reconstruction (SoGR) XG-419M | 4 | CONSTRUCTION | Mar 2022 | Sep 2023 | Mar 2022 | Sep 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PAVBRX | Bronx Pavement Reconstruction (SoGR) XG-419M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PAVMOS | Mosholu Parkway Greenway Pavement Reconstruction (SoGR) | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2018 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PAVMOS | Mosholu Parkway Greenway Pavement Reconstruction (SoGR) | 2 | DESIGN | Dec 2019 | Dec 2021 | Dec 2019 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PAVMOS | Mosholu Parkway Greenway Pavement Reconstruction (SoGR) | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PAVMOS | Mosholu Parkway Greenway Pavement Reconstruction (SoGR) | 4 | CONSTRUCTION | Sep 2022 | Sep 2024 | Sep 2022 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PAVMOS | Mosholu Parkway Greenway Pavement Reconstruction (SoGR) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PBEAST | Bronx Park East - Ped Access Ramp | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PBEAST | Bronx Park East - Ped Access Ramp | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PBEAST | Bronx Park East - Ped Access Ramp | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PBEAST | Bronx Park East - Ped Access Ramp | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PBEAST | Bronx Park East - Ped Access Ramp | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PDSMRC | PDF -St. Mary's Rec Ctr RC X045-115M | 1 | DEVELOP SCOPE | May 2014 | Aug 2014 | May 2017 | Aug 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PDSMRC | PDF -St. Mary's Rec Ctr RC X045-115M | 2 | DESIGN | Aug 2014 | Nov 2014 | Aug 2017 | Sep 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PDSMRC | PDF -St. Mary's Rec Ctr RC X045-115M | 3 | BID/ REGISTER CONTRACT | Nov 2014 | Feb 2015 | Sep 2020 | Dec 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PDSMRC | PDF -St. Mary's Rec Ctr RC X045-115M | 4 | CONSTRUCTION | Feb 2015 | Feb 2016 | Dec 2020 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PDSMRC | PDF -St. Mary's Rec Ctr RC X045-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2016 | Feb 2017 | Dec 2021 | Aug 2029
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELBRV | Pelham parkway -connection to Bronx river greenwayX002-211M | 1 | DEVELOP SCOPE | Jul 2008 | Sep 2008 | Jul 2008 | Sep 2011
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELBRV | Pelham parkway -connection to Bronx river greenwayX002-211M | 2 | DESIGN | Sep 2008 | Dec 2008 | Sep 2011 | Dec 2012
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELBRV | Pelham parkway -connection to Bronx river greenwayX002-211M | 3 | BID/ REGISTER CONTRACT | Dec 2008 | Mar 2009 | Dec 2012 | Dec 2013
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELBRV | Pelham parkway -connection to Bronx river greenwayX002-211M | 4 | CONSTRUCTION | Mar 2009 | Mar 2010 | Dec 2013 | Dec 2014
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELBRV | Pelham parkway -connection to Bronx river greenwayX002-211M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2010 | Mar 2011 | Dec 2014 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELFTR | Pelham Bay Park- Forest Tree Replace. Ph. II | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELFTR | Pelham Bay Park- Forest Tree Replace. Ph. II | 2 | DESIGN | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELFTR | Pelham Bay Park- Forest Tree Replace. Ph. II | 3 | BID/ REGISTER CONTRACT | Sep 2022 | Jun 2023 | Sep 2022 | Jun 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELFTR | Pelham Bay Park- Forest Tree Replace. Ph. II | 4 | CONSTRUCTION | Jun 2023 | Dec 2025 | Jun 2023 | Dec 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELFTR | Pelham Bay Park- Forest Tree Replace. Ph. II | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2025 | Dec 2027 | Dec 2025 | Dec 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELHAM | Pelham Parkway Malls-Plaza"A" | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELHAM | Pelham Parkway Malls-Plaza"A" | 2 | DESIGN | Dec 2021 | Dec 2022 | Dec 2021 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELHAM | Pelham Parkway Malls-Plaza"A" | 3 | BID/ REGISTER CONTRACT | Dec 2022 | Sep 2023 | Dec 2022 | Sep 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELHAM | Pelham Parkway Malls-Plaza"A" | 4 | CONSTRUCTION | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELHAM | Pelham Parkway Malls-Plaza"A" | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Jun 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PNYFL5 | PlaNYC- Coop City ballfield - Irrigation Install X251-116M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2013
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PNYFL5 | PlaNYC- Coop City ballfield - Irrigation Install X251-116M | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PNYFL5 | PlaNYC- Coop City ballfield - Irrigation Install X251-116M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2013 | Mar 2014
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PNYFL5 | PlaNYC- Coop City ballfield - Irrigation Install X251-116M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2015
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PNYFL5 | PlaNYC- Coop City ballfield - Irrigation Install X251-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2015 | Jun 2030
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PNYT18 | FY14 Street Tree Planting, Bronx CBs 7-12, PlaNYC (XG-713M) | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2013 | Sep 2013
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PNYT18 | FY14 Street Tree Planting, Bronx CBs 7-12, PlaNYC (XG-713M) | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2013 | Dec 2013
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PNYT18 | FY14 Street Tree Planting, Bronx CBs 7-12, PlaNYC (XG-713M) | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2013 | Mar 2014
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PNYT18 | FY14 Street Tree Planting, Bronx CBs 7-12, PlaNYC (XG-713M) | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2014 | Mar 2015
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PNYT18 | FY14 Street Tree Planting, Bronx CBs 7-12, PlaNYC (XG-713M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2015 | Jun 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1POECOT | POE COTTAGE - INSTALLATION OF ROOF & EXTERIOR RENOVATIONS | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1POECOT | POE COTTAGE - INSTALLATION OF ROOF & EXTERIOR RENOVATIONS | 2 | DESIGN | Dec 2019 | Dec 2021 | Dec 2019 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1POECOT | POE COTTAGE - INSTALLATION OF ROOF & EXTERIOR RENOVATIONS | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1POECOT | POE COTTAGE - INSTALLATION OF ROOF & EXTERIOR RENOVATIONS | 4 | CONSTRUCTION | Sep 2022 | Sep 2024 | Sep 2022 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1POECOT | POE COTTAGE - INSTALLATION OF ROOF & EXTERIOR RENOVATIONS | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PTSNPK | Patterson Park (X155-116M | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Sep 2015
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PTSNPK | Patterson Park (X155-116M | 2 | DESIGN | Sep 2015 | Dec 2015 | Sep 2015 | Dec 2015
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PTSNPK | Patterson Park (X155-116M | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Dec 2015 | Mar 2016
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PTSNPK | Patterson Park (X155-116M | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Mar 2016 | Mar 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PTSNPK | Patterson Park (X155-116M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Mar 2017 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PUGSLY | PUGSLEY CREEK & SOUNDVIEW PARKS INSTALLATION OF BLUE LIGHT | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Sep 2014 | Mar 2015
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PUGSLY | PUGSLEY CREEK & SOUNDVIEW PARKS INSTALLATION OF BLUE LIGHT | 2 | DESIGN | Dec 2017 | Dec 2018 | Mar 2015 | Mar 2016
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PUGSLY | PUGSLEY CREEK & SOUNDVIEW PARKS INSTALLATION OF BLUE LIGHT | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Mar 2016 | Dec 2016
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PUGSLY | PUGSLEY CREEK & SOUNDVIEW PARKS INSTALLATION OF BLUE LIGHT | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Dec 2016 | Dec 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PUGSLY | PUGSLEY CREEK & SOUNDVIEW PARKS INSTALLATION OF BLUE LIGHT | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Dec 2017 | Jun 2029
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RNQ22A | Ranaqua Facade Safety Repairs | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RNQ22A | Ranaqua Facade Safety Repairs | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RNQ22A | Ranaqua Facade Safety Repairs | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RNQ22A | Ranaqua Facade Safety Repairs | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RNQ22A | Ranaqua Facade Safety Repairs | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RNQARF | Ranaqua Roof Reconstruction | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RNQARF | Ranaqua Roof Reconstruction | 2 | DESIGN | Dec 2018 | Dec 2019 | Oct 2021 | Oct 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RNQARF | Ranaqua Roof Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Oct 2022 | Jul 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RNQARF | Ranaqua Roof Reconstruction | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Jul 2023 | Jun 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RNQARF | Ranaqua Roof Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Jul 2024 | Jun 2029
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RNQRMP | Reconstruction of Ranaqua M&O Storehouse Ramp - X002-220M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Apr 2021 | Oct 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RNQRMP | Reconstruction of Ranaqua M&O Storehouse Ramp - X002-220M | 2 | DESIGN | Dec 2018 | Dec 2019 | Oct 2021 | Oct 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RNQRMP | Reconstruction of Ranaqua M&O Storehouse Ramp - X002-220M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Oct 2022 | Jul 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RNQRMP | Reconstruction of Ranaqua M&O Storehouse Ramp - X002-220M | 4 | CONSTRUCTION | Sep 2020 | Sep 2021 | Jul 2023 | Jun 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RNQRMP | Reconstruction of Ranaqua M&O Storehouse Ramp - X002-220M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2021 | Sep 2022 | Jul 2024 | Jun 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1SPACET | SpaceTime Playgroun Reconstruction (X221-121M) | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1SPACET | SpaceTime Playgroun Reconstruction (X221-121M) | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1SPACET | SpaceTime Playgroun Reconstruction (X221-121M) | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1SPACET | SpaceTime Playgroun Reconstruction (X221-121M) | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1SPACET | SpaceTime Playgroun Reconstruction (X221-121M) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1SPC21A | Pelham Bay Park Forest Tree Replacement | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1SPC21A | Pelham Bay Park Forest Tree Replacement | 2 | DESIGN | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1SPC21A | Pelham Bay Park Forest Tree Replacement | 3 | BID/ REGISTER CONTRACT | Sep 2022 | Jun 2023 | Sep 2022 | Jun 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1SPC21A | Pelham Bay Park Forest Tree Replacement | 4 | CONSTRUCTION | Jun 2023 | Dec 2025 | Jun 2023 | Dec 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1SPC21A | Pelham Bay Park Forest Tree Replacement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2025 | Dec 2027 | Dec 2025 | Dec 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1STFPEL | Synthetic Turf Field Reconstruction at Pelham Bay | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Apr 2021 | Oct 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1STFPEL | Synthetic Turf Field Reconstruction at Pelham Bay | 2 | DESIGN | Dec 2019 | Dec 2020 | Oct 2021 | Oct 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1STFPEL | Synthetic Turf Field Reconstruction at Pelham Bay | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Oct 2022 | Jul 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1STFPEL | Synthetic Turf Field Reconstruction at Pelham Bay | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Jul 2023 | Jun 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1STFPEL | Synthetic Turf Field Reconstruction at Pelham Bay | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Jul 2024 | Jun 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1STR21A | Bronx Street Tree Planting - XG-321M | 2 | DESIGN | Dec 2020 | Jun 2021 | Dec 2025 | Jun 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1STR21A | Bronx Street Tree Planting - XG-321M | 3 | BID/ REGISTER CONTRACT | Jun 2021 | Mar 2022 | Jun 2026 | Mar 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1STR21A | Bronx Street Tree Planting - XG-321M | 4 | CONSTRUCTION | Mar 2022 | Mar 2023 | Mar 2027 | Mar 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1STR21A | Bronx Street Tree Planting - XG-321M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Mar 2025 | Mar 2028 | Mar 2030
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE23A | Bronx CB 1-4 Street Tree Planting FY23 | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE23A | Bronx CB 1-4 Street Tree Planting FY23 | 2 | DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE23A | Bronx CB 1-4 Street Tree Planting FY23 | 3 | BID/ REGISTER CONTRACT | Jun 2023 | Mar 2024 | Jun 2023 | Mar 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE23A | Bronx CB 1-4 Street Tree Planting FY23 | 4 | CONSTRUCTION | Mar 2024 | Sep 2025 | Mar 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE23A | Bronx CB 1-4 Street Tree Planting FY23 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE23B | Bronx CB 9-10 Street Tree Planting FY23 | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE23B | Bronx CB 9-10 Street Tree Planting FY23 | 2 | DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE23B | Bronx CB 9-10 Street Tree Planting FY23 | 3 | BID/ REGISTER CONTRACT | Jun 2023 | Mar 2024 | Jun 2023 | Mar 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE23B | Bronx CB 9-10 Street Tree Planting FY23 | 4 | CONSTRUCTION | Mar 2024 | Sep 2025 | Mar 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE23B | Bronx CB 9-10 Street Tree Planting FY23 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TREL21 | FY21 Street Trees BX CB's5-8,11,12 (3Y) | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TREL21 | FY21 Street Trees BX CB's5-8,11,12 (3Y) | 2 | DESIGN | Dec 2019 | Jun 2021 | Dec 2019 | Jun 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TREL21 | FY21 Street Trees BX CB's5-8,11,12 (3Y) | 3 | BID/ REGISTER CONTRACT | Jun 2021 | Mar 2022 | Jun 2021 | Mar 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TREL21 | FY21 Street Trees BX CB's5-8,11,12 (3Y) | 4 | CONSTRUCTION | Mar 2022 | Mar 2025 | Mar 2022 | Mar 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TREL21 | FY21 Street Trees BX CB's5-8,11,12 (3Y) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Mar 2027 | Mar 2025 | Mar 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TREP22 | Bronx ParkTree Planting FY22-CB, XG-122M | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TREP22 | Bronx ParkTree Planting FY22-CB, XG-122M | 2 | DESIGN | Dec 2021 | Jun 2022 | Dec 2021 | Jun 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TREP22 | Bronx ParkTree Planting FY22-CB, XG-122M | 3 | BID/ REGISTER CONTRACT | Jun 2022 | Mar 2023 | Jun 2022 | Mar 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TREP22 | Bronx ParkTree Planting FY22-CB, XG-122M | 4 | CONSTRUCTION | Mar 2023 | Sep 2024 | Mar 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TREP22 | Bronx ParkTree Planting FY22-CB, XG-122M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Sep 2026 | Sep 2024 | Sep 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VANCPL | Van Cortlandt Pool | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VANCPL | Van Cortlandt Pool | 2 | DESIGN | Dec 2022 | Dec 2024 | Dec 2022 | Dec 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VANCPL | Van Cortlandt Pool | 3 | BID/ REGISTER CONTRACT | Dec 2024 | Sep 2025 | Dec 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VANCPL | Van Cortlandt Pool | 4 | CONSTRUCTION | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VANCPL | Van Cortlandt Pool | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Sep 2028 | Sep 2027 | Sep 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VCTURF | Van Cortlandt Park Limited Scope Syn Turf & Track Recon | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VCTURF | Van Cortlandt Park Limited Scope Syn Turf & Track Recon | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VCTURF | Van Cortlandt Park Limited Scope Syn Turf & Track Recon | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VCTURF | Van Cortlandt Park Limited Scope Syn Turf & Track Recon | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VCTURF | Van Cortlandt Park Limited Scope Syn Turf & Track Recon | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Jun 2029
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VNCFTR | Van Cortlandt Park - Forest Tree Repl. Ph. I | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VNCFTR | Van Cortlandt Park - Forest Tree Repl. Ph. I | 2 | DESIGN | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VNCFTR | Van Cortlandt Park - Forest Tree Repl. Ph. I | 3 | BID/ REGISTER CONTRACT | Sep 2022 | Jun 2023 | Sep 2022 | Jun 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VNCFTR | Van Cortlandt Park - Forest Tree Repl. Ph. I | 4 | CONSTRUCTION | Jun 2023 | Dec 2025 | Jun 2023 | Dec 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VNCFTR | Van Cortlandt Park - Forest Tree Repl. Ph. I | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2025 | Dec 2027 | Dec 2025 | Dec 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WASHPK | Washington Park Basketball Court Reconstruction | 1 | DEVELOP SCOPE | Jul 2025 | Dec 2025 | Jul 2018 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WASHPK | Washington Park Basketball Court Reconstruction | 2 | DESIGN | Dec 2025 | Dec 2026 | Dec 2025 | Dec 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WASHPK | Washington Park Basketball Court Reconstruction | 3 | BID/ REGISTER CONTRACT | Dec 2026 | Sep 2027 | Dec 2026 | Sep 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WASHPK | Washington Park Basketball Court Reconstruction | 4 | CONSTRUCTION | Sep 2027 | Sep 2028 | Sep 2027 | Sep 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WASHPK | Washington Park Basketball Court Reconstruction | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2028 | Sep 2029 | Sep 2028 | Sep 2029
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WDLNCS | Woodlawn Playground PRB X092-119M | 1 | DEVELOP SCOPE | Jul 2018 | Dec 2018 | Jul 2018 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WDLNCS | Woodlawn Playground PRB X092-119M | 2 | DESIGN | Dec 2018 | Dec 2019 | Dec 2018 | Dec 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WDLNCS | Woodlawn Playground PRB X092-119M | 3 | BID/ REGISTER CONTRACT | Dec 2019 | Sep 2020 | Dec 2019 | Sep 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WDLNCS | Woodlawn Playground PRB X092-119M | 4 | CONSTRUCTION | Sep 2020 | Mar 2022 | Sep 2020 | Mar 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WDLNCS | Woodlawn Playground PRB X092-119M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Mar 2023 | Mar 2022 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WDLNSS | Woodlawn Plgd- Recon of Spray Shower X092-118M | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2018 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WDLNSS | Woodlawn Plgd- Recon of Spray Shower X092-118M | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2018
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WDLNSS | Woodlawn Plgd- Recon of Spray Shower X092-118M | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2018 | Sep 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WDLNSS | Woodlawn Plgd- Recon of Spray Shower X092-118M | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2019 | Sep 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WDLNSS | Woodlawn Plgd- Recon of Spray Shower X092-118M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2020 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WKFLDC | Wakefield PLGD public restroom CNYG-1922M | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WKFLDC | Wakefield PLGD public restroom CNYG-1922M | 2 | DESIGN | Dec 2022 | Dec 2024 | Dec 2022 | Dec 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WKFLDC | Wakefield PLGD public restroom CNYG-1922M | 3 | BID/ REGISTER CONTRACT | Dec 2024 | Sep 2025 | Dec 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WKFLDC | Wakefield PLGD public restroom CNYG-1922M | 4 | CONSTRUCTION | Sep 2025 | Sep 2027 | Sep 2025 | Sep 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WKFLDC | Wakefield PLGD public restroom CNYG-1922M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Jun 2030 | Sep 2027 | Jun 2030
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WKFLRF | Wakefield Plgd public restroom bldg Roof Recon CNYG-1018MA1 | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WKFLRF | Wakefield Plgd public restroom bldg Roof Recon CNYG-1018MA1 | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WKFLRF | Wakefield Plgd public restroom bldg Roof Recon CNYG-1018MA1 | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WKFLRF | Wakefield Plgd public restroom bldg Roof Recon CNYG-1018MA1 | 4 | CONSTRUCTION | Sep 2024 | Sep 2025 | Sep 2024 | Sep 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WKFLRF | Wakefield Plgd public restroom bldg Roof Recon CNYG-1018MA1 | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2025 | Sep 2026 | Sep 2025 | Sep 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WPSOTO | Sotomayor Houses - Construction of Open Space | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WPSOTO | Sotomayor Houses - Construction of Open Space | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WPSOTO | Sotomayor Houses - Construction of Open Space | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WPSOTO | Sotomayor Houses - Construction of Open Space | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WPSOTO | Sotomayor Houses - Construction of Open Space | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WPWATS | Watson Houses - Construction of Open Space | 1 | DEVELOP SCOPE | Jul 2019 | Dec 2019 | Jul 2019 | Dec 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WPWATS | Watson Houses - Construction of Open Space | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WPWATS | Watson Houses - Construction of Open Space | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WPWATS | Watson Houses - Construction of Open Space | 4 | CONSTRUCTION | Sep 2021 | Sep 2022 | Sep 2021 | Sep 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WPWATS | Watson Houses - Construction of Open Space | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2022 | Sep 2023 | Sep 2022 | Jun 2029
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-6ENVLP1 | $1 CW Envelope Contract | 1 | DEVELOP SCOPE | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-6ENVLP1 | $1 CW Envelope Contract | 2 | DESIGN | Feb 2024 | Feb 2025 | Feb 2024 | Feb 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-6ENVLP1 | $1 CW Envelope Contract | 3 | BID/ REGISTER CONTRACT | Feb 2025 | Nov 2025 | Feb 2025 | Nov 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-6ENVLP1 | $1 CW Envelope Contract | 4 | CONSTRUCTION | Nov 2025 | Nov 2026 | Nov 2025 | Nov 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-6ENVLP1 | $1 CW Envelope Contract | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2026 | Nov 2027 | Nov 2026 | Nov 2027
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-06 | SANDY - Ferry Point Park Type 3 X126-115M | 1 | DEVELOP SCOPE | Jul 2013 | Sep 2013 | Jul 2010 | Sep 2010
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-06 | SANDY - Ferry Point Park Type 3 X126-115M | 2 | DESIGN | Sep 2013 | Dec 2013 | Sep 2010 | Dec 2010
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-06 | SANDY - Ferry Point Park Type 3 X126-115M | 3 | BID/ REGISTER CONTRACT | Dec 2013 | Mar 2014 | Dec 2010 | Mar 2011
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-06 | SANDY - Ferry Point Park Type 3 X126-115M | 4 | CONSTRUCTION | Mar 2014 | Mar 2015 | Mar 2011 | Mar 2012
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-06 | SANDY - Ferry Point Park Type 3 X126-115M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Mar 2016 | Mar 2012 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-10 | Hammond Cove Marina X310-117M | 1 | DEVELOP SCOPE | Jul 2016 | Dec 2016 | Jul 2014 | Dec 2014
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-10 | Hammond Cove Marina X310-117M | 2 | DESIGN | Dec 2016 | Mar 2018 | Dec 2014 | Dec 2015
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-10 | Hammond Cove Marina X310-117M | 3 | BID/ REGISTER CONTRACT | Mar 2018 | Dec 2018 | Dec 2015 | Sep 2016
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-10 | Hammond Cove Marina X310-117M | 4 | CONSTRUCTION | Dec 2018 | Dec 2020 | Sep 2016 | Sep 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-10 | Hammond Cove Marina X310-117M | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2020 | Dec 2021 | Sep 2017 | Sep 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-11 | Pelham Bay Landfill | 1 | DEVELOP SCOPE | Jul 2017 | Dec 2017 | Jul 2017 | Dec 2017
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-11 | Pelham Bay Landfill | 2 | DESIGN | Dec 2017 | Dec 2018 | Dec 2017 | Dec 2019
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-11 | Pelham Bay Landfill | 3 | BID/ REGISTER CONTRACT | Dec 2018 | Sep 2019 | Dec 2019 | Sep 2020
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-11 | Pelham Bay Landfill | 4 | CONSTRUCTION | Sep 2019 | Sep 2020 | Sep 2020 | Sep 2022
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-11 | Pelham Bay Landfill | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2020 | Sep 2021 | Sep 2022 | Jun 2028
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-12 | Hart Island Shoreline Restore. (FEMA 428) | 1 | DEVELOP SCOPE | Jan 2023 | Jun 2023 | Jan 2023 | Jun 2023
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-12 | Hart Island Shoreline Restore. (FEMA 428) | 2 | DESIGN | Jun 2023 | Jun 2025 | Jun 2023 | Jun 2025
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-12 | Hart Island Shoreline Restore. (FEMA 428) | 3 | BID/ REGISTER CONTRACT | Jun 2025 | Mar 2026 | Jun 2025 | Mar 2026
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-12 | Hart Island Shoreline Restore. (FEMA 428) | 4 | CONSTRUCTION | Mar 2026 | Mar 2029 | Mar 2026 | Mar 2029
20231026 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-12 | Hart Island Shoreline Restore. (FEMA 428) | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2029 | Mar 2031 | Mar 2029 | Mar 2031
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-X | Boro Based Jails New Bronx Detention Facility DesignBuild | 1 | DEVELOP SCOPE | Sep 2021 | Nov 2021 | Sep 2021 | Nov 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-X | Boro Based Jails New Bronx Detention Facility DesignBuild | 2 | PRELIMINARY DESIGN | Nov 2021 | Mar 2022 | Nov 2021 | Mar 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-X | Boro Based Jails New Bronx Detention Facility DesignBuild | 3 | FINAL DESIGN | Mar 2022 | Sep 2022 | Mar 2022 | Sep 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-X | Boro Based Jails New Bronx Detention Facility DesignBuild | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-X | Boro Based Jails New Bronx Detention Facility DesignBuild | 5 | CONSTRUCTION TO 25% | Dec 2022 | Apr 2023 | Dec 2022 | Apr 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-X | Boro Based Jails New Bronx Detention Facility DesignBuild | 6 | CONSTRUCTION TO 50% | Apr 2023 | Aug 2023 | Apr 2023 | Aug 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-X | Boro Based Jails New Bronx Detention Facility DesignBuild | 7 | CONSTRUCTION TO 75% | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-X | Boro Based Jails New Bronx Detention Facility DesignBuild | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2023 | Mar 2024 | Dec 2023 | Mar 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-X | Boro Based Jails New Bronx Detention Facility DesignBuild | 9 | SUBSTANTIAL COMPLETION | Mar 2024 | May 2024 | Mar 2024 | May 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-X | Boro Based Jails New Bronx Detention Facility DesignBuild | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Jun 2029 | May 2024 | Jun 2029
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75EWAMKC | Emergency Work for AMKC | 1 | PROJECT START | Sep 2021 | Sep 2021 | Sep 2021 | Sep 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75EWAMKC | Emergency Work for AMKC | 2 | DESIGN START | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75EWAMKC | Emergency Work for AMKC | 3 | DESIGN COMPLETION | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75EWAMKC | Emergency Work for AMKC | 4 | CONSTRUCTION START | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75EWAMKC | Emergency Work for AMKC | 5 | CONSTRUCTION COMPLETION | Oct 2021 | Aug 2023 | Oct 2021 | Aug 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75EWGRVC | Emergency Work for GRVC | 1 | PROJECT START | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75EWGRVC | Emergency Work for GRVC | 2 | DESIGN START | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75EWGRVC | Emergency Work for GRVC | 3 | DESIGN COMPLETION | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75EWGRVC | Emergency Work for GRVC | 4 | CONSTRUCTION START | Oct 2021 | Nov 2021 | Oct 2021 | Nov 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75EWGRVC | Emergency Work for GRVC | 5 | CONSTRUCTION COMPLETION | Nov 2021 | Aug 2022 | Nov 2021 | Aug 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75EWNIC | Emergency Work for NIC | 1 | PROJECT START | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75EWNIC | Emergency Work for NIC | 2 | DESIGN START | Jul 2021 | Jul 2021 | Jul 2021 | Jul 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75EWNIC | Emergency Work for NIC | 3 | DESIGN COMPLETION | Aug 2021 | Aug 2021 | Aug 2021 | May 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75EWNIC | Emergency Work for NIC | 4 | CONSTRUCTION START | Aug 2021 | Aug 2021 | May 2022 | Mar 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75EWNIC | Emergency Work for NIC | 5 | CONSTRUCTION COMPLETION | Aug 2021 | Aug 2021 | Mar 2023 | Jun 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75EWRMSC | Emergency Work for RMSC | 1 | PROJECT START | Sep 2021 | Sep 2021 | Sep 2021 | Sep 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75EWRMSC | Emergency Work for RMSC | 2 | DESIGN START | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75EWRMSC | Emergency Work for RMSC | 3 | DESIGN COMPLETION | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75EWRMSC | Emergency Work for RMSC | 4 | CONSTRUCTION START | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75EWRMSC | Emergency Work for RMSC | 5 | CONSTRUCTION COMPLETION | Oct 2021 | Aug 2023 | Oct 2021 | Jun 2031
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75EWRNDC | Emergency Work for RNDC | 1 | PROJECT START | Sep 2021 | Sep 2021 | Sep 2021 | Sep 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75EWRNDC | Emergency Work for RNDC | 2 | DESIGN START | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75EWRNDC | Emergency Work for RNDC | 3 | DESIGN COMPLETION | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75EWRNDC | Emergency Work for RNDC | 4 | CONSTRUCTION START | Oct 2021 | Oct 2021 | Oct 2021 | Oct 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75EWRNDC | Emergency Work for RNDC | 5 | CONSTRUCTION COMPLETION | Oct 2021 | Aug 2023 | Oct 2021 | Aug 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO290BCHJ | 265 E161 St.- BCHJ-Post Construction Work | 1 | PROJECT START | Nov 2013 | Nov 2013 | Nov 2013 | Nov 2013
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO290BCHJ | 265 E161 St.- BCHJ-Post Construction Work | 2 | DESIGN START | Feb 2014 | Feb 2014 | Feb 2014 | Feb 2014
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO290BCHJ | 265 E161 St.- BCHJ-Post Construction Work | 3 | DESIGN COMPLETION | Dec 2014 | Dec 2014 | Dec 2014 | Dec 2014
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO290BCHJ | 265 E161 St.- BCHJ-Post Construction Work | 4 | CONSTRUCTION START | Apr 2015 | May 2015 | Apr 2015 | May 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO290BCHJ | 265 E161 St.- BCHJ-Post Construction Work | 5 | CONSTRUCTION COMPLETION | May 2020 | May 2020 | May 2020 | Mar 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293LL11 | 851 GRAND CONCOURSE - FACADE RECONSTRUCTION | 1 | DEVELOP SCOPE | Mar 2021 | May 2021 | Mar 2021 | May 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293LL11 | 851 GRAND CONCOURSE - FACADE RECONSTRUCTION | 2 | PRELIMINARY DESIGN | May 2021 | Sep 2021 | May 2021 | Sep 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293LL11 | 851 GRAND CONCOURSE - FACADE RECONSTRUCTION | 3 | FINAL DESIGN | Sep 2021 | Mar 2022 | Sep 2021 | Mar 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293LL11 | 851 GRAND CONCOURSE - FACADE RECONSTRUCTION | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2022 | Jun 2022 | Mar 2022 | Jun 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293LL11 | 851 GRAND CONCOURSE - FACADE RECONSTRUCTION | 5 | CONSTRUCTION TO 25% | Jun 2022 | Oct 2022 | Jun 2022 | Oct 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293LL11 | 851 GRAND CONCOURSE - FACADE RECONSTRUCTION | 6 | CONSTRUCTION TO 50% | Oct 2022 | Feb 2023 | Oct 2022 | Feb 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293LL11 | 851 GRAND CONCOURSE - FACADE RECONSTRUCTION | 7 | CONSTRUCTION TO 75% | Feb 2023 | Jun 2023 | Feb 2023 | Jun 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293LL11 | 851 GRAND CONCOURSE - FACADE RECONSTRUCTION | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293LL11 | 851 GRAND CONCOURSE - FACADE RECONSTRUCTION | 9 | SUBSTANTIAL COMPLETION | Sep 2023 | Nov 2023 | Sep 2023 | Nov 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293LL11 | 851 GRAND CONCOURSE - FACADE RECONSTRUCTION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2023 | Dec 2023 | Nov 2023 | Jun 2031
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293SP | 851 GRAND CONCOURSE - FIRE PROTECTION/SPRINKLERS | 1 | DEVELOP SCOPE | Feb 2017 | May 2017 | Feb 2017 | May 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293SP | 851 GRAND CONCOURSE - FIRE PROTECTION/SPRINKLERS | 2 | PRELIMINARY DESIGN | May 2017 | Aug 2017 | May 2017 | Aug 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293SP | 851 GRAND CONCOURSE - FIRE PROTECTION/SPRINKLERS | 3 | FINAL DESIGN | Aug 2017 | Feb 2018 | Aug 2017 | Dec 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293SP | 851 GRAND CONCOURSE - FIRE PROTECTION/SPRINKLERS | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2018 | May 2018 | Dec 2019 | Mar 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293SP | 851 GRAND CONCOURSE - FIRE PROTECTION/SPRINKLERS | 5 | CONSTRUCTION TO 25% | May 2018 | Sep 2018 | Mar 2020 | Oct 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293SP | 851 GRAND CONCOURSE - FIRE PROTECTION/SPRINKLERS | 6 | CONSTRUCTION TO 50% | Sep 2018 | Jan 2019 | Oct 2021 | Feb 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293SP | 851 GRAND CONCOURSE - FIRE PROTECTION/SPRINKLERS | 7 | CONSTRUCTION TO 75% | Jan 2019 | May 2019 | Feb 2022 | Jun 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293SP | 851 GRAND CONCOURSE - FIRE PROTECTION/SPRINKLERS | 8 | ORIGINAL EQUIP & FURNISHING | May 2019 | Aug 2019 | Jun 2022 | Aug 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293SP | 851 GRAND CONCOURSE - FIRE PROTECTION/SPRINKLERS | 9 | SUBSTANTIAL COMPLETION | Aug 2019 | Oct 2019 | Aug 2022 | Sep 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293SP | 851 GRAND CONCOURSE - FIRE PROTECTION/SPRINKLERS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2019 | Nov 2019 | Sep 2027 | Oct 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO294RF | 215 E161 ST.- ROOF | 1 | DEVELOP SCOPE | Feb 2022 | May 2022 | Feb 2022 | May 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO294RF | 215 E161 ST.- ROOF | 2 | PRELIMINARY DESIGN | May 2022 | Aug 2022 | May 2022 | Aug 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO294RF | 215 E161 ST.- ROOF | 3 | FINAL DESIGN | Aug 2022 | Feb 2023 | Aug 2022 | Feb 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO294RF | 215 E161 ST.- ROOF | 4 | BID AWARD AND REGISTER CONTRCT | Feb 2023 | May 2023 | Feb 2023 | May 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO294RF | 215 E161 ST.- ROOF | 5 | CONSTRUCTION TO 25% | May 2023 | Sep 2023 | May 2023 | Sep 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO294RF | 215 E161 ST.- ROOF | 6 | CONSTRUCTION TO 50% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO294RF | 215 E161 ST.- ROOF | 7 | CONSTRUCTION TO 75% | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO294RF | 215 E161 ST.- ROOF | 8 | ORIGINAL EQUIP & FURNISHING | May 2024 | Aug 2024 | May 2024 | Aug 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO294RF | 215 E161 ST.- ROOF | 9 | SUBSTANTIAL COMPLETION | Aug 2024 | Oct 2024 | Aug 2024 | Oct 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO294RF | 215 E161 ST.- ROOF | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2024 | Nov 2024 | Oct 2024 | Nov 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO295EV | 1118 GRAND CONCOURSE - ELEVATORS | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Aug 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO295EV | 1118 GRAND CONCOURSE - ELEVATORS | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO295EV | 1118 GRAND CONCOURSE - ELEVATORS | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO295EV | 1118 GRAND CONCOURSE - ELEVATORS | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO295EV | 1118 GRAND CONCOURSE - ELEVATORS | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO295EV | 1118 GRAND CONCOURSE - ELEVATORS | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2022 | May 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO295EV | 1118 GRAND CONCOURSE - ELEVATORS | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2022 | Sep 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO295EV | 1118 GRAND CONCOURSE - ELEVATORS | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO295EV | 1118 GRAND CONCOURSE - ELEVATORS | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2022 | Feb 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO295EV | 1118 GRAND CONCOURSE - ELEVATORS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Feb 2023 | May 2031
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CRO-AGS | CROTON ABOVE-GROUND STRUCTURE AND LANDSCAPING | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CRO-AGS | CROTON ABOVE-GROUND STRUCTURE AND LANDSCAPING | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CRO-AGS | CROTON ABOVE-GROUND STRUCTURE AND LANDSCAPING | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CRO-AGS | CROTON ABOVE-GROUND STRUCTURE AND LANDSCAPING | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CRO-AGS | CROTON ABOVE-GROUND STRUCTURE AND LANDSCAPING | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CRO-AGS | CROTON ABOVE-GROUND STRUCTURE AND LANDSCAPING | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CRO-AGS | CROTON ABOVE-GROUND STRUCTURE AND LANDSCAPING | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CRO-AGS | CROTON ABOVE-GROUND STRUCTURE AND LANDSCAPING | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CRO-AGS | CROTON ABOVE-GROUND STRUCTURE AND LANDSCAPING | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Jun 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CRO-AGS | CROTON ABOVE-GROUND STRUCTURE AND LANDSCAPING | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Jun 2022 | Jul 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEX23 | Reconstruction of Existing Sewers, The Bronx | 1 | DEVELOP SCOPE | Sep 2021 | Dec 2021 | Sep 2021 | Dec 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEX23 | Reconstruction of Existing Sewers, The Bronx | 2 | PRELIMINARY DESIGN | Dec 2021 | Apr 2022 | Dec 2021 | Apr 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEX23 | Reconstruction of Existing Sewers, The Bronx | 3 | FINAL DESIGN | Apr 2022 | Oct 2022 | Apr 2022 | Oct 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEX23 | Reconstruction of Existing Sewers, The Bronx | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2022 | Jan 2023 | Oct 2022 | Jan 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEX23 | Reconstruction of Existing Sewers, The Bronx | 5 | CONSTRUCTION TO 25% | Jan 2023 | May 2023 | Jan 2023 | May 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEX23 | Reconstruction of Existing Sewers, The Bronx | 6 | CONSTRUCTION TO 50% | May 2023 | Sep 2023 | May 2023 | Sep 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEX23 | Reconstruction of Existing Sewers, The Bronx | 7 | CONSTRUCTION TO 75% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEX23 | Reconstruction of Existing Sewers, The Bronx | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2024 | Apr 2024 | Jan 2024 | Apr 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEX23 | Reconstruction of Existing Sewers, The Bronx | 9 | SUBSTANTIAL COMPLETION | Apr 2024 | Jun 2024 | Apr 2024 | Jun 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEX23 | Reconstruction of Existing Sewers, The Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2024 | Jul 2024 | Jun 2024 | Jul 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEX24 | Reconstruction of Existing Sewers, The Bronx | 1 | DEVELOP SCOPE | Jun 2024 | Aug 2024 | Jun 2024 | Aug 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEX24 | Reconstruction of Existing Sewers, The Bronx | 2 | PRELIMINARY DESIGN | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEX24 | Reconstruction of Existing Sewers, The Bronx | 3 | FINAL DESIGN | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEX24 | Reconstruction of Existing Sewers, The Bronx | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEX24 | Reconstruction of Existing Sewers, The Bronx | 5 | CONSTRUCTION TO 25% | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEX24 | Reconstruction of Existing Sewers, The Bronx | 6 | CONSTRUCTION TO 50% | Jan 2026 | May 2026 | Jan 2026 | May 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEX24 | Reconstruction of Existing Sewers, The Bronx | 7 | CONSTRUCTION TO 75% | May 2026 | Sep 2026 | May 2026 | Sep 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEX24 | Reconstruction of Existing Sewers, The Bronx | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2026 | Dec 2026 | Sep 2026 | Dec 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEX24 | Reconstruction of Existing Sewers, The Bronx | 9 | SUBSTANTIAL COMPLETION | Dec 2026 | Feb 2027 | Dec 2026 | Feb 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEX24 | Reconstruction of Existing Sewers, The Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2027 | Mar 2027 | Feb 2027 | Mar 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | GI-BX-PP | GI - POROUS PAVEMENT INSTALLATIONS, BRONX | 1 | DEVELOP SCOPE | Jun 2022 | Mar 2023 | Jun 2022 | Mar 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | GI-BX-PP | GI - POROUS PAVEMENT INSTALLATIONS, BRONX | 2 | PRELIMINARY DESIGN | Mar 2023 | Mar 2024 | Mar 2023 | Mar 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | GI-BX-PP | GI - POROUS PAVEMENT INSTALLATIONS, BRONX | 3 | FINAL DESIGN | Mar 2024 | Sep 2025 | Mar 2024 | Sep 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | GI-BX-PP | GI - POROUS PAVEMENT INSTALLATIONS, BRONX | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2025 | Jun 2026 | Sep 2025 | Jun 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | GI-BX-PP | GI - POROUS PAVEMENT INSTALLATIONS, BRONX | 5 | CONSTRUCTION TO 25% | Jun 2026 | Jun 2027 | Jun 2026 | Jun 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | GI-BX-PP | GI - POROUS PAVEMENT INSTALLATIONS, BRONX | 6 | CONSTRUCTION TO 50% | Jun 2027 | May 2028 | Jun 2027 | May 2028
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | GI-BX-PP | GI - POROUS PAVEMENT INSTALLATIONS, BRONX | 7 | CONSTRUCTION TO 75% | May 2028 | May 2029 | May 2028 | May 2029
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | GI-BX-PP | GI - POROUS PAVEMENT INSTALLATIONS, BRONX | 8 | ORIGINAL EQUIP & FURNISHING | May 2029 | Feb 2030 | May 2029 | Feb 2030
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | GI-BX-PP | GI - POROUS PAVEMENT INSTALLATIONS, BRONX | 9 | SUBSTANTIAL COMPLETION | Feb 2030 | Aug 2030 | Feb 2030 | Aug 2030
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | GI-BX-PP | GI - POROUS PAVEMENT INSTALLATIONS, BRONX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2030 | Nov 2030 | Aug 2030 | Nov 2030
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-560 | RECON WM IN WEST FARMS SQUARE (HWXP2007) | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-560 | RECON WM IN WEST FARMS SQUARE (HWXP2007) | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-560 | RECON WM IN WEST FARMS SQUARE (HWXP2007) | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-560 | RECON WM IN WEST FARMS SQUARE (HWXP2007) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-560 | RECON WM IN WEST FARMS SQUARE (HWXP2007) | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-560 | RECON WM IN WEST FARMS SQUARE (HWXP2007) | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-560 | RECON WM IN WEST FARMS SQUARE (HWXP2007) | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-560 | RECON WM IN WEST FARMS SQUARE (HWXP2007) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-560 | RECON WM IN WEST FARMS SQUARE (HWXP2007) | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-560 | RECON WM IN WEST FARMS SQUARE (HWXP2007) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Jun 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-562 | New 46" Trunk Water Main in E.233rd St. Bronx | 1 | DEVELOP SCOPE | May 2012 | Aug 2012 | May 2015 | Aug 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-562 | New 46" Trunk Water Main in E.233rd St. Bronx | 2 | PRELIMINARY DESIGN | Aug 2012 | Dec 2012 | Aug 2015 | Dec 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-562 | New 46" Trunk Water Main in E.233rd St. Bronx | 3 | FINAL DESIGN | Dec 2012 | Jun 2013 | Dec 2015 | Jun 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-562 | New 46" Trunk Water Main in E.233rd St. Bronx | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2013 | Sep 2013 | Jun 2016 | Sep 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-562 | New 46" Trunk Water Main in E.233rd St. Bronx | 5 | CONSTRUCTION TO 25% | Sep 2013 | Jan 2014 | Sep 2016 | Jan 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-562 | New 46" Trunk Water Main in E.233rd St. Bronx | 6 | CONSTRUCTION TO 50% | Jan 2014 | May 2014 | Jan 2017 | May 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-562 | New 46" Trunk Water Main in E.233rd St. Bronx | 7 | CONSTRUCTION TO 75% | May 2014 | Sep 2014 | May 2017 | Sep 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-562 | New 46" Trunk Water Main in E.233rd St. Bronx | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2014 | Dec 2014 | Sep 2017 | Dec 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-562 | New 46" Trunk Water Main in E.233rd St. Bronx | 9 | SUBSTANTIAL COMPLETION | Dec 2014 | Jan 2015 | Dec 2017 | Jan 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-562 | New 46" Trunk Water Main in E.233rd St. Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2015 | Mar 2015 | Jan 2018 | Mar 2030
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-568 | New 20" sub-aqueous water main extension to Randall's Island | 1 | DEVELOP SCOPE | Jul 2011 | Sep 2011 | Jul 2011 | Sep 2011
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-568 | New 20" sub-aqueous water main extension to Randall's Island | 2 | PRELIMINARY DESIGN | Sep 2011 | Jan 2012 | Sep 2011 | Jan 2012
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-568 | New 20" sub-aqueous water main extension to Randall's Island | 3 | FINAL DESIGN | Jan 2012 | Jul 2012 | Jan 2012 | Oct 2014
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-568 | New 20" sub-aqueous water main extension to Randall's Island | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2012 | Oct 2012 | Oct 2014 | Jan 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-568 | New 20" sub-aqueous water main extension to Randall's Island | 5 | CONSTRUCTION TO 25% | Oct 2012 | Feb 2013 | Jan 2015 | Sep 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-568 | New 20" sub-aqueous water main extension to Randall's Island | 6 | CONSTRUCTION TO 50% | Feb 2013 | Jun 2013 | Sep 2015 | May 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-568 | New 20" sub-aqueous water main extension to Randall's Island | 7 | CONSTRUCTION TO 75% | Jun 2013 | Oct 2013 | May 2016 | Jan 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-568 | New 20" sub-aqueous water main extension to Randall's Island | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2013 | Jan 2014 | Jan 2017 | Apr 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-568 | New 20" sub-aqueous water main extension to Randall's Island | 9 | SUBSTANTIAL COMPLETION | Jan 2014 | Mar 2014 | Apr 2017 | Jun 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-568 | New 20" sub-aqueous water main extension to Randall's Island | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2014 | Apr 2014 | Jun 2017 | Jun 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-569 | Replacement of Trunk WM in Bainbridge Ave | 1 | DEVELOP SCOPE | Mar 2014 | May 2014 | Mar 2014 | May 2014
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-569 | Replacement of Trunk WM in Bainbridge Ave | 2 | PRELIMINARY DESIGN | May 2014 | Sep 2014 | May 2014 | Sep 2014
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-569 | Replacement of Trunk WM in Bainbridge Ave | 3 | FINAL DESIGN | Sep 2014 | Mar 2015 | Sep 2014 | Mar 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-569 | Replacement of Trunk WM in Bainbridge Ave | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2015 | Jun 2015 | Mar 2015 | Jun 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-569 | Replacement of Trunk WM in Bainbridge Ave | 5 | CONSTRUCTION TO 25% | Jun 2015 | Oct 2015 | Jun 2015 | Jan 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-569 | Replacement of Trunk WM in Bainbridge Ave | 6 | CONSTRUCTION TO 50% | Oct 2015 | Feb 2016 | Jan 2016 | Jul 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-569 | Replacement of Trunk WM in Bainbridge Ave | 7 | CONSTRUCTION TO 75% | Feb 2016 | Jun 2016 | Jul 2016 | Feb 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-569 | Replacement of Trunk WM in Bainbridge Ave | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2016 | Sep 2016 | Feb 2017 | Aug 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-569 | Replacement of Trunk WM in Bainbridge Ave | 9 | SUBSTANTIAL COMPLETION | Sep 2016 | Nov 2016 | Sep 2017 | Jun 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-569 | Replacement of Trunk WM in Bainbridge Ave | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2016 | Dec 2016 | Jun 2018 | Jun 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-572 | Rep WM in Westchester Ave (HWPLZ004X) | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-572 | Rep WM in Westchester Ave (HWPLZ004X) | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-572 | Rep WM in Westchester Ave (HWPLZ004X) | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-572 | Rep WM in Westchester Ave (HWPLZ004X) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-572 | Rep WM in Westchester Ave (HWPLZ004X) | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-572 | Rep WM in Westchester Ave (HWPLZ004X) | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-572 | Rep WM in Westchester Ave (HWPLZ004X) | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-572 | Rep WM in Westchester Ave (HWPLZ004X) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-572 | Rep WM in Westchester Ave (HWPLZ004X) | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-572 | Rep WM in Westchester Ave (HWPLZ004X) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Feb 2028
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-578 | Replcmt of Dist WM In Mundy Lane btwn Cranford & Nereid Ave | 1 | DEVELOP SCOPE | Aug 2019 | Nov 2019 | Aug 2019 | Nov 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-578 | Replcmt of Dist WM In Mundy Lane btwn Cranford & Nereid Ave | 2 | PRELIMINARY DESIGN | Nov 2019 | Mar 2020 | Nov 2019 | Mar 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-578 | Replcmt of Dist WM In Mundy Lane btwn Cranford & Nereid Ave | 3 | FINAL DESIGN | Mar 2020 | Sep 2020 | Mar 2020 | Sep 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-578 | Replcmt of Dist WM In Mundy Lane btwn Cranford & Nereid Ave | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2020 | Dec 2020 | Sep 2020 | Dec 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-578 | Replcmt of Dist WM In Mundy Lane btwn Cranford & Nereid Ave | 5 | CONSTRUCTION TO 25% | Dec 2020 | Apr 2021 | Dec 2020 | Apr 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-578 | Replcmt of Dist WM In Mundy Lane btwn Cranford & Nereid Ave | 6 | CONSTRUCTION TO 50% | Apr 2021 | Aug 2021 | Apr 2021 | Aug 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-578 | Replcmt of Dist WM In Mundy Lane btwn Cranford & Nereid Ave | 7 | CONSTRUCTION TO 75% | Aug 2021 | Dec 2021 | Aug 2021 | Dec 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-578 | Replcmt of Dist WM In Mundy Lane btwn Cranford & Nereid Ave | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2021 | Mar 2022 | Dec 2021 | Mar 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-578 | Replcmt of Dist WM In Mundy Lane btwn Cranford & Nereid Ave | 9 | SUBSTANTIAL COMPLETION | Mar 2022 | May 2022 | Mar 2022 | May 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-578 | Replcmt of Dist WM In Mundy Lane btwn Cranford & Nereid Ave | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2022 | Jun 2022 | May 2022 | Jun 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED580 | Dist WM & SE Rpl E161 St -Gerard &Cortlandt Av,BX, HWX100SBC | 1 | DEVELOP SCOPE | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED580 | Dist WM & SE Rpl E161 St -Gerard &Cortlandt Av,BX, HWX100SBC | 2 | PRELIMINARY DESIGN | Apr 2022 | Jul 2022 | Apr 2022 | Jul 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED580 | Dist WM & SE Rpl E161 St -Gerard &Cortlandt Av,BX, HWX100SBC | 3 | FINAL DESIGN | Jul 2022 | Jan 2023 | Jul 2022 | Jan 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED580 | Dist WM & SE Rpl E161 St -Gerard &Cortlandt Av,BX, HWX100SBC | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2023 | Apr 2023 | Jan 2023 | Apr 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED580 | Dist WM & SE Rpl E161 St -Gerard &Cortlandt Av,BX, HWX100SBC | 5 | CONSTRUCTION TO 25% | Apr 2023 | Aug 2023 | Apr 2023 | Aug 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED580 | Dist WM & SE Rpl E161 St -Gerard &Cortlandt Av,BX, HWX100SBC | 6 | CONSTRUCTION TO 50% | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED580 | Dist WM & SE Rpl E161 St -Gerard &Cortlandt Av,BX, HWX100SBC | 7 | CONSTRUCTION TO 75% | Dec 2023 | Apr 2024 | Dec 2023 | Apr 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED580 | Dist WM & SE Rpl E161 St -Gerard &Cortlandt Av,BX, HWX100SBC | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2024 | Jul 2024 | Apr 2024 | Jul 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED580 | Dist WM & SE Rpl E161 St -Gerard &Cortlandt Av,BX, HWX100SBC | 9 | SUBSTANTIAL COMPLETION | Jul 2024 | Sep 2024 | Jul 2024 | Sep 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED580 | Dist WM & SE Rpl E161 St -Gerard &Cortlandt Av,BX, HWX100SBC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Oct 2024 | Sep 2024 | Oct 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-581 | Dist WM rplmt in Mace Ave btwn Olinville & Cruger Ave, BX | 1 | DEVELOP SCOPE | Nov 2020 | Aug 2021 | Nov 2020 | Aug 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-581 | Dist WM rplmt in Mace Ave btwn Olinville & Cruger Ave, BX | 2 | PRELIMINARY DESIGN | Aug 2021 | Jul 2022 | Aug 2021 | Jul 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-581 | Dist WM rplmt in Mace Ave btwn Olinville & Cruger Ave, BX | 3 | FINAL DESIGN | Aug 2022 | Jan 2024 | Aug 2022 | Jan 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-581 | Dist WM rplmt in Mace Ave btwn Olinville & Cruger Ave, BX | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2024 | Oct 2024 | Jan 2024 | Oct 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-581 | Dist WM rplmt in Mace Ave btwn Olinville & Cruger Ave, BX | 5 | CONSTRUCTION TO 25% | Oct 2024 | Oct 2025 | Oct 2024 | Oct 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-581 | Dist WM rplmt in Mace Ave btwn Olinville & Cruger Ave, BX | 6 | CONSTRUCTION TO 50% | Oct 2025 | Oct 2026 | Oct 2025 | Oct 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-581 | Dist WM rplmt in Mace Ave btwn Olinville & Cruger Ave, BX | 7 | CONSTRUCTION TO 75% | Oct 2026 | Oct 2027 | Oct 2026 | Oct 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-581 | Dist WM rplmt in Mace Ave btwn Olinville & Cruger Ave, BX | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2027 | Jun 2028 | Oct 2027 | Jun 2028
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-581 | Dist WM rplmt in Mace Ave btwn Olinville & Cruger Ave, BX | 9 | SUBSTANTIAL COMPLETION | Jun 2028 | Dec 2028 | Jun 2028 | Dec 2028
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-581 | Dist WM rplmt in Mace Ave btwn Olinville & Cruger Ave, BX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2028 | Mar 2029 | Dec 2028 | Mar 2029
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED582 | Dis WM at iJerome Ave & East Clarke Pl, BX (HWCSCH4D) | 1 | DEVELOP SCOPE | Jan 2022 | Mar 2022 | Jan 2022 | Mar 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED582 | Dis WM at iJerome Ave & East Clarke Pl, BX (HWCSCH4D) | 2 | PRELIMINARY DESIGN | Apr 2022 | Jul 2022 | Apr 2022 | Jul 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED582 | Dis WM at iJerome Ave & East Clarke Pl, BX (HWCSCH4D) | 3 | FINAL DESIGN | Jul 2022 | Jan 2023 | Jul 2022 | Jan 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED582 | Dis WM at iJerome Ave & East Clarke Pl, BX (HWCSCH4D) | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2023 | Apr 2023 | Jan 2023 | Apr 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED582 | Dis WM at iJerome Ave & East Clarke Pl, BX (HWCSCH4D) | 5 | CONSTRUCTION TO 25% | Apr 2023 | Aug 2023 | Apr 2023 | Aug 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED582 | Dis WM at iJerome Ave & East Clarke Pl, BX (HWCSCH4D) | 6 | CONSTRUCTION TO 50% | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED582 | Dis WM at iJerome Ave & East Clarke Pl, BX (HWCSCH4D) | 7 | CONSTRUCTION TO 75% | Dec 2023 | Apr 2024 | Dec 2023 | Apr 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED582 | Dis WM at iJerome Ave & East Clarke Pl, BX (HWCSCH4D) | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2024 | Jul 2024 | Apr 2024 | Jul 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED582 | Dis WM at iJerome Ave & East Clarke Pl, BX (HWCSCH4D) | 9 | SUBSTANTIAL COMPLETION | Jul 2024 | Sep 2024 | Jul 2024 | Sep 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED582 | Dis WM at iJerome Ave & East Clarke Pl, BX (HWCSCH4D) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2024 | Oct 2024 | Sep 2024 | Oct 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED593 | Dist WM installation at E 142 St & Southern Blvd, the BX | 1 | DEVELOP SCOPE | Dec 2022 | Mar 2023 | Dec 2022 | Mar 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED593 | Dist WM installation at E 142 St & Southern Blvd, the BX | 2 | PRELIMINARY DESIGN | Mar 2023 | Jul 2023 | Mar 2023 | Jul 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED593 | Dist WM installation at E 142 St & Southern Blvd, the BX | 3 | FINAL DESIGN | Jul 2023 | Jan 2024 | Jul 2023 | Jan 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED593 | Dist WM installation at E 142 St & Southern Blvd, the BX | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2024 | Apr 2024 | Jan 2024 | Apr 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED593 | Dist WM installation at E 142 St & Southern Blvd, the BX | 5 | CONSTRUCTION TO 25% | Apr 2024 | Jul 2024 | Apr 2024 | Jul 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED593 | Dist WM installation at E 142 St & Southern Blvd, the BX | 6 | CONSTRUCTION TO 50% | Jul 2024 | Nov 2024 | Jul 2024 | Nov 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED593 | Dist WM installation at E 142 St & Southern Blvd, the BX | 7 | CONSTRUCTION TO 75% | Nov 2024 | Mar 2025 | Nov 2024 | Mar 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED593 | Dist WM installation at E 142 St & Southern Blvd, the BX | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2025 | Jun 2025 | Mar 2025 | Jun 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED593 | Dist WM installation at E 142 St & Southern Blvd, the BX | 9 | SUBSTANTIAL COMPLETION | Jun 2025 | Aug 2025 | Jun 2025 | Aug 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED593 | Dist WM installation at E 142 St & Southern Blvd, the BX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2025 | Sep 2025 | Aug 2025 | Jun 2030
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: BX | 1 | DEVELOP SCOPE | Mar 2016 | May 2016 | Mar 2016 | May 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: BX | 2 | PRELIMINARY DESIGN | May 2016 | Sep 2016 | May 2016 | Sep 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: BX | 3 | FINAL DESIGN | Sep 2016 | Mar 2017 | Sep 2016 | Mar 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: BX | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2017 | Jun 2017 | Mar 2017 | Jun 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: BX | 5 | CONSTRUCTION TO 25% | Jun 2017 | Oct 2017 | Jun 2017 | Oct 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: BX | 6 | CONSTRUCTION TO 50% | Oct 2017 | Feb 2018 | Oct 2017 | Feb 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: BX | 7 | CONSTRUCTION TO 75% | Feb 2018 | Jun 2018 | Feb 2018 | Jun 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: BX | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2018 | Sep 2018 | Jun 2018 | Sep 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: BX | 9 | SUBSTANTIAL COMPLETION | Sep 2018 | Nov 2018 | Sep 2018 | Nov 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: BX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2018 | Dec 2018 | Nov 2018 | Jun 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CWFR | COMMONWEALTH AVENUE FIRE SAFETY SYSTEM | 1 | PROJECT START | Mar 2016 | Mar 2016 | Mar 2016 | Mar 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CWFR | COMMONWEALTH AVENUE FIRE SAFETY SYSTEM | 2 | DESIGN START | Apr 2016 | Jul 2016 | Apr 2016 | Jul 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CWFR | COMMONWEALTH AVENUE FIRE SAFETY SYSTEM | 3 | DESIGN COMPLETION | Jul 2016 | Jun 2017 | Jul 2016 | Jun 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CWFR | COMMONWEALTH AVENUE FIRE SAFETY SYSTEM | 4 | CONSTRUCTION START | Jul 2017 | Oct 2017 | Jul 2017 | Oct 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CWFR | COMMONWEALTH AVENUE FIRE SAFETY SYSTEM | 5 | CONSTRUCTION COMPLETION | Nov 2017 | Jun 2023 | Nov 2017 | Jun 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112WLFA | WILLOW AVE FIRE SAFETY | 1 | PROJECT START | Jul 2016 | Jul 2016 | Jul 2016 | Jul 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112WLFA | WILLOW AVE FIRE SAFETY | 2 | DESIGN START | Jul 2016 | Oct 2016 | Oct 2016 | Oct 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112WLFA | WILLOW AVE FIRE SAFETY | 3 | DESIGN COMPLETION | Oct 2016 | Jun 2017 | Jun 2017 | Jun 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112WLFA | WILLOW AVE FIRE SAFETY | 4 | CONSTRUCTION START | Jun 2017 | Feb 2019 | Jun 2018 | Jun 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112WLFA | WILLOW AVE FIRE SAFETY | 5 | CONSTRUCTION COMPLETION | Feb 2019 | May 2019 | Jun 2018 | Jun 2031
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115FRFA | FREEMAN FAMILY RESIDENCE - FIRE ALARM SYSTEM UPGRADE | 1 | PROJECT START | Mar 2016 | Mar 2016 | Mar 2016 | Mar 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115FRFA | FREEMAN FAMILY RESIDENCE - FIRE ALARM SYSTEM UPGRADE | 2 | DESIGN START | Apr 2016 | Jul 2016 | Apr 2016 | Jul 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115FRFA | FREEMAN FAMILY RESIDENCE - FIRE ALARM SYSTEM UPGRADE | 3 | DESIGN COMPLETION | Jul 2016 | Jun 2017 | Jul 2016 | Jun 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115FRFA | FREEMAN FAMILY RESIDENCE - FIRE ALARM SYSTEM UPGRADE | 4 | CONSTRUCTION START | Jul 2017 | Oct 2017 | Jul 2017 | Oct 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115FRFA | FREEMAN FAMILY RESIDENCE - FIRE ALARM SYSTEM UPGRADE | 5 | CONSTRUCTION COMPLETION | Nov 2017 | Jun 2023 | Nov 2017 | Sep 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCFS | JACKSON FAMILY FIRE SAFETY | 1 | PROJECT START | Jul 2016 | Jul 2016 | Jul 2016 | Jul 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCFS | JACKSON FAMILY FIRE SAFETY | 2 | DESIGN START | Jul 2016 | Oct 2016 | Jul 2016 | Oct 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCFS | JACKSON FAMILY FIRE SAFETY | 3 | DESIGN COMPLETION | Oct 2016 | Jun 2017 | Oct 2016 | Jun 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCFS | JACKSON FAMILY FIRE SAFETY | 4 | CONSTRUCTION START | Jun 2017 | Aug 2018 | Jun 2017 | Aug 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCFS | JACKSON FAMILY FIRE SAFETY | 5 | CONSTRUCTION COMPLETION | Aug 2018 | May 2019 | Aug 2018 | Jun 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SNEC | SENECA HOUSES - ELECTRICAL AND KITCHEN UPGRADE | 1 | PROJECT START | Jun 2018 | Jun 2018 | Jun 2018 | Jun 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SNEC | SENECA HOUSES - ELECTRICAL AND KITCHEN UPGRADE | 2 | DESIGN START | Jun 2018 | Jun 2018 | Jun 2019 | Jun 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SNEC | SENECA HOUSES - ELECTRICAL AND KITCHEN UPGRADE | 3 | DESIGN COMPLETION | Jun 2018 | Jun 2018 | Jun 2020 | Jun 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SNEC | SENECA HOUSES - ELECTRICAL AND KITCHEN UPGRADE | 4 | CONSTRUCTION START | Jun 2018 | Jun 2018 | Jun 2021 | Jun 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SNEC | SENECA HOUSES - ELECTRICAL AND KITCHEN UPGRADE | 5 | CONSTRUCTION COMPLETION | Jun 2018 | Jun 2020 | Jun 2022 | Jun 2031
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115UNFA | UNIVERSITY FAMILY RESIDENCE - FIRE ALARM SYSTEM UPGRADE | 1 | PROJECT START | Mar 2016 | Mar 2016 | Mar 2016 | Mar 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115UNFA | UNIVERSITY FAMILY RESIDENCE - FIRE ALARM SYSTEM UPGRADE | 2 | DESIGN START | Apr 2016 | Jul 2016 | Apr 2016 | Jul 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115UNFA | UNIVERSITY FAMILY RESIDENCE - FIRE ALARM SYSTEM UPGRADE | 3 | DESIGN COMPLETION | Jul 2016 | Jun 2017 | Jul 2016 | Jun 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115UNFA | UNIVERSITY FAMILY RESIDENCE - FIRE ALARM SYSTEM UPGRADE | 4 | CONSTRUCTION START | Jul 2017 | Oct 2017 | Jun 2018 | Apr 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115UNFA | UNIVERSITY FAMILY RESIDENCE - FIRE ALARM SYSTEM UPGRADE | 5 | CONSTRUCTION COMPLETION | Nov 2017 | Jun 2023 | Apr 2020 | Nov 2032
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BRONX | Bronx Animal Care Center and Veterinary Clinic | 1 | PROJECT START | Jul 2016 | Dec 2016 | Jul 2019 | Jul 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BRONX | Bronx Animal Care Center and Veterinary Clinic | 2 | DESIGN START | Dec 2016 | Mar 2017 | Jul 2019 | Oct 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BRONX | Bronx Animal Care Center and Veterinary Clinic | 3 | CONSTRUCTION | Mar 2017 | Mar 2018 | Oct 2019 | Oct 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BRONX | Bronx Animal Care Center and Veterinary Clinic | 4 | CONSTRUCTION START | Mar 2018 | Sep 2018 | Oct 2020 | Jan 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BRONX | Bronx Animal Care Center and Veterinary Clinic | 5 | CONSTRUCTION COMPLETION | Mar 2018 | Sep 2018 | Jan 2021 | Jun 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPBX | SAFE ROUTES TO SCHOOLS- BRONX | 1 | DEVELOP SCOPE | Mar 2019 | May 2019 | Mar 2019 | May 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPBX | SAFE ROUTES TO SCHOOLS- BRONX | 2 | PRELIMINARY DESIGN | May 2019 | Sep 2019 | May 2019 | Sep 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPBX | SAFE ROUTES TO SCHOOLS- BRONX | 3 | FINAL DESIGN | Sep 2019 | Mar 2020 | Sep 2019 | Mar 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPBX | SAFE ROUTES TO SCHOOLS- BRONX | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Jun 2020 | Mar 2020 | Jun 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPBX | SAFE ROUTES TO SCHOOLS- BRONX | 5 | CONSTRUCTION TO 25% | Jun 2020 | Oct 2020 | Jun 2020 | Oct 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPBX | SAFE ROUTES TO SCHOOLS- BRONX | 6 | CONSTRUCTION TO 50% | Oct 2020 | Feb 2021 | Oct 2020 | Feb 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPBX | SAFE ROUTES TO SCHOOLS- BRONX | 7 | CONSTRUCTION TO 75% | Feb 2021 | Jun 2021 | Feb 2021 | Jun 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPBX | SAFE ROUTES TO SCHOOLS- BRONX | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPBX | SAFE ROUTES TO SCHOOLS- BRONX | 9 | SUBSTANTIAL COMPLETION | Sep 2021 | Nov 2021 | Sep 2021 | Nov 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPBX | SAFE ROUTES TO SCHOOLS- BRONX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2021 | Dec 2021 | Nov 2021 | Jun 2029
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10501A | HUGH GRANT CIRCLE - METROPOLITAN AV AND WESTCHESTER AV | 1 | DEVELOP SCOPE | Feb 2008 | May 2008 | Feb 2008 | May 2008
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10501A | HUGH GRANT CIRCLE - METROPOLITAN AV AND WESTCHESTER AV | 2 | PRELIMINARY DESIGN | May 2008 | Sep 2008 | May 2008 | Sep 2008
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10501A | HUGH GRANT CIRCLE - METROPOLITAN AV AND WESTCHESTER AV | 3 | FINAL DESIGN | Sep 2008 | Mar 2009 | Sep 2008 | Mar 2009
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10501A | HUGH GRANT CIRCLE - METROPOLITAN AV AND WESTCHESTER AV | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2009 | Jun 2009 | Feb 2010 | May 2010
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10501A | HUGH GRANT CIRCLE - METROPOLITAN AV AND WESTCHESTER AV | 5 | CONSTRUCTION TO 25% | Jun 2009 | Oct 2009 | May 2010 | Sep 2010
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10501A | HUGH GRANT CIRCLE - METROPOLITAN AV AND WESTCHESTER AV | 6 | CONSTRUCTION TO 50% | Oct 2009 | Feb 2010 | Sep 2010 | Jan 2011
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10501A | HUGH GRANT CIRCLE - METROPOLITAN AV AND WESTCHESTER AV | 7 | CONSTRUCTION TO 75% | Feb 2010 | Jun 2010 | Jan 2011 | May 2011
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10501A | HUGH GRANT CIRCLE - METROPOLITAN AV AND WESTCHESTER AV | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2010 | Sep 2010 | Feb 2011 | May 2011
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10501A | HUGH GRANT CIRCLE - METROPOLITAN AV AND WESTCHESTER AV | 9 | SUBSTANTIAL COMPLETION | Sep 2010 | Nov 2010 | May 2011 | Oct 2011
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10501A | HUGH GRANT CIRCLE - METROPOLITAN AV AND WESTCHESTER AV | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2010 | Dec 2010 | Oct 2011 | May 2032
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-03 | LIBRARY LANE PROJECT | 1 | DEVELOP SCOPE | Aug 2005 | Dec 2005 | Jun 2005 | Sep 2005
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-03 | LIBRARY LANE PROJECT | 2 | DESIGN START | Dec 2005 | Jun 2007 | Sep 2005 | Jan 2006
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-03 | LIBRARY LANE PROJECT | 3 | CONSTRUCTION START | Jun 2007 | Jun 2009 | Jan 2006 | Mar 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-03 | LIBRARY LANE PROJECT | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2007 | Jun 2009 | Mar 2016 | Jun 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-03 | LIBRARY LANE PROJECT | 5 | CONSTRUCTION TO 25% | Jun 2007 | Jun 2009 | Jun 2016 | Oct 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-03 | LIBRARY LANE PROJECT | 6 | CONSTRUCTION TO 50% | Jun 2007 | Jun 2009 | Oct 2016 | Feb 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-03 | LIBRARY LANE PROJECT | 7 | CONSTRUCTION TO 75% | Jun 2007 | Jun 2009 | Feb 2017 | Jun 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-03 | LIBRARY LANE PROJECT | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2007 | Jun 2009 | Jun 2017 | Sep 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-03 | LIBRARY LANE PROJECT | 9 | SUBSTANTIAL COMPLETION | Jun 2007 | Jun 2009 | Sep 2017 | Nov 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-03 | LIBRARY LANE PROJECT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2007 | Jun 2009 | Nov 2017 | Jun 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM10INWD | Inwood 10th Avenue Improvements, NDF-IWHRG | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM10INWD | Inwood 10th Avenue Improvements, NDF-IWHRG | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM10INWD | Inwood 10th Avenue Improvements, NDF-IWHRG | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2025 | Jul 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM10INWD | Inwood 10th Avenue Improvements, NDF-IWHRG | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2025 | Oct 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM10INWD | Inwood 10th Avenue Improvements, NDF-IWHRG | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2025 | Feb 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM10INWD | Inwood 10th Avenue Improvements, NDF-IWHRG | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2026 | Jun 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM10INWD | Inwood 10th Avenue Improvements, NDF-IWHRG | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2026 | Oct 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM10INWD | Inwood 10th Avenue Improvements, NDF-IWHRG | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2026 | Jan 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM10INWD | Inwood 10th Avenue Improvements, NDF-IWHRG | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2027 | Mar 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM10INWD | Inwood 10th Avenue Improvements, NDF-IWHRG | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2027 | Apr 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ004X | Morrison Avenue Plaza (HED-572) | 1 | DEVELOP SCOPE | Jun 2016 | Aug 2016 | Jun 2016 | Aug 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ004X | Morrison Avenue Plaza (HED-572) | 2 | PRELIMINARY DESIGN | Aug 2016 | Dec 2016 | Aug 2016 | Dec 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ004X | Morrison Avenue Plaza (HED-572) | 3 | FINAL DESIGN | Dec 2016 | Jun 2017 | Dec 2016 | Jun 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ004X | Morrison Avenue Plaza (HED-572) | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2017 | Sep 2017 | Jun 2017 | Sep 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ004X | Morrison Avenue Plaza (HED-572) | 5 | CONSTRUCTION TO 25% | Sep 2017 | Jan 2018 | Sep 2017 | Jan 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ004X | Morrison Avenue Plaza (HED-572) | 6 | CONSTRUCTION TO 50% | Jan 2018 | May 2018 | Jan 2018 | May 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ004X | Morrison Avenue Plaza (HED-572) | 7 | CONSTRUCTION TO 75% | May 2018 | Sep 2018 | May 2018 | Sep 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ004X | Morrison Avenue Plaza (HED-572) | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2018 | Dec 2018 | Sep 2018 | Dec 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ004X | Morrison Avenue Plaza (HED-572) | 9 | SUBSTANTIAL COMPLETION | Dec 2018 | Feb 2019 | Dec 2018 | Feb 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ004X | Morrison Avenue Plaza (HED-572) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2019 | Mar 2019 | Feb 2019 | Jun 2033
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2014X | PRIOR NOTICE SIDEWALKS - BRONX | 1 | DEVELOP SCOPE | Feb 2013 | May 2013 | Feb 2013 | May 2013
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2014X | PRIOR NOTICE SIDEWALKS - BRONX | 2 | PRELIMINARY DESIGN | May 2013 | Sep 2013 | May 2013 | Sep 2013
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2014X | PRIOR NOTICE SIDEWALKS - BRONX | 3 | FINAL DESIGN | Sep 2013 | Mar 2014 | Sep 2013 | Mar 2014
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2014X | PRIOR NOTICE SIDEWALKS - BRONX | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2014 | Jun 2014 | Mar 2014 | Jun 2014
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2014X | PRIOR NOTICE SIDEWALKS - BRONX | 5 | CONSTRUCTION TO 25% | Jun 2014 | Oct 2014 | Jun 2014 | Oct 2014
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2014X | PRIOR NOTICE SIDEWALKS - BRONX | 6 | CONSTRUCTION TO 50% | Oct 2014 | Feb 2015 | Oct 2014 | Feb 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2014X | PRIOR NOTICE SIDEWALKS - BRONX | 7 | CONSTRUCTION TO 75% | Feb 2015 | Jun 2015 | Feb 2015 | Jun 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2014X | PRIOR NOTICE SIDEWALKS - BRONX | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2015 | Sep 2015 | Jun 2015 | Sep 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2014X | PRIOR NOTICE SIDEWALKS - BRONX | 9 | SUBSTANTIAL COMPLETION | Sep 2015 | Nov 2015 | Sep 2015 | Nov 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2014X | PRIOR NOTICE SIDEWALKS - BRONX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2015 | Dec 2015 | Nov 2015 | Jun 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2014X | PRIOR NOTICE SIDEWALKS - BRONX | 11 | PROJECT START | Nov 2015 | Dec 2015 | Jul 2022 | Jul 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2014X | PRIOR NOTICE SIDEWALKS - BRONX | 12 | DESIGN START | Nov 2015 | Dec 2015 | Jul 2022 | Jul 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2014X | PRIOR NOTICE SIDEWALKS - BRONX | 13 | DESIGN COMPLETION | Nov 2015 | Dec 2015 | Jul 2022 | Jul 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2014X | PRIOR NOTICE SIDEWALKS - BRONX | 14 | CONSTRUCTION START | Nov 2015 | Dec 2015 | Jul 2022 | Jul 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2014X | PRIOR NOTICE SIDEWALKS - BRONX | 15 | CONSTRUCTION COMPLETION | Nov 2015 | Dec 2015 | Jul 2022 | Jul 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021X | PRIOR NOTICE SIDEWALK - BRONX | 1 | DEVELOP SCOPE | Feb 2020 | Mar 2020 | Feb 2021 | Mar 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021X | PRIOR NOTICE SIDEWALK - BRONX | 2 | DESIGN START | Mar 2020 | Sep 2020 | Mar 2021 | Sep 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021X | PRIOR NOTICE SIDEWALK - BRONX | 3 | CONSTRUCTION START | Sep 2020 | Jun 2021 | Sep 2021 | Jul 2032
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023X | Prior Notice Sidewalks - Bronx | 1 | DEVELOP SCOPE | Jun 2024 | Sep 2024 | Jun 2023 | Sep 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023X | Prior Notice Sidewalks - Bronx | 2 | PRELIMINARY DESIGN | Sep 2024 | Jan 2025 | Sep 2023 | Jan 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023X | Prior Notice Sidewalks - Bronx | 3 | FINAL DESIGN | Jan 2025 | Jul 2025 | Jan 2024 | Jul 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023X | Prior Notice Sidewalks - Bronx | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Oct 2025 | Jul 2024 | Oct 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023X | Prior Notice Sidewalks - Bronx | 5 | CONSTRUCTION TO 25% | Oct 2025 | Feb 2026 | Oct 2024 | Feb 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023X | Prior Notice Sidewalks - Bronx | 6 | CONSTRUCTION TO 50% | Feb 2026 | Jun 2026 | Feb 2025 | Jun 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023X | Prior Notice Sidewalks - Bronx | 7 | CONSTRUCTION TO 75% | Jun 2026 | Oct 2026 | Jun 2025 | Oct 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023X | Prior Notice Sidewalks - Bronx | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2026 | Jan 2027 | Oct 2025 | Jan 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023X | Prior Notice Sidewalks - Bronx | 9 | SUBSTANTIAL COMPLETION | Jan 2027 | Mar 2027 | Jan 2026 | Mar 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2023X | Prior Notice Sidewalks - Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2027 | Apr 2027 | Mar 2026 | Apr 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX006-01 | Henwood Place Step Street | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jun 2019 | Sep 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX006-01 | Henwood Place Step Street | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Sep 2019 | Jan 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX006-01 | Henwood Place Step Street | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2020 | Jul 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX006-01 | Henwood Place Step Street | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2020 | Oct 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX006-01 | Henwood Place Step Street | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2020 | Feb 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX006-01 | Henwood Place Step Street | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2021 | Jun 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX006-01 | Henwood Place Step Street | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2021 | Oct 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX006-01 | Henwood Place Step Street | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2021 | Jan 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX006-01 | Henwood Place Step Street | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2022 | Mar 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX006-01 | Henwood Place Step Street | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2022 | Dec 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBC | South Bronx East-West Crosstown SBS (HED580) | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2019 | Sep 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBC | South Bronx East-West Crosstown SBS (HED580) | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2019 | Jan 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBC | South Bronx East-West Crosstown SBS (HED580) | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jan 2020 | Jul 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBC | South Bronx East-West Crosstown SBS (HED580) | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2020 | Oct 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBC | South Bronx East-West Crosstown SBS (HED580) | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Oct 2020 | Feb 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBC | South Bronx East-West Crosstown SBS (HED580) | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Feb 2021 | Jun 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBC | South Bronx East-West Crosstown SBS (HED580) | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jun 2021 | Oct 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBC | South Bronx East-West Crosstown SBS (HED580) | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Oct 2021 | Jan 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBC | South Bronx East-West Crosstown SBS (HED580) | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jan 2022 | Mar 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBC | South Bronx East-West Crosstown SBS (HED580) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Mar 2022 | Jun 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX402 | Bruner and Ely | 1 | DEVELOP SCOPE | Jun 2018 | Sep 2018 | Jun 2020 | Sep 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX402 | Bruner and Ely | 2 | PRELIMINARY DESIGN | Sep 2018 | Jan 2019 | Sep 2020 | Jan 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX402 | Bruner and Ely | 3 | FINAL DESIGN | Jan 2019 | Jul 2019 | Jan 2021 | Jul 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX402 | Bruner and Ely | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Oct 2019 | Jul 2021 | Oct 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX402 | Bruner and Ely | 5 | CONSTRUCTION TO 25% | Oct 2019 | Feb 2020 | Oct 2021 | Feb 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX402 | Bruner and Ely | 6 | CONSTRUCTION TO 50% | Feb 2020 | Jun 2020 | Feb 2022 | Jun 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX402 | Bruner and Ely | 7 | CONSTRUCTION TO 75% | Jun 2020 | Oct 2020 | Jun 2022 | Oct 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX402 | Bruner and Ely | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2020 | Jan 2021 | Oct 2022 | Jan 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX402 | Bruner and Ely | 9 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Jan 2023 | Mar 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX402 | Bruner and Ely | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Mar 2023 | Jun 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX404 | Southern Bronx Multi-Site Safety Improvements | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Mar 2019 | Jan 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX404 | Southern Bronx Multi-Site Safety Improvements | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Jan 2020 | May 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX404 | Southern Bronx Multi-Site Safety Improvements | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | May 2020 | Oct 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX404 | Southern Bronx Multi-Site Safety Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Oct 2020 | Jan 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX404 | Southern Bronx Multi-Site Safety Improvements | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Jan 2021 | May 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX404 | Southern Bronx Multi-Site Safety Improvements | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | May 2021 | Sep 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX404 | Southern Bronx Multi-Site Safety Improvements | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Sep 2021 | Jan 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX404 | Southern Bronx Multi-Site Safety Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Jan 2022 | Apr 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX404 | Southern Bronx Multi-Site Safety Improvements | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Apr 2022 | Jun 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX404 | Southern Bronx Multi-Site Safety Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Jun 2022 | Jun 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX405 | Southern Blvd Pedestrian and Bike Improvements | 1 | DEVELOP SCOPE | Jun 2020 | Sep 2020 | Jun 2024 | Sep 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX405 | Southern Blvd Pedestrian and Bike Improvements | 2 | PRELIMINARY DESIGN | Sep 2020 | Jan 2021 | Sep 2024 | Jan 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX405 | Southern Blvd Pedestrian and Bike Improvements | 3 | FINAL DESIGN | Jan 2021 | Jul 2021 | Jan 2025 | Jul 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX405 | Southern Blvd Pedestrian and Bike Improvements | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2021 | Oct 2021 | Jul 2025 | Oct 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX405 | Southern Blvd Pedestrian and Bike Improvements | 5 | CONSTRUCTION TO 25% | Oct 2021 | Feb 2022 | Oct 2025 | Feb 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX405 | Southern Blvd Pedestrian and Bike Improvements | 6 | CONSTRUCTION TO 50% | Feb 2022 | Jun 2022 | Feb 2026 | Jun 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX405 | Southern Blvd Pedestrian and Bike Improvements | 7 | CONSTRUCTION TO 75% | Jun 2022 | Oct 2022 | Jun 2026 | Oct 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX405 | Southern Blvd Pedestrian and Bike Improvements | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2022 | Jan 2023 | Oct 2026 | Jan 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX405 | Southern Blvd Pedestrian and Bike Improvements | 9 | SUBSTANTIAL COMPLETION | Jan 2023 | Mar 2023 | Jan 2027 | Mar 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX405 | Southern Blvd Pedestrian and Bike Improvements | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Apr 2023 | Mar 2027 | Apr 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX406 | Northwest Bronx School Safety Improvements, SEX002274 | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Mar 2019 | Dec 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX406 | Northwest Bronx School Safety Improvements, SEX002274 | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Dec 2019 | Apr 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX406 | Northwest Bronx School Safety Improvements, SEX002274 | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | Apr 2020 | Oct 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX406 | Northwest Bronx School Safety Improvements, SEX002274 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Oct 2020 | Jan 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX406 | Northwest Bronx School Safety Improvements, SEX002274 | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Jan 2021 | May 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX406 | Northwest Bronx School Safety Improvements, SEX002274 | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | May 2021 | Sep 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX406 | Northwest Bronx School Safety Improvements, SEX002274 | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Sep 2021 | Dec 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX406 | Northwest Bronx School Safety Improvements, SEX002274 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Jan 2022 | Mar 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX406 | Northwest Bronx School Safety Improvements, SEX002274 | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Apr 2022 | May 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX406 | Northwest Bronx School Safety Improvements, SEX002274 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | May 2022 | Jun 2028
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX411 | Bus Stops Under the El: White Plains Rd and Mace Ave | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2023 | Sep 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX411 | Bus Stops Under the El: White Plains Rd and Mace Ave | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2023 | Jan 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX411 | Bus Stops Under the El: White Plains Rd and Mace Ave | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2024 | Jul 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX411 | Bus Stops Under the El: White Plains Rd and Mace Ave | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2024 | Oct 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX411 | Bus Stops Under the El: White Plains Rd and Mace Ave | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2024 | Feb 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX411 | Bus Stops Under the El: White Plains Rd and Mace Ave | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2025 | Jun 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX411 | Bus Stops Under the El: White Plains Rd and Mace Ave | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2025 | Oct 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX411 | Bus Stops Under the El: White Plains Rd and Mace Ave | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2025 | Jan 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX411 | Bus Stops Under the El: White Plains Rd and Mace Ave | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2026 | Mar 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX411 | Bus Stops Under the El: White Plains Rd and Mace Ave | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2026 | Apr 2028
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX710A | Pelham Pkwy - West & East and North & South Bounds (Phase A) | 1 | DEVELOP SCOPE | Mar 2010 | Jun 2010 | Jul 2006 | Jun 2007
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX710A | Pelham Pkwy - West & East and North & South Bounds (Phase A) | 2 | PRELIMINARY DESIGN | Jun 2010 | Sep 2010 | Jul 2007 | Jun 2009
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX710A | Pelham Pkwy - West & East and North & South Bounds (Phase A) | 3 | FINAL DESIGN | Oct 2010 | Mar 2011 | Jun 2009 | Mar 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX710A | Pelham Pkwy - West & East and North & South Bounds (Phase A) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2011 | Jun 2011 | Mar 2016 | Jun 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX710A | Pelham Pkwy - West & East and North & South Bounds (Phase A) | 5 | CONSTRUCTION TO 25% | Jun 2011 | Oct 2011 | Jun 2016 | Sep 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX710A | Pelham Pkwy - West & East and North & South Bounds (Phase A) | 6 | CONSTRUCTION TO 50% | Oct 2011 | Feb 2012 | Sep 2016 | Jan 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX710A | Pelham Pkwy - West & East and North & South Bounds (Phase A) | 7 | CONSTRUCTION TO 75% | Feb 2012 | Jun 2012 | Jan 2017 | May 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX710A | Pelham Pkwy - West & East and North & South Bounds (Phase A) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2012 | Sep 2012 | May 2017 | Aug 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX710A | Pelham Pkwy - West & East and North & South Bounds (Phase A) | 9 | SUBSTANTIAL COMPLETION | Sep 2012 | Nov 2012 | Aug 2017 | Jul 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX710A | Pelham Pkwy - West & East and North & South Bounds (Phase A) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2012 | Dec 2012 | Aug 2027 | Apr 2030
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXF2000B | 1400 WILLIAMSBRIDGE RD - HVAC AND FIRE ALARM SYS | 1 | DEVELOP SCOPE | Jun 2016 | Sep 2016 | Jun 2016 | Sep 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXF2000B | 1400 WILLIAMSBRIDGE RD - HVAC AND FIRE ALARM SYS | 2 | PRELIMINARY DESIGN | Sep 2016 | Jan 2017 | Sep 2016 | Jan 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXF2000B | 1400 WILLIAMSBRIDGE RD - HVAC AND FIRE ALARM SYS | 3 | FINAL DESIGN | Jan 2017 | Jul 2017 | Jan 2017 | Jul 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXF2000B | 1400 WILLIAMSBRIDGE RD - HVAC AND FIRE ALARM SYS | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2017 | Oct 2017 | Jul 2017 | Oct 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXF2000B | 1400 WILLIAMSBRIDGE RD - HVAC AND FIRE ALARM SYS | 5 | CONSTRUCTION TO 25% | Oct 2017 | Feb 2018 | Oct 2017 | Feb 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXF2000B | 1400 WILLIAMSBRIDGE RD - HVAC AND FIRE ALARM SYS | 6 | CONSTRUCTION TO 50% | Feb 2018 | Jun 2018 | Feb 2018 | Jun 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXF2000B | 1400 WILLIAMSBRIDGE RD - HVAC AND FIRE ALARM SYS | 7 | CONSTRUCTION TO 75% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXF2000B | 1400 WILLIAMSBRIDGE RD - HVAC AND FIRE ALARM SYS | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2018 | Jan 2019 | Oct 2018 | Jan 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXF2000B | 1400 WILLIAMSBRIDGE RD - HVAC AND FIRE ALARM SYS | 9 | SUBSTANTIAL COMPLETION | Jan 2019 | Mar 2019 | Jan 2019 | Mar 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXF2000B | 1400 WILLIAMSBRIDGE RD - HVAC AND FIRE ALARM SYS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Apr 2019 | Mar 2019 | Jun 2032
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXJEROME | Jerome Avenue Safety Improvements (NDF-JEROM) | 1 | DEVELOP SCOPE | Jun 2019 | Sep 2019 | Feb 2016 | Jan 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXJEROME | Jerome Avenue Safety Improvements (NDF-JEROM) | 2 | PRELIMINARY DESIGN | Sep 2019 | Jan 2020 | Feb 2021 | Sep 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXJEROME | Jerome Avenue Safety Improvements (NDF-JEROM) | 3 | FINAL DESIGN | Jan 2020 | Jul 2020 | May 2022 | Nov 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXJEROME | Jerome Avenue Safety Improvements (NDF-JEROM) | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Oct 2020 | Nov 2023 | Jan 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXJEROME | Jerome Avenue Safety Improvements (NDF-JEROM) | 5 | CONSTRUCTION TO 25% | Oct 2020 | Feb 2021 | Sep 2024 | Dec 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXJEROME | Jerome Avenue Safety Improvements (NDF-JEROM) | 6 | CONSTRUCTION TO 50% | Feb 2021 | Jun 2021 | Dec 2024 | Apr 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXJEROME | Jerome Avenue Safety Improvements (NDF-JEROM) | 7 | CONSTRUCTION TO 75% | Jun 2021 | Oct 2021 | Apr 2025 | Dec 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXJEROME | Jerome Avenue Safety Improvements (NDF-JEROM) | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2021 | Jan 2022 | Dec 2027 | Mar 2028
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXJEROME | Jerome Avenue Safety Improvements (NDF-JEROM) | 9 | SUBSTANTIAL COMPLETION | Jan 2022 | Mar 2022 | Mar 2028 | May 2028
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXJEROME | Jerome Avenue Safety Improvements (NDF-JEROM) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2022 | Apr 2022 | May 2028 | Jun 2028
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136C | Grand Concourse Phase 4 (SEX002268) | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2017 | Sep 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136C | Grand Concourse Phase 4 (SEX002268) | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2017 | Jan 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136C | Grand Concourse Phase 4 (SEX002268) | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jan 2018 | Jul 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136C | Grand Concourse Phase 4 (SEX002268) | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2018 | Oct 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136C | Grand Concourse Phase 4 (SEX002268) | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136C | Grand Concourse Phase 4 (SEX002268) | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136C | Grand Concourse Phase 4 (SEX002268) | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jun 2019 | Oct 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136C | Grand Concourse Phase 4 (SEX002268) | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Oct 2019 | Jan 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136C | Grand Concourse Phase 4 (SEX002268) | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jan 2020 | Mar 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136C | Grand Concourse Phase 4 (SEX002268) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Mar 2020 | Jun 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136C | Grand Concourse Phase 4 (SEX002268) | 11 | PROJECT START | Mar 2020 | Apr 2020 | Jul 2024 | Jul 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136C | Grand Concourse Phase 4 (SEX002268) | 12 | DESIGN START | Mar 2020 | Apr 2020 | Jul 2024 | Jul 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136C | Grand Concourse Phase 4 (SEX002268) | 13 | DESIGN COMPLETION | Mar 2020 | Apr 2020 | Jul 2024 | Jul 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136C | Grand Concourse Phase 4 (SEX002268) | 14 | CONSTRUCTION START | Mar 2020 | Apr 2020 | Jul 2024 | Jul 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136C | Grand Concourse Phase 4 (SEX002268) | 15 | CONSTRUCTION COMPLETION | Mar 2020 | Apr 2020 | Jul 2024 | Jul 2032
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136D | Grand Concourse Phase 5, SEX002275 | 1 | DEVELOP SCOPE | Jun 2022 | Sep 2022 | Jun 2019 | Sep 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136D | Grand Concourse Phase 5, SEX002275 | 2 | PRELIMINARY DESIGN | Sep 2022 | Jan 2023 | Sep 2019 | Jan 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136D | Grand Concourse Phase 5, SEX002275 | 3 | FINAL DESIGN | Jan 2023 | Jul 2023 | Jan 2020 | Jul 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136D | Grand Concourse Phase 5, SEX002275 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Oct 2023 | Jul 2020 | Oct 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136D | Grand Concourse Phase 5, SEX002275 | 5 | CONSTRUCTION TO 25% | Oct 2023 | Feb 2024 | Oct 2020 | Feb 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136D | Grand Concourse Phase 5, SEX002275 | 6 | CONSTRUCTION TO 50% | Feb 2024 | Jun 2024 | Feb 2021 | Jun 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136D | Grand Concourse Phase 5, SEX002275 | 7 | CONSTRUCTION TO 75% | Jun 2024 | Oct 2024 | Jun 2021 | Oct 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136D | Grand Concourse Phase 5, SEX002275 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2024 | Jan 2025 | Oct 2021 | Jan 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136D | Grand Concourse Phase 5, SEX002275 | 9 | SUBSTANTIAL COMPLETION | Jan 2025 | Mar 2025 | Jan 2022 | Mar 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136D | Grand Concourse Phase 5, SEX002275 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2025 | Apr 2025 | Mar 2022 | Jun 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP2007 | E177TH ST/DEVOE AVE BT SHERIDAN (I-895) /E.TREMONT HED-560 | 1 | DEVELOP SCOPE | May 2002 | Aug 2002 | May 2002 | Aug 2002
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP2007 | E177TH ST/DEVOE AVE BT SHERIDAN (I-895) /E.TREMONT HED-560 | 2 | PRELIMINARY DESIGN | Aug 2002 | Dec 2002 | Aug 2002 | Dec 2002
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP2007 | E177TH ST/DEVOE AVE BT SHERIDAN (I-895) /E.TREMONT HED-560 | 3 | FINAL DESIGN | Dec 2002 | Jun 2003 | Dec 2002 | Jun 2003
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP2007 | E177TH ST/DEVOE AVE BT SHERIDAN (I-895) /E.TREMONT HED-560 | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2003 | Sep 2003 | Mar 2022 | Jun 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP2007 | E177TH ST/DEVOE AVE BT SHERIDAN (I-895) /E.TREMONT HED-560 | 5 | CONSTRUCTION TO 25% | Sep 2003 | Jan 2004 | Jun 2022 | Jun 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP2007 | E177TH ST/DEVOE AVE BT SHERIDAN (I-895) /E.TREMONT HED-560 | 6 | CONSTRUCTION TO 50% | Jan 2004 | May 2004 | Jun 2022 | Jun 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP2007 | E177TH ST/DEVOE AVE BT SHERIDAN (I-895) /E.TREMONT HED-560 | 7 | CONSTRUCTION TO 75% | May 2004 | Sep 2004 | Jun 2022 | Jun 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP2007 | E177TH ST/DEVOE AVE BT SHERIDAN (I-895) /E.TREMONT HED-560 | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2004 | Dec 2004 | Jun 2022 | Jun 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP2007 | E177TH ST/DEVOE AVE BT SHERIDAN (I-895) /E.TREMONT HED-560 | 9 | SUBSTANTIAL COMPLETION | Dec 2004 | Feb 2005 | Jun 2022 | Jun 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP2007 | E177TH ST/DEVOE AVE BT SHERIDAN (I-895) /E.TREMONT HED-560 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2005 | Mar 2005 | Nov 2023 | Dec 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXPRATT | Pratt Ave Reconstruction and Retaining Wall, SEX20049 | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2017 | Sep 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXPRATT | Pratt Ave Reconstruction and Retaining Wall, SEX20049 | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Sep 2017 | Jan 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXPRATT | Pratt Ave Reconstruction and Retaining Wall, SEX20049 | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Jan 2018 | Jul 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXPRATT | Pratt Ave Reconstruction and Retaining Wall, SEX20049 | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jul 2018 | Oct 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXPRATT | Pratt Ave Reconstruction and Retaining Wall, SEX20049 | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXPRATT | Pratt Ave Reconstruction and Retaining Wall, SEX20049 | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXPRATT | Pratt Ave Reconstruction and Retaining Wall, SEX20049 | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | Jun 2019 | Oct 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXPRATT | Pratt Ave Reconstruction and Retaining Wall, SEX20049 | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Oct 2019 | Jan 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXPRATT | Pratt Ave Reconstruction and Retaining Wall, SEX20049 | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Jan 2020 | Jan 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXPRATT | Pratt Ave Reconstruction and Retaining Wall, SEX20049 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Jan 2022 | Jan 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS711 | RECONSTRUCTION OF STEP STREET AT DAVIDSON AVE (SEX002272) | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS711 | RECONSTRUCTION OF STEP STREET AT DAVIDSON AVE (SEX002272) | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS711 | RECONSTRUCTION OF STEP STREET AT DAVIDSON AVE (SEX002272) | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS711 | RECONSTRUCTION OF STEP STREET AT DAVIDSON AVE (SEX002272) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS711 | RECONSTRUCTION OF STEP STREET AT DAVIDSON AVE (SEX002272) | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS711 | RECONSTRUCTION OF STEP STREET AT DAVIDSON AVE (SEX002272) | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS711 | RECONSTRUCTION OF STEP STREET AT DAVIDSON AVE (SEX002272) | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS711 | RECONSTRUCTION OF STEP STREET AT DAVIDSON AVE (SEX002272) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS711 | RECONSTRUCTION OF STEP STREET AT DAVIDSON AVE (SEX002272) | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS711 | RECONSTRUCTION OF STEP STREET AT DAVIDSON AVE (SEX002272) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Jan 2032
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS911 | Reconstruction of the Summit Place Step Street | 1 | DEVELOP SCOPE | Jun 2021 | Sep 2021 | Jun 2025 | Sep 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS911 | Reconstruction of the Summit Place Step Street | 2 | PRELIMINARY DESIGN | Sep 2021 | Jan 2022 | Sep 2025 | Jan 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS911 | Reconstruction of the Summit Place Step Street | 3 | FINAL DESIGN | Jan 2022 | Jul 2022 | Jan 2026 | Jul 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS911 | Reconstruction of the Summit Place Step Street | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Oct 2022 | Jul 2026 | Oct 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS911 | Reconstruction of the Summit Place Step Street | 5 | CONSTRUCTION TO 25% | Oct 2022 | Feb 2023 | Oct 2026 | Feb 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS911 | Reconstruction of the Summit Place Step Street | 6 | CONSTRUCTION TO 50% | Feb 2023 | Jun 2023 | Feb 2027 | Jun 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS911 | Reconstruction of the Summit Place Step Street | 7 | CONSTRUCTION TO 75% | Jun 2023 | Oct 2023 | Jun 2027 | Oct 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS911 | Reconstruction of the Summit Place Step Street | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2023 | Jan 2024 | Oct 2027 | Jan 2028
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS911 | Reconstruction of the Summit Place Step Street | 9 | SUBSTANTIAL COMPLETION | Jan 2024 | Mar 2024 | Jan 2028 | Mar 2028
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS911 | Reconstruction of the Summit Place Step Street | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2024 | Apr 2024 | Mar 2028 | Apr 2028
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18ALELE | ALLERTON - Elevator Replacement - 3 stop | 1 | DEVELOP SCOPE | Jul 2019 | Sep 2019 | Jun 2021 | Aug 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18ALELE | ALLERTON - Elevator Replacement - 3 stop | 2 | DESIGN | Sep 2019 | Sep 2020 | Aug 2021 | Aug 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18ALELE | ALLERTON - Elevator Replacement - 3 stop | 3 | BID/ REGISTER CONTRACT | Sep 2020 | Jun 2021 | Aug 2022 | May 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18ALELE | ALLERTON - Elevator Replacement - 3 stop | 4 | CONSTRUCTION | Jun 2021 | Jun 2022 | May 2023 | May 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18ALELE | ALLERTON - Elevator Replacement - 3 stop | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2022 | Jun 2023 | May 2024 | May 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18ALELE | ALLERTON - Elevator Replacement - 3 stop | 6 | PROJECT START | Jun 2022 | Jun 2023 | May 2025 | May 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18ALELE | ALLERTON - Elevator Replacement - 3 stop | 7 | DESIGN START | Jun 2022 | Jun 2023 | May 2025 | May 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18ALELE | ALLERTON - Elevator Replacement - 3 stop | 8 | DESIGN COMPLETION | Jun 2022 | Jun 2023 | May 2025 | May 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18ALELE | ALLERTON - Elevator Replacement - 3 stop | 9 | CONSTRUCTION START | Jun 2022 | Jun 2023 | May 2025 | May 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18ALELE | ALLERTON - Elevator Replacement - 3 stop | 10 | CONSTRUCTION COMPLETION | Jun 2022 | Jun 2023 | May 2025 | May 2031
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18MRBOI | Morrisania - Boiler Replacement | 1 | DEVELOP SCOPE | Jul 2021 | Sep 2021 | Aug 2021 | Aug 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18MRBOI | Morrisania - Boiler Replacement | 2 | DESIGN START | Sep 2021 | Sep 2022 | Aug 2021 | Nov 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18MRBOI | Morrisania - Boiler Replacement | 3 | DESIGN COMPLETION | Sep 2022 | Jun 2023 | Nov 2021 | Jul 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18MRBOI | Morrisania - Boiler Replacement | 4 | CONSTRUCTION START | Jun 2023 | Jun 2024 | Jul 2022 | Jun 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18MRBOI | Morrisania - Boiler Replacement | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2024 | Jun 2025 | Jun 2023 | May 2032
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN23GDCON | GRAND CONCOURSE - Exterior Rehabilitation & HVAC | 1 | DEVELOP SCOPE | Jul 2023 | Sep 2023 | Jul 2023 | Sep 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN23GDCON | GRAND CONCOURSE - Exterior Rehabilitation & HVAC | 2 | DESIGN | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN23GDCON | GRAND CONCOURSE - Exterior Rehabilitation & HVAC | 3 | BID/ REGISTER CONTRACT | Sep 2024 | Jun 2025 | Sep 2024 | Jun 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN23GDCON | GRAND CONCOURSE - Exterior Rehabilitation & HVAC | 4 | CONSTRUCTION | Jun 2025 | Jun 2026 | Jun 2025 | Jun 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN23GDCON | GRAND CONCOURSE - Exterior Rehabilitation & HVAC | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2026 | Jun 2027 | Jun 2026 | Jun 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNBXA08LS | BRONX - Life Safety Projects @ 8 Branch Libraries | 1 | PROJECT START | Jan 2010 | Jan 2010 | Jan 2008 | Jan 2008
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNBXA08LS | BRONX - Life Safety Projects @ 8 Branch Libraries | 2 | DESIGN START | Feb 2010 | Feb 2010 | Oct 2014 | Oct 2014
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNBXA08LS | BRONX - Life Safety Projects @ 8 Branch Libraries | 3 | DESIGN COMPLETION | Feb 2010 | Feb 2010 | Oct 2014 | Oct 2014
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNBXA08LS | BRONX - Life Safety Projects @ 8 Branch Libraries | 4 | CONSTRUCTION START | Feb 2010 | Feb 2010 | Nov 2014 | Nov 2014
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNBXA08LS | BRONX - Life Safety Projects @ 8 Branch Libraries | 5 | CONSTRUCTION COMPLETION | Feb 2010 | Feb 2010 | Dec 2020 | Dec 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNC4WLEX | WOODLAWN - Branch Expansion | 1 | PROJECT START | Aug 2006 | Aug 2006 | May 2012 | May 2012
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNC4WLEX | WOODLAWN - Branch Expansion | 2 | DESIGN START | Aug 2006 | Aug 2006 | Jun 2013 | Jun 2013
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNC4WLEX | WOODLAWN - Branch Expansion | 3 | DESIGN COMPLETION | Aug 2006 | Aug 2006 | Jul 2016 | Jul 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNC4WLEX | WOODLAWN - Branch Expansion | 4 | CONSTRUCTION START | Aug 2006 | Aug 2006 | Dec 2017 | Dec 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNC4WLEX | WOODLAWN - Branch Expansion | 5 | CONSTRUCTION COMPLETION | Aug 2006 | Aug 2007 | Jan 2023 | Jun 2032
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA11BEL | BELMONT - Upper and Lower Roof | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2012 | Dec 2012 | May 2015 | May 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA11BEL | BELMONT - Upper and Lower Roof | 5 | CONSTRUCTION COMPLETION | Jun 2012 | Dec 2012 | Jun 2016 | Dec 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13ECH | EASTCHESTER: HVAC Replacement | 1 | PROJECT START | Jun 2013 | Jun 2013 | Jun 2013 | Jun 2013
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13ECH | EASTCHESTER: HVAC Replacement | 2 | DESIGN START | Dec 2014 | Dec 2014 | Dec 2014 | Jun 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13ECH | EASTCHESTER: HVAC Replacement | 3 | DESIGN COMPLETION | Jun 2018 | Jun 2018 | Jun 2021 | Jun 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13ECH | EASTCHESTER: HVAC Replacement | 4 | CONSTRUCTION START | Jul 2019 | Jul 2019 | Jun 2024 | Dec 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13ECH | EASTCHESTER: HVAC Replacement | 5 | CONSTRUCTION COMPLETION | Dec 2019 | Dec 2019 | Dec 2026 | Dec 2028
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MOR | MORRISANIA: HVAC and Roof | 1 | PROJECT START | Feb 2013 | Feb 2013 | Feb 2013 | Feb 2013
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MOR | MORRISANIA: HVAC and Roof | 2 | DESIGN START | Jun 2014 | Jun 2014 | Jun 2014 | Jun 2014
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MOR | MORRISANIA: HVAC and Roof | 3 | DESIGN COMPLETION | Mar 2015 | Mar 2015 | Mar 2015 | Mar 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MOR | MORRISANIA: HVAC and Roof | 4 | CONSTRUCTION START | Oct 2015 | Oct 2015 | Oct 2015 | Oct 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MOR | MORRISANIA: HVAC and Roof | 5 | CONSTRUCTION COMPLETION | Jul 2016 | Jul 2016 | Jul 2016 | Jul 2031
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MOT | MOTT HAVEN: HVAC | 1 | PROJECT START | Feb 2013 | Feb 2013 | Feb 2017 | Feb 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MOT | MOTT HAVEN: HVAC | 2 | DESIGN START | Aug 2014 | Aug 2014 | Feb 2017 | Jan 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MOT | MOTT HAVEN: HVAC | 3 | DESIGN COMPLETION | May 2015 | May 2015 | Jan 2023 | Oct 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MOT | MOTT HAVEN: HVAC | 4 | CONSTRUCTION START | Nov 2015 | Nov 2015 | Oct 2023 | Oct 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MOT | MOTT HAVEN: HVAC | 5 | CONSTRUCTION COMPLETION | Sep 2016 | Sep 2016 | Oct 2027 | Oct 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCL15CAS | CASTLE HILL: Partial Interior Renovation | 1 | PROJECT START | Dec 2014 | Dec 2014 | Dec 2014 | Dec 2014
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCL15CAS | CASTLE HILL: Partial Interior Renovation | 2 | DESIGN START | Dec 2014 | Dec 2014 | Dec 2014 | Dec 2014
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCL15CAS | CASTLE HILL: Partial Interior Renovation | 3 | DESIGN COMPLETION | Dec 2014 | Dec 2014 | Dec 2014 | Dec 2014
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCL15CAS | CASTLE HILL: Partial Interior Renovation | 4 | CONSTRUCTION START | Dec 2014 | Dec 2014 | Dec 2014 | Dec 2014
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCL15CAS | CASTLE HILL: Partial Interior Renovation | 5 | CONSTRUCTION COMPLETION | Aug 2018 | Aug 2018 | Aug 2018 | Jun 2028
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | 1 | DEVELOP SCOPE | Oct 2010 | Dec 2010 | Dec 2007 | Dec 2007
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | 2 | PRELIMINARY DESIGN | Dec 2010 | Apr 2011 | Dec 2011 | Dec 2011
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | 3 | FINAL DESIGN | Apr 2011 | Oct 2011 | Dec 2011 | Dec 2011
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2011 | Jan 2012 | Dec 2011 | Dec 2011
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | 5 | CONSTRUCTION TO 25% | Jan 2012 | May 2012 | Dec 2011 | Dec 2011
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | 6 | CONSTRUCTION TO 50% | May 2012 | Sep 2012 | Dec 2011 | Dec 2011
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | 7 | CONSTRUCTION TO 75% | Sep 2012 | Jan 2013 | Dec 2011 | Dec 2011
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2013 | Apr 2013 | Dec 2011 | Dec 2011
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | 9 | SUBSTANTIAL COMPLETION | Apr 2013 | Jun 2013 | Dec 2011 | Dec 2011
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2013 | Jul 2013 | Dec 2011 | Dec 2011
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | 11 | PROJECT START | Jun 2013 | Jul 2013 | Dec 2011 | Dec 2011
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | 12 | DESIGN START | Jun 2013 | Jul 2013 | Dec 2011 | May 2013
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | 13 | DESIGN COMPLETION | Jun 2013 | Jul 2013 | May 2013 | May 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | 14 | CONSTRUCTION START | Jun 2013 | Jul 2013 | May 2018 | May 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | 15 | CONSTRUCTION COMPLETION | Jun 2013 | Jul 2013 | May 2018 | May 2033
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13MHU | Mosholu: New Roof and Exterior Work | 1 | PROJECT START | Feb 2013 | Feb 2013 | Feb 2013 | Feb 2013
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13MHU | Mosholu: New Roof and Exterior Work | 2 | DESIGN START | Feb 2015 | Feb 2015 | Feb 2015 | Feb 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13MHU | Mosholu: New Roof and Exterior Work | 3 | DESIGN COMPLETION | Jul 2015 | Jul 2015 | Jul 2015 | Jul 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13MHU | Mosholu: New Roof and Exterior Work | 4 | CONSTRUCTION START | Dec 2015 | Dec 2015 | Dec 2015 | Dec 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13MHU | Mosholu: New Roof and Exterior Work | 5 | CONSTRUCTION COMPLETION | Jul 2016 | Jul 2016 | Dec 2021 | Dec 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA14VNT | HVAC Replacement | 1 | PROJECT START | Sep 2014 | Sep 2014 | Sep 2014 | Sep 2014
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA14VNT | HVAC Replacement | 2 | DESIGN START | Jun 2015 | Jun 2015 | Jun 2015 | Jun 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA14VNT | HVAC Replacement | 3 | DESIGN COMPLETION | Oct 2015 | Oct 2015 | Oct 2015 | Oct 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA14VNT | HVAC Replacement | 4 | CONSTRUCTION START | Apr 2016 | Apr 2016 | Apr 2016 | Apr 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA14VNT | HVAC Replacement | 5 | CONSTRUCTION COMPLETION | Feb 2017 | Feb 2017 | Feb 2021 | Feb 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA11WFM | WEST FARMS - New Front Entry | 1 | DESIGN | Oct 2010 | Mar 2011 | Jan 2011 | Jan 2011
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA11WFM | WEST FARMS - New Front Entry | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2011 | Jun 2011 | Jul 2012 | Jul 2012
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA11WFM | WEST FARMS - New Front Entry | 3 | CONSTRUCTION | Jun 2011 | Jun 2012 | May 2019 | May 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA11WFM | WEST FARMS - New Front Entry | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2012 | Dec 2012 | Mar 2021 | Mar 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA11WFM | WEST FARMS - New Front Entry | 5 | CONSTRUCTION COMPLETION | Jun 2012 | Dec 2012 | Jan 2022 | Jan 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA12GRC | GRAND CONCOURSE - ADA Compliance and Related Work | 1 | DEVELOP SCOPE | Sep 2012 | Dec 2012 | Jan 2012 | Jan 2012
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA12GRC | GRAND CONCOURSE - ADA Compliance and Related Work | 2 | PRELIMINARY DESIGN | Dec 2012 | Apr 2013 | Apr 2013 | Apr 2013
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA12GRC | GRAND CONCOURSE - ADA Compliance and Related Work | 3 | FINAL DESIGN | Apr 2013 | Oct 2013 | Aug 2015 | Aug 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA12GRC | GRAND CONCOURSE - ADA Compliance and Related Work | 4 | BID AWARD AND REGISTER CONTRCT | Oct 2013 | Jan 2014 | Apr 2016 | Apr 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA12GRC | GRAND CONCOURSE - ADA Compliance and Related Work | 5 | CONSTRUCTION TO 25% | Jan 2014 | May 2014 | May 2021 | May 2031
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA12GRC | GRAND CONCOURSE - ADA Compliance and Related Work | 6 | CONSTRUCTION TO 50% | May 2014 | Sep 2014 | May 2021 | May 2031
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA12GRC | GRAND CONCOURSE - ADA Compliance and Related Work | 7 | CONSTRUCTION TO 75% | Sep 2014 | Jan 2015 | May 2021 | May 2031
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA12GRC | GRAND CONCOURSE - ADA Compliance and Related Work | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2015 | Apr 2015 | May 2021 | May 2031
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA12GRC | GRAND CONCOURSE - ADA Compliance and Related Work | 9 | SUBSTANTIAL COMPLETION | Apr 2015 | Jun 2015 | May 2021 | May 2031
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA12GRC | GRAND CONCOURSE - ADA Compliance and Related Work | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2015 | Jul 2015 | May 2021 | May 2031
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA20WKF | Wakefield - Infrastructure and ADA Upgrades | 1 | DEVELOP SCOPE | Sep 2019 | Dec 2019 | Sep 2019 | Dec 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA20WKF | Wakefield - Infrastructure and ADA Upgrades | 2 | DESIGN | Dec 2019 | Dec 2020 | Dec 2019 | Dec 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA20WKF | Wakefield - Infrastructure and ADA Upgrades | 3 | BID/ REGISTER CONTRACT | Dec 2020 | Sep 2021 | Dec 2020 | Sep 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA20WKF | Wakefield - Infrastructure and ADA Upgrades | 4 | CONSTRUCTION | Sep 2021 | Mar 2023 | Sep 2021 | Mar 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA20WKF | Wakefield - Infrastructure and ADA Upgrades | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2023 | Mar 2024 | Mar 2023 | Mar 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA20WKF | Wakefield - Infrastructure and ADA Upgrades | 6 | PROJECT START | Mar 2023 | Mar 2024 | Mar 2024 | Mar 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA20WKF | Wakefield - Infrastructure and ADA Upgrades | 7 | DESIGN START | Mar 2023 | Mar 2024 | Mar 2024 | Mar 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA20WKF | Wakefield - Infrastructure and ADA Upgrades | 8 | DESIGN COMPLETION | Mar 2023 | Mar 2024 | Mar 2024 | Mar 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA20WKF | Wakefield - Infrastructure and ADA Upgrades | 9 | CONSTRUCTION START | Mar 2023 | Mar 2024 | Mar 2024 | Mar 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA20WKF | Wakefield - Infrastructure and ADA Upgrades | 10 | CONSTRUCTION COMPLETION | Mar 2023 | Mar 2024 | Mar 2024 | Mar 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXEA08BA | BAYCHESTER: HVAC | 1 | PROJECT START | Jan 2008 | Jan 2008 | Nov 2015 | Nov 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXEA08BA | BAYCHESTER: HVAC | 2 | DESIGN START | Oct 2009 | Oct 2009 | Nov 2015 | Nov 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXEA08BA | BAYCHESTER: HVAC | 3 | DESIGN COMPLETION | Oct 2011 | Oct 2011 | Nov 2015 | Jul 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXEA08BA | BAYCHESTER: HVAC | 4 | CONSTRUCTION START | Dec 2014 | Dec 2014 | Jul 2017 | Jul 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXEA08BA | BAYCHESTER: HVAC | 5 | CONSTRUCTION COMPLETION | Feb 2016 | Feb 2016 | Jul 2020 | Jan 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-DAVID | NDF - DAVIDSON AVE COMMUNITY CENTER | 1 | DEVELOP SCOPE | Jun 2021 | Aug 2021 | Jun 2021 | Aug 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-DAVID | NDF - DAVIDSON AVE COMMUNITY CENTER | 2 | PRELIMINARY DESIGN | Aug 2021 | Dec 2021 | Aug 2021 | Dec 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-DAVID | NDF - DAVIDSON AVE COMMUNITY CENTER | 3 | FINAL DESIGN | Dec 2021 | Jun 2022 | Dec 2021 | Jun 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-DAVID | NDF - DAVIDSON AVE COMMUNITY CENTER | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-DAVID | NDF - DAVIDSON AVE COMMUNITY CENTER | 5 | CONSTRUCTION TO 25% | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-DAVID | NDF - DAVIDSON AVE COMMUNITY CENTER | 6 | CONSTRUCTION TO 50% | Jan 2023 | May 2023 | Jan 2023 | May 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-DAVID | NDF - DAVIDSON AVE COMMUNITY CENTER | 7 | CONSTRUCTION TO 75% | May 2023 | Sep 2023 | May 2023 | Sep 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-DAVID | NDF - DAVIDSON AVE COMMUNITY CENTER | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Dec 2023 | Sep 2023 | Dec 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-DAVID | NDF - DAVIDSON AVE COMMUNITY CENTER | 9 | SUBSTANTIAL COMPLETION | Dec 2023 | Feb 2024 | Dec 2023 | Feb 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-DAVID | NDF - DAVIDSON AVE COMMUNITY CENTER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2024 | Mar 2024 | Feb 2024 | Mar 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-JEROM | Jerome Avenue Safety Improvements NDF Funding (HWXJEROME) | 1 | DESIGN | Jul 2019 | Jul 2019 | Jul 2019 | Jul 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-JEROM | Jerome Avenue Safety Improvements NDF Funding (HWXJEROME) | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jul 2019 | Aug 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-JEROM | Jerome Avenue Safety Improvements NDF Funding (HWXJEROME) | 3 | CONSTRUCTION | Aug 2019 | Sep 2019 | Aug 2019 | Sep 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-JEROM | Jerome Avenue Safety Improvements NDF Funding (HWXJEROME) | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Sep 2019 | Sep 2019 | Sep 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-JEROM | Jerome Avenue Safety Improvements NDF Funding (HWXJEROME) | 5 | SUBSTANTIAL COMPLETION | Sep 2019 | Oct 2019 | Sep 2019 | Oct 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-JEROM | Jerome Avenue Safety Improvements NDF Funding (HWXJEROME) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2019 | Oct 2023 | Oct 2019 | Oct 2028
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-SCH4D | School Safety 4D NDF Funding, HWCSCH4D | 1 | DESIGN | Jul 2019 | Jul 2019 | Jul 2021 | Jul 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-SCH4D | School Safety 4D NDF Funding, HWCSCH4D | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2019 | Aug 2019 | Jul 2026 | Aug 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-SCH4D | School Safety 4D NDF Funding, HWCSCH4D | 3 | CONSTRUCTION | Aug 2019 | Sep 2019 | Aug 2026 | Sep 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-SCH4D | School Safety 4D NDF Funding, HWCSCH4D | 4 | ORIGINAL EQUIP & FURNISHING | Sep 2019 | Sep 2019 | Sep 2026 | Sep 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-SCH4D | School Safety 4D NDF Funding, HWCSCH4D | 5 | SUBSTANTIAL COMPLETION | Sep 2019 | Oct 2019 | Sep 2026 | Oct 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-SCH4D | School Safety 4D NDF Funding, HWCSCH4D | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2019 | Oct 2021 | Oct 2026 | Oct 2032
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NEWHJC2 | NEW CONSTRUCTION AT HORIZON JC PHASE 2.0 | 1 | DESIGN | Jan 2023 | Jul 2023 | Jan 2023 | Jul 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NEWHJC2 | NEW CONSTRUCTION AT HORIZON JC PHASE 2.0 | 2 | CONSTRUCTION | Jul 2023 | Jun 2024 | Jul 2023 | Jun 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NEWHJC2 | NEW CONSTRUCTION AT HORIZON JC PHASE 2.0 | 3 | PROJECT START | Jul 2023 | Jun 2024 | Jul 2024 | Jul 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NEWHJC2 | NEW CONSTRUCTION AT HORIZON JC PHASE 2.0 | 4 | DESIGN START | Jul 2023 | Jun 2024 | Jul 2024 | Jul 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NEWHJC2 | NEW CONSTRUCTION AT HORIZON JC PHASE 2.0 | 5 | DESIGN COMPLETION | Jul 2023 | Jun 2024 | Jul 2024 | Jul 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NEWHJC2 | NEW CONSTRUCTION AT HORIZON JC PHASE 2.0 | 6 | CONSTRUCTION START | Jul 2023 | Jun 2024 | Jul 2024 | Jul 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NEWHJC2 | NEW CONSTRUCTION AT HORIZON JC PHASE 2.0 | 7 | CONSTRUCTION COMPLETION | Jul 2023 | Jun 2024 | Jul 2024 | Jul 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-102DELV | Del Valle Square X009-111M | 1 | DEVELOP SCOPE | Mar 2018 | May 2018 | Mar 2018 | May 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-102DELV | Del Valle Square X009-111M | 2 | PRELIMINARY DESIGN | May 2018 | Sep 2018 | May 2018 | Sep 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-102DELV | Del Valle Square X009-111M | 3 | FINAL DESIGN | Sep 2018 | Mar 2019 | Sep 2018 | Mar 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-102DELV | Del Valle Square X009-111M | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2019 | Jun 2019 | Mar 2019 | Jun 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-102DELV | Del Valle Square X009-111M | 5 | CONSTRUCTION TO 25% | Jun 2019 | Oct 2019 | Jun 2019 | Oct 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-102DELV | Del Valle Square X009-111M | 6 | CONSTRUCTION TO 50% | Oct 2019 | Feb 2020 | Oct 2019 | Feb 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-102DELV | Del Valle Square X009-111M | 7 | CONSTRUCTION TO 75% | Feb 2020 | Jun 2020 | Feb 2020 | Jun 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-102DELV | Del Valle Square X009-111M | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2020 | Sep 2020 | Jun 2020 | Sep 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-102DELV | Del Valle Square X009-111M | 9 | SUBSTANTIAL COMPLETION | Sep 2020 | Nov 2020 | Sep 2020 | Nov 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-102DELV | Del Valle Square X009-111M | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2020 | Dec 2020 | Nov 2020 | Oct 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-108VCCS | Van Cortlandt Park - Construction of a new restroom | 1 | DEVELOP SCOPE | Jul 2022 | Dec 2022 | Jul 2022 | Dec 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-108VCCS | Van Cortlandt Park - Construction of a new restroom | 2 | DESIGN | Dec 2022 | Dec 2023 | Dec 2022 | Dec 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-108VCCS | Van Cortlandt Park - Construction of a new restroom | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-108VCCS | Van Cortlandt Park - Construction of a new restroom | 4 | CONSTRUCTION | Sep 2024 | Mar 2026 | Sep 2024 | Mar 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-108VCCS | Van Cortlandt Park - Construction of a new restroom | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2026 | Mar 2027 | Mar 2026 | Mar 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P109STARA | STARLIGHT PARK COMFORT STATION X147-111M | 1 | PROJECT START | Feb 2012 | Feb 2012 | Apr 2014 | May 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P109STARA | STARLIGHT PARK COMFORT STATION X147-111M | 2 | DESIGN START | Feb 2012 | Mar 2013 | May 2015 | Jul 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P109STARA | STARLIGHT PARK COMFORT STATION X147-111M | 3 | DESIGN COMPLETION | Mar 2013 | Mar 2014 | Jul 2016 | Aug 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P109STARA | STARLIGHT PARK COMFORT STATION X147-111M | 4 | CONSTRUCTION START | Mar 2014 | Oct 2015 | Aug 2019 | Mar 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P109STARA | STARLIGHT PARK COMFORT STATION X147-111M | 5 | CONSTRUCTION COMPLETION | Oct 2015 | Nov 2015 | Mar 2021 | Aug 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1CROT16A | BRONX RIVER GRWAY RIVER HOUSE IN STARLIGHT PK X147-107M/407M | 2 | DESIGN START | Jan 2011 | Nov 2011 | Jan 2011 | Nov 2011
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1CROT16A | BRONX RIVER GRWAY RIVER HOUSE IN STARLIGHT PK X147-107M/407M | 3 | DESIGN COMPLETION | Nov 2011 | Jan 2013 | Nov 2011 | Jan 2013
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1CROT16A | BRONX RIVER GRWAY RIVER HOUSE IN STARLIGHT PK X147-107M/407M | 4 | CONSTRUCTION START | Jan 2013 | Mar 2014 | Jan 2013 | Mar 2014
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1CROT16A | BRONX RIVER GRWAY RIVER HOUSE IN STARLIGHT PK X147-107M/407M | 5 | CONSTRUCTION COMPLETION | Mar 2014 | May 2015 | Mar 2014 | Jan 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1HARTIS | Hart Island | 1 | DEVELOP SCOPE | Jul 2020 | Dec 2020 | Jul 2020 | Dec 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1HARTIS | Hart Island | 2 | DESIGN | Dec 2020 | Dec 2021 | Dec 2020 | Dec 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1HARTIS | Hart Island | 3 | BID/ REGISTER CONTRACT | Dec 2021 | Sep 2022 | Dec 2021 | Sep 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1HARTIS | Hart Island | 4 | CONSTRUCTION | Sep 2022 | Sep 2023 | Sep 2022 | Sep 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1HARTIS | Hart Island | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2023 | Sep 2024 | Sep 2023 | Sep 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1ORCHMO | Orchard Beach M&O Facility Reconstruction DB | 1 | DEVELOP SCOPE | Oct 2016 | Apr 2017 | Oct 2018 | Apr 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1ORCHMO | Orchard Beach M&O Facility Reconstruction DB | 2 | DESIGN | Apr 2017 | Apr 2019 | Apr 2019 | Apr 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1ORCHMO | Orchard Beach M&O Facility Reconstruction DB | 3 | BID/ REGISTER CONTRACT | Apr 2019 | Jan 2020 | Apr 2021 | Jan 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1ORCHMO | Orchard Beach M&O Facility Reconstruction DB | 4 | CONSTRUCTION | Jan 2020 | Jan 2023 | Jan 2022 | Jan 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1ORCHMO | Orchard Beach M&O Facility Reconstruction DB | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Jan 2023 | Jan 2024 | Jan 2025 | Jan 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1SDVREC | Construction of a New Recreation Center at Soundview Park | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1SDVREC | Construction of a New Recreation Center at Soundview Park | 2 | DESIGN | Dec 2021 | Dec 2023 | Dec 2021 | Dec 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1SDVREC | Construction of a New Recreation Center at Soundview Park | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1SDVREC | Construction of a New Recreation Center at Soundview Park | 4 | CONSTRUCTION | Sep 2024 | Sep 2027 | Sep 2024 | Sep 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1SDVREC | Construction of a New Recreation Center at Soundview Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Sep 2029 | Sep 2027 | Sep 2029
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1STARLP | BRONX RIVER GREENWAY: STARLIGHT PARK PHASE II, STAGE 2, BX | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Aug 2014 | Feb 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1STARLP | BRONX RIVER GREENWAY: STARLIGHT PARK PHASE II, STAGE 2, BX | 2 | DESIGN | Sep 2015 | Dec 2015 | Feb 2015 | May 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1STARLP | BRONX RIVER GREENWAY: STARLIGHT PARK PHASE II, STAGE 2, BX | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | May 2016 | Feb 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1STARLP | BRONX RIVER GREENWAY: STARLIGHT PARK PHASE II, STAGE 2, BX | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Feb 2017 | Feb 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1STARLP | BRONX RIVER GREENWAY: STARLIGHT PARK PHASE II, STAGE 2, BX | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Feb 2018 | May 2028
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1TREREC | Construction of a New Recreation Center at Tremont Park | 1 | DEVELOP SCOPE | Jul 2021 | Dec 2021 | Jul 2021 | Dec 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1TREREC | Construction of a New Recreation Center at Tremont Park | 2 | DESIGN | Dec 2021 | Dec 2023 | Dec 2021 | Dec 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1TREREC | Construction of a New Recreation Center at Tremont Park | 3 | BID/ REGISTER CONTRACT | Dec 2023 | Sep 2024 | Dec 2023 | Sep 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1TREREC | Construction of a New Recreation Center at Tremont Park | 4 | CONSTRUCTION | Sep 2024 | Sep 2027 | Sep 2024 | Sep 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1TREREC | Construction of a New Recreation Center at Tremont Park | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2027 | Sep 2029 | Sep 2027 | Sep 2029
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1VCPDBR | Vancortlandt Park pedestrian bridge | 1 | DEVELOP SCOPE | Jul 2015 | Sep 2015 | Jul 2015 | Dec 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1VCPDBR | Vancortlandt Park pedestrian bridge | 2 | DESIGN | Sep 2015 | Dec 2015 | Dec 2015 | Jun 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1VCPDBR | Vancortlandt Park pedestrian bridge | 3 | BID/ REGISTER CONTRACT | Dec 2015 | Mar 2016 | Jul 2019 | Oct 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1VCPDBR | Vancortlandt Park pedestrian bridge | 4 | CONSTRUCTION | Mar 2016 | Mar 2017 | Oct 2023 | Oct 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1VCPDBR | Vancortlandt Park pedestrian bridge | 5 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2017 | Mar 2018 | Oct 2024 | Mar 2031
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1YANK15A | Bronx Children's Museum Fitout | 1 | PROJECT START | Jul 2012 | Jul 2012 | Jul 2012 | Apr 2013
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1YANK15A | Bronx Children's Museum Fitout | 2 | DESIGN START | Jul 2012 | Apr 2013 | Apr 2013 | Jun 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1YANK15A | Bronx Children's Museum Fitout | 3 | DESIGN COMPLETION | Apr 2013 | Jul 2015 | Jun 2015 | Jul 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1YANK15A | Bronx Children's Museum Fitout | 4 | CONSTRUCTION START | Jul 2015 | Mar 2016 | Jul 2016 | Jun 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1YANK15A | Bronx Children's Museum Fitout | 5 | CONSTRUCTION COMPLETION | Mar 2016 | Nov 2018 | Jun 2017 | Feb 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1YANK15A | Bronx Children's Museum Fitout | 6 | CONSTRUCTION TO 50% | Mar 2016 | Nov 2018 | Feb 2018 | Oct 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1YANK15A | Bronx Children's Museum Fitout | 7 | CONSTRUCTION TO 75% | Mar 2016 | Nov 2018 | Oct 2018 | Oct 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1YANK15A | Bronx Children's Museum Fitout | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2016 | Nov 2018 | Oct 2019 | Jan 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1YANK15A | Bronx Children's Museum Fitout | 9 | SUBSTANTIAL COMPLETION | Mar 2016 | Nov 2018 | Jan 2020 | May 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1YANK15A | Bronx Children's Museum Fitout | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Nov 2018 | May 2020 | Dec 2032
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDBNX | BRONX FRONT DESK REPLACEMENT 42ND, 44TH, 46TH, 108TH | 1 | PROJECT START | Mar 2018 | Mar 2018 | Mar 2018 | Mar 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDBNX | BRONX FRONT DESK REPLACEMENT 42ND, 44TH, 46TH, 108TH | 2 | DESIGN START | Mar 2018 | Mar 2018 | Mar 2018 | Mar 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDBNX | BRONX FRONT DESK REPLACEMENT 42ND, 44TH, 46TH, 108TH | 3 | DESIGN COMPLETION | Mar 2018 | Mar 2018 | Mar 2018 | Mar 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDBNX | BRONX FRONT DESK REPLACEMENT 42ND, 44TH, 46TH, 108TH | 4 | CONSTRUCTION START | Mar 2018 | Mar 2018 | Mar 2018 | Mar 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDBNX | BRONX FRONT DESK REPLACEMENT 42ND, 44TH, 46TH, 108TH | 5 | CONSTRUCTION COMPLETION | Mar 2018 | Mar 2018 | Mar 2018 | Jun 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79ROD | NEW FIREARMS TRAINING FACILITY | 1 | DESIGN | Jun 2017 | Dec 2017 | Jun 2017 | Jul 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79ROD | NEW FIREARMS TRAINING FACILITY | 2 | BID AWARD AND REGISTER CONTRCT | Dec 2017 | Mar 2018 | Jul 2017 | Sep 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79ROD | NEW FIREARMS TRAINING FACILITY | 3 | CONSTRUCTION | Mar 2018 | Mar 2019 | Sep 2018 | Apr 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79ROD | NEW FIREARMS TRAINING FACILITY | 4 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2019 | Sep 2019 | Apr 2021 | Jan 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79ROD | NEW FIREARMS TRAINING FACILITY | 5 | CONSTRUCTION COMPLETION | Mar 2019 | Sep 2019 | Jan 2022 | Jul 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV176CESU | WCS - Bronx Zoo - Con Ed Switchgear Upgrade | 1 | PROJECT START | Feb 2014 | Feb 2014 | Oct 2013 | Oct 2013
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV176CESU | WCS - Bronx Zoo - Con Ed Switchgear Upgrade | 2 | DESIGN START | Feb 2014 | Dec 2014 | Oct 2015 | Feb 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV176CESU | WCS - Bronx Zoo - Con Ed Switchgear Upgrade | 3 | DESIGN COMPLETION | Dec 2014 | Dec 2015 | Feb 2020 | Nov 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV176CESU | WCS - Bronx Zoo - Con Ed Switchgear Upgrade | 4 | CONSTRUCTION START | Dec 2015 | Jul 2016 | Dec 2025 | Jun 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV176CESU | WCS - Bronx Zoo - Con Ed Switchgear Upgrade | 5 | CONSTRUCTION COMPLETION | Jul 2016 | Jul 2017 | Jun 2026 | Jul 2030
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV176ITF1 | WCS - Bronx Zoo Parking Lot Improvements | 1 | CONSTRUCTION | Sep 2013 | Sep 2014 | Jul 2011 | Sep 2011
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV176ITF1 | WCS - Bronx Zoo Parking Lot Improvements | 2 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2014 | Sep 2015 | Sep 2011 | Sep 2012
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV176ITF1 | WCS - Bronx Zoo Parking Lot Improvements | 3 | PUNCHLIST COMPLETE, JOB CLOSED | Sep 2014 | Sep 2015 | Sep 2012 | Sep 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV176ITF1 | WCS - Bronx Zoo Parking Lot Improvements | 4 | PROJECT START | Sep 2014 | Sep 2015 | Sep 2015 | Sep 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV176ITF1 | WCS - Bronx Zoo Parking Lot Improvements | 5 | DESIGN START | Sep 2014 | Sep 2015 | Sep 2015 | Sep 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV176ITF1 | WCS - Bronx Zoo Parking Lot Improvements | 6 | DESIGN COMPLETION | Sep 2014 | Sep 2015 | Sep 2015 | Sep 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV176ITF1 | WCS - Bronx Zoo Parking Lot Improvements | 7 | CONSTRUCTION START | Sep 2014 | Sep 2015 | Sep 2015 | Sep 2015
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV176ITF1 | WCS - Bronx Zoo Parking Lot Improvements | 8 | CONSTRUCTION COMPLETION | Sep 2014 | Sep 2015 | Sep 2015 | Sep 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV205CHIL | NYBG - Children's Adventure Garden Renovations | 1 | PROJECT START | Apr 2019 | Apr 2019 | Apr 2019 | Apr 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV205CHIL | NYBG - Children's Adventure Garden Renovations | 2 | DESIGN START | Apr 2019 | Apr 2019 | Apr 2019 | Apr 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV205CHIL | NYBG - Children's Adventure Garden Renovations | 3 | DESIGN COMPLETION | Apr 2019 | Apr 2019 | Apr 2019 | Apr 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV205CHIL | NYBG - Children's Adventure Garden Renovations | 4 | CONSTRUCTION START | Apr 2019 | Apr 2019 | Apr 2019 | Apr 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV205CHIL | NYBG - Children's Adventure Garden Renovations | 5 | CONSTRUCTION COMPLETION | Apr 2019 | Apr 2025 | Apr 2019 | Apr 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77198CT | 198 E 161 ST.- COOLING TOWER REPLACEMENT | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Aug 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77198CT | 198 E 161 ST.- COOLING TOWER REPLACEMENT | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77198CT | 198 E 161 ST.- COOLING TOWER REPLACEMENT | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77198CT | 198 E 161 ST.- COOLING TOWER REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77198CT | 198 E 161 ST.- COOLING TOWER REPLACEMENT | 5 | CONSTRUCTION TO 25% | Sep 2022 | May 2023 | Sep 2022 | May 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77198CT | 198 E 161 ST.- COOLING TOWER REPLACEMENT | 6 | CONSTRUCTION TO 50% | May 2023 | Sep 2023 | May 2023 | Sep 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77198CT | 198 E 161 ST.- COOLING TOWER REPLACEMENT | 7 | CONSTRUCTION TO 75% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77198CT | 198 E 161 ST.- COOLING TOWER REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | Jan 2024 | Apr 2024 | Jan 2024 | Apr 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77198CT | 198 E 161 ST.- COOLING TOWER REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | Apr 2024 | Jun 2024 | Apr 2024 | Jun 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77198CT | 198 E 161 ST.- COOLING TOWER REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jun 2024 | Jul 2024 | Jun 2024 | Jul 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77198CT | 198 E 161 ST.- COOLING TOWER REPLACEMENT | 11 | PROJECT START | Jun 2024 | Jul 2024 | Jul 2024 | Jul 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77198CT | 198 E 161 ST.- COOLING TOWER REPLACEMENT | 12 | DESIGN START | Jun 2024 | Jul 2024 | Jul 2024 | Jul 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77198CT | 198 E 161 ST.- COOLING TOWER REPLACEMENT | 13 | DESIGN COMPLETION | Jun 2024 | Jul 2024 | Jul 2024 | Jul 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77198CT | 198 E 161 ST.- COOLING TOWER REPLACEMENT | 14 | CONSTRUCTION START | Jun 2024 | Jul 2024 | Jul 2024 | Jul 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77198CT | 198 E 161 ST.- COOLING TOWER REPLACEMENT | 15 | CONSTRUCTION COMPLETION | Jun 2024 | Jul 2024 | Jul 2024 | Jul 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWX78BXP | BRONX BOROUGH PRESIDENT'S OFFICE INITIAL OUT-FITTING | 1 | PROJECT START | Jun 2016 | Jun 2016 | Jun 2016 | Jun 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWX78BXP | BRONX BOROUGH PRESIDENT'S OFFICE INITIAL OUT-FITTING | 2 | DESIGN START | Jul 2016 | Sep 2016 | Jul 2016 | Sep 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWX78BXP | BRONX BOROUGH PRESIDENT'S OFFICE INITIAL OUT-FITTING | 3 | DESIGN COMPLETION | Oct 2016 | Apr 2017 | Oct 2016 | Apr 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWX78BXP | BRONX BOROUGH PRESIDENT'S OFFICE INITIAL OUT-FITTING | 4 | CONSTRUCTION START | May 2017 | Oct 2017 | May 2017 | Oct 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWX78BXP | BRONX BOROUGH PRESIDENT'S OFFICE INITIAL OUT-FITTING | 5 | CONSTRUCTION COMPLETION | Oct 2017 | Oct 2023 | Oct 2017 | Oct 2032
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXDAVDCC | DCAS/DAVIDSON COMMUNITY CENTER - CONSTRUCT 2 ADDITIONAL FLOO | 1 | DEVELOP SCOPE | Jun 2021 | Aug 2021 | Jun 2028 | Aug 2028
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXDAVDCC | DCAS/DAVIDSON COMMUNITY CENTER - CONSTRUCT 2 ADDITIONAL FLOO | 2 | PRELIMINARY DESIGN | Aug 2021 | Dec 2021 | Aug 2028 | Dec 2028
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXDAVDCC | DCAS/DAVIDSON COMMUNITY CENTER - CONSTRUCT 2 ADDITIONAL FLOO | 3 | FINAL DESIGN | Dec 2021 | Jun 2022 | Dec 2028 | Jun 2029
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXDAVDCC | DCAS/DAVIDSON COMMUNITY CENTER - CONSTRUCT 2 ADDITIONAL FLOO | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Sep 2022 | Jun 2029 | Sep 2029
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXDAVDCC | DCAS/DAVIDSON COMMUNITY CENTER - CONSTRUCT 2 ADDITIONAL FLOO | 5 | CONSTRUCTION TO 25% | Sep 2022 | Jan 2023 | Sep 2029 | Jan 2030
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXDAVDCC | DCAS/DAVIDSON COMMUNITY CENTER - CONSTRUCT 2 ADDITIONAL FLOO | 6 | CONSTRUCTION TO 50% | Jan 2023 | May 2023 | Jan 2030 | May 2030
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXDAVDCC | DCAS/DAVIDSON COMMUNITY CENTER - CONSTRUCT 2 ADDITIONAL FLOO | 7 | CONSTRUCTION TO 75% | May 2023 | Sep 2023 | May 2030 | Sep 2030
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXDAVDCC | DCAS/DAVIDSON COMMUNITY CENTER - CONSTRUCT 2 ADDITIONAL FLOO | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Dec 2023 | Sep 2030 | Dec 2030
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXDAVDCC | DCAS/DAVIDSON COMMUNITY CENTER - CONSTRUCT 2 ADDITIONAL FLOO | 9 | SUBSTANTIAL COMPLETION | Dec 2023 | Feb 2024 | Dec 2030 | Feb 2031
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXDAVDCC | DCAS/DAVIDSON COMMUNITY CENTER - CONSTRUCT 2 ADDITIONAL FLOO | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2024 | Mar 2024 | Feb 2031 | Mar 2031
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXFITWEL | FITNESS AND WELLNESS CENTER | 1 | PROJECT START | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXFITWEL | FITNESS AND WELLNESS CENTER | 2 | DESIGN START | Jul 2024 | Jul 2025 | Jul 2024 | Jul 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXFITWEL | FITNESS AND WELLNESS CENTER | 3 | DESIGN COMPLETION | Jul 2026 | Jun 2027 | Jul 2026 | Jun 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXFITWEL | FITNESS AND WELLNESS CENTER | 4 | CONSTRUCTION START | Jul 2027 | Jul 2028 | Jul 2027 | Jul 2028
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXFITWEL | FITNESS AND WELLNESS CENTER | 5 | CONSTRUCTION COMPLETION | Jul 2028 | Jul 2029 | Jul 2028 | Jul 2029
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXTNLLRE | Throgs Neck Little League- Infrastructure Rehabilitation | 1 | PROJECT START | Jun 2016 | Jun 2016 | Jun 2016 | Jun 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXTNLLRE | Throgs Neck Little League- Infrastructure Rehabilitation | 2 | DESIGN START | Jul 2016 | Oct 2016 | Jul 2017 | Jul 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXTNLLRE | Throgs Neck Little League- Infrastructure Rehabilitation | 3 | DESIGN COMPLETION | Oct 2016 | Feb 2017 | Jul 2018 | Aug 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXTNLLRE | Throgs Neck Little League- Infrastructure Rehabilitation | 4 | CONSTRUCTION START | Mar 2017 | Aug 2017 | Aug 2019 | Jan 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXTNLLRE | Throgs Neck Little League- Infrastructure Rehabilitation | 5 | CONSTRUCTION COMPLETION | Aug 2017 | Aug 2024 | Jan 2020 | Jan 2031
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXTNLLS | Throgs Neck Little League- Solar Panel and Infrastructure | 1 | PROJECT START | Jun 2022 | Jun 2022 | Jun 2022 | Jun 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXTNLLS | Throgs Neck Little League- Solar Panel and Infrastructure | 2 | DESIGN START | Jul 2022 | Jul 2022 | Jul 2022 | Jul 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXTNLLS | Throgs Neck Little League- Solar Panel and Infrastructure | 3 | DESIGN COMPLETION | Jul 2022 | Jul 2022 | Jul 2022 | Jul 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXTNLLS | Throgs Neck Little League- Solar Panel and Infrastructure | 4 | CONSTRUCTION START | Jul 2022 | Jul 2022 | Jul 2022 | Jul 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXTNLLS | Throgs Neck Little League- Solar Panel and Infrastructure | 5 | CONSTRUCTION COMPLETION | Aug 2022 | Aug 2022 | Aug 2022 | Jun 2031
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | RWX020 | RETAINING WALL - JEROME AV NB AFTER E 196 ST | 1 | DEVELOP SCOPE | Feb 2012 | May 2012 | Feb 2012 | May 2012
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | RWX020 | RETAINING WALL - JEROME AV NB AFTER E 196 ST | 2 | PRELIMINARY DESIGN | May 2012 | Sep 2012 | May 2012 | Sep 2012
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | RWX020 | RETAINING WALL - JEROME AV NB AFTER E 196 ST | 3 | FINAL DESIGN | Sep 2012 | Mar 2013 | Sep 2012 | Mar 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | RWX020 | RETAINING WALL - JEROME AV NB AFTER E 196 ST | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2013 | Jun 2013 | Mar 2016 | Jun 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | RWX020 | RETAINING WALL - JEROME AV NB AFTER E 196 ST | 5 | CONSTRUCTION TO 25% | Jun 2013 | Oct 2013 | Jun 2016 | Sep 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | RWX020 | RETAINING WALL - JEROME AV NB AFTER E 196 ST | 6 | CONSTRUCTION TO 50% | Oct 2013 | Feb 2014 | Oct 2016 | Jan 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | RWX020 | RETAINING WALL - JEROME AV NB AFTER E 196 ST | 7 | CONSTRUCTION TO 75% | Feb 2014 | Jun 2014 | Jan 2017 | May 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | RWX020 | RETAINING WALL - JEROME AV NB AFTER E 196 ST | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2014 | Sep 2014 | May 2017 | Aug 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | RWX020 | RETAINING WALL - JEROME AV NB AFTER E 196 ST | 9 | SUBSTANTIAL COMPLETION | Sep 2014 | Nov 2014 | Aug 2017 | Jan 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | RWX020 | RETAINING WALL - JEROME AV NB AFTER E 196 ST | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2014 | Dec 2014 | Jan 2019 | Aug 2032
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | 1 | DEVELOP SCOPE | Jun 2013 | Sep 2013 | Aug 2016 | Nov 2016
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | 2 | PRELIMINARY DESIGN | Sep 2013 | Jan 2014 | Nov 2016 | Mar 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | 3 | FINAL DESIGN | Jan 2014 | Jul 2014 | Mar 2017 | Sep 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2014 | Oct 2014 | Sep 2017 | Dec 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | 5 | CONSTRUCTION TO 25% | Oct 2014 | Feb 2015 | Dec 2017 | Apr 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | 6 | CONSTRUCTION TO 50% | Feb 2015 | Jun 2015 | Apr 2018 | Aug 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | 7 | CONSTRUCTION TO 75% | Jun 2015 | Oct 2015 | Aug 2018 | Dec 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2015 | Jan 2016 | Dec 2018 | Mar 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | 9 | SUBSTANTIAL COMPLETION | Jan 2016 | Mar 2016 | Mar 2019 | May 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2016 | Apr 2016 | May 2019 | Sep 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | 11 | PROJECT START | Mar 2016 | Apr 2016 | Apr 2013 | May 2013
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | 12 | DESIGN START | Mar 2016 | Apr 2016 | May 2013 | Apr 2014
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | 13 | DESIGN COMPLETION | Mar 2016 | Apr 2016 | Apr 2014 | Jun 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | 14 | CONSTRUCTION START | Mar 2016 | Apr 2016 | Jul 2017 | Dec 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | 15 | CONSTRUCTION COMPLETION | Mar 2016 | Apr 2016 | Dec 2017 | Jun 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SE849 | Dist WM SE Rplmt in Southeast Clason Point, BX | 1 | DEVELOP SCOPE | Jun 2026 | Aug 2026 | Jun 2024 | Aug 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SE849 | Dist WM SE Rplmt in Southeast Clason Point, BX | 2 | PRELIMINARY DESIGN | Aug 2026 | Dec 2026 | Aug 2024 | Dec 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SE849 | Dist WM SE Rplmt in Southeast Clason Point, BX | 3 | FINAL DESIGN | Dec 2026 | Jun 2027 | Dec 2024 | Jun 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SE849 | Dist WM SE Rplmt in Southeast Clason Point, BX | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2027 | Sep 2027 | Jun 2025 | Sep 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SE849 | Dist WM SE Rplmt in Southeast Clason Point, BX | 5 | CONSTRUCTION TO 25% | Sep 2027 | Jan 2028 | Sep 2025 | Jan 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SE849 | Dist WM SE Rplmt in Southeast Clason Point, BX | 6 | CONSTRUCTION TO 50% | Jan 2028 | May 2028 | Jan 2026 | May 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SE849 | Dist WM SE Rplmt in Southeast Clason Point, BX | 7 | CONSTRUCTION TO 75% | May 2028 | Sep 2028 | May 2026 | Sep 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SE849 | Dist WM SE Rplmt in Southeast Clason Point, BX | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2028 | Dec 2028 | Sep 2026 | Dec 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SE849 | Dist WM SE Rplmt in Southeast Clason Point, BX | 9 | SUBSTANTIAL COMPLETION | Dec 2028 | Feb 2029 | Dec 2026 | Feb 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SE849 | Dist WM SE Rplmt in Southeast Clason Point, BX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2029 | Mar 2029 | Feb 2027 | Mar 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002268 | Reconstruction of Grand Concourse - Phase 4 (HWXP136C) | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002268 | Reconstruction of Grand Concourse - Phase 4 (HWXP136C) | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002268 | Reconstruction of Grand Concourse - Phase 4 (HWXP136C) | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002268 | Reconstruction of Grand Concourse - Phase 4 (HWXP136C) | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002268 | Reconstruction of Grand Concourse - Phase 4 (HWXP136C) | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002268 | Reconstruction of Grand Concourse - Phase 4 (HWXP136C) | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002268 | Reconstruction of Grand Concourse - Phase 4 (HWXP136C) | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002268 | Reconstruction of Grand Concourse - Phase 4 (HWXP136C) | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002268 | Reconstruction of Grand Concourse - Phase 4 (HWXP136C) | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002268 | Reconstruction of Grand Concourse - Phase 4 (HWXP136C) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Jun 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002272 | Combined SE Replacement in Davidson Avenue. Bronx (HWXS711) | 1 | DEVELOP SCOPE | Jun 2021 | Feb 2022 | Jun 2021 | Feb 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002272 | Combined SE Replacement in Davidson Avenue. Bronx (HWXS711) | 2 | PRELIMINARY DESIGN | Feb 2022 | Feb 2023 | Feb 2022 | Feb 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002272 | Combined SE Replacement in Davidson Avenue. Bronx (HWXS711) | 3 | FINAL DESIGN | Feb 2023 | Aug 2024 | Feb 2023 | Aug 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002272 | Combined SE Replacement in Davidson Avenue. Bronx (HWXS711) | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2024 | May 2025 | Aug 2024 | May 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002272 | Combined SE Replacement in Davidson Avenue. Bronx (HWXS711) | 5 | CONSTRUCTION TO 25% | May 2025 | May 2026 | May 2025 | May 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002272 | Combined SE Replacement in Davidson Avenue. Bronx (HWXS711) | 6 | CONSTRUCTION TO 50% | May 2026 | Apr 2027 | May 2026 | Apr 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002272 | Combined SE Replacement in Davidson Avenue. Bronx (HWXS711) | 7 | CONSTRUCTION TO 75% | May 2027 | Apr 2028 | May 2027 | Apr 2028
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002272 | Combined SE Replacement in Davidson Avenue. Bronx (HWXS711) | 8 | ORIGINAL EQUIP & FURNISHING | Apr 2028 | Jan 2029 | Apr 2028 | Jan 2029
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002272 | Combined SE Replacement in Davidson Avenue. Bronx (HWXS711) | 9 | SUBSTANTIAL COMPLETION | Jan 2029 | Jul 2029 | Jan 2029 | Jul 2029
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002272 | Combined SE Replacement in Davidson Avenue. Bronx (HWXS711) | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2029 | Oct 2029 | Jul 2029 | Oct 2029
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002274 | Recon W254 St btwn Railroad Terrace& Riverdale Av, BX HWX406 | 1 | DEVELOP SCOPE | Sep 2021 | Dec 2021 | Sep 2021 | Dec 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002274 | Recon W254 St btwn Railroad Terrace& Riverdale Av, BX HWX406 | 2 | PRELIMINARY DESIGN | Dec 2021 | Mar 2022 | Dec 2021 | Mar 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002274 | Recon W254 St btwn Railroad Terrace& Riverdale Av, BX HWX406 | 3 | FINAL DESIGN | Apr 2022 | Sep 2022 | Apr 2022 | Sep 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002274 | Recon W254 St btwn Railroad Terrace& Riverdale Av, BX HWX406 | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002274 | Recon W254 St btwn Railroad Terrace& Riverdale Av, BX HWX406 | 5 | CONSTRUCTION TO 25% | Dec 2022 | Apr 2023 | Dec 2022 | Apr 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002274 | Recon W254 St btwn Railroad Terrace& Riverdale Av, BX HWX406 | 6 | CONSTRUCTION TO 50% | Apr 2023 | Aug 2023 | Apr 2023 | Aug 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002274 | Recon W254 St btwn Railroad Terrace& Riverdale Av, BX HWX406 | 7 | CONSTRUCTION TO 75% | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002274 | Recon W254 St btwn Railroad Terrace& Riverdale Av, BX HWX406 | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2023 | Mar 2024 | Dec 2023 | Mar 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002274 | Recon W254 St btwn Railroad Terrace& Riverdale Av, BX HWX406 | 9 | SUBSTANTIAL COMPLETION | Mar 2024 | May 2024 | Mar 2024 | May 2024
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002274 | Recon W254 St btwn Railroad Terrace& Riverdale Av, BX HWX406 | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Jun 2024 | May 2024 | Jun 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002275 | Reconstruction of Grand Concourse Phase 5, Bronx, HWXP136D | 1 | DEVELOP SCOPE | Sep 2021 | Dec 2021 | Apr 2024 | Jun 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002275 | Reconstruction of Grand Concourse Phase 5, Bronx, HWXP136D | 2 | PRELIMINARY DESIGN | Dec 2021 | Mar 2022 | Jun 2025 | Oct 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002275 | Reconstruction of Grand Concourse Phase 5, Bronx, HWXP136D | 3 | FINAL DESIGN | Apr 2022 | Sep 2022 | Oct 2025 | Apr 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002275 | Reconstruction of Grand Concourse Phase 5, Bronx, HWXP136D | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2022 | Dec 2022 | Apr 2026 | Jul 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002275 | Reconstruction of Grand Concourse Phase 5, Bronx, HWXP136D | 5 | CONSTRUCTION TO 25% | Dec 2022 | Apr 2023 | Jul 2026 | Nov 2026
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002275 | Reconstruction of Grand Concourse Phase 5, Bronx, HWXP136D | 6 | CONSTRUCTION TO 50% | Apr 2023 | Aug 2023 | Nov 2026 | Mar 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002275 | Reconstruction of Grand Concourse Phase 5, Bronx, HWXP136D | 7 | CONSTRUCTION TO 75% | Aug 2023 | Dec 2023 | Mar 2027 | Jul 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002275 | Reconstruction of Grand Concourse Phase 5, Bronx, HWXP136D | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2023 | Mar 2024 | Jul 2027 | Oct 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002275 | Reconstruction of Grand Concourse Phase 5, Bronx, HWXP136D | 9 | SUBSTANTIAL COMPLETION | Mar 2024 | May 2024 | Oct 2027 | Dec 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002275 | Reconstruction of Grand Concourse Phase 5, Bronx, HWXP136D | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2024 | Jun 2024 | Dec 2027 | Jan 2028
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX0201ZC | Reconstruction of Existing Sewers, the Bronx | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX0201ZC | Reconstruction of Existing Sewers, the Bronx | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX0201ZC | Reconstruction of Existing Sewers, the Bronx | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX0201ZC | Reconstruction of Existing Sewers, the Bronx | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX0201ZC | Reconstruction of Existing Sewers, the Bronx | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX0201ZC | Reconstruction of Existing Sewers, the Bronx | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX0201ZC | Reconstruction of Existing Sewers, the Bronx | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX0201ZC | Reconstruction of Existing Sewers, the Bronx | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX0201ZC | Reconstruction of Existing Sewers, the Bronx | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX0201ZC | Reconstruction of Existing Sewers, the Bronx | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Jun 2027
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX200400 | STORM & SAN SEWERS REPL & EXT IN MININIEFORD AVE AREA | 1 | DEVELOP SCOPE | Jun 2012 | Sep 2012 | May 2009 | Aug 2009
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX200400 | STORM & SAN SEWERS REPL & EXT IN MININIEFORD AVE AREA | 2 | PRELIMINARY DESIGN | Sep 2012 | Jan 2013 | Dec 2008 | Dec 2009
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX200400 | STORM & SAN SEWERS REPL & EXT IN MININIEFORD AVE AREA | 3 | FINAL DESIGN | Jan 2013 | Jul 2013 | Dec 2009 | Mar 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX200400 | STORM & SAN SEWERS REPL & EXT IN MININIEFORD AVE AREA | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2013 | Oct 2013 | Mar 2017 | Jun 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX200400 | STORM & SAN SEWERS REPL & EXT IN MININIEFORD AVE AREA | 5 | CONSTRUCTION TO 25% | Oct 2013 | Feb 2014 | Jun 2017 | Dec 2017
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX200400 | STORM & SAN SEWERS REPL & EXT IN MININIEFORD AVE AREA | 6 | CONSTRUCTION TO 50% | Feb 2014 | Jun 2014 | Dec 2017 | Dec 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX200400 | STORM & SAN SEWERS REPL & EXT IN MININIEFORD AVE AREA | 7 | CONSTRUCTION TO 75% | Jun 2014 | Oct 2014 | Dec 2018 | Jun 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX200400 | STORM & SAN SEWERS REPL & EXT IN MININIEFORD AVE AREA | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2014 | Jan 2015 | Jun 2019 | Aug 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX200400 | STORM & SAN SEWERS REPL & EXT IN MININIEFORD AVE AREA | 9 | SUBSTANTIAL COMPLETION | Jan 2015 | Mar 2015 | Aug 2019 | Oct 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX200400 | STORM & SAN SEWERS REPL & EXT IN MININIEFORD AVE AREA | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Apr 2015 | Oct 2019 | Mar 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20047 | Replacement of combined sewer in Burr Ave | 1 | DEVELOP SCOPE | Mar 2018 | Nov 2018 | Mar 2018 | Nov 2018
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20047 | Replacement of combined sewer in Burr Ave | 2 | PRELIMINARY DESIGN | Dec 2018 | Mar 2019 | Dec 2018 | Mar 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20047 | Replacement of combined sewer in Burr Ave | 3 | FINAL DESIGN | Mar 2019 | Sep 2019 | Mar 2019 | Sep 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20047 | Replacement of combined sewer in Burr Ave | 4 | BID AWARD AND REGISTER CONTRCT | Sep 2019 | Dec 2019 | Sep 2019 | Dec 2019
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20047 | Replacement of combined sewer in Burr Ave | 5 | CONSTRUCTION TO 25% | Dec 2019 | Apr 2020 | Dec 2019 | Apr 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20047 | Replacement of combined sewer in Burr Ave | 6 | CONSTRUCTION TO 50% | Apr 2020 | Aug 2020 | Apr 2020 | Aug 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20047 | Replacement of combined sewer in Burr Ave | 7 | CONSTRUCTION TO 75% | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20047 | Replacement of combined sewer in Burr Ave | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2020 | Mar 2021 | Dec 2020 | Mar 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20047 | Replacement of combined sewer in Burr Ave | 9 | SUBSTANTIAL COMPLETION | Mar 2021 | May 2021 | Mar 2021 | May 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20047 | Replacement of combined sewer in Burr Ave | 10 | PUNCHLIST COMPLETE, JOB CLOSED | May 2021 | Jun 2021 | May 2021 | May 2025
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20049 | Replace deteriorating retain wall Pratt Av, BX HWXPRATT | 1 | DEVELOP SCOPE | Dec 2019 | Mar 2020 | Dec 2019 | Mar 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20049 | Replace deteriorating retain wall Pratt Av, BX HWXPRATT | 2 | PRELIMINARY DESIGN | Mar 2020 | Jul 2020 | Mar 2020 | Jul 2020
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20049 | Replace deteriorating retain wall Pratt Av, BX HWXPRATT | 3 | FINAL DESIGN | Jul 2020 | Jan 2021 | Jul 2020 | Jan 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20049 | Replace deteriorating retain wall Pratt Av, BX HWXPRATT | 4 | BID AWARD AND REGISTER CONTRCT | Jan 2021 | Apr 2021 | Jan 2021 | Apr 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20049 | Replace deteriorating retain wall Pratt Av, BX HWXPRATT | 5 | CONSTRUCTION TO 25% | Apr 2021 | Jul 2021 | Apr 2021 | Jul 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20049 | Replace deteriorating retain wall Pratt Av, BX HWXPRATT | 6 | CONSTRUCTION TO 50% | Jul 2021 | Nov 2021 | Jul 2021 | Nov 2021
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20049 | Replace deteriorating retain wall Pratt Av, BX HWXPRATT | 7 | CONSTRUCTION TO 75% | Nov 2021 | Mar 2022 | Nov 2021 | Mar 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20049 | Replace deteriorating retain wall Pratt Av, BX HWXPRATT | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2022 | Jun 2022 | Mar 2022 | Jun 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20049 | Replace deteriorating retain wall Pratt Av, BX HWXPRATT | 9 | SUBSTANTIAL COMPLETION | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20049 | Replace deteriorating retain wall Pratt Av, BX HWXPRATT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Aug 2022 | Sep 2022 | Aug 2022 | Jun 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA221 | DCLA - NYBG CHILLER REPLACMENT, WATER SYSTEM OPTIMIZATION | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA221 | DCLA - NYBG CHILLER REPLACMENT, WATER SYSTEM OPTIMIZATION | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA221 | DCLA - NYBG CHILLER REPLACMENT, WATER SYSTEM OPTIMIZATION | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA221 | DCLA - NYBG CHILLER REPLACMENT, WATER SYSTEM OPTIMIZATION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA221 | DCLA - NYBG CHILLER REPLACMENT, WATER SYSTEM OPTIMIZATION | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA221 | DCLA - NYBG CHILLER REPLACMENT, WATER SYSTEM OPTIMIZATION | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA221 | DCLA - NYBG CHILLER REPLACMENT, WATER SYSTEM OPTIMIZATION | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA221 | DCLA - NYBG CHILLER REPLACMENT, WATER SYSTEM OPTIMIZATION | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA221 | DCLA - NYBG CHILLER REPLACMENT, WATER SYSTEM OPTIMIZATION | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA221 | DCLA - NYBG CHILLER REPLACMENT, WATER SYSTEM OPTIMIZATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA222 | DCLA - BRONX ZOO ADMIN WEST AHU - 2300 SOUTHERN BLVD, BX | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA222 | DCLA - BRONX ZOO ADMIN WEST AHU - 2300 SOUTHERN BLVD, BX | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA222 | DCLA - BRONX ZOO ADMIN WEST AHU - 2300 SOUTHERN BLVD, BX | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA222 | DCLA - BRONX ZOO ADMIN WEST AHU - 2300 SOUTHERN BLVD, BX | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA222 | DCLA - BRONX ZOO ADMIN WEST AHU - 2300 SOUTHERN BLVD, BX | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA222 | DCLA - BRONX ZOO ADMIN WEST AHU - 2300 SOUTHERN BLVD, BX | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA222 | DCLA - BRONX ZOO ADMIN WEST AHU - 2300 SOUTHERN BLVD, BX | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA222 | DCLA - BRONX ZOO ADMIN WEST AHU - 2300 SOUTHERN BLVD, BX | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA222 | DCLA - BRONX ZOO ADMIN WEST AHU - 2300 SOUTHERN BLVD, BX | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA222 | DCLA - BRONX ZOO ADMIN WEST AHU - 2300 SOUTHERN BLVD, BX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE211 | DOE- Building Management System Upgrade | 1 | DEVELOP SCOPE | Jun 2023 | Jun 2023 | Jun 2023 | Jun 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE211 | DOE- Building Management System Upgrade | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE211 | DOE- Building Management System Upgrade | 3 | CONSTRUCTION TO 50% | Aug 2023 | Feb 2024 | Aug 2023 | Feb 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE211 | DOE- Building Management System Upgrade | 4 | CONSTRUCTION TO 75% | Feb 2024 | May 2024 | Feb 2024 | May 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE211 | DOE- Building Management System Upgrade | 5 | SUBSTANTIAL COMPLETION | May 2024 | Jul 2024 | May 2024 | Jul 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE211 | DOE- Building Management System Upgrade | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOT221 | DOT - HVAC and Lighting Upgrades at Fleet Services | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOT221 | DOT - HVAC and Lighting Upgrades at Fleet Services | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOT221 | DOT - HVAC and Lighting Upgrades at Fleet Services | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOT221 | DOT - HVAC and Lighting Upgrades at Fleet Services | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOT221 | DOT - HVAC and Lighting Upgrades at Fleet Services | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOT221 | DOT - HVAC and Lighting Upgrades at Fleet Services | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2027
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOT222 | HVAC Upgrades at Fleet Services Maintenance and Repair | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOT222 | HVAC Upgrades at Fleet Services Maintenance and Repair | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOT222 | HVAC Upgrades at Fleet Services Maintenance and Repair | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOT222 | HVAC Upgrades at Fleet Services Maintenance and Repair | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOT222 | HVAC Upgrades at Fleet Services Maintenance and Repair | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOT222 | HVAC Upgrades at Fleet Services Maintenance and Repair | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFDN212 | FDNY - Various energy conservation measures at 8 Fire Houses | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFDN212 | FDNY - Various energy conservation measures at 8 Fire Houses | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFDN212 | FDNY - Various energy conservation measures at 8 Fire Houses | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFDN212 | FDNY - Various energy conservation measures at 8 Fire Houses | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFDN212 | FDNY - Various energy conservation measures at 8 Fire Houses | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFDN212 | FDNY - Various energy conservation measures at 8 Fire Houses | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACENPL222 | Comprehensive Upgrades - Grand Concourse Branch Library | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACENPL222 | Comprehensive Upgrades - Grand Concourse Branch Library | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACENPL222 | Comprehensive Upgrades - Grand Concourse Branch Library | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACENPL222 | Comprehensive Upgrades - Grand Concourse Branch Library | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACENPL222 | Comprehensive Upgrades - Grand Concourse Branch Library | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACENPL222 | Comprehensive Upgrades - Grand Concourse Branch Library | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | AG01NELS | DFTA - 1181 NELSON AVE, BX LEASE RENEWAL | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | AG01NELS | DFTA - 1181 NELSON AVE, BX LEASE RENEWAL | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | AG01NELS | DFTA - 1181 NELSON AVE, BX LEASE RENEWAL | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | AG01NELS | DFTA - 1181 NELSON AVE, BX LEASE RENEWAL | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | AG01NELS | DFTA - 1181 NELSON AVE, BX LEASE RENEWAL | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | AG01NELS | DFTA - 1181 NELSON AVE, BX LEASE RENEWAL | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | AG01NELS | DFTA - 1181 NELSON AVE, BX LEASE RENEWAL | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | AG01NELS | DFTA - 1181 NELSON AVE, BX LEASE RENEWAL | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | AG01NELS | DFTA - 1181 NELSON AVE, BX LEASE RENEWAL | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | AG01NELS | DFTA - 1181 NELSON AVE, BX LEASE RENEWAL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2029
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | APIBXMSM1 | Bronx Museum Atrium Reconstruction | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | APIBXMSM1 | Bronx Museum Atrium Reconstruction | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | APIBXMSM1 | Bronx Museum Atrium Reconstruction | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | APIBXMSM1 | Bronx Museum Atrium Reconstruction | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | APIBXMSM1 | Bronx Museum Atrium Reconstruction | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | APIBXMSM1 | Bronx Museum Atrium Reconstruction | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | BXCONSOL | Renovation of Bronx DCP office at 211 Bartow Ave. | 1 | DEVELOP SCOPE | Jun 2021 | Aug 2021 | Jun 2021 | Aug 2021
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | BXCONSOL | Renovation of Bronx DCP office at 211 Bartow Ave. | 2 | PRELIMINARY DESIGN | Aug 2021 | Dec 2021 | Aug 2021 | Dec 2021
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | BXCONSOL | Renovation of Bronx DCP office at 211 Bartow Ave. | 3 | FINAL DESIGN | Dec 2021 | Feb 2022 | Dec 2021 | Feb 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | BXCONSOL | Renovation of Bronx DCP office at 211 Bartow Ave. | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2022 | May 2022 | Mar 2022 | May 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | BXCONSOL | Renovation of Bronx DCP office at 211 Bartow Ave. | 5 | CONSTRUCTION TO 25% | May 2022 | Sep 2022 | May 2022 | Sep 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | BXCONSOL | Renovation of Bronx DCP office at 211 Bartow Ave. | 6 | CONSTRUCTION TO 50% | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | BXCONSOL | Renovation of Bronx DCP office at 211 Bartow Ave. | 7 | CONSTRUCTION TO 75% | Jan 2023 | Feb 2023 | Jan 2023 | Feb 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | BXCONSOL | Renovation of Bronx DCP office at 211 Bartow Ave. | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2023 | May 2023 | Mar 2023 | May 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | BXCONSOL | Renovation of Bronx DCP office at 211 Bartow Ave. | 9 | SUBSTANTIAL COMPLETION | May 2023 | Jul 2023 | May 2023 | Jul 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | BXCONSOL | Renovation of Bronx DCP office at 211 Bartow Ave. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2023 | Aug 2023 | Jul 2023 | Aug 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293201A | DASNY - 851 GRAND CONCOURSE- RENOVATIONS | 1 | DEVELOP SCOPE | Aug 2006 | Oct 2006 | Jul 2006 | Sep 2006
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293201A | DASNY - 851 GRAND CONCOURSE- RENOVATIONS | 2 | PRELIMINARY DESIGN | Oct 2006 | Feb 2007 | Sep 2006 | Jan 2007
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293201A | DASNY - 851 GRAND CONCOURSE- RENOVATIONS | 3 | FINAL DESIGN | Feb 2007 | Aug 2007 | Jan 2007 | Jul 2007
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293201A | DASNY - 851 GRAND CONCOURSE- RENOVATIONS | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2007 | Nov 2007 | Jul 2007 | Oct 2007
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293201A | DASNY - 851 GRAND CONCOURSE- RENOVATIONS | 5 | CONSTRUCTION TO 25% | Nov 2007 | Nov 2008 | Oct 2007 | Oct 2008
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293201A | DASNY - 851 GRAND CONCOURSE- RENOVATIONS | 6 | CONSTRUCTION TO 50% | Nov 2008 | Nov 2009 | Oct 2008 | Oct 2009
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293201A | DASNY - 851 GRAND CONCOURSE- RENOVATIONS | 7 | CONSTRUCTION TO 75% | Nov 2009 | Nov 2010 | Jun 2027 | May 2028
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293201A | DASNY - 851 GRAND CONCOURSE- RENOVATIONS | 8 | ORIGINAL EQUIP & FURNISHING | Nov 2010 | Nov 2011 | May 2028 | May 2029
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293201A | DASNY - 851 GRAND CONCOURSE- RENOVATIONS | 9 | SUBSTANTIAL COMPLETION | Nov 2011 | Dec 2011 | May 2029 | Aug 2029
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293201A | DASNY - 851 GRAND CONCOURSE- RENOVATIONS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2011 | Dec 2011 | Nov 2029 | Feb 2030
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293CTR | 851 GRAND CONCOURSE -COOLING TOWER REPLACEMENT | 1 | DEVELOP SCOPE | Mar 2022 | May 2022 | Mar 2022 | May 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293CTR | 851 GRAND CONCOURSE -COOLING TOWER REPLACEMENT | 2 | PRELIMINARY DESIGN | May 2022 | Sep 2022 | May 2022 | Sep 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293CTR | 851 GRAND CONCOURSE -COOLING TOWER REPLACEMENT | 3 | FINAL DESIGN | Sep 2022 | Mar 2023 | Sep 2022 | Mar 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293CTR | 851 GRAND CONCOURSE -COOLING TOWER REPLACEMENT | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2023 | Jun 2023 | Mar 2023 | Jun 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293CTR | 851 GRAND CONCOURSE -COOLING TOWER REPLACEMENT | 5 | CONSTRUCTION TO 25% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293CTR | 851 GRAND CONCOURSE -COOLING TOWER REPLACEMENT | 6 | CONSTRUCTION TO 50% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293CTR | 851 GRAND CONCOURSE -COOLING TOWER REPLACEMENT | 7 | CONSTRUCTION TO 75% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293CTR | 851 GRAND CONCOURSE -COOLING TOWER REPLACEMENT | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293CTR | 851 GRAND CONCOURSE -COOLING TOWER REPLACEMENT | 9 | SUBSTANTIAL COMPLETION | Sep 2024 | Nov 2024 | Sep 2024 | Nov 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293CTR | 851 GRAND CONCOURSE -COOLING TOWER REPLACEMENT | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2024 | Dec 2024 | Nov 2024 | Dec 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293ELEC | 851 GRAND CONCOURSE- ELECTRICAL UPGRADE | 1 | DEVELOP SCOPE | Jun 2005 | Sep 2005 | Jun 2005 | Sep 2005
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293ELEC | 851 GRAND CONCOURSE- ELECTRICAL UPGRADE | 2 | PRELIMINARY DESIGN | Sep 2005 | Jan 2006 | Sep 2005 | Jan 2006
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293ELEC | 851 GRAND CONCOURSE- ELECTRICAL UPGRADE | 3 | FINAL DESIGN | Jan 2006 | Jul 2006 | Jan 2006 | Jul 2006
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293ELEC | 851 GRAND CONCOURSE- ELECTRICAL UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2006 | Mar 2007 | Jul 2006 | Oct 2006
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293ELEC | 851 GRAND CONCOURSE- ELECTRICAL UPGRADE | 5 | CONSTRUCTION TO 25% | Apr 2007 | Nov 2007 | Oct 2006 | Oct 2007
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293ELEC | 851 GRAND CONCOURSE- ELECTRICAL UPGRADE | 6 | CONSTRUCTION TO 50% | Dec 2007 | Mar 2008 | Oct 2007 | Oct 2008
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293ELEC | 851 GRAND CONCOURSE- ELECTRICAL UPGRADE | 7 | CONSTRUCTION TO 75% | Apr 2008 | Apr 2008 | Jun 2022 | May 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293ELEC | 851 GRAND CONCOURSE- ELECTRICAL UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2007 | Jan 2008 | May 2023 | Sep 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293ELEC | 851 GRAND CONCOURSE- ELECTRICAL UPGRADE | 9 | SUBSTANTIAL COMPLETION | Nov 2008 | Feb 2009 | Sep 2024 | Jan 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293ELEC | 851 GRAND CONCOURSE- ELECTRICAL UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2009 | Mar 2009 | Jan 2026 | Jul 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293EV | 851 GRAND CONCOURSE - ELEVATORS | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293EV | 851 GRAND CONCOURSE - ELEVATORS | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293EV | 851 GRAND CONCOURSE - ELEVATORS | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293EV | 851 GRAND CONCOURSE - ELEVATORS | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293EV | 851 GRAND CONCOURSE - ELEVATORS | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293EV | 851 GRAND CONCOURSE - ELEVATORS | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293EV | 851 GRAND CONCOURSE - ELEVATORS | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293EV | 851 GRAND CONCOURSE - ELEVATORS | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293EV | 851 GRAND CONCOURSE - ELEVATORS | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293EV | 851 GRAND CONCOURSE - ELEVATORS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293GCON | 851 GRAND CONCOURSE - ADA COMPLIANCE | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293GCON | 851 GRAND CONCOURSE - ADA COMPLIANCE | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293GCON | 851 GRAND CONCOURSE - ADA COMPLIANCE | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293GCON | 851 GRAND CONCOURSE - ADA COMPLIANCE | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293GCON | 851 GRAND CONCOURSE - ADA COMPLIANCE | 5 | CONSTRUCTION TO 25% | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293GCON | 851 GRAND CONCOURSE - ADA COMPLIANCE | 6 | CONSTRUCTION TO 50% | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293GCON | 851 GRAND CONCOURSE - ADA COMPLIANCE | 7 | CONSTRUCTION TO 75% | Jan 2026 | May 2026 | Jan 2026 | May 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293GCON | 851 GRAND CONCOURSE - ADA COMPLIANCE | 8 | ORIGINAL EQUIP & FURNISHING | May 2026 | Aug 2026 | May 2026 | Aug 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293GCON | 851 GRAND CONCOURSE - ADA COMPLIANCE | 9 | SUBSTANTIAL COMPLETION | Aug 2026 | Oct 2026 | Aug 2026 | Oct 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293GCON | 851 GRAND CONCOURSE - ADA COMPLIANCE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2026 | Nov 2026 | Oct 2026 | Nov 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293HO | 851 GRAND CONCOURSE - HOUSING COURT RELOCATION | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Aug 2020
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293HO | 851 GRAND CONCOURSE - HOUSING COURT RELOCATION | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293HO | 851 GRAND CONCOURSE - HOUSING COURT RELOCATION | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293HO | 851 GRAND CONCOURSE - HOUSING COURT RELOCATION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293HO | 851 GRAND CONCOURSE - HOUSING COURT RELOCATION | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293HO | 851 GRAND CONCOURSE - HOUSING COURT RELOCATION | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2022 | May 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293HO | 851 GRAND CONCOURSE - HOUSING COURT RELOCATION | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2022 | Sep 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293HO | 851 GRAND CONCOURSE - HOUSING COURT RELOCATION | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293HO | 851 GRAND CONCOURSE - HOUSING COURT RELOCATION | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2022 | Feb 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293HO | 851 GRAND CONCOURSE - HOUSING COURT RELOCATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2023 | Feb 2023 | Jun 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BACK | DASNY - 215 E. 161ST ST.- BACKFILL | 1 | DEVELOP SCOPE | Dec 2006 | Feb 2007 | Dec 2010 | Feb 2011
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BACK | DASNY - 215 E. 161ST ST.- BACKFILL | 2 | PRELIMINARY DESIGN | Mar 2007 | Jun 2007 | Mar 2011 | Jun 2011
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BACK | DASNY - 215 E. 161ST ST.- BACKFILL | 3 | FINAL DESIGN | Jun 2007 | Dec 2007 | Jun 2011 | Dec 2011
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BACK | DASNY - 215 E. 161ST ST.- BACKFILL | 4 | BID AWARD AND REGISTER CONTRCT | Dec 2007 | Mar 2008 | Dec 2011 | Mar 2012
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BACK | DASNY - 215 E. 161ST ST.- BACKFILL | 5 | CONSTRUCTION TO 25% | Mar 2008 | Mar 2009 | Mar 2012 | Mar 2013
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BACK | DASNY - 215 E. 161ST ST.- BACKFILL | 6 | CONSTRUCTION TO 50% | Mar 2009 | Mar 2010 | Mar 2013 | Mar 2014
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BACK | DASNY - 215 E. 161ST ST.- BACKFILL | 7 | CONSTRUCTION TO 75% | Mar 2010 | Mar 2011 | Jun 2027 | May 2028
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BACK | DASNY - 215 E. 161ST ST.- BACKFILL | 8 | ORIGINAL EQUIP & FURNISHING | Mar 2011 | Sep 2011 | May 2028 | Nov 2028
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BACK | DASNY - 215 E. 161ST ST.- BACKFILL | 9 | SUBSTANTIAL COMPLETION | Sep 2011 | Nov 2011 | Nov 2028 | Jan 2029
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BACK | DASNY - 215 E. 161ST ST.- BACKFILL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2011 | Dec 2011 | Jan 2029 | Apr 2029
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295FIRE | 1118 GRAND CONCOURSE - FIRE ALARM UPGRADE | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295FIRE | 1118 GRAND CONCOURSE - FIRE ALARM UPGRADE | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295FIRE | 1118 GRAND CONCOURSE - FIRE ALARM UPGRADE | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295FIRE | 1118 GRAND CONCOURSE - FIRE ALARM UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295FIRE | 1118 GRAND CONCOURSE - FIRE ALARM UPGRADE | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295FIRE | 1118 GRAND CONCOURSE - FIRE ALARM UPGRADE | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295FIRE | 1118 GRAND CONCOURSE - FIRE ALARM UPGRADE | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | May 2024 | Sep 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295FIRE | 1118 GRAND CONCOURSE - FIRE ALARM UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295FIRE | 1118 GRAND CONCOURSE - FIRE ALARM UPGRADE | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Dec 2024 | Feb 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295FIRE | 1118 GRAND CONCOURSE - FIRE ALARM UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Jun 2026 | Feb 2025 | Jun 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295ROOF | 1118 GRAND CONCOURSE - ROOF | 1 | DEVELOP SCOPE | Mar 2022 | May 2022 | Mar 2022 | May 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295ROOF | 1118 GRAND CONCOURSE - ROOF | 2 | PRELIMINARY DESIGN | May 2022 | Sep 2022 | May 2022 | Sep 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295ROOF | 1118 GRAND CONCOURSE - ROOF | 3 | FINAL DESIGN | Sep 2022 | Mar 2023 | Sep 2022 | Mar 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295ROOF | 1118 GRAND CONCOURSE - ROOF | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2023 | Jun 2023 | Mar 2023 | Jun 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295ROOF | 1118 GRAND CONCOURSE - ROOF | 5 | CONSTRUCTION TO 25% | Jun 2023 | Oct 2023 | Jun 2023 | Oct 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295ROOF | 1118 GRAND CONCOURSE - ROOF | 6 | CONSTRUCTION TO 50% | Oct 2023 | Feb 2024 | Oct 2023 | Feb 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295ROOF | 1118 GRAND CONCOURSE - ROOF | 7 | CONSTRUCTION TO 75% | Feb 2024 | Jun 2024 | Feb 2024 | Jun 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295ROOF | 1118 GRAND CONCOURSE - ROOF | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295ROOF | 1118 GRAND CONCOURSE - ROOF | 9 | SUBSTANTIAL COMPLETION | Sep 2024 | Nov 2024 | Sep 2024 | Nov 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295ROOF | 1118 GRAND CONCOURSE - ROOF | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2024 | Dec 2024 | Nov 2024 | Dec 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | COD294CBG | 215 E 161st BX CENTRAL BOOKING COURT SECTION FITNESS CENTER | 1 | DEVELOP SCOPE | Jun 2021 | Aug 2021 | Jun 2025 | Aug 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | COD294CBG | 215 E 161st BX CENTRAL BOOKING COURT SECTION FITNESS CENTER | 2 | PRELIMINARY DESIGN | Aug 2021 | Dec 2021 | Aug 2025 | Dec 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | COD294CBG | 215 E 161st BX CENTRAL BOOKING COURT SECTION FITNESS CENTER | 3 | FINAL DESIGN | Dec 2021 | Jun 2022 | Dec 2025 | Jun 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | COD294CBG | 215 E 161st BX CENTRAL BOOKING COURT SECTION FITNESS CENTER | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2022 | Sep 2022 | Jun 2026 | Sep 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | COD294CBG | 215 E 161st BX CENTRAL BOOKING COURT SECTION FITNESS CENTER | 5 | CONSTRUCTION TO 25% | Sep 2022 | Jan 2023 | Sep 2026 | Jan 2027
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | COD294CBG | 215 E 161st BX CENTRAL BOOKING COURT SECTION FITNESS CENTER | 6 | CONSTRUCTION TO 50% | Jan 2023 | May 2023 | Jan 2027 | May 2027
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | COD294CBG | 215 E 161st BX CENTRAL BOOKING COURT SECTION FITNESS CENTER | 7 | CONSTRUCTION TO 75% | May 2023 | Sep 2023 | May 2027 | Sep 2027
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | COD294CBG | 215 E 161st BX CENTRAL BOOKING COURT SECTION FITNESS CENTER | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2021 | Aug 2021 | Sep 2027 | Dec 2027
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | COD294CBG | 215 E 161st BX CENTRAL BOOKING COURT SECTION FITNESS CENTER | 9 | SUBSTANTIAL COMPLETION | Aug 2021 | Oct 2021 | Dec 2027 | Feb 2028
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | COD294CBG | 215 E 161st BX CENTRAL BOOKING COURT SECTION FITNESS CENTER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2021 | Nov 2021 | Feb 2028 | Mar 2028
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | DAVIDCC | DAVIDSON COMMUNITY CENTER GYM | 1 | DEVELOP SCOPE | Jun 2019 | Aug 2019 | Jun 2024 | Aug 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | DAVIDCC | DAVIDSON COMMUNITY CENTER GYM | 2 | PRELIMINARY DESIGN | Aug 2019 | Dec 2019 | Aug 2024 | Dec 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | DAVIDCC | DAVIDSON COMMUNITY CENTER GYM | 3 | FINAL DESIGN | Dec 2019 | Jun 2020 | Dec 2024 | Jun 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | DAVIDCC | DAVIDSON COMMUNITY CENTER GYM | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2020 | Sep 2020 | Jun 2025 | Sep 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | DAVIDCC | DAVIDSON COMMUNITY CENTER GYM | 5 | CONSTRUCTION TO 25% | Sep 2020 | Jan 2021 | Sep 2025 | Jan 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | DAVIDCC | DAVIDSON COMMUNITY CENTER GYM | 6 | CONSTRUCTION TO 50% | Jan 2021 | May 2021 | Jan 2026 | May 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | DAVIDCC | DAVIDSON COMMUNITY CENTER GYM | 7 | CONSTRUCTION TO 75% | May 2021 | Sep 2021 | May 2026 | Sep 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | DAVIDCC | DAVIDSON COMMUNITY CENTER GYM | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2021 | Dec 2021 | Sep 2026 | Dec 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | DAVIDCC | DAVIDSON COMMUNITY CENTER GYM | 9 | SUBSTANTIAL COMPLETION | Dec 2021 | Feb 2022 | Dec 2026 | Feb 2027
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | DAVIDCC | DAVIDSON COMMUNITY CENTER GYM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2022 | Mar 2022 | Feb 2027 | Mar 2029
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E10-00004 | DCLA - 09-013; WCS - Bronx Zoo; 2300 Southern Boulevard | 1 | DEVELOP SCOPE | Jun 2011 | Jun 2011 | Jun 2017 | Jul 2017
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E10-00004 | DCLA - 09-013; WCS - Bronx Zoo; 2300 Southern Boulevard | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2011 | Jul 2011 | Apr 2022 | Mar 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E10-00004 | DCLA - 09-013; WCS - Bronx Zoo; 2300 Southern Boulevard | 3 | CONSTRUCTION TO 50% | Jul 2011 | Jan 2012 | Apr 2022 | Mar 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E10-00004 | DCLA - 09-013; WCS - Bronx Zoo; 2300 Southern Boulevard | 4 | CONSTRUCTION TO 75% | Jan 2012 | Apr 2012 | Apr 2022 | Mar 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E10-00004 | DCLA - 09-013; WCS - Bronx Zoo; 2300 Southern Boulevard | 5 | SUBSTANTIAL COMPLETION | Apr 2012 | May 2012 | Jun 2023 | May 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E10-00004 | DCLA - 09-013; WCS - Bronx Zoo; 2300 Southern Boulevard | 6 | PUNCHLIST COMPLETE, JOB CLOSED | May 2012 | Jun 2012 | Jun 2023 | Jun 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E14-0002 | DCAS - BRONX COUNTY COURT COMP ENERGY UPGRADE | 1 | DEVELOP SCOPE | Dec 2013 | Mar 2015 | Jun 2020 | Sep 2021
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E14-0002 | DCAS - BRONX COUNTY COURT COMP ENERGY UPGRADE | 2 | BID AWARD AND REGISTER CONTRCT | Apr 2015 | May 2015 | Sep 2021 | Nov 2021
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E14-0002 | DCAS - BRONX COUNTY COURT COMP ENERGY UPGRADE | 3 | CONSTRUCTION TO 50% | May 2015 | Aug 2015 | Jun 2022 | Aug 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E14-0002 | DCAS - BRONX COUNTY COURT COMP ENERGY UPGRADE | 4 | CONSTRUCTION TO 75% | Aug 2015 | Oct 2015 | Aug 2022 | Oct 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E14-0002 | DCAS - BRONX COUNTY COURT COMP ENERGY UPGRADE | 5 | SUBSTANTIAL COMPLETION | Oct 2015 | Nov 2015 | Oct 2022 | Nov 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E14-0002 | DCAS - BRONX COUNTY COURT COMP ENERGY UPGRADE | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2015 | Dec 2015 | Nov 2022 | Oct 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0002 | NYPD - Comprehensive Lighting Upgrades at 20 NYPD Facilities | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2022 | Jun 2019 | Jun 2019
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0002 | NYPD - Comprehensive Lighting Upgrades at 20 NYPD Facilities | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Aug 2022 | Jul 2019 | Aug 2019
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0002 | NYPD - Comprehensive Lighting Upgrades at 20 NYPD Facilities | 3 | CONSTRUCTION TO 50% | Aug 2022 | Feb 2023 | Aug 2019 | Feb 2020
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0002 | NYPD - Comprehensive Lighting Upgrades at 20 NYPD Facilities | 4 | CONSTRUCTION TO 75% | Feb 2023 | May 2023 | Feb 2020 | May 2020
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0002 | NYPD - Comprehensive Lighting Upgrades at 20 NYPD Facilities | 5 | SUBSTANTIAL COMPLETION | May 2023 | Jul 2023 | May 2020 | Jul 2020
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0002 | NYPD - Comprehensive Lighting Upgrades at 20 NYPD Facilities | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2023 | Aug 2023 | Jul 2020 | Aug 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0006 | NYPL Bronx Library | 1 | DEVELOP SCOPE | Jun 2022 | Jun 2022 | Jun 2022 | Jun 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0006 | NYPL Bronx Library | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2022 | Aug 2022 | Jul 2022 | Aug 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0006 | NYPL Bronx Library | 3 | CONSTRUCTION TO 50% | Aug 2022 | Feb 2023 | Aug 2022 | Feb 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0006 | NYPL Bronx Library | 4 | CONSTRUCTION TO 75% | Feb 2023 | May 2023 | Feb 2023 | May 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0006 | NYPL Bronx Library | 5 | SUBSTANTIAL COMPLETION | May 2023 | Jul 2023 | May 2023 | Jul 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0006 | NYPL Bronx Library | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2023 | Aug 2023 | Jul 2023 | Oct 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0008 | CUNY Hostos Community College (DI) | 1 | DEVELOP SCOPE | Jun 2025 | Jun 2025 | Jun 2025 | Jun 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0008 | CUNY Hostos Community College (DI) | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0008 | CUNY Hostos Community College (DI) | 3 | CONSTRUCTION TO 50% | Aug 2025 | Feb 2026 | Aug 2025 | Feb 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0008 | CUNY Hostos Community College (DI) | 4 | CONSTRUCTION TO 75% | Feb 2026 | May 2026 | Feb 2026 | May 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0008 | CUNY Hostos Community College (DI) | 5 | SUBSTANTIAL COMPLETION | May 2026 | Jul 2026 | May 2026 | Jul 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E23-0008 | CUNY Hostos Community College (DI) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2026 | Aug 2026 | Jul 2026 | Aug 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-DOE02 | DOE Direct Install Lighting - Phase 3 | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-DOE02 | DOE Direct Install Lighting - Phase 3 | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-DOE02 | DOE Direct Install Lighting - Phase 3 | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-DOE02 | DOE Direct Install Lighting - Phase 3 | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-DOE02 | DOE Direct Install Lighting - Phase 3 | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E24-DOE02 | DOE Direct Install Lighting - Phase 3 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Jun 2026 | Jul 2025 | Jun 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0042 | CUNY - Bronx Community College Campus: Polowczyk Hall | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2020 | Jun 2020 | Jun 2020
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0042 | CUNY - Bronx Community College Campus: Polowczyk Hall | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Aug 2020 | Jul 2020 | Aug 2020
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0042 | CUNY - Bronx Community College Campus: Polowczyk Hall | 3 | CONSTRUCTION TO 50% | Aug 2020 | Feb 2021 | Aug 2020 | Feb 2021
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0042 | CUNY - Bronx Community College Campus: Polowczyk Hall | 4 | CONSTRUCTION TO 75% | Feb 2021 | May 2021 | Feb 2021 | May 2021
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0042 | CUNY - Bronx Community College Campus: Polowczyk Hall | 5 | SUBSTANTIAL COMPLETION | May 2021 | Jul 2021 | May 2021 | Jul 2021
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0042 | CUNY - Bronx Community College Campus: Polowczyk Hall | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Aug 2021 | Jul 2021 | Aug 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0064 | NYPD - 52nd Precinct | 1 | DEVELOP SCOPE | Mar 2020 | Mar 2020 | Jun 2022 | Jun 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0064 | NYPD - 52nd Precinct | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | May 2020 | Jul 2022 | Aug 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0064 | NYPD - 52nd Precinct | 3 | CONSTRUCTION TO 50% | May 2020 | Nov 2020 | Aug 2022 | Feb 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0064 | NYPD - 52nd Precinct | 4 | CONSTRUCTION TO 75% | Nov 2020 | Feb 2021 | Feb 2023 | May 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0064 | NYPD - 52nd Precinct | 5 | SUBSTANTIAL COMPLETION | Feb 2021 | Apr 2021 | May 2023 | Jul 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0064 | NYPD - 52nd Precinct | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2021 | May 2021 | Jul 2023 | Aug 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0075 | NYPD - 44TH PRECINCT | 1 | DEVELOP SCOPE | Jan 2020 | Feb 2020 | Jan 2020 | Feb 2020
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0075 | NYPD - 44TH PRECINCT | 2 | BID AWARD AND REGISTER CONTRCT | Feb 2020 | Apr 2020 | Feb 2020 | Apr 2020
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0075 | NYPD - 44TH PRECINCT | 3 | CONSTRUCTION TO 50% | Apr 2020 | Oct 2020 | Jun 2025 | Nov 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0075 | NYPD - 44TH PRECINCT | 4 | CONSTRUCTION TO 75% | Oct 2020 | Jan 2021 | Nov 2025 | Feb 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0075 | NYPD - 44TH PRECINCT | 5 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | Feb 2026 | Apr 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0075 | NYPD - 44TH PRECINCT | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Apr 2026 | May 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0080 | DHS - FRANKLIN WOMEN'S SHELTER | 1 | DEVELOP SCOPE | Feb 2020 | Mar 2020 | Jun 2022 | Jun 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0080 | DHS - FRANKLIN WOMEN'S SHELTER | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | May 2020 | Jul 2022 | Aug 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0080 | DHS - FRANKLIN WOMEN'S SHELTER | 3 | CONSTRUCTION TO 50% | May 2020 | Nov 2020 | Aug 2022 | Feb 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0080 | DHS - FRANKLIN WOMEN'S SHELTER | 4 | CONSTRUCTION TO 75% | Nov 2020 | Feb 2021 | Feb 2023 | May 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0080 | DHS - FRANKLIN WOMEN'S SHELTER | 5 | SUBSTANTIAL COMPLETION | Feb 2021 | Apr 2021 | May 2023 | Jul 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0080 | DHS - FRANKLIN WOMEN'S SHELTER | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2021 | May 2021 | Jul 2023 | Aug 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0089 | DPR - BRONX PARKS HEADQUARTERS AND SHOPS | 1 | DEVELOP SCOPE | Feb 2020 | Mar 2020 | Jun 2022 | Jun 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0089 | DPR - BRONX PARKS HEADQUARTERS AND SHOPS | 2 | BID AWARD AND REGISTER CONTRCT | Mar 2020 | Apr 2020 | Jul 2022 | Aug 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0089 | DPR - BRONX PARKS HEADQUARTERS AND SHOPS | 3 | CONSTRUCTION TO 50% | May 2020 | Oct 2020 | Aug 2022 | Feb 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0089 | DPR - BRONX PARKS HEADQUARTERS AND SHOPS | 4 | CONSTRUCTION TO 75% | Oct 2020 | Jan 2021 | Feb 2023 | May 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0089 | DPR - BRONX PARKS HEADQUARTERS AND SHOPS | 5 | SUBSTANTIAL COMPLETION | Jan 2021 | Mar 2021 | May 2023 | Jul 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0089 | DPR - BRONX PARKS HEADQUARTERS AND SHOPS | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2021 | Apr 2021 | Jul 2023 | Aug 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | MICROH M | DEP - MICRO-HYDRO TURBINE AT CRTOTON LAKE GATE HOUSE | 1 | DEVELOP SCOPE | Jun 2026 | Aug 2026 | Jun 2026 | Aug 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | MICROH M | DEP - MICRO-HYDRO TURBINE AT CRTOTON LAKE GATE HOUSE | 2 | PRELIMINARY DESIGN | Aug 2026 | Dec 2026 | Aug 2026 | Dec 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | MICROH M | DEP - MICRO-HYDRO TURBINE AT CRTOTON LAKE GATE HOUSE | 3 | FINAL DESIGN | Dec 2026 | Jun 2027 | Dec 2026 | Jun 2027
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | MICROH M | DEP - MICRO-HYDRO TURBINE AT CRTOTON LAKE GATE HOUSE | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2027 | Sep 2027 | Jun 2027 | Sep 2027
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | MICROH M | DEP - MICRO-HYDRO TURBINE AT CRTOTON LAKE GATE HOUSE | 5 | CONSTRUCTION TO 25% | Sep 2027 | Jan 2028 | Sep 2027 | Jan 2028
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | MICROH M | DEP - MICRO-HYDRO TURBINE AT CRTOTON LAKE GATE HOUSE | 6 | CONSTRUCTION TO 50% | Jan 2028 | May 2028 | Jan 2028 | May 2028
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | MICROH M | DEP - MICRO-HYDRO TURBINE AT CRTOTON LAKE GATE HOUSE | 7 | CONSTRUCTION TO 75% | May 2028 | Sep 2028 | May 2028 | Sep 2028
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | MICROH M | DEP - MICRO-HYDRO TURBINE AT CRTOTON LAKE GATE HOUSE | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2028 | Dec 2028 | Sep 2028 | Dec 2028
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | MICROH M | DEP - MICRO-HYDRO TURBINE AT CRTOTON LAKE GATE HOUSE | 9 | SUBSTANTIAL COMPLETION | Dec 2028 | Feb 2029 | Dec 2028 | Feb 2029
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | MICROH M | DEP - MICRO-HYDRO TURBINE AT CRTOTON LAKE GATE HOUSE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2029 | Mar 2029 | Feb 2029 | Mar 2029
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79BSVD | bronx special victimsdivision relocation | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Mar 2017 | May 2017
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79BSVD | bronx special victimsdivision relocation | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | May 2017 | Sep 2017
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79BSVD | bronx special victimsdivision relocation | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Sep 2017 | Mar 2018
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79BSVD | bronx special victimsdivision relocation | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Mar 2018 | Jun 2018
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79BSVD | bronx special victimsdivision relocation | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Jun 2018 | Oct 2018
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79BSVD | bronx special victimsdivision relocation | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Oct 2018 | Feb 2019
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79BSVD | bronx special victimsdivision relocation | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | Feb 2019 | Jun 2019
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79BSVD | bronx special victimsdivision relocation | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79BSVD | bronx special victimsdivision relocation | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Sep 2019 | Nov 2019
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79BSVD | bronx special victimsdivision relocation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Nov 2019 | Dec 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293198X | 198 E 161ST STREET - FIRE ALARM UPGRADE | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Aug 2020
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293198X | 198 E 161ST STREET - FIRE ALARM UPGRADE | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293198X | 198 E 161ST STREET - FIRE ALARM UPGRADE | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293198X | 198 E 161ST STREET - FIRE ALARM UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293198X | 198 E 161ST STREET - FIRE ALARM UPGRADE | 5 | CONSTRUCTION TO 25% | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293198X | 198 E 161ST STREET - FIRE ALARM UPGRADE | 6 | CONSTRUCTION TO 50% | Jan 2023 | May 2023 | Jan 2023 | May 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293198X | 198 E 161ST STREET - FIRE ALARM UPGRADE | 7 | CONSTRUCTION TO 75% | May 2023 | Sep 2023 | May 2023 | Sep 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293198X | 198 E 161ST STREET - FIRE ALARM UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2023 | Dec 2023 | Sep 2023 | Dec 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293198X | 198 E 161ST STREET - FIRE ALARM UPGRADE | 9 | SUBSTANTIAL COMPLETION | Dec 2023 | Feb 2024 | Dec 2023 | Feb 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293198X | 198 E 161ST STREET - FIRE ALARM UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2024 | Mar 2024 | Feb 2024 | Jun 2027
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TOR2 | LAW DEPT TORTS - 260 EAST 161ST BRONX | 1 | DEVELOP SCOPE | Jun 2018 | Aug 2018 | Jun 2018 | Aug 2018
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TOR2 | LAW DEPT TORTS - 260 EAST 161ST BRONX | 2 | PRELIMINARY DESIGN | Aug 2018 | Dec 2018 | Aug 2018 | Dec 2018
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TOR2 | LAW DEPT TORTS - 260 EAST 161ST BRONX | 3 | FINAL DESIGN | Dec 2018 | Jun 2019 | Dec 2018 | Jun 2019
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TOR2 | LAW DEPT TORTS - 260 EAST 161ST BRONX | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2019 | Sep 2019 | Jun 2019 | Sep 2019
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TOR2 | LAW DEPT TORTS - 260 EAST 161ST BRONX | 5 | CONSTRUCTION TO 25% | Sep 2019 | Jan 2020 | Sep 2019 | Jan 2020
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TOR2 | LAW DEPT TORTS - 260 EAST 161ST BRONX | 6 | CONSTRUCTION TO 50% | Jan 2020 | May 2020 | Jan 2020 | May 2020
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TOR2 | LAW DEPT TORTS - 260 EAST 161ST BRONX | 7 | CONSTRUCTION TO 75% | May 2020 | Sep 2020 | May 2020 | Sep 2020
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TOR2 | LAW DEPT TORTS - 260 EAST 161ST BRONX | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2020 | Dec 2020 | Sep 2020 | Dec 2020
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TOR2 | LAW DEPT TORTS - 260 EAST 161ST BRONX | 9 | SUBSTANTIAL COMPLETION | Dec 2020 | Feb 2021 | Dec 2020 | Feb 2021
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TOR2 | LAW DEPT TORTS - 260 EAST 161ST BRONX | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2021 | Mar 2021 | Feb 2021 | Mar 2027
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198EV | 198 E 161 ST - ELEVATOR ,MODERNIZATION | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Aug 2020
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198EV | 198 E 161 ST - ELEVATOR ,MODERNIZATION | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198EV | 198 E 161 ST - ELEVATOR ,MODERNIZATION | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198EV | 198 E 161 ST - ELEVATOR ,MODERNIZATION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198EV | 198 E 161 ST - ELEVATOR ,MODERNIZATION | 5 | CONSTRUCTION TO 25% | Jun 2022 | Sep 2022 | Jun 2022 | Sep 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198EV | 198 E 161 ST - ELEVATOR ,MODERNIZATION | 6 | CONSTRUCTION TO 50% | Sep 2022 | Jan 2023 | Sep 2022 | Jan 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198EV | 198 E 161 ST - ELEVATOR ,MODERNIZATION | 7 | CONSTRUCTION TO 75% | Jan 2023 | May 2023 | Jan 2023 | May 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198EV | 198 E 161 ST - ELEVATOR ,MODERNIZATION | 8 | ORIGINAL EQUIP & FURNISHING | May 2023 | Aug 2023 | May 2023 | Aug 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198EV | 198 E 161 ST - ELEVATOR ,MODERNIZATION | 9 | SUBSTANTIAL COMPLETION | Aug 2023 | Oct 2023 | Aug 2023 | Oct 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198EV | 198 E 161 ST - ELEVATOR ,MODERNIZATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Oct 2023 | Nov 2023 | Oct 2023 | Nov 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198HV | 198 EAST 161 ST - MECHANICAL UPGRADE | 1 | DEVELOP SCOPE | Jun 2024 | Aug 2024 | Jun 2024 | Aug 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198HV | 198 EAST 161 ST - MECHANICAL UPGRADE | 2 | PRELIMINARY DESIGN | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198HV | 198 EAST 161 ST - MECHANICAL UPGRADE | 3 | FINAL DESIGN | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198HV | 198 EAST 161 ST - MECHANICAL UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198HV | 198 EAST 161 ST - MECHANICAL UPGRADE | 5 | CONSTRUCTION TO 25% | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198HV | 198 EAST 161 ST - MECHANICAL UPGRADE | 6 | CONSTRUCTION TO 50% | Jan 2026 | May 2026 | Jan 2026 | May 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198HV | 198 EAST 161 ST - MECHANICAL UPGRADE | 7 | CONSTRUCTION TO 75% | Jun 2027 | Sep 2027 | Jun 2027 | Sep 2027
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198HV | 198 EAST 161 ST - MECHANICAL UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2027 | Dec 2027 | Sep 2027 | Dec 2027
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198HV | 198 EAST 161 ST - MECHANICAL UPGRADE | 9 | SUBSTANTIAL COMPLETION | Dec 2027 | Feb 2028 | Dec 2027 | Feb 2028
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198HV | 198 EAST 161 ST - MECHANICAL UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2028 | Mar 2028 | Feb 2028 | Mar 2028
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198PD | 198 E 161st Street - DCAS Police Command Center | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198PD | 198 E 161st Street - DCAS Police Command Center | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198PD | 198 E 161st Street - DCAS Police Command Center | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198PD | 198 E 161st Street - DCAS Police Command Center | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198PD | 198 E 161st Street - DCAS Police Command Center | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198PD | 198 E 161st Street - DCAS Police Command Center | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198PD | 198 E 161st Street - DCAS Police Command Center | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198PD | 198 E 161st Street - DCAS Police Command Center | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198PD | 198 E 161st Street - DCAS Police Command Center | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198PD | 198 E 161st Street - DCAS Police Command Center | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207EL | 1932 ARTHUR AVE.- ELECTRICAL UPGRADES | 1 | DEVELOP SCOPE | Jul 2017 | Oct 2017 | May 2022 | Aug 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207EL | 1932 ARTHUR AVE.- ELECTRICAL UPGRADES | 2 | PRELIMINARY DESIGN | Oct 2017 | Feb 2018 | Aug 2022 | Dec 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207EL | 1932 ARTHUR AVE.- ELECTRICAL UPGRADES | 3 | FINAL DESIGN | Feb 2018 | Aug 2018 | Dec 2022 | Jun 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207EL | 1932 ARTHUR AVE.- ELECTRICAL UPGRADES | 4 | BID AWARD AND REGISTER CONTRCT | Aug 2018 | Nov 2018 | Jun 2023 | Sep 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207EL | 1932 ARTHUR AVE.- ELECTRICAL UPGRADES | 5 | CONSTRUCTION TO 25% | Nov 2018 | Mar 2019 | Sep 2023 | Jan 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207EL | 1932 ARTHUR AVE.- ELECTRICAL UPGRADES | 6 | CONSTRUCTION TO 50% | Mar 2019 | Jul 2019 | Jan 2024 | May 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207EL | 1932 ARTHUR AVE.- ELECTRICAL UPGRADES | 7 | CONSTRUCTION TO 75% | Jul 2019 | Nov 2019 | May 2024 | Sep 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207EL | 1932 ARTHUR AVE.- ELECTRICAL UPGRADES | 8 | ORIGINAL EQUIP & FURNISHING | Nov 2019 | Jan 2020 | Jun 2021 | Aug 2021
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207EL | 1932 ARTHUR AVE.- ELECTRICAL UPGRADES | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Aug 2021 | Oct 2021
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207EL | 1932 ARTHUR AVE.- ELECTRICAL UPGRADES | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Oct 2021 | Jun 2030
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207HV | 1932 ARTHUR AVE - CENTRAL HVAC SYSTEM | 1 | DEVELOP SCOPE | Jun 2022 | Jan 2023 | Jun 2022 | Jan 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207HV | 1932 ARTHUR AVE - CENTRAL HVAC SYSTEM | 2 | PRELIMINARY DESIGN | Jan 2023 | Oct 2023 | Jan 2023 | Oct 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207HV | 1932 ARTHUR AVE - CENTRAL HVAC SYSTEM | 3 | FINAL DESIGN | Oct 2023 | Apr 2024 | Oct 2023 | Apr 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207HV | 1932 ARTHUR AVE - CENTRAL HVAC SYSTEM | 4 | BID AWARD AND REGISTER CONTRCT | Apr 2024 | Nov 2024 | Apr 2024 | Nov 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207HV | 1932 ARTHUR AVE - CENTRAL HVAC SYSTEM | 5 | CONSTRUCTION TO 25% | Dec 2024 | Mar 2025 | Dec 2024 | Mar 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207HV | 1932 ARTHUR AVE - CENTRAL HVAC SYSTEM | 6 | CONSTRUCTION TO 50% | Mar 2025 | Jul 2025 | Mar 2025 | Jul 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207HV | 1932 ARTHUR AVE - CENTRAL HVAC SYSTEM | 7 | CONSTRUCTION TO 75% | Jul 2025 | Nov 2025 | Jul 2025 | Nov 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207HV | 1932 ARTHUR AVE - CENTRAL HVAC SYSTEM | 8 | ORIGINAL EQUIP & FURNISHING | Nov 2025 | Feb 2026 | Nov 2025 | Feb 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207HV | 1932 ARTHUR AVE - CENTRAL HVAC SYSTEM | 9 | SUBSTANTIAL COMPLETION | Feb 2026 | Apr 2026 | Feb 2026 | Apr 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207HV | 1932 ARTHUR AVE - CENTRAL HVAC SYSTEM | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Apr 2026 | May 2026 | Apr 2026 | May 2030
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207RF | 1932 ARTHUR AVE ENVELOPE STABILIZATION | 1 | DEVELOP SCOPE | Jun 2020 | Aug 2020 | Jun 2020 | Aug 2020
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207RF | 1932 ARTHUR AVE ENVELOPE STABILIZATION | 2 | PRELIMINARY DESIGN | Aug 2020 | Dec 2020 | Aug 2020 | Dec 2020
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207RF | 1932 ARTHUR AVE ENVELOPE STABILIZATION | 3 | FINAL DESIGN | Dec 2020 | Jun 2021 | Dec 2020 | Jun 2021
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207RF | 1932 ARTHUR AVE ENVELOPE STABILIZATION | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2021 | Sep 2021 | Jun 2021 | Sep 2021
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207RF | 1932 ARTHUR AVE ENVELOPE STABILIZATION | 5 | CONSTRUCTION TO 25% | Sep 2021 | Jan 2022 | Sep 2021 | Jan 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207RF | 1932 ARTHUR AVE ENVELOPE STABILIZATION | 6 | CONSTRUCTION TO 50% | Jan 2022 | May 2022 | Jan 2022 | May 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207RF | 1932 ARTHUR AVE ENVELOPE STABILIZATION | 7 | CONSTRUCTION TO 75% | May 2022 | Sep 2022 | May 2022 | Sep 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207RF | 1932 ARTHUR AVE ENVELOPE STABILIZATION | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2022 | Dec 2022 | Sep 2022 | Dec 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207RF | 1932 ARTHUR AVE ENVELOPE STABILIZATION | 9 | SUBSTANTIAL COMPLETION | Dec 2022 | Feb 2023 | Dec 2022 | Feb 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207RF | 1932 ARTHUR AVE ENVELOPE STABILIZATION | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2023 | Mar 2025 | Feb 2023 | Mar 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77208EL | 4101 WHITE PLAINS RD. - ELECTRICAL & FA UPGRADE | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2022 | Aug 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77208EL | 4101 WHITE PLAINS RD. - ELECTRICAL & FA UPGRADE | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2022 | Dec 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77208EL | 4101 WHITE PLAINS RD. - ELECTRICAL & FA UPGRADE | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2022 | Jun 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77208EL | 4101 WHITE PLAINS RD. - ELECTRICAL & FA UPGRADE | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2023 | Sep 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77208EL | 4101 WHITE PLAINS RD. - ELECTRICAL & FA UPGRADE | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | Sep 2023 | Jan 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77208EL | 4101 WHITE PLAINS RD. - ELECTRICAL & FA UPGRADE | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | Jan 2024 | May 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77208EL | 4101 WHITE PLAINS RD. - ELECTRICAL & FA UPGRADE | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | May 2024 | Sep 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77208EL | 4101 WHITE PLAINS RD. - ELECTRICAL & FA UPGRADE | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Sep 2024 | Dec 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77208EL | 4101 WHITE PLAINS RD. - ELECTRICAL & FA UPGRADE | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Dec 2024 | Feb 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77208EL | 4101 WHITE PLAINS RD. - ELECTRICAL & FA UPGRADE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Mar 2025 | Feb 2025 | Mar 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CTCX4 | 2556 BAINBRIDGE AVE- CIVIL SERVICE EXAM TESTING CENTER | 1 | PROJECT START | Jun 2016 | Jun 2016 | Jun 2016 | Sep 2016
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CTCX4 | 2556 BAINBRIDGE AVE- CIVIL SERVICE EXAM TESTING CENTER | 2 | DESIGN START | Jul 2016 | Dec 2016 | Sep 2016 | Jan 2017
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CTCX4 | 2556 BAINBRIDGE AVE- CIVIL SERVICE EXAM TESTING CENTER | 3 | DESIGN COMPLETION | Dec 2016 | Apr 2017 | Jan 2017 | Jul 2017
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CTCX4 | 2556 BAINBRIDGE AVE- CIVIL SERVICE EXAM TESTING CENTER | 4 | CONSTRUCTION START | Apr 2017 | Nov 2017 | Jul 2017 | Oct 2017
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CTCX4 | 2556 BAINBRIDGE AVE- CIVIL SERVICE EXAM TESTING CENTER | 5 | CONSTRUCTION COMPLETION | Dec 2017 | Dec 2024 | Oct 2017 | Feb 2018
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CTCX4 | 2556 BAINBRIDGE AVE- CIVIL SERVICE EXAM TESTING CENTER | 6 | CONSTRUCTION TO 50% | Dec 2017 | Dec 2024 | Feb 2018 | Jun 2018
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CTCX4 | 2556 BAINBRIDGE AVE- CIVIL SERVICE EXAM TESTING CENTER | 7 | CONSTRUCTION TO 75% | Dec 2017 | Dec 2024 | Jun 2018 | Oct 2018
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CTCX4 | 2556 BAINBRIDGE AVE- CIVIL SERVICE EXAM TESTING CENTER | 8 | ORIGINAL EQUIP & FURNISHING | Dec 2017 | Dec 2024 | Oct 2018 | Jan 2019
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CTCX4 | 2556 BAINBRIDGE AVE- CIVIL SERVICE EXAM TESTING CENTER | 9 | SUBSTANTIAL COMPLETION | Dec 2017 | Dec 2024 | Jan 2019 | Mar 2019
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CTCX4 | 2556 BAINBRIDGE AVE- CIVIL SERVICE EXAM TESTING CENTER | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Dec 2017 | Dec 2024 | Mar 2019 | Apr 2028
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77X215 | 215 E161 ST.- OFFICE RENOVATIONS | 1 | DEVELOP SCOPE | Jun 2012 | Sep 2012 | Jun 2027 | Aug 2027
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77X215 | 215 E161 ST.- OFFICE RENOVATIONS | 2 | PRELIMINARY DESIGN | Sep 2012 | Jan 2013 | Aug 2027 | Dec 2027
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77X215 | 215 E161 ST.- OFFICE RENOVATIONS | 3 | FINAL DESIGN | Jan 2013 | Jul 2013 | Dec 2027 | Jun 2028
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77X215 | 215 E161 ST.- OFFICE RENOVATIONS | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2013 | Oct 2013 | Jun 2028 | Sep 2028
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77X215 | 215 E161 ST.- OFFICE RENOVATIONS | 5 | CONSTRUCTION TO 25% | Oct 2013 | Feb 2014 | Sep 2028 | Jan 2029
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77X215 | 215 E161 ST.- OFFICE RENOVATIONS | 6 | CONSTRUCTION TO 50% | Feb 2014 | Jun 2014 | Jan 2029 | May 2029
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77X215 | 215 E161 ST.- OFFICE RENOVATIONS | 7 | CONSTRUCTION TO 75% | Jun 2014 | Oct 2014 | May 2029 | Sep 2029
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77X215 | 215 E161 ST.- OFFICE RENOVATIONS | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2014 | Jan 2015 | Sep 2029 | Dec 2029
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77X215 | 215 E161 ST.- OFFICE RENOVATIONS | 9 | SUBSTANTIAL COMPLETION | Jan 2015 | Mar 2015 | Dec 2029 | Feb 2030
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77X215 | 215 E161 ST.- OFFICE RENOVATIONS | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2015 | Apr 2015 | Feb 2030 | May 2032
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWBXDHVAC | BRONX DA DATACENTER HVAC | 1 | DEVELOP SCOPE | Jun 2023 | Aug 2023 | Jun 2023 | Aug 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWBXDHVAC | BRONX DA DATACENTER HVAC | 2 | PRELIMINARY DESIGN | Aug 2023 | Dec 2023 | Aug 2023 | Dec 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWBXDHVAC | BRONX DA DATACENTER HVAC | 3 | FINAL DESIGN | Dec 2023 | Jun 2024 | Dec 2023 | Jun 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWBXDHVAC | BRONX DA DATACENTER HVAC | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2024 | Sep 2024 | Jun 2024 | Sep 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWBXDHVAC | BRONX DA DATACENTER HVAC | 5 | CONSTRUCTION TO 25% | Sep 2024 | Jan 2025 | Sep 2024 | Jan 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWBXDHVAC | BRONX DA DATACENTER HVAC | 6 | CONSTRUCTION TO 50% | Jan 2025 | May 2025 | Jan 2025 | May 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWBXDHVAC | BRONX DA DATACENTER HVAC | 7 | CONSTRUCTION TO 75% | May 2025 | Sep 2025 | May 2025 | Sep 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWBXDHVAC | BRONX DA DATACENTER HVAC | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2025 | Dec 2025 | Sep 2025 | Dec 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWBXDHVAC | BRONX DA DATACENTER HVAC | 9 | SUBSTANTIAL COMPLETION | Dec 2025 | Feb 2026 | Dec 2025 | Feb 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWBXDHVAC | BRONX DA DATACENTER HVAC | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2026 | Mar 2026 | Feb 2026 | Mar 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA1 | 2556 Bainbridge Ave. Community Ctr. | 1 | DEVELOP SCOPE | Jun 2022 | Aug 2022 | Jun 2027 | Aug 2027
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA1 | 2556 Bainbridge Ave. Community Ctr. | 2 | PRELIMINARY DESIGN | Aug 2022 | Dec 2022 | Aug 2027 | Dec 2027
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA1 | 2556 Bainbridge Ave. Community Ctr. | 3 | FINAL DESIGN | Dec 2022 | Jun 2023 | Dec 2027 | Jun 2028
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA1 | 2556 Bainbridge Ave. Community Ctr. | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2023 | Sep 2023 | Jun 2028 | Sep 2028
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA1 | 2556 Bainbridge Ave. Community Ctr. | 5 | CONSTRUCTION TO 25% | Sep 2023 | Jan 2024 | Sep 2028 | Jan 2029
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA1 | 2556 Bainbridge Ave. Community Ctr. | 6 | CONSTRUCTION TO 50% | Jan 2024 | May 2024 | Jan 2029 | May 2029
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA1 | 2556 Bainbridge Ave. Community Ctr. | 7 | CONSTRUCTION TO 75% | May 2024 | Sep 2024 | May 2029 | Sep 2029
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA1 | 2556 Bainbridge Ave. Community Ctr. | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2024 | Dec 2024 | Sep 2029 | Dec 2029
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA1 | 2556 Bainbridge Ave. Community Ctr. | 9 | SUBSTANTIAL COMPLETION | Dec 2024 | Feb 2025 | Dec 2029 | Feb 2030
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA1 | 2556 Bainbridge Ave. Community Ctr. | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2025 | Mar 2025 | Feb 2030 | Mar 2030
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA2 | 2556 Bainbridge Ave - Fordham Library renovation | 1 | DEVELOP SCOPE | Jun 2017 | Sep 2017 | Jun 2027 | Aug 2027
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA2 | 2556 Bainbridge Ave - Fordham Library renovation | 2 | PRELIMINARY DESIGN | Sep 2017 | Jan 2018 | Aug 2027 | Dec 2027
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA2 | 2556 Bainbridge Ave - Fordham Library renovation | 3 | FINAL DESIGN | Jan 2018 | Jul 2018 | Dec 2027 | Jun 2028
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA2 | 2556 Bainbridge Ave - Fordham Library renovation | 4 | BID AWARD AND REGISTER CONTRCT | Jul 2018 | Oct 2018 | Jun 2028 | Sep 2028
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA2 | 2556 Bainbridge Ave - Fordham Library renovation | 5 | CONSTRUCTION TO 25% | Oct 2018 | Feb 2019 | Sep 2028 | Jan 2029
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA2 | 2556 Bainbridge Ave - Fordham Library renovation | 6 | CONSTRUCTION TO 50% | Feb 2019 | Jun 2019 | Jan 2029 | May 2029
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA2 | 2556 Bainbridge Ave - Fordham Library renovation | 7 | CONSTRUCTION TO 75% | Jun 2019 | Oct 2019 | May 2029 | Sep 2029
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA2 | 2556 Bainbridge Ave - Fordham Library renovation | 8 | ORIGINAL EQUIP & FURNISHING | Oct 2019 | Jan 2020 | Sep 2029 | Dec 2029
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA2 | 2556 Bainbridge Ave - Fordham Library renovation | 9 | SUBSTANTIAL COMPLETION | Jan 2020 | Mar 2020 | Dec 2029 | Feb 2030
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA2 | 2556 Bainbridge Ave - Fordham Library renovation | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Mar 2020 | Apr 2020 | Feb 2030 | Mar 2030
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDPLONG2 | POLICE ATHLETIC LEAGUE | 1 | DEVELOP SCOPE | Jun 2024 | Aug 2024 | Jun 2024 | Aug 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDPLONG2 | POLICE ATHLETIC LEAGUE | 2 | PRELIMINARY DESIGN | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDPLONG2 | POLICE ATHLETIC LEAGUE | 3 | FINAL DESIGN | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDPLONG2 | POLICE ATHLETIC LEAGUE | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDPLONG2 | POLICE ATHLETIC LEAGUE | 5 | CONSTRUCTION TO 25% | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDPLONG2 | POLICE ATHLETIC LEAGUE | 6 | CONSTRUCTION TO 50% | Jan 2026 | May 2026 | Jan 2026 | May 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDPLONG2 | POLICE ATHLETIC LEAGUE | 7 | CONSTRUCTION TO 75% | May 2026 | Sep 2026 | May 2026 | Sep 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDPLONG2 | POLICE ATHLETIC LEAGUE | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2026 | Dec 2026 | Sep 2026 | Dec 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDPLONG2 | POLICE ATHLETIC LEAGUE | 9 | SUBSTANTIAL COMPLETION | Dec 2026 | Feb 2027 | Dec 2026 | Feb 2027
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDPLONG2 | POLICE ATHLETIC LEAGUE | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2027 | Mar 2027 | Feb 2027 | Mar 2027
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXBP78 | Bronx BP Initial Outfit., Demo, Cons - 851 Grand Concourse | 1 | DEVELOP SCOPE | Jun 2028 | Aug 2028 | Jun 2024 | Aug 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXBP78 | Bronx BP Initial Outfit., Demo, Cons - 851 Grand Concourse | 2 | PRELIMINARY DESIGN | Aug 2028 | Dec 2028 | Aug 2024 | Dec 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXBP78 | Bronx BP Initial Outfit., Demo, Cons - 851 Grand Concourse | 3 | FINAL DESIGN | Dec 2028 | Jun 2029 | Dec 2024 | Jun 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXBP78 | Bronx BP Initial Outfit., Demo, Cons - 851 Grand Concourse | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2029 | Sep 2029 | Jun 2025 | Sep 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXBP78 | Bronx BP Initial Outfit., Demo, Cons - 851 Grand Concourse | 5 | CONSTRUCTION TO 25% | Sep 2029 | Jan 2030 | Sep 2025 | Jan 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXBP78 | Bronx BP Initial Outfit., Demo, Cons - 851 Grand Concourse | 6 | CONSTRUCTION TO 50% | Jan 2030 | May 2030 | Jan 2026 | May 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXBP78 | Bronx BP Initial Outfit., Demo, Cons - 851 Grand Concourse | 7 | CONSTRUCTION TO 75% | May 2030 | Sep 2030 | May 2026 | Sep 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXBP78 | Bronx BP Initial Outfit., Demo, Cons - 851 Grand Concourse | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2030 | Dec 2030 | Sep 2026 | Dec 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXBP78 | Bronx BP Initial Outfit., Demo, Cons - 851 Grand Concourse | 9 | SUBSTANTIAL COMPLETION | Dec 2030 | Feb 2031 | Dec 2026 | Feb 2027
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXBP78 | Bronx BP Initial Outfit., Demo, Cons - 851 Grand Concourse | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2031 | Mar 2032 | Feb 2027 | Mar 2028
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXGLASS | 851 GRAND CONCOURSE- Entry Glass Doors | 1 | DEVELOP SCOPE | Jun 2024 | Aug 2024 | Jun 2024 | Aug 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXGLASS | 851 GRAND CONCOURSE- Entry Glass Doors | 2 | PRELIMINARY DESIGN | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXGLASS | 851 GRAND CONCOURSE- Entry Glass Doors | 3 | FINAL DESIGN | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXGLASS | 851 GRAND CONCOURSE- Entry Glass Doors | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXGLASS | 851 GRAND CONCOURSE- Entry Glass Doors | 5 | CONSTRUCTION TO 25% | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXGLASS | 851 GRAND CONCOURSE- Entry Glass Doors | 6 | CONSTRUCTION TO 50% | Jan 2026 | May 2026 | Jan 2026 | May 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXGLASS | 851 GRAND CONCOURSE- Entry Glass Doors | 7 | CONSTRUCTION TO 75% | May 2026 | Sep 2026 | May 2026 | Sep 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXGLASS | 851 GRAND CONCOURSE- Entry Glass Doors | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2026 | Dec 2026 | Sep 2026 | Dec 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXGLASS | 851 GRAND CONCOURSE- Entry Glass Doors | 9 | SUBSTANTIAL COMPLETION | Dec 2026 | Feb 2027 | Dec 2026 | Feb 2027
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXGLASS | 851 GRAND CONCOURSE- Entry Glass Doors | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2027 | Mar 2027 | Feb 2027 | Mar 2027
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-365 | DSNY - 125 E 149TH ST, BX - MN WEST 9 GARAGE LEASE RENEWAL | 1 | DEVELOP SCOPE | Jun 2024 | Aug 2024 | Jun 2024 | Aug 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-365 | DSNY - 125 E 149TH ST, BX - MN WEST 9 GARAGE LEASE RENEWAL | 2 | PRELIMINARY DESIGN | Aug 2024 | Dec 2024 | Aug 2024 | Dec 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-365 | DSNY - 125 E 149TH ST, BX - MN WEST 9 GARAGE LEASE RENEWAL | 3 | FINAL DESIGN | Dec 2024 | Jun 2025 | Dec 2024 | Jun 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-365 | DSNY - 125 E 149TH ST, BX - MN WEST 9 GARAGE LEASE RENEWAL | 4 | BID AWARD AND REGISTER CONTRCT | Jun 2025 | Sep 2025 | Jun 2025 | Sep 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-365 | DSNY - 125 E 149TH ST, BX - MN WEST 9 GARAGE LEASE RENEWAL | 5 | CONSTRUCTION TO 25% | Sep 2025 | Jan 2026 | Sep 2025 | Jan 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-365 | DSNY - 125 E 149TH ST, BX - MN WEST 9 GARAGE LEASE RENEWAL | 6 | CONSTRUCTION TO 50% | Jan 2026 | May 2026 | Jan 2026 | May 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-365 | DSNY - 125 E 149TH ST, BX - MN WEST 9 GARAGE LEASE RENEWAL | 7 | CONSTRUCTION TO 75% | May 2026 | Sep 2026 | May 2026 | Sep 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-365 | DSNY - 125 E 149TH ST, BX - MN WEST 9 GARAGE LEASE RENEWAL | 8 | ORIGINAL EQUIP & FURNISHING | Sep 2026 | Dec 2026 | Sep 2026 | Dec 2026
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-365 | DSNY - 125 E 149TH ST, BX - MN WEST 9 GARAGE LEASE RENEWAL | 9 | SUBSTANTIAL COMPLETION | Dec 2026 | Feb 2027 | Dec 2026 | Feb 2027
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-365 | DSNY - 125 E 149TH ST, BX - MN WEST 9 GARAGE LEASE RENEWAL | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Feb 2027 | Mar 2027 | Feb 2027 | Mar 2027
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-434 | DSNY - 720-780 E132 St - Bronx 1 3 4 Garage Rehab | 1 | DEVELOP SCOPE | Mar 2017 | May 2017 | Jun 2021 | Aug 2021
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-434 | DSNY - 720-780 E132 St - Bronx 1 3 4 Garage Rehab | 2 | PRELIMINARY DESIGN | May 2017 | Sep 2017 | Aug 2021 | Dec 2021
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-434 | DSNY - 720-780 E132 St - Bronx 1 3 4 Garage Rehab | 3 | FINAL DESIGN | Sep 2017 | Mar 2018 | Dec 2021 | Jun 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-434 | DSNY - 720-780 E132 St - Bronx 1 3 4 Garage Rehab | 4 | BID AWARD AND REGISTER CONTRCT | Mar 2018 | Jun 2018 | Jun 2022 | Sep 2022
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-434 | DSNY - 720-780 E132 St - Bronx 1 3 4 Garage Rehab | 5 | CONSTRUCTION TO 25% | Jun 2018 | Oct 2018 | Sep 2022 | Jan 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-434 | DSNY - 720-780 E132 St - Bronx 1 3 4 Garage Rehab | 6 | CONSTRUCTION TO 50% | Oct 2018 | Feb 2019 | Jan 2023 | May 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-434 | DSNY - 720-780 E132 St - Bronx 1 3 4 Garage Rehab | 7 | CONSTRUCTION TO 75% | Feb 2019 | Jun 2019 | May 2023 | Sep 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-434 | DSNY - 720-780 E132 St - Bronx 1 3 4 Garage Rehab | 8 | ORIGINAL EQUIP & FURNISHING | Jun 2019 | Sep 2019 | Sep 2023 | Dec 2023
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-434 | DSNY - 720-780 E132 St - Bronx 1 3 4 Garage Rehab | 9 | SUBSTANTIAL COMPLETION | Sep 2019 | Nov 2019 | Dec 2023 | Feb 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-434 | DSNY - 720-780 E132 St - Bronx 1 3 4 Garage Rehab | 10 | PUNCHLIST COMPLETE, JOB CLOSED | Nov 2019 | Dec 2019 | Feb 2024 | Mar 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCA24X039 | SCA FY24 Electrification - X039 | 1 | DEVELOP SCOPE | Jun 2024 | Jun 2024 | Jun 2024 | Jun 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCA24X039 | SCA FY24 Electrification - X039 | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2024 | Aug 2024 | Jul 2024 | Aug 2024
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCA24X039 | SCA FY24 Electrification - X039 | 3 | CONSTRUCTION TO 50% | Aug 2024 | Feb 2025 | Aug 2024 | Feb 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCA24X039 | SCA FY24 Electrification - X039 | 4 | CONSTRUCTION TO 75% | Feb 2025 | May 2025 | Feb 2025 | May 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCA24X039 | SCA FY24 Electrification - X039 | 5 | SUBSTANTIAL COMPLETION | May 2025 | Jul 2025 | May 2025 | Jul 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCA24X039 | SCA FY24 Electrification - X039 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2025 | Aug 2025 | Jul 2025 | Aug 2025
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-X099 | SCA Electrification - X099 | 1 | DEVELOP SCOPE | Jun 2028 | Jun 2028 | Jun 2028 | Jun 2028
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-X099 | SCA Electrification - X099 | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2028 | Aug 2028 | Jul 2028 | Aug 2028
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-X099 | SCA Electrification - X099 | 3 | CONSTRUCTION TO 50% | Aug 2028 | Feb 2029 | Aug 2028 | Feb 2029
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-X099 | SCA Electrification - X099 | 4 | CONSTRUCTION TO 75% | Feb 2029 | May 2029 | Feb 2029 | May 2029
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-X099 | SCA Electrification - X099 | 5 | SUBSTANTIAL COMPLETION | May 2029 | Jul 2029 | May 2029 | Jul 2029
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCAE-X099 | SCA Electrification - X099 | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2029 | Aug 2029 | Jul 2029 | Aug 2029
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARPQL2 | DCAS PQL Round 2 (EdEn) | 1 | DEVELOP SCOPE | Jun 2020 | Jun 2020 | Jun 2020 | Jun 2020
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARPQL2 | DCAS PQL Round 2 (EdEn) | 2 | BID AWARD AND REGISTER CONTRCT | Jul 2020 | Aug 2020 | Jul 2020 | Aug 2020
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARPQL2 | DCAS PQL Round 2 (EdEn) | 3 | CONSTRUCTION TO 50% | Aug 2020 | Feb 2021 | Aug 2020 | Feb 2021
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARPQL2 | DCAS PQL Round 2 (EdEn) | 4 | CONSTRUCTION TO 75% | Feb 2021 | May 2021 | Feb 2021 | May 2021
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARPQL2 | DCAS PQL Round 2 (EdEn) | 5 | SUBSTANTIAL COMPLETION | May 2021 | Jul 2021 | May 2021 | Jul 2021
20231026 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARPQL2 | DCAS PQL Round 2 (EdEn) | 6 | PUNCHLIST COMPLETE, JOB CLOSED | Jul 2021 | Aug 2021 | Jul 2021 | Aug 2025