## NYC Rezoning Commitments Tracke
Rezoning Area | Commitment Title | Map Order | Rezoning Policy Domain | Lead Agency | Commitment Stage | 2019 Narrative Content | Statement from Source Document/POA | Original schedule | 2017 Narrative Content (East New York only) | 2018 Narrative Content
East Harlem | Prioritize the development of over 2,600 affordable homes on publicly owned land | 1 | Housing | HPD | In Progress | The City is expediting the construction of over 2,600 affordable homes on publicly owned sites in East Harlem over the next several years. Several of these projects have been in development for some time, while others are being prioritized based on feedback from the community. The MEC Center continues to make progress: in early 2019, construction begain on 270 affordable homes. The East Harlem NIHOP/NCP RFQ cluster was designated to Ascendant Neighborhood Development and MDG (Las Raices), which will culminate into four buildings and approximately 80 new affordable homes, with two buildings that contain commercial properties. This development will soon undergo the Uniform Land Use Reform Procedure (ULURP) for disposition and other potential actions. ACACIA Gardens completed construction and lease up in 2018, providing about 180 affordable homes to extremely low- to moderate-income New Yorkers, including formerly homeless households. In response to feedback from the community, the City committed to deeper levels of affordability for the Lexington Gardens II, Sendero Verde (SustaiNYC), and 126th Street Bus Depot sites, where at least 20% of all units will be set aside for households earning up to 30% of AMI. Lexington Gardens II is currently under construction and is expected to be completed around the end of the year. Sendero Verde is undergoing a phased development, with the first phase anticipated to begin construction in 2019. Lastly, EDC anticipates issuing an RFP for the 126th St Bus Depot in 2020. | The City will expedite the construction of over 2,600 units of affordable housing on publicly owned sites in East Harlem over the next several years. A few of these projects - such as the MEC Center and NIHOP/NCP RFQ Clusters - have been in development for some time, while others are being prioritized based on feedback from the community. In response to feedback from the community, the City is committing to deeper levels of affordability for the Lexington Gardens II, Sendero Verde (SustaiNYC), and 126th Street Bus Depot sites, where at least 20% of all units will be set aside for households earning up to 30% of AMI. The Acacia Gardens project, which is already under construction, will primarily serve low-income and formerly homeless households. | N/A |  | The City is expediting the construction of over 2,600 units of affordable housing on publicly owned sites in East Harlem over the next several years. In response to feedback from the community, the City committed to deeper levels of affordability for the Lexington Gardens II, Sendero Verde (SustaiNYC), and 126th Street Bus Depot sites, where at least 20% of all units will be set aside for households earning up to 30% of AMI.
East Harlem | Invest in capital improvements within 17 NYCHA developments and early childhood centers | 2 | Housing | NYCHA | In Progress | Since June 2018, NYCHA has moved forward with obtaining project management support to carry out capital improvement projects within 17 NYCHA developments and early childhood centers. The Program Management contracts are in the process of approval by OMB and the Controller. Design work is expected to commence in FY20. | The city will commit $50 million in capital improvements including: 1. Modernize all ventilation in 17 East Harlem developments including 122 buildings and 12,719 apartments ($20 million) 2. Renovate kitchens and bathrooms at Leggett Memorial Early Childhood Center at 237 East 104th Street, Union Carver Early Childhood Center at 1565 Madison Avenue, and Union Washington Early Childhood Center at 1893 Second Avenue. Renovate playground at Jefferson Houses Early Childhood Center at 2211 First Avenue ($7.7 million) 3. Fund a new elevator at 335 East 111th Street ($1 million) 4. Replace boilers at Lehman Village and Wilson Houses ($13.2 million) 5. Conduct roof and parapet work at UPACA (Site 5) ($2.5 million) 6. Install new gas risers at Johnson Houses ($5.5 million) | FY 2018 |  | NYCHA’s Capital team released an RFP for Program Management services in June 2018. This team will be managing special capital projects for NYCHA, including the East Harlem Rezoning. These East Harlem projects will enter the planning phase by the end of 2018.
East Harlem | Establish a Certificate of No Harassment (CONH) Pilot Program | 3 | Housing | HPD | In Progress | HPD received funding in the FY 2019 budget to implement the pilot Certification of No Harassment (CONH) program in designated neighborhoods, including East Harlem, to protect tenants from being harassed from their homes. Owners of designated buildings are required to obtain a CONH before being granted building permits for specified covered work in the buildings. The program launched in fall 2018. In East Harlem, 37 buildings are subject to the program, and HPD has received a CONH application related to one building since the program went into effect. | In response to feedback from the community and growing interest across the city, the Administration, pursuant to legislative authorization, will enforce a pilot CONH program in designated neighborhoods, including East Harlem, to protect certain tenants from being harassed from their homes. This program will identify specific buildings which meet criteria indicating that tenants may be at risk for harassment. Owners of such buildings would be required to obtain a CONH before being granted building permits for specified covered work in the buildings. | Within a year of legislation passage |  | HPD received funding in the Fiscal Year 2019 preliminary budget to implement the pilot Certification of No Harassment (CONH) program in designated neighborhoods, including East Harlem, to protect certain tenants from being harassed from their homes. Owners of such buildings would be required to obtain a CONH before being granted building permits for specified covered work in the buildings. HPD continues to refine program implementation and will formally launch the program in Fall 2018.
East Harlem | Expand anti-harassment legal services | 4 | Housing | HRA | Done with ongoing work | To support tenants who are facing eviction or harassment, the City has expanded funding for civil legal services for low-income New Yorkers. Since October 2015, the City has provided 2,154 households with legal services in East Harlem; this includes 6,142 individuals of which 2,239 were children. In Fiscal 2018, 738 households were provided with legal services and in the first 10 months of Fiscal 2019, 550 households have already been served. These legal services have been a mixture of affirmative litigation to identify and combat harassment and eviction defense. The Fiscal 2020 Executive Budget includes a city-wide total of $127 million for anti-eviction and anti-harassment tenant legal services. | To support tenants who are facing eviction or harassment, the City has expanded funding for civil legal services for low-income New Yorkers. In East Harlem, the City's Human Resources Administration (HRA) launched the tenant legal services program in FY 2015. HRA is investing $4.6 million of funding annually, which is fully secured through FY 2021. The program focuses on ensuring that tenants can stay in their neighborhood by providing access to legal representation that is both proactive - i.e., working with residents and tenant associations to identify patterns of harassment - and responsive to evictions and other cases tenants may face in court. | 2017-2021 |  | To support tenants who are facing eviction or harassment, the City has expanded funding for civil legal services for low-income New Yorkers. From October 2015 to March 2018, the City provided 1,436 households with legal services in East Harlem, including 2,628 adults and 1,602 children. In Fiscal 2017, 574 households were provided with legal services and in the first 10 months of Fiscal 2018, 579 households had already been served. These legal services have included affirmative litigation to identify and combat harassment and eviction defense. The Fiscal 2019 Executive Budget includes a citywide total of $94 million for anti-eviction and anti-harassment tenant legal services.
East Harlem | Implement the Neighborhood Pillars Program to help community organizations acquire rent stabilized buildings | 5 | Housing | HPD | In Progress | HPD and HDC announced the Neighborhood Pillars program in fall 2017 to finance the acquisition and rehabilitation of existing rent-regulated buildings to protect current tenants and stabilize communities. HPD released a Preservation Buyers Request for Qualifications (RFQ), and responses from organizations interested in participating are accepted on a rolling basis. HPD launched the Downpayment Assistance Fund and issued a new financing program term sheet in late 2018. The City expects to support the acquisition of a half dozen or more properties across New York City by fall 2019. | HPD and HDC are launching a new Neighborhood Pillars program to finance the acquisition and rehabilitation of existing rent-regulated buildings to protect current tenants and stabilize communities. In fast-changing neighborhoods, the sale of rent-stabilized apartment buildings is often a harbinger of rising rents and tenant turnover. However, non-profit and other mission-based organizations that want to purchase buildings in order to keep them affordable often lack the capital and financing to compete in those transactions. In response, the new program will leverage funding from private sector banking partners and philanthropic organizations to provide capital to neighborhood-based organizations well positioned to identify the buildings most at risk of speculation and rapid turnover. The City will double the capacity of the Acquisition Loan Fund to $275 million, leveraging funding contributions from private sector banking partners and philanthropic organizations, to enable non-profits and mission-based organizations to acquire buildings that are rent-regulated, but not otherwise part of an existing affordable housing program. | 2019 |  | HPD and HDC announced the Neighborhood Pillars program in Fall 2017 to finance the acquisition and rehabilitation of existing rent-regulated buildings to protect current tenants and stabilize communities. HPD released a Preservation Buyers Request for Qualifications (RFQ) and responses from organizations interested in participating in Neighborhood Pillars are rolling starting May 31, 2018. HPD continues to finalize program implementation and expects to launch Neighborhood Pillars by Fall 2018.
East Harlem | Have Tenant Support Unit (TSU) conduct outreach | 6 | Housing | HPD | In Progress | Tenant Support Unit (TSU) specialists are on the ground in East Harlem, conducting proactive outreach to tenants to inform them of their rights, identify housing-related issues faced by members of the community and connect tenants to free City services, such as legal assistance to mitigate displacement, landlord harassment, and facilitate home-related repairs. To date, specialists, who speak multiple languages and are often from the community in which they work, have knocked on over 24,280 doors in the area. TSU has also made over 12,242 follow up calls to provide comprehensive case management to tenants – bridging the gap between the City and tenants by helping them through the process of accessing resources. From July 2015 through June 2019, TSU specialists have assisted over 1,855 New Yorkers in zip codes 10029 and 10035. | Finally, outreach specialists with the City's new Tenant Support Unit (TSU) are going door-to-door in East Harlem, informing tenants of their rights, documenting complaints related to harassment and eviction, and making referrals to free legal support whenever necessary. Since July 2015, TSU specialists have knocked on over 28,000 doors and assisted over 1,500 tenants in East Harlem. | 2017-ongoing |  | Tenant Support Unit (TSU) specialists are on the ground in East Harlem, conducting proactive outreach to tenants to inform them of their rights, identify housing-related issues and connect tenants to free City services like legal assistance to mitigate displacement and landlord harassment, and facilitate home-related repairs. From July 2015 through mid-May 2018, specialists, who collectively speak over 12 languages, knocked on over 21,000 doors in the area. TSU also made over 9,900 follow-up calls to provide comprehensive case management to tenants – bridging the gap between the City and tenants by helping them through the process of accessing resources. During this period, TSU specialists assisted over 1,500 New Yorkers in zip codes 10029 and 10035.
East Harlem | Include East Harlem in the new Partners in Preservation initiative to develop a comprehensive anti-displacement strategy for the neighborhood | 7 | Housing | HPD | In Progress | HPD will launch its new Partners in Preservation pilot program in East Harlem (Manhattan CD 11) in the summer of 2019. Through the program, HPD seeks to proactively prevent tenant harassment by jointly developing anti-displacement strategies with tenant organizing groups, legal service providers, and other government agencies. With funding from the New York City Housing Development Corporation and Enterprise Community Partners, tenant organizers will target at-risk buildings for strategic, tenant-led interventions and create a neighborhood-wide anti-displacement plan. Community Voices Heard will receive $490,000 to implement the program in collaboration with Tenants & Neighbors and Picture the Homeless, as well as other community-based organizations and legal service providers. The pilot program will run for 18 months. | HPD will include East Harlem in its new Partners in Preservation initiative. Representing our most aggressive and targeted efforts to date, Partners in Preservation will pair HPD's available data with the on-the-ground experience and work of community-based organizations to advance comprehensive anti-displacement plans in neighborhoods identified as most at risk of losing affordability. Strategies are expected to combine new and existing tools to address harassment and disrepair; provide tenants with anti-eviction legal services; protect homeowners from foreclosure and predatory activities; and help building owners access HPD financial resources to improve their buildings and preserve affordability. | 2018-2019 |  | HPD plans to launch the new “Partners in Preservation" initiative in East Harlem in the spring of 2019. In preparation for the launch, HPD staff have been meeting with community-based organizations, legal service providers, and other stakeholders in East Harlem to inform them of how the agency intends to implement this new initiative, gain feedback, and learn about which strategies these stakeholders have found to be most effective to protect tenants from displacement. The agency has also begun developing a data analysis methodology to identify buildings where tenants are at risk of being harassed by their landlords, in order to pursue more targeted interventions. Moreover, HPD is in the process of hiring additional staff who will be dedicated to this new initiative. By the fall of 2018, HPD will issue a Request for Proposals to select community-based organizations that will receive funding to increase their tenant organizing capacity and help implement the Partners in Preservation initiative.
East Harlem | Pilot a Landlord Ambassadors Program to provide technical assistance to East Harlem property owners | 8 | Housing | HPD | In Progress | Since June 2017, HPD has partnered with Enterprise Community Partners and community-based organizations to pilot a two year demonstration program called the Landlord Ambassadors Program. Organizations have been conducting outreach and providing technical assistance to owners of multifamily buildings in specific communities throughout the city, including East Harlem. Since the pilot began, 77 property owners have participated, 39 have applied for HPD financing, and seven have closed on construction financing. With the Ambassadors help, active properties have decreased their violations by 42% and reduced municipal arrears by 21%. HPD has recently secured some funding to continue the pilot and expand it citywide, including in the Southwest Bronx. The Mutual Housing Association of New York (MHANY), a pilot program Ambassador, and Habitat for Humanity have recently requested City Council Discretionary funding to expand their services citywide, increase the number of property owners assisted, and expand the scope of services for new and currently participating owners. MHANY will continue working with local property owners to provide information about the benefits of using HPD financing programs; navigate HPD program requirements, including regulatory requirements; and package application materials for HPD review and approval. | In addition to strategic outreach to owners, the local community identified a need for more sustained technical assistance for mission-driven, faith-based, and small- to mid-sized property owners who are interested in, but unfamiliar with, the process of securing a loan to undertake building improvements. HPD is partnering with Enterprise Community Partners to pilot a Landlord Ambassadors Program to contract with community-based organizations who will conduct outreach and provide technical assistance to owners of multifamily buildings in targeted areas across the city. The Mutual Housing Association of New York (MHANY) has been designated as the Landlord Ambassador for Upper Manhattan, inclusive of East Harlem. MHANY will work with local property owners to: Provide information about the benefits of using HPD financing programs. Navigate HPD program requirements, including regulatory requirements, and package application materials for HPD review and approval. Access local resources and vendors needed in order to close, construct, and operate their properties, including contractors, property managers, attorneys, and other professionals. | 2017-2018 |  | HPD is partnering with Enterprise Community Partners to pilot a Landlord Ambassadors Program in partnership with community-based organizations who will conduct outreach and provide technical assistance to owners of multifamily buildings in East Harlem. The Mutual Housing Association of New York (MHANY) has been designated as the Landlord Ambassador for Upper Manhattan, which includes East Harlem. MHANY has begun working with local property owners to provide information about the benefits of using HPD financing programs; navigate HPD program requirements, including regulatory requirements; and package application materials for HPD review and approval. To date, they have worked with nearly 20 buildings in Upper Manhattan.
East Harlem | Support mission-driven groups interested in developing affordable housing on underutilized sites | 9 | Housing | HPD | In Progress | HPD continues to steer mission-driven groups to the Pre-Qualified List of Owner's Representatives and NYC Acquisition Fund to support their affordable housing initiatives. Since the launch of Housing New York, HPD has financed 17 projects, comprising more than 2,500 affordable homes, with faith-based organizations as development partners; more than 30 additional projects are in various stages of discussion. HPD’s collaboration with LISC on the New York Land Opportunity Program (NYLOP) has resulted in three of four participating churches signing agreements to form joint ventures with affordable housing developers. As part of Housing New York 2.0, HPD is launching the Neighborhood Pillars program to provide funding for non-profits to purchase privately-owned buildings and keep or make them affordable. Additionally, 55% of our public site designations have gone to non-profits, either as sole developers (15) or joint ventures with for-profits (28). | The community expressed a desire to see more participation by mission-driven organizations, including faith-based groups, in affordable housing development and preservation. To assist those interested in affordable housing, a number of resources are available, including the Pre-Qualified List of Owner's Representatives and the New York City Acquisition Fund. HPD also recently introduced new policy reforms for its RFPs, including a new preference for community development plans and experience and the recognition of development experience in affordable housing preservation. | 2017-ongoing |  | HPD continues to steer mission-driven groups to the Pre-Qualified List of Owner's Representatives and NYC Acquisition Fund for the furtherance of their affordable housing initiatives. Since the launch of Housing New York, HPD has financed the creation of 689 units of affordable housing over 7 projects with faith-based organizations as development partners, with 11 more expected to close in Fiscal Years 2018 and 2019, comprising approximately 1,900 additional units. HPD also worked closely with LISC on the New York Land Opportunity Program (NYLOP), holding multiple affordable housing workshops for mission-based organizations citywide and providing technical assistance to 5 mission-based organizations, four of whom have issued RFP for development of their land for affordable housing. As part of Housing New York 2.0, HPD launched the Neighborhood Pillars program to provide funding for non-profits to purchase privately-owned buildings and keep or make them affordable. Additionally, we designated 30 projects where non-profit developers are either sole developers (11) or part of a joint venture (19). For example, nonprofits received 68% of awards in the Neighborhood Infill Housing Opportunity Program (NIHOP), including 6 sites in East Harlem that will be developed into four rental buildings totaling 75 apartments by a development team led by Ascendant Neighborhood Development Corp and MDG Design and Construction, LLC. Finally, HPD partners with JOE NYC, a nonprofit collaborative that uses HPD financing to acquire and asset manage affordable multifamily properties on behalf of member nonprofits.
East Harlem | Make it easier for residents to understand, prepare for, and complete the affordable housing application process | 10 | Housing | HPD | Done with ongoing work | HPD recognizes that the affordable housing application process can be time-consuming, and it continues to take steps to help residents become better prepared to submit complete and accurate applications. In addition to revamping its affordable housing application and lottery education materials, HPD has been recruiting and training Housing Ambassadors in East Harlem, which are local community groups that provide free technical assistance to residents who wish to apply for affordable housing. Current East Harlem Housing Ambassadors are 116th St. Block Association, East Harlem Council for Community Improvement, and Hope Community. | HPD recognizes that the affordable housing application process can be time-consuming, and it continues to take steps to help residents become better prepared to submit complete and accurate applications. In addition to revamping its affordable housing application and lottery education materials, HPD has been recruiting and training Housing Ambassadors in East Harlem, which are local community groups that provide free technical assistance to residents who wish to apply for affordable housing. | 2017-ongoing |  | HPD recognizes that the affordable housing application process can be time-consuming, and it continues to take steps to help residents become better prepared to submit complete and accurate applications. In addition to revamping its affordable housing application and lottery education materials, HPD has been recruiting and training Housing Ambassadors in East Harlem, which are local community groups that provide free technical assistance to residents who wish to apply for affordable housing. Current East Harlem Housing Ambassadors are 116th St. Block Association, East Harlem Council for Community Improvement, and Hope Community, Inc.
East Harlem | Keep homes affordable by continuing to offer loans and tax incentives to building owners | 11 | Housing | HPD | Done with ongoing work | HPD continues to monitor homes with affordability restrictions in its portfolio and use its various financing programs to preserve and invest in the neighborhood's existing affordable housing stock. This is coupled with proactive outreach work to get new owners into affordability programs. Since 2014, HPD has financed the rehabilitation and continued affordability of 6,099 homes in East Harlem. This includes nearly 3,000 homes that were preserved since the rezoning was adopted in November 2017. | Since 2014, HPD has financed the preservation of 3,387 affordable homes in East Harlem, representing about 8% of all homes preserved across the city. HPD will continue monitoring East Harlem homes with affordability restrictions in its portfolio, and use its various financing programs to preserve and invest in the neighborhood's existing affordable housing stock | 2017–ongoing |  | HPD will continues to monitor East Harlem homes with affordability restrictions in its portfolio, and use its various financing programs to preserve and invest in the neighborhood's existing affordable housing stock. This is coupled with proactive outreach work to get new owners into affordability programs. Since 2014, HPD has financed the rehabilitation and continued affordability of 3,621 homes in East Harlem.
East Harlem | Fund and support the East Harlem/El Barrio Community Land Trust | 12 | Housing | HPD | In Progress | On June 13, 2019, the City Council approved the disposition of four City-owned residential buildings to be the first properties of the East Harlem/El Barrio Community Land Trust (EHEBCLT). The properties will now undergo a substantial rehabilitation. HPD continues to work with EHEBCLT and developer Banana Kelly CIA to advance the rehabilitation and long-term stewardship of these buildings. HPD expects rehabilitation to begin in 2019. In parallel with advancing rehabilitation of these buildings, the EHEBCLT continues to use grant funding from Enterprise Community Partners and HPD to prepare the organization to manage the properties upon project completion, as well as support construction costs. | A Community Land Trust (CLT) is a non-profit organization that maintains control and oversight of affordable housing through ownership of land, and whose primary purpose is the creation and/or maintenance of permanently affordable housing. The CLT's land ownership, paired with a governance structure that reflects the interests of residents and the broader neighborhood, can offer a unique housing model that empowers communities. To support CLTs across the city, HPD issued a Request for Expressions of Interest (RFEI) early in 2017 to identify qualified groups interested in forming CLTs. In addition, HPD recently announced an award of $500,000 from Enterprise Community Partners to Banana Kelly to support the efforts of the East Harlem El Barrio Community Land Trust. Over the next 24 months, the grant will fund operations and start-up support and is expected to be integrated into the budget of its first rehabilitation project of three buildings in East Harlem. HPD will continue exploring additional opportunities to partner with CLTs in Upper Manhattan. | 2019 |  | HPD continues to work with the East Harlem El Barrio Community Land Trust (EHEBCLT) and developer Banana Kelly CIA to advance the rehabilitation of a cluster of four City-owned buildings in East Harlem. The properties will undergo a substantial rehabilitation prior to becoming part of a Community Land Trust. HPD has been working with the development team to support the achievement of predevelopment milestones prior to construction commencement. These milestones include coordinating tenant kickoff meetings and communication, developing scopes of work, creating a development budget, forming legal documents and ensuring environmental testing is done. EHEBCLT recently hired a coordinator using funds that were awarded by HPD from Enterprise Community Partners. HPD continues to work with the team on predevelopment with the goal of closing on financing and substantially rehabilitating the four properties.
East Harlem | Fund and implement Universal Access to Counsel | 13 | Housing | HRA | In Progress | As part of its commitment to provide universal access to counsel for tenants facing eviction in Housing Court, by Fiscal 2022 the City will dedicate $166 million citywide to ensure that low-income residents who have incomes of roughly $50,000 for a family of four will have access to free legal representation. Residents who earn more than that will have access to free and individualized legal counseling. | In February 2017, the Mayor announced that the City will fund universal access to legal services for tenants facing eviction in Housing Court. Through a five-year implementation plan, free legal representation will be available to all tenants with household incomes at or below 200% of the federal poverty line, or roughly $50,000 for a four-person family. Legal counseling will be available to those earning more. | 2017-2021 |  | As part of its commitment to provide universal access to counsel for tenants facing eviction in Housing Court, by Fiscal 2022 the City will dedicate $155 million to ensure that low-income New Yorkers, including East Harlem residents, who have incomes of roughly $50,000 for a family of four, have access to free legal representation. Residents who earn more will have access to free and individualized legal counseling.
East Harlem | Explore opportunities to finance the development of affordable artist housing | 14 | Housing | HPD | In Progress | HPD will seek to fulfill the goal of financing artist live-work space through a combination of new construction and adaptive reuse of existing buildings on both public and private sites. The City will aim to co-locate affordable live/work housing and publicly accessible community arts space. An inter-agency collaboration, comprised of DCLA, EDC, HPD, and the Mayor’s Office, is leading the implementation of the Affordable Real Estate for Artists (AREA) initiative to identify potential sites citywide, backed by $30 million from the Department of Cultural Affairs’ (DCLA) capital budget for the workspace component. In March 2019, HPD and DCLA hosted a roundtable with a diverse set of artists, arts organizations, architects, and developers to discuss design guidelines and considerations for the development of mixed-use live-work housing for the AREA initiative. | As part of Housing New York, the City committed to building 1,500 affordable apartments for artists. Consistent with goals of the community, HPD will review proposals from private and mission-driven developers seeking to build or preserve artist housing, live/work spaces, or traditional affordable housing integrated with studio and performance spaces in East Harlem. The City will also explore artist housing on future public sites if desired by the community. | 2017-ongoing |  | HPD will seek to fulfill the goal of financing 1,500 units of artists housing through a combination of new construction and adaptive reuse of existing buildings on both public and private sites. Where possible, and if desired by the community, the City will aim to co-locate housing for artists with community facility space for cultural organizations. An inter-agency collaboration, comprised of DCLA, EDC, HPD, and the Mayor’s Office, is leading the implementation of the Affordable Real Estate for Artists Task Force to identify potential sites citywide, backed by $30 million from the Department of Cultural Affairs’ (DCLA) capital budget.
East Harlem | Expand local hiring incentives in HPD-financed developments | 15 | Housing | HPD | Done with ongoing work | In all HPD RFPs for the development of City-owned property, respondents must demonstrate a plan for outreach to residents of the local community district related to employment opportunities generated by the proposed project. This requirement will apply to upcoming RFPs for the East Harlem Multi-Service Center and the NYPD 25th Precinct Parking Lot. | In all HPD RFPs for the development of City-owned property, respondents must demonstrate a plan for outreach to residents of the local community district related to employment opportunities generated by the proposed project. Applicants will be required to comply with their outreach plans and report regularly on outreach activities. | 2017-ongoing |  | In all HPD RFPs for the development of City-owned property, respondents must demonstrate a plan for outreach to residents of the local community district related to employment opportunities generated by the proposed project.
East Harlem | Educate tenants about their rights and resources to prevent displacement | 16 | Housing | HPD | Done with ongoing work | HPD is committed to working with partner agencies, elected officials, and community groups to ensure tenants are aware of their rights and have access to important housing resources. HPD's Neighborhood Education and Outreach Unit will be partnering with Council Member Diana Ayala to host a Tenant Resource Fair in East Harlem on July 17. In East Harlem, HPD contracts with the Urban Homestead Assistance Board (UHAB) to conduct outreach and educational initiatives for tenants, including coordinating tenant meetings and conducting surveys to assess physical conditions in apartments. HPD also administers City Council-funded contracts with Strycker’s Bay Neighborhood Council and New York State Tenants and Neighbors, both of whom work directly with East Harlem tenants to educate them about their rights and prevent displacement. | HPD is committed to working with partner agencies, elected officials, and community groups to ensure tenants are aware of their rights and have access to important housing resources. HPD's Neighborhood Education and Outreach Unit hosts tenant fairs and coordinates HPD and other agency participation in community events. In addition, through its discretionary awards and Neighborhood Preservation Consultant contracts, the City Council and HPD support community-based organizations that promote and provide tenant resources. | 2017-ongoing |  | HPD is committed to working with partner agencies, elected officials, and community groups to ensure tenants are aware of their rights and have access to important housing resources. In East Harlem, HPD contracts with the Urban Homestead Assistance Board (UHAB) to engage with tenants through various outreach and organizing methods such as coordinating tenant meetings and conducting surveys to assess apartment physical conditions. HPD additionally administers City Council-funded contracts with Strycker’s Bay Neighborhood Council and New York State Tenants and Neighbors, both of whom work directly with East Harlem tenants to educate them about their rights and prevent displacement.
East Harlem | Continue to work with the Tenant Harassment Prevention Task Force to investigate and take action against landlords who harass tenants | 17 | Housing | HPD | Done with ongoing work | HPD participates on the Tenant Harassment Prevention Task Force, in partnership with the New York State Attorney General's office, New York State Department of Housing and Community Renewal, and other City agencies. To date, charges have been brought against two negligent landlords in the neighborhood. Additionally, HPD participates on the City Agency Task Force on Tenant Harassment with City and State agencies. Since launching in 2014 and as of March 2019, the City Agency Task Force has inspected 690 building with nearly 12,000 homes, issued nearly 30,000 hazardous or immediately hazardous violations, and had either HPD- or tenant-initiated Housing Court cases against 115 buildings. | The Administration helped to create an interagency, multi-jurisdictional Tenant Harassment Prevention Task Force to investigate and bring enforcement actions - including criminal charges - against landlords who are found to be harassing tenants to force them to vacate rent-regulated apartments. HPD will continue to work with the Tenant Harassment Prevention Task Force to take action against landlords in East Harlem who are harassing tenants. | 2017-ongoing |  | HPD participates on the Tenant Harassment Task Force, in partnership with the New York State Attorney General's office, New York State Department of Housing and Community Renewal, and other City agencies. To date, charges have been brought against two negligent landlords in the neighborhood. Additionally, HPD participates on the City Agency Task Force on Tenant Harassment with City and State agencies. Since launching in 2014, the Task Force has inspected nearly 10,000 homes, issued nearly 20,000 hazardous or immediately hazardous violations, and initiated Housing Court cases against 90 buildings.
East Harlem | Continue promoting programs that help owners make repairs and preserve affordability | 18 | Housing | HPD | Done with ongoing work | HPD continues to take a proactive and strategic approach to engaging building owners who could benefit from financing and tax incentives in exchange for maintaining affordable rents for existing tenants. HPD contacts property owners by email, mail, phone, and at community events. These efforts are coupled with a new marketing campaign HPD launched in 2017 titled “Let’s Invest”. The new marketing materials were created with the feedback received from property owners. Additionally, HPD added a monthly Property Owner Clinic held at 100 Gold Street where property owners sign up to speak one on one with agency representatives to troubleshoot issues with their property. The clinics are open to all property owners throughout the City, and include representatives from HPD finance programs, HPD code enforcement, DOF, and DEP. Through these efforts, HPD has reached the owners of 2,630 properties in East Harlem representing over 49,000 apartments. | HPD is taking a proactive and strategic approach to engaging building owners who could benefit from financing and tax incentives in exchange for maintaining affordable rents for existing tenants. HPD will continue implementing its outreach strategy, targeting property owners in East Harlem through owner outreach events, mailings, e-mails, calls, and surveying distressed properties. | 2017-ongoing |  | HPD continues to take a proactive and strategic approach to engaging building owners who could benefit from financing and tax incentives in exchange for maintaining affordable rents for existing tenants. HPD contacts property owners by email, mail, phone, and at community events. These efforts are coupled with a new marketing campaign HPD launched in 2017 titled “Let’s Invest”. The new marketing materials were created with the feedback received from property owners. Additionally, HPD added a monthly Property Owner Clinic held at 100 Gold Street where property owners sign up to speak one on one with agency representatives to troubleshoot issues with their property. The clinics are open to all property owners throughout the City, and include representatives from HPD finance programs, HPD code enforcement, DOF, and DEP. Through these efforts, HPD has reached the owners of 2,625 properties in East Harlem representing over 48,000 apartments.
East Harlem | Continue to improve housing quality through rigorous enforcement of the Housing Maintenance Code | 19 | Housing | HPD | In Progress | HPD's Office of Enforcement & Neighborhood Services (OENS) responds to 311 calls, Housing Court requests, and building referrals by community groups and elected officials by sending inspectors to see if building conditions violate the City's Housing Maintenance Code. As part of HPD's focus on East Harlem, and in response to recommendations from the community, OENS prioritized "block sweeps" throughout the neighborhood. Through this initiative, HPD identified buildings and blocks with maintenance or other housing-related issues. HPD will continue monitoring the properties surveyed during this initiative and continue accepting building referrals from the community for additional surveying. In FY 2018, HPD conducted 8,825 inspections in East Harlem and issued 11,895 violations, a 62% increase in violations issued compared to FY 2015. | OENS responds to 311 calls, Housing Court requests, and building referrals by community groups and elected officials by sending inspectors to see if building conditions violate the City's Housing Maintenance Code. As part of HPD's focus on East Harlem, and in response to recommendations from the community, OENS prioritized "block sweeps" throughout the neighborhood. Through this initiative, HPD identified buildings and blocks with maintenance or other housing-related issues. HPD will continue monitoring the properties surveyed during this initiative, and will continue accepting building referrals from the community for additional surveying. | 2017-ongoing |  | HPD's Office of Enforcement & Neighborhood Services (OENS) responds to 311 calls, Housing Court requests, and building referrals by community groups and elected officials by sending inspectors to see if building conditions violate the City's Housing Maintenance Code. As part of HPD's focus on East Harlem, and in response to recommendations from the community, OENS prioritized "block sweeps" throughout the neighborhood. Through this initiative, HPD identified buildings and blocks with maintenance or other housing-related issues. HPD will continue monitoring the properties surveyed during this initiative, and will continue accepting building referrals from the community for additional surveying. In Fiscal 2017, HPD conducted 9,315 inspections in East Harlem and issued 10,756 violations, a 46% increase in violations issued compared to Fiscal 2015.
East Harlem | Continue to offer financing to incentivize the development of affordable housing that exceeds minimum MIH requirements | 20 | Housing | HPD | Done with ongoing work | Since 2014, HPD has financed the construction of 1,182 new affordable homes in East Harlem. Of these, approximately 35% are serving households earning extremely low and very low incomes. HPD has financed the creation of 328 affordable homes in the rezoning area since the rezoning was adopted. | HPD aims to affirmatively further fair housing and economic diversity by financing the development of housing that is affordable to families with a range of incomes and needs, from extremely low- to middle-income households, as well as seniors and those with special needs. HPD recently updated its financing terms to require that any MIH project receiving City subsidy must provide 15% more permanently affordable homes than required by the MIH program alone. | 2017-ongoing |  | HPD advances fair housing and economic diversity by financing the development of housing that is affordable to families with a range of incomes and needs, from extremely low- to middle-income households, as well as seniors and those with special needs. HPD recently updated its financing terms to require that any Mandatory Inclusionary Housing (MIH) project receiving City subsidy must provide 15% more permanently affordable homes than otherwise required under MIH. Since 2014, HPD has financed the construction of 860 new affordable homes in East Harlem. Of these, approximately 35% are serving households earning extremely low and very low incomes.
East Harlem | Develop DSNY 123rd Street Parking Lot | 21 | Housing | HPD | Not Started | DSNY occupies a large surface parking lot on the north side of 123rd Street between Lexington and 3rd Avenues. The site is currently used as vehicle storage, including for large DSNY salt and other utility trucks, and it is expected to host additional spillover vehicles from the new Potamkin garage. HPD has been working with DSNY to evaluate the feasibility of redeveloping this site with affordable housing and a new garage for DSNY vehicles. At this time, development on this site is not viable given the current lack of appropriate permanent relocation space for the DSNY vehicles and concerns regarding the compatibility of co-locating the sanitation garage with affordable housing. | The Department of Sanitation (DSNY) occupies a large surface parking lot on the north side of 123rd Street between Lexington and 3rd Avenues. The site is currently used as vehicle storage, including for large DSNY salt and other utility trucks, and it is expected to host additional spillover vehicles from the new Potamkin garage. The City will explore the feasibility of redeveloping this site with affordable housing and a new garage for DSNY vehicles in 2018. Any future RFP would need to be subsequent to a relocation site being identified and any related land use approvals completed. | TBD |  | DSNY occupies a large surface parking lot on the north side of 123rd Street between Lexington and 3rd Avenues. The site is currently used as vehicle storage, including for large DSNY salt and other utility trucks, and it is expected to host additional spillover vehicles from the new Potamkin garage. HPD is currently evaluating the feasibility of redeveloping this site with affordable housing and a new garage for DSNY vehicles.
East Harlem | Develop HRA East Harlem Multi-Service Center | 22 | Housing | HPD | In Progress | The NYC Human Resources Administration (HRA) East Harlem Multi-Service Center is located on East 120th Street between 1st and Pleasant Avenues. The project will include new affordable housing and new community/office space for as many of the current Multi-Service Center tenants as possible. Request for Proposals (RFP) respondents will be required to submit a relocation plan for the non-profit tenants that the City will analyze as part of its ongoing assessment of the future space needs for the tenants. HPD and HRA are continuing to work with the Councilmember and current tenants to more deeply understand their relocation needs and options. The City will also work with the selected development team to ensure minimal disruption to the services they provide. This Spring, in collaboration with DCP, Community Board 11, Office of Borough President Gale Brewer, and the Offices of Council Members Bill Perkins and Diana Ayala, HPD conducted two community visioning workshops and distributed an online and paper questionnaire to gather input on what residents hope to see on this site, which will be used to inform the development of the RFP. HPD is targeting summer 2019 for the release of an RFP. | The NYC Human Resources Administration (HRA) East Harlem Multi-Service Center is located on East 120th Street between 1st and Pleasant Avenues. The project will include affordable housing and may include new community/office space for Multi-Service Center tenants. RFP respondents must submit a tenant relocation plan, and the City will work with the selected developer to temporarily relocate existing non-profit tenants of the Multi-Service Center and possibly bring back select tenants to the new building. | 2018-2019 |  | HPD and HRA are working with the Councilmember and existing tenants of the Multi-Service Center to understand their current use of the building and their relocation needs. HPD is targeting the second quarter of 2019 for the release of an RFP for this site. In advance of releasing an RFP, HPD will conduct outreach with community residents and stakeholders to better understand their desired programming and design.
East Harlem | Develop NYPD 25th Precinct Parking Lot | 23 | Housing | HPD | In Progress | The New York Police Department (NYPD) 25th Precinct is located on 119th Street between Park and Lexington Avenues and includes a large surface parking lot fronting Park Avenue. HPD is coordinating with the NYPD to plan for the future of the 25th Precinct Parking Lot. The Precinct uses 75 parking spaces on a daily basis for emergency response, school safety, and other vehicles. The project will include affordable housing, a new parking garage for NYPD vehicles, and new retail or community facility space. This Spring, in collaboration with DCP, Community Board 11, Office of Borough President Gale Brewer, and Offices of Council Members Bill Perkins and Diana Ayala, HPD conducted two community visioning workshops and an online and paper questionnaire to gather input on what residents hope to see on this site, which will inform the development of the Request for Proposal. HPD is targeting summer 2019 for the release of an RFP for this site. | The New York Police Department (NYPD) 25th Precinct is located on 119th Street between Park and Lexington Avenues and includes a large surface parking lot fronting Park Avenue. The Precinct uses 75 parking spaces on a daily basis, including emergency response, school safety, and other vehicles. The project will include affordable housing and a new parking garage for NYPD vehicles. | 2018-2019 |  | HPD is coordinating with the NYPD to plan for the future of the 25th Precinct Parking Lot. The Precinct uses 75 parking spaces on a daily basis for emergency response, school safety, and other vehicles. The project will include affordable housing and a new parking garage for NYPD vehicles. HPD is targeting the second quarter of 2019 for the release of an RFP for this site. In advance of releasing an RFP, HPD will conduct outreach with community residents and stakeholders to better understand their desired programming and design.
East Harlem | Rebuild Urban Assembly School | 24 | Housing | HPD | Not Started | At this time, the redevelopment of the school located at 2005 Madison Avenue is not feasible. The DOE will continue to periodically evaluate the financial and operational feasibility of redeveloping this school. | The City will periodically evaluate the financial and operational feasibility of rebuilding the school at 2005 Madison Avenue to include a state of the art school building as well as affordable housing, taking into account the needs of the existing schools in the building (Urban Assembly School for Global Commerce & Promise Academy II Charter School) before, during and after any possible construction on the site. | TBD |  | At this time, the redevelopment of the school located at 2005 Madison Avenue is not feasible. The Department of Education will continue to periodically evaluate the financial and operational feasibility of redeveloping this school.
East Harlem | Build a comfort station in Harlem River Park | 25 | Open Space | DPR | In Progress | Responding to strong community desire for more comfort stations in parks throughout East Harlem, a comfort station will be constructed in Harlem River Park. In order to serve the heavily used ballfields, the comfort station will be sited near the upland portion of Harlem River Park, north of E128th Street and east of the Lexington/Third Avenue Bridge. DPR started design of the comfort station in January 2019. | Responding to strong community desire for more comfort stations in parks throughout East Harlem, a comfort station will be constructed in Harlem River Park. In order to serve the heavily used ballfields, the comfort station will be sited near the upland portion of Harlem River Park, north of E128th Street and east of the Lexington/Third Avenue Bridge. | 2019 |  | In response to strong community desire for more comfort stations in parks throughout East Harlem, the City has committed over four million dollars to construct a comfort station in Harlem River Park. DPR will build the comfort station near the upland portion of Harlem River Park, north of East 128th Street and east of the Lexington/Third Avenue Bridge, in order to serve the heavily used ball fields. Funding is in place and design will begin in 2019.
East Harlem | Build intergeneration playgrounds to accommodate seniors in local parks | 26 | Open Space | DPR | In Progress | DPR aims to serve multiple generations and users through the design of our active and passive park spaces using a variety of amenities for users of all ages. James Weldon Johnson Playground completed construction in February 2018. Playground 103 completed construction in June 2018. Pending successful procurement, construction is expected to begin at Abraham Lincoln Playground by the end of 2019. | Throughout the City open spaces are undergoing major renovations to offer intergenerational recreation to accommodate people of all ages in our local parks. DPR aims to serve multiple generations and users through the design of our active and passive park spaces, using a variety of amenities to invite users of all ages. Within East Harlem we have three such sites: James Weldon Johnson Playground and Playground 103, currently in construction, and Abraham Lincoln Playground, which will begin construction in late 2018. | 2017-ongoing |  | The City is transforming open spaces in East Harlem to offer recreational options that accommodate people of all ages, like children’s play areas, adult fitness equipment, and seating areas. The City committed $18.1 million dollars to renovate three local playgrounds, which were redesigned with the community and are in different stages of reconstruction. James Weldon Johnson Playground reopened in February 2018, while the reconstruction of Playground 103 will be completed in spring 2018. The design of Abraham Lincoln Playground was completed in March 2018.
East Harlem | Construct a new East 125th Street Plaza (Park Ave between 124th and 126th St | 27 | Open Space | DOT | In Progress | Work will begin this summer on the East 125th Street Plaza under the Park Avenue Viaduct. Following completion of all federal design reviews in 2019, EDC managed public contractor procurement and selected a contractor to build the new plaza and streetscape improvements. The Plaza will be closed during construction and is anticipated to be re-open by the end of 2020. The project team includes a Community Construction Liaison to answer any public concerns that arise relating to this project throughout its duration. Community inquiries during construction can be referred to the following project email address: EDCPark125CCL@gmail.com. | The new East 125th Street Plaza project will be constructed under the Park Ave Viaduct between E124th and E126th St and will contain a newly-constructed plaza area with amenities to expand the space's activation options. Expanded sidewalks surrounding the Metro-North station, improved crosswalks and street lighting, and traffic signal timing changes, will improve the pedestrian experience and calm traffic movements. The plaza project's sidewalk extensions also create the opportunity to provide taxi stands along Park Avenue along both sides of the plaza, which will allow for more efficient transfers between the train and taxis in all directions to and from the station. The project is currently in final design. The New Harlem East Merchants Association (NHEMA) - recently renamed Uptown Grand Central - applied to Round 7 of the Plaza Program in 2014 and is responsible for the maintenance of the plaza and leads on all community programming. NYCEDC is providing Capital planning and will oversee project implementation on DOT's behalf. | 2018 |  | Metro North Railroad is performing station improvements at Park Avenue that are scheduled to be completed at the end of 2018. NYCEDC, which is providing capital planning of the plaza and will oversee project implementation, has submitted designs for approval by the Federal Highway Administration and plans to begin work on the plaza project in early 2019. Uptown Grand Central (formerly the New Harlem East Merchants Association) is responsible for maintenance of the plaza and leads on all community programming.
East Harlem | Expand the Harlem River Greenway Link to connect 125th and 132nd St | 28 | Open Space | DPR | In Progress | This new seven-block waterfront park between East 125th and 132nd Streets will provide an exciting new amenity for East Harlem residents, and will close one of the last remaining gaps in the Manhattan Waterfront Greenway. Design is currently underway. DPR and EDC expect to have a public visioning session in fall 2019. | The waterfront between E125th and E132nd streets provides a rare opportunity to build a new 7 block long waterfront park. It will provide an exciting amenity for East Harlem residents and will complete one of the last remaining gaps in the Manhattan Waterfront Greenway; today, East Harlem is essentially cut off from the Manhattan Greenway. The bulkhead and waterfront platform will be repaired/replaced and a new park constructed on top. The community has joined The New York City Department of Parks and Recreation (DPR)to design the new park, which is anticipated to include bicycle and pedestrian paths, play and picnic areas, landscaping, and other recreational amenities. The City has already committed $18M to be used towards waterfront repair work between E125th-E132nd Streets, and is committing an additional $83M to be used towards further open space development between E125th and E132nd Streets. | 2019 |  | The waterfront between East 125th and 132nd Streets provides a rare opportunity to build a new 7 block waterfront park on one of the last remaining gaps in the Manhattan Waterfront Greenway. In 2017, the community joined DPR to develop a conceptual design for the new park. The City has committed $101 million to be used for waterfront repair work, bicycle and pedestrian paths, and landscaping between East 125th and 132nd Streets. The project will be led by EDC, which will release a Request for Proposals for design this summer and start design in early 2019.
East Harlem | Make improvements to the East River Esplanade from 96th through 125th Streets | 29 | Open Space | DPR | In Progress | As part of the City’s commitment to an accessible waterfront, the City allocated an additional $15 million for repairs of the East River Esplanade between East 96th and East 125th Streets. The City completed a re-inspection of the East River Esplanade. Design for the needed repairs is expected to begin in summer 2019. | A waterfront inspection of the East River Esplanade conducted in 2012/13 highlighted a need for structural repairs along the entire stretch of the esplanade, including various items identified between E96th and E125th streets. With funding from Mayor de Blasio and City Council Speaker Mark-Viverito, DPR is currently performing a portion of these repairs. The City plans to re-inspect the esplanade in 2018, which will result in updated cost estimates for reconstruction. As part of this POA and the City's commitment to an accessible waterfront, the City commits an additional $15M for repairs of the East River Esplanade between E96th and E125th Streets. The scope of work for this $15M will be determined once the updated inspection reports are received, but the funds will be earmarked specifically for the East River Esplanade between E96th and E125th Streets. | 2018 -2023 |  | The City committed $15 million dollars for repairs and/or improvements to the waterfront along the East River Esplanade between East 96th and 125th Streets. DPR is working with the EDC to re-inspect the waterfront infrastructure and create an updated scope of work for repairs to this vital waterfront area. The inspection is underway and should be complete by December 2018.
East Harlem | Renovations of La Marqueta | 30 | Open Space | EDC | In Progress | EDC in partnership with the Council Member and the Friends of La Marqueta (FoLM) released a market partner competitive procurement this April. Once selected, EDC will fund the new market partner. The current market partner's (ACACIA) contract was extended through June 2019. The Friends of La Marqueta and EDC established a joint Memorandum of Understanding to outline roles and responsibilities to help activate the market. La Placita is under construction and is set for completion this Summer. Redevelopment for La Marquetas other lots will begin design late-2019. Redevelopment for all lots is anticipated to take approximately 70 months, pending additional City Capital and MTA approvals. | La Marqueta is located along Park Avenue, between E111th Street and E119th Street underneath the Park Avenue viaduct. Since its inception in 1936, La Marqueta has steadfastly remained a landmark in East Harlem. The Speaker's Office and the New York City Economic Development Corporation (NYCEDC) have engaged in a feasibility study to develop goals and a framework for future investments at La Marqueta. This work led to a conceptual plan for Lots 1 through 8 that illustrates and reflects the goals and framework developed through the feasibility study. The next step will be to move from concept phase to design phase, which is anticipated to be in FY18, after which construction is anticipated to start in the winter of 2019. An overview of the organizational structure for La Marqueta is included as an exhibit to this POA. Moving forward, NYCEDC is open to exploring public-private partnerships to further activate the public market. | 2019 |  | La Marqueta is located along Park Avenue, between E111th Street and E119th Street underneath the Park Avenue viaduct. Since its inception in 1936, La Marqueta has steadfastly remained a landmark in East Harlem. The City Council and EDC have engaged in a feasibility study to develop goals and a framework for future investments at La Marqueta. This work led to a conceptual plan for Lots 1 through 8 that illustrates and reflects the goals and framework developed through the feasibility study. The next step will be to move from concept phase to design phase, which is anticipated to be in Fiscal Year 19, after which construction is anticipated to start in Spring of 2020. Capital improvement work began in June, 2018 at Lot 5-La Placita, with an expected completion date is December, 2018. ACACIA and Council Member Ayala are working on the formation of FolaM (Friends of La Marqueta, an independent community non-profit). While their deadline was set for May 21, 2018, EDC granted two extra months for the formation of the non-profit. Once FolaM is formed, EDC will start the RFP process for public-private partnership with an organization to further activate La Marqueta.
East Harlem | Create three Community Schools | 31 | Community Resources | DOE | Done | DOE created three new Community Schools in East Harlem starting in the 2017-2018 School Year: PS 83 Luis Munoz Rivera (City Year), PS 108 Assemblyman Angelo Del Toro Educational Campus (The Leadership Program), and Esperanza Preparatory Academy School (Union Settlement). These schools are funded for five years, bringing the total number of Community Schools in East Harlem to eight. Pursuant to available funding, the DOE will explore future opportunities to create additional Community Schools in East Harlem and citywide. | For the 2017-18 school year, the City created three new Community Schools in East Harlem: PS 83 Luis Munoz Rivera (City Year), PS 108 Assemblyman Angelo Del Toro Educational Complex (The Leadership Program), and Esperanza Preparatory Academy School (Union Settlement). The three new Community Schools, which are funded for five years, bring the total number of Community Schools in East Harlem to eight. Community Schools are neighborhood hubs where students receive high-quality academic instruction, families can access social services, and communities congregate to share resources and address common challenges. Each school has a Lead Community-Based Organization (CBO) partner that coordinates and delivers comprehensive services through a Community School Director (CSD), who is a CBO employee. In addition, the Office of Community Schools (OCS) provides support and partners with other DOE departments, city agencies, and philanthropic partners, allowing schools to efficiently access resources. Pursuant to available funding, the DOE will explore future opportunities to create additional Community Schools in East Harlem and citywide. |  |  | DOE created three new Community Schools in East Harlem starting in the 2017-2018 School Year: PS 83 Luis Munoz Rivera (City Year), PS 108 Assemblyman Angelo Del Toro Educational Campus (The Leadership Program), and Esperanza Preparatory Academy School (Union Settlement). These schools are funded for five years, bringing the total number of Community Schools in East Harlem to eight. Community Schools provide students high-quality academic instruction, and access to social services through community-based organizations, and communities share resources coordinated through a Community Schools Director. Pursuant to available funding, the DOE will explore future opportunities to create additional Community Schools in East Harlem and citywide.
East Harlem | Create DOHMH East Harlem Neighborhood Health Action Center | 32 | Community Resources | DOHMH | Done | The East Harlem Neighborhood Health Action Center was implemented to address long-running inequities in health outcomes for residents of East Harlem. The Center opened in April 2017 and during the first year received over 16,000 visits. The Center provides co-located health and social services, including SNAP and Health Insurance enrollment, HIV/AIDS programs, nutrition education classes, urban gardening and physical activity programs, and mental health services for children and families. | The East Harlem Neighborhood Health Action Center provides co-located health and social services, including SNAP and Health Insurance enrollment, HIV/AIDS programs, nutrition education and cooking classes, urban gardening and physical activity programs, mental health services for children and families, as well as a Federally Qualified Health Center (FQHC) and a community kitchen. The centers are located at 158 East 115th St. and 161 East 110th St. | 2017 |  | The East Harlem Neighborhood Health Action Center was implemented to address long-running inequities in health outcomes for residents of East Harlem. The Center provides co-located health and social services, including SNAP and Health Insurance enrollment, HIV/AIDS programs, nutrition education classes, urban gardening and physical activity programs, and mental health services for children and families. In particular, it has focused on Asthma, diabetes, and other chronic disease management. In 2017, the Center received over 16,000 visits.
East Harlem | Explore locations for a new Evacuation Center for East Harlem residents | 33 | Community Resources | NYCEM | Done | IS 88 located at 215 West 114th Street is now an accessible Evacuation Center. While there are no evacuation centers directly in the East Harlem neighborhood, in addition to the completion of IS 88, there are additional accessible evacuation centers at PS 92 located at 222 West 134th Street (alternately PS 153 1750 Amsterdam Avenue while PS 92 is under construction until the start of the 2019 school year) and the Midtown East Campus PS 59 Beekman Hill International located at 233 East 56th Street. All mentioned evacuation centers are available for East Harlem residents. Additionally, NYCEM will continue to provide Homebound Evacuation Operation (HEO) to coordinate evacuation assistance for homebound individuals in East Harlem and throughout the city. | NYCEM has recently conducted surveys of potential evacuation centers for East Harlem, and identified IS 88 at 215 West 114th Street as a potential location. NYCEM and its partner agencies will continue to canvass and identify appropriate locations in areas outside of evacuation zones but close to the East Harlem neighborhood. In particular, they will survey nearby schools that are accessible (or could practically be made accessible if renovations are deemed viable) and outside of the evacuation zones. IS 88 is undergoing renovations to become accessible and the work is expected to be complete for the 2019 hurricane season, at which point OEM will determine if the school is a viable option to serve as an evacuation center. In addition, NYCEM will continue to provide Homebound Evacuation Operation (HEO) to coordinate evacuation assistance for homebound individuals in East Harlem and throughout the city. | 2017-ongoing |  | NYCEM is continuing to review the viability of naming IS 88 an Evacuation Center in spring 2019, in advance of hurricane season. IS 88 is undergoing renovations to become accessible and the work is expected to be complete for the 2019 hurricane season, at which point OEM will determine if the school is a viable option to serve as an evacuation center. In addition, NYCEM will continue to provide Homebound Evacuation Operation (HEO) to coordinate evacuation assistance for homebound individuals in East Harlem and throughout the city.
East Harlem | Designate historic and culturally significant buildings as landmarks | 34 | Community Resources | LPC | Done | In March 2018 LPC designated as individual landmarks the Richard Webber Harlem Packing House (designation report: http://s-media.nyc.gov/agencies/lpc/lp/2595.pdf), Public School 109/now El Barrio’s Artspace PS109 (designation report: http://s-media.nyc.gov/agencies/lpc/lp/2597.pdf), and the Benjamin Franklin High School/ now the Manhattan Center for Science and Mathematics (designation report: http://s-media.nyc.gov/agencies/lpc/lp/2596.pdf). The First Spanish Methodist Church was calendared for future consideration as landmark on December 12, 2017. These buildings embody East Harlem’s unique development history and recognize the civic institutions and businesses that helped shape the lives of the neighborhood’s immigrant groups. | The Landmarks Preservation Commission calendared the three below properties for future consideration as landmarks (the first step in the designation process). They are: Public School 109, 215 East 99th Street (Property 1) o The former Public School 109 was constructed in 1899 and transformed in 2015 into an affordable housing complex for local artists, and is architecturally and culturally significant as a Progressive-era elementary school designed by the Superintendent of School Buildings Charles B. J. Snyder. The architecture of P.S. 109 embodies the goals of urban educational and social reform at the turn of the twentieth century. Benjamin Franklin High School, 260 Pleasant Avenue (Property 2) o Benjamin Franklin High School, now the Manhattan School for Science and Math, is a Colonial Revival school from 1942 that was built to house East Harlem's first high school. This school featured an experimental curriculum referred to as "citizen-centered community education" that was implemented and developed by the pioneering educator, sociologist, and East Harlem resident Leonard Covello, to serve the diverse immigrant community of East Harlem. The Richard Webber Harlem Packing House, 207-215 East 119th Street (Property 3) o The former Richard Webber Harlem Packing House is a historic meat market building in East Harlem, constructed in 1895 and originally part of a larger commercial slaughterhouse, meat packing and retail complex. Prominent butcher Richard Webber commissioned the architectural firm of Bartholomew & John P. Walther in 1895, to design a Romanesque Revival style building to house his operations in Harlem. Additionally, the Landmarks Preservation Commission is expediting a detailed and comprehensive look at the First Spanish United Methodist Church (163 E111th Street) for landmark consideration due to its role in the history of the Young Lords in New York City, and will be considered by the Commission for calendaring on December 12, 2017. | 2018 |  | In March 2018 LPC designated as individual landmarks the Richard Webber Harlem Packing House (designation report: http://s-media.nyc.gov/agencies/lpc/lp/2595.pdf), Public School 109/now El Barrio’s Artspace PS109 (designation report: http://s-media.nyc.gov/agencies/lpc/lp/2597.pdf), and the Benjamin Franklin High School/ now the Manhattan Center for Science and Mathematics (designation report: http://s-media.nyc.gov/agencies/lpc/lp/2596.pdf). The First Spanish Methodist Church was calendared for future consideration as landmark on December 12, 2017. These buildings embody East Harlem’s unique development history and recognize the civic institutions and businesses that helped shape the lives of the neighborhood’s immigrant groups.
East Harlem | Conduct outreach and identify new OOPP providers in East Harlem | 35 | Community Resources | DOHMH | Done with ongoing work | In 2017, there were 21 OOPP's working in East Harlem. Currently, there are 22 OOPPs with a total of 46 registered sites in UHF 303 (zipcodes 10029 and 10034) where community members can receive overdose prevention training and naloxone. Community members who would like to go to these sites to get a kit should call in advance to ensure availability. | In response to requests for more Opioid Overdose Prevention Providers (OOPP's) to train East Harlem residents to administer naloxone, DOHMH has alerted community leaders to the 21 OOPP's currently working in East Harlem. Community members who would like to go to these sites to get a kit should call in advance to ensure availability. DOHMH is committed to helping additional interested organizations become OOPPs. | 2017 |  | In response to requests for more Opioid Overdose Prevention Providers (OOPP’s) to train East Harlem residents to administer naloxone, DOHMH has alerted community leaders to the 21 OOPP’s currently working in East Harlem. Community members who would like to obtain a kit from one of these sites should call in advance to ensure availability. DOHMH is committed to helping additional interested organizations become OOPPs, and four additional OOPPs with sites in the area have recently registered, bringing the total number of East Harlem sites where community members can receive overdose prevention training and naloxone to 25.
East Harlem | Fund targeted local marketing for the NYC Well program | 36 | Community Resources | DOHMH | Done | A new NYC Well campaign "We're Here" launched in May 2018 and ran through this year. It was targeted to Mandarin, Cantonese and Spanish speakers, and included additional placements in East Harlem. Campaign placements included all major platforms, including TV, print, newspaper, digital, ferry, subways, bus shelters, billboards, and neighborhood placement (laundromats, check cashing facilities, bodegas, nail salons). | DOHMH has developed an ad campaign promoting NYC Well, planned for rollout in Winter 2018. Ad placements are planned for East Harlem, and will include bus shelters, nail salons, barber shops, and LinkNYC kiosks. | 2018 |  | A new NYC Well campaign launched in May, targeted to Mandarin, Cantonese and Spanish speakers. It includes additional placements in East Harlem. Placements of advertisements include all major platforms, such as TV, print, newspaper, digital, ferry, subways, bus shelters, and more.
East Harlem | Expand mental health first aid training, with a focus on youth | 37 | Community Resources | DOHMH | Done | DOHMH launched a MHFA public awareness campaign in January 2018. The City is now able to offer MHFA training to people 17 years and older. DOHMH ran a "Choose Your Best Words" campaign from 1/22-/18-4/1/18. The campaign promoted Mental Health First Aid training, and included placements in various medium in East Harlem (newspapers, laundromats, check cashing facilities, bodegas, nail salons). DOHMH also worked with DOE to advertise youth MHFA. | Mental Health First Aid (MHFA) training is for individuals ages 18 and older. The Youth MHFA training, offered citywide, is designed to teach adults how to address the needs of adolescents (ages 12-18). DOHMH has recently received clearance from the National Council for Behavioral Health (the owners of the curriculum) to extend MHFA training to 17 year olds as long as they are high school seniors. DOHMH will be meeting with DOE to roll this out to high school seniors in the coming school year and will seek to target schools in East Harlem. In addition, DOHMH will be launching a MHFA public awareness campaign in mid-December, and will include targeted marketing to East Harlem. DOHMH will continue to make MHFA trainings available to all interested community partners. | 2017-2018 |  | The City has now expanded its Mental Health First Aid (MHFA) training to High School seniors who are 17 years of age. DOHMH launched a city-wide MHFA public awareness campaign in the winter, including targeted marketing in East Harlem. In Summer 2018, DOHMH will work with DOE to place advertisements in East Harlem schools.
East Harlem | Locate additional benches in areas that provide respite for seniors | 38 | Community Resources | DOT | In Progress | There are currently 61 CityBenches installed in Manhattan Community District 11. DOT has committed to installing up to 25 CityBenches based on community stakeholder requests. DOT has been coordinating with Community Board 11 to determine the best locations for the CityBenches. For details on CityBench siting requirements, refer to the CityBench website at http://www.nyc.gov/html/dot/html/pedestrians/citybench.shtml. | The CityBench program is an initiative to increase the amount of public seating on New York City's streets. DOT installs attractive and durable benches around the city, particularly at bus stops, retail corridors, and in areas with high concentrations of senior citizens. These benches make streets more comfortable for transit riders and pedestrians, especially for those who are older and disabled. To date DOT has installed 57 benches within Manhattan Community District 11. In response to additional interest from the community, DOT will work Council Members Diana Ayala and Bill Perkins to engage the following community stakeholders to identify appropriate locations for benches through the CityBench program. 1. Manhattan North District Council of Presidents to focus on areas around NYCHA developments 2. East Harlem Community Alliance to focus on commercial and crosstown corridors 3. Health Action Center (Dept. of Health and Mental Hygiene) to focus on areas around NORCs/Franklin Plaza and East Harlem Walking Trail | 2018 |  | There are currently 61 CityBenches installed in Manhattan Community District 11. DOT has committed to installing up to 25 CityBenches based on community stakeholder requests. DOT has been coordinating with Community Board 11 to determine the best locations for the CityBenches. For details on CityBench siting requirements, refer to the CityBench website at http://www.nyc.gov/html/dot/html/pedestrians/citybench.shtml.
East Harlem | Install air conditioners in all East Harlem schools | 39 | Community Resources | DOE | In Progress | As of January 2019, 85% of classrooms in East Harlem have functional air conditioning (AC). There is currently capital construction work underway related to AC capacity at PS 108 in East Harlem. Five school buildings in East Harlem are in the process of capital scoping, design, or construction work and seven buildings are scheduled for scoping and/or replacement installations to be completed in Fiscal Year 2020. | As part of the 2018 Fiscal Year Budget, the City has committed to ensuring every classroom in East Harlem and across the City has air conditioning by 2022. The City has dedicated $28.75 million over the next five years to purchase and install air conditioning units and, where needed, the SCA's five year Capital Plan includes funding for electrical upgrades to support the installation of those units, providing thousands of students with a more comfortable learning environment. DOE is currently in the planning stages of this initiative. | 2022 |  | As part of New York City’s commitment to ensuring every classroom has air conditioning by 2022, the City will install air conditioning in East Harlem schools so that students can learn in a safe and comfortable environment. DOE allocated approximately $28.75 million over the next five years to purchase and install air conditioning units, where needed. The School Construction Authority's (SCA) Five Year Capital Plan includes funding for electrical upgrades to support installation of the units. This initiative is currently in the planning stages.
East Harlem | Roll out 3K program across East Harlem | 40 | Community Resources | DOE | In Progress | As of fall 2019, 3-K will be offered in School Districts 4 and 5, which include East Harlem. 3-K will be universal in these districts in the 2020-21 school year. | 3-K for All programs will provide free, full-day, high-quality early education for three year olds, starting in fall 2017 in District 7 and 23. As a citywide initiative, our goal is to bring 3-K to all school districts citywide, to make it a universal program. Starting in fall 2018, the DOE will expand its 3-K portfolio to include new programs in 2 additional school districts, District 4 and District 27, and each year thereafter until 2020, for a total of 8 districts. We are working closely with the Superintendents and district school principals, as well as community based organization leaders, in School District 4 on implementation. The expansion of seats for 3-year olds in these districts will continue over two years. | 2018 |  | As part of DOE's goal to bring 3-K—free, full-day, high-quality early education for three-year-olds—to all school districts citywide, DOE began serving children in Districts 7 and 23 in Fall 2017. Starting in Fall 2018, DOE will expand 3-K to programs in District 4—which includes East Harlem—5, 16, and 27, and additional districts will be added through 2020 to include a total of 12 districts. DOE continues to work closely with superintendents, district school principals, and community based organization leaders, both citywide and in District 4, on implementation. Seat implementation for three year olds will continue over the next two years.
East Harlem | Provide funding to the East Harlem COAD (Community Organizations Active In Disasters) | 41 | Community Resources | NYCEM | Done | NYCEM funded and conducted the first Community Preparedness Boot Camp to the East Harlem Community and started a Community Preparedness Council. NYCEM continues to support the Community Organizations Active in Disasters (COAD) at monthly meetings and through direct staff support. NYCEM also works to build a community and connect emerging groups to the East Harlem COAD and connect the COAD to broader city-wide efforts. | NYCEM works closely with the East Harlem COAD to increase the preparedness of residents in the area. In 2018 NYCEM will be piloting a training curriculum to accompany its community planning toolkit. NYCEM will pilot this training with the East Harlem COAD before rolling it out citywide to assist the COAD in its efforts and identify the areas all stakeholders in the community, including community groups, elected officials, Community Emergency Response Teams, businesses, schools, houses of worship and other groups, are needed to work together to accomplish mutual goals. | 2018 |  | NYCEM's Community Preparedness program is launching a Community Preparedness Boot Camp for community and faith-based organizations in East Harlem and the Bronx. This two-day training is for community leaders interested in creating an emergency plan for their community and connecting to City resources. The Community Preparedness Boot Camp was held on June 13th and June 27th at the Salvation Army Corps Community Center. The East Harlem COAD is an active participant in this training.
East Harlem | Increase number of schools that offer Career and Technical Education (CTE) programs | 42 | Community Resources | DOE | In Progress | The Department of Education will provide technical assistance to Heritage High School and Park East High School with their plans to create meaningful career pathways courses serving as electives for students. The Office of Postsecondary Readiness will continue to provide guidance to the principals of Heritage High School and Park East High School in the development of career pathway coursework taking into account the limitations of the campus facilities and funding. Students in this area have access to up to 20 CTE programs at the School of Cooperative Technical Education, located at 321 East 96th Street. Plans to redevelop the campus are still in the works and Park East and another school is slated to be colocated at the site. This is a long term project that is still in development. Manhattan Center for Science and Mathematics has launched an Aeronautics / Pre-Engineering program for their students, utilizing new program resources. | The Department of Education (DOE) is committed to ensuring all students, including District 4 students, have the academic and technical education resources to have a pathway to a successful career. As such, we provide various pathways to help our students achieve that success; one pathway is our Career and Technical Education (CTE) programs. The development of a school-based CTE program requires sequenced programming and three years of development to meet New York State Department of Education CTE program approval. In order to create alternate pathways to graduation, the DOE will work with the following high schools to develop two new certified CTE programs: Heritage High School and Park East High School. While extensive funding for a CTE program is not available,, we will provide the schools with support to ensure students have the academic and industry-recognized skills that lead to high-quality college and career pathways, including technical assistance for schools, teacher per session fees, and a small allocation for technology and program supplies. | 2017-ongoing |  | DOE is committed to ensuring all students, including those in District 4, have the academic and technical education resources to have a pathway to a successful career. Career and Technical Education (CTE) programs can provide students with the skills they need to be competitive and succeed in the workforce. Developing a school-based CTE program requires sequenced programming and three years of development to meet New York State Department of Education CTE approval. In order to create alternative pathways to graduation, DOE will work with Heritage High School and Park East High School to develop two new certified CTE programs. While extensive funding is not currently available, DOE will provide these schools with supports to ensure students have the academic and industry-recognized skills that lead to college and career pathways, including technical assistance for schools, teacher per session fees, and a small allocation for technology and program supplies.
East Harlem | Implement the Building Community Capacity Program in East Harlem | 43 | Community Resources | DCLA | In Progress | The grant supports a Community Arts Coordinator to oversee the East Harlem Culture Collective's efforts to foster a social ecosystem in which local artists and cultural institutions can flourish, new audiences can be reached, and the local economy stimulated. Projects include development of a social media platform, an interactive neighborhood map, a monthly publication, and a temporary cultural exchange gallery for local artists, neighbors, cultural institutions, and community based organizations. | The Building Community Capacity program will support the East Harlem community in creating a strategy capable of driving action toward the arts and culture objectives identified in the East Harlem Neighborhood Plan (EHNP). In order to satisfy the City's procurement regulations and identify a grantee, an East Harlem nonprofit organization must submit an application to DCLA for funding. Working with DCLA, the selected grantee will (i) create a work scope and strategy based on EHNP goals; and (ii) select a consultant responsible for project management. Working with consultant, the community participants will (i) lay out project tasks; (ii) develop a volunteer infrastructure consisting of an oversight committee, leadership, and working groups; and (iii) cultivate cross-sector leaders who can catalyze efforts, provide assistance, and bring additional resources. | 2017-2019 |  | El Museo del Barrio was selected as the grantee to oversee the community arts development work. Over a dozen community members/cultural stakeholders have met regularly to identify and prioritize scope objectives. A job description was issued to select a project manager.
East Harlem | Increase afterschool funding for high school students | 44 | Community Resources | DYCD | Done | Afterschool programs such as Cornerstone and Beacon provide students in East Harlem the opportunity to build skills, get homework help, and explore their interests outside the classroom. A new three-year Beacon contract with SCAN New York Volunteer Parent Aides Association commenced in September 2017. The funding committed for this contract totals $1.69 million over three years, representing a significant increase in funding to Beacon programs. | The Administration has made providing high school aged youth alternatives for out-of-school time a key priority with increased funding and a steadfast commitment to support and strengthen the overall development of young people. In Community District 11 (CD11), we serve high school youth in after- school programs at 5 Cornerstones Programs located in community centers located in Clinton, East River, Lehman, Wagner, and Johnson Houses. These programs serve 275 high school aged youth. Additionally, there are two Beacon programs located at M.S. 224 and Coalition School for Social Change. New Beacon program contracts commenced September, 2017. DYCD awards increased funding for each of our CD11 Beacon Programs from $400,000 to $550,000. Both contracts together total $1.1 million per year for 3 years and represent a 37.5% percent increase in Beacon funding in the East Harlem community. To create the RFP, DYCD held several roundtable discussions with community stakeholders, non-profits, and advocates. The new RFP allows providers to identify the age groups of focus in each community to ensure the needs of each specific community are being met. The RFP included three major enhancements for all Beacons: each program now has increased flexibility to identify populations to provide intensive services, every Beacon program will now have a Street Outreach Worker on staff, and each Beacon will have the option of opening during the weekend and increased late night hours during the Summer months. These enhancements allow Beacons to better target high school students for services, and provide resources for them - especially in the East Harlem community where Beacons have been mobilizing over the years to act as supports for young adults. | 2017 |  | Afterschool programs like Cornerstone and Beacon provide students in East Harlem the opportunity to build skills, get homework help, and explore their interests outside the classroom. A new three-year Beacon contract with SCAN New York Volunteer Parent Aides Association commenced in September 2017. The funding committed for this contract totals $1.69 million over three years, or nearly $600,000 per year, representing a significant increase in funding to Beacon programs.
East Harlem | Improve access to early care and education | 45 | Community Resources | ACS | Done with ongoing work | ACS converted vacant Head Start seats into new Early Head Start Seats to serve toddlers in East Harlem. This Early Head Start program, as part of the City's Early Learn NYC continuum of childcare programming, offers subsidized, high-quality care to families who earn up to 100 percent of the federal poverty level in either centers or home-based care. Programs operate eight to ten hours per day year-round, and offer comprehensive services including developmental screenings, family support, health and mental services. As of July 1, 2017, ACS has converted two classrooms among the 27 East Harlem locations in order to serve more toddlers in East Harlem. ACS and DOE continue to collaborate as the City's EarlyLearn Programs transition into DOE's portfolio in 2019. ACS’s Head Start grant ends June 30, 2019, and DOE applied for and was awarded the grant for NYC starting July 1, 2019. | The Administration for Children's Services (ACS) has converted vacant Head Start seats into new Early Head Start seats to serve toddlers in East Harlem. This Early Head Start program, as part of the City's EarlyLearn NYC continuum of childcare programming, offers subsidized, high quality care to families who earn up to 200% of the federal poverty level in either centers or home-based care. Programs operate 8-10 hours per day, year round, and offer comprehensive services including developmental screenings, family support, health and mental health services. As of July 1, 2017, ACS has converted 2 classrooms among their 28 East Harlem locations in order to serve more toddlers in the East Harlem community. | 2019 |  | ACS converted vacant Head Start seats into new Early Head Start Seats to serve toddlers in East Harlem. This Early Head Start program, as part of the City's Early Learn NYC continuum of childcare programming, offers subsidized, high-quality care to families who earn up to 100 percent of the federal poverty level in either centers or home-based care. Programs operate eight to ten hours per day year-round, and offer comprehensive services including developmental screenings, family support, health and mental services. As of July 1, 2017, ACS has converted two classrooms among the 27 East Harlem locations in order to serve more toddlers in East Harlem. ACS and DOE continue to collaborate as the City's EarlyLearn Programs transition into DOE's portfolio in 2019. DOE will manage the next solicitation in 2019 to begin services in 2020.
East Harlem | Build a new SBS station on 125th St and Lexington Ave | 46 | Transportation & Infrastructure | DOT | In Progress | To enhance the existing Select Bus Service service at Lexington Avenue and 125th Street, DDC will begin installation of two new bus bulbs, bus pads, and a new bus shelter. Bus bulbs extend the sidewalk, providing bus riders with more room at the bus stop and improving bus operations. Construction at this location is projected to start this summer 2019. | DOT works closely with the Metropolitan Transportation Authority (MTA) on SBS Routes, the City's version of bus rapid transit. In the decade since SBS began, SBS routes have seen: 10-30% faster bus speeds, 10% increase in ridership, and customer satisfaction of 95%. Select Bus Routes achieve this through off-board fare collection, all-door boarding, bus lanes, bus bulbs, curb extensions, bus shelters, and real time arrival information. Also, any buses can use the bus lanes, which is an advantage for all transit. SBS began along 125th street in 2014 with the M60. To enhance the existing SBS service at Lexington Ave and 125th St, the Department of Design and Construction (DDC) will begin installation of two new bus bulbs, bus pads and a new bus shelter. This work will provide riders more waiting space as well as shelter. Extending the sidewalk to the bus lane allows for better bus operations. | 2018 |  | Starting in 2018, DDC will begin construction of two new bus bulbs, bus pads, and a new bus shelter at 125th Street and Lexington Avenue. Bus bulbs extend the sidewalk, providing bus riders with more room at the bus stop and improving bus operations. The work is estimated to finish in 2020.
East Harlem | Improve way-finding to Randall's Island | 47 | Transportation & Infrastructure | DOT | In Progress | DOT is taking steps to improve wayfinding to Randall's Island and throughout East Harlem. DOT installed two wayfinding signs in 2018 and plans to install six signs throughout the neighborhood in 2019. In Spring 2019, DOT staff began analysis and site planning for an additional six signs, including one that will provide real-time passenger information at the M15 Select Bus Service stop on 2nd Avenue and East 106th Street. | In 2014 the New York City Department of Transportation (DOT) installed bicycle way-finding signs that indicate the route to Randall's Island at the corner of 1st Ave/102nd St and at the sidewalk ramp near the east end of the block. In October 2017 the DOT Borough Engineer completed the installation of a Bike signage plan designed to bring users to the RFK and Willis Ave Bridges. While there is a bike lane leading to the Wards Island Bridge (103rd Street Footbridge) on E.102nd Street, there is currently no marked and signed return route for bikes; however, one is being planned for E.105th Street. Additionally, DOT's pedestrian way-finding group has been planning a system of signs and a map with local stakeholders. Using in-house crews DOT will be installing new way-finding signs in East Harlem in 2018. The way-finding group started the project with a workshop at CB11 in February 2015. Since then the staff have met with the New York Restoration Project, the Department of Health and Building Healthy Communities, specifically regarding signage to direct bicyclists and pedestrians from East Harlem and the South Bronx to Randall's Island. DOT is also working with the Randall's Island Park Alliance on this East Harlem sign network plan. Once DOT has completed the network plan, DOT will share the locations with CB 11 and CB 8. | 2018 |  | This spring, DOT installed a fingerpost sign at 2nd Avenue between E 101 Street and E 102 Street that directs people to Randall’s Island via the 103 Street Bridge. It also points people in the direction of Central Park. This is the first of two fingerpost signs scheduled to be installed in East Harlem this year. Additionally, DOT has two wayfinding area signs (also known as WalkNYC signs) pending installation and is analyzing two more sites for potential signs.
East Harlem | Improve safety for visually-impaired pedestrians | 48 | Transportation & Infrastructure | DOT | Done with ongoing work | Intersections that receive accessible pedestrian signal (APS) installations are selected based on a ranked list of intersections citywide. DOT has committed to evaluating a list of intersections of concern provided by local stakeholders and responding within four months. A status report of APS installation citywide is available (https://www1.nyc.gov/html/dot/downloads/pdf/2018-aps-program-status-report.pdf), and includes the 150 top-ranked intersections for installation of new APS units. | Accessible Pedestrian Signals (APS) are devices affixed to pedestrian signal poles or added with a supplemental pole. These devices provide information in non-visual formats, such as audible tones, speech messages and vibrating surfaces, to alert vision-impaired pedestrians when the "walk" phase is available at a given intersection. Since August 2016, DOT has installed thirteen APSs in East Harlem, and will evaluate additional crosswalks and intersections in East Harlem for the treatment. Intersections that receive APS installations are selected based on a ranked list of intersections city-wide. DOT will commit to evaluate a list of intersections of concern provided by the local council members and respond within four months of receiving the list of requested locations. | 2016-17 |  | Intersections that receive accessible pedestrian signal (APS) installations are selected based on a ranked list of intersections citywide. DOT has committed to evaluating a list of intersections of concern provided by local stakeholders and responding within four months of receiving the list of requested locations. A status report of APS installation citywide is available at http://www.nyc.gov/html/dot/downloads/pdf/2017-aps-program-status-report.pdf, and it includes the 100 top ranked intersections for installation of new APS units as of December 31, 2017.
East Harlem | Working with community stakeholders, plan for the development of an enclosed consolidated DSNY sanitation facility for M10 and M11, which meets LEED gold standards | 49 | Transportation & Infrastructure | DSNY | In Progress | Community stakeholders from Manhattan Community Boards 10 and 11 continue to meet quarterly to make progress towards building consensus on a preferred alternative site, including evaluating and surveying viable sites, for the development of an enclosed DSNY facility to serve sanitation needs for residents over the next 100 years. | DSNY will immediately begin planning for a permanent, long-term facility to serve District 11 sanitation needs, which includes the following goals: Explore options for a permanent consolidated facility that could house multiple garages, including: District 11, District 10, District 9, and/or the Manhattan Lot Cleaning Unit. Assess suitable sites for the permanent facility that will serve residents for the next 100 years. Explore all City-owned sites and appropriate privately-owned sites in Manhattan Community Boards 9, 10, and 11, as well as potential acquisition of the entire Block 1792. DSNY will engage with local stakeholders on a quarterly basis starting in Q4 2017. The stakeholder group will include representatives from Community Board 11, the local Council Member, the Manhattan Borough President, and additional members that the stakeholders identify. The stakeholder group will provide feedback and accountability on the following tasks:1. Developing a shared vision with H+H for future use of existing East 99th Street DSNY facility that reflects the needs of H+H and the community. 2. Providing ongoing community feedback on the construction and operation of the East 127th Street facility. 3. Formalizing a community-engagement process for planning a permanent consolidated facility. This process will include clear benchmarks: o Establish shared priorities/goals with the stakeholder group for the permanent sanitation facility (Q2 2018). o Share site and building program options with the stakeholder group, including a survey of viable sites, potential building programs for each site, costs associated with acquiring and building a garage on each site, and the critical path to acquiring and developing those sites (Q4 2018). o Community consensus and agreement on preferred alternative site (Q2 2019). o Contingent on the above, timeline and further milestones for site selection, budget allocation, feasibility, design, and construction (Q2 2019). o Contingent on establishing community consensus on a proposed site and securing the necessary funding to develop the facility. DSNY's goal is to complete a facility by 2027. | 2017-2027 |  | In 2018, DSNY initiated a community planning process to address East Harlem's sanitation needs for the long term. In collaboration with Community Board 11, Council Member Ayala, and Manhattan Borough President Gale Brewer, DSNY is working with community stakeholders to assess potential sites and to establish consensus around a preferred site and building program. DSNY expects this work to continue through 2019.
East Harlem | Integrate subway station entrances into building envelopes at East 116th Street and Lexington Avenue | 50 | Transportation & Infrastructure | DCP | Done | DCP introduced a series of zoning proposals, including text amendments to restrict building height on a section of Park Avenue between East 122nd and East 124th streets, to further restrict building heights on a section of Park Avenue in R7D and R8A districts, and to include provisions for the integration of subway entrances into building envelopes at the intersection of East 116th Street and Lexington Avenue. These proposals were referred into public review in December 2018 and approved by the City Council Land Use Committee in May 2019. | The City will pursue a follow-up zoning action to include provisions for the integration of subway entrances into building envelopes at East 116th Street and Lexington Avenue. Such integration is to include potential subway stair relocation and renovation requirements, subject to consultation with MTA. | 2018 |  | Following the public review process, the community expressed concerns regarding better integration of streetscape design and transit accessibility. DCP has committed to modifying the Zoning Resolution to allow for the integration of subway station entrances into building envelopes at the intersection of East 116th Street and Lexington Avenue. In order to evaluate the impact of such integration, DCP has consulted the MTA to ensure that the proposed text amendment is aligned with their current station standards. As a result, there was one projected development site identified where the bulk and height may change in order to accommodate a subway station. This change will also be included in the revised analysis of the FEIS and memorialized in a technical memorandum that will outline the changes being made. The Department is currently on track to complete this commitment and refer this text amendment out by the end of 2018.
East Harlem | Modify parking and commercial delivery loading / unloading regulations along 125th St | 51 | Transportation & Infrastructure | DOT | In Progress | DOT is developing a comprehensive plan to improve the efficiency of truck deliveries across the five boroughs. The Smart Truck Management Plan is scheduled to be released in 2019. Information gathered during this process will be used to evaluate changes to commercial loading regulations on the street, if necessary, and to more broadly identify opportunities to improve truck safety and air quality and reduce congestion. | DOT's Office of Freight Mobility is in the process of developing a comprehensive plan (scheduled to be released in 2018) to improve the efficiency of truck deliveries across the five boroughs, while also reducing the environmental and community impacts of trucking. As part of this study, DOT's consultants have evaluated various commercial corridors citywide, including in the East Harlem area, to assess the variability of freight flow and curb access to local businesses. This information will be used to evaluate any changes to commercial loading regulations on the street, if necessary. | 2018 |  | DOT is in the process of developing a comprehensive plan to improve the efficiency of truck deliveries across the five boroughs. The Smart Truck Management Plan is scheduled to be released in Summer 2018. Information gathered during this process will be used to evaluate changes to commercial loading regulations on the street, if necessary and more broadly identify opportunities to improve truck safety and air quality and reduce inefficiency, congestion, and impacts on neighborhoods.
East Harlem | DEP will seek opportunities in the district to connect with existing homeowners and new developers to expand the Green Infrastructure Grant Program to private properties throughout CD11 | 52 | Transportation & Infrastructure | DEP | In Progress | DEP continues to notify local businesses about workshops aimed at potential recipients of the Green Infrastructure Grant Program, which covers 100% of the design and construction of green stormwater management projects. | DEP offers a grant program for private property owners in New York City. The minimum requirement is to manage 1-inch of stormwater runoff from the contributing impervious area. In order to educate properties owners on the program, DEP will partner with the Councilmember of District 8 on events involving homeowner outreach for the Green Infrastructure Grant Program. | 2017-ongoing |  | DEP is working with local elected officials to identify local businesses that may be potential grant recipients of the Green Infrastructure Grant Program. Grants cover 100% of the design and construction of green stormwater management projects like green roofs and rain gardens or pervious pavement in parking lots.
East Harlem | Establish a height limit in the R10 district on Park Ave between East 122nd and East 124th Streets | 53 | Transportation & Infrastructure | DCP | Done | DCP introduced a series of zoning proposals as part of the City's East Harlem Neighborhood Initiative, including text amendments to restrict building height on a section of Park Avenue between East 122nd and East 124th streets, to further restrict building heights on a section of Park Avenue in R7D and R8A districts, and to include provisions for the integration of subway entrances into building envelopes at the intersection of East 116th Street and Lexington Avenue. These proposals were referred into public review in December 2018 and approved by the City Council Land Use Committee in May 2019. | The City will introduce a follow-up zoning text amendment to restrict building heights on the section of Park Avenue between 122nd and 124th Streets zoned R10. City Planning will determine appropriate height limits after gathering input from community stakeholders, including elected officials and a height limit of 275' will be in scope. | 2018 |  | In response to community concerns regarding height limits, DCP will establish a maximum height limit of 275 feet in the C6-4 (R10 equivalent) zoning district on Park Avenue between East 122nd and East 124th Streets. Currently, DCP is evaluating how these changes would modify the Final Environmental Impact Statement (FEIS). As part of this analysis, DCP will determine whether this change will impact projected development sites within this area and require changes to mitigation measures identified in the FEIS. This process ensures that the size and shape of potential developments sites continue to have no significant adverse effect on the neighborhood. Any changes identified will be outlined in a technical memorandum. DCP is currently on track to complete this commitment and refer this text amendment out by the end of 2018.
East Harlem | Follow up correction to height limit on Park Ave between East 115 and East 118 Streets | 54 | Transportation & Infrastructure | DCP | Done | DCP introduced a series of zoning proposals, including text amendments to restrict building height on a section of Park Avenue between East 122nd and East 124th streets, to further restrict building heights on a section of Park Avenue in R7D and R8A districts, and to include provisions for the integration of subway entrances into building envelopes at the intersection of East 116th Street and Lexington Avenue. These proposals were referred into public review in December 2018 and approved by the City Council Land Use Committee in May 2019. | The City will introduce a follow-up zoning text amendment to further restrict building heights in this section of Park Avenue to 125 in the R7D and 145 in the R8A district. | 2018 |  | DCP has committed to reducing the maximum height limit from 215 feet to 125 feet in the R7D districts mapped along Park Avenue between East 115th and East 117th Streets and reducing the maximum height limit from 215 feet to 145 feet in the R8A district mapped along Park Avenue between East 116th and East 118th Streets. In order to facilitate this change, DCP must also evaluate how these sites were analyzed in the FEIS and how the reduction in height impacts the environmental analysis. After considering each of the projected development sites, DCP has determined that only one site would be affected by the reduction in height. The Department is currently on track to complete this commitment and refer this text amendment out by the end of 2018.
East Harlem | Fund a Safe Routes to School (SRTS) study and implement new routes in East Harlem | 55 | Transportation & Infrastructure | DOT | In Progress | A Safe Routes to School (SRTS) study was conducted in 2007, and SRTS capital work has already been performed in East Harlem as a result of that initial study. Work was completed at PS 7 in 2011 and at PS 72 in 2009. In the time since the first study, DOT has made sweeping citywide safety policy changes and specific capital investments that have benefited East Harlem. In Fall 2021, DDC will begin construction of a curb extension and pedestrian island that will improve pedestrian visibility and slow down vehicles near PS 83, Esperanza Prep Academy, TAG Young Scholars, PS 138, and PS 146. | A SRTS Study was conducted in 2007. SRTS capital work has already been performed in East Harlem as a result of that initial study: work was completed at PS 7 in 2011 and at PS 72 in 2009. In the time since the first study, DOT has made sweeping itywide safety policy changes and specific capital investments that have benefitted East Harlem. Although school safety zones created in the 2007 program brought speeds near schools to 20 M.P.H., as part of Vision Zero, the City speed limit was brought down to 25 M.P.H. everywhere. Similarly, both 1st and 2nd Avenue are Vision Zero priority corridors and the safety improvements implemented on these corridors, such as pedestrian islands, benefit children, parents and residents who walk around the neighborhood, including to and from local schools. In a new phase of SRTS projects, planned between 2020 and 2022, DOT will construct a curb extension and pedestrians island in the vicinity of PS 83, Esperanza Prep Academy, TAG Young Scholars, PS 138 and PS 146. The curb extension is planned for 2nd Ave & 109th St across the street from PS 83 and directly in front of IS 12 and the pedestrian island is slated for 1st Ave & 106th St. The curb extension and pedestrian island will slow down vehicles and improve pedestrian visibility. | 2020 |  | A Safe Routes to School (SRTS) Study was conducted in 2007. SRTS capital work has already been performed in East Harlem as a result of that initial study: work was completed at PS 7 in 2011 and at PS 72 in 2009. In the time since the first study, DOT has made sweeping citywide safety policy changes and specific capital investments that have benefited East Harlem. Starting in 2021, the Department of Design and Construction will begin construction of a curb extension and pedestrian island that will improve pedestrian visibility and slow down vehicles near PS 83, Esperanza Prep Academy, TAG Young Scholars, PS 138, and PS 146.
East Harlem | Coordinate with Agencies to incorporate green infrastructure into city projects | 56 | Transportation & Infrastructure | DEP | Done with ongoing work | Since the 2018 update, DEP completed Playground 103 CIII on the FDR Drive and E. 102nd St., which includes rain gardens and a turf field that serves as a subsurface stormwater detention. DEP also completed the James Weldon Johnson Playground on 115th and Lexington Ave, which includes rain gardens, permeable pavers, permeable asphalt and subsurface detention via a turf field installation. | Department of Environmental Protection (DEP) will partner with DPR, DOT, HPD, and EDC to incorporate green infrastructure into new development and public property retrofit projects when possible. | 2017-ongoing |  | DEP has completed green infrastructure projects along 5th Avenue and 138th Street and at the 2nd Avenue Select Bus Service stop, including two right-of-way green streets. In addition, DEP and DPR are collaborating on green infrastructure improvements at the Playground 103 CIII and the James Weldon Johnson Playground. DEP will continue to seek opportunities to incorporate green infrastructure into public property projects wherever possible.
East Harlem | Study parking requirements in East Harlem | 57 | Transportation & Infrastructure | DCP | In Progress | DCP has commenced a study of parking requirements in East Harlem. | City Planning will study parking requirements in the East Harlem area, and pursue follow-up action if deemed appropriate. ? | 2019 |  | While DCP is committed to studying the parking conditions in East Harlem, this effort will require consultation with a number of divisions internally at DCP as well as a number of interagency partners to determine the appropriate scope of this study. The Department is taking the necessary steps to meet this commitment and commence a study in 2019.
East Harlem | Increase access to employment opportunities for local residents by establishing a satellite Workforce 1 Career Center in East Harlem | 58 | Economic Development | SBS | In Progress | SBS is working in collaboration with community leaders, partners, and organizations to identify the most appropriate local site to develop and establish the satellite Workforce 1 Career Center. | The City commits to establishing a satellite Workforce1 Career Center in East Harlem in a location accessible to the public and developed with input from the community and local councilmembers. The satellite Workforce1 Career Center will offer connections to employment and training services, including services for target populations such as out of school, out of work youth aged 18-24 years old. Small Business Services (SBS) operates 21 Workforce1 Career Centers throughout the city, providing recruitment expertise, industry knowledge, and skill-building workshops to connect New Yorkers to jobs. SBS connects more than 25,000 New Yorkers with quality employment each year. Through the City's HireNYC policy, City contractors are required to consider New Yorkers for employment opportunities created through eligible City contracts. The City's HireNYC program leverages SBS's network of Workforce1 Career Centers to connect New Yorkers to open positions created through the City's purchases and investments. Through HireNYC and the Workforce1 Career Center system, New Yorkers have a first shot at jobs related to City projects, and employers have access to a pool of talent from the local community. East Harlem residents will be able to access opportunities created through the City's HireNYC policy by visiting their local Workforce1 Career Center, or any of the City's 21 Workforce1 Career Centers. | 2019 |  | SBS is committed to expanding workforce services in East Harlem. We are currently incorporating feedback from the community, district councilmembers, and other local stakeholders on potential locations for the satellite Workforce1 Career Center.
East Harlem | Protect and enhance viability of local businesses through SBS grants | 59 | Economic Development | SBS | Done with ongoing work | SBS awarded $1.49 Million in Neighborhood 360 grants to Union Settlement Association to staff, plan, and implement customized commercial revitalization programs informed by the Commercial District Needs Assessment over the next three years. Initial Projects include supplemental sanitation and corridor beautification, business support and merchant organization, along with place making and district marketing. SBS will provide ongoing business planning workshops and available one-on-one technical assistance for local merchants to improve skills in digital marketing, accounting, hospitality, and customer service to help "brick and mortar" businesses thrive in place. Weekly merchant "pop up" events are held at the community plaza on East 125th Street and Park avenue to expose consumers to the cuisine of East Harlem. | Through its Neighborhood 360° grant program, SBS has funded $1.49M to local non-profit partners. This funding will allow local partners over the next three years to staff, plan and, implement customized commercial revitalization programs for East Harlem's primary commercial corridors. Programs will be informed by the recently-completed Commercial District Needs Assessment for East Harlem and will be responsive to recommendations from the community. | 2017-2020 |  | Through the Neighborhood 360° program, SBS awarded $1.49M in grant funding to local non-profit partners in East Harlem. This funding enables local partners to staff, plan, and implement customized commercial revitalization programs for East Harlem’s primary commercial corridors over the next three years. So far, through the Neighborhood 360 program, 46 new trash cans have been installed throughout the commercial corridors, merchant meetings are being held monthly to develop leadership in the neighborhood, holiday lighting was installed on 116th Street, and supplemental sanitation services are being provided in East Harlem. To date, over 19,000 trash bags have been collected through the supplemental sanitation services made possible by the Neighborhood 360 Funding.
East Harlem | Connect residents to good jobs in the building trades through Upper Manhattan Workforce 1 Career Center and East Harlem Satellite Workforce 1 Center | 60 | Economic Development | SBS | Done with ongoing work | SBS, via the Upper Manhattan Workforce1 career center conducts ongoing weekly recruitments and training events in collaboration with local community partners. Community partners include the Aguilar library, local New York City Housing Authority sites, and local High Schools. SBS is working in collaboration with community leaders, partners, and organizations to identify most appropriate local site to develop and establish the satellite Workforce1 Career Center. | SBS will connect East Harlem residents to trainings provided through the Workforce1 Center System. Trainings offered are employer-informed, and prepare participants to connect to quality jobs within growth sectors such as healthcare, construction, and technology. SBS will partner with local community organizations, to recruit, serve and prepare East Harlem residents for training and quality employment opportunities within in-demand, growth sectors. | 2017-ongoing |  | SBS connects East Harlem residents to trainings provided through our network of 21 Workforce1 Career Centers. Trainings offered are employer-informed and prepare participants to connect to quality jobs within growing sectors like healthcare, construction, and technology. SBS partners with a network of more than 350 community partners, including East Harlem organizations like Strive and Union Settlement, to connect candidates to opportunities with our training and employer partners. For example, in November 2017, in partnership with NYCHA REES, SBS held a recruitment event at the East Harlem Isaac Houses/Holmes Towers for Nontraditional Employment for Women’s (NEW) fall pre-apprenticeship programs. SBS has partnered with four exclusive pre-apprenticeship programs, including NEW, to connect qualified individuals to training opportunities that lead to apprenticeships in the construction trades in NYC. SBS is working with the East Harlem community to convene stakeholders to plan for workforce development services and resources that will best serve the community needs.
East New York | Break ground on 1,200 units of affordable housing. Possible sites include Phipps Site, Dinsmore-Chestnut, Christopher-Glenmore, NIHOP and NCP clusters. | 1 | Housing | HPD | In Progress | HPD recently closed on the financing for a 228 unit affordable building at 50 Pennsylvania Avenue using the Extremely Low and Low Income Affordability (ELLA) program. HPD has released four requests for proposals (RFPs) for the development of affordable housing in the East New York area, including Dinsmore-Chestnut and Christopher-Glenmore. Together, these sites will create over 500 affordable apartments on formerly City-owned land. HPD is also working with a number of private owners who will be creating 100% affordable housing on their sites. Overall, 503 units of new construction affordable housing have been created in the rezoning area since the rezoning. This includes 318 affordable homes in projects financed by HPD (50 Pennsylvania Avenue and 315 Linwood Street) and 185 affordable homes created through the Mandatory Inclusionary Housing program across three sites (2437 Pitkin Avenue, 975 Liberty Avenue, and 2178 Bergen Street). All of these new affordable homes are under construction now. HPD will continue working with the development partners selected through RFPs and the owners of private sites to advance 100% affordable housing projects reaching deep affordability. | HPD will expedite the construction of over 1,200 units of deeply affordable housing over the next two years following ULURP approval. These units will be constructed on sites that include the publicly owned site at the intersection of Dinsmore Place and Chestnut Street. HPD will host a community-visioning process for the Dinsmore-Chestnut site in June 2016 to explore the different types of housing, community facilities, and retail uses that residents hope to see built there. Two additional publicly owned parcels have been identified by the Council Member as priority development sites since the release of the East New York Housing Plan in September 2015. One is located at the intersection of Christopher and Glenmore Avenues; it can accommodate approximately 100 units of affordable housing. A community-visioning process for this site will begin in the summer of 2016, and an RFP will be released before the end of the year. A smaller site, on Essex Street between Fulton Street and Folsom Place, can accommodate approximately 15 affordable units and will be made available for redevelopment as part of the NIHOP/NCP RFQ process. Further, the former Chloe Foods facility is now controlled by the non-profit affordable housing developer, Phipps Houses, who has committed to developing over 900 affordable units serving the incomes described above. | 2016–2018 | Between April 2016 and March 2017, HPD financed the construction of 752 new units of affordable housing throughout Brooklyn Community District 5. This includes homeownership opportunities for first-time buyers and 639 new rental units through the Extremely Low and Low Income Affordability program. In addition, HPD is moving forward on financing the development of deeply affordable housing on publicly and privately-owned sites in and around the immediate rezoning area, including the following key sites. Phipps Site, formerly Chloe Foods (private, in predevelopment) – The former Chloe Foods facility is controlled by the nonprofit affordable housing developer Phipps Houses, which has committed to developing approximately 900 affordable units serving the incomes described in the table on the following page. Phase I, which includes approximately 400 affordable apartments and ground-floor retail/community facility space, is anticipated to close in 2018. Dinsmore-Chestnut (public, RFP submissions under review) – On June 19 and June 23, 2016, HPD convened two interactive community visioning workshops to gather public input for the future development of new affordable housing, neighborhood amenities, and a new 1,000-seat public school and community school yard on the publicly-owned Dinsmore-Chestnut site. Results from the workshop and additional feedback received through emails and a paper/online questionnaire are summarized in a report available on HPD’s website (nyc.gov/dinsmore-chestnut). The Request for Proposal (RFP) for this site, which is projected to facilitate the creation of about 200 units of affordable housing, was issued in December 2016. Developers were encouraged to consult the community visioning report in developing their proposals, which were submitted in March 2017 and are currently under review. Christopher-Glenmore (public, RFP in development) – The comprehensive neighborhood planning process in Brownsville that began in Summer 2016 included community visioning for the Christopher-Glenmore site RFP. The Brownsville Plan was released on June 1, 2017, and a subsequent RFP will ensure that proposals address the community goals and priorities outlined in the plan. Approximately 100 affordable units are expected to be created on this site. NIHOP and NCP clusters (public, RFP submissions under review) – Submissions are currently under review with anticipated designation in Summer 2017. The clusters contain about 125 units of affordable homeownership and rental units. | HPD recently closed on the financing for a 100 unit affordable building at 315 Linwood Street using the ELLA term sheet. HPD has released four requests for proposals (RFPs) for the development of affordable housing in the East New York area, including Dinsmore-Chestnut and Christopher-Glenmore. Together, these sites will create over 500 affordable apartments on formerly City-owned land. HPD is also working with a number of private owners who will be creating 100% affordable housing on their sites. The former Chloe Foods facility, which is controlled by a private owner and expected to generate over 900 affordable homes, has been unexpectedly delayed due to a title claim by a former property owner. HPD continues to work with the owner and will work towards starting construction as soon as possible.
East New York | Study the feasibility of affordable housing development on the Grant Avenue municipal parking lot | 2 | Housing | HPD | Done | On March 4th, 2019, HPD selected a winner of the Grant Avenue Muni Lot Modular RFP. The development team, a partnership between Thorobird Companies and local non-profit Bangladeshi American Community Development and Youth Services (BACDYS), will develop over 160 affordable homes using modular construction methods. Brooklyn-based FullStack Modular will manufacture the modules used to construct the project, and Think! Architecture and Design will serve as the project architect. The mixed-use development will be 100% affordable at a range of income levels, with a set-aside for formerly homeless households. Non-profit partner BACDYS will oversee programming in the community space that will focus on serving immigrants, women, and low-income community members. The project will also include a medical clinic operated by Brooklyn-based BMS Health and Wellness, a Federally Qualified Health Center that sees patients regardless of their ability to pay or health insurance status. | The site is currently operated by DOT as a municipal surface parking lot. However, it is adjacent to the Grant Avenue A train station, and the subway runs underneath a significant portion of the site. Because of these constraints, further analysis is needed to understand development feasibility and the potential costs associated with building above and/or adjacent to the subway line. Timeline: HPD will dedicate resources to undertake a site analysis and study the development potential of the site in 2016, which will determine the potential for an RFP release in 2017. | 2016–2017 | The City continues to explore the feasibility and appropriateness of other public sites for affordable housing development. The Grant Avenue Municipal Parking Field is currently operated by the NYC Department of Transportation (DOT) as an active municipal surface parking lot with 203 spaces adjacent to the Grant Avenue subway station on the IND line (A train) in East New York. HPD began conducting a feasibility analysis of the site for affordable housing at the end of 2016 and higher level coordination with both DOT and MTA is currently underway. The subway runs underneath a significant portion of the site and poses formidable engineering constraints, which require further analysis to understand development feasibility and the potential costs associated with building above and/or adjacent to the subway line. HPD will continue working with DOT and MTA in order to determine the development feasibility and potential project timeline by the end of 2017. | HPD released a Request for Proposals (RFP) on May 24, 2018 for an affordable housing development at the Grant Avenue municipal parking lot. As part of the project, the City is proposing to close the eastern DOT-managed Municipal Parking Lot and develop affordable housing, community facility space and/or retail on the lot, with a portion being retained for open space. This RFP is the first disposition of City-owned land under the City’s modular construction initiative announced under Housing New York 2.0. The submission deadline for responses is September 10, 2018.
East New York | Finance the rehabilitation of existing housing to preserve affordability | 3 | Housing | HPD | Done with ongoing work | HPD continues to monitor rent-restricted units and reach out to owners with regulatory agreements that are near the end of their affordability period to let them know about the financial incentives HPD can provide to preserve affordability. HPD is also taking a much more proactive and strategic approach than ever before to target building owners who could benefit from HPD's financing and tax incentives in exchange for agreeing to maintain the affordability of their units. Since 2014, HPD has financed the rehabilitation and continued affordability of 6,925 apartments in CD 5. This includes the 5,881 apartments at Starrett City, the largest federally subsidized development in the nation and a critical source of deeply affordable housing for the community. | HPD will monitor units already rent-restricted through regulatory agreements with government agencies. HPD will reach out to owners with any such regulatory agreements that are near the end of their affordability period to let them know about the financial incentives HPD can provide to preserve affordability. On an annual basis, HPD will provide reports to the Council Member of all units with regulatory agreements expiring in the next five years to ensure careful monitoring. HPD is also working to identify opportunities to protect the affordability of buildings that are not currently regulated. With the help of its new Community Partnerships unit, HPD is taking a much more proactive and strategic approach than ever before to target building owners who could benefit from HPD's financing and tax incentives in exchange for agreeing to maintain the affordability of their units. Many owners are either not aware of HPD's products or feel uncomfortable working with a public agency, but HPD is trying to better serve those owners. | Ongoing | Between April 2016 and March 2017, HPD financed the preservation of 322 affordable homes in Brooklyn Community District 5, 144 of which serve households earning extremely low and very low incomes (less than 50% of AMI). These buildings are undergoing various repairs and rehabilitation work, including kitchen and bathroom upgrades, energy efficiency retrofits, façade improvements, and more. HPD continues to work with property owners in East New York with regulatory agreements that may be expiring, and proactively reaches out to building owners who could benefit from HPD’s loan programs and tax benefits to make repairs and preserve affordability. Between April 2016 and March 2017, this outreach included events, mailings, emails, and calls to owners of physically distressed properties, owners of HUD 202 buildings, owners with expiring or recently expired J51 tax benefits, owners of Low Income Housing Tax Credit properties, and owners of buildings on or at risk of being on the tax lien sale. These targeted efforts reached 293 multifamily buildings in Brooklyn Community District 5 with a total of more than 3,000 rental units. Going forward, HPD will schedule annual meetings with Council Member Espinal to discuss recent preservation activities and opportunities in East New York. HPD, in partnership with Enterprise Community Partners, will pilot a Landlord Ambassadors Program to contract with community-based organizations to conduct outreach and help private multifamily building owners with navigate HPD financing programs and access resources needed to close on, construct, and operate their properties. HPD has selected Mutual Housing Association of New York (MHANY) as the nonprofit contractor to serve the Central/East Brooklyn area, including East New York. Lastly, with support from the City, the NYU Furman Center has created CoreData.nyc, a new tool to enable community organizations, residents, and elected officials to find information on government subsidized housing, including projected expiration of affordability restrictions. This resource facilitates improved coordination between the City and elected officials on extending the affordability of these properties. | HPD continues to monitor rent-restricted units and reach out to owners with any such regulatory agreements that are near the end of their affordability period to let them know about the financial incentives HPD can provide to preserve affordability. HPD is also taking a much more proactive and strategic approach than ever before to target building owners who could benefit from HPD's financing and tax incentives in exchange for agreeing to maintain the affordability of their units. Since 2014, HPD has financed the rehabilitation and continued affordability of 982 apartments in East New York.
East New York | HPD will only finance buildings that are 100% affordable and target low and extremely low incomes | 4 | Housing | HPD | Done with ongoing work | In East New York, MIH is only the floor, not the ceiling. When developers come to HPD for financing, HPD will only finance buildings that are 100% affordable, and at levels that target low and extremely low incomes. Through the East New York rezoning, HPD committed to achieving deeper affordability on sites in the neighborhood. In the years since, HPD has revised its financing programs to achieve these same goals on projects citywide. In 2017 HPD revised the terms of its Extremely Low and Low Income Affordability (ELLA) and Mix and Match financing programs, which are two of the most commonly used programs, to provide more homes for the lowest earners and also require that a portion of all homes are set aside for formerly homeless families. These changes were made in response to advocacy from organizations and individuals in East New York, as well as others from around the city. Key updates include: • Requiring 40% of all apartments in the ELLA program to serve extremely low and very low incomes as well as requiring and incentivizing deeper affordability under the Mix and Match program. • Requiring a 10% set aside for homeless families and individuals in every project, while still providing units for extremely low- and very low-income households. • Encouraging the incorporation of senior or supportive housing. • Increasing the number of permanently affordable units by 15% in MIH projects • Achieving a greater mix of incomes within individual projects, which contributes to their long-term sustainability and allows for projects to provide more units for low earners. | In East New York, MIH is only the floor not the ceiling. When developers come to HPD for financing, HPD will only finance buildings that are 100% affordable, and at levels that target low and extremely low incomes. Within these 100% affordable buildings, HPD is committing that at least 40% of all units will be reserved for households earning less than 50% of AMI (currently, as little as $23,350 to $38,850 for a three-person family). The remainder of the units in each building would primarily be affordable to households making 60% of AMI (currently less than $46,620 for a three-person family). The chart below breaks down the specific AMI requirements for HPD financed housing. In addition, HPD controls six clusters of public sites in the East New York rezoning area that could generate approximately 300 units of affordable housing. To meet calls from the Council Member and the community that more housing should serve the lowest income families, on these public sites, HPD is committing to finance even more units at the 30% and 40% AMI bands. | 2016–2024 | HPD continues to only finance buildings that are 100 percent affordable in East New York. The East New York projects whose finances have closed and/or are in the pipeline primarily target low and extremely low income households and include affordable housing for formerly homeless households. HPD remains committed to maximizing the number of units it finances at the deepest affordability levels on public sites in the East New York rezoning area, including on the Dinsmore-Chestnut site. | In East New York, MIH is only the floor not the ceiling. When developers come to HPD for financing, HPD will only finance buildings that are 100% affordable, and at levels that target low and extremely low incomes. Through the East New York rezoning, HPD commited to achieving deeper affordability on sites in the neighborhood. In the years since, HPD has revised its financing programs to achieve these same goals on projects citywide. In 2017 HPD revised the terms of its Extremely Low and Low Income Affordability (ELLA) and Mix and Match financing programs, which are two of the most commonly used programs, to provide more homes for the lowest earners and also require that a portion of all homes are set aside for formerly homeless families. These changes were made in response to advocacy from organizations and individuals in Inwood, as well as others from around the city. Key updates include: • Requiring 40% of all apartments in the ELLA program to serve extremely low and very low incomes as well as requiring and incentivizing deeper affordability under the Mix and Match program. • Requiring a 10% set aside for homeless families and individuals in every project, while still providing units for extremely low- and very low-income households. • Encouraging the incorporation of senior or supportive housing. • Increasing the number of permanently affordable units by 15% in MIH projects • Achieving a greater mix of incomes within individual projects, which contributes to their long-term sustainability and allows for projects to provide more units for low earners.
East New York | Issue annual progress reports on local affordable housing development and preservation | 5 | Housing | HPD | Done with ongoing work | HPD is working with the owners of potential development sites in the East New York rezoning area to explore development that exceeds MIH requirements. HPD recently closed on the financing for a nine-story apartment building with 218 affordable homes at 50 Pennsylvania Avenue using the ELLA term sheet. Below is a summary of all affordable housing development in CD 5 since 2014. Future updates will include a breakdown of affordable housing creation within the rezoning area. Please click here for a list of projects and relevant details. Several other new construction and preservation projects are currently in the pipeline, and HPD will continue to share information about projects it finances each year as part of the annual reports. | Once per year, HPD will report on the stock of all affordable housing that is built or preserved in the rezoning area. The following data will be made available to the public: Project location Construction type (new construction or preservation) Number of units AMI levels Rental or owner Start/completion dates Size of retail/community uses In this annual report, HPD will communicate progress in implementing and achieving the many goals and strategies described above and in the East New York Housing Plan. | 2017–ongoing | The NYC Department of Housing Preservation and Development (HPD) is continuing its commitment to the preservation and new construction of affordable housing in East New York. Between April 2016 and March 2017, HPD financed the construction and preservation of 1,076 affordable homes in Brooklyn Community District 5, including 984 rental units and 92 homeownership units. This includes 324 preserved units and 752 newly constructed units, integrated with approximately 61,000 square feet of new retail and community facility space. About 90 percent of these units serve households earning less than 80 percent of Area Median Income (AMI). Please refer to the table in the appendix for a list of projects and relevant details. Several other new construction and preservation projects are currently in the pipeline, and HPD will continue to share projects for which it has closed financing each year in conjunction with the annual reports. | HPD is working with the owners of potential development sites in the East New York rezoning area to explore development that exceeds MIH requirements. HPD recently closed on the financing for a 100 unit affordable building at 315 Linwood Street using the ELLA term sheet. Below is a summary of all affordable housing development in Community District 5 since 2014. Future updates will include a breakdown of affordable housing creation within the rezoning area. Please click here for a list of projects and relevant details. Several other new construction and preservation projects are currently in the pipeline, and HPD will continue to share projects for which it has closed financing each year in conjunction with the annual reports.
East New York | Launch an ENY Homeowner Helpdesk to connect homeowners to free financial and legal counseling | 6 | Housing | HPD | Done | The Center for NYC Neighborhoods launched the Homeowner Help Desk in East New York in February 2017 in partnership with Council Member Rafael Espinal, Cypress Hills Local Development Corporation, MHANY Management, and Brooklyn Legal Services Corp A. The Homeowner Help Desk provides advice on foreclosure prevention, home repairs, property tax exemptions, weatherization loans, avoiding scams, and more. Now in its third year, the Homeowner Help Desk has reached over 4,700 New York residents through a combination of door-knocking, phone calls, and targeted mailings; conducted or attended 58 community events, workshops, and presentations; and educated over 1,900 residents. The Help Desk has provided individualized services to homeowners through 914 counseling sessions. The Help Desk also partners with the NYC Department of Finance, which hosts the Help Desk at the annual tax lien sale events held across the city. | HPD will establish a dedicated Homeowner Helpdesk in the community with financial and legal counselors to help homeowners modify mortgages, prevent foreclosures, access home repair, DEP water relief programs, and weatherization loans, and address scams such as deed thefts and other issues. Outreach will be conducted through a combination of mailings, door knocking, phone calls, and the staffing of help desks in various locations...... Timeline: Launch Homeowner Helpdesk in summer 2016, continue for one year, then evaluate need to continue. Expense funding commitment is $250,000. Please see notes for entirity of commitment. | 2016–2017 | In January 2017, the Center began the East New York Homeowner Help Desk in partnership with Council Member Espinal. The Help Desk officially launched in February 2017 at the Cypress Hills Community School / PS 89 and is staffed by local nonprofit partners Brooklyn Legal Services Corp A, Cypress Hills Local Development Corporation, and MHANY Management. As of April 2017, the Homeowner Help Desk has reached out to over 3,000 East New York residents through a combination of methods, including door-knocking, phone calls, targeted mailings, community events, workshops, and presentations. So far, the Help Desk’s partners have educated over 1,000 neighborhood residents and provided housing or legal advice to about 280 homeowners on topics including foreclosure prevention, home repairs, tax exemptions, weatherization loans, and information about avoiding scams. | The Center for NYC Neighborhoods launched the Homeowner Help Desk in East New York in February 2017 in partnership with Council Member Rafael Espinal, Cypress Hills Local Development Corporation, MHANY Management, and Brooklyn Legal Services Corp A. The Homeowner Help Desk provides advice on foreclosure prevention, home repairs, property tax exemptions, weatherization loans, avoiding scams, and more. In the first year, the Homeowner Help Desk reached out to over 4,200 East New York residents through a combination of door-knocking, phone calls, and targeted mailings; conducted 12 community events, workshops, and presentations; educated over 1,600 residents; and provided housing and legal advice to 628 homeowners.
East New York | Market loans and grant funding to ENY low-income homeowners for critical repairs | 7 | Housing | HPD | Done with ongoing work | Homeownership represents both a critical source of housing and the largest asset-building opportunity for many New Yorkers, yet many lower income homeowners are struggling to obtain financing and other assistance to maintain their homes. HPD, in collaboration with Enterprise Community Partners, is working to launch HomeFix, a new program to help low- and moderate-income homeowners in small, one- tofour-family properties fund home repairs. The new program will pair financial counseling with affordable low-interest or forgivable loans and leverage the services of community and non-profit partners. The program is expected to launch in 2019. | HPD has loan programs to help low-income homeowners make critical repairs to their buildings so they can resist pressures to raise rents or sell. The Home Improvement Program, for example, offers low-interest loans of up to $30,000 to low-income owner-occupants of a one- to four-family home. The Senior Citizen Home Assistance Program specifically targets low-income seniors. In addition, HPD is currently working with Neighborhood Housing Services (NHS) to disburse $2 million under Project Help, a new program that will target the neediest homeowners across the city who would not be able to finance repairs by other means. NHS will be awarding up to $20,000 per applicant, and the loans will be treated as non-repayable grants that are forgivable if the owner remains in her home for at least 10 years. HPD and NHS will work with CM Espinal to coordinate a marketing strategy specifically targeting East New York residents. Timeline: Spring / Summer 2016 | 2016–ongoing | HPD continues to work with its partners to provide loan programs to help low-income homeowners in East New York maintain ownership and make critical repairs to their buildings. Since April 2016, $109,212 was distributed to four low-income homeowners in Brooklyn Community District 5 through the Senior Citizen Home Assistance Program (SCHAP) and Neighborhood Housing Services (NHS) Revolving Loan Fund to assist with financing repairs. The two low-income senior households in East New York received a total of $58,745 through the SCHAP program to complete roof installation, plumbing repairs, electrical repairs, door and window replacements, basement water penetration fixes, boiler replacement, and other repairs. HPD and its partner NHS worked with Council Member Espinal to coordinate marketing strategies for these loan programs in East New York. Since April 2016, NHS has facilitated four workshops/forums that included 213 participants; provided six presentations to Community Board 5, block/civic associations, and churches; counseled 43 residents at Council Member Inez Barron’s office on foreclosure intervention, insurance, and home repair; and facilitated three seminars/workshops in East New York. NHS initiated a partnership with the East New York Restoration LDC and plans additional outreach in the neighborhood. In addition, HPD, in partnership with the Center for New York City Neighborhoods (the Center), launched the East New York Homeowner Help Desk to connect homeowners to these financial resources (see the next section for details). | HPD has loan programs to help low-income homeowners make critical repairs to their buildings so they can resist pressures to raise rents or sell. The Home Improvement Program, for example, offers low-interest loans of up to $30,000 to low-income owner-occupants of a one- to four-family home. The Senior Citizen Home Assistance Program specifically targets low-income seniors. In addition, HPD is currently working with Neighborhood Housing Services (NHS) and Parodneck to disburse $2 million under Project Help, a new program that will target the neediest homeowners across the city who would not be able to finance repairs by other means. NHS and Parodneck have participated in six events in East New York to inform homeowners about these resources.
East New York | Launch Community Retrofit NYC to boost participation in the Green Housing Preservation Program | 8 | Housing | HPD | Done with ongoing work | Launched in 2016, the Community Retrofit NYC Program engaged owners of 600 buildings and initiated or completed retrofit projects in 543 buildings in Brooklyn and Queens. In East New York, 76 buildings comprising 851 homes were engaged. The Community Retrofit pilot is now complete and will relaunch under a new contract in mid- to late-2019. | HPD's new Green Housing Preservation Program targets small buildings of five to 50 units with low interest loans that will make buildings more energy efficient in exchange for maintaining the affordability of their units. On or around Earth Day, 2016, the City will launch Community Retrofit NYC, a comprehensive outreach and technical assistance campaign specifically targeting East New York and other Brooklyn property owners who could benefit from this new financing tool. Outreach will include community based events with local organizations to promote awareness of the program and canvassing to recruit building owners to participate in the program. Timeline: Late April, 2016, continuing for three years | 2016–2019 | On Earth Day 2016, the Mayor’s Office of Sustainability and HPD launched Community Retrofit NYC to support small and mid-sized multifamily building owners in Central/East Brooklyn and Southern Queens in pursuing energy and water upgrades. The team works with owners of five- to 50-unit buildings through every step of a retrofit process, from identifying opportunities for savings and connecting owners to incentives and financing such as HPD’s Green Housing Preservation Program (GHPP), to helping select a contractor for a project. Since its launch, Community Retrofit NYC has engaged over 300 building owners and initiated or completed retrofits in over 200 buildings citywide. This has reduced greenhouse gas emissions equivalent to taking over 50 cars off the street annually. Of those owners engaged with the program, nearly 40 are building owners in East New York, representing nearly 225 housing units. The Community Retrofit NYC team has met with East New York’s local clergy, community-based organizations such as Cypress Hills Local Development Corporation (LDC) and National Housing Services (NHS) Brooklyn, and elected officials in order to connect with building owners in need of these services. In the coming two years, the program will work with local leaders to hold events, conduct targeted canvassing, and use mailings and newsletters to reach new building owners and help them lower utility costs, reduce greenhouse gas emissions, and preserve affordability through HPD’s GHPP financing. | Since its launch in 2016, the Community Retrofit Program has engaged 847 buildings across 263 property owners, and initiated or completed retrofit projects in 535 buildings. Of those buildings engaged with the program, 44 building owners, across 75 buildings totaling 875 units, are in East New York. Over the past year, the Community Retrofit NYC team has held 5 events in East New York, including a Green Resource Fair in collaboration with East New York Restoration at Spring Creek Park.
East New York | Pilot a Neighborhood Retail Preservation program requiring subsidized new development to include discounted space for local businesses | 9 | Housing | HPD | In Progress | HPD included a requirement that proposals to the Dinsmore-Chestnut RFP set aside space for neighborhood retail businesses. The RFP was released in March 2017 and designated in October 2017 to MHANY Management, the Urban Builders Collaborative, and Cypress Hills Local Development Corporation (CHLDC). HPD is currently working with the development team to incorporate this pilot program. Additionally, HPD is working with the owners of private sites receiving more than $2 million in HPD subsidy to implement this requirement, including the owners of 50 Pennsylvania Avenue, which is under construction now. | In East New York, the City will pilot a program to require developers to set aside space for neighborhood retail businesses in all RFP sites and sites receiving more than $2 million in HPD subsidy with at least 10,000 square feet of ground floor retail space. The amount of space set aside in each individual project would be the lesser of 20% of ground floor retail or 5,000 square feet of total space, and rents would be set initially at 30% below market. In conjunction with a proposed City-wide program to assist local small retailers, SBS will build and maintain a Neighborhood Business Registry from which developers would source tenants. Eligible businesses include independent businesses operating at least two years, and business types may include retail trade, food services, personal services, professional services, and select community facilities (e.g., childcare/pre-K, senior center, health clinic). Building owners will be subject to the terms of the program through the life of the HPD regulatory agreement, which is generally 30 years or more. Timeline: Q2 2016 Program Launch in conjunction with Council Member | 2016–ongoing | In the East New York rezoning area, the City is piloting a program to require developers to set aside space for neighborhood retail businesses in all RFP sites and sites receiving more than $2 million in HPD subsidy with at least 10,000 square feet of ground floor retail space. The amount of retail space set aside in each individual project will be the lesser of 20 percent of ground floor retail or 5,000 square feet of total space, and rents would be set initially at 30 percent below market. HPD issued the Dinsmore-Chestnut RFP to include a requirement for discounted retail space in the ground floor. HPD will continue to work with developers of mixed-use affordable housing projects in the East New York rezoning area to incorporate the requirements of this pilot program into more projects. HPD is developing eligibility criteria for businesses that might be potential tenants for these spaces as they become available. HPD will encourage developers to work with Neighborhood 360° partners in East New York to find businesses interested in becoming tenants. | HPD included a requirement for set aside space for neighborhood retail businesses in the Dinsmore-Chestnut RFP, which was released in March 2017 and designated in October 2017 to joint venture between MHANY Management, the Urban Builders Collaborative, and the Cypress Hills Local Development Corporation (CHLDC). HPD is currently working with the development team to incorporate this pilot program. Additionally, HPD is working with the owners of private sites receiving more than $2 million in HPD subsidy to implement this requirement.
East New York | Publish demographic and housing analyses to evaluated neighborhood change and determine whether policy changes are needed | 10 | Housing | HPD | Done with ongoing work | Every three years, HPD partners with the United States Census Bureau to conduct the New York City Housing and Vacancy Survey (NYCHVS). Since 1965, the NYCHVS has been used to measure the rental vacancy rate and other housing characteristics throughout the city. The 2017 NYCHVS was made publicly available in the Summer of 2018. HPD will use this data to issue a report describing changing demographic characteristics and affordable housing needs in the community. Please click here to see housing and demographic data from the 2017 HVS. | Every three years, as the data become available, HPD's Division of Research and Evaluation will use the Housing and Vacancy Survey to issue a report describing changing demographic characteristics and affordable housing needs in the community. The report will include the following information in comparison to previous years: Household incomes Regulatory status of housing Rental housing costs Property values Housing quality | 2019–ongoing | HPD partners with the United States Census Bureau to conduct the New York City Housing and Vacancy Survey (NYCHVS) every three years. The NYCHVS is used to measure the rental vacancy rate and housing stock for the five boroughs of New York City. Survey data in the NYCHVS include regulatory and homeownership status; unit, building, and neighborhood conditions; rents, utility costs, employment, and income; and much more information about housing and households in New York City. Data collection was recently completed for the 2017 NYCHVS. In 2018, and every three years thereafter, HPD will use the most recent Housing and Vacancy Survey data to describe changing demographic characteristics and affordable housing needs in the community, including comparisons of household incomes, regulatory status of housing, rental housing costs, property values, and housing quality. | Every three years, HPD partners with the United States Census Bureau to conduct the New York City Housing and Vacancy Survey (NYCHVS). Since 1965, the NYCHVS has been used to measure the rental vacancy rate and housing stock for the five boroughs of New York City. 2017 NYCHVS data will be publicly available in the Summer of 2018. HPD will use this data to issue a report describing changing demographic characteristics and affordable housing needs in the community. HPD will release this report by the end of 2018.
East New York | Study the feasibility of a basement legalization pilot program | 11 | Housing | HPD | In Progress | New legislation authorizing code modifications to facilitate basement and cellar apartment conversions in single-family homes in Brooklyn CB 5 was passed by the City Council and signed by the Mayor this spring and will be effective starting in July 2019. HPD has created a Basement Apartment Conversion financing program to help homeowners of one- to three-unit homes undertake renovations. The City selected ENY BASE, a partnership of various community based organizations led by Cypress Hills LDC, to conduct outreach within the community, assess homes for feasibility and eligibility, help homeowners navigate the approvals necessary to undertake the renovations, and access HPD and other financial assistance. HPD and ENY BASE are currently conducting outreach to homeowners and performing feasibility assessments to determine eligibility. Upon completion of this phase this summer, HPD expects approximately 40 homeowners to move into the application and pre-development phase. | "The City will convene a working group with Council Member Espinal, community stakeholders, other elected officials, DOB, FDNY, HPD, and DCP to study barriers related to legalizing basement units in East New York (including such factors as the housing maintenance code, building code, multiple dwelling law and other legal constraints, building parameters, costs, and protections for existing tenants). There are approximately 1,800 single- and two-family buildings located in the East New York rezoning area, a unknown fraction of which have illegal basement apartments. The City will commit $12 million in funding to support conversions if the working group recommends actions that allow such funds to be used, with the appropriate form of the funding support to be determined by HPD. If HPD, in consultation with working group, determines funds cannot be used for this purpose they will be redirected to other weatherization or small home repair programs for 2-4 family homeowners in the East New York rezoning area in consultation with the Council Member. Expense Funding: $12 million Timeline: Working group to convene Summer 2016" (East New York Neighborhood Plan, 4/14/16) "Unleashes capacity through the basement apartment program pilot in East New York for $2.4 million in FY19." (FY 2019 Preliminary Budget) | 2016–ongoing | A multi-agency working group, including HPD, the NYC Department of Buildings (DOB), the NYC Fire Department (FDNY), and the NYC Department of City Planning (DCP), working with Council Member Espinal and multiple community-based organizations in East New York, began meeting in the Summer 2016 to study the feasibility of a basement legalization pilot program in East New York. This working group is supplementing the feasibility analysis by conducting targeted meetings with community groups, experts, and City staff. As a result of the working group’s efforts to date, the City now has several data products that aid in the feasibility analysis. Based on analysis from DCP, the City has identified properties where the existing zoning would allow for an additional dwelling unit. In addition, the community partners provided sample data on homeowner demographics and the physical housing stock by surveying homeowners and producing schematics of their basements and cellars. The interagency working group is using these schematics as examples for potential legal conversions and to better understand the real-world regulatory and financial barriers of legalizing these units. Over the coming months, the working group will continue to identify barriers, propose solutions, and assess the feasibility of the program. Recommendations are anticipated to be issued at the end of Summer 2017. | The basement legalization working group with Council Member Espinal and community-based organizations officially recommended launching the Basement Legalization pilot program and the City committed to funding the pilot. Pending passage of City Council legislation, the City expects to launch the pilot by the end of 2018.
East New York | Support local organizations in effort to establish a Cease and Desist Zone to protect homeowners from unwanted solicitation | 12 | Housing | HPD | In Progress | HPD supports local efforts to persuade the New York State Department of State (NYSDOS) to establish a Cease and Desist Zone in East New York. As background, NYSDOS is authorized to designate a neighborhood as a Cease and Desist Zone in order to protect enrolled homeowners from aggressive solicitations from real estate brokers and salespersons. At the request of the Coalition for Community Advancement, State Senators Martin M. Dilan and Roxanne Persaud jointly sent a letter to the NYS Secretary of State requesting that Brooklyn CD 5 be designated as a Cease and Desist Zone. The Coalition for Community Advancement will be conducting a community-wide campaign to collect evidence of homeowner harassment to provide to the NYSDOS, which requested evidence before initiating formal proceedings. Homeowners can drop off examples of mail solicitations at the offices of United Community Centers of East New York and Cypress Hills LDC and/or can use a homeowner harassment log to report when they have been called, visited in person, or received text messages. | Homeowners in a Cease and Desist Zone can notify the relevant government agency that they no longer wish to receive mailings, phone calls, and in-person visits about selling their homes from real estate brokers and other individuals. The City will partner with Council Member Espinal and the Center for NYC Neighborhoods to explore the feasibility of implementing this strategy in East New York. Timeline: Stakeholder convening Spring/Summer 2016 | 2016–ongoing | HPD is actively supporting local efforts to persuade the New York State Department of State (NYSDOS) to establish a Cease and Desist Zone in East New York. As background, NYSDOS is authorized to designate a neighborhood as a Cease and Desist Zone in order to protect enrolled homeowners from aggressive solicitations from real estate brokers and salespersons. At the request of the Coalition for Community Advancement, State Senators Martin M. Dilan and Roxanne Persaud jointly sent a letter to the NYS Secretary of State requesting that Brooklyn Community District 5 be designated as a Cease and Desist Zone. The Coalition for Community Advancement will be conducting a community-wide campaign to collect evidence of homeowner harassment to provide to the NYSDOS which requested evidence before initiating formal proceedings. Homeowners can drop off examples of mail solicitations at the offices of United Community Centers of East New York and Cypress Hills LDC, and/or can use a homeowner harassment log to report when they have been called, visited in person or received text messages. HPD has offered to support with supplementary outreach to help collect evidence, expert testimony at public hearings to establish the zone, and assistance in educating homeowners about the zone and how to sign up for the do-not-call list if and when it is approved. | HPD supports local efforts to persuade the New York State Department of State (NYSDOS) to establish a Cease and Desist Zone in East New York. As background, NYSDOS is authorized to designate a neighborhood as a Cease and Desist Zone in order to protect enrolled homeowners from aggressive solicitations from real estate brokers and salespersons. At the request of the Coalition for Community Advancement, State Senators Martin M. Dilan and Roxanne Persaud jointly sent a letter to the NYS Secretary of State requesting that Brooklyn Community District 5 be designated as a Cease and Desist Zone. The Coalition for Community Advancement will be conducting a community-wide campaign to collect evidence of homeowner harassment to provide to the NYSDOS which requested evidence before initiating formal proceedings. Homeowners can drop off examples of mail solicitations at the offices of United Community Centers of East New York and Cypress Hills LDC, and/or can use a homeowner harassment log to report when they have been called, visited in person or received text messages.
East New York | Continue to proactively engage tenants to report housing quality issues | 13 | Housing | PEU | Done with ongoing work | Tenant Support Unit (TSU) specialists are on the ground in East New York, conducting proactive outreach to tenants to inform them of their rights, identify housing-related issues faced by members of the community and connect tenants to free City services, like legal assistance, to mitigate displacement, landlord harassment and facilitate home-related repairs. To date, specialists, who speak multiple languages and are often from the community in which they work, have knocked on over 22,680 doors in the area. TSU has also made over 10,450 follow up calls to provide comprehensive case management to tenants – bridging the gap between the City and tenants by helping them through the process of accessing resources. From July 2015 through April 2019, TSU specialists have assisted over 1,730 New Yorkers in zip codes 11207 and 11208. | The City's new Tenant Support Unit (TSU) has been going door-to-door in East New York informing tenants of their rights, documenting building violations, soliciting complaints related to harassment and eviction, and making referrals to free legal support whenever necessary. Since June 2015, the TSU has knocked on 9,425 doors and made contact with 3,460 tenants in East New York. Citywide, the Unit has identified 2,400 New Yorkers that needed help. Of those cases, 1,000 have been resolved so far, and agencies and legal service providers are addressing the remainder. | 2015–ongoing | Between July 2015 and April 2017, the City’s Tenant Support Unit (TSU) specialists knocked on 16,414 doors and opened 533 cases in East New York.* As part of their efforts in East New York, specialists made 5,688 case management calls and closed 397 cases. Cases involve repairs, assistance applying for NYC Rent Freeze programs and HRA’s emergency assistance (rent arrears), and referrals to legal service providers that keep East New York tenants in their homes. Through its targeted engagement efforts and individualized case management approach, TSU assisted a total of 1,270 tenants in East New York. TSU, which is part of the the Mayor’s Public Engagement Unit (PEU), helps low-income New Yorkers across the City stay in their homes, with a focus on tenants in neighborhoods undergoing rezoning. The unit partners closely with elected officials, community-based organizations, and City agencies to directly engage communities across all five boroughs. TSU outreach specialists go door-to-door informing tenants of their rights, identifying any housing-related issues, and connecting tenants with a range of resources including free anti-eviction legal assistance. *East New York defined as zip codes 11207 and 11208 | Tenant Support Unit (TSU) specialists are on the ground in East New York, conducting proactive outreach to tenants to inform them of their rights, identify housing-related issues and connect tenants to free City services, like legal assistance, to mitigate displacement, landlord harassment and facilitate home-related repairs. To date, specialists, who collectively speak over 12 languages, have knocked on over 19,800 doors in the area. TSU has also made over 8,240 follow up calls to provide comprehensive case management to tenants – bridging the gap between the City and tenants by helping them through the process of accessing resources. From July 2015 through mid-May 2018, TSU specialists have assisted over 1,447 New Yorkers in zip codes 11207 and 11208.
East New York | Continue to identify and remediate housing quality issues | 14 | Housing | HPD | Done with ongoing work | HPD's Office of Enforcement and Neighborhood Services (OENS) responds to resident complaints and referrals to identify and remediate problems with the quality or safety of buildings. In FY 2018, OENS conducted 13,870 inspections in East New York, issued 19,586 violations, and worked with owners to remediate 18,191 violations. The agency also spent nearly $2.5 million in emergency repair work. | HPD's Office of Enforcement and Neighborhood Services (OENS) responds to resident complaints and referrals to identify and remediate problems with the quality or safety of buildings. In fiscal year 2014, OENS conducted 20,900 inspections in East New York, issued 12,700 violations, and worked with owners to remediate 11,242 violations. The agency spent more than $1.5 million in emergency repair work. Seven buildings in East New York successfully completed the Underlying Conditions Program, which addresses the root causes of water leaks and mold. HPD's Housing Litigation Division is currently involved in 150 Housing Court cases, including 29 comprehensive cases, in East New York. | Ongoing | HPD’s Office of Enforcement and Neighborhood Services (OENS) responds to resident complaints and referrals in East New York to identify and remediate problems with the quality or safety of buildings. From July 2016 through March 2017 in Brooklyn Community District 5, OENS conducted 17,717 inspections, issued 13,314 violations, and worked with owners to remedy 11,357 violations. HPD spent nearly $650,000 in emergency repair work, which was subsequently billed to the building owners. There are also 64 area buildings in HPD’s Alternative Enforcement Program, which identifies the 250 most distressed multiple dwellings citywide each year. Through the program, HPD has spent $200,000 making repairs and replacing building systems in Brooklyn Community District 5 between July 2016 and March 2017. Additionally, HPD’s Housing Litigation Division is currently involved in 318 Housing Court cases in the area, including 57 comprehensive cases brought by HPD to enforce compliance with housing quality standards. | HPD's Office of Enforcement and Neighborhood Services (OENS) responds to resident complaints and referrals to identify and remediate problems with the quality or safety of buildings. In Fiscal 2017, OENS conducted 14,980 inspections in East New York, issued 18,773 violations, and worked with owners to remediate 15,598 violations. The agency also spent nearly $1.5 million in emergency repair work.
East New York | Expand local hiring incentives in HPD-financed developments | 15 | Economic Development | HPD | Done with ongoing work | In all HPD RFPs for the development of City-owned property, respondents must demonstrate a plan for outreach to residents of the local community district related to employment opportunities generated by the proposed project. The Dinsmore-Chestnut and Grant Avenue Muni Lot RFPs have been released in East New York, both of which were subject to these requirements. | HPD will include the following language in all future Requests for Proposals: "15% of the granted points for the category "Developer Track Record and Capacity" will be awarded to Applicants who demonstrate a plan for outreach to residents of the Community District within which the proposed project is located related to employment opportunities generated by the proposed project. Said outreach may be demonstrated by activities including, but not limited to, training programs, job placement activities, Applicants' own staffing practices, and/or Applicants' contracting practices on the proposed project. Applicants will be required to comply with their outreach plans and will be required to regularly report on their outreach activities." Timeline: All RFPs issued after the date of this agreement. | 2016–ongoing | In Spring 2016, HPD RFPs for the development of City-owned properties began requiring respondents to demonstrate a plan for outreach to residents of the local community district related to employment opportunities generated by the proposed project. Outreach may include training programs, job placement activities, the applicants’ own staffing practices, and/or the applicants’ contracting practices on the proposed project. Applicants will be required to comply with their outreach plans and report regularly on outreach activities. HPD included this language in the East New York Dinsmore-Chestnut RFP and will use the outreach plan requirement as one of the criteria to evaluate proposals. | In all HPD RFPs for the development of City-owned property, respondents must demonstrate a plan for outreach to residents of the local community district related to employment opportunities generated by the proposed project. The Dinsmore-Chestnut and Grant Avenue Muni Lot RFPs have been released in East New York, both of which were subject to these requirements.
East New York | Continue to provide free legal representation to tenants experiencing harassment | 15 | Housing | HRA | Done with ongoing work | Between March 2015 and April 2019, the City provided free legal assistance to 5,026 households in East New York, including over 14,095 individuals of which 5,956 were children. Undocumented families are also able to access these services and the City's Tenant Support Unit continues to canvass the neighborhood to ensure that residents are aware of these services. As part of the City's efforts to reduce unlawful evictions and prevent displacement, the Fiscal Year 2020 Executive Budget includes a total of $127 million for anti-eviction and anti-harassment tenant legal services. As part of its commitment to provide universal access to counsel for tenants facing eviction in Housing Court, the City will fund legal services in East New York. Universal Access will represent $166 million citywide commitment at full implementation in 2022, ensuring free legal representation for low-income tenants and free legal counseling for those who earn more. | The City has committed $36 million for free legal representation in housing court to any tenant in a rezoned neighborhood facing harassment. In East New York, between March and October 2015, this legal funding has already served 90 buildings totaling approximately 870 households. Undocumented families are also able to access these services, and the City's Tenant Support Unit continues to canvass the neighborhood to ensure that residents are aware of these services. The Administration commits to funding this work in East New York for no less than five years to ensure that adequate legal resources are in place. The Administration helped to create an interagency, multi-jurisdictional Tenant Harassment Prevention Task Force to investigate and bring enforcement actions - including criminal charges - against landlords who harass tenants in East New York and other neighborhoods. The Task Force addresses complaints and uses data analysis to identify landlords who use a variety of tactics, including disruptive and dangerous renovation and construction projects, to force tenants into vacating rent-regulated apartments. HPD will work with Tenant Harassment Task Force to take action against landlords who harass tenants. | 2015–ongoing | Between March 2015 and April 2017, the City provided free legal assistance to 1,958 households in East New York.* Undocumented families are also able to access these services, and the City’s Tenant Support Unit continues to canvass the neighborhood to ensure that residents are aware of these services. As part of its commitment to provide universal access to legal help for tenants facing eviction in Housing Court, the City will fund legal assistance in East New York for no less than five years to ensure that adequate legal resources are in place. As part of the City’s efforts to reduce unlawful evictions and prevent displacement, the FY18 Executive Budget includes a total of $77 million for anti-eviction and anti-harassment tenant legal services. This baseline funding includes $36 million for free legal assistance for low-income tenants in rezoned neighborhoods facing eviction or harassment and $41 million for anti-eviction legal services citywide. In February 2017, the Mayor and Council Speaker committed to fund universal access to eviction defense services for tenants in Housing Court, to be implemented over five years starting in July 2017. The FY18 Executive Budget’s $41 million for anti-eviction legal services citywide includes $15 million for the first phase of the universal access to counsel program. The interagency, multi-jurisdictional Tenant Harassment Task Force continues to investigate and bring enforcement actions—including criminal charges—against landlords who harass tenants. To submit harassment complaints, email the Task Force at thpt@hpd.nyc.gov and include relevant building information, including address, owner, and details of harassment. *East New York defined as zip codes 11207 and 11208 | Between March 2015 and April 2018, the City provided free legal assistance to 3,490 households in East New York, including over 10,000 individuals of which 4,442 were children. Undocumented families are also able to access these services, and the City's Tenant Support Unit continues to canvass the neighborhood to ensure that residents are aware of these services. As part of the City’s efforts to reduce unlawful evictions and prevent displacement, the Fiscal 2019 Executive Budget includes a total of $94 million for anti-eviction and anti-harassment tenant legal services. As part of its commitment to provide universal access to counsel for tenants facing eviction in Housing Court, the City will fund legal services in East New York. Universal Access will represent a $155 million commitment at full implementation in 2022, ensuring free legal representation for low-income tenants and free legal counseling for those who earn more.
East New York | Dedicate rental assistance to help move 500 families out of shelters and into stable, affordable housing | 16 | Housing | HRA | Done with ongoing work | From April 2016 through March 2019, 532 homeless families and individuals displaced from East New York moved into permanent housing with the support of the Living in Communities (LINC), CITYFEPS Rental Supplement (CITYFEPS), and Special Exit and Prevention Supplement (SEPS) rental assistance programs. Of these families and individuals, 98 moved back to East New York with this rental assistance. The City created LINC, CITYFEPS, and SEPS to help homeless families and individuals move from temporary shelters back to their communities by paying part of their rent, The HRA is dedicating resources from these programs to help 500 homeless families and individuals displaced from East New York and living in shelters move back into the neighborhood if they so choose. | The Living in Communities (LINC), CITYFEPS Rent Supplement (CITYFEPS), and Special Exit and Prevention Supplement (SEPS) Rental Assistance programs were created to help homeless families and individuals move from temporary, emergency shelter back to the community as quickly as possible by paying a portion of their rent. The Human Resources Administration (HRA) will dedicate LINC, CITYFEPS and SEPS resources to help 500 homeless families that were displaced from East New York and are currently living in shelter move back into the neighborhood if they so choose. HPD will use best efforts to encourage developers to set aside homeless set-aside units in new affordable housing buildings being built in East New York. Timeline: HRA expects to begin allocating vouchers within 120 days of the memorialization of the ENY plan Expense Funding: 500 vouchers | 2016–ongoing | From April 2016 through March 2017, 206 homeless families and individuals displaced from East New York* moved into permanent housing with the support of the Living in Communities (LINC), CITYFEPS Rent Supplement (CITYFEPS), and Special Exit and Prevention Supplement (SEPS) rental assistance programs. Of these families and individuals, 34 moved back to East New York with this rental assistance. The City created LINC, CITYFEPS, and SEPS to help homeless families and individuals move from temporary shelters back to their communities by paying part of their rent. The NYC Human Resources Administration (HRA) is dedicating resources from these programs to help 500 homeless families and individuals displaced from East New York and living in shelters move back into the neighborhood if they so choose. When taking into consideration all housing assistance programs, including Section 8, NYCHA, NY/NY supportive housing, and enhanced one-shot deals, the number of homeless families and individuals from East New York who moved into permanent housing rises to 533, with 73 having moved back to East New York. HPD continues to incentivize, and in many cases require, developers to set aside units for formerly homeless households in new affordable housing buildings being built in East New York. For example, HPD’s new Our Space Initiative funds the construction of rental units affordable to formerly homeless households who earn less than 30% of the AMI. HPD also recently released revised ELLA and Mix & Match new construction term sheets to ensure that projects financed under these programs include at least 10 percent of units for formerly homeless households. *East New York defined as zip codes 11207 and 11208 | From April 2016 through March 2018, 1,040 homeless families and individuals displaced from East New York moved into permanent housing with the support of the Living in Communities (LINC), CITYFEPS Rent Supplement (CITYFEPS), and Special Exit and Prevention Supplement (SEPS) rental assistance programs. Of these families and individuals, 160 moved back to East New York with this rental assistance. The City created LINC, CITYFEPS, and SEPS to help homeless families and individuals move from temporary shelters back to their communities by paying part of their rent. HRA is dedicating resources from these programs to help 500 homeless families and individuals displaced from East New York and living in shelters move back into the neighborhood if they so choose.
East New York | Transition Hector's Court shelter and shelter units at 1801 Pitkin Ave and 247 Vermont Ave out of operation | 17 | Housing | HRA | Done | In East New York, the City closed the Hector's Court shelter in December 2016 and the cluster shelter units at 1801 Pitkin Avenue and 247 Vermont Avenue in February 2017. | The City will commit to close the Hector's Court shelter in FY 17 and complete the closure of shelter units at 1801 Pitkin Avenue and 247 Vermont Avenue by the end of FY16. HRA and HPD will make every reasonable effort to encourage the owners of Hector's Court, along with the owners of 1801 Pitkin Avenue and 247 Vermont Street to convert all cluster homeless units and shelter units that DHS vacates to affordable housing. Timeline: FY2016 & FY2017 | FY16–FY17* | In East New York, the City closed the Hector’s Court shelter in December 2016 and the cluster shelter units at 1801 Pitkin Avenue and 247 Vermont Avenue in February 2017. The City is working with the New York State Division of Housing and Community Renewal to ensure the former cluster units are registered as rent stabilized, where appropriate. HPD will reach out to the owners of 1801 Pitkin Avenue and 247 Vermont Avenue to let them know about the loans and tax incentives available to improve the quality and physical condition of their properties and keep apartments affordable for existing tenants. | In East New York, the City closed the Hector’s Court shelter in December 2016 and the cluster shelter units at 1801 Pitkin Avenue and 247 Vermont Avenue in February 2017.
East New York | Make improvements to Highland Park with new play equipment, pathways, picnic tables, and landscaping | 18 | Open Space | DPR | In Progress | DPR expects to complete the design of Highland Park Lower Eastern Playground and Comfort Station in summer 2019, complete construction of Highland Park Lower Western Playground in summer 2019, and start construction of Highland Park Pedestrian Paths and Sidewalks by the end of 2019. | $13.1 million will be committed to improvements to Highland Park, potentially including new play equipment, a new spray shower, and expanded landscape areas for the Lower Playground, new paths, picnic tables and grills for the Upper Highland Park BBQ area, connectivity and pathway enhancements throughout the park, including to the children's garden and tennis courts and along Jamaica Avenue, improvements to comfort stations, creation of a dog run, and/or redevelopment of the park's handball courts. Timeline: Lower Playground design to start Spring 2016. Targeted construction start Spring 2018; Other connectivity and programming improvements: Design to start FY2018. Targeted construction start FY2020 Capital Funding: $13.1 million | Lower playground 2016-2019, Upper Highland Park 2018 start | The NYC Department of Parks and Recreation (NYC Parks) is revitalizing Highland Park with new features that make it greener and more inviting. On April 20, 2016, NYC Parks began the design process for the Lower Highland Park Playground with a community listening session at PS 108. Dozens of local residents and students shared their vision for a greener, more innovative playground with space for staging outdoor events. Using this feedback, NYC Parks staff developed a design that includes a unique play space with a spray fountain and performance area. Community Board 5 and the PDC approved the project, and in April 2017 NYC Parks completed the design process. The construction contractor procurement process is underway, and NYC Parks expects construction to begin in mid-2018. In Summer 2017, NYC Parks will start design on a series of improvements to Highland Park’s Jamaica Avenue section, including repurposing the large spray shower area into a formal performance area and reconstructing the comfort station, entry plaza, and playground for children aged two to five. | In April 2018, DPR procured a contractor to renovate the Western Lower Playground to include dynamic play equipment, space for staging outdoor events, and seating areas. Construction will begin in mid-summer 2018 and take approximately 12 months to complete. In November 2017, NYC Parks started the year-long design process for the Highland Park Pedestrian Paths and Sidewalks Reconstruction. These improvements seek to better link the lower and upper portions of Highland Park. In April 2018, NYC Parks began the design process for the Lower Eastern Playground and Comfort Station. The project will reconstruct the playground, spray shower, and comfort station. You can keep tabs on each project here: https://www.nycgovparks.org/planning-and-building/capital-project-tracker
East New York | Convert an asphalt area of City Line Park into a new green recreational space | 19 | Open Space | DPR | In Progress | DPR expects to finish construction of City Line Park in summer 2019. | City Line Park's underused asphalt area will be transformed into a new, one-acre active recreational space. NYC Parks will lead a public design process to re-envision the space as a community resource for active living, which will serve existing needs while also helping to anchor a series of affordable housing developments planned for the eastern portion of Atlantic Avenue. New amenities could include a synthetic turf field, running track, fitness equipment, seating areas, and new shade trees. Timeline: Design to start Spring 2016. Targeted construction start Summer 2018 Capital Funding: $5.2 million | 2016–2019 | NYC Parks is reimagining City Line Park’s underused asphalt area and transforming it into a new one-acre recreational space. On June 8, 2016, NYC Parks began the design process with a community listening session at the Arlington Library, where students from the park’s neighboring Transit Tech Career and Technical Education High School shared their vision for a dynamic athletic area with room to run, skateboard, and work out. With these objectives in mind, NYC Parks designed a park plan that converts asphalt into a fitness hub where local residents can exercise and school sports teams can practice. The design includes a new multipurpose athletic turf field, fitness equipment, and the community’s first skate park, and complements the park’s existing basketball courts, baseball field, and playground. Community Board 5 approved the plan in December 2016, and PDC final approval is expected by end of June 2017. NYC Parks expects to complete the design process in Summer 2017 and then begin contractor procurement, with construction slated to start in mid-2018. | In April 2018, DPR procured a contractor for reconstruction of City Line Park. The project converts the existing asphalt athletic field into a multipurpose active recreation area including a synthetic turf field, skate park, basketball courts, adult fitness equipment, and other amenities. Construction will begin in summer 2018.
East New York | Make upgrades to the playground at NYCHA's Fiorentino Plaza | 20 | Open Space | NYCHA | In Progress | Scope of work at the Fiorentino Plaza development will include work at two of the three play areas and will include the installation of new play equipment with safety surfacing, and a spray shower area. Work will be done at the play areas between buildings 4&5 and 9,10, &11. The construction start date is in July, 2019 and will be over by July, 2020. DSNY managed playground improvements at the play area between building 11, building 12 and building 13 was completed on October 2, 2018. | The scope of work will include the removal and disposal of existing children's play equipment, the leveling of the area and immediate grounds area, the installation of new rubberized safety surfacing, and the installation new customized and colorized children's play equipment. Timeline: Design to start Q1 2017. Targeted construction start Q4 2017 Capital Funding: $500,000 | 2017 start | The New York City Housing Authority (NYCHA) Fiorentino Plaza is comprised of eight four-story buildings along the north side of Pitkin Avenue between Wyona Street and Van Siclen Avenue. The City is planning upgrades to the open space at Fiorentino Plaza, including the installation of new rubberized safety surfacing and new customized children’s play equipment. The project is currently in the planning stage which should be completed by July 2017. Once the planning stage is complete it will likely require an additional 18 to 21 months for construction completion. | NYCHA's Fiorentino Plaza is comprised of eight four-story buildings along the north side of Pitkin Avenue between Wyona Street and Van Siclen Avenue. The City has completed planning for upgrades to the open space at Fiorentino Plaza, including the installation of new rubberized safety surfacing and new customized children’s play equipment. NYCHA recently directed the contractor to begin work and construction will be completed by June 2019.
East New York | Renovate Callahan-Kelly Playground to provide more diverse recreational options | 21 | Open Space | DPR | In Progress | DPR expects to begin construction of Callahan-Kelley Playground in late 2019. | Callahan-Kelly Playground, located adjacent to the transit hub at Broadway Junction, will undergo a major renovation to offer more diverse recreational options for residents of the surrounding neighborhoods of Ocean Hill, Brownsville, East New York and Bushwick. Once scoped, the project is expected to include: the addition of a new comfort station, reconstruction of existing basketball courts, new adult fitness equipment, playground renovation, new seating and landscaping, and potentially a new skate park. Timeline: Design to start in FY2017. Targeted construction start in FY2019 Capital Funding: $18.1 million | FY17–FY20* | NYC Parks is breathing new life into Callahan-Kelly Playground, which is adjacent to Broadway Junction, one of the City’s busiest subway stations. On September 28, 2016, NYC Parks began the design process with a community listening session at PS/IS 155. Neighborhood residents shared their vision for creating a beautiful and dynamic open space that serves people of all generations, including young children, teens, and seniors. The design achieves these objectives through a combination of active and passive elements like adult fitness equipment, a skate park, several new seating areas, and double the amount of children’s play equipment. Community Board 16 approved the design, and PDC approval is pending. NYC Parks is scheduled to complete its park design by Winter 2018 and expects construction to begin in Winter 2019. | In summer 2018, DPR will complete the design process for the Callahan-Kelly Playground reconstruction. This project reconstructs the playground, spray shower, perimeter sidewalks and walls, basketball courts, adult fitness equipment, and sitting areas. In addition, this project will include a new skate park and park entrances. NYC Parks anticipates construction will begin in mid-2019 and take 12-18 months.
East New York | Upgrade handball and basketball courts at Sperandeo Brothers Playground | 22 | Open Space | DPR | Done | DPR completed construction at Sperandeo Brothers Playground in December 2018 and reopened the site to the public. | Reconstruct the handball and basketball courts at Sperandeo Brothers Playground. Timeline: Construction started April 2016. Construction completion anticipated in April 2017. Capital Funding: $400,000 | 2016–2017 | NYC Parks is refurbishing the handball and basketball courts at Sperandeo Brothers Playground, a heavily used park adjacent to Achievement First Apollo Elementary Charter School. NYC Parks expects to complete these upgrades in 2017. | DPR is refurbishing the handball and basketball courts at Sperandeo Brothers Playground and anticipates re-starting construction in June 2018. The work will take approximately six months.
East New York | Create a new community center at 127 Pennsylvania Avenue | 23 | Community Resources | NYPD | In Progress | Public engagement began in spring 2017 with palm cards about the community affairs units to be located within the center. Construction on the community center began in March 2018. NYPD community affairs units began operating out of part of the center in April 2019. The center is anticipated to be completed by fall 2019. The Child Center will begin planning and executing community engagement with Council Member Rafael Espinal and Community Board 5 in spring 2019. Engagement will continue with banner placements on the site, as well as an inaugural Community Outreach Committee meeting including the community and project stakeholders. The NYPD will collaborate on a press plan with the Child Center and other Committee members. Press events will begin summer 2019 and center programming is set to begin fall 2019 | The City-owned building at 127 Pennsylvania Avenue will be converted into a multi-purpose NYPD community center with a variety of recreational, academic and supportive programs for young people. This center will offer a range of programs led by community and police partners such as basketball, volleyball, boxing, dance classes, computer skills and general tutoring, targeting youth between the ages of 12-19. In conjunction with community partners and elected officials, NYPD will lead visioning workshops to help understand programming preferences in summer 2016. The City will invest in a significant interior renovation of the building to accommodate these new uses. Timeline: Programming to begin by Fall 2017 Capital Funding: $10 million for building renovation and fit out | 2016–2017 | The City-owned former courthouse on 127 Pennsylvania Avenue will re-open as the first New York City Police Department (NYPD) Community Center in New York City. In October 2016, NYPD and Council Member Espinal hosted a visioning session with members of the community. Ideas generated from that open house were used to create the RFP for programming vendors, which was published in May 2017. NYPD is looking for vendors who will not only provide quality programming to youth aged 12-19, but will actively engage with the community to ensure that their evolving educational, recreational, and social needs are being met. Ideas for programming included a boxing program, dance classes, sports teams (basketball, soccer, volleyball, etc.), tutoring, career development programs and computer classes.The building is currently going through structural and stylistic renovations. One-third of the space will be used by several divisions of NYPD’s Community Affairs Bureau, whose members are anticipated to move in by Fall 2017. The rest of the facility will be dedicated to the community center. The proposed designs for this space will honor the building’s history, while incorporating comprehensive updates and state-of-the-art technology. Proposed designs have included multiple classrooms, a computer lab and library, two gymnasium spaces, and a fully refurbished dance studio. The building will also include spaces for organizations, such as Community Board 5, to engage with the neighborhood. Due to unforeseen construction delays, development of plans for the community center renovations has taken longer than expected. Final designs are estimated to be completed by the end of Summer 2017. NYPD intends to announce the center’s anticipated opening date by the end of 2017. | The City-owned former courthouse on 127 Pennsylvania Avenue will re-open as the first New York City Policy Department (NYPD) Community Center. The building is currently going through structural and stylistic renovations. Ultimately one-third of the space will be used by NYPD’s Community Affairs bureau while the rest of the facility will be dedicated to the community center. In October 2016, NYPD and Council Member Espinal hosted a visioning session with members of the community, which generated ideas that were used to create the RFP for programming vendors. NYPD Community Affairs moved into its space in April 2018 while construction has begun on the community center component of the project. The City is in the process of selecting a programming vendor and is on schedule to complete and open the community center in 2019.
East New York | Build a new 1,000 seat school | 24 | Community Resources | SCA | In Progress | Construction is underway for the development of a new 1,000 seat school at 3269 Atlantic Avenue, which is located at the Disnmore-Chestnut renewal site within the rezoning area. The school will meet SCA’s Green School Guide for new construction and includes an at-grade playground that will be open to the public during non-school hours. SCA committed to meeting with local stakeholders in District 19 and Councilmember Espinal regarding the design of the school and presented to the CEC before the design was finalized. The school will open in September 2020. | The School Construction Authority (SCA) will build a new 1,000 seat school in District 19, to alleviate school overcrowding and provide for a growing population. The site for this new school is envisioned to be a portion of the Dinsmore-Chestnut Urban Renewal Site within the rezoning area. The school will include an at-grade playground that will be open to the public during non-school hours. The school will meet the SCA's Green Schools guide for new construction. SCA commits to meeting with local stakeholders and the Council Member regarding the design of the school and to keep the community informed. They also will present to the CEC before the design is finalized. Timeline: School is included the FY2015 - FY2019 Capital Plan Capital Funding: $98 million | 2017–2020 | The NYC School Construction Authority (SCA) will construct a new 1,000 seat school in School District 19 to alleviate school overcrowding and support a growing population. The City plans to build the school and schoolyard on part of the Dinsmore-Chestnut development site, a vacant piece of land bounded by Atlantic Avenue, Chestnut Street, and Dinsmore Place. The vision for the site also includes affordable housing, retail space, and community facilities. Community Board 5 and the School District 19 Community Education Council (CEC) hosted a public hearing on January 10, 2017 and a subsequent meeting on February 15, 2017 on the selection of the Dinsmore-Chestnut site for the new school. At these events SCA presented information on the site and answered community questions and concerns, and currently SCA is developing a design for the school. SCA has actively engaged key stakeholders during the design process, sharing its progress with Council Member Espinal on multiple occasions, hosting District 19 superintendent Dr. Thomas McBryde to review the design, and presenting design plans to the District 19 CEC at a public meeting on April 26, 2017. On May 24, 2017, the City Council approved the Dinsmore-Chestnut site for the new school, and in the coming months SCA will complete the design. The new school, which is scheduled to open in September 2020, will have a playground that is open to the public during non-school hours and will meet SCA’s Green Schools Guide for sustainability. | SCA is building a new, 1,000 seat pre-K through 8th grade school at 3269 Atlantic Avenue, which is the Dinsmore-Chestnut redevelopment site. SCA began construction in August 2017. SCA has been in close contact with stakeholders throughout the process including Councilmember Espinal, the District 19 superintendent and CEC, and the local Community Board. The project includes an at grade playground that will be open to the community during non-school hours. This project will meet SCA's Green Schools guide for new construction. The project is on track and anticipated occupancy is September 2020.
East New York | Make improvements to existing school facilities | 25 | Community Resources | SCA | In Progress | As part of the East New York rezoning, 46 projects were created in Brooklyn schools. Twenty were technology purchases and twenty six were construction projects. All technology purchases have been completed and SCA is on track to meet the 2020 commitments with all projects. | The Administration will fund up to $17.45 million in SCA School improvement projects including removal of trailers, to be selected by Councilmember Espinal in consultation with the Administration prior to June 1, 2016. Capital Funding: $17.45 million | 2016–2020 | As part of the East New York Neighborhood Plan, the City will fund improvements to local schools. Council Member Espinal worked with the Administration to create 46 projects in 26 schools. Of all 46 school improvement projects, 26 involve construction and 20 involve technology purchases. Construction projects include library upgrades at PS 155 and William Maxwell Vocational High School, a renovated dance studio at Brooklyn Landmark Elementary School, and auditorium and playground updates at PS 158. SCA will complete the design for 16 of the construction projects by Summer 2017 and expects to begin construction in Fall 2017. The other 10 construction projects require more extensive review and discussion with the schools to ensure that the scopes of these projects are within the allocated budget. SCA is finishing the scoping phase for these projects and will complete all 46 projects by 2020. The City is also working to remove transportable classroom units (TCUs), known as trailers, across the city. In East New York, the City removed one trailer at PS 290 in January 2017 and three trailers at IS 302 in April 2017, and is in the process of removing seven trailers at PS 214. | As part of the East New York rezoning funding, 46 projects were created in Brooklyn schools. Twenty eight are technology projects and SCA will meet its 2020 commitments on all of these projects. Seventeen projects involve construction: Six of these projects are substantially complete, and eight projects are currently in construction and expected to be completed by fall 2018. One project is currently in design, with design to be completed by summer 2018 and the project to be completed by fall 2019. Three remaining projects are on hold due to scope and funding challenges--the Culinary Arts Lab and auditorium upgrade at Lane HS, and the auditorium upgrade at PS 7. The City and SCA are working to address these challenges and move the projects ahead.
East New York | Open new Schoolyards to Playgrounds sites at PS 677 and PS 345 | 26 | Community Resources | SCA | Done | Through the City's Schoolyards-to-Playground program, both PS 677-East Elementary School of Excellence and PS 345-Patrolman Robert Bolden will open for community use after school hours and on weekends. Renovations at PS 345 are completed and include new play equipment and the resurfacing of the play yard to include soft surface pieces for enhanced safety, a new soccer field, new landscaping and benches. | Through the City's Schoolyards-to-Playground program, both PS 677-East Elementary School of Excellence and PS 345-Patrolman Robert Bolden will open for community use after school hours and on weekends. Additionally, part of the play yard at PS 345 will be resurfaced and new play equipment will be installed. Timeline: PS345 play area design to begin in 2017 Capital Funding: $1.3 million | 2017–2018 | The City’s Schoolyards to Playgrounds program renovates schoolyards and opens them to the public. In 2016, through the program, both PS 677-East Elementary School of Excellence and PS 345-Patrolman Robert Bolden opened for community use after school hours and on weekends. Improving access to these schoolyards will help address the open space needs of East New York residents and increase the number of New Yorkers living within walking distance to a park. SCA met with the principal and custodian of PS 345 to discuss and elicit feedback on playground renovation and continues to be in touch with the school about design and construction plans. SCA has completed the design for the school playground, which includes a new asphalt surface with painted games, a new safety surface for play equipment, new benches and trees, a new artificial soccer turf, and new fencing. The school principal has approved the design, and the project has moved into the public procurement process. SCA expects to complete all improvements to the playground in 2018. | SCA has completed the resurfacing and renovation of the PS 345 play yard. A new soccer field has been completed, and new fencing, benches, trees and pavement have been installed. The final component to this work is a new safety surface to be installed underneath the existing play equipment - SCA is waiting for the soft surface pieces to be delivered and expects to install those by the end of June 2018.
East New York | Support the construction of a new child care center in East New York | 27 | Community Resources | ACS | In Progress | Funding was allocated for this project in the capital plan, totaling $4.4 million in Fiscal Year 2021. EDC is awaiting an updated scope of work & budget from the funding recipient (Cypress Hills Local Development Corporation) to move forward with securing approvals needed for implementation. | The Administration will work with the City Council to provide funding for the acquisition and/or renovation of a new childcare center in East New York at 3289 Fulton Street, subject to the project meeting capital eligibility criteria. If this location does not qualify, funding will be allocated for childcare at alternative sites. Capital Funding: $2.8 million; 2.1 million for renovation and $700,000 for acquisition | FY17* | In the Fiscal Year 2017 Executive Budget, the City Council allocated $2.8 million in capital funding for the construction of a new child care center in East New York. The Cypress Hills Child Care Corporation (CCC) has acquired the site at 3289 Fulton Street for the center and is developing the architectural plans. It expects the project bidding process to begin in Summer 2017 and construction to start by the end of 2017. The Cypress Hills CCC anticipates the opening of the child care center by early 2019 and estimates that it will serve about 90 children. | After acquisition of the building intended to house the daycare center, CHCCC’s design team mobilized to complete structural probes and geotechnical investigations. These investigations revealed unforeseen foundation and structural conditions that would require the building to be braced with a secondary steel structure and underpinned along all property walls. The significant costs associated with these unforeseen challenges impacted the design and subsequent construction budget of the Childcare Center project, which necessitated the submission of an additional funding request. Construction anticipated to start Fall 2018 and be complete in 2020, pending budget approval.
East New York | Make Atlantic Avenue safer for pedestrians with a raised, planted median and other improvements | 28 | Transportation & Infrastructure | DOT | In Progress | Atlantic Avenue today functions as a barrier in East New York and has a high number of accidents. DOT is redeveloping this central spine of the neighborhood with a new raised and planted median, curb extensions at 15 intersections, a complete road resurfacing, safer crosswalks, more than 100 new street trees, and new sidewalks with benches and bike racks. This project will advance Vision Zero's goal of increasing pedestrian safety, while supporting more active uses along the Atlantic Avenue corridor. The projects are currently in construction with an anticipated completion this fall 2019. | Atlantic Avenue today functions as a barrier within the neighborhood and has a high number of accidents. DOT will redevelop this central spine of the neighborhood with a new raised, planted median, curb extensions at fifteen intersections, a complete road resurfacing, safer crosswalks, more than 100 new street trees, and new sidewalks with public benches and bike racks. This project will advance Vision Zero for pedestrian safety while supporting more active uses along the Atlantic Avenue corridor. Timeline Currently in design with construction start expected to begin Spring 2017. Anticipated completion in 2019 Capital Funding: $40.8 million (Phase I) | 2016–2019 | In December 2015, DOT presented to Community Board 5 the proposal for Phase 1 of the Atlantic Avenue Great Streets Project, which spans Georgia Avenue to Logan Street. Phase 1 features a new raised and planted median, new curb extensions to create shorter and safer crossings, a complete resurfacing and remarking that includes high-visibility crosswalks, and sidewalks with new street trees, benches, and bike racks. Construction on Phase 1 will begin in late 2017. DOT is currently planning a second phase between Logan Street and Rockaway Boulevard, which it will present to the public later in 2017. Construction on both Phase 1 and Phase 2 is expected to be complete by the end of 2020. Since 2015, DOT has solicited feedback from the community through workshops, on-site surveys, and an online feedback portal. The feedback portal remains open and constituents can continue to share their thoughts here: nycdotfeedbackportals.nyc/atlantic-avenue. | DOT and DDC joined Council Member Espinal to mark the groundbreaking of Atlantic Avenue Phase 1 (between Georgia Ave and Logan St) in May 2018. This work will result in an Atlantic Avenue with a raised and planted median, as well as significant safety improvements to pedestrian crossings and overall streetscape. The overall project is expected to be completed in 2019.
East New York | Resurface portions of Fulton Street and Ridgewood Avenue | 29 | Transportation & Infrastructure | DOT | Done | In Spring 2016, DOT resurfaced Ridgewood Avenue between Jamaica Avenue and Elton Street and between Euclid Avenue and Eldert Lane. In Spring 2017, DOT resurfaced Fulton Street between Essex Street and Hale Street. | Resurface roads along Fulton Street from Essex Street to Hale Street and along Ridgewood Avenue from Jamaica Avenue to Elton Street and from Euclid Avenue to Eldert Lane. Timeline: Ridgewood Avenue resurfacing underway; Fulton Street resurfacing scheduled to begin Spring 2017 Capital Funding: $412,000 | 2016–2017 | In Spring 2016, DOT resurfaced Ridgewood Avenue between Jamaica Avenue and Elton Street and between Euclid Avenue and Eldert Lane. In Spring 2017, DOT resurfaced Fulton Street between Essex Street and Hale Street. | In Spring 2016, DOT resurfaced Ridgewood Avenue between Jamaica Avenue and Elton Street and between Euclid Avenue and Eldert Lane. In Spring 2017, DOT resurfaced Fulton Street between Essex Street and Hale Street.
East New York | Improve connectivity and streetscape in and around the IBZ | 30 | Transportation & Infrastructure | DOT | In Progress | DOT will implement major capital improvements within East New York’s Industrial Business Zone through upgrades to the north-south and east-west corridors of Van Sinderen Avenue between Blake and Atlantic Avenues, and Sutter Avenue. Such improvements may include: new sidewalks, street repaving, new lighting around elevated transit infrastructure, new decorative fencing along city-owned vacant lots and transit infrastructure, and safety improvements at the intersection of Van Sinderen and Sutter. | DOT will implement major capital improvements to the IBZ's physical environment through upgrades to certain north-south and east-west corridors, like Van Sinderen and Sutter Avenues. Such improvements may include: new sidewalks and street repaving; new lighting around elevated transit infrastructure; and new fencing along city-owned vacant lots and transit infrastructure. Timeline: The City will commence a design process on the infrastructure improvements in 2017 in consultation with adjacent property owners, the East Brooklyn BID, and Community Board 5 Capital Funding: $8.2 million | 2017–2020 | DOT will improve lighting and accessibility along Van Sinderen Avenue between East New York Avenue and Sutter Avenue. DOT will also construct safety and accessibility improvements at the intersection of Van Sinderen Avenue and Sutter Avenue, improving the streetscape around the Sutter Avenue L train station. DOT completed scoping the IBZ streetscape project in April 2017 and expects to begin the design process in Summer 2017. In Fall 2017, DOT and NYCEDC will coordinate an outreach effort to various community stakeholders. | EDC is working with DCP and DOT on the overall Broadway Junction area planning study, which includes the IBZ. The project is led by DOT and includes $8.2 million of funding dedicated to streetscape improvements on Van Sinderen Street. DOT will implement major capital improvements within East New York’s Industrial Business Zone through upgrades to the north-south and east-west corridors of Van Sinderen Avenue between Blake and Atlantic Avenues, and Sutter Avenue. Such improvements may include: new sidewalks, street repaving, new lighting around elevated transit infrastructure, new decorative fencing along city-owned vacant lots and transit infrastructure, and safety improvements at the intersection of Van Sinderen and Sutter.
East New York | Install new rain gardens at strategic locations | 31 | Transportation & Infrastructure | DEP | In Progress | DEP completed the geotechnical report of the rezoning area in order to finalize the recommendations for the design and construction of green infrastructure projects in East New York. The completed report will allow the construction of rain gardens and green infrastructure projects to improve the quality of water in Jamaica Bay, management stormwater runoff in East New York and improve local draining in the rezoning area. Construction is expected to begin in 2019. | The Department of Environmental Protection will install new curbside bioswales to absorb and manage storm water in East New York, improving water quality in Jamaica Bay while beautifying streets. Timeline: Two contracts are currently in advertisement for design; construction anticipated to start January 2017 Capital Funding: $21 million | 2019 | The NYC Department of Environmental Protection (DEP) is planning to install bioswales, known as rain gardens, throughout East New York that will green the streets and improve the water quality in Jamaica Bay by absorbing stormwater runoff. These projects are currently in design, and DEP has performed walkthroughs of the area to determine the most effective locations for the rain gardens. DEP has also begun geotechnical investigations, which will dictate the suitability of the green infrastructure at the selected locations. DEP expects to complete design of the rain gardens by the end of 2017 and anticipates construction to begin in 2018. | DEP is committed to expanding green infrastructure in East New York to manage stormwater and improve the quality of water in Jamaica Bay. In summer 2019, DEP will begin installing rain gardens in the rezoning area that will improve street drainage by providing storage and retention for excess stormwater. In addition to building rain gardens within the rezoning footprint for this area, DEP is installing other green infrastructure projects around the area that will improve local draining overall. DEP expects to complete the geotechnical report—the results of the subsoil investigation required for the project—on rain gardens for the rezoning area by early 2019 and to complete the designs in the summer of 2019.
East New York | Upgrade sewer infrastructure at targeted locations | 32 | Transportation & Infrastructure | DEP | In Progress | DEP will complete three projects in the rezoning area in conjunction with DOT upgrades of the same streets. The first two projects are currently in the design phase and include a trunk water main and distribution main replacement along East New York from Howard Street to Pacific Street, with a project cost of $56.3 million. The second project is a sanitary and combined sewer repair estimated to cost of $500,000 along Schenck Avenue and surrounding areas. Phase 1 of the trunk water main, distribution main, sanitary and combined sewer repair project along Atlantic Ave between Georgia Avenue and Fountain Avenue is currently under construction with an estimated cost of $8.7 million. It is scheduled for completion in September 2019. | The Department of Environmental Protection is planning up to $17 million in water main, sewer and distribution main replacement along East New York Avenue between Howard and Pacific, Schenck between Flatlands and Jamaica, Atlantic between Georgia and Conduit, in the rezoning area. Timeline: Anticipated completion of projects ranges from 2018 through 2021 Capital Funding: up to $17 million | 2018–2021 | DEP is undertaking substantial capital projects to upgrade water and sewer infrastructure in East New York. Projects involve the replacement of old unlined cast-iron distribution water mains and old trunk water mains to improve water distribution in the area. DEP’s active projects also include the replacement of distribution water mains and repair of combined sewers on Atlantic Avenue. The contract for the first phase of work on Atlantic Avenue is currently in procurement and construction is expected to begin later in 2017. The rest of the planned work is currently in design at the New York City Department of Design and Construction. | DEP will install fire hydrants and water mains and replace combined sewer infrastructure and catch basins on Atlantic Avenue between Georgia and Fountain Avenues. Construction is estimated to be completed by September 2019, with water main work projected to take place from June 2018 through November 2018. These projects are being undertaken concurrently with DOT upgrades occurring on the same street (project HWD10105). The design is complete and the groundbreaking ceremony for Atlantic Avenue – Phase 1 occurred in May 2018.
East New York | Bring high-speed broadband to residential areas | 33 | Transportation & Infrastructure | MOTI | In Progress | The City is working on a series of initiatives to increase broadband access in underserved areas like East New York. In Q2 2019, the City opened up a reservation phase for mobile telecom installations with an emphasis on locations outside of the core of Manhattan, including East New York. The City is making progress on its investments in affordable broadband from the IBZ to residential areas in East New York. The City issued an RFEI in Q4 2018 and is reviewing solutions informed by the responses to that RFEI. The City plans to identify a procurement approach in partnership with DOITT and EDC in Q3 2019. | Installation of conduit along key corridors in East New York will provide connections to City facilities, enable free public Wi-Fi along Atlantic Avenue and in City Line Park and support deployment of broadband in an area without affordable, reliable high speed internet service. Timeline: Currently in scoping with construction start expected to begin Spring 2017. Anticipated completion in 2019 Capital Funding: $1.7 million | 2016–2019 | The NYC Department of Information Technology and Telecommunications (DoITT) has requested that Cablevision/Altice, pursuant to a requirement in its franchise agreement, bring service to currently unserved non-residential buildings in the East New York IBZ. It is expected that the addition of this infrastructure will improve options for IBZ businesses in search of fast, reliable cable or cable-related services, such as internet and phone. Cablevision/Altice will work with the local business community to identify potential customers and deliver expanded service. It is anticipated that Cablevision/Altice will begin design and construction by the fourth quarter of 2017. | The City is coordinating installation of LinkNYC kiosks to provide free public Wi-Fi along Atlantic Avenue and will make further infrastructure investments that expand from the IBZ to bring affordable, reliable high speed internet service to residential areas. The City will release an RFP/RFEI for a combined IBZ / residential area project in Q1 2019.
East New York | Establish a Workforce1 Career Center in ENY | 34 | Economic Development | SBS | Done | In November 2016, SBS opened a Workforce1 Career Center at 2619 Atlantic Avenue in East New York. SBS worked with more than 14 local community-based organizations to design a custom suite of services to support East New York jobseekers and employers. The East New York Workforce1 Career Center offers a range of services, including intensive interview preparation and individualized career counseling. | SBS will establish a Workforce1 Career Center in Council District 37 in East New York where employers can access free recruitment services to find qualified talent, and jobseekers can receive employment services including job placement, skills training, career advisement and job search counseling. SBS is working with more than 14 local community-based organizations to design a custom suite of services for this new Workforce1 Center to ensure that the services provided will best address the needs of the East New York community. Residents of East New York will also be able to connect to the City's newly expanded HireNYC program through the East New York Workforce1 Center. As one of the largest and most impactful targeted hiring program in the nation, HireNYC will enable the City to leverage its economic development investments to connect more New Yorkers to jobs while helping ensure local businesses find the talent they need. HireNYC now requires that any city contract over $1 million and any housing project receiving $2 million or more in HPD subsidy post open positions with the Workforce1 system and consider qualified candidates, making it easier for local jobseekers to find good jobs. Timeline: Best efforts to open a Workforce 1 Center by summer 2016, but no later than the end of 2016 | 2016 | In November 2016, SBS opened a Workforce1 Career Center at 2619 Atlantic Avenue in East New York. SBS worked with more than 14 local community-based organizations to design a custom suite of services to support East New York jobseekers and employers. The East New York Workforce1 Career Center offers a range of services including intensive interview preparation and individualized career counseling. Since opening its doors, the center has served over 1,750 jobseekers. East New York jobseekers and employers can also access services at any of SBS’s 20 Workforce1 Career Centers located throughout the City. Since June 2016, the Workforce1 Center network has connected more than 400 East New York* residents to jobs citywide. At the East New York Workforce1 Career Center, residents of East New York are also able to connect to the City’s newly expanded HireNYC program. HireNYC will allow the City to leverage its economic development investments to connect more New Yorkers to jobs, while helping local businesses find the talent they need. HireNYC now requires contractors, subcontractors, and developers with a City contract worth at least $1 million or a housing project that receives at least $2 million in HPD subsidy post open positions through the Workforce1 system and consider qualified candidates, making it easier for local jobseekers to find good jobs. *East New York defined as zip codes 11207 and 11208 | In November 2016, SBS opened a Workforce1 Career Center at 2619 Atlantic Avenue in East New York. SBS worked with more than 14 local community-based organizations to design a custom suite of services to support East New York jobseekers and employers. The East New York Workforce1 Career Center offers a range of services, including intensive interview preparation and individualized career counseling. Since opening its doors, the center has served over 3,000 jobseekers. East New York jobseekers and employers can also access services at any of SBS’s 21 Workforce1 Career Centers located throughout the city.
East New York | Launch an East New York-based business training course | 36 | Economic Development | SBS | Done | In March 2016, SBS launched a FastTrac GrowthVenture business course in East New York to help neighborhood business owners strategically grow their businesses and adapt to changes in the market. With support from the Cypress Hills LDC, this free comprehensive business development program was customized for East New York to help local businesses access capital, identify growth opportunities, build sales strategies, improve financial performance, and adapt to changing markets. | In March 2016, SBS launched its first FastTrac GrowthVenture business course in East New York to help neighborhood business owners strategically grow their businesses and adapt to changes in the market. With support from the Cypress Hills LDC, this free comprehensive business development program is customized for East New York to help local businesses access capital, identify growth opportunities, build sales strategies, improve financial performance, and adapt to changing markets. Timeline: Ongoing | 2016–ongoing | In March 2016, SBS launched its first FastTrac GrowthVenture business course in East New York to help neighborhood business owners strategically sustain and grow their businesses. Created with support from the Cypress Hills LDC, this free eight-week business development program is designed to help East New York businesses access capital, identify growth opportunities, build sales strategies, improve financial performance, and adapt to changes in the market. Participants can focus either on improving their existing businesses or cultivating their ideas for a new business. The course consists of sessions facilitated by certified professors who run their own businesses, and includes small-group exercises, expert guest speakers, and business coaching and mentoring. There were 10 participants in the first course. In addition to this course, SBS held three workshops in East New York on topics including commercial landlord harassment, going digital, and marketing 101. | In March 2016, SBS launched its first FastTrac GrowthVenture business course in East New York to help neighborhood business owners strategically grow their businesses and adapt to changes in the market. With support from the Cypress Hills LDC, this free comprehensive business development program was customized for East New York to help local businesses access capital, identify growth opportunities, build sales strategies, improve financial performance, and adapt to changing markets.
East New York | Increase bidding opportunities for local IBZ businesses in upcoming local real estate projects | 37 | Economic Development | EDC | Done | As part of the new marketing campaign created for the East Brooklyn BID, EDC developed unique material to promote upcoming "Meet the Developer" events. | With existing companies in the IBZ specializing in construction trades and materials, there is potential for synergy between the ENY IBZ and anticipated construction activity. NYCEDC will work with local organizations and developers to support "Meet the Developer" events to facilitate awareness of the services and skills available in the IBZ Timeline: Commencing by the end of 2016 | 2016–ongoing | In Summer 2016, The NYC Economic Development Corporation (NYCEDC) attended a “Meet the Developer” event sponsored by the LDC of East New York to provide information on NYCEDC’s robust programs, such as ConstructNYC, to support small, local contractors and subcontractors that are M/W/DBE certified. Through the East New York IBZ Marketing Campaign, NYCEDC is developing new marketing and advertising materials for future “Meet the Developer” events to be used by the LDC of East New York. NYCEDC will also make good faith efforts to procure local East New York IBZ and M/W/DBE subcontractors to complete the $6 million renovation of the East New York industrial building. | NYC Economic Development Corp. (NYCEDC) has partnered with East Brooklyn BID to organize several “Meet the Developer” events and will continue to plan them on an ongoing basis as new projects move forward in the IBZ.
East New York | Expand opportunities for Minority and Women-owned Businesses (M/WBEs) in the Affordable Housing Development Industry | 38 | Economic Development | HPD | Done with ongoing work | HPD has services and programs to support M/WBEs and create a pathway for smaller businesses to build capacity. The M/WBE Build Up Program requires development projects receiving $2 million or more in City contribution to utilize M/WBE construction or professional firms. In addition, under HNY, 15 out of 74 public site designations went to M/WBEs, six of which were through HPD's M/WBE RFP. 461 Alabama Ave in East New York was awarded to CB Emmanuel Realty through this RFP, who will develop the vacant site into supportive housing with 55 apartments for formerly homeless and low-income households. Lastly, in 2019, HPD began year four of its Developer Capacity Building Program, which provides courses and networking opportunities to M/WBE developers. | HPD will encourage affordable housing developers in East New York to employ M/WBE contractors and professional service firms. HPD will continue to work to build the capacity of M/WBE developers through professional development, networking, and mentoring programs, improve access to capital for M/WBE developers with low-cost financing options for site acquisition and predevelopment costs, and enhance the ability of M/WBE developers to compete more effectively for HPD support by providing targeted new construction and preservation opportunities. | 2016–ongoing | HPD aims to increase opportunities for M/WBEs to develop affordable housing by providing targeted opportunities to M/WBE firms, encouraging use of M/WBE contractor and sub-contractors, helping build capacity of M/WBE developers, and improving access to capital. As part of these efforts, HPD launched the M/WBE Building Opportunity RFP and designated six sites to M/WBE developers citywide. One of these sites is located in East New York at 461 Alabama Avenue. The project was awarded to CB Emmanuel Realty, which will develop the vacant site into approximately 69 units of affordable housing for low-income and formerly homeless households. HPD’s new M/WBE Build Up Program requires developers of projects closing after April 1, 2017, to which HPD/HDC contributes $2 million or more in subsidy, to spend at least a quarter of all HPD/HDC-supported costs on certified M/WBE construction, design, or professional service firms. HPD’s Building Capacity Workshop series introduces M/WBE and nonprofit developers to best practices in affordable housing development from site selection and project financing to construction and property management. Sabaoth Group, Inc. is an M/WBE developer based in East New York participating in the program. HPD is working to improve access to capital for M/WBE developers by providing low-cost financing options for site acquisition and predevelopment costs through the New York City Acquisition Fund, which offers flexible bridge loans for the purchase of vacant sites or occupied buildings, predevelopment, and moderate rehabilitation to developers committed to creating or preserving affordable housing. | HPD has nearly met or exceeded all M/WBE utilization goals in our breakout categories by type of service and expanded services/programs to support M/WBEs. HPD RFPs now give preference for local community experience and a pathway for smaller businesses to build up capacity. The M/WBE Build Up Program requirements now apply to 42 projects, expected to generate over $177M in spending to MWBE vendors. Twelve out of 53 public site designations went to M/WBEs, 6 of whom were through the our M/WBE RFP. 461 Alabama Ave, in East New York, was awarded to CB Emmanuel Realty through this RFP, who will develop the vacant site into supportive housing with 55 units for formerly homeless and low-income households.HPD also completed year 3 of its Developer Capacity Building Program which provides courses and networking opportunities to M/WBE developers.
East New York | Provide support to small businesses with commercial lease negotiations | 39 | Economic Development | SBS | Done with ongoing work | Beginning in 2016, SBS provides free commercial lease workshops and clinics to local business owners in East New York in partnership with the LDC of East New York, the East New York Restoration LDC, and the Brooklyn Public Library. SBS also recently launched our Commercial Lease Assistance Program, which provides eligible businesses with pro-bono legal services to address commercial lease issues prior to litigation. Through the program, our legal service providers continue to be available to assist small businesses with lease-related matters in the areas of signing a new lease; renewing, amending or terminating an existing lease; or resolving other commercial lease-related issues, such as landlord harassment or bad conditions. | SBS will provide free commercial lease workshops and clinics to local business owners and is partnering with the East New York Restoration LDC and Brooklyn Public Library. Timeline: Spring/Summer 2016 | 2016–ongoing | In 2016, SBS began providing free commercial lease workshops and clinics to local business owners in East New York in partnership with the LDC of East New York, the East New York Restoration LDC, and the Brooklyn Public Library. These sessions help prepare business owners to enter the lease negotiation process by reviewing the components of commercial leases and sharing strategies for reaching a fair agreement. After gaining a better understanding of lease negotiations, businesses in the process of signing a lease can use SBS’s Legal Assistance services. In East New York, SBS has held four courses that engaged a total of 39 participants. | In 2016, SBS began providing free commercial lease workshops and clinics to local business owners in East New York in partnership with the LDC of East New York, the East New York Restoration LDC, and the Brooklyn Public Library. These sessions help prepare business owners to enter the lease negotiation process by reviewing the components of commercial leases and sharing strategies for reaching a fair agreement. SBS has held four courses in East New York to date. SBS also recently launched our Commercial Lease Assistance Program, which provides eligible businesses with pro-bono legal services to address commercial lease issues prior to litigation. Through the program, our legal service providers are available to assist small businesses with lease-related matters in the areas of signing a new lease; renewing, amending or terminating an existing lease; or resolving other commercial lease-related issues, such as landlord harassment or bad conditions.
East New York | Conduct a commercial district needs assessment of ENY retail corridors | 40 | Economic Development | SBS | Done | SBS worked in partnership with the Cypress Hills LCD, the LDC of East New York, and the Highland Park CDC to conduct a Commercial District Needs Assessment (CDNA) of the Fulton, Atlantic, Liberty, and Pitkin Avenue corridors. A CDNA is a tool aimed at helping community organizations gain an in-depth and comprehensive understanding of the current strengths, needs, challenges, and opportunities of neighborhood commercial corridors. The East New York CDNA was published in October 2016 and highlights the neighborhood’s business landscape, consumer characteristics, physical environment, and demographic data, and informed the subsequent Neighborhood 360 programming. The full report can be found at www.nyc.gov/neighborhood360. | SBS is currently working in partnership with the Cypress Hills Local Development Corporation, the Local Development Corporation of East New York, and Highland Park Community Development Corporation to conduct a Commercial District Needs Assessment (CDNA) of the Fulton, Atlantic, Liberty, and Pitkin Avenue commercial corridors. CDNA includes analysis of community capacity, physical environment, business environment, and market and demographic data to help SBS and its partners better understand the needs of local commercial corridors and develop ground-up recommendations to foster a healthy local retail mix. The results of this assessment will be published later this year in the form of an East New York commercial district profile coproduced by East New York partner organizations. Following results from the commercial district needs assessment, SBS will develop a work plan with local stakeholders to align SBS, City, and community resources with the needs of the East New York's commercial corridors. (....) Timeline: CDNA completion and competitive funding to local groups in Summer 2016 Please see notes for full details | 2016 | The NYC Department of Small Business Services (SBS) worked in partnership with the Cypress Hills LDC, the LDC of East New York, and the Highland Park CDC to conduct a Neighborhood 360° Commercial District Needs Assessment (CDNA) of the Fulton Street, Atlantic Avenue, Liberty Avenue, and Pitkin Avenue commercial corridors. The CDNA, conducted between December 2015 and May 2016, highlights East New York’s business landscape and consumer characteristics to help SBS and its partners better understand the needs of local commercial corridors. In October 2016, SBS published the results of the assessment, which can be found at nyc.gov/neighborhood360. The results, based on 239 surveys and various stakeholder meetings with neighborhood merchants, shoppers, workers, property owners, and residents, provide insight into existing conditions, business data, and opportunities for improvement. The CDNA will help SBS determine how it prioritizes local investments and serve as an informational and marketing resource for the neighborhood. Its findings informed how SBS awarded competitive Neighborhood 360° grant funding to nonprofits for commerical revitalization services in East New York. | SBS worked in partnership with the Cypress Hills LDC, the LDC of East New York, and the Highland Park CDC to conduct a Commercial District Needs Assessment (CDNA) of the Fulton, Atlantic, Liberty, and Pitkin Avenue corridors. A CDNA is a tool aimed at helping SBS and our local partners gain an in-depth and comprehensive understanding of the current strengths, needs, challenges, and opportunities of neighborhood commercial corridors. The East New York CDNA, published in October 2016, highlights the neighborhood’s business landscape, consumer characteristics, physical environment, and demographic data. The information identified in the CDNA informed how SBS awarded the competitive Neighborhood 360 grant funding for East New York non-profits to develop customized commercial revitalization initiatives. The full report can be found at www.nyc.gov/neighborhood360.
East New York | Complete streetscape enhancement projects along commercial corridors | 41 | Economic Development | SBS | Done with ongoing work | To create a more inviting environment for local businesses and the people they serve, a portion of SBS’s Neighborhood 360 grant funding in East New York focuses on streetscape enhancements. Streetscape improvements will include new sidewalk planters and signage that will be installed in tree pits on Liberty Avenue by the end of Fiscal Year 2019, district-wide banners will begin installation in Fiscal Year 2019, and 62 upgraded garbage bins have been placed on various corners along Fulton Street and Liberty Avenue to help keep the corridor clean. | Statement from Source: Capital funding will be made available for streetscape enhancement projects that could include additional street lighting, benches, bike racks, street trees and planters, improved sanitation and corner garbage bins, wayfinding, identity banners and other placemaking initiatives developed by local stakeholders. Capital Funding: $500k | 2016–ongoing | A portion of Neighborhood 360° grant funding to the Cypress Hills LDC and the LDC of East New York will cover streetscape enhancements that create a cleaner, more inviting environment for local businesses and the people they serve. These upgrades, which will be completed between 2017 and 2020, will include improved sanitation, new sidewalk planters and garbage bins, and banners and neighborhood events that promote small businesses. SBS will use the East New York CDNA and input from Neighborhood 360° grantees to guide additional streetscape improvements for neighborhood commercial corridors. | To create a cleaner, more inviting environment for local businesses and the people they serve, a portion of SBS’s Neighborhood 360 grant funding in East New York will focus on streetscape enhancements. These upgrades, which will be completed between 2018 and 2020, will include supplemental sanitation services, new sidewalk planters, garbage bins, district banners, and neighborhood events that promote local small businesses. So far, 62 upgraded garbage bins have been placed on various corners along Fulton Street and Liberty Avenue to help keep the corridor clean.
East New York | Award competitive funding to nonprofits for commercial revitalization services | 42 | Economic Development | SBS | Done with ongoing work | In January 2017, SBS awarded the Cypress Hills LDC and the LDC of East New York approximately $1.4 million in Neighborhood 360° grant funding to implement commercial revitalization projects in East New York over three years. | SBS will award competitive funding to nonprofits to deliver commercial revitalization services to East New York...Expense Funding: $300,000 (SBS) | 2016–2020 | SBS launched Neighborhood 360° Grants to support projects that strengthen and revitalize streets, small businesses, and community-based organizations. Neighborhood 360° Grants will help organizations execute high-quality commercial revitalization projects by providing dedicated funding for personnel and programming. In March 2017, SBS announced recipients of Neighborhood 360° grants. The Cypress Hills LDC and the LDC of East New York received $1.47 million in funding to implement commercial revitalization projects in East New York over three years. Year one projects will include street cleaning services, banner and planter installations, business support workshops, shop local events, merchant organizing, cultural programming, and other quality-of-life enhancements. In addition to receiving Neighborhood 360° grant funding, the Cypress Hills LDC was awarded a NYC Commercial Corridor Challenge grant from Local Initiatives Support Coalition and Citi Community Development to make further early-action improvements to Fulton Street’s businesses and streetscape. | In January 2017, SBS awarded the Cypress Hills LDC and the LDC of East New York $1.47 million in Neighborhood 360° grant funding to implement commercial revitalization projects in East New York over three years. Over the first year, this funding supported supplemental sanitation services, business support workshops, merchant organizing support, cultural programming, and other quality of life enhancements. In addition to receiving Neighborhood 360° grant funding, the Cypress Hills LDC was awarded a NYC Commercial Corridor Challenge grant from Local Initiatives Support Coalition (LISC NYC) and Citi Community Development to implement early-action storefront improvements on businesses along the Fulton Street corridor.
East New York | Renovate the City-owned industrial building to create modern industrial space for six industrial companies | 43 | Economic Development | EDC | In Progress | Construction has commenced and is anticipated to be complete by Summer 2020. | The 30,000 square foot city-owned industrial building at Powell Street and Pitkin Avenue is currently underutilized and in poor condition. EDC will invest city capital to complete major capital upgrades to the building's exterior and interior, including new lighting, facade repair, signage and mechanical systems. The improvements will result in more modern industrial space accommodating six industrial tenants and around 60 new jobs. Timeline: The first phase of improvements will begin Q3 2016; the second phase of work is anticipated to begin Q3 2017 Capital Funding: $6 million | 2016–2019 | NYCEDC is transforming the underused 30,000 square foot City-owned industrial building at Powell Street and Pitkin Avenue into a modern industrial space. The first phase of improvements, limited to the exterior of the building, was originally scheduled to begin in the third quarter of 2016. In order to achieve efficiencies of scale and maintain ongoing site operations, NYCEDC combined phases one and two of design and construction and committed $6 million of City capital funds. The combined project will include both interior and exterior rehabilitation of the building, and will be designed and bid out together. NYCEDC has procured a City-and State-certified M/WBE firm to serve as construction manager for the project. Local stakeholders will be consulted on the project’s design, which will begin in Summer 2017. Construction is anticipated to begin in late Summer 2018. | NYCEDC has completed design and procured a Construction Manager for the enhancement project, with construction anticipated to commence in Q3 2018, and be complete in 2019. EDC was pleased to work with Council Member Barron to ensure that existing building tenants who wanted to stay would be able to.
East New York | Select IBZ service provider to help IBZ businesses access incentives and navigate government | 44 | Economic Development | SBS | Done | In 2016 SBS selected Business Outreach Center Network (BOCNET) to serve as the East New York Industrial Business Services Provider (IBSP). Industrial Business Service providers are selected through a competitive process, and BOCNET was selected based on their experience working with industrial businesses in Brooklyn. SBS has a network of nine Industrial Business Services Providers (“IBSPs”) to provide assistance to industrial and manufacturing businesses. IBSPs help industrial businesses navigate government and access financing and incentives. The IBSP network also collects real-time data on industrial and manufacturing businesses, allowing the City to refine policies and better respond to the evolving needs of these businesses. | SBS will select a new IBSP for the IBZ and will seek an organization that is familiar with the businesses and physical environment of the IBZ. Timeline: Award new contracts by end of 2016 | 2016 | In 2016, through a competitive process, SBS selected Business Outreach Center Network (BOCNET) to serve as the East New York Industrial Business Services Provider (IBSP). SBS’ eight IBSPs help industrial businesses navigate government and access financing and incentives. The IBSP network also collects real-time data on industrial and manufacturing businesses, allowing the City to refine policies and better respond to the evolving needs of these businesses. | To provide assistance to industrial and manufacturing businesses, SBS has a network of nine Industrial Business Services Providers (“IBSPs”). IBSPs help industrial businesses navigate government and access financing and incentives. The IBSP network also collects real-time data on industrial and manufacturing businesses, allowing the City to refine policies and better respond to the evolving needs of these businesses. In 2016 SBS selected Business Outreach Center Network (BOCNET) to serve as the East New York Industrial Business Services Provider (IBSP). Industrial Business Service providers are selected through a competitive process, and BOCNET was selected based on their experience working with industrial businesses in Brooklyn.
East New York | Assist IBZ businesses and property owners to adopt solar energy | 45 | Economic Development | EDC | Done | The Solar Pioneers program has resulted in creation of two workforce development offerings: a one-day Solar Boot Camp, and a six-week Solar Pioneers Professional Skills & Work Experience Program. During the second phase in East New York, 50 young adults completed the Solar Boot Camp and five young adults completed the Solar Pioneers Professional Skills & Work Experience Program. Over 300 households received a briefing from a trained Solar Pioneer, which generated 103 leads. | NYCEDC, through the NYC Solar Partnership, will launch the NYC Solarize Campaign to assist communities in increasing solar deployment across the five boroughs. The East NY IBZ is an excellent candidate for a Solarize campaign, and NYCEDC will encourage local organizations to apply to be part of the NYC Solarize Campaign. | 2016–ongoing | In Spring 2016, NYCEDC partnered with the Mayor’s Office of Sustainability to launch SolarizeNYC, which offers short-term, community-led initiatives to bring together groups of potential solar customers through widespread outreach and community education. The program will run on a biannual basis for the next 10 years. CUNY has started conversations with local East New York leaders and stakeholders to identify an interested subset of the East New York community to enroll in the program. Once this group is identified, SolarizeNYC can be tailored to meet the unique needs of East New York residents and businesses while increasing the community’s access to solar. | NYC Economic Development Corp. partnered with Nehemiah Economic Development, Inc. (NED) to launch its Solarize Nehemiah campaign, and the contract for Nehemiah Phase II was executed by CUNY in May 2018. NED will continue to implement the Solar Pioneers program, which is the youth training/workforce development arm of the campaign.
East New York | Bring affordable high-speed broadband to businesses in the IBZ | 46 | Economic Development | EDC | In Progress | In December 2018, MOCTO released a Request for Expressions of Interest for the use of City assets to expand broadband infrastructure and service in East New York and is reviewing responses in collaboration with EDC and DOITT | EDC will bring affordable, high-speed broadband access to 250 businesses in IBZ. As currently planned, fiber will be extended south from an existing hub in Broadway Junction to the IBZ and a fixed wireless network will be installed connecting to receivers on the roofs of IBZ businesses. The new broadband network will greatly improve the reliability, capacity, and speed of internet and phone service. Timeline: The City will release RFP/RFEI to procure Internet Service Provider in Q1 2017 with design and construction to commence by Q4 2017 Capital Funding: $2.5 million | 2017–2020 | The NYC Department of Information Technology and Telecommunications (DoITT) has requested that Cablevision/Altice, pursuant to a requirement in its franchise agreement, bring service to currently unserved non-residential buildings in the East New York IBZ. It is expected that the addition of this infrastructure will improve options for IBZ businesses in search of fast, reliable cable or cable-related services, such as internet and phone. Cablevision/Altice will work with the local business community to identify potential customers and deliver expanded service. It is anticipated that Cablevision/Altice will begin design and construction by the fourth quarter of 2017. | The NYC Department of Information Technology and Telecommunications (DoITT) and NYCEDC continues to work with Cablevision/Altice to improve services for local businesses in the IBZ. The City is evaluating responses to a request for information for citywide broadband in preparation for an RFP/RFEI to bring competitive service options to the area. The City will release an RFP/RFEI for a combined IBZ / residential area project in Q1 2019.
East New York | Improve the public realm through expanded area-wide maintenance for the IBZ and the installation of banners | 47 | Economic Development | EDC | Done with ongoing work | In Fiscal Year 2019, the Graffiti Free NYC (GFNYC) Program cleaned 380 properties located in East New York throughout Community Board 5. Working with the Local Development Corporation of East New York (LDCENY), GFNYC concentrated their cleaning efforts on commercial corridors in the rezoning area. Starting with Fulton Street between Pennsylvania Avenue and Eldert Lane, LDCENY obtained permission from individual property owners to clean over 70 properties in the rezoning area during a single nighttime cleaning blitz. GFNYC will be expanding its efforts with LDCENY to identify properties on Atlantic and Liberty Avenues for additional nighttime removal efforts later this season. | NYCEDC will expand efforts to provide area-wide maintenance for the IBZ. NYCEDC will work in partnership with local property owners and the East Brooklyn BID to identify and respond to service requests in a timely fashion, including disposal of illegal dumping and removal of graffiti through the expanded Graffiti-Free NYC Program. NYCEDC will dedicate funding to install additional banners in the IBZ to enhance the streetscape and bring awareness to activity in the IBZ. Timeline: Commencing immediately | 2016–ongoing | NYCEDC provides regular sanitation and graffiti removal services through the Graffiti-Free NYC program, in partnership with the Department of Sanitation and Office of the Mayor. In Fiscal Year 2016, NYCEDC removed 330 yards of street debris and 90 yards of debris from vacant lots in the East New York IBZ through the Area Maintenance Program. NYCEDC cleaned 153 properties in zip codes 11207 and 11212 through the Graffiti Free NYC Program between April 2016 and April 2017. As part of the IBZ marketing campaign, NYCEDC and the East Brooklyn BID are developing new marketing material, including street banners, to be implemented by late 2017. | NYC Economic Development Corp. (NYCEDC) has worked with East Brooklyn BID to install banners throughout the IBZ to highlight local businesses. In addition, NYCEDC has cleaned over 250 properties via the GraffitiFreeNYC program, and continues to do so on an ongoing basis.
East New York | Work with East Brooklyn BID to create a digital marketing campaign to promote IBZ businesses and real estate | 48 | Economic Development | EDC | Done | EDC launched the new EBBID website and promotional material that can be used by the EBBID for industry and other events. Together with new street banners and a wall mural in the ENY IBZ, the new design provides a strong unified branding and visual appeal to the industrial area. | NYCEDC will dedicate funding to develop a digital campaign to increase the profile of the IBZ. NYCEDC will work with the East Brooklyn BID in developing and launching a property opportunities map and/or other marketing materials. | 2016–2017 | NYCEDC engaged the East Brooklyn BID in Fall 2016 to inform and develop a digital marketing campaign to highlight East New York IBZ diverse businesses and products. The marketing campaign will include street banners, marketing brochures, and online materials that feature local businesses, as well as the unique assets and opportunities that the East New York IBZ offers as a place to do business. The campaign launch has been postponed to Fall 2017 to allow more time for input from local businesses and the East Brooklyn BID. | NYC Economic Development Corp. (NYCEDC) has worked with the East Brooklyn BID to develop and launch a digital campaign, which will continue on an ongoing basis.
East New York | Work with local partners to develop new industrial spaces | 49 | Economic Development | EDC | Done with ongoing work | The Industrial Developer Loan Fund continues to accept proposals on an ongoing, quarterly basis. More information can be found on the RFP page here: https://www.nycedc.com/opportunity/profit-non-profit-industrial-real-estate-developers-and-owner-users-rfp | Announced as part of the City's Industrial Action Plan, the $150 million Industrial Developer Fund was created to provide project financing for industrial real estate development projects in New York City. NYCEDC will work with the local community to market the Industrial Developer Fund to potential not-for-profit and for-profit developers to create new and modernized industrial space in the East New York IBZ. Timeline: Commencing immediately | 2016–ongoing | In Spring 2016, NYCEDC announced the Industrial Developer Fund, a unique toolkit of financing solutions for nonprofit and for-profit industrial developers with the aim of creating new and modernized industrial space in the City. NYCEDC is currently accepting proposals from nonprofit and for-profit industrial developers on a rolling basis. NYCEDC has held one-on-one information sessions on the Fund with East New York stakeholders, including elected officials, Community Boards 5 and 16, local development corporations, and other community-based organizations and businesses. NYCEDC has not yet received applications for projects in the East New York IBZ, but will continue to proactively seek development opportunities here. | NYC Economic Development Corp. continues to market both the Industrial Developer Fund and the Emerging Developer Loan Fund to potential developers in the IBZ.
East New York | Activate publicly-owned sites with job generating uses through strategic property dispositions | 50 | Economic Development | EDC | In Progress | EDC identified publicly-owned vacant and/or underutilized lots in the ENY IBZ, and worked with other agencies to consolidate their presence on such lots thereby making them available for private activation. As a result, DCAS is working with private industrial businesses to advance short-term lease agreements with such businesses to occupy the spaces for business expansion. The businesses are anticipated to be operational on the city-owned lots by the end of 2019. | NYCEDC will advance near-term activation of vacant lots with short-term leases to industrial businesses. NYCEDC will work with City agencies to consolidate their spaces and, where feasible, identify properties that can be sold or leased for development of new industrial space or activation with job generating uses. Timeline: Commencing immediately | 2016–ongoing | NYCEDC continues to work with City agencies to consolidate the City’s footprint in the East New York IBZ, leasing or disposing of City-owned properties, in order to promote job generating uses and development of new industrial space. | NYC Economic Development Corp. (NYCEDC) continues to work with City agencies to consolidate the City's footprint in the Industrial Business Zone on an ongoing basis. In addition, NYCEDC is working with community partners to market available spaces for activation.
East New York | Conduct a study to identify opportunities to bring regional-scale uses to Broadway Junction. Conduct a land use study of the IBZ to identify opportunities to densify industrial uses along key corridors. | 51 | Economic Development | EDC | Done | EDC led an interagency planning study and community engagement process on the area in and around Broadway Junction, including the ENY IBZ. Public outreach included seven meetings with the Broadway Junction Working Group (co-chaired by Council Member Rafael Espinal and Borough President Adams), a public open house with over 100 community members in attendance, and an online and in-person survey with over 600 responses from 2018-2019. This work has culminated in the Broadway Junction Vision Document which will be released in Summer 2019 | DCP, together with NYCEDC, will conduct a follow-up study of Broadway Junction. To support this study, NYCEDC is prepared to commit resources to fund a real estate/planning consultant. Acknowledging the significant role of the MTA in this area, the scope of the study will be informed by further coordination with the MTA. In order to successfully start the Broadway Junction work, DCP requires the final recommendations of the North Brooklyn study and complete public review of the IBZ hotel and self-storage zoning text proposal. These elements inform the commitment to begin this study in the second quarter of 2017. Timeline: DCP and NYCEDC would commence stakeholder engagement in support of this planning effort in the second quarter of 2017. | 2017–2020 | The City is currently exploring new models for innovation districts to support 21st century businesses and jobs, with opportunities for a mix of light industrial, commercial, and residential uses. DCP is also developing new tools to support economic development within the City’s IBZs and areas zoned for manufacturing use, including new special permits for self-storage facilities and hotels. These proposed regulations will be entering public review over the next year and could be adopted in 2018. Once these new policies are in place, DCP and NYCEDC will begin a land use study to drive industrial and commercial business and job growth in the IBZ. This study will help to identify strategies to transform the area around the Broadway Junction transit hub into a center of economic activity. DCP and NYCEDC will engage local business owners, community leaders, elected officials and other stakeholders throughout the course of the study. Preliminary stakeholder outreach is anticipated to begin by the end of 2017. | NYCEDC formally launched Broadway Junction planning study and working group in November 2017. There have been 5 working group meetings thus far, and additional meetings will be scheduled this summer. There will be a public event to discuss working group progress in June 2018. The study is expected to continue through late-Summer 2018.
Far Rockaway | Develop 100% affordable housing on public land | 1 | Housing | HPD | In Progress | In July 2018, HPD, HDC, and EDC announced the selection of The Community Builders (TCB) to redevelop an underutilized City-owned lot at Beach 21st Street with approximately 224 affordable homes, commercial space, and community facilities. The new mixed-use, mixed-income development will create over 130 homes allocated for households earning up to 60% of area median income. The remaining apartments will be offered at a range of affordability levels. The project will also create approximately 24,000 square feet of ground-floor retail space, 8,000 square feet of community space for early childhood education and other community services, and approximately 90 parking spots for residents of the building and the public. The City is currently working with the development team to secure construction financing for the project and expects to break ground in 2020. | The City commits to financing the development of 100% affordable housing on the existing public site (known as the Beach 21st Street site at Block 15705, Lot 69 and Part of Lot 59), and future public sites within the rezoning area. The Beach 21st Street site would facilitate the development of approximately 150-200 units of affordable housing in accordance with HPD term sheets. Although responses are still being reviewed, the City expects to finance the development of this site under the Mix and Match term sheet, under which the City commits to financing 20% of the total number of units affordable to families earning 30% AMI, and no units will be offered for households earning above 110% of AMI. The City commits to including a retail and/or community facility component within the ground floor of development on the Beach 21st Street site. The City commits to providing an update to the Council Member on the selection process in fall 2017. Additionally, HPD will continue to prioritize planning and development efforts for investments in new affordable housing on publicly-owned land in the adjacent Edgemere and Arverne East neighborhoods. | 2017–2020 |  | HPD has partnered with EDC to develop 150-200 units of affordable housing on the city-owned property located on Beach 21st Street. The development will be 100% affordable for extremely low, very low, low and moderate income households. Although responses are still being reviewed, the City expects to finance the development of this site under the Mix and Match term sheet, under which the City commits to financing 20% of the total number of units affordable to families earning 30% AMI, and no units will be offered for households earning above 110% of AMI. Designation of a developer is expected early Summer, 2018.
Far Rockaway | HPD will expand requirements for developers to advertise open housing lotteries on construction sites and notify interested applicants | 2 | Housing | HPD | Done | Developers are required to post application information on construction sites for interested applicants, in addition to posting information online on Housing Connect. Since 2018, these signs also include information in multiple languages. | Developers will be required to post contact information on construction sites for interested applicants, in addition to posting information online on Housing Connect. | 2017–ongoing |  | Developers are required to post application information on construction sites for interested applicants, in addition to posting information online on Housing Connect. In 2018, these signs will also include more detailed information in multiple languages.
Far Rockaway | Make it easier for residents to understand, prepare for, and complete the affordable housing application process through the Housing Ambassadors program | 3 | Housing | HPD | Done with ongoing work | In order to build the capacity of current Far Rockaway Housing Ambassador partners Margert Community Corporation and Ocean Bay CDC, HPD provided both organizations with Housing Ambassador trainings in 2017 and 2018. Both organizations also received “Ready to Rent” funding in FY 2018 to help residents apply for affordable housing, and Margert was awarded funding again in FY 2019. HPD welcomed Queens Law Associates’ Outreach Center as the newest Housing Ambassador for Far Rockaway in 2019, and the Office of Councilmember Donovan Richards continued to partner with HPD through the program, sending their staff to trainings so they are equipped to provide affordable housing application assistance for their constituents. | In order to build the capacity of current Far Rockaway Housing Ambassador partners Margert Community Corporation and Ocean Bay CDC, HPD will offer a Housing Ambassador training in Far Rockaway in 2018 in order to make it easier for local organization staff and community leaders to attend and thereby assist Far Rockaway residents with the affordable housing application process. | 2018 |  | In order to build the capacity of current Far Rockaway Housing Ambassador partners Margert Community Corporation and Ocean Bay CDC, HPD provided both organizations with Housing Ambassador trainings in 2017 and 2018. Both organizations also received “Ready to Rent” FY 2018 funding to help residents apply to affordable housing.
Far Rockaway | Launch the Zombie Homes Initiative | 4 | Housing | HPD | Done with ongoing work | HPD launched the Zombie Homes Initiative in the summer of 2017 to address the problem of vacant and abandoned “zombie” homes. Through the Initiative, HPD has conducted 72 exterior surveys of zombie homes in Queens CD 14 to assess the properties’ maintenance conditions. HPD has also connected homeowners at risk of foreclosure in Queens CD 14 to foreclosure prevention resources via robocalls and mailings. As part of the Initiative, HPD is partnering with the NYC Law Department to pursue civil penalties against mortgage holders that fail to maintain the zombie homes in their portfolios in accordance with the New York State Zombie Property and Foreclosure Prevention Act of 2016. The Initiative is also compiling a database of information on zombie homes citywide and developing strategies to return zombie homes to productive use. | HPD will work closely with the Council Member and the community in launching a new initiative to address the problem of "zombie properties" which can be defined as vacant and distressed small homes, whose owners have fallen behind on their mortgage payments. Zombie properties lead to lower property values and higher crime rates in the surrounding area. Through the Zombie Homes Initiative, HPD will help enforce a New York State law, the Zombie Property and Foreclosure Prevention Act of 2016, requiring banks to inspect, report, and maintain zombie properties. As a first step, beginning in Fall 2017, HPD will work collaboratively with the community to identify properties believed to be zombie properties so the City can create a database to check against the State's list. Additionally, HPD will begin outreach in Fall 2017 to connect homeowners to available foreclosure prevention resources and counseling. | 2017–2018 |  | HPD launched the Zombie Homes Initiative in July 2017 to better understand the zombie homes problem in NYC and to develop strategies to address them. Through the Initiative, HPD conducted 41 exterior surveys of zombie homes in Queens Community Board 14. In December 2017, HPD presented the Initiative to Queens Community Board 14, providing an overview of the project, progress in the neighborhood to date, and information on foreclosure prevention resources, as well as encouraging residents to report vacant homes in the community via HPD’s online Zombie Homes Information Form: http://www1.nyc.gov/site/hpd/community/zombie-homes.page. In the coming months, HPD will partner with the NYC Law Department to pursue civil penalties against mortgage holders that fail to comply with the New York State Zombie Property and Foreclosure Prevention Act of 2016, which requires mortgage holders to maintain the zombie homes in their portfolios. The Initiative is also compiling a database of information on zombie homes citywide and developing strategies to return zombie homes to productive use.
Far Rockaway | Dedicate rental assistance to help move homeless families out of shelter and into stable, affordable housing | 5 | Housing | HRA | In Progress | From September 2017 through March 2019, 78 homeless families and individuals displaced from Far Rockaway moved into permanent housing with the support of the Living in Communities (LINC), CITYFEPS Rent Supplement (CITYFEPS), and Special Exit and Prevention Supplement (SEPS) rental assistance programs. Of these families and individuals, 16 moved back to Far Rockaway with this rental assistance. The City created LINC, CITYFEPS, and SEPS to help homeless families and individuals move form temporary shelters back to their communities by paying part of their rent. The NYC Human Resources Administration (HRA) is dedicating resources from these programs to help 200 homeless families and individuals displaced from Far Rockaway and living in shelters move back into the neighborhood if they so choose. | The Human Resources Administration (HRA) will dedicate City rental assistance resources to help 200 homeless families and individuals from Far Rockaway (zip codes 11692, 11691) who are currently living in shelters move back into the neighborhood if they so choose. | 2017–ongoing |  | From September 2017 through March 2018, 105 homeless families and individuals displaced from Far Rockaway moved into permanent housing with the support of the Living in Communities (LINC), CITYFEPS Rent Supplement (CITYFEPS), and Special Exit and Prevention Supplement (SEPS) rental assistance programs. Of these families and individuals, 8 moved back to Far Rockaway with this rental assistance. The City created LINC, CITYFEPS, and SEPS to help homeless families and individuals move from temporary shelters back to their communities by paying part of their rent. The NYC Human Resources Administration (HRA) is dedicating resources from these programs to help 200 homeless families and individuals displaced from Far Rockaway and living in shelters move back into the neighborhood if they so choose.
Far Rockaway | Provide tenant legal services to keep families and individuals stably housed and preserve affordable housing | 6 | Housing | HRA | Done with ongoing work | Since September 2017, the City has provided 1,245 households with legal services in Far Rockaway; this includes over 3,859 individuals of which 1,858 were children. As part of its commitment to provide universal access to counsel for tenants facing eviction in housing Court, the City will dedicate $166 million citywide, at full implementation in Fiscal 2022, to ensure free legal representation for low-income tenants and free legal counseling for those who earn more. The Fiscal 2020 Executive Budget includes a total of $127 million to prevent unlawful evictions, harassment by unscrupulous landlords, and displacement. | Since 2014, the City has increased investment in tenant legal services programs, to help families and individuals remain in their homes and prevent the loss of affordable housing. The City's new Universal Access to Counsel program dedicates $93 million, on top of the $62 million already allocated, to ensure free legal representation for low-income tenants (under $50,000 for a 4-person family) and free legal counseling for those that earn more. The Human Resources Administration will provide tenant legal services in zip codes 11692 and 11691, to prevent unlawful evictions, harassment by unscrupulous landlords and displacement. | 2017–ongoing |  | From September 2017 to March 2018, the City provided 446 households with legal services in Far Rockaway, including 733 adults and 730 children. As part of its commitment to provide universal access to counsel for tenants facing eviction in Housing Court, the City will dedicate $155 million, at full implementation in Fiscal 2022, to ensure free legal representation for low-income tenants and free legal counseling for those who earn more. The Fiscal 2019 Executive Budget includes a total of $94 million to prevent unlawful evictions, harassment by unscrupulous landlords, and displacement.
Far Rockaway | Provide resources to educate and support tenants facing potential harassment | 7 | Housing | HPD | Done with ongoing work | HPD is committed to working with partner agencies, elected officials, and community groups to ensure tenants are aware of their rights and have access to important housing resources. In Far Rockaway, HPD contracts with the Jewish Community Council of the Rockaway Peninsula to conduct outreach and educational initiatives for tenants, including coordinating tenant meetings and conducting surveys to assess physical conditions in apartments. HPD also collaborated with Councilmember Donovan Richards to host a Tenant Resource Fair in Far Rockaway in summer 2018. | HPD will work with the Tenant Harassment Prevention Task Force to investigate and take action against landlords who harass tenants. HPD will educate tenants about their rights and resources to prevent displacement through public information campaigns and through coordination with the Council Member's office and the Community Board. Additionally, HPD's Neighborhood Education and Outreach Unit hosts tenant resource fairs, where they provide information about tenants' rights, legal services, rental assistance programs, and the affordable housing application process. HPD commits to hold the next resource fair in spring 2018. | 2018 |  | HPD is committed to working with partner agencies, elected officials, and community groups to ensure tenants are aware of their rights and have access to important housing resources. In Far Rockaway, HPD contracts with the Jewish Community Council of the Rockaway Peninsula to engage with tenants through various outreach and organizing methods that lead to deliverables such as helping coordinate tenant meetings and conducting surveys to assess apartment physical conditions. HPD will also work with the Councilmember to schedule a Tenant Resource Fair in Far Rockaway in Summer 2018.
Far Rockaway | Implement an extensive outreach strategy to promote programs that could help homeowners and multifamily property owners make repairs and preserve affordability for existing tenants | 8 | Housing | HPD | Done with ongoing work | HPD continues to take a proactive and strategic approach to engaging building owners who could benefit from financing and tax incentives in exchange for maintaining affordable rents for existing tenants. HPD hosted a Landlord and Homeowner Resource Fair in Far Rockaway in February 2018. HPD also contacts property owners by email, mail, phone, and at community events. These efforts are coupled with a new marketing campaign HPD launched in 2017 titled “Let’s Invest.” Additionally, HPD now conducts monthly Property Owner Clinics at 100 Gold Street where property owners sign up to speak one-on-one with agency representatives HPD, DOB, DOF, DEP, and the Center for NYC Neighborhoods to troubleshoot issues with their properties. The clinics are open to all property owners throughout the city. Through these efforts, HPD has reached the owners of 71 properties in the Rockaways representing over 3,000 apartments. | HPD's Neighborhood Education and Outreach Unit hosts landlord and homeowner resource fairs. HPD commits to hold its next resource fair in spring 2018. Multifamily buildings in Far Rockaway are included in citywide and boroughwide mailings and robocalls to share information on HPD's loan and tax incentive programs. HPD will begin work in fall 2017 with CNYCN and their partners to conduct outreach to homeowners to provide financial and legal counseling and prevent foreclosures. | 2017–2018 |  | HPD continues to take a proactive and strategic approach to engaging building owners who could benefit from financing and tax incentives in exchange for maintaining affordable rents for existing tenants. HPD also hosted a Landlord and Homeowner Resource Fair in Far Rockaway in February 2018. HPD contacts property owners by email, mail, phone, and at community events. These efforts are coupled with a new marketing campaign HPD launched in 2017 titled “Let’s Invest”. The new marketing materials were created with the feedback received from property owners. Additionally, HPD added a monthly Property Owner Clinic held at 100 Gold Street where property owners sign up to speak one on one with agency representatives to troubleshoot issues with their property. The clinics are open to all property owners throughout the City. Representatives from HPD finance programs, HPD code enforcement, Department of Buildings, Department of Finance, and Department of Environmental Protection. Through these efforts, HPD has reached the owners of 66 properties inthe Rockaways representing over 3,000 apartments.
Far Rockaway | HPD will provide support to community land trusts to create new permanently affordable homeownership opportunities | 9 | Housing | HPD | Done | HPD continues to work with Interboro CLT and its member organizations to expand affordable housing opportunities for NYC residents. Supported by a grant from Enterprise Community Partners, in partnership with HPD, Interboro CLT incorporated as a Housing Development Fund Corporation (HDFC) in 2018. The group is finalizing their CLT bylaws and ground lease structure and is engaged in predevelopment negotiations with HPD on a number of sites. HPD will continue working with Interboro CLT to build organizational capacity and advance affordable housing construction and preservation projects. | HPD recently announced an award of $500,000 from Enterprise Community Partners to the Interboro CLT, a partnership of the Center for NYC Neighborhoods, the Urban Homesteading Assistance Board (UHAB), the Mutual Housing Association of New York (MHANY), and Habitat for Humanity that intends to create a land trust in nearby Edgemere. Over the next 24 months, the grant will fund operations and start-up support while the Interboro CLT works to identify sites for acquisition in Edgemere and elsewhere. | 2017–2019 |  | HPD continues to work with Interboro CLT and its member organizations to expand affordable housing opportunities for NYC residents. In April 2018, Interboro CLT incorporated as a Housing Development Fund Corporation (HDFC). This designation allows Interboro to partner with HPD. The group is finalizing their CLT bylaws and ground lease structure and is engaged in predevelopment negotiations with HPD on a number of sites.
Far Rockaway | Continue to offer financing to incentivize the development of affordable housing on privately owned sites in Downtown Far Rockaway | 10 | Housing | HPD | Done with ongoing work | Since the rezoning was adopted, HPD financed the construction of 599 new affordable homes in two projects: 1414 Central Avenue and Roackaway Village Phase 1. These affordable projects serve a range of incomes, including nearly 200 homes for extremely low- and very low-income households. | In June 2017, HPD released updated ELLA and Mix and Match programs to allow for deeper affordability and greater flexibility in affordability levels that buildings can serve. Because rents in Downtown Far Rockaway do not currently support the creation of 100% market rate housing, we expect owners of private sites seeking to engage in residential development to approach the City for financing. When approached by private owners, the City will utilize its term sheets to incentivize the maximum number of affordable units at a range of income levels, including extremely-low, low and moderate income households. | 2017–ongoing |  | Currently HPD is working with a developer on the first phase of a planned multi-phase affordable housing development that will be up to two 100% affordable buildings. The project will be financed under either the ELLA or Mix and Match programs. The first phase is expected to bring approximately 450 affordable units, along with new commercial space and public open space to the heart of Downtown Far Rockaway.
Far Rockaway | Keep existing homes affordable by continuing to offer loans and tax incentives to building owners | 11 | Housing | HPD | Done with ongoing work | HPD continues to seek opportunities to preserve and invest in existing affordable housing through its various programs. Since 2014, HPD has financed the rehabilitation and continued affordability of 3,540 homes in CD 14. | Building on recent successes with 2,854 units in the Council Member's district preserved between 2014 and 2017, HPD will continue to seek opportunities to preserve and invest in existing affordable housing through its various programs. | 2017–ongoing |  | HPD continues to seek opportunities to preserve and invest in existing affordable housing through its various programs. Since 2014, HPD has financed the rehabilitation and continued affordability of 3,537 homes in Community District 14.
Far Rockaway | Support the community's application for the establishment of a Cease and Desist Zone to protect homeowners from unwanted solicitation | 12 | Housing | HPD | In Progress | HPD is prepared to support efforts by community stakeholders to prepare an application for the Cease and Desist Zone program to the State of New York. As of yet, no community groups have approached HPD to begin such an effort. HPD can offer guidance and expert testimony through the public process. | HPD will support the community's preparation of application for the Cease and Desist Zone program to the State. HPD can offer guidance and expert testimony through the public process. | 2017–ongoing |  | HPD is prepared to support efforts by community stakeholders to prepare an application for the Cease and Desist Zone program to the State of New York. As of yet, no community groups have approached HPD to begin such an effort. HPD can offer guidance and expert testimony through the public process.
Far Rockaway | Advance the complete renovation of Bayswater Park | 13 | Open Space | DPR | In Progress | DPR held a second community design meeting in October 2018 to discuss renovations of Bayswater Park. Design work is underway with an anticipated final design completion in fall 2020. | The park will see a full scale renovation and NYC Parks will undertake outreach and hold a public scoping meeting to ask the community what they would like to see in this important neighborhood park. New amenities could include new or improved playing fields and playground, improved entrances and expanded shoreline access, and an enhanced area for performances and festivals. | 2018–2023 |  | Pre-engineering and design work commenced in March 2018. A community visioning session to guide the park's reconstruction took place on May 22, 2018. Detailed design work is expected to begin in Fall 2018.
Far Rockaway | Implement Redfern Open Space improvements | 14 | Open Space | DPR | In Progress | DPR presented the conceptual design of Redfern open space improvements to the Redfern Houses Tenants Association and Queens Community Board 14 in April 2019. Design work is underway with an anticipated final design completion in summer 2019. | Looking comprehensively at NYC Parks Redfern Playground site and the adjacent NYCHA-owned playground, in close coordination with NYCHA and with community input, Parks will lead efforts to improve and enhance recreational amenities, creating an attractive open space that serves the growing needs of current and future residents. | 2018–2021 |  | DPR and NYCHA are crafting an agreement that would allow NYC Parks to perform open space improvements on NYCHA property. Design is expected to begin in Fall 2018 with a community scoping session.
Far Rockaway | Build New Park at Block 15534, Lot 70 | 15 | Open Space | DPR | In Progress | DCAS assigned jurisdiction of the property to DPR in November 2017. A public meeting was held in May 2019 to kick off the design process. | In response to the strong advocacy of the Council Member as echoed by others in the community, the City will withdraw the ULURP application related to the disposition of this site for housing uses, and will instead dedicate significant capital funding and work through the Department of Parks and Recreation ("Parks") to transform the vacant lot at Block 15534, Lot 70 (corner of Augustina Avenue and Nameoke Avenue) into a new, 14,000-sf park to serve the Downtown Far Rockaway area. Parks will engage the community in a design process to determine the final programming of the space, which could include court amenities, play and/or water features, a comfort station, landscaping, seating, and/or other park amenities. | 2019–2022 |  | DCAS assigned jurisdiction of the property to DPR in November 2017. Project design is expected to begin in Summer 2019 with a community scoping session.
Far Rockaway | Advance comprehensive renovation of the Downtown Far Rockaway library | 16 | Community Resources | DDC | In Progress | Construction on the new Downtown Far Rockaway Library commenced in August 2018. DDC is progressing on schedule with an expected construction completion of summer 2021. | DDC will replace the existing 9,000-sf single-story Queens Public Library branch at the corner of Mott and Central Avenues with a new, two-story, 18,000 sf building designed by Snohetta Architects. The new library will meet both the current needs of the community and future neighborhood growth, and will serve as an anchor for this key corner in Downtown Far Rockaway. The branch services will include programs for all ages, after-school study hours, story reading and community events. | 2017–2021 |  | DDC will replace the existing 9,000 square foot single-story Queens Public Library branch at the corner of Mott and Central Avenues with a new, two-story 18,000 square foot building designed by Snohetta Architects. The new library will meet both the current needs of the community and future neighborhood growth, and will serve as an anchor for this key corner in Downtown Far Rockaway. The branch services will include programs for all ages, after-school study hours, story reading and community events. The project is currently going through the City’s procurement process, with a construction kickoff expected for summer 2018, and physical work targeted for fall 2018. Demolition of the existing building, followed by construction of the new building, is expected to take three years. The project also includes a temporary swing space facility, which will be in place once the current facility is closed to provide temporary library services to the community.
Far Rockaway | Expand daycare offerings in Downtown Far Rockaway | 17 | Community Resources | HPD | In Progress | EDC and HPD jointly issued an RFP in 2016 calling for an affordable housing and mixed use development on the current municipal parking lot and bus depot in Downtown Far Rockaway adjacent the A train subway station. The RFP encouraged community facilities including daycare/pre-K uses. The selected project, from The Community Builders, a non-profit developer of affordable and mixed-income housing, includes 8,000 square feet of community space for early childhood education and other community services. | HPD will encourage the inclusion of daycare providers in any RFPs for sites within the DFRURA as well as any developments receiving HPD subsidy. The City will monitor the demand and need for additional publicly funded day care services in the area and identify the appropriate measures to meet demand for additional slots. The City anticipates that additional procurement of center-based daycare seats may be necessary within the redevelopment area to mitigate increased need, and will continue to monitor enrollment and capacity within the rezoning area and address the need as it arises. | 2017–ongoing |  | EDC and HPD jointly issued an RFP in 2016 calling for an affordable housing and mixed use development on the current municipal parking lot and bus depot in Downtown Far Rockaway adjacent the A train subway station. The RFP encouraged community facilities including daycare/pre-K uses. Currently there are no other city owned properties in Downtown Far Rockaway suitable for redevelopment, but if there are future RFPs of any city-owned property as a result of the Urban Renewal Plan, HPD will continue to affirmatively encourage daycare and pre-K uses to be incorporated on all redevelopment sites.
Far Rockaway | Encourage healthcare uses in new developments on city-owned sites | 18 | Community Resources | EDC | In Progress | EDC selected The Community Builders, Inc. as the developer for the Beach 21st Street RFP in 2018 to construct a 100% affordable housing development at a range of incomes with ground floor retail and community facility space. The RFP required retail and community facility uses that respond to the needs of the community, and incorporated a list of recommendations from the community which included healthcare, daycare, restaurants and coffee shops, among others. | EDC and HPD are exploring the possibility of including healthcare uses in the Beach 21st Street development site, and will update the Council Member on this project in Fall 2017. Additionally, future HPD RFPs for city-owned sites will give preference to responses that include healthcare facilities. | 2017–ongoing |  | EDC is in active negotiations with respondents to the Beach 21st Street RFP and selection is anticipated in Spring 2018. This project will deliver a 100% affordable housing development at a range of incomes with retail and community facility space. The RFP required retail and community facility uses that respond to the needs of the community, and provided a list of recommendations from the community which included daycare, healthcare, restaurants and coffee shops among others. The project will connect to a new open space plaza at the subway entrance to the A train and provide a more welcoming entranceway to what was historically the downtown commercial corridor of the Rockaway peninsula.
Far Rockaway | Additional commitment of funding to support violence prevention, education, and community support | 19 | Community Resources | MOCJ | Done | As part of the city’s commitment to re-zoning downtown Far Rockaway, CMS partner Sheltering Arms/Rock Safe Streets (RSS) received a onetime FY 19 stimulus of $250K as part of Far Rockaways “Revitalization Funding”. OPGV is requesting to continue the funding which supports CMS programming in downtown Far Rockaway and expansion into the Red Fern Housing Development. The amelioration of RSS current services accomplishes the following tasks: • Resolving conflicts and reducing violence: RSS will hire program staff to identify potentially violent conflicts and work to preempt violence through conflict de-escalation and mediation strategies and building trust with individuals. • Outreach and mentoring to high-risk youth: RSS violence interrupters will engage with youth and guide them towards positive behavior-changing activities (i.e. referrals to pre-existing community resources. • Community mobilization: RSS program staff will raise awareness about violence through organizing community responses to shooting incidents and community events (e.g., rallies, marches) that occur within 72 hours of the shooting occurrence. • Public education: RSS program staff will distribute public education materials while canvassing the service area, at neighborhood events, and other activities. Appropriate forms of messaging will be directed to members of the community, those most likely to be involved in a shooting, and the public at large. • Conduct daily community canvassing: RSS staff will canvas the service area to establish program presence, understand current and past conflicts, create opportunities for informal contact with those at risk of involvement in shootings and other serious violence and become familiar with community members. | Cure Violence is an evidence-based violence prevention program that works with communities that have high levels of gun violence. The City will commit to an additional $250,000 of Cure Violence funding to support "Rock Safe Streets", the Sheltering Arms gun violence interruption program in Far Rockaway. Rock Safe Streets works to identify potential incidents of violence and prevent them through mediation and de-escalation. In addition, Rock Safe Streets supports those most affected by violence with therapeutic mental health supportive services. The additional funding will allow Rock Safe Streets to hire a new Education/Employment Specialist, Community Coordinator and Administrative Assistant. | 2018 |  | This one-time allocation of $250,000 will be utilized to hire additional Violence Interrupters/Outreach workers that will be deployed throughout targeted areas in the Rockaways to deescalate/mediate ongoing feuds as well as provide additional violence intervention/prevention services. Funding for a new Education/Employment Specialist, Community Coordinator and Administrative Assistant will be covered by previous investments to expand Rock Safe Streets rather than this one-time allocation of $250,000.
Far Rockaway | Support for Cultural Activities in Far Rockaway | 20 | Community Resources | DCLA | In Progress | Building Community Capacity program's Phase II grant application will be released in July 2019 with the Far Rockaway program scheduled to launch in fall 2019. | The Department of Cultural Affairs will grant $50,000 to the Queens Council for the Arts for the following initiatives in Downtown Far Rockaway: Regrant Program, which enables the Council to support small organizations for various cultural events (e.g. local dance/music/visual arts groups); 2) Professional Development for Artists and Arts Organizations, which funds individuals and groups to build capacity; and 3) High School Portfolio Preparation Program, which helps students to create art portfolios to apply to specialized high schools. The Queens Council will work with the Councilmember to determine how best to use these funds in the district. | 2017–2018 |  | DCLA granted an additional $50,000 to the Queens Council for the Arts for enhanced activity in Downtown Far Rockaway. The following projects are underway: High School Portfolio Preparation Program: Providing qualified high school juniors and seniors with the art skills training, mentorship, essay writing techniques, college application assistance and financial aid planning necessary to gain acceptance into competitive art colleges. To date, the Council has conducted focused outreach and recruitment of students from Far Rockaway to ensure the community has access to this program. Professional Development for Artists and Arts Organizations: Career development services, marketing efforts, peer resources, and leadership training made available to emerging and established individual artists and arts organizations. To date, the Council has conducted focused outreach and recruitment of participants from Far Rockaway to ensure the community has access to this program.
Far Rockaway | Review five buildings for potential landmark eligibility | 21 | Community Resources | LPC | Done | The LPC reviewed five properties for their historical significance and potential landmark eligibility, including 16-18 Central Avenue, 21-17 Mott Avenue, 19-31 Mott Avenue, 16-17 Central Avenue and 16-12 Mott Avenue. Of the five, LPC identified two as eligible for designation, and on May 29, 2018 the Commission voted to designate as landmarks Firehouse, Engine Companies 264 & 328/Hook and Ladder 134 at 16-15 Central Avenue, and the 53rd (now 101st) Precinct Police Station at 16-12 Mott Avenue. They are both prominent civic structures and significant reminders of an important era in Downtown Far Rockaway’s development, and fine examples of the Renaissance Revival style used in the early 20th century expansion of the City’s fire and police departments. | The LPC will perform a review of five properties for their historical significance and potential landmark eligibility. The sites include 16-18 Central Avenue, 21-17 Mott Avenue, 19-31 Mott Avenue, 16-17 Central Avenue and 16-12 Mott Avenue. | 2017–2018 |  | The LPC reviewed five properties for their historical significance and potential landmark eligibility, including 16-18 Central Avenue, 21-17 Mott Avenue, 19-31 Mott Avenue, 16-17 Central Avenue and 16-12 Mott Avenue. Of the five, LPC identified two as eligible for designation, and on May 29, 2018 the Commission voted to designate as landmarks Firehouse, Engine Companies 264 & 328/Hook and Ladder 134 at 16-15 Central Avenue, and the 53rd (now 101st) Precinct Police Station at 16-12 Mott Avenue. They are both prominent civic structures and significant reminders of an important era in Downtown Far Rockaway’s development, and fine examples of the Renaissance Revival style used in the early 20th century expansion of the City’s fire and police departments.
Far Rockaway | Add mosquito mitigation in Dubos Point Park and Edgemere Park | 22 | Community Resources | DOHMH | Done | To address concerns regarding mosquitos at Dubos Point Park and Edgemere Park, DOHMH ordered and installed five additional “mosquito magnets” to those already in place at those locations. | To address concerns regarding mosquitos at Dubos Point Park and Edgemere Park, the NYC Department of Health and Mental Hygiene will install five (5) additional "mosquito magnets" to those already in place at those locations. | 2017 |  | To address concerns regarding mosquitoes at Dubos Point Park and Rockaway Community Park, DOHMH will install five additional "mosquito magnets" to those already in place at those locations. There currently are five magnets operational in the Rockaways (3 in Dubos Point and 2 in Rockaway Community Park). DOHMH has already installed several new cages in the Rockaways, and installation of the new magnets is expected to take place in Summer 2018.
Far Rockaway | Advance Bridge Creek clean-up efforts | 23 | Community Resources | DSNY | Done with ongoing work | DSNY cleaned the perimeter of the wetlands in August 2017. DSNY inspects the perimeter of this property on a regular basis and performs cleaning as resources are available. DPR will continue to keep the Council Member apprised of future wetland clean-up opportunities for this site. | Parks will work with DSNY to assess strategies, understand NYSDEC permitting requirements, and will report back to the Council Member by December 2017 with suggested course of action. DSNY will immediately clean the perimeter of the property, and the City will remove trash from this area by Spring 2018. | 2017–2018 |  | DSNY completed a perimeter clean-up of the wetlands in August 2017 and will continue to inspect and clean the perimeter of the property on a regular basis (most recently in May 2018). DPR and the Jamaica Bay-Rockaway Parks Conservancy held a volunteer wetland clean-up event on World Wetlands Day in February 2018. NYC Parks will continue to keep the Council Member apprised of future wetland clean-up opportunities for this site.
Far Rockaway | ADA access ramp project at the 101 Police Precinct | 24 | Community Resources | NYPD | In Progress | Design completion for the construction of the ADA access ramp in the 101 precinct is scheduled for spring 2019. Construction is anticipated to start March 2020. | The City will perform upgrades for the 101st Precinct including an ADA access ramp project, estimated at $300,000. Construction is anticipated start in the fall of 2018. | 2018–2019 |  | NYPD hired the engineering firm LiRo to conduct borings and structural review as part of the pre-design phase. Following design, construction is expected to be complete by the end of 2019.
Far Rockaway | Upgrades to 101 Police Precinct in the form of asbestos remediation, bathroom renovation, and locker room renovations | 25 | Community Resources | NYPD | In Progress | Asbestos abatement and bathroom renovations were completed in 2018. Locker room design and scope are in development. NYPD is on schedule to renovate the locker rooms by 2021. | In May 2017 the NYPD completed a bathroom renovation project at the 101 Precinct which also included renovation of locker rooms. There was asbestos remediation within the gym area completed approximately two years ago. Asbestos was abated and the remainder was encapsulated. NYPD has committed to abate the previously encapsulated remainder in the Fall of 2017. The abatement from contract to completion should take 4-6 weeks and will cost approximately $25,000. | 2017 |  | NYPD completed renovations to the public and police officer bathrooms and locker rooms, and completed asbestos remediation within the gym area.
Far Rockaway | Invest in upgrades to existing schools | 26 | Community Resources | SCA | In Progress | As part of the Downtown Far Rockaway rezoning, DOE and SCA committed additional funds for school improvement projects and worked with Council Member Richards to identify appropriate opportunities. SCA is advancing these projects and have assigned integrators to work with the selected schools to purchase new technology. | The DOE/SCA is happy to work with the community as part of the Downtown Far Rockaway rezoning effort. DOE/SCA is currently advancing over $130million in capital work to provide necessary improvements to the schools within the Council Member's district. In addition, DOE/SCA is accelerating projects currently in design so that students may benefit from the work on an accelerated timeline. DOE/SCA will continue working closely with the community and use the feedback received to ensure that future upgrades meet the needs of the schools and improve the state of facilities within the district. Additionally, the Administration will fund up to $10million in other SCA School Improvements, to be selected in consultation with Council Member Richards prior to June 1, 2018. | 2018–2022 |  | As part of the Downtown Far Rockaway rezoning, DOE/SCA committed additional funds for school improvement projects and worked with the Council Member to identify appropriate projects. SCA will initiate scoping for these projects in Fiscal Year 2019.
Far Rockaway | Hold a site within the Urban Renewal Area for a potential elementary school | 27 | Community Resources | SCA | In Progress | As part of the Downtown Far Rockaway Rezoning, over time the population within the neighborhood is projected to increase and contribute towards new school enrollments. To accommodate existing students as well as the new projected enrollment, SCA and DOE plan to reserve a site in the urban renewal area to accommodate a new elementary school if determined necessary during the 10-year period. SCA is currently reviewing potential sites. | While the Downtown Far Rockaway Rezoning would result in new development and demand for public schools, as demonstrated in the FEIS there is capacity in Sub-district 1 of CSD 27 to accommodate existing students as well as new enrollment projected to result from the rezoning. However, the City recognizes the Council Member's concerns about public school capacity, specifically elementary schools. We anticipate that the rezoning will increase the population of the neighborhood over time, and SCA and DOE will continue to monitor school enrollment and capacity in the future as development occurs and will address capacity issues as they arise. To this end, the City will reserve a site in the urban renewal area for a period of 10 years in order to be able to accommodate a new elementary school, to be utilized if SCA and DOE determines a need for one during that 10 year period. | 2017–2027 |  | The Final Environmental Impact Statement of the Downtown Far Rockaway Rezoning showed capacity in sub-district 1 of District 27 to accommodate existing students as well as new projected enrollment as a result of the rezoning. DOE anticipates the rezoning will increase the population of the neighborhood over time, and the School Construction Authority (SCA) and DOE will continue to monitor school enrollment and capacity as development occurs and will address capacity issues as they arise. The City will reserve a site in the urban renewal area for a period of 10 years to be able to accommodate a new elementary school, to be utilized, if SCA and DOE determine a need for a school during the 10 year period.
Far Rockaway | Explore new models at Downtown Far Rockaway Schools | 28 | Community Resources | DOE | In Progress | The DOE is continuing to have conversations with the Superintendent about the feasibility and interest in a dual langauge program. DOE will re-evaluate for the 2019-2020 school year. | The Department of Education will meet with the Council Member to explore a Dual Language program for a school in Downtown Far Rockaway for the 2018-2019 school year. DOE will meet with the Council Member to also discuss the potential for new programming and other ways to increase enrollment in schools that are currently significantly under capacity. The Chancellor will also convene a Round Table with Principals to educate and encourage participation in new models and programs such as Dual Language Programs by Downtown Far Rockaway schools. | 2017–2019 |  | DOE will meet with Council Member Donovan Richards to explore a Dual Language program for a school in Downtown Far Rockaway for the 2018-2019 school year. The Council Member and DOE will continue exploring the potential for new programming and other ways to increase enrollment in schools that are significantly under capacity.
Far Rockaway | Study potential to establish a weekly farmers market in the Downtown area | 29 | Community Resources | EDC | In Progress | EDC has brought on GrowNYC to organize a Youth Market Farm Stand in Downtown Far Rockaway for summer 2019, to be operated by neighborhood youth and supplied by local farmers. The Youthmarket will increase access to farm fresh food in the neighborhood, and provide an opportunity for young people to earn money and learn small-business skills. The farm stand will run on Saturdays between 9AM-1PM from July 13, 2019 to November 11, 2019, and will be located on the corner of Beach 20th Street and Cornaga Avenue. | Building on the success of the nearby Rockaway Youth Task Force farm and the Edgemere Farm, the City will conduct outreach to better understand the feasibility and logistics of a market in Downtown Far Rockaway. | 2017–2018 |  | In spring 2018, EDC met with Council Member Richard's staff and GrowNYC staff to discuss the feasibility and logistics of a Youth Market Farm Stand in Downtown Far Rockaway. The Youth Market Farm Stand would be operated by neighborhood youth and supplied by local farmers. The Youthmarket would increase access to farm fresh food in the neighborhood, and provide an opportunity for young people to earn money and learn small-business skills. The project is in the planning stages and coordination is ongoing.
Far Rockaway | Quarterly meetings with steering committee | 30 | Community Resources | EDC | In Progress | EDC continues to hold quarterly meetings with the Downtown Far Rockaway steering committee. The meetings have been used to provide updates on a number of projects related to the Downtown Far Rockaway rezoning commitments by various City agencies. In the last steering committee meeting held in spring 2019, SBS presented its initial findings for the Downtown Far Rockaway Neighborhood 360 Commercial District Needs Assessment and solicited feedback to be incorporated into the final report. | EDC will commit to quarterly steering committee meetings, whose members will be selected by the Council Member, after the conclusion of ULURP. These meetings will be used to provide project updates and serve as a forum for the City to receive feedback from community stakeholders. | 2017–ongoing |  | The Downtown Far Rockaway steering committee held its first meeting in late December 2017. The meeting was used to provide updates on a number of projects related to the Downtown Far Rockaway rezoning commitments by various City agencies. Along with EDC, the City had representatives from City Hall, NYC Parks, HPD, and SBS provide project updates and receive feedback from the community stakeholders. A steering committee meeting is scheduled for spring 2018.
Far Rockaway | Implement a comprehensive streetscape improvement project in Downtown Far Rockaway, coordinating with district-wide sewer infrastructure upgrades | 31 | Transportation & Infrastructure | DOT | In Progress | DOT has been working closely with DDC and DEP to coordinate an area-wide street reconstruction/sewer infrastructure project in the Downtown Far Rockaway area. Construction is expected to begin in fall 2019. | Implement a comprehensive streetscape improvement project in Downtown Far Rockaway, coordinating with district-wide sewer infrastructure upgrades DOT's Downtown Far Rockaway Streetscape Reconstruction project will reconstruct Mott Avenue from Redfern Avenue to Beach 17th Street, on Beach 21st and Beach 20th Street from Mott Avenue to Cornaga Avenue, and on Central Avenue from Mott Avenue to Foam Place. Mott Avenue will have expanded sidewalks with new street trees and improved street lighting. This project will also introduce a new DOT public plaza that safely connects pedestrians between the A-train on Beach 22nd Street and regional buses on Beach 21st Street, along with a new gathering space for residents and visitors. This project will be constructed in conjunction with the installation of DEP storm and sanitary sewer infrastructure, supporting the City's rezoning efforts and strengthening resiliency in the wake of extreme weather events. DOT is also currently exploring an interim project, which will use agency in-house materials (markings, signage, etc.) to enhance safety, mobility and quality of life around the intersection of B. 22nd Street. DOT aims to share preliminary designs with the Council Member in spring 2018. | 2017–2022 |  | DOT has been working closely with DDC and DEP to coordinate the area-wide street reconstruction/sewer infrastructure project in the Downtown Far Rockaway area. The DOT safety and mobility project includes key streetscape upgrades that feature a "town square" public plaza, transit corridor on Beach 21 St., expanded sidewalks and improved street lighting and trees/landscaping.
Far Rockaway | Install new bus shelters in the Downtown Far Rockaway area | 32 | Transportation & Infrastructure | DOT | In Progress | Bus amenities to make rides more comfortable will be added as part of the street reconstruction and streetscape project. | As part of the Downtown Far Rockaway Streetscape Reconstruction project, DOT plans to install two bus shelters and twelve leaning bars at bus stops across the area. DOT plans to create an improved linear bus terminal on Beach 21st street with bus shelters, two leaning bars and street trees to improve the passenger waiting experience. | 2017–2022 |  | As part of DOT's street reconstruction and streetscape project in the Downtown Far Rockaway area, the agency is installing amenities (i.e., leaning bars, shelters, etc.) to make for a more comfortable experience for waiting bus passengers at this key transit hub in Queens.
Far Rockaway | Install real-time bus arrival displays at key bus stops | 33 | Transportation & Infrastructure | DOT | Done | As part of the Select Bus Service (SBS) launch (Q52/53) launch in November 2017, DOT installed nine wayfinding totems with real-time bus arrival displays in the Rockaways. The totems were spread out over various stops along the routes and provide real-time bus arrival information for both local and SBS routes. | DOT will install nine wayfinding totems with real-time bus arrival displays at Q22/Q52/Q53 bus stops in the Rockaways. These totems will provide real-time bus arrival information for both local and SBS routes. | 2017 |  | As part of the Select Bus Service (SBS) launch (Q52/53) launch in November 2017, DOT installed nine wayfinding totems with real-time bus arrival displays in the Rockaways. The totems were spread out over various stops along the routes and provide real-time bus arrival information for both local and SBS routes.
Far Rockaway | Pilot ferry service shuttle from Downtown Far Rockaway to current Beach 108th Street landing | 34 | Transportation & Infrastructure | EDC | In Progress | EDC worked with the Council Member to launch a three month pilot of weekday shuttle bus service providing a direct connection from Downtown Far Rockaway to the Beach 108th St ferry landing. The pilot operated for the three months between November 2017 and January 2018, and was followed by an evaluation based on ridership and other planning factors such as on-time performance and time travel savings. In response to the Council Member's request to re-launch the pilot in summer 2019, EDC is running the shuttle bus service between May 20 - Sept 9, aligning with the NYC Ferry summer schedule. | EDC will work with the Council Member to launch a pilot of weekday shuttle service providing a direct connection from Downtown Far Rockaway to the Beach 108th Street landing. This service will operate for three months and will be followed by an evaluation based on ridership and other planning factors. | 2017–2019 |  | EDC worked with the Council Member to launch a three month pilot of weekday shuttle bus service providing a direct connection from Downtown Far Rockaway to the Beach 108th Street ferry landing. The pilot operated for the three months between November 2017 and January 2018, and was followed by an evaluation based on ridership and other planning factors such as on-time performance and time travel savings. Local elected officials were briefed on the results of the study, which found that less than 3% of Rockaway ferry riders used the pilot shuttle. Based on the analysis of the pilot, the service was discontinued.
Far Rockaway | Explore the feasibility of a new ferry landing east of 108th Street | 35 | Transportation & Infrastructure | EDC | Done | EDC undertook a planning study to determine the feasibility of an additional ferry landing in the Rockaways. The study looked at a landing at Motts Basin as well as weighed the option of purchasing additional vessels to support the ridership demand at the current Beach 108th St landing. EDC completed the study at the end of 2018 and found that a new ferry landing is infeasible due to underwater environmental conditions. | EDC is currently in the process of determining the feasibility of an additional ferry landing east of 108th street. EDC will commit to sharing the results of the feasibility study with the Council Member at its conclusion this fall. | 2017 |  | EDC has undertaken a planning study to determining the feasibility of an additional ferry landing in the Rockaways. The study looked at several sites along the peninsula as well as weighed the option of purchasing additional vessels to support the ridership demand at the current Beach 108th St landing. EDC will share the results of the feasibility study with the community and elected officials by fall of 2018.
Far Rockaway | Pilot car share program in Far Rockaway | 36 | Transportation & Infrastructure | DOT | Done | DOT included Far Rockaway in the launch of the citywide carshare pilot in June 2018. | The Eastern Rockaways is a designated pilot neighborhood for DOT's on-street car share parking pilot. In fall 2017, the city will distribute permits for up to 18 designated curbside spaces in the Eastern Rockaways to participating car share providers. As part of the pilot program, DOT will provide incentives for car share companies to offer discounts and conduct outreach to local NYCHA residents and Section 8 recipients. | 2017–2019 |  | The citywide carshare pilot was launched in June 2018. Carshare companies selected 2 curbside spaces and 1 municipal lot space in the Eastern Rockaways. DOT is working with car share companies to offer discounted services to NYCHA residents and Section 8 recipients.
Far Rockaway | Monitor and, as needed, conduct follow-on traffic studies of the Downtown Far Rockaway area and its environs through the capital program. | 37 | Transportation & Infrastructure | DOT | In Progress | DOT continues to monitor the area to respond to requests and review potential additional safety enhancements through signage and markings. | DOT completed a comprehensive traffic study of Downtown Far Rockaway in 2014. Under the current DOT capital effort, the traffic analysis was updated in 2016 in coordination with the schematic geometric design for the project. DOT will continue to update the analysis through the capital process to ensure we are accurately addressing current traffic conditions. DOT is willing to investigate specific intersections on a case-by-case basis while the capital project is moving through design. | 2017–ongoing |  | DOT conducted extensive traffic analysis of the Downtown Far Rockaway area, with the latest review in 2016 resulting in safety and mobility redesigns for pedestrians, motorists, transit riders and bicyclists that have been incorporated into the street reconstruction and streetscape project. DOT continues to monitor the area to respond to requests and review potential additional safety enhancements through signage and markings.
Far Rockaway | Encourage green infrastructure in all new developments on City-owned sites | 38 | Transportation & Infrastructure | HPD | Done with ongoing work | HPD requires all new construction and substantial rehabilitation projects in the rezoning area that are receiving funding from HPD to comply with the Enterprise Green Communities Criteria. These criteria provide proven, cost-effective standards for creating healthy and energy-efficient homes. | HPD will require all new construction and substantial rehabilitation projects in the rezoning area that are receiving funding from HPD to comply with the Enterprise Green Communities Criteria. These criteria provide proven, cost-effective standards for creating healthy and energy-efficient homes. | 2017–ongoing |  | NYCEDC is in active negotiations with respondents to the Beach 21st Street RFP and selection is anticipated in early summer 2018. This project will deliver a 100% affordable housing development at a range of incomes with retail and community facility space. The RFP required retail and community facility uses that respond to the needs of the community. The project will connect to a new open space plaza at the subway entrance to the A train and provide a more welcoming entranceway to what was historically the downtown commercial corridor of the Rockaway peninsula.
Far Rockaway | Implement immediate short-term measures to address drainage issues in Arverne | 39 | Transportation & Infrastructure | DEP | Done | DEP completed the installation of three new storm sewer extensions in Far Rockaway, Queens. The work completed in this area included the installation of new storm sewers, sanitary sewers, water mains, and catch basins to help improve drainage, reduce localized street flooding and ensure a reliable supply of water for the future. DEP installed new storm sewer infrastructure on B79th Street and Beach Channel Drive, on Bayfield Avenue between B68th Street and B69th Street, and on Alameda Avenue from B68th Street to B69th Street. | In acknowledgement of area drainage issues highlighted by the Council Member, the City will take near-term action to address these conditions, even while evaluating long-term solutions. By Fall 2017, DEP will install two to three new storm sewer extensions, pending the results of a feasibility study to determine optimal locations. By Fall 2017, DOT will assess the area streets for potential resurfacing and/or pothole mitigation. The City will continue to monitor the drainage situation in Arverne and will work with the Council Member to advance near-term and long-term plans. | 2017 |  | DEP completed the installation of three new storm sewer extensions in Far Rockaway in September 2017. This work includes the installation of new storm sewers and catch basins to help improve drainage and reduce localized street flooding. DEP installed new storm sewer infrastructure on B79th Street and Beach Channel Drive, on Bayfield between B68th Street and B69th Street, and on Alameda Avenue from B68th Street to B69th Street.
Far Rockaway | Support the opportunity to bring LinkNYC to Downtown Far Rockaway | 40 | Transportation & Infrastructure | DOT | In Progress | LinkNYC conduits are expected to be installed as part of the street reconstruction and streetscape project. | In order to allow for future installation of Links in Downtown Far Rockaway, the LinkNYC franchisee will coordinate with DOT-DDC and will install the required subsurface infrastructure within the DOT-DDC capital reconstruction project. | 2019–TBD |  | DOT and DDC are working to coordinate infrastructure to support LinkNYC service in the area as part of its streetscape reconstruction project. The preliminary plans for the LinkNYC conduits were included in the streetscaping project.
Far Rockaway | Continue implementation of RISE:NYC program in Far Rockaway | 41 | Transportation & Infrastructure | EDC | Done | Through the RISE : NYC program, the non-profit New America is currently working in partnership with the Rockaway Development and Revitalization Corporation (RDRC) to install a resilient mesh wireless Internet network for Sandy-impacted small businesses in Downtown Far Rockaway and to train the local workforce in its deployment. Installation has been completed for 14 businesses and the network is expected to be fully complete by summer 2019. | With support through RISE:NYC, a company named New America is currently working in partnership with the Rockaway Development and Revitalization Corporation ("RDRC") to install resilient mesh wireless networks for Sandy-impacted small businesses and to train the local workforce in its deployment. Implementation of this project is underway, and the City estimates that approximately 15 businesses will participate in the program. | 2017–ongoing |  | Through the RISE : NYC program, the non-profit New America is currently working in partnership with the Rockaway Development and Revitalization Corporation (RDRC) to install a resilient mesh wireless Internet network for Sandy-impacted small businesses in Downtown Far Rockaway and to train the local workforce in its deployment. The resilient mesh network design has been completed, and installation is scheduled to begin in summer 2018.
Far Rockaway | Advocate for improved MTA bus, subway, and LIRR service | 42 | Transportation & Infrastructure | DOT | Done with ongoing work | As part of the City and State's efforts to implement Congestion Pricing to fund mass transit, DOT will continue working with the MTA and various stakeholders for improved and equitable bus, subway and rail service. This builds on the Vision Zero and mobility projects that the agency constructed in 2017 and 2018 in Eastern Rockaway to improve the accessibility and reliability of transit and the safety of pedestrians to these services. | Building on the March 2017 extension of the Q52 to Beach 54th Street and the upcoming implementation of Select Bus Service on the Q52/Q53 routes this fall, DOT will continue to work with MTA to improve bus service to the Eastern Rockaways and Downtown Far Rockaway. Together with MTA, DOT is evaluating local bus service reliability improvements timed to the Q52/Q53 SBS implementation and considering key Southeast Queens corridors for future SBS upgrades as part of the forthcoming Citywide Transit Plan. The City is also making efforts to improve the affordability of commuter rail service to city residents. Through its representatives on the MTA Board, the City will continue to advocate for lower Long Island Road fares for trips from the Far Rockaway Station to destinations within the five boroughs and for the expansion of City Ticket to Far Rockaway passengers. The City will also advocate alongside the Council Member for improvements to the Far Rockaway LIRR station, improved subway and bus service, and other service improvements in the area. | 2017–ongoing |  | MTA/DOT extended Q52/53 to Beach 54 St. in March 2017 and new SBS service was launched on the route in Fall 2017. The City continues to advocate for transit improvements to and from Eastern Rockaway through its representatives on the MTA Board.
Far Rockaway | Reserve $91 million in Capital Funding for implementation of the Downtown Far Rockaway Redevelopment Project | 43 | Economic Development | EDC | In Progress | EDC, in coordination with other City agencies, is guiding the continued deployment of funds from the $91 million Capital Reserve to advance the goals of the Downtown Far Rockaway Roadmap for Action. EDC updated the Council Member on the utilization of these funds in Fiscal 2019. | As a demonstration of the Administration's commitment to realizing the goals of the Downtown Far Rockaway Roadmap for Action and the Downtown Far Rockaway Redevelopment Project, the City has pledged $91million in Capital Funding for implementation. These funds are reserved to facilitate activation of key underutilized properties within the rezoning area. The City will provide annual updates to Council Member on the utilization of these pledged funds. If, through the course of implementation of the project or by June 2021, there is a surplus of funds remaining AND it is clear that such funds will not be needed and can be repurposed, the City will work in consultation with the Council Member to reprogram funds for other related projects in the area. | 2017–2021 |  | EDC, in coordination with other City agencies, is in the planning stages of deploying funds from the $91 million Capital Reserve to advance the goals of the Downtown Far Rockaway Roadmap for Action. EDC will provide an update to the Council Member on the utilization of these funds in Fiscal Year 2019, after the preliminary capital plan is complete.
Far Rockaway | Establish an Urban Renewal Area to enable mixed-use development | 44 | Economic Development | HPD | Done with ongoing work | HPD established an Urban Renewal Area in Downtown Far Rockaway in September 2017 in order to facilitate new mixed use development that would include up to 1,700 homes. In June 2018, HPD financed the first phase of a planned multi-phase affordable housing development that will include up to two 100% affordable buildings. The first phase included 457 affordable homes along with new commercial and public open space in the heart of Downtown Far Rockaway. Future phases are expected in the coming years. | In order to ensure that development moves forward in Downtown Far Rockaway after years of false-starts, the City will establish an Urban Renewal Area ("URA"). The City projects that approximately 1,700 units of housing can be developed in this URA. While there are several scenarios under which development in the URA may proceed, it is the City's goal to facilitate a compelling mixed-use, mixed-income, phased 100% affordable development. Under the HPD's existing ELLA term sheet, for instance, 70% of those units would be affordable to families earning less than 60% AMI, and under Mix and Match 40-60% of units would be would be affordable to households earning less than 60% AMI with the remainder of units affordable to those earning less than 130% AMI. Both ELLA and Mix and Match term sheets require inclusion of between 20-40% of units targeted to extremely low and very low income households. Should the Mix and Match term sheet be used on the first phase of a development within the URA, HPD commits to financing units affordable to families earning 30% AMI in addition to requiring 10% of units be reserved for formerly homeless families. As described elsewhere in this document, the City intends to reserve space within the URA for various desired uses such as a potential school, potential community facility use, and potential business incubator space. | 2017–ongoing |  | HPD established an Urban Renewal Area in Downtown Far Rockaway in September 2017 in order to facilitate new mixed use development that would include up to 1,700 units of housing. HPD is working with a developer on the first phase of a planned multi-phase affordable housing development that will be up to two 100% affordable buildings. The first phase is expected to close in June 2018 and is expected to bring approximately 450 affordable units along with new commercial space and public open space to the heart of Downtown Far Rockaway. Future phases are expected in the coming years that could enable up to 1,700 apartments to be built.
Far Rockaway | Complete Commercial District Needs Assessment, including BID feasibility study | 45 | Economic Development | SBS | Done with ongoing work | The Commercial District Needs Assessment was conducted between November 2018 and May 2019. Merchant and consumer surveys were conducted through the end of March. Data collection was completed on April 15. A merchant and consumer workshop was held on April 25 hosted by community partners where SBS presented on the preliminary findings of the Commercial District Needs Assessment. Merchants and consumers were engaged to participate in a strategy generation exercise to address issues in Downtown Far Rockaway. SBS, along with other city agencies, presented to Councilmember Richards' Communiity Working Group on April 30 and presented to Community Board 14 on May 14. SBS hosted a second merchant and consumer workshop on May 30. The final report is scheduled to be released in the summer 2019. The final report and Downtown Far Rockaway N360° Grant is scheduled to be released in the summer of 2019. | SBS will conduct a Commercial District Needs Assessment (CDNA) to look at the existing storefront business landscape in the neighborhood, including the retail vacancy rate, retail mix, retail leakage, physical conditions, and unique character of the commercial corridors and local businesses. | 2017–2018 |  | A Commercial District Needs Assessment (CDNA) is a tool aimed at helping SBS and our local partners gain an in-depth and comprehensive understanding of the current strengths, needs, challenges, and opportunities of neighborhood commercial corridors. SBS will conduct a CDNA of Downtown Far Rockaway in partnership with local organizations and the Councilmember’s Office. SBS anticipates that the CDNA will begin in Summer 2018. The CDNA will highlight the neighborhood’s business landscape, consumer characteristics, physical environment, and demographic data. Examples of completed CDNAs can be found at www.nyc.gov/neighborhood360.
Far Rockaway | Provide services for new businesses in Far Rockaway | 46 | Economic Development | SBS | Done with ongoing work | Through the work of Chamber On the Go and the Mobile Outreach Unit, SBS is working collaboratively with Council Member Richards' office to directly engage with local business owners to determine their needs and tailor our services accordingly. | SBS will work with the Council Member's Office to encourage local business owners and aspiring entrepreneurs to apply and participate in the full suite of FastTrac NewVenture and FastTrac Growth Venture business incubation workshops in Downtown Far Rockaway in collaboration with local community organizations such as the Queens Public Library. | 2017–2018 |  | SBS is committed to making business services available to Downtown Far Rockaway small business owners. SBS is currently working with Council Member Richards’s Office, City Hall, and other community partners to expand outreach in DTFR to further determine the needs of the business community and tailor our services to those needs.
Far Rockaway | Explore potential business incubation space in Far Rockaway to support area businesses | 47 | Economic Development | SBS | Done with ongoing work | Through the outreach work of Neighborhood 360, Chamber On the Go, and the Mobile Outreach Unit, SBS is reaching local business owners to provide services in the community. SBS will continue to partner with local stakeholders to determine and subsequently meet the needs of small business owners in Downtown Far Rockaway. | Working through SBS and/or NYCEDC, the City will assess the current business landscape and identify the space and programming that would be most appropriate and relevant to area businesses. In spring 2018, the City will report back to the Council Member on a suggested course of action, which could include additional resources for existing programs, the release an RFEI seeking proposals from operators, or other strategies. | 2018 |  | Through the outreach work of Chamber On the Go and the Mobile Outreach Unit, SBS is reaching local business owners to provide services in the community. SBS will continue to partner with local stakeholders to determine and subsequently meet the needs of small business owners in Downtown Far Rockaway.
Far Rockaway | Support existing businesses through free legal services and other business outreach efforts | 48 | Economic Development | SBS | Done with ongoing work | Through the data collected during work on our Commercial District Needs Assessment, SBS connected several business owners to our various suite of services. In addition, SBS helped businesses prepare for upcoming Department of Design and Construction street improvement project. | In Downtown Far Rockaway, SBS will conduct door-to-door engagement with business owners and provide services in Far Rockaway to meet business needs through Chamber-on-the-Go. SBS will roll out additional entrepreneurship education programs for immigrant and women-owned businesses, including Women Entrepreneurs NYC (WENYC) workshops on credit, funding, and leadership, in addition to one-on-one financial counseling and mentorship sessions. SBS will continue to monitor needs and provide appropriate entrepreneurship resources in coordination with community partners such as the Queens Public Library. Finally, SBS will work with business owners in Downtown Far Rockaway to coordinate consultation visits from our Compliance Advisors, who educate business owners on how to avoid the most commonly issued City violations. | 2017–TBD** |  | In partnership with the Queens Chamber of Commerce and Council Member Richards's office, SBS conducted a Chamber On the Go visit in November 2017. Chamber On the Go staff provided door-to-door outreach to businesses along Mott Avenue in order to connect these businesses to SBS services; such as financing assistance, legal assistance, and help navigating government. In December 2017, SBS’s Mobile Outreach Unit visited the Mott Avenue shopping center to provide services to businesses on-site. SBS will continue to assess needs and provide resources to Far Rockaway small businesses.
Far Rockaway | Support area M/WBEs | 49 | Economic Development | SBS | In Progress | SBS conducted several outreach events in Far Rockaway to provide connections to our services including M/WBE certification and capacity building resources. SBS will look for additional opportunities to provide these services moving forward in Far Rockaway. | SBS will work with the Council Member to host M/WBE certification events in the district. In addition, it will provide a number of capacity building services to M/WBE business owners in Downtown Far Rockaway. These include certifying firms with contract financing assistance, business courses, one-on-one technical assistance, networking and educational events, assistance with obtaining bonds, and access to City and private sector contracting opportunities. Residents of Far Rockaway can access these opportunities by calling the Certification Helpline or visiting any one of the seven NYC Business Solutions Centers, including the NYC Small Business Support Center located in Jamaica. | 2017–TBD** |  | SBS held a M/WBE (Minority/ Women Owned Business Enterprise) certification workshop in March 2018 in partnership with Councilmember Richards’s office. SBS presented on LBE Certification (Locally Based Enterprise), EBE Certification (Emerging Business Enterprise), and M/WBE Certification. SBS also provided information on Procurement Technical Assistance Center (PTAC) services, the Bond Collateral Fund, and the Contract Financing Loan Fund. SBS plans to use the Mobile Outreach Unit to reach more Rockaway residents through a Selling to Government Express workshop in the summer of 2018. M/WBEs and other entrepreneurs in Far Rockaway can access these opportunities on a regular basis by calling the Certification Helpline- 212-513-6311- or visiting any one of the seven NYC Business Solutions Centers, including the NYC Small Business Support Center located in Jamaica at 90-27 Sutphin Boulevard, 4th Floor Jamaica, NY 11435
Far Rockaway | Expand opportunities for M/WBEs in the affordable housing development industry | 50 | Economic Development | HPD | Done with ongoing work | HPD has services and programs to support M/WBEs and create a pathway for smaller businesses to build capacity. The M/WBE Build Up Program requires development projects receiving $2 million or more in City contribution to utilize M/WBE construction or professional firms. In addition, under HNY, 15 out of 74 public site designations went to M/WBEs, six of whom were through the our M/WBE RFP. In 2019, HPD began year four of its Developer Capacity Building Program, which provides courses and networking opportunities to M/WBE developers. | HPD's new M/WBE Build Up Program requires developers of projects where HPD contributes $2 million or more in subsidy to spend at least a quarter of all HPD-supported costs on certified M/WBE construction, design, or professional service firms. HPD will partner with the Council Member to hold a networking and outreach event for M/WBE and small businesses by the spring of 2018 with the intent of identifying possible opportunities for these businesses to work on HPD-supported affordable housing projects in Downtown Far Rockaway. | 2018 |  | HPD has nearly met or exceeded all M/WBE utilization goals in our breakout categories by type of service and expanded services/programs to support M/WBEs. Our RFPs now give preference for local community experience and a pathway for smaller businesses to build up capacity. The M/WBE Build Up Program requirements now apply to 42 projects and are expected to generate over $177 million in spending to MWBE vendors. Twelve out of 53 public site designations were awarded to M/WBEs, 6 of whom were selected through the M/WBE RFP. HPD also completed year three of our Developer Capacity Building Program which provides courses and networking opportunities to M/WBE developers.
Far Rockaway | Require HPD RFP respondents to implement a targeted hiring outreach plan | 51 | Economic Development | HPD | Done with ongoing work | In all Requests for Proposals for the development of City-owned property, respondents must demonstrate a plan for outreach to residents of the local community district related to employment opportunities generated by the proposed project. Outreach may be demonstrated by activities such as training programs, job placement activities, the applicants' own staffing practices, and/or the applicants' contracting practices. Applicants will be required to comply with their outreach plans and report regularly on outreach activities | HPD will require respondents to any HPD RFPs in Downtown Far Rockaway to demonstrate a plan for targeted employment outreach to residents of the Rockaways related to the proposed project(s). Applicants will be required to comply with and report on their outreach. | 2017–ongoing |  | In all Requests for Proposals for the development of City-owned property, respondents must demonstrate a plan for outreach to residents of the local community district related to employment opportunities generated by the proposed project. Outreach may be demonstrated by activities such as training programs, job placement activities, the applicants' own staffing practices, and/or the applicants' contracting practices. Applicants will be required to comply with their outreach plans and report regularly on outreach activities
Far Rockaway | Require developers, general contractors, and subcontractors on major projects in Downtown Far Rockaway to use HireNYC | 52 | Economic Development | HPD | Done with ongoing work | All firms working on HPD and other City projects receiving more than $1 million in City subsidy ($2 million from HPD) must comply with the City’s HireNYC program. This requires them to source job placements for entry- and mid-level construction positions from the Workforce1 system, including the Rockaway Workforce1 Center in Arverne, and interview any qualified candidates. | All firms working on HPD and other City projects receiving more than $1 million in City subsidy ($2 million from HPD) are required to share job openings in entry- and mid-level construction positions with HireNYC, post at the local Workforce1 Center in Arverne, and interview any qualified candidates. | 2017–ongoing |  | All firms working on HPD and other City projects receiving more than $1 million in City subsidy ($2 million from HPD) must comply with the City’s HireNYC program. This requires them to source job placements for entry- and mid-level construction positions from the Workforce1 system, including the Rockaway Workforce1 Center in Arverne, and interview any qualified candidates.
Far Rockaway | Promote local hiring and job opportunities for area residents | 53 | Economic Development | SBS | Done with ongoing work | SBS hosts monthly meetings at the Rockaway Workforce 1 Center on the third Thursday of each month in partnership with community partner organizations to discuss best practices and to develop strategies to better connect Far Rockaway residents with workforce opportunities. Through the work of our Mobile Outreach Unit, Small Business Services will continue to engage with community based organizations and jobseekers in Far Rockaway. | SBS will host monthly meetings at the Rockaway Workforce1 Center with community partners, including Rockaway Development & Revitalization Corporation (RDRC) and Ocean Bay Community Development Corporation, to connect Far Rockaway residents with workforce opportunities. Building on existing services, SBS will enhance outreach to the local community including quarterly recruiting events with various community partners such as faith based organization, the Queens Public Library, and other groups. | 2017–TBD** |  | To serve job seekers, SBS operates a network of 21 Workforce1 Career Centers, including one in Rockaway, located at 57-17 Shore Front Parkway in Arverne. To connect Far Rockaway residents with these resources, SBS works with over 35 community partners in Downtown Far Rockaway to connect residents to job opportunities and other services that combat barriers to employment. This group meets monthly on the third Thursday of the month.
Greater East Midtown | Establish the East Midtown Governing Group and fund up to $38 million in City Capital for capital-eligible public realm projects, to be selected by the Governing Group | 1 | Transportation & Infrastructure | DOT | Done with ongoing work | DOT and DDC continue to work with the East Midtown Governing Group, and will provide updates as current projects progress through design. | A commitment of $38M in City Capital for capital eligible public realm projects selected by the East Midtown Governing Group. The above-mentioned public realm projects will be subject to consultation with relevant stakeholders, including the Governing Group, and will take into account the needs of property and business owners along the street. Project selection and design will incorporate the needs for overall circulation, transit connections, building and loading dock access, pick-up and drop-offs, parking, sanitation, deliveries, ADA accessibility, emergency access, and utilities. | 2017-2018 |  | As of May 2018, the Governing Group has allocated $34 million to fund three capital projects to construct permanent public realm enhancements in East Midtown: a pedestrian plaza at Pershing Square East ($15 million), thoroughfare improvements along Lexington Avenue between 41st and 48th Streets ($12.8 million), and security upgrades at the forthcoming 43rd Street shared street ($6.2 million). The Governing Group will continue to meet and explore additional opportunities for the remaining funding. Discussions with Community Board 6 continue on the exact treatments and location of thoroughfare improvements along Lexington Avenue.
Greater East Midtown | Advance five upfront public realm improvement projects in the East Midtown area | 2 | Open Space | DOT | In Progress | The planned rehabilitation of the Grand Central Terminal train shed presents the possibility of transformational public realm improvements along Park Avenue. Based on the scale of the planned work along the corridor, the City will delay any immediate changes to the street patterns and will collaborate with Metro North and local stakeholders on next steps. Due to complexities, the timeline has been extended. | Through the completion of upfront capital commitments (estimated cost of up to $12M), including: * A permanent shared street on 43rd Street between Lexington and 3rd Avenue * Designation of Pershing East as a pedestrian plaza and a refresh of the space * Thoroughfare improvements on 53rd Street between 2nd and 5th Avenues * Improvements to Park Avenue traffic patterns through turn lane upgrades * Improvements to Lexington Avenue at 43rd Street | 2017-2019 |  | The administration has funded $12 million for the construction of a permanent shared street on 43rd Street and improvements to Lexington Avenue at 43rd and 44th Streets. DOT expects preliminary design to begin in fall 2018. In addition, earlier this year, DOT designated Pershing Square East as a public plaza, and is working with community stakeholders to install interim treatments at 43rd Street, Pershing Square East, 53rd Street, and Park Avenue. DOT is currently engaging with Community Boards on the proposed interim treatments.
Greater East Midtown | Continue engagement with Greenacre Foundation regarding development within the vicinity of Greenacre Park | 3 | Open Space | DCP | Done with ongoing work | DCP met with the Greenacre Foundation (GF) on March 28, 2018. The discussion focused on GF's analysis regarding possible shadow impacts from potential development east of the Greater East Midtown rezoning area. | Greenacre Park is a gem of a public space situated in East Midtown and a valuable asset for workers, residents, and visitors alike. As such, DCP will do the following for development that occurs within the radius of Greenacre Park (as identified by the Greenacre Foundation): 1. DCP will send the Greenacre Foundation any filed application for any zoning actions pursuant to the East Midtown rezoning at the same time it is sent to the Community Board; 2. DCP will inform any such applicant to discuss its development plans with the Greenacre Foundation; and 3. DCP commits to again meet with Greenacre Foundation to discuss potential shadow impacts from development both within and outside this rezoning plan. | 2017-ongoing |  | DCP met with the Greenacre Foundation (GF) on March 28, 2018. The discussion focused on the GF's analysis regarding possible shadow impacts from potential development east of the Greater East Midtown rezoning area.
Greater East Midtown | Meet with American Jewish Committee on East Midtown rezoning district boundaries | 4 | Community Resources | DCP | Done | DCP met with the American Jewish Committee (AJC) on November 28, 2017. The discussion focused on AJC’s interest to have the East Midtown Subdistrict boundary amended to include its property at 165 East 56 Street. DCP conveyed that this would require a text amendment to the Zoning Resolution and explained the necessary process to pursue a text amendment. | The American Jewish Committee owns a site at 165 East 56 Street that is immediately adjacent to the northern edge of the rezoning district. AJC has expressed interest in having that site included in the rezoning, and DCP commits to meeting with them to discuss AJC's interest in a follow-up action that would amend the district boundaries to include that site. | 2017 |  | DCP met with the American Jewish Committee (AJC) on November 28, 2017. The AJC discussed its interest to have the East Midtown Subdistrict boundary amended to include its property at 165 East 56 Street and DCP explained the process of a private application for a text amendment to the Zoning Resolution.
Greater East Midtown | Report on residential conversion activity in East Midtown | 5 | Housing | DCP | In Progress | DCP will release its three-year report on residential conversion activity in East Midtown in August 2020. | We have not seen evidence that the ability for owners to convert their properties to residential uses as-of-right poses issues for this area. Nonetheless at your request, DCP will report back to the Manhattan Borough President's Office and the City Council on the prevalence of residential conversions and any associated impacts in the rezoning boundaries in both 3 years and 5 years time. | 2017-2022 |  | The City will release its three-year report on August 9, 2020.
Inwood | Advance affordable housing development on publicly-owned land | 1 | Housing | HPD |  | HPD has partnered with The New York Public Library (NYPL) to redevelop the Inwood Library site at 4790 Broadway. The project will result in the construction of a new 20,000 square foot modern library branch, combined with approximately 175 affordable apartments, Universal Pre-K classrooms, and community facility space. The City has designated a development team, led by Community League of the Heights (CLOTH), The Children’s Village, Ranger Properties, and Alembic Community Development, to construct and operate the new building. The community will have access to a temporary library space at 4857 Broadway during construction, and NYPL has committed to providing all core services at the temporary site including circulation of materials, computer appointments, readers’ advisory, and reference. Construction of the new building will begin in early 2020. Dyckman Houses: On a site within NYCHA’s Dyckman Houses, NYCHA will engage with Dyckman residents on the planning of a new residential building and subsequent issuance of an RFP for the development of approximately 180-250 units of 100% affordable housing, in addition to space for community services. Such housing will include housing for seniors, subject to feedback from the Dyckman Houses residents and financing feasibility. There will be a 25% preference for NYCHA residents for all new affordable housing units, and NYCHA will encourage residents living in oversized homes in Dyckman Houses to apply for apartments in the new building, thus making new public housing units available. NYCHA will continue to engage residents of Dyckman Houses this fall to identify detailed development goals and needed community services. In the course of the engagement process, NYCHA will work to identify priorities for improving campus amenities, including the playgrounds at Dyckman Houses. DOT Bridge Repair Facility: The City will issue an RFP to redevelop the DOT bridge repair facility at West 206th Street for affordable housing. Development plans for the site will include DOT relocation to Fordham Landing (300 W Fordham Road - Block 3231, Lot 350), including reconstruction of the facility for DOT with the same square footage of DOT’s West 206th Street site and build-out for operations comparable to the West 206th Street site. In addition, the building will be elevated to allow the same square footage of staging, storage, and operations below. Development will be subsequent to relocation of DOT services and is subject to any necessary Council and other land use approvals on the Fordham and Inwood sites. 4095 Ninth Ave site is a new lot created by reconfiguring two existing irregularly shaped lots owned by the City and Charter Communications, and currently used as a parking lot. The City will issue an RFP for the development of this site, which will include approximately 570 units of affordable housing, in addition to an Inwood Innovation Hub focused on STEM Talent Solutions. The site will also include publicly accessible waterfront open space, as required by zoning. The 4095 Ninth Avenue RFP is anticipated to be issued in 2020. | The city will issue an RFP to redevelop the DOT bridge repair facility at West 206th Street, for affordable housing. Development plans for the site will include DOT relocation to Fordham Landing (300 W Fordham Road - Block 3231, Lot 350), including reconstruction of the facility for DOT with the same square footage of DOT’s West 206th Street site and build-out for operations comparable to the West 206th Street site. In addition the building will be elevated to allow the same square footage of staging, storage and operations below. Development will be subsequent to relocation of DOT services and is subject to any necessary Council and other land use approvals on the Fordham site and Inwood sites. | ongoing
Inwood | Explore additional potential opportunities for affordable housing on public land | 2 | Housing | HPD | Not Started | Upon relocation of DSNY Manhattan CD 8 operations to the Brookdale garage, the City will study the feasibility of redeveloping the Manhattan CD 8 garage site. Redevelopment may include consolidating remaining Inwood garages and/or consolidation of other City uses within the rezoning area to allow for an additional mixed-use development that would include affordable housing and other potential uses. | When the City relocates the Manhattan CD 8 Sanitation Garage to the Brookdale site in Manhattan (the block bounded by East 25-26th Streets, First Avenue, and the FDR Drive), the existing sanitation facility on West 215th Street and 10th Avenue will be redeveloped to facilitate the creation of affordable housing. Upon relocation of DSNY Manhattan CD 8 operations to the Brookdale garage, the City commits to studying the feasibility of redeveloping the Manhattan CD8 garage site. Redevelopment may include consolidating remaining Inwood garages and/or consolidation of other City uses within the rezoning area to allow for an additional mixed-use development that would include affordable housing and other potential uses. | ongoing
Inwood | Advance preservation projects in City-owned Buildings | 3 | Housing | HPD | In Progress | HPD is committed to the rehabilitation of vacant and occupied City-owned residential buildings in the neighborhood. In partnership with local non-profits, Community League of the Heights (CLOTH) and the Northern Manhattan Improvement Corporation (NMIC), HPD is prioritizing the renovation of two vacant City-owned buildings at 2110 Amsterdam and 21 Arden Street, respectively. HPD closed on a construction loan for 21 Arden Street, and the building left City ownership in January 2019. As of June 2019, construction is underway in the building. Tenants are currently being engaged to begin their cooperative homeownership trainings. HPD is additionally working with CLOTH to advance renovations of 2185 and 2110 Amsterdam Avenue, as well as two other City-owned buildings. Construction is anticipated to begin in July 2019. HPD will work with tenants and the local council member to advance Affordable Neighborhood Cooperative Program (ANCP) projects in all remaining Tenant Interim Lease (TIL) properties in Council District 10. | HPD is committed to the rehabilitation of vacant and occupied City-owned residential buildings in the neighborhood. In partnership with local nonprofits, Community League of the Heights (CLOTH) and the Northern Manhattan Improvement Corporation (NMIC), HPD is prioritizing the renovation of two vacant City-owned buildings at 2110 Amsterdam and 21 Arden Street, respectively. HPD will work with tenants and the local councilmember to advance Affordable Neighborhood Cooperative Program (ANCP) projects in all remaining Tenant Interim Lease (TIL) properties in Council District 10. | Fy2019-fy2021
Inwood | Open a SUS Homebase Office in Washington Heights | 4 | Housing | HRA | Done | The SUS Homebase Office opened in December 2018. | Services for the Underserved (SUS), a provider of homeless services through the HRA Homebase program, will open an office in Washington Heights in August of 2018. A cornerstone of the City’s homelessness prevention strategy and the first point of entry for New Yorkers at risk of homelessness, Homebase was launched in 2004. The program was dramatically expanded by the De Blasio administration, which increased the number of locations and doubled the program’s funding. The Homebase program crafts individualized service plans that can contain eviction prevention, tenant/landlord services, assistance with relocation, employment and training, household financial assistance, rental assistance screening and application, as well as referrals to other programs. Homebase will also have regular satellite office hours in another local service location where community members can receive housing advice, enroll in Homebase, and receive housing-related referrals. Homebase also offers aftercare services to all households leaving shelter through a rental assistance program, followed by a thorough assessment, the development of an individualized service plan, and intensive services for the most at-risk households. HRA workers are onsite to assist with the tenants’ public benefits issues and emergency rent arrears grant applications. Homebase also offers regular workshops, inviting at-risk community members, including former shelter residents, and providing information on affordable housing, subsidies, employment, work supports, and financial empowerment. SUS will work with local groups to ensure Homebase services reach all of Community District 12. | 2018-09-01
Inwood | Help community organizations acquire rent stabilized buildings through the Neighborhood Pillars Program | 5 | Housing | HPD | In Progress | HPD and HDC announced the Neighborhood Pillars program in fall 2017 to finance the acquisition and rehabilitation of existing rent-regulated buildings to protect current tenants and stabilize communities. HPD released a Preservation Buyers Request for Qualifications (RFQ), and responses from organizations interested in participating are accepted on a rolling basis. HPD launched the Downpayment Assistance Fund and issued a new financing program term sheet in late 2018. The City expects to support the acquisition of a half dozen or more properties across New York City by fall 2019. | HPD and New York Housing Development Corporation (HDC) are launching a new Neighborhood Pillars program to finance the acquisition and rehabilitation of existing rent-regulated buildings to protect current tenants and stabilize communities. The City will double the capacity of the Acquisition Loan Fund to $275 million to enable non-profits and mission-based organizations to acquire buildings that are rent-regulated, but not otherwise part of an existing affordable housing program. | FY2019 Launch
Inwood | Include Inwood, Washington Heights, and Marble Hill in the new "Partners of Preservation" initiative to develop a comprehensive neighborhood anti-displacement strategy | 6 | Housing | HPD | In Progress | HPD launched its new Partners in Preservation pilot program in Inwood, Washington Heights, and Marble Hill (Manhattan CD 12 and a portion of Bronx CD 8) in the spring of 2019. Through the program, HPD seeks to proactively prevent tenant harassment by jointly developing anti-displacement strategies with tenant organizing groups, legal service providers, and other government agencies. With funding from the New York City Housing Development Corporation and Enterprise Community Partners, tenant organizers will target at-risk buildings for strategic, tenant-led interventions and create a neighborhood-wide anti-displacement plan. Northern Manhattan Improvement Corporation will receive $490,000 to implement the program in Inwood, Washington Heights, and Marble Hill in partnership with Community League of the Heights, Inwood Community Services, and Goddard Riverside Community Center, as well as other community-based organizations and legal service providers. The pilot program will run for 18 months. | HPD will include Inwood, Washington Heights, and Marble Hill in its new Partners in Preservation initiative and launch a Preservation Action Center that will serve as a hub for neighborhood-based anti-displacement initiatives. HPD will pair agency data with the on-the-ground experience and work of community-based organizations, legal services providers and HRA’s Office of Civil Justice, Council Members and other elected officials, the City’s Tenant Support Unit (TSU), and local stakeholders to advance a comprehensive anti-displacement plan for the Inwood area. • Coordination: HPD and partner organizations will implement action plans in close coordination with tenant organizers, legal service providers, TSU, HRA, and other government agencies. • Tenant organizing: This initiative will leverage funding for tenant organizers to partner with HPD to develop and implement building action plans. • Meeting frequency: HPD will convene regular project management/coordination meetings with all partners, and it will meet every two months or upon request with local Council Members’ offices. • Data sharing: Affordable housing data, including preserved and newly constructed homes with affordability levels and homes at risk of deregulation, as well as updates on the implementation of building action plans, will be shared with the Council Members at meetings every two months or upon request. | Q1 2019 Launch (1 year pilot)
Inwood | Facilitate the consolidation of Con Edison infrastructure to free up sites for mixed-use development, including affordable housing, in the Sherman Creek Area | 7 | Housing | EDC | In Progress | Con Edison is advancing design of the new operations facility, which will be located on two blocks along the Harlem River waterfront between West 202nd and 204th Streets. In early 2019, the Public Design Commission approved the design of a vehicular bridge that will connect two parts of the facility. In 2020, Con Edison will release Requests for Proposals for the redevelopment of several of its Sherman Creek properties that it will no longer need once the new facility is completed. Completion of this commitment depends on a set of property transactions between the City and Con Ed that are still in progress. | Con Edison currently owns six sites in the Sherman Creek area between West 202nd and West 205th Streets that are included in the rezoning area. With the rezoning, Con Edison will be able to consolidate a new planned operations facility on the two parcels located between West 202nd and West 204th Streets east of 9th Avenue. This will free up the remaining Con Edison lots to be sold for mixed-use development by others, subject to New York State Public Service Commission (“PSC”) approval. These sites are mapped in the Mandatory Inclusionary Housing (MIH) Area, and any residential development will be required to provide a portion of permanently affordable housing. Con Edison’s written testimony from the City Council’s public hearing on the Inwood Rezoning is attached as Exhibit X. | 2020
Inwood | Support mission‐driven groups interested in developing affordable housing on underutilized sites | 8 | Housing | HPD | In Progress | HPD continues to steer mission-driven groups to the Pre-Qualified List of Owner's Representatives and NYC Acquisition Fund for the furtherance of their affordable housing initiatives. Since the launch of Housing New York, HPD has financed 17 projects, comprising more than 2,500 affordable homes, with faith-based organizations as development partners; more than 30 additional projects are in various stages of discussion. HPD’s collaboration with LISC on the New York Land Opportunity Program (NYLOP), has resulted to date in three of four participating churches signing agreements to form joint ventures with affordable housing developers. As part of Housing New York 2.0, HPD launched the Neighborhood Pillars program to provide funding for non-profits to purchase privately-owned buildings and keep or make them affordable. Additionally, 55% of our public site designations have gone to nonprofits, either as sole developers (15) or joint ventures with for-profits (28). This includes the Inwood Library development project, which is being developed by a team led by non-profit Community League of the Heights (CLOTH). | Inwood residents and stakeholders expressed a desire to see more participation by mission-driven organizations in affordable housing development and preservation. To assist those interested in affordable housing, HPD will work with local faith-based organizations to explore development opportunities. HPD maintains a Pre-Qualified List of Owner’s Representatives to help mission-driven organizations who may have underutilized land but little to no real estate experience. In creating the list, HPD evaluated each organization’s technical expertise, experience, and capacity to represent owners in the development of affordable housing. Additionally, HPD will implement recent RFP reforms for future public site RFPs in Inwood, including a new preference for community development plans and experience; recognition of development experience in rehabilitation; and the use of a remainder interest, which is a legal tool that gives the City ownership of the property at the end of the initial affordability period unless HPD and the owner agree on an extension. | Ongoing
Inwood | Make it easier for residents to understand, prepare for, and complete the affordable housing application process | 10 | Housing | HPD | Done with ongoing work | HPD continues to take steps to help residents become better prepared to submit complete and accurate applications. In addition to revamping its affordable housing application and lottery education materials, HPD has trained staff from Community League of the Heights (CLOTH) to serve as a Housing Ambassador for the Inwood neighborhood. Housing Ambassadors help people prepare and apply for Housing Connect affordable housing lotteries. | HPD continues to take steps to help residents become better prepared to submit complete and accurate applications. In addition to revamping its affordable housing application and lottery education materials, HPD will recruit and train Housing Ambassadors in the Inwood area, which are local community groups that provide free technical assistance to residents who wish to apply for affordable housing. | Ongoing
Inwood | Keep homes affordable by continuing to offer loans and tax incentives to building owners | 11 | Housing | HPD | Done with ongoing work | Since 2014, HPD has financed the preservation of 445 affordable homes in CD 12. HPD will continue monitoring homes in CD 12 with affordability restrictions in its portfolio and use its various financing programs to preserve and invest in the neighborhood’s existing affordable housing stock. HPD will strive to preserve the affordability of as many homes as possible in Inwood and Washington Heights through 2026. | Since 2014, HPD has financed the preservation of 445 affordable homes in Community District 12. HPD will continue monitoring homes in Community District 12 with affordability restrictions in its portfolio and use its various financing programs to preserve and invest in the neighborhood’s existing affordable housing stock. HPD will strive to preserve the affordability of as many homes as possible in Inwood and Washington Heights through 2026 | Ongoing
Inwood | Establish a “Certification of No Harassment” (CONH) Pilot Program | 12 | Housing | HPD | In Progress | HPD received funding in the FY 2019 budget to implement the pilot Certification of No Harassment (CONH) program in designated neighborhoods, including Inwood and Washington Heights, to protect tenants from being harassed from their homes. Owners of designated buildings are be required to obtain a CONH before being granted building permits for specified covered work in the buildings. The program launched in fall 2018. In Inwood and Washington Heights, 144 buildings are subject to the program, and HPD has received seven CONH applications since the program went into effect. | In response to feedback from the community and growing interest across the city, the Administration will enforce a pilot CONH program in designated neighborhoods, including CD 12, to protect certain tenants from being harassed from their homes. This program will identify specific buildings which meet criteria indicating that tenants may be at risk for harassment. Owners of such buildings will be required to obtain a CONH before being granted building permits for specified covered work in the buildings. Community groups, under contract with HPD and identified through a Request for Proposals (RFP), will investigate buildings that apply for CONHs. | September 2018 - September 2021
Inwood | Pilot a Landlord Ambassadors Program to provide technical assistance to Inwood property owners | 12 | Housing | HPD | In Progress | Since June 2017, HPD has partnered with Enterprise Community Partners and community-based organizations to pilot a two year demonstration program called the Landlord Ambassadors Program. Organizations have been conducting outreach and providing technical assistance to owners of multifamily buildings in specific communities throughout the city, including Inwood. Since the pilot began, 77 property owners have participated, 39 have applied for HPD financing, and seven have closed on construction financing. With the Ambassadors help, active properties have decreased their violations by 42% and reduced municipal arrears by 21%. HPD has recently secured some funding to continue the pilot and expand it citywide, including in the Southwest Bronx. The Mutual Housing Association of New York (MHANY), a pilot program Ambassador, and Habitat for Humanity have recently requested City Council Discretionary funding to expand their services citywide, increase the number of property owners assisted, and expand the scope of services for new and currently participating owners. MHANY will continue working with local property owners to provide information about the benefits of using HPD financing programs; navigate HPD program requirements, including regulatory requirements; and package application materials for HPD review and approval. | HPD is partnering with Enterprise Community Partners to pilot a Landlord Ambassadors Program to contract with community-based organizations who will conduct outreach and provide technical assistance to owners of multifamily buildings in targeted areas across the city. The selected Landlord Ambassador for Inwood, Mutual Housing Association of New York (MHANY) will work with local property owners to: • Provide information about the benefits of using HPD financing programs; • Navigate HPD program requirements, including regulatory requirements, and package application materials for HPD review and approval; and • Access local resources and vendors needed in order to close, construct, and operate their properties, including contractors, property managers, attorneys, and other professionals. | FY2019-FY2021
Inwood | Host outreach and marketing events to promote programs that help owners make repairs and preserve affordability | 13 | Housing | HPD | In Progress | Since 2014, HPD has financed the preservation of 769 affordable homes in Community District 12. HPD will continue monitoring homes in Community District 12 with affordability restrictions in its portfolio and use its various financing programs to preserve and invest in the neighborhood’s existing affordable housing stock. HPD will strive to preserve the affordability of as many homes as possible in Inwood and Washington Heights through 2026 | HPD will continue its targeted outreach to property owners, including through events, mailings, emails, calls, and surveying of distressed properties. HPD currently hosts monthly Property Owners Clinics at its downtown location, where building owners can consult one-on-one with HPD preservation finance specialists and representatives from Department of Buildings (DOB), Department of Finance (DOF), and Department of Environmental Protection (DEP). HPD will target outreach for its monthly Property Owner Clinics – including via calls, mailings, and e-mails – to owners in the Inwood area. | ongoing
Inwood | Create a new Tenant Anti-Harassment Unit at HPD to investigate construction and maintenance harassment | 14 | Housing | HPD | In Progress | The newly established Tenant Anti-Harassment Unit will have eight dedicated staff, including two attorneys to initiate litigation, which may include a claim of harassment, against unscrupulous owners and landlords. The new Unit will use data analysis to identify potential buildings and portfolios where harassment is occurring; respond to emergency complaints; partner closely with the Department of Buildings and other agencies to address issues in buildings where maintenance as harassment has been identified; and connect tenants with legal services resources. The new Unit will enable HPD to increase the number of buildings with potential maintenance harassment that HPD can inspect from 200 buildings annually to approximately 1,500 buildings. HPD will also seek civil penalties for harassment where warranted. HPD expects to launch the Unit in summer 2019. | The newly established Tenant Anti-Harassment Unit will have 10 dedicated staff, including two attorneys to initiate litigation, which may include a claim of harassment, against unscrupulous owners and landlords. The new Unit will use data analysis to identify potential buildings and portfolios where harassment is occurring; respond to emergency complaints; partner closely with the Department of Buildings and other agencies to address issues in buildings where maintenance as harassment has been identified; and connect tenants with legal services resources. The new Unit will enable HPD to increase the number of buildings with potential construction or maintenance harassment that HPD can inspect from 200 buildings annually to approximately 1,500 buildings. HPD will also seek civil penalties for harassment where warranted | Fy2019
Inwood | Incentivize the development of deeply affordable housing that exceeds minimum MIH requirements | 14 | Housing | HPD | In Progress | HPD is currently working with multiple Inwood property owners to facilitate the creation of affordable housing that exceeds MIH requirements, prioritizing the creation of deeply affordable homes. HPD-financed projects in the rezoning area will create hundreds of new affordable homes. | HPD will work with Inwood property owners to facilitate the creation of affordable housing that exceeds MIH requirements, prioritizing the creation of deeply affordable homes. HPD recently updated its financing terms for its Extremely Low- and Low-Income Affordability (ELLA) and Mix and Match programs to enable deeper affordability levels and to set aside homes for formerly homeless households. Additionally, any MIH project receiving City subsidy must now provide 15% more permanently affordable homes than required by the MIH program alone. Housing developments financed by HPD, greater than 45 homes, will include at least 10% of all homes for families earning less than 30% of the Area Median Income (AMI), and an additional 10% for families earning at or below 50% of AMI. Several property owners in the Inwood area have already committed to using City financing to develop affordable housing, including senior housing, that exceeds the minimum MIH requirements. Development of additional affordable housing on these sites will require the continued partnership of these private owners. | Ongoing
Inwood | Continue to provide robust free legal representation to tenants | 15 | Housing | HRA | Done with ongoing work | Since July 2015, the City has provided 4,424 households with legal services in Inwood; this includes over 11,070 adults of which 2,958 were children. Between Fiscal Year 2013 and Fiscal Year 2020, Administration funding for legal services programs for tenants in need grew from approximately $6 million to $127 million. | Since July of 2015, free legal services programs through the Human Resources Administration’s Office of Civil Justice have provided approximately 8,000 Inwood residents with free legal representation, advice and assistance for families and individuals facing eviction, harassment by unscrupulous landlords and other displacement pressures. Between Fiscal Year 2013 and Fiscal Year 2019, Administration funding for legal services programs for tenants in need grew from approximately $6 million to $93 million, a fifteen-fold increase. As a part of the Administration’s historic continuing investment in tenant legal services, including implementation of the City’s Universal Access to Counsel law which makes New York City the first city in the United States to ensure that all tenants facing eviction in Housing Court or in NYCHA administrative proceedings will have access to legal services, HRA’s tenant legal services programs will serve Inwood tenants in zip code 10034 and 10040 by providing access to legal services to all low-income households facing eviction in Housing Court in this zip code every year starting in Fiscal Year 2020. Based on current data, this initiative will serve an estimated 10,000 Inwood residents facing eviction every year. Universal Access will also be implemented in the Inwood zip code 10040, the Washington Heights zip codes 10032 and 10033, and the Marble Hill prioritized zip code 10463 no later than Fiscal Year 2022. In addition, the Public Engagement Unit will dedicate staff to conduct proactive outreach to tenants in these zip codes who may be eligible for legal assistance under Universal Access to Counsel law and in accordance with HRA OCJ’s expansion timeline. At full implementation, HRA’s tenant legal services are expected to provide access to legal assistance for 125,000 households in all five boroughs, or 400,000 New Yorkers, and will level the playing field for tenants facing eviction and displacement. | Ongoing
Inwood | Host tenant resource fairs to educate tenants about their rights and resources to prevent displacement | 16 | Housing | HPD | Done with ongoing work | HPD is committed to working with partner agencies, elected officials, and community groups to ensure tenants are aware of their rights and have access to important housing resources. HPD hosted a tenant resource fair on June 26, 2019, in partnership with the local council member. Also working with the local council member, HPD conducted conduct targeted outreach to tenants eligible for SCRIE and DRIE Rent Freeze programs and partnered with DOF to enroll residents in the programs. Additionally, staff from HPD's Neighborhood Outreach and Education Unit attended eight public events since June 2018 in Inwood and Washington Heights, including numerous Constituent Service Nights hosted by Councilmember Ydanis Rodriguez. | HPD is committed to working with partner agencies, elected officials, and community groups to ensure tenants are aware of their rights and have access to important housing resources. HPD will host two tenant resource fairs by the end of 2019 in coordination with the local Council Member. HPD will work with the local Councilmember to conduct targeted outreach to tenants eligible for SCRIE and DRIE Rent Freeze programs, and will partner with DOF to enroll residents in the programs. Timeline: Host two tenant resource fairs by the end of 2019 | 2019
Inwood | Continue to work with the Tenant Harassment Prevention Task Force to investigate and take action against landlords who harass tenants | 17 | Housing | HPD | Done with ongoing work | HPD participates on the Tenant Harassment Prevention Task Force, in partnership with the New York State Attorney General's office, New York State Department of Housing and Community Renewal, and other City agencies. To date, charges have been brought against two negligent landlords in the neighborhood. Additionally, HPD participates on the City Agency Task Force on Tenant Harassment with City and State agencies. Since launching in 2014 and as of March 2019, the City Agency Task Force has inspected 690 building with nearly 12,000 homes, issued nearly 30,000 hazardous or immediately hazardous violations, and had either HPD- or tenant-initiated Housing Court cases against 115 buildings. | The Administration helped to create an interagency, multi-jurisdictional Tenant Harassment Prevention Task Force comprised of HPD, DOB, Department of Health and Mental Hygiene (DOHMH), the NYC Law Department, Department of Housing and Community Renewal (DHCR), and the New York State Office of the Attorney General (OAG) to investigate and bring enforcement actions – including criminal charges – against landlords who are found to be harassing tenants to force them to vacate rent-regulated homes. HPD will continue to work with the Tenant Harassment Prevention Task Force to take action against landlords in the Inwood neighborhood area who are harassing tenants. | Ongoing
Inwood | Continue proactive outreach to Inwood tenants to provide access to anti-displacement resources including legal services | 17 | Housing | PEU | Done with ongoing work | Specialists from the City’s Tenant Support Unit (TSU) of the Public Engagement Unit (PEU) are on the ground in Inwood, conducting proactive outreach to tenants to inform them of their rights, identify housing-related issues faced by members of the community and connect tenants to free City services, like legal assistance, to mitigate displacement, landlord harassment and facilitate home-related repairs. To date, TSU specialists have knocked on over 34,125 doors in the area. TSU has also made over 14,915 follow up calls to provide comprehensive case management to tenants – bridging the gap between the City and tenants by helping them through the process of accessing resources. From July 2015 through June 2019, TSU specialists have assisted over 2,835 New Yorkers in zip code 10034. | Since July 2015, TSU specialists have knocked on over 31,800 doors and assisted over 2,500 tenants in the area. The Tenant Support Unit (TSU), part of the Mayor’s Public Engagement Unit (PEU), uses a data-driven approach to engage and provide assistance to New Yorkers who may be at risk of displacement or experiencing harassment. Outreach specialists conduct door-to-door outreach to inform tenants of their rights, identify any housing-related issues and connect them with a range of resources, such as emergency repairs and HRA’s free legal assistance. Working in coordination with HPD, HRA’s Office of Civil Justice and tenant organizing groups, as part of the Partners in Preservation Initiative, TSU will receive building referrals from HPD, and will conduct outreach to help tenants access a range of benefits and services that help keep them in their home, including legal assistance and rent freeze benefits. This can be accompanied by mailings and social media campaigns to educate tenants throughout the neighborhood about their rights and available resources. | Ongoing
Inwood | Conduct outreach to Inwood tenants for the NYC Rent Freeze Program | 18 | Housing | PEU | In Progress | PEU’s Rent Freeze Team has conducted proactive outreach to all likely eligible tenants for or already enrolled in NYC Rent Freeze programs, assisting all eligible tenants identified through this outreach in enrolling in the Rent Freeze programs. Between August 2018-April 2019, 2,331 New Yorkers in CD10 were successfully enrolled or renewed in Rent Freeze programs. | PEU’s Rent Freeze Team will conduct proactive outreach to all likely eligible tenants for or already enrolled in NYC Rent Freeze programs. The Rent Freeze team will aim to enroll or renew 4,100 New Yorkers in NYC Rent Freeze programs. Outreach shall include door knocking, live and robo-calls, mailings, and co-hosting various events in the area in partnership with Council Member Rodríguez. The team will assist all eligible tenants identified through this outreach in enrolling in the Rent Freeze programs. | 2018-2019
Inwood | Continue to improve housing quality through rigorous enforcement of the Housing Maintenance Code | 19 | Housing | HPD | Done with ongoing work | HPD responds to 311 calls, Housing Court requests, and building referrals by community groups and elected officials by sending inspectors to see if building conditions violate the City’s Housing Maintenance Code. If HPD finds such conditions, they issue violations, which require that the owner correct the condition. The most serious conditions must be corrected immediately, while less serious conditions must be corrected within 30 to 90 days. If owners do not correct violations, buildings may enter into one of HPD’s enforcement programs. HPD completed 23,691 inspections in Inwood and Washington Heights in FY 2018 and as a result issued 33,353 violations. | HPD responds to 311 calls, Housing Court requests, and building referrals by community groups and elected officials by sending inspectors to see if building conditions violate the City’s Housing Maintenance Code. If HPD finds such conditions, they issue violations, which require that the owner correct the condition. The most serious conditions must be corrected immediately, while less serious conditions must be corrected within 30 to 90 days. If owners do not correct violations, buildings may enter into one of HPD’s enforcement programs. As part of the City’s focus in the Inwood area, HPD has increased code inspections in Community District (CD) 12 by 11%, and violations issued by 25% since 2014. HPD also spent $2.2 million in emergency repairs between Fiscal Years 2014-2017. | Ongoing
Inwood | Proactively engage property owners in Inwood about the City’s resources to develop affordable housing | 21 | Housing | HPD | In Progress | HPD, in partnership with other City agencies and local elected officials, will host two events by the end of 2019 for property owners in the rezoning area to inform them of the City’s resources for developing new mixed-use affordable housing. | HPD, in partnership with other City agencies and local elected officials, will host two events by the end of 2019 for property owners in the rezoning area to inform them of the City’s resources for developing new mixed-use affordable housing. | Winter 2019
Inwood | Expand local hiring incentives in HPD‐financed developments | 22 | Housing | HPD | In Progress | In all HPD RFPs for the development of City-owned property, including the Inwood Library development project, respondents must demonstrate a plan for outreach to residents of the local community district related to employment opportunities generated by the proposed project. The outreach plan could also include activities such as skills, safety, and job training programs. The outreach plan must include a timeline for implementation. The outreach plan could also include activities such as skills, safety, and job training programs. Applicants will be required to comply with their outreach plans and report regularly on outreach activities. Regarding the development of private sites, applicants requesting City subsidies will be encouraged to demonstrate a plan for outreach to residents of the local community district related to employment opportunities generated by the proposed project. Private site developers submitting plans will be required to comply with these plans and report regularly on outreach activities. In addition, HPD will continue implementing HireNYC, which requires that any housing development receiving $2 million or more in HPD subsidy post open positions with the Workforce1 system and consider qualified candidates. Inwood area residents will be able to apply for jobs through the City’s HireNYC program at nearby Workforce1 Centers. HPD will also continue to explore how it can further more job opportunities on projects assisted by the agency. | Expand local hiring incentives in HPD‐financed developments In all HPD RFPs for the development of City-owned property, including the Inwood Library development project, respondents must demonstrate a plan for outreach to residents of the local community district related to employment opportunities generated by the proposed project. The outreach plan could also include activities such as skills, safety, and job training programs. The outreach plan must include a timeline for implementation. The outreach plan must include a timeline for implementation. The outreach plan could also include activities such as skills, safety, and job training programs. Applicants will be required to comply with their outreach plans and report regularly on outreach activities. Regarding the development of private sites, applicants requesting City subsidies will be encouraged to demonstrate a plan for outreach to residents of the local community district related to employment opportunities generated by the proposed project. Private site developers submitting plans will be required to comply with these plans and report regularly on outreach activities. In addition, HPD will continue implementing HireNYC, which requires that any housing development receiving $2 million or more in HPD subsidy post open positions with the Workforce1 system and consider qualified candidates. Inwood area residents will be able to apply for jobs through the City’s HireNYC program at nearby Workforce1 Centers. HPD will also continue to explore how it can further more job opportunities on projects assisted by the agency. See the “Workforce Development and Small Business” section for more information. | Ongoing
Inwood | Construct the Sherman Creek Malecón at Academy Street | 26 | Open Space | EDC | In Progress | EDC will transform Academy Street east of 10th Avenue, which has been fenced off and closed to the public for many years, into a new waterfront park. A designer was selected in May 2019, and design is expected to be complete in Winter 2020-2021. The programming and amenities of the new park will be informed by engagement with the Inwood community. | For many years, Academy Street east of 10th Avenue, along the northern side of Sherman Creek Inlet, has been fenced off and inaccessible to the public. Through the rezoning, the City is de-mapping the street and reclaiming it for public use. EDC will construct a new, two-acre waterfront park, the Sherman Creek Malecón, as a place for the Inwood community, including residents of the adjacent Dyckman Houses, to come together and play amid a beautiful natural setting. Recreational amenities could include space for community gatherings such as picnics and barbecues; lawns, seating, and shade structures; and opportunities for water-based activities like fishing or kayaking. EDC will also construct a bike and pedestrian connection along the east side of 10th Avenue to safely connect the Malecón with the five-acre Sherman Creek to the south, creating a continuous green gem along the entire shoreline of Sherman Creek Inlet. | FY2019 Design Start
Inwood | Restore the North Cove and create a North Cove park | 27 | Open Space | EDC | In Progress | EDC will restore the North Cove, site of an informal community space and wildlife habitat, and reclaim City-owned property currently used for parking to become part of a new park. A designer was selected in May 2019 and design is expected to be complete in Winter 2020-2021. The design of the new park will be informed by engagement with the Inwood community. |  | FY 2019 Design Start
Inwood | Rebuild Monsignor Kett Playground as an intergenerational park and destination | 28 | Open Space | DPR | In Progress | DPR started the design of the Monsignor Kett playground and comfort station in January 2019. | Monsignor Kett Playground is a key open space for the residents of NYCHA’s Dyckman Houses and Inwood. The site’s basketball courts are very heavily used for tournaments and free play. The facility has not seen a major capital upgrade in decades and lacks a year-round comfort station. The City will fund a comprehensive renovation of Monsignor Kett Playground, potentially including high-grade basketball courts with amenities for league play, an intergenerational fitness area, a new year-round comfort station, and connections from the park to the streetscape through Parks-Without-Borders perimeter treatments. NYC Parks will lead a public design process to re-envision the space and will include the Council Member, CB 12, Dyckman Houses, the leagues and sports groups that utilize the site, and other stakeholders. | FY 2019 Design Start
Inwood | Repair waterfront structures near Dyckman Pier, improve public access to Dyckman Pier, and build a new dock | 29 | Open Space | EDC | In Progress | EDC has developed a project scope to replace the Inwood Canoe Pier and associated bulkhead, replace the Dyckman Street Fishing Pier with a new high-level platform, and improve public access to the pier; relocate piles that support the existing dock; and install a new floating dock. EDC expects to begin design in summer 2019, begin construction in 2020, and complete construction in 2021. | The City will complete the reconstruction and/or restoration of multiple waterfront structures in the vicinity of the Dyckman Street pier, to address critical structural issues. The repairs are anticipated to include the Inwood Canoe Pier and nearby timber bulkhead, and the Dyckman Street Fishing Pier, as well as routine upkeep of the nearby structures, revetments and shorelines. The City will also make improvements to the west end of Dyckman Street, at the entrance to the Dyckman Street Pier, to make the pier more inviting to the public by reconfiguring physical access and adding recreational amenities, landscaping, and signage making it clear which areas of the site are open to the public, and will specify public hours. The City will also construct a new floating dock along the Hudson River in the vicinity of Dyckman Pier. The City will coordinate with the local Council Member on project scope and will provide updates as the project progresses and as operations are determined. The optimal location will be determined based on site conditions, including water depth. The dock will be designed to allow side-loading cultural and excursion vessels to use the facilities, and will support increased visitation, economic development, and enhanced leisure activities in the neighborhood. | FY 2020 Design Start
Inwood | Repair and reopen High Bridge Water Tower | 30 | Open Space | DPR | In Progress | DPR expects to begin construction in summer 2019 pending successful procurement. | Building on the successful 2015 reopening of the historic High Bridge, NYC Parks is now advancing the restoration of the High Bridge Water Tower. The project, currently out to bid in the procurement process, will stabilize the historic structure and establish public access. Pending successful procurement Parks expects the project to begin construction in late 2018. For project updates, please visit: https://www.nycgovparks.org/planning-and-building/capital-project-tracker/project/5937. | FY 2018 Design Start
Inwood | Renovate Dyckman Rest and transform space into a welcoming entrance | 31 | Open Space | DPR | Not Started | DPR is expected to start design in Fiscal Y. | Highbridge is a heavily used park, but the northwestern corner of the park at Nagle Avenue and Dyckman Street is underutilized and uninviting. The City will fund NYC Parks to transform approximately 1.5 acres of unprogrammed and underutilized space into a gateway for Highbridge Park and the neighborhood. Improvements are expected to potentially include new playground equipment, an area for possible park concessionaires, landscape improvements, and new pathways to better connect to the rest of Highbridge Park across Fort George Hill. | FY 2019 Design Start
Inwood | Repair waterfront infrastructure along the Harlem River (from south of Dyckman Street to West 155th Street) | 32 | Open Space | EDC | In Progress | The Harlem River waterfront between Dyckman Street and West 155th Street is part of a larger Manhattan Waterfront Greenway capital project stretching to East 125th St. EDC will repair and reconstruct bulkheads and seawalls to ensure the longevity of the waterfront. EDC has selected a designer for the project and expects to begin construction in 2021. | The City will complete the reconstruction and/or restoration of multiple waterfront structures from south of Dyckman Street to West 155th Street. The repairs are anticipated to address the structural integrity of waterfront edge structures to ensure the public’s safe continued use and enjoyment of open space amenities on the water and to protect critical roadways like the Harlem River Drive. | FY 2020 Design Start
Inwood | Improve and enhance Highbridge Park through the Anchor Park Initiative | 33 | Open Space | DPR | In Progress | DPR started Phase I construction in December 2018, which is expected to take approximately 18 months. | At over 130 acres, Highbridge Park is one of the area’s most important open spaces. The park offers natural beauty intertwined with passive and active recreational amenities. In 2016, Highbridge was tapped for a $30 million investment under Mayor de Blasio’s Anchor Parks Initiative – a once-in-a-lifetime opportunity to make an old park new again. Working closely with the community, NYC Parks has since developed a conceptual master plan and is advancing a series of capital improvements for Highbridge Park based on the community’s priorities. Phase I, currently in procurement process, improves safety and connectivity within the northern reaches of the Park by upgrading the pathways between the soon to be reconstructed Grand Staircase at Laurel Hill Terrace and a brand new entry plaza at Dyckman Street and Harlem River Drive. | FY 2017 Design Start
Inwood | Renovate Anne Loftus Playground | 34 | Open Space | DPR | In Progress | DPR is expected to complete design of Anne Loftus playground and begin procurement in summer 2019. | NYC Parks is in the process of renovating this playground. Design was initiated in June 2018 with feedback from the June 25, 2018 public input meeting currently being analyzed and incorporated into the design. A second public input meeting is being scheduled for later this summer. While the project has yet to be designed, based on initial feedback received at the June 25th meeting, pending approvals, NYC Parks expects the design could potentially include installation of contemporary play equipment with a focus on water activities, basketball or other active recreation elements, and upgraded drainage infrastructure to eliminate flooding. | FY 2019 Design Start
Inwood | Renovate Inwood Hill Park Soccer Field #1 (Dyckman Fields), including installation of new water service | 35 | Open Space | DPR | Not Started | DPR is expected to start design of Inwood Hill Park Soccer Field #1 (Dyckman Fields) in spring 2020. | Dyckman Fields Soccer Field #1 is a heavily used recreational amenity. The lack of water service to Dyckman Fields has led to soil compaction at this soccer field resulting in significant bare spots in the lawn and frequent dust bowl conditions, reducing public access due to flooding during wet conditions, and resulting in further erosion. The City will fund NYC Parks to reconstruct Soccer Field #1 to create a high-caliber, safe athletic facility for league and recreation use. A key component of the project will also include installation of water service, which will increase usability. | FY 2020 Design Start
Inwood | Upgrade court amenities at Highbridge Park | 36 | Open Space | DPR | Done | DPR completed upgrades to court amenities at Highbridge Park in October 2018. | Highbridge Park has a number of heavily used basketball and volleyball courts in need of upgrade. At the 175th Street Recreation Area, Parks has improved the volleyball and basketball courts by applying new sports coating. Parks will also apply similar sports coating work at the 3.5 basketball courts at Wallenberg Playground (190th Streets), if feasible, to help to extend the usable life of the courts. Timeline: Investigation and work | FY 2019 Design Start
Inwood | Install adult fitness equipment in Inwood Hill Park - Dyckman Green Gym | 37 | Open Space | DPR | Done | DPR completed construction in October 2018, six months ahead of schedule. | To promote physical activity among adults, NYC Parks is installing outdoor fitness equipment in Inwood Hill Park. The new equipment is located within Inwood Hill Park, north of Dyckman Street along Hudson River. | 2018
Inwood | Deploy mobile field lighting pilot at Inwood Hill Park ballfield | 38 | Open Space | DPR | Done | DPR completed the pilot project of deploying mobile field lighting at Inwood Hill Park in September 2018. | To provide more field access and support youth tournaments, in summer 2018, NYC Parks will pilot weekend mobile lights use at Inwood Hill Park's Ballfield #1 near Seaman Avenue. NYC Parks will notify local leagues and current athletic permit holders of this amenity which allows for maximum field usage during weekend evening hours. | Summer 2018
Inwood | Build a new state-of-the-art library in Inwood | 39 | Community Resources | NYPL | In Progress | NYPL has secured a nearby storefront as a temporary site to be used during the construction of the new Inwood Library that will provide the community with core services, such as circulation of materials, computer use, readers advisory, and reference services. These services will be supplemented with regular visits from the Library's new bookmobile and partnerships with local organizations to regularly host popular library programs such as storytime, technology workshops, and more. Once construction is completed, the Inwood Library will house a large collection of books, periodicals, and digital resources. The Inwood Library also hopes to provide a collection of circulating materials and a range of public programs related to the immigrant experience reflected in the community. | At approximately 20,000 square feet, the new Inwood Library will be open, light-filled, and welcoming. It will house a large collection of books and periodicals, as well as updated infrastructure for computer-based learning, digital access to a wide range of resources, programming such as adult literacy, and flexible spaces that can be used for meetings and presentations. The programming at the branch would be a part of the general and educational programs offered by the Library which would be clearly connected to IRCPA. NYPL could also provide a discreet collection of circulating materials on the immigrant experience to create a visible connection as well as continue to offer a range of public programs related to the immigrant experience. The community will have access to a temporary library space during construction, and NYPL has committed to providing all core services at the temporary site including circulation of materials, computer appointments, readers’ advisory, and reference. NYPL will work with the community to determine temporary locations within other community spaces for popular library programs like ESOL, Teen Tech, and Story Time. | Based on the Inwood Library development project timeline
Inwood | Increase local access to healthy foods | 39 | Community Resources | DOHMH | In Progress | The Health Bucks application for community organizations opened in May, 2019. DOHMH invited Inwood Community Based Organizations to apply to distribute Health Bucks. The Fort Washington and 175th Street Greenmarkets are scheduled to open in late June and began distributing Health Bucks then. | Health Bucks are $2 coupons distributed by DOHMH that can be used to purchase fresh fruits and vegetables at all NYC farmers markets. The City will conduct targeted outreach to qualified Community-Based Organizations (CBOs), in coordination with the local Council Member’s offices, with the goal of increasing the number of organizations that apply to distribute Health Bucks and connect to local greenmarkets such as the 175th Street Greenmarket and the Fort Washington Greenmarket. | 2018
Inwood | Make large scale comprehensive capital investments to George Washington Educational Campus (GWEC) | 40 | Community Resources | SCA | In Progress | As part of capital investments to George Washington Campus (GWEC), SCA committed to a comprehensive window replacement project. SCA is currently in the design phase for window replacement which will include windows, window frames, window guards, and window shades. | The SCA will design a window replacement project at the George Washington Campus, which will address all windows currently rated a 5 on the Building Condition Assessment Survey (BCAS). Replacement is anticipated to include windows, window frames, window guards, and window shades. The project will bring the windows of the building into a state of good repair. | FY 2019 Design Start
Inwood | Open a new Pre-K for All Facility as part of the Inwood Library development project | 41 | Community Resources | HPD | In Progress | The Department of Education will operate a new Pre-K for All facility that will be part of the Inwood Library development project, known as the Eliza. The facility will include three classrooms and a total of approximately 6,500 square feet. Following the selection of an operator, DOE will begin discussions about integrating STEM education into the curriculum for the new facility and explore partnerships with topic experts, such as the NYC FIRST STEM Center also located in the Inwood Library development, to tie this school into the broader District 6 STEM network. The Eliza development team is expecting to break ground in early 2020. | The Department of Education will operate a new Pre-K for All facility that will be part of the Inwood Library development project. The facility will include three classrooms and a total of approximately 6,500 SF. Following the selection of an operator, DOE will begin discussions about integrating STEM education into the curriculum for the new facility and explore partnerships with topic experts, such as the NYC FIRST STEM Center also located in the Inwood Library development, to tie this school into the broader District 6 STEM network. | Based on the Inwood Library development project timeline
Inwood | Create a state-of-the-art flagship STEM Center at Gregorio Luperon High School for Science and Mathematics | 42 | Community Resources | SCA | In Progress | SCA and DOE are in the design phase of creating a state-of-the-art STEM center with a focus on aviation and robotics at Gregorio Luperon High School for Science and Mathematics. The new project will include an FAA approved aviation training simulator to make Gregorio Luperon a Science, Technology, Engineering, and Mathematics hub for Northern Manhattan. The project is currently on schedule as planned. | SCA and DOE will invest in structural and program investments to create a state-of-the-art, 21st-century flagship STEM center with a focus on aviation and robotics at Gregorio Luperon High School for Science and Mathematics. The new project will include an FAA approved aviation training simulator to make Gregorio Luperon a Science, Technology, Engineering, and Mathematics hub for Northern Manhattan. | 2019 Design Start
Inwood | Create a new cultural and research center to celebrate the immigrant experience | 43 | Community Resources | EDC | In Progress | In recognition of the rich cultural and artistic ecosystem in Inwood and the neighborhood’s important role in the immigrant experience in New York City and the United States, the City is committed to support the development of the Immigrant Research and Performing Arts Center (IRPAC). The facility will be up to 15,000 SF and is expected to include a performing arts space designed to allow for flexibility of programming and staging of performances in a variety of settings, as well as space for members of the public and academics to research and discuss the immigrant experience. The space may also include storage, dressing rooms, classroom, rehearsal space, administrative offices, and/or other flexible cultural space depending on the programmatic needs and operations of the operator of the space. EDC and DCLA will release a Request for Expressions of Interest in Summer 2019 to request proposals from arts and cultural organizations interested in operating the future facility. Once an operator has been selected, EDC and DCLA will work to identify a suitable location for IRPAC and will work closely with the operator to create a project scope for the new facility that meets their programmatic and operational needs. | In consultation with the winner of the RFP, the City will additionally provide funding for the acquisition, design, and construction of an approximately 15,000-square foot Immigrant Research Center & Performing Arts (IRCPA) at a location to be identified (potentially in conjunction with an affordable housing development project. The site shall include a performing arts space designed to allow for flexibility of programming and staging of performances in a variety of settings including: with the audience on one side (proscenium style), two sides (center stage), three sides (thrust), four sides (theater in the round), or environmental staging, in which the audience and actors intermingle. The space will also include storage, dressing rooms, lobby, classroom, and rehearsal space. IRCPA will also include space for members of the public and Inwood Points of Agreement 33 academics to research and discuss historical and contemporary materials related to the immigrant experience. The City will also collaborate with relevant academic institutions, including the NYPL, CUNY, and others to assist in programming the space. The City shall provide dedicated funding to the NYPL to provide staff to assist the cultural operator of IRPAC in facilitating an academic and research component of the center. Such assistance may include assisting scholars with inquiries on subjects related to immigrant issues by connecting them to various available digital collections, curating and providing a discreet collection of circulating materials on the immigrant experience, and working with the operator to offer a range of public programs at both the library and IPRAC related to the immigrant experience. Upon construction, the IRCPA facility will be owned by DCLA and cost to the selected cultural organization will be limited to common area rent, providing a large effective subsidy to operations | 2019 - ongoing
Inwood | Upgrade space and equipment and outfit new space to accommodate increased STEM education and after-school programming at GWEC | 44 | Community Resources | SCA | In Progress | SCA has met with several stakeholders to discuss upgrading outdated science labs and spaces at GWEC for increased programming on STEM. SCA is working with GWEC regarding the location of the proposed project. | In addition, the City will fund SCA to upgrade existing outdated science labs, create new lab workstations and upgrade space at GWEC to make room for increased programming on STEM. The project may be subject to approval by the Panel for Educational Policy if significant change to building utilization is necessary. | 2019 Design Start
Inwood | Repair two pools at GWEC | 45 | Community Resources | SCA | In Progress | SCA is working with DOE and the local Council Member to develop the design for refurbishing the two pools at GWEC. | The City will refurbish the two pools in GWEC to allow expanded programming for the schools at GWEC and allow them to be open to the public through a private, non-profit operator. The improvements include new HVAC system, electrical upgrades, floor waterproofing and new tiling for the existing "Girls Pool", as well as structural work, new filtration system, new HVAC system, electrical upgrades, and lighting for the Boys' pool, which is currently not used. The improvements would also include new roofing for both pools, new bleachers, and complete upgrades to the girls' and boys' locker rooms to make them usable. The pools would be available for public programming during non-school hours through DOE's permit process. DOE and SCA will work with the local Council Member's office throughout the design and construction and permit processes. | FY 2020 Design Start
Inwood | Explore the expansion of the STEM Hub on the current TCU site at GWEC | 46 | Community Resources | DOE | In Progress | $2 million is allocated to provide STEM curriculum, in collaboration with selected teachers from the 4 GWEC schools, and the faculty for the afterschool, Saturday, and Summer programs. | If the Transportable Classroom Units (TCU) at GWEC are vacated, which may involve proposals requiring Panel for Educational Policy approval, DOE will explore the expansion of STEM education, which will include assessing space and capacity at GWEC and overall demand for increased STEM programming. | Upon TCU being vacated
Inwood | Create an Inwood Innovation Hub focused on STEM Talent Solutions | 47 | Community Resources | HPD | In Progress | The 4095 Ninth Avenue RFP will include a request for the development of a new Inwood Innovation Hub that will be a center for Science, Technology, Engineering, and Math (STEM) training; education; and entrepreneurship services and programs. It will offer small business and talent development support and resources to create access to economic and advancement opportunities for local and neighboring communities. The City will work with the local Council office throughout the RFP process, and will specify that the facility operator/project developer provide the following: - Staffed Community Space available for education, training, events, innovation-facilitating networks, research and development, entrepreneurship, and programming focused on STEM and other high growth industries and emerging fields. - Entrepreneurship Services offering resources, support staff, equipment, and tools for local individual users, groups and small businesses. - Programming delivered by training providers, industry partners, and local institutions. - Cross Sector Partnerships and Industry Collaborations with academia, workforce, and small business providers, employers, and corporations. 4095 Ninth Avenue RFP is anticipated to be issued in 2020. | The 4095 Ninth Avenue RFP will include a request for the development of a new Inwood Innovation Hub that will be a center for Science, Technology, Engineering, & Math (STEM) training, education, and entrepreneurship services and programs. It will offer small business and talent development support and resources to create access to economic and advancement opportunities for local and neighboring communities. The City will work with the local Council office throughout the RFP process, and will specify that the facility operator/project developer provide the following:  Staffed Community Space available for education, training, events, innovation-facilitating networks, research & development, entrepreneurship and programming focused on STEM and other high growth industries and emerging fields.  Entrepreneurship Services offering resources, support staff, equipment and tools for local individual users, groups and small businesses.  Programming delivered by training providers, industry partners and local institutions.  Cross Sector Partnerships and Industry Collaborations with academia, workforce and small business providers, employers and corporations. Suggested local partners could include but are not limited to: CUNY, NY-Presbyterian, Columbia University Medical Center, and Yeshiva University. | FY 2020-2021 tentative RFP release date
Inwood | Implement second NYCx Co-Lab in Inwood | 48 | Community Resources | MOCTO | In Progress | MOCTO will launch the second NYCx Co-Lab Challenge in Inwood in the fall of 2019. The NYCx Co-Lab Challenge will engage the tech industry to partner with City agencies and neighborhood leaders to solve urban problems in real-world settings. The winning proposals will be awarded with City funding, access to municipal infrastructure, and spaces in the neighborhood to test and build solutions developed to respond to community needs. | The City will implement the second NYCx Co-Lab programming in Inwood. Led by the Mayor’s Office of the Chief Technology Officer (MOCTO), NYCx Co-Labs combines technology piloting and education in high-need, high-opportunity neighborhoods by connecting local residents, government, academia, and tech entrepreneurs to identify, co-develop, and test innovative solutions that address the neighborhood’s most pressing needs. MOCTO will collaborate with Inwood-based community organizations to assemble a local advisory board and a cohort of youth leaders to guide program activities in the neighborhood, including a series of in-depth workshops to help the community define local priorities and understand the potential for new technologies to address the self-identified neighborhood needs. The workshops will also convene an intergenerational group of civic entrepreneurs to help advance the opportunities for their neighborhood to benefit from the introduction of new technologies. MOCTO will aim to launch the first NYCx Co-Lab Challenge in Inwood in early 2019. The NYCx Co-Lab Challenge will engage the tech industry to partner with City agencies and neighborhood leaders to solve urban problems in real-world settings. The winning proposals will be awarded with City funding and access to municipal infrastructure and neighborhood spaces to test and build solutions developed to respond to community needs. | 2018-2019
Inwood | Open a NYC FIRST STEM Center as part of the Inwood Library development project | 49 | Community Resources | HPD | In Progress | The Inwood Library development project will include an NYC FIRST STEM Center, focused on robotics and mechatronics, in the new facility. NYC FIRST STEM Centers offer hands-on, sustained STEM (“science, technology, engineering, and mathematics”) education and robotics competitions, including a range of courses and programs that integrate the disciplines of computer science, digital and non-digital fabrication, mechanical engineering, electronics, and sensors. The STEM Center will complement programming offered by the Activities, Culture, and Training (ACTS) Center. It will include programming in partnership with Inwood, Washington Heights, and Marble Hill schools and will also partner with the Pre-K for All facility in the Inwood Library development project. | the Inwood Library development project will include an NYC FIRST STEM Center, focused on robotics and mechatronics, in the new facility. NYC FIRST STEM Centers offer hands-on, sustained STEM (“science, technology, engineering and mathematics”) education and robotics competitions, including a range of courses and programs that integrate the disciplines of computer science, digital and non-digital fabrication, mechanical engineering, electronics, and sensors. The STEM Center will complement programming offered by the Activities, Culture, and Training (ACTS) Center. It will include programming in partnership with Inwood, Washington Inwood Points of Agreement 26 Heights, and Marble Hill schools and will also partner with the Pre-K for All facility in the Inwood Library development project. | Based on the Inwood Library development project timeline
Inwood | Deploy Algebra for All in Inwood by making District 6 a Focus District | 50 | Community Resources | DOE | Done with ongoing work | There are 46 DOE schools geographically located in District 6; 39 of these schools are under Community Superintendent Ramirez and all are participating in A4A in SY2019-20. Participation means the teachers and administrators have access to professional learning beginning with summer 2019 and for two schools years. In the first year of A4A (School Year 2019-20), schools who fully commit to A4A will receive in-school coaching for their math teachers and have access to a school-based allocation to invest in regents prep, bridge programs, and/or creating/participating in professional learning communities. | The Department of Education will roll out Algebra for All district-wide and will ensure that the middle schools in the program have the necessary resources and teacher training needed to deliver on this expansion. Algebra for All will reach all 20 middle schools in D6 by the 2019-20 school year. | 2019 - 2020 School Year
Inwood | Expand opportunities for M/WBEs in the affordable housing development industry | 50 | Housing | HPD | Done with ongoing work | HPD has services and programs to support M/WBEs and create a pathway for smaller businesses to build capacity. The M/WBE Build Up Program requires development projects receiving $2 million or more in City contribution to utilize M/WBE construction or professional firms. In addition, under HNY, 15 out of 74 public site designations went to M/WBEs, six of which were selected through our M/WBE RFP. In 2019, HPD began year four of its Developer Capacity Building Program, which provides courses and networking opportunities to M/WBE developers. | HPD will continue promoting the participation of M/WBEs and non-profit organizations in the development and management of City-subsidized affordable housing, and aggressively targeting outreach to local small businesses. Through the Building Opportunity Initiative, HPD seeks to:  Expand the use of M/WBE construction contractors and professional service providers on HPD-financed development projects through the M/WBE Build Up Program. The program requires that developers of projects where HPD contributes $2 million or more in subsidy must spend at least 25 percent of all HPD-supported costs on certified M/WBE construction, design, or professional service firms. HPD will encourage the utilization of a diverse pool of contractors and subcontractors, including those from Northern Manhattan, for all projects in the Inwood rezoning area.  Build the capacity of M/WBE and nonprofit developers through professional development, networking, and mentoring programs. The Building Capacity Workshop Series introduces M/WBE and non-profit developers to best practices in affordable housing development, from site selection and project financing to construction and property management.  Improve access to capital for M/WBE developers with low-cost financing options for site acquisition and predevelopment costs through the New York City Acquisition Fund, which offers flexible bridge loans for the purchase of vacant sites or occupied buildings, predevelopment, and moderate rehabilitation. | Ongoing
Inwood | Expand Computer Science for All in Inwood through aggressive outreach to District 6 Schools | 51 | Community Resources | DOE | In Progress | The DOE recruited schools in District 6 to join the SY 19-20 CS4All cohort. Teachers at the following schools are scheduled to participate in CS4All training in the summer and throughout the school year. 06M223 The Mott Hall School 06M293 City College Academy of the Arts 06M319 M.S. 319 - Maria Teresa 06M328 Community Math & Science Prep 06M366 Washington Heights Academy 06M462 The College Academy 06M463 High School for Media and Communications 06M467 High School for Law and Public Service 06M468 High School for Health Careers and Sciences 06M552 Gregorio Luperon High School for Science and Mathematics 06m005 PS 5 Ellen Lurie 06M098 PS 98 Shorac Kappock | The Department of Education will undertake an aggressive outreach strategy to drive school-level participation in Computer Science for All. This includes expansion of Computer Science for All programs to additional elementary, middle and high schools in the area, and increased participation of superintendents, principals, and school leadership in teacher professional development opportunities like Computer Science Education Week. The Department of Education estimates that 30 additional District 6 schools will join Computer Science for All over the next three years, to bring computer science education to students in the Inwood community. | ongoing
Inwood | Upgrade District 6 schools broadband and technology access to support increased focus on STEM education | 52 | Community Resources | DOE | In Progress | [Update pending] | To date, all but one school in District 6 have been upgraded to fiber optics, and a number of schools have seen their internet bandwidth increased to meet growing demand. DOE will conduct a review and verify the status of the school tech refresh process for every school in District 6 to ensure each school is refreshed by December 2021. In addition, DOE will undertake the process of ensuring increased access to bandwidth for GWEC upon launch of the STEM Hub. | Ongoing
Inwood | Provide adult education, training, and certificate programs at the Activities, Culture, and Training (ACTS) Center in the Inwood Library development project | 53 | Community Resources | HPD | In Progress | The ACTS Center at the Inwood Library development project, known as the Eliza, will provide adult education programming such as high school equivalency, computer training, English as a second language, and CUNY classes, in partnership with CUNY in the Heights. It will also provide certificate programs for Safe Serve and Home Health Aide. The Eliza development team is expecting to break ground in early 2020. | The ACTS Center at the Inwood Library development project will provide adult education programming such as high school equivalency, computer training, English as a second language, and CUNY classes, in partnership with CUNY in the Heights. It will also provide certificate programs for Safe Serve and Home Health Aide. | Based on the Inwood Library development project timeline
Inwood | Expand Community Services Offered at the DOHMH Washington Heights Center | 54 | Community Resources | DOHMH | In Progress | Located at 600 West 168 Street, the DOHMH Washington Heights Center is an important piece of the City’s Upper Manhattan health service network. On the floors operated by the DOHMH, we have public services that range from free and confidential testing and treatment for tuberculosis, and insurance enrollment, and co-located community based service providers. DOHMH is developing an outreach strategy to inform and attract more eligible residents of Manhattan Community Board 12 to take advantage of the services on site. Further, DOHMH is making best faith efforts to collaborate with Columbia Mailman School of Public Health, which also occupies space within the building, to strategize how their own programming can best serve the Washington Heights and Inwood communities. | Located at 600 West 168 Street, the DOHMH Washington Heights Center is an important piece of the City’s Upper Manhattan health service network. On the floors operated by the DOHMH, we have public services that range from free and confidential testing and treatment for tuberculosis, and insurance enrollment, and co-located community based service providers. The City also recognizes there is a strong interest to do more to connect these services to the community and are excited for the prospect of working on that with the Council Member to do that work  The City will work with the Council Member’s office to develop an outreach strategy to inform and attract more eligible residents of Manhattan Community Board 12 to take advantage of the health services on site. Outreach to include health fairs, targeted neighborhood advertisement (including Get Covered NYC and other medical campaigns as funding allows), and promoting available services through Columbia University’s Get Health Heights coalition. Timeline: To begin Q1 CY 2019  The City will make best faith efforts to collaborate with Columbia University Mailman School of Public Health, which also occupies space within the building, to strategize how their own programming can best serve the Washington Heights and Inwood communities. Timeline: To begin Q4 CY 2018  The City will upgrade the broadband internet availability for the Washington Heights Center, and ensure that visitors have access to public wi-fi. Capital Cost: $55,300 Timeline: November 2018  HRA will work with their designated Upper Manhattan HomeBase provider and DOHMH to have representatives on site at 600 West 168th Street. Homebase will hold regular satellite office hours so that visitors to 600 West 168th Street members can receive housing advice, enroll in Homebase, and receive housing-related referrals. Having HomeBase representatives on site will provide a direct connection to onsite providers to a set of new supportive services and strengthen the network between their work and HRA The Public Engagement Unit (PEU) will also hold regular satellite office hours at 600 West 168th Street. Tenant Support specialists will be available to connect tenants in the area to resources and services to mitigate displacement, including referrals to legal assistance through HRA, and provide ongoing case management of all housing-related issues. In addition, specialists will screen any interested constituents for over 30 government benefits through AccessNYC, including Rent Freeze programs (e.g. SCRIE, DRIE) and cash assistance, and advise them through the application processes. | 2018 - 2019
Inwood | Expand Community Services Offered at the DOHMH Washington Heights Center | 54 | Community Resources | DOHMH | In Progress | The DOHMH Washington Heights Center is an important piece of the City’s Upper Manhattan health service network. On the floors operated by the DOHMH, we have public services that range from free and confidential testing and treatment for tuberculosis, and insurance enrollment, and co-located community based service providers. DOHMH is developing an outreach strategy to inform and attract more eligible residents of Manhattan Community Board 12 to take advantage of the services on site. Further, DOHMH is collaborating with Columbia Mailman School of Public Health, which also occupies space within the building, to explore how their own programming can best serve the Washington Heights and Inwood communities. | Located at 600 West 168 Street, the DOHMH Washington Heights Center is an important piece of the City’s Upper Manhattan health service network. On the floors operated by the DOHMH, we have public services that range from free and confidential testing and treatment for tuberculosis, and insurance enrollment, and co-located community based service providers. The City also recognizes there is a strong interest to do more to connect these services to the community and are excited for the prospect of working on that with the Council Member to do that work  The City will work with the Council Member’s office to develop an outreach strategy to inform and attract more eligible residents of Manhattan Community Board 12 to take advantage of the health services on site. Outreach to include health fairs, targeted neighborhood advertisement (including Get Covered NYC and other medical campaigns as funding allows), and promoting available services through Columbia University’s Get Health Heights coalition. Timeline: To begin Q1 CY 2019  The City will make best faith efforts to collaborate with Columbia University Mailman School of Public Health, which also occupies space within the building, to strategize how their own programming can best serve the Washington Heights and Inwood communities. Timeline: To begin Q4 CY 2018  The City will upgrade the broadband internet availability for the Washington Heights Center, and ensure that visitors have access to public wi-fi. Capital Cost: $55,300 Timeline: November 2018  HRA will work with their designated Upper Manhattan HomeBase provider and DOHMH to have representatives on site at 600 West 168th Street. Homebase will hold regular satellite office hours so that visitors to 600 West 168th Street members can receive housing advice, enroll in Homebase, and receive housing-related referrals. Having HomeBase representatives on site will provide a direct connection to onsite providers to a set of new supportive services and strengthen the network between their work and HRA The Public Engagement Unit (PEU) will also hold regular satellite office hours at 600 West 168th Street. Tenant Support specialists will be available to connect tenants in the area to resources and services to mitigate displacement, including referrals to legal assistance through HRA, and provide ongoing case management of all housing-related issues. In addition, specialists will screen any interested constituents for over 30 government benefits through AccessNYC, including Rent Freeze programs (e.g. SCRIE, DRIE) and cash assistance, and advise them through the application processes. | 2018 - 2019
Inwood | Create a new Career & Technical Education Program at High School for Health Careers and Sciences | 55 | Community Resources | DOE | Done | The High School for Health Careers and Sciences has successfully launched its Health Careers program. The program offers four high school credits of health core curriculum allowing students to branch into many fields within the health careers sector. Career-related activities are being developed with Isabella Geriatric Center with the hopes of using the site for clinical rotation of students as well as paid internships. | The Department of Education will create a new CTE program that will include partnerships with healthcare institutions like the Isabella Geriatric Center. Students will learn theoretical and practical components of the Certified Nurse Assistant program through a required core curriculum and through work-based learning opportunities in clinical settings. Upon completion, students will be eligible for the Certified Nurse Aid New York State licensing exam | 2018-2019 school year
Inwood | Seek Potential Partners to Develop a P-TECH Program at GWHS | 56 | Community Resources | DOE | Done with ongoing work | At this time, a new Grades 9-14 school or program is not being pursued in District 6. The DOE conducted a review of feasible sites for the Grades 9-14 (P-TECH) expansion in underserved communities. During the assessment of District 6 (which has 10 high schools and 1 transfer school), it was determined that: ● District 6 already has two early college high schools and would not be an equitable choice for another early college school a) Inwood Early College for Health and Information Tech (06M211) (P-TECH) b) City College Academy of the Arts (06M293) ● 8 of the 10 high schools in District 6 offer College Now coursework in which students can earn college credits ● Potential college partners are at capacity with their current early college school partnerships. | Pathways in Technology Early College High School (P-TECH) is a post-secondary education model that connects high school, college, and the world of work through college and industry partnerships. DOE will study the feasibility of the development of a mechatronics-related P-TECH program in Inwood. Subject to community interest, labor market demand analysis, and the identification of a feasible partnership including higher education and high school partner capacity and interest, the city will work towards the development of a P-TECH program at a school in District 6, including potentially at GWHS campus. | 2018-2019
Inwood | Expand Teacher Professional Development and Training in STEM fields, including through participation to the biannual DOE STEM Institute | 57 | Community Resources | DOE | In Progress | The STEM team has refocused the STEM professional learning away from large biannual 3-day institutes to smaller and more local professional learning, in collaboration with Borough/Citywide Office staff. Professional learning offerings will be determined based on the needs and instructional priorities of each district. The STEM team is providing continued professional learning for the K-5 Science Core Curriculum (Amplify Science), and is developing engineering and technology extensions to select lessons for School Year 2019-20. The STEM Team is also providing teacher professional learning for the 6-8 Science Core Curriuclum (Amplify Science) beginning in July 2019. These offerings are available to schools that have opted into science core curriculum. Through a partnership with the District 6 Community Superintendent, the STEM Team is piloting the integration of a robotics curriculum with 10-12 district 6 schools during SY2019-20. | The Department of Education will ensure that District 6 teachers are well-trained to teach the content and skills students need to succeed in the academic and professional fields of the future. DOE will undertake an aggressive outreach strategy to drive participation from school leadership in teacher training programs like the biannual DOE STEM Institute. The Department of Education aims to ensure that each school has five teachers trained in high quality STEM professional development, and that schools with over 1,000 students have at least eight teachers trained. For purposes of this effort, the DOE considers the biannual DOE STEM Institute to be the premier teacher training program for this work. This Institute connects school teachers and leadership with some of the most innovative programming partners in the country and provides a forum for them to network with other STEM educators and share best practices and toolkits. CS For All training, AP For All professional development (for math, science, and technology AP classes), and Math for America trainings are additional sources of relevant, high quality professional development that qualify for purposes of this initiative. The DOE reserves the right to add internally-provided, university-provided, or third party-provided professional development to this list upon an in depth review of the program’s offerings and alignment, with the goal of ensuring that District 6 teachers and administrators are highly trained in rigorous content and highly effective pedagogy in STEM. All of these efforts are in support of the intention to provide students in District 6 with a truly excellent and equitable education. | ongoing
Inwood | Develop and launch the GWEC STEM Institute, a year-long STEM enrichment program to prepare students to be ready for college matriculation in STEM fields | 58 | Community Resources | DOE | In Progress | $2 Million was allocated to CUNY for expansion. According to Superintendent Ramirez, “CCNY will provide STEM curriculum, in collaboration with selected teachers from the 4 GWEC schools, and the faculty for the afterschool, Saturday, and Summer." | The goal of the GWEC STEM Institute is to prepare, expose and encourage GWEC students to enter and succeed in STEM baccalaureate or associate programs, including the mechatronics and technology programs. The GWEC STEM Institute, through a combination of investments in DOE and higher education/ STEM partners programs, will offer students the unique opportunity to access some of the best and latest learning in STEM fields and maximize their academic potential with the explicit goal of going to college in promising 21st Century career fields. During school hours, DOE will make investments to increase Math and Science learning, with trained teachers with high quality providers. Additionally, and to build upon and maximize the upgrades to the GWEC facilities that will provide students with best-in-class project-based learning opportunities, the DOE will develop and launch a set of programs to provide students a head start on college readiness in the science, technology and engineering fields. These initiatives will include, but may not be limited to, after-school, weekend, and summer STEM programming that complement daytime STEM instruction and introduce students to fields such as mechatronics and robotics; access to college-credit classes through partnership with CUNY and CCNY; and GWEC leadership collaboration with Council District 10 schools, higher education partners, community-based organizations, and industry partners to ensure that GWEC is always at the forefront of innovation on STEM learning. These programs may be made available to not just students at GWEC but also members of the broader community. This initiative may seek to partner with a higher education institution to ensure alignment with college-level academic expectations. | 2019 Design Start
Inwood | Expand program with CUNY Tutor Corps to fund CUNY students providing supplemental tutoring during school to support existing algebra and CS instruction | 59 | Community Resources | DOE | In Progress | CUNY Tutor Corps is managed by CUNY. The Office of Postsecondary Readiness in the DOE offers recommendations to CUNY when requested in connecting schools with tutors. In 2018-19, 3 schools in District 6 had CUNY Tutor Corps support in their CS classrooms. The schools were Inwood Early College, City College Academy of the Arts, and Washington Heights Expeditionary Learning School. DOe is working with CUNY to see how many available tutors could be placed to support CS4All or Algebra for All for the 2019 - 2020 school year. | DOE will continue to partner with CUNY Tutor Corps to reinforce Computer Science for All and Algebra for All curriculum taught in elementary, middle and high schools throughout District 6. Tutor Corps is funded to expand in FY19 from 180 to 360 tutors citywide. DOE will help support connecting tutors with host teachers at participating schools in District 6. | Ongoing
Inwood | Continue upholding responsible contracting and labor standards for affordable housing projects receiving City subsidy | 59 | Housing | HPD | Done with ongoing work | HPD conducts integrity checks to ensure the integrity of individuals and entities seeking to do business with HPD (e.g., as developers or contractors). Through this process, some of which is performed in consultation with the Department of Investigation (DOI), HPD ensures that sponsors are honest, reliable stewards of public resources. Among other things, HPD attempts to identify: history of noncompliance with local, state and federal rules and regulations, including violations, administrative findings and debarments; pending and prior litigation; and negative contracting history with the city. | HPD will require disclosure and background checks through its Sponsor Review process to ensure the integrity of individuals and entities seeking to do business with HPD (e.g., as developers or contractors). Through this review process, some of which will be performed in consultation with the Department of Investigation (DOI), HPD’s Sponsor Review Unit will ensure that sponsors are honest, reliable stewards of public resources. Through the sponsor review process, HPD attempts to identify:  History of noncompliance with local, state and federal rules and regulations; including violations, administrative findings and debarments;  Pending and prior litigation; and  Negative contracting history with the city. | Ongoing
Inwood | Provide technical assistance to bolster capacity of local cultural organizations | 60 | Community Resources | DCLA | In Progress | DCLA developed a RFP for selection of a facilities planning consultant to assist the nonprofit arts organization who will operate the Inwood Research and Performing Arts Center. The RFP is expected to be released in summer 2019. | DCLA’s Community Arts Development Program will offer a year-long technical assistance program to Upper Manhattan cultural organizations, ensuring that leadership of these organizations have the skills and capacities to successfully meet the demands of running a performing art center. The goal of the technical assistance funding will be to enable groups to be better equipped to respond to an RFP soliciting the IRCPA operator. After a one year period, the City will issue an open RFP for an operator of IRCPA. The organization(s) selected through the RFP process to operate IRCPA will receive additional technical assistance to align IRCPA programming with community needs and interests. | Within 1 year
Inwood | Implement broadband improvements in Inwood | 61 | Community Resources | DoITT | Not Started | The City is working on a series of initiatives to increase broadband access in underserved areas like Inwood. In Q2 2019, the City opened up a reservation phase for mobile telecom installations with an emphasis on locations outside of the core of Manhattan, including Inwood. | The City will use its franchise and contracting authority to bring broadband improvements to Inwood. MOCTO and DOITT will seek private partner(s) to use City assets for the introduction of next generation "5G" wireless service and will consider possible City investment as part of a citywide study currently underway. MOCTO will also work with NYCHA and local stakeholders to enhance free Wi-Fi access for NYCHA residents. DoITT will coordinate the deployment of LinkNYC kiosks to deliver free gigabit-speed Wi-Fi along key commercial corridors. | LinkNYC installation Q3 2019; Franchise agreements Q4 2019
Inwood | Provide energy assistance to cultural organization selected to operate IRCPA | 62 | Community Resources | DCLA | Not Started | The operator will join DCLA's Energy Coalition and will be reimbursed for up to $75,000 annually once the building is constructed and open to the public. | The City, upon selection of the operator, will add IRCPA to the “Energy Coalition.” In FY 2017 the city established the “Energy Coalition,” which is a group of cultural organizations on City-owned property under DCLA’s jurisdiction that are provided baseline energy assistance. The goals of the ‘Energy Coalition’, which align strongly with the City’s CreateNYC cultural plan, are to provide stable funding to select anchor cultural organizations, especially in underserved communities, and to strengthen NYC’s non-profit cultural sector through more equitable City funding. 10 organizations citywide are part of the Coalition and this would be the first site in the Inwood/Washington Heights area to be included. | Upon opening of the new performing art space
Inwood | Program the Historic Audubon Ballroom | 63 | Community Resources | EDC | In Progress | EDC is collaborating with the Malcolm X and Dr Betty Shabazz Memorial & Educational Center to improve and activate the historic Audubon Ballroom. To this end, EDC recently engaged a consultant who will work with the local Council Member and community to identify programming opportunities and produce events and programs related to the legacy of Malcolm X. To support this programming, EDC is also making capital improvements to the ballroom, including renovating floors and curtains and adding amenities to make the space more inviting and increase its use. | NYCEDC will program the Historic Audubon Ballroom with programming from the Malcolm X Betty Shabazz Center and also collaborate with the local City Council office to make the Ballroom available for use by other local organizations to conduct events and provide services. | 2019 - 2020
Inwood | Advance calendaring of the Park Terrace Historic District | 64 | Community Resources | LPC | Done | On December 11, 2018 the LPC designated the Park Terrace West-West 217th Street Historic District in Inwood, Manhattan. This historic district features an enclave of early 20th-century houses, with a unique history in the development of Inwood, and a special character that is reflected in its picturesque houses and landscaped topography. | LPC has determined that Park Terrace West would require further study to determine eligibility for designation as a Historic District. LPC is undertaking this study of a potential historic district and met with property owners on July 23, 2018 to discuss the research and what designation would mean. If the final results of the study and outreach are positive, the Commission will consider calendaring the Park Terrace Historic District no later than Fall 2018. | 2018
Inwood | Complete the Broadway Bridge Rehabilitation | 66 | Transportation & Infrastructure | DOT | In Progress | DOT awarded the contract to perform bridge improvements and issued the formal Notice to Proceed to the contractor in September 2018. DOT also assigned a Community Liaison for the project who has begun public outreach in both Manhattan and the Bronx. Preparations for construction are underway with work scheduled to begin later in 2019. | The current Broadway Bridge opened to traffic in 1962. In addition to the roadway and sidewalks, it also carries the #1 train. Capital plans for major rehabilitation work include repairing deteriorated steel members, replacing the roadway deck, and adding a solid-surface bike lane. Mechanical and electrical work will be done on the bridge's lift system including: replacing the current underwater control cables with droop cables hung between the towers. Each tower will get new electric service as well as auxiliary generators. | Winter 2019 Construction
Inwood | Harlem River Drive Gateway | 67 | Transportation & Infrastructure | DOT | In Progress | DOT is currently scoping the capital improvement project focused on reconstructing the intersections of Dyckman Street, 10th Avenue, and Harlem River Drive. Once the project scope is completed, DOT will formally transmit the project to DDC with design planned for 2021. This project will likely be coordinated with the initiative to improve priority intersections along 10th Avenue. | The City will reconstruct the intersection of Dyckman Street, 10th Avenue, and Harlem River Drive to provide better pedestrian crossings, provide a safer connection between Highbridge Park and the Sherman Creek/Harlem River waterfront, and create a more attractive gateway for the neighborhood. Improvements would include reduced pedestrian crossing distances, new crosswalks, sidewalks, traffic signals, pedestrian wayfinding, and street lighting. | FY 2020 Design Start
Inwood | Improve priority intersections along 10th Avenue | 68 | Transportation & Infrastructure | DOT | In Progress | DOT is scoping a capital project to improve priority intersections along 10th Avenue. This scope will be formally transmitted to DDC, who will contract for the design work in 2021 with a target start of construction in 2023. | The City will improve priority intersections along 10th Avenue, focusing on providing better pedestrian crossings, simplifying complex intersections, and calming traffic, where feasible. Intersections will include intersections with 10th Avenue at West 205th Street, West 207th Street, West 218th Street, as well as Dyckman Street and Nagle Avenue. Improvements could include reduced pedestrian crossing distances, new crosswalks, sidewalks, traffic signals, pedestrian wayfinding, benches, and street lighting, and would take into account traffic impacts. The City will also focus on enhancing the public realm and pedestrian safety under the elevated 1 Train viaduct infrastructure from Dyckman Street along Nagle and 10th Avenue to the Broadway Bridge. “Under the El” improvements would include new lighting under the elevated structure along Nagle and 10th Avenue, streetscape improvements and public realm activation at intersections, and column treatments. DOT will consult with the Community Board and the local Council Member to prioritize intersections for improvements. | FY 2020 Design Start; FY 2023-2024 Construction
Inwood | Water main and sanitary sewer replacement in northwestern Inwood | 69 | Transportation & Infrastructure | DEP | In Progress | DEP started construction of combined sewers, sanitary sewers, water distribution mains, and a small section of a new 24" trunk water main / water system regulator and chamber. Project construction costs are $13.2 million with an anticipated construction completion scheduled for October 2020. | DDC will continue to implement the project to replace sanitary sewer and water mains in the northwestern portion of Inwood. The project includes distribution water main and sanitary sewer replacements in the area generally bounded by Park Terrace East and West and West 214th and 218th Streets. | 2017-2020 (Construction) |  | DDC will continue to implement the project to replace sanitary sewer and water mains in the northwestern portion of Inwood. The project includes distribution water main and sanitary sewer replacements in the area generally bounded by Park Terrace East and West and West 214th and 218th Streets.
Inwood | Create a Drainage Plan for Inwood | 70 | Transportation & Infrastructure | EDC | In Progress | EDC is in the process of creating a drainage plan for the Inwood area. The plan will map out tributary areas and existing water and sewer routes and infrastructure and will include technical analysis to determine improvements necessary to accommodate future growth. Working with the NYC Department of Environmental Protection, EDC is on track to complete the drainage plan by the end of 2019. | The City will complete a comprehensive Drainage Plan for the Inwood area. The drainage plan will map out tributary areas and existing water and sewer routes and infrastructure and conduct technical analysis to determine the necessary improvements and changes to accommodate future growth. Following approval of the plan by the Department of Environmental Protection, DEP will identify and advance infrastructure projects to implement the Drainage Plan. | 2019
Inwood | Improve Bus Service along the 207th Street Corridor | 71 | Transportation & Infrastructure | DOT | In Progress | DOT collected traffic data at the intersections along the Bx12 route, which begins in Inwood and continues throughout the Bronx, to understand service conditions along the 207th Street Corridor. The data will be analyzed to create a signal prioritization plan. DOT expects this plan to be ready to implement, in both Manhattan and the Bronx, by the end of 2020. There is long-term DEP work happening along bus's route in the Bronx. The DEP project is scheduled to end in 2023 and there will be no impact to the Transit Signal Prioritization. | The City will examine potential enhancements to bus service along 207th Street, including ways to make the existing bus lane more visible. The City will also study adding Transit Signal Priority, or TSP, along the corridor. TSP uses smart signal technology to talk to buses as they are arriving at the signal to either extend the green signal so the bus may continue through the intersection, or turn the red signal green a few seconds sooner. On average, DOT has seen approximately a 10 percent improvement in bus speeds as a result of TSP. | Fall 2020 implementation
Inwood | Implement a neighborhood Traffic Monitoring Plan | 72 | Transportation & Infrastructure | EDC | Not Started | The Traffic Monitoring Plan will evaluate traffic and pedestrian conditions in the rezoning area, with a focus on intersections where significant adverse impacts were identified in the Final Environmental Impact Statement, such as those adjacent to the University Heights Bridge. Monitoring will commence following completion of a number of initial projects in the neighborhood. | The City will fund a Traffic Monitoring Plan (TMP) to monitor traffic and pedestrian conditions in the neighborhood for the next 15 years. The TMP will cover the entire rezoning area, with focus on intersections where significant adverse impacts were identified in the FEIS, including the intersections adjacent to the University Heights Bridge (at West 207th Street and 9th Avenue in Manhattan and at West Fordham Road and Major Deegan Expressway in the Bronx). The TMP is a product of extensive coordination between EDC, DOT, and ODMHED as the lead agency for environmental review. The TMP is intended to confirm the traffic and pedestrian impacts identified in the EIS (and the associated mitigation measures) by considering future changes in traffic and pedestrian volumes and patterns. The TMP will include monitoring of transportation conditions during construction as well as conditions once buildings are completed and operational. The TMP will track the development programs and construction methods of new developments, and compare EIS projections with real world conditions, adjusting mitigation measures if needed to reflect the incremental development of the neighborhood. By periodically monitoring traffic conditions in the neighborhood, the City will install traffic mitigation measures when needed and where most appropriate. | Ongoing
Inwood | Evaluate and explore additional modifications to the protected bicycle lanes on Dyckman Street | 73 | Transportation & Infrastructure | DOT | In Progress | Following a resurfacing project last year, DOT agreed to evaluate the Dyckman Street corridor for potential modifications to the street design. City Hall and DOT will coordinate with CB 12 and elected officials and expects to update the community later in 2019. | The Department of Transportation recently completed modifications to the bike lanes on Dyckman Street and continues to feel the facilities provide important benefits to all users of the corridor. DOT commits to make additional changes to the configuration by retaining a protected bicycle lane on the north side of the street and creating a buffered bike lane on the south side of the street, and to evaluate the effectiveness of this design over the next year. | N/A
Inwood | Work with MTA to improve subway accessibility | 74 | Transportation & Infrastructure | DOT | Not Started | MTA's New York City Transit will work to improve the accessibility of Inwood’s transit infrastructure through capital improvements or with the redevelopment of site adjacent to the subway. DOT will review designs as they relate to any street and sidewalk modifications that may be required. | As part of the Fast Forward plan, MTA New York City Transit has committed to dramatically increasing the number of accessible subway stations in the next capital program and making sure that no rider is more than two stations away from an accessible station. This standard is only partially met in Inwood. The 207th Street A Line station is fully accessible, and the Dyckman Street 1 Line station is only accessible in the southbound direction. Other Inwood stations lack ADA access. The City will work closely with the MTA on its subway accessibility plan and will seek to ensure that all communities, including Inwood, meet NYCT’s new accessibility standard | Ongoing
Inwood | Include Inwood in Ferry Feasibility Study | 75 | Transportation & Infrastructure | EDC | Done | In January 2019, EDC released a study of the feasibility of adding additional stops and routes to the existing NYC Ferry network. Dyckman Street was one of 35 sites around the city examined as potential stops. In its initial findings, NYCEDC identified 11 potential expansion sites, five of which were ultimately selected. After analysis, an Inwood/Dyckman ferry landing was not selected because commute time would be comparable or slower than existing methods of travel to job centers in Midtown and Lower Manhattan, such as the subway. | Following the launch of the first six NYC Ferry routes, EDC will undertake a new Ferry Feasibility Study to examine additional sites around the city that may be viable for future routes. The study will include Inwood as one of the neighborhoods under consideration, and will explore potential locations for routes including the Hudson River. Evaluation criteria will include: water depths, population density, travel time competitiveness with other modes, navigational challenges, journey-to-work information, capital and operating costs, transit access, planned and future developments in vicinity, and environmental siting concerns, among others. | September 2018 through mid-2019
Inwood | Mitigate transportation impacts identified in the Environmental Impact Statement | 76 | Transportation & Infrastructure | DOT | Not Started | As EDC carries out the Traffic Monitoring Plan, DOT will work with EDC in installing the signals the data would indicate are required. | The FEIS identified potential transportation impacts throughout Inwood. As new development takes place, and subject to feasibility and the results of the Traffic Monitoring Plan (described below), the City will install 13 new traffic signals at currently unsignalized intersections to mitigate traffic impacts. If practicable, the City will also install a corner bulb-out at 10th Avenue and West 206th Street to mitigate pedestrian impacts. | Ongoing through 2032
Inwood | Develop a Pilot Inwood Retail Incentive Program through UMEZ | 77 | Economic Development | UMEZ | In Progress | Implementation is paused to allow time for stakeholder input on development of the pilot program. | UMEZ will formulate an Inwood pilot retail incentive program to assist, through convertible loans, certain existing Inwood retail small businesses that relocate within Community District 12 with the purpose of continuing to operate and serve the Inwood and Washington Heights areas. Eligible businesses relocating to new developments in Inwood are eligible to apply to the pilot program. Details on program eligibility and timing is subject to UMEZ’s approval process. | Design and Approval in FY 2019 |  | Implementation is paused to allow time for stakeholder input on development of the pilot program.
Inwood | Expand outreach to provide access to capital for Inwood businesses through the Upper Manhattan Empowerment Zone (UMEZ) | 78 | Economic Development | UMEZ | In Progress | In February 2019, UMEZ closed a $4 million micro-loan program with Grameen America, Inc. The new program recommits capital to home-based and other entrepreneurs in the Washington Heights and Inwood communities as well as expands access to micro-loans for entrepreneurs in East Harlem. Grameen America, Inc. will also receive a $115,000 grant to administer this program. UMEZ is working with the Chamber of Commerce of Washington Heights and Inwood and Union Settlement, together with WEnyc, to expand access to capital to entrepreneurs in the Upper Manhattan communities and to provide training through workshops to help strengthen their business operations. | UMEZ offers capital access to qualifying small businesses in Upper Manhattan seeking term loans between $50,000 and $250,000 and Lines of Credit between $25,000 and $100,000. All Upper Manhattan businesses, including small businesses relocating to new developments in Inwood are eligible to apply for UMEZ loans and lines of credit. To increase uptake, UMEZ will conduct outreach to Inwood area businesses, including through the Business Solutions Center. | ongoing |  | In February 2019, UMEZ closed a $4 million micro-loan program with Grameen America, Inc. The new program recommits capital to home-based and other entrepreneurs in the Washington Heights and Inwood communities as well as expands access to micro-loans for entrepreneurs in East Harlem. Grameen America, Inc. will also receive a $115,000 grant to administer this program. UMEZ is working with the Chamber of Commerce of Washington Heights and Inwood and Union Settlement, together with WEnyc, to expand access to capital to entrepreneurs in the Upper Manhattan communities and to provide training through workshops to help strengthen their business operations.
Inwood | Increase access to employment opportunities for local residents | 79 | Economic Development | SBS | In Progress | SBS is currently hosting a variety of bridge training programs at the local Washington Heights Workforce1 Career Center, located at 516 West 181St street. The current training programs include the Bi-lingual Commercial Driver's license training, Bilingual Medical Assistant training, and the Bridge to tech entry level web development training. Ongoing targeted outreach to Inwood residents is conducted in partnership with local community organizations and partners. Outreach and services are also delivered via our Mobile Outreach Unit events, and recruitment events hosted at the local Inwood Public Library. SBS will work with its Workforce Development Division to schedule meeting with the Council Member to report on businesses and workforce services. | SBS will prioritize access for Inwood residents to Workforce1 training and recruitment services. SBS operates a network of 21 Workforce1 Career Centers across the city, including one located at 516 West 181st Street. Additionally, SBS works with a network of over 300 workforce development community partners across the city to connect Inwood residents to quality employment and training opportunities. The Center’s programming includes services designed to provide the necessary support for foreign-born New Yorkers to be successful in growing industries in the New York City labor market. The Center focuses on providing integrated and customized services to help foreign-born New Yorkers to effectively connect to job opportunities. Jobseekers can also receive support to connect to employment opportunities, connect to training opportunities and post-training employment in industries with quality employment including healthcare and technology, and develop skills to strengthen their job candidacy. Inwood residents will be able to access opportunities by visiting the Washington Heights Workforce1 Career Center, or any of the City’s 21 Workforce1 Career Centers. SBS and EDC will work with local employers, particularly healthcare providers, to make training and employment opportunities available for local residents targeting high-demand occupations, including opportunities in the healthcare, technology, and construction industries. Through the City’s Industry Partnerships, the City is developing training programs and resources to increase access to careers in industries with quality employment, including the healthcare (New York Alliance for Careers in Healthcare), technology (Tech Talent Pipeline) and construction industries. These industry partnership-developed training programs will be available for Inwood residents. The Washington Heights Workforce1 Career Center offers training opportunities for Inwood residents for careers in the healthcare and technology fields. The Center offers occupational training programs, including Bilingual Medical Assistant Training; Commercial Driver’s License Training; and Web Development Training. SBS will commit to twice-annual meetings with the Council Member to report on business and workforce services. | ongoing
Inwood | Connect Inwood residents to training programs in the healthcare industry | 80 | Economic Development | SBS | Done with ongoing work | SBS, in partnership with La Guardia Community college, is currently offering ongoing trainings in the healthcare sector at the Washington Heights Workforce 1 Career Center. Different trainings include those for a Bilingual Medical Assistant and preparation support for foreign born nurses. | The New York Alliance for Careers in Healthcare (NYACH) is an Industry Partnership, bringing together multiple stakeholders of the healthcare industry in order to address the sector’s rapidly changing labor force needs. NYACH works with employer partners to develop training program models that are aligned with industry needs. NYACH has informed trainings for in-demand occupations, including medical assistant, health coach, certified peer recovery advocate and medical coding. NYACH will continue the City’s partnership with New York Presbyterian Hospital to develop healthcare workforce development training programs, prioritized for Washington Heights and Inwood residents, to access careers in healthcare. NYACH training programs will help New York Presbyterian fulfill its commitment to hire local residents from Washington Heights and Inwood. NYACH/SBS will work with New York-Presbyterian on developing a qualified pipeline of local talent. This will include participating in the design and expansion of work-based learning experiences; recruiting local residents through industry-designed training programs for positions like medical assistants and unit clerks; expanding clinical placement agreements with local colleges offering laboratory tech science programs in an effort to address an under-supply of graduates; and exploring the development of new programs to meet high demand occupations. The Workforce1 Career Center located at 516 West 181st Street serves the residents of Inwood and Washington Heights and offers healthcare trainings tailored for foreign-born New Yorkers, including a Bi-lingual Medical Assistant training program. Through the Workforce1 Career Center system and community partners, SBS will conduct outreach to Inwood residents to connect these jobseekers to training programs in the healthcare industry. | Ongoing
Inwood | Connect Inwood residents to training programs in the technology industry | 81 | Economic Development | SBS | Done with ongoing work | SBS is currently offering a 9 week part-time tech training program designed for individuals interested in gaining access to the tech industry. The Bridge-to-tech training program serves those who seek to develop the basic technical and professional skills needed to gain admission to occupational training in web development. Courses are currently being offered at the Washington Heights Workforce 1 Career center. | The Tech Talent Pipeline (TTP) is an Industry Partnership, bringing together multiple stakeholders of the tech industry in order to address the sector’s talent pipeline needs. TTP works with employer partners to develop training program models that are aligned with industry needs. TTP has informed trainings for in-demand occupations, including associate engineers, web development, and quality assurance. SBS offers industry-informed technology training programs for Inwood residents through the Washington Heights Workforce1 Career Center, including a Web Development training program, as well as other technology training programs developed through the Tech Talent Pipeline Industry Partnership. The technology trainings accessible through the Washington Heights Workforce1 Career Center include a wide range of opportunities for New Yorkers in tech – from those with no tech experience and limited education to those with some experience. Foreign-born New Yorkers, young adults who are out-of-school, out-of-work, and veterans are priority participants for these trainings. | Ongoing
Inwood | Connect Inwood residents to training programs in the construction industry | 82 | Economic Development | SBS | Done with ongoing work | In Fiscal Year 2018, SBS launched a new partnership with Dominicanos USA (DUSA) to increase outreach to foreign born New Yorkers and connect them with workforce services. Ongoing Recruitment events in partnership with DUSA are conducted along the Inwood corridor for the upcoming cohort of Green Jobs pre-apprenticeship construction training. | Through the NYC Green Jobs Corps, SBS, with outreach assistance from the local Council office and Community Board 12, will screen Inwood residents for construction trade pre-apprenticeship training opportunities and free construction trade training. Partners in the Green Jobs Corps include Helmets to Hard Hats, Edward J. Malloy Initiative for Construction Skills and Non-Traditional Employment for Women (NEW) and Building Works, all of whom are recognized as pre-apprenticeship trainers by the Building Construction Trades Council. This construction trade training includes pre-apprenticeship training for careers in the green economy, including retrofitting buildings for increased energy efficiency. Individuals with a high school equivalency are eligible for pre-apprenticeship programs and those who may not be ready are referred to community partners and local institutions that provide additional adult and young adult education services. Additionally, SBS will connect jobseekers to construction safety training programs as these programs become available, and screen residents for employment opportunities. | Ongoing
Inwood | Encourage the development of affordable space for local small businesses | 83 | Economic Development | HPD | In Progress | In order to encourage long-term stability and affordability for local small businesses, for any mixed-use new construction project in the Inwood rezoning area receiving $2 million or more in HPD subsidy, HPD will require long-term leases (minimum of 10 years) with limited rental increases. The requirement will apply to the lesser of 5,000 square feet or 25% of the total non-residential floor area. In addition, HPD will encourage developers to work with knowledgeable community stakeholders to identify potential tenants that serve community needs. | In order to encourage long-term stability and affordability for local small businesses, for any mixed-use new construction project in the Inwood rezoning area receiving $2 million or more in HPD subsidy, HPD will require long-term leases (minimum of 10 years) with limited rental increases. The requirement will apply to the lesser of 5,000 square feet or 25 percent of the total non-residential floor area. In addition, HPD will encourage developers to work with knowledgeable community stakeholders to identify potential tenants that serve community needs. | ongoing
Inwood | Provide legal services to local businesses | 84 | Economic Development | SBS | Done with ongoing work | Ongoing biweekly legal clinics are hosted at local Washington Heights Business Solutions Center. Clients are able to connect one-on-one with with lawyers for a consultation in the following areas: selecting business structure, contract reviews, intellectual property, human resources, and employment. Additionally the Commercial Lease Assistance Program provide full representation for commercial tenants dealing with lease-related challenges. The Commercial Lease Assistance Program also delivered services and private consultations in person via the Mobile outreach unit. | SBS provides free legal assistance to Inwood businesses through the Commercial Lease Assistance Program, which provides eligible businesses with pro-bono legal services to address commercial lease issues prior to litigation. Through the program, legal service providers can assist small businesses with signing a lease; renewing, amending, or terminating an existing lease; or resolving other commercial lease-related issues, such as landlord harassment, bad conditions, and breach of contract. | ongoing
Inwood | Continue outreach to Inwood small businesses for access to support services | 85 | Economic Development | SBS | Done with ongoing work | SBS conducts ongoing outreach efforts to local merchants in the Inwood area via the local Chambers of Commerce, door to door outreach, and hosting Mobile Outreach events. The local Washington Heights Business Solutions Center partners with local organizations, community leaders, and stakeholders to promote ongoing business education courses, bimonthly legal clinics, business development workshops, and to host local business resource fairs. | Continue outreach to Inwood small businesses for access to support services SBS provides free business services to small businesses in Inwood through the NYC Business Solutions Center located at 560 West 181st street. These free services help businesses start, operate and expand in New York City and include business education, access to capital, free legal resources and commercial lease review. Since the start of the de Blasio Administration SBS has provided financing to 64 Inwood and Washington Heights businesses, connecting them to nearly $1.8 million in financing. SBS will meet with the Council Member twice a year to discuss workforce development and business services provided to Inwood residents. SBS will conduct outreach to Inwood small businesses to ensure these businesses are aware of SBS’s capital access resources for small businesses. SBS will utilize the agency’s Mobile Outreach Unit and other methods of outreach to connect Inwood businesses with capital resources. SBS works with businesses and lenders to:  Evaluate financial needs  Analyze business/ personal financials  Identify best available financial product  Work with lender(s) to package loan  Collect financial documents and complete all forms  Structure loan request  Submit final loan application to lender for analysis and review  Follow-up to ensure disbursement of funds disbursement  Provide additional clarity on loan approval/ declination, if possible  Assist in post-financing advisory SBS will meet with the Council Member twice a year to discuss workforce development and business services provided to Inwood residents. | Ongoing
Inwood | Protect and enhance viability of local businesses (Neighborhood 360°) | 86 | Economic Development | SBS | Done with ongoing work | SBS awarded $1.14 million in Neighborhood 360 grants to the Washington Heights Business Improvement District and other local nonprofit partners to staff, plan, and implement customized commercial revitalization programs informed by the Commercial District Needs Assessment over the next three years. Initial Projects include supplemental sanitation seven days a week for more than 25 block faces that include more than three hundred businesses, the recent hire of a merchant organizer dedicated to overseeing a steering committee for the newly formed Inwood Merchant Association, upcoming placemaking events, and celebration of restaurant week. | Through Neighborhood 360°, SBS worked with local community partners, including the Washington Heights BID, to conduct a Commercial District Needs Assessment (CDNA) that analyzed several local commercial corridors’ conditions and opportunities for improvements. Findings from the CDNA directly guided the priorities for the competitive Neighborhood 360° Grant opportunity, which resulted in SBS awarding $1.14 million in funding to the Inwood community from FY2017 through FY2020. In partnership with several Inwood community-based organizations, the funding is providing direct resources to staff, plan, and implement customized commercial revitalization projects including direct business services, place making activities, district marketing, supplemental sanitation services, merchant organizing door-to-door communication with merchants, and merchant networking events to facilitate formation of a merchants association if desired by community. | FY 2017 - FY 2020
Inwood | Work with Con Edison to increase local outreach for workforce development and hiring | 87 | Economic Development | SBS | In Progress | Con Edison's project is in the preliminary phase of development for the new Northern Manhattan facility. SBS will continue to work and communicate with Con Edison to develop best strategies to connect local residents to available employment opportunities once closer to the project’s development. | Con Edison will expand its efforts on workforce development in Inwood and Washington Heights. ConEd will work with the Workforce1 Career Center system to develop the best strategy to connect local residents to available employment opportunities. Con Edison will consider candidates referred by the Workforce1 Career Center system and other workforce development community partners. | ongoing
Jerome | Advance affordable housing development on publicly-owned land | 1 | Housing | HPD | In Progress | 97 West 169th Street is a site adjacent to Corporal Fischer Park that was approved for a non-open space use through State legislation and signed by Governor Cuomo in September 2017. HPD issued an RFP for the development of senior housing for this site in December 2018. Submissions were received in spring 2019. HPD is currently conducting competitive review throughout the summer and anticipates designating a developer in the fall. 1337 Jerome Avenue is a small vacant, single-story commercial building owned by HPD and located in the Jerome Avenue rezoning area. HPD will continue evaluating the feasibility of development of mixed-use affordable housing on this site. 1640-1642 Anthony Avenue includes a small vacant lot, a former play lot, owned by the Administration for Children’s Services (ACS). The site sits adjacent to the Lower Bathgate Child Care Center and across an entrance to Claremont Park. HPD will prioritize 100% affordable housing on this site. HPD hopes to begin community engagement in early fall 2019, which will inform the development of a Requests for Proposals that will be issued in fall 2019. Morrisania and Morris Heights: The City continues to advance the development of publicly owned sites in CDs 4 and 5 for affordable housing. HPD selected a development team led by Neighborhood Infill Partners in February 2018 to develop the Morrisania and Morris Heights cluster, which includes two small sites located at 130 West 182nd Street and 1647 Popham Avenue, along with seven other small and difficult-to-develop sites scattered across CDs 3 and 12. The two sites in CD 5 will be developed into approximately 29 affordable rental homes under the Neighborhood Construction Program. The sites will need to undergo environmental analysis and, eventually, Uniform Land Use Reform Procedure (ULURP) for disposition and other potential actions. The Morrisania Diagnostic and Treatment Center Surface Lot is owned by NYC Health and Hospitals (H+H), behind the Morrisania Diagnostic and Treatment Center at 1225 Gerard Avenue. The site’s address is approximately 1252 River Avenue, adjacent to the elevated train, and sits on a slope with a raised foundation, which serves to level the lot. The site is currently used for parking, and the Administration continues to evaluate how current uses can be temporarily relocated and/or incorporated into a new affordable housing development on the site. In addition to prioritizing 100% affordability, HPD will set aside at least 20% of all homes for households earning up to 30% of AMI. The Administration continues to work with H+H to meet their temporary and replacement parking needs, as well as meeting their board process requirements for site disposition. HPD plans to begin community engagement around these sites in early fall 2019, which will inform the development of a Requests for Proposals that will be issued in fall 2019. | The City will advance the development of publicly owned sites in CDs 4 and 5 for affordable housing. Morrisania and Morris Heights NCP Two small sites located at 130 West 182nd St and 1647 Popham Avenue, were included in the New Infill Homeownership Opportunities Program (NIHOP)/Neighborhood Construction Program (NCP) Request for Qualifications (RFQ) as part of the Morrisania and Morris Heights cluster. HPD selected a development team led by Neighborhood Infill Partners in February 2018 to develop these two sites, along with seven other small and difficult to develop sites scattered across CDs 3 and 12. The two sites in CD 5 will be developed into approximately 29 affordable rental homes under the Neighborhood Construction Program. The sites will need to undergo environmental analysis and, eventually, Uniform Land Use Reform Procedure (ULURP) for disposition and other potential actions. 97 West 169th Street This is a site adjacent to Corporal Fischer Park that was approved for a non-open space use through State legislation and signed by Governor Cuomo in September 2017. HPD will prioritize 100% affordable housing and deep affordability at this site, and will issue an RFP for the development of senior housing. A development team will be selected through a competitive RFP process. Morrisania Diagnostic and Treatment Center Surface Lot This is a surface lot owned by NYC Health and Hospitals (H+H), behind the Morrisania Diagnostic and Treatment Center at 1225 Gerard Avenue. The site’s address is approximately 1252 River Avenue, adjacent to the elevated train (4 line), and sits on a slope with a raised foundation, which serves to level the lot. The site is currently used for parking, and the Administration is evaluating how current uses can be temporarily relocated and/or incorporated into new affordable housing development on site. The City will recommend to the H+H board that the health clinic parking lot be developed as affordable housing with parking for clinic staff, in partnership with HPD. Approval is pursuant to review by the H+H Board and City Council. In addition to prioritizing 100% affordability, HPD will set aside at least 20% of all homes for households earning up to 30% of theAMI. A development team will be selected through a competitive RFP process. 1640-1642 Anthony Avenue This site is located at Anthony Ave and includes a small vacant lot adjacent to an active ACS facility. This small vacant site, a former play lot, is owned by Administration for Children’s Services (ACS). The site sits adjacent to the Lower Bathgate Child Care Center and across an entrance to Claremont Park. The administration will continue evaluating feasibility and determine the best course of action for the site’s development. HPD will prioritize 100% affordable housing on this site. A development team will be selected through a competitive RFP process. 1337 Jerome Avenue This site is a small vacant, single-story commercial building owned by HPD and located in the Jerome Avenue rezoning area. HPD will continue evaluating feasibility of development of mixed-use affordable housing on this site. | 2018 through Q2/3 2019
Jerome | Dedicate rental assistance to help move 250 homeless families and individuals out of shelter and into affordable housing | 2 | Housing | DSS | Done with ongoing work | From March 2018 through March 2019, 532 homeless families and individuals displaced from Jerome Avenue moved into permanent housing with the support of the Living in Communities (LINC), CITYFEPS Rent Supplement (CITYFEPS), and Special Exit and Prevention Supplement (SEPS) rental assistance programs. Of these families and individuals, 98 moved back to Jerome Avenue with this rental assistance. The City created LINC, CITYFEPS, and SEPS to help homeless families and individuals move from temporary shelters back to their communities by paying part of their rent. | The Living in Communities (LINC), CITYFEPS Rent Supplement (CITYFEPS), and Special Exit and Prevention Supplement (SEPS) Rental Assistance programs were created to help homeless families and individuals move from temporary, emergency shelter back to the community as quickly as possible by paying a portion of their rent. HRA will dedicate LINC, CITYFEPS and SEPS or any successor program resources to help 250 homeless families and individuals from the rezoning area (zip codes 10451,10452,10453,10456,10457,10468) who are currently living in shelter move back into the neighborhood if they so choose. | Within 120 days
Jerome | Department of Homeless Services (DHS) will discontinue the use of all Cluster units in Council Districts 14 and 16 | 3 | Housing | DSS | In Progress | In Council District 16, as of February 2019, 23 out of 33 cluster sites have been closed; 14 units of permanent affordable housing units have been established. In Council District 14, as of February 2019, 21 out of the 37 cluster sites have been closed; 30 units of permanent affordable housing units have been established. | DHS will discontinue the use of all cluster units in Council Districts 14 and 16 by 2021. Council District 16: As of February 2018, Council District 16 housed 46 homeless facilities, including 22 shelters, 23 cluster sites, and 1 safe haven. The 23 cluster sites will be systematically closed by 2021. Subject to cooperation of private property owners, Department of Social Services (DSS) will move forward with the goal of transitioning clusters to Tier II transitional housing or permanent affordable housing. Council District 14: As of February 2018, Council District 14 housed 38 homeless facilities, including 13 shelters and 25 cluster sites. The 25 cluster sites will be systematically closed by 2021. Subject to cooperation of private property owners, DSS will move forward with the goal of transitioning clusters to Tier II transitional housing or permanent affordable housing. Buildings that contain cluster housing will be targeted for conversion to Tier II transitional housing or permanent affordable housing. | By 2021
Jerome | The Administration commits to the continuation of its work to identify Three Quarters Housing (TQHs) | 4 | Housing | Ops | In Progress | The Task Force has continued its work to identify three-quarter houses across the five boroughs, leveraging City data and referrals from local elected officials, tenant advocacy groups and 311. The Task Force conducts weekly inspections of known three-quarter houses in order to address immediate health and safety issues. In addition, HRA has established the Rapid Rehousing Hotline where three-quarter house residents can call to make complaints. Depending on the nature of the call, HRA staff contact HPD and request an inspection which usually occurs within three days. Residents living in three-quarter housing are also encouraged to call 311 to log complaints related to health and safety in three-quarter houses. 311 accepts a broad range of complaints every day. If the caller does not reference “a three-quarter house” the assigned agency will follow up in their standard course of business. | The Task Force will continue to work with local advocates and community members on identifying three quarter houses and addressing immediate health and safety issues. This includes refreshing data on three quarter houses and inspecting new potential addresses as they are brought to the task force, as well as promoting the Rapid Rehousing Hotline. Human Resources Administration (HRA) will follow up on referrals from local elected officials and tenant advocacy groups. | Ongoing
Jerome | Create a Southwest Bronx Housing Task Force to address unsafe building conditions | 5 | Housing | HPD | Done with ongoing work | The Bronx Borough President’s office, with the offices of Council Members Gibson and Cabrera, launched the Southwest Bronx Housing Task Force in January 2019 and set goals for what the Task Force will work on. The Task Force held its first meeting with local Partners in Preservation organizations in May 2019. The goal of the Task Force is to identify buildings of concern and create action plans to address issues for each building. Building issues may include but are not limited to tax delinquencies, code violations, source of income discrimination, harassment, and expiring affordability restrictions. | HPD will convene and manage a Task Force led by the Bronx Borough President and local Council Members to identify buildings of concern and create action plans to address issues for each building. Building issues may include but are not limited to tax delinquencies, code violations, source of income discrimination, harassment, and expiring affordability restrictions. The Task Force will meet quarterly. | Summer 2018
Jerome | Implement the Neighborhood Pillars Program to help community organizations acquire rent stabilized buildings | 5 | Housing | HPD | In Progress | HPD and HDC announced the Neighborhood Pillars program in fall 2017 to finance the acquisition and rehabilitation of existing rent-regulated buildings to protect current tenants and stabilize communities. HPD released a Preservation Buyers Request for Qualifications (RFQ), and responses from organizations interested in participating are accepted on a rolling basis. HPD launched the Downpayment Assistance Fund and issued a new financing program term sheet in late 2018. The City expects to support the acquisition of a half dozen or more properties across New York City by fall 2019. | HPD and New York Housing Development Corporation (HDC) are launching a new Neighborhood Pillars program to finance the acquisition and rehabilitation of existing rent-regulated buildings to protect current tenants and stabilize communities. The City will double the capacity of the Acquisition Loan Fund to $275 million to enable non-profits and mission-based organizations to acquire buildings that are rent-regulated, but not otherwise part of an existing affordable housing program. | 2019 start
Jerome | Pilot a Landlord Ambassadors Program to provide technical assistance to Jerome Avenue area property owners | 7 | Housing | HPD | In Progress | Since June 2017, HPD has partnered with Enterprise Community Partners and community-based organizations to pilot a two year demonstration program called the Landlord Ambassadors Program. Organizations have been conducting outreach and providing technical assistance to owners of multifamily buildings in specific communities throughout the city, including the Southwest Bronx. Since the pilot began, 77 property owners have participated, 39 have applied for HPD financing, and seven have closed on construction financing. With the Ambassadors help, active properties have decreased their violations by 42% and reduced municipal arrears by 21%. HPD has recently secured funding to continue the pilot and expand it citywide, including in the Southwest Bronx. The Mutual Housing Association of New York (MHANY), a pilot program Ambassador, and Habitat for Humanity have recently requested City Council Discretionary funding to expand their services citywide, increase the number of property owners assisted, and expand the scope of services for new and currently participating owners. MHANY will continue working with local property owners to provide information about the benefits of using HPD financing programs; navigate HPD program requirements, including regulatory requirements; and package application materials for HPD review and approval. | HPD is partnering with Enterprise Community Partners to pilot a Landlord Ambassadors Program to contract with community-based organizations who will conduct outreach and provide technical assistance to owners of multifamily buildings in targeted areas across the city. The Landlord Ambassador will work with local property owners to: Provide information about the benefits of using HPD financing programs; Navigate HPD program requirements, including regulatory requirements, and package application materials for HPD review and approval; and Access local resources and vendors needed in order to close, construct, and operate their properties, including contractors, property managers, attorneys and other professionals | 2017 through 2019
Jerome | Help homeowners access the resources they need to keep, maintain, and improve their homes | 8 | Housing | HPD | In Progress | Homeownership represents both a critical source of housing and a significant asset-building opportunity for many New Yorkers, yet many lower income homeowners are struggling to obtain financing and other assistance to maintain their homes. HPD, in collaboration with Enterprise Community Partners, is working to launch HomeFix, a new program to help low- and moderate-income homeowners in small, one- to four-family properties fund home repairs. The new program will pair financial counseling with affordable low-interest or forgivable loans and leverage the services of community and non-profit partners. The program is expected to launch in 2019. | Funding for home repairs is often hard to find for low-income homeowners, especially families struggling to make mortgage payments. HPD will create HomeFix, a new program to help low- and moderate-income homeowners in small, one-to-four family properties fund home repairs. The new program will pair financial counseling with financial assistance, and leverage the services of community and non-profit partners. | 2019 start
Jerome | Proactive outreach to Jerome Ave tenants to provide access to anti-displacement resources including legal services | 10 | Housing | PEU | In Progress | Outreach specialists from the Tenant Support Unit (TSU) of the Public Engagement Unit (PEU) are conducting proactive door-to-door outreach to inform tenants of their rights, identify any housing-related issues and connect them with a range of resources, such as anti-eviction legal assistance, to keep them in their homes. To date, TSU specialists have knocked on over 58,411 doors in the area. TSU has also made over 17,458 follow up calls to provide comprehensive case management to tenants – bridging the gap between the City and tenants by helping them through the process of accessing resources. From November 2015 through June 2019, TSU specialists have assisted over 4,975 New Yorkers in zip codes 10452 and 10453. | The Tenant Support Unit (TSU), part of the Mayor’s Public Engagement Unit (PEU), uses a data-driven approach to engage and provide assistance to New Yorkers who may be at risk of displacement or experiencing harassment. Outreach specialists conduct door-to-door outreach to inform tenants of their rights, identify any housing-related issues and connect them with a range of resources, such as emergency repairs and HRA’s free legal services. Since July 2015, TSU specialists have knocked on over 32,600 doors and assisted over 6,000 tenants in the area. TSU will provide quarterly data (disaggregated by Council District) on all activities, including a list of targeted building, findings and issues encountered, and next steps to address issues. | Ongoing through 2023
Jerome | Make it easier for residents to understand, prepare for, and complete the affordable housing application process | 10 | Housing | HPD | Done with ongoing work | HPD continues to take steps to help residents become better prepared to submit complete and accurate applications. In addition to revamping its affordable housing application and lottery education materials, HPD continues to welcome new Housing Ambassadors, which are local community groups that provide free technical assistance to residents who wish to apply for affordable housing. Interested organizations are offered training and educational materials on an ongoing basis. | HPD continues to take steps to help residents become better prepared to submit complete and accurate applications. In addition to revamping its affordable housing application and lottery education materials, HPD will recruit and train Housing Ambassadors in the Jerome Avenue area, which are local community groups that provide free technical assistance to residents who wish to apply for affordable housing. | 2019
Jerome | Keep homes affordable by continuing to offer loans and tax incentives to building owners | 11 | Housing | HPD | In Progress | Since 2014, HPD has financed the preservation of over 6,900 affordable homes in CDs 4 and 5. HPD will continue monitoring homes CDs 4 and 5 with affordability restrictions in its portfolio, and use its various financing programs to preserve and invest in the neighborhood’s existing affordable housing stock. HPD will strive to preserve the affordability of as many homes as possible in the Jerome area. Since the rezoning was adopted, HPD financed the preservation of 1,400 affordable homes in CDs 4 and 5. | Since 2014, HPD has financed the preservation of over 5,500 affordable homes in CBs 4 and 5, representing more than 10% of all homes preserved across the city. HPD will continue monitoring homes in Community Districts (CDs) 4 and 5 with affordability restrictions in its portfolio, and use its various financing programs to preserve and invest in the neighborhood’s existing affordable housing stock. HPD will strive to preserve the affordability of as many homes as possible in the Jerome area through 2026. Based on an assessment of its current pipeline, the agency will initiate preservation on at least 1,500 additional affordable homes over the next two years. | Ongoing
Jerome | Establish a “Certification of No Harassment” (CONH) Pilot Program | 12 | Housing | HPD | In Progress | HPD received funding in the FY 2019 budget to implement the pilot Certification of No Harassment (CONH) program in designated neighborhoods, including Jerome Avenue area, to protect tenants from being harassed from their homes. Owners of designated buildings are be required to obtain a CONH before being granted building permits for specified covered work in the buildings. The program launched in Fall 2018. In Bronx CDs 4 and 5, 158 buildings are subject to the program, and HPD has received a CONH application related to one building since the program went into effect. | In response to feedback from the community and growing interest across the city, the Administration will enforce a pilot CONH program in designated neighborhoods, including CDs 4 and 5, to protect certain tenants from being harassed from their homes. This program will identify specific buildings which meet criteria indicating that tenants may be at risk for harassment. Owners of such buildings will be required to obtain a CONH before being granted building permits for specified covered work in the buildings. Community groups, under contract with HPD and identified through a Request for Proposals (RFP), will investigate buildings that apply for CONHs. | Fall 2018 through Fall 2021
Jerome | Pilot the new “Partners in Preservation” initiative to develop comprehensive anti-displacement strategies for buildings at risk | 13 | Housing | HPD | In Progress | HPD is launching its new Partners in Preservation pilot program in the Jerome Avenue area (Bronx CDs 4 and 5) in summer 2019. Through the program, HPD seeks to proactively prevent tenant harassment by jointly developing anti-displacement strategies with tenant organizing groups, legal service providers, and other government agencies. With funding from the New York City Housing Development Corporation and Enterprise Community Partners, tenant organizers will target at-risk buildings for strategic, tenant-led interventions and create a neighborhood-wide anti-displacement plan. Northwest Bronx Community and Clergy Coalition will receive $490,000 to implement the program in the Jerome Avenue area in partnership with New Settlement Apartments/CASA, as well as other community-based organizations and legal service providers. The pilot program will run for 18 months. | HPD will include the Jerome Avenue area in its new Partners in Preservation initiative and launch a Preservation Action Center that will serve as a hub for neighborhood-based anti-displacement initiatives. HPD will pair agency data with the on-the-ground experience and work of Council Members and other elected officials, community-based organizations, legal service providers, and local stakeholders to advance a comprehensive anti-displacement plan for the Jerome Avenue area. Strategies are expected to combine new and existing tools to address harass­ment and disrepair; provide tenants with anti-eviction legal services; protect home­owners from foreclosure and predatory activities; and help building owners access HPD financial resources to improve their buildings and preserve affordability. As part of this initiative: This initiative will seek to identify and prevent the deregulation of affordable homes in CDs 4 and 5. HPD will conduct an analysis of the existing housing stock, including an inventory of all regulated affordable housing to the extent possible using existing data sources and an assessment of the potential for displacement and/or deregulation. HPD and partner organizations will develop and implement tailored action plans for approximately 40 rent-regulated buildings comprising 1,000 homes. Action plans will consist of building-specific strategies that seek to keep people in their homes, prevent deregulation, and preserve affordability. Strategies will include tenant organizing and education, legal counseling, litigation, proactive code enforcement, and owner outreach and technical assistance. Risk analysis: This initiative will seek to identify and prevent the deregulation of affordable homes in CDs 4 and 5. HPD will conduct an analysis of the existing housing stock, including an inventory of all regulated affordable housing to the extent possible using existing data sources and an assessment of the potential for displacement and/or deregulation. Neighborhood preservation goals: The risk analysis will inform a series of neighborhood-wide preservation goals, strategies, and actions to protect vulnerable households to protect vulnerable households and and ensure the Jerome Avenue area remains affordable into the future. Building action plans: HPD and partner organizations will develop and implement tailored action plans for approximately 40 rent-regulated buildings comprising 1,000 homes. Action plans will consist of building-specific strategies that seek to keep people in their homes, prevent deregulation, and preserve affordability. Strategies will include tenant organizing and education, legal counseling, litigation, proactive code enforcement, and owner outreach and technical assistance. Coordination: HPD and partner organizations will implement action plans in close coordination with tenant organizers, legal service providers, TSU, other government agencies, and the new Southwest Bronx Housing Task Force. Tenant organizing: This initiative will leverage funding for tenant organizers and legal service providers to partner with HPD to develop and implement building action plans. The Preservation Action Center will be housed within a community-based organization already on the ground in the neighborhood. Meeting frequency: HPD will convene regular project management/coordination meetings with partner organizations, and it will meet bi-monthly or upon request with local Council Members’ offices. Data sharing: Affordable housing data, including preserved and newly constructed homes with affordability levels and homes at risk of deregulation, as well as updates on the implementation of building action plans, will be shared with the Council Members at bi-monthly meetings or upon request. | 2019
Jerome | Incentivize the development of deeply affordable housing that exceeds minimum MIH requirements | 14 | Housing | HPD | In Progress | Since 2014, HPD has financed the construction of 2,222 new affordable homes in Bronx CDs 4 and 5. Of these, approximately 50% are serving households earning extremely low and very low incomes. Since the rezoning, 355 new affordable homes have been created in the rezoning area. In July 2019, construction is expected to commence on the first of the 2-phased River Crest project. Once completed, the 2 buildings will provide 500 new affordable homes, of which over 110 units will be serving households earning extremely low and very low incomes. The project's first phase is expected to have 250 units with at least 20,000 sqf each of retail and community facility space. | HPD recently updated its financing terms for its Extremely Low & Low-Income Affordability (ELLA) and Mix & Match programs to enable deeper affordability levels and to set aside homes for formerly homeless households. Additionally, any MIH project receiving City subsidy must now provide 15% more permanently affordable homes than required by the MIH program alone. Housing developments financed by HPD, greater than 45 homes, will include at least 10% of all homes for families earning less than 30% of the Area Median Income (AMI), and an additional 10% for families earning at or below 50% of AMI. If MIH Option 1 and the Deep Affordability Option are mapped along the Jerome Avenue corridor, any project that receives HPD financing under the ELLA or Mix & Match programs will be required to set aside between 35% and 40% of all homes as permanently affordable. | Ongoing
Jerome | Expand local hiring incentives in HPD-financed developments | 15 | Economic Development | HPD | In Progress | In all HPD RFPs for the development of City-owned property, respondents must demonstrate a plan for outreach to residents of the local community district related to employment opportunities generated by the proposed project. Applicants will be required to comply with their outreach plans and report regularly on outreach activities. Regarding the development of private sites, beginning with FY 2019 projects, applicants requesting City subsidies will be encouraged to demonstrate a plan for outreach to residents of the local community district related to employment opportunities generated by the proposed project. Private site developers submitting plans will be required to comply with these plans and report regularly on outreach activities. In addition, HPD will continue implementing HireNYC, which requires that any housing development receiving $2 million or more in HPD subsidy post open positions with the Workforce1 system and consider qualified candidates. Jerome Avenue area residents will be able to apply for jobs through the City’s HireNYC program at nearby Workforce1 Centers. | In all HPD RFPs for the development of City-owned property, respondents must demonstrate a plan for outreach to residents of the local community district related to employment opportunities generated by the proposed project. Applicants will be required to comply with their outreach plans and report regularly on outreach activities. Regarding the development of private sites, beginning with FY 2019 projects, applicants requesting city subsidies will be encouraged to demonstrate a plan for outreach to residents of the local community district related to employment opportunities generated by the proposed project. Private site developers submitting plans will be required to comply with these plans and report regularly on outreach activities. In addition, HPD will continue implementing HireNYC, which requires that any housing development receiving $2 million or more in HPD subsidy post open positions with the Workforce1 system and consider qualified candidates. Jerome Avenue area residents will be able to apply for jobs through the City’s HireNYC program at nearby Workforce1 Centers. See the “Workforce Development and Small Business” section for more information. | Ongoing; 2019 for private sites
Jerome | Proactively engage property owners along Jerome Avenue about the City’s resources to develop affordable housing | 15 | Housing | HPD | Done | HPD, in partnership with the Department of City Planning (DCP), the Department of Small Business Services (SBS), and local elected officials, hosted two events in 2018 for property owners in the rezoning area. At the events, HPD and DCP informed owners about the City’s resources for developing new mixed-use affordable housing and about the requirements of any developers in the rezoning area. SBS was on hand to offer information about local retail needs and resources for finding community-serving commercial tenants. | HPD, in partnership with the Department of City Planning (DCP), the Department of Small Business Services (SBS), and local elected officials, will host an event this spring for property owners in the rezoning area to inform them of the City’s resources for developing new mixed-use affordable housing and for small business support and development. | Spring 2018
Jerome | Host tenant resource fairs to educate tenants about their rights and resources to prevent displacement | 16 | Housing | HPD | In Progress | HPD is committed to working with partner agencies, elected officials, and community groups to ensure tenants are aware of their rights and have access to important housing resources. HPD hosted a tenant and homeowner resource fair for the Jerome Avenue area in 2019 in coordination with local councilmembers. In addition, staff from HPD's Neighborhood Education and Outreach Unit attended 10 events since last year to inform Jerome Avenue area tenants about their rights and resources. | HPD is committed to working with partner agencies, elected officials, and community groups to ensure tenants are aware of their rights and have access to important housing resources. HPD will host two tenant resource fairs per year in coordination with local Council Members. Additionally, as the Tenant Support Unit (TSU) conducts door-to-door outreach, they provide flyers informing tenants of their rights and offer assistance with accessing available resources to prevent displacement, including free legal services. | 2018 through 2021
Jerome | Continue to work with the Tenant Harassment Prevention Task Force to investigate and take action against landlords who harass tenants | 17 | Housing | HPD | Done with ongoing work | HPD participates on the Tenant Harassment Prevention Task Force, in partnership with the New York State Attorney General's office, New York State Department of Housing and Community Renewal, and other City agencies. To date, charges have been brought against two negligent landlords in the neighborhood. Additionally, HPD participates on the City Agency Task Force on Tenant Harassment with City and State agencies. Since launching in 2014 and as of March 2019, the City Agency Task Force inspected 690 buildings comprising nearly 12,000 homes, issued nearly 30,000 hazardous or immediately hazardous violations, and had either HPD- or tenant-initiated Housing Court cases against 115 buildings. | The Administration helped to create an interagency, multi-jurisdictional Tenant Harassment Prevention Task Force comprised of HPD, DOB, Department of Health and Mental Hygiene (DOHMH), the NYC Law Department, Department of Housing and Community Renewal (DHCR), and the New York State Office of the Attorney General (OAG) to investigate and bring enforcement actions – including criminal charges – against landlords who are found to be harassing tenants to force them to vacate rent-regulated homes. HPD will continue to work with the Tenant Harassment Prevention Task Force to take action against landlords in the Jerome Avenue area who are harassing tenants. | Ongoing
Jerome | Provide robust free legal representation | 17 | Housing | HRA | Done with ongoing work | Since March 2018, the City has provided 7,885 households with legal services in the Jerome Avenue Neighborhood; this includes over 20,863 individuals of which 8,440 were children. Between Fiscal Year 2013 and Fiscal Year 2020, Administration funding for legal services programs for tenants in need grew from approximately $6 million to $127 million. | New York City is the first city in the United States to ensure that all tenants facing eviction in Housing Court or in NYCHA administrative proceedings will have access to legal assistance. Through a five-year implementation plan, free legal representation will be available to all tenants with household incomes at or below 200% of the federal poverty line, or roughly $50,000 for a four-person family. Brief legal counseling will be available to those earning more. New investments to support Universal Access will be implemented and phased in over the next five fiscal years and will reach $155 million by FY 2022. At full implementation, the City’s tenant legal services programs are expected to provide access to legal services for 125,000 households, or 400,000 New Yorkers, and will level the playing field for tenants facing eviction and displacement. | Ongoing through 2022
Jerome | Continue to improve housing quality through rigorous enforcement of the Housing Maintenance Code | 19 | Housing | HPD | Done with ongoing work | As part of the City’s continued focus in the Jerome Avenue area, HPD conducted 42,166 inspections in CDs 4 and 5 in FY 2018, and as a result issued 57,345 violations. | As part of the City’s focus in the Jerome Avenue area, HPD has increased code inspections in Community Districts (CDs) 4 and 5 by 11%, and violations issued by 25% since 2014. HPD also spent $2.2 million in emergency repairs between Fiscal Years 2014-2017. | Ongoing
Jerome | Host outreach and marketing events to continue promoting programs that help owners make repairs and preserve affordability | 19 | Housing | HPD | In Progress | HPD continues its targeted outreach to property owners in the Jerome Avenue area, including through events, mailings, e-mails, calls, and surveying of distressed properties. HPD hosts monthly Property Owners Clinics at its downtown location, where building owners can consult one-on-one with HPD preservation finance specialists and representatives from Department of Buildings (DOB), Department of Finance (DOF), and Department of Environmental Protection (DEP). HPD has additionally hosted a homeowner and landlord resource fair, in collaboration with Councilmember Gibson. Through these efforts, HPD has reached the owners or managers of 1,847 properties in CDs 4 and 5, representing nearly 90,000 apartments. | HPD will continue its targeted outreach to property owners, including through events, mailings, e-mails, calls, and surveying of distressed properties. HPD currently hosts monthly Property Owners Clinics at its downtown location, where building owners can consult one-on-one with HPD preservation finance specialists and representatives from Department of Buildings (DOB), Department of Finance (DOF), and Department of Environmental Protection (DEP). HPD will target outreach for its monthly Property Owner Clinics – including via calls, mailings, and e-mails – to owners in the Jerome Avenue area. HPD will also conduct at least two property owner and homeowner resource events in the neighborhood. Outreach will be coordinated with local Council Members to determine communication and outreach strategies. HPD will e-mail to the Council Members regular reports of all property owner outreach conducted in the Jerome Avenue area and meet upon request. | Ongoing starting Winter 2019
Jerome | Develop Corporal Fischer Park | 21 | Open Space | DPR | In Progress | DPR kicked off the design of Corporal Fischer Park with public input meetings in September and December 2018. Design completion is expected by winter 2020. | The development of this new, approximately 1/2 acre park is an important opportunity to better serve local residents. Department of Parks and Recreation (DPR) will design and build this new park with community input. | 2019 design start
Jerome | Renovate and Expand Grant Avenue Park | 22 | Open Space | DPR | In Progress | Grant Avenue between 169th and 170th Streets will undergo a full renovation including roadbed conversion, infrastructure work, lawn area, and sports courts. A public meeting was held in May 2019 to kick off the design process. | The development of Grant Park offers an opportunity to expand open space and create a sizable neighborhood park for this community. This capital project will expand the existing park by closing Grant Avenue between 169th and 170th Streets, responding to strong community desire for increased open space and recreational opportunities. The full renovation is expected to include roadbed conversion, infrastructure work, lawn area, and 2-3 sports courts. | 2019 design start
Jerome | Activate and Enhance Bridge Playground | 23 | Open Space | DPR | In Progress | Design is complete and construction procurement is underway. DPR expects to begin construction in early 2020 pending successful procurement. | Council Member Vanessa Gibson and Borough President Ruben Diaz have each allocated $500,000 towards design and construction of a new playground on this site. The Administration commits an additional $1.6 million of funding to expand upon that previously envisioned playground project. The project is expected to include play equipment for children, and fitness equipment for adults. | 2019 design start
Jerome | Develop a new park at 1801-1805 Davidson Avenue | 24 | Open Space | DPR | In Progress | The property has been transferred to DPR and design is anticipated to start by summer 2020. | Expedite transfer of 1801-1805 Davidson Avenue (Block 2867, lot 142 lot) to the Department of Parks and Recreation (DPR) to design and build this new park with community input. If site development as a park is deemed infeasible within the budget allocated, if the Council Member and Community Board indicate in writing that other parks projects have emerged as higher priorities based on more detailed cost estimates from DPR, or if unresolved structural issues with the neighboring buildings would make the site unsafe for open space use, DPR will, in consultation with the community and Council Member, re-allocate funds to (an)other project(s) within the same Council District. | 2020 design
Jerome | Improve and Increase Access to Aqueduct Walk | 25 | Open Space | DPR | In Progress | The City continues to explore opportunities for increasing and improving access in the southern portions of Aqueduct Walk. Design is underway for reconstruction of Morton Playground and is expected to be completed by fall 2019. A planning study examining the southern segments of Aqueduct Walk is underway and is anticipated to be complete by summer 2020. | The City will continue to explore opportunities to increase and improve access in the southern portions of Aqueduct Walk, augmenting the existing linear park as well as expanding and enhancing the existing playground amenities. | 2019 - 2020
Jerome | Rename park at West 181 Street between Aqueduct Avenue and Dr. Martin Luther King Jr. Boulevard Commemorating Roscoe Brown and the Tuskegee Airmen | 26 | Open Space | DPR | Done | DPR worked with Council Member Cabrera and community board advocates to rename this site Captain Roscoe Brown, Ph.D Plaza in December 2018. | DPR will work with the Council Member, Community Board and advocates to advance the renaming of this site to Roscoe Brown Park and installation of signage. | End of 2018
Jerome | Rename park at West 181 Street between Aqueduct Avenue and Dr. Martin Luther King Jr. Boulevard Commemorating Roscoe Brown and the Tuskegee Airmen | 26 | Transportation & Infrastructure | DSNY | Done with ongoing work | DSNY continues to provide supplemental litter basket collection along the Jerome Avenue corridor as part of the Mayor's Neighborhood Rat Reduction Initiative. | In 2017, the City increased Sanitation service in the Bronx rat mitigation zone, which includes the entirety of the Jerome Avenue corridor, as part of the Mayor’s Rat Reduction Initiative. All litter baskets in the zone are now collected at least once per day, including on Sundays and holidays. In addition, the City increased curbside trash collection from three days per week to four days per week. DSNY will also expedite a review of any requests for additional street sweeping regulations and alternate side parking in the Jerome corridor as a result of additional development. | Ongoing
Jerome | Reinvigorate Department of Parks and Recreation Greenthumb community gardens | 27 | Open Space | DPR | Done | Over the last year DPR worked to invigorate and increase public access to local community gardens. DPR also worked with GrowNYC to convert a vacant site at the corner of Morton Place and University Avenue into a new community garden. | DPR will connect with each DPR Greenthumb community garden group in CDs4 and 5 and develop a plan to reinvigorate underutilized community gardens. DPR will offer technical support, resources, and collaborate on events and programming that will activate the gardens. DPR will also enforce hours of operations to ensure community members have adequate access to these spaces. | 2019 design start
Jerome | Build new Community School District 9 Elementary school | 28 | Community Resources | SCA | In Progress | SCA has identified the location 1302 Edward L. Grant Highway as a future District 9 elementary school. The new, state-of-the-art school will hold approximately 458 seats. The school will include a state-of-the art gymatorium among its amenities, and is anticipated to be completed by September 2023. | The SCA is pursuing multiple sites in CSD 9 with the goal of securing one for a new primary school. The Administration commits to building a school on one of these, or any other subsequently identified site, to hold approximately 458 seats. The school will include a state-of-the art gymatorium among its amenities. | July 2018 until identified
Jerome | Build a new Community School District (CSD) 10 Elementary school at 2355 Morris Avenue | 29 | Community Resources | SCA | In Progress | SCA has determined that a DOE-controlled site adjacent to the existing MS 363 is feasible for construction of a new, approximately 458 seat primary school. The school will include a state-of-the art gymatorium among its amenities, as well as office space that could be utilized by an afterschool provider. SCA will begin design in July 2019, with the goal of opening a new school in September 2023. | The School Construction Authority (SCA) has determined that a Department of Education (DOE)-controlled site adjacent to the existing MS 363 is feasible for construction of a new, approximately 458 seat primary school. The school will include a state-of-the art gymatorium among its amenities, as well as an office space that could be utilized by an afterschool provider. The SCA will begin design in July 2019, with the goal of opening a new school in September 2023. | 2019 - 2021
Jerome | Complete PS 33 Annex | 30 | Community Resources | SCA | In Progress | SCA has named a General Contractor for the PS 33 Annex, which will add 388 much-needed elementary seats to District 10. The new annex is anticipated to be completed by September 2021. | The PS 33 annex will add 388 much-needed elementary school seats to District 10. This new annex is anticipated to be completed by September 2021. | 2019 - Fall 2021
Jerome | Construct a new “stand-alone gymnasium” at PS 246 Poe Center School | 31 | Community Resources | SCA | In Progress | SCA has selected a General Contractor for the stand-alone gymnasium at PS 246 POE Center School. The new, stand-alone gymnasium is anticipated to open by fall 2020. | None | Beginning 2018
Jerome | Commit to fund current Capital Plan Identified Need in Community School Districts 9 and 10 in the next Capital Plan | 32 | Community Resources | SCA | In Progress | SCA has identified funding in the proposed Fiscal 2020-2024 Capital Plan for Community School District 9, Subdistrict 1 and Community School District 10, Subdistrict 4. | According to the November 2017 Amendment of the 2015-2019 SCA Capital Plan, CSD 9, Subdistrict 1 has an unfunded Identified Need of 572 seats. CSD 10, Subdistrict 4 has an unfunded Identified Need of 892 seats. The Administration commits to funding all currently unfunded Identified Needs in Districts 9 and 10 in the next Capital Plan. | 2020-2024
Jerome | Explore Community School District 10 school rezoning | 33 | Community Resources | DOE | Done with ongoing work | The DOE will work closely with the Superintendent, Community Education Council (CEC), and broader school community to plan for the new school building at 2355 Morris Avenue (anticipated opening in 2023). This may include rezoning to create a new zone for the school and address over-utilization at nearby schools, in alignment with other new capacity opening in the district. | The DOE will work closely with the Superintendent and Community Education Council (CEC) for CSD 10 to plan for the new school and address attendance zone needs, which may include rezoning. | Ongoing
Jerome | Address 46th Precinct Facility Challenges | 34 | Community Resources | NYPD | In Progress | NYPD initiated a site search request with DCAS for alternative locations for the 46th precinct. The request was conceptually approved by OMB in Fall 2018, and NYPD submitted all programmatic requirements to DCAS and CBRE early 2019. CBRE will generate a program for NYPD and OMB approval and then site search will begin. The site search process is managed by DCAS. | The City will initiate a process to conduct a site search for alternative locations that can later be assessed for feasibility of relocating the NYPD 46th Precinct to a more central location along the Jerome Avenue corridor. The City will report the findings of this site search, including a list of potential sites, to the local Council Member. The City will explore interim solutions (including the potential for on-site parking stackers) to relieve neighborhood parking congestion. | 2020
Jerome | Install NYPD Argus security cameras within the Jerome Avenue rezoning area along Jerome Avenue corridor and intersecting commercial corridors | 35 | Community Resources | NYPD | In Progress | NYPD completed site surveys and secured funding through the City Council. NYPD anticipates completing the installment of cameras by December 2019. | The NYPD will site and install 20 cameras along the corridor in consultation with local Council Members. | Ongoing
Jerome | Convene Jerome Avenue Public Health Taskforce & Neighborhood Health Plan | 36 | Community Resources | DOHMH | Done with ongoing work | The Jerome Avenue Public Health Taskforce first convened in December 2018. The Taskforce, which is made up of community-based organizations, advocacy groups, healthcare partners, and community residents, meets monthly to develop a vision, goals and strategies for a Neighborhood Health Plan. The Taskforce held their first meeting in June 2019. | DOHMH’s Center for Health Equity will partner with the Council Members and local stakeholders to form the Jerome Avenue Public Health Taskforce. This Taskforce will develop and implement a Neighborhood Health Plan to address health outcomes in the Jerome Avenue Study area. The Jerome Avenue Public Health Taskforce will include local partners from the healthcare sector, community-based organizations, faith-based organizations, community boards, educational institutions, local residents, and advocates, among others. The taskforce will work together for 18 months to develop and begin implementation of a Neighborhood Health Plan for CDs 4 & 5 to address key community health priorities including healthy food access, air quality and environmental health, access to healthcare, and construction mitigation strategies (including noise, pollutants, pest control, etc.). | Spring 2018
Jerome | Invest in improvements and expansion Davidson Community Center | 37 | Community Resources | DDC | In Progress | DDC is working with the Davidson Community Center, DCP, and DCAS to confirm an appropriate scope to meet project goals within the given budget. | The Davidson Community Center facility (located at 2038 Davidson Avenue) provides much-needed social and community services in the neighborhood and frequently hosts community events. To invest in this important facility and make it accessible, the City will install an elevator and expand the building to a full second floor. | Design to begin within 3 months of completion of CPSD
Jerome | Provide afterschool programming at new school to be located at 2355 Morris Avenue | 38 | Community Resources | DYCD | Not Started | DYCD is committed to providing engaging afterschool services at the new District 10 community school upon its completion. The school is scheduled to open for the 2023-24 school year. | Community center administrative space will be incorporated into the design of the District school, and the City will fund afterschool services at the new school when it opens. | Pending completion of school
Jerome | Increase local access to healthy foods | 39 | Community Resources | DOHMH | Done with ongoing work | The 2019 Health Bucks application for community organizations opened in May, 2019. DOHMH invited Inwood CBO’s to apply to distribute Health Bucks. | Health Bucks are $2 coupons distributed by DOHMH that can be used to purchase fresh fruits and vegetables at all NYC farmers markets. The City will conduct targeted outreach to qualified Community-Based Organizations (CBOs), in coordination with the local Council Members’ offices, with the goal of increasing the number of organizations that apply to distribute Health Bucks. Increasing access to healthy food will be a focus of the planning efforts of the Jerome Public Health Task Force. | Summer 2018
Jerome | Implement “Under the EL” Public Realm Improvements | 40 | Transportation & Infrastructure | DOT | In Progress | Three sites on Jerome Avenue, 170th Street, Burnside Avenue, and Tremont Avenue, are in preliminary design at DDC and will be completed in summer 2019. Additional improvements such as “Under the EL” Public Realm Improvements and pedestrian safety measures will also begin preliminary design at DDC in summer 2019. | The City will make public realm improvements along 16 blocks and pedestrian improvements at critical intersections along Jerome Avenue. These improvements will create safe and vibrant sidewalks and open spaces, contributing to consistent, distinctive streetscape corridor. Access and mobility will be improved across Jerome Avenue, connections strengthened to adjacent retail and residential uses, and new public space destinations for pedestrians will be created. | 2019 design, completed by 2024
Jerome | Reconstruct key step streets and commit to regular cleaning and trash removal | 41 | Transportation & Infrastructure | DOT | In Progress | The construction of the Clifford Place Step Street is mostly completed. In May 2019, the contractor opened the street to the public. DDC began working on preliminary design for the Davidson Avenue Step Street in January 2019 and expects to complete it by January 2020. | DOT will complete key projects underway or forthcoming on Jerome Avenue step streets. New York City Department of Sanitation (DSNY) will clean step streets as needed and in response to cleaning requests from community leaders, elected officials, and 311. DOT will complete the Clifford Place Step-Street Reconstruction using Inwood’s 215th Street step street as a model with, seating, LED lighting, and a bike channel. DSNY will clean step streets as needed and in response to cleaning requests from community leaders, elected officials and 311 Davidson Avenue Step-Street Reconstruction using Inwood’s 215th Street Step-Street as a model with, seating, LED lighting, and a bike channel. | 2017-2018
Jerome | Repave key streets along the corridor | 42 | Transportation & Infrastructure | DOT | Done with ongoing work | DOT completed the resurfacing of the following streets: E 179th Street between Jerome Avenue and Grand Concourse, Creston Avenue from E 178th Street to E 183rd Street, E 163rd Street from Grand Concourse to Teller Avenue, and Sheridan Avenue from E 161st Street to E 167th Street in August and September of 2018. DOT resurfaced Jerome Avenue from E 175th Street to E Tremont Avenue in April 2019. | DOT will resurface the following streets within the Jerome Ave Neighborhood Study Area: Jerome Avenue from E 175th Street to E Tremont Avenue E 179th Street between Jerome Ave and Grand Concourse Creston Avenue from E 178th St to E 183rd St E 163rd St from Grand Concourse to Teller Ave Sheridan Avenue from E 161st Street to E 167th Street DOT will inspect streets on a regular basis to include in annual resurfacing schedule. | Spring 2018
Jerome | Make Improvements to Cross Bronx intersection of Cross Bronx and Jerome Avenue | 43 | Transportation & Infrastructure | DOT | Done | DOT completed the intersection improvements at the Cross Bronx Expressway and Jerome Avenue in summer 2018. DOT also installed new crosswalks, additional pedestrian space, and a new traffic signal. | As part of the Safety Improvement Project at the intersection of the Cross Bronx Expressway and Jerome Avenue, DOT will install new crosswalks, pedestrian space, and traffic signals across Jerome Avenue and the Cross Bronx exit ramps. | Summer 2018
Jerome | Implement Commercial Corridor Improvements | 44 | Transportation & Infrastructure | DOT | In Progress | DDC will begin preliminary design for the commercial corridor streets scape in summer 2019. | The commercial corridor improvements will improve pedestrian crossings throughout the Jerome Avenue corridor intersections. These improvements address pedestrian safety concerns and promote street activation. Improvements to the underpasses under Grand Concourse shall also be considered as part of the scope of work. | 2020 design, completed by 2024
Jerome | Support Metropolitan Transportation Authority (MTA) ADA accessibility project at the 170 Street Station on the 4 line | 46 | Transportation & Infrastructure | DOT | In Progress | NYCT is currently moving forward with developing the preliminary design to make the E 170th Street Station fully ADA accessible. Once design is 30% complete, NYCT will put the contract for design-build out to bid in 2019. | The MTA has preliminarily identified the 170th Street station as one of the five City-priority stations to receive access improvements. These projects were developed as part of the City’s $2.5 billion contribution to the MTA’s 2015-2019 Capital Program. Under the proposal, the MTA will add elevators to the station and make it fully ADA accessible. | Ongoing
Jerome | The City will advocate to MTA New York City Transit (NYCT) to provide additional peak hour bus service based on growth in the area | 47 | Transportation & Infrastructure | DOT | In Progress | DOT has been meeting with NYCT to provide input about the Bronx Bus Redesign. In June 2019, NYCT released a draft Bus Redesign plan and is currently soliciting public feedback through a series of public meetings and an online portal. NYCT plans to release a final redesign plan in the fall 2019. | The rezoning was found to create significant adverse impacts for the Bx11, Bx32, Bx35 and will likely require additional peak hour buses. The DEIS analysis did not include Bx13, which also has significant ridership. The City will request that NYCT regularly review crowding on these four lines and increase bus frequencies as needed. The City will also request that NYCT study the potential need for increased peak hour buses in the Highbridge neighborhood. | Ongoing
Jerome | Address NYPD 44th Precinct parking issues through increased enforcement and changing nearby parking regulations. | 48 | Transportation & Infrastructure | NYPD | Done with ongoing work | The West Clarke Street one-way street modification and parking space increases were completed in early 2019. NYPD sends regular reminders to officers, facilitates more frequent verbal communication by the desk officer during roll calls, and distributes written materials to officers about the relevant street parking regulations and the consequences for violating those rules. | Expand NYPD parking at the intersection of River Avenue and Jerome Avenue. Implement modifications to West Clarke Street to convert to a one-way street and increase parking spaces. The department will also take additional steps to strengthen compliance among officers with existing street parking regulations. The protocol will include, but not be limited to, more frequent verbal communication by the desk officer at daily roll calls, the posting and annual distribution of written materials to officers about the relevant street parking regulations and the consequences for violating those rules. | Ongoing
Jerome | Participate in regular meetings with Council Members to review progress on POA commitments | 49 | Transportation & Infrastructure | CH | Done with ongoing work | The Mayor’s Office, DCP and CH agency partners have organized meetings with the Council Members and local Community Boards to provide annual updates on the items in the Community Plan. An interagency meeting was held in February 2019 and DCP led public presentations to Community Board 4 and 5 in April and May 2019. Additionally CH will continue to maintain more informal regular communication on specific topics and implementation actions so that we work collaboratively to deliver on the investments for the Jerome Community. | Meetings to include DCP, HPD, SBS, and other agencies as requested by Council Members. | Spring 2018
Jerome | Create a new “Jerome Program Manager” position, which will oversee all business and workforce strategies related to the Jerome Avenue rezoning. | 50 | Economic Development | SBS | Done with ongoing work | The Rezoning Manager was hired by SBS at the end of 2018. Additionally, the Rezoning Manager regularly hosts office hours at local Council members' offices in order to engage directly with local residents. | The position, housed at SBS, will provide a central contact point for businesses seeking assistance with compliance, business management, legal services, and relocation resources from SBS and partnering organization. | 2019 - 2022
Jerome | Design and Deliver Workforce Training for Auto Workers | 51 | Economic Development | SBS | In Progress | SBS is actively meeting with with different community stakeholders, local merchants, and auto workers along the Jerome avenue corridor to better understand the needs and further influence the design of the training program. Auto Training program is set to launch by the end of 2019. | SBS commits to working with a local partner to design and deliver a training program(s) tailored to the need of autoworkers. The program(s) will prepare autoworkers for new jobs in the auto industry or other in-demand industries, including construction programs like NYC Green Jobs Corps. The program would only be open to Jerome Avenue-area auto workers. SBS will also work with the JobsFirst Network as a community partner to connect Jerome Avenue youth with the West Farms Workforce 1 Career Center, which provides targeted services for out of school, out of work youth over the age of 18. SBS’s Community Partner Coordinators in the Bronx Workforce 1 Career Centers will work with JobsFirst to build this relationship. | 2019 - 2020
Jerome | Create Jerome Avenue Business Grant Program | 52 | Economic Development | SBS | In Progress | SBS is finalizing program details, including necessary changes to the NYC Administrative Code. | SBS will create a Jerome Avenue Business Grant Program to help businesses that are directly displaced and need to adapt to changes in the neighborhood. Each business that may be directly displayed will be eligible to receive grants of up to $20,000 per business. Relocation reimbursement grants will be disbursed on a rolling basis. The business owner is responsible for identifying a new location within New York City. SBS will coordinate with local community organizations and elected officials to conduct regular door-to-door outreach to notify all businesses along the corridor of these grant and loan programs. | 2018 - 2022
Jerome | Work with Jerome Avenue businesses to connect them to capital access services | 53 | Economic Development | SBS | Done with ongoing work | SBS works in partnership with local Council Members to host workshops to inform local merchant and business owners of available financing options. Through SBS's network of over 40 lenders, SBS staff assists with identifying right lines of funding as well as packaging loan applications. Capital Access assistance and services are also available via the mobile outreach unit events, at local Bronx Business Solutions Center, and by connecting with the Rezoning manager during office hours. | SBS works with business owners to assess their financing needs, identify appropriate financing options, and connect businesses to our network of over 40 lenders. SBS will connect Jerome Avenue-area to capital through on-site outreach events and the City’s NYC Business Solutions Centers. | Ongoing
Jerome | Deploy the SBS Mobile Unit to the Jerome Corridor monthly | 54 | Economic Development | SBS | Done with ongoing work | The SBS Mobile Unit is in the Jerome Corridor on a monthly basis and alternates between delivering workforce resources and business services. SBS workforce, recruitment, and training efforts are delivered via community partnerships and staff from local Workforce 1 Career centers. SBS business services are delivered via workshops in partnership with both Council members, and local community based organizations. SBS utilizes the mobile unit to connect one-on-one with merchants along the corridor and deliver business services related to financing, legal assistance, and navigating government directly in the corridor. | The SBS Mobile Unit will provide small business services and workforce development services (such as application screenings and interviews with employers) on a regular basis. The City will coordinate with local Council Members on outreach strategies, deployment schedule, locations, and specific focus areas. | 2018 - 2022
Jerome | Partner with Council Members to launch the Jerome Avenue Local Hiring and Responsible Contracting Working Group | 55 | Economic Development | SBS | Not Started | SBS looks forward to the formation of the task force and is prepared to support the its goals and plan. | This task force will be led by Council Members Gibson and Cabrera and will explore the feasibility of potential new policies to hold developers and contractors accountable for providing real and substantial job opportunities to the residents of the Bronx. This work will focus on projects receiving public subsidies within the Jerome Corridor and will consider: 1) guidelines for developing contractor local hiring plan, 2) guidelines for execution of local hiring plans, including hiring timeline requirements, 3) guidelines for contractor's communication with subcontractors, 4) methods for tracking and reporting hiring strategy outcomes, 5) suggestions for oversight/remediation, 6) proposals for more robust pre-construction skill training curriculum, and 7) consideration for future funding. The task force would also explore the feasibility of enacting and enforcing responsible contractor provisions. This task force would include but not be limited to representatives from HPD and SBS, community stakeholders, as well Council Members Gibson and Cabrera's offices, the Office of the Deputy Mayor for Housing & Economic Development. | Launch 2018
Jerome | Connect Jerome corridor residents to construction training programs. | 56 | Economic Development | SBS | Done with ongoing work | SBS utilizes the Mobile Outreach Unit in partnership with community organizations, the local Bronx Workforce1 Industrial and transportation career center and the Washington Heights Workforce1 Career center to organize outreach efforts to recruit and connect local residents to training and job opportunities in the industrial and construction sector | Through the NYC Green Jobs Corps, SBS will screen Jerome Avenue residents for construction trade pre-apprenticeship training opportunities and free construction trade training. Partners in the Green Jobs Corps include Helmets to Hard Hats, Edward J. Malloy Initiative for Construction Skills and Non-Traditional Employment for Women (NEW) and Building Works, all of whom are recognized as pre-apprenticeship trainers by the Building Construction Trades Council. This construction trade training includes pre-apprenticeship training for careers in the green economy, including retrofitting buildings for increased energy efficiency. In coordination with the Council Members, SBS will organize outreach events to screen and assess jobseekers for pre-apprenticeships through the program. Individuals with a high school equivalency are eligible for pre-apprenticeship programs and those who may not be ready are referred to community partners and local institutions who provide additional adult and young adult education services. | Ongoing
Jerome | Launch Auto Business Compliance and Retention Initiative | 57 | Economic Development | SBS | Done with ongoing work | SBS, in collaboration with local Council Members, City Hall, and partnering city agencies, is actively working with the New York State Department of Environmental Conservation's Office of Environmental Justice to roll out the State’s Eco-Quality Compliance program. The State’s Eco-Quality Program is scheduled to connect their services to businesses throughout the Jerome Avenue area in Summer 2019. The State's program will help inform the development of SBS’s outreach program, in which a selected community organization will follow up with businesses that have received DEC services. SBS is working to identify the community partner that will conduct and connect businesses to existing services. | City Hall will pursue partnership with the New York State Department of Environmental Conservation (DEC) to connect their services to businesses throughout the Jerome Avenue area. The City will also fund a community partner organization to follow up with businesses that have received DEC services and connect these businesses to additional local assistance, including the business services provided by SBS. Follow-up will include door-to-door visits, meetings, connection to workshops surveys, and assistance accessing capital. | 2018 - 2023
Jerome | Conduct Workforce Outreach and Recruitment Events | 58 | Economic Development | SBS | Done with ongoing work | SBS delivers workforce services directly along Jerome avenue corridor through the utilization of the Mobile Outreach Unit. SBS partners with local stakeholders and community based organizations to target and engage with local residents, foreign born, and the out-of-school out-of-work youth population | SBS will conduct outreach in the district, including recruitment events, at least every other week to connect individuals to the Workforce 1 training and employment services based on demand. Workforce 1 will hold regular recruitment events in the district where recruiters will be screening candidates to fill open jobs for current employers. Recruiters will screen and assess individuals for skills training in several sectors including: healthcare, industrial, construction, food service, and retail. Recruitment Events will include: ● Events in the neighborhood with local community partners; ● Events at the Council member’s offices; and ● Monthly deployment of the SBS Mobile Outreach Unit. | 2019 - 2023
Jerome | Continue upholding responsible contracting and labor standards for affordable housing projects receiving City subsidy | 59 | Economic Development | HPD | Done with ongoing work | HPD conducts integrity checks to ensure the integrity of individuals and entities seeking to do business with HPD (e.g., as developers or contractors). This process, some of which is performed in consultation with the Department of Investigation (DOI), ensures that sponsors are honest, reliable stewards of public resources. Among other things, HPD attempts to identify: history of noncompliance with local, state and federal rules and regulations, including violations, administrative findings and debarments; pending and prior litigation; and negative contracting history with the City. | HPD will require disclosure and background checks through its Sponsor Review process to ensure the integrity of individuals and entities seeking to do business with HPD (e.g., as developers or contractors). Through this review process, some of which will be performed in consultation with the Department of Investigation (DOI), HPD’s Sponsor Review Unit will continue to ensure that sponsors are honest, reliable stewards of public resources. Through the sponsor review process, HPD attempts to identify: History of noncompliance with local, state and federal rules and regulations; including violations, administrative findings and debarments. Pending and prior litigation; and Negative contracting history with the city. | Ongoing