## Sheet1
PUB_DATE | BORO | MANAGING_AGCY_CD | MANAGING_AGCY | PROJECT_ID | PROJECT_DESCR | TYP_CATEGORY_NAME | COMMUNITY_BOARD | BUDGET_LINE | DELAY_DESC | SITE_DESCR | SCOPE_TEXT | FY_YR1_PLAN | ORIG_BUD_AMT | CITY_PRIOR_ACTUAL | CITY_YR1_PLAN | CITY_YR2_PLAN | CITY_YR3_PLAN | CITY_YR4_PLAN | CITY_YR5_PLAN | CITY_RTC | CITY_PLAN_TOTAL | NONCITY_PRIOR_ACTUAL | NONCITY_YR1_PLAN | NONCITY_YR2_PLAN | NONCITY_YR3_PLAN | NONCITY_YR4_PLAN | NONCITY_YR5_PLAN | NONCITY_RTC | NONCITY_PLAN_TOTAL
20220309 | CITYWIDE | 042 | CITY UNIVERSITY | CA207-006 | CUNY Incubator Network | MISCELLANEOUS RECONSTRUCTION | 000 | HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PROVIDE SPACE IN EACH COMMUNITY COLLEGE TO OFFER RESOURCES FOR SMALL BUSINESS OWNERS. | 2022 | 7500 | 0 | 0 | 0 | 0 | 7160 | 0 | 0 | 7160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 042 | CITY UNIVERSITY | WFF-CUNY | Water Efficiency Upgrades at CUNY Colleges | WATER FOR THE FUTURE | 000 | EP-0009 |  |  | UNDER THIS PROJECT, WATER EFFICIENCY UPGRADES (TOILET, URINAL, AND BATHROOM FAUCET FIXTURE REPLACEMENTS AND RETROFITS) WILL BE COMPLETED ATCUNY QUEENS COLLEGE AND CUNY LEHMAN COLLEGE. HIGH-EFFICIENCY BATHROOMSINK FAUCETS, HIGH-EFFICIENCY WALL AND FLOOR MOUNTED TOILET BOWLS, WALL HUNG URINALS, AND HIGH-EFFICIENCY PLUMBING/PIPING VALVES WILL BE INSTALLED IN VERTICALLY OR HORIZONTALLY CONNECTED BATHROOMS IN CUNY QUEENS COLLEGE AND CUNY LEHMAN COLLEGE CAMPUS BUILDINGS. | 2022 | 900 | 0 | 591 | 0 | 0 | 0 | 0 | 0 | 591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79-ADA | ADA COMPLIANCE RENOVATIONS AT NYPD PRECINCTS | POLICE FACILITIES | 000 | PO-0079 |  |  | ADA COMPLIANCE RENOVATION AT NYPD PRECINTS | 2022 | 29337 | 0 | 4547 | 15753 | 9037 | 0 | 0 | 0 | 29337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79-ADA2 | ADA COMPLIANCE HUB RENOVATIONS AT NYPD PRECINCTS | POLICE FACILITIES | 000 | PO-0079 |  |  | SCOPE OF WORK | 2022 | 31852 | 0 | 0 | 2389 | 2389 | 0 | 27074 | 0 | 31852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BATH | CITYWIDE BATHROOM RENOVATION | POLICE FACILITIES | 000 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BATHROOM RENOVATION | 2022 | 346 | 36574.96 | 543 | 0 | 0 | 0 | 0 | 0 | 37117.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHD | BATHROOM RENO AT 67TH, 77TH AND TRAFFIC CONTROL DIVISION | POLICE FACILITIES | 000 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BATHROOM RENOVATION | 2022 | 1407 | 1354 | 0 | 53 | 0 | 0 | 0 | 0 | 1407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHI | BOILER REPLACEMENT AT 68TH, 76TH AND 102ND PCTS | POLICE FACILITIES | 000 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BOILER REPLACEMENTS | 2022 | 1430 | 104.5 | 1066 | 0 | 0 | 0 | 0 | 0 | 1170.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAHY | BOILERS AT 26TH, 42ND & 46TH PRECINCTS | POLICE FACILITIES | 000 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BOILER REPLACEMENT | 2022 | 1258 | 136.5 | 0 | 1521 | 0 | 0 | 0 | 0 | 1657.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAJZ | 49TH & 115TH & MTN PCT HVAC REPLACEMENT | POLICE FACILITIES | 000 | PO-0079 PU-0025 |  |  | ESTIMATES | 2022 | 2755 | 0 | 5301 | 0 | 0 | 0 | 0 | 0 | 5301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKI | BOILERS AT MTS, HWY 3, 75 & 77 PRECINCTS | POLICE FACILITIES | 000 | PO-0079 |  |  | ESTIMATE | 2022 | 3268 | 0 | 600 | 5568 | 0 | 0 | 0 | 0 | 6168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKM | PSA4 HVAC | POLICE FACILITIES | 000 | PO-0079 |  |  | ESTIMATE | 2022 | 2908 | 0 | 0 | 2908 | 0 | 0 | 0 | 0 | 2908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMAKN | BOILERS REPLACEMENT AT BMS & SRG4 | POLICE FACILITIES | 000 | PO-0079 |  |  | ESTIMATE | 2022 | 3000 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMALC | BOILERS REPLACEMENT AT 52, 77, & 108 PCT | POLICE FACILITIES | 000 | PO-0079 |  |  | SCOPE OF WORK | 2022 | 2525 | 0 | 300 | 2225 | 0 | 0 | 0 | 0 | 2525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMALE | Electric Upgrade and Generator at the 68, 108, and 120 Pct | POLICE FACILITIES | 000 | PO-0079 |  |  | SCOPE OF WORK | 2022 | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMALF | MULTI-YEAR PAVING AT VARIOUS NYPD PRECINCTS | POLICE FACILITIES | 000 | PO-0079 |  |  | SCOPE OF WORK | 2022 | 1419 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79BMALG | 101ST AND 103RD PRECINCT ROOF AND FACADE | POLICE FACILITIES | 000 | PO-0079 |  |  | SCOPE OF WORK | 2022 | 9847 | 0 | 0 | 9847 | 0 | 0 | 0 | 0 | 9847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79CWAC | CITYWIDE HVAC PROGRAM | POLICE FACILITIES | 000 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CITYWIDE | HVAC | 2022 | 20800 | 4989 | 0 | 15811 | 0 | 0 | 0 | 0 | 20800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79-GEN | PRECINCT GENERATORS LIFE CYCLE REPLACEMENTS | POLICE FACILITIES | 000 | PO-0079 |  |  | SCOPE OF WORK | 2022 | 28014 | 0 | 4816 | 6984 | 16214 | 0 | 0 | 0 | 28014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 056 | POLICE DEPARTMENT | PO79LOCK | CITYWIDE LOCKER ROOM RENOVATION | POLICE FACILITIES | 000 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CITYWIDE | LOCKER ROOMS | 2022 | 59699 | 47348.44 | 3900 | 3700 | 4751 | 0 | 0 | 0 | 59699.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 056 | POLICE DEPARTMENT | SANDCONDT | ELECTRICAL CONDUIT REPLACEMENT (SANDY) | POLICE FACILITIES |  | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ELECTRICAL | 2022 | 30329 | 0 | 0 | 404 | 0 | 0 | 0 | 0 | 404 | 0 | 207 | 3781 | 0 | 0 | 0 | 0 | 3988
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | F175DW211 | Door widening and retaining wall reconstruction - EC211 | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 |  |  | DOOR WIDENING AND RETAINING WALL RECONSTRUCTION - EC211 | 2022 | 811 | 0 | 181 | 630 | 0 | 0 | 0 | 0 | 811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | F175EC287 | Engine Company 287 | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 |  |  | EC287 | 2022 | 40000 | 0 | 3782 | 2218 | 34000 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | F175EMS20 | EMS 20 EXPANSION AND RENOVATON | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | EMS 20 EXPANSION AND RENOVATON | 2022 | 3000 | 8204.43 | 494 | 0 | 0 | 0 | 0 | 0 | 8698.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | F175EMS4M | MULTI COMPONENT RENOVATIONS - EMS 4 | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MULTI COMPONENT RENOVATIONS - EMS 4 | 2022 | 3576 | 523.35 | 0 | 0 | 3214 | 0 | 0 | 0 | 3737.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | F175EMS58 | EMS 58 Construction | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 |  |  | EMS 58 CONSTRUCTION | 2022 | 14500 | 0 | 0 | 7500 | 7000 | 0 | 0 | 0 | 14500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | F175-EMS7 | EMS 7 Station | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 |  |  | EMS 7 STATION | 2022 | 71000 | 0 | 0 | 0 | 10650 | 60350 | 0 | 0 | 71000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | F175FE220 | Emergency Floor Replacement at Engine 220/ Ladder 122 | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 |  |  | EMERGENCY FLOOR REPLACEMENT AT ENGINE 220/ LADDER 122 | 2022 | 839 | 786.08 | 64 | 0 | 0 | 0 | 0 | 0 | 850.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | F175FEC52 | Flood Mitigation Site Drainage - EC52 | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 |  |  | FLOOD MITIGATION SITE DRAINAGE - EC52 | 2022 | 712 | 0 | 112 | 600 | 0 | 0 | 0 | 0 | 712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | F175MARN4 | Marine 4 Pier Renovation | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 |  |  | MARINE 4 PIER RENOVATION | 2022 | 8600 | 0 | 0 | 0 | 8600 | 0 | 0 | 0 | 8600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | F175MC153 | MULTI COMPONENT RENOVATIONS - EC153 | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MULTI COMPONENT RENOVATIONS - EC153 | 2022 | 3070 | 1209.49 | 6615 | 0 | 0 | 0 | 0 | 0 | 7824.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | F175MC253 | Multi-Component Renovations - EC253 | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MULTI COMPONENT RENOVATIONS - EC253 | 2022 | 4471 | 10628.34 | 269 | 0 | 0 | 0 | 0 | 0 | 10897.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | F175RFMR9 | Marine 9 Roof Renovation | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 |  |  | MARINE 9 ROOF RENOVATION | 2022 | 4200 | 0 | 0 | 0 | 200 | 4000 | 0 | 0 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | F175TOI24 | Female Firefighter Toilet Upgrade - EC24 | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FEMALE FIREFIGHTER TOILET UPGRADE - EC24 | 2022 | 1348 | 3806.23 | 222 | 0 | 0 | 0 | 0 | 0 | 4028.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | F175WP276 | WATERPROOFING - EC276 | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 | PROJECT DELAYED RESULTING FROM CONTRACTOR DEFAULT |  | WATERPROOFING - EC276 | 2022 | 2329 | 3508.2 | 141 | 0 | 0 | 0 | 0 | 0 | 3649.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | F175WPE46 | Roof and Waterproofing Project - EC46 | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ROOF AND WATERPROOFING PROJECT - EC46 | 2022 | 1698 | 232.53 | 0 | 2004 | 0 | 0 | 0 | 0 | 2236.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | F175WU299 | Cellar Reconstruction - EC299 | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WATER UTILITIES- EC299 | 2022 | 994 | 157.02 | 247 | 2600 | 0 | 0 | 0 | 0 | 3004.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | F175YDE48 | Side Yard - EC48 | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 |  |  | SIDE YARD - EC48 | 2022 | 544 | 0 | 544 | 0 | 0 | 0 | 0 | 0 | 544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | F204-DEMO | FORT TOTEN DEMOLITION | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FORT TOTEN DEMOLITION | 2022 | 600 | 3298.65 | 300 | 0 | 0 | 0 | 0 | 0 | 3598.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | F204FTBLD | Fort Totten Buildings 322 and 323 | NEW FACILITIES AND RENOVATIONS | 000 | F-0204 |  | FORT TOTTEN BUILDINGS 322 AND 323 | FORT TOTTEN BUILDINGS 322 AND 323 | 2022 | 4000 | 0 | 101 | 3899 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | F204HZTAC | HazTac Trailer Replacement | NEW FACILITIES AND RENOVATIONS | 000 | F-0204 |  |  | HAZTAC TRAILER REPLACEMENT | 2022 | 350 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | F204MR634 | Fort Totten Building #634 Renovation for Marine Operations | NEW FACILITIES AND RENOVATIONS | 000 | F-0204 |  |  | FORT TOTTEN BUILDING #634 RENOVATION FOR MARINE OPERATIONS | 2022 | 650 | 590.66 | 309 | 0 | 0 | 0 | 0 | 0 | 899.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | F204RDWSH | Randall's Bunker Gear Laundry | NEW FACILITIES AND RENOVATIONS | 000 | F-0204 |  |  | RANDALL'S BUNKER GEAR LAUNDRY | 2022 | 1755 | 0 | 142 | 740 | 0 | 0 | 0 | 0 | 882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | F204RF333 | Roofing replacement at Fort Totten Building # 333 | NEW FACILITIES AND RENOVATIONS | 000 | F-0204 |  |  | ROOFING REPLACEMENT AT BUILDING # 333 ON FORT TOTTEN | 2022 | 497 | 0 | 497 | 0 | 0 | 0 | 0 | 0 | 497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | F204SHADE | Randall's Island Shade Structure | NEW FACILITIES AND RENOVATIONS | 000 | F-0204 |  | TRAINING SHADE STRUCTURE | TRAINING SHADE STRUCTURE | 2022 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | F204WATER | Randall's Island Water Tank Replacement | NEW FACILITIES AND RENOVATIONS | 000 | F-0204 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RANDALL'S ISLAND WATER TANK REPLACEMENT | 2022 | 1395 | 6631.33 | 655 | 0 | 0 | 0 | 0 | 0 | 7286.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | F212-COOL | Power and Cooling for Data Center 11 MetroTech | ELECTRONICS AND DATA PROCESSING | 000 | F-0212 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2022 | 845 | 588.55 | 8 | 248 | 0 | 0 | 0 | 0 | 844.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175D155 | Door Replacement - EC155 | NEW FACILITIES AND RENOVATIONS | 000 | F-D175 |  |  | DOOR REPLACEMENT - EC155 | 2022 | 160 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175D158 | Door Replacement - EC158 | NEW FACILITIES AND RENOVATIONS | 000 | F-D175 |  |  | DOOR REPLACEMENT - EC158 | 2022 | 160 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175D161 | Door Replacement - EC161 | NEW FACILITIES AND RENOVATIONS | 000 | F-D175 |  |  | DOOR REPLACEMENT - EC161 | 2022 | 160 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175D255 | Door Replacement - EC255 | NEW FACILITIES AND RENOVATIONS | 000 | F-D175 |  |  | DOOR REPLACEMENT - EC255 | 2022 | 250 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175DES8 | Door Replacement - EMS 8 | NEW FACILITIES AND RENOVATIONS | 000 | F-D175 |  |  | DOOR REPLACEMENT - EMS 8 | 2022 | 300 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175E287 | Door Replacement - EC287 | NEW FACILITIES AND RENOVATIONS | 000 | F-D175 |  |  | DOOR REPLACEMENT - EC287 | 2022 | 200 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175G157 | Generator - EC157 | NEW FACILITIES AND RENOVATIONS | 000 | F-D175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | GENERATOR - EC157 | 2022 | 410 | 0 | 410 | 0 | 0 | 0 | 0 | 0 | 410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175G158 | Generator - EC158 | NEW FACILITIES AND RENOVATIONS | 000 | F-D175 |  |  | GENERATOR - EC158 | 2022 | 410 | 0 | 410 | 0 | 0 | 0 | 0 | 0 | 410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175KT96 | KITCHEN - EC96 | NEW FACILITIES AND RENOVATIONS | 000 | F-D175 |  |  | KITCHEN - EC96 | 2022 | 656 | 0 | 0 | 0 | 656 | 0 | 0 | 0 | 656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | FD175MLFT | Mobile Fire Trainer- Mobile Live Fire Training Simulator | NEW FACILITIES AND RENOVATIONS | 000 | F-D175 F-0175 |  |  | MOBILE MODULAR FIRE TRAINER- MOBILE LIVE FIRE TRAINING SIMULATOR | 2022 | 500 | 0 | 518 | 0 | 0 | 0 | 0 | 0 | 518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | SANDHM265 | HURRICANE SANDY HAZMAT MITIGATION-EC265 | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 | PROJECT DELAYED PENDING NON-CITY GRANT APPROVAL |  | HURRICANE SANDY HAZMAT MITIGATION-EC265 | 2022 | 1216 | 20.19 | 0 | 173 | 0 | 0 | 0 | 0 | 193.19 | 181.73 | 0 | 1553 | 0 | 0 | 0 | 0 | 1734.73
20220309 | CITYWIDE | 057 | FIRE DEPARTMENT | SANDHM266 | HURRICANE SANDY HAZMAT MITIGATION - EC266 | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 | PROJECT DELAYED PENDING NON-CITY GRANT APPROVAL |  | HURRICANE SANDY HAZMAT MITIGATION - EC266 | 2022 | 946 | 10 | 0 | 85 | 0 | 0 | 0 | 0 | 95 | 90.05 | 0 | 765 | 0 | 0 | 0 | 0 | 855.05
20220309 | CITYWIDE | 068 | ADMIN FOR CHILDREN'S SERVICES | ACSPDF | Renovation projects for field offices | SOCIAL SERVICE BUILDINGS | 000 | CS-0003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION PROJECTS FOR FIELD OFFICES: PAINTING, NEW FLOORING, NEW CEILING SYSTEMS, AS WELL AS, PURCHASE AND INSTALLATION OF NEW MODULAR SYSTEMS FURNITURE AND ASSOCIATED EQUIPMENT | 2022 | 14821 | 0 | 1054 | 0 | 3432 | 0 | 1746 | 20132 | 26364 | 0 | 1554 | 0 | 0 | 0 | 0 | 0 | 1554
20220309 | CITYWIDE | 071 | DEPT OF HOMELESS SERVICES | HH-MRBU | MAJOR REPAIRS AND BLD UPGRADES | SHELTERS FOR HOMELESS INDIVIDUALS | 000 | HH-0112 HH-0115 |  |  |  | 2022 | 0 | 0 | 0 | 4158 | 3426 | 18779 | 4000 | 201558 | 231921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 071 | DEPT OF HOMELESS SERVICES | HRCN100VA | Volunteers of America | SHELTERS FOR HOMELESS FAMILIES | 000 | HH-D025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | IMPROVEMENTS TO VARIOUS DOMESTIC VIOLENCE SHELTERS. (CONSTRUCTION COSTS) | 2022 | 908 | 0 | 0 | 0 | 0 | 908 | 0 | 0 | 908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C75GENREP | Installation of Replacement Generators RNDC, EMTC,GMDC,RMSC | EQUIPMENT |  | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2022 | 12540 | 705.31 | 0 | 0 | 0 | 0 | 10753 | 0 | 11458.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C-75MISC | MISC INFRASTRUCTURE RECON | BUILDING SYSTEMS AND INFRASTRUCTURE | 000 | C-0075 |  | CITYWIDE | MISCELLANIOUS ITEMSMISCELLANIOUS PROJECETS FOR C-75 BUDGET LINE | 2022 | 425881 | 480.24 | 0 | 0 | 0 | 0 | 113249 | 317871 | 431600.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 072 | DEPARTMENT OF CORRECTION | C75POWRF | Replace 5 and 27 KV Feeders | BUILDING SYSTEMS AND INFRASTRUCTURE |  | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACE 5 AND 27 KV ELECTRICAL POWER FEEDERS AT RI. | 2022 | 5950 | 416.72 | 12888 | 0 | 0 | 0 | 0 | 0 | 13304.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 096 | HUMAN RESOURCES ADMINISTRATION | HR25EFOY | HRA FACILITIES & EQUIPMENT OUTYEARS FOR UPGRADES | SOCIAL SERVICES BUILDINGS | 000 | HR-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CITYWIDE | CITYWIDE FACILITIES AND EQUIPMENT UPGRADES IN OUT YEARS | 2022 | 35921 | 0 | 0 | 0 | 0 | 0 | 0 | 31870 | 31870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501CRTY | MoMA PS1 - Courtyard Access Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 000 | PV-D501 PV-0501 |  |  | COURTYARD ACCESS RENOVATION | 2022 | 2000 | 0 | 0 | 0 | 0 | 4230 | 3000 | 0 | 7230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSBARGE | New York City Ferry Barges | WATERFRONT DEVELOPMENT | 000 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CITYIWDE FERRY SERVICE BARGES | 2022 | 55000 | 99144.27 | 21561 | 10441 | 0 | 0 | 0 | 0 | 131146.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSFERRY | New York City Ferry - Ferry Purchase and Upgrade | WATERFRONT DEVELOPMENT | 000 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CITYWIDE FERRY SERVICE FERRY PURCHASE (4) | 2022 | 11600 | 6000 | 0 | 0 | 0 | 5600 | 0 | 0 | 11600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | FSHELTER | East River Ferry Service Passenger Shelters | MISCELLANEOUS | 000 | FA-D001 FA-0027 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WILLIAMSBURG FERRY SHELTERS | 2022 | 100 | 81.31 | 418 | 0 | 0 | 0 | 0 | 0 | 499.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFNEIG-H | Neighborhood Fund - Hold | NEIGHBORHOOD REVITALIZATION | 000 | ED-0384 |  |  | NEIGHBORHOOD FUND - HOLD | 2022 | 127984 | 0 | 0 | 0 | 0 | 0 | 0 | 139564 | 139564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | INFRANEIG | Neighborhood Fund | NEIGHBORHOOD REVITALIZATION | 000 | ED-0384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEIGHBORHOOD FUND | 2022 | 630821 | 0 | 0 | 0 | 0 | 0 | 0 | 3443 | 3443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | LOWMANHUD | East River Waterfront | COMMERCIAL DEVELOPMENT | 000 | ED-0075 SE-0002M HW-0001M WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REDEVELOPMENT | 2022 | 137980 | 9874.01 | 851 | 0 | 0 | 0 | 0 | 0 | 10725.01 | 154404.79 | 161 | 0 | 0 | 0 | 0 | 0 | 154565.79
20220309 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | PFLANDING | Rehabilitation of Ferry Landings | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 000 | FA-0027 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ADA REHAB | 2022 | 3600 | 2948.68 | 15 | 0 | 0 | 0 | 0 | 35 | 2998.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | RS-PH1 | Raise Shoreline- Phase 1 | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 000 | PU-0100 HW-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RAISE SHORELINE PHASE 1 | 2022 | 17883 | 0 | 25941 | 0 | 0 | 0 | 0 | 0 | 25941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDEDCAM | EDC - Hurricane Sandy - Asset Management | MISCELLANEOUS | 000 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REPAIRS TO EDC-MANAGED CITY-OWNED PROPERTY CAUSED BY HURRICANE SANDY | 2022 | 94081 | 0 | 0 | 0 | 0 | 0 | 0 | 11570 | 11570 | 0 | 20500 | 0 | 0 | 0 | 0 | 9793 | 30293
20220309 | CITYWIDE | 801 | DEPT OF SMALL BUSINESS SERVICES | TENANTIMP | Tenant Improvement Fund | INDUSTRIAL DEVELOPMENT |  | ED-0380 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TENANT IMPROVEMENT FUND - 100K JOBS PLAN | 2022 | 7500 | 0 | 0 | 0 | 0 | 1481 | 4819 | 929 | 7229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM11IHWH | INSTANTANEOUS HOT WATER HEATERS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE |  | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INSTALL INSTANTANEOUS HOT WATER HEATERS AT VARIOUS DEVELOPMENTS | 2022 | 25000 | 26587.59 | 2883 | 0 | 0 | 0 | 0 | 0 | 29470.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13GCON | GENERAL CONSTRUCTION CITYWIDE | LOW TO MODERATE INCOME PUBLIC HOUSING REHAB/RECONSTRUCTION | 000 | HA-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | GENERAL CONSTRUCTION CITYWIDE | 2022 | 4551 | 0 | 8391 | 19700 | 10000 | 41598 | 10000 | 20000 | 109689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM13VAEL | CITYWIDE ELEVATOR REPAIRS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CITYWIDE REPAIRS | 2022 | 10000 | 9870.93 | 0 | 0 | 0 | 0 | 89 | 0 | 9959.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM14VAUP | Major Renovations-Brickwork and Roofs at Sotomayer Houses | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | OPERATIONS AND MAINTENANCE | 2022 | 10000 | 17862.52 | 13304 | 0 | 0 | 0 | 0 | 0 | 31166.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM15HMLS | HOMELESS INITIATIVE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REHABILITATE 200 NYCHA UNITS | 2022 | 16940 | 11873.81 | 8380 | 0 | 0 | 0 | 0 | 0 | 20253.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SLVA | SECURITY INITIATIVES - LIGHTING AT VARIOUS DEVELOPMENTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EXTERIOR SITE LIGHTING UPGRADES AT VARIOUS DEVELOPMENTS | 2022 | 25000 | 44220.09 | 0 | 0 | 0 | 4917 | 5244 | 145 | 54526.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM16FACD | BUILDING FACADES | LOW TO MODERATE INCOME PUBLIC HOUSING REHAB/RECONSTRUCTION |  | HA-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BUILDING FACADE WORK AT VARIOUS DEVELOPMENTS | 2022 | 75000 | 39034.3 | 0 | 0 | 0 | 0 | 77 | 991 | 40102.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM16MRVR | ROOF WORK TO PREVENT MOLD AT VARIOUS DEVELOPMENTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE |  | HA-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MOLD REMOVAL AT VARIOUS DEVELOPMENTS | 2022 | 300000 | 531129.31 | 259800 | 87608 | 93395 | 136373 | 81949 | 158528 | 1348782.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BOIL | MOBLE BOILERS AT VARIOUS NYCHA DEVELOPMENTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE |  | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CITIWIDE | MOBLE BOILERS AT VARIOUS NYCHA DEVELOPMENTS CITIWIDE | 2022 | 9300 | 3791.4 | 0 | 0 | 0 | 0 | 0 | 5508 | 9299.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDCH | CITY HEATING PLANT SCOPE CHANGE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE |  | HA-0001 |  |  | CITY HEATING PLANT SCOPE CHANGE (2 DEVELOPMENTS) | 2022 | 50252 | 0 | 50252 | 0 | 0 | 0 | 0 | 0 | 50252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDCP | BUILDING IMPROVEMENTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE |  | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FUNDING FOR REHABILITATION AND CAPITAL REPAIRS TO NYCHA DEVELOPMENTS | 2022 | 2200000 | 0 | 121195 | 0 | 0 | 0 | 0 | 0 | 121195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDEE | ELEVATOR ESCALATION COST | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE |  | HA-0001 |  |  | ELEVATOR ESCALATION COST (8 DEVELOPMENTS) | 2022 | 34927 | 0 | 34927 | 0 | 0 | 0 | 0 | 0 | 34927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDLC | LEAD ABATEMENT & COMP APRROACH TO MOLD | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE |  | HA-0001 |  |  | LEAD ABATEMENT & COMPREHENSIVE APPROACH TO MOLD (2 DEVELOPMENTS) | 2022 | 501040 | 0 | 15000 | 224811 | 226073 | 0 | 35156 | 0 | 501040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDLP | LEADA ABATEMENT (PHASED PROGRAM) | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE |  | HA-0001 |  |  | LEAD ABATEMENT (PHASED PROGRAM) | 2022 | 1462296 | 0 | 31880 | 15329 | 94473 | 290686 | 100514 | 929414 | 1462296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CDWM | WASTE MANAGEMENT | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE |  | HA-0001 |  |  | WASTE MANAGEMENT | 2022 | 630290 | 0 | 83252 | 150158 | 125085 | 66908 | 64331 | 140556 | 630290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CSVA | CONCRETE SLABS AT VARIOUS DEVELOPMENTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONCRETE SLABS | 2022 | 17941 | 12468.8 | 383 | 0 | 0 | 0 | 3458 | 0 | 16309.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HEAT | HEATING SYSTEM IMPROVEMENTS AT NYCHA DEVELOPMENTS CITYWIDE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HEATING SYSTEM IMPROVEMENTS AT NYCHA DEVELOPMENTS CITYWIDE | 2022 | 200000 | 122082.25 | 207 | 0 | 0 | 0 | 76873 | 0 | 199162.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18IHWH | INSTANTANEOUS HOT WATER HEATERS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INSTALL INSTANTANEOUS HOT WATER HEATERS | 2022 | 7642 | 0 | 0 | 0 | 0 | 7642 | 0 | 0 | 7642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PNAP | Gas Risers | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE |  | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GAS RISERS | 2022 | 9558 | 0 | 0 | 0 | 0 | 0 | 0 | 8689 | 8689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RAEX | EXTERNAL COMPACTORS-BULK CRUSHERS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE |  | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INSTALL EXTERNAL COMPACTORS AND BULK CRUSHERS | 2022 | 10982 | 6456.04 | 2704 | 0 | 0 | 0 | 0 | 0 | 9160.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM18RSPL | Citywide Gas Risers, Steam Distribution, Condensate Lines | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GAS RISERS, STEAM DISTRIBUTION, CONDENSATE LINES, CITYWIDE | 2022 | 73533 | 8797.63 | 29736 | 5063 | 0 | 29936 | 0 | 0 | 73532.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DGV2 | DIGITAL VAN | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-M001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FUNDING FOR DIGITAL VAN | 2022 | 160 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MOCJ | Installation of LED Exterior Lighting Citywide | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | AS PART OF THE MAYOR'S ACTION PLAN FOR NEIGHBORHOOD SAFETY, NYCHA IS REPLACING DEVELOPMENT'S OUTDATED EXTERIOR LIGHTING SYSTEM WITH STATE-OF-THE-ART, ENERGY-EFFICIENT LED LIGHTING FOR ENTRANCES, WALKWAYS AND PARKING AREAS TO IMPROVE SAFETY IN PUBLIC SPACES FOR RESIDENTS, NYCHA STAFF, VISITORS AND VENDORS. THE NEW LIGHT INSTALLATION AS PART OF MOCJIS DESIGNED TO ENHANCE SAFETY AND REDUCE VIOLENCE AT NYCHA SITES ACCOUNTING FOR A SIGNIFICANT PORTION OF VIOLENT CRIME IN PUBLIC HOUSING. IN ADDITION, THIS WORK WILL ELIMINATE THE ONGOING OPERATING EXPENSE BEING INCURRED BY MAINTAINING PORTABLE LIGHT-SETS AT MANY OF THE LOCATIONS. | 2022 | 12478 | 4718.11 | 0 | 0 | 0 | 0 | 7760 | 0 | 12478.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20DMSC | SENIOR CENTER RENOVATION- DYCKMAN AND MARBLE HILL | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-D001 |  |  | NYCHA - RENOVATION OF DYCKMAN HOUSE AND MARBLE HILL SENIOR CENTERS --CONSTRUCTION OR RENOVATION OF DYCKMAN HOUSE SENIOR CENTER 3758 10TH AVE., MANHATTAN | 2022 | 2000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ECFL | ELLIOTT CHELSEA AND FULTON LIGHTING FOR PARKS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-D001 |  |  | IMPROVED LIGHTING FOR NYCHA PARKS -- LIGHTING IN THE PARK AREAS OF ELLIOT-CHELSEA AND FULTON HOUSES TO MAKE PLAY AREAS SAFE AND SECURE. | 2022 | 600 | 0 | 2185 | 0 | 0 | 0 | 0 | 0 | 2185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20QWGR | BEAUTIFICATION OF QUEENSBRIDGE HOUSES AND WOODSIDE HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BEAUTIFICATION OF QUEENSBRIDGE HOUSES AND WOODSIDE HOUSES -- FUNDING FOR ADDITIONAL LIGHTING NEAR GARDENS AND RENOVATION OF GARDENS INCLUDING BUT NOT LIMITED TO BENCHES, PATHWAYS, FENCING AND OTHER CAPITALLY ELIGIBLE WORK. | 2022 | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SCD8 | SECURITY CAMERAS AT NYCHA FACILITY IN DISTRICT 8 | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NYCHA SECURITY CAMERAS -- SECURITY CAMERAS AT A NYCHA FACILITY IN DISTRICT 8. | 2022 | 250 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WMEX | WASTE MANAGEMENT EXTERIOR COMPACTORS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-D001 HA-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WASTE MANAGEMENT SYSTEM -- NYCHA WASTE MANAGEMENT SYSTEM THAT INCLUDELARGE OUTDOOR COMPACTORS. HOUSING AUTHORITY CITY CAPITAL SUBSIDIES --GARBAGE CONTAINMENT COMPACTORS | 2022 | 1303 | 0 | 150 | 0 | 0 | 1153 | 0 | 0 | 1303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM21BASK | RICHARMOND TERRACE HOUSES BASKETBALL COURT RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-D001 |  |  | PB: -RENOVATION OF ONE OUTDOOR BASKETBALL COURT-INSTALLATION OF METALROOF, POSTS, HOOPS, BACKBOARDS, RESURFACINGAND PAINTING OF BLEACHERS AND REPAVING OF COURT SURFACE. | 2022 | 320 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM21COMM | NYCHA COMMUNITY CENTERS NYCHA COMMUNITY CENTERS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NYCHA COMMUNITY CENTERS | 2022 | 949 | 0 | 0 | 0 | 940 | 0 | 0 | 0 | 940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM21EXTL | NYCHA EXTERIOR LIGHTING UPGRADES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-D001 |  |  | PB: -EXTERIOR LIGHTING UPGRADES IN NYCHA DEVELOPMENTS-EXTERIOR LIGHTING UPGRADES IN | 2022 | 300 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MCCT | MARCY HOUSES COMMUNITY CENTER TECHNOLOGY UPGRADES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-K001 |  |  | MARCY HOUSES COMMUNITY CENTER TECHNOLOGY UPGRADES | 2022 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM21RPTB | 20 RAT PROOF TRASH BINS-20 RAT PROOF TRASH | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-D001 |  |  | 20 RAT PROOF TRASH BINS-20 RAT PROOF TRASH BINS | 2022 | 52 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SCD8 | NYCHA - SECURITY CAMERAS- DISTRICT 8 | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-D001 |  |  | NYCHA - SECURITY CAMERAS - DISTRICT 8-SECURITY CAMERAS IN DISTRICT 8 | 2022 | 50 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM21UWMS | UPGRADED WASTE MANAGEMENT SYSTEM FOR NYCHA PROJECT | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-D001 |  |  | PB: -UPGRADED WASTE MANAGEMENT SYSTEM FOR NYCHA--FUNDING FOR NYCHA PROJECT | 2022 | 362 | 0 | 362 | 0 | 0 | 0 | 0 | 0 | 362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM22EMAR | EAST NY CENTER- FUNDING FOR TECH UPGRADES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-D001 |  |  | EAST NEW YORK CENTER FOR MEDIA ARTS COMMUNICATIONS & TECHNOLOGY--FUNDING FOR TECH UPGRADES | 2022 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM22FACD | BUILDING FACADES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE |  | HA-0001 |  |  | BUILDING FACADES | 2022 | 111000 | 0 | 111000 | 0 | 0 | 0 | 0 | 0 | 111000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM22GISW | GREEN INFRASTRUCTURE AND STORM WATER MANAGEMENT | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE |  | HA-0001 |  |  | GREEN INFRASTRUCTURE AND STORM WATER MANAGEMENT | 2022 | 84000 | 0 | 14090 | 14090 | 14090 | 14090 | 14090 | 0 | 70450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SBNC | SOUTHEAST BRONX NEIGHBORHOOD CENTERS, INC. REPAIRS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 000 | HA-D001 |  |  | SOUTHEAST BRONX NEIGHBORHOOD CENTERS, INC. (SEBNC) - FOREST CENTER-FUNDING IS REQUEST TO MAKE REPAIRS TO THE OFFICES, CLASSROOMS, CAFETERIAAND OTHER PUBLIC SPACES UTILIZE BY STAFF AND THE COMMUNITY IN THE FACILITY. THE LOCATION IS IN NEED OF REPAIRS NOT | 2022 | 70 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CMESECURE | OCME - Agency-wide Physical Security System Upgrades | OCME | 000 | HL-0083 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  |  | 2022 | 19842 | 0 | 1000 | 9732 | 999 | 8111 | 0 | 0 | 19842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82VCLIN | EMERGENCY FUNDING FOR VARIOUS CLINICS | CLINIC RENOVATION AND REHABILITATION | 000 | HL-0082 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RENOVATE VARIOUS HEALTH CENTERS | 2022 | 41723 | 4559.92 | 4695 | 500 | 500 | 0 | 1420 | 67498 | 79172.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 02201601 | HHC PRIMARY HEALTH CLINICS | ROUTINE RECONSTRUCTION |  | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EXPAND CAPACITY IN EXISTING CLINICS AND BUILD NEW CLINICS IN UNDERSERVED AREAS. | 2022 | 104661 | 0 | 0 | 0 | 0 | 25718 | 0 | 0 | 25718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 02201602 | UPGRADE IDF AND MDF ROOMS (LAN ENVIRONMENTALS) | ROUTINE RECONSTRUCTION |  | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CORPORATE-WIDE | THIS IS A CENTRAL OFFICE INITIATIVE MANAGED BY THE OFFICE OF FACILITIES DEVELOPMENT, WORKING WITH ENTERPRISE IT SERVICES MANAGEMENT, TO UPGRADE THE IMMEDIATE DISTRIBUTION FRAME (IDF) AND MEDIUM DISTRIBUTION FRAME (MDF) ROOMS AT VARIOUS FACILITIES THROUGHOUT THE PUBLIC HEALTH CARE SYSTEM. | 2022 | 8768 | 19959.52 | 11 | 5104 | 0 | 0 | 0 | 0 | 25074.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 02202101 | SYSTEM WIDE ELEVATOR DOOR LOCK MONITORING | ROUTINE RECONSTRUCTION |  | HO-0214 |  | CORPORATE-WIDE | INSTAL ELEVATOR DOOR LOCKS | 2022 | 3554 | 3504.93 | 0 | 0 | 49 | 0 | 0 | 0 | 3553.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | 022021PM | PM/CM Services | ROUTINE RECONSTRUCTION |  | HO-0214 |  |  | PM/CM SERVIICES, SYSTEMWIDE | 2022 | 5000 | 0 | 0 | 3000 | 2000 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | HL82DISHC | DISTRICT HEALTH CENTER | CLINIC RENOVATION AND REHABILITATION |  | HL-0082 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | DISTRICT HEALTH CENTER RENOVATION | 2022 | 1600 | 1267 | 333 | 0 | 0 | 0 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 819 | HEALTH AND HOSPITALS CORP | SANDNEW | MISC CORPORATE-WIDE RECONSTRUCTION AS A RESULT OF SANDY | ROUTINE RECONSTRUCTION |  | HO-0214 |  | N/A | ADDITIONAL $410M FOR HHC FOR CORPORATE-WIDE RECONSTRUCTION PROJECTS NECESSITATED BY HURRICANE SANDY - PLACEHOLDER. | 2022 | 411111 | 0 | 0 | 725 | 0 | 0 | 0 | 0 | 725 | 0 | 17241 | 17241 | 68966 | 110041 | 108836 | 0 | 322325
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | 1360-DCS | RECONSTRUCTION OF DIST. CONTROL SYS. AT JA, NR, & OH WPCP | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SERVICE AND REPAIR OF THE DISTRIBUTED CONTROL SYSTEM AT THE JAMAICA, NORTH RIVER & OWLS HEAD WASTEWATER TREATMENT PLANT | 2022 | 647 | 646.52 | 432 | 0 | 0 | 0 | 0 | 0 | 1078.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP504 | HVAC Upgrades at Grahamsville WWTP | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT |  | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | UPSTATE | 2022 | 470 | 0 | 451 | 0 | 0 | 0 | 0 | 0 | 451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP505 | HVAC Upgrades at Margaretville WWTP | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT |  | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SQ FT | 2022 | 730 | 0 | 701 | 0 | 0 | 0 | 0 | 0 | 701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP701 | DEP- DEMAND CONTROLLED VENTILATION UPGRADE | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 000 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DEP- DEMAND CONTROLLED VENTILATION UPGRADE | 2022 | 248 | 0 | 0 | 248 | 0 | 0 | 0 | 0 | 248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AGRI-18 | FAD 18-22 WAP AND FORESTRY | FILTRATION AVOIDANCE DETERMINATION | 000 | WM-0030 |  |  | FAD 18-22 WAP AND FORESTRY | 2022 | 61750 | 40764.43 | 0 | 0 | 20000 | 0 | 0 | 0 | 60764.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON1 | Air Monitoring Analysis | FACILITY PURCHASES AND RECONSTRUCTION |  | EP-0006 |  |  | AIR MONITORING ANALYSIS | 2022 | 1500 | 0 | 1078 | 120 | 0 | 0 | 0 | 0 | 1198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AIR-MON2 | Air Monitoring Analysis | FACILITY PURCHASES AND RECONSTRUCTION |  | EP-0006 |  |  | AIR MONITORING ANALYSIS | 2022 | 1500 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ASB-REM | Asbestos Removal | FACILITY PURCHASES AND RECONSTRUCTION |  | EP-0006 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ASBESTOS REMOVAL | 2022 | 7900 | 1779.25 | 3881 | 1210 | 0 | 0 | 0 | 0 | 6870.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | AWT2-CARB | CONSTRUCTION OF CARBON ADDITION FACILITY AT VARIOUS WWTPs | BIOLOGICAL NUTRIENT REMOVAL |  | WP-0285 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | THIS PROJECT IS DESIGNED TO PROVIDE SUPPLEMENTAL CARBON ADDITION SYSTEMS TO ENHANCE NITROGEN REMOVAL AT BOWERY BAY, TALLMAN ISLAND, WARDS ISLAND, AND 26TH WARD WWTP. GLYCEROL HAS BEEN SELECTED AS THE PRIMARY CARBON SOURCE. THE SYSTEM WILL INCLUDE SUPPLEMENTAL CARBON RECEIVING STATION, BULK STORAGE, FEED AND DELIVERY, AND ANY ANCILLARY INSTRUMENTATION AND CONTROL SYSTEMS NEEDED TO OPERATE THESE FACILITIES. | 2022 | 123537 | 102102.09 | 652 | 0 | 0 | 0 | 0 | 0 | 102754.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | C519 | MODIFICATION OF CHAMBERS AT HILLVIEW | CITY TUNNEL NO. 3, STAGE 1 | 000 | W-0010 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | VALVE CHAMBERS AT HILL VIEW RESERVOIR (UPSTATE) | MODIFICATION OF CHAMBERS AT HILL VIEW RES IN CONNECTION WITH THE CONSTOF CITY TUNNEL NO 3, STAGE 1, GENERAL, ELECTRICAL, PLUMBING | 2022 | 198184 | 88475.11 | 628 | 0 | 345787 | 0 | 0 | 137300 | 572190.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAN-HYDRO | Development of Hydroelectric Cannonsville Dam. incl P'wrhse | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DEVELOPMENT OF HYDROELECTRIC CANNONSVILLE DAM. INCL P'WRHSE | 2022 | 138000 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-186 | RESURFACING SCHOHARIE ROADS WEST AND BEARKILL BRIDGE | DAM SAFETY PROGRAM | 000 | WM-0030 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | UPSTATE | RESURFACING SCHOHARIE ROADS WEST AND BEARKILL BRIDGE | 2022 | 7875 | 9880.15 | 644 | 0 | 0 | 0 | 0 | 0 | 10524.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-210 | CAT/DEL UV LIGHT TREATMENT FACILITIES | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CATSKILL & DELAWARE RESERVIORS | CATSKILL & DELAWARE ULTRAVIOLET LIGHT TREATMENT FACILITIES | 2022 | 904233 | 1572011.77 | 10811 | 0 | 0 | 0 | 0 | 0 | 1582822.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-210MP | CAT/DEL UV - MT. PLEASANT UV PLANT | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CATSKILL & DELAWARE RESERVIORS - MT. PLEASANT UV PLANT | CATSKILL & DELAWARE ULTRAVIOLET LIGHT TREATMENT FACILITIES - MT. PLEASANT UV PLANT | 2022 | 18000 | 2309.88 | 71 | 0 | 0 | 0 | 0 | 0 | 2380.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-212 | SCHOHARIE RESERVOIR/GILBOA DAM AND INTAKE/OUTLET CHAMBER | DAM SAFETY PROGRAM | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SCHOLARIE RESERVIOR/GILBOA DAM | SCHOLARIE RESERVIOR/GILBOA DAM AND INTAKE/OUTLET CHAMBER | 2022 | 390807 | 446240.73 | -2280 | 0 | 0 | 30800 | 0 | 0 | 474760.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-213 | ASHOKAN RESERVOIR/OLIVE BRIDGE DAM & UPPER/LOWER OUTLET& SCR | DAM SAFETY PROGRAM | 000 | WM-0030 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | UPSTATE | ASHOKAN RESERVIOR/OLIVE BRIDGE DAM & UPPER/LOWER OUTLET& SCREEN CHAMBERS RECONSTRUCTION | 2022 | 110000 | 135103.55 | 3841 | 9000 | 150000 | 14400 | 10300 | 913300 | 1235944.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-367 | Reconstruction of Roads at Ashokan Reservoir | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | RECONSTRUCTION OF ROUTE 28A | 2022 | 0 | 0 | 0 | 0 | 5300 | 0 | 0 | 33000 | 38300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-379 | Bureau of Police & Security Academy Renovation, Kingston | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | KINGSTON FACILITY UPGRADES & REPAIRS | 2022 | 5000 | 0 | 3643 | 2300 | 0 | 23000 | 0 | 0 | 28943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-390 | Schoharie Reservoir road improvement- NYS Rt. 990V | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SCHOHARIE RESERVOIR ROAD IMPROVEMENT- NYS RT. 990V | 2022 | 585 | 584.1 | 0 | 1100 | 0 | 0 | 4325 | 0 | 6009.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-392 | Energy Conservation Measures Improvement at Three WWTPs | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ENERGY CONSERVATION MEASURES IMPROVEMENT AT GRAND GORGE AND TANNERSVILLE WWTPS | 2022 | 10000 | 18532.59 | 571 | 0 | 0 | 0 | 0 | 0 | 19103.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-399 | CA Hudson River Drainage Chamber | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CA HUDSON RIVE DRAINAGE CHAMBER | 2022 | 2000 | 5764.89 | 2032 | 0 | 4947 | 40000 | 0 | 0 | 52743.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-427 | POOR FARM ARCH BRIDGE RECONSTRUCTION | WATER QUALITY PRESERVATION |  | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | POOR FARM ARCH BRIDGE RECONSTRUCTION | 2022 | 6000 | 0 | 0 | 0 | 5700 | 4800 | 31500 | 0 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-431 | CATSKILL AQUEDUCT RECONST.-KENSICO TO HILVIEW | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CATSKILL AQUEDUCT RECONST.-KENSICO TO HILVIEW | 2022 | 59032 | 28509.14 | 0 | 0 | 0 | 0 | 10000 | 115000 | 153509.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-452 | WOH Catskill Acqueduct Chambers Rehab & Restoration | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | WOH CATSKILL ACQUEDUCT CHAMBERS REHABILITATION & RESTORATION | 2022 | 9600 | 0 | 2644 | 0 | 0 | 18000 | 0 | 0 | 20644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-454 | RECONSTRUCTION GRAND GORGE WWTP | MISCELLANEOUS IMPROVEMENTS UPSTATE |  | WM-0030 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION GRAND GORDE WWTP | 2022 | 1700 | 0 | 0 | 0 | 1700 | 0 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-455 | RECONSTRUCTION TANNERSVILLE WWTP | MISCELLANEOUS IMPROVEMENTS UPSTATE |  | WM-0030 |  |  | PINE HILL MUNICIPAL WATER LINE EXTENSION | 2022 | 1700 | 0 | 0 | 0 | 1700 | 0 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-475 | GILBOA HLO | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | GILBOA HLO | 2022 | 14500 | 0 | 3793 | 0 | 0 | 0 | 13365 | 0 | 17158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-477 | Catskill Acqueduct Pressure Tunnels | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | TUNNEL WORK | 2022 | 217389 | 6819.23 | 6161 | 0 | 8800 | 0 | 8000 | 76700 | 106480.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-506 | Watershed WRRFs RBC Replacement | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | WATERSHED WRRFS RBC REPLACEMENT D-CM | 2022 | 18000 | 0 | 0 | 1600 | 3300 | 0 | 0 | 0 | 4900 | 0 | 0 | 0 | 0 | 33200 | 0 | 0 | 33200
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-507 | Watershed WRRFS Microfiltration and Plant Upgrades | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | WATERSHED WRRFS MICROFILTRATION AND PLANT UPGRADES | 2022 | 43000 | 0 | 0 | 0 | 3500 | 0 | 0 | 3500 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 36000
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-508 | DR-30 Culvert Repair & Embankment Stabilization | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | DR-30 CULVERT REPAIR & EMBANKMENT STABILIZATION | 2022 | 5020 | 0 | 0 | 2000 | 0 | 2000 | 0 | 7000 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-511 | Grand Gorge and Tannersville WWTP Collection System Repairs | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | GRAND GORGE AND TANNERSVILLE WWTP COLLECTION SYSTEM REPAIRS | 2022 | 10000 | 0 | 0 | 1400 | 0 | 800 | 7800 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-515 | Hudson River Drainage Chmb Bridge IGA | WATER QUALITY PRESERVATION |  | WM-0030 |  |  | IGA TO RECONSTRUCT BRIDGE PROVIDING ACCESS TO HUDSON RIVER DRAINAGE CHAMBER | 2022 | 10000 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-521 | Ashokan Fleet Garage Floor | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | ASHOKAN FLEET GARAGE FLOOR | 2022 | 2000 | 0 | 0 | 2037 | 0 | 0 | 0 | 0 | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-523 | Walkill Blow off Valves | WATER QUALITY PRESERVATION |  | WM-0030 |  |  | CATSKILL AQUEDUCT WALKILL BLOWOFF VALVES | 2022 | 18150 | 0 | 150 | 3600 | 2400 | 0 | 12000 | 0 | 18150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CAT-OPTIM | To Increase the Capacity of Upper Catskill Aqueduct | WATER FOR THE FUTURE | 000 | W-0005 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | THE PROJECT INVOLVES IMPROVEMENTS TO INCREASE THE CAPACITY OF UPPER CATSKILL AQUEDUCT,UP TO 60 MGD, WHICH EXTENDS APPROXIMATELY 74 MILES FROM ASHOKAN RESERVOIR TO KENSICO RESERVOIR. | THE PROJECT INVOLVES IMPROVEMENTS TO INCREASE THE CAPACITY OF UPPER CATSKILL AQUEDUCT,UP TO 60 MGD, WHICH EXTENDS APPROXIMATELY 74 MILES FROM ASHOKAN RESERVOIR TO KENSICO RESERVOIR. | 2022 | 139000 | 261340.52 | 33854 | 0 | 0 | 0 | 0 | 0 | 295194.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CFP-PMCS | Croton Filtration Process Monitoring & Control System | CROTON FILTER PROJECT |  | WM-0011 |  |  | CROTON FILTRATION PROCESS MONITORING & CONTROL SYSTEM UPGRADE | 2022 | 3500 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-208B | NEW CROTON DAM RECONSTRUCTION | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NEW CROTON DAM RECONSTRUCTION | 2022 | 17000 | 12650.74 | 538 | 0 | 0 | 15000 | 130000 | 0 | 158188.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-366 | REPLACE DOORS, EAST-OF-HUDSON DISTRICT | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | VARIOUS LOCATIONS THROUGHOUT THE EAST-OF-HUDSON WATER SUPPLY DISTRICT | REMOVAL AND REPLACEMENT OF HEAVY STEEL DOORS AT VARIOUS WATER SUPPLY STRUCTURES IN THE EAST-OF-HUDSON WATER SUPPLY DISTRICT | 2022 | 1275 | 4606.16 | 129 | 0 | 0 | 0 | 0 | 0 | 4735.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-410 | NEW CROTON LAKE GATE HOUSE HVAC REHABILITATION | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CROTON LAKE GATE HOUSE HVAC | 2022 | 850 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-452 | WWTP - CYCLICAL EQUIPMENT REPLACEMENT | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MAHOPAC WWTP - EQUIPMENT REPLACEMENT & FACILITY REHAB. | 2022 | 4500 | 2263.83 | 1139 | 950 | 187 | 750 | 0 | 1250 | 6539.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-502 | Road Improvement due to Kensico Dam Road Closure | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ROAD IMPROVEMENT DUE TO KENSICO DAM ROAD CLOSURE | 2022 | 2400 | 6425.95 | 791 | 0 | 0 | 0 | 0 | 0 | 7216.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-509 | Arcady Road Reconstruction | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | ARCADY ROAD IS LOCATED IN WESTCHESTER COUNTY, NY ADJACENT TO THE CROTON RESERVOIR. THIS CONSTRUCTION CONTRACT IS FOR THE RECONSTRUCTION OF APPROXIMATELY 1 MILE OF ROADWAY AND REPLACEMENT/RECONSTRUCTION OF ALL DRAINAGE CULVERTS AND GUIDE RAILING. A PORTION OF THE EXISTING ROADWAY IS COLLAPSED (DUE TO TROPICAL STORM FLOYD IN 1999) AND THE ROAD IS CURRENTLY CLOSED TO TRAFFIC. THIS SECTION OF ROADWAY WILL NEED TO BE RECONSTRUCTED AND STABILIZED. | 2022 | 2000 | 0 | 0 | 3000 | 3000 | 0 | 12000 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-530 | Removal and reconstruction of DEP bridges, upstate watershed | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACEMENT OF THE BAPTIST CHURCH ROAD BRIDGE | 2022 | 19000 | 3648.59 | 473 | 9000 | 0 | 0 | 0 | 5000 | 18121.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-534 | WEST BRANCH AUXILIARY DAM-CREEP REMEDIATION | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WEST BRANCH AUXILIARY DAM-CREEP REMEDIATION | 2022 | 4000 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-536 | EOH Dam Facing | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CATSKILL AQUEDUCT PRESSURE CAPS-MODNA SIPHON | 2022 | 21000 | 4195.8 | 0 | 3000 | 35000 | 0 | 0 | 0 | 42195.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-552 | Shaft 18 Traveling Screens & Other Work | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | PURCHASE AND INSTALLATION OF TRAVELING SCREENS AT SHAFT 18 | 2022 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-557 | Kensico Waterfowl Facility Construction & Paving | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | KENSICO WATERFOWL FACILITY CONSTRUCTION & PAVING | 2022 | 8100 | 0 | 0 | 11040 | 0 | 0 | 0 | 0 | 11040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-558 | Aqueduct Restoration at Lake Street - EOH | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | AQUEDUCT RESTORATION AT LAKE STREET - EOH | 2022 | 3500 | 0 | 0 | 0 | 3300 | 0 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-559 | MAHOPAC WTP Upgrades | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | CONVERTED DATA | 2022 | 17500 | 0 | 0 | 6000 | 0 | 0 | 3700 | 0 | 9700 | 0 | 0 | 0 | 0 | 0 | 0 | 29100 | 29100
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-570 | HILLVIEW MAINTENANCE SHOP | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HILLVIEW MAINTENANCE SHOP | 2022 | 5000 | 0 | 0 | 5250 | 0 | 0 | 0 | 0 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-586 | Amawalk Dam Improvements | DAM SAFETY PROGRAM | 000 | WM-0030 |  |  | AMAWALK DAM IMPROVEMENTS | 2022 | 23800 | 0 | 0 | 1000 | 4000 | 5000 | 0 | 13800 | 23800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-589 | EASTVIEW MAINTENANCE SHOP | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | EASTVIEW MAINTENANCE SHOP | 2022 | 5000 | 0 | 0 | 0 | 0 | 0 | 7000 | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-594 | UV FOUNDATION DRAIN MH PHASE 2 | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | UV FOUNDATION DRAIN MH PHASE 2 | 2022 | 1300 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-607 | Shaft 17 Elevator Replacement | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SHAFT 17 ELEVATOR REPLACEMENT | 2022 | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-609 | Cyclic Equipment Replacement for WTO | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | CYCLIC EQUIPMENT REPLACEMENT FOR WTO | 2022 | 3000 | 0 | 1500 | 2000 | 0 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-611 | BWS Emergency Services Contract | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BWS EMERGENCY SERVICES CONTRACT | 2022 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-624 | Conversion of Kensico Lab to EOH Operations HQ | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | CONVERSION OF KENSICO LAB TO EOH OPERATIONS HQ | 2022 | 6300 | 0 | 0 | 11174 | 0 | 0 | 0 | 0 | 11174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-636 | Hillview South Connecting Conduit Repair | CONVEYANCE |  | WM-0030 |  |  | REPAIR OF LEAK IN SOUTH CONNECTING CONDUIT AT HILLVIEW RESERVOIR | 2022 | 10700 | 0 | 0 | 0 | 1900 | 0 | 800 | 8000 | 10700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-UPGRD | UPGRADES AT CSO FACILITIES | WATER QUALITY MANDATES | 000 | WP-0169 |  |  | UPGRADES AT CSO FACILITIES | 2022 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT12VENT | CITY TUNNELS1 & 2, REPLACE VENTURI LINES @ SHAFTS | CITY TUNNEL NO. 1, RECONSTRUCTION | 000 | W-0015 |  |  | CITY TUNNELS1 & 2, REPLACE VENTURI LINES @ SHAFTS | 2022 | 22000 | 0 | 0 | 965 | 0 | 0 | 0 | 0 | 965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT315B | CITY TUNNEL 3, REPAIR LEAK@ SHAFT 15B | WATER QUALITY PRESERVATION |  | W-0013 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CITY TUNNEL 3, REPAIR LEAK@ SHAFT 15B | 2022 | 4000 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | CT3CORR | Repairs & Remediate Corrosion Issues - CT 3 | CORROSION PROTECTION SYSTEM |  | W-0013 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITY TUNNEL 3, CORRECT STAGE 1 CORROSION ISSUES | 2022 | 67000 | 11224.4 | 0 | 0 | 0 | 4244 | 42440 | 0 | 57908.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-194 | Merriman Dam Spillway | DAM SAFETY PROGRAM | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | UPSTATE | MERRIMAN DAM & RONDOUT RESERVOIR INTAKE & EFFLUENT CHAMBER | 2022 | 25250 | 2027.66 | 216 | 0 | 3000 | 35000 | 0 | 0 | 40243.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-233 | WOH WWTPs Sewer Line Stream Crossings | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | VILLAGE OF GRAHAMSVILLE, SULLIVAN COUNTY, NY | INSPECTION, AND RECONSTRUCTION IF NECESSARY, ALL PARTS OF THE GRAHAMSVILLE SEWER SYSTEM THAT CROSS STREAMS FEEDING NEW YORK CITY WATER SUPPLY | 2022 | 550 | 6517.78 | 122 | 0 | 0 | 0 | 0 | 0 | 6639.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-260 | DEL Shaft 18 Kensico Electrical Upgrade | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DEL SHAFT 18 KENSICO ELECTRICAL UPGRADE | 2022 | 775 | 11839.47 | 306 | 0 | 0 | 0 | 0 | 0 | 12145.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-359V | Shaft 4 Gate Valve Replacements | WATER QUALITY PRESERVATION |  | PU-0025 WM-0030 |  |  | SHAFT 4 GATE VALVE REPLACEMENTS | 2022 | 6000 | 0 | 500 | 2649 | 0 | 14377 | 0 | 0 | 17526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-397 | Riser Valve Control Mechanism at DA Chambers | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | DA/CA FASTENERS REPLACMENT & RISER VALVE OPERATORS | 2022 | 10000 | 1350 | 0 | 10512 | 0 | 0 | 0 | 0 | 11862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-415 | EAST DELAWARE RELEASE CHAMBER VALVE REPLACEMENTS | MISCELLANEOUS IMPROVEMENTS UPSTATE |  | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACEMENT OF RELEASE CHAMER VALVE AT EAST DELAWARE. | 2022 | 5990 | 0 | 0 | 11493 | 0 | 0 | 0 | 0 | 11493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-424 | Replacement/Rehabilitation of Honk Falls Dam | DAM SAFETY PROGRAM | 000 | WM-0030 |  |  | REPLACEMENT/REHABILITATION OF HONK FALLS DAM | 2022 | 8221 | 4327.07 | 19558 | 0 | 0 | 0 | 0 | 0 | 23885.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-434 | DAM STABILITY IMPROVEMENTS | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | DAM STABILITY IMPROVEMENTS | 2022 | 19500 | 0 | 0 | 2878 | 0 | 0 | 23000 | 0 | 25878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-439 | Sludge Drying Greenhouse Recon. at Margaretville WWTP | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | THIS PROJECT IS TO REPLACE GREENHOUSE SUPERSTRUCTURE OVER 6 SLUDGE DRYING BEDS AT THE MARGARETVILLE WASTEWATER TREATMENT PLANT (MVWWTP). | 2022 | 1990 | 2390.09 | 46 | 0 | 0 | 0 | 0 | 0 | 2436.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-450 | Downsville Water Connection | WATER QUALITY PRESERVATION | 000 | WM-0030 |  |  | DOWNSVILLE WATER CONNECTION | 2022 | 365 | 0 | 365 | 0 | 0 | 0 | 0 | 0 | 365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEL-SHFT4 | Dependability- Connection from Del Aqueduct to Cat Aqueduct | WATER FOR THE FUTURE | 000 | W-0005 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | TO CONSTRUCT A CONNCECTION FROM SHAFT 4 OF THE DELAWARE AQUEDUCT TO THE CATSKILL AQUEDUCT | TO CONSTRUCT A CONNCECTION FROM SHAFT 4 OF THE DELAWARE AQUEDUCT TO THE CATSKILL AQUEDUCT. | 2022 | 57000 | 31014.07 | 246 | 0 | 0 | 0 | 0 | 0 | 31260.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-DRA | DELAWARE-RONDOUT AQUEDUCT (PARALLEL TUNNEL TO RWBT) | WATER FOR THE FUTURE | 000 | W-0005 |  | UPSTATE | DELAWARE-RONDOUT AQUEDUCT (PARALLEL TUNNEL TO RWBT). | 2022 | 2221696 | 1063774.2 | 26326 | 0 | 0 | 0 | 0 | 0 | 1090100.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | DEP-LAB | DEP Lab Relocation | FACILITY PURCHASES AND RECONSTRUCTION |  | EP-0006 |  |  | DEP LAB RELOCATION | 2022 | 77000 | 0 | 0 | 0 | 0 | 8000 | 0 | 70000 | 78000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-GUN24 | Emergency Guniting of Sewers, Citywide | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 000 | SE-0758 |  |  | EMERGENCY GUNITING OF SEWERS, CITYWIDE. THIS IS A 1 YEAR PROJECT. THETARGETED START DATE FOR THIS CONTRACT IS AS SOON AS THE PREVIOUS CONTRACT, EC-GUN23, EXPIRES. | 2022 | 8911 | 0 | 0 | 0 | 8100 | 0 | 0 | 0 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-LC24 | Emergency Sewer Lining Contract, Citywide | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 000 | SE-0002K SE-0002M SE-0002Q SE-0002R SE-0002X |  |  | EMERGENCY SEWER LINING CONTRACT, CITYWIDE. THIS IS A 1 YEAR PROJECT. THE TARGETED START DATE FOR THIS CONTRACT IS AS SOON AS THE PREVIOUS CONTRACT, EC-LC23, EXPIRES. | 2022 | 4143 | 0 | 0 | 0 | 4052 | 0 | 0 | 0 | 4052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEC24 | Emergency Construction of Sewers, Citywide | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 000 | SE-0002K SE-0002M SE-0002Q SE-0002R SE-0002X SE-0200K SE-0200Q SE-0200R SE-0200X EP-0007 |  |  | CITYWIDE EMERGENCY RECONSTRUCTION OF SEWERS. THIS IS A 1 YEAR TIME AND MATERIALS CONTRACT . THE TARGETED START DATE FOR THIS CONTRACT IS ASSOON AS THE PREVIOUS CONTRACT EC-SEC23, EXPIRES. | 2022 | 24607 | 0 | 0 | 0 | 23750 | 0 | 0 | 0 | 23750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-WMC24 | Emergency Construction of Water Mains, Citywide | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 000 | WM-0001 WM-0006 EP-0007 |  |  | EMERGENCY CONSTRUCTION OF WATER MAINS, CITYWIDE. THIS IS A 1 YEAR TIME AND MATERIALS CONTRACT. THE TARGETED START DATE FOR THIS CONTRACT ISAS SOON AS THE PREVIOUS CONTRACT, EC-WMC23, EXPIRES. | 2022 | 13368 | 0 | 0 | 0 | 12350 | 0 | 0 | 0 | 12350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FADFLOOD | FAD - FLOOD HAZARD MITIGATION | FILTRATION AVOIDANCE DETERMINATION | 000 | WM-0030 |  |  | FAD - FLOOD HAZARD MITIGATION | 2022 | 15000 | 12000 | 0 | 11000 | 0 | 0 | 0 | 0 | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | FMC-LEAD | LEAD PAINT ABATEMENT & REMOVAL | FACILITY PURCHASES AND RECONSTRUCTION | 000 | EP-0006 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LEAD PAINT ABATEMENT & REMOVAL | 2022 | 1986 | 1783.39 | 3000 | 4442 | 1750 | 1500 | 0 | 0 | 12475.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CON-AS | GI - DPR ONSITE GREEN INFRASTRUCTURE ASPHALT | GREEN INFRASTRUCTURE PROGRAM | 000 | P-1018 |  |  | CONSTRUCT GREEN INFRASTRUCTURE RETROFITS ON PUBLIC PARKS ASPHALT REPLACEMENT. | 2022 | 6239 | 0 | 6239 | 0 | 0 | 0 | 0 | 0 | 6239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-1 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | GREEN INFRASTRUCTURE PROGRAM | 000 | WP-0169 |  |  | CONSTRUCT GREEN INFRASTRUCTURE RETROFITS ON PUBLIC PARKS, HOUSING DEVELOPMENTS OR SCHOOLS DESIGNED UNDER THE GI-P, GI-S AND GI-H CONTRACTS. | 2022 | 17000 | 0 | 17061 | 0 | 0 | 0 | 0 | 0 | 17061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CONS-2 | GI - GREEN INFRASTRUCTURE ONSITE CONSTRUCTION CONTRACTS | GREEN INFRASTRUCTURE PROGRAM | 000 | WP-0169 |  |  | CONSTRUCT GREEN INFRASTRUCTURE RETROFITS ON PUBLIC PARKS, HOUSING DEVELOPMENTS OR SCHOOLS DESIGNED UNDER THE GI-P, GI-S AND GI-H CONTRACTS. | 2022 | 14600 | 0 | 0 | 0 | 14600 | 0 | 0 | 0 | 14600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-GRANT | GI - GREEN INFRASTRUCTURE GRANT PROGRAM | GREEN INFRASTRUCTURE PROGRAM | 000 | WP-0169 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GREEN INFRASTRUCTURE GRANT PROGRAM | 2022 | 30000 | 11049.06 | 865 | 619 | 1823 | 3375 | 0 | 0 | 17731.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-HPD | GI - FUNDING FOR HPD GREEN INFRASTRUCTURE PROJECTS | GREEN INFRASTRUCTURE PROGRAM | 000 | WP-0169 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GI - FUNDING FOR HPD GREEN INFRASTRUCTURE PROJECTS | 2022 | 750 | 0 | 0 | 1000 | 0 | 500 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-POMISC | GI-MISCELLANEOUS CAPITAL PURCHASES FOR GREEN INFRASTRUCTURE | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0169 |  |  | GI-MISCELLANEOUS CAPITAL PURCHASES FOR GREEN INFRASTRUCTURE | 2022 | 0 | 0 | 0 | 450 | 1000 | 1000 | 0 | 0 | 2450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | HVR-500 | Hillview Police Precinct | WATER QUALITY PRESERVATION |  | WM-0030 |  |  | THIS PROJECT WILL CONSTRUCT A NEW BUILDING FOR THE DEP POLICE AT THE HILLVIEW RESERVOIR, TO SERVE AS A MORE PERMANENT SITE FOR THE DEP HILLVIEW POLICE PRECINCT. THIS NEW FACILITY IS CURRENTLY ESTIMATED TO BE APPROXIMATELY 11,000 SQUARE FEET OF BUILDING SPACE AND CONTAINS PROGRAMMABLE SPACE FOR ADMINISTRATIVE, INVESTIGATIVE, AND TRAINING PURPOSES. THE FACILITY WILL ALSO BE FULLY EQUIPPED WITH CLOSED-CIRCUIT TELEVISION MONITORING AND ACCESS CONTROL. SOME OF THE SPACES IN THE FACILITY INCLUDE, BUT ARE NOT LIMITED TO, A PRISONER PROCESSING AREA, A HAZARDOUSMATERIALS CLEAN-UP STATION, OFFICE SPACES FOR COMMANDING OFFICERS, A TRAINING ROOM, A CONFERENCE ROOM, LOCKER ROOMS AND LAVATORIES, A GENERAL STORAGE ROOM, AND AN ATTACHED GARAGE. | 2022 | 9000 | 0 | 5000 | 3100 | 14000 | 0 | 2000 | 0 | 24100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ID21-PUMP | REHABILITATION OF VARIOUS PUMP STATIONS DUE TO HURRICANE IDA | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0269 |  |  | REHABILITATION OF (16) PUMPING STATION LOCATIONS IMPACTED BY HURRICANE IDA DAMAGE | 2022 | 20000 | 0 | 1750 | 3250 | 0 | 0 | 0 | 0 | 5000 | 0 | 5250 | 9750 | 0 | 0 | 0 | 0 | 15000
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-12-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH, & EAST | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | VARIOUS LOCATIONS - CITY-WIDE | JOB ORDER CONTRACTING FOR PLUMBING WORK IN REGION SOUTH (NEWTOWN CREEK, NORTH RIVER, OAKWOOD BEACH, PORT RICHMOND, AND RED HOOK, | 2022 | 119798 | 65482.73 | 63 | 0 | 0 | 0 | 0 | 0 | 65545.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-15BWS | Facilities Improvement Program | WATER QUALITY PRESERVATION | 000 | WM-0030 WM-0011 WM-0105 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PROCUREMENT CONTRACT FOR JOB ORDER CONTRACTING-UPSTATE | 2022 | 44160 | 35785 | 22080 | 19543 | 2269 | 0 | 0 | 0 | 79677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-17-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | VARIOUS WPCPS IN VARIOUS REGIONS AND LOCATIONS CITY-WIDE | JOB ORDER CONTRACTING FOR SMALL TO MEDIUM SIZED PROJECTS IN GENERAL CONSTRUCTION/ PLUMBING/ HVAC AND ELECTRICAL WORK IN REGIONS NORTH, SOUTH AND EAST AT VARIOUS WASTEWATER TREATMANT PLANTS AND FACILITIES CITY-WIDE. | 2022 | 121700 | 146500.42 | 2754 | 0 | 0 | 0 | 0 | 0 | 149254.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-18-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | VARIOUS LOCATIONS CITY-WIDE | JOB ORDER CONTRACTING FOR GENERAL CONSTRUCTION/PLUMBING/HVAC / ELECTRICAL/SCADA AND FIRE ALARM SYSTEMS WORK IN VARIOUS REGIONS IN NORTH, SOUTH, AND EAST AT THE VARIOUS WASTEWATER TREATMENT PLANTS, CITY-WIDE | 2022 | 54800 | 69603.73 | 6720 | 4800 | 0 | 0 | 0 | 0 | 81123.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-20-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | JOB ORDER CONTRACTING FOR SMALL TO MEDIUM SIZED PROJECTS IN GENERAL CONSTRUCTION/ PLUMBING/ HVAC AND ELECTRICAL WORK IN REGIONS NORTH, SOUTH AND EAST AT VARIOUS WASTEWATER TREATMANT PLANTS AND FACILITIES CITY-WIDE. | 2022 | 34594 | 0 | 28800 | 0 | 0 | 0 | 0 | 0 | 28800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-22-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  |  | JOB ORDER CONTRACTING FOR SMALL TO MEDIUM SIZED PROJECTS IN GENERAL CONSTRUCTION/ PLUMBING/ HVAC AND ELECTRICAL WORK IN REGIONS NORTH, SOUTH AND EAST AT VARIOUS WASTEWATER TREATMANT PLANTS AND FACILITIES CITY-WIDE. | 2022 | 45280 | 0 | 85440 | 0 | 0 | 0 | 0 | 0 | 85440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-23-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  |  | JOB ORDER CONTRACTING FOR SMALL TO MEDIUM SIZED PROJECTS IN GENERAL CONSTRUCTION/ PLUMBING/ HVAC AND ELECTRICAL WORK IN REGIONS NORTH, SOUTH AND EAST AT VARIOUS WASTEWATER TREATMANT PLANTS AND FACILITIES CITY-WIDE. | 2022 | 30200 | 0 | 0 | 14400 | 0 | 0 | 0 | 0 | 14400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-24-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  |  | JOB ORDER CONTRACTING FOR SMALL TO MEDIUM SIZED PROJECTS IN GENERAL CONSTRUCTION/ PLUMBING/ HVAC AND ELECTRICAL WORK IN REGIONS NORTH, SOUTH AND EAST AT VARIOUS WASTEWATER TREATMANT PLANTS AND FACILITIES CITY-WIDE. | 2022 | 30080 | 0 | 0 | 0 | 14400 | 0 | 0 | 0 | 14400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-25-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  |  | JOB ORDER CONTRACTING FOR SMALL TO MEDIUM SIZED PROJECTS IN GENERAL CONSTRUCTION/ PLUMBING/ HVAC AND ELECTRICAL WORK IN REGIONS NORTH, SOUTH AND EAST AT VARIOUS WASTEWATER TREATMANT PLANTS AND FACILITIES CITY-WIDE. | 2022 | 45000 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-26-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  |  | JOB ORDER CONTRACTING FOR SMALL TO MEDIUM SIZED PROJECTS IN GENERAL CONSTRUCTION/ PLUMBING/ HVAC AND ELECTRICAL WORK IN REGIONS NORTH, SOUTH AND EAST AT VARIOUS WASTEWATER TREATMANT PLANTS AND FACILITIES CITY-WIDE. | 2022 | 115000 | 0 | 0 | 0 | 0 | 0 | 14400 | 0 | 14400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-27-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  |  | JOB ORDER CONTRACTING FOR SMALL TO MEDIUM SIZED PROJECTS IN GENERAL CONSTRUCTION/ PLUMBING/ HVAC AND ELECTRICAL WORK IN REGIONS NORTH, SOUTH AND EAST AT VARIOUS WASTEWATER TREATMANT PLANTS AND FACILITIES CITY-WIDE. | 2022 | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 14400 | 14400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-28-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  |  | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 2022 | 20160 | 0 | 0 | 0 | 0 | 0 | 0 | 34580 | 34580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-29-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  |  | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 2022 | 68160 | 0 | 0 | 0 | 0 | 0 | 0 | 43200 | 43200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-30-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  |  | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 2022 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-31-L | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  |  | JOB ORDER CONTRACTING WORK IN REGIONS NORTH, SOUTH & EAST | 2022 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWS | BWS JOC Contracts (E-O-H & W-O-H) | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BWS JOC CONTRACTS (E-O-H & W-O-H) | 2022 | 64000 | 0 | 0 | 0 | 0 | 6430 | 1500 | 31500 | 39430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-BWSO | BWSO Facilities Improvement Program | PLANT UPGRADING AND RECONSTRUCTION | 000 | WM-0105 |  |  | PROCUREMENT CONTRACT FOR JOB ORDER CONTRACTING - CITYWIDE FOR THE BUREAU OF WATER & SEWER OPERATIONS | 2022 | 51348 | 26188 | 1048 | 4768 | 8035 | 16320 | 0 | 0 | 56359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC3 | FMC Facilities Improvement Program | FACILITY PURCHASES AND RECONSTRUCTION |  | EP-0006 |  |  | FMC FACILITIES IMPROVEMENT PROGRAM | 2022 | 5720 | 4320 | 0 | 1480 | 0 | 0 | 0 | 0 | 5800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC4 | Job Order Contract 2 - CIitywide | FACILITY PURCHASES AND RECONSTRUCTION |  | EP-0006 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | JOB ORDER CONTRACT 2 - CITYWIDE | 2022 | 4760 | 2400 | 0 | 2360 | 0 | 0 | 0 | 0 | 4760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC6 | FMC Facilities Improvement Program | FACILITY PURCHASES AND RECONSTRUCTION |  | EP-0006 |  |  | FMC FACILITIES IMPROVEMENT PROGRAM | 2022 | 3600 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC7 | Job Order Contract 2 - Citywide | FACILITY PURCHASES AND RECONSTRUCTION |  | EP-0006 |  |  | JOB ORDER CONTRACT 2 - CITYWIDE | 2022 | 3600 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC8 | FMC Facilities Improvement Program | FACILITY PURCHASES AND RECONSTRUCTION |  | EP-0006 |  |  | FMC FACILITIES IMPROVEMENT PROGRAM | 2022 | 3600 | 0 | 0 | 0 | 2400 | 0 | 1200 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-FMC9 | Job Order Contract 2 - Citywide | FACILITY PURCHASES AND RECONSTRUCTION |  | EP-0006 |  |  | JOB ORDER CONTRACT 2 - CITYWIDE | 2022 | 3600 | 0 | 0 | 0 | 3600 | 0 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JOC-WSO20 | BWSO Facilities Improvement Program Citywide | PLANT UPGRADING AND RECONSTRUCTION | 000 | WM-0105 |  |  | PROCUREMENT CONTRACT FOR JOB CONTRACTSING - CITYWIDE FOR THE BUREAU OF WATER & SEWER OPERATIONS | 2022 | 10560 | 0 | 10560 | 0 | 0 | 0 | 0 | 0 | 10560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | JPSCOMPEH | JEROME PS ELECTRIC & HYDRAULIC SVC REPLAMNT | WATER QUALITY PRESERVATION |  | WM-0105 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | JEROME PS ELECTRIC & HYDRAULIC SVC REPLAMNT | 2022 | 5000 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | KENS-EAST | KENSICO-EASTVIEW CONNECTION TUNNEL | KENSICO-CITY TUNNEL | 000 | W-0014 |  |  | KENSICO-EASTVIEW CONNECTION TUNNEL | 2022 | 563000 | 113196.83 | 7328 | 6417 | 0 | 218098 | 595579 | 741000 | 1681618.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | LFK-RELO | Lefrak Relocation | FACILITY PURCHASES AND RECONSTRUCTION |  | EP-0006 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | LEFRAK RELOCATION INCLUDING OIT COST, LABS, PARKING AND ETC. | 2022 | 10500 | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MONIT-13 | FAD 13-17 Monitoring | FILTRATION AVOIDANCE DETERMINATION | 000 | WM-0030 |  |  | FAD 13-17 MONITORING | 2022 | 215 | 136.57 | 236 | 0 | 0 | 0 | 0 | 0 | 372.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MONIT-18 | FAD MONITORING | FILTRATION AVOIDANCE DETERMINATION | 000 | WM-0030 |  |  | FAD 18-22 MONITORING | 2022 | 839 | 0 | 0 | 103 | 187 | 250 | 299 | 0 | 839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-GRANT | GREEN INFRASTRUCTURE GRANT PROGRAM - MS4 PROJECTS | BLUEBELT PROGRAM | 000 | SE-0005 |  |  | GREEN INFRASTRUCTURE GRANT PROGRAM - MS4 PROJECTS TO MEET WATER QUALITY ATTAINMENT GOALS AND ALLEVIATE LOCALIZED FLOODING FROM STORMWATER RUNOFF | 2022 | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | MS4-STORM | MS4 CITYWIDE STORMWATER MANAGEMENT PROGRAM | WATER QUALITY MANDATES | 000 | SE-0005 |  |  | MS4 CITYWIDE STORMWATER MANAGEMENT PROGRAM | 2022 | 29378 | 9377.85 | 2100 | 1000 | 1000 | 1000 | 1206 | 0 | 15683.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | NYSDOTBRG | NYS DOT Bridges El Grant, Jesup, Nelson, Depot, Boston Road | WATER QUALITY PRESERVATION | 000 | WM-0006 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NYS DOT EL GRANT, JESUP AND NELSON AVENUE (PIN X806.56), DEPOT PLACE (PIN X720.39), AND BOSTON ROAD BRIDGE REHABILITATION. ADDITIONAL WATERMAINS ON THE BRIDGES OR UPGRADE OF EXISTING WATER MAINS ON THESE BRIDGES THAT WAS REQUESTED BY DEP BWSO DISTRIBUTION. | 2022 | 5000 | 1002.8 | 0 | 0 | 0 | 1948 | 0 | 3000 | 5950.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PJ-PLNT | RECONSTRUCTION OF PORT JERVIS WPCP, DEL | WATER QUALITY PRESERVATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | UPSTATE | RECONSTRUCTION OF THE PORT JERVIS WATER POLLUTION CONTROL PLANT | 2022 | 44140 | 16788.36 | 316 | 40000 | 0 | 0 | 0 | 0 | 57104.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PS179 | REHAB 179 ST PS/CONST MULTIPLE PS IN TOWER AREA | WATER QUALITY PRESERVATION |  | WM-0105 |  |  | REHAB 179 ST PS/CONST MULTIPLE PS IN TOWER AREA | 2022 | 12000 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | PW-117-L | INSTALLATION OF DISTRIBUTED CONTROL SYSTEMS @ VARIOUS WWTPS | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | VARIOUS LOCATIONS CITY-WIDE HUNTS WWTP, BOWERY BAY WWTP, AND PAERDEGAT BWQY | INSTALLATION OF VARIOUS HARDWARE AND SOFTWARE EQUIPMENT TO UPGRADE THE EXISTING DISTRIBUTED CONTROL SYSTEMS. THE SCOPE OF THE PROJECT IS TOUPGRADE THE VARIOUS CONTROL SYSTEMS HARDWARE AND SOFTWARE AT THE HUNTS POINT WWTP, BOWERY BAY WWTP, AND PAERDEGAT BWQF. | 2022 | 2650 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | QED1059 | Area Contract Install Dist WM through BX & QNS | AUGMENTATION OF WATER SUPPLY SYSTEMS | 000 | WM-0001 |  |  | AREA CONTRACT - TO INSTALL DISTRIBUTION WATER MAINS THROUGHOUT THE BRONX AND QUEENS AS DIRECTED BY THE DISTRIBUTION ENGINEER. | 2022 | 20183 | 0 | 0 | 0 | 17550 | 0 | 0 | 0 | 17550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RED394 | Area contract - Install Dist WM throughout BKLYN & SI | AUGMENTATION OF WATER SUPPLY SYSTEMS | 000 | WM-0001 |  |  | AREA CONTRACT FOR WATER MAIN REPLACEMENT. INSTALLATION OF DISTRIBUTION WATER MAINS THROUGHOUT BROOKLYN AND STATEN ISLAND AS DIRECTED BY DISTRIBUTION ENGINEER. | 2022 | 20183 | 0 | 0 | 0 | 17550 | 0 | 0 | 0 | 17550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RESAMSAF | DESIGN & CM FOR DAM SAFETY CONSTRUCTION | WATER QUALITY PRESERVATION | 000 | WM-0105 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DESIGN & CM FOR DAM SAFETY CONSTRUCTION | 2022 | 29000 | 10714.05 | 279 | 0 | 10000 | 0 | 0 | 56000 | 76993.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RIDGEPIPE | RIDGEWOOD RESERVOIR PIPE ABANDONMENT | WATER QUALITY PRESERVATION |  | WM-0105 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RIDGEWOOD RESERVOIR PIPE ABANDONMENT - FILLING IN OF ABANDONED UNDERGROUND RESERVOIR PIPES IN ORDER TO AVOID COLLAPSE AND DANGEROUS CONDITIONS | 2022 | 2000 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | RLCY-WWT | FLOODWATER RESILIENCY AT BWT FACILITES | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  |  | DESIGN AND CONSTRUCTION REQUIREMENTS CONTRACTS WHICH WILL FOCUS ON IMPLEMENTING THE WASTEWATER RESILIENCY PLAN AT VARIOUS WASTEWATER TREATMENT PLANT FACILITIES THROUGHOUT THE CITY. THE VARIOUS MEASURES WHICH HAVE BEEN IDENTIFIED AND ARE INTENDED TO BE THE FOCUS OF THE DESIGN WORK UNDER THIS CONTRACT ARE: PERMANENT BARRIERS, TEMPORARY, SEAL BUILDING, SANDBAGGING, FLOOD-PROOF EQUIPMENT, ELEVATE EQUIPMENT AND BACKUP POWER. | 2022 | 181000 | 263737.05 | 6966 | 18334 | 0 | 0 | 0 | 0 | 289037.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | ROWGI-A | GI - CITYWIDE CONSTRUCTION OF ROW GREEN INFRASTRUCTURE | GREEN INFRASTRUCTURE PROGRAM | 000 | WP-0169 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | GI - CITYWIDE CM SERVICES FOR RIGHT OF WAY GREEN INFRASTRUCTURE PROJECTS | 2022 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDHILLV | HILLVIEW RESERVOIR SECURITY FENCE IMPROVEMENTS | MANAGEMENT INFORMATION SYSTEMS | 000 | EP-0006 |  | HILLVIEW RESERVIOR AT YONKERS, NEW YORK | IMPROVEMENTS TO THE HILLVIEW RESERVOIR SECURITY FENCE AND INTRUSION ALERT SYSTEM AS A RESULT OF HURRICANE SANDY | 2022 | 574 | 229.15 | 119 | 10 | 0 | 0 | 0 | 0 | 358.15 | 0 | 486 | 90 | 0 | 0 | 0 | 0 | 576
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDPUMP | RECONS OF VARIOUS PUMPING STATIONS DUE TO HURRICANE SANDY | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0269 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECONSTRUCTION OF VARIOUS PUMPING STATIONS CITYWIDE DUE TO HURRICANE SANDY | 2022 | 12969 | 1552.25 | 0 | 220 | 300 | 0 | 300 | 107 | 2479.25 | 2464.08 | 0 | 1980 | 2700 | 0 | 2700 | 958 | 10802.08
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWM | RECONS OF WATER MAINS CITYWIDE DUE TO HURRICANE SANDY | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 000 | WM-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECONS OF WATER MAINS CITYWIDE DUE TO HURRICANE SANDY | 2022 | 3300 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 3000
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDWPCPS | RECONS OF WPCPS AND PUMPING STATIONS DUE TO HURRICANE SANDY | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 |  |  | RECONSTRUCTION OF CITYWIDE WATER POLLUTION CONTROL PLANTS AND PUMPINGSTATIONS DUE TO HURRICANE SANDY | 2022 | 111579 | 2988.46 | 2136 | 8475 | 8494 | 0 | 0 | 0 | 22093.46 | 13875.68 | 19166 | 76465 | 76446 | 0 | 0 | 0 | 185952.68
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | STMEOH-18 | FAD 18-22 STORMWATER MGMT. (EOH) | FILTRATION AVOIDANCE DETERMINATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FAD 18-22 STORMWATER MGMT. (EOH) | 2022 | 22500 | 22000 | 0 | 0 | 15000 | 493 | 0 | 0 | 37493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | STMWOH-18 | FAD 18-22 STORMWATER MGMT. (WOH) | FILTRATION AVOIDANCE DETERMINATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FAD 18-22 STORMWATER MGMT. (WOH) | 2022 | 14721 | 4720.86 | 0 | 0 | 10000 | 0 | 0 | 0 | 14720.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | STPUPG-18 | FAD 18-22 WWTP UPGRADE PROGRAM | FILTRATION AVOIDANCE DETERMINATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FAD 18-22 WWTP UPGRADE PROGRAM | 2022 | 26200 | 26200 | 20000 | 0 | 0 | 0 | 0 | 0 | 46200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | STREAM-13 | FAD 13-17 Stream Management | FILTRATION AVOIDANCE DETERMINATION | 000 | WM-0030 |  |  | FAD 13-17 STREAM MANAGEMENT | 2022 | 25395 | 17870.15 | 1822 | 0 | 0 | 0 | 0 | 0 | 19692.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | STREAM-18 | FAD 18-22 STREAM MANAGEMENT | FILTRATION AVOIDANCE DETERMINATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FAD 18-22 STREAM MANAGEMENT | 2022 | 52167 | 40094.64 | 0 | 0 | 7440 | 25000 | 0 | 2000 | 74534.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | TOSC1 | TASK ORDER SERVICES | AUGMENTATION OF WATER SUPPLY SYSTEMS | 000 | SE-0432 |  |  | TASK ORDER SERVICES CONTRACT FOR VARIOUS WATER AND SEWER PROJECTS | 2022 | 19884 | 4543.3 | 1038 | 5232 | 1673 | 1750 | 1750 | 8750 | 24736.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | UTIUTIL | UTILITY RELOCATION FOR SE AND WM PROJECTS | UTILITY RELOCATION FOR SE AND WM PROJECTS | 000 | EP-0007 | PROJECT DELAYED DUE TO SCHEDULING OF UTILITY WORK |  |  | 2022 | 502357 | 325612.76 | 0 | 0 | 0 | 0 | 0 | 151241 | 476853.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WCR-GRANT | Water Conservation and Reuse Grant Pilot Program | WATER FOR THE FUTURE | 000 | EP-0009 |  |  | UNDER THIS PROJECT, CAPITAL FUNDING WILL SUPPORT IMPLEMENTATION OF THE TOP-RANKED WATER CONSERVATION/REUSE PROJECTS. ALL APPLICATIONS ARE THOROUGHLY REVIEWED AND SCORED FOR THE GREATEST WATER SAVINGS, HIGHEST LEVEL OF COST EFFICIENCY, AND GREATEST ACHIEVABLE CO-BENEFITS. | 2022 | 5100 | 0 | 0 | 4000 | 9600 | 1409 | 0 | 0 | 15009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WEC-LGE16 | LARGE WATER METER PURCHASES, REPLACEMENTS AND INSTALLATIONS | CONSERVATION FOR WATER METER REPLACEMENTS | 000 | EP-0010 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PURCHASES AND INSTALLATION OF METERS AND RELATED AUTOMATIC METER READING (AMR) SYSTEM THROUGHOUT THE FIVE BOROUGHS. REPLACEMENT AND REPAIR OF LARGE WATER METERS EITHER BECAUSE THE METERS ARE NO LONGER FUNCTIONING OR BECAUSE THEIR AGE IS RESULTING IN UNDER REGISTRATION. | 2022 | 44983 | 24157.37 | 5000 | 874 | 500 | 2490 | 2000 | 7453 | 42474.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-HHC | HHC Fixture Replacement in City-owned Hospitals | WATER FOR THE FUTURE |  | EP-0009 |  |  | WATER DEMAND MANAGEMENT PROGRAM - MUNICIPAL WATER EFFICIENCY PROGRAM (MWEP): HHC FIXTURE REPLACEMENT IN CITY-OWNED HOSPITALS | 2022 | 6000 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-IGAS | WFF-INTER-GOV'T AGREEMENT | WATER FOR THE FUTURE | 000 | WM-0030 |  |  | TWO INTER-GOV'T AGREEMENTS TIED TO THE BYPASS TUNNEL PROJECT-WFF. THEAGREEMENTS ARE INTENDED TO PROVIDE AN ALTERNATE SOURCE OF WATER FOR COMMUNITIES WHO WILL BE IMPACTED BY THE CONSTRUCTION OF THE BYPASS TUNNEL. | 2022 | 23000 | 27226.12 | 1321 | 0 | 0 | 0 | 0 | 0 | 28547.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WFINSP-SP | CITYWIDE WATERFRONT INSPECTIONS AT VARIOUS WPCPS | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITYWIDE WATERFRONT INSPECTIONS AT VARIOUS WPCPS | 2022 | 22200 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WQMON-EN2 | ABOVE GROUND MONITORING STATIONS 2 | WATER QUALITY PRESERVATION | 000 | WM-0105 |  |  | CONSTRUCT ABOVE GROUND ONE ROOM STRUCTURE | 2022 | 2769 | 3097.92 | 189 | 0 | 0 | 0 | 0 | 0 | 3286.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WWMGT-13 | FAD 13-17 Community Wastewater Mgmt. | FILTRATION AVOIDANCE DETERMINATION | 000 | WM-0030 |  |  | FAD 13-17 COMMUNITY WASTEWATER MGMT. | 2022 | 29500 | 38100 | 5000 | 0 | 0 | 0 | 0 | 0 | 43100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 826 | DEPT ENVIRONMENTAL PROTECTION | WWMGT-18 | FAD 18-22 COMMUNITY WASTEWATER MGMT. | FILTRATION AVOIDANCE DETERMINATION | 000 | WM-0030 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FAD 18-22 COMMUNITY WASTEWATER MGMT. | 2022 | 30000 | 24000 | 0 | 24120 | 0 | 0 | 0 | 0 | 48120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-281D | Female Locker Rooms in the Bronx, Brooklyn, Queens, citywide | GARAGES AND FACILITIES | 000 | S-0136 |  |  | CONSTRUCTION OF FEMALE LOCKER ROOMS INCLUDING TOILETS, SINKS, SHOWERS, CHANGING ROOMS, AND LOCKERS/BENCHES WITHIN EXISTING BUT UNIMPROVED SPACE. | 2022 | 2081 | 4562.39 | 1367 | 0 | 0 | 0 | 0 | 0 | 5929.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366C | SI Compost Site | SOLID WASTE MANAGEMENT | 000 | S-0136 S-0129 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS |  | REHABILITATION, MITIGATION, AND DEVELOPMENT OF COMPOSTING FACILITIES CITYWIDE. | 2022 | 5801 | 22666.43 | 203 | 1955 | 0 | 0 | 0 | 0 | 24824.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366D | Construct/Reconstruct composting sites Citywide | SOLID WASTE MANAGEMENT | 000 | S-D136 S-K136 |  |  | CONSTRUCT/RECONSTRUCT COMPOSTING SITES CITYWIDE | 2022 | 15195 | 10685.07 | 205 | 0 | 0 | 0 | 0 | 0 | 10890.07 | 34.45 | 0 | 0 | 0 | 0 | 0 | 0 | 34.45
20220309 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-366F | Composting Citywide | SOLID WASTE MANAGEMENT | 000 | S-0136 |  |  | COMPOST SITE | 2022 | 0 | 0 | 742 | 1090 | 0 | 0 | 0 | 0 | 1832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S136-439 | DSNY FACILITY REHAB, CITYWIDE | GARAGES AND FACILITIES | 000 | S-0136 |  |  | REHABILITATION PROJECTS CITYWIDE | 2022 | 32800 | 0 | 0 | 0 | 0 | 21201 | 25000 | 128040 | 174241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 827 | DEPARTMENT OF SANITATION | S216-240 | DSNY PIER WORK RECONSTRUCTION CITYWIDE | WASTE DISPOSAL | 000 | S-0216 |  |  | ENGINEER'S ESTIMATE | 2022 | 39121 | 0 | 0 | 0 | 1356 | 3948 | 4070 | 22733 | 32107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BIKE2030 | BIKE NETWORK DEVELOPMENT 2030 | TRAFFIC WORK IN CONJUNCTION WITH HIGHWAY RECONSTRUCTION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BIKE NETWORK DEVELOPMENT 2030 | 2022 | 12340 | 0 | 0 | 0 | 0 | 0 | 0 | 1240 | 1240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BR10YR15 | Waterway Bridges Ten Year Plan | USEFUL LIFE EXTENSION | 000 | BR-0270 |  | WATERWAY BRIDGES TEN YEAR PLAN | WATERWAY BRIDGES TEN YEAR PLAN | 2022 | 175000 | 0 | 0 | 18747 | 35000 | 121642 | 35000 | 320247 | 530636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC156F | MANHATTAN BRIDGE #15 | EAST RIVER BRIDGES | 000 | BR-0156 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REHAB OF MANHATTAN BRIDGE | 2022 | 98600 | 49183.21 | 15542 | 0 | 0 | 0 | 0 | 0 | 64725.21 | 61983.88 | 0 | 0 | 0 | 0 | 0 | 0 | 61983.88
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC231F | QUEENSBORO BRIDGE #10 OVER EAST RIVER | EAST RIVER BRIDGES | 000 | BR-0231 TF-Q005 HW-D103 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REHAB OF QUEENSBORO BRIDGE | 2022 | 153800 | 348895.97 | 10553 | 5482 | 0 | 0 | 0 | 0 | 364930.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC253D | WILLIAMSBURG BRIDGE MISC REPAIRS AND PAINTING FY20 | EAST RIVER BRIDGES | 000 | BR-0253 HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WILLIAMSBURG BRIDGE MISC REPAIRS AND PAINTING FY20 | WILLIAMSBURG BRIDGE MISC REPAIRS AND PAINTING FY20 | 2022 | 414300 | 14677.56 | 74270 | 0 | 0 | 0 | 0 | 0 | 88947.56 | 0 | 118750 | 0 | 0 | 0 | 0 | 0 | 118750
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRC270D | BROOKLYN BRIDGE REHABILITATION OF APPOACH ARCHES FY19 | EAST RIVER BRIDGES | 000 | BR-0270 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BROOKLYN BRIDGE REHABILITATION OF APPOACH ARCHES FY19 | BROOKLYN BRIDGE REHABILITATION OF APPOACH ARCHES FY19 | 2022 | 300000 | 100612.84 | 31708 | 9465 | 0 | 0 | 0 | 0 | 141785.84 | 82550.35 | 129124 | 0 | 0 | 0 | 0 | 0 | 211674.35
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRCHAZMIG | HAZARD MITIGATION (EAST RIVER BRIDGES - CITYWIDE) | EAST RIVER BRIDGES | 000 | BR-0231 BR-0156 BR-0253 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HAZARD MITIGATION (EAST RIVER BRIDGES - CITYWIDE) | HAZARD MITIGATION (EAST RIVER BRIDGES - CITYWIDE) | 2022 | 107081 | 579605.43 | 0 | 44000 | 0 | 96876 | 0 | 0 | 720481.43 | 76431 | 0 | 0 | 0 | 0 | 0 | 0 | 76431
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRKA24039 | GRAND STREET/ NEWTON CREEK BIN: 2240390 | USEFUL LIFE EXTENSION | 000 | HB-1012 HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | GRAND STREET/ NEWTON CREEK BIN: 2240390 | GRAND STREET/ NEWTON CREEK BIN: 2240390 | 2022 | 138500 | 6992.49 | 0 | 6000 | 0 | 126884 | 0 | 0 | 139876.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BRX287S | MACOMBS DAM BRIDGE - REHAB OF FENDER SYSTEM & 155TH VIA | USEFUL LIFE EXTENSION | 000 | BR-0287 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MACOMBS DAM BRIDGE - SEISMIC RETROFIT | MACOMBS DAM BRIDGE - SEISMIC RETROFIT | 2022 | 45920 | 34147.14 | 321 | 0 | 0 | 0 | 0 | 0 | 34468.14 | 36780.2 | 0 | 0 | 587 | 0 | 0 | 0 | 37367.2
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | BUSLANSY3 | PURCHASE & INSTALL BUS LANE PHOTO ENFORCEMENT SYSTEM | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PURCHASE & INSTALL BUS LANE PHOTO ENFORCEMENT SYSTEM | 2022 | 12800 | 0 | 0 | 6400 | 6400 | 0 | 0 | 0 | 12800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5447 | MISCELLANEOUS UPGRADES TO FERRYBOATS | RECONSTRUCTION OF FERRY BOATS | 000 | FA-0313 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NA |  | 2022 | 7252 | 449.76 | 0 | 0 | 72 | 0 | 202 | 12265 | 12988.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5586 | REPLACEMENT OF COSGROVE FERRY BOAT | RECONSTRUCTION OF FERRY BOATS | 000 | FA-0313 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DESIGN AND CONS OF COSGROVE F/BOAT | 2022 | 5275 | 755.49 | 8050 | 0 | 0 | 0 | 0 | 4319 | 13124.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5589AUS | DRYDOCK AUSTEN CLASS FERRY BOATS | RECONSTRUCTION OF FERRY BOATS | 000 | FA-0313 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DRYDOCK AUSTEN FBOATS | 2022 | 3500 | 4059.39 | 203 | 0 | 1490 | 1029 | 0 | 0 | 6781.39 | 6312.29 | 0 | 0 | 0 | 0 | 0 | 0 | 6312.29
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | C5BARBERI | Drydocking and Reconstructtion of Barberi Class Ferryboats | RECONSTRUCTION OF FERRY BOATS | 000 | FA-0313 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DRYDOCK AND RECON OF FERRY VESSELS | 2022 | 11000 | 11837.04 | 0 | 2900 | 0 | 0 | 324 | 0 | 15061.04 | 12202.61 | 0 | 0 | 0 | 0 | 0 | 0 | 12202.61
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | CONG2030 | CONGESTED CORRIDORS/ GROWTH AREAS | TRAFFIC WORK IN CONJUNCTION WITH HIGHWAY RECONSTRUCTION | 000 | TF-0777 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CONGESTED CORRIDORS/ GROWTH AREAS | 2022 | 124790 | 942.58 | 0 | 0 | 0 | 0 | 0 | 10104 | 11046.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | DECKSCRPL | Deck Scows Replacement | FERRY MAINTENANCE FACILITY CONSTRUCTION | 000 | FA-0313 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SCOWS REPLACEMENT | 2022 | 3300 | 310.75 | 0 | 0 | 0 | 0 | 0 | 0 | 310.75 | 2796.78 | 0 | 0 | 0 | 0 | 173 | 0 | 2969.78
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FACLUMP | LUMP SUM FOR FACILITIES | BRIDGE FACILITIES | 000 | HW-0003 HB-1014 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CITYWIDE |  | 2022 | 66253 | 0 | 0 | 6959 | 0 | 1650 | 928 | 62284 | 71821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FARRSLIP | Arrestors for all slips | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 000 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | INSTALLATION OF ARRESTORS AT SLIPS | 2022 | 45137 | 947.16 | 0 | 0 | 0 | 1621 | 11555 | 45330 | 59453.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FATERMTBC | STG & WHT Ferry Terminals Transfer Bridge Control Update | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 000 | FA-0021 |  |  | ELECTRICAL UPGRADE AT TERMINALS TRANSFER BRIDGE | 2022 | 1600 | 142.51 | 0 | 57 | 1470 | 0 | 0 | 0 | 1669.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | FAVEHBARP | Vehicle Barrier Replacement Upgrade | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 000 | FA-0021 |  |  | BARRIER REPLACEMENT | 2022 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEAN2019 | STREET LIGHTING ANNUAL CONSTRUCTION 2019 | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 000 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | THIS CONTRACT IS FOR INSTALLING AND REMOVING EQUIPMENT FURNISHED BY THE CITY, OR BY THE CONTRACTOR, AND FOR PERFORMING OTHER ELECTRICAL WORK IN CONNECTION WITH STREET LIGHTING IN THE CITY OF NEW YORK. | 2022 | 8915 | 575 | 15 | 0 | 0 | 0 | 0 | 0 | 590 | 1449.78 | 4335 | 0 | 0 | 0 | 0 | 0 | 5784.78
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | GEHD2023 | Highways & Parks Distribution, citywide FY23 | REPLACEMENT OF ELECTRICAL DISTRIBUTION SYSTEMS | 000 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HIGHWAYS AND PARKS LIGHTING DISTRIBUTION SYSTEM | 2022 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1013EQ | SHOP EQUIPMENT FOR BRIDGES | BRIDGE VEHICLES | 000 | HB-1013 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SHOP EQUIPMENT FOR BRIDGES | SHOP EQUIPMENT FOR BRIDGES | 2022 | 1329 | 0 | 0 | 1329 | 0 | 0 | 0 | 0 | 1329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1014GP | WYTHE AVE. EXPLOSION PROOF CONTAINER | BRIDGE FACILITIES | 000 | HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BUILD-OUT COST FOR GREENPOINT YARD NEW TRAILERS | BUILD-OUT COST FOR GREENPOINT YARD NEW TRAILERS | 2022 | 847 | 261.77 | 126 | 0 | 0 | 0 | 0 | 0 | 387.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070BR | Protective Coating of Various Bridges in Brooklyn | Bridge Painting | 000 | HB-1070 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PROTECTIVE COATING OF VARIOUS BRIDGES IN BROOKLYN | PROTECTIVE COATING OF VARIOUS BRIDGES IN BROOKLYN | 2022 | 9600 | 0 | 0 | 9600 | 0 | 0 | 0 | 0 | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070BW | Protective Coating of Broadway Bridge over Harlem River | Bridge Painting | 000 | HB-1070 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PROTECTIVE COATING OF BROADWAY BRIDGE OVER HARLEM RIVER | PROTECTIVE COATING OF BROADWAY BRIDGE OVER HARLEM RIVER | 2022 | 28900 | 0 | 0 | 0 | 0 | 0 | 0 | 28900 | 28900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070BX | Protective Coating of Various Bridges in the Bronx | Bridge Painting | 000 | HB-1070 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PROTECTIVE COATING OF VARIOUS BRIDGES IN THE BRONX | PROTECTIVE COATING OF VARIOUS BRIDGES IN THE BRONX | 2022 | 12200 | 0 | 0 | 0 | 0 | 0 | 0 | 12200 | 12200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070EN | Protective Coating of LIRR and East New York Bridges | Bridge Painting | 000 | HB-1070 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PROTECTIVE COATING OF LIRR AND EAST NEW YORK BRIDGES | PROTECTIVE COATING OF LIRR AND EAST NEW YORK BRIDGES | 2022 | 13800 | 0 | 0 | 0 | 0 | 0 | 0 | 13800 | 13800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070LR | Protective Coating of LIRR Bay Ridge Bridges | Bridge Painting | 000 | HB-1070 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PROTECTIVE COATING OF LIRR BAY RIDGE BRIDGES | PROTECTIVE COATING OF LIRR BAY RIDGE BRIDGES | 2022 | 17950 | 0 | 0 | 0 | 0 | 0 | 0 | 17950 | 17950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070MD | Protective Coating of Macombs Dam Bridge | Bridge Painting | 000 | HB-1070 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PROTECTIVE COATING OF MACOMBS DAM BRIDGE | PROTECTIVE COATING OF MACOMBS DAM BRIDGE | 2022 | 42005 | 0 | 0 | 0 | 42005 | 0 | 0 | 0 | 42005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070MH | Protective Coating of Various Bridges in Manhattan | Bridge Painting | 000 | HB-1070 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PROTECTIVE COATING OF VARIOUS BRIDGES IN MANHATTAN | PROTECTIVE COATING OF VARIOUS BRIDGES IN MANHATTAN | 2022 | 11400 | 0 | 0 | 0 | 0 | 0 | 0 | 11400 | 11400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070RD | Protective Coating of Riverside Drive Bridge over W 125th St | Bridge Painting | 000 | HB-1070 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PROTECTIVE COATING OF RIVERSIDE DRIVE BRIDGE OVER W 125TH ST. (UNPAINTED PORTIONS OF THE BRIDGES) | PROTECTIVE COATING OF RIVERSIDE DRIVE BRIDGE OVER W 125TH ST. (UNPAINTED PORTIONS OF THE BRIDGES) | 2022 | 11800 | 0 | 0 | 0 | 11800 | 0 | 0 | 0 | 11800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070ST | PROTECTIVE COATING OF VARIOUS BRIDGES IN STATEN ISLAND | Bridge Painting | 000 | HB-1070 |  |  | PROTECTIVE COATING OF VARIOUS BRIDGES IN QUEENS & STATEN ISLAND | 2022 | 13650 | 11348.06 | 130 | 0 | 0 | 0 | 0 | 0 | 11478.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB1070WB | Williamsburg Bridge Painting | Bridge Painting | 000 | HB-1070 |  | WILLIAMSBURG BRIDGE PAINTING | WILLIAMSBURG BRIDGE PAINTING | 2022 | 58750 | 0 | 0 | 0 | 11500 | 0 | 17250 | 276000 | 304750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HB-BIDSAD | ADVERTISEMENT FOR CAPITAL BRIDGE PROJECTS | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CITYWIDE | ADVERTISEMENT FOR CAPITAL PROJECTS | 2022 | 1425 | 679.19 | 0 | 0 | 102 | 0 | 0 | 0 | 781.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBC1070 | BRIDGE PROTECTIVE COATING | Bridge Painting | 000 | HB-1070 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PAINTING FOR VARIOUS BRIDGES CITYWIDE | PAINTING AND PROTECTIVE TREATMENT FOR VARIOUS BRIDGES, FUNDING IS ALL | 2022 | 206749 | 0 | 0 | 0 | 9996 | 3100 | 2024 | 74650 | 89770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011A | IN-PROCESS FAB INSPECTION STRUCTURAL STEEL IN NE USA | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 |  | IN-PROCESS FAB INSPECTION STRUCTURAL STEEL IN NE USA | IN-PROCESS FAB INSPECTION STRUCTURAL STEEL IN NE USA | 2022 | 12383 | 3800 | 4800 | 3783 | 0 | 0 | 0 | 0 | 12383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US/CAN | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 |  | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US/CAN | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US/CAN | 2022 | 6756 | 3151.67 | 0 | 3604 | 0 | 0 | 0 | 0 | 6755.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0011C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN NE USA | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN NE USA | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN NE USA | 2022 | 3165 | 3526.14 | 0 | 270 | 0 | 0 | 0 | 0 | 3796.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD0012 | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 |  | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | 2022 | 10876 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD007P | Citywide Inspection/Monitoring of Bridge Paint Removal & App | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1070 |  | CITYWIDE INSPECTION/MONITORING OF BRIDGE PAINT REMOVAL & APP | CITYWIDE INSPECTION/MONITORING OF BRIDGE PAINT REMOVAL & APP | 2022 | 2711 | 0 | 0 | 0 | 2711 | 0 | 0 | 0 | 2711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD008P | Citywide Inspection/Monitoring of Bridge Paint Removal & App | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1070 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CITYWIDE INSPECTION/MONITORING OF BRIDGE PAINT REMOVAL AND APPLICATION | CITYWIDE INSPECTION/MONITORING OF BRIDGE PAINT REMOVAL & APP | 2022 | 3050 | 0 | 0 | 0 | 0 | 0 | 0 | 3050 | 3050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013 | Inspection Services at Concrete & Asphalt Plants | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | INSPECTION SERVICES AT CONCRETE & ASPHALT PLANTS | INSPECTION SERVICES AT CONCRETE & ASPHALT PLANTS | 2022 | 5200 | 0 | 0 | 3400 | 0 | 0 | 0 | 0 | 3400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE US | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 |  | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE US | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE US | 2022 | 12386 | 0 | 0 | 0 | 12386 | 0 | 0 | 0 | 12386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 |  | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US | 2022 | 6756 | 0 | 0 | 0 | 6756 | 0 | 0 | 0 | 6756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD013C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 |  | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | 2022 | 3165 | 0 | 0 | 0 | 3165 | 0 | 0 | 0 | 3165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD014 | Testing and Sampling of Material (Citywide) | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 |  | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | 2022 | 11301 | 0 | 0 | 0 | 0 | 11301 | 0 | 0 | 11301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015 | INSPECTION SERVICES AT CONCRETE & ASPHALT PLANTS | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | 2022 | 5400 | 0 | 0 | 0 | 0 | 0 | 5400 | 0 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015A | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE USA | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 |  | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE USA | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN NE USA | 2022 | 12383 | 0 | 0 | 0 | 0 | 0 | 0 | 12767 | 12767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015B | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US/CAN | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 |  | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US/CAN | IN-PROCESS FAB INSPECTION OF STRUCTURAL STEEL IN US/CAN | 2022 | 6756 | 0 | 0 | 0 | 0 | 0 | 0 | 6965 | 6965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD015C | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | IN-PROCESS FAB INSPECTION OF PP CONCRETE IN USA/CAN | 2022 | 3165 | 0 | 0 | 0 | 0 | 0 | 0 | 3263 | 3263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCD016 | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-1012 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | TESTING AND SAMPLING OF MATERIAL (CITYWIDE) | 2022 | 12802 | 0 | 0 | 0 | 0 | 0 | 0 | 12802 | 12802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCITYWIM | Citywide Wiegh-in-Motion System | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CITYWIDE WIEGH-IN-MOTION SYSTEM | CITYWIDE WIEGH-IN-MOTION SYSTEM | 2022 | 4500 | 0 | 450 | 0 | 2025 | 2025 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR03B | COMPONENT REHABILITATION 03B CONSTRUCTION | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMP REHAB 03B CONST | COMP REHAB 03B CONST | 2022 | 12120 | 3898.23 | 33769 | 0 | 0 | 0 | 0 | 0 | 37667.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR16 | COMPONENT REHAB OF BRIDGES CITYWIDE (8 BRIDGES) | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 |  | COMPONENT REHAB OF BRIDGES CITYWIDE (8 BRIDGES) | COMPONENT REHAB OF BRIDGES CITYWIDE (8 BRIDGES) | 2022 | 10724 | 8055.12 | 19555 | 0 | 0 | 0 | 0 | 0 | 27610.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR21A | COMPONENT REHAB OF BRIDGES 21A | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CONVERSION DATA- DESCRIPTION REQUIRED | COMPONENT REHAB OF BRIDGES 21A | 2022 | 21550 | 3139.17 | 22660 | 0 | 0 | 0 | 0 | 0 | 25799.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR21B | COMPONENT REHAB OF BRIDGES 21B | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | P-1018 HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPONENT REHAB OF BRIDGES 21B | COMPONENT REHAB OF BRIDGES 21B | 2022 | 19234 | 2203.07 | 23769 | 0 | 0 | 0 | 0 | 0 | 25972.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR22A | COMPONENT REHAB OF BRIDGES 22A | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPONENT REHAB | COMPONENT REHAB OF BRIDGES | 2022 | 21695 | 2370.24 | 0 | 0 | 21091 | 0 | 0 | 0 | 23461.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR22B | COMPONENT REHAB OF BRIDGES 22B | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPONENT REHAB OF BRIDGES 22B | COMPONENT REHAB OF BRIDGES 22B | 2022 | 19530 | 2315.3 | 0 | 0 | 24206 | 0 | 0 | 0 | 26521.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23A | COMPONENT REHAB OF BRIDGES 23A | FINANCING COSTS | 000 | HB-0215 |  |  | COMPONENT REHAB OF BRIDGES 23A | 2022 | 22345 | 2132.55 | 418 | 0 | 22639 | 0 | 0 | 0 | 25189.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR23B | COMPONENT REHAB OF BRIDGES 23B | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | COMPONENT REHAB OF BRIDGES 23B | 2022 | 22345 | 1860.89 | 0 | 0 | 20435 | 0 | 0 | 0 | 22295.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR24A | COMPONENT REHAB OF BRIDGES 24A | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPONENT REHAB OF BRIDGES 24A | COMPONENT REHAB OF BRIDGES 24A | 2022 | 23020 | 0 | 0 | 1970 | 0 | 0 | 21050 | 0 | 23020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR24B | COMPONENT REHAB OF BRIDGES 24B | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPONENT REHAB OF BRIDGES 24B | COMPONENT REHAB OF BRIDGES 24B | 2022 | 20725 | 0 | 0 | 1970 | 0 | 18755 | 0 | 0 | 20725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR25A | COMPONENT REHAB OF BRIDGES 25A | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPONENT REHAB OF BRIDGES 25A | COMPONENT REHAB OF BRIDGES 25A | 2022 | 23715 | 0 | 0 | 0 | 2030 | 0 | 0 | 21685 | 23715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR25B | COMPONENT REHAB OF BRIDGES 25B | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPONENT REHAB OF BRIDGES 25B | COMPONENT REHAB OF BRIDGES 25B | 2022 | 21350 | 0 | 0 | 0 | 2030 | 0 | 0 | 19320 | 21350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR26A | COMPONENT REHAB OF BRIDGES 26A | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPONENT REHAB OF BRIDGES 26A | COMPONENT REHAB OF BRIDGES 26A | 2022 | 24430 | 0 | 0 | 0 | 0 | 2090 | 0 | 22340 | 24430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR26B | COMPONENT REHAB OF BRIDGES 26B | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPONENT REHAB OF BRIDGES 26B | COMPONENT REHAB OF BRIDGES 26B | 2022 | 21995 | 0 | 0 | 0 | 0 | 2090 | 0 | 19905 | 21995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR27A | COMPONENT REHAB OF BRIDGES 27A | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPONENT REHAB OF BRIDGES 27A | COMPONENT REHAB OF BRIDGES 27A | 2022 | 25175 | 0 | 0 | 0 | 0 | 0 | 0 | 25175 | 25175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBCR27B | COMPONENT REHAB OF BRIDGES 27B | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPONENT REHAB OF BRIDGES 27B | COMPONENT REHAB OF BRIDGES 27B | 2022 | 22665 | 0 | 0 | 0 | 0 | 0 | 0 | 22665 | 22665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBKBQE | Rehabilitation of BQE (I-278) from Sands St. to Atlantic Ave | FAIR BRIDGES | 000 | HB-0278 HB-1012 P-0508 |  | 21 BINS: 2268497; 2268498;2268507;2268508;2268517;2268518;2268350;2230410;2230420; 2230430; 2230440;2230450;2230460;2230470;2230480;2230490;2230857;2230858;2230870;2230887;2230888 | 21 BINS: 2268497; 2268498;2268507;2268508;2268517;2268518;2268350;2230410;2230420; 2230430; 2230440;2230450;2230460;2230470;2230480;2230490;2230857;2230858;2230870;2230887;2230888 | 2022 | 1901292 | 206070.88 | 31389 | 33810 | 53800 | 0 | 92605 | 779587 | 1197261.88 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBKBQE4C | Rehabilitation of BQE (I-278) Four Crossings | FAIR BRIDGES | 000 | HB-0278 |  | REHABILITATION OF BQE (I-278) FOUR CROSSINGS | REHABILITATION OF BQE (I-278) FOUR CROSSINGS | 2022 | 181260 | 0 | 300 | 151260 | 0 | 0 | 0 | 0 | 151560 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 30000
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBKBQECH | Rehabilitation of BQE (I-278) Columbia Heights | FAIR BRIDGES | 000 | HB-0278 P-0508 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | REHABILITATION OF BQE (I-278) COLUMBIA HEIGHTS | REHABILITATION OF BQE (I-278) COLUMBIA HEIGHTS | 2022 | 155000 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBKBQEPRE | Preservation of BQE (I-278) from Sands St. to Atlantic Ave | FAIR BRIDGES | 000 | HB-0278 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PRESERVATION OF BQE (I-278) FROM SANDS ST. TO ATLANTIC AVE | PRESERVATION OF BQE (I-278) FROM SANDS ST. TO ATLANTIC AVE | 2022 | 492000 | 0 | 0 | 0 | 0 | 492000 | 0 | 0 | 492000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBM24064 | Fender System for Roosevelt Island Bridge over East River | FAIR BRIDGES | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | FENDER SYSTEM FOR ROOSEVELT ISLAND BRIDGE OVER THE EAST RIVER | FENDER SYSTEM FOR ROOSEVELT ISLAND BRIDGE OVER THE EAST RIVER | 2022 | 34126 | 0 | 0 | 2625 | 3938 | 27563 | 0 | 0 | 34126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBR10COMP | TEN YR COMP | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2022 | 43020 | 0 | 0 | 0 | 0 | 11922 | 50000 | 196277 | 258199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBREP6919 | Emergency Contract for 181st (Washington Bridge) over Harlem | FAIR BRIDGES | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | EMERGENCY CONTRACT FOR 181ST (WASHINGTON BRIDGE) OVER HARLEM RIVER | EMERGENCY CONTRACT FOR 181ST (WASHINGTON BRIDGE) OVER HARLEM RIVER | 2022 | 25918 | 24254.53 | 4593 | 0 | 0 | 0 | 0 | 0 | 28847.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HBX1670 | EAST 169TH STREET OVER METRO NORTH RR BIN: 2241670 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0167 TF-0002 TF-0502 |  |  | EAST 169TH STREET OVER METRO NORTH RR ÝBIN: 2241670 | 2022 | 7265 | 7955.65 | 2522 | 927 | 0 | 0 | 0 | 0 | 11404.65 | 0 | 381 | 0 | 0 | 0 | 0 | 0 | 381
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA1 | In-House Pedestrian Ramp Rehabilitation - Crews | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | IN-HOUSE PEDESTRIAN RAMP REHABILITATION - CREWS | IN-HOUSE PEDESTRIAN RAMP REHABILITATION - CREWS | 2022 | 19402 | 61265.43 | 24483 | 28588 | 33569 | 40234 | 40242 | 302302 | 530683.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW200IFA2 | In-House Pedestrian Ramp Rehabilitation - OTPS | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | IN-HOUSE PEDESTRIAN RAMP REHABILITATION - OTPS | IN-HOUSE PEDESTRIAN RAMP REHABILITATION - OTPS | 2022 | 24888 | 30870.76 | 14317 | 15587 | 6535 | 6535 | 6535 | 40852 | 121231.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR06 | CITYWIDE MILLING | PRIMARY STREET RESURFACING | 099 | HW-0002M HW-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | N/A |  | 2022 | 125195 | 0 | 0 | 71294 | 71728 | 73777 | 75946 | 412859 | 705604 | 0 | 0 | 15581 | 0 | 0 | 0 | 0 | 15581
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR19F | Citywide Milling - Brooklyn and Queens | PRIMARY STREET RESURFACING | 000 | HW-0002K HW-0002Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITYWIDE MILLING- BROOKLYN AND QUEENS | 2022 | 2529 | 12305.69 | 7815 | 0 | 0 | 0 | 0 | 0 | 20120.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21C | Citywide Milling - Brooklyn and Staten Island | PRIMARY STREET RESURFACING | 000 | HW-0002K HW-0002R | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITYWIDE MILLING - BROOKLYN AND STATEN ISLAND | 2022 | 2043 | 0 | 2043 | 0 | 0 | 0 | 0 | 0 | 2043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21E | Citywide Milling - BK, QN, and SI | PRIMARY STREET RESURFACING | 000 | HW-0002K HW-0002Q HW-0002R | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITYWIDE MILLING - BK, QN, AND SI | 2022 | 1572 | 0 | 1572 | 0 | 0 | 0 | 0 | 0 | 1572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HW34907 | IN-HOUSE RESURFACING - CREWS&OTHER NON-ASPHALT OTPS | PRIMARY STREET RESURFACING | 099 | HW-0349 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2022 | 891282 | 1453867.2 | 174334 | 129562 | 133670 | 137746 | 141915 | 783248 | 2954342.2 | 83493.27 | 0 | 0 | 0 | 0 | 0 | 0 | 83493.27
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC349M03 | MANHOLE RINGS | PRIMARY STREET RESURFACING | 000 | HW-0349 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2022 | 8370 | 646.99 | 468 | 500 | 517 | 534 | 551 | 3074 | 6290.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCFTRLR | Citywide Trailer Rehabilitation | FACILITY RECONSTRUCTION | 000 | HB-1014 HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITYWIDE TRAILER REHABILITATION | 2022 | 3169 | 2331.96 | 1756 | 836 | 0 | 0 | 1200 | 0 | 6123.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWC-HDBP | High-Density Bike Parking | PRIMARY STREET RECONSTRUCTION | 000 | HW-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HIGH-DENSITY BIKE PARKING | HIGH-DENSITY BIKE PARKING | 2022 | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 2800 | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCPDLOC2 | Perimeter Security Measures 2 | PRIMARY STREET RECONSTRUCTION | 000 | HW-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PERIMETER SECURITY MEASURES 2 | PERIMETER SECURITY MEASURES 2 | 2022 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 592 | 592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCURB10 | Curb Reconstruction | SIDEWALK RECONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CURB RECONSTRUCTION | 2022 | 2058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCWREC | CITYWIDE RECONSTRUCTION OF STREETS | PRIMARY STREET RECONSTRUCTION | 099 | HW-0001Q HW-0001K HW-0001 TF-0002 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NA |  | 2022 | 546260 | 0 | 12307 | 0 | 0 | 5000 | 0 | 33750 | 51057 | 0 | 0 | 0 | 0 | 0 | 0 | 5434 | 5434
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWCW-SOGR | Citywide Streets - 30-Year State of Good Repair | PRIMARY STREET RECONSTRUCTION |  | HW-0001 HW-1684 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CITYWIDE | FY13 JAN PLAN SUPPLEMENTAL REQUEST - CITYWIDE RECONSTRUCTION OF PRIMARY STREETS TO A STATE OF GOOD REPAIR ON A 30-YEAR CYCLE | 2022 | 49250 | 0 | 0 | 0 | 0 | 0 | 0 | 127169 | 127169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWMMPEDSW | MULTI-MODAL #2 - 2000 PED RAMPS AND SIDEWALK | SIDEWALK RECONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MULTI-MODAL #2 - 2000 PED RAMPS AND SIDEWALK | MULTI-MODAL #2 - 2000 PED RAMPS AND SIDEWALK | 2022 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 260
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP19MKLM | COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BROOKLYN | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BROOKLYN | COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BROOKLYN | 2022 | 5901 | 0 | 0 | 0 | 5901 | 0 | 0 | 0 | 5901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWP19MXLM | COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | CITYWIDE COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | 2022 | 3139 | 0 | 0 | 0 | 3139 | 0 | 0 | 0 | 3139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRAPS | Pedestrian Ramps - Required APS add on | PEDESTRIAN RAMP CONSTRUCTION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PEDESTRIAN RAMPS - REQUIRED APS ADD ON | PEDESTRIAN RAMPS - REQUIRED APS ADD ON | 2022 | 79680 | 0 | 0 | 7080 | 18990 | 11910 | 0 | 0 | 37980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPDRTREE | Pedestrian Ramps - Tree Replacement | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PEDESTRIAN RAMPS - TREE REPLACEMENT | PEDESTRIAN RAMPS - TREE REPLACEMENT | 2022 | 3199 | 0 | 0 | 0 | 1566 | 0 | 0 | 0 | 1566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMLM | REPACKAGED COMPLEX PED RAMP INSTALL LANDMARK | PEDESTRIAN RAMP CONSTRUCTION |  | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX PED RAMP INSTALLS | REPACKED CORNERS | 2022 | 3635 | 0 | 0 | 0 | 5345 | 0 | 0 | 0 | 5345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMMX | Repacked Complex Ped Ramps Installs - Manhattan & Bronx | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPACKED CORNERS | 2022 | 5268 | 0 | 0 | 0 | 1709 | 0 | 0 | 0 | 1709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMQR | Repacked Complex Ped Ramp Installs - Queens, Mnhn, & SI | PEDESTRIAN RAMP CONSTRUCTION |  | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX PED RAMP INSTALLS - QUEENS, MANHATTAN, & BRONX | REPACKED CORNERS | 2022 | 4853 | 0 | 0 | 0 | 4073 | 0 | 0 | 0 | 4073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPELIMTA | Repacked Complex Ped Ramps (TA) | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX PED RAMP INSTALLS (TA) | REPACKED CORNERS | 2022 | 6612 | 0 | 0 | 0 | 4583 | 0 | 0 | 0 | 4583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPL20006 | PRIOR NOTICE SIDEWALK(SIM) | SIDEWALK RECONSTRUCTION | 000 | P-1018 P-1331 HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2022 | 180000 | 0 | -5143 | 15582 | 29304 | 51108 | 33407 | 265502 | 389760 | 0 | 0 | 6668 | 6668 | 13336 | 6668 | 33340 | 66680
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ015Q | Ozone Park Plaza | PRIMARY STREET RECONSTRUCTION | 000 | HW-1684 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | OZONE PARK PLAZA | OZONE PARK PLAZA | 2022 | 3000 | 0 | 0 | 0 | 0 | 8717 | 0 | 0 | 8717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRINSTL | Pedestrian Ramps Installation - Lump Sum | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PEDESTRIAN RAMPS INSTALLATION - LUMP SUM | PEDESTRIAN RAMPS INSTALLATION - LUMP SUM | 2022 | 40000 | 0 | 0 | 0 | 13290 | 119982 | 144821 | 139179 | 417272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWPRREHAB | Pedestrian Ramps Rehabilitation - Lump Sum | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PEDESTRIAN RAMPS REHABILITATION | PEDESTRIAN RAMPS REHABILITATION - LUMP SUM | 2022 | 75074 | 0 | -9565 | 0 | 12817 | 114284 | 178349 | 903686 | 1199571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWRAP07 | RAP HAULING | PRIMARY STREET RESURFACING | 000 | HW-0349 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RAP HAULING | RAP HAULING | 2022 | 74651 | 82218.14 | 6552 | 5023 | 6905 | 7132 | 7353 | 41045 | 156228.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWSAFTR | Safe Routes to Transit | PRIMARY STREET RECONSTRUCTION | 000 | HW-0988 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SAFE ROUTES TO TRANSIT | 2022 | 16058 | 0 | 0 | 0 | 0 | 0 | 0 | 14382 | 14382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWSTEP04 | STEP STREET REHABILITATION | RECONSTRUCTION OF STEP STREETS | 000 | HW-0211 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CITYWIDE | STEP STREET REHABILITATION CITYWIDE | 2022 | 10100 | 0 | 0 | 0 | 0 | 0 | 0 | 1122 | 1122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | HWTSQI | Public Plaza Improvements | PRIMARY STREET RECONSTRUCTION | 000 | HW-1684 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | TOWN SQUARE INITIATIVE | 2022 | 133970 | 0 | 0 | 0 | 0 | 0 | 0 | 53782 | 53782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | ITSBELTPK | Intelligent Transportation Systems on Belt Parkway X501.62 | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NYCDOT'S TRAFFIC MANAGEMENT CENTER HAS LIMITATIONS TO PROVIDING DAILYTRAFFIC INCIDENT REPORTS ALONG THE BELT PARKWAY. THIS ITS PROJECT AIMS AT DEPLOYING ITS SYSTEM TO PROVIDE REAL-TIME INFORMATION AND DISSEMINATE TRAFFIC ADVISORY INFORMATION TO THE MOTORIST OF RECURRING, NON-RECURRING EVENTS AND TRAVEL TIME. | 2022 | 4925 | 682.25 | 46 | 31 | 0 | 0 | 0 | 226 | 985.25 | 2729.02 | 181 | 128 | 0 | 0 | 0 | 902 | 3940.02
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | ITSJACKPK | Intelligent Transportation Syston Jackie Robinson Pk X501.60 | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | THIS JRP PROJECT AIMS TO IMPLEMENT AN ITS SYSTEM CONSISTING OF TRAFFIC SURVEILLANCE CAMERAS AND VEHICLE DETECTION EQUIPMENT VARIABLE MESSAGE SIGNS, TRAVEL TIME SIGN, AUTOMATIC VEHICLE IDENTIFICATION DETECTORS,AND COMMUNICATION EQUIPMENT ALONG THE JACKIE ROBINSON PARKWAY FROM GCP/WHITESTONE EXPRESSWAY IN QUEENS TO BUSHWICK AVENUE IN BROOKLYN. | 2022 | 3009 | 0 | 0 | 528 | 74 | 0 | 0 | 0 | 602 | 0 | 0 | 2111 | 0 | 0 | 0 | 0 | 2111
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | MOLRETROF | MOLINARI CLASS UPGRADES-RETRO FIT | RECONSTRUCTION OF FERRY BOATS | 000 | FA-0313 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MOLINARI CLASS UPGRADES-RETRO FIT | MOLINARI CLASS UPGRADES-RETRO FIT | 2022 | 11030 | 836.7 | 1741 | 1864 | 4000 | 0 | 3000 | 0 | 11441.7 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 1200
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | NYCWINRPL | NYCWIN Replacement | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NYCWIN REPLACEMENT | 2022 | 75000 | 71010.51 | 0 | 0 | 0 | 0 | 0 | 3990 | 75000.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | PLANTRANS | TRANSIT SIGNAL PRIORITY-2030 | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | TRANSIT SIGNAL PRIORITY-2030 | TRANSIT SIGNAL RIORITY-2030 | 2022 | 9246 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 300 | 1222.03 | 0 | 0 | 0 | 0 | 0 | 0 | 1222.03
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | RTPIFY19 | REAL TIME PASSENGER INFO SIGNS - FY19 | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-K001 TF-D005 TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FUNDING FOR FURNISH AND INSTALLATION OF REAL TIME PASSENGER INFORMATION SIGNS CITYWIDE FY19 | 2022 | 7441 | 9100.98 | -206 | 0 | 0 | 0 | 0 | 1615 | 10509.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | RTPIFY20 | Real Time Passenger Info Signs FY20ADOP | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-K001 TF-D005 TF-X001 TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FURNISH AND INSTALL RTPI AT VARIOUS LOCATIONS | 2022 | 2760 | 0 | 2337 | 2060 | 1996 | 0 | 0 | 0 | 6393 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 250
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDCONDU | SANDY CONDUIT ADDITIONAL CITY-WIDE WORK | FACILITY RECONSTRUCTION | 000 | HW-0003 TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SANDY CONDUIT ADDITIONAL CITY-WIDE WORK | 2022 | 29731 | 40 | 0 | 223 | 0 | 0 | 0 | 0 | 263 | 0 | 0 | 1892 | 5295 | 0 | 0 | 0 | 7187
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDHB002 | Rehab of Movable Bridges Citywide - Sandy | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 000 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | TO REPAIR VARIOUS MOVABLE BRIDGES DAMAGED DUE TO HURRICANE SANDY, CITYWIDE. | 2022 | 35654 | 24828.96 | 0 | 0 | 0 | 0 | 0 | 0 | 24828.96 | 77333.37 | 0 | 8816 | 0 | 0 | 0 | 0 | 86149.37
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF05 | Construction of New Ferryboats | RECONSTRUCTION OF FERRY BOATS | 000 | FA-0313 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CONSTRUCTION OF 3 NEW FERRYBOATS | 2022 | 340000 | 52136.86 | 0 | 0 | 0 | 0 | 0 | 48453 | 100589.86 | 184050.58 | 16030 | 0 | 0 | 45684 | 0 | 0 | 245764.58
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF07 | STATEN ISLAND FERRY HEAVY WEATHER MOORING | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 000 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SEVERE WEATHER MOORING UPGRADE | SEVERE WEATHER MOORING UPGRADE | 2022 | 2844 | 172.26 | 750 | 500 | 2596 | 42 | 0 | 0 | 4060.26 | 380.39 | 0 | 0 | 15342 | 0 | 0 | 0 | 15722.39
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF11 | Ferry Terminal Floodproofing | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 000 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MEASURES TO MITIGATE STORM SURGE IMPACT AT SIF FACILITIES | 2022 | 25355 | 20 | 707 | 7197 | 0 | 0 | 0 | 0 | 7924 | 0 | 1029 | 22328 | 0 | 0 | 0 | 0 | 23357
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SEQUEENS | South East Queens Initiative | PRIMARY STREET RECONSTRUCTION | 000 | HW-0001Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SOUTH EAST QUEENS INITIATIVE | SOUTH EAST QUEENS INITIATIVE | 2022 | 100505 | 0 | 0 | 0 | 0 | 0 | 0 | 47119 | 47119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SIGNALSF2 | TRAFFIC SIGNAL SAFETY, CITYWIDE | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | TRAFFIC SIGNAL SAFETY, CITYWIDE | TRAFFIC SIGNAL SAFETY, CITYWIDE | 2022 | 70000 | 29776.84 | 1624 | 0 | 0 | 0 | 0 | 0 | 31400.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | SIGNALSF3 | Traffic Signals Safety, Citywide | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FURNISH AND INSTALL SIGNALS, CITYWIDE | 2022 | 30555 | 0 | 5000 | 12555 | 13000 | 0 | 0 | 0 | 30555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | STEFFSCMV | NYC Street Efficiency Strategic Commercial Vehicle Monitorin | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CVM | 2022 | 2441 | 0 | 0 | 332 | 919 | 0 | 1190 | 0 | 2441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF012013 | NEW SIGNAL INSTALLATION REQUIREMENT CONTRACT FY13 | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | INSTALLATION OF NEW SIGNALS | 2022 | 15500 | 4475.09 | 0 | 0 | 0 | 0 | 0 | 0 | 4475.09 | 12485.08 | 0 | 0 | 0 | 1499 | 0 | 0 | 13984.08
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF012014 | NEW SIGNALS INSTALLATION REQUIREMENT | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NEW SIGNAL INSTALLATION REQUIREMENT | NEW SIGNAL INSTALLATION REQUIREMENT | 2022 | 16600 | 8075.24 | 0 | 0 | 0 | 0 | 0 | 0 | 8075.24 | 15182.75 | 0 | 0 | 0 | 289 | 0 | 0 | 15471.75
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF012019 | NEW SIGNALS INSTALLATION REQUIREMENT 2019 | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | THIS CONTRACT IS FOR THE FURNISHING, INSTALLATION AND REMOVAL OF ELECTRICAL TRAFFIC SIGNAL EQUIPMENT TO CONTROL TRAFFIC IN THE FIVE BOROUGHS OF THE CITY OF NEW YORK. THE WORK WILL BE ISSUED TO THE CONTRACTOR. | 2022 | 32426 | 17369.17 | 4468 | 903 | 0 | 0 | 0 | 0 | 22740.17 | 10593.76 | 7223 | 2688 | 0 | 0 | 0 | 0 | 20504.76
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF012023 | New Signals Installation requirement, citywide FY23 | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NEW SIGNALS INSTALLATION | 2022 | 35020 | 0 | 0 | 14520 | 0 | 0 | 0 | 0 | 14520 | 0 | 0 | 20500 | 0 | 0 | 0 | 0 | 20500
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01-9910 | LOCAL STREET NETWORK MGMT AND INCIDENT MGMT X500.94 | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | LOCAL STREET NETWORK MGMT AND INCIDENT MGMT | LOCAL STREET NETWORK MGMT AND INCIDENT MGMT | 2022 | 4346 | 2335.5 | 0 | 0 | 350 | 1388 | 0 | 0 | 4073.5 | 3228.33 | 0 | 0 | 0 | 0 | 0 | 0 | 3228.33
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01-9911 | Advance Travel Information System Upgrade | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | UPGRADE OF EZPASS REVENUE SYSTEM | 2022 | 500 | 0 | 80 | 210 | 210 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01APS | Accessible Pedestrian Signals, citywide - TEN YEARS | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | APS (AT 75 LOCATIONS PER YEAR ) | APS (AT 75 LOCATIONS PER YEAR ) | 2022 | 15200 | 0 | 0 | 40386 | 28269 | 51802 | 65180 | 108902 | 294539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01TPM21 | Thermoplastic Marking-FY21 | INSTALLATION OF PAVEMENT MARKINGS | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECONSTRUCTION | 2022 | 19000 | 4000 | 7517 | 0 | 0 | 0 | 3483 | 4000 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF01VARMS | Variable Message Signs Replacement, Citywide | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | VARIABLE MESSAGE SIGNS REPLACEMENT , CITYWIDE | 2022 | 4586 | 198.51 | 1319 | 943 | 1017 | 4230 | 0 | 0 | 7707.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TF18-LUMP | LUMP SUM FOR PARKING RECONSTRUCTION | Parking Meters, Lots, and Garages | 000 | TF-0018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CITY-WIDE | LUMP SUM FOR PARKING RECONSTRUCTION | 2022 | 1405 | 0 | 0 | 0 | 0 | 0 | 0 | 5745 | 5745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFAPEDSY3 | Accessible Pedestrian Signals-Retrofit | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FURNISH AND INSTALL APS | 2022 | 10098 | 17744.38 | 0 | 0 | 0 | 0 | 1081 | 0 | 18825.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFCORRBAS | Replacement of Corroded Street light and Signal Poles | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REPLACEMENT OF CORRODED STREET LIGHT AND SIGNAL POLES | 2022 | 6116 | 0 | 4583 | 0 | 0 | 0 | 0 | 831 | 5414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFCWSBST | SBS-Citywide Real Time Totem System | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PURCHASE AND INSTALLATION OF TOTEM SIGNS CITYWIDE ON SBS ROUTES | 2022 | 3557 | 1684.61 | 0 | 0 | 0 | 1872 | 0 | 0 | 3556.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFITSAMS | INTELLIGENT TRANSPORTATION SYSTEM(ITS) ON HIGHWAYS | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | ITS AND AMS INSTALLATION | ITS AND AMS INSTALLATION | 2022 | 27758 | 565.84 | 0 | 52 | 100 | 0 | 0 | 2596 | 3313.84 | 2263.37 | 0 | 209 | 400 | 0 | 0 | 5985 | 8857.37
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFLGUDECK | Lighting at underdeck Structure, citywide | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 000 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FURNISH AND INSTALL LIGHT AT UNDERDECK | 2022 | 4000 | 2413.71 | 0 | 0 | 800 | 800 | 601 | 0 | 4614.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFLGUSBWY | Furnish and Install Lighting under elevated structures | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 000 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FURNISH AND INSTALL LIGHT UNDER ELEVEATED SUBWAY | 2022 | 7735 | 3433.63 | 0 | 0 | 1000 | 1442 | 1200 | 0 | 7075.63 | 0 | 0 | 0 | 0 | 759 | 0 | 0 | 759
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFLUMP | Traffic projects | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FURNISHED AND INSTALLATION OF VARIOUS COMPONENTS | 2022 | 27147 | 0 | 0 | 0 | 0 | 0 | 0 | 9315 | 9315 | 0 | -2000 | 0 | 0 | 0 | 0 | 0 | -2000
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFMARKLMP | THERMOPLASTIC MARKINGS-TEN YEARS | INSTALLATION OF PAVEMENT MARKINGS | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | INSTALLATION OF THERM MARKINGS ON RESURFACED STREETS | 2022 | 30456 | 0 | 0 | 0 | 5719 | 0 | 12065 | 68194 | 85978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFPEDCDW3 | Furnish and install Pedestrian Countdown Clocks | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | URNISH AND INSTALL PEDESTRIAN COUNTDOWN CLOCKS | 2022 | 3222 | 713.49 | 0 | 129 | 0 | 0 | 0 | 0 | 842.49 | 1741.49 | 0 | 1159 | 0 | 0 | 0 | 0 | 2900.49
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFSPDCAM | Purchase and Install Speed Cameras in School Zones Areas | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SPEED CAMERA | SPEED CAMERA | 2022 | 2495 | 121228.06 | 65000 | 0 | 0 | 0 | 1611 | 3704 | 191543.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TFVISIONZ | Traffic Vision Zero projects-St Light Enhancement | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 000 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ST LIGHT AND SPEED CAMERAS FURNISHED AND INSTALLATION | 2022 | 3949 | 3455 | 0 | 0 | 0 | 0 | 0 | 886 | 4341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TRNCHREST | Trench Restoration | PRIMARY STREET RECONSTRUCTION | 000 | HW-0001 HW-0001K | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | TRENCH RESTORATION | TRENCH RESTORATION | 2022 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 2846 | 2846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TYPLILL | STREET LIGHTING <TEN YEAR PLAN) | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 000 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2022 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 246 | 246 | 0 | 0 | 7500 | 0 | 7500 | 0 | 20795 | 35795
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TYPLREP | TRAFFIC PARK & HIGHWAY DISTRIBUTION(TEN YEAR PLAN) | REPLACEMENT OF ELECTRICAL DISTRIBUTION SYSTEMS | 000 | P-0705 TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2022 | 55300 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 5000 | 0 | 15000 | 20000
20220309 | CITYWIDE | 841 | DEPARTMENT OF TRANSPORTATION | TYPLSGM | TRAFFIC SIGNALS (TEN YEAR PLAN) | SIGNAL INSTALLATION AND COMPUTERIZATION | 000 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2022 | 172000 | 0 | 0 | 0 | 0 | 7096 | 7094 | 38427 | 52617 | 0 | 0 | 0 | 0 | 20500 | 0 | 51000 | 71500
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR403 | DPR efficient lighting @various facilities 5bor CNYG-2415MA1 | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT |  | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | FY15 $1 CONTRACT FOR DCAS ACE PROGRAM | FY15 $1 CONTRACT FOR DCAS ACE PROGRAM | 2022 | 2500 | 2731.34 | 0 | 0 | 0 | 228 | 0 | 0 | 2959.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | ACEDPR405 | DPR efficient lighting @ ballfields MN, BK & BX CNYG-2915 | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY |  | P-1018 PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | DCAS - ENERGY EFFICIENCY BALLFIELD LIGHTING RETROFIT AT VARIOUS PARKS& RECREATION FACILITIES, FOR THE BOROUGHS OF THE MN, BK & SI | DCAS - ENERGY EFFICIENCY BALLFIELD LIGHTING RETROFIT AT VARIOUS PARKS& RECREATION FACILITIES, FOR THE BOROUGHS OF THE MN, BK & SI | 2022 | 2386 | 5042.66 | 20 | 0 | 0 | 290 | 0 | 0 | 5352.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | GXBXBKQ1 | GI Citywide-Bioswales in Parks Bronx, Queens & Brooklyn | LAND ACQUISITION AND TREE PLANTING | 000 | WP-0169 P-0822 |  | GI CITYWIDE-BIOSWALES IN PARKS BRONX, QUEENS & BROOKLYN | GI CITYWIDE-BIOSWALES IN PARKS BRONX, QUEENS & BROOKLYN | 2022 | 2272 | 377.3 | 488 | 60 | 0 | 0 | 0 | 0 | 925.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-3TREMTA | FY14 St Tree Planti for Trees removed 2nd Ave Subway MG214M | LAND ACQUISITION AND TREE PLANTING | 000 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 2ND AV SUBWAY CONTRACT- 540 DAY CONTRACT | 2022 | 1586 | 334.34 | 0 | 0 | 0 | 0 | 0 | 0 | 334.34 | 1137.03 | 0 | 0 | 0 | 0 | 185 | 0 | 1322.03
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO3 | Citywide Zoos - roof replacements at various buildings | ZOOS | 000 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | REPLACEMENT OF ROOFS AT QUEENS ZOO OPERATIONS BUILDING, PROSPECT PARKZOO BUILDING A, PROSPECT PARK ZOO BUILDING E, AND PROSPECT PARK ZOO BUILDING F | REPLACEMENT OF ROOFS AT QUEENS ZOO OPERATIONS BUILDING, PROSPECT PARKZOO BUILDING A, PROSPECT PARK ZOO BUILDING E, AND PROSPECT PARK ZOO BUILDING F | 2022 | 2007 | 1773 | 0 | 177 | 0 | 0 | 0 | 0 | 1950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO4 | Citywide Zoos - HVAC replacements | ZOOS | 000 | P-0887 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CENTRAL PARK ZOO AND PROSPECT PARK ZOO | HVAC REPLACEMENT AT CPZ DANCING CRANE CAFE, CPZ ZOOTIQUE GIFT SHOP, CPZ OUTDOOR BIRD HOLDING, AND PPZ CLINIC | 2022 | 790 | 718 | 0 | 72 | 0 | 0 | 0 | 0 | 790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-600ZOO5 | Citywide Zoos - HVAC at CPZ snow leopard & QZ concession | ZOOS | 000 | P-0887 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CITYWIDE ZOOS - HVAC AT CPZ SNOW LEOPARD & QZ CONCESSION | CITYWIDE ZOOS - HVAC AT CPZ SNOW LEOPARD & QZ CONCESSION | 2022 | 700 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6517CBF | Capital Fund Reconstitution | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 000 | P-1018 P-0245K P-1250 P-0720 P-0973 P-0245X P-0245Q P-C050 P-0013 P-0972 P-0060 P-0127 P-0412 P-1026 P-1321 P-1246 P-0245M P-0245R | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 11/20/17 $168K (P-0060 FY18) FR P-1PNYC06...$25K P1250 FY19 FR P-217HVAC...$201K TR FR P-2PNYSP2 (P-0127 CHANGED BL TO P 1018)...$803(FY19 ) AND $197K(FY18) TRF FR P-212CDMP (CHANGED B/L P 1018)...$2388K (P-1018,FY18) TR TO P-1FERRY8...$17K FY20 P1026 & $10K FY20 P1018 TR FR P-501SIB2..$1K FY20 FR P-5BWPA00..$65K P-0245 TR FR P-500WAR..$57K P-1322FY18 FR P-6517CBF..$106K FR P-1PNYC04..$72K(FY18,PC021) FR P-102LAFA.. $1K(,P1329) FR P-1VCMEMO $242K OFFSET FORESTFY18 TO FY19..$20K FR P-501SIB2..$2K (P1250 FR P-4061250..$480K FR P-5GBPATH.. | TRF TO P-208LTPG (P 0374 FY19) $676K...8/17/17 $134K P1018 FY19 TRSFRTO P-4CARSON...FY18 $112K TR TO P-501CLRT...$187K P0374 FY18 TRSF TOP-313CPAB...8/24/17 $205K (P-1018, FY19) XFER FROM P-1BCREQ6...$66K (P1018, FY 18) TRF FR P-2BFREQ2 TO FY'19..8/29/17 $1.5M (P-0374, FY18)TR TO P-1PTSNPK, BUT WILL CHNAGE B/L TO P-1018 IN P-1PTSNPK,...FY 18 $31K ( P C017) TRF IN FR P-202C17I... $6K ( P C017) TRF IN FR P-203C17G...$19K ( P C017) TRF IN FR P-209C17B...$335K ( P0972) & $77K ( P C017) TRF IN FR P-210P972..$154K ( P0245K) TRF IN FR P-212245K...$6K ( P C017) TRF IN FR P-211C017...$8K ( P C017) TRF IN FR P-211C17A...$5K ( P C017) TRF IN FR P-213C17E...$77K ( P C017) TRF IN FR P-213C54B...$2K( P 0245K TRF IN FR P-200JFKM...$15K TRF FR P-3BWPE98...$412K FR P-413IDPK.. $10K FR P-3PLG11A.$101K FR 850 P3CROMNEW..$2K FR 850 P-1PBSSTAR | 2022 | 7121 | 0 | 5878 | 6242 | 15 | 180 | 816 | 47 | 13178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-65BORO | 5 Boro Relocation - 850 East 138th street, Bronx | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 000 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CW | 5 BORO RELOCATION | 2022 | 30000 | 5.08 | 0 | 0 | 0 | 1604 | 0 | 0 | 1609.08 | 10200 | 0 | 0 | 0 | 0 | 0 | 0 | 10200
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BLDG9C | FY10 Building Requirements (CNYG-409M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 000 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CW | BUILDING REQUIREMENTS | 2022 | 590 | 1246.24 | 37 | 0 | 0 | 0 | 0 | 0 | 1283.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6BOIL15 | MOSHOLU PK CS, PROSPECT PK PAINT SHOP, BENSONHURST SR CTR | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 000 | P-1250 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MOSHOLU PK CS, PROSPECT PK PAINT SHOP, BENSONHURST SR CTR | 2022 | 348 | 62.61 | 1063 | 0 | 0 | 0 | 0 | 0 | 1125.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CBLDG4 | REQUIREMENTS - BLDGS - PLMB CNYG-404M | VEHICLES AND EQUIPMENT | 000 | P-R245 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | REQUIREMENTS - BLDGS - PLMB | REQUIREMENTS - BLDGS - PLMB | 2022 | 456 | 274.1 | 100 | 0 | 0 | 0 | 0 | 0 | 374.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CGDWTR | Greenthumb - Installation of water service | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-1018 |  | CITYWIDE | GREENTHUMB - INSTALLATION OF WATER SERVICE | 2022 | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6COMF18 | Recon citywide Comfort Stations $1 contract | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-0505 |  | CITYWIDE | RECON CITYWIDE COMFORT STATIONS $1 CONTRACT | 2022 | 2657 | 2579 | 0 | 217 | 0 | 0 | 0 | 0 | 2796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CPIBN3 | CPI PH1- Construction of CW C/S CNYG-3215M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 000 | P-1018 WP-0169 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CITYWIDE | THE CONSTRUCTION OF TEN, EYCK PLGD CS, LYONS SQUARE PLGD CS, MELROSE COMMONS CS, SAW MILL PLGD CS, HENRY M. JACKSON PLGD CS, LUTHER GULICK PLGD CS | 2022 | 1392 | 20089.34 | 0 | 0 | 0 | 821 | 0 | 0 | 20910.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CPIBN4 | CPI PH1- Bx & Mn C/S-Bundle 4 CNYG-3315M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION |  | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CPI- BX & MN COMFORT STATIONS-BUNDLE 4 | CPI- BX & MN COMFORT STATIONS-BUNDLE 4 | 2022 | 555 | 9240.75 | -36 | 0 | 0 | 623 | 0 | 0 | 9827.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWCGDN | CITYWIDE COMMUNITY GARDENS | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 000 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | VARIOUS LOCATIONS, CITYWIDE | THIS PROJECT WILL PROVIDE FUNDING TO IMPROVE VARIOUS GREENTHUMB COMMUNITY GARDENS CITYWIDE. | 2022 | 3900 | 0 | 0 | 0 | 0 | 0 | 2900 | 0 | 2900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWCMVE | Citywide - Comfort Stations Standards Study | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 000 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITYWIDE COMFORT STATIONS STANDARDS STUDY | 2022 | 225 | 184.21 | 0 | 0 | 0 | 41 | 0 | 0 | 225.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWMARI | CITYWIDE - MARINAS | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 000 | P-1018 P-1245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | VARIOUS LOCATIONS, CITYWIDE | THIS IS LUMP SUM FUNDING FOR MARINAS. | 2022 | 5000 | 0 | 0 | 0 | 0 | 0 | 2699 | 0 | 2699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWMINI | MINI-POOLS - CITYWIDE CNYG-1601MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 000 | P-1008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CITYWIDE | RECONSTRUCTION OF MINI-POOLS - CITYWIDE | 2022 | 789 | 369.44 | 0 | 0 | 0 | 0 | 0 | 0 | 369.44 | 277.98 | 0 | 0 | 0 | 71 | 0 | 0 | 348.98
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWPLE1 | Recon pool electrical systems, Citywide | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-1008 P-1249 |  | CITYWIDE | RECON POOL ELECTRICAL SYSTEMS, CITYWIDE | 2022 | 2200 | 0 | 0 | 0 | 2443 | 0 | 0 | 0 | 2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWPLG1 | Recon pool structural systems, Citywide | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-1008 |  | CITYWIDE | RECON POOL STRUCTURAL SYSTEMS, CITYWIDE | 2022 | 1371 | 0 | 0 | 754 | 0 | 0 | 0 | 0 | 754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWR22D | Citywide HVAC R22 Reconstruction CNYG-1721M | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-1250 |  | CITYWIDE | CITYWIDE HVAC R22 RECONSTRUCTION | 2022 | 2000 | 0 | 0 | 0 | 1001 | 999 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWR23C | CityWide - HVAC R22 coolant retrofit CNYG-920M | VEHICLES AND EQUIPMENT | 000 | P-1250 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CITYWIDE | HVAC | 2022 | 15467 | 30 | 753 | 73 | 4075 | 0 | 4876 | 0 | 9807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWRDIO | CITYWIDE - RUPS/ Radio System & Field equipment Revamp | VEHICLES AND EQUIPMENT | 000 | P-1018 P-0931 |  |  | FY20 JAN NN | 2022 | 4871 | 4189.95 | 0 | 681 | 0 | 0 | 0 | 0 | 4870.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWREWA | Retaining Walls- Citywide-Man.-S.I. & BX CNYG-1320M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 000 | P-1329 |  |  | RETAINING WALLS- CITYWIDE-MAN.-S.I. & BX | 2022 | 12269 | 1248.43 | 1 | 0 | 4910 | 0 | 6130 | 0 | 12289.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6CWSTF | CITYWIDE SYNTHETIC RC | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 000 | P-0245Q P-0510 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | VARIOUS LOCATIONS, CITYWIDE | THIS IS LUMP SUM FUNDING FOR SYNTHETIC TURF FIELDS. | 2022 | 101548 | 0 | 0 | 1274 | 0 | 0 | 0 | 0 | 1274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6DEERFE | Citywide - Deer Fencing - SI ,BX | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 000 | P-1018 WM-0001 |  | BOROUGHS OF STATEN ISLAND AND BRONX | CITYWIDE DEER FENCING | 2022 | 356 | 0 | 0 | 730 | 0 | 0 | 0 | 0 | 730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6DTREE7 | Trees - FY07 Spring Trees (CNYG-407M) | LAND ACQUISITION AND TREE PLANTING | 000 | P-D171 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | FY07 SPRING TREES - CITYWIDE | FY07 SPRING TREES (CNYG-407M) | 2022 | 633 | 623.04 | 0 | 0 | 0 | 69 | 0 | 0 | 692.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRA | Emerald Ash Borer (EAB) Tree Remove BX & MN | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 |  | CITYWIDE | EMERALD ASH BORER (EAB) TREE REMOVE BX &MHT | 2022 | 345 | 243.32 | 0 | 490 | 0 | 0 | 0 | 0 | 733.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6EABTRB | Emerald Ash Borer (EAB) Tree Remove BK &SI-CNYG-2319M | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 |  | EMERALD ASH BORER (EAB) TREE REMOVE BK &SI | EMERALD ASH BORER (EAB) TREE REMOVE BK &SI | 2022 | 894 | 710.52 | 0 | 289 | 0 | 0 | 0 | 0 | 999.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ENVTST | Citywide environment testing at DPR facilities CNYG-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-1018 P-1249 P-1008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CITYWIDE | CITYWIDE ENVIRONMENT TESTING AT DPR FACILITIES | 2022 | 0 | 0 | 0 | 0 | 0 | 266 | 0 | 0 | 266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6FNCE01 | GreenThumb Capital Fencing Work, Citywide | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-1018 |  | CITYWIDE | GREENTHUMB CAPITAL FENCING WORK, CITYWIDE | 2022 | 444 | 0 | 0 | 444 | 0 | 0 | 0 | 0 | 444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GASBSI | CONVERSION OF OIL TO GAS BKLYN & SI CNYG-1914M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION |  | P-1250 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CONVERSION OF OIL TO GAS BKLYN & SI | CONVERSION OF OIL TO GAS BROOKLYN & STATEN ISLAND | 2022 | 1250 | 318.14 | 0 | 0 | 1950 | 1550 | 0 | 0 | 3818.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GASMAN | CONVERSION OF OIL TO GAS MANHATTAN MG-814M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION |  | P-1250 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CONVERSION OF OIL TO GAS MANHATTAN | CONVERSION OF OIL TO GAS MANHATTAN | 2022 | 1750 | 184.96 | 0 | 0 | 0 | 269 | 0 | 0 | 453.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GDRL15 | FY15 Citywide guiderail & fencing CNYG-2015M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION |  | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CITYWIDE | FY15 CITYWIDE GUIDERAIL & FENCING | 2022 | 901 | 204 | 0 | 0 | 0 | 0 | 0 | 0 | 204 | 82.8 | 0 | 0 | 0 | 0 | 57 | 0 | 139.8
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6GMBXGI | Crotona & Harlem River Green Infrastructure Cons., BX, MN | LAND ACQUISITION AND TREE PLANTING | 000 | P-1018 |  | CROTONA AND HARLEM RIVER GREEN INFRASTRUCTURE CONSTRUCTION MANHATTAN& BRONX | CROTONA AND HARLEM RIVER GREEN INFRASTRUCTURE CONSTRUCTION | 2022 | 1937 | 0 | 0 | 0 | 910 | 890 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6LIGHT1 | Construction Of Multisite Path Lighting | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 000 | P-0087 P-1018 P-D021 |  |  | CONSTRUCTION OF MULTISITE PATH LIGHTING-KISSENA CORRIDOR PARK AND CO-OP CITY BIKE PATH | 2022 | 1016 | 73 | 720 | 78 | 0 | 0 | 0 | 0 | 871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6MSHVAC | Recon HVAC at Greenbelt R/C & Queens Museum CNYG-1318M | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | PU-0025 P-0505 P-1250 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | GREENBELT R/C & QUEENS MUSEUM | RECON HVAC AT GREENBELT R/C & QUEENS MUSEUM | 2022 | 650 | 266.59 | 0 | 578 | 1188 | 1960 | 0 | 0 | 3992.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6NCRC15 | FY15 Citywide Nature & Rec Ctr CNYG-1215MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION |  | P-M245 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CITYWIDE | FY15 CITYWIDE NAURE & REC CTR | 2022 | 620 | 85 | 0 | 0 | 0 | 200 | 0 | 0 | 285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6NRGF01 | NRG - Bronx & Queens Reforestation FY'20 CNYG-3019MA | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 |  | BOROUGHS OF BRONX & QUEENS | BRONX AND QUEENS REFORESTATION | 2022 | 1125 | 0 | 0 | 1035 | 0 | 0 | 0 | 0 | 1035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6OLYMPL | Citywide Olympic Pool Mechanical Systems Recon CNYG-2719M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION |  | P-1008 |  | CITYWIDE | CITYWIDE OLYMPIC POOL MECHANICAL SYSTEMS RECON | 2022 | 2985 | 214 | 0 | 1145 | 0 | 0 | 0 | 0 | 1359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ORCAST | Recon Orchard Beach Nature Center | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-1018 P-0505 |  | BRONX & QUEENS | RECON ORCHARD BEACH N/C & ASTORIA PARK F/H | 2022 | 2990 | 213 | 0 | 2350 | 0 | 0 | 0 | 0 | 2563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PBUT15 | FY15 site utility (dig job) plumbing CNYG-1815M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION |  | PU-0025 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CITYWIDE | FY15 SITE UTILITY (DIG JOB) PLUMBING - $1 CONTRACT | 2022 | 1016 | 652.97 | 0 | 152 | 0 | 0 | 39 | 0 | 843.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PLFLTR | Recon of intermediate pool filter plants citywide CNYG-619M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 000 | P-1008 |  | CITYWIDE | RECON OF INTERMEDIATE POOL FILTER PLANTS CITYWIDE | 2022 | 3200 | 2021 | 0 | 393 | 0 | 0 | 0 | 0 | 2414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYG05 | PlaNYC - FY09 Spring Greenstreets (CNYG-2109M) | LAND ACQUISITION AND TREE PLANTING | 000 | P-D171 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CW | FY09 SPRING GREENSTREETS | 2022 | 769 | 696.08 | 0 | 0 | 0 | 73 | 0 | 0 | 769.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYR34 | PlaNYC - Reforestatiob Bk,Que,& SI FY17-25 (CNYG-3816M) | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 |  | PLANYC - REFORESTATION BK,QUE,& SI FY17-25 | PLANYC - REFORESTATIOB BK,QUE,& SI FY17-25 | 2022 | 500 | 514.29 | 0 | 92 | 0 | 0 | 0 | 0 | 606.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PNYT25 | PlaNYC - FY21 Citiwide Tree Guard Installation | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 |  | PLANYC - FY121 CITIWIDE TREE GUARD INSTALLATION | PLANYC - FY121 CITIWIDE TREE GUARD INSTALLATION | 2022 | 842 | 0 | 842 | 0 | 0 | 0 | 0 | 0 | 842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6POOL18 | Recon Citywide pools $1 Contract CNYG-918M | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-1008 |  | CITYWIDE | RECON CITYWIDE POOLS $1 CONTRACT | 2022 | 1529 | 109 | 0 | 2439 | 0 | 0 | 0 | 0 | 2548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6POOL21 | Citywide Pool Plumbing Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-1008 |  | CITYWIDE | FY21 POOL RECON. CITYWIDE | 2022 | 2010 | 0 | 0 | 0 | 2010 | 0 | 0 | 0 | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PVMNT1 | Reconstruct pavement various Parks CNYG-117MA | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | VARIOUS PARKS AND RECREATION LOCATIONS | DOLLAR CONTRACT WILL RECONSTRUCT PAVEMENT SURFACES AT VARIOUS PARKS AND RECREATION LOCATIONS CITYWIDE. | 2022 | 1 | 1674.94 | 483 | 0 | 0 | 57 | 0 | 0 | 2214.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6PVMNT2 | Citywide Pavement Reconstruction 2 CNYG-1618M | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CITYWIDE | THIS DOLLAR CONTRACT WILL RECONSTRUCT PAVEMENT SURFACES AT VARIOUS PARKS AND RECREATION LOCATIONS, CITYWIDE - DOLLAR CONTRACT | 2022 | 1 | 2611.5 | -50 | 204 | 0 | 51 | 0 | 0 | 2816.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REC07D | FY07 Recreation & Nature Centers (HVAC) - CNYG-2007MA2 | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION |  | P-Q245 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CW | FY07 RECREATION & NATURE CENTERS (HVAC) - CNYG-2007M | 2022 | 1145 | 9.11 | 0 | 0 | 0 | 200 | 0 | 0 | 209.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REMT35 | Non Sandy Tree Removal Bx, Mht, Qn | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CITYWIDE | NON SANDY TREE REMOVAL BX, MHT, QN | 2022 | 210 | 94.9 | 0 | 0 | 0 | 1 | 114 | 0 | 209.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6REMT37 | Tree Removal Bx, Mht, Qn FY19 | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | NON SANDY TREE REMOVAL BX, MHT, QN FY19 | NON SANDY TREE REMOVAL BX, MHT, QN FY19 | 2022 | 1013 | 277.06 | 0 | 0 | 0 | 0 | 736 | 0 | 1013.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW14 | Retaining Wall R/C (CNYG-514M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 099 | P-1329 P-D018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CITYWIDE | THE RECONSTRUCTION AND STABILIZATION OF RETAINING WALLS - CITYWIDE | 2022 | 24853 | 25167.03 | 0 | 0 | 0 | 3934 | 0 | 0 | 29101.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RETW18 | Citywide Retaining Wall FY18 CNYG-1818M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 099 | P-1329 |  | CITYWIDE | CITYWIDE RETAINING WALL FY18 | 2022 | 8081 | 3155.88 | 8713 | 780 | 0 | 0 | 0 | 0 | 12648.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6ROOF9A | FY09 Roof Requirements QNS & BX (CNYG-3009M) | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 000 | P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | QNS & BX | FY09 ROOF REQUIREMENTS QNS & BX | 2022 | 2403 | 5508.65 | 0 | 0 | 0 | 330 | 0 | 0 | 5838.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6RPZBKQ | Brooklyn & Queens Multi-Site RPZ Installation | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 000 | P-1250 |  | CITYWIDE | BROOKLYN & QUEENS MULTI-SITE RPZ INSTALLATION | 2022 | 1300 | 242.64 | 8 | 0 | 985 | 0 | 0 | 0 | 1235.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SANDT1 | FY18 Sandy Related Tree Replacement - Q, X, M | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FY18 SANDY RELATED TREE REPLACEMENT - Q, X, M | 2022 | 0 | 2279.53 | 0 | 0 | 0 | 424 | 0 | 0 | 2703.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SECBOL | Parks Security Measures Citywide | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-1095 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CITYWIDE | PARKS SECURITY BOLLARDS CITYWIDE | 2022 | 33740 | 1081.13 | 0 | 0 | 0 | 3789 | 0 | 0 | 4870.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SPCR15 | NRG - Spring Creek Salt Marsh Restoration CNYG-2715M | LAND ACQUISITION AND TREE PLANTING | 000 | P-1327 | PROJECT DELAYED PENDING NON-CITY GRANT APPROVAL | BORDERS THE BOROUGHS OF BROOKLYN AND QUEENS. | SPRING CREEK SALT MARSH AND COASTAL UPLAND RESTORATION | 2022 | 2000 | 1175.11 | 1692 | 1000 | 0 | 5241 | 0 | 0 | 9108.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6STRUC1 | Citywide structural stabilization - Multisite CNYG-1617M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION |  | P-1018 P-0505 P-D018 |  | CITYWIDE | CITYWIDE STRUCTURAL STABILIZATION - MULTISITE - FOR METROPOLITAN POOL& E54TH ST REC CTR... | 2022 | 1267 | 209 | 1185 | 0 | 0 | 0 | 0 | 0 | 1394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6SUSTN1 | Citywide Dollar Sustainability Contract CNYG-319MA | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 000 | PU-0025 |  | CITYWIDE | THIS PROJECT WILL BE FOR RECONSTRUCTION OF VARIOUS SYSTEMS IN CONNECTIONS WITH SUSTAINABILTY AND ENERGY SAVING MEASURES | 2022 | 0 | 0 | 2212 | 0 | 0 | 0 | 0 | 0 | 2212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TPSS21 | Citywide- Tree Planting Supervision Service FY21 | LAND ACQUISITION AND TREE PLANTING | 000 | P-1018 P-0822 |  | CITYWIDE | TREE PLANTING SUPERVISION | 2022 | 654 | 0 | 286 | 0 | 0 | 0 | 0 | 0 | 286 | 0 | 414 | 0 | 0 | 0 | 0 | 0 | 414
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRAI20 | FY19 NRG Arden Woods Trail Construction | LAND ACQUISITION AND TREE PLANTING | 000 | P-R245 P-D019 P-D021 P-0822 |  | BX,QUE,SI TRAIL R/C, & PLANTING TREES | BX,QUE,SI TRAIL R/C, & PLANTING TREES | 2022 | 522 | 55 | 300 | 267 | 0 | 0 | 0 | 0 | 622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRDS22 | Citywide- Tree-Damaged Sidewalks Supervison FY22 | LAND ACQUISITION AND TREE PLANTING | 000 | P-1018 |  | CITYWIDE | CITYWIDE TREE DAMAGED SIDEWALK SUPERVISION FY22 | 2022 | 2270 | 0 | 2396 | 0 | 0 | 0 | 0 | 0 | 2396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE18A | Street Trees Supervision FY18 | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | STREET TREES SUPERVISION FY18 | STREET TREES SUPERVISION FY18 | 2022 | 3813 | 1227.18 | 0 | 1173 | 0 | 0 | 0 | 0 | 2400.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE19A | Street Trees Supervision FY19 | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 |  | STREET TREES SUPERVISION FY19 | STREET TREES SUPERVISION FY19 | 2022 | 1142 | 0 | 0 | 0 | 0 | 958 | 0 | 0 | 958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE22A | CW Tree Planting Supervision FY 22 -MWBE | LAND ACQUISITION AND TREE PLANTING | 000 | P-1018 P-0822 |  | CITYWIDE | CW TREE PLANTING | 2022 | 200 | 0 | 0 | 285 | 0 | 0 | 0 | 0 | 285 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 200
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRE23B | CW Tree & Park Planting Supervision FY 23 | LAND ACQUISITION AND TREE PLANTING | 000 | P-0822 P-1018 PV-0176 |  | VARIOUS LOCATIONS, CITYWIDE | VARIOUS LOCATIONS, CITYWIDE | 2022 | 1948 | 0 | 245 | 301 | 0 | 815 | 0 | 0 | 1361 | 0 | 0 | 587 | 0 | 0 | 0 | 0 | 587
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREEP1 | Procurement of Street Trees Region 1-CNYG-3916M | LAND ACQUISITION AND TREE PLANTING |  | P-0822 |  | CITYWIDE | PROCUREMENT OF STREET TREES REGION 1-CNYG-3916M | 2022 | 13800 | 14879.5 | 0 | 783 | 0 | 0 | 0 | 0 | 15662.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREEP2 | Procurement of Street Trees Region 2-CNYG-4016M | LAND ACQUISITION AND TREE PLANTING |  | P-0822 |  | CITYWIDE | PROCUREMENT OF STREET TREES REGION 2-CNYG-4016M | 2022 | 13800 | 10260 | 0 | 2876 | 0 | 0 | 0 | 0 | 13136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREESB | TREES - CITYWIDE | LAND ACQUISITION AND TREE PLANTING | 099 | P-0822 P-1018 HB-0215 HB-1193 P-D822 ED-0075 ED-0409 P-0950 |  | VARIOUS LOCATIONS, CITYWIDE | THIS IS A GENERAL FUND FOR STREET TREE PLANTING CITYWIDE. | 2022 | 74316 | 0 | 2 | 257 | 0 | 25421 | 10000 | 51216 | 86896 | 0 | 1805 | 0 | 0 | 0 | 0 | 0 | 1805
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREGRD | FY21 CitywideTree Guards | LAND ACQUISITION AND TREE PLANTING |  | P-0822 |  | FY21 CITYWIDETREE GUARDS | FY21 CITYWIDETREE GUARDS | 2022 | 420 | 0 | 149 | 0 | 0 | 0 | 0 | 0 | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREL21 | FY21 Street Tree Long Term Supervision | LAND ACQUISITION AND TREE PLANTING | 000 | WM-0006 P-0822 SE-0002Q |  | FY21 STREET TREE LONG TERM SUPERVISION | FY21 STREET TREE LONG TERM SUPERVISION | 2022 | 1636 | 0 | 3729 | 0 | 0 | 0 | 0 | 0 | 3729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TREP22 | Man. & Bx Street Tree Plant. FY22 -CNYG-922M | LAND ACQUISITION AND TREE PLANTING | 000 | P-D822 P-0822 P-1018 SE-0002M W-0005 S-0195 |  | BOROUGHS OF MANHATTAN AND BRONX | MANHATTAN AND BRONX STREET TREE PLANTING- FY 22 | 2022 | 130 | 0 | 230 | 250 | 0 | 0 | 0 | 0 | 480 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 20
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRPS21 | Citywide Tree Planting Planning Service FY21 | LAND ACQUISITION AND TREE PLANTING | 000 | P-1018 |  | CITYWIDE | CITYWIDE TREE PLANTING PLANNING SERVICE | 2022 | 448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448 | 0 | 0 | 0 | 0 | 0 | 448
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRS19A | CW- RC Sidewalks Damaged by Trees Supervision CNYG-1319M | LAND ACQUISITION AND TREE PLANTING | 000 | P-1331 |  | CITYWIDE- R/C SIDEWALKS DAMAGED BY TREES SUPERVISION | CITYWIDE- R/C SIDEWALKS DAMAGED BY TREES SUPERVISION | 2022 | 1691 | 1945.18 | 0 | 37 | 0 | 0 | 0 | 0 | 1982.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6TRS21A | Man. & Bx -Tree-Damaged Sidewalk | LAND ACQUISITION AND TREE PLANTING | 000 | P-1018 |  | BOROUGHS OF BRONX AND MANHATTAN. | MANHATTAN AND BRONX TREE DAMAGED SIDEWALKS | 2022 | 2800 | 0 | 2800 | 0 | 0 | 0 | 0 | 0 | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | P-6VHXHST | Vehicle Exhaust | VEHICLES AND EQUIPMENT |  | P-1018 |  | CITYWIDE | VEHICLE EXHAUST | 2022 | 180 | 0 | 0 | 305 | 0 | 0 | 0 | 0 | 305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-06 | SANDY - S.I. Beaches Protective Measures North RG-813M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 000 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SANDY -EMERGENCY BOILER WORK | 2022 | 6003 | 408.71 | 0 | 0 | 0 | 0 | 0 | 90 | 498.71 | 3699.81 | 0 | 0 | 0 | 0 | 0 | 799 | 4498.81
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-14 | SANDY - Boardwalks Design CW | BEACHES AND BOARDWALKS |  | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CW | SANDY CW BOARDWALK DESIGN | 2022 | 9966 | 1308.67 | 18418 | 0 | 0 | 0 | 0 | 0 | 19726.67 | 10150.5 | 0 | 0 | 0 | 0 | 0 | 0 | 10150.5
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-17 | Sandy-Trees Removal in Bk & SI CNYG-3616M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 000 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BROOKLYN & STATEN ISLAND | SANDY-TREES REMOVAL IN BK & SI | 2022 | 1100 | 103.9 | 0 | 0 | 0 | 0 | 0 | 6 | 109.9 | 935.1 | 0 | 0 | 0 | 0 | 0 | 55 | 990.1
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-18 | Sandy-Trees Removal in BX ,Mnht & Que CNYG-3516M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 000 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BRONX, MANHATTAN , QUEENS | SANDY-TREES REMOVAL IN BX ,MNHT & QUE | 2022 | 550 | 49.93 | 0 | 4 | 0 | 0 | 1 | 0 | 54.93 | 449.44 | 0 | 0 | 0 | 0 | 0 | 46 | 495.44
20220309 | CITYWIDE | 846 | DEPT OF PARKS AND RECREATION | SANDY6-21 | Sandy Tree Planting and Replanting - BX, Q, & M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 000 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SANDY TREE PLANTING AND REPLANTING - BX, Q, & M | 2022 | 2200 | 384.2 | 0 | 0 | 4 | 0 | 0 | 0 | 388.2 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 32
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-827 | Regulator Chamber Roof Replacements | TRUNK AND DISTRIBUTION MAIN REPLACEMENT |  | WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | REGULATOR CHAMBER ROOF REPLACEMENTS: BROOKLYN (5), BRONX (1). REMOVAL AND REPLACEMENT OF EXISTING DEHABILITATED CONCRETE SLAB ROOFS WITH SUPPORTING STRUCTURAL STEEL SUPPORTS. | 2022 | 563 | 222.38 | 0 | 818 | 0 | 0 | 0 | 0 | 1040.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | C114ACADY | Construction of a New Training Academy | SUPPORT SPACE | 000 | C-0114 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CONSTRUCTION OF NEW ACADEMY BUILDING | 2022 | 100600 | 0 | 3771 | 25000 | 45000 | 151229 | 0 | 0 | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | CT2-INTER | CITY TUNNEL #2, REPLACE GUARD VALVES @ 16A | WATER QUALITY PRESERVATION | 000 | WM-0105 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CITY TUNNEL #2, REPLACE GUARD VALVES @ 16A 17A, ETC | 2022 | 10012 | 10189.48 | 1000 | 1500 | 0 | 0 | 0 | 0 | 12689.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-GUN22 | Emergency Guniting of Sewers, Citywide | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 000 | SE-0758 EP-0007 |  |  | EMERGENCY GUNITING OF SEWERS, CITYWIDE | 2022 | 8911 | 312 | 9796 | 0 | 0 | 0 | 0 | 0 | 10108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-GUN23 | Emergency Guniting of Sewers, Citywide | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 000 | SE-0758 |  |  | EMERGENCY GUNITING OF SEWERS, CITYWIDE. THIS IS A 1 YEAR PROJECT. THETARGETED START DATE FOR THIS CONTRACT IS AS SOON AS THE PREVIOUS CONTRACT, EC-GUN22, EXPIRES. | 2022 | 8101 | 0 | 0 | 8100 | 0 | 0 | 0 | 0 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-LC22A | Emergency Sewer Lining | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 000 | SE-0002K SE-0002M SE-0002Q SE-0002R SE-0002X EP-0007 SE-0200K SE-0200M SE-0200Q SE-0200R SE-0200X |  |  | EMERGENCY SEWER LINING | 2022 | 4458 | 190 | 4446 | 0 | 0 | 0 | 0 | 0 | 4636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-LC23 | Emergency Sewer Lining Contract, Citywide | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 000 | SE-0002K SE-0002M SE-0002Q SE-0002R SE-0002X |  |  | EMERGENCY SEWER LINING CONTRACT, CITYWIDE. THIS IS A 1 YEAR PROJECT. THE TARGETED START DATE FOR THIS CONTRACT IS AS SOON AS THE PREVIOUS CONTRACT, EC-LC22, EXPIRES. | 2022 | 4051 | 0 | 0 | 4050 | 0 | 0 | 0 | 0 | 4050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEC22 | Emergency Reconstruction of Sewers, Citywide | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 000 | EP-0007 SE-0002K SE-0002M SE-0002Q SE-0002R SE-0002X SE-0200K SE-0200Q SE-0200R SE-0200X SE-D200Q |  |  | THIS IS A TIME AND MATERIAL CONTRACT AND A ONE YEAR CONTRACT. HE TARGETED START DATE IS 10/01/2021. | 2022 | 26125 | 48 | 25250 | 0 | 0 | 0 | 0 | 0 | 25298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEC23 | Emergency Construction of Sewers, Citywide | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 000 | EP-0007 SE-0002K SE-0002M SE-0002Q SE-0002R SE-0002X SE-0200K SE-0200Q SE-0200R SE-0200X |  |  | EMERGENCY CONSTRUCTION OF SEWERS, CITYWIDE. THIS IS A 1 YEAR TIME ANDMATERIALS CONTRACT. THE TARGETED START DATE FOR THIS CONTRACT IS AS SOON AS THE PREVIOUS CONTRACT, EC-SEC22, EXPIRES. | 2022 | 23750 | 0 | 0 | 23750 | 0 | 0 | 0 | 0 | 23750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-WMC22 | Emergency Reconstruction of Water Mains, Citywide | AUGMENTATION OF WATER SUPPLY SYSTEMS |  | EP-0007 WM-0001 WM-0006 |  |  | EMERGENCY RECONSTRUCTION OF WATER MAINS, CITYWIDE | 2022 | 13586 | 85 | 12350 | 0 | 0 | 0 | 0 | 0 | 12435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-WMC23 | Emergency Construction of Water Mains, Citywide | AUGMENTATION OF WATER SUPPLY SYSTEMS | 000 | EP-0007 WM-0001 WM-0006 |  |  | EMERGENCY CONSTRUCTION OF WATER MAINS, CITYWIDE. THIS IS A 1 YEAR TIME AND MATERIALS CONTRACT. THE TARGETED START DATE FOR THIS CONTRACT ISAS SOON AS THE PREVIOUS CONTRACT, EC-WMC22, EXPIRES. | 2022 | 12350 | 0 | 0 | 12350 | 0 | 0 | 0 | 0 | 12350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EMS17 | EMS Station 17 - New Facility | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EMS STATION 17 - NEW FACILITY | 2022 | 17001 | 3857.39 | 2461 | 25357 | 0 | 0 | 0 | 0 | 31675.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-359 | Area-wide Contract for Water Mains | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 000 | HW-0200 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | AREA-WIDE CONTRACT FOR WATER MAINS | 2022 | 12600 | 18003.04 | 526 | 0 | 0 | 0 | 0 | 0 | 18529.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | GE-363 | Energency Reconstruction of Water Mains, Citywide | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 000 | WM-0001 WM-0006 EP-0007 |  |  | CITYWIDE EMERGENCY CONSTRUCTION OF WATER MAINS | 2022 | 12543 | 11400 | 5622 | 0 | 0 | 0 | 0 | 0 | 17022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25FACA | FACADE RESTORATION MULTIPLE SITES | SOCIAL SERVICES BUILDINGS | 000 | HR-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | OBA ADVISED THAT ONLY ONE ADDRESS COULD BE LISTED AS THIS PROJECT ISCONSIDERED TO BE CONFIDENTIAL. | FACADE RESTORATION: ROOFS, PARAPETS, EXTERIOR MASONRY, WINDOWS, DOORS, AND RELATED APPURTANCES (EXTERIOR LIGHTING, WINDOW GUARDS, ETC.,) | 2022 | 3260 | 20428.42 | 250 | 0 | 0 | 0 | 0 | 0 | 20678.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25FACA4 | FACADE RESTORATION MULTIPLE SITES | SOCIAL SERVICES BUILDINGS | 000 | HR-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | (1.) 1275 WESTCHESTER AVE., BX. OBA ADVISED THAT ONLY ONE ADDRESS COULD BE LISTED AS THIS PROJECT IS CONSIDERED TO BE CONFIDENTIAL. | FACADE RESTORATION: ROOFS, PARAPETS, EXTERIOR MASONRY, WINDOWS, DOORS, AND RELATED APPURTANCES (EXTERIOR LIGHTING, WINDOW GUARDS, ETC.,) | 2022 | 4322 | 0 | 0 | 505 | 1270 | 3949 | 0 | 0 | 5724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWBUSPAD6 | Citywide Bus Pad Contract (SIM) | PRIMARY STREET RECONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CITYWIDE BUS PAD CONTRACT (SIM) | CITYWIDE BUS PAD CONTRACT (SIM) | 2022 | 3222 | 3500.37 | 7 | 100 | 0 | 0 | 0 | 0 | 3607.37 | 2104.9 | 0 | 0 | 0 | 0 | 0 | 0 | 2104.9
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCPEDLOC | Perimeter Security Measures | PRIMARY STREET RECONSTRUCTION | 000 | HW-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CITYWIDE PEDESTRIAN REFUGE LOCATIONS | CITYWIDE PEDESTRIAN REFUGE LOCATIONS | 2022 | 26970 | 16520.26 | 0 | 0 | 0 | 0 | 0 | 8432 | 24952.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3E | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | PRIMARY STREET RECONSTRUCTION | 000 | HW-0988 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 2022 | 9123 | 2056.66 | 0 | 0 | 0 | 0 | 0 | 0 | 2056.66 | 10528.31 | 0 | 1074 | 0 | 0 | 0 | 0 | 11602.31
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3F1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | PRIMARY STREET RECONSTRUCTION | 000 | HW-0988 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 2022 | 10137 | 7188.02 | 0 | 0 | 0 | 87 | 0 | 0 | 7275.02 | 4480.5 | 0 | 0 | 0 | 0 | 0 | 0 | 4480.5
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3H1 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | PRIMARY STREET RECONSTRUCTION | 000 | HW-0988 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 2022 | 1718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 770 | 770
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH3H2 | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | PRIMARY STREET RECONSTRUCTION | 000 | HW-0988 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | SAFE ROUTES TO SCHOOLS-94 SCHOOLS | 2022 | 2909 | 914.78 | 0 | 0 | 0 | 0 | 0 | 0 | 914.78 | 932.35 | 0 | 0 | 0 | 0 | 0 | 1451 | 2383.35
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4A | Safe Route to Schools - Phase 4A (MED-635) | PRIMARY STREET RECONSTRUCTION | 000 | HW-0988 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SAFE ROUTES TO SCHOOLS PHASE 4 - 31 SCHOOLS | SAFE ROUTES TO SCHOOLS PHASE 4 - 31 SCHOOLS | 2022 | 5344 | 2361.41 | 0 | 0 | 0 | 0 | 0 | 0 | 2361.41 | 5052.08 | 0 | 0 | 0 | 0 | 0 | 398 | 5450.08
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4B1 | Safe Routes to Schools - Phase 4B1 | PRIMARY STREET RECONSTRUCTION | 000 | HW-0944 HW-0988 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SAFE ROUTES TO SCHOOLS - PHASE 4B1 | SAFE ROUTES TO SCHOOLS - PHASE 4B1 | 2022 | 5542 | 4656.72 | 0 | 0 | 0 | 40 | 0 | 0 | 4696.72 | 4474.29 | 10 | 0 | 0 | 0 | 0 | 0 | 4484.29
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C2 | Safe Routes to Schools - Phase 4C2 | PRIMARY STREET RECONSTRUCTION | 000 | HW-0988 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SRTS - PHASE 4C2 | SRTS - PHASE 4C2 | 2022 | 17600 | 7572.01 | 0 | 0 | 0 | 33 | 0 | 0 | 7605.01 | 8945.21 | 0 | 0 | 0 | 37 | 0 | 0 | 8982.21
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4D | Safe Routes to Schools - Phase 4D, NDF-SCH4D (HED582) | PRIMARY STREET RECONSTRUCTION | 000 | HW-0988 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SAFE ROUTES TO SCHOOLS - PHASE 4D | SAFE ROUTES TO SCHOOLS - PHASE 4D | 2022 | 4200 | 1378.43 | 0 | 4129 | 0 | 0 | 0 | 0 | 5507.43 | 0 | 0 | 14695 | 0 | 0 | 0 | 0 | 14695
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPKR | Safe Routes to Schools - Brooklyn & Staten Island | PRIMARY STREET RECONSTRUCTION | 000 | HW-0001 HW-D101 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | SAFE ROUTES TO SCHOOLS - BROOKLYN & STATEN ISLAND | SAFE ROUTES TO SCHOOLS - BROOKLYN & STATEN ISLAND | 2022 | 14060 | 1807.99 | 500 | 11983 | 0 | 0 | 0 | 0 | 14290.99 | 0 | 0 | 840 | 0 | 0 | 0 | 0 | 840
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPMN | SAFE ROUTES TO SCHOOLS- MANHATTAN | PRIMARY STREET RECONSTRUCTION | 099 | HW-0988 HW-D102 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SAFE ROUTES TO SCHOOLS- MANHATTAN | SAFE ROUTES TO SCHOOLS- MANHATTAN | 2022 | 18702 | 2182.71 | 0 | 26958 | 0 | 0 | 0 | 0 | 29140.71 | 0 | 0 | 13357 | 0 | 0 | 0 | 0 | 13357
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15XMCL | Simple, Complex & Landmark Ped Ramps - Bronx and Manhattan | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 TF-0502 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SIMPLE, COMPLEX & LANDMARK PED RAMPS - BRONX AND MANHATTAN | SIMPLE, COMPLEX & LANDMARK PED RAMPS - BRONX AND MANHATTAN | 2022 | 5081 | 7883.27 | 589 | 0 | 0 | 0 | 0 | 0 | 8472.27 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 35
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP15XMTA | Complex Ped Ramps - Transit Authority - Manhattan | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 TF-0002 TF-0502 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | COMPLEX PED RAMPS - TRANSIT AUTHORITY - BRONX AND MANHATTAN | COMPLEX PED RAMPS - TRANSIT AUTHORITY - BRONX AND MANHATTAN | 2022 | 4524 | 10652.61 | 724 | 0 | 0 | 0 | 0 | 0 | 11376.61 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 20
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19CWLM | CITYWIDE COMPLEX PED RAMPS (LANDMARK) - MANHATTAN AND BRONX | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITYWIDE COMPLEX PED RAMPS (LANDMARK)- MANHATTAN AND BRONX | 2022 | 7290 | 1648.1 | 0 | 6738 | 0 | 0 | 0 | 0 | 8386.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KQTA | CITYWIDE COMPLEX PED RAMPS (TA) - BROOKLYN AND QUEENS | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY)- BROOKLYN AND QUEENS | 2022 | 5588 | 1504.38 | 120 | 5244 | 0 | 0 | 0 | 0 | 6868.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19QRC | Citywide Complex Pedestrian Ramps - Queens and Staten Island | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITYWIDE COMPLEX PEDESTRIAN RAMPS- QUEENS AND STATEN ISLAND | 2022 | 6687 | 1299.56 | 0 | 6180 | 0 | 0 | 0 | 0 | 7479.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2019S | Citywide Simple Pedestrian Ramps | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITYWIDE SIMPLE PEDESTRIAN RAMPS | 2022 | 6466 | 6441.71 | 300 | 0 | 0 | 0 | 0 | 0 | 6741.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020LM | Non-Standard Ped Ramp Installs - Citywide Landmark Locations | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX PED RAMP INSTALLS - CITYWIDE LANDMARK LOCATIONS | COMPLEX PED RAMP INSTALLS - CITYWIDE LANDMARK LOCATIONS | 2022 | 7586 | 1036.14 | 0 | 0 | 7017 | 0 | 0 | 0 | 8053.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020TA | Non-Standard Ped Ramp Installs - Manh, Brnx, Bk, & Queens | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX PED RAMP INSTALLS - MANH, BRNX, BK, & QUEENS | COMPLEX PED RAMP INSTALLS - MANH, BRNX, BK, & QUEENS | 2022 | 6019 | 1020.65 | 450 | 0 | 5691 | 0 | 0 | 66 | 7227.65 | 0 | 0 | 0 | 5 | 0 | 0 | 5 | 10
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021LM | Non-Standard Installs - Landmark | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NON-STANDARD INSTALLS - LANDMARK | NON-STANDARD INSTALLS - LANDMARK | 2022 | 0 | 0 | 0 | 586 | 0 | 7175 | 0 | 0 | 7761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021TA | Non-Standard Installs - TA | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NON-STANDARD INSTALLS - TA | NON-STANDARD INSTALLS - TA | 2022 | 0 | 0 | 0 | 449 | 0 | 5794 | 0 | 0 | 6243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20KRC | Non-Standard Ped Ramp Installs - Brooklyn & Staten Island | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX PED RAMP INSTALLS - BROOKLYN & STATEN ISLAND | COMPLEX PED RAMP INSTALLS - BROOKLYN & STATEN ISLAND | 2022 | 7137 | 984.03 | 120 | 0 | 6597 | 0 | 0 | 0 | 7701.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MKC | Non-Standard Ped Ramp Installs - Manhattan & Brooklyn | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX PED RAMP INSTALLS - MANHATTAN & BROOKLYN | COMPLEX PED RAMP INSTALLS - MANHATTAN & BROOKLYN | 2022 | 7956 | 675 | 158 | 0 | 7353 | 0 | 0 | 0 | 8186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP20MXQC | Non-Standard Ped Ramp Install- Manh,Queens & Bronx -DSGN BLD | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX PED RAMP INSTALLS - MANHATTAN, QUEENS, & BRONX | COMPLEX PED RAMP INSTALLS - MANHATTAN, QUEENS, & BRONX | 2022 | 7244 | 275 | 7268 | 0 | 0 | 0 | 0 | 0 | 7543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21KQC | Non-Standard Installs - Brooklyn and Queens | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NON-STANDARD INSTALLS - BROOKLYN AND QUEENS | NON-STANDARD INSTALLS - BROOKLYN AND QUEENS | 2022 | 0 | 0 | 0 | 540 | 0 | 6592 | 0 | 0 | 7132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21KRC | Non-Standard Installs - Brooklyn and Staten Island | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NON-STANDARD INSTALLS - BROOKLYN AND STATEN ISLAND | NON-STANDARD INSTALLS - BROOKLYN AND STATEN ISLAND | 2022 | 0 | 0 | 0 | 495 | 0 | 6041 | 0 | 0 | 6536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP21MXQC | Non-Standard Installs - Manhattan, Bronx, Queens | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NON-STANDARD INSTALLS - MANHATTAN, BRONX, QUEENS | NON-STANDARD INSTALLS - MANHATTAN, BRONX, QUEENS | 2022 | 0 | 0 | 0 | 575 | 0 | 7004 | 0 | 0 | 7579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF1 | Multi-Site Pedestrian Safety | PRIMARY STREET RECONSTRUCTION | 000 | HW-0001Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | MULTI-SITE PEDESTRIAT SAFETY - NF & EARMARKS | PED SAFETY | 2022 | 3971 | 4696.65 | 127 | 0 | 0 | 0 | 0 | 0 | 4823.65 | 1082 | 0 | 0 | 0 | 0 | 0 | 0 | 1082
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF3A | MULTI-SITE PEDESTRIAN SAFETY - 7 LOCATIONS | PRIMARY STREET RECONSTRUCTION | 000 | HW-0988 TF-0002 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | MULTI-SITE PEDESTRIAN SAFETY - 5 LOCATIONS | MULTI-SITE PEDESTRIAN SAFETY - 5 LOCATIONS | 2022 | 5583 | 10539.21 | 1950 | 0 | 0 | 0 | 0 | 0 | 12489.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MXC | Complex Upgrades Ped Ramps - Manhattan and the Bronx | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX UPGRADES PED RAMPS - MANHATTAN AND THE BRONX | COMPLEX UPGRADES PED RAMPS - MANHATTAN AND THE BRONX | 2022 | 7510 | 1096.97 | 0 | 6955 | 0 | 0 | 0 | 0 | 8051.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19QRC | Complex Upgrades Ped Ramps - Queens and Staten Island | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX UPGRADES PED RAMPS - QUEENS AND STATEN ISLAND | COMPLEX UPGRADES PED RAMPS - QUEENS AND STATEN ISLAND | 2022 | 7421 | 1330.65 | 0 | 6942 | 0 | 0 | 0 | 0 | 8272.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KMC | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX UPGRADES PED RAMP - MANHATTAN & BROOKLYN | COMPLEX UPGRADES PED RAMP - MANHATTAN & BROOKLYN | 2022 | 7982 | 1032 | 0 | 564 | 7418 | 0 | 0 | 0 | 9014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKL | Non-Standard Upgrades Ped Ramp - Manhattan & Brooklyn | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX UPGRADES PED RAMP - MANHATTAN & BROOKLYN | COMPLEX UPGRADES PED RAMP - MANHATTAN & BROOKLYN | 2022 | 6816 | 850 | 0 | 478 | 6338 | 0 | 0 | 0 | 7666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MKT | Non-Standard Upgrades Ped Ramp - TA Manhattan & Brooklyn | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX UPGRADES PED RAMP - TA MANHATTAN & BROOKLYN | COMPLEX UPGRADES PED RAMP - TA MANHATTAN & BROOKLYN | 2022 | 6303 | 700.34 | 250 | 0 | 5877 | 0 | 0 | 0 | 6827.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQC | Non-Standard Upgrades Ped Ramp - Manhattan & Queens | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX UPGRADES PED RAMP - MANHATTAN & QUEENS | COMPLEX UPGRADES PED RAMP - MANHATTAN & QUEENS | 2022 | 7641 | 300 | 0 | 0 | 7101 | 0 | 0 | 0 | 7401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MQX | Non-Standard Upgrades Ped Ramp - TA Manhattan,Queens,&Bronx | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX UPGRADES PED RAMP - TA MANHATTAN, QUEENS, & BRONX | COMPLEX UPGRADES PED RAMP - TA MANHATTAN, QUEENS, & BRONX | 2022 | 6784 | 190 | 0 | 0 | 6784 | 0 | 0 | 0 | 6974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MX | Pedestrian Ramp Rehabilitation - Manhattan and Bronx | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PEDESTRIAN RAMP REHABILITATION - MANHATTAN AND BRONX | PEDESTRIAN RAMP REHABILITATION - MANHATTAN AND BRONX | 2022 | 13716 | 2426.6 | 9528 | 0 | 2027 | 0 | 0 | 0 | 13981.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MXC | Non-Standard Upgrades Ped Ramp - Manhattan & Bronx | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX UPGRADES PED RAMP - MANHATTAN & BRONX | COMPLEX UPGRADES PED RAMP - MANHATTAN & BRONX | 2022 | 8136 | 935 | 575 | 0 | 7561 | 0 | 0 | 0 | 9071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KR | Rehabilitation of Standard Ped Ramps - Brooklyn&Staten Islan | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 |  |  | REHABILITATION OF STANDARD PED RAMPS - BROOKLYN & STATEN ISLAND | 2022 | 15382 | 300 | 21128 | 0 | 0 | 0 | 0 | 0 | 21428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21KRC | FY23 Non-Standard Pedestrian Ramp Upgrades | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | FY23 NON-STANDARD PEDESTRIAN RAMP UPGRADES | FY23 NON-STANDARD PEDESTRIAN RAMP UPGRADES | 2022 | 0 | 0 | 0 | 573 | 0 | 7559 | 0 | 0 | 8132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21LMT | FY23 Non-Standard Pedestrian Ramp Upgrades | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | FY23 NON-STANDARD PEDESTRIAN RAMP UPGRADES | FY23 NON-STANDARD PEDESTRIAN RAMP UPGRADES | 2022 | 0 | 0 | 0 | 585 | 0 | 8065 | 0 | 0 | 8650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MQ | Rehabilitation of Standard Ped Ramps - Queens & Manhattan | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 |  |  | REHABILITATION OF STANDARD PED RAMPS - QUEENS & MANHATTAN | 2022 | 15491 | 200 | 21368 | 0 | 0 | 0 | 0 | 0 | 21568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21MTA | FY23 Non-Standard Pedestrian Ramp Upgrades | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | FY23 NON-STANDARD PEDESTRIAN RAMP UPGRADES | FY23 NON-STANDARD PEDESTRIAN RAMP UPGRADES | 2022 | 0 | 0 | 0 | 687 | 0 | 9491 | 0 | 0 | 10178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QC | FY23 Non-Standard Pedestrian Ramp Upgrades | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | FY23 NON-STANDARD PEDESTRIAN RAMP UPGRADES | FY23 NON-STANDARD PEDESTRIAN RAMP UPGRADES | 2022 | 8117 | 0 | 0 | 573 | 0 | 7544 | 0 | 0 | 8117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 |  |  | REHABILITATION OF STANDARD PED RAMPS - QUEENS & BRONX | 2022 | 14310 | 200 | 17346 | 0 | 0 | 0 | 0 | 0 | 17546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21XC | FY23 Non-Standard Pedestrian Ramp Upgrades | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | FY23 NON-STANDARD PEDESTRIAN RAMP UPGRADES | FY23 NON-STANDARD PEDESTRIAN RAMP UPGRADES | 2022 | 0 | 0 | 0 | 574 | 0 | 7574 | 0 | 0 | 8148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22KR | Rehabilitation of Standard Ped Ramps - Brooklyn & SI | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | REHABILITATION OF STANDARD PED RAMPS - BROOKLYN & SI | REHABILITATION OF STANDARD PED RAMPS - BROOKLYN & SI | 2022 | 13358 | 0 | 5129 | 5235 | 2617 | 0 | 0 | 0 | 12981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22MQ | Rehabilitation of Standard Ped Ramps - Manhattan & Queens | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | REHABILITATION OF STANDARD PED RAMPS - MANHATTAN & QUEENS | REHABILITATION OF STANDARD PED RAMPS - MANHATTAN & QUEENS | 2022 | 18591 | 0 | 7141 | 7284 | 3641 | 0 | 0 | 0 | 18066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22QX | Rehabilitation of Standard Ped Ramps - Queens & Bronx | PEDESTRIAN RAMP CONSTRUCTION | 000 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | REHABILITATION OF STANDARD PED RAMPS - QUEENS & BRONX | REHABILITATION OF STANDARD PED RAMPS - QUEENS & BRONX | 2022 | 15955 | 0 | 6126 | 6253 | 3126 | 0 | 0 | 0 | 15505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2009DS | PRIOR NOTICE SIDEWALKS (DISTINCTIVE) - CITYWIDE(SIM) | SIDEWALK RECONSTRUCTION | 000 | HW-0200 |  | PRIOR NOTICE SIDEWALKS (DISTINCTIVE) - CITYWIDE | PRIOR NOTICE SIDEWALKS (DISTINCTIVE) - CITYWIDE | 2022 | 2149 | 1604.71 | 0 | 0 | 0 | 0 | 0 | 452 | 2056.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020XM | Prior Notice Sidewalks- Manhattan & Bronx | SIDEWALK RECONSTRUCTION | 000 | HW-0200 P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PRIOR NOTICE SIDEWALKS- MANHATTAN & BRONX | PRIOR NOTICE SIDEWALKS- MANHATTAN & BRONX | 2022 | 4759 | 2162.76 | 1212 | 0 | 0 | 0 | 1447 | 0 | 4821.76 | 866 | 0 | 0 | 0 | 0 | 0 | 0 | 866
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021XM | PRIOR NOTICE SIDEWALK - BRONX & MANHATTAN | SIDEWALK RECONSTRUCTION | 000 | HW-0200 P-1331 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PRIOR NOTICE SIDEWALK - CITYWIDE - BRONX AND MANHATTAN | PRIOR NOTICE SIDEWALK - CITYWIDE - BRONX AND MANHATTAN | 2022 | 3941 | 0 | 2485 | 0 | 0 | 0 | 0 | 0 | 2485 | 0 | 956 | 0 | 0 | 0 | 0 | 0 | 956
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRQX1 | Trench Restoration - Queens and Bronx (SEX002271) | PRIMARY STREET RECONSTRUCTION |  | HW-0001 HW-D103 HW-0200 TF-0002 TF-0502 HW-0944 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TRENCH RESTORARTION - QUEENS AND BRONX | 2022 | 14700 | 2275.03 | 16646 | 0 | 0 | 0 | 0 | 0 | 18921.03 | 0 | 970 | 0 | 0 | 0 | 0 | 0 | 970
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | JJ1FACREN | FACILITIES RENOVATIONS | CHILD WELFARE FACILITIES | 000 | CS-0005 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | FACILITY RENOVATION | VARIOUS FACILITY RENOVATION | 2022 | 13514 | 71405.8 | 1443 | 0 | 0 | 0 | 0 | 0 | 72848.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA16WH1 | Washington Heights - Third Floor Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | LN-D008 LN-0008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | THIRD FLOOR RENOVATION | 2022 | 2701 | 0 | 0 | 2641 | 0 | 0 | 0 | 0 | 2641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO141-40P | NEW 40TH PRECINCT | POLICE FACILITIES |  | PO-0141 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | EAST 149TH STREET AND SAINT ANNS AVENUE, BRONX | NEW 40TH PCT | 2022 | 68914 | 75992.26 | 4321 | 0 | 0 | 0 | 0 | 0 | 80313.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO205-PA | CONSTRUCTION OF A NEW POLICE ACADEMY/TRAINING FACILITY | POLICE FACILITIES | 000 | PO-0205 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CONSTRUCTION OF A NEW POLICE ACADEMY AND TRAINING FACILITY, CITYWIDE | 2022 | 1130200 | 875552.35 | 277 | 2714 | 0 | 0 | 0 | 0 | 878543.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDCW1 | Front Desk Renovations for 45th, 75th, 105th, 123rd PCTS | POLICE FACILITIES | 000 | PO-0079 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FRONT DESK RENOVATIONS CITY WIDE | 2022 | 940 | 344.75 | 96 | 1184 | 0 | 0 | 0 | 0 | 1624.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79WNDWS | HWY UNIT 3, 67TH, 76TH, 111TH PCT WINDOW RPLCMNT | POLICE FACILITIES | 000 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | WINDOW REPLACEMENT | 2022 | 2200 | 2327.21 | 6100 | 0 | 0 | 0 | 0 | 0 | 8427.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PS-312MX | REPAIRS & REHAB OF INTERCEPTING SEWERS - MANHATTAN | PLANT UPGRADING AND RECONSTRUCTION | 000 | WP-0269 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CITYWIDE REPAIRS TO AND REHABILITATION OF INTERCEPTING SEWERS THAT HAVE STRUCTURAL DEFECTS THAT MAY RESULT IN PIPE FAILURES IN THE NEAR TERM - MANAHTTAN AND BRONX | CITYWIDE REPAIRS TO AND REHABILITATION OF INTERCEPTING SEWERS THAT HAVE STRUCTURAL DEFECTS THAT MAY RESULT IN PIPE FAILURES IN THE NEAR TERM - MANAHTTAN AND BRONX | 2022 | 13714 | 1021.44 | 19246 | 0 | 0 | 0 | 0 | 0 | 20267.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW335ALLS | Asbestos and Lead Abatement Lump Sum | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS |  | PW-0335 |  |  | ASBESTOS AND LEAD ABATEMENT LUMP SUM | 2022 | 6910 | 1284.63 | 0 | 1407 | 0 | 0 | 0 | 0 | 2691.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-71 | FUEL TANK REPLACEMENT | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 000 | PW-0348 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | FUEL TANKS | FUEL TANKS | 2022 | 12385 | 21319.48 | 0 | 7445 | 0 | 0 | 0 | 0 | 28764.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-72 | FUEL TANK REPLACEMENT | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS |  | PW-0348 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FUEL TANKS | 2022 | 12500 | 14690 | 0 | 3913 | 0 | 0 | 3913 | 0 | 22516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-81 | FUEL TANK REPLACEMENT | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 000 | PW-0348 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FUEL TANKS. | 2022 | 27500 | 7821.44 | 7478 | 0 | 0 | 0 | 10000 | 0 | 25299.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-82 | FUEL TANK REPLACEMENT | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 000 | PW-0348 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FUEL TANKS | 2022 | 27500 | 7920 | 7250 | 0 | 0 | 0 | 10000 | 0 | 25170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-83 | FUEL TANK REPLACEMENT | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 000 | PW-0348 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FUEL TANK. | 2022 | 27400 | 7711.3 | 7535 | 0 | 0 | 0 | 10000 | 0 | 25246.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-84 | FUEL TANK REPLACEMENT | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 000 | PW-0348 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FUEL TANKS. | 2022 | 27500 | 6900 | 8316 | 0 | 0 | 0 | 10000 | 0 | 25216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | PWCOMPDAT | Comptroller's Office Data Center Replacement at 1 Centre St. | REHABILITATION OF CITY-OWNED OFFICE SPACE | 000 | PW-0077 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COMPTROLLER'S OFFICE DATA CENTER REPLACEMENT AT 1 CENTRE ST. | 2022 | 1401 | 831.39 | 0 | 0 | 0 | 7670 | 0 | 0 | 8501.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1050 | Install Distribution WM throughout Bronx & Queens | AUGMENTATION OF WATER SUPPLY SYSTEMS | 000 | WM-0001 |  |  | INSTALL DISTRIBUTION WM THROUGHOUT BRONX & QUEENS. ALL EXISTING HYDRANTS MUST BE REPAINTED & STENCILED, A CONCRETE PAD MUST BE INSTALLED WITH PROCTECTIVE BOLLARDS IN ACCORDANCE WITH THE DEP SPECIFICATIONS/STANDARDS DRAWINGS. ALL CATCH BASINS WITHIN PROJECT LIMITS SHALL BE CLEANED. | 2022 | 4604 | 10831.41 | 4435 | 0 | 0 | 0 | 0 | 0 | 15266.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-388 | Install Distribution WM throughout Brooklyn & Staten Island | AUGMENTATION OF WATER SUPPLY SYSTEMS | 000 | WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INSTALL DISTRIBUTION WM THROUGHOUT BROOKLYN & STATEN ISLAND. ALL EXISTING HYDRANTS MUST BE REPAINTED AND STENCILED, A CONCRETE PAD MUST BE INSTALLED WITH PROTECTIVE BOLLARDS IN ACCORDANCE WITH THE DEP SPECIFICATIONS/ STANDARD DRAWINGS. ALL CATCH BASINS WITHIN PROJECT LIMIT SHALL BE CLEANED. | 2022 | 4604 | 11048.66 | 607 | 0 | 0 | 0 | 608 | 0 | 12263.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBCHCM | HURRICANE SANDY DAMAGE CM MANAGED PROJECTS | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION |  | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | HURRICANE SANDY CM MANAGED PROJECTS | 2022 | 11413 | 1217.4 | 0 | 10232 | 0 | 0 | 0 | 0 | 11449.4 | 10252.62 | 0 | 0 | 0 | 0 | 0 | 0 | 10252.62
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDCONDC | Sandy Conduit Replacement - Citywide | FACILITY RECONSTRUCTION | 000 | HW-0003 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SANDY CONDUIT REPLACEMENT - CITYWIDE | SANDY CONDUIT REPLACEMENT - CITYWIDE | 2022 | 5326 | 759.21 | 0 | 0 | 0 | 657 | 0 | 0 | 1416.21 | 86.75 | 0 | 0 | 0 | 5907 | 0 | 0 | 5993.75
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDISLND | HURRICANE SANDY DAMAGE ROCKAWAY BEACH ENTRY ISLANDS | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION |  | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION OF ROCKAWAY BEACH ENTRY ISLANDS | 2022 | 65009 | 5674.43 | 579 | 0 | 0 | 0 | 0 | 0 | 6253.43 | 47813.3 | 0 | -11 | 0 | 0 | 517 | 0 | 48319.3
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDPRFAB | HURRICANE SANDY DAMAGE BEACHFRONT RESTORATION PROJECT | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION |  | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACE MODULAR BUILDING UNITS AT VARIOUS FACILITIES | 2022 | 136680 | 36832.79 | 0 | 20464 | 0 | 0 | 0 | 122 | 57418.79 | 111319.48 | 0 | 0 | 0 | 0 | 0 | 0 | 111319.48
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRENO | HURRCANE SANDY DAMAGE STATEN ISLAND BEACHES-VARIOUS | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION |  | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW MODULAR STRUCTURES AT VARIOUS BEACHES IN STATEN ISLAND AND BROOKLYN | 2022 | 13563 | 1254.27 | 2032 | 0 | 0 | 0 | 0 | 0 | 3286.27 | 11179.28 | 0 | 0 | 0 | 0 | 0 | 0 | 11179.28
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM1 | Citywide Resiliency Measures, ESCR, Project Area 1 | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 000 | PU-0100 SE-0002M EP-0007 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITYWIDE RESILIENCY MEASURES-EAST SIDE COASTAL RESILIENCY | 2022 | 510854 | 8093.57 | 166175 | 282304 | 350109 | 324282 | 144860 | 5304 | 1281127.57 | 13900.12 | 67977 | 27209 | 26832 | 33443 | 14839 | 0 | 184200.12
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESM2 | Citywide Reiliency Measures, ESCR, Project Area 2 | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 000 | PU-0100 WM-0001 |  |  | CITYWIDE RESILIENCY MEASURES - EAST SIDE COASTAL RESILIENCY, PROJECT AREA 2 | 2022 | 216235 | 14129.31 | 360 | 21700 | 5425 | 5234 | 0 | 0 | 46848.31 | 174918.15 | 926 | 438 | 0 | 0 | 0 | 0 | 176282.15
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRESPC | Citywide Resiliency Measures, ESCR, Parallel Conveyance | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 000 | PU-0100 SE-0002M WM-0001 EP-0007 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  |  | 2022 | 103633 | 14 | 127753 | 10207 | 0 | 0 | 0 | 0 | 137974 | 0 | 27807 | 0 | 0 | 0 | 0 | 0 | 27807
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDTWOBR | CITYWIDE RESILENCY MEASURES-Lower Manhattan Two Bridges SIRR | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 000 | PU-0100 |  |  |  | 2022 | 446383 | 0 | 0 | 1 | 205965 | 98882 | 13155 | 0 | 318003 | 0 | 15677 | 110376 | 69649 | 2654 | 126 | 0 | 198482
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-813 | WATER MAIN WORK IN JEWEL STREETS AREA | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 000 | SE-0002K SE-0200K WM-0001 SE-0005 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WATER MAIN WORK IN JEWEL STREETS AREA COMMUNITY BOARD 10 IN QUEENS AND CB 5 BROOKLYN | 2022 | 25910 | 1138.2 | 0 | 0 | 4527 | 35304 | 0 | 0 | 40969.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEBLQX01 | Reconstruction of existing sewers from back log QN & BX | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 000 | SE-0002Q SE-0002X |  |  | RECONSTRUCTION OF EXISTING SEWERS FROM BACK LOG IN QUEENS AND THE BRONX | 2022 | 9500 | 71 | 0 | 4750 | 4750 | 0 | 0 | 0 | 9571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEC20004W | Emergency Reconstruction of Sewers, Citywide | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 000 | EP-0007 SE-0002K SE-0002M SE-0002Q SE-0002R SE-0002X SE-0200K SE-0200Q SE-0200R SE-0200X |  |  | CITYWIDE EMERGENCY RECONSTRUCTION OF SEWERS | 2022 | 26129 | 27127.25 | 13213 | 0 | 0 | 0 | 0 | 0 | 40340.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-GUN-18 | Guniting of Sewers, Citywide | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 000 | SE-0758 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | GUNITING OF SEWERS, CITYWIDE | 2022 | 10704 | 20044.85 | 236 | 0 | 0 | 0 | 0 | 0 | 20280.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-GUN-20 | Emergency Guniting of Sewers, Citywide | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS |  | SE-0758 |  |  | EMERGENCY GUNITING OF SEWERS, CITYWIDE | 2022 | 9000 | 7905.6 | 4043 | 0 | 0 | 0 | 0 | 0 | 11948.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-LC-22 | Emergency Sewer Lining | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS |  | SE-0002K SE-0002M SE-0002Q SE-0002R SE-0002X |  |  | EMERGENCY SEWER LINING, CITYWIDE | 2022 | 4050 | 3765.97 | 2607 | 0 | 0 | 0 | 0 | 0 | 6372.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC09 | SEWER LINING CONTRACT, CITYWIDE | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 000 | SE-0002Q SE-0002K SE-0002R SE-0002X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SEWER LINING OF NEW INTERIOR SURFACE TO SEWER WITHOUT REQUIRING OPEN TRENCH SEWER REPAIRS. | 2022 | 4000 | 7585.71 | 22 | 462 | 0 | 0 | 0 | 0 | 8069.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SELCDDC10 | SEWER LINING CONTRACT, CITYWIDE | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 000 | SE-0002K SE-0002M SE-0002Q SE-0002R SE-0002X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SEWER LINING OF NEW INTERIOR SURFACE TO SEWER WITHOUT REQUIRING OPEN TRENCH SEWER REPAIRS. | 2022 | 4000 | 97.42 | 4045 | 1000 | 1000 | 0 | 456 | 0 | 6598.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002271 | Upgrade combined sewer Franklin ave- other Locs HWTRQX1 | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 000 | SE-0002X SE-0002Q EP-0007 WM-0001 WP-0169 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | UPGRADE COMBINED SEWER IN FRANKLIN AVENUE AND OTHER LOCATIONS IDENTIFIED ON SHEET 3.UPGRADE WATR MAIN FRANKLIN AVENUE.THIS WORK WILL BE DONE IN CONJUNCTION WITH DOT PROJECT HWTRQX1. | 2022 | 2970 | 0 | 3519 | 0 | 0 | 0 | 0 | 0 | 3519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 850 | DEPT OF DESIGN & CONSTRUCTION | WM-LC-17 | Citywide Lining Contract for Water Mains | AUGMENTATION OF WATER SUPPLY SYSTEMS | 000 | WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CITYWIDE LINING CONTRACT FOR LINING OF WATER MAINS ON BRIDGES AND OTHER NECESSARY INSTANCES | 2022 | 1000 | 5213.73 | 1582 | 0 | 0 | 0 | 0 | 0 | 6795.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264CADA | CITYWIDE COURTS ADA LUMP SUM | RECONSTRUCTION/RENOVATION OF COURT FACILITIES |  | CO-0264 |  |  | CITYWIDE COURTS ADA REHABILATION | 2022 | 38139 | 0 | 0 | 0 | 3829 | 4210 | 4331 | 13308 | 25678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264DCAS | REHABILITATION OF VARIOUS COURT FACILITES | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 000 | CO-0264 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | REHABILITATION OF VARIOUS COURT FACILITIES | REHABILITATION OF VARIOUS COURT FACILITIES | 2022 | 1774 | 0 | 31 | 0 | 0 | 0 | 1123 | 25407 | 26561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-ADA | VARIOUS COURTS BUILDINGS - ADA WORK | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 000 | CO-0264 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ACCESSIBILITY COMPLIANCE FOR DCAS MANAGED COURT BUILDINGS | 2022 | 3881 | 0 | 0 | 0 | 0 | 0 | 0 | 3881 | 3881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-HVAC | VARIOUS PUBLIC BUILDINGS - COURTS HVAC UPGRADES | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 000 | CO-0264 |  |  | VARIOUS PUBLIC BUILDINGS - COURTS HVAC UPGRADES | 2022 | 18346 | 0 | 0 | 0 | 0 | 0 | 1038 | 12208 | 13246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5 | VARIOUS PUBLIC BUILDINGS - COURTS FIRE/LIFE SAFETY | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 000 | CO-0264 |  |  | VARIOUS PUBLIC BUILDINGS - COURTS FIRE/LIFE SAFETY | 2022 | 27761 | 0 | 0 | 0 | 0 | 852 | 0 | 18312 | 19164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO-LL5FS | VARIOUS PUBLIC BUILDINGS - COURTS FIRE SUPPRESSION DETECTION | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 000 | CO-0264 |  |  | VARIOUS PUBLIC BUILDINGS - COURTS FIRE DETECTION | 2022 | 43362 | 0 | 0 | 0 | 0 | 0 | 2538 | 34977 | 37515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | F175-ES49 | Construction EMS 49 | NEW FACILITIES AND RENOVATIONS | 000 | F-0175 |  |  | CONSTRUCTION EMS 49 | 2022 | 4077 | 0 | 4326 | 0 | 0 | 0 | 0 | 0 | 4326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PT195-VAR | VARIOUS WATERFRONT PROPERTIES- RECONSTRUCTION | REHABILITATION OF WATERFRONT PROPERTIES | 000 | RE-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | VARIOUS | RECONSTRUCTION OF EXISTING PIERS & BULKHEADS. | 2022 | 39825 | 1778.71 | 0 | 0 | 0 | 0 | 0 | 1041 | 2819.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW335ASB4 | VARIOUS PUBLIC BUILDINGS- ENVIRONMENTAL REMEDIATION | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 000 | PW-0335 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REMEDIATE HAZARDOUS MATERIALS AT VARIOUS CITY SITES | 2022 | 10774 | 7450.46 | 0 | 0 | 0 | 64 | 1270 | 0 | 8784.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340EMAC | BOARD OF ELECTIONS | BOARD OF ELECTIONS MODERNIZATION | 000 | PW-0340 |  |  |  | 2022 | 18110 | 11478.89 | -67 | 0 | 0 | 0 | 6030 | 0 | 17441.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CJC | Community Justice Center | REHABILITATION OF CITY-OWNED OFFICE SPACE | 000 | PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | COMMUNITY JUSTICE CENTER | 2022 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77NG911 | DoITT Next Generation 911 and SDE Expansion | COMMUNICATIONS EQUIPMENT | 000 | PW-0077 PW-0326 |  |  |  | 2022 | 6188 | 3500.96 | 2687 | 0 | 0 | 0 | 0 | 0 | 6187.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SECAM | SECURITY CAMERAS - DCAS PUBLIC BUILDINGS | REHABILITATION OF CITY-OWNED OFFICE SPACE | 000 | PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SECURITY CAMERAS - DCAS PUBLIC BUILDINGS | 2022 | 4250 | 108.96 | 0 | 389 | 0 | 0 | 0 | 0 | 497.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCOMPDA2 | Comptroller's Office Data Center Replacement at 1 Centre St. | REHABILITATION OF CITY-OWNED OFFICE SPACE | 000 | PW-0077 |  |  | COMPTROLLER'S OFFICE DATA CENTER REPLACEMENT AT 1 CENTRE ST. | 2022 | 1283 | 0 | 195 | 971 | 0 | 0 | 0 | 0 | 1166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | CITYWIDE | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARGR4 | NYPA - SOLAR PARKING | DISTRIBUTED GENERATION | 000 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2022 | 26700 | 0 | 0 | 0 | 0 | 11000 | 0 | 0 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC17DRBR | DYKER INTERIOR RENOVATION | ESSENTIAL RECONSTRUCTION OF FACILITIES | 210 | LB-D104 LB-K001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DYKER INTERIOR RENOVATION | 2022 | 1000 | 0 | 0 | 0 | 0 | 1657 | 0 | 0 | 1657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC18CTRF | CORTELYOU ROOF & PLAZA | ESSENTIAL RECONSTRUCTION OF FACILITIES | 214 | LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CORTELYOU ROOF | 2022 | 850 | 0 | 0 | 0 | 1266 | 0 | 0 | 0 | 1266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC18FHSG | FT HAMILTON ROOF | ESSENTIAL RECONSTRUCTION OF FACILITIES | 210 | LB-D104 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FT HAMILTON ROOF | 2022 | 175 | 0 | 0 | 0 | 0 | 156 | 0 | 0 | 156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC18GSMR | GRAVESEND MEETING ROOM | ESSENTIAL RECONSTRUCTION OF FACILITIES | 215 | LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GRAVESEND MEETING ROOM | 2022 | 300 | 0 | 0 | 272 | 0 | 0 | 0 | 0 | 272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC18KBFS | KINGS BAY FIRE SAFETY | ESSENTIAL RECONSTRUCTION OF FACILITIES | 215 | LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | KINGSBAY FIRE SAFETY | 2022 | 250 | 0 | 0 | 25 | 202 | 0 | 0 | 0 | 227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC18KBHC | KINGS BAY BOILER | ESSENTIAL RECONSTRUCTION OF FACILITIES | 215 | LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | KINGSBAY BOILER | 2022 | 750 | 0 | 0 | 75 | 606 | 0 | 0 | 0 | 681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC19CHEL | Clinton Hill Wiring Upgrade | ESSENTIAL RECONSTRUCTION OF FACILITIES | 202 | LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CLINTON HILL WIRING UPGRADE. | 2022 | 150 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC20CTOP | CORTELYOU OUTDOOR PLAZA | ESSENTIAL RECONSTRUCTION OF FACILITIES | 214 | LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CORTELYOU OUTDOOR PLAZA | 2022 | 350 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC20MPMR | MCKINLEY PARK MEETING ROOM | ESSENTIAL RECONSTRUCTION OF FACILITIES | 210 | LB-D104 |  |  | MCKINLEY PARK MEETING ROOM | 2022 | 250 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC21MNRF | Macon Roof Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 203 | LB-D104 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | LIBRARY ROOF RENOVATION. | 2022 | 1500 | 0 | 0 | 0 | 150 | 1191 | 0 | 0 | 1341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC22CDEL | CLARENDON ELECTRICAL UPGRADE | ESSENTIAL RECONSTRUCTION OF FACILITIES | 211 | LB-D104 |  |  | TIME AND MATERIALS | 2022 | 374 | 0 | 0 | 0 | 0 | 374 | 0 | 0 | 374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC22JBIF | JAMAICA BAY INFRASTRUCTURE UPGRADE | ESSENTIAL RECONSTRUCTION OF FACILITIES | 208 | LB-D104 |  |  | JAMAICA BAY INFRASTRUCTURE | 2022 | 2000 | 0 | 0 | 200 | 1600 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC22KBIF | KINGS BAY INFRASTRUCTURE UPGRADE | ESSENTIAL RECONSTRUCTION OF FACILITIES | 208 | LB-D104 LB-0104 |  |  | INFRASTRUCTURE | 2022 | 1800 | 0 | 0 | 200 | 1600 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBC22SAIF | STONE AVENUE INFRASTRUCTURE UPGRADE | ESSENTIAL RECONSTRUCTION OF FACILITIES | 208 | LB-D104 |  |  | STONE AVENUE INFRASTRUCTURE UPGRADE | 2022 | 2400 | 0 | 0 | 200 | 2000 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBCENPH2 | CENTRAL RENOVATION - PHASE 2 | ESSENTIAL RECONSTRUCTION OF FACILITIES | 201 | LB-0104 LB-K001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CENTRAL RENOVATION - PHASE 2 | 2022 | 26345 | 0 | 0 | 0 | 0 | 27845 | 0 | 0 | 27845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBEM05SWR | SYSTEM-WIDE FUNDING | ESSENTIAL RECONSTRUCTION OF FACILITIES | 201 | LB-0104 LB-D104 LB-K001 LB-D001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RENOVATIONS /REHABILITTION/ACQUISTION/INITAL OUTFITTING - SYSTEM WIDECAPITAL INITIATIVES BROOKYN PUBLIC LIBRARY | 2022 | 43121 | 0 | 0 | 0 | 403 | 7096 | 784 | 6376 | 14659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBK16HLRF | Highlawn - Roof Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 211 | LB-K001 LB-D104 LB-0101 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HIGHLAWN - ROOF REPLACEMENT | 2022 | 988 | 0 | 0 | 0 | 904 | 0 | 0 | 0 | 904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBK16SCRF | SPRING CREEK ROOF REPLACEMENT | ESSENTIAL RECONSTRUCTION OF FACILITIES | 205 | LB-D104 LB-K001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SPRING CREEK ROOF REPLACEMENT | 2022 | 850 | 0 | 0 | 0 | 535 | 85 | 300 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBK22BRHC | Bay Ridge - Heating & Cooling Upgrade | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | LB-K001 LB-D104 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BAY RIDGE - HEATING & COOLING UPGRADE | 2022 | 1500 | 0 | 0 | 0 | 0 | 2750 | 0 | 0 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBM18NLOH | New Lots Overhaul | ESSENTIAL RECONSTRUCTION OF FACILITIES | 205 | LB-D104 LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW LOTS OVERHAUL | 2022 | 28405 | 0 | 0 | 0 | 0 | 8536 | 0 | 20000 | 28536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBM19CAOH | Canarsie Overhaul | ESSENTIAL RECONSTRUCTION OF FACILITIES | 218 | LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CANARSIE BRANCH OVERHAUL | 2022 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBM22WWBR | Walt Whitman Branch Overhaul | ESSENTIAL RECONSTRUCTION OF FACILITIES | 202 | LB-D104 LB-0101 LB-0108 LB-0104 |  |  | WALT WHITMAN BRANCH OVERHAUL | 2022 | 7412 | 0 | 0 | 0 | 0 | 250 | 0 | 7162 | 7412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBP18LDIN | LEONARD INFRASTRUCTURE UPGRADE | ESSENTIAL RECONSTRUCTION OF FACILITIES | 201 | LB-0101 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LEONARD INFRASTRUCTURE UPGRADE | 2022 | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBP18PCAD | PACIFIC ADA COMPLIANCE | ESSENTIAL RECONSTRUCTION OF FACILITIES | 206 | LB-D104 LB-0101 LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PACIFIC ADA COMPLIANCE | 2022 | 3500 | 0 | 0 | 0 | 0 | 1265 | 8076 | 0 | 9341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 038 | BROOKLYN PUBLIC LIBRARY | LBP21WIBR | WASHINGTON IRVING RENOVATION | ESSENTIAL RECONSTRUCTION OF FACILITIES | 204 | LB-0101 LB-0108 LB-D104 LB-0104 |  |  | WASHINGTON IRVING RENOVATION. | 2022 | 10811 | 0 | 0 | 0 | 0 | 14403 | 0 | 0 | 14403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-021 | Quad Rehab Project | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | QUAD REHAB PROJECT | 2022 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | BY001-022 | Lecture Halls Upgrades for Science Instruction | MISCELLANEOUS RECONSTRUCTION | 200 | HN-0300 |  |  | LECTURE HALLS UPGRADES FOR SCIENCE INSTRUCTION | 2022 | 2000 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | BY003-021 | Ingersoll Lecture Hall Upgrades | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 |  |  | BROOKLYN COLLEGE | 2022 | 2000 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | BY024-012 | Haitian Studies Institute Initial Outfitting | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TECHNOLOGY AND CAPITAL IMPROVEMENT | 2022 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | BY025-012 | Haitian Studies Institute Initial Outfitting | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TECHNOLOGY AND CAPITAL IMPROVEMENT | 2022 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | BY026-013 | Renovation of Ingersoll Extension | MISCELLANEOUS RECONSTRUCTION | 214 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION OF INGERSOLL EXTENSION | 2022 | 1000 | 5797.2 | 0 | 459 | 0 | 0 | 0 | 0 | 6256.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | BY031-017 | Electrical Upgrades | MISCELLANEOUS RECONSTRUCTION | 200 | HN-K300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ELECTRICAL UPGRADES | 2022 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | BY032-018 | ADA Upgrades for the Brooklyn College Student Center | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ADA UPGRADES FOR THE BROOKLYN COLLEGE STUDENT CENTER | 2022 | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | BY033-019 | Ingersoll Lecture Halls | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INGERSALL LECTURE HALLS | 2022 | 2000 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | BY034-019 | Restoration of Main Quad | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RESTORATION OF MAIN QUAD | 2022 | 724 | 0 | 0 | 0 | 0 | 724 | 0 | 0 | 724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | BY036-020 | Main Quad Restoration | MISCELLANEOUS RECONSTRUCTION | 200 | HN-K300 HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MAIN QUAD RESTORATION | 2022 | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | BY037-020 | Ingersoll Lecture Halls Upgrade | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 |  |  | INGERSOLL LECTURE HALLS UPGRADE | 2022 | 2000 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | CA034KG13 | Gas Booster Pump Upgrade | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D005 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GAS BOOSTER PUMP UPGRADE | 2022 | 127 | 28.36 | 99 | 0 | 0 | 0 | 0 | 0 | 127.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | CA234KG13 | Library Roof Replacement | MISCELLANEOUS RECONSTRUCTION | 200 | HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LIBRARY ROOF REPLACEMENT | 2022 | 550 | 674.56 | 6822 | 0 | 0 | 0 | 0 | 0 | 7496.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-021 | Library Building | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D004 |  |  | KINGSBOROUGH COMMUNITY COLLEGE | 2022 | 2000 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | KG001-022 | Kibbee Library & Media Center Renovations | MISCELLANEOUS RECONSTRUCTION | 200 | HN-K250 |  |  | KIBBEE LIBRARY & MEDIA CENTER RENOVATIONS | 2022 | 450 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | KG030-012 | Critical Maintenance A/P/U Buildings | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D002 HN-D004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CRITICAL MAINTENANCE A/P/U BUILDINGS | 2022 | 3000 | 3810.99 | 0 | 1100 | 0 | 0 | 0 | 0 | 4910.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | KG031-013 | Renovation of Pool Facilities | MISCELLANEOUS RECONSTRUCTION | 200 | HN-K250 HN-D002 HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION OF POOL FACILITIES | 2022 | 1000 | 405 | 0 | 0 | 2095 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | KG043-018 | Campus Roadway Improvements | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CAMPUS ROADWAYS UPGRADES | 2022 | 750 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | KG045-020 | Performing Arts Center Upgrades | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D002 HN-K250 HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PERFORMING ARTS CENTER UPGRADES | 2022 | 2000 | 0 | 7963 | 0 | 0 | 0 | 0 | 0 | 7963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | KG206-006 | T4 Roof Replacement | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D002 HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | T4 ROOF REPLACEMENT | 2022 | 1566 | 1870.66 | 1411 | 0 | 0 | 0 | 0 | 0 | 3281.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | ME001-022 | Athletic Center Improvements | MISCELLANEOUS RECONSTRUCTION | 200 | HN-0300 |  |  | ATHLETIC CENTER IMPROVEMENTS | 2022 | 2000 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | ME002-022 | Technology Equipment and Facility upgrades | DATA PROCESSING AND OTHER EQUIPMENT | 200 | HN-0300 |  |  |  | 2022 | 1500 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | ME018-005 | LIBRARY EXPANSION | MISCELLANEOUS RECONSTRUCTION | 200 | HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW | 2022 | 5230 | 9651.32 | 0 | 0 | 75 | 0 | 0 | 0 | 9726.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | ME027-011 | Carroll Street Building Upgrade | MISCELLANEOUS RECONSTRUCTION | 200 | HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ADDITIONAL FUNDING FOR UPGRADE OF BUILDING | 2022 | 1000 | 5000 | 0 | 219 | 0 | 0 | 0 | 0 | 5219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | ME031-013 | Virtual Desktop Infrastructure | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | VIRTUAL DESKTOP INFRASTRUCTURE #3 | 2022 | 1400 | 1352.88 | 0 | 47 | 0 | 0 | 0 | 0 | 1399.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | ME037-016 | College Prep School Classroom Improvements | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COLLEGE PREP SCHOOL CLASSROOM IMPROVEMENTS | 2022 | 65 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | ME038-016 | Child Development Center Upgrades | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CHILD DEVELOPMENT CENTER UPGRADES | 2022 | 1500 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | ME039-017 | Student Lounge Upgrades | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STUDENT LOUNGE UPGRADES | 2022 | 1500 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | ME040-018 | Differently-Abled Lab | MISCELLANEOUS RECONSTRUCTION |  | HN-K300 HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DIFERENTLY-ABLED LAB | 2022 | 1000 | 0 | 1550 | 0 | 0 | 0 | 0 | 0 | 1550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | ME041-018 | Art and Historic Space Renovation | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ART AND HISTORIC SPACE RENOVATION | 2022 | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | ME042-019 | Founder's Auditorium Renovation & Upgrades | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FOUNDER'S AUDITORIUM RENOVATION & UPGRADES | 2022 | 2250 | 0 | 0 | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | ME043-020 | Open Computer and Lab Digital Interactive Learning Spaces | MISCELLANEOUS RECONSTRUCTION | 200 | HN-K300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | OPEN COMPUTER AND LAB DIGITAL INTERACTIVE LEARNING SPACES | 2022 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | ME044-020 | Athletic Center | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 HN-K300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ATHLETIC CENTER | 2022 | 2000 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | NY008-010 | Student Lounge/Eating/Study Space Build-out | MISCELLANEOUS RECONSTRUCTION | 202 | HN-K300 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | STUDENT LOUNGE/EATING/STUDY SPACE BUILD-OUT | 2022 | 734 | 0 | 0 | 0 | 0 | 734 | 0 | 0 | 734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | NY012-011 | Initial Outfitting of the Biological Science Labs | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INITIAL OUTFITTING OF THE BIOLOGICAL SCIENCE LABS | 2022 | 217 | 108.93 | 0 | 0 | 91 | 0 | 0 | 0 | 199.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | NY013-012 | Network Upgrades | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NETWORK UPGRADES | 2022 | 1500 | 1471.62 | 0 | 114 | 37 | 0 | 0 | 0 | 1622.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | NY018-014 | Dental Hygiene Facilities Upgrade | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DENTAL HYGIENE FACILITIES UPGRADE | 2022 | 400 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | NY019-015 | Fabrication Laboratory | MISCELLANEOUS RECONSTRUCTION | 200 | HN-K300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FABRICATION LABORATORY | 2022 | 400 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | NY020-015 | Academic Learning Center Renovations | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ACADEMIC LEARNING CENTER RENOVATIONS | 2022 | 400 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | NY021-016 | Academic Learning Center Renovations and Equipment | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ACADEMIC LEARNING CENTER RENOVATIONS & EQUIPMENT | 2022 | 1290 | 0 | 0 | 0 | 1290 | 0 | 0 | 0 | 1290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | NY024-018 | Exterior Space Improvements | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | UPGRADE EXTERIOR SPACES AT NEW YORK CITY TECH | 2022 | 500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | NY025-018 | NYC College of Technolgy Pearl Street Building Renovation | MISCELLANEOUS RECONSTRUCTION | 200 | HN-D300 HN-0300 HN-D004 HN-K002 HN-K300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PEARL STREET BUILDING RENOVATION | 2022 | 2500 | 1761.1 | 8586 | 0 | 0 | 0 | 0 | 0 | 10347.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | NY031-022 | NYCT Stem Lab Build-out on 3rd Fl of Vorhees & 4th Fl Namm | MISCELLANEOUS RECONSTRUCTION | 200 | HN-K300 |  |  | BUILDOUT OF STEM CELL LABS FOR VOORHEES & NAMM BUILDINGS | 2022 | 400 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | NY034-022 | Physics Lab Renovation | MISCELLANEOUS RECONSTRUCTION | 200 | HN-0300 |  |  | PHYSICS LAB RENOVATION | 2022 | 1100 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG02 | HVAC Repair/Replacement - Sandy Related | MISCELLANEOUS RECONSTRUCTION | 200 | HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HVAC REPAIR/REPLACEMENT - SANDY RELATED | 2022 | 285 | 28.41 | 0 | 486 | 0 | 0 | 0 | 0 | 514.41 | 255.69 | 0 | 0 | 0 | 0 | 0 | 0 | 255.69
20220309 | BROOKLYN | 042 | CITY UNIVERSITY | SAND-KG03 | Marina Reconstruction Kingsborough CC - Brooklyn | MISCELLANEOUS RECONSTRUCTION | 200 | HN-K250 HN-0206 HN-D002 HN-D004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MARINA RECONSTRUCTION | 2022 | 2592 | 42.5 | 6500 | 0 | 0 | 0 | 0 | 0 | 6542.5 | 382.5 | 4139 | 0 | 0 | 0 | 0 | 0 | 4521.5
20220309 | BROOKLYN | 056 | POLICE DEPARTMENT | PO7911FR | 11 FRONT STR RENOVATION | POLICE FACILITIES | 200 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | 11 FRONT STR RENOVATION | 2022 | 3747 | 5856.94 | 193 | 0 | 0 | 0 | 0 | 0 | 6049.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAHS | FIRING RANGE RECONSTRUCTION AT CONEY ISLAND | POLICE FACILITIES | 200 213 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 2556 MCDONALD AV, BRROKLYN NY | RANGE RECONSTRUCTION | 2022 | 2591 | 443.2 | 0 | 6167 | 0 | 0 | 0 | 0 | 6610.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKG | FBF AVIATION AND DRIVER TRAINING UNIT ROOF REHABILITATION | POLICE FACILITIES | 200 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SCOPE DESCRIPTION | 2022 | 2756 | 0 | 0 | 2756 | 0 | 0 | 0 | 0 | 2756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKJ | REHABILITATION OF 67TH PCT ELEVATOR | POLICE FACILITIES | 200 | PO-0079 |  |  | ESTIMATE | 2022 | 1500 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKR | 88TH PCT ROOF REPLACEMENT | POLICE FACILITIES | 200 | PO-0079 |  |  | ESTIMATE | 2022 | 600 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKS | 81ST PCT ROOF REPLACEMENT | POLICE FACILITIES | 200 | PO-0079 |  |  | ESTIMATE | 2022 | 600 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKT | 60TH PCT ROOF REPLACEMENT | POLICE FACILITIES | 200 | PO-0079 |  |  | ESTIMATE | 2022 | 600 | 0 | 200 | 400 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79BMAKW | 245 GLENMORE ROOF REPLACEMENT | POLICE FACILITIES | 200 | PO-0079 |  |  | ESTIMATE | 2022 | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 056 | POLICE DEPARTMENT | PO79HCFDR | HARBOR CHARLIE FLOATING DOCKS RENOVATION | POLICE FACILITIES | 200 | PO-0079 |  |  | SCOPE OF WORK | 2022 | 4150 | 0 | 650 | 3500 | 0 | 0 | 0 | 0 | 4150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 056 | POLICE DEPARTMENT | PODMTRPE | Mounted Unit facility betterment | POLICE FACILITIES | 200 | PO-D079 PO-0079 |  |  | ESTIMATE | 2022 | 104 | 0 | 123 | 0 | 0 | 0 | 0 | 0 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 056 | POLICE DEPARTMENT | PO-KVEST | PEOPLE'S PRECINCTS VESTIBULE REDESIGN | POLICE FACILITIES | 200 | PO-K079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RENOVATION | 2022 | 1000 | 227.67 | 772 | 0 | 0 | 0 | 0 | 0 | 999.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD3 | POLICE SERVICE AREA 1 (PSA1) | POLICE FACILITIES | 200 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 2860 WEST 23RD STREET BROOKLYN | ELECTRICAL REHABILITATION | 2022 | 322 | 6.15 | 27 | 0 | 0 | 0 | 0 | 0 | 33.15 | 55.37 | 234 | 0 | 0 | 0 | 0 | 0 | 289.37
20220309 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD4 | FLOYD BENNETT FIELD ELECTRICAL | POLICE FACILITIES | 200 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ELECTRICAL REHABILITATION | 2022 | 575 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 517 | 0 | 0 | 0 | 0 | 0 | 517
20220309 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDCD5 | TRANSIT DISTRICT 34 ELECTRICAL | POLICE FACILITIES | 200 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ELECTRICAL REHABILITATION | 2022 | 1058 | 7.39 | 99 | 0 | 0 | 0 | 0 | 0 | 106.39 | 66.53 | 885 | 0 | 0 | 0 | 0 | 0 | 951.53
20220309 | BROOKLYN | 056 | POLICE DEPARTMENT | SANDWARE | 23RD STR WAREHOUSE RECONSTRUCTION | POLICE FACILITIES | 200 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RECONSTRUCTION | 2022 | 8434 | 0 | 204 | 1358 | 0 | 0 | 0 | 0 | 1562 | 0 | 1832 | 12215 | 0 | 0 | 0 | 0 | 14047
20220309 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN701 | FDNY - LED LIGHTING UPGRADE AT 14 FDNY FACILITIES | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 | PROJECT DELAYED RESULTING FROM CONTRACTOR DEFAULT |  | FDNY - LED LIGHTING UPGRADE AT 14 FDNY FACILITIES | 2022 | 1084 | 797.63 | 656 | 0 | 0 | 0 | 0 | 0 | 1453.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN703 | FDNY - DESIGN & INSTALLATION OF 37 KW SOLAR SYSTEM AT EC332 | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FDNY - DESIGN & INSTALLATION OF 37 KW SOLAR PHOTOVOLTAIC SYSTEM AT EC3332 | 2022 | 235 | 44.29 | 518 | 0 | 0 | 0 | 0 | 0 | 562.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 057 | FIRE DEPARTMENT | ACEFDN801 | FDNY - Solar Photo-voltaic system at EMS 58 | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SOLAR PHOTO-VOLTAIC SYSTEM AT EMS 58 | 2022 | 257 | 36.61 | 0 | 221 | 0 | 0 | 0 | 0 | 257.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 057 | FIRE DEPARTMENT | F175FASBK | Fire Alarm System at Brooklyn CO | NEW FACILITIES AND RENOVATIONS | 209 | F-0175 |  |  | FIRE ALARM SYSTEM AT BROOKLYN CO | 2022 | 2171 | 0 | 171 | 2000 | 0 | 0 | 0 | 0 | 2171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 057 | FIRE DEPARTMENT | F175MC218 | Multi-Component Renovations - EC218 | NEW FACILITIES AND RENOVATIONS | 204 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MULTI-COMPONENT RENOVATIONS - EC218 | 2022 | 5598 | 686.48 | 7006 | 0 | 0 | 0 | 0 | 0 | 7692.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 057 | FIRE DEPARTMENT | F175MC224 | Multi-Component Renovations- EC224 | NEW FACILITIES AND RENOVATIONS | 202 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FLOOR, KITCHEN L-OHD - EC224 | 2022 | 2282 | 9527.11 | 2501 | 0 | 0 | 0 | 0 | 0 | 12028.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175W245 | WINDOW REPLACEMENT - EC245 | NEW FACILITIES AND RENOVATIONS | 213 | F-D175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WINDOW REPLACEMENT - EC245 | 2022 | 750 | 261.46 | 488 | 0 | 0 | 0 | 0 | 0 | 749.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175W248 | WINDOW REPLACEMENT - EC248 | NEW FACILITIES AND RENOVATIONS | 217 | F-D175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WINDOW REPLACEMENT - EC248 | 2022 | 375 | 160.9 | 214 | 0 | 0 | 0 | 0 | 0 | 374.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 057 | FIRE DEPARTMENT | FD175W330 | Window Replacement - EC330 | NEW FACILITIES AND RENOVATIONS | 211 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WINDOW REPLACEMENT - EC330 | 2022 | 582 | 616.84 | 110 | 0 | 0 | 0 | 0 | 0 | 726.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 068 | ADMIN FOR CHILDREN'S SERVICES | JJZROSSLB | THE CROSSROADS JUVENILE CENTER - LIBRARY RENOVATION | SOCIAL SERVICE BUILDINGS | 216 | CS-K001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION OF LIBRARY ROOM AND EQUIPMENT PURCHASE | 2022 | 250 | 73.05 | 0 | 0 | 0 | 100 | 0 | 0 | 173.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112HWCR | HELP WOMEN'S CENTER ROOF | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | HELP WOMEN'S CENTER ROOF | 2022 | 780 | 60 | 300 | 436 | 0 | 0 | 0 | 0 | 796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112LFER | LINDEN MEN'S SHELTER - ELEVATOR REPLACEMENT | SHELTERS FOR HOMELESS INDIVIDUALS | 205 | HH-0112 |  |  | LINDEN MEN'S SHELTER - ELEVATOR REPLACEMENT | 2022 | 530 | 80 | 0 | 0 | 450 | 0 | 0 | 0 | 530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112LINT | 85 LEXINGTON AVE BATHROOM RECONSTRUCTION | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | BATHROOM RECONSTRUCTION | 2022 | 504 | 0 | 42 | 0 | 462 | 0 | 0 | 0 | 504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112LMEP | LINDEN BOILER RECONSTRUCTION | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | BOILER RECONSTRUCTION | 2022 | 1950 | 0 | 300 | 700 | 950 | 0 | 0 | 0 | 1950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PAFL | PAMOJA HOUSE FLOOR | SHELTERS FOR HOMELESS INDIVIDUALS | 203 | HH-0112 |  |  | RECONSTRUCT DORM FLOORS | 2022 | 1475 | 125 | 0 | 500 | 850 | 0 | 0 | 0 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PJRR | PAMOJA HOUSE - ROOF REPLACEMENT | SHELTERS FOR HOMELESS INDIVIDUALS | 203 | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PAMOJA HOUSE - ROOF REPLACEMENT | 2022 | 1999 | 4807.03 | 871 | 0 | 561 | 2550 | 0 | 0 | 8789.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PREK | RENOVATION AND IMPROVEMENTS TO THE PARK SLOPE ARMORY | SHELTERS FOR HOMELESS INDIVIDUALS | 206 | HH-D025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PARK SLOPE ARMORY-REHABILITATION OF ROOMS FOR PRE-K PROGRAM | 2022 | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH112PSBH | PARK SLOPE - BATHROOMS | SHELTERS FOR HOMELESS INDIVIDUALS | 206 | HH-0112 |  |  | PARK SLOPE - BATHROOMS | 2022 | 0 | 0 | 0 | 150 | 0 | 1500 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115BFRR | Bushwick Family Roof Replacement | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0115 |  |  | ROOF REPLACEMENT | 2022 | 2600 | 200 | 0 | 2000 | 1800 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115BINT | BUSHWICK FAMILY FACADE RECONSTRUCTION | SHELTERS FOR HOMELESS FAMILIES |  | HH-0112 |  |  | RECONSTRUCT FACADE | 2022 | 1920 | 0 | 0 | 160 | 0 | 1000 | 760 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115FAFA | FLATLANDS - FIRE ALARM UPGRADE | SHELTERS FOR HOMELESS FAMILIES | 218 | HH-0115 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FLATLANDS - FIRE ALARM UPGRADE | 2022 | 938 | 94 | 611 | 0 | 0 | 0 | 0 | 0 | 705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115FBME | FANNIE BARNES BOILER RECONSTRUCTION | SHELTERS FOR HOMELESS FAMILIES | 216 | HH-0112 |  |  | RECON BOILER | 2022 | 1008 | 0 | 500 | 424 | 0 | 0 | 0 | 0 | 924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115FLRF | FLATLANDS ROOF REPLACEMENT | SHELTERS FOR HOMELESS FAMILIES | 218 | HH-0115 |  |  | ROOF REPLACEMENT AT FLATLANDS FAMILY RESIDENCE | 2022 | 1950 | 150 | 500 | 3553 | 0 | 0 | 0 | 0 | 4203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115MMEP | WAYSIDE MACDONOUGH BOILER RECONS | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0115 |  |  | RECONSTRUCT BOILER | 2022 | 300 | 25 | 0 | 275 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115RMCX | ROSE MCCARTHY - WINDOW REPLACEMENT AND EXTERIOR RECONSTRUCT | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ROSE MCCARTHY - WINDOW REPLACEMENT AND EXTERIOR RECONSTRUCTION | 2022 | 0 | 115 | 0 | 483 | 0 | 0 | 0 | 0 | 598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115SAEU | FANNIE BARNES EXTERIOR UPGRADE | SHELTERS FOR HOMELESS FAMILIES | 216 | HH-0115 |  |  | FANNIE BARNES EXTERIOR UPGRADE | 2022 | 3900 | 300 | 0 | 500 | 3100 | 0 | 0 | 0 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115SEXT | STOCKHOLM FAMILY CENTER - ROOF AND FACADE RECONSTRUCTION | SHELTERS FOR HOMELESS FAMILIES |  | HH-0112 |  |  | ROOF AND FACADE | 2022 | 1008 | 0 | 0 | 84 | 924 | 0 | 0 | 0 | 1008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HH115STEP | STOCKHOLM FAMILY CENTER -BOILER RECONSTRUCTION | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 |  |  | BOILER RECON | 2022 | 1152 | 96 | 500 | 556 | 0 | 0 | 0 | 0 | 1152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN001 | BROOKLYN NEIGHBORHOOD IMPROVEMENT DIST.-BEDFORD AVE. RENOVAT | SHELTERS FOR HOMELESS FAMILIES |  | HH-D025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BROOKLYN NEIGHBORHOOD IMPROVEMENT DIST.-BEDFORD AVE. RENOVATION | 2022 | 300 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN002 | RENOVATION OF BEDFORD ATLANTIC ARMORY INTO RECREATIONAL CTR. | SHELTERS FOR HOMELESS FAMILIES | 208 | HH-D025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RENOVATION OF BEDFORD ATLANTIC ARMORY INTO RECREATIONAL CTR. | 2022 | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | HHCN003 | BEDFORD ATLANTIC ARMORY ATHLETIC CENTER | SHELTERS FOR HOMELESS INDIVIDUALS | 209 | HH-D112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BEDFORD ATHLETIC ARMORY ATHLETIC CENTER | 2022 | 250 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS3 | Solar PV system - Flatlands Residence | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 201 | PU-0025 |  |  | SOLAR PV SYSTEM - FLATLANDS RESIDENCE LOCATED AT 108-75 AVENUE D, BROOKLYN | 2022 | 339 | 0 | 309 | 0 | 0 | 0 | 0 | 0 | 309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25ENY | East New York Office, 2440 Fulton Street, Brooklyn | SOCIAL SERVICES BUILDINGS | 200 | HR-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCTION AT 2440 FULTON STREET, BROOKLYN. | 2022 | 52924 | 0 | 0 | 3553 | 10314 | 13160 | 0 | 0 | 27027 | 0 | 0 | 1837 | 5332 | 6804 | 0 | 0 | 13973
20220309 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25FOSF2 | Initial Outfitting of 102-50 Foster Avenue (Warehouse Space) | SOCIAL SERVICES BUILDINGS | 214 | HR-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2022 | 501 | 0 | 0 | 0 | 0 | 256 | 0 | 0 | 256 | 0 | 0 | 0 | 0 | 245 | 0 | 0 | 245
20220309 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25FOST2 | Construction at 102-50 Foster Ave to accomodate warehouses | SOCIAL SERVICES BUILDINGS | 214 | HR-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2022 | 7539 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 1489 | 0 | 1489
20220309 | BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | HRCNBDST | Bedford Stuyvesant MSC Boiler Replacement, 1958 Fulton St | SOCIAL SERVICES BUILDINGS | 203 | HR-D002 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 1958 FULTON ST//1001 HERKIMER ST BK 11233-3104 | EXTERIOR RENOVATIONS | 2022 | 1070 | 0 | 0 | 1070 | 0 | 0 | 0 | 0 | 1070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 125 | DEPARTMENT FOR THE AGING | AGREDHOOK | PB: -Red Hook Senior Center -- Funding for senior center | DEPARTMENT FOR THE AGING BUILDING RECONSTRUCTION | 200 | AG-D001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PB: -RED HOOK SENIOR CENTER -- FUNDING FOR SENIOR CENTER | 2022 | 1260 | 0 | 0 | 0 | 0 | 0 | 1260 | 0 | 1260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230GLOV | NYA - Glovers Reef Exhibit Tank Reconstruction | ESSENTIAL RECONSTRUCTION OF FACILITIES | 213 | PV-D230 PV-K230 PV-0230 |  |  | CONSTRUCTION | 2022 | 4800 | 0 | 0 | 0 | 0 | 2500 | 2300 | 0 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV230-SEA | WCS - New York Aquarium - Sea Cliffs Exhibit | ESSENTIAL RECONSTRUCTION OF FACILITIES | 213 | PV-0230 PV-K230 PV-D230 PV-D467 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NY AQUARIUM SEA CLIFF EXHIBIT | 2022 | 1000 | 0 | 0 | 0 | 9686 | 0 | 0 | 0 | 9686 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000
20220309 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AFAR | BMA - Brooklyn Museum - African Art Gallery Renovations | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-D235 PV-0235 PV-K235 |  | 200 EASTERN PARKWAY, BROOKLYN, NY | AFRICAN ART GALLERY IN BROOKLYN MUSEUM. | 2022 | 3711 | 0 | 0 | 0 | 0 | 6393 | 4119 | 0 | 10512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235AMER | BMA - Brooklyn Museum - American Gallery Renovations | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-0235 |  |  | CONSTRUCTION | 2022 | 9000 | 0 | 0 | 0 | 0 | 5000 | 45000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV235EDUC | BMA - Brooklyn Museum - Education Space | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-K235 PV-D235 PV-0235 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DESIGN AND CONSTRUCTION OF EDUCATION SPACE IN BROOKLYN MUSEUM'S HALL | 2022 | 3040 | 0 | 0 | 0 | 3520 | 0 | 2505 | 0 | 6025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236AUDI | BBG - Auditorium Renovations | ESSENTIAL RECONSTRUCTION OF FACILITIES | 209 | PV-K236 PV-D236 PV-0236 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 1000 WASHINGTON AVENUE, BROOKLYN NY | BBG AUDITORIUM RENOVATION: UPGRADES TO THE 280-SEAT PUBLIC THEATER. | 2022 | 1878 | 0 | 0 | 0 | 0 | 3000 | 2489 | 0 | 5489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236BCSG | BBG - Brooklyn Botanic Garden - Sustainable Gardening Center | ESSENTIAL RECONSTRUCTION OF FACILITIES | 208 209 | PV-D236 PV-K236 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BROOKLYN BOTANIC GARDEN: BROOKLYN CENTER FOR SUSTAINABLE GARDENING | 2022 | 1500 | 0 | 0 | 0 | 0 | 2183 | 3101 | 0 | 5284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236-NSY | BBG - North Service Yard | ESSENTIAL RECONSTRUCTION OF FACILITIES | 209 | PV-D236 |  |  | CONSTRUCTION | 2022 | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 0 | 3100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV236ROSE | BBG -Brooklyn Botanic Garden - Accessibility Improvements | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-D236 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 1000 WASHINGTON, BROOKLYN | SITE WIDE AND BUILDING WIDE AADA IMPROVEMENTS. | 2022 | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262HOLD | BCM - Brooklyn Children's Museum - HOLD | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-D262 PV-0262 |  |  | TBD | 2022 | 0 | 0 | 0 | 0 | 0 | 0 | 189 | 3200 | 3389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV262HVAC | BCM - Brooklyn Children's Museum - HVAC | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-K262 PV-D262 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BROOKLYN CHILDREN'S MUSEUM - HVAC | 2022 | 1000 | 0 | 0 | 0 | 0 | 4545 | 0 | 0 | 4545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264-PJS | BAM - Peter J. Sharp Infrastructure Improvments Escalator | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-D264 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BAM INFRASTRUCURE IMPROVEMENTS AT PJS INCLUDING ESCALATOR | 2022 | 525 | 0 | 0 | 0 | 525 | 0 | 0 | 0 | 525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV264ROSE | BAM - Rose Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-K264 PV-D264 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BAM - ROSE RENOVATION | 2022 | 7000 | 0 | 0 | 0 | 0 | 4500 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467BKLN | DCA - Brooklyn Fund | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-0467 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DCA FUNDS TO SUPPORT NON-PROFIT CULTURAL ORGANIZATIONS IN BROOKLYN | 2022 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467DBCD | DBCD South Site Cultural Condo | ESSENTIAL RECONSTRUCTION OF FACILITIES | 202 | PV-0467 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CONSTRUCTION | 2022 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467SWBB | Spaceworks Brooklyn Bridge Park | ESSENTIAL RECONSTRUCTION OF FACILITIES | 202 | PV-0467 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 334 FURMAN STREET, BROOKLYN, NY | RECONSTRUCTION OF TWO FLOORS AT 334 FURMAN STREET IN BROOKLYN BRIDGE PARK FOR ARTIST STUDIOS AND REHEARSAL SPACE. | 2022 | 6200 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMNSITEA | BAM Cultural District - North Site Condemnation | MISCELLANEOUS | 202 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BAM LDC - CONDEMNATION OF LIQUOR STORE ON NORTH SITE AND ASSOCIATED COSTS | 2022 | 5128 | 2199.12 | 0 | 0 | 0 | 187 | 0 | 0 | 2386.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAMPARK | BAM Park Renovation | MISCELLANEOUS | 202 | ED-D075 ED-0384 ED-D380 ED-K075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BAM PARK RENOVATION | 2022 | 300 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BAT4LAN | BAT Pier 4: Ferry Landing Rehabilitation | WATERFRONT DEVELOPMENT | 207 | ED-0373 ED-0409 ED-0401 ED-0404 ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FERRY LANDING REHABILITATION | 2022 | 500 | 3332.65 | 4147 | 3500 | 3500 | 4753 | 2000 | 306 | 21538.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATANCHOR | BAT Anchor Tenant Strategy | INDUSTRIAL DEVELOPMENT | 200 | ED-0373 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BAT ANCHOR TENANT STRATEGY - 100K JOBS PLAN | 2022 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 15405 | 15405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATBEYOND | BAT New Needs | INDUSTRIAL DEVELOPMENT | 200 | ED-0075 ED-0373 ED-K075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BAT NEW NEEDS | 2022 | 100000 | 119099.48 | 2226 | 373 | 2333 | 2000 | 2000 | 1852 | 129883.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATIMPRO | BAT Improvements | INDUSTRIAL DEVELOPMENT | 200 | ED-0373 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BAT IMPROVEMENTS | 2022 | 3152 | 12600.84 | 4386 | 4000 | 4600 | 0 | 0 | 0 | 25586.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATLOGIST | Brooklyn Army Terminal Logistics Center | INDUSTRIAL DEVELOPMENT | 200 | ED-0373 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BAT LOGISTICS CENTER | 2022 | 50000 | 0 | 0 | 0 | 0 | 0 | 26691 | 3309 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATPLUGIN | BAT Plug-In Industrial Strategy | INDUSTRIAL DEVELOPMENT | 200 | ED-0373 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BAT PLUG-IN INDUSTRIAL STRATEGY - 100K JOBS PLAN | 2022 | 13000 | 0 | 0 | 2000 | 7500 | 3000 | 500 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BATRPZDEP | BAT RPZ Installation - DEP Compliance | INDUSTRIAL DEVELOPMENT | 200 | ED-0373 |  |  | RPZ INSTALL | 2022 | 3600 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BCTMCABLE | Brooklyn Cruise Terminal - Mobile Cable Positioning Device | MISCELLANEOUS | 200 | ED-K409 |  |  | MOBILE CABLE POSITIONING DEVICE FOR BROOKYN CRUISE TERMINAL | 2022 | 750 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BCTPIER11 | Brooklyn Cruise Terminal Pier 11 | MISCELLANEOUS | 200 | ED-D075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BROOKLYN CRUISE TERMINAL PIER 11 | 2022 | 3000 | 938.32 | 0 | 0 | 0 | 0 | 0 | 347 | 1285.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKBRESP | Brooklyn Bridge Esplanade | MISCELLANEOUS | 200 | ED-M075 ED-0075 ED-D075 ED-0409 |  |  | BROOKLYN BRIDGE ESPLANADE | 2022 | 20000 | 0 | 17918 | 0 | 0 | 0 | 0 | 0 | 17918 | 1511.02 | 11545 | 0 | 0 | 0 | 0 | 0 | 13056.02
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCRUISE | Brooklyn Cruise Terminal Substructre Rehab | PORT DEVELOPMENT | 206 | ED-K409 ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BROOKLYN CRUISE TERMINAL SUBSTRUCTRE REHAB | 2022 | 5000 | 0 | 0 | 0 | 0 | 2700 | 0 | 836 | 3536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BKCTPIER | Brooklyn Cruise Terminal Pier 12 Substructure Rehab | MISCELLANEOUS | 200 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BROOKLYN CRUISE TERMINAL PIER 12 SUBSTRUCTURE REHAB | 2022 | 1500 | 3831.28 | 332 | 0 | 0 | 0 | 0 | 0 | 4163.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNY5THST | BNYDC 5th Street Reconstruction | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BNYDC 5TH STREET RECONSTRUCTION | 2022 | 1233 | 0 | 1750 | 0 | 0 | 0 | 0 | 0 | 1750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNY910SBB | BNYDC Berths 9, 10 and Small Boat Basin Structural Work | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | RECONSTRUCTION OF THE STRUCTURAL FOUNDATIONS OF BERTHS 9, 10 AND THE SMALL BOAT BASIN, LOCATED AT THE BROOKLYN NAVY YARD, | 2022 | 46047 | 1577 | 10000 | 23000 | 15251 | 14999 | 0 | 0 | 64827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB131RM | BNYDC Building 131 Asbestos and Mold Remediation - 1st Floor | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REMEDIATION OF MOLD AND ASBESTOS CONDITIONS ON THE 1ST FLOOR OF BUILDING 131 AT THE BROOKLYN NAVY YARD | 2022 | 1600 | 0 | 1600 | 900 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB280RF | BNYDC Building 280 Roof | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FULL REPLACEMENT OF THE ROOF AT BUILDING 280, LOCATED IN THE BROOKLYNNAVY YARD | 2022 | 1500 | 0 | 2500 | 2857 | 0 | 0 | 0 | 0 | 5357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB3SUBD | BNYDC Building 3 Subdivision | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SUBDIVISION OF THE 7TH AND 9TH FLOORS OF BUILDING 3, LOCATED AT THE BROOKLYN NAVY YARD | 2022 | 3476 | 0 | 2976 | 500 | 0 | 0 | 0 | 0 | 3476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYB74DEM | BNYDC Demolition of Building 74 and Parking Lot | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DEMOLITION OF BUILDING 74 AT THE BROOKLYN NAVY YARD AND CONSTRUCTION OF A NEW PARKING LOT IN ITS FOOTPRINT | 2022 | 3500 | 0 | 1000 | 2500 | 0 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBD132 | BNYDC Building 132 Roof Rehabilitation | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | BNYDC BUILDING 132 | 2022 | 1055 | 45.75 | 0 | 1367 | 0 | 0 | 0 | 0 | 1412.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBDELEV | BNYDC Elevator Reconstruction and Replacement | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 ED-K319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BROOKLYN NAVY YARD-WIDE REPAIRS AND RECONSTRUCTION OF BUILDING ELEVATORS | 2022 | 16500 | 274.43 | 5132 | 9207 | 0 | 0 | 0 | 0 | 14613.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBLD292 | BNYDC Building 292 Roof Replacement | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DESIGN AND RECONSTRUCTION OF ROOFING SSYTEM FOR BUILDING 292 IN BROOKLYN NAVY YARD. | 2022 | 1499 | 1443.44 | 56 | 0 | 0 | 0 | 0 | 0 | 1499.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYBLDG50 | BNYDC Building 50 Roof Rehabilitation | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | BNYDC BUILDING 50 ROOF REPLACEMENT | 2022 | 1055 | 1055 | 337 | 0 | 0 | 0 | 0 | 0 | 1392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYCUNY | BNYDC - CUNY Building 3 7th Floor Buildout | INDUSTRIAL DEVELOPMENT | 200 | ED-D319 |  |  | CONSTRUCTION OF NEW CUNY SPACE AT BNY ON THE 7TH FLOOR OF BUILDING 3 | 2022 | 3000 | 0 | 1500 | 1500 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYDCSUBF | BNYDC Con Edison Substation F Upgrade | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | POWER SUBSTATION UPGRADE | 2022 | 4232 | 621.82 | 1000 | 5050 | 1810 | 0 | 0 | 0 | 8481.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYDCWELD | BNYDC Welding Lab | INDUSTRIAL DEVELOPMENT | 200 | ED-D319 ED-K319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DESIGN AND CONSTRUCTION OF A WELDING LAB AT THE BROOKLYN NAVY YARD | 2022 | 3000 | 435.42 | 0 | 2565 | 0 | 0 | 0 | 0 | 3000.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYELEV22 | BNYDC Building 22 Elevator Modernization | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BNYDC BUILDING 22 ELEVATOR MODERNIZATION | 2022 | 276 | 192.8 | 83 | 0 | 0 | 0 | 0 | 0 | 275.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYFNCLIN | BNYDC Fence Line Restructuring | INDUSTRIAL DEVELOPMENT | 200 | ED-D319 ED-0319 ED-K319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BNY FENCE LINE RESTRUCTURING - VARIOUS LOCATIONS | 2022 | 1926 | 426 | 4050 | 2750 | 0 | 0 | 0 | 0 | 7226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYHARBOR | BNYDC PS 331 NY Harbor School Trailer Installation | INDUSTRIAL DEVELOPMENT | 200 | ED-K319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NY HARBOR SCHOOL TRAILER INSTALLATION | 2022 | 242 | 0 | 242 | 0 | 0 | 0 | 0 | 0 | 242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYHITN | BNYDC HITN Eco-Rooftop Production Studio | INDUSTRIAL DEVELOPMENT | 200 | ED-K319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BNYDC HISPANIC INFORMATION AND TELECOMMUNICATION NETWORK ECO ROOFTOP PRODUCTION STUDIO | 2022 | 500 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-BD | BNYDC Infrastructure Building Rehab | INDUSTRIAL DEVELOPMENT | 202 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BNYDC INFRASTRUCTURE BUILDING REHAB | 2022 | 4207 | 2365.58 | 8382 | 29385 | 61982 | 86259 | 61875 | 42054 | 292302.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINFRAW | BNYDC Infrastructure - Water Projects | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WEST 125TH STREET/MANHATTANVILLE | 2022 | 32950 | 32388.83 | 0 | 2497 | 1000 | 1000 | 3000 | 0 | 39885.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-ST | BNYDC Infrastructure Steam | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BNYDC INFRASTRUCTURE STEAM | 2022 | 19169 | 0 | 0 | 0 | 5200 | 3000 | 5282 | 0 | 13482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYINF-WF | BNYDC Infrastructure Waterfront | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BNYDC INFRASTRUCTURE WATERFRONT | 2022 | 29790 | 16806.64 | 1436 | 9491 | 3000 | 3000 | 3000 | 19718 | 56451.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYLIGHT | BNYDC Lighting Replacement | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BNYDC LIGHTING REPLACEMENT | 2022 | 5000 | 0 | 500 | 4000 | 500 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYLL11 | BNYDC Local Law 11 Compliance - Buildings 3 and 5 | MISCELLANEOUS | 200 | ED-0319 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | LOCAL LAW 11 COMPLIANCE - BUILDINGS 3 AND 5 | 2022 | 6390 | 1556.04 | 3334 | 1500 | 0 | 0 | 0 | 0 | 6390.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMACRO | BNYDC Macro Sea | MISCELLANEOUS | 200 | ED-D319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MACRO SEA DESIGN AND FABRICATION CENTER, A TENANT OF THE GREEN MANUFACTURING CENTER AT THE BROOKLYN NAVY YARD | 2022 | 7000 | 6920.27 | 0 | 0 | 0 | 0 | 0 | 80 | 7000.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYMWBEEI | BNYDC MWBE Equity Incubator | INDUSTRIAL DEVELOPMENT | 200 | ED-K319 ED-D319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BNYDC MWBE EQUITY INCUBATOR DESIGN AND CONSTRUCTION | 2022 | 2000 | 0 | 1000 | 2000 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYROOF77 | BNYDC - Building 77 Roof | INDUSTRIAL DEVELOPMENT | 200 | ED-D319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BUILDING 77 ROOF | 2022 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYRPZBFL | BNYDC Installation of RPZ Backflow Devices | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NYCDEP REQUIRES EACH PERIMETER SERVICE CONNECTIONS RETROFITED WITH BACKFLOW PREVENTION DEVICES IN THE FORM OF REDUCED PRESSURE ZONE DEVICES. RPZ DEVICES PREVENT CONTAMINATES PRODUCED BY BUSINESSES OR BUILDINGS FROM FLOWING BACK INTO THE PUBLIC WATER SUPPLY. | 2022 | 3703 | 2892.67 | 811 | 0 | 0 | 0 | 0 | 0 | 3703.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYSPKFIR | BNYDC Sprinkler and Fire Alarm System Upgrades | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | BNYDC SPRINKLER AND FIRE ALARM SYSTEM UPGRADE | 2022 | 8318 | 899.24 | 12190 | 7610 | 0 | 0 | 0 | 0 | 20699.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYSTEAM2 | BNYDC Brooklyn STEAM Center BP | INDUSTRIAL DEVELOPMENT | 200 | ED-K319 |  |  | CONSTRUCTION OF STEAM CENTER AT BNYDC | 2022 | 175 | 0 | 0 | 175 | 0 | 0 | 0 | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYTIFUND | BNYDC Tenant Improvement Fund | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BNY TENANT IMPROVEMENT FUND | 2022 | 6179 | 0 | 5715 | 2950 | 750 | 500 | 0 | 0 | 9915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYUBFARM | BNYDC Urban Farm Incubator | INDUSTRIAL DEVELOPMENT | 200 | ED-K319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROOFTOP FARMING FOR PUBLIC CONSUMPTION | 2022 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BNYUPSTM | BNYDC Above Ground Steam Main | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ABOVE GROUND STEAM MAIN RELOCATION | 2022 | 1313 | 170.36 | 580 | 2000 | 0 | 0 | 0 | 0 | 2750.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BPMCBUA | Brooklyn Medical Plaza - BPMC Bedford Armory Clinic | MISCELLANEOUS | 200 | ED-0075 |  |  | BROOKLYN MEDICAL PLAZA - BPMC BEDFORD ARMORY CLINIC | 2022 | 2000 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHDEVSP | Bush Terminal Development Site Preparation | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 200 | ED-0075 |  |  | BUSHDEVSP | 2022 | 10000 | 4504 | 14496 | 0 | 0 | 0 | 0 | 0 | 19000 | 8138.76 | 1862 | 0 | 0 | 0 | 0 | 0 | 10000.76
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHTCAFE | Bush Terminal Cafe Building Improvements | MISCELLANEOUS | 200 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BUSH TERMINAL CAFÔ BUILDING IMPROVEMENTS | 2022 | 3000 | 316.57 | 0 | 0 | 0 | 0 | 1073 | 1610 | 2999.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUNTAC | Bush Terminal Made in NY Unit A and C | MISCELLANEOUS | 200 | ED-0410 ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCTION AND RENOVATION OF UNIT A AT BUSH TERMINAL | 2022 | 53501 | 95654.5 | 21619 | 5000 | 0 | 3000 | 0 | 35730 | 161003.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUNTBD | BUSH MINY--UNIT D | MISCELLANEOUS | 200 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BUSH MINY--BUILDING B/D | 2022 | 50000 | 7586.98 | 86 | 7914 | 0 | 8000 | 32413 | 4000 | 59999.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | BUSHUTIL | Bush Terminal Site and Utility Improvements | MISCELLANEOUS | 200 | ED-0410 ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BUSH TERMINAL UTILITY IMPROVEMENTS | 2022 | 39301 | 22907.14 | 31417 | 0 | 1500 | 1500 | 0 | 0 | 57324.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CANTONBLK | Canton Court Bulkhead Replacement | MISCELLANEOUS | 200 | RE-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CANTON COURT BULKHEAD REPLACEMENT BROOKLYN | 2022 | 4400 | 2541.84 | 1418 | 0 | 0 | 0 | 0 | 0 | 3959.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYPLAZ | Coney Island Steeplechase Plaza | NEIGHBORHOOD REVITALIZATION | 213 | ED-0404 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CONEY ISLAND STEEPLECHASE PLAZA | 2022 | 34582 | 29717.99 | 89 | 0 | 0 | 0 | 0 | 0 | 29806.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYWEST | Coney Island West | MISCELLANEOUS | 200 | ED-0075 SE-0200K SE-0002K WM-0006 WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONEY ISLAND WEST | 2022 | 181000 | 119356.71 | 8000 | 0 | 0 | 0 | 0 | 78038 | 205394.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CONEYWIRD | Coney West - Abe Stark Ice Rink Demolition | MISCELLANEOUS | 200 | ED-0075 |  |  | CONEY WEST ABE STARK ICE RINK DEMOLITION | 2022 | 8000 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSHOMEP | New York City Ferry - Homeport | WATERFRONT DEVELOPMENT | 200 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HOMEPORT PIER AT THE BROOKLYN NAVY YARD FOR CITYWIDE FERRY SERVICE | 2022 | 41033 | 47887.11 | 6068 | 0 | 0 | 0 | 0 | 0 | 53955.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKLYNDV | Downtown Brooklyn Redevelopment | COMMERCIAL DEVELOPMENT | 202 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BROOKLYN | REDEVELOPMENT | 2022 | 57239 | 17335.85 | 3926 | 0 | 0 | 1770 | 0 | 0 | 23031.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | DTBKWSPK | Downtown Brooklyn - Willoughby Square Park | MISCELLANEOUS | 202 | ED-0075 ED-K075 ED-D075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DESIGN AND CONSTRUCTION OF WILLOUGHBY SQUARE PARK | 2022 | 8500 | 334.01 | 14317 | 0 | 0 | 0 | 0 | 0 | 14651.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | FREIGHTSP | Freight NYC - Rail Transload | MISCELLANEOUS | 200 | ED-0410 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FREIGHT NYC - SUNSET PARK RAIL - 100K JOBS PLAN | 2022 | 15800 | 0 | 0 | 0 | 0 | 8670 | 0 | 7129 | 15799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GK26W5-05 | DSGN & CONS OF ROW GI IN 26W-005 | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GI - DESIGN AND CONSTRUCTION OF RIGHTOF WAY BIOSWALES AND STORMAWATERGREENSTREETS AT CSO TRIBUTARY AREA 26W-005 IN BROOKLYN | 2022 | 45271 | 166678.44 | 9335 | 0 | 0 | 0 | 0 | 0 | 176013.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GKNC15-02 | GI - Green Infrastructure in Newtown Creek Drainage Area | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GREEN INFRASTRUCTURE IN NEWTOWN CREEK DRAINAGE AREA | 2022 | 48795 | 61756.26 | 3164 | 0 | 0 | 0 | 0 | 0 | 64920.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | GREEN | Green Infrastructure 26W | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GREEN INFRASTRUCTURE 26W | 2022 | 48855 | 55084.54 | 4475 | 0 | 0 | 0 | 0 | 0 | 59559.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWKFHAWF | Hamilton Ave - DOT Asphalt Plant (Waterfront) | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 200 | PU-0200 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | HAMILTON AVE - DOT ASPHALT PLANT (WATERFRONT) | HAMILTON AVE - DOT ASPHALT PLANT (WATERFRONT) | 2022 | 5575 | 0 | 1228 | 0 | 0 | 0 | 3840 | 0 | 5068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-BIOBAT | BioBAT Life Sciences | MISCELLANEOUS | 200 | ED-0075 |  |  | BIO BAT LIFE SCIENCES | 2022 | 50000 | 0 | 0 | 5000 | 15000 | 0 | 15000 | 15000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MILLREHAB | Mill Basin - Waterfront Rehabilitation | MISCELLANEOUS | 200 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MILL BASIN WATERFRONT REHABILITATION | 2022 | 3250 | 2931.86 | 218 | 100 | 0 | 0 | 0 | 0 | 3249.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MOOREROOF | Moore Street Market Roof Rehabilitation | MARKET DEVELOPMENT | 200 | ED-K384 ED-D384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MOORE STREET MARKET ROOF REHABILITATION | 2022 | 200 | 0 | 0 | 1200 | 0 | 0 | 0 | 1000 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | MOOREST | Moore Street Market | MISCELLANEOUS | 201 | ED-D384 ED-K075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MOORE STREET MARKET PROJECT | 2022 | 200 | 537.1 | 0 | 157 | 0 | 500 | 0 | 0 | 1194.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDFATLBB | NDF - Atlantic Avenue Broadband Conduit (HWD10105) | NEIGHBORHOOD REVITALIZATION | 200 | ED-0384 |  |  | NDF - ATLANTIC AVENUE BROADBAND CONDUIT (HWD10105) | 2022 | 1700 | 0 | 0 | 0 | 0 | 0 | 1700 | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-BROAD | NDF - ENY IBZ Infrastructure - Broadband | NEIGHBORHOOD REVITALIZATION | 200 | ED-0384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NDF-ENY IBZ BROADBAND | 2022 | 2500 | 0 | 0 | 0 | 500 | 0 | 2000 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-IBMOD | NDF - ENY Industiral Buiding Modernization and Activation | NEIGHBORHOOD REVITALIZATION | 200 | ED-0384 ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INDUSTRIAL BUILDING MODERNIZATION AND ACTIVATION | 2022 | 4500 | 3686.18 | 813 | 3300 | 0 | 0 | 0 | 0 | 7799.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NEWKIRK | FA - Newkirk Plaza Reconstruction | MISCELLANEOUS | 214 | ED-D075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | NEWKIRK | NEWKIRK PLAZA | 2022 | 463 | 463 | 0 | 0 | 0 | 50 | 0 | 0 | 513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NOSTRAND | FA - Nostrand Avenue Merchants Assoc. (Flatbush Gateway) | COMMERCIAL DEVELOPMENT | 209 | ED-D384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROWIDE | COMMERCIAL REVITALIZATION | 2022 | 850 | 0 | 0 | 0 | 850 | 0 | 0 | 0 | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NWBURGFL | North Williamsburg Ferry Landing | WATERFRONT DEVELOPMENT | 201 | FA-0027 ED-0075 ED-D401 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCTION OF BARGE FERRY LANDING AT THE NORTH 5TH ST PIER IN NORTHWILLIAMSBURG, BROOKLYN | 2022 | 1176 | 535.93 | 1 | 0 | 42 | 0 | 0 | 0 | 578.93 | 1711.73 | 0 | 0 | 220 | 0 | 0 | 0 | 1931.73
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFHP2 | NYC Ferry Homeport 2 | MISCELLANEOUS | 200 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HOMEPORT 2 AT ATLANTIC BASIN | 2022 | 65000 | 10108.94 | 35000 | 9891 | 0 | 0 | 10000 | 0 | 64999.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | OFFSHRWND | Offshore Wind - Development and Manufacturing | MISCELLANEOUS | 200 | ED-0075 |  |  | OFFSHORE WIND - RESEARCH FACILITIES/STAGING SITES DEVELOPMENT AND EQUIPMENT MANUFACTURING | 2022 | 130000 | 0 | 3000 | 15000 | 30000 | 30000 | 15000 | 37000 | 130000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB07 | GPWB - Box Street and Newtown Barge Parks | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 201 | P-0839 WP-0283 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | DUPONT ST - BKLYN | GPWB - DUPONT ST NEWTOWN BARGE PLGRD | 2022 | 10670 | 3743.83 | 567 | 0 | 0 | 0 | 0 | 0 | 4310.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWB08 | GPWB - 65 Commercial St Soccer Pk-MTA Reloc. & Park Develop. | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 201 | P-1018 P-0839 ED-0384 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 65 COMMERCIAL ST - BKLYN | GPWB - 65 COMMERCIAL ST SOCCER PK | 2022 | 15400 | 9885.55 | 545 | 0 | 0 | 0 | 0 | 0 | 10430.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWBOX | GPWB - Box Street Park | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 201 | P-0839 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCTION OF BOX STREET PARK | 2022 | 18000 | 0 | 16150 | 0 | 0 | 0 | 0 | 0 | 16150 | 2351.15 | 2649 | 0 | 0 | 0 | 0 | 0 | 5000.15
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-2GPWNB | GPWB - Newtown Barge Park | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 201 | P-0839 WP-0283 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEWTOWN BARGE PARK | 2022 | 20608 | 15414.15 | 713 | 0 | 0 | 0 | 0 | 0 | 16127.15 | 4493.22 | 1007 | 0 | 0 | 0 | 0 | 0 | 5500.22
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER12PH2 | Brooklyn Cruise Terminal Pier 12 Substructure Rehab phase2 | MISCELLANEOUS | 200 | ED-0409 |  |  | BROOKLYN CRUISE TERMINAL PIER 12 SUBSTRUCTURE REHAB PHASE2 | 2022 | 14000 | 0 | 1000 | 13000 | 0 | 0 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV230-SHA | FA - WCS - New York Aquarium | NEW TECHNOLOGY AND CONSTRUCTION | 213 | PV-K230 PV-0230 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOARDWALK AT WEST 8TH STREET & SURF AVENUE, BROOKLYN NY, 11224 | CONSTRUCTION OF NEW SHARK EXHIBIT ON AQUARIUM GROUNDS | 2022 | 37735 | 117650.84 | 0 | 0 | 1519 | 0 | 0 | 0 | 119169.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV264CINE | BAM - BAM South Site Theaters | MISCELLANEOUS | 299 | PV-0264 PV-K264 PV-D264 PV-0467 ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BAM - BAM SOUTH SITE THEATERS | 2022 | 7500 | 10212.52 | 18241 | 0 | 0 | 0 | 0 | 0 | 28453.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467SOST | DBCD South Site Cultural Condo Fitout | ESSENTIAL RECONSTRUCTION OF FACILITIES | 202 | PV-0467 ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 20 LAFAYETTE AVENUE BROOKLYN | DBCD SOUTH SITE CULTURAL CONDO FITOUT OF COMMON AREAS | 2022 | 1000 | 4187.56 | 7631 | 0 | 0 | 0 | 0 | 0 | 11818.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467STFO | 651 Arts South Site Studios Fitout | ESSENTIAL RECONSTRUCTION OF FACILITIES | 202 | PV-0467 PV-D467 PV-K467 ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 20 LAFAYETTE AVENUE BROOKLYN | 651 ARTS SOUTH SITE STUDIOS FITOUT | 2022 | 7750 | 7409.8 | 10641 | 0 | 0 | 0 | 0 | 0 | 18050.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | REDHOOK | Red Hook Library | MISCELLANEOUS | 206 200 | LB-D104 LB-0104 PU-0025 |  |  | RED HOOK LIBRARY | 2022 | 2835 | 1188.73 | 16535 | 0 | 0 | 0 | 0 | 0 | 17723.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | RS-CIC | Raise Shoreline - Coney Island Creek | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 200 | PU-0100 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FUNDING TO RAISE SHORELINE - CONEY ISLAND CREEK | 2022 | 32000 | 0 | 2000 | 0 | 45000 | 0 | 0 | 0 | 47000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND2601C | CIH: RELOCATE OUTPATIENT RADIOLOGIC IMAGING SERVICES | ROUTINE RECONSTRUCTION | 213 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 2601 OCEAN PARKWAY, BROOKLYN, NY 11235 | RENOVATE EXISTING SPACE ON THE 5TH FLOOR OF THE MAIN HOSPITAL BUILDING TO RELOCATE OUTPATIENT RADIOLOGIC IMAGING SERVICES FROM THE FIRST FLOOR OF THE BUILDING THAT WAS DESTROYED BY SEVERE WATER DAMAGES DUE TOEXPOSURE TO SALT WATER FROM HURRICANE SANDY AT CONEY ISLAND HOSPITAL. | 2022 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7658.3 | 240 | 0 | 0 | 0 | 1502 | 0 | 9400.3
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND2603C | CIH: RENOVATE VACANT SPACE ON FIRST FL MAIN HOSPITAL BLG. | ROUTINE RECONSTRUCTION | 213 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 2601 OCEAN PARKWAY, BROOKLYN, NY 11235 | RENOVATE APPROXIMATELY 11,000 SQ. FT. OF VACANT SPACE ON THE FIRST FLOOR OF THE MAIN HOSPITAL BUILDING TO CREATE OFFICE SPACE THAT WAS DESTROYED BY SEVERE WATER DAMAGES DUE TO EXPOSURE TO SALT WATER FROM HURRICANE SANDY AT CONEY ISLAND HOSPITAL. | 2022 | 3876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6217.03 | 45 | 100 | 0 | 2013 | 0 | 0 | 8375.03
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND2605 | CIH: DESIGN & CONSTRUCTION MANAGEMENT FOR HOSPITAL CAMPUS | MISCELLANEOUS | 200 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONEY ISLAND HOSPITAL DESIGN AND CONSTRUCTION | 2022 | 1084343 | 46489.46 | 21709 | 0 | 0 | 0 | 0 | 0 | 68198.46 | 526431.13 | 71875 | 102268 | 0 | 0 | 0 | 0 | 700574.13
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB3416 | Sandy - BNYDC - PW 3416 - Berth 6 Concrete Slab | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PW 3416 - CONCRETE SLAB | 2022 | 335 | 11.25 | 50 | 0 | 0 | 0 | 0 | 0 | 61.25 | 101.3 | 433 | 0 | 0 | 0 | 0 | 0 | 534.3
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4123 | Sandy - BNYDC - PW 4123 Rehabilitation | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | PW 4123 - PIER D REHABILITATION AT THE BROOKLYN NAVY YARD | 2022 | 4832 | 0 | 484 | 0 | 0 | 0 | 0 | 0 | 484 | 0 | 4348 | 0 | 0 | 0 | 0 | 0 | 4348
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4225 | Sandy - BNYDC - PW 4225 Dry-Dock/Caisson Gate 5,6, PWell 156 | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PW 4225 - DRY-DOCK /CAISSON GATE #5,#6, PUMP WELL #156 - RESTORATION AND MITIGATION | 2022 | 15897 | 171.57 | 0 | 0 | 911 | 0 | 0 | 0 | 1082.57 | 1544.19 | 2000 | 11270 | 0 | 0 | 0 | 0 | 14814.19
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4269 | BNYDC Sandy - PW 4269 - B270 Boilers | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 |  |  | BUILDING 280 BOILER REPLACEMENT AND MITIGATION | 2022 | 4001 | 0 | 455 | 0 | 0 | 0 | 0 | 0 | 455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4270 | Sandy - BNYDC - PW 4270 - BNYDC SITE-WIDE CONDUIT - PAAP | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PW 4270 - BNYDC SITE-WIDE CONDUIT - PAAP - RESTORATION AND MITIGATION | 2022 | 1184 | 13.44 | 0 | 0 | 65 | 0 | 0 | 0 | 78.44 | 121.03 | 985 | 0 | 0 | 0 | 0 | 0 | 1106.03
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4271 | Sandy - BNYDC - PW 4271 - Substations No. 292 and No. 542 | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PW 4271 - SUBSTATIONS NO. 292 AND NO. 542 - RESTORATION AND MITIGATION | 2022 | 3071 | 24.7 | 0 | 0 | 175 | 0 | 0 | 0 | 199.7 | 222.35 | 1349 | 1300 | 0 | 0 | 0 | 0 | 2871.35
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4273 | Sandy - BNYDC - PW 4273 - Steam Back-Up Plant - Bldg #41A | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PW 4273 - STEAM GENERATING BACK-UP PLANT - BLDG #41A - RESTORATION AND MITIGATION | 2022 | 1441 | 18.1 | 0 | 0 | 79 | 0 | 0 | 0 | 97.1 | 162.94 | 1181 | 0 | 0 | 0 | 0 | 0 | 1343.94
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4274 | Sandy - BNYDC - PW 4274 - Dry Dock 1 | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PW 4274 - DRY DOCK 1 | 2022 | 2931 | 115.42 | 0 | 0 | 179 | 0 | 0 | 0 | 294.42 | 1038.78 | 1693 | 0 | 0 | 0 | 0 | 0 | 2731.78
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4275 | Sandy - BNYDC - PW 4275 - SUB STATION G BUILDING 386 | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PW 4275 - SUB STATION G BUILDING 386 - RESTORATION AND MITIGATION | 2022 | 14243 | 152.96 | 0 | 0 | 744 | 0 | 0 | 0 | 896.96 | 1376.64 | 11969 | 0 | 0 | 0 | 0 | 0 | 13345.64
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4307 | Sandy - BNYDC - PW 4307 Substation B | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PW 4307 - SUBSTATION B - RESTORATION AND MITIGATION | 2022 | 8184 | 77.62 | 0 | 0 | 440 | 0 | 0 | 0 | 517.62 | 698.63 | 3967 | 3000 | 0 | 0 | 0 | 0 | 7665.63
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4388 | Sandy - BNYDC - PW 4388 - Boiler Replacement | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PW 4388 - BOILER REPLACEMENT - RESTORATION AND MITIGATION | 2022 | 1079 | 24.9 | 0 | 0 | 43 | 0 | 0 | 0 | 67.9 | 224.14 | 787 | 0 | 0 | 0 | 0 | 0 | 1011.14
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4582 | Sandy - BNYDC - PW 4582 - BERTH 9,9A | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PW 4582 - BERTH 9,9A - RESTORATION AND MITIGATION | 2022 | 10502 | 0 | 0 | 0 | 697 | 0 | 0 | 0 | 697 | 391.09 | 2414 | 7000 | 0 | 0 | 0 | 0 | 9805.09
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDB4583 | Sandy - BNYDC - PW 4583 - BERTH 10 & 10A | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PW 4583 - BERTH 10 & 10A - RESTORATION AND MITIGATION | 2022 | 11538 | 0 | 0 | 0 | 723 | 0 | 0 | 0 | 723 | 350.89 | 2464 | 8000 | 0 | 0 | 0 | 0 | 10814.89
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBCT | EDC - Hurricane Sandy - BCT Repairs | MISCELLANEOUS | 206 207 | ED-0404 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REPAIRS AT THE BCT PROJECT AS A RESULT OF HURRICANE SANDY | 2022 | 3000 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 300 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 2700
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYAM | Sandy - BNYDC Hurricane Sandy Asset Management Repairs | INDUSTRIAL DEVELOPMENT | 200 | ED-0319 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | BROOKLYN NAVY YARD - HURRICANE SANDY RECOVERY LOCAL MATCH | 2022 | 3610 | 0 | 1545 | 545 | 4808 | 0 | 0 | 0 | 6898 | 0 | 3430 | 46224 | 0 | 0 | 0 | 0 | 49654
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYEC | Sandy - BNYDC Hurricane Sandy Electrical Repairs | MISCELLANEOUS | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ELECTRICAL REPAIRS IN THE BROOKLYN NAVY YARD AS A RESULT OF HURRICANESANDY | 2022 | 3100 | 0 | 0 | 0 | 320 | 0 | 0 | 0 | 320 | 1118.29 | 979 | 3000 | 0 | 0 | 0 | 0 | 5097.29
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDBNYWF | Sandy - BNYDC Hurricane Sandy Waterfront Repair | MISCELLANEOUS | 200 | ED-0319 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WATERFRONT REPAIRS DUE TO HURRICANE SANDY | 2022 | 24850 | 0 | 0 | 0 | 761 | 0 | 0 | 0 | 761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD9 | HARBOR CHARLIE | POLICE FACILITIES | 200 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HARBOR ELECTRICAL | 2022 | 5368 | 0 | 0 | 572 | 0 | 0 | 0 | 0 | 572 | 266.78 | 0 | 4874 | 0 | 0 | 0 | 0 | 5140.78
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG3BAT | FEMA 428 Projects - Group 3 - Brooklyn Army Terminal BAT | MISCELLANEOUS | 200 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FEMA 428 PROJECTS - GROUP 3 - BROOKLYN ARMY TERMINAL BAT | 2022 | 6557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1006.24 | 5551 | 0 | 0 | 0 | 0 | 0 | 6557.24
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG3BSH | FEMA 428 Projects - Group 3 - BUSH Terminal | MISCELLANEOUS | 200 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FEMA 428 PROJECTS - GROUP 3 RESILIENCY PROJECTS - BUSH TERMINAL | 2022 | 13606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1045.18 | 12561 | 0 | 0 | 0 | 0 | 0 | 13606.18
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRBCT | FA Resiliency - BCT | MISCELLANEOUS | 200 | FA-0027 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FA RESILIENCY - BCT | 2022 | 10000 | 201.1 | 250 | 2049 | 0 | 0 | 0 | 0 | 2500.1 | 603.3 | 750 | 6147 | 0 | 0 | 0 | 0 | 7500.3
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDYNYA | WCS - New York Aquarium Sandy Renovation | NEW TECHNOLOGY AND CONSTRUCTION | 213 | PV-0230 PV-0467 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SANDY RELATED RENOVATION/RESTORATION - WCS NEW YORK AQUARIUM | 2022 | 111256 | 23495.32 | 10 | 0 | 0 | 0 | 0 | 0 | 23505.32 | 161793.01 | 23281 | 0 | 0 | 0 | 0 | 0 | 185074.01
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBMTOSW | SBMT Offshore Wind | WATERFRONT DEVELOPMENT | 200 | ED-0404 ED-0409 |  |  | OFFSHORE WIND | 2022 | 56278 | 0 | 2000 | 0 | 10560 | 5626 | 5626 | 32466 | 56278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SNSTFRGH2 | Sunset Park Areawide Infrastructure Improvements | NEIGHBORHOOD REVITALIZATION | 200 | ED-0384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SUNSET PARK IMPROVEMENTS - AREA IMPROVEMENTS | 2022 | 37500 | 7499.5 | 25000 | 0 | 0 | 5000 | 0 | 0 | 37499.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | SUNSETPAR | Sunset Park Waterfront Redevelopment | WATERFRONT DEVELOPMENT | 207 | ED-0075 P-D017 ED-D075 P-1245 ED-0410 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  |  | 2022 | 1382 | 24368.72 | 5033 | 0 | 0 | 0 | 0 | 0 | 29401.72 | 25859.53 | 662 | 0 | 0 | 0 | 0 | 0 | 26521.53
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | TIMP-BRCS | Tenant Improvement Fund-Brooklyn Roasting Coffee Shop | INDUSTRIAL DEVELOPMENT | 200 | ED-0380 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | THIS CP COVERS THE WORK TO FIT OUT THE SPACE IN PREPARATION FOR THE TENANT'S COFFEE SHOP. THE WORK ENTAILS THE ARCHITECTURAL SERVICES, CM WORK, AND CONSTRUCTION TO PROVIDE NECESSARY UTILITY CONNECTIONS IN THE SPACE. | 2022 | 271 | 0 | 0 | 0 | 271 | 0 | 0 | 0 | 271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLBKWSMM | BROOKLYN WHOLESALE MEAT MARKET | MISCELLANEOUS | 200 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BROOKLYN WHOLESALE MEAT MARKET | 2022 | 2000 | 0 | 0 | 0 | 0 | 0 | 800 | 1200 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLPIER6 | BUSH TERMINAL PIER 6 RECONSTRUCTION | WATERFRONT DEVELOPMENT | 200 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BUSH TERMINAL PIER 6 RECONSTRUCTION | 2022 | 34000 | 0 | 3202 | 12248 | 0 | 0 | 18550 | 0 | 34000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLPIER7 | BUSH TERMINAL PIER 7 DEMOLITION | WATERFRONT DEVELOPMENT | 200 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BUSH TERMINAL PIER 7 DEMOLITION | 2022 | 8500 | 0 | 1700 | 0 | 0 | 3400 | 3400 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | GI-RH-GR | GI - GREEN ROOF INSTALLATION AT RED HOOK HOUSES IN BKLYN | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 |  |  | GREEN ROOF INSTALLATION AT THE RED HOOK HOUSES IN BROOKLYN AS PART OFHURRICAN SANDY RESLIENCY UPGRADES | 2022 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM06BOBK | BOULEVARD BRICKWORK | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 205 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | LINDEN BLVD, ASHFORD ST, WORTMAN AVE, SCHENCK AVE | BRICKWORK | 2022 | 7136 | 4275.77 | 0 | 0 | 0 | 0 | 2210 | 0 | 6485.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM10WYCR | WYCKOFF GARDENS COMMUNITY ROOM | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 206 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WYCKOFF GARDENS COMMUNITY ROOM | 2022 | 450 | 0 | 641 | 0 | 0 | 0 | 0 | 0 | 641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM12MCPL | MARCY HOUSES DAY CARE CENTER PLAYGROUND | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 203 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | UPGRADE PLAYGROUND AT DAY CARE CENTER | 2022 | 209 | 169.17 | 40 | 0 | 0 | 0 | 0 | 0 | 209.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM12WYCC | WYCKOFF GARDENS COMMUNITY CENTER UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 206 | HA-D001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | UPGRADES TO INCLUDE CLASSROOMS, OPEN SHOP AREA AND OFFICES | 2022 | 150 | 0 | 810 | 0 | 0 | 0 | 0 | 0 | 810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13SURF | SUMNER HOUSES ROOF REPLACEMENT | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 203 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROOF REPLACEMENT | 2022 | 11476 | 9376.05 | 0 | 0 | 0 | 1057 | 0 | 0 | 10433.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM14KBEY | KINGSBOROUGH AND EXTENSION ENERGY IMPROVEMENTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 208 | HA-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ENERGY UPGRADES | 2022 | 2290 | 3141.66 | 160 | 0 | 0 | 0 | 0 | 0 | 3301.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM14RHSR | RED HOOK SENIOR CENTER RENOVATION | DEPARTMENT FOR THE AGING BUILDING RECONSTRUCTION | 206 | AG-D001 | PROJECT DELAYED DUE TO SCHEDULING OF UTILITY WORK |  | RENOVATE SENIOR CENTER | 2022 | 1800 | 1645.37 | 155 | 0 | 0 | 0 | 0 | 0 | 1800.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15ODPA | O'DWYER GARDENS PLAYGROUND UPGRADES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 213 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PLAYGROUND UPGRADE | 2022 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16HPBR | HOPE GARDENS INSTALLATION OF BOILERS AND RELATED EQUIPMENT | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 204 | HA-D001 HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INSTALLATION AND REPAIRS OF BOILERS AND RELATED EQUIPMENT | 2022 | 500 | 0 | 500 | 0 | 0 | 1000 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16NHGR | NOSTRAND HOUSES PLAYGROUND RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 215 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PLAYGROUND RENOVATION | 2022 | 250 | 645.43 | 65 | 0 | 0 | 0 | 0 | 0 | 710.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16SURF | SURF GARDENS DEVELOPMENT - PLAYGROUND RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 200 | HA-K001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SURF GARDENS DEVELOPMENT - PLAYGROUND RENOVATION | 2022 | 250 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17WISR | WHITMAN HOUSES - WILLOUGHBY SENIOR CENTER HVAC | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 202 | HA-K001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | UPGRADE HVAC SYSTEM | 2022 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BPBC | BORINQUEN PLAZA I BASKETBALL COURT UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 201 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | UPGRADE BASKETBALL COURT AT BORINQUEN PLAZA I COMMUNITY CENTER | 2022 | 400 | 297.95 | 102 | 0 | 0 | 0 | 0 | 0 | 399.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BREV | Brevoort Resident Association - Coliseum Repairs and CCTVs | LOW TO MODERATE INCOME PUBLIC HOUSING CONSTRUCTION | 200 | HA-K001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BREVOORT RESIDENT ASSOCIATION - COLISEUM REPAIRS AND CCTVS | 2022 | 500 | 240.38 | 260 | 0 | 0 | 0 | 0 | 0 | 500.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BSVB | BROWNSVILLE AND SARATOGA VILLAGE BOILER REPAIR | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 200 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BROWNSVILLE AND SARATOGA VILLAGE BOILER REPAIR | 2022 | 12600 | 0 | 12600 | 0 | 0 | 0 | 0 | 0 | 12600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CHBW | CYPRESS HILLS BOILER WORK | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 200 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BOILER REPAIR AT CYPRESS HILLS | 2022 | 10500 | 8624.57 | 1876 | 0 | 0 | 0 | 0 | 0 | 10500.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HGCC | HOPE GARDENS COMMUNITY CENTER--MODERNIZE GYM. | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 204 | HA-K001 HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION OF THE GYM AT HOPE GARDEN'S COMMUNITY CENTER. | 2022 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18HYEL | HYLAN ELEVATORS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 201 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ELEVATOR UPGRADE | 2022 | 4070 | 0 | 3700 | 0 | 0 | 0 | 0 | 0 | 3700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18IGIR | INGERSOLL GARDENS INSTALLATION OF IRRIGATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 202 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INSTALLATION OF IRRIGATION | 2022 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18INBC | INGERSOLL HOUSES BASKETBALL COURT RENOVATIONS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 202 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BASKETBALL COURT RENOVATIONS | 2022 | 400 | 359.3 | 41 | 0 | 0 | 0 | 0 | 0 | 400.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18OHPG | OCEAN HILL PLAYGROUND | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 216 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | UPGRADE PLAYGROUND | 2022 | 500 | 65.48 | 435 | 0 | 0 | 0 | 0 | 0 | 500.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PKTV | PINK CCTV | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 200 | HA-0001 |  |  | SECURITY UPGRADES AT PINK HOUSES | 2022 | 3000 | 392 | 2608 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WBCC | PLAYGROUND UPGRADES AT WILLIAMSBURG DAY CARE CENTER | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 201 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PLAYGROUND UPGRADES AT WILLIAMSBURG DAY CARE CENTER 222 GRAHAM AVENUE | 2022 | 350 | 325.29 | 95 | 0 | 0 | 0 | 0 | 0 | 420.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WHIT | NYCHA WHITMAN/WILLOUGHBY SENIOR CENTER HVAC UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 200 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NYCHA WHITMAN/WILLOUGHBY SENIOR CENTER HVAC UPGRADE | 2022 | 400 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WIPG | WILLIAMSBURG HOUSES PLAYGROUND UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 201 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WILLIAMSBURG HOUSES PLAYGROUND UPGRADE AT 176 MAUJER | 2022 | 350 | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WKCC | WYCKOFF GARDENS COMMUNITY CENTER RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 206 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WYCKOFF GARDENS COMMUNITY CENTER RENOVATION | 2022 | 414 | 0 | 414 | 0 | 0 | 0 | 0 | 0 | 414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WKLG | WYCKOFF GARDENS LIGHTING | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 206 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INSTALLATION OF LIGHTING AT WYCKOFF GARDENS | 2022 | 300 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BVPU | BAYVIEW HOUSES PLAYGROUND UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 218 | HA-D001 |  |  | PLAYGROUND UPGRADE | 2022 | 250 | 0 | 355 | 0 | 0 | 0 | 0 | 0 | 355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CSVE | SARATOGA VILLAGE ELEVATORS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 216 | HA-0001 |  |  | FUNDING FOR SARATOGA VILLAGE ELEVATORS | 2022 | 2000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19FHSE | FARRAGUT HOUSES SECURITY LIGHTING | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 202 | HA-D001 |  |  | FARRAGUT HOUSES-SECURITY LIGHTING FUNDING TO SUPPORT SECURITY LIGHTING | 2022 | 581 | 0 | 581 | 0 | 0 | 0 | 0 | 0 | 581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19HHTV | HOWARD HOUSES CCTV | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 200 | HA-K001 HA-D001 |  |  | HOWARD HOUSES CCTV | 2022 | 1400 | 182 | 1218 | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19SBPU | SHEEPSHEAD BAY HOUSES PLAYGROUND UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 215 | HA-D001 |  |  | PLAYGROUND UPGRADE | 2022 | 350 | 308 | 42 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19TCPU | TOMPKINS HOUSES CHILDRENS PARK UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 203 | HA-D001 |  |  | FUNDING FOR CHILDRENS PARK UPGRADE | 2022 | 507 | 436.66 | 70 | 0 | 0 | 0 | 0 | 0 | 506.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19WPLF | WILLIAMS PLAZA LIGHTING AND FENCING IMPROVEMENTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 201 | HA-D001 |  |  | LIGHTING AND FENCING IMPROVEMENTS | 2022 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ALPU | PLAYGROUND RENOVATION- ALBANY HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 208 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NYCHA ALBANY HOUSES PLAYGROUND -- FUNDING TO RENOVATE PLAYGROUND | 2022 | 250 | 123.21 | 127 | 0 | 0 | 0 | 0 | 0 | 250.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BCCG | BUSHWICK HOUSES UPGRADE COMMUNITY CENTER GYM | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 216 | HA-0001 HA-D001 |  |  | UPGRADES TO COMMUNITY CENTER GYM | 2022 | 1000 | 0 | 1165 | 0 | 0 | 0 | 0 | 0 | 1165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHPU | BREVOORT UPGRADES TO PLAYGROUND | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 203 | HA-D001 |  |  | BREVOORT HOUSES -- UPGRADES TO BREVOORT PLAYGROUND | 2022 | 800 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BVPL | BAYVIEW HOUSES PLAYGROUND UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 208 | HA-D001 |  |  | FUNDING TO RENOVATE PLAYGROUND INCLUDES SPECIAL NEEDS EQUIPMENT | 2022 | 291 | 0 | 291 | 0 | 0 | 0 | 0 | 0 | 291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CPPU | COOPER PARK PLAY GROUND UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 201 | HA-0001 |  |  | UPGRADE OF COOPER PARK HOUSES PLAYGROUND | 2022 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GCBR | GLENWOOD COMMUNITY CENTER RENOVATE BATHROOM | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 218 | HA-D001 |  |  | RENOVATE BATHROOMS AT COMMUNITY CENTER- GLENWOOD | 2022 | 650 | 0 | 650 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GHLC | LED LIGHTING AND CAMERAS GOWANUS HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 206 | HA-D001 |  |  | GOWANUS HOUSES -- LED LIGHTING AND CAMERAS | 2022 | 150 | 23.4 | 127 | 0 | 0 | 0 | 0 | 0 | 150.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20HCAM | PHASE 2 CAMERAS AT LANGSTON HUGES HOUSES | FINANCING COSTS | 216 | HA-D001 |  |  | PHASE 2 CAMERAS- LANGSTON HUGHES HOUSES | 2022 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20KRWJ | KINGSBOROUGH DEVELOPMENT RESTORATION OF WALLS OF JERICHO | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 200 | HA-D001 |  |  | KINGSBOROUGH DEVELOPMENT -- RESTORATION OF WALLS OF JERICHO | 2022 | 1800 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MGSC | SECURITY CAMERAS MARCUS GARVEY | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 216 | HA-K001 |  |  | NYCHA SECURITY CAMERAS--SECURITY CAMERAS FOR MARCUS GARVEY HOUSES. | 2022 | 75 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SHEL | SHEEPSHEAD HOUSES-EXTERIOR LIGHTING UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 215 | HA-D001 |  |  | EXTERIOR LIGHTING UPGRADE- SHEEPSHEAD HOUSES | 2022 | 300 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20TCCU | TOMPKINS - UPGRADE THE SPACE IN THE COMMUNITY CENTER | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 200 | HA-D001 |  |  | TOMPKINS HOUSES COMMUNITY CENTER UPGRADE -- UPGRADE THE SPACE IN THE COMMUNITY CENTER | 2022 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20THRR | TOMPKINS HOUSES ROOF REPLACEMENT | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 203 | HA-K001 |  |  | TOMPKINS HOUSES--ROOF REPLACEMENT. | 2022 | 50 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20VDCC | VAN DYKE 1 HOUSES COMPUTERS FOR NEW DAY CARE CENTER | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 216 | HA-D001 |  |  | COMPUTERS FOR NEW DAY CARE CENTER- VAN DYKE I 381 SUTTER AVE | 2022 | 64 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WRCS | WYCKOFF GARDENS - RENOVATION OF COMMUNITY SPACE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 206 | HA-D001 |  |  | WYCKOFF GARDENS -- FUNDING FOR RENOVATIONS OF COMMUNITY SPACES, LIGHTING, CAMERAS AND OTHER CAPITAL WORK | 2022 | 2500 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21BHPR | NEW PLAYGROUND-REFURBISH AT BAYVIEW HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 218 | HA-D001 |  |  | BAYVIEW HOUSES - NEW PLAYGROUND-REFURBISH EXISTING PLAYGROUND WITH NEW SAFETY SURFACE AND PLAY EQUIPMENT. | 2022 | 250 | 0 | 647 | 0 | 0 | 0 | 0 | 0 | 647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21CIHC | CONEY ISLAND HANDBALL COURT | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 213 | HA-D001 |  |  | CONEY ISLAND I(SITE 1B) HANDBALL COURT-FUNDING FOR A HANDBALL COURTATNYCHA'S CONEY ISLAND I(SITE 1B) LOCATED AT 2007 SURF AVENUE. | 2022 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21FAST | FARRAGUT UNDERGROUND STEAM | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 202 | HA-0001 HA-D001 |  |  | FARRAGUT UNDERGROUND STEAM | 2022 | 7498 | 0 | 7490 | 0 | 0 | 0 | 0 | 0 | 7490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21GHCC | INSTALL AWNING AT GLENWOOD HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 218 | HA-D001 |  |  | PB: INSTALL AWNING AT GLENWOOD HOUSES COMMUNITY CENTER--REINSTALL AWNING AT GLENWOOD HOUSES | 2022 | 135 | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SHCC | SHEEPSHEAD HOUSES-COMMUNITY CENTER | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 215 | HA-0001 |  |  | SHEEPSHEAD HOUSES-COMMUNITY CENTER | 2022 | 322 | 0 | 0 | 322 | 0 | 0 | 0 | 0 | 322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SVCU | CAMERA UPGRADES AT SARATOGA VILLAGE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 216 | HA-D001 |  |  | SARATOGA VILLAGE - CAMERAS--CAMERA UPGRADES | 2022 | 750 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21UPCC | BATHROOM RENOVATION AT UNITY PLAZA COMMUNITY CENTER | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 205 | HA-D001 |  |  | UNITY PLAZA COMMUNITY CENTER GIRLS BATHROOM - BATHROOM RENOVATION--BATHROOM UPGRADES FOR THE SCHOOL | 2022 | 164 | 0 | 164 | 0 | 0 | 0 | 0 | 0 | 164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22BCAM | BROWN HOUSES- CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 216 | HA-D001 |  |  | NYCHA- BROWN HOUSES -- CAMERAS | 2022 | 750 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22BCCY | BORINQUEN HOUSES- COMMUNITY CENTER & YMCA UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 201 | HA-D001 |  |  | BORINQUEN HOUSES COMMUNITY CENTER AND YMCA UPGRADE -- FUNDS WILL BE UTILIZED TO FACILITATE UPGRADES AT THE BORINQUEN HOUSES COMMUNITY CENTER AND YMCA. | 2022 | 900 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22BHCC | BUSHWICK HOUSES- COMMUNITY CENTER UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 201 | HA-D001 |  |  | BUSHWICK HOUSES COMMUNITY CENTER UPGRADE -- FUNDS WILL BE UTILIZED TOFACILITATE UPGRADES AT THE BUSHWICK HOUSES COMMUNITY CENTER. | 2022 | 405 | 0 | 405 | 0 | 0 | 0 | 0 | 0 | 405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22BRLC | BREUKELEN HOUSES - LEARNING CENTER | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 218 | HA-D001 |  |  | NYCHA - BREUKELEN HOUSES - LEARNING CENTER -- LEARNING CENTER AT BREUKELEN HOUSES, NYCHA, AT 926 WILLIAMS AVE, BASEMENT, BKLYN. | 2022 | 430 | 0 | 430 | 0 | 0 | 0 | 0 | 0 | 430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22CWLB | CARTER G WOODSON- LOBBY SECURITY | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 216 | HA-D001 |  |  | NYCHA - CARTER G WOODSON HOUSES - LOBBY SECURITY BOOTH -- LOBBY SECURITY BOOTH AT CARTER G WOODSON HOUSES NYCHA, AT 395 POWELL ST, BKLYN | 2022 | 50 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22LCAM | LANGSTON HUGHES HOUSES- CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 216 | HA-D001 |  |  | NYCHA- LANGSTON HUGHES -- CAMERAS | 2022 | 231 | 0 | 231 | 0 | 0 | 0 | 0 | 0 | 231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22LPGU | LINDEN HOUSES- PLAYGROUND RENO | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 205 | HA-D001 |  |  | NYCHA - LINDEN PLAYGROUND -- PLAYGROUND RENOVATION AT LINDEN HOUSES, NYCHA, AT CENTER COURT IN FRONT OF 300 WORTMAN AVE, BKLYN | 2022 | 1591 | 0 | 1591 | 0 | 0 | 0 | 0 | 0 | 1591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22LSTM | LAFAYETTE GARDENS- STEM CENTER CONSTRUCTION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 203 | HA-D001 |  |  | LAFAYETTE GARDENS STEM CENTER -- STEM CENTER CONSTRUCTION/RENOVATION. | 2022 | 501 | 0 | 501 | 0 | 0 | 0 | 0 | 0 | 501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SCAM | SETH LOW HOUSES - CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 216 | HA-D001 |  |  | NYCHA- SETH LOW HOUSES -- CAMERAS | 2022 | 232 | 0 | 232 | 0 | 0 | 0 | 0 | 0 | 232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22UTPR | UNITY TOWERS- CONEY ISLAND SITE 1B- PLAYGROUND | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 213 | HA-D001 |  |  | UNITY TOWERS (CONEY ISLAND SITE 1B) PLAYGROUND RENOVATIONS -- SUPPLEMENTAL FUNDING TO RENOVATE THE PLAYGROUND AT UNITY TOWERS (CONEY ISLANDSITE 1B) | 2022 | 250 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22WMED | WORTMAN HOUSES- E NY CENTER FOR MEDIA ARTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 205 | HA-D001 |  |  | WORTMAN HOUSES - EAST NEW YORK CENTER FOR MEDIA ARTS -- ADDITIONAL FUNDING FOR PROJECT AT 520-530 STANLEY AVENUE, PREVIOUSLY P.S. 4 LOCATION | 2022 | 946 | 0 | 946 | 0 | 0 | 0 | 0 | 0 | 946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 806 | HOUSING PRESERVATION AND DEVEL | HAM24VDGR | VAN DYKE I, II GAS RISERS #10 | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 216 | HA-0001 |  |  | INSTALLATION OF GAS RISERS #10 | 2022 | 7150 | 0 | 0 | 0 | 6500 | 0 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BRNHC | Brownsville Health Center Renovation of interior space | CLINIC RENOVATION AND REHABILITATION |  | HL-0082 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BROWNSVILLE HEALTH CENTER RENOVATION OF INTERIOR SPACE | 2022 | 10000 | 0 | 0 | 0 | 0 | 0 | 4760 | 274 | 5034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BUSHC | Bushwick Health Center exterior renovation/interior upgrades | CLINIC RENOVATION AND REHABILITATION |  | HL-0082 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BUSHWICK HEALTH CENTER EXTERIOR RENOVATION/INTERIOR UPGRADES | 2022 | 6500 | 0 | 0 | 0 | 164 | 4000 | 0 | 0 | 4164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CROWH | CROWN HEIGHTS EXPRESS CLINIC | CLINIC RENOVATION AND REHABILITATION |  | HL-0082 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | EXPRESS CLINIC ON PARTIAL FIRST FLOOR | 2022 | 700 | 0 | 0 | 0 | 0 | 0 | 571 | 0 | 571 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 11
20220309 | BROOKLYN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WLSHC | Williamsburg Health Center Interior Renovation | CLINIC RENOVATION AND REHABILITATION |  | HL-0082 |  |  | WILLIAMSBURG HEALTH CENTER INTERIOR RENOVATION | 2022 | 4400 | 0 | 1314 | 6392 | 3300 | 387 | 0 | 0 | 11393 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 48
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22200601 | ENY: CAPITAL IMPROVEMENTS | ROUTINE RECONSTRUCTION | 205 | HO-D003 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 2094 PITKIN AVENUE, BROOKLYN, N.Y. 11207 | CAPITAL IMPROVEMENTS (SIDEWALK REPAIR, LOBBY UPGRADE, PEDIATRIC CLINIC UPGRADE) AT EAST NEW YORK D&TC | 2022 | 1250 | 1191.98 | 0 | 0 | 0 | 47 | 0 | 0 | 1238.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22200801 | ENY RENOVATE THIRD FLOOR CLINICAL AREAS | ROUTINE RECONSTRUCTION | 205 | HO-D003 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 2094 PITKIN AVENUE, BROOKLYN, N. Y. 11207 | CONSTRUCT WOMEN'S OPTIONS CENTER | 2022 | 2100 | 2022.53 | 0 | 0 | 0 | 64 | 0 | 0 | 2086.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22201610 | RENOVATE BROWNSVILLE CHILD HEALTH CLINIC | ROUTINE RECONSTRUCTION | 216 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 259 BRISTOL STREET, BROOKLYN, NY 11212 | RENOVATE THE BROWNSVILLE CHILD HEALTH CLINIC IN ORDER TO EXPAND PRIMARY CARE HEALTH SERVICES. | 2022 | 3870 | 3162.26 | 0 | 0 | 0 | 679 | 0 | 0 | 3841.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22201611 | RENOVATE CROWN HEIGHTS CHILD HEALTH CLINIC | ROUTINE RECONSTRUCTION | 208 | HO-0214 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 1218 PROSPECT PLACE, BROOKLYN, NY 11213 | RENOVATE THE CROWN HEAIGHTS CHILD HEALTH CLINIC IN ORDER TO EXPAND PRIMARY CARE HEALTH SERVICES. | 2022 | 464 | 715.78 | 10 | 0 | 0 | 105 | 0 | 0 | 830.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22201901 | ENY: MODERNIZE 2 PASSENGER ELEVATORS | ROUTINE RECONSTRUCTION |  | HO-0214 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 2094 PITKIN AVENUE, BROOKLYN, NY 11207 | MODERNIZE 2 PASSENGER ELEVATORS AT NYC HEALTH + HOSPITALS / GOTHAM HEALTH, EAST NEW YORK. | 2022 | 634 | 780 | 0 | 250 | 0 | 0 | 0 | 0 | 1030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22202001 | ENY WATER SYSTEM STRUCTURAL RESTORATION | ROUTINE RECONSTRUCTION |  | HO-0214 |  | EAST NEW YORK: 2094 PITKIN AVE |  | 2022 | 154 | 0 | 328 | 0 | 0 | 0 | 0 | 0 | 328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22202201 | ENY: BATHROOM ADA | ROUTINE RECONSTRUCTION |  | HO-K001 |  | 2094 PITKIN AVE, BROOKLYN, NY 11207 | N/A | 2022 | 510 | 0 | 100 | 410 | 0 | 0 | 0 | 0 | 510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 22202202 | EAST NEW YORK WATER INFILTRATION | ROUTINE RECONSTRUCTION | 209 | HO-0214 |  | 2094 PITKIN AVENUE, BROOKLYN, NY 11207 | NYC HEALTH + HOSPITALS/ EAST NEW YORK (2094 PITKIN AVE, BROOKLYN, NEWYORK) WATER INFILTRATION | 2022 | 1213 | 0 | 1256 | 0 | 0 | 0 | 0 | 0 | 1256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 23201901 | MCKINNEY MODERNIZE 3 PASSENGER ELEVATORS | ROUTINE RECONSTRUCTION |  | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 594 ALBANY AVENUE, BROOKLYN, NY 11203 | NYC HEALTH + HOSPITALS / MCKINNEY, BRKLYN: MODERNIZE 3 PASSENGER ELEVATORS | 2022 | 909 | 868 | 0 | 0 | 0 | 41 | 0 | 0 | 909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 23202001 | MCKINNEY FRONT LOBBY RENOVATIONS | ROUTINE RECONSTRUCTION |  | HO-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 594 ALBANY AVENUE, BROOKLYN, NY 11203 | FRONT LOBBY RENOVATIONS AT NYC HEALTH + HOSPITALS/MCKINNEY | 2022 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 23202101 | MCKINNEY: FIRE ALARM | ROUTINE RECONSTRUCTION |  | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 594 ALBANY, AVENUE BROOKLYN NY 11203 | FIRE ALARM UPGRADES | 2022 | 165 | 0 | 0 | 165 | 0 | 0 | 0 | 0 | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26201101 | GOTHAM: CONSTRUCT VANDERBILT AVENUE HEALTH CENTER AT S.I. | ROUTINE RECONSTRUCTION | 213 | HO-D003 HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 2601 OCEAN PARKWAY, BROOKLYN, N. Y. 11235 | THE PURPOSE OF THIS PROJECT IS TO CONSTRCUT A HEALTH CENTER AT VANDERBILT AVENUE. | 2022 | 23685 | 21217.86 | 0 | 0 | 0 | 6884 | 0 | 0 | 28101.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26201402 | CONEY ADD DEHUMIDICATION & ADD'L COOLING CAPACITY TO THE ORs | ROUTINE RECONSTRUCTION | 213 | HO-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 2601 OCEAN PARKWAY, BROOKLYN, NY 11235 | ADD DEHUMIDICATION AND ADDITIONAL COOLING CAPACITY TO THE ORS AT CONEY ISLAND HOSPITAL, A FUNDING TRANSFER OF $966,000 WAS APPROVED FROM PROJECT ID 26201201 (RENOVATE PSYCH ED) BY THE CITY COUNCIL ON 8/26/13. | 2022 | 966 | 929.34 | 0 | 0 | 36 | 0 | 0 | 0 | 965.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26201902 | CONEY UPGRADE FIRE ALARM SYSTEM | ROUTINE RECONSTRUCTION |  | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 2601 OCEAN PARKWAY, BROOKLYN, NY 11235 | CONEY ISLAND HOSPITAL (2601 OCEAN PARKWAY, BK), UPGRADE THE FIRE ALARM SYSTEM THROUGHOUT THE HOSPITAL CAMPUS IN THE MAIN BLDG, TOWER BLDG, HAMMETT PAVILION AND POWERHOUSE BLDG. | 2022 | 268 | 0 | 0 | 0 | 268 | 0 | 0 | 0 | 268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26202001 | CONEY MODERNIZE 9 ELEVATORS IN MAIN BUILDING | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 2601 OCEAN PKWY, BK NY 11235 | MODERNIZE 9 ELEVATORS IN MAIN BUILDING AT CONEY ISLAND HOSPITAL. | 2022 | 4541 | 4366.3 | 175 | 0 | 0 | 0 | 0 | 0 | 4541.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26202101 | CONEY ROOF REPLACEMENT MAIN BUILDING | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 2601 OCEAN PARKWAY, BROOKLYN NY 11235 | ROOF REPLACEMENT MAIN BUILDING | 2022 | 1250 | 0 | 200 | 1050 | 0 | 0 | 0 | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26202103 | CONEY DENTAL SUITE | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 2601 OCEAN PARKWAY, BROOKLYN, NY 11235 | N/A | 2022 | 4000 | 0 | 168 | 3832 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 26202104 | CONEY ISLAND AMBULATORY CARE CENTER | ROUTINE RECONSTRUCTION |  | HO-K001 HO-D003 HO-0214 |  | 2601 OCEAN PARKWAY, BROOKLYN, NY 11235 | NYC HEALTH + HOSPITALS/ CONEY ISLAND AMBULATORY CARE CENTER | 2022 | 17244 | 0 | 1000 | 744 | 15500 | 0 | 0 | 0 | 17244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201201 | CUMBERLAND: RENOVATE CHEMICAL DEPENDENCY DEPARTMENT | ROUTINE RECONSTRUCTION | 202 | HO-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 100 NORTH PORTLAND AVENUE, BROOKLYN, NY 11205 | THE PURPOSE OF THIS PROJECT IS TO RENOVATE CHEMICAL DEPENDENCY DEPARTMENT AT CONEY ISLAND HOSPITAL | 2022 | 273 | 0 | 0 | 0 | 0 | 0 | 273 | 0 | 273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201301 | CUMBERLAND: RENOVATE PEDIATRIC PRACTICE DEPARTMENT | ROUTINE RECONSTRUCTION | 202 | HO-K001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 100 NORTH PORTLAND AVENUE, BROOKLYN, NY 111205 | RENOVATE/UPGRADE PEDIATRIC PRACTICE AT CUMBERLAND D&TC TO PROVIDE FORMORE EXAM ROOMS, PATIENT ROOMS, BATHROOMS AND NURSES' STATIONS. | 2022 | 490 | 0 | 0 | 0 | 490 | 0 | 0 | 0 | 490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201515 | CUMBERLAND: RENOVATE WOMEN'S HEALTH SVCS DEPT. | ROUTINE RECONSTRUCTION | 202 | HO-D003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 100 NORTH PORTLAND AVENUE, BROOKLYN, NY 11206 | RECONIGURE EXISTING WOMEN'S HEALTH SERVICES DEPARTMENT TO MAKE SERVICES ACCESSIBLE FOR WOMEN WITH DISABILITIES. | 2022 | 524 | 67.17 | 0 | 0 | 0 | 0 | 133 | 0 | 200.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201610 | RENOVATE BEDFORD HEALTH CLINIC | ROUTINE RECONSTRUCTION | 203 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 485 THROOP AVENUE, BROOKLYN, NY 11221 | RENOVATE THE BEDFORD HEALTH CLINIC IN ORDER TO EXPAND PRIMARY CARE HEALTH SERVICES. | 2022 | 3136 | 2976.25 | 0 | 0 | 0 | 132 | 0 | 0 | 3108.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201702 | CUMBERLAND: CONSTRUCT NEW DENTAL FACILITY | ROUTINE RECONSTRUCTION | 202 | HO-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 100 NORTH PORTLAND AVENUE, BROOKLYN, NY 11205 | CONSTRUCT NEW DENTAL FACILITY AT NYC HEALTH + HOSPITALS ¦ CUMBERLAND | 2022 | 825 | 89.3 | 0 | 736 | 0 | 0 | 0 | 0 | 825.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 27201803 | CUMBERLAND: FACADE REHABILITATION BUILDING B & C | ROUTINE RECONSTRUCTION |  | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 100 NORTH PORTLAND AVENUE | FACADE REHABILITATION, INCLUDING DESIGN, CONSTRUCTION, AND ASBESTOS ABATEMENT | 2022 | 1658 | 1327.11 | 402 | 0 | 0 | 0 | 0 | 0 | 1729.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201301 | KINGS UPGRADE FIRE ALARM SYSTEM IN "ABC" & "T" BLDGS | ROUTINE RECONSTRUCTION | 209 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 451 CLARKSON AVENUE, BROOKLYN, NY 11203 | INSTALL UPDATED FIRE ALARM SYSTEM AT KINGS COUNTY HOSPITAL CENTER. MANY PORTIONS OF THE EXISTING SYSTEM ARE OBSOLETE AND DO NOT MEET CURRENT FDNY CODE REQUIREMENT. | 2022 | 5395 | 4928.63 | 90 | 343 | 0 | 0 | 0 | 0 | 5361.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201501 | BED-STUY REHAB CTR: FIRE ALARM SYSTEM REPLACEMENT | ROUTINE RECONSTRUCTION | 203 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 722 MYRTLE AVENUE, BROOKLYN, NY 11205 | CURRENT FIRE ALARM SYSTEM AT THE BEDFORD-STUYVESANT ALCOHOLISM TREATMENT CENTER IS OBSOLETE. A COMPLETE REPLACEMENT WILL ENSURE PATIENT ANDSTAFF SAFETY. | 2022 | 200 | 41.16 | 0 | 0 | 356 | 0 | 0 | 0 | 397.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201610 | KCHC: LOCAL LAW -11 COMPLIANCE - BLDG T | ROUTINE RECONSTRUCTION | 209 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 451 CLARKSON AVENUE, BROOKLYN, N. Y. 11203 | THE PURPOSE OF THIS PROJECT IS TO RENOVATE BUILDING "T" AT KINGS COUNTY HOSPITAL CENTER USING LOCAL LAW 11- FUNDS FOR LOCAL LAW 11 COMPLIANCE. | 2022 | 618 | 13853.34 | 2299 | 0 | 0 | 0 | 0 | 0 | 16152.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201611 | KCHC: LOCAL LAW 11 COMPLIANCE - BLDG ABC | ROUTINE RECONSTRUCTION | 209 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 451 CLARKSON AVENUE, BROOKLYN, N. Y. 11203 | THE PURPOSE OF THIS PROJECT IS TO RENOVATE BUILDINGS A, B, AND C AT KINGS COUNTY HOSPITAL CENTER USING LOCAL LAW 11- FUNDS FOR LOCAL LAW 11 COMPLIANCE. | 2022 | 1100 | 851.96 | 0 | 0 | 0 | 247 | 0 | 0 | 1098.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201612 | KCHC: BLDG "P" FACADE REMEDIATION - LOCAL LAW 11 COMPLIANCE | ROUTINE RECONSTRUCTION | 209 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 451 CLARKSON AVENUE, BROOKLYN, N. Y. 11203 | THE PURPOSE OF THIS PROJECT IS TO RENOVATE BLDNG "P" FACADE AT KINGS COUNTY HOSPITAL CENTER USING LOCAL LAW 11- FUNDS FOR LOCAL LAW 11 COMPLIANCE. | 2022 | 17606 | 14609.54 | 675 | 2323 | 0 | 0 | 0 | 0 | 17607.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201614 | KINGS BOILER REPLACEMENT | ROUTINE RECONSTRUCTION | 209 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 451 CLARKSON AVENUE, BROOKLYN, NY 11203 | REPLACE BOILER AT KINGS COUNTY HOSPITAL CENTER, BROOKLYN, NY. | 2022 | 5000 | 4568.74 | 0 | 0 | 432 | 0 | 0 | 0 | 5000.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201802 | KCHC: REPLACEMENT OF C6 HEMODIALYSIS WATER TREATMENT SYSTEM | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 451 CLARKSON AVENUE, BROOKLYN, NY 11203 | REPLACEMENT OF C6 HEMODIALYSIS WATER TREATMENT & DISTRIBUTION SYSTEM AT KINGS COUNTY HOSPITAL CENTER. | 2022 | 2697 | 2145.86 | 105 | 100 | 0 | 0 | 0 | 0 | 2350.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29201803 | KINGS, ABC BUILDING ELECTRICAL FEEDER REPLACEMENT | ROUTINE RECONSTRUCTION |  | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 451 CLARKSON AVENUE, BROOKLYN, NY 11203 | ABC BUILDING ELECTRICAL FEEDER REPLACEMENT AT KINGS COUNTY HOSPITAL | 2022 | 460 | 417.03 | 0 | 43 | 0 | 0 | 0 | 0 | 460.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202001 | KINGS REHABILITATE STEAM TUNNEL UNDER WINTHROP STREET | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 451 CLARKSON AVENUE, BROOKLYN, NY 11203 | KINGS COUNTY HOSPITAL CENTER: REHABILITATE STEAM TUNNEL UNDER WINTHROP STREET | 2022 | 26146 | 475.8 | 2500 | 23170 | 0 | 0 | 0 | 0 | 26145.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202002 | KINGS BUILDING D ELEVATOR MODERNIZATION | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 451 CLARKSON AVE, BK, NY, 11203 |  | 2022 | 2090 | 1900 | 0 | 190 | 0 | 0 | 0 | 0 | 2090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202101 | KINGS RESTORATION OF WEST SMOKE STACK | ROUTINE RECONSTRUCTION |  | HO-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 451 CLARKSON ST, BROOKLYN, NY 11203 | NA | 2022 | 600 | 0 | 0 | 0 | 0 | 0 | 53 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202102 | KINGS: WELLNESS CENTER | NEW FACILITIES |  | HO-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 451 CLARKSON AVENUE, BROOKLYN, NY 11203 | CONSTRUCT NEW WELLNESS CENTER FOR PHYSICIANS | 2022 | 70 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202103 | KINGS P BUILDING MORGUE | ROUTINE RECONSTRUCTION |  | HO-0214 |  |  | RENOVATION OF MORGUE | 2022 | 575 | 0 | 0 | 575 | 0 | 0 | 0 | 0 | 575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202104 | KINGS BUILDING D ELECTRICAL UPGRADES | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 451 CLARKSON ST, BROOKLYN, NY 11203 | KINGS BLDG D ELECTRICAL UPGRADES | 2022 | 2268 | 0 | 268 | 2000 | 0 | 0 | 0 | 0 | 2268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202114 | KINGS PHARMACY COMPOUNDING USP 797/800 COMPLIANCE | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 451 CLARKSON AVENUE, BROOKLYN, NY 11203 | NYC HEALTH + HOSPITALS ¦ KINGS COUNTY: RENOVATION OF S BUILDING PHARMACY TO COMPLY WITH CURRENT USP 797 AND 800 STANDARDS FOR COMPOUNDING ROOMS. | 2022 | 1602 | 0 | 1210 | 320 | 0 | 0 | 0 | 0 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202115 | KINGS HVAC UPGRADE/TELEMETRY ROOM | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 451 CLARKSON AVENUE, BROOKLYN, NY 11203 | KINGS HVAC | 2022 | 385 | 0 | 385 | 0 | 0 | 0 | 0 | 0 | 385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202116 | KINGS: L&D RENOVATION EXPANSION | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 451 CLARKSON AVENUE, BROOKLY, NY 11203 | L&D RENOVATION EXPANSION | 2022 | 13000 | 0 | 3000 | 0 | 27000 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202201 | Kings Replacement of Water Feeder Pipes for the Boilers Oper | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 451 CLARKSON AVE, BROOKLYN, NY 11207 | KINGS REPLACEMENT OF WATER FEEDER PIPES FOR THE BOILER OPERAT | 2022 | 0 | 0 | 961 | 0 | 0 | 0 | 0 | 0 | 961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202202 | KINGS: ELECTRICAL REMEDIAL WORK- S BUILDING | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 451 CLARKSON AVENUE, BROOKLYN, NY 11203 | NYC HEALTH+HOSPITALS/ KINGS (451 CLARKSON AVE. BROOKLYN, NEW YORK) KINGS: ELECTRICAL REMEDIAL WORK- S BUILDING | 2022 | 10000 | 0 | 1000 | 9000 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 29202203 | KINGS: E BLDG ELEVATOR MODERNIZATION | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 451 CLARKSON AVENUE, BROOKLYN, NY 11203 | E BLDG ELEVATOR MODERNIZATION | 2022 | 5000 | 0 | 500 | 3000 | 1500 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48200803 | WOODHULL: OB UNIT EXPANSION | ROUTINE RECONSTRUCTION | 203 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 760 BROADWAY, BROOKLYN, NY 11206 | CREATE 14 PATIENT ROOMS (2 LABOR & DELIVERY ROOMS, 1 BREASTFEEDING RM, 1 MEDICATION/TREATMENT RM, A WELL BABY NURSERY RM, A NURSES STATION,A UTILITY ROOM, ETC. | 2022 | 3578 | 2930.52 | 0 | 107 | 0 | 0 | 0 | 0 | 3037.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201402 | WOODHULL: ESTABLISH CPEP | ROUTINE RECONSTRUCTION |  | HO-0214 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 760 BROADWAY, BROOKLYN, NY 11206 | RENOVATE THE CPEP DEPARTMENT AT WOODHULL MEDICAL & MENTAL HEALTH CENTER. | 2022 | 1817 | 1665.91 | 0 | 0 | 127 | 0 | 0 | 0 | 1792.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201516 | WOODHULL: AMBULATORY CARE RENOVATIONS (8-300) | ROUTINE RECONSTRUCTION | 203 | HO-D003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 760 BROADWAY, BROOKLYN, NY 11206 | RECONIGURE EXISTING WOMEN'S HEALTH PAVILION TO MAKE SERVICES ACCESSIBLE FOR WOMEN WITH DISABILITIES. | 2022 | 256 | 49.3 | 0 | 133 | 0 | 0 | 0 | 0 | 182.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201602 | WOODHULL: LOCAL LAW 11 COMPLIANCE | ROUTINE RECONSTRUCTION |  | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | THE PURPOSE OF THIS PROJECT IS TO RENOVATE BUILDINGS AT WOODHULL HOSPITAL CENTER USING LOCAL LAW 11- FUNDS FOR LOCAL LAW 11 COMPLIANCE. | THE PURPOSE OF THIS PROJECT IS TO RENOVATE BUILDINGS AT WOODHULL HOSPITAL CENTER USING LOCAL LAW 11- FUNDS FOR LOCAL LAW 11 COMPLIANCE. | 2022 | 8036 | 7508.23 | 528 | 0 | 0 | 0 | 0 | 0 | 8036.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201610 | RENOVATE BUSHWICK COMMUNICARE | ROUTINE RECONSTRUCTION | 204 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 335 CENTRAL AVENUE, BROOKLYN, NY 11221 | RENOVATE THE BUSHWICK COMMUNICARE HEALTH CLINIC IN ORDER TO EXPAND PRIMARY CARE HEALTH SERVICES. | 2022 | 3319 | 4227.74 | 0 | 0 | 0 | 182 | 0 | 0 | 4409.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201901 | WOODHULL: CPEP RENOVATION | ROUTINE RECONSTRUCTION |  | HO-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 760 BROADWAY, BROOKLYN, NY 11203 | CPEP RENOVATION | 2022 | 150 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201902 | WOODHULL: EMERGENCY DEPARTMENT RENOVATION | ROUTINE RECONSTRUCTION |  | HO-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 760 BROADWAY, BROOKLYN, NY 11203 | EMERGENCY DEPARTMENT RENOVATION | 2022 | 5000 | 3584 | 239 | 0 | 1177 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48201903 | WOODHULL: RETAIL PHARMACY RENOVATION | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 760 BROADWAY, BROOKLYN, NY 11206 | RENOVATE RETAIL PHARMACY AT WOODHULL MEDICAL & MENTAL HEALTH CENTER | 2022 | 37 | 0 | 0 | 1857 | 0 | 0 | 0 | 0 | 1857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202001 | WOODHULL: CREATE 14 EXAM ROOMS FOR ADULT MEDICINE CLINIC | ROUTINE RECONSTRUCTION |  | HO-D003 |  | 760 BROADWAY, BROOKLYN, NY 11206 | CREATE 14 EXAM ROOMS FOR THE ADULT MEDICINE CLINIC AT NYC HEALTH + HOSPITALS / WOODHULL | 2022 | 842 | 0 | 0 | 0 | 842 | 0 | 0 | 0 | 842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202002 | WOODHULL: Modernize Elevators | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 760 BROADWAY, BROOKLYN, NY 11206 | MODERNIZATION OF ELEVATORS | 2022 | 2232 | 1972.98 | 0 | 259 | 0 | 0 | 0 | 0 | 2231.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202101 | WOODHULL: COMMAND CENTER MODERNIZATION | ROUTINE RECONSTRUCTION |  | HO-D003 HO-0214 |  | 760 BORADWAY, BROOKLYN, NY 11206 | SURVEILLANCE MODERNIZATION | 2022 | 258 | 0 | 270 | 0 | 0 | 0 | 0 | 0 | 270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202102 | WOODHULL: ELECTRICAL UPGRADES | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 760 BROADWAY, BROOKLYN, NY 11206 | ELECTRICAL UPGRADES AT WOODHULL | 2022 | 1540 | 1539.47 | 125 | 1 | 0 | 0 | 0 | 0 | 1665.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202105 | WOODHULL: SIM LAB | ROUTINE RECONSTRUCTION |  | HO-K001 |  | 760 BROADWAY, BROOKLYN, NY 11206 | FY22 SEC 211 PROJECT ADD (90) NYC HEALTH + HOSPITALS - WOODHULL MEDICAL CENTER: SIMLAB - MATERNAL CHILD HEALTH | 2022 | 90 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202106 | WOODHULL GENERATOR REPLACEMENT | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 760 BROADWAY, BROOKLYN, NY 11206 | WOODHULL GENERATOR REPLACEMENT | 2022 | 10000 | 0 | 500 | 9500 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202107 | WOODHULL OIL SPILL REMEDIATION | ROUTINE RECONSTRUCTION |  | HO-0214 |  |  | WOODHULL OIL SPILL REMEDIATION | 2022 | 450 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202108 | WOODHULL DECANTING/RELOCATION (CHS OTxHU) | ROUTINE RECONSTRUCTION |  | HO-0341 |  | 760 BROADWAY, BROOKLYN, NY 11206 | WOODHULL DECANTING | 2022 | 30000 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202201 | WOODHULL: NEW WOMEN'S HEALTH PAVILLION (7-300) | ROUTINE RECONSTRUCTION |  | HO-K001 |  | 760 BROADWAY, BROOKLYN, NY 11206 | N/A | 2022 | 1950 | 0 | 400 | 1550 | 0 | 0 | 0 | 0 | 1950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202202 | WOODHULL INTERVENTIONAL RADIOLOGY- SPECIAL PROCEDURE UNIT | ROUTINE RECONSTRUCTION |  | HO-0214 |  |  | NYC HEALTH + HOSPITALS ¦ WOODHULL (760 BROADWAY, BROOKLYN, NEW YORK) INTERVENTIONAL RADIOLOGY- SPECIAL PROCEDURE UNIT | 2022 | 2200 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202203 | WOODHULL: OTXHU FULL ROOF REPLACEMENT | ROUTINE RECONSTRUCTION |  | HO-0341 |  | 760 BROADWAY, BROOKLYN, NY 11206 | OTXHU FULL ROOF REPLACEMENT AT NYC H+H / WOODHULL | 2022 | 12000 | 0 | 439 | 11561 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | 48202205 | WOODHULL OUTPOSTED THERAPEUTIC UNITS (CHS OTxHU) | ROUTINE RECONSTRUCTION |  | HO-0341 |  | 760 BROADWAY | CONSTRUCTION OF OUT-POSTED THERAPEUTIC HOUSING UNITS (OTXHU) AT NYC HEALTH + HOSPITALS ¦ WOODHULL HOSPITAL | 2022 | 152687 | 0 | 0 | 111687 | 41000 | 0 | 0 | 0 | 152687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC407 | Cumberland : Boiler Plant Replacement | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 205 | HO-0214 |  |  | REPLACE EXISTING HPS BOILERS & ANCILLARY EQUIPMENT WITH NEW HIGH EFFICIENCY LOW EMISSIONS FIRETUBE STEAM BOILERS AND ANCILLARY EQUIPMENT. INSTALL NEW EFFICIENT MODULATING VERTICAL DOMESTIC HOT WATER BOILERS. NEW CONTROLS WILL BE INSTALLED | 2022 | 8542 | 7936.63 | 605 | 0 | 0 | 0 | 0 | 0 | 8541.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC607 | KINGS LIGHTING UPGRADES - PHASE 2 | ROUTINE RECONSTRUCTION |  | PU-0025 HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 451 CLARKSON AVENUE, BROOKLYN, NY 11203 | LIGHTING UPGRADES - PHASE 2 AT KINGS COUNTY HOSPITAL CENTER | 2022 | 1229 | 711.89 | 0 | 423 | 0 | 0 | 0 | 0 | 1134.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | CIH1 | CONEY MODERNIZE GENERAL CARE INPATIENT/AMB CARE FACILITIES | MAJOR OR PARTIAL HOSPITAL RECONSTRUCTION | 200 | HO-0377 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 2601 OCEAN PARKWAY, BROOKLYN, NY 11235 | CONEY ISLAND HOSPITAL - MAJOR MODERNIZATION PROJECT TO CONSOLIDATE AND MODERNIZE THE FENERAL CARE INPATIENT & AMBULATORY CARE FACILITIES; | 2022 | 92012 | 37912.77 | 0 | 0 | 0 | 1645 | 0 | 0 | 39557.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 819 | HEALTH AND HOSPITALS CORP | GABIHHC | GROUP ATTACHMENT BASED INTERVENTION | CHILD WELFARE FACILITIES | 200 | CS-0003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TBD | 2022 | 759 | 302.95 | 83 | 0 | 0 | 0 | 0 | 0 | 385.95 | 544.18 | 10 | 0 | 0 | 0 | 0 | 0 | 554.18
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26-STAB20 | 26th Ward Primary Settling Tank & Solid Handling | PLANT COMPONENT STABILIZATION | 218 205 216 | WP-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EMERGENCY INSTALLATION OF (3) LOW LEVEL MAIN SEWAGE PUMPS AND MOTOR CONTROLS AT 26TH WARD WPCP | 2022 | 232200 | 193816.98 | 6033 | 0 | 0 | 0 | 0 | 0 | 199849.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-144-L | INSTALLATION OF (13) NEW CENTRIFUGES @ 26TH WARD WPCP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  | 12266 FLATLANDS AVENUE, BROOKLYN NEW YORK 11270 | INSTALLATION OF (13) NEW CENTRIFUGES ATH THE 26TH WARD WPCP | 2022 | 50850 | 15000.84 | 0 | 11000 | 0 | 0 | 0 | 34686 | 60686.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-148-L | TRC - CONS OF DISINFECTION FACILITIES AT 26TH WARD WPCP | CONSENT DECREE UPGRADING AND CONSTRUCTION | 200 | WP-0282 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CONSTRUCTION OF DISINFECTION FACILITIES AT 26TH WARD WPCP | 2022 | 33000 | 0 | 5895 | 0 | 5217 | 26316 | 0 | 0 | 37428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-149 | RECONSTRUCT TIDE GATES/EFFLUENT CHAMBERS @ SPRING CREEK | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 122-66 FLATLANDS AVENUE, BROOKLYN, NEW YORK 11207 | RECONSTRUCTION OF EFFLUENT CHAMBERS AND RETROFITTING OF 48 TIDE GATESIN THE EXISTING WALL OPENINGS AT THE 26TH WARD WWTP. | 2022 | 7150 | 8900 | 150 | 0 | 0 | 0 | 0 | 0 | 9050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-156-L | REPLACE WASTE ACTIVATED SLUDGE PIPING AT 26TH WARD WPCP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACE WASTE ACTIVATED SLUDGE PIPING AT 26TH WARD WPCP | 2022 | 6600 | 0 | 0 | 0 | 2300 | 0 | 0 | 29500 | 31800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-167-L | Installation of SCADA System at 26W WRRF | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  |  | INSTALLATION OF SCADA SYSTEM AT 26W WRRF | 2022 | 12000 | 0 | 0 | 0 | 1000 | 0 | 0 | 11000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | 26W-21 | HIGH LEVEL MAIN SEWAGE PUMP IMPROVEMENTS AT 26TH WARD WPCP | PLANT COMPONENT STABILIZATION | 200 | WP-0206 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HIGH LEVEL MAIN SEWAGE PUMP IMPROVEMENTS AT 26TH WARD WPCP | 2022 | 18156 | 16800.88 | 174 | 0 | 0 | 0 | 0 | 0 | 16974.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-828 | Dist WM work in 86th St between Bay 20th & 28th St, BKLYN | AUGMENTATION OF WATER SUPPLY SYSTEMS | 211 | SE-0002K WM-0001 SE-0200K |  |  | DISTRIBUTION WATER MAIN WORK IN 86TH STREET BETWEEN BAY 20TH STREET AND BAY 28TH STREET, BOROUGH OF BROOKLYN | 2022 | 6878 | 0 | 0 | 976 | 7604 | 0 | 0 | 0 | 8580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | BED-834 | Dist WM work in Nostrand Ave from Dean St to Prospect Pl, BK | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 200 | WM-0001 |  |  | DISTRIBUTION WATER MAIN WORK IN NOSTRAND AVE FROM DEAN ST TO PROSPECTPL, BROOKLYN. | 2022 | 28505 | 0 | 0 | 0 | 28505 | 0 | 0 | 0 | 28505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-113-L | RECONSTRUCT (4) ENGINE GENERATOR CONTROL SYSTEM | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  | AVENUE "Z" AND KNAPP STREET, BROOKLYN, NEW YORK 11235 | RECONSTRUCTION OF (4) FOUR ENGINE GENERATOR CONTROL SYSTEM AT THE CONEY ISLAND WPCP | 2022 | 70450 | 303.34 | 0 | 23561 | 0 | 0 | 0 | 0 | 23864.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-119-L | RECONSTRUCTION OF GATES & MSP MOTORS & CONTROLS @ C.I. | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  | AVENUE Z AND KNAPP STREET, BROOKLYN, N.Y. 11208 | RECONSTRUCTION OF GATES AND MSP MOTORS AND CONTROL AT CONEY ISLAND WWTP | 2022 | 23294 | 141986.06 | 142 | 0 | 0 | 0 | 0 | 0 | 142128.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-124 | RECONSTRUCTION OF HEATING SYSTEM AT CONEY ISLAND WPCP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  |  | RECONSTRUCTION OF HEATING SYSTEM AT CONEY ISLAND WPCP | 2022 | 10000 | 0 | 0 | 0 | 7000 | 0 | 0 | 70000 | 77000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-140-L | INSTALL ODOR CONTROL PANELS FOR AERATION SCRUBBER SYSTEM | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  | AVENUE Z AND KNAPP STREET, BROOKLYN, N.Y. 11208 | INSTALLATION OF ODOR CONTROL PANELS FOR THE AERATION SCRUBBER SYSTEM AT THE CONEY ISLAND WWTP | 2022 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | 2100 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CI-142-L | RECONSTRUCTION OF BLOWER CONTROL SYSTEMS @ CONEY ISLAND | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | AVENUE Z AND KNAPP STREET, BROOKLYN, N.Y. 11208 | RECONSTRUCTION OF THE BLOWER CONTROL SYSTEMS AT THE CONEY ISLAND WASTEWATER TREATMENT PLANT, BROOKLYN, NEW YORK. | 2022 | 2763 | 0 | 0 | 3895 | 0 | 0 | 0 | 0 | 3895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-GC-SFS | CONSTRUCTION OF GOWANUS CSO RETENTION FAC SUPERFUND SITE | WATER QUALITY MANDATES | 299 | WP-0169 |  |  | CONSTRUCTION OF OF TWO IN-LINE SEWAGE/STORMWATER RETENTIONS TANKS TO RETAIN STORMWATER WHICH CURRENTLY DISCHARGES THROUGH OUTFALLS RH-034 AND OH-007 AT THE GOWANUS CANAL SUPERFUND SITE | 2022 | 348000 | 213385.49 | 51002 | 537411 | 37298 | 269723 | 0 | 328552 | 1437371.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC | FLUSHING TUNNEL REACTIVATION & GOWANUS CANAL FORCE MAIN | WATER QUALITY MANDATES | 299 | WP-0169 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | GOWANUS CANAL & FLUSHING TUNNEL, BROOKLYN,NY | FLUSHING TUNNEL REACTIVATION AND GOWANUS CANAL FORCE MAIN, (FORMERLY IN WP-152) CONTS. 15 & 16 | 2022 | 126428 | 197120.45 | 279 | 0 | 0 | 0 | 0 | 0 | 197399.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-GC-SP | CONSTRUCTION OF GOWANUS CANAL PILOT SPONGE PARK | WATER QUALITY MANDATES | 200 | P-D017 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DESIGN AND CONSTRUCTION OF GOWANUS CANAL PILOT SPONGE PARK | 2022 | 1273 | 593.67 | 116 | 0 | 0 | 0 | 0 | 0 | 709.67 | 535 | 0 | 0 | 0 | 0 | 0 | 0 | 535
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKN24 | Reconstruction of Existing Sewers, North Brooklyn | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 200 | SE-0002K EP-0007 |  |  | RECONSTRUCTION OF EXISTING SEWERS, NORTH BROOKLYN. THIS IS A 1 YEAR CONTRACT. THE TARGETED START DATE FOR THIS CONTRACT IS AS SOON AS THE PREVIOUS CONTRACT, EC-SEKN23, EXPIRES. | 2022 | 8720 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEKS24 | Reconstruction of Existing Sewers, South Brooklyn | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 200 | SE-0002K EP-0007 |  |  | RECONSTRUCTION OF EXISTING SEWERS, SOUTH BROOKLYN. THIS IS A 1 YEAR CONTRACT. THE TARGETED START DATE FOR THIS CONTRACT IS AS SOON AS THE PREVIOUS CONTRACT, EC-SEKS23, EXPIRES. | 2022 | 8720 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GKCI05-2A | GI- CONS OF ROW GREEN INFRASTRUCTURE IN CI-005 PHASE 2A | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 |  |  | GI-CONSTRUCT RIGHT-OF-WAY GREEN INFRASTRUCTURE PRACTICES SUCH AS RAINGARDENS, INFILTRATION BASINS AND STROMWATER GREEN STREETS IN CONEY ISLAND CREEK WATERSHED CI-005 | 2022 | 33810 | 0 | 0 | 0 | 33200 | 0 | 0 | 0 | 33200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GKCI05-3A | GI- CONS OF ROW GREEN INFRASTRUCTURE IN CI-005 PHASE 3A | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 |  |  | GI- CONSTRUCT RIGHT-OF-WAY GREEN INFRASTRUCTURE PRACTICES SUCH AS RAIN GARDENS, INFILTRATION BASINS AND STORMWATER GREEN STREETS IN CONEY ISLAND CREEK WATERSHED CI-005. | 2022 | 33810 | 0 | 0 | 33200 | 0 | 0 | 0 | 0 | 33200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-A | GI - INSTALL GI AT NYPD PCTS 75, 77 & 115 PARKING LOTS | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 |  |  | GI - INSTALL GREEN INFRASTRUCTURE AT NEW YORK POLICE DEPARTMENT PRECINCTS 75, 77 & 115 PARKING LOTS | 2022 | 1296 | 0 | 0 | 1296 | 0 | 0 | 0 | 0 | 1296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-B | GI - INSTALL GI AT NYPD PCTS 73, 79 & 81 PARKING LOTS | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | INSTALL GREEN INFRASTRUCTURE AT NEW YORK POLICE DEPARTMENT PRECINCTS 73, 79 & 81 PARKING LOTS | 2022 | 1804 | 0 | 0 | 0 | 0 | 1804 | 0 | 0 | 1804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-C | GI - INSTALL GI AT NYPD 83 PRECINCT PARKING LOTS | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | GI - INSTALL GREEN INFRASTRUCTURE AT NEW YORK POLICE DEPARTMENT PRECINCT 83 PARKING LOTS | 2022 | 1016 | 0 | 0 | 0 | 0 | 1016 | 0 | 0 | 1016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | GK-PD-D | GI - INSTALL GI AT NYPD PCTS 43, 71,107 & FLUSHING ARMORY | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | GI - INSTALL GREEN INFRASTRUCTURE AT NEW YORK POLICE DEPARTMENT PRECINCTS 43, 71, 107 PARKING LOTS & FLUSHING ARMORY | 2022 | 2379 | 0 | 0 | 0 | 0 | 2379 | 0 | 0 | 2379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-159 | TRC - NEWTOWN CREEK DECLORINATION FACILITY | CONSENT DECREE UPGRADING AND CONSTRUCTION | 200 | WP-0282 |  | 301 GREEN POINT AVENUE BROOKLYN, N.Y. 11222 | NEWTOWN CREEK DECLORINATION | 2022 | 8974 | 13520.91 | 261 | 0 | 0 | 0 | 0 | 0 | 13781.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | NC-GATEGP | CONSTRUCTION OF NEWTOWN CREEK GATEWAY TO GREENPOINT PROJECT | WATER QUALITY MANDATES | 200 | WP-D169 |  |  | CONSTRUCTION OF GREEN SPACE FOR A 12,000 SF PARCEL AT THE CORNER OF GREENPOINT AND KINGSLAND AVENUES | 2022 | 150 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-112-L | REPLACE MAIN SEWAGE PUMPS & PIPING AT OWLS HEAD WPCP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  | 6700 SHORE ROAD FOOT OF 69TH STREET & THE NARROWS BROOKLYN, N.Y. 11220 | REPLACE MAIN SEWAGE PUMPS & PIPING AT OWLS HEAD WPCP | 2022 | 209700 | 0 | 0 | 0 | 17000 | 0 | 169000 | 0 | 186000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-123 | INSTALL GRAVITY BELT THICKENER & ODOR CTRL @OH WPCP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  |  | ORGANIC LOADING REDUCTION - INSTALLATION OF GRAVITY BELT THICKENER AND ODOR CONTROL FOR THICKENER/DIGESTER COMPLEX @ OWLS HEAD WRRF | 2022 | 61000 | 0 | 0 | 0 | 5000 | 0 | 45000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-88-L | RECONSTRUCTION OF FINAL TANKS AT OWLS HEAD WPCP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 6700 SHORE ROAD, FOOT OF 69TH STREET & NARROWS, BROOKLYN, N.Y. 11220 | RECONSTRUCTION OF FINAL TANKS AT THE OWLS HEAD WPCP | 2022 | 29521 | 0.3 | 0 | 0 | 0 | 0 | 0 | 34500 | 34500.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-91-L | RECONSTRUCTION OF SEA WALL AND DOCK @ OWLS HEAD WWTP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  | 6700 SHORE ROAD, FOOT OF 69TH STREET & NARROWS, BROOKLYN, N.Y. 11220 | RECONSTRUCTION OF SEA WALL AND DOCK @ OWLS HEAD WWTP | 2022 | 4250 | 56859.37 | 1986 | 0 | 0 | 0 | 0 | 0 | 58845.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-94-L | RECONSTRUCTION OF PRIMARY TANKS AT OWLS HEAD WPCP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  |  | RECONSTRUCTION OF PRIMARY TANKS AT OWLS HEAD WPCP | 2022 | 9550 | 6261.99 | 94 | 0 | 0 | 0 | 0 | 0 | 6355.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | OH-95-L | REPLACE #3 ENGINE GENERATOR/SUPPORT SYS. @ OWLS HEAD WPCP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  | 6700 SHORE ROAD, BROOKLYN, N.Y. 11220 | REPLACEMENT OF #3 ENGINE GENERATOR, SUPPORT SYSTEMS ASSOCIATED SWITCHGEAR AND HEAT RECOVERY UNIT AT OWLS HEAD WPCP. | 2022 | 20500 | 484.2 | 0 | 93000 | 0 | 0 | 0 | 0 | 93484.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-281 | PROSPECT EXPRESSWAY | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0269 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PROSPECT EXPRESSWAY | PROSPECT EXPRESSWAY | 2022 | 19670 | 13045.77 | 264 | 0 | 0 | 0 | 0 | 0 | 13309.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-315 | RECONSTRUCTION OF THE VAN BRUNT PUMPING STATION | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0269 |  | FOOT OF VAN BRUNT STREET NEAR READ STREET BROOKLYN, N.Y. | RECONSTRUCTION OF THE VAN BRUNT PUMPING STATION BROOKLY NEW YORK | 2022 | 5350 | 0 | 0 | 0 | 1000 | 0 | 10000 | 0 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-316 | RECONSTRUCTION OF AVENUE U PUMPING STATION BROOKLYN | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0269 |  | NORTHEAST CORNER OF AVENUE V AND OCEAN PARKWAY BROOKLYN, NEW YORK | RECONSTRUCTION OF AVENUE U PUMPING STATION BROOKLYN, NEW YORK | 2022 | 5300 | 0 | 0 | 0 | 0 | 0 | 17000 | 0 | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-318 | RECONSTRUCTION OF PAERDEGAT PUMPING STATION, BROOKLYN, N.Y. | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0269 |  | 6016 FLATLANDS AVENUE (CORNER OF RALPH AVENUE) BROOKLYN, NEW YORK | RECONSTRUCTION OF PAERDEGATE PUMPING STATION, BROOKLYN, N.Y. | 2022 | 6000 | 0 | 0 | 0 | 0 | 44000 | 0 | 0 | 44000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-80-L | TRC - DISINFECTION SYSTEM REHABILITATION AT RED HOOK WPCP | CONSENT DECREE UPGRADING AND CONSTRUCTION | 200 | WP-0282 |  | 63 FLUSHING AVENUE, BROOKLYN, NY, 11205-1069 | DISINFECTION SYSTEM REHABILITATION AT RED HOOK WPCP | 2022 | 1076 | 0 | 0 | 0 | 0 | 1076 | 0 | 0 | 1076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-83 | REPLACE MAIN SEWAGE PUMPS AT RED HOOK WPCP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACE MAIN SEWAGE PUMPS AT RED HOOK WPCP | 2022 | 25000 | 0 | 8400 | 0 | 0 | 0 | 97200 | 0 | 105600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | RH-93-L | RECONSTRUCTION OF TWO ABSORPTION CHILLERS @ RED HOOK WWTP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  | 63 FLUSHING AVENUE, BROOKLYN, N.Y. 11205 | PROVIDE ALL NECESSARY LABOR, MATERIALS, AND EQUIPMENT FOR DEMOLITION AND REPLACEMENT OF TWO EXISTINGS ABSORPTION CHILLERS, TWO CHILLED WATER PUMPS, TWO EFFLUENT PUMPS, AND ONE HOT WATER PUMP. DEMOLITION OF CORRESPONDING PIPING, PIPE SUPPORTS, VALVES, FITTINGS, ELECTRICAL FEEDERS, AND MONITORING AND CONTROL DEVICES ARE ALSO INCLUDED AT THE RED HOOKWASTEWATER TREATMENT PLANT, BROOKLYN N.Y. | 2022 | 1401 | 1984.5 | 67 | 0 | 0 | 0 | 0 | 0 | 2051.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SAND26W | STORM MITIGATION WORK ATTHE 26TH WARD WPCP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  |  | INSTALLATION OR CONSTRUCTION OF STORM MITIGATION WORK AT 26TH WARD WPCP | 2022 | 20181 | 0 | 0 | 280 | 350 | 0 | 350 | 738 | 1718 | 0 | 0 | 2520 | 3150 | 0 | 3150 | 6643 | 15463
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDCI | STORM MITIGATION WORK ATTHE CONEY ISLAND WPCP | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 |  |  | CONSTRUCTION OF STORM MITIGATION ATTHE CONEY ISLAND WATER POLLUTION CONTROL PLANT | 2022 | 38419 | 0 | 0 | 280 | 350 | 0 | 350 | 2772 | 3752 | 0 | 0 | 2520 | 3150 | 0 | 3150 | 24947 | 33767
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOH | STORM MITIGATION WORK AT THE OWLS HEAD WPCP (HMP) | PLANT UPGRADING AND RECONSTRUCTION | 200 | WP-0112 | PROJECT DELAYED PENDING NON-CITY GRANT APPROVAL |  | CONSTRUCTION OF STORM MITIGATION ATTHE OWLS HEAD WATER POLLUTION CONTROL PLANT | 2022 | 71645 | 0 | 0 | 280 | 700 | 0 | 700 | 5485 | 7165 | 0 | 0 | 2520 | 6300 | 0 | 6300 | 49360 | 64480
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002385 | Rehab of Combined brick sewer via guniting 92st & 4 Ave, BK | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 210 | SE-0002K |  |  | REHABILITATION OF 132" COMBINED BRICK SEWER BY GUNITING ALONG 92 ST. B/T RIDGE BLVD. & 4 AVE, BROOKLYN | 2022 | 5645 | 0 | 0 | 5645 | 0 | 0 | 0 | 0 | 5645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002387 | Repair of CSO Outfall on Williams Avenue, BKLYN | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 218 | SE-0002K SE-0200K |  |  | REPAIR OF CSO OUTFALL ON WILLIAMS AVENUE, BKLYN. | 2022 | 8010 | 0 | 0 | 0 | 0 | 8010 | 0 | 0 | 8010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002388 | Upgrade sewers on Ave L between Ocean & Bedford avenue BKLYN | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 214 218 | SE-0200K SE-0002K WM-0001 |  |  | UPGRADING OF COMBINED SEWERS AND STORM SEWERS AND DISTRIBUTION WATER MAIN REPLACEMENT WORK ON AVE L BETWEEN OCEAN AVE AND BEDFORD AVE IN BROOKLYN | 2022 | 30491 | 0 | 0 | 0 | 0 | 33456 | 0 | 0 | 33456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002390 | Guniting of Outfall Sewers on Wolcott St BKLYN | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 206 | SE-0002K |  |  | REHABILITATION OF 72" CIRCULAR BRICK OUTFALL SEWER BY GUNITING ALONG WOLCOTT STREET ASSOCIATED WITH DOT SANDRDHK PROJECT IN BOROUGH OF BROOKLYN | 2022 | 1469 | 0 | 0 | 1304 | 0 | 0 | 0 | 0 | 1304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK002392 | Install of combined sewers & dist WM work along 3rd Ave MH | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 206 | SE-0002K WM-0001 WM-0006 EP-0007 |  |  | INSTALLATION OF COMBINED BOX SEWERS AND DISTRIBUTION WATER MAIN WORK ALONG 3RD AVE BETWEEN 19TH STREET AND 7TH STREET, MANHATTAN. | 2022 | 110278 | 0 | 0 | 0 | 0 | 0 | 110278 | 0 | 110278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEK20072 | Rplcmnt of Sanitary & Storm Sewers & WM on Homecrest Ave BK | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 215 | SE-0200K SE-0002K WM-0001 |  |  | REPLACEMENT OF SANITARY & STORM SEWERS AND WATER MAINS ON HOMECREST AVENUE BETWEEN AVENUE V AND GRAVESEND NECK ROAD, AND OTHER LOCATIONS INBROOKLYN | 2022 | 4717 | 0 | 0 | 0 | 0 | 4800 | 0 | 0 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEKDSMH23 | Reconstruction and repair of deep sewer manholes, Bklyn | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 200 | SE-0002K |  |  | RECONSTRUCTION AND REPAIR OF DEEP SEWER MANHOLES, BROOKLYN | 2022 | 30759 | 0 | 0 | 0 | 26747 | 0 | 0 | 0 | 26747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-CI | STEP FEED BNR AT CONEY ISLAND & ROCKAWAY WPCPs | BIOLOGICAL NUTRIENT REMOVAL | 200 | WP-0285 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | THIS PROJECT IS TO RETROFIT THE EXISTING CI AND ROCK WWTPS FOR THE STEP FEED BNR PROCESS. THIS WORK IS A REQUIREMENT OF THE JAMAICA BAY NEGOTIATIONS WITHT THE DEC AND WILL BE ENFORCEABLE UNDER THE NEW NITROGENCONSENT JUDGMENT. THE WORK WILL INVOLVE INSTALLING NEW DIFFUSERS, SUBMERSIBLE MIXERS, BAFFLES, FROTH CONTROL AND INSTRUMENTAION IN ALL FOURAERATION TANKS. | 2022 | 27250 | 65532.58 | 131 | 0 | 0 | 0 | 0 | 0 | 65663.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | ACEDOS211 | Brooklyn 1/4 HVAC Chillers | GARAGES AND FACILITIES |  | S-0136 |  | BROOKLYN 1/4 HVAC CHILLERS | BROOKLYN 1/4 HVAC CHILLERS | 2022 | 0 | 0 | 477 | 0 | 0 | 0 | 0 | 0 | 477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-264Y | Brooklyn Cioffe Borough Shop Roof Replacement | GARAGES AND FACILITIES | 200 | S-0136 |  |  | ROOF REPLACEMENT | 2022 | 2300 | 762.9 | 0 | 7833 | 0 | 0 | 0 | 0 | 8595.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-374W | Brooklyn 11 Boiler Replacement | GARAGES AND FACILITIES | 211 | S-0136 |  |  | BROOKLYN 11 BOILER REPLACEMENT | 2022 | 0 | 0 | 423 | 778 | 5184 | 0 | 0 | 0 | 6385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-380D | Brooklyn 14 Garage HVAC System Rehabilitation | GARAGES AND FACILITIES | 214 218 | S-0136 |  |  | HVAC REHAB | 2022 | 890 | 846.03 | 103 | 0 | 0 | 0 | 0 | 0 | 949.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-380H | Brooklyn 6 Garage Boiler System Rehabilitation | GARAGES AND FACILITIES | 206 | S-0136 |  |  | REPLACE BOILER AND ASSOCIATED CONTROLS AND EQP | 2022 | 976 | 0 | 2529 | 0 | 0 | 0 | 0 | 0 | 2529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-383G | BROOKLYN CIOFFE SHOP HVAC REPLACEMENT | GARAGES AND FACILITIES | 200 | S-0136 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HVAC REPLACEMENT | 2022 | 4250 | 5731.51 | 1021 | 0 | 0 | 0 | 0 | 0 | 6752.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-427 | Brooklyn 16 922 Georgia Ave Garage Rehabilitation | GARAGES AND FACILITIES | 205 216 | S-0136 |  |  | REHAB | 2022 | 19316 | 0 | 0 | 1174 | 1665 | 16652 | 0 | 0 | 19491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-433 | Brooklyn 10 Pier /53rd St Rehab | GARAGES AND FACILITIES | 200 | PU-0200 |  |  | REHAB OF PIER NEEDED FOR SALT STORAGE AND VEHICLE PARKING | 2022 | 3450 | 0 | 0 | 529 | 20113 | 0 | 0 | 0 | 20642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-449D | Brooklyn 15 Oil Water Separator | GARAGES AND FACILITIES | 215 | S-0136 |  |  | OIL WATER SEPARATOR | 2022 | 538 | 0 | 0 | 388 | 0 | 0 | 0 | 0 | 388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-451 | Brooklyn Greenpoint Warehouse Pump Replacement | GARAGES AND FACILITIES | 201 | S-0136 |  |  | PUMP REPLACEMENT | 2022 | 50 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464B | Brooklyn 8 Garage Roof and HVAC Replacement | GARAGES AND FACILITIES | 208 | S-0136 |  |  | ROOF REPLACEMENT | 2022 | 2400 | 637 | 0 | 6463 | 0 | 0 | 0 | 0 | 7100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S136-464F | Brooklyn 16 923 Georgia Ave Roof Replacement | GARAGES AND FACILITIES | 205 216 | S-0136 |  |  | ROOF REPLACEMENT | 2022 | 4255 | 4602.95 | 144 | 0 | 0 | 0 | 0 | 0 | 4746.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S186-224 | Brooklyn 3 Garage New Construction | GARAGES AND FACILITIES | 203 | S-0186 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BEGINNING AT THE INTERSECTION OF NOSTRAND AVE AND MYRTLE AVE, MOVING SOUTH 200' THEN WEST 458' THEN NORTH 200' THEN WEST 508' TO BEGINNING. | NEW DOS GARAGE TO SERVE THE BROOKLYN DISTRICT 3 . | 2022 | 93710 | 188430.93 | 4412 | 3459 | 0 | 0 | 0 | 0 | 196301.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-227K | BROOKLYN 7/10 SALT SHED REPLACEMENT | GARAGES AND FACILITIES | 207 210 | S-0195 |  |  | SALT SHED ROOF REPLACEMENT | 2022 | 3226 | 228.23 | 0 | 129 | 2281 | 0 | 0 | 0 | 2638.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-227R | BROOKLYN 7 /10 SALT SHED ROOF DEMOLITiON | GARAGES AND FACILITIES | 207 210 | S-0195 |  |  | ELIMINATE DANGER BY REMOVING COLLAPSING ROOF | 2022 | 783 | 0 | 897 | 0 | 0 | 0 | 0 | 0 | 897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S195-228N | Brooklyn 11 Salt Shed Demolition | GARAGES AND FACILITIES | 211 | S-0195 |  |  | DEMOLISH UNSAFE STRUCTURE | 2022 | 514 | 0 | 70 | 444 | 0 | 0 | 0 | 0 | 514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403A | Hamilton Avenue MTS Bulkhead | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 200 | PU-0200 |  |  | REPLACEMENT OF BULKHEAD WALL BY HAMILTON AVE MTS | 2022 | 6159 | 1485.35 | 0 | 4674 | 0 | 0 | 0 | 0 | 6159.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | S216-403C | Hamilton Avenue MTS Rehab | SOLID WASTE MANAGEMENT | 200 | S-0216 |  |  | MTS SLAB REHAB | 2022 | 5312 | 0 | 1580 | 8172 | 0 | 0 | 0 | 0 | 9752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK11C | Hurricane Sandy Brooklyn 11 Conduit Replacement | GARAGES AND FACILITIES | 200 | S-0136 |  |  | CONDUIT | 2022 | 96 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 28
20220309 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDBK4FA | Hurricane Sandy Brooklyn 1/4 Fire Alarm Replacement | GARAGES AND FACILITIES | 201 | S-0136 |  |  | REPLACEMENT OF FIRE ALARM DUE TO HURRICANE SANDY | 2022 | 200 | 121.18 | 299 | 0 | 0 | 0 | 0 | 0 | 420.18 | 73.08 | 615 | 0 | 0 | 0 | 0 | 0 | 688.08
20220309 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPTWH | Hurricane Sandy GRNPT Warehouse R/R & Haz Mitigation | GARAGES AND FACILITIES | 200 | S-0136 |  |  | REPLACE HOT WATER HEATERS, TRANSFORMER BOILER AND OTHER EQUIPMENT ANDRAISE CRITICAL EQUIPMENT TO MITIGATE FLOOD HAZARD | 2022 | 943 | 117.02 | 7 | 52 | 0 | 0 | 0 | 0 | 176.02 | 4.37 | 30 | 281 | 0 | 0 | 0 | 0 | 315.37
20220309 | BROOKLYN | 827 | DEPARTMENT OF SANITATION | SANDGPWHC | Hurricane Sandy GRNPT Warehouse Conduit Replacement | GARAGES AND FACILITIES | 200 | S-0136 |  |  | REPLACE CONDUIT | 2022 | 295 | 2.01 | 1 | 74 | 0 | 0 | 0 | 0 | 77.01 | 18.16 | 1 | 399 | 0 | 0 | 0 | 0 | 418.16
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT601 | DOT - Hamilton Administrative Building | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DOT - HAMILTON ADMINISTRATIVE BUILDING ENERGY EFFICIENT UPGRADES | 2022 | 226 | 17 | 0 | 84 | 0 | 0 | 0 | 0 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT802 | DOT - Parking Garage LED Lighting Upgrade | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PARKING GARAGE LED LIGHTING UPGRADE | 2022 | 685 | 637.46 | 0 | 0 | 0 | 53 | 0 | 0 | 690.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | BEDSTLIG | DOT BEDFORD HISTORIC LIGHT RESTORATION | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 200 | TF-K503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DOT BEDFORD HISTORIC DISTRICT LIGHTING RESTORATION: DECORATIVE LIGHTING IN THE BEDFORD DISTRICT | 2022 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | BKBRDGCAM | Brooklyn Bridge Surveillance Cameras | SIGNAL INSTALLATION AND COMPUTERIZATION | 200 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CAMERAS INSTALLATION FOR BROOKLYN BRIDGE | 2022 | 13447 | 8843.92 | 0 | 0 | 0 | 500 | 555 | 500 | 10398.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | BKBRDGITS | Brooklyn Bridge Approaches-DOT ITS | SIGNAL INSTALLATION AND COMPUTERIZATION | 200 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ITS FOR BROOKLYN BRIDGE APPROACHES | 2022 | 2276 | 802.21 | 0 | 0 | 350 | 0 | 0 | 1124 | 2276.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | BRK24027 | UNION STREET over GOWANUS CANAL BIN 2240270 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 200 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | UNION STREET OVER GOWANUS CANAL BIN 2240270 - NEW | UNION STREET OVER GOWANUS CANAL BIN 2240270 - NEW | 2022 | 47871 | 0 | 0 | 0 | 0 | 4000 | 0 | 43871 | 47871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBC2030 | BRIDGES 2030 | FAIR BRIDGES | 200 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BRIDGES 2030 | BRIDGES 2030 | 2022 | 249000 | 0 | 133433 | 0 | 125727 | 907184 | 0 | 0 | 1166344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK1023 | MILL BASIN BR / BELT PARKWAY #2-23147-9/TN | FAIR BRIDGES | 218 | HB-1023 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MILL BASIN BR/BELT PARKWAY, BROOKLYN | RECONSTRUCTION AND REHABILITATION OF THE MILL BASIN BR/ BELT PARKWAY BREPLACEMENT OF DECK INCLUSIVE OF ANY INCIDENTAL STEEL WORK, CURBS ANDSIDEWALKS THE FUNDING FOR THIS PROJECT IS ALL CITY | 2022 | 228336 | 140539.91 | 0 | 0 | 0 | 0 | 0 | 0 | 140539.91 | 183914.13 | 0 | 1306 | 0 | 0 | 0 | 0 | 185220.13
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK1205 | RECON OF 5TH AVE BRIDGE OVER LIRR AND SEA BEACH, BR 2-243580 | FAIR BRIDGES | 207 210 | HB-1205 HB-1012 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RECONS OF 5TH AVE BR OVER LIRR/SEA BEACH, BROOKLYN | RECONS OF 5TH AVE BR OVER LIRR/SEA BEACH, BROOKLYN | 2022 | 12977 | 6968.94 | 47125 | 41 | 0 | 0 | 0 | 0 | 54134.94 | 0 | 55017 | 0 | 0 | 0 | 0 | 0 | 55017
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK224404 | EAST DRIVE (E WOOD ARCH) PED PATH NEAR CENTER DRIV # 2244040 | FAIR BRIDGES | 200 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | EAST DRIVE (EAST WOOD ARCH) PEDESTRIAN PATH NEAR CENTER DRIVE | EAST DRIVE (EAST WOOD ARCH) PEDESTRIAN PATH NEAR CENTER DRIVE | 2022 | 4823 | 0 | 0 | 0 | 0 | 750 | 0 | 4073 | 4823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK244120 | HILL DR (TERRACE BR) OVER PROSPECT PARK LAKE BIN:2244120 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 200 | P-0508 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HILL DR (TERRACE BR) OVER PROSPECT PARK LAKE BIN 2244120 | 2022 | 27776 | 1260.24 | 1253 | 0 | 0 | 25640 | 0 | 0 | 28153.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK4470 | SEELY STREET OVER PROSPECT AVENUE BIN: 2244470 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 200 | HB-1070 HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SEELY STREET OVER PROSPECT AVENUE BIN: 2244470 | 2022 | 15815 | 2158.26 | 0 | 1551 | 27512 | 0 | 0 | 0 | 31221.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBK530 | PARKSIDE AVE AND OCEAN AVE RR BR #2-24302-0 | FAIR BRIDGES | 209 214 | HB-0530 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REHABILITATION OF THE PARKSIDE AVE AND OCEAN AVE RR BR REPLACEMENT OF, INCLUSIVE OF ANY INCIDENTAL STEEL WORK, RAILING AND SAFETY FENCE THEFOR THIS PROJECT IS 100% CITY | 2022 | 18056 | 8771.48 | 0 | 0 | 50640 | 0 | 0 | 0 | 59411.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23036 | UNION ST OVER 278I BQE BIN 2230360 | FAIR BRIDGES | 200 | HB-1012 HB-0215 |  | UNION ST OVER 278I BQE BIN 2230360 | UNION ST OVER 278I BQE BIN 2230360 | 2022 | 17111 | 0 | 0 | 0 | 1316 | 0 | 1974 | 13821 | 17111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23038 | KANE ST/ 278I (BQE) BIN# 2230380 | FAIR BRIDGES | 200 | HB-3038 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | KANE ST/ 278I (BQE) BIN# 2230380 | KANE ST/ 278I (BQE) BIN# 2230380 | 2022 | 17456 | 1029.35 | 0 | 0 | 806 | 0 | 0 | 16113 | 17948.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23140 | BSHP over Sheepshead Bay Road BIN 2231409 | FAIR BRIDGES | 200 | HB-1012 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BSHP OVER SHEEPSHEAD BAY ROAD BIN 22331409 | 2022 | 21822 | 767.46 | 520 | 20604 | 0 | 0 | 0 | 0 | 21891.46 | 0 | 0 | 9309 | 0 | 0 | 0 | 0 | 9309
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23141 | BSHP over Ocean Ave BIN 2231419 | FAIR BRIDGES | 200 | HB-1012 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BSHP OVER OCEAN AVE BIN 2231419 | 2022 | 43739 | 1460.57 | 1375 | 44694 | 0 | 0 | 0 | 0 | 47529.57 | 0 | 0 | 9309 | 0 | 0 | 0 | 0 | 9309
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23142 | BSHP OVER BEDFORD AVE BIN 2231429 | FAIR BRIDGES | 200 | HB-1012 HB-0215 |  | BSHP OVER BEDFORD AVE BIN 2231429 | BSHP OVER BEDFORD AVE BIN 2231429 | 2022 | 41069 | 1124.46 | 1195 | 37670 | 0 | 0 | 0 | 0 | 39989.46 | 0 | 0 | 9309 | 0 | 0 | 0 | 0 | 9309
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23143 | Belt Shore Pkwy over Nostrand Ave 2231439 | FAIR BRIDGES | 200 | HB-1090 |  | BELT SHORE PKWY OVER NOSTRAND AVE 2231439 | BELT SHORE PKWAY OVER NOSTRAND AVE 2231439 | 2022 | 48468 | 1162.7 | 1357 | 44103 | 0 | 0 | 0 | 0 | 46622.7 | 0 | 0 | 9310 | 0 | 0 | 0 | 0 | 9310
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA23308 | E 14TH ST PED BRIDGE BIN:2233080 | FAIR BRIDGES | 200 | HB-1012 HB-1028 |  | E 14TH ST PED BRIDGE BIN:2233080 | E 14TH ST PED BRIDGE BIN:2233080 | 2022 | 22037 | 1855.43 | 1462 | 2543 | 17951 | 0 | 0 | 0 | 23811.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24310 | Beverly Road over BMT Subway, Brighton BIN 2243100 | FAIR BRIDGES | 200 | HB-4310 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BEVERLY ROAD OVER BMT SUBWAY, BRIGHTON BIN 2243100 | BEVERLY ROAD OVER BMT SUBWAY, BRIGHTON BIN 2243100 | 2022 | 47202 | 1714.23 | 302 | 2763 | 1750 | 41952 | 0 | 0 | 48481.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24315 | Foster Ave over BMT Subway BIN 2243150 | FAIR BRIDGES | 200 | HB-1208 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FOSTER AVE OVER BMT SUBWAY BIN 2243150 | 2022 | 0 | 0 | 0 | 3061 | 0 | 3000 | 23168 | 0 | 29229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24371 | 19TH AVENUE over BMT SEA BEACH BIN 2243710 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 200 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 19TH AVENUE OVER BMT SEA BEACH | 19TH AVENUE OVER BMT SEA BEACH | 2022 | 24107 | 0 | 0 | 0 | 3596 | 0 | 2338 | 18173 | 24107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBKA24382 | 21st Ave RR BR & 64th St #2-24382-1/TN35190 | FAIR BRIDGES | 200 | HB-0548 HB-0061 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 21ST AVE RR BR & 64TH ST #2-24382-1/TN35190 | 21ST AVE RR BR & 64TH ST #2-24382-1/TN35190 | 2022 | 110900 | 0 | 0 | 0 | 7101 | 0 | 9237 | 95062 | 111400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBPK17K | 17TH AVENUE PEDESTRIAN BRIDGE OVER BELT PARKWAY 2231300 | FAIR BRIDGES | 210 | P-0956 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 17TH STREET PEDESTRIAN BRIDGE | 17TH STREET PEDESTRIAN BRIDGE | 2022 | 8006 | 22709.36 | 2130 | 3125 | 0 | 0 | 0 | 0 | 27964.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HBPK27K | 27TH AVENUE PEDESTRIAN BRIDGE OVER BELT PARKWAY | FAIR BRIDGES | 213 | P-0507 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 27TH AVENUE PEDESTRIAN BRIDGE | 27TH AVENUE PEDESTRIAN BRIDGE | 2022 | 7473 | 22670.87 | 1209 | 3472 | 0 | 0 | 0 | 0 | 27351.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR19C | Citywide Milling - Brooklyn | PRIMARY STREET RESURFACING | 200 | HW-0002K | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITYWIDE MILLING- BROOKLYN | 2022 | 7478 | 9359.51 | 1575 | 0 | 0 | 0 | 0 | 0 | 10934.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HW349LUM | IN-HOUSE RESURFACING LUMP SUM - ASPHALT | PRIMARY STREET RESURFACING | 299 | HW-D101 HW-D103 HW-D105 HW-0349 HW-D102 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RESURFACING ROADWAYS | 2022 | 251043 | 757251.48 | 46238 | 56303 | 59475 | 61296 | 63143 | 347741 | 1391447.48 | 76112.38 | 15700 | 0 | 0 | 0 | 0 | 0 | 91812.38
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWCSCH98 | East 98th Street School Safety Improvements | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | EAST 98TH STREET SCHOOL SAFETY IMPROVEMENTS | EAST 98TH STREET SCHOOL SAFETY IMPROVEMENTS | 2022 | 6053 | 0 | 0 | 0 | 0 | 0 | 6053 | 0 | 6053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10109 | JORALEMON STREET IMPROVEMENTS | PRIMARY STREET RECONSTRUCTION | 200 | HW-D101 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | JORALEMON STREET | JORALEMON STREET IMPROVEMENTS | 2022 | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10110 | Strickland Avenue - Reconstruction | PRIMARY STREET RECONSTRUCTION | 200 | HW-D101 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | STRICKLAND AVENUE - RECONSTRUCTION | STRICKLAND AVENUE - RECONSTRUCTION | 2022 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10111 | Intersection Safety Improvements Ocean Parkway & Ave Z | PRIMARY STREET RECONSTRUCTION | 200 | HW-D101 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | INTERSECTION SAFETY IMPROVEMENTS OCEAN PARKWAY & AVE Z | INTERSECTION SAFETY IMPROVEMENTS OCEAN PARKWAY & AVE Z | 2022 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10113 | Street Reconstruction in Community Board 14 | PRIMARY STREET RECONSTRUCTION | 200 | HW-D101 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | STREET RECONSTRUCTION IN COMMUNITY BOARD 14 | STREET RECONSTRUCTION IN COMMUNITY BOARD 14 | 2022 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10115 | Safety Improvements Broadway Corridor | PRIMARY STREET RECONSTRUCTION | 200 | HW-D101 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SAFETY IMPROVEMENTS BROADWAY CORRIDOR | SAFETY IMPROVEMENTS BROADWAY CORRIDOR | 2022 | 235 | 0 | 0 | 0 | 0 | 235 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10119 | PS 92 SIDE WALK EXTENSION | SIDEWALK RECONSTRUCTION | 200 | HW-D101 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PS 92 SIDE WALK EXTENSION | 2022 | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWFKGPYRD | Build-Out Cost for Greenpoint Yard New Trailers | FACILITY RECONSTRUCTION | 200 | HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BUILD-OUT COST FOR GREENPOINT YARD NEW TRAILERS | BUILD-OUT COST FOR GREENPOINT YARD NEW TRAILERS | 2022 | 757 | 0 | 757 | 0 | 0 | 0 | 0 | 0 | 757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00502 | 8th Avenue Sunset Park Chinatown Archway | PRIMARY STREET RECONSTRUCTION | 200 | TF-K005 HW-0001M | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 8TH AVENUE SUNSET PARK CHINATOWN ARCHWAY | 8TH AVENUE SUNSET PARK CHINATOWN ARCHWAY | 2022 | 1000 | 129.42 | 1200 | 0 | 900 | 3741 | 0 | 0 | 5970.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00503 | BQ Green | PRIMARY STREET RECONSTRUCTION | 200 | HW-K005 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BQ GREEN | BQ GREEN | 2022 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00504 | Atlantic Avenue - Purchase of WalkNYC Signs | PRIMARY STREET RECONSTRUCTION | 200 202 | HW-K005 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ATLANTIC AVENUE DISTRICT MANAGEMENT ASSOCIATION, INC.: PURCHASE OF WALKNYC SIGNS | 2022 | 35 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK00514 | Brooklyn Greenway:Atlantic Avenue Connector | PRIMARY STREET RECONSTRUCTION |  | HW-K005 HW-0001K HW-D101 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BIKE LANE CONSTRUCTION | 2022 | 2300 | 0 | 0 | 0 | 0 | 0 | 2300 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1673 | South Brooklyn Pedestrian and Bicycle Safety Improvements | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K HW-K005 HW-D101 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SOUTH BROOKLYN PEDESTRIAN AND BICYCLE SAFETY IMPROVEMENTS | SOUTH BROOKLYN PEDESTRIAN AND BICYCLE SAFETY IMPROVEMENTS | 2022 | 15938 | 0 | 0 | 0 | 0 | 0 | 31161 | 0 | 31161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK1674 | Flatbush Avenue Downtown Brooklyn Safety Improvements | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K HW-D101 HW-K005 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | FLATBUSH AVENUE DOWNTOWN BROOKLYN SAFETY IMPROVEMENTS | FLATBUSH AVENUE DOWNTOWN BROOKLYN SAFETY IMPROVEMENTS | 2022 | 22563 | 0 | 0 | 0 | 0 | 23863 | 0 | 0 | 23863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK2048A | Jamaica Bay Greenway - Marine Park Connector & Flatbush Ave | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | JAMAICA BAY GREENWAY - MARINE PARK CONNECTOR & FLATBUSH AVE | 2022 | 19278 | 0 | 0 | 2754 | 0 | 0 | 16524 | 0 | 19278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWK639WB | Adams Street Pedestrian Safety and Security | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | ADAMS STREET PEDESTRIAN SAFETY AND SECURITY | ADAMS STREET PEDESTRIAN SAFETY AND SECURITY | 2022 | 11269 | 0 | 0 | 1197 | 13188 | 0 | 0 | 0 | 14385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKDAREWF | Plumb Beach Channel Waterfront - Dare Court Street End | PRIMARY STREET RECONSTRUCTION | 200 | PU-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PLUMB BEACH CHANNEL WATERFRONT - DARE COURT STREET END | PLUMB BEACH CHANNEL WATERFRONT - DARE COURT STREET END | 2022 | 1527 | 0 | 0 | 229 | 0 | 1298 | 0 | 0 | 1527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKF029Z | FLATLANDS YARD AND STRUCTURES REHABILITATION | FACILITY RECONSTRUCTION | 218 | HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | FLATLANDS YARD AND STRUCTURES REHABILITATION | REBUILD EXISTING 23000 SQ OF GARAGE AND AUTO REPAIR SHOP SPACE | 2022 | 11545 | 0 | 0 | 0 | 0 | 0 | 1050 | 10495 | 11545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFANEWF | Shell Bank Creek - Fane Court Street End | PRIMARY STREET RECONSTRUCTION | 200 | PU-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SHELL BANK CREEK - FANE COURT STREET END | SHELL BANK CREEK - FANE COURT STREET END | 2022 | 1257 | 0 | 0 | 189 | 0 | 1068 | 0 | 0 | 1257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFBERRY | Berry Street | FACILITY RECONSTRUCTION | 200 | HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BERRY STREET | BERRY STREET | 2022 | 2300 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFLATAV | 6080 Flatlands Ave | FACILITY RECONSTRUCTION | 200 | HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 6080 FLATLANDS AVENUE. | 6080 FLATLANDS AVENUE. | 2022 | 279 | 0 | 279 | 0 | 0 | 0 | 0 | 0 | 279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFRH | Red Hook Build-out | FACILITY RECONSTRUCTION | 200 | HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RED HOOK BUILD-OUT | RED HOOK BUILD-OUT | 2022 | 3901 | 0 | 0 | 0 | 3901 | 0 | 0 | 0 | 3901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKFVAR | Varick Build-out | FACILITY RECONSTRUCTION | 200 | HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | VARICK BUILD-OUT | VARICK BUILD-OUT | 2022 | 31462 | 0 | 0 | 7462 | 0 | 0 | 24000 | 0 | 31462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMETWF | Newtown Creek Waterfront - Metropolitan Ave Street End | PRIMARY STREET RECONSTRUCTION | 200 | PU-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NEWTOWN CREEK WATERFRONT - METROPOLITAN AVE STREET END | NEWTOWN CREEK WATERFRONT - METROPOLITAN AVE STREET END | 2022 | 1575 | 0 | 0 | 236 | 0 | 1339 | 0 | 0 | 1575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMGB | McGuinness Blvd Safety Improvements | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K SE-0200K WM-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MCGUINNESS BLVD SAFETY IMPROVEMENTS | MCGUINNESS BLVD SAFETY IMPROVEMENTS | 2022 | 39300 | 0 | 0 | 0 | 0 | 0 | 39300 | 0 | 39300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKMSPTWF | Newton Creek Waterfront - Maspeth Ave Street End | PRIMARY STREET RECONSTRUCTION | 200 | PU-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NEWTON CREEK WATERFRONT - MASPETH AVE STREET END | NEWTON CREEK WATERFRONT - MASPETH AVE STREET END | 2022 | 3244 | 0 | 0 | 487 | 0 | 2757 | 0 | 0 | 3244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKNBP | North Brooklyn Pedestrian Safety | PRIMARY STREET RECONSTRUCTION | 200 | HW-D102 HW-1684 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NORTH BROOKLYN MULTISITE PEDESTRIAN SAFETY | NORTH BROOKLYN MULTISITE PEDESTRIAN SAFETY | 2022 | 13500 | 0 | 300 | 0 | 0 | 0 | 13500 | 0 | 13800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWKNUAV | New Utrecht Ave Micro-Milling and Reconstruction | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NEW UTRECHT AVE MICRO-MILLING AND RECONSTRUCTION | NEW UTRECHT AVE MICRO-MILLING AND RECONSTRUCTION | 2022 | 18077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18077 | 0 | 0 | 18077
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | HWP19KTA | Complex Pedestrian Ramps - Landmark Installation | PEDESTRIAN RAMP CONSTRUCTION | 200 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX PEDESTRIAN RAMPS - LANDMARK INSTALLATION | COMPLEX PEDESTRIAN RAMPS - LANDMARK INSTALLATION | 2022 | 2734 | 0 | 0 | 0 | 2734 | 0 | 0 | 0 | 2734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | NDF-CCIMP | NDF - Commercial Corridor Improvements | NEIGHBORHOOD REVITALIZATION | 200 | ED-0384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NDF - COMMERCIAL CORRIDOR IMPROVEMENTS | 2022 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF18-2017 | AVENUE M MUNICIPAL PARKING FIELD | Parking Meters, Lots, and Garages | 200 214 | TF-0018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECON OF PARKING FIELD | 2022 | 570 | 0 | 0 | 0 | 0 | 0 | 0 | 218 | 218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50311 | Rpl St lg pl Bedford Ave fm Campus Rd to Foster Ave-XMA165.3 | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 200 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACEMENT OF STANDARD STREET LIGHTING WITH BC TYPE LAMP POSTS ON BEDFORD AVENUE FROM CAMPUS ROAD TO FOSTER AVENUE | 2022 | 254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117.78 | 0 | 0 | 0 | 0 | 0 | 136 | 253.78
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50313 | Instl lg on Cortelyou Rd&Newkirk XMA193.30 & A835 | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 200 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FURNISH AND INSTALL LIGHT ON CORTELYOU RD & NEWKIRK AVENUE BETWEEN CONEY ISLAND AVE AND OCEAN AVENUE IN BROOKLYN | 2022 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 243.5 | 0 | 0 | 0 | 0 | 0 | 156 | 399.5
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50315 | Historic St lg poles on Mermaid Avenue bet W21St &W29th St, | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 200 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HISTORIC STREET LIGHT POLES, BENCHES, AND TREE GUARDS ALONG MERMAID AVENUE BETWEEN WEST 21ST STREET AND WEST 29TH STREET. | 2022 | 400 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 471 | 0 | 0 | 0 | 0 | 471
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TF50317 | Upgrade of poles& lg on McDonald Ave, fr BPWY&Kingshwy Ave R | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 200 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | UPGRADE ST LG POLES | 2022 | 888 | 0 | 0 | 1090 | 0 | 0 | 0 | 0 | 1090 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503K23 | BROOKLYN HEIGHTS HISTORIC LIGHTING | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 200 202 | TF-D503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BROOKLYN HEIGHT HISTORIC LIGHTING | BROOKLYN HEIGHT HISTORIC LIGHTING | 2022 | 250 | 443.95 | 0 | 600 | 600 | 414 | 0 | 0 | 2057.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503K26 | FLATBUSH AVE. ST. PURCHASE AND INSTALLATION OF LAMP POST | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 200 | TF-D503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | FLATBUSH AVE. ST. PURCHASE AND INSTALLATION OF LAMP POST | FLATBUSH AVE. ST. PURCHASE AND INSTALLATION OF LAMP POST | 2022 | 450 | 336.73 | 0 | 0 | 0 | 125 | 0 | 0 | 461.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFK50313 | Historic Lighting on Broadway btw Roebling and Bedford | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 200 201 | TF-K503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HISTORIC LIGHTING ON BROADWAY BTW ROEBLING AND BEDFORD | THE WILLIAMSBURG SAVINGS BANK - 175 BROADWAY HOSPITALITY LLC HAS AGREED TO A MAINTENANCE CONTRACT WITH DOT TO PAY EXTRA WATTAGE - REPLACEMENT OF 18 LAMP POSTS WITH HISTORIC LIGHTING FIXTURES ALONG BROADWAY BETWEEN ROEBLING AND BEDFORD STREETS IN WILLIAMSBURG. | 2022 | 290 | 0 | 0 | 0 | 0 | 290 | 0 | 0 | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFKVANDMD | VANDERBILT AVE MERCHANTS DISTRICT/PHNDC: ELEGANT STREET LIG | INSTALLATION OF LAMPPOSTS AND LUMINAIRES |  | TF-K503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ELEGANT STREET LIGHTING FOR VANDERBILT AVE MERCHANTS DISTRICT | 2022 | 615 | 552.33 | 0 | 0 | 0 | 70 | 0 | 0 | 622.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 841 | DEPARTMENT OF TRANSPORTATION | TFLGAVEU | St Lg on Ave U from Ocean Pkwy to McDonald Ave XMA206.30A | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 200 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FURNISH AND INSTALL ST LIGHT ON AVENUE U | 2022 | 508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 508 | 0 | 0 | 0 | 508
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | GKBKGI-01 | GI - DSGN & CONS OF PARKLAND RETROFITS IN BROOKLYN | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 P-1018 |  |  | GI - DSGN & CONS OF PARKLAND RETROFITS IN BROOKLYN | 2022 | 3155 | 593.33 | 0 | 2391 | 546 | 0 | 0 | 0 | 3530.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-BNDST | NDF- Bond Street End | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | ED-0384 |  | NDF- BOND STREET END, BOROUGH OF BROOKLYN | NDF- BOND STREET END | 2022 | 4160 | 0 | 0 | 320 | 0 | 1280 | 0 | 1600 | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-BRMPK | NDF- Boerum Park | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | ED-0384 |  | NDF- BOERUM PARK, BOROUGH OF BROOKLYN | NDF- BOERUM PARK | 2022 | 5474 | 0 | 0 | 421 | 0 | 1684 | 0 | 2105 | 4210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-CLNKY | NDF - Callahan-Kelly Park (B219-117M) | NEIGHBORHOOD REVITALIZATION | 200 | P-0245K ED-0384 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CALAHAN KELLY PARK | 2022 | 18893 | 21397.8 | 903 | 2 | 0 | 1504 | 0 | 0 | 23806.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-GESPL | NDF - Gowanus Esplanade to 9th Street | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | ED-0384 |  | NDF- GOWANUS ESPLANADE TO 9TH STREET, BROOKLYN | NDF- GOWANUS ESPLANADE TO 9TH STREET | 2022 | 5970 | 0 | 0 | 597 | 0 | 2388 | 0 | 2985 | 5970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-GGPRK | NDF- Gowanus Green Park | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | ED-0384 |  | NDF- GOWANUS GREEN PARK | NDF- GOWANUS GREEN PARK | 2022 | 14400 | 0 | 0 | 0 | 0 | 1440 | 0 | 12960 | 14400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN3 | NDF - Highland Park Eastern Playground R/C Q020-119M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | ED-0384 |  |  | RECONSTRUCTION OF THE EASTERN PLAYGROUND AT HIGHLAND PARK, BOROUGH OFKINGS | 2022 | 8707 | 4085.2 | 0 | 394 | 0 | 394 | 514 | 2570 | 7957.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN4 | NDF - Highland Park Comfort Station R/C Q020-219M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | ED-0384 |  |  | RECONSTRUCTION OF THE COMFORT STATION AT HIGHLAND PARK, BOROUGH OF KINGS | 2022 | 2600 | 1369.85 | 0 | 200 | 0 | 480 | 0 | 0 | 2049.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLDN5 | NDF - Highland Park Pedestrian Improvements Q020-118M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | ED-0384 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | PEDESTRIAN IMPROVEMENTS ALONG HIGHLAND BOULEVARD, IN HIGHLAND PARK, BOROUGH OF QUEENS | 2022 | 1170 | 1083.96 | 0 | 0 | 0 | 0 | 0 | 94 | 1177.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-HLND | Neighborhood Dev. Fund - East NY - Highland Park Q020-216M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 205 | P-0896 ED-0384 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | JAMAICA AVENUE, CRESCENT STREET, CYPRESS HILLS - BOROUGH OF BROOKLYN | NEIGHBORHOOD DEVELOPMENT FUND - HIGHLAND PARK | 2022 | 3120 | 2862.07 | 0 | 0 | 0 | 119 | 0 | 96 | 3077.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | NDF-OLDSH | NDF- Old Stone House ADA Upgrades | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | ED-0384 |  | NDF- OLD STONE HOUSE ADA UPGRADES, BOROUGH OF BROOKLYN | NDF- OLD STONE HOUSE ADA UPGRADES | 2022 | 10950 | 0 | 0 | 1095 | 0 | 4380 | 0 | 5475 | 10950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200CPSW | Canarsie Park Sidewalk Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0245K |  |  | RECONSTRUCTION OF SIDEWALK ALONG CANARSIE PARK | 2022 | 3000 | 0 | 0 | 0 | 1505 | 1495 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200CRSL | PPA- Recon. Carousel (B073-218M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 206 207 208 209 214 | P-D017 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PROSPECT PARK WEST , PARKSIDE AVENUE, BETWEEN FLATBUSH AVENUE, OCEAN AVENUE AND PROSPECT PARK SOUTH WEST | PROSPECT PARK - CAROUSEL RECONSTRUCTION | 2022 | 500 | 167.57 | 405 | 17 | 0 | 0 | 0 | 0 | 589.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200FITS | PPA- Prospect Park Fitness Playground/Equipment (B068-119M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-D017 |  | PROSPECT PARK PARADE GROUND | PROSPECT PARK PARADE GROUND - INSTALL ADULT FITNESS EQUIPMENT | 2022 | 1023 | 125.97 | 480 | 0 | 0 | 0 | 0 | 0 | 605.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200HPPP | PPA - Harmony Playground Improvements B073-119M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-D017 P-0412 |  |  | INSTALL SHADE STRUCTURE OVER SANDBOX AND REPLACE NON WORKING PLAYGROUND STUCTURES WITH VIABLE EQUIPMENT | 2022 | 532 | 141.54 | 791 | 0 | 0 | 0 | 0 | 0 | 932.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200LFHH | PPA- Restor. Lefferts Historic House | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 206 207 208 209 214 | P-D017 P-0412 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | PROSPECT PARK WEST, PARKSODE AVENUE, BETWEEN FLATBUSH AVENUE, OCEAN AVENUE AND PROSPECT PARK SOUTHWEST. | PROSPECT PARK - LEFFERTS HISTORIC HOUSE | 2022 | 2500 | 2745.72 | 194 | 262 | 0 | 0 | 0 | 0 | 3201.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200LMBF | PPA Long Meadow Ballfields restoration 34 acre ballfield | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 P-0412 |  |  | BALLFIELD | 2022 | 1033 | 171.64 | 1418 | 0 | 0 | 0 | 0 | 0 | 1589.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPBL | PPA- Long Meadow Ballfields 4-5 (B073-215M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 206 207 208 209 214 | P-D017 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PROSPECT PARK WEST, PARKSIDE AVENUE, BETWEEN FLATBUSH AVENUE, OCEAN AVENUE AND PROSPECT PARK SOUTH WEST. | PROSPECT PARK - LONG MEADOW | 2022 | 750 | 1512.18 | 0 | 0 | 0 | 42 | 0 | 0 | 1554.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPCC | Prospect Park - Reconstruction of Children's Corner | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 |  | PROSPECT PK W, FLATBUSH, PARKSIDE, OCEAN AVES BROOKLYN | PROSPECT PARK - RECONSTRUCTION OF CHILDREN'S CORNER, BOROUGH OF BROOKLYN | 2022 | 553 | 0 | 0 | 0 | 425 | 0 | 0 | 0 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPCS | PP - Shirley Chisholm Recon. Welcome Ctr./Comfort Station | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 206 207 208 209 214 | P-D017 |  | PROSPECT PARK W, PARKSIDE AVE. BET. FLATBUSH AVE., OCEAN AVE. AND PROSPECT PARK SW, BROOKLYN. | RECONSTRUCTION OF COMFORT STATION IN PROSPECT PARK, BROOKLYN. | 2022 | 2250 | 0 | 0 | 0 | 3375 | 3375 | 0 | 0 | 6750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPEC | PPA - Environmental Cntr. Cons., Vale of Cashmere B073-222M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-0412 |  | PROSPECT PK W, FLATBUSH, PARKSIDE, OCEAN AVES BROOKLYN | CONSTRUCTION OF AN ENVIRONMENTAL CENTER AT THE VALE OF CASHMERE IN PROSPECT PARK | 2022 | 26000 | 0 | 0 | 1429 | 0 | 8572 | 8570 | 1429 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPFB | PPA - Flatbush Avenue Park Perimeter B073-315M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 206 207 209 209 214 | P-D017 P-K001 P-K011 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PROSPECT PARK WEST, PARKSIDE AVENUE, BETWEEN FLATBUSH AVENUE, OCEAN AVENUE & PROSPECT PARK SOUTH. BOROUGH OF BROOKLYN | PROSPECT PARK ALLIANCE-FLATBUSH AVENUE PARK PERIMETER RESTORATION | 2022 | 400 | 2258.78 | 0 | 0 | 0 | 284 | 0 | 0 | 2542.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPLV | PPA - Recon. of the Lower Portion of the Vale of Cashmere | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-0412 |  | RECONSTRUCTION OF THE LOWER PORTION OF THE VALE OF CASHMERE PROSPECTPK W, FLATBUSH, PARKSIDE, OCEAN AVES BROOKLYN | PPA - RECONSTRUCTION OF THE LOWER PORTION OF THE VALE OF CASHMERE, BOROUGH OF BROOKLYN | 2022 | 13000 | 0 | 0 | 714 | 0 | 4287 | 4285 | 714 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPMB | PPA-Building Reconstruction (B073-319M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-D017 P-0412 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PROSPECT PARK- BOROUGH OF BROOKLYN | PROSPECT PARK BUILDING | 2022 | 6093 | 498.24 | 0 | 0 | 543 | 962 | 0 | 0 | 2003.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPMO | PPA- New M&O Facility & Compound in Prospect Park B073-415M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 206 207 208 209 214 | P-D017 P-0412 P-K001 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | PROSPECT PARK WEST, PARKSIDE AVENUE BETWEEN FLATBUSH AVENUE, OCEAN AVENUE, PROSPECT PARK SOUTH. BOROUGH OF BROOKLYN.. | PROSPECT PARK ALLIANCE - NEW MAINTENANCE AND OPERATIONS FACILITY AND COMPOUND IN PROSPECT PARK | 2022 | 2000 | 552.51 | 14 | 0 | 2687 | 3050 | 0 | 0 | 6303.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPNM | Prospect Park Nethermead - Repave Walking Path B073-221M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 206 207 214 209 208 | P-D017 |  | PROSPECT PARK W, PARKSIDE AVE. BET. FLATBUSH AVE., OCEAN AVE. AND PROSPECT PARK SW, BROOKLYN | PROSPECT PARK NETHERMEAD - REPAVE WALKING PATH | 2022 | 535 | 35 | 62 | 438 | 0 | 0 | 0 | 0 | 535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPOC | PROSPECT PARK ALLIANCE: RESTORATION TO OCEAN AVE PERIMETER | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-K011 HW-0001K HW-D101 P-K001 P-0412 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | PPA-OCEAN AVENUE PERIMETER | PROSPECT PARK ALLIANCE: RESTORATION TO OCEAN AVE PERIMETER | 2022 | 1750 | 983.77 | 0 | 0 | 10531 | 4441 | 0 | 0 | 15955.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPOP | PPA - Prospect Park Oriental Pavilion B073-416M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-K001 P-C412 P-K011 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | BOROUGH OF BROOKLYN | PROSPECT PARK | 2022 | 2362 | 2272.9 | 0 | 0 | 0 | 218 | 0 | 0 | 2490.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPPH | PPA- PROSPECT PARK PICNIC HOUSE RENOVATION B073-419M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 206 207 208 209 214 200 | P-K001 P-1018 P-C412 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF BROOKLYN | INSTALLATION OF AIR CONDITIONING IN THE PICNIC HOUSE | 2022 | 1000 | 172.78 | 0 | 0 | 566 | 0 | 0 | 0 | 738.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPUV | PPA - Recon. of the Upper Portion of the Vale of Cashmere | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-0412 |  | PROSPECT PK W, FLATBUSH, PARKSIDE, OCEAN AVES BROOKLYN | PPA RECONSTRUCTION OF THE UPPER PORTION OF THE VALE OF CASHMERE, BROOKLYN | 2022 | 13000 | 0 | 0 | 714 | 0 | 4287 | 4287 | 712 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200PPWM | PPA - Prospect Park - Water Line Reconstruction B073-321M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 206 207 214 209 208 | EP-0009 |  | PROSPECT PARK W, PARKSIDE AVE. BET. FLATBUSH AVE., OCEAN AVE. AND PROSPECT PARK SW | PPA - PROSPECT PARK - VALVE REPLACEMENT ON WATER MAIN | 2022 | 1407 | 10 | 129 | 1278 | 0 | 0 | 0 | 0 | 1417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200STFP | PPA - Parade Ground replace turf field 9 (B068-118M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PARADE TURF | 2022 | 1011 | 87.47 | 0 | 0 | 0 | 0 | 663 | 0 | 750.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200TNCR | PPA- Prospect Park Tennis Center | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-D017 |  | BOROUGH OF BROOKLYN | PROSPECT PARK TENNIS CENTER | 2022 | 3150 | 0 | 328 | 0 | 1272 | 1400 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200WCST | PPA-WELLHOUSE COMFORT STATION RENOVATION - (B073-209M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 207 | P-D017 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | PROSPECT PARK, FLATBUSH, OCEAN | RENOVATION OF WELLHOUSE COMFORT STATION IN PROSPECT PARK | 2022 | 900 | 2560.38 | 0 | 0 | 0 | 96 | 0 | 0 | 2656.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO10 | Prospect Park Zoo - Renovation of Discovery Trail | ZOOS | 209 | P-D017 P-0884 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | PROSPECT PARK, BOROUGH OF BROOKLYN | PROSPECT PARK ZOO - RECONSTRUCTION OF THE DISCOVERY TRAIL | 2022 | 337 | 0 | 0 | 908 | 0 | 0 | 0 | 0 | 908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO17 | PPZ- Building "D" Dome Restoration | ZOOS | 200 | P-0887 P-K011 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PPZ- BUILDING"D" DOME RESTORATION | PPZ- BUILDING"D" DOME RESTORATION | 2022 | 164 | 0 | 0 | 0 | 0 | 1475 | 0 | 0 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO18 | PPZ- Off exhibit primate holding expansion | ZOOS | 200 | P-0887 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PPZ- OFF EXHIBIT PRIMATE HOLDING EXPENSION | PPZ- OFF EXHIBIT PRIMATE HOLDING EXPENSION | 2022 | 180 | 0 | 0 | 0 | 0 | 650 | 0 | 0 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-200ZO19 | PPZ- Central plaza stairs,benches reconstruction | ZOOS | 200 | P-0887 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PPZ- CENTRAL PLAZA STAIRS,BENCHES RECONSTRACTION | PPZ- CENTRAL PLAZA STAIRS,BENCHES RECONSTRACTION | 2022 | 250 | 0 | 0 | 650 | 0 | 0 | 7613 | 0 | 8263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201DEHO | De Hostos Playground | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 201 | P-D017 |  | HARRISON AVE. BETWEEN WALTON ST. AND LORIMER ST., BROOKLYN | DE HOSTOS PLAYGROUND | 2022 | 962 | 0 | 0 | 0 | 0 | 740 | 0 | 0 | 740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201EYCK | TEN EYCK PLAZA - RENOVATION OF THE PLAZA B386-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | RENOVATION OF PLAZA | 2022 | 591 | 306 | 1633 | 0 | 198 | 0 | 0 | 0 | 2137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201FROS | Frost Street Playground - Basketball Court Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 201 | P-D017 |  | FROST ST. BET. DEBEVOISE AVE. AND KINGSLAND AVE., BROOKLYN | FROST STREET PLAYGROUND - BASKETBALL COURT RECONSTRUCTION | 2022 | 1075 | 136 | 14 | 986 | 0 | 0 | 0 | 0 | 1136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCBH | McCarren -RC Bathhouse B058-117M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 201 | P-1018 |  | LOCATED N. 12 STREET, LORIMER STREET, MANHATTAN AVENUE, BETWEEN BAYARD STREET, AND BERRY STREET-NASSAU AVENUE, IN THE BOROUUGH OF BROOKLYN. | MCCARREN | 2022 | 3090 | 1020.04 | 8015 | 0 | 2932 | 0 | 0 | 0 | 11967.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCC2 | McCarren Park - Brooklyn | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0819 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MCCARREN PARK - BROOKLYN | 2022 | 6500 | 581.48 | 0 | 0 | 2776 | 2982 | 0 | 0 | 6339.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MCGK | McGolrick Park - Sidewalk Replacement | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 201 | P-D017 P-0245K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RUSSELL STREET, MONITOR STREET, BETWEEN NASSAU AVENUE AND DRIGGS AVENUE | MCGOLRICK PARK - SIDEWALK REPLACEMENT | 2022 | 684 | 249 | 1492 | 0 | 673 | 0 | 0 | 0 | 2414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MDLT | Middleton Playground - Phase 1 Renovations B022-121M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 201 | P-D017 |  | LYNCH ST., MIDDLETON ST. BET. LEE AVE. AND BEDFORD AVE., BOROUGH OF BROOKLYN | MIDDLETON PLAYGROUND - PHASE 1 RENOVATIONS | 2022 | 1075 | 175 | 39 | 0 | 961 | 0 | 0 | 0 | 1175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MPFA | Metropolitan Rec. Center: Fire Alarm Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 201 | P-0506 |  | 261 BEDFORD AVENUE,BROOKLYN. | RECONSTRUCTION OF FIRE ALARM AT METROPOLITAB REC CENTER. | 2022 | 416 | 0 | 592 | 0 | 0 | 0 | 0 | 0 | 592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201MRCY | Marcy Green Park-Reconstruction of Rec. Facilities BG-120M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0245K | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MARCY GREEN PARK - BROOKLYN | 2022 | 5673 | 350 | 3374 | 434 | 1392 | 0 | 0 | 0 | 5550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201STRN | Sternberg Park Upgrades B055-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 201 | P-D017 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | LORIMER STREET, BETWEEN MONTROSE AVENUE AND BOERUM STREET. BROOKLYN | STERNBERG PARK | 2022 | 2600 | 2527.05 | 125 | 0 | 0 | 934 | 0 | 0 | 3586.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201TRNS | Transmitter Park - Shoreline Rehabilitation | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 201 | P-D017 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | WEST ST. BET. KENT ST. AND GREENPOINT AVE., BROOKLYN | TRANSMITTER PARK - SHORELINE REHABILITATION | 2022 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-201WILL | William Sheridan - Brooklyn- B124-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0245K | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WILLIAM SHERIDAN - BROOKLYN | 2022 | 8500 | 583.49 | 5727 | 0 | 0 | 2090 | 0 | 0 | 8400.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202018A | Brooklyn Bridge Park | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 202 | P-K011 P-1200 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | EAST RIVER BETWEEN ATLANTIC AVENUE AND JAY STREET | THIS PROJECT WILL CONSTRUCT BROOKLYN BRIDGE PARK. | 2022 | 61561 | 279620.85 | 500 | 501 | 0 | 0 | 0 | 0 | 280621.85 | 3400 | 0 | 0 | 1240 | 0 | 0 | 0 | 4640
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202BRDG | Susan Smith McKinney Steward Park Reconstruction B223-118MA | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | JAY AND BQE, JAY STREET, PROSPECT STREET, BRIDGE STREET | BRIDGE PARK | 2022 | 8908 | 886 | 0 | 0 | 0 | 0 | 0 | 0 | 886 | 5608.88 | 94 | 571 | 726 | 0 | 0 | 0 | 6999.88
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202C974 | FORT GREENE PK PRISONSH MARTYRS MONU&BR EAGL B32-103MA,203MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 202 | P-0245K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | MYRTLE AVENUE, DEKALB AVENUE, WASHINGTON PARK, ST. EDWARDS STREET | THIS PROJECT WILL RESTORE AND REINSTALL THE FOUR BRONZE EAGLES TO THEIR ORIGINAL LOCATION, RECONSTRUCT THE PLAZA SURROUNDING THE MONUMENT AND EAGLES TO INCLUDE GRANITE LIGHTING SHAFTS, EAGLE PEDESTALS, GRANITEWALL AND COPING, AND RESTORATION OF BRONZE DOOR ON THE MARTYRS' MONUMENT. | 2022 | 4655 | 3969.14 | 0 | 0 | 0 | 0 | 0 | 0 | 3969.14 | 267.5 | 0 | 0 | 0 | 76 | 0 | 0 | 343.5
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CAD2 | Cadman Plaza Park - Brooklyn (B113A-119M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0245K | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CADMAN PLAZA PARK - BROOKLYN | 2022 | 6900 | 475.26 | 0 | 4083 | 2207 | 0 | 0 | 0 | 6765.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CADM | CADMAN PLAZA (RC L/S SURROND BKLN WAR MEM. BLDG ACCESS) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-0245K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CADMAN PLAZA WEST, TILLARY STREET, CADMAN PLAZA EAST, TILLARY STREET,BROOKLYN BRIDGE | THIS PROJECT WILL INSTALL AN ACCESSIBLE RAMP AND ELEVATOR AT THE BROOKLYN WAR MEMORIAL IN CADMAN PLAZA PARK. | 2022 | 265 | 3091.95 | 28 | 0 | 0 | 525 | 0 | 0 | 3644.95 | 619.55 | 0 | 0 | 0 | 0 | 0 | 0 | 619.55
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CBPK | COMMODORE BARRY PARK (B021-119M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 202 200 | P-D017 P-K011 P-0245K P-0977 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | NASSAU STREET, PARK AVENUE, BETWEEN NAVY STREET AND NORTH ELLIOT PLACE. | COMMODORE BARRY PARK | 2022 | 350 | 1341.08 | 122 | 0 | 3923 | 0 | 5000 | 0 | 10386.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CHAP | CHAPIN PLAYGROUND -RECON. SPRINKLER BG-311M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 202 200 | P-1018 P-D017 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | COLUMBIA HTS AT MIDDAGH STREET, BOROUGH OF BROOKLYN | RECONSTRUCTION OF THE SPRINKLER | 2022 | 50 | 88.96 | 0 | 0 | 0 | 320 | 0 | 0 | 408.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202CUGP | Cuyler Gore Park Renovations B026-121M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 202 | P-D017 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CARLTON AVE., FULTON ST., GREEN AVE., BROOKLYN | CUYLER GORE PARK RENOVATIONS | 2022 | 5700 | 200 | 206 | 0 | 2604 | 2790 | 0 | 0 | 5800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202FTGN | Fort Grene Park - entrance & pass (B032-110M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 202 200 | P-K011 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | MYRTLE AVE, CUMBERLAND ST & DEKALB AVE | 500K FROM CC FOR RENOVATION OF WASHINGTON PARK/MYRTLE AVENUE ENTRANCEAT FORT GREENE PARK | 2022 | 500 | 1982.06 | 0 | 0 | 0 | 0 | 206 | 0 | 2188.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202FTGP | PWOB-FT. GREENE PK- PATHS,ENTRANCE RC & DRAINAGE B032-116M) | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 202 | P-D017 P-K011 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | MYRTLE AVENUE, DE KALB AVENUE, WASHINGTON PARK & ST. EDWARDS STREET IN THE BOROUGH OF BROOKLYN. | THE RECON. OF ENTRANCE TO FT. GREENE PK & DRAINAGE IMPROVE. | 2022 | 500 | 873 | 0 | 0 | 0 | 0 | 3969 | 0 | 4842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202GREN | Greene Playground Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 202 | P-D017 |  | GREENE AVE. BET. WAVERLY AVE. AND WASHINGTON AVE., BROOKLYN | GREENE PLAYGROUND RECONSTRUCTION | 2022 | 5200 | 0 | 0 | 0 | 2000 | 2000 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202GRPL | Greene Playground - Reconstruction of Playground | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 202 | P-D017 |  | GREENE AVE. BET. WAVERLY AVE. AND WASHINGTON AVE., BROOKLYN | GREENE PLAYGROUND - RECONSTRUCTION OF PLAYGROUND, BOROUGH OF BROOKLYN | 2022 | 3150 | 250 | 97 | 0 | 1408 | 1495 | 0 | 0 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202WASH | Washington Hall Playground basketball courts, Brooklyn | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0245K | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WASHINGTON AVENUE, PARK AVENUE, HALL STREET | THIS PROJECT WILL RECONSTRUCT THE BASKETBALL COURTS AT WASHINGTON HALL PLAYGROUND. | 2022 | 1655 | 232 | 1305 | 0 | 95 | 0 | 0 | 0 | 1632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-202WPDR | Washington Park Dog Run B111-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 P-K011 P-0245K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | DOG RUN | 2022 | 473 | 163 | 0 | 500 | 0 | 154 | 0 | 0 | 817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203CHPL | Charlie's Place - Asphalt Field to Synthetic Turf | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 203 | P-K011 |  | ELLERY ST. AT DELMONICO PL., HOPKINDS ST. BET. TOMPKINS AVE. AND THROOP AVE. BROOKLYN | CHARLIE'S PLACE - ASPHALT FIELD TO SYNTHETIC TURF, BOROUGH OF BROOKLYN | 2022 | 1300 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203CHRL | Charlie's Place Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 P-0245K | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PARKS - CHARLIE'S PLACE: CONVERT ASPHALT FIELD TO SYNTHETIC TURF; MONDO PERIMETER TRACK, FENCING AND SIDEWALKS ON HOPKINS AND ELLERY. RECONSTRUCT EXISTING BASKETBALL COURT, HANDBALL COURT, COMMUNITY GARDEN, FENCING AND SIDEWALK | 2022 | 1182 | 137 | 892 | 0 | 184 | 0 | 0 | 0 | 1213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203D17E | Von King Cultural Arts Center - Phase 3 B088-111MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 203 | P-1250 P-1018 P-D017 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | HERBERT VON KING PARK CULTURAL ARTS CENTER | VON KING PARK CULTURAL ARTS CENTER PHASE 3 | 2022 | 1000 | 8158.8 | 611 | 0 | 0 | 0 | 0 | 0 | 8769.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203FULT | FULTON PARK - RESTORATION OF COMFORT STATION B038-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 203 200 | P-D017 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BROOKLYN - FULTON STREET, CHAUNCEY STREETS STUYVESANT AND LEWIS AVENUES | FULTON PARK - RESTORATION OF COMFORT STATION | 2022 | 2820 | 1883.84 | 0 | 0 | 0 | 1366 | 0 | 0 | 3249.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203HPUP | Harmony Park - Upgrades and Beautification | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-D017 P-K011 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | UPGRADES AND BEAUTIFICATION TO HARMONY PARK | 2022 | 450 | 0 | 0 | 0 | 0 | 470 | 0 | 0 | 470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203LFGP | Lafayette Gardens Playground Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 203 | P-D017 |  | LAFAYETTE AVE. AND FRANKLIN AVE., BROOKLYN | LAFAYETTE GARDENS PLAYGROUND RECONSTRUCTION, BROOKLYN | 2022 | 1625 | 125 | 0 | 0 | 2000 | 1500 | 0 | 0 | 3625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-203SRTG | Saratoga Park - Playground Reconstruction (B079-119M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 203 | P-D017 |  | HALSEY STREET BETWEEN HOWARD AVENUE AND SARATOGA AVENUE IN THE BOROUGH OF BROOKLYN | SARATOGA PARK- REPAVE ALL PATHS AND PLAZA AREAS, NEW BENCHES, SITTINGAREAS, PICNIC TABLES, DRINKING FOUNTAINS AND GROUND HYDRANTS. IMPROVESECURITY LIGHTING. RECONSTRUCT SMALL PLAYGROUND. PRUNE TREES, IMPROVELANDSCAPING AND CREATE LOW-FENCE ENTRY. | 2022 | 2528 | 306.69 | 1796 | 340 | 0 | 0 | 0 | 0 | 2442.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-204GRCK | Green Central Knoll - Comfort Station B395-115M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | FLUSHING AVENUE, CENTRAL AVENUE, NOLL STREET, EVERGREEN STREET. BOROUGH OF BROOKLYN | GREEN CENTRAL KNOLL - COMFORT STATION | 2022 | 750 | 3686.35 | 0 | 9 | 0 | 376 | 0 | 0 | 4071.35 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 350
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205CYPS | Cypress Park - Renovation of Cypress Park B103-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-K011 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | EUCLID AVENUE BETWEEN DUMONT AVENUE & BLAKE AVENUE, BOROUGH OF BROOKLYN | RENOVATION OF CYPRESS PARK | 2022 | 4000 | 6002.97 | 0 | 0 | 0 | 36 | 0 | 0 | 6038.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205GRPG | Grace Playground Park Renovation Phase I B078-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 |  |  | GRACE PLAYGROUND PARK RENOVATION PHASE I | 2022 | 1973 | 328.4 | 1772 | 0 | 0 | 0 | 0 | 0 | 2100.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205GTHB | Highland Park Community Garden -Greenthumb | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-D017 |  | BOROUGHS OF QUEENS AND BROOKLYN | HIGHLAND PARK COMMUNITY GARDEN | 2022 | 196 | 0 | 0 | 0 | 225 | 0 | 0 | 0 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205HPSB | Highland Park Stone Bridge Q020-418M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HIGHLAND PARK STONE BRIDGE | 2022 | 5068 | 281 | 3314 | 746 | 0 | 0 | 0 | 0 | 4341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LIN1 | Linden Park:Phase 4-Playground,Spray Shower & Basketball crt | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 |  | VERMONT ST. BET. LINDEN BLVD. AND STANLEY AVE.BROOKLYN | LINDEN PARK: RENOVATION OF LINDEN PARK PHASE 4: PLAYGROUND, SPRAY SHOWER & MINI-BASKETBALL COURT | 2022 | 4100 | 400 | 0 | 0 | 2060 | 2040 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LIN2 | Linden Park: Phase 5 Area Renovation | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 205 | P-D017 |  | VERMONT ST. BET. LINDEN BLVD. AND STANLEY AVE. BROOKLYN | LINDEN PARK PHASE 5 AREA RENOVATION | 2022 | 3596 | 230 | 0 | 0 | 2282 | 2281 | 0 | 0 | 4793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205LION | Lion's Pride Playground - B107-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0245K P-D017 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | LION'S PRIDE PLAYGROUND - BROOKLYN | 2022 | 4727 | 535.69 | 3630 | 363 | 0 | 0 | 0 | 0 | 4528.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205PPMT | Public Place - Monument Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 205 | P-D017 |  | ELDERT LA. BETWEEN LIBERTY AVE. AND GLENMORE AVE. BROOKLYN | PUBLIC PLACE - MONUMENT RECONSTRUCTION | 2022 | 250 | 34 | 0 | 0 | 1250 | 0 | 0 | 0 | 1284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-205SHNK | Schenk Playground - B261 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 205 200 | P-D017 P-K011 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | LIVONIA AVENUE BETWEEN BARBEY STREET & SCHENK AVENUE | SCHENK PARK | 2022 | 2527 | 851.93 | -32 | 0 | 1543 | 1437 | 0 | 0 | 3799.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206GDAM | Restoration of Grand Army Plaza Arch, Bailey Ftn, &SRND AREA | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1141 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RESTORATION OF GRAND ARMY PLAZA ARCH, BAILEY FTN, &SRND AREA | RESTORATION OF GRAND ARMY PLAZA ARCH, BAILEY FTN, &SRND AREA | 2022 | 9495 | 955.13 | 241 | 0 | 5054 | 0 | 0 | 0 | 6250.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206GDAS | Grand Army Plaza - Site Restoration B040-120M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1141 P-0412 |  | PROSPECT PARK - GRAND ARMY PLAZA | GRAND ARMY PLAZA - SITE RESTORATION | 2022 | 3403 | 75 | 335 | 2757 | 0 | 0 | 0 | 0 | 3167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206ICKE | HAROLD ICKES PLGRD PH 1 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-K011 P-D017 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BIKE, SKATE PARK | 2022 | 3726 | 904.43 | 78 | 3450 | 0 | 0 | 0 | 0 | 4432.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RH02 | Red Hook - Oversight 9 | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-0245K | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BROOKLYN | RED HOOK - OVERSIGHT 9 | 2022 | 3300 | 60.99 | 982 | 0 | 0 | 2256 | 0 | 0 | 3298.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHBF | Red Hook - Ball field 9/Soccer 2 (B126-117M) | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-0245K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BROOKLYN | RED HOOK - BALL FIELD 9/SOCCER 2 | 2022 | 18836 | 17740.48 | 1178 | 0 | 0 | 2000 | 0 | 0 | 20918.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHBS | Red Hook Track 1/Soccer 3 & Ballfields 1-4 (B126-118M) | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-0245K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | REMEDIATION AND RECONSTRUCTION OF TRACK 1, SOCCER 3 AND BALLFIELDS 1-4 AT RED HOOK PARK. | 2022 | 50380 | 38212.38 | 2 | 0 | 0 | 0 | 25290 | 0 | 63504.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHCF | Red Hook - Community Farm Upgrades (B126-220M) | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 206 | P-D017 P-K011 |  | HALLECK ST., BUSH ST. BET. OTSEGO ST. AND COURT ST. , BROOKLYN | RED HOOK - COMMUNITY FARM UPGRADES | 2022 | 500 | 83 | 0 | 500 | 0 | 0 | 0 | 0 | 583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHO1 | Red Hook- EPA Oversight 5-8 | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-0245K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RED HOOK BROOKLYN | RED HOOK | 2022 | 3300 | 183.14 | 571 | 537 | 0 | 2009 | 0 | 0 | 3300.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHRC | Red Hook Recreation Center Reconstruction | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-0506 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RED HOOK RECREATION CENTER & FIRE ALARMS | 2022 | 34545 | 0 | 1970 | 0 | 10632 | 0 | 21943 | 0 | 34545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-206RHSF | Red Hook - Soccer 1 & 6 | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-0245K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | LOCATED AT HALLECK STREET, BUSH STREET, BETWEEN OTSEGO STREET AND COURT STREET IN THE BOROUGH OF BROOKLYN | RED HOOK RECREATION AREA | 2022 | 21196 | 1766.72 | 0 | 0 | 10739 | 12348 | 0 | 0 | 24853.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207OPML | Ocean Parkway Malls - RC B065-119M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-D017 P-K011 |  |  | OCEAN PARKWAY MALLS - RC | 2022 | 2129 | 218 | 0 | 1919 | 692 | 0 | 0 | 0 | 2829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207RAIN | Rainbow Playground - Playground Update B265 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 207 | P-D017 |  | 6 AVENUE, BETWEEN 55 STREET AND 56 STREET.. BOROUGH OF BROOKLYN | RAINBOW PLAYGROUND UPGRADE | 2022 | 591 | 300 | 0 | 1220 | 380 | 0 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SNST | Sunset Park - Benches -B087-116M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 207 200 | P-K011 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BROOKLYN - 41 STREET, 44 STREET BETWEEN 5 AVENUE & 7 AVENUE | SUNSET PARK | 2022 | 1090 | 1635.65 | 0 | 0 | 0 | 131 | 0 | 0 | 1766.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SPHD | HANDBALL COURT RENOVATIONS AT SUNSET PARK (B087-119M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 |  |  | HANDBALL COURT RENOVATION | 2022 | 682 | 591 | 39 | 0 | 0 | 0 | 0 | 0 | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SPOS | Sunset Park - Open Stage Creation | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 207 | P-D017 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 41 ST., 44 ST., BET. 5 AVE. AND 7 AVE., BROOKLYN | SUNSET PARK - OPEN STAGE CREATION | 2022 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-207SSPK | Sunset Park - Renovation - B087-117MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 207 | P-D017 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 41STREET 44 STREET, BETWEEN 5 AVENUE AND 7 AVENUE. BROOKLYN | SUNSET PARK RENOVATIONS | 2022 | 500 | 1119.75 | 79 | 5 | 0 | 0 | 0 | 0 | 1203.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208HVAC | ST. JOHNS HVAC UPGRADE-B245-114M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 208 | P-1250 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 1251 PROSPECT PLACE, BOROUGH OF BROOKLYN | THE UPGRADE OF THE HVAC IN ST JOHNS RECREATION CENTER | 2022 | 2568 | 4279.71 | 126 | 0 | 0 | 0 | 0 | 0 | 4405.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208K11A | ST. MARK'S AVE. STREETBED PARK RECONSTR; BG-38050-199 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 208 | P-K011 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  |  | 2022 | 1058 | 964.47 | 0 | 0 | 0 | 48 | 0 | 0 | 1012.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208K11E | St. John's Recreation Center - comfort station (B245-111M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 208 200 | P-D017 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | TROY AVENUE, BERGEN, PROSPECT PL, SCHENECTADY AVENUE | IMPROVEMENTS AND RENOVATION OF THE COMFORT STATION IN THE PARK | 2022 | 750 | 2201.28 | 0 | 0 | 0 | 171 | 0 | 0 | 2372.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208LIN2 | Lincoln Terrace Park - Brooklyn (B054-119M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0245K | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | LINCOLN TERRACE PARK - BROOKLYN | 2022 | 4737 | 370 | 3447 | 220 | 333 | 0 | 0 | 0 | 4370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208LTCS | Lincoln Terrace- Comfort Station B054-115M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 208 | P-D017 P-1018 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | EASTERN PARKWAY, EAST NEW YORK AVENUE BETWEEN ROCHESTER AVENUE AND PORTAL STREET. BOROUGH OF BROOKLYN. | LINCOLN TERRACE COMFORT STATION | 2022 | 2000 | 654.54 | 0 | 3859 | 0 | 0 | 0 | 0 | 4513.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208SJFA | ST. John's Rec. Center: Fire Alarm Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 208 | P-0506 |  | 1251 PROSPECT PLACE, BROOKLYN. | FIRE ALARM RECONSTRUCTION AT ST. JOHN'S REC. CENTER. | 2022 | 628 | 0 | 717 | 0 | 0 | 0 | 0 | 0 | 717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-208STFE | ST. JOHNS REC CENTER - OUTDOOR FITNESS EQUIPMENT (B245-118M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 |  |  | OUTDOOR FITNESS EQUIPMENT | 2022 | 682 | 91 | 500 | 0 | 0 | 0 | 0 | 0 | 591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209MTPP | Mount Prospect Park Improvements | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 209 208 | P-D017 |  | EASTERN PKWY., FLATBUSH AVE. BET. UNDERHILL AVE. AND WASHINGTON AVE. BROOKLYN | MOUNT PROSPECT PARK, BOROUGH OF BROOKLYN | 2022 | 390 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-209WNGE | Wingate Park - Basketball Courts | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 209 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | WINTHROP STREET, BROOKLYN AVENUE, RUTLAND ROAD | WINGATE PARK - BASKETBALL COURTS | 2022 | 250 | 2864.56 | 0 | 0 | 0 | 243 | 0 | 0 | 3107.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210245A | OWL'S HEAD PK - GREENWAY CONNECTOR B066-108M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 210 | P-0245K | PROJECT DELAYED DUE TO UNFORESEEN HAZARDOUS CONDITION | BROOKLYN CB 10 AT FORT HAMILTON PARKWAY AND 94TH STREET | JJ CARTY PARK OFFICE | 2022 | 1100 | 346.87 | 0 | 0 | 0 | 0 | 0 | 0 | 346.87 | 1045.53 | 0 | 0 | 0 | 44 | 0 | 0 | 1089.53
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210D17T | SHORE ROAD PATHWAY BICYCLE PATH | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 210 200 | PU-0200 P-D017 P-K011 P-1130 P-0501 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF BROOKLYN | SHORE ROAD PATHWAY | 2022 | 250 | 241 | 0 | 0 | 3917 | 0 | 3411 | 0 | 7569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210DOG | Shore Park - Shore Park Dog Run | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 210 | P-D017 |  | 4 AVE., SHORE RD., BELT PKWY., VERRAZANO BRIDGE, BROOKLYN | SHORE PARK - SHORE ROAD DOG RUN | 2022 | 1000 | 200 | 0 | 641 | 359 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210FTHM | Ft. Hamilton Courts - RC of Bsktball & Tennis Cts -B192A | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 210 | P-0245K |  | 83 STREET TO 85 STREET, BETWEEN COLONIAL ROAD AND NARROWS AVENUE, IN THE BOROUGH OF BROOKLYN | THE RECONSTRUCTION OF 2 BASKETBALL COURTS; PHASE 3 RECONSTRUCTION OF 3 TENNIS COURTS | 2022 | 2600 | 2211.98 | 98 | 183 | 0 | 0 | 0 | 0 | 2492.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210JCAR | John J. Carty Tennis Courts B210-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 210 | P-1018 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | FORT HAMILTON PARKWAY, BETWEEN 94 STREET AND 101STREET, BOROUGH OF BROOKLYN | JOHN J. CARTY TENNIS COURTS | 2022 | 1000 | 3370.94 | 0 | 70 | 0 | 0 | 0 | 0 | 3440.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210JJCP | JJ Carty Park - Renovation of Playground | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 210 | P-D017 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | FT. HAMILTON PKWY. BET. 94 ST. AND 101 ST., BROOKLYN | JJ CARTY PARK - RENOVATION OF PLAYGROUND | 2022 | 5400 | 100 | 0 | 0 | 2710 | 2690 | 0 | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210MCKP | McKinley Park Playground Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 210 | P-D017 |  | 73 ST., FT. HAMILTON PKWY., 7 AVE. BROOKLYN | MCKINLEY PARK PLAYGROUND RECONSTRUCTION, BOROUGH OF BROOKLYN | 2022 | 6500 | 0 | 0 | 0 | 2600 | 2400 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210OWLH | Owl's Head Park - Reconstruction of Basketball Courts | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 210 | P-D017 P-0245K |  |  | OWL'S HEAD PARK - RECONSTRUCTION OF BASKETBALL COURTS | 2022 | 4200 | 100 | 30 | 0 | 3970 | 0 | 4000 | 0 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210OWLR | Owl's Head Park - Reconstruction of Retaining Walls & Paths | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 210 | P-D017 |  | SHORE RD., 68 ST., COLONIAL RD. BROOKLYN | OWL'S HEAD PARK - RECONSTRUCTION OF RETAINING WALLS & PATHS | 2022 | 2600 | 0 | 0 | 0 | 1000 | 1000 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210RUPP | Russell Pedersen Playground Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 210 | P-D017 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | COLONIAL RD. FROM 83 ST. TO 85 ST., BROOKLYN | RUSSELL PEDERSEN PLAYGROUND RECONSTRUCTION | 2022 | 5600 | 100 | 0 | 0 | 2800 | 2600 | 0 | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHCP | Shore Road Park - Path Reconstruction (B082-220M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0973 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SHORE ROAD PARK | 2022 | 1308 | 299 | 0 | 1270 | 0 | 0 | 0 | 0 | 1569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHOR | SHORE ROAD PK - PERIMETER SIDEWALKS (B082A-110M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 210 | P-0245K | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF BROOKLYN | PARK IMPROVEMENTS AND RENOVATIONS TO THE SIDEWALKS | 2022 | 1800 | 127.08 | 0 | 0 | 0 | 0 | 0 | 0 | 127.08 | 1182.46 | 0 | 0 | 0 | 122 | 0 | 0 | 1304.46
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHRD | Shore Road Pk- Rehab C/S -Field House B082-116M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 210 | P-D017 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | 4TH AVENUE, SHORE ROAD, BELT PARKWAY,. BOROUGH OF BROOKLYN. | SHORE ROAD PARK- REHABILITATE COMFORT STATION/FIELD HOUSE | 2022 | 5250 | 5038.91 | 390 | 108 | 0 | 0 | 0 | 0 | 5536.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210SHRS | Shore Park & Parkway - Bike Path Surface Repair BG-715MA | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 |  | SHORE PARKWAY- BOROUGH OF BROOKLYN | SHORE PARKWAY - SOUTH | 2022 | 6146 | 763.45 | 0 | 55 | 0 | 0 | 0 | 0 | 818.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-210VINP | Shore Park & Parkway Vinland Playground Recon. B082-320M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 210 | P-D017 |  | 95 ST & SHORE ROAD | COMPLETE RENOVATION OF PLAYGROUND IN VINLAND PARK | 2022 | 6800 | 279.8 | 0 | 499 | 1176 | 1695 | 0 | 0 | 3649.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-211BBCH | BATH BEACH PARK - PH2 and PH3 (B164-119M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION | 2022 | 5592 | 343.3 | 4005 | 0 | 1334 | 0 | 0 | 0 | 5682.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212ALBE | Albemarle Playground - Resurface Soccer Field (B297-119M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 212 | P-D017 P-K011 |  | ALBEMARLE ROAD, DAHILL ROAD, MCDONALD AVENUE IN THE BOROUGH OF BROOKLYN | ALBEMARLE PLAYGROUND - RESURFACE SOCCER FIELD - REPLACE DAMAGED, HAZARDOUS TURF IN JOP... | 2022 | 591 | 91 | 509 | 91 | 0 | 0 | 0 | 0 | 691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-212FRFD | Friends Field - B372-116M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 212 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BROOKLYN - AVENUE L, EAST 4 STREET, MCDONALD AVENUE, AVENUE M | FRIENDS FIELD | 2022 | 1680 | 2991.91 | 0 | 0 | 0 | 252 | 0 | 0 | 3243.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213ALAE | Asser Levy Park - Adult Exercise Equipment (B080-118M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ADULT EXERCISE EQUIPMENT | 2022 | 914 | 151 | 0 | 723 | 157 | 0 | 0 | 0 | 1031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213BABI | BABI YAR Triangle - Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECONSTRUCTION | 2022 | 1636 | 1704.95 | 135 | 0 | 0 | 0 | 0 | 0 | 1839.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213BOIL | ABE STARK BOILERS AND CHILLERS (B169-111M) | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 213 200 | P-D017 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BOROUGH OF BROOKLYN | ABE STARK BOILERS AND CHILLERS | 2022 | 1000 | 2683.84 | 0 | 128 | 0 | 0 | 0 | 0 | 2811.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213K11B | CONEY ISLAMD BWA;LK MISC RC W37-CORBIN B169-100MA | BEACHES AND BOARDWALKS | 213 | P-K011 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BROOKLYN CB 13 | CONEY ISLAND BOARDWALK REPAIRS AND RENOVATIONS | 2022 | 1453 | 1140.88 | 0 | 0 | 0 | 92 | 0 | 0 | 1232.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213KAI | KAISER PARK RECONSTRUCTION | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-D017 |  | BROOKLYN | KAISER PARK RECON... | 2022 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SCRN | Scarangella Park C/S CONS B106-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 213 200 | P-0245K P-D017 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | WEST 13 STREET, STILLWELL AVENUE, BETWEEN AVENUE U & AVENUE V | RECONSTRUCTION OF SCARANGELLA PARK | 2022 | 2400 | 536.41 | 2424 | 0 | 207 | 0 | 0 | 0 | 3167.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SNPK | Scarangella Park - Reconstruction of Playground B106A-120M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-K011 P-D017 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION | 2022 | 1182 | 612.37 | 0 | 0 | 0 | 250 | 5819 | 0 | 6681.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213SURF | SURF PLAYGROUND - PLAYGROUND RENOVATION (B315-118M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PLGD RENOVATION | 2022 | 4092 | 3700.81 | 35 | 0 | 0 | 184 | 0 | 0 | 3919.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-213WEST | West Playground CS B252-115M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 213 | P-D017 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | AVENUE Z, BETWEEN WEST 1 STREET AND WEST STREET, BOROUGH OF BROOKLYN | WEST PLAYGROUND | 2022 | 1800 | 628.35 | 0 | 2487 | 66 | 0 | 0 | 0 | 3181.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214ANDP | Andries Playground - Phase 1 & 2 Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 214 | P-D017 |  | NOSTRAND AVE. BETWEEN AVE. L AND AVE. K, BROOKLYN | ANDRIES PLAYGROUND - PHASE 1 & 2 RECONSTRUCTION | 2022 | 1200 | 0 | 0 | 0 | 0 | 900 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214KPKP | Kolbert Park RC Perimeter B150 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 |  | RC PERIMTER SIDEWALKS | KOLBERT PARK RC PERIMETER | 2022 | 473 | 450.24 | 0 | 36 | 0 | 0 | 0 | 0 | 486.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214LTFN | Lt. Federico Navaez Tot Lot- RC B397-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 214 | P-1018 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | ARGYLE ROAD AND CORTELYOU ROAD. BROOKLYN | LT. FEDERICO NAVAEZ TOT LOT | 2022 | 950 | 1633.5 | 0 | 0 | 0 | 99 | 0 | 0 | 1732.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214PARK | Acquisition/Recon. - Parkland in 44th Council District | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 |  | COUNCIL DISTRICT 44, CB#14, BOROUGH OF BROOKLYN | NEW PARK/ PLAYGROUND IN CD#44- NOT YET IDENTIFIED | 2022 | 1065 | 0 | 0 | 0 | 0 | 1655 | 0 | 0 | 1655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214RIDE | PPA - Riding Ring Construction B073-421M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 214 200 | P-D017 P-K001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BROOKLYN - PARKSIDE AVENUE, CATON AVENUEM BETWEEN PARADE PLACE AND CONEY ISLAND AVENUE. | PROJECT TO BUILD A RIDING ARENA IN PROSPECT PARK | 2022 | 2900 | 10.14 | 367 | 0 | 1893 | 1880 | 0 | 0 | 4150.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-214UMMA | Umma Park & Plg Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-K011 P-K001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | UMMA PARK AND PLAYGROUND REHABILITATION: PARK GROUNDS REHABILITATION | 2022 | 295 | 0 | 0 | 0 | 0 | 850 | 0 | 0 | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215BBPG | BILL BROWN PLAYGROUND FLDHSE CMFT ST. FY'10 B109-112M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 215 200 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BEDFORD AVENUE BETWEEN AVENUE X & AVENUE Y | RECONSTRUCT FIELD HOUSE INCLUDING NEW REST ROOMS AND COMMUNITY SPACE. | 2022 | 1400 | 5893.81 | 117 | 0 | 0 | 100 | 0 | 0 | 6110.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KELL | Kelly Park Playground - Recon. of Playground (B051-120M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 P-0245K | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | KELLY PARY | 2022 | 1761 | 748 | 0 | 0 | 0 | 0 | 0 | 0 | 748 | 29.4 | 32 | 9939 | 0 | 0 | 0 | 0 | 10000.4
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KLCS | KELLY PARK COMFORT STATION B051-212M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-K011 P-1072 P-0505 |  | BROOKLYN | KELLY PLGD COMFORT STATION | 2022 | 1425 | 75 | 0 | 1625 | 0 | 0 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215KLLY | Kelly Playground Reconstruction B157-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 215 | P-D017 P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | AVENUE S. MORRE PLACE BETWEEN E 16 STREET AND E17 STREET | KELLY PLAYGROUND - RENOVATION PLAYGROUND | 2022 | 2843 | 342 | 2553 | 0 | 255 | 0 | 0 | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MBP2 | Manhattan Beach Park - Ctr Promenade & Beach Entryway Recons | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-1245 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | PHASE 2 | 2022 | 4582 | 607 | 95 | 306 | 0 | 0 | 0 | 0 | 1008 | 4530 | 52 | 0 | 0 | 0 | 0 | 0 | 4582
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MBTC | Manhattan Beach Park:Tennis Courts New Drainage/Resurfacing | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 215 | P-D017 |  |  | MANHATTAN BEACH PARK: RESURFACING AND NEW DRAINAGE OF TENNIS COURTS. | 2022 | 3800 | 215 | 0 | 0 | 2000 | 1800 | 0 | 0 | 4015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MCDD | McDonald Playground - RC Play Equipment Area B244-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 215 | P-0245K P-D017 P-K011 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | BROOKLYN - MCDONALD BETWEEN AVENUE S & AVENUE T | MCDONALD PLAYGROUND | 2022 | 1010 | 499.88 | 3150 | 0 | 148 | 0 | 0 | 0 | 3797.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MCDP | McDonald Playground Reconstruction Phase 2 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 215 | P-D017 |  | MCDONALD AVE. BETWEEN AVE. S AND AVE. T BROOKLYN | MCDONALD PLAYGROUND RECONSTRUCTION PHASE 2, BK | 2022 | 11700 | 0 | 0 | 0 | 4600 | 4400 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215MELL | MELLET PLAYGROUND- RECONSTRUCT PLAYGROUND (B197-118M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0245K |  |  | RECONSTRUCTION | 2022 | 2728 | 2439.02 | 222 | 0 | 0 | 0 | 0 | 0 | 2661.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215PB15 | EMMONS AVENUE SIDEWALKS & SHEEPSHEAD PIER RCNSTR NYSMMGRANTS | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 215 200 | P-0245K | PROJECT DELAYED PENDING NON-CITY GRANT APPROVAL | BRIGHTON 15TH ST AND CONEY ISLAND AVENUE, BROOKLYN | PEDESTRIAN BIKEWAY CONSTRUCTION, BRIGHTON 15TH ST AND CONEY ISLAND AVENUE, BROOKLYN | 2022 | 407 | 51.49 | 0 | 0 | 0 | 0 | 0 | 0 | 51.49 | 155.58 | 0 | 0 | 0 | 0 | 0 | 141 | 296.58
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-215PIER | SHEEPSHEAD BAY PIERS B393-118M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-0501 PU-0200 |  | SHEEPSHEAD BAY PIERS | SHEEPSHEAD BAY PIERS | 2022 | 4096 | 367.04 | 0 | 3729 | 0 | 0 | 0 | 0 | 4096.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216BHIP | BETSY HEAD - IMAGINATION PLGD CS B008 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-0505 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BETSY HEAD - IMAGINATION PLGD CS | 2022 | 2000 | 3864.89 | 41 | 144 | 0 | 800 | 0 | 0 | 4849.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216CHES | Chester Park - Playground Renovation Phase 1 B362-120M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 216 | P-0245K P-D017 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CHESTER ST. TO BRISTOL ST. BETWEEN SUTTER AVE. AND PITKIN AVE., BROOKLYN | CHESTER PARK - PLAYGROUND RENOVATION PHASE 1 | 2022 | 6000 | 251.32 | 27 | 0 | 4000 | 3972 | 0 | 0 | 8250.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OCAN | Ocean Hill Playground - Brooklyn | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0245K |  |  | OCEAN HILL PLAYGROUND - BROOKLYN | 2022 | 5891 | 697.75 | 0 | 4921 | 0 | 0 | 0 | 0 | 5618.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OSBN | Osborn Playground - Park Renovation (B343-119M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 216 | P-D017 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | LINDEN BLVD, OSBORN STREET, ROCKAWAY AVENUE, HEGEMAN AVENUE IN THE BOROUGH OF BROOKLYN | OSBORN PLAYGORUND PARK RENOVATION-CONVERT EXISTING FIELD TO SYNTHETICTURF WITH PERIMETER TRACK AND ACCESS RAMP. | 2022 | 3427 | 387.24 | 1897 | 0 | 911 | 0 | 0 | 0 | 3195.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216OSPL | Osborn Playground - Phase 2 Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 216 | P-D017 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | LINDEN BLVD., OSBORN ST., ROCKAWAY AVE., HEGEMAN AVE., BROOKLYN | OSBORN PLAYGROUND - PHASE 2 RECONSTRUCTION | 2022 | 1075 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-216PS25 | PS 125 Playground - Brooklyn | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0245K |  |  | PS 125 PLAYGROUND - BROOKLYN | 2022 | 1064 | 174 | 0 | 759 | 141 | 0 | 0 | 0 | 1074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217AQBO | Paerdegat Aquatic Center Boiler Reconstruction | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-1250 |  |  | PAERDEGAT AQUATIC CENTER BOILER RECONSTRUCTION | 2022 | 500 | 45 | 500 | 0 | 0 | 0 | 0 | 0 | 545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217D017 | WYCKOFF HOUSE PARK CULT. EDUC. COMPLX B376-113M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 217 | P-D017 P-K011 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RALPH AVENUE, DITMAS AVENUE AND CLARENDON ROAD | THIS PROJECT WILL CONSTRUCT A COMFORT STATION IN WYCKOFF HOUSE PARK. | 2022 | 2250 | 1635.55 | 5310 | 354 | 175 | 0 | 0 | 0 | 7474.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217HMCS | Harry Maze Playground - Comfort Station Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 217 | P-D017 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | AVE. D, DITMAS AVE. BET. E. 56 ST. AND E. 57 ST., BROOKLYN | HARRY MAZE PLAYGROUND - COMFORT STATION RECONSTRUCTION | 2022 | 540 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PADG | Paerdegat Park - Reconstruction of Turf | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 217 | P-0245K |  | ALBANY AVE., E. 40 ST. BET. FARRAGUT RD. AND FOSTER AVE. BROOKLYN | PAERDEGAT PARK - RECONSTRUCTION OF TURF, BOROUGH OF BROOKLYN | 2022 | 7150 | 0 | 300 | 0 | 2500 | 0 | 2700 | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217PDGT | PAERDEGAT ATHLETIC CLUB - HVAC WORK | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1250 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF BROOKLYN | PAERDEGAT ATHLETIC CLUB HVAC WORK | 2022 | 1850 | 419.78 | 0 | 0 | 0 | 562 | 0 | 0 | 981.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-217WYKF | WYCKOFF FARMHOUSE - ROOF RESTORATION B376-111M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-0245K | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF BROOKLYN | FARMHOUSE ROOF RESTORATION | 2022 | 550 | 229.62 | 0 | 0 | 0 | 0 | 0 | 0 | 229.62 | 451.1 | 0 | 0 | 0 | 99 | 0 | 0 | 550.1
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BKBF | Breukelen Ball Fields Renovations (Phase I) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 218 | P-D017 |  | LOUISIANA AVE., STANLEY AVE., FLATLANDS AVE., WILLIAMS AVE. BROOKLYN | BREUKELEN BALL FIELDS RENOVATIONS (PHASE I), BOROUGH OF BROOKLYN | 2022 | 6500 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BPLG | Bildersee plgd-new plgd and ph2 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-K011 P-0245K | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECONSTRUCTION | 2022 | 3227 | 35.99 | 0 | 0 | 0 | 2367 | 0 | 0 | 2402.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218BVHP | Bayview Houses Playground Reconstruction - Phase 2 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 218 | P-D017 |  | SEAVIEW AVE. BETWEEN E. 99 ST. AND E. 101 ST. BROOKLYN | BAYVIEW HOUSES PLAYGROUND RECONSTRUCTION - PHASE 2 | 2022 | 494 | 0 | 0 | 0 | 0 | 0 | 380 | 0 | 380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218CCMF | CANARSIE PARK PHASE V- COMFORT STATION B018-214M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 218 200 | P-D017 P-K011 P-1018 P-0245K | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SEAVIEW AVENUE BETWEEN PAERDEGAT BASIN AND EAST 93 STREET, EAST 102 STREET AND FRESH CREEK BASIN | NEW COMFORT STATION FOR CRICKET, SKATE PARK AND PLAYGROUND | 2022 | 850 | 755.48 | 2702 | 389 | 374 | 0 | 0 | 0 | 4220.48 | 0 | 466 | 0 | 0 | 0 | 0 | 0 | 466
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218GOLF | BK Golf Alliance - Marine Pk. Golf Course - B057-119M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 218 200 | P-D017 P-K011 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF BROOKLYN - FLATBUSH AVENUE, GERRITSEN AVENUE, FILLMORE AVENUE, JAMAICA BAY | BROOKLYN GOLF ALLIANCE INC. - MARINE PARK GOLF COURSE | 2022 | 840 | 282 | 131 | 837 | 482 | 0 | 0 | 0 | 1732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218HKMN | Hickman Playground Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 218 | P-D017 |  | VETERANS AVE. BETWEEN E. 66 ST. AND E 68 ST. BROOKLYN | HICKMAN PLAYGROUND RECONSTRUCTION, BOROUGH OF BROOKLYN | 2022 | 4550 | 0 | 0 | 0 | 0 | 3500 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218JFEE | Jacob Joffe Playground- Park Renovations | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-K011 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | AVENUE K BETWEEN EAST 58 STREET AND EAST 59 STREET. | JACOB JOFFE PLAYGROUND | 2022 | 3000 | 2979.87 | 0 | 0 | 0 | 190 | 0 | 0 | 3169.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218LOTT | HENDRICK I. LOTT HOUSE -INTERIOR RESTORATION | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 218 | P-D017 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF BROOKLYN | PHASE 3 - RENOVATION OF THE INTERIOR OF THE HOUSE FOR PUBLIC USE | 2022 | 800 | 131 | 405 | 0 | 1820 | 1988 | 0 | 0 | 4344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218MPOV | Marine Park Oval Reconstruction B057-120M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 215 218 | P-D017 P-0077 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MARINE PARK BICYCLE AND PEDESTRIAN OVALS - RE-SURFACE ASPHALT TRACK. | 2022 | 5114 | 607 | 14 | 0 | 5279 | 0 | 5206 | 0 | 11106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218MPPG | Marine Park Playground - Recon. of Playground 278 B057-220M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 218 215 | P-D017 P-0245K P-K011 |  |  | RECONSTRUCTION OF A PLAYGROUND AT MARINE PARK IN BROOKLYN | 2022 | 4000 | 350 | 67 | 0 | 1000 | 0 | 4863 | 0 | 6280 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 4000
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218PWMP | Power-Memorial- Seating Area ( B219-120M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 218 | P-D017 P-K011 P-K001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | AVENUE N BETWEEN EAST 49 STREET & UTICA AVENUE | POWER -MEMORIAL PLAYGROUND | 2022 | 250 | 389.87 | 33 | 0 | 2000 | 2032 | 0 | 0 | 4454.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-218SUNN | Sunners Playground - Renovate Playground (B206-119M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 218 | P-D017 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | AVENUE H BETWEEN KINGS HIGHWAY, EAST 49 STREET IN THE BOROUGH OF BROOKLYN | RENOVATION OF PLAYGROUND DEVASTATED BY HURRICANE SANDY - SUNNERS PLAYGROUND | 2022 | 1432 | 202 | 1260 | 0 | 290 | 0 | 0 | 0 | 1752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH01 | ANCHOR PARK- Betsy Head (B008-) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 216 | P-0605 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BLAKE AVENUE, DUMONT AVENUE, LIVONIA AVENUE BETWEEN STRAUSS STREET, HOPKINSON AVENUE AND BRISTOL STREET | BETSY HEAD | 2022 | 10388 | 2785.13 | 0 | 0 | 0 | 386 | 0 | 0 | 3171.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH02 | Betsy Head Park Comfort Station Reconstruction (B008-218M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-0605 |  |  | BETSY HEAD RECONSTRUCTION | 2022 | 4000 | 2917.61 | 122 | 0 | 0 | 0 | 0 | 0 | 3039.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH03 | Betsy Head Park Syn. Turf, Field, Track, Sport Crts Ft Ctr | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-0605 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | BETSY HEAD | 2022 | 20091 | 14770.55 | 0 | 0 | 0 | 4105 | 0 | 0 | 18875.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ANCH04 | ANCHOR PARK- Betsy Head Multi-Purpose Play Area Reconst. | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 216 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BETSY HEAD | 2022 | 7200 | 6583.08 | 0 | 0 | 0 | 410 | 0 | 0 | 6993.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BARRYP | Barry Playground | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0245K |  |  | RECON OF BARRY PLAYGROUND | 2022 | 3500 | 0 | 0 | 0 | 1755 | 1745 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPA | Belt Pkwy Lndscp Restoration & Tree Planting Ph2 B166-113M | LAND ACQUISITION AND TREE PLANTING | 200 | P-0822 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RESTORATION OF LANDSCAPE AND TREE PLANTING ALONG THE BELT PARKWAY | 2022 | 2260 | 6851.83 | 0 | 0 | 0 | 1734 | 0 | 0 | 8585.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPC | FY14 Belt Parkway Street Trees | LAND ACQUISITION AND TREE PLANTING | 299 | HB-0643 P-0822 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BROOKLYN | STREET TREE PLANTING | 2022 | 5826 | 6000.81 | 140 | 0 | 0 | 1598 | 0 | 0 | 7738.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPD | CON - BIKE PATH THRU CANARSIE PARK WEST | LAND ACQUISITION AND TREE PLANTING | 200 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF BROOKLYN | CONSTRUCTION OF BIKE PATH THRU CANARSIE PARK WEST | 2022 | 1550 | 182.14 | 0 | 0 | 0 | 0 | 0 | 0 | 182.14 | 1359.89 | 0 | 190 | 0 | 0 | 0 | 0 | 1549.89
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BELTPE | Mill Basin Bridge Trees | LAND ACQUISITION AND TREE PLANTING | 200 | HB-1023 PU-0200 |  | MIL BASIN BRIDGE TREES | MIL BASIN BRIDGE TREES | 2022 | 10429 | 1051.11 | 0 | 10310 | 0 | 0 | 0 | 0 | 11361.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKPAV1 | Brooklyn Multisite Pavement Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BROOKLYN | BROOKLYN MULTISITE PAVEMENT RECONSTRUCTION | 2022 | 2290 | 356.44 | 0 | 0 | 4491 | 0 | 0 | 0 | 4847.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BKPLG1 | Brooklyn MPPA SOGR Reconstruction BG-220M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | WP-0169 P-1018 |  | BROOKLYN | THIS PROJECT WILL RECONSTRUCT MULTI-PURPOSE PLAY AREAS IN DYKER PLAYGROUND, O'ROURKE PLAYGROUND AND WILSON PLAYGROUND. BOROUGH OF BROOKLYNNY. | 2022 | 3200 | 100 | 47 | 7459 | 0 | 0 | 0 | 0 | 7606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BQGRN | BQ GREEN | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BQ GREEN | 2022 | 11818 | 0 | 0 | 0 | 0 | 2575 | 0 | 0 | 2575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BRIGHM | Brigham Park - plgd & passive area B057-212M/512M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 215 218 200 | P-D017 P-0245K P-1018 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | BOROUGH OF BROOKLYN | GRIGHAM STREET PARK DESIGN | 2022 | 400 | 6547.44 | 0 | 0 | 0 | 490 | 0 | 0 | 7037.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BSKBL1 | Brooklyn Basketball Courts Reconstruction (SoGR) BG-320M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 WP-0169 |  | BROOKLYN | BROOKLYN BASKETBALL COURTS RECONSTRUCTION (SOGR) | 2022 | 2800 | 45 | 3147 | 369 | 0 | 0 | 0 | 0 | 3561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BTSYEL | Betsy Head Pool Tunnel Electrical Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1008 |  |  | BETSY HEAD POOL TUNNEL ELECTRICAL RECONSTRUCTION | 2022 | 190 | 0 | 0 | 190 | 0 | 0 | 0 | 0 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BTSYRC | Besy Head Pool Structural Recon | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1008 |  | BETSY HEAD, BROOKLYN | BESY HEAD POOL STRUCTURAL RECON | 2022 | 225 | 0 | 225 | 0 | 0 | 0 | 0 | 0 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BUSHDE | Bushwick Inlet Park: CitiStorage Demolition | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 |  |  | FRIENDS OF BUSHWICK INLET PARK, CM LEVIN, AM LENTOL, SS KAVANAGH AND CONGRESSWOMAN MALONEY ARE PUSHING FOR THE ADMINISTRATION TO FUND THE NEXT PHASE OF BIP; DEMOLITION OF THE REMAINING BUILDING AT CITISTORAGE. PARKS ESTIMATED THE DEMOLITION COST AT $36.8M AS PART OF OUR FY20 JAN PLAN SUBMISSION. CITY HALL HAS ASKED EDC TO DEVELOP AN UPDATED DEMOLITION COST. EDC'S COST ESTIMATE IS $16.321M. | 2022 | 75021 | 0 | 0 | 0 | 0 | 0 | 16921 | 58100 | 75021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWCC04 | BKLYN MULTISITE CMFT STA.- TILDEN & BANNEKER BG-111M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 203 218 | P-1018 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | IN BOROUGH OF BROOKLYN. | RECONSTRUCTION OF COMFORT STATIONS AT BANNEKER AND TILDEN PLAYGROUNDS | 2022 | 1300 | 1895.62 | 34 | 80 | 0 | 0 | 0 | 0 | 2009.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWK11I | RQMT CNTR BKLYN BP FY00 PLEQ SFTYSRF PAV FNC GNLSW BG-300M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-K011 |  | BROOKLYN : VARIOUS PARKS AND PLGDS | BROOKLYN REQUIREMENTS CONTRACT FY2000 BP FUNDS | 2022 | 966 | 928.78 | 0 | 0 | 0 | 35 | 0 | 0 | 963.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWK11J | BROOKLYN REQMT FY03/4 INCL OCEAN PKWY MALLS BENCHES BG-504M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 207 212 213 214 215 | P-K011 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BROOKLYN BOROUGH-WIDE | BROOKLYN PARKS REQUIREMENT CONTRACT FY03 | 2022 | 839 | 578.61 | 0 | 0 | 0 | 119 | 0 | 0 | 697.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2BWRPAV | Brower Park Path Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BROOKLYN | BROWER PARK PATH RECONSTRUCTION | 2022 | 700 | 0 | 609 | 0 | 0 | 0 | 0 | 91 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIB22H | Coney Island Beach and Boardwalk (Phase 1) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-1018 |  | BROOKLYN | CONEY ISLAND BEACH AND BOARDWALK (PHASE 1) | 2022 | 114558 | 0 | 1500 | 0 | 0 | 0 | 113058 | 0 | 114558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIBBOL | Coney Island Boardwalk - Cons Security Measures B169-120M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-1095 |  | CONEY ISL BDWK- CONSTRUCTION SECURITY MEASURES | CONEY ISL BDWK- CONSTRUCTION SECURITY MEASURES | 2022 | 0 | 0 | 0 | 5150 | 0 | 0 | 0 | 0 | 5150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIGNWY | CONEY ISLAND GREENWAY PROPOSED SAFETEA GRANT | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 213 | P-0007 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BRIGHTON 15TH STREET & CONEY ISLAND AVE | CONEY ISALAND GREENWAY (AKA BRIGHTON 15TH STREET & CONEY ISLAND AVE | 2022 | 2608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2560 | 2560
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CIWALK | CONEY ISLAND BWALK - RC OF VARIOUS SEGMENT B169-220M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-1245 P-0007 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CONEY ISLAND BOARDWALK IN THE BOROUGH OF BROOKLYN | THE RECONSTRUCTION OF VARIOUS SEGMENTS OF CONEY ISLAND BOARDWALK - KNOWN AS PROPERTY B169.. | 2022 | 9818 | 290.15 | 36 | 0 | 5714 | 0 | 5750 | 0 | 11790.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CONYGS | CONEY ISLAND COASTAL RESIL. GREENSTREETS BG-515MA | LAND ACQUISITION AND TREE PLANTING | 200 | P-0822 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF BROOKLYN | TO STRENGTHEN CONEY ISLAND RESILIENCY THROUHG GREENSTREETS. | 2022 | 990 | 326.27 | 0 | 0 | 0 | 161 | 0 | 0 | 487.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2COOPCS | Cooper Park-Reconstruction of Comfort Station | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0505 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COOPER PARK-RECONSTRUCTION OF COMFORT STATION | 2022 | 2243 | 214.56 | 0 | 1636 | 0 | 0 | 0 | 0 | 1850.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIBN2 | CPI PH1- J. Owens, Stockton & Stroud C/S RC BG-815M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-1018 | PROJECT DELAYED DUE TO SCHEDULING OF UTILITY WORK | JESSE OWENS- STUYVESANT & LAFAYETTE AVES.- STOCKTON N- MARCY & PARK AVENUES, STROUD - PARK PLACE, CLASSON AVENUE, STERLING PLACE, WASHINGTON AVENUE, ALL IN THE BOROUGH OF BROOKLYN | THE RECONSTRUCTION OF JESSE OWENS, STOCKTON AND STROUD PLAYGROUND COMFORT STATIONS IN BROOKLYN | 2022 | 315 | 5090.62 | 0 | 0 | 0 | 467 | 0 | 0 | 5557.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIBPG | CPI PH2 - Bartlett Playground B286-218M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RECONSTRUCTION OF BARTLETT PLAYGROUND, BOROUGH OF KINGS | 2022 | 9636 | 6336.53 | 205 | 0 | 0 | 1644 | 0 | 0 | 8185.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIEPP | CPI PH2 - R/C Epiphany Playground (B405 -116M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 201 | P-1018 WP-0169 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BOROUGH OF BROOKLYN - BERRY STREET, BETWEEN SOUTH 9TH STREET, AND SOUTH 10TH STREET (11211) | THE RECONSTRUCTION OF EPIPHANY PLAYGROUND (CPI) | 2022 | 2879 | 404.98 | 3576 | 0 | 0 | 0 | 0 | 0 | 3980.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIJRM | CPI - JEROME PLGD | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 |  |  | CPI - JEROME PLGD B246 | 2022 | 7200 | 0 | 0 | 0 | 2410 | 2990 | 0 | 0 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILAG | CPI ph2. - LaGuardia Playground Ph 2. (B167-217M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 201 | P-0245K P-1018 |  | SOUTH 4 STREET BETWEEN ROEBLING STREET AND WILLIAMSBURG GRIDGE RAMP, BOROUGH OF BROOKLYN | RECONSTRUCTION OF LAGUARDIA PLAYGROUND | 2022 | 3545 | 3336.38 | 214 | 154 | 0 | 450 | 0 | 0 | 4154.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPILJP | CPI PH2 - RC- Lt. Joseph Petrosino Park (B099-) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 211 | WP-0169 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 16TH AVENUE, NEW UTRECHT AVENUE, BETWEEN 70 TH STREET AND 71TH STREET | THE RECONSTRUCTION OF LT. JOSEPH PETROSINO PARK PLAYGROUND | 2022 | 4605 | 4364.6 | 0 | 86 | 0 | 0 | 0 | 0 | 4450.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIMJP | CPI - MARC & JASONS PLGD | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 209 | P-1018 |  | MARC & JASON PLGD | MARC & JASONS PLGD | 2022 | 7800 | 0 | 0 | 0 | 2610 | 3240 | 0 | 0 | 5850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPINEW | CPI Ph2.- Newport Comfort Station (B339-117M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 216 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | NEWPORT AVENUE, THATFORD AVENUE AND OSBORN STREET | CPI - PH.2 - NEWPORT COMFORT STATION | 2022 | 1500 | 1256.72 | 0 | 0 | 0 | 356 | 0 | 0 | 1612.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2CPIWKS | CPI PH2- Weeksville Playground | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 203 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | HOWARD AVENUE, BETWEEN ATLANTIC AVENUE AND HERKIMER STREET | WEEKSVILLE | 2022 | 2061 | 1380.31 | 0 | 0 | 0 | 0 | 273 | 0 | 1653.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2DCTBWR | Telephone Communication Ducts | VEHICLES AND EQUIPMENT | 200 | P-0931 |  | BROOKLYN | TELEPHONE COMMUNICATION DUCTS | 2022 | 90 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2DCTKSR | Kaiser Park | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0931 |  | KAISER PARK, BROOKLYN | KAISER PARK | 2022 | 91 | 11 | 80 | 0 | 0 | 0 | 0 | 0 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2DCTSNS | Sunset Park, Brooklyn | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | PU-0025 |  | SUNSET PARK, BROOKLYN | SUNSET PARK, BROOKLYN | 2022 | 150 | 161 | 109 | 0 | 0 | 0 | 0 | 0 | 270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2DCTSTJ | Telephone Communication Ducts | VEHICLES AND EQUIPMENT | 200 | P-0931 |  | BROOKLYN | TELEPHONE COMMUNICATION DUCTS | 2022 | 85 | 0 | 85 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2FGCSUP | FORT GREENE PARK--COMFORT STATION UPGRADES | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-K011 |  |  | FORT GREENE PARK--COMFORT STATION UPGRADES | 2022 | 1950 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATE10 | Gateway Estates-Multi-purpose ballfield B548-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0245K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | COMBINING GATEWAY PROJECTS | 2022 | 8377 | 1148.08 | 0 | 5963 | 0 | 1289 | 0 | 0 | 8400.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GATEW6 | Gateway Estates -Cleveland Pk playground (B547- 114M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 205 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF BROOKLYN | CONSTRUCTION OF A PLAYGROUND IN GATEWAY ESTATES- PHASE II | 2022 | 2170 | 10.83 | 0 | 0 | 0 | 0 | 1678 | 0 | 1688.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWB25 | GPWB-Bushwick Inlet Park-Motiva Parcel Remediation B529-119M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-0839 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | GREENPOINT WILLIAMSBURG BROOKLYN | GREENPOINT WILLIAMSBURG | 2022 | 11603 | 1229.91 | 0 | 0 | 3920 | 4908 | 0 | 0 | 10057.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWBKT | GPWB- 50 Kent Development | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-0839 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BOROUGH OF BROOKLYN | GPWB- KENT DEVELOPMENT | 2022 | 9157 | 6481.16 | 342 | 0 | 0 | 1100 | 0 | 0 | 7923.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GPWBPC | FY'22 Bushwick Inlet - Park Creation | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-D017 |  | KENT AVE. BET. QUAY ST. AND N 9 ST. BROOKLYN | FY'22 BUSHWICK INLET - PARK CREATION, BOROUGH OF BROOKLYN | 2022 | 1300 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GRNTHB | Green Thumb Irrigation systems (Brooklyn) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-K011 P-1018 |  | BOROUGH OF BROOKLYN | BROOKLYN IRRIGATION SYSTEM | 2022 | 2600 | 0 | 0 | 0 | 1300 | 1000 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GRST01 | Greenstreets - Brooklyn Tree Planting & Greenstreets | LAND ACQUISITION AND TREE PLANTING | 200 | P-0822 P-D822 |  | BOROUGH OF BROOKLYN - UNION STREET BETWEEN BOND AND 3RD AVENUE | GREENSTREETS- BOROUGH OF BROOKLYN | 2022 | 136 | 35 | 0 | 0 | 653 | 0 | 0 | 0 | 688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2GTGRDN | RPZ installation at various sites in Brooklyn BG-618M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 P-D017 P-1250 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RPZ INSTALLATION | 2022 | 489 | 61 | 585 | 0 | 167 | 0 | 0 | 0 | 813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2HWRDPL | HOWARD POOL CNYG-918MA1 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BROOKLYN | POOL | 2022 | 1077 | 25 | 1077 | 0 | 113 | 0 | 0 | 0 | 1215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2ISAGRD | ISABAHLIA GARDENS WATER SPIGOT | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-K011 |  |  | CONSTRUCTION OF WATER SPIGOT FOR ISABAHLIA GARDENS IN BROOKLYN. | 2022 | 220 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2KISRPV | Kaiser Park Path and Tennis Court Pavement Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 |  | IN BROOKLYN | KAISER PARK PATH AND TENNIS COURT PAVEMENT RECONSTRUCTION | 2022 | 8000 | 0 | 0 | 0 | 2500 | 0 | 2500 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2LITCHF | PPA - Litchfield Villa Renovations B073-120M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION | 2022 | 272 | 35.98 | 162 | 0 | 736 | 896 | 0 | 0 | 1829.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2MTFLTR | Met Pool Filter plant Bk | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 P-1008 P-0510 |  | MET POOL, BK | MET POOL FILTER PLANT BK | 2022 | 2255 | 0 | 57 | 0 | 0 | 267 | 1931 | 0 | 2255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PDBRC2 | Brownsville Rec Ctr RC B270-214M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BROOKLYN | BROWNSVILLE REC CTR | 2022 | 18000 | 1739.08 | 15027 | 0 | 1 | 3704 | 0 | 0 | 20471.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PDSSRC | Sunset Pk Rec Ctr RC B087-115M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-0506 P-1018 P-D017 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BROOKLYN | SUNSET PK RC | 2022 | 4000 | 767.66 | 0 | 1 | 2244 | 2763 | 0 | 0 | 5775.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PEPWIN | Prospect Park Parade Ground PEP HQ window replace CNYG-2819M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 |  | PROSPECT PARK PARADE GROUND PEP HQ, BROOKLYN | PROSPECT PARK PARADE GROUND PEP HQ WINDOW REPLACE | 2022 | 600 | 0 | 700 | 0 | 315 | 0 | 0 | 0 | 1015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PGRD11 | MULTISITE- PAVEMTS,TENNIS CTS, BB CTS, FENCING (BG-711M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0245K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BOROUGH OF BROOKLYN | MULTISITE- PAVEMENTS, TENNIS COURTS, BASKETBALL COURTS, FENCING , PLANTINGS AND GENERAL SITE WORK AT VARIOUS LOCATIONS IN THE BOROUGH OF BROOKLYN | 2022 | 1576 | 3169.21 | 0 | 0 | 0 | 0 | 0 | 0 | 3169.21 | 192.81 | 0 | 0 | 0 | 0 | 40 | 0 | 232.81
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PKTR21 | FY21-Park Trees - Brooklyn | LAND ACQUISITION AND TREE PLANTING | 200 | P-0822 |  | FY21-PARK TREES - BROOKLYN | FY21-PARK TREES - BROOKLYN | 2022 | 2880 | 329 | 2880 | 0 | 0 | 0 | 0 | 0 | 3209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLAY13 | MULTISITE- OCEAN HILL PLGD, WINGATE, MLK SPRAY SHWER BG-114M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 209 216 200 205 | P-K011 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BOROUGH OF BROOKLYN | LINCOLN TERRACE PLAYGROUND AND OCEAN HILL PLAYGROUND | 2022 | 635 | 1713.9 | 0 | 0 | 0 | 128 | 0 | 0 | 1841.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PLG13A | RECON. FENCING & GEN. SITEWORK-RAPPAPORT HOCKEY RINK-BG311M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 212 200 | P-K011 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BOROUGH OF BROOKLYN | RECONSTRUCTION OF PLAY EQUIPMENT, SAFERY SURFACING, HANDBALL COURT, GENERAL SITEWORK-RAPPAPORT ICE RINK | 2022 | 200 | 86.13 | 0 | 0 | 0 | 0 | 75 | 0 | 161.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PNYC01 | PlaNYC - McCarren Pk Pool & Bathhouse RC - B058-108M/408M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 201 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | LORIMER STREET BETWEEN BAYARD STREET AND DRIGGS AVENUE | THIS PROJECT WILL RECONSTRUCT THE POOL AND BATHHOUSE AT MCCARREN PARK. | 2022 | 50510 | 56863.39 | 0 | 0 | 0 | 0 | 63 | 0 | 56926.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PNYC05 | PlaNYC - Calvert Vaux CS/M&O bldg (B125-112M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 213 | P-0507 P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BOROUGH OF BROOKLYN | CALVERT VAUX | 2022 | 2760 | 9707.45 | 59 | 917 | 0 | 0 | 0 | 0 | 10683.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PNYT32 | Brooklyn Street Tree Planting FY22-CB 5 &16 | LAND ACQUISITION AND TREE PLANTING | 200 | P-0822 |  | BROOKLYN | BROOKLYN STREET TREE PLANTING FY22-CB 5 &16 | 2022 | 2990 | 0 | 0 | 0 | 2990 | 0 | 0 | 0 | 2990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PPANEP | Northeast Paths - Prospect Park Alliance | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-0245K | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | NORTHEAST PATHS - PROSPECT PARK ALLIANCE | 2022 | 2000 | 431.64 | 0 | 0 | 0 | 300 | 1436 | 0 | 2167.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PPESIT | Ocean Parkway Sitting Areas Reconstruction BG-121M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-K001 P-1018 P-D017 |  |  | RECONSTRUCT SITTING AREAS INCLUDING WATER SERVICE, BENCHES, SEATING, LANDSCAPING, FENCING, SECURITY LIGHTING, BOLLARDS, FENCING, PAVEMENT. | 2022 | 916 | 319 | 0 | 1080 | 0 | 0 | 0 | 0 | 1399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PWBFTG | PWOB- Fort Greene (B032-117M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-1018 P-0935 P-K011 P-D017 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | MYRTLE AVENUE, DE KALB AVENUE, BETWEEN WASHINGTON PARK AND ST EDWARDS'S STREET BROOKLYN | FORT GREENE | 2022 | 900 | 1254.7 | 0 | 0 | 10045 | 0 | 10217 | 0 | 21516.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PWBPFB | PWOB- PP Flatbush Avenue (B073-117M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PROSPECT PARK - BOROUGH OF BROOKLYN | PWOB- PROSPECT PARK | 2022 | 3200 | 3420.29 | 0 | 0 | 0 | 194 | 0 | 0 | 3614.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2PWPADT | Power Memorial Plgd. Phase 2 Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 P-K011 |  |  | ADULT FITNESS RECON IN POWER PARK IN BROOKLYN | 2022 | 1000 | 0 | 0 | 0 | 2000 | 1000 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2RBDRNG | Dainage connection at Raymond Bush Pk, BK | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-D017 |  | BROOKLYN | DAINAGE WORK AT RAYMOND BUSH PK. BK | 2022 | 180 | 0 | 180 | 0 | 0 | 0 | 0 | 0 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2RHBALL | Red Hook ball fields B126-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 206 | P-0245K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RED HOOK BALL FIELDS | 2022 | 11690 | 13982.97 | 1315 | 0 | 0 | 599 | 0 | 0 | 15896.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SEAGTE | SEAGATE SHORELINE REMEDIATION | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 213 200 | P-D017 P-0379 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF BROOKLYN | REMEDIATION OF SHORELINE AT SEAGATE | 2022 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 2600 | 2600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SNSTCN | Sunset Park Pool Tunnel Structural Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1008 |  | SUNSET PARK, BROOKLYN | SUNSET PARK POOL TUNNEL STRUCTURAL RECONSTRUCTION | 2022 | 392 | 0 | 392 | 0 | 0 | 0 | 0 | 0 | 392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SNSTEL | Sunset Park Pool Tunnel Electrical Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1008 |  | SUNSET PARK, BROOKLYN | SUNSET PARK POOL TUNNEL ELECTRICAL RECONSTRUCTION | 2022 | 251 | 0 | 0 | 251 | 0 | 0 | 0 | 0 | 251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SNSTRW | Commodore Barry Park C.S | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0505 |  |  | COMMODORE BARRY PARK COMFORT STATION | 2022 | 4550 | 260 | 3131 | 316 | 127 | 0 | 0 | 0 | 3834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SPC21A | Marine Park Forest Restoration | LAND ACQUISITION AND TREE PLANTING | 200 | P-0822 |  | BOROUGH OF BROOKLYN | FY 21 TREE PLANTING CONTRACT | 2022 | 1148 | 0 | 0 | 0 | 1148 | 0 | 0 | 0 | 1148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SPT21B | Street Tree Planting - Bkln -Sm. Pur. BG-321M | LAND ACQUISITION AND TREE PLANTING | 200 | P-1018 |  | BOROUGH OF BROOKLYN | STREET TREE | 2022 | 551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 1 | 0 | 0 | 0 | 0 | 501
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFBSH | Synthetic Turf Field Reconstruction at Bushwick Inlet Pk, BK | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0510 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BUSHWICK INLET PK, BROOKLYN | SYNTHETIC TURF FIELD RECONSTRUCTION AT BUSHWICK INLET PK, BK | 2022 | 1058 | 0 | 983 | 0 | 0 | 75 | 0 | 0 | 1058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFHM | Hamilton-Metz Field Synthetic Turf Field Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS |  | P-0510 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HAMILTON-METZ FIELD SYNTHETIC TURF FIELD | 2022 | 2133 | 2091.09 | 0 | 0 | 0 | 488 | 0 | 0 | 2579.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFLEF | Synthetic Turf Field Recon at Quaker Parrot Pk, BK | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | LEIF ERICSON, BK | SYNTHETIC TURF FIELD RECONSTRUCTION AT LEIF ERICSON, BK | 2022 | 1060 | 0 | 941 | 0 | 0 | 119 | 0 | 0 | 1060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2STFMH | Maria Hernandez Park - Synthetic Turf Field (B016-118M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0510 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SYNTHETIC TURF FIELD | 2022 | 4642 | 3092.29 | 1 | 621 | 0 | 0 | 0 | 0 | 3714.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2SUCSGN | Success Garden - Park Renovation | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-K011 |  | BOROUGH OF BROOKLYN | SUCCESS GARDEN PARK RENOVATION INCLUDING THE RECONSTRUCTION OF BROKEN ASPHALT AND OVERGROWN SECTION OF PROPERTY | 2022 | 2009 | 2073.21 | 193 | 0 | 0 | 0 | 0 | 0 | 2266.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE14A | FY14 Street Tree Planting, Brooklyn CB's 1 - 6 & 8 - BG-813M | LAND ACQUISITION AND TREE PLANTING | 200 201 202 203 204 205 206 208 | P-D822 P-K822 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PLANTING OF NEW AND REPLACEMENT STREET TREES AT VARIOUS LOCATIONS IN COMMUNITY BOARDS 1-6 &8 IN THE BOROUGH OF THE BROOKLYN. | 2022 | 2638 | 2438.81 | 0 | 0 | 0 | 0 | 42 | 0 | 2480.81 | 488.8 | 0 | 0 | 0 | 0 | 0 | 0 | 488.8
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE18B | FY18 Street Tree Brooklyn1,5,14,18 | LAND ACQUISITION AND TREE PLANTING | 200 | P-0822 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | FY18 STREET TREE BROOKLYN1,5,14,18 | FY18 STREET TREE BROOKLYN1,5,14,18 | 2022 | 2520 | 3185.63 | 0 | 0 | 0 | 80 | 0 | 0 | 3265.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE18C | FY18 Street Tree Brooklyn6,7,9,12 | LAND ACQUISITION AND TREE PLANTING | 200 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | FY18 STREET TREE BROOKLYN6,7,9,12 | FY18 STREET TREE BROOKLYN6,7,9,12 | 2022 | 2057 | 3130 | 0 | 0 | 0 | 180 | 0 | 0 | 3310 | 231 | 0 | 0 | 0 | 0 | 0 | 0 | 231
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE21A | FY21 Street Tree Brooklyn1,3,4,5,16 BG-1219M | LAND ACQUISITION AND TREE PLANTING | 200 | P-D822 P-0822 P-1018 WM-0006 |  | BOROWIDE | FY21 STREET TREE BROOKLYN13,4,,5,16 | 2022 | 2990 | 75 | 1315 | 0 | 0 | 0 | 0 | 0 | 1390 | 0 | 1675 | 0 | 0 | 0 | 0 | 0 | 1675
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE21B | FY21 Street Tree Brooklyn2,6,7,10 BG-1419M | LAND ACQUISITION AND TREE PLANTING | 200 | P-D017 P-K822 P-0822 WP-0269 |  | BOROWIDE | FY21 STREET TREE BROOKLYN2,6,7,10 | 2022 | 1376 | 25 | 2633 | 0 | 0 | 0 | 0 | 0 | 2658 | 0 | 357 | 0 | 0 | 0 | 0 | 0 | 357
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE21C | FY21 Street Tree Brooklyn11,13,15 BG-1519M | LAND ACQUISITION AND TREE PLANTING | 200 | P-0822 |  | FY21 STREET TREE BROOKLYN11,13,15 | FY21 STREET TREE BROOKLYN11,13,15 | 2022 | 2356 | 75 | 2356 | 0 | 0 | 0 | 0 | 0 | 2431 | 0 | 634 | 0 | 0 | 0 | 0 | 0 | 634
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE21D | FY21 Street Tree Brooklyn12,14 BG-1619M | LAND ACQUISITION AND TREE PLANTING | 200 | P-0822 |  | FY21 STREET TREE BROOKLYN12,14 | FY21 STREET TREE BROOKLYN12,14 | 2022 | 990 | 30 | 2530 | 0 | 0 | 0 | 0 | 0 | 2560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE22A | Brooklyn Street Tree Planting FY22-CB 1&4 BG-522M | LAND ACQUISITION AND TREE PLANTING | 200 | P-1018 P-D822 |  | BOROUGH OF BROOKLYN | BROOKLYN STREET TREE PLANTING | 2022 | 375 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 125 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 375
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE22B | Brooklyn Street Tree Planting FY22-CB 2&3 BG-722M | LAND ACQUISITION AND TREE PLANTING | 200 | P-1018 P-D822 |  | BOROUGH OF MANHATTAN | BROOKLYN STREET TREE PLANTING | 2022 | 250 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 250
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE22D | Brooklyn Street Tree Planting FY22-CB 6,7,10 | LAND ACQUISITION AND TREE PLANTING | 200 | P-1018 HW-0001K P-0822 |  | BOROUGH OF BROOKLYN | BROOKLYN STREET TREE PLANTING | 2022 | 1390 | 0 | 0 | 162 | 1680 | 0 | 0 | 0 | 1842 | 0 | 0 | 1148 | 0 | 0 | 0 | 0 | 1148
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE22E | Brooklyn Street Tree Planting FY22-CB 11,13,15 | LAND ACQUISITION AND TREE PLANTING | 200 | P-1018 SE-0200K SE-0002K P-0822 |  | BOROUGH OF BROOKLYN | BROOKLYN STREET TREE PLANTING | 2022 | 2905 | 0 | 0 | 140 | 2006 | 0 | 0 | 0 | 2146 | 0 | 0 | 759 | 0 | 0 | 0 | 0 | 759
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRE22F | Brooklyn ParkTree Planting FY22 | LAND ACQUISITION AND TREE PLANTING | 200 | P-1018 S-0186 P-0822 P-0245K |  | BOROUGH OF BROOKLYN | BROOKLYN PARK TREE PLANTING | 2022 | 2444 | 0 | 0 | 34 | 2280 | 0 | 0 | 0 | 2314 | 0 | 0 | 130 | 0 | 0 | 0 | 0 | 130
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TREL21 | FY21 Street Trees BK CB's9,17,18 (3Y)BG-1319M | LAND ACQUISITION AND TREE PLANTING | 200 | P-1018 P-K822 P-0822 |  | BROOKLYN | FY21 STREET TREES BK CB'S9,17,18 (3Y) | 2022 | 5950 | 5995 | 0 | 329 | 0 | 800 | 0 | 0 | 7124 | 3500 | 0 | 350 | 0 | 0 | 0 | 0 | 3850
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TREP22 | Brooklyn Street Tree Planting FY22 - CD 38-BG-122M | LAND ACQUISITION AND TREE PLANTING | 200 | P-1018 P-D822 |  | BOROUGH OF BROOKLYN | BROOKLYN STREET TREE PLANTING FY22-CD38 | 2022 | 60 | 0 | 0 | 440 | 0 | 0 | 0 | 0 | 440 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 60
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRS21A | Brooklyn Tree-Damaged Sidewalk CB 7,10-13,15,18 | LAND ACQUISITION AND TREE PLANTING | 200 | P-1018 P-1331 |  | BOROUGH OF BROOKLYN | TREES AND SIDEWALK DAMAGE CONTRACT RENEWAL | 2022 | 2090 | 0 | 1964 | 0 | 0 | 0 | 0 | 0 | 1964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2TRS21B | Brooklyn Tree-Damaged Sidewalk CB 3,5-18 | LAND ACQUISITION AND TREE PLANTING | 200 | P-1018 |  | BOROUGH OF BROOKLYN | BROOKLYN TREE DAMAGED SIDEWALK CB3, 5-18 | 2022 | 2800 | 0 | 0 | 0 | 2800 | 0 | 0 | 0 | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2WPKBGH | NYCHA Kingsborough Houses Open Space Construction | LAND ACQUISITION AND TREE PLANTING | 205 | P-1018 |  | KINGSBOROUGH - BOROUGH OF BROOKLYN | NYCHA KINGSBOROUGH HOUSES OPEN SPACE CONSTRUCTION, BOROUGH OF BROOKLYN | 2022 | 5000 | 419.95 | 0 | 580 | 0 | 4500 | 0 | 0 | 5499.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-2WPS228 | I.S. 228 Playground Reconstruction (BG-39100-117M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 228 AVENUE S, BROOKLYN, NY 11223 | I.S. 228 PLAYGROUND RECONSTRUCTION | 2022 | 1508 | 1063.66 | -293 | 0 | 0 | 840 | 0 | 0 | 1610.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-6CADMAR | Recon Marlboro & Cadman Plaza CS | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0505 P-K011 P-1008 |  | BROOKLYN | RECON MARLBORO & CADMAN PLAZA CS | 2022 | 837 | 353.99 | 0 | 524 | 1560 | 0 | 0 | 0 | 2437.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | P-6WPEBCS | Recon War Mem bldg & Elenor Roosevelt CS | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-0505 |  | BROOKLYN | RECON WAR MEM BLDG, PIERREPONT & ELENOR ROOSEVELT CS | 2022 | 1782 | 1825 | 0 | 363 | 0 | 0 | 0 | 0 | 2188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-03 | SANDY-Emergency Clean up & Safe Up - Shore Pkway B166-313M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BOROUGH OF BROOKLYN | HURRICANE SANDY EMERGENCY WORK AT SHORE PARKWAY | 2022 | 600 | 278.14 | 0 | 1 | 0 | 0 | 0 | 0 | 279.14 | 1920.98 | 0 | 99 | 0 | 0 | 0 | 30 | 2049.98
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-09 | SANDY-Brooklyn Playground requirements(Type 1) BG-311M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 200 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PLAYGROUNDS IN THE BOROUGH OF BROOKLYN | SANDY RELATED WORK | 2022 | 1455 | 131.69 | 40 | 0 | 0 | 0 | 0 | 0 | 171.69 | 922.07 | 0 | 0 | 0 | 0 | 0 | 1 | 923.07
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-12 | SANDY - Brooklyn Plgd requirements (Type 2) BG-1113M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BOROUGH OF BROOKLYN | STORM SANDY - PLAYGROUND R/C | 2022 | 3168 | 556.26 | 104 | 0 | 0 | 0 | 0 | 26 | 686.26 | 1271.42 | 1 | 0 | 0 | 0 | 0 | 1161 | 2433.42
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-13 | SANDY - PNP Prospect Park Alliance | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 206 207 208 209 214 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BROOKLYN | PROSPECT PARK | 2022 | 548 | 37 | 0 | 0 | 0 | 0 | 0 | 46 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 410 | 410
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-14 | SANDY- Abe Stark boilers and chillers (B169-111M) | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 213 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | LOCATED ADJACENT TO THE CONEY ISLAND BOARDWALK AT WEST 19TH STREET, IN THE BOROUGH OF BROOKLYN | SANDY RELATED WORK AT ABE STARK SKATING RINK | 2022 | 1852 | 101.48 | 0 | 12 | 0 | 0 | 42 | 0 | 155.48 | 1001 | 0 | 0 | 0 | 0 | 0 | 383 | 1384
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-16 | SANDY-Sheepshead Bay Piers Type 3 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SHEEPSHEAD BAY PIERS AT EMMONS AVE, BROOKLYN | R/C OF TRANSFORMERS AND ELECTRICAL COMPONENTS AT SHEEPSHEAD BAY PIERS | 2022 | 653 | 352.94 | 0 | 694 | 0 | 0 | 0 | 0 | 1046.94 | 548.48 | 0 | 6247 | 0 | 0 | 0 | 0 | 6795.48
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-21 | SANDY - Tree removals -Brooklyn CB 7-18 BG-614M | LAND ACQUISITION AND TREE PLANTING | 200 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF BROOKLYN | TREE REMOVALS IN BROOKLYN CB 7-18 RELATED TO SANDY | 2022 | 2100 | 472.37 | 0 | 41 | 0 | 0 | 0 | 0 | 513.37 | 1521.51 | 0 | 0 | 0 | 0 | 0 | 368 | 1889.51
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-25 | Abe Stark - Non-Boiler Repair | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 200 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF BROOKLYN | SANDY - ABE STARK | 2022 | 2603 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 2343 | 2343
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-28 | Red Hook Recreation Center RC B126-121M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-1018 |  |  | RED HOOK RECREATION CENTER | 2022 | 3109 | 25 | 81 | 0 | 872 | 0 | 0 | 0 | 978 | 0 | 725 | 0 | 7855 | 0 | 0 | 0 | 8580
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-30 | Hudson River Yacht Club B406-122M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-1018 |  |  | HUDSON RIVER YACHT CLUB | 2022 | 440 | 0 | 47 | 0 | 173 | 0 | 0 | 0 | 220 | 0 | 407 | 0 | 1566 | 0 | 0 | 0 | 1973
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-31 | Diamond Point Yacht Club B406-122M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-1018 |  |  | DIAMOND PONT YACHT CLUB | 2022 | 483 | 0 | 24 | 0 | 142 | 0 | 0 | 0 | 166 | 0 | 211 | 0 | 1274 | 0 | 0 | 0 | 1485
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-32 | Paerdegat Squadron Yacht Club B406-122M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PAERDEGAT SQUADRON YACHT CLUB | 2022 | 294 | 0 | 24 | 0 | 96 | 0 | 0 | 0 | 120 | 0 | 190 | 822 | 74 | 0 | 0 | 0 | 1086
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-33 | Sandy - Midget Squadron Yacht Club B406-122M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | MIDGET SQUADRON YACHT CLUB | 2022 | 2029 | 0 | 89 | 0 | 658 | 0 | 0 | 97 | 844 | 0 | 798 | 0 | 1094 | 0 | 0 | 1200 | 3092
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-34 | Paerdegat Athletic Center HVAC recon. B406-114M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PAERDEGAT ATHLETIC CENTER HVAC RECON. B406-114M | 2022 | 2696 | 778.96 | 9 | 0 | 0 | 0 | 0 | 0 | 787.96 | 2343.43 | 0 | 0 | 0 | 0 | 0 | 83 | 2426.43
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-35 | Paerdegat Athletic Center - Remaining Scope B406-521M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | PAERDEGAT ATHLETIC CENTER - REMAINING SCOPE | 2022 | 12797 | 0 | 162 | 0 | 17 | 941 | 113 | 0 | 1233 | 0 | 1452 | 0 | 8638 | 0 | 1008 | 0 | 11098
20220309 | BROOKLYN | 846 | DEPT OF PARKS AND RECREATION | SANDY2-37 | SANDY-John Malone Community Center | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-1018 |  | BERGEN AVENUE, BETWEEN AVENUE W AND AVENUE X. | JOHN MALONE COMMUNITY CENTER IN BOROUGH OF BROOKLYN | 2022 | 1978 | 40 | 0 | 0 | 198 | 0 | 0 | 0 | 238 | 0 | 0 | 0 | 1780 | 0 | 0 | 0 | 1780
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-K | Borough Based Jails New Brooklyn Detention Facility | New Jail Facilities |  | C-0114 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CONSTRUCTION OF NEW BROOKLYN FACILITY | 2022 | 2021426 | 0 | 51187 | 366957 | 453970 | 487705 | 378350 | 153257 | 1891426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-768B | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE II (HWK700B) | TRUNK AND DISTRIBUTION MAIN EXTENSION | 200 | WM-0001 WM-0006 SE-0002K | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE II | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE II | 2022 | 7244 | 0 | 0 | 0 | 58964 | 0 | 0 | 0 | 58964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-776 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 205 216 | SE-0002K WM-0001 WM-0006 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, IN JAMAICA AVE B/T HERLIMER ST AND VERMONT ST AND ATLANTIC AVE B/T VAN SINDEREN AV AND PENNSYLVANIA | 2022 | 18872 | 88525.55 | 138 | 501 | 0 | 0 | 0 | 0 | 89164.55 | 547.92 | 0 | 0 | 0 | 0 | 0 | 0 | 547.92
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-778A | Trunk & Dist WM Rep in Atlantic Ave b/t Carlton & Portland | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 202 | WM-0006 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TRUNK & DIST. W/M REPL IN ATALNTIC AV B/T CARLTON & S. PORTLAND AVENUES | 2022 | 3700 | 13157.33 | 0 | 919 | 0 | 0 | 0 | 0 | 14076.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-782A | Reconstuction of water main & combined sewer,Tillary st. PH2 | AUGMENTATION OF WATER SUPPLY SYSTEMS | 202 | WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RECONSTRUCTION OF WATER MAIN & COMBINED SEWER,TILLARY ST. PHASE 2 | 2022 | 14039 | 13994.21 | 47 | 0 | 0 | 0 | 0 | 0 | 14041.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-784 | RECON OF WM I& STORM SWR IN BERGEN AVE AREA | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 218 | SE-0200K WM-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECON OF WM IN BERGEN AVE AREA | 2022 | 11730 | 37333.23 | 1749 | 0 | 0 | 0 | 2886 | 0 | 41968.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-794 | DUMBO/Vinegar Hill Area Reconstruction & Plaza. HWKKP005 | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 202 206 | SE-0002K SE-0004 EP-0007 WM-0001 WM-0006 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | TRUNK/DIST WM REPLAC. & INSTALLATION, COMBINED SWR REPLACE, HI LEVEL STORM SWR EXTENSION, BKLYN | 2022 | 9413 | 48452.64 | 5575 | 513 | 0 | 0 | 0 | 0 | 54540.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-796 | Trunk & Distribution WM replcmnt in Empire Blvd, HWK779W | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 209 217 | SE-0002K WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TRUNK & DISTRIBUTION WM REPLCMNT IN EMPIRE BLVD AT THE INTERSECTION OF EAST NEW YORK AVENUE, UTICA AVENUE, ETC., BOROUGH OF BROOKLYN | 2022 | 6540 | 11906.71 | 1243 | 0 | 0 | 0 | 1052 | 0 | 14201.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED798 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 206 208 | SE-0002K WM-0006 HW-0001K WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | 72" REPLACEMENT IN FLATBUSH AVENUE BETWEEN STERLING PL & 8TH AVE. (WITH COMBINED AND SANITARY REPLACEMENTS) | 2022 | 25804 | 50365.38 | 3416 | 0 | 0 | 0 | 0 | 0 | 53781.38 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 31
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-802 | WM Replacement Hamilton Ave Gowanus Connector, BK HWK1048D | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 206 207 | WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WM REPLACEMENT HAMILTON AVE GOWARNUS CONNECTOR B/T SMITH & 19 ST, BKLYN | 2022 | 1920 | 15477.67 | 522 | 0 | 0 | 0 | 2088 | 0 | 18087.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-803 | WM Repl in Schenck Av b/t Flatlands & Jamaica Av Bk, HWK797W | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 205 | SE-0002K WP-0169 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | WM REPLAC. SCHENCK AVE B/T FLATLANDS & JAMAICA AVES, BKLYN | 2022 | 4600 | 0 | 2925 | 0 | 0 | 0 | 0 | 0 | 2925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-805 | New Storm & San Swrs & WM-Gateway Estates, Phase E (HD-161E) | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 205 | SE-0200K SE-0002K WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW STORM & SANI SWRS & WM IN GATEWAY ESTATES, PHASE E, BKLY | 2022 | 5776 | 13806.56 | 1005 | 0 | 0 | 1020 | 0 | 0 | 15831.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-806 | Water Main work in Brooklyn Waterfront Greenway, HWK1048E | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 201 | WM-0001 SE-0002K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | WATER MAIN WORK IN BROOKLYN WATERFRONT GREENWAY (COMMERCIAL STREET, ASH STREET AND BOX STREET)-BED-806 | 2022 | 1594 | 0 | 0 | 601 | 0 | 5885 | 0 | 0 | 6486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-807 | WM work in Brooklyn Waterfront Greenway. SAND1048 | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 201 | WM-0001 SE-0002K EP-0007 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | WM WORK IN BROOKLYN WATERFRONT GREENWAY. (2ND AVENUE BETWEEN 37TH STREET & 39TH STREET ETC.) | 2022 | 569 | 0 | 0 | 3255 | 0 | 0 | 0 | 0 | 3255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-809 | Replacement of Water Mains in Avenue S | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 215 | WM-0944 WM-0001 |  |  | REPLACEMENT OF WATER MAINS IN AVENUE S BET. CONEY ISLAND AVENUE AND EAST 18TH STREET | 2022 | 14445 | 26234.12 | 1607 | 0 | 0 | 0 | 0 | 0 | 27841.12 | 4333.24 | 4 | 0 | 0 | 0 | 0 | 0 | 4337.24
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-810 | Water Main work in Brooklyn Waterfront Gateway, HWK1048C | AUGMENTATION OF WATER SUPPLY SYSTEMS | 201 | SE-0002K WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | WATER MAIN WORK IN BROOKLYN WATERFRONT GATEWAY (KENT AVENUE BET. CLYMER ST & TAYLOR ST. ETC) | 2022 | 244 | 12686.29 | 1551 | 500 | 0 | 0 | 0 | 0 | 14737.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-819 | WM replacement in Oriental Blvd | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 215 | EP-0007 WM-0001 F-0001 WM-0944 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | WM REPLACEMENT IN ORIENTAL BLVD BETWEEN CORBIN PLACE AND PEMBROKE ST,ETC MANHATTAN BEACH AREA, BROOKLYN | 2022 | 17750 | 5876.09 | 38339 | 389 | 0 | 0 | 0 | 0 | 44604.09 | 0 | 4634 | 0 | 0 | 0 | 0 | 0 | 4634
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED829 | Dts. WM Rplmt in 4th Ave from Atlantic ave to 64th ST, BKLYN | AUGMENTATION OF WATER SUPPLY SYSTEMS | 206 | SE-0002K WM-0001 |  |  | DISTRIBUTION WATER MAIN REPLACEMENT IN 4TH AVE FROM ATLANTIC AVE TO 64TH ST, BKLYN. DDC TO TV EXISTING SEWERS WITHIN THE PROJECT LIMITS. THIS PROJECT WILL BE COMPLETED IN CONJUCTION WITH DOT PROJECT HWK1669B. | 2022 | 71769 | 0 | 0 | 0 | 7870 | 61380 | 0 | 0 | 69250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-830 | Rplment WM Park Ave btw Classon Ave & Ryerson (HWD007K03) | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 202 | SE-0002K WM-0001 |  |  | (HW007K03) REPLACEMENT OF WATER MAIN ALONG PARK AVENUE BETWEEN CLASSON AVENUE AND RYERSON STREET, OTHER LOCATIONS AS LISTED ON PAGE 3 "DESIGN SCOPE" AS SHOWN ON ATTACHED SKETCH IN BOROUGH OF BROOKLYN. | 2022 | 2308 | 0 | 0 | 0 | 2308 | 0 | 0 | 0 | 2308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BED-833 | Rel.& Inst.WMs Flatland Ave bet Ralph Ave & E 76 St HWK2048 | AUGMENTATION OF WATER SUPPLY SYSTEMS | 218 | WM-0001 |  |  | RELOCATION & INSTALLATION OF NEW WATER MAINS ON FLATLAND AVENUE BETWEEN RALPH AVE AND EAST 76TH STREET IN BROOKLYN. THIS PROJECT IS IN CONJUNCTION WITH HWK2048. | 2022 | 389 | 0 | 0 | 1363 | 0 | 0 | 0 | 0 | 1363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | BEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 200 | WM-0001 SE-0002K SE-0200K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ACCELERATED DISTRIBUTION WATER MAIN REPLCMNT & SEWER REHAB/REPLCMNT, BROOKLYN | 2022 | 17175 | 27152.18 | 3291 | 1709 | 409 | 0 | 0 | 0 | 32561.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CJCREN | FACIILITY RENOVATIONS AT CROSSROADS JC | CHILD WELFARE FACILITIES | 200 | CS-0005 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | THIS PROJECT ENCOMPASSES THE RENOVATION OF THE SECURE JUVENILE DETENTION CENTER LOCATED AT 17 BRISTOL STREET IN BROOKLYN (CROSSROADS JUVENILE CENTER). THE PROJECT INCLUDES BUT IT IS NOT LIMITED TO: REINFORCEMENT OF BEDROOM WALLS; BATHROOM RECONFIGURATION; FUNCTIONAL CHANGES OF EXISTING DORM SPACE TO PSYCHIATRIC MEDICAL SUITE; UPGRADE OF ALL SYSTEMS: LIGHTING, ROOFING, PLUMBING, MECH., ELECTRICAL, SECURITY, FIRE ALARM AND FIRE SUPPRESSION SYSTEMS; UPGRADE AND UPDATE OF: EXISTING CLASSROOMS, COMMERCIAL KITCHEN AND KITCHEN EQUIPMENT; RENOVATION OF ENTIRE EXTERIOR RECREATIONAL AREA TO REFLECT SHADE AREAS AND UPGRADE OF THE LANDSCAPING. ACS HAS BEEN TAKING TEMPORARY MEASURES TO MAINTAIN THE FACILITY OPERATIONS WITH MATERIALS AND FIXTURES OF THE ORIGINAL CONSTRUCTION WHICH HAVE NOT EXHIBITED THE RESILIENCE AND VANDAL RESISTANCE EXPEC | 2022 | 15205 | 64922.63 | 540 | 0 | 0 | 0 | 0 | 0 | 65462.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272DW2 | 45 MONROE PL- DRIVEWAY/PARKING LOT RECONSTRUCTION | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 201 | CO-0272 |  |  | IA/SQ | 2022 | 1436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 409 | 912 | 0 | 0 | 0 | 0 | 1321
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELC2 | 45 MONROE PL - ELECTRICAL / FA UPGRADE | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 202 | CO-0272 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | BROOKLYN APPELLATE COURT WILL HAVE ITS ELECTRICAL SYSTEM UPGRADED. | 2022 | 7126 | 1340.48 | 0 | 0 | 0 | 0 | 0 | 0 | 1340.48 | 7046.25 | 1834 | 0 | 0 | 0 | 0 | 0 | 8880.25
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO272ELV2 | 45 MONROE PL. - ELEVATOR | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 202 | CO-0272 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 45 MONROE PL. - ELEVATOR | 2022 | 1056 | 410.69 | 0 | 0 | 0 | 0 | 0 | 0 | 410.69 | 2387.6 | 140 | 0 | 0 | 0 | 324 | 0 | 2851.6
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278EXT2 | 360 ADAMS ST. - EXTERIOR | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 201 | CO-0278 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | EXTERIOR RESTORATION | 2022 | 3269 | 731.24 | 1100 | 19276 | 319 | 0 | 0 | 2286 | 23712.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO278FA3 | 360 ADAMS STREET - FIRE ALARM SYSTEM & SPRINKLER UPGRADE | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 202 | CO-0278 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | COMPREHENSIVE FIRE ALARM SYSTEM & SPRINKLER UPGRADE | 2022 | 40820 | 9354.79 | 638 | 1439 | 53717 | 0 | 6316 | 18950 | 90414.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO281TOIL | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 202 | CO-0281 C-0075 CO-0264 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 2022 | 4000 | 903.8 | 10806 | 1333 | 0 | 0 | 0 | 0 | 13042.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH04 | SAN & STRM SWR, WM1, IN CONEY ISL AREA, PH 4 | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 213 | SE-0200K WM-0006 WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | STORM & SANITARY SEWER, DISTRIBUTION WATER MAIN IN CONEY ISLAND AREA,PHASE 4 | STORM & SANITARY SEWER, DISTRIBUTION PWATER MAIN IN CONEY ISLAND AREA, PHASE 4 | 2022 | 27679 | 370 | 0 | 0 | 27679 | 0 | 0 | 0 | 28049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH2B | SAN & STRM SWR, WM1, WM6 IN CONEY ISL AREA, PH 2B | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 213 | WM-0006 SE-0002K SE-0200K WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | STORM & SANITARY SEWER, TRUNK AND DISTRIBUTION WATER MAIN IN CONEY ISLAND AREA, PHASE 2B | STORM & SANITARY SEWER, TRUNK AND DISTRIBUTION WATER MAIN IN CONEY ISLAND AREA, PHASE 2B | 2022 | 18282 | 57794.08 | 1919 | 0 | 0 | 0 | 0 | 0 | 59713.08 | 166.5 | 0 | 0 | 0 | 0 | 0 | 0 | 166.5
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CONISPH3A | Storm and Sanitary Sewer, Trunk and Distribution Water Main | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 213 | SE-0200K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STORM AND SANITARY SEWER, TRUNK AND DISTRIBUTION WATER MAIN IN CONEY ISLAND AREA, PHASE 3A | 2022 | 38399 | 60087.56 | 506 | 0 | 0 | 0 | 1802 | 0 | 62395.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | CV19COEBU | Centers of Excellence: Bushiwick | NEW FACILITIES |  | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BUILDING IS A NEWLY LEASED SPACE LOCATED AT 815 BROADWAY, BROOKLYN, NY 11206. | THE WORK TO BE DONE WILL INCLUDE GENERAL CONSTRUCTION, NEW PLUMBING FIXTURES ON ALL FLOORS, NEW ENTRANCE DOORS AND STOREFRONT, NEW HVAC DUCTWORK, NEW ACOUSTIC CEILINGS, NEW SECURITY AND FIRE ALARM SYSTEMS. | 2022 | 66858 | 39406.09 | 0 | 0 | 0 | 0 | 0 | 0 | 39406.09 | 28275.39 | 0 | 55 | 0 | 0 | 0 | 0 | 28330.39
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E12-0043 | NYPD 84th Precinct - EE Upgrade | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NYPD 84TH PRECINCT & EC 207 ENERGY UPGRADES | 2022 | 694 | 3757.56 | 118 | 0 | 0 | 0 | 0 | 0 | 3875.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0006 | DSNY - BROOKLYN NORTH 1 DISTRICT &4 DISTRICT GARAGE | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BROOKLYN NORTH 1 DISTRICT &4 DISTRICT GARAGE | 2022 | 13191 | 860.21 | 5700 | 0 | 2498 | 0 | 0 | 0 | 9058.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKN22 | Reconstruction of Existing Sewers, North Brooklyn | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 200 | EP-0007 SE-0002K |  |  | THIS IS A ONE YEAR CONTRACT. THE TARGETED CONTRACT START DATE IS 11/25/2021. | 2022 | 8370 | 224 | 5955 | 2894 | 0 | 0 | 0 | 0 | 9073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKN23 | Reconstruction of Existing Sewers, North Brooklyn | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 200 | EP-0007 SE-0002K |  |  | RECONSTRUCTION OF EXISTING SEWERS, NORTH BROOKLYN. THIS IS A 1 YEAR CONTRACT. THE TARGETED START DATE FOR THIS CONTRACT IS AS SOON AS THE PREVIOUS CONTRACT, EC-SEKN22, EXPIRES. | 2022 | 8000 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKS22 | Reconstruction of Existing Sewers, South Brooklyn | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 200 | EP-0007 SE-0002K |  |  | RECONSTRUCTION OF EXISTING SEWERS, SOUTH BROOKLYN | 2022 | 8800 | 305 | 7723 | 128 | 0 | 0 | 0 | 0 | 8156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEKS23 | Reconstruction of Existing Sewers, South Brooklyn | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 200 | EP-0007 SE-0002K |  |  | RECONSTRUCTION OF EXISTING SEWERS, SOUTH BROOKLYN. THIS IS A 1 YEAR CONTRACT. THE TARGETED START DATE FOR THIS CONTRACT IS AS SOON AS THE PREVIOUS CONTRACT, EC-SEKS22, EXPIRES. | 2022 | 8000 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0013 | DCLA -New York Aquarium Campus: Aquatic Animal Health Center | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW YORK BOTANICAL GARDEN CAMPUS: TRANSFORMER BUILDING - LIGHTING UPGRADE | 2022 | 300 | 0 | 0 | 61 | 405 | 0 | 0 | 0 | 466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0014 | DCLA - New York Aquarium Campus: Aqua Theater Pump Room | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW YORK BOTANICAL GARDEN CAMPUS: LEON LEVY VISITOR CENTER: RESTROOM (FOUNTAIN) - LIGHTING AND HVAC UPGRADES | 2022 | 300 | 0 | 0 | 57 | 261 | 0 | 0 | 0 | 318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | EP6-KENT2 | 356 FLUSING, BUILDING REPAIR/UPGRADE | FACILITY PURCHASES AND RECONSTRUCTION | 201 202 | EP-0006 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | BASE BUILDING REPAIRS REQUIRED TO BE DONE AS PART OF MAINTENANCE OF FACILITY | 2022 | 954 | 36010.01 | 538 | 0 | 0 | 0 | 0 | 0 | 36548.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | F175RES2 | NEW FIREHOUSE - RESCUE 2 | NEW FACILITIES AND RENOVATIONS | 200 | F-0175 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW FIREHOUSE - RESCUE 2 | 2022 | 22525 | 35538.39 | 199 | 0 | 0 | 0 | 0 | 0 | 35737.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GCNC77-PA | GI - PERMEABLE ASPHALT PAVEMENT PILOT & GI IN CSO AREA NC-77 | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | PERMEABLE ASPHALT PAVEMENT PILOT AND GREEN INFRASTRUCTURE N CSO TRIBUTARY AREA NC-077 | 2022 | 5172 | 5390.37 | 0 | 789 | 0 | 0 | 0 | 0 | 6179.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKCI05-1A | GI- CONS OF ROW GREEN INFRASTRUCTURE IN CI-005 PHASE 1A | GREEN INFRASTRUCTURE PROGRAM | 200 | EP-0007 WP-0169 |  |  | GI- CONSTRUCT RIGHT-OF-WAY GREEN INFRASTRUCTURE PRACTICES SUCH AS RAIN GARDENS, INFILTRATION BASINS AND STORMWATER GREEN STREETS IN CONEY ISLAND CREEK WATERSHED CI-005. | 2022 | 31650 | 150 | 34967 | 0 | 0 | 0 | 0 | 0 | 35117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-01 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 1 | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO TIBUTARY AREA PHASE 1 | 2022 | 18817 | 8386.97 | 0 | 2000 | 26146 | 0 | 0 | 0 | 36532.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-02 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 2 | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO TIBUTARY AREA PHASE 2 | 2022 | 17234 | 7784 | 3704 | 28910 | 0 | 0 | 0 | 0 | 40398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-03 | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 3 | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO TIBUTARY AREA PHASE 3 | 2022 | 17982 | 8241.88 | 0 | 2000 | 29264 | 0 | 0 | 0 | 39505.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-04 | GI - DESIGN BUILD GREEN INFRA, OH-015 GRAVESEND BAY CSO PH4 | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 |  |  | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO TIBUTARY AREA PHASE 4 | 2022 | 23046 | 4395.36 | 3023 | 300 | 38000 | 0 | 0 | 0 | 45718.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GKOH15-DB | GI-DSGN BUILD ROW GI PH 4 OH-15 GRAVESEND BAY CSO TRIB AREA | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 |  |  | DESIGN BUILD OF RIGHT-OF-WAY GI POROUS CONCRETE; STAGES 1, 2 & 3 OF PHASE 4 OH-015 GRAVESEND BAY CSO TRIBUTARY AREA | 2022 | 18620 | 0 | 0 | 27930 | 0 | 0 | 0 | 0 | 27930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | GNCB14-2A | GI-CONSTRUCTION OF GI NIN NCB-014, PHASE II | GREEN INFRASTRUCTURE PROGRAM | 200 | WP-0169 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | GI-CONSTRUCTION OF GREEN INFRASTRUCTURE IN NCB-014, PHASE II | 2022 | 5750 | 24744.47 | 401 | 0 | 0 | 0 | 0 | 0 | 25145.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM14GOCC | GOWANUS COMMUNITY CENTER RENOVATIONS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 206 | HA-D001 HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COMMUNITY CENTER RENOVATIONS | 2022 | 150 | 545.31 | 85 | 3490 | 0 | 0 | 0 | 0 | 4120.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17GHSE | MARLBOROUGH HOUSES BSCAH GREENHOUSE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 213 | HA-K001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MARLBOROUGH HOUSES BSCAH GREENHOUSE | 2022 | 2000 | 932 | 16161 | 0 | 0 | 0 | 0 | 0 | 17093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM17MRCC | MARCY HOUSES - RENOVATE 492 MARCY AVE INTO A COMM CENTER | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 203 | HA-D001 HA-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RENOVATE VACANT SPACE AT 492 MARCY AVENUE TO CREATE A COMMUNITY CENTER | 2022 | 5335 | 13015.64 | 595 | 894 | 0 | 0 | 0 | 0 | 14504.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM20BVBG | VAN DYKE BOXING GYM | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 216 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BOXING GYM AT BROWNSVILLE | 2022 | 385 | 1216.12 | 198 | 0 | 8824 | 0 | 0 | 0 | 10238.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM20BVCC | BROWNSVILLE COMMUNITY CENTER | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 216 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BRONWSVILLE COMMUNITY CENTER RENOVATION | 2022 | 5000 | 1258.67 | 203 | 0 | 8781 | 0 | 0 | 0 | 10242.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HD-161E | GATEWAY ESTATE - PHASE E (BED-805) | OTHER HOUSING SUPPORT INVESTMENT | 205 | HD-0161 HW-0200 TF-0002 TF-0502 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | GATEWAY ESTATE - PHASE E | GATEWAY ESTATE - PHASE E | 2022 | 12422 | 18657.77 | 25045 | 1402 | 0 | 0 | 0 | 0 | 45104.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112AAFS | ATLANTIC ARMORY FIRE SAFETY | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ATLANTIC ARMORY FIRE SAFETY | 2022 | 4975 | 526.69 | 0 | 414 | 4741 | 0 | 0 | 0 | 5681.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BVFA | BROWNSVILLE WOMEN FIRE SAFETY | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BROWNSVILLE WOMEN FIRE SAFETY | 2022 | 598 | 249.71 | 0 | 1393 | 0 | 0 | 0 | 0 | 1642.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FBFS | FANNIE BARNES FIRE SAFETY | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FANNIE BARNES FIRE SAFETY | 2022 | 1400 | 299.26 | 0 | 1400 | 3090 | 0 | 0 | 0 | 4789.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HWFS | HELP WOMEN'S CENTER FIRE SAFETY | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HELP WOMEN'S CENTER FIRE SAFETY | 2022 | 1313 | 249.54 | 33 | 0 | 1570 | 0 | 0 | 0 | 1852.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112LXEP | 85 LEXINGTON AVE BOILER RECONSTRUCTION | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | BOILER RECONS | 2022 | 2040 | 0 | 0 | 170 | 0 | 1870 | 0 | 0 | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJBO | PAMOJA - BOILER | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PAMOJA - BOILER | 2022 | 2934 | 1117.5 | 0 | 2000 | 7940 | 0 | 0 | 0 | 11057.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJFC | PAMOJA HOUSE - FACADE REHABILITATION/RESTORATION | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PAMOJA HOUSE - FACADE REHABILITATION/RESTORATION | 2022 | 1693 | 407.77 | 500 | 0 | 2238 | 1500 | 2355 | 0 | 7000.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJPL | PAMOJA HOUSE - PLUMBING UPGRADE | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PAMOJA HOUSE - PLUMBING UPGRADE | 2022 | 2600 | 392.04 | 373 | 21 | 2400 | 0 | 0 | 0 | 3186.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112PJRC | PAMOJA HOUSE FIRE SAFETY | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FIRE SAFETY SYSTEM AND FIRE DOORS | 2022 | 4035 | 832.61 | 0 | 50 | 0 | 5924 | 0 | 0 | 6806.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115BMEP | BUSHWICK FAMILY BOILER RECONSTRUCTION | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 |  |  | BOILER RECONSTRUCTION | 2022 | 2160 | 0 | 0 | 180 | 1000 | 2960 | 0 | 0 | 4140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115BWKF | BUSHWICK - FIRE ALARM SYSTEM UPGRADE | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 |  |  | BUSHWICK - FIRE ALARM SYSTEM UPGRADE | 2022 | 769 | 1426.29 | 152 | 0 | 0 | 0 | 0 | 0 | 1578.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115DSFA | DEAN STREET FIRE SAFETY | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DEAN STREET FIRE SAFETY | 2022 | 860 | 360.39 | 0 | 0 | 2580 | 0 | 0 | 0 | 2940.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115LFAU | LINDEN FIRE ALARM UPGRADE | SHELTERS FOR HOMELESS FAMILIES |  | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FIRE ALARM UPGRADE | 2022 | 1115 | 683.91 | 0 | 0 | 581 | 0 | 0 | 0 | 1264.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SFFA | Stockholm at 99-103 Stockholm St, 11221 - Fire Alarm Upgrade | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 |  |  | STOCKHOLM AT 99-103 STOCKHOLM ST, 11221 - FIRE ALARM UPGRADE | 2022 | 335 | 979.29 | 185 | 0 | 0 | 0 | 0 | 0 | 1164.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HIFHPD | Housing Infrastructure Fund for HPD Projects, HD-161D | OTHER HOUSING SUPPORT INVESTMENT | 205 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | HPD | INFRASTRUCTURE COSTS RELATED TO HPD PROJECTS | 2022 | 3482 | 2275.21 | 232 | 975 | 0 | 0 | 0 | 0 | 3482.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BRKLN | Brooklyn Animal Care Center Upgrade | ANIMAL CARE |  | HL-0082 PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BROOKLYN ANIMAL SHELTER HVAC UPGRADE | 2022 | 3500 | 10215.6 | 37618 | 0 | 0 | 0 | 0 | 0 | 47833.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BUSHX | BUSHWICK HEALTH CENTER - EXTERIOR RENOVATION | CLINIC RENOVATION AND REHABILITATION |  | HL-0082 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | EXTERIOR RENOVATION AND OTHER REHAB PROJECTS AT THE BUSHWICK HEALTH CENTER | EXTERIOR RENOVATION AND OTHER REHAB PROJECTS AT THE BUSHWICK HEALTH CENTER | 2022 | 1736 | 2853.78 | 15712 | 0 | 0 | 0 | 0 | 0 | 18565.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HR25BRCS | Brownsville Community Center | SOCIAL SERVICES BUILDINGS |  | HR-0025 |  |  | BROWNSVILLE COMMUNITY CENTER | 2022 | 22167 | 0 | 737 | 27578 | 84213 | 16211 | 0 | 0 | 128739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD005K01 | FULTON ST IMPROVEMENTS AT GREEN AV, HANSEN PL & GATES AV | PRIMARY STREET RECONSTRUCTION | 202 | HW-D101 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | FULTON ST IMPROVEMENTS AT GREEN AV, HANSEN PL & GATES AV INTERSECTIONS | FULTON ST IMPROVEMENTS AT GREEN AV, HANSEN PL & GATES AV INTERSECTIONS | 2022 | 400 | 4224.19 | 0 | 0 | 0 | 0 | 0 | 121 | 4345.19 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 15
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD007K03 | Park Avenue Ped Safety Improvement at the Crossover,BED-830 | PRIMARY STREET RECONSTRUCTION | 202 203 204 | HW-K005 HW-D101 HW-0001K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | MYRTLE AVE WORK | 2022 | 300 | 1062.35 | 0 | 0 | 6242 | 0 | 0 | 0 | 7304.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10105A | Ped Safety Upgrades on Atlantic Ave - Phase 2 (BED-785B) | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PEDESTIAN SAFETY UPGRADES ON ATLANTIC AVE - PHASE 2 | PEDESTIAN SAFETY UPGRADES ON ATLANTIC AVE - PHASE 2 | 2022 | 31830 | 29140.81 | 2749 | 5335 | 0 | 0 | 0 | 0 | 37224.81 | 106.96 | 0 | 0 | 0 | 0 | 0 | 0 | 106.96
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK002377 | East 72nd Street Reconstruction Brooklyn, SEK002377 | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EAST 72ND STREET RECONSTRUCTION BROOKLYN | 2022 | 5670 | 0 | 0 | 5670 | 0 | 0 | 0 | 0 | 5670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100BUS | Utica Ave Bus Priority | TRAFFIC WORK IN CONJUNCTION WITH HIGHWAY RECONSTRUCTION | 200 208 209 217 218 | HW-0001K TF-0502 HW-D101 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | UTICA AVE BROOKLYN | UTICA AVE BUS PRIORITY | 2022 | 6400 | 10704.52 | 167 | 300 | 0 | 0 | 0 | 0 | 11171.52 | 13966.68 | 0 | 0 | 0 | 0 | 0 | 0 | 13966.68
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK100SBC | South Brooklyn Crosstown SBS | PRIMARY STREET RECONSTRUCTION | 200 | HW-D101 HW-1684 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SOUTH BROOKLYN CROSSTOWN SBS | SOUTH BROOKLYN CROSSTOWN SBS | 2022 | 7750 | 4242.15 | 0 | 38743 | 0 | 0 | 0 | 0 | 42985.15 | 0 | 0 | 40628 | 0 | 0 | 0 | 0 | 40628
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048B | FLUSHING AVE - BROOKLYN GREENWAY | PRIMARY STREET RECONSTRUCTION | 202 | HW-0001K HW-0200 TF-0002 TF-0502 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | NAVY YARD - BROOKLYN GREENWAY | NAVY YARD - BROOKLYN GREENWAY | 2022 | 6664 | 11435.77 | 1800 | 0 | 0 | 0 | 0 | 0 | 13235.77 | 4460.34 | 0 | 0 | 0 | 0 | 0 | 0 | 4460.34
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048C | KENT AVE, BED-810 | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K TF-0002 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | KENT AVE | KENT AVE | 2022 | 32633 | 10326.13 | 1304 | 0 | 0 | 0 | 0 | 0 | 11630.13 | 2234.35 | 0 | 0 | 0 | 0 | 0 | 0 | 2234.35
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048D | BK Waterfront Greenway:Sunset Pk Gowanus Connect BED-802 | PRIMARY STREET RECONSTRUCTION | 207 | HW-0001K WM-0001 HW-K005 HW-0200 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | IMPROVEMENTS TO THE PEDESTRIAN AND BICYCLE NETWORK FROM THE HAMILTON AVENUE BRIDGE TO 43RD STREET AND 1ST AVENUE, THE FUTURE LOCATION OF BUSH TERMINAL PIERS PARK | IMPROVEMENTS TO THE PEDESTRIAN AND BICYCLE NETWORK FROM THE HAMILTON AVENUE BRIDGE TO 43RD STREET AND 1ST AVENUE, THE FUTURE LOCATION OF BUSH TERMINAL PIERS PARK | 2022 | 12060 | 14630.73 | 1626 | 454 | 0 | 1166 | 0 | 0 | 17876.73 | 8864.76 | 0 | 1115 | 0 | 0 | 0 | 0 | 9979.76
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048E | Brooklyn Waterfront Greenway - Commercial St/Ash St, BED-806 | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K HW-D101 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BROOKLYN WATERFRONT GREENWAY - COMMERCIAL STREET/ASH STREET | BROOKLYN WATERFRONT GREENWAY - COMMERCIAL STREET/ASH STREET | 2022 | 10300 | 0 | 972 | 0 | 0 | 999 | 0 | 0 | 1971 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 10000
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1048G | OWL'S HEAD-BROOKLYN GREENWAY (SEK002378) | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | OWL'S HEAD - BROOKLYN GREENWAY | OWL'S HEAD - BROOKLYN GREENWAY | 2022 | 6400 | 16575.73 | 2043 | 0 | 0 | 0 | 0 | 0 | 18618.73 | 4412.8 | 0 | 0 | 0 | 0 | 0 | 0 | 4412.8
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1148 | JEWEL STREET AREA | PRIMARY STREET RECONSTRUCTION | 205 | WM-0001 HW-1148 HW-0061 HW-0200 TF-0002 TF-0502 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  |  | 2022 | 9274 | 3128.02 | 0 | 0 | 0 | 0 | 33902 | 0 | 37030.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669A | 4th Ave Safety Improvements - Phase A | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 4TH AVE FROM 18TH TO 33RD ST | 4TH AVE SAFETY IMPROVEMENTS - PHASE 2 | 2022 | 54835 | 33106.86 | 4717 | 0 | 0 | 2477 | 0 | 0 | 40300.86 | 20544.78 | 0 | 0 | 0 | 0 | 0 | 0 | 20544.78
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1669B | 4th Ave Safety Improvements - Phase B | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | 4TH AVE SAFETY IMPROVEMENTS PHASE B - ATLANTIC AVENUE TO 8TH ST | 2022 | 149799 | 0 | 4858 | 1306 | 0 | 0 | 141760 | 0 | 147924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK1672 | WASHINGTON AVENUE SAFETY IMPROVEMENTS | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | WASHINGTON AVENUE SAFETY IMPROVEMENTS | WASHINGTON AVENUE SAFETY IMPROVEMENTS | 2022 | 11100 | 1677.87 | 0 | 0 | 9323 | 0 | 0 | 0 | 11000.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2013GB | Gerritsen Beach - Street Reconstruction | LOCAL STREET RECONSTRUCTION | 215 | HW-0001K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | GERRITSEN BEACH AREA IN BROOKLYN INCLUDING ABBEY CT, BEACON CT, EATONCT, AND FRANK CT FROM SEBA AVE TO CYRUS AVE; CANTON CT AND DARE CT FROM BARTLETT PL TO CYRUS AVE; AND BARTLETT PL FROM ABBEY CT TO PLUMB BEACH AVE | RECONSTRUCTION OF STREETS WITHIN GERRITSEN BEACH AREA IN BROOKLYN INCLUDING ABBEY CT, BEACON CT, EATON CT, AND FRANK CT FROM SEBA AVE TO CYRUS AVE; CANTON CT AND DARE CT FROM BARTLETT PL TO CYRUS AVE; AND BARTLETT PL FROM ABBEY CT TO PLUMB BEACH AVE. THE PROJECT WILL BRING STREETS TO A STATE-OF-GOOD-REPAIR. | 2022 | 4400 | 10866.3 | 750 | 0 | 0 | 0 | 0 | 0 | 11616.3 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 2500
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK2048 | Jamaica Bay Greenway - Paerdegat Ave.N Connector BED-833 | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K HW-0200 TF-0002 TF-0502 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | JAMAICA BAY GREENWAY - PAERDEGAT AVE. NORTH CONNECTOR | JAMAICA BAY GREENWAY - PAERDEGAT AVE. NORTH CONNECTOR | 2022 | 3540 | 1066 | 0 | 5629 | 0 | 0 | 0 | 0 | 6695 | 299.9 | 0 | 840 | 0 | 0 | 0 | 0 | 1139.9
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK614D | RECONSTRUCTION OF BERGEN AVENUE AREA, BKLYN /BED-784 | PRIMARY STREET RECONSTRUCTION | 218 | HW-0614 HW-0001K | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RECONSTRUCTION OF BERGEN AVENUE AREA, BKLYN | RECONSTRUCTION OF BERGEN AVENUE AREA, BKLYN | 2022 | 30591 | 30164.62 | 3575 | 0 | 100 | 0 | 0 | 0 | 33839.62 | 191.25 | 0 | 0 | 0 | 0 | 0 | 0 | 191.25
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK639WA | RECON: TILLARY STREET PHASE 2 | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RECON: TILLARY STREET PHASE 2 | RECON: TILLARY STREET PHASE 2 | 2022 | 17200 | 13873.3 | 218 | 0 | 0 | 0 | 0 | 0 | 14091.3 | 31561.08 | 0 | 0 | 0 | 0 | 0 | 0 | 31561.08
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK700B | Reconstruction of Columbia Street Area Phase II (BED-768B) | PRIMARY STREET RECONSTRUCTION | 206 | HW-0001K | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | COLUMBIA STREET RECONSTRUCTION (SOUTH OF HAMILTON AVE.) THIS PROJECTIS IN CONJUNCTION WITH NYCDEP PROJECT BED768/SE. | COLUMBIA STREET RECONSTRUCTION (SOUTH OF HAMILTON AVE.) THIS PROJECTIS IN CONJUNCTION WITH NYCDEP PROJECT BED768/SE. | 2022 | 14097 | 2873.16 | 0 | 0 | 48185 | 0 | 0 | 0 | 51058.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK779W | EMPIRE BOULEVARD, BED-796 | PRIMARY STREET RECONSTRUCTION | 209 | HW-0779 TF-0002 TF-0502 HW-0944 HW-0001K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCT EMPIRE BOULEVARD | RECONSTRUCTION OF EMPIRE BLVD FROM FRANKLIN AVENUE TO UTICA AVENUERECONSTRUCTION OF THE EXISTING ROADWAYROADWAY RECONSTRUCTION SHALL INCLUDE NEW CURBS, SIDEWALKS, AND REQUIREREPLACEMENTAMENITIES WILL BE INCLUDEDCITY FUNDEDIN CONJUNCTION WITH DEP | 2022 | 20921 | 5645.67 | 1322 | 0 | 0 | 0 | 0 | 0 | 6967.67 | 8668.46 | 416 | 0 | 0 | 0 | 0 | 0 | 9084.46
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK797W | Schenck Avenue, BED-803 | PRIMARY STREET RECONSTRUCTION | 205 | HW-0796 HW-0200 HW-0944 TF-0002 TF-0502 HW-D101 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | SCHENCK AVENUE | SCHENCK AVENUE | 2022 | 4882 | 1384 | 10738 | 1500 | 1414 | 0 | 0 | 0 | 15036 | 0 | 3629 | 0 | 0 | 0 | 0 | 0 | 3629
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK876 | RECONSTRUCTION OF WYCKOFF AVENUE, BROOKLYN, SEK002351 | PRIMARY STREET RECONSTRUCTION | 204 | HW-0876 HW-D101 HW-K005 HW-0200 TF-0002 TF-0502 HW-0944 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WYCKOFF AVENUE FROM FLUSHING AVENUE TO GATES AVENUERECONSTRUCTION OF THE EXISTING ROADWAYROADWAY RECONSTRUCTION SHALL INCLUDE NEW CURBS, SIDEWALKS, AND REQUIREREPLACEMENTAMENITIES WILLL NOT BE INCLUDEDCITY FUNDEDIN CONJUNCTION WITH DEP | 2022 | 19145 | 6697.93 | 0 | 0 | 0 | 31708 | 0 | 0 | 38405.93 | 0 | 0 | 0 | 0 | 2363 | 0 | 0 | 2363
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWK900 | Brownsville Pedestrian Safety Improvements | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K HW-D101 HW-K005 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BROWNSVILLE PEDESTRIAN SAFETY IMPROVEMENTS | BROWNSVILLE PEDESTRIAN SAFETY IMPROVEMENTS | 2022 | 10400 | 700 | 0 | 0 | 11700 | 0 | 0 | 0 | 12400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKDTBK | Park Avenue - Ingersoll Safety Improvements | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K HW-K005 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PARK AVENUE - INGERSOLL SAFETY IMPROVEMENTS | PARK AVENUE - INGERSOLL SAFETY IMPROVEMENTS | 2022 | 1700 | 0 | 1115 | 0 | 0 | 1434 | 1868 | 0 | 4417 | 0 | 0 | 0 | 0 | 0 | 5599 | 0 | 5599
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKF488R | Hamilton Asphalt Plant Roof Replacement | FACILITY RECONSTRUCTION | 200 | HW-0003 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | HAMILTON ASPHALT PLANT ROOF REPLACEMENT | HAMILTON ASPHALT PLANT ROOF REPLACEMENT | 2022 | 727 | 1101.57 | 5960 | 19 | 0 | 0 | 0 | 0 | 7080.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWKKP005 | DUMBO D.M.A. - VINEGAR HILL AREA, BED-794,SANDHWK05 | PRIMARY STREET RECONSTRUCTION | 202 | HW-0001K HW-0944 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | DUMBO D.M.A. | DUMBO D.M.A. | 2022 | 2200 | 42318.07 | 1133 | 0 | 0 | 4372 | 0 | 0 | 47823.07 | 23579.91 | 678 | 0 | 0 | 0 | 0 | 0 | 24257.91
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC1 | Citywide Complex Pedestrian Ramps - Brooklyn | PEDESTRIAN RAMP CONSTRUCTION | 200 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITYWIDE COMPLEX PEDESTRIAN RAMPS- BROOKLYN | 2022 | 6687 | 1257.48 | 85 | 6180 | 0 | 116 | 0 | 0 | 7638.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC2 | Citywide Complex Pedestrian Ramps - Brooklyn | PEDESTRIAN RAMP CONSTRUCTION | 200 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITYWIDE COMPLEX PEDESTRIAN RAMPS- BROOKLYN | 2022 | 6687 | 1780.3 | 0 | 7215 | 0 | 0 | 0 | 0 | 8995.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP19KC3 | Citywide Complex Pedestrian Ramps - Brooklyn | PEDESTRIAN RAMP CONSTRUCTION | 200 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITYWIDE COMPLEX PEDESTRIAN RAMPS- BROOKLYN | 2022 | 6687 | 1947.95 | 0 | 6180 | 0 | 0 | 0 | 0 | 8127.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2020KC | Non-Standard Ped Ramp Installs - Brooklyn | PEDESTRIAN RAMP CONSTRUCTION | 200 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX PED RAMP INSTALLS - BROOKLYN | COMPLEX PED RAMP INSTALLS - BROOKLYN | 2022 | 7275 | 1166.49 | 0 | 0 | 8170 | 0 | 0 | 30 | 9366.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4 | Multi-Site Pedestrian Safety | LOCAL STREET RECONSTRUCTION | 299 | HW-0988 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | FUNDING IS FOR TWO LOCATIONS; 1) $200K FOR CHRUCH AVE/PROSPECT EXPY AND 2) $189K FOR 8TH AVE & 57TH ST SAFE ROUTES FOR SENIORS | FUNDING IS FOR TWO LOCATIONS; 1) $200K FOR CHRUCH AVE/PROSPECT EXPY AND 2) $189K FOR 8TH AVE & 57TH ST SAFE ROUTES FOR SENIORS | 2022 | 563 | 17560.71 | 1544 | 0 | 0 | 0 | 0 | 0 | 19104.71 | 1664.31 | 0 | 20 | 0 | 0 | 0 | 0 | 1684.31
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF4A | Multi-Site Pedestrian Safety - Phase 4A | PRIMARY STREET RECONSTRUCTION | 200 | HW-1684 HW-D103 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | MULTI-SITE PEDESTRIAN SAFETY - PHASE 4A | MULTI-SITE PEDESTRIAN SAFETY - PHASE 4A | 2022 | 4123 | 1162.42 | 2500 | 612 | 0 | 0 | 0 | 0 | 4274.42 | 2514 | 0 | 0 | 0 | 0 | 0 | 0 | 2514
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPEDSF5 | Multi-Site Pedestrian Safety Phase 5 | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001Q HW-0001K HW-D102 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | MULTI-SITE LOCATIONS | MULTI-SITE LOCATIONS | 2022 | 400 | 22213.63 | 201 | 690 | 0 | 728 | 0 | 0 | 23832.63 | 1524.7 | 0 | 0 | 0 | 0 | 0 | 0 | 1524.7
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ017K | Osborn Street Plaza | PRIMARY STREET RECONSTRUCTION | 200 | HW-1684 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | OSBORN STREET PLAZA | OSBORN STREET PLAZA | 2022 | 2500 | 1039.32 | 0 | 3232 | 0 | 0 | 0 | 0 | 4271.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19K2 | Pedestrian Ramp Rehabilitation - Brooklyn | PEDESTRIAN RAMP CONSTRUCTION | 200 | HW-0200 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | PEDESTRIAN RAMP REHABILITATION- BROOKLYN | 2022 | 13813 | 14121.35 | 0 | 0 | 572 | 0 | 0 | 0 | 14693.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19KC | Complex Upgrades Ped Ramp - Brooklyn | PEDESTRIAN RAMP CONSTRUCTION | 200 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX UPGRADES PED RAMP - BROOKLYN | COMPLEX UPGRADES PED RAMP - BROOKLYN | 2022 | 7705 | 1975 | 0 | 7238 | 635 | 0 | 0 | 0 | 9848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K1 | Pedestrian Ramps Rehabilitation - Brooklyn | PEDESTRIAN RAMP CONSTRUCTION | 200 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PEDESTRIAN RAMP REHAB - BROOKLYN | PEDESTRIAN RAMPS REHAB - BROOKLYN | 2022 | 17211 | 2724.61 | 10976 | 198 | 2790 | 0 | 0 | 0 | 16688.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K2 | Pedestrian Ramp Rehabilitation - Brooklyn | PEDESTRIAN RAMP CONSTRUCTION | 200 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PEDESTRIAN RAMP REHABILITATION - BROOKLYN | PEDESTRIAN RAMP REHABILITATION - BROOKLYN | 2022 | 17211 | 2810.01 | 11061 | 745 | 2650 | 0 | 0 | 0 | 17266.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20K3 | Pedestrian Ramp Rehabilitation - Brooklyn | PEDESTRIAN RAMP CONSTRUCTION | 200 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PEDESTRIAN RAMP REHABILITATION - BROOKLYN | PEDESTRIAN RAMP REHABILITATION - BROOKLYN | 2022 | 17211 | 2638.78 | 11012 | 0 | 3656 | 0 | 0 | 0 | 17306.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20KC | Non-Standard Upgrades Ped Ramp - Brooklyn | PEDESTRIAN RAMP CONSTRUCTION | 200 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX UPGRADES PED RAMP - BROOKLYN | COMPLEX UPGRADES PED RAMP - BROOKLYN | 2022 | 6348 | 670 | 0 | 0 | 5899 | 0 | 0 | 0 | 6569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | PEDESTRIAN RAMP CONSTRUCTION | 200 | HW-0200 |  |  | REHABILITATION OF STANDARD PED RAMPS - BROOKLYN | 2022 | 16626 | 200 | 21835 | 0 | 0 | 0 | 0 | 0 | 22035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22K1 | Rehabilitation of Standard Ped Ramps - Brooklyn | PEDESTRIAN RAMP CONSTRUCTION | 200 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | REHABILITATION OF STANDARD PED RAMPS - BROOKLYN | REHABILITATION OF STANDARD PED RAMPS - BROOKLYN | 2022 | 15958 | 0 | 6128 | 6253 | 3126 | 0 | 0 | 0 | 15507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2009K | PRIOR NOTICE SIDEWALKS - BROOKLYN(SIM) | SIDEWALK RECONSTRUCTION | 200 | HW-0200 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PRIOR NOTICE SIDEWALKS - BROOKLYN | PRIOR NOTICE SIDEWALKS - BROOKLYN | 2022 | 3274 | 3211 | 0 | 0 | 0 | 0 | 0 | 226 | 3437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K1 | Prior Notice Sidewalks- Brooklyn | SIDEWALK RECONSTRUCTION | 200 | HW-0200 P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PRIOR NOTICE SIDEWALKS- BROOKLYN | PRIOR NOTICE SIDEWALKS- BROOKLYN | 2022 | 8000 | 4923.19 | 2455 | 0 | 123 | 0 | 0 | 2110 | 9611.19 | 866 | 0 | 0 | 866 | 0 | 0 | 0 | 1732
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020K2 | Prior Notice Sidewalks- Brooklyn | SIDEWALK RECONSTRUCTION | 200 | HW-0200 P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PRIOR NOTICE SIDEWALKS- BROOKLYN | PRIOR NOTICE SIDEWALKS- BROOKLYN | 2022 | 8000 | 100 | 6317 | 0 | 0 | 0 | 0 | 0 | 6417 | 0 | 865 | 0 | 0 | 0 | 0 | 0 | 865
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021K | PRIOR NOTICE SIDEWALK - BROOKLYN | SIDEWALK RECONSTRUCTION | 200 | HW-0200 P-1331 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PRIOR NOTICE SIDEWALKS | 2022 | 9418 | 0 | 7190 | 0 | 0 | 0 | 0 | 0 | 7190 | 0 | 1914 | 0 | 0 | 0 | 0 | 0 | 1914
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWSRT200E | Safe Routes to Transit: 86th Street | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K HW-0200 HW-0988 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SAFE ROUTES TO TRANSIT: 86TH STREET | SAFE ROUTES TO TRANSIT: 86TH STREET | 2022 | 500 | 2270.08 | 0 | 680 | 9110 | 0 | 0 | 0 | 12060.08 | 0 | 0 | 0 | 10250 | 0 | 0 | 0 | 10250
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK1 | Trench Restoration - Brooklyn | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K HW-K005 HW-D101 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TRENCH RESTORATION - BROOKLYN | 2022 | 25278 | 2563.83 | 0 | 23158 | 0 | 0 | 0 | 0 | 25721.83 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRK883 | Trench Restoration -- Bay Parkway, Brooklyn, SE-883 | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | TRENCH RESTORATION -- BAY PARKWAY, BROOKLYN | TRENCH RESTORATION -- BAY PARKWAY, BROOKLYN | 2022 | 5129 | 250 | 0 | 0 | 0 | 5129 | 0 | 0 | 5379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LB20DUMBO | ADAMS STREET LIBRARY FIT OUT | ESSENTIAL RECONSTRUCTION OF FACILITIES | 201 | LB-0101 LB-0108 LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW BRANCH FIT OUT | 2022 | 5000 | 0 | 4535 | 0 | 0 | 0 | 0 | 0 | 4535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC10CDHC | CLARENDON HVAC Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 217 | LB-D104 LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BOILER REPLACEMENT | 2022 | 775 | 1070.96 | 1473 | 593 | 0 | 0 | 0 | 0 | 3136.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC12STHC | Saratoga Heating & Cooling | ESSENTIAL RECONSTRUCTION OF FACILITIES | 216 | LB-0104 LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SARATOGA HVAC REPLACEMENT | 2022 | 790 | 2952.52 | 550 | 0 | 0 | 0 | 0 | 0 | 3502.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC13BPRF | Borough Park Overhaul | ESSENTIAL RECONSTRUCTION OF FACILITIES | 210 | LB-0104 LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROOF RENOVATION | 2022 | 3177 | 1918.16 | 0 | 2044 | 0 | 18616 | 0 | 0 | 22578.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC14LDRF | LEONARD ROOF REPLACEMENT | ESSENTIAL RECONSTRUCTION OF FACILITIES | 201 | LB-D104 LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LEONARD ROOF REPAIR | 2022 | 975 | 356.61 | 0 | 0 | 766 | 0 | 0 | 0 | 1122.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC15BWHC | Bushwick Heating & Cooling | ESSENTIAL RECONSTRUCTION OF FACILITIES | 201 | LB-D104 LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BUSHWICK HEATING & COOLING | 2022 | 750 | 583.33 | 0 | 2736 | 0 | 0 | 0 | 0 | 3319.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC15FLRF | Flatlands Envelope Rehabilitation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 218 | LB-D104 LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FLATLANDS ENVELOPE REHABILITATION | 2022 | 750 | 2270.32 | 236 | 123 | 0 | 0 | 0 | 0 | 2629.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC16MD2F | MIDWOOD 2ND FLOOR RENOVATIONS | ESSENTIAL RECONSTRUCTION OF FACILITIES | 214 | LB-0104 LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MIDWOOD 2ND FLOOR RENOVATION | 2022 | 1030 | 1273 | 0 | 830 | 6697 | 0 | 0 | 0 | 8800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC16MPHC | MAPLETON HVAC REPLACEMENT | ESSENTIAL RECONSTRUCTION OF FACILITIES | 212 | LB-D104 LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MAPLETON HVAC REPLACEMENT | 2022 | 750 | 549.4 | 0 | 3003 | 0 | 0 | 0 | 0 | 3552.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17CDOP | CLARENDON OUTDOOR PLAZA | ESSENTIAL RECONSTRUCTION OF FACILITIES | 217 | LB-D104 LB-0104 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CLARENDON OUTDOOR PLAZA | 2022 | 218 | 579.01 | 17 | 691 | 0 | 0 | 0 | 0 | 1287.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17MPGD | MAPLETON GARDEN RENOVATION | ESSENTIAL RECONSTRUCTION OF FACILITIES | 212 | LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MAPLETON GARDEN RENOVATION | 2022 | 1000 | 161.27 | 0 | 788 | 0 | 0 | 0 | 0 | 949.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBC17MRAD | MARCY AUDITORIUM REHABILITATION | ESSENTIAL RECONSTRUCTION OF FACILITIES | 203 | LB-D104 LB-0104 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MARCY AUDITORIUM REHABILITATION | 2022 | 422 | 250.64 | 413 | 0 | 0 | 0 | 0 | 0 | 663.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBCA06SPK | Sunset Park Library | ESSENTIAL RECONSTRUCTION OF FACILITIES | 201 | LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INTERIOR MODIFICATIONS | 2022 | 1435 | 578.58 | 0 | 0 | 329 | 0 | 0 | 0 | 907.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBCA07FBH | FLATBUSH - Roof and Boiler Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 214 | LB-0104 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NEW ROOF AND BOILER | 2022 | 800 | 1866.98 | 0 | 0 | 0 | 0 | 249 | 0 | 2115.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK13EFBR | EAST FLATBUSH - BRANCH RENOVATION | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES |  | LB-0104 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | EAST FLATBUSH TECHNOLOGY CENTER | 2022 | 3325 | 13612.8 | 317 | 0 | 0 | 0 | 0 | 0 | 13929.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK15BDHC | Bedford Heating & Cooling | ESSENTIAL RECONSTRUCTION OF FACILITIES | 203 | LB-D104 LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HEATING AND COOLING | 2022 | 1070 | 3363.27 | 138 | 251 | 300 | 0 | 0 | 0 | 4052.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK15WTHC | Windsor Terrace Heating & Cooling | ESSENTIAL RECONSTRUCTION OF FACILITIES | 207 | LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WINDSOR TERRACE HEATING & COOLING REPLACEMENT | 2022 | 750 | 3814.37 | 96 | 0 | 0 | 0 | 217 | 0 | 4127.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBK16STRF | Saratoga Envelope Rehab | ESSENTIAL RECONSTRUCTION OF FACILITIES | 216 | LB-K001 LB-D104 LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SARATOGA ROOF REPLACEMENT | 2022 | 1260 | 568.68 | 0 | 1639 | 0 | 0 | 0 | 0 | 2207.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBKA05RUG | Rugby - Branch Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 217 | LB-D104 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PARTIAL INTERIOR /PUBLIC SERVICE ENHANCEMENTS | 2022 | 1140 | 12152.74 | 1192 | 0 | 0 | 0 | 0 | 0 | 13344.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13CGHC | Carroll Gardens HVAC & Teen Ctr | ESSENTIAL RECONSTRUCTION OF FACILITIES | 206 | LB-0104 LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CARROLL GARDENS HVAC REPLACEMENT | 2022 | 1105 | 1292.04 | 0 | 6405 | 0 | 0 | 0 | 0 | 7697.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM13LDHC | LEONARD HVAC REPLACEMENT | ESSENTIAL RECONSTRUCTION OF FACILITIES | 201 | LB-0104 LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LEONARD HVAC REPLACEMENT | 2022 | 965 | 902.48 | 0 | 0 | 2283 | 0 | 0 | 0 | 3185.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM14BWRF | BUSHWICK ROOF REPLACEMENT | ESSENTIAL RECONSTRUCTION OF FACILITIES | 201 | LB-0104 LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BUSHWICK ROOF REPLACEMENT | 2022 | 1072 | 324.38 | 0 | 1116 | 0 | 0 | 0 | 0 | 1440.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15GBRF | GERRITSEN BEACH ENVELOPE REHAB | ESSENTIAL RECONSTRUCTION OF FACILITIES | 215 | LB-K001 LB-0104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BUILDING ENVELOPE REHAB | 2022 | 827 | 371.25 | 50 | 0 | 1356 | 0 | 0 | 0 | 1777.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15MPRF | Mapleton Envelope Rehabilitation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 212 | LB-0104 LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MAPLETON ENVELOPE REHABILITATION | 2022 | 870 | 580.15 | 0 | 3678 | 0 | 0 | 0 | 0 | 4258.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15RDHC | Ryder Heating & Cooling | ESSENTIAL RECONSTRUCTION OF FACILITIES | 212 | LB-0104 LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RYDER HEATING & COOLING | 2022 | 827 | 709.44 | 2508 | 0 | 0 | 0 | 0 | 0 | 3217.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM15RDRF | Ryder Envelope Rehabilitation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 212 | LB-0104 LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RYDER ENVELOPE REHABILITATION | 2022 | 873 | 441.01 | 1578 | 0 | 0 | 0 | 0 | 0 | 2019.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM16GSFC | GRAVESEND FACADE REHAB | ESSENTIAL RECONSTRUCTION OF FACILITIES | 215 | LB-0104 LB-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GRAVESEND FACADE REHAB | 2022 | 637 | 462.75 | 300 | 1753 | 0 | 0 | 0 | 0 | 2515.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM17ARBR | ARLINGTON BRANCH RENOVATION | ESSENTIAL RECONSTRUCTION OF FACILITIES | 205 | LB-0104 LB-D104 |  |  | ARLINGTON BRANCH RENOVATION | 2022 | 9175 | 1461.27 | 0 | 1763 | 8019 | 0 | 0 | 0 | 11243.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM17NUOH | New Utrecht Overhaul | ESSENTIAL RECONSTRUCTION OF FACILITIES | 211 | LB-0104 LB-D104 |  |  | NEW UTRECHT BRANCH OVERHAUL | 2022 | 26333 | 780.47 | 0 | 1615 | 0 | 0 | 22358 | 0 | 24753.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM18BVOH | Brownsville Overhaul | ESSENTIAL RECONSTRUCTION OF FACILITIES | 216 | LB-0104 LB-D104 |  |  | BROWNSVILLE BRANCH OVERHAUL | 2022 | 23742 | 3053.34 | 0 | 3634 | 23547 | 0 | 0 | 0 | 30234.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM18EPOH | Eastern Parkway Overhaul | ESSENTIAL RECONSTRUCTION OF FACILITIES | 209 | LB-0104 LB-D104 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | EASTERN PARKWAY BRANCH OVERHAUL | 2022 | 22000 | 2880.5 | 0 | 0 | 748 | 30000 | 0 | 0 | 33628.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | LBM19BPLB | Brower Park Library Fit Out | ESSENTIAL RECONSTRUCTION OF FACILITIES | 208 | LB-0107 LB-D107 LB-K107 PU-0025 |  |  | BROWER PARK LIBRARY FIT OUT | 2022 | 3300 | 0 | 5450 | 0 | 0 | 0 | 0 | 0 | 5450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-IBZ | NDF - ENY IBZ Improvements, SEK002384 | NEIGHBORHOOD REVITALIZATION | 200 | ED-0384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | IBZ STREET IMPROVEMENTS AND BROADBAND SERVICE | 2022 | 8200 | 1639.47 | 33 | 7197 | 0 | 0 | 0 | 0 | 8869.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | NEWCJC2 | NEW CONSTRUCTION AT CROSSROADS JC PHASE 2.0 | CHILD WELFARE FACILITIES | 200 | CS-0005 |  |  | TBD | 2022 | 161040 | 0 | 24340 | 0 | 136700 | 0 | 0 | 0 | 161040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-213CNTR | Asser Levy Park Reconstruction | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 213 | P-K707 ED-0075 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | CONEY ISLAND CENTER (BROOKLYN) | CONEY ISLAND CENTER | 2022 | 34711 | 5077.44 | 0 | 0 | 0 | 0 | 0 | 5822 | 10899.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-217SCRC | Shirley Chisholm Recreation Center-Nostrand Playground DB | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-D017 P-0245K P-K011 P-0506 |  |  | SHIRLEY CHISHOLM RECREATION CENTER-NOSTRAND PLAYGROUND | 2022 | 183286 | 0 | 1724 | 14932 | 46320 | 78012 | 0 | 0 | 140988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-2CIB1HQ | Coney Island Beach Operations HQ at West 25th Street | BEACHES AND BOARDWALKS | 200 | P-0704 |  |  | CONEY ISLAND BEACH OPERATIONS HQ AT WEST 25TH STREET | 2022 | 56807 | 4704.03 | 301 | 3350 | 0 | 0 | 39184 | 0 | 47539.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77AX | 77TH PRECINCT ANNEX RENOVATION | POLICE FACILITIES | 200 208 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | 77 ANNEX RENOVATION | 2022 | 800 | 1678.59 | 50 | 0 | 0 | 0 | 0 | 0 | 1728.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79-77FA | 77TH PRECINCT FIRE ALARM SYSTEM | POLICE FACILITIES | 200 208 | PO-0079 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 77TH PRECINCT FIRE ALARM SYSTEM | 2022 | 835 | 641.15 | 0 | 1597 | 0 | 0 | 0 | 0 | 2238.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79SHOPR | SERVICE SHOP #6 ROOF RENOVATION | POLICE FACILITIES | 200 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SERVICE SHOP #3 AND # 6 | SHOP # 3 AND # 6 ROOF RENOVATIONS | 2022 | 4727 | 569.89 | 384 | 8089 | 0 | 0 | 0 | 0 | 9042.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV072HVAC | BHS - Brooklyn Historic Society HVAC Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 202 | LB-0109 LB-D109 LB-K109 |  |  | BROOKLYN HISTORIC SOCIETY: HVAC REPLACEMENT. | 2022 | 3983 | 621.9 | 0 | 3361 | 0 | 0 | 0 | 0 | 3982.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV235BDEV | BMA - Brooklyn Museum - Building Envelope Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 209 | PV-K235 PV-D235 PV-0235 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BMA - BROOKLYN MUSEUM - BUILDING ENVELOPE REHAB | 2022 | 8600 | 0 | 0 | 0 | 3555 | 0 | 5350 | 0 | 8905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-AUD | Brooklyn Children's Museum Auditorium | ESSENTIAL RECONSTRUCTION OF FACILITIES | 208 | PV-0262 PV-D262 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | MAIN AUDITORIUM FITOUT. | 2022 | 1000 | 8653.16 | 1239 | 0 | 0 | 0 | 0 | 0 | 9892.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-RT | BCM - BROOKLYN CHILDREN'S MUSEUM - Roof Top Theater Canopy | ESSENTIAL RECONSTRUCTION OF FACILITIES | 208 | PV-D262 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | 145 BROOKLYN AVE, BROOKLYN NY | ROOF TOP THEATER CONSTRUCTION | 2022 | 1000 | 9362.49 | 92 | 0 | 0 | 0 | 0 | 0 | 9454.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV262-RTW | BCM - Brooklyn Children's Museum Retaining Wall | ESSENTIAL RECONSTRUCTION OF FACILITIES | 208 | PV-K262 PV-D262 PV-0467 PV-0262 |  |  | BROOKLYN CHILDREN'S MUSEUM: RETAINING WALL CONSTRUCTION | 2022 | 5856 | 1313.7 | 0 | 0 | 8934 | 0 | 0 | 0 | 10247.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW322X7 | 345 ADAMS ST. - LL 11 CYCLE 7 FACADE REPAIRS | REHABILITATION OF CITY-OWNED OFFICE SPACE | 202 | PW-0322 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FACADE REPAIRS AS PER LL 11/98 INSPECTIONS FOR 345 ADAMS STREET | 2022 | 1089 | 0 | 0 | 0 | 1189 | 0 | 0 | 0 | 1189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77DCA | 245 MESEROLE ST. - DCA TEST STATION REHABILITATION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 201 | PW-0077 PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REHABILITATION OF CRITICAL LIFE AND SAFETY SYSTEMS | 2022 | 249 | 4267.88 | 507 | 0 | 0 | 0 | 0 | 0 | 4774.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GOWAN | GOWANUS CANAL 1 ST TURNING BASIN | MISCELLANEOUS CONSTRUCTION | 206 | PW-0077 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | GOWANUS CANAL 1ST STREET TURNING BASIN ENVIRONMENTAL REMEDIATION DESIGN | 2022 | 4800 | 3856.07 | 0 | 444 | 0 | 0 | 0 | 0 | 4300.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD308JCI | JCC OF GREATER CONEY ISLAND | RENOVATION OF OTHER CITY-OWNED FACILITIES | 213 | PW-D308 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RESCIND $414,207 IN 8/12. | JCC CONEY ISLAND | 2022 | 1635 | 125.73 | 0 | 0 | 0 | 0 | 1060 | 0 | 1185.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWKBEFORD | BEDFORD ATLANTIC ARMORY - NENOVATIONS BEDFORD ATLANTIC ARMOR | MISCELLANEOUS CONSTRUCTION |  | PW-K077 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATIONS OF BEDFORD ATLANTIC ARMORY DRILL SHED AND OTHER SPACES INTO A RECREATIONAL FACILITY. | 2022 | 1060 | 180.23 | 0 | 0 | 0 | 0 | 0 | 1975 | 2155.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | REMPIV | Remsen Yard Reconstruction Phase IV | FACILITY PURCHASES AND RECONSTRUCTION | 218 | EP-0006 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REMSEN YARD RECONSTRUCTION PHASE 4 | 2022 | 1300 | 3486.23 | 435 | 0 | 0 | 0 | 0 | 0 | 3921.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383N | Brooklyn 17/18 HVAC and Roof Replacement | GARAGES AND FACILITIES | 217 218 | S-0136 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | REPLACE ROOF TOP HVAC INCLUDING INSTALLATION OF BUILDING MAINTENCE SYSTEM AND FIRE ALARM WORK | 2022 | 7500 | 3289.9 | 22410 | 0 | 0 | 0 | 0 | 0 | 25699.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-436 | Brooklyn 6 Garage Rehabilitation | GARAGES AND FACILITIES | 206 | S-0136 |  |  | REHAB | 2022 | 100 | 3136.85 | 109 | 13928 | 0 | 0 | 0 | 0 | 17173.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1048 | BWG - Sunset Park North, BED-807 | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K HW-0200 HW-0944 TF-0002 TF-0502 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BWG - IMPROVED PROJECT | BWG - IMPROVED PROJECT | 2022 | 5795 | 146 | 0 | 10032 | 0 | 0 | 0 | 0 | 10178 | 506 | 0 | 2539 | 0 | 0 | 0 | 0 | 3045
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBRIGH | SANDY - NEW BRIGHTON COMFORT STATION RECONSTRUCTION | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 200 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW BRIGHTON COMFORT STATION RECONSTRUCTION | 2022 | 5453 | 719.1 | 2 | 0 | 0 | 0 | 1276 | 0 | 1997.1 | 3312.97 | 12 | 0 | 0 | 0 | 131 | 0 | 3455.97
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC4 | 60TH PRECINCT ELECTRICAL SYSTEM REPLACEMENT( SANDY) | POLICE FACILITIES | 213 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 60TH PRECINCT ELECTRICAL SYSTEM REPLACEMENT( SANDY) | 2022 | 4409 | 1516.13 | 1286 | 9 | 0 | 0 | 0 | 0 | 2811.13 | 3175.68 | 0 | 227 | 0 | 0 | 0 | 0 | 3402.68
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC8 | ERIE BASIN TOW POUND ELECTRICAL (SANDY) | POLICE FACILITIES | 200 206 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ELECTRICAL SYSTEM REPLACEMENT | 2022 | 1990 | 36.11 | 416 | 41 | 0 | 0 | 0 | 0 | 493.11 | 3.11 | 3735 | 369 | 0 | 0 | 0 | 0 | 4107.11
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW19 | Reconstruction of Downtown Brooklyn - Hurricane Sandy | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RECONSTRUCTION OF DOWNTOWN BROOKLYN - HURRICANE SANDY | RECONSTRUCTION OF DOWNTOWN BROOKLYN - HURRICANE SANDY | 2022 | 1607 | 5 | 0 | 0 | 0 | 0 | 0 | 126 | 131 | 0.5 | 0 | 0 | 0 | 0 | 0 | 1123 | 1123.5
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR03 | Jamaica Bay Greenway - Canarsie Pier Connector | PRIMARY STREET RECONSTRUCTION | 200 | HW-0001K HW-0200 TF-0002 TF-0502 HW-0944 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CANARSIE PIER | CANARSIE PIER ACCESS IMPROVEMENTS | 2022 | 2000 | 1031.2 | 2440 | 0 | 0 | 0 | 0 | 0 | 3471.2 | 474 | 2101 | 0 | 0 | 0 | 0 | 0 | 2575
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDRDHK | Red Hook HMGP | MISCELLANEOUS | 200 | PU-0100 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RED HOOK HMGP PROJECT | 2022 | 100000 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 47486 | 0 | 0 | 0 | 47486
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-853 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2A | PROGRAMMATIC RESPONSE TO REGULATORY MANDATES | 218 205 | SE-0200K SE-0004 |  |  | HLSS , STRM, SAN & COMB SWERS & WM IN FRESH CREEK BASIN AREA | 2022 | 16356 | 52338.06 | 2427 | 0 | 0 | 0 | 0 | 0 | 54765.06 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 18
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-855 | HLSS, Strm, San & Comb Swrs, & WM Fresh Creek Basin, Ph 2B | PROGRAMMATIC RESPONSE TO REGULATORY MANDATES | 218 205 | SE-0004 SE-0200K SE-0002K WM-0001 HW-0200 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | HLSS , STRM, SAN & COMB SWERS & WM IN FRESH CREEK BASIN AREA | 2022 | 46639 | 49748.93 | 4700 | 623 | 0 | 0 | 0 | 0 | 55071.93 | 49.5 | 0 | 0 | 0 | 0 | 0 | 0 | 49.5
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-858 | HLSS Installation, Combined Sewer Replmnt (HWK1048A) | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 201 | SE-0004 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | HIGH LEVEL STORM SEWER INSTALLATION, COMBINED SEWER REPLACEMENT AND WATER MAIN REPLACEMENT IN WEST ST. BETWEEN EAGLE ST. AND QUAY ST., ETC BOROUGH OF BROOKLYN. | 2022 | 18792 | 31775.76 | 509 | 0 | 0 | 0 | 0 | 0 | 32284.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002351 | Rehab of SWR & WM in Wycoff Av bt Cooper &Flushing Av,HWK876 | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 204 | SE-0002K WM-0001 EP-0007 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REHAB OF COMB SWRS &W/M IN WYCOFF AV BET COOPER &FLUSHING AV | 2022 | 6020 | 234.11 | 0 | 0 | 0 | 27652 | 0 | 0 | 27886.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002376 | COMB SWR REPLCMNT & WM WORK IN PRESIDENT ST | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 209 | SE-0002K WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COMB SWR REPLCMNT & WM WORK IN PRESIDENT ST, B/T KINGSTON AV & ALBANYAV | 2022 | 3824 | 1335 | 6977 | 0 | 0 | 0 | 0 | 0 | 8312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002377 | San sewer & WM repl 72nd St btwn Av L & Royce Pl, HWK002377 | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 218 | SE-0002K WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SANITARY SEWER & WM REPLACEMENT IN EAST 72ND STREET BETWEEN AVE L & ROYCE PLACE | 2022 | 2148 | 297.85 | 0 | 3680 | 0 | 0 | 0 | 0 | 3977.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002378 | Combined Sewer in Brooklyn Waterfront Greenway (HWK1048G) | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 201 | SE-0002K |  |  | COMBINED SEWER IN BROOKLYN WATERFRONT GREENWAY, BK | 2022 | 2930 | 3458.25 | 347 | 0 | 0 | 0 | 0 | 0 | 3805.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002383 | Combined SE installation & WM replacement in Dean Street | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 208 | SE-0002K WM-0001 SE-1000 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COMBINED SEWER INSTALLATION & WATER MAIN REPLACEMENT IN DEAN STREET, BTW 6TH AVE & VANDERBILT AVE, BROOKLYN | 2022 | 11721 | 1005 | 0 | 13739 | 0 | 0 | 0 | 0 | 14744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002384 | Combined SE rplcmt & dist WM Van Sinderen Av BK NDF-IBZ | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 205 216 | SE-0002K WM-0001 |  |  | COMBINED SEWER REPLACEMENT AND DISTRIBUTION WATER MAIN INSTALLATION IN VAN SINDEREN AVENUE BETWEEN EAST NEW YORK AVE AND RIVERDALE AVE, ANDIN SUTTER AVE BETWEEN VAN SINDEREN AVENUE AND HINSDALE ST. THIS PROJECT IS BEING DEVELOPED IN CONJUNCTION WITH NYCDOT PROJECT NDF-IBZ | 2022 | 13454 | 0 | 0 | 11959 | 0 | 0 | 0 | 0 | 11959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK002386 | Replace combined sewer & WM work,Park Pl & Underhill Ave, BK | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 208 | SE-0002K WM-0001 WM-0006 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACEMENT OF COMBINED SEWER, BULKHEADING OF EXISTING SEWERS & WATERMAIN WORK, PARK PL. B/T UNDERHILL & FLATBUSH AVES, BROOKLYN | 2022 | 8478 | 11310.9 | 1560 | 0 | 0 | 0 | 0 | 0 | 12870.9 | 1407.07 | 0 | 0 | 0 | 0 | 0 | 0 | 1407.07
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20056 | STORM SEWERS-GATEWAY ESTATES - PHASE C (HD-161C) | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 205 | SE-0002K | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | STORM SEWERS IN GATEWAY ESTATES - PHASE C | STORM SEWERS IN GATEWAY ESTATES - PHASE C | 2022 | 4899 | 11850.76 | 195 | 0 | 0 | 0 | 0 | 0 | 12045.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20065 | High level storm sewer Gowanus Canal Area | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 206 | SE-0004 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | DRAINAGE PLAN HIGH LEVEL STORM SEWER INSTALLATION AND WM-1 REPLACEMENT IN GOWANUS CANAL AREA. | 2022 | 9400 | 34783.02 | 0 | 256 | 0 | 0 | 0 | 0 | 35039.02 | 122.24 | 0 | 0 | 0 | 0 | 0 | 0 | 122.24
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20067 | High level storm sewer Gowanus Canal Area. Phase 2. | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 206 | SE-0004 WM-0001 HW-0200 SE-0944 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DRAINAGE PLAN HIGH LEVEL STORM SEWER INSTALLATION AND WM-1 REPLACEMENT IN GOWANUS CANAL AREA. PHASE 2. | 2022 | 9600 | 26832.58 | 1525 | 232 | 0 | 0 | 0 | 0 | 28589.58 | 11387.92 | 687 | 0 | 0 | 0 | 0 | 0 | 12074.92
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20069 | Storm Sewer install & WM replace Gerritsen Beach, HWK2013GB | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 215 | SE-0002K SE-0200K | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STORM SEWER INSTALLATION, & WM REPLACEMENT, GERRITSEN BEACH AREA. PHASE 1, BOROUGH OF BROOKLYN | 2022 | 4195 | 16258.91 | 159 | 0 | 0 | 0 | 409 | 0 | 16826.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK20076 | Replace deficient combined sewers and WM in East 80 St | AUGMENTATION OF WATER SUPPLY SYSTEMS | 200 | SE-0002K WM-0001 |  |  | REPLACE DEFICIENT COMBINED SEWERS IN EAST 80TH STREET AND OTHER LOCATIONS. UPGRADE WATER MAIN IN MAUJER STREET AND HANCOCK STREET. THIS WORK WILL BE DONE IN CONJUNCTION WITH DOT PROJECT HWTRK1. | 2022 | 5456 | 0 | 0 | 4847 | 0 | 0 | 0 | 0 | 4847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK201BN6 | Reconstruction of Existing Sewers, Brooklyn NORTH | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 200 | SE-0002K |  |  | EMERGENCY RECONSTRUCTION OF EXISTING SEWERS, BROOKLYN NORTH | 2022 | 6000 | 8122 | 105 | 0 | 0 | 0 | 0 | 0 | 8227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEK201BN7 | Reconstruction of Existing Sewers, North Brooklyn | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 200 | EP-0007 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RECONSTRUCTION OF EXISTING SEWERS, NORTH BROOKLYN | 2022 | 6250 | 7995.34 | 58 | 0 | 0 | 0 | 0 | 0 | 8053.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEKBN9 | Reconstruction of Existing Sewers, North Brooklyn | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 200 | SE-0002K EP-0007 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RECONSTRUCTION OF EXISTING SEWERS, NORTH BROOKLYN | 2022 | 7125 | 6959.83 | 3575 | 0 | 0 | 0 | 0 | 0 | 10534.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARDOS1 | Brooklyn 17/18 HVAC AND ROOF REPLACEMENT | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  |  | 2022 | 3793 | 736.25 | 8415 | 0 | 0 | 0 | 0 | 0 | 9151.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDEP901 | DEP - Gravity Belt Thickener (GBT) at Newtown Creek WRRF | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | GRAVITY BELT THICKENER (GBT) AT NEWTOWN CREEK WRRF | 2022 | 36101 | 0 | 0 | 0 | 31000 | 0 | 4500 | 0 | 35500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE607 | DOE - LIGHTING UPGRADES | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 204 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | UNIT | 2022 | 1224 | 1018.1 | 0 | 0 | 0 | 0 | 92 | 0 | 1110.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE702 | DOE - VACANCY SENSORS | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | DOE - VACANCY SENSORS | 2022 | 441 | 0 | 441 | 0 | 0 | 0 | 0 | 0 | 441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFDN902 | FDNY - Window Replacement at 4 FDNY Fire Houses | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 |  |  | FDNY - WINDOW REPLACEMENT AT 4 FDNY FIRE HOUSES | 2022 | 743 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264BKCV | 210 JORALEMON ST. OCA RELOCATION | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 201 | CO-0264 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | OCA- RELOCATION FROM 141 LIVINGSTON ST. TO 210 JORALEMON | 2022 | 251438 | 11330.74 | 207931 | 0 | 0 | 18723 | 14645 | 0 | 252629.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272BLR | 45 MONROE PL - BOILER PLANT UPGRADE | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 201 | CO-0272 |  |  | SQ FT | 2022 | 4624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328 | 0 | 3935 | 0 | 0 | 0 | 4263
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO272CHIL | 45 MONROE PL CHILLER REPLACEMENT | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 201 | CO-0272 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SQ FT | 2022 | 1958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190 | 1454 | 0 | 0 | 0 | 0 | 1644
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ADA1 | 360 ADAMS ST - ADA IMPROVEMENTS | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 201 | CO-0278 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | IA/SQ | 2022 | 13238 | 926 | 0 | 0 | 0 | 11108 | 0 | 0 | 12034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278ELV | 360 ADAMS ST.- ELEVATOR MODERNIZATION | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 202 | CO-0278 |  |  | 360 ADAMS ST - ELEVATOR MODERNIZATION | 2022 | 23963 | 0 | 0 | 1000 | 0 | 22963 | 0 | 0 | 23963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278RF | 360 ADAMS STREET - ROOF | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 201 | CO-0278 |  |  | 360 ADAMS STREET - ROOF | 2022 | 521 | 0 | 850 | 43 | 0 | 7144 | 0 | 0 | 8037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO278TOIL | 360 ADAMS ST. - CODE COMPLIANT TOILET UPGRADE | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 202 | CO-0278 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 360 ADAMS ST. - CODE COMPLIANT TOILET UPGRADE | 2022 | 3350 | 0 | 0 | 0 | 0 | 350 | 3000 | 0 | 3350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO281EX | 120 SCHERMERHORN ST.- FACADE/EXTERIOR | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 202 | CO-0281 |  |  | 120 SCHERMERHORN ST.- EXTERIOR CYCLE 8 | 2022 | 3737 | 0 | 0 | 0 | 0 | 380 | 0 | 3357 | 3737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0002 | DOHMH - Brownsville Health Center | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DOHMH - BUSHWICK HEALTH CENTER | 2022 | 182 | 169.3 | 37 | 15 | 0 | 0 | 0 | 0 | 221.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0008 | OCME Brooklyn Chief Medical Examiner Office | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 201 | PU-0025 |  |  | OCME BROOKLYN CHIEF MEDICAL EXAMINER OFFICE | 2022 | 11954 | 0 | 0 | 2236 | 9718 | 0 | 0 | 0 | 11954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0057 | NYPD - 62nd Precinct | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 62ND PRECINCT | 2022 | 300 | 0 | 0 | 131 | 0 | 0 | 0 | 0 | 131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0060 | NYPD - 70th Precinct | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 70TH PRECINCT | 2022 | 300 | 0 | 0 | 136 | 0 | 0 | 0 | 0 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0061 | NYPD - 88th Precinct | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 88TH PRECINCT | 2022 | 300 | 0 | 132 | 0 | 0 | 0 | 0 | 0 | 132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0062 | NYPD - 94th Precinct | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 94TH PRECINCT | 2022 | 300 | 0 | 0 | 209 | 0 | 0 | 0 | 0 | 209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0073 | NYPD - 77TH PRECINCT ANNEX | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | IA/SQ | 2022 | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0074 | NYPD - HARBOR UNIT CHARLIE | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | IA/SQ | 2022 | 300 | 0 | 0 | 297 | 0 | 0 | 0 | 0 | 297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0077 | NYPD - 75TH PRECINCT | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | IA/SQ | 2022 | 300 | 0 | 0 | 198 | 0 | 0 | 0 | 0 | 198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0079 | HHC/DHS - AUBURN FAMILY RESIDENCE (CUMBERLAND DIAGNOSTIC) | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | IA/SQ | 2022 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0082 | DHS - FANNIE BARNES (URBAN TRANSITIONAL HOUSING) | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | IA/SQ | 2022 | 500 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0083 | DHS - PARK SLOPE ARMORY SHELTER | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | IA/SQ | 2022 | 500 | 0 | 277 | 0 | 0 | 0 | 0 | 0 | 277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0085 | DHS - ROSE McCARTHY FAMILY RESIDENCE CAMPUS (2) | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | IA/SQ | 2022 | 400 | 0 | 111 | 0 | 0 | 0 | 0 | 0 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0086 | HRA - BUSHWICK JOB CENTER (FLSUHING) (LEASED IN) | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | IA/SQ | 2022 | 400 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0088 | DPR - McCARREN PARK RECREATION CENTER | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 201 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | IA/SQ | 2022 | 400 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HWKF2514 | 25 14th St Fleet Services Shop Rehabilitation | FACILITY RECONSTRUCTION | 200 | HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 25 14TH ST FLEET SERVICES SHOP REHABILITATION | 2022 | 3300 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW291EV | 209 JORALEMON ST.- ELEVATOR UPGRADE | REHABILITATION OF CITY-OWNED OFFICE SPACE | 201 | PW-0291 |  |  | PER UNIT | 2022 | 5007 | 417 | 0 | 4198 | 0 | 0 | 0 | 0 | 4615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLA6 | 345 Adams, 8th and 9th Fl | REHABILITATION OF CITY-OWNED OFFICE SPACE | 201 | PW-0077 |  |  | SQ/IA | 2022 | 24600 | 0 | 1800 | 22800 | 0 | 0 | 0 | 0 | 24600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW322PLAN | 345 ADAMS RESTACKING PLAN | REHABILITATION OF CITY-OWNED OFFICE SPACE | 202 | PW-0322 PW-0077 |  |  | 345 ADAMS, RESTACKING OF AGENCIES | 2022 | 107049 | 114763.18 | 12712 | 0 | 0 | 0 | 0 | 0 | 127475.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325ELC3 | 210 JORALEMON ST. ELECTRICAL UPGRADE AND EMERGENCY GENERATOR | REHABILITATION OF CITY-OWNED OFFICE SPACE | 201 | PW-0325 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ELECTRICAL UPGRADE AND EMERGENCY GENERATOR | 2022 | 33358 | 29769.7 | 1000 | 0 | 0 | 0 | 0 | 3357 | 34126.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325EV | 210 JORALEMON ST - SIDEWALK ELEVATOR MODERNIZATION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 201 | PW-0325 |  |  | IA/SQ | 2022 | 2352 | 0 | 210 | 0 | 2100 | 0 | 0 | 0 | 2310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW325STA3 | 210 JORALEMON STREET STABILIZATION | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 200 202 | PW-0325 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | INSPECTION, PROBING CORE DRILLING AND STABILIZATION REAR OF BUILDING TO DDC | 2022 | 3672 | 3299.9 | 513 | 100 | 0 | 0 | 0 | 0 | 3912.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAK1 | BKLYN DA - 350 JAY ST, FLs 14-15 RENEWAL OPTION & ADDL SPACE | RENOVATION OF LEASED SPACE | 201 | PW-0326 |  |  | SQ/IA | 2022 | 16007 | 0 | 0 | 16007 | 0 | 0 | 0 | 0 | 16007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAK2 | BKLYN DA - 335 ADAMS STREET, FLs 7 & 26 FAMILY JUSTICE CNTR | RENOVATION OF LEASED SPACE | 201 | PW-0326 |  |  | SQ/IA | 2022 | 7283 | 0 | 0 | 7283 | 0 | 0 | 0 | 0 | 7283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DCPK | DCP - 16 COURT ST RENOVATION | RENOVATION OF LEASED SPACE | 201 | PW-0326 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SQ/IA | 2022 | 920 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOF5 | DOF - RELOCATION FROM 210 JORALEMON AND 345 ADAMS | RENOVATION OF LEASED SPACE | 201 | PW-0326 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RELOCATION FROM 210 JORALEMON AND 345 ADAMS STREET. TO LEASED SPACE | 2022 | 23523 | 15731.57 | 0 | 508 | 0 | 0 | 0 | 0 | 16239.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326LAW7 | LAW - 167 41ST - LAW DEPT CONSOLIDATION | RENOVATION OF LEASED SPACE | 201 | PW-0326 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 167 41ST - LAW DEPT CONSOLIDATION | 2022 | 13182 | 0 | 0 | 0 | 0 | 0 | 0 | 13182 | 13182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAK | LAW DEPT - RAISE THE AGE - BROOKLYN | RENOVATION OF LEASED SPACE | 201 | PW-0326 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | LAW DEPT - RAISE THE AGE - BROOKLYN | 2022 | 5499 | 3409.81 | 0 | 0 | 0 | 0 | 0 | 257 | 3666.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340BOE | BOE - 345 ADAMS ST.- BATHROOMS RENOVATION | BOARD OF ELECTIONS MODERNIZATION | 202 | PW-0340 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BOE - 345 ADAMS ST.- BATHROOMS RENOVATION | 2022 | 260 | 0 | 0 | 0 | 0 | 0 | 260 | 0 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340KEXP | BOE - 5112 2nd AVE, BROOKLYN EXPANSION | RENOVATION OF LEASED SPACE | 201 | PW-0340 |  |  | IA/SQ | 2022 | 801 | 0 | 801 | 0 | 0 | 0 | 0 | 0 | 801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77BHCAM | 209 JORALEMON STREET - CCTV | EQUIPMENT AND INTERAGENCY SERVICES | 201 | PW-0077 |  |  |  | 2022 | 1026 | 904.34 | 98 | 0 | 0 | 0 | 0 | 0 | 1002.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77OEM5 | OEM - EXPANSION OF HEADQUARTERS | RENOVATION OF OTHER CITY-OWNED FACILITIES | 201 | PW-0077 |  |  | OEM EXPANSION OF LEASED SPACE AT CADMAN PLAZA | 2022 | 85000 | 0 | 0 | 10000 | 0 | 0 | 75000 | 0 | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77ZK07 | BROOKLYN COMMUNITY BOARD 7- 4201 4TH AVENUE | REHABILITATION OF CITY-OWNED OFFICE SPACE | 200 | PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BROOKLYN CB 7 RENOVATIONS | 2022 | 473 | 0 | 0 | 0 | 0 | 0 | 473 | 0 | 473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD007HPD | HPD - CONSTRUCTION AND RENOVATION OF NORTHSIDE TOWN HALL | MISCELLANEOUS CONSTRUCTION | 201 | PW-D007 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 134 WYTHE AVE | 2022 | 3150 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD30BENC | BENJAMIN BANNEKER ACADEMY FOR COMMUNITY DEVELOPMENT | EQUIPMENT AND INTERAGENCY SERVICES |  | PW-D308 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BENJAMIN BANNEKER ACADEMY FOR COMMUNITY DEVELOPMENT--TECHNOLOGY UPGRADES | 2022 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78BLL | 360 ADAMS STREET- BROOKLYN SUPREME COURT LAW LIBRARY | REHABILITATION OF CITY-OWNED OFFICE SPACE | 201 | PW-D078 |  |  | DCAS - BROOKLYN SUPREME COURT LAW LIBRARY | 2022 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78SSCT | 360 ADAMS ST.- HVAC STATE SUPREME COURT | RENOVATION OF OTHER CITY-OWNED FACILITIES | 201 | PW-D078 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | STATE SUPREME COURT 360 ADAMS HVAC | 2022 | 230 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2LEED | Brooklyn Borough Hall - LEED- Funding for LEED | REHABILITATION OF CITY-OWNED OFFICE SPACE | 202 | PW-K002 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BROOKLYN BOROUGH HALL - LEED- FUNDING FOR LEED | 2022 | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWK2MEDIA | 209 JORALEMON ST.- BKLYN BORO HALL MEDIA ROOM | REHABILITATION OF CITY-OWNED OFFICE SPACE | 202 | PW-K002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BROOKLYN BORO HALL MEDIA ROOM | 2022 | 1627 | 1449.97 | 0 | 0 | 0 | 398 | 0 | 0 | 1847.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25LL | LOTTS LANE REPAIRING | REHABILITATION OF NON-WATERFRONT PROPERTIES | 201 | RE-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SQ/IA | 2022 | 1438 | 0 | 0 | 0 | 0 | 364 | 0 | 1042 | 1406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25QR | QUENTIN ROAD BROOKLYN STREET RECONSTRUCTION | REHABILITATION OF NON-WATERFRONT PROPERTIES | 201 | RE-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | IA/SQ | 2022 | 1585 | 0 | 0 | 111 | 0 | 351 | 0 | 1110 | 1572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP08 | K005 Building Electrification | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 201 | PU-0025 |  |  | K005 BUILDING ELECTRIFICATION | 2022 | 5380 | 0 | 4950 | 0 | 0 | 0 | 0 | 0 | 4950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | TKYHHC906 | HHC - East New York Comprehensive Energy Upgrade | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 201 | PU-0025 |  |  | EAST NEW YORK COMPREHENSIVE ENERGY UPGRADE | 2022 | 3099 | 0 | 0 | 3099 | 0 | 0 | 0 | 0 | 3099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | TKYHHC907 | HHC - Woodhull Roof and Solar | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 201 | PU-0025 |  |  | WOODHULL ROOF AND SOLAR | 2022 | 7189 | 0 | 0 | 1654 | 5535 | 0 | 0 | 0 | 7189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | TKYHHC908 | HHC - McKinney Nursing Center Comp Energy Upgrade | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 201 | PU-0025 |  |  | DR. SUSAN S. MCKINNEY NURSING CENTER COMPREHENSIVE ENERGY UPGRADE | 2022 | 7403 | 0 | 0 | 600 | 6803 | 0 | 0 | 0 | 7403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | TKYHHC910 | HHC - Kings County D Building BMS Upgrade | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 201 | PU-0025 |  |  | KINGS COUNTY D BUILDING BMS UPGRADE | 2022 | 1868 | 0 | 0 | 430 | 1438 | 0 | 0 | 0 | 1868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BROOKLYN | 856 | DEPT OF CITYWIDE ADMIN SERVS | WD77STAR | STAR ENGINEERING LAB | MISCELLANEOUS CONSTRUCTION | 214 | PW-D077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | TO CONVERT A CLASSROOM AT THE SCIENCE TECHNOLOGY AND REASEARCH EARLYCOLLEGE SCHOOL AT ERASMUS CAMPUS IN BROOKLYN TO AN ELECTRICAL ENGINEERING LAB | 2022 | 350 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18FEEL | 58th Street - New Elevator (ADA Compliance) | ESSENTIAL RECONSTRUCTION OF FACILITIES | 305 | LN-D008 |  |  | 58TH STREET BRANCH--ADA COMPLIANCE - NEW ELEVATOR | 2022 | 150 | 0 | 0 | 0 | 0 | 15 | 135 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18HGHVA | HAMILTON GRANGE - HVAC System Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 309 | LN-0008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACE HVAC | 2022 | 1500 | 0 | 0 | 150 | 1350 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN18TSHVA | TOMPKINS SQUARE - HVAC System Upgrade | ESSENTIAL RECONSTRUCTION OF FACILITIES | 303 | LN-0008 |  |  | HVAC | 2022 | 1500 | 0 | 0 | 150 | 1350 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN2058FPS | 58th St - New Fire Protection Sprinkler System | IMPROVEMENTS TO EXISTING FACILITIES |  | LN-0008 LN-D008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PROVIDE A COMPLETELY CODE COMPLIANT FIRE PROTECTION SPRINKLER SYSTEM THROUGH OUT THE LIBRARY IN FULL COMPLIANCE WITH NYC DEPARTMENT OF BUILDINGS' CODES, RULES & REGULATIONS. THE SYSTEM SHALL BE TIED TO THE BUILDING'S MAIN WATER SUPPLY & INTEGRATED INTO THE BUILDING'S MAIN FIRE ALARM SYSTEM. PROVIDE ALL THE NECESSARY & REQUIRED DOB FILINGS, APPROVALS, SIGN OFFS, ANCILLARY EQUIPMENT, COMPONENTS, DEVICES & PROGRAMMING FOR A FULLY OPERATIONAL & CODE COMPLIANT SYSTEM. | 2022 | 715 | 0 | 0 | 0 | 0 | 131 | 550 | 0 | 681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN21LBHVA | Andrew Heiskell - HVAC System Upgrade | IMPROVEMENTS TO EXISTING FACILITIES | 305 | LN-0008 PU-0025 |  |  | ANDREW HEISKELL - HVAC SYSTEM UPGRADE | 2022 | 10261 | 0 | 0 | 6605 | 0 | 3656 | 0 | 0 | 10261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN22HUDPK | Hudson Park - Comprehensive Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | LN-D008 LN-0008 LN-0101M |  |  | HUDSON PARK - COMPREHENSIVE RENOVATION | 2022 | 24046 | 0 | 0 | 0 | 2000 | 19600 | 2446 | 0 | 24046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LN22YVADA | Yorkville - ADA Accessibility | ACCESS FOR THE HANDICAPPED |  | LN-0008 |  |  | YORKVILLE - ADA ACCESSIBILITY | 2022 | 1800 | 0 | 0 | 500 | 0 | 1300 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA16BLD | Bloomingdale - Roof Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 307 | LN-M001 LN-D008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ROOF RENOVATION | 2022 | 600 | 0 | 0 | 0 | 0 | 65 | 479 | 0 | 544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNMA17CSQ | CHATHAM SQUARE - Boiler Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 303 | LN-D008 LN-M001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CHATHAM SQUARE - BOILER REPLACEMENT. | 2022 | 400 | 0 | 0 | 0 | 0 | 43 | 319 | 0 | 362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNSSEXTFW | 67th St - Building Envelope - Facade & Window Restoration | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | LN-D008 |  |  | NYPL EAST 67TH STREET BRANCH BUILDING ENVELOPE -- FAÚADE AND WINDOW RESTORATION. FY19 ADP | 2022 | 1500 | 0 | 0 | 0 | 0 | 150 | 1350 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 037 | NEW YORK PUBLIC LIBRARY | LNWBEXTFA | Webster - Building Envelope, Facade Restoration | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | LN-D008 |  |  | NYPL WEBSTER BRANCH BUILDING ENVELOPE -- FAÚADE RESTORATION | 2022 | 2000 | 0 | 0 | 0 | 0 | 200 | 1800 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-021 | Bathroom Upgrades | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ALL GENDER BATHROOMS | 2022 | 292 | 0 | 0 | 0 | 0 | 292 | 0 | 0 | 292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | BA001-022 | 17 Lexington Multi-purpose Room | MISCELLANEOUS RECONSTRUCTION | 300 | HN-0300 |  |  | 17 LEXINGTON MULTI-PURPOSE ROOM | 2022 | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | BA013-013 | Data Center, UPS, and Cooling | MISCELLANEOUS RECONSTRUCTION | 300 306 | HN-D300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DATA CENTER, UPS AND COOLING | 2022 | 570 | 0 | 412 | 1 | 157 | 0 | 0 | 0 | 570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | BA019-016 | Library Modernization | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LIBRARY MODERNIZATION | 2022 | 1000 | 1550.45 | 0 | 50 | 0 | 0 | 0 | 0 | 1600.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | BA024-018 | Modification of Main Entrance at 17 Lexington Avenue | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MODIFICATION OF MAIN ENTRANCE AT 17 LEXINGTON AVE | 2022 | 250 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | BA025-018 | Marxe Lab/Public Space Upgrades for School of Public Affairs | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MARXE LAB/PUBLIC SPACE UPGRADES FOOE SCHOOL OF PUBLIC AFFAIRS | 2022 | 500 | 0 | 0 | 0 | 260 | 0 | 0 | 0 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | BA030-020 | Mason Hall A/V System | MISCELLANEOUS RECONSTRUCTION | 300 | HN-M300 HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MASON HALL A/V SYSTEM | 2022 | 1950 | 0 | 0 | 0 | 150 | 1800 | 0 | 0 | 1950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CA001-021 | SLUS - Facility Upgrades | MISCELLANEOUS RECONSTRUCTION | 300 | HN-M300 |  |  | SCHOOL OF LABOR UPGRADE | 2022 | 150 | 0 | 0 | 105 | 45 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CA002-021 | SPS - Virtual Online Desktop - Informatics & Data Analytics | MISCELLANEOUS RECONSTRUCTION | 300 | HN-M300 |  |  | SCHOOL OF PROFESSIONAL STUDIES | 2022 | 100 | 0 | 86 | 0 | 14 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CA003-021 | Critical Maintenance | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CUNY-WIDE LUMP SUM | 2022 | 7000 | 0 | 0 | 0 | 0 | 6851 | 0 | 0 | 6851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CA004-021 | CUNY STEM Institute | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D004 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CUNY STEM INSTITUTE | 2022 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-021 | CUNY SPH Renovation | MISCELLANEOUS RECONSTRUCTION | 300 | HN-M300 |  |  | SCHOOL OF PUBLIC HEALTH | 2022 | 100 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CA005-022 | SPH Expansion and Renovation | MISCELLANEOUS RECONSTRUCTION | 300 | HN-M300 HN-0300 |  |  | SPH EXPANSION AND RENOVATION | 2022 | 150 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CA006-022 | SLUS- Classroom Spaces Upgrade | MISCELLANEOUS RECONSTRUCTION | 300 | HN-0300 |  |  | CLASSROOM SPACES UPGRADE | 2022 | 1500 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CA007-022 | SPS- Workspace Expansion and Welcome Center | MISCELLANEOUS RECONSTRUCTION | 300 | HN-0300 |  |  | SPS- WORKSPACE EXPANSION AND WELCOME CENTER | 2022 | 2600 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CA013-008 | WEB VIDEO SYSTEMS FOR HANDICAPPED STUDENTS, CUNYWIDE | MISCELLANEOUS RECONSTRUCTION |  | HN-D002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MECHANICAL, ELECTRICAL AND PLUMBING UPGRADES, CUNYWIDE | 2022 | 3998 | 681.99 | 0 | 0 | 1317 | 0 | 0 | 0 | 1998.99 | 528.09 | 0 | 0 | 0 | 0 | 0 | 0 | 528.09
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CA027-012 | Community College Laboratories | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D002 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | COMMUNITY COLLEGE LABORATORY IMPROVEMENTS | 2022 | 2000 | 1321.88 | 0 | 0 | 0 | 396 | 0 | 0 | 1717.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CA032-013 | Center for Innovation and Entrepreneurship | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CENTER FOR INNOVATION AND ENTREPRENEURSHIP | 2022 | 2000 | 1786.83 | 0 | 0 | 213 | 0 | 0 | 0 | 1999.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-019 | CUNY In The Heights | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CUNY IN THE HEIGHTS | 2022 | 3040 | 2865.06 | 0 | 0 | 175 | 0 | 0 | 0 | 3040.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CA049-022 | CUNY in the Heights -Media Room Construction/Renovation | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D002 |  |  | CUNY IN THE HEIGHTS- MEDIA ROOM CONSTRUCTION /RENOVATION | 2022 | 2500 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CA050-019 | CUNY-Wide Community College Health, Safety & ADA Projects | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CUNY-WIDE COMMUNITY COLLEGE HEALTH, SAFETY & ADA PROJECTS | 2022 | 12000 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CA056-020 | John Jay School of Law | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | JOHN JAY SCHOOL OF LAW | 2022 | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CA200CW21 | REPLACE 109 ELEVATOR DOORS AT SIX COMMUNITY COLLEGES | MISCELLANEOUS RECONSTRUCTION | 300 | HN-0206 |  |  | REPLACE 109 ELEVATOR DOORS AT SIX COMMUNITY COLLEGES | 2022 | 3026 | 0 | 0 | 3026 | 0 | 0 | 0 | 0 | 3026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CA200MC02 | Pedestrian Plaza and Roof Replacement | NEW SCHOOL CONSTRUCTION | 301 | HN-D002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FIRE ALARM SYSTEM | 2022 | 175 | 2774.9 | 225 | 0 | 0 | 0 | 0 | 0 | 2999.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CA201MC04 | BMCC RAMP & PLAZA PEDESTAL REPAIRS | MISCELLANEOUS RECONSTRUCTION | 301 | HN-D004 | PROJECT DELAYED DUE TO UNFORESEEN HAZARDOUS CONDITION |  | CHAMBERS ST. RAMP AND PLAZA PEDESTAL REPAIRS | 2022 | 500 | 1060.86 | 197 | 0 | 0 | 0 | 0 | 0 | 1257.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CA202MC01 | ADA BATHROOM UPGRADES FOR BMCC | MISCELLANEOUS RECONSTRUCTION | 301 | HN-D002 HN-M001 HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ADA BATHROOM UPGRADES FOR 199 CHAMBERS ST. | 2022 | 940 | 3581.05 | 0 | 502 | 0 | 1 | 0 | 0 | 4084.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CC001-022 | Student Disability Center | MISCELLANEOUS RECONSTRUCTION | 300 | HN-M300 |  |  | STUDENT DISABILITY CENTER | 2022 | 200 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CC002-022 | The Accessibility Center | MISCELLANEOUS RECONSTRUCTION | 300 | HN-0300 |  |  | THE ACCESSIBILITY CENTER | 2022 | 2300 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CC009-007 | Upgrade North Academic Center Classrooms | MISCELLANEOUS RECONSTRUCTION | 300 309 | HN-D004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | UPGRADE NORTH ACADEMIC CENTER CLASSROOMS | 2022 | 350 | 614.36 | 0 | 4 | 41 | 0 | 0 | 0 | 659.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CC012-008 | RESTORATION OF LIBRARY AND BLDG, RANGEL CTR FOR PUBLIC SERV | MISCELLANEOUS RECONSTRUCTION |  | HN-D300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RESTORATION OF LIBRARY AND BLDG, RANGEL CTR FOR PUBLIC SERVICE | 2022 | 40 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CC018-009 | ARONOW THEATER UPGRADE | MISCELLANEOUS RECONSTRUCTION | 300 309 | HN-D300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | AARON DAVIS HALL - IMPROVEMENTS TO LOBBY AND ENTRANCE | 2022 | 1434 | 0 | 0 | 0 | 1174 | 0 | 0 | 0 | 1174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CC022-012 | Schiff House Day Care Center Upgrades | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SCHIFF HOUSE DAY CARE CENTER UPGRADES | 2022 | 1600 | 2077.99 | 0 | 0 | 322 | 0 | 0 | 0 | 2399.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CC025-013 | Dominican Studies Institute | MISCELLANEOUS RECONSTRUCTION | 300 309 | HN-D300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DOMINICAN STUDIES INSTITUTE EXPANSION | 2022 | 200 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CC026-013 | Aaron Davis Hall | MISCELLANEOUS RECONSTRUCTION | 300 309 | HN-M300 HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | AARON DAVIS HALL | 2022 | 400 | 0 | 0 | 0 | 6096 | 0 | 0 | 0 | 6096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CC027-014 | Max Bond Center | MISCELLANEOUS RECONSTRUCTION | 300 309 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MAX BOND CENTER/WINGATE POOL RESTORATION/CONT. & PROF. STUDIES | 2022 | 500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CC029-014 | Network Infrastructure Modernization | MISCELLANEOUS RECONSTRUCTION | 300 309 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NETWORK INFRASTRUCTURE MODERNIZATION | 2022 | 2500 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CC032-015 | City College Computer Lab | MISCELLANEOUS RECONSTRUCTION | 300 | HN-M300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CITY COLLEGE COMPUTER LAB | 2022 | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CC034-016 | Computer Lab Renovation | MISCELLANEOUS RECONSTRUCTION | 300 | HN-M300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COMPUTER LAB RENOVATION | 2022 | 250 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CC037-017 | Harlem Rooftop Garden | MISCELLANEOUS RECONSTRUCTION | 300 | HN-M300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HARLEM ROOFTOP GARDEN | 2022 | 201 | 0 | 0 | 201 | 0 | 0 | 0 | 0 | 201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CC039-017 | Street Improvements | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STREET IMPROVEMENTS | 2022 | 200 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CC041-018 | Wireless Network Upgrade Expansion | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CITY COLLEGE WIRELESS NETWORK UPGRADE AXPANSION | 2022 | 1800 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CC042-018 | Facility Upgrades | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CITY COLLEGE FACILITY UPGRADES | 2022 | 1252 | 0 | 0 | 0 | 1252 | 0 | 0 | 0 | 1252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | CC045-019 | Kitchen Upgrade for the Culinary Program | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | KITCHEN UPGRADE FOR THE CULINARY PROGRAM | 2022 | 1200 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | GR010-022 | Recital Hall & Theater Upgrades | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 |  |  | RECITAL HALL & THEATER UPGRADES | 2022 | 120 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | GR017-014 | Bathroom and HVAC Upgrades | MISCELLANEOUS RECONSTRUCTION | 300 305 | HN-D300 HN-M300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BATHROOM AND HVAC UPGRADES | 2022 | 1000 | 1498.33 | 0 | 27 | 12 | 50 | 0 | 0 | 1587.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | GR018-015 | Library Renovations | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BATHROOM UPGRADES | 2022 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | GR022-017 | Ninth Floor Reconstruction | MISCELLANEOUS RECONSTRUCTION | 300 | HN-M300 HN-D300 |  |  |  | 2022 | 3604 | 0 | 0 | 0 | 3404 | 200 | 0 | 0 | 3604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | GR023-017 | Improvement of Public Spaces | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | IMPROVEMENT OF PUBLIC SPACES | 2022 | 1200 | 0 | 0 | 0 | 975 | 0 | 0 | 0 | 975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | GR029-020 | AUDITORIUM SOUND SYSTEM | MISCELLANEOUS RECONSTRUCTION | 300 305 | HN-D300 HN-M300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | AUDITORIUM SOUND SYSTEM | 2022 | 250 | 0 | 0 | 0 | 125 | 125 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | GU031-013 | New Community College Student Lab Renovations | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW COMMUNITY COLLEGE STUDENT LAB RENOVATIONS | 2022 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | GU051-015 | Guttman Comm. Coll. Building Canopy | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GUTTMAN BUILDING CANOPY | 2022 | 35 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | HC001-021 | Athletic Facility Renovation | MISCELLANEOUS RECONSTRUCTION | 300 | HN-M300 |  |  | ATHLETIC FACILITY RENOVATION | 2022 | 100 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | HC005-022 | Roof Reconstruction | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D002 |  |  | ROOF REPAIRS | 2022 | 100 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | HC026-011 | Phone System Upgrade And Expansion | MISCELLANEOUS RECONSTRUCTION | 300 308 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PHONE SYSTEM UPGRADE AND EXPANSION | 2022 | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | HC032-017 | Athletic Facilities Renovation | MISCELLANEOUS RECONSTRUCTION | 300 | HN-M300 HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ATHLETIC FACILITIES RENOVATION | 2022 | 365 | 1081.6 | 0 | 0 | 117 | 0 | 0 | 0 | 1198.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | HC033-019 | Expansive Glass Addition to the Building Facing West | MISCELLANEOUS RECONSTRUCTION | 308 | HN-M300 HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EXPANSIVE GLASS ADDITION TO THE BUILDING FACING WEST | 2022 | 400 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | HC034-018 | Hunter Campus Atrium | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HUNTER CAMPUS ATRIUM | 2022 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | HC036-020 | GLASS BOX | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GLASS BOX | 2022 | 400 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | HC075-098 | HVAC Improvements | ELECTRICAL, MECHANICAL AND HVAC SYSTEM UPGRADING | 308 | HN-0244 HN-0206 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2022 | 3267 | 16441.85 | 0 | 176 | 0 | 0 | 0 | 0 | 16617.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | HU001-021 | EQFN for the Welcome Center at the School of Education | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 |  |  | SCHOOL OF EDUCATION RENOVATION | 2022 | 100 | 0 | 0 | 70 | 30 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-021 | Construction of a Teaching Kitchen | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 |  |  | TEACHING KITCHEN | 2022 | 75 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | HU002-022 | Auditorium Renovation in North Building | MISCELLANEOUS RECONSTRUCTION | 300 | HN-0300 |  |  | AUDITORIUM RENOVATION IN NORTH BUILDING | 2022 | 4000 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | HU003-021 | Auditorium Renovation | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HUNTER COLLEGE | 2022 | 4000 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | HU004-021 | School of Education Renovation | MISCELLANEOUS RECONSTRUCTION | 300 | HN-M300 |  |  | SCHOOL OF EDUCATION RENOVATION | 2022 | 100 | 0 | 0 | 70 | 30 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | HU007-004 | Restore Roosevelt House | MISCELLANEOUS RECONSTRUCTION | 300 308 | HN-D004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | OTHER | 2022 | 1000 | 785.92 | 0 | 0 | 207 | 0 | 0 | 0 | 992.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | HU011-022 | School of Education Renovation | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 |  |  | SCHOOL OF EDUCATION RENOVATION | 2022 | 150 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | HU022-009 | EXPERIMENTAL PSYCHOLOGY LAB BUILDOUT | MISCELLANEOUS RECONSTRUCTION | 300 308 | HN-D004 HN-M004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EXPAND PSYCHOLOGY LAB | 2022 | 732 | 588.47 | 0 | 0 | 51 | 36 | 0 | 0 | 675.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | HU026-013 | Science and Health Professions Building | NEW SCHOOL CONSTRUCTION | 300 308 | HN-0300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SCIENCE AND HEALTH PROFESSIONS BUILDING | 2022 | 100000 | 0 | 0 | 0 | 0 | 0 | 13468 | 14282 | 27750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | HU027-013 | SCHOOL OF NURSING/HEALTH SCIENCE RELOCATION TO C3 | MISCELLANEOUS RECONSTRUCTION | 300 | HN-0300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SCHOOL OF NURSING/HEALTH SCIENCE RELOCATION TO C3 | 2022 | 47150 | 0 | 0 | 0 | 0 | 0 | 0 | 47150 | 47150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | HU028-015 | Black Box Performance Space | MISCELLANEOUS RECONSTRUCTION | 300 | HN-M300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BLACK BOX PERFORMANCE SPACE | 2022 | 300 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | HU029-015 | Black Box Media & Arts Flex Space Improvements | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BLACK BOX MEDIA & ARTS FLEX SPACE IMPROVEMENTS | 2022 | 375 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | HU035-016 | Black Box Theater Renovation Black Box Theater Renovation | MISCELLANEOUS RECONSTRUCTION | 308 | HN-M003 HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | THEATER RENOVATION | 2022 | 612 | 0 | 0 | 0 | 612 | 0 | 0 | 0 | 612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | HU036-017 | Black Box Renovation | MISCELLANEOUS RECONSTRUCTION | 300 | HN-M300 HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BLACK BOX RENOVATION | 2022 | 500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | HU037-017 | CUNY Hunter College - Performing Arts Hub Project | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CUNY PERFORMING ARTS HUB | 2022 | 5000 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | HU039-018 | Performing Arts Hub - Renovate N Building Auditorium | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATE "N" BUILDING AUDITORIUM | 2022 | 3500 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-018 | Renovate Performing Arts Hub in North Building | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATE PERFORMING ARTS HUB IN NORTH BUILDING | 2022 | 1900 | 0 | 0 | 0 | 1900 | 0 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | HU040-019 | Computer Science 10th FL. North Expansion | MISCELLANEOUS RECONSTRUCTION | 300 | HN-M300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COMPUTER SCIENCE 10TH FL. NORTH EXPANSION | 2022 | 250 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | HU041-019 | Black Box Media Flex Space | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HUNTER COLLEGE BLACK BOX MEDIA FLEX SPACE | 2022 | 2285 | 0 | 0 | 0 | 2285 | 0 | 0 | 0 | 2285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | HU042-019 | Thomas Hunter Hall Upgrades | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | THOMAS HUNTER HALL UPGRADES | 2022 | 950 | 471.87 | 0 | 0 | 478 | 0 | 0 | 0 | 949.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | HU043-020 | Auditorium Renovation in North Building | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | AUDITORIUM RENOVATION IN NORTH BUILDING | 2022 | 4000 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | HU044-020 | Dance Department Lobby Renovation | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DANCE DEPARTMENT LOBBY RENOVATION | 2022 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | JJ001-021 | Multimedia Distribution System | MISCELLANEOUS RECONSTRUCTION | 300 | HN-M300 |  |  | MULTIMEDIA DISTRIBUTION SYSTEM | 2022 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | JJ021-015 | Lloyd Sealy Library Upgrade | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LLOYD SEALY LIBRARY UPGRADE | 2022 | 250 | 215 | 0 | 0 | 0 | 35 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | JJ024-017 | Locker Rooms and Gym Entrance | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LOCKER ROOMS AND GYM ENTRANCE | 2022 | 650 | 0 | 0 | 0 | 650 | 0 | 0 | 0 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | JJ029-018 | Theater ADA Upgrades | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | THEATER ADA UPGRADES | 2022 | 1000 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-021 | Library Interior Renovation | MISCELLANEOUS RECONSTRUCTION | 300 | HN-M005 |  |  | LIBRARY RENOVATION | 2022 | 1800 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | MC001-022 | Library Interior Renovation | MISCELLANEOUS RECONSTRUCTION | 300 | HN-M001 HN-0206 HN-D002 HN-D004 |  |  | LIBRARY INTERIOR RENOVATION | 2022 | 100 | 0 | 748 | 2952 | 1100 | 0 | 0 | 0 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | MC028-010 | CUNY: BMCC, 199 Chambers Street - EE Upgrade | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | HN-M001 PU-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ENERGY EFFICIENCY UPGRADE AT BOROUGH OF MANHATTAN COMMUNITY COLLEGE; 199 CHAMBERS STREET | 2022 | 9900 | 11236.43 | 58 | 2 | 0 | 0 | 0 | 0 | 11296.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | MC029-012 | Gymnasium Air Conditioning System | MISCELLANEOUS RECONSTRUCTION | 300 301 | HN-D004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GYMNASIUM AIR CONDITIONING SYSTEM | 2022 | 1400 | 1000 | 400 | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | MC036-016 | Perimeter Security Lighting | MISCELLANEOUS RECONSTRUCTION | 301 | HN-D002 HN-M005 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PERIMETER SECURITY LIGHTING | 2022 | 300 | 0 | 0 | 0 | 150 | 150 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | MC040-018 | LED Conversion in Public Areas | MISCELLANEOUS RECONSTRUCTION |  | HN-M005 HN-D004 HN-D002 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | LED CONVERSION IN PUBLIC AREAS | 2022 | 1325 | 0 | 0 | 1325 | 0 | 0 | 0 | 0 | 1325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | MC042-018 | BMCC Pedestrian Enclosed Extension | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D004 HN-D002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BMCC PEDESTRIAN ENCLOSED EXTENSION | 2022 | 900 | 202 | 248 | 652 | 1148 | 0 | 0 | 0 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | MC044-019 | New Corridor Access Controls and Doors | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW CORRIDOR ACCESS AND CONTROLS | 2022 | 925 | 0 | 0 | 0 | 925 | 0 | 0 | 0 | 925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | MC045-020 | Tribeca Performing Arts Center Theater 1 & 2 Lighting Upgra | MISCELLANEOUS RECONSTRUCTION | 300 | HN-M005 HN-D002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TRIBECA PERFORMING ARTS CENTER THEATER 1 & 2 LIGHTING UPGRADE INSTALLATION OF NEW LIGHTING FIXTURES | 2022 | 1300 | 0 | 0 | 0 | 1300 | 0 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | MH040-014 | Macaulay Honors College Classroom Upgrades | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MACCAULEY HONORS COLLEGE CLASSROOM UPGRADES | 2022 | 285 | 0 | 0 | 0 | 285 | 0 | 0 | 0 | 285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | MH053-016 | Macaulay Honors College - New Media Lab | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW MEDIA LAB | 2022 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | MH059-017 | Macaulay Honors College Data Science Lab | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DATA SCIENCE LAB | 2022 | 450 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | MH060-020 | New Media/Data Science Lab | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW MEDIA/DATA SCIENCE LAB | 2022 | 450 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | SAND-MC01 | Rehabilitation and Improvements due to Hurricane Sandy | MISCELLANEOUS RECONSTRUCTION | 300 | HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RESTORATION AND IMPROVEMENTS OF CAPITAL FACILITIES | 2022 | 2173 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 042 | CITY UNIVERSITY | SJ049-015 | School of Journalism - Space Upgrades | MISCELLANEOUS RECONSTRUCTION | 300 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SPACE UPGRADES | 2022 | 250 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79 PAL | POLICE ATHLETIC LEAGUE MASONRY | POLICE FACILITIES | 302 | PO-0079 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 24 1/2 EAST 12TH STREET, NY | TO PROVIDE FOR THE FACADE RE POINTING | 2022 | 300 | 144.46 | 0 | 0 | 0 | 0 | 5298 | 0 | 5442.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79137CS | 137 centre street renovation | POLICE FACILITIES | 300 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | 137 CENTRE STREET RENOVATION | 2022 | 0 | 0 | 2045 | 0 | 7980 | 8558 | 0 | 0 | 18583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPDR | One Police Plaza Doors | POLICE FACILITIES | 300 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ONE POLICE PLAZA DOORS | 2022 | 1018 | 0 | 0 | 0 | 0 | 1018 | 0 | 0 | 1018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPF | EMERGENCY RECONSTRUCTION OF 1 POLICE PLAZA FACADE | POLICE FACILITIES | 300 | PO-0079 |  |  | EMERGENCY RECONSTRUCTION OF 1 POLICE PLAZA | 2022 | 17763 | 0 | 17763 | 0 | 0 | 0 | 0 | 0 | 17763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPR2 | ONE POLICE PLAZA & POLICE LAB ROOFS | POLICE FACILITIES | 300 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RECONSTRUCTION | 2022 | 9964 | 6110.83 | 3168 | 0 | 685 | 0 | 0 | 0 | 9963.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 056 | POLICE DEPARTMENT | PO791PPSD | 1 Police Plaza Security Desk | POLICE FACILITIES | 300 | PO-0079 |  |  | SCOPE OF WORK | 2022 | 1020 | 0 | 0 | 568 | 0 | 0 | 0 | 0 | 568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAHO | HVAC REPLACEMENT FOR 20TH, 24TH AND 25TH PCTS | POLICE FACILITIES | 300 307 311 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HVAC SYSTEMS | 2022 | 2024 | 2422 | 236 | 0 | 0 | 0 | 0 | 0 | 2658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAIZ | 24th Precinct Facade | POLICE FACILITIES | 300 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | TO PROVIDE FOR THE FACADE REHABILITATION OF THE 24TH PCT | 2022 | 715 | 0 | 0 | 1083 | 0 | 0 | 0 | 0 | 1083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJF | 32ND PCT PARKING LOT | POLICE FACILITIES | 300 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | PARKING LOT REHABILITATION | 2022 | 67 | 110.44 | 511 | 0 | 0 | 0 | 0 | 0 | 621.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAJQ | 1 Police Plaza Auditorium | POLICE FACILITIES | 300 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ONE POLICE PLAZA AUDITOIUM | 2022 | 8661 | 0 | 0 | 0 | 0 | 3661 | 5000 | 0 | 8661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKC | ELEVATOR REHABILITATION FOR MIDTOWN NORTH PCT | POLICE FACILITIES | 300 | PO-0079 |  |  | ESTIMATE | 2022 | 842 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKP | 1PP STORM DRAIN | POLICE FACILITIES | 300 | PO-0079 |  |  | ESTIMATE | 2022 | 200 | 0 | 652 | 0 | 0 | 0 | 0 | 0 | 652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKX | IAB HVAC REPLACEMENT | POLICE FACILITIES | 300 | PO-0079 |  |  | ESTIMATE | 2022 | 680 | 0 | 1516 | 15 | 0 | 0 | 0 | 0 | 1531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMAKY | 1PP SUMP PUMP | POLICE FACILITIES | 300 | PO-0079 |  |  | ESTIMATE | 2022 | 125 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79BMALA | 5TH PRECINCT CONSTRUCTION RENOVATION | POLICE FACILITIES | 300 | PO-0079 |  |  | SCOPE DESCRIPTION | 2022 | 1533 | 0 | 200 | 1333 | 0 | 0 | 0 | 0 | 1533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79-BMS | BMS PROJECTS | POLICE FACILITIES | 300 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | NA | LUMP SUM | 2022 | 121310 | 0 | 2787 | 826 | 1915 | 9659 | 17299 | 96047 | 128533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79HQBB | 1 POLICE PLAZA SECURITY BARRIERS & BOOTHS | POLICE FACILITIES | 300 | PO-0079 |  |  | 1POLICE PLAZA SECURITY BARRIERS AND BOOTHS | 2022 | 8940 | 6591.53 | 683 | 0 | 0 | 0 | 0 | 0 | 7274.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PA13 | RENOVATION OF OLD POLICE ACADEMY/13TH PCT | POLICE FACILITIES | 300 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | PA RENOVATION | 2022 | 20000 | 379.33 | 0 | 6122 | 2803 | 7500 | 0 | 0 | 16804.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 056 | POLICE DEPARTMENT | PO79PAAUD | OLD POLICE ACADEMY AUDITORIUM RENOVATION | POLICE FACILITIES | 300 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | OLD POLICE ACADEMY AUDITORIUM RENOVATION | OLD POLICE ACADEMY AUDITORIUM RENOVATION | 2022 | 1430 | 3723.69 | 723 | 0 | 0 | 0 | 0 | 0 | 4446.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD6 | HARBOR LAUNCH RANDALL'S ISLAND ELECTRICAL | POLICE FACILITIES | 300 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RANDALL'S ISLND | ELECTRICAL REHABILITATION | 2022 | 713 | 9.56 | 62 | 0 | 0 | 0 | 0 | 0 | 71.56 | 86.11 | 555 | 0 | 0 | 0 | 0 | 0 | 641.11
20220309 | MANHATTAN | 056 | POLICE DEPARTMENT | SANDCD7 | POLICE SERVICE AREA 4 (PSA4) | POLICE FACILITIES | 300 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ELECTRICAL REHABILITATION | 2022 | 2192 | 9.68 | 210 | 0 | 0 | 0 | 0 | 0 | 219.68 | 87.12 | 1885 | 0 | 0 | 0 | 0 | 0 | 1972.12
20220309 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN201 | FDNY - Lighting Upgrades at 11 FDNY Facilities | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 301 | PU-0025 F-0175 |  |  | LIGHTING UPGRADES AT 11 FDNY FACILITIES | 2022 | 1127 | 0 | 1127 | 0 | 0 | 0 | 0 | 0 | 1127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN803 | FDNY - Solar photo-voltaic system at SOC | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SOLAR PHOTO-VOLTAIC SYSTEM AT SOC TACTICAL UNIT FACILITY, ROOSEVELT ISLAND MANHATTAN | 2022 | 142 | 38.34 | 0 | 103 | 0 | 0 | 0 | 0 | 141.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 057 | FIRE DEPARTMENT | ACEFDN901 | FDNY- Solar PV at FDNY Academy Building 12 | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | BLDG 12, FDNY ACADEMY RANDALLS ISLAND | 2022 | 968 | 45.94 | 0 | 822 | 0 | 0 | 0 | 0 | 867.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 057 | FIRE DEPARTMENT | F175KTE22 | KITCHENT RENOVATION - EC22 | NEW FACILITIES AND RENOVATIONS | 308 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | KITCHENT RENOVATION - EC22 | 2022 | 1734 | 233.8 | 0 | 1500 | 0 | 0 | 0 | 0 | 1733.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE33 | Multi-Component Renovations - EC33 | NEW FACILITIES AND RENOVATIONS | 302 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HVAC AND INTERIORS - EC33 | 2022 | 961 | 637.88 | 35 | 7200 | 0 | 0 | 0 | 0 | 7872.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE74 | Multi-Component Renovations - EC74 | NEW FACILITIES AND RENOVATIONS | 307 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FLOOR, KITCHEN & TOILETS L-OHD GENERATOR - EC74 | 2022 | 4452 | 557.41 | 5786 | 0 | 0 | 0 | 0 | 0 | 6343.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCE91 | Multi-Component Renovations - EC91 | NEW FACILITIES AND RENOVATIONS | 311 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MULTI-COMPONENT RENOVATIONS - EC91 | 2022 | 14116 | 1150.7 | 0 | 0 | 96 | 13000 | 0 | 0 | 14246.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 057 | FIRE DEPARTMENT | F175MCL20 | FIREHOUSE RENOVATIONS - LC20 | NEW FACILITIES AND RENOVATIONS | 302 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FIREHOUSE RENOVATIONS - LC20 | 2022 | 2200 | 1207.59 | 0 | 0 | 6 | 8520 | 0 | 0 | 9733.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 057 | FIRE DEPARTMENT | F175RFE54 | ROOF AND WATERPROOFING - EC54 | NEW FACILITIES AND RENOVATIONS | 305 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ROOF AND WATERPROOFING - EC54 | 2022 | 3638 | 437.12 | 0 | 3200 | 0 | 0 | 0 | 0 | 3637.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175DE95 | Door Replacement - EC95 | NEW FACILITIES AND RENOVATIONS | 312 | F-D175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DOOR REPLACEMENT - EC95 | 2022 | 75 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175GE95 | Generator - EC95 | NEW FACILITIES AND RENOVATIONS | 312 | F-D175 F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | GENERATOR - EC95 | 2022 | 575 | 91.12 | 757 | 0 | 0 | 0 | 0 | 0 | 848.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175WN22 | Windown Replacement - EC22 | NEW FACILITIES AND RENOVATIONS | 308 | F-D175 F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WINDOW REPLACEMENT - EC22 | 2022 | 587 | 101.79 | 485 | 0 | 0 | 0 | 0 | 0 | 586.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175WN28 | Window Replacement - EC28 | NEW FACILITIES AND RENOVATIONS | 303 | F-D175 F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WINDOW REPLACEMENT - EC28 | 2022 | 511 | 125.17 | 409 | 0 | 0 | 0 | 0 | 0 | 534.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 057 | FIRE DEPARTMENT | FD175WN74 | Window Replacement - EC74 | NEW FACILITIES AND RENOVATIONS | 307 | F-D175 F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WINDOW REPLACEMENT - EC74 | 2022 | 500 | 598.01 | 234 | 0 | 0 | 0 | 0 | 0 | 832.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | CAPC | CHINESE AMERICAN PLANNING COUNCIL | CHILD WELFARE FACILITIES | 300 303 | CS-D002 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | CONST. | 2022 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 068 | ADMIN FOR CHILDREN'S SERVICES | NSCC | Children's Center High Needs Unit | CHILD WELFARE FACILITIES |  | CS-0003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CHILDREN'S CENTER HIGH NEEDS UNIT | 2022 | 468 | 0 | 758 | 5068 | 0 | 0 | 0 | 0 | 5826 | 0 | 1173 | 7840 | 0 | 0 | 0 | 0 | 9013
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | DHS-LIGHT | DEPT OF HOMELESS SVCS: INSTALL LIGHTING AT 30TH STR SHELTER | ROUTINE RECONSTRUCTION | 306 | HH-D025 |  | 400-430 EAST 30TH STREET, NEW YORK, NY | DEPARTMENT OF HOMELESS SERVICES: FUNDING WILL SUPPORT THE INSTALLATION OF LIGHTING AT THE 30TH STREET SHELTER. | 2022 | 50 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112BLSB | BELLEVUE BASEMENT STRUCTURAL RECONSTRUCTION | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | BELLEVUE BASEMENT STRUCTURAL RECONSTRUCTION | 2022 | 38750 | 0 | 0 | 1000 | 1105 | 10169 | 26476 | 0 | 38750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112BLWB | BELLEVUE WEST BANK ELEVATORS | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | BELLEVUE WEST BANK ELEVATORS | 2022 | 7546 | 0 | 0 | 0 | 1132 | 3414 | 3000 | 0 | 7546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112ETEU | 282 East 3rd Street, 10009 - Exterior Upgrade | SHELTERS FOR HOMELESS INDIVIDUALS | 303 | HH-0112 |  |  | 8 EAST 3RD STREET, 10009 - EXTERIOR UPGRADE | 2022 | 2600 | 175.5 | 0 | 1200 | 1200 | 0 | 0 | 0 | 2575.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112FWBA | FORT WASHINGTON ARMORY- | SHELTERS FOR HOMELESS INDIVIDUALS | 312 | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FORT WASHINGTON ARMORY-1ST FLOOR BATHROOM RENOVATION | 2022 | 400 | 157 | 750 | 305 | 0 | 0 | 0 | 0 | 1212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112FWBO | FT. WASHINGTON ARMORY - BOILER UPGRADE | SHELTERS FOR HOMELESS INDIVIDUALS | 312 | HH-0112 |  |  | FT. WASHINGTON ARMORY - BOILER UPGRADE | 2022 | 3586 | 7844.23 | 2646 | 0 | 0 | 0 | 0 | 0 | 10490.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112FWFR | FORT WASHINGTON ARMORY-DORMITORIES FLOOR REPLACEMENT | SHELTERS FOR HOMELESS INDIVIDUALS | 312 | HH-0112 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FORT WASHINGTON ARMORY - DORMITORIES FLOOR REPLACEMENT | 2022 | 450 | 200 | 750 | 1000 | 2953 | 0 | 0 | 0 | 4903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112GDFC | GEORGE DALY FACADE AND WINDOWS | SHELTERS FOR HOMELESS INDIVIDUALS | 303 | HH-0112 |  |  | GEORGE DALY FACADE AND WINDOWS | 2022 | 2590 | 185 | 500 | 2000 | 3005 | 0 | 0 | 0 | 5690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HBAT | HARLEM 1 BATHROOM RECONSTRUCTION | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | RECONSTRUCT BATHROOMS | 2022 | 2080 | 0 | 0 | 450 | 470 | 1000 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HHAC | HARLEM 1 ROOF AND VENTILATION SYSTEM | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | RECONSTRUCT ROOF AND VENTILATION SYSTEMS | 2022 | 3360 | 0 | 0 | 0 | 280 | 0 | 0 | 3080 | 3360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HINT | HARLEM 1 iNTERIOR RECONSTRUCTION | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | RECONSTRUCT INTERIOR | 2022 | 3000 | 0 | 0 | 250 | 0 | 0 | 0 | 2750 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HLET | HARLEM 1 ELECTRICAL UPGRADE | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | ELECTRICAL UPGRADE | 2022 | 12000 | 0 | 0 | 500 | 700 | 2000 | 0 | 10000 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HMBL | HARLEM 1 BOILER REPLACEMENT | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | HARLEM 1 BOILER REPLACEMENT | 2022 | 1475 | 125 | 1350 | 4153 | 0 | 0 | 0 | 0 | 5628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HMED | HARLEM 1 - ELECTRICAL PANEL UPGRADE | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | HARLEM 1 - ELECTRICAL PANEL UPGRADE | 2022 | 500 | 40 | 0 | 460 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HSCR | HELP SEC-COTTAGE ROOF REPLACEMENT | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | HELP SEC- COTTAGE ROOF REPLACEMENT | 2022 | 2210 | 170 | 2040 | 4026 | 0 | 0 | 0 | 0 | 6236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HSHP | HELP SEC.- HEATING AND PLUMBING | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | HELP SEC.- HEATING AND PLUMBING | 2022 | 0 | 0 | 0 | 200 | 200 | 0 | 4000 | 0 | 4400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112HSMR | HELP SEC.-MIAN BLDG.ROOF REPLACEMENT | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | HELP SEC.-MIAN BLDG. ROOF REPLACEMENT | 2022 | 2340 | 180 | 2160 | 2114 | 0 | 0 | 0 | 0 | 4454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KITC | PROJECT RENEWAL-EAST 3RD STREET KITCHEN NC#13-260288T82144 | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-D025 HH-0112 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | PROJECT RENEWAL-EAST 3RD STREET SHELTER-KITCHEN RENOVATION | 2022 | 1540 | 61.6 | 1527 | 956 | 0 | 0 | 0 | 0 | 2544.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KNUG | KEENER ASSESSMENT SHELTER - BUILDING UPGRADE | SHELTERS FOR HOMELESS INDIVIDUALS | 311 | HH-0112 |  |  | KEENER ASSESSMENT SHELTER - BUILDING UPGRADE | 2022 | 10782 | 0 | 0 | 0 | 829 | 0 | 0 | 4500 | 5329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KTEX | KENTON HALL - FACADE RECONSTRUCTION | SHELTERS FOR HOMELESS INDIVIDUALS | 303 | HH-0112 |  |  | KENTON HALL - FACADE RECONSTRUCTION | 2022 | 456 | 0 | 0 | 0 | 37 | 0 | 419 | 0 | 456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112KTFR | FLUE REPLACEMENT AT KENTON HALL | EQUIPMENT |  | HH-0112 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  |  | 2022 | 880 | 76 | 804 | 0 | 0 | 0 | 0 | 0 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112SWBU | Schwartz Homeless Shelter | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | SCHWARTZ HOMELESS SHELTER - BUILDING UPGRADE | 2022 | 1000 | 0 | 0 | 150 | 0 | 850 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112THBH | 8 EAST THIRD ST BATHROOM RECONSTRUCTION | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | BATHROOM RECON | 2022 | 3600 | 0 | 0 | 300 | 0 | 2000 | 2300 | 0 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112THBR | 282 EAST THIRD ST BOILER RECONSTRUCTION | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | BOILER RECONSTRUCTION | 2022 | 1200 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112THEV | 8 EAST THIRD STREET ELEVATOR REHABILITATION | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | 8 EAST THIRD STREET ELEVATOR REHABILITATION | 2022 | 748 | 0 | 68 | 680 | 0 | 0 | 0 | 0 | 748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH112THFC | 8 EAST THIRD ST SHELTER FACADE AND STAIRS | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | RECONSTRUCT FACADE AND STAIRS | 2022 | 1040 | 80 | 760 | 1200 | 0 | 0 | 0 | 0 | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115CTBU | 78 CATHERINE STREET - BATHROOM UPGRADE | SHELTERS FOR HOMELESS FAMILIES | 303 | HH-0115 |  |  | DESIGN AND CONSTRUCTION SERVICES RE THE RENOVATION OF BATHROOMS AT THE CATHERINE STREET FAMILY SHELTER | 2022 | 7350 | 5565.52 | 1100 | 0 | 0 | 0 | 0 | 0 | 6665.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115CTEF | CATHERINE STREET ELECTRICAL UPGRADE | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 |  |  | CATHERINE STREET ELECTRICAL AND FIRE SAFETY UPGRADE | 2022 | 3950 | 300 | 0 | 1050 | 2600 | 0 | 0 | 0 | 3950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115JCFA | JENNIE CLARKE BACKFLOW PREVENTER | SHELTERS FOR HOMELESS FAMILIES | 311 | HH-0115 |  |  | 179 - 191 EAST 100TH STREET - FA, PA SYS, BACKFLOW PREVENTION | 2022 | 750 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115REBO | REGENT BOILER | SHELTERS FOR HOMELESS FAMILIES | 307 | HH-0115 |  |  | REGENT BOILER | 2022 | 1950 | 150 | 900 | 900 | 0 | 0 | 0 | 0 | 1950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RECL | REGENT CEILINGS | SHELTERS FOR HOMELESS FAMILIES | 307 | HH-0115 |  |  | REGENT CEILINGS | 2022 | 4707 | 85 | 0 | 0 | 0 | 0 | 0 | 1758 | 1843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HH115RFRE | REGENT FAMILY RESIDENCE LIFE SAFETY UPGRADE, FIRE SAFETY | SHELTERS FOR HOMELESS FAMILIES | 307 | HH-0115 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ELECTRICAL UPGRADE THROUGHOUT THE BUILDING AND TO ADDRESS ANY CODE VIOLATIONS AT THE REGENT FAMILY RESIDENCE. | 2022 | 2174 | 2650.71 | 1200 | 0 | 0 | 0 | 0 | 0 | 3850.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHCN007 | INSTALLATION OF BACKUP GENERATOR | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-D025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | INSTALLATION OF A BACKUP GENERATOR | 2022 | 301 | 0 | 0 | 0 | 0 | 542 | 0 | 0 | 542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHMNEW1 | PROJECT RENEWAL - RENOVATE FT. WASH. ARMORY | SHELTERS FOR HOMELESS INDIVIDUALS | 312 | HH-M112 |  |  | PROJECT RENEWAL - RENOVATE FT. WASH. ARMORY | 2022 | 101 | 0 | 0 | 76 | 0 | 0 | 0 | 0 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHNC005 | KITCHEN RENOVATION AT 8 EAST THIRD STREET HOMELESS SHELTER | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-D025 |  |  | KITCHEN RENOVATION AT 8 EAST THIRD STREET HOMELES SHELTER | 2022 | 378 | 0 | 378 | 0 | 0 | 0 | 0 | 0 | 378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HHNC006 | FORT WASHINGTON ARMORY - ENTRYWAY REPAIR | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-D025 |  |  | FORT WASHINGTON ARMORY - ENTRYWAY REPAIR | 2022 | 200 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | HLCN014 | PROJECT RENEWAL , INC. - NEW PROVIDENCE BACKUP GENERATOR | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-D112 |  |  | PROJECT RENEWAL , INC. - NEW PROVIDENCE BACKUP GENERATOR | 2022 | 275 | 0 | 0 | 0 | 0 | 275 | 0 | 0 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS1 | Solar PV system - HELP SEC at 111 Sunken Garden Loop | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 301 | PU-0025 |  |  | SOLAR PV SYSTEM - HELP SEC AT 111 SUNKEN GARDEN LOOP | 2022 | 2936 | 0 | 2711 | 0 | 0 | 0 | 0 | 0 | 2711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 072 | DEPARTMENT OF CORRECTION | C75WTRMN | Replace Water Mains on Rikers Island | BUILDING SYSTEMS AND INFRASTRUCTURE | 300 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACE DOMESTIC WATER AND FIRE MAINS AT RIKERS ISLAND. | 2022 | 6175 | 410.36 | 500 | 0 | 0 | 4465 | 0 | 0 | 5375.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 096 | HUMAN RESOURCES ADMINISTRATION | HR2560LAC | 60 Lafayette Street Construction | SOCIAL SERVICES BUILDINGS |  | HR-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2022 | 750 | 0 | 0 | 0 | 0 | 0 | 255 | 0 | 255 | 0 | 0 | 0 | 0 | 0 | 495 | 0 | 495
20220309 | MANHATTAN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25CHRYC | 115 Chrystie Street Construction | SOCIAL SERVICES BUILDINGS |  | HR-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2022 | 1701 | 0 | 0 | 500 | 1165 | 0 | 0 | 0 | 1665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25E162C | 109 East 16th Street Construction | SOCIAL SERVICES BUILDINGS |  | HR-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2022 | 5245 | 0 | 715 | 0 | 0 | 0 | 0 | 0 | 715 | 0 | 355 | 0 | 0 | 0 | 0 | 0 | 355
20220309 | MANHATTAN | 096 | HUMAN RESOURCES ADMINISTRATION | HR25W125C | 132 W 125th St Construction | SOCIAL SERVICES BUILDINGS |  | HR-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  |  | 2022 | 4609 | 377.68 | 271 | 0 | 0 | 0 | 0 | 0 | 648.68 | 345.16 | 248 | 0 | 0 | 0 | 0 | 0 | 593.16
20220309 | MANHATTAN | 125 | DEPARTMENT FOR THE AGING | AGCBCOV | CARTER BURDEN/LEONARD COVELLO | DEPARTMENT FOR THE AGING BUILDING RECONSTRUCTION | 311 | AG-M001 |  |  | CARTER BURDEN/LEONARD COVELLO SENIOR PROGRAM KITCHEN RELOCATION | 2022 | 98 | 0 | 0 | 0 | 98 | 0 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 125 | DEPARTMENT FOR THE AGING | AGCBURDEN | LEONARD COVELLO Kitchen Renovation | DEPARTMENT FOR THE AGING BUILDING RECONSTRUCTION | 311 | AG-D001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SEPT 17 PLAN 400K FOR KITCHEN RENOVATION | 2022 | 400 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 125 | DEPARTMENT FOR THE AGING | HAM14CRSR | CARVER HOUSES SENIOR CENTER COMPUTER LAB | DEPARTMENT FOR THE AGING BUILDING RECONSTRUCTION | 311 | AG-D001 |  |  | INSTALL A COMPUTER LAB AT THE SENIOR CENTER | 2022 | 100 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | ACEDCA434 | DCLA: AMNH - Lighting Control Upgrade, Rd 4 & Garage Rd 5 | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 307 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REMOVAL AND REPLACEMENT OF LIGHTING CONTROLS SYSTEMS IN PUBLIC SPACESFOR 10 EXHIBIT HALLS. THESE UPGRADES WILL PROVIDE CONTROLS NECESSARY TO AUTOMATICALLY TURN OFF LIGHTING FOR EIGHT HOUR PERIODS EACH DAY. | 2022 | 583 | 0 | 0 | 0 | 0 | 710 | 0 | 0 | 710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022AAOA | MMA- Metropolitan Museum AAOA Gallery | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-0467 PV-D022 PV-M022 PV-0022 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RENOVATION TO AAOA GALLERIES AT METROPOLITAN MUSEUM OF ART. | 2022 | 5900 | 0 | 0 | 1000 | 0 | 7800 | 5000 | 0 | 13800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022ANEG | MMA -Ancient Near East Gallery Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-D022 PV-M022 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MMA -ANCIENT NEAR EAST GALLERY RENOVATION | 2022 | 75 | 0 | 0 | 0 | 3585 | 75 | 0 | 0 | 3660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV022-SKY | MMA - Metropolitan Museum Skylight Replacement for A, B, C W | ESSENTIAL RECONSTRUCTION OF FACILITIES | 308 | PU-0025 PV-M022 PV-0022 PV-D022 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | METROPOLITAN MUSEUM OF ART: SKYLIGHT REPLACEMENT OF WINGS A, B & C. | 2022 | 19738 | 0 | 6114 | 0 | 31410 | 0 | 0 | 0 | 37524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV034GRUV | AMNH - Gilder Center Green Bldg. | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-0034 PV-D034 PV-M034 |  |  | CONSTRUCTION | 2022 | 2350 | 0 | 0 | 10000 | 0 | 2350 | 8000 | 0 | 20350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV034-INF | AMNH - Security & Infrastructure Upgrade | ESSENTIAL RECONSTRUCTION OF FACILITIES | 307 | PV-D034 PV-M034 PU-0025 PV-0034 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CENTRAL PARK WEST AT 79TH STREET, NEW YORK, NY | SECURITY AND INFRASTRUCTURE UPGRADE | 2022 | 1803 | 0 | 0 | 0 | 3275 | 4202 | 1100 | 0 | 8577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV101-EDU | MJH - Museum Education Wing | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-D101 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BUILDING RENOVATION | 2022 | 1050 | 0 | 0 | 0 | 0 | 1050 | 0 | 0 | 1050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV101HVAC | MJH - Museum HVAC | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-M101 PV-D101 PV-0101 |  |  | MJH - MUSEUM HVAC | 2022 | 1150 | 0 | 0 | 0 | 0 | 7516 | 0 | 0 | 7516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV219-HLD | MCC - Fresh Air Intake | ESSENTIAL RECONSTRUCTION OF FACILITIES | 304 | PV-0467 |  |  | ADDED FRESH AIR INTAKE TAS NEEDED FOR ONGOING RENOVATION | 2022 | 550 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV241BOIL | MCNY - Boiler Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 311 | PV-D241 PV-0241 PU-0025 PV-0467 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 1220 5TH AVE, MANHATTAN NY | BOILER SYSTEM REPLACEMENT. | 2022 | 1512 | 0 | 0 | 2211 | 0 | 60 | 0 | 0 | 2271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV279ACON | NYCC - NY City Center Chiller Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-M279 PV-D279 PV-0279 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NYCC - NY CITY CENTER CHILLER REPLACEMENT | 2022 | 650 | 0 | 0 | 0 | 0 | 2123 | 0 | 0 | 2123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV289-DEL | NYSF - DELACORTE Theater Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 307 | PV-M289 PV-D289 PV-0289 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NYSF - DELCORTE THEATER RENOVATION | 2022 | 9900 | 0 | 0 | 0 | 0 | 22581 | 19120 | 0 | 41701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467HOLD | FUND BALANCE 467 EX | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-0467 |  |  | EXCESS FUNDS FROM VARIOUS PROJECTS | 2022 | 1919 | 0 | 0 | 0 | 0 | 0 | 2459 | 0 | 2459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV467PCTS | DCA PFA - Percent for Art Conservation of Public Art | ESSENTIAL RECONSTRUCTION OF FACILITIES | 301 302 | PV-0467 |  |  | CONSERVATION | 2022 | 1992 | 0 | 0 | 0 | 0 | 0 | 1992 | 0 | 1992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV475ROOF | NYST - NYC Ballet Roof Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-0475 PV-D475 PV-M475 PU-0025 PV-0467 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DAVID H. KOCH THEATER ROOF REPLACEMENT | 2022 | 4178 | 0 | 0 | 3481 | 0 | 708 | 6939 | 0 | 11128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503FACD | CH - CARNEGIE HALL Historic Facade Restoration | ESSENTIAL RECONSTRUCTION OF FACILITIES | 305 | PV-D503 PV-0503 |  |  | CONSTRUCTION | 2022 | 2500 | 0 | 0 | 0 | 0 | 1250 | 1250 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV503SDWK | CH - Carnegie Sidewalk Restoration | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-M503 PV-0503 PV-D503 |  |  | CH - CARNEGIE SIDEWALK RESTORATION | 2022 | 2025 | 0 | 0 | 4006 | 0 | 0 | 0 | 0 | 4006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV788-TER | 122C - 122 Community Center Roof Terrace | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-M788 PV-D788 PV-0788 |  |  | 122 COMMUNITY CENTER ROOF TERRACE CONSTRUCTION | 2022 | 168 | 0 | 0 | 0 | 0 | 168 | 0 | 0 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 125THPDIM | 125th St & Park Ave - Pedestrian Improvements | MISCELLANEOUS | 300 | ED-D075 ED-0075 HW-0001M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 125TH & PARK AVE - EDC PUBLIC REALM PROJECT -- PEDESTRIAN IMPROVEMENTS ON 125TH STREET AND PARK AVENUE, AS PART OF EDC'S LARGER PUBLIC REALM PROJECT | 2022 | 1000 | 1604.53 | 730 | 0 | 0 | 0 | 0 | 0 | 2334.53 | 3749.7 | 450 | 0 | 0 | 0 | 0 | 0 | 4199.7
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 126STDEPO | 126th Street Depot | MISCELLANEOUS | 300 | ED-0075 |  |  | 126TH STREET DEPOT | 2022 | 30000 | 0 | 1000 | 4000 | 0 | 0 | 12500 | 12500 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 34STHELI | E. 34th Street Heliport Rehabilitation | MISCELLANEOUS | 301 306 308 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REHABILITATION OF SUB-STRUCTURE | 2022 | 1900 | 5554.23 | 405 | 0 | 0 | 0 | 0 | 0 | 5959.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 8890PHA3 | Piers 88 & 90 Cluster Encapsulation Project Phase 3 | MISCELLANEOUS | 300 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PIERS 88 & 90 CLUSTER ENCAPSULATION PROJECT PHASE 3 | 2022 | 10000 | 8054.81 | 638 | 306 | 0 | 0 | 1000 | 0 | 9998.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 8THSTREET | FA - Village Alliance - Reconstruction of St. & Sidewalks | COMMERCIAL DEVELOPMENT | 302 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | MANHATTAN | VILLAGE ALLIANCE - RECONSTRUCTION OF STREET AND SIDEWALKS | 2022 | 1001 | 199.88 | 0 | 0 | 0 | 0 | 0 | 0 | 199.88 | 156.76 | 0 | 429 | 0 | 0 | 0 | 0 | 585.76
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | 911MEMOR | 9/11 Postcard Memorial Electrical Improvements | MISCELLANEOUS | 300 | ED-0075 |  |  | ELECTRICAL IMPROVEMENTS AT THE 9/11 POSTCARD MEMORIAL | 2022 | 970 | 0 | 970 | 0 | 0 | 0 | 0 | 0 | 970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | AHGREEN | Andrew Haswell Green Park - Phase 2B | MISCELLANEOUS | 300 | P-1018 P-0245M ED-0075 ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ANDREW HASWELL GREEN PARK - PHASE 2B | 2022 | 25603 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 8000 | 3544.85 | 22057 | 0 | 0 | 0 | 0 | 0 | 25601.85
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | AMSTCORNR | LPCA Redevelopment Final Phase -Amsterdam Corner | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 | PV-0489 PV-M489 PV-D489 |  |  | LPCA REDEVELOPMENT FINAL PHASE -AMSTERDAM CORNER | 2022 | 8398 | 0 | 0 | 8398 | 0 | 0 | 0 | 0 | 8398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CMPRENO | Chinatown Manpower Project - 4th Floor Renovation | MISCELLANEOUS CONSTRUCTION | 300 303 | PW-M077 ED-D075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CHINATOWN MANPOWER PROJECT - 4TH FLOOR RENOVATION | 2022 | 546 | 0 | 0 | 273 | 273 | 0 | 0 | 0 | 546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | CWFSFERY2 | New York City Ferry - Infrastructure | WATERFRONT DEVELOPMENT | 300 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CITYWIDE FERRY SERVICE - NEW VESSEL PURCHASE & UPGRADE | 2022 | 84400 | 144028.5 | 12636 | 0 | 0 | 0 | 25000 | 40000 | 221664.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | DMECODOCK | Dyckman Pier -- Ferry Access to Eco-Dock | MISCELLANEOUS | 300 | ED-D075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DYCKMAN PIER -- FERRY ACCESS TO ECO-DOCK | 2022 | 500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | FFMSHREDR | Fulton Fish Market - Pallet Shredder & Backup Power Bank | MISCELLANEOUS | 300 | ED-D408 |  |  | PURCHASE OF PALLET SHREDDER AND BACKUP POWER BANK FOR NEW FULTON FISHMARKET | 2022 | 820 | 0 | 0 | 0 | 820 | 0 | 0 | 0 | 820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | FFREEDOMS | Four Freedoms Park Utilities | MISCELLANEOUS | 300 | ED-D075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EDC/RIOC - PARK UTILITIES -- CONNECTING FOUR FREEDOMS PARK TO POTABLEWATER UTILITIES, INSTALLING A FULLY ACCESSIBLE WATER STATION. | 2022 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISB301 | Governors Island - Building 301 Renovation | MISCELLANEOUS |  | ED-0831 |  |  | GOVERNORS ISLAND - BUILDING 301 RENOVATION - STABILIZATION AND BUILD-OUT OF BUILDING LOCATED IN THE HISTORIC DISTRICT ON THE NORTH ISLAND. | 2022 | 4000 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBL20 | Governors Island - Building 20 Nolan Park Renovation | MISCELLANEOUS |  | ED-0831 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BUILDING 20 NOLAN PARK RENOVATION | 2022 | 2727 | 588 | 5583 | 0 | 0 | 0 | 0 | 0 | 6171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBLD2 | Governors Island Building Stabilization | MISCELLANEOUS | 300 301 | ED-0831 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BUILDING STABILIZATION | 2022 | 4951 | 2306.16 | 1575 | 0 | 0 | 0 | 0 | 0 | 3881.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBLDG | Governors Island Building Stabilization | MISCELLANEOUS | 300 | ED-0831 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GOVERNORS ISLAND BUILDING STABILIZATION | 2022 | 9435 | 5797.75 | 529 | 0 | 0 | 0 | 0 | 0 | 6326.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBLNP | Governor's Island Building Stabilization - Nolan Park | MISCELLANEOUS |  | ED-0831 |  |  | RENOVATION OF A HISTORIC BUILDING IN NOLAN PARK ON GOVERNORS ISLAND. | 2022 | 5347 | 0 | 0 | 5347 | 0 | 0 | 0 | 0 | 5347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBMB2 | Governors Island BMB Slip5/6 Pile Cluster&Slip 6/7FenderRack | MISCELLANEOUS | 300 301 | ED-0075 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS |  | BMB SLIP 5/6 PILE CLUSTER AND SLIP 6/7 FENDER RACK | 2022 | 6031 | 2308.24 | 771 | 200 | 0 | 0 | 0 | 0 | 3279.24 | 1919.91 | 3012 | 0 | 0 | 0 | 0 | 0 | 4931.91
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISBMBG | Governors Island BMB SLIP 6 & SLIP 7 GANTRIES | MISCELLANEOUS | 300 301 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REHABILITATION OF THE GANTRY TOWERS AT SLIP 6 AND SLIP 7 AT THE BATTERY MARITIME BUILDING, WHICH PROVIDES FERRY SERVICE TO GOVERNORS ISLAND. | 2022 | 1206 | 983.76 | 281 | 0 | 0 | 0 | 0 | 0 | 1264.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISELE2 | Governors Island Electric Projects | MISCELLANEOUS |  | ED-0831 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GOVERNORS ISLAND - DESIGN PORTION OF THE FOLLOWING PROJECTS :NORTH ISLAND ELECTRIC - SECONDARY SYSTEM UPGRADES (GOVISNIEL),; ISLAND WIDE BACK-UP POWER (GOVISGNTR); NORTH ISLAND LIGHTING (GOVISNILI), ISLAND PERIMETER LIGHTING (GOVISPRLI). $1,014,084 TRANSFER FROM THESE PJIDS DURING FY19 PRELIMINARY PLAN. | 2022 | 17000 | 5389.24 | 1610 | 10000 | 0 | 0 | 0 | 0 | 16999.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISESUB | Governors Island - Electrical Substation | MISCELLANEOUS |  | ED-0831 |  |  | GOVERNORS ISLAND ELECTRICAL SUBSTATION - TO PROVIDE ELECTIRCAL SERVICE FOR EXISTING AND FUTURE DEMAND. | 2022 | 27500 | 0 | 0 | 2500 | 25000 | 0 | 0 | 0 | 27500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISLIMA | Governors Island - Lima Pier Reconstruction | MISCELLANEOUS |  | ED-0831 |  |  | GOVERNORS ISLAND - LIMA PIER RECONSTRUCTION | 2022 | 5180 | 0 | 0 | 500 | 4680 | 0 | 0 | 0 | 5180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISLND2 | Governors Island Infrastructure Improvements | MISCELLANEOUS | 301 | ED-0831 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION/UPGRADE OF INFRASTRUCTURE ON GOVERNORS ISLAND. | 2022 | 31390 | 0 | 0 | 10000 | 50000 | 40885 | 4124 | 22905 | 127914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISPUMP | Governors Island Sewage Pump House | MISCELLANEOUS |  | ED-0831 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GOVERNOR ISLAND SEWAGE PUMP HOUSE | 2022 | 1500 | 3014.54 | 191 | 0 | 0 | 0 | 0 | 0 | 3205.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISSSNE | Governors Island Soissons Dock East Slip | MISCELLANEOUS |  | ED-0831 |  |  | SOISSONS DOCK EAST SLIP - LIFT BRIDGE REHABILITATION - GOVERNORS ISLAND | 2022 | 2320 | 200.22 | 1670 | 0 | 0 | 0 | 0 | 0 | 1870.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISTNGO | Governors Island - Tango Pier | MISCELLANEOUS |  | ED-0831 |  |  | GOVERNORS ISLAND - TANGO PIER - DEMOLITION OF WATERFRONT PIER. | 2022 | 3576 | 0 | 414 | 3162 | 0 | 0 | 0 | 0 | 3576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISUNUT | Governors Island Underground Utilities | MISCELLANEOUS |  | ED-0831 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GOVERNORS ISLAND UNDERGROUND UTILITIES - NORTH ISLAND, HISTORIC DISTRICT, INSTALLATION. | 2022 | 10000 | 2616.57 | 21037 | 3000 | 0 | 0 | 0 | 0 | 26653.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISWLL2 | Governors Island Seawall Rehabilitation | MISCELLANEOUS | 300 | ED-0831 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REHABILITATION OF THE SEAWALL AT GOVERNORS ISLAND | 2022 | 7452 | 0 | 0 | 1000 | 3875 | 0 | 0 | 0 | 4875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | GOVISWTR2 | Governors Island Potable Water System | MISCELLANEOUS | 300 | ED-0831 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REHABILITATION OF THE POTABLE WATER SYSTEM ON GOVERNORS ISLAND | 2022 | 2000 | 0 | 0 | 3500 | 15000 | 0 | 0 | 0 | 18500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HARLMPIER | Harlem Area Piers & Bulkhead Stabilization | WATERFRONT DEVELOPMENT | 309 | ED-0401 P-C018 ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  |  | 2022 | 14619 | 7702.79 | 23 | 0 | 0 | 0 | 0 | 0 | 7725.79 | 7593.99 | 243 | 0 | 0 | 0 | 0 | 63 | 7899.99
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HBGRWESPN | Manhattan Greenway - UN Esplanade | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 300 | HB-0215 |  | MANHATTAN GREENWAY - UN ESPLANADE | MANHATTAN GREENWAY - UN ESPLANADE | 2022 | 153000 | 0 | 0 | 15000 | 0 | 0 | 138000 | 0 | 153000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HBMA4501B | 33rd Street West of 11th Avenue (Hudson Yards) | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 300 | HB-0215 HW-0001M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REGARDING OF 33RD STREET WEST OF 11TH AVENUE (HUDSON YARDS) LOCATION:33RD STREET BETWEEN 11TH AND 12TH AVENUES | 2022 | 100000 | 2830.1 | 2830 | 0 | 0 | 94340 | 0 | 0 | 100000.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HL82PHL | DOHMH PHL BUILDING CONSTRUCTION | LABORATORIES |  | HL-0082 PU-0025 |  |  | ESTIMATE | 2022 | 177527 | 51862.17 | 206932 | 292429 | 60010 | 60010 | 0 | 0 | 671243.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | HWD10214 | Hudson Sq Streetscape Improvements | PRIMARY STREET RECONSTRUCTION | 300 302 | HW-D102 HW-0001M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | HUDSON SQ STREETSCAPE IMPROVEMENTS | HUDSON SQ STREETSCAPE IMPROVEMENTS | 2022 | 11080 | 6000 | 1001 | 0 | 0 | 0 | 0 | 0 | 7001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQPLZ | La Marqueta Plaza Rehabilitation | NEIGHBORHOOD REVITALIZATION | 300 | ED-D075 ED-D408 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LA MARQUETA PLAZA REHABILITATION | 2022 | 10500 | 7536.1 | 225 | 9 | 1532 | 0 | 1199 | 0 | 10501.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LAMARQUE4 | La Marqueta Building 4 Exterior Envelope Rehab | MISCELLANEOUS | 300 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LA MARQUETA BUILDING #4 | 2022 | 1400 | 155.44 | 0 | 0 | 119 | 1125 | 0 | 0 | 1399.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LCNPARK | Lower Concourse Park | MISCELLANEOUS | 300 | ED-0384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LOWER CONCOURSE PARK | 2022 | 35408 | 3561.66 | 5873 | 0 | 0 | 0 | 25974 | 0 | 35408.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LMCRFIDI | FIDI Seaport resilient waterfront | MISCELLANEOUS | 300 | ED-0075 |  |  | FIDI SEAPORT RESILIENT WATERFRONT | 2022 | 183000 | 0 | 9000 | 10000 | 62000 | 9000 | 20000 | 0 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16125 | 125th St: Interior and Exterior Comprehensive Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 | LN-0008 LN-D008 LN-M001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INTERIOR AND EXTERIOR COMPREHENSIVE RENOVATION | 2022 | 20000 | 1174.75 | 24365 | 2551 | 0 | 0 | 0 | 0 | 28090.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16FWT | FORT WASHINGTON: MAJOR RENOVATION | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 | LN-0008 LN-D008 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MAJOR RENOVATION | 2022 | 20000 | 3891.28 | 23972 | 2776 | 0 | 0 | 0 | 0 | 30639.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-COLUM | New York City Therapeutic Validation Center Space | MISCELLANEOUS | 300 | ED-0075 |  |  | NEW YORK CITY THERAPEUTIC VALIDATION CENTER SPACE | 2022 | 9000 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-PRI | Life Sci Pandemic Response Institute | MISCELLANEOUS | 300 | ED-0075 |  |  | LIFE SCI PANDEMIC RESPONSE INSTITUTE | 2022 | 20000 | 0 | 5000 | 5000 | 5000 | 5000 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-ROCKU | Multi-Institutional Translational Center | MISCELLANEOUS | 300 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MULTI-INSTITUTIONAL TRANSLATIONAL CENTER | 2022 | 9000 | 0 | 0 | 0 | 0 | 0 | 9000 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-STEM | New York City Translational Stem Cell Research Facility | MISCELLANEOUS | 300 | ED-0075 |  |  | NEW YORK CITY TRANSLATIONAL STEM CELL RESEARCH FACILITY | 2022 | 6500 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MANHGREEN | Manhattan Greenway | COMMUNITY DEVELOPMENT | 300 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MANHATTAN GREENWAY | 2022 | 100000 | 83051.01 | 50000 | 0 | 28279 | 11711 | 0 | 0 | 173041.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTFEND | MCT PIER 90 FENDERING | MISCELLANEOUS | 300 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MCT PIER 90 FENDERING | 2022 | 8000 | 0 | 1000 | 0 | 0 | 0 | 0 | 7000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MCTROOFSV | MCT Piers & Viaduct Roofs | MISCELLANEOUS | 300 | ED-0409 |  |  | ROOF REHAB | 2022 | 51100 | 0 | 2100 | 0 | 9000 | 10000 | 0 | 30000 | 51100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | MECAFIT | MECA FITNESS CENTER RENOVATION--FITNESS CENTER RENOVATION | MISCELLANEOUS | 300 | PW-D005 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MECA FITNESS CENTER RENOVATION--FITNESS CENTER RENOVATION | 2022 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-3HRGL | NDF - Harlem River Greenway Link - New Park Development | MISCELLANEOUS | 300 | ED-0384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HARLEM RIVER GREENWAY LINK - NEW PARK DEVELOPMENT | 2022 | 83000 | 3792.52 | 0 | 0 | 0 | 73915 | 0 | 5293 | 83000.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-EHWF1 | NDF - East Harlem SBS Workforce1 Center | NEIGHBORHOOD REVITALIZATION | 300 | ED-0384 |  |  | NDF - EAST HARLEM SBS WORKFORCE1 CENTER | 2022 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-INWCC | NDF - Inwood Cultural Center | NEIGHBORHOOD REVITALIZATION | 300 | ED-0384 |  |  | NDF - INWOOD CULTURAL CENTER | 2022 | 15000 | 0 | 0 | 5000 | 0 | 0 | 0 | 10000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-LAMAR | La Marqueta Redevelopment | MARKET DEVELOPMENT | 300 | ED-0384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LA MARQUETA REDEVELOPMENT | 2022 | 25000 | 0 | 0 | 1000 | 0 | 0 | 0 | 24000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-NWOOD | NDF - Inwood Greenway and New Parks Development | MISCELLANEOUS | 300 | ED-0384 ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INWOOD GREENWAY AND NEW PARKS CONSTRUCTION | 2022 | 50000 | 0 | 7458 | 0 | 0 | 60000 | 60000 | 164542 | 292000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NONTDW | Nontraditional Employment for Women - Renovation of HQ | MISCELLANEOUS | 300 | ED-D075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NONTRADITIONAL EMPLOYMENT FOR WOMEN - RENOVATIONS OF CITY-OWNED HEADQUARTERS | 2022 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NR COGEN | DEP: North River Cogeneration Plant, Hudson River Greenway | MISCELLANEOUS | 300 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NORTH RIVER COGENERATION PLANT | 2022 | 5432 | 1888 | 1237 | 0 | 0 | 0 | 0 | 0 | 3125 | 2307 | 0 | 0 | 0 | 0 | 0 | 0 | 2307
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | NYCFBARGE | New York City Ferry - Barge Expansion | MISCELLANEOUS | 300 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW YORK CITY FERRY - BARGE LANDING EXPANSION | 2022 | 29633 | 19862.46 | 29089 | 16513 | 5000 | 862 | 5238 | 0 | 76564.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-301BATW | Battery Park - Wharf | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | PU-0200 RE-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF MANHATTAN | BATTERY PARK WHARF | 2022 | 4300 | 4373.65 | 21 | 911 | 0 | 0 | 0 | 0 | 5305.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-309RVP2 | RIVERSIDE PARK 79 ST BOAT BASIN: C DOCK | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-1018 PU-0200 |  | RIVERSIDE PARK 79 ST BOAT BASIN: C DOCK | RIVERSIDE PARK | 2022 | 60938 | 4091.04 | 5585 | 0 | 0 | 51262 | 0 | 0 | 60938.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3ERE22J | East River Esplanande phase 4+ | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INSPECTIONS COMPLETED IN 2012 (AECOM) AND 2018 (PENNMAX) VIA EDC WFMMS INSPECTION PROGRAM. PHASE 4 CONTINUES WORK OF PRIOR PHASES, ADDRESSING ESPLANADE AREAS RATED AS CRITICAL. AREA 1 ADDRESSES 94TH TO 107TH($73.8M); AREA 2 ADDRESSES 118TH TO 124TH ($197.8M). THESE SECTIONS ADJOIN PHASES 2 & 3 AS WELL AS ESPLANADE WORK BEING PERFORMED BY EDC TO NORTH. THESE SECTIONS OF EESPLANADE ARE DISPLAYING PROGRESSIVE STRUCTURAL FAILURE WITH EXPANSIVE DETERIORATION OF SUPPORTING TIMBER SUBSTRUCTURES. COLLAPSE OF VARIOUS SECTIONS IS A NEAR-TERM POSSIBILITY. DPR HAS MADE PARTIAL AS WELL AS FULL PEDESTRIAN CLOSURES IN AREAS. PLEASE NOTE FUNDING REQUEST IS IN FY20 DOLLARS AND DOES NOT INCLUDE ESCALATION. | 2022 | 284592 | 0 | 29507 | 0 | 0 | 0 | 255085 | 0 | 284592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HIGHLL | FRIENDS OF THE HIGH LINE-LIFE SAFETY UPGRADES & CIRCULATION | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-0245M P-M245 |  |  | MADISON SQ. PARK ETERNAL LIGHT FLAGSTAFF LANDSCAPE, MAHATTAN | 2022 | 617 | 0 | 5650 | 0 | 0 | 0 | 0 | 0 | 5650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HILIN3 | Highline Phase 3 | MISCELLANEOUS | 304 | P-1326 P-1018 |  |  | HIGHLINE PHASE 3 | 2022 | 11000 | 10369.44 | 463 | 0 | 0 | 0 | 0 | 0 | 10832.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3HRP132 | Harlem River Park 132-135 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | PU-0200 ED-0075 P-0501 |  | HARLEM RIVER PK 132-135 ST. | HARLEM RIVER PK 132-135 ST. | 2022 | 20216 | 8513.42 | 36539 | 103000 | 847 | 8759 | 57000 | 100000 | 314658.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | P-3RETWAL | Seawall and Henry Hudson Parkway | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-1018 P-1515 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | MANHATTAN | E. RIVER PARK RETAINING WALLS | 2022 | 3286 | 4232.07 | 344 | 0 | 0 | 0 | 0 | 0 | 4576.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PASSSHIP4 | Manhattan Cruise Terminal - Viaduct Concrete Rehabilitation | WATERFRONT DEVELOPMENT | 304 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | NEW YORK, NEW YORK 10019 | MANHATTAN CRUISE TERMINAL - VIADUCT CONCRETE REHABILITATION | 2022 | 6000 | 5648.26 | 0 | 0 | 0 | 0 | 350 | 0 | 5998.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36 | Pier 36 Structural Rehab | GARAGES AND FACILITIES | 303 | PU-0200 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CAPITAL REHAB/REPLACEMENT OF PILES, PILE CAPS, SLAB, TOPPING | 2022 | 108594 | 0 | 28594 | 0 | 0 | 80000 | 0 | 0 | 108594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER36STR | Pier 36 Structural Rehab | GARAGES AND FACILITIES | 303 | PU-0200 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STRUCTURRAL REHAB | 2022 | 13630 | 8371.67 | 5259 | 0 | 0 | 0 | 0 | 0 | 13630.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIER42CNT | Pier 42 and East River Park Connector Program | MISCELLANEOUS | 300 | ED-0075 P-1018 SE-0002M P-0245M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PIER 42 | 2022 | 23890 | 8609.27 | 9921 | 14628 | 0 | 0 | 0 | 0 | 33158.27 | 5333.24 | 13407 | 0 | 0 | 0 | 0 | 0 | 18740.24
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIERS35N6 | Pier 35 & 36 Substructure Rehabilitation | MISCELLANEOUS | 300 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PIER 35 & 36 SUBSTRUCTURE REHABILITATION | 2022 | 2000 | 704.1 | 1295 | 0 | 0 | 0 | 0 | 0 | 1999.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PIERS8890 | Piers 88 & 90 Cluster Encapsulation Project | MISCELLANEOUS | 301 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PIERS 88 & 90 CLUSTER ENCAPSULATION PROJECT | 2022 | 20500 | 19202.88 | 97 | 600 | 0 | 600 | 0 | 0 | 20499.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV279-STU | NYCC - New York City Center Studios Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-0279 PV-M279 PV-D279 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TBD | 2022 | 1350 | 1884.7 | 0 | 203 | 46 | 83 | 0 | 0 | 2216.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467-BEY | DCA PFA - Percent for Art Beyond Sims | ESSENTIAL RECONSTRUCTION OF FACILITIES | 301 302 | PV-0467 |  |  | MONUMENT | 2022 | 1000 | 184.99 | 815 | 0 | 0 | 0 | 0 | 0 | 999.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | PV467ELMB | ELM- El Museo - Gallery Environmental Stabilzation Project | ESSENTIAL RECONSTRUCTION OF FACILITIES | 311 | PV-D018 PV-0103 PV-0467 PV-D467 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 1230 FIFTH AVENUE, MANHATTAN, NY | MUSUEM GALLERY HVAC AND ENVIRONMENTAL STABILIZATION | 2022 | 2718 | 4120.2 | 213 | 0 | 0 | 458 | 0 | 0 | 4791.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSEDOCK | Roosevelt Island Dock | WATERFRONT DEVELOPMENT | 308 | ED-D401 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROOSEVELT ISLAND DOCK | 2022 | 500 | 0 | 0 | 0 | 0 | 698 | 0 | 0 | 698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSEOPER | Roosevelt Island Operating Corp - Blackwell House | MISCELLANEOUS | 308 | ED-D075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROOSEVELT ISLAND OPERATING CORP - BLACKWELL HOUSE -- ADDITION OF A PLAYGROUND AREA - BLACKWELL PARK - NORTHEAST CORNER. | 2022 | 144 | 0 | 0 | 0 | 144 | 0 | 0 | 0 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | ROOSISLTH | ROOSEVELT ISLAND LIGHTHOUSE | MISCELLANEOUS | 300 | ED-D075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROOSEVELT ISLAND LIGHTHOUSE RESTORATION FOR PUBLIC ACCESS--RESTORE THE LIGHTHOUSE OF ROOSEVELT ISLAND TO ALLOW FOR PUBLIC ACCESS. | 2022 | 700 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1101 | HHC FEMA PMP BELLEVUE: WATER REDUNDANCY A4 | MISCELLANEOUS | 300 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BELLEVUE | 2022 | 1316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3061.01 | 118 | 0 | 0 | 0 | 37 | 0 | 3216.01
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1104 | HHC FEMA Bellevue Hospital Center Flood Protection Barrier | MISCELLANEOUS | 300 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BELLEVUE | 2022 | 314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 503.66 | 0 | 0 | 142 | 0 | 0 | 0 | 645.66
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1108 | HHC FEMA BELLEVUE HOSPITAL PARKING LOT LIFTS | MISCELLANEOUS | 300 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HHC | 2022 | 2388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3377.53 | 0 | 0 | 0 | 2347 | 0 | 0 | 5724.53
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND1113 | HHC FEMA PMP BELLEVUE EXISTING VERTICAL TRANSPORTATION | MISCELLANEOUS | 300 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BELLEVUE HOSPITAL VERTICAL TRANSPORTATION | 2022 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14946.3 | 2064 | 800 | 0 | 0 | 2190 | 0 | 20000.3
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND3705 | METROPOLITAN HOSPITAL FLOOD MITIGATION SYSTEM | MISCELLANEOUS | 300 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | METRO HOSPITAL | 2022 | 7597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6759.2 | 80253 | 0 | 0 | 0 | 0 | 0 | 87012.2
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6701 | COLER : DESIGN & CONSTRUCTION FOR NEW GENERATOR | MISCELLANEOUS | 300 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COLER | 2022 | 11023 | 0 | 1847 | 0 | 0 | 0 | 0 | 0 | 1847 | 3859.71 | 11824 | 0 | 0 | 0 | 0 | 0 | 15683.71
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SAND6704 | COLER : AUDITORIUM DESIGN AND CONSTRUCTION MANAGEMENT | MISCELLANEOUS | 300 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COLER | 2022 | 918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1183.65 | 0 | 0 | 0 | 321 | 0 | 0 | 1504.65
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDCD15 | PIER 36 ELECTRICAL CONDUIT | POLICE FACILITIES | 300 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PIER36 ELECTRICAL CONDUIT | 2022 | 894 | 0 | 0 | 96 | 0 | 0 | 0 | 0 | 96 | 185.34 | 158 | 514 | 0 | 0 | 0 | 0 | 857.34
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDR2BRG | Construction of Flex Barges | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 300 | FA-0021 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCTION OF FLEX BARGES | 2022 | 12000 | 225 | 2775 | 0 | 0 | 0 | 0 | 0 | 3000 | 675 | 8325 | 0 | 0 | 0 | 0 | 0 | 9000
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRLE34 | FA Resiliency - Land Hardening E 34 street | MISCELLANEOUS | 300 | FA-0027 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FA RESILIENCY - LAND HARDENING E 34 STREET | 2022 | 1000 | 20.25 | 25 | 205 | 0 | 0 | 0 | 0 | 250.25 | 60.75 | 75 | 614 | 0 | 0 | 0 | 0 | 749.75
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGI | Governors Island Hurricane Sandy Repairs | MISCELLANEOUS | 300 301 | ED-0831 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CAPITAL PROJECTS EMERGENCY WORK AS A RESULT OF HURRICANE SANDY | 2022 | 3360 | 0 | 115 | 0 | 0 | 0 | 0 | 0 | 115 | 0 | 1563 | 0 | 0 | 0 | 0 | 0 | 1563
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDTGIEL | Governors Island - Hurricane Sandy Electrical Repairs | MISCELLANEOUS | 300 301 | ED-0075 | PROJECT DELAYED DUE TO SCHEDULING OF UTILITY WORK |  | TGI HURRICANE SANDY ELECTRICAL REPAIRS | 2022 | 6103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4937.15 | 2642 | 0 | 0 | 0 | 0 | 0 | 7579.15
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SBSRELOCA | SBS FY18 Relocation to 1 Liberty Plaza | MISCELLANEOUS | 300 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DESIGN AND CONSTRUCTION COSTS FOR SBS MOVE TO 1 LIBERTY PLAZA | 2022 | 20013 | 18028.89 | 3282 | 0 | 0 | 0 | 0 | 0 | 21310.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SKYPORT | Skyport Garage and Marina Rehabilitation | MISCELLANEOUS | 300 306 | ED-0409 ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SKYPORT GARAGE AND MARINA REHABILITATION | 2022 | 5000 | 1132.34 | 1508 | 0 | 0 | 0 | 3360 | 0 | 6000.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | SOLAR2 | CEC Stuyvesant Cove Inc.-Construction of Solar 2 | WATERFRONT DEVELOPMENT | 300 306 | PW-0077 ED-0075 ED-D401 ED-M075 ED-D075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CEC STUYVESANT COVE INC.-CONSTRUCTION OF SOLAR 2 | 2022 | 1500 | 1272.72 | 8500 | 1019 | 0 | 1837 | 0 | 0 | 12628.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | STUYBULK2 | Stuyvesant Cove Park Bulkhead Park Repair | WATERFRONT DEVELOPMENT | 306 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STUYVESANT COVE PARK, 18TH TO 23RD STREETS ALONG THE EAST RIVER | 2022 | 654 | 145.6 | 508 | 2200 | 0 | 0 | 0 | 0 | 2853.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | TINMARKET | New Market Tin Building Demolition | MISCELLANEOUS | 300 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW MARKET TIN BUILDING DEMOLITION | 2022 | 4331 | 787.16 | 7543 | 0 | 0 | 0 | 0 | 0 | 8330.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | W125TRANS | West 125th Street/Manhattanville | COMMERCIAL DEVELOPMENT | 300 309 | ED-0384 ED-0075 WM-0001 WM-0006 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WEST 125TH STREET/MANHATTANVILLE | 2022 | 32978 | 8341.16 | 1927 | 0 | 0 | 0 | 0 | 0 | 10268.16 | 14571.73 | 7637 | 0 | 0 | 0 | 0 | 0 | 22208.73
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WATERST | Water Street Corridor Streetscape Improvements | MISCELLANEOUS | 300 | ED-0075 HW-0001M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WATER STREET CORRIDOR STREETSCAPE IMPROVEMENTS | 2022 | 10000 | 2025.09 | 203 | 0 | 0 | 0 | 0 | 0 | 2228.09 | 16395.66 | 10615 | 0 | 0 | 0 | 0 | 0 | 27010.66
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WHARLMPK | West Harlem Piers Park | MISCELLANEOUS | 300 | P-D018 ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REPAIRS TO VARIOUS ASPECTS OF THE PARK | 2022 | 1162 | 0 | 300 | 0 | 0 | 0 | 0 | 862 | 1162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WL34STHL | EAST 34TH STREET HELIPORT SUBSTRUCTURE | MISCELLANEOUS | 300 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EAST 34TH STREET HELIPORT SUBSTRUCTURE | 2022 | 4057 | 0 | 811 | 0 | 0 | 1623 | 1623 | 0 | 4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 801 | DEPT OF SMALL BUSINESS SERVICES | WLWCLBWF | WATER CLUB WHARF | MISCELLANEOUS | 300 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WATER CLUB WHARF | 2022 | 4000 | 0 | 800 | 0 | 0 | 1600 | 1600 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | AGDLINADA | CONSTRUCTION TO CREATE TWO ADA COMPLIANT TOILETS | DEPARTMENT FOR THE AGING BUILDING RECONSTRUCTION | 309 | AG-D001 |  |  | ADA UPGRADE | 2022 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM02USCC | (WHITE) UNION SETTLEMENT ASSOC. - COMM. CTR. RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 300 311 | HA-0001 HA-D001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CREATION OF ADDITIONAL CLASSROOMS, PROGRAM SPACE AND RECONFIGURATION OF LOBBY TO MAKE THE CENTER MORE ACCESSIBLE. | 2022 | 1008 | 2460.89 | 764 | 0 | 0 | 0 | 0 | 0 | 3224.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM06CSCP | CLINTON SENIOR CENTER-PROJECT FIND | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | AG-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | KITCHEN REDESIGN AND COMPREHENSIVE UPGRADE, BATHROOM REDESIGN FOR ACCESSIBILITY AND IMPROVEMENTS, ARCHITECTURAL FEES. | 2022 | 495 | 1965.21 | 129 | 0 | 0 | 0 | 0 | 0 | 2094.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM06MHEL | Manhattanville Houses Elevators | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 309 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | UPGRADING OF ELEVATORS AT MANHATTANVILLE HOUSES | 2022 | 2970 | 2229.65 | 0 | 0 | 0 | 0 | 267 | 0 | 2496.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM08HSST | HENRY STREET SETTLEMENT - GOOD COMPANIONS SR CTR RENOVATIONS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-M001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION OF THE HENRY STREET SETTLEMENT | 2022 | 750 | 2098.67 | 51 | 0 | 0 | 0 | 0 | 0 | 2149.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM08RUHI | RUTGERS HOUSES ENERGY INITIATIVES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RUTGERS HOUSES HEATING UPGRADES | 2022 | 7790 | 4875.14 | 0 | 0 | 0 | 0 | 275 | 0 | 5150.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM11VLFA | VLADECK HOUSES- GOOD COMPANIONS/HENRY ST, FIRE ALARM SYSTEM | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INSTALL A FIRE ALARM SYSTEM AT GOOD COMPANIONS/ HENRY STREET SETTLEMENT | 2022 | 250 | 35.9 | 214 | 0 | 0 | 0 | 0 | 0 | 249.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM13CLEV | CLINTON HOUSES ELEVATOR REHABILITATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ELEVATOR REHABILITATION | 2022 | 5610 | 4452 | 0 | 0 | 0 | 0 | 648 | 0 | 5100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MNSE | METRO NORTH PLAZA SECURITY UPGRADES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SECURITY UPGRADES | 2022 | 100 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15ICNB | STANLEY ISAACS UPGRADE OF SENIOR AND YOUTH CENTER COMP. UPGR | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 308 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SENIOR AND YOUTH CENTER UPGRADES | 2022 | 680 | 1791.04 | 211 | 0 | 0 | 0 | 0 | 0 | 2002.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15JFSR | JEFFERSON SENIOR CENTER UPGRADE | DEPARTMENT FOR THE AGING BUILDING RECONSTRUCTION | 311 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | UPGRADE SENIOR CENTER | 2022 | 450 | 985 | 86 | 0 | 0 | 0 | 0 | 0 | 1071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15MOGD | METRO NORTH PLAZA DAY CARE CENTER PLAYGROUND RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DAY CARE CENTER RENOVATION | 2022 | 200 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM15WSPL | WASHINGTON HOUSES DAY CARE CENTER PLAYGROUND UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DAY CARE CENTER PLAYGROUND UPGRADE | 2022 | 200 | 220.27 | 37 | 0 | 0 | 0 | 0 | 0 | 257.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16AMBL | AMSTERDAM HOUSES BARRELS PLAYGROUND RENO | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 307 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BARRELS PLAYGROUND RENO | 2022 | 500 | 0 | 1050 | 0 | 0 | 0 | 0 | 0 | 1050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16AMUP | AMSTERDAM HOUSES NYCHA-UPGRADES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 307 | HA-D001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | AMSTERDAM HOUSES NYCHA-UPGRADES | 2022 | 50 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CRCC | CORSI HOUSES UPGRADES TO LAGUARDIA COMMUNITY CENTER | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-D001 HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CORSI HOUSES UPGRADES TO LAGUARDIA COMMUNITY CENTER | 2022 | 1000 | 0 | 3688 | 0 | 0 | 0 | 380 | 0 | 4068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16LGSC | 282 CHERRY STREET SECURITY CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 282 CHERRY STREET SECURITY CAMERAS | 2022 | 70 | 22 | 148 | 0 | 0 | 0 | 0 | 0 | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16LXCG | LEXINGTON HOUSES GROUND UPGRADE COMMUNITY GARDEN | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GROUNDS UPGRADE-COMMUNITY GARDEN | 2022 | 385 | 335.26 | 50 | 0 | 0 | 0 | 0 | 0 | 385.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM16UPGI | UNDERGROUND WATER AND FIRE DISTRIBUTION PIPING | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 300 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REPLACEMENT OF UNDERGROUND WATER AND FIRE DISTRIBUTION PIPING. | 2022 | 8000 | 7775.56 | 224 | 0 | 0 | 0 | 0 | 0 | 7999.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17CRGR | CORSI HOUSES SITTING AREA FOR SENIORS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATE GROUNDS TO PROVIDE A SITTING AREA FOR SENIORS | 2022 | 300 | 403.33 | 47 | 0 | 0 | 0 | 0 | 0 | 450.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17HRPL | HERNANDEZ PLAYGROUND RENOVATION AY 189 ALLEN STREET | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-M001 HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PLAYGROUND RENOVATION | 2022 | 165 | 983.92 | 353 | 0 | 0 | 0 | 0 | 0 | 1336.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17TBPL | TWO BRIDGES PLAYGROUND RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATE PLAYGROUND AT 286 SOUTH STREET | 2022 | 350 | 0 | 506 | 0 | 0 | 0 | 0 | 0 | 506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17THUR | ROOF WORK AT THURGOOD MARSHALL HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 300 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROOF WORK AT THURGOOD MARSHALL HOUSES | 2022 | 2200 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17WGPA | WAGNER HOUSES PLAY AREA UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PLAY AREA UPGRADE | 2022 | 500 | 457.76 | 42 | 0 | 0 | 0 | 0 | 0 | 499.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM17WSCR | WSUR A Community Room Bathroom Installation | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 307 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INSTALL A BATHROOM IN THE COMMUNITY ROOM | 2022 | 140 | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18DIGV | DIGITAL VAN | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 300 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DIGITAL VAN | 2022 | 150 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ECGR | GROUNDS RENOVATION AT ELLIOT - CHELSEA HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 304 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GROUNDS RENOVATION | 2022 | 500 | 310.64 | 189 | 0 | 0 | 0 | 0 | 0 | 499.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18GOBR | GOMPERS BOILER REPAIR | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 300 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GOMPERS BOILER REPAIR | 2022 | 2500 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18GRLM | GRANT HOUSES LAUNDROMAT RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 309 | HA-M001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GRANT HOUSES LAUNDROMAT RENOVATION | 2022 | 1100 | 1440 | 405 | 0 | 0 | 0 | 0 | 0 | 1845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18JOCC | JOHNSON COMM. CTR. STANLEY ISACCS NBRHD ROOF GLASS PANES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | JOHNSON COMM. CTR. STANLEY ISACCS NBRHD ROOF GLASS PANES & SURFACES | 2022 | 626 | 0 | 961 | 0 | 0 | 0 | 0 | 0 | 961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18LIPG | RENOVATION OF A PLAYGROUND AT LOWER EAST SIDE I INFILL | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION OF A PLAYGROUND AT LOWER EAST SIDE I INFILL | 2022 | 266 | 208.6 | 57 | 0 | 0 | 0 | 0 | 0 | 265.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18URBF | URBAN FARMS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 300 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | URBAN FARMS | 2022 | 120 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18VLPG | VLADECK HOUSES PLAYGROUND UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-M001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | VLADECK HOUSES PLAYGROUND. MADISON STREET BET. JACKSON AND GOUVERNEURSTREETS | 2022 | 500 | 498.49 | 202 | 0 | 0 | 0 | 0 | 0 | 700.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM18WAGD | WASHINGTON HOUSES MAKE PLAYGROUND ADA ACCESSIBLE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MAKE PLAYGROUND ADA ACCESSIBLE | 2022 | 500 | 664.77 | 135 | 0 | 0 | 0 | 0 | 0 | 799.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19AMEL | AMSTERDAM HOUSES ELEVATOR UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 307 | HA-0001 |  |  | UPGRADE ELEVATORS AT AMSTERDAM HOUSES | 2022 | 12392 | 449.82 | 10815 | 0 | 0 | 0 | 0 | 0 | 11264.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DCCR | DYCKMAN HOUSES COMMUNITY CENTER RAMP | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 312 | HA-D001 |  |  | FUNDING FOR COMMUNITY CENTER RAMP | 2022 | 300 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19DHPR | DYCKMAN HOUSES PLAYGROUND RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 312 | HA-D001 |  |  | FUNDING FOR DYCKMAN HOUSES PLAYGROUND RENOVATION | 2022 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19ECSC | ELLIOTT-CHELSEA HOUSES SECURITY CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 304 | HA-D001 |  |  | ELLIOTT SECURITY CAMERAS | 2022 | 250 | 31 | 219 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19FHSC | FULTON HOUSES SECURITY CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 304 | HA-D001 |  |  | SECURITY CAMERAS | 2022 | 250 | 31 | 219 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19GHEL | GRANT HOUSES EXTERNAL LIGHTING UPGRADES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 309 | HA-D001 |  |  | EXTERNAL LIGHTING UPGRADES | 2022 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19HBBR | HARBORVIEW COMMUNITY/SENIOR CENTER BATHROOM RENOVATIONS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION OF BATHROOMS IN COMMUNITY/SENIOR CENTER AT HARVORVIEW HOUSES | 2022 | 235 | 181.97 | 53 | 0 | 0 | 0 | 0 | 0 | 234.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19RCCK | RUTGERS COMMUNITY CENTER KITCHEN RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COMMUNITY CENTER KITCHENETTE, INCLUDING A NEW STOVE AND GAS LINES | 2022 | 120 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19RLTV | RANGEL HOUSES SAFE GROUNDS SECURITY INITIATIVE - CCTV | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 300 | HA-M001 |  |  | RANGEL HOUSES CCTV | 2022 | 200 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19STEL | ST NICHOLAS HOUSES ELEVATOR UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 310 | HA-0001 |  |  | UPGRADE ELEVATORS AT ST . NICHOLAS HOUSES | 2022 | 10973 | 678.3 | 9105 | 0 | 0 | 0 | 0 | 0 | 9783.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM19VLPR | VLADECK HOUSES: PLAYGROUND REPAVING | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-M001 |  |  | VLADECK HOUSES: PLAYGROUND REPAVING | 2022 | 600 | 557.23 | 43 | 0 | 0 | 0 | 0 | 0 | 600.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHNE | BARUCH HOUSES NEW ELEVATOR | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW ELEVATOR AT 72 COLUMBIA-BARUCH | 2022 | 1000 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CHHT | HEATING UPGRADES- CHELSEA HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 304 | HA-D001 |  |  | NYCHA - CHELSEA -- BURNERS AND CONTROLS ON 2 BOILERS NYCHA - CHELSEA -- REPLACE 4 INSTANTANEOUS HW PRODUCING SYSTEMS NYCHA - CHELSEA -- REPLACE THE BOILER ROOMS MAIN CONDENSATE RECEIVING TANK NYCHA - CHELSEA -- 1 NEW ZONE VALUE STATION WITH NEW PIPING AND CONTROL VALVES | 2022 | 920 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CSKR | CARVER HOUSES KITCHEN RENOVATION IN SENIOR CENTER | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-D001 |  |  | KITCHEN RENOVATION AT SENIOR CENTER-CARVER | 2022 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20CUSD | CARVER UNDERGROUND STEAM DISTRIBUTION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CARVER UNDERGROUND STEAM DISTRIBUTION | 2022 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ELHU | HEATING UPGRADES- ELLIOTT HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 304 | HA-D001 |  |  | NYCHA - ELLIOTT -- REPLACE 5 INSTANTANEOUS HW PRODUCING SYSTEMS NYCHA- ELLIOTT -- ?S FEED WATER PUMPING SYSTEM. THIS INCLUDES 3 NEW FEED WATER PUMPS, NEW PUMP CONTROL PANELS, ELECTRICAL COMPONENTS, WIRING ANDNEW FEED WATER PIPING AND ISOLATION VALVES NYCHA - ELLIOTT -- 5 HEAT CONTROL PANELS | 2022 | 515 | 0 | 515 | 0 | 0 | 0 | 0 | 0 | 515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20FSHL | FULTON HOUSES STAIRWAY AND HALL LIGHTING | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 304 | HA-D001 |  |  | NYCHA - FULTON HOUSES -- STAIRWAY AND HALL LIGHTING | 2022 | 464 | 0 | 464 | 0 | 0 | 0 | 0 | 0 | 464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20FUHU | FULTON HOUSES HEATING UPGRADES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 304 | HA-D001 |  |  | NYCHA - FULTON HOUSES -- INSTANTANEOUS HOT WATER HEATERS FOR 11 BUILDINGS NYCHA - FULTON HOUSES -- VACUMM TANK REPLACEMENTS IN 11 BUIDLINGS NYCHA - FULTON HOUSES -- STANDALONE CONDENSATE RECEIVING TANKS IN 11 BUILDINGS | 2022 | 1645 | 0 | 1645 | 0 | 0 | 0 | 0 | 0 | 1645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GHCL | GRANT - LAUNDROMART CONSTRUCTION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 309 | HA-D001 |  |  | NYCHA - GRANT HOUSES LAUNDROMAT -- CONSTRUCTION OF LAUNDROMAT AT GRANT HOUSES - COMPLETION OF PROJECT | 2022 | 985 | 0 | 985 | 0 | 0 | 0 | 0 | 0 | 985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JFPG | JEFFERSON HOUSES PLAYGROUND RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING CONSTRUCTION | 311 | HA-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RENOVATE PLAYGROUND AT JEFFERSON HOUSES | 2022 | 330 | 0 | 0 | 0 | 0 | 0 | 2190 | 0 | 2190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LESD | LES INFILL 1 NEW LAYERED ACCESS DOORS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-D001 |  |  | NYCHA LOWER EAST SIDE INFILL I LAYERED ACCESS DOORS -- TO FUND NEW LAYERED ACCESS DOORS FOR LES INFILL I | 2022 | 675 | 105 | 570 | 0 | 0 | 0 | 0 | 0 | 675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SGCU | STRAUS HOUSES GARBAGE COMPACTOR | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 306 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NYCHA GARBAGE COMPACTOR UPGRADES AT STRAUS HOUSES -- GARBAGE COMPACTOR UPGRADES AT STRAUS HOUSES | 2022 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SHDR | ALFRED SMITH -DOG RUN FOR 10 CATHERINE SLIP | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-D001 |  |  | NYCHA ALFRED E. SMITH HOUSES DOG RUN FOR 10 CATHERINE SLIP -- TO SUPPORT DOG RUN FOR 10 CATHERINE SLIP | 2022 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SISC | STANLEY ISAACS SENIOR CENTER BATHROOM ADA UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 300 | HA-M001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STANLEY ISAACS NEIGHBORHOOD CENTER - SENIOR CENTER BATHROOM RENOVATIONS - ADA BATHROOM UPGRADES | 2022 | 300 | 3.8 | 296 | 0 | 0 | 0 | 0 | 0 | 299.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SPER | SEWARD PARK EXTENSION RENOVATIONS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-D001 HA-M001 |  |  | SEWARD PARK EXTENSION RENOVATIONS -- RENOVATE VACANT SPACE AT 64-66 ESSEX STREET, SEWARD PARK EXTENSION. | 2022 | 500 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20TUSD | TAFT UNDERGROUND STEAM DISTRIBUTION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 310 | HA-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | TAFT UNDERGROUND STEAM DISTRIBUTION | 2022 | 7000 | 0 | 0 | 0 | 0 | 7000 | 0 | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WSCC | WOODSON CCTV | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-0001 |  |  | INSTALLATION OF CCTV | 2022 | 858 | 796.7 | 61 | 0 | 0 | 0 | 0 | 0 | 857.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM20WSLP | WOODSON LIGHT POLES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | INSTALLATION OF NEW LED FIXTURES AT LIGHT POLES AT WOODSON | 2022 | 250 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21CHIC | INTERIOR COMPACTOR AT CHELSEA HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 304 | HA-D001 |  |  | CHELSEA HOUSES-INTERIOR COMPACTOR | 2022 | 981 | 0 | 981 | 0 | 0 | 0 | 0 | 0 | 981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21CHRE | RENOVATIONS FOR CHELSEA HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 304 | HA-D001 |  |  | CHELSEA HOUSES-FUNDING FOR RENOVATIONS | 2022 | 1177 | 0 | 1177 | 0 | 0 | 0 | 0 | 0 | 1177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21DYEL | DYCKMAN HOUSES ELEVATOR REPLACEMENT | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 312 | HA-0001 |  |  | REPLACE ELEVATORS AT DYCKMAN HOUSES | 2022 | 6600 | 421.51 | 6078 | 0 | 0 | 0 | 0 | 0 | 6499.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21EHRE | RENOVATIONS AT ELLIOT HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 304 | HA-D001 |  |  | ELLIOT HOUSES--FUNDING FOR RENOVATIONS | 2022 | 811 | 0 | 811 | 0 | 0 | 0 | 0 | 0 | 811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21FHEC | EXTERIOR COMPACTOR AT FULTON HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 304 | HA-D001 |  |  | FULTON HOUSES-EXTERIOR COMPACTOR | 2022 | 441 | 0 | 441 | 0 | 0 | 0 | 0 | 0 | 441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21GHPS | REPAIR PAVEMENT AT GRANT HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 309 | HA-D001 |  |  | PB: -REPAIR PAVEMENT AT GRANT HOUSES--TO REPAIR PAVEMENT AND/OR SIDEWALKS AROUND GRANT HOUSES | 2022 | 365 | 0 | 365 | 0 | 0 | 0 | 0 | 0 | 365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21JHPR | PLAYGROUND RENOVATION AT JOHNSON HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-D001 |  |  | NYCHA JOHNSON HOUSES - PLAYGROUND RENOVATION--PLAYGROUND RENOVATION | 2022 | 175 | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21JUPG | JEFFERSON HOUSES UNION SETTLEMENT PLAYGROUND UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-M001 |  |  | UNION SETTLEMENT PLAYGROUND RENOVATIONS- JEFFERSON: FUNDING TO RENOVATE THE 6,370 SQUARE-FOOT PLAYGROUND AT THE JEFFERSON EARLY CHILDHOOD EDUCATION CENTER | 2022 | 425 | 0 | 425 | 0 | 0 | 0 | 0 | 0 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21LMPG | LEGGET MEMORIAL PLAYGROUND UPGRADE GAYLORD WHITE HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-M001 |  |  | UNION SETTLEMENT PLAYGROUND RENOVATIONS- LEGGETT MEMORIAL: FUNDING TO RENOVATE THE 2,346 SQUARE-FOOT PLAYGROUND AT THE LEGGETT MEMORIAL EARLY CHILDHOOD CENTER WITHIN THE NYCHA GAYLORD WHITE HOUSES DEVELOPMENT | 2022 | 275 | 0 | 275 | 0 | 0 | 0 | 0 | 0 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21LSCB | LINCOLN HOUSES SENIOR CENTER ADA BATHROOMS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-M001 |  |  | LINCOLN HOUSES SENIOR CENTER: CONVERTING 2 EXISTING BATHROOMS TO ADA | 2022 | 50 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHAS | MARBLE HILL HOUSES -ADDITIONAL SEATING | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE |  | HA-D001 |  |  | PB: -ADDITIONAL SEATING AT MARBLE HILL HOUSES- ADDITIONAL BENCHES WILL ALLOW RESIDENTS TO BE ABLE TO SIT ANDINCREASE THE SURROUNDING COMMUNITY MORAL. | 2022 | 50 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHEL | MELTZER HERNANDEZ HOUSES ELEVATOR REPLACEMENT | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-0001 |  |  | REPLACE ELEVATORS AT MELTZER HERNANDEZ | 2022 | 2295 | 122.38 | 2278 | 0 | 0 | 0 | 0 | 0 | 2400.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21RCCK | CC KITCHEN RENOVATION AT RUTGERS HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-D001 |  |  | RUTGERS HOUSES COMMUNITY CENTER - KITCHEN RENOVATION--FUNDING FOR COMMUNITY CENTER | 2022 | 348 | 0 | 348 | 0 | 0 | 0 | 0 | 0 | 348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SHLD | LAYERED ACCESS ENTRY FOR LOBBY DOORS AT STRAUS HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 306 | HA-D001 |  |  | STRAUS HOUSES - LAYERED ACCESS ENTRY FOR LOBBY DOORS-FUNDING FOR DOORS | 2022 | 300 | 0 | 737 | 0 | 0 | 0 | 0 | 0 | 737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SWTI | STEPHEN WISE TOWERS NYCHA - INFRASTRUCTURE- | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 307 | HA-D001 |  |  | STEPHEN WISE TOWERS NYCHA - INFRASTRUCTURE- WSUR C FRONT DOOR | 2022 | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21TABC | TAFT HOUSES BASKETBALL COURT | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 310 | HA-D001 |  |  | TAFT HOUSES GROUNDS BASKETBALL COURT RENOVATION | 2022 | 900 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21THCR | COMPACTOR REPLACEMENT AT TAFT HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 310 | HA-D001 |  |  | NYCHA TAFT HOUSES - COMPACTOR REPLACEMENT- COMPACTOR REPLACEMENT | 2022 | 310 | 0 | 882 | 0 | 0 | 0 | 0 | 0 | 882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21USPR | JOHNSON- UNION SETTLEMENT PLAYGROUND RENO | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-M001 |  |  | NYCHA- UNION SETTLEMENT PLAYGROUND RENOVATIONS- JOHNSON HOUSES--FUNDING TOWARDS PLAYGROUND RENOVATIONS AT JOHNSON HOUSES 237 EAST 104TH STREET, NEW YORK, NY 10029 | 2022 | 175 | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21WATC | REPLACING TRASH COMPACTORS AT WALD HOUSE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-D001 |  |  | PB: -REPLACING TRASH COMPACTORS AT WALD HOUSES-FUNDING FOR NYCHA PROJECT | 2022 | 70 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21WHBC | NYCHA WAGNER HOUSES-BASKETBALL COURT RENOVATIONS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-D001 |  |  | NYCHA WAGNER HOUSES-BASKETBALL COURT RENOVATIONS | 2022 | 1500 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21WHCC | WAGNER HOUSES- COMMUNITY CENTER | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-0001 |  |  | WAGNER HOUSES- COMMUNITY CENTER | 2022 | 15000 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM21WSUG | GARBAGE ENCLOSURES AT WSUR BROWNSTONES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 307 | HA-D001 |  |  | PB: -GARBAGE ENCLOSURES FOR 26 NYCHA WSUR BROWNSTONES- FUNDING FOR NYCHA PROJECT | 2022 | 70 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22ASEL | SMITH HOUSES- ADA UPGRADES AND EXISTING LEAKS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-D001 |  |  | ALFRED E. SMITH HOUSES ADA UPGRADES -- FUND SHORTFALL TOWARDS ADA UPGRADES AND FIX EXISTING LEAKS | 2022 | 146 | 0 | 2531 | 0 | 0 | 0 | 0 | 0 | 2531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22CTDR | CLINTON AVENUE- TERRACE DOOR REPLACEMENT | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-D001 |  |  | NYCHA CLINTON AVENUE (2070 CLINTON AVENUE) -- TERRACE DOOR REPLACEMENT | 2022 | 800 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22DCAM | DYCKMAN HOUSES- TECHNONOLGY UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 312 | HA-D001 |  |  | NYCHA DYCKMAN HOUSES DEVELOPMENT -- TECHNOLOGY UPGRADE: SECURITY CAMERAS SYSTEM | 2022 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22ISCK | STANLEY ISAACS KITCHEN - STRUCTURAL IMPROVEMENTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 308 | HA-D001 |  |  | ÝNYCHAÛ STANLEY M. ISAACS NEIGHBORHOOD CENTER KITCHEN -- TO COMPLETE STRUCTURAL IMPROVEMENTS TO AN EXISTING 1100 SQUARE FOOT COMMERCIAL KITCHEN | 2022 | 250 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22LESD | LES INFILL I- DOOR UPGRADES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-D001 |  |  | DOOR UPGRADES -- FUNDS WILL SUPPORT DOOR UPGRADES AT LES INFILL I. | 2022 | 700 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22MEBC | SMITH-HAMILTON MADISON HOUSE- ELEVATORS & ADA BATHRM SNR CTR | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-M001 |  |  | NYCHA HAMILTON MADISON HOUSE--THE CAPITAL PROJECT CONSISTS OF THE INSTALLATION OF AN ELEVATOR AND ADA-COMPLIANT BATHROOM, FOR THE NEW SENIOR AND COMMUNITY CENTER (SMITH HOUSE). 50 MADISON STREET, NEW YORK, NY 10038 | 2022 | 150 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SLAD | STRAUSS HOUSES- LAYERED ACCESS DOORS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 306 | HA-D001 |  |  | STRAUSS HOUSES LAYERED ACCESS DOORS -- STRAUSS HOUSES LAYERED ACCESS DOORS | 2022 | 432 | 0 | 432 | 0 | 0 | 0 | 0 | 0 | 432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SMGR | SMITH HOUSES INSTALLATION OF GAS RISERS #7 | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-0001 |  |  | INSTALLATION OF GAS RISERS #7 | 2022 | 9075 | 0 | 0 | 0 | 0 | 8250 | 0 | 0 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SPDS | SEWARD PARK EXT- DOORS & SECURITY UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-D001 |  |  | NYCHA SEWARD PARK EXTENSION - DOORS & SECURITY UPGRADE -- FUNDS WILL SUPPORT THE INSTALLATION OF NEW DOORS AND A NEW KEY FOB SYSTEM. | 2022 | 297 | 0 | 297 | 0 | 0 | 0 | 0 | 0 | 297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SPLS | SEWARD PARK- 65 NORFOLK ST RENOVATIONS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 309 | HA-D001 |  |  | RENOVATIONS AT 65 NORFOLK STREET -- FUNDS WILL SUPPORT THE RENOVATIONOF SEWARD PARK EXTENSION'S VACANT FORMER LAUNDRY SPACE FOR ADDITIONALCOMMUNITY PROGRAMMING AND SERVICES AT 65 NORFOLK STREET | 2022 | 540 | 0 | 540 | 0 | 0 | 0 | 0 | 0 | 540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22TAEL | TAFT HOUSES ELEVATOR REHABILITATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-0001 |  |  | ELEVATOE UPGRADES | 2022 | 9075 | 0 | 0 | 0 | 8000 | 250 | 0 | 0 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22USLM | UNION SETTLEMENT- LEGGETT & JEFFERSON | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-D001 |  |  | NYCHA - UNION SETTLEMENT -- UNION SETTLEMENT ( LEGGETT MEMORIAL & JEFFERSON RENOVATION) | 2022 | 700 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22WAGR | WAGNER HOUSES GAS RISER REPLACEMENTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 311 | HA-0001 |  |  | GAS RISER REPLACEMENT | 2022 | 10230 | 0 | 0 | 5300 | 0 | 4000 | 0 | 0 | 9300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | HAM22WAPL | WALD HOUSES- PLAYGROUND RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 303 | HA-D001 |  |  | WALD HOUSES ADULT PLAYGROUND -- WALD HOUSES PLAYGROUND RENOVATION FORADULT AND SENIOR ACTIVITIES. | 2022 | 550 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18BOI | Replace boilers at Lehman Village and Wilson Houses | NEIGHBORHOOD REVITALIZATION | 300 | ED-0384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REPLACE BOILERS AT LEHMAN VILLAGE AND WILSON HOUSES | 2022 | 13200 | 0 | 1980 | 13556 | 0 | 0 | 0 | 0 | 15536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ECC | Renovations at Early Childhood Centers in East Harlem | NEIGHBORHOOD REVITALIZATION | 300 | ED-0384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATIONS AT EARLY CHILDHOOD CENTERS IN EAST HARLEM | 2022 | 7700 | 0 | 1155 | 4761 | 0 | 0 | 0 | 0 | 5916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18GAS | Install new gas risers at Johnson Houses Install new gas ris | NEIGHBORHOOD REVITALIZATION | 300 | ED-0384 |  |  | INSTALL NEW GAS RISERS AT JOHNSON HOUSES | 2022 | 5500 | 0 | 825 | 5123 | 0 | 0 | 0 | 0 | 5948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18ROF | Conduct roof and parapet work at UPACA (Site 5) | NEIGHBORHOOD REVITALIZATION | 300 | ED-0384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONDUCT ROOF AND PARAPET WORK AT UPACA (SITE 5) | 2022 | 2500 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | NDF-18VNT | Modernize ventilation systems in 17 East Harlem Developments | NEIGHBORHOOD REVITALIZATION | 300 | ED-0384 |  |  | MODERNIZE VENTILATION SYSTEMS IN 17 EAST HARLEM DEVELOPMENTS | 2022 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 806 | HOUSING PRESERVATION AND DEVEL | P-3WAGNER | Wagner Playground, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | WAGNER PLAYGROUND -- TO PROVIDE FUNDING FOR OVERALL PLAYGROUND RENOVATIONS | WAGNER PLAYGROUND -- TO PROVIDE FUNDING FOR OVERALL PLAYGROUND RENOVATIONS | 2022 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH501 | DOHMH - LIGHTING UPGRADES | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | HL-0082 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LIGHTING UPGRADES | 2022 | 539 | 421.05 | 69 | 0 | 0 | 0 | 0 | 0 | 490.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CME520FPC | OCME - New Medical Examiner Facility | OCME | 301 | HL-0083 |  |  | NEW MEDICAL FACILITY | 2022 | 500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82CHRHC | Central Harlem Health Center interior renovation | CLINIC RENOVATION AND REHABILITATION |  | HL-0082 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CENTRAL HARLEM HEALTH CENTER INTERIOR RENOVATION | 2022 | 9500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EASTH | EAST HARLEM HEALTH HUB | CLINIC RENOVATION AND REHABILITATION |  | HL-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EAAT HARLEM HEALTH HUB BUILD OUT OF MAIN BUILDING TO CREATE HUB | 2022 | 600 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHREL | EAST HARLEM HEALTH CENTER ELEVATOR MODERNIZATION | CLINIC RENOVATION AND REHABILITATION |  | HL-0082 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | EAST HARLEM HEALTH CENTER ELEVATOR MODERNIZATION | 2022 | 350 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82EHRHC | East Harlem Health Center interior renovation | CLINIC RENOVATION AND REHABILITATION |  | HL-0082 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | EAST HARLEM HEALTH CENTER INTERIOR RENOVATION | 2022 | 9000 | 0 | 0 | 0 | 0 | 0 | 3947 | 0 | 3947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82PHLNB | DOHMH FACILITIES | CLINIC RENOVATION AND REHABILITATION | 300 | HL-0082 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PUBLIC HEALTH LAB NEW BUILDING | 2022 | 121113 | 1680.36 | 804 | 0 | 0 | 0 | 0 | 0 | 2484.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82WASHT | WASHINGTON HEIGHTS HEALTH CENTER FACADE RENOVATION | CLINIC RENOVATION AND REHABILITATION |  | HL-0082 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WASHINGTON HEIGHTS HEALTH CENTER FACADE REPAIR PER LOCAL LAW 11 | 2022 | 3234 | 0 | 0 | 1378 | 2892 | 13300 | 0 | 0 | 17570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 02200901 | CENTRAL OFFICE: PRIMARY CARE INITIATIVE | ROUTINE RECONSTRUCTION |  | HO-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 346 BROADWAY, CSS, 12E | THE PURPOSE OF THIS PROJEC T IS TO RENOVATE PRIMARY CARE INITIATIVE CLINICS THROUGHTOUT THE HHC SYSTEM -CITY WIDE. | 2022 | 1329 | 714.3 | 0 | 807 | 0 | 0 | 0 | 0 | 1521.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 02201805 | LWH: REPLACE COOLING TOWER AND UPGRADES TO CHILLER & BOILER | ROUTINE RECONSTRUCTION |  | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 1721-35 AMSTERDAM AVENUE, NEW YORK, NY | REPLACE COOLING TOWER AND UPGRADES TO CHILLER & BOILER AT THE NYC HEALTH + HOSPITALS LOWER WASHINGTON HEIGHTS HEALTH CENTER. | 2022 | 866 | 801.45 | 0 | 0 | 0 | 65 | 0 | 0 | 866.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 02201901 | H+H: RENOVATE AND OUTFIT OFFICES AT 50 WATER STREET | ROUTINE RECONSTRUCTION |  | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 50 WATER STREET, NEW YORK, NY | NYC HEALTH + HOSPITALS: RENOVATE AND OUTFIT OFFICES AT 50 WATER STREET FOR RELOCATED CENTRAL OFFICE STAFF | 2022 | 4403 | 28644.1 | 1603 | 0 | 0 | 0 | 0 | 0 | 30247.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201001 | BELLEVUE OR UPGRADE | ROUTINE RECONSTRUCTION | 306 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 462 FIRST AVENUE, NEW YORK, NY 10016 | UPGRADE OPERATING ROOMS ON THE 11TH FLOOR AT BELLEVUE. | 2022 | 3200 | 2943.38 | 0 | 0 | 257 | 0 | 0 | 0 | 3200.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201705 | BELLEVUE CONSTRUCT NEW CHEMISTRY LABORATORY | ROUTINE RECONSTRUCTION | 306 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 462 FIRST AVENUE, NEW YORK, NY 10016 | BELLEVUE HOSPITAL CENTER: CONSTRUCT NEW CHEMISTRY LABORATORY | 2022 | 886 | 3588.34 | 0 | 693 | 0 | 0 | 0 | 0 | 4281.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201803 | BELLEVUE EXPAND HEIGHT OF GUARDRAILS IN THE ACB ATRIUM | ROUTINE RECONSTRUCTION |  | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 462 FIRST AVENUE, NEW YORK, NY 10016 | EXPAND HEIGHT OF GUARDRAILS IN THE ACB ATRIUM | 2022 | 1046 | 886.16 | 0 | 160 | 0 | 0 | 0 | 0 | 1046.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201901 | BELLEVUE CONVERT SPACE TO CREATE 4 PYXIS MEDICATION ROOMS | ROUTINE RECONSTRUCTION |  | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 462 FIRST AVENUE, NEW YORK, NY 10016 | CONVERT SPACE TO CREATE 4 PYXIS MEDICATION ROOMS FOR THE INPATIENT PHYCHIATRIC MENTAL HEALTH UNITS AT BELLEVUE HOSPITAL CENTER. | 2022 | 700 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201903 | BELLEVUE: RENOVATION AND UPGRADE OF TRAUMA SLOTS IN ADULT ED | ROUTINE RECONSTRUCTION |  | HO-M001 HO-D003 |  | 462 FIRST AVENUE, NEW YORK, NY, 10016 | BELLEVUE: RENOVATION AND UPGRADE OF TRAUMA SLOTS IN ADULT ED | 2022 | 951 | 0 | 0 | 325 | 0 | 0 | 626 | 0 | 951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11201904 | BELLEVUE UNDERGROUND STORAGE TANK SUMP UPGRADES | ROUTINE RECONSTRUCTION |  | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 425 FIRST AVENUE, NEW YORK, NY 10016 | UPGRADE UNDERGROUND STORAGE TANK SUMPS ON THE BELLEVUE CAMPUS. | 2022 | 796 | 1123.02 | 0 | 0 | 136 | 0 | 0 | 0 | 1259.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202101 | BELLEVUE: REPLACE EMERGENCY DEPT NURSES STATION | ROUTINE RECONSTRUCTION |  | HO-M001 HO-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 462 FIRST AVENUE, MANHATTAN, NY 10016 | REPLACE EMERGENCY DEPT NURSE STATION | 2022 | 940 | 0 | 0 | 100 | 840 | 0 | 0 | 0 | 940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202104 | Bellevue: Bldg H (16th Fl) - New Infusion Center (Interior R | ROUTINE RECONSTRUCTION |  | HO-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BELLEVUE BUILDING H (16HT FLOOR) - NEW INFUSION CENTER (INTERIROR R) | 2022 | 1100 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202106 | BELLEVUE PHARMACY COMPOUNDING USP 797/800 COMPLIANCE | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 462 1ST AVENUE, NEW YORK, NY 10016 | NYC HEALTH + HOSPITALS/BELLEVUE.PHARMACY COMPOUNDING USP 797/800 COMPLIANCE | 2022 | 3533 | 0 | 335 | 3053 | 145 | 0 | 0 | 0 | 3533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202201 | BELLEVUE FIRE ALARM PANELS REPLACEMENT- MAIN HOSPITAL | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 462 FIRST AVENUE, NEW YORK, NY 10016 | BELLEVUE FIRE ALARM PANELS REPLACEMENT - MAIN HOSPITAL | 2022 | 6000 | 0 | 1000 | 2500 | 2500 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202202 | BELLEVUE SOUTH STAND PIPE REPLACEMENT- HOSPITAL BLD | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 462 FIRST AVENUE, NEW YORK, NY 10016 | BELLEVUE SOUTH STAND PIPE REPLACEMENT - HOSPITAL BLD | 2022 | 3000 | 0 | 1000 | 2000 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202204 | BELLEVUE FORENSIC PSYCH-19E | ROUTINE RECONSTRUCTION |  | HO-0214 |  |  | NYC HEALTH + HOSPITALS/ BELLEVUE (462 FIRST AVENUE, MANHATTAN, NEW YORK) FORENSIC PSYCH-19E | 2022 | 1500 | 0 | 500 | 1000 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202205 | BELLEVUE REPLACE FIRE PUMP | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 462 FIRST AVENUE, NEW YORK, NY 10016 | NYC HEALTH + HOSPITALS/ BELLEVUE (462 FIRST AVENUE, MANHATTAN, NEW YORK) REPLACE FIRE PUMP | 2022 | 5000 | 0 | 300 | 4700 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 11202206 | BELLEVUE CHS OUTPOSTED THERAPEUTIC UNITS | ROUTINE RECONSTRUCTION |  | HO-0341 |  | 462 FIRST AVENUE, NEW YORK, NY 10016 | BELLEVUE CHS OUTPOSTED THERAPEUTIC UNITS | 2022 | 183000 | 0 | 165000 | 18000 | 0 | 0 | 0 | 0 | 183000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201501 | GOUVERNEUR: ROBERTO CLEMENTE CENTER RENOVATION | ROUTINE RECONSTRUCTION | 303 | HO-M001 HO-D003 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 540 EAST 13TH STREET, NEW YORK, NY 10009 | GOUVERNEUR: ROBERTO CLEMENTE CENTER RENOVATION | 2022 | 1000 | 811.16 | 0 | 189 | 0 | 0 | 95 | 0 | 1095.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201801 | GOUVERNEUR REHABILITATE FACADE-CYCLE 7B AMENDED AND CYCLE 8B | ROUTINE RECONSTRUCTION |  | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 227 MADISON STREET, NEW YORK, NY | REHABILITATE FACADE - CYCLE 7B AMENDED AND CYCLE 8B AT GOUVERNEUR HEALTHCARE SERVICES | 2022 | 291 | 246.21 | 0 | 0 | 0 | 45 | 0 | 0 | 291.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201802 | GOUVERNEUR: Installation of Exhaust Fan, 5th Floor Air | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 277 MADISON ST, NY, NYC 10002 | N/A | 2022 | 89 | 0 | 89 | 0 | 0 | 0 | 0 | 0 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12201902 | GOUVERNEUR: RENOVATE COURTYARD | ROUTINE RECONSTRUCTION |  | HO-0214 HO-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 277 MADISON STREET, NEW YORK, NY 10002 | NA | 2022 | 248 | 276.62 | 85 | 0 | 0 | 20 | 0 | 0 | 381.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12202101 | GOUVERNEUR EXPRESS CARE | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 227 MADISON STREET, MANHATTAN, 10002 | EXPRESS CARE CONSTRUCTION | 2022 | 4300 | 0 | 193 | 0 | 0 | 4107 | 0 | 0 | 4300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 12202201 | GOUVERNEUR: POST ACUTE DIALYSIS DENS | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 277 MADISON STREET, NEW YORK, NY 10002 | NYC HEALTH + HOSPITALS/ GOUVERNEUR: (277 277 MADISON ST. NEW YORK, NY) POST ACUTE DIALYSIS DENS. | 2022 | 2300 | 0 | 221 | 2079 | 0 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13200573 | HARLEM: CONSTRUCT NEW PARKING FACILITY | ROUTINE RECONSTRUCTION | 310 | HO-0377 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 506 LENOX AVENUE, NEW YORK, NY 10037 | CONSTRUCT NEW PARKING FACILITY AT HARLEM HOSPITAL CENTER THAT WILL ADD 99 ADDITIOANL CAPACITY. | 2022 | 3500 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201101 | HARLEM: RELOCATE SYDENHAM CLINIC FROM 125TH TO 118TH STREET | ROUTINE RECONSTRUCTION |  | HO-0214 HO-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | WEST 118TH STREET, NEW YORK NY | THE FPURPOSE OF THIS PROJECT IS TO RENOVATE SPACE AT 118TH STREET (DCAS BUIDING) IN ORDER TO RELOCATE THE SYDENHAM/RENAISSANCE CLINIC FROM 125TH STREET TO 118TH STREET. SYDENHAM/RENAISSANCE CLINIC IS AN EXTENSION OF HARLEM HOSPITAL CENTER. | 2022 | 2500 | 3293.63 | 0 | 0 | 147 | 0 | 23 | 0 | 3463.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201301 | HARLEM: RENOVATE POST PARTUM UNIT | ROUTINE RECONSTRUCTION | 310 | HO-0214 HO-D003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 506 LENOX AVENUE, NEW YORK, NY 10037 | RENOVATE POST PARTUM UNIT AT HARLEM HOSPITAL CENTER. | 2022 | 600 | 75.5 | 2398 | 0 | 0 | 0 | 0 | 0 | 2473.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201502 | HARLEM: UPGRADE ELECTRICAL SYSTEM | ROUTINE RECONSTRUCTION | 310 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 506 LENOX AVENUE, NEW YORK, NY 10037 | UPGRADE ELECTRICAL SYSTEM AT HARLEM HOSPITAL CENTER TO COMPLY WITH NFPA LIFE SAFETY CODE FOR CRITICAL BRANCH SEPARATION. 95% DRAWINGS ARE COMPLETE AND STOPPED. HHC CONSIDERING IMPLEMENTING EMERGENCY POWER ONLY TO ACHIEVE TYPE 1 SYSTEM (TYPE 1 EES). | 2022 | 8300 | 18144.72 | 825 | 0 | 0 | 0 | 0 | 0 | 18969.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201602 | HARLEM: REHABILITATE THE EXTERIOR FACADE OF MLK BLG - LL 11 | ROUTINE RECONSTRUCTION | 310 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 506 LENOX AVENUE | THEPURPOSE OF THIS PROJECT IS TO REHABILITATE THE EXTERIOR FASCADE OF MILK BUILDING AT HARLEM HOSPITAL CENTER WITH LOCAL LAW 11- FUNDS | 2022 | 15966 | 12143.78 | 0 | 3823 | 0 | 0 | 0 | 0 | 15966.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201603 | HARLEM: WP DECANTING, ONR DEMOLITION, & NEW DATA CENTER | ROUTINE RECONSTRUCTION | 310 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 506 LENOX AVENUE NEW YORK, NY 10037 | THE PURPOSE OF THIS PROJECT IS TO DECANT AND DEMOLISH THE WP ROOM AT HARLEM HOSPITAL CENTER WITH LOCAL LAW 11- FUNDS. | 2022 | 28184 | 9714.01 | 13463 | 0 | 0 | 0 | 0 | 0 | 23177.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13201803 | HARLEM: KOUNTZ PAVILION STAIRWELL REHABILITATION | ROUTINE RECONSTRUCTION |  | HO-0214 HO-0377 HO-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 506 LENOX AVENUE, NEW YORK, NY 10037 | NYC HEALTH + HOSPITALS ¦ HARLEM: STAIRWELL REHABILITATION IN THE KOUNTZ PAVILION REQUIRED TO CORRECT UNSAFE CONDITIONS. | 2022 | 173 | 14.51 | 1974 | 0 | 0 | 0 | 0 | 0 | 1988.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202001 | HARLEM: RELOCATE VARIOUS DEPARTMENTS FROM THE WP | ROUTINE RECONSTRUCTION |  | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | MLK PAVILION: 506 LENOX AVENUE, NEW YORK, NY 10037; AND KOUNTZ PAVILION: 15 WEST 137TH STREET, NEW YORK, NY 10037; BOTH BLDS HAVE THE SAMEBLOCK & LOT 1734-1 | HARLEM HOSPITAL CENTER: RELOCATE VARIOUS DEPARTMENTS FROM THE WOMENS PAVILION (WP) TO BE DEMOLISHED TO THE MLK PAVILION AND THE KOUNTZ PAVILION. | 2022 | 5008 | 4503.84 | 50 | 0 | 455 | 0 | 0 | 0 | 5008.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202101 | HARLEM ELEVATOR HVAC UPGRADE | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 506 LENOX AVE, NEW YORK NY 10037 | ELEVATOR MER HVAC UPGRADE FOR NYC H+H/ HARLEM | 2022 | 150 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202102 | Harlem: Cooling Tower Replacement | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 506 LENOX AVE, NEW YORK NY 10037 | COOLING TOWER REPLACEMENT | 2022 | 866 | 0 | 866 | 0 | 0 | 0 | 0 | 0 | 866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202103 | HARLEM PHARMACY COMPOUNDING USP 797/800 COMPLIANCE | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 506 LENOX AVENUE, NEW YORK, NY 10037 | NYC HEALTH + HOSPITALS/HARLEM. PHARMACY COMPOUNDING USP 797/800 COMPLIANCE | 2022 | 3808 | 0 | 393 | 3245 | 170 | 0 | 0 | 0 | 3808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202201 | HARLEM CONDENSER WATER PIPING REPLACEMENT | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 506 LENOX AVENUE, NEW YORK, NY 10037 | NYC HEALTH + HOSPITALS/ HARLEM (506 LENOX AVENUE). CONDENSER WATER PIPING REPLACEMENT | 2022 | 6426 | 0 | 6426 | 0 | 0 | 0 | 0 | 0 | 6426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202244 | HARLEM: 3 GE Logiq Ultrasound Machines | MAJOR MEDICAL EQUIPMENT |  | HO-0214 |  |  |  | 2022 | 344 | 0 | 344 | 0 | 0 | 0 | 0 | 0 | 344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 13202246 | HARLEM: Retinal Camera (NICU) | MAJOR MEDICAL EQUIPMENT |  | HO-0214 |  |  |  | 2022 | 99 | 0 | 99 | 0 | 0 | 0 | 0 | 0 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 18202001 | SYDENHAM: RETAIL PHARMACY RENOVATION | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 264 WEST 118TH STREET, NEW YORK NY 10026 | SYDENHAM: RETAIL PHARMACY RENOVATION | 2022 | 1093 | 0 | 0 | 0 | 1093 | 0 | 0 | 0 | 1093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 18202201 | SYDENHAM BATHROOM RENOVATION | ROUTINE RECONSTRUCTION |  | HO-D003 |  |  | SYDENHAM BATHROOM RENOVATION | 2022 | 250 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37201301 | METROPOLITAN COMPLETE RENOVATION OF SIXTH FLOOR 6C MAIN BLDG | ROUTINE RECONSTRUCTION | 311 | HO-D003 HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 1901 FIRST AVENUE, NEW YORK, NY 10029 | RENOVATE/FURNISH CLINIC SPACE THAT IS CURRENTLY IN MAJOR DISREPAIR ONTHE 6TH FLLOR (6C) OPD BUILDING AT METROPOLITAN HOSPITAL CENTER. RENOVATIONS WILL ADDRESS OR IMPROVE PATIENT FLOW/OPERATIONS. THIS SERVICE INCLUDES: AUDIOLOGY, CARDIAC, DIABETES CARE, ENDOCRINOLOGY, OPHTHALMOLOGY AND GI. | 2022 | 2420 | 286.36 | 4712 | 0 | 0 | 0 | 0 | 0 | 4998.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37201401 | METROPOLITAN PERIMETER GATE/FENCING & SIGNAGE-LANDSCAPING | ROUTINE RECONSTRUCTION | 311 | HO-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 1901 FIRST AVENUE, NEW YORK , NY10029 | THE PURPOSE OF THIS PROJECT IS TO INSTALL PERIMETER FENCING AND A GATE TO PROVIDE A COMPREHENSIVE AND COMPLETE ENCLOSURE TO THE MAIN CAMPUS AT METROPOLITAN HOSPITAL CENTER IN ORDER TO IMPROVE THE HOSPITAL'SSECURITY. IN ADDITION, THE PROJECT SCOPE INCLUDES LANDSCAPING TO BEAUTIFY THE HOSPITAL SURROUNDINGS. | 2022 | 900 | 451.32 | 0 | 0 | 448 | 0 | 0 | 0 | 899.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37201501 | METROPOLITAN ESTABLISH A COMPREHENSIVE LBGT HEALTH CENTER | ROUTINE RECONSTRUCTION | 311 | HO-0214 HO-D003 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | 1901 FIRST AVNUE, NEW YORK, NY 10029 | RENOVATE AND OUTFIT SPACE ON THE FIRST FLOOR OF METROPOLITAN HOSPITAL'S OURPATIENT BUILDING INTO A STATE-OF-THE-ART LGBT COMPREHENSIVE FAMILY HEALTH CENTER. | 2022 | 2100 | 2439.88 | 380 | 700 | 2 | 0 | 0 | 0 | 3521.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37201601 | MHC: EXTERIOR FACADE RESTORATION CAMPUS-WIDE | ROUTINE RECONSTRUCTION | 311 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 1901 FIRST AVENUE, NEW YORK, NY 10029 | RESTORE EXTERIOR FACADE ON THE CAMPUS OF METROPOLITAN HOSPITAL CENTERTO COMPLY WITH LOCAL LAW 11 REGULATIONS. | 2022 | 399 | 145.62 | 198 | 300 | 0 | 0 | 0 | 0 | 643.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37201901 | MET REPLACE MEDIUM PRESSURE STEAM CONDENSATE RETURN RISER | ROUTINE RECONSTRUCTION |  | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 1901 FIRST AVENUE, NEW YORK, NY 10029 | REPLACE MEDIUM PRESSURE STEAM CONDENSATE RETURN RISER AT METROPOLITANHOSPITAL CENTER. | 2022 | 648 | 0 | 648 | 0 | 0 | 0 | 0 | 0 | 648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202001 | METROPOLITAN : REPLACE MRI AT MODULAR MRI BUILDING | ROUTINE RECONSTRUCTION |  | HO-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 1901 FIRST AVENUE , NEW YORK, NY 10029 | REPLACE MRI UNIT AT MODULAR MRI BUILDING FOR HEALTH + HOSPITALS/METROPOLITAN | 2022 | 3800 | 251.44 | 249 | 3300 | 0 | 0 | 0 | 0 | 3800.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202002 | METROPOLITAN: WINDOW REPLACEMENT | ROUTINE RECONSTRUCTION |  | HO-0214 |  |  | METROPOLITAN: WINDOW REPLACEMENT | 2022 | 13000 | 266 | 0 | 12734 | 0 | 0 | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202003 | MET: EMERGENCY POWER SEPARATION AND UPGRADES | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 1901 FIRST AVENUE, NEW YORK, NY 10029 | EMERGENCY POWER SEPARATION AND UPGRADES AT METROPOLITAN HOSPITAL CENTER | 2022 | 25000 | 261.01 | 27 | 24712 | 0 | 0 | 0 | 0 | 25000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202004 | METROPOLITAN: CREATE URGENT CARE CENTER | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 1901 FIRST AVENUE, NEW YORK, NY 10038 | HHC METROPOLITAN: CREATE URGENT CARE CENTER. THE METROPOLITAN HOSPITAL EXPRESSCARE CLINIC IS AN URGENT CARE CENTER MODEL MANAGED BY THE EMERGENCY DEPARTMENT TO PROVIDE PATIENTS WITH FASTER ACCESS TO THE APPROPRIATE LEVEL OF CARE. THE PROPOSED NEW CENTER WILL BE LOCATED ON THE 1ST FLOOR AND WILL PROVIDE WALK-IN SERVICES FOR PATIENTS WITH NON-EMERGENT CONDITIONS AND WILL BE STAFFED WITH BOARD-CERTIFIED DOCTORS, NURSES, AND PATIENT CARE STAFF. | 2022 | 1664 | 0 | 0 | 1664 | 0 | 0 | 0 | 0 | 1664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202102 | METROPOLITAN CHILLER PLANT UPGRADE | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 1901 FIRST AVENUE, MANHATTAN, NY 10029 | CHILLER PLANT UPGRADE AT METROPOLITAN | 2022 | 12624 | 11646.7 | 0 | 977 | 0 | 0 | 0 | 0 | 12623.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202103 | METROPOLITAN FIRE PROTECTION UPGRADES | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 1901 FIRST AVENUE, MANHATTAN, NY 10029 | FIRE PROTECTION UPGRADES | 2022 | 2267 | 0 | 2060 | 2666 | 7274 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202108 | METROPOLITAN: FIRE ALARM SYSTEM | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 1901 FIRST AVENUE, NEW YORK, NY 10029 | FIRE ALARM SYSTEM | 2022 | 2000 | 0 | 200 | 1800 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202201 | METROPOLITAN WATER MAIN BREAK | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 1901 FIRST AVENUE, NEW YORK, NY 10029 | METROPOLITAN WATER MAIN BREAK | 2022 | 266 | 0 | 266 | 0 | 0 | 0 | 0 | 0 | 266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202202 | METROPOLITAN: REHAB RENOVATION | ROUTINE RECONSTRUCTION |  | HO-M001 HO-D003 |  | 1901 1ST AVENUE, NY, NY 10029 | N/A | 2022 | 1240 | 0 | 200 | 1040 | 0 | 0 | 0 | 0 | 1240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 37202203 | METROPOLITAN: INDOOR/OUTDOOR RESPITE SPACE RENOVATION | ROUTINE RECONSTRUCTION |  | HO-D003 |  | 1901 1ST AVENUE, NY, NY 10029 | N/A | 2022 | 878 | 0 | 0 | 878 | 0 | 0 | 0 | 0 | 878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 67200901 | COLER: RENOVATE THE NURSING FACILITY DAY ROOM | ROUTINE RECONSTRUCTION |  | HO-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 900 MAINS STR. ROOSEVELT NEW YORK , NY 10044 | THE PURPOSE OF THIS PROJECT IS TO RENOVATE THE NURSING FACILITY DAY ROOM AT COLER SPECIIALITY HOSPITAL & NUSING FACILITY. | 2022 | 300 | 3.8 | 0 | 0 | 296 | 0 | 0 | 0 | 299.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 67201170 | COLER: WINDOW REPLACEMENT AND ROOF/FACADE REHABILITATION | ROUTINE RECONSTRUCTION |  | HO-0214 |  | THE PURPOSE OF THIS PROJECT IS TO REPLACE WINDORS AND REHABILITATE THE FACADE AT COLER SPECIALITY HOSPITAL AND NURSING FACILITY. | THE PURPOSE OF THIS PROJECT IS TO REPLACE WINDORS AND REHABILITATE THE FACADE AT COLER SPECIALITY HOSPITAL AND NURSING FACILITY. | 2022 | 12826 | 10868.23 | 0 | 0 | 1958 | 0 | 0 | 0 | 12826.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 68202102 | CARTER: NEW CENTRALIZED BUILDING MANAGEMENT CONTROL SYSTEM | ROUTINE RECONSTRUCTION |  | HO-M001 |  | 1752 PARK AVENUE NEW YORK, NY 10035 | NYC HEALTH + HOSPITALS/CARTER: NEW CENTRALIZED BUILDING MANAGEMENT CONTROL SYSTEM | 2022 | 63 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 68202103 | CARTER PHARMACY COMPOUNDING USP 797/800 COMPLIANCE | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 1752 PARK AVENUE, NEW YORK NEW YORK 10035 | CARTER PHARMACY COMPOUNDING USP 797/800 COMPLIANCE | 2022 | 2090 | 0 | 2090 | 0 | 0 | 0 | 0 | 0 | 2090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 68202201 | CARTER ROOF TANK REPLACEMENT | ROUTINE RECONSTRUCTION |  | HO-D003 |  | 1752 PARK AVENUE, NEW YORK, NY 10035 | CARTER ROOF TANK REPLACEMENT | 2022 | 150 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | 68202202 | CARTER FACADE REHABILITATION | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 1752 PARK AVENUE | NYC HEALTH + HOSPITALS/ HENRY J. CARTER (1752 PARK AVENUE) DESIGN COST AND CONSTRUCTION COSTS ASSOCIATED WITH FA×ADE REHABILITATION | 2022 | 388 | 0 | 0 | 0 | 0 | 388 | 0 | 0 | 388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC403 | HARLEM HOSPITAL CENTER ENERGY UPGRADE | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HARLEM HOSPITAL CENTER ACE PROGRAM | 2022 | 10682 | 10681.4 | 0 | 0 | 176 | 0 | 0 | 0 | 10857.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC406 | BELLEVUE HOSPITAL CHILLERS | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 302 | PU-0025 HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CHILLERS | 2022 | 4493 | 4165.06 | 0 | 0 | 0 | 327 | 0 | 0 | 4492.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC408 | COLER BOILER REPLACEMENT | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 311 | PU-0025 HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INSTALL NEW LPS BOILER PLANT & ALL ASSOCIATED ANCILLARY EQUIPMENT. INSTALL NEW INDEPENDENT DOMESTIC HOT WATER BOILERS. CONVERT HIGH PRESSURE SYS TO LOW PRESSURE SYS, INSTALL NEW GAS SERVICE & FUEL OIL STORAGE. | 2022 | 21355 | 18189.06 | 0 | 0 | 1905 | 0 | 0 | 0 | 20094.06 | 1260.02 | 0 | 0 | 0 | 0 | 0 | 0 | 1260.02
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | ACEHHC602 | BELLEVUE LIGHTING AND CONTROLS UPGRADE | ROUTINE RECONSTRUCTION |  | HO-0214 PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 462 FIRST AVENUE, NEW YORK, NY 10016 | LIGHTING AND CONTROLS UPGRADE AT BELLEVUE | 2022 | 14851 | 13875.05 | 297 | 679 | 0 | 0 | 0 | 0 | 14851.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SAND1117 | BHC: MEP MITIGATION | ROUTINE RECONSTRUCTION |  | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 462 FIRST AVENUE, NEW YORK, NY 10016 | MEP MITIGATION PROJECT TO ENSURE THAT NYC HEALTH + HOSPITALS ¦ BELLEVUE WILL BE PROTECTED FROM FUTURE HURRICANE STORMS LIKE SANDY. FUNDS TOBE USED FOR THE RELOCATION OF SWITHGEAR AND AIR HANDKLING UNITS TO A HIGHER FLOOR, | 2022 | 15914 | 1628 | 96 | 0 | 0 | 74 | 0 | 0 | 1798 | 16225.99 | 870 | 0 | 0 | 658 | 0 | 0 | 17753.99
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SAND1121 | BHC: Elevate Security Systems | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 462 FIRST AVENUE, NEW YORK, NY 10016 | MEP MITIGATION PROJECT TO ENSURE THAT NYC HEALTH + HOSPITALS ¦ BELLEVUE WILL BE PROTECTED FROM FUTURE HURRICANE STORMS LIKE SANDY. FUNDS TOBE USED FOR THE ELEVATION OF THE SECURITY SYSTEMS | 2022 | 5500 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | 4950 | 0 | 0 | 0 | 0 | 0 | 4950
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SAND11B | BELLEVUE RECONSTRUCTION AS A RESULT OF SANDY | ROUTINE RECONSTRUCTION | 306 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 462 FIRST AVENUE, NEW YORK, NY 10016 | RECONSTRUCTION OF BELLEVUE HOSPITAL CENTER NECESSITATED BY HURRICANE SANDY. | 2022 | 67500 | 5239.69 | 0 | 0 | 0 | 504 | 0 | 0 | 5743.69 | 54219.03 | 0 | 0 | 0 | 6911 | 0 | 0 | 61130.03
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SAND3706 | MHC: INSTALL ELECTRIC AND CHILLER QUICK CONNECTS | ROUTINE RECONSTRUCTION | 311 | HO-0214 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 1901 FIRST AVENUE, NEW YORK, NY 10029 | INSTALL ELECTRIC AND CHILLER QUICK CONNECTS FOR THREE ROLL-UP TYPE GENERATORS AND ONE CHILER AND ONE QUICK CONNECT WATER CONNECTION THAT WERE DESTRPYED BY SEVERE WATER DAMAGES DUE TO EXPOSURE TO SALT WATER BY HURRICANE SANDY. NYC H+H WILL MANAGE THE DESIGN, PHASE, AND NYC EDC (801) WILL MANAGE THE CONSTRUCTION PHASE. | 2022 | 5230 | 1108.74 | 94 | 0 | 135 | 0 | 0 | 0 | 1337.74 | 3376.73 | 277 | 0 | 235 | 0 | 0 | 0 | 3888.73
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | SANDCOFW | Coler Flood Mitigation | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 900 MAIN ST ROOSEVELT ISLAND, NY | COLER FLOOD MITIGATION | 2022 | 0 | 0 | 0 | 813 | 0 | 18970 | 0 | 0 | 19783 | 0 | 0 | 7312 | 0 | 87193 | 0 | 0 | 94505
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | TKYHHC903 | BELLEVUE COMBINED HEAT AND POWER (CHP) | ROUTINE RECONSTRUCTION |  | HO-0214 PU-0025 |  | 462 1ST AVENUE., NEW YORK NY 10016 | BELLEVUE CHP | 2022 | 35245 | 0 | 22788 | 12457 | 0 | 0 | 0 | 0 | 35245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 819 | HEALTH AND HOSPITALS CORP | TKYHHC904 | HARLEM BOILER PLANT REPLACEMENT AND COMBINED HEAT AND POWER | ROUTINE RECONSTRUCTION |  | HO-0214 PU-0025 HO-D003 |  | 506 LENNOX AVENUE. NEW YORK NY 10037 | HARLEM BOILER PLANT | 2022 | 33568 | 0 | 10693 | 22375 | 500 | 0 | 0 | 0 | 33568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP502 | DEP - WARDS ISLAND SHAFT MIXERS | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 300 | WP-0112 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WARDS ISLAND SHAFT MIXERS | 2022 | 6568 | 6931.25 | 61 | 0 | 0 | 0 | 0 | 0 | 6992.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED677 | WM work in 10th Ave, Union Sq E, FDR Drive, MN | AUGMENTATION OF WATER SUPPLY SYSTEMS | 304 | WM-0001 |  |  | WATER MAIN WORK IN 10TH AVENUE, UNION SQUARE EAST, AND FDR DRIVE AREA, MANHATTAN. | 2022 | 10612 | 0 | 0 | 0 | 10612 | 0 | 0 | 0 | 10612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED680 | Dist & Trunk WM in Broadway btwn W 60 ST & W 64 ST, MN | TRUNK AND DISTRIBUTION MAIN EXTENSION | 304 307 | WM-0001 WM-0006 |  |  | DISTRIBUTION AND TRUNK WATER MAINS IN BROADWAY BETWEEN W 60 ST AND W 64 STREET, IN MANHATTAN. | 2022 | 17702 | 0 | 0 | 0 | 17702 | 0 | 0 | 0 | 17702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED681 | Dist WM work in W 34 St from 7th to 9th Ave, MN | AUGMENTATION OF WATER SUPPLY SYSTEMS | 304 306 | WM-0001 |  |  | DISTRIBUTION WATER MAIN WORK IN WEST 34TH STREET FROM 7TH AVENUE TO 9TH AVENUE, MANHATTAN. | 2022 | 17251 | 0 | 0 | 0 | 17251 | 0 | 0 | 0 | 17251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED682 | WM work in Central Park W btwn W 81 & 85 Streets, MN | AUGMENTATION OF WATER SUPPLY SYSTEMS | 307 | WM-0001 |  |  | DEP-SOGR DISTRIBUTION WATER MAIN REPLACEMENT. WATER MAIN WORK IN CENTRAL PARK WEST BETWEEN WEST 81ST STREET AND WEST 85TH STREET, MANHATTAN. | 2022 | 7174 | 0 | 0 | 0 | 0 | 6238 | 0 | 0 | 6238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | MED683 | Dist Trunk WM Rplmt at Broadway & W 135 St, Manhattan | AUGMENTATION OF WATER SUPPLY SYSTEMS | 309 311 312 | WM-0001 WM-0006 |  |  | DISTRIBUTION AND TRUNK WATER MAIN REPLACEMENT IN THE INTERSECTION OF BROADWAY AND WEST 135TH STREET AND OTHER LOCATUIONS IN MANHATTAN. THISPROJECT WILL BE DONE IN CONJUNCTION WITH NYCDOT PROJECT HWCSCHPMN. | 2022 | 6545 | 0 | 718 | 5597 | 0 | 0 | 0 | 0 | 6315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-111-L | RECONSTRUCTION OF PRIMARY TANKS AT NORTH RIVER WPCP | PLANT UPGRADING AND RECONSTRUCTION | 300 309 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WEST 135TH STREET & 12TH AVENUE, MANHATTANVILLE STSTION, NEW YORK, N.Y. 10027 | RECONSTRUCTION OF PRIMARY TANKS AT NORTH RIVER WPCP | 2022 | 38154 | 826.04 | 0 | 0 | 0 | 0 | 0 | 79000 | 79826.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-115-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP | PLANT UPGRADING AND RECONSTRUCTION | 300 309 | WP-0112 |  | 135TH ST., & 12TH AVENUE, MAHNATTANVILLE STATION, N.Y., N.Y. 10027 | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ NORTH RIVER WWTP | 2022 | 36505 | 2841.18 | 0 | 0 | 6200 | 0 | 6200 | 68000 | 83241.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-117-L | RECONST OF FIRE PROTECTION SYSTEM @ THE NORTH RIVER WWTP | PLANT UPGRADING AND RECONSTRUCTION | 300 309 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 135TH STREET AND 12TH AVENUE, MANHATTANVILLE STATION, N.Y, N.Y. 10027 | RECONSTRUCTION OF FIRE PROTECTION SYSTEM @ THE NORTH RIVER WWTP | 2022 | 3100 | 0 | 0 | 0 | 3000 | 0 | 0 | 33000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-124 | RECONSTRUCT DIGESTER GAS SYSTEM AT NORTH RIVER WPCP | PLANT UPGRADING AND RECONSTRUCTION | 300 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECONSTRUCT DIGESTER GAS SYSTEM AT NORTH RIVER WPCP | 2022 | 15000 | 0 | 0 | 0 | 3000 | 0 | 0 | 15000 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-129 | RECONS MAIN SEWAGE PUMPS & PIPING/VALVES AT NORTH RIVER WPCP | PLANT UPGRADING AND RECONSTRUCTION | 300 | WP-0112 |  |  | RECONS MAIN SEWAGE PUMPS & PIPING/VALVES AT NORTH RIVER WPCP | 2022 | 30000 | 0 | 0 | 6250 | 0 | 0 | 68750 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-131-L | RECONSTRUCTION OF MAIN HYDRAULIC SYSTEM @ NORTH RIVER WWTP | PLANT UPGRADING AND RECONSTRUCTION | 300 | WP-0112 |  | 725 W. 135TH STREET, NEW YORK, N.Y. 10031 | REMOVE EXISTING MAIN HYDRAULIC SYSTEM AND INSTALL TEN (10) INDIVIDUALACTUATORS FOR THE SIX (6) SCREENING SLUICE GATES , AND FOUR (4) FOREBAY GATES. THIS SCOPE INCLUDES NEW PLC, REWIRING ABOVE FLOOD LEVEL PLIAN, PLC RELAY BACKUP BOARDS AND MANUAL OPERATION OPTION. | 2022 | 5665 | 7315.29 | 48 | 0 | 0 | 0 | 0 | 0 | 7363.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-33 | PROCESS CONTROL | CONSENT DECREE UPGRADING AND CONSTRUCTION | 399 | WP-0164 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NA |  | 2022 | 146790 | 189813.55 | 258 | 0 | 0 | 0 | 0 | 0 | 190071.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-99-L | REHAB NORTH RIVER INFLUENT/EFFUENT GATES & BAR SCREENS | PLANT UPGRADING AND RECONSTRUCTION | 300 309 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECONSTRUCTION OF SCREEN CHANNEL INFLUENT GATES AT NORTH RIVER WPCP | 2022 | 8200 | 0 | 0 | 0 | 1000 | 0 | 0 | 8000 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-CH2O | FORMALDEHYDE MITIGATION @ NORTH RIVER WRRF | PLANT UPGRADING AND RECONSTRUCTION | 300 | WP-0112 |  |  | FORMALDEHYDE MITGATION AT NORTH RIVER WATER RESOURCE RECOVERY FACILITY | 2022 | 50000 | 0 | 2500 | 2500 | 0 | 5000 | 40000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-COGEN | NORTH RIVER WWTP COGENERATION AND ELECTRIFICATION | PLANT COMPONENT STABILIZATION | 300 309 | WP-0164 |  |  | BASED ON THE FEBRUARY 2012 INVESTMENT GRADE FEASIBILITY STUDY FOR COGENERATION AT THE NORTH RIVER WWTP IT HAS BEEN IDENTIFIED THAT ELECTRIFICATION OF THE PLANT AND INSTALLATION OF COGENERATION FACILITIES SHOULD BE PURSUED TO IMPROVE OPERATIONS AND RELIABILITY, REDUCE GREENHOUSE GAS EMISSIONS, AND PROVIDE COST EFFECTIVE SOLUTIONS OVER THE EXISTING ENGINE DRIVEN PUMP AND BLOWER SYSTEMS. THE MOST COST EFFECTIVE ALTERNATIVE FOR COGENERATION AT THE NORTH RIVER WWTP IS THE 10 MW COGENERATION | 2022 | 319977 | 315518.02 | 20682 | 0 | 0 | 0 | 0 | 0 | 336200.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-GBT-L | INSTALLATION OF GRAVITY BELT THICKENERS @ NR WRRF | PLANT UPGRADING AND RECONSTRUCTION | 300 | WP-0112 |  |  | FREE AMMONIA TOXICITY - INSTALLATION OF GRAVITY BELT THICKENERS @ NR WRRF | 2022 | 50000 | 0 | 0 | 0 | 4200 | 0 | 0 | 45800 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | NR-STRUCT | STRUCTURAL IMPROVEMENTS AT NORTH RIVER WPCP | PLANT UPGRADING AND RECONSTRUCTION | 300 309 | WP-0164 |  |  | STRUCTURAL IMPROVEMENTS TO THE ROOF, INTERMEDIATE STRUCTURE AND UNDERDECK OF THE NORTH RIVER WPCP | 2022 | 360000 | 39740.45 | 0 | 0 | 49500 | 0 | 0 | 400000 | 489240.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-278 | PARK DRIVE EAST | PLANT UPGRADING AND RECONSTRUCTION | 300 | WP-0269 |  | PARK DRIVE EAST | PARK DRIVE EAST | 2022 | 5000 | 0 | 0 | 0 | 40600 | 0 | 0 | 0 | 40600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-289 | 19TH STREET PUMPING STATION | PLANT UPGRADING AND RECONSTRUCTION | 300 306 | WP-0269 |  | 19TH STREET PUMPING STATION | 19TH STREET PUMPING STATION | 2022 | 4690 | 0 | 0 | 0 | 0 | 22000 | 0 | 0 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-324 | RECONSTRUCTION OF CANAL STREET PUMPING STATION, MANHATTAN | PLANT UPGRADING AND RECONSTRUCTION | 300 | WP-0269 |  | IN FRONT OF 417 CANAL STREET AT VARICK STREET, MANHATTAN, NEW YORK 10013 | RECONSTRUCTION OF CANAL STREET PUMPING STATION, MANHATTAN, NEW YORK | 2022 | 5200 | 170 | 0 | 22000 | 0 | 0 | 0 | 0 | 22170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-348 | REHABILITATION OF DAMAGED NORTH RIVER INTERCEPTOR | PLANT UPGRADING AND RECONSTRUCTION | 300 | WP-0269 |  |  | REHABILITATION OF DAMAGED NORTH RIVER INTERCEPTOR | 2022 | 1150 | 588 | 0 | 0 | 562 | 4680 | 0 | 0 | 5830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDNR | STORM MITIGATION WORK ATTHE NORTH RIVER WPCP | PLANT UPGRADING AND RECONSTRUCTION | 300 309 | WP-0164 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | INSTALLATION AND CONSTRUCTION OF STORM MITIGATION WORK AT THE NORTH RIVER WATER POLLUTION CONTROL PLANT | 2022 | 3000 | 500 | 0 | 0 | 0 | 0 | 0 | 2574 | 3074 | 8721.28 | 0 | 0 | 0 | 0 | 0 | 12520 | 21241.28
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SEN002180 | Replcmt of combined sewers & dist WM in West 33 St MH | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 304 | SE-0002M WM-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACEMENT OF COMBINED SEWERS AND DISTRIBUTION WATER MAINS IN WEST 33RD STREET BETWEEN 11TH AVENUE AND 12TH AVENUE BOROUGH OF MANHATTAN | 2022 | 11364 | 0 | 0 | 0 | 0 | 11364 | 0 | 0 | 11364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | SHAFT21 | RECONSTRUCTION OF SHAFT 21, MANHATTAN, Cont., 602 | FACILITY PURCHASES AND RECONSTRUCTION | 303 | EP-0006 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2022 | 29116 | 8675.62 | 300 | 0 | 0 | 0 | 0 | 0 | 8975.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WFF-CPR | WATER EFICIENCY UPGRADES AT CENTRAL PARK RECIRCULATION | WATER FOR THE FUTURE | 300 | EP-0009 |  |  | WATER EFFICIENCY UPGRADES AT CENTRAL PARK RECIRCULATION | 2022 | 14246 | 0 | 0 | 0 | 14246 | 0 | 0 | 0 | 14246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-279-L | INSTALLATION OF EMERGENCY GENERATORS AT WARDS ISAND WPCP | PLANT UPGRADING AND RECONSTRUCTION | 300 | WP-0112 |  | WARDS ISLAND, NEW YORK, N.Y. 10035 | INSTALLATION OF EMERGENCY GENERATORS AT WARDS ISLAND WPCP | 2022 | 96500 | 847.3 | 0 | 0 | 7000 | 0 | 0 | 67000 | 74847.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-281-L | RECONSTRUCTION OF (39) FINAL TANKS AT WARDS ISLAND | PLANT UPGRADING AND RECONSTRUCTION | 300 311 | WP-0112 |  | WARDS ISLAND, NEW YORK, N.Y. 10035 | RECONSTRUCTION OF (39) FINAL TANKS AT WARDS ISLAND WPCP | 2022 | 87240 | 144151.51 | 1386 | 0 | 0 | 0 | 0 | 0 | 145537.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-284-L | RECONSTRUCTION OF PRIMARY TANKS AT WARDS ISLAND WPCP | PLANT UPGRADING AND RECONSTRUCTION | 300 311 | WP-0112 |  | WARDS ISLAND NEW YORK, N.Y 10035 | RECONSTRUCTION OF PRIMARY TANKS AT WARDS ISLAND WPCP | 2022 | 35633 | 7334.72 | 0 | 94520 | 0 | 0 | 0 | 0 | 101854.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-288-L | RECONSTRUCT MAIN SEWAGE PUMPS AT WARDS ISLAND WPCP | PLANT UPGRADING AND RECONSTRUCTION | 300 311 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WARDS ISLAND WPCP - WARDS ISLAND, NEW YORK, N.Y. 10035 | RECONSTRUCTION OF MAIN SEWAGE PUMPS AT WARDS ISLAND WPCP | 2022 | 6545 | 6423.84 | 515 | 0 | 0 | 0 | 0 | 0 | 6938.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-292-L | RECONSTRUCTION OF POWER DISTRIBUTION @ THE WARDS ISLAND WWTP | PLANT UPGRADING AND RECONSTRUCTION | 300 311 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WARDS ISLAND , N.Y., N.Y. 10035 | RECONSTRUCTION OF POWER DISTRIBUTION @ THE WARDS ISLAND WWTP | 2022 | 57098 | 9880.6 | 0 | 0 | 107915 | 0 | 0 | 0 | 117795.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-298-B | CONSULTANT DESIGN FOR CONVERSION OF SHARON DEMO @ WARDS ISL | BIOLOGICAL NUTRIENT REMOVAL | 300 | WP-0285 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | WARDS ISLAND WPCP - WARDS ISLAND, N.Y. 10035 | CONSULTANT DESIGN FOR THE CONVERSION OF THE SHARON DEMONSTRATION FACILITY AT THE WARDS ISLAND WASTEWAER TREATMENT FACILITY TO AN ANAMMOX MOVING BED BIOLOGICAL REACTOR (MBBR) PROCESS. | 2022 | 57276 | 4738.8 | 700 | 0 | 0 | 29000 | 0 | 0 | 34438.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-305 | RECONSTRUCTION OF FENDER @ WARDS ISLAND WPCP | PLANT UPGRADING AND RECONSTRUCTION | 300 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECONSTRUCTION OF FENDER @ WARDS ISLAND WPCP | 2022 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-307-L | RECONSTRUCTION OF SLUDGE FEED LINES @ WARDS ISLAND WWTP | PLANT UPGRADING AND RECONSTRUCTION | 300 | WP-0112 |  | WARDS ISLAND, NEW YORK 10035 | RECONSTRUCTION OF THE SLUDGE TRANSFER LINES BETWEEN THE SLUDGE STORAGE BUILDING AND DEWATERING BUILDING USING CLOSED--IN-PLACE-PIPING METHOD AND THE REPLACEMENT OF ALL ASSOCIATED PLUG VALVES AT THE WARDS ISLAND WWTP | 2022 | 4831 | 5275.25 | 991 | 0 | 0 | 0 | 0 | 0 | 6266.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-308-L | INSTALLATION OF CITY WATER LINES @ WARDS ISLAND WWTP | PLANT UPGRADING AND RECONSTRUCTION | 300 | WP-0112 |  | WARDS WPCP WARDS ISLAND, NEW YORK, N.Y. 10035 | NSTALLATION OF SECONDARY CITY WATER LINES BETWEEN THE PUMP AND BLOWERBUILDING AND THE SLUDGE STORAGE TANK BUILDING, ON THE NORTHERN SIDE OF THE PLANT AND THE RECONSTRUCTION OF SERVICE WATER PIPING FOR THE SEAL WATER SYSTEM AT WARDS ISLAND WPCP.. | 2022 | 3850 | 0 | 2862 | 0 | 0 | 0 | 0 | 0 | 2862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-310-L | RECONSTRUCTION OF RESIDUAL BUILDING @ WARDS ISLAND WWTP | PLANT UPGRADING AND RECONSTRUCTION | 300 | WP-0112 |  | WARDS ISLAND, NEW YORK, N.Y. 10035 | RESCONSTRUCTION OF RESIDUAL BUILDING AT WARDS ISLAND. RESKINNING OF EXTERIOR EXTERIOR FABRIC ALONG WITH NEW FRAMING. REMOVE OLD DAMAGED FABRICS FOR THE ENTIRE BUILDING | 2022 | 2742 | 2441.22 | 92 | 0 | 0 | 0 | 0 | 0 | 2533.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-318-L | RECONSTRUCT TWO MAIN SEWAGE PUMP RESISTOR BANKS @ WARDS ISL | PLANT UPGRADING AND RECONSTRUCTION | 300 | WP-0112 |  | WARDS ISLAND, NEW YORK, N.Y. 10035 | RECONSTRUCT/UPGRADE THE RESISTOR BANKS FOR MSP'S #2 AND #6. DEMOLITION OF THE OLD RESISTOR BANKS #2 AND #6 CONTAINING ASBESTOS. FURNISH ANDINSTALL TWO NEW RESISTOR BANKS. DEMOLITION OF 48 CONTACTORS AND FURNISH AND INSTALL 48 NEW CONTACTORS AT HE WARDS ISLAND WWTP, MANHATTAN NEW YORK. | 2022 | 2848 | 0 | 2448 | 0 | 0 | 0 | 0 | 0 | 2448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-323-L | UPGRADE MSP CC VALVE,ACTUATORS,DISCHARGE PIP REPL @ WI WRRF | PLANT UPGRADING AND RECONSTRUCTION | 300 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | UPGRADE OF MSP CONE CHECK VALVE, ACTUATORS AND DISCHARGE PIPING REPLACEMENT AT WI WRRF | 2022 | 5000 | 0 | 0 | 7008 | 0 | 0 | 0 | 0 | 7008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 826 | DEPT ENVIRONMENTAL PROTECTION | WI-EXP | INTERIM FAC & UPGRADING AT WARDS ISLAND WPCP | PLANT COMPONENT STABILIZATION | 311 | WP-0103 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MANHATTAN | THE FINAL DESIGN FOR WARDS ISLAND EXPANSION | 2022 | 1198376 | 517698.42 | 3170 | 0 | 0 | 0 | 0 | 0 | 520868.42 | 30455.42 | 0 | 0 | 0 | 0 | 0 | 0 | 30455.42
20220309 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | P-300HRP2 | HUDSON RIVER PARK - Gansevoort MOU | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 301 302 304 | P-1246 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | HUDSON RIVER PARK - GANSEVOORT MOU | 2022 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-264M | Manhattan 26th St Manhattan Borough Shop Roof Replacement | GARAGES AND FACILITIES | 300 | S-0136 |  |  | REPLACE ROOF | 2022 | 2000 | 3436.74 | 3519 | 0 | 0 | 0 | 0 | 0 | 6955.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-374R | MANHATTAN 12 HV UNITS & BOILER REPLACEMENT | GARAGES AND FACILITIES | 301 | S-0136 |  |  | HV AND BOILER REPLACEMENT | 2022 | 8327 | 0 | 518 | 1008 | 6714 | 0 | 0 | 0 | 8240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-380E | Manhattan 3 Garage HVAC System Rehabilitation | GARAGES AND FACILITIES | 303 | S-0136 |  |  | HVAC SYSTEM REHAB | 2022 | 1133 | 1845.57 | 49 | 0 | 0 | 0 | 0 | 0 | 1894.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-385E | MANHATTAN 4/4A/7 GARAGE GLASS FACADE REHABILITATION | GARAGES AND FACILITIES | 304 307 | S-0136 |  |  | REPLACEMENT OF MAJOR SECTIONS OF GLASS FACADE AND PERMANENT INSTALLATION OF SAFETY BARRIERS | 2022 | 1365 | 986.41 | 519 | 553 | 0 | 0 | 0 | 0 | 2058.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-430 | Manhattan 4039 9th Ave/W 215th St garage Rehab | GARAGES AND FACILITIES | 308 | S-0136 |  |  | REHAB | 2022 | 1800 | 1510.78 | 99 | 297 | 0 | 0 | 0 | 0 | 1906.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-430A | Manhattan 8 Smokestacks Demolition 4039 9th Ave/W 215th St | GARAGES AND FACILITIES | 308 | S-0136 |  |  | REMOVAL OF DETERIORATED AND DANGEROUS SMOKE STACKS | 2022 | 10321 | 851.08 | 5795 | 0 | 0 | 0 | 0 | 0 | 6646.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-432 | MANHATTAN 44 BEAVER ST REHABILITATION | GARAGES AND FACILITIES | 301 | S-0136 |  |  | HCF RECONSTRUCTION AT 44 BEAVER ST | 2022 | 3075 | 386.27 | 0 | 841 | 0 | 0 | 0 | 0 | 1227.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-435 | Manhattan 11 2496 Second Ave Rehab & Building Addition | GARAGES AND FACILITIES | 300 | S-0136 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REHABILITATION OF EXISTING STRUCTURE AND CONSTRUCTION OF ONE STORY ADDITION | 2022 | 20683 | 24613.19 | 3193 | 0 | 0 | 0 | 0 | 0 | 27806.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-437 | MANHATTAN 44 BEAVER ST SPRINKLER SYSTEM REPLACEMENT | GARAGES AND FACILITIES | 301 | S-0136 |  |  | INSTALLATION OF SPRINKLERS THROUGHOUT 44 BEAVER STREET | 2022 | 2500 | 597.3 | 510 | 8613 | 0 | 0 | 0 | 0 | 9720.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-440B | Bronx 7/8 Garage Slab Replacement | GARAGES AND FACILITIES | 312 | S-0136 |  |  | REMOVE AND REPLACE CEMENT FLOOR SLAB INCLUDING STRENGTHENING STRUCTURE | 2022 | 24589 | 1660.63 | 5094 | 17935 | 0 | 0 | 0 | 0 | 24689.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441B | Manhattan 4/4A/7 Garage Broom Wash Drainage | GARAGES AND FACILITIES | 304 307 | S-0136 |  |  | ADDITION OF CATCH BASIN, SUMP PUMPS, CURBS AND SLAB REHABILITATION. | 2022 | 1048 | 163.21 | 0 | 1149 | 0 | 0 | 0 | 0 | 1312.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-441S | Manhattan 4/4A/7 Garage Sprinkler System Upgrades | GARAGES AND FACILITIES | 304 307 | S-0136 |  |  | EXPANSION AND UPFRADES OF SPRINKLER SYSTEM | 2022 | 1633 | 186.61 | 0 | 1192 | 0 | 0 | 0 | 0 | 1378.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-447 | Manhattan 44 Beaver St Elevators | GARAGES AND FACILITIES | 301 | S-0136 |  |  | REPLACE ELEVATORS | 2022 | 3903 | 819.88 | 4504 | 563 | 0 | 0 | 0 | 0 | 5886.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464A | Bronx 7/8 Garage Roof Replacement | GARAGES AND FACILITIES | 312 | S-0136 |  |  | ROOF REPLACEMENT | 2022 | 2400 | 2741 | 705 | 0 | 0 | 0 | 0 | 0 | 3446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464D | Manhattan Henry St Roof Replacement | GARAGES AND FACILITIES | 303 | S-0136 |  |  | ROOF REPLACEMENT | 2022 | 1325 | 200 | 1046 | 0 | 0 | 0 | 0 | 0 | 1246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S136-464E | Manhattan 8 215th St Garage Roof and Masonry Replacement | GARAGES AND FACILITIES | 303 | S-0136 |  |  | ROOF AND MASONRY REPLACEMENT | 2022 | 2300 | 0 | 208 | 738 | 1055 | 2937 | 0 | 0 | 4938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S195-228E | Manhattan West 55th Salt Shed gate and related work | GARAGES AND FACILITIES | 304 307 | S-0195 |  |  | DESIGN OF NEW TRI-FOLD GATE FOR WEST 55TH SALT SHED M 4/4A/7 | 2022 | 722 | 297.93 | 0 | 9 | 493 | 0 | 0 | 0 | 799.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S216-401D | E. 91 ST ST MTS PIER REHAB | SOLID WASTE MANAGEMENT | 300 | S-0216 |  |  | REHAB OF UNDER PIER PIPING AND PRIVSION OF HEAT TRACING | 2022 | 1238 | 0 | 257 | 981 | 0 | 0 | 0 | 0 | 1238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S216-415C | West 59th street MTS Dredging | SOLID WASTE MANAGEMENT | 300 | S-0216 |  |  | DREDGING TO MAKE WATERWAY AROUND FACILITY NAVIGABLE | 2022 | 12600 | 2100 | 0 | 7853 | 2647 | 0 | 0 | 0 | 12600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | S236-335A | Manhattan 6/6A/8 Garage Construction | GARAGES AND FACILITIES | 306 308 | S-0236 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CONSTRUCTION OF A NEW DSNY GARAGE COMPLEX SERVING MANHATTAN DISTRICTS6, 8, AND 8A. THIS PROJECT IS 100% CITY FUNDED, NON-EXEMPT. | 2022 | 200000 | 894.76 | 0 | 0 | 0 | 0 | 0 | 199714 | 200608.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBC | Hurricane Sandy 26 St Manh Boro Rpr Shop Conduit Work | GARAGES AND FACILITIES | 300 | S-0136 |  |  | CONDUIT WORK DUE TO SANDY | 2022 | 324 | 2.29 | 1 | 9 | 53 | 0 | 0 | 0 | 65.29 | 20.67 | 10 | 69 | 473 | 0 | 0 | 0 | 572.67
20220309 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND26MBS | Hurricane Sandy 26 St Manh Boro R/R & Haz Mitigation | GARAGES AND FACILITIES | 300 | S-0136 |  |  | CAPITAL-ELIGIBLE REPLACEMENTS DUE TO HURRICANE SANDY AND ELEVATING CRIITICAL EQUIPMENT TO MITIGATE FLOOD HAZARD | 2022 | 5988 | 914.55 | 98 | 36 | 522 | 0 | 0 | 0 | 1570.55 | 0 | 0 | 322 | 3056 | 0 | 0 | 0 | 3378
20220309 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVC | Hurricane Sandy 44 Beaver Street Conduit Replacement | GARAGES AND FACILITIES | 300 | S-0136 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONDUIT WORK DUE TO HURRICANE SANDY | 2022 | 14 | 0.05 | 0 | 0 | 6 | 0 | 0 | 0 | 6.05 | 0.45 | 0 | 0 | 41 | 0 | 0 | 0 | 41.45
20220309 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SAND44BVR | Hurricane Sandy 44 Beaver St System Replacement | GARAGES AND FACILITIES | 301 | S-0136 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PUMPS, ELEVATOR CONTROLS AND OTHER REPLACEMENTS DUE TO HURRICANE SANDY | 2022 | 621 | 109.41 | 0 | 13 | 104 | 0 | 0 | 0 | 226.41 | 84.74 | 0 | 115 | 922 | 0 | 0 | 0 | 1121.74
20220309 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3C | Hurricane Sandy Manh 3 Garage Conduit Replacement | GARAGES AND FACILITIES | 303 | S-0136 |  |  | CONDUIT REPLACEMENT AT DSNY MANHATTAN 3 GARAGE AT PIER 36 | 2022 | 48 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 42
20220309 | MANHATTAN | 827 | DEPARTMENT OF SANITATION | SANDMAN3G | Hurricane Sandy Manh 3 Garage Repl & Haz Mitigation | GARAGES AND FACILITIES | 303 | S-0136 |  |  | DSNY MANHATTAN 3 GARAGE REPLACEMENT WORK DUE TO HURRICANE SANDY AND HAZARD MITIGATION INCLUDING RAISING AND RELOCATING CRITICAL EQUIPMENT | 2022 | 3843 | 0 | 0 | 0 | 366 | 0 | 0 | 0 | 366 | 0 | 0 | 0 | 3286 | 0 | 0 | 0 | 3286
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT504 | Replacement of Park, Highway and Flood Lights with LEDs | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT |  | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACEMENT OF EXISTING HIGH PRESSURE SODIUM (HPS) IN PARKS, PLAYGROUNDS (FLOOD LIGHTS) AND HIGHWAYS WITH ENERGY EFFICIENT, LONG LIFE LED FIXTURES. | 2022 | 16598 | 16071.32 | 0 | 0 | 0 | 0 | 3514 | 0 | 19585.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT602 | DOT - Various locations- Rooftop Solar | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | HW-0003 PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DOT - VARIOUS LOCATIONS : ROOFTOP SOLAR PHOTOVOLTAIC SYSTEMS | 2022 | 515 | 415.97 | 57 | 0 | 0 | 1 | 0 | 0 | 473.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | E34CCTV | East 34th St Ferry Landing CCTV upgrade | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 300 | FA-0027 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CCTV UPGRADE | 2022 | 4314 | 0 | 0 | 185 | 0 | 0 | 0 | 0 | 185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | EMIDTWNRZ | East Midtown Rezoning | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | EAST MIDTOWN REZONING | EAST MIDTOWN REZONING | 2022 | 18730 | 0 | 0 | 0 | 0 | 0 | 0 | 8257 | 8257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | FAWTCCTV | WHT Terminal CCTV Upgrades | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 300 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WHT TERMINAL CCTV UPGRADES | 2022 | 1500 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBINSPSSC | South Stuy Cove - Captain Brown Walk | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 300 | PU-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SOUTH STUY COVE - CAPTAIN BROWN WALK | SOUTH STUY COVE - CAPTAIN BROWN WALK | 2022 | 3394 | 0 | 3394 | 0 | 0 | 0 | 0 | 0 | 3394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1027 | HARLEM RV DRIVE VIADUCT: 127TH ST - 2ND AVE #2-23305-9/TN,,, | FAIR BRIDGES | 311 | HB-1027 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HARLEM RIVER DR VIADUCT: 127TH ST TO 2ND AVE, MANHATTAN | RECONSTRUCTION AND REHABILITATION OF THE HARLEM RIVER DRIVE VIADUCTREPLACEMENT OF DECK, INCLUSIVE OF ANY INCIDENTAL STEEL WORK, CURBS ANDSIDEWALK THE FUNDING FOR THIS PROJECT IS ALL CITY | 2022 | 94722 | 41260.41 | 0 | 182 | 0 | 0 | 0 | 0 | 41442.41 | 120951.45 | 0 | 2116 | 0 | 0 | 0 | 0 | 123067.45
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1120B | 11TH AVENUE VIADUCT NORTH SECTION - 33 ST to 35 ST #2245010 | FAIR BRIDGES | 304 | HB-1120 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | REPLACEMENT (NORTH SECTION) OF THE 11TH AVENUE VIADUCT BETWEEN WEST 33RD AND WEST 35TH STREETS | REPLACEMENT (NORTH SECTION) OF THE 11TH AVENUE VIADUCT BETWEEN WEST 33RD AND WEST 35TH STREETS | 2022 | 85076 | 339.5 | 0 | 0 | 0 | 0 | 76437 | 0 | 76776.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1147 | BROADWAY BRIDGE/HARLEM RIVER (BIN 2-24013-7) | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 312 | HB-1147 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | N/A |  | 2022 | 36746 | 34949.07 | 10158 | 3758 | 11183 | 0 | 0 | 0 | 60048.07 | 87436.71 | 12354 | 1794 | 1329 | 0 | 0 | 0 | 102913.71
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1165 | RIVERSIDE DRIVE BR/WEST 158TH 2-24672-0 | FAIR BRIDGES | 312 | HB-1165 HB-1012 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2022 | 23896 | 51972.79 | 9398 | 12650 | 0 | 0 | 0 | 0 | 74020.79 | 80983.33 | 0 | 0 | 0 | 0 | 0 | 0 | 80983.33
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1189 | WEST 79TH STREET/ AMTRAK (7 BIN#'S) | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 307 | HB-1189 P-1018 P-0508 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NA |  | 2022 | 59995 | 171893.91 | 18926 | 6471 | 1000 | 0 | 0 | 0 | 198290.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1212 | REHAB OF PARK AVE VIADUCT, NORTH SIDE OF EAST 42ND STREET | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 306 | HB-1212 TF-0002 HW-0001M | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | REHAB OF PARK AVE VIADUCT | REHAB OF PARK AVE VIADUCT | 2022 | 16995 | 25924.11 | 2279 | 0 | 0 | 0 | 0 | 195 | 28398.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM1221 | E25TH STREET PEDESTRIAN BRIDGE OVER FDR | FAIR BRIDGES | 306 | HB-1221 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | E25TH STREET PEDESTRIAN BRIDGE OVER FDR | E25TH STREET PEDESTRIAN BRIDGE OVER FDR | 2022 | 9785 | 924.19 | 0 | 0 | 700 | 0 | 9276 | 0 | 10900.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM191TUN | 191st St Pedestrian Tunnel over Broadway & IRT #1 Subway | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 300 | HB-1012 HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 191ST ST PEDESTRIAN TUNNEL OVER BROADWAY & IRT #1 SUBWAY | 191ST ST PEDESTRIAN TUNNEL OVER BROADWAY & IRT #1 SUBWAY | 2022 | 47000 | 2261.41 | 0 | 2558 | 43000 | 0 | 0 | 0 | 47819.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM224624 | WEST DRIVE OVER TRANSVERSE ROAD #2 BIN 2246240 | FAIR BRIDGES | 300 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WEST DRIVE OVER TRANSVERSE ROAD #2 | WEST DRIVE OVER TRANSVERSE ROAD #2 | 2022 | 30945 | 0 | 0 | 0 | 0 | 3438 | 0 | 27507 | 30945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM224625 | EAST DRIVE OVER TRANSVERSE ROAD #3 BIN 2246250 | FAIR BRIDGES | 300 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | EAST DRIVE OVER TRANSVERSE ROAD #3 | EAST DRIVE OVER TRANSVERSE ROAD #3 | 2022 | 20470 | 0 | 0 | 0 | 2934 | 0 | 2192 | 15344 | 20470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM224627 | EAST DRIVE OVER TRANSVERSE ROAD #4 BIN 2246270 | FAIR BRIDGES | 300 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | EAST DRIVE OVER TRANSVERSE ROAD #4 | EAST DRIVE OVER TRANSVERSE ROAD #4 | 2022 | 100608 | 0 | 0 | 0 | 11623 | 0 | 14831 | 74154 | 100608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM224628 | WEST DRIVE OVER TRANSVERSE ROAD #4 BIN 2246280 | FAIR BRIDGES | 300 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WEST DRIVE OVER TRANSVERSE ROAD #4 | WEST DRIVE OVER TRANSVERSE ROAD #4 | 2022 | 20799 | 0 | 0 | 0 | 0 | 2844 | 0 | 17955 | 20799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM224643 | W 110TH ST ENT (MTCLIFF ARCH) PED PATH OPP W 109ST B#2246430 | FAIR BRIDGES | 300 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WEST 110TH ST ENT (MOUNTCLIFF ARCH) PED PATH OPP WEST 109 ST | WEST 110TH ST ENT (MOUNTCLIFF ARCH) PED PATH OPP WEST 109 ST | 2022 | 7203 | 0 | 0 | 0 | 0 | 2434 | 596 | 4173 | 7203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM224650 | FORT TRYON PLACE ENTRANCE FROM RIVERSIDE DRIVE BIN 2246500 | FAIR BRIDGES | 300 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | FORT TRYON PLACE ENTRANCE FROM RIVERSIDE DRIVE | FORT TRYON PLACE ENTRANCE FROM RIVERSIDE DRIVE | 2022 | 15145 | 0 | 0 | 0 | 0 | 2615 | 1566 | 10964 | 15145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM245070 | West 38th St over Amtrak 30 St Branch BIN 2245070 | FAIR BRIDGES | 300 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WEST 38TH ST OVER AMTRAK 30 ST BRANCH BIN 2245070 | WEST 38TH ST OVER AMTRAK 30 ST BRANCH BIN 2245070 | 2022 | 35323 | 0 | 0 | 4083 | 0 | 0 | 2599 | 28641 | 35323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM245080 | West 39th St over Amtrak 30 St Branch BIN 2245080 | FAIR BRIDGES | 300 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WEST 39TH ST OVER AMTRAK 30 ST BRANCH BIN 2245080 | WEST 39TH ST OVER AMTRAK 30 ST BRANCH BIN 2245080 | 2022 | 35719 | 0 | 0 | 4146 | 0 | 0 | 2640 | 28933 | 35719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM245230 | W 148TH ST PED BR OVER AMTRAK 30 ST BRANCH BIN 2245230 | FAIR BRIDGES | 300 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WEST 148TH ST PED BRIDGE OVER AMTRAK 30 STREET BRANCH | WEST 148TH ST PED BRIDGE OVER AMTRAK 30 STREET BRANCH | 2022 | 12145 | 0 | 0 | 0 | 0 | 2220 | 0 | 9925 | 12145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM246350 | EAST DR OVER PED PATH OPP EAST 80TH ST BIN 2246350 | FAIR BRIDGES | 300 | P-0508 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | EAST DR OVER PED PATH OPP EAST 80TH ST BIN 2246350 | 2022 | 4598 | 508.36 | 0 | 203 | 4098 | 0 | 0 | 0 | 4809.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM551 | PARK AVE TUNNEL FROM E34TH TO E39TH ST'S #2-24654-0/TN61420 | FAIR BRIDGES | 306 | HB-0551 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECON AND REHAB OF THE PARK AVE TUNNEL FROM E34TH TO E39TH ST REPLACEMHE DECK, INCIDENTAL STEEL WORK CURBS AND SIDEWALKS THE FUNDING FOR THIIS ALL CITY | 2022 | 22424 | 45572.54 | 2332 | 2378 | 0 | 0 | 0 | 0 | 50282.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM702990 | Rehabilitation of Fort Washington Pedestrian Bridge over AMT | FAIR BRIDGES | 300 | P-0245M P-0861 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | REHABILITATION OF FORT WASHINGTON PEDESTRIAN BRIDGE OVER AMTRAK | REHABILITATION OF FORT WASHINGTON PEDESTRIAN BRIDGE OVER AMTRAK | 2022 | 5774 | 0 | 5812 | 129 | 0 | 0 | 0 | 0 | 5941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBM8650 | REHAB FDR NORTHBOUND FROM EAST 42-49TH ST BIN: 2268650 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 300 306 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REHAB FDR NORTHBOUND FROM EAST 42-49TH ST | 2022 | 97300 | 13205.17 | 0 | 64162 | 1068 | 0 | 0 | 0 | 78435.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA22934 | RAMP TO NB HHP OVER AMTRAK WEST SIDE BIN 222934A | FAIR BRIDGES | 300 | HB-2934 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RAMP TO NB HHP OVER AMTRAK WEST SIDE BIN 222934A | RAMP TO NB HHP OVER AMTRAK WEST SIDE BIN 222934A | 2022 | 53051 | 2136.62 | 0 | 1868 | 4604 | 45443 | 0 | 0 | 54051.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA23216 | Promenade over FDR E81st - 90th St Bin 2232167 | FAIR BRIDGES | 300 | P-1018 |  | PROMENADE OVER FDR E81ST - 90TH ST BIN 2232167 | PROMENADE OVER FDR E81ST - 90TH ST BIN 2232167 | 2022 | 312992 | 36302.65 | 0 | 995 | 79445 | 0 | 0 | 0 | 116742.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24501 | WEST 35TH ST/ AMTRAK 30ST BRANCH BIN# 224501E | FAIR BRIDGES | 300 | HB-1012 HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WEST 35TH ST/ AMTRAK 30ST BRANCH | WEST 35TH ST/ AMTRAK 30ST BRANCH | 2022 | 2739 | 1538.03 | 0 | 1012 | 0 | 2618 | 28003 | 0 | 33171.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24544 | WEST 40TH ST / AMTRAK 30ST BRANCH BIN# 2245440 | FAIR BRIDGES | 300 | HB-1012 HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WEST 40TH ST / AMTRAK 30ST BRANCH BIN# 2245440 | 2022 | 4407 | 2596.17 | 0 | 1935 | 0 | 3787 | 42600 | 0 | 50918.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24613 | East Dr (Willowdell Arch) over Ped Path Opp East 67th st | FAIR BRIDGES | 300 | P-0508 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | EAST DR (WILLOWDELL ARCH) OVER PED PATH OPP EAST 67TH ST | 2022 | 2543 | 499.54 | 0 | 2343 | 0 | 0 | 0 | 0 | 2842.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA24646 | W 77TH ST ENT (EAGLEVALE ARC) PED PATH OPP W 77TH ST 2246460 | FAIR BRIDGES | 300 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WEST 77TH ST ENTR (EAGLEVALE ARCH) PED PATH OPP W 77TH ST | WEST 77TH ST ENTR (EAGLEVALE ARCH) PED PATH OPP W 77TH ST | 2022 | 14619 | 0 | 0 | 0 | 0 | 2672 | 0 | 11947 | 14619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA25756 | MILLER HIGHWAY over TERRAIN BIN 2257569 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 300 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MILLER HIGHWAY OVER TERRAIN | MILLER HIGHWAY OVER TERRAIN | 2022 | 277192 | 0 | 0 | 0 | 31243 | 0 | 0 | 245949 | 277192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA26724 | Trans-Manhattan Expressway BIN 2267240 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 300 | HB-1078 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | REHAB OF TRANS MANHATTAN EXPRESSWAY CONNECTOR | REHAB OF TRANS MANHATTAN EXPRESSWAY CONNECTOR | 2022 | 429583 | 8534.54 | 25471 | 0 | 0 | 0 | 351077 | 0 | 385082.54 | 0 | 0 | 0 | 0 | 0 | 45000 | 0 | 45000
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA29349 | HHP over West 158th St BIN 2229349 | FAIR BRIDGES | 300 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HHP OVER WEST 158TH ST BIN 2229349 | HHP OVER WEST 158TH ST BIN 2229349 | 2022 | 0 | 0 | 0 | 0 | 17232 | 0 | 0 | 149271 | 166503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA4501D | West 34Th St over Amtrak 30 St Branch BIN 224501D | FAIR BRIDGES | 300 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WEST 34TH ST OVER AMTRAK 30 ST BRANCH BIN 224501D | WEST 34TH ST OVER AMTRAK 30 ST BRANCH BIN 224501D | 2022 | 70243 | 0 | 0 | 6498 | 0 | 0 | 5748 | 57997 | 70243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMA4501F | West 36Th St over Amtrak 30 St Branch BIN 224501F | FAIR BRIDGES | 300 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WEST 36TH ST OVER AMTRAK 30 ST BRANCH BIN 224501F | WEST 36TH ST OVER AMTRAK 30 ST BRANCH BIN 224501F | 2022 | 36767 | 0 | 0 | 3954 | 0 | 0 | 2743 | 30070 | 36767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBMFDNY20 | FDNY/NFPA CODE UPDATE HHP VARIOUS AND PARK AVE TUNNEL | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 300 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FDNY/NFPA CURRENT CODE UPDATE HHP VARIOUS SECTIONS AND PARK AVE TUNNEL | 2022 | 61000 | 2746.04 | 0 | 2221 | 57200 | 0 | 0 | 0 | 62167.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HBRIBIKE | Roosevelt Island Bridge Bike Lane | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 300 | HW-D102 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | ROOSEVELT ISLAND BRIDGE BIKE LANE | ROOSEVELT ISLAND BRIDGE BIKE LANE | 2022 | 150 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR19D | Citywide Milling - Manhattan | PRIMARY STREET RESURFACING | 300 | HW-0002M | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITYWIDE MILLING- MANHATTAN | 2022 | 5958 | 11378.25 | 6290 | 0 | 0 | 0 | 0 | 0 | 17668.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR21D | Citywide Milling - Manhattan | PRIMARY STREET RESURFACING | 300 | HW-0002M | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITYWIDE MILLING - MANHATTAN | 2022 | 1130 | 0 | 1130 | 0 | 0 | 0 | 0 | 0 | 1130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10216 | Walk of Fame -- Walk of Fame installation in CD 8 | PRIMARY STREET RECONSTRUCTION | 300 | HW-D102 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WALK OF FAME -- WALK OF FAME INSTALLATION IN CD 8 | WALK OF FAME -- WALK OF FAME INSTALLATION IN CD 8 | 2022 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10217 | SAFETY IMPROVEMENTS | PRIMARY STREET RECONSTRUCTION | 300 | HW-D102 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SAFETY IMPROVEMENTS | SAFETY IMPROVEMENTS | 2022 | 50 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD10220 | DOT - 3rd Avenue Sidewalks | PRIMARY STREET RECONSTRUCTION | 300 | HW-D102 HW-0001M | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | DOT - 3RD AVENUE SIDEWALKS | DOT - 3RD AVENUE SIDEWALKS | 2022 | 2200 | 0 | 0 | 0 | 0 | 0 | 9529 | 0 | 9529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWD200-05 | Sidewalk Reconstruction, 125th St & Lexington | PRIMARY STREET RECONSTRUCTION | 300 | HW-D200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SIDEWALK RECONSTRUCTION, 125TH ST & LEXINGTON | SIDEWALK RECONSTRUCTION, 125TH ST & LEXINGTON | 2022 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM100CTN | 23rd St Crosstown SBS | PRIMARY STREET RECONSTRUCTION | 300 | HW-1684 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 14TH ST OR 23RD ST CROSSTOWN SBS | 14TH ST OR 23RD ST CROSSTOWN SBS | 2022 | 7750 | 0 | 0 | 0 | 0 | 0 | 0 | 7750 | 7750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1048 | Manhattan Waterfront Greenway - Inwood 10th Ave | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MANHATTAN WATERFRONT GREENWAY - INWOOD 10TH AVE | MANHATTAN WATERFRONT GREENWAY - INWOOD 10TH AVE | 2022 | 65000 | 0 | 0 | 5000 | 0 | 0 | 60000 | 0 | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1684 | Allen & Pike Street Malls Phase 2 | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | ALLEN & PIKE STREET MALLS PHASE 2 | ALLEN & PIKE STREET MALLS PHASE 2 | 2022 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1687 | Holland Tunnel Area Pedestrian Safety Improvements & Public | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HOLLAND TUNNEL AREA PEDESTRIAN SAFETY IMPROVEMENTS & PUBLIC | HOLLAND TUNNEL AREA PEDESTRIAN SAFETY IMPROVEMENTS & PUBLIC | 2022 | 12180 | 0 | 0 | 0 | 0 | 0 | 12180 | 0 | 12180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM1688 | Harlem Multi-Site | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HARLEM MULTI-SITE | HARLEM MULTI-SITE | 2022 | 15300 | 0 | 0 | 0 | 0 | 0 | 15300 | 0 | 15300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM2026 | YESHIVA UNIVERSITY AMSTERDAM AVENUE PUBLIC PLAZA | PRIMARY STREET RECONSTRUCTION | 300 | HW-D102 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | YESHIVA UNIVERSITY AMSTERDAM AVENUE PUBLIC PLAZA | YESHIVA UNIVERSITY AMSTERDAM AVENUE PUBLIC PLAZA | 2022 | 100 | 0 | 1500 | 0 | 0 | 0 | 100 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWM300 | BLEECKER ST. | PRIMARY STREET RECONSTRUCTION | 300 302 | HW-0001M | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BLEECKER ST. | BLEECKER ST. | 2022 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMBRT5 | 34th STREET | TRAFFIC WORK IN CONJUNCTION WITH HIGHWAY RECONSTRUCTION | 300 304 305 306 | TF-0777 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 34TH STREET | 34TH STREET | 2022 | 25000 | 270.34 | 0 | 0 | 0 | 0 | 0 | 1861 | 2131.34 | 2433.09 | 0 | 0 | 0 | 0 | 0 | 0 | 2433.09
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMBRT6 | 1st & 2nd Avenue | TRAFFIC WORK IN CONJUNCTION WITH HIGHWAY RECONSTRUCTION | 300 | TF-0777 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 1ST & 2ND AVENUE | 1ST & 2ND AVENUE | 2022 | 33608 | 2215.74 | 0 | 0 | 0 | 0 | 0 | 3171 | 5386.74 | 10064.32 | 0 | 0 | 0 | 0 | 0 | 0 | 10064.32
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMM009 | GATEWAYS TO CHINATOWN | PRIMARY STREET RECONSTRUCTION | 300 301 302 303 | HW-0001M HW-D102 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CHINA TOWN PARTNERSHIP LOCAL DEVELOPMENT CORP. I NC. | CHINA TOWN PARTNERSHIP LOCAL DEVELOPMENT CORP. I NC. | 2022 | 314 | 198 | 0 | 75 | 0 | 0 | 0 | 0 | 273 | 148.38 | 0 | 650 | 0 | 0 | 0 | 0 | 798.38
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A8 | WORLD TRADE CENTER AREA 8 | PRIMARY STREET RECONSTRUCTION | 300 301 | HW-1670 HW-0200 TF-0002 TF-0502 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RECONSTRUCTION OF WORLD TRADE CENTER | RECONSTRUCTION OF WORLD TRADE CENTER AREA 8. | 2022 | 12504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8566 | 8566
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC A9 | WORLD TRADE CENTER AREA 9. | PRIMARY STREET RECONSTRUCTION | 300 301 | HW-1670 HW-0200 TF-0502 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RESURFACING WTC AREA 9 | RESURFACING WORLD TRADE CENTER AREA 9. | 2022 | 36299 | 0 | 0 | 0 | 0 | 0 | 0 | 1072 | 1072 | 0 | 0 | 0 | 0 | 0 | 0 | 34695 | 34695
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTC11 | WORLD TRADE CENTER AREA 11 | PRIMARY STREET RECONSTRUCTION | 301 | HW-1670 HW-0200 TF-0002 TF-0502 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RECONSTRUCTION OF WORLD TRADE CENTER AREA 11 | RECONSTRUCTION OF WORLD TRADE CENTER AREA 11 | 2022 | 306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186 | 186
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCA10 | WORLD TRADE CENTER AREA 10 | PRIMARY STREET RECONSTRUCTION | 301 | HW-1670 HW-0200 TF-0002 TF-0502 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RECONSTRUCTION OF WORLD TRADE CENTER AREA 10 | RECONSTRUCTION OF WORLD TRADE CENTER AREA 10 | 2022 | 770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 770 | 770
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB3 | Reconstruction of Broadway | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RECONSTRUCTION OF BROADWAY | RECONSTRUCTION OF BROADWAY | 2022 | 10640 | 0 | 0 | 0 | 0 | 0 | 0 | 2128 | 2128 | 0 | 0 | 0 | 0 | 0 | 0 | 8512 | 8512
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWMWTCB4 | Reconstruction of Varick St | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RECONSTRUCTION OF VARICK ST | RECONSTRUCTION OF VARICK ST | 2022 | 397 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 317 | 317
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ010M | Flatiron Plaza Reconstruction | LOCAL STREET RECONSTRUCTION | 300 305 | HW-0001M HW-1684 HW-D102 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | FLATIRON PLAZA RECONSTRUCTION | FLATIRON PLAZA RECONSTRUCTION | 2022 | 200 | 40 | 0 | 0 | 0 | 0 | 0 | 9975 | 10015 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 300
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ014M | Broadway Boulevard | PRIMARY STREET RECONSTRUCTION | 300 | HW-1684 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BROADWAY BOULEVARD | BROADWAY BOULEVARD | 2022 | 18700 | 0 | 0 | 0 | 0 | 0 | 26700 | 0 | 26700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ016M | Hamilton Place Plaza | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HAMILTON PLACE PLAZA | HAMILTON PLACE PLAZA | 2022 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWPSMGANC | Gansevoort/Astor Planters | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | GANSEVOORT/ASTOR PLANTERS | GANSEVOORT/ASTOR PLANTERS | 2022 | 800 | 0 | 0 | 635 | 0 | 0 | 0 | 0 | 635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWTFLMAD | Street Lamp Posts on Madison Avenue | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 300 | TF-0502 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | STREET LAMP POSTS ON MADISON AVENUE | STREET LAMP POSTS ON MADISON AVENUE | 2022 | 236 | 0 | 0 | 236 | 0 | 0 | 0 | 0 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | HWWTCLUMP | World Trade Center - Lump Sum | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WORLD TRADE CENTER - LUMP SUM | WORLD TRADE CENTER - LUMP SUM | 2022 | 23630 | 0 | 0 | 0 | 0 | 0 | 0 | 33326 | 33326 | 0 | 0 | 0 | 0 | 0 | 0 | 49504 | 49504
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | NDF-IW10A | NDF - Improve Prioroity intersections along 10th Ave | NEIGHBORHOOD REVITALIZATION | 300 | ED-0384 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NDF - IMPROVE PRIOROITY INTERSECTIONS ALONG 10TH AVE | 2022 | 17417 | 0 | 0 | 0 | 0 | 0 | 17417 | 0 | 17417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | NDF-IWEIS | NDF - EIS Transportation Mitigation Inwood | NEIGHBORHOOD REVITALIZATION | 300 | ED-0384 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NDF - EIS TRANSPORTATION MITIGATION INWOOD | 2022 | 2000 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | NDF-IWHRG | NDF - Harlem River Drive Gateway | NEIGHBORHOOD REVITALIZATION | 300 | ED-0384 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NDF - IMPROVE PRIOROITY INTERSECTIONS ALONG 10TH AVE | 2022 | 10583 | 0 | 0 | 3603 | 0 | 6980 | 0 | 0 | 10583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | P-3RVOVER | Rec of the Riverside Park Amtrak Overbuild 2271180 & 2271190 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-0508 |  |  | RECONSTRUCTION OF THE OVERBUILD STRUCTURE IN RIVERSIDE PARK (NORTH AND SOUTH SECTIONS OVER AMTRAK) | 2022 | 151000 | 0 | 0 | 42500 | 0 | 42000 | 263500 | 0 | 348000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | REALTIMEM | Real Time Traffic Monitoring in Lower Manhattan | SIGNAL INSTALLATION AND COMPUTERIZATION | 300 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REAL TIME SYSTEM FOR LOWER MANHATTAN | 2022 | 2800 | 3115.26 | 0 | 0 | 500 | 392 | 0 | 0 | 4007.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | REALTMIDM | Expand Real Time Traffic Monitoring in Midtown Manhattan | SIGNAL INSTALLATION AND COMPUTERIZATION | 300 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | TRAFFIC MONITORING IN MANHATTAN | 2022 | 9480 | 4704 | 250 | 0 | 0 | 2000 | 1369 | 2250 | 10573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHB2U | SANDY ER BETTERMENTS FOR BATTERY PARK & WEST ST UNDERPASSES | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 300 | HB-0215 |  |  | SANDY ER BETTERMENTS FOR BATTERY PARK & WEST ST UNDERPASSES | 2022 | 18850 | 825.99 | 2723 | 10141 | 0 | 0 | 0 | 0 | 13689.99 | 1898.53 | 1921 | 37534 | 0 | 0 | 0 | 0 | 41353.53
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHBFDR | SANDY ER FOR FDR 18TH TO 25TH STREET | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 300 | HB-0215 |  |  | SANDY ER BETTERMENTS FOR FDR 18TH TO 25TH STREET | 2022 | 8414 | 1873.43 | 741 | 2002 | 0 | 0 | 0 | 0 | 4616.43 | 6057.6 | 1773 | 119 | 0 | 0 | 0 | 0 | 7949.6
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | SANDHW27 | Montgomery to 15th Street - Hurricane Sandy | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MONTGOMERY TO 15TH STREET - HURRICANE SANDY | MONTGOMERY TO 15TH STREET - HURRICANE SANDY | 2022 | 16130 | 0 | 0 | 0 | 0 | 0 | 0 | 3226 | 3226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFCPARKLG | Central Park Light Infrastructure | REPLACEMENT OF ELECTRICAL DISTRIBUTION SYSTEMS | 300 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CENTRA PARK LIGHT INFRASTRUCTURE | CENTRAL PARK LIGHT INFRASTRUCTURE | 2022 | 28000 | 24076.35 | 0 | 0 | 0 | 0 | 0 | 1989 | 26065.35 | 12864.12 | 0 | 0 | 1136 | 0 | 0 | 0 | 14000.12
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503-20 | DOWNTOWN ALLIANCE-HISTORIC LIGHTPOLES | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 300 301 | TF-M503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | DOWNTOWN ALLIANCE-HISTORIC LIGHTPOLES | DOWNTOWN ALLIANCE-HISTORIC LIGHTPOLES | 2022 | 383 | 518.11 | 0 | 0 | 0 | 38 | 0 | 0 | 556.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M29 | Second Avenue Street lights | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 300 | TF-D503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 2ND AVENUD LIGHT | 2022 | 434 | 257.89 | 0 | 0 | 0 | 176 | 0 | 0 | 433.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M30 | Garment District street light | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 300 | TF-D503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DECORATIVE LIGHTING IN GARMENT DISTRICT | 2022 | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M31 | Historic St lg on 11th St and on 12th St, Manhattan | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 300 | TF-D503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DECORATIVE LIGHT | 2022 | 70 | 54.01 | 0 | 0 | 0 | 410 | 0 | 0 | 464.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M33 | GREENWICH VILLAGE DECORATIVE LIGHTING | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 300 | TF-D503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | GREEWICH VILLAGE DECRATIVE LIGHTING | 2022 | 250 | 193.99 | 0 | 0 | 56 | 0 | 0 | 0 | 249.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFD503M34 | Lg Poles on Crosby and Bleecker- NOHO, Manhattan | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 300 | TF-D503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | OUTDOOR LIGHT POLES IN NOHO--TO SUPPORT INSTALLATION OF 4 OUTDOOR LIGHT POLES ON CROSBY AND BLEECKER | 2022 | 80 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFM50311 | INSTALL S-POLE LIGHTING- VARIOUS STREETS WEST OF BROADWAY | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 300 301 302 | TF-M503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HISTORIC LIGHTING:LINCOLN PLACE BETWEEN 6TH AND 7TH AVENUE | HISTORIC LIGHTING:LINCOLN PLACE BETWEEN 6TH AND 7TH AVENUE | 2022 | 450 | 298.94 | 0 | 0 | 0 | 151 | 0 | 0 | 449.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | TFM50316 | Frederick Douglas Blvd Street Lamps | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 300 310 | TF-M503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | STREET LAMPS LAMPS FOR FREDERICK DOUGLAS BLVD | 2022 | 198 | 236.65 | 0 | 0 | 0 | 79 | 0 | 0 | 315.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | W125STLG | W 125TH ST LG & SIGNAL-5TH AVE TO MORNINGSIDE AVE, MA2288.3 | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 300 309 310 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | INSTALLATION OF NEW DECORATIVE ST LIGHT AND STANDARD SIGNALS | 2022 | 2056 | 1166.17 | 0 | 0 | 0 | 503 | 0 | 0 | 1669.17 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 500
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | W147LIGH | West 147th Street Sugar Hill Historical Street Lights | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 310 | TF-M503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2022 | 35 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | WHTGIRDS2 | Whitehall Ferry Terminal-Slip2 Girder Reconstruction | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 300 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WHITEHALL FERRY TERMINAL - SLIP 2 GIRDER RECONSTRUCTION | 2022 | 2750 | 0 | 0 | 0 | 0 | 0 | 250 | 2500 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | WHTGIRDS3 | Whitehall Ferry Terminal-Slip3 Girder Reconstruction | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 300 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WHITEHALL FERRY TERMINAL - SLIP 3 GIRDER RECONSTRUCTION | 2022 | 3000 | 0 | 0 | 0 | 0 | 0 | 500 | 2500 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 841 | DEPARTMENT OF TRANSPORTATION | WHTLBRIDG | Whitehall Slips 1,2,3 Bridge Reconstruction | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 300 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WHITEHALL SLIPS 1,2,3 LOWER BRIDGE RECONSTRUCTION | 2022 | 5300 | 1097.18 | 0 | 0 | 0 | 0 | 4203 | 0 | 5300.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | ACEDPR408 | Centralized HVAC Controls CNYG-1317MA | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT |  | PU-0025 P-1018 P-0505 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INSTALLATION OF BUILDING CONTROLS TO OPTIMIZE HVAC SYSTEMS IN MULTIPLE FACILITES | 2022 | 1412 | 128 | 0 | 1646 | 688 | 0 | 0 | 0 | 2462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | EDMFPM | FERRY PIER AT DYCKMAN MARINA | MISCELLANEOUS | 300 | P-0501 PU-0200 P-0245M P-D018 ED-D401 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FERRY PIER AT DYCKMAN MARINA | 2022 | 5000 | 0 | 1504 | 0 | 9546 | 6215 | 0 | 5000 | 22265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-DYMAN | NDF - Highbridge Park Dyckman Rest Reconstruction M037-121M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | ED-0384 |  |  | RENOVATE DYCKMAN REST IN HIGHBRIDGE PARK, BOROUGH OF MANHATTAN | 2022 | 5000 | 262 | 42 | 4231 | 727 | 0 | 0 | 0 | 5262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-HRPCS | NDF Harlem River Park (M208D) - New Comfort Station | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | ED-0384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NDF HARLEM RIVER PARK (M208D) - NEW COMFORT STATION | 2022 | 4716 | 445.97 | 0 | 4313 | 393 | 0 | 0 | 0 | 5151.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-IWOOD | NDF - Inwood Hill Park Soccer Field #1 R/C | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 312 | ED-0384 P-D018 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RENOVATE INWOOD HILL PARK SOCCER FIELD #1 (DYCKMAN FIELDS), BOROUGH OF MANHATTAN | 2022 | 6000 | 425 | 0 | 0 | 8722 | 0 | 0 | 0 | 9147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-MKECS | NDF-Monsignor Kett Playground Comfort Station RC M199-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | ED-0384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MONSIGNOR KETT PLAYGROUND COMFORT STATION RECONSTRUCTION | 2022 | 2690 | 272.56 | 0 | 4047 | 364 | 79 | 0 | 0 | 4762.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | NDF-MKETT | NDF - Monsignor Kett Playground R/C, M199-219M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 312 | ED-0384 |  |  | REBUILD MONSIGNOR KETT PLAYGROUND, BOROUGH OF MANHATTAN | 2022 | 15186 | 591.4 | 4972 | 996 | 0 | 0 | 480 | 2898 | 9937.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300EAST | East River Esplanade Projects - M108-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | PU-0200 P-0501 PU-0026 P-1018 P-1245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF MANHATTAN | EAST RIVER ESPLANADE | 2022 | 23522 | 4277.98 | 2197 | 0 | 586 | 0 | 12767 | 0 | 19827.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ERES | East River Esplanade GLICK PK RC | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  |  | EAST RIVER ESPLANADE RECONSTRUCTION (M289-116M) | 2022 | 54 | 18.83 | 35 | 0 | 0 | 0 | 0 | 0 | 53.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300LMDC | LMDC-(BUNDLED) PROJECTS MG-703M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 301 302 304 | P-0245M | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | MANHATTAN | LOWER MANHATTAN PROJECTS | 2022 | 16499 | 2757.29 | 0 | 0 | 0 | 0 | 0 | 0 | 2757.29 | 13401.45 | 0 | 0 | 0 | 1496 | 0 | 0 | 14897.45
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO18 | Central Park Zoo - Sea Lion Exhibit Renovation | ZOOS | 300 | P-0887 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CENTRAL PARK ZOO - SEA LION EXHIBIT RENOVATION | CENTRAL PARK ZOO - SEA LION EXHIBIT RENOVATION | 2022 | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO19 | Central Park Zoo - Roofs | ZOOS | 300 | P-0887 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CENTRAL PARK ZOO - ROOFS | CENTRAL PARK ZOO - ROOFS | 2022 | 2300 | 0 | 0 | 0 | 0 | 2300 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-300ZO20 | Central Park Zoo - Tractor and attachments | ZOOS | 300 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CENTRAL PARK ZOO - TRACTOR AND ATTACHMENTS | CENTRAL PARK ZOO - TRACTOR AND ATTACHMENTS | 2022 | 103 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPBP | BATTERY PARK BIKEWAY PERIMETER M005-111M (SUPERCEDES 308M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 301 | P-0828 P-0245M | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | BATTERY PARK BIKEWAY PERIMETER | BATTERY PARK BIKEWAY PERIMETER | 2022 | 350 | 1897.57 | 0 | 0 | 0 | 0 | 0 | 0 | 1897.57 | 15190.26 | 55 | 0 | 0 | 0 | 454 | 0 | 15699.26
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPCG | Battery Park Coast Guard Memorial Relocation (M005-217M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-0828 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BATTERY PARK COAST GUARD MEMORIAL RELOCATION | BATTERY PARK COAST GUARD MEMORIAL RELOCATION | 2022 | 662 | 209 | 0 | 0 | 0 | 0 | 0 | 0 | 209 | 525.88 | 244 | 0 | 0 | 0 | 0 | 0 | 769.88
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BPOC | Battery Park Office convert to Comfort station M005 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 301 | P-0828 P-D018 P-M245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BATTERY PK OFFICE CONVERT TO COMFORT STATION | BATTERY PK OFFICE CONVERT TO COMFORT STATION | 2022 | 500 | 100 | 0 | 0 | 0 | 3665 | 0 | 0 | 3765 | 0 | 278 | 0 | 0 | 0 | 0 | 0 | 278
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301BURL | LMDC-BURLING SLIP - IMAGINATION PLGD MG-41100-107M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 301 | SE-0002M | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BURLING SLIP | BURLING SLIP | 2022 | 4125 | 4367.09 | 0 | 288 | 0 | 0 | 0 | 0 | 4655.09 | 5499.61 | 0 | 0 | 0 | 0 | 0 | 0 | 5499.61
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301EPPK | Elizabeth H. Berger Plaza, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 301 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | EDGAR PLAZA PARK - GREEN STREET | EDGAR PLAZA PARK - GREEN STREET | 2022 | 1000 | 7222.64 | -237 | 0 | 0 | 985 | 0 | 0 | 7970.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301PEAR | LMDC-PEARL ST PLGD MG-41000-107M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 301 | P-0245M | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PEARL ST PLGD | PEARL STREET PLAYGROUND | 2022 | 852 | 873.09 | 0 | 0 | 0 | 0 | 0 | 0 | 873.09 | 1868.47 | 0 | 0 | 0 | 232 | 0 | 0 | 2100.47
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301PECK | LMDC-PECK SLIP RECONSTRUCTION M167-106M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 301 | P-0245M P-1018 | PROJECT DELAYED DUE TO SCHEDULING OF UTILITY WORK | PECK SLIP RECONSTRUCTION, MANHATTAN | PECK SLIP RECONSTRUCTION, MANHATTAN | 2022 | 4030 | 1280.27 | 1 | 0 | 0 | 0 | 0 | 0 | 1281.27 | 4738.34 | 59 | 0 | 0 | 0 | 0 | 0 | 4797.34
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-301VIE2 | VIETNAM VETERANS PLAZA RC M046-114M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MANHATTAN | VIETNAM VETERANS PLAZA RC M046-114M | 2022 | 82 | 0 | 82 | 0 | 0 | 0 | 0 | 0 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302AIDM | NYC AIDS Memorial -- Capital Refurbishment to Memorial | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NYC AIDS MEMORIAL -- CAPITAL REFURBISHMENT TO MEMORIAL | 2022 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302BLEE | Bleecker Street Playground,Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  |  | BLEECKER STREET PLAYGROUND,MANHATTAN | 2022 | 1550 | 0 | 0 | 0 | 0 | 1550 | 0 | 0 | 1550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302CJSC | CORPORAL JOHN A SERAVALLI PLGD CS RC M237-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 302 | P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CORPORAL JOHN A SERAVALLI PLGD COMF STAT RECON | CORPORAL JOHN A SERAVALLI PLGD COMF STAT RECON | 2022 | 1700 | 1327.33 | 0 | 0 | 0 | 641 | 0 | 0 | 1968.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302DRYD | DRY DOCK PLAYGROUND RECON M270-110M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 302 | P-D018 P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | DRY DOCK PLAYGROUND RECON | DRY DOCK PLAYGROUND RECON | 2022 | 800 | 2024.98 | 36 | 0 | 0 | 0 | 0 | 0 | 2060.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302GLAF | DEP Shaft Site -- Grand & Lafayette Streets | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 302 | P-D018 P-M245 W-0013 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS |  | DPR - GRAND & LAFAYETTE -- CREATE A NEW PARK AT THE GRAND AND LAFAYETTE STREET DEP WATERSHAFT SITE. DEP HAS TOLD PARKS THEY CAN HAVE 5K SQ. FT. ON THE WESTERN PORTION OF THE SITE. | 2022 | 300 | 240 | 1922 | 430 | 0 | 0 | 0 | 0 | 2592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302HGLR | HIGH LINE REPAIRS | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-1326 |  |  | HIGHLINE REPAIRS | 2022 | 5214 | 0 | 0 | 517 | 0 | 4697 | 0 | 0 | 5214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302HIGH | HIGH LINE RENOVATIONS M360 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-D018 |  | HIGH LINE RENOVATIONS M360 | HIGH LINE RENOVATIONS M360 | 2022 | 3050 | 0 | 0 | 0 | 0 | 2900 | 0 | 0 | 2900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302HUHO | DEP shaft site 28B - Hudson and West Houston | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | W-0013 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | DEP SHAFT SITE 28B - HUDSON AND WEST HOUSTON | 2022 | 0 | 67.99 | 0 | 0 | 1000 | 0 | 0 | 0 | 1067.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-302MHSA | DEP Shaft Site 31B at Bowery and East 4th Street | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-D018 W-0013 P-M245 |  |  | DEP SHAFT SITE 31B AT BOWERY AND EAST 4TH STREET | 2022 | 0 | 191 | 1270 | 0 | 0 | 0 | 0 | 0 | 1461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ASRC | Al Smith Rec Cntr-replace a/c & new windows | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-M245 P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | AL SMITH REC CENTER | REPLACE A/C & NEW WINDOWS AT AL SMITH REC CENTER | 2022 | 380 | 0 | 450 | 0 | 121 | 0 | 0 | 0 | 571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303BPCS | Baruch Playground C/S Renovations M165A-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 303 | P-1018 P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BARUCH PLAYGROUND BATHROOM RENOVATIONS -- RECONSTRUCT THE COMFORT STATION, INCLUDING NEW WINDOWS, DOORS, FIXTURES AND PARTITIONS AS WELL ASNEW PLUMBING, ELECTRICAL AND MECHANICAL SYSTEMS. MAKE BATHROOMS ADA COMPLIANT | 2022 | 340 | 2358.95 | 46 | 0 | 0 | 0 | 0 | 0 | 2404.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303CRH2 | Corlears Hook Playground, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-M245 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CORLEARS HOOK - CORLEARS HOOK PLAYGROUND -- FUNDING FOR PLAYGROUND UPGRADES | 2022 | 450 | 25 | 0 | 0 | 0 | 0 | 1000 | 0 | 1025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ERP4 | East River Park -Fireboat Wet Floodproofing | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | RE-0025 |  |  | EAST RIVER PARK -FIREBOAT WET FLOODPROOFING | 2022 | 2000 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303ERSF | ERP - E 6TH ST SOCCER FLD NEW TURF M144-214m | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 303 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | ERP - E 6TH ST SOCCER FLD NEW TURF & LIGHTS | ERP - E 6TH ST SOCCER FLD NEW TURF & LIGHTS | 2022 | 600 | 3358.77 | 82 | 0 | 0 | 0 | 0 | 0 | 3440.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303HFFA | Hamilton Fish Rec. Center: Fire Alarm Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0506 |  | 128 PITT STREET, MANHATTAN | FIRE ALARM RECONSTRUCTION AT HAMILITON FISH REC CENTER. | 2022 | 416 | 0 | 0 | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303HFRC | Hamilton Fish Rec.Ctr-replace roof & alarm system | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-D018 P-0506 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | HAMILTON FISH REC.CTR- | HAMILTON FISH REC.CTR-REPLACE ROOF & ALARM SYSTEM | 2022 | 300 | 50.17 | 0 | 0 | 10480 | 0 | 10478 | 0 | 21008.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303HMFS | Hamilton Fish Park-Full renovation , Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  |  | HAMILTON FISH PARK-FULL RENOVATION | 2022 | 3728 | 85 | 0 | 0 | 1865 | 1800 | 0 | 0 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303KIML | Kimlau Square Improvements , Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  |  | KIMLAU SQUARE IMPROVEMENTS -- TO UPGRADE KIMLAU SQUARE ARCH | 2022 | 50 | 25 | 0 | 0 | 1139 | 0 | 0 | 0 | 1164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303LFPG | Reconstruction of Little Flower Playground, Manhattan | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-1018 |  |  | RECONSTRUCTION OF LITTLE FLOWER PLAYGROUND | 2022 | 6801 | 50 | 0 | 0 | 2827 | 0 | 2824 | 0 | 5701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303LGPK | CPI PH1 - LUTHER GULICK PARK - RECON WEST PORTION | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 303 | P-M245 P-D018 P-1018 | PROJECT DELAYED PENDING NON-CITY GRANT APPROVAL | LUTHER GULICK PARK - RECON WEST PORTION | LUTHER GULICK PARK - RECON WEST PORTION | 2022 | 360 | 4704.69 | 2 | 0 | 0 | 2055 | 0 | 0 | 6761.69 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 4500
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303MCKY | McKinley Playground renovation, M259-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-M245 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | MCKINLEY PLAYGROUND RE4OVATION. | MCKINLEY PLAYGROUND RENOVATION. | 2022 | 2505 | 3262 | 125 | 0 | 0 | 0 | 0 | 0 | 3387 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303SDRP | Sara D. Roosevelt Park - Pathways, sidewalks, exterior walls | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-M245 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | ROOSEVELT PARK, MANHATTAN | SARA. D ROOSEVELT PARK- PATHWAYS, SIDEWALKS, EXTERIOR WALLS | 2022 | 300 | 169.99 | 0 | 0 | 2876 | 1300 | 1414 | 0 | 5759.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303TPSQ | Tompkin's Square Park - Manhattan M088-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0926 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | TOMPKIN'S SQUARE PARK - MANHATTAN | 2022 | 4600 | 570 | 18 | 0 | 5582 | 0 | 0 | 0 | 6170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-303TSPL | PWOB-Tompkins Square Plgr-R/c at Ave B/E7 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | TOMPKINS SQ PK | 2022 | 611 | 2769.63 | 0 | 0 | 0 | 231 | 0 | 0 | 3000.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-30420S2 | West 20th St. Park Construction, M402-116M, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | ED-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WEST 20TH ST. PARK CONSTRUCTION | 2022 | 3043 | 2738.74 | 0 | 0 | 0 | 0 | 0 | 293 | 3031.74 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 500
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CBBC | Chelsea Basketball Court Renovation, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CHELSEA BASKETBALL COURT RENOVATION -- THIS PROJECT WOULD REPAVE AND REPAINT THE COURT SURFACE, INSTALL NEW HOOPS AND ADD NEW SEATING | 2022 | 943 | 121 | 1053 | 0 | 30 | 0 | 0 | 0 | 1204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CPTF | Chelsea Park-Replace the synthetic turf field and track M011 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 304 | P-D018 |  |  | CHELSEA PARK-REPLACE THE SYNTHETIC TURF FIELD AND TRACK | 2022 | 1650 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304CRLB | CHELSEA REC CTR ROOF DECK, LOCKER RM & BTHRM M260-114M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 304 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | WEST 25TH STREET BETWEEN 9TH & 10TH AVENUES | CHELSEA RECREATION CENTER ROOF DECK, LOCKER ROOM AND BATHROOM RECONSTRUCTION | 2022 | 600 | 3376.01 | 190 | 0 | 0 | 0 | 0 | 0 | 3566.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304DWIT | De Witt Clinton Park- Staircase Recons, M022-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0245M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | DE WITT CLINTON PARK | DE WITT CLINTON PARK | 2022 | 500 | 1596.86 | 0 | 0 | 0 | 124 | 0 | 0 | 1720.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304HELK | Hell's Kitchen Park -Surface Renovation, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  |  | PB: -SURFACE RENOVATION AT HELL'S KITCHEN PARK -- FUNDING FOR PARK RENOVATIONS | 2022 | 450 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304LRSQ | Little Red Square, Manhattan, MG-41350-115M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 302 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NYC PARKS DEPARTMENT -- LITTLE RED TRIANGLE -- RENOVATE EXISTING SITTING AREA AND EXPAND RECREATION SPACE | 2022 | 1140 | 3099.12 | 18 | 0 | 0 | 35 | 0 | 0 | 3152.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-304PENN | Penn South Playground, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-M245 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PENN SOUTH PLAYGROUND | 2022 | 400 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-305MSEL | Madison Square Park Pavement Reconstruction Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-1011 P-M245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | MADISON SQUARE PARK | MADISON SQUARE PARK CONSERVANCY : ETERNAL LIGHT FLAGSTAFF LANDSCAPE RENOVATION PROJECT. | 2022 | 3460 | 235 | 1350 | 0 | 350 | 0 | 0 | 0 | 1935 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 300
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-305UNIO | UNION SQUARE RECONSTRUCTION M089-198 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 305 | WM-0001 WM-0006 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BROADWAY TO 4 AVE, E. 14 TO E 17 STS | EXPAND THE CENTER OVAL INTO UNUSED STREET BEDS, RECONSTRUCTION OF PAVERBS, STONE WALLS, WATER LINES, WATER SERVICE, SECURITY & STREET LIGHTITING. RELOCATE "GANDHI" STATUE | 2022 | 7961 | 6351.53 | 0 | 369 | 0 | 0 | 0 | 0 | 6720.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-305UNQP | Union Square Park-Water lines and walkways | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-D018 |  | BROADWAY TO 4 AVENUE, E. 14 STREET TO E 17 STREET, BOROUGH OF MANHATTAN. | UNION SQUARE PARK WATER LINES AND WALKWAYS -UPGRADE THE WATER LINES AND WALKKING PATH AT UNION SQUARE PARK | 2022 | 4040 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306APMU | Albano Playground Handball Court Multi-use Conve M265-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 306 | P-D018 P-M245 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | ALBANO PLAYGROUND HANDBALL COURT MULTI USE -- CONVERT HANDBALL COURT INTO MULTI USE SPACE | 2022 | 354 | 149.86 | 0 | 0 | 800 | 750 | 0 | 0 | 1699.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ASEQ | Asser Levy Fitness Equipment, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-0505 P-1249 |  |  | ASSER LEVY FITNESS EQUIPMENT -- FUNDING FOR NEW FITNESS EQUIPMENT | 2022 | 250 | 0 | 513 | 0 | 194 | 0 | 0 | 0 | 707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306ASLV | Asser Levy Recreation Center | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-0506 P-1250 P-M245 | PROJECT DELAYED DUE TO SCHEDULING OF UTILITY WORK | HVAC AT ASSER LEVY PLAYGROUND, MANHATTAN | HVAC AT ASSER LEVY PLAYGROUND | 2022 | 300 | 322.71 | 1508 | 0 | 621 | 2604 | 0 | 0 | 5055.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306GLIC | Glick Park | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | PU-0200 P-0501 |  | GLICK PARK | GLICK PARK | 2022 | 17276 | 158 | 0 | 0 | 3088 | 0 | 12673 | 0 | 15919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306PETD | Peter Detmold Park, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-D822 |  |  | RECONSTRUCTION OF WATER LINE AT PETER DETMOLD PARK. -- RENOVATIONS TOPARK | 2022 | 560 | 76 | 0 | 0 | 480 | 0 | 0 | 0 | 556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306STVA | St. Vartan Park - Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-0245M | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ST. VARTAN PARK - MANHATTAN | 2022 | 5613 | 655 | 55 | 0 | 2296 | 0 | 2139 | 0 | 5145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306TRPL | Tramway Plaza Irrigation | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 306 308 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DEPARTMENT OF PARKS & RECREATION -- FUNDING WILL SUPPORT IMPROVEDMENTS AT TRAMWAY PLAZA, ICLUDING IRRIGATION SYSTEM INSTALLATION AND CONSTRUCTION OF A FOUNTAIN | 2022 | 60 | 10 | 0 | 0 | 0 | 0 | 50 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-306TUDO | Tudor Grove Playground - Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-0245M | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | TUDOR GROVE PLAYGROUND - MANHATTAN | 2022 | 500 | 210 | 0 | 1000 | 395 | 0 | 0 | 0 | 1605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BLOC | CPI PH2 - Bloomingdale Comfort Station (CONS) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CPI PH2 - BLOOMINGDALE PLGR COMFORT STATION RECO | CPI PH2 - BLOOMINGDALE PLGR COMFORT STATION RECO | 2022 | 1776 | 1419.68 | 0 | 0 | 0 | 251 | 0 | 0 | 1670.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BLOP | CPI PH2 - Bloomingdale Playground (construction)- M238-217M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | AMSTERDAM AVENUE BETWEEN WEST 104TH STREET AND WEST 105TH STREET | THIS PROJECT WILL RECONSTRUCT BASKETBALL COURTS, PATHS, BENCHES, SPRAY SHOWER, PLANTING, PLAY EQUIPMENT AND ADULT FITNESS EQUIPMENT AT BLOOMINGDALE PLAYGROUND. | 2022 | 6138 | 4885.47 | 0 | 0 | 0 | 783 | 0 | 0 | 5668.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307BMAP | BROADWAY MALLS - RECON & UPGRADE BROADWAY MALLS | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 307 309 312 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BROADWAY MALLS - RECON & UPGRADE 14 MALLS | BROADWAY MALLS - RECON & UPGRADE 14 MALLS | 2022 | 400 | 1777.02 | 0 | 0 | 0 | 208 | 0 | 0 | 1985.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPKS | RIVERSIDE PARK SOUTH - PHASE 5 M353-112M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 307 | P-0380 P-0245M | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RIVERSIDE PARK SOUTH - MILLER HGWY RELOC | 2022 | 10496 | 3683.95 | 2 | 0 | 0 | 503 | 0 | 0 | 4188.95 | 18023.92 | 0 | 0 | 0 | 259 | 0 | 0 | 18282.92
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPPI | RVSD PK SOUTH-SHADE STRUCTURES, SOCCER FIELD, REC AREA M071 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 307 | P-D018 P-0380 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RIVERSIDE PARK RECONSTRUCT TURF BALL FIELD, ADJACENT ACTIVE RECREATION AND SHADE STRUCTURE ON PIER I. | 2022 | 6485 | 6988.46 | 31 | 562 | 0 | 0 | 0 | 0 | 7581.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPRP | RIVERSIDE PARK 78 ST. RAMP RC M071 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  | RIVERSIDE PARK 78 ST. RAMP RC M071 | RIVERSIDE PARK 78 ST. RAMP RC M071 | 2022 | 810 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RPSB | Riverside Park South Ph. 5 Building | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 307 | P-0380 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RIVERSIDE PARK SOUTH PH. 5 BUILDING | 2022 | 2280 | 108.82 | 0 | 0 | 0 | 0 | 0 | 0 | 108.82 | 0 | 0 | 0 | 0 | 2713 | 0 | 0 | 2713
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307RVSD | RIVERSIDE PK- CANTILEVER 83RD-91ST M071-297A | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 307 | P-0380 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RIVERSIDE PARK BETWEEN WEST 83RD STREET AND WEST 91ST STREET | THIS PROJECT WILL CONSTRUCT A BICYCLE AND PEDESTRIAN PATH IN RIVERSIDE PARK, INCLUDING NEW PAVEMENT, FENCES, FURNISHING, LIGHTING, DRAINAGE, PLANTING AND INTERPRETIVE SIGNAGE FOR WETLAND BIRD HABITATS. | 2022 | 10058 | 14796.22 | 0 | 43 | 0 | 0 | 0 | 0 | 14839.22 | 297 | 0 | 0 | 0 | 0 | 0 | 0 | 297
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SAPO | MATTHEW P. SAPOLIN PARK PLAYGROUND: PLAYGROUND EQUIPMENT | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-M245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | W. 70 BETWEEN W. END AVE AND AMSTERDAM | MATTHEW P. SAPOLIN PARK PLAYGROUND : PLAYGROUND EQUIPMENT UPGRADES | 2022 | 870 | 320 | 0 | 1555 | 0 | 0 | 0 | 0 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307SOLB | Sol Bloom Playground Improvements, Manhattan | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-D018 |  |  | SOL BLOOM PLAYGROUND IMPROVEMENTS -- FUNDING FOR PLAYGROUND UPGRADES | 2022 | 600 | 151 | 0 | 0 | 600 | 0 | 0 | 0 | 751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307STGR | PWOB-St. Gregory's Park Reconstruction (M301-114M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 307 | P-D018 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NYC DPR - ST. GREGORY'S PARK -- PARK RECONSTRUCTION | 2022 | 1200 | 1525.23 | 0 | 0 | 0 | 111 | 0 | 0 | 1636.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307TDRV | Theodore Roosevelt Park- Dog run noise Reduction | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-M245 |  | BOROUGH OF MANHATTAN | THEODORE ROOSEVELT PARK- BULL MOOSE DOG RUN NOISE REDUCTION PROJECT- INSTALL NOISE REDUCTION MEASURES. | 2022 | 215 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307TRDR | Theodore Roosevelt Park Dog Run Renovation | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 307 | P-M245 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NYC DPR - THEODORE ROOSEVELT PARK -- DOG RUN RENOVATION | 2022 | 300 | 946.22 | 63 | 0 | 0 | 0 | 0 | 0 | 1009.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-307VER1 | VERDI SQUARE IRRIGATION M097 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-D018 |  | VERDI SQUARE IRRIGATION M097 | VERDI SQUARE IRRIGATION M097 | 2022 | 695 | 0 | 0 | 0 | 635 | 0 | 0 | 0 | 635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AG02 | Asphalt Green- Pool Filter Upgrades | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | ASPHALT GREEN POOL FILTER UPGRADES | ASPHALT GREEN - POOL FILTER UPGRADES | 2022 | 713 | 0 | 713 | 0 | 0 | 0 | 0 | 0 | 713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AG03 | ASPHALT GREEN LOBBY EXPANSION & LOCKER UPGRADES | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  |  | EXPANSION OF THE AQUACENTER LOBBY | 2022 | 1665 | 0 | 0 | 0 | 0 | 795 | 0 | 0 | 795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGEE | Asphalt Green- Energy Efficiency, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 555 EAST 90TH STREET | THIS PROJECT WILL INCREASE ENERGY EFFICIENCY AT ASPHALT GREEN. | 2022 | 738 | 0 | 0 | 0 | 0 | 738 | 0 | 0 | 738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGFB | ASPHALT GREEN BOILER M286-114M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 308 | P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | ASPHALT GREEN BOILER & BULKHEAD | ASPHALT GREEN BOILER & BULKHEAD | 2022 | 1130 | 538.28 | 0 | 80 | 0 | 0 | 0 | 0 | 618.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGPF | Asphalt Green Pool Filtration | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-D018 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | ASPHALT GREEN | ASPHALT GREEN-POOL FILTRATION | 2022 | 108 | 0 | 0 | 0 | 0 | 108 | 0 | 0 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308AGPO | Asphalt Green Pool Filtration | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-D018 |  | 555 EAST 90TH STREET | THIS PROJECT WILL RECONSTRUCT THE ASPHALT GREEN POOL FILTRATION SYSTEM. | 2022 | 140 | 0 | 0 | 0 | 0 | 140 | 0 | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308CSPG | Carl Schurz Playground Reconstruction | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 308 | P-D018 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION OF CARL SCHURZ PLAYGROUND | 2022 | 2848 | 3794.22 | 0 | 0 | 0 | 305 | 0 | 0 | 4099.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308EPOA | POA East River Esplanade Improvements, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0501 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | POA EAST RIVER ESPLANADE IMPROVEMENTS, MANHATTAN | 2022 | 15000 | 200 | 1076 | 0 | 0 | 0 | 13924 | 0 | 15200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308EREI | ERP- East River Esplanade Improvements | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | EAST RIVER ESPLANADE IMPROVEMENTS | EAST RIVER ESPLANADE IMPROVEMENTS | 2022 | 1450 | 2148.14 | 187 | 0 | 0 | 0 | 0 | 0 | 2335.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308ERP2 | East River Esplanade Stabilization And Reconstruction PHASE | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-0501 P-D018 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS |  | EAST RIVER ESPLANADE STABILIZATION AND RECONSTRUCTION PHASE | 2022 | 8366 | 300 | 816 | 0 | 0 | 10557 | 0 | 0 | 11673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308ERP3 | EAST RIVER ESPLANADE PHASE 3+ | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-0501 PU-0200 P-1018 P-1245 P-D018 |  | EAST RIVER ESPLANADE | EAST RIVER ESPLANADE | 2022 | 74350 | 355 | 2976 | 40682 | 0 | 5670 | 0 | 0 | 49683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308FFCA | FDR FOUR FREEDOMS PARK CONSERVANCY -- ENHANCED ACCESS, FDR F | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-M245 |  |  | FDR FOUR FREEDOMS PARK CONSERVANCY -- ENHANCED ACCESS, FDR FOUR FREEDOMS PARK | 2022 | 325 | 250 | 0 | 75 | 0 | 0 | 0 | 0 | 325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308GMBR | Gracie Mansion Rooftop Balustrade RC M081-122M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-0245M |  |  | GRACIE MANSION ROOFTOP BALUSTRADE RC | 2022 | 966 | 0 | 830 | 0 | 0 | 0 | 0 | 0 | 830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308GMGL | GRACIE MANSION GUTTERS AND LEADERS RC M081 | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-0245M |  |  | GRACIE MANSION | 2022 | 200 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308GMRD | GRACIE MANSION RAMP AND DRAINAGE RC M081 | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-0245M |  |  | GRACIE MANSION | 2022 | 1272 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308HNYL | 14 HONEY LOCUSTS PARK, Manhattan, M177-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0245M W-0013 |  |  | 14 HONEY LOCUSTS PARK, MANHATTAN | 2022 | 1920 | 200 | 993 | 139 | 538 | 0 | 0 | 0 | 1870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308MHM2 | MERCHANT HOUSE MUSEUM- EAST FACADE & SHUTTER RESTO M318 | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 302 | P-M245 P-D018 P-C018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MERCHANT HOUSE MUSEUM- EAST FACADE & SHUTTER RESTORATION, MANHATTAN | MERCHANT HOUSE MUSEUM- EAST FACADE & SHUTTER RESTORATION, MANHATTAN | 2022 | 300 | 28 | 0 | 0 | 660 | 645 | 0 | 0 | 1333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308SPCS | 24 Sycamores Park C/S Renovation M108-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 308 | P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 24 SYCAMORES PARK -- RENOVATE BATHROOMS IN THE PARK | 2022 | 2040 | 1937.8 | 17 | 0 | 0 | 157 | 0 | 0 | 2111.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-308STCP | St. Catherine's Park -- sportscoating iin the children's p | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ÝDPRÛ ST. CATHERINE'S PARK -- IMPROVEMENTS TO THE SPORTSCOATING IN THE CHILDREN'S PLAY AREA | 2022 | 460 | 105 | 0 | 0 | 0 | 590 | 0 | 0 | 695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309AHAM | Alexander Hamilton Plg Basketball Renovation M041-121M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-M245 |  |  | ALEXANDER HAMILTON PLG BASKETBALL RENOVATION ,MANHATTAN | 2022 | 955 | 72 | 62 | 0 | 616 | 677 | 0 | 0 | 1427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309ANUN | Annunciation Playground | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 P-D018 |  | CONVENT AVENUE, AMSTERDAM AVENUE WEST 135 STREET | ANNUNCIATION PLAYGROUND | 2022 | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 300
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JRFA | Jackie Robinson Rec. Center: Fire Alarm Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 309 | P-0506 |  | 85 BRADHURST AVENUE, NEW YORK, NY | FIRE ALARM RECONSTRUCTION AT JACKIE ROBINSON REC CENTER, MANHATTAN. | 2022 | 390 | 0 | 0 | 518 | 0 | 0 | 0 | 0 | 518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JRRC | Jackie Robinson Recreation Ctr HVAC System RC M014-119M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 309 310 | P-1250 |  | 85 BRADHURST AVENUE NEW YORK, NY 10039, MANHATTAN | JACKIE ROBINSON RECREATION CENTER HVAC SYSTEM RECONSTRUCTION | 2022 | 4000 | 300 | 0 | 2780 | 1520 | 0 | 0 | 0 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JSPL | Jacob Schiff Playground Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0245M | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | JACOB SCHIFF PLAYGROUND, MANHATTAN | JACOB SCHIFF PLAYGROUND RECONSTRUCTION | 2022 | 300 | 1228.66 | 93 | 0 | 0 | 0 | 0 | 0 | 1321.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309JSST | Jacob Schiff Park- Recons of Seating area, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 309 | P-1018 P-D018 |  |  | JACOB SCHIFF PARK- RECONS OF SEATING AREA, MANHATTAN | 2022 | 760 | 238 | 0 | 1253 | 267 | 0 | 0 | 0 | 1758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309RBUS | RVSD DR -TIEMANN PL TO 97TH ST | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 307 309 | P-0380 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | UPGRADE RIVERSIDE DRIVE BETWEEN 97TH ST. AND TIEMANN, NEW YORK CITY | 2022 | 2000 | 1793.76 | 0 | 0 | 0 | 310 | 0 | 0 | 2103.76 | 1447.8 | 0 | 0 | 0 | 0 | 0 | 0 | 1447.8
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309RPK1 | Riverside Park Improvements, Manhattan | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-D018 P-0380 |  |  | RIVERSIDE PARK RENOVATIONS | 2022 | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309RSLG | Lighthouse Park Roosevelt Island, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  | NORTHERN TIP OF ROOSEVELT ISLAND | THIS PROJECT WILL RECONSTRUCT LIGHTHOUSE PARK. | 2022 | 70 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309SKRP | Sakura Park - Reconstruction of the Staircase | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1329 P-0245M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | SAKURA PARK | RECONSTRUCTION OF THE STAIRCASE | 2022 | 425 | 2150.13 | 25 | 39 | 0 | 0 | 313 | 0 | 2527.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-309SSTF | Jacob Schiff Playground Synthetic Turf Field Recon,Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0510 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | JACOB SCHIFF PLAYGROUND SYNTHETIC TURF FIELD RECON,MANHATTAN | 2022 | 2919 | 141 | 1268 | 0 | 324 | 1327 | 0 | 0 | 3060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-30AG05 | Asphalt Green- Building Management System | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  | BOROUGH OF MANHATTAN | ASPHALT GREEN BUILDING MANAGEMENT SYSTEM | 2022 | 807 | 0 | 0 | 0 | 0 | 797 | 0 | 0 | 797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310ARFA | The Arsenal: Fire Alarm Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0506 |  | 830 5TH AVENUE, THE ARSENAL NY, NY 10065 | FIRE ALARM RECONSTRUCTION AT THE ARSENAL, MANHATTAN. | 2022 | 315 | 43 | 407 | 0 | 0 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310CCPG | Courtney Callendar Playground-handball court | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | COURTNEY CALLENDAR PLAYGROUND | R/C OF SITTING AREA AT COURTNEY CALLENDAR PLAYGROUND | 2022 | 100 | 479.07 | 35 | 0 | 0 | 0 | 0 | 0 | 514.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-310MCCY | McCray Playground , Manhattan | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-D018 P-M245 P-1018 |  |  | MCCRAY PALYGROUND | 2022 | 150 | 0 | 0 | 0 | 2660 | 2340 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HCTR | HIGHBRIDGE RECREATION CTR -RC BOILERS AND HVAC - M037-217M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-1250 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | MANHATTAN | HIGHBRIDGE RECREATION CTR RC | 2022 | 3272 | 3531.57 | 200 | 667 | 0 | 0 | 0 | 0 | 4398.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HEL3 | Phase 3 of Hell Gate Pathway, below Viaduct Randalls Island | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-X245 WP-0112 | PROJECT DELAYED PENDING NON-CITY GRANT APPROVAL | PH 3 OF HELL GATE PATHWAY | PH 3 OF HELL GATE PATHWAY | 2022 | 3140 | 601.99 | 0 | 0 | 0 | 657 | 0 | 0 | 1258.99 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 3000
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311HWTR | HIGHBRIDGE AQUEDUCT WATER TOWER RESTORATION M037-113M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 312 | P-0245M | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HIGHBRIDGE AQUEDUCT WATER TOWER RESTORATION, MANHATTAN | HIGHBRIDGE AQUEDUCT WATER TOWER RESTORATION INCLUDING ROOF AND WINDOWS | 2022 | 742 | 4929.97 | 298 | 0 | 429 | 0 | 0 | 0 | 5656.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGFI | MARCUS GARVEY PK FIRE WATCHTOWER RESTORATION M058-115M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED DUE TO UNAVAILABILITY OF PRODUCT | MARCUS GARVEY PK | FIRE WATCH TOWER RESTORATION | 2022 | 280 | 8126.77 | 198 | 0 | 0 | 0 | 0 | 0 | 8324.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311MGLL | MARCUS GARVEY CS LITTLE LEAGUE FACILTY M058-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 311 | P-1018 P-0245M | PROJECT DELAYED RESULTING FROM CONTRACTOR DEFAULT | MARCUS GARVEY LITTLE LEAGUE BLDG | MARCUS GARVEY LITTLE LEAGUE BLDG | 2022 | 400 | 3579.69 | 46 | 0 | 0 | 286 | 0 | 0 | 3911.69 | 2229.99 | 0 | 0 | 0 | 0 | 0 | 0 | 2229.99
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PFFA | Pelham Fritz Rec. Center: Fire Alarm Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 311 | P-0506 |  | 18 MOUNT MORRIS PARK WEST, MANHATTAN. | FIRE ALARM RECONSTRUCTION AT PELHAM FRITZ REC. CENTER. | 2022 | 284 | 0 | 0 | 284 | 0 | 0 | 0 | 0 | 284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PFRC | PELHAM FRITZ REC CENTER | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-0506 |  |  | PELHAM FRITZ REC CENTER | 2022 | 4671 | 0 | 0 | 463 | 0 | 4208 | 0 | 0 | 4671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PFRI | MARCUS GARVEY PK -PELHAM FRITZ RECREATION CTR CONS M058-118M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-0506 |  |  | MARCUS GARVEY PK - PELHAM FRITZ RECREATION CTR CONS M058 | 2022 | 750 | 1194.76 | 109 | 0 | 0 | 0 | 0 | 0 | 1303.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311PRPL | Poor Richard's Playground Renovations | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-0245M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | POOR RICHARD'S PLAYGROUND RENOVATIONS, MANHATTAN | POOR RICHARDS PLAYGROUND RENOVATIONS | 2022 | 950 | 1408.7 | 99 | 0 | 0 | 0 | 0 | 0 | 1507.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJFA | Thomas Jefferson Rec. Center: Fire Alarm Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 311 | P-0506 |  | 2180 1ST AVENUE, MANHATTAN. | FIRE ALARM RECONSTRUCTION AT THOMAS JEFFESON REC. CENTER. | 2022 | 349 | 0 | 0 | 379 | 0 | 0 | 0 | 0 | 379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJHV | THOMAS JEFFERSON PARK REC CTR HVAC M047-109M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 311 | P-0245M | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | THOMAS JEFFERSON PARK REC CTR HVAC | THOMAS JEFFERSON PARK REC CTR HVAC | 2022 | 1000 | 320.4 | 0 | 0 | 0 | 0 | 0 | 0 | 320.4 | 646.92 | 0 | 0 | 0 | 123 | 0 | 0 | 769.92
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TJPK | Thomas Jefferson Park Renovations | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | THOMAS JEFFERSON PARK RENOVATIONS, MANHATTAN | THOMAS JEFFERSON PARK RENOVATIONS | 2022 | 350 | 690.54 | 59 | 0 | 0 | 0 | 0 | 0 | 749.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-311TURF | Harlem River Park Synthetic Turf, Manhattan M208D-219M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0510 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HARLEM RIVER PARK FIELD ( AT 128TH ST)- SYNTHETIC TURF, MANHATTAN | 2022 | 6650 | 310 | 2313 | 0 | 3902 | 0 | 0 | 0 | 6525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312DFAR | DYCKMAN FARMHOUSE : ADA RAMP AND BATHROOM RENOVATION | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-M245 P-1018 P-0245M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | DYCKMAN FARMHOUSE | DYCKMAN FARMHOUSE : ADA RAMP AND BATHROOM RENOVATION | 2022 | 750 | 864 | 118 | 0 | 2554 | 3487 | 0 | 0 | 7023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INNC | Inwood Hill Nature Center M042 -116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0506 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | INWOOD NATURE CENTER, MANHATTAN | INWOOD NATURE CENTER | 2022 | 100 | 2223.35 | 754 | 0 | 0 | 0 | 0 | 0 | 2977.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INNG | RIVERSIDE-INWOOD NEIGHBORHOOD GARDENS, INC. | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-M245 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RIVERSIDE-INWOOD NEIGHBORHOOD GARDENS, INC: RING GARDEN PROJECT | RIVERSIDE-INWOOD NEIGHBORHOOD GARDENS, INC. : RING GARDEN PROJECT | 2022 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312INWD | Inwood Hill Nature Center- Exhibit Display Reconstruction | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-1018 |  | INWOOD HILL NATURE CENTER, MANHATTAN | RECONSTRUCTION OF THE EXHIBIT DISPLAY AT INWOOD HILL NATURE CENTER | 2022 | 268 | 0 | 268 | 0 | 0 | 0 | 0 | 0 | 268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312ISA2 | ISHAM PARK IRRIGATION & DRINK FOUNTAINS M043 M43112 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 312 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | ISHAM PARK IRRIGATION & DRINK FOUNTAINS | ISHAM PARK IRRIGATION & DRINK FOUNTAINS | 2022 | 750 | 1064.11 | 35 | 0 | 0 | 0 | 0 | 0 | 1099.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312IWDH | Inwood Hill Park - Baseball Field Lights | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-D018 |  | BOROUGH OF MANHATTAN | INWOOD HILL PARK- BASEBALL FIELD LIGHTING SSYSTEM AT INWOOD HILL PARKBASEBALL FIELD | 2022 | 8458 | 0 | 0 | 0 | 0 | 0 | 8333 | 0 | 8333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JHFA | J. Hood Wright Rec. Center: Fire Alarm Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 312 | P-0506 |  | 351 FT. WASHINGTON AVE, MANHATTAN. | FIRE ALARM RECONSTRUCTION AT J. HOOD WRIGHT REC. CENTER. | 2022 | 233 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JHRW | J HOOD WRIGHT PARK REC CTR WINDOWS M099 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 312 | P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | J HOOD WRIGHT PARK REC CTR WINDOWS | J HOOD WRIGHT PARK REC CTR WINDOWS | 2022 | 75 | 16 | 0 | 0 | 0 | 0 | 175 | 0 | 191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312JJPG | Jacob Javits Plgr-renovation | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | JACOB JAVITS PLGR | PLGR RENOVATION | 2022 | 1640 | 3164.06 | 0 | 0 | 0 | 277 | 0 | 0 | 3441.06 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 350
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-312MJM2 | Morris Jumel mansion - exterior renovation- ph II M073 | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 312 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | MORRIS JUMEL MANSION EXTERIOR (PERIMETER STREETSCAPE AND STONE WALLS)PHASE 2 RECONSTRUCTION, MANHATTAN | MORRIS JUMEL MANSION EXTERIOR (PERIMETER STREETSCAPE AND STONE WALLS)RECONSTRUCTION | 2022 | 1500 | 457.21 | 0 | 0 | 0 | 0 | 0 | 0 | 457.21 | 1371.94 | 0 | 0 | 0 | 0 | 0 | 128 | 1499.94
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-313CPAB | CENTRAL PARK - ARSENAL BRICK FACADE M010-214M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RC OF ARSENAL BRICK FACADE ALONG THE 4TH FLOOR SE TURRET 5TH FLOOR ELEVATOR TURRET | 2022 | 1133 | 2999.16 | 0 | 1 | 0 | 0 | 1402 | 0 | 4402.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-313CPSW | Central Park - Swedish Cottage M010-116M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 304 305 307 308 310 311 | P-D018 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | CENTRAL PARK - SWEDISH COTTAGE, MANHATTAN | CENTRAL PARK - SWEDISH COTTAGE, MANHATTAN | 2022 | 120 | 5.37 | 0 | 0 | 543 | 516 | 0 | 0 | 1064.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-314RPDR | RIVERSIDE PARK DOG RUN M071 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 309 312 | P-D018 P-0380 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RIVERSIDE DRIVE, HUDSON RIVER, WEST 72ND STREET, WEST 95TH STREET | RIVERSIDE PARK DOG RUN IN MANHATTAN | 2022 | 76 | 68 | 0 | 0 | 850 | 0 | 0 | 0 | 918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3AIDSLC | AIDS MEMORIAL-LARRY STATUE | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | AIDS MEMORIAL-LARRY STATUE | AIDS MEMORIAL-LARRY STATUE | 2022 | 1100 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH02 | Highbridge Anchor Park Phase II- Manhattan M037-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 P-0415A | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HIGHBRIDGE ANCHOR PARK PHASE II- MANHATTAN | 2022 | 13740 | 12343.73 | 12 | 0 | 0 | 1074 | 0 | 0 | 13429.73 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH03 | Highbridge Anchor Park Phase III- COMFORT STATION, M037-218M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0415A |  |  | HIGHBRIDGE ANCHOR PARK PHASE III- COMFORT STATION, MANHATTAN | 2022 | 4364 | 3610.26 | 747 | 0 | 0 | 0 | 0 | 0 | 4357.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANCH04 | Highbridge Anchor Park Reconstruction Phase I, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0415A P-1018 P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HIGHBRIDGE ANCHOR PARK RECONSTRUCTION PHASE I, MANHATTAN | 2022 | 10260 | 10365.94 | 8 | 0 | 0 | 855 | 0 | 0 | 11228.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ANNEPG | ANNE LOFTUS PLAYGROUND//WATER PARK, M029-118M, Mahattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  |  | ANNE LOFTUS PLAYGROUND//WATER PARK, MAHATTAN | 2022 | 5701 | 3903.13 | 683 | 0 | 0 | 0 | 0 | 0 | 4586.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ASGRGN | ASPHALT GREEN: EMERGENCY GENERATOR PROJECT | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ASPHALT GREEN, INC.: EMERGENCY GENERATOR PROJECT | 2022 | 660 | 0 | 0 | 0 | 0 | 183 | 0 | 0 | 183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ASGRSU | ASPHALT GREEN: CONSTRUCTION OF SUNDIAL PLAZA | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-M245 P-D018 |  |  | CONSTRUCTION OF SUNDIAL PLAZA IN ASPHALT GREEN IN MANHATTAN. | 2022 | 300 | 0 | 0 | 0 | 0 | 677 | 0 | 0 | 677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3ASRRMP | Asser Levy Recreation Center Ramp Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0506 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MANHATTAN | ASSER LEVY RECREATION CENTER RAMP RECONSTRUCTION | 2022 | 192 | 92.6 | 0 | 0 | 0 | 57 | 0 | 0 | 149.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BBASIN | Riverside Park- Moving Costs Associated With The 79th Street | VEHICLES AND EQUIPMENT | 300 | P-0245M |  | 698 WEST 135TH STREET, NEW YORK, NEW YORK 10031 | THE RELOCATION OF THE RIVERSIDE PARK DISTRICT M&O OPERATIONS OUT OF THE W79TH ROTUNDA, MANHATTAN | 2022 | 493 | 155.91 | 232 | 0 | 0 | 0 | 0 | 0 | 387.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BBGARD | BATTERY PARK SEAGLASS CAROUSEL M005-208M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 301 | P-0828 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BATTERY PARK CAROUSEL | BATTERY PARK CAROUSEL | 2022 | 8230 | 5553.06 | 0 | 0 | 0 | 0 | 100 | 0 | 5653.06 | 7050 | 0 | 0 | 0 | 0 | 0 | 0 | 7050
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BELLVU | BELLEVUE PARK SOUTH, RECONS Mahattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-M245 P-0245M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BELLEVUE PARK SOUTH, MAHATTAN | 2022 | 1500 | 430 | 3500 | 1550 | 0 | 0 | 0 | 0 | 5480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BENNSF | BENNETT PARK SYNTHETIC FIELD | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-M245 P-D018 |  |  | BENNETT PARK SYNTHETIC FIELD: INSTALLATION OF SYNTHETIC FIELD | 2022 | 1100 | 190 | 0 | 0 | 1100 | 0 | 0 | 0 | 1290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BOOKTW | BOOKER T WASHINGTON Plg Synthetic Turf Rpl, Mahattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0510 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BOOKER T WASHINGTON PLAYGROUND--SYNTHETIC TURF REPLACEMENT | 2022 | 136 | 1884.92 | 0 | 0 | 0 | 370 | 0 | 0 | 2254.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BOTWAT | 6BC Botanical Garden:Garden Water Source | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  |  | GARDEN WATER SOURCE AT 6BC BOTANICAL GARDEN. | 2022 | 125 | 20 | 0 | 0 | 125 | 0 | 0 | 0 | 145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BPPLGD | BATTERY PARK Plg (SOUTH FERRY-MTA) M005-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 301 | P-M245 P-D018 P-0828 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BATTERY PARK PLAYGROUND (SOUTH FERRY-MTA) | BATTERY PARK PLAYGROUND (SOUTH FERRY-MTA) | 2022 | 5100 | 1601.55 | 43 | 0 | 0 | 800 | 0 | 0 | 2444.55 | 16649.6 | 0 | 0 | 0 | 0 | 0 | 0 | 16649.6
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3BWWATE | RPZ - WATER SERVICE INSTALLATION MG-518M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-0245M P-C020 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RPZ - WATER SERVICE INSTALLATION | 2022 | 340 | 736.17 | 0 | 0 | 0 | 114 | 0 | 0 | 850.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENBOL | Central Park - Construction Security Measures M010-221M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-1095 P-1018 |  |  | CENTRAL PARK - CONSTRUCTION SECURITY MEASURES | 2022 | 0 | 0 | 2088 | 17611 | 0 | 1601 | 0 | 0 | 21300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT08 | Central Park - Recons of Perimeter E84-E108ST WO# 8 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-1300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECONSTRUCTION OF THE PARK PERIMETER LOCATED BETWEEN E84-E109 ST., CENTRAL PARK | 2022 | 0 | 4395 | 0 | 0 | 0 | 425 | 0 | 0 | 4820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENT13 | Recon. of Naumburg Bandshell in Central Park, WO#13, | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-1300 |  |  | RECON. OF NAUMBURG BANDSHELL IN CENTRAL PARK, WO#13, | 2022 | 6927 | 6297 | 0 | 630 | 0 | 0 | 0 | 0 | 6927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CENTRL | Central Park - Roller Skating Park Repaving, Manhattan | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-M245 |  |  | DPR- CENTRAL PARK ROLLER SKATING PARK REPAVING--FUNDING TO REPAVE THEROLLER SKATING RINK CENTRAL PARK NEW YORK, NY | 2022 | 80 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CHLENT | Chelsea Recreation Center Entrance Lobby Recon CNYG-2819M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  | CHELSEA RECREATION CENTER | CHELSEA RECREATION CENTER ENTRANCE LOBBY RECON | 2022 | 260 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CMGWAT | Childrens Magical Garden:Drinking Fountain/Water Spigot | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  |  | CHILDRENS MAGICAL GARDEN:DRINKING FOUNTAIN/WATER SPIGOT | 2022 | 200 | 43 | 0 | 200 | 0 | 0 | 0 | 0 | 243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3COLPCS | COLUMBUS PARK -RENOVATE COMFORT STATION ON WORTH STREET | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-0245M |  |  | COLUMBUS PARK -- RENOVATE COMFORT STATION ON WORTH STREET | 2022 | 1000 | 0 | 0 | 0 | 5650 | 0 | 5606 | 0 | 11256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3COLUBT | COLUMBUS PARK - COLUMBUS PARK NEW TURF, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  |  | COLUMBUS PARK NEW TURF -- TO PROVIDE NEW TURF FOR COLUMBUS PARK | 2022 | 552 | 0 | 552 | 0 | 0 | 0 | 0 | 0 | 552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3COLUMB | COLUMBUS PARK - Entrance Renovation, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | COLUMBUS PARK - ENTRANCE RENOVATION -- TURN THE MULBERRY ST. ENTRANCESTEPS AT COLUMBUS PARK (MANHATTAN) INTO A RAMP | COLUMBUS PARK - ENTRANCE RENOVATION -- TURN THE MULBERRY ST. ENTRANCESTEPS AT COLUMBUS PARK (MANHATTAN) INTO A RAMP | 2022 | 219 | 489.07 | 42 | 0 | 0 | 0 | 0 | 0 | 531.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3A2 | CPI PH2 - ABRAHAM LINCOLN CS RC | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CPI PH3 - ABRAHAM LINCOLN CS RC | 2022 | 1940 | 1492.52 | 195 | 0 | 0 | 568 | 0 | 0 | 2255.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AB | CPI PH2 - Audubon Plg & Comf Reconstruction (DESIGN) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CPI PH3 - AUDUBON PLAYGROUND RECONSTRUCTION | 2022 | 5909 | 1044.63 | 0 | 0 | 0 | 0 | 269 | 0 | 1313.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AC | CPI PH2 - Audubon Comfort Station Recons M240-218M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  |  | CPI PH2 - AUDUBON COMFORT STATION RECONSTRUCTION | 2022 | 2100 | 1351.88 | 501 | 0 | 0 | 0 | 0 | 0 | 1852.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AL | CPI PH2 - Abraham Lincoln plg .... | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CPI PH3 - ABRAHAM LINCOLN PLG & COMFORT STATION RECONS.. | 2022 | 8932 | 9394.15 | 127 | 0 | 0 | 988 | 0 | 0 | 10509.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPI3AP | CPI PH2 - Audubon Playground Reconst M240-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CPI PH2 - AUDUBON PLAYGROUND RECONSTRUCTION | 2022 | 3320 | 6154.64 | 0 | 0 | 0 | 0 | 1132 | 0 | 7286.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIAAP | CPI - ANIBAL AVILES PLGD | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  |  | CPI - ANIBAL AVILES PLGD | 2022 | 8171 | 0 | 0 | 0 | 3143 | 3142 | 0 | 0 | 6285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIBBJ | CPI PH2 - Bill Bojangles Playground | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CPI PH2 - BILL BOJANLES PLAYGROUND | 2022 | 1590 | 2042.46 | 0 | 0 | 0 | 419 | 0 | 0 | 2461.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIBN9 | CPI PH1 Plg 103 and St Nicholas North Plg Recons (MG-216M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-1018 | PROJECT DELAYED DUE TO SCHEDULING OF UTILITY WORK |  |  | 2022 | 10861 | 8810.06 | 0 | 0 | 0 | 177 | 0 | 0 | 8987.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIDOE | CPI - DETECTIVE OMAR EDWARDS PLGD | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  |  | CPI - DETECTIVE OMAR EDWARDS PLGD | 2022 | 4713 | 0 | 0 | 0 | 1813 | 1812 | 0 | 0 | 3625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIFGC | CPI PH2 - Frederick Johnson Comfort Station, M141-418M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | ADAM CLAYTON POWELL JR. BOULEVARD (7TH AVENUE) AT WEST 150TH STREET | THIS PROJECT WILL CONSTRUCT A NEW COMFORT STATION AT FREDERICK JOHNSON PLAYGROUND. | 2022 | 5200 | 127.77 | 3947 | 0 | 699 | 0 | 0 | 0 | 4773.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIFJP | CPI PH2 -Frederick Johnson Playground M159-219M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CPI PH2 -FREDERICK JOHNSON PLAYGROUND M141-218M | 2022 | 5300 | 5686.93 | 49 | 0 | 0 | 406 | 149 | 0 | 6290.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIHLP | CPI PH2 - Harlem Lane Playground, MG-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  |  | CPI PH2 - HARLEM LANE PLAYGROUND, M141-318M | 2022 | 7930 | 6856.6 | 504 | 939 | 0 | 0 | 0 | 0 | 8299.6 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 950
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPIPGI | CPI PH2 -Playground One, M196-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CPI PH2 -PLAYGROUND ONE | 2022 | 2801 | 3298.18 | 0 | 0 | 0 | 494 | 0 | 0 | 3792.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CPISUR | CPI PH2 - Sauer Playground | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CPI PH2 - SAUER PLAYGROUND | 2022 | 4067 | 3909.08 | 0 | 0 | 0 | 0 | 547 | 0 | 4456.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CSPBOL | Carl Schulz Pk- Construction Security Measures M081-120M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-1095 |  | CARL SCHULZ PK- CONSTRUCTION SECURITY MEASURES | CARL SCHULZ PK- CONSTRUCTION SECURITY MEASURES | 2022 | 1400 | 0 | 0 | 1570 | 0 | 0 | 0 | 0 | 1570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3CYPGCS | Colonel Young Plgd-Comfort Station Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-M245 P-D018 P-1018 |  |  | COLONEL YOUNG PLAYGROUND COMFORT STATION RENOVATION--RECONSTRUCT THE COMFORT STATION W. 145 ST. TO W. 143 ST., LENOX AVE., AND HARLEM RIVER. MANHATTAN. | 2022 | 1070 | 0 | 0 | 0 | 1251 | 1250 | 0 | 0 | 2501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DAGHAM | Dag Hammarskjold Plaza, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PARKS -- IMPROVEMENTS TO DAG HAMMARSKJOLD PLAZA -- FUNDING WILL PROVIDE CAPITAL IMPROVEMENTS TO DAG HAMMARSKJOLD PLAZA | PARKS -- IMPROVEMENTS TO DAG HAMMARSKJOLD PLAZA -- FUNDING WILL PROVIDE CAPITAL IMPROVEMENTS TO DAG HAMMARSKJOLD PLAZA | 2022 | 920 | 303 | 0 | 0 | 1280 | 0 | 0 | 0 | 1583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DDOKPL | Recon pool deck at Dry Dock Pool, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | DRY DOCK POOL, MANHATTAN | RECON POOL DECK AT DRY DOCK POOL, MANHATTAN | 2022 | 1200 | 50 | 1200 | 0 | 0 | 0 | 0 | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3DIRVPK | Riverside Park-Critical Drainage Infrastructure | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-0245M |  |  | RIVERSIDE PARK- DRAINAGE INFRASTRUCTURE | 2022 | 11500 | 985 | 0 | 0 | 4900 | 0 | 5650 | 0 | 11535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3FCSADA | Fort Washington Park CS-Renovate CS to Make it ADA Compliant | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  |  | FORT WASHINGTON PARK COMFORT STATION -- TO RENOVATE THE COMFORT STATION TO MAKE IT ADA-COMPLIANT | 2022 | 3650 | 0 | 0 | 0 | 1755 | 1745 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3FTPATH | FORT TRYON / INWOOD HILL PARKS PATH RESTORATION MG-819M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-M245 P-1018 |  |  | PATH RESTORATION IN FORT TRYON/ INWOOD HILL PARKS IN MANHATTAN. | 2022 | 250 | 0 | 0 | 1350 | 0 | 0 | 0 | 0 | 1350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GERCTE | GERTRUDE EDERLE RECREATION CENTER -- EQUIPMENT REPLACEMENT | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-0505 |  |  | GERTRUDE EDERLE RECREATION CENTER -- EQUIPMENT REPLACEMENT | 2022 | 140 | 0 | 363 | 0 | 0 | 0 | 0 | 0 | 363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GOVTFN | Governors Island - Drinking Fountains | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-M245 |  | BOROUGH OF MANHATTAN | THE TRUST FOR GOVERNORS ISLAND DRINKING FOUNTAINS-OUTFIT (5) LOCATIONS WITH FOUNTAIN/WATER BOTTLE FILLING STATIONS. | 2022 | 158 | 0 | 0 | 0 | 137 | 0 | 0 | 0 | 137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GRST01 | Greenstreets - Manhattan Greenstreets Planting | LAND ACQUISITION AND TREE PLANTING | 300 | P-0822 |  | BOROUGH OF MANHATTAN -EAST 66 STREET BETWEEN 2ND AND 3RD AVENUES. | GREENSTREETS - MANHATTAN | 2022 | 87 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3GTACQM | Land Acuisition: Green Thumb on 143rd ST, Manhattan | LAND ACQUISITION AND TREE PLANTING | 300 | P-D056 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | LAND ACUISITION: GREEN THUMB ON 143RD ST, MANHATTAN | 2022 | 300 | 3.1 | 0 | 447 | 0 | 0 | 0 | 0 | 450.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HBCGRD | Highbridge Community Garden | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HIGHBRIDGE COMMUNITY GARDEN | HIGHBRIDGE COMMUNITY GARDEN | 2022 | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HELIP2 | Heliport(Andrew Haswell) Park - phase 2 M108-109M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 308 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN HAZARDOUS CONDITION | HELIPORT PARK CONSTRUCTION PHASE 2 | HELIPORT PARK CONSTRUCTION PHASE 2 | 2022 | 2500 | 3500.66 | 0 | 0 | 0 | 192 | 0 | 0 | 3692.66 | 1550 | 0 | 0 | 0 | 0 | 0 | 0 | 1550
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HELLKT | DEP Shaft Site - Hell's Kitchen Park Construction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | W-0013 P-0245M P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RIVERSIDE PARK--101ST STAIRCASE PROJECT | 2022 | 200 | 695 | 0 | 1300 | 1100 | 1800 | 0 | 0 | 4895 | 0 | 0 | 0 | 125 | 0 | 0 | 0 | 125
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HGLNPH | HIGHLINE-Path replace Rail Track Rehab, Lead Paint, light | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | THE HIGH LINE -- PATH-PERMANET REPLACEMENT, RAIL TRACK WALK REHAB, LEAD PAINT ENCAPULSTION, LIGHTING | 2022 | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 0 | 3800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HGLNRC | HIGHLINE Reconstruction, Misc Park & Playground., | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0245M | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HIGHLINE RECONSTRUCTION, MISC PARK & PLAYGROUND., | 2022 | 6000 | 0 | 0 | 0 | 0 | 1917 | 0 | 0 | 1917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HIGHL3 | FRIENDS OF THE HIGH LINE- Western Rail Yards, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | THE HIGH LINE: LIGHTING AND SECURITY -- WESTERN RAIL YARDS: LIGHTING AND SECURITY; THE HIGH LINE: RUST AND CONCRETE -- WESTERN RAIL YARDS: RUST AND CONCRETE REPAIR; THE HIGH LINE: DRAINAGE -- WESTERN RAIL YARDS: DRAINAGE | 2022 | 2700 | 0 | 0 | 0 | 0 | 2700 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HLNACC | Friends of Highline: accessibility, secur/safety, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-M245 |  |  | FRIENDS OF THE HIGH LINE -- FUNDS RELATED TO ACCESSIBILITY, CIRCULATION AND VISITOR EXPERIENCE, SECURITY/LIFE SAFETY AND LANDSCAPE SUSTAINABILITY | 2022 | 1850 | 0 | 0 | 0 | 0 | 1850 | 0 | 0 | 1850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HLNERP | FRIENDS OF THE HIGH LINE: HIGH LINE REPAIRS | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-M245 |  |  | RENOV AND REPAIRS AT THE HIGH LINE IN MANHATTAN. | 2022 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HMFISH | Hamilton Fish Park Basketball Courts and Adult Fitness | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-D018 P-M245 |  |  | HAMILTON FISH PARK BASKETBALL COURTS AND ADULT FITNESS | 2022 | 655 | 676.86 | 151 | 0 | 0 | 0 | 0 | 0 | 827.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HR2944 | HRPT - 29th to 44th Sts. Construction, Manhattan | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-1246 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HRPT - 29TH TO 44TH STS. CONSTRUCTION | 2022 | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 23000 | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP26S | HRPT-Pier 26 Science Playground | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  | BOROUGH OF MANHATTAN | HUDSON RIVER PARK TRUST - PIER 26 SCIENCE PLAYGROUND | 2022 | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP26U | HRPT: Pier 26 Upland Estuarium Construction | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-1246 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HRPT | 2022 | 4609 | 0 | 0 | 0 | 0 | 4609 | 0 | 0 | 4609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRP45A | HRPT - Pier 45 Boardwalk Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  | BOROUGH OF MANHATTAN | HRP- PIER 45 BOARDWALK RECONSTRUCTION | 2022 | 1367 | 0 | 1241 | 0 | 0 | 0 | 0 | 0 | 1241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPCP1 | Hudson River Park - Composter | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  |  | HUDSON RIVER PARK - COMPOSTER | 2022 | 130 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPCW1 | HARRIET TUBMAN MEMORIAL BEAUTIFICATION, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HRP - CHELSEA WATERSIDE PARK & DOG RUN, MANHATTAN | 2022 | 175 | 0 | 0 | 0 | 0 | 0 | 175 | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPCWP | HRPT - Chelsea Waterside Park Phase 2 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-M245 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CHELSEA WATERSIDE PARK RESTORE SAFETY SURFACE | CHELSEA WATERSIDE PARK RESTORE SAFETY SURFACE | 2022 | 170 | 0 | 5571 | 0 | 0 | 0 | 0 | 0 | 5571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPDG8 | HUDSON RIVER PARK TRUST PIER 84 DOG RUN | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-M245 |  |  | HUDSON RIVER PARK TRUST RENOVATION TO PIER 84 DOG RUN | 2022 | 525 | 0 | 907 | 0 | 0 | 0 | 0 | 0 | 907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPP40 | Hudson River Park Trust - Pier 40 Repairs | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-D018 |  |  | PIER 40 REPAIRS | 2022 | 10645 | 9615 | 276 | 0 | 0 | 0 | 0 | 0 | 9891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPT34 | HUDSON RIVER PARK | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1246 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HUDSON RIVER PARK | 2022 | 3400 | 0 | 0 | 3409 | 0 | 0 | 0 | 0 | 3409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3HRPTEN | Houston St. Tennis Courts RC | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  |  | HUDSON RIVER PARK -- HOUSTON STREET TENNIS COURT REPAVING | 2022 | 550 | 504.04 | 46 | 0 | 0 | 0 | 0 | 0 | 550.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3INHILL | Inwood Hill Park - Baseball fields,Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INWOOD HILL PARK- BASEBALL, SOCCER, & DOG RUN, MANHATTAN | 2022 | 682 | 995 | 76 | 0 | 3840 | 3616 | 0 | 0 | 8527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3INWDPK | Inwood Hill Park MG-819M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  | MANHATTAN | INWOOD HILL PARK | 2022 | 700 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LASKE2 | CPC Reconstruction of the Pool & Rink at Harlem Meer | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-1300 |  |  | CPC RECONSTRUCTION OF THE POOL & RINK AT HARLEM MEER IN CENTRAL PARK' | 2022 | 50000 | 0 | 21194 | 10002 | 0 | 0 | 0 | 28804 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LFLWER | Little Flower Playground Comfort Station Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  | LITTLE FLOWER PLAYGROUND COMFORT STATION RECONSTRUCTION, MANHATTAN | LITTLE FLOWER PLAYGROUND COMFORT STATION RECONSTRUCTION | 2022 | 1500 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LGTURF | Little Flower Plg Synth. Turf Field Cons, Manhattan MG-316MA | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-1018 |  |  | LA GUARDIA - SYNTHETIC TURF FIELD | 2022 | 745 | 616.11 | 54 | 0 | 0 | 0 | 0 | 0 | 670.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3LMDCCH | LMDC - Corlear's Hook Comfort Station M017-216M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | MANHATTAN | COMFORT STATION CONSTRUCTION | 2022 | 2800 | 1076.82 | 56 | 0 | 155 | 0 | 0 | 0 | 1287.82 | 1999.97 | 0 | 0 | 0 | 0 | 0 | 0 | 1999.97
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MCRPAV | Marcus Garvey | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  | MANHATTAN | MARCUS GARVEY PARK PATH RECONSTRUCTION | 2022 | 2400 | 0 | 0 | 0 | 2210 | 2190 | 0 | 0 | 4400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MORJUM | MORRIS-JUMEL MANSION: TECHNOLOGY/ELECTRICAL UPGRADE | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-M094 |  |  | MORRIS-JUMEL MANSION: TECHNOLOGY/ELECTRICAL UPGRADE | 2022 | 38 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MORNHR | MORNINGSIDE PARK HANDRAILS | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-M245 P-D018 |  |  | MORNINGSIDE PARK INSTALL HANDRAILS IN STAIRS LOCATED AT EAST 113TH STREET, MANHATTAN | 2022 | 250 | 100 | 0 | 550 | 0 | 0 | 0 | 0 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3MRNGPK | Morningstar Park MG-819M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  | MANHATTAN | MORNINGSTAR PARK | 2022 | 600 | 86 | 950 | 0 | 0 | 0 | 0 | 0 | 1036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3NRGF01 | NRG- Manhattan Reforestation FY 20- MG-619MA | LAND ACQUISITION AND TREE PLANTING | 300 | P-0822 |  | BOROUGH OF MANHATTAN | MANHATTAN REFORESTATION | 2022 | 1035 | 0 | 0 | 0 | 1035 | 0 | 0 | 0 | 1035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3P155CS | PS 155 Plgd-Comfort Station Recon.-ADA Acessible | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-M245 P-D018 |  |  | PS155 PLAYGROUND COMFORT STATION ADA ACCESS--RECONSTRUCT THE COMFORT STATION TO UPGRADE IT AND MAKE ADA ACCESSIBLE | 2022 | 1460 | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3P40SPR | Hudson River Park Pier 40 Fire Sprinkler Recon | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1246 |  |  | HUDSON RIVER PARK PIER 40 FIRE SPRINKLER RECON | 2022 | 3455 | 3455 | 330 | 0 | 0 | 0 | 0 | 0 | 3785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PAVTMK | Tompkins Sq Park Paths & Multi-Purpose Play Area Pave RC | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  | MANHATTAN | THIS PROJECT WILL RECONSTRUCT PAVEMENTS AT TOMPKINS SQUARE PARK, INCLUDING PATHS AND THE MULTI-PURPOSE PLAY AREA (MPPA). THIS IS A STATE OFGOOD REPAIR (SOGR) PROJECT. | 2022 | 2400 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PDHBRC | Hansborough Rec Ctr M131-115M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-1018 P-1008 P-1250 P-D018 P-0506 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | MANHATTAN | HANSBOROUGH REC CTR | 2022 | 4000 | 2333.67 | 692 | 0 | 12617 | 157 | 14214 | 0 | 30013.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PDTDRC | Tony Dapolito Rec Ctr RC M103-115M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-0506 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | MANHATTAN | TONY DAPOLITO REC CTR | 2022 | 4000 | 6940.82 | 1228 | 9150 | 0 | 0 | 0 | 0 | 17318.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PHILSQ | A. PHILLIP RANDOLPH SQUARE RENOVATION Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-M245 P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | A. PHILLIP RANDOLPH SQUARE RENOVATION--PARK RENOVATION 7TH AVENUE, WEST 117TH STREET, ST. NICHOLAS AVE | 2022 | 460 | 0 | 0 | 0 | 0 | 1870 | 0 | 0 | 1870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PIN181 | PINEHURST AV/181ST - STAIRCASE/GARDEN UPGRADES | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-M245 P-D018 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | PINEHURST AVENUE STEPS @ 181ST STREET | PINEHURST AVENUE STEPS @ 181ST STREET : STAIRCASE/GARDEN UPGRADES | 2022 | 625 | 70 | 472 | 0 | 67 | 0 | 0 | 0 | 609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PL14A6 | Ruppert Park Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-M245 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RUPPERT PARK-INSTALL NEW IRRIGATION SYSTEM | RUPPERT PARK-INSTALL NEW IRRIGATION SYSTEM | 2022 | 110 | 110 | 461 | 0 | 5336 | 3097 | 2700 | 0 | 11704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PLG13B | Reconstruction of plgr, Borough of Manhattan MG-213M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 399 | PV-D034 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | THE RECONSTRUCTION OF PAVEMENTS, FENCING, SAFETY SURFACING, PLUMBING,STONE WALLS, STEPS AND GENERAL SITEWORK, MANHATTAN | 2022 | 1817 | 1620.48 | 0 | 117 | 0 | 0 | 0 | 0 | 1737.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3POORRD | POOR RICHARD'S PLAYGROUND RENOVATIONS M230-118MA | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | POOR RICHARD'S PLAYGROUND RENOVATIONS, MAHATTAN | 2022 | 2489 | 343.05 | 2030 | 188 | 29 | 0 | 0 | 0 | 2590.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PS155M | PS155M Playground , Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-M245 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PS 155M PLAYGROUND (DPR) -- PLAYGROUND RECONSTRUCTION MANAGED BY PARKS | PS 155M PLAYGROUND (DPR) -- PLAYGROUND RECONSTRUCTION MANAGED BY PARKS | 2022 | 1000 | 433.2 | 0 | 0 | 3312 | 0 | 0 | 0 | 3745.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3PWBJRP | PWOB - Jackie Robinson Pk stairways, fencing, sidewalks, (M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1329 P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PWB - JACKIE ROBINSON PARK (M | PWB - JACKIE ROBINSON PARK STAIRWAYS, FENCING, SIDEWALKS, (M | 2022 | 6000 | 5477.08 | 0 | 0 | 0 | 276 | 0 | 0 | 5753.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3QUISCS | Quisqueya Playground-Reconstruction of Comfort Station | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0505 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | QUISQUEYA PLAYGROUND-RECONSTRUCTION OF COMFORT STATION | 2022 | 1710 | 254 | 0 | 0 | 1704 | 0 | 0 | 0 | 1958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3R5422A | Constance Baker Motley Recreation Center Recon. M130-122M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-1250 P-0506 |  |  | "RECREATION CENTER 54 RECEIVED AN EMERGENCY DECLARATION FROM DOB ON 1/27/2020 (BACKUP ATTACHED) CALLING FOR THE EXPEDITED INSTALLATION OF ASIDEWALK SHED DUE TO THE SEVERITY OF THE UNSAFE CONDITION POSED BY THE REC CENTER FA×ADE, WHICH HAS BEEN PROVIDED. THE CONDITION WHICH RESULTED IN THE EMERGENCYDECLARATION IS OUTSTANDING, AND NEEDS TO BE ADDRESSED IN ORDER TO REMOVE THE SIDEWALK SHED. AS CONDITION EXACERBATES OVER TIME, ADDITIONAL RISK TO PUBLIC HEALTH AND SAFETY MAY BE IDENTIFIED RESULTING IN ADDITIONAL DOB EMERGENCY VIOLATIONS UNLESS THE FA×ADE IS REPAIRED. FUNDING IS REQUESTED TO REHABILITATE/RECONSTRUCT THE FA×ADE AT THE RECREATION CENTER IN ORDER TO ALLEVIATE THE UNSAFE CONDITION NOTED BY DOB AND EL | 2022 | 16105 | 0 | 1656 | 107 | 7349 | 1874 | 7200 | 0 | 18186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RANDSC | Randall's Island Sunken Garden Connector | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-0245M P-D018 P-M245 P-1018 |  |  | RANDALL'S ISLAND SUNKEN GARDEN CONNECTOR (NEW PROJECT) ¦ NYSDOT PIN# X773.98 | 2022 | 794 | 0 | 0 | 0 | 0 | 650 | 0 | 0 | 650 | 0 | 0 | 0 | 794 | 0 | 0 | 0 | 794
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RANDVC | RANDALL'S ISLAND VISITOR CENTER | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-M245 |  |  | CONSTRUCT A NATURE CENTER AT RANDALL'S ISLAND PARK, MANHATTAN | 2022 | 239 | 0 | 0 | 239 | 0 | 0 | 0 | 0 | 239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3REC54E | RECREATION CTR 54 FITNESS EQUIPMENT-FUNDING FOR NEW FITNESS | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-0505 |  |  | RECREATION CENTER 54 FITNESS EQUIPMENT -- FUNDING FOR NEW FITNESS EQUIPMENT | 2022 | 125 | 0 | 322 | 0 | 0 | 0 | 0 | 0 | 322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIV105 | Riversidw Park, 105Street MG-519M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MANHATTAN | RIVERSIDE PARK, 105 ST | 2022 | 840 | 0 | 840 | 20 | 0 | 0 | 0 | 0 | 860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIV110 | Riverside Park, 110 Street | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  | MANHATTAN | RIVERSIDE PARK, 110STREET | 2022 | 450 | 0 | 0 | 385 | 0 | 0 | 0 | 0 | 385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIV148 | Riverside Park, 148 Street MG-519M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  | MANHATTAN | RIVERSIDE PARK, 148TH STREET | 2022 | 110 | 10 | 90 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVDIN | Riverside Park - Dinosaur Playground | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-0380 |  | BOROUGH OF MANHATTAN | RIVERSIDE PARK DINOSAUR PLAYGROUND | 2022 | 1300 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVFTW | Shoreline Work in Riverside and Fort Washington Parks | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  |  | ASSOCIATED SANDY ID IS SANDY3-13 | 2022 | 147 | 141.59 | 38 | 0 | 0 | 0 | 0 | 0 | 179.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVRMP | RIVERSIDE PARK: RIVERSIDE PARK 105TH STREET STEP RAMP RECON | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-M245 P-0380 |  |  | RIVERSIDE PARK: RIVERSIDE PARK 105TH STREET STEP RAMP RECONSTRUCTION | 2022 | 200 | 0 | 0 | 0 | 1500 | 1200 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVS83 | Riverside Park, 83rd Street MG-519M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  | MANHATTAN | RIVERSIDE PARK, 83 STREET | 2022 | 245 | 58 | 275 | 0 | 0 | 0 | 0 | 0 | 333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVS97 | Riverside Park, 97th Street MG-519M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  | MANHATTAN | RIVERSIDE PARK, 97TH STREET | 2022 | 550 | 30 | 520 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RIVSTR | RIVERSIDE PARK--102nd ST Staircase, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-M245 P-0380 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RIVERSIDE PARK--101ST STAIRCASE PROJECT | 2022 | 818 | 430.65 | 13 | 1167 | 1571 | 0 | 0 | 0 | 3181.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RNDLGL | Recon gas line at Randalls Island | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0245M |  | RANDALLS ISLAND, MANHATTAN | RECON GAS LINE AT RANDALLS ISLAND | 2022 | 340 | 0 | 340 | 0 | 0 | 0 | 0 | 0 | 340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RNDLOT | Randall's Island PEP Office Trailer Parking Lot M104-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0944 P-1018 |  | RANDALL'S ISLAND | THIS PROJECT IS FOR THE PARKING LOT AT THE RANDALL'S ISLAND PEP OFFICE TRAILER | 2022 | 6954 | 5026.99 | 0 | 1 | 0 | 368 | 0 | 0 | 5395.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RSOVAL | Riverside Oval: Water Line Hookup | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-M822 |  | RIVERSIDE OVAL | WATER LINE HOOKUP | 2022 | 125 | 0 | 0 | 0 | 238 | 0 | 0 | 0 | 238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RVPFWP | Riverside Park and Fort Washington Park Greenway Reconstruct | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  | MANHATTAN | RIVERSIDE PARK AND FORT WASHINGTON PARK GREENWAY RECONSTRUCTION | 2022 | 2300 | 50 | 0 | 0 | 1300 | 1000 | 0 | 0 | 2350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3RVSSCA | Riverside Pk-Skate park at 109 St., M071-115MA | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-M380 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | EAST RIVER PK-SKATE PARK AT 109 STR | EAST RIVER PK-SKATE PARK AT 109 STR | 2022 | 1000 | 3110.71 | 0 | 0 | 0 | 303 | 0 | 0 | 3413.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SEWARD | SEWARD PARK- RESTORATION OF SCHIFF FOUNTAIN | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RESTORATION OF SCHIFF FOUNTAIN -SEWARD PARK | 2022 | 272 | 36 | 0 | 0 | 0 | 0 | 79 | 0 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SHARCS | Sheltering Arms Playgound Comfort Station M190-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0505 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | WEST 129TH STREET, AMSTERDAM AVENUE, WEST 126TH STREET, OLD BROADWAY | THIS PROJECT WILL RECONSTRUCT THE COMFORT STATION IN SHELTERING ARMS PLAYGROUND. | 2022 | 1493 | 274 | 1543 | 0 | 153 | 0 | 0 | 0 | 1970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SHRMRW | ROW NEW YORK: SHERMAN CREEK FLOATING DOCK AND GANGWAY | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-M245 P-D018 |  |  | ROW NEW YORK, INC: MOVEABLE PROPERTY FOR FLOATING DOCK AND GANGWAY AT SHERMAN CREEK | 2022 | 150 | 0 | 0 | 0 | 0 | 1155 | 0 | 0 | 1155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SOHAGS | Green Street Fencing - Amsterdam Ave and 126th St. | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-M245 |  |  | GREEN STREET FENCING - AMSTERDAM AVE AND 126TH ST. | 2022 | 65 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SOHO | SOHO Square Manhattan (MG25000-116M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | MANHATTAN | RECONSTRUCTION OF SOHO SQUARE | 2022 | 1512 | 806.42 | 0 | 0 | 0 | 0 | 0 | 0 | 806.42 | 2923.79 | 0 | 0 | 544 | 0 | 0 | 0 | 3467.79
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SPT21B | Street Tree Planting - Man.-Sm. Pur. CB MG-321M | LAND ACQUISITION AND TREE PLANTING | 300 | P-1018 |  | BOROUGH OF MANHATTAN | STREET TREES | 2022 | 551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 1 | 0 | 0 | 0 | 0 | 501
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SRAWIN | BRC Senior Ctr Sara D., Park (MN) window replace CNYG-2819M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 P-D018 |  | SARA D., PARK (MN) | BRC SENIOR CENTER IN SARA D., PARK (MN) WINDOW REPLACE | 2022 | 600 | 0 | 920 | 82 | 0 | 0 | 0 | 0 | 1002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3STFCRL | Syn turf renovation at Corlears hook in Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0510 |  | CORLEARS HOOK IN MANHATTAN | SYN TURF RENOVATION AT CORLEARS HOOK IN MANHATTAN | 2022 | 1443 | 0 | 0 | 1443 | 0 | 0 | 0 | 0 | 1443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3STNICK | St. Nicholas Park MG-819M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  | MANHATTAN | PAVEMENT RECONSTRUCTION | 2022 | 500 | 18 | 500 | 0 | 0 | 0 | 0 | 0 | 518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SUTTON | ONE SUTTON PLACE PARK CONSTRUCTION (M108-111M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 306 | P-D018 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | ONE SUTTON PLACE PARK, MANHATTAN | ONE SUTTON PLACE PARK - CONSTRUCT NEW PARK, MANHATTAN | 2022 | 600 | 1441.31 | 75 | 0 | 0 | 0 | 0 | 0 | 1516.31 | 749.79 | 0 | 0 | 0 | 0 | 0 | 0 | 749.79
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3SUTTPK | SUTTON PLACE PARK.- Fountain & Spray Shower, Mahattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SUTTON PLACE PARK.- FOUNTAIN & SPRAY SHOWER, MAHATTAN | 2022 | 850 | 13.98 | 0 | 0 | 0 | 0 | 450 | 0 | 463.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TDCREC | MNHTN REC CTR-FITNESS EQUIPMENT-TONY DAPOLITO & CHELSEA CTR | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 P-D933 |  |  | MANHATTAN RECREATION CENTERS -- FITNESS EQUIPMENT FOR TONY DAPOLITO AND CHELSEA RECREATION CENTERS | 2022 | 260 | 0 | 260 | 0 | 0 | 0 | 0 | 0 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TDREC2 | Reconstruction of Tony Dapolito Recreation Center-Phase 2 | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-0506 |  |  | RECONSTRUCTION OF TONY DAPOLITO RECREATION CENTER -PHASE 2 | 2022 | 62261 | 0 | 0 | 0 | 0 | 0 | 6261 | 56000 | 62261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TJRCUP | Thomas Jefferson Recreational Center-Upgrades | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  |  | THOMAS JEFFERSON RECREATIONAL CENTER --UPGRADES | 2022 | 330 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TOMJPK | Thomas Jefferson Park Plg Reconst. Mahattan (M047-118M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  | EAST 114TH STREET BETWEEN PLEASANT AVENUE AND 1ST AVENUE | THIS PROJECT WILL RECONSTRUCT THOMAS JEFFERSON PLAYGROUND. | 2022 | 2920 | 2722.58 | 143 | 0 | 0 | 0 | 0 | 0 | 2865.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TONYDL | Tony Dapolito RC Ctr 7th Ave Sidewalk Vault & Pool Stb rest | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-0506 |  |  | TONY DAPOLITO RECREATION CENTER - 7TH AVENUE SIDEWALK VAULT RESTORATION AND POOL STABILIZATION | 2022 | 5126 | 75 | 0 | 0 | 513 | 1713 | 0 | 0 | 2301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE20A | FY 20 Street Tree Mnht CB 1,3,5,6,8,11 MG-319M | LAND ACQUISITION AND TREE PLANTING | 300 | P-0822 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | FY 20 STREET TREE MNHT CB 1,3,5,6,8,11 MG-319M | FY 20 STREET TREE MNHT CB 1,3,5,6,8,11 MG-319M | 2022 | 3768 | 3659.5 | 0 | 0 | 0 | 67 | 0 | 0 | 3726.5 | 1288 | 0 | 0 | 0 | 0 | 0 | 0 | 1288
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE22A | Manhattan Street Tree Planting & Comm. Green. FY 22 MG-322M | LAND ACQUISITION AND TREE PLANTING | 300 | P-0822 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF MANHATTAN | MANHATTAN LOWER EAST SIDE STREET TREE PLANTING AND COMMUNITY GREENINGFY22 | 2022 | 450 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TRE22B | Manhattan Park Tree Planting FY 22 | LAND ACQUISITION AND TREE PLANTING | 300 | P-1018 WM-0001 S-0216 P-0822 |  | BOROUGH OF MANHATTAN | MANHATTAN PARTK TREE PLANTING | 2022 | 993 | 0 | 0 | 223 | 650 | 0 | 0 | 0 | 873 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 120
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TREL21 | FY21 Street Trees MN CB's 1,2,4,5,,7-12 (3Y) MG-1319M | LAND ACQUISITION AND TREE PLANTING | 300 | HB-1027 P-1018 P-0822 P-D018 |  | MANHATTAN | FY21 STREET TREES MN CB'S 1,2,4,5,,7-12 (3Y) | 2022 | 3371 | 145 | 21 | 6461 | 0 | 0 | 0 | 0 | 6627 | 0 | 6018 | 0 | 0 | 0 | 0 | 0 | 6018
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3TREP22 | Manhattan - Street Tree Plant. FY-22 CD-5- MG-222M | LAND ACQUISITION AND TREE PLANTING | 300 | P-1018 P-D822 |  | BOROUGH OF MANHATTAN | MANHATTAN STREET TREE PLANTING FY22 - COUNCIL DISTRICT 5 | 2022 | 650 | 0 | 0 | 413 | 0 | 0 | 0 | 0 | 413 | 0 | 0 | 87 | 0 | 0 | 0 | 0 | 87
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3W185BC | WEST 186TH ST BASKEBALL COURTS, Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-D018 |  |  | ONE HALF COURTS - WEST 186TH ST BASKEBALL COURTS -- TO BUILD ONE HALFCOURT | 2022 | 400 | 0 | 0 | 0 | 1110 | 0 | 0 | 0 | 1110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-3W69SB2 | West 69th Street transverse bridge - phase 2 M353-212M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 307 | P-0380 P-0245M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | WEST 69TH TRANSVERSE BRIDGE PHASE 2 | WEST 69TH TRANSVERSE BRIDGE PHASE 2 | 2022 | 650 | 363 | 0 | 0 | 786 | 0 | 0 | 0 | 1149 | 447.88 | 0 | 2950 | 0 | 0 | 0 | 0 | 3397.88
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-5STFMHN | Synthetic Turf Field Reconstruction at Mahoney Park, SI | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  | STATEN ISLAND | SYNTHETIC TURF FIELD RECONSTRUCTION AT MAHONEY PARK, SI | 2022 | 508 | 0 | 462 | 0 | 46 | 0 | 0 | 0 | 508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | P-6STFMAT | Purchase syn turf materials to recon fields in Manhattan | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-0245M |  | MANHATTAN | PURCHASE SYN TURF MATERIALS TO RECON FIELDS IN MANHATTAN | 2022 | 1111 | 663.1 | 0 | 448 | 0 | 0 | 0 | 0 | 1111.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SAND3TREE | FY21- ESCR Tree Planting, Manhattan MG-1219M | LAND ACQUISITION AND TREE PLANTING | 300 | PU-0100 |  | MANHATTAN | FY21- ESCR TREE PLANTING, MANHATTAN | 2022 | 0 | 100 | 22784 | 0 | 0 | 0 | 0 | 0 | 22884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SAND4TREE | ESCR -Stormwater Greenstreets Construction- MG-421M | LAND ACQUISITION AND TREE PLANTING | 300 | PU-0100 |  | BOROUGH OF MANHATTAN | ESCR -FY21-RAIN GARDENS | 2022 | 8950 | 60 | 0 | 0 | 5045 | 0 | 0 | 0 | 5105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SAND5TREE | ESCR- Right of Way Bioswale Construction | LAND ACQUISITION AND TREE PLANTING | 300 | PU-0100 |  | BOROUGH OF MANHATTAN | VARIOUS LOCATIONS - CONSTRUCTION OF RIGHT OF WAY BIOSWALES | 2022 | 4000 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-02 | SANDY - Manhattan Plgd requirements (Type 1) MG-112M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION OF PLAYGROUNDS DAMAGED BY HURRICANE SANDY IN THE BOROUGH OF MANHATTAN | 2022 | 1949 | 139.86 | 0 | 0 | 0 | 0 | 0 | 0 | 139.86 | 758.84 | 0 | 0 | 0 | 0 | 0 | 234 | 992.84
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-03 | SANDY - John Jay & Tony Dapolito - boilers (MG-113M) | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SANDY SAFE-UP MANHATTAN BOILER REPLACEMENTS | 2022 | 862 | 311.14 | 107 | 0 | 0 | 0 | 0 | 0 | 418.14 | 908.56 | 0 | 0 | 0 | 0 | 0 | 962 | 1870.56
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-06 | SANDY - PNP Friends of the Highline | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 304 | P-1018 | PROJECT DELAYED PENDING NON-CITY GRANT APPROVAL | MANHATTAN | HIGHLINE | 2022 | 336 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 302 | 302
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-07 | SANDY - PNP Asphalt Green | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 308 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MANHATTAN | ASPHALT GREEN | 2022 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 139 | 139
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-08 | SANDY - PNP Battery Conservancy | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 301 | P-1018 | PROJECT DELAYED PENDING NON-CITY GRANT APPROVAL | MANHATTAN | BATTERY PARK | 2022 | 650 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 506 | 0 | 0 | 0 | 506
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-09 | SANDY - PNP Riverside Park Conservancy | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 307 309 | P-1018 | PROJECT DELAYED PENDING NON-CITY GRANT APPROVAL | MANHATTAN | RIVERSIDE PARK | 2022 | 446 | 2.48 | 0 | 0 | 0 | 0 | 0 | 45 | 47.48 | 0 | 0 | 0 | 0 | 0 | 0 | 401 | 401
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-11 | Vietnam Vet. Memorial Lighting (M046-114M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SOUTH STREET, MANHATTAN | R/C OF LIGHTING & ELECTR. AT VIETNAM VET. PLAZA,MANHATTAN | 2022 | 600 | 142.95 | 166 | 0 | 0 | 0 | 0 | 0 | 308.95 | 0 | 1477 | 0 | 0 | 0 | 0 | 0 | 1477
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-13 | SANDY-Riverside & F. Washington Pk Shoreline (Type 3 ) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED PENDING NON-CITY GRANT APPROVAL | RIVERSIDE & F. WASHINGTON PARKS, MANHATTAN | SHORELINE WORK IN RIVERSIDE & F. WASHINGTON PK | 2022 | 1770 | 728.25 | 10 | 0 | 0 | 0 | 0 | 0 | 738.25 | 1519.36 | 78 | 0 | 0 | 0 | 0 | 0 | 1597.36
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-17 | SANDY- E.River Esplanade (Glick Park)-Elec (Type 3) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | EAST RIVER ESPLANADE (GLICK PARK) , BOROUGH OF MANHATTAN | EAST RIVER ESPLANADE (GLICK PK)- ELECTRICAL REPAIR | 2022 | 239 | 234.47 | 8 | 0 | 0 | 0 | 0 | 0 | 242.47 | 551.3 | 58 | 0 | 0 | 0 | 0 | 0 | 609.3
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-18 | SANDY - Mannahatta Fountains RC (Type 3) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | MANNAHATTA (WALL STREET) , BOROUGH OF MANHATTAN | FOUNTAIN DAMAGE AND ELECTRICAL REPAIR | 2022 | 1640 | 367.35 | 0 | 0 | 292 | 0 | 0 | 0 | 659.35 | 356.4 | 0 | 0 | 2608 | 0 | 0 | 0 | 2964.4
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-19 | SANDY - John Jay & Tony Dapolito - Electrical (Balance) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SANDY - JOHN JAY & TONY DAPOLITO - ELECTRICAL (BALANCE) | 2022 | 1018 | 0 | 0 | 0 | 0 | 0 | 102 | 0 | 102 | 0 | 0 | 0 | 0 | 0 | 916 | 0 | 916
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-20 | Playground 103 (CIII) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PLAYGROUND 103 (CIII) | 2022 | 795 | 63.96 | 14 | 0 | 0 | 0 | 0 | 0 | 77.96 | 500 | 0 | 0 | 0 | 0 | 0 | 125 | 625
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-21 | Four Parks Safety Surface | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FOUR PARKS SAFETY SURFACE | 2022 | 718 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 646 | 646
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-24 | SANDY-Inwood Nature Center Exhibit Displays | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 300 | P-1018 |  | INWOOD HILL NATURE CENTER, MANHATTAN | RECONSTRUCTION OF INWOOD NATURE CENTER EXHIBIT DISPLAY | 2022 | 330 | 17.62 | 25 | 0 | 0 | 0 | 0 | 0 | 42.62 | 67 | 230 | 0 | 0 | 0 | 0 | 0 | 297
20220309 | MANHATTAN | 846 | DEPT OF PARKS AND RECREATION | SANDY3-25 | Riverside Park Electrical Repairs | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | P-1018 |  | RIVERSIDE DR. TO HUDSON RIVER, W. 72 ST.TO ST CLAIR PL. MANHATTAN. | RIVERSIDE PARK ELECTRICAL REPAIRS. | 2022 | 1691 | 0 | 169 | 0 | 0 | 0 | 0 | 0 | 169 | 0 | 1522 | 0 | 0 | 0 | 0 | 0 | 1522
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | 70MULBREC | 70 MULBERRY STREET - RECONSTRUCTION | RENOVATION OF OTHER CITY-OWNED FACILITIES | 301 | PW-0077 |  |  | RECONSTRUCTION OF 70 MULBERRY STREET, WHICH WAS DEMOLISHED AFTER A FIRE. | 2022 | 80000 | 0 | 13588 | 0 | 80000 | 0 | 76412 | 0 | 170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | AGNYCHANG | NYCHANGE PROJECT WITH DFTA | DEPARTMENT FOR THE AGING BUILDING RECONSTRUCTION | 303 | AG-0001 AG-D001 HR-0025 AG-M001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SEPT 2012 ADD 254 PROJECT. NYCHANGE PROJECT WITH DFTA. SCOPE IS TO UPGRADE THE SENIOR CENTER AND EXTERIOR GARDEN. | 2022 | 1000 | 1691.01 | 0 | 0 | 0 | 10648 | 9096 | 0 | 21435.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-M | Borough Based Jails New Manhattan Detention Facility | New Jail Facilities |  | C-0114 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CONSTRUCTION OF NEW MANHATTAN FACILITY | 2022 | 2188413 | 0 | 108359 | 402697 | 480029 | 511213 | 394022 | 161093 | 2057413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC1C3 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | 49-51 CHAMBERS AND 346 BROADWAY 21C3 | 2022 | 3740 | 8876.8 | 250 | 55 | 0 | 0 | 0 | 0 | 9181.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CC253B | 100 GOLD- 21C3 | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 253 BROADWAY 21C3 | 2022 | 17078 | 16879.94 | 0 | 139 | 0 | 0 | 0 | 0 | 17018.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283SID2 | 100 CENTRE STREET - SIDEWALK REPLACEMENT | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 301 | CO-0283 CO-0264 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 100 CENTRE STREET - SIDEWALK REPLACEMENT | 2022 | 6808 | 7707.28 | 132 | 0 | 0 | 0 | 0 | 0 | 7839.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283TOIL | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 301 | CO-0283 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 100 CENTRE ST.- CODE COMPLIANT TOILET UPGRADE | 2022 | 5500 | 1103.54 | 384 | 1623 | 10927 | 0 | 0 | 0 | 14037.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO283WT | 100 CENTRE STREET - WATER TANK | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 301 | CO-0283 |  |  | 100 CENTRE STREET - WATER TANK | 2022 | 3769 | 230 | 0 | 4015 | 0 | 0 | 0 | 0 | 4245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO285FIRE | 60 LAFAYETTE ST - FIRE ALARM UPGRADE | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 301 | CO-0285 |  |  | 60 LAFAYETTE ST - FIRE ALARM DESIGN & REPLACEMENT | 2022 | 10826 | 909.48 | 2163 | 10051 | 0 | 0 | 0 | 0 | 13123.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO304REHB | 60 CENTRE ST. - RECONSTRUCTION | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 301 | CO-0304 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 60 CENTRE STREET, NEW YORK, NY | RESTORATION OF THE BUILDING ENVELOPE INTEGRITY - BASEMENT, ROOF & FACADE | 2022 | 15869 | 2169.96 | 310 | 1540 | 13295 | 0 | 0 | 0 | 17314.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO306EXT2 | 170 E121 ST. EXTERIOR - LL11 | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 311 | CO-0306 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FACADE | 2022 | 1633 | 0 | 243 | 0 | 2751 | 0 | 0 | 0 | 2994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO306REHB | 170-74 E 121ST STREET - HARLEM COURT FIRE PROTECTION | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 311 | CO-0306 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HARLEM COURTHOUSE REHABILITATION | 2022 | 1970 | 0 | 0 | 568 | 0 | 0 | 5510 | 0 | 6078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO80ROOF2 | 27 MADISON AVE - ROOF & MISC. OPERATIONS SPACES UPGRADE | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 305 | CO-0080 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | 27 MADISON AVE - ROOF & MISC. OPERATIONS SPACES UPGRADE | 2022 | 3881 | 2378.2 | 0 | 0 | 0 | 0 | 0 | 0 | 2378.2 | 13230.75 | 64 | 0 | 0 | 0 | 0 | 0 | 13294.75
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81ELEC | 31 CHAMBERS ST. - ELECTRICAL AND FA SYSTEM UPGRADE | IMPROVEMENT AND EXPANSION OF COURT FACILITIES | 301 | CO-0081 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MANHATTAN SURROGATE'S COURT ELECTRICAL AND FIRE ALARM SYSTEM UPGRADESAND DOOR REPLACEMENTS | 2022 | 19090 | 100 | 0 | 0 | 2000 | 0 | 30060 | 0 | 32160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | CO81SKY2 | 31 CHAMBERST ST.- RENOVATE SKYLIGHT | IMPROVEMENT AND EXPANSION OF COURT FACILITIES | 301 | CO-0081 CO-0264 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SKYLIGHT RESTORATION AND SURROUNDING SPACE | 2022 | 6189 | 10283.69 | 8 | 53 | 0 | 0 | 0 | 0 | 10344.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E14-0017 | DHS - Bellevue Men's Shelter | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | DHS - BELLEVUE MEN'S SHELTER | 2022 | 2782 | 5153.82 | 76 | 0 | 0 | 0 | 0 | 0 | 5229.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0003 | DCAS - Manhattan Civil Court | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | MANHATTAN CIVIL COURT | 2022 | 3780 | 5533.24 | 100 | 453 | 0 | 0 | 0 | 0 | 6086.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0005 | DSNY -Manhattan 3 District Garage | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 303 | PU-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | MANHATTAN 3 DISTRICT GARAGE | 2022 | 3427 | 1851.05 | 50 | 35 | 0 | 0 | 0 | 0 | 1936.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | E17-0001 | DCAS - LOUIS J LEFKOWITZ - ENERGY EFFICIENCY UPGRADE | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 302 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ENERGY EFFICIENCY UPGRADE | 2022 | 3422 | 1543.19 | 7100 | 350 | 350 | 0 | 0 | 0 | 9343.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | EO26-0002 | DCAS-Manhattan Municipal Building | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | CITY HALL CAMPUS: MANHATTAN MUNICIPAL BUILDING - HEAT LIGHT INSTALLATION | 2022 | 300 | 0 | 1122 | 0 | 0 | 0 | 0 | 0 | 1122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | F175MCE23 | ELECTRIC & TOILETS - EC23 | NEW FACILITIES AND RENOVATIONS | 305 | F-0175 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ELECTRIC & TOILETS - EC23 | 2022 | 1201 | 6842.32 | 41 | 0 | 0 | 0 | 0 | 0 | 6883.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HBFDR14BP | East 14th St (near ConEd Plant) Bike Path | FAIR BRIDGES | 300 | P-0508 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | EAST 14TH ST (NEAR CONED PLANT) BIKE PATH | EAST 14TH ST (NEAR CONED PLANT) BIKE PATH | 2022 | 39122 | 0 | 10750 | 0 | 0 | 171378 | 0 | 0 | 182128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HBMA24662 | W 128TH ST PED BRIDGE BIN:2246620 | FAIR BRIDGES | 300 | HB-0215 |  | W 128TH ST PED BRIDGE BIN:2246620 | W 128TH ST PED BRIDGE BIN:2246620 | 2022 | 14143 | 2464.61 | 0 | 0 | 12511 | 0 | 0 | 0 | 14975.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED100M | PED BRIDGE - E 81 ST (M) | FAIR BRIDGES | 300 308 | P-0245M | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PED BRIDGE - E 81 ST (M) | PED BRIDGE - E 81 ST (M) | 2022 | 18118 | 17177.22 | 676 | 0 | 0 | 0 | 0 | 0 | 17853.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BEES | BELLEVUE - ELECT SVC UPGRADE | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BELLEVUE - ELECT SVC UPGRADE | 2022 | 3131 | 18943.73 | 3754 | 0 | 0 | 0 | 0 | 0 | 22697.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLBR | BELLEVUE BATHROOMS RECONSTRUCTION | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RECONSTRUCT ALL BATHROOMS AT BELLEVUE MEN'S SHELTER | 2022 | 18200 | 1681.63 | 299 | 0 | 0 | 3000 | 8339 | 5499 | 18818.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLCY | BELLEVUE COURTYARD | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECONSTRUCT COURTYARD AT BELLEVUE | 2022 | 5700 | 0 | 0 | 0 | 0 | 0 | 250 | 5000 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLEN | BELLEVUE MAIN ATRIUM | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECONSTRUCT MAIN ATRIUM ENTRANCEWAY AT BELLEVUE | 2022 | 11200 | 1443.8 | 0 | 0 | 0 | 0 | 775 | 9571 | 11789.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLFS | BELLEVUE MEN'S RESIDENCE- FIRE SAFETY | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | UPGRADE AND MODERNIZE FIRE SAFETY SYSTEM | 2022 | 14792 | 1192.98 | 200 | 2000 | 6000 | 6660 | 0 | 0 | 16052.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112BLRR | BELLEVUE ROOF/ FACADE | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BELLEVUE ROOF/ FACADE | 2022 | 19139 | 20409.11 | 2500 | 5000 | 9555 | 12353 | 6080 | 0 | 55897.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CGIU | Keener Assessment Shelter - Fire Alarm Upgrade | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | ADULT SHELTER AT 65 CHARLES GAY LOOP - INTERIOR UPGRADE | 2022 | 1320 | 244.14 | 946 | 0 | 0 | 0 | 0 | 0 | 1190.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CTFS | CLARKE THOMAS FIRE SAFETY | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CLARKE THOMAS FIRE SAFETY | 2022 | 1855 | 336.79 | 642 | 0 | 0 | 0 | 0 | 0 | 978.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FTRF | FT. WASHINGTON ARMORY ROOF REPLACEMENT | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FORT WASHINGTON ARMORY - ROOF REPLACEMENT | 2022 | 5400 | 1034.69 | 230 | 3000 | 7968 | 0 | 0 | 0 | 12232.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112FWFA | FT. WASHINGTON - FIRE ALARM | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FT. WASHINGTON - FIRE ALARM | 2022 | 639 | 2537.32 | 37 | 0 | 3277 | 0 | 0 | 0 | 5851.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HMFA | HARLEM 1 FIRE SAFETY | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HARLEM 1 FIRE SAFETY | 2022 | 886 | 412.21 | 0 | 0 | 0 | 0 | 0 | 618 | 1030.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112HSFA | HELP SEC - FIRE SAFETY | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HELP SEC - FIRE SAFETY | 2022 | 2406 | 779.34 | 180 | 0 | 1965 | 0 | 0 | 0 | 2924.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112KEFA | Kenton Hall Fire Safety | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FIRE SAFETY SYTEM | 2022 | 630 | 310.69 | 0 | 1349 | 0 | 0 | 0 | 0 | 1659.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112KELC | 282 EAST 3RD STREET - ELECTRICAL UPGRADE | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | EAST 3RD STREET - KITCHENS AND ELECTRICAL UPGRADE | 2022 | 5000 | 822 | 0 | 670 | 0 | 0 | 2300 | 2300 | 6092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112SWFA | SCHWARTZ WARDS ISLAND FIRE SAFETY | SHELTERS FOR HOMELESS INDIVIDUALS | 311 | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FIRE SAFETY SYSTEM | 2022 | 2488 | 254.97 | 0 | 850 | 1500 | 0 | 0 | 0 | 2604.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112THFA | 8 EAST THIRD ST SHELTER FIRE SAFETY | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FIRE SAFETY SYSTEM | 2022 | 1110 | 0 | 0 | 1150 | 0 | 0 | 0 | 0 | 1150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112THKR | 8 EAST THIRD KITCHEN DDC | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | KITCHEN REHAB | 2022 | 1300 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCEK | Jennie Clarke Elec and Kitchen | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | JENNIE CLARKE ELECTRIC AND KITCHEN | 2022 | 7253 | 63 | 0 | 0 | 0 | 0 | 0 | 8403 | 8466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCFB | JENNIE CLARK RESIDENCE - FIRE ALARM UPGRADE | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | JENNIE CLARK RESIDENCE - FIRE ALARM UPGRADE | 2022 | 1598 | 1175.17 | 0 | 0 | 449 | 0 | 0 | 0 | 1624.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115REGX | REGENT FAMILY RESIDENCE EXTERIOR UPGRADE | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ALL ARCHITECTURAL AND ENGINEERING DESIGN SERVICES DURING CONSTRUCTIONREQUIRED FOR ALL WORK ASSOCIATED WITH THE NECESSARY MASONRY AND APPURTENANCES STABILIZATION AND UPGRADE; REMOVAL OF ALL BUILDING DEPARTMENTVIOLATIONS FOR THE EXTERIOR OF THE FACILITY. | 2022 | 1080 | 12989.74 | 3877 | 2000 | 0 | 0 | 0 | 0 | 18866.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115RFEU | REGENT FAMILY APT. ELEC UPGRADE | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | APT. ELECT UPGRADE | 2022 | 7650 | 1456.71 | 0 | 0 | 3056 | 5000 | 15897 | 0 | 25409.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CHNWH | COMMUNITY HEALTHCARE NETWORK-WASHINGTON HEIGHTS | CLINIC RENOVATION AND REHABILITATION | 312 | HL-D999 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | COMMUNITY HEALTHCARE NETWORK-WASHINGTON HEIGHTS | 2022 | 560 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82MANAT | Manhattan Animal Care Center Upgrade | ANIMAL CARE |  | HL-0082 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | MANHATTAN ANIMAL SHELTER UPGRADE EXISTING GARAGE AND PET RECEIVING CENTER | 2022 | 5000 | 7616.22 | 531 | 0 | 0 | 0 | 0 | 0 | 8147.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWBARUCH | Baruch College - 25th Street Plaza (MED-634) | PRIMARY STREET RECONSTRUCTION | 300 305 306 | HW-1684 TF-0002 TF-0502 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BARUCH COLLEGE - 25TH STREET PLAZA (LOCATED BETWEEN LEX AND 3RD AVE) | BARUCH COLLEGE - 25TH STREET PLAZA (LOCATED BETWEEN LEX AND 3RD AVE) | 2022 | 4100 | 7528.23 | 754 | 0 | 0 | 0 | 0 | 0 | 8282.23 | 4771.19 | 415 | 0 | 0 | 0 | 0 | 0 | 5186.19
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM100SNC | 79TH STREET SBS, MED673 | PRIMARY STREET RECONSTRUCTION | 300 | HW-1684 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 79TH STREET SBS | 79TH STREET SBS | 2022 | 11500 | 2402.12 | 0 | 0 | 21461 | 0 | 0 | 0 | 23863.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM12AVE | 12th Avenue Accessibility Improvements | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M HW-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 12TH AVENUE ACCESSIBILITY IMPROVEMENTS | 12TH AVENUE ACCESSIBILITY IMPROVEMENTS | 2022 | 2300 | 770.08 | 0 | 0 | 0 | 5065 | 0 | 0 | 5835.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM2025 | Delancey Street Safety Improvements (MED-667) | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M HW-0001 HW-D102 HW-M002 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | DELANCEY STREET SAFETY IMPROVEMENTS | 2022 | 24177 | 1035 | 0 | 35918 | 0 | 0 | 0 | 0 | 36953 | 959.38 | 0 | 5290 | 0 | 0 | 0 | 0 | 6249.38
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWM42PSM | 42nd Street Pedestrian Security Measures | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M |  |  | 42ND STREET PEDESTRIAN SECURITY MEASURES | 2022 | 55247 | 0 | 3432 | 0 | 0 | 0 | 50049 | 0 | 53481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMM008 | EAST 86TH ST STREETSCAPE-225 EAST 79TH ,MADISON TO YORK AVE | PRIMARY STREET RECONSTRUCTION | 300 308 | HW-0001M | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | EAST 86TH MERCHANT/RESIDENTS ASSOCIATION-STREETSCAPE IMPRV. | EAST 86TH MERCHANT/RESIDENT ASSOCIATION-STREETSCAPE IMPRV. | 2022 | 1000 | 12408.67 | 0 | 0 | 0 | 0 | 0 | 0 | 12408.67 | 2704 | 0 | 0 | 0 | 0 | 0 | 1094 | 3798
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMME43ST | 43rd Street Shared Street, MED-670 | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 43RD STREET SHARED STREET | HWMME43ST | 2022 | 11000 | 1885.1 | 0 | 0 | 15778 | 0 | 0 | 0 | 17663.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMMLEXAV | Lexington Avenue Pedestrian Safety Improvements - DSGN BUILD | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M HW-0200 HW-0944 TF-0002 TF-0502 |  | LEXINGTON AVENUE PEDESTRIAN SAFETY IMPROVEMENTS | LEXINGTON AVENUE PEDESTRIAN SAFETY IMPROVEMENTS | 2022 | 13715 | 0 | 1377 | 13690 | 0 | 0 | 0 | 0 | 15067 | 0 | 0 | 4893 | 0 | 0 | 0 | 0 | 4893
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMNYPL | New York Public Library Pedestrian Improvements | PRIMARY STREET RECONSTRUCTION | 300 | HW-0200 HW-0001M TF-0002 TF-0502 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | NEW YORK PUBLIC LIBRARY PEDESTRIAN IMPROVEMENTS | NEW YORK PUBLIC LIBRARY PEDESTRIAN IMPROVEMENTS | 2022 | 4832 | 732.89 | 80 | 2899 | 0 | 0 | 0 | 0 | 3711.89 | 0 | 0 | 2993 | 0 | 0 | 0 | 0 | 2993
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2012 | TIMES SQUARE (SEN002160) | PRIMARY STREET RECONSTRUCTION | 305 | HW-0001 HW-0944 HW-1666 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | TIMES SQUARE | TIMES SQUARE | 2022 | 24719 | 70168.42 | 2 | 0 | 515 | 0 | 0 | 0 | 70685.42 | 14879.6 | 0 | 0 | 11 | 200 | 0 | 0 | 15090.6
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2019 | RECONSTRUCTION OF EAST HOUSTON STREET (MED-604) | PRIMARY STREET RECONSTRUCTION | 300 303 | HW-0001M | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF EAST HOUSTON STREET | RECONSTRUCTION OF EAST HOUSTON STREET | 2022 | 3903 | 37823.71 | 81 | 0 | 0 | 0 | 0 | 0 | 37904.71 | 1075.36 | 0 | 0 | 0 | 0 | 0 | 0 | 1075.36
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMP2020 | Reconstruction of Gansevoort Area, Manhattan | PRIMARY STREET RECONSTRUCTION | 300 302 | HW-0001M TF-0002 HW-0944 WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF GANSEVOORT AREA | RECONSTRUCTION OF GANSEVOORT AREA | 2022 | 14700 | 19958.36 | 5199 | 0 | 0 | 0 | 0 | 0 | 25157.36 | 8275 | 2 | 0 | 0 | 0 | 0 | 0 | 8277
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA7E | RECONSTRUCTION OF WORTH ST - HUDSON ST TO EAST BROADWAY | PRIMARY STREET RECONSTRUCTION | 301 | HW-0944 HW-1670 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RECONSTRUCTION OF WORTH ST - HUDSON ST TO EAST BROADWAY | RECONSTRUCTION OF WORTH ST - HUDSON ST TO EAST BROADWAY | 2022 | 7045 | 4553.93 | 0 | 0 | 0 | 0 | 0 | 0 | 4553.93 | 85844.28 | 0 | 2420 | 0 | 20 | 0 | 0 | 88284.28
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCA8B | RECONSTRUCTION OF FULTON ST & ANCILLARY STREETSCAPE, MED-601 | PRIMARY STREET RECONSTRUCTION | 301 | HW-1670 HW-0944 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF FULTON ST & ANCILLARY STREETSCAPE | RECONSTRUCTION OF FULTON ST & ANCILLARY STREETSCAPE | 2022 | 26563 | 5041.42 | 0 | 0 | 0 | 0 | 0 | 0 | 5041.42 | 39151.35 | 0 | 472 | 0 | 0 | 0 | 157 | 39780.35
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB1 | Reconstruction of Nassau St | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M HW-0200 HW-0944 TF-0002 TF-0502 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF NASSAU ST | RECONSTRUCTION OF NASSAU ST | 2022 | 12650 | 675.89 | 3389 | 720 | 0 | 0 | 0 | 0 | 4784.89 | 863.59 | 10975 | 5665 | 0 | 0 | 0 | 0 | 17503.59
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB2 | Reconstruction of Greenwich | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M HW-0944 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF GREENWICH | RECONSTRUCTION OF GREENWICH | 2022 | 21360 | 4264.15 | 1545 | 2341 | 0 | 0 | 0 | 0 | 8150.15 | 17671.78 | 6103 | 1265 | 0 | 0 | 0 | 0 | 25039.78
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB6 | Reconstruction of Vesey St, MED-668 | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M HW-0200 HW-0944 TF-0002 TF-0502 |  | RECONSTRUCTION OF VESEY ST | RECONSTRUCTION OF VESEY ST | 2022 | 23010 | 1725 | 1618 | 1184 | 0 | 0 | 0 | 0 | 4527 | 0 | 7239 | 0 | 0 | 0 | 0 | 0 | 7239
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB7 | Reconstruction of Trinity Pl | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M HW-0200 HW-0944 TF-0002 TF-0502 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RECONSTRUCTION OF TRINITY PL | RECONSTRUCTION OF TRINITY PL | 2022 | 39140 | 826.13 | 250 | 8303 | 0 | 0 | 0 | 0 | 9379.13 | 748.53 | 1000 | 39111 | 0 | 0 | 0 | 0 | 40859.53
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWMWTCB8 | Reconstruction of Broadway Phase 2, MED-674 | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF BROADWAY PHASE 2 | RECONSTRUCTION OF BROADWAY PHASE 2 | 2022 | 67660 | 600 | 218 | 0 | 0 | 0 | 0 | 0 | 818 | 0 | 872 | 0 | 23600 | 835 | 0 | 0 | 25307
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ003M | Montefiore Park and Plaza Reconstruction/Improvement | PRIMARY STREET RECONSTRUCTION | 300 309 | WM-0001 WM-0006 HW-1684 TF-0002 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | MONTEFIORE PARK AND PLAZA RECONSTRUCTION/IMPROVEMENT | MONTEFIORE PARK AND PLAZA RECONSTRUCTION/IMPROVEMENT | 2022 | 6003 | 17919.71 | 3953 | 0 | 0 | 0 | 0 | 0 | 21872.71 | 23.18 | 0 | 0 | 0 | 0 | 0 | 0 | 23.18
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ012M | Bogardus Plaza Clock Tower | PRIMARY STREET RECONSTRUCTION | 300 301 | HW-0200 TF-0502 HW-1684 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BOGARDUS PLAZA CLOCK TOWER | BOGARDUS PLAZA CLOCK TOWER | 2022 | 1835 | 10167.98 | 34 | 15 | 0 | 0 | 0 | 0 | 10216.98 | 322.5 | 0 | 0 | 0 | 0 | 0 | 0 | 322.5
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ015M | Pershing Square East Plaza/Streetscape Reconstruction | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PERSHING SQUARE EAST PLAZA/STREETSCAPE RECONSTRUCTION | PERSHING SQUARE EAST PLAZA/STREETSCAPE RECONSTRUCTION | 2022 | 13020 | 8628.14 | 5107 | 1705 | 0 | 0 | 0 | 0 | 15440.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC1 | Complex Upgrades Ped Ramps - Manhattan | PEDESTRIAN RAMP CONSTRUCTION | 300 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX UPGRADES PED RAMPS - MANHATTAN | COMPLEX UPGRADES PED RAMPS - MANHATTAN | 2022 | 8516 | 1293.43 | 0 | 7815 | 0 | 0 | 0 | 0 | 9108.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19MC2 | Complex Upgrades Ped Ramps - Manhattan | PEDESTRIAN RAMP CONSTRUCTION | 300 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX UPGRADES PED RAMPS - MANHATTAN | COMPLEX UPGRADES PED RAMPS - MANHATTAN | 2022 | 8043 | 1199 | 0 | 7497 | 0 | 0 | 0 | 0 | 8696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20MCL | Non-Standard Upgrades Ped Ramp - Manhattan Landmark | PEDESTRIAN RAMP CONSTRUCTION | 300 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX UPGRADES PED RAMP - MANHATTAN LANDMARK | COMPLEX UPGRADES PED RAMP - MANHATTAN LANDMARK | 2022 | 7257 | 384 | 0 | 505 | 6752 | 0 | 0 | 0 | 7641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2018M | Prior Notice Sidewalks - Manhattan | SIDEWALK RECONSTRUCTION | 300 | HW-0200 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PRIOR NOTICE SIDEWALKS - MANHATTAN | PRIOR NOTICE SIDEWALKS - MANHATTAN | 2022 | 2338 | 3336.32 | 0 | 40 | 0 | 0 | 0 | 0 | 3376.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2019M | Prior Notice Sidewalks- Manhattan | SIDEWALK RECONSTRUCTION | 300 | HW-0200 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PRIOR NOTICE SIDEWALKS- MANHATTAN | 2022 | 2500 | 3455.62 | -417 | 472 | 0 | 0 | 0 | 0 | 3510.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA0996S | 96TH STREET - Exterior Rehabilitation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 308 | LN-D008 LN-0008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | EXTERIOR REHABILITATION | 2022 | 670 | 2253.75 | 329 | 0 | 0 | 0 | 0 | 0 | 2582.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10115 | 115TH STREET - Removal and Replacement of Floors | IMPROVEMENTS TO EXISTING FACILITIES | 310 | LN-0008 LN-M001 LN-D008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REMOVAL AND REPLACEMENT OF FLOORS | 2022 | 334 | 3545.48 | 1262 | 0 | 0 | 0 | 0 | 0 | 4807.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10AGL | AGUILAR - Facade Restoration | IMPROVEMENTS TO EXISTING FACILITIES | 311 | LN-D008 LN-0008 LN-D003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FACADE RESTORATION | 2022 | 525 | 954.05 | 1428 | 0 | 0 | 0 | 0 | 0 | 2382.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10JMB | JEFFERSON MARKET - ADA Accessibility | IMPROVEMENTS TO EXISTING FACILITIES | 302 | LN-0008 LN-0101M LN-D008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | JEFFERSON MARKET - ADA ACCESSIBILITY | 2022 | 1540 | 11785.37 | 754 | 280 | 0 | 0 | 0 | 0 | 12819.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA10RIS | ROOSEVELT ISLAND - NEW BRANCH LIBRARY | EXPANSION AND CONSTRUCTION OF FACILITIES | 308 | LN-0008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ROOSEVELT ISL - SITE SLECTION/DESIGN | 2022 | 5700 | 9538.97 | 10 | 0 | 0 | 0 | 129 | 0 | 9677.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA11BLD | BLOOMINGDALE - Interior Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 307 | LN-0008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | INTERIOR | 2022 | 200 | 3651.11 | 50 | 0 | 0 | 0 | 0 | 0 | 3701.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA12EPH | EPIPHANY - FACADE RESTORATION | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 306 | LN-D008 LN-0008 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FACADE | 2022 | 700 | 394.6 | 0 | 0 | 0 | 0 | 775 | 1383 | 2552.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13GBR | GEORGE BRUCE: Partial Interior/Exterior,/ Roof / Boiler | ESSENTIAL RECONSTRUCTION OF FACILITIES | 309 | LN-D008 LN-0008 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROOF / BOILER | 2022 | 2650 | 362.41 | 268 | 32 | 7734 | 0 | 0 | 0 | 8396.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13HAM | HAMILTON FISH: REHABILITATION | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 303 | LN-0008 PU-0025 LN-D008 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REHABILITATION | 2022 | 2590 | 1954.93 | 59 | 10998 | 224 | 56 | 0 | 0 | 13291.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MLB | MUHLENBERG: Elevator | ESSENTIAL RECONSTRUCTION OF FACILITIES | 304 | LN-D008 LN-0101M LN-0008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ELEVATOR | 2022 | 709 | 307.41 | 802 | 0 | 0 | 0 | 0 | 0 | 1109.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13NAM | NEW AMSTERDAM - HVAC and Cooling Tower | IMPROVEMENTS TO EXISTING FACILITIES | 300 301 | LN-0008 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HVAC AND COOLING TOWER | 2022 | 3024 | 5582.99 | 75 | 0 | 0 | 0 | 0 | 0 | 5657.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA14MBG | HVAC and Related Work | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 | LN-D008 LN-0008 LN-M001 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | HVAC AND RELATED WORK | 2022 | 500 | 630.76 | 2420 | 0 | 0 | 0 | 0 | 0 | 3050.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCAL15CC | Countee Cullen:Exterior Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 | LN-D008 LN-0008 LN-M001 LN-D003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | COUNTEE CULLEN:EXTERIOR RENOVATION | 2022 | 2593 | 1093.9 | 6404 | 554 | 0 | 0 | 0 | 0 | 8051.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA08MHV | MANHATTAN (Northern) - HVAC @ Four Branch Libraries | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 308 309 311 312 | LN-0101M LN-0008 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | HVAC @ FOUR BRANCHS - MANHATTAN 125TH STREET BRANCH 96TH STREET BRANCH FORT WASHINGTON BRANCH GEORGE BRUCE BRANCH | 2022 | 4460 | 5995.62 | 0 | 1464 | 0 | 0 | 0 | 0 | 7459.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13HGR | HAMILTON GRANGE:Exterior Rehabiliation/ Window | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 309 | LN-0008 LN-D008 LN-0101X | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | EXTERIOR REHABILIATION/ WINDOW REPLACEMENT | 2022 | 885 | 852.87 | 566 | 4691 | 0 | 0 | 0 | 0 | 6109.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEM12MLB | MUHLENBERG - Sidewalk Vault | ESSENTIAL RECONSTRUCTION OF FACILITIES | 304 | LN-0008 LN-D008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | VAULT | 2022 | 856 | 319.62 | 839 | 0 | 0 | 0 | 0 | 0 | 1158.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | LNMNA08LS | MANHATTAN - Life Safety Projects @ 17 Branch Libraries | ESSENTIAL RECONSTRUCTION OF FACILITIES | 300 | LN-D003 LN-0008 LN-D008 LN-0101M LN-0101X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | LIFE SAFETY PROJECTS @ 16 BRANCH LIBRARIES - MANHATTAN | 2022 | 3719 | 5455.15 | 11 | 643 | 0 | 0 | 0 | 0 | 6109.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-594 | WM RPLMT IN E 46 ST & E 47 ST B/T MADISON AV & LEXINGTON AV | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 305 | WM-0001 EP-0007 TF-0502 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WM RPLMT IN E 46 ST & E 47 ST B/T MADISON AV & LEXINGTON AV | 2022 | 772 | 1163.05 | 0 | 0 | 27824 | 0 | 0 | 0 | 28987.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-597 | TRUNK WM IN EAST 31 STREET FRM 5TH AV TO 2ND AV | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 305 306 | WM-0006 WM-0001 SE-0002M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TRUNK WM IN EAST 31 STREET FRM 5TH AV TO 2ND AV | 2022 | 6454 | 174.34 | 0 | 0 | 0 | 0 | 0 | 14944 | 15118.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-598B | TRUNK WM IN W 30 ST - 9 AV TO 10 AV (SHAFT 26B) - PHASE B | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 304 305 | WM-0006 WM-0001 SE-0002M TF-0002 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | TRUNK WM IN W 30 ST - 9 AV TO 10 AV (SHAFT 26B) - PHASE B | TRUNK WM IN W 30 ST - 9 AV TO 10 AV (SHAFT 26B) - PHASE B | 2022 | 64919 | 57790.81 | 3748 | 126 | 0 | 0 | 0 | 0 | 61664.81 | 772.04 | 0 | 0 | 0 | 0 | 0 | 0 | 772.04
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-604 | TRUNK & DIS WM IN EAST HOUSTONS ST (HWMP2019) | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 303 | WM-0006 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | TRUNK & DIS WM IN EAST HOUSTONS ST B/T BOWERY & FDR DR | 2022 | 11357 | 33359.49 | 503 | 0 | 0 | 0 | 0 | 0 | 33862.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-607 | TRUNK MAIN CONN TO SHAFT 32B IN 2ND AVE. INTER. OF E. 35ST. | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 306 | WM-0006 WM-0001 SE-0002M TF-0002 TF-0502 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TRUNK MAIN CONN TO SHAFT 32B IN 2ND AVE. INTER. OF E. 35ST. | 2022 | 13913 | 47909.16 | 544 | 99 | 0 | 2800 | 0 | 0 | 51352.16 | 18.9 | 0 | 0 | 0 | 0 | 0 | 0 | 18.9
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-609 | TRUNK MAIN IN W60 ST, W.E. AVE TO COLUMBUS AV | TRUNK AND DISTRIBUTION MAIN EXTENSION | 307 | WM-0006 EP-0007 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | TRUNK MAIN IN W60 ST, WEST END AVE TO COLUMBUS AV, TO CONNECT TO SHAFT 24B | 2022 | 9031 | 100548.95 | 1139 | 0 | 0 | 0 | 0 | 0 | 101687.95 | 2804.04 | 0 | 0 | 0 | 0 | 0 | 0 | 2804.04
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-610 | TRUNK MAIN CONNECTION TO SHAFT 27B | TRUNK AND DISTRIBUTION MAIN EXTENSION | 303 | HW-D102 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | TRUNK MAIN CONNECTION TO SHAFT 27B IN HUDSON ST BETW GANSEVOORT ST & W 13 ST | 2022 | 14250 | 30546.66 | 0 | 55 | 0 | 0 | 0 | 0 | 30601.66 | 937.1 | 0 | 0 | 0 | 0 | 0 | 0 | 937.1
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-611 | TRUNK WM REPLACMT IN TRANSVERSE RD 3 | AUGMENTATION OF WATER SUPPLY SYSTEMS | 308 | WM-0006 WM-0001 |  |  | TRUNK WM REPLACMT IN TRANSVERSE RD 3, B/T 85 ST & 86 ST | 2022 | 4158 | 0 | 0 | 0 | 0 | 4158 | 0 | 0 | 4158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-619 | Trunk Main replacement, b'way b/t w 93 & 97 st, Manh | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 307 | WM-0006 WM-0001 SE-0002M | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RUNK MAIN REPLACEMENT, B'WAY B/T W 93 & 97 ST, MANH | 2022 | 7751 | 1080.5 | 0 | 20551 | 0 | 0 | 0 | 0 | 21631.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-645 | Distribution water main Installation, Manhattan | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 300 | WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | DISTRIBUTION WATER MAIN INSTALLATION, MANHATTAN | 2022 | 4567 | 10958.6 | 1023 | 3652 | 1900 | 0 | 0 | 0 | 17533.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-667 | Replacement of Water main in Delancey Street (HWM2025) | AUGMENTATION OF WATER SUPPLY SYSTEMS | 300 | SE-0002M WM-0001 WM-0006 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | REPLACEMENT OF WATER MAIN IN DELANCEY STREET BETWEEN BOWERY AND CLINTON STREET, BORIUGH OF MANHATTAN | 2022 | 11122 | 0 | 0 | 11284 | 0 | 0 | 0 | 0 | 11284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-668 | Installation of Distri WM & appurtenances Vesey st, HWMWTCB6 | AUGMENTATION OF WATER SUPPLY SYSTEMS | 300 | WM-0001 EP-0007 |  |  | INSTALLATION OF DISTRIBUTION WATER MAIN AND APPURTENANCES IN VESEY STREET BETWEEN CHURCH STREET AND BROADWAY.THIS PROJECT IS TO BE BUILT IN CONJUNCTION WITH DOT PROJECT HWMWTCB6.NO SEWER WORK IS REQUIRED BASED ON DDC TV REPORT DATED JULY 31,2018. | 2022 | 917 | 0 | 1119 | 0 | 0 | 0 | 0 | 0 | 1119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED669 | Dist. WM work in 7th Ave between W 14th & W 34th Street, MN | AUGMENTATION OF WATER SUPPLY SYSTEMS | 304 305 | WM-0001 |  |  | NEW WATER MAIN WORK IN 7TH AVENUE BETWEEN 14TH STREET & 34TH STREET, BOROUGH OF MANHATTAN. | 2022 | 42638 | 3674 | 0 | 0 | 59694 | 0 | 0 | 0 | 63368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-670 | Replacement of distriibution WM in 43rd Street, HWMME43ST | AUGMENTATION OF WATER SUPPLY SYSTEMS | 300 | WM-0001 SE-0002M | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | REPLACEMENT OF DISTRIBUTION WATER MAINS IN E 43RD STREET BETWEEN LEXINGTON AVENUE AND 3RD AVENUE | 2022 | 2486 | 50 | 0 | 0 | 2933 | 0 | 0 | 0 | 2983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED673 | WM Rplcmt in 79 ST from Henry Hudson Pkwy to FDR, MN | AUGMENTATION OF WATER SUPPLY SYSTEMS | 307 308 | SE-0002M WM-0001 WM-0006 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | WATER MAIN REPLACEMENT IN 79TH STREET FROM HENRY HUDSON PARKWAY TO FDR, MN. THIS PROJECT IS DONE IN CONJUNCTION WITH NYC DOT PROJECT HWM100SNC. | 2022 | 36816 | 0 | 0 | 0 | 35525 | 0 | 0 | 0 | 35525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED-674 | Water Main and trunk main installin Broadway MH,HWMWTCB8 | AUGMENTATION OF WATER SUPPLY SYSTEMS | 301 | SE-0002M WM-0001 WM-0006 |  |  | WATER MAIN AND TRUNK MAIN INSTALLATION IN BROADWAY FROM WORTH STREET TO VESEY STREET, BOROUGH OF MANHATTAN | 2022 | 14303 | 0 | 0 | 0 | 13800 | 0 | 0 | 0 | 13800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED678 | WM Rplmt in Lexington Ave btwn E 45 & E 49 St, MN | AUGMENTATION OF WATER SUPPLY SYSTEMS | 305 306 | WM-0001 |  |  | WATER MAIN REPLACEMENT IN LEXINGTON AVE BETWEEN EAST 45TH STREET AND EAST 49TH STREET, MANHATTAN. THIS PROJECT WILL BE COMPLETED IN CONJUNCTIUON WITH NYCDOT'S PROJECT HWMMLEXAV AND THEIR VISION ZERO IMPROVEMENTS TO THE AREA. | 2022 | 3944 | 0 | 1556 | 5880 | 1571 | 0 | 0 | 0 | 9007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MED679 | Dist. WM & SE Rplcmt work in West 42nd St btwn 7 & 8 Ave MN | AUGMENTATION OF WATER SUPPLY SYSTEMS | 304 | SE-0002M WM-0001 WM-0006 |  |  | DISTRIBUTION WATER MAIN AND COMBINED SEWER REPLACEMENT WORK IN WEST 42ND STREET. BETWEEN 7TH 8TH AVENUE. THIS PROJECT WILL BE DONE IN CONJUNCTION WITH DOT MAYORAL PRIORITY PROJECT HWM42PSM. | 2022 | 32922 | 0 | 0 | 0 | 0 | 0 | 18470 | 0 | 18470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | MEDA-002 | Accelerated Distribution WM replcmnt & sewer rebhab - MAN | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 300 | WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ACCELERATED DISTRIBUTION WATER MAIN REPLCMNT & SEWER REBHAB/REPLCMNT,MANHATTAN | 2022 | 17900 | 22221.78 | 0 | 0 | 0 | 11392 | 0 | 0 | 33613.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-303ERPK | East River Park | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 300 | RE-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | EAST RIVER PARK | EAST RIVER PARK | 2022 | 9274 | 1186.82 | 947 | 3648 | 1544 | 0 | 0 | 0 | 7325.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-30420SP | West 20th St. Park Demolition & Abatement | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 300 | ED-0075 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 20TH STREET PARK CONSTRUCTION, MANHATTAN | 20TH STREET PARK CONSTRUCTION | 2022 | 1000 | 2574.32 | 0 | 0 | 0 | 299 | 0 | 0 | 2873.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | P-3RANDAL | Randall's Island Infrastructure, Roadways, Drainage, & CS | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 311 | P-0944 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RANDALL'S ISLAND | CONCESSION | 2022 | 16700 | 2398.61 | 0 | 0 | 0 | 15171 | 0 | 0 | 17569.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHJ | One Police Plaza | POLICE FACILITIES | 300 301 | PO-0079 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | ONE POLICE PLAZA AND POLICE ACADEMY | FACADE REPAIR FOR ONE POLICE PLAZA AND POLICE ACADEMY AT 235 E 29TH STREET MANHATTAN | 2022 | 5063 | 2569.13 | 89 | 0 | 0 | 0 | 0 | 0 | 2658.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHQ | ONE POLICE PLAZA PAVING AND LANDSCAPING | POLICE FACILITIES | 300 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | ONE POLICE PLAZA | ONE POLICE PLAZA | 2022 | 816 | 2621.75 | 230 | 0 | 0 | 0 | 0 | 0 | 2851.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAJU | 26TH PRECINCT ROOF, WINDOWS & FACADE | POLICE FACILITIES | 300 | PO-0079 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ROOF, WINDOWS, FACADE | 2022 | 2903 | 1160.83 | 6415 | 0 | 0 | 0 | 0 | 0 | 7575.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV234CSV1 | CSV - Clemente Soto Velez - Interior Code Compliance | ESSENTIAL RECONSTRUCTION OF FACILITIES | 303 | PV-0234 PV-D234 PV-M467 PV-0467 PW-0077 PW-C077 PV-M234 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 107 SUFFOLK STREET, NY NY 10002 | CSV - CLEMENTE SOTO VELEZ - INTERIOR CODE COMPLIANCE - ADA ACCESS, RESTROOMS, EGRESS, ETC. | 2022 | 1500 | 303.02 | 0 | 0 | 10290 | 0 | 0 | 0 | 10593.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV241EXTR | MCNY - Exterior Facade Rehabilitation | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-D241 PV-0241 PV-M241 PV-0467 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 1220 FIFTH AVENUE, MANHATTAN, NY | FACADE RENOVATION AND REHABILITATION. | 2022 | 2296 | 707.97 | 90 | 3857 | 0 | 0 | 0 | 0 | 4654.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV467-122 | 122C - 122 Community Center Bldg Reconstruction | ESSENTIAL RECONSTRUCTION OF FACILITIES | 303 | PV-0467 PV-0788 PV-M788 PV-M467 PV-D467 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 150 1ST AVENUE, NEW YORK NY | PS 122 - BLDG RECONSTRUCTION | 2022 | 16812 | 34333.44 | 187 | 624 | 4 | 0 | 0 | 0 | 35148.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV503ELEV | CH- Carnegie Hall Elevators | ESSENTIAL RECONSTRUCTION OF FACILITIES | 305 | PV-M503 PV-0503 PV-D503 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CH- CARNEGIE HALL ELEVATORS AND SIDEWALK. FY19 EXEC SECTION 211 ADD | 2022 | 2760 | 0 | 0 | 0 | 2735 | 0 | 0 | 0 | 2735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PV788-FAC | 122C - 122 CC Facade Reconstruction | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-0788 PV-D788 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCTION | 2022 | 5650 | 0 | 538 | 0 | 4484 | 0 | 0 | 0 | 5022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW195SW2 | 80 CENTRE ST. - SIDEWALK REHABILITATION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0195 PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 80 CENTRE ST. - SIDEWALK REHABILITATION | 2022 | 2240 | 955.08 | 0 | 5343 | 0 | 0 | 0 | 0 | 6298.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW29380FC | 80 CENTRE ST.- FIRE ALARMS/SPRINKLERS | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 301 | PW-0293 |  |  | 80 CENTRE ST.- FIRE ALARMS/SPRINKLERS | 2022 | 44728 | 2413.72 | 100 | 4301 | 36654 | 0 | 0 | 0 | 43468.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW316BWY2 | 280 BROADWAY - EXTERIOR | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 301 | PW-0077 PW-0316 |  |  | EXTERIOR WORK AT 280 BROADWAY - | 2022 | 24398 | 22861.5 | 246 | 56 | 0 | 0 | 0 | 0 | 23163.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW3171C | 1 CENTRE STREET- FACADE REHAB | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 301 | PW-0317 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 1 CENTRE STREET - FACADE REPAIRS | 2022 | 8334 | 9 | 0 | 0 | 0 | 0 | 24811 | 0 | 24820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW3172L | 2 LAFAYETTE STREET - FACADE REPAIRS | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 301 | PW-0317 PW-0080 |  |  | 2 LAFAYETTE STREET - FACADE REPAIRS | 2022 | 4850 | 34.84 | 1016 | 70 | 3345 | 0 | 0 | 0 | 4465.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW317WOR | 125 WORTH STREET - FACADE REPAIRS | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 301 | PW-0317 PW-0266 |  |  | 125 WORTH STREET - FACADE REAPIRS | 2022 | 4050 | 0 | 0 | 1225 | 0 | 6444 | 0 | 0 | 7669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357ELEV | 253 BROADWAY- ELEVATOR MODERNIZATION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0357 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 253 BROADWAY ELEVATOR MODERNIZATION | 2022 | 2653 | 7892.52 | 0 | 2261 | 0 | 0 | 0 | 0 | 10153.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW357FIRE | 253 BROADWAY- FIRE ALARM REPLACEMENT | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 301 | PW-0293 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 253 BROADWAY FIRE ALARM REPLACEMENT | 2022 | 2743 | 8302.11 | 35103 | 818 | 0 | 0 | 0 | 0 | 44223.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77102S3 | CITY HALL STEPS RECONSTRUCTION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | STEPS | 2022 | 3284 | 549.47 | 8244 | 176 | 0 | 0 | 0 | 0 | 8969.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW7722R | 22 READE STREET EXTERIOR | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 301 | PW-0077 |  |  | THE EXTERIOR RECONSTRUCTION OF THE CITY PLANNING BUILDING | 2022 | 21175 | 274 | 0 | 3196 | 27880 | 0 | 0 | 0 | 31350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77GLDA2 | 100 GOLD ST.- MIS HVAC UPGRADES | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 100 GOLD ST.- MIS HVAC UPGRADES | 2022 | 2535 | 3912.87 | 0 | 288 | 0 | 314 | 0 | 0 | 4514.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77LYA | 253 BROADWAY- LPC MOVE TO 2nd, 11th, 12th, 13th FLS | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 253 BROADWAY- LPC MOVE FROM 1 CENTRE ST, 9TH FLOOR | 2022 | 23714 | 51575.47 | 11431 | 3737 | 0 | 0 | 0 | 0 | 66743.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PW80DYCD2 | 2 LAFAYETTE STREET- DYCD RELOCATION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0293 PW-0077 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | DYCD RELOCATION TO 2 LAFAYETTE STREET. | 2022 | 34658 | 65109.2 | 5950 | 0 | 0 | 0 | 0 | 0 | 71059.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD005NEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN | RENOVATION OF OTHER CITY-OWNED FACILITIES | 304 | PW-D005 PW-M077 ED-D075 | PROJECT DELAYED PENDING NON-CITY GRANT APPROVAL |  | NO SCOPE FROM COUNCIL STAFF | 2022 | 870 | 1861.93 | 0 | 0 | 0 | 0 | 259 | 2000 | 4120.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S195-227S | Spring St Salt Enclosure | GARAGES AND FACILITIES | 301 | S-0195 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCTION OF A SALT ENCLOSURE | 2022 | 10375 | 21948.78 | 0 | 0 | 176 | 0 | 0 | 0 | 22124.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-401A | EAST 91st ST MARINE TRANSFER STATION | SOLID WASTE MANAGEMENT | 300 308 | S-0216 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | E 91ST ST MTS | E 91ST ST MTS | 2022 | 131355 | 245996.92 | 814 | 0 | 0 | 0 | 0 | 0 | 246810.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-404A | GANSEVOORT MARINE TRANSFER STATION | SOLID WASTE MANAGEMENT | 300 302 | S-0216 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | GANSEVOORT MTS SITE | GANSEVOORT MTS | 2022 | 89458 | 36460.12 | 0 | 0 | 0 | 0 | 0 | 52872 | 89332.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S216-415A | WEST 59th STREET MTS | SOLID WASTE MANAGEMENT | 300 304 307 | S-0216 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | WEST 59TH ST MTS SITE | WEST 59TH ST MTS | 2022 | 60937 | 99168.31 | 2331 | 2054 | 0 | 0 | 0 | 0 | 103553.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | S219-233A | CONSTRUCTION MANHATTAN 1/2/5 GARAGE | GARAGES AND FACILITIES | 301 302 305 | S-0219 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BLOCK 596 LOT 50 MANHATTAN | CONSTRUCTION OF A NEW SANITATION GARAGE TO SERVICE MANHATTAN COMMUNITY DISTRICTS 1, 2, AND 5. | 2022 | 147907 | 213545.39 | 0 | 0 | 0 | 0 | 1076 | 0 | 214621.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBHFW | Sandy: Bellevue Flood Wall | NEW FACILITIES |  | HO-0214 |  | SERVICE ROAD PARALLEL TO FDR BETWEEN 25TH AND 30TH STREETS | BELLEVUE FLOOD WALL TO BUILT ALONG THE SERVICE ROAD PARALLEL TO THE FDR FROM 25TH TO 30TH STREETS. | 2022 | 90000 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 81000 | 0 | 0 | 0 | 81000
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW06 | Reconstruction of Vestry Street- Hurricane Sandy | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M WM-0001 SE-0002M TF-0002 HW-0200 TF-0502 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF VESTRY STREET- HURRICANE SANDY | RECONSTRUCTION OF VESTRY STREET- HURRICANE SANDY | 2022 | 2232 | 3334.09 | 1113 | 0 | 0 | 0 | 0 | 0 | 4447.09 | 2319.33 | 0 | 877 | 0 | 0 | 0 | 0 | 3196.33
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW08 | Reconstruction of Front Street-Hurricane Sandy | PRIMARY STREET RECONSTRUCTION | 300 | HW-0001M HW-0944 SE-0002M | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF FRONT STREET-HURRICANE SANDY | RECONSTRUCTION OF FRONT STREET-HURRICANE SANDY | 2022 | 4888 | 4992.63 | 3597 | 0 | 0 | 0 | 0 | 0 | 8589.63 | 18098.97 | 2018 | 0 | 0 | 0 | 0 | 0 | 20116.97
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDSLIP | 100 OLD SLIP RESTORATION & SYSTEMS REPLACEMENT | POLICE FACILITIES | 300 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 100 OLD SLIP RESTORATION | 2022 | 19124 | 680.63 | 0 | 0 | 0 | 0 | 0 | 0 | 680.63 | 2075.73 | 0 | 78 | 2238 | 0 | 0 | 0 | 4391.73
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002152 | COMBINE SEWERS IN WORTH ST | PROGRAMMATIC REPLACEMENT AND RECONSTRUCTION | 301 302 | WM-0006 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | REPLACEMENT OF COMBINE SEWER IN WOTH STREET BETWEEN CENTRE ST AND MULBERRY ST, ETC. | 2022 | 8443 | 30665.73 | 0 | 629 | 0 | 0 | 0 | 0 | 31294.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002153 | Water Main in Water St. (w/HWMWTCA7D) | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 301 | WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WATER MAIN AND SEWER WORK IN WATER ST. BETW BEEKMAN ST. AND DOVER ST. | 2022 | 565 | 1367.09 | 627 | 0 | 0 | 0 | 0 | 0 | 1994.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002156 | WATERMAIN & SEWER WORK IN WARREN ST- WEST ST & BROADWAY ETC | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 301 | SE-0002M WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WATERMAIN & SEWER WORK IN WARREN ST- WEST ST & BROADWAY ETC (HWMWTCA7F) | 2022 | 1528 | 7735.12 | 182 | 0 | 0 | 0 | 0 | 0 | 7917.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002157 | Replacement of Combined Sewer in E. 26th Street, Manhattan | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 306 312 | WM-0006 SE-0002M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REPLMT OF COMB SEWER IN E. 26 ST B/T 1ST AV & FDR | 2022 | 2816 | 20724.22 | 807 | 0 | 0 | 0 | 0 | 0 | 21531.22 | 21.37 | 0 | 0 | 0 | 0 | 0 | 0 | 21.37
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002169 | RECON OF COMBINED SEWER & WM IN YORK AVE | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 308 | SE-0002M WM-0001 HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECON OF COMB SWR & WM IN YORK AV B/T 61 & 63 STREET | 2022 | 1220 | 18036.87 | 1141 | 0 | 0 | 0 | 1714 | 0 | 20891.87 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 36
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002178 | Replacement & guniting comb SE in W. Broadway | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 301 | SE-0002M TF-0502 EP-0007 WM-0001 SE-0944 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COMBINED SEWER REPLACEMENT AND GUNITING IN WEST BROADWAY BETWEEN THOMAS & LEONARD STREET | 2022 | 1069 | 980 | 4801 | 889 | 262 | 0 | 0 | 0 | 6932 | 0 | 1222 | 0 | 0 | 0 | 0 | 0 | 1222
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | SEN002182 | Rplmt SE on Trinity Pl betw Thames & Rector Str MN HWMWTCB7 | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 301 | SE-0002M |  |  | REPLACEMENT OF COLLAPSED PORTION OF COMBINED SEWER ON TRINITY PLACE BETWEEN THAMES STREET AND RECTOR STREET, MANHATTAN | 2022 | 1288 | 0 | 1652 | 566 | 0 | 0 | 0 | 0 | 2218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 850 | DEPT OF DESIGN & CONSTRUCTION | TAVREH | Tavern on the Green Structure | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION |  | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RENOVATION OF TAVERN ON THE GREEN STRUCTUE - LANDMARK BUILDING | 2022 | 10894 | 20251.34 | 0 | 0 | 150 | 0 | 0 | 0 | 20401.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | 1250-RELO | 1250 Broadway DEP Relocation | FACILITY PURCHASES AND RECONSTRUCTION | 300 | EP-0006 |  |  | DEPARTMENT OF ENVIRONMENTAL PROTECTION IS RELOCATING FROM 1250 BROADWAY, NY 10001 DUE TO THE CURRENT LEASE EXPIRATION | 2022 | 1965 | 0 | 1965 | 0 | 0 | 0 | 0 | 0 | 1965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | 70MULB1 | 70 MULBERRY - DEMOLITION | REHABILITATION OF NON-WATERFRONT PROPERTIES | 301 | RE-0025 |  |  | DEMOLITION | 2022 | 6470 | 5558.55 | 911 | 0 | 0 | 0 | 0 | 0 | 6469.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDCA202 | DCLA - AMNH Lighting Upgrade and Controls | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 301 | PU-0025 |  |  | DCLA - AMNH LIGHTING UPGRADE AND CONTROLS | 2022 | 1435 | 0 | 0 | 1435 | 0 | 0 | 0 | 0 | 1435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE701 | DOE - STEAM SYSTEM OPTIMIZATION | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 |  |  | DOE - STEAM SYSTEM OPTIMIZATION | 2022 | 5661 | 0 | 5689 | 0 | 0 | 0 | 0 | 0 | 5689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT211 | FIT - Replacement of Air Handling Units with higher efficien | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 301 | PU-0025 |  |  | REPLACEMENT OF AIR HANDLING UNITS WITH HIGHER EFFICIENCY AHUS | 2022 | 5332 | 0 | 1199 | 0 | 2952 | 0 | 0 | 0 | 4151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEFIT212 | FIT - Replace Air Handling Unit with high efficiency | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 301 | PU-0025 |  |  | REPLACEMENT OF AC-4A AIR HANDLING UNIT WITH HIGHER EFFICIENCY AHU | 2022 | 918 | 0 | 0 | 918 | 0 | 0 | 0 | 0 | 918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | AGHVACRM | 2 Lafayette 9th floor DFTA IT room HVAC upgrade | DEPARTMENT FOR THE AGING BUILDING RECONSTRUCTION | 301 | AG-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 2 LAFAYETTE 9TH FLOOR DFTA IT ROOM HVAC UPGRADE | 2022 | 607 | 594.31 | 0 | 0 | 75 | 0 | 0 | 0 | 669.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264MN60 | DASNY - 60 CENTRE ST RENOVATION | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 300 | CO-0264 |  |  | DASNY - 60 CENTRE ST RENOVATION | 2022 | 390404 | 0 | 0 | 0 | 0 | 0 | 41815 | 348589 | 390404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283CTSP | 100 CENTRE ST- COOLING TOWERS TO REPLACE SPRAY PONDS | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 301 | CO-0283 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 100 CENTRE - TOWERING SYSTEM TO REPLACE SPRAY PONDS | 2022 | 9716 | 12875.94 | 30 | 726 | 0 | 0 | 0 | 0 | 13631.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283FIRE | 100 CENTRE ST.- FIRE SAFETY | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 301 | CO-0283 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 100 CENTRE ST MANHATTAN | MAKE FIRE SAFETY SYSTEM CODE COMPLIANT | 2022 | 7730 | 8963.46 | 137 | 150 | 0 | 1350 | 0 | 0 | 10600.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283LL11 | 100 CENTRE ST - FACADE RECONSTRUCTION | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 301 | CO-0283 |  |  | 100 CENTRE ST.- FAÝADE REPAIRS LL 11 | 2022 | 5578 | 0 | 0 | 0 | 0 | 5578 | 0 | 0 | 5578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283MP1 | 100 CENTRE ST- RETUBE BOILER 3 AND 4 | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 301 | CO-0283 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 100 CENTRE ST- HVAC UPGRADES | 2022 | 1660 | 1657.26 | 848 | 0 | 0 | 0 | 0 | 0 | 2505.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO283RF | 100 Centre St Roof Rehab | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 301 | CO-0283 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SQ/IA | 2022 | 6867 | 0 | 763 | 0 | 6104 | 0 | 0 | 0 | 6867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO304HEA2 | 60 CENTRE STREET- SPRINKLERS | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 301 | CO-0304 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 60 CENTRE STREET - HEATING UPGRADE - SPRINKLERS | 2022 | 20210 | 0 | 0 | 0 | 0 | 0 | 0 | 18065 | 18065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO304HEA5 | 60 CENTRE ST.- HEATING DISTRIBUTION SYSTEM | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 301 | CO-0304 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 60 CENTRE ST.- HEATING DISTRIBUTION SYSTEM | 2022 | 31293 | 0 | 0 | 0 | 0 | 0 | 0 | 28362 | 28362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO305REHB | 314 W. 54TH ST.- MIDTOWN COMM COURT EXPANSION | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 304 | CO-0305 CO-0264 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 314 W. 54TH ST. NY, NY 10019 | ROOF REPLACEMENT; INSTALLATION OF FIRE SAFETY SYSTEM; ELECTRICAL & HVAC UPGRADE; FACADE RECONSTRUCTION; WINDOW & SKYLIGHT REPLACEMENT; ELEVATOR MODERNIZATION | 2022 | 17830 | 32042.71 | 0 | 723 | 0 | 0 | 0 | 0 | 32765.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO306MHCB | 170 E. 121 ST. - HARLEM COURT BOILER | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 311 | CO-0306 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BOILER REPLACEMENT | 2022 | 770 | 0 | 0 | 0 | 885 | 0 | 0 | 0 | 885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO81ADA1 | 31 CHAMBERS ST - ADA LIFT | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 301 | CO-0081 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | IA/SQ | 2022 | 347 | 0 | 90 | 257 | 0 | 0 | 0 | 0 | 347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E19-0009 | NYPD - 20th Precinct | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NYPD - 20TH PRECINCT | 2022 | 1378 | 1551.21 | 100 | 79 | 0 | 0 | 0 | 0 | 1730.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0001 | NYPD Comprehensice Lighting Upgrade | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 301 | PU-0025 |  |  | COMPREHENSICE LIGHTING UPGRADE AT THE NYPD 24TH PRECINCT | 2022 | 291 | 0 | 291 | 0 | 0 | 0 | 0 | 0 | 291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0003 | DSNY - W57th Street Garage Comprehensive Energy Upgrade | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 301 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 57TH STREET GARAGE COMPREHENSIVE ENERGY UPGRADE | 2022 | 50323 | 0 | 1125 | 20000 | 20000 | 9200 | 0 | 0 | 50325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0007 | OCME Center for Forensic Sciences | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 301 | PU-0025 |  |  | OCME CENTER FOR FORENSIC SCIENCES | 2022 | 13963 | 0 | 0 | 2611 | 0 | 11352 | 0 | 0 | 13963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0019 | DCLA - Lincoln Center Campus: Plaza/Public Spaces/Garages | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DCLA - LINCOLN CENTER CAMPUS: PLAZA/PUBLIC SPACES/GARAGES | 2022 | 900 | 2324.44 | 0 | 175 | 0 | 0 | 0 | 0 | 2499.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0026 | NYPL - The Library for the Performing Arts | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NYPL - THE LIBRARY FOR THE PERFORMING ARTS | 2022 | 900 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0034 | DPR-Central Park Campus: Wollman Rink | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DPR-CENTRAL PARK CAMPUS: WOLLMAN RINK | 2022 | 250 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0046 | CUNY - BMCC Campus: Chambers St. Building (Main Campus) | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CUNY - BMCC CAMPUS: CHAMBERS ST. BUILDING (MAIN CAMPUS) | 2022 | 900 | 0 | 0 | 3473 | 0 | 0 | 0 | 0 | 3473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0054 | CIG - David H. Koch Theater | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DAVID H. KOCH THEATER | 2022 | 1000 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0055 | DCAS - Midtown Community Court | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MIDTOWN COMMUNITY COURT | 2022 | 300 | 0 | 219 | 29 | 0 | 0 | 0 | 0 | 248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0056 | NYPD - 18th Precinct (Midtown North) | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 18TH PRECINCT (MIDTOWN NORTH) | 2022 | 300 | 0 | 217 | 0 | 0 | 0 | 0 | 0 | 217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0065 | NYPD - 10th Precinct | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 10TH PRECINCT | 2022 | 300 | 0 | 115 | 0 | 0 | 0 | 0 | 0 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0066 | NYPD -Engine Co. 39, Ladder Co. 16 and 19th Precinct Campus | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 19TH PRECINCT | 2022 | 300 | 0 | 0 | 244 | 0 | 0 | 0 | 0 | 244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0067 | NYPD - 30th Precinct | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 30TH PRECINCT | 2022 | 300 | 0 | 186 | 0 | 0 | 0 | 0 | 0 | 186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0068 | NYPD - 32nd Precinct | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 32ND PRECINCT | 2022 | 300 | 0 | 0 | 169 | 0 | 0 | 0 | 0 | 169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0078 | DHS - MANHATTAN BOWERY SHELTER | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | IA/SQ | 2022 | 500 | 0 | 0 | 313 | 0 | 0 | 0 | 0 | 313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0081 | DHS - FORT WASHINGTON ARMORY - SHELTER (PROJECT RENEWAL) | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | IA/SQ | 2022 | 500 | 0 | 1180 | 0 | 0 | 0 | 0 | 0 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0093 | CIG - METROPOLITAN MUSEUM OF ART - OFFICE SPACES | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | IA/SQ | 2022 | 2500 | 0 | 0 | 6345 | 0 | 0 | 0 | 0 | 6345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0094 | NYPD - 13TH PRECINCT (OLD ACADEMY) | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 301 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | IA/SQ | 2022 | 950 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | HR258AVEC | 400 8th Ave Construction | SOCIAL SERVICES BUILDINGS |  | HR-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2022 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 5603 | 5603 | 0 | 0 | 0 | 0 | 0 | 0 | 2897 | 2897
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79-375P | NYPD - 375 Pearl Street Renovation | POLICE FACILITIES | 300 | PO-0079 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | COST ESTIMATE | 2022 | 11356 | 14059.06 | 836 | 0 | 0 | 0 | 0 | 0 | 14895.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79BOMB | nypd- relocate bomb squad to 241 w 26th street | POLICE FACILITIES | 300 305 | PO-0079 |  |  | NYPD- RELOCATE BOMB SQUAD TO 241 W 26TH STREET | 2022 | 15217 | 0 | 14191 | 1026 | 0 | 0 | 0 | 0 | 15217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79SRG1 | NYPD - RELOCATE STRATEGIC RESPONSE GROUP TO 521-533 W 57 ST | POLICE FACILITIES | 301 | PO-0079 |  |  | SQ/IA | 2022 | 7359 | 0 | 7359 | 0 | 0 | 0 | 0 | 0 | 7359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19315A | 1 CENTRE ST.- 15 FL CITYSTORE AND CITY GRAPHICS | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0193 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TEST | 2022 | 1685 | 832.33 | 0 | 50 | 0 | 0 | 0 | 0 | 882.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW19325A | 1 CENTRE ST.- 25TH FL BUILDOUT | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0193 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DQ FT | 2022 | 5845 | 1159.63 | 514 | 0 | 17610 | 1165 | 0 | 0 | 20448.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193DCPS | 1 CENTRE ST. - CONSOLIDATION AND RESTACKING | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0193 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 1 CENTRE ST. - DCAS CITYWIDE TRAINING CENTER MOVE FROM 2 WASHINGTON | 2022 | 14224 | 6888.78 | 50 | 0 | 0 | 0 | 0 | 0 | 6938.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193ELV | 1 CENTRE ST - ELEVATOR MODERNIZATION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0193 |  |  | IA/SQ | 2022 | 77609 | 0 | 0 | 5504 | 0 | 0 | 66049 | 0 | 71553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193EV13 | 1 CENTRE ST - 13TH FL ELEVATOR REPAIR GROUP RELOCATION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0193 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | IA/SQ | 2022 | 2475 | 0 | 2001 | 0 | 0 | 0 | 0 | 0 | 2001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW193FANS | 1 CENTRE ST. - REPLACEMENT OF LOBBY FANS | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DEMOLITION OF FANS AND ASSOCIATED EQUIPMENT AND ACCESSORIES; FIELD ERECTION OF FANS, COMPLETE WITH STEAM HEATING COILS, DUCTWORK, PIPING, INSULATION, CONTROL, AND ASSOCIATED ELECTRICAL AND GC WORK. | 2022 | 1575 | 154.62 | 0 | 0 | 0 | 0 | 0 | 1291 | 1445.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195ADA | 80 CENTRE ST - ADA LIFT | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0282 |  |  | IA/SQ | 2022 | 746 | 65 | 677 | 3204 | 0 | 0 | 0 | 0 | 3946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW195RF | 80 CENTRE ST.- ROOF REPLACEMENT | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0195 |  |  | SQ FT | 2022 | 4925 | 0 | 0 | 482 | 0 | 0 | 4200 | 0 | 4682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266FE | 125 WORTH ST - FREIGHT ELEVATOR | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0266 |  |  | IA/SQ | 2022 | 1095 | 0 | 1095 | 0 | 0 | 0 | 0 | 0 | 1095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266R2 | 125 Worth St Roof | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0266 |  |  | SQ/IA | 2022 | 4677 | 0 | 520 | 0 | 4157 | 0 | 0 | 0 | 4677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW266TOIL | 125 WORTH ST.- CODE COMPLIANT TOILET UPGRADES | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CODE COMPLIANT TOILET UPGRADES | 2022 | 2450 | 0 | 0 | 0 | 250 | 0 | 0 | 2200 | 2450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW28280C | 80 CENTRE ST.- ADA IMPROVEMENTS | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 301 | PW-0282 |  |  | ADA IMPROVEMENTS | 2022 | 6500 | 0 | 0 | 500 | 6000 | 0 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293125D | 125 WORTH STREET - FIRE ALARM -SPRINKLERS | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 301 | PW-0293 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 125 WORTH STREET - FIRE ALARM DESIGN | 2022 | 49479 | 0 | 0 | 3612 | 0 | 0 | 45145 | 0 | 48757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW2931C | 1 CENTRE STREET - FIRE SPRINKLERS | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 301 | PW-0293 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 1 CENTRE STREET - FIRE SPRINKLERS | 2022 | 47865 | 86.41 | 0 | 4280 | 0 | 0 | 0 | 42786 | 47152.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293280A | 280 Broadway Sprinkler | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0293 |  |  | SQ/IA | 2022 | 1495 | 0 | 0 | 345 | 0 | 1150 | 0 | 0 | 1495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293GLDS | 100 Gold St Sprinkler | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0293 |  |  | SQ/IA | 2022 | 7800 | 0 | 600 | 7200 | 0 | 0 | 0 | 0 | 7800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW308PS1 | MAYOR'S OFFICE - 100 GOLD ST - PRINTSHOP UPGRADE | EQUIPMENT AND INTERAGENCY SERVICES | 301 | PW-0308 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2022 | 704 | 299.11 | 0 | 0 | 792 | 0 | 0 | 0 | 1091.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310COOL | 31 CHAMBERS ST.- COLD STORAGE SYSTEM FOR DORIS | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0310 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 31 CHAMBERS ST. NY, NY 10007 | REPLACEMENT OF 2 COOLING TOWERS; REPLACEMENT OF PUMPS, CONTROLS, & STEEL DUNNAGE | 2022 | 775 | 5.48 | 0 | 0 | 0 | 0 | 365 | 0 | 370.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW310FAN | 31 CHAMBERS ST. - REPLACEMENT OF FAN COIL UNITS ON FIRST FL. | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0310 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REPLACE EXISITNG 20 FAN COIL UNITS ON FIRST FLOOR, ASSOCIATED EQUIPMENT AND CONTROLS. EQUIPMENT HAS EXCEEDED ITS USEFUL LIFE SPAN. PERFORMALL RELATED MARBLE WORK. | 2022 | 1035 | 284.3 | 0 | 0 | 0 | 0 | 1122 | 0 | 1406.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW316EL | 280 BROADWAY - ELECTRICAL AND FIRE ALARM UPGRADE | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0316 |  |  | SQ FT | 2022 | 25539 | 0 | 0 | 1937 | 0 | 0 | 23238 | 0 | 25175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW324OMIS | DCAS IT LUMP SUM | EQUIPMENT AND INTERAGENCY SERVICES | 301 | PW-0324 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | VARIOUS DCAS FACILITIES |  | 2022 | 22998 | 798.33 | 0 | 0 | 0 | 0 | 10022 | 44191 | 55011.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326NYCC | CITY COUNCIL - 250 BROADWAY, FLS 14-18, 30 RENO & EXPANSION | RENOVATION OF LEASED SPACE | 301 | PW-D005 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SQ/IA | 2022 | 24633 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OLR2 | OLR - RELOCATION OF EMPLOYEE ASSISTANCE PROGRAM | RENOVATION OF LEASED SPACE | 301 | PW-0326 |  |  | SQ/IA | 2022 | 485 | 0 | 478 | 0 | 0 | 0 | 0 | 0 | 478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326OMBP | OMB Pantry at 255 Greenwich | RENOVATION OF LEASED SPACE | 301 | PW-0326 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LEASED SPACE - RENOVATION OF OMB PANTRY AT 255 GREENWICH | 2022 | 187 | 226.49 | 142 | 0 | 0 | 0 | 0 | 0 | 368.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAM | LAW DEPT - RAISE THE AGE - MANHATTAN | RENOVATION OF LEASED SPACE | 301 | PW-0326 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | LAW DEPT - RAISE THE AGE - MANHATTAN | 2022 | 4682 | 0 | 2327 | 0 | 2355 | 0 | 0 | 0 | 4682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZM03 | CBMN - RELOCATE COMM BD 3 FROM 59 E. 4TH STREET | RENOVATION OF LEASED SPACE | 301 | PW-0326 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MANHATTAN COMMUNITY BOARD 3 - RELOCATION FROM 59 EAST 4TH STREET | 2022 | 226 | 0 | 0 | 0 | 0 | 0 | 0 | 226 | 226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW327PLZ2 | 1 CENTRE STREET PLAZA REHABILITATION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 1 CENTRE STREET PLAZA REHABILITATION | 2022 | 11555 | 869 | 0 | 0 | 0 | 0 | 10858 | 0 | 11727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340FIP2 | BOE- FACILITIES IMPROVEMENT PROJECT | BOARD OF ELECTIONS MODERNIZATION | 301 | PW-0340 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FACILITIES IMPROVEMENT PROJECT | 2022 | 394 | 0 | 0 | 0 | 0 | 0 | 394 | 0 | 394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357ELC2 | 253 BROADWAY- ELECTRICAL UPGRADES PHASE 2 | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0357 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 253 BROADWAY- ELECTRICAL UPGRADES | 2022 | 5200 | 0 | 0 | 960 | 0 | 0 | 11520 | 0 | 12480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357STM2 | 253 BROADWAY - RECONSTRUCT STEAM STATION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0357 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECONSTRUCT STEAM STATION AT 253 BROADWAY | 2022 | 2364 | 0 | 0 | 200 | 0 | 0 | 2164 | 0 | 2364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW357VAUL | 253 BROADWAY - VAULT RECONSTRUCTION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0357 |  |  | SQ/IA | 2022 | 10678 | 0 | 0 | 777 | 0 | 8930 | 0 | 0 | 9707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77115CH | 115 CHRYSTIE ST. - INTERIOR RENOVATIONS | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | INTERIOR RENOVATIONS | 2022 | 4262 | 0 | 0 | 0 | 0 | 0 | 0 | 3362 | 3362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77136A | 60 LAFAYETTE ST, 2nd 4th FL - DOP | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | SQ/IA | 2022 | 3985 | 360.64 | -72 | 7553 | 401 | 0 | 0 | 0 | 8242.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77137C | 137 CENTRE ST. Renovation | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS |  | 137 CENTRE ST. RENOVATION | 2022 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C09 | 1 CENTRE ST. - 9th Floor Renovation | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 1 CENTRE ST. - 9TH FLOOR RENOVATION | 2022 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW771C21 | 1 CENTRE ST. - 21st Floor Renovation | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 1 CENTRE ST. - 21ST FLOOR RENOVATION | 2022 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722R5 | 22 READE ST.- 5th AND 6th FLOOR BUILDOUT | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | $390 PER SQ FT | 2022 | 9930 | 0 | 0 | 0 | 0 | 820 | 0 | 8208 | 9028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7722REV | 22 READE ST.- ELEVATOR MODERNIZATION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DCAS - 22 READE STREET ELEVATOR MODERNIZATION | 2022 | 2976 | 2808.75 | 0 | 241 | 0 | 0 | 0 | 0 | 3049.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77280V | 280 Broadway Vault Reconstruction | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | SQ/IA | 2022 | 27117 | 0 | 0 | 2086 | 0 | 25031 | 0 | 0 | 27117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW7780FAC | 80 CENTRE ST.- EXTERIOR REHABILITATION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 80 CENTRE ST MANHATTAN | RECONSTRUCT BUILDING FACADE | 2022 | 2679 | 2855.58 | 77 | 0 | 0 | 0 | 0 | 0 | 2932.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DAK01 | NY COUNTY DA'S OFFICE FIRE UPGRADES | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 PW-0293 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NY COUNTY DA'S OFFICE - FIRE ALARM SYSTEM UPGRADES AT 80 CENTRE AND 100 CENTRE STREET | 2022 | 308 | 406.99 | 26 | 0 | 0 | 11 | 0 | 0 | 443.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77DATU | DA MANHATTAN - ADA BATHROOM UPGRADE | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 301 | PW-0077 |  |  | ADA AT 100 CENTRE ST | 2022 | 2739 | 0 | 0 | 0 | 283 | 0 | 2000 | 0 | 2283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLD2F | 100 GOLD STREET 2 FLOOR - MOCs | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 100 GOLD STREET 2 FLOOR - MOCS | 2022 | 11681 | 9174.66 | 4608 | 1035 | 0 | 0 | 0 | 0 | 14817.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDBR | 100 GOLD ST - BATHROOM RENOVATION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | 100 GOLD ST - BATHROOM RENOVATION | 2022 | 7306 | 0 | 0 | 0 | 6617 | 0 | 0 | 0 | 6617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDEV | 100 GOLD ST - ELEVATOR MODERNIZATION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | IA/SQ | 2022 | 22554 | 0 | 1600 | 0 | 19194 | 0 | 0 | 0 | 20794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDFA | 100 GOLD ST - FIRE ALARM | REHABILITATION OF CITY-OWNED OFFICE SPACE | 300 | PW-0077 |  |  | 100 GOLD ST - FIRE ALARM | 2022 | 17160 | 1164.48 | 14581 | 0 | 0 | 0 | 0 | 0 | 15745.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77GLDX2 | 100 GOLD ST.- WINDOW REPLACEMENT AND EXTERIOR REHABILITATION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | SQ/IA | 2022 | 3828 | 0 | 0 | 0 | 0 | 3828 | 0 | 0 | 3828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77MBAC | CITY CLERK MARRIAGE BUREAU - SERVER ROOM AC UPGRADE | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | SERVER ROOM AC UPGRADE | 2022 | 118 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77MU8EL | 1 CENTRE ST.- 8TH FL. COMPTROLLERS OFFICE RENOVATIONS | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 1 CENTRE STREET 8TH FLOOR ELECTRICAL AND LIGHTING UPGRADE | 2022 | 15094 | 14217 | 0 | 0 | 0 | 0 | 0 | 272 | 14489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SANIT | DSNY - RELOCATE DSNY SPACE FROM 137 CENTRE ST. | RENOVATION OF LEASED SPACE | 301 | PW-0326 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 137 CENTRE ST. - RELOCATION OF DSNY SPACE | 2022 | 9829 | 7740.26 | 96 | 0 | 0 | 0 | 0 | 350 | 8186.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC14 | 1 CENTRE ST.- 14 FL SECURITY CAMERAS | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | CAMERA CONSTRUCTION | 2022 | 445 | 45 | 355 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC1C | 1 CENTRE ST - DCAS POLICE CCTV SYSTEM UPGRADE | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | SQ/IA | 2022 | 1985 | 1605.35 | 231 | 0 | 0 | 0 | 0 | 0 | 1836.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC22R | 22 READE ST - DCAS POLICE CCTV SYSTEM | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | SQ/IA | 2022 | 814 | 73.13 | 742 | 0 | 0 | 0 | 0 | 0 | 815.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC280 | 280 BROADWAY - DCAS POLICE CCTV SYSTEM | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | SQ/IA | 2022 | 814 | 73.13 | 742 | 0 | 0 | 0 | 0 | 0 | 815.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77SC2C | 2 LAFAYETTE ST - DCAS POLICE CCTV SYSTEM | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | SQ/IA | 2022 | 894 | 80.12 | 815 | 0 | 0 | 0 | 0 | 0 | 895.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80CT1 | 2 LAFAYETTE ST.- COOLING TOWER | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0080 |  |  | UNIT | 2022 | 599 | 0 | 0 | 58 | 0 | 500 | 0 | 0 | 558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEC | 2 LAFAYETTE STREET ELECTRICAL UPGRADE | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0080 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 2 LAFAYETTE STREET ELECTRICAL UPGRADE PHASE 2 | 2022 | 13000 | 0 | 0 | 0 | 1000 | 0 | 0 | 12000 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW80ELEV | 2 LAFAYETTE ST - ELEVATOR MODERNIZATION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0080 |  |  | IA/SQ | 2022 | 21483 | 0 | 1524 | 0 | 18282 | 0 | 0 | 0 | 19806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWCN001 | Sixth Street compost project | MISCELLANEOUS CONSTRUCTION | 300 303 | PW-D077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SIXTH STREET COMPOST PROJECT | 2022 | 68 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05CYBR | 80 CENTRE ST. - NY COUNTY DA CYBERCRIME AND IDENTITY THEFT | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-D005 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NY COUNTY DA'S OFFICE CYBERCRIME AND ID THEFT - CONSTRUCTION/OUTFITTING OF 11,307 SQ FT SPACE | 2022 | 5240 | 3629.75 | 0 | 0 | 0 | 0 | 92 | 0 | 3721.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD05DAHV | 80 CENTRE ST. - NY COUNTY DA HVAC UPGRADE SERVER ROOM | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-D005 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NEW YORK COUNTY DISTRICT ATTORNEY'S OFFICE -REPLACING THE HVAC SYSTEMIN THREE IT NETWORK ROOMS | 2022 | 479 | 0 | 0 | 0 | 0 | 0 | 479 | 0 | 479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BAG | 1 CENTRE ST.- BIG APPLE GREETER | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-D005 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BIG APPLE GREETER AT 1 CENTRE ST. | 2022 | 917 | 213.98 | 0 | 0 | 0 | 0 | 0 | 200 | 413.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5HSCHR | HECKSCHER Building -- Roof Renovation at 1 East 104th Street | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-D005 |  |  | SQ/IA | 2022 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWDNTEW | NONTRADITIONAL EMPLOYMENT FOR WOMEN 243 W 20th St | MISCELLANEOUS CONSTRUCTION |  | PW-D005 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NON-TRADITIONAL EMPLOYMENT FOR WOMEN -- BUILDING RENOVATION OF 243 W 20TH ST | 2022 | 800 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | MANHATTAN | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWMOCSIT1 | MOCS IT NETWORK INFRASTRUCTURE 100 GOLD STREET 2ND FL | REHABILITATION OF CITY-OWNED OFFICE SPACE | 301 | PW-0077 |  |  | MOCS IT NETWORK INFRASTRUCTURE 100 GOLD STREET 2ND FL | 2022 | 684 | 0 | 0 | 622 | 0 | 0 | 0 | 0 | 622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 037 | NEW YORK PUBLIC LIBRARY | LN20LSCRF | Library Services Center - Roof Deck Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | LN-0110 |  |  | LIBRARY SERVICES CENTER - ROOF DECK REPLACEMENT | 2022 | 7500 | 0 | 0 | 250 | 0 | 7250 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQ122-GEN | SYSTEMWIDE - General Projects/Infrastructure | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-D122 LQ-0122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GENERAL PROJECTS / INFRASTRUCTURE | 2022 | 5691 | 0 | 0 | 0 | 1696 | 0 | 0 | 18166 | 19862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQBCHREAD | BROAD CHANNEL: Library Seating Area | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-D122 |  |  | LIBRARY SEATING AREA | 2022 | 250 | 0 | 0 | 230 | 0 | 0 | 0 | 0 | 230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQBC-ROOF | BROAD CHANNEL: New roof | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-0122 |  |  | NEW ROOF | 2022 | 545 | 0 | 0 | 0 | 0 | 490 | 0 | 0 | 490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQBR-ROOF | BROADWAY - ROOF | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-0122 |  |  | BROADWAY ROOF | 2022 | 1002 | 0 | 0 | 0 | 0 | 783 | 0 | 117 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA19LHS | LANGSTON HUGHES:BMS SYSTEM | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-D122 |  |  | BMS SYSTEM | 2022 | 150 | 0 | 0 | 136 | 0 | 0 | 0 | 0 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA19QVB | QUEENS VILLAGE: Exterior Rehabilitation, ADA Access, Windows | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-D122 LQ-0122 |  |  | THIS PROJECT IS FOR THE EXTERIOR REHABILITATION, ADA ACCESS, WINDOWS AT THE QUEENS VILLAGE LIBRARY | 2022 | 0 | 0 | 0 | 0 | 5246 | 0 | 0 | 0 | 5246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA19WSD | WOODSIDE: Branch Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-D122 LQ-0122 |  |  | BRANCH RENOVATION | 2022 | 16156 | 0 | 0 | 0 | 572 | 6899 | 0 | 9501 | 16972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCA20MGR | McGoldrick: New Roof | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-D122 |  |  | MCGOLDRICK: NEW ROOF | 2022 | 1000 | 0 | 0 | 908 | 0 | 0 | 0 | 0 | 908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCC-XCES | SYSTEMWIDE - CC Excess Funding | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-D122 LQ-D001 |  |  | THIS PROJECT IS FOR EXCESS CITY COUNCIL FUNDING FROM CLOSED/COMPLETEDPROJECTS. CITY COUNCIL MEMBER WILL DETERMINE WHERE THIS FUNDING WILLBE TRANSFERRED TO. | 2022 | 494 | 0 | 0 | 0 | 0 | 523 | 0 | 0 | 523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCELHVAC | CENTRAL: Facade Restoration, Replace HVAC, Roof Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-D122 LQ-0122 |  |  | COMPREHENSIVE FACADE RESTORATION, ROOF AND HVAC SYSTEMS REPLACEMENT. | 2022 | 2000 | 0 | 0 | 1818 | 0 | 0 | 10316 | 1105 | 13239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQCORENOV | CORONA : Branch Expansion and Renovation | REPLACEMENT BRANCHES | 400 | LQ-D122 LQ-D001 LQ-0122 |  |  | CORONA RENOVATION | 2022 | 31064 | 0 | 0 | 1673 | 0 | 0 | 22343 | 957 | 24973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQD122LAE | LAURELTON: Branch Renovation | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-D122 LQ-0122 |  |  |  | 2022 | 11233 | 0 | 0 | 265 | 0 | 2284 | 880 | 6454 | 9883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQD122VEN | Mobile Library Unit | SUPPORT SERVICES IMPROVEMENTS | 414 | LQ-D122 LQ-D001 |  |  | VENDING MACHINES | 2022 | 984 | 0 | 698 | 231 | 0 | 0 | 0 | 0 | 929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQFH-ADA | Forest Hills - Main Entrance Accessibility | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | LQ-D122 LQ-Q122 |  |  | THIS PROJECT IS FOR MAIN ENTRANCE ACCESSIBILITY AT THE FOREST HILLS LIBRARY. | 2022 | 1200 | 0 | 46 | 1289 | 4670 | 0 | 0 | 0 | 6005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQFL-REP | Flushing - Replacement of Roof, HVAC, and Cooling Tower | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES |  | LQ-0122 |  |  | THIS PROJECT IS FOR THE REPLACEMENT OF THE ROOFING AND THE HEATING, VENTILATION AND AIR CONDITIONING, AND COOLING TOWER SYSTEMS. | 2022 | 5443 | 0 | 0 | 0 | 0 | 5400 | 0 | 0 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQHBW/D | HOWARD BEACH WINDOWS/DOORS | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-D122 LQ-0122 |  |  | HOWARD BEACH WINDOWS/DOORS | 2022 | 607 | 0 | 0 | 43 | 0 | 0 | 502 | 0 | 545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQHILRENO | HILLCREST: Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-D122 |  |  | LIBRARY ROOM RENOVATION | 2022 | 1450 | 0 | 0 | 0 | 0 | 0 | 1314 | 0 | 1314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLAHEXTR | LANGSTON HUGHES: Exterior Restoration | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-D122 LQ-0122 |  |  | EXTERIOR RESTORATION | 2022 | 1116 | 0 | 0 | 1009 | 0 | 0 | 0 | 0 | 1009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLFK-INT | Lefrak City Library - Interior renovations | ESSENTIAL RECONSTRUCTION OF FACILITIES | 404 | LQ-Q122 LQ-D122 LQ-0122 |  |  | LEFRAK CITY LIBRARY - INTERIOR RENOVATIONS | 2022 | 5000 | 0 | 0 | 2849 | 2000 | 0 | 0 | 0 | 4849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQLI-ROOF | LONG ISLAND CITY: New Roof | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-0122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW ROOF | 2022 | 1057 | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQMA-HVAC | MASPETH - HVAC | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-D122 LQ-0122 |  |  | MASPETH HVAC | 2022 | 1000 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQMAROOF | MASPETH ROOF | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-D122 LQ-0122 |  |  | MASPETH ROOF | 2022 | 1056 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQNFP-ADA | North Forest - Main Entrance Accessibility | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | LQ-D122 |  |  | THIS PROJECT IS FOR MAIN ENTRANCE ACCESSIBILITY AT NORTH FOREST PARK. | 2022 | 200 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQNFP-REN | North Forest Park - Renovation | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 406 | LQ-D122 LQ-0122 |  |  | THIS PROJECT IS FOR THE COMPLETE INTERIOR RENOVATION OF THE NORTH FOREST PARK LIBRARY. | 2022 | 2982 | 0 | 0 | 0 | 0 | 13175 | 0 | 170 | 13345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQNO-HVAC | NORTH HILLS - HVAC | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-D122 |  |  | NORTH HILLS - HVAC | 2022 | 850 | 0 | 0 | 773 | 0 | 0 | 0 | 0 | 773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQPOMHVAC | POMONOK - HVAC System Replacement | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 408 | LQ-Q122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | POMONOK - HVAC SYSTEM REPLACEMENT | 2022 | 500 | 0 | 0 | 453 | 0 | 0 | 0 | 0 | 453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQQ122-MT | MITCHELL-LINDEN - Site Acquisition & Renovation | REPLACEMENT BRANCHES | 407 | LQ-D122 LQ-0122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SITE ACQUISITION | 2022 | 7170 | 4300 | 0 | 0 | 4500 | 0 | 0 | 370 | 9170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQQA21CTQ | Court Square - New Library Fit Out | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | LQ-Q122 LQ-D122 |  |  | COURT SQUARE - NEW LIBRARY FIT OUT | 2022 | 1000 | 0 | 0 | 2801 | 0 | 0 | 0 | 0 | 2801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQQBH-RES | QUEENSBORO HILL - Resiliency | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-D122 |  |  | THIS PROJECT IS FOR RESILIENCY EFFORTS AT QUEENSBORO HILL LIBRARY. | 2022 | 2800 | 0 | 0 | 0 | 0 | 2800 | 0 | 0 | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQQV-TECH | QUEENS VILLAGE: Improvements | SUPPORT SERVICES IMPROVEMENTS | 400 | LQ-D122 |  |  | IMPROVEMENTS | 2022 | 200 | 0 | 0 | 0 | 182 | 0 | 0 | 0 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQRH-RENO | Richmond Hill - Branch Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | LQ-Q122 LQ-D122 LQ-0122 |  |  | THIS PROJECT IS FOR THE RENOVATION OF THE RICHMOND HILL LIBRARY. | 2022 | 15005 | 0 | 0 | 0 | 14428 | 0 | 0 | 0 | 14428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQRS-EXTR | ROSEDALE: Branch Expansion and Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-0122 LQ-D122 LQ-Q122 |  |  | EXPANSION AND RENOVATION | 2022 | 13048 | 0 | 0 | 6712 | 0 | 7690 | 0 | 6536 | 20938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSE-ROOF | SEASIDE: New Roof | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-0122 |  |  | NEW ROOF | 2022 | 891 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSE-WIN | SEASIDE: Windows and Doors | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-0122 |  |  | WINDOWS AND DOORS | 2022 | 891 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSJ-INT | SOUTH JAMAICA: Branch Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-0122 |  |  | INTERIOR RENOVATION | 2022 | 15195 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSTWSOLR | STEINWAY: Solar Panels | SUPPORT SERVICES IMPROVEMENTS | 400 | LQ-D122 |  |  | SOLAR PANELS | 2022 | 150 | 0 | 0 | 134 | 0 | 0 | 0 | 0 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQSZ-RENO | SOUTH OZONE PARK - Branch Expansion and Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-0122 |  |  | SOUTH OZONE PARK RENOVATION | 2022 | 12095 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWP-MASO | WINDSOR PARK - MASONRY | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-0122 |  |  | WINDSOR PARK MASONRY | 2022 | 350 | 0 | 0 | 50 | 0 | 0 | 0 | 300 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWP-TECH | WINDSOR PARK: Improvement | SUPPORT SERVICES IMPROVEMENTS | 400 | LQ-D122 |  |  | BRANCH IMPROVEMENT | 2022 | 200 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWS-TEEN | WOODSIDE: Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-D122 |  |  | TEEN SPACE RENOVATION | 2022 | 150 | 0 | 0 | 18 | 0 | 116 | 0 | 0 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | LQWSTTECH | WHITESTONE: Technology Initiative | SUPPORT SERVICES IMPROVEMENTS | 400 | LQ-D122 |  |  | TECHNOLOGY INITIATIVE | 2022 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 039 | QUEENS BOROUGH PUBLIC LIBRARY | SANDYLQLS | SANDY DAMAGES - QBPL | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-0122 |  |  | HURRICANE SANDY RELATED DAMAGES - QBPL | 2022 | 2963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2963 | 0 | 2963
20220309 | QUEENS | 042 | CITY UNIVERSITY | ACECUN201 | HVAC Damper Upgrades for CUNY Community Colleges | MISCELLANEOUS RECONSTRUCTION | 400 | PU-0025 |  |  | HVAC DAMPER UPGRADES | 2022 | 6050 | 0 | 6050 | 0 | 0 | 0 | 0 | 0 | 6050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | ACECUN801 | CUNY - Building Automation Controls Upgrade @ QCC | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | QUEENSBOROUGH COMMUNITY COLLEGE - BUILDING AUTOMATION CONTROLS UPGRADE PROJECT | 2022 | 4674 | 0 | 4674 | 0 | 0 | 0 | 0 | 0 | 4674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | CA034QB13 | Fire Alarm Reconstruction - Phase 3 | MISCELLANEOUS RECONSTRUCTION | 400 | HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FIRE ALARM RECONSTRUCTION - PHASE 3 | 2022 | 1000 | 26.25 | 0 | 974 | 0 | 0 | 0 | 0 | 1000.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | CA052-017 | Flushing Immigration Center | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FLUSHING IMMIGRATION CENTER | 2022 | 500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | CA055QB17 | CUNY ASAP Expansion | MISCELLANEOUS RECONSTRUCTION | 400 | HN-Q001 HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CUNY ASAP EXPANSION | 2022 | 4650 | 2935.05 | 0 | 0 | 0 | 1715 | 0 | 0 | 4650.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | CL018-015 | Trial Practice Room | MISCELLANEOUS RECONSTRUCTION | 400 | HN-Q300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TRIAL PRACTICE ROOM | 2022 | 500 | 895.66 | 0 | 249 | 106 | 0 | 0 | 0 | 1250.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | CL021-018 | Renovation of Community Room | MISCELLANEOUS RECONSTRUCTION | 411 | HN-Q300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION OF COMMUNITY ROOM | 2022 | 650 | 0 | 0 | 0 | 650 | 0 | 0 | 0 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | CL023-019 | Worker Educational and Development Center | MISCELLANEOUS RECONSTRUCTION | 411 | HN-Q300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WORKER EDUCATIONAL AND DEVELOPMENT CENTER | 2022 | 850 | 0 | 0 | 0 | 850 | 0 | 0 | 0 | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | CL024-019 | Data Center Fire Suppression System | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NON WATERBASED FIRE SUPPRESSION | 2022 | 1100 | 0 | 0 | 0 | 0 | 1100 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | KG037-015 | Science and Resilience Institute at Jamaica Bay | MISCELLANEOUS RECONSTRUCTION | 400 | HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DESCRIPTION: SCIENCE AND RESILIENCE INSTITUTE AT JAMAICA BAY | 2022 | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | LAGUARDIA | LaGuardia Community College Streetscape | MISCELLANEOUS | 400 402 | ED-Q384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LAGUARDIA COMMUNITY COLLEGE STREETSCAPE | 2022 | 400 | 314.79 | 108 | 0 | 0 | 0 | 0 | 0 | 422.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | LG001-021 | IT Network Infrastructure Replacements | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D003 |  |  | LAGUARDIA COMMUNITY COLLEGE | 2022 | 3100 | 0 | 0 | 3100 | 0 | 0 | 0 | 0 | 3100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | LG002-021 | Greenhouse Construction | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D003 |  |  | LAGUARDIA COMMUNITY COLLEGE | 2022 | 75 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | LG020-009 | NEW LIBRARY SPACE at LaGuardia CC | MISCELLANEOUS RECONSTRUCTION | 400 402 | HN-Q004 HN-D004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION AND CONSTRUCTION FOR NEW LIBRARY SPACE | 2022 | 5000 | 7008.54 | 1557 | 0 | 0 | 0 | 0 | 0 | 8565.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | LG024-022 | E Bldg - Scince & Occu Physical Therapy Labs Recon | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D002 HN-Q004 |  |  | E-BLDG - SCIENCE & OCCU PHYSICAL THERAPY LABS RECON | 2022 | 2350 | 0 | 0 | 2350 | 0 | 0 | 0 | 0 | 2350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | LG036-014 | Library Expansion and HVAC Upgrade | MISCELLANEOUS RECONSTRUCTION | 400 402 | HN-Q004 HN-D004 HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LIBRARY EXPANSION AND HVAC UPGRADE | 2022 | 1000 | 592.5 | 794 | 0 | 0 | 1250 | 0 | 0 | 2636.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | LG040-016 | Center 3 Infrastr. Upgrade, Fitout | MISCELLANEOUS RECONSTRUCTION | 400 | HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CENTER 3 INFRA. UPGRADE, 5TH & 8TH FOORS FITOUT | 2022 | 41000 | 1586.18 | 500 | 0 | 39025 | 0 | 0 | 0 | 41111.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | LG041-016 | Business and Entrepreneurial Training Center | MISCELLANEOUS RECONSTRUCTION | 402 | HN-Q006 HN-D002 HN-Q004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BUSINESS AND ENTREPRENEURIAL TRAINING CENTER | 2022 | 3400 | 1115.1 | 0 | 1750 | 4672 | 0 | 0 | 0 | 7537.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | LG043-018 | Shenker Hall Lab Renovation | MISCELLANEOUS RECONSTRUCTION | 402 | HN-Q004 HN-D004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SHENKAR HALL LAB RENOVATION | 2022 | 1500 | 795.6 | 704 | 3600 | 0 | 0 | 0 | 0 | 5099.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | LG071-019 | Student Success Center: Tutoring Hub | MISCELLANEOUS RECONSTRUCTION | 402 | HN-Q004 HN-D002 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RENOVATION TO C BLDG - CENTRALIZEDTUTORIN HUB - 5TH FLR | 2022 | 5100 | 0 | 0 | 0 | 0 | 4100 | 0 | 0 | 4100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | LG072-019 | Archive Construction | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D002 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ARCHIVE CONSTRUCTION | 2022 | 150 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | LG073-020 | LIBRARY PHASE II CONSTRUCTION | MISCELLANEOUS RECONSTRUCTION | 402 | HN-Q004 HN-D002 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | LIBRARY PHASE II CONSTRUCTION | 2022 | 9100 | 0 | 0 | 0 | 0 | 8543 | 0 | 0 | 8543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | QB001-021 | ADA Restroom Upgrades | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D004 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | AUXILLARY ENTERPRISE INC. | 2022 | 4106 | 0 | 0 | 0 | 0 | 4106 | 0 | 0 | 4106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | QB001-022 | Renovate Chemistry Lab | MISCELLANEOUS RECONSTRUCTION | 400 | HN-Q001 HN-0206 |  |  | RENOVATE CHEMISTRY LAB | 2022 | 750 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | QB002-010 | Queensborough CC - ADA Bathroom Upgrades at Kurt Schmeller L | MISCELLANEOUS RECONSTRUCTION | 411 | HN-0206 HN-Q006 HN-D002 HN-Q004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | QUEENSBOROUGH CC - ART EXHIBIT SPACE BIULD-OUT | 2022 | 400 | 66 | 1462 | 0 | 0 | 0 | 0 | 0 | 1528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | QB023-022 | ADA Restroom Reconstruction | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D002 HN-Q004 |  |  | ADA RESTROOM RENOVATION | 2022 | 612 | 0 | 0 | 612 | 0 | 0 | 0 | 0 | 612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | QB042-012 | THEATER RENOVATIONS AND ADA UPGRADES | MISCELLANEOUS RECONSTRUCTION | 400 | HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | THEATER RENOVATIONS AND ADA UPGRADES | 2022 | 750 | 6816 | 583 | 0 | 0 | 0 | 0 | 0 | 7399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | QB045-013 | Replace Three Roofs & Renovate Campus Theater | MISCELLANEOUS RECONSTRUCTION | 400 411 | HN-D005 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REPLACE THREE ROOFS & RENOVATE CAMPUS THEATER | 2022 | 1100 | 0 | 0 | 0 | 109 | 0 | 0 | 0 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | QB054-016 | Refurbishment and Upgrade of Research Labs | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D005 HN-D002 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REFURBISHMENT & UPGRADE OF RESEARCH LABS | 2022 | 1500 | 157.83 | 0 | 1442 | 0 | 0 | 0 | 0 | 1599.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | QB062-020 | RFK Gymnasium Ventilation and Air Conditioning | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RFK GYMNASIUM VENTILATION AND AIR CONDITIONING | 2022 | 2200 | 0 | 255 | 45 | 1900 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | QB063-020 | Theater Upgrades (PHASE II) | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D002 |  |  | THEATER UPGRADES | 2022 | 250 | 0 | 247 | 3 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | QB200-006 | Upgrade Electric System | ELECTRICAL, MECHANICAL AND HVAC SYSTEM UPGRADING | 400 411 | HN-D002 HN-Q004 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | THIS PROJECT WILL PROVIDE INCREASED ELECTRICAL SERVICE TO ALL BUILDINGS ON CAMPUS BY REPLACING SWITCHBOARDS, TRANSFORMERS, WIRING, AND HIGHVOLTAGE SUPPLY TO TRANSFORMERS. NEW ELECTRICAL PANELS WILL BE PROVIDED AT VARIOUS LOCATIONS WITHIN THE BUILDINGS. THE INCREASED ELECTRICAL SERVICE IS NEEDED FOR NEW COMPUTERS THAT ARE BEING USED IN LABS, CLASSROOMS AND OFFICES FOR THE COLLEGE'S NETWORK INFRASTRUCTURE PROJECT. | 2022 | 500 | 21050 | 250 | 0 | 0 | 0 | 0 | 0 | 21300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | QC001-021 | Renovate and Upgrade Lab Spaces | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D300 |  |  | QUEENS COLLEGE | 2022 | 2225 | 0 | 0 | 0 | 2225 | 0 | 0 | 0 | 2225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | QC001-022 | Food and Science Mgmt Lab Renovation | MISCELLANEOUS RECONSTRUCTION | 400 | HN-Q300 HN-D300 |  |  | FOOD AND SCIENCE LAB RENOVATION | 2022 | 750 | 0 | 0 | 2675 | 0 | 0 | 0 | 0 | 2675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | QC004-013 | Library and Classroom Space Upgrades | MISCELLANEOUS RECONSTRUCTION | 400 407 | HN-D300 HN-Q006 HN-Q300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LIBRARY AND CLASSROOM SPACE UPGRADES | 2022 | 1500 | 250.21 | 5070 | 0 | 0 | 0 | 0 | 0 | 5320.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | QC006-022 | Colden Auditorium | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D300 |  |  | COLDEN AUDITORIUM | 2022 | 1150 | 0 | 0 | 1150 | 0 | 0 | 0 | 0 | 1150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | QC039-011 | Louis Armstrong Visitor's Center | MISCELLANEOUS RECONSTRUCTION | 400 408 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CREATE LOUIS ARMSTRONG HOUSE MUSEUM VISITORS CENTER | 2022 | 50 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | QC047-013 | Kupferberg Renovation | MISCELLANEOUS RECONSTRUCTION | 400 407 | HN-Q300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ATRIUM RENOVATION | 2022 | 467 | 0 | 0 | 227 | 0 | 0 | 0 | 0 | 227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | QC054-015 | Speech & Hearing Center Upgrade Ph 2 | MISCELLANEOUS RECONSTRUCTION | 400 | HN-Q300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SPEECH & HEARING CENTER UPGRADE PH 2 | 2022 | 1500 | 2903.92 | 0 | 96 | 0 | 0 | 0 | 0 | 2999.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | QC061-016 | One Stop Service Center | MISCELLANEOUS RECONSTRUCTION | 408 | HN-Q300 HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SERVICE CENTER CONSTRUCTION | 2022 | 1500 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | QC061-017 | One Stop Center | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ONE STOP CENTER | 2022 | 1326 | 0 | 0 | 1326 | 0 | 0 | 0 | 0 | 1326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | QC065-017 | Recording Studio Renovation in the Music Bldg | MISCELLANEOUS RECONSTRUCTION | 400 | HN-Q300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECORDING STUDIO RENOVATION IN THE MUSIC BLDG | 2022 | 1000 | 161.17 | 0 | 0 | 839 | 0 | 0 | 0 | 1000.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | QC066-017 | Digital Film Center Construction | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DIGITAL FILM CENTER CONSTRUCTION | 2022 | 2000 | 245.5 | 0 | 0 | 1754 | 0 | 0 | 0 | 1999.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | QC070-018 | Psychology and Digital Photography Labs | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PSYCHOLOGY AND DIGITAL PHOTOGRAPHY LABS | 2022 | 1900 | 0 | 0 | 0 | 1900 | 0 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | QC072-019 | Renovation of Rathaus Hall Arts Center | MISCELLANEOUS RECONSTRUCTION | 400 407 | HN-Q300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION OF RATHAUS HALL ARTS CENTER | 2022 | 3200 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | QC074-019 | Biology Core Facility Upgrade | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BIOLOGY CORE FACILITY UPGRADE | 2022 | 1450 | 0 | 0 | 0 | 1450 | 0 | 0 | 0 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | QC075-020 | Colden Auditorium Renovation and Upgrades | MISCELLANEOUS RECONSTRUCTION | 411 | HN-Q300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GOLDEN AUDITORIUM RENOVATION AND UPGRADES | 2022 | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | QC076-020 | Air Pollution Laboratory-Commoner Center | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | AIR POLLUTION LABORATORY-COMMONER CENTER | 2022 | 1000 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | QC077-020 | Remsen Hall Science Bldg Upgrades | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REMSEN HALL SCIENCE BLDG UPGRADES | 2022 | 500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | QC078-020 | Construction of a Student Engagement and learning Ctr. | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D300 |  |  | CONSTRUCTION OF A STUDENT ENGAGEMENT AND LEARNING CENTER | 2022 | 2500 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | QC079-020 | Louis Armstrong House - Theater Lighting and Sound Systems | MISCELLANEOUS RECONSTRUCTION | 400 | HN-Q300 |  |  | LOUIS ARMSTRONG HOUSE-THEATER LIGHTING AND SOUND SYSTEMS | 2022 | 500 | 0 | 498 | 1 | 1 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | YC001-010 | YORK COLLEGE - DISABLED ACCESS UPGRADE | MISCELLANEOUS RECONSTRUCTION | 400 412 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DISABLED ACCESS UPGRADE | 2022 | 448 | 0 | 0 | 314 | 134 | 0 | 0 | 0 | 448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | YC001-021 | Track & Field Renovations | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D300 |  |  | TRACK & FIELD RENOVATIONS | 2022 | 2000 | 0 | 0 | 1035 | 0 | 0 | 0 | 0 | 1035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | YC001-022 | Track and Field Renovation | MISCELLANEOUS RECONSTRUCTION | 400 | HN-Q300 |  |  | TRACK AND FIELD RENOVATION | 2022 | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | YC008-022 | Track & Field Facility Upgrades | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D300 |  |  | TRACK & FIELD FACILITY UPGRADES | 2022 | 2000 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | YC022-007 | Financial Aid Office Renovation | MISCELLANEOUS RECONSTRUCTION | 411 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FINANCIAL AID OFFICE RENOVATION | 2022 | 411 | 0 | 0 | 0 | 411 | 0 | 0 | 0 | 411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | YC025-008 | SCIENCE FACILITY UPGRADES | DATA PROCESSING AND OTHER EQUIPMENT |  | HN-D300 HN-Q300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  |  | 2022 | 3372 | 3327.6 | 0 | 31 | 13 | 0 | 0 | 0 | 3371.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | YC027-008 | EXTERIOR BEAUTIFICATION, YORK COLLEGE | MISCELLANEOUS RECONSTRUCTION | 400 412 | HN-Q006 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EXTERIOR BEAUTIFICATION | 2022 | 3698 | 0 | 0 | 0 | 199 | 0 | 0 | 0 | 199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | YC028-008 | IMPROVEMENTS TO THE PERFORMING ARTS CENTER | MISCELLANEOUS RECONSTRUCTION |  | HN-Q300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | IMPROVEMENTS TO THE PERFORMING ARTS CENTER | 2022 | 145 | 0 | 0 | 0 | 145 | 0 | 0 | 0 | 145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | YC043-013 | Daycare Facility Improvements | MISCELLANEOUS RECONSTRUCTION | 400 412 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TO INCLUDE LEAP FROG ACADEMY WITHIN DAYCARE FACILITY | 2022 | 150 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | YC049-014 | Renovate/Build 3D Graphics and Printing Lab | MISCELLANEOUS RECONSTRUCTION | 400 412 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATE/BUILD 3D GRAPHICS AND PRINTING LAB | 2022 | 200 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | YC051-015 | Performing Arts Center Renovations | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PERFORMING ARTS CENTER RENOVATIONS | 2022 | 2800 | 0 | 0 | 339 | 145 | 0 | 0 | 0 | 484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | YC052-016 | Laboratory and Classroom Upgrades | MISCELLANEOUS RECONSTRUCTION | 412 | HN-Q300 HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LABORATORY AND CLASSROOM UPGRADES | 2022 | 1000 | 2015.68 | 0 | 1968 | 0 | 0 | 0 | 0 | 3983.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | YC054-017 | Greenhouse Renovation | MISCELLANEOUS RECONSTRUCTION | 400 | HN-Q300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GREENHOUSE RENOVATION | 2022 | 640 | 0 | 0 | 448 | 192 | 0 | 0 | 0 | 640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | YC055-017 | Digital Convergence Center | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DIGITAL CONVERGENCE CENTER | 2022 | 2000 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | YC059-019 | Renovation to Track | MISCELLANEOUS RECONSTRUCTION | 411 | HN-Q300 HN-D300 HN-0300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENONVATION TO TRACK | 2022 | 1700 | 0 | 3811 | 0 | 0 | 0 | 0 | 0 | 3811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | YC061-020 | Performing Arts Center Upgrades | MISCELLANEOUS RECONSTRUCTION | 411 | HN-Q300 HN-D300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2022 | 9105 | 7027.78 | 0 | 1454 | 623 | 0 | 0 | 0 | 9104.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 042 | CITY UNIVERSITY | YC063-020 | Recapture Academic Space | MISCELLANEOUS RECONSTRUCTION | 400 | HN-D300 |  |  | RECAPTURE ACADEMIC SPACE | 2022 | 2000 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 056 | POLICE DEPARTMENT | ACENYP601 | NYPD - Old Police Academy Steam Trap Replacement | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 402 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NYPD - CENTRAL MOTOR REPAIR | 2022 | 158 | 0 | 144 | 0 | 0 | 0 | 0 | 0 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 056 | POLICE DEPARTMENT | ACEPOL701 | NYPD - CRS STEAM TRAP REPLACEMENT | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NYPD - CRS STEAM TRAP REPLACEMENT | 2022 | 135 | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHH | HWY # 3 SEPTIC TANK | POLICE FACILITIES | 400 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 198-15 GRAND CENTRAL QUEENS | NEW SEPTIC TANK | 2022 | 98 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAHM | 101ST PCT HANDICAP RAMP | POLICE FACILITIES | 400 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 16-12 MOTT AV, FAR ROCKWAY QUEENS NY | HANDICAP RAMP | 2022 | 50 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAIF | 110TH FACADE | POLICE FACILITIES | 400 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 110TH PCT | FACADE REHAB | 2022 | 259 | 0 | 0 | 259 | 0 | 0 | 0 | 0 | 259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAII | FACADE AT NYPD'S FORENSIC LABORATORY | POLICE FACILITIES | 400 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | POLICE LAB | FACADE | 2022 | 67 | 0 | 0 | 2415 | 0 | 0 | 0 | 0 | 2415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAIJ | 106th pct FACADE | POLICE FACILITIES | 400 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 106TH PCT | FACADE | 2022 | 790 | 0 | 0 | 790 | 0 | 0 | 0 | 0 | 790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKB | REPLACEMENT OF GASOLINE PIPES AT HARBOR GEORGE | POLICE FACILITIES | 400 | PO-0079 |  |  | ESTIMATE | 2022 | 135 | 23.19 | 112 | 0 | 0 | 0 | 0 | 0 | 135.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKH | SRG4 BATHROOM RENOVATION | POLICE FACILITIES | 400 | PO-0079 |  |  | ESTIMATE | 2022 | 884 | 0 | 884 | 0 | 0 | 0 | 0 | 0 | 884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMAKZ | MOUNTED TROOP F AUGER COMPACTOR AND CONCRETE PAD | POLICE FACILITIES | 400 | PO-0079 |  |  | SCOPE DESCRIPTION | 2022 | 124 | 0 | 144 | 0 | 0 | 0 | 0 | 0 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 056 | POLICE DEPARTMENT | PO79BMALI | FT. TOTTEN TANKS REPLACEMENT | POLICE FACILITIES | 400 | PO-0079 |  |  | SCOPE OF WORK | 2022 | 306 | 0 | 306 | 0 | 0 | 0 | 0 | 0 | 306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 056 | POLICE DEPARTMENT | PO79FTTIL | K9 RELOCATION FROM BAT TO FORT TILDEN | POLICE FACILITIES | 400 | PO-0079 ED-0373 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SCOPE DESCRIPTION | 2022 | 8956 | 0 | 0 | 8956 | 0 | 0 | 0 | 0 | 8956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 056 | POLICE DEPARTMENT | PO79-MED | MEDICAL DIVISION RELOCATION | POLICE FACILITIES | 400 | PO-0079 |  |  | ESTIMATE | 2022 | 1398 | 0 | 0 | 2253 | 0 | 0 | 0 | 0 | 2253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 056 | POLICE DEPARTMENT | POD106COM | 106TH PCT - UPGRADE COMMUNITY ROOM | POLICE FACILITIES | 400 | PO-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION | 2022 | 75 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 056 | POLICE DEPARTMENT | POD115PRK | Parking Lot - 115th Precinct | POLICE FACILITIES | 400 | PO-D079 PO-0079 |  |  | COST ESTIMATE | 2022 | 185 | 0 | 209 | 0 | 0 | 0 | 0 | 0 | 209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q106 | 106th Precinct Renovation | POLICE FACILITIES | 400 | PO-Q079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RENOVATION | 2022 | 1000 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q107 | 107th Precinct Renovation | POLICE FACILITIES | 400 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 107TH PCT | RENOVATION | 2022 | 1295 | 1294.7 | 193 | 0 | 0 | 0 | 0 | 0 | 1487.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 056 | POLICE DEPARTMENT | PO-Q109 | 109th Precinct Locker Room Upgrade | POLICE FACILITIES | 400 | PO-Q079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RECONSTRUCTION OF THE LOCKER ROOM AT THE 109TH PRECINCT | 2022 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD08 | TRANSIT DISTRICT 23 ELECTRICAL | POLICE FACILITIES | 400 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ELECTRICAL REHABILITATION | 2022 | 854 | 6.92 | 79 | 0 | 0 | 0 | 0 | 0 | 85.92 | 62.36 | 706 | 0 | 0 | 0 | 0 | 0 | 768.36
20220309 | QUEENS | 056 | POLICE DEPARTMENT | SANDCD10 | HARBOR GEORGE | POLICE FACILITIES | 400 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | HARBOR GEORGE | ELECTRICAL SYTEM REHABILITATION | 2022 | 748 | 8.9 | 66 | 0 | 0 | 0 | 0 | 0 | 74.9 | 80.14 | 593 | 0 | 0 | 0 | 0 | 0 | 673.14
20220309 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN211 | FDNY- Lighting upgrade in 9 EMS Stations | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 401 | PU-0025 |  |  | LIGHTING UPGRADE IN 9 EMS STATIONS | 2022 | 593 | 0 | 0 | 593 | 0 | 0 | 0 | 0 | 593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN704 | FDNY - DESIGN & INSTALLATION OF 97 KW SOLAR SYSTEMS AT EMS45 | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FDNY - DESIGN & INSTALLATION OF 97 KW SOLAR PHOTOVOLTAIC SYSTEMS AT EMS45 | 2022 | 386 | 44.11 | 783 | 0 | 0 | 0 | 0 | 0 | 827.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 057 | FIRE DEPARTMENT | ACEFDN802 | FDNY - Lighting upgrades at 15 buildings at FDNY center | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | F-0175 PU-0025 | PROJECT DELAYED RESULTING FROM CONTRACTOR DEFAULT |  | LIGHTING UPGRADES AT 15 BUILDINGS AT FDNY TRAINING CENTER FORT TOTTEN | 2022 | 1262 | 0 | 377 | 1291 | 0 | 0 | 0 | 0 | 1668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 057 | FIRE DEPARTMENT | F175FMHVC | FLEET MAINTENANCE HVAC SYSTEM UPGRADE | NEW FACILITIES AND RENOVATIONS | 402 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FLEET MAINTENANCE HVAC SYSTEM UPGRADE | 2022 | 3321 | 356.55 | 0 | 0 | 3023 | 0 | 0 | 0 | 3379.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 057 | FIRE DEPARTMENT | F175MC266 | Multi-Component Renovations - EC266 | NEW FACILITIES AND RENOVATIONS | 414 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MULTI-COMPONENT RENOVATIONS - EC266 | 2022 | 6014 | 775.9 | 0 | 0 | 7349 | 0 | 0 | 0 | 8124.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 057 | FIRE DEPARTMENT | F175MC304 | Multi-Component Renovations - EC304 | NEW FACILITIES AND RENOVATIONS | 413 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MULTI-COMPONENT RENOVATIONS - EC304 | 2022 | 4556 | 555.53 | 67 | 4000 | 0 | 0 | 0 | 0 | 4622.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 057 | FIRE DEPARTMENT | F175MC307 | Multi-Component Renovations - EC307 | NEW FACILITIES AND RENOVATIONS | 403 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MULTI-COMPONENT RENOVATIONS - EC307 | 2022 | 7535 | 790.67 | 83 | 0 | 6750 | 0 | 0 | 0 | 7623.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 057 | FIRE DEPARTMENT | F175WN266 | WINDOW REPLACEMENT - EC266 | NEW FACILITIES AND RENOVATIONS | 414 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WINDOW REPLACEMENT - EC266 | 2022 | 480 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 057 | FIRE DEPARTMENT | F175WN329 | WINDOW REPLACEMENT - EC329 | NEW FACILITIES AND RENOVATIONS | 414 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WINDOW REPLACEMENT - EC329 | 2022 | 480 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 057 | FIRE DEPARTMENT | F175WP301 | Waterproofing - EC301 | NEW FACILITIES AND RENOVATIONS | 412 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WATERPROOFING - EC301 | 2022 | 4122 | 562.31 | 0 | 3620 | 0 | 0 | 0 | 0 | 4182.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 057 | FIRE DEPARTMENT | F175WP303 | Waterproofing - EC303 | NEW FACILITIES AND RENOVATIONS | 412 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WATERPROOFING - EC303 | 2022 | 3041 | 394.34 | 53 | 2650 | 0 | 0 | 0 | 0 | 3097.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 057 | FIRE DEPARTMENT | F175WP325 | Roofing and Waterproofing - EC325 | NEW FACILITIES AND RENOVATIONS | 402 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ROOFING AND WATERPROOFING - EC325 | 2022 | 2172 | 81.91 | 2590 | 0 | 0 | 0 | 0 | 0 | 2671.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 057 | FIRE DEPARTMENT | F1WOODSID | Unmanned Telemetry - Woodside | COMMUNICATIONS | 402 | F-0001 | PROJECT DELAYED DUE TO UNAVAILABILITY OF PRODUCT |  | UNMANNED TELEMETRY - WOODSIDE | 2022 | 1500 | 327.3 | 0 | 929 | 0 | 0 | 0 | 0 | 1256.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 057 | FIRE DEPARTMENT | FD175D262 | Door Replacement - EC262 | NEW FACILITIES AND RENOVATIONS | 401 | F-D175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DOOR REPLACEMENT - EC262 | 2022 | 150 | 80.72 | 0 | 69 | 0 | 0 | 0 | 0 | 149.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 057 | FIRE DEPARTMENT | FD175D316 | Door Replacement - EC316 | NEW FACILITIES AND RENOVATIONS | 403 | F-D175 F-0175 |  |  | DOOR REPLACEMENT - EC316 | 2022 | 75 | 0 | 76 | 0 | 0 | 0 | 0 | 0 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 057 | FIRE DEPARTMENT | FD175D324 | Door Replacement - EC324 | NEW FACILITIES AND RENOVATIONS | 404 | F-D175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DOOR REPLACEMENT - EC324 | 2022 | 150 | 90.89 | 59 | 0 | 0 | 0 | 0 | 0 | 149.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 057 | FIRE DEPARTMENT | FD175G289 | Generator - EC289 | NEW FACILITIES AND RENOVATIONS | 404 | F-D175 F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | GENERATOR - EC289 | 2022 | 771 | 101.85 | 1017 | 0 | 0 | 0 | 0 | 0 | 1118.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 057 | FIRE DEPARTMENT | FD175W316 | Window Replacement - EC316 | NEW FACILITIES AND RENOVATIONS | 403 | F-D175 |  |  | WINDOW REPLACEMENT - EC316 | 2022 | 350 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 057 | FIRE DEPARTMENT | FQ175G260 | Generator - EC260 | NEW FACILITIES AND RENOVATIONS |  | F-Q175 F-0175 |  |  | INSTALLATION OF NEW BUILDING GENERATOR AT EC260. | 2022 | 750 | 0 | 856 | 0 | 0 | 0 | 0 | 0 | 856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 057 | FIRE DEPARTMENT | FQ175K307 | KITCHEN RENOVATION - EC307 | NEW FACILITIES AND RENOVATIONS | 403 | F-Q175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | KITCHEN RENOVATION - EC307 | 2022 | 1200 | 78.52 | 0 | 1121 | 0 | 0 | 0 | 0 | 1199.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 057 | FIRE DEPARTMENT | FQ175WASH | REPLACEMENT OF WASHERS AND DRYERS | NEW FACILITIES AND RENOVATIONS |  | F-Q175 F-0175 |  |  | FDNY DECONTAMINATION FACILITY: REPLACEMENT OF WASHERS AND DRYERS, INCLUDING NECESSARY PLUMBING AND ELECTRICAL WORK | 2022 | 1000 | 64.5 | 1183 | 0 | 0 | 0 | 0 | 0 | 1247.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | ACEDHS801 | DHS - Gas fired condensing hot water systems | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 |  |  | GAS FIRED CONDENSING HOT WATER SYSTEMS FOR DOMESTIC HOT WATER (BRIARWOOD) | 2022 | 115 | 0 | 0 | 115 | 0 | 0 | 0 | 0 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH112BARS | Shelter at 21-10 Borden Avenue, 11110 - Roof/Skylight Replac | SHELTERS FOR HOMELESS INDIVIDUALS | 402 | HH-0112 |  |  | SHELTER AT 21-10 BORDEN AVENUE, 11110 - ROOF/SKYLIGHT REPLACEMENT | 2022 | 6650 | 384 | 116 | 0 | 3000 | 3000 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH112BOFW | Borden Avenue Flood Mitigation | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | FLOOD MITIGATION | 2022 | 2479 | 42 | 578 | 0 | 0 | 0 | 0 | 0 | 620 | 128 | 1731 | 0 | 0 | 0 | 0 | 0 | 1859
20220309 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH112FRRF | Franklin Women's Shelter - Roof Reconstruction | SHELTERS FOR HOMELESS INDIVIDUALS | 402 | HH-0112 |  |  | FRANKLIN WOMEN'S SHELTER - ROOF RECONSTRUCTION | 2022 | 0 | 0 | 1200 | 1200 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115BWRF | BRIARWOOD FAMILY RESIDENCE - ROOF AND FACADE UPGRADE | SHELTERS FOR HOMELESS FAMILIES | 408 | HH-0115 |  |  | BRIARWOOD FAMILY RESIDENCE - ROOF AND FACADE UPGRADE | 2022 | 1030 | 83 | 500 | 447 | 0 | 0 | 0 | 0 | 1030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115JAEX | JAMAICA FAMILY EXTERIOR | SHELTERS FOR HOMELESS FAMILIES | 412 | HH-0115 |  |  | JAMAICA FAMILY EXTERIOR | 2022 | 3250 | 250 | 0 | 1500 | 1500 | 0 | 0 | 0 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115JAFA | JAMAICA ASSESSMENT FIRE ALARM SYSTEM | SHELTERS FOR HOMELESS FAMILIES | 412 | HH-0115 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | JAMAICA ASSESSMENT -- | FIRE ALARM SYSTEM | 2022 | 1075 | 212.95 | 567 | 0 | 0 | 0 | 0 | 0 | 779.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115SINT | SPRINGFIELD BLD FACADE RECONSTRUCTION | SHELTERS FOR HOMELESS FAMILIES | 401 | HH-0112 |  |  | FACADE RECONSTRUCTION | 2022 | 576 | 0 | 0 | 48 | 528 | 0 | 0 | 0 | 576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | HH115SMEP | SPRINGFIELD BLD BOILER RECONSTRUCTION | SHELTERS FOR HOMELESS FAMILIES | 401 | HH-0112 |  |  | BOILER RECONST | 2022 | 420 | 0 | 420 | 0 | 0 | 0 | 0 | 0 | 420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 071 | DEPT OF HOMELESS SERVICES | SOLARDHS2 | Solar PV system at Borden Avenue facility | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 401 | PU-0025 |  |  | SOLAR PV SYSTEM AT BORDEN AVENUE FACILITY AT 21-10 BORDEN AVENUE, QUEENS | 2022 | 1428 | 0 | 1313 | 0 | 0 | 0 | 0 | 0 | 1313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C101-SEC | PERIMETER SECURITY & CAMERA REPLACEMENT | BUILDING SYSTEMS AND INFRASTRUCTURE | 400 | C-0101 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2022 | 1500 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 072 | DEPARTMENT OF CORRECTION | C75SEWR | RECONSTRUCTION OF RI SEWER LINES | BUILDING SYSTEMS AND INFRASTRUCTURE | 400 401 | C-0075 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RIKER ISLAND SEWER LINES HAVE DETERIORATED AND NEED TO BE RECONSTRUCTED. | 2022 | 1550 | 2143.95 | 500 | 7060 | 0 | 0 | 0 | 0 | 9703.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 096 | HUMAN RESOURCES ADMINISTRATION | HRCNSJMS2 | South Jamaica MSC renovation. | SOCIAL SERVICES BUILDINGS |  | HR-D002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION OF SOUTH JAMAICA MSC | 2022 | 190 | 0 | 0 | 0 | 0 | 190 | 0 | 0 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 096 | HUMAN RESOURCES ADMINISTRATION | HRCNSJMSC | South Jamaica MSC renovation | SOCIAL SERVICES BUILDINGS |  | HR-D002 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RENOVATION | 2022 | 250 | 0 | 0 | 0 | 0 | 298 | 0 | 0 | 298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 125 | DEPARTMENT FOR THE AGING | AGWOODRE1 | Woodside houses new gym for the elderly | DEPARTMENT FOR THE AGING BUILDING RECONSTRUCTION | 401 | AG-D001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WOODSIDE HOUSE NEW GYM FOR THE ELDERLY | 2022 | 65 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV040BTH1 | FTH - Flushing Town Hall - Bathroom Renovations HLD | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-Q040 PV-0040 PV-D040 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RENVATIONS TO BATHROOM IN FTH. | 2022 | 1022 | 0 | 0 | 0 | 0 | 0 | 2016 | 0 | 2016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050CYLT | MMI - Courtyard Lighting | ESSENTIAL RECONSTRUCTION OF FACILITIES | 401 | PV-Q050 PV-D050 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INSTALLATION OF NEW LIGHTING IN COURTYARD NEEDED FOR SPECIAL EVENTS AND EMERGENCIES. | 2022 | 750 | 0 | 0 | 0 | 0 | 957 | 0 | 0 | 957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050ENTR | MMI - Upgrades to Building Entrance | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-D050 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | UPGRADES TO ENTRANCE INCLUDING FACADE LIGHTING, SIGNAGE INFRASTRUCTURE, DIGITAL KIOSKS AND AUTOMATED DOORS. | 2022 | 223 | 0 | 0 | 0 | 0 | 223 | 0 | 0 | 223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV050MECH | MMI - Mechanical Systems Upgrade | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-D050 PV-Q050 PV-0050 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | UPGRADES TO HVAC, BMS AND SECURITY SYSTEMS. | 2022 | 1724 | 0 | 0 | 0 | 0 | 2253 | 481 | 0 | 2734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274-AH2 | NYHOS - New York Hall of Science - Air Handlers Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 407 | PV-0274 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | AIR HANDLERS | 2022 | 4500 | 0 | 0 | 0 | 0 | 0 | 3950 | 0 | 3950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274ELV2 | NYHOS - New York Hall of Science - Elevator | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-Q274 PV-0274 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NYHOS - NEW YORK HALL OF SCIENCE - ELEVATOR | 2022 | 1986 | 0 | 0 | 0 | 1765 | 0 | 0 | 0 | 1765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274PERI | NYHOS - New York Hall of Science, Perimeter Landscaping | ESSENTIAL RECONSTRUCTION OF FACILITIES | 407 | PV-D274 PV-Q274 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW PERIMETER FENCE AND SECURITY CAMERAS. | 2022 | 1186 | 0 | 0 | 0 | 0 | 4186 | 0 | 0 | 4186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV274RSRF | NYHOS - New York Hall of Science - Air Handlers Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 407 | PV-D274 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TBD | 2022 | 4317 | 0 | 0 | 0 | 4317 | 0 | 0 | 0 | 4317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV466QTP | QTIP - Queens Theater in the Park Shulman Theatre Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 407 | PV-Q466 PV-D466 PV-0466 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION | 2022 | 2846 | 0 | 0 | 0 | 0 | 4702 | 0 | 0 | 4702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ATTC | PS1 - Attic Renovation for Studios | ESSENTIAL RECONSTRUCTION OF FACILITIES | 401 | PV-Q501 PV-D501 PV-D467 PV-0501 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION OF PS1'S ATTIC SPACE AND BASEMENT TO CREATE ARTISTS STUDIOS AND EDUCATION SPACE. SCOPE INCLUDES ADA UPGRADES ELEVATOR. | 2022 | 2230 | 0 | 0 | 0 | 2701 | 200 | 0 | 0 | 2901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ELEV | PS1 - Elevator Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 401 | PV-0501 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CONSTRUCTION | 2022 | 563 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501ROOF | PS1 - Renovation of PS1 Roof Areas PH 2 | ESSENTIAL RECONSTRUCTION OF FACILITIES | 402 | PV-D501 PV-Q501 PV-0501 |  |  | RENOVATION OF PS1 ROOF AREAS, SUBSEQUENT PHASE OF PS1'S ROOF ACCESS AND ATTIC PROJECT PV501ATTC | 2022 | 3500 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV501RPH1 | PS1 - Renovation of PS1 Roof Areas PH 1 | ESSENTIAL RECONSTRUCTION OF FACILITIES | 402 | PV-Q501 PV-D501 |  |  | ROOF RENOVATION | 2022 | 1111 | 0 | 0 | 0 | 8224 | 0 | 0 | 0 | 8224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502ELEV | JCAL - Elevator Reconstruction/Modernization Section | ESSENTIAL RECONSTRUCTION OF FACILITIES | 412 | PV-Q502 PV-0502 PV-D502 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ELEVATOR UPGRADES | 2022 | 3217 | 0 | 0 | 0 | 0 | 2878 | 0 | 0 | 2878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV502-SDW | JCAL - JPAC Outdoor Performance Space & Sidewals | ESSENTIAL RECONSTRUCTION OF FACILITIES | 412 | PV-0502 PV-D502 PV-Q502 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CONSTRUCTION | 2022 | 2443 | 0 | 0 | 0 | 0 | 2172 | 0 | 0 | 2172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ECODOCKHC | ECO-DOCK AT HALLETS COVE | MISCELLANEOUS | 400 | ED-D401 ED-0409 P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ECODOCKHC | 2022 | 1000 | 1159.12 | 3841 | 0 | 0 | 0 | 0 | 0 | 5000.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ1191 | Vernon Boulevard Bulkhead Replacement | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q RE-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | VERNON BOULEVARD BULKHEAD REPLACEMENT | VERNON BOULEVARD BULKHEAD REPLACEMENT | 2022 | 1750 | 4542.72 | 466 | 0 | 0 | 0 | 0 | 0 | 5008.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | HWQ187A | 132nd St Construction - 20th Ave to Linden Place | PRIMARY STREET RECONSTRUCTION | 407 | ED-0075 HW-1674 HW-0001Q HW-0001 SE-0200Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCTION OF 132ND STREET BETWEEN 20TH AVE AND LINDEN PLACE IN THECOLLEGE POINT CORPORATE PARK. PROJECT IS ALSO KNOWN AS THE LINDEN PLACE EXTENSION | 2022 | 7000 | 11281.37 | 28003 | 0 | 0 | 0 | 0 | 0 | 39284.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMAAECT | GDJC - Atlantic Avenue Extension - Construction | COMMERCIAL DEVELOPMENT | 400 | ED-0075 ED-Q384 HW-0001Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GDJC - ATLANTIC AVENUE EXTENSION - CONSTRUCTION INCLUDING PM AND CM FEES. | 2022 | 11318 | 8243.98 | 212 | 0 | 0 | 0 | 0 | 1390 | 9845.98 | 5576.29 | 1 | 0 | 0 | 0 | 0 | 0 | 5577.29
20220309 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | JAMSTPLZ | Station Plaza Design & Construction | MISCELLANEOUS | 400 | HW-0001Q ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STATION PLAZA DESIGN & CONSTRUCTION | 2022 | 27212 | 0 | 754 | 0 | 0 | 3500 | 0 | 9371 | 13625 | 0 | 15933 | 0 | 0 | 0 | 0 | 0 | 15933
20220309 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | PV994FLXX | FLFC_Building Acquisition | ESSENTIAL RECONSTRUCTION OF FACILITIES | 401 | PV-0467 |  |  | FLFC_BUILDING ACQUISITION | 2022 | 4098 | 3999.99 | 0 | 0 | 0 | 0 | 0 | 98 | 4097.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | ROCKBLVD | FA - Rockaway BLVD | NEIGHBORHOOD REVITALIZATION | 400 410 412 413 | ED-D384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROCKAWAY BLVD | 2022 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDRLHPS | FA Resiliency - Land Hardening Hunters Point South | MISCELLANEOUS | 402 | FA-0027 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FA RESILIENCY - LAND HARDENING HUNTS POINTS | 2022 | 1000 | 24.86 | 119 | 106 | 0 | 0 | 0 | 0 | 249.86 | 74.59 | 357 | 318 | 0 | 0 | 0 | 0 | 749.59
20220309 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLTFAOF | FA - Willets Point Phase IA Offsite Infrastructure | MISCELLANEOUS | 400 | ED-0075 |  |  | FA - WILLETS POINT PHASE IA OFFSITE INFRASTRUCTURE | 2022 | 104031 | 0 | 93376 | 24075 | 11502 | 15224 | 11000 | 11000 | 166177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 801 | DEPT OF SMALL BUSINESS SERVICES | WILLTFAON | FA - Willet's Point Onsite Infrastructure | MISCELLANEOUS | 400 | ED-0075 SE-0200Q |  |  | FA - WILLETS POINT ONSIDE INFRASTRUCUTRE | 2022 | 75638 | 0 | 65773 | 9865 | 0 | 0 | 0 | 0 | 75638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM01ASCC | ASTORIA HOUSES - COMMUNITY CENTER UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 401 | HA-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SENIOR CITIZEN CENTER | 2022 | 500 | 1271.68 | 128 | 0 | 0 | 0 | 0 | 0 | 1399.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM15RFGR | REDFERN COMMUNITY CENTER PLAYGROUND | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 414 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | UPGRADE COMMUNITY CENTER PLAYGROUND | 2022 | 150 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SJBC | SOUTH JAMAICA HOUSES BASKETBALL COURT UPGRADES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 412 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | UPGRADE BASKETBALL COURTS | 2022 | 50 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CMPL | CARLTON MANOR PLAYGROUND RENOVATIONS BASKETBALL COURTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 414 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PLAYGROUND RENOVATIONS, INCLUDING BASKETBALL COURTS | 2022 | 250 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17BPSC | BAISLEY PARK INSTALLATION OF SECURITY CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 400 | HA-Q001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BAISLEY PARK HOUSES INSTALLATION OF SECURITY CAMERAS | 2022 | 500 | 434.22 | 66 | 0 | 0 | 0 | 0 | 0 | 500.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17LGPL | LATIMER GARDENS PLAYGROUND UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 400 | HA-Q001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LATIMER GARDENS PLAYGROUND UPGRADE | 2022 | 350 | 312.72 | 37 | 0 | 0 | 0 | 0 | 0 | 349.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM17SHSC | SHELTON HOUSES INSTALLATION OF CCTV'S AND LAC'S | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 412 | HA-Q001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SHELTON HOUSES INSTALLATION OF SECURITY CAMERAS | 2022 | 500 | 462.28 | 38 | 0 | 0 | 0 | 0 | 0 | 500.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18ASBC | RENOVATION OF BASKETBALL COURT AT ASTORIA HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 401 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION OF BASKETBALL COURT AT ASTORIA HOUSES | 2022 | 250 | 487.52 | 327 | 0 | 0 | 0 | 0 | 0 | 814.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BLGR | BLAND HOUSES GROUNDS BEAUTIFICATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 407 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BLAND GROUNDS BEAUTIFICATION, INCLUDES BENCHES, SIGNAGE AND GATE AT ENTRANCE | 2022 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM18COTV | LAYERED SECURITY ACCESS AT CONLON LIFHE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 412 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LAYERED SECURITY ACCESS AT CONLON LIFHE | 2022 | 220 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19AHSC | ASTORIA HOUSES SECURITY CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 401 | HA-D001 |  |  | INSTALL SECURITY CAMERAS | 2022 | 100 | 12 | 88 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CLHS | CONLON LIHFE HVAC SYSTEM | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 412 | HA-D001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FUNDING WILL PROVIDE UPGRADES TO THE HVAC SYSTEM | 2022 | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM19WHRB | WOODSIDE HOUSES RENOVATION OF BOYS AND GIRLS BATHROOMS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 401 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION OF BOYS AND GIRLS BATHROOM | 2022 | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20ASGR | ASTORIA- GARDEN AND GROUNDS BEAUTIFICATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 401 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NYCHA GARDEN AND GROUND BEAUTIFICATION -- FUNDS WILL BE USED TO SUPPORT OUTDOOR FURNITURE, ADDITIONAL PLANT BEDS, AND A NEW IRRIGATION SYSTEM BEHIND THE ASTORIA HOUSES COMMUNITY CENTER | 2022 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHCS | BAISLEY - CCTV CAMERA SYSTEM FOR ALL 27 BUILDINGS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 412 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NYCHA BAISLEY HOUSES CCT CAMERA SYSTEM -- CCT CAMERA SYSTEM FOR ALL 27 BUILDGINGS AT NYCHA BAISLEY HOUSES | 2022 | 1500 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHLL | BLAND HOUSES- LED LIGHTING | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 407 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BLAND HOUSES- ADDITIONAL LED LIGHTING THROUGHOUT THE DEVELOPMENT | 2022 | 300 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BPCC | Baisley Park Houses Community Center Reopen | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE |  | HA-0001 |  |  | REOPEN BAISLEY PARK HOUSES COMMUNITY CENTER TO BE NAMED FOR AAMIR GRIFFIN | 2022 | 6600 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20JYCL | S JAMAICA - UPGRADE TO COMPUTER LAB AT YOUTH CENTER | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 412 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NYCHA SOUTH JAMAICA HOUSES CORNERSTONE YOUTH CENTER RENOVATION -- UPGRADE TO COMPUTER LAB AT NYCHA YOUTH CENTER | 2022 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20LCSC | LEWIS H. LATIMER SECURITY CAMERAS AT SENIOR CENTER | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 407 | HA-D001 |  |  | LEWIS H. LATIMER SECURITY CAMERAS AT SENIOR CENTER | 2022 | 200 | 30.8 | 169 | 0 | 0 | 0 | 0 | 0 | 199.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM20RCCB | RAVENSWOOD COMMUNITY CENTER BATHROOMS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 401 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION OF THE BATHROOMS IN THE RAVENSWOOD HOUSES COMMUNITY CENTER-- RENOVATION OF THE BATHROOMS THAT ARE IN BAD CONDITION IN THE RAVENSWOOD HOUSES COMMUNITY CENTER. (PB) | 2022 | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM21BHEL | BEACH 41 STREET SECURITY UPGRADES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 414 | HA-Q001 |  |  | BEACH 41 STREET- INSTALLATION OF EXTERIOR LIGHTING | 2022 | 400 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SJWW | DIAGONAL CEMENT WALKWAY AT SOUTH JAMAICA HOUSES II | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 412 | HA-D001 |  |  | PB: -NEW OPEN AREA WALKWAY AT SOUTH JAMAICA HOUSES II-DIAGONAL CEMENTWALKWAY BETWEEN BUILDING 15 AND BUILDING 16 | 2022 | 160 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM21WSCB | BATHROOM RENOVATIONS AT WOODSIDE HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 401 | HA-D001 |  |  | WOODSIDE HOUSES SENIOR CENTER & COMMUNITY CENTER BATHROOM RENOVATIONS-FUNDING FOR BATHROOM RENOVATIONS | 2022 | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22AHSL | ASTORIA HOUSES- SCIENCE LAB | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 401 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NYCHA ASTORIA HOUSES SCIENCE LAB -- SCIENCE LAB CONSTRUCTION/RENOVATION IN ASTORIA HOUSES. | 2022 | 650 | 0 | 650 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22LMTU | LEWIS LATIMER HOUSE MUSEUM- TECHNOLOGY UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 407 | HA-D001 |  |  | LEWIS LATIMER HOUSE MUSEUM -- TECHNOLOGY UPGRADE | 2022 | 150 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22PBBQ | POMONOK HOUSES- OUTDOOR RENOVATIONS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 408 | HA-D001 |  |  | POMONOK HOUSES - OUTDOOR RENOVATIONS -- NEW BBQ AREA | 2022 | 250 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SJCA | SOUTH JAMAICA I & II- SECURITY OPERATIONS CENTER & CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 412 | HA-Q001 |  |  | NYCHA SOUTH JAMAICA HOUSES I&II--SECURITY OPERATIONS CENTER (SOC), CAMERAS AND INFRASTRUCTURE FOR CAMERAS. | 2022 | 1550 | 0 | 1550 | 0 | 0 | 0 | 0 | 0 | 1550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SJCB | SOUTH JAMAICA HOUSES- CLOUDBURST PLA ADDITIONS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 412 | HA-D001 |  |  | NYCHA SOUTH JAMAICA HOUSES: CLOUDBURST PLAN ADDITIONS -- BENCHES,AND LIGHTING FIXTURES IN BIORETENTION AREA | 2022 | 305 | 0 | 305 | 0 | 0 | 0 | 0 | 0 | 305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | ACEDOH901 | DOHMH - Boiler Controls Upgrade at 3 DOHMH Health Centers | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BOILER CONTROLS UPGRADE AT 3 DOHMH HEALTH CENTERS | 2022 | 200 | 49.59 | 150 | 0 | 0 | 0 | 0 | 0 | 199.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | CMEQANNEX | OCME - Queens Annex Phase | OCME |  | HL-0083 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | THE OCME ENDEAVORS TO REQUEST THE DESIGN AND CONSTRUCTION OF AN ANNEXFACILITY TO THE EXISTING QUEENS MORGUE TO ACCOMMODATE A SEPARATE CLAIMS-ONLY CASE MANAGEMENT DEPARTMENT AND FAMILY SERVICES CENTER (IN LIEUOF ANY TEMPORARY MEASURES WHICH MAY HAVE ALREADY BEEN IMPLEMENTED AND/OR PLANNED). THE FOLLOWING ARE BRIEF DESCRIPTION OF THE PROGRAMMATICNEEDS | 2022 | 7773 | 0 | 0 | 0 | 294 | 0 | 0 | 0 | 294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82JAMPH | JAMAICA HEALTH CENTER PHARMACY RETRO-FIT | CLINIC RENOVATION AND REHABILITATION |  | HL-0082 |  |  | DOHMH RETROFIT PARTIAL 4TH FLOOR STI OFFICE SUITE TO PHARMACY AT JAMAICA HEALTH CENTER LOCATED AT 9307 PARSONS BOULEVARD IN QUEENS, NY 11432 | 2022 | 125 | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 135 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 02201804 | LIC OUTFIT OFFICE SPACE | ROUTINE RECONSTRUCTION |  | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 30-30 47TH AVENUE, LIC, NY 11101 | NYC H+H IS OUTFITTING THE NEWLY LEASED SPACE AT 30-30 46TH AVE., LIC,4TH FLOOR, WITH HARDWARE FOR NETWORK INFRASTRUCTURE AND END-USER DEVICES, AND FURNITURE. | 2022 | 2874 | 2763.67 | 0 | 0 | 0 | 110 | 0 | 0 | 2873.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201301 | ELMHURST RENOVATION OF ADULT ER | ROUTINE RECONSTRUCTION | 404 | HO-0214 HO-Q378 HO-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 79-01 BROADWAY, ELMHURST, NY 11373 | RENOVATE THE ADULT ER INCLUDING THE CONSTRUCTION OF AN ENCLOSED STRETCHER BAY AREA ADJACENT TO THE ER, REDESIGN OF THE TRIAGE/REGISTRATION AREA, AND CONSTRUCTION OF AN EMS RAMP. | 2022 | 20000 | 2422.37 | 0 | 30339 | 0 | 0 | 0 | 0 | 32761.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201602 | EHC PARAPET & CORNER FACADE REHAB A,B,D,E, J AND O&G ANNEX. | ROUTINE RECONSTRUCTION | 404 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 79-01 BROADWAY, ELMHURST, N. Y. 11373 | THE PURPOSE OF THIS PROJECT IS TO RENOVATE BUILDINGS A, B, C, F AND G AT ELMHURST HOSPITAL CENTER USING LOCAL LAW 11- FUNDS FOR LOCAL LAW11 COMPLIANCE. | 2022 | 2804 | 152.4 | 0 | 2652 | 0 | 0 | 0 | 0 | 2804.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201610 | RENOVATE JUNCTION BLVD CHILD HEALTH CLINIC | ROUTINE RECONSTRUCTION | 403 | HO-0214 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 34-33 JUNCTION BLVD. CORONA, NY 11372 | RENOVATE THE JUNCTION BLVD CHILD HEALTH CLINIC IN ORDER TO EXPAND PRIMARY CARE HEALTH SERVICES. | 2022 | 4087 | 3739.85 | 0 | 0 | 0 | 341 | 0 | 0 | 4080.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201804 | ELMHURST: REHABILITATE N & S STAIRWELLS IN PARKING GARAGE | ROUTINE RECONSTRUCTION |  | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 79-01 BROADWAY, QUEENS, NY | REHABILITATE N & S STAIRWELLS IN PARKING GARAGE | 2022 | 992 | 586.02 | 185 | 221 | 0 | 0 | 0 | 0 | 992.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33201901 | ELMHURST L&D ROOMS AND MFM UNIT SUITE RENOVATIONS | ROUTINE RECONSTRUCTION |  | HO-D003 HO-Q378 HO-0214 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 79-01 BROADWAY, ELMHURST, NEW YORK 11373 | CONSTRUCTION OF THE LABOR AND DELIVERY ROOMS AND NURSING STATIONS AT ELMHURST HOSPITAL CENTER | 2022 | 4320 | 503.79 | 0 | 11216 | 0 | 0 | 0 | 0 | 11719.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202002 | ELMHURST: CONSTRUCT AMBULATORY CENTER | ROUTINE RECONSTRUCTION |  | HO-0214 HO-D003 |  | 79-01 BROADWAY, ELMHURST, NY 11373 | CONSTRUCT AMBULATORY CENTER AT NYC HEALTH + HOSPITALS / ELMHURST | 2022 | 5500 | 551.3 | 299 | 6949 | 0 | 0 | 0 | 0 | 7799.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202003 | ELMHURST: Upgrade of Emergency Electrical System | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 79-01 BROADWAY, ELMHURST, NY 11373 | UPGRADE EMERGENCY ELECTRICAL SYSTEMS - EES TYPE 1 | 2022 | 5004 | 326.57 | 0 | 4708 | 0 | 0 | 0 | 0 | 5034.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202101 | Elmhurst Re-lining of Sub-Basement Water Lines | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 79-01 BROADWAY, QUEENS, NY 11373 | NA | 2022 | 760 | 690.34 | 70 | 0 | 0 | 0 | 0 | 0 | 760.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202102 | ELMHURST: CONVERSION OF VACANT PYSCH UNIT 30 BED UNIT | ROUTINE RECONSTRUCTION |  | HO-D003 |  | 79-01 BROADWAY, ELMHURST, NY 11373 | CONVERSION OF VACANT PYSCH UNIT | 2022 | 2500 | 0 | 300 | 2200 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202104 | ELMURST MODERNIZE FREIGHT ELEVATORS | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 79-01 BROADWAY, QUEENS, NY 11373 | MODERNIZE FREIGHT ELEVATORS | 2022 | 1012 | 0 | 156 | 900 | 0 | 0 | 0 | 0 | 1056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202111 | ELMHURST: BUILD A CERTIFIED PEDIATRIC INTENSIVE CARE UNIT | ROUTINE RECONSTRUCTION |  | HO-Q378 |  | 79-01 BROADWAY, QUEENS, NY 11373 | ELMHURST HOSPITAL CENTER: BUILD A CERTIFIED PEDIATRIC INTENSIVE CAREUNIT | 2022 | 3000 | 0 | 500 | 2500 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202112 | ELMHURST ELEVATOR MODERNIZATION CARS 1-5, O & G | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 79-01 BROADWAY, ELMHURST NY 11373 | ELEVATOR MODERNIZATION ON PASSENGER CARS 1-5 & O & G | 2022 | 2253 | 0 | 253 | 2000 | 0 | 0 | 0 | 0 | 2253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202201 | ELMHURST CONVERSION OF CYSTO ROOMS TO FULL ORS | ROUTINE RECONSTRUCTION |  | HO-Q378 |  | 79-01 BROADWAY, ELMHURST NY 11373 | ELMHURST CONVERSION OF CYSTO ROOMS TO FULLS ORS | 2022 | 2500 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202202 | ELMHURST RADIATION ONCOLOGY SPACE RENOVATION | ROUTINE RECONSTRUCTION |  | HO-D003 |  | 79-01 BROADWAY, ELMHURST NY 11373 | ELMHURST RADIATION ONCOLOGY SPACE RENOVATION | 2022 | 1407 | 0 | 1407 | 0 | 0 | 0 | 0 | 0 | 1407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202203 | ELMHURST FIRE PUMP & SPRINKLER | ROUTINE RECONSTRUCTION |  | HO-0214 |  |  | NYC HEALTH + HOSPITALS/ ELMHURST (79-01 BROADWAY, QUEENS, NEW YORK) FIRE PUMP | 2022 | 17000 | 0 | 2000 | 0 | 15000 | 0 | 0 | 0 | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202204 | ELMHURST NEURO CRITICAL CARE UNIT/MULTI-DISCIPLINARY ICU | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 79-01 BROADWAY, ELMHURST NY 11373 | NYC HEALTH + HOSPITALS/ ELMHURST (79-01 BROADWAY, QUEENS, NEW YORK), NEURO CRITICAL CARE UNIT/MULTI-DISCIPLINARY ICU | 2022 | 12000 | 0 | 1200 | 10800 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202205 | ELMHURST ROOF REPLACEMENT | ROUTINE RECONSTRUCTION |  | HO-0214 |  |  | NYC HEALTH + HOSPITALS/ ELMHURST (79-01 BROADWAY, QUEENS, NEW YORK) ROOF REPLACEMENT | 2022 | 2075 | 0 | 375 | 1700 | 0 | 0 | 0 | 0 | 2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 33202206 | ELMHURST:FIRE ALARM SYSTEM & SPRINKLER MODERNIZATION | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 8268 164TH ST, JAMAICA, NY11432 | NYC HEALTH + HOSPITALS/ ELMHURST. FIRE ALARM SYSTEM & SPRINKLER MODERNIZATION | 2022 | 5000 | 0 | 1000 | 4000 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201201 | QUEENS "T" BUILDING RELOCATIONS | ROUTINE RECONSTRUCTION | 408 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 82-68 164 STREET, JAMAICA, NY 11432 | RELOCATE QUEEN HOSPITAL CENTER'S "T" BUILDING PROGRAMS TO MAKE WAY FOR AFFORDABLE/SUPPORTIVE HOUSING. | 2022 | 6500 | 2493.3 | 0 | 0 | 3689 | 0 | 0 | 0 | 6182.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201401 | QUEENS RENOVATIONS TO RELOCATE ACUTE DIALYSIS PROG. | ROUTINE RECONSTRUCTION | 400 408 | HO-Q003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 82-68 164TH STREET, JAMAICA, N. Y. 11432 | THE PURPOSE OF THIS PROJECT IS TO RENOVATE SPACE TO SUPPORT RELOCATION OF ACUTE DIALYSIS PROGRAM AT QUEENS HOSPITAL CENTER. | 2022 | 1200 | 101.92 | 0 | 11 | 1087 | 0 | 0 | 0 | 1199.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201402 | QUEENS RENOVATE/EXPAND ADULT EMERGENCY DEPARTMENT | ROUTINE RECONSTRUCTION | 408 | HO-Q003 HO-0214 HO-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 82-68 164TH STREET, JAMAICA, NY 11432 | QUEENS HOSPITAL CENTER PLANS TO EXPAND ITS ED INTO THE VACATED CPEP AND ED ADMINISTRATIVE OFFICES OF APPROXIMATELY 5,865 SQ. FT. OF SPACE IN ORDER TO ADD 20 TREATMENT SPACES. | 2022 | 3480 | 4990.2 | 0 | 140 | 757 | 0 | 0 | 0 | 5887.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201502 | QUEENS BOILER CONTROLS REPLACEMENT | ROUTINE RECONSTRUCTION | 408 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 82-68 164TH STREET, JAMAICA, NY 11432 | REPLACE END OF LIFE BOILER CONTROLS AT QUEENS HOSPITAL CENTER. | 2022 | 150 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201503 | QUEENS EXPAND AND RENOVATE PHARMACY | ROUTINE RECONSTRUCTION | 408 | HO-Q003 HO-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 82-68 164 STREET JAMAICA, NY 11432 | QHC: EXPAND AND RENOVATE PHARMACY | 2022 | 3600 | 110.67 | 0 | 3489 | 0 | 0 | 0 | 0 | 3599.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34201741 | QHC: PURCHASE IMAGING MACHINE AND RENOVATE IMAGING SUITE | MAJOR MEDICAL EQUIPMENT | 408 | HO-Q003 HO-D003 |  | 82-68 164TH STREET, JAMAICA, NY11432 |  | 2022 | 2300 | 73.15 | 2227 | 0 | 0 | 0 | 0 | 0 | 2300.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34202101 | QUEENS CONSTRUCT PARKING GARAGE | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 82-70 164TH STREET, JAMAICA, NY, 11432 | CONSTRUCT NEW PARKING GARAGE | 2022 | 10000 | 126.17 | 9874 | 0 | 0 | 0 | 0 | 0 | 10000.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34202102 | QUEENS BUILDING F ROOF REPLACEMENT | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 82-68 164TH STREET, JAMAICA NY 11432 | BUILDING S AN F ROOF REPLACEMENT | 2022 | 1200 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 34202247 | Queens Dental Camera X-Ray | MAJOR MEDICAL EQUIPMENT |  | HO-0214 |  |  |  | 2022 | 65 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | 69202101 | NEPONSIT DEMOLITION FOR THE CONSTRUCTON OF A PLAZA | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 149-25 ROCKAWAY BEACH BLVD QUEENS NY 11694 | YC H+H/ NEPONSIT. DEMOLITION AND REMOVAL OF THE FACILITY TO ALLOW FORTHE CONSTURCTION OF A PAVED PLAZA. THE PAVED PLAZA WILL BE BIULT BY NYC PARKS | 2022 | 11785 | 0 | 1218 | 32782 | 0 | 0 | 0 | 0 | 34000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | ACEHHC803 | QUEENS: ENERGY EFFICIENCY UPGRADES | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 HO-0214 |  |  | NYC HEALTH + HOSPITALS/QUEENS ENERGY EFFICIENCY UPGRADE | 2022 | 3197 | 0 | 5163 | 267 | 0 | 0 | 0 | 0 | 5430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 819 | HEALTH AND HOSPITALS CORP | ACEHHC902 | QUEENS ENERGY UPGRADES- N BUILDING | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ENERGY UPGRADES AT QUEENS HOSPITAL N BUILDING | 2022 | 2783 | 0 | 2783 | 0 | 0 | 0 | 0 | 0 | 2783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | ACEDEP601 | DEP - LED LIGHTING AT CATSKILL DELAWARE UV FACILITY | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 404 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | UNIT | 2022 | 960 | 0 | 0 | 873 | 0 | 0 | 0 | 0 | 873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-216-L | RECONSTRUCTION OF PRIMARY TANKS AT BOWERY BAY WPCP | PLANT UPGRADING AND RECONSTRUCTION | 400 401 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 43-01 BERRIAN BL;VD., ASTORIA, N.Y. 11105 | RECONSTRUCTION OF PRIMARY TANKS AT BOWERY BAY WPCP | 2022 | 16726 | 8582.65 | 0 | 0 | 104500 | 0 | 0 | 0 | 113082.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-220-L | REPLACEMENT OF EXISTING EMERGENCY GENERATORS @ BOWERY BAY | PLANT UPGRADING AND RECONSTRUCTION | 400 401 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 43-01 BERRIAN BLVD., ASTORIA, N.Y. 11105 | REPLACEMENT OF EXISTING EMERGENCY GENERATORS AT THE BOWERY BAY WASTEWATER TREATMENT PLANT | 2022 | 30650 | 0 | 0 | 12000 | 0 | 0 | 0 | 110000 | 122000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-239-L | INSTALL NEW WASTE ACTIVATED SLUDGE PUMPS @ BOWERY BAY WWTP | PLANT UPGRADING AND RECONSTRUCTION | 400 | WP-0112 |  | 43-01 BERRIAN BLVD. ASTORIA , NEW YORK 11105 | INSTALL A NEW WASTE ACTIVATED SLUDGE PUMPS AT THE BOWERY BAY WASTEWATER TREATMENT PLANT, QUEENS, NEW YORK. THERE IS NO WASTE ACTIVATED PUMPING SYSTEM (WAS), AT THE PLANT, THE PLANT IS CURRENTLY USING SURFACE WASTE ACTIVATED SLUDGE SYSTEM (SWAS) TO CONTROL THE SOLIDS INVENTORY.THERE IS A TOTAL OF (10) AERATION TANKS, THE SWAS PUMP SYSTEM IS USED TO PUMP WASTE ACTIVATED SLUDGE TO THE THICKENER DISTRIBUTION TOWER. SOME OF THE PIPING WILL BE MODIFIED TO INCORPORATE THE NEW WAS SYSTEM. | 2022 | 2500 | 0 | 0 | 5336 | 0 | 0 | 0 | 0 | 5336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | BB-61 | Main Sewage Pump Upgrades at Bowery Bay WPCP | PLANT COMPONENT STABILIZATION | 407 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | INSTALLATION OF MAIN SEWAGE PUMPS / VARIABLE FREQUENCY DRIVES AND GENERATORS AT THE BOWERY BAY WPCP | 2022 | 6988 | 12646.37 | 999 | 0 | 0 | 0 | 0 | 0 | 13645.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | C540 | Completion of CT3 Stage 2 B/Q Leg & Bklyn Downtake Intercon. | CITY TUNNEL NO. 3, STAGE 2 | 413 | W-0013 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | APPROXIMATE LOCATION: SHAFT 18B - VICINITY OF 30 AV & BROOKLYN-QUEENS EXPRESSWAY | CONSTRUCTION OF SHAFTS 17B AND 18B FOR CITY TUNNEL NO 3, STAGE 2 IN THEBOROUGH OF QUEENS | 2022 | 104830 | 569122.07 | 9078 | 0 | 174376 | 5200 | 0 | 0 | 757776.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-JA-BWR | JAMAICA BAY BENDING WEIRS AT REGULATORS | WATER QUALITY MANDATES | 400 410 412 413 414 | WP-0169 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | JAMAICA BAY BENDING WEIRS | 2022 | 14366 | 10055.08 | 244 | 0 | 0 | 0 | 0 | 0 | 10299.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-BAF | BORDEN AVENUE PUMP STATION FORCE MAIN | WATER QUALITY MANDATES | 400 | WP-0169 |  |  | ONSTRUCTION OF THE BORDEN AVENUE PUMP STATION FORCE MAIN. THE PROJECTWILL CONTROL CSO DISCHARGES TO DUTCH KILLS BY DIVERTING WET WEATHER FLOW FROM OUTFALL BB-026 VIA A NEW DIVERSION CHAMBER WITH TIDE GATE. | 2022 | 69236 | 0 | 5700 | 0 | 0 | 0 | 62081 | 0 | 67781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-BAP | BORDEN AVENUE PUMP STATION EXPANSION | WATER QUALITY MANDATES | 400 | WP-0169 |  |  | THE PROJECT WILL CONTROL CSO DISCHARGES TO DUTCH KILLS BY DIVERTING WET WEATHER FLOW FROM OUTFALL BB-026 VIA A NEW DIVERSION CHAMBER WITH TIDE GATE. NEW GRAVITY PIPING WILL BE CONSTRUCTED TO CONVEY FLOW FROM THE NEW DIVERSION CHAMBER TO THE BORDEN AVENUE PUMP STATION. THE CAPACITY OF THE BORDEN AVENUE PUMP STATION WILL BE EXPANDED TO INCLUDE 26 MGD OF WET WEATHER FLOW AND NEW FORCE MAIN WILL BE CONSTRUCTED FROM THE BORDEN AVENUE PUMP STATION TO UPSTREAM OF THE KENT AVENUE GATE WHICH SERVICES THE NEWTOWN CREEK WWTP. | 2022 | 74000 | 5814.62 | 0 | 0 | 6000 | 0 | 25904 | 0 | 37718.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-NC-EKE | ENGLISH KILLS AERATION BORDEN AVE PUMP STATION UPGRADE | WATER QUALITY MANDATES | 400 402 405 | WP-0169 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | ENGLISH KILLS AERATION, ENHANCED ZONE II. WATER QUALITY FACILITY COMBINED SEWER OVERFLOW NEWTOWN CREEK. | 2022 | 97309 | 25259.78 | 28151 | 0 | 0 | 0 | 0 | 0 | 53410.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-FC-DF | CSO FLUSHING CREEK & TI-011 DISINFECTION | WATER QUALITY MANDATES | 400 407 | WP-0169 |  |  | CSO FLUSHING CREEK & TI-011 DISINFECTION | 2022 | 24000 | 14900.28 | 0 | 0 | 0 | 18500 | 0 | 56500 | 89900.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-JA | JAMAICA WATER QUALITY COMBINED SEWER OVERLOW | WATER QUALITY MANDATES | 400 410 412 413 414 | WP-0169 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2022 | 170508 | 17640.4 | 1297 | 0 | 0 | 0 | 0 | 0 | 18937.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | DMCCSG | REPLACE SWITCHEARS & MCCS AT DOUGLASTON PS | WATER QUALITY PRESERVATION | 400 | WM-0105 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACE SWITCHEARS & MCCS AT DOUGLASTON PS | 2022 | 2500 | 6229.58 | 152 | 0 | 0 | 0 | 0 | 0 | 6381.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQN24 | Reconstruction of Existing Sewers, North Queens. | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 400 | SE-0002Q EP-0007 |  |  | RECONSTRUCTION OF EXISTING SEWERS, NORTH QUEENS. THIS IS A 1 YEAR CONTRACT. THE TARGETED START DATE FOR THIS CONTRACT IS AS SOON AS THE PREVIOUS CONTRACT EC-SEQN23, EXPIRES. | 2022 | 9252 | 0 | 0 | 0 | 8500 | 0 | 0 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEQS24 | Reconstruction of Existing Sewers, South Queens | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 400 | SE-0002Q EP-0007 |  |  | RECONSTRUCTION OF EXISTING SEWERS, SOUTH QUEENS. THIS IS A 1 YEAR CONTRACT. THE TARGETED START DATE FOR THIS CONTRACT IS AS SOON AS THE PREVIOUS CONTRACT, EC-SEQS23, EXPIRES. | 2022 | 10364 | 0 | 0 | 0 | 9500 | 0 | 0 | 0 | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | FCWET | CONSTRUCTION OF FLUSHING CREEK WETLAND PROJECT | WATER QUALITY MANDATES | 400 | WP-0169 |  |  | CONSTRUCTION OF FLUSHING CREEK WETLAND PROJECT | 2022 | 8000 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-BROADC | GI - GREEN INFRASTRUCTURE CONSTRUCTION IN BROAD CHANNEL, QNS | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-D169 |  |  | GREEN INFRASTRUCTURE CONSTRUCTION FOR STORM WATER MITIGATION FOR SHADCREEK ROAD AND W22ND ROAD IN BROAD CHANNEL | 2022 | 250 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-179-L | INSTALLATION OF EMERGENCY GENERATORS AT JAMAICA WPCP | PLANT UPGRADING AND RECONSTRUCTION | 400 410 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 150-2- 134TH STREET, JAMAICA, N.Y. 11430 | INSTALLATION OF EMERGENCY GENERATORS AT JAMAICA WPCP | 2022 | 57768 | 8133.34 | 32500 | 0 | 0 | 0 | 0 | 0 | 40633.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-187 | REPLACE MAIN SEWAGE PUMP CONTROLS AT JAMAICA WPCP | PLANT UPGRADING AND RECONSTRUCTION | 400 | WP-0112 |  |  | REPLACE MAIN SEWAGE PUMP CONTROLS AT JAMAICA WPCP | 2022 | 5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JA-STAB | STABILIZATION PROGRAM AT JAMAICA WPCP | PLANT COMPONENT STABILIZATION | 412 | WP-0247 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | QUEENS | FINAL DESIGN TO IMPROVE PROCESS AND TREATMENT OPERATIONS AND TO ALLOWTO ACCEPT FLOW EQUAL TO AT LEAST TWICE THE DRY WEATHER FLOW | 2022 | 638406 | 482632.39 | 375 | 0 | 0 | 0 | 0 | 0 | 483007.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | JFK-INTER | REROUTING OF INTERCEPTOR AT NEW JFK CARGO BUILDIING | PLANT UPGRADING AND RECONSTRUCTION | 400 | WP-0269 |  |  | RELOCATION OF INTERCEPTOR AT THE NEW JFK CARGO BUILDING | 2022 | 7000 | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | MASPETH | RECONSTRUCTION OF BUILDING, MASPETH, QUEENS | FACILITY PURCHASES AND RECONSTRUCTION | 400 | EP-0006 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RECONSTRUCTION OF BUILDING, MASPETH, QUEENS | RECONSTRUCTION OF BUILDING, MASPETH, QUEENS | 2022 | 67374 | 5542.88 | 0 | 1000 | 0 | 0 | 10000 | 0 | 16542.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-284 | CLEARVIEW PUMPING STATION | PLANT UPGRADING AND RECONSTRUCTION | 400 407 | WP-0269 |  | CLEARVIEW PUMPING STATION | CLEARVIEW PUMPING STATION | 2022 | 25422 | 5450.72 | 25286 | 0 | 0 | 0 | 0 | 0 | 30736.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-285 | RIKERS ISLAND NORTH AND SOUTH PUMPING STATION | PLANT UPGRADING AND RECONSTRUCTION | 400 401 | WP-0269 |  | RIKERS ISLAND NORTH | RIKERS ISLAND NORTH & SOUTH PUMPING STATION | 2022 | 9000 | 26381.63 | 138 | 0 | 0 | 0 | 0 | 0 | 26519.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-286 | ST ALBANS PUMPING STATION | PLANT UPGRADING AND RECONSTRUCTION | 400 412 | WP-0269 |  |  | ST ALBANS PUMPING STATION | 2022 | 8000 | 0 | 0 | 0 | 1500 | 15000 | 0 | 0 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-291 | 154TH STREET PUMPING STATION | PLANT UPGRADING AND RECONSTRUCTION | 400 407 | WP-0269 |  | 154TH STREET PUMPING STATION | 154TH STREET PUMPING STATION | 2022 | 4551 | 0 | 0 | 0 | 17900 | 0 | 0 | 0 | 17900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-292 | RECONSTRUCTIONOF LINDEN PLACE PUMPING STATION | PLANT UPGRADING AND RECONSTRUCTION | 400 407 | WP-0269 |  | LINDEN PLACE PUMPING STATION | LINDEN PLACE PUMPING STATION | 2022 | 6436 | 0 | 0 | 0 | 2000 | 36300 | 0 | 0 | 38300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-293 | RECONSTRUCTION AT HOWARD BEACH PUMPING STATION | PLANT UPGRADING AND RECONSTRUCTION | 400 410 | WP-0269 |  | HOWARD BEACH | RECONSTRUCTION AT HOWARD BEACH PUMPING STATION | 2022 | 8867 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-304 | RECONSTRUCTION AT GLENDALE PUMPING STATION | PLANT UPGRADING AND RECONSTRUCTION | 400 405 | WP-0269 |  | GLENDALE, QUEENS | RECONSTRUCTION AT GLENDALE PUMPING STATION | 2022 | 6000 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-321 | RECONSTRUCTION OF LITTLE NECK PUMPING STATION, QUEENS, N.Y. | PLANT UPGRADING AND RECONSTRUCTION | 400 411 | WP-0269 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 40TH AVENUE WEST OF 248TH STREET, QUEENS, NEW YORK | RECONSTRUCTION OF LITTLE NECK PUMPING STATION, QUEENS, N.Y. | 2022 | 7000 | 0 | 0 | 0 | 2000 | 38200 | 0 | 0 | 40200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-349 | REHABILITATION OF DAMAGED ROCKAWAY INTERCEPTOR | PLANT UPGRADING AND RECONSTRUCTION | 400 | WP-0269 |  |  | REHABILITATION OF DAMAGED ROCKAWAY INTERCEPTOR | 2022 | 25000 | 0 | 0 | 4000 | 0 | 21000 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED1040B | Dist. WM work along Woodhaven Blvd, Phase B QNS | AUGMENTATION OF WATER SUPPLY SYSTEMS | 406 409 410 | SE-0002Q WM-0001 |  |  | DISTRIBUTION WATER MAIN WORK ALONG WOODHAVEN BOULEVARD, PHASE B, QUEENS BETWEEN 107TH AVENUE AND UNION TURNPIKE. QED-1040B WILL BE COMPLETED IN CONJUCTION WITH DOT PROJECT HWQ100SBB. DDC TO TV INSPECT EXISTING SEWERS IN ROADWAY RECONSTRUCTION AREA. | 2022 | 16493 | 0 | 0 | 0 | 1813 | 14136 | 0 | 0 | 15949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1042B | WM & TM repmnt & SE repair in Queens Blvd | AUGMENTATION OF WATER SUPPLY SYSTEMS | 400 | SE-0002Q WM-0001 WM-0006 |  |  | WATER MAIN & TRUNK MAIN REPLACEMENT AND SEWER REPAIR IN QUEENS BOULVEARD FROM 73RD STREET TO 62ND AVENUE, IN QUEENS | 2022 | 74906 | 0 | 0 | 0 | 0 | 0 | 72278 | 0 | 72278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED-1053 | Trunk Water Main Replacement in Rockaway Blvd | AUGMENTATION OF WATER SUPPLY SYSTEMS | 400 | WM-0001 WM-0006 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | TRUNK WATER MAIN REPLACEMENT IN ROCKAWAY BLVD | 2022 | 27621 | 0 | 0 | 0 | 0 | 27621 | 0 | 0 | 27621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QED1058 | Dist WM in Francis Lewis Blvd from Weeks Ln to 53 Ave, QNS | AUGMENTATION OF WATER SUPPLY SYSTEMS | 400 | WM-0001 |  |  | DISTRIBUTION WATER MAIN WORK IN FRANCIS LEWIS BLVD FROM WEEKS LN TO 53RD AVE, QUEENS. | 2022 | 22015 | 0 | 0 | 0 | 0 | 22015 | 0 | 0 | 22015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | QNSREPAIR | REHABILITATION OF QUEENS REPAIR FACILITY | FACILITY PURCHASES AND RECONSTRUCTION | 400 | EP-0006 |  |  | REHABILITATION FO QUEENS REPAIR FACILITY | 2022 | 37750 | 0 | 0 | 0 | 0 | 4000 | 0 | 49000 | 53000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-151-L | RECONS FENDER & BULKHEAD AT THE ROCKAWAY WPCP | PLANT UPGRADING AND RECONSTRUCTION | 400 414 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 106-21 BEACH CHANNEL DRIVE, ROCKAWAY, N.Y. 11694 | REPLACE FENDERS AND BULKHEADS AT THE ROCKAWAY WPCP | 2022 | 26932 | 24.63 | 0 | 4000 | 0 | 0 | 43000 | 0 | 47024.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-153-L | RECONSTRUCT FINAL SETTLING SYSTEM @ ROCKAWAY WWTP | PLANT UPGRADING AND RECONSTRUCTION | 400 414 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 106-21 BECH CHANNEL DRIVE, ROCKAWAY, N.Y. 11694 | RECONSTRUCT FINAL SETTLING SYSTEM @ ROCKAWAY WWTP | 2022 | 21358 | 0 | 0 | 0 | 2106 | 0 | 0 | 23164 | 25270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | R-156-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ ROCKAWAY WWTP | PLANT UPGRADING AND RECONSTRUCTION | 400 414 | WP-0112 |  | 106-21 BEACH CHANNEL DRIVE, ROCKAWAY, N.Y. 11694 | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ ROCKAWAY WWTP | 2022 | 2254 | 0 | 0 | 5100 | 0 | 0 | 0 | 56000 | 61100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-2 | REPLACE MAIN SEWAGE PUMPS AT ROCKAWAY WPCP | PLANT UPGRADING AND RECONSTRUCTION | 400 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACE MAIN SEWAGE PUMPS AT ROCKAWAY WPCP | 2022 | 25000 | 0 | 7100 | 0 | 0 | 7100 | 70600 | 0 | 84800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | RO-ODOR | ODOR CONTROL UPGRADE IN THE THICKENER BLDG AT ROCKAWAY WPCP | PLANT UPGRADING AND RECONSTRUCTION | 400 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ODOR CONTROL UPGRADE IN THE THICKENER BLDG AT ROCKAWAY WPCP | 2022 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDROCK | RECONS OF THE ROCKAWAY WPCP DUE TO HURRICANE SANDY | PLANT UPGRADING AND RECONSTRUCTION | 400 414 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECONSTRUCTION OF THE ROCKAWAY WATER POLLUTION CONTROL PLANT DUE TO HURRICANE SANDY | 2022 | 2100 | 0 | 0 | 280 | 700 | 0 | 700 | 5655 | 7335 | 0 | 0 | 2520 | 6300 | 0 | 6300 | 50896 | 66016
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE-861A | HLSS; Strm, san & comb swers & WM, Borden Ave, Phase 2, Qns | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 402 | SE-0004 SE-0200Q SE-9336 SE-0002Q WM-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NEW HLSS; STRM, SAN & COMB SWERS & WM BORDEN AVE B/T JACKSON AVE & E RIVER, PHASE 2, QNS | 2022 | 27575 | 0 | 0 | 0 | 0 | 0 | 95000 | 0 | 95000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SE877 | Combined Swr installtion & WM Replac,77 Ave & 81-88st Qns | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 405 | SE-0002Q WM-0001 WM-0006 |  |  | COMBINED SEWER INSTALLATION AND WATER MAIN REPLACEMENT IN 77 AVE B/T 81ST. & 88TH. STREETS, QUEENS | 2022 | 78771 | 0 | 0 | 0 | 0 | 0 | 0 | 76007 | 76007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ002717 | WM & SE work on 48 St btwn Barnett & 37th Ave, QN Shaft 17B | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 401 | SE-0002Q WM-0001 |  |  | WATER MAIN AND SEWER WORK ALONG 48TH STREET BETWEEN BARNETT AVE AND 37TH AVE IN QUEENS. THIS PROJECT WILL CONNECT TO SHAFT 17B. | 2022 | 49226 | 0 | 0 | 0 | 0 | 0 | 49226 | 0 | 49226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200592 | SEQ - Rosedale South | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 413 | WM-0001 SE-0200Q SE-0002Q |  |  | INSTALLATION OF STORM AND SANITARY SEWERS AND WATER MAINS IN THE ROSEDALE AREA OF QUEENS BOUNDED BY HOOK CREEK BLVD, 257TH ST, CRAFT AVE, AND FRANCIS LEWIS BLVD, ETC. THIS PROJECT IS TO BE COMPLETED IN CONJUNCTION WITH DOT. | 2022 | 53282 | 0 | 0 | 0 | 38332 | 0 | 0 | 0 | 38332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200601 | Storm SE Ext at intersection of E 16 Rd & Channel Rd, QNS | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 414 | SE-0200Q |  |  | STORM SEWER EXTENSION AT THE INTERSECTION OF EAST 16TH ROAD AND CHANNEL ROAD IN THE BOROUGH OF QUEENS. | 2022 | 3787 | 0 | 0 | 0 | 0 | 0 | 3787 | 0 | 3787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ200605 | Installation of relief sewer, storm sewers, and WM | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 412 | SE-0200Q SE-0002Q WM-0001 |  |  | INSTALLATION OF RELIEF SEWER, STORM SEWERS, AND WATER MAINS ALONG 166TH ST, HENDRICKSON PL, AND 108TH AVE, NEAR ALLEN CATHEDRAL SENIOR RESIDENCE. | 2022 | 9213 | 0 | 0 | 0 | 0 | 8011 | 0 | 0 | 8011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-B67 | BEACH 67TH STREET MEDIAN GREEN INFRASTRUCTURE | BLUEBELT PROGRAM | 412 413 | SE-0005 |  |  | INSTALLATION OF FLOOD CONTROL BIOSWALES, NEW STORMWATER RUNOFF INLETS, AND PIPES TO IMPROVE DRAINAGE CONVEYANCE AND REDUCE FLOODING AT THE INTERSECTION OF BEACH 67TH STREET AND ALMEDA AVENUE | 2022 | 500 | 0 | 1194 | 0 | 0 | 0 | 0 | 0 | 1194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-DKWPK | CONSTRUCTION FOR DETECTIVE KEITH WILLIAMS PARK | BLUEBELT PROGRAM | 412 413 | SE-0005 |  |  | CONSTRUCTION FOR DETECTIVE KEITH WILLIAMS PARK | 2022 | 1250 | 0 | 0 | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQGI-01 | SEQ - CONSTRUCTION OF GREEN INFRASTRUCTURE SOUTHEAST QUEENS | BLUEBELT PROGRAM | 412 413 | SE-0005 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCTION OG RIGHT OF WAY BIOSWALES, RIGHT OF WAY GREENSTRIPS, STORMWATER GREENSTREETS, AND PRECAST POROUS CONCRETE IN SOUTHEAST QUEENS. | 2022 | 7957 | 8596.05 | 0 | 0 | 20590 | 0 | 0 | 0 | 29186.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-MEDHW | SEQ - MEDIAN GREEN INFRASTRUCTURE HILLSIDE AVENUE | BLUEBELT PROGRAM | 412 413 | SE-0005 |  |  | CONSTRUCT GREEN INFRASTRUCTURE PRACTICES IN THREE PUBLICLY OWNED MEDIANS ON AND ADJACENT TO HILLSIDE AVENUE IN SOUTHEASTERN QUEENS. THE GREEN INFRASTRUCTURE PRACTICES INCLUDE BIORETENTION AND SUBSURFACE STORAGE SYSTEMS. | 2022 | 2500 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-SACBA | SEQ -Design and construction of St. Albans Cloudburst Green | BLUEBELT PROGRAM | 412 413 | SE-0005 |  |  | SEQ -DESIGN AND CONSTRUCTION OF ST. ALBANS CLOUDBURST GREEN | 2022 | 2124 | 0 | 300 | 0 | 1770 | 0 | 0 | 0 | 2070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-SJH | CONSTRUCTION FOR CLOUDBURST PROJECT AT SOUTH JAMAICA HOUSES | BLUEBELT PROGRAM | 412 413 | SE-0005 |  |  | CONSTRUCTION FOR CLOUDBURST PROJECT AT SOUTH JAMAICA HOUSES | 2022 | 5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SEQ-STA | CONSTRUCTION FOR CLOUDBURST PROJECT AT ST ALBANS | BLUEBELT PROGRAM | 412 413 | SE-0005 |  |  | CONSTRUCTION FOR CLOUDBURST PROJECT AT ST ALBANS | 2022 | 2800 | 0 | 730 | 0 | 0 | 0 | 0 | 0 | 730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | SF-BNR-RK | STEP FEED BNR AT ROCKAWAY | BIOLOGICAL NUTRIENT REMOVAL | 400 414 | WP-0285 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | THIS PROJECT IS TO RETROFIT THE EXISTING ROCKAWAY WWTP FOR THE STEP FEED BNR PROCESS. THIS WORK IS A REQUIREMENT OF THE JAMAICA BAY NEGOTIATIONS WITHT THE DEC AND WILL BE ENFORCEABLE UNDER THE NEW NITROGEN CONSENT JUDGMENT. THE WORK WILL INVOLVE INSTALLING NEW DIFFUSERS, SUBMERSIBLE MIXERS, BAFFLES, FROTH CONTROL AND INSTRUMENTAION IN ALL FOUR AERATION TANKS. | 2022 | 27250 | 20277.85 | 134 | 0 | 0 | 0 | 0 | 0 | 20411.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | STA24TNKS | STATION 24 GROUNDWATER TANKS DEMOLITION | FACILITY PURCHASES AND RECONSTRUCTION | 400 | EP-0006 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DEMOLITION, REMOVAL AND DISPOSAL OF TWO (2) ON-GROUND WATER TANKS AT STATION 24, BWSO GROUNDWATER FACILITY (THE LOT ALSO INCLUDES FIELD OPERATIONS QUEENS REPAIR AND SOUTH SEWER MAINTENANCE FACILITIES) LOCATED AT 106-36 180TH ST, JAMAICA, NY. REMOVAL OF THE TANKS PRIOR TO THE COMPLETE REHABILITATION OF THE QUEENS REPAIR SITE WILL PROVIDE SPACE TO PARK DEP VEHICLES, AS WELL AS PROVIDE ADDITIONAL STORAGE AREA. | 2022 | 2500 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-006 | WESTERN CRIBWALL REPLACEMENT AT THE TALLMAN ISLAND WRRF | PLANT UPGRADING AND RECONSTRUCTION | 400 407 | WP-0112 |  |  | WESTERN CRIBWALL REPLACEMENT AT THE TALLMAN ISLAND WRRF | 2022 | 5000 | 0 | 0 | 4600 | 0 | 0 | 0 | 0 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-168-L | HEADWORKS IMPROVEMENTS AT THE TALLMAN ISLAND WPCP | PLANT UPGRADING AND RECONSTRUCTION | 400 407 | WP-0112 |  | 127 STREET AND EAST RIVER, COLLEGE POINT, N.Y. 11356 | HEADWORKS IMPROVEMENTS AT THE TALLMAN ISLAND WPCP | 2022 | 11273 | 5545.05 | 185 | 34000 | 0 | 0 | 0 | 0 | 39730.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-169-L | RECONSTRUCT OF THE POWER DISTRIBUTION AT TALLMAN ISLAND WPCP | PLANT UPGRADING AND RECONSTRUCTION | 400 407 | WP-0112 |  | 127TH STREET & EAST RIVER, COLLEGE POINT, N.Y. 11356 | RECONSTRUCTION OF THE POWER DISTRIBUTION AT TALLMAN ISLAND WPCP | 2022 | 7269 | 8691.78 | 0 | 55800 | 0 | 0 | 0 | 0 | 64491.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-5 | TALLMAN ISLAND LANDSCAPING UPGRADE & MISC. SITE IMPROVEMENTS | PLANT UPGRADING AND RECONSTRUCTION | 407 | WP-0249 |  |  | NATIVE VEGETATION, INCREASED PARKING CAPACITY, INCORPORATION OF INTERIORLY LOCATED SIDEWALK ACCESS TO BUILDINGS, GENERAL SAFETY MEASURES, SITE BEAUTIFICATION, AND IMPROVED VEHICULAR CIRCULATION. THE WORK WILL SATISFY THE PUBLIC DESIGN COMMISSION NEEDS FOR SIGN OFF ON THE TI-3 CERTIFICATE OF OCCUPANCY | 2022 | 6000 | 12766.33 | 114 | 0 | 0 | 0 | 0 | 0 | 12880.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 826 | DEPT ENVIRONMENTAL PROTECTION | TI-STAB | STABILIZATION OF THE TALLMANS' ISLAND WPCP | PLANT COMPONENT STABILIZATION | 407 | WP-0249 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | QUEENS | THE DESIGN FOR THE STABILIZATION OF THE TALLMAN'S ISLAND WPCP | 2022 | 496967 | 530573.65 | 89 | 0 | 0 | 0 | 0 | 0 | 530662.65 | 14361.31 | 0 | 0 | 0 | 0 | 0 | 0 | 14361.31
20220309 | QUEENS | 827 | DEPARTMENT OF SANITATION | ID21-QEFN | ID21 TROPICAL STORM IDA QUEENS ENF BOILERS Replacement | GARAGES AND FACILITIES | 401 | S-0136 |  |  | TROPICAL STORM IDA 21 RESTORATION AND REPAIRS DSNY: QUEENS POLICE ENFORCEMENT GARAGE, BOILERS REPLACEMENT, FACILITY IS LOCATED AT 51-13 AND 51-15 FLUSHING AVE, MASPETH, NY 11378, EEL 15 YEARS, CITY OWNED, CITY OPERATED. UA:905 BC:IDQE | 2022 | 306 | 0 | 77 | 0 | 0 | 0 | 0 | 0 | 77 | 0 | 229 | 0 | 0 | 0 | 0 | 0 | 229
20220309 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251E | QUEENS CRS AIR COMPRESSORS REPLACEMENT | GARAGES AND FACILITIES | 403 | S-0136 |  |  | AIR COMPRESSORS RUN VARIOUS TYPES OF EQUIPMENT AND FILL TIRES | 2022 | 130 | 0 | 506 | 0 | 0 | 0 | 0 | 0 | 506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251H | Queens CRS Water Tank Rehabilitation | GARAGES AND FACILITIES | 402 | S-0136 |  |  | REPLACE LINER OF WATER TANK TO REHABILITATE TANK | 2022 | 282 | 0 | 282 | 0 | 0 | 0 | 0 | 0 | 282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251K | Queens CRS Server Room Air Conditioning | GARAGES AND FACILITIES | 400 | S-0136 |  |  | QUEENS CRS SERVER ROOM AIR CONDITIONING | 2022 | 581 | 865.63 | 342 | 0 | 0 | 0 | 0 | 0 | 1207.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-251O | QUEENS CRS Main Steam Line | GARAGES AND FACILITIES | 402 | S-0136 |  |  | REPLACE STEAM PIPE | 2022 | 300 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-264Q | Queens 6 Betts Ave Garage Roof Replacement | GARAGES AND FACILITIES | 406 | S-0136 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | REPLACE ROOF | 2022 | 1226 | 2440.85 | 423 | 0 | 0 | 0 | 0 | 0 | 2863.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-332N | QUEENS 8/10/12 GARAGE REHAB | GARAGES AND FACILITIES | 408 410 412 | S-0136 |  |  | QUEENS 8/10/12 REHAB | 2022 | 23690 | 2277.15 | 541 | 0 | 30457 | 0 | 0 | 0 | 33275.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-380F | Queens 1 Garage Boilers Rehabilitation | GARAGES AND FACILITIES | 401 | S-0136 |  |  | BOILERS REHAB | 2022 | 459 | 558.42 | 319 | 0 | 0 | 0 | 0 | 0 | 877.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-380G | Queens 14 Garage HVAC Rehabilitation | GARAGES AND FACILITIES | 414 | S-0136 |  |  | REHABILITATE HVAC SYSTEM | 2022 | 487 | 168 | 487 | 0 | 0 | 0 | 0 | 0 | 655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-383Z | Queens 11/13 Gas Pipes | GARAGES AND FACILITIES | 411 413 | S-0136 |  |  | REPLACE GAS PIPES | 2022 | 250 | 0 | 982 | 0 | 0 | 0 | 0 | 0 | 982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431 | QUEENS 1 GARAGE | GARAGES AND FACILITIES | 401 | S-0136 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | GARAGE CONSTRUCTION | 2022 | 150650 | 0 | 0 | 9671 | 12088 | 0 | 120881 | 0 | 142640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-431A | Queens 1 Garage Rehabilitation | GARAGES AND FACILITIES | 401 | S-0136 |  |  | STRUCTURAL REHABILITATION TO EXTEND USEFUL LIFE | 2022 | 751 | 339.29 | 168 | 1066 | 0 | 0 | 0 | 0 | 1573.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-442 | Queens Northborough Repair Shop Fire Alarm System Replacemen | GARAGES AND FACILITIES | 400 | S-0136 |  |  | REPLACE FIRE ALARM SYSTEM | 2022 | 808 | 1340.39 | 30 | 66 | 0 | 0 | 0 | 0 | 1436.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-445 | Queens 6 Betts Ave Garage Rehab | GARAGES AND FACILITIES | 406 | S-0136 |  |  | REHAB | 2022 | 26495 | 0 | 175 | 2460 | 10505 | 13355 | 0 | 0 | 26495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-449B | Queens 5/5A Site Drainage Rehabilitation | GARAGES AND FACILITIES | 405 | S-0136 |  |  | DRAINS, PIPES AND OIL WATER SEPARATOR REPLACEMENT | 2022 | 1500 | 451.81 | 426 | 4006 | 0 | 0 | 0 | 0 | 4883.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 827 | DEPARTMENT OF SANITATION | S136-464H | Queens Flushing Ave Enforcement Garage Roof Replacement | GARAGES AND FACILITIES | 400 | S-0136 |  |  | ROOF REPL | 2022 | 1848 | 241.08 | 1016 | 0 | 0 | 0 | 0 | 0 | 1257.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 827 | DEPARTMENT OF SANITATION | S216-402D | North Shore MTS Dredging | SOLID WASTE MANAGEMENT | 400 | S-0216 |  |  | DREDGING OF NORTH SHORE MTS | 2022 | 7772 | 0 | 0 | 1296 | 6476 | 0 | 0 | 0 | 7772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 827 | DEPARTMENT OF SANITATION | S216-402F | NORTH SHORE MTS FUELING SYSTEM | SOLID WASTE MANAGEMENT | 400 407 | S-0216 |  |  | INSTALLATION OF FUELING SYSTEM | 2022 | 909 | 0 | 0 | 174 | 735 | 0 | 0 | 0 | 909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 827 | DEPARTMENT OF SANITATION | SANDQ14EL | Hurricane Sandy Queens 14 Electrical Replacement | GARAGES AND FACILITIES | 414 | S-0136 |  |  | REPLACEMENT OF CONDUIT, RAISING OF EQUIPMENT ABOVE FLOOD PLAIN | 2022 | 3797 | 1946.41 | 3 | 53 | 0 | 0 | 0 | 0 | 2002.41 | 3122.35 | 26 | 269 | 0 | 0 | 0 | 0 | 3417.35
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | ACEDOT212 | DOT- 32-11 Harper St Envelope and Garage Roll doors | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 401 | PU-0025 HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DOT- 32-11 HARPER ST ENVELOPE AND GARAGE ROLL DOORS | 2022 | 616 | 0 | 0 | 616 | 0 | 0 | 0 | 0 | 616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HB1070NB | Protective Coating of N blvd Bridges over Flushing River | Bridge Painting | 400 | HB-1070 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PROTECTIVE COATING OF NORTHERN BLVD BRIDGES OVER FLUSHING RIVER | PROTECTIVE COATING OF NORTHERN BLVD BRIDGES OVER FLUSHING RIVER | 2022 | 18100 | 0 | 18141 | 0 | 0 | 0 | 0 | 0 | 18141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HB1070QN | Protective Coating of Various Bridges in Queens | Bridge Painting | 400 | HB-1070 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PROTECTIVE COATING OF VARIOUS BRIDGES IN QUEENS | PROTECTIVE COATING OF VARIOUS BRIDGES IN QUEENS | 2022 | 11900 | 0 | 0 | 12470 | 0 | 0 | 0 | 0 | 12470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBGATES | Barrier Gates | Bridge Painting | 400 | HB-1070 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BARRIER GATES | BARRIER GATES | 2022 | 2000 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1114 | HEMPSTEAD AVE BR/CIP 2231780 | FAIR BRIDGES | 413 | HB-1114 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NA |  | 2022 | 24716 | 576 | 2251 | 0 | 0 | 0 | 6740 | 41531 | 51098 | 0 | 0 | 0 | 0 | 0 | 0 | 36237 | 36237
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1115 | UNION TURNPIKE / CROSS ISLAND PKWY 2-23185-0 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 413 | HB-1012 HB-1115 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NA |  | 2022 | 9031 | 4455.77 | 867 | 0 | 0 | 7019 | 53990 | 0 | 66331.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1137 | RECON ELLIOT AVE BRIDGE OVER QUEENS BLVD 2-24816-0 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 406 | HB-1137 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | N/A |  | 2022 | 11529 | 1557.58 | 0 | 0 | 0 | 0 | 1532 | 21631 | 24720.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1203 | RECON ROOSEVELT AVE BR OVER VAN WYCK EXPWY QUEENS 2-240507 | FAIR BRIDGES | 407 | HB-1203 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RECONS ROOSEVELT AVE BR OVER VAN WYCK EXPWY, QUEENS | RECONS ROOSEVELT AVE BR OVER VAN WYCK EXPWY, QUEENS | 2022 | 71248 | 55325.36 | 17685 | 0 | 0 | 0 | 0 | 0 | 73010.36 | 63311.46 | 21 | 0 | 0 | 0 | 0 | 0 | 63332.46
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1208 | LINDEN BLVD BRIDGE OVER CROSS ISLAND PKWY , QUEENS 2-23175-0 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 410 | HB-1012 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | LINDEN BOULEVARDD BRIDGE OVER CROSS ISLAND PARKWAY , QUEENS BIN#2-23175-0 | LINDEN BOULEVARD BRIDGE OVER CROSS ISLAND PARKWY , QUEENS BIN#2-23175-0 | 2022 | 7865 | 0 | 0 | 0 | 1910 | 0 | 2865 | 20095 | 24870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ1209 | SUNRISE HWY W/B BRIDGE OVER BLP W/B, QUEENS 2-23166-0 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 400 413 | HB-1012 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SUNRISE HIGHWAY W/B BRIDGE OVER BLP W/B, QUEENS BIN#2-23166-0 | SUNRISE HIGHWAY W/B BRIDGE OVER BLP W/B, QUEENS BIN#2-23166-0 | 2022 | 6360 | 0 | 0 | 1555 | 0 | 2765 | 19183 | 0 | 23503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ224766 | FOREST PARK DRIVE OVER ABANDONED LIRR BIN 2247660 | FAIR BRIDGES | 400 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | FOREST PARK DRIVE OVER ABANDONED LIRR | FOREST PARK DRIVE OVER ABANDONED LIRR | 2022 | 45264 | 0 | 0 | 0 | 0 | 5474 | 0 | 39790 | 45264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ224814 | Meridian Road over Stream North of LIE BIN 2248140 | FAIR BRIDGES | 400 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | FLUSHING MEADW PARK ROAD OVER STREAM NORTH OF LIE | FLUSHING MEADW PARK ROAD OVER STREAM NORTH OF LIE | 2022 | 19040 | 0 | 0 | 0 | 0 | 3063 | 0 | 15977 | 19040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ224837 | BOATHOUSE BRIDGE OVER AQUACADE LAKE BIN 2248379 | FAIR BRIDGES | 400 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BOATHOUSE BRIDGE OVER AQUACADE LAKE | BOATHOUSE BRIDGE OVER AQUACADE LAKE | 2022 | 25494 | 0 | 0 | 0 | 0 | 3459 | 0 | 22035 | 25494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ231710 | Merrick Blvd over BLP NB BIN 2231710 | FAIR BRIDGES | 400 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MERRICK BLVD OVER BLP NB BIN 2231710 | MERRICK BLVD OVER BLP NB BIN 2231710 | 2022 | 24556 | 0 | 0 | 3206 | 0 | 2669 | 18681 | 0 | 24556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ231720 | Merrick Blvd over BLP SB BIN 2231720 | FAIR BRIDGES | 400 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MERRICK BLVD OVER BLP SB BIN 2231720 | MERRICK BLVD OVER BLP SB BIN 2231720 | 2022 | 23324 | 0 | 0 | 3206 | 0 | 2515 | 17603 | 0 | 23324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ231880 | CROCHERON PARK PEDESTRIAN OVER BCIP BIN 223188 | FAIR BRIDGES | 400 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CROCHERON PARK PEDESTRIAN OVER BCIP | CROCHERON PARK PEDESTRIAN OVER BCIP | 2022 | 14904 | 0 | 0 | 0 | 0 | 2297 | 0 | 12607 | 14904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ49AV | 49TH AVE OVER LIRR, AMT, CON NE (BIN2247290) | FAIR BRIDGES | 400 402 | HB-1012 HB-0431 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 49TH AVE OVER LIRR, AMT, CON NE (BIN2247290) | 49TH AVE OVER LIRR, AMT, CON NE (BIN2247290) | 2022 | 30460 | 11958.41 | 4195 | 0 | 16570 | 81681 | 0 | 0 | 114404.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQ8019 | WOODHAVEN BLVD OVER ATLANTIC AVE BIN 2248019 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 400 405 406 409 | HB-1070 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REBAH WOODHAVEN BLVD BIN 2248019 | 2022 | 37644 | 0 | 0 | 5293 | 0 | 0 | 7589 | 53695 | 66577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23081 | ASTORIA BLVD EB/ 278I( BQE WEST LEG) BIN# 2230810 | FAIR BRIDGES | 400 | HB-1012 HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ASTORIA BLVD EB/ 278I( BQE WEST LEG) BIN# 2230810 | 2022 | 29201 | 1763.65 | 300 | 1491 | 26955 | 0 | 0 | 0 | 30509.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23165 | Sunrise Hwy WB over BLP EB BIN 2231650 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 400 | HB-1012 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SUNRISE HWY WB OVER BLP EB BIN 2231650 | SUNRISE HWY WB OVER BLP EB BIN 2231650 | 2022 | 18727 | 0 | 0 | 2750 | 0 | 1997 | 13980 | 0 | 18727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA23176 | BCIP OVER DUTCH BROADWAY-115 AVE BIN 2231760 | FAIR BRIDGES | 400 | HB-1173 |  | BCIP OVER DUTCH BROADWAY-115 AVE BIN 2231760 | BCIP OVER DUTCH BROADWAY-115 AVE BIN 2231760 | 2022 | 24984 | 1039.17 | 1756 | 37759 | 0 | 0 | 0 | 0 | 40554.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24750 | METROPOLITAN AVE OVER CSX TRANSPORT | FAIR BRIDGES | 400 | HB-1141 |  | METROPOLITAN AVE OVER CSX TRANSPORT | METROPOLITAN AVE OVER CSX TRANSPORT | 2022 | 67102 | 8166.39 | 300 | 624 | 63211 | 0 | 0 | 0 | 72301.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24815 | WOODHAVEN BLVD/ QUEENS BLVD BIN# 2248159 | FAIR BRIDGES | 400 | HB-1012 HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WOODHAVEN BLVD/ QUEENS BLVD BIN# 2248159 | 2022 | 40560 | 2013.24 | 3900 | 6147 | 0 | 53728 | 0 | 0 | 65788.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA24823 | BEACH CHANNEL DR WB over DR EB BIN 2248230 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 400 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BEACH CHANNEL DR WB OVER DR EB BIN 2248230 | BEACH CHANNEL DR WB OVER DR EB BIN 2248230 | 2022 | 16762 | 0 | 0 | 0 | 2733 | 0 | 1754 | 12275 | 16762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQA26614 | HEMPSTEAD AVE OVER BCIP RAMP NB BIN 2266149 | FAIR BRIDGES | 400 | HB-1012 HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HEMPSTEAD AVE OVER BCIP RAMP NB BIN 2266149 | HEMPSTEAD AVE OVER BCIP RAMP NB BIN 2266149 | 2022 | 30911 | 0 | 2157 | 0 | 0 | 0 | 3751 | 26260 | 32168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HBQENB012 | Emergency Fender System Northern Blvd WB/EB | FAIR BRIDGES | 400 | HB-0215 |  | EMERGENCY FENDER SYSTEM NORTHERN BLVD WB/EB | EMERGENCY FENDER SYSTEM NORTHERN BLVD WB/EB | 2022 | 18100 | 7298.21 | 400 | 5070 | 0 | 0 | 0 | 0 | 12768.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR19B | Citywide Milling - Queens | PRIMARY STREET RESURFACING | 400 | HW-0002Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITYWIDE MILLING- QUEENS | 2022 | 8000 | 4638.72 | 4196 | 0 | 0 | 0 | 0 | 0 | 8834.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HW349FT | In-House Paving | PRIMARY STREET RESURFACING | 400 | HW-0349 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | IN-HOUSE PAVING | IN-HOUSE PAVING | 2022 | 316 | 0 | 316 | 0 | 0 | 0 | 0 | 0 | 316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWCOINFAC | METER PROCESSING FACILITY REHABILITATION | FACILITY RECONSTRUCTION | 400 | HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COIN COLLECTION FACILITY REHABILITATION | COIN COLLECTION FACILITY REHABILITATION | 2022 | 5750 | 63.38 | 0 | 0 | 0 | 0 | 0 | 6731 | 6794.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD103100 | RECON OF MYRTLE AVE / UNION TURNPIKE ENTRANCE TO FOREST PK | PRIMARY STREET RECONSTRUCTION | 405 | HW-D103 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECON OF MYRTLE AVE / UNION TURNPIKE ENTRANCE TO FOREST PK | 2022 | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10312 | Safety Improvements at St. Margaret's School | PRIMARY STREET RECONSTRUCTION | 400 405 | HW-D103 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SAFETY IMPROVEMENTS AT ST. MARGARET'S SCHOOL | SAFETY IMPROVEMENTS AT ST. MARGARET'S SCHOOL | 2022 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10323 | Upgrades within the Bayside BID | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 400 | TF-Q503 TF-D503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | UPGRADES WITHIN THE BAYSIDE BID | UPGRADES WITHIN THE BAYSIDE BID | 2022 | 350 | 382.36 | 80 | 0 | 68 | 0 | 0 | 240 | 770.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10324 | Parsons Blvd & 84th Ave & Hoover Ave Ped Safety Improvements | PRIMARY STREET RECONSTRUCTION | 400 | HW-D103 HW-Q001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PARSONS BLVD & 84TH AVE & HOOVER AVE PEDESTRIAN SAFETY IMPROVEMENTS | PARSONS BLVD & 84TH AVE & HOOVER AVE PEDESTRIAN SAFETY IMPROVEMENTS | 2022 | 300 | 0 | 0 | 0 | 0 | 146 | 154 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10326 | Long Island City Bikeway Improvements | PRIMARY STREET RECONSTRUCTION | 400 | HW-D103 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | LONG ISLAND CITY BIKEWAY IMPROVEMENTS | LONG ISLAND CITY BIKEWAY IMPROVEMENTS | 2022 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10327 | Dutch Kills Pedestrian Safety Project | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | DUTCH KILLS PEDESTRIAN SAFETY PROJECT | DUTCH KILLS PEDESTRIAN SAFETY PROJECT | 2022 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10328 | A Safer Intersection at 71st Avenue and Austin Street | PRIMARY STREET RECONSTRUCTION | 400 | HW-D103 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | A SAFER INTERSECTION AT 71ST AVENUE AND AUSTIN STREET | A SAFER INTERSECTION AT 71ST AVENUE AND AUSTIN STREET | 2022 | 400 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10330 | Median and Street Reconstruction in Broad Channel | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MEDIAN AND STREET RECONSTRUCTION IN BROAD CHANNEL | MEDIAN AND STREET RECONSTRUCTION IN BROAD CHANNEL | 2022 | 4050 | 0 | 0 | 0 | 0 | 0 | 0 | 3750 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWD10332 | Reconstruct Curbs along median of Rockaway Freeway | PRIMARY STREET RECONSTRUCTION | 400 | HW-D103 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RECONSTRUCT CURBS ALONG MEDIAN OF ROCKAWAY FREEWAY. | RECONSTRUCT CURBS ALONG MEDIAN OF ROCKAWAY FREEWAY | 2022 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWNBVZ | Vision Zero Great Streets on Northern Blvd | SIDEWALK RECONSTRUCTION |  | HW-Q001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NORTHERN BLVD BETWEEN BROADWAY AND 114TH STREET | VISION ZERO GREAT STREETS: IMPROVEMENTS INCLUDING A RAISED PLANTED MEDIUM, CURB EXTENSIONS AND BUS BULBS ON NORTHERN BLVD BETWEEN BROADWAY AND 114TH STREET | 2022 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ005-01 | Median Updates at Junction/82nd & Ditmars/78-82 | PRIMARY STREET RECONSTRUCTION | 400 | HW-Q005 HW-0001Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MEDIAN UPDATES AT JUNCTION/82ND & DITMARS/78-82 | MEDIAN UPDATES AT JUNCTION/82ND & DITMARS/78-82 | 2022 | 4000 | 0 | 5530 | 0 | 0 | 0 | 0 | 0 | 5530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ100SBS | Woodhaven Blvd SBS | TRAFFIC WORK IN CONJUNCTION WITH HIGHWAY RECONSTRUCTION | 400 405 406 409 | HW-D103 HW-Q001 HW-1684 HW-0001Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WOODHAVEN BLVD QUEENS | WOODHAVEN BLVD SBS | 2022 | 3000 | 373.9 | 0 | 0 | 0 | 1888 | 0 | 9084 | 11345.9 | 0 | 0 | 0 | 0 | 0 | 0 | 112674 | 112674
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1190 | Reconstruction of Queens Blvd | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RECONSTRUCTION OF QUEENS BLVD | RECONSTRUCTION OF QUEENS BLVD | 2022 | 98781 | 2066 | 0 | 0 | 0 | 0 | 0 | 18963 | 21029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1192 | Jewel Ave | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | JEWEL AVE | JEWEL AVE | 2022 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1196 | Cloudburst Project - St Albans | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CLOUDBURST PROJECT - ST ALBANS | 2022 | 31758 | 0 | 0 | 0 | 0 | 0 | 0 | 31758 | 31758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1199 | Beach 84th Street End | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BEACH 84TH STREET | IMPROVEMENT OF THE STREET END ON BEACH 84TH STREET | 2022 | 5289 | 0 | 0 | 0 | 0 | 0 | 5289 | 0 | 5289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1200 | Vision Zero Great Streets Northern Boulevard Phase 1 | PRIMARY STREET RECONSTRUCTION | 400 | HW-D103 HW-0001Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | VISION ZERO GREAT STREETS NORTHERN BOULEVARD PHASE 1 | VISION ZERO GREAT STREETS NORTHERN BOULEVARD PHASE 1 | 2022 | 78750 | 0 | 0 | 0 | 0 | 300 | 78750 | 0 | 79050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1202 | 34TH AVENUE MALLS | PRIMARY STREET RECONSTRUCTION | 400 | HW-D103 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 34TH AVENUE MALLS | 34TH AVENUE MALLS | 2022 | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1203 | Maspeth Ave and Rust Street Safety Improvements | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001 HW-0001K | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MASPETH AVE AND RUST STREET SAFETY IMPROVEMENTS | MASPETH AVE AND RUST STREET SAFETY IMPROVEMENTS | 2022 | 8928 | 0 | 0 | 1109 | 0 | 0 | 7819 | 0 | 8928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1204 | Bayswater Park Pedestrian Access | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001K HW-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BAYSWATER PARK PEDESTRIAN ACCESS | BAYSWATER PARK PEDESTRIAN ACCESS | 2022 | 12621 | 0 | 0 | 1803 | 0 | 0 | 10818 | 0 | 12621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ1205 | Belt Parkway Guardrail at Sunrise Highway | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BELT PARKWAY | BELT PARKWAY | 2022 | 4000 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ20AVWF | East River Waterfront - 20th Avenue Street End | PRIMARY STREET RECONSTRUCTION | 400 | PU-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | EAST RIVER WATERFRONT - 20TH AVENUE STREET END | EAST RIVER WATERFRONT - 20TH AVENUE STREET END | 2022 | 3168 | 0 | 0 | 475 | 0 | 2693 | 0 | 0 | 3168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ788 | LIC/Hunters Point Area-wide Reconstruction | PRIMARY STREET RECONSTRUCTION | 402 | HW-0788 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | AREA BOUNDED BY 44TH DRIVE, JACKSON AVENUE, BORDEN AVENUE, AND U S PIERHEAD LINE | 21 & 11 STS: 44 DR - JACKSON AVE; VERNON BLVD: 44 DR - BORDEN AVE; 5THBORDEN AVE - POINT 250' +/- N/O 46 AVE; 45 AVE & 45 RD: JACKSON AVE -BLVD; 46 AVE & 46 RD: 5TH ST - JACKSON AVE; 47 AVE: JACKSON AVE - POIN+/- W/O 5TH ST; 47 RD: JACKSON AVE - POINT 650' +/- W/O 5TH ST; 48 AVEJACKSON AVE - POINT 700' +/- W/O 5TH ST; 49 AVE: JACKSON AVE - POINT 4W/O 5TH ST; 50 AVE: JACKSON AVE - 2ND ST; 51 AVE: VERNON BLVD - 2ND ST2ND ST: BORDEN AVE - 50TH AVE; PEARSON ST:THE EXISTING ROADWAY SHALL BE RECONSTRUCTED/ROADWAY RECONSTRUCTION SHAINCLUDE NEW CURBS, SIDEWALKS AND REQUIRED UTILITY REPLACEMENT/THERE ARAMENITIES/THIS PROJECT IS CITY FUNDED/THIS PROJECT IS IN CONJUNCTION W | 2022 | 35743 | 125.04 | 0 | 0 | 0 | 0 | 0 | 27453 | 27578.04 | 0 | 0 | 0 | 0 | 0 | 0 | 1920 | 1920
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ789 | THOMSON AVE. SAFETY IMPROVEMENTS -- LAGUARDIA COMM. COLLEGE | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | THOMSON AVE. SAFETY IMPROVEMENTS -- LAGUARDIA COMMUNITY COLLEGE | THOMSON AVE. SAFETY IMPROVEMENTS -- LAGUARDIA COMMUNITY COLLEGE | 2022 | 17000 | 163.04 | 10 | 0 | 0 | 4974 | 17000 | 0 | 22147.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQ985A | Shore Road Embankment Repair | PRIMARY STREET RECONSTRUCTION | 400 | HW-0988 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SHORE ROAD EMBANKMENT REPAIR | SHORE ROAD EMBANKMENT REPAIR | 2022 | 4000 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQBCH6WF | Reynolds Channel Waterfront - Beach 6 Street End | PRIMARY STREET RECONSTRUCTION | 400 | PU-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | REYNOLDS CHANNEL WATERFRONT  BEACH 6 STREET END | REYNOLDS CHANNEL WATERFRONT  BEACH 6 STREET END | 2022 | 5658 | 0 | 0 | 849 | 0 | 4809 | 0 | 0 | 5658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQBCH8WF | Reynolds Channel Waterfront - Beach 8 Street End | PRIMARY STREET RECONSTRUCTION | 400 | PU-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | REYNOLDS CHANNEL WATERFRONT - BEACH 8 STREET END | REYNOLDS CHANNEL WATERFRONT - BEACH 8 STREET END | 2022 | 6840 | 0 | 0 | 1026 | 0 | 5814 | 0 | 0 | 6840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF031C | Glendale Yard Pre-Engineered Shed | FACILITY RECONSTRUCTION |  | HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | GLENDALE YARD, QUEENS | REBUILD EXISTING GARAGE SPACE | 2022 | 348 | 97.57 | 0 | 0 | 250 | 0 | 0 | 0 | 347.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF041 | QUEENS SAFETY CITY CONSTRUCTION 2 | FACILITY RECONSTRUCTION | 400 | HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | QUEENS SAFTERY CITY CONSTRUCTION 2 | QUEENS SAFETY CITY CONSTRUCTION 2 | 2022 | 7638 | 0 | 0 | 0 | 0 | 0 | 858 | 6938 | 7796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF12ST | 38-21 12th Street Rehabilitation | FACILITY RECONSTRUCTION | 400 | HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 38-21 12TH STREET REHABILITATION | 2022 | 2500 | 0 | 0 | 0 | 0 | 0 | 500 | 2000 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF2002V | GLENDALE YARD TRAILERS | FACILITY RECONSTRUCTION | 400 406 | HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SYBILLA STREET FACILITY RENOVATION | SYBILLA STREET FACILITY RENOVATION | 2022 | 5049 | 1362.28 | 242 | 0 | 0 | 0 | 0 | 0 | 1604.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQF4200V | Installation of Sewer & Water Services for 4200 Vernon Blvd. | FACILITY RECONSTRUCTION | 400 | HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | INSTALLATION OF SEWER & WATER SERVICES FOR 4200 VERNON BLVD. | INSTALLATION OF SEWER & WATER SERVICES FOR 4200 VERNON BLVD. | 2022 | 168 | 0 | 227 | 0 | 0 | 0 | 0 | 0 | 227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFFRTN | Fort Totten | FACILITY RECONSTRUCTION | 400 | HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | FORT TOTTEN | FORT TOTTEN | 2022 | 363 | 0 | 330 | 0 | 0 | 0 | 0 | 0 | 330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQFSW033 | 33-00 Northern Blvd Swing Space | FACILITY RECONSTRUCTION | 400 | HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 3300 NORTHERN BLVD QUEENS | SWING SPACE FOR THE REHAB OF 28-11 QPN. | 2022 | 6619 | 615.21 | 2291 | 493 | 1100 | 1100 | 1019 | 0 | 6618.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQMASPET | Maspeth Climate Control and Air Quality Improvements | FACILITY RECONSTRUCTION | 400 402 | HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 58-50 57TH ROAD | MASPETH CLIMATE CONTROL AND AIR QUALITY IMPROVEMENTS | 2022 | 5301 | 0 | 0 | 0 | 78106 | 4332 | 11562 | 0 | 94000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQSE877 | Woodhaven Blvd SBS SE-877 | PRIMARY STREET RECONSTRUCTION | 400 | HW-0988 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WOODHAVEN BLVD SBS SE-877 | WOODHAVEN BLVD SBS SE-877 | 2022 | 22292 | 0 | 0 | 0 | 0 | 0 | 0 | 32925 | 32925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWF164 | Hawtree Basin Waterfront - 164 Ave/McKee Ave Street End | PRIMARY STREET RECONSTRUCTION | 400 | PU-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HAWTREE BASIN WATERFRONT - 164 AVE/MCKEE AVE STREET END | HAWTREE BASIN WATERFRONT - 164 AVE/MCKEE AVE STREET END | 2022 | 171 | 0 | 0 | 26 | 0 | 145 | 0 | 0 | 171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWQWILLPT | Willets Point Engineered Resurfacing | PRIMARY STREET RECONSTRUCTION | 400 | HW-0988 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WILLETS POINT ENGINEERED RESURFACING | WILLETS POINT ENGINEERED RESURFACING | 2022 | 17670 | 0 | 0 | 0 | 0 | 0 | 0 | 17670 | 17670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | HWWATER37 | 37TH AVE DOT MOVE DUE TO DEP WATER TUN 3 | FACILITY RECONSTRUCTION | 400 | W-0013 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 37TH AVE DOT MOVE DUE TO DEP WATER TUN 3 | 37TH AVE DOT MOVE DUE TO DEP WATER TUN 3 | 2022 | 3873 | 917.51 | 2968 | 0 | 0 | 0 | 0 | 0 | 3885.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | JAMASTPLZ | Greater Jamaica Dev Corp Station Plaza Acquisition | COMMERCIAL DEVELOPMENT | 400 412 | ED-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | GJDC STATION PLAZA ACQUISITION | 2022 | 5820 | 3352.84 | 311 | 0 | 0 | 0 | 0 | 0 | 3663.84 | 7017.43 | 2222 | 0 | 0 | 0 | 0 | 0 | 9239.43
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | QUEENSCWH | QUEENS COMMERCIAL CORRIDOR AT WOODHAVEN | MISCELLANEOUS | 400 | ED-Q384 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | QUEENS COMMERCIAL CORRIDOR AT WOODHAVEN--GREEN STREET WITH TREES AND PLANTINGS AT THE INTERSECTION OF JAMAICA AVENUE AND WOODHAVEN BLVD. | 2022 | 75 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD4 | Southeast Queens Priority Grids 31-40 | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SOUTHEAST QUEENS PRIORITY GRIDS 31-40 | 2022 | 17695 | 0 | 0 | 0 | 0 | 0 | 0 | 17695 | 17695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | SEQPGRD5 | Southeast Queens Priority Grids 41-50 | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SOUTHEAST QUEENS PRIORITY GRIDS 41-50 | 2022 | 17784 | 0 | 0 | 0 | 0 | 0 | 0 | 17784 | 17784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF072017 | Extension of lighting project Woodhaven | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 400 | TF-Q503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | EXTENSION OF EXISTNG LIGHTING PROJECT (841 QUEENSCJW) TO INCLUDE JAMAICA AVENUE FROM 102 STREET TO LEFFERTS BLVD | 2022 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF18-2020 | STEINWAY #1&2 MUNICIPAL PARKING FIELDS | Parking Meters, Lots, and Garages | 400 401 | TF-0018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECON OF PARKING FIELDS | 2022 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 182 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF18GRANP | Construction of Grand Central Parking Lot, Queens | Parking Meters, Lots, and Garages | 400 | TF-0018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DOT, CH AND DCAS TO BUILD A (METERED) PARKING LOT NEAR THE GRAND CENTRAL PARKWAY AND LITTLE NECK PARKWAY IN QUEENS THIS ESTIMATE IS FOR CONSTRUCTION OF 29,630 SF PARKING LOT (ROUGH ESTIMATE); APPROXIMATELY 57 SPACES - NEW SIDEWALK BUILD-OUT ALONG THE LOT PERIMETER (CURRENTLY IN ASPHALT) | 2022 | 8878 | 0 | 0 | 0 | 0 | 8878 | 0 | 0 | 8878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50308 | St lg Poles:Cross Bay Blvd ,156th to 165th Ave -S4319,MA122. | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 400 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACE/INSTALL STREET LIGHTING POLES: CROSS BAY BLVD. FROM 156TH TO 165TH AVENUES | 2022 | 685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 685 | 0 | 685
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50310 | Rlp lg brackets 102nd St and 159 Ave, -XMA123.30A | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 400 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 102ND STREET (FROM 160TH TO 159TH AVENUE) AND 159TH AVENUE (FROM 102ND TO 103RD STREET) REPLACEMENT OF LIGHTING BRACKETS ON EXISTING WOOD POLES | 2022 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 36
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TF50312 | St lg repl Union Turnpike:Main St to Utopia Pkwy MA2179.30 | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 400 | TF-0503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | STREET LIGHTING REPLACEMENT: UNION TURNPIKE: MAIN STREET TO UTOPIA PARKWAY | 2022 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660 | 0 | 660
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503-04 | ROOSEVELT AVENUE STREET LIGHTING | INSTALLATION OF LAMPPOSTS AND LUMINAIRES |  | TF-D503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | ROOSEVELT AVENUE STREET LIGHTING | ROOSEVELT AVENUE STREET LIGHTING | 2022 | 500 | 529.19 | 0 | 0 | 0 | 56 | 0 | 0 | 585.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFD503Q32 | MYRTLE AVE DECORATIVE LIGHTING QUEENS | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 400 | TF-D503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MYRTLE AVE DECRATIVE LIGHTING QUEENS | 2022 | 725 | 463.76 | 0 | 0 | 301 | 0 | 0 | 0 | 764.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | TFWHSBSRT | SBS - Real Time Totem System | SIGNAL INSTALLATION AND COMPUTERIZATION | 400 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WOODHAVEN SBS - REAL TIME TOTEM SIGNS | WOODHAVEN SBS - REAL TIME TOTEM SIGNS | 2022 | 517 | 1521.41 | 0 | 0 | 0 | 186 | 0 | 0 | 1707.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 841 | DEPARTMENT OF TRANSPORTATION | WHAMBEACH | HAMILTON BEACH BULKHEADS AND ROADWAYS | PRIMARY STREET RECONSTRUCTION | 410 | HW-D103 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HAMILTON BEACH AREA BULKHEADS AND ROADWAYS | HAMILTON BEACH AREA BULKHEADS AND ROADWAYS | 2022 | 597 | 0 | 0 | 0 | 0 | 0 | 0 | 597 | 597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | GQGIKISE | GI - CONS OF PARKLAND RETROFITS IN KISSENA PK | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-0169 P-0822 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | KISSENA PK AND KISSENA CORRIDOR, QUEENS | GI - CONS OF PARKLAND RETROFITS IN KISSENA PK AND KISSENA CORRIDOR | 2022 | 1906 | 218.6 | 493 | 0 | 0 | 0 | 0 | 0 | 711.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | GQQNGI-01 | GI - DSGN & CONS OF PARKLAND RETROFITS IN QUEENS | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-0169 P-1018 |  |  | GI - DSGN & CONS OF PARKLAND RETROFITS IN QUEENS | 2022 | 1861 | 332.8 | 0 | 4091 | 925 | 0 | 0 | 0 | 5348.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | IDA21-01 | OLMSTED CTR RC (BUILDING) Q099-808MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | QUEENS | OLMSTED CTR RC (BUILDING) | 2022 | 764 | 0 | 192 | 0 | 0 | 0 | 0 | 0 | 192 | 0 | 572 | 0 | 0 | 0 | 0 | 0 | 572
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | LIC-CTSQP | LIC- Court Square Park - Q267-120M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 402 | ED-0075 |  | JACKSON AVENUE, BETWEEN COURT SQUARE AND THOMSON AVENUE | COURT SQUARE PARK | 2022 | 4364 | 338.49 | 0 | 989 | 2979 | 0 | 0 | 0 | 4306.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | LIC-QNBBP | LIC-Queensbridge Baby Park Q104 | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 400 | ED-0075 |  | QUEENSBORO BRIDGE, 41 ROAD, 40 AVENUE, BETWEEN THE EAST RIVER VERNON BLVD AND 21 STREET | QUEENSBRIDGE BABY PARK | 2022 | 11000 | 150 | 348 | 0 | 5162 | 5490 | 0 | 0 | 11150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-NMKE1 | Nameoke Avenue Park- Site Work-Q509-220M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | ED-0384 |  | NAMEOKE AVENUE | SITE WORK AT NAMEOKE AVENUE PARK | 2022 | 5826 | 141.5 | 253 | 2781 | 0 | 253 | 0 | 2539 | 5967.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-NMKE2 | Nameoke Avenue Park- Comfort Station | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | ED-0384 |  | NAMEOKE AVENUE | COMFORT STATION AT NAMEOKE AVENUE PARK | 2022 | 3720 | 125 | 10 | 3700 | 0 | 0 | 0 | 0 | 3835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | NDF-RDFR | NDF - Redfern Playground | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | ED-0384 |  |  | NEIGHBORHOOD DEVELOPMENT FUND - REDFERN PLAYGROUND, BOROUGH OF QUEENS | 2022 | 9300 | 502 | 6009 | 578 | 95 | 0 | 340 | 2278 | 9802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-218MPNC | MARINE PARK- SALT MARSH CTR B057-115M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-0506 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BROOKLYN | MARINE PARK- SALT MARSH CTR | 2022 | 777 | 1870.33 | 444 | 0 | 0 | 0 | 0 | 0 | 2314.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400LNCP | Challenge Playground R/C Q346-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 411 | P-Q245 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CHALLENGE PLAYGROUND: UPGRADE PLAYGROUND | CHALLENGE PLAYGROUND: UPGRADE PLAYGROUND | 2022 | 4165 | 2964.06 | 444 | 0 | 0 | 0 | 0 | 0 | 3408.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400QZOO | QUEENS ZOO - AVIARY WALKWAY | ZOOS | 400 | P-Q245 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | QUEENS ZOO RC WOODEN PLATFORMS & RAILINGS Q099- | 2022 | 640 | 373.55 | 0 | 0 | 0 | 266 | 0 | 0 | 639.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400SITE | EDERLE SITE Q099-599/899 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-Q001 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | FLUSHING MEADOW PARK | RECON | 2022 | 13078 | 13043.13 | 35 | 0 | 0 | 0 | 0 | 0 | 13078.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO17 | Queens Zoo - Aviary Mesh Replacement | ZOOS | 400 | P-D019 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | QUEENS ZOO | 2022 | 400 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO18 | Wildlife Conservation Society Farm Fence | ZOOS | 400 | P-D019 P-0887 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WILDLIFE CONSERVATION SOCIETY FARM FENCE AND SHED REPLACEMENT | 2022 | 600 | 597.72 | 0 | 0 | 0 | 256 | 0 | 0 | 853.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO20 | Queens Zoo - Concessions Roof Replacement | ZOOS | 400 | P-0887 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | QUEENS ZOO - CONCESSIONS ROOF REPLACEMENT | QUEENS ZOO - CONCESSIONS ROOF REPLACEMENT | 2022 | 540 | 0 | 0 | 0 | 0 | 540 | 0 | 0 | 540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO22 | Queens Zoo - Bear ExhibitGuest Railing/Bench replacement | ZOOS | 400 | P-0887 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | QUEENS ZOO - BEAR EXHIBITGUEST RAILING/BENCH REPLACEMENT | QUEENS ZOO - BEAR EXHIBITGUEST RAILING/BENCH REPLACEMENT | 2022 | 83 | 0 | 0 | 0 | 0 | 83 | 0 | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZO23 | Queens Zoo - sh/Eagle Boardwalk/Dance Floor Replacement | ZOOS | 400 | P-0887 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | QUEENS ZOO - SH/EAGLE BOARDWALK/DANCE FLOOR REPLACEMENT | QUEENS ZOO - SH/EAGLE BOARDWALK/DANCE FLOOR REPLACEMENT | 2022 | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZOO4 | Queens Zoo - Admnistration Building - roof replacement | ZOOS | 400 | P-0887 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | QUEENS ZOO | REPLACEMENT OF THE ROOF AT THE QUEENS ZOO ADMINISTRATION BUILDING | 2022 | 110 | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-400ZOO8 | Queens Zoo - Education Classroom initiative | ZOOS | 400 | P-D019 P-0887 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | QUEENS ZOO | QUEENS ZOO EDUCATION CLASSROOM INITIATIVE -DESIGN | 2022 | 4308 | 381.69 | 91 | 0 | 0 | 4446 | 0 | 0 | 4918.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401APFS | Astoria Pool Filtration System | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0990 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | ASTORIA POOL FILTRATION SYSTEM | ASTORIA POOL FILTRATION SYSTEM | 2022 | 18262 | 1428.34 | 0 | 0 | 8836 | 0 | 8835 | 0 | 19099.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401DKHR | DUTCH KILLS UPGRADE OF THE HOCKEY RINK | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 |  |  | DUTCH KILLS PLAYGROUND--UPGRADE THE HOCKEY RINK. | 2022 | 3900 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401HCSW | Hallets Cove Seawall Q226-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0245Q P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HALLETS COVE SEAWALL | 2022 | 3491 | 4655.11 | 500 | 0 | 0 | 1800 | 0 | 0 | 6955.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401JOEM | Joe Michael's Mile Path and Lighting Q135-214M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 411 | P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | JOE MICHAELS MILE PATHS AND LIGHTING | 2022 | 2040 | 1551.99 | 0 | 0 | 0 | 303 | 0 | 0 | 1854.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401QBHB | Queensbridge Baby Park Handball Courts Q104-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | QUEENSBRIDGE BABY PARK UPGRADE 6 HANDBALL COURT WALLS, BOROUGH OF QUEENS | 2022 | 1422 | 182 | 1025 | 93 | 0 | 0 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401QSE2 | QUEENSBRIDGE PARK FIELDHOUSE CONS. Q104-114M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 401 | P-0245Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DEMOLISH OLD C/S AND CONSTRUCT NEW STATION/FIELDHOUSE | 2022 | 2954 | 6217.04 | 0 | 0 | 0 | 787 | 0 | 0 | 7004.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401RAV2 | Ravenswood Playground R/C Q333-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 P-0935 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RAVENSWOOD PLAYGROUND AND PLAY AREA IMPROVEMENTS | 2022 | 2760 | 6503.67 | 4 | 261 | 0 | 693 | 0 | 0 | 7461.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SHOR | Ralph Demarco Park Shoreline Reconstruction Q004-213M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0245Q |  |  | RALPH DEMARCO PARK SHORELINE RECONSTRUCTION | 2022 | 76 | 0 | 0 | 76 | 0 | 0 | 0 | 0 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SMST | St. Michael's Playground Synthetic Turf Field R/C Q174A-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 401 | P-0510 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ST. MICHAEL'S PLAYGROUND SYNTHETIC TURF FIELD RECONSTRUCTION, BOROUGHOF QUEENS | 2022 | 5825 | 556.04 | 0 | 0 | 4882 | 0 | 0 | 0 | 5438.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SOC2 | Socrates Sculpture Park Building Expansion Q465-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 401 | P-Q245 P-D019 P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SOCRATES SCULPTURE PARK BUILDING EXPANSION | 2022 | 720 | 282 | 4735 | 0 | 0 | 0 | 0 | 0 | 5017 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SOC3 | SOCRATES SCULPTURE PARK -REPAIR TO SEAWALL | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SOCRATES SCULPTURE PARK -REPAIR TO SEAWALL | 2022 | 750 | 68 | 0 | 682 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401SOGP | SIXTEEN OAKS GROVE PK RENO | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | SIXTEEN OAKS GROVE PARK RENOVATION -- FUNDING TO RENOVATE SIXTEEN OAKS GROVE PARK | 2022 | 164 | 0 | 0 | 0 | 0 | 0 | 126 | 0 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401TBDR | Triborough Bridge Plgd C Dog Run & Bball Court Q066-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 401 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCTION/RENOVATION OF DOG RUN AND RECONSTRUCTION OF A BASKETBALLCOURT INTRIBOROUGH BRIDGE PLAYGROUND C | 2022 | 1000 | 1284.54 | 92 | 0 | 0 | 0 | 0 | 0 | 1376.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401WFF | Whitey Ford Field | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | PU-0200 P-0501 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WHITEY FORD FIELD | 2022 | 1054 | 96 | 0 | 0 | 718 | 0 | 244 | 0 | 1058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-401WFF1 | WHITEY FORD FIELD: R/C OF BASEBALL FIELD Q215-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 401 | P-0245Q P-D019 |  | WHITEY FORD FIELD: RECONSTRUCTION OF BASEBALL FIELD | WHITEY FORD FIELD: RECONSTRUCTION OF BASEBALL FIELD | 2022 | 3228 | 2731.69 | 726 | 213 | 0 | 0 | 0 | 0 | 3670.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402DBOY | Doughboy Plaza Park Seating Area R/C Q031A-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION OF THE SEATING AREA ADJACENT TO DOUGHBOY MONUMENT, AT DOUGHBOY PLAZA PARK, BOROUGH OF QUEENS | 2022 | 1996 | 2307.95 | 38 | 0 | 0 | 133 | 0 | 0 | 2478.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402HART | Hart Playground R/C Q067-117MA | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 407 | P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HART PLGD PLAY EQUIPMENT AND SPRAY SHOWER | 2022 | 600 | 3636.12 | 0 | 0 | 0 | 188 | 0 | 0 | 3824.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-402SOHN | Carl R. Sohncke Square Renovations with Flagpole Q057-120M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 402 | P-D019 P-Q245 |  | ROOSEVELT, WOODSIDE AVENUES, 58TH STREET | CARL R. SOHNCKE SQUARE RENOVATIONS INCLUDING ADDING A FLAGPOLE BASE AND FLAGPOLE, BOROUGH OF QUEENS | 2022 | 3410 | 330 | 30 | 0 | 2220 | 0 | 0 | 0 | 2580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403GOR2 | Gorman Playground Upgrades-Q085-120M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | GORMAN PLAYGROUND UPGRADES, BOROUGH OF QUEENS | 2022 | 4900 | 385 | 0 | 4600 | 0 | 0 | 0 | 0 | 4985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403GORP | Gorman Park Improvements | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GORMAN PARK IMPROVEMENT | 2022 | 1800 | 75 | 0 | 0 | 0 | 0 | 1150 | 0 | 1225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403NORT | Northern Playground Synthetic Field Upgrade Q363-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | UPGRADE AND RENOVATE SYNTHETIC FIELD AT NORTHERN PLAYGROUND | 2022 | 2328 | 1608.97 | 0 | 0 | 0 | 410 | 0 | 0 | 2018.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403TPP4 | Travers Park and Staunton Play Field R/C QG-714M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 403 | HW-1684 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | QUEENS | MULTI USE ASPHALT PLAY FIELD RC AND REDESIGN. | 2022 | 3664 | 7925.93 | 496 | 0 | 0 | 0 | 0 | 0 | 8421.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-403TTOT | Travers Park Tot Lot R/C Q303-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION OF TRAVERS PARK TOT LOT | 2022 | 2000 | 2394.9 | 0 | 0 | 0 | 219 | 0 | 0 | 2613.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404ATRI | AMERICAN TRIANGLE RECON | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | DPR AMERICAN TRIANGLE -- RECONSTRUCTION | 2022 | 976 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404CCPS | Moore Homestead Playground R/C Q361-115M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 404 | P-D019 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | C.C, MOORE PLGD & PRE-SCHOOL RC | 2022 | 2160 | 5769.84 | 0 | 0 | 0 | 206 | 0 | 0 | 5975.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404CROW | Crowley Playground R/C Q360J-121M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 404 | P-Q245 P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CROWLEY PLAYGROUND RECONSTRUCTION | 2022 | 300 | 93.8 | 0 | 0 | 1931 | 1820 | 0 | 0 | 3844.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404GSPS | GRAND SLOPE PK STAIRCASE RECON | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | GRAND SLOPE PARK -- STAIRCASE RECONSTRUCTION | 2022 | 390 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404HOPK | CPI - HOFFMAN PK CONS OF MULTI PLAY AREA | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 P-0245Q P-1018 |  | HOFFMAN DR. BET. 58 AVE. AND WOODHAVEN BLVD. QUEENS | HOFFMAN PARK -- CONSTRUCTION OF MULTI-PLAY PURPOSE AREA. | 2022 | 8800 | 0 | 0 | 0 | 3600 | 4600 | 0 | 0 | 8200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404JCPI | Josephine Caminiti Playground Improvements Q046-121M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | JOSEPHINE CAMINITI PLAYGROUND | 2022 | 3225 | 1.48 | 397 | 0 | 3110 | 890 | 2603 | 0 | 7001.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404LIND | LINDEN PK RENOVATIONS | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | LINDEN PARK RENOVATION -- BASKETBALL COURTS, LIGHTING AND ENTRANCES | 2022 | 6500 | 0 | 273 | 0 | 2237 | 2490 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404PATF | Park of the Americas Renovation- Q026-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PARK OF THE AMERICAS (LINDEN PARK) RENOVATION, BOROUGH OF QUEENS | 2022 | 1200 | 164 | 711 | 0 | 489 | 0 | 0 | 0 | 1364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404PKAM | PARK OF THE AMERICAS BATHROOM IMPROVEMENTS RC Q026 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PARK OF THE AMERICAS BATHROOM IMPROVEMENTS RC | 2022 | 500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404WFMP | William F. Moore Park Renovation Q029-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WILLIAM F. MOORE PARK RENOVATION OF PARK, BOROUGH OF QUEENS | 2022 | 700 | 100.62 | 0 | 0 | 0 | 400 | 0 | 0 | 500.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-404WMPG | William F Moore Park RECONSTRUCTION | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 P-D019 |  |  | WILLIAM F MOORE PARK RECONSTRUCTION | 2022 | 2200 | 0 | 284 | 0 | 1845 | 2121 | 0 | 0 | 4250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405BENN | BENNINGER PK PLGD RENO | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | BENNINGER PARK RENOVATE PLAYGROUND: NEW PLAY EQUIP & SAFETY SURFACE -- BENNINGER PARK RENOVATE PLAYGROUND W/NEW PLAY EQUIPMENT & SAFETY SURFACE | 2022 | 5200 | 0 | 282 | 0 | 1728 | 1990 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405EVE2 | Evergreen Park R/C Phase II Q302-121M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 405 | P-D019 P-0938 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PHASE II OF THE RECONSTRUCTION OF EVERGREEN PARK, BOROUGH OF QUEENS | 2022 | 2100 | 212.5 | 467 | 399 | 1601 | 1600 | 500 | 0 | 4779.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405HIDR | HIGHLAND PARK DOG RUN | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | HIGHLAND PARK (QN) -- DOG RUN | 2022 | 1300 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405HPRR | Highland Park Ridgewood Reservoir Site Restoration | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0896 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SITE RESTORATION AND IMPROVEMENTS AT THE RIDGEWOOD RESERVOIR IN HIGHLAND PARK | 2022 | 4771 | 99.97 | 0 | 0 | 0 | 1219 | 0 | 0 | 1318.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JPSS | Juniper Valley Park Spray Shower R/C Q102-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 405 | P-Q245 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | JUNIPER VALLEY PARK: UPGRADES TO SPRAY SHOWERS | 2022 | 2000 | 1674.81 | 453 | 232 | 0 | 0 | 0 | 0 | 2359.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JPTK | Juniper Valley Park Track & Syn. Turf Field R/C Q102-118M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | JUNIPER VALLEY PARK TRACK | 2022 | 2500 | 4534.04 | 1191 | 0 | 0 | 0 | 0 | 0 | 5725.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405JVBB | Juniper Valley Park Baseball Fields | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | JUNIPER VALLEY PARK BASEBALL FIELDS, BOROUGH OF QUEENS | 2022 | 2864 | 99.99 | 0 | 0 | 0 | 0 | 4250 | 0 | 4349.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405ROSP | ROSEMARY PLGD RENO BBALL COURT & ASPHALT AREA | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | ROSEMARY'S PLAYGROUND: LARGE ASPHALT MPPA AREA, BASKETBALL COURTS -- ROSEMARY'S PLAYGROUND RENOVATE LARGE ASPHALT MPPA AREA; UPGRADE BASKETBALL COURTS | 2022 | 9100 | 0 | 0 | 0 | 0 | 0 | 7000 | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405RRGH | Ridgewood Reservoir Gatehouse Rehab Q020-318M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0896 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GATEHOUSE REHAB AT RIDGEWOOD RESERVOIR, IN HIGHLAND PARK, BOROUGH OF QUEENS | 2022 | 7228 | 230 | 2200 | 0 | 3100 | 0 | 0 | 0 | 5530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405RRIV | Ridgewood Reservoir Invasive Removals -Q020-518M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0896 |  |  | INVASIVE REMOVALS AT RIDGEWOOD RESERVOIR, IN HIGHLAND PARK, BOROUGH OF QUEENS | 2022 | 3250 | 443.9 | 0 | 2966 | 0 | 0 | 0 | 0 | 3409.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405STR2 | Starr Playground R/C Phase II Q291-120M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 405 | P-D019 P-0245Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PHASE II OF THE RECONSTRUCTION OF STARR PLAYGROUND, BOROUGH OF QUEENS | 2022 | 1000 | 300 | 2115 | 0 | 185 | 0 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-405STRR | Starr Playground MPPA R/C Q291-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STARR PLAYGROUND - UPGRADES | 2022 | 2500 | 1520.16 | 21 | 336 | 0 | 786 | 0 | 0 | 2663.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406HHPR | HORACE HARDING PLGD RENOVATIONS Q428-121M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | HORACE HARDING PLGD RENOVATIONS | 2022 | 3200 | 200 | 0 | 0 | 1600 | 1400 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406LBAT | LOST BATTALION HALL RECR CTR - PHASE I & PHASE IV | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 400 | P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | QUEENS BLVD BETWEEN 62ND AVENUE AND 62ND ROAD IN REGO PARK, QUEENS | PHASE I - ADA COMPLIANCY AND HVAC WORK, PHASE IV - UPGRADE LIGHTS ANDELECTRICAL SYSTEMS IN GYMNASIUM | 2022 | 500 | 657.07 | 77 | 0 | 0 | 0 | 0 | 0 | 734.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406PG62 | Playground Sixty Two R/C Q377-120M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 406 | P-Q245 P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PLAYGROUND SIXTY TWO | 2022 | 504 | 209.5 | 0 | 0 | 2100 | 1560 | 0 | 0 | 3869.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-406YPFN | Yellowstone Park Fencing Pt. 1 R/C 68th Avenue Q425-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 406 | P-D019 |  |  | RECONSTRUCTION OF FENCING AT YELLOWSTONE PARK, BOROUGH OF QUEENS | 2022 | 550 | 75 | 0 | 550 | 0 | 0 | 0 | 0 | 625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BBSF | COLLEGE PT FIELDS CONVERT BASEBALL TO SOCCER FIELD | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 |  |  | COLLEGE POINT FIELDS -- CONVERT BASEBALL TO SOCCER FIELD | 2022 | 5850 | 0 | 655 | 0 | 1605 | 2240 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BLND | Bland Playground Lighting (Q326-120M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ADDITION OF LIGHTING AT BLAND PLAYGROUND | 2022 | 682 | 682.97 | 600 | 4843 | 0 | 0 | 0 | 0 | 6125.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BPFF | BOWNE PK POND R/C Q006-215MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-0245Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BOWNE PK FOUNTAINS AND FILTRATION SYSTEMS UPGRADE | 2022 | 1150 | 2205.09 | 125 | 0 | 0 | 0 | 0 | 0 | 2330.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BTPL | Bay Terrace Playground R/C Q399-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 |  | BAY TERRACE PLAYGROUND, QUEENS | REPAVING OF BASKETBALL AND HANDBALL COURTS | 2022 | 1033 | 3202.14 | 207 | 0 | 0 | 0 | 0 | 0 | 3409.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407BWPK | Bowne Park Bocce Court Renovations | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | BOWNE PARK UPGRADE PLAZA ADJACENT TO BOCCE AREA, PROVIDE PASSING SITTING AREA, DECORATIVE ELEMENTS, AND ENHANCED PLANTINGS, BOROUGH OF QUEENS | 2022 | 1272 | 143 | 454 | 661 | 0 | 0 | 0 | 0 | 1258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407CPSC | College Point Fields Cons. of a Football Field Q476-117M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 407 | P-0935 P-D019 P-0245Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCT NEW SYSTHETIC FOOTBALL FIELD, MONDO RUNNING TRACK, PARKING AREA, LIGHTING AND NEW BENCHES AND BEACHES | 2022 | 500 | 6980.87 | 922 | 0 | 0 | 0 | 0 | 0 | 7902.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FGP2 | Frank Golden Pk - R/C of Athletic Fields Phase II Q445-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 407 | P-Q126 P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FRANK GOLDEN PK -SHANNON GAELS | 2022 | 1580 | 5264.04 | 669 | 0 | 0 | 0 | 0 | 0 | 5933.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407FLPT | Francis Lewis Park Pathway & Entrance Way Impts Q126-120M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | FRANCIS LEWIS PARK PATHWAY AND ENTRANCE WAY REPAVING AND IMPROVEMENTS, BOROUGH OF QUEENS | 2022 | 2000 | 250 | 0 | 996 | 1004 | 0 | 0 | 0 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MAPL | Maple Playground R/C Q211-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 407 | P-Q245 P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INSTALL NEW EQUIPMENT, ENTRANCE PAVEMENT, AND SEATING IN MAPLE PLAYGROUND | 2022 | 1200 | 678.57 | 0 | 3985 | 2059 | 0 | 0 | 0 | 6722.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MCN4 | Herman MacNeil Park Entrance and Pathways | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 407 | P-1018 |  |  | IMPOVEMENTS TO THE HERMAN MACNEIL PARK, INCLUDING THE ENTRANCE AND PATHWAYS, BOROUGH OF QUEENS | 2022 | 575 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 575 | 0 | 0 | 0 | 0 | 575
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407MNPW | MACNEIL PARK WATERFRONT REPAIRS | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 P-Q245 |  |  | MACNEIL PARK WATERFRONT REPAIRS | 2022 | 5200 | 0 | 695 | 0 | 2150 | 2750 | 0 | 0 | 5595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407PWLL | Powells Cove Park - Restoration | LAND ACQUISITION AND TREE PLANTING | 400 407 | P-D019 P-Q245 P-0245Q |  | BOUROUGH OF QUEENS, - 11TH AVENUE BETWEEN 130 STREET AND POWELLS COVEBLVD & 138 PLACE AND 9TH AVENUE. | POWELLS COVE PARK RESTORATION | 2022 | 1600 | 0 | 0 | 0 | 810 | 800 | 0 | 0 | 1610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407VELO | KISENNA VALLEY PK RC VELODROME | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 P-0087 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | KISENNA VALLEY PK RC VELODROME | KISENNA VALLEY PK RC VELODROME | 2022 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 2000 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-407WBPK | WEEPING BEECH PK RENO MULTI PLAY AREA, BBALL COURTS | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0245Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WEEPING BEECH PARK -- RENOVATION OF THE MULTI-PURPOSE PLAY AREA, BASKETBALL COURT AREA, AND PLAYGROUND AREA. | 2022 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CPBF | CUNNINGHAM PARK BALLFIELDS (#1 & #5) Q021-108M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 408 | P-Q245 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | QUEENS | RC CORE BALL FIELDS TO INCLUDE SYNTHETIC COMPLEX, MUTI-USE SYTHETIC FOOTBALL/SOCCER FIELD, AND PROVISIONS FOR EASIER ACCESS FOR LARGE SCALEEVENTS | 2022 | 1000 | 1137.05 | 71 | 0 | 0 | 0 | 0 | 0 | 1208.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408CPGA | Cunningham Park Garage Space Conversion Q021-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0704 P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CONVERT A PORTION OF CUNNINGHAM PARK GARAGE SPACE INTO A HUB SPACE FOR MNO STAFF | 2022 | 5670 | 2147.89 | 0 | 0 | 9750 | 11510 | 0 | 0 | 23407.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408HOV2 | Hoover Playground Q220G-121M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 408 | P-D019 P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HOOVER PLAYGROUND | 2022 | 960 | 200 | 44 | 0 | 2300 | 2048 | 0 | 0 | 4592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408MLDY | Site for Mother Language Day in Captain Tilly Park | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COMMEMORATIVE SITE FOR MOTHER LANGUAGE DAY IN CAPTAIN TILLY PARK | 2022 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408VAN2 | Vanderbilt Motor Parkway Repaving Phase II QG-719M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-0245Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PHSE II OF THE REPAVING OF VANDERBILT MOTOR PARKWAY, LOCATED IN CUNNINGHAM PARK, BOROUGH OF QUEENS | 2022 | 4000 | 500 | 2367 | 0 | 1318 | 0 | 0 | 0 | 4185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-408VAND | Vanderbilt Motor Parkway Repaving QG-718M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 P-0245Q |  |  | REPAVING OF VANDERBILT MOTOR PARKWAY, LOCATED IN CUNNINGHAM PARK | 2022 | 1664 | 1587.16 | 678 | 0 | 0 | 0 | 0 | 0 | 2265.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409DEMO | Forest Park Towers Demolition | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 |  |  | FOREST PARK TOWERS DEMOLITION | 2022 | 1300 | 101 | 542 | 0 | 0 | 458 | 0 | 0 | 1101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409EQTY | Equity Park Playground Upgrades | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PLAYGROUND EQUIPMENT UPGRADE AT EQUITY PARK | 2022 | 682 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPAP | Forest Park Asphalt Pathways Improvements | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 |  |  | FOREST PARK ASPHALT PATHWAYS IMPROVEMENTS | 2022 | 755 | 0 | 0 | 3186 | 0 | 0 | 0 | 0 | 3186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPG3 | FOREST PARK GREENHOUSES Q015-117MA1 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 405 406 409 | P-Q245 P-D019 P-0245Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FOREST PARK GREENHOUSES Q015 | 2022 | 1000 | 319.82 | 0 | 0 | 1841 | 0 | 0 | 0 | 2160.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409FPP2 | Forest Park Pathways | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 409 | P-D019 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FOREST PARK PATHWAYS | 2022 | 600 | 113 | 455 | 0 | 45 | 0 | 0 | 0 | 613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-409MARD | Glendale Entrance to Forest Park Q015-217MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 P-0245Q P-1018 P-Q771 P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MYRTLE AVENUE ROAD IN FOREST PARK | 2022 | 1100 | 423.08 | 3674 | 0 | 0 | 0 | 0 | 0 | 4097.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410ALST | Al Stabile Playground Renovation Q285-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | AL STABILE PLAYGROUND RENOVATION, BOROUGH OF QUEENS | 2022 | 1988 | 179 | 1242 | 0 | 508 | 0 | 0 | 0 | 1929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410BYRN | Edward Byrne Park Playground C/S X092-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCTION OF A COMFORT STATION AT EDWARD BYRNE PARK PLAYGROUND | 2022 | 3537 | 315.41 | 0 | 2088 | 870 | 0 | 0 | 0 | 3273.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410PEBP | Recon of Police Officer Edward O'Byrne Park Q092-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0245Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | POLICE OFFICER EDWARD O'BYRNE PARK - QUEENS | 2022 | 2650 | 100 | 1687 | 250 | 713 | 0 | 0 | 0 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-410SCN2 | Harold Schneiderman Playground Upgrades Q408-121M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | UPGRADE PLAY EQUIPMENT AT HAROLD SCHNEIDERMAN PLAYGROUND | 2022 | 1022 | 120 | 27 | 0 | 1250 | 2223 | 0 | 0 | 3620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411APE2 | ALLEY POND ENVIRONMENTAL CENTER & CONS. OF ANNEX Q001-110M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 411 | P-Q002 P-0506 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CONSTRUCTION OF AN ANNEX AND RC OF APEC | 2022 | 1060 | 25659.93 | 3069 | 0 | 0 | 0 | 0 | 0 | 28728.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411APNA | Alley Pond Park Natural Areas Restoration Phase 3 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-1245 |  | BOROUGH OF QUEENS | ALLLEY POND PARK NATURAL AREAS RESTORATION PHASE 3 | 2022 | 1609 | 0 | 0 | 0 | 809 | 800 | 0 | 0 | 1609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411CDTR | Captain Dermody Triangle- Reconstruction of the triangle | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 |  | 216 ST., 48 AVE. QUEENS | RECONSTRUCTION OF CAPTAIN DERMODY TRIANGLE | 2022 | 500 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-411OKPT | Oakland Lake Pathways Reconstruction Q001-120M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 P-Q245 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | ALLEY POND PARK | OAKLAND LAKE PATHWAYS RECONSTRUCTION | 2022 | 106 | 89.5 | 0 | 0 | 412 | 0 | 0 | 0 | 501.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412BAI2 | Baisley Pond Park Track & Field, Syn. Turf R/C Q005-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0245Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BAISLEY POND PARK - QUEENS | 2022 | 10275 | 858.42 | 0 | 4267 | 0 | 4900 | 0 | 0 | 10025.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412BPP4 | Athletic Courts Multi-Site QG-216M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 P-1018 P-Q708 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BAISLEY POND PK ATHLETIC CTS | 2022 | 1000 | 2117.96 | -245 | 0 | 0 | 484 | 0 | 0 | 2356.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412DKWP | Detective Keith L Williams Park (Liberty) Basketball Cts | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0245Q |  |  | DETECTIVE KEITH L WILLIAMS PARK (LIBERTY PARK) RENOVATE TWO BASKETBALL COURTS, BOROUGH OF QUEENS | 2022 | 700 | 105 | 0 | 0 | 700 | 0 | 0 | 0 | 805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412DOP3 | Daniel M. O'Connell Playground Renovation Q106-120M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 P-0245Q |  |  | DANIEL M. O'CONNELL PLAYGROUND FULL RENOVATION, BOROUGH OF QUEENS | 2022 | 4500 | 571.53 | 0 | 0 | 760 | 3318 | 0 | 0 | 4649.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412HVDP | HOWARD VON DOHLEN PLAYGROUND-RENOVATIONS Q105-112M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 409 | P-Q245 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | QUEENS | HOWARD VON DOHLEN PLAYGROUND-RENOVATIONS Q105 | 2022 | 1927 | 1508.12 | 62 | 0 | 0 | 0 | 0 | 0 | 1570.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412JAMP | Jamaica Playground -- Renovate MPPA Q301-121M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | JAMAICA PLAYGROUND -- RENOVATE MPPA | 2022 | 5280 | 25 | 189 | 0 | 2311 | 2300 | 0 | 0 | 4825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412JMIC | Jamaica Playground R/C Q301-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0245Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | JAMAICA PLAYGROUND - QUEENS | 2022 | 4650 | 574.81 | 3281 | 0 | 1191 | 0 | 0 | 0 | 5046.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412KLWP | Det. Keith Williams Pk--Reno The Synthetic Turf Q121-121M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 P-Q245 P-0245Q |  |  | DETECTIVE KEITH WILLIAMS PARK--RENOVATE THE SYNTHETIC TURF FIELD AND MONDO TRACK | 2022 | 20615 | 200 | 0 | 0 | 8695 | 2000 | 1217 | 5000 | 17112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412MBPF | Montebellier Park Field - Playing Field Upgrades | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MONTEBELLIER PARK FIELD - PLAYING FIELD UPGRADES | 2022 | 550 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412NAUT | Nautilus Playground R/C Q448-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 412 | P-D019 P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NAUTILUS PLAYGROUND | 2022 | 600 | 496.7 | 4300 | 0 | 1391 | 0 | 0 | 0 | 6187.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412NOR2 | Norelli-Hargreaves Playground MPPA R/C Q220B-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NORELLI HARGREAVES PLAYGROUND - RENOVATION TO BASKETBALL COURTS AND MULTI PURPOSE PLAY AREA | 2022 | 3326 | 2044.69 | 0 | 0 | 0 | 960 | 0 | 0 | 3004.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RCON | RAYMOND O'CONNOR PK PATHWAY & SOCCER RENO | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | RAYMOND O'CONNOR PARK -- PATHWAY REPAVINGS AND SOCCER FIELD RENOVATIONS | 2022 | 3576 | 0 | 0 | 0 | 2750 | 0 | 0 | 0 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RKM2 | RUFUS KING MANOR MUSEUM -HVAC Q23-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 412 | P-D019 P-0245Q P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RUFUS KING MANOR MUSEUM | 2022 | 400 | 799.58 | 0 | 160 | 0 | 0 | 0 | 0 | 959.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RKPP | RUFUS KING PARK RENO OF PLGD | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 P-0506 |  |  | RUFUS KING PARK -- RENOVATE PLAYGROUND AREA | 2022 | 5526 | 0 | 75 | 0 | 3733 | 2942 | 0 | 0 | 6750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWFA | Roy Wilkens Rec. Center: Fire Alarm Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 412 | P-0506 |  | 177TH STREET & BAISLEY BOULEVARD, JAMAICA, NY 11434, QUEENS. | FIRE ALARM RECONSTRUCTION AT ROY WILKENS REC CENTER. | 2022 | 768 | 0 | 0 | 1042 | 0 | 0 | 0 | 0 | 1042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWIL | ROY WILKINS REC CTR ROOF & SITE Q448-112M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 412 | P-0245Q P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | QUEENS | RC ROOF ROY WILKINS REC CTR, ROOFTOP GYM AC, SITE /GARDEN DRAINAGE | 2022 | 4318 | 5461.86 | -48 | 0 | 0 | 1099 | 0 | 0 | 6512.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWP3 | ROY WILKINS PARK RECREATION CTR RC Q448-115M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 412 | P-Q245 P-0506 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROY WILKINS PARK RECREATION CTR | 2022 | 1440 | 1826.4 | 37 | 374 | 0 | 792 | 0 | 0 | 3029.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412RWR1 | Roy Wilkins Recreation Center | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0506 |  |  | ROY WILKINS RECREATION CENTER | 2022 | 92000 | 0 | 0 | 9200 | 0 | 0 | 82800 | 0 | 92000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-412SRPC | SOUTH ROCHDALE PLGD- RENO OF PLGD & CS | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | SOUTH ROCHDALE PLGD- RENO OF PLGD & CS | 2022 | 3200 | 0 | 500 | 0 | 3855 | 1495 | 2850 | 0 | 8700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRO4 | Brookville Park Dog Run | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BROOKVILLE PARK DOG RUN, BOROUGH OF QUEENS | 2022 | 2000 | 0 | 0 | 0 | 0 | 1100 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BROK | BROOKVILLE PARK RENO PATHS & BRIDGES | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | BROOKVILLE PARK -- RENOVATE THE PATHS, POND EDGES & BRIDGES | 2022 | 780 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413BRSY | Brookville Park Synthetic Turf Field R/C Q008-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 413 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BROOKVILLE PARK SYNTHETIC TURF FIELD RECONSTRUCTION, BOROUGH OF QUEENS | 2022 | 3837 | 246.52 | 2124 | 0 | 809 | 0 | 0 | 0 | 3179.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413CAMB | CAMBRIA PLGD RECONSTRUCTION Q339-121M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 P-D019 |  |  | CAMBRIA PLAYGROUND/CABBELL PARK--PLAYGROUND RECONSTRUCTION | 2022 | 4211 | 50 | 0 | 0 | 2000 | 2011 | 0 | 0 | 4061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413CAST | Castlewood Playground - Reconstruction of the MPPA Q327-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CASTLEWOOD PLAYGROUND: RECONSTRUCTION OF MPPA | 2022 | 3700 | 429.3 | 2595 | 165 | 1 | 250 | 0 | 0 | 3440.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413COV2 | Sunset Cove Pk Oyster Garden/Boardwalk Cons. Q498-117M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-Q003 P-Q245 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SUNSET COVE PARK PHASE II - CONSTRUCTION OF AN OFFSHORE EDUCATIONAL OYSTER GARDEN AND BOARDWALK | 2022 | 1000 | 25 | 3199 | 0 | 212 | 0 | 0 | 0 | 3436 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413IDL3 | IDLEWILD PK SITE B Q392-219M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 413 | ED-0075 P-0245Q | PROJECT DELAYED PENDING APPROVAL OF STATE REQ CONTRACT | QUEENS | IDLEWILD PK SITE B | 2022 | 2001 | 75 | 1566 | 214 | 786 | 0 | 0 | 0 | 2641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413IDPK | IDLEWILD PK MARSH NATURE CENTER Q392-210M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 413 | P-1018 P-0245Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | IDLEWILD PK MARSH ENVIRONMENTAL CENTER Q392 | 2022 | 100 | 8661.99 | 41 | 0 | 0 | 384 | 0 | 0 | 9086.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413JH72 | VIC HANSON/JHS 72 PLGD RC Q352 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 413 | P-Q245 P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | VIC HANSON/JHS 72 PLGD RC Q352 | 2022 | 420 | 0 | 0 | 0 | 1700 | 1650 | 0 | 0 | 3350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413LPCT | Laurelton Playground BBall and Handball Courts Q108-120M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | LAURELTON PLAYGROUND PHASE 2 (BASKETBALL AND HANDBALL COURTS), BOROUGH OF QUEENS | 2022 | 2000 | 100 | 34 | 0 | 1976 | 1990 | 0 | 0 | 4100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413LPL2 | Laurelton Playground RC Q027-110M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 413 | P-Q245 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BROOKVILLE BLVD BETWEEN 136 AND 137 AVENUES | INSTALLATION OF NEW TOT PLAYGROUND, SPRAY SHOWER, BENCHES, NEW LANDSCAPING | 2022 | 1500 | 1766.59 | 36 | 0 | 0 | 0 | 0 | 0 | 1802.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413QCFM | QNS FMHSE-RENOV ED BLDG,GRNHSE & ADRIANCE FMHSE Q453-102MA | VEHICLES AND EQUIPMENT | 413 | P-Q010 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | QNS COUNTY | RENOV ED BLDG, GREENHOUSE COMPLEX, & ADRIANCE FARMHOUSE | 2022 | 482 | 390.02 | 0 | 47 | 0 | 0 | 0 | 0 | 437.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413READ | Bellerose Playground (PS 133) Creation of Reading Garden | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CREATION OF A READING GARDEN AT PS 133 (BELLEROSE PLAYGROUND), BOROUGH OF QUEENS | 2022 | 250 | 54 | 0 | 0 | 20 | 0 | 0 | 0 | 74 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 250
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413SPBD | Springfield Park Basketball Courts and BBQ Area Q107-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0245Q P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SPRINGFIELD PARK BASKETBALL COURTS AND BBQ, BOROUGH OF QUEENS | 2022 | 4200 | 449.11 | 5 | 1272 | 1944 | 0 | 0 | 0 | 3670.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-413WGPF | WILLIAM GUNN PLAYGROUND EXPANSION | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 413 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EXPAND MPPA MULTI USE YARD INTO STREET BED AS PER YESHIVA AGREEMENT ADD FENCING AND LANDSCAPING | 2022 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-41417PG | BROAD CHANNEL 17TH STREET PLAYGROUND Q460-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 414 | P-Q245 |  | BROAD CHANNEL 17TH STREET PLAYGROUND: RENOVATE ENTRY PLAZA | BROAD CHANNEL 17TH STREET PLAYGROUND: RENOVATE ENTRY PLAZA | 2022 | 2678 | 2525.37 | 43 | 0 | 0 | 0 | 0 | 0 | 2568.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414B108 | Beach 108th Esplanade Improvements Q496-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0581 |  |  | IMPROVEMENTS TO THE HARBOR PARK ESPLANADE ALONG BEACH CHANNEL DRIVE, AT BEACH 108TH STREET, BOROUGH OF QUEENS | 2022 | 2276 | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 205.6 | 1463 | 0 | 0 | 0 | 0 | 0 | 1668.6
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414B9TH | Beach 9th Street Basketball Courts | BEACHES AND BOARDWALKS | 400 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BEACH 9TH STREET RENOVATION OF BASKETBALL COURTS, AT ROCKAWAY BEACH AND BOARDWALK, BOROUGH OF QUEENS | 2022 | 400 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BAY6 | Michaelis-Bayswater Park Reconstruction Q007-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 414 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION OF BAYSWATER PARK, BOROUGH OF QUEENS | 2022 | 4280 | 274.5 | 0 | 0 | 0 | 258 | 3672 | 0 | 4204.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BAY9 | Michaelis-Bayswater Park Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  | DWIGHT AVE., SEAGIRT BLVD. BET. BEACH 38 ST. AND BAY 32 ST. | MICHAELIS-BAYSWATER PARK RECONSTRUCTION | 2022 | 80 | 0 | 0 | 0 | 888 | 0 | 0 | 0 | 888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BAYS | BAYSWATER-MICHAELIS PK-W0 B/F'S INCL IRRIG Q007-102M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 414 | P-Q245 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BEACH CHANEL DRIVE, B. 32ND ST | RECON 2 B/F'S | 2022 | 960 | 880.46 | 66 | 0 | 0 | 0 | 0 | 0 | 946.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BC88 | Beach 88th Street Park Construction Q499-118M | BEACHES AND BOARDWALKS | 400 | P-1018 P-D019 P-D020 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCTION OF A PARK ON BEACH 88TH STREET, BOROUGH OF QUEENS | 2022 | 200 | 18.96 | 0 | 0 | 635 | 0 | 0 | 0 | 653.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414BCAP | Broad Channel American Park Q467-120M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 414 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BROAD CHANNEL AMERICAN PARK | 2022 | 312 | 146.1 | 0 | 0 | 1500 | 1475 | 0 | 0 | 3121.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414C03B | BROAD CHANNEL PK DAY CAMP Q467-199 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 414 | P-Q005 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CROSS BAY BLVD, 207TH AVE, 20TH ROAD, BROAD CHANNEL | CONSTR OF A BALLFLD & RESTORATION OF WETLANDS AND ADJOINING LANDSCAPEIN BROAD CHANNEL PARK --- SCOPE OF WORK TO INCLUDE CONSTR OF AN ASPHALT SOFTBALL FIELD, PORTIONS OF A LOOP TRAIL, EARTH BERMS, FLAGPOLE, PLANTINGS, RESTORATION OF WETLANDS | 2022 | 1060 | 149.35 | 36 | 0 | 0 | 0 | 0 | 0 | 185.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414LABY | Shorefront Labyrinth and Seating Area Q163-518M | BEACHES AND BOARDWALKS | 400 | P-D019 P-Q003 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CREATION OF A LABYRINTH/YOGA AREA ALONG SHORE FRONT PARKWAY, IN THE VICINITY OF BEACH 90-102 STREETS, BOROUGH OF QUEENS | 2022 | 332 | 21.15 | 267 | 169 | 0 | 0 | 0 | 0 | 457.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414LAN2 | Lannett Playground Sitting Area R/C Q407-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | LANNETT PLAYGROUND | LANNETT PLAYGROUND | 2022 | 250 | 1182.51 | 0 | 0 | 0 | 333 | 0 | 0 | 1515.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414ODON | O'Donohue Park Picnic Grove Construction | BEACHES AND BOARDWALKS | 400 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | O'DONOHUE PARK PICNIC GROVE AND BBQ AREA CONSTRUCTION, AT ROCKAWAY BEACH AND BOARDWALK, BOROUGH OF QUEENS | 2022 | 320 | 0 | 0 | 0 | 0 | 0 | 320 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414RB59 | Beach 59th Street Playground R/C Q162E-118M | BEACHES AND BOARDWALKS | 400 | P-D019 P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BEACH 59 ST PLAYGROUND UPGRADE PK | 2022 | 200 | 518.02 | 3093 | 0 | 1791 | 0 | 0 | 0 | 5402.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-414THUR | Thursby Basin Park Construction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D171 P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCTION OF THURSBY BASIN PARK, AT ROCKAWAY BEACH AND BOARDWALK, IN THE BOROUGH OF QUEENS | 2022 | 583 | 44.61 | 5 | 0 | 533 | 0 | 0 | 0 | 582.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415AQFL | Flushing Mead Cor Aquatic Center Pool Floor Recon Q099-322M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION |  | P-1008 |  | GRAND CENTRAL PKWY, VAN WYCK EXWY QUEENS | FLUSHING MEADOWS CORONA PARK AQUATIC CENTER POOL FLOOR RECON | 2022 | 650 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415AQNT | FMCP Aquatic Center Netting | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-0245Q |  |  | FMCP AQUATIC CENTER NETTING | 2022 | 7954 | 2323.99 | 445 | 0 | 0 | 4681 | 0 | 0 | 7449.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415AQUA | FMCP - Aquatic Center Roof Replacement | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-0245Q P-0013 P-1250 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REPLACEMENT OF ROOF AT THE AQUATIC CENTER, IN FLUSHING MEADOWS CORONAPARK | 2022 | 12056 | 943.23 | 1535 | 0 | 11149 | 0 | 16293 | 0 | 29920.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415CAND | FMCP - Reconstruction of Candela Structures Q099-120M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-0245Q P-D019 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION OF CANDELAS AT FLUSHING MEADOWS CORONA PARK, BOROUGH OF QUEENS | 2022 | 3500 | 538.12 | 90 | 0 | 391 | 0 | 0 | 0 | 1019.12 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 2500
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FMWS | FMCP - Adult Fitness Equipment Installation Q099-318M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 P-0245Q P-1018 |  |  | INSTALLATION OF ADULT FITNESS EQUIPMENT AT FLUSHING MEADOWS CORONA PARK, BOROUGH OF QUEENS | 2022 | 266 | 35.5 | 414 | 0 | 0 | 0 | 0 | 0 | 449.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415FSTF | FMCP - Synthetic Turf Fields 8 & 9 R/C Q099-319M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-0510 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FLUSHING MEADOWS CORONA PARK - RECONSTRUCTION OF SYNTHETIC TURF FIELDS 8 & 9, BOROUGH OF QUEENS | 2022 | 9973 | 688.26 | 0 | 0 | 3460 | 3998 | 0 | 0 | 8146.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415LWCS | FMCP - Lawrence Playground Comfort Station R/C Q099-817MA | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0245Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION OF COMFORT STATION IN LAWRENCE PLAYGROUND, IN FLUSING MEADOWS CORONA PARK | 2022 | 1310 | 1203.94 | 0 | 0 | 0 | 257 | 0 | 0 | 1460.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415MEA2 | FMCP - MEADOW LAKE- PATHS Q099-215M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 403 404 406 407 408 | P-Q245 P-D019 P-0013 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FMCP - MEADOW LAKE- PATHS Q099 | 2022 | 900 | 615.8 | 0 | 3750 | 0 | 0 | 0 | 0 | 4365.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415PAS4 | FMCP-Passerelle Roof | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-0245Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PASSERELLE ROOF, BOROUGH OF QUEENS | 2022 | 21280 | 0 | 0 | 0 | 0 | 0 | 21280 | 0 | 21280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415PAVI | FMCP - NYS PAVILION RC Q099-116M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 403 404 406 407 408 | P-0245Q P-Q001 P-0013 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PERIMETER ROAD AND UNITED NATIONS AVENUE SOUTH | THIS PROJECT WILL RECONSTRUCT PORTIONS OF THE NEW YORK STATE PAVILIONOBSERVATION TOWERS IN FLUSHING MEADOWS CORONA PARK. | 2022 | 150 | 20589.92 | 1794 | 2000 | 0 | 0 | 0 | 0 | 24383.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415WRD2 | FMCP - World's Fair Marina Pier 1 & 3 R/C Q099-218M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-1018 |  |  | RECONSTRUCTION OF PIER 1 & 3 AT WORLD'S FAIR MARINA, IN FLUSHING MEADOWS CORONA PARK | 2022 | 35962 | 2266.46 | 221 | 0 | 0 | 115 | 4164 | 32059 | 38825.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-415WRLD | FMCP - World's Fair Playground Asphalt Field Q099-517M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATE ASPHALT FIELD AT WORLD'S FAIR PLAYGROUND | 2022 | 2400 | 1746.1 | 0 | 0 | 0 | 396 | 0 | 0 | 2142.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ALYPND | Alley Pond Park adventure course path reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 |  | ALLEY POND, QUEENS | ALLEY POND PARK ADVENTURE COURSE PATH RECONSTRUCTION | 2022 | 900 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH01 | Anchor Park Site - Astoria Park (DESIGN ONLY - ALL PHASES) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ANCHOR PARK SITE - ASTORIA PARK | 2022 | 32730 | 3470.27 | 0 | 0 | 0 | 300 | 0 | 0 | 3770.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH03 | Anchor Pk - Astoria Park PH2A: Charybdis Plgd R/C Q004-318M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-0848 |  |  | RECONSTRUCTION OF CHARYBDIS PLAYGROUND AND ASTORIA POOL PLAY AREA, INASTORIA PARK, BOROUGH OF QUEENS | 2022 | 9546 | 12592.25 | 215 | 0 | 0 | 0 | 0 | 0 | 12807.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH04 | Anchor Pk - Astoria Pk PH2B: Charybdis Plgd CS R/C Q004-418M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-0848 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECONSTRUCTION OF THE COMFORT STATION AT CHARYBDIS PLAYGROUND, IN ASTORIA PARK, BOROUGH OF QUEENS | 2022 | 3272 | 1565.32 | 62 | 0 | 0 | 958 | 0 | 0 | 2585.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ANCH05 | Anchor Park - Astoria Park Phase 3 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-0848 P-D019 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ANCHOR PARK - ASTORIA PARK PHASE 3, BOROUGH OF QUEENS | 2022 | 4510 | 100 | 0 | 0 | 1837 | 0 | 2510 | 0 | 4447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BASDCS | Bayside Playground-Reconstruction of Comfort Station | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0505 |  |  | BAYSIDE PLAYGROUND-RECONSTRUCTION OF COMFORT STATION | 2022 | 1645 | 296.96 | 1293 | 0 | 344 | 0 | 0 | 0 | 1933.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BAYMAR | Bayside Marina RC | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 400 | P-1018 P-1245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION OF BAYSIDE MARINA | 2022 | 1849 | 361 | 0 | 0 | 0 | 0 | 3215 | 0 | 3576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BC94S1 | Beach 94th Street Performance Space Cons. Q163-418M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q003 P-D019 P-1018 |  |  | BEACH 94TH STREET PERFORMANCE SPACE - CONSTRUCTION OF A PERFORMANCE SPACE AT SHORE FRONT PARKWAY, IN ROCKAWAY BEACH, BOROUGH OF QUEENS | 2022 | 3326 | 13.34 | 580 | 0 | 0 | 0 | 0 | 0 | 593.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BLISSV | BLISSVILLE VET MEMORIAL FLAGPOLE & UPGRADES | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | BLISSVILLE VET MEMORIAL FLAGPOLE & UPGRADES | 2022 | 650 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BLSPTH | Black Spectrum Theatre -Interior renovations q448-219m | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | BLACK SPECTRUM THEATRE -INTERIOR RENOVATIONS | 2022 | 500 | 56 | 455 | 45 | 0 | 0 | 0 | 0 | 556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BRKVBB | BROOKVILLE PARK TWO BASEBALL FIELD Q008-121M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 P-Q773 |  |  | BROOKVILLE PARK CONSTRUCTION OF TWO BASEBALL FIELDS IN QUEENS | 2022 | 6700 | 194.8 | 0 | 33 | 2817 | 2825 | 0 | 0 | 5869.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BRODCH | Broad Channel American Park Shad Creek Road Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 |  | QUEENS | BROAD CHANNEL AMERICAN PARK SHAD CREEK ROAD RECONSTRUCTION | 2022 | 3088 | 0 | 0 | 0 | 1502 | 1586 | 0 | 0 | 3088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BSHIST | Ft. Totten Bayside Historical Society Officers ClubQ458-116M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 400 407 | P-D019 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS |  | FT. TOTTEN BAYSIDE HISTORICAL SOCIETY OFFICERS CLUBQ458-116M | 2022 | 180 | 467.9 | 0 | 0 | 0 | 229 | 0 | 0 | 696.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEF | QUEENS - MULTI SITE QG-210M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-0245Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RC OF PAVEMENTS, HANDBALL AND TENNIS CTS, ROLLER HOCKEY RINKS, FENCES, PLANTINGS AND GENERAL SITE WORK | 2022 | 1582 | 1345.47 | 0 | 0 | 0 | 0 | 0 | 0 | 1345.47 | 347.91 | 0 | 0 | 0 | 52 | 0 | 0 | 399.91
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEM | QUEENS - MULTI SITE QG-1216M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 P-1018 P-Q245 |  | VARIOUS LOCATIONS IN QUEENS | THIS PROJECT WILL RECONSTRUCT A STAIRWAY AT CUNNINGHAM PARK, THE PASSIVE AREA OF BRINKERHOFF MALL, AND FENCING AROUND THE DOG RUN IN FORESTPARK, AND CONSTRUCT A ROLLER HOCKEY RINK AT BROAD CHANNEL PARK. | 2022 | 2935 | 1067.8 | 87 | 0 | 0 | 0 | 0 | 0 | 1154.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEN | QUEENS - COUNCIL & BP MULTI SITE QG-1316M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 |  |  | RECONSTRUCTION OF ONE ROOM SCHOOL HOUSE PLAYGROUND, KISSENA PARK CORRIDOR MEDITATION GARDEN, AND FITNESS EQUIPMENT IN ALLEY POND PARK | 2022 | 1978 | 2130.87 | 35 | 0 | 0 | 0 | 0 | 0 | 2165.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4BWIDEP | QUEENS - COUNCIL MULTI SITE QG-217M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | QUEENS MULTI-SITE | 2022 | 400 | 2461.57 | 1 | 0 | 0 | 355 | 0 | 0 | 2817.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CAPTGP | CAPT. TILLY PK RESTORE GOOSE POND | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 P-Q245 |  |  | CAPTAIN TILLY PARK -- RESTORATION OF GOOSE POND | 2022 | 6897 | 0 | 400 | 0 | 1507 | 1500 | 0 | 1900 | 5307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIBN5 | CPI PH1- RC- Astoria Heights & Bowne Plgd C/S QG-1015M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 407 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | ASTORIA HEIGHTS - 30RD, 45 TO 46 STREETS - BOROUGH OF QUEENS, BOWNE PLAYGROUND - UNION & SANFORD | ASTORIA HEIGHTS PLAYGROUND & BOWNE PLAYGROUND C/S RECONSTRUCTION | 2022 | 3132 | 4416.88 | 2 | 0 | 0 | 282 | 0 | 0 | 4700.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIHCS | CPI - HOFFMAN COMFORT STATION | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 |  |  | HOFFMAN COMFORT STATION | 2022 | 1820 | 0 | 0 | 0 | 705 | 695 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPIP35 | CPI PH2 - Playground Thirty Five XXXV R/C Q296-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | THE RECONSTRUCTION OF PLAYGROUND THIRTY FIVE XXXV | 2022 | 2532 | 3062.99 | 0 | 0 | 0 | 119 | 0 | 0 | 3181.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPPLGD | Cunningham Park Upper Playground R/C Q021-120M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0936 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CUNNINGHAM PARK PLAYGROUND | 2022 | 4000 | 423 | 3467 | 0 | 533 | 0 | 0 | 0 | 4423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPSLIT | College Point Sports Park - New Lighting | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 P-D019 |  |  | COLLEGE POINT SPORTS PARK - NEW LIGHTING | 2022 | 2400 | 150 | 0 | 0 | 1210 | 1190 | 0 | 0 | 2550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CPTLCS | Captain Tilly Park Comfort Station | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0505 |  |  | CAPTAIN TILLY PARK COMFORT STATION | 2022 | 2701 | 290 | 1555 | 568 | 0 | 0 | 0 | 0 | 2413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CROCHP | Crocheron Park Path Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 P-D019 |  | CROCHERON PARK, QUEENS | CROCHERON PARK PATH RECONSTRUCTION | 2022 | 903 | 0 | 0 | 1163 | 0 | 0 | 0 | 0 | 1163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CUN210 | CUNNINGHAM PARK 210 ST PLAYGROUND UPGRADE Q021-220M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q936 P-D019 |  |  | CUNNINGHAM PARK 210TH STREET PLAYGROUND UPGRADE | 2022 | 4914 | 270 | 0 | 0 | 1910 | 1890 | 0 | 0 | 4070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4CUNPLG | Redwood Playground in Cunningham Park R/C Q021-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 408 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CUNNINGHAM PARK LOWER PLAYGROUND RENOVATION | 2022 | 1940 | 2334.06 | 0 | 0 | 0 | 134 | 0 | 0 | 2468.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DCTALP | Alley Pond Park, Queens | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0931 |  | ALLEY POND PARK, QUEENS | ALLEY POND PARK, QUEENS | 2022 | 180 | 0 | 180 | 0 | 0 | 0 | 0 | 0 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DCTRFS | Telecom duct at Kings Manor in Rufus King Park, Queens | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0931 |  | KINGS MANOR IN RUFUS KING PARK, QUEENS | TELECOM DUCT AT KINGS MANOR IN RUFUS KING PARK, QUEENS | 2022 | 280 | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4DUTCH1 | Dutch Kills Comfort Station Q218-216M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 401 | P-0245Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RECONSTRUCTION OF PLAYGROUND AND COMFORT STATION | 2022 | 1681 | 935.98 | 0 | 0 | 0 | 745 | 0 | 0 | 1680.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4EABTRC | Emerald Ash Borer (EAB) Tree Remove Queens QG-819M | LAND ACQUISITION AND TREE PLANTING | 400 | P-0822 |  | EMERALD ASH BORER (EAB) TREE REMOVE QUEENS | EMERALD ASH BORER (EAB) TREE REMOVE QUEENS | 2022 | 1219 | 1001.25 | 0 | 155 | 0 | 0 | 0 | 0 | 1156.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ELMPRK | HELEN MARSHALL PLGD TURF FIELD Q373-121M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EAST ELMHURST PARK - CONVERT GRASS FIELD TO SYNTHETIC TURF, QUEENS | 2022 | 5300 | 50 | 30 | 0 | 3570 | 0 | 3500 | 0 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FITZPG | FITZGERALD PLAYGROUND | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 P-Q245 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FITGERALD PLAYGROUND RENOVATION, QN | 2022 | 3250 | 0 | 0 | 0 | 0 | 3500 | 0 | 2250 | 5750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FLBAY2 | FLUSHING BAY DREDGING & CONSTR OF BOAT RAMP Q099-300M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | WP-0169 |  | EASTERN TERMINUS OF THE FLUSHING BAY PROM. LOCATED IN FLUSHING MEADOWS-CORONA PARK, BOROUGH OF QUEENS | DREDGING AND CONSTR BOAT RAMP | 2022 | 1718 | 1444.66 | 0 | 98 | 0 | 0 | 0 | 0 | 1542.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMAGDN | Flushing Meadows Corona Park Installation of Retired Animals | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 |  | FLUSHING MEADOWS CORONA PARK | FLUSHING MEADOWS CORONA PARK INSTALLATION OF RETIRED ANIMALS GARDEN | 2022 | 65 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMCPIC | Recon ice plant at FMCP, Queens Q099-420M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1250 |  | QUEENS | RECON ICE PLANT AT FMCP, QUEENS | 2022 | 3400 | 0 | 0 | 0 | 1705 | 1695 | 0 | 0 | 3400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMDOOR | Flushing Meadows Corona Park Aquatic Center Exterior Doors R | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0506 |  | FLUSHING MEADOWS CORONA PARK AQUATIC CENTER | FLUSHING MEADOWS CORONA PARK AQUATIC CENTER EXTERIOR DOORS RECONSTRUCTION | 2022 | 400 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FMGARG | Flushing Meadows Corona Park Garage Q099-217MA | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 400 | P-0245Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FLUSHING MEADOWS CORONA PARK GARAGE | 2022 | 8000 | 6506.88 | 879 | 1183 | 0 | 0 | 0 | 0 | 8568.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FRDJPU | FREDERICK JUDGE PLAYGROUND UPGRADES Q119-120M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 P-Q245 |  |  | UPGRADES TO FREDERICK JUDGE PLAYGROUND IN QUEENS | 2022 | 3953 | 300 | 0 | 0 | 2010 | 2000 | 0 | 0 | 4310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FTTOTB | FT. TOTTEN PK CHAPEL & COMMANDER'S HOUSE Q458-112M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 407 | P-1018 P-1324 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | QUEENS | FORT TOTTEN BUILDING 422 ADA ACCESSIBILITY, NEW ROOF AND EXTERIOR WORK | 2022 | 3087 | 6053.66 | 1 | 0 | 0 | 1735 | 0 | 0 | 7789.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4FTTOTC | FT. TOTTEN ELEVATORS Q458 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FT. TOTTEN ELEVATORS Q458 | 2022 | 350 | 0 | 0 | 0 | 1564 | 1550 | 0 | 0 | 3114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GBLPLG | SEVEN GABLES PLAYGROUND | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATIONO OF SEVEN GABLES PLAYGROUND, QUEENS | 2022 | 5540 | 0 | 0 | 0 | 0 | 1050 | 0 | 0 | 1050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GLNOAK | Tenney Pk (Glen Oaks) Bball Ct./Play Equip. R/C Q310-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION OF THE PLAY EQUIPMENT AT TENNEY PARK (GLEN OAKS OVAL)... | 2022 | 1500 | 1185.79 | 0 | 0 | 0 | 482 | 0 | 0 | 1667.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GRST21 | Greenstreets - Queens | LAND ACQUISITION AND TREE PLANTING | 400 | ED-Q384 P-0822 P-Q245 P-Q822 P-D171 |  | BOROUGH OF QUEENS - BELL BOULEVARD BETWEEB HORACE HARDING EXPRESSWAY AND 48TH AVENUE, MERRICK BOULEVARD BETWEEN 107TH AVENUE AND SPRINGFIELD BOULEVARD AND 75TH STREET BETWEEN 37TH AVENUE AND WOODSIDE AVENUE | GREENSTREETS | 2022 | 266 | 0 | 0 | 0 | 800 | 698 | 0 | 0 | 1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4GWENCS | GWEN IFILL PLGD COMFORT STATION RECON | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0245Q |  |  | GWEN IFILL PLGD COMFORT STATION RECON | 2022 | 3500 | 0 | 0 | 0 | 1755 | 1745 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HARTRF | Recon of Roofing systems at Hart Comf Sta | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1249 |  | QUEENS | RECON OF ROOFING SYSTEMS AT HART COMF STA | 2022 | 175 | 27 | 152 | 0 | 0 | 0 | 0 | 0 | 179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HCHAND | HALLET'S COVE RENOVATION OF HANDBALL COURT AND FENCING | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 |  |  | RENOVATION OF THE HANDBALL COURT WALL & ADJACENT FENCING AT HALLET'S COVE IN QUEENS | 2022 | 450 | 30 | 0 | 450 | 0 | 0 | 0 | 0 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HCOVP2 | Hallet's Cove Playground MPPA Q226-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CREATE A MULTIPURPOSE PLAY AREA AT HALLETS COVE PLAYGROUND | 2022 | 3537 | 2575.32 | 24 | 549 | 0 | 0 | 0 | 0 | 3148.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HILNDP | Highland Park Path Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 P-D019 P-D017 |  | HIGHLAND PARK, QUEENS | HIGHLAND PARK PATH RECONSTRUCTION | 2022 | 700 | 0 | 0 | 2350 | 0 | 0 | 0 | 0 | 2350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HLNDSW | Highland Park Upper Playground Comfort Station Sewer Reconst | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D017 |  | QUEENS | HIGHLAND PARK UPPER PLAYGROUND COMFORT STATION SEWER RECONSTRUCTION | 2022 | 390 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4HOLSCS | Hollis Playground Comfort Station Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0505 P-1008 |  | QUEENS | HOLLIS PLAYGROUND COMFORT STATION RECONSTRUCTION | 2022 | 1200 | 0 | 0 | 0 | 481 | 0 | 0 | 0 | 481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4IDLETB | IDLEWILD PARK CONSTRUCTION OF NATURE TRAIL AND BOARDWALK | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 413 | P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | IDLEWILD PARK - EASTERN QUEENS ALLIANCE: CONSTRUCTION OF NATURE TRAIL AND BOARDWALK | 2022 | 1000 | 0 | 0 | 0 | 510 | 490 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4JAUSTI | JOSEPH AUSTIN PLAYGROUND Q391-108M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 408 | P-Q245 | PROJECT DELAYED DUE TO UNFORESEEN HAZARDOUS CONDITION | QUEENS | JOSEPH AUSTIN PLGD | 2022 | 3700 | 3229.34 | 81 | 0 | 0 | 0 | 0 | 0 | 3310.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4JMMPP2 | JOE MICHAEL MILE PHASE 2 PATH RENO NORTH | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  |  | JOE MICHAEL MILE PHASE 2 PATH RENO NORTH | 2022 | 3600 | 0 | 0 | 351 | 0 | 3049 | 0 | 0 | 3400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4KCPPAV | KISSENA CORRIDOR PARK: NEW SECURITY LIGHTING AND REPAVING | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 P-D019 |  |  | KISSENA CORRIDOR PARK: CONSTRUCT NEW SECURITY LIGHTING AND PAVE PATHWITH ASPHALT | 2022 | 950 | 0 | 0 | 0 | 950 | 475 | 0 | 0 | 1425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4KSNAPK | Kissena Park Path Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 |  | KISSENA PARK, QUEENS | KISSENA PARK PATH RECONSTRUCTION | 2022 | 1100 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LATRUF | RUFUS KING MANOR & LEWIS H LATIMER HOUSE ROOFS QG-411M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 412 | P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | KING MANOR AND LEWIS H LATIMER HOUSE ROOF PROJECTS | 2022 | 1400 | 1978.41 | 0 | 0 | 541 | 0 | 0 | 0 | 2519.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LIBTPL | Recon pool deck at Liberty Pool, Queens | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | LIBERTY POOL, QUEENS | RECON POOL DECK AT LIBERTY POOL, QUEENS | 2022 | 1201 | 60 | 1301 | 0 | 0 | 0 | 0 | 0 | 1361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4LTLBSH | Nathan Weidenbaum Park Playground R/C Q205B-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 P-0935 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NATHAN WEIDENBAUM (LITTLE BUSH) PARK - PLAYGROUND RENOVATION | 2022 | 500 | 3387.49 | 0 | 0 | 0 | 0 | 516 | 0 | 3903.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4MARFAJ | MARIO FAJARDO PLAYGROUND Q300-121M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 P-Q245 |  |  | MARI FAJARDO PLAYGROUND RENOVATION, QUEENS | 2022 | 3200 | 200 | 174 | 0 | 2726 | 2700 | 0 | 0 | 5800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4NEPONS | NEPONSIT HOSPITAL- CONS OF PLAZA | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 |  |  | THE SCOPE OF WORK INCLUDES THE CONSTRUCTION OF A PASSIVE SEATING AREAWITH BENCHES AND NEW PAVING TOWARD THE SOUTHERN EDGE OF THE SITE TO OPTIMIZE THE PUBLIC'S CONNECTION TO THE BEACH. ADDITIONAL WORK INCLUDESTHE CONSTRUCTION OF A PATHWAY SYSTEM THAT BUILDS UPON THE LIMITED EXISTING PATHS AS WELL AS THE BEAUTIFICATION OF THE SURROUNDING LANDSCAPEWITH TREES AND SHRUB PLANTINGS. THIS PROJECT WILL TRANSFORM THIS DERELICT SITE INTO A PASSIVE RECREATION AREA THAT SERVES AS AN EXTENSION TO JACOB RIIS PARK TO THE WEST. PLEASE NOTE THAT IN ORDER TO CREATE THIS PASSIVE RECREATION AREA, THE EXISTING STRUCTURES ON SITE MUST BE DEMOLISHED. THE BUILDINGS POSE A DIRECT CONFLICT WITH THE SITING OF THE PATHWAYS AND THE PASSIVE SEATING AREA. | 2022 | 350 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4NNANPG | NOONAN PLAYGROUND- Q044-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0245Q |  |  | NOONAN PLAYGROUND | 2022 | 3082 | 200 | 0 | 1036 | 1464 | 0 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OLMSRF | Reconstruction of the roof at Olmsted Center | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-1018 |  |  | RECONSTRUCTION OF THE ROOF AT OLMSTED CENTER. FLUSHING MEADOWS CORONAPARK, BOROUGH OF QUEENS | 2022 | 3391 | 0 | 0 | 0 | 1700 | 0 | 1660 | 0 | 3360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OLMST3 | OLMSTED CTR FURNITURE Q099-808MA1 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 403 404 406 407 408 | P-0013 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | FMCP, QUEENS | OLMSTED CTR PARKING LOT | 2022 | 1200 | 1397.01 | 589 | 0 | 0 | 0 | 0 | 0 | 1986.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4OLMST4 | OLMSTED CTR RC (BUILDING) Q099-808MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 403 404 406 407 408 | P-0245Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 117-02 ROOSEVELT AVENUE | THIS PROJECT WILL RECONSTRUCT THE OLMSTED CENTER IN FLUSHING MEADOWS CORONA PARK. | 2022 | 16483 | 31337.29 | 776 | 0 | 0 | 0 | 0 | 0 | 32113.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PASAIR | Passerelle Building/ Port Arth. AirTrain | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 400 | P-0245Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | PASSERELLE/PORT AUTHORITY | PARKS PASSERELLE/PORT AUTHORITY AIRTRAIN | 2022 | 125141 | 0 | 0 | 0 | 0 | 0 | 124891 | 0 | 124891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PDLBRC | Lost Battalion Rec Ctr RC Q401-115M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 400 | P-D019 P-0506 P-Q245 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | QUEENS | LOST BATTALION REC CTR RC | 2022 | 4000 | 1425.53 | 15955 | 0 | 1450 | 0 | 0 | 0 | 18830.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PHIPPS | Lt. Michael R. Davidson Playground Construction Q516-120M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D056 P-D019 |  |  | PHIPPS PLAYGROUND ACQUISITION, BOROUGH OF QUEENS | 2022 | 4943 | 150 | 0 | 0 | 2500 | 2315 | 0 | 0 | 4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG12A | Reconstruction of plgr, Borough ofQueens (QG-112M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-0245Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | QUEENS BOROUGHWIDE | PLGR | 2022 | 50 | 146.39 | 0 | 0 | 0 | 0 | 0 | 0 | 146.39 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 38
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG12B | FY12 Reconstruction of plgr Queens QG-212M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGHWIDE | FY12 RECONSTRUCTION OF PLGR QUEENS | 2022 | 925 | 837.52 | 0 | 0 | 0 | 145 | 0 | 0 | 982.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PLG13G | FY13 Queens Plgrd Multisite QG-913M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION OF PAVEMENTS, DRAINAGE, PLANTINGS, AND GENERAL SITEWORK AT HOLY COW PLAYGROUND AND UPPER HIGHLAND PARK | 2022 | 1478 | 1122.9 | 0 | 0 | 0 | 235 | 0 | 0 | 1357.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PNYT29 | PlaNYC FY18 Street Tree Queens CB 7,8,11 QG- | LAND ACQUISITION AND TREE PLANTING | 400 | P-0822 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | PLANYC FY18 STREET TREE QUEENS CB 7,8,11 | PLANYC FY18 STREET TREE QUEENS CB 7,8,11 | 2022 | 2386 | 3180 | 0 | 0 | 0 | 340 | 0 | 0 | 3520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4PWOB01 | PWOB - FMCP Henry Hudson Entrance Q099-317M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PARKS WITHOUT BORDERS SITE - FLUSHING MEADOWS CORONA PARK 111TH STREET (HENDRY HUDSON) ENTRANCE | 2022 | 3950 | 4158.09 | 0 | 0 | 0 | 0 | 371 | 0 | 4529.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QMULT2 | QUEENS MULTISITE QG-506M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 | PROJECT DELAYED DUE TO SCHEDULING OF UTILITY WORK |  | IDLEWILD PK CRICKET PITCH FIELD CONSTRUCTION; JOHN BOWNE HS BASEBALLFIELDS | 2022 | 225 | 0 | 0 | 0 | 1509 | 1507 | 0 | 0 | 3016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QNHSRC | QUEENS HISTORICAL SOCIETY CONSTRUCTION AND RENOVATION | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 P-D019 |  |  | QUEENS HISTORICAL SOCIETY CONSTRUCTION AND RENOVATION IN QUEENS | 2022 | 1700 | 0 | 0 | 0 | 0 | 1700 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QNPAV1 | State of Good Repair - Queens QG-121M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | WP-0169 P-1018 |  | QUEENS | STATE OF GOOD REPAIR - QUEENS | 2022 | 1219 | 0 | 0 | 1584 | 1258 | 3922 | 0 | 0 | 6764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QSTORE | QUEENS STOREHOUSE Q099-520M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 400 | P-0245Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | QUEENS | QUEENS STOREHOUSE | 2022 | 14048 | 534.94 | 7 | 0 | 5174 | 2574 | 7773 | 0 | 16062.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4QWCAMS | Queens Wildlife Center Aviary Mesh Replacement | ZOOS | 400 | P-Q245 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | QUEENS WILDLIFE CENTER AVIARY MESH REPLACEMENT: REPLACE THE VINYL-COATED MESH AND REHABILITATE STRUCTURAL FAME OF DOME. | 2022 | 400 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RAINE2 | Rainey Pk Picnic Grove, Bsktball Ct, & Dog Run R/C Q048-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 401 | P-D019 P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RAINEY PARK - RECONSTRUCTION OF THE PICNIC GROVE, BASKETBALL COURT, AND DOG RUN, BOROUGH OF QUEENS | 2022 | 1200 | 450 | 0 | 0 | 6523 | 977 | 0 | 0 | 7950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RAMBLE | Ramblersville Restoration Areas | LAND ACQUISITION AND TREE PLANTING | 400 | P-1018 |  |  | RAMBLERSVILLE RESTORATION AREAS | 2022 | 4500 | 0 | 0 | 0 | 2260 | 2240 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RDGEWD | Rosemary's Plgd R/C Q398-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RIDGEWOOD PARK | 2022 | 300 | 3344.7 | 0 | 0 | 0 | 302 | 0 | 0 | 3646.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RGROI2 | Rockaway Beach Reformulation- Groin removal & crossing cons | BEACHES AND BOARDWALKS | 400 | P-0245Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | THE US ARMY CORPS OF ENGINEERS WILL BE CONSTRUCTING NEW GROINS ON ROCKAWAY BEACH IN THE SPRING OF 2020 TO CONTROL SAND EROSION. AT THE CITYS REQUEST, THE CORPS HAS AGREED TO INCLUDE THE REMOVAL OF DECAYING WOODEN GROINS IN A SECTION OF ROCKAWAY BEACH IN THEIR CONSTRUCTION PLANS, IF FUNDED BY THE CITY. THESE GROINS NO LONGER PROVIDE EROSION CONTROL AND COULD BE HAZARDOUS IF LEFT TO CONTINUE DECAYING. COUPLING THE GROIN REMOVAL WITH THE CORPS CONSTRUCTION OF NEW GROINS WILL PROVIDE A COST SAVINGS TO THE CITY. | 2022 | 8288 | 860 | 428 | 0 | 0 | 0 | 32000 | 0 | 33288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4ROYWKG | ROY WILKINS PARK: INSTALLATION OF A HUT FOR THE URBAN GARDEN | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q847 |  |  | ROY WILKINS PARK: INSTALLATION OF A QUONSET HUT FOR THE URBAN GARDEN | 2022 | 665 | 0 | 0 | 0 | 0 | 665 | 0 | 0 | 665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4RRDPK | RAILROAD PARK | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0245Q |  |  | RAILROAD PARK | 2022 | 21000 | 0 | 555 | 0 | 8195 | 0 | 8750 | 0 | 17500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SAND03 | SANDY - Spring Creek Reforestation CNYG-316M | LAND ACQUISITION AND TREE PLANTING | 400 | P-1018 |  |  | SPRING CREEK REFORESTATION | 2022 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 779.95 | 244 | 0 | 0 | 0 | 0 | 0 | 1023.95
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREAC | Shorefront Parkway Adventure Course Q163-218M | BEACHES AND BOARDWALKS | 400 | P-Q003 |  |  | CONSTRUCTION OF AN ADVENTURE COURSE ALONG SHOREFRONT PARKWAY, BOROUGHOF QUEENS | 2022 | 408 | 480 | 103 | 0 | 0 | 0 | 0 | 0 | 583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREDP | Shorefront Parkway Dog Run Cons. Q163-118M | BEACHES AND BOARDWALKS | 400 | P-Q003 |  |  | CONSTRUCTION OF A DOG PARK ALONG SHOREFRONT PARKWAY, BOROUGH OF QUEENS | 2022 | 154 | 0 | 154 | 0 | 0 | 0 | 0 | 0 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHREPG | Shorefront Tot Playground and Plaza Area Q163-318M | BEACHES AND BOARDWALKS | 400 | P-Q003 |  |  | CONSTRUCTION OF A TOT PLAYGROUND AND PLAZA AREA ALONG SHOREFRONT PARKWAY, BOROUGH OF QUEENS | 2022 | 644 | 0 | 644 | 0 | 0 | 0 | 0 | 0 | 644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHRESA | Shorefront Parkway Park Amenities Q163-120M | BEACHES AND BOARDWALKS | 400 | P-Q003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCTION OF PARK AMENITIES ALONG SHOREFRONT PARKWAY, BOROUGH OF QUEENS | 2022 | 491 | 0 | 0 | 0 | 359 | 0 | 0 | 0 | 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SHRESF | Shorefront Parkway Multi-Purpose Sports Field Cons Q163-618M | BEACHES AND BOARDWALKS | 400 | P-Q003 |  |  | CONSTRUCTION OF A MULTI-PURPOSE SPORTS FIELD ALONG SHOREFRONT PARKWAY, BOROUGH OF QUEENS | 2022 | 728 | 51.22 | 677 | 0 | 0 | 0 | 0 | 0 | 728.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SPRNGF | Alley Pond Park Springfield Plgd Parking Lot Recon | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 |  | ALLEY POND PARK, QUEENS | ALLEY POND PARK SPRINGFIELD PLAYGROUND PARKING LOT RECONSTRUCTION | 2022 | 1100 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4STFCAR | Syn Turf Field Recon at Rachel Carson at Kessina, QN | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 |  | RACHEL CARSON AT KESSINA, QN | SYN TURF FIELD RECON AT RACHEL CARSON AT KESSINA, QN | 2022 | 605 | 61 | 581 | 24 | 0 | 0 | 0 | 0 | 666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4STRNSW | FMCP Saturn Playground Water Line Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  | QUEENS | FMCP SATURN PLAYGROUND WATER LINE RECONSTRUCTION | 2022 | 73 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4SUNRSE | Sunrise Stables Acquisition | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 |  | SOUTH CONDUIT AND LINDEN | SUNRISE STABLES ACQUISITION | 2022 | 636 | 0 | 10 | 490 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE18A | FY18 Street Tree Queens CBs 1-5 QG- | LAND ACQUISITION AND TREE PLANTING | 400 | P-Q245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | FY18 STREET TREE QUEENS CBS 1-5 | FY18 STREET TREE QUEENS CBS 1-5 | 2022 | 2660 | 172.99 | 0 | 0 | 0 | 500 | 0 | 0 | 672.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE20B | FY20 Street Tree Queens CBs 7,8,11 QG-219M | LAND ACQUISITION AND TREE PLANTING | 400 | P-0822 WP-0169 P-1018 |  | FY20 STREET TREE QUEENS CBS 7,8,11 QG-219M | FY20 STREET TREE QUEENS CBS 7,8,11 QG-219M | 2022 | 1977 | 175 | 1977 | 0 | 0 | 0 | 0 | 0 | 2152 | 0 | 823 | 0 | 0 | 0 | 0 | 0 | 823
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE20R | Queens Street Tree Planting Renewal cb 12, 13 QG-319M | LAND ACQUISITION AND TREE PLANTING | 400 | P-1018 P-0822 |  | BOROUGH OF QUEENS | QUEENS STREET TREE PLANTING RENEWAL | 2022 | 2918 | 0 | 830 | 0 | 0 | 0 | 0 | 0 | 830 | 0 | 1938 | 0 | 0 | 0 | 0 | 0 | 1938
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE21A | FY21 Street Tree Queens CBs 1-6 QG- | LAND ACQUISITION AND TREE PLANTING | 400 | P-D019 P-0822 P-D822 |  | FY21 STREET TREE QUEENS CBS 1-6 | FY21 STREET TREE QUEENS CBS 1-6 | 2022 | 797 | 75 | 2752 | 0 | 0 | 0 | 0 | 0 | 2827 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 920
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE21B | FY21 Street Tree Queens CBs 9,14 QG-1319M | LAND ACQUISITION AND TREE PLANTING | 400 | WM-0006 P-0822 P-1018 |  | FY21 STREET TREE QUEENS CBS 9,14 | FY21 STREET TREE QUEENS CBS 9,14 | 2022 | 1631 | 25 | 451 | 0 | 0 | 0 | 0 | 0 | 476 | 0 | 2069 | 0 | 0 | 0 | 0 | 0 | 2069
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE22A | Queens Street Tree Planting Prep FY22 CD30 QG-522M | LAND ACQUISITION AND TREE PLANTING | 400 | P-D822 |  | BOROUGH OF QUEENS. | QUEENS STREET TREE PLANTING SITE PREPARTION FY22 - CD 30 | 2022 | 520 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE22B | Queens Street Plant. CD 30 FY 22 QG-622M | LAND ACQUISITION AND TREE PLANTING | 400 | P-D822 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF QUEENS | QUEENS STREE TREE PLANTING - CD30 | 2022 | 454 | 0 | 0 | 348 | 0 | 0 | 0 | 0 | 348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE22C | Queens Street Plant. FY 22-CB 9,10,14 | LAND ACQUISITION AND TREE PLANTING | 400 | P-1018 F-0175 P-0822 |  | BOROUGH OF QUEENS | QUEENS STREET TREE PLANTING | 2022 | 1873 | 0 | 0 | 29 | 736 | 0 | 0 | 0 | 765 | 0 | 0 | 1266 | 0 | 0 | 0 | 0 | 1266
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRE22D | Queens Park Tree Planting | LAND ACQUISITION AND TREE PLANTING | 400 | WM-0006 P-0822 SE-0002Q P-0245Q WP-0169 SE-0200Q |  | BOROUGH OF QUEENS. | QUEENS PARK TREE PLANTING | 2022 | 2747 | 0 | 11 | 2747 | 0 | 0 | 0 | 0 | 2758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREL21 | FY21 Street Trees QN CB's 8,11-13, QG-1219M | LAND ACQUISITION AND TREE PLANTING | 400 | P-D822 P-D019 SE-0200Q WM-0006 P-0822 P-1018 SE-0002Q |  | QUEENS | FY21 STREET TREES QN CB'S 8,11-13(3Y) | 2022 | 3591 | 25 | 4307 | 0 | 0 | 1067 | 0 | 0 | 5399 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 2200
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TREP22 | Queens Street Tree Planting FY22 - CB 1-4, QG-422M | LAND ACQUISITION AND TREE PLANTING | 400 | P-1018 |  | BOROUGH OF QUEENS | QUEENS STREET TREE PLANTING FY22 -CB1-4 | 2022 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRS21A | FY21 Street Tree 7mo Queens CBs7 QG-1019M | LAND ACQUISITION AND TREE PLANTING | 400 | P-0822 |  | FY21 STREET TREE 7MO QUEENS CBS7 | FY21 STREET TREE 7MO QUEENS CBS7 | 2022 | 882 | 25 | 882 | 0 | 0 | 0 | 0 | 0 | 907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRS21B | FY21 Street Tree 7mo Queens CBs 10 QG-919M | LAND ACQUISITION AND TREE PLANTING | 400 | P-0822 |  | FY21 STREET TREE 7MO QUEENS CBS 10 | FY21 STREET TREE 7MO QUEENS CBS 10 | 2022 | 945 | 25 | 945 | 0 | 0 | 0 | 0 | 0 | 970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRS21D | Queens -Tree Damaged Sidewalk | LAND ACQUISITION AND TREE PLANTING | 400 | P-D822 P-1331 P-1018 |  | BOROUGH OF QUEENS | QUEENS BOROUGH WIDE | 2022 | 3001 | 0 | 3001 | 0 | 0 | 0 | 0 | 0 | 3001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4TRS21E | Queens -Tree Damaged Sidewalk | LAND ACQUISITION AND TREE PLANTING | 400 | P-1018 |  | BOROUGH OF QUEENS | QUEENS TREE DAMAGED SIDEWALK - BOROUGH WIDE | 2022 | 2080 | 0 | 2080 | 0 | 0 | 0 | 0 | 0 | 2080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4UDALNP | Udalls Cove Park & Nature Preserve | LAND ACQUISITION AND TREE PLANTING | 400 | P-D019 |  | BOROUGH OF QUEENS | UDALLS COVE PARK & NATURE PRESERVE | 2022 | 350 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4UNION | Union Street Beautification | LAND ACQUISITION AND TREE PLANTING | 400 | P-D019 |  | BOROUGH OF QUEENS | UNION STREET BEAUTIFICATION IN QUEENS. PERMEABLE PAVEMENT ALONG UNION STREET AND GREENSTREETS RENOVATION ALONG NORTHERN BLVD | 2022 | 650 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4VIETNA | VIETNAM VETERAN MEMORIAL - ELMHURST PARK Q492-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | FORMER KEYSPAN GAS TANK PROPERTY ON 57TH AVENUE BETWEEN 74TH AND 80THSTREETS | CONSTRUCT WAR MEMORIAL ON SITE OF FORMER KEYSPAN GAS TANK PROPERTY ON57TH AVE BET 74 AND 80 STREETS. | 2022 | 500 | 2750.69 | 0 | 0 | 0 | 253 | 0 | 0 | 3003.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WATECS | WATERS EDGE PLGD COMFORT STATION RECON | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0245Q |  | WATERS EDGE PLGD COMFORT STATION RECON | WATERS EDGE PLGD COMFORT STATION RECON | 2022 | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WATEDG | WATERS EDGE PLGD RECON | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0245Q |  |  | MISCELLANEOUS PARKS, PLAYGROUNDS, CONSTRUCTION, RECONSTRUCTION, QUEENS -- WATERS EDGE PLAYGROUND | 2022 | 19500 | 0 | 461 | 0 | 5288 | 5751 | 0 | 0 | 11500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WOODPG | WOODTREE PLAYGROUND: RENOVATE THE BASKETBALL COURTS | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-Q245 P-D019 |  |  | WOODTREE PLAYGROUND: RENOVATE THE BASKETBALL COURTS TO ADDRESS DRAINAGE ISSUES | 2022 | 2450 | 0 | 254 | 0 | 2600 | 2196 | 0 | 0 | 5050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WOODPZ | WOODSIDE PLAZA Q198-121M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-D019 P-Q245 |  |  | RENOVATION OF WOODSIDE PLAZA, QUEENS | 2022 | 2000 | 150 | 100 | 650 | 0 | 1000 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WPJAMC | Walk to Park NYCHA Pomonok Houses Construction Q515-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0245Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WALK TO PARK NYCHA SOUTH JAMAICA II PLAYGROUND CONSTRUCTION, BOROUGH OF QUEENS | 2022 | 3000 | 2477.36 | 251 | 0 | 0 | 692 | 0 | 0 | 3420.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-4WPWSDE | Walk to Park NYCHA Woodside Playground Construction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-0245Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WALK TO PARK NYCHA WOODSIDE PLAYGROUND CONSTRUCTION, BOROUGH OF QUEENS | 2022 | 1200 | 164 | 1000 | 200 | 0 | 0 | 0 | 0 | 1364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-6BLD14B | FY14 BUILDINGS-RC OF C/S & FACILTIES AT VAR PKS & RECR LOC | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-Q245 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FY14 BUILDINGS-RC OF C/S & FACILTIES AT VAR PKS & RECR LOC | 2022 | 1674 | 2016.5 | 0 | 66 | 0 | 0 | 0 | 0 | 2082.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | P-6ROOFQN | Recon roofs at Forest Pk garage & Oak Ridge QG-918M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1249 |  | CITYWIDE | RECON ROOFS AT FOREST PK GARAGE & OAK RIDGE IN FOREST PARK | 2022 | 3774 | 2353.04 | 382 | 0 | 0 | 0 | 0 | 0 | 2735.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-02 | SANDY- Emergency Storm Make Safe - Rockaway Beach Q162-213M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 414 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EMERGENCY-STORM MAKE SAFE OF ROCKAWAY BEACH | 2022 | 2531 | 912.82 | 46 | 0 | 0 | 0 | 0 | 0 | 958.82 | 7214.87 | 0 | 0 | 0 | 0 | 0 | 249 | 7463.87
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-08 | PNP Socrates Sculpture Park | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 401 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | QUEENS | QUEENS SOCRATES SCULPTURE PARK | 2022 | 206 | 98.92 | 0 | 31 | 0 | 0 | 0 | 0 | 129.92 | 26.35 | 0 | 268 | 0 | 0 | 0 | 0 | 294.35
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-10 | Ralph DeMarco Pk, Shoreline R/C Q004-213M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RALPH DEMARCO PK, QUEENS | SANDY - R/C OF SHORELINE IN RALPH DEMARCO PK, TYPE 3 | 2022 | 92 | 321.1 | 0 | 1449 | 0 | 0 | 0 | 0 | 1770.1 | 348.09 | 0 | 5501 | 300 | 0 | 0 | 0 | 6149.09
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-12 | SANDY- Joe Michael's Mile Promenade Q135-214M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 28 ROAD AND CROSS ISLAND PKWY, QUEENS | R/C OF THE PROMENADE(JOE MICHAEL'S MILE) | 2022 | 222 | 311.5 | 5 | 0 | 0 | 0 | 0 | 1 | 317.5 | 172.78 | 0 | 0 | 0 | 0 | 0 | 39 | 211.78
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-13 | SANDY-Rockaway Beach roller hockey rink - Type 3 Q163-114M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SANDY-ROCKAWAY BEACH: LONG TERM RC | 2022 | 446 | 31.03 | 45 | 0 | 0 | 0 | 0 | 0 | 76.03 | 599.48 | 0 | 0 | 0 | 0 | 0 | 48 | 647.48
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-15 | SANDY - Tree removals - Queens CB 6-15 QG-414M | LAND ACQUISITION AND TREE PLANTING | 400 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | QUEENS | TREE REMOVALS RELATED TO SANDY IN THE BOROUGH OF QUEENS | 2022 | 1900 | 80.58 | 0 | 131 | 8 | 0 | 0 | 0 | 219.58 | 462.66 | 0 | 0 | 0 | 0 | 0 | 1244 | 1706.66
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-18 | SANDY - Tribute Park Reconstruction Q028-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | SANDY - TRIBUTE PK AND FLIGHT 587 MEMORIAL | SANDY - TRIBUTE PK AND FLIGHT 587 MEMORIAL | 2022 | 476 | 562.7 | 19 | 0 | 0 | 0 | 0 | 0 | 581.7 | 508.84 | 0 | 0 | 0 | 0 | 0 | 156 | 664.84
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-21 | SANDY-FOREST PARK GREENHOUSE BROKEN GLASS REPLACEMENT | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-1018 |  |  | SANDY-FOREST PARK GREENHOUSE BROKEN GLASS REPLACEMENT | 2022 | 253 | 10.28 | 0 | 27 | 0 | 0 | 0 | 0 | 37.28 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 235
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-22 | SANDY - Rockaway Beach Shorefront Pkwy Handball Ct Q163-315M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BEACH 105 STREET AND BEACH 102 STREET, SOUTH OF SHORE FRONT PARKWAY AT ROCKAWAY BCH | SANDY-ROCKAWAY BCH-R/C OF 8 HANDBALL COURTS | 2022 | 1658 | 570.33 | 29 | 0 | 0 | 0 | 0 | 0 | 599.33 | 2700.13 | 0 | 0 | 0 | 0 | 0 | 252 | 2952.13
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-25 | Bayside Marina Reconstruction (Q135-117M) | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 400 | P-1018 |  |  | BAYSIDE MARINA | 2022 | 1939 | 347.06 | 0 | 388 | 0 | 0 | 0 | 0 | 735.06 | 378.59 | 0 | 3490 | 0 | 0 | 0 | 0 | 3868.59
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-26 | World's Fair Marina Q099-218M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 400 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WORLD'S FAIR MARINA | 2022 | 7081 | 472.85 | 8 | 0 | 672 | 0 | 0 | 0 | 1152.85 | 601.66 | 0 | 0 | 6129 | 0 | 0 | 0 | 6730.66
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-27 | Little Bay Revetment | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 |  |  | JOE MICHAEL'S MILE/LITTLE BAY REVETMENT | 2022 | 457 | 51.63 | 0 | 103 | 0 | 0 | 0 | 0 | 154.63 | 86.7 | 0 | 515 | 411 | 0 | 0 | 0 | 1012.7
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-29 | FMCP Electrical Repairs | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FMCP ELECTRICAL REPAIRS | 2022 | 15440 | 408.49 | 10 | 0 | 1606 | 1689 | 0 | 0 | 3713.49 | 2182.41 | 90 | 0 | 14449 | 15185 | 0 | 0 | 31906.41
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-32 | SANDY - Beach 94th Street Performance Space Cons. Q163-418M | BEACHES AND BOARDWALKS | 400 | P-1018 |  |  | CONSTRUCTION OF A PERFORMANCE SPACE ON BEACH 94TH STREET, IN ROCKAWAYBEACH, BOROUGH OF QUEENS | 2022 | 3532 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 342.71 | 2657 | 0 | 0 | 0 | 0 | 0 | 2999.71
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-33 | SANDY - Shorefront Park MPPA Sports Field Cons. Q163-618M | BEACHES AND BOARDWALKS | 400 | P-1018 |  |  | SHOREFRONT PARK MULTI-PURPOSE SPORTS FIELD CONSTRUCTION | 2022 | 8448 | 84.56 | 17 | 0 | 0 | 0 | 0 | 0 | 101.56 | 563.3 | 6459 | 0 | 0 | 0 | 0 | 0 | 7022.3
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-34 | SANDY - Shorefront Labyrinth and Seating Area Q163-518M | BEACHES AND BOARDWALKS | 400 | P-1018 |  |  | SHOREFRONT LABYRINTH AND SEATING AREA CONSTRUCTION - BOROUGH OF QUEENS | 2022 | 2398 | 94.54 | 143 | 11 | 0 | 0 | 0 | 0 | 248.54 | 183.09 | 1481 | 128 | 0 | 0 | 0 | 0 | 1792.09
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-35 | SANDY - Shorefront Tot Playground and Plaza Area Q163-318M | BEACHES AND BOARDWALKS | 400 | P-1018 |  |  | SHOREFRONT TOT PLAYGROUND AND PLAZA AREA CONSTRUCTION, BOROUGH OF QUEENS | 2022 | 10141 | 422.14 | 321 | 0 | 0 | 0 | 0 | 0 | 743.14 | 172.24 | 6759 | 0 | 0 | 0 | 0 | 0 | 6931.24
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-36 | SANDY - Shorefront Parkway Adventure Course Q163-218M | BEACHES AND BOARDWALKS | 400 | P-1018 |  |  | SHOREFRONT PARKWAY ADVENTURE COURSE CONSTRUCTION, AT ROCKAWAY BEACH AND BOARDWALK, BOROUGH OF QUEENS | 2022 | 4890 | 448.9 | 36 | 67 | 0 | 0 | 0 | 0 | 551.9 | 2755.33 | 621 | 452 | 0 | 0 | 0 | 0 | 3828.33
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-37 | SANDY - Beach 88th Street Park Construction Q499-118M | BEACHES AND BOARDWALKS | 400 | P-1018 |  |  | CONSTRUCTION OF A PARK ON BEACH 88TH STREET, BOROUGH OF QUEENS | 2022 | 9172 | 129 | 0 | 0 | 0 | 0 | 0 | 0 | 129 | 741.08 | 0 | 7039 | 0 | 0 | 0 | 0 | 7780.08
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-38 | SANDY - Beach 24th to Beach 25th Street Ramp Q162-218M | BEACHES AND BOARDWALKS | 400 | P-1018 |  |  | CONSTRUCTION OF A RAMP BETWEEN BEACH 24TH AND BEACH 25TH STREETS, BOROUGH OF QUEENS | 2022 | 1473 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 150.27 | 691 | 0 | 100 | 309 | 0 | 0 | 1250.27
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-39 | SANDY - Rockaway Community Park Shoreline R/C Q371-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 414 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION OF THE SHORELINE AT ROCKAWAY COMMUNITY PARK, BOROUGH OF QUEENS | 2022 | 13819 | 157 | 0 | 0 | 0 | 0 | 0 | 0 | 157 | 948.34 | 30 | 0 | 10742 | 0 | 0 | 0 | 11720.34
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-42 | SANDY - Shorefront Parkway Dog Run Cons. Q163-118M | BEACHES AND BOARDWALKS | 400 | P-1018 |  |  | CONSTRUCTION OF A DOG PARK ON SHOREFRONT PARKWAY, BOROUGH OF QUEENS | 2022 | 1885 | 220.05 | 88 | 0 | 0 | 0 | 0 | 0 | 308.05 | 9.5 | 1585 | 0 | 0 | 0 | 0 | 0 | 1594.5
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-44 | SANDY - Shorefront Parkway Park Amenities | BEACHES AND BOARDWALKS | 400 | P-1018 |  |  | CONSTRUCTION OF PARK AMENITIES ALONG SHOREFRONT PARKWAY, BOROUGH OF QUEENS | 2022 | 3611 | 505 | 0 | 8 | 0 | 0 | 0 | 0 | 513 | 0 | 0 | 3603 | 0 | 0 | 0 | 0 | 3603
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-45 | SANDY - Thursby Basin Park Construction Q479-120M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCTION OF THURSBY BASIN PARK, AT ROCKAWAY BEACH AND BOARDWALK, IN THE BOROUGH OF QUEENS | 2022 | 12025 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 912.8 | 72 | 0 | 5574 | 5366 | 0 | 0 | 11924.8
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-46 | Joe Michael's Mile (Q012-120M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 |  | CROSS ISLAND PARKWAY, UTOPIA PARKWAY, QUEENS. | RECONSTRUCTION, REPLACEMENT, REHABILITATION AND/OR STABALIZATION OF DAMAGED WATERFRONT AREAS, QUEENS. | 2022 | 1955 | 21.86 | 0 | 44 | 134 | 0 | 0 | 0 | 199.86 | 151.73 | 0 | 104 | 1504 | 0 | 0 | 0 | 1759.73
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-48 | Bayswater Park Reconstruction-FEMA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-1018 |  | DWIGHT AVE., SEAGIRT BLVD. BET. BEACH 38 ST. AND BAY 32 ST. QUEENS | THIS PROJECT WILL RECONSTRUCT BAYSWATER PARK | 2022 | 39588 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 19486 | 0 | 20000 | 0 | 39486
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-49 | Bayswater Park Recons of Maint. & Operations-FEMA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-1018 |  | DWIGHT AVE., SEAGIRT BLVD. BET. BEACH 38 ST. AND BAY 32 ST. QUEENS | THIS PROJECT WILL CONSTRUCT A COMFORT STATION AND MAINTENANCE AND OPERATIONS BUILDING IN BAYSWATER PARK | 2022 | 12093 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 11 | 0 | 4780 | 0 | 0 | 0 | 4791
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY4-51 | Bayswater Park Comfort Station Construction-FEMA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-1018 |  | DWIGHT AVE., SEAGIRT BLVD. BET. BEACH 38 ST. AND BAY 32 ST. QUEENS | BAYSWATER PARK COMFORT STATION CONSTRUCTION | 2022 | 7302 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | 10 | 0 | 7292 | 0 | 0 | 0 | 7302
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SANDY6-08 | Asser Levy HMP (Hazard Mitigation Plan ) Funding | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SANDY-SAFETY SURFACE & PAVEMENTS (NON-EMERGENCY) | 2022 | 3732 | 151.94 | 287 | 0 | 202 | 0 | 0 | 0 | 640.94 | 71.51 | 4820 | 0 | 0 | 0 | 0 | 0 | 4891.51
20220309 | QUEENS | 846 | DEPT OF PARKS AND RECREATION | SEQ-TREES | South East Queens Sewer Build-out Trees Restitution | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 400 | SE-0002Q |  | QUEENS BOROWIDE | SOUTH EAST QUEENSTREES RESTITUTION | 2022 | 3000 | 0 | 2918 | 0 | 0 | 0 | 0 | 0 | 2918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BB05-01-A | GI - Cons of ROW Bioswales & Stormwwater GS in BB-005, Ph 1 | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-0169 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | GI - CONSTRUCTION OF RIGHT- OF - WAY BIOSWALES AND STORMWATER GREENSTREETS IN BB-005, PHASE I, STAGE 1 | 2022 | 9636 | 18386.19 | 3677 | 1138 | 0 | 0 | 0 | 0 | 23201.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BB05-02-A | GI - Cons of ROW Bioswales & Stormwwater GS in BB-005, Ph 2 | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-0169 HW-0200 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GI - CONSTRUCTION OF RIGHT- OF - WAY BIOSWALES AND STORMWATER GREENSTREETS IN BB-005, PHASE 2, STAGE 1 | 2022 | 5082 | 17062.92 | 0 | 2143 | 0 | 116 | 0 | 0 | 19321.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-Q | Borough Based Jails New Queens Detention Facility | New Jail Facilities |  | C-0114 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CONSTRUCTION OF NEW QUEENS FACILITY | 2022 | 2113874 | 0 | 40872 | 377924 | 481120 | 519733 | 398095 | 166130 | 1983874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-QGAR | Borough Based Jails Queens Garage | New Jail Facilities |  | C-0114 TF-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CONSTRUCTION OF NE W QUEENS GARAGE | 2022 | 97683 | 25148.52 | 60510 | 8513 | 0 | 0 | 0 | 0 | 94171.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277ELV2 | 25-10 COURT HOUSE SQ.- ELEVATORS | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 401 | CO-0277 CO-0264 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 25-10 COURT HOUSE SQ.- ELEVATORS | 2022 | 1056 | 4378.5 | 215 | 0 | 0 | 0 | 0 | 0 | 4593.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO277FA | 25-10 COURT HOUSE SQ.- FIRE ALARM SYSTEM | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 402 | CO-0264 CO-0277 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 25-10 COURT HOUSE SQUARE - FIRE ALARM SYSTEM | 2022 | 276 | 261 | 842 | 188 | 6532 | 0 | 0 | 0 | 7823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296ELEC | 125-01 QUEENS BLVD - ELECTRICAL, FA, SPRINKLER UPGRADES | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 409 | CO-0296 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 125-01 QUEENS BLVD - ELECTRICAL UPGRADES | 2022 | 51044 | 7806.16 | 0 | 0 | 0 | 20860 | 44119 | 0 | 72785.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO296RF | 125-01 QUEENS BLVD.- ROOF | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 409 | CO-0296 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 125-01 QUEENS BLVD.- ROOF | 2022 | 3359 | 744.04 | 2013 | 17924 | 0 | 0 | 0 | 0 | 20681.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299EXT2 | 89-17 SUTPHIN BLVD.- PLAZA/SIDEWALK RECONSTRUCTION | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 412 | CO-0299 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PLAZA RENOVATION | 2022 | 7006 | 883.79 | 0 | 5779 | 0 | 0 | 0 | 0 | 6662.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | CO299FIRE | 89-17 SUTPHIN BLVD - FIRE ALARM DESIGN & REPLACEMENT | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 401 | CO-0299 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 89-17 SUTPHIN BLVD - FIRE ALARM DESIGN & REPLACEMENT | 2022 | 6944 | 806.15 | 398 | 17673 | 0 | 0 | 0 | 0 | 18877.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ01 | Southeast Queens - DOT Priority Grids Group 1 (SEQPGRD1) | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 400 | SE-0200Q WM-0001 SE-0002Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SOUTHEAST QUEENS PROGRAM JOINT PROJECT BETWEEN DOT AND DEP TO IMPROVEDRAINAGE CONDITIONS - GROUP 1, AS DETERMINED BY DOT. | 2022 | 12229 | 362.76 | 0 | 11324 | 0 | 0 | 0 | 0 | 11686.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | DOTSEQ02 | Southeast Queens - DOT Priority Grids Group 2 (SEQPGRD2) | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 400 | WM-0001 SE-0200Q SE-0002Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | OUTHEAST QUEENS PROGRAM JOINT PROJECT BETWEEN DOT AND DEP TO IMPROVE DRAINAGE CONDITIONS - GROUP 2, AS DETERMINED BY DOT. | 2022 | 11085 | 382.08 | 0 | 0 | 1462 | 13641 | 0 | 0 | 15485.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0002 | DCAS - Queens Civil Court | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 412 | PU-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | QUEENS CIVIL COURT | 2022 | 3005 | 5477.4 | 101 | 500 | 0 | 0 | 0 | 0 | 6078.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | E16-0004 | DSNY - Queens 7 District Garage Annex | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 407 | PU-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | QUEENS 7 DISTRICT GARAGE ANNEX | 2022 | 2162 | 1939.59 | 50 | 24 | 0 | 0 | 0 | 0 | 2013.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQN22 | Reconstruction of Existing Sewers, North Queens | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 400 | EP-0007 SE-0002Q |  |  | RECONSTRUCTION OF EXISTING SEWERS, NORTH QUEENS | 2022 | 9352 | 223 | 7577 | 0 | 0 | 0 | 0 | 0 | 7800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQN23 | Reconstruction of Existing Sewers, North Queens | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 400 | EP-0007 SE-0002Q |  |  | RECONSTRUCTION OF EXISTING SEWERS, NORTH QUEENS. THIS IS A 1 YEAR CONTRACT. THE TARGETED START DATE FOR THIS CONTRACT IS AS SOON AS THE PREVIOUS CONTRACT EC-SEQN22, EXPIRES. | 2022 | 8500 | 0 | 0 | 8500 | 0 | 0 | 0 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQS22 | Reconstruction of Existing Sewers, South Queens | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 400 | EP-0007 SE-0002Q |  |  | THIS IS A ONE YEAR CONTRACT. THE TARGETED CONTRACT START DATE IS 11/17/2021. | 2022 | 10478 | 105 | 11532 | 0 | 0 | 0 | 0 | 0 | 11637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEQS23 | Reconstruction of Existing Sewers, South Queens | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 400 | EP-0007 SE-0002Q |  |  | RECONSTRUCTION OF EXISTING SEWERS, SOUTH QUEENS. THIS IS A 1 YEAR CONTRACT. THE TARGETED START DATE FOR THIS CONTRACT IS AS SOON AS THE PREVIOUS CONTRACT, EC-SEQS22, EXPIRES. | 2022 | 9500 | 0 | 0 | 9500 | 0 | 0 | 0 | 0 | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F175EC268 | NEW FIREHOUSE - EC268 | NEW FACILITIES AND RENOVATIONS | 414 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NEW FIREHOUSE - EC268 | 2022 | 22000 | 2479.68 | 0 | 18412 | 0 | 0 | 0 | 0 | 20891.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | F204INFRA | Fort Totten Infrastructure Upgrade | NEW FACILITIES AND RENOVATIONS | 400 | F-0204 |  |  | FORT TOTTEN INFRASTRUCTURE UPGRADE | 2022 | 57686 | 3029.27 | 0 | 0 | 52756 | 0 | 0 | 0 | 55785.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCJA03-3B | GI - CONS OF ROW GI IN JAMAICA BAY CSO AREAS JAM-03 & JAM-3A | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-0169 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CONSTRUCTION OF RIGHT-OF-WAY GREEN INFRASTRUCTURE IN THE JAMAICA BAY CSO AREAS JAM-003 AND JAM-003A | 2022 | 20497 | 18910.12 | 0 | 350 | 0 | 0 | 0 | 0 | 19260.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GCTI10-1B | CONS OF ROW GI FLUSHING CRK CSO TRIB AREA TI-10, ST 1, PH B | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-0169 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CONSTRUCTION OF ROW GREEN INFRASTRUCTURE IN FLUSHING CREEK CSO TRIBUTARY AREA TI-10, STAGE1, PHASE B | 2022 | 18547 | 18408.03 | 0 | 624 | 0 | 0 | 0 | 0 | 19032.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | GQTI03-23 | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO | GREEN INFRASTRUCTURE PROGRAM | 400 | WP-0169 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO | 2022 | 18714 | 8913.61 | 18965 | 0 | 0 | 0 | 0 | 0 | 27878.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED216S | PED BRIDGE - 216 ST (Q) | FAIR BRIDGES | 400 411 | HB-0215 SE-1000 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PED BRIDGE - 216 ST (Q) | PED BRIDGE - 216 ST (Q) | 2022 | 6321 | 2787.73 | 790 | 8 | 0 | 0 | 0 | 0 | 3585.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HBPED800Q | PED BRIDGE - PORPOISE BR & TIDE GATE(SANDY4-30, 4-31)QED1062 | FAIR BRIDGES | 400 | P-0245Q WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | PED BRIDGE - PORPOISE BRIDGE AND TIDE GATE | PED BRIDGE - PORPOISE BRIDGE AND TIDE GATE | 2022 | 65656 | 7044.61 | 155 | 51031 | 0 | 0 | 0 | 0 | 58230.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115BWFA | BRIARWOOD - FIRE ALARM UPGRADE | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 |  |  | BRIARWOOD - FIRE ALARM UPGRADE | 2022 | 1082 | 1260.65 | 152 | 0 | 0 | 0 | 0 | 0 | 1412.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SGFA | SPRINGFIELD GARDEN - FIRE ALARM SYSTEM UPGRADE | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 |  |  | SPRINGFIELD GARDEN - FIRE ALARM SYSTEM UPGRADE | 2022 | 408 | 1036.31 | 52 | 100 | 0 | 0 | 0 | 0 | 1188.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82CORHC | Corona Health Center-Exterior Facade, Basement and Lobby | CLINIC RENOVATION AND REHABILITATION |  | HL-0082 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CORONA HEALTH CENTER EXTERIOR FACADE, BASEMENT AND LOBBY | 2022 | 8200 | 1465.75 | 0 | 8816 | 0 | 0 | 0 | 0 | 10281.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCH4C1 | Safe Routes to Schools - Phase 4C1 | PRIMARY STREET RECONSTRUCTION | 400 | HW-0988 WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SAFE ROUTES TO SCHOOLS - PHASE 4C1 | SAFE ROUTES TO SCHOOLS - PHASE 4C1 | 2022 | 4209 | 7911.76 | 378 | 0 | 0 | 0 | 0 | 0 | 8289.76 | 62.1 | 0 | 0 | 0 | 0 | 0 | 0 | 62.1
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPQN | SAFE ROUTES TO SCHOOLS- QUEENS | PRIMARY STREET RECONSTRUCTION | 400 | HW-0988 HW-D103 HW-D105 |  | SAFE ROUTES TO SCHOOLS- QUEENS | SAFE ROUTES TO SCHOOLS- QUEENS | 2022 | 11289 | 1765.37 | 0 | 389 | 10700 | 0 | 0 | 0 | 12854.37 | 0 | 0 | 0 | 1174 | 0 | 0 | 0 | 1174
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD10311 | 111th Street Malls (QED-1049) | PRIMARY STREET RECONSTRUCTION | 400 403 404 | HW-D103 HW-0001Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 111TH ST MALLS | 111TH ST MALLS | 2022 | 2700 | 1507.5 | 0 | 2869 | 15707 | 0 | 0 | 0 | 20083.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWHARPADM | Harper Street Administration Building Reconstruction DB | FACILITY RECONSTRUCTION | 400 | HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HARPER STREET ADMINISTRATION BUILDING RECONSTRUCTION | 2022 | 40000 | 0 | 1529 | 121187 | 7522 | 0 | 840 | 0 | 131078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWHARPER | Reconstruction of Harper Street Asphalt Plant - Construction | FACILITY RECONSTRUCTION | 400 | HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RECONSTRUCTION OF HARPER STREET ASPHALT PLANT | RECONSTRUCTION OF HARPER STREET ASPHALT PLANT | 2022 | 37801 | 18942.04 | 394 | 38528 | 0 | 0 | 0 | 0 | 57864.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP14QTA | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - QUEENS | PEDESTRIAN RAMP CONSTRUCTION | 400 | HW-0200 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - QUEENS | CITYWIDE COMPLEX PED RAMPS (TRANSIT AUTHORITY) - QUEENS | 2022 | 3102 | 6294.28 | 208 | 0 | 0 | 0 | 0 | 0 | 6502.28 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 33
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ010Q | Corona Plaza | PRIMARY STREET RECONSTRUCTION | 400 403 404 | HW-1684 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CORONA PLAZA | CORONA PLAZA | 2022 | 3500 | 8765.18 | 251 | 0 | 0 | 0 | 0 | 0 | 9016.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPMWBEQ | Installation of Standard Pedestrian Ramps - MWBE | PEDESTRIAN RAMP CONSTRUCTION | 400 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | INSTALLATION OF STANDARD PEDESTRIAN RAMPS - MWBE | INSTALLATION OF STANDARD PEDESTRIAN RAMPS - MWBE | 2022 | 321 | 0 | 534 | 0 | 0 | 0 | 0 | 0 | 534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19Q2 | Pedestrian Ramp Rehabilitation - Queens | PEDESTRIAN RAMP CONSTRUCTION | 400 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PEDESTRIAN RAMP REHABILITATION - QUEENS | 2022 | 15471 | 14842.5 | 376 | 0 | 0 | 0 | 0 | 0 | 15218.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q1 | Pedestrian Ramp Rehabilitation - Queens | PEDESTRIAN RAMP CONSTRUCTION | 400 | HW-0200 |  | PEDESTRIAN RAMP REHABILITATION - QUEENS | PEDESTRIAN RAMP REHABILITATION - QUEENS | 2022 | 17211 | 5747 | 8306 | 1181 | 2583 | 0 | 0 | 0 | 17817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q2 | Pedestrian Ramp Rehabilitation - Queens | PEDESTRIAN RAMP CONSTRUCTION | 400 | HW-0200 |  | PEDESTRIAN RAMP REHABILITATION - QUEENS | PEDESTRIAN RAMP REHABILITATION - QUEENS | 2022 | 17211 | 2965.16 | 11288 | 1000 | 2514 | 0 | 0 | 0 | 17767.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20Q3 | Pedestrian Ramp Rehabilitation - Queens | PEDESTRIAN RAMP CONSTRUCTION | 400 | HW-0200 |  | PEDESTRIAN RAMP REHABILITATION - QUEENS | PEDESTRIAN RAMP REHABILITATION - QUEENS | 2022 | 17211 | 2861.23 | 11129 | 961 | 2716 | 0 | 0 | 0 | 17667.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR20QC | Non-Standard Upgrades Ped Ramp - Queens | PEDESTRIAN RAMP CONSTRUCTION | 400 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COMPLEX UPGRADES PED RAMP - QUEENS | COMPLEX UPGRADES PED RAMP - QUEENS | 2022 | 6088 | 865.25 | 0 | 0 | 5659 | 0 | 0 | 0 | 6524.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR21Q1 | Rehabilitation of Standard Ped Ramps - Queens | PEDESTRIAN RAMP CONSTRUCTION | 400 | HW-0200 |  |  | REHABILITATION OF STANDARD PED RAMPS - QUEENS | 2022 | 16533 | 200 | 21054 | 0 | 0 | 0 | 0 | 0 | 21254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR22Q1 | Rehabilitation of Standard Ped Ramps - Queens | PEDESTRIAN RAMP CONSTRUCTION | 400 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | REHABILITATION OF STANDARD PED RAMPS - QUEENS | REHABILITATION OF STANDARD PED RAMPS - QUEENS | 2022 | 15958 | 0 | 6128 | 6253 | 3126 | 0 | 0 | 0 | 15507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ100SBB | Woodhaven Blvd SBS Phase B (QED-1040B) | TRAFFIC WORK IN CONJUNCTION WITH HIGHWAY RECONSTRUCTION | 400 | HW-1684 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WOODHAVEN BLVD SBS PHASE B | WOODHAVEN BLVD SBS PHASE B | 2022 | 48691 | 2834.55 | 0 | 0 | 0 | 46103 | 0 | 0 | 48937.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1182B | Broad Channel Bulkheads - Phase II (SEQ200586) | PRIMARY STREET RECONSTRUCTION | 400 | TF-0002 HW-0001Q SE-0200Q WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BROAD CHANNEL BULKHEADS PHASE II | BROAD CHANNEL BULKHEADS PHASE II | 2022 | 19167 | 25210.13 | 12 | 8801 | 0 | 0 | 258 | 0 | 34281.13 | 12.9 | 0 | 0 | 0 | 0 | 0 | 0 | 12.9
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1184A | James Court Roadway & Bulkhead, Queens (Joint Bid) | PRIMARY STREET RECONSTRUCTION | 400 412 | HW-D103 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | JAMES COURT ROADWAY AND BULKHEAD | JAMES COURT ROADWAY AND BULKHEAD | 2022 | 1948 | 3860.73 | 280 | 0 | 0 | 0 | 0 | 0 | 4140.73 | 107.25 | 0 | 0 | 0 | 0 | 0 | 0 | 107.25
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1187 | Westbourne-Dunbar Roadways & Bulkheads (SAND1187, SEQ200595) | PRIMARY STREET RECONSTRUCTION | 400 414 | HW-0001Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WESTBOURNE - DUNBAR ROADWAYS & BULKHEADS | WESTBOURNE - DUNBAR ROADWAYS & BULKHEADS | 2022 | 5000 | 1834.02 | 0 | 0 | 0 | 0 | 0 | 39595 | 41429.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190A | Reconstruction of Queens Blvd Phase 1 (QED-1042A) | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF QUEENS BLVD PHASE 1 | RECONSTRUCTION OF QUEENS BLVD PHASE 1 | 2022 | 49520 | 10742.53 | 0 | 0 | 65406 | 0 | 0 | 0 | 76148.53 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 2000
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190B | Reconstruction of Queens Blvd Phase 2( QED-1042B) | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RECONSTRUCTION OF QUEENS BLVD PHASE 2 | RECONSTRUCTION OF QUEENS BLVD PHASE 2 | 2022 | 81984 | 2539.48 | 0 | 0 | 0 | 70597 | 0 | 0 | 73136.48 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 10000
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1190-C | Reconstruction of Queens Blvd Phase 3 | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q HW-D103 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION OF QUEENS BLVD, PHASE 3 | 2022 | 98817 | 2121.64 | 0 | 0 | 0 | 0 | 96722 | 0 | 98843.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1193 | Union Turnpike Curb Repair | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | UNION TURNPIKE CURB REPAIR | UNION TURNPIKE CURB REPAIR | 2022 | 24709 | 720 | 0 | 7523 | 0 | 0 | 0 | 0 | 8243 | 0 | 0 | 215 | 0 | 0 | 0 | 0 | 215
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1195 | Colfax and Murdock Street Raising (SEQNS003) | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | COLFAX AND MURDOCK STREET RAISING | 2022 | 29735 | 971.33 | 0 | 9317 | 0 | 0 | 0 | 0 | 10288.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1198 | Reconst. of Beach Channel Drive-Phase B Non Sandy(QED-1030B) | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RECONSTRUCTION OF BEACH CHANNEL DRIVE -- PHASE B NON SANDY | RECONSTRUCTION OF BEACH CHANNEL DRIVE -- PHASE B NON SANDY | 2022 | 37214 | 0 | 224 | 26 | 0 | 0 | 38976 | 0 | 39226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ1201 | ASTORIA BLVD SAFETY IMPROVEMENTS | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q HW-D103 |  | 34TH AVE MALLS IMPROVEMENTS | 34TH AVE MALLS IMPROVEMENTS | 2022 | 750 | 0 | 1609 | 0 | 0 | 11341 | 0 | 0 | 12950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ121B3 | RECONSTRUCTION OF SOUTH JAMAICA AREA (SEQ200562) | PRIMARY STREET RECONSTRUCTION | 412 | HW-0121 HW-0061 HW-0200 TF-0002 TF-0502 HW-0944 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | SOUTH JAMAICA QUEENS | RECON OF SOUTH JAMAICA AREA | 2022 | 10404 | 3469.01 | 0 | 1259 | 30411 | 0 | 0 | 0 | 35139.01 | 0 | 0 | 0 | 717 | 0 | 0 | 0 | 717
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ200578 | SEQ - Foch Boulevard Safety Improvements (SEQ200578) | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SE-Q FOCH BOULEVARD SAFETY IMPROVEMENTS | SE-Q FOCH BOULEVARD SAFETY IMPROVEMENTS | 2022 | 6653 | 4974.09 | 193 | 1503 | 1529 | 0 | 0 | 0 | 8199.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ274F2 | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 (SEQ200592) | PRIMARY STREET RECONSTRUCTION | 400 | HW-0061 HW-0274 |  | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 | RECON OF STREETS IN ROSEDALE AREA - PHASE 2 | 2022 | 22140 | 2305.7 | 0 | 1067 | 41914 | 0 | 0 | 0 | 45286.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ631B-3 | ALMEDA AV - PHASE III | PRIMARY STREET RECONSTRUCTION | 414 | SE-087HW | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | ALMEDA AV - PHASE III | ALMEDA AV - PHASE III | 2022 | 12332 | 25.4 | 0 | 0 | 0 | 0 | 0 | 1284 | 1309.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ662G | Springfield Gardens Phase V (SE-862) | PRIMARY STREET RECONSTRUCTION | 413 | HW-0001Q HW-0061 HW-0662 HW-0200 TF-0002 TF-0502 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | ROCKAWAY BLVD | ROCKAWAY BLVD | 2022 | 24283 | 1681.27 | 602 | 1607 | 0 | 1500 | 18711 | 0 | 24101.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ724B | Recon of Streets in Brookville-Edgewood Triangle (SEQ200519) | PRIMARY STREET RECONSTRUCTION | 413 | HW-0061 HW-0001Q HW-0724 HW-0200 TF-0002 TF-0502 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BROOKVILLE-EDGEWOOD TRIANGE ROSEDALE QUEENS | BROOKVILLE-EDGEWOOD TRIANGE | 2022 | 11889 | 7565.36 | 380 | 1080 | 0 | 15657 | 0 | 0 | 24682.36 | 0 | 0 | 0 | 435 | 0 | 0 | 0 | 435
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ787B3 | Sutter Ave, Etc - Phase V (B3) | PRIMARY STREET RECONSTRUCTION | 402 | HW-0061 HW-0787 HW-0200 TF-0002 TF-0502 HW-0001Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | SUTTER AVE, ETC - PHASE V (B3) | SUTTER AVE, ETC - PHASE V (B3) | 2022 | 513 | 476.5 | 65 | 0 | 0 | 0 | 0 | 1751 | 2292.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ788CS | Court Square Pedestrian Improvements | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q |  | COURT SQUARE PEDESTRIAN IMPROVEMENTS | COURT SQUARE PEDESTRIAN IMPROVEMENTS | 2022 | 18187 | 0 | 0 | 1709 | 0 | 0 | 15826 | 0 | 17535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ976 | SEQ - FRANCIS LEWIS BLVD & 93RD AVE (QED-976) | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SEQ FRANCIS LEWIS BLVD - BUS PADS AND STEEL-FACED CURBS | 2022 | 725 | 0 | 0 | 0 | 0 | 0 | 0 | 725 | 725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQ985 | SHORE ROAD RECONSTRUCTION (SEQ200585) | PRIMARY STREET RECONSTRUCTION | 400 407 | HW-0001Q TF-0002 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SHORE ROAD FROM EAST DRIVE TO 36TH AVE, DOUGLASTON | 2022 | 7725 | 8117.3 | 4353 | 0 | 0 | 0 | 0 | 0 | 12470.3 | 213.45 | 0 | 0 | 0 | 0 | 0 | 0 | 213.45
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWQF033 | 28-11 QPN 7TH FL REHABILITATION | FACILITY RECONSTRUCTION | 400 402 | HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | QUEENS | COLLEGE POINT WINDOWS | 2022 | 3347 | 128 | 2075 | 1280 | 11751 | 0 | 0 | 0 | 15234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q1 | Prior Notice Sidewalks- Queens | SIDEWALK RECONSTRUCTION | 400 | HW-0200 P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PRIOR NOTICE SIDEWALKS- QUEENS | PRIOR NOTICE SIDEWALKS- QUEENS | 2022 | 8000 | 4726.85 | 2315 | 0 | 550 | 0 | 0 | 0 | 7591.85 | 866 | 0 | 0 | 0 | 0 | 0 | 0 | 866
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020Q2 | Prior Notice Sidewalks- Queens | SIDEWALK RECONSTRUCTION | 400 | HW-0200 WM-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PRIOR NOTICE SIDEWALKS- QUEENS | PRIOR NOTICE SIDEWALKS- QUEENS | 2022 | 7999 | 4723.28 | 1265 | 960 | 0 | 0 | 0 | 0 | 6948.28 | 865 | 0 | 0 | 0 | 0 | 0 | 0 | 865
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021Q | PRIOR NOTICE SIDEWALK - QUEENS | SIDEWALK RECONSTRUCTION | 400 | HW-0200 P-1331 HW-Q001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PRIOR NOTICE SIDEWALKS | 2022 | 12350 | 0 | 10032 | 0 | 0 | 0 | 0 | 0 | 10032 | 0 | 1914 | 0 | 0 | 0 | 0 | 0 | 1914
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQARVEXPN | Arverne Library - Replacement facility | REPLACEMENT BRANCHES | 400 | LQ-0122 LQ-Q122 LQ-D122 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ARVERNE LIBRARY EXPANSION | 2022 | 7600 | 1780.14 | 66 | 14982 | 0 | 0 | 0 | 0 | 16828.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQASADA | ASTORIA - Brach renovation with ADA | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-D122 LQ-0122 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ASTORIA ADA RENOVATION FY16 CM CONSTANTINIDES | 2022 | 1479 | 1567.26 | 0 | 11051 | 0 | 0 | 0 | 0 | 12618.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQAUB-RG | Auburndale - Reading Garden | SUPPORT SERVICES IMPROVEMENTS |  | LQ-D122 LQ-Q122 |  |  | THIS PROJECT IS FOR THE AUBURNDALE READING GARDEN. | 2022 | 940 | 0 | 0 | 941 | 0 | 0 | 0 | 0 | 941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBPEXPN | BAISLEY PARK - Branch Renovation | REPLACEMENT BRANCHES | 412 | LQ-0122 LQ-Q122 LQ-D122 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BAISLEY PARK - EXPANSION | 2022 | 6500 | 1367.92 | 0 | 55 | 10780 | 0 | 0 | 0 | 12202.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBTRENOV | BAY TERRACE: Branch Renovation and Expansion | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-Q122 LQ-D122 LQ-0122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BAY TERRACE RENOVATION | 2022 | 3822 | 0 | 0 | 849 | 0 | 5628 | 0 | 0 | 6477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQBW-EXP | Briarwood: Branch Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-D122 LQ-0122 |  |  | ROOF AND EXTERIOR UPGRADE | 2022 | 12901 | 25 | 0 | 0 | 0 | 1132 | 0 | 10582 | 11739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQC122-JH | JACKSON HEIGHTS - Branch Expansion & Renovation | REPLACEMENT BRANCHES | 403 | LQ-D122 LQ-0122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 35-51 81ST ST, JACKSON HEIGHTS 11372 | EXPANSION OF EXISTING BUILDING | 2022 | 2250 | 0 | 1983 | 408 | 0 | 1135 | 36629 | 0 | 40155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQCLDC-CE | Central Library: Rehabilitation of Ceilings | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-0122 LQ-D122 |  |  | CENTRAL LIBRARY: REHABILITATION OF CHILDREN'S LIBRARY DISCOVERY CENTER CEILINGS. | 2022 | 392 | 0 | 355 | 0 | 0 | 0 | 0 | 0 | 355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122BR2 | BROADWAY LIBRARY - RENOVATION (PHASE THREE AND FOUR) | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 401 | LQ-D122 LQ-Q122 LQ-0122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  |  | 2022 | 1575 | 895.85 | 4591 | 0 | 0 | 0 | 0 | 0 | 5486.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-CM | CAMBRIA HEIGHTS - Lower Level Renovation | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 413 | LQ-D122 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | RENOVATION | 2022 | 2800 | 1421.02 | 0 | 0 | 0 | 71 | 0 | 0 | 1492.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122GL2 | GLENDALE LIBRARY RENOVATION | ESSENTIAL RECONSTRUCTION OF FACILITIES | 405 | LQ-0122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION | 2022 | 2803 | 9609.65 | 130 | 0 | 0 | 0 | 0 | 0 | 9739.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122HO1 | Hollis Library - Building Infrastructure | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 408 | LQ-D122 LQ-Q122 LQ-0122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BUILDING INFRASTRUCTURE | 2022 | 3125 | 1750.16 | 0 | 375 | 0 | 5592 | 5719 | 0 | 13436.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-QW | QUEENS WEST BRANCH | REPLACEMENT BRANCHES | 401 | LQ-0122 LQ-D122 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | LONG ISLAND CITY | NEW BRANCH FACILITY | 2022 | 2000 | 29047.1 | 302 | 1526 | 0 | 0 | 0 | 0 | 30875.1 | 20269.67 | 63 | 0 | 0 | 0 | 0 | 0 | 20332.67
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122RO2 | ROCHDALE VILLAGE - HVAC & Controls | ESSENTIAL RECONSTRUCTION OF FACILITIES | 412 | LQ-D122 LQ-0122 LQ-Q122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BOILER & CONTROLS | 2022 | 460 | 566.71 | 0 | 1430 | 0 | 0 | 0 | 0 | 1996.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-S2 | STEINWAY - Phase II Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 401 | LQ-D122 LQ-0122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STEINWAY RENOVATION | 2022 | 2405 | 7256 | 832 | 628 | 0 | 0 | 0 | 0 | 8716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-WN | WOODHAVEN - Renovation | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 409 | LQ-D122 LQ-Q122 LQ-0122 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACEMENT OF WINDOWS & DOORS | 2022 | 200 | 1655.85 | 0 | 0 | 16849 | 0 | 0 | 0 | 18504.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQD122-WP | WINDSOR PARK - Renovation | REPLACEMENT BRANCHES | 411 | LQ-D122 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RENOVATION | 2022 | 1650 | 1555.52 | 0 | 0 | 0 | 102 | 0 | 0 | 1657.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQDL-NEW | DOUGLASTON: Replacement Facility | REPLACEMENT BRANCHES | 400 | LQ-0122 LQ-Q122 LQ-D122 |  |  | REPLACEMENT FACILITY | 2022 | 23968 | 2713.32 | 0 | 30 | 0 | 726 | 24822 | 0 | 28291.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19BKP | BAISLEY PARK: AC Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-0122 LQ-D122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BAISLEY PARK: AC REPLACEMENT | 2022 | 1365 | 1309 | 187 | 0 | 0 | 0 | 0 | 0 | 1496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19BPK | BAISLEY PARK: New Boiler | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-0122 LQ-D122 |  |  | BAISLEY PARK: NEW BOILER | 2022 | 275 | 599.4 | 840 | 0 | 0 | 0 | 0 | 0 | 1439.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FFA | FLUSHING: FIRE ALARM | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-0122 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FLUSHING: FIRE ALARM | 2022 | 551 | 0 | 411 | 45 | 3155 | 0 | 0 | 0 | 3611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQEM19FLU | FLUSHING:Emergency Functionality | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-0122 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FLUSHING:EMERGENCY FUNCTIONALITY | 2022 | 1190 | 0 | 163 | 912 | 0 | 0 | 0 | 0 | 1075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQFLELV | FLUSHING LIBRARY - CONSTRUCTION OF SECOND ELEVATOR | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-Q122 LQ-0122 LQ-D122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCTION OF SECOND ELEVATOR AT FLUSHING. BP FUNDED FY 16 | 2022 | 2990 | 956.9 | 5951 | 3414 | 0 | 0 | 0 | 0 | 10321.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQHIROOF | HILLCREST ROOF | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-D122 LQ-0122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HILLCREST ROOF - FY 16 | 2022 | 903 | 493.78 | 0 | 3004 | 0 | 0 | 0 | 0 | 3497.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQLAROOF | LAURELTON ROOF | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-0122 LQ-D122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LAURELTON ROOF - | 2022 | 860 | 433.84 | 50 | 1780 | 0 | 0 | 0 | 0 | 2263.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQOZROOF | OZONE PARK ROOF REPLACEMENT | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-0122 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | OZONE PARK ROOF REPLACEMENT | 2022 | 800 | 1293.96 | 79 | 0 | 0 | 0 | 0 | 0 | 1372.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-BL | Masonry Repairs - Bellerose | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 413 | LQ-0122 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MASONRY REPAIRS - BL | 2022 | 634 | 1072.14 | 47 | 0 | 0 | 0 | 0 | 0 | 1119.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-DL | MULTIBRANCH (C, DL, NO, RO, S &SZ) - Roof Replacements | ESSENTIAL RECONSTRUCTION OF FACILITIES | 411 | LQ-0122 LQ-D122 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ROOF REPLACEMENT | 2022 | 1620 | 2020.83 | 247 | 0 | 0 | 0 | 0 | 0 | 2267.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122EE2 | EAST ELMHURST - Expansion | REPLACEMENT BRANCHES | 403 | LQ-Q122 LQ-0122 LQ-D122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EAST ELMHURST EXPANSION | 2022 | 2967 | 10919.19 | 642 | 286 | 0 | 0 | 0 | 0 | 11847.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-FA | FAR ROCKAWAY - Replacement Facility | REPLACEMENT BRANCHES | 414 | LQ-Q122 LQ-D001 LQ-0122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DESIGN, CONSTRUCTION, OUTFITTING FOR REPLACEMENT FAR ROCKAWAY LIBRARY | 2022 | 1250 | 27059.61 | 116 | 6029 | 0 | 0 | 0 | 0 | 33204.61 | 2142.88 | 0 | 6097 | 0 | 0 | 0 | 0 | 8239.88
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-KE | KEW GARDENS HILLS - Renovation and Expansion | REPLACEMENT BRANCHES | 408 | LQ-D122 LQ-0122 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 72-33 VLEIGH PLACE, FLUSHING, NEW YORK 11367 | DESIGN / CONSTRUCTION FOR EXPANSION OF KEW GARDENS HILLS LIBRARY | 2022 | 3100 | 11257.94 | 59 | 0 | 0 | 0 | 0 | 0 | 11316.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQ122-RG | REGO PARK LIBRARY - REPLACEMENT FACILITY | REPLACEMENT BRANCHES | 406 | LQ-0122 LQ-D122 LQ-Q122 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 91-41 63RD DRIVE, REGO PARK, NEW YORK 11374 | DESIGN, CONSTRUCTION AND OUTFITTING FOR NEW REPLACEMENT FACILITY | 2022 | 1250 | 4111.78 | 32 | 117 | 0 | 33829 | 0 | 0 | 38089.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQBHHVAC | QUEENSBORO HILL - HVAC | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-D122 LQ-0122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | QUEENSBORO HILL HVAC | 2022 | 815 | 399.78 | 0 | 2510 | 0 | 0 | 0 | 0 | 2909.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQVHVAC | QUEENS VILLAGE - HVAC | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-0122 LQ-D122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | QUEENS VILLAGE HVAC | 2022 | 1000 | 377.81 | 0 | 3253 | 0 | 0 | 0 | 0 | 3630.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQQVROOF | QUEENS VILLAGE - ROOF | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-0122 LQ-D122 |  |  | QUEENS VILLAGE ROOF | 2022 | 761 | 185.99 | 0 | 733 | 0 | 0 | 0 | 0 | 918.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQRDMASON | RIDGEWOOD - MASONRY | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-0122 LQ-D122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RIDGEWOOD MASONRY | 2022 | 1718 | 481.76 | 0 | 3029 | 0 | 0 | 0 | 0 | 3510.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSARENOV | ST. ALBANS RENOVATION | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 | LQ-Q122 LQ-D122 LQ-D001 LQ-0122 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ST. ALBANS RENOVATION | 2022 | 2485 | 0 | 0 | 0 | 19016 | 662 | 0 | 216 | 19894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | LQSEHVAC | SEASIDE -HVAC | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 400 | LQ-D122 LQ-0122 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SEASIDE HVAC | 2022 | 645 | 205.94 | 0 | 2409 | 0 | 0 | 0 | 0 | 2614.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-FAR | NDF Far Rockaway Replacement Facility | REPLACEMENT BRANCHES | 414 | ED-0384 |  |  | DESIGN, CONSTRUCTION ,AND OUTFITTING FOR REPLACEMENT OF FAR ROCKAWAY BRANCH | 2022 | 11400 | 10352.63 | 1047 | 0 | 0 | 0 | 0 | 0 | 11399.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-407BHI3 | BOWNE HOUSE INTERIOR RESTORATIONS | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-Q245 P-D019 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | QUEENS | BOWNE HOUSE INTERIOR RESTORATIONS | 2022 | 1875 | 1223.58 | 0 | 0 | 0 | 3519 | 0 | 0 | 4742.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-407BHV4 | BOWNE HOUSE VISITORS CENTER Q022 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 400 | P-D019 P-Q245 P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BOWNE HOUSE VISITORS CENTER Q022 | 2022 | 2465 | 45.74 | 0 | 0 | 0 | 4909 | 0 | 0 | 4954.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | P-4RCKGHQ | Rockaway Operational Headquarters, SANDY4-50 and Sandy4-11 | BEACHES AND BOARDWALKS | 400 | P-1018 |  |  | ROCKAWAY OPERATIONAL HEADQUARTERS | 2022 | 16796 | 0 | 294 | 0 | 0 | 0 | 0 | 0 | 294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO002-116 | NEW 116TH PCT | POLICE FACILITIES | 400 | PO-0002 PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NEW PCT | 2022 | 70000 | 86824.92 | 6970 | 10229 | 1795 | 0 | 0 | 0 | 105818.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79BMAHW | 114TH PCT PLUMBING SYSTEM REPLACEMENT | POLICE FACILITIES | 400 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | PLUMBING SYSTEM | 2022 | 436 | 1902.23 | 77 | 0 | 0 | 0 | 0 | 0 | 1979.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV001SELM | LAH - Louis Armstrong House - Administration Facility | ESSENTIAL RECONSTRUCTION OF FACILITIES | 403 | PV-0001 PV-D001 PV-Q001 PV-0467 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SCOPE OF WORK INCLUDES: UPGRADE ELECTRICAL SYSTEMS, NEW MECHANICAL SYSTEMS, ADA COMPLIANT OFFICES ND REST ROOMS. ALL CONSTRUCTION WORK WILL COMPLY WITH ALL BUILDING CODES FOR ADMINISTRATION OFFICES AND STORAGE FACILITIES. | 2022 | 1265 | 1113.13 | 10 | 0 | 3082 | 0 | 0 | 0 | 4205.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040ELEV | FTH - Flushing Town Hall Elevator Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 407 | PV-Q040 PV-0040 PV-D040 PV-Q467 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FLUSHING TOWN HALL - ELEVATOR: COMPLETE REPLACEMENT OF ELEVATOR. | 2022 | 813 | 364.55 | 881 | 0 | 0 | 0 | 0 | 0 | 1245.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV040HVAC | FTH - Flushing Town Hall HVAC System Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 407 | PV-Q040 PV-D040 PV-0040 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FLUSHING TOWN HALL - ROOFTOP AIR CONDITIONING UNIT: REPLACEMENT ROOFTOP AIR CONDITIONING UNITS: ONE (1) LARGER 50-TON UNIT, AND TWO (2) SMALLER 3-TON UNITS. | 2022 | 809 | 0 | 245 | 0 | 1332 | 0 | 0 | 0 | 1577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272EDUC | QBG - Queens Botanical Garden Educ Bldg Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 407 | PV-D272 PV-Q272 PV-0272 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | QUEENS BOTANICAL GARDEN - EDUCATION BUILDING: CONSTRUCTION/RENOVATION OF EDUCATION BUILDING | 2022 | 20152 | 2878.18 | 1 | 0 | 24535 | 0 | 0 | 0 | 27414.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV272SITE | QBG - Site-wide Exterior Improvements | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-D272 PV-0272 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 43-50 MAIN STREET, QUEENS, NY | SITEWIDE LANDSCAPE IMPROVEMENTS. | 2022 | 903 | 804.87 | 0 | 41 | 0 | 0 | 0 | 0 | 845.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274CHLL | NYHOS - New York Hall of Science - Chiller Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 407 | PV-D274 PV-0274 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NEW YORK HALL OF SCIENCE CHILLER REPLACEMENT: REPLACEMENT AND MODERNIZATION OF TWO OUTDATED CHILLER UNITS | 2022 | 3083 | 3626.17 | 1015 | 0 | 0 | 1766 | 0 | 0 | 6407.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV274KITR | NYHOS - NY Hall of Science,Great Hall, Kitchen & Restroom | ESSENTIAL RECONSTRUCTION OF FACILITIES | 401 | PV-Q274 PV-D274 PV-0274 PV-D467 | PROJECT DELAYED PENDING RELEASE OF NEW TECHNOLOGY |  | SCOPE OF WORK IS THE RECONSTRUCTION OF THE GREAT HALL KITCHEN AND THERECONSTRUVTION OG THE GREAT HALL RESTROOMS. | 2022 | 2449 | 569.68 | 2614 | 0 | 0 | 2476 | 0 | 0 | 5659.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV291-QM2 | QMA - Queen's Museum of Art Expansion Phase II | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-Q291 PV-0291 PV-D291 PV-D467 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | QMA | 2022 | 2315 | 0 | 1705 | 0 | 13033 | 7080 | 3203 | 0 | 25021 | 0 | 0 | 0 | 0 | 3239 | 0 | 0 | 3239
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV466BOIL | QTIP - Queens Theater in the Park Boiler | ESSENTIAL RECONSTRUCTION OF FACILITIES | 400 407 | PV-0466 PV-Q466 |  |  | CONSTRUCTION | 2022 | 1041 | 0 | 201 | 1341 | 0 | 0 | 0 | 0 | 1542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PV501BOIL | PS1 - PS1 Boiler Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-0501 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACEMENT OF TWO BOILERS AT PS1 | 2022 | 1000 | 3544.59 | 387 | 0 | 0 | 0 | 0 | 0 | 3931.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW293QBLV | 120-55 QUEENS BLVD - FIRE ALARM | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 401 | PW-0293 |  |  | 120-55 QUEENS BLVD - FIRE ALARM | 2022 | 3119 | 9391.36 | 1161 | 1738 | 0 | 0 | 0 | 0 | 12290.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77417DA | 120-55 QUEENS BLVD.- QUEENS DA TRAINING ROOM | REHABILITATION OF CITY-OWNED OFFICE SPACE | 401 | PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 120-55 QUEENS BLVD.- QUEENS DA TRAINING ROOM | 2022 | 1705 | 1029.11 | 4627 | 615 | 0 | 0 | 0 | 0 | 6271.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77417P2 | 120-55 QUEENS BLVD - PLAZA, STEPS AND ENTRANCE | REHABILITATION OF CITY-OWNED OFFICE SPACE | 400 409 | PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPAIRS AND REPLACEMENT OF GRANITE PAVE CRACKED, DISPLACEMENT OF GRANITE, CONCRETE AND BRICKS. REPAIR OF PLAZA CONCRETE MASONRY FOUNDATION | 2022 | 3940 | 100 | 5200 | 1297 | 0 | 0 | 0 | 0 | 6597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77ELEV | 120-55 QUEENS BLVD. ELEVATOR MODERNIZATION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 401 | PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SQ FT | 2022 | 1300 | 0 | 432 | 2110 | 0 | 0 | 0 | 0 | 2542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD99WNY1 | CENTER FOR THE WOMEN OF NEW YORK | MISCELLANEOUS CONSTRUCTION | 400 | P-Q245 P-D019 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | RECONSTRUCTION | 2022 | 1100 | 4454.63 | 60 | 0 | 0 | 0 | 0 | 0 | 4514.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | PWQ077AT2 | 120-55 QUEENS BLVD- QUEENS BOROUGH HALL ATRIUM | REHABILITATION OF CITY-OWNED OFFICE SPACE | 401 | PW-0077 PW-Q077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 120-55 QUEENS BVLD- QUEENS BOROUGH HALL ATRIUM | 2022 | 21854 | 19393.76 | 0 | 98 | 0 | 0 | 25 | 0 | 19516.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1002 | WATER MAIN WORK IN VARIOUS LOCATIONS PROJ Q2007-05 | TRUNK AND DISTRIBUTION MAIN EXTENSION | 406 | SE-1000 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | WATER MAIN WORK IN VARIOUS LOCATIONS PROJ Q2007-05 | 2022 | 16900 | 30115.22 | 287 | 0 | 0 | 0 | 0 | 0 | 30402.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1005 | DIST WATER MAIN REPLACEMENT LONG ISLAND CITY | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 401 | WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | DIST WATER MAIN REPLACEMENT LONG ISLAND CITY , ASTORIA AT VARIOUS LOCATIONS | 2022 | 11600 | 39483.3 | 65 | 0 | 0 | 0 | 0 | 0 | 39548.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1007 | New Trunk Water Main in Rockaway Beach Blvd (SANDHW12) | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 414 | WM-0006 WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW TRUNK WATER MAIN IN ROCKAWAY BEACH BLVD. B/W B 59 STREET AND B 49STREET | 2022 | 4994 | 28434.7 | 231 | 0 | 0 | 0 | 0 | 0 | 28665.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1014 | Rehabilitation of Astoria Water Trunk Main by Lining | AUGMENTATION OF WATER SUPPLY SYSTEMS | 401 | TF-0002 WM-0006 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REHABILITATION OF ASTORIA WATER TRUNK MAIN BY LINING IN 41ST STREET BETWEEN 25TH AVENUE AND 28TH AVENUE | 2022 | 3300 | 30268.49 | 82 | 0 | 0 | 0 | 100 | 0 | 30450.49 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 15
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1023B | Distr & Trunk WM Replacement Cypress Ave, Queens (Joint Bid) | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 405 | WM-0006 WM-0001 SE-0002Q TF-0002 HW-0200 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DISTRIBUTION & TRUNK REPLACEMENT CYPRESS AVE B/T WIILLOUGHBY AVE & HIMROD ST, QNS | 2022 | 26150 | 47537.17 | 3495 | 565 | 0 | 0 | 0 | 0 | 51597.17 | 4561.44 | 0 | 0 | 0 | 0 | 0 | 0 | 4561.44
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1027 | Replacement of Dist WM in 222nd St | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 413 | WM-0001 SE-0200Q SE-0002Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | REPLACEMENT OF DIST WM IN 222ND ST BETWEEN JAMAICA AVE AND HEMPSTEAD AVE, ETC. JAMAICA WATER SUPPLU TERRITORY-ZONE 12, QUEENS | 2022 | 34476 | 1315.43 | 0 | 0 | 37317 | 0 | 0 | 0 | 38632.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1030 | Water Main & Sewer Work, Beach Channel Drive Area (SANDHW11) | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 400 | WM-0001 SE-0002Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | OF BEACH CHANNEL DRIVE FROM BEACH 124TH STREET TO BEACH 116TH STREET IN ROCKAWAY BEACH, QUEENS | WM AND SW -BEACH CHANNEL DRIVE FROM BEACH 124TH STREET TO BEACH 116THSTREET IN ROCKAWAY BEACH, QUEENS | 2022 | 7540 | 8954.08 | 633 | 1233 | 0 | 0 | 0 | 0 | 10820.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1037 | WM Replacement in South Conduit Ave, Queens | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 413 | WM-0001 SE-1000 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | WM REPLACEMENT IN SOUTH CONDUIT AVE BETWEEN 124TH ST AND 134TH ST, ETC QUEENS | 2022 | 12076 | 8731.8 | 101 | 0 | 0 | 0 | 0 | 0 | 8832.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1042A | Watermain replacement & sewer repair on Queens Blvd-HWQ1190A | AUGMENTATION OF WATER SUPPLY SYSTEMS | 402 | WM-0006 SE-0002Q WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WATERMAIN REPLACEMENT AND SEWER REPAIR ON QUEENS BLVD FROM 48TH STREET TO 73RD STREET | 2022 | 46661 | 0 | 71 | 5385 | 93988 | 0 | 0 | 0 | 99444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1044 | Replacement of Water Mains in Beach 108th Street (SANDR04) | AUGMENTATION OF WATER SUPPLY SYSTEMS | 414 | WM-0001 SE-0200Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REPLACEMENT OF WATER MAINS IN BEACH 108TH STREET BETWEEN BEACH CHANNEL DRIVE AND SHORE FRONT PARKWAY AND OTHER LOCATIONS WITHIN THE AREA. | 2022 | 3428 | 4797.19 | 1839 | 0 | 2744 | 0 | 0 | 0 | 9380.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1049 | Rplmnt WM at 111 St btw 45th & Corona Ave (HWD10311) | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 400 | SE-0002Q WM-0001 |  |  | REPLACEMENT OF DISTRIBUTION WATER MAIN AT 111TH STREET BETWEEN 45TH AVENUE AND CORONA AVENUE. BOROUGH OF QUEENS. | 2022 | 5974 | 0 | 0 | 0 | 5974 | 0 | 0 | 0 | 5974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1051 | Water Main Replacement in Maspeth Avenue | AUGMENTATION OF WATER SUPPLY SYSTEMS | 401 | WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TO REPLACE AGEING AND UNDERSIZED WATER MAIN PIPES IN ADDITION TO IMPROVING WATER DISTRIBUTION.IT WILL BENEFIT INDIVIDUALS RESIDENT IN 61ST STREET,56TH AVENUE,56TH ROD,MASPETH AVENUE,CLINTON AVENUE,REMSEN PLACE. | 2022 | 3221 | 857 | 7685 | 0 | 0 | 0 | 0 | 0 | 8542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1054 | Dist WM work in Ellwell Crescent from Alderton to Carlton St | AUGMENTATION OF WATER SUPPLY SYSTEMS | 400 | WM-0001 EP-0007 WM-0944 |  |  | DISTRIBUTION WASTER MAIN WORK IN ELLWEEL CRESCENT FROM ALDERTON STREET TO CARLTON STREET, BOROUGH OF QUEENS | 2022 | 21962 | 825 | 24383 | 0 | 0 | 0 | 0 | 0 | 25208 | 0 | 2509 | 0 | 0 | 0 | 0 | 0 | 2509
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1055 | Dist. WM work in Jay Ave btwn Borden Ave & 66th St, QNS | AUGMENTATION OF WATER SUPPLY SYSTEMS | 400 | WM-0001 |  |  | DISTRIBUTION WATER MAIN WORK IN JAY AVENUE BETWEEN BORDEN AVENUE & 66TH STREET, BOROUGH OF QUEENS | 2022 | 9342 | 350 | 0 | 10493 | 0 | 0 | 0 | 0 | 10843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-1056 | Dist WM work in 43rd Ave btwn National St & 104 St, QNS | AUGMENTATION OF WATER SUPPLY SYSTEMS | 400 | WM-0001 |  |  | DISTRIBUTION WATER MAIN WORK IN 43RD AVENUE BETWEEN NATIONAL STREET &104TH STREET, BOROUGH OF QUEENS | 2022 | 13631 | 75 | 0 | 12392 | 0 | 0 | 0 | 0 | 12467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED1062 | WM Lining in Porpoise Bridge Flushing Meadows QNS, HBPED800Q | AUGMENTATION OF WATER SUPPLY SYSTEMS | 404 | WM-0001 |  |  | PORPOISE BRIDGE IN FLUSHING MEADOWS - CORONA. PROJECT IS IN CONJUNCTION WITH HBPED800Q. DPR TO FUND PITS, TV INSPECTION, AND VALVES AS EXPECTED WORK. | 2022 | 468 | 0 | 0 | 407 | 0 | 0 | 0 | 0 | 407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-976 | SEQ - Trunk Water Main in Francis Lewis Blvd (HWQ976) | TRUNK AND DISTRIBUTION MAIN EXTENSION | 413 | TF-0502 HW-0001Q WM-0006 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | TRUNK MAIN IN FRANCIS LEWIS BLVD - 90 AV TO 99 AV | TRUNK MAIN IN FRANCIS LEWIS BLVD - 90 AV TO 99 AV | 2022 | 38249 | 60019.24 | 1378 | 0 | 0 | 0 | 0 | 0 | 61397.24 | 169.22 | 0 | 0 | 0 | 0 | 0 | 0 | 169.22
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-988 | DISTRIB. WATER MAIN EXTENSIONS/REPLACEMENTS | TRUNK AND DISTRIBUTION MAIN EXTENSION | 400 | EP-0007 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DISTRIB. WATER MAIN EXTENSIONS/REPLACEMENTS, NEW BUILDINGS. | 2022 | 5066 | 4301.33 | 71 | 0 | 0 | 0 | 0 | 0 | 4372.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | QED-991 | New WM, Trunk Main Ext, 33 Ave & Francis Lewis Blvd, Queens | TRUNK AND DISTRIBUTION MAIN EXTENSION | 407 411 | TF-0002 WM-0006 SE-0002Q SE-0200Q WM-0001 HW-0200 TF-0502 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW WM, EXTEND TRUNK MAINS, UPGRADE 33RRD, 37TH & 38 AVE-FRANCIS LEWIS BLVD & UTOPIA PKWY, QNS | 2022 | 44838 | 82531.2 | 7302 | 0 | 0 | 0 | 4048 | 0 | 93881.2 | 635.41 | 0 | 0 | 0 | 0 | 0 | 0 | 635.41
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383K | QUEENS 5/5A HVAC | GARAGES AND FACILITIES | 405 | S-0136 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | HVAC REPLACEMENT | 2022 | 5150 | 6489.04 | 261 | 0 | 0 | 0 | 0 | 0 | 6750.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-419L | OAU Offices Expansion at CRS | GARAGES AND FACILITIES | 402 | S-0136 PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | OFFICE CONSTRUCTION FOR OAU | 2022 | 150 | 4008.82 | 386 | 0 | 0 | 0 | 0 | 0 | 4394.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-423 | Queens 11/13 FLOOR SLAB REPLACEMENT | GARAGES AND FACILITIES | 411 | S-0136 PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FLOOR SLAB REPLACEMENT | 2022 | 11250 | 8585.53 | 502 | 4542 | 65745 | 0 | 0 | 0 | 79374.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-438 | QUEENS 7 GARAGE REHABILITATION | GARAGES AND FACILITIES | 407 | S-0136 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REHABILITATION OF QUEENS 7 GARAGE | 2022 | 28680 | 22891.43 | 1111 | 1914 | 0 | 0 | 0 | 0 | 25916.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND1187 | Recon of Norton Drive - Hurricane Sandy (HWQ1187, SEQ200595) | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF NORTON DRIVE - HURRICANE SANDY | RECONSTRUCTION OF NORTON DRIVE - HURRICANE SANDY | 2022 | 1732 | 41.55 | 0 | 0 | 0 | 0 | 0 | 41 | 82.55 | 194 | 0 | 0 | 0 | 0 | 0 | 1364 | 1558
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBROAD | SANDY DAMAGES BROAD CHANNEL BRANCH LIBRARY | RECONSTRUCTION NECESSARY TO MAINTAIN FACILITIES | 414 | LQ-0122 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | HURRICANE SANDY RELATED DAMAGES AT BROAD CHANNEL BRANCH LIBRARY | 2022 | 1095 | 51.67 | 0 | 0 | 0 | 0 | 0 | 0 | 51.67 | 250.05 | 0 | 0 | 0 | 0 | 216 | 0 | 466.05
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDELEC5 | 100 the precint electrical system replacement, Sandy | POLICE FACILITIES | 414 | PO-0079 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | 100 THE PRECINT ELECTRICAL SYSTEM REPLACEMENT, SANDY | 2022 | 1802 | 1633.54 | 277 | 34 | 0 | 0 | 0 | 0 | 1944.54 | 2200.8 | 0 | 250 | 0 | 0 | 0 | 0 | 2450.8
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW11 | Recon of Beach Channel Drive - Hurricane Sandy (QED-1030) | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q TF-0002 TF-0502 F-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RECONSTRUCTION OF BEACH CHANNEL DRIVE - HURRICANE SANDY | RECONSTRUCTION OF BEACH CHANNEL DRIVE - HURRICANE SANDY | 2022 | 12427 | 4262.11 | 3120 | 0 | 0 | 634 | 0 | 0 | 8016.11 | 8468.49 | 5007 | 0 | 0 | 0 | 0 | 0 | 13475.49
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW12 | Reconstruction of Edgemere - Hurricane Sandy (QED-1007) | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF EDGEMERE - HURRICANE SANDY | RECONSTRUCTION OF EDGEMERE - HURRICANE SANDY | 2022 | 5392 | 2965.2 | 1818 | 0 | 0 | 0 | 0 | 0 | 4783.2 | 5022.23 | 104 | 0 | 0 | 0 | 463 | 0 | 5589.23
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW13 | Reconstruction of Rockaway Beach - Hurricane Sandy (QED-982) | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q HW-0200 TF-0502 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF ROCKAWAY BEACH - HURRICANE SANDY | RECONSTRUCTION OF ROCKAWAY BEACH - HURRICANE SANDY | 2022 | 14603 | 5844.34 | 209 | 0 | 1500 | 0 | 0 | 0 | 7553.34 | 14445.91 | 1567 | 0 | 9595 | 0 | 0 | 0 | 25607.91
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW24 | WHEN AND WHERE HURRICANE SANDY - QUEENS | PRIMARY STREET RECONSTRUCTION | 400 | WM-0001 HW-D103 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | WHEN AND WHERE HURRICANE SANDY - QUEENS | RECONSTRUCTION OF ROCKAWAY - HURRICANE SANDY | 2022 | 22186 | 7693.07 | 1 | 0 | 0 | 296 | 0 | 0 | 7990.07 | 8319.72 | 0 | 0 | 0 | 0 | 0 | 0 | 8319.72
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW26 | Reconstruction of East 10th Road - Hurricane Sandy | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RECONSTRUCTION OF EAST 10TH ROAD - HURRICANE SANDY | RECONSTRUCTION OF EAST 10TH ROAD - HURRICANE SANDY | 2022 | 620 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 1.73 | 0 | 0 | 0 | 0 | 0 | 382 | 383.73
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR02 | FAR ROCKAWAY BUSINESS DISTRICT IMPROVEMENTS (SE-830) | PRIMARY STREET RECONSTRUCTION | 400 414 | HW-0944 HW-0001Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | FAR ROCKAWAY IMPROVEMENTS BUSINESS DISTRICT | FAR ROCKAWAY IMPROVEMENTS BUSINESS DISTRICT | 2022 | 2400 | 19230.44 | 2941 | 0 | 6199 | 0 | 0 | 0 | 28370.44 | 12091.25 | 155 | 0 | 0 | 0 | 0 | 0 | 12246.25
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR04 | Beach 108th Streetscape Improvements (QED-1044) | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q TF-0502 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BEACH 108TH STREETSCAPE IMPROVEMENTS | BEACH 108TH STREETSCAPE IMPROVEMENTS | 2022 | 8200 | 4641.53 | 5053 | 1000 | 0 | 3726 | 0 | 0 | 14420.53 | 10478.99 | 3999 | 0 | 0 | 0 | 0 | 0 | 14477.99
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-11 | SANDY- R/C of Rockaway Garage DB | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 |  | ROCKAWAY GARAGE , QUEENS | R/C OF ARCHITECTURAL AND MACHANICAL COMPONENTS AT THE ROCKAWAY GARAGE | 2022 | 843 | 0 | 479 | 0 | 0 | 0 | 0 | 0 | 479 | 0 | 397 | 0 | 0 | 0 | 0 | 0 | 397
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-30 | Tide Gate - FEMA 406 In-Kind, HMP & 428 Conduit HBPED800Q | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | TIDE GATE - FEMA 406 IN-KIND, HMP & 428 CONDUIT | 2022 | 1311 | 20.57 | 0 | 113 | 0 | 0 | 0 | 0 | 133.57 | 185.17 | 0 | 992 | 0 | 0 | 0 | 0 | 1177.17
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-31 | Tide Gate - 404 HMGP HBPED800Q | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 400 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | TIDE GATE - 404 HMGP | 2022 | 5962 | 444.04 | 0 | 1379 | 0 | 0 | 0 | 0 | 1823.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDY4-50 | SANDY-Rockaway Operational Headquarters Reconstruction | BEACHES AND BOARDWALKS | 400 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SANDY-ROCKAWAY OPERATIONAL HEADQUARTERS RECONSTRUCTION | 2022 | 18876 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 1650 | 2272.32 | 23998 | 0 | 0 | 0 | 0 | 0 | 26270.32
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-785 | STORM SEWER IN 110 AV - SUTPHIN BLVD AND 173 ST | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 412 | SE-0785 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | STORM SEWER IN 110 AV - SUTPHIN BLVD AND 173 ST | STORM SEWER IN 110 AV - SUTPHIN BLVD AND 173 ST | 2022 | 10202 | 9031.96 | 35 | 0 | 0 | 0 | 0 | 0 | 9066.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-789B-3 | B 63 ST - BAYFIELD AV & ROCKAWAY FWAY (SOMMERVILLE III) | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 414 | SE-0789 WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | B 63 ST - BAYFIELD AV & ROCKAWAY FWAY (SOMMERVILLE III) | B 63 ST - BAYFIELD AV & ROCKAWAY FWAY (SOMMERVILLE III) | 2022 | 6190 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-795 | Storm & Sani Sewer in Chandler St - Nameoke Av & Battery Rd | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 414 | SE-0200Q SE-0002Q WM-0001 F-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STORM & SANITARY SEWER IN CHANDLER ST- NAMEOKE AV&BATTERY RD, WATERMAIN WORK. | 2022 | 7163 | 30637.65 | 284 | 0 | 0 | 0 | 0 | 0 | 30921.65 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-807 | Storm & San Sewers in 20th Ave b/t 126 St & US Bulkhead Line | PROGRAMMATIC REPLACEMENT AND RECONSTRUCTION | 407 | SE-0002Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STORM & SAN SEWERS IN 20TH AVE B/T126 ST & US BULKHEAD LINE, ETC WATER MAIN WORKS. ABANDONED REGULATOR R-5 | 2022 | 18910 | 129849.62 | 0 | 0 | 0 | 0 | 5939 | 0 | 135788.62 | 508.21 | 0 | 0 | 0 | 0 | 0 | 0 | 508.21
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-810 | STORM & SAN SWR, WILLET PT BLVD WHITESTONE AREA PHASE 2 | PROGRAMMATIC REPLACEMENT AND RECONSTRUCTION | 407 | SE-0002Q SE-0200Q WM-0001 SE-0944 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | WHITESTONE AREA PHASE 2 STORM & SAN SWR, WILLET PT BLVD (25TH AVENUE)BETWEEN 149TH STREET AND PARSONS BLVD, ETC. WATER MAIN WORKS | 2022 | 13279 | 81950.03 | 4981 | 0 | 0 | 0 | 1243 | 0 | 88174.03 | 11857.46 | 7812 | 0 | 0 | 0 | 0 | 0 | 19669.46
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-811 | STORM & SAN SWR, N.B. WHITESTONE EXPWY SERV RD PHASE 3 | PROGRAMMATIC REPLACEMENT AND RECONSTRUCTION | 407 | HW-0001Q SE-0200Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WHITESTONE AREA PHASE 3, STORM & SAN SWR, N.B. WHITESTONE EXPWY SERV RD BETWEEN 15TH AVENUE AND 25TH AVENUE, ETC WATER MAIN WORKS | 2022 | 11333 | 59707.69 | 0 | 590 | 0 | 0 | 5901 | 0 | 66198.69 | 9581.63 | 0 | 0 | 0 | 0 | 0 | 0 | 9581.63
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-823 | SEQ - 229th Street Laurelton Area - Part 1, Phase A (HWQ823) | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 413 | SE-0200Q SE-0002Q WM-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HI LEVEL STRM & COMB SWRS IN 229 ST, BTW 145 & 147 AVES. SE QUEENS LAURELTON AREA | 2022 | 19793 | 84546.65 | 5234 | 0 | 0 | 0 | 0 | 0 | 89780.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-824 | SEQ - 230th Place Laurelton Area - Part 1, Phase B | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 413 | SE-0200Q SE-0002Q WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SOUTH-EAST QUEENS LAURELTON AREA PART 1 PHASE B. STORM, SANITARY AND COMBINES SEWERS IN 230TH PLACE BETWEEN 145TH AVENUE AND 139TH AVENUE, ETC. | 2022 | 105667 | 1320 | 0 | 0 | 0 | 0 | 121155 | 0 | 122475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-825 | SEQ - Laurelton Area - Part 1, Phase C | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 413 | SE-0200Q SE-0002Q WM-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SOUTH-EAST QUEENS LAURELTON AREA PART 1 PHASE C. STORM, SANITARY AND COMBINED SEWERS IN 138TH AVENUE BETWEEN 225TH STREET AND 230TH PLACE, ETC. | 2022 | 74335 | 300 | 0 | 0 | 0 | 0 | 0 | 112857 | 113157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-829 | NDF -- Storm and Sanitary Sewers in Brundwick Ave, Queens | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 414 | SE-0200Q SE-0002Q WM-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | STORM AND SANIRTATY SEWERS IN BRUNDWICK AVE BETWEEN DOUGHTY BLVD. AND NAMEOKE AVE. ETC. | 2022 | 20701 | 0 | 0 | 0 | 0 | 0 | 30865 | 0 | 30865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-830 | NDF Storm & Sanitary SE, WM Work in Mott Ave, QNS (SANDR02) | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 414 | SE-0200Q SE-0002Q WM-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | STORM & SANITARY SEWERS, WM WORK IN REDFERN AVE B/T MOTT AVE & NAMEOKE AVE, QNS - HWQ1079 | 2022 | 57472 | 105150.64 | 3696 | 380 | 0 | 0 | 0 | 0 | 109226.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A | SEQ - Storm, Sanitary Sewers & WM in 225th Street | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 413 | SE-0200Q SE-0002Q WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STRM, SAN SWERS & WM 225ST & B/T 145RD & 149AVE QNS | 2022 | 58431 | 1140.11 | 0 | 0 | 0 | 0 | 0 | 65477 | 66617.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842A1 | SEQ - Storm Sewer Outlet in 224th Street | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 413 | SE-0200Q EP-0007 TF-0502 HW-0001Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STORM SEWER OUTLET IN 224TH STREET BETWEEN 149TH AVE AND A POINT APPROXIMATELY 200 FEET DUE SOUTH OF ROCKAWAY BLVD | 2022 | 95416 | 5052.35 | 100868 | 0 | 0 | 0 | 0 | 0 | 105920.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-842B | SEQ - Storm & Sanitary Sewers & WM Work in 224th Street | AUGMENTATION OF WATER SUPPLY SYSTEMS | 413 | SE-0200Q SE-0002Q WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STORM & SANITARY & W/M WORK IN 224TH STREET B/W 146TH AVENUE AND SOUTH CONDUIT AVENUE | 2022 | 35618 | 281.67 | 0 | 0 | 0 | 0 | 0 | 57107 | 57388.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE848 | SEQ - Sewer & WM Work in Baisley Blvd, Guy R Brewer Blvd | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 412 | SE-0200Q SE-0002Q WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STORM EXTENSIONS, CATCH BASINS, SANITARY REPLACEMENTS AND WM WORK IN BAISLEY BLVD., GUY R. BREWER BLVD., AND N. CONDUIT AVENUE AREA IN QUEENS | 2022 | 30786 | 61541.29 | 2710 | 138 | 0 | 0 | 0 | 0 | 64389.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-859 | Combined Sewer Replmnt & WM work 70 st & calamus ave, Qns | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 402 | HW-0200 TF-0002 TF-0502 SE-0002Q |  |  | OMBINED SEWER REPLACEMENT & WATER MAIN WORK 70TH ST & CALAMUS AVE, QNS | 2022 | 32854 | 113401.61 | 505 | 500 | 0 | 0 | 2000 | 0 | 116406.61 | 6008.55 | 0 | 0 | 0 | 0 | 0 | 0 | 6008.55
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-860 | Combined Swr Replac & WM work 71st, QNS | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 405 | HW-0200 SE-0002Q WM-0001 EP-0007 TF-0002 TF-0502 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COMBINED SEWER REPLACEMENT & WATER MAIN WORK 71ST & JUNIPER VALLEY BLVD, QNS | 2022 | 59467 | 1735 | 0 | 63800 | 0 | 0 | 0 | 0 | 65535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-862 | SEQ - Storm & Sanitary Sewer Replcmnt/Ext. 146 Ave (HWQ662G) | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 413 | SE-0200Q WM-0001 SE-0002Q WM-0006 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STORM AND SANITARY SEWER REPLACEMENT AND EXTENSIONS AND WM WORK IN 146TH AVE BETWEEN 153RD PL AND 159TH ST, ETC. QUEENS | 2022 | 80778 | 2096.85 | 98 | 0 | 84057 | 0 | 0 | 0 | 86251.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885 | SEQ - 150th St Spine: Phase I, Outlet at Bergen Basin | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 413 | SE-0200Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW STORM SEWER OUTLET AT BERGEN BASIN | 2022 | 50976 | 1710.8 | 0 | 140000 | 0 | 0 | 0 | 0 | 141710.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-885A | SEQ - 150th St Spine: Phase II, Trunk Storm Sewer in JFK | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 412 413 | SE-0200Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | TRUNK STORM SEWER 150TH STREET SPINE THAT GOES THROUGH JFK, QUEENS | 2022 | 3940 | 8721.46 | 0 | 0 | 0 | 0 | 0 | 38585 | 47306.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE885AVWE | SEQ - 150th St Spine Phase II DOT Van Wyck Exp -Trunk Combi | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 412 413 | SE-0200Q SE-0002Q |  |  | 150TH ST SPINE PHASE II DOT VAN WYCK EXP - TRUNK COMB SE | 2022 | 103293 | 150 | 135665 | 0 | 0 | 0 | 0 | 0 | 135815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-886 | NDF -- Storm & Sanitary Sewers in Beach Channel Drive, Qns | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 414 | SE-0200Q SE-0002Q WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STORM & SANITARY SEWERS, WM WORK, ETC IN BEACH CHANNEL DR BETWEEN REGINA AVE & HASSOCK STREET, QNS | 2022 | 12883 | 148.02 | 0 | 0 | 12883 | 0 | 0 | 0 | 13031.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-887 | NDF -- Storm & Sanitary Sewers, WM work in Cornaga Ave, Qns | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 414 | SE-0200Q SE-0002Q WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STORM & SANITARY SEWERS, WM WORK IN CORNAGA AVE BETWEEN MOTT AVE & BEACH CHANNEL DRIVE, QNS | 2022 | 25148 | 120.74 | 0 | 0 | 0 | 0 | 0 | 25148 | 25268.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-889 | SEQ - New Storm Sewer N. Conduit Ave | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 412 | SE-0200Q SE-0002Q WM-0001 WM-0006 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW STRM SWR N. CONDUIT AV -BAISLY BLVD S TO GUY BREWER BLVD | 2022 | 112349 | 568.35 | 0 | 0 | 0 | 0 | 112142 | 0 | 112710.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002693 | Combined Sewer and Water Main Replacements at Penelope Ave. | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 405 | SE-0002Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | COMBINED SEWER AND WATERMAIN REPLACEMENTS AT PENELOPE AVE. B/T 71STREET AND 74TH STREET, ETC., | 2022 | 8838 | 36332.21 | 432 | 0 | 0 | 0 | 0 | 0 | 36764.21 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 15
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002700 | REHABILITATION OF COMBINED SEWER AND WATER MAIN | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 405 | SE-0002Q WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REHABILITATION OF COMBINED SEWER AND WATER MAIN IN 73RD PLACE AREA INMIDDLE VILLAGE | 2022 | 4893 | 39.69 | 0 | 0 | 0 | 0 | 0 | 8644 | 8683.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ002715 | Replmnt & repair of combined SE outfall north 81st &19 Ave | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 400 | SE-0002Q |  |  | REPLACEMENT AND REPAIR OF COMBINED SEWER OUTFALL LOCATED NORTH OF 81 STREET AND 19 AVENUE, ON LAGUARDIA AIRPORT PROPERTY. | 2022 | 5328 | 187 | 4632 | 0 | 0 | 0 | 0 | 0 | 4819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200467 | STRM & SAN SWRS IN 14 AV B/T 115 ST & US BULKHEAD LINE | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 407 | SE-0004 SE-0002Q WM-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | STRM & SAN SWRS IN 14 AV B/T 115 ST & US BULKHEAD LINE | 2022 | 7417 | 90 | 0 | 0 | 0 | 0 | 8158 | 0 | 8248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200489 | STRM SWR & W/M IN 202 ST B/T 118 AV & LINDEN BLVD, ETC... | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 412 | SE-0002Q WM-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | STRM SWR & W/M IN 202 ST B/T 118 AV & LINDEN BLVD, FRANCIS LEWIS BLVD B/T 115 DR & LINDEN BLVD, NASHVILLE BLVD B/T 116 AV & 208 ST, SANITARY SWR IN 197 STREET B/T 115 AV AND 116 AVE | 2022 | 2535 | 7802.86 | 86 | 0 | 0 | 0 | 0 | 0 | 7888.86 | 186.36 | 0 | 0 | 0 | 0 | 0 | 0 | 186.36
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200519 | SEQ - Brookville-Edgewood Triangle West - Phase II (HWQ724B) | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 413 | SE-0002Q SE-0200Q WM-0001 SE-0005 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | BROOKVILLE- EDGEWOOD TRIANGLE, WEST (HWQ-724B PAHSE II) STORM AND SANITARY SEWERS IN BROOKVILLE BLVD BETWEEN NEWHALL AVE AND 147TH AVENUE, ETC. WATER MANIN WORKS | 2022 | 10475 | 2304.71 | 0 | 0 | 36 | 59068 | 0 | 0 | 61408.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200547 | SEQ - Storm Sewer in Commonwealth Blvd | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 413 | SE-0200Q WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STORM SEWER IN: COMMONWEATH BOULEVARD BETWEEN GRAND CENTRAL PARKWAY (SERVICE ROAD SOUTH) AND UNION TURNPIKE. | 2022 | 5590 | 154.2 | 0 | 0 | 0 | 0 | 0 | 9254 | 9408.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200558 | Install of storm SE & replacement of sanitary SE & dist.WM | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 400 | SE-0200Q SE-0002Q WM-0001 |  |  | INSTALLATION OF STORM SEWERS AND REPLACEMENT OF SANITARY SEWERS AND DISTRIBUTION WATER MAINS AT ETON STREET BETWEEN BARRINGTON AND WEXORD TERRACE ALONG WITH OTHER STREETS AS LISTED UNDER PRELIMINARY DESIGN SCOPE. | 2022 | 7229 | 939 | 8288 | 0 | 0 | 0 | 0 | 0 | 9227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200562 | SEQ - Storm Sewer & WM Work in 158th Street (HWQ121B3) | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 412 | SE-0200Q SE-1000 WM-0001 SE-0002Q EP-0007 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STORM EXT, REPLACE & WM WORK, 158 ST B/T 110 & 116 AVE, QNS | 2022 | 291 | 330 | 0 | 0 | 16754 | 0 | 0 | 0 | 17084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200578 | SEQ - Storm & San Sewers, WM Work in Foch Blvd (HWQ200578) | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 412 | SE-0200Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | 1-STORM & SANITARY SEWERS & WM IN FOCH BLVD B/T MERRICK BLVD. & 166THST. 2-STORM SEWER AND WATER MAIN IN ILION AVE B/T FARMERS BLVD. & WOOD ST. | 2022 | 12935 | 21276.73 | 2226 | 0 | 1004 | 0 | 0 | 0 | 24506.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200585 | SE & WM WORK IN SHORE RD (HWQ985) | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 411 | SE-0200Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RECONSTRUCTION OF EXISTING SEWERS, BROOKLYN | 2022 | 6787 | 6395.67 | 88 | 0 | 0 | 0 | 0 | 0 | 6483.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200586 | Broad Channel: Storm & San Sewers in W 11th Rd. (HWQ1182B) | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 414 | SE-0200Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | BROAD CHANNEL: STORM AND SAN SEWERS IN W 11TH RD. (198 AV) B/T CROSSBAY BLVD AND BROAD CHANNEL RD. | 2022 | 25000 | 45870.65 | 0 | 0 | 0 | 6289 | 0 | 0 | 52159.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200595 | Westbourne Ave-Norton Drive Recon (HWQ1187, SAND1187) | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 414 | WM-0001 SE-0200Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | INSTALLATION AND REPLACEMENT OF STORM SEWERS ALONG NORTON DRIVE BETWEEN COLDSPRING ROAD AND WESTBOURNE AVENUE. REPLACEMENT OF WATERMAINS ALONG NORTON DRIVE BETWEEN COLDSPRING ROAD AND WESTBOURNE AVENUE. | 2022 | 16200 | 0 | 0 | 0 | 0 | 116 | 0 | 16084 | 16200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ200604 | St. SE Ext in College Pl btwn 5th ave to US Bulkhead Line QN | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 407 | SE-0200Q |  |  | STORM SEWER EXTENSION IN COLLEGE POINT BETWEEN 5TH AVENUE (POPPENHUSEN AVENUE) AND US BULKHEAD LINE, BOROUGH OF QUEENS. THIS PROJECT WILL CONNECT WITH SEQ200463 | 2022 | 6054 | 0 | 0 | 6442 | 0 | 0 | 0 | 0 | 6442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ201BN9 | Reconstruction of Existing Sewers, North Queens | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 400 | SE-0002Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RECONSTRUCTION OF EXISTING SEWERS, NORTH QUEENS | 2022 | 6700 | 19955.34 | 85 | 0 | 0 | 0 | 0 | 0 | 20040.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQ201BS9 | Reconstruction of Existing Sewers, South Queens | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 400 | SE-0002Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RECONSTRUCTIION OF EXISTING SEWERS, SOUTH QUEENS | 2022 | 7800 | 19755.38 | 89 | 0 | 0 | 0 | 0 | 0 | 19844.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQBN11 | Reconstruction of Existing Sewers, North Queens | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 400 | SE-0002Q EP-0007 |  |  | RECONSTRUCTION OF EXISTING SEWERS, NORTH QUEENS | 2022 | 7600 | 7320.74 | 6262 | 0 | 0 | 0 | 0 | 0 | 13582.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQBS11 | Reconstruction of Existing Sewers, South Queens | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 400 | SE-0002Q |  |  | RECONSTRUCTION OF EXISTING SEWERS, SOUTH QUEENS | 2022 | 8550 | 9152.52 | 8081 | 0 | 0 | 0 | 0 | 0 | 17233.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS001 | SEQ - Sewer When & Where Contract in SE Queens | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 412 413 | SE-0002Q SE-1000 SE-0200Q WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SEWER WHEN &NWHERE CONTRACT IN SE QUEENS TO INCLUDE, STORM , SANITARYAND COMBIND SEWERS, WMS AND BORING, SURVEY & GEOTECHNICAL WORK AS REQUIRED | 2022 | 27500 | 38751.9 | 321 | 0 | 0 | 0 | 0 | 0 | 39072.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS003 | SEQ - Sewer When & Where Contract in SE Queens (HWQ1195) | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 412 413 | SE-0200Q SE-0002Q SE-0005 WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STORM, SANITARY,COMBINED SEWERS, WATER MAIN WORK, BORNING, SURGEY, GEOTECHNICAL WORK, SE QUEENS | 2022 | 28900 | 2809.99 | 0 | 28900 | 0 | 0 | 0 | 0 | 31709.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS004 | SEQ -SEWER WHEN & WHERE CONTRACT IN S.E. QNS | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 412 413 | SE-0200Q SE-0002Q WM-0001 EP-0007 SE-1000 SE-0944 HW-0200 TF-0002 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STORM SEWERS ANSD ADDTIONAL WORK AS NEEDED, SE QUEENS. | 2022 | 25000 | 812 | 32323 | 0 | 0 | 0 | 0 | 0 | 33135 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 16
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQNS005 | SEQ - Sewer When & Where Contract in SE Queens | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 412 413 | SE-0200Q SE-0002Q WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STORM SEWERS ANSD ADDTIONAL WORK AS NEEDED, SE QUEENS. | 2022 | 25000 | 1600 | 0 | 0 | 0 | 0 | 0 | 25000 | 26600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD1 | Southeast Queens Priority Grids -- Group 1 (DOTSEQ01) | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SOUTHEAST QUEENS PRIORITY GRIDS 01-10 | 2022 | 18154 | 1613.54 | 0 | 0 | 1291 | 18387 | 0 | 0 | 21291.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | SEQPGRD2 | Southeast Queens Priority Grids -- Group 2 (DOTSEQ02) | PRIMARY STREET RECONSTRUCTION | 400 | HW-0001Q | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SOUTHEAST QUEENS PRIORITY GRIDS 11-20 | 2022 | 12837 | 1389.56 | 0 | 0 | 1972 | 28316 | 0 | 0 | 31677.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 850 | DEPT OF DESIGN & CONSTRUCTION | TLCWOOD | TLC - NEW OFFICE FACILITY - 24-55 BQE WEST | RENOVATION OF OTHER CITY-OWNED FACILITIES | 401 | PW-0077 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW FACILITY | 2022 | 36000 | 135763.37 | 3175 | 8774 | 0 | 0 | 0 | 0 | 147712.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOT211 | DOT- 32-11 Harper St Envelope Improvements and Solar PV | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 401 | PU-0025 |  |  | 32-11 HARPER ST ENVELOPE IMPROVEMENTS AND SOLAR PV | 2022 | 12494 | 0 | 0 | 316 | 5701 | 0 | 0 | 0 | 6017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | C75BULOVA | Reconstruction of Bulova Building Suite 330 | SUPPORT SPACE |  | C-0075 |  |  | RECONSTRUCTION OF BULOVA BUILDIING SUITE 330 | 2022 | 1118 | 0 | 1016 | 0 | 0 | 0 | 0 | 0 | 1016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296EV | 125-01 QUEENS BLVD.- ELEVATORS | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 409 | CO-0296 |  |  | 125-01 QUEENS BLVD.- ELEVATORS | 2022 | 25978 | 0 | 0 | 1358 | 0 | 24120 | 0 | 0 | 25478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO296FA | 125-01 QUEENS BLVD.- FIRE ALARMS | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 409 | CO-0296 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 125-01 QUEENS BLVD. - FIRE ALARMS | 2022 | 2989 | 0 | 0 | 350 | 0 | 2600 | 0 | 0 | 2950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298CHIL | 151-20 JAMAICA AVE.- CHILLER REPLACEMENT | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 412 | CO-0298 |  |  | SQ FT | 2022 | 1689 | 0 | 0 | 149 | 0 | 1385 | 0 | 0 | 1534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO298RF | 151-20 JAMAICA AVE ROOF REHAB | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 401 | CO-0298 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SQ/IA | 2022 | 8770 | 0 | 975 | 0 | 7795 | 0 | 0 | 0 | 8770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO299CHIL | 89-17 SUTPHIN BLVD.- CHILLER REPLACEMENT | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 412 | CO-0299 |  |  | SQ FT | 2022 | 2694 | 0 | 0 | 0 | 0 | 2435 | 0 | 0 | 2435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO299RF | 89-17 Sutphin Blvd Roof | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 401 | CO-0299 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SQ/IA | 2022 | 8476 | 0 | 942 | 0 | 7534 | 0 | 0 | 0 | 8476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300415A | DASNY - 88-11 SUTPHIN BLVD.- RENOVATION | CONSTRUCTION OF NEW COURT FACILITIES | 412 | CO-0300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 88-11 SUTPHIN BLVD. QUEENS, NY 11435 | INTERIOR RENOVATIONS; ELECTRICAL & HVAC DISTRIBUTION; INITIAL OUTFITTING OF NEWLY RENOVATED SPACE | 2022 | 55978 | 9364.15 | 0 | 0 | 687 | 0 | 0 | 0 | 10051.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300FIRE | 88-11 SUTPHIN BLVD. FIRE ALARM SPRINKLER SYSTEM UPGRADE | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 412 | CO-0300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 88-11 SUTPHIN BLVD.FIRE ALARM SYSTEM UPGRADE | 2022 | 4030 | 0 | 0 | 1116 | 0 | 0 | 7531 | 7397 | 16044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO300RF | 88-11 SUTPHIN BOULEVARD - ROOF | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 412 | CO-0300 |  |  | 88-11 SUTPHIN BOULEVARD - ROOF | 2022 | 376 | 0 | 644 | 0 | 5121 | 310 | 0 | 0 | 6075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0005 | Jamaica Arms Hotel/Family Respite Residence | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 401 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | JAMAICA ARMS HOTEL/FAMILY RESPITE RESIDENCE | 2022 | 5581 | 0 | 0 | 0 | 0 | 0 | 5581 | 0 | 5581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0009 | OCME Queens Chief Medical Examiner | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 401 | PU-0025 |  |  | OCME QUEENS CHIEF MEDICAL EXAMINER | 2022 | 7074 | 0 | 0 | 1323 | 5751 | 0 | 0 | 0 | 7074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0069 | NYPD - 101st Precinct | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 101ST PRECINCT | 2022 | 300 | 0 | 0 | 168 | 0 | 0 | 0 | 0 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0070 | NYPD - 106th Precinct | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 0 | 2022 | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0071 | NYPD - 108TH PRECINCT | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | IA/SQ | 2022 | 300 | 0 | 0 | 244 | 0 | 0 | 0 | 0 | 244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0090 | QPL - McGOLDRICK COMMUNITY LIBRARY | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | IA/SQ | 2022 | 500 | 0 | 0 | 126 | 0 | 0 | 0 | 0 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0091 | QPL - OZONE PARK COMMUNITY LIBRARY | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | IA/SQ | 2022 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | HR25QCRT | 151-20 Jamaica Ave 4th floor | SOCIAL SERVICES BUILDINGS |  | HR-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  |  | 2022 | 1921 | 147.71 | 1833 | 0 | 0 | 0 | 0 | 0 | 1980.71 | 52.28 | 649 | 0 | 0 | 0 | 0 | 0 | 701.28
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79QTP | NYPD - COLLEGE POINT TOW POUND | POLICE FACILITIES | 400 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COLLEGE POINT TOW POUND | 2022 | 3670 | 12857.02 | 336 | 0 | 0 | 0 | 0 | 0 | 13193.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ3 | DA QUEENS - CYBER CRIME UNIT | RENOVATION OF LEASED SPACE | 407 | PW-0326 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SQFT | 2022 | 2676 | 2247.29 | 207 | 0 | 222 | 0 | 0 | 0 | 2676.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DAQ4 | DA QUEENS - SUPREME COURT TRIAL BUREAU | RENOVATION OF LEASED SPACE | 409 | PW-0326 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SQFT | 2022 | 7748 | 3062.83 | 0 | 0 | 0 | 0 | 0 | 4685 | 7747.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOPQ | DOP - 162-24 JAMAICA AVE, QUEENS ADD'L SPACE (MEZZANINE) | RENOVATION OF LEASED SPACE | 401 | PW-0326 |  |  | SQ/IA | 2022 | 1037 | 0 | 0 | 1037 | 0 | 0 | 0 | 0 | 1037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326EV | DOHMH - 2 GOTHAM CHARGING STATION INFRASTRUCTURE | RENOVATION OF LEASED SPACE | 401 | PW-0308 |  |  | SQ FT | 2022 | 375 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAQ | LAW DEPT - RAISE THE AGE - QUEENS | RENOVATION OF LEASED SPACE | 401 | PW-0326 |  |  | LAW DEPT - RAISE THE AGE - QUEENS | 2022 | 4500 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TLQ3 | TLC -31-00 47 AVE QUEENS | RENOVATION OF LEASED SPACE | 401 | PW-0326 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | TLC -31-0047 AVE QUEENS -EXPANSION | 2022 | 1141 | 0 | 0 | 0 | 0 | 0 | 0 | 1141 | 1141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW340QNS1 | BOE - 126-06 QUEENS BLVD - OFFICES | BOARD OF ELECTIONS MODERNIZATION | 401 | PW-0340 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 47-25 34TH ST. QUEENS- BOARD OF ELECTIONS OFFICES | RENOVATE WAREHOUSE AND OFFICE SPACE FOR THE BOARD OF ELECTIONS | 2022 | 784 | 2219.89 | 56 | 0 | 0 | 0 | 0 | 0 | 2275.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417SW | 120-55 QUEENS BLVD.- SITE WORK | REHABILITATION OF CITY-OWNED OFFICE SPACE | 409 | PW-0077 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 120-55 QUEENS BLVD - SITE WORK | 2022 | 4841 | 405.18 | 0 | 874 | 0 | 0 | 4370 | 0 | 5649.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77417TU | 120-55 QUEENS BOULEVARD- CODE COMPLIANT TOILET UPGRADES | REHABILITATION OF CITY-OWNED OFFICE SPACE | 401 | PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CODE COMPLIANT TOILET UPGRADES | 2022 | 4400 | 0 | 0 | 400 | 0 | 0 | 4000 | 0 | 4400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD78415A | 88-11 SUTPHIN BLVD.- FACADE RESTORATION | REHABILITATION OF COURT BUILDINGS | 400 412 | PW-D078 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | QUEENS SUPREME COURT FACADE RESTORATION | 2022 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77QBH2 | 120-55 QUEENS BLVD.- RENOVATIONS | REHABILITATION OF CITY-OWNED OFFICE SPACE | 401 | PW-Q077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | QUEENS BORO HALL--RENOVATIONS | 2022 | 186 | 0 | 0 | 0 | 0 | 0 | 0 | 186 | 186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWQ77R213 | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS | REHABILITATION OF CITY-OWNED OFFICE SPACE | 401 | PW-Q077 PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 120-55 QUEENS BLVD- QUEENS BORO HALL RENOVATIONS-TOPOGRAPHY | 2022 | 847 | 0 | 0 | 0 | 0 | 0 | 1448 | 0 | 1448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | RE25VERN | PLATFORM / BULKHEAD REPLACEMENT | REHABILITATION OF WATERFRONT PROPERTIES | 401 | RE-0025 |  |  | PLATFORM / BULKHEAD REPLACEMENT | 2022 | 492 | 0 | 0 | 0 | 0 | 0 | 492 | 0 | 492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SCACIP04 | CAPACITY NEW SCHOOL - DSF0000866092 @ Q472 | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 400 | PU-0025 |  |  | CAPACITY NEW SCHOOL - DSF0000866092 @ Q472 , 3079 SEATS | 2022 | 8000 | 0 | 7725 | 0 | 0 | 0 | 0 | 0 | 7725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARPQL1 | DCAS PQL Round 1 (EME) DCAS PQL Round 1 (EME) | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 401 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DCAS PQL ROUND 1 (EME) | 2022 | 3400 | 0 | 0 | 3400 | 0 | 0 | 0 | 0 | 3400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | QUEENS | 856 | DEPT OF CITYWIDE ADMIN SERVS | UNIONHALL | ACS - WORKFORCE INSTITUTE UNION HALL | SOCIAL SERVICE BUILDINGS | 400 | CS-0003 |  |  | CONSTRUCTION AND FURNITURE AT WORKFORCE INSTITUTE | 2022 | 18003 | 3959.86 | 275 | 0 | 5093 | 0 | 0 | 0 | 9327.86 | 5706.47 | 399 | 0 | 7749 | 0 | 0 | 0 | 13854.47
20220309 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNCA17THL | TODT HILL - New Lighting | ESSENTIAL RECONSTRUCTION OF FACILITIES | 500 | LN-D008 |  |  | TODT HILL: NEW LIGHTING | 2022 | 700 | 0 | 0 | 0 | 0 | 76 | 558 | 0 | 634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNCM15STB | South Beach - New Roof | ESSENTIAL RECONSTRUCTION OF FACILITIES | 500 | LN-D008 |  |  | ROOF | 2022 | 200 | 0 | 0 | 0 | 0 | 22 | 178 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNEM17RTW | RICHMONDTOWN - HVAC System Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 500 | LN-D008 LN-0008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RICHMONDTOWN: REPLACE HVAC | 2022 | 1200 | 0 | 0 | 162 | 940 | 0 | 0 | 0 | 1102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA17WNB | WEST NEW BRIGHTON - ADA-compliant Elevators | ACCESS FOR THE HANDICAPPED | 501 | LN-R001 LN-D008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NYPL - WEST BRIGHTON BRANCH: ADA ELEVATOR COMPLIANCE AT WEST BRIGHTON BRANCH LIBRARY; 976 CASTLETON AVE, STATEN ISLAND, NY 10310 | 2022 | 1000 | 0 | 406 | 0 | 0 | 0 | 500 | 0 | 906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA18GCK | Great Kills - ADA-compliant Restrooms | ACCESS FOR THE HANDICAPPED | 503 | LN-R001 |  |  | NYPL-GREAT KILLS-ADA COMPLIANT RESTROOMS | 2022 | 350 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 037 | NEW YORK PUBLIC LIBRARY | LNRA18RCH | Richmondtown - New Boiler | IMPROVEMENTS TO EXISTING FACILITIES | 502 | LN-R001 |  |  | NYPL-RICHMONDTOWN BRANCH-NEW BOILER | 2022 | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 042 | CITY UNIVERSITY | ST001-021 | Science Lecture Room | MISCELLANEOUS RECONSTRUCTION | 500 | HN-D300 |  |  | SCIENCE LECTURE ROOM | 2022 | 615 | 0 | 0 | 615 | 0 | 0 | 0 | 0 | 615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 042 | CITY UNIVERSITY | ST030-015 | Support Center for High Performance Computer | MISCELLANEOUS RECONSTRUCTION | 500 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SUPPORT CENTER FOR HIGH PERFORMANCE COMPUTER | 2022 | 350 | 352.99 | 0 | 97 | 0 | 0 | 0 | 0 | 449.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 042 | CITY UNIVERSITY | ST032-015 | Media Culture Screening Room | MISCELLANEOUS RECONSTRUCTION | 500 | HN-D300 HN-D005 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MEDIA CULTURE SCREENING ROOM | 2022 | 510 | 479.18 | 0 | 148 | 0 | 0 | 0 | 0 | 627.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 042 | CITY UNIVERSITY | ST034-016 | High Performance Computer Center | MISCELLANEOUS RECONSTRUCTION | 500 | HN-D300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HIGH PERFORMANCE CENTER | 2022 | 125 | 0 | 0 | 0 | 125 | 0 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 042 | CITY UNIVERSITY | ST038-018 | Reconstruction of Baseball Field | MISCELLANEOUS RECONSTRUCTION |  | HN-R300 HN-D300 HN-R001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECONSTRUCTION OF BASEBALL FIELD | 2022 | 3150 | 0 | 4379 | 0 | 0 | 0 | 0 | 0 | 4379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 042 | CITY UNIVERSITY | ST039-019 | Maker Space Lab | MISCELLANEOUS RECONSTRUCTION | 500 502 | HN-D300 HN-R001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MAKER SPACE LAB | 2022 | 1350 | 202.16 | 0 | 1148 | 0 | 0 | 0 | 0 | 1350.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 042 | CITY UNIVERSITY | ST041-020 | Room Conversion for the Genomic Research Center | MISCELLANEOUS RECONSTRUCTION | 500 | HN-D300 HN-R001 |  |  | ROOM CONVERSION FOR THE GENOMIC RESEARCH CENTER | 2022 | 1250 | 0 | 0 | 1250 | 0 | 0 | 0 | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 056 | POLICE DEPARTMENT | PO79120AC | 120TH PCT - NEW HVAC SYSTEM | POLICE FACILITIES | 500 501 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW HVAC SYSTEM | 2022 | 400 | 1387 | 1112 | 0 | 0 | 0 | 0 | 0 | 2499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 057 | FIRE DEPARTMENT | F175MC152 | Multi-Component Renovations - EC152 | NEW FACILITIES AND RENOVATIONS | 501 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MULTI-COMPONENT RENOVATIONS - EC152 | 2022 | 7613 | 870.04 | 0 | 4795 | 3436 | 0 | 0 | 0 | 9101.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 057 | FIRE DEPARTMENT | F175MC159 | Multi-Component Renovations - EC159 | NEW FACILITIES AND RENOVATIONS | 502 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MULTI-COMPONENT RENOVATIONS - EC159 | 2022 | 5295 | 561.4 | 16 | 6431 | 0 | 0 | 0 | 0 | 7008.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 057 | FIRE DEPARTMENT | F175SEWER | New Sewer Main and Pumping Station - Outside Plant Garage | NEW FACILITIES AND RENOVATIONS | 500 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NEW SEWER MAIN - OUTSIDE PLANT GARAGE | 2022 | 837 | 137.16 | 50 | 0 | 0 | 0 | 0 | 0 | 187.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 057 | FIRE DEPARTMENT | FD175G161 | Generator - EC161 | NEW FACILITIES AND RENOVATIONS | 502 | F-D175 F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | GENERATOR - EC161 | 2022 | 802 | 93.26 | 786 | 0 | 0 | 0 | 0 | 0 | 879.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 057 | FIRE DEPARTMENT | FD175G165 | Generator - EC165 | NEW FACILITIES AND RENOVATIONS | 502 | F-D175 F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | GENERATOR - EC165 | 2022 | 679 | 108.95 | 855 | 0 | 0 | 0 | 0 | 0 | 963.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 057 | FIRE DEPARTMENT | FR175G166 | Generator - EC166 | NEW FACILITIES AND RENOVATIONS |  | F-R175 F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | INSTALLATION OF NEW BUILDING GENERATOR AT EC166. | 2022 | 614 | 57.83 | 900 | 0 | 0 | 0 | 0 | 0 | 957.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 071 | DEPT OF HOMELESS SERVICES | HH115HOBU | HOSPITALITY HOUSE BUILDING UPGRADE | SHELTERS FOR HOMELESS FAMILIES | 501 | HH-0115 |  |  | HOSPITALITY HOUSE BUILDING UPGRADE | 2022 | 2250 | 0 | 0 | 180 | 0 | 2070 | 0 | 0 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV302BPH2 | SIIAS - Building B at SHCC Phase 2 | ESSENTIAL RECONSTRUCTION OF FACILITIES | 501 | PV-R302 PV-D302 PV-0302 |  |  | RENOVATION PH2 | 2022 | 125 | 0 | 250 | 0 | 0 | 3315 | 0 | 0 | 3565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341CAR2 | SIHS - Carriage Barn Phase 2 | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-0341 PV-D467 PV-D341 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 441 CLARKE AVENUE, STATEN ISLAND | PHASE II OF CONSTRUCTION WORK ON CARRIAGE BARN STRUCTURES. | 2022 | 1112 | 0 | 0 | 0 | 1387 | 0 | 0 | 0 | 1387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341GALL | SIHS - Gallery Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 503 | PV-D341 |  |  | GALLERY | 2022 | 450 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV341SIPA | SIHS - Security System and Security Gates | CAPITAL EQUIPMENT | 502 | PV-R341 PV-0341 PV-D341 PV-0467 |  |  |  | 2022 | 2154 | 0 | 506 | 0 | 1538 | 0 | 0 | 0 | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490CPSD | SHCC - Snug Harbor CPSD: Phase 1A | ESSENTIAL RECONSTRUCTION OF FACILITIES | 501 | PV-D490 |  |  | CPSD | 2022 | 3125 | 0 | 0 | 0 | 3125 | 0 | 0 | 0 | 3125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-GOV | SHCC - SNUG HARBOR - Governor's House Exterior Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 501 | PV-0490 |  |  | RENOVATION | 2022 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000
20220309 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490-K | SHCC - SNUG HARBOR - BLDG K Matrons House | ESSENTIAL RECONSTRUCTION OF FACILITIES | 501 | PV-R490 PV-D490 PV-0490 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BLDG K MATRONS HOUSE | 2022 | 1628 | 0 | 250 | 0 | 0 | 1612 | 1500 | 0 | 3362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV490SWTG | SHCC - Emergency Electrical Switchgear | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-R490 PV-D490 PV-0490 |  |  | CONSTRUCTION | 2022 | 2325 | 0 | 75 | 0 | 0 | 250 | 2000 | 0 | 2325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | ANNADALE | Annadale Road Streetscape Project - Infrastructure Reno | MISCELLANEOUS | 500 503 | ED-D384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ANNADALE ROAD STREETSCAPE PROJECT - INFRASTRUCTURE RENOVATIONS | 2022 | 1855 | 0 | 0 | 0 | 0 | 0 | 0 | 1855 | 1855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | C5215AB2 | St. George Ferry Terminal | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 501 | FA-0021 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | STATEN ISLAND | ST GEORGE PHASE II IMPROVEMENT | 2022 | 159617 | 132196.88 | 120 | 0 | 0 | 0 | 0 | 0 | 132316.88 | 8466.5 | 0 | 0 | 0 | 957 | 0 | 0 | 9423.5
20220309 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | CMETENT | OCME Relocation of Disaster Cache Equipment to Fresh Kills | OCME | 501 | HL-0083 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RELOCATION OF OCME DISASTER CACHE RESPONSE EQUIPMENT TO FRESH KILLS, STATEN ISLAND | 2022 | 4160 | 3719.38 | 440 | 0 | 0 | 0 | 0 | 0 | 4159.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | FORESTAVE | FOREST AVENUE | MISCELLANEOUS | 500 | ED-0075 HW-0001Q HW-0001R | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FOREST AVE REALIGNMENT | 2022 | 2500 | 0 | 4476 | 0 | 0 | 0 | 0 | 0 | 4476 | 0 | 1375 | 0 | 0 | 0 | 0 | 0 | 1375
20220309 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | GE-343 | Replacement of Siphons b/t Brooklyn & SI | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 501 | WM-0006 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REPLACEMENT OF THE SIPHONS WHICH RUN BETWEEN BROOKLYN AND STATEN ISLAND | 2022 | 74150 | 140168.63 | 2740 | 0 | 0 | 0 | 0 | 0 | 142908.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HMPRTBULK | Home Port Bulkhead | MISCELLANEOUS | 500 | ED-0409 |  |  | BULKHEAD WORK | 2022 | 2300 | 0 | 800 | 1500 | 0 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HOMEPORT2 | Stapleton Waterfront Phase II & III | MISCELLANEOUS | 500 | ED-0075 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STAPLETON WATERFRONT PHASE II & III | 2022 | 95000 | 21808.49 | 5000 | 5156 | 5000 | 5000 | 12000 | 47194 | 101158.49 | 603.88 | 0 | 0 | 0 | 0 | 0 | 0 | 603.88
20220309 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | HWRLASEWF | Lipsett Avenue Street End (Waterfront) | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 500 | PU-0200 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | LIPSETT AVENUE STREET END (WATERFRONT) | LIPSETT AVENUE STREET END (WATERFRONT) | 2022 | 900 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LNC018CHA | CHARLESTON - Site Acquisition and New Branch Construction | EXPANSION AND CONSTRUCTION OF FACILITIES | 503 | LN-0008 LN-D002 LN-D008 LN-R001 PU-0025 P-0245R | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CHARLESTON - SITE ACQUISITION AND NEW BRANCH CONSTRUCTION | 2022 | 11103 | 10980.15 | 4975 | 0 | 0 | 0 | 0 | 0 | 15955.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16PRT | PORT RICHMOND: MAJOR RENOVATION | ESSENTIAL RECONSTRUCTION OF FACILITIES | 500 | LN-0008 LN-D008 LN-R001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PORT RICHMOND: MAJOR RENOVATION | 2022 | 20000 | 1131.12 | 20346 | 2133 | 0 | 0 | 0 | 0 | 23610.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | NDF-TOMPK | NDF - Tompkinsville Esplanade and Pier | MISCELLANEOUS | 500 | ED-0384 |  |  | NDF - TOMPKINSVILLE ESPLANADE AND PIER | 2022 | 35000 | 0 | 5000 | 0 | 0 | 15000 | 10000 | 5000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | PWDSIBPCT | Van for the Staten Island Borough President's Clean Team -- | MISCELLANEOUS | 500 | PW-D308 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | VAN FOR THE STATEN ISLAND BOROUGH PRESIDENT'S CLEAN TEAM -- VAN PURCHASE | 2022 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | RCBBALLPK | RICHMOND COUNTY BANK BALLPARK AT ST. GEORGE | MISCELLANEOUS | 500 | ED-D075 ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RICHMOND COUNTY BANK BALLPARK AT ST. GEORGE--RENOVATIONS OF BALLPARK | 2022 | 1750 | 0 | 9374 | 0 | 0 | 0 | 0 | 0 | 9374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDEDCG5 | Tompkinsville Esplanade - FEMA 428 Group 5 | MISCELLANEOUS | 500 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TOMPKINSVILLE ESPLANADE - FEMA 428 GROUP 5 | 2022 | 670 | 0 | 670 | 0 | 0 | 0 | 0 | 0 | 670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG1HP | FEMA 428 G1 - Homeport Pier | MISCELLANEOUS | 500 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FEMA 428 G1 - HOMEPORT PIER | 2022 | 13489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1044.96 | 12319 | 0 | 0 | 0 | 0 | 0 | 13363.96
20220309 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG1HS | FEMA 428 G1 - Homeport Substation | MISCELLANEOUS | 500 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FEMA 428 G1 - HOMEPORT SUBSTATION | 2022 | 3808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 454.94 | 3479 | 0 | 0 | 0 | 0 | 0 | 3933.94
20220309 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDG4DOC | FEMA 428 G4- DOCKBUILDERS | MISCELLANEOUS | 500 | ED-0075 FA-0021 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FEMA 428 GROUP 4 - DOCKBUILDERS | 2022 | 31250 | 0 | 250 | 33314 | 0 | 13277 | 0 | 0 | 46841 | 3058.24 | 27942 | 0 | 0 | 0 | 0 | 0 | 31000.24
20220309 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHOME | Repairs to Homeport as a result of Hurricane Sandy | MISCELLANEOUS | 500 501 | ED-0404 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REPAIRS TO THE HOMEPORT PROJECT AS A RESULT OF DAMAGE CAUSED BY HURRICANE SANDY | 2022 | 2175 | 0 | 0 | 0 | 218 | 0 | 0 | 0 | 218 | 0 | 0 | 0 | 1957 | 0 | 0 | 0 | 1957
20220309 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDSIHP2 | Stapleton Waterfront Phase II & III - Sandy Repairs | MISCELLANEOUS | 500 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STAPLETON WATERFRONT PHASE II & III - FEMA RESILIENCY | 2022 | 3408 | 0 | 341 | 0 | 0 | 0 | 0 | 0 | 341 | 0 | 3067 | 0 | 0 | 0 | 0 | 0 | 3067
20220309 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDSMC | Hurricane Sandy - Saw Mill Creek Marsh Restoration | MISCELLANEOUS | 500 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REHABILITATION OF SAW MILL CREEK IN STATEN ISLAND | 2022 | 13000 | 10448.12 | 881 | 0 | 0 | 0 | 0 | 0 | 11329.12 | 1435.46 | 5 | 0 | 0 | 0 | 0 | 0 | 1440.46
20220309 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIBULK | Sandy Staten Island Esplanade Emergency Bulkhead Work | MISCELLANEOUS | 501 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STATEN ISLAND ESPLANADE EMERGENCY BULKHEAD WORK | 2022 | 2005 | 35.07 | 110 | 349 | 0 | 0 | 0 | 0 | 494.07 | 226.95 | 368 | 0 | 35 | 3855 | 0 | 0 | 4484.95
20220309 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | SIESPLAND | Staten Island North Shore Esplanade | WATERFRONT DEVELOPMENT | 501 | ED-0409 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | SI, NY 10301 | INSTALLATION OF NEW PAVERS; CONCRETE & ASPHALT PAVING; BULKHEAD RECONSTRUCTION | 2022 | 10543 | 6175.11 | 0 | 234 | 0 | 0 | 0 | 0 | 6409.11 | 560.81 | 2497 | 0 | 0 | 0 | 0 | 0 | 3057.81
20220309 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | STGRGEFIT | St. George Ferry Terminal - Fit Out | WATERFRONT DEVELOPMENT | 500 501 | ED-R075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ST. GEORGE FERRY TERMINAL FIT OUT | 2022 | 400 | 332.84 | 0 | 0 | 0 | 0 | 68 | 0 | 400.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TRAVLIFT | Travis Avenue Lift Project -- Elevating section of Travis Av | MISCELLANEOUS | 500 | ED-D075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TRAVIS AVENUE LIFT PROJECT -- ELEVATING SECTION OF TRAVIS AVENUE TO PREVENT FLOODING | 2022 | 1500 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 801 | DEPT OF SMALL BUSINESS SERVICES | TRAVSIDEW | TRAVIS AVENUE ELEVATION - FOR SIDEWALK/WALKWAY TO NATURE PRE | MISCELLANEOUS | 500 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TRAVIS AVENUE ELEVATION - FOR SIDEWALK/WALKWAY TO NATURE PRESERVE | 2022 | 2000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM16NLSC | NEW LANE HOUSES - SECURITY CAMERAS AND DOORS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 501 | HA-R001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW LANE HOUSES - SECURITY CAMERAS AND DOORS | 2022 | 700 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM16THSC | TODT HILL HOUSES SECURITY CAMERAS AND DOORS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 502 | HA-R001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TOD HILL HOUSES SECURITY CAMERAS AND DOORS | 2022 | 1800 | 1170.51 | 1729 | 0 | 0 | 0 | 0 | 0 | 2899.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM17THTV | Todt Hill Cameras -- CCTV Security Cameras | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 502 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INSTALLATION OF SECURITY CAMERAS AT TODT HILL | 2022 | 200 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CSLF | CASSIDY LAFAYETTE SECURITY CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 501 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INSTALL SECURITY CAMERAS | 2022 | 2760 | 2521.64 | 239 | 0 | 0 | 0 | 0 | 0 | 2760.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM20BHCC | BERRY HOUSES CAMERA UPGRADES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 502 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BERRY HOUSES ON STATEN ISLAND CAMERA UPGRADES | 2022 | 200 | 30.8 | 169 | 0 | 0 | 0 | 0 | 0 | 199.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SBLU | SOUTH BEACH HOUSES- LIGHTING UPGRADES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 502 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW YORK CITY HOUSING AUTHORITY - SOUTH BEACH HOUSES ON STATEN ISLAND-- SOUTH BEACH HOUSES OF STATEN ISLAND LIGHTING UPGRADES | 2022 | 200 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHTV | CCTV CAMERAS AT MARINERS HARBOR HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 501 | HA-D001 |  |  | NYCHA MARINERS HARBOR HOUSES - MARINERS HARBOR SECURITY CAMERAS-INSTALLATION OF CCTV CAMERAS INTHE DEVELOPMENT | 2022 | 650 | 0 | 650 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 806 | HOUSING PRESERVATION AND DEVEL | HAM21NLCI | CONCRETE INSTALLATION AT NEW LANE HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 501 | HA-D001 |  |  | NEW LANE HOUSES - CONCRETE INSTALLATION- REMOVE BOCCE BALL COURT AND REPLACE WITH CONCRETE | 2022 | 205 | 0 | 205 | 0 | 0 | 0 | 0 | 0 | 205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75200902 | SEAVIEW: RENOVATION OF ISOLATION BUILDING | ROUTINE RECONSTRUCTION | 502 | HO-R001 HO-0214 HO-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 460 BRIELLE AVENUE, STATEN ISLAND, N. Y. 10314 | THEPURPOSE OF THIS PROJECT IS TO RENOVATE THE ISOLATION BUILDING AT SEAVIEW HOSPITAL REHABILITATION CENTER & HOME. | 2022 | 3950 | 4012.4 | 302 | 0 | 11 | 585 | 0 | 0 | 4910.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75201502 | SEAVIEW EMERGENCY GENERATOR REPLACEMENT | ROUTINE RECONSTRUCTION | 502 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 460 BRIELLE AVENUE, STATEN ISLAND, NY 10314 | PROJECT WILL REPLACE FUEL TANK AND GENERATOR AT SEA VIEW HOSPITAL REHABILITATION CENTER AND HOME TO COMPLY WITH EPA CODE COMPLIANCE. | 2022 | 2233 | 2799.77 | 0 | 0 | 96 | 0 | 0 | 0 | 2895.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75202201 | SEAVIEW SHOWER ROOMS REPLACEMENT | ROUTINE RECONSTRUCTION |  | HO-R001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 460 BRIELLE AVENUE, STATEN ISLAND, NY 10314 | SEAVIEW SHOWER ROOMS REPLACEMENT | 2022 | 200 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 819 | HEALTH AND HOSPITALS CORP | 75202202 | SEAVIEW PEDIATRIC CENTER | ROUTINE RECONSTRUCTION |  | ED-0075 HO-0214 |  | 460 BRIELLE AVE, STATEN ISLAND NY | SEAVIEW PEDIATRIC CENTER (460 BRIELLE AVE, STATEN ISLAND NY) | 2022 | 0 | 0 | 0 | 0 | 0 | 17960 | 19740 | 0 | 37700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SER24 | Reconstruction of Existing Sewers, Staten Island | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 500 | SE-0002R EP-0007 |  |  | RECONSTRUCTION OF EXISTING SEWERS, STATEN ISLAND. THIS IS A 1 YEAR CONTRACT. THE TARGETED START DATE FOR THIS CONTRACT IS AS SOON AS THE PREVIOUS CONTRACT, EC-SER23, EXPIRES. | 2022 | 6013 | 0 | 0 | 0 | 5501 | 0 | 0 | 0 | 5501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | MIBBNC05B | Instal New Storm SE & Rplmt San SE & Dist WM Hylan Blvd SI | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 502 | SE-0200R SE-0002R WM-0001 |  |  | INSTALLATION OF NEW STORM SEWER AND REPLACEMENT OF SANITARY SEWERS AND DISTRIBUTION WATER MAINS IN HYLAN BOULEVARD - PHASE B. NYCDEP APPROVAL OF FINAL DESIGN DRAWINGS IS REQUIRED BEFORE PROCUREMENT. ALL EXISTING CATCH BASINS WITHIN THE PROJECT LIMITS MUST BE CLEANED. | 2022 | 37850 | 0 | 0 | 0 | 0 | 0 | 79132 | 0 | 79132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | NCMCCSG | NEW CLOVE PS: EQUIPMENT REPLACEMENT | WATER QUALITY PRESERVATION | 500 | WM-0105 |  |  | REPLACE SWITCHGEARS A& MCCS AT NEW CLOVE PS | 2022 | 22000 | 1280 | 0 | 0 | 3500 | 35000 | 0 | 0 | 39780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-125-L | RECONSTRUCTION OF SUBSTATION AT THE OAKWOOD BEACH WPCP | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 751 MILL ROAD STATEN ISLAND, N.Y. 10306 | RECONSTRUCTION OF SUBSTATION AT THE OAKWOOD BEACH WPCP. | 2022 | 13350 | 8276.58 | 45 | 0 | 0 | 0 | 0 | 0 | 8321.58 | 7408.97 | 0 | 0 | 0 | 0 | 0 | 0 | 7408.97
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-133-L | SLUDGE THICKENING IMPROVEMENT @ OAKWOOD BEACH WPCP | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 751 MILL ROAD STATEN ISLAND, NEW YORK 10306 | SLUDGE THICKENING IMPROVEMENT AT OAKEOOD BEACH WPCP | 2022 | 26201 | 5044.18 | 0 | 0 | 0 | 67478 | 0 | 0 | 72522.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-134-L | POWER DISTRIBUTION AT OAKWOOD BEACH WPCP | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 751 MILL ROAD STATEN ISLAND, N.Y. 10306 | POWER DISTRIBUTION AT OAKWOOD BEACH WPCP | 2022 | 3920 | 7773.26 | 0 | 0 | 4000 | 23500 | 0 | 0 | 35273.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-135-L | HEADWORKS AT OAKWOOD BEACH WPCP | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 751 MILL ROAD, STATEN ISLAND NEW YORK 10306 | HEADWORKS AT OAKWOOD BEACH WPCP | 2022 | 18610 | 600 | 0 | 0 | 4000 | 0 | 45000 | 0 | 49600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-136-L | INSTALLATION OF (2) MAIN TRANSFORMERS @ OAKWOOD BEACH WPCP | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 751 MILL ROAD STATEN ISLAND, N.Y. 10306 | INSTALLATION OF (2) MAIN TRANSFORMERS AT THE OAKWOOD BEACH WPCP | 2022 | 17676 | 4069.78 | 7000 | 0 | 20000 | 0 | 0 | 0 | 31069.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | OB-149-L | UPGRADE FIRE ALARM SYSTEM @ OAKWOOD BEACH DEWATERING BLDG | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 751 MILL ROAD STATEN ISLAND, N.Y. 10306 | UPGRADE FIRE ALARM SYSTEM @ OAKWOOD BEACH DEWATERING BLDG | 2022 | 2330 | 0 | 0 | 0 | 0 | 0 | 0 | 7200 | 7200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-132-L | RECONSTRUCTION OF SEA WALL/SLUDGE DOCK IMPROVEMENTS | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECONSTRUCTION OF SEA WALL/SLUDGE DOCK IMPROVEMENTS | 2022 | 3188 | 6255.94 | 0 | 0 | 6000 | 30000 | 0 | 0 | 42255.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-134-L | RECONSTRUCT FINAL SETTLING SYSTEM EQUIPMENT @ PORT RICHMOND | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RICHMOND TERRACE & BODINE STREET, STATEN ISLAND, N.Y. 10310 | RECONSTRUCT FINAL SETTLING SYSTEM EQUIPMENT @ PORT RICHMOND | 2022 | 6900 | 0 | 0 | 0 | 0 | 23000 | 0 | 0 | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-135-L | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ PORT RICHMOND | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RICHMOND TERRACE & BODINE STREET, STATEN ISLAND N.Y. 10310 | RECONSTRUCT POWER DISTRIBUTION EQUIPMENT @ PORT RICHMOND WWTP | 2022 | 10620 | 2421.42 | 0 | 0 | 6000 | 0 | 0 | 37500 | 45921.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-138-L | RECONSTRUCT MAIN SEWAGE PUMP CONTROLS @ PORT RICHMOND WWTP | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0112 |  | RICHMOND TERRACE & BODINE STREET, STATEN ISLAND, N.Y. 10310 | RECONSTRUCT MAIN SEWAGE PUMP CONTROLS @ PORT RICHMOND WWTP | 2022 | 45322 | 5429.97 | 96 | 38000 | 0 | 0 | 0 | 0 | 43525.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-139-L | RECONSTRUCT AERATION EQUIPMENT @ THE PORT RICHMOND WWTP | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0112 |  | RICHMOND TERRACE AND BODINE STREET, STATEN ISLAND, N.Y. 10310 | RECONSTRUCT AERATION EQUIPMENT @ THE PORT RICHMOND WWTP | 2022 | 24153 | 0 | 0 | 0 | 3500 | 0 | 0 | 38500 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-144-L | RECONSTRUCT BLOWERS AND CONTROLS @ PORT RICHMOND WPCP | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0112 |  | RICHMOND TERRACE AND BODINE STREET, STATEN ISLAND, N.Y 10310 | RECONSTRUCT BLOWERS AND CONTROLS @ PORT RICHMOND WPCP | 2022 | 2975 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PR-151-L | RECONST AERATION TANK GATES/ACTUATOR & SUPPORTS @ PR WRRF | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0112 |  |  | RECONSTRUCTION OF AERATION TANK GATES/ACTUATOR & SUPPORTS @ PORT RICHMOND WRRF | 2022 | 8000 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-276 | RECONSTRUCTION AT HANNAH STREET PUMPING STATION (BEDC) | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0269 |  | HANNAH STREET/MURRAY HULBERT AVENUE, STATEN ISLAND, N.Y. 10301 | RECONSTRUCTION AT HANNAH STREET P.S. (BEDC) | 2022 | 100225 | 105791.79 | 610 | 0 | 0 | 0 | 0 | 0 | 106401.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-287 | RECONSTRUCT ELTINGVILLE PUMPING STATION | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0269 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | ELTINGVILLE PUMPING STATION | ELTINGVILLE PUMPING STATION | 2022 | 9641 | 757.33 | 0 | 0 | 54063 | 0 | 0 | 0 | 54820.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-295 | RECONSTRUCTION AT MERSEREAU PUMPING STATION | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0269 |  | RECONSTRUCTION AT MESEREAU PUMPING STATION | RECONSTRUCTION AT MESEREAU PUMPING STATION | 2022 | 8552 | 0 | 0 | 0 | 0 | 2000 | 34000 | 0 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-296 | RECONSTRUCTION AT MELVIN PUMPING STATION | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0269 |  | RECONSTRUCTION AT MELVIN PUMPING STATION | RECONSTRUCTION AT MELVIN PUMPING STATION | 2022 | 5000 | 300 | 0 | 6000 | 0 | 0 | 0 | 0 | 6300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-317 | RECONSTRUCT VICTORY BOULEVARD PUMPING STATION STATEN ISLAND | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0269 |  | VICTORY VLVD., NEAR CON ED TRAVIS POWER PLANT SOUTH OF WEST SHORE EXTRESSWAY, STATEN ISLAND, NEW YORK | RECONSTRUCTION OF VICTORY BOULEVARD PUMPING STATION STATEN ISLAND, NEW YORK | 2022 | 6000 | 300 | 21505 | 0 | 0 | 44100 | 0 | 0 | 65905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-322 | RECONSTRUCT MAYFLOWER AVENUE PUMPING STATION, STATEN ISLAND | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0269 |  | MAYFLOWER AVENUE AND SRTHUR KILL ROAD, STATEN ISLAND, NEW YORK, 10309 | RECONSTRUCTION OF THE MAYFLOWER AVENUE PUMPING STATION, STATEN ISLAND, NEW YORK | 2022 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 43600 | 43600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-323 | RECONSTRUCT RICHMOND AVENUE PUMPING STATION, STATEN ISLAND | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0269 |  | RICHMOND AVENUE AND PROL PLACE, STATEN ISLAND, NEW YORK 10305 | RECONSTRUCTION OF RICHMOND AVENUE PUMPING STATION, STATEN ISLAND, NEWYORK | 2022 | 5200 | 0 | 0 | 2500 | 23000 | 0 | 0 | 0 | 25500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-384 | TRUNK AND DISTRIBUTION WATER MAIN IN FRONT ST, SI | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 501 | WM-0006 WM-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | TRUNK AND DISTRIBUTION WATER MAIN IN FRONT ST FROM HANNAH STREET TO VANDERBILT AVENUE, ETC. STATEN ISLAND | 2022 | 16997 | 0 | 0 | 0 | 0 | 16397 | 0 | 0 | 16397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED391A | Rplmt Upgrade WM & SE Infra Westervelt Ave Phase A, SI | AUGMENTATION OF WATER SUPPLY SYSTEMS | 501 | SE-0002R WM-0001 |  |  | REPLACE AND UPGRADE CURRENT WATER MAIN AND SANITARY SEWER INFRASTRUCTURE IN WESTERVELT AVENUE-PHASE A, STATEN ISLAND. DUE TO SEVERAL PASTWATER MAIN BREAKS, DEP DISTRIBUTION HAS RECOMMENDED THAT THE WATER MAINS BE REPLACED IN THIS AREA. WATER MAIN WORK ON BAY STREET BETWEEN MINTHRONE STREET AND NICK LAPORTE PLACE WILL BE COVERED UNDER PROJECTS HWR700 AND HWR703. | 2022 | 31476 | 0 | 0 | 0 | 0 | 31476 | 0 | 0 | 31476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED-392 | WM rplcmt in Bay St between Slosson Ter & Minthorne St SI | AUGMENTATION OF WATER SUPPLY SYSTEMS | 501 | SE-0002R WM-0001 |  |  | WATER MAIN REPLACEMENT IN BAY STREET BETWEEN SLOSSON TERRACE TO MINTHORNE STREET INTERSECTION, STATEN ISLAND. IN CONJUNCTION WITH NYC DOT PROJECT HWR703 | 2022 | 9005 | 0 | 0 | 0 | 11152 | 0 | 0 | 0 | 11152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | RED393 | Dist WM Rplmt on Hylan Blvd btwn Arbutus Hales Ave, SI | AUGMENTATION OF WATER SUPPLY SYSTEMS | 503 | WM-0001 SE-0200R SE-0002R WM-0006 |  |  | DISTRIBUTION WATER MAIN REPLACEMENT IN SI ON HYLAN BLVD BETWEEN ARBUTUS AVENUE & HALES AVENUE. THIS WORK WILL BE DONE IN CONJUNCTION WITH SI2018-02 | 2022 | 16150 | 0 | 0 | 0 | 0 | 21312 | 0 | 0 | 21312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SANDOB | RECONS OF THE OAKWOOD BEACH WPCP DUE TO HURRICANE SANDY | PLANT UPGRADING AND RECONSTRUCTION | 500 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECONSTRUCTION OF THE OAKWOOD BEACH WATER POLLUTION CONTROL PLANT DUETO HURRICANE SANDY | 2022 | 1277 | 0 | 0 | 850 | 0 | 500 | 4904 | 0 | 6254 | 0 | 0 | 7650 | 0 | 4500 | 44137 | 0 | 56287
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER002331 | Dist WM & San Storm SE Rplmt work in Rice Ave, SI | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 501 | SE-0002R SE-0200R WM-0001 |  |  | DISTRIBUTION WATER MAIN AND 6" SANITARY AND STORM SEWERS REPLACEMENT WORK IN RICE AVENUE, STATNE ISLAND. THIS PROJECT IS REQUIRED TO UPGRADE UNDERSIZED 6 INCH SANITARY SEWERS TO CURRENT DEP SEWER STANDARDS. | 2022 | 16048 | 0 | 0 | 0 | 16048 | 0 | 0 | 0 | 16048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200199 | STRM & SAN SEWER IN LAMOKA AV, LOVELACE AV, GENESSE AV, ETC | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 503 | SE-0002R SE-0200R WM-0001 |  |  | STRM & SAN SEWER IN LAMOKA AV- ESCANABA AV & DEMOPOLIS, LOVELACE AV- GENESSE AV & SCRANTON AVE, GENESSE AV- POMPEY AV & LOVELACE, ETC | 2022 | 18826 | 0 | 0 | 0 | 0 | 18826 | 0 | 0 | 18826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200256 | Extension & Replacmt of San Sewers in Victory Blvd SI | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 502 | SE-0200R SE-0002R WM-0001 |  |  | EXTENSION AND REPLACEMENT OF STORM AND SANITARY SEWERS IN VICTORY BLVD.. NOSTRAND AVE., ETC. BETWEEN GRAHAM AVE AND ARLENE ST TOGETHER WITHDISTRIBUTION WATER MAIN WORK | 2022 | 16608 | 0 | 0 | 21788 | 0 | 0 | 0 | 0 | 21788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SER200265 | Storm SE Ext in Park Dr N btwn Rivington Ave & Plymouth Rd | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 502 | SE-0200R |  |  | STORM SEWER EXTENSIONS IN PARK DRIVE NORTH BETWEEN RIVINGTON AVE AND PLYMOUTH ROAD, SI. | 2022 | 2795 | 0 | 0 | 2795 | 0 | 0 | 0 | 0 | 2795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SIBB2-OAK | STATEN ISLAND BLUEBELT - OAKWOOD BEACH | BLUEBELT PROGRAM | 500 503 | SE-0716 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | LAND ACQUISITION FOR THE DEVELOPMENT OF BLUEBELT TYPE STORM SEWERS IN THE OAKWOOD BEACH DRAINAGE AREA. | 2022 | 6814 | 11958.72 | 566 | 0 | 0 | 2972 | 0 | 0 | 15496.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 826 | DEPT ENVIRONMENTAL PROTECTION | SISEAWL-1 | US Army Corps SI Seawall Project | BLUEBELT PROGRAM | 502 | SE-0005 SE-0200R SE-0002R WM-0001 |  |  | BETTERMENTS TO BE MADE TO DEP FACILITIES IN CONJUNCTION WITH THE U.S.ARMY CORPS OF ENGINEER'S SEA WALL PROJECT. THIS WILL INCLUDE POND EXCAVATIONS, OUTFALL EXTENSIONS, SEWER REROUTING, AND WATERMAIN WORK. THIS PROJECT WILL REQUIRE SPECIAL COORDINATION WITH USACE AND DEP DUE TO ITS CONNECTION TO MULTIPLE OTHER CITY AND FEDERAL PROJECTS | 2022 | 100000 | 0 | 1869 | 98131 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S111-395D | DSNY STATEN ISLAND TRANSFER STATION Scales | SOLID WASTE MANAGEMENT | 501 502 503 | S-0111 |  |  | REPLACE TRUCK SCALES INCLUDING FOUNDATION PILES | 2022 | 550 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-366G | S I Compost Bagging Building | SOLID WASTE MANAGEMENT | 500 | S-0136 |  |  | CONSTRUCT COMPOST BAGGING BUILDING INCLUDING BAGGING EQUIPMENT | 2022 | 895 | 894.62 | 323 | 0 | 0 | 0 | 0 | 0 | 1217.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-367D | Staten Island 1 and 3 Garage Initial Outfitting | GARAGES AND FACILITIES | 501 503 | S-0136 |  |  | INITITAL OUTFITTING | 2022 | 700 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 827 | DEPARTMENT OF SANITATION | S136-374P | STATEN ISLAND 2 BOILER REPLACEMENT | GARAGES AND FACILITIES | 502 | S-0136 |  |  | BOILER REPLACEMENT | 2022 | 1414 | 0 | 112 | 169 | 1122 | 0 | 0 | 0 | 1403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | C5219FM5 | STATEN ISLAND FMF FACILITY UTILITIES UPGRADES X823.48 | FERRY MAINTENANCE FACILITY CONSTRUCTION | 501 | FA-0026 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HVAC, ELECTRICAL SYSTEM REPAIR | 2022 | 5280 | 2946.45 | 594 | 0 | 0 | 0 | 0 | 0 | 3540.45 | 7491.32 | 1250 | 0 | 0 | 0 | 0 | 0 | 8741.32
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | C5517B | DOCKBUILDING HARDWOOD TIMBER | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 501 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CITYWIDE | HARDWOOD TIMBER REPAIR AT FERRY FACILITIES | 2022 | 1727 | 4939.94 | 500 | 500 | 548 | 500 | 1000 | 2261 | 10248.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | C5588 | REPLACEMENT OF OIL BARGE #5 | RECONSTRUCTION OF FERRY BOATS | 500 501 | FA-0313 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | OIL BARGE#5 REPLACE | 2022 | 8050 | 0 | 0 | 0 | 0 | 0 | 0 | 8050 | 8050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | C5590 | DRYDOCK MOLINARI FERRY BOATS | RECONSTRUCTION OF FERRY BOATS | 500 501 | FA-0313 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DRYDOCK F/BOATS | 2022 | 22550 | 19243.35 | 2810 | 2890 | 2981 | 0 | 0 | 0 | 27924.35 | 8904.91 | 0 | 0 | 0 | 0 | 0 | 0 | 8904.91
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FABLDG45R | Building 45 Rehabilitation | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REHABILITATION OF BUILDING 45 | 2022 | 1985 | 1105.31 | 899 | 6546 | 0 | 0 | 0 | 0 | 8550.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FABOLLIS | Drydock and Reconstruction of Ollis Class Ferryboats | RECONSTRUCTION OF FERRY BOATS | 500 | FA-0313 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DRYDOCK AND RECONSTRUCTION OLLIS CLASS FERRYBOATS | 2022 | 1800 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FASEAWALL | Ferry Maintenance Facility Seawall PinX823.78 | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FERRY MAINTENANCE FACILITY SEAWALL RECONSTRUCTION | 2022 | 3250 | 0 | 117 | 0 | 0 | 570 | 0 | 0 | 687 | 0 | 468 | 0 | 0 | 2279 | 0 | 0 | 2747
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FASGTRCN | St.George Ferry Terminal Waterfront Remediation | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 | FA-0021 |  |  | SGT FERRY TERMINAL BULKHEAD RECONSTRUCTION | 2022 | 20458 | 85.37 | 115 | 3500 | 0 | 0 | 880 | 5620 | 10200.37 | 341.51 | 0 | 8000 | 0 | 0 | 0 | 0 | 8341.51
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FASGTRHB | SGT Terminal Brick Facade Rehabilitation | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SGT TERMINAL BRICK FACADE REHABILITATION | 2022 | 750 | 0 | 0 | 0 | 0 | 50 | 700 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FAUREABRG | SIF Diesel Exhaust Fluid (DEF) Storage & Distribution | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 | FA-0021 |  |  | STATEN ISLAND FERRY UREA BARGE | 2022 | 1500 | 297.9 | 4209 | 0 | 0 | 0 | 0 | 0 | 4506.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FBENVCOM | Ferryboat Environmental Compliance Upgrades | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ENVIRONMENTAL COMPLIANCE UPGRADES | 2022 | 5500 | 417.61 | 783 | 0 | 0 | 0 | 0 | 2287 | 3487.61 | 0 | 5021 | 0 | 0 | 0 | 0 | 0 | 5021
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FERRYR1SG | Construction of Ferryrack at Slip1, St. George Terminal | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CONSTRUCTION OF FERRYRACK SLIP1 SGT | 2022 | 23680 | 0 | 0 | 0 | 10336 | 9985 | 3359 | 0 | 23680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FERRYR3SG | Construction of Ferryrack at Slip3, St. George Terminal | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CONSTRUCTION OF FERRYRACK AT SLIP3, ST. GEORGE TERMINAL | 2022 | 7770 | 569.07 | 0 | 2201 | 3000 | 0 | 2000 | 0 | 7770.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FERRYRACK | CONSTRUCTION OF FERRY RACK | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 501 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CONST OF NEW FERRY RACK ST.GEORGE/WHITEHALL | 2022 | 15500 | 2674.38 | 0 | 325 | 675 | 5011 | 2263 | 16568 | 27516.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FMFVARNR | FMF Vehicle Access Ramps and Nose Upgrade | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 | FA-0026 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RAMPS AND NOSE RACK UPGARDE | 2022 | 4000 | 546.7 | 724 | 3400 | 0 | 0 | 0 | 0 | 4670.7 | 0 | 0 | 8973 | 0 | 0 | 0 | 0 | 8973
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | FVESSGANR | Facility/Vessel Gangways Replacement/Upgrade | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | GANGWAY REPLACEMENT | 2022 | 3300 | 287.02 | 0 | 220 | 600 | 0 | 0 | 181 | 1288.02 | 0 | 0 | 1980 | 720 | 0 | 0 | 0 | 2700
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBR249730 | BR OVER DAM OVER NORTH END CLOVE LAKE BIN 2249730 | FAIR BRIDGES | 500 | P-0508 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BR OVER DAM OVER NORTH END CLOVE LAKE BIN 2249730 | 2022 | 7062 | 0 | 714 | 0 | 815 | 5704 | 0 | 0 | 7233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24939 | CEDARVIEW AVE PED BRIDGE BIN: 2249390 | FAIR BRIDGES | 500 | HB-1012 HB-4939 |  | CEDARVIEW AVE PED BRIDGE BIN:2249390 | CEDARVIEW AVE PED BRIDGE BIN:2249390 | 2022 | 9819 | 1688.36 | 0 | 252 | 0 | 8823 | 1 | 0 | 10764.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRA24982 | ARTHUR KILL RD/ ARTHUR KILL STREAM BIN#2249820 | FAIR BRIDGES | 500 | HB-4982 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | ARTHUR KILL RD/ ARTHUR KILL STREAM BIN#2249820 | ARTHUR KILL RD/ ARTHUR KILL STREAM BIN#2249820 | 2022 | 10350 | 799.2 | 0 | 682 | 0 | 9350 | 0 | 0 | 10831.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HBRSGFT17 | ARMAJANI STRUCTURE | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 500 | PV-0467 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ARMAJANI STRUCTURE | 2022 | 2701 | 226 | 0 | 0 | 0 | 1100 | 0 | 0 | 1326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR19E | Citywide Milling - Staten Island | PRIMARY STREET RESURFACING | 500 | HW-0002K HW-0002R | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITYWIDE MILLING- STATEN ISLAND | 2022 | 7739 | 14824.21 | 6661 | 0 | 0 | 0 | 0 | 0 | 21485.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-07 | North Bridge Street/South Bridge Street - Construction | PRIMARY STREET RECONSTRUCTION | 500 | HW-0001R | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NORTH BRIDGE STREET/SOUTH BRIDGE STREET - CONSTRUCTION OF A CONNECTORROAD | NORTH BRIDGE STREET/SOUTH BRIDGE STREET - CONSTRUCTION OF A CONNECTORROAD | 2022 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-08 | Victory CPI | PRIMARY STREET RECONSTRUCTION | 500 | HW-D104 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | VICTORY CPI | VICTORY CPI | 2022 | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-09 | Pleasant Plains Park and Ride | PRIMARY STREET RECONSTRUCTION | 500 | HW-D104 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PLEASANT PLAINS PARK AND RIDE FY19 SECTION 254 RESO ADD $895,000 CM BORELLI | 2022 | 2895 | 0 | 0 | 0 | 0 | 3995 | 0 | 0 | 3995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-10 | Sidewalks along Forest Hill Rd btw Ashworth and Ballfield | PRIMARY STREET RECONSTRUCTION | 500 | HW-D200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NYC PARKS DEPARTMENT - SIDEWALKS ALONG FOREST HILL ROAD BETWEEN ASHWORTH AVENUE AND THE BALLFIELD | NYC PARKS DEPARTMENT - SIDEWALKS ALONG FOREST HILL ROAD BETWEEN ASHWORTH AVENUE AND THE BALLFIELD | 2022 | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWD104-11 | Christopher Lane Extension | PRIMARY STREET RECONSTRUCTION | 500 | HW-D104 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CHRISTOPHER LANE EXTENSION | CHRISTOPHER LANE EXTENSION | 2022 | 4000 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR00513 | Street Widening in the 50th Council District | PRIMARY STREET RECONSTRUCTION | 500 | HW-D104 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | STREET WIDENING IN THE 50TH COUNCIL DISTRICT | STREET WIDENING IN THE 50TH COUNCIL DISTRICT | 2022 | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR703 | Bay Street Area Safety Improvements | PRIMARY STREET RECONSTRUCTION | 500 | HW-0001R |  |  | BAY STREET AREA SAFETY IMPROVEMENTS | 2022 | 15316 | 0 | 0 | 0 | 0 | 27743 | 0 | 0 | 27743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR705 | Clove Road and Howard Avenue Re-alignment | PRIMARY STREET RECONSTRUCTION | 500 | HW-0001 HW-0001K | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CLOVE ROAD AND HOWARD AVENUE RE-ALIGNMENT | CLOVE ROAD AND HOWARD AVENUE RE-ALIGNMENT | 2022 | 7678 | 0 | 0 | 1097 | 0 | 6581 | 0 | 0 | 7678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR706 | Willowbrook Road Sidewalks | PRIMARY STREET RECONSTRUCTION | 500 | HW-0001K | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WILLOWBROOK ROAD SIDEWALKS | WILLOWBROOK ROAD SIDEWALKS | 2022 | 5349 | 0 | 0 | 765 | 0 | 0 | 0 | 4584 | 5349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR72017 | Richmond Ave Ped Safety | PRIMARY STREET RECONSTRUCTION | 500 | HW-R005 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RICHMOND AVE PEDESTRIAN SAFETY FOR THE INTERSECTION OF RICHMOND AVE AND FOREST HILL ROAD | 2022 | 250 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR920 | Huguenot Park N Ride | PRIMARY STREET RECONSTRUCTION |  | HW-0001R | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HUGUENOT PARK N RIDE | 2022 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWR921 | Mid Island Blue Belt Street Reconstruction | PRIMARY STREET RECONSTRUCTION | 500 | HW-0988 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MID ISLAND BLUE BELT STREET RECONSTRUCTION | MID ISLAND BLUE BELT STREET RECONSTRUCTION | 2022 | 24000 | 0 | 0 | 0 | 0 | 1000 | 23000 | 0 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWRFPATH | Arthur Kill Road Build-out | FACILITY RECONSTRUCTION | 500 | HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | ARTHUR KILL ROAD BUILD-OUT | ARTHUR KILL ROAD BUILD-OUT | 2022 | 22327 | 0 | 0 | 0 | 0 | 0 | 22327 | 0 | 22327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWRFVLMN | Villa Marin | FACILITY RECONSTRUCTION | 500 | HW-0003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | VILLA MARIN | VILLA MARIN | 2022 | 452 | 0 | 452 | 0 | 0 | 0 | 0 | 0 | 452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | HWSCD50 | Sidewalk Construction in Council District 50 | PRIMARY STREET RECONSTRUCTION | 500 | HW-D104 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SIDEWALK CONSTRUCTION/RECONSTRUCTION IN COUNCIL DISTRICT 50 | SIDEWALK CONSTRUCTION/RECONSTRUCTION IN COUNCIL DISTRICT 50 | 2022 | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | ITSKOREAN | Intelligent Transportation Systems on Korean Vet Pky X501.65 | SIGNAL INSTALLATION AND COMPUTERIZATION | 500 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PIN X501.65 IMPLEMENTING AN ITS SYSTEM (SMART ZONES) ALONG THE KOREANWAR VETERANS PKWY/RICHMOND AVE | 2022 | 2069 | 302.31 | 44 | 68 | 0 | 0 | 0 | 0 | 414.31 | 1209.27 | 177 | 269 | 0 | 0 | 0 | 0 | 1655.27
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | NDF-BSIMP | NDF - Bay Street Streetscape Improvements | NEIGHBORHOOD REVITALIZATION | 500 | ED-0384 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NDF - REAL TIME PASSENGER INFORMATION BAY STREET | 2022 | 11400 | 0 | 3031 | 0 | 0 | 8369 | 0 | 0 | 11400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | NDF-BSRTP | NDF - Real Time Passenger Information Bay Street | NEIGHBORHOOD REVITALIZATION | 500 | ED-0384 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NDF - REAL TIME PASSENGER INFORMATION BAY STREET | 2022 | 900 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDHWSIB | Swaim & Huguenot Ave Improvements | PRIMARY STREET RECONSTRUCTION | 500 | HW-0001R | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SWAIM & HUGUENOT AVE IMPROVEMENTS | SWAIM & HUGUENOT AVE IMPROVEMENTS | 2022 | 1240 | 0 | 0 | 0 | 124 | 0 | 0 | 0 | 124 | 0 | 0 | 0 | 1116 | 0 | 0 | 0 | 1116
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDRF09 | FMF Emergency Generator Installation | FERRY MAINTENANCE FACILITY CONSTRUCTION | 500 | FA-0026 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | INSTALLATION OF EMERGENCY GENERATOR AT FMF | 2022 | 1131 | 784.92 | 36 | 1 | 0 | 0 | 0 | 0 | 821.92 | 1709.34 | 309 | 0 | 0 | 0 | 0 | 0 | 2018.34
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | SANDSIFMF | Whitehall Ferry Terminal Roof Replacement | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SIF FACILITIES RESTORATION & REPLACEMENT - HURRICANE SANDY | SIF FACILITIES RESTORATION & REPLACEMENT - HURRICANE SANDY | 2022 | 1541 | 130.43 | 0 | 0 | 0 | 0 | 328 | 0 | 458.43 | 479.46 | 0 | 0 | 0 | 0 | 0 | 0 | 479.46
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | STGTELPAN | St. George Terminal Electrical Panel Upgrade | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | STG TERMINAL ELEC PANEL UPGRADE | 2022 | 1300 | 606.67 | 0 | 0 | 0 | 0 | 0 | 694 | 1300.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | STGTROOF | Reconstruction of St.George Terminal Roof | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECON OF ST GEORGE TERMINAL ROOF | 2022 | 4400 | 625.22 | 900 | 0 | 0 | 678 | 421 | 2000 | 4624.22 | 0 | 4704 | 0 | 0 | 0 | 0 | 0 | 4704
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | STGWIRERP | ST. GEORGE FERRY SLIPS WIRE ROPES, X823.66 | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 500 501 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | ST. GEORGE FERRY SLIPS WIRE ROPES | ST. GEORGE FERRY SLIPS WIRE ROPES | 2022 | 2750 | 2140.15 | 836 | 0 | 0 | 0 | 0 | 0 | 2976.15 | 4903.1 | 825 | 0 | 0 | 0 | 0 | 0 | 5728.1
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | TFD503-07 | GREAT KILLS MUNICIPAL PARKING LOT LIGHTING | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 500 502 503 | TF-D503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | TRAFFIC CONTROL ISLAND | TRAFFIC CONTROL ISLAND | 2022 | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 841 | DEPARTMENT OF TRANSPORTATION | TFR0103 | Smart Lights-various locations Staten Island | SIGNAL INSTALLATION AND COMPUTERIZATION | 500 | TF-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SMART LIGHTS-VARIOUS LOCATION STATEN ISLAND | TO PURCHASE AND TO INSTALL SMART LIGHTS AT VARIOUS INTERSECTIONS ON STATEN ISLAND | 2022 | 850 | 888.45 | 372 | 0 | 0 | 0 | 0 | 0 | 1260.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | GRSIGI-01 | Staten Island Parking Lot Green Infrastructure Construction | LAND ACQUISITION AND TREE PLANTING | 500 | P-1018 |  | STATEN ISLAND PARKING LOT GREEN INFRASTRUCTURE CONSTRUCTION | STATEN ISLAND PARKING LOT GREEN INFRASTRUCTURE CONSTRUCTION | 2022 | 1721 | 0 | 0 | 0 | 810 | 790 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | HWPLZ001R | Van Name/Van Pelt Plaza | PRIMARY STREET RECONSTRUCTION | 500 501 | HW-1684 P-0245R | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | VAN NAME/VAN PELT | VAN NAME/VAN PELT | 2022 | 2000 | 4331.2 | 10 | 49 | 0 | 266 | 0 | 0 | 4656.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | NDF-VHALL | NDF-Village Hall Roof R028-120M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | ED-0384 |  | CANAL STREET, WATER STREET, BAY STREET. | BAY STREET REZONING -TAPPAN VILLAGE HALL | 2022 | 5700 | 150 | 0 | 4067 | 0 | 413 | 124 | 1096 | 5850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501ALAS | Alice Austen House-Landscape & Site Impr. R117- | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-D020 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | ALICE AUSTEN HOUSE-LANDSCAPE & SITE IMPR. | ALICE AUSTEN HOUSE-LANDSCAPE & SITE IMPR. | 2022 | 750 | 73.73 | 0 | 0 | 640 | 559 | 0 | 0 | 1272.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CLEX | Clove Lakes Pk-Adult Exercise Equipment R005-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-D020 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | CLOVE LAKES PK-ADULT EXERCISE EQUIPMENT | CLOVE LAKES PK-ADULT EXERCISE EQUIPMENT | 2022 | 700 | 549.25 | 27 | 0 | 0 | 140 | 0 | 0 | 716.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CLP2 | Cloves Lakes Walking Path Rehab R005 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 | P-D020 |  | STATEN ISLAND | CLOVES LAKES WALKING PATH REHAB R005 | 2022 | 4250 | 136 | 0 | 0 | 2130 | 2120 | 0 | 0 | 4386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501CRPL | CPL. Thompson Park | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 501 | P-D020 |  | BROADWAY, HENDERSON AVENUE, CHAPPELL STREET. BOROUGH OF SI. | CPL THOMPSON PARK - RECONSTRUCT TRACK AND FIELD, AND OTHER PARK RENOVATIONS | 2022 | 3525 | 0 | 0 | 4050 | 0 | 0 | 0 | 0 | 4050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501FABL | Faber Park-Install of active recreation, lighting-R008-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 P-D020 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | FABER PARK, STATEN ISLAND | FABER PARK -ISTALLATION OF ACTIVE RECREATION, LIGHTING | 2022 | 5405 | 6605.56 | 11 | 0 | 0 | 872 | 0 | 0 | 7488.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501FPFA | Faber Park Rec. Center: Fire Alarm Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 501 | P-0506 |  | 2175 RICHMOND TERRACE,STATEN ISLAND, NY 10301 | FIRE ALARM RECONSTRUCTION AT FABER PARK REC. CENTER. | 2022 | 272 | 0 | 0 | 272 | 0 | 0 | 0 | 0 | 272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501JWPK | Jones Woods Park Trail Restoration R048 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-D020 P-0822 |  | STATEN ISLAND | JONES WOODS PARK TRAIL RESTORATION R048 | 2022 | 80 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501LLCS | Luis Lopez Park Modular Comfort Station Cons. R125-120M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-0505 |  |  | LUIS LOPEZ PARK MODULAR COMFORT STATION CONSTRUCTION | 2022 | 2396 | 679.62 | 3184 | 212 | 0 | 0 | 0 | 0 | 4075.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501LPFA | Lyons Pool Rec. Center: Fire Alarm Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 501 | P-0506 |  | 6 VICTORY BLVD STATEN ISLAND, NY 10301 | FIRE ALARM RECONSTRUCTION AT LYONS POOL REC. CENTER | 2022 | 299 | 29 | 0 | 315 | 0 | 0 | 0 | 0 | 344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501NAPL | Naple Plgr-Reconstruction R073-119M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 500 | P-D020 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NAPLE PLGR-NETTING SI | NAPLE PLGR-NETTING | 2022 | 49 | 307 | 2566 | 317 | 232 | 0 | 0 | 0 | 3422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-501PRLL | Prall Playground - Remove & Replace Artifical Turf | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 501 | P-R245 P-D020 |  | ELIZABETH STREET, CLOVE LAKE, FOREST, BROADWAY - BOROUGH OF STATEN ISLAND | PRALL PLAYGROUND | 2022 | 215 | 0 | 200 | 0 | 50 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502CTPK | MIDLAND BEACH PROMENADE ENTRY PLAZA & PARKING LT R046-107MA2 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 502 | HW-R005 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | TO CONSTRUCT A CHILDRENS THEME PK NEAR THE SOUTH BEACH BOARDWALK | 2022 | 5643 | 6963.14 | 121 | 0 | 0 | 0 | 0 | 0 | 7084.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502GBFA | Greenbelt Rec. Center: Fire Alarm Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 502 | P-0506 |  | 501 BRIELLE AVENUE, STATEN ISLAND, NEW YORK 10314 | FIRE ALARM RECONSTRUCTION AT GREENBELT REC. CENTER | 2022 | 305 | 0 | 305 | 0 | 0 | 0 | 0 | 0 | 305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502GBRE | Greenbelt Recreation Center Basketball Cts RC | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 | P-D020 |  |  | GREENBELT RECREATION CENTER BASKETBALL CTS RC | 2022 | 2500 | 0 | 0 | 0 | 1255 | 1245 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502OCEA | Ocean Breeze Athletic Complex Track RC | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 | P-0506 P-1018 |  | OCEAN BREEZE ATHLETIC COMPLEX TRACK RC | OCEAN BREEZE ATHLETIC COMPLEX TRACK RC | 2022 | 2780 | 0 | 0 | 2780 | 0 | 0 | 0 | 0 | 2780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502OTWN | Oldtown Playground | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 502 | P-D020 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PARKINSON AVENUE AND KRAMER STREET, BOROUGH OF STATEN ISLAND | OLD TOWN PLAYGROUND RECONSTRUCTION | 2022 | 4570 | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502RUSS | Detective Russell Timoshenko Synthetic Turf Field | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-D020 |  |  | DETECTIVE RUSSELL TIMOSHENKO SYNTHETIC TURF FIELD | 2022 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-502SHML | Schmul Park Playground | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 502 | P-R245 |  | WILD AVENUE, PEARSON STREET MELVIN AVENUE | SCHMUL PARK RENOVATION | 2022 | 5050 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503AESP | Aesop Park - Safety Surface | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 503 | P-R245 |  | BARTOW STREET AND PAGE STREET- BOROUGH OF STATEN ISLAND. | AESOP PARK - REMOVAL & REPLACEMENT OF EXISTING PLAY EQUIPMENT AND BENCHES AND REPLACE WOOD CHIPS FOR SAFETY SURFACE. | 2022 | 3290 | 0 | 3140 | 0 | 0 | 0 | 0 | 0 | 3140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CLSN | Clawson Playground - Multi Purpose Area | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 503 | P-D020 |  | ADELAIDE AVENUE & CLAWSON - BOROUGH OF STATEN ISLAND. | CLAWSON PLAYGROUND - MULTI-PURPOSE PLAY AREA RECONSTRUCTION/LAWN CONSTRUCTION | 2022 | 4700 | 0 | 0 | 0 | 0 | 4600 | 0 | 0 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503CRBP | CRESCENT BEACH PARK CONS 135-113MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 503 | P-D020 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CRESCENT BEACH PARK, BOROUGH OF S.I. | CONSTRUCTION OF NEW PARK | 2022 | 1200 | 2974.76 | 48 | 0 | 0 | 0 | 0 | 0 | 3022.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503DUPL | DUGAN PLAYGROUND R/C R026-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-0245R P-D020 |  | DUGAN PLAYGROUND R/C R026- | DUGAN PLAYGROUND R/C R026- | 2022 | 3732 | 284.18 | 3131 | 0 | 524 | 0 | 0 | 0 | 3939.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503GCPG | Greencroft Playgroud R089 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 503 | P-D020 P-0245R |  | STATEN ISLAND | GREENCROFT PLAYGROUD R089 | 2022 | 1500 | 0 | 250 | 0 | 4150 | 0 | 4000 | 0 | 8400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503GCPL | Greencroft Plgr- R/C of Comfort Station R089-115M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 503 | P-R245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | GREENCROFT PLAYGROUND , BROOKLYN | RECONSTRUCTION OF THE COMFORT STATION AT GREENCROFT PLAYGROUND | 2022 | 3102 | 3660.57 | 92 | 0 | 0 | 0 | 0 | 0 | 3752.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503LEMN | Lemon Creek Park- Reconstruction | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 500 503 | P-D020 |  | BOROUGH OF STATEN ISLAND | LEMON CREEK PARK | 2022 | 1610 | 0 | 0 | 0 | 755 | 745 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503SNCS | Seaside Nature Pk CS construction R145-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 503 | P-D020 P-0245R P-0505 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SEASIDE NATURE PARK, SI | THE CONSTRUCTION OF A NEW COMFORT STATION AT SEASIDE NATURE PARK | 2022 | 1207 | 657 | 0 | 5449 | 1305 | 0 | 0 | 0 | 7411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-503TOTT | Tottenville Shoreline Protection - Staten Island | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | PU-0100 PU-0200 |  |  | TOTTENVILLE SHORELINE PROTECTION - MANHATTAN | 2022 | 19225 | 135 | 0 | 19200 | 0 | 0 | 0 | 0 | 19335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH01 | Anchor Park Site - South Pk Fresh kills DESIGN | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 | P-1018 P-1321 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | SOUTH PK FRESH KILS | ANCHOR PARK SITE - SOUTH PK FRESH KILS | 2022 | 4492 | 3969.7 | 61 | 0 | 0 | 1104 | 0 | 0 | 5134.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH02 | Anchor Park Site - South Pk Construction /Fresh kills | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 | P-1321 |  | ANCHOR PARK SITE - SOUTH PK CONSTRUCTION /FRESH KILLS | ANCHOR PARK SITE - SOUTH PK CONSTRUCTION /FRESH KILLS | 2022 | 27000 | 155 | 0 | 0 | 13600 | 0 | 13400 | 0 | 27155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ANCH03 | Anchor Park Site - South Pk CS /Fresh kills | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 | P-1321 |  | ANCHOR PARK SITE - SOUTH PK CS /FRESH KILLS | ANCHOR PARK SITE - SOUTH PK CS /FRESH KILLS | 2022 | 5200 | 90 | 0 | 0 | 2610 | 2590 | 0 | 0 | 5290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5ARDTR | Arden Heights Wood -Trails & Parking R120-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-0245R | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | ARDEN HEIGHTS WOOD -TRAILS & PARKING, SI | ARDEN HEIGHTS WOOD -TRAILS & PARKING | 2022 | 0 | 1640.04 | 414 | 0 | 0 | 0 | 0 | 0 | 2054.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BBPAV | Multisite SI-Basketball Cours paving R | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-0245R P-D020 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | MULTISITE SI-BASKETBALL COURS PAVING | MULTISITE SI-BASKETBALL COURS PAVING | 2022 | 555 | 3027.64 | 26 | 0 | 0 | 365 | 0 | 0 | 3418.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BLOOJF | Bloomingdale Park Junior Fields Installation | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-R245 P-D020 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BLOOMINGDALE PARK - INSTALLATION OF JUNIOR FIELDS: REMOVE EXISTING SOFTBALL FIELD AND REPLACE WITH TWO SYNTHETIC TURF JUNIOR FIELDS. 1150 CLOVE ROAD, STATEN ISLAND 10301 | 2022 | 4625 | 4835.06 | 1 | 13 | 0 | 1200 | 0 | 0 | 6049.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5BUNBCH | Buono Beach-Reconstruction of Fountain | BEACHES AND BOARDWALKS | 500 | P-D020 P-1018 |  |  | BUONO BEACH-RECONSTRUCTION OF FOUNTAIN | 2022 | 131 | 0 | 382 | 0 | 0 | 0 | 0 | 0 | 382 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 200
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CHARCS | Fairview Park - Cons. Comfort Station R153-218M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 503 | P-D020 P-R245 |  |  | FAIRVEIEW PARK COMFORT STATION RECON | 2022 | 3954 | 3296.54 | 269 | 0 | 0 | 0 | 0 | 0 | 3565.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CHARLS | Fairview Park Landscape Construction | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 503 | P-R245 P-D020 P-0245R | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS |  | FAIRVIEW PARK LANDSCAPE CONSTRUCTION | 2022 | 12299 | 9195.71 | 64 | 0 | 0 | 1676 | 0 | 0 | 10935.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLAWS | RENOVATION OF CLAWSON PLAYGROUND | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 503 | P-D020 P-0245R | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | ADELAIDE AVE., CLAWSON ST. | PARKS - CLAWSON PLAYGROUND RENOVATION: RENOVATION OF CLAWSON PLAYGROUND; 1150 CLOVE ROAD, STATEN ISLAND 10301 | 2022 | 1900 | 3046.39 | 0 | 0 | 0 | 249 | 0 | 0 | 3295.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLVCHL | Recon chiller slab & header at Cloves Lake Park R005-120M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1250 |  | CITYWIDE | RECON CHILLER SLAB & HEADER AT CLOVES LAKE PARK | 2022 | 1656 | 178 | 0 | 0 | 1600 | 1600 | 0 | 0 | 3378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CLVLKP | Clove Lakes Park | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-D020 P-1018 P-0245R |  | CLOVE LAKES PARK, STATEN ISLAND | CLOVE LAKES PARK | 2022 | 1500 | 30 | 334 | 6000 | 0 | 0 | 0 | 0 | 6364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIB12 | CPI PH1- SI COMFORT STATIONS -BUNDLE 3 RG-216MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CPI - SI COMFORT STATIONS -BUNDLE 3 RG-216M | 2022 | 9676 | 8368.04 | 0 | 0 | 0 | 1487 | 0 | 0 | 9855.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIBN6 | CPI - SI Comfort Stations-Bundle 2 RG-515M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CPI-SI COMFORT STATIONS-BUNDLE 6 | CPI-SI COMFORT STATIONS-BUNDLE 2 | 2022 | 8076 | 3889.18 | 73 | 0 | 0 | 0 | 0 | 0 | 3962.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPILLP | CPI - LT LIA PLGD | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 |  |  | LT LIA PLGD | 2022 | 7800 | 0 | 0 | 0 | 3010 | 2990 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIMDP | CPI PH1- McDonald Playground reconstruction | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | STATEN ISLAND CPI-MCDONALD PLAYGROUND | CPI-MCDONALD PLAYGROUND RECONSTRUCTION | 2022 | 4490 | 5797.54 | 0 | 0 | 0 | 100 | 0 | 0 | 5897.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPIMH | CPI PH2 - Mariner's Harbor Playground-RC R036-118M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 | P-D020 P-1018 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | CPI PH - MARINER'S HARBOR PLAYGROUND-RECONSTRUCTION | CPI PH2 - MARINER'S HARBOR PLAYGROUND-RECONSTRUCTION | 2022 | 2258 | 3695.16 | 12 | 0 | 0 | 0 | 633 | 0 | 4340.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5CPISTP | CPI PH2 - RC-Stapleton Playground- R061-116M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 | P-1018 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | CPI - STAPLETON PLAYGROUND-RECONSTRUCTION | CPI - STAPLETON PLAYGROUND-RECONSTRUCTION | 2022 | 11076 | 11285.35 | 21 | 0 | 0 | 311 | 0 | 0 | 11617.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5DCTFRV | Fairview Park Telecom conduit installation | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-0931 |  | FAIRVIEW PARK, STATEN ISLAND | FAIRVIEW PARK TELECOM CONDUIT INSTALLATION | 2022 | 110 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5DONGAN | Dongan Plgr-reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-D020 |  | DONGAN PLGR-RECONSTRUCTION, SI | DONGAN PLGR-RECONSTRUCTION | 2022 | 3875 | 267.74 | 8 | 148 | 1556 | 1745 | 0 | 0 | 3724.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FABBAS | Faber Park -Remove Equipment & Install Basketball Court | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 | P-D020 |  | FABER PARK -REMOVE EQUIPMENT & INSTALL BASKETBALL COURT | FABER PARK -REMOVE EQUIPMENT & INSTALL BASKETBALL COURT | 2022 | 700 | 220 | 4 | 0 | 1962 | 0 | 0 | 0 | 2186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FABRWF | Faber Park Waterfront | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 | PU-0200 P-0501 |  |  | FABER PARK WATERFRONT | 2022 | 1505 | 50 | 0 | 0 | 1017 | 0 | 356 | 0 | 1423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRES10 | FRESH KILLS OWL HOLLOW FIELDS C/S | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 | P-1321 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FRESH KILLS OWL HOLLOW FIELDS C/S | 2022 | 9160 | 859.3 | 24 | 0 | 4204 | 4619 | 0 | 0 | 9706.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRES11 | Owl Hollow Parking Access Road - R017-121M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 | P-1321 |  |  | OWL HOLLOW PARKING ACCESS ROAD | 2022 | 550 | 85 | 0 | 0 | 455 | 45 | 0 | 0 | 585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRESH9 | Fresh Kills - construction of North Park R017-115M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 502 503 | P-1321 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | STATEN ISLAND | NORTH PARK MULTI-USE PATH AND WETLAND RESTORATION | 2022 | 2080 | 28031.56 | 250 | 0 | 0 | 2093 | 0 | 0 | 30374.56 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 1650
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5FRESHS | Fresh Kills - Springville Greenway bicycle path RG-410M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 502 503 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SECTION OF FRESH KILLS PARK, BOROUGH OF STATEN ISLAND | SECTION OF FRESH KILLS PARK, BOROUGH OF STATEN ISLAND | 2022 | 12250 | 3229.89 | 0 | 0 | 0 | 0 | 0 | 0 | 3229.89 | 7074.91 | -896 | 0 | 0 | 0 | 1692 | 0 | 7870.91
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GBRCTF | Greenbelt Rec.Cntr-Constr. of turf field | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-D020 |  | GREENBELT REC.CNTR-CONSTR. OF TURF FIELD, SI | GREENBELT REC.CNTR-CONSTR. OF TURF FIELD | 2022 | 5500 | 451.48 | 0 | 0 | 5299 | 0 | 0 | 0 | 5750.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GKBIKE | GREAT KILLS BICYCLE PATH R016-204MA | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 503 | P-1322 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | GREAT KILLS PARK, STATEN ISLAND | CONSTRUCTION OF GREAT KILLS BICYCLE PATH | 2022 | 1600 | 500.59 | 0 | 0 | 0 | 0 | 0 | 0 | 500.59 | 1052.32 | 0 | 0 | 0 | 147 | 0 | 0 | 1199.32
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GRNBRC | Greenbelt Rec Ctr Partial RC R129-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-0506 P-0505 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | GREENBELT RECREATION CENTER IN SI | PARTIAL RECONSTRUCTION OF GREENBELT RECREATION CENTER IN SI | 2022 | 1000 | 89.96 | 1498 | 0 | 0 | 0 | 0 | 0 | 1587.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5GSIGI1 | Staten Island Parks Green Infrastructure Construction | LAND ACQUISITION AND TREE PLANTING | 500 | P-1018 |  | STATEN ISLAND PARKS GREEN INFRASTRUCTURE CONSTRUCTION | STATEN ISLAND PARKS GREEN INFRASTRUCTURE CONSTRUCTION | 2022 | 1300 | 0 | 0 | 0 | 610 | 590 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5HEROPK | Hero Park Path Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 |  | CITYWIDE | HERO PARK PATH RECONSTRUCTION | 2022 | 195 | 0 | 0 | 0 | 195 | 0 | 0 | 0 | 195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5IRENE | IRENE - Wolfe's Pond Park Berm | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 |  | WOLFE'S POND PARK BERM | WOLFE'S POND PARK BERM | 2022 | 943 | 13.64 | 85 | 0 | 0 | 0 | 0 | 0 | 98.64 | 606.41 | 20 | 0 | 0 | 0 | 0 | 0 | 626.41
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5LILOPL | Luis LopezPlgr- Play Equipment (R125-118M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-D020 P-0245R |  | LUIZ LOPEZPLGR- PLAY EQUIPMENT SI | LUIZ LOPEZPLGR- PLAY EQUIPMENT | 2022 | 3360 | 3479.01 | 277 | 0 | 0 | 0 | 0 | 0 | 3756.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5MCARPK | Gen. MacArthur Park Baseball Field Renovation R067-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 502 | P-R245 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GEN. MACARTHUR PARK BASEBALL FIELD RENOVATION | 2022 | 2620 | 5741.04 | 243 | 0 | 0 | 83 | 0 | 0 | 6067.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5OBRZDR | Ocean Breeze Athletic Complex Exterior Doors Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-0506 |  | STATEN ISLAND | OCEAN BREEZE ATHLETIC COMPLEX EXTERIOR DOORS RECONSTRUCTION | 2022 | 600 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PKTR21 | FY21-Park Trees - Staten Island | LAND ACQUISITION AND TREE PLANTING | 500 | P-0822 |  | FY21-PARK TREES - STATEH ISLAND | FY21-PARK TREES - STATEH ISLAND | 2022 | 2000 | 95 | 2000 | 0 | 0 | 0 | 0 | 0 | 2095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PLG15B | R/C of parks & plgr in Staten Island RG-315MA1 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | WOLFE'S POND DOG RUN & BLOOMINGDALE BOCCE COURT-R/C | WOLFE'S POND DOG RUN & BLOOMINGDALE BOCCE COURT-R/C | 2022 | 3537 | 2801.09 | 0 | 0 | 0 | 682 | 0 | 0 | 3483.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PNYC08 | PlaNYC-Ocean Breeze Beach Parking Lot | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 | P-1018 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | PLANYC-OCEAN BREEZE BEACH PARKING LOT | PLANYC-OCEAN BREEZE BEACH PARKING LOT | 2022 | 310 | 0 | 0 | 0 | 0 | 0 | 0 | 319 | 319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PRALCS | Prall Playground-Reconstruction of Comfort Station | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-0505 |  |  | PRALL PLAYGROUND-RECONSTRUCTION OF COMFORT STATION | 2022 | 1790 | 265 | 14 | 1561 | 0 | 0 | 0 | 0 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5PRESPL | Prescott Playground RC R085-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-R245 P-D020 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | PRESCOTT PLGR-CREATION OF SENCORY PLGR, SI | PRESCOTT PLGR-CREATION OF SENCORY PLGR | 2022 | 5456 | 4476.47 | 141 | 0 | 0 | 100 | 0 | 0 | 4717.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5RECSI | Lyons Rec Ctr RC in Staten Island R043-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-0506 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RECON GREENBELT REC CTR IN STATEN ISLAND | RECON GREENBELT REC CTR IN STATEN ISLAND | 2022 | 965 | 202 | 0 | 2073 | 0 | 0 | 0 | 0 | 2275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SEGNRF | Seguine House Roof Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 P-1249 |  | STATEN ISLAND | SEGUINE HOUSE ROOF RECONSTRUCTION | 2022 | 187 | 0 | 0 | 187 | 0 | 0 | 0 | 0 | 187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SIPOOL | Staten Island Indoor Pool | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 500 | P-0632 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | STATEN ISLAND INDOOR POOL | 2022 | 50000 | 0 | 0 | 0 | 0 | 0 | 15000 | 35900 | 50900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SLVLK1 | Silver Lake Park | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | SILVER LAKE PARK, STATEN ISLAND | SILVER LAKE PARK | 2022 | 1000 | 30 | 0 | 0 | 0 | 0 | 1000 | 0 | 1030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SNUGLL | Snug Harbor Little League | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 |  |  | SNUG HARBOR LITTLE LEAGUE FIELD RECON | 2022 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SOBLPK | Sobel Park Path Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 |  | SOBEL PARK, STATEN ISLAND | SOBEL PARK PATH RECONSTRUCTION | 2022 | 200 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5SPT21B | Street Tree Planting - SI.-Sm. Pur. CB 1-3 RG-121M | LAND ACQUISITION AND TREE PLANTING | 500 | P-1018 |  | BOROUGH OF STATEN ISLAND | STREET TREES | 2022 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TPSBF | Tappen Park & South Beach Fountain Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 |  |  | TAPPEN PARK & SOUTH BEACH FOUNTAIN RECONSTRUCTION | 2022 | 166 | 25.99 | 140 | 0 | 0 | 0 | 0 | 0 | 165.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRE21A | FY21 Street Trees Staten Island, CB 1-3 RG- | LAND ACQUISITION AND TREE PLANTING | 500 | P-0822 HW-0001R P-1018 |  | FY21 STREET TREES STATEN ISLAND, CB 1-3 | FY21 STREET TREES STATEN ISLAND, CB 1-3 | 2022 | 400 | 130 | 920 | 0 | 0 | 0 | 0 | 0 | 1050 | 0 | 1580 | 0 | 0 | 0 | 0 | 0 | 1580
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5TRSD20 | Staten Island - Tree-Damaged Sidewalk Recon. RG-418MR | LAND ACQUISITION AND TREE PLANTING | 500 | P-1018 |  | STATEN ISLAND BOROUGH WIDE | TREE DAMAGED SIDEWALK RECONSTRUCTION IN STATEN ISLAND | 2022 | 2880 | 0 | 2880 | 0 | 0 | 0 | 0 | 0 | 2880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | P-5WHITEP | White Plgr-Hillside Slide Construction R012-119m | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-0245R |  | LYMAN AVE | WHITE PLGR-HILLSIDE SLIDE CONSTRUCTION | 2022 | 1236 | 176 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 742.87 | 257 | 0 | 0 | 0 | 0 | 0 | 999.87
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-HLG | SIBG -SI BOTANICAL GARDEN Healing Garden R116-506M | ESSENTIAL RECONSTRUCTION OF FACILITIES | 501 | PV-0510 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 1000 RICHMOND TERRACE, STATEN ISLAND | DEVELOPMENT OF NEW GARDEN AREA OVERLOOKING THE WETLAND AND NEAR THE NY CHINESE SCHOLAR'S GARDEN. | 2022 | 1217 | 1119.55 | 0 | 0 | 53 | 0 | 0 | 0 | 1172.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | PV510-IRR | SIBG -SI BOTANICAL GARDEN Site Irrigation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 501 | PV-0510 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 1000 RICHMOND TERRACE, STATEN ISLAND | PROVIDE THREE WELLS AND UNDERGROUND WATER DISTRIBUTION SYSTEM. | 2022 | 817 | 805.4 | 0 | 0 | 165 | 0 | 0 | 0 | 970.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDRP3 | Crescent Beach Park Acquisition | LAND ACQUISITION AND TREE PLANTING | 500 | PW-0319 |  |  | ACQUISITION OF 4 LOTS AND 5 UNBUILT RECORD STREETS AS OPEN SPACE TO BE INCORPORATED INTO CRESCENT BEACH PARK | 2022 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 2400
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-05 | SANDY - Blissenbach Marina Demo (Type 3) R160-113M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | STATEN ISLAND | SANDY- BLISSENBACH MARINA DEMO & R/C | 2022 | 0 | 254.07 | 102 | 0 | 0 | 0 | 0 | 0 | 356.07 | 131.91 | 0 | 0 | 0 | 0 | 0 | 449 | 580.91
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-13 | SANDY - SI Type 2 Plgrd R/C (RG-713M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | SI | PLAYGROUNDS | 2022 | 2082 | 346.31 | 166 | 0 | 0 | 0 | 0 | 0 | 512.31 | 1275.77 | 0 | 0 | 0 | 0 | 0 | 779 | 2054.77
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-16 | Conference House Pk landscape (Type 3 ) R006-114M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CONFERENCE HOUSE PARK, STATEN ISLAND | SANDY-R/C OF LANDSCAPE AT CONFERENCE HOUSE PARK | 2022 | 2245 | 369.54 | 7 | 0 | 0 | 0 | 0 | 0 | 376.54 | 254.7 | 0 | 0 | 0 | 0 | 0 | 53 | 307.7
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-17 | Tappen Park & Dolphin Fountains (Type3) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 501 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | TAPPEN PK , SI | SANDY- R/C OF FONTAIN AT TAPPEN PK TYPE3 | 2022 | 383 | 806.36 | 44 | 0 | 0 | 0 | 0 | 0 | 850.36 | 1514.41 | 397 | 0 | 0 | 0 | 0 | 0 | 1911.41
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-18 | SANDY-Midland Beach Protective Berm Emergency | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | FROM NEW DORP LANE TO OCEAN BREEZE PK, SI | EMERGENCY TEMP.PROTECTIVE BERM AT MIDLAND BCH | 2022 | 5492 | 548.09 | 2869 | 0 | 0 | 0 | 0 | 0 | 3417.09 | 4438.29 | 0 | 0 | 0 | 0 | 0 | 491 | 4929.29
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-20 | SANDY - Tree removals - Staten Island RG-614M | LAND ACQUISITION AND TREE PLANTING | 500 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF STATEN ISLAND | TREE REMOVALS IN STATEN ISLAND RELATED TO SANDY | 2022 | 815 | 173.36 | 0 | 11 | 0 | 0 | 0 | 0 | 184.36 | 641.64 | 0 | 0 | 0 | 0 | 0 | 91 | 732.64
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-24 | Sandy-Seaside Wildlife Nature Pk-reconstruction | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 500 | P-1018 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | SANDY-SEASIDE WILDLIFE NATURE PK- | SANDY-SEASIDE WILDLIFE NATURE PK-RECONSTRUCTION | 2022 | 1135 | 1007.61 | 174 | 0 | 0 | 0 | 0 | 0 | 1181.61 | 762.58 | 0 | 0 | 0 | 0 | 0 | 340 | 1102.58
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-26 | Sandy-R/C of playground at Wolfe's Pond Park | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 500 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | SANDY-R/C OF WOLFE'S POND PARK | SANDY-R/C OF WOLFE'S POND PARK | 2022 | 842 | 480.21 | 9 | 0 | 0 | 0 | 0 | 0 | 489.21 | 606.53 | 0 | 0 | 0 | 0 | 0 | 68 | 674.53
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-27 | Sandy-Wolfe's Pond Park-R/C of the berm | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 500 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | WOLFE'S POND PARK, SI | SANDY-R/C OF THE BERM AT WOLFE'S POND PARK | 2022 | 2964 | 757.39 | 19 | 0 | 0 | 0 | 0 | 0 | 776.39 | 1841.4 | 0 | 0 | 0 | 0 | 0 | 167 | 2008.4
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-28 | Sandy-FDR bdwk & Midland Plgr-R/C of tthe pavements,etc | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 500 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | SANDY-R/C OF TTHE PAVEMENTS,ETC AT FDR BDWK & MIDLAND PLGR | SANDY-R/C OF TTHE PAVEMENTS,ETC AT FDR BDWK & MIDLAND PLGR | 2022 | 651 | 38.36 | 0 | 0 | 0 | 0 | 0 | 28 | 66.36 | 333.74 | 0 | 0 | 0 | 0 | 0 | 246 | 579.74
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-30 | Sandy-New Dorp Bch Site Restor.R016-115M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 500 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SANDY-NEW DORP BCH | SANDY-NEW DORP BCH SITE RESTORATION | 2022 | 778 | 189.97 | 59 | 0 | 0 | 0 | 0 | 0 | 248.97 | 0 | 0 | 0 | 0 | 0 | 0 | 535 | 535
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-32 | Sandy-R/C of S. Bch-Playland Plgr, RG-212M WO 1 | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 500 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 300 FATHER CAPODANO BLVD | R/C OF PLAYGROUND | 2022 | 373 | 137.88 | 95 | 0 | 0 | 0 | 0 | 0 | 232.88 | 347.52 | 0 | 0 | 0 | 0 | 0 | 852 | 1199.52
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-37 | SANDY - BUONO BEACH FOUNTAIN REPAIR - R117-117MA | BEACHES AND BOARDWALKS | 500 | P-1018 |  |  | SANDY - BUONO BEACH FOUNTAIN REPAIR | 2022 | 381 | 40 | 51 | 0 | 0 | 0 | 0 | 0 | 91 | 0 | 432 | 0 | 0 | 0 | 0 | 0 | 432
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-42 | Sandy-Conference House Barrier Rail RG-212M WO6 | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 500 | P-1018 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | SANDY-CONFERENCE HOUSE BARRIER RAIL | SANDY-CONFERENCE HOUSE BARRIER RAIL | 2022 | 293 | 29.09 | 6 | 0 | 0 | 0 | 0 | 0 | 35.09 | 176.37 | 0 | 0 | 0 | 0 | 0 | 82 | 258.37
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-43 | Lemon Creek Marina R079-120M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 |  |  | LEMON CREEK MARINA | 2022 | 11807 | 305.76 | 0 | 0 | 1056 | 220 | 0 | 0 | 1581.76 | 951.83 | 0 | 0 | 9509 | 0 | 0 | 0 | 10460.83
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-44 | New Dorp Pk./Corp. Kivlehan Pk. | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 |  |  | NEW DORP PK./CORP. KIVLEHAN PK. | 2022 | 444 | 254.63 | 13 | 0 | 0 | 0 | 0 | 0 | 267.63 | 291.69 | 29 | 0 | 0 | 0 | 0 | 0 | 320.69
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-47 | Midland Beach Bath House | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 500 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MIDLAND BEACH BATH HOUSE | 2022 | 872 | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 785 | 785
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-48 | Five Parks in SI | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FIVE PARKS IN SI | 2022 | 704 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 633 | 633
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-49 | Fairview Park Comfort Station Construction | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 503 | P-1018 |  |  | FAIRVIEW PARK COMFORT STATION | 2022 | 0 | 200 | 9 | 0 | 0 | 0 | 0 | 0 | 209 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 70
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-50 | Fairview Park Landscape Construction R153-118M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 503 | P-1018 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS |  | FAIRVIEW PARK LANDSCAPE CONSTRUCTION | 2022 | 0 | 970.99 | 0 | 0 | 0 | 287 | 0 | 0 | 1257.99 | 4319.99 | 0 | 0 | 0 | 2590 | 0 | 0 | 6909.99
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-55 | Detective Russell Timoshenko Synthetic Turf Field | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 |  | STATEN ISLAND | DETECTIVE RUSSELL TIMOSHENKO SYNTHETIC TURF FIELD | 2022 | 673 | 0 | 0 | 0 | 0 | 67 | 0 | 0 | 67 | 0 | 0 | 0 | 0 | 606 | 0 | 0 | 606
20220309 | RICHMOND | 846 | DEPT OF PARKS AND RECREATION | SANDY5-56 | Alice Austen Park Revetment Reconstruction (Hurricane Sandy) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 500 | P-1018 |  | EDGEWATER STREET, HYLAN BOULEVARD, MARYLAND AVENUE | BUONO BEACH REVETMENT RECONSTRUCION | 2022 | 510 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 459 | 0 | 0 | 0 | 0 | 0 | 459
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301LL | 130 STUYVESANT PL - FACADE REPAIRS LOCAL LAW 11 | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 501 | CO-0301 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | 130 STUYVESANT PL - FAÓADE REPAIRS LOCAL LAW 11 | 2022 | 3601 | 831.98 | 7060 | 0 | 0 | 0 | 0 | 0 | 7891.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO301PD | 130 STUYVESANT PL.- PARKING GARAGE DECK | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 501 | CO-0301 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | WATERPROOFING | 2022 | 1401 | 882 | 5240 | 0 | 0 | 0 | 0 | 0 | 6122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | CO302ST | 18 RICHMOND TERRACE - EXTERIOR STEPS RECONSTRUCTION | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 501 | CO-0302 |  |  | DCAS - LANDMARK EXTERIOR STEPS | 2022 | 2421 | 1137.9 | 6427 | 0 | 0 | 0 | 0 | 0 | 7564.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER22 | Reconstruction of Existing Sewers, Staten Island | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 500 | EP-0007 SE-0002R |  |  | THIS IS A TWO YEAR CONTRACT. THE TARGETED CONTRACT START DATE IS 06/22/2022. | 2022 | 11495 | 110 | 6748 | 0 | 0 | 0 | 0 | 0 | 6858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SER23 | Reconstruction of Existing Sewers, Staten Island | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 500 | EP-0007 SE-0002R |  |  | RECONSTRUCTION OF EXISTING SEWERS, STATEN ISLAND. THIS IS A 1 YEAR CONTRACT. THE TARGETED START DATE FOR THIS CONTRACT IS AS SOON AS THE PREVIOUS CONTRACT, EC-SER22, EXPIRES. | 2022 | 5501 | 0 | 0 | 5501 | 0 | 0 | 0 | 0 | 5501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HAM18MHCC | Mariner's Harbor Community Center | LOW TO MODERATE INCOME PUBLIC HOUSING CONSTRUCTION | 500 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FUNDING TO EXPAND THE COMMUNITY CENTER AT MARINER'S HARBOR | 2022 | 5700 | 1359.91 | 58 | 4782 | 0 | 0 | 0 | 0 | 6199.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82SIABE | REHAB OF THE STATEN ISLAND ANIMAL SHELTER | ANIMAL CARE |  | HL-R001 HL-0082 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | REHAB OF THE STATEN ISLAND ANIMAL SHELTER | 2022 | 2913 | 14182.74 | 593 | 0 | 0 | 0 | 0 | 0 | 14775.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWP2021RC | Non-Standard Installs - Staten Island | PEDESTRIAN RAMP CONSTRUCTION | 500 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NON-STANDARD INSTALLS - STATEN ISLAND | NON-STANDARD INSTALLS - STATEN ISLAND | 2022 | 0 | 0 | 0 | 540 | 0 | 6590 | 0 | 0 | 7130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19R | Pedestrian Ramp Rehabilitation - Staten Island | PEDESTRIAN RAMP CONSTRUCTION | 500 | HW-0200 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | PEDESTRIAN RAMP REHABILITATION - STATEN ISLAND | 2022 | 16182 | 15635.75 | 1746 | 0 | 0 | 0 | 0 | 0 | 17381.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00505 | VICTORY BLVD AND MANOR ROAD INTERSECTION IMPROVEMENT | PRIMARY STREET RECONSTRUCTION | 500 501 | HW-0061 HW-D104 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | VICTORY BLVD AND MANOR ROAD | PROJECT WILL IMPROVE THE INTERSECTION OF VICTORY BLVD AND MANOR ROAD | 2022 | 3882 | 12505.39 | 0 | 0 | 0 | 7560 | 0 | 0 | 20065.39 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 15
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00508 | AMBOY ROAD IMPROVEMENTS AT ELTINGVILLE CORRIDOR | PRIMARY STREET RECONSTRUCTION | 500 503 | HW-R005 HW-0061 HW-0001R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | AMBOY ROAD IMPROVEMENTS | AMBOY ROAD IMPROVEMENTS | 2022 | 3500 | 2156.81 | 5536 | 15284 | 0 | 0 | 0 | 0 | 22976.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00510 | Woodrow Rd Improvements btw Gladwin Ave & Veterans Rd East | PRIMARY STREET RECONSTRUCTION | 500 503 | HW-R005 HW-0001R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | TO CONDUCT VARIOUS ROAD IMPROVEMENTS AT WOODROW ROAD BETWEEN BLOOMINGDALE ROAD AND VETERANS ROAD EAST | TO CONDUCT VARIOUS ROAD IMPROVEMENTS AT WOODROW ROAD BETWEEN BLOOMINGDALE ROAD AND VETERANS ROAD EAST | 2022 | 1500 | 1434.33 | 850 | 0 | 0 | 0 | 1065 | 0 | 3349.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00511 | Travis Avenue Widening | PRIMARY STREET RECONSTRUCTION | 500 502 | HW-R005 HW-0001R HW-D104 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | TO WIDEN TRAVIS AVE BTWN RICHMOND AVE & PARK DRIVE NORTH | TO WIDEN TRAVIS AVE BTWN RICHMOND AVE & PARK DRIVE NORTH | 2022 | 1700 | 2025.35 | 813 | 3765 | 8786 | 0 | 0 | 0 | 15389.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR00512 | Richmond Valley Road | PRIMARY STREET RECONSTRUCTION | 500 | HW-R005 HW-R988 HW-0061 HW-0001R HW-D104 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RICHMOND VALLEY ROAD | RICHMOND VALLEY ROAD | 2022 | 3971 | 1729.78 | 1968 | 2053 | 2814 | 0 | 0 | 0 | 8564.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B | TODT HILL ROAD CURVE REHAB, | PRIMARY STREET RECONSTRUCTION | 502 | HW-R005 HW-0001R | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  |  | 2022 | 3324 | 1392.28 | 500 | 0 | 0 | 0 | 13538 | 0 | 15430.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR005B1 | TODT HILL ROAD - CIRCLE RD | PRIMARY STREET RECONSTRUCTION | 500 | WM-0001 HW-0061 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | TODT HILL ROAD - CIRCLE RD | TODT HILL ROAD - CIRCLE RD | 2022 | 3150 | 889.25 | 0 | 0 | 3597 | 0 | 0 | 0 | 4486.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1132B | SOUTH BEACH AREA PHASE II (SE-793) | PRIMARY STREET RECONSTRUCTION | 502 | HW-0061 HW-1132 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  |  | 2022 | 19512 | 30754.8 | 6332 | 4607 | 0 | 0 | 0 | 0 | 41693.8 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 21
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1140A | ARTHUR KILL ROAD (PHASE I) - CLARKE AVE, RICHMOD AV, RED-366 | PRIMARY STREET RECONSTRUCTION | 503 | HW-0061 HW-1140 HW-D104 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RECONSTRUCTION OF EXISTING ROADWAYROADWAY RECONSTRUCTION SHALL INCLUDE NEW CURBS, SIDEWALKS AND REQUIREDREPLACEMENTAMENITIES WILL NOT BE INCLUDEDCITY FUNDEDIN CONJUNCTION WITH DEP | 2022 | 55985 | 5668.91 | 0 | 0 | 3640 | 15636 | 0 | 0 | 24944.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR1160 | RE- ALIGN ROCKLAND AVE AT MANOR RD/MEISNER AVE | PRIMARY STREET RECONSTRUCTION | 502 | HW-0001R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  |  | 2022 | 7020 | 178.45 | 0 | 0 | 0 | 0 | 0 | 21867 | 22045.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR300-03 | ROAD WIDENING AT SOUTH AVENUE AND FOREST AVENUE | PRIMARY STREET RECONSTRUCTION | 501 | HW-R061 HW-D104 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ROAD WIDENING AT SOUTH AVENUE AND FOREST AVENUE | 2022 | 500 | 6353.22 | 774 | 0 | 0 | 0 | 0 | 1400 | 8527.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR669C | RECONSTRUCTION OF ROMA, HETT, ETC, SAND669C | PRIMARY STREET RECONSTRUCTION | 502 | HW-0669 SE-0200R HW-0061 WM-0001 HW-0001R | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  |  | 2022 | 11863 | 78048.79 | -2436 | 6522 | 0 | 0 | 0 | 0 | 82134.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR700 | St George-Richmond Terrace Intersection Improvements | PRIMARY STREET RECONSTRUCTION | 500 | HW-0001R | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | ST GEORGE-RICHMOND TERRANCE INTERSECTION IMPROVEMENTS | ST GEORGE-RICHMOND TERRANCE INTERSECTION IMPROVEMENTS | 2022 | 11300 | 0 | 1623 | 637 | 0 | 20020 | 0 | 0 | 22280 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 750
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWR919 | BLOOMINGDALE ROAD: AMBOY ROAD TO ARTHUR KILL ROAD | PRIMARY STREET RECONSTRUCTION | 503 | HW-D104 HW-0919 TF-0502 TF-0002 HW-0200 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCT AND WIDEN BLOOMINGDALE ROAD FROM AMBOY ROAD TO ARTHUR KILL ROAD | RECONSTRUCTION OF BLOOMINGDALE ROADRECONSTRUCTION OF THE EXISTING ROADWAYROADWAY RECONSTRUCTION SHALL INCLUDE NEW CURBS SIDEWALKS AND REQUIREDREPLACEMENTAMENITIES TO BE DETERMINEDALL CITY FUNDEDIN CONJUNCTION WITH SEWERS | 2022 | 10461 | 2175.57 | 0 | 0 | 0 | 250 | 0 | 42364 | 44789.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWRF05R | Dubois Yard Roof | FACILITY RECONSTRUCTION | 500 | HW-0003 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | DUBOIS YARD ROOF | DUBOIS YARD ROOF | 2022 | 700 | 1565.39 | 1072 | 8907 | 0 | 0 | 0 | 0 | 11544.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020R | Prior Notice Sidewalks- Staten Island | SIDEWALK RECONSTRUCTION | 500 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PRIOR NOTICE SIDEWALKS- STATEN ISLAND | PRIOR NOTICE SIDEWALKS- STATEN ISLAND | 2022 | 3000 | 1976.03 | 1498 | 0 | 0 | 0 | 0 | 0 | 3474.03 | 866 | 0 | 0 | 0 | 0 | 0 | 0 | 866
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2020X | Prior Notice Sidewalks- Bronx | SIDEWALK RECONSTRUCTION | 500 | HW-0200 P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PRIOR NOTICE SIDEWALKS- BRONX | PRIOR NOTICE SIDEWALKS- BRONX | 2022 | 5000 | 2903.77 | 1451 | 0 | 0 | 0 | 0 | 185 | 4539.77 | 866 | 0 | 0 | 0 | 0 | 0 | 0 | 866
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021R | PRIOR NOTICE SIDEWALK - STATEN ISLAND | SIDEWALK RECONSTRUCTION | 500 | HW-0200 P-1331 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PRIOR NOTICE SIDEWALKS - STATEN ISLAND | PRIOR NOTICE SIDEWALKS - STATEN ISLAND | 2022 | 2239 | 0 | 1282 | 0 | 0 | 0 | 0 | 0 | 1282 | 0 | 957 | 0 | 0 | 0 | 0 | 0 | 957
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | HWTRR1 | Trench Restoration - Staten Island (SER002333) | PRIMARY STREET RECONSTRUCTION | 500 | HW-0061 HW-0001R |  |  | TRENCH RESTORARTION - STATEN ISLAND | 2022 | 7011 | 2041.61 | 477 | 6232 | 0 | 0 | 0 | 0 | 8750.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCAL15TV | Tottenville: New Roof | ESSENTIAL RECONSTRUCTION OF FACILITIES | 500 | LN-D008 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TOTTEENVILLE: NEW ROOF | 2022 | 715 | 681.04 | 0 | 0 | 169 | 0 | 0 | 0 | 850.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13STG | ST GEORGE: Exterior and Interior renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 500 501 | LN-0008 LN-D008 LN-R001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | EXTERIOR AND INTERIOR RENOVATION | 2022 | 3510 | 6121.39 | 790 | 0 | 0 | 0 | 0 | 0 | 6911.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEAL15RT | Richmond town: New Roof | ESSENTIAL RECONSTRUCTION OF FACILITIES | 500 | LN-0008 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | RICHMONDTOWN: NEW ROOF | 2022 | 980 | 1604.8 | 0 | 0 | 0 | 0 | 162 | 0 | 1766.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | LNRA17NDP | NEW DORP - HVAC System Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 502 | LN-R001 LN-D008 LN-0008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NYPL - NEW DORP BRANCH: NEW HVAC SYSTEM FOR NEW DORP BRANCH LIBRARY;309 NEW DORP LANE, STATEN ISLAND, NY 10306 | 2022 | 700 | 0 | 534 | 3675 | 0 | 0 | 0 | 0 | 4209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC002 | Last Chance Pond BMP NC 11/12, storm & sanitary sewer constr | BLUEBELT PROGRAM | 500 | WM-0001 SE-0005 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | LAST CHANCE POND BMP NC 11/12, STORM & SANITARY SEWER CONSTRUCTION AND WATER MAIN REPLACEMENT IN HUSSON STREET BETWEEN STOBE AVENUE AND HUNTER AVE, ETC, BOUROUGH OF STATEN ISLAND | 2022 | 47890 | 39695.72 | 4541 | 0 | 0 | 0 | 741 | 0 | 44977.72 | 9524.88 | 0 | 0 | 0 | 0 | 4500 | 0 | 14024.88
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC003 | Strm & Sani Swr const & WM replac in Mason Ave, SI | BLUEBELT PROGRAM | 502 | SE-0002R SE-0005 WM-0001 SE-0200R HW-0200 |  |  | STORM & SANITARY SWEER CONSTRUCTION & WM REPLACEMENT IN MASON AVE B/TSLATER BLVD & ADAMS AVE, SI, BMP, NC, 16 | 2022 | 29452 | 39475.39 | 5541 | 459 | 0 | 0 | 3412 | 0 | 48887.39 | 6171.9 | 5788 | 0 | 0 | 0 | 0 | 0 | 11959.9
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC005 | Storm Sewer Tributary for BMPs NC-13 and NC-14 | BLUEBELT PROGRAM | 502 | TF-0002 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | BMP 13, 14 AND 15 STORM AND SANITARY SEWER CONSTRUCTION AND WATER MAIN REPLACEMENT IN HYLAN BLVD B/W SLATER BLVD AND HAMDEN AVE, ETC. STATEN ISLAND | 2022 | 53068 | 0 | 0 | 93 | 0 | 0 | 0 | 0 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04A | BMP NC 6 and 15 storm & sanitary sewer installation | BLUEBELT PROGRAM | 502 | SE-0200R SE-0005 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | MIBBNC04A-BMP NC 6, STORM & SANITARY SEWER INSTALLATION & WATER MAINREPLCMNT IN LINCOLN AVE BET. HYLAN BLVD. & MASON AVE, ETC. STATEN ISLAND | 2022 | 34680 | 1740 | 0 | 20611 | 0 | 0 | 0 | 0 | 22351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC04B | Storm and sanitary sewer installation | BLUEBELT PROGRAM | 502 | SE-0200R SE-0002R WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | MIBBNC04B-BMP NC 6, STORM AND SANITARY SEWER INSTALLATION AND WATER MAIN REPLACEMENT IN LINCOLN AVE BETWEEN S. RAILROAD AVE AND HYLAND BLVD, ETC. BOROUGH STATEN ISLAND | 2022 | 30221 | 0 | 0 | 0 | 0 | 0 | 43248 | 0 | 43248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | MIBBNC05 | Construction of BMPs NC-13 and NC-14 (SANDR01) | BLUEBELT PROGRAM | 502 | SE-0200R WM-0006 SE-0005 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | IN HYLAN BLVD. BET STOBE AVE. & SEAVER AVE. | 2022 | 19512 | 21787.59 | 2722 | 0 | 0 | 0 | 3319 | 0 | 27828.59 | 7489.16 | 0 | 0 | 0 | 0 | 0 | 0 | 7489.16
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-CRLYN | Mary Cali Dalton Recreation Center DB | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 500 | ED-0384 |  | BOROUGH OF STATEN ISLAND | RC CROMWELL REC @ LYONS POOL SITE | 2022 | 46000 | 1902.54 | 14462 | 75985 | 0 | 0 | 0 | 0 | 92349.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | P-5PNYC06 | PlaNYC-Ocean Breeze Athletic Fac-Building Fit-Out R149-108M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 500 502 | ED-D075 P-0504 P-R245 P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | OCEAN BREEZE PARK IN STATEN ISLAND | CONSTRUCTION OF THE ATHLETIC FACILITY FIT-OUT | 2022 | 92343 | 106523.68 | 1183 | 0 | 0 | 0 | 0 | 0 | 107706.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175CLOV | SIZ - Staten Island Zoo Clove Road Restoration | ESSENTIAL RECONSTRUCTION OF FACILITIES | 501 | PV-R175 PV-D175 PV-0175 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STATEN ISLAND ZOO: RESTORATION OF CLOVE ROAD ENTRANCE AND PATHWAYS; 614 BROADWAY, STATEN ISLAND, 10310 | 2022 | 5332 | 0 | 3118 | 619 | 5121 | 0 | 0 | 0 | 8858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV175ROOF | SIZ - Roof Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 501 | PV-R175 PV-0175 PV-D175 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | THE STATEN ISLAND ZOO IS REQUESTING CAPITAL FUNDS TO REPLACE THE ROOFOF THE ZOO'S MAIN BUILDING (EXCLUDING THE REPTILE WING). THE PROJECT WOULD ALSO INCLUDE THE REPLACMENT OF THE ROOF OVER THE AFRICAN SAVANNAH AND TROPICAL FOREST WINGS. THE ROOF OF THE MAIN BUILDING IS OVER FORTY YEARS OLD AND IS SUBSTANTIALLY DETERIORATED. THE ROOF OF THE AFRICAN SAVANNAH AND TROPICAL FOREST WINGS IS ARE OVER TWENTY FIVE YEAR OLD AND ARE ALSO IN DETERIORATED CONDITION. | 2022 | 3450 | 2828.36 | 58 | 681 | 1212 | 0 | 0 | 0 | 4779.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV302BPH1 | SIIAS - Building B at SHCC Phase1 Geo-Thermal & Ground Floor | ESSENTIAL RECONSTRUCTION OF FACILITIES | 501 | PV-R302 PV-0302 PV-D302 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | SCOPE OF WORK IS THE INSTALLATION OF A GEO-THERMAL WELL FIELD WHICH WILL HEAT AND COOL BUILDING "B" AT SHCC. SCOPE OF WORK ALSO INCLUDES THE CONSTRUCTION OF NEW CLASSROOMS AND AN EXHIBITION PREPARATION ROOM/SHOP. | 2022 | 5993 | 1867.3 | 2029 | 0 | 8280 | 0 | 0 | 0 | 12176.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV341BRIT | SIHS - Britton Cottage Restoration | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-R341 PV-0341 PV-D341 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | BRITTON COTTAGE RESTORATION | 2022 | 750 | 333 | 200 | 0 | 0 | 898 | 0 | 0 | 1431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV477TEMP | SICM -Staten Island Children's Museum Temp Control System | ESSENTIAL RECONSTRUCTION OF FACILITIES | 501 | PV-0477 PV-R477 PV-D477 |  |  | STATEN ISLAND CHILDREN'S MUSEUM: UPGRADE OF TEMPERATURE CONTROL SYSTEM; 1000 RICHMOND TERRACE, STATEN ISLAND 10301 | 2022 | 4406 | 727.89 | 594 | 0 | 3798 | 1500 | 0 | 0 | 6619.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-C | SHCC - SHCC Main Hall Bldg C Roof Reconstruction | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-R490 PV-0490 PV-D490 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SHCC BUILDING C ROOF RECONSTRUCTION | 2022 | 600 | 703.09 | 2296 | 0 | 0 | 0 | 0 | 0 | 2999.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490ELEC | SHCC - Snug Harbor Cult. Ctr. Site - Wide Electrical Upgrade | ESSENTIAL RECONSTRUCTION OF FACILITIES | 501 | PV-D490 PV-0467 PV-0490 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 1000 RICHMOND TERRACE, STATEN ISLAND | PHASE 1 WILL INCLIUDE THE INSTALLATION OF NEW ELECTRICAL SERVICE ROOMWHICH WILL BE CODE COMPLIANT AND SIZED FOR THE NEW SERVICE EQUIPMENT IN BUILDING "G". THIS PHASE WILL PROVIDE TEMPORARY SERVICE FROM EXISTING MANHOLE. PHASE 2 WILL INCLUDE THE INSTALLATION OF TWO SUBSTATIONS IN BUILDING "L" . | 2022 | 5175 | 3803.86 | 3 | 0 | 5411 | 0 | 0 | 0 | 9217.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-INF | SHCC - Site-wide Infrastructure Upgrade | ESSENTIAL RECONSTRUCTION OF FACILITIES | 501 | PV-0490 PV-D490 PV-R490 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SITE-WIDE HVAC UPGRADE FOR SNUG HARBOR CAMPUS, INCLUDING COMPLETE REPLACEMENT OF EQUIPMENT AT THE CENTRAL BOILER AND COOLING PLANT (BUILDING L) AND THE UPGRADE AND CONNECTION OF SYSTEMS AT THE 12 BUILDINGS SERVED BY THE CENTRAL PLANT. | 2022 | 11000 | 6157.26 | 8502 | 0 | 0 | 0 | 0 | 0 | 14659.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PV490-Q3 | SHCC - Snug Harbor Cult. Ctr. Music Hall, Dressing Rooms | ESSENTIAL RECONSTRUCTION OF FACILITIES | 501 | PV-0490 PV-R490 PV-D490 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | 1000 RICHMOND TERRACE, STATEN ISLAND NY 10301 | PROJECT SCOPE OF WORK IS TO SECURE FOR SHCC A FDNY CODE COMPLIANT FIRE ALARM FOR THE MUSIC HALL BUILDING "T" | 2022 | 3634 | 20108 | 2072 | 0 | 1 | 0 | 0 | 0 | 22181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PW29310R | 10 RICHMOND TERRACE - FIRE ALARM | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 501 | PW-0293 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 10 RICHMOND TERRACE - FIRE ALARM | 2022 | 11216 | 0 | 931 | 0 | 0 | 10120 | 0 | 0 | 11051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PW348-74 | FUEL TANK REPLACEMENT | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS |  | PW-0348 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FUEL TANKS | 2022 | 12500 | 30432.58 | 0 | 661 | 0 | 0 | 0 | 0 | 31093.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | PWD5SOUTH | SOUTH SHORE LITTLE LEAGUE | MISCELLANEOUS CONSTRUCTION | 503 | P-D020 PW-D077 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | 500K FOR REHAB EXISTING FIELD AND INSTALL STADIUM SEATING, LIGHTS ANDSCOREBOARD. $150K FOR CONSRUCTION OF PRACTICE FACILITY. | 2022 | 1150 | 10111.8 | 49 | 0 | 0 | 0 | 1 | 0 | 10161.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-366 | WM WORK ARTHUR KILL RD BTW RICHMOND & ABINGTON AVE HWR1140A | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 503 | SE-0200R SE-0002R WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | WATER MAIN WORK IN ARTHUR KILL RD BETWEEN RICHMOND AVE & ABINGDON AVE | 2022 | 589 | 187.36 | 1738 | 0 | 0 | 14555 | 0 | 0 | 16480.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-372 | WM, PART OF RECON TRAVIS AVE FORM PARK DR N TO DRAPER PL | AUGMENTATION OF WATER SUPPLY SYSTEMS | 501 | WM-0001 SE-0002R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | WM, PART OF RECON TRAVIS AVE FORM PARK DR N TO DRAPER PL | 2022 | 901 | 150 | 0 | 3695 | 0 | 0 | 0 | 0 | 3845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-381 | (SANDHWSI) Storm swr replacement ext. in Harold Avenue | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 503 | SE-0200R |  |  | (SANDHWS) STORM SEWER EXTENSIONS IN HAROLD AVE FROM BAYVIEW TERRACE TO OCEAN DRIVEWAY AND IN OCEAN DRIVEWAY FROM HAROLD AVE TO ARDEN AVE; WATER MAIN REPLACEMENTS IN HAROLD AVE FROM HYLAN BLVD TO OCEAN DRIVEWAY. | 2022 | 2880 | 1987.69 | 1000 | 1114 | 0 | 0 | 0 | 0 | 4101.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | RED-386 | Water Main replacement, South & Arlington Aves, SI | AUGMENTATION OF WATER SUPPLY SYSTEMS | 501 | WM-0001 EP-0007 WM-0944 |  |  | INSTALLATION OF DISTRIBUTION WATER MAINS, SOUTH AVE B/T RICHMOND TERRACE, NETHERLAND AVE & ARLINGTON PLACE, STATEN ISLAND | 2022 | 7197 | 850 | 10128 | 0 | 0 | 0 | 0 | 0 | 10978 | 0 | 687 | 0 | 0 | 0 | 0 | 0 | 687
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-367 | Staten Island 1 and 3 Garage Construction + SOLARGR10 | GARAGES AND FACILITIES | 501 503 | S-0136 PU-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CONSTRUCTION OF NEW GARAGE | 2022 | 143872 | 172603.87 | 10737 | 189 | 0 | 0 | 0 | 0 | 183529.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | S136-383S | STATEN ISLAND 3 GARAGE HVAC | GARAGES AND FACILITIES | 503 | S-0136 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HVAC REPLACEMENT | 2022 | 477 | 23313.66 | 2139 | 0 | 0 | 0 | 0 | 0 | 25452.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SAND669C | Reconstruction of Roma,Hett,Etc - Hurricane Sandy | PRIMARY STREET RECONSTRUCTION | 500 | HW-0001R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF ROMA,HETT,ETC - HURRICANE SANDY | RECONSTRUCTION OF ROMA,HETT,ETC - HURRICANE SANDY | 2022 | 3748 | 170.81 | 533 | 0 | 0 | 0 | 0 | 0 | 703.81 | 1537.29 | 5858 | 0 | 0 | 0 | 0 | 0 | 7395.29
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW14 | Reconstruction of South Beach - Hurricane Sandy - RED-375 | PRIMARY STREET RECONSTRUCTION | 500 | TF-0002 HW-0001R TF-0502 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF SOUTH BEACH - HURRICANE SANDY | RECONSTRUCTION OF SOUTH BEACH - HURRICANE SANDY | 2022 | 21204 | 7430.88 | 232 | 0 | 0 | 40 | 0 | 0 | 7702.88 | 12909.03 | 0 | 0 | 0 | 1710 | 0 | 0 | 14619.03
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHW15 | Reconstruction of Midland Beach - Hurricane Sandy | PRIMARY STREET RECONSTRUCTION | 500 | HW-0001R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF MIDLAND BEACH - HURRICANE SANDY | RECONSTRUCTION OF MIDLAND BEACH - HURRICANE SANDY | 2022 | 12825 | 4161.28 | 327 | 0 | 0 | 0 | 0 | 0 | 4488.28 | 6556.12 | 0 | 3599 | 0 | 0 | 0 | 0 | 10155.12
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDHWSI | Non When & Where - Staten Island - Hurricane Sandy | PRIMARY STREET RECONSTRUCTION | 500 | HW-0001R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | NON WHEN AND WHERE - STATEN ISLAND HURRICANE SANDY | NON WHEN AND WHERE - STATEN ISLAND HURRICANE SANDY | 2022 | 7589 | 1839.55 | 0 | 0 | 3193 | 0 | 0 | 0 | 5032.55 | 2829.45 | 0 | 0 | 0 | 0 | 0 | 0 | 2829.45
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDR01 | Hylan Blvd Streetscape Improvements (MIBBNC05) | PRIMARY STREET RECONSTRUCTION | 500 | HW-0001R | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HYLAN BLVD STREETSCAPE IMPROVEMENTS | HYLAN BLVD STREETSCAPE IMPROVEMENTS | 2022 | 1800 | 1963.81 | 570 | 0 | 0 | 0 | 0 | 0 | 2533.81 | 3663.31 | 507 | 0 | 516 | 0 | 0 | 0 | 4686.31
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-740B | SANITARY SEWERS IN ROCKLAND AVENUE | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 502 | SE-0740 WM-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SANITARY SEWERS IN ROCKLAND AVENUE | SANITARY SEWERS IN ROCKLAND AVENUE | 2022 | 10232 | 769.56 | 0 | 0 | 0 | 0 | 0 | 13691 | 14460.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-751 | CHESTER AV - IRVINGTON ST AND ARBUTUS AVE | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 503 | WM-0001 SE-0002R SE-0200R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CHESTER AV - IRVINGTON ST AND ARBUTUS AVE | CHESTER AV - IRVINGTON ST AND ARBUTUS AVE | 2022 | 15870 | 4225.15 | 0 | 0 | 0 | 0 | 0 | 18163 | 22388.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SE-812 | Sanitary & Storm swr in Page Av b/t Amboy Rd & Estella Pl | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 503 | HW-D104 HW-R005 SE-0200R HW-0061 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SANITARY & STORM SWR IN PAGE AV B/T AMBOY RD & ESTELLA PL | 2022 | 15518 | 62397.55 | 1941 | 0 | 0 | 0 | 0 | 0 | 64338.55 | 31.8 | 0 | 0 | 0 | 0 | 0 | 0 | 31.8
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002237 | Sanitary and Storm Sewer in Manee Avenue | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 503 | SE-0002R SE-0200R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SANITARY AND STORM SEWER IN MANEE AVENUE BETWEEN AMBOY ROAD AND DEAD END, ETC | 2022 | 4113 | 0 | 0 | 0 | 0 | 0 | 0 | 4113 | 4113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002311 | SAN & STRM SWR IN BERTRAM AV B/T ZEPHYR AV & HYLAN BLVD. ETC | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 503 | SE-0200R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SAN & STRM SWR IN BERTRAM AV B/T ZEPHYR AV & HYLAN BLVD. ETC | 2022 | 6526 | 25536.45 | 135 | 0 | 0 | 0 | 0 | 0 | 25671.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002317 | SAN & STRM SEWER IN HALPIN AVE | BLUEBELT PROGRAM | 503 | SE-0002R SE-0200R WM-0001 SE-0005 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SAN & STRM SEWER IN HALPIN AVE | 2022 | 11969 | 3104.26 | 0 | 0 | 15370 | 0 | 0 | 0 | 18474.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002324 | New sanitary sewers in Camden ave. Staten Island | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 503 | SE-0002R WM-0001 SE-0200R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW SANITARY SEWERS IN CAMDEN AVE. STATEN ISLAND | 2022 | 2358 | 1384 | 0 | 5438 | 0 | 0 | 0 | 0 | 6822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002329 | SAN, STM & WM IN LANDMARK COLONY | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 500 | SE-0002R SE-0200R WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STORM, SAN & WM IN LANDMARK COLONY | 2022 | 10046 | 700 | 0 | 13464 | 0 | 0 | 0 | 0 | 14164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002333 | SE & WM Van Buren St btwn York Ave & FranklIn Ave SI, HWTRR1 | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 501 502 | SE-0002R SE-0200R WM-0001 WM-0006 |  |  | NEW SANITARY SEWER & WATER MAIN WORK IN VAN BUREN STREET BETWEEN TORKAVENUE & FRANKLIN AVENUE IN STATEN ISLANDS. THIS PROJECT IS IN CONJUNCTION WITH DOT PROJECT HWTRR1. | 2022 | 8216 | 0 | 0 | 7036 | 0 | 0 | 0 | 0 | 7036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER002334 | NDF - Rplcmt 6" sanitary sewers & distribution wtr mains SI | AUGMENTATION OF WATER SUPPLY SYSTEMS | 501 | SE-0002R SE-0200R WM-0001 |  |  | REPLACEMENT OF 6" SANITARY SEWERS AND DISTRIBUTION WATER MAINS IN LONGVIEW ROAD BETWEEN HOLSMAN ROAD AND RICHMOND ROAD IN STATEN ISLAND | 2022 | 41366 | 35 | 0 | 0 | 0 | 37343 | 0 | 0 | 37378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200202 | New Stm. Swr. Ext. in Eagan Ave. S.I. | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 503 | SE-0200R | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW STM. SWR. EXT. IN EAGAN AVE. AND WATER MAIN REPAIR IN KEEGANS LANE. | 2022 | 4266 | 32975.21 | 51 | 397 | 0 | 0 | 0 | 0 | 33423.21 | 1075.4 | 0 | 0 | 0 | 0 | 0 | 0 | 1075.4
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200226 | STORM AND SANITARY SEWERS & WM WORK IN TRAVIS AREA | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 500 502 | HW-0200 WM-0001 SE-0200R | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STORM, SANITARY AND WATER MAIN WORK IN TRAVIS AREA. | 2022 | 13223 | 38466.63 | 1499 | 985 | 0 | 0 | 0 | 0 | 40950.63 | 375.69 | 0 | 0 | 0 | 0 | 0 | 0 | 375.69
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200232 | STORM,SANIT SEWERS & WATER MAIN IN XENIA ST | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 501 | HW-0200 SE-0200R SE-0002R WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STORM SANITARY SEWERS AND WATER MAIN IN XENIA STREET BETWEEN HURLBERTSTREET AND MASON AVENUE | 2022 | 1419 | 5330.12 | 492 | 1537 | 0 | 0 | 0 | 0 | 7359.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200236 | STRM SWR EXT & WM WORK IN NORTH AV, ETC. | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 501 | EP-0007 HW-0200 SE-1000 SE-0200R SE-0002R TF-0002 WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STRM SWR EXT & WM WORK IN NORTH AV, B/T NEAL DOW AV & LIVERMORE AV, STRM SWR EXT IN FOREST AV, B/T LIVERMORE AV & MARIANNE ST | 2022 | 1998 | 1325 | 6879 | 0 | 0 | 0 | 2085 | 0 | 10289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200245 | NEW STRM SWR & WM REPLACEMT IN ACACIA AV, ETC. | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 503 | SE-0005 SE-0200R SE-0002R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW STORM SEWER AND WATER MAIN REPLACEMENT IN ACACIA AVENUE BETWEEN DEAD END AND AMBOY ROAD ETC. | 2022 | 21157 | 37628.74 | 976 | 0 | 233 | 0 | 0 | 0 | 38837.74 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200247 | New Storm Sewers in King St | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 503 | SE-0200R SE-0002R WM-0001 WM-0006 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW STORM SEWERS IN KING ST BETWEEN PRESTON AVE AND RIDGECREST AVE ETC | 2022 | 3406 | 618.76 | 0 | 0 | 46790 | 0 | 0 | 0 | 47408.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200251 | EXT OF STRM SWR AND WM WORK IN 3RD ST | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 502 | SE-0200R WM-0001 SE-0002R SE-1000 EP-0007 HW-0200 TF-0002 |  |  | EXT OF STRM SWR AND WM WORK IN 3RD ST, B/T NEW DORP LA AND STEELE AV | 2022 | 5354 | 1514.8 | 0 | 15251 | 0 | 0 | 0 | 0 | 16765.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200258 | Sanitary and Storm Sewer in West Castor Place between Alvers | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 503 | SE-0200R SE-0002R WM-0001 HW-0200 EP-0007 SE-0005 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SANITARY AND STORM SEWER BETWEEN WEST CASTOR PLACE AND BETWEEN ALVERSON AVENUE AND POWELL STREET, ETC | 2022 | 6587 | 2326.24 | 19808 | 0 | 0 | 0 | 0 | 0 | 22134.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200261 | Storm sewer in Roma Ave bet Tysens Lane & Ebbits Street | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 502 | SE-0200R WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STORM SEWER IN ROMA AVE BET TYSENS LANE & EBBITS STREET | 2022 | 1976 | 500 | 0 | 2312 | 0 | 0 | 0 | 0 | 2812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200285 | NEW STM. SWR EXT. & WM REPL IN TODT HILL RD., SI | BLUEBELT PROGRAM | 502 | SE-0200R WM-0001 SE-0005 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW STM. SWR EXT. & WM REPL ACEMENT IN TODT HILL RD BETWEEN WILLOW POND RD & FOUR CORNERS RD. ETC. | 2022 | 7249 | 1048.03 | 1 | 0 | 49130 | 0 | 0 | 0 | 50179.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200290 | New Storm Sewer Ext & Water Main Replacement in Forest Ave | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 501 | SE-0200R WM-0001 SE-0002R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW STROM SEWER EXT & WATER MAIN REPLACEMENT IN FOREST AVE BETWEEN BROADWAY AND RAYMOND PLACE ETC | 2022 | 3675 | 650 | 0 | 0 | 0 | 0 | 0 | 4300 | 4950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200292 | SAN & STRM SWR REPLACMT & WM WORK IN FLOYD ST | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 501 | SE-0002R SE-0200R WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SAN & STRM SWR REPLACMT & WM WORK IN FLOYD ST | 2022 | 18099 | 515.26 | 0 | 0 | 0 | 0 | 0 | 14738 | 15253.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200309 | Strm swr R+Ext & WM Work, Maguire Avenue | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 503 | SE-0200R WM-0001 SE-0002R | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | REPLACEMENT AND EXTENSION OF STORM SEWER IN MAGURIE AVENUE BETWEEN DEPEW PLACE AND SAGONA COURT. | 2022 | 5047 | 309.48 | 263 | 0 | 7046 | 0 | 0 | 0 | 7618.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200322 | New Storm Sewers in Saxon Ave & Draper Pl, Staten Island | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 502 | SE-0200R SE-0002R WM-0001 WM-0006 |  |  | NEW STORM SEWERS IN SAXON AVENUE AND DRAPER PLACE AS WELL AS AN OUTFALL IN FRESHKILLS PARK, STATEN ISLAND | 2022 | 64852 | 0 | 0 | 0 | 0 | 0 | 62470 | 0 | 62470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER200552 | STRM & SAN SWR AND WM WORK IN GRANITE AV | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 501 | SE-0200R SE-0002R WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STRM & SAN SWR AND WM WORK IN GRANITE AV, B/T WALKER ST & DAVID PL | 2022 | 5603 | 381.72 | 0 | 0 | 0 | 0 | 0 | 4313 | 4694.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SER20079 | RECON OF STORM SEWER, WILLOW AV(TOMPKINS-EDGEWATER AVS) | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 501 | SE-0002R SE-0200R WM-0001 SE-1000 HW-0200 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | N/A |  | 2022 | 1343 | 12197.22 | 2976 | 0 | 0 | 0 | 0 | 0 | 15173.22 | 862.54 | 0 | 0 | 0 | 0 | 0 | 0 | 862.54
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARDOS2 | Staten Island 3 Garage HVAC | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 503 | PU-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  |  | 2022 | 755 | 1464.6 | 140 | 1924 | 0 | 0 | 0 | 0 | 3528.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 850 | DEPT OF DESIGN & CONSTRUCTION | SOLARGR10 | DSNY - PV INSTALLATION ON NEW GARAGE- STATEN ISLAND 1/3 | DISTRIBUTED GENERATION | 501 | PU-0025 |  |  | DSNY - PV INSTALLATION ON NEW GARAGE- STATEN ISLAND 1/3 | 2022 | 7601 | 7085.22 | 1214 | 187 | 0 | 0 | 0 | 0 | 8486.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO264SIMP | DASNY - STATEN ISLAND MASTER PLAN- PHASE 2 | CONSTRUCTION OF NEW COURT FACILITIES | 501 | CO-0264 |  | 100 RICHMOND TERRACE | CONSTRUCTION OF ADDITION TO STATEN ISLAND FAMILY COURT BUIILDING AND RENOVATION OF 18 RICHMOND TERR. | 2022 | 216508 | 0 | 0 | 23147 | 8903 | 184458 | 0 | 0 | 216508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO276EXT2 | 100 Richmond Terrace - Family Court/ Exterior | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 501 | CO-0276 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | EXTERIOR OF COURTHOUSE | 2022 | 4414 | 0 | 0 | 0 | 327 | 0 | 0 | 4087 | 4414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO287R-1 | DASNY - NEW STATEN ISLAND SUPREME COURT | CONSTRUCTION OF NEW COURT FACILITIES | 501 | CO-0287 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | STATEN ISLAND, NY 10301 | CONSTRUCTION OF AN ENTIRE NEW BUILDING | 2022 | 213781 | 5726.13 | 0 | 1976 | 0 | 0 | 0 | 0 | 7702.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301FA | 130 STUYVESANT PL.- ELEC/FIRE ALARM/SPRINKLER | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 501 | CO-0301 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 130 STUYVESANT PL.- FIRE ALARM/SPRINKLER | 2022 | 13000 | 0 | 0 | 1000 | 0 | 12000 | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO301HV1 | 130 STUYVESANT PL.- CHILLER AND BOILER | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 501 | CO-0301 |  |  | 130 STUYVESANT PLACE - CHILLER AND BOILER REPLACEMEN | 2022 | 5791 | 0 | 345 | 0 | 0 | 5426 | 0 | 0 | 5771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0010 | DCAS - S.I. Campus - Deep Energy Retrofit | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 501 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DER - S.I. CAMPUS | 2022 | 33817 | 0 | 0 | 17409 | 16408 | 0 | 0 | 0 | 33817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0072 | NYPD - 123RD PRECINCT | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 501 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | IA/SQ | 2022 | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0076 | NYPD - 122ND PRECINCT | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 501 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | IA/SQ | 2022 | 300 | 0 | 317 | 0 | 0 | 0 | 0 | 0 | 317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PO79SIMD | NYPD - RELOCATE STATEN ISLAND MEDICAL DIVISION | POLICE FACILITIES | 501 | PO-0079 |  |  | SQ/IA | 2022 | 4076 | 0 | 3659 | 417 | 0 | 0 | 0 | 0 | 4076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326DOFR | DOF - 350 ST. MARK'S PLACE - LEASED SPACE | RENOVATION OF LEASED SPACE | 501 | PW-0326 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 350 ST. MARK'S PLACE - DOF LEASED SPACE | 2022 | 1544 | 0 | 0 | 0 | 0 | 0 | 0 | 1591 | 1591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RAR | LAW DEPT - RAISE THE AGE -SI | RENOVATION OF LEASED SPACE | 501 | PW-0326 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | LAW DEPT - RAISE THE AGE -SI | 2022 | 2697 | 0 | 0 | 0 | 0 | 0 | 0 | 2697 | 2697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326RHP | OCA RELOCATION FROM HOMEPORT - STATEN ISLAND | RENOVATION OF LEASED SPACE | 500 501 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RELOCATION FROM HOMEPORT - STATEN ISLAND - DUE TO MAYOR'S REDEVELOPMENT PLAN | 2022 | 1012 | 2766.7 | 160 | 0 | 0 | 0 | 0 | 0 | 2926.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326ZR02 | CB#2 - 2 TELEPORT DR | RENOVATION OF LEASED SPACE | 501 | PW-0326 |  |  | OFFICE RENOVATON | 2022 | 554 | 0 | 0 | 0 | 554 | 0 | 0 | 0 | 554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501BL | 10 RICHMOND TERR.- BOILER REPLACEMENT | REHABILITATION OF CITY-OWNED OFFICE SPACE | 501 | PW-0077 |  |  | SQ FT | 2022 | 1307 | 0 | 0 | 1185 | 0 | 0 | 0 | 0 | 1185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77501DB | 10 RICHMOND TERRACE - 2nd & 3rd FLs CCHR/DOB RENOVATION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 501 | PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SQ/IA | 2022 | 6322 | 0 | 819 | 0 | 0 | 6000 | 626 | 0 | 7445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR077MUR | 18 RICHMOND TERRACE- STATEN ISLAND COURTHOUSE MURALS | REHABILITATION OF COURT BUILDINGS | 501 | PW-R077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PERFORM NECESSARY CONSTRUCTION ASSOCIATED WITH THE TRANSFER OF COURTHOUSE MURALS | 2022 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77GRGE | ST. GEORGE COURTHOUSE & HYATT STREET PLAZA | REHABILITATION OF CITY-OWNED OFFICE SPACE | 500 501 | PW-R077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ST. GEORGE COURTHOUSE & HYATT STREET PLAZA | 2022 | 1518 | 0 | 0 | 0 | 0 | 0 | 780 | 0 | 780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWR77SICC | NYC OFFICE OF EMERGENCY MANAGEMENT BOROUGH COMMAND CENTER ON | MISCELLANEOUS CONSTRUCTION |  | PW-R077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NYC OFFICE OF EMERGENCY MANAGEMENT BOROUGH COMMAND CENTER ON STATEN ISLAND: RENOVATION OF BUILDING INCLUDING NEW FLOORS, PARTITION WALLS, NEW LIGHTING, SECURITY CAMERAS, DOORS, ELECTRICAL OUTLETS. | 2022 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | RICHMOND | 856 | DEPT OF CITYWIDE ADMIN SERVS | STGESPLND | ST. GEORGE ESPLANADE | WATERFRONT DEVELOPMENT | 501 | PW-R077 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | ST. GEORGE ESPLANADE STATEN ISLAND | RECONSTRUCTION | 2022 | 4760 | 3317.04 | 0 | 0 | 0 | 0 | 0 | 800 | 4117.04 | 3.07 | 0 | 0 | 0 | 0 | 0 | 0 | 3.07
20220309 | RICHMOND | 858 | DEPT OF INFO TECH & TELECOMM | DATACENTR | FISA Alternative Data Center | RENOVATION OF LEASED SPACE | 501 | PW-0326 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | DOITT BACK UP FACILITY TO BE MOVED TO CORPORATE COMMONS | 2022 | 30450 | 2434.85 | 6809 | 5207 | 0 | 0 | 0 | 0 | 14450.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18ALRFW | Allerton - New Roof and Windows | ESSENTIAL RECONSTRUCTION OF FACILITIES | 111 | LN-X001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NYPL ALLERTON BRANCH--NEW ROOF AND WINDOWS 2740 BARNES AVENUE. | 2022 | 1000 | 0 | 0 | 0 | 0 | 100 | 900 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18BEADA | BELMONT- ADA-compliant Restrooms | ESSENTIAL RECONSTRUCTION OF FACILITIES | 106 | LN-D008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BELMONT BRANCH--UPGRADE RESTROOMS TO BECOME ADA COMPLIANT | 2022 | 500 | 0 | 0 | 0 | 0 | 50 | 450 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18CPBOI | CLASON'S POINT - New Boiler | ESSENTIAL RECONSTRUCTION OF FACILITIES | 109 | LN-0008 |  |  | NEW BOILER | 2022 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18DYBHV | SPUYTEN DUYVIL - Boiler and HVAC Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 108 | LN-0008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SPUYTEN DUYVIL - BOILER AND HVAC | 2022 | 725 | 0 | 0 | 0 | 0 | 0 | 0 | 725 | 725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN18RDADA | Riverdale - ADA-compliant Bathroom Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 108 | LN-D008 |  |  | BATHROOM RENOVATION AT THE RIVERDALE BRANCH LIBRARY (ADA COMPLIANCE) | 2022 | 500 | 0 | 0 | 0 | 0 | 50 | 450 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LN21GDHVA | Grand Concourse - HVAC System Replacement | IMPROVEMENTS TO EXISTING FACILITIES |  | LN-0008 |  |  | GRAND CONCOURSE - HVAC SYSTEM REPLACEMENT | 2022 | 3000 | 0 | 0 | 500 | 2500 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNBEREXRE | Belmont - Exterior Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | LN-D008 |  |  | BELMONT PUBLIC LIBRARY - EXTERIOR RENOVATION -- BUILDING ENVELOPE/FACILITY PRESERVATION. FY19 ADP | 2022 | 1000 | 0 | 0 | 0 | 0 | 100 | 900 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNBERHVAC | Belmont - HVAC /Mechnical Systems Upgrade | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | LN-D008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BELMONT PUBLIC LIBRARY - HVAC UPGRADE -- HVAC/MECHANICAL SYSTEMS UPGRADE. FY19 ADP | 2022 | 1500 | 0 | 0 | 0 | 0 | 150 | 1350 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNCA16SDW | Sedgwick - New Roof | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 | LN-D008 |  |  | NEW ROOF | 2022 | 300 | 0 | 0 | 0 | 0 | 30 | 270 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNCA17PBY | PELHAM BAY - ADA Restrooms, New Roof | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 | LN-D008 |  |  | PELHAM BAY: ADA RESTROOMS AND NEW ROOF | 2022 | 1300 | 0 | 0 | 0 | 0 | 141 | 1037 | 0 | 1178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNGDEXTRO | Grand Concourse - New Roof, Building Envelope | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | LN-0008 LN-D008 |  |  | GRAND CONCOURSE PUBLIC LIBRARY - NEW ROOF -- BUILDING ENVELOPE/FACILITY PRESERVATION | 2022 | 2078 | 0 | 0 | 278 | 4046 | 0 | 0 | 0 | 4324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNMPADA01 | Morris Park - ADA-compliant Entrance | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | LN-D008 |  |  | NYPL: MORRIS PARK BRANCH -- ADA COMPLIANT ENTRANCE | 2022 | 500 | 0 | 0 | 0 | 0 | 50 | 450 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNVNADABA | Pelham Pkwy/Van Nest - ADA-compliant Bathroom | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | LN-D008 |  |  | NYPL: PELHAM PARKWAY- VAN NEST BRANCH -- ADA COMPLIANT BATHROOM | 2022 | 500 | 0 | 0 | 0 | 0 | 50 | 450 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 037 | NEW YORK PUBLIC LIBRARY | LNXA20WKF | Wakefield - Infrastructure and ADA Upgrades | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | LN-X001 LN-0008 LN-D008 |  |  | WAKEFIELD - INFRASTRUCTURE AND ADA UPGRADES | 2022 | 3443 | 0 | 0 | 568 | 3022 | 0 | 0 | 0 | 3590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | ACECUN507 | CUNY - Hostos CC Summer Boiler | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 104 | HN-0206 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HOSTOOS CC SUMMER BOILER | 2022 | 103 | 202.6 | 50 | 0 | 0 | 0 | 0 | 0 | 252.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | ACECUN901 | CUNY - BMS Upgrade at 4 Hostos College Buildings | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 101 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CUNY - BMS UPGRADE AT 4 HOSTOS COLLEGE BUILDINGS | 2022 | 5108 | 0 | 5108 | 0 | 0 | 0 | 0 | 0 | 5108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | BX001-021 | Roscoe Brown Memorial | MISCELLANEOUS RECONSTRUCTION | 100 | HN-D004 |  |  | ROSCOE BROWN MEMORIAL | 2022 | 350 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | BX006-022 | Food Pantry Construction | MISCELLANEOUS RECONSTRUCTION | 100 | HN-D002 |  |  | NEW FOOD PANTRY | 2022 | 1150 | 0 | 0 | 1150 | 0 | 0 | 0 | 0 | 1150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | BX022-009 | Gould Memorial Lib Rotunda Staircase Installation | MISCELLANEOUS RECONSTRUCTION | 100 105 | HN-D002 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | INSTALLATION OF STAIRCASES FOR GOULD MEMORIAL LIB ROTUNDA | 2022 | 1093 | 958.32 | 0 | 0 | 134 | 0 | 0 | 0 | 1092.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | BX026-013 | ADA Entrance Ramps | MISCELLANEOUS RECONSTRUCTION | 100 105 | HN-X002 HN-X001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ADA ENTRANCE RAMPS | 2022 | 300 | 43.59 | 0 | 0 | 256 | 0 | 0 | 0 | 299.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | BX027-015 | Ohio Track & Field Restoration | MISCELLANEOUS RECONSTRUCTION | 100 | HN-X002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | OHIO TRACK & FIELD RESTORATION | 2022 | 375 | 75 | 0 | 0 | 425 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | BX032-015 | Monument Hills Restoration | MISCELLANEOUS RECONSTRUCTION | 100 | HN-D002 HN-0206 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MONUMENT HILLS RESTORATION | 2022 | 200 | 210.11 | 0 | 0 | 24 | 116 | 0 | 0 | 350.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | BX038-016 | Lowe Hall ADA Accessibility Improvements | MISCELLANEOUS RECONSTRUCTION | 100 | HN-D002 HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LOWE HALL ADA ACCESSIBILITY IMPROVEMENTS | 2022 | 250 | 0 | 1163 | 0 | 0 | 0 | 0 | 0 | 1163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | BX039-016 | Alumni Gym Locker Room Accessibility Improvements - Bronx CC | MISCELLANEOUS RECONSTRUCTION | 100 | HN-D005 HN-D002 HN-0206 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ALUMNI GYM ADA IMPROVEMENTS | 2022 | 250 | 0 | 1145 | 0 | 0 | 0 | 0 | 0 | 1145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | BX040-017 | Bronx Express | MISCELLANEOUS RECONSTRUCTION | 100 | HN-0206 HN-X002 HN-D002 HN-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STUDENT SUCCESS CENTER | 2022 | 4500 | 763.26 | 7307 | 0 | 0 | 0 | 0 | 0 | 8070.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | BX041-017 | STEM Resource Center | MISCELLANEOUS RECONSTRUCTION | 100 | HN-D002 HN-D004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STEM RESOURSE CENTER | 2022 | 150 | 28.06 | 0 | 0 | 122 | 0 | 0 | 0 | 150.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | BX042-018 | Renovate Roscoe Brown Student Center | MISCELLANEOUS RECONSTRUCTION | 107 | HN-X002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATE ROSCOE BROWN STUDENT CENTER | 2022 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | BX044-018 | Community Hall First Floor Renovation | MISCELLANEOUS RECONSTRUCTION | 100 | HN-D004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COMMUNITY HALL FIRST FLOOR RENOVATION | 2022 | 500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | BX045-018 | ADA Accessibility for Roscoe C Brown Student Center | MISCELLANEOUS RECONSTRUCTION | 100 | HN-D004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ADA ACCESSIBILITY FOR ROSCOE C BROWN STUDENT CENTER | 2022 | 400 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | BX046-019 | Alumni Gym HVAC & ADA Improvements | MISCELLANEOUS RECONSTRUCTION | 105 | HN-D002 HN-X002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ALUMNI GYM HVAV& ADA UPGRADES | 2022 | 3000 | 0 | 0 | 250 | 2750 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | BX047-020 | Ohio Track & Field Upgrade | MISCELLANEOUS RECONSTRUCTION | 105 | HN-X002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | OHIO TRACK & FIELD UPGRADE | 2022 | 500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | BX048-020 | ELEVATOR UPGRADES | MISCELLANEOUS RECONSTRUCTION | 100 | HN-D002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ELEVATOR UPGRADES | 2022 | 1008 | 0 | 0 | 125 | 883 | 0 | 0 | 0 | 1008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | BX049-020 | Carl Polowczyk Hall Upgrades | MISCELLANEOUS RECONSTRUCTION | 100 | HN-D002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CARL POLOWCZYK HALL UPGRADES | 2022 | 3000 | 0 | 0 | 250 | 2750 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | BX050-021 | Elevator Installation Gould Memorial Library | MISCELLANEOUS RECONSTRUCTION | 100 | HN-X002 HN-D004 |  |  | ELEVATOR INSTALLATION GOULD MEMORIAL LIBRARY | 2022 | 750 | 0 | 0 | 250 | 500 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | CA034HS13 | 500 Grand Concourse 3rd Floor Renovation | MISCELLANEOUS RECONSTRUCTION | 100 | HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 500 GRAND CONCOURSE THIRD FLOOR RENOVATION | 2022 | 6950 | 5875 | 0 | 1075 | 0 | 0 | 0 | 0 | 6950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | CA036-014 | Hostos CC: Allied Health and Sciences Building | MISCELLANEOUS RECONSTRUCTION | 100 101 | HN-X002 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | COMMUNITY COLLEGE IMPROVEMENTS | 2022 | 2003 | 0 | 0 | 0 | 0 | 2003 | 0 | 0 | 2003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | CA091HS96 | Hostos Retaining Wall Project | MISCELLANEOUS RECONSTRUCTION | 100 | HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HOSTOS RETAINING WALL PROJECT | 2022 | 1500 | 1000 | 0 | 500 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | CA200BX21 | BCC Boiler Plant Upgrade | MISCELLANEOUS RECONSTRUCTION | 100 | HN-0206 |  |  | BCC BOILER PLANT UPGRADE | 2022 | 16000 | 600 | 0 | 15400 | 0 | 0 | 0 | 0 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | CA201BX21 | Bronx CC - Philosophy Hall Roof Replacement | MISCELLANEOUS RECONSTRUCTION | 100 | HN-0206 |  |  | PHILOSOPHY HALL ROOF REPLACEMENT | 2022 | 900 | 0 | 150 | 0 | 750 | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | CA202HS04 | ADA Improvements | MISCELLANEOUS RECONSTRUCTION | 105 | HN-D002 HN-0206 | PROJECT DELAYED DUE TO UNAVAILABILITY OF PRODUCT |  | ADA IMPROVEMENTS | 2022 | 750 | 770.12 | 0 | 0 | 137 | 630 | 0 | 0 | 1537.12 | 91.7 | 0 | 0 | 0 | 0 | 0 | 0 | 91.7
20220309 | BRONX | 042 | CITY UNIVERSITY | HS007-010 | PEDESTRIAN BRIDGE ROOF REPLACEMENT | MISCELLANEOUS RECONSTRUCTION | 100 101 | HN-D004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROOF REPLACEMENT | 2022 | 323 | 150 | 0 | 0 | 173 | 0 | 0 | 0 | 323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | HS007-022 | Second Floor & Basement Renovations | MISCELLANEOUS RECONSTRUCTION | 100 | HN-D002 HN-X002 |  |  | SECOND FLOOR & BASEMENT RENOVATIONS | 2022 | 2500 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | HS033-007 | Brick Wall Restoration/Garden Upgrades | MISCELLANEOUS RECONSTRUCTION | 100 101 | HN-X002 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NATURAL SCIENCE LAB RENOVATION | 2022 | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | HS034-007 | 450 Grand Concourse Theater Improvements | MISCELLANEOUS RECONSTRUCTION | 100 | HN-D004 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 450 GRAND CONCOURSE THEATER IMPROVEMENTS | 2022 | 250 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | HS041-011 | 500 Grand Concourse 4th Floor and Emerg. Generator | MISCELLANEOUS RECONSTRUCTION | 100 101 | HN-X002 HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | EMERGENCY GENERATOR | 2022 | 778 | 5807.82 | 0 | 0 | 38 | 0 | 0 | 0 | 5845.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | HS043-011 | Hostos CC - 500 Grand Concourse Renovations | MISCELLANEOUS RECONSTRUCTION | 100 101 | HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 500 GRAND CONCOURSE RENOVATIONS | 2022 | 3970 | 0 | 0 | 0 | 0 | 535 | 0 | 0 | 535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | HS047-013 | Savoy Building Roof Replacement | MISCELLANEOUS RECONSTRUCTION | 100 101 | HN-D002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SAVOY BLDG. ROOF REPLACEMENT | 2022 | 600 | 900 | 0 | 0 | 50 | 0 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | HS048-013 | Renovation and HVAC Upgrade | MISCELLANEOUS RECONSTRUCTION | 100 101 | HN-D002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION AND HVAC UPGRADE | 2022 | 200 | 2622.6 | 0 | 0 | 77 | 0 | 0 | 0 | 2699.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | HS050-014 | Allied Health and Sciences Building | MISCELLANEOUS RECONSTRUCTION | 100 101 | HN-D005 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ALLIED HEALTH AND SCIENCES BUILDING | 2022 | 2500 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | HS054-017 | Create one Stop Center -425 Grand Concourse | MISCELLANEOUS RECONSTRUCTION | 100 | HN-X002 HN-D002 HN-0206 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CREATE ONE STOP CENTER | 2022 | 3850 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | HS057-019 | Smart Classroom Conversion | MISCELLANEOUS RECONSTRUCTION | 100 | HN-X002 HN-D002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SMART CLASSROOM CONVERSION | 2022 | 1500 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | HS058-019 | Basement Renovations at 500 Grand Concourse | MISCELLANEOUS RECONSTRUCTION | 100 | HN-D002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BASEMENT RENOVATIONS AT 500 GRAND CONCOURSE | 2022 | 2000 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | HS058-020 | 2nd Floor & Basement Renovation/Final Phase (500 GC) | MISCELLANEOUS RECONSTRUCTION | 105 | HN-X002 HN-D002 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 2ND FLOOR & BASEMENT RENOVATION/FINAL PHASE | 2022 | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | HS059-021 | Video Projection | DATA PROCESSING AND OTHER EQUIPMENT | 100 | HN-X002 |  |  |  | 2022 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | LM002-021 | Teaching and Learning Innovation Space - Art | MISCELLANEOUS RECONSTRUCTION | 100 | HN-D300 |  |  | TEACHING AND LEARNING COMMONS | 2022 | 950 | 0 | 0 | 0 | 950 | 0 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | LM004-022 | Lecture Hall Upgrades | MISCELLANEOUS RECONSTRUCTION | 100 | HN-0300 |  |  | LECTURE HALL UPGRADES | 2022 | 1500 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | LM019-011 | Concert Hall Lighting Upgrade / Acoustics Upgrade | MISCELLANEOUS RECONSTRUCTION | 100 107 | HN-X005 | PROJECT DELAYED DUE TO UNAVAILABILITY OF PRODUCT |  | LOCKER ROOM LOCKER REPLACEMENT | 2022 | 850 | 809.98 | 0 | 0 | 39 | 0 | 0 | 0 | 848.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | LM021-012 | Teaching and Learning Commons | MISCELLANEOUS RECONSTRUCTION | 100 | HN-X300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TEACHING AND LEARNING COMMONS | 2022 | 1300 | 1299.99 | 1000 | 0 | 0 | 0 | 0 | 0 | 2299.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | LM029016 | Upgrade and Convert Carman Hall | MISCELLANEOUS RECONSTRUCTION | 107 | HN-X005 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | UPGRADE AND CONVERT CARMAN HALL | 2022 | 550 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | LM032-017 | Gillet Auditorium Renovation | MISCELLANEOUS RECONSTRUCTION | 100 | HN-D300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | GILLET AUDITORIUM RENOVATION | 2022 | 1700 | 0 | 0 | 0 | 1700 | 0 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | LM034-018 | Convert classrooms into NetworkSmart Rooms | MISCELLANEOUS RECONSTRUCTION |  | HN-X300 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONVERT CLASSROOMS INTO NETWORKSMART ROOMS | 2022 | 368 | 0 | 0 | 0 | 368 | 0 | 0 | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | LM035-018 | Gillet Auditorium Renovation | MISCELLANEOUS RECONSTRUCTION | 100 | HN-D300 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | GILLET AUDITORIUM RENOVATION | 2022 | 1866 | 0 | 0 | 0 | 1866 | 0 | 0 | 0 | 1866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | LM041-020 | Studio Theatre Lighting & Dimming System | MISCELLANEOUS RECONSTRUCTION | 105 | HN-X300 HN-D300 |  |  | STUDIO THEATRE LIGHTING & DIMMING SYSTEM | 2022 | 700 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | LM042-020 | Nursing Facility Construction, Furniture and Equipment | MISCELLANEOUS RECONSTRUCTION | 100 | HN-D300 |  |  | NURSING FACILITY CONSTRUCTION, FURNITURE AND EQUIPMENT | 2022 | 3000 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 042 | CITY UNIVERSITY | LM043-021 | Social Work Department Expansion | MISCELLANEOUS RECONSTRUCTION | 100 | HN-X300 HN-D300 |  |  | SOCIAL WORK DEPPARTMENT EXPANSION | 2022 | 1050 | 0 | 0 | 0 | 1050 | 0 | 0 | 0 | 1050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 056 | POLICE DEPARTMENT | PO79-52P | 52ND PRECINCT RENOVATION | POLICE FACILITIES | 100 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ESTIMATE | 2022 | 20618 | 0 | 100 | 0 | 0 | 20518 | 0 | 0 | 20618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAJX | 46th PRECINCT ADA RAMP | POLICE FACILITIES | 100 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | 46TH ADA RAMP | 2022 | 325 | 57.5 | 267 | 0 | 0 | 0 | 0 | 0 | 324.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKD | RODMAN'S NECK BATHROOM TRAILERS | POLICE FACILITIES | 100 | PO-0079 |  |  | ESTIAMTE | 2022 | 116 | 0 | 552 | 264 | 0 | 0 | 0 | 0 | 816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKK | REHABILITATION OF 48TH PCT ELEVATOR | POLICE FACILITIES | 100 | PO-0079 |  |  | ESTIMATE | 2022 | 1500 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKO | ROOF REPLACEMENT AT 49TH PCT | POLICE FACILITIES | 100 | PO-0079 |  |  | ESTIMATE | 2022 | 2300 | 0 | 500 | 1800 | 0 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKU | 49TH PCT ROOF REPLACEMENT | POLICE FACILITIES | 100 | PO-0079 |  |  | ESTIMATE | 2022 | 560 | 0 | 0 | 560 | 0 | 0 | 0 | 0 | 560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 056 | POLICE DEPARTMENT | PO79BMAKV | 41ST PCT ROOF REPLACEMENT | POLICE FACILITIES | 100 | PO-0079 |  |  | ESTIMATE | 2022 | 800 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 056 | POLICE DEPARTMENT | PO79BXTPT | Bronx Tow Pound Trailers at the Fordham Landing | POLICE FACILITIES | 100 | PO-0079 |  |  | SCOPE OF WORK | 2022 | 2500 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 056 | POLICE DEPARTMENT | PO79RNSA | RODMAN'S NECK SOUND ABATEMENT | POLICE FACILITIES | 100 | PO-0079 | PROJECT DELAYED PENDING RELEASE OF NEW TECHNOLOGY |  | SCOPE DESCRIPTION | 2022 | 3800 | 0 | 3800 | 0 | 0 | 0 | 0 | 0 | 3800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 056 | POLICE DEPARTMENT | POD47RENO | Renovate/Upgrade 47th Precinct. | POLICE FACILITIES | 100 | PO-D079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION | 2022 | 1000 | 64 | 0 | 936 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 056 | POLICE DEPARTMENT | POD49PARK | 49th Precinct Parking Lot Renovation Upgrade | POLICE FACILITIES | 100 | PO-D079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ESTIMATE | 2022 | 150 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 056 | POLICE DEPARTMENT | POD49RENO | 49TH PCT - RENOVATION | POLICE FACILITIES | 100 111 | PO-0079 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 2121 EASTCHESTER ROAD, BRONX | RENOVATION | 2022 | 250 | 566 | 0 | 85 | 0 | 0 | 0 | 0 | 651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 056 | POLICE DEPARTMENT | POD50ELGE | 50TH PCT REPLACE ELEVATORS AND GENERATORS | POLICE FACILITIES | 108 | PO-D001 PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 3450 KINGSBRIDGE AV. BRONX | DUE TO A FIRE IN THE ELEVATOR SHAFT IT BECAME NECESSARY TO PROCEED WITH THE ELEVATOR PART OF THE PROJECT THROUGH AN EMERGENCY CONTRACT PROCESS USING NYPD INTERNAL CAPITAL FUNDING. THE GENERATOR PART OF THE PROJECT WAS DONE USING OTHER THAN CAPITAL FUNDING. | 2022 | 325 | 59.93 | 706 | 0 | 0 | 0 | 0 | 0 | 765.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 056 | POLICE DEPARTMENT | POD52PARK | 52nd Precinct Parking Lot Renovation Upgrade | POLICE FACILITIES | 100 | PO-D079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ESTIMATE | 2022 | 425 | 0 | 312 | 113 | 0 | 0 | 0 | 0 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 057 | FIRE DEPARTMENT | ACEFDN202 | FDNY - PV Installation at 4 Facilities | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 101 | PU-0025 F-0175 |  |  | PV INSTALLATION AT 4 FACILITIES | 2022 | 550 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 057 | FIRE DEPARTMENT | F175KIT42 | KITCHEN REPLACEMENT - EC42 | NEW FACILITIES AND RENOVATIONS | 105 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | KITCHEN REPLACEMENT | 2022 | 961 | 149.33 | 0 | 1171 | 0 | 0 | 0 | 0 | 1320.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 057 | FIRE DEPARTMENT | F175RFW20 | Roof and Windows - EMS 20 | NEW FACILITIES AND RENOVATIONS | 111 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ROOF AND WINDOWS - EMS 20 | 2022 | 1430 | 24.49 | 1656 | 0 | 0 | 0 | 0 | 0 | 1680.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 057 | FIRE DEPARTMENT | F175XIN82 | Exterior and Interior Renovations - EC 82 | NEW FACILITIES AND RENOVATIONS | 103 | F-0175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | EXTERIOR AND INTERIOR RENOVATIONS - EC 82 | 2022 | 4270 | 7454.23 | 3974 | 0 | 0 | 0 | 0 | 0 | 11428.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 057 | FIRE DEPARTMENT | F1TELMPS2 | PSACII Telemetry | COMMUNICATIONS | 111 | F-0001 | PROJECT DELAYED DUE TO UNAVAILABILITY OF PRODUCT |  |  | 2022 | 6264 | 3675.75 | 32 | 1150 | 0 | 0 | 0 | 0 | 4857.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 057 | FIRE DEPARTMENT | FX175GE42 | Generator - EC42 | NEW FACILITIES AND RENOVATIONS |  | F-0175 F-X175 |  |  | GENERATOR REPLACEMENT AT EC42. | 2022 | 375 | 89.24 | 891 | 0 | 0 | 0 | 0 | 0 | 980.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 057 | FIRE DEPARTMENT | FX175WN46 | Window Replacement - EC46 | NEW FACILITIES AND RENOVATIONS |  | F-X175 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WINDOW REPLACEMENT AT EC46. | 2022 | 375 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 068 | ADMIN FOR CHILDREN'S SERVICES | BXELEVFAR | 1250 E229th Street Elevator and Fire Alarm Replacement | CHILD WELFARE FACILITIES | 112 | CS-0005 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 1250 E229TH STREET ELEVATOR AND FIRE ALARM REPLACEMENT. | 2022 | 358 | 0 | 1284 | 0 | 0 | 0 | 0 | 0 | 1284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 068 | ADMIN FOR CHILDREN'S SERVICES | JJCONS | Secure Detention Facility Renovations | CHILD WELFARE FACILITIES | 101 | CS-0005 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | TBD | TBD | 2022 | 170000 | 0 | 5000 | 0 | 0 | 0 | 0 | 13245 | 18245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH112FAFC | FRANKLIN'S WOMEN'S SHELTER - FACADE REHABILITATION | SHELTERS FOR HOMELESS INDIVIDUALS | 103 | HH-0112 |  |  | FRANKLIN'S WOMEN'S SHELTER - FACADE REHABILITATION | 2022 | 1693 | 0 | 135 | 0 | 1558 | 0 | 0 | 0 | 1693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115JEXT | UNIVERSITY AVENUE FAMILY FACAD | SHELTERS FOR HOMELESS FAMILIES |  | HH-0112 |  |  | FACADE AND WINDOWS | 2022 | 3600 | 0 | 0 | 0 | 300 | 0 | 3300 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115NLBR | JAMAICA'S WOMENN'S SHELTER - BATHROOM RECONSTRUCTION | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 |  |  | JAMAICA WOMEN'S SHELTER - BATHROOM RECONSTRUCTION | 2022 | 3562 | 0 | 281 | 281 | 0 | 3283 | 0 | 0 | 3845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115SNBH | SENECA HOUSES - BOILER AND HEATING | SHELTERS FOR HOMELESS FAMILIES | 102 | HH-0115 |  |  | SENECA HOUSES - BOILER AND HEATING | 2022 | 0 | 0 | 0 | 200 | 0 | 2000 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115SNRF | SENECA HOUSES - ROOF REPLACEMENT AND FACADE REHABILITATION | SHELTERS FOR HOMELESS FAMILIES | 102 | HH-0115 |  |  | SENECA HOUSES - ROOF REPLACEMENT AND FACADE REHABILITATION | 2022 | 730 | 58 | 0 | 672 | 0 | 0 | 0 | 0 | 730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNBT | UNIVERSITY FAMILY KITCHEN BATHROOMS AND VENTILATION | SHELTERS FOR HOMELESS FAMILIES | 104 | HH-0115 |  |  | RECONSTRUCT KITCHENS BATHROOMS AND ASSOCIATED INTERNAL VENTILATION | 2022 | 2130 | 0 | 0 | 330 | 0 | 900 | 900 | 0 | 2130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNEU | UNIVERSITY FAMILY RESIDENCE ROOF REPLACEMENT | SHELTERS FOR HOMELESS FAMILIES | 104 | HH-0115 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RESTORATION OF ROOF AND FACADE AT THE UNIVERSITY AVENUE FAMILY RESIDENCE | 2022 | 1356 | 946.52 | 0 | 150 | 0 | 700 | 500 | 0 | 2296.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HH115UNFL | UNIVERSITY AVENUE FOUNDATION RECONSTRUCTION | SHELTERS FOR HOMELESS FAMILIES |  | HH-0112 |  |  | RECONSTRUCT BUILDING FOUNDATION | 2022 | 360 | 0 | 30 | 0 | 330 | 0 | 0 | 0 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 071 | DEPT OF HOMELESS SERVICES | HHNC001 | NEW ERA VETERANS SRO- KITCHEN RENOVATION | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-D025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW ERA VETERANS SRO- KITCHEN RENOVATION | 2022 | 400 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C-101WEST | RI WEST PERIMETER EXTERIOR FENCING REPLACEMENT | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACE WEST PERIMETER FENCING | 2022 | 11147 | 15578.47 | 0 | 0 | 0 | 3000 | 1973 | 0 | 20551.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C130PANEL | REPLACEMENT OF ELECTRICAL DISTRIBUTION PANELS- RI POWERHOUSE | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0130 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACEMENT OF ELECTRICAL DISTRIBUTION PANELS AT RI POWERHOUSE | 2022 | 715 | 107.49 | 1332 | 0 | 0 | 0 | 0 | 0 | 1439.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FEDER | NIC Power Feder Replacement | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0138 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NIC POWER FEEDER REPLACEMENT. | 2022 | 1000 | 158.26 | 1593 | 0 | 0 | 0 | 0 | 0 | 1751.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSPH2 | Fire Life Safety Phase II | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0138 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FIRE LIFE SAFETY PHASE II AT ALL DOC RIKERS AND BOROUGH FACILITIES | 2022 | 80849 | 0 | 0 | 0 | 0 | 0 | 52430 | 0 | 52430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138FSYS | FIRE SAFETY SYSTEM CONSTRUCTION | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0138 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FABRICATE AND INTEGRATE FIRE SAFETY SYSTEMS | 2022 | 24000 | 25959.56 | 0 | 0 | 0 | 0 | 0 | 802 | 26761.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138GRFS2 | GRVC - Fire Life Safety Phase II | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0138 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | GRVC FIRE LIFE SAFETY PHASE II | 2022 | 20469 | 2652.42 | 54714 | 0 | 0 | 0 | 0 | 0 | 57366.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138NCFS2 | Fire Life Safety Phase II for NIC Annex | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0138 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FIRE LIFE SAFETY PHASE II FOR NIC ANNEX | 2022 | 11872 | 770 | 649 | 0 | 0 | 0 | 0 | 0 | 1419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PURGR | POST FIRE PURGE SYSTEM AT GRVC | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0138 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | POST FORE PURGE SYSTEM FOR 200 AND 300 BED ADDITIONS GRVC | 2022 | 1800 | 239.71 | 1680 | 0 | 0 | 0 | 0 | 0 | 1919.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138PWRHS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT EXISTING POWERHOUSE | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0138 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DESIGN AND INSTALL FIRE ALARM SYSTEM AT EXISTING POWERHOUSE | 2022 | 2240 | 252.05 | 6000 | 0 | 0 | 0 | 0 | 0 | 6252.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C138TRANS | DESIGN AND INSTALL FIRE ALARM SYSTEM AT TRANSPORTATION DIV | BUILDING SYSTEMS AND INFRASTRUCTURE |  | C-0138 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DESIGN AND INSTALL FIRE ALARM SYSTEM AT TRANSPORTATION DIVISION | 2022 | 4380 | 261.51 | 4568 | 0 | 0 | 0 | 0 | 0 | 4829.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACOM | ADA COMPLIANCE FOR NIC, CENTRAL VISITS, FACILITY VISIT AREAS | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ADA COMPLIANCE FOR NIC, CENTRAL VISITS, AND FACILITY VISIT AREAS | 2022 | 33738 | 0 | 0 | 1280 | 0 | 0 | 0 | 0 | 1280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADACVT | ADA Compliance for Central Visits | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ADA COMPLIANCE FOR CENTRAL VISITS | 2022 | 10326 | 1136.82 | 8487 | 0 | 0 | 0 | 0 | 0 | 9623.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADAGRV | ADA Compliance for GRVC | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ADA COMPLIANCE FOR GRVC | 2022 | 5679 | 443.77 | 4205 | 0 | 0 | 0 | 0 | 0 | 4648.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ADARMS | ADA Compliance for RMSC | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ADA COMPLIANCE FOR RMSC | 2022 | 6352 | 376 | 200 | 0 | 0 | 0 | 0 | 0 | 576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ASBEST | Asbestos Abatement and Air Monitoring - Various Facilities | BUILDING SYSTEMS AND INFRASTRUCTURE |  | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REMOVAL OF ASBESTOS CONTAINING MATERIALS. | 2022 | 12210 | 8805.06 | 0 | 0 | 478 | 1235 | 3561 | 6600 | 20679.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75CELLD | Electronic Cell Door Panels at All Facilities | BUILDING SYSTEMS AND INFRASTRUCTURE |  | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ELECTRONIC CELL DOOR PANELS AT ALL FACILITIES TO FIX NON-OPERABLE DOORS | 2022 | 6900 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-ELEV | ELEVATOR REHAB VARIOUS FACILITIES | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RIKERS ISLAND BRONX | RECONSTRUCTION OF PASSENGER/FREIGHT ELEVATOR SERVING 3 FLOORS IN THEADMINISTRATION BUILDING INCLUDING ALL CONTROLS AND THE ENTIRE HYDRAULISYSTEM | 2022 | 4556 | 3132.05 | 0 | 0 | 0 | 0 | 13500 | 0 | 16632.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ENTGRV | Modification of Facility Entrance-GRVC | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MODIFICATION OF FACILITY ENTRANCE-GRVC | 2022 | 7946 | 669.79 | 7261 | 0 | 0 | 0 | 0 | 0 | 7930.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ENTNC | Modification for Facility Entries - NIC | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MODIFICATION FOR FACILITY ENTRIES - NIC | 2022 | 4131 | 405.79 | 200 | 0 | 0 | 0 | 0 | 0 | 605.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75ESUCP | New ESU Compound at Rikers Island | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NEW ESU COMPOUND AT RIKERS ISLAND | 2022 | 11952 | 2311.7 | 0 | 0 | 0 | 8743 | 0 | 0 | 11054.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75FENCE1 | FENCING RECONSTRUCTION | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | INTERIOR PERIMETER FENCE REPLACEMENT @ VAR. FAC. | 2022 | 3311 | 11693.9 | 2002 | 2000 | 0 | 0 | 0 | 0 | 15695.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-GCELL | GANG CELL DOOR RELEASE | BUILDING SYSTEMS AND INFRASTRUCTURE | 101 | C-0075 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RECONSTRUCT GANG DOORS NOT CURRENTLY SERVED BY ELECTRICAL RELEASE SYSTEMS | 2022 | 4000 | 0 | 0 | 1000 | 0 | 0 | 1000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GPARK | Construction of Parking Lot for GMDC Academy | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CONSTRUCTION OF PARKING LOT FOR GMDC ACADEMY | 2022 | 1250 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GRVCHV | GRVC HVAC Upgrades and Related Housing Area Renovations | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | GRVC (GROUP A) HEATING, VENTILATION AND RELATED SYSTEM COMPONENTS AT ALL DOC FACILITIES ARE IN VARYING DEGREE OF DETERIORATION AS THE SYSTEMS ARE 25 PLUS YEARS OLD AND ARE REACHING AT THE END OF ITS USEFUL LIFE. ADDITIONALLY, DUE TO THE CONTINUOUS OPERATION (24/7) THE SYSTEM'S LIFE SPAN SHORTENS AS SERVICING OF SUCH A SYSTEM OFTEN BECOMES VERY DIFFICULT. THIS PROPOSED PROJECT WILL PERFORM SYSTEMIC AND COMPREHENSIVEEXAMINATION OF ALL VENTILATION, HEATING AND COOLING SYSTEM COMPONENTS. | 2022 | 16717 | 1026.02 | 19460 | 0 | 0 | 0 | 0 | 0 | 20486.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75GRVRFW | GRVC Roof Replacement, Exterior Facades, Windows, Court Yard | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ALL OF THE DOC FACILITIES ARE 25+ YEARS OLD AND EXTERIOR ENVELOPE SHOWS SIGN OF DETERIORATION WHICH NEEDS FIXING BEFORE CONDITIONS GET BAD WHICH CAN FURTHER DAMAGE THE INTERIOR BUILDING SYSTEM INFRASTRUCTURE.THIS NEW NEEDS ACKNOWLEGES EXISTING FUNDS FOR SIMILAR PROJECTS IN THEAMOUNT OF $53,956,000. THIS REQUEST IS IN ADDITION TO THE EXISTING FUNDS. FOLLOWED BY INSPECTION PHASE A REHABILITATION PLAN AND PRIORITIES WILL BE DEVELOPED FOR DESIGN AND CONSTRUCTION PHASE. | 2022 | 10800 | 916.93 | 0 | 0 | 0 | 16000 | 0 | 0 | 16916.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75K9UNIT | New K 9 Facility at Rikers Island | SUPPORT SPACE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CONSTRUCT NEW K9 UNIT WITH REQUIRED OFFICES AND SUPPOTY SPACES. | 2022 | 3650 | 3830.53 | 3226 | 0 | 0 | 0 | 0 | 0 | 7056.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75MARINA | Rehabilitation of Existing Marina on RI | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REHABILITATION OF MARINA | 2022 | 4026 | 0 | 0 | 0 | 0 | 0 | 4200 | 0 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75-METH | Methane Detection System Replacement and Central Monitoring | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | METHANE SYSTEM REPLACEMENT AND CENTRAL MONITORING | 2022 | 6197 | 1289.84 | 18731 | 0 | 0 | 0 | 0 | 0 | 20020.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICA/C | NIC Air Conditioning -Benjamin Ventilation Order | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NIC REQUIRES AIR CONDITIONING | 2022 | 5300 | 8244.61 | 542 | 0 | 0 | 0 | 0 | 0 | 8786.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75NICFAC | ROOF & FACADE RECONSTRUCTION FOR MAIN AND ANNEX | BUILDING SYSTEMS AND INFRASTRUCTURE | 101 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ROOF & FACADE RESTORATIONS FOR MAIN AND ANNEX | 2022 | 6248 | 8152.63 | 2400 | 0 | 0 | 0 | 0 | 0 | 10552.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75PTREAT | Water Treatment for Powerhouse | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | WATER TREATMENT FOR POWERHOUSE | 2022 | 8203 | 522.72 | 13277 | 0 | 0 | 0 | 0 | 0 | 13799.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RDSRNG | New Modular Trailers and Classroom Renovation- Rodman's Neck | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | NEW MODULAR TRAILERS AND CLASSROOM RENOVATION | 2022 | 3116 | 8013.11 | 7897 | 0 | 0 | 0 | 0 | 0 | 15910.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMPWR | RMSC Power Upgrades for buildings 1,2,3,4,5,6 & 7 | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RMSC POWER UPGRADES FOR BUILDINGS 1,2,3,4,5,6 & 7 | 2022 | 10220 | 554.7 | 5229 | 0 | 0 | 0 | 0 | 0 | 5783.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75RMSRFW | RMSC Roof Replacement, Exterior Facades, Windows, Court Yard | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ALL OF THE DOC FACILITIES ARE 25+ YEARS OLD AND EXTERIOR ENVELOPE SHOWS SIGN OF DETERIORATION WHICH NEEDS FIXING BEFORE CONDITIONS GET BAD WHICH CAN FURTHER DAMAGE THE INTERIOR BUILDING SYSTEM INFRASTRUCTURE.THIS NEW NEEDS ACKNOWLEGES EXISTING FUNDS FOR SIMILAR PROJECTS IN THEAMOUNT OF $53,956,000. THIS REQUEST IS IN ADDITION TO THE EXISTING FUNDS. FOLLOWED BY INSPECTION PHASE A REHABILITATION PLAN AND PRIORITIES WILL BE DEVELOPED FOR DESIGN AND CONSTRUCTION PHASE. | 2022 | 13090 | 897.19 | 25688 | 0 | 0 | 0 | 0 | 0 | 26585.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SEAWLL | Construction of Sea Wall and Raising of Madanici Road | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | THE RAISING OF MANDANICI ROAD IS REQUIRED AS THE ROAD OFTEN GETS FLOODED DURING INCLEMENT WEATHER CUTTING OFF TRAFFIC BETWEEN THE EASTSIDE FACILITIES AND HAZEN STREET. THE BUILDING OF THE SEA WALL IS REQUIRED TO PROTECT THE COGEN POWER PLANT FROM STORM SURGES OR FLOODING. | 2022 | 7017 | 649.97 | 0 | 0 | 0 | 5850 | 0 | 0 | 6499.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75STDRN | Replace Storm Water Mains and Outfalls | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACE STORM WATER DRAINS ,MAINS AND OUTFALLS AT RIKERS ISLAND. | 2022 | 6000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75STEAM | Upgrade Steam Lines | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | STEAM LINES UPGRADE. | 2022 | 6000 | 476.83 | 9644 | 0 | 0 | 0 | 0 | 0 | 10120.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SUPFC | Exterior Reconstruction for Support Facilities | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ALL SUPPORT FACILITIES ARE 25 + YEARS OLD AND HAVE SIGNIFICANT DETERIORATION TO THE EXTERIOR ELEMENTS OF THESE PERMANENT STRUCTURES. THIS WORK RELATES TO PROVIDING SAFE AND SECURED ENVIRONMENT FOR DELIVERINGVARIOUS SUPPORT FUNCTIONS TO ALL JAIL FACILITIES. | 2022 | 5800 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75SWITCH | REPLACEMENT OF ELECTRICAL AUTOMATIC TRANSFER SWITCHES | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REPLACEMENT OF ELECTRICAL AUTOMATIC TRANSFER SWITCHES | 2022 | 6600 | 391.48 | 6147 | 0 | 0 | 0 | 0 | 0 | 6538.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75TMTRLR | Design and Installation of new Teams Modular Building | SUPPORT SPACE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DESIGN AND CONSTRUCTION WORK FOR NEW TEAMS MEETING MODULAR BUILDINGS AT RIKERS ISLAND. | 2022 | 6532 | 729.12 | 0 | 0 | 0 | 7795 | 0 | 0 | 8524.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | C75VLAUND | VCBC Laundry System Installation | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | VCBC LAUNDRY SYSTEM INSTALLATION | 2022 | 400 | 1728.48 | 281 | 0 | 0 | 0 | 0 | 0 | 2009.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDAMKC | Hurricane Sandy - AMKC Roof Reconstruction | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ROOF RECONSTRUCTION AT AMKC REQUIRED DUE TO DAMAGE FROM HURRICANE SANDY. ROOF RECONSTRUCTION WILL BE NECESSARY AT THE FOLLOWING AMIKC LOCATIONS: AMKC BUILDING 3, AMKC BUILDING 2 (HOUSING WING 2 AND HOUSING WING 7), THE ROOF OF AMKC MECHANICAL ROOM IN THE AMKC MAIN BUILDING AND ASSOCIATED CORRIDORS. | 2022 | 2375 | 1640.96 | 3 | 0 | 0 | 0 | 0 | 0 | 1643.96 | 4094.39 | 247 | 0 | 0 | 0 | 0 | 0 | 4341.39
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDGRVC | Hurricane Sandy - GRVC Roof Replacement due to Storm Damage | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | ROOF RECONSTRUCTION AT GRVC REQUIRED DUE TO DAMAGE FROM HURRICANE SANDY. | 2022 | 22338 | 0 | 1144 | 0 | 0 | 0 | 0 | 0 | 1144 | 0 | 10297 | 0 | 0 | 0 | 0 | 0 | 10297
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDHART | Hurricane Sandy-harts island Reconstruct from storm damage | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HURRICANE SANDY-HARTS ISLAND RECONSTRUCT FROM STORM DAMAGE | 2022 | 8749 | 1282.94 | 701 | 0 | 0 | 0 | 0 | 0 | 1983.94 | 5597.46 | 6306 | 0 | 0 | 0 | 0 | 0 | 11903.46
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDRNDC | Hurricane Sandy - RNDC Roof Reconstruction | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FUNDING IS REQUIRED TO REPLACE TWO AREAS OF THE ROOF OF RNDC BUILDINGDAMAGED BY HURRICANE SANDY. THE REPLACEMENT WORK IS NEEDED AT THE GYMROOF AND THE ROOF OF THE SOUTHEAST CORNER OF THE ADMINISTRATIVE BUILDING ROOF . | 2022 | 11396 | 373.8 | 0 | 0 | 0 | 0 | 0 | 0 | 373.8 | 2193.24 | 217 | 0 | 0 | 0 | 0 | 0 | 2410.24
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDSHORE | Hurricane Sandy- RI NShoreline Reconstruct from Storm Damage | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECONSTRUCTION OF RI NORTH SHORELINE DUE TO EXTENSIVE DAMAGE FROM HURRICANE SANDY. | 2022 | 33492 | 4180.99 | 1171 | 0 | 0 | 0 | 0 | 0 | 5351.99 | 34190.37 | 14339 | 0 | 0 | 0 | 0 | 0 | 48529.37
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDTRLR | Hurricane Sandy-Relocation of RI Trailers - Storm Damage | SUPPORT SPACE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | THE RI TRAILERS HAVE BEEN EXTENSIVELY DAMAGED DUE TO HURRICANE SANDY AND NEED TO BE RELOCATED. | 2022 | 43579 | 1379.83 | 27 | 0 | 0 | 0 | 0 | 0 | 1406.83 | 7033.65 | 247 | 0 | 0 | 0 | 0 | 0 | 7280.65
20220309 | BRONX | 072 | DEPARTMENT OF CORRECTION | SANDVCBC | Hurricane Sandy - VCBC Reconstruction Due To Storm Damage | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ENGINEERING ASSESMENT DESIGN AND RECONSTRUCTION AREAS DAMAGED AT VCBCINCLUDING MOORING ARMS. ELECTRICAL PARKING LOT, FENCING, AND ROADWAY. | 2022 | 2940 | 69.02 | 267 | 0 | 0 | 0 | 0 | 0 | 336.02 | 216.31 | 2376 | 0 | 0 | 0 | 0 | 0 | 2592.31
20220309 | BRONX | 096 | HUMAN RESOURCES ADMINISTRATION | HR25305RC | 305 Rider Avenue construction | SOCIAL SERVICES BUILDINGS |  | HR-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2022 | 2368 | 0 | 0 | 1249 | 0 | 0 | 0 | 0 | 1249 | 0 | 0 | 645 | 0 | 0 | 0 | 0 | 645
20220309 | BRONX | 096 | HUMAN RESOURCES ADMINISTRATION | HR25TREMC | 555 E Tremont Construction | SOCIAL SERVICES BUILDINGS |  | HR-0025 |  |  |  | 2022 | 824 | 0 | 0 | 543 | 0 | 0 | 0 | 0 | 543 | 0 | 0 | 281 | 0 | 0 | 0 | 0 | 281
20220309 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176-BLR | WCS Bronx Zoo - Boiler Replacement Various Bldgs. | ESSENTIAL RECONSTRUCTION OF FACILITIES | 106 | PV-0176 PV-D176 PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BX ZOO 2300 SOUTHERN BLVD., BRONX NY | REPLACEMENT OF BOILERS IN ZOO BUILDINGS. | 2022 | 5500 | 0 | 0 | 5538 | 0 | 0 | 0 | 0 | 5538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176CES2 | WCS - Bronx Zoo - Switch Gear Phase 2 | ESSENTIAL RECONSTRUCTION OF FACILITIES | 106 107 111 | PV-D176 PV-0176 |  |  | CONSTRUCTION | 2022 | 3320 | 0 | 0 | 1057 | 0 | 825 | 7983 | 0 | 9865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176GELA | WCS - Bronx Zoo - Gelada Exhibit | ESSENTIAL RECONSTRUCTION OF FACILITIES | 106 | PV-X176 PV-D176 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GELADA PROPAGATION ANNEX TO HOUSE A NEW GROUP FO GELADA BABOONS | 2022 | 1500 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176-REP | WCS - Bronx Zoo - Reptile House Facade Restoration | ESSENTIAL RECONSTRUCTION OF FACILITIES | 106 | PV-X176 PV-D176 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | WCS - BRONX ZOO | 2022 | 1872 | 0 | 0 | 0 | 1575 | 300 | 0 | 0 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV176WILD | WCS - Bronx Zoo - Wildlife Exhibit Center | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-D176 PV-X176 |  |  | WCS BRONX ZOO - WILDLIFE EXHIBIT CENTER | 2022 | 5300 | 0 | 0 | 0 | 10100 | 500 | 0 | 0 | 10600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV205GLIB | NYBG - Green Library/Energy Reduction Project | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-D205 PV-0205 |  | 2900 SOUTHERN BLVD. BRONX NY | LIBARY GREEN BUILDING IMPROVEMENTS; HVAC, ROOF | 2022 | 1000 | 0 | 0 | 0 | 0 | 1000 | 9000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV205WOC | NYBG - Worker's Operation Center Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 106 | PV-D205 PV-0205 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 2300 SOUTHERN BLVD. BRONX NY | CREATION AND REVOVATION OF WORKERS OPERATION CENTER | 2022 | 5820 | 0 | 0 | 0 | 0 | 5049 | 5320 | 0 | 10369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV293-EXT | BCHS - Exterior/Interior Rehab and Tech Upgrade | ESSENTIAL RECONSTRUCTION OF FACILITIES | 107 | PV-X293 PV-D467 |  |  | BRONX COUNTY HISTORICAL SOCIETY  EXTERIOR/INTERIOR REHAB & TECHNOLOGY | 2022 | 198 | 0 | 0 | 0 | 0 | 198 | 0 | 0 | 198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464GLYN | WH - Wave Hill - Glyndor Hse. Boiler/Armor Hall AHU | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-D464 PV-0464 PV-X464 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 675 WEST 254TH STREET, BRONX, NY | BOILER REPLACEMENT | 2022 | 987 | 0 | 0 | 0 | 1167 | 0 | 0 | 0 | 1167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464-PAV | WH - Wave Hill - Woodland Pavilion | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-D464 P-D021 PV-X464 |  |  | CONSTRUCTION OF WOODLAND PAVILION. | 2022 | 1350 | 0 | 0 | 0 | 0 | 1600 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 126 | DEPARTMENT OF CULTURAL AFFAIRS | PV464SITE | WH - Wave Hill - Sitewide Pathway Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 108 | PV-D464 PV-0464 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 675 WEST 252ND STREET. BRONX, NY | SITE WIDE PATHWAY REPLACEMENT | 2022 | 550 | 0 | 0 | 0 | 0 | 3699 | 0 | 0 | 3699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | 600FCDRNV | 600 FCD 2nd Fl Renovation | MISCELLANEOUS | 100 | ED-0075 |  |  | RENOVATION OF 2ND FL OF 600 FCD | 2022 | 4500 | 0 | 0 | 1500 | 0 | 3000 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | ARTHURAVE | ARTHUR AVENUE MARKET | MISCELLANEOUS | 100 | ED-0408 ED-X075 ED-D408 ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ARTHUR AVENUE MARKET | 2022 | 1648 | 220.87 | 1271 | 4056 | 0 | 0 | 0 | 0 | 5547.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | EDXHPGEN | Hunts Point Cooperative Market | MARKET DEVELOPMENT | 100 | ED-D408 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HUNTS POINT COOPERATIVE MARKET - TO PURCHASE TWO NEW GENERATORS | 2022 | 3450 | 2737.24 | 0 | 1712 | 0 | 0 | 0 | 0 | 4449.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | FFMDRAIN | New Fulton Fish Market -- Facility Upgrades: New Drainage Sy | MISCELLANEOUS | 100 | ED-D408 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW FULTON FISH MARKET -- FACILITY UPGRADES: NEW DRAINAGE SYSTEM | 2022 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | FREIGHTHP | Freight NYC - Hunts Point Marine Highway | PORT DEVELOPMENT | 100 | ED-0404 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FREIGHT NYC - HUNTS POINT MARINE HIGHWAY - 100K JOBS | 2022 | 25000 | 0 | 0 | 0 | 0 | 2500 | 13500 | 9000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP07-02 | GI - DSGN & CONS OF ROW BIOSWALES & GREENSTREETS IN HP-007 | GREEN INFRASTRUCTURE PROGRAM | 112 | WP-0169 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GI - DESIGN AND CONSTRUCTION OF RIGHTOF WAY BIOSWALES AND STORMAWATERGREENSTREETS AT CSO TRIBUTARY AREA HP-007 IN THE BRONX | 2022 | 23154 | 43921.12 | 881 | 0 | 0 | 0 | 0 | 0 | 44802.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | GXHP14-01 | GI - Green infrastructure in Westchester Creek HP-14 | GREEN INFRASTRUCTURE PROGRAM | 112 | WP-0169 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GI - GREEN INFRASTRUCTURE IN WESTCHESTER CREEK HP-14 | 2022 | 41898 | 20720.73 | 326 | 0 | 0 | 0 | 0 | 0 | 21046.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HOMESTACT | Home Street Properties activation of vacant lots | MISCELLANEOUS | 100 | ED-0075 |  |  | HOME STREET PROPERTIES ACTIVATION OF VACANT LOTS | 2022 | 2000 | 0 | 2163 | 0 | 0 | 0 | 0 | 0 | 2163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPBOILER | HUNTS POINT MEAT MARKET (EDC)--BOILER UPDATES | NEIGHBORHOOD REVITALIZATION | 100 | ED-D408 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HUNTS POINT MEAT MARKET (EDC)--BOILER UPDATES | 2022 | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPPRINGLE | HP Pringle Switch - Electrical Upgrades | MARKET DEVELOPMENT | 100 | ED-0075 |  |  | ELECTRICAL UPGRADES | 2022 | 1000 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500
20220309 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HPRAILSBG | HUNTS POINT RAIL SPUR | NEIGHBORHOOD REVITALIZATION | 100 102 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HUNTS POINT RAIL SPUR | 2022 | 0 | 294.15 | 0 | 0 | 0 | 0 | 5 | 0 | 299.15 | 2679.52 | 21 | 0 | 0 | 10000 | 0 | 0 | 12700.52
20220309 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HTPRODUC2 | Hunts Point Market | MARKET DEVELOPMENT | 102 | ED-X075 ED-D075 ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HUNTS POINT MARKET | 2022 | 1500 | 0 | 192 | 4049 | 6250 | 634 | 0 | 58 | 11183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTMEAT2 | Hunts Point Meat Market 2 | MARKET DEVELOPMENT | 100 | ED-0408 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HUNTS POINT - MEAT MARKET. INFRASTRUCTURE REPAIRS | 2022 | 65000 | 13468.86 | 0 | 9818 | 7894 | 7051 | 0 | 0 | 38231.86 | 0 | 495 | 0 | 0 | 0 | 0 | 0 | 495
20220309 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSAOU2 | Hunts Point AOU-2 and Building G Development | MARKET DEVELOPMENT | 100 | ED-0408 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HUNTS POINT AOU-2 AND BUILDING G DEVELOPMENT | 2022 | 6768 | 1807.14 | 0 | 0 | 992 | 0 | 508 | 3461 | 6768.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | HUNTSFISH | Hunts Point Fish Market | MARKET DEVELOPMENT | 100 | ED-0408 ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HUNTS POINT - FISH MARKET | 2022 | 10000 | 4201.14 | 2000 | 0 | 5779 | 1419 | 0 | 0 | 13399.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LAFFAVELT | Laffayette Avenue Street Lighting | MISCELLANEOUS | 100 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LAFFAYETTE AVENUE STREET LIGHTING | 2022 | 1800 | 939.45 | 861 | 0 | 0 | 0 | 0 | 0 | 1800.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16HPT | HUNTS POINT: MAJOR RENOVATION | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 | LN-0008 LN-D008 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HUNTS POINT: MAJOR RENOVATION | 2022 | 20000 | 1177.76 | 24505 | 2565 | 0 | 0 | 0 | 0 | 28247.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LNEA16MLR | Melrose: Major Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 | LN-0008 LN-D008 LN-X001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MELROSE: MAJOR RENOVATION | 2022 | 20000 | 3956.85 | 23458 | 2739 | 0 | 0 | 0 | 0 | 30153.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | LS-MONTE | Montefiore Biotechnology Accelerated Research Center | MISCELLANEOUS | 100 | ED-0075 |  |  | ALBERT EINSTEIN COLLEGE OF MEDICINE | 2022 | 13000 | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | NFFMSTORG | NEW FULTON FISH MARKET RENOVATION-- REFRIGERATED STORAGE ARE | MISCELLANEOUS | 100 | ED-D408 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW FULTON FISH MARKET RENOVATION-- REFRIGERATED STORAGE AREA AND DRYSTORAGE AREA RENOVATION/CONSTRUCTION | 2022 | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | P-1ORCHPA | Orchard Beach Pavillion & Ancillary Reconstruction | BEACHES AND BOARDWALKS | 100 | P-X245 P-0715 P-D021 P-1018 |  | ORCHARD BEACH | ORCHARD BEACH COMPLETE RENOVATION OF PAVILION & ANCILLARY SPACE | 2022 | 10000 | 6284.31 | 57369 | 0 | 0 | 4000 | 0 | 0 | 67653.31 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
20220309 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | PV471SWA2 | BxMA - South Wing Atrium Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 104 | PV-D471 PV-0471 PV-0467 PV-D467 PV-X471 PV-X467 |  |  | BRONX MUSEUM OF THE ARTS  SOUTH WING ATRIUM RENOVATION | 2022 | 19230 | 0 | 2880 | 0 | 18550 | 0 | 0 | 0 | 21430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHPRX2 | Hunts Point Resiliency Mob-Gen/SP | MISCELLANEOUS | 100 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HUNTS POINT RESILIENCY - MOBILE GENERATORS/SOLAR PANELS | 2022 | 6197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1435.23 | 4762 | 0 | 0 | 0 | 0 | 0 | 6197.23
20220309 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SANDHPRXD | Hunts Point Energy Resiliency Pilot - DR | MISCELLANEOUS | 100 | ED-0075 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HUNTS POINT | 2022 | 40844 | 0 | 0 | 0 | 26000 | 0 | 0 | 23405 | 49405 | 7488.06 | 2437 | 0 | 0 | 0 | 0 | 0 | 9925.06
20220309 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | STHBRXGRN | South Bronx Greenway | NEIGHBORHOOD REVITALIZATION | 100 102 106 109 111 112 | ED-0075 WP-0056 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SOUTH BRONX GREENWAY | 2022 | 0 | 25449.72 | 107 | 0 | 0 | 0 | 0 | 0 | 25556.72 | 7645.33 | 16 | 0 | 0 | 0 | 0 | 0 | 7661.33
20220309 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SWBXINFRA | Southwest Bronx Infrastructure Improvements | NEIGHBORHOOD REVITALIZATION | 100 | ED-0384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SOUTHWEST BRONX INFRASTRUCTURE IMPROVEMENTS | 2022 | 194300 | 48800.21 | 20000 | 0 | 12757 | 15000 | 9946 | 12127 | 118630.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | SWBXLCN | Lower Concourse North | NEIGHBORHOOD REVITALIZATION | 100 | ED-0384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LOWER CONCOURSE NORTH DEVELOPMENT | 2022 | 27800 | 494.34 | 306 | 0 | 0 | 0 | 0 | 0 | 800.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 801 | DEPT OF SMALL BUSINESS SERVICES | VINCEAVE | Vincent Avenue Seawall Rehabilitation | MISCELLANEOUS | 100 | RE-0025 RE-D024 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | VINCENT AVENUE SEAWALL REHAB | 2022 | 2600 | 436.1 | 2300 | 0 | 0 | 0 | 0 | 0 | 2736.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM07PPCR | PELHAM PARKWAY HOUSES - COMMUNITY ROOM UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 111 | HA-X001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | COMMUNITY ROOM UPGRADE | 2022 | 150 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM07VYSE | VYSE AVENUE FRONT ENTRANCE DOORS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 103 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REPLACE FRONT ENTRANCES | 2022 | 1410 | 2671.28 | 873 | 0 | 0 | 0 | 0 | 0 | 3544.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM11CPGP | CLASON POINT PLAYGROUND AND OUTDOOR AREA IMPROVEMENTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 109 | HA-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PLAYGROUND AND OUTDOOR AREA IMPROVEMENTS | 2022 | 50 | 511.98 | 0 | 0 | 0 | 0 | 49 | 0 | 560.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM11DAVC | DAVIDSON/ SITE 166 RES. ASSN SPORTS DOME AND CULINARY PROG. | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 103 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CULINARY KITCHEN | 2022 | 1000 | 1197.45 | 290 | 0 | 0 | 0 | 0 | 0 | 1487.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM13BRPG | BRONX RIVER HOUSES PLAYGROUND RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 109 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | UPGRADE PLAYGROUNDS | 2022 | 250 | 408.48 | 0 | 0 | 0 | 0 | 38 | 0 | 446.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MKGH | MILLBROOK HOUSES SOLAR POWERED GREENHOUSE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 101 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCT A SOLAR POWERED GREENHOUSE | 2022 | 300 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MLBQ | MILLBROOK HOUSES - TWO BARBEQUE AREAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 101 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | TWO BARBEQUE AREAS | 2022 | 300 | 895.48 | 66 | 0 | 0 | 0 | 0 | 0 | 961.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14MRSR | MONROE HOUSES SENIOR CENTER RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 109 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATE SENIOR CENTER | 2022 | 1000 | 2956.54 | 422 | 0 | 0 | 0 | 0 | 0 | 3378.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM14SHPL | STEBBINS AVENUE - HEWITT PLACE PLAYGROUND RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 102 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PLAYGROUND AREA RENOVATION | 2022 | 600 | 771.67 | 79 | 0 | 0 | 0 | 0 | 0 | 850.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM15FOCC | FOREST HOUSES COMMUNITY CENTER GYM AND LOCKER ROOMS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 103 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | UPGRADE GYM AND LOCKER ROOMS | 2022 | 400 | 352.22 | 48 | 0 | 0 | 0 | 0 | 0 | 400.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM15SHGC | STEBBINS AVENUE-HEWITT PLACE INFRASTRUCTURE IMPROVEMENTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 102 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INFRASTRUCTURE IMPROVEMENTS | 2022 | 280 | 559.52 | 0 | 0 | 0 | 0 | 863 | 0 | 1422.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16BSGD | BOSTON SECOR PLAYGROUND RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 112 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | UPGRADE PLAYGROUNDS | 2022 | 300 | 470.05 | 130 | 0 | 0 | 0 | 0 | 0 | 600.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16CLGY | CLAREMONT HOUSES GYM RENOVATION FOR CLAREMONT NEIGHBORHOOD | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 103 | HA-X001 HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CLAREMONT HOUSES GYM RENOVATION FOR CLAREMONT NEIGHBORHOOD CENTER | 2022 | 450 | 0 | 1445 | 0 | 0 | 0 | 0 | 0 | 1445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM16MODC | JAMES MONROE HOUSES RENOVATE COMMUNITY CENTER | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 109 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATE LOCATION AT 816 SOUNDVIEW AVENUE FOR USE OF DAY CARE | 2022 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17FORF | ROOF REPLACEMENT AT FOREST HOUSES | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 103 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROOF REPLACEMENT | 2022 | 11110 | 383.82 | 0 | 0 | 0 | 17297 | 0 | 0 | 17680.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MASC | MORRISANIA SECURITY ENHANCEMENTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 103 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SECURITY ENHANCEMENTS AT MORRISANIA HOUSES | 2022 | 700 | 645.97 | 55 | 0 | 0 | 0 | 0 | 0 | 700.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17MUGR | MURPHY HOUSES GROUNDS RENOVATION | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 105 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | GROUNDS RENOVATION | 2022 | 300 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17PHCC | PATTERSON HOUSES COMMUNITY CENTER REHAB | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 100 | HA-X001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | PATTERSON HOUSES COMMUNITY CENTER REHABILITATION | 2022 | 200 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM17SOSK | BRONXDALE NURSERY AT SOTOMAYOR HOUSES SPRINKLER SYSTEM | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 109 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NSTALL NEW SPRINKLER SYSTEM AT THE BRONXDALE NURSERY SCHOOL | 2022 | 220 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BRCB | BOSTON ROAD SENIOR CENTER ROOF REPLACEMENT | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 100 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BOSTON ROAD SENIOR CENTER ROOF REPLACEMENT | 2022 | 1000 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18BRCC | Bronx River CC: Children's Arts and Science Workshops | LOW TO MODERATE INCOME PUBLIC HOUSING CONSTRUCTION | 100 | HA-X001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BRONX RIVER CC: CHILDREN'S ARTS AND SCIENCE WORKSHOPS | 2022 | 55 | 9.19 | 46 | 0 | 0 | 0 | 0 | 0 | 55.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18CCMH | MELROSE HOUSES CCTV AND LAC | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 101 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | INSTALL CCTV AND LAC | 2022 | 3300 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18COSC | SECURITY CAMERA INSTALLATION AT 372 EAST 152ND ST COURTLANDT | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 101 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SECURITY CAMERA INSTALLATION AT 372 EAST 152ND ST COURTLANDT STREET | 2022 | 50 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18EATR | Renovation of East Tremont Childcare Center Playground | LOW TO MODERATE INCOME PUBLIC HOUSING CONSTRUCTION | 100 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION OF EAST TREMONT CHILDCARE CENTER | 2022 | 500 | 0 | 108 | 0 | 0 | 0 | 0 | 0 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18FSBO | Boiler Replacements at Pelham Parkway | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 111 | HA-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BOILER REPLACEMENTS AT PELHAM PARKWAY | 2022 | 29000 | 0 | 0 | 0 | 0 | 8628 | 0 | 0 | 8628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MBSS | MILL BROOK HOUSES SPRAY SHOWERS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 101 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MILL BROOK HOUSES SPRAY SHOWERS INSTALLATION | 2022 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MRP1 | MORRIS I PLAYGROUND RENOVATION IN FRONT OF 3606 THIRD AVE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 103 | HA-X001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION OF A PLAYGROUND IN FRONT OF 3606 THIRD AVENUE | 2022 | 500 | 65.08 | 210 | 0 | 0 | 0 | 0 | 0 | 275.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18MRPG | MORRIS II PLAYGROUND RENOVATION IN FRONT OF 1481 WASHINGTON | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 103 | HA-X001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MORRIS II HOUSES PLAYGROUND--PLAYGROUND RENOVATION IN FRONT OF 1481 WASHINGTON AVENUE. | 2022 | 500 | 65.08 | 435 | 0 | 0 | 0 | 0 | 0 | 500.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18PCCK | KITCHEN RENOVATION AT PATTERSON HOUSES COMMUNITY CENTER | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 101 | HA-X001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATION OF THE KITCHEN AT PATTERSON HOUSES COMMUNITY CENTER 340 MORRIS AVE | 2022 | 800 | 585.7 | 214 | 0 | 0 | 0 | 0 | 0 | 799.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SMTV | SOTOMAYOR SECURITY ENHANCEMENTS AT 1055 ROSEDALE AVENURE | LOW TO MODERATE INCOME PUBLIC HOUSING CONSTRUCTION | 100 | HA-X001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SOTOMAYOR SECURITY ENHANCEMENTS AT 1055 ROSEDALE AVENURE | 2022 | 1000 | 919.19 | 81 | 0 | 0 | 0 | 0 | 0 | 1000.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SOCC | Sotomayor CC Cornerstone Program - Computer Technology | LOW TO MODERATE INCOME PUBLIC HOUSING CONSTRUCTION | 100 | HA-X001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SOTOMAYOR CC CORNERSTONE PROGRAM - COMPUTER TECHNOLOGY | 2022 | 42 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SOMO | SOTOMAYOR HOUSES/MONTEFIORE BEHAVIOR HC - PSYCH CENTER | LOW TO MODERATE INCOME PUBLIC HOUSING CONSTRUCTION | 100 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SOTOMAYOR HOUSES/MONTEFIORE BEHAVIOR HC - PSYCH CENTER | 2022 | 5500 | 0 | 4250 | 0 | 0 | 0 | 0 | 0 | 4250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18SVCC | Soundview CC Cornerstone Program - Computer Technology | LOW TO MODERATE INCOME PUBLIC HOUSING CONSTRUCTION | 100 | HA-X001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SOUNDVIEW CC CORNERSTONE PROGRAM - COMPUTER TECHNOLOGY | 2022 | 42 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TCCK | THROGGS NECK COMMUNITY C ENTER KITCHEN UPDATE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 110 | HA-X001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NYCHA THROGS NECK ADDITION COMMUNITY CENTER--UPDATE KITCHEN 550 BALCOLM AVENUE. | 2022 | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TCCL | THROGGS NECK COMMUNITY CENTER LIGHTING | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 110 | HA-X001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NYCHA THROGS NECK HOUSES COMMUNITY CENTER--LIGHTING THROUGHOUT FACILITY 550 BALCOM AVENUE. | 2022 | 500 | 305.11 | 195 | 0 | 0 | 0 | 0 | 0 | 500.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM18TNCR | THROGGS NECK COMMUNITY - ROOF RENOVATIONS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 110 | HA-X001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NYCHA THROGS NECK HOUSES COMMUNITY CENTER--NEW ROOF RENOVATIONS 550 BALCOLM AVENUE. | 2022 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19ADEL | ADAMS HOUSES ELEVATOR REPLACEMENT | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 101 | HA-0001 |  |  | REPLACE ELEVATOR AT ADAMS HOUSES | 2022 | 8566 | 357 | 7030 | 0 | 0 | 0 | 0 | 0 | 7387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BESC | BETANCES SENIOR CENTER COURTYARD RENOVATIONS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 100 | HA-X001 |  |  | BETANCES SENIOR CENTER COURTYARD RENOVATIONS | 2022 | 500 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BHSC | BAILEY HOUSES SECURITY CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 107 | HA-D001 |  |  | FUNDING FOR SECURITY CAMERAS | 2022 | 500 | 64 | 436 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BPWS | BUTLER HOUSES PLAYGROUND WATER SPRAYS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 103 | HA-D001 |  |  | PLAYGROUND WATER SPRAY SYSTEMS | 2022 | 200 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19BRSC | BRONX RIVER SENIOR CENTER KITCHEN RENOVATIONS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 100 | HA-X001 HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | BRONX RIVER SENIOR CENTER KITCHEN RENOVATIONS | 2022 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CAGR | CASTLE HILL HOUSES GAS RISER REPLACEMENTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 109 | HA-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | GAS RISER REPLACEMENT | 2022 | 10602 | 565.02 | 0 | 9573 | 0 | 0 | 0 | 0 | 10138.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CASC | EAST 152ND-COURTLANDT AVENUE SECURITY CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 107 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | FUNDING FOR SECURITY CAMERAS | 2022 | 225 | 30 | 195 | 0 | 0 | 0 | 0 | 0 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19CMHP | MOORE HOUSES PLAYGROUND | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 101 | HA-0001 |  |  | FUNDING FOR MOORE HOUSES PLAYGROUND UPGRADE | 2022 | 1200 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MARE | MORRISANIA AIR RIGHTS ELEVATOR REPLACEMENT AT 3135 PARK AVE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 103 | HA-D001 |  |  | ELEVATOR REPLACEMENT AT 3135 PARK AVENUE | 2022 | 2000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19MHSE | MARBLE HILL SECURITY ENHANCEMENTS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 108 | HA-D001 |  |  | MARBLE HILL SECURITY ENHANCEMENTS-INSTALLATION OF SECURITY EQUIPMENT | 2022 | 75 | 13.8 | 61 | 0 | 0 | 0 | 0 | 0 | 74.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19PHBC | PATTERSON HOUSES BASKETBALL COURT UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 101 | HA-D001 |  |  | BASKETBALL COURT UPGRADE | 2022 | 500 | 338.8 | 161 | 0 | 0 | 0 | 0 | 0 | 499.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM19UNSC | 1865 UNIVERSITY AVE- SECURITY CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 105 | HA-D001 |  |  | SECURITY CAMERAS AT 1865 UNIVERSITY AVENUE | 2022 | 121 | 0 | 1206 | 0 | 0 | 0 | 0 | 0 | 1206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20EGCC | EASTCHESTER GARDENS COMMUNITY CENTER UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 111 | HA-0001 |  |  | EASTCHESTER GARDENS COMMUNITY CENTER UPGRADE | 2022 | 3650 | 0 | 0 | 3650 | 0 | 0 | 0 | 0 | 3650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20GMEL | GOUVERNEUR MORRIS- GROUNDS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 103 | HA-D001 |  |  | INSTALLATION OF EXTERIOR LED LIGHTING AT GOUVERNEUR MORRIS HOUSES | 2022 | 250 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MCIE | JAMES MONROE HOUSES- CAMERAS, INSTALLATION, EQUIPMENT | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 109 | HA-D001 |  |  | JAMES MONROE HOUSES- CAMERAS, INSTALLATION, EQUIPMENT | 2022 | 2506 | 0 | 2506 | 0 | 0 | 0 | 0 | 0 | 2506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MHGR | MONTEREY HOUSES-RENOVATIONS TO PLAYGROUND | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 106 | HA-D001 |  |  | NYCHA MONTEREY HOUSES OUTDOOR RENOVATIONS -- FUNDS WILL SUPPORT RENOVATIONS TO THE PLAYGROUND AND BENCHES. | 2022 | 225 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20MLPC | MILLBROOK- LIGHTS, PLAYGROUNDS UPGRADES AND CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 101 | HA-D001 |  |  | INSTALLATION OF LED LIGHTS, PLAYGROUND UPGRADES, AND CAMERAS AT MILLBROOK HOUSES | 2022 | 300 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20PSCC | PARKSIDE COMMUNITY CENTER UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 100 | HA-0001 HA-D001 |  |  | PARKSIDE COMMUNITY CENTER UPGRADE | 2022 | 1700 | 0 | 1869 | 0 | 0 | 0 | 0 | 0 | 1869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM20SEED | SEDGWICK HOUSES ENHANCEMENT ENTRANCE DOORS AND CCTV | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 105 | HA-D001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NYCHA SEDGWICK HOUSES -- 4 ENHANCEMENT ENTRANCE DOORS | 2022 | 880 | 0 | 880 | 0 | 0 | 0 | 0 | 0 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21BRST | BRONX RIVER UNDERGROUND STEAM | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 109 | HA-0001 |  |  | BRONX RIVER UNDERGROUND STEAM | 2022 | 7703 | 0 | 9990 | 0 | 0 | 0 | 0 | 0 | 9990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21EWGR | EDENWALD GAS RISERS #6 | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 112 | HA-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | INSTALLATION OF GAS RISERS #6 | 2022 | 9900 | 0 | 0 | 0 | 0 | 9000 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21HMCC | MONROE HOUSES- COMMUNITY CENTER | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 109 | HA-0001 |  |  | MONROE HOUSES- COMMUNITY CENTER | 2022 | 5738 | 0 | 0 | 5738 | 0 | 0 | 0 | 0 | 5738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHCC | UPGRADE COMMUNITY CENTER MOTT HAVEN | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 101 | HA-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | UPGRADE COMMUNITY CENTER MOTT HAVEN | 2022 | 1600 | 0 | 320 | 1280 | 0 | 0 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MHOA | NYCHA MONTEREY HOUSES-OUTDOOR AREA RENOVATIONS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 106 | HA-D001 |  |  | NYCHA MONTEREY HOUSES-OUTDOOR AREA RENOVATIONS | 2022 | 225 | 0 | 518 | 0 | 0 | 0 | 0 | 0 | 518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MICC | UPGRADE COMMUNITY CENTER MITCHEL | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 101 | HA-0001 |  |  | UPGRADE COMMUNITY CENTER MITCHEL | 2022 | 4400 | 0 | 880 | 3520 | 0 | 0 | 0 | 0 | 4400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MLCC | UPGRADE COMMUNITY CENTER MILLBROOK | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 101 | HA-0001 |  |  | UPGRADE COMMUNITY CENTER MILLBROOK | 2022 | 1800 | 0 | 360 | 1440 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21MMMP | UPGRADES TO MILL BROOK, MITCHELL, MOTT HAVEN AND PATTERSON | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 101 | HA-0001 |  |  | UPGRADES TO MILL BROOK, MITCHELL, MOTT HAVEN AND PATTERSON : LIGHTING, CAMERAS, PLAY EQUIPMENT | 2022 | 13000 | 0 | 2600 | 10400 | 0 | 0 | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21PHCC | UPGRADE COMMUNITY CENTER PATTERSON | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 101 | HA-0001 |  |  | UPGRADE COMMUNITY CENTER PATTERSON | 2022 | 5100 | 0 | 1020 | 4080 | 0 | 0 | 0 | 0 | 5100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21SORF | SOTOMAYOR BRICKS AND ROOFS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 109 | HA-0001 |  |  | SOTOMAYOR HOUSES BRICKS AND ROOFS | 2022 | 24712 | 0 | 14259 | 0 | 0 | 0 | 0 | 0 | 14259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM21WMCI | SECURITY CAMERA INSTALLATION AT WEBSTER MORRISANIA | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 103 | HA-D001 |  |  | NYCHA WEBSTER MORRISANIA-FY19 SHORTFALL OF SECURITY CAMERA INSTALLATION | 2022 | 800 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22BPGU | BUTLER HOUSES- PLAYGROUND UPGRADE | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 103 | HA-D001 |  |  | NYCHA BUTLER HOUSES -- PLAYGROUND UPGRADE | 2022 | 800 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22FHRF | FOREST HOUSES- SEBNC- ROOF REPLACEMENT | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 103 | HA-D001 |  |  | SOUTHEAST BRONX NEIGHBORHOOD CENTERS (SEBNC) @ NYCHA FOREST HOUSES --ROOF REPLACEMENT | 2022 | 940 | 0 | 940 | 0 | 0 | 0 | 0 | 0 | 940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22MHIL | MONTEREY HOUSES- INTERIOR LIGHTING & CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 106 | HA-D001 |  |  | MONTEREY HOUSES - NYCHA -- INSTALL NEW INTERIOR LIGHTING ON EVERY FLOOR, AND INSTALL SECURITY CAMERAS ON EVERY FLOOR | 2022 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22MHPF | MARBLE HILL HOUSES- PERIMETER FENCING | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 108 | HA-D001 |  |  | NYCHA MARBLE HILL DEVELOPMENT -- CONSTRUCTION/RENOVATION: PERIMETER FENCING | 2022 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22MHRC | MARBLE HILL- TECHNOLOFY UPGRADE - ROOF CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 108 | HA-D001 |  |  | NYCHA MARBLE HILL DEVELOPMENT -- TECHONOLY UPGRADE: ROOF LANDING CAMERAS FOR BUILDING 11 (210 W 230 ST.) | 2022 | 200 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22MHTU | MARBLE HILL HOUSES- TECHNOLOGY UPGRADE LED LIGHTING | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 108 | HA-D001 |  |  | NYCHA MARBLE HILL DEVELOPMENT -- TECHONOLY UPGRADE: LED/CANOPY LIGHTING FOR THE MANHATTAN BUILDINGS | 2022 | 70 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22MUIL | MURPHY HOUSES- INTERIOR LIGHTING & CAMERAS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 106 | HA-D001 |  |  | NYCHA MURPHY HOUSES - 1010 E. 178TH STREET -- INTERIOR SECURITY CAMERAS, AND INTERIOR LIGHTING | 2022 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22PHIL | PARKSIDE HOUSES- INERIOR LIGHTING | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 111 | HA-D001 |  |  | PARKSIDE HOUSES - NYCHA -- INSTALL NEW INTERIOR LIGHTING ON EVERY FLOOR, AND INSTALL SECURITY CAMERAS ON EVERY FLOOR (APPROX. 10 BUILDINGS) | 2022 | 1250 | 0 | 1250 | 1250 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SMRA | SAINT MARYS HOUSES- ADA RAMP | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 101 | HA-D001 |  |  | NYCHA SAINT MARY'S HOUSES -- ADA RAMP | 2022 | 350 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM22SREB | SOUNDVIEW HOUSES - EXTERNAL BOILER | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 109 | HA-D001 |  |  | NYCHA- SOUNDVIEW HOUSES -- FUNDS WILL BE TO REMOVE THE EXTERNAL BOILER | 2022 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 806 | HOUSING PRESERVATION AND DEVEL | HAM24CHBR | CASTLE HILL BATHROOMS | LOW TO MODERATE INCOME PUBLIC HOUSING UPGRADE | 109 | HA-0001 |  |  | INSTALLATION OF CASTLE HILL BATHROOMS | 2022 | 42800 | 0 | 0 | 0 | 500 | 7000 | 15465 | 15944 | 38909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82BERGN | BERGEN BUILDING RENOVATION - 1932 ARTHUR AVE., BRONX, NY | CLINIC RENOVATION AND REHABILITATION |  | HL-0082 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | GENERAL CONSTRUCTION, ELECTRICAL POWER, LIGHTING & PLUMBING | 2022 | 800 | 1224.65 | 379 | 0 | 0 | 0 | 0 | 0 | 1603.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82GLEEB | BUILDING RENOVATION - 2527 GLEBE AVE, BRONX, NY | CLINIC RENOVATION AND REHABILITATION |  | HL-0082 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BUILDING ROOFING AND EXTERIOR RENOVATION | 2022 | 2500 | 0 | 0 | 0 | 800 | 3200 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82MORHC | Morrisania Health Center interior renovation | CLINIC RENOVATION AND REHABILITATION |  | HL-0082 |  |  | MORRISANIA HEALTH CENTER INTERIOR RENOVATION | 2022 | 4700 | 0 | 0 | 0 | 0 | 0 | 1496 | 1000 | 2496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 816 | DEPARTMENT OF HEALTH AND MENTAL HYGIENE | HL82ZERGA | LEASE SPACE RENOVATION - 1235 ZEREGA AVENUE, BRONX, NY | ADMINISTRATION |  | HL-0082 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | LEASE SPACE RENOVATION | 2022 | 2000 | 3457.41 | 199 | 0 | 0 | 0 | 0 | 0 | 3656.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 02201801 | JACOBI: BUILDING #4 RENOVATIONS | ROUTINE RECONSTRUCTION |  | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 1400 PELHAM PARKWAY SOUTH, BRONX, NY 10461 | THIS PROJECT CONSISTS OF THE NECESSARY RELOCATION OF EXISTING JACOBI DEPARTMENTS TO NEW AREAS IN ORDER TO RENOVATE THE VACATED SPACE ON MULTIPLE FLOORS TO HOUSE CENTRAL OFFICE AND EITS ADMINISTRATIVE AND OPERATIONAL UNITS. | 2022 | 7638 | 6728.18 | 0 | 0 | 360 | 0 | 0 | 0 | 7088.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 20201501 | BELVIS: PEDIATRIC SUITE MODERNIZATION | ROUTINE RECONSTRUCTION | 101 | HO-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 545 EAST 142ND STREET, BRONX, BY 10454 | MODERNIZE PEDIATRIC SUITE, INCLUDING NEW PHYSICIAN AND NURSE WORKSTATIONS, EXPANDED SEATING FOR RECEPTION AND SUB-WAITING AREAS, AND RENOVATION OF PUBLIC TOILETS. | 2022 | 92 | 0 | 0 | 0 | 0 | 0 | 92 | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21201601 | JACOBI: LOCAL LAW 11 COMPLIANCE | ROUTINE RECONSTRUCTION | 111 | HO-0214 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 1400 PELHAM PARKWAY SOUTH, BRONX NY 10461 | THE PURPOSE OF THIS PROJECT IS TO RENOVATE BUILDINGS AT JACOBI HOSPITAL CENTER USING LOCAL LAW 11- FUNDS FOR LOCAL LAW 11 COMPLIANCE. | 2022 | 2034 | 266.04 | 4682 | 0 | 0 | 0 | 0 | 0 | 4948.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21201751 | JACOBI: PURCHASE NEW MRI & Construction | ROUTINE RECONSTRUCTION | 111 | HO-0214 HO-X002 HO-D003 |  | 1400 PELHAM PARKWAY SOUTH, BRONX, NY 10461 |  | 2022 | 5575 | 0 | 150 | 5425 | 0 | 0 | 0 | 0 | 5575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21201840 | JACOBI: CARDIAC CATHETERIZATION LAB UPGRADE | ROUTINE RECONSTRUCTION |  | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 1400 PELHAM PARKWAY SOUTH, BRONX, NY 10461 |  | 2022 | 3097 | 2525.22 | 457 | 114 | 0 | 0 | 0 | 0 | 3096.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202001 | JACOBI CHILLERS FOR MRI UNIT | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 1400 PELHAM PKWAY SOUTH, BRONX, NY 10461 |  | 2022 | 119 | 0 | 119 | 0 | 0 | 0 | 0 | 0 | 119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202004 | JACOBI: WELLNESS GYM | ROUTINE RECONSTRUCTION |  | HO-X002 HO-D003 HO-0214 |  | 1400 PELHAM PKWY SOUTH, BRONX | RENOVATE AND UPGRADE JACOBI'S WELLNESS CENTER LOCATED ON THE CELLAR LEVEL OF BUILDING 4." | 2022 | 500 | 0 | 3715 | 1000 | 0 | 0 | 0 | 0 | 4715 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202101 | JACOBI: HVAC SYSTEM LAB UPGRADE | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 1400 PELHAM PARKWAY SOUTH, BRONX NY 10461 | HVAC SYSTEM LAB UPGRADE | 2022 | 1547 | 5.84 | 1541 | 0 | 0 | 0 | 0 | 0 | 1546.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202108 | JACOBI COMPOUNDING USP 797/800 COMPLIANCE | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 1400 PELHAM PARKWAY SOUTH, BRONX, NY 10461 | NYC HEALTH + HOSPITALS.JACOBI. COMPOUNDING USP 797/800 COMPLIANCE | 2022 | 3663 | 0 | 350 | 3163 | 150 | 0 | 0 | 0 | 3663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202109 | JACOBI: OBGYN 7S/7W | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 1400 PELHAM PARKWAY SOUTH, BRONX, NY | NYC HEALTH + HOSPITALS/JACOBI. POST PARTUM RENOVATION BLDG 1 | 2022 | 15000 | 0 | 1500 | 12200 | 0 | 0 | 0 | 0 | 13700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202110 | JACOBI: 11E OR ROOMS UPGRADE | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 1400 PELHAM PARKWAY SOUTH, BRONX, NY | NYC HEALTH + HOSPITALS/JACOBI. 11E OR ROOMS UPGRADE | 2022 | 15000 | 0 | 1500 | 12200 | 0 | 0 | 0 | 0 | 13700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202111 | JACOBI: SPRINKLER SYSTEM UPGRADE BUILDING 4 | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 1400 PELHAM PARKWAY SOUTH, BRONX, NY | NYC HEALTH + HOSPITALS/JACOBI. SPRINKLER SYSTEM UPGRADE BUILDING 4 | 2022 | 15000 | 0 | 1500 | 13500 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 21202112 | JACOBI: FIRE ALARM SYSTEM BLDG 1 | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 1400 PELHAM PARKWAY SOUTH | FIRE ALARM SYSTEM IN BUILDING 1 | 2022 | 10000 | 0 | 1000 | 9000 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24201502 | NCB: OB/GYN NURSING UNIT UPGRADE | ROUTINE RECONSTRUCTION |  | HO-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | RENOVATE THE NURSING AND DELIVERY SUITE AT NORTH CENTRAL BRONX HOSPITAL AND RE-OPEN SERVICE IN FALL OF 2014, | 2022 | 1200 | 0 | 0 | 0 | 83 | 0 | 0 | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24201610 | RENOVATE TREMONT HEALTH CLINIC | ROUTINE RECONSTRUCTION | 106 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 1826 ARTHUR AVENUE, BRONX, NY 10457 | RENOVATE TREMONT HEALTH CLINIC IN ORDER TO EXPAND PRIMARY CARE HEALTHSERVICES. | 2022 | 841 | 1186.08 | 0 | 0 | 54 | 0 | 0 | 0 | 1240.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24201920 | NCB: REPLACE DISHWASHER | MAJOR MEDICAL EQUIPMENT |  | HO-0214 |  | 3424 KOSSUTH AVENUE, BRONX, NEW YORK 10467 |  | 2022 | 192 | 157.38 | 55 | 0 | 0 | 0 | 0 | 0 | 212.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202001 | NCB - ELEVATOR UPGRADE | ROUTINE RECONSTRUCTION |  | HO-X002 HO-D003 |  | 3424 KOSSUTH AVENUE | NORTH CENTRAL BRONX HOSPITAL - ELEVATOR UPGRADE | 2022 | 900 | 5 | 1790 | 0 | 0 | 0 | 0 | 0 | 1795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202104 | NCB OR RENOVATIONS | ROUTINE RECONSTRUCTION |  | HO-0214 |  |  | NCB OR RENOVATION | 2022 | 3600 | 0 | 360 | 3240 | 0 | 0 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202202 | NCB: RADIOLOGY DR ROOM | ROUTINE RECONSTRUCTION |  | HO-D003 |  | 3424 KOSSUTH AVE, BRONX, NY 10467 | N/A | 2022 | 502 | 0 | 100 | 402 | 0 | 0 | 0 | 0 | 502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202204 | NCB OUTPOSTED UNITS | ROUTINE RECONSTRUCTION |  | HO-0341 |  | 3424 KOSSUTH AVENUE, BRONX, NEW YORK 10467 | NCB OUTPOSTED UNITS (3424 KOSSUTH AVENUE, BRONX, NEW YORK 10467) | 2022 | 0 | 0 | 18000 | 20000 | 202000 | 0 | 0 | 0 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202205 | NCB: SPRINKLER UPGRADE | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 3424 KOSSUTH AVENUE, BRONX, NY 10467 | UPGRADE BUILDING FIRE SPRINKLER | 2022 | 9000 | 0 | 1500 | 3500 | 4000 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202206 | NCB: EMERGENCY POWER SEPARATION | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 3424 KOSSUTH AVENUE, BRONX, NY 10467 | TO UPGRADE EMERGENCY POWER SEPARATION | 2022 | 18000 | 0 | 1000 | 6000 | 6000 | 5000 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202207 | NCB: SPRINKLER SYSTEM UPGRADE | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 3424 KOSSUTH AVENUE, BRONX, NY 10467 | UPGRADE SPINKLKER SYSTEM | 2022 | 16000 | 0 | 1500 | 3500 | 5500 | 5500 | 0 | 0 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 24202208 | NCB: BOILER REPLACEMENT | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 3424 KOSSUTH AVE, BRONX NY 10467 | NYC HEALTH + HOSPITALS/ NCB (3424 KOSSUTH AVENUE, BRONX, NEW YORK 10467) BOILER REPLACEMENT | 2022 | 25000 | 0 | 1500 | 23500 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201401 | LINCOLN: RENOVATE ADOLESCENT CLINIC | ROUTINE RECONSTRUCTION | 101 | HO-X002 HO-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 234 149TH STREET, BRONX, NY 10451 | RENOVATE AND MODERNIZE ADOLESCENT AND PEDIATRIC CLINIC AT LINCOLN MEDICAL CENTER. | 2022 | 1248 | 1.95 | 0 | 0 | 338 | 0 | 908 | 0 | 1247.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201601 | LINCOLN: COOLING TOWER REPLACEMENT | ROUTINE RECONSTRUCTION | 101 | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 234 EAST 149TH STREET, BRONX, NY 10451 | REPLACE COOLING TOWER AT LINCOLN MEDICAL & MENTAL HEALTH CENTER | 2022 | 11235 | 10626.43 | 0 | 0 | 609 | 0 | 0 | 0 | 11235.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201602 | LINCOLN: REPLACE UNDERGROUND FUEL TANKS | ROUTINE RECONSTRUCTION |  | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 234 EAST 149TH STREET, BRONX, NY 10451 | REPLACE UNDERGROUND FUEL TANKS AT LINCOLN MEDICAL & MENTAL HEALTH CENTER | 2022 | 9834 | 18468.04 | 0 | 1147 | 0 | 0 | 0 | 0 | 19615.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201604 | LINCOLN: EXTERIOR FACADE RESTORATION - LL11 COMPLIANCE | ROUTINE RECONSTRUCTION |  | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 234 EAST 149TH STREET, BRONX, NY 10451 | RESTORE EXTERIOR FACADE TO COMPLY WITH LOCAL LAW 11 GUIDELINES. | 2022 | 335 | 0 | 0 | 335 | 0 | 0 | 0 | 0 | 335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201701 | LINCOLN: EES UPGRADE | ROUTINE RECONSTRUCTION |  | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 234 EAST 149TH STREET, BRONX, NY 10451 | UPGRADE THE ELECTRICAL PANELS AT LINCOLN MEDICAL & MENTAL HEALTH CENTER. | 2022 | 945 | 5400.24 | 403 | 500 | 0 | 0 | 0 | 0 | 6303.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201806 | LINCOLN: REPLACEMENT OF GENERATORS B1 AND B2 & 6 RADIATORS | ROUTINE RECONSTRUCTION |  | HO-0214 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 234 EAST 149TH STREET, BRONX, NY 10451 | NYC HEALTH + HOSPITALS ¦ LINCOLN: REPLACEMENT OF GENERATORS B1 AND B2& 6 RADIATORS | 2022 | 3900 | 82 | 4961 | 0 | 0 | 0 | 0 | 0 | 5043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201901 | LINCOLN: RETAIL PHARMACY RENOVATION | ROUTINE RECONSTRUCTION |  | HO-0214 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | EAST 149TH STREET, BRONX, NY 10451 | RETAIL PHARMACY RENOVATION AT LINCOLN MEDICAL & MENTAL HEALTH CENTER | 2022 | 686 | 610.11 | 0 | 201 | 0 | 0 | 0 | 0 | 811.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25201942 | LINCOLN: PURCHASE MRI & CONSTRUCT SUITE | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 234 EAST 149TH STREET, BRONX, NY 10451 |  | 2022 | 2173 | 0 | 173 | 2000 | 0 | 0 | 0 | 0 | 2173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202001 | LINCOLN CONSTRUCT INPATIENT PHARMACY VAULT | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 234 EAST 149TH STREET, BRONX, NY 10451 | LINCOLN MEDICAL & MENTAL HEALTH CENTER: CONSTRUCT INPATIENT PHARMACY VAULT | 2022 | 236 | 0 | 0 | 236 | 0 | 0 | 0 | 0 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202002 | LINCOLN MEDICAL CENTER - DEVELOP A BRIDGE CLINIC | ROUTINE RECONSTRUCTION |  | HO-X002 |  | 234 EAST 149TH STREET, BRONX, NY 10451 | LINCOLN MEDICAL CENTER - DEVELOP A BRIDGE CLINIC | 2022 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202003 | LINCOLN: INSTALLATION OF ENTRANCE TURNSTILES | ROUTINE RECONSTRUCTION |  | HO-0214 |  | EAST 149TH STREET | NA | 2022 | 515 | 0 | 515 | 0 | 0 | 0 | 0 | 0 | 515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202106 | LINCOLN PHARMACY COMPOUNDING USP 797/800 COMPLIANCE | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 234 E 194TH STREET, BRONX, NY 10451 | NYC HEALTH + HOSPITALS/LINCOLN COMPOUNDING USP 797/800 COMPLIANCE | 2022 | 4026 | 0 | 426 | 3410 | 190 | 0 | 0 | 0 | 4026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202201 | LINCOLN MAIN ENTRANCE AND PLAZA RENOVATION | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 234 EAST 149TH STREET, BRONX, NY 10451 | NYC HEALTH + HOSPITALS/ LINCOLN (234 EAST 149TH STREET, BRONX, NY) MAIN ENTRANCE AND PLAZA RENOVATION | 2022 | 3000 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202202 | LINCOLN FIRE ALARM SYSTEM UPGRADE | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 234 EAST 149TH STREET, BRONX, NY 10451 | LINCOLN HOSPITAL (234 EAST 149TH STREET, BRONX, NEW YORK) FIRE ALARM SYSTEM UPGRADE | 2022 | 1200 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202203H | LIN: PARKING GARAGE RENOVATION | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 234 EAST 149 STREET | RENOVATE PARKING GARAGE | 2022 | 5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 25202204 | LINCOLN: LOADING DOCK & UNDERGROUND DRAINAGE RECON | ROUTINE RECONSTRUCTION |  | HO-0214 |  | 234 EAST 149TH STREET, BRONX, NY 10451 | LOADING DOCK 7 UNDERGROUND DRAINAGE RECONNYC HEALTH+HOSPITALS/ LINCOLN | 2022 | 17650 | 0 | 0 | 7650 | 10000 | 0 | 0 | 0 | 17650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 42201301 | MORRISANIA: RENOVATE DENTAL SUITE | ROUTINE RECONSTRUCTION | 104 | HO-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 1225 GERARD AVENUE, BRONX, NY 10452 | THE DENTAL SUITE AT MORRISANIA D&TC IS IN NEED OF RENOVATION AND NEW EXAM CHAIRS. | 2022 | 345 | 0 | 0 | 0 | 0 | 0 | 345 | 0 | 345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | 42201515 | MORRISANIA: RENOVATE WOMEN'S HEALTH SERVICES - RADIOLOGY | ROUTINE RECONSTRUCTION | 104 | HO-D003 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 1225 GERARD AVENUE, BRONX, NY 10452 | RECONIGURE EXISTING WOMEN'S HEALTH SERVICES/RADIOLOGY DEPARTMENT TO MAKE SERVICES ACCESSIBLE FOR WOMEN WITH DISABILITIES. | 2022 | 588 | 742.32 | 0 | 0 | 0 | 0 | 113 | 0 | 855.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | ACEHHC409 | LINCOLN ENERGY UPGRADE | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT |  | HO-0214 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ENERGY UPGRADE OF TWENTY (20) AIR HANDLER UNITS. UPGRADE OF FLOURESCENT FIXTURES WITH SUPER EFFICIENNT LED RETROFITS. | 2022 | 13495 | 12302.12 | 0 | 1193 | 0 | 0 | 0 | 0 | 13495.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | ACEHHC606 | JMC ENERGY CONSERVATION MEASURES | ROUTINE RECONSTRUCTION |  | HO-0214 PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 1400 PELHAM PARKWAY SOUTH, BRONX, NY 10461 | ENERGY CONSERVATION MEASURES AT JACOBI MEDICAL CENTER | 2022 | 11051 | 10273.47 | 175 | 602 | 0 | 0 | 0 | 0 | 11050.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | ACEHHC901 | LINCOLN ENERGY UPGRADES PHASE 2 | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 101 | PU-0025 HO-0214 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ENERGY UPGRADES AT LINCOLN HOSPITAL PHASE 2 | 2022 | 27000 | 25673.43 | 2042 | 0 | 0 | 0 | 0 | 0 | 27715.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 819 | HEALTH AND HOSPITALS CORP | TKYHHC905 | NCB ENERGY EFFICIENY MEASURES | ROUTINE RECONSTRUCTION |  | HO-0214 PU-0025 |  | 3424 KOSSUTH AVE., BRONX NY 10467 | NYC H+H/NCB ENERGY EFFICIENCY MEASURES. THIS PROJECT INCLUDES THE UPGRADE OF THE VENTILATION SYSTEM, DOMESTIC HOT WATER SYSTEM, WINDOWS, LIGHTING, STEAM DISTRIBUTION AND ELEVATORS. | 2022 | 38217 | 0 | 1612 | 36605 | 0 | 0 | 0 | 0 | 38217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | 138BRIDGE | Dist WM in E 138 St Bridge btwn Exterior St & Gerard Ave, BX | AUGMENTATION OF WATER SUPPLY SYSTEMS | 101 | WM-0001 |  |  | TO IMPROVE WATER DISTRIBUTION SYSTEM AND WATER QUALITY-BETTERMENT FORNEW 12 INCH STEEL WATER MAIN ON EAST 138TH STREET BRIDGE AND 12 INCH DUCTILE IRON WATER MAIN AT BRIDGE APPROACH THAT TIED INTO THE EXISTING 12 INCH WATER MAIN IN EXTERIOR STREET AND 20 INCH WATER MAIN IN GERARD AVENUE. | 2022 | 370 | 0 | 370 | 0 | 0 | 0 | 0 | 0 | 370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | BBJ-X | Comb SE Rplmt extens & WM rplmt E 142 St & Southern Blvd, BX | AUGMENTATION OF WATER SUPPLY SYSTEMS | 101 | WM-0001 |  |  | THIS PROJECT CALLS FOR COMBINED SEWER REPLACEMENT AND EXTENSION AND WATER MAIN REPLACEMENT IN EAST 142ND STREET AND SOUTHERN BOULEVARD. | 2022 | 2195 | 0 | 0 | 0 | 0 | 2195 | 0 | 0 | 2195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-590 | Jerome Park Gate House #7 Sluice Gate and Operator Replacmnt | WATER QUALITY PRESERVATION | 107 | WM-0105 |  |  | JEROME PARK GATE HOUSE #7 SLUICE GATE & OPERATOR REPLACEMENT | 2022 | 3000 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-604 | Croton Filtration Optimization | CROTON FILTER PROJECT | 100 | WM-0011 |  |  | CROTON FILTATION PLANT WRAP UP ITEMS | 2022 | 2300 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-M&A | MITIGATION AND AMENITIES FOR WTP | CROTON FILTER PROJECT | 107 108 | WM-0011 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | MITIGATION AND AMENITIES FOR WTP (IN CONJUNCTION WITH HED-545) | 2022 | 44386 | 0 | 0 | 0 | 0 | 0 | 0 | 23386 | 23386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CRO-NCA | NEW CROTON AQUEDUCT | CROTON FILTER PROJECT | 107 108 | WM-0011 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NEW CROTON AQUEDUCT | 2022 | 116162 | 176059 | 149 | 0 | 0 | 0 | 0 | 0 | 176208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-BX-LTP | BRONX RIVER LONG TERM CONTROL PLAN FOR CSO ABATEMENT | WATER QUALITY MANDATES | 100 | WP-0169 |  |  | CITY-WIDE LONG TERM CONTROL PLAN FOR COMBINED SEWER OVERFLOW ABATEMENT | 2022 | 146200 | 17311.58 | 159 | 0 | 17600 | 136618 | 0 | 0 | 171688.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CS-ER-WCM | WESTCHESTER CSO MODIFICATIONS | WATER QUALITY MANDATES | 100 | WP-0169 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WESTCHESTER CREEK CSO MODIFICATION @EAST RIVER | 2022 | 48000 | 32971.08 | 907 | 0 | 0 | 0 | 0 | 0 | 33878.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | CSO-HR-DF | CSO HUTCHINSON RIVER DISINFECTION FACILITY | WATER QUALITY MANDATES | 100 | WP-0169 |  |  | CSO HUTCHINSON RIVER OUTFALL & DISINFECTION | 2022 | 131000 | 14472.28 | 0 | 0 | 0 | 0 | 20000 | 190000 | 224472.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | EC-SEX24 | Reconstruction of Existing Sewers, The Bronx | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 100 | SE-0002X EP-0007 |  |  | RECONSTRUCTION OF EXISTING SEWERS, THE BRONX. THIS IS A 1 YEAR CONTRACT. THE TARGETED START DATE FOR THIS CONTRACT IS AS SOON AS THE PREVIOUS CONTRACT, EC-SEX23, EXPIRES | 2022 | 7122 | 0 | 0 | 0 | 6500 | 0 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-BX-PP | GI - POROUS PAVEMENT INSTALLATIONS, BRONX | GREEN INFRASTRUCTURE PROGRAM | 100 | WP-0169 |  |  | GI - INSTALLATION OF POROUS PAVEMENT IN THE BRONX. | 2022 | 49500 | 0 | 0 | 49500 | 0 | 0 | 0 | 0 | 49500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-CD11 | GI - CONSTRUCTION OF BIOSWALES IN CITY COUNCIL DISTRICT 11 | GREEN INFRASTRUCTURE PROGRAM | 100 | WP-D169 |  |  | GREEN INFRASTRUCTURE CONSTRUCTION OF BIOSWALES IN CITY COUNCIL DISTRICT 11, BRONX | 2022 | 165 | 0 | 165 | 0 | 0 | 0 | 0 | 0 | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | GI-TIBBET | GI - TIBBETS BROOK AND VAN CORTLAND LAKE IMPROVEMENTS | GREEN INFRASTRUCTURE PROGRAM | 100 | WP-0169 P-1018 |  |  | THE SCOPE OF WORK FOR THIS PROJECT WILL PRODUCE THE DESIGNS NECESSARYTO IMPLEMENT THE PROJECT IN ACCORDANCE WITH THE LTCP AND COMMITMENTS MADE TO THE HARLEM RIVER WATERSHED STAKEHOLDERS. THE PROPOSED PROJECTWOULD REROUTE FLOW INTO VAN CORTLANDT LAKE FROM ITS CURRENT PATH THROUGH THE BROADWAY SEWER TO A DAY LIGHTED STREAM ALONG THE FORMER CSX RIGHT-OF-WAY. | 2022 | 124355 | 0 | 0 | 0 | 29235 | 95120 | 0 | 0 | 124355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HBBA24181 | Replacement of WM Infra on E 188 Street, Bronx | AUGMENTATION OF WATER SUPPLY SYSTEMS | 106 | WM-0001 |  |  | REPLACEMENT/INSTALLATION OF WATER MAIN INFRASTRUCTURE TO CONNECT WITHNYC DOTS PROJECT TO UPZIDE THE WATER MAIN ON E 188 STREET BRIDGE OVERMETRO NORTH RAILROAD IN THE BRONX. | 2022 | 983 | 0 | 983 | 0 | 0 | 0 | 0 | 0 | 983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-545 | CROTON FILTRATION PLANT | CROTON FILTER PROJECT | 107 108 | WM-0011 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | THE BRONX | CONSTRUCTION OF CROTON FILTRATION PLANT WRAP UP | 2022 | 1689115 | 2883859.11 | 5260 | 14 | 0 | 0 | 0 | 0 | 2889133.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-581 | Dist WM rplmt in Mace Ave btwn Olinville & Cruger Ave, BX | AUGMENTATION OF WATER SUPPLY SYSTEMS | 100 | WM-0001 |  |  | DISTRIBUTION WATER MAIN REPLACEMENT WORK IN MACE AVENUE BETWEEN OLINVILLE AVENUE & CRUGER AVENIE, BOROUGH OF BRONX | 2022 | 10953 | 0 | 0 | 9840 | 0 | 0 | 0 | 0 | 9840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED583 | Trunk & Dist WM work on W 177 St, Bronx | TRUNK AND DISTRIBUTION MAIN EXTENSION | 105 | SE-0002X WM-0001 WM-0006 |  |  | TRUNK AND DISTRIBUTION WORK WATER MAIN ON W 177 STREET IN THE BRONX.NEW TRUNK AND DISTRIBUTION WORK ARE PROPOSED BY DISTRIBUTION PROJECTX2020-31 | 2022 | 21000 | 0 | 0 | 0 | 0 | 22391 | 0 | 0 | 22391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED585 | New Trunk WM install from W 181 st & Jerome Ave, Bronx | AUGMENTATION OF WATER SUPPLY SYSTEMS | 105 | SE-0002X WM-0001 WM-0006 |  |  | NEW TRUNK WATER MAIN INSTALLATION FROM THE INTERSECTION OF WEST 181STSTREET AND JEROME AVE TO THE INTERSECTION OF EAST 180TH STREET AND GRAND CONCOURSE AS WELL AS VARIOUS DISTRIBUTION MAIN WORK IN THE BRONX. | 2022 | 16014 | 0 | 0 | 0 | 0 | 13925 | 0 | 0 | 13925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HED-CROOS | CROTON FILTRATION PLANT - OFF-SITE FACILITIES | CROTON FILTER PROJECT | 107 108 | WM-0011 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CROTON FILTRATION PLANT - OFF-SITE FACILITIES | 2022 | 168500 | 160676.83 | 274 | 0 | 0 | 0 | 0 | 0 | 160950.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-238-L | REPLACEMENT OF THE DIGESTER @ THE HUNTS POINT WWTP | PLANT UPGRADING AND RECONSTRUCTION | 100 | WP-0112 |  | COSTER STREET AND RYAWA AVENUE, BRONX, N.Y. 10474 | REPLACEMENT OF THE DIGESTER AT THE HUNTS POINT WWTP | 2022 | 100000 | 26508.98 | 340031 | 0 | 0 | 0 | 0 | 0 | 366539.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-239-L | RECONSTRUCT SLUDGE HANDLING EQUIPMENT @ HUNTS POINT WWTP | PLANT UPGRADING AND RECONSTRUCTION | 100 102 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | COSTER STREET & RYAWA AVENUE, BRONX, N.Y. 10474 | RECONSTRUCT SLUDGE HANDLING EQUIPMENT @ HUNTS POINT WWTP | 2022 | 57498 | 0 | 0 | 26015 | 0 | 0 | 0 | 249985 | 276000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-253-L | INSTALL EDDY CURRENT DRIVE SYS. FOR MSP @ HUNTS POINT | PLANT UPGRADING AND RECONSTRUCTION | 100 | WP-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 1270 RYAWA AVENUE, BRONX, N.Y. 10474 | NSTALLATION OF EDDY CURRENT DRIVE SYSTEMS FOR MAIN SEWAGE PUMPS AT HUNTS POINT WWTP. DEMOLISH EXISTING VARIABLE FREQUENCY DRIVE SYSTEMS, FURNISH AND INSTALL SIX (6) EDDY CURRENT DRIVE SYSTEMS, RECONSTRUCT EXISTING PUMP-AND-MOTOR SUPPORT STRUCTURES, DRIVE INTEGRATION WITH EXISTING SCADA SYSTEM, STARTUP SYSTEM, TESTING, AS-BUILTS-AND TRAINING | 2022 | 7100 | 0 | 0 | 0 | 0 | 0 | 0 | 6700 | 6700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-254-L | TRC - CONS OF DECHLORINATION FACILITY @ HUNTS POINT WWTP | CONSENT DECREE UPGRADING AND CONSTRUCTION | 100 | WP-0282 |  | COSTER STREET & RYAWA AVENUE, BRONX, NEW YORK 10474 | CONSTRUCTION OF DECHLORINATION FACILITY TO UTILIZE SODIUM BISULFITE AT THE EFFLUENT AT THE HUNTS POINT WASTEWATER TREATMENT PLANT, BRONX, NEW YORK. | 2022 | 22552 | 4327.75 | 0 | 4500 | 18697 | 0 | 0 | 0 | 27524.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HP-3R | RECONSTRUCTION OF EXISTING DIGESTERS AT HUNTS POINT WPCP | PLANT COMPONENT STABILIZATION | 100 102 | WP-0056 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECONSTRUCT EXISTING DIGESTERS AT HUNTS POINT WATER POLLUTION CONTROLPLANT | 2022 | 40000 | 17391.58 | 129 | 0 | 0 | 0 | 0 | 0 | 17520.58 | 34055.13 | 0 | 0 | 0 | 0 | 0 | 0 | 34055.13
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | HUTCHPKW | Improve WM Dist in Hutchinson River Pkwy Ramp AC & ACD, BX | AUGMENTATION OF WATER SUPPLY SYSTEMS | 100 | WM-0006 |  |  | TO IMPROVE WATER DISTRIBUTION SYSTEM AND WATER QUALITY-BETTERMENT FORUPSIZING EXISTING 20 INCH WATER MAIN INTO 24 INCH WATER MAIN IN HUTCHINSON RIVER PARKWAY IN THE VICINITY OF RAMP AC AND ACD, BOROUGH OF THEBRONX. | 2022 | 42 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | JRAQ-REH | JEROME RESERVOIR & AQUEDUCT REHABILITATION | WATER QUALITY PRESERVATION | 107 | WM-0105 |  |  | JEROME RESERVOIR & AQUEDUCT REHABILITATION | 2022 | 31000 | 75998.35 | 601 | 0 | 0 | 0 | 0 | 0 | 76599.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-236A | Throgs Neck Pumping Station Rehabilitation and Improvements | PLANT UPGRADING AND RECONSTRUCTION | 100 | WP-0269 |  |  | RECONSTRUCTION OF THROGS NECK PS | 2022 | 54000 | 5100 | 50244 | 0 | 0 | 0 | 0 | 0 | 55344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-288 | 233RD STREET PUMPING STATION | PLANT UPGRADING AND RECONSTRUCTION | 100 | WP-0269 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 233RD STREET PUMPING STATION | 233RD STREET PUMPING STATION | 2022 | 2000 | 0 | 0 | 0 | 0 | 2000 | 9400 | 0 | 11400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | PS-290 | CONNER STREET PUMPING STATION | PLANT UPGRADING AND RECONSTRUCTION | 100 | WP-0269 |  | CONNOR STREET PUMPING STATION | CONNOR STREET PUMPING STATION | 2022 | 9848 | 0 | 0 | 2200 | 50000 | 0 | 0 | 0 | 52200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | SE849 | Dist WM SE Rplmt in Southeast Clason Point, BX | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 109 | SE-0200X WM-0001 SE-0002X |  |  | DISTRIBUTION WATER MAIN AND COMBINED AND STORM SEWERS REPLACEMENT WORK IN SOUTHEAST CLASON POINT IN THE BRONX. THIS IS THE SECOND PHASE OF CONSTRUCTION FOR THE AMENDED DRAINAGE PLAN ALONGSIDE PUGLSEY CREEK TO INCREASE CONVEYANCE OF CSO TO HUNTS POINT WWTP. THE FIRST PHASE IS COMPLETED PROJECT CS-ER-WCP. | 2022 | 30216 | 0 | 0 | 0 | 30367 | 0 | 0 | 0 | 30367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | SEX002273 | Replacement of combined sewers in Bruckner Blvd BRONX | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 102 | SE-0002X |  |  | REPAIR/ REPLACE COMBINES SEWER IN BRUCKNER BOULEVARD AND OTHER LOCATIONS IN THE BRONX. | 2022 | 1153 | 0 | 0 | 1023 | 0 | 0 | 0 | 0 | 1023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | SEX002274 | Recon of W 254 St btwn Railroad Terrace & Riverdale Ave, BX | AUGMENTATION OF WATER SUPPLY SYSTEMS | 108 | SE-0002X WM-0001 |  |  | RECONSTRUCTION OF WM & SE ON WEST 254 STREET BETWEEN RAILROAD TERRACE & RIVERDALE AVE, BRONX. IN CONJUNCTION WITH DOT PROJECT HWX406 | 2022 | 2306 | 0 | 0 | 0 | 253 | 1972 | 0 | 0 | 2225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 826 | DEPT ENVIRONMENTAL PROTECTION | SEX002275 | Reconstruction of Grand Concourse Phase 5, Bronx | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 105 107 | SE-0002X |  |  | RECONSTRUCTION OF COMBINED SEWER REPLACEMENT FROM E. FORDHAM ROAD TO E. 198 STREET, GRAND CONCOURSE PHASE 5 IN THE BRONX. THIS PROJECT IS DONE IN CONJUNCTION WITH HWXP136D. NO WATER MAIN WORK IS REQUIRED AS DIRECTED BY DISTRIBUTION ENGINEERING. | 2022 | 2698 | 0 | 0 | 296 | 2308 | 0 | 0 | 0 | 2604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-332M | BRONX 6/6A GARAGE REHAB | GARAGES AND FACILITIES | 106 107 | S-0136 |  |  | BRONX 6/6A GARAGE REHAB | 2022 | 20240 | 2385.13 | 116 | 6910 | 21194 | 0 | 0 | 0 | 30605.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-424 | Bronx 12 Rehabilitation (Slabs, Roof, Fueling Enclosure) | GARAGES AND FACILITIES | 112 | S-0136 |  |  | FLOOR SLAB REPLACEMENT | 2022 | 44594 | 2632.74 | 59 | 40991 | 0 | 0 | 0 | 0 | 43682.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-429 | Bronx 3A 1661 West Farms Road Garage Reconstruction | GARAGES AND FACILITIES | 103 | S-0136 |  |  | REHAB | 2022 | 9891 | 0 | 0 | 0 | 853 | 6353 | 0 | 0 | 7206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-429D | Bronx 3A 1661 West Farms Road Garage Demolition | GARAGES AND FACILITIES | 103 | S-0136 |  |  | DEMOLITION | 2022 | 300 | 3223.74 | 381 | 0 | 0 | 0 | 0 | 0 | 3604.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 827 | DEPARTMENT OF SANITATION | S136-464G | Bronx 3 Sec 31 Roof Replacement Washington Ave | GARAGES AND FACILITIES | 103 | S-0136 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ROOF REPLACEMENT | 2022 | 144 | 533.3 | 117 | 726 | 0 | 0 | 0 | 0 | 1376.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 827 | DEPARTMENT OF SANITATION | S195-228M | Bronx 2 Salt Shed Rehabilitation | GARAGES AND FACILITIES | 102 | S-0195 |  |  | DEMOLISH UNSAFE ROOF | 2022 | 350 | 100 | 363 | 0 | 0 | 0 | 0 | 0 | 463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 827 | DEPARTMENT OF SANITATION | S248-423 | Bronx 9/10/11 Garage Replacement | GARAGES AND FACILITIES | 100 | S-0248 |  |  | REPLACEMENT OF THE BRONX 9/10/11 GARAGES | 2022 | 266742 | 32603.38 | 2746 | 0 | 301746 | 0 | 3000 | 0 | 340095.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 827 | DEPARTMENT OF SANITATION | SANDBX12G | Hurricane Sandy Bronx 12 Garage R/R & Haz Mitigation | GARAGES AND FACILITIES | 112 | S-0136 |  |  | REPLACEMENT WORK AND HAZRD MITIGATION DUE TO HURRICANE SANDY | 2022 | 1197 | 143.1 | 43 | 94 | 0 | 0 | 0 | 0 | 280.1 | 0 | 140 | 834 | 0 | 0 | 0 | 0 | 974
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BRX2110 | BOSTON ROAD OVER BRONX RIVER BIN: 2242110 | USEFUL LIFE EXTENSION | 100 111 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BOSTON ROAD OVER BRONX RIVER ÝBIN: 2242110 | 2022 | 12036 | 1326.12 | 0 | 942 | 19588 | 0 | 0 | 0 | 21856.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BRX9579 | BOSTON ROAD OVER HUTCHINSON RIVER BIN: 2229579 | USEFUL LIFE EXTENSION | 100 112 | HB-1070 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BOSTON POST ROAD OVER HUTCHINSON RIVER ÝBIN: 2229579 | 2022 | 185832 | 7607.81 | 12293 | 64000 | 0 | 0 | 0 | 0 | 83900.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | BXECONDEV | FA - BX Council for Economic Devel. - Streetscape Furniture | COMMERCIAL DEVELOPMENT | 100 | ED-D384 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BRONX COUNCIL FOR ECONOMIC DEVELOPMENT-STREETSCAPE FURNITURE | 2022 | 1430 | 754.05 | 88 | 0 | 0 | 0 | 0 | 0 | 842.05 | 38.29 | 0 | 0 | 0 | 0 | 0 | 0 | 38.29
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | CTYISLBRD | Reconstruction of City Island Access Bridge | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 100 | FA-0021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECON CITY ISLAND ACCESS BRIDGE | 2022 | 5180 | 7823.22 | 0 | 0 | 10 | 0 | 0 | 4996 | 12829.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HB1070MN | Protective Coating of Metro North Bridges | Bridge Painting | 100 | HB-1070 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PROTECTIVE COATING OF METRO NORTH BRIDGES | PROTECTIVE COATING OF METRO NORTH BRIDGES | 2022 | 16900 | 0 | 0 | 0 | 0 | 0 | 16900 | 0 | 16900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBB224222 | SNUFF MILL ROAD OVER BRONX RIVER BIN 2242220 | FAIR BRIDGES | 100 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SNUFF MILL ROAD OVER BRONX RIVER | SNUFF MILL ROAD OVER BRONX RIVER | 2022 | 22181 | 0 | 0 | 0 | 0 | 3102 | 0 | 19079 | 22181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBB241850 | CONN RD BETWEEN MOS OVER METRO NORTH RR-HAR BIN 2241850 | FAIR BRIDGES | 100 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CONN RD BETWEEN MOS OVER METRO NORTH RR-HAR | CONN RD BETWEEN MOS OVER METRO NORTH RR-HAR | 2022 | 29292 | 0 | 0 | 0 | 2582 | 0 | 2582 | 24128 | 29292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA06672 | EAST 174TH ST/SHERIDAN EXPWY AMTRAK BIN# 2066720 | FAIR BRIDGES | 100 | HB-6672 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | EAST 174TH ST/SHERIDAN EXPWY AMTRAK BIN# 2066720 | EAST 174TH ST/SHERIDAN EXPWY AMTRAK BIN# 2066720 | 2022 | 14670 | 3733.88 | 250 | 6520 | 0 | 130951 | 0 | 0 | 141454.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA23025 | MOSHOLU PKWY/BRONX RIVER 2-23025-0 (TD PKG) | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 100 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MOSHOLU PKWY/BRONX RIVER 2-23025-0 (TD PKG) | MOSHOLU PKWY/BRONX RIVER 2-23025-0 (TD PKG) | 2022 | 71957 | 0 | 0 | 0 | 8440 | 0 | 0 | 63517 | 71957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24138 | Pelham Bay Park Equestrian over Amtrak- CSX BIN 2241380 | FAIR BRIDGES | 100 | P-0508 |  | PELHAM BAY PARK EQUESTRIAN OVER AMTRAK- CSX BIN 2241380 | PELHAM BAY PARK EQUESTRIAN OVER AMTRAK- CSX BIN 2241380 | 2022 | 41329 | 1708.99 | 0 | 1402 | 2998 | 35358 | 0 | 0 | 41466.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24180 | East 183rd St over MNRR Har BIN 2241800 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 100 | HB-1139 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | EAST 183RD ST OVER MNRR HAR BIN 2241800 | EAST 183RD ST OVER MNRR HAR BIN 2241800 | 2022 | 22339 | 1209.75 | 2400 | 11839 | 0 | 0 | 0 | 0 | 15448.75 | 0 | 0 | 11200 | 0 | 0 | 0 | 0 | 11200
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24181 | East 188th St over MNRR Har BIN 2241810 | FAIR BRIDGES | 100 | HB-1172 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | EAST 188TH ST OVER MNRR HAR BIN 2241810 | EAST 188TH ST OVER MNRR HAR BIN 2241810 | 2022 | 30967 | 1671.7 | 3328 | 33167 | 0 | 0 | 0 | 0 | 38166.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24236 | GRAND CONCOURSE over BURNSIDE AVENUE BIN 2242360 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 100 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | GRAND CONCOURSE OVER BURNSIDE AVENUE | GRAND CONCOURSE OVER BURNSIDE AVENUE | 2022 | 36673 | 0 | 0 | 0 | 3940 | 0 | 0 | 32733 | 36673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA24245 | EAST 233RD ST/ BRONX RIVER BIN # 2242459 | FAIR BRIDGES | 100 | HB-1012 HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | EAST 233RD ST/ BRONX RIVER | EAST 233RD ST/ BRONX RIVER BIN # 2242459 | 2022 | 24927 | 1942.36 | 0 | 1191 | 0 | 0 | 23010 | 0 | 26143.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA42081 | BRONX BOULEVARD SOUTHBOUND over BRONX RIVER BIN 2242081 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 100 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BRONX BOULEVARD SOUTHBOUND OVER BRONX RIVER BIN 2242081 | BRONX BOULEVARD SOUTHBOUND OVER BRONX RIVER BIN 2242081 | 2022 | 13712 | 0 | 0 | 0 | 2801 | 0 | 1364 | 9547 | 13712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBBA42082 | BRONX BOULEVARD NORTHBOUND over BRONX RIVER BIN 2242082 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 100 | HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BRONX BOULEVARD NORTHBOUND OVER BRONX RIVER BIN 2242082 | BRONX BOULEVARD NORTHBOUND OVER BRONX RIVER BIN 2242082 | 2022 | 14152 | 0 | 0 | 0 | 2800 | 0 | 1419 | 9933 | 14152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1086 | WESTCHESTER AVE BR OVER HUTCH RIVER PKWY 2-075837 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 110 111 | HB-1086 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WESTCHESTER AVE BRIDGE | 2022 | 27909 | 29645.26 | 12503 | 0 | 0 | 0 | 0 | 0 | 42148.26 | 44388 | 0 | 344 | 0 | 0 | 0 | 0 | 44732
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1103 | CONCOURSE VLGE AVE/ M-N 2-24159-0 | FAIR BRIDGES | 104 | HB-1103 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2022 | 10949 | 1918.19 | 2592 | 0 | 46059 | 0 | 0 | 0 | 50569.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1127 | RECON PELHAM PKWY BRIDGE OVER HUTCHINSON PKWY 2-07584-9 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 110 111 | HB-1012 HB-1127 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2022 | 10870 | 8888.53 | 111 | 0 | 59096 | 0 | 0 | 0 | 68095.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1131 | BRUCKNER EXP / WESTCHESTER CREEK 1-066510 | FAIR BRIDGES | 109 110 | HB-1131 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  |  | 2022 | 57008 | 122210.36 | 11810 | 0 | 0 | 0 | 0 | 0 | 134020.36 | 162685.7 | 0 | 0 | 0 | 0 | 0 | 0 | 162685.7
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1148B | SHORE ROAD BRIDGE / HUTCHINSON RIVER 2-240200 | FAIR BRIDGES | 110 | HB-1148 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | N/A |  | 2022 | 113110 | 15787.85 | 601 | 100 | 11376 | 0 | 244411 | 0 | 272275.85 | 0 | 0 | 0 | 0 | 0 | 67365 | 0 | 67365
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1190 | GRAND CONCOURSE / METRO NORTH RR HUD2-24140-9 | FAIR BRIDGES | 104 | HB-1190 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NA |  | 2022 | 16514 | 69939.42 | 2900 | 1660 | 0 | 0 | 0 | 0 | 74499.42 | 438.2 | 1165 | 0 | 0 | 0 | 0 | 0 | 1603.2
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1215 | E. 175TH ST/METRO NORTH RR HAR 2-24174-0 TD PKG 1 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 100 105 | HB-4174 TF-0002 TF-0502 WM-0001 HB-1012 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | E. 175TH ST/METRO NORTH RR HAR 2-24174-0 | E. 175TH ST/METRO NORTH RR HAR 2-24174-0 TD PKG 1 | 2022 | 5799 | 17197.25 | 2230 | 876 | 0 | 0 | 0 | 0 | 20303.25 | 0 | 799 | 0 | 0 | 0 | 0 | 0 | 799
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX1460 | WEST TREMONT AVENUE OVER METRO NORTH RR BIN:2241460 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 100 105 | HB-4146 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | WEST TREMONT AVENUE OVER METRO NORTH RR ÝBIN:2241460 | 2022 | 27508 | 7359.08 | 1550 | 12646 | 0 | 0 | 0 | 0 | 21555.08 | 0 | 0 | 64657 | 0 | 0 | 0 | 0 | 64657
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX156 | E 156TH ST BRIDGE OVER ACCESS TO HOUSING (BIN 2270030) | FAIR BRIDGES | 100 101 | HB-7003 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RECONSTRUCTION OF E 156TH ST BRIDGE OVER ACCESS TO HOUSING (BIN 2270030) | RECONSTRUCTION OF E 156TH ST BRIDGE OVER ACCESS TO HOUSING (BIN 2270030) | 2022 | 9916 | 1886.33 | 4114 | 0 | 60000 | 0 | 0 | 0 | 66000.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX163 | 5 Bridges - Melrose, Bronx | FAIR BRIDGES | 100 101 | HD-0098 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | FIVE BRIDGES - MELROSE, BRONX | FIVE BRIDGES - MELROSE, BRONX | 2022 | 14751 | 23364.71 | 2256 | 0 | 0 | 0 | 0 | 0 | 25620.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX180 | E. 180TH ST OVER METRO NORTH RR HAR (BIN 2-24179-0) | FAIR BRIDGES | 100 106 | HB-1010 TF-0002 TF-0502 HB-0215 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | E. 180TH ST OVER METRO NORTH RR HAR (BIN 2241790) | E. 180TH ST OVER METRO NORTH RR HAR (BIN 2241790) | 2022 | 8120 | 26925.32 | 6784 | 0 | 0 | 0 | 0 | 0 | 33709.32 | 2348.3 | 712 | 0 | 0 | 0 | 0 | 0 | 3060.3
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX199 | E153RD ST BR AT PARK AVE OVER RR | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 101 104 | HB-0199 HB-0061 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | THE WORK CONSISTS OF DEMOLITION OF THE EAST 153RD STREET BRIDGE OVER TNORTH COMMUTER RAILROAD IN THE BORO OF THE BRONX THE BRIDGE CONSISTS ORUSS SPANS, ONE OF WHICH IS LOCATED OVER ELECTRIFIED RAILROAD TRACKS TINCLUDES REMOVAL OF THE EXISTING BRIDGE SUBSTRUCTURE, AND CONSTRUCTIONRIDGE APPROACH ALTERATIONS A 6 INCH DIAMETER WATER SUPPLY PIPE TO METRS FACILITIES, WHICH IS ATTACHED TO THE SPAN OVER THE RAILROAD, IS TO BD BY A NEW 6 INCH PIPE INSERTED IN A 12 INCH SLEAVE JACKED UNDER THE RRACKS DEMO IS PHASE 1 AND RECON IS PHASE 2 THE FUNDING IS 100% CITY | 2022 | 121223 | 20701.49 | 0 | 0 | 0 | 0 | 0 | 11477 | 32178.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX2370 | REHAB GRAND CONCOURSE BIN 2242370 | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 100 101 104 105 107 | HB-1070 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REHAB GRAND CONCOURSE BIN 2242370 | 2022 | 17721 | 0 | 0 | 0 | 0 | 0 | 2077 | 26600 | 28677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HBX644S | MADISON AVE BR - REHAB OF ELECTRICAL AND MECHANICAL SYSTEM | BRIDGE LIFE EXTENSION AND MISCELLANEOUS WORK | 101 104 | HB-0644 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MAIDISON AVE BR - SEISMIC RETROFITTING & REHABILITATION | MADISON AVE BR - SEISMIC RETROFITTING & REHABILITATION | 2022 | 43944 | 30317.3 | 7113 | 600 | 0 | 0 | 0 | 0 | 38030.3 | 21360 | 40 | 0 | 0 | 0 | 0 | 0 | 21400
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HW2CR19A | Citywide Milling - Bronx | PRIMARY STREET RESURFACING | 100 | HW-0002X | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITYWIDE MILLING- BRONX | 2022 | 5857 | 6592.03 | 5409 | 0 | 0 | 0 | 0 | 0 | 12001.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWCWSTPR | NY RESTORATION PROJECT - DEVELOP & DESIGN STREET PIER | PRIMARY STREET RECONSTRUCTION |  | HW-X001 HW-D105 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NY RESTORATION PROJECT - DEVELOP & DESIGN STREET PIER | 2022 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 2750 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWM10INWD | Inwood 10th Avenue Improvements | PRIMARY STREET RECONSTRUCTION | 100 | HW-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | INWOOD 10TH AVENUE IMPROVEMENTS | INWOOD 10TH AVENUE IMPROVEMENTS | 2022 | 24400 | 0 | 0 | 0 | 0 | 27546 | 0 | 0 | 27546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWPLZ006X | Westchester Square Plaza | PRIMARY STREET RECONSTRUCTION | 100 | HW-0001X | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WESTCHESTER SQUARE PLAZA | WESTCHESTER SQUARE PLAZA | 2022 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWSRT200F | Bus Stops Under the EI - Southern Blvd | PRIMARY STREET RECONSTRUCTION | 100 | HW-0001 HW-0001K | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BUS STOPS UNDER THE EI - SOUTHERN BLVD | BUS STOPS UNDER THE EI - SOUTHERN BLVD | 2022 | 12190 | 0 | 0 | 1742 | 0 | 0 | 10448 | 0 | 12190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX405 | Southern Blvd Pedestrian and Bike Improvements | PRIMARY STREET RECONSTRUCTION | 100 | HW-0001X | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SOUTHERN BLVD PEDESTRIAN AND BIKE IMPROVEMENTS (BEDFORD PARK BLVD TO E 179TH ST) | SOUTHERN BLVD PEDESTRIAN AND BIKE IMPROVEMENTS (BEDFORD PARK BLVD TO E 179TH ST) | 2022 | 9482 | 0 | 0 | 0 | 0 | 0 | 11621 | 0 | 11621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX407 | Mott Haven Pedestrian and Cyclist Safety Improvements | PRIMARY STREET RECONSTRUCTION | 100 | HW-0001X | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | INTERSECTION IMPROVEMENTS AT 3RD AVENUE AND 138TH STREET | INTERSECTION IMPROVEMENTS AT 3RD AVENUE AND 138TH STREET | 2022 | 11046 | 0 | 0 | 1578 | 0 | 0 | 9468 | 0 | 11046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX409 | Willis Ave Bikeway Improvements | PRIMARY STREET RECONSTRUCTION | 100 | HW-0001X | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | WILLIS AVE BIKEWAY IMPROVEMENTS | WILLIS AVE BIKEWAY IMPROVEMENTS | 2022 | 10259 | 0 | 0 | 0 | 0 | 0 | 10259 | 0 | 10259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWX711 | Bronx River Greenway @ 233rd St | PRIMARY STREET RECONSTRUCTION | 100 | HW-0001X | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BRONX RIVER GREENWAY @ 233RD ST. | BRONX RIVER GREENWAY @ 233RD ST. | 2022 | 750 | 0 | 0 | 0 | 0 | 0 | 2625 | 0 | 2625 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 750
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXFMDYD | Macombs Dam Yard | FACILITY RECONSTRUCTION | 100 | HB-1014 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MACOMBS DAM YARD | MACOMBS DAM YARD | 2022 | 123 | 0 | 123 | 0 | 0 | 0 | 0 | 0 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXP136E | Reconstruction of Grand Concourse Phase 6 (138th - 161st) | PRIMARY STREET RECONSTRUCTION | 100 | HW-0001X | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RECONSTRUCTION OF GRAND CONCOURSE PHASE 6 (138TH - 161ST) | RECONSTRUCTION OF GRAND CONCOURSE PHASE 6 (138TH - 161ST) | 2022 | 0 | 0 | 0 | 0 | 10618 | 0 | 0 | 63708 | 74326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXS1011 | Reconstruction of the E 169th Street Step Street | RECONSTRUCTION OF STEP STREETS | 100 | HW-0001K HW-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RECONSTRUCTION OF THE E 169TH STREET STEP STREET | RECONSTRUCTION OF THE E 169TH STREET STEP STREET | 2022 | 8984 | 0 | 0 | 1495 | 0 | 0 | 7489 | 0 | 8984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | HWXS911 | Reconstruction of the Summit Place Step Street | RECONSTRUCTION OF STEP STREETS | 100 | HW-0001X HW-0001K | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RECONSTRUCTION OF THE SUMMIT PLACE STEP STREET | RECONSTRUCTION OF THE SUMMIT PLACE STEP STREET | 2022 | 8456 | 0 | 0 | 1407 | 0 | 7049 | 0 | 0 | 8456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | RWX023 | Retaining Wall - Netherland Avenue | RECONSTRUCTION OF RETAINING WALLS | 100 | HW-0001K HW-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RETAINING WALL - NETHERLAND AVENUE | RETAINING WALL - NETHERLAND AVENUE | 2022 | 16021 | 0 | 0 | 1849 | 0 | 0 | 14172 | 0 | 16021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TFD005X01 | DOT Camera install at Clay Avenue Step Street and 169th BX | SIGNAL INSTALLATION AND COMPUTERIZATION | 100 | TF-D005 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | (PB) DOT 169TH STREET CLAY AVENUE--DOT CAMERA INSTALLATION AT CLAY AVENUE STEP STREET AND 169TH STREET | 2022 | 75 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TFD503X21 | CLAY AV.HISTORIC DISTRICT OLD-STYLE ST LAMP BET. E165& 167TH | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 100 104 | TF-D503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CLAY AV. HSITORIC DISTRICT OLD-STYLE LAMP BET. E165& 167TH | CLAY AV. HSITORIC DISTRICT OLD-STYLE LAMP BET. E165& 167TH | 2022 | 200 | 73.18 | 0 | 0 | 0 | 127 | 0 | 0 | 200.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TFX50301 | GRAND CONCOURSE DECORATIVE STREET LIGHTING | INSTALLATION OF LAMPPOSTS AND LUMINAIRES | 100 101 104 105 107 | TF-X503 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | GRAND CONCOURSE DECORATIVE STREET LIGHTING | GRAND CONCOURSE DECORATIVE STREET LIGHTING | 2022 | 250 | 651.21 | 0 | 0 | 0 | 177 | 0 | 0 | 828.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 841 | DEPARTMENT OF TRANSPORTATION | TRANSBCTY | Reconstruction Transfer Bridge Structure at City Island | RECONSTRUCTION OF FERRY TERMINAL FACILITIES | 100 | FA-0021 |  |  | RECONSTRUCT TRANSFER BRIDGE STRUCTURE AT CITY ISLAND | 2022 | 3400 | 0 | 340 | 0 | 3060 | 0 | 0 | 0 | 3400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | GXBXGI-01 | Bronx Parkland Green Infrastructure Retrofits | LAND ACQUISITION AND TREE PLANTING | 100 | P-D021 WP-0169 |  | BRONX PARKLAND GREEN INFRASTRUCTURE RETROFITS | BRONX PARKLAND GREEN INFRASTRUCTURE RETROFITS | 2022 | 2270 | 611.44 | 113 | 219 | 0 | 0 | 0 | 0 | 943.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | GXBXGI-02 | Bronx Green Inrastructure | LAND ACQUISITION AND TREE PLANTING | 100 | WP-0169 |  | BRONX -VARIOUS | BRONX GREEN INFRASTRUCTURE | 2022 | 850 | 0 | 0 | 850 | 0 | 0 | 0 | 0 | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | GXBXGI-03 | GI- Van Cortlandt Park | LAND ACQUISITION AND TREE PLANTING | 100 | WP-0169 |  | BOUROUGH OF BRONX- BROADWAY, JEROME AVENUE, CITY LINE, VAN CORTLANDT PARK SOUTH | PROJECT WILL INSTALL MULTIPLE GREEN INFRASTRUCTURE ELEMENTS IN VAN CORTLANDT PARK IN THE BOROUGH OF BRONX | 2022 | 733 | 0 | 0 | 1172 | 0 | 0 | 0 | 0 | 1172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | HIF-1FSPB | Franz Sigel Park Ballfields-Install BallField Lighting | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | ED-0075 P-D021 |  | GERARD AVE., WALTON AVE., GRAND CONCOURSE BET. E. 151 ST., E. 153 ST.AND E. 158 ST IN THE BRONX | FRANZ SIGEL PARK BALLFIELD LIGHTING | 2022 | 9614 | 1046.75 | 20 | 6244 | 200 | 2247 | 0 | 0 | 9757.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-BRPLG | NDF-Bridge Playground- X148A3-318M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 104 105 | P-X245 |  | HARLEM RIVER BETWEEN W 175 STREET AND ALEXANDER HAMILTON BRIDGE | BRIDGE PLAYGROUND | 2022 | 1575 | 2702.11 | 359 | 0 | 0 | 0 | 0 | 0 | 3061.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-CPFSP | NDF-CORPORAL FISCHER PLAYGROUND X269-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 104 | ED-0384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | NELSON AVE BET. W169 STREET AND W. 170 ST BOROUGH OF THE BRONX | CORPROAL FISHCER PLAYGROUND CONSTRUCTION | 2022 | 4642 | 575 | 3228 | 0 | 296 | 296 | 137 | 685 | 5217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-DVDSO | Neighborhood Dev. Fund-1801 Davidson X367-120M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | ED-0384 |  | BRONX | NEIGHBORHOOD DEV. FUND-1801 DAVIDSON | 2022 | 11233 | 1345.94 | 0 | 4869 | 460 | 637 | 749 | 3745 | 11805.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-GRANT | NDF-Grant Park X271-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 104 | HW-0001M ED-0384 P-X245 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | EAST 170 STREET BET SHERIDAN AVENUE AND MORRIS AVENUE | NDF-GRANT PARK -NEW DEVELOPMENT | 2022 | 25717 | 2391.95 | 0 | 23760 | 79 | 600 | 0 | 1005 | 27835.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-JROME | NDF- Jerome Trees | LAND ACQUISITION AND TREE PLANTING | 100 | ED-0384 |  | BOROUGH OF BRONX | TREE RESTITUTION (BRONX) | 2022 | 235 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-MORTN | NDF-MORTON PLAYGROUND RECONSTRUCTION (X001A) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 105 107 | ED-0384 | PROJECT DELAYED DUE TO UNFORESEEN HAZARDOUS CONDITION | MORTON PL & UNIVERSITY AVE BOROUGH OF BRONX | RECONSTRUCTION OF MORTONPLAYGROUND USIING NDF FUNDS | 2022 | 5216 | 2753.73 | 244 | 0 | 0 | 243 | 335 | 1675 | 5250.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | NDF-SOAQK | NDF-Aqueduct Walk X001A-121M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | ED-0384 |  | BOROUGH OF BRONX | NDF- RC AQUEDUCT WALK | 2022 | 10000 | 75 | 581 | 0 | 4420 | 4151 | 0 | 848 | 10075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-100CDAR | Cedar Playground - RC C/S X111-114M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 105 | P-X245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CEDAR PLGD, THE BRONX | CEDAR PLGD RC | 2022 | 1200 | 1265.03 | 0 | 0 | 0 | 130 | 0 | 0 | 1395.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101BPAR | Brook Park - sitting area & comfort station X246-120M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 104 | P-D021 P-X245 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BRONX | BROOK PARK RECON SITTING AREA AND COMFORT STATION. | 2022 | 1850 | 177.96 | 0 | 0 | 884 | 0 | 0 | 0 | 1061.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101LZDA | Lozada Park Renovation- New play equip.,spray shower, swings | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 101 | P-0245X | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | E 135 ST BET. ALEXANDER AV AND WILLIS AVE IN THE BRONX | LOZADA PARK RENOVATION - NEW PLAY EQUIPMENT, DRINKING FOUNTAINS, SPRAY SHOWERS, SWINGS | 2022 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101MAR2 | St. Mary's Plgd West - ADA CS X045-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0505 P-1018 P-1250 |  |  | ST MARY'S PLGD WEST - ADA CS | 2022 | 0 | 2864.64 | 562 | 0 | 0 | 0 | 0 | 0 | 3426.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101PULP | Pulaski Park Reconstruction- X041-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0510 | PROJECT DELAYED DUE TO UNFORESEEN HAZARDOUS CONDITION |  | PULASKI PARK RECONSTRUCTION | 2022 | 1750 | 3351.94 | 20 | 0 | 0 | 221 | 0 | 0 | 3592.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101STMH | ST. MARY'S PK REC CTR HVAC X045-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1250 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ST. MARY'S PK REC CTR HVAC | 2022 | 1500 | 2374.18 | 7 | 0 | 0 | 153 | 0 | 0 | 2534.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-101WLSP | Willis Plgd Recon - X217-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 |  |  | WILLIS PLGD RENOV. NEW EQUIPMENT, SAFETY SURFACING &FOUNTAIN | 2022 | 3410 | 2757.26 | 161 | 0 | 0 | 0 | 0 | 0 | 2918.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102BRPP | Bill Rainey Park--Lights For Baseball Field & Score Board | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS |  | BILL RAINEY PARK--LIGHTS FOR BASEBALL FIELD & SCORE BOARD X255-119M | 2022 | 1364 | 176 | 804 | 0 | 0 | 196 | 0 | 0 | 1176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102HNT2 | Hunts Point - Riverside Park - Dock Repair X336-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 102 | P-D021 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | HUNTS POINT RIVERSIDE PARK | HUNTS POINT RIVERSIDE PARK DOCK REPAIR PH II | 2022 | 100 | 68 | 0 | 0 | 350 | 0 | 0 | 0 | 418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102MNDA | Manida Park-Lighting & Scoreboard Renovation | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 P-0245X | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MANIDA PARK-LIGHTING & SCOREBOARD RENOVATION | 2022 | 382 | 181 | 1475 | 291 | 220 | 0 | 0 | 0 | 2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102RJPP | Rev. J Polite Plgd-Recon of synthetic turf | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 102 | P-1018 P-0510 |  | REV JAMES POLITE AV TO INTERVAL AV BET. E 167 ST AND HOME ST BRONX | RECON OF SYNTHETIC TURF AT REV. J. POLITE PLAYGROUND | 2022 | 3736 | 327 | 508 | 2872 | 0 | 0 | 0 | 0 | 3707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-102TOWR | Concrete Plant Park - Tower Stabilization | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 |  |  | CONCRETE PLANT PARK - TOWER STABILIZATION | 2022 | 4350 | 0 | 3922 | 399 | 29 | 0 | 0 | 0 | 4350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CGJF | CS-134-Fence and Water Supply- (X340-116MA) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 103 | P-D021 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CS134 COMMUNITY GARDEN AND JACKSON FOREST COMMUNITY GARDEN | ONSTRUCTION OF PERIMETER FENCE & WATER SUPPLY IN CS134 COMMUNITY GARDEN AND WATER SUPPLY IN JACKSON FOREST COMMUNITY GARDEN | 2022 | 841 | 1260.61 | 285 | 0 | 0 | 0 | 0 | 0 | 1545.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPB5 | Crotona Park - ballfield #5 - X010-115M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 103 | P-1018 P-D021 P-0245X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BOROUGH OF THE BRONX | CROTONA PARK BALLFIELD# 5 | 2022 | 1000 | 5221.86 | 1166 | 0 | 0 | 0 | 0 | 0 | 6387.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPBT | TREE RESTITUTION REQ FOR CROTONA PARK | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 |  | CROTONA PARK | THIS TREE PLANTING CONTRACT WILL COVER TREE RESTITUTION REQUIREMENTS FOR CUTTING DOWN ONE TREE WITHIN THE SCOPE OF X010-115M. | 2022 | 200 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CPEW | CROTONA PARK GREENWAY - X010-105M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 103 | P-0697 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BRONX | CROTONA PARK ENVIRONMENTAL WORK | 2022 | 1035 | 244.92 | 0 | 0 | 0 | 0 | 0 | 0 | 244.92 | 519.05 | 0 | 0 | 0 | 80 | 0 | 0 | 599.05
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103CRCS | CROTONA PK COMFORT STATION X010-214M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 103 | P-0245X P-D021 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CROTONA PARK | CROTONA PARK: COMFORT STATION # 10 - RENOV TO THE COMFORT STATION IN PLGD# 10 INCLUDING NEW UTILITIES AND ADA ACCESSIBILITY | 2022 | 840 | 1729.03 | 0 | 0 | 0 | 218 | 0 | 0 | 1947.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103DPLS | Drew Playground Security Lighting X021-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SECURITY LIGHTING | 2022 | 420 | 568.79 | 0 | 0 | 0 | 67 | 0 | 0 | 635.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-103WPBC | Waring Plgd Basketball Courts Recon (X002-118M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0245X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | WARING PLGD BASKETBALL COURTS RECON (X002- | 2022 | 500 | 3159.54 | 427 | 0 | 0 | 0 | 0 | 0 | 3586.54 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 500
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104CLMT | Claremont Park Improvements | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-D021 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CLAY AVE., ANTHONY AVE. BET. MOUNT EDEN PKWY. AND E. 170 ST IN THE BRONX | CLAREMONT PARK IMPROVEMENTS | 2022 | 2418 | 29 | 868 | 0 | 0 | 0 | 0 | 0 | 897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104FISH | Cons of 182nd St. Fish Passage Dam X002-111M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 106 104 | P-X245 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 182ND ST, BRONX | CONST OF 182ND ST FISH PASSAGE DAM | 2022 | 1572 | 1390.16 | 0 | 0 | 0 | 0 | 101 | 0 | 1491.16 | 876.8 | 0 | 0 | 0 | 0 | 0 | 0 | 876.8
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104GBLE | Goble Playground- new BBall equip., swings, handball court | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 104 | P-D021 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | GOBLE PL BET. INWOOD AV AND MACOMBS RD IN THE BRONX | GOBLE PLAYGROUND -- NEW BASKETBALL EQUIPMENT, SWINGS, AND HANDBALL COURT. | 2022 | 1750 | 239 | 194 | 0 | 2616 | 0 | 2668 | 0 | 5717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104HGBG | Highbridge Park - step streets/park ldscape X120-110M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 104 105 | P-D021 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | WEST 170TH STREET BETWEEN UNIVERSITY AVENUE AND SEDGWICK AVENUE | THIS PROJECT WILL RESTORE THE STEP STREET AND SURROUNDING LANDSCAPE IN HIGHBRIDGE PARK. | 2022 | 200 | 5844.77 | 30 | 0 | 0 | 581 | 0 | 0 | 6455.77 | 719.72 | 0 | 0 | 0 | 0 | 0 | 0 | 719.72
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104HPRM | Bridge Park-Highbridge Greenway promenade | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 104 | P-X245 P-D021 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | HIGHBRIDGE IN THE BRONX | EXPANSION OF THE GREENWAY TO IMMEDIATE NORTH OF HIGHBRIDGE FOR A SMALL PARK AREA AND EVENTUAL NON-MOTORIZED SMALL BOAT ACCESS TO THE RIVER | 2022 | 600 | 579.43 | 7 | 0 | 1663 | 0 | 1000 | 0 | 3249.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104JRME | Jerome Playground S- Handball courts renovation X148C7-120M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 104 | P-D021 P-X245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | S/S CROSS BRONX EXWY BET. TOWNSEND AV AND JEROME AVE IN THE BRONX | JEROME PLAYGROUND SOUTH -- HANDBALL COURTS NEED TO BE RENOVATED | 2022 | 1800 | 454.63 | 0 | 2145 | 0 | 0 | 0 | 0 | 2599.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104MPSK | Mullaly Park Skate Park Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 104 | P-0801 P-0245X P-D021 |  | JEROME AV TO RIVER AV BET. E 164 ST AND MCCLELLAN ST AT CROMWELL AVE IN THE BRONX | MULLALY PARK SKATE PARK RECONSTRUCTION | 2022 | 2000 | 0 | 471 | 0 | 0 | 1552 | 0 | 0 | 2023 | 0 | 0 | 0 | 2592 | 0 | 0 | 0 | 2592
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-104SMPG | Summit Playground - Improvements | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 104 | P-D021 |  |  | SUMMIT PLAYGROUND - IMPROVEMENTS | 2022 | 86 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-105GALO | Galileo Playground - bring surface area to grade | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 105 | P-D021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | MACOMBS RD BET. W 176 ST AND W 175 ST. IN THE BRONX | GALILEO PLAYGROUND -- FILL AND COMPACT SUBSIDENCE TO BRING SURFACE AREA TO GRADE. | 2022 | 1100 | 0 | 0 | 0 | 0 | 0 | 7925 | 0 | 7925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106BRZD | BRONX RIVER ZOO DAM | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-1018 |  |  | BRONX RIVER ZOO DAM | 2022 | 5199 | 0 | 61 | 1512 | 0 | 3626 | 0 | 0 | 5199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106MAPE | CPI Phase 2-Mapes Ballfield-X289-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0245X P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MAPES BALLFIELD | 2022 | 11379 | 13232.19 | 0 | 0 | 0 | 220 | 0 | 0 | 13452.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-106QUAR | Quarry Ballfield-Cons of synthetic turf soccer fd-X263-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0245X |  |  | QUARRY BALLFIELD - BRONX | 2022 | 7798 | 916.2 | 258 | 4207 | 2304 | 0 | 0 | 0 | 7685.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107CPFE | Classic Plgd in Van Cortlandt Park-Install Fitness Equipment | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-D021 P-X245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CLASSIC PLGD IN VAN CORTLANDT PARK-INSTALL FITNESS EQUIPMENT | 2022 | 272 | 137 | 0 | 0 | 1475 | 0 | 0 | 0 | 1612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107KOSS | Kossuth Playground Recon X033-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 P-X245 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | KOSSUTH PLAYGROUND RECON (X033- | 2022 | 660 | 4089.62 | 0 | 0 | 0 | 426 | 0 | 0 | 4515.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107POEP | POE PARK PLAZA RECON | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0245X |  | E 192ND STREET, GRAND CONCOURSE, AND E KINGSBRIDGE RD | E 192ND STREET, GRAND CONCOURSE, AND E KINGSBRIDGE RD | 2022 | 4069 | 0 | 0 | 300 | 1405 | 1695 | 0 | 0 | 3400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107PPV1 | Poe Park - Poe Cottage - ADA ramp X040-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | POE ARK, BRONX | POE PARK | 2022 | 444 | 576.86 | 572 | 0 | 0 | 0 | 0 | 0 | 1148.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107SJDR | St. James Park--Dog Run- X044-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 P-0245X | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ST. JAMES PARK--DOG RUN | 2022 | 894 | 146 | 585 | 246 | 0 | 0 | 0 | 0 | 977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107SJRC | ST JAMES PARK REC CTR RENOV. | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0245X P-D021 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | MISCELLANEOUS PARKS, PLAYGROUNDS, CONSTRUCTION, RECONSTRUCTION, BRONX-- ST. JAMES PARK REC CENTER RENOVATION | 2022 | 3200 | 150 | 0 | 0 | 0 | 3364 | 0 | 0 | 3514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107STFA | ST. James Rec. Center: Fire Alarm Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 107 | P-0506 |  | 2550 JEROME AVE, BRONX. | RECONSTRUCTION OF FIRE ALARM AT ST. JAMES REC CENTER. | 2022 | 331 | 0 | 357 | 0 | 0 | 0 | 0 | 0 | 357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-107WBSK | Williamsbridge Oval const Skate Park- X104-115M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | WILLIAMSBRIDGE OVAL CONST SKATE PARK, BRONX | WILLIAMSBRIDGE OVAL CONST SKATE PARK, BRONX | 2022 | 750 | 1325.38 | 0 | 0 | 0 | 89 | 0 | 0 | 1414.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108EWNP | Ewen Park Installation of adult fitness equipment(X019-119M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 108 | P-D021 |  | JOHNSON AV, W 232 ST, RIVERDALE AVE IN THE BRONX | ADULT FITNESS EQUIPMENT AT EWEN PARK -- INSTALLATION OF ADULT FITNESSEQUIPMENT AT EWEN PARK | 2022 | 910 | 165 | 601 | 200 | 0 | 0 | 0 | 0 | 966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108EWPK | Ewen Park - Reconstruct. Staircase | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 108 | P-D021 |  | JOHNSON AVENUE, WEST 232 STREET AND RIVERDALE AVENUE, BOROUGH OF BRONX | EWEN PARK - RECONSTRUCTION OF STAIRCASE | 2022 | 4924 | 0 | 308 | 0 | 1702 | 1990 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108FTFR | Washington's Walk Fort Four Plgd comfort station- X038-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-X245 P-D021 P-0505 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | RESERVOIR AVENUE & SEDWICK AVENUE | CONSTRUCT NEW COMFORT STATION | 2022 | 700 | 388.94 | 3297 | 0 | 289 | 0 | 0 | 0 | 3974.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108HHPK | Henry Hudson Park basketball court renovation (X080-115M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | HENRY HUDSON PARK, BRONX | HENRY HUDSON PARK BASKETBALL COURT RENOVATION | 2022 | 1000 | 1145.77 | 0 | 0 | 0 | 200 | 0 | 0 | 1345.77 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 1500
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108MHDR | Marble Hill Playground - Dog Run | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 108 | P-D021 |  |  | MARBLE HILL PLAYGROUND - DOG RUN | 2022 | 115 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108MUSE | Van Cortlandt Park -Museum- New perimeter Fencing | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 100 | P-D021 |  | BOROUGH OF BROOKLYN | VAN CORT HOUSEE MUSEUM-NEW PERIMETER FENCING | 2022 | 3308 | 0 | 0 | 0 | 1354 | 670 | 676 | 0 | 2700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108MUSM | Van Cortlandt Park - House Museum Renovation | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 100 | P-0245X |  |  | VAN CORTLANDT PARK - HOUSE MUSEUM RENOVATION | 2022 | 4650 | 0 | 325 | 0 | 1975 | 2250 | 0 | 0 | 4550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108RIVE | RIVERDALE PARK-WETLANDS & SLOPES / X142-101M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 108 | P-0245X | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HUDSON RIVER, W 254 ST, PALISADE AVE, W 232 ST | RECONSTRUCTION OF A FRESHWATER WETLAND AND THE ADJACENT SLOPES | 2022 | 243 | 157.55 | 0 | 0 | 0 | 0 | 0 | 0 | 157.55 | 0 | 0 | 0 | 0 | 180 | 0 | 0 | 180
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SKTE | Van Cortlandt Park - Skate park & Basketballl cou(X092-114M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 108 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | SKATE PARK @ VAN CORTLANDT PARK | SKATE PARK PROJECT | 2022 | 1400 | 1691.07 | 0 | 1 | 0 | 102 | 0 | 0 | 1794.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SPBC | Seton Park Basketball Court Recon (X201-220M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 P-D018 P-0245X P-X245 P-1250 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | SETON PARK BASKETBALL COURT RECON (X201- | 2022 | 210 | 302.08 | 0 | 0 | 2083 | 2240 | 0 | 0 | 4625.08 | 0 | 0 | 0 | 210 | 0 | 0 | 0 | 210
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108SPDU | Spuyten Duyvil Park - pond restoration- X171-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 108 | P-D021 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PALISADE AVENUE, JOHNSON AVENUE AND EDSALL AVENUES | POND RESTORATION | 2022 | 170 | 976.78 | 0 | 0 | 0 | 141 | 0 | 0 | 1117.78 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 600
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCBD | Van Cortlandt Pk. Tot Lot Recon (X092-115M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | VAN CORTLANDT PARK CONST OF PLGD ON BDWAY, BRONX | VAN CORTLANDT PARK CONST OF PLGD ON BDWAY, BRONX | 2022 | 2263 | 3234.73 | 40 | 0 | 0 | 40 | 0 | 0 | 3314.73 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 500
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCIW | Van Cortlandt Park renovate Indian Fields (X092-116M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-1018 P-D021 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | VAN CORTLANDT PARK RENOVATE INDIAN LAKE & WOODLAWN, BRONX | VAN CORTLANDT PARK RENOVATE INDIAN LAKE & WOODLAWN, BRONX | 2022 | 1500 | 2081.95 | 25 | 843 | 0 | 0 | 0 | 0 | 2949.95 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108VCPT | Van Cortlandt Park Trails Recon (X092- | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0088 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | VAN CORTLANDT PARK TRAILS RECON (X092- | 2022 | 543 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 543 | 543
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WDLN | WOODLAWN PARK RENOVATIONS X092-121M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 108 | P-D021 |  | WOODLAWN PLAYGROUND LIES WITHIN VAN CORTLANDT PARK, NEAR VAN CORTLANDT PARK EAST AND EAST 239TH STREET, AND TAKES ITS NAME FROM THE ADJACENT NEIGHBORHOOD AND CEMETERY. | WOODLAWN PARK -- FUNDING FOR WOODLAWN PARK RENOVATIONS | 2022 | 250 | 184 | 48 | 1953 | 359 | 2340 | 0 | 0 | 4884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-108WWST | Strong Street Plg Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 P-X245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STRONG STREET PLAYGROUND  RECONSTRUCTION OF PLAYGROUND | 2022 | 1200 | 295.98 | 32 | 0 | 1638 | 1370 | 0 | 0 | 3335.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109NOBE | Noble Playground Reconstruction (X123-119M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 |  | NOBLE AVE. BET. BRONX RIVER AV AND E 177 ST IN THE BRONX | NYC PARKS - NOBLE PLAYGROUND -- NOBLE PLAYGROUND RECONSTRUCTION | 2022 | 3000 | 250 | 1593 | 713 | 194 | 0 | 0 | 0 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-109PAR2 | Parque de los Ninos Ph II - track & BField X004A-114M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 109 | P-X245 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PARQUES DE LOS NINOS, BRONX | INSTALLATION OF RUNNING TRACK AND MULTIPURPOSE BALL FIELDS | 2022 | 2000 | 4171.38 | 0 | 0 | 0 | 254 | 0 | 0 | 4425.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110CCCS | Co-Op City Park - Comfort Station | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0505 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CO-OP CITY PARK - COMFORT STATION | 2022 | 4772 | 159 | 0 | 0 | 0 | 0 | 0 | 3500 | 3659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110CCTY | Co-Op City Park | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0245X | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CO-OP CITY PARK | 2022 | 14320 | 25 | 0 | 0 | 0 | 0 | 0 | 10500 | 10525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110CIDR | City Island Dog Run | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CITY ISLAND DOG RUN | 2022 | 840 | 109 | 0 | 0 | 0 | 300 | 0 | 0 | 409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110EXPA | ORCHARD BEACH BATHHOUSE -- X039-102M/402M | BEACHES AND BOARDWALKS | 110 | P-X715 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | ORCHARD BEACH AT PELHAM BAY PARK, BRONX | RECONSTRUCTION OF PORTIONS OF THE BATH HOUSE AT ORCHARD BEACH IN PELHAM BAY PARK | 2022 | 755 | 557.43 | 0 | 0 | 0 | 86 | 0 | 0 | 643.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110FLAG | Ferry Point Park - Flagpole at 911 Memorial Hilltop Grove | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 110 | P-D021 |  |  | FERRY POINT PARK - FLAGPOLE AT 911 MEMORIAL HILLTOP GROVE | 2022 | 1050 | 150 | 20 | 0 | 930 | 300 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110MAN2 | Bartow Mansion Structural Stabilization&Carriage House Roof | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 P-X245 P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | BARTOW PELL MANSION STRUCTURAL STABILIZATION AND CARRIAGE HOUSE ROOF RECONSTRUCTION | 2022 | 142 | 0 | 318 | 0 | 500 | 546 | 0 | 0 | 1364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110ODFA | Owen Dolen Rec. Center: Fire Alarm Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 110 | P-0506 |  | 2551 WESTCHESTER AVENUE, BRONX. | FIRE ALARM RECONSTRUCTION AT OWEN DOLEN REC. CENTER. | 2022 | 280 | 0 | 309 | 0 | 0 | 0 | 0 | 0 | 309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110PFIT | Pelham bay Park - construction of fitness area X039-213M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 110 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PELHAM BAY PARK, BOROUGH OF THE BRONX | CONSTRUCTION OF FITNESS CENTER IN PELHAM BAY PARK | 2022 | 500 | 1199.18 | 0 | 0 | 0 | 79 | 0 | 0 | 1278.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-110PSKT | PELHAM BAY PK- Renovation of Skate Park (X039-220M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 110 | P-D021 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | HUTCHINSON RIVER, LONG ISLAND SOUND BET. BRONC COUNTY LINE AND MIDDLETOWN RD., WATT AVE., IN THE BRONX | PELHAM BAY PARK- RENOVATION OF SKATE PARK | 2022 | 3818 | 361.5 | 0 | 0 | 0 | 2770 | 0 | 0 | 3131.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111BPWF | Bronx PK- Installation of a water fountain X002-320M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 106 111 | P-D021 |  | BURKE AVE., E. 180 ST. BET. DR. KAZAMIROFF BLVD., SOUTHERN BLVD. AND BRONX PARK E., UNIONPORT RD. IN THE BRONX | BRONX PK- INSTALLATION OF A WATER FOUNTAIN | 2022 | 250 | 64 | 4 | 286 | 0 | 0 | 0 | 0 | 354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111ESPG | Eastchester Playground | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 111 | P-0245X |  | ADEE AVENUE AT TENBOECK AVENUE, BOROUGH OF BROOKLYN | EASTCHESTER PLAYGROUND - PLAYGROUND REDEVELOPMENT | 2022 | 5970 | 0 | 0 | 0 | 2430 | 0 | 2420 | 0 | 4850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111FFBB | FRISCH FIELD IN BRONX PK- RENO OF BBALL FIELD | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-D021 |  | BURKE AVE., E. 180 ST. BET. DR. KAZAMIROFF BLVD., SOUTHERN BLVD. AND BRONX PARK E., UNIONPORT RD., IN THE BRONX | FRISCH FIELD IN BRONX PARK- RENO OF BASEBALL FIELD | 2022 | 2500 | 171 | 86 | 0 | 2686 | 2770 | 0 | 0 | 5713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111LPFE | Cons. of Adult Fitness Equip in Colucci Pk. (X122-117M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0245X | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CONS. OF ADULT FITNESS EQUIP IN LORETO PK. (X122- | 2022 | 1299 | 1488.72 | 0 | 38 | 0 | 0 | 0 | 0 | 1526.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111LRTO | Loreto Park - Recon Soccer field Asphalt to Turf (X163-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0245X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | LORETO PARK - RECON SOCCER FIELD ASPHALT TO TURF (X163- | 2022 | 1500 | 1005.34 | 150 | 0 | 0 | 0 | 0 | 0 | 1155.34 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 1300
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111VCPE | PWOB - Van Cortlandt Park Broadway Entrance Recon- X092-217M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | VAN CORTLANDT PARK BROADWAY ENTRANCE RECON | 2022 | 5040 | 6784.66 | 26 | 0 | 0 | 92 | 0 | 0 | 6902.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-111ZIMP | Zimmerman Playground Basketball Court Recon.-X087-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ZIMMERMAN PLAYGROUND BASKETBALL COURT RECON. | 2022 | 500 | 42.72 | 0 | 0 | 0 | 1612 | 0 | 0 | 1654.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112AGNS | Agnes Haywood Park - basketball court & park house X169-114M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 112 | P-D021 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | IN BRONX | AGNES HAYWOOD PK RENOVATE BASKETBALL CT & PKHOUSE | 2022 | 650 | 3800.84 | 0 | 0 | 0 | 191 | 0 | 0 | 3991.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112LACE | BX River Shoelace Pk- Recon of Paths & Entrance (X004-117M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | THE SHOELACE PARK LINK IS A MULTI-BENEFIT PROJECT TO ENHANCE PEDESTRIAN AND BICYCLE CIRCULATION IN A 1.2-MILE LINK IN THE BRONX RIVER GREENWAY, TREAT STORMWATER RUNOFF FROM ADJACENT ROADWAYS INCLUDING THE BRONX RIVER PARKWAY TO REDUCE POLLUTION IN THE BRONX RIVER, AND COMMEMORATE THE HISTORIC ROUTE OF THE BRONX RIVER PARKWAY, IMPLEMENTING ELEMENTSOF THE MASTER PLAN FOR SHOELACE PARK ON THE BRONX RIVER GREENWAY. | 2022 | 3150 | 3029.74 | 310 | 0 | 0 | 0 | 0 | 0 | 3339.74 | 2520 | 0 | 0 | 0 | 0 | 0 | 0 | 2520
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112SETW | Seton Falls Park Walkways Renovations X092-113M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 112 | P-D021 P-X245 |  | E. 233 ST. BET. SETON AVE. AND BAYCHESTER AVE. IN THE BRONX | SETON FALLS PARK WALKWAYS RENOVATIONS IN THE BRONX | 2022 | 1181 | 81 | 975 | 206 | 0 | 0 | 0 | 0 | 1262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112SHLP | Shoelace Park - Fitness Equipment | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 100 | P-D021 |  | BOROUGH OF BRONX | SHOELACE PARK - CONSTRUCT FITNESS AND ADULT EXERCISE EQUIPMENT | 2022 | 1974 | 0 | 0 | 0 | 780 | 770 | 0 | 0 | 1550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-112WKFD | Wakefield Park Reconstruction (X188-116M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-X245 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | WAKEFIELD PARK RECON | 2022 | 200 | 3817.94 | 102 | 50 | 0 | 680 | 0 | 0 | 4649.94 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-113LLSF | Resurfacing of little league fields and sports field in CD13 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | UNKNOWN | RESURFACING OF LITTLE LEAGUE FIELDS AND OTHER SPORTS FIELDS IN COUNCIL DISTRICT 13 | 2022 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-117CPBM | Crotona Park- Install Bluelight Monitors in CD17 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 103 | P-D021 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CROTONA PARK NORTH TO SOUTH, FULTON AV TO SOUTHERN BLVD AND CROTONA PARK EAST IN THE BRONX | NYC PARKS (CROTONA PARK) -- FUNDS WILL GO TO INSTALL BLUELIGHT MONITORS THROUGHOUT CROTONA PARK IN CD17 | 2022 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-118FOXP | FOX PLAYGROUND C/S X247-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 |  |  | FOX PLAYGROUND C/S | 2022 | 3500 | 3367.51 | 472 | 0 | 0 | 0 | 0 | 0 | 3839.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ANCH01 | Anchor Pk St.Mary's Park Ballfields &Dog Run Recon X045-318M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-0568 P-C024 | PROJECT DELAYED DUE TO UNFORESEEN HAZARDOUS CONDITION | ST MARY'S STREET BETWEEN ST ANNS'S AVE AND JACKSON AVE BRONX | ANCHOR PARK ST. MARY'S PARK BALLFIELDS AND DOG RUN RECON | 2022 | 10450 | 9142.24 | 31 | 0 | 0 | 338 | 0 | 0 | 9511.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ANCH02 | St. Mary's Anchor Pk Ph. 2-Amphi, Plaza &Pathways X045-218M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0568 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ST. MARY'S ANCHOR PARK PHASE 2-AMPHITHEATER, PLAZA &PATHWAYS | 2022 | 17380 | 17551.45 | 487 | 0 | 0 | 2283 | 0 | 0 | 20321.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ARAELV | Bronx Aramark building for elevator - X360-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 |  | ARAMARK BUILDING, BRONX | BRONX ARAMARK DELEVATOR | 2022 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ARAMEZ | Mezzanine dsgn & cons Aramark Bldg Shops & store X360-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 P-0505 |  | 850 EAST 138TH STREET, BRONX | MEZZANINE DESIGN AND CONSTRUCTION AT ARAMARK BUILDING (CWS SHOPS AND STOREHOUSE) | 2022 | 559 | 164 | 0 | 409 | 0 | 0 | 0 | 0 | 573 | 52.62 | 0 | 97 | 0 | 0 | 0 | 0 | 149.62
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BOLTPK | Bolton Park Wetland Restore. & PK Con. | LAND ACQUISITION AND TREE PLANTING | 100 | P-D021 P-1245 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BOROUGH OF BROOKLYN | BOLTON PARK -WETLAND | 2022 | 7009 | 0 | 220 | 0 | 1780 | 0 | 5400 | 0 | 7400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BRXPK1 | Bronx Park, bet. Zones 3 & 5A, Priority 1 XG-419M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 |  | BRONX | BRONX PARK, BET. ZONES 3 & 5A, PRIORITY 1 | 2022 | 600 | 30 | 400 | 200 | 0 | 0 | 0 | 0 | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BRXPK2 | Bronx Park, bet. Zones 3 & 5A, Priority 2 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 |  | BRONX | BRONX PARK, BET. ZONES 3 & 5A, PRIORITY 2 | 2022 | 250 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BRXPK3 | Bronx Park, Zone 1 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 |  | BRONX | BRONX PARK, ZONE 1 | 2022 | 450 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BWBXP1 | Reconstruction of plgrs, Borough of Bronx (XG-508M) | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | VARIOUS IN THE BRONX | RC OF PLGRDS | 2022 | 1236 | 1609.89 | 0 | 0 | 0 | 0 | 0 | 0 | 1609.89 | 81.5 | 0 | 0 | 0 | 0 | 0 | 130 | 211.5
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1BWRCTR | WEST BX RECR CTR HVAC RC- X261-116M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-1250 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | BX REC CTRS HVAC RC | 2022 | 1228 | 1320.66 | 0 | 0 | 0 | 133 | 0 | 0 | 1453.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CASHIL | Castle Hill Park - reconstruction of pier X007-113M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 109 | P-X245 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | HART ST., CASTLE HILL AVE | CASTLE HILL PARK - RECONSTRUCTION OF PIER | 2022 | 696 | 1041.93 | 0 | 0 | 0 | 50 | 0 | 0 | 1091.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CHARLG | Charlton Garden - Phase II X086-108M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 103 | P-X245 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | BRONX | CHARLTON GARDEN RECONSTRUCTION | 2022 | 1050 | 1696.74 | 0 | 0 | 0 | 230 | 0 | 0 | 1926.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CHRLRF | French Charley's Playground Comfort Station Roof Reconstruct | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1249 P-1250 P-1018 |  | FRENCH CHARLEY'S PLAYGROUND COMFORT STATION, THE BRONX | FRENCH CHARLEY'S PLAYGROUND COMFORT STATION ROOF RECONSTRUCTION | 2022 | 212 | 0 | 0 | 212 | 0 | 0 | 0 | 0 | 212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPI134 | CPI PH2 - Playground 134 Reconstruction (X138-117M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CPI PH3 - PLAYGROUND 134 RECONSTRUCTION (X138- | 2022 | 3270 | 5333.82 | 245 | 0 | 0 | 192 | 1843 | 0 | 7613.82 | 1999.99 | 0 | 0 | 0 | 0 | 0 | 0 | 1999.99
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIBR2 | CPI PH2-174TH St.Plgd/BX River House-Plgd/Mini Pool X159-118 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CPI PH2 - 174TH ST. PLGD/BX RIVER HOUSE-PLAYGROUND/MINI POOL | CPI PH2 - 174TH ST. PLGD/BX RIVER HOUSE-PLAYGROUND/MINI POOL | 2022 | 0 | 4634.35 | 0 | 0 | 0 | 521 | 0 | 0 | 5155.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIBR3 | CPI PH2-174TH St.Plgd/BX River House- Comfort Stat X159-218M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 |  |  | CPI PH2-174TH ST. PLGD/BX RIVER HOUSE- COMFORT STATION | 2022 | 1516 | 1594.01 | 417 | 0 | 0 | 0 | 0 | 0 | 2011.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIDVP | CPI-CHIEF DENNIS L. DEVLIN PK RECON | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 109 | P-1018 |  | ELLIS AVENUE, OLMSTEAD AVENUE, AND CROSS BRONX SERVICE ROAD NORTH | CHIEF DENNIS L. DEVLIN PARK RECONSTRUCTION | 2022 | 3525 | 0 | 0 | 0 | 1505 | 1495 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIHCS | CPI - HORESHOE COMFORT STATION | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 |  |  | HORSESHOE COMFORT STATION | 2022 | 1820 | 0 | 0 | 0 | 705 | 695 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIHNT | CPI PH 1- Hunts Point Playground (X113-115M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | HUNTS POINT PLAYGROUND, BRONX | CPI - HUNTS POINT PLAYGROUND | 2022 | 1500 | 4200.3 | 0 | 0 | 0 | 41 | 0 | 0 | 4241.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIHSP | CPI - HORESHOE PLGD | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 |  |  | HORSESHOE PLGD | 2022 | 4818 | 0 | 0 | 0 | 1980 | 1970 | 0 | 0 | 3950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIPMT | CPI PH 2 - Plimpton Playground (X148A2-117M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CPI PH 3 - PLIMPTON PLAYGROUND (X1482- | 2022 | 4436 | 4359.28 | 0 | 0 | 0 | 626 | 0 | 0 | 4985.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIPNT | CPI - PONTIAC PLGD X207 | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 |  |  | PONTIAC PLGD | 2022 | 9215 | 0 | 380 | 0 | 3430 | 3790 | 0 | 0 | 7600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CPIPRO | CPI Phase 2- Prospect Playground-X148H1-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 | PROJECT DELAYED DUE TO UNAVAILABILITY OF PRODUCT |  | CPI PHASE 2- PROSPECT PLAYGROUND | 2022 | 6266 | 5712.06 | 1364 | 72 | 0 | 0 | 0 | 0 | 7148.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRNAPK | Crotona Park RC of the Nature Center X010-114M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 103 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | CROTONA PARK, BRONX | CROTONA PARK NATURE CTR - PH I EXTER & INTER RENOV | 2022 | 500 | 4299.32 | 0 | 0 | 0 | 174 | 0 | 0 | 4473.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRO17A | Williamsbridge Oval Park - Recr Bldg X104-207M/507M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 107 | WM-0011 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BX | PORTION OF PARK WORK TO INCLUDE: PERIMETER WALLS & FENCING WITH GATES, TRACK & FIELD, PLAYGROUND #1, PLAYGROUND #3, SENIOR AREA, ROLLER HOCKEY AREA/SKATE PARK, SLOPE STABILIZATION AND PROMENADE AND RECREATION CENTER SITE WORK. | 2022 | 3480 | 6827.43 | 210 | 0 | 0 | 0 | 0 | 0 | 7037.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROALG | CROTONA PARK INDIAN LAKE ALGAE REDUCTION | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-X245 P-0822 |  |  | CROTONA PARK ALGAE REDUCTION AT INDIAN LAKE IN THE BRONX | 2022 | 500 | 0 | 0 | 575 | 0 | 0 | 0 | 0 | 575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT13 | VC PK- Recon Headhouse & Demolish Greenhouse X092-207M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 107 108 112 | WM-0011 P-0245X | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BX | THE UPGRADE AND EXPANSION OF THE EXISTING NURSERY. WORK TO INCLUDE CONSTRUCTION AND RENOVATION OF COLD FRAMES, GREEN HOUSES, LOADING DOCKS, IRRIGATION LINES, SEWER LINES AND ACCESS WAY... 12.22.21 TRANS $90K FR P-1BCSPL1 & $15K FR P-1BCSHV1..1.12.22 TRANS $450K FR P-1PELSHO, $475K FR P-1CROT68 & $225K FR P-1CROT14..CONT FR PJNO 2.23.21 P-1CROT28,P-1CROT32,P-1CROT38, P-1CROT45, P-1CROT49, P-1CROT56, P-1CROT64, P-1CROT66, P-1CROT67, P-1CROUL6.. 3.2.22 TRANS $541K FR P-1CROT06,19,36 & P-1CROUL1.. | 2022 | 3001 | 1158.17 | 7647 | 2320 | 0 | 3235 | 0 | 0 | 14360.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT14 | AQUEDUCT WALK - COMF. STATION X001-207M/507M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 105 | WM-0011 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BX | CONSTRUCTION OF A COMFORT STATION WITH AN OPERATIONS COMPONENT | 2022 | 1800 | 1921.71 | 118 | 0 | 0 | 0 | 0 | 0 | 2039.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CROT68 | MULLALY PARK - SKATE BUILDING X034-207M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 199 | WM-0011 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | MULLALY PARK - BOROUGH OF THE BRONX | RECONSTRUCTION OF THE SKATE BUILDING AT MULLALY PARK | 2022 | 1782 | 3148.41 | 54 | 0 | 0 | 0 | 0 | 0 | 3202.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRPOHS | Crotona Park - pool towers X010-210MA3 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 103 | P-D021 P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | CROTONA PARK POOL HOUSE | CROTONA PARK POOL HOUSE - RENOVATION | 2022 | 500 | 3330.47 | 0 | 0 | 0 | 159 | 0 | 0 | 3489.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRTMAL | Crotona Parkway Mall Recon XG-419M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BRONX | CROTONA PRKWAY MALL RECON | 2022 | 558 | 10 | 0 | 0 | 558 | 0 | 0 | 0 | 568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1CRTORF | Crotona Park Pool Roof Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1249 |  | THE BRONX | CROTONA PARK POOL ROOF RECONSTRUCTION | 2022 | 2870 | 50 | 0 | 0 | 1264 | 1262 | 0 | 0 | 2576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1DBPLYG | DANIEL BOONE PLAYGROUND - CONSTRUCT A PLAYGROUND | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 P-X245 |  |  | DANIEL BOONE PLAYGROUND - CONSTRUCT A SENSORY PLAYGROUND | 2022 | 3000 | 0 | 0 | 0 | 6200 | 0 | 6000 | 0 | 12200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1DCTMUL | Mullaly Park Rec Ctr Telecom Line Installation | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0931 |  | THE BRONX | MULLALY PARK RECREATION CENTER TELECOMMUNICATION LINE INSTALLATION | 2022 | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1DCTVCP | Van Cortlandt Park Museum Telecom Service Installation | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0931 |  | VAN CORTLANDT PARK MUSEUM | VAN CORTLANDT PARK MUSEUM TELECOM SERVICE INSTALLATION | 2022 | 550 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1DEPOT | Depot Place - portion of Harlem River greenway XG-31800-106M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 104 | P-X245 P-1018 | PROJECT DELAYED PENDING APPROVAL OF NECESSARY PERMITS | DEPOT PLACE GREENWAY PROJECT | DEPOT PLACE GREENWAY PROJECT | 2022 | 1015 | 1374.76 | 0 | 0 | 0 | 11 | 0 | 0 | 1385.76 | 2182.87 | 0 | 0 | 0 | 907 | 0 | 0 | 3089.87
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ECHOPK | Echo Park Playground and Sports Fields- X017-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 105 | P-D021 P-0245X P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECONSTRUCTION OF THE PLAYGROUND AND SPORTS FIELDS AT ECHO PARK IN THE BRONX. | 2022 | 5452 | 4884.32 | 23 | 0 | 0 | 674 | 0 | 0 | 5581.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1EDENPG | Edenwald PLGD - basketball & handball crts (X165-116MA) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 112 | P-X245 P-0245X P-1018 P-1008 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | EDENWALD PLAYGROUND, BRONX | EDENWALD PLAYGROUND - PHASE1 RECONSTRUCT BASKETBALL & HANDBALL COURTS | 2022 | 700 | 396.65 | 5 | 3976 | 0 | 0 | 0 | 0 | 4377.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1FACDCR | Crotona Park Pool Facade Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1249 P-1018 |  | CROTONA PARK POOL, THE BRONX | CROTONA PARK POOL FACADE RECONSTRUCTION | 2022 | 767 | 0 | 0 | 0 | 767 | 0 | 0 | 0 | 767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1FERPNT | Ferry Point Community Park - Adult Fitness Area | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-X245 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CONSTRUCTION OF ADULT FITNESS AREA - FERRY POINT COMMUNITY PARK - THEBRONX | 2022 | 400 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1FERRY8 | Ferry Point Park - Waterfront Park X126-116M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 110 | P-0720 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | FERRY POINT WATERFRONT | FERRY POINT WATERFRONT | 2022 | 20656 | 13058.95 | 0 | 0 | 0 | 3685 | 0 | 0 | 16743.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1GHPCSR | Grove Hill Playground-Comfort Station Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0505 |  |  | RECONSTRUCTION OF GROVE HILL PLAYGROUND COMFORT STATION | 2022 | 2114 | 1680.54 | 185 | 0 | 0 | 0 | 0 | 0 | 1865.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAFFP1 | Haffen Park - RC- Tennis & Basketball Court X196 | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-0245X |  | GUNTER AVENUE AND BURKE AVENUE, BOROUGH OF BRONX | HAFFEN PARK - RECONSTRUCTION OF TENNIS AND BASKETBALL COURTS | 2022 | 18400 | 0 | 864 | 0 | 8536 | 0 | 9000 | 0 | 18400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAFFP3 | Haffen Park - Fld House,Bathrooms, & Amphitheater | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-0245X |  | GUNTHER AVENUE AND HAMMERSLEY AVENUE, IN BRONX | HAFFEN PARK- FIELD HOUSE | 2022 | 12500 | 0 | 15 | 0 | 6485 | 0 | 6000 | 0 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAFFPL | Haffen Park Pool Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0245X |  | HAFFEN PARK POOL, THE BRONX | HAFFEN PARK POOL RECONSTRUCTION | 2022 | 10920 | 0 | 141 | 0 | 4159 | 0 | 4100 | 0 | 8400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAFFPT | HAFFEN PARK - CONSTRUCT ADULT FITNESS AREA | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-X245 P-D021 P-1018 P-0245X | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | CONSTRUCTION OF ADULT FITNESS AREA - HAFFEN PARK - THE BRONX | 2022 | 6020 | 200 | 830 | 0 | 6500 | 0 | 6200 | 0 | 13730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HAMMON | Hammond Cove Shoreline Stabilization and Restoration | LAND ACQUISITION AND TREE PLANTING | 100 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HAMMOND COVE SHORELINE STABILIZATION AND RESTORATION | 2022 | 1842 | 0 | 0 | 0 | 810 | 790 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HCMARI | Hammond Cove Marina | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 P-D721 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HAMMOND COVE MARIA | 2022 | 14020 | 62.45 | 0 | 0 | 358 | 0 | 0 | 0 | 420.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HGCVPR | PWOB-Hugh Grant Circle & Virginia Pk. Recon. XG-117MA | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HUGH GRANT CIRCLE & VIRGINIA PK. RECON. | 2022 | 7624 | 9868.52 | 306 | 0 | 0 | 914 | 0 | 0 | 11088.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HUNTPT | HUNTS POINT RECREATION CENTER - REPLACE GYMNASIUM FLOOR | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 100 | P-X245 P-D021 P-1249 |  |  | REPLACEMENT OF GYMNASIUM FLOOR AT HUNTS POINT RECREATION CENTER - THEBRONX | 2022 | 600 | 0 | 600 | 0 | 62 | 0 | 0 | 0 | 662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1HVMRCS | Havemeyer Playground C.S. | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0505 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HAVEMEYER PLAYGROUND COMFORT STATION | 2022 | 1698 | 146.85 | 1086 | 0 | 402 | 0 | 0 | 0 | 1634.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1JASPBB | JASPER BASEBALL STADIUM | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-D021 |  |  | JASPER BASEBALL STADIUM CONSTRUCTION, BRONX | 2022 | 500 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1LZDARF | Lozada Playground Comfort Station Roof Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1249 P-1250 |  | LOZADA PLAYGROUND COMFORT STATION, THE BRONX | LOZADA PLAYGROUND COMFORT STATION ROOF RECONSTRUCTION | 2022 | 70 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1MBRKCS | Millbrook Playground Comfort Station Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0505 P-1018 P-1250 |  | THE BRONX | MILLBROOK PLAYGROUND COMFORT STATION RECONSTRUCTION | 2022 | 1175 | 0 | 0 | 0 | 1175 | 16 | 0 | 0 | 1191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1MELRO | Melrose Commons URA Site 62 Park Development (X350-119M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0245X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | MELROSE COMMONS URA SITE 62 PARK DEVELOPMENT | 2022 | 5987 | 1254.49 | 5501 | 676 | 0 | 2274 | 0 | 0 | 9705.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1ORCHLN | ORCHARD BEACH - SOUTH LAWN RENOVATIONS | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-X245 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | ORCHARD BEACH - SOUTH LAWN RENOVATIONS | 2022 | 6000 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1OWEND2 | OWEN F. DOLEN PK GOLDEN AGE CTR X016-114M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 109 | P-X245 P-D021 P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | OWEN DOLAN REC CRT, BOROUGH OF THE BRONX | INSTALL NEW ROOF AND WATERPROOF OWEN DOLAN RECREATION CENTER | 2022 | 2485 | 2270.79 | 0 | 0 | 0 | 631 | 0 | 0 | 2901.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1OWEND3 | OWEN DOLEN RECREATION CENTER - X016-118M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-X245 P-D021 P-0506 |  |  | OWEN DOLEN RECREATION CENTER | 2022 | 1364 | 190.84 | 0 | 2343 | 0 | 0 | 0 | 0 | 2533.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PAVMOS | Mosholu Parkway Greenway Pavement Reconstruction (SoGR) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 P-D021 |  | THE BRONX | MOSHOLU PARKWAY GREENWAY PAVEMENT RECONSTRUCTION (SOGR) | 2022 | 1350 | 30 | 0 | 0 | 780 | 770 | 0 | 0 | 1580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PBEAST | Bronx Park East - Ped Access Ramp | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-D021 |  | BOROUGH OF BRONX | BRONX PARK EAST PEDESTRIAN ACCESS RAMP TO THE NY BOTANICAL GARDEN--ADA PROJECT FOR PEDESTRIAN | 2022 | 4924 | 0 | 308 | 0 | 1702 | 1990 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PDSMRC | PDF -St. Mary's Rec Ctr RC X045-115M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 100 | P-1018 P-0506 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BRONX | ST. MARY'S REC CTR | 2022 | 4000 | 938.35 | 7000 | 0 | 635 | 0 | 0 | 0 | 8573.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELBRV | Pelham parkway -connection to Bronx river greenwayX002-211M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 111 | P-0245X | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | PELHAM BAY PARKWAY CONNECTION TO BRONX RIVER GREENWAY | PELHAM BAY PARKWAY CONNECTION TO BRONX RIVER GREENWAY | 2022 | 300 | 999.39 | 0 | 0 | 0 | 0 | 0 | 0 | 999.39 | 2293.98 | 0 | 39 | 167 | 0 | 0 | 0 | 2499.98
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELHAM | Pelham Parkway Malls-Plaza"A" | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 100 | P-D021 |  | BOROUGH OF BRONX | PELHAM PARKWAY MALLS | 2022 | 6340 | 0 | 0 | 0 | 2580 | 2570 | 0 | 0 | 5150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PELSHO | Pelham Bay Park- Shoreline Recons. (X039-116M) | BEACHES AND BOARDWALKS | 100 | WM-0011 |  |  | THIS PROJECT WILL REMOVE INTRUSIVE INFRASTRUCTURE FROM THE NATURAL ROCKY SHORE OF PELHAM BAY PARK, RESTORE COASTAL HABITATS, AND IMPROVE PUBLIC ACCESS TO THE SCENIC BAY. | 2022 | 2867 | 3242.45 | 86 | 0 | 0 | 0 | 0 | 0 | 3328.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PNYFL5 | PlaNYC- Coop City ballfield - Irrigation Install X251-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 110 | P-0705 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | COOP CITY BALLFIELD, THE BRONX | COOP CITY BALLFIELD PATH, BLEACHER & GREEN AREA | 2022 | 360 | 984.49 | 0 | 0 | 0 | 74 | 0 | 0 | 1058.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PNYR07 | PLANYC- BX PK CHANNEL RESTORATION X002-214M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0822 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BOROUGH OF THE BRONX | TO REHABILITATE THE CHANNEL AROUND THE ISLAND IN THE BRONX FOREST TO FACILITATE TREE PLANTING AND FOREST RESTORATION. | 2022 | 1150 | 257.09 | 0 | 0 | 1956 | 0 | 0 | 0 | 2213.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1POECOT | POE COTTAGE - INSTALLATION OF ROOF & EXTERIOR RENOVATIONS | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 100 | P-X245 P-D021 |  |  | INSTALLATION OF ROOF & EXTERIOR RENOVATIONS AT POE COTTAGE IN THE BRONX | 2022 | 450 | 45 | 0 | 0 | 929 | 0 | 0 | 0 | 974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PTSNPK | Patterson Park (X155-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 P-D021 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | PATTERSON PARK | 2022 | 2200 | 4724.03 | -85 | 0 | 0 | 144 | 0 | 0 | 4783.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PUGSLY | PUGSLEY CREEK & SOUNDVIEW PARKS INSTALLATION OF BLUE LIGHT | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-X245 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PUGSLEY CREEK/ SOUNDVIEW PARK | PUGSLEY CREEK & SOUNDVIEW PARKS  INSTALLATION OF BLUE LIGHT HELP & FLASHCAMS | 2022 | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1PVMNTX | Pathways at Patterson, the Bronx | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 |  | THE BRONX | PATHWAYS AT PATTERSON | 2022 | 330 | 0 | 330 | 0 | 0 | 0 | 0 | 0 | 330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RNQ22A | Ranaqua Facade Safety Repairs | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 |  |  | "PARKS INSPECTIONS HAVE IDENTIFIED SAFETY CONDITIONS RELATED TO THE RANAQUA STOREHOUSE AT THE DISPATCH OFFICE AND BATHROOM AREAS, RESULTING IN CLOSURE OF BOTH THESE FACILITIES. THE CLOSURE OF THE DISPATCH OFFICE HAS RELOCATED STAFF AWAY FROM THE CENTER OF THE COMPOUND, RESULTING IN REDUCED ABILITY TO SURVEIL THE AREA. CONSEQUENTLY, THERE HAS BEEN AN INCREASE IN TRESPASSERS AND STOLEN MATERIAL IN THE AREA. IF THE EXISTING CONDITION AND UNDERLYING CAUSES ARE NOT ADDRESSED, STRUCTURE WILL FACE CONTINUED DETERIORATION. THIS WILL RESULT IN EXPANDING THE AREA AND FACILITIES THAT ARE CLOSED OFF DUE TO INCREASED RISK TO HEALTHAND SAFETY. WATER INFILTRATION WILL CONTINUE TO CAUSE DAMAGE TO THE FA×ADE, AND MAY EVENTUALLY POSE A RISK TO OTHER BUILDING COMPONENTS. USE OF THESE FACILITIES CANNOT RESUME UNTIL THE LIFE SAFETY CONCERNS AS | 2022 | 17408 | 0 | 2227 | 0 | 11249 | 0 | 13475 | 0 | 26951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RNQARF | Ranaqua Roof Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1249 PU-0025 P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | RANAQUA, BOROUGH OF THE BRONX | RECONSTRUCTION OF RNAQUA ROOF | 2022 | 2500 | 302 | 4000 | 0 | 149 | 0 | 0 | 0 | 4451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1RNQRMP | Reconstruction of Ranaqua M&O Storehouse Ramp | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | RECONSTRUCTION OF RANAQUA M&O STOREHOUSE RAMP | 2022 | 3275 | 533.14 | 0 | 0 | 1582 | 1984 | 0 | 0 | 4099.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1SDVREC | Construction of a New Recreation Center at Soundview Park | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 100 | P-0506 |  |  | CONSTRUCTION OF A NEW RECREATION CENTER AT SOUNDVIEW PARK | 2022 | 90000 | 0 | 0 | 9000 | 0 | 0 | 81000 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1SHOEB1 | Shoelace Park-BX Green Infrastructure Constr.X004- | LAND ACQUISITION AND TREE PLANTING | 100 | P-1018 |  | SHOELACE PARK-BX GREEN INFRASTRUCTURE CONSTR.X004- | SHOELACE PARK-BX GREEN INFRASTRUCTURE CONSTR.X004- | 2022 | 92 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 92 | 0 | 0 | 0 | 0 | 92
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1SPACET | SpaceTime Playgroun Reconstruction (X221-121M) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | WP-0169 P-D021 |  |  | SPACE TIME PLAYGROUND RENOOVATION OF SYNTHETIC TURF, BRONX | 2022 | 500 | 100 | 0 | 584 | 1862 | 2169 | 0 | 0 | 4715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1SPC21A | Pelham Bay Park Forest Tree Replacement | LAND ACQUISITION AND TREE PLANTING | 100 | WM-0001 |  | BRONX | FY 21 PELHAM BAY PARK FOREST | 2022 | 3139 | 0 | 0 | 2880 | 0 | 0 | 0 | 0 | 2880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1STFPEL | Synthetic Turf Field Reconstruction at Pelham Bay | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0510 P-0245M |  | PELHAM BAY PARK, BRONX | SYNTHETIC TURF FIELD RECONSTRUCTION AT PELHAM BAY | 2022 | 485 | 0 | 1134 | 0 | 0 | 0 | 0 | 0 | 1134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1STJMPK | St. James Park | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 |  | BRONX | ST. JAMES PARK | 2022 | 400 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1STR21A | Bronx Street Tree Planting - XG-321M | LAND ACQUISITION AND TREE PLANTING | 100 | P-0822 |  | BRONX BOROUGH WIDE | TREE PLANTING IN BOROUGH OF BRONX | 2022 | 129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 10 | 0 | 0 | 0 | 0 | 101
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE20B | FY20 Street Trees Bronx CB's 5-8 XG-219M | LAND ACQUISITION AND TREE PLANTING | 100 | P-D822 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | FY20 STREET TREES BRONX CB'S 5-8 XG-219M | FY20 STREET TREES BRONX CB'S 5-8 XG-219M | 2022 | 2800 | 155 | 0 | 0 | 0 | 106 | 0 | 0 | 261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE20R | Bronx Street Tree Planting - XG-319MR cb9-12 | LAND ACQUISITION AND TREE PLANTING | 100 | P-1018 P-0822 |  | BOROUGH OF BRONX | RENEWAL CONTRACT - BRONX STREET TREE | 2022 | 2745 | 0 | 473 | 0 | 0 | 0 | 0 | 0 | 473 | 0 | 2197 | 0 | 0 | 0 | 0 | 0 | 2197
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TRE21A | FY21 Street Trees Bronx CB's 1-4,9,10 XG- | LAND ACQUISITION AND TREE PLANTING | 100 | P-0822 |  | BOROWIDE | FY21 STREET TREES BRONX CB'S 1-4,9,10 | 2022 | 2631 | 145 | 0 | 2631 | 0 | 0 | 0 | 0 | 2776 | 0 | 294 | 0 | 0 | 0 | 0 | 0 | 294
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TREL21 | FY21 Street Trees BX CB's5-8,11,12 (3Y) | LAND ACQUISITION AND TREE PLANTING | 100 | P-1018 P-0822 |  | BRONX | FY21 STREET TREES BX CB'S5-8,11,12 (3Y) | 2022 | 6719 | 120 | 7881 | 0 | 0 | 0 | 0 | 0 | 8001 | 0 | 2882 | 0 | 0 | 0 | 0 | 0 | 2882
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TREP22 | Bronx ParkTree Planting FY22-CB | LAND ACQUISITION AND TREE PLANTING | 100 | P-1018 PV-0176 WM-0006 P-0822 |  | BOROUGH OF THE BRONX | BRONX PARK TREE PLANTING | 2022 | 3824 | 0 | 0 | 3379 | 0 | 0 | 0 | 0 | 3379 | 0 | 0 | 445 | 0 | 0 | 0 | 0 | 445
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1TREREC | Construction of a New Recreation Center at Tremont Park | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 100 | P-0506 |  |  | CONSTRUCTION OF A NEW RECREATION CENTER AT TREMONT PARK | 2022 | 90000 | 0 | 0 | 9000 | 0 | 0 | 81000 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1UNVPTH | University Hill Path Pavement Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 |  | UNIVERSITY HILL PATH PAVEMENT RECONSTRUCTION IN THE BRONX | UNIVERSITY HILL PATH PAVEMENT RECONSTRUCTION | 2022 | 220 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VCSHND | Van Cortlandt Park, Shandler Rec. Area, XG-419M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | BRONX | VAN CORTLANDT PARK, SHANDLER REC. AREA, ALL 3 PRIORITIES | 2022 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VCSTDM | Pavement | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 |  | BRONX | PAVEMENT | 2022 | 250 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VCTRAL | Van Cortlandt's Tail | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 |  | BRONX | VAN CORTLANDT'S TAIL | 2022 | 700 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1VNFPOL | Van Nest Flag Pole X093-116M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 P-X245 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | VAN NEST FLAG POLE | 2022 | 60 | 648.48 | 17 | 0 | 0 | 30 | 0 | 0 | 695.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WDLNCS | Woodlawn Playground C.S X092-119M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0505 P-D021 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | WOODLAWN PLAYGROUND COMFORT STATIONS | 2022 | 1554 | 232 | 0 | 0 | 1579 | 0 | 0 | 0 | 1811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WDLNSS | Woodlawn Plgd- Recon of Spray Shower X092-118M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-X245 P-0935 |  | WOODLAWN PLAYGROUND, VAN CORTLANDT PARK | WOODLAWN PLAYGROUND - SPRAY SHOWER | 2022 | 1296 | 1159.24 | 91 | 0 | 0 | 0 | 0 | 0 | 1250.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WKFLRF | Wakefield Playground Comfort Station Roof Reconstruction | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1249 |  | WAKEFIELD PLAYGROUND COMFORT STATION IN THE BRONX | WAKEFIELD PLAYGROUND COMFORT STATION ROOF RECONSTRUCTION | 2022 | 342 | 0 | 0 | 262 | 0 | 0 | 0 | 0 | 262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WPSOTO | Sotomayor Houses - Construction of Open Space | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 |  |  | NYCHA SOTOMAYOR HOUSES OPEN SPACE CONSTRUCTION | 2022 | 1900 | 22 | 0 | 0 | 955 | 945 | 0 | 0 | 1922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1WPWATS | Watson Houses - Construction of Open Space | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 100 | P-1018 |  |  | NYCHA WATSON HOUSES OPEN SPACE CONSTRUCTION | 2022 | 2500 | 365 | 0 | 2500 | 0 | 0 | 0 | 0 | 2865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | P-1YANK22 | Bronx Children's Museum CNYG-219M | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 100 | P-1018 |  | BOROUGH OF BRONX | BRONX CHILDRENS MUSEUM | 2022 | 1700 | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-06 | SANDY - Ferry Point Park Type 3 X126-115M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BRONX | FERRY PT PK TYPE 3 | 2022 | 1924 | 284.09 | 38 | 0 | 0 | 0 | 0 | 332 | 654.09 | 782.3 | 0 | 0 | 0 | 0 | 0 | 1465 | 2247.3
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-10 | Hammond Cove Marina X310-117M | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | HAMMOND'S COVE MARINA | 2022 | 1187 | 264.16 | 0 | 0 | 412 | 0 | 0 | 0 | 676.16 | 433.44 | 0 | 0 | 2346 | 0 | 0 | 0 | 2779.44
20220309 | BRONX | 846 | DEPT OF PARKS AND RECREATION | SANDY1-11 | Pelham Bay Landfill | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-1018 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | HUTCHINSON RIVER, LONG ISLAND SOUND BET. BRONC COUNTY LINE AND MIDDLETOWN RD., WATT AVE. IN THE BRONX | SANDY - PELHAM BAY LANDFILL | 2022 | 10750 | 334.88 | 0 | 0 | 990 | 0 | 0 | 0 | 1324.88 | 763.99 | 0 | 0 | 8911 | 0 | 0 | 0 | 9674.99
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | ACEDCA433 | DCLA: Wildlife Conservation Society: Bronx Zoo Roofs | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 107 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROOF REPLACEMENT FOR THE AQUATIC BIRD HOUSE BUILDING AT THE BRONX ZOO. NEW ROOF WILL USE ENERGY EFFICIENT MATERIALS INCL. UP TO 4 INCHES OF INSULATION. | 2022 | 688 | 0 | 688 | 0 | 0 | 0 | 0 | 0 | 688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | BBJ-X | Borough Based Jails New Bronx Detention Facility | New Jail Facilities |  | C-0114 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CONSTRUCTION OF NEW BRONX FACILITY | 2022 | 2073288 | 0 | 65891 | 100385 | 496825 | 379890 | 400741 | 499556 | 1943288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75EWAMKC | Emergency Work for AMKC | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | EMERGENCY WORK REQUIRED FOR AMKC. | 2022 | 16930 | 0 | 16663 | 0 | 0 | 0 | 0 | 0 | 16663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75EWGRVC | Emergency Work for GRVC | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | EMERGENCY WORK REQUIRED FOR GRVC. | 2022 | 4400 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75EWNIC | Emergency Work for NIC | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | EMERGENCY WORK REQUIRED FOR NIC. | 2022 | 19189 | 0 | 18886 | 0 | 0 | 0 | 0 | 0 | 18886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75EWRMSC | Emergency Work for RMSC | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | EMERGENCY WORK REQUIRED FOR RMSC. | 2022 | 51374 | 0 | 50532 | 0 | 0 | 0 | 0 | 0 | 50532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75EWRNDC | Emergency Work for RNDC | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 |  |  | EMERGENCY WORK REQUIRED FOR RNDC | 2022 | 35249 | 0 | 34661 | 0 | 0 | 0 | 0 | 0 | 34661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | C75-FCAD | FACADE RECONSTRUCTION AT EMTC, NIC,QDC, MDC, and GRVC | BUILDING SYSTEMS AND INFRASTRUCTURE | 100 | C-0075 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FACADE RECONSTRUCTION AT NIC,QDC,BBKC,BKDC | 2022 | 1650 | 18770.36 | 35 | 0 | 0 | 0 | 0 | 0 | 18805.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO290BCHJ | 265 E161 St.- BCHJ-Post Construction Work | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 104 | CO-0290 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | BCHJ-POST CONSTRUCTION WORK | 2022 | 44000 | 42196.21 | 2540 | 0 | 0 | 0 | 0 | 0 | 44736.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293LL11 | 851 GRAND CONCOURSE - FACADE RECONSTRUCTION | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 101 | CO-0293 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 851 GRAND CONCOURSE - FAÝADE REPAIRS LOCAL LAW 11 | 2022 | 13057 | 1246.9 | 2901 | 0 | 0 | 0 | 59494 | 0 | 63641.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO293SP | 851 GRAND CONCOURSE - FIRE PROTECTION/SPRINKLERS | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 100 | CO-0293 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 851 GRAND CONCOURSE - FIRE PROTECTION/SPRINKLERS | 2022 | 44850 | 7650.23 | 2239 | 0 | 66935 | 0 | 0 | 0 | 76824.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO294RF | 215 E161 ST.- ROOF | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 104 | CO-0294 |  |  | 215 E161 ST.- ROOF | 2022 | 6305 | 0 | 581 | 0 | 6851 | 0 | 0 | 0 | 7432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CO295EV | 1118 GRAND CONCOURSE - ELEVATORS | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 101 | CO-0295 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | 1118 GRAND CONCOURSE - ELEVATORS | 2022 | 9855 | 901.82 | 116 | 0 | 10752 | 0 | 0 | 0 | 11769.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CRO-AGS | CROTON ABOVE-GROUND STRUCTURE AND LANDSCAPING | CROTON FILTER PROJECT | 107 108 | WM-0011 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CONSTRUCTION OF THE ABOVE GROUND STRUCTURES FOR THE DPR PORTION OF THE MOSHULU GOLF COURSE. INCLUDED ARE THE CLUB HOUSE, THE TEEBOXES FOR THE DRIVING RANGE, THE WATER FRATURES, AND A PARKING LOT FOR THE GOLF COURSE. | 2022 | 58786 | 84009.56 | 346 | 0 | 0 | 0 | 0 | 0 | 84355.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | CS-ER-WCP | PARALLEL SEWER-REDUCE CSO DISCHARGE FROM PUGSLEY CREEK | CONSENT DECREE UPGRADING AND CONSTRUCTION | 100 | SE-0002X | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | THIS PROJECT WILL INVOLVE CONSTRUCTING A NEW PARALLEL INTERCEPTOR FROM CSO-24 TO R-6 TO REDUCE CSO DISCHARGE FROM PUGSLEY CREEK AS REQUIREDBY DEC IN ORDER TO APPROVE A MODIFICATION REQUEST TO ELIMINATE A 12-MG CSO TANK ($300M) FROM WESTCHESTER CREEK. | 2022 | 76000 | 101134.11 | 1000 | 0 | 0 | 0 | 0 | 0 | 102134.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEX22 | Reconstruction of Existing Sewers, The Bronx | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 100 | EP-0007 SE-0002X | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | THIS IS A TWO YEAR CONTRACT. THE TARGETED CONTRACT START DATE IS 021/16/2022. | 2022 | 13585 | 184 | 7040 | 0 | 0 | 0 | 0 | 0 | 7224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | EC-SEX23 | Reconstruction of Existing Sewers, The Bronx | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 100 | EP-0007 SE-0002X |  |  | RECONSTRUCTION OF EXISTING SEWERS, THE BRONX. THIS IS A 1 YEAR CONTRACT. THE TARGETED START DATE FOR THIS CONTRACT IS AS SOON AS THE PREVIOUS CONTRACT, EC-SEX22, EXPIRES | 2022 | 6500 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-553 | WATER MAIN IN SOUTHERN BLVD - WESTCHESTER AV & BOSTON RD | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 102 103 | WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | WATER MAIN IN SOUTHERN BLVD - WESTCHESTER AV & BOSTON RD | WATER MAIN IN SOUTHERN BLVD - WESTCHESTER AV & BOSTON RD | 2022 | 16885 | 60232.37 | 67 | 0 | 0 | 0 | 0 | 0 | 60299.37 | 516.91 | 0 | 0 | 0 | 0 | 0 | 0 | 516.91
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-560 | RECON WM IN WEST FARMS SQUARE (HWXP2007) | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 106 | SE-0002X WM-0006 WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RECON WM IN WEST FARMS SQUARE | 2022 | 8096 | 48.59 | 174 | 7873 | 0 | 0 | 0 | 0 | 8095.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-562 | New 46" Trunk Water Main in E.233rd St. Bronx | AUGMENTATION OF WATER SUPPLY SYSTEMS | 112 | WM-0001 WM-0006 SE-0002X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW 46" TRUNK WATER MAIN IN E.233RD ST. BRONX, BETWEEN BRONXWOOD AVENUE AND BAYCHESTER AVENUE. | 2022 | 8234 | 1325.9 | 178 | 31143 | 0 | 0 | 0 | 0 | 32646.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-564 | NEW 20" SUB-AQUEOUS WATER MAIN TO CITY ISLAND | EXTENSIONS | 110 | WM-0001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW 20" SUB-AQUEOUS WATER MAIN TO CITY ISLAND | 2022 | 23334 | 35558.94 | 2589 | 4465 | 0 | 0 | 0 | 0 | 42612.94 | 13.98 | 0 | 0 | 0 | 0 | 0 | 0 | 13.98
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-568 | New 20" sub-aqueous water main extension to Randall's Island | EXTENSIONS | 101 | WM-0001 SE-1000 HW-0001X | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW 20" SUB-AQUEOUS WATER MAIN EXTENSION TO RANDALL'S ISLAND | 2022 | 6243 | 39772.45 | 333 | 0 | 0 | 0 | 0 | 0 | 40105.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-569 | Replacement of Trunk WM in Bainbridge Ave | AUGMENTATION OF WATER SUPPLY SYSTEMS | 108 | WM-0006 SE-0002X WM-0001 HW-0200 HW-0001X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | REPLACEMENT OF TRUNK WM IN BAINBRIDGE AVE BETWEEN GUN HILL RD & HOLLYLA, AND IN JEROME AVE BETWEEN HOLLY LA AND E. 233RD ST., ETC | 2022 | 19229 | 60283.04 | 8793 | 0 | 0 | 0 | 0 | 0 | 69076.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-572 | Rep WM in Westchester Ave (HWPLZ004X) | AUGMENTATION OF WATER SUPPLY SYSTEMS | 108 | SE-0004 WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | REPLACE WM IN WESTCHESTER AVE BETWEEN MORRISON AVE AND HARROD PLACE,ETC. | 2022 | 227 | 4242.13 | 348 | 0 | 0 | 0 | 0 | 0 | 4590.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED-578 | Replcmt of Dist WM In Mundy Lane btwn Cranford & Nereid Ave | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 112 | WM-0001 SE-0002X | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | REPLACEMENT OF DISTRIBUTION WATER MAIN IN MUNDY LANE BETWEEN CRANFORDAVENUE AND NEREID AVENUE | 2022 | 6391 | 100 | 0 | 5675 | 0 | 0 | 0 | 0 | 5775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED580 | Dist WM & SE Rplmt E 161 St btwn Gerard & Cortlandt Ave BX | AUGMENTATION OF WATER SUPPLY SYSTEMS | 103 104 | SE-0002X WM-0001 |  |  | DISTRIBUTION WATER MAIN AND COMBINED SEWER REPLACEMENT IN EAST 161ST STREET BETWEEN GERARD AVE AND CORTLANDT AVE IN THE BOROUGH OF BRONX. THIS PROJECT IS IN CONJUNCTION WITH DOT PROJECT HWX100SBC | 2022 | 5679 | 0 | 0 | 656 | 5110 | 0 | 0 | 0 | 5766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HED582 | Dis WM at iJerome Ave & East Clarke Pl, BX (HWCSCH4D) | AUGMENTATION OF WATER SUPPLY SYSTEMS | 104 | WM-0001 |  |  | DISTRIBUTION WM IN THE INTERSECTION OF JEROME AVENUE & CLARKE PLACE EAST. THIS PROJECT WOULD BE DONE IN CONJUNCTION WITH NYC DOT PROJECT HWCSCH4D. FURTHERMORE, THIS PROJECT WOULD FUND INSTALLATION OF DISTRIBUTION MAIN PROPOSED BY DISTRIBUTION ENGINEERING THAT LIES OUTSIDE THE DOT SCOPE. | 2022 | 96 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HEDA-003 | Accelerated Distribution WM replcmnt & sewer rehab: BX | TRUNK AND DISTRIBUTION MAIN REPLACEMENT | 100 | WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ACCELERATED DISTRIBUTION WATER MAIN REPLCMNT & SEWER REHAB/REPLACEMENT, BRONX | 2022 | 19516 | 24345.05 | 809 | 0 | 0 | 573 | 0 | 0 | 25727.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112CWFR | COMMONWEALTH AVENUE FIRE SAFETY SYSTEM | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 |  |  | COMMONWEALTH AVENUE FIRE SAFETY SYSTEM | 2022 | 650 | 2095.02 | 146 | 0 | 0 | 0 | 0 | 0 | 2241.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH112WLFA | WILLOW AVE FIRE SAFETY | SHELTERS FOR HOMELESS INDIVIDUALS |  | HH-0112 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | FIRE SAFETY SYSTEM | 2022 | 750 | 781.99 | 83 | 0 | 0 | 0 | 0 | 0 | 864.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115FRFA | FREEMAN FAMILY RESIDENCE - FIRE ALARM SYSTEM UPGRADE | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 |  |  | FREEMAN FAMILY RESIDENCE - FIRE ALARM SYSTEM UPGRADE | 2022 | 256 | 744.96 | 555 | 0 | 0 | 0 | 0 | 0 | 1299.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115JCFS | JACKSON FAMILY FIRE SAFETY | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | JACKSON FAMILY FIRE SAFETY | 2022 | 1485 | 1050.65 | 416 | 0 | 0 | 0 | 0 | 0 | 1466.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SNEC | SENECA HOUSES - ELECTRICAL AND KITCHEN UPGRADE | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SENECA HOUSES - ELECTRICAL AND KITCHEN UPGRADE | 2022 | 1480 | 31 | 0 | 0 | 0 | 0 | 0 | 2952 | 2983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115SNFA | SENECA HOUSES - FIRE ALARM SYSTEM UPGRADE | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 |  |  | SENECA HOUSES - FIRE ALARM SYSTEM UPGRADE | 2022 | 665 | 1649.25 | 190 | 0 | 0 | 0 | 0 | 0 | 1839.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HH115UNFA | UNIVERSITY FAMILY RESIDENCE - FIRE ALARM SYSTEM UPGRADE | SHELTERS FOR HOMELESS FAMILIES |  | HH-0115 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | UNIVERSITY FAMILY RESIDENCE - FIRE ALARM SYSTEM UPGRADE | 2022 | 646 | 1669.05 | 0 | 0 | 0 | 2619 | 0 | 0 | 4288.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HL82BRONX | Bronx Animal Care Center and Veterinary Clinic | ANIMAL CARE |  | HL-0082 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CONSTRUCTION | 2022 | 5000 | 13179.4 | 1555 | 74947 | 0 | 0 | 0 | 0 | 89681.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWCSCHPBX | SAFE ROUTES TO SCHOOLS- BRONX | PRIMARY STREET RECONSTRUCTION | 100 | HW-0988 HW-D105 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | SAFE ROUTES TO SCHOOLS- BRONX | SAFE ROUTES TO SCHOOLS- BRONX | 2022 | 9628 | 1465.63 | 12334 | 0 | 0 | 0 | 0 | 0 | 13799.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-01 | METROPOLITAN AVE & UNIONPORT ROAD IN PARKCHESTER -CENTER IS. | PRIMARY STREET RECONSTRUCTION | 100 109 | HW-X001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | METROPOLITAN AVE & UNIONPORT ROAD IN PARCHESTER CENTER ISLAND MALL | MATROPOLITAN AVE & UNIOPORT ROAD PARCHESTER-CENTER ISLAND MALL | 2022 | 4488 | 7442.53 | 0 | 0 | 182 | 0 | 0 | 0 | 7624.53 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 2200
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWD105-03 | LIBRARY LANE PROJECT | PRIMARY STREET RECONSTRUCTION | 100 110 | HW-0061 HW-D105 HW-0001X HW-0200 WM-0001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | LIBRARY LANE PROJECT | LIBRARY LANE PROJECT | 2022 | 600 | 1685.75 | 410 | 6057 | 0 | 0 | 0 | 0 | 8152.75 | 400 | 0 | 980 | 0 | 0 | 0 | 0 | 1380
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPLZ004X | Morrison Avenue Plaza (HED-572) | PRIMARY STREET RECONSTRUCTION | 100 | HW-0200 TF-0502 HW-1684 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | MORRISON AVENUE PLAZA | MORRISON AVENUE PLAZA | 2022 | 2700 | 4219.44 | 78 | 0 | 0 | 670 | 0 | 0 | 4967.44 | 2490.69 | 0 | 0 | 0 | 0 | 0 | 0 | 2490.69
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWPR19X | Pedestrian Ramp Rehabilitation - The Bronx | PEDESTRIAN RAMP CONSTRUCTION | 100 | HW-0200 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PEDESTRIAN RAMP REHABILITATION - THE BRONX | 2022 | 12472 | 12796.53 | 154 | 0 | 0 | 0 | 0 | 0 | 12950.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2014X | PRIOR NOTICE SIDEWALKS - BRONX | SIDEWALK RECONSTRUCTION | 100 | HA-D001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PRIOR NOTICE SIDEWALKS - BRONX | PRIOR NOTICE SIDEWALKS - BRONX | 2022 | 3971 | 3720.6 | 179 | 0 | 0 | 0 | 0 | 0 | 3899.6 | 703 | 0 | 0 | 0 | 0 | 0 | 0 | 703
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWS2021X | PRIOR NOTICE SIDEWALK - BRONX | SIDEWALK RECONSTRUCTION | 100 | HW-0200 P-1331 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | PRIOR NOTICE SIDEWALKS - BRONX | PRIOR NOTICE SIDEWALKS - BRONX | 2022 | 2280 | 0 | 1323 | 0 | 0 | 0 | 0 | 0 | 1323 | 0 | 957 | 0 | 0 | 0 | 0 | 0 | 957
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX006-01 | Henwood Place Step Street | PRIMARY STREET RECONSTRUCTION | 100 | HW-0211 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | HENWOOD PLACE STEP STREET | HENWOOD PLACE STEP STREET | 2022 | 9700 | 1288.86 | 0 | 0 | 326 | 10815 | 0 | 0 | 12429.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBC | South Bronx East-West Crosstown SBS | PRIMARY STREET RECONSTRUCTION | 100 | HW-1684 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SOUTH BRONX EAST-WEST CROSSTOWN SBS | SOUTH BRONX EAST-WEST CROSSTOWN SBS | 2022 | 7750 | 2397.82 | 0 | 0 | 38895 | 0 | 0 | 0 | 41292.82 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 10000
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX100SBS | Webster Ave SBS | TRAFFIC WORK IN CONJUNCTION WITH HIGHWAY RECONSTRUCTION | 100 | WM-0001 PU-0026 TF-0777 TF-0002 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | WEBSTER AVE SBS - PLANYC | WEBSTER AVE SBS - PLANYC | 2022 | 16058 | 13042.99 | 60 | 1263 | 0 | 95 | 0 | 272 | 14732.99 | 16043.81 | 0 | 0 | 0 | 0 | 0 | 0 | 16043.81
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX402 | Bruner and Ely | PRIMARY STREET RECONSTRUCTION | 100 | HW-0001X | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | BRUNER AND ELY | BRUNER AND ELY | 2022 | 12506 | 1184.4 | 0 | 751 | 12095 | 0 | 0 | 0 | 14030.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX404 | Southern Bronx Multi-Site Safety Improvements | PRIMARY STREET RECONSTRUCTION | 100 | HW-0001X | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | SOUTHERN BRONX MULTI-SITE SAFETY IMPROVEMENTS | SOUTHERN BRONX MULTI-SITE SAFETY IMPROVEMENTS | 2022 | 5128 | 0 | 940 | 109 | 0 | 6553 | 0 | 0 | 7602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX406 | Northwest Bronx School Safety Improvements | PRIMARY STREET RECONSTRUCTION | 100 | HW-0988 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NORHEAST BRONX SCHOOL SAFETY IMPROVEMENTS | NORHEAST BRONX SCHOOL SAFETY IMPROVEMENTS | 2022 | 13930 | 20 | 1525 | 0 | 0 | 10131 | 0 | 0 | 11676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWX710A | Pelham Pkwy - West & East and North & South Bounds (Phase A) | PRIMARY STREET RECONSTRUCTION | 111 | TF-0502 WM-0006 WM-0001 HW-0710 TF-0002 HW-0001X HW-0944 HW-1684 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | PELHAM PKWY-WEST & EAST AND NORTH & SOUTH BOUNDS (PHASE A) | PELHAM PKWY-WEST & EAST AND NORTH & SOUTH BOUNDS (PHASE A) | 2022 | 25093 | 132605.87 | 7514 | 181 | 3841 | 2250 | 0 | 535 | 146926.87 | 559.94 | 0 | 0 | 0 | 0 | 0 | 11 | 570.94
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXF2000B | 1400 WILLIAMSBRIDGE RD - HVAC AND FIRE ALARM SYS | FACILITY RECONSTRUCTION | 111 | HW-0003 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | 1400 WILLIAMSBRIDGE ROAD - UPGRADES | 1400 WILLIAMSBRIDGE ROAD - UPGRADES | 2022 | 1340 | 8809.36 | 373 | 539 | 0 | 0 | 0 | 0 | 9721.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXFPLZA | FORDHAM PLAZA PHASE A | PRIMARY STREET RECONSTRUCTION | 100 106 | HW-0001X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | FORDHAM PLAZA PHASE A | FORDHAM PLAZA PHASE A | 2022 | 14925 | 10560.07 | 0 | 75 | 0 | 0 | 0 | 0 | 10635.07 | 11267.39 | 0 | 0 | 0 | 0 | 0 | 0 | 11267.39
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXJEROME | Jerome Avenue Safety Improvements (NDF-JEROM) | PRIMARY STREET RECONSTRUCTION | 100 | HW-0001 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | JEROME AVENUE SAFETY IMPROVEMENTS | 2022 | 48253 | 0 | 0 | 0 | 0 | 8553 | 0 | 0 | 8553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136A | GRAND CONCOURSE RECON SERVICE ROAD E.166 TO E171ST | PRIMARY STREET RECONSTRUCTION | 104 | HW-1678 HW-1672 TF-0002 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RECON SERVICE ROAD WITH WIDENED MALL | 2022 | 13588 | 12203.33 | 0 | 0 | 0 | 179 | 0 | 32 | 12414.33 | 12853.62 | 0 | 3145 | 0 | 89 | 0 | 0 | 16087.62
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136B | Grand Concourse Phase 3 | PRIMARY STREET RECONSTRUCTION | 100 | HW-0001X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | GRAND CONCOURSE PHASE 3 | GRAND CONCOURSE PHASE 3 | 2022 | 21136 | 12971.88 | 49 | 75 | 0 | 1897 | 0 | 0 | 14992.88 | 15871.9 | 0 | 395 | 0 | 0 | 0 | 0 | 16266.9
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136C | Grand Concourse Phase 4 (SEX002268) | PRIMARY STREET RECONSTRUCTION | 100 | HW-0944 HW-0001X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | GRAND CONCOURSE PHASE 4 | GRAND CONCOURSE PHASE 4 | 2022 | 64599 | 47688.44 | 0 | 4171 | 0 | 2145 | 0 | 0 | 54004.44 | 27920.64 | 0 | 143 | 0 | 0 | 0 | 0 | 28063.64
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP136D | Grand Concourse Phase 5 | PRIMARY STREET RECONSTRUCTION | 100 | HW-0001X | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | GRAND CONCOURSE PHASE 5 | GRAND CONCOURSE PHASE 5 | 2022 | 54000 | 2786.1 | 0 | 0 | 1000 | 51234 | 0 | 0 | 55020.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXP2007 | E177TH ST/DEVOE AVE BT SHERIDAN (I-895) /E.TREMONT HED-560 | PRIMARY STREET RECONSTRUCTION | 106 | HW-0001X HW-0200 TF-0502 TF-0002 HW-X006 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | NTERSECTION OF E.177TH ST., DEVOE AVE. AND I-895. INTERSECTION OF DEVOE AVE. AND E. TREMONT AVE. (PINX027.05.101) SOUTHERN SEGMENT OF THE BRONX RIVER GREENWAY | INTERSECTION OF E.177TH ST., DEVOE AVE. AND I-895. INTERSECTION OF DEVOE AVE. AND E. TREMONT AVE. (PINX027.05.101) SOUTHERN SEGMENT OF THEBRONX RIVER GREENWAY | 2022 | 4939 | 2597.19 | 262 | 15730 | 0 | 0 | 0 | 0 | 18589.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXPRATT | Pratt Ave Reconstruction and Retaining Wall | PRIMARY STREET RECONSTRUCTION | 100 | HW-0001X HW-0061 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | PRATT AVE AND RETAINING WALL | 2022 | 8750 | 1548.25 | 19 | 67 | 6704 | 0 | 0 | 0 | 8338.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXRCPLZ | ROBERTO CLEMENTE PLAZA & HUB REDESIGN AND RECONSTRUCTION | PRIMARY STREET RECONSTRUCTION | 100 105 | TF-0502 HW-0001X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RECON OF PLAZA & HUB | 2022 | 2550 | 15279.8 | 0 | 128 | 0 | 0 | 0 | 0 | 15407.8 | 4396.3 | 0 | 0 | 0 | 0 | 0 | 0 | 4396.3
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS311V1 | CLIFFORD PLACE STEP STREET | RECONSTRUCTION OF STEP STREETS | 100 105 | HW-0211 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | CLIFFORD PALCE STEP STREET | CLIFFORD PLACE STEP STREET | 2022 | 3248 | 8155.06 | 0 | 0 | 0 | 221 | 0 | 0 | 8376.06 | 1687 | 0 | 0 | 0 | 0 | 0 | 0 | 1687
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS411 | West 229th St Step Street | RECONSTRUCTION OF STEP STREETS | 100 108 | HW-0211 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | WEST 229TH ST STEP STREET | WEST 229TH ST STEP STREET | 2022 | 3725 | 10712.69 | 0 | 50 | 0 | 31 | 0 | 0 | 10793.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS511 | West Tremont Ave Step Street | RECONSTRUCTION OF STEP STREETS | 100 105 | HW-0211 SE-0002X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | WEST TREMONT AVE STEP STREET | WEST TREMONT AVE STEP STREET | 2022 | 1617 | 8917.66 | 0 | 290 | 0 | 272 | 0 | 0 | 9479.66 | 1295.68 | 0 | 0 | 0 | 0 | 0 | 0 | 1295.68
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | HWXS711 | RECONSTRUCTION OF STEP STREET AT DAVIDSON AVE (SEX002272) | RECONSTRUCTION OF STEP STREETS | 100 | HW-0211 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | RECONSTRUCTION OF STEP STREET AT DAVIDSON AVE | RECONSTRUCTION OF STEP STREET AT DAVIDSON AVE | 2022 | 7260 | 1773.36 | 0 | 0 | 6516 | 0 | 0 | 0 | 8289.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18ALELE | ALLERTON - Elevator Replacement - 3 stop | ESSENTIAL RECONSTRUCTION OF FACILITIES | 111 | LN-0008 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | *NEW* -ELEVATOR REPLACEMENT - 3 STOP | 2022 | 2071 | 0 | 321 | 0 | 1577 | 0 | 0 | 0 | 1898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LN18MRBOI | Morrisania - Boiler Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 103 | LN-D008 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW BOILER AT MORRISANIA BRANCH LIBRARY | 2022 | 3015 | 0 | 366 | 0 | 2378 | 0 | 0 | 0 | 2744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNBXA08LS | BRONX - Life Safety Projects @ 8 Branch Libraries | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 | LN-0101X LN-D004 LN-D008 LN-X001 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | LIFE SAFETY PROJECTS @ 12 BRANCH LIBRARIES - BRONX | 2022 | 2570 | 1952.2 | 162 | 243 | 0 | 0 | 0 | 0 | 2357.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNC4WLEX | WOODLAWN - Branch Expansion | IMPROVEMENTS TO EXISTING FACILITIES | 112 | LN-X001 LN-D004 LN-D008 LN-0008 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 4355 KATONAH AVENUE, BRONX, NY 10470 | LIBRARY EXPANSION | 2022 | 2312 | 1020.89 | 0 | 0 | 8567 | 0 | 0 | 0 | 9587.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA11BEL | BELMONT - Upper and Lower Roof | ESSENTIAL RECONSTRUCTION OF FACILITIES | 108 | LN-0008 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROOF REPLACEMENT | 2022 | 400 | 2098.96 | 178 | 0 | 0 | 0 | 0 | 0 | 2276.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13ECH | EASTCHESTER: HVAC Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 112 | LN-D008 LN-0008 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | HVAC REPLACEMENT | 2022 | 1010 | 2049.18 | 127 | 0 | 0 | 0 | 0 | 0 | 2176.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MOR | MORRISANIA: HVAC and Roof | ESSENTIAL RECONSTRUCTION OF FACILITIES | 103 | LN-0008 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | HVAC AND ROOF | 2022 | 569 | 2530.47 | 266 | 0 | 0 | 0 | 0 | 0 | 2796.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA13MOT | MOTT HAVEN: HVAC | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 101 | LN-0008 LN-D008 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HVAC | 2022 | 390 | 3523.89 | 85 | 0 | 0 | 0 | 0 | 0 | 3608.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA15EDW | HVAC Replacement @ Edenwald | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 | LN-D008 LN-0008 LN-0101X | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | HVAC | 2022 | 965 | 509.53 | 0 | 17 | 1515 | 0 | 0 | 0 | 2041.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA15MOT | Window Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 | LN-0008 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | WINDOW REPLACEMENT | 2022 | 944 | 3716.57 | 325 | 0 | 0 | 0 | 0 | 0 | 4041.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCA15RSD | RIVERDALE BRANCH Exterior / Facades/ Retaining Wall / HVAC | ESSENTIAL RECONSTRUCTION OF FACILITIES | 108 | LN-D008 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | REHABILITATION TO EXTERIOR AND FACADES & RETAINING WALL | 2022 | 1303 | 512.97 | 0 | 0 | 0 | 0 | 1052 | 0 | 1564.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCL15CAS | CASTLE HILL: Partial Interior Renovation | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 | LN-D008 LN-X001 LN-D004 LN-0008 LN-0101X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | CASTLE HILL: INTERIOR RENOVATION | 2022 | 5191 | 1003.8 | 632 | 0 | 7653 | 0 | 0 | 0 | 9288.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM10WCH | WESTCHESTER SQUARE - Replacement Branch Construction | EXPANSION AND CONSTRUCTION OF FACILITIES | 111 | LN-0008 PU-0025 LN-D004 LN-D008 LN-X001 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES |  | NEW BRANCH CONSTRUCTION - LNCM10WCH | 2022 | 9300 | 3892.63 | 1046 | 28497 | 0 | 0 | 0 | 0 | 33435.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNCM12CPT | CLASON'S POINT - NEW ROOF AND DRAINS | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 109 | LN-D008 LN-X001 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW ROOF AND DRAINS | 2022 | 600 | 1222.19 | 0 | 0 | 66 | 0 | 0 | 0 | 1288.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13MHU | Mosholu: New Roof and Exterior Work | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 107 | LN-0008 LN-D004 LN-D008 LN-0101M | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ROOF | 2022 | 1137 | 851.2 | 3399 | 0 | 0 | 0 | 0 | 0 | 4250.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA13TNK | THROGS NECK: New Roof, HVAC | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 | LN-0008 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | NEW ROOF, HVAC | 2022 | 550 | 4014.57 | 0 | 0 | 0 | 0 | 363 | 0 | 4377.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNEA14VNT | HVAC Replacement | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 111 | LN-0101X LN-0008 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | HVAC REPLACEMENT | 2022 | 500 | 680.58 | 6 | 2888 | 0 | 0 | 0 | 0 | 3574.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA11WFM | WEST FARMS - New Front Entry | ESSENTIAL RECONSTRUCTION OF FACILITIES | 106 | LN-X001 LN-D004 LN-D008 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | NEW FRONT ENTRY | 2022 | 150 | 749.96 | 758 | 0 | 0 | 0 | 0 | 0 | 1507.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXA12GRC | GRAND CONCOURSE - ADA Compliance and Related Work | IMPROVEMENTS TO EXISTING FACILITIES | 100 104 | LN-0008 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | ADA COMPLIANCE AND RELATED WORK | 2022 | 750 | 4881.5 | 151 | 200 | 0 | 0 | 0 | 0 | 5232.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXEA08BA | BAYCHESTER: HVAC | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 112 | LN-0008 LN-0101M LN-0101X LN-D008 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | HVAC | 2022 | 632 | 0 | 73 | 762 | 0 | 0 | 0 | 0 | 835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | LNXEA08FN | FRANCIS MARTIN: HVAC | ESSENTIAL RECONSTRUCTION OF FACILITIES | 100 105 | LN-0008 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | HAVC | 2022 | 975 | 1413.74 | 0 | 0 | 0 | 0 | 77 | 0 | 1490.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-JEROM | Jerome Avenue Safety Improvements NDF Funding (HWXJEROME) | NEIGHBORHOOD REVITALIZATION | 100 | ED-0384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | JEROME AVENUE SAFETY IMPROVEMENTS NDF FUNDING | 2022 | 39700 | 0 | 4114 | 0 | 0 | 35586 | 0 | 0 | 39700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NDF-SCH4D | School Safety 4D NDF Funding, HWCSCH4D | NEIGHBORHOOD REVITALIZATION | 100 | ED-0384 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | SCHOOL SAFETY 4D NDF FUNDING | 2022 | 3800 | 0 | 0 | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | NEWHJC2 | NEW CONSTRUCTION AT HORIZON JC PHASE 2.0 | CHILD WELFARE FACILITIES | 100 | CS-0005 |  |  | TBD | 2022 | 161040 | 0 | 24340 | 0 | 136700 | 0 | 0 | 0 | 161040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-102DELV | Del Valle Square X009-111M | PRIMARY STREET RECONSTRUCTION | 100 | HW-1684 HW-0001X HW-0200 HW-0944 TF-0002 TF-0502 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | TRSNFR $4M (HW 1684) FROM HWPLZ003X...FY'14 ADOPT. ROLLS $3.649M FROMFY'14 TO FY15...$970K XFER FROM 850 HWPLZ011Q (3/14)...$970K NEW NEEDFUND (JAN PLAN FY15) ADDED PER IGOR'S E-MAIL FROM DOT ON 11.20.14 (NEW NEED DENIED)... | TRSNFR $4M (HW 1684) FROM HWPLZ003X...FY'14 ADOPT. ROLLS $3.649M FROMFY'14 TO FY15...$970K XFER FROM 850 HWPLZ011Q (3/14)...$970K NEW NEEDFUND (JAN PLAN FY15) ADDED PER IGOR'S E-MAIL FROM DOT ON 11.20.14 (NEW NEED DENIED)... | 2022 | 16961 | 2253.9 | 21510 | 2491 | 0 | 0 | 0 | 0 | 26254.9 | 0 | 3655 | 0 | 0 | 0 | 0 | 0 | 3655
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P109STARA | STARLIGHT PARK COMFORT STATION X147-111M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 109 | P-1018 P-0245X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | STARLIGHT PARK | 2022 | 1881 | 4223.4 | 666 | 0 | 0 | 131 | 0 | 0 | 5020.4 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 600
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1CROT16A | BRONX RIVER GRWAY RIVER HOUSE IN STARLIGHT PK X147-107M/407M | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 109 | P-0245X P-1018 P-0882 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | BX RIVER | 2022 | 14562 | 14783.45 | 46 | 52 | 0 | 0 | 0 | 0 | 14881.45 | 1020.83 | 26 | 0 | 0 | 0 | 0 | 0 | 1046.83
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1HARTIS | Hart Island | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-0245X |  |  | HART ISLAND: IMMEDIATE CAPITAL NEEDS (NOT INCLUDING COST OF BUILDING RE-INSPECTION AND DEMOLITION)- RELATED TO THE IMPENDING CLOSING OF RIKERS ISLAND PRISON AND CITY COUNCIL INTRO 906, IT IS ANTICIPATED THAT HART ISLAND WILL BE TRANSFERRED TO PARKS JURISDICTION IN 2021. AT CITY HALL'S REQUEST, IN MARCH 2019, PARKS PREPARED A PLAN WHICH INCLUDED IMMEDIATE AND MORE LONG TERM CAPITAL AND EXPENSE NEEDS. IN MARCH 2019, IMMEDIATE CAPITAL NEEDS (FENCING, ROADWAY REPAIR WORK, AND VISITOR/GAZEBO AREA ENHANCEMENTS) WERE ESTIMATED AT $2.9M. HOWEVER, IN ADDITION TO THE $2.9M, THE COST OF DEMOLISHING 20+ CONDEMNED BUILDINGS ON THE ISLAND IS $100M+. RE-INSPECTION OF THE BUILDINGS BY DOB IS NEEDED AND THE APPROPRIATE AGENCY(IES) MUST BE TASKED WITH DEVELOPING MORE REFINEDDEMOLITION COSTS AND COMPLETING DEMOLITION WORK. BUILDING INSPECTION A | 2022 | 0 | 0 | 52000 | 0 | 0 | 0 | 0 | 0 | 52000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1ORCHMO | Orchard Beach M&O Facility Reconstruction DB | BEACHES AND BOARDWALKS | 100 | P-D021 P-1018 P-0715 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | FY17 JAN PLAN NN SUBMISSION $4M IN FY 19 AND $12.4M IN FY20... | 2022 | 35500 | 2500 | 8455 | 0 | 0 | 30000 | 445 | 0 | 41400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1PBSTAR | Starlight Park Pedestrian Bridge (P-1SAND01) | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 109 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BRONX | RECONSTRUCTION OF PEDESTRIAN BRIDGES IN STARLIGHT PARK | 2022 | 16400 | 17881.89 | 218 | 0 | 0 | 0 | 0 | 0 | 18099.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1STARLP | BRONX RIVER GREENWAY: STARLIGHT PARK PHASE II, STAGE 2, BX | NEIGHBORHOOD PARKS AND PLAYGROUNDS | 100 | P-1018 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | BX RIVER ALLIANCE STARLIGHT PARK (DDC) | 2022 | 658 | 10021.73 | 2456 | 0 | 0 | 0 | 0 | 0 | 12477.73 | 29873.02 | 1 | 0 | 0 | 0 | 0 | 0 | 29874.02
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P-1VCPDBR | Vancortlandt Park pedestrian bridge | LARGE, MAJOR AND REGIONAL PARK RECONSTRUCTION | 100 | P-0245X P-0508 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | VANCORTLANDT PARK PEDESTRIAN BRIDGE | 2022 | 9800 | 3120.33 | 0 | 0 | 0 | 0 | 7636 | 0 | 10756.33 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 4000
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | P1YANK15A | Bronx Children's Museum Fitout | MAJOR RECREATIONAL FACILITIES AND FACILITY RECONSTRUCTION | 104 | PV-X467 P-D021 P-1018 PV-D467 PV-0467 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | YANKEE STADIUM | 2022 | 5892 | 12267.55 | 2062 | 0 | 0 | 0 | 0 | 0 | 14329.55 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 2000
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79FDBNX | BRONX FRONT DESK REPLACEMENT 42ND, 44TH, 46TH, 108TH | POLICE FACILITIES | 100 | PO-0079 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | DESK REPLACEMENT | 2022 | 1011 | 2241.17 | 0 | 182 | 0 | 0 | 0 | 0 | 2423.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PO79ROD | NEW FIREARMS TRAINING FACILITY | POLICE FACILITIES | 100 | PO-0079 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | NEW TRAINING FACILITY AT RODMAN'S NECK, BRNX | NEW TRAINING FACILITY | 2022 | 274630 | 33695.87 | 1271 | 6348 | 0 | 217815 | 0 | 0 | 259129.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV176CESU | WCS - Bronx Zoo - Con Ed Switchgear Upgrade | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-0176 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | 2300 SOUTHERN BLVD, FORDAM ROAD BRONX NY | ELECTRICAL SWITCHGEAR UPGRADE AT BRONX ZOO. | 2022 | 5909 | 15239.17 | 0 | 1313 | 0 | 0 | 0 | 0 | 16552.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV205CONS | NYBG - NY Botanical Garden - Conservatory Dome/Boiler Rep. | ESSENTIAL RECONSTRUCTION OF FACILITIES | 106 107 111 112 | PV-0205 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | NY BOTANICAL GARDEN - CONSERVATORY DOME | 2022 | 8000 | 10843 | 0 | 0 | 0 | 0 | 0 | 0 | 10843 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV464PRKG | WH - Wave Hill - Parking Lot Improvements | ESSENTIAL RECONSTRUCTION OF FACILITIES |  | PV-0464 | PROJECT DELAYED PENDING RESOLUTION OF LEGAL ISSUES | 675 WEST 252ND STREET, BRONX, NY | PARKING LOT IMPROVEMENTS | 2022 | 1581 | 4995.07 | 333 | 39 | 0 | 0 | 0 | 0 | 5367.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PV467BRAC | BRAC - Bronx River Art Center Reconstruction | ESSENTIAL RECONSTRUCTION OF FACILITIES | 106 | PV-X467 PV-0467 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 1087 EAST TREMONT AVE BRONX, NY 10460 | BRONX RIVER ART CENTER RECONSTRUCTION | 2022 | 3024 | 15510.21 | 0 | 139 | 0 | 0 | 0 | 0 | 15649.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PW77198CT | 198 E 161 ST.- COOLING TOWER REPLACEMENT | REHABILITATION OF CITY-OWNED OFFICE SPACE | 104 | PW-0077 |  |  | UNIT | 2022 | 878 | 0 | 0 | 683 | 0 | 0 | 3629 | 0 | 4312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | PWXTNLLRE | Throgs Neck Little League- Infrastructure Rehabilitation | MISCELLANEOUS CONSTRUCTION | 110 | PW-X078 PW-D005 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | THROGS NECK LITTLE LEAGUE INFRASTRUCTURE REHABILITATION | 2022 | 453 | 0 | 0 | 0 | 0 | 0 | 400 | 1 | 401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | REG-HP06 | RECONSTRUCTION OF REGULATOR HP-06 | WATER QUALITY MANDATES | 100 | WP-0169 SE-0002X WM-0001 WP-0269 EP-0007 TF-0002 TF-0502 |  |  | RECONSTRUCTION OF REGULATOR HP-06 | 2022 | 25000 | 825.54 | 61868 | 0 | 0 | 0 | 0 | 0 | 62693.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SANDBOMB | Reconstruct Hurricane Sandy Damaged Bomb Sq bldg | POLICE FACILITIES | 110 | PO-0079 PU-0025 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RECONSTRUCT MULTIPURPOSE BUILDING FOR THE BOMB SQUAD IN RODMAN'S NECKDAMAGED BY HURRICANE SANDY | 2022 | 5000 | 1002.8 | 0 | 13648 | 70 | 0 | 0 | 0 | 14720.8 | 1271.32 | 0 | 6665 | 635 | 0 | 0 | 0 | 8571.32
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002266 | Repl & Rehab of Combined swrs 171 to 175 sts, bx | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 100 | SE-0002K | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | REPL AND REHAB OF COMB SWRS FROM E. 171 ST TO E 175 ST., BRONX | 2022 | 153 | 0 | 153 | 0 | 0 | 0 | 0 | 0 | 153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002268 | Reconstruction of Grand Concourse - Phase 4 (HWXP136C) | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 104 | SE-0002X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RECONSTRUCTION OF GRAND CONCOURSE - PHASE 4( HWXP136C) - COMBINED SEWER REPLACEMENT FROM EAST 175TH STREET TO EAST FORDHAM ROAD, WORK DONE IN CONJUNCTION WITH NYC DOT PROJECT HWXP136C. | 2022 | 4258 | 3862.44 | 404 | 0 | 417 | 0 | 0 | 0 | 4683.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX002272 | Combined SE Replacement in Davidson Avenue. Bronx (HWXS711) | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 105 | SE-0002X |  |  | THI PROJECT IS IN CONJUNCTION WITH DOT HIGHWAY PROJECT ID HWXS711 TO REPLACE COMBINED SEWERS IN DAVIDSON AVENUE BETWEEN WEST 174 STREET ANDDEAD END TO STEP STREET. | 2022 | 239 | 0 | 0 | 0 | 0 | 0 | 0 | 267 | 267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX0201ZB | Reconstruction of existing sewers, Bronx | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 100 | SE-0002X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | RECONSTRUCTION OF EXISTING SEWERS, BRONX | 2022 | 5250 | 12273.74 | 785 | 0 | 0 | 0 | 0 | 0 | 13058.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX200400 | STORM & SAN SEWERS REPL & EXT IN MININIEFORD AVE AREA | EXTENSIONS TO ACCOMMODATE NEW DEVELOPMENT | 110 | SE-0002X SE-0200X HW-0001X | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | STORM & SAN SEWERS REPL & EXT IN MININIEFORD AVE AREA | 2022 | 1378 | 1120.22 | 16 | 2554 | 0 | 0 | 0 | 0 | 3690.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20047 | Replacement of combined sewer in Burr Ave | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 110 | HW-0200 SE-0200X WM-0001 SE-0002X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | REPLACEMENT OF COMBINED SEWER IN BURR AVE BET. PELHAM PKWY S. AND WESTCHESTER AVE, ETC, DISTRIBUTION WATER MAIN REPLACEMENT. | 2022 | 12149 | 19674.26 | 1400 | 308 | 0 | 0 | 0 | 0 | 21382.26 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX20049 | Replacing deteriorating retain wall along Pratt Ave in BX | REPLACEMENT OR AUGMENTATION OF EXISTING SYSTEMS | 112 | SE-0002X | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION |  | REPLACEMENT OF DETERIORATING RETAINING WALL ALONG PRATT AVENUE. NEW COMBINED SEWER IS NEEDED FOR THE PROPOSED CATCH BASINS THAT ARE INTENDED TO ALLEVIATE FLOODING AND PONDING CONDITIONS IN PRATT AVENUE. | 2022 | 1254 | 0 | 188 | 0 | 1114 | 0 | 0 | 0 | 1302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 850 | DEPT OF DESIGN & CONSTRUCTION | SEX-SURV4 | SURVEYS FOR SEWERS IN BRONX | REPLACEMENT OF CHRONICALLY FAILING COMPONENTS | 100 | HW-0348 SE-0002X SE-0432 | PROJECT DELAYED DUE TO UNFORESEEN SITE/FIELD CONDITION | BOROUGH WIDE | SURVEYS FOR SEWER CONSTRUCTION/ RECONSTRUCTION | 2022 | 10564 | 7716.53 | 0 | 1362 | 199 | 0 | 0 | 0 | 9277.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE211 | DOE- Building Management System Upgrade | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 101 | PU-0025 |  |  | DOE BUILDING MANAGEMENT SYSTEM UPGRADE | 2022 | 5444 | 0 | 0 | 545 | 4899 | 0 | 0 | 0 | 5444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | ACEDOE703 | DOE - STEAM TRAPS | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 101 | PU-0025 |  |  | DOE - STEAM TRAPS | 2022 | 228 | 0 | 726 | 0 | 0 | 0 | 0 | 0 | 726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | BXCONSOL | Renovation of Bronx DCP office at 211 Bartow Ave. | CHILD WELFARE FACILITIES | 101 | CS-0003 |  |  | TBD | 2022 | 5697 | 0 | 2205 | 0 | 0 | 0 | 0 | 0 | 2205 | 0 | 3492 | 0 | 0 | 0 | 0 | 0 | 3492
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293201A | DASNY - 851 GRAND CONCOURSE- RENOVATIONS | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 104 | CO-0293 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS | 851 GRAND CONCOURSE BRONX, NY 10451 | INTERIOR RENOVATIONS; ELECTRICAL & HVAC DISTRIBUTION; INITIAL OUTFITTING OF NEWLY RENOVATED SPACE | 2022 | 40475 | 1751.1 | 0 | 0 | 0 | 0 | 2618 | 0 | 4369.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293CTR | 851 GRAND CONCOURSE -COOLING TOWER REPLACEMENT | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 101 | CO-0293 |  |  | 851 GRAND CONCOURSE - COOLING TOWER REPLACEMENT | 2022 | 1140 | 0 | 0 | 85 | 0 | 0 | 945 | 0 | 1030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293ELEC | 851 GRAND CONCOURSE- ELECTRICAL UPGRADE | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 101 | CO-0293 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 851 GRAND CONCOURSE BRONX, NY 10451 | REPLACEMENT OF BRAIDED CLOTH WIRING; INSTALLATION OF CCTV SYSTEM & RELATED WIRING; HOOKUP TO TELEMETERING SYSTEM; REPLACEMENT OF SWITCHGEARS & CONTROLS | 2022 | 16807 | 19523.49 | 150 | 214 | 0 | 0 | 0 | 0 | 19887.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293EV | 851 GRAND CONCOURSE - ELEVATORS | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 101 | CO-0293 |  |  | 851 GRAND CONCOURSE - ELEVATORS | 2022 | 13000 | 0 | 4000 | 0 | 0 | 36000 | 12000 | 0 | 52000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO293HO | 851 GRAND CONCOURSE - HOUSING COURT RELOCATION | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 104 | CO-0264 |  |  | INTERIOR BUILDOUT | 2022 | 19684 | 1170.74 | 0 | 17171 | 0 | 0 | 0 | 0 | 18341.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BACK | DASNY - 215 E. 161ST ST.- BACKFILL | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 104 | CO-0294 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 215 E. 161ST ST. BRONX, NY | EXTENSIVE INTERIOR RENOVATIONS; INITIAL OUTFITTING; VOICE & DATA CABLING | 2022 | 63456 | 1857.04 | 445 | 0 | 0 | 0 | 3758 | 0 | 6060.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294BOIL | 215 EAST161ST STREET- REPLACEMENT OF BOILER | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 104 | CO-0294 |  |  | 215 EAST161ST STREET- REPLACEMENT OF BOILER | 2022 | 3523 | 402.9 | 0 | 0 | 460 | 0 | 2600 | 0 | 3462.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO294ELEC | 215 E. 161ST ST.- ELECTRICAL UPGRADE | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 104 | CO-0294 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN | 215 E. 161ST ST. BRONX, NY 10451 | REPLACEMENT OF BUSSES, CONTROLS & SWITCHES; RELATED WIRING | 2022 | 21612 | 18420.38 | 98 | 0 | 0 | 0 | 0 | 0 | 18518.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295FIRE | 1118 GRAND CONCOURSE - FIRE ALARM UPGRADE | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 101 | CO-0295 |  |  | 1118 GRAND CONCOURSE - FIRE ALARM DESIGN & REPLACEMENT | 2022 | 5815 | 0 | 0 | 534 | 0 | 0 | 0 | 5181 | 5715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | CO295ROOF | 1118 GRAND CONCOURSE - ROOF | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 101 | CO-0295 |  |  | 1118 GRAND CONCOURSE -ROOF | 2022 | 172 | 0 | 0 | 195 | 0 | 1560 | 0 | 0 | 1755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | COD294CBG | BRONX CENTRAL BOOKING /BRONX COURT SECTION - FITNESS CENTER | RECONSTRUCTION/RENOVATION OF COURT FACILITIES | 101 | CO-D294 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | SQ/IA | 2022 | 50 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | DAVIDCC | DAVIDSON COMMUNITY CENTER GYM | MISCELLANEOUS CONSTRUCTION | 103 | PW-D005 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DAVIDSON COMMUNITY CENTER GYM | 2022 | 750 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E10-00004 | DCLA - 09-013; WCS - Bronx Zoo; 2300 Southern Boulevard | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 106 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ENERGY EFFICIENCY UPGRADE AT WCS - BRONX ZOO; 2300 SOUTHERN BOULEVARD | 2022 | 16885 | 16827.97 | 2661 | 0 | 0 | 0 | 0 | 0 | 19488.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E14-0002 | DCAS - BRONX COUNTY COURT COMP ENERGY UPGRADE | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 100 104 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | ENERGY UPGRADE | 2022 | 6179 | 5759.53 | 100 | 0 | 399 | 0 | 0 | 0 | 6258.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0002 | NYPD - Comprehensive Lighting Upgrades at 20 NYPD Facilities | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 101 | PU-0025 |  |  | COMPREHENSIVE LIGHTING UPGRADES AT 20 NYPD FACILITIES | 2022 | 3744 | 0 | 0 | 5635 | 0 | 0 | 0 | 0 | 5635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | E21-0006 | NYPL Bronx Library | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 101 | PU-0025 |  |  | NYPL BRONX LIBRARY | 2022 | 5031 | 0 | 0 | 5031 | 0 | 0 | 0 | 0 | 5031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0042 | CUNY - Bronx Community College Campus: Polowczyk Hall | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 101 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CUNY - BRONX COMMUNITY COLLEGE CAMPUS: POLOWCZYK HALL | 2022 | 300 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0043 | CUNY - Bronx Community College Campus: Colston Hall | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 101 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CUNY - BRONX COMMUNITY COLLEGE CAMPUS: COLSTON HALL | 2022 | 375 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0044 | CUNY - Bronx Community College Campus: Loew Hall | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 101 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CUNY - BRONX COMMUNITY COLLEGE CAMPUS: LOEW HALL | 2022 | 375 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0045 | CUNY - Bronx Community College Campus: Nichols Hall | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 101 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CUNY - BRONX COMMUNITY COLLEGE CAMPUS: NICHOLS HALL | 2022 | 375 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0064 | NYPD - 52nd Precinct | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 101 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | 52ND PRECINCT | 2022 | 300 | 0 | 256 | 0 | 0 | 0 | 0 | 0 | 256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0080 | DHS - FRANKLIN WOMEN'S SHELTER | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 101 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | IA/SQ | 2022 | 500 | 0 | 403 | 0 | 0 | 0 | 0 | 0 | 403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | EO26-0089 | DPR - BRONX PARKS HEADQUARTERS AND SHOPS | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 101 | PU-0025 | PROJECT DELAYED DUE TO CHANGES IN SCOPE/DESIGN |  | IA/SQ | 2022 | 500 | 0 | 229 | 0 | 0 | 0 | 0 | 0 | 229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | NDF-DAVID | NDF - DAVIDSON AVE COMMUNITY CENTER | NEIGHBORHOOD REVITALIZATION | 105 | ED-0384 |  |  | BLDG CONS | 2022 | 1875 | 0 | 1125 | 2429 | 0 | 0 | 0 | 0 | 3554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW293198X | 198 E 161ST STREET - FIRE ALARM UPGRADE | LEGAL MANDATES AND CORRECTION OF UNSAFE CONDITIONS | 101 | PW-0293 |  |  | 198 E 161ST STREET - FIRE ALARM DESIGN | 2022 | 4655 | 0 | 0 | 846 | 0 | 12107 | 0 | 0 | 12953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW326TOR2 | LAW DEPT TORTS - 260 EAST 161ST BRONX | RENOVATION OF LEASED SPACE | 101 | PW-0326 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | LAW DEPT TORTS - 260 EAST 161ST BRONX | 2022 | 7023 | 2672.8 | 0 | 0 | 0 | 0 | 0 | 3589 | 6261.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198EV | 198 E 161 ST - ELEVATOR ,MODERNIZATION | REHABILITATION OF CITY-OWNED OFFICE SPACE | 101 | PW-0077 |  |  | IA/SQ | 2022 | 16306 | 0 | 867 | 1156 | 13877 | 0 | 0 | 0 | 15900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77198PD | 198 E 161st Street - DCAS Police Command Center | REHABILITATION OF CITY-OWNED OFFICE SPACE |  | PW-0077 |  |  | SQ/IA | 2022 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW772076 | 1932 ARTHUR AVE.- 7th FLOOR BUILDOUT | REHABILITATION OF CITY-OWNED OFFICE SPACE | 106 | PW-0077 |  |  | $490 PER SQ FT | 2022 | 9200 | 0 | 0 | 764 | 0 | 0 | 7600 | 0 | 8364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207DC | 1932 ARTHUR AVENUE RENOVATION - 5TH FLOOR - DOB | REHABILITATION OF CITY-OWNED OFFICE SPACE | 101 | PW-0077 |  |  | SQ/IA | 2022 | 6716 | 0 | 0 | 550 | 0 | 0 | 6166 | 0 | 6716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207EL | 1932 ARTHUR AVE.- ELECTRICAL UPGRADES | REHABILITATION OF CITY-OWNED OFFICE SPACE | 101 | PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | 1932 ARTHUR AVE.- ELECTRICAL UPGRADES | 2022 | 3510 | 0 | 0 | 688 | 0 | 0 | 8261 | 0 | 8949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207HV | 1932 ARTHUR AVE - CENTRAL HVAC SYSTEM | REHABILITATION OF CITY-OWNED OFFICE SPACE | 101 | PW-0077 |  |  | IA/SQ | 2022 | 26000 | 0 | 0 | 2000 | 0 | 0 | 24000 | 0 | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207RF | 1932 ARTHUR AVE.- ROOF | REHABILITATION OF CITY-OWNED OFFICE SPACE | 106 | PW-0077 |  | 1932 ARTHUR AVE BRONX | RECONSTRUCT ROOF | 2022 | 1482 | 0 | 0 | 123 | 0 | 0 | 1225 | 0 | 1348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207TU | 1932 ARTHUR AVENUE- CODE COMPLIANT TOILET UPGRADES | REHABILITATION OF CITY-OWNED OFFICE SPACE | 101 | PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | CODE COMPLIANT TOILET UPGRADES | 2022 | 1550 | 0 | 0 | 150 | 0 | 0 | 1400 | 0 | 1550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77207W | 1932 ARTHUR AVE.- WINDOWS AND FACADE | REHABILITATION OF CITY-OWNED OFFICE SPACE | 101 | PW-0077 |  |  | 1932 ARTHUR AVE - WINDOWS AND FACADE | 2022 | 7995 | 0 | 0 | 662 | 0 | 0 | 6606 | 0 | 7268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77208EL | 4101 WHITE PLAINS RD. - ELECTRICAL & FA UPGRADE | REHABILITATION OF CITY-OWNED OFFICE SPACE | 101 | PW-0077 |  |  | NEIGHBORHOOD GOVERNMENT BUILDING - ELECTRICAL & FA UPGRADE | 2022 | 1901 | 0 | 0 | 208 | 0 | 0 | 1667 | 0 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77208RF | 4101 White Plains Rd Roof | REHABILITATION OF CITY-OWNED OFFICE SPACE | 101 | PW-0077 |  |  | SQ/IA | 2022 | 950 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77CTCX4 | 2556 BAINBRIDGE AVE- CIVIL SERVICE EXAM TESTING CENTER | REHABILITATION OF CITY-OWNED OFFICE SPACE | 101 | PW-0077 |  |  | 2556 BAINBRIDGE AVE- CIVIL SERVICE EXAM TESTING CENTER | 2022 | 18675 | 0 | 0 | 0 | 0 | 2000 | 0 | 28201 | 30201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PW77X215 | 215 E161 ST.- OFFICE RENOVATIONS | REHABILITATION OF CITY-OWNED OFFICE SPACE | 101 | PW-0077 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | COMPLAINT PROCESSING AREA RELOCATION TO 4TH FLR ANNEX. | 2022 | 628 | 0 | 0 | 0 | 0 | 2494 | 0 | 0 | 2494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA1 | 2556 Bainbridge Ave. Community Ctr. | REHABILITATION OF CITY-OWNED OFFICE SPACE | 102 | PW-D005 |  |  | 2556 BAINBRIDGE AVE. COMMUNITY CTR. | 2022 | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWD5BA2 | 2556 Bainbridge Ave - Fordham Library renovation | REHABILITATION OF CITY-OWNED OFFICE SPACE | 102 | PW-D005 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DCAS - OLD FORDHAM LIBRARY RENOVATION -- FUNDS WILL GO TO DCAS TO RENOVATE THE OLD FORDHAM LIBRARY. | 2022 | 1128 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | PWXDAVDCC | DCAS/DAVIDSON COMMUNITY CENTER - CONSTRUCT 2 ADDITIONAL FLOO | MISCELLANEOUS CONSTRUCTION | 103 | PW-X078 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DCAS/DAVIDSON COMMUNITY CENTER - CONSTRUCT 2 ADDITIONAL FLOORS & ELEVATOR, FY20 EXE SECTION 211 ADD @$500K | 2022 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-365 | DSNY - 125 E 149TH ST, BX - MN WEST 9 GARAGE LEASE RENEWAL | GARAGES AND FACILITIES | 101 | S-0136 |  |  | SQ/IA | 2022 | 1038 | 0 | 0 | 0 | 1038 | 0 | 0 | 0 | 1038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | S136-434 | DSNY - 720-780 E132 St - Bronx 1 3 4 Garage Rehab | GARAGES AND FACILITIES | 101 | S-0136 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | REHABILITATION | 2022 | 3214 | 0 | 0 | 8460 | 0 | 0 | 0 | 0 | 8460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARDOS5 | DSNY - PV Installation on Garage - Bronx 9/10/11 | DISTRIBUTED GENERATION | 101 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DSNY - PV INSTALLATION ON GARAGE - BRONX | 2022 | 4016 | 0 | 0 | 0 | 0 | 0 | 3716 | 0 | 3716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | SOLARPQL2 | DCAS PQL Round 2 (EdEn) | BUILDING CONSTRUCTION, RECONSTRUCTION OR RETROFIT | 101 | PU-0025 | PROJECT DELAYED DUE TO BUDGETARY CONSTRAINTS |  | DCAS PQL ROUND 2 (EDEN) | 2022 | 4300 | 0 | 0 | 4300 | 0 | 0 | 0 | 0 | 4300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20220309 | BRONX | 856 | DEPT OF CITYWIDE ADMIN SERVS | TKYHHC911 | HHC - Morrisania Comprehensive Energy Upgrades | MISCELLANEOUS ENERGY EFFICIENCY AND SUSTAINABILITY | 101 | PU-0025 |  |  | MORRISANIA COMPREHENSIVE ENERGY UPGRADES | 2022 | 10691 | 0 | 0 | 600 | 10091 | 0 | 0 | 0 | 10691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0